## Sheet1
Activity ID | Activity Name | Original Duration | Remaining Duration | Baseline Start | Baseline Finish | Start | Finish | Total Float
EPC FOR PKG 3 SALES GAS PIPELINE NETWORK ENHANCEMENT PROJECT-Rev.1 25-Oct-24 Update |  | 921 | 440 | 2023-07-03 | 2026-01-09 | 03-Jul-23 A | 2026-01-09 | 0
Milestones |  | 921 | 439 | 2023-07-03 | 2026-01-09 | 03-Jul-23 A | 2026-01-09 | 0
ML1000 | Award / Project Start | 0 | 0 | 2023-07-03 |  | 03-Jul-23 A
PRJ-MI-1000 | Project Commencement Date (Effective) | 0 | 0 |  | 2023-07-09 |  | 09-Jul-23 A
ML1001 | Project Effective Date | 0 | 0 | 2023-07-10 |  | 10-Jul-23 A
ML1002 | Project Kick off Meeting | 0 | 0 | 2023-07-19 |  | 19-Jul-23 A
ML1509-D3 | Receive at Site - Coated / Painted Line pipes- 52" (50% to total Qty) | 0 | 0 |  | 2024-11-05 |  | 13-Sep-24 A
ML1070 | Complete 25% Construction & Pre-commissioning | 0 | 0 |  | 2024-12-14 |  | 2024-12-14 | 23
ML1052-D1 | Receive at Site - Coated / Painted Line pipes- 56" | 0 | 0 |  | 2025-01-12 |  | 2025-01-12 | 76
ML1389-D2 | Receive at Site - Coated / Painted Line pipes- 4" (Nitrogen & Water line) | 0 | 0 |  | 2025-02-19 |  | 2025-02-19 | 38
ML1080 | Complete 50% Construction & Pre-commissioning | 0 | 0 |  | 2025-03-26 |  | 2025-03-26 | 23
ML1399-D5 | Receive at Site - Coated / Painted Line pipes- 52" (100% to total Qty) | 0 | 0 |  | 2025-03-26 |  | 2025-03-26 | 24
ML1090 | Complete 75% Construction & Pre-commissioning | 0 | 0 |  | 2025-07-30 |  | 2025-07-30 | 23
ML1020 | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | 0 | 0 |  | 2025-10-09 |  | 2025-10-09 | 31
ML1100 | Complete 100% Construction & Pre-commissioning | 0 | 0 |  | 2025-11-03 |  | 2025-11-03 | 17
ML1030 | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | 0 | 0 |  | 2025-11-09 |  | 2025-11-09 | 0
ML1040 | Achieve PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | 0 | 0 |  | 2025-12-09 |  | 2025-12-09 | 17
ML1050 | Achieve PAC-2 for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | 0 | 0 |  | 2026-01-09 |  | 2026-01-09 | 0
ML1060 | Project Finish | 0 | 0 |  | 2026-01-09 |  | 2026-01-09 | 0
General |  | 312 | 0 | 2023-10-20 | 2024-11-15 | 20-Oct-23 A | 2025-01-20 | 108
ML1002-A02 | Issue Project Control, PMS and Planning Dossier covering Baseline Schedule, Histograms, S-Curves, etc. - Final Issue | 0 | 0 |  | 2023-10-20 |  | 20-Oct-23 A
ML1011-A05 | Obtain Final Route Approval from Authorities | 0 | 0 |  | 2024-09-27 |  | 28-Feb-24 A
ML1159-A08 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (4" Nitrogen Pipeline) | 0 | 0 |  | 2024-10-28 |  | 15-Mar-24 A
ML1169-A09 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (4" Water line) | 0 | 0 |  | 2024-10-04 |  | 15-Mar-24 A
ML1003-A03 | Issue Construction Execution Plan/ Procedures/ Method Statements along with Procedures & Philosophies-Final Issue | 0 | 0 |  | 2024-10-28 |  | 22-Mar-24 A
ML1001-A01 | Issue Project Execution Plan (PEP), Coordination, Engineering, Procurement, HSE and Quality Procedures-Final Issue | 0 | 0 |  | 2024-04-13 |  | 13-Apr-24 A
ML1139-A06 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (56" Pipeline) | 0 | 0 |  | 2024-11-15 |  | 28-Aug-24 A
ML1149-A07 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | 0 | 0 |  | 2024-09-27 |  | 28-Aug-24 A
ML1004-A04 | Issue cleaning & gauging, hydrotesting , Drying, Purging, Pre-commissioning and commissioning Procedure (Final Issue) | 0 | 0 |  | 2024-10-28 |  | 2025-01-20 | 108
Detail Engineering |  | 337 | 50 | 2023-09-05 | 2024-12-24 | 05-Sep-23 A | 2025-01-08 | 219
ML1007-B02 | Award Subcontracts for Topographical Survey/ Geotechnical Investigation Studies | 0 | 0 |  | 2023-09-05 |  | 05-Sep-23 A
ML1021-B15 | Issue MR (Final) - Line pipes | 0 | 0 |  | 2023-09-21 |  | 21-Sep-23 A
ML1012-B06 | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | 0 | 0 |  | 2023-11-22 |  | 22-Nov-23 A
ML1189-B16 | Issue MR (Final) - Hot Bends | 0 | 0 |  | 2023-11-23 |  | 23-Nov-23 A
ML2059-B05 | 30% Model Review | 0 | 0 |  | 2023-11-28 |  | 28-Nov-23 A
ML1010-B14 | Issue Tie-in Philosophy for all new facilities - IFC | 0 | 0 |  | 2024-07-29 |  | 29-Nov-23 A
ML1013-B07 | Complete HAZOP/ SIL/ LOPA Review as applicable and Submit final Report after incorporating Company comments (IFA) | 0 | 0 |  | 2024-07-29 |  | 26-Feb-24 A
ML1008-B03 | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 56" Pipeline(IFC) | 0 | 0 |  | 2024-08-16 |  | 26-Feb-24 A
ML1005-B01 | Prepare Design Basis for all Engineering Disciplines and Issue to COMPANY - Final Issue | 0 | 0 |  | 2024-03-25 |  | 25-Mar-24 A
ML2069-B09 | 60% Model Review | 0 | 0 |  | 2024-03-27 |  | 27-Mar-24 A
ML1199-B24 | Issue Civil / Structural Drawings for Launcher/ Receiver facilities | 0 | 0 |  | 2024-04-06 |  | 06-Apr-24 A
ML1017-B18 | Issue MRs for All Mechanical Equipment & Packages (Final Issue) | 0 | 0 |  | 2024-04-16 |  | 16-Apr-24 A
ML1027-B17 | Issue MRs for All E&I Equipment & Packages (Final Issue) | 0 | 0 |  | 2024-04-16 |  | 16-Apr-24 A
ML1009-B04 | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 52" Pipeline(IFC) | 0 | 0 |  | 2024-08-16 |  | 06-May-24 A
ML1016-B12 | Complete HSEIA, QRA, and Gas Dispersion Studies after review / approval by Company and Submit Final Reports | 0 | 0 |  | 2024-08-05 |  | 07-May-24 A
ML2079-B13 | 90% Model Review | 0 | 0 |  | 2024-07-29 |  | 26-Jul-24 A
ML1015-B08 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | 0 | 0 |  | 2024-09-06 |  | 18-Oct-24 A
ML1014-B10 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | 0 | 0 |  | 2024-09-27 |  | 18-Oct-24 A
ML1033-B22 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | 0 | 0 |  | 2024-07-29 |  | 2024-10-28 | 158
ML1179-B11 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | 0 | 0 |  | 2024-09-27 |  | 2024-11-01 | 117
ML1031-B20 | Issue SLD, Hazardous Area Classification Details for All Areas - IFC | 0 | 0 |  | 2024-08-16 |  | 2024-11-01 | 101
ML1219-B39 | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | 0 | 0 |  | 2024-08-09 |  | 2024-11-01 | 114
ML1219-B49 | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | 0 | 0 |  | 2024-08-09 |  | 2024-11-01 | 114
ML1219-B59 | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | 0 | 0 |  | 2024-08-02 |  | 2024-11-01 | 91
ML1032-B21 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | 0 | 0 |  | 2024-09-20 |  | 2024-11-08 | 96
ML1059-B28 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | 0 | 0 |  | 2024-09-20 |  | 2024-11-15 | 104
ML1036-B23 | Issue Civil / Structural Drawings for Gas Filters, Pressure Reducing Skids and Metering Skids facilities - IFC. | 0 | 0 |  | 2024-09-20 |  | 2024-11-22 | 175
ML1035-B26 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | 0 | 0 |  | 2024-10-11 |  | 2024-12-10 | 9
ML1209-B27 | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | 0 | 0 |  | 2024-10-11 |  | 2024-12-17 | 44
ML1034-B25 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | 0 | 0 |  | 2024-09-20 |  | 2024-12-17 | 33
ML1219-B19 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | 0 | 0 |  | 2024-12-17 |  | 2024-12-31 | 77
ML1219-B29 | Completion of all Detailed Engineering | 0 | 0 |  | 2024-12-24 |  | 2025-01-08 | 56
Procurement |  | 339 | 0 | 2023-08-25 | 2025-02-12 | 25-Aug-23 A | 2024-12-31 | 111
ML1040-C01 | Issue Purchase Order (Final) - Line pipes | 0 | 0 |  | 2023-08-25 |  | 25-Aug-23 A
ML1229-C02 | Issue Purchase Order (Final) - Hot Bends | 0 | 0 |  | 2023-10-02 |  | 02-Oct-23 A
ML1041-C03 | Issue Purchase Order (Final) - Isolation Joints | 0 | 0 |  | 2023-11-23 |  | 23-Nov-23 A
ML1279-C05 | Issue Purchase Order (Final) - Pig Launcher & Receiver | 0 | 0 |  | 2023-12-21 |  | 21-Dec-23 A
ML1259-C09 | Issue Purchase Order (Final) - Sales Gas Metering Skids | 0 | 0 |  | 2024-02-16 |  | 16-Feb-24 A
ML1039-C08 | Issue Purchase Order (Final) - Pressure Reduction Skids | 0 | 0 |  | 2024-02-23 |  | 23-Feb-24 A
ML1319-C16 | Issue Purchase Order (Final) - AC UPS System | 0 | 0 |  | 2024-03-26 |  | 26-Mar-24 A
ML1022-C07 | Issue Purchase Order (Final) - MOV/ROV/GOV Valves | 0 | 0 |  | 2024-03-27 |  | 27-Mar-24 A
ML1289-C11 | Issue Purchase Order (Final) - Leak Detection System | 0 | 0 |  | 2024-03-28 |  | 28-Mar-24 A
ML1369-C21 | Issue Purchase Order (Final) - Valves – Globe/Check/Plug | 0 | 0 |  | 2024-03-29 |  | 29-Mar-24 A
ML1043-C14 | Issue Purchase Order (Final) - Manual Ball Valves | 0 | 0 |  | 2024-04-04 |  | 04-Apr-24 A
ML1239-C04 | Issue Purchase Order (Final) - Barred Tee | 0 | 0 |  | 2024-04-25 |  | 25-Apr-24 A
ML1329-C17 | Issue Purchase Order (Final) - Fiber Optic Cable | 0 | 0 |  | 2024-04-26 |  | 26-Apr-24 A
ML1038-C10 | Issue Purchase Order (Final) - CP System | 0 | 0 |  | 2024-05-20 |  | 20-May-24 A
ML1339-C18 | Issue Purchase Order (Final) - IDS & PIDS System | 0 | 0 |  | 2024-06-07 |  | 07-Jun-24 A
ML1028-C20 | Issue Purchase Order (Final) - CCTV Systems | 0 | 0 |  | 2024-06-07 |  | 07-Jun-24 A
ML1349-C19 | Issue Purchase Order (Final) - RTUs | 0 | 0 |  | 2024-06-10 |  | 10-Jun-24 A
ML1309-C15 | Issue Purchase Order (Final) - Passive Cooling Shelters | 0 | 0 |  | 2024-06-14 |  | 14-Jun-24 A
ML1026-C13 | Issue Purchase Order (Final) - Solar Power System | 0 | 0 |  | 2024-06-14 |  | 14-Jun-24 A
ML1269-C12 | Issue Purchase Order (Final) - F & G System | 0 | 0 |  | 2024-07-29 |  | 24-Jun-24 A
ML1249-C06 | Issue Purchase Order (Final) - Anchor Flanges | 0 | 0 |  | 2024-07-01 |  | 01-Jul-24 A
ML1038-C20 | Completion of Procurement Services | 0 | 0 |  | 2025-02-12 |  | 2024-12-31 | 61
Manufacturing & Delivery |  | 354 | 307 | 2024-09-26 | 2025-11-02 | 25-Oct-24 A | 2025-10-14 | 86
ML1057-D19 | Receive at Site - Fiber Optic Cable | 0 | 0 |  | 2024-11-01 |  | 25-Oct-24 A
ML1449-D11 | Receive at Site - Hot Bends for 52" Pipeline (50% to total Qty) | 0 | 0 |  | 2024-09-26 |  | 2024-12-11 | 195
ML1439-D10 | Receive at Site - Hot Bends for 56" Pipeline | 0 | 0 |  | 2024-09-26 |  | 2024-12-22 | 127
ML1459-D12 | Receive at Site - Hot Bends for 52" Pipeline (100% to total Qty) | 0 | 0 |  | 2024-12-24 |  | 2025-01-26 | 60
ML1519-D04 | Receive at Site - Pig Launcher & Receiver | 0 | 0 |  | 2025-03-12 |  | 2025-03-12 | 105
ML1529-D20 | Receive at Site - Valves – Globe/Check/Plug | 0 | 0 |  | 2025-02-16 |  | 2025-03-13 | 190
ML1539-D21 | Receive at Site - Manual Valves | 0 | 0 |  | 2025-02-16 |  | 2025-03-13 | 137
ML1053-D23 | Receive at Site - Leak Detection System | 0 | 0 |  | 2025-05-06 |  | 2025-03-27 | 155
ML1499-D18 | Receive at Site - UPS System | 0 | 0 |  | 2025-05-06 |  | 2025-03-27 | 155
ML2089-D16 | Receive at Site - F & G System | 0 | 0 |  | 2025-04-03 |  | 2025-04-03 | 119
ML1549-D22 | Receive at Site - Cathodic Protection (CP) System | 0 | 0 |  | 2024-12-24 |  | 2025-04-03 | 125
ML1054-D09 | Receive at Site - Passive Cooling Shelter | 0 | 0 |  | 2025-02-16 |  | 2025-04-25 | 90
ML1429-D17 | Receive at Site - Solar Power System | 0 | 0 |  | 2025-04-24 |  | 2025-04-25 | 97
ML1409-D24 | Receive at Site - Isolation Joints, Barred Tee, and Anchor Flanges | 0 | 0 |  | 2025-05-09 |  | 2025-05-09 | 126
ML1419-D08 | Receive at Site - Sales Gas Metering Skids | 0 | 0 |  | 2025-05-11 |  | 2025-05-11 | 151
ML1479-D15 | Receive at Site - E&I Equipment's (IDS & PIDS System) | 0 | 0 |  | 2025-05-27 |  | 2025-05-27 | 103
ML1056-D14 | Receive at Site - E&I Equipment's (CCTV System) | 0 | 0 |  | 2025-05-27 |  | 2025-05-27 | 103
ML1051-D07 | Receive at Site - Pressure Reduction Skids | 0 | 0 |  | 2025-05-28 |  | 2025-05-28 | 100
ML1024-D06 | Receive at Site - MOV/ROV/GOV Valves | 0 | 0 |  | 2025-06-30 |  | 2025-07-23 | 169
ML1469-D13 | Receive at Site - E&I Equipment's (RTUs) | 0 | 0 |  | 2025-06-30 |  | 2025-07-23 | 169
ML1549-D32 | Complete Delivery to Site | 0 | 0 |  | 2025-11-02 |  | 2025-10-14 | 25
Construction & Pre-Commissioning |  | 669 | 439 | 2024-03-11 | 2026-01-09 | 11-Mar-24 A | 2026-01-09 | 0
ML1559-E01 | Mobilization of Automatic Welding Machines at site | 0 | 0 | 2024-03-11 |  | 11-Mar-24 A
ML1689-E14 | Complete Pipeline welding - 52" Sales Gas Pipeline - 25% Welding | 0 | 0 |  | 2025-01-23 |  | 18-Oct-24 A
ML1659-E11 | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -HGCP to BVS-3 | 0 | 0 |  | 2024-10-29 |  | 2024-10-27 | 57
ML1569-E02 | Complete Site Grading & ROW along the Pipeline - 56" Sales Gas Pipeline | 0 | 0 |  | 2024-12-20 |  | 2024-12-08 | 128
ML1699-E15 | Complete Pipeline welding - 52" Sales Gas Pipeline - 50% Welding | 0 | 0 |  | 2025-03-23 |  | 2025-01-09 | 99
ML1869-E32 | Complete Site Grading & ROW along the Pipeline - 4" Water line | 0 | 0 |  | 2024-12-22 |  | 2025-01-30 | 105
ML1589-E04 | Complete Pipeline welding - 56" Sales Gas Pipeline (50% Welding) | 0 | 0 |  | 2025-01-29 |  | 2025-03-05 | 16
ML1879-E33 | Complete Pipeline Jointing - 4" Waterline | 0 | 0 |  | 2025-01-29 |  | 2025-03-11 | 76
ML1709-E16 | Complete Pipeline welding - 52" Sales Gas Pipeline - 75% Welding | 0 | 0 |  | 2025-05-27 |  | 2025-03-13 | 99
ML1779-E23 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 02 to BVS-03 | 0 | 0 |  | 2025-10-08 |  | 2025-04-03 | 117
ML1669-E12 | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -BVS-3 to Sweihan CRS | 0 | 0 |  | 2025-02-06 |  | 2025-04-10 | 36
ML1889-E34 | Complete Hydrotesting - 4" Water line | 0 | 0 |  | 2025-03-03 |  | 2025-04-17 | 54
ML1939-E39 | Achieve Mechanical Completion of PL & facilities- ( 4" Water line) | 0 | 0 |  | 2025-03-03 |  | 2025-04-17 | 104
ML1839-E29 | Complete Civil works for CRS Building & equipment's foundations at Sweihan CRS | 0 | 0 |  | 2025-03-16 |  | 2025-04-22 | 148
ML1599-E05 | Complete Pipeline welding - 56" Sales Gas Pipeline (100% Welding) | 0 | 0 |  | 2025-03-23 |  | 2025-04-30 | 19
ML1769-E22 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 01 to BVS-02 | 0 | 0 |  | 2025-09-26 |  | 2025-05-14 | 144
ML1619-E07 | Complete foundations for Launchers and Receiver- 56" Sales Gas Pipeline | 0 | 0 |  | 2025-03-18 |  | 2025-05-20 | 109
ML1789-E24 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 03 to BVS-04 | 0 | 0 |  | 2025-10-20 |  | 2025-06-04 | 126
ML1909-E36 | Complete Pipeline welding - 4" Nitrogen Pipeline | 0 | 0 |  | 2025-05-19 |  | 2025-06-12 | 101
ML1609-E06 | Complete Construction of Anchor Blocks - 56" Sales Gas Pipeline | 0 | 0 |  | 2025-05-14 |  | 2025-06-15 | 90
ML1759-E21 | Complete Hydrotesting - 52" Sales Gas Pipeline -Launcher to BVS-01 | 0 | 0 |  | 2025-09-03 |  | 2025-06-16 | 107
ML1739-E19 | Complete foundations for Launchers and Receiver- 52" Sales Gas Pipeline | 0 | 0 |  | 2025-06-03 |  | 2025-07-11 | 68
ML1829-E28 | Complete Drying & Purging of all facilities including Pipeline & Block Valve Stations - 52" Sales Gas Pipeline | 0 | 0 |  | 2025-11-04 |  | 2025-07-21 | 95
ML1719-E17 | Complete Pipeline welding - 52" Sales Gas Pipeline - 100% Welding | 0 | 0 |  | 2025-08-26 |  | 2025-07-21 | 2
ML1729-E18 | Complete Construction of Anchor Blocks - 52" Sales Gas Pipeline | 0 | 0 |  | 2025-08-29 |  | 2025-07-29 | 136
ML1579-E03 | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | 0 | 0 |  | 2025-06-18 |  | 2025-08-03 | 49
ML1849-E30 | Complete Piping works at Sweihan CRS | 0 | 0 |  | 2025-07-10 |  | 2025-08-13 | 56
ML1899-E35 | Complete Pipeline Welding - 36"Jump-over line | 0 | 0 |  | 2025-09-02 |  | 2025-08-17 | 24
ML1969-E42 | Achieve Mechanical Completion of PL & facilities- ( 36"Jump over Line) | 0 | 0 |  | 2025-09-17 |  | 2025-08-21 | 116
ML1679-E13 | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | 0 | 0 |  | 2025-07-13 |  | 2025-08-24 | 60
ML1949-E40 | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | 0 | 0 |  | 2025-08-11 |  | 2025-09-07 | 103
ML1919-E37 | Complete Hydrotesting - 4" Nitrogen Pipeline | 0 | 0 |  | 2025-08-20 |  | 2025-09-14 | 33
ML1639-E09 | Complete Hydrotesting - 56" Sales Gas Pipeline | 0 | 0 |  | 2025-09-04 |  | 2025-09-17 | 29
ML1929-E38 | Complete Drying & Purging of all facilities including Pipeline - 4" Nitrogen Pipeline | 0 | 0 |  | 2025-09-01 |  | 2025-09-25 | 87
ML1799-E25 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 04 to BVS-05 | 0 | 0 |  | 2025-11-02 |  | 2025-10-03 | 32
ML1809-E26 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 05 to BVS-06 | 0 | 0 |  | 2025-10-23 |  | 2025-10-05 | 26
ML1629-E08 | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | 0 | 0 |  | 2025-10-01 |  | 2025-10-09 | 75
ML1649-E10 | Complete Drying & Purging of all facilities including Pipeline & Block Valve Stations- 56" Sales Gas Pipeline | 0 | 0 |  | 2025-10-09 |  | 2025-10-09 | 75
ML1959-E41 | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | 0 | 0 |  | 2025-10-09 |  | 2025-10-09 | 31
ML1020 (Internal) | Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | 0 | 0 |  | 2025-10-09 |  | 2025-10-11 | 9
ML1819-E27 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 06 to Sweihan Receiver | 0 | 0 |  | 2025-10-26 |  | 2025-10-31 | 2
ML1859-E31 | Complete E&I Installation Works - Sweihan CRS | 0 | 0 |  | 2025-11-02 |  | 2025-11-03 | 54
ML1749-E20 | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | 0 | 0 |  | 2025-11-03 |  | 2025-11-03 | 53
ML1979-E43 | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | 0 | 0 |  | 2025-11-04 |  | 2025-11-04 | 0
ML1030 (Internal) | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | 0 | 0 |  | 2025-11-09 |  | 2025-11-09 | 10
ML1989-E44 | Complete As-Built drawings including Project close out report and submit to COMPANY | 0 | 0 |  | 2026-01-09 |  | 2026-01-09 | 0
Commissioning and PAC |  | 52 | 52 | 2025-11-10 | 2026-01-09 | 2025-11-18 | 2026-01-09 | 0
ML2019-F03 | Commission New pipelines system - 4" Nitrogen Pipeline | 0 | 0 |  | 2025-11-10 |  | 2025-11-18 | 38
ML2029-F04 | Commission New pipelines system - 4" Water line | 0 | 0 |  | 2025-11-10 |  | 2025-11-18 | 38
ML1999-F01 | Commission New pipeline system - 56" Sales Gas Pipeline | 0 | 0 |  | 2025-11-10 |  | 2025-11-18 | 38
ML2039-F05 | Achieve (PAC-1) for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | 0 | 0 |  | 2025-12-09 |  | 2025-12-09 | 17
ML-PAC1 (Internal) | PAC 1 - 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | 0 | 0 |  | 2025-12-09 |  | 2025-12-09 | 14
ML2009-F02 | Commission New pipeline system -52" Sales Gas Pipeline | 0 | 0 |  | 2025-12-22 |  | 2025-12-13 | 27
ML-PAC2 (Internal) | PAC 2 - 52" Sales Gas Pipeline & 36"Jump-over Line | 0 | 0 |  | 2026-01-08 |  | 2026-01-05 | 4
ML2049-F06 | Achieve (PAC-2) for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | 0 | 0 |  | 2026-01-09 |  | 2026-01-09 | 0
Home Office Services |  | 498 | 174 | 2023-07-13 | 2025-06-25 | 13-Jul-23 A | 2025-07-10 | 117
General /Project Management |  | 492 | 174 | 2023-07-24 | 2025-06-25 | 24-Jul-23 A | 2025-07-10 | 106
Planning Package |  | 63 | 0 | 2023-07-31 | 2023-10-26 | 31-Jul-23 A | 26-Oct-23 A
HC-GN-0010 | Issue ICR-Planning Package | 8 | 0 | 2023-07-31 | 2023-08-10 | 31-Jul-23 A | 10-Aug-23 A
HC-GN-0020 | Receive Company Comments-Planning Package | 7 | 0 | 2023-08-06 | 2023-08-16 | 06-Aug-23 A | 16-Aug-23 A
HC-GN-0030 | Re-Issue for Approval-Planning Package | 4 | 0 | 2023-08-20 | 2023-08-25 | 20-Aug-23 A | 25-Aug-23 A
HC-GN-0040 | Obtain Company Approval-Planning Package | 5 | 0 | 2023-08-26 | 2023-09-04 | 26-Aug-23 A | 04-Sep-23 A
HC-GN-0050 | Final Issue for Design/ Construction-Planning Package | 43 | 0 | 2023-08-28 | 2023-10-26 | 28-Aug-23 A | 26-Oct-23 A
Project Procedure (PEP, Numbering Procedure) |  | 182 | 0 | 2023-07-24 | 2024-04-13 | 24-Jul-23 A | 13-Apr-24 A
HC-GN-0070 | Issue ICR-Project Procedure (PEP, Numbering Procedure etc.) | 21 | 0 | 2023-07-24 | 2023-08-22 | 24-Jul-23 A | 22-Aug-23 A
HC-GN-0080 | Receive Company Comments-Project Procedure (PEP, Numbering Procedure etc.) | 36 | 0 | 2023-08-21 | 2023-10-10 | 21-Aug-23 A | 10-Oct-23 A
HC-GN-0090 | Re-Issue for Approval-Project Procedure (PEP, Numbering Procedure etc.) | 127 | 0 | 2023-09-10 | 2024-03-08 | 10-Sep-23 A | 08-Mar-24 A
HC-GN-0100 | Obtain Company Approval-Project Procedure (PEP, Numbering Procedure etc.) | 125 | 0 | 2023-09-20 | 2024-03-17 | 20-Sep-23 A | 17-Mar-24 A
HC-GN-0110 | Final Issue for Design/ Construction-Project Procedure (PEP, Numbering Procedure) | 14 | 0 | 2024-03-18 | 2024-04-13 | 18-Mar-24 A | 13-Apr-24 A
Workshops |  | 464 | 174 | 2023-08-31 | 2025-06-25 | 31-Aug-23 A | 2025-07-10 | 31
HE-WS-0070 | Lesson Learned Workshop | 0 | 0 | 2023-08-31 | 2023-08-31 | 31-Aug-23 A | 31-Aug-23 A
HE-WS-0010 | Project Risk Review Workshop | 0 | 0 | 2023-09-28 | 2023-09-28 | 28-Sep-23 A | 28-Sep-23 A
HE-WS-0030 | Design Review Workshop | 1 | 0 | 2023-10-09 | 2023-10-10 | 09-Oct-23 A | 10-Oct-23 A
HE-WS-0090 | Plot Plan Layout Review Workshop | 1 | 0 | 2023-10-24 | 2023-10-25 | 24-Oct-23 A | 25-Oct-23 A
HE-WS-0020 | HAZID /ENVID/OHID/ PHSER Workshop | 2 | 0 | 2023-10-31 | 2023-11-02 | 31-Oct-23 A | 02-Nov-23 A
HE-WS-0210 | HAZOP Workshop | 2 | 0 | 2023-11-21 | 2023-11-23 | 21-Nov-23 A | 23-Nov-23 A
HE-WS-0190 | Bow Tie Workshop | 1 | 0 | 2023-11-23 | 2023-11-24 | 23-Nov-23 A | 24-Nov-23 A
HE-WS-0200 | ALARP Workshop | 1 | 0 | 2023-11-23 | 2023-11-24 | 23-Nov-23 A | 24-Nov-23 A
HE-WS-0310 | CRAS Workshop | 1 | 0 | 2023-11-23 | 2023-11-24 | 23-Nov-23 A | 24-Nov-23 A
HE-WS-0050 | Constructability Review Workshop | 2 | 0 | 2024-05-14 | 2024-05-16 | 14-May-24 A | 16-May-24 A
HE-WS-0170 | SIMOPS Workshop | 2 | 2 | 2024-07-29 | 2024-07-30 | 2024-10-28 | 2024-10-29 | 196
HE-WS-0270 | PHSER III Workshop | 2 | 2 | 2024-07-31 | 2024-08-01 | 2024-10-30 | 2024-10-31 | 196
HE-WS-0280 | PHSER IV Workshop | 2 | 2 | 2024-08-02 | 2024-08-05 | 2024-11-01 | 2024-11-04 | 196
HE-WS-0290 | PHSER V Workshop | 2 | 2 | 2025-06-23 | 2025-06-25 | 2025-07-08 | 2025-07-10 | 31
Smart Plant |  | 169 | 0 | 2023-08-18 | 2024-09-13 | 18-Aug-23 A | 22-Apr-24 A
HC-GN-300 | Issue ICR-Smart Plant | 124 | 0 | 2023-08-18 | 2024-08-02 | 18-Aug-23 A | 09-Feb-24 A
HC-GN-310 | Receive Company Comments-Smart Plant | 113 | 0 | 2024-08-05 | 2024-08-16 | 18-Sep-23 A | 23-Feb-24 A
HC-GN-320 | Re-Issue for Approval-Smart Plant | 84 | 0 | 2024-08-19 | 2024-08-23 | 10-Nov-23 A | 08-Mar-24 A
HC-GN-330 | Obtain Company Approval-Smart Plant | 85 | 0 | 2024-08-26 | 2024-09-06 | 22-Nov-23 A | 22-Mar-24 A
HC-GN-290 | Final Issue for Design/ Construction-Smart Plant | 85 | 0 | 2024-09-09 | 2024-09-13 | 15-Dec-23 A | 22-Apr-24 A
Quality documents |  | 179 | 0 | 2023-08-07 | 2024-04-24 | 07-Aug-23 A | 24-Apr-24 A
HC-GN-0190 | Issue ICR-QAQC procedure | 53 | 0 | 2023-08-07 | 2023-10-19 | 07-Aug-23 A | 19-Oct-23 A
HC-GN-0200 | Receive Company Comments-QAQC procedure | 11 | 0 | 2023-10-20 | 2023-11-05 | 20-Oct-23 A | 05-Nov-23 A
HC-GN-0210 | Re-Issue for Approval-QAQC procedure | 81 | 0 | 2023-11-07 | 2024-03-01 | 07-Nov-23 A | 01-Mar-24 A
HC-GN-0220 | Obtain Company Approval-QAQC procedure | 9 | 0 | 2024-03-04 | 2024-03-17 | 04-Mar-24 A | 17-Mar-24 A
HC-GN-0230 | Final Issue for Design/ Construction-Quality documents | 21 | 0 | 2024-03-18 | 2024-04-24 | 18-Mar-24 A | 24-Apr-24 A
NOC Register |  | 35 | 35 | 2024-07-29 | 2024-09-13 | 2024-10-28 | 2024-12-17 | 244
HC-GN-0250 | Issue ICR-NOC Register | 5 | 5 | 2024-07-29 | 2024-08-02 | 2024-10-28 | 2024-11-01 | 244
HC-GN-0260 | Receive Company Comments-NOC Register | 10 | 10 | 2024-08-05 | 2024-08-16 | 2024-11-04 | 2024-11-15 | 244
HC-GN-0270 | Re-Issue for Approval-NOC Register | 5 | 5 | 2024-08-19 | 2024-08-23 | 2024-11-18 | 2024-11-22 | 244
HC-GN-0280 | Obtain Company Approval-NOC Register | 10 | 10 | 2024-08-26 | 2024-09-06 | 2024-11-25 | 2024-12-10 | 244
HC-GN-0290 | Final Issue for Design/ Construction-NOC Register | 5 | 5 | 2024-09-09 | 2024-09-13 | 2024-12-11 | 2024-12-17 | 244
Hot Tap Scope of Work |  | 103 | 0 | 2023-11-01 | 2024-03-29 | 01-Nov-23 A | 29-Mar-24 A
HC-GN-340 | Issue ICR-Hot Tap SOW | 7 | 0 | 2023-11-01 | 2023-11-10 | 01-Nov-23 A | 10-Nov-23 A
HC-GN-350 | Receive Company Comments-Hot Tap SOW | 7 | 0 | 2023-11-13 | 2023-11-22 | 13-Nov-23 A | 22-Nov-23 A
HC-GN-360 | Re-Issue for Approval-Hot Tap SOW | 74 | 0 | 2023-11-23 | 2024-03-08 | 23-Nov-23 A | 08-Mar-24 A
HC-GN-370 | Obtain Company Approval-Hot Tap SOW | 9 | 0 | 2024-03-10 | 2024-03-25 | 10-Mar-24 A | 25-Mar-24 A
HC-GN-380 | Final Issue for Design/ Construction-Hot Tap SOW | 2 | 0 | 2024-03-26 | 2024-03-29 | 26-Mar-24 A | 29-Mar-24 A
Detailed Engineering |  | 368 | 50 | 2023-07-23 | 2024-12-24 | 23-Jul-23 A | 2025-01-08 | 240
Survey & Studies |  | 340 | 40 | 2023-08-17 | 2024-09-27 | 17-Aug-23 A | 2024-12-24 | 229
HE-SS-0010 | Data Acquisition | 24 | 0 | 2023-08-17 | 2023-09-20 | 17-Aug-23 A | 20-Sep-23 A
HE-SS-0020 | Site Visit | 27 | 0 | 2023-08-22 | 2023-09-28 | 22-Aug-23 A | 28-Sep-23 A
HE-SS-0040 | Geo Technical Survey | 46 | 0 | 2023-11-15 | 2024-01-22 | 15-Nov-23 A | 22-Jan-24 A
HE-SS-0030 | Topographical Survey | 112 | 0 | 2023-09-15 | 2024-02-22 | 15-Sep-23 A | 22-Feb-24 A
Site Visit Report |  | 244 | 5 | 2023-11-10 | 2024-09-27 | 10-Nov-23 A | 2024-11-01 | 101
HE-SV-0010 | Issue ICR - Site Visit /Survey Report | 29 | 0 | 2023-11-10 | 2024-08-02 | 10-Nov-23 A | 21-Dec-23 A
HE-SV-0020 | Receive Company Comments- - Site Visit /Survey Report | 62 | 0 | 2023-11-13 | 2024-08-16 | 13-Nov-23 A | 08-Feb-24 A
HE-SV-0030 | Re-Issue for Approval - Site Visit /Survey Report | 13 | 0 | 2024-08-26 | 2024-08-30 | 31-May-24 A | 21-Jun-24 A
HE-SV-0040 | Obtain Company Approval - Site Visit /Survey Report | 43 | 0 | 2024-09-09 | 2024-09-13 | 22-Jun-24 A | 22-Aug-24 A
HE-SV-0050 | Final Issue for Design/ Construction-Site Visit Report | 52 | 5 | 2024-09-23 | 2024-09-27 | 22-Aug-24 A | 2024-11-01 | 101
Project Risk Review Register |  | 35 | 0 | 2023-09-27 | 2023-11-15 | 27-Sep-23 A | 15-Nov-23 A
HE-RR-0010 | Issue ICR- Project Risk review register | 1 | 0 | 2023-09-27 | 2023-09-28 | 27-Sep-23 A | 28-Sep-23 A
HE-RR-0020 | Receive Company Comments-Project Risk review register | 2 | 0 | 2023-09-29 | 2023-10-03 | 29-Sep-23 A | 03-Oct-23 A
HE-RR-0030 | Re-Issue for Approval-Project Risk review register | 11 | 0 | 2023-10-04 | 2023-10-19 | 04-Oct-23 A | 19-Oct-23 A
HE-RR-0040 | Obtain Company Approval-Project Risk review register | 7 | 0 | 2023-10-20 | 2023-10-31 | 20-Oct-23 A | 31-Oct-23 A
HE-RR-0050 | Final Issue for Design/ Construction-Project Risk Review Register | 9 | 0 | 2023-11-02 | 2023-11-15 | 02-Nov-23 A | 15-Nov-23 A
Topographical Survey Report |  | 145 | 0 | 2024-01-29 | 2024-08-16 | 29-Jan-24 A | 30-Aug-24 A
HE-TS-0010 | Issue ICR-Topographical Survey Report (Overall) | 23 | 0 | 2024-01-29 | 2024-02-29 | 29-Jan-24 A | 29-Feb-24 A
HE-TS-0020 | Receive Company Comments-Topographical Survey Report (Overall) | 4 | 0 | 2024-03-01 | 2024-03-07 | 01-Mar-24 A | 07-Mar-24 A
HE-TS-0030 | Re-Issue for Approval-Topographical Survey Report (Overall) | 54 | 0 | 2024-03-08 | 2024-08-02 | 08-Mar-24 A | 31-May-24 A
HE-TS-0040 | Obtain Company Approval-Topographical Survey Report (Overall) | 36 | 0 | 2024-08-05 | 2024-08-09 | 03-Jun-24 A | 26-Jul-24 A
HE-TS-0050 | Final Issue for Design/ Construction-Topographical Survey Report (Overall) | 24 | 0 | 2024-08-12 | 2024-08-16 | 29-Jul-24 A | 30-Aug-24 A
Topographical Survey Report 52" Line |  | 125 | 0 | 2024-02-26 | 2024-08-02 | 26-Feb-24 A | 30-Aug-24 A
HE-TS-280 | Issue ICR-Topographical Survey Report 52" Line | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-TS-290 | Receive Company Comments-Topographical Survey Report 52" Line | 4 | 0 | 2024-03-10 | 2024-03-17 | 10-Mar-24 A | 17-Mar-24 A
HE-TS-250 | Re-Issue for Approval-Topographical Survey Report 52" Line | 49 | 0 | 2024-03-18 | 2024-08-02 | 18-Mar-24 A | 31-May-24 A
HE-TS-260 | Obtain Company Approval-Topographical Survey Report 52" Line | 72 | 0 | 2024-04-12 | 2024-08-02 | 12-Apr-24 A | 26-Jul-24 A
HE-TS-270 | Final Issue for Design/ Construction-Topographical Survey Report 52" Line | 92 | 0 | 2024-04-19 | 2024-08-02 | 19-Apr-24 A | 30-Aug-24 A
Topographical Survey Report 56" Line |  | 120 | 0 | 2024-03-04 | 2024-08-16 | 04-Mar-24 A | 30-Aug-24 A
HE-TS-230 | Issue ICR-Topographical Survey Report 56" Line | 4 | 0 | 2024-03-04 | 2024-03-08 | 04-Mar-24 A | 08-Mar-24 A
HE-TS-240 | Receive Company Comments-Topographical Survey Report 56" Line | 4 | 0 | 2024-03-10 | 2024-03-17 | 10-Mar-24 A | 17-Mar-24 A
HE-TS-200 | Re-Issue for Approval-Topographical Survey Report 56" Line | 49 | 0 | 2024-03-18 | 2024-08-02 | 18-Mar-24 A | 31-May-24 A
HE-TS-210 | Obtain Company Approval-Topographical Survey Report 56" Line | 36 | 0 | 2024-08-05 | 2024-08-09 | 03-Jun-24 A | 26-Jul-24 A
HE-TS-220 | Final Issue for Design/ Construction-Topographical Survey Report 56" Line | 25 | 0 | 2024-08-12 | 2024-08-16 | 29-Jul-24 A | 30-Aug-24 A
Topographical Survey Report 4" Line |  | 120 | 0 | 2024-03-04 | 2024-08-02 | 04-Mar-24 A | 30-Aug-24 A
HE-TS-330 | Issue ICR-Topographical Survey Report 4" Line | 4 | 0 | 2024-03-04 | 2024-03-08 | 04-Mar-24 A | 08-Mar-24 A
HE-TS-340 | Receive Company Comments-Topographical Survey Report 4" Line | 4 | 0 | 2024-03-10 | 2024-03-17 | 10-Mar-24 A | 17-Mar-24 A
HE-TS-310 | Obtain Company Approval-Topographical Survey Report 4" Line | 2 | 0 | 2024-05-10 | 2024-05-14 | 10-May-24 A | 14-May-24 A
HE-TS-320 | Final Issue for Design/ Construction-Topographical Survey Report 4" Line | 5 | 0 | 2024-05-20 | 2024-05-26 | 20-May-24 A | 26-May-24 A
HE-TS-300 | Re-Issue for Approval-Topographical Survey Report 4" Line | 110 | 0 | 2024-03-18 | 2024-08-02 | 18-Mar-24 A | 30-Aug-24 A
Geotechnical Survey Report |  | 125 | 0 | 2024-02-26 | 2024-08-16 | 26-Feb-24 A | 30-Aug-24 A
HE-GS-0010 | Issue ICR - Geo Technical Survey Report (Overall) | 4 | 0 | 2024-02-26 | 2024-03-01 | 26-Feb-24 A | 01-Mar-24 A
HE-GS-0020 | Receive Company Comments - Geo Technical Survey Report (Overall) | 4 | 0 | 2024-03-04 | 2024-03-08 | 04-Mar-24 A | 08-Mar-24 A
HE-GS-0030 | Re-Issue for Approval - Geo Technical Survey Report (Overall) | 17 | 0 | 2024-03-10 | 2024-04-07 | 10-Mar-24 A | 07-Apr-24 A
HE-GS-0040 | Obtain Company Approval - Geo Technical Survey Report (Overall) | 4 | 0 | 2024-04-12 | 2024-04-18 | 12-Apr-24 A | 18-Apr-24 A
HE-GS-0050 | Final Issue for Design/ Construction-Geotechnical Survey Report (Overall) | 26 | 0 | 2024-07-29 | 2024-08-02 | 26-Jul-24 A | 30-Aug-24 A
Geotechnical Survey Report 52" Line |  | 125 | 0 | 2024-02-26 | 2024-08-16 | 26-Feb-24 A | 30-Aug-24 A
HE-GS-90 | Issue ICR - Geo Technical Survey Report 52" Line | 4 | 0 | 2024-02-26 | 2024-03-01 | 26-Feb-24 A | 01-Mar-24 A
HE-GS-50 | Receive Company Comments - Geo Technical Survey Report 52" Line | 4 | 0 | 2024-03-04 | 2024-03-08 | 04-Mar-24 A | 08-Mar-24 A
HE-GS-60 | Re-Issue for Approval - Geo Technical Survey Report 52" Line | 54 | 0 | 2024-03-10 | 2024-08-02 | 10-Mar-24 A | 31-May-24 A
HE-GS-70 | Obtain Company Approval - Geo Technical Survey Report 52" Line | 36 | 0 | 2024-08-05 | 2024-08-09 | 03-Jun-24 A | 26-Jul-24 A
HE-GS-80 | Final Issue for Design/ Construction-Geotechnical Survey Report 52" Line | 25 | 0 | 2024-08-12 | 2024-08-16 | 29-Jul-24 A | 30-Aug-24 A
Geotechnical Survey Report 56" Line |  | 120 | 0 | 2024-03-04 | 2024-08-16 | 04-Mar-24 A | 30-Aug-24 A
HE-GS-140 | Issue ICR - Geo Technical Survey Report 56" Line | 4 | 0 | 2024-03-04 | 2024-03-08 | 04-Mar-24 A | 08-Mar-24 A
HE-GS-100 | Receive Company Comments - Geo Technical Survey Report 56" Line | 4 | 0 | 2024-03-10 | 2024-03-17 | 10-Mar-24 A | 17-Mar-24 A
HE-GS-110 | Re-Issue for Approval - Geo Technical Survey Report 56" Line | 48 | 0 | 2024-03-18 | 2024-08-02 | 18-Mar-24 A | 31-May-24 A
HE-GS-120 | Obtain Company Approval - Geo Technical Survey Report 56" Line | 36 | 0 | 2024-08-05 | 2024-08-09 | 03-Jun-24 A | 26-Jul-24 A
HE-GS-130 | Final Issue for Design/ Construction-Geotechnical Survey Report 56" Line | 25 | 0 | 2024-08-12 | 2024-08-16 | 29-Jul-24 A | 30-Aug-24 A
Geotechnical Survey Report 4" Line |  | 49 | 0 | 2024-03-10 | 2024-05-26 | 10-Mar-24 A | 26-May-24 A
HE-GS-190 | Issue ICR - Geo Technical Survey Report 4" Line | 4 | 0 | 2024-03-10 | 2024-03-17 | 10-Mar-24 A | 17-Mar-24 A
HE-GS-150 | Receive Company Comments - Geo Technical Survey Report 4" Line | 4 | 0 | 2024-03-18 | 2024-03-25 | 18-Mar-24 A | 25-Mar-24 A
HE-GS-160 | Re-Issue for Approval - Geo Technical Survey Report 4" Line | 22 | 0 | 2024-03-26 | 2024-05-01 | 26-Mar-24 A | 01-May-24 A
HE-GS-170 | Obtain Company Approval - Geo Technical Survey Report 4" Line | 2 | 0 | 2024-05-10 | 2024-05-14 | 10-May-24 A | 14-May-24 A
HE-GS-180 | Final Issue for Design/ Construction-Geotechnical Survey Report 4" Line | 5 | 0 | 2024-05-20 | 2024-05-26 | 20-May-24 A | 26-May-24 A
Constructability Review/ SIMOPS Report |  | 40 | 40 | 2024-07-29 | 2024-09-20 | 2024-10-28 | 2024-12-24 | 71
HE-ST-0010 | Issue ICR-Constructability Review / SIMOPS Report | 10 | 10 | 2024-07-29 | 2024-08-09 | 2024-10-28 | 2024-11-08 | 71
HE-ST-0020 | Receive Company Comments-Constructability Review / SIMOPS Report | 10 | 10 | 2024-08-12 | 2024-08-23 | 2024-11-11 | 2024-11-22 | 71
HE-ST-0030 | Re-Issue for Approval-Constructability Review / SIMOPS Report | 5 | 5 | 2024-08-26 | 2024-08-30 | 2024-11-25 | 2024-11-29 | 71
HE-ST-0040 | Obtain Company Approval-Constructability Review / SIMOPS Report | 10 | 10 | 2024-09-02 | 2024-09-13 | 2024-12-04 | 2024-12-17 | 71
HE-ST-0050 | Final Issue for Design/ Construction-Constructability Review/ SIMOPS Report | 5 | 5 | 2024-09-16 | 2024-09-20 | 2024-12-18 | 2024-12-24 | 71
Process |  | 338 | 20 | 2023-07-23 | 2024-09-05 | 23-Jul-23 A | 2024-11-22 | 102
Process Design Basis |  | 82 | 0 | 2023-07-23 | 2023-11-15 | 23-Jul-23 A | 15-Nov-23 A
HE-DB-0010 | Issue ICR-Design Basis | 7 | 0 | 2023-07-23 | 2023-08-02 | 23-Jul-23 A | 02-Aug-23 A
HE-DB-0020 | Receive Company Comments-Design Basis | 6 | 0 | 2023-08-02 | 2023-08-10 | 02-Aug-23 A | 10-Aug-23 A
HE-DB-0030 | Re-Issue for Approval-Design Basis | 19 | 0 | 2023-08-11 | 2023-09-07 | 11-Aug-23 A | 07-Sep-23 A
HE-DB-0040 | Obtain Company Approval-Design Basis | 7 | 0 | 2023-09-08 | 2023-09-19 | 08-Sep-23 A | 19-Sep-23 A
HE-DB-0050 | Final Issue for Design-Design Basis | 5 | 0 | 2023-11-08 | 2023-11-15 | 08-Nov-23 A | 15-Nov-23 A
Process Flow Diagrams |  | 259 | 0 | 2023-08-04 | 2024-08-02 | 04-Aug-23 A | 16-Aug-24 A
HE-PR-0040 | Issue ICR- Process Flow Diagrams ( New + Existing) | 3 | 0 | 2023-08-04 | 2023-08-09 | 04-Aug-23 A | 09-Aug-23 A
HE-PR-0050 | Receive Company Comments- Process Flow Diagrams ( New + Existing) | 10 | 0 | 2023-08-15 | 2023-08-29 | 15-Aug-23 A | 29-Aug-23 A
HE-PR-0070 | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | 5 | 0 | 2023-09-11 | 2023-09-18 | 11-Sep-23 A | 18-Sep-23 A
HE-PR-0080 | Obtain Company Approval- Process Flow Diagrams ( New + Existing) | 5 | 0 | 2023-09-19 | 2023-09-26 | 19-Sep-23 A | 26-Sep-23 A
HE-PR-0060 | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | 18 | 0 | 2023-09-01 | 2023-09-27 | 01-Sep-23 A | 27-Sep-23 A
HE-PR-0090 | Final Issue for Design/ Construction-Process Flow Diagrams ( New + Existing) | 203 | 0 | 2023-10-23 | 2024-08-02 | 23-Oct-23 A | 16-Aug-24 A
Heat & Material Balance |  | 230 | 0 | 2023-08-04 | 2024-08-15 | 04-Aug-23 A | 08-Jul-24 A
HE-PR-1240 | Issue ICR- H&MB Report | 6 | 0 | 2023-08-04 | 2023-08-14 | 04-Aug-23 A | 14-Aug-23 A
HE-PR-1250 | Receive Company Comments- H&MB Report | 8 | 0 | 2023-08-14 | 2023-08-24 | 14-Aug-23 A | 24-Aug-23 A
HE-PR-1200 | Re-Issue after incorporating Review Comments- H&MB Report | 12 | 0 | 2023-09-13 | 2023-09-29 | 13-Sep-23 A | 29-Sep-23 A
HE-PR-1210 | Obtain Company Approval- H&MB Report | 9 | 0 | 2023-10-03 | 2023-10-16 | 03-Oct-23 A | 16-Oct-23 A
HE-PR-1220 | Final Issue for Design/ Construction- H&MB Report | 26 | 0 | 2024-07-29 | 2024-08-15 | 28-May-24 A | 08-Jul-24 A
Isolation & Tie-In philosophy |  | 117 | 0 | 2023-08-06 | 2024-01-19 | 06-Aug-23 A | 19-Jan-24 A
HE-PR-0850 | Issue ICR- Isolation & Tie-In philosophy | 7 | 0 | 2023-08-06 | 2023-08-16 | 06-Aug-23 A | 16-Aug-23 A
HE-PR-0860 | Receive Company Comments-Isolation & Tie-In philosophy | 8 | 0 | 2023-08-15 | 2023-08-25 | 15-Aug-23 A | 25-Aug-23 A
HE-PR-0870 | Re-Issue for Approval-Isolation & Tie-In philosophy | 8 | 0 | 2023-10-03 | 2023-10-13 | 03-Oct-23 A | 13-Oct-23 A
HE-PR-0880 | Obtain Company Approval-Isolation & Tie-In philosophy | 5 | 0 | 2023-10-13 | 2023-10-20 | 13-Oct-23 A | 20-Oct-23 A
HE-PR-0890 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | 4 | 0 | 2024-01-15 | 2024-01-19 | 15-Jan-24 A | 19-Jan-24 A
P&ID's (New) |  | 298 | 15 | 2023-09-10 | 2024-09-05 | 10-Sep-23 A | 2024-11-15 | 91
HE-PR-0110 | Issue ICR- P&ID's | 10 | 0 | 2023-09-10 | 2023-09-25 | 10-Sep-23 A | 25-Sep-23 A
HE-PR-0120 | Receive Company Comments-P&ID's | 7 | 0 | 2023-09-30 | 2023-10-11 | 30-Sep-23 A | 11-Oct-23 A
HE-PR-0170 | Issues for Design Review | 5 | 0 | 2023-10-16 | 2023-10-23 | 16-Oct-23 A | 23-Oct-23 A
HE-PR-0240 | Receive comments from Design Review | 3 | 0 | 2023-10-24 | 2023-10-27 | 24-Oct-23 A | 27-Oct-23 A
HE-PR-0130 | Re-Issue for HAZOP Studies- P&ID's review | 4 | 0 | 2023-11-10 | 2023-11-16 | 10-Nov-23 A | 16-Nov-23 A
HE-PR-0140 | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | 8 | 0 | 2023-12-09 | 2023-12-21 | 09-Dec-23 A | 21-Dec-23 A
HE-PR-0150 | Obtain Company Approval-P&ID's | 12 | 0 | 2023-12-22 | 2024-01-10 | 22-Dec-23 A | 10-Jan-24 A
HE-PR-0160 | Final Issue for Design / Construction-P&ID's | 182 | 15 | 2024-08-16 | 2024-09-05 | 22-Feb-24 A | 2024-11-15 | 91
Tie-In Schedule |  | 230 | 0 | 2023-08-26 | 2024-08-09 | 26-Aug-23 A | 31-Jul-24 A
HE-PR-0270 | Re-Issue for Approval-Tie-In Schedule | 22 | 0 | 2023-08-26 | 2023-09-27 | 26-Aug-23 A | 27-Sep-23 A
HE-PR-0280 | Obtain Company Approval-Tie-In Schedule | 9 | 0 | 2023-09-28 | 2023-10-11 | 28-Sep-23 A | 11-Oct-23 A
HE-PR-0250 | Issue ICR-Tie-In Schedule | 5 | 0 | 2023-11-16 | 2023-11-23 | 16-Nov-23 A | 23-Nov-23 A
HE-PR-0260 | Receive Company Comments-Tie-In Schedule | 12 | 0 | 2023-11-25 | 2023-12-14 | 25-Nov-23 A | 14-Dec-23 A
HE-PR-0290 | Final Issue for Design/ Construction-Tie-In Schedule | 12 | 0 | 2024-07-29 | 2024-08-09 | 15-Jul-24 A | 31-Jul-24 A
Process Data Sheet |  | 215 | 0 | 2023-08-08 | 2024-06-14 | 08-Aug-23 A | 14-Jun-24 A
Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) |  | 122 | 0 | 2023-08-14 | 2024-02-02 | 14-Aug-23 A | 02-Feb-24 A
HE-PR-0310 | Issue ICR- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | 8 | 0 | 2023-08-14 | 2023-08-24 | 14-Aug-23 A | 24-Aug-23 A
HE-PR-0320 | Receive Company Comments- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | 6 | 0 | 2023-08-25 | 2023-09-03 | 25-Aug-23 A | 03-Sep-23 A
HE-PR-0330 | Re-Issue for Approval- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | 4 | 0 | 2023-10-06 | 2023-10-12 | 06-Oct-23 A | 12-Oct-23 A
HE-PR-0340 | Obtain Company Approval- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | 9 | 0 | 2023-10-13 | 2023-10-26 | 13-Oct-23 A | 26-Oct-23 A
HE-PR-0350 | Final Issue for Design/ Construction-Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | 4 | 0 | 2024-01-29 | 2024-02-02 | 29-Jan-24 A | 02-Feb-24 A
Process Datasheets - Pressure Reduction System (At Sweihan CRS) |  | 211 | 0 | 2023-08-14 | 2024-06-14 | 14-Aug-23 A | 14-Jun-24 A
HE-PR-0370 | Issue ICR- Process Datasheets - PRS Skid (at Sweihan CRS) | 8 | 0 | 2023-08-14 | 2023-08-24 | 14-Aug-23 A | 24-Aug-23 A
HE-PR-0380 | Receive Company Comments- Process Datasheets - PRS Skid (at Sweihan CRS) | 6 | 0 | 2023-08-25 | 2023-09-03 | 25-Aug-23 A | 03-Sep-23 A
HE-PR-0390 | Re-Issue for Approval- Process Datasheets - PRS Skid (at Sweihan CRS) | 5 | 0 | 2023-09-15 | 2023-09-22 | 15-Sep-23 A | 22-Sep-23 A
HE-PR-0400 | Obtain Company Approval- Process Datasheets - PRS Skid (at Sweihan CRS) | 5 | 0 | 2023-11-08 | 2023-11-15 | 08-Nov-23 A | 15-Nov-23 A
HE-PR-0410 | Final Issue for Design/ Construction-Process Datasheets - PRS Skid (at Sweihan CRS) | 143 | 0 | 2023-11-16 | 2024-06-14 | 16-Nov-23 A | 14-Jun-24 A
Process Datasheets - Filters (At Sweihan CRS) |  | 82 | 0 | 2023-08-08 | 2023-11-30 | 08-Aug-23 A | 30-Nov-23 A
HE-PR-0430 | Issue ICR- Process Datasheets - Filters (At Sweihan CRS) | 8 | 0 | 2023-08-08 | 2023-08-18 | 08-Aug-23 A | 18-Aug-23 A
HE-PR-0440 | Receive Company Comments- Process Datasheets - Filters (At Sweihan CRS) | 6 | 0 | 2023-08-19 | 2023-08-29 | 19-Aug-23 A | 29-Aug-23 A
HE-PR-0450 | Re-Issue for Approval- Process Datasheets - Filters (At Sweihan CRS) | 5 | 0 | 2023-09-14 | 2023-09-21 | 14-Sep-23 A | 21-Sep-23 A
HE-PR-0460 | Obtain Company Approval- Process Datasheets - Filters (At Sweihan CRS) | 4 | 0 | 2023-10-06 | 2023-10-12 | 06-Oct-23 A | 12-Oct-23 A
HE-PR-0470 | Final Issue for Design/ Construction-Process Datasheets - Filters (At Sweihan CRS) | 7 | 0 | 2023-11-21 | 2023-11-30 | 21-Nov-23 A | 30-Nov-23 A
Process Datasheets - Pig Launcher / Receiver |  | 76 | 0 | 2023-08-14 | 2023-11-28 | 14-Aug-23 A | 28-Nov-23 A
HE-PR-0490 | Issue ICR- Process Datasheets - Pig Launcher / Receiver | 9 | 0 | 2023-08-14 | 2023-08-25 | 14-Aug-23 A | 25-Aug-23 A
HE-PR-0500 | Receive Company Comments- Process Datasheets - Pig Launcher / Receiver | 1 | 0 | 2023-08-25 | 2023-08-26 | 25-Aug-23 A | 26-Aug-23 A
HE-PR-0510 | Re-Issue for Approval- Process Datasheets - Pig Launcher / Receiver | 21 | 0 | 2023-08-27 | 2023-09-26 | 27-Aug-23 A | 26-Sep-23 A
HE-PR-0520 | Obtain Company Approval- Process Datasheets - Pig Launcher / Receiver | 4 | 0 | 2023-10-06 | 2023-10-12 | 06-Oct-23 A | 12-Oct-23 A
HE-PR-0530 | Final Issue for Design/ Construction-Process Datasheets - Pig Launcher / Receiver | 3 | 0 | 2023-11-23 | 2023-11-28 | 23-Nov-23 A | 28-Nov-23 A
Process Datasheets - MOV |  | 81 | 0 | 2023-08-22 | 2023-12-14 | 22-Aug-23 A | 14-Dec-23 A
HE-PR-0550 | Issue ICR- Process Datasheets | 9 | 0 | 2023-08-22 | 2023-09-03 | 22-Aug-23 A | 03-Sep-23 A
HE-PR-0560 | Receive Company Comments- Process Datasheets | 8 | 0 | 2023-09-04 | 2023-09-14 | 04-Sep-23 A | 14-Sep-23 A
HE-PR-0570 | Re-Issue for Approval- Process Datasheets | 5 | 0 | 2023-09-18 | 2023-09-25 | 18-Sep-23 A | 25-Sep-23 A
HE-PR-0580 | Obtain Company Approval- Process Datasheets | 4 | 0 | 2023-10-06 | 2023-10-12 | 06-Oct-23 A | 12-Oct-23 A
HE-PR-0590 | Final Issue for Design/ Construction-Process Datasheets | 21 | 0 | 2023-11-14 | 2023-12-14 | 14-Nov-23 A | 14-Dec-23 A
Process Datasheets - ROV |  | 76 | 0 | 2023-09-04 | 2023-12-20 | 04-Sep-23 A | 20-Dec-23 A
HE-PR-1260 | Issue ICR- Process Datasheets | 5 | 0 | 2023-09-04 | 2023-09-11 | 04-Sep-23 A | 11-Sep-23 A
HE-PR-1270 | Receive Company Comments- Process Datasheets | 8 | 0 | 2023-09-12 | 2023-09-22 | 12-Sep-23 A | 22-Sep-23 A
HE-PR-1280 | Re-Issue for Approval- Process Datasheets | 4 | 0 | 2023-11-01 | 2023-11-07 | 01-Nov-23 A | 07-Nov-23 A
HE-PR-1290 | Obtain Company Approval- Process Datasheets | 6 | 0 | 2023-11-08 | 2023-11-16 | 08-Nov-23 A | 16-Nov-23 A
HE-PR-1300 | Final Issue for Design/ Construction-Process Datasheets | 22 | 0 | 2023-11-17 | 2023-12-20 | 17-Nov-23 A | 20-Dec-23 A
Process Datasheets - Restriction Orifice Pipeline |  | 91 | 0 | 2023-11-14 | 2024-03-25 | 14-Nov-23 A | 25-Mar-24 A
HE-PR-1560 | Issue ICR- Process Datasheets | 3 | 0 | 2023-11-14 | 2023-11-17 | 14-Nov-23 A | 17-Nov-23 A
HE-PR-1570 | Receive Company Comments- Process Datasheets | 2 | 0 | 2023-11-21 | 2023-11-23 | 21-Nov-23 A | 23-Nov-23 A
HE-PR-1580 | Re-Issue for Approval- Process Datasheets | 10 | 0 | 2023-12-29 | 2024-01-15 | 29-Dec-23 A | 15-Jan-24 A
HE-PR-1590 | Obtain Company Approval- Process Datasheets | 11 | 0 | 2024-02-26 | 2024-03-12 | 26-Feb-24 A | 12-Mar-24 A
HE-PR-1600 | Final Issue for Design/ Construction-Process Datasheets | 8 | 0 | 2024-03-12 | 2024-03-25 | 12-Mar-24 A | 25-Mar-24 A
Process Datasheets - Temprature Transmitters |  | 74 | 0 | 2023-10-02 | 2024-01-16 | 02-Oct-23 A | 16-Jan-24 A
HE-PR-1360 | Issue ICR- Process Datasheets | 9 | 0 | 2023-10-02 | 2023-10-13 | 02-Oct-23 A | 13-Oct-23 A
HE-PR-1370 | Receive Company Comments- Process Datasheets | 9 | 0 | 2023-10-16 | 2023-10-27 | 16-Oct-23 A | 27-Oct-23 A
HE-PR-1380 | Re-Issue for Approval- Process Datasheets | 4 | 0 | 2023-11-15 | 2023-11-21 | 15-Nov-23 A | 21-Nov-23 A
HE-PR-1390 | Obtain Company Approval- Process Datasheets | 9 | 0 | 2023-12-04 | 2023-12-15 | 04-Dec-23 A | 15-Dec-23 A
HE-PR-1400 | Final Issue for Design/ Construction-Process Datasheets | 11 | 0 | 2023-12-29 | 2024-01-16 | 29-Dec-23 A | 16-Jan-24 A
Process Datasheets - Temprature Guage |  | 51 | 0 | 2023-11-02 | 2024-01-16 | 02-Nov-23 A | 16-Jan-24 A
HE-PR-1410 | Issue ICR- Process Datasheets | 8 | 0 | 2023-11-02 | 2023-11-14 | 02-Nov-23 A | 14-Nov-23 A
HE-PR-1420 | Receive Company Comments- Process Datasheets | 3 | 0 | 2023-11-15 | 2023-11-20 | 15-Nov-23 A | 20-Nov-23 A
HE-PR-1430 | Re-Issue for Approval- Process Datasheets | 3 | 0 | 2023-11-21 | 2023-11-24 | 21-Nov-23 A | 24-Nov-23 A
HE-PR-1440 | Obtain Company Approval- Process Datasheets | 9 | 0 | 2023-12-04 | 2023-12-15 | 04-Dec-23 A | 15-Dec-23 A
HE-PR-1450 | Final Issue for Design/ Construction-Process Datasheets | 11 | 0 | 2023-12-29 | 2024-01-16 | 29-Dec-23 A | 16-Jan-24 A
Process Datasheets - Pressure Transmitters |  | 51 | 0 | 2023-11-02 | 2024-01-16 | 02-Nov-23 A | 16-Jan-24 A
HE-PR-1460 | Issue ICR- Process Datasheets | 8 | 0 | 2023-11-02 | 2023-11-14 | 02-Nov-23 A | 14-Nov-23 A
HE-PR-1470 | Receive Company Comments- Process Datasheets | 3 | 0 | 2023-11-15 | 2023-11-20 | 15-Nov-23 A | 20-Nov-23 A
HE-PR-1480 | Re-Issue for Approval- Process Datasheets | 3 | 0 | 2023-11-21 | 2023-11-24 | 21-Nov-23 A | 24-Nov-23 A
HE-PR-1490 | Obtain Company Approval- Process Datasheets | 9 | 0 | 2023-12-04 | 2023-12-15 | 04-Dec-23 A | 15-Dec-23 A
HE-PR-1500 | Final Issue for Design/ Construction-Process Datasheets | 11 | 0 | 2023-12-29 | 2024-01-16 | 29-Dec-23 A | 16-Jan-24 A
Process Datasheets - Pressure Guage |  | 41 | 0 | 2023-11-16 | 2024-01-16 | 16-Nov-23 A | 16-Jan-24 A
HE-PR-1510 | Issue ICR- Process Datasheets | 4 | 0 | 2023-11-16 | 2023-11-22 | 16-Nov-23 A | 22-Nov-23 A
HE-PR-1520 | Receive Company Comments- Process Datasheets | 7 | 0 | 2023-11-23 | 2023-12-05 | 23-Nov-23 A | 05-Dec-23 A
HE-PR-1530 | Re-Issue for Approval- Process Datasheets | 3 | 0 | 2023-12-06 | 2023-12-11 | 06-Dec-23 A | 11-Dec-23 A
HE-PR-1540 | Obtain Company Approval- Process Datasheets | 8 | 0 | 2023-12-12 | 2023-12-22 | 12-Dec-23 A | 22-Dec-23 A
HE-PR-1550 | Final Issue for Design/ Construction-Process Datasheets | 11 | 0 | 2023-12-29 | 2024-01-16 | 29-Dec-23 A | 16-Jan-24 A
Process Datasheets - PRV |  | 80 | 0 | 2023-11-17 | 2024-03-11 | 17-Nov-23 A | 11-Mar-24 A
HE-PR-1310 | Issue ICR- Process Datasheets | 4 | 0 | 2023-11-17 | 2023-11-23 | 17-Nov-23 A | 23-Nov-23 A
HE-PR-1320 | Receive Company Comments- Process Datasheets | 4 | 0 | 2023-11-27 | 2023-12-01 | 27-Nov-23 A | 01-Dec-23 A
HE-PR-1330 | Re-Issue for Approval- Process Datasheets | 10 | 0 | 2023-12-29 | 2024-01-15 | 29-Dec-23 A | 15-Jan-24 A
HE-PR-1340 | Obtain Company Approval- Process Datasheets | 4 | 0 | 2024-02-26 | 2024-03-01 | 26-Feb-24 A | 01-Mar-24 A
HE-PR-1350 | Final Issue for Design/ Construction-Process Datasheets | 6 | 0 | 2024-03-02 | 2024-03-11 | 02-Mar-24 A | 11-Mar-24 A
Process Simulations Report |  | 80 | 0 | 2023-08-04 | 2023-11-24 | 04-Aug-23 A | 24-Nov-23 A
HE-PR-0610 | Issue ICR- Process Simulations Report | 6 | 0 | 2023-08-04 | 2023-08-14 | 04-Aug-23 A | 14-Aug-23 A
HE-PR-0620 | Receive Company Comments- Process Simulations Report | 8 | 0 | 2023-08-14 | 2023-08-24 | 14-Aug-23 A | 24-Aug-23 A
HE-PR-0630 | Re-Issue for Approval- Process Simulations Report | 10 | 0 | 2023-09-06 | 2023-09-20 | 06-Sep-23 A | 20-Sep-23 A
HE-PR-0640 | Obtain Company Approval- Process Simulations Report | 4 | 0 | 2023-10-06 | 2023-10-12 | 06-Oct-23 A | 12-Oct-23 A
HE-PR-0650 | Final Issue for Design/ Construction-Process Simulations Report | 1 | 0 | 2023-11-23 | 2023-11-24 | 23-Nov-23 A | 24-Nov-23 A
Operating , control and safeguarding philosophy |  | 241 | 0 | 2023-10-26 | 2024-08-02 | 26-Oct-23 A | 14-Oct-24 A
HE-PR-0730 | Issue ICR- Operating and control philosophy, Safeguarding philosophy | 26 | 0 | 2023-10-26 | 2023-12-01 | 26-Oct-23 A | 01-Dec-23 A
HE-PR-0740 | Receive Company Comments- Operating and control philosophy , Safeguarding philosophy | 5 | 0 | 2023-12-04 | 2023-12-11 | 04-Dec-23 A | 11-Dec-23 A
HE-PR-0750 | Re-Issue for Approval- Operating and control philosophy , Safeguarding philosophy | 12 | 0 | 2023-12-12 | 2023-12-28 | 12-Dec-23 A | 28-Dec-23 A
HE-PR-0760 | Obtain Company Approval- Operating and control philosophy , Safeguarding philosophy | 6 | 0 | 2023-12-29 | 2024-01-09 | 29-Dec-23 A | 09-Jan-24 A
HE-PR-0770 | Final Issue for Design/ Construction-Operating , control and safeguarding philosophy | 207 | 0 | 2023-12-14 | 2024-08-02 | 14-Dec-23 A | 14-Oct-24 A
Relief, Vent and Blowdown philosophy |  | 74 | 0 | 2023-09-06 | 2023-12-20 | 06-Sep-23 A | 20-Dec-23 A
HE-PR-0790 | Issue ICR - Relief, Vent and Blowdown Philosophy | 4 | 0 | 2023-09-06 | 2023-09-12 | 06-Sep-23 A | 12-Sep-23 A
HE-PR-0800 | Receive Company Comments - Relief, Vent and Blowdown Philosophy | 20 | 0 | 2023-09-13 | 2023-10-11 | 13-Sep-23 A | 11-Oct-23 A
HE-PR-0810 | Re-Issue for Approval - Relief, Vent and Blowdown Philosophy | 6 | 0 | 2023-11-09 | 2023-11-17 | 09-Nov-23 A | 17-Nov-23 A
HE-PR-0820 | Obtain Company Approval - Relief, Vent and Blowdown Philosophy | 7 | 0 | 2023-11-22 | 2023-12-01 | 22-Nov-23 A | 01-Dec-23 A
HE-PR-0830 | Final Issue for Design/ Construction-Relief, Vent and Blowdown philosophy | 12 | 0 | 2023-12-04 | 2023-12-20 | 04-Dec-23 A | 20-Dec-23 A
Vent and Depressurization Report (for new facilities) |  | 87 | 0 | 2023-11-03 | 2024-03-07 | 03-Nov-23 A | 07-Mar-24 A
HE-PR-0970 | Issue ICR- Vent and Depressurization Report (for new facilities) | 38 | 0 | 2023-11-03 | 2023-12-28 | 03-Nov-23 A | 28-Dec-23 A
HE-PR-0980 | Receive Company Comments- Vent and Depressurization Report (for new facilities) | 38 | 0 | 2023-11-03 | 2023-12-28 | 03-Nov-23 A | 28-Dec-23 A
HE-PR-0990 | Re-Issue for Approval- Vent and Depressurization Report (for new facilities) | 38 | 0 | 2023-11-03 | 2023-12-28 | 03-Nov-23 A | 28-Dec-23 A
HE-PR-1000 | Obtain Company Approval- Vent and Depressurization Report (for new facilities) | 38 | 0 | 2023-11-03 | 2023-12-28 | 03-Nov-23 A | 28-Dec-23 A
HE-PR-1010 | Final Issue for Design/ Construction-Vent and Depressurization Report (for new facilities) | 48 | 0 | 2023-12-29 | 2024-03-07 | 29-Dec-23 A | 07-Mar-24 A
Equipment List |  | 78 | 0 | 2023-08-11 | 2023-11-29 | 11-Aug-23 A | 29-Nov-23 A
HE-PR-1030 | Issue ICR - Equipment List | 6 | 0 | 2023-08-11 | 2023-08-21 | 11-Aug-23 A | 21-Aug-23 A
HE-PR-1040 | Receive Company Comments - Equipment List | 7 | 0 | 2023-08-22 | 2023-08-31 | 22-Aug-23 A | 31-Aug-23 A
HE-PR-1050 | Re-Issue for Approval - Equipment List | 14 | 0 | 2023-09-01 | 2023-09-21 | 01-Sep-23 A | 21-Sep-23 A
HE-PR-1060 | Obtain Company Approval - Equipment List | 10 | 0 | 2023-09-22 | 2023-10-06 | 22-Sep-23 A | 06-Oct-23 A
HE-PR-1070 | Final Issue for Design/ Construction-Equipment List | 6 | 0 | 2023-11-21 | 2023-11-29 | 21-Nov-23 A | 29-Nov-23 A
Line List |  | 288 | 20 | 2023-10-02 | 2024-08-23 | 02-Oct-23 A | 2024-11-22 | 48
HE-PR-1090 | Issue ICR- Line List | 14 | 0 | 2023-10-02 | 2023-10-20 | 02-Oct-23 A | 20-Oct-23 A
HE-PR-1100 | Receive Company Comments- Line List | 5 | 0 | 2023-10-20 | 2023-10-27 | 20-Oct-23 A | 27-Oct-23 A
HE-PR-1110 | Re-Issue for Approval- Line List | 18 | 0 | 2023-12-01 | 2023-12-28 | 01-Dec-23 A | 28-Dec-23 A
HE-PR-1120 | Obtain Company Approval- Line List | 9 | 0 | 2023-12-29 | 2024-01-12 | 29-Dec-23 A | 12-Jan-24 A
HE-PR-1130 | Final Issue for Design/ Construction-Line List | 218 | 20 | 2024-01-10 | 2024-08-23 | 10-Jan-24 A | 2024-11-22 | 48
Pipeline |  | 357 | 40 | 2023-07-25 | 2024-10-17 | 25-Jul-23 A | 2024-12-24 | 229
Pipeline Design Basis |  | 226 | 0 | 2023-08-06 | 2024-07-02 | 06-Aug-23 A | 02-Jul-24 A
HE-DB-80 | Issue ICR- Pipeline Design Basis | 7 | 0 | 2023-08-06 | 2023-08-16 | 06-Aug-23 A | 16-Aug-23 A
HE-DB-90 | Receive Company Comments-Design Basis | 8 | 0 | 2023-08-15 | 2023-08-25 | 15-Aug-23 A | 25-Aug-23 A
HE-DB-50 | Re-Issue for Approval-Design Basis | 45 | 0 | 2023-08-26 | 2023-10-30 | 26-Aug-23 A | 30-Oct-23 A
HE-DB-70 | Obtain Company Approval-Design Basis | 12 | 0 | 2023-10-31 | 2023-11-16 | 31-Oct-23 A | 16-Nov-23 A
HE-DB-60 | Final Issue for Design/ Construction-Design Basis | 152 | 0 | 2023-11-17 | 2024-07-02 | 17-Nov-23 A | 02-Jul-24 A
Pipeline Wall Thickness Calculation Report |  | 117 | 0 | 2023-07-29 | 2024-01-12 | 29-Jul-23 A | 12-Jan-24 A
HE-PL-0010 | Issue ICR - Specification - Pipeline Wall Thickness Calculation Report | 3 | 0 | 2023-07-29 | 2023-08-03 | 29-Jul-23 A | 03-Aug-23 A
HE-PL-0020 | Receive Company Comments - Pipeline Wall Thickness Calculation Report | 5 | 0 | 2023-08-03 | 2023-08-10 | 03-Aug-23 A | 10-Aug-23 A
HE-PL-0030 | Re-Issue for Approval - Specification -Pipeline Wall Thickness Calculation Report | 4 | 0 | 2023-08-10 | 2023-08-16 | 10-Aug-23 A | 16-Aug-23 A
HE-PL-0040 | Obtain Company Approval - Pipeline Wall Thickness Calculation Report | 4 | 0 | 2023-08-16 | 2023-08-22 | 16-Aug-23 A | 22-Aug-23 A
HE-PL-0050 | Final Issue for Design/ Construction - Pipeline Wall Thickness Calculation Report | 9 | 0 | 2023-12-29 | 2024-01-12 | 29-Dec-23 A | 12-Jan-24 A
PIPELINE CROSSING CALCULATION REPORT |  | 96 | 0 | 2023-08-23 | 2024-01-08 | 23-Aug-23 A | 08-Jan-24 A
HE-PL-3860 | Issue ICR - Specification - PIPELINE CROSSING CALCULATION REPORT | 12 | 0 | 2023-08-23 | 2023-09-08 | 23-Aug-23 A | 08-Sep-23 A
HE-PL-3870 | Receive Company Comments - PIPELINE CROSSING CALCULATION REPORT | 13 | 0 | 2023-09-11 | 2023-09-28 | 11-Sep-23 A | 28-Sep-23 A
HE-PL-3830 | Re-Issue for Approval - Specification -PIPELINE CROSSING CALCULATION REPORT | 0 | 0 | 2023-11-28 | 2023-11-28 | 28-Nov-23 A | 28-Nov-23 A
HE-PL-3840 | Obtain Company Approval - PIPELINE CROSSING CALCULATION REPORT | 0 | 0 | 2023-11-28 | 2023-11-28 | 28-Nov-23 A | 28-Nov-23 A
HE-PL-3850 | Final Issue for Design/ Construction - PIPELINE CROSSING CALCULATION REPORT | 27 | 0 | 2023-11-28 | 2024-01-08 | 28-Nov-23 A | 08-Jan-24 A
Pipeline Specifications - Addendum to DGS |  | 52 | 0 | 2023-10-31 | 2024-01-15 | 31-Oct-23 A | 15-Jan-24 A
HE-PL-0070 | Issue ICR - Pipeline Specifications - Addendum to DGS | 6 | 0 | 2023-10-31 | 2023-11-08 | 31-Oct-23 A | 08-Nov-23 A
HE-PL-0080 | Receive Company Comments - Pipeline Specifications - Addendum to DGS | 6 | 0 | 2023-11-09 | 2023-11-17 | 09-Nov-23 A | 17-Nov-23 A
HE-PL-0090 | Re-Issue for Approval - Pipeline Specifications - Addendum to DGS | 7 | 0 | 2023-11-20 | 2023-11-29 | 20-Nov-23 A | 29-Nov-23 A
HE-PL-0100 | Obtain Company Approval - Pipeline Specifications - Addendum to DGS | 9 | 0 | 2023-12-01 | 2023-12-15 | 01-Dec-23 A | 15-Dec-23 A
HE-PL-0110 | Final Issue for Design/ Construction-Pipeline Specifications - Addendum to DGS | 19 | 0 | 2023-12-16 | 2024-01-15 | 16-Dec-23 A | 15-Jan-24 A
Overall Pipeline Route Map - 56" |  | 128 | 0 | 2024-03-18 | 2024-08-09 | 18-Mar-24 A | 26-Sep-24 A
HE-PL-0130 | Issue ICR - Overall Pipeline Route Map - 56" | 29 | 0 | 2024-03-18 | 2024-05-06 | 18-Mar-24 A | 06-May-24 A
HE-PL-0140 | Receive Company Comments - Overall Pipeline Route Map - 56" | 14 | 0 | 2024-05-07 | 2024-05-25 | 07-May-24 A | 25-May-24 A
HE-PL-0150 | Re-Issue for Approval - Overall Pipeline Route Map - 56" | 1 | 0 | 2024-05-26 | 2024-05-28 | 26-May-24 A | 28-May-24 A
HE-PL-0160 | Obtain Company Approval - Overall Pipeline Route Map - 56" | 2 | 0 | 2024-05-29 | 2024-05-31 | 29-May-24 A | 31-May-24 A
HE-PL-0170 | Final Issue for Design/ Construction-Overall Pipeline Route Map - 56" | 79 | 0 | 2024-06-03 | 2024-08-09 | 03-Jun-24 A | 26-Sep-24 A
Overall Pipeline Route Map - 52" |  | 54 | 0 | 2024-03-30 | 2024-08-09 | 30-Mar-24 A | 24-Jun-24 A
HE-PL-0190 | Issue ICR - Overall Pipeline Route Map - 52" | 21 | 0 | 2024-03-30 | 2024-05-05 | 30-Mar-24 A | 05-May-24 A
HE-PL-0200 | Receive Company Comments - Overall Pipeline Route Map - 52" | 14 | 0 | 2024-05-07 | 2024-05-27 | 07-May-24 A | 27-May-24 A
HE-PL-0210 | Re-Issue for Approval - Overall Pipeline Route Map - 52" | 9 | 0 | 2024-05-28 | 2024-06-08 | 28-May-24 A | 08-Jun-24 A
HE-PL-0220 | Obtain Company Approval - Overall Pipeline Route Map - 52" | 2 | 0 | 2024-06-09 | 2024-06-12 | 09-Jun-24 A | 12-Jun-24 A
HE-PL-0230 | Final Issue for Design/ Construction-Overall Pipeline Route Map - 52" | 5 | 0 | 2024-06-13 | 2024-08-09 | 13-Jun-24 A | 24-Jun-24 A
Overall Pipeline Route Map - 4" |  | 61 | 0 | 2024-03-19 | 2024-08-09 | 19-Mar-24 A | 24-Jun-24 A
HE-PL-0250 | Issue ICR - Overall Pipeline Route Map - 4" | 30 | 0 | 2024-03-19 | 2024-05-08 | 19-Mar-24 A | 08-May-24 A
HE-PL-0260 | Receive Company Comments - Overall Pipeline Route Map - 4" | 17 | 0 | 2024-05-09 | 2024-06-02 | 09-May-24 A | 02-Jun-24 A
HE-PL-0270 | Re-Issue for Approval - Overall Pipeline Route Map - 4" | 2 | 0 | 2024-06-03 | 2024-06-05 | 03-Jun-24 A | 05-Jun-24 A
HE-PL-0280 | Obtain Company Approval - Overall Pipeline Route Map - 4" | 2 | 0 | 2024-06-05 | 2024-06-07 | 05-Jun-24 A | 07-Jun-24 A
HE-PL-0290 | Final Issue for Design/ Construction-Overall Pipeline Route Map - 4" | 8 | 0 | 2024-06-08 | 2024-08-09 | 08-Jun-24 A | 24-Jun-24 A
Pipeline Schematic Arrangement- 56", 52" and 4" Pipline |  | 45 | 0 | 2024-07-29 | 2024-10-04 | 22-Mar-24 A | 30-May-24 A
HE-PL-0310 | Issue ICR - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | 5 | 0 | 2024-07-29 | 2024-08-09 | 22-Mar-24 A | 30-Mar-24 A
HE-PL-0320 | Receive Company Comments - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | 6 | 0 | 2024-08-12 | 2024-08-23 | 01-Apr-24 A | 15-Apr-24 A
HE-PL-0330 | Re-Issue for Approval - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | 11 | 0 | 2024-08-26 | 2024-09-06 | 16-Apr-24 A | 30-Apr-24 A
HE-PL-0340 | Obtain Company Approval - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | 13 | 0 | 2024-09-09 | 2024-09-20 | 01-May-24 A | 17-May-24 A
HE-PL-0350 | Final Issue for Design/ Construction-Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | 9 | 0 | 2024-09-23 | 2024-10-04 | 18-May-24 A | 30-May-24 A
Pipeline Typical Drawings |  | 231 | 0 | 2023-11-15 | 2024-08-29 | 15-Nov-23 A | 18-Oct-24 A
HE-PL-0370 | Issue ICR - Pipeline Typical Drawings | 6 | 0 | 2023-11-15 | 2023-11-23 | 15-Nov-23 A | 23-Nov-23 A
HE-PL-0380 | Receive Company Comments - Pipeline Typical Drawings | 5 | 0 | 2023-11-27 | 2023-12-05 | 27-Nov-23 A | 05-Dec-23 A
HE-PL-0390 | Re-Issue for Approval - Pipeline Typical Drawings | 5 | 0 | 2023-12-06 | 2023-12-13 | 06-Dec-23 A | 13-Dec-23 A
HE-PL-0400 | Obtain Company Approval - Pipeline Typical Drawings | 8 | 0 | 2023-12-14 | 2023-12-26 | 14-Dec-23 A | 26-Dec-23 A
HE-PL-0410 | Final Issue for Design/ Construction-Pipeline Typical Drawings | 202 | 0 | 2023-12-27 | 2024-08-29 | 27-Dec-23 A | 18-Oct-24 A
Specification - Split Tee |  | 69 | 0 | 2023-11-16 | 2024-02-23 | 16-Nov-23 A | 23-Feb-24 A
HE-PL-0430 | Issue ICR - Specification - Split Tee | 4 | 0 | 2023-11-16 | 2023-11-22 | 16-Nov-23 A | 22-Nov-23 A
HE-PL-0440 | Receive Company Comments - Specification - Split Tee | 18 | 0 | 2023-12-01 | 2023-12-28 | 01-Dec-23 A | 28-Dec-23 A
HE-PL-0450 | Re-Issue for Approval - Specification - Split Tee | 5 | 0 | 2023-12-29 | 2024-01-07 | 29-Dec-23 A | 07-Jan-24 A
HE-PL-0460 | Obtain Company Approval - Specification - Split Tee | 6 | 0 | 2024-01-08 | 2024-01-16 | 08-Jan-24 A | 16-Jan-24 A
HE-PL-0470 | Final Issue for Design/ Construction-Specification - Split Tee | 12 | 0 | 2024-02-07 | 2024-02-23 | 07-Feb-24 A | 23-Feb-24 A
Pipeline Upheavl Calculation |  | 142 | 0 | 2023-11-07 | 2024-06-04 | 07-Nov-23 A | 04-Jun-24 A
HE-PL-0610 | Issue ICR - Pipeline Upheaval Calculation | 4 | 0 | 2023-11-08 | 2023-11-14 | 08-Nov-23 A | 14-Nov-23 A
HE-PL-0620 | Receive Company Comments - Pipeline Upheaval Calculation | 8 | 0 | 2023-11-07 | 2023-11-17 | 07-Nov-23 A | 17-Nov-23 A
HE-PL-0630 | Re-Issue for Approval - Pipeline Upheaval Calculation | 35 | 0 | 2023-11-18 | 2024-01-10 | 18-Nov-23 A | 10-Jan-24 A
HE-PL-0640 | Obtain Company Approval - Pipeline Upheaval Calculation | 35 | 0 | 2023-11-18 | 2024-01-10 | 18-Nov-23 A | 10-Jan-24 A
HE-PL-0650 | Final Issue for Design/ Construction-Pipeline Upheaval Calculation | 98 | 0 | 2024-01-10 | 2024-06-04 | 10-Jan-24 A | 04-Jun-24 A
Pipeline Road and Railway Crossing Calculation Report |  | 304 | 10 | 2023-08-25 | 2024-08-23 | 25-Aug-23 A | 2024-11-08 | 72
HE-PL-0670 | Issue ICR - Pipeline Road Crossing Calculation Report | 6 | 0 | 2023-08-25 | 2023-09-02 | 25-Aug-23 A | 02-Sep-23 A
HE-PL-0680 | Receive Company Comments - Pipeline Road Crossing Calculation Report | 3 | 0 | 2023-09-03 | 2023-09-07 | 03-Sep-23 A | 07-Sep-23 A
HE-PL-0690 | Re-Issue for Approval - Pipeline Road Crossing Calculation Report | 56 | 0 | 2023-09-11 | 2023-11-28 | 11-Sep-23 A | 28-Nov-23 A
HE-PL-0700 | Obtain Company Approval - Pipeline Road Crossing Calculation Report | 12 | 0 | 2023-11-29 | 2024-08-09 | 29-Nov-23 A | 15-Dec-23 A
HE-PL-0710 | Final Issue for Design/ Construction-Pipeline Road and Railway Crossing Calculation Report | 137 | 10 | 2024-08-12 | 2024-08-23 | 26-Apr-24 A | 2024-11-08 | 72
Pipeline Location Class selection Report |  | 174 | 20 | 2024-03-12 | 2024-10-04 | 12-Mar-24 A | 2024-11-22 | 86
HE-PL-0790 | Issue ICR - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | 2 | 0 | 2024-03-12 | 2024-03-15 | 12-Mar-24 A | 15-Mar-24 A
HE-PL-0800 | Receive Company Comments - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | 6 | 0 | 2024-03-18 | 2024-03-28 | 18-Mar-24 A | 28-Mar-24 A
HE-PL-0810 | Re-Issue for Approval - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | 5 | 0 | 2024-07-29 | 2024-08-23 | 02-Sep-24 A | 08-Sep-24 A
HE-PL-0820 | Obtain Company Approval - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | 6 | 0 | 2024-08-26 | 2024-09-06 | 09-Sep-24 A | 16-Sep-24 A
HE-PL-0830 | Final Issue for Design/ Construction-Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | 49 | 20 | 2024-09-09 | 2024-10-04 | 17-Sep-24 A | 2024-11-22 | 86
Data Sheets |  | 332 | 5 | 2023-07-25 | 2024-09-20 | 25-Jul-23 A | 2024-11-15 | 72
Data Sheet - Linepipes |  | 83 | 0 | 2023-07-30 | 2023-11-23 | 30-Jul-23 A | 23-Nov-23 A
HE-PL-1150 | Issue ICR - Data Sheet - Line pipes | 4 | 0 | 2023-07-30 | 2023-08-04 | 30-Jul-23 A | 04-Aug-23 A
HE-PL-1160 | Receive Company Comments - Data Sheet - Line pipes | 6 | 0 | 2023-08-05 | 2023-08-15 | 05-Aug-23 A | 15-Aug-23 A
HE-PL-1170 | Re-Issue for Approval - Data Sheet - Line pipes | 3 | 0 | 2023-08-16 | 2023-08-21 | 16-Aug-23 A | 21-Aug-23 A
HE-PL-1180 | Obtain Company Approval - Data Sheet - Line pipes | 17 | 0 | 2023-08-22 | 2023-09-14 | 22-Aug-23 A | 14-Sep-23 A
HE-PL-1190 | Final Issue for Design/ Construction-Data Sheet - Line pipes | 55 | 0 | 2023-09-07 | 2023-11-23 | 07-Sep-23 A | 23-Nov-23 A
Data Sheet - Hot Induction Bends |  | 84 | 0 | 2023-07-25 | 2023-11-20 | 25-Jul-23 A | 20-Nov-23 A
HE-PL-1270 | Issue ICR - Data Sheet - Hot Induction Bends | 8 | 0 | 2023-07-25 | 2023-08-04 | 25-Jul-23 A | 04-Aug-23 A
HE-PL-1280 | Receive Company Comments - Data Sheet - Hot Induction Bends | 6 | 0 | 2023-08-05 | 2023-08-15 | 05-Aug-23 A | 15-Aug-23 A
HE-PL-1290 | Re-Issue for Approval - Data Sheet - Hot Induction Bends | 10 | 0 | 2023-08-16 | 2023-08-30 | 16-Aug-23 A | 30-Aug-23 A
HE-PL-1300 | Obtain Company Approval - Data Sheet - Hot Induction Bends | 3 | 0 | 2023-08-31 | 2023-09-05 | 31-Aug-23 A | 05-Sep-23 A
HE-PL-1310 | Final Issue for Design/ Construction-Data Sheet - Hot Induction Bends | 53 | 0 | 2023-09-06 | 2023-11-20 | 06-Sep-23 A | 20-Nov-23 A
Data Sheet - Split Tee |  | 86 | 0 | 2023-11-20 | 2024-03-22 | 20-Nov-23 A | 22-Mar-24 A
HE-PL-1330 | Issue ICR - Data Sheet - Split Tee | 29 | 0 | 2023-11-20 | 2024-01-02 | 20-Nov-23 A | 02-Jan-24 A
HE-PL-1340 | Receive Company Comments - Data Sheet - Split Tee | 9 | 0 | 2024-01-02 | 2024-01-15 | 02-Jan-24 A | 15-Jan-24 A
HE-PL-1350 | Re-Issue for Approval - Data Sheet - Split Tee | 9 | 0 | 2024-01-16 | 2024-01-27 | 16-Jan-24 A | 27-Jan-24 A
HE-PL-1360 | Obtain Company Approval - Data Sheet - Split Tee | 10 | 0 | 2024-01-28 | 2024-02-12 | 28-Jan-24 A | 12-Feb-24 A
HE-PL-1370 | Final Issue for Design/ Construction-Data Sheet - Split Tee | 3 | 0 | 2024-03-16 | 2024-03-22 | 16-Mar-24 A | 22-Mar-24 A
Data Sheet - Pipeline Isolating Joints |  | 54 | 0 | 2023-09-10 | 2023-11-24 | 10-Sep-23 A | 24-Nov-23 A
HE-PL-1390 | Issue ICR - Data Sheet - Isolating joints | 6 | 0 | 2023-09-10 | 2023-09-19 | 10-Sep-23 A | 19-Sep-23 A
HE-PL-1400 | Receive Company Comments - Data Sheet - Isolating joints | 10 | 0 | 2023-09-14 | 2023-09-28 | 14-Sep-23 A | 28-Sep-23 A
HE-PL-1410 | Re-Issue for Approval - Data Sheet - Isolating joints | 4 | 0 | 2023-10-30 | 2023-11-03 | 30-Oct-23 A | 03-Nov-23 A
HE-PL-1420 | Obtain Company Approval - Data Sheet - Isolating joints | 8 | 0 | 2023-11-06 | 2023-11-16 | 06-Nov-23 A | 16-Nov-23 A
HE-PL-1430 | Final Issue for Design/ Construction-Data Sheet - Pipeline Isolating Joints | 4 | 0 | 2023-11-20 | 2023-11-24 | 20-Nov-23 A | 24-Nov-23 A
Data Sheet - Pipeline Pigging Tees |  | 79 | 0 | 2023-10-02 | 2024-01-23 | 02-Oct-23 A | 23-Jan-24 A
HE-PL-1450 | Issue ICR - Data Sheet - Pigging Tees | 10 | 0 | 2023-10-02 | 2023-10-14 | 02-Oct-23 A | 14-Oct-23 A
HE-PL-1460 | Receive Company Comments - Data Sheet - Pigging Tees | 7 | 0 | 2023-10-15 | 2023-10-25 | 15-Oct-23 A | 25-Oct-23 A
HE-PL-1470 | Re-Issue for Approval - Data Sheet - Pigging Tees | 3 | 0 | 2023-12-29 | 2024-01-04 | 29-Dec-23 A | 04-Jan-24 A
HE-PL-1480 | Obtain Company Approval - Data Sheet - Pigging Tees | 7 | 0 | 2024-01-05 | 2024-01-16 | 05-Jan-24 A | 16-Jan-24 A
HE-PL-1490 | Final Issue for Design/ Construction-Data Sheet - Pipeline Pigging Tees | 2 | 0 | 2024-01-19 | 2024-01-23 | 19-Jan-24 A | 23-Jan-24 A
Data Sheet - Anchor Flange |  | 195 | 5 | 2024-02-05 | 2024-09-20 | 05-Feb-24 A | 2024-11-15 | 72
HE-PL-1510 | Issue ICR - Data Sheet - Anchor Flange (If Required) | 5 | 0 | 2024-02-05 | 2024-02-10 | 05-Feb-24 A | 10-Feb-24 A
HE-PL-1520 | Receive Company Comments - Data Sheet - Anchor Flange (If Required) | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-PL-1530 | Re-Issue for Approval - Data Sheet - Anchor Flange (If Required) | 6 | 0 | 2024-07-29 | 2024-08-02 | 03-Jun-24 A | 10-Jun-24 A
HE-PL-1540 | Obtain Company Approval - Data Sheet - Anchor Flange (If Required) | 7 | 0 | 2024-08-05 | 2024-08-16 | 11-Jun-24 A | 24-Jun-24 A
HE-PL-1550 | Final Issue for Design/ Construction-Data Sheet - Anchor Flange | 103 | 5 | 2024-09-16 | 2024-09-20 | 25-Jun-24 A | 2024-11-15 | 72
Material Requisition |  | 338 | 10 | 2023-07-31 | 2024-10-04 | 31-Jul-23 A | 2024-11-29 | 72
MR for Linepipes |  | 81 | 0 | 2023-08-03 | 2023-11-24 | 03-Aug-23 A | 24-Nov-23 A
HE-PL-1640 | Receive Company Comments - MR for Line pipes | 10 | 0 | 2023-08-03 | 2023-08-17 | 03-Aug-23 A | 17-Aug-23 A
HE-PL-1630 | Issue ICR - MR for Line pipes | 3 | 0 | 2023-08-19 | 2023-08-24 | 19-Aug-23 A | 24-Aug-23 A
HE-PL-1650 | Re-Issue for Approval - MR for Line pipes | 5 | 0 | 2023-08-17 | 2023-08-24 | 17-Aug-23 A | 24-Aug-23 A
HE-PL-1660 | Obtain Company Approval - MR for Line pipes | 5 | 0 | 2023-08-24 | 2023-08-31 | 24-Aug-23 A | 31-Aug-23 A
HE-PL-1670 | Final Issue for Design/ Construction-MR for Line pipes | 47 | 0 | 2023-09-20 | 2023-11-24 | 20-Sep-23 A | 24-Nov-23 A
MR for Hot Induction Bends |  | 83 | 0 | 2023-07-31 | 2023-11-23 | 31-Jul-23 A | 23-Nov-23 A
HE-PL-1750 | Issue ICR - MR for Hot Induction Bends | 8 | 0 | 2023-07-31 | 2023-08-10 | 31-Jul-23 A | 10-Aug-23 A
HE-PL-1760 | Receive Company Comments - MR for Hot Induction Bends | 8 | 0 | 2023-08-08 | 2023-08-18 | 08-Aug-23 A | 18-Aug-23 A
HE-PL-1770 | Re-Issue for Approval - MR for Hot Induction Bends | 57 | 0 | 2023-08-19 | 2023-11-08 | 19-Aug-23 A | 08-Nov-23 A
HE-PL-1780 | Obtain Company Approval - MR for Hot Induction Bends | 4 | 0 | 2023-11-10 | 2023-11-16 | 10-Nov-23 A | 16-Nov-23 A
HE-PL-1790 | Final Issue for Design/ Construction-MR for Hot Induction Bends | 4 | 0 | 2023-11-17 | 2023-11-23 | 17-Nov-23 A | 23-Nov-23 A
MR for Pipeline Pigging Tees |  | 81 | 0 | 2023-12-29 | 2024-05-01 | 29-Dec-23 A | 01-May-24 A
HE-PL-1820 | Receive Company Comments - MR for Pigging Tees | 6 | 0 | 2023-12-29 | 2024-01-09 | 29-Dec-23 A | 09-Jan-24 A
HE-PL-1810 | Issue ICR - MR for Pigging Tees | 7 | 0 | 2024-01-03 | 2024-01-12 | 03-Jan-24 A | 12-Jan-24 A
HE-PL-1830 | Re-Issue for Approval - MR for Pigging Tees | 49 | 0 | 2024-02-06 | 2024-04-23 | 06-Feb-24 A | 23-Apr-24 A
HE-PL-1840 | Obtain Company Approval - MR for Pigging Tees | 3 | 0 | 2024-04-24 | 2024-04-28 | 24-Apr-24 A | 28-Apr-24 A
HE-PL-1850 | Final Issue for Design/ Construction-MR for Pipeline Pigging Tees | 2 | 0 | 2024-04-29 | 2024-05-01 | 29-Apr-24 A | 01-May-24 A
MR for Split Tee |  | 59 | 0 | 2023-12-08 | 2024-03-01 | 08-Dec-23 A | 01-Mar-24 A
HE-PL-3650 | Issue ICR - MR for Split Tee | 10 | 0 | 2023-12-08 | 2023-12-22 | 08-Dec-23 A | 22-Dec-23 A
HE-PL-3660 | Receive Company Comments - MR for Split Tee | 10 | 0 | 2023-12-22 | 2024-01-08 | 22-Dec-23 A | 08-Jan-24 A
HE-PL-3670 | Re-Issue for Approval - MR for Split Tee | 5 | 0 | 2024-01-08 | 2024-01-15 | 08-Jan-24 A | 15-Jan-24 A
HE-PL-3630 | Obtain Company Approval - MR for Split Tee | 30 | 0 | 2024-01-15 | 2024-02-26 | 15-Jan-24 A | 26-Feb-24 A
HE-PL-3640 | Final Issue for Design/ Construction-MR for Split Tee | 4 | 0 | 2024-02-26 | 2024-03-01 | 26-Feb-24 A | 01-Mar-24 A
MR for Isolating Joints |  | 48 | 0 | 2023-09-14 | 2023-11-21 | 14-Sep-23 A | 21-Nov-23 A
HE-PL-1870 | Issue ICR - MR for Isolating Joints | 3 | 0 | 2023-09-14 | 2023-09-19 | 14-Sep-23 A | 19-Sep-23 A
HE-PL-1880 | Receive Company Comments - MR for Isolating Joints | 6 | 0 | 2023-09-20 | 2023-09-28 | 20-Sep-23 A | 28-Sep-23 A
HE-PL-1890 | Re-Issue for Approval - MR for Isolating Joints | 10 | 0 | 2023-10-18 | 2023-11-01 | 18-Oct-23 A | 01-Nov-23 A
HE-PL-1900 | Obtain Company Approval - MR for Isolating Joints | 7 | 0 | 2023-11-02 | 2023-11-13 | 02-Nov-23 A | 13-Nov-23 A
HE-PL-1910 | Final Issue for Design/ Construction-MR for Isolating Joints | 5 | 0 | 2023-11-14 | 2023-11-21 | 14-Nov-23 A | 21-Nov-23 A
MR for Anchor Flanges |  | 190 | 10 | 2024-02-26 | 2024-10-04 | 26-Feb-24 A | 2024-11-29 | 72
HE-PL-3460 | Issue ICR - MR for Anchor Flanges | 27 | 0 | 2024-02-26 | 2024-04-06 | 26-Feb-24 A | 06-Apr-24 A
HE-PL-3470 | Receive Company Comments - MR for Anchor Flanges | 44 | 0 | 2024-07-29 | 2024-08-09 | 08-Apr-24 A | 12-Jun-24 A
HE-PL-3430 | Re-Issue for Approval - MR for Anchor Flanges | 7 | 0 | 2024-08-12 | 2024-08-23 | 13-Jun-24 A | 26-Jun-24 A
HE-PL-3440 | Obtain Company Approval - MR for Anchor Flanges | 16 | 0 | 2024-08-26 | 2024-09-06 | 27-Jun-24 A | 21-Jul-24 A
HE-PL-3450 | Final Issue for Design/ Construction-MR for Anchor Flanges | 95 | 10 | 2024-09-23 | 2024-10-04 | 22-Jul-24 A | 2024-11-29 | 72
TBE |  | 337 | 34 | 2023-08-13 | 2024-10-17 | 13-Aug-23 A | 2024-12-16 | 235
TBE for Linepipes |  | 141 | 0 | 2023-08-13 | 2024-02-29 | 13-Aug-23 A | 29-Feb-24 A
HE-PL-2050 | Issue ICR - TBE for Line pipes | 4 | 0 | 2023-08-13 | 2023-08-18 | 13-Aug-23 A | 18-Aug-23 A
HE-PL-2060 | Receive Company Comments - TBE for Line pipes | 1 | 0 | 2023-08-19 | 2023-08-22 | 19-Aug-23 A | 22-Aug-23 A
HE-PL-2070 | Final Issue for Design/ Construction-TBE for Line pipes | 131 | 0 | 2023-08-26 | 2024-02-29 | 26-Aug-23 A | 29-Feb-24 A
TBE for Hot Induction Bends |  | 290 | 5 | 2023-09-07 | 2024-08-02 | 07-Sep-23 A | 2024-11-01 | 264
HE-PL-2090 | Issue ICR - TBE for Hot Induction Bends | 7 | 0 | 2023-09-07 | 2023-09-17 | 07-Sep-23 A | 17-Sep-23 A
HE-PL-2100 | Receive Company Comments - TBE for Hot Induction Bends | 3 | 0 | 2023-09-18 | 2023-09-21 | 18-Sep-23 A | 21-Sep-23 A
HE-PL-2110 | Re-Issue for Approval - TBE for Hot Induction Bends | 7 | 0 | 2023-11-08 | 2023-11-17 | 08-Nov-23 A | 17-Nov-23 A
HE-PL-2120 | Obtain Company Approval - TBE for Hot Induction Bends | 4 | 0 | 2023-11-20 | 2023-11-24 | 20-Nov-23 A | 24-Nov-23 A
HE-PL-2130 | Final Issue for Design/ Construction-TBE for Hot Induction Bends | 171 | 5 | 2024-02-23 | 2024-08-02 | 23-Feb-24 A | 2024-11-01 | 264
TBE for Pigging Tees |  | 163 | 0 | 2024-02-26 | 2024-08-02 | 26-Feb-24 A | 23-Oct-24 A
HE-PL-2150 | Issue ICR - TBE for Pigging Tees | 13 | 0 | 2024-02-26 | 2024-03-15 | 26-Feb-24 A | 15-Mar-24 A
HE-PL-2160 | Receive Company Comments - TBE for Pigging Tees | 9 | 0 | 2024-03-31 | 2024-04-18 | 31-Mar-24 A | 18-Apr-24 A
HE-PL-2170 | Re-Issue for Approval - TBE for Pigging Tees | 26 | 0 | 2024-04-19 | 2024-05-25 | 19-Apr-24 A | 25-May-24 A
HE-PL-2180 | Obtain Company Approval - TBE for Pigging Tees | 6 | 0 | 2024-05-26 | 2024-06-04 | 26-May-24 A | 04-Jun-24 A
HE-PL-2190 | Final Issue for Design/ Construction-TBE for Pigging Tees | 13 | 0 | 2024-07-29 | 2024-08-02 | 07-Oct-24 A | 23-Oct-24 A
TBE for Split Tee |  | 39 | 0 | 2024-01-29 | 2024-03-25 | 29-Jan-24 A | 25-Mar-24 A
HE-PL-3690 | Issue ICR - TBE for Split Tee | 19 | 0 | 2024-01-29 | 2024-02-23 | 29-Jan-24 A | 23-Feb-24 A
HE-PL-3700 | Receive Company Comments - TBE for Split Tee | 4 | 0 | 2024-02-26 | 2024-03-01 | 26-Feb-24 A | 01-Mar-24 A
HE-PL-3710 | Re-Issue for Approval - TBE for Split Tee | 4 | 0 | 2024-03-04 | 2024-03-08 | 04-Mar-24 A | 08-Mar-24 A
HE-PL-3680 | Obtain Company Approval - TBE for Split Tee | 4 | 0 | 2024-03-10 | 2024-03-17 | 10-Mar-24 A | 17-Mar-24 A
HE-PL-3720 | Final Issue for Design/ Construction-TBE for Split Tee | 4 | 0 | 2024-03-18 | 2024-03-25 | 18-Mar-24 A | 25-Mar-24 A
TBE for Isolating Joints |  | 254 | 10 | 2023-11-03 | 2024-08-09 | 03-Nov-23 A | 2024-11-08 | 254
HE-PL-2210 | Issue ICR - TBE for Isolating Joints | 7 | 0 | 2023-11-03 | 2023-11-14 | 03-Nov-23 A | 14-Nov-23 A
HE-PL-2220 | Receive Company Comments - TBE for Isolating Joints | 4 | 0 | 2023-11-15 | 2023-11-21 | 15-Nov-23 A | 21-Nov-23 A
HE-PL-2230 | Re-Issue for Approval - TBE for Isolating Joints | 61 | 0 | 2023-11-22 | 2024-02-17 | 22-Nov-23 A | 17-Feb-24 A
HE-PL-2240 | Obtain Company Approval - TBE for Isolating Joints | 0 | 0 | 2024-02-18 | 2024-02-18 | 18-Feb-24 A | 18-Feb-24 A
HE-PL-2250 | Final Issue for Design/ Construction-TBE for Isolating Joints | 180 | 10 | 2024-02-19 | 2024-08-09 | 19-Feb-24 A | 2024-11-08 | 254
TBE for Anchor Flanges |  | 130 | 34 | 2024-06-10 | 2024-10-17 | 10-Jun-24 A | 2024-12-16 | 72
HE-PL-3480 | Issue ICR - TBE for Anchor Flanges | 4 | 0 | 2024-06-10 | 2024-06-14 | 10-Jun-24 A | 14-Jun-24 A
HE-PL-3490 | Receive Company Comments - TBE for Anchor Flanges | 7 | 0 | 2024-07-29 | 2024-08-09 | 15-Jun-24 A | 28-Jun-24 A
HE-PL-3500 | Re-Issue for Approval - TBE for Anchor Flanges | 14 | 0 | 2024-08-12 | 2024-08-23 | 30-Sep-24 A | 17-Oct-24 A
HE-PL-3510 | Obtain Company Approval - TBE for Anchor Flanges | 10 | 10 | 2024-08-26 | 2024-09-06 | 2024-10-28 | 2024-11-08 | 87
HE-PL-3520 | Final Issue for Design/ Construction-TBE for Anchor Flanges | 9 | 9 | 2024-10-07 | 2024-10-17 | 2024-12-04 | 2024-12-16 | 72
Pipeline Alignment Sheets - 56" |  | 190 | 5 | 2024-01-27 | 2024-08-09 | 27-Jan-24 A | 2024-11-01 | 8
HE-PL-2390 | Issue ICR - Pipeline Alignment Sheets -56" | 18 | 0 | 2024-01-27 | 2024-02-22 | 27-Jan-24 A | 22-Feb-24 A
HE-PL-2400 | Receive Company Comments - Pipeline Alignment Sheets -56" | 8 | 0 | 2024-02-23 | 2024-03-06 | 23-Feb-24 A | 06-Mar-24 A
HE-PL-2410 | Re-Issue for Approval - Pipeline Alignment Sheets -56" | 5 | 0 | 2024-03-07 | 2024-03-15 | 07-Mar-24 A | 15-Mar-24 A
HE-PL-2420 | Obtain Company Approval - Pipeline Alignment Sheets -56" | 5 | 0 | 2024-03-16 | 2024-03-25 | 16-Mar-24 A | 25-Mar-24 A
HE-PL-2430 | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | 150 | 5 | 2024-03-26 | 2024-08-09 | 26-Mar-24 A | 2024-11-01 | 8
Pipeline Alignment Sheets - 52" |  | 236 | 5 | 2023-11-22 | 2024-08-09 | 22-Nov-23 A | 2024-11-01 | 3
HE-PL-2450 | Issue ICR - Pipeline Alignment Sheets-52" | 56 | 0 | 2023-11-22 | 2024-02-11 | 22-Nov-23 A | 11-Feb-24 A
HE-PL-2460 | Receive Company Comments - Pipeline Alignment Sheets-52" | 36 | 0 | 2023-12-21 | 2024-02-11 | 21-Dec-23 A | 11-Feb-24 A
HE-PL-2470 | Re-Issue for Approval - Pipeline Alignment Sheets-52" | 33 | 0 | 2024-01-26 | 2024-03-13 | 26-Jan-24 A | 13-Mar-24 A
HE-PL-2480 | Obtain Company Approval - Pipeline Alignment Sheets-52" | 12 | 0 | 2024-03-04 | 2024-03-21 | 04-Mar-24 A | 21-Mar-24 A
HE-PL-2490 | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | 155 | 5 | 2024-03-18 | 2024-08-09 | 18-Mar-24 A | 2024-11-01 | 3
Pipeline Alignment Sheets - 4" Nitrogen |  | 170 | 5 | 2024-02-26 | 2024-08-02 | 26-Feb-24 A | 2024-11-01 | 23
HE-PL-2510 | Issue ICR - Pipeline Alignment Sheets-4" | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-PL-2520 | Receive Company Comments - Pipeline Alignment Sheets-4" | 9 | 0 | 2024-03-10 | 2024-03-25 | 10-Mar-24 A | 25-Mar-24 A
HE-PL-2530 | Re-Issue for Approval - Pipeline Alignment Sheets-4" | 8 | 0 | 2024-03-25 | 2024-04-07 | 25-Mar-24 A | 07-Apr-24 A
HE-PL-2540 | Obtain Company Approval - Pipeline Alignment Sheets-4" | 9 | 0 | 2024-04-12 | 2024-04-25 | 12-Apr-24 A | 25-Apr-24 A
HE-PL-2550 | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | 122 | 5 | 2024-05-10 | 2024-08-02 | 10-May-24 A | 2024-11-01 | 23
Pipeline Alignment Sheets - 4" Waterline |  | 170 | 5 | 2024-02-26 | 2024-08-02 | 26-Feb-24 A | 2024-11-01 | 49
HE-PL-3530 | Issue ICR - Pipeline Alignment Sheets-4" | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-PL-3540 | Receive Company Comments - Pipeline Alignment Sheets-4" | 9 | 0 | 2024-03-10 | 2024-03-25 | 10-Mar-24 A | 25-Mar-24 A
HE-PL-3550 | Re-Issue for Approval - Pipeline Alignment Sheets-4" | 7 | 0 | 2024-03-26 | 2024-04-07 | 26-Mar-24 A | 07-Apr-24 A
HE-PL-3560 | Obtain Company Approval - Pipeline Alignment Sheets-4" | 9 | 0 | 2024-04-12 | 2024-04-25 | 12-Apr-24 A | 25-Apr-24 A
HE-PL-3570 | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | 5 | 5 | 2024-07-29 | 2024-08-02 | 2024-10-28 | 2024-11-01 | 49
Pipeline Station approach drawing - 56" |  | 158 | 10 | 2024-03-29 | 2024-09-06 | 29-Mar-24 A | 2024-11-15 | 72
HE-PL-2570 | Issue ICR - Pipeline Station Approach drawing -56" | 5 | 0 | 2024-03-29 | 2024-04-07 | 29-Mar-24 A | 07-Apr-24 A
HE-PL-2580 | Receive Company Comments - Pipeline Station Approach drawing -56" | 9 | 0 | 2024-04-08 | 2024-04-25 | 08-Apr-24 A | 25-Apr-24 A
HE-PL-2590 | Re-Issue for Approval - Pipeline Station Approach drawing -56" | 25 | 0 | 2024-04-26 | 2024-05-31 | 26-Apr-24 A | 31-May-24 A
HE-PL-2600 | Obtain Company Approval - Pipeline Station Approach drawing -56" | 9 | 0 | 2024-06-01 | 2024-06-14 | 01-Jun-24 A | 14-Jun-24 A
HE-PL-2610 | Final Issue for Design/ Construction-Pipeline Station approach drawing - 56" | 96 | 10 | 2024-08-26 | 2024-09-06 | 04-Jul-24 A | 2024-11-15 | 72
Pipeline Station approach drawing - 52" |  | 147 | 5 | 2024-03-31 | 2024-08-23 | 31-Mar-24 A | 2024-11-01 | 4
HE-PL-2630 | Issue ICR - Pipeline Station Approach drawing -52" | 15 | 0 | 2024-03-31 | 2024-04-26 | 31-Mar-24 A | 26-Apr-24 A
HE-PL-2640 | Receive Company Comments - Pipeline Station Approach drawing -52" | 21 | 0 | 2024-07-29 | 2024-08-02 | 26-Apr-24 A | 25-May-24 A
HE-PL-2650 | Re-Issue for Approval - Pipeline Station Approach drawing -52" | 7 | 0 | 2024-08-05 | 2024-08-09 | 27-May-24 A | 04-Jun-24 A
HE-PL-2660 | Obtain Company Approval - Pipeline Station Approach drawing -52" | 19 | 0 | 2024-08-12 | 2024-08-16 | 05-Jun-24 A | 04-Jul-24 A
HE-PL-2670 | Final Issue for Design/ Construction-Pipeline Station approach drawing-52" | 85 | 5 | 2024-08-19 | 2024-08-23 | 05-Jul-24 A | 2024-11-01 | 4
Pipeline Station approach drawing - 4" Nitrogen |  | 148 | 5 | 2024-03-29 | 2024-08-23 | 29-Mar-24 A | 2024-11-01 | 114
HE-PL-2690 | Issue ICR - Pipeline Station Approach drawing -4" | 28 | 0 | 2024-03-29 | 2024-05-14 | 29-Mar-24 A | 14-May-24 A
HE-PL-2700 | Receive Company Comments - Pipeline Station Approach drawing -4" | 10 | 0 | 2024-05-15 | 2024-05-29 | 15-May-24 A | 29-May-24 A
HE-PL-2710 | Re-Issue for Approval - Pipeline Station Approach drawing -4" | 24 | 0 | 2024-05-30 | 2024-08-02 | 30-May-24 A | 08-Jul-24 A
HE-PL-2720 | Obtain Company Approval - Pipeline Station Approach drawing -4" | 5 | 0 | 2024-08-05 | 2024-08-16 | 09-Jul-24 A | 15-Jul-24 A
HE-PL-2730 | Final Issue for Design/ Construction-Pipeline Station approach drawing-4" | 5 | 5 | 2024-08-19 | 2024-08-23 | 2024-10-28 | 2024-11-01 | 114
Pipeline Station approach drawing - 4" Waterline |  | 148 | 5 | 2024-07-29 | 2024-09-20 | 29-Mar-24 A | 2024-11-01 | 114
HE-PL-3580 | Issue ICR - Pipeline Station Approach drawing -4" | 29 | 0 | 2024-07-29 | 2024-08-09 | 29-Mar-24 A | 14-May-24 A
HE-PL-3590 | Receive Company Comments - Pipeline Station Approach drawing -4" | 11 | 0 | 2024-08-12 | 2024-08-23 | 15-May-24 A | 29-May-24 A
HE-PL-3600 | Re-Issue for Approval - Pipeline Station Approach drawing -4" | 63 | 0 | 2024-08-26 | 2024-08-30 | 30-May-24 A | 02-Sep-24 A
HE-PL-3610 | Obtain Company Approval - Pipeline Station Approach drawing -4" | 9 | 0 | 2024-09-02 | 2024-09-13 | 03-Sep-24 A | 13-Sep-24 A
HE-PL-3620 | Final Issue for Design/ Construction-Pipeline Station approach drawing-4" | 5 | 5 | 2024-09-16 | 2024-09-20 | 2024-10-28 | 2024-11-01 | 114
Pipeline Route Verification and Selection Report |  | 117 | 0 | 2024-07-29 | 2024-09-20 | 06-May-24 A | 21-Oct-24 A
HE-PL-2750 | Issue ICR - Pipeline Route Verification and Selection Report | 10 | 0 | 2024-07-29 | 2024-08-09 | 06-May-24 A | 20-May-24 A
HE-PL-2760 | Receive Company Comments - Pipeline Route Verification and Selection Report | 9 | 0 | 2024-08-12 | 2024-08-23 | 21-May-24 A | 31-May-24 A
HE-PL-2770 | Re-Issue for Approval - Pipeline Route Verification and Selection Report | 10 | 0 | 2024-08-26 | 2024-08-30 | 03-Jun-24 A | 17-Jun-24 A
HE-PL-2780 | Obtain Company Approval - Pipeline Route Verification and Selection Report | 69 | 0 | 2024-09-02 | 2024-09-13 | 18-Jun-24 A | 26-Sep-24 A
HE-PL-2790 | Final Issue for Design/ Construction-Pipeline Route Verification and Selection Report | 11 | 0 | 2024-09-16 | 2024-09-20 | 07-Oct-24 A | 21-Oct-24 A
Pipeline Stress Analysis Report |  | 136 | 5 | 2024-05-06 | 2024-09-13 | 06-May-24 A | 2024-11-15 | 72
HE-PL-2810 | Issue ICR - Pipeline Stress Analysis Report | 8 | 0 | 2024-05-06 | 2024-05-16 | 06-May-24 A | 16-May-24 A
HE-PL-2820 | Receive Company Comments - Pipeline Stress Analysis Report | 5 | 0 | 2024-05-17 | 2024-05-24 | 17-May-24 A | 24-May-24 A
HE-PL-2830 | Re-Issue for Approval - Pipeline Stress Analysis Report | 4 | 0 | 2024-05-26 | 2024-05-31 | 26-May-24 A | 31-May-24 A
HE-PL-2840 | Obtain Company Approval - Pipeline Stress Analysis Report | 11 | 0 | 2024-06-01 | 2024-06-21 | 01-Jun-24 A | 21-Jun-24 A
HE-PL-2850 | Final Issue for Design/ Construction-Pipeline Stress Analysis Report | 114 | 5 | 2024-09-09 | 2024-09-13 | 05-Jun-24 A | 2024-11-15 | 72
Detailed crossing drawings - 56" |  | 181 | 5 | 2024-02-09 | 2024-09-06 | 09-Feb-24 A | 2024-11-01 | 24
HE-PL-2870 | Issue ICR - Detailed crossing drawings - 56" | 33 | 0 | 2024-02-09 | 2024-03-29 | 09-Feb-24 A | 29-Mar-24 A
HE-PL-2880 | Receive Company Comments - Detailed crossing drawings - 56" | 95 | 0 | 2024-03-21 | 2024-08-09 | 21-Mar-24 A | 13-Aug-24 A
HE-PL-2890 | Re-Issue for Approval - Detailed crossing drawings - 56" | 107 | 0 | 2024-05-13 | 2024-08-09 | 13-May-24 A | 14-Oct-24 A
HE-PL-2900 | Obtain Company Approval - Detailed crossing drawings - 56" | 105 | 0 | 2024-08-12 | 2024-08-23 | 26-May-24 A | 24-Oct-24 A
HE-PL-2910 | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | 97 | 5 | 2024-08-26 | 2024-09-06 | 14-Jun-24 A | 2024-11-01 | 24
Crossing Schedule - 56" |  | 181 | 5 | 2024-07-29 | 2024-09-20 | 09-Feb-24 A | 2024-11-01 | 24
HE-PL-2930 | Issue ICR - Crossing Schedule - 56" | 6 | 0 | 2024-07-29 | 2024-08-09 | 09-Feb-24 A | 16-Feb-24 A
HE-PL-2940 | Receive Company Comments - Crossing Schedule - 56" | 54 | 0 | 2024-08-12 | 2024-08-23 | 17-Feb-24 A | 10-May-24 A
HE-PL-2950 | Re-Issue for Approval - Crossing Schedule - 56" | 15 | 0 | 2024-08-26 | 2024-08-30 | 13-May-24 A | 31-May-24 A
HE-PL-2960 | Obtain Company Approval - Crossing Schedule - 56" | 10 | 0 | 2024-09-02 | 2024-09-13 | 03-Jun-24 A | 14-Jun-24 A
HE-PL-2970 | Final Issue for Design/ Construction-Crossing Schedule - 56" | 5 | 5 | 2024-09-16 | 2024-09-20 | 2024-10-28 | 2024-11-01 | 24
Detailed crossing drawings-52" |  | 206 | 30 | 2024-02-09 | 2024-10-04 | 09-Feb-24 A | 2024-12-10 | 224
HE-PL-2990 | Issue ICR - Detailed crossing drawings-52" | 29 | 0 | 2024-02-09 | 2024-03-22 | 09-Feb-24 A | 22-Mar-24 A
HE-PL-3000 | Receive Company Comments - Detailed crossing drawings-52" | 117 | 0 | 2024-03-15 | 2024-08-09 | 15-Mar-24 A | 07-Sep-24 A
HE-PL-3010 | Re-Issue for Approval - Detailed crossing drawings-52" | 138 | 0 | 2024-03-04 | 2024-08-23 | 04-Mar-24 A | 26-Sep-24 A
HE-PL-3020 | Obtain Company Approval - Detailed crossing drawings-52" | 116 | 10 | 2024-08-26 | 2024-09-06 | 26-May-24 A | 2024-11-08 | 224
HE-PL-3030 | Final Issue for Design/ Construction-Detailed crossing drawings-52" | 122 | 20 | 2024-09-09 | 2024-10-04 | 14-Jun-24 A | 2024-12-10 | 224
Crossing Schedule-52" |  | 171 | 5 | 2024-07-29 | 2024-09-20 | 23-Feb-24 A | 2024-11-01 | 48
HE-PL-3050 | Issue ICR - Crossing Schedule-52" | 35 | 0 | 2024-07-29 | 2024-08-09 | 23-Feb-24 A | 20-Apr-24 A
HE-PL-3060 | Receive Company Comments - Crossing Schedule-52" | 11 | 0 | 2024-08-12 | 2024-08-23 | 22-Apr-24 A | 06-May-24 A
HE-PL-3070 | Re-Issue for Approval - Crossing Schedule-52" | 15 | 0 | 2024-08-26 | 2024-08-30 | 07-May-24 A | 27-May-24 A
HE-PL-3080 | Obtain Company Approval - Crossing Schedule-52" | 68 | 0 | 2024-09-02 | 2024-09-13 | 28-May-24 A | 04-Sep-24 A
HE-PL-3090 | Final Issue for Design/ Construction-Crossing Schedule-52" | 5 | 5 | 2024-09-16 | 2024-09-20 | 2024-10-28 | 2024-11-01 | 48
Detailed crossing drawings-4" |  | 196 | 30 | 2024-02-23 | 2024-09-06 | 23-Feb-24 A | 2024-12-10 | 76
HE-PL-3110 | Issue ICR - Detailed crossing drawings-4" | 20 | 0 | 2024-02-23 | 2024-03-25 | 23-Feb-24 A | 25-Mar-24 A
HE-PL-3120 | Receive Company Comments - Detailed crossing drawings-4" | 142 | 10 | 2024-04-19 | 2024-08-09 | 19-Apr-24 A | 2024-11-08 | 86
HE-PL-3130 | Re-Issue for Approval - Detailed crossing drawings-4" | 142 | 20 | 2024-05-03 | 2024-08-23 | 03-May-24 A | 2024-11-22 | 76
HE-PL-3140 | Obtain Company Approval - Detailed crossing drawings-4" | 5 | 5 | 2024-08-26 | 2024-08-30 | 2024-11-25 | 2024-11-29 | 76
HE-PL-3150 | Final Issue for Design/ Construction-Detailed crossing drawings-4" | 5 | 5 | 2024-09-02 | 2024-09-06 | 2024-12-04 | 2024-12-10 | 76
Crossing Schedule-4" |  | 201 | 40 | 2024-07-29 | 2024-10-04 | 01-Mar-24 A | 2024-12-24 | 229
HE-PL-3170 | Issue ICR - Crossing Schedule-4" | 38 | 0 | 2024-07-29 | 2024-08-09 | 01-Mar-24 A | 01-May-24 A
HE-PL-3180 | Receive Company Comments - Crossing Schedule-4" | 18 | 0 | 2024-08-12 | 2024-08-23 | 02-May-24 A | 27-May-24 A
HE-PL-3190 | Re-Issue for Approval - Crossing Schedule-4" | 115 | 10 | 2024-08-26 | 2024-09-06 | 28-May-24 A | 2024-11-08 | 239
HE-PL-3200 | Obtain Company Approval - Crossing Schedule-4" | 10 | 10 | 2024-09-09 | 2024-09-20 | 2024-11-11 | 2024-11-22 | 239
HE-PL-3210 | Final Issue for Design/ Construction-Crossing Schedule-4" | 10 | 10 | 2024-09-23 | 2024-10-04 | 2024-12-11 | 2024-12-24 | 229
Pipeline Tie In List |  | 72 | 0 | 2024-02-26 | 2024-06-13 | 26-Feb-24 A | 13-Jun-24 A
HE-PL-3330 | Issue ICR - Pipeline Tie In List | 14 | 0 | 2024-02-26 | 2024-03-17 | 26-Feb-24 A | 17-Mar-24 A
HE-PL-3340 | Receive Company Comments - Pipeline Tie In List | 5 | 0 | 2024-03-31 | 2024-04-09 | 31-Mar-24 A | 09-Apr-24 A
HE-PL-3350 | Re-Issue for Approval - Pipeline Tie In List | 2 | 0 | 2024-04-10 | 2024-04-16 | 10-Apr-24 A | 16-Apr-24 A
HE-PL-3360 | Obtain Company Approval - Pipeline Tie In List | 9 | 0 | 2024-04-17 | 2024-04-30 | 17-Apr-24 A | 30-Apr-24 A
HE-PL-3370 | Final Issue for Design/ Construction-Pipeline Tie In List | 22 | 0 | 2024-05-14 | 2024-06-13 | 14-May-24 A | 13-Jun-24 A
Pipeline Support Schdule |  | 100 | 0 | 2024-04-05 | 2024-08-09 | 05-Apr-24 A | 02-Sep-24 A
HE-PL-3780 | Issue ICR - Pipeline Support Schedule | 2 | 0 | 2024-04-05 | 2024-04-12 | 05-Apr-24 A | 12-Apr-24 A
HE-PL-3790 | Receive Company Comments - Pipeline Support Schedule | 9 | 0 | 2024-04-13 | 2024-04-26 | 13-Apr-24 A | 26-Apr-24 A
HE-PL-3800 | Re-Issue for Approval - Pipeline Support Schedule | 9 | 0 | 2024-04-27 | 2024-05-10 | 27-Apr-24 A | 10-May-24 A
HE-PL-3810 | Obtain Company Approval - Pipeline Support Schedule | 9 | 0 | 2024-05-11 | 2024-05-24 | 11-May-24 A | 24-May-24 A
HE-PL-3820 | Final Issue for Design/ Construction- Pipeline Support Schedule | 58 | 0 | 2024-06-07 | 2024-08-09 | 07-Jun-24 A | 02-Sep-24 A
Pipeline MTO - 56", 52" and 4" |  | 32 | 0 | 2024-02-16 | 2024-04-05 | 16-Feb-24 A | 05-Apr-24 A
HE-PL-3230 | Issue ICR - Pipeline MTO - 56" | 10 | 0 | 2024-02-16 | 2024-03-01 | 16-Feb-24 A | 01-Mar-24 A
HE-PL-3240 | Receive Company Comments - Pipeline MTO - 56" | 8 | 0 | 2024-03-02 | 2024-03-15 | 02-Mar-24 A | 15-Mar-24 A
HE-PL-3250 | Re-Issue for Approval - Pipeline MTO - 56" | 3 | 0 | 2024-03-16 | 2024-03-22 | 16-Mar-24 A | 22-Mar-24 A
HE-PL-3260 | Obtain Company Approval - Pipeline MTO - 56" | 0 | 0 | 2024-03-22 | 2024-03-22 | 22-Mar-24 A | 22-Mar-24 A
HE-PL-3270 | Final Issue for Design/ Construction-Pipeline MTO - 56" and 52" | 10 | 0 | 2024-03-20 | 2024-04-05 | 20-Mar-24 A | 05-Apr-24 A
Pipeline Coating MTO |  | 32 | 0 | 2024-02-16 | 2024-04-05 | 16-Feb-24 A | 05-Apr-24 A
HE-PL-3730 | Issue ICR - Pipeline Coating MTO | 10 | 0 | 2024-02-16 | 2024-03-01 | 16-Feb-24 A | 01-Mar-24 A
HE-PL-3740 | Receive Company Comments - Pipeline Coating MTO | 8 | 0 | 2024-03-02 | 2024-03-15 | 02-Mar-24 A | 15-Mar-24 A
HE-PL-3750 | Re-Issue for Approval - Pipeline Coating MTO | 3 | 0 | 2024-03-16 | 2024-03-22 | 16-Mar-24 A | 22-Mar-24 A
HE-PL-3760 | Obtain Company Approval - Pipeline Coating MTO | 1 | 0 | 2024-03-20 | 2024-03-22 | 20-Mar-24 A | 22-Mar-24 A
HE-PL-3770 | Final Issue for Design/ Construction-Pipeline Coating MTO | 9 | 0 | 2024-03-22 | 2024-04-05 | 22-Mar-24 A | 05-Apr-24 A
Piping |  | 353 | 45 | 2023-08-06 | 2024-12-17 | 06-Aug-23 A | 2024-12-31 | 208
Piping Design Basis |  | 75 | 0 | 2023-08-06 | 2023-11-20 | 06-Aug-23 A | 20-Nov-23 A
HE-DB-130 | Issue ICR-Design Basis | 7 | 0 | 2023-08-06 | 2023-08-16 | 06-Aug-23 A | 16-Aug-23 A
HE-DB-140 | Receive Company Comments-Design Basis | 7 | 0 | 2023-08-16 | 2023-08-25 | 16-Aug-23 A | 25-Aug-23 A
HE-DB-100 | Re-Issue for Approval-Design Basis | 4 | 0 | 2023-09-11 | 2023-09-15 | 11-Sep-23 A | 15-Sep-23 A
HE-DB-120 | Obtain Company Approval-Design Basis | 5 | 0 | 2023-09-18 | 2023-09-25 | 18-Sep-23 A | 25-Sep-23 A
HE-DB-110 | Final Issue for Design/ Construction-Design Basis | 7 | 0 | 2023-11-09 | 2023-11-20 | 09-Nov-23 A | 20-Nov-23 A
Piping Specifications - Addendum to DGS |  | 102 | 0 | 2023-10-20 | 2024-03-15 | 20-Oct-23 A | 15-Mar-24 A
HE-PI-3440 | Issue ICR - Piping Specifications - Addendum to DGS | 3 | 0 | 2023-10-20 | 2023-10-25 | 20-Oct-23 A | 25-Oct-23 A
HE-PI-3450 | Receive Company Comments - Piping Specifications - Addendum to DGS | 5 | 0 | 2023-10-30 | 2023-11-06 | 30-Oct-23 A | 06-Nov-23 A
HE-PI-3460 | Re-Issue for Approval - Piping Specifications - Addendum to DGS | 10 | 0 | 2023-11-07 | 2023-11-21 | 07-Nov-23 A | 21-Nov-23 A
HE-PI-3470 | Obtain Company Approval - Piping Specifications - Addendum to DGS | 14 | 0 | 2023-11-22 | 2023-12-13 | 22-Nov-23 A | 13-Dec-23 A
HE-PI-3430 | Final Issue for Design/ Construction-Piping Specifications - Addendum to DGS | 77 | 0 | 2023-11-24 | 2024-03-15 | 24-Nov-23 A | 15-Mar-24 A
Piping Tie In Schedule |  | 87 | 0 | 2023-12-04 | 2024-04-10 | 04-Dec-23 A | 10-Apr-24 A
HE-PI-3480 | Issue ICR-Piping Tie In Schedule | 15 | 0 | 2023-12-04 | 2023-12-23 | 04-Dec-23 A | 23-Dec-23 A
HE-PI-3490 | Receive Company Comments-Piping Tie In Schedule | 14 | 0 | 2023-12-25 | 2024-01-15 | 25-Dec-23 A | 15-Jan-24 A
HE-PI-3500 | Re-Issue for Approval-Piping Tie In Schedule | 15 | 0 | 2024-02-26 | 2024-03-18 | 26-Feb-24 A | 18-Mar-24 A
HE-PI-3510 | Obtain Company Approval-Piping Tie In Schedule | 7 | 0 | 2024-03-19 | 2024-03-30 | 19-Mar-24 A | 30-Mar-24 A
HE-PI-3520 | Final Issue for Design/ Construction-Piping Tie In Schedule | 3 | 0 | 2024-04-03 | 2024-04-10 | 03-Apr-24 A | 10-Apr-24 A
Piping Material Specification |  | 132 | 0 | 2023-08-27 | 2024-03-01 | 27-Aug-23 A | 01-Mar-24 A
HE-PI-0010 | Issue ICR-Piping Material Specifications | 7 | 0 | 2023-08-27 | 2023-09-06 | 27-Aug-23 A | 06-Sep-23 A
HE-PI-0020 | Receive Company Comments-Piping Material Specifications | 8 | 0 | 2023-09-06 | 2023-09-16 | 06-Sep-23 A | 16-Sep-23 A
HE-PI-0030 | Re-Issue for Approval-Piping Material Specifications | 3 | 0 | 2023-10-30 | 2023-11-02 | 30-Oct-23 A | 02-Nov-23 A
HE-PI-0040 | Obtain Company Approval-Piping Material Specifications | 10 | 0 | 2023-11-03 | 2023-11-17 | 03-Nov-23 A | 17-Nov-23 A
HE-PI-0050 | Final Issue for Design/ Construction-Piping Material Specification | 71 | 0 | 2023-11-21 | 2024-03-01 | 21-Nov-23 A | 01-Mar-24 A
3D Model |  | 199 | 0 | 2023-11-08 | 2024-08-09 | 08-Nov-23 A | 28-Aug-24 A
HE-PI-0130 | 30% Model Review | 1 | 0 | 2023-11-08 | 2023-11-09 | 08-Nov-23 A | 09-Nov-23 A
HE-PI-0140 | 30% Model Review Report | 8 | 0 | 2023-11-10 | 2023-11-22 | 10-Nov-23 A | 22-Nov-23 A
HE-PI-0150 | 60% Model Review | 1 | 0 | 2024-03-25 | 2024-03-27 | 25-Mar-24 A | 27-Mar-24 A
HE-PI-0160 | 60% Model Review Report | 6 | 0 | 2024-03-22 | 2024-04-01 | 22-Mar-24 A | 01-Apr-24 A
HE-PI-0170 | 90% Model Review | 5 | 0 | 2024-07-22 | 2024-07-26 | 22-Jul-24 A | 26-Jul-24 A
HE-PI-0180 | 90% Model Review Report | 23 | 0 | 2024-07-29 | 2024-08-09 | 27-Jul-24 A | 28-Aug-24 A
Pipe Wall Thickness Calculation |  | 108 | 0 | 2023-08-15 | 2024-01-16 | 15-Aug-23 A | 16-Jan-24 A
HE-PI-0200 | Issue ICR-Pipe Wall Thickness Calculation | 8 | 0 | 2023-08-15 | 2023-08-25 | 15-Aug-23 A | 25-Aug-23 A
HE-PI-0210 | Receive Company Comments-Pipe Wall Thickness Calculation | 9 | 0 | 2023-09-11 | 2023-09-22 | 11-Sep-23 A | 22-Sep-23 A
HE-PI-0220 | Re-Issue for Approval-Pipe Wall Thickness Calculation | 4 | 0 | 2023-09-25 | 2023-09-29 | 25-Sep-23 A | 29-Sep-23 A
HE-PI-0230 | Obtain Company Approval-Pipe Wall Thickness Calculation | 6 | 0 | 2023-12-29 | 2024-01-09 | 29-Dec-23 A | 09-Jan-24 A
HE-PI-0240 | Final Issue for Design/ Construction-Pipe Wall Thickness Calculation | 2 | 0 | 2024-01-12 | 2024-01-16 | 12-Jan-24 A | 16-Jan-24 A
Critical line List |  | 152 | 0 | 2023-11-06 | 2024-06-19 | 06-Nov-23 A | 19-Jun-24 A
HE-PI-0262 | Issue ICR-Critical line List | 7 | 0 | 2023-11-06 | 2023-11-15 | 06-Nov-23 A | 15-Nov-23 A
HE-PI-0272 | Receive Company Comments-Critical line List | 7 | 0 | 2023-11-16 | 2023-11-25 | 16-Nov-23 A | 25-Nov-23 A
HE-PI-0282 | Re-Issue for Approval-Critical line List | 17 | 0 | 2023-11-28 | 2023-12-22 | 28-Nov-23 A | 22-Dec-23 A
HE-PI-0292 | Obtain Company Approval-Critical line List | 10 | 0 | 2024-01-10 | 2024-01-24 | 10-Jan-24 A | 24-Jan-24 A
HE-PI-0302 | Final Issue for Design/ Construction-Critical line List | 94 | 0 | 2024-01-29 | 2024-06-19 | 29-Jan-24 A | 19-Jun-24 A
Plot Plan |  | 284 | 5 | 2023-09-15 | 2024-08-23 | 15-Sep-23 A | 2024-11-01 | 71
Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) |  | 284 | 5 | 2023-09-15 | 2024-08-23 | 15-Sep-23 A | 2024-11-01 | 71
HE-PI-0320 | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | 9 | 0 | 2023-09-15 | 2023-09-28 | 15-Sep-23 A | 28-Sep-23 A
HE-PI-0330 | Receive Company Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | 2 | 0 | 2023-11-07 | 2023-11-09 | 07-Nov-23 A | 09-Nov-23 A
HE-PI-0340 | Re-Issue for HAZOP Studies- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | 3 | 0 | 2023-11-10 | 2023-11-15 | 10-Nov-23 A | 15-Nov-23 A
HE-PI-0350 | Re-Issue after HAZOP /Review Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | 7 | 0 | 2023-11-28 | 2023-12-08 | 28-Nov-23 A | 08-Dec-23 A
HE-PI-0360 | Obtain Company Approval- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | 10 | 0 | 2023-12-12 | 2023-12-26 | 12-Dec-23 A | 26-Dec-23 A
HE-PI-0370 | Final Issue for Design/ Construction-Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | 56 | 5 | 2024-08-19 | 2024-08-23 | 16-Aug-24 A | 2024-11-01 | 71
Overall Plot Plan - 52" Pipeline SWEIHAN CRS |  | 281 | 5 | 2023-09-20 | 2024-08-23 | 20-Sep-23 A | 2024-11-01 | 34
HE-PI-0390 | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | 5 | 0 | 2023-09-20 | 2023-09-27 | 20-Sep-23 A | 27-Sep-23 A
HE-PI-0400 | Receive Company Comments- Overall Plot Plan - 52" Pipeline SWEIHAN CRS | 9 | 0 | 2023-10-02 | 2023-10-13 | 02-Oct-23 A | 13-Oct-23 A
HE-PI-0410 | Re-Issue for HAZOP Studies- Overall Plot Plan - 52" Pipeline SWEIHAN CRS | 6 | 0 | 2023-10-30 | 2023-11-07 | 30-Oct-23 A | 07-Nov-23 A
HE-PI-0420 | Re-Issue after incorporating HAZOP /Review Comments - 52" Pipeline SWEIHAN CRS | 10 | 0 | 2023-11-08 | 2023-11-22 | 08-Nov-23 A | 22-Nov-23 A
HE-PI-0430 | Obtain Company Approval- Overall Plot Plan - 52" Pipeline SWEIHAN CRS | 10 | 0 | 2024-01-09 | 2024-01-23 | 09-Jan-24 A | 23-Jan-24 A
HE-PI-0440 | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | 56 | 5 | 2024-08-19 | 2024-08-23 | 16-Aug-24 A | 2024-11-01 | 34
Overall Plot Plan - 4" N2 Source Pipeline |  | 284 | 5 | 2023-09-15 | 2024-08-23 | 15-Sep-23 A | 2024-11-01 | 66
HE-PI-0460 | Issue ICR- Overall Plot Plan - 4" N2 Source Pipeline | 9 | 0 | 2023-09-15 | 2023-09-28 | 15-Sep-23 A | 28-Sep-23 A
HE-PI-0470 | Receive Company Comments- Overall Plot Plan - 4" N2 Source Pipeline | 9 | 0 | 2023-10-02 | 2023-10-13 | 02-Oct-23 A | 13-Oct-23 A
HE-PI-0480 | Re-Issue for HAZOP Studies- Overall Plot Plan - 4" N2 Source Pipeline | 6 | 0 | 2023-10-30 | 2023-11-07 | 30-Oct-23 A | 07-Nov-23 A
HE-PI-0490 | Re-Issue after incorporating HAZOP /Review Comments - 4" N2 Source Pipeline | 10 | 0 | 2023-11-08 | 2023-11-22 | 08-Nov-23 A | 22-Nov-23 A
HE-PI-0500 | Obtain Company Approval- Overall Plot Plan - 4" N2 Source Pipeline | 9 | 0 | 2024-07-29 | 2024-08-09 | 30-Apr-24 A | 10-May-24 A
HE-PI-0510 | Final Issue for Design/ Construction-Overall Plot Plan- 4" N2 Source Pipeline | 56 | 5 | 2024-08-19 | 2024-08-23 | 16-Aug-24 A | 2024-11-01 | 66
Plot Plan - Block Valve Station (7 nos) |  | 284 | 5 | 2023-09-15 | 2024-08-23 | 15-Sep-23 A | 2024-11-01 | 71
HE-PI-0530 | Issue ICR- Plot plan - BVS | 9 | 0 | 2023-09-15 | 2023-09-28 | 15-Sep-23 A | 28-Sep-23 A
HE-PI-0540 | Receive Company Comments- Plot plan - BVS | 9 | 0 | 2023-10-02 | 2023-10-13 | 02-Oct-23 A | 13-Oct-23 A
HE-PI-0550 | Re-Issue for HAZOP Studies- Plot plan - BVS | 6 | 0 | 2023-10-30 | 2023-11-07 | 30-Oct-23 A | 07-Nov-23 A
HE-PI-0560 | Re-Issue after incorporating HAZOP / Review Comments- Plot plan - BVS | 10 | 0 | 2023-11-08 | 2023-11-22 | 08-Nov-23 A | 22-Nov-23 A
HE-PI-0570 | Obtain Company Approval- Plot plan - BVS | 5 | 0 | 2024-01-15 | 2024-01-22 | 15-Jan-24 A | 22-Jan-24 A
HE-PI-0580 | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | 56 | 5 | 2024-08-19 | 2024-08-23 | 16-Aug-24 A | 2024-11-01 | 71
GA Drawings |  | 85 | 45 | 2024-08-26 | 2024-12-17 | 02-Sep-24 A | 2024-12-31 | 31
Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) |  | 35 | 5 | 2024-08-26 | 2024-10-18 | 29-Sep-24 A | 2024-11-15 | 61
HE-PI-0600 | Issue ICR-Piping GA-56" Pipeline Launcher and metering Station (Habshan Complex) | 5 | 0 | 2024-08-26 | 2024-09-06 | 29-Sep-24 A | 04-Oct-24 A
HE-PI-0610 | Receive Company Comments-56" Pipeline Launcher and metering Station (Habshan Complex) | 6 | 0 | 2024-09-09 | 2024-09-20 | 04-Oct-24 A | 11-Oct-24 A
HE-PI-0620 | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | 6 | 0 | 2024-09-23 | 2024-09-27 | 11-Oct-24 A | 18-Oct-24 A
HE-PI-0630 | Obtain Company Approval-Piping GA-56" Pipeline Launcher and metering Station (Habshan Complex) | 4 | 0 | 2024-09-30 | 2024-10-11 | 18-Oct-24 A | 23-Oct-24 A
HE-PI-0640 | Final Issue for Design/ Construction-Piping GA- 56" Pipeline Launcher and metering Station (Habshan Complex) | 17 | 5 | 2024-10-14 | 2024-10-18 | 24-Oct-24 A | 2024-11-15 | 61
Piping GA - 52" Pipeline SWEIHAN CRS |  | 55 | 5 | 2024-09-09 | 2024-11-01 | 02-Sep-24 A | 2024-11-15 | 61
HE-PI-0660 | Issue ICR-Piping GA for 52" Pipeline SWEIHAN CRS | 5 | 0 | 2024-09-09 | 2024-09-20 | 02-Sep-24 A | 06-Sep-24 A
HE-PI-0670 | Receive Company Comments-Piping GA for 52" Pipeline SWEIHAN CRS | 5 | 0 | 2024-09-23 | 2024-10-04 | 09-Sep-24 A | 13-Sep-24 A
HE-PI-0680 | Re-Issue for Approval-Piping GA for 52" Pipeline SWEIHAN CRS | 5 | 0 | 2024-10-07 | 2024-10-11 | 16-Sep-24 A | 20-Sep-24 A
HE-PI-0690 | Obtain Company Approval-Piping GA for 52" Pipeline SWEIHAN CRS | 5 | 0 | 2024-10-14 | 2024-10-25 | 23-Sep-24 A | 27-Sep-24 A
HE-PI-0700 | Final Issue for Design/ Construction-Piping GA- 52" Pipeline SWEIHAN CRS | 29 | 5 | 2024-10-28 | 2024-11-01 | 08-Oct-24 A | 2024-11-15 | 61
Piping GA - 4" N2 Source Pipeline |  | 45 | 45 | 2024-09-23 | 2024-11-22 | 2024-10-28 | 2024-12-31 | 31
HE-PI-0720 | Issue ICR- Piping GA for 4" N2 Source Pipeline | 10 | 10 | 2024-09-23 | 2024-10-04 | 2024-10-28 | 2024-11-08 | 31
HE-PI-0730 | Receive Company Comments-Piping GA for 4" N2 Source Pipeline | 10 | 10 | 2024-10-07 | 2024-10-18 | 2024-11-11 | 2024-11-22 | 31
HE-PI-0740 | Re-Issue for Approval-Piping GA for 4" N2 Source Pipeline | 10 | 10 | 2024-10-21 | 2024-11-01 | 2024-11-25 | 2024-12-10 | 31
HE-PI-0750 | Obtain Company Approval-Piping GA for 4" N2 Source Pipeline | 10 | 10 | 2024-11-04 | 2024-11-15 | 2024-12-11 | 2024-12-24 | 31
HE-PI-0760 | Final Issue for Design/ Construction-Piping GA for 4" N2 Source Pipeline | 5 | 5 | 2024-11-18 | 2024-11-22 | 2024-12-25 | 2024-12-31 | 31
Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline |  | 55 | 5 | 2024-10-07 | 2024-11-29 | 02-Sep-24 A | 2024-11-15 | 61
HE-PI-0780 | Issue ICR - Piping GA Drawings for 591-BVS-01 | 5 | 0 | 2024-10-07 | 2024-10-18 | 02-Sep-24 A | 06-Sep-24 A
HE-PI-0790 | Receive Company Comments-Piping GA Drawings for 591-BVS-01 | 5 | 0 | 2024-10-21 | 2024-11-01 | 09-Sep-24 A | 13-Sep-24 A
HE-PI-0800 | Re-Issue for Approval-Piping GA Drawings for 591-BVS-01 | 5 | 0 | 2024-11-04 | 2024-11-08 | 16-Sep-24 A | 20-Sep-24 A
HE-PI-0810 | Obtain Company Approval-Piping GA Drawings for 591-BVS-01 | 5 | 0 | 2024-11-11 | 2024-11-22 | 23-Sep-24 A | 27-Sep-24 A
HE-PI-0820 | Final Issue for Design/ Construction-Piping GA Drawings for 591-BVS-01 | 35 | 5 | 2024-11-25 | 2024-11-29 | 30-Sep-24 A | 2024-11-15 | 61
Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline |  | 75 | 5 | 2024-10-21 | 2024-12-17 | 16-Sep-24 A | 2024-12-31 | 31
HE-PI-0840 | Issue ICR-Piping GA for 591-BVS-01 to 06 | 6 | 0 | 2024-10-21 | 2024-11-01 | 16-Sep-24 A | 23-Sep-24 A
HE-PI-0850 | Receive Company Comments-Piping GA for 591-BVS-01 to 06 | 4 | 0 | 2024-11-04 | 2024-11-15 | 23-Sep-24 A | 26-Sep-24 A
HE-PI-0860 | Re-Issue for Approval-Piping GA for 591-BVS-01 to 06 | 3 | 0 | 2024-11-18 | 2024-11-22 | 26-Sep-24 A | 30-Sep-24 A
HE-PI-0870 | Obtain Company Approval-Piping GA for 591-BVS-01 to 06 | 5 | 0 | 2024-11-25 | 2024-12-10 | 30-Sep-24 A | 04-Oct-24 A
HE-PI-0880 | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | 60 | 5 | 2024-12-11 | 2024-12-17 | 07-Oct-24 A | 2024-12-31 | 31
Data Sheets |  | 192 | 0 | 2023-09-22 | 2024-08-09 | 22-Sep-23 A | 02-Jul-24 A
Datasheet for Ball valves |  | 43 | 0 | 2023-09-22 | 2023-11-22 | 22-Sep-23 A | 22-Nov-23 A
HE-PI-0900 | Issue ICR-Data sheet for Ball Valves | 4 | 0 | 2023-09-22 | 2023-09-28 | 22-Sep-23 A | 28-Sep-23 A
HE-PI-0910 | Receive Company Comments-Data sheet for Ball Valves | 7 | 0 | 2023-09-30 | 2023-10-11 | 30-Sep-23 A | 11-Oct-23 A
HE-PI-0920 | Re-Issue for Approval-Data sheet for Ball Valves | 5 | 0 | 2023-10-31 | 2023-11-07 | 31-Oct-23 A | 07-Nov-23 A
HE-PI-0930 | Obtain Company Approval-Data sheet for Ball Valves | 4 | 0 | 2023-11-08 | 2023-11-14 | 08-Nov-23 A | 14-Nov-23 A
HE-PI-0940 | Final Issue for Design/ Construction-Datasheet for Ball valves | 5 | 0 | 2023-11-15 | 2023-11-22 | 15-Nov-23 A | 22-Nov-23 A
Datasheet for Check Valve |  | 43 | 0 | 2023-09-22 | 2023-11-22 | 22-Sep-23 A | 22-Nov-23 A
HE-PI-3580 | Issue ICR-Data sheet for Check Valves | 4 | 0 | 2023-09-22 | 2023-09-28 | 22-Sep-23 A | 28-Sep-23 A
HE-PI-3590 | Receive Company Comments-Data sheet for Check Valves | 8 | 0 | 2023-10-05 | 2023-10-17 | 05-Oct-23 A | 17-Oct-23 A
HE-PI-3600 | Re-Issue for Approval-Data sheet for Check Valves | 5 | 0 | 2023-10-31 | 2023-11-07 | 31-Oct-23 A | 07-Nov-23 A
HE-PI-3610 | Obtain Company Approval-Data sheet for Check Valves | 4 | 0 | 2023-11-08 | 2023-11-14 | 08-Nov-23 A | 14-Nov-23 A
HE-PI-3620 | Final Issue for Design/ Construction-Datasheet for Check valves | 5 | 0 | 2023-11-15 | 2023-11-22 | 15-Nov-23 A | 22-Nov-23 A
Datasheet for Plug valves |  | 43 | 0 | 2023-09-22 | 2023-11-22 | 22-Sep-23 A | 22-Nov-23 A
HE-PI-0960 | Issue ICR- Datasheet for Plug Valves | 4 | 0 | 2023-09-22 | 2023-09-28 | 22-Sep-23 A | 28-Sep-23 A
HE-PI-0970 | Receive Company Comments- Datasheet for Plug Valves | 7 | 0 | 2023-09-30 | 2023-10-11 | 30-Sep-23 A | 11-Oct-23 A
HE-PI-0980 | Re-Issue for Approval- Datasheet for Plug Valves | 5 | 0 | 2023-10-31 | 2023-11-07 | 31-Oct-23 A | 07-Nov-23 A
HE-PI-0990 | Obtain Company Approval- Datasheet for Plug Valves | 4 | 0 | 2023-11-08 | 2023-11-14 | 08-Nov-23 A | 14-Nov-23 A
HE-PI-1000 | Final Issue for Design/ Construction-Datasheet for Plug valves | 5 | 0 | 2023-11-15 | 2023-11-22 | 15-Nov-23 A | 22-Nov-23 A
Datasheet for Piping Special Items |  | 153 | 0 | 2023-11-16 | 2024-08-09 | 16-Nov-23 A | 02-Jul-24 A
HE-PI-1320 | Issue ICR- Datasheet for Piping Special Items | 22 | 0 | 2023-11-16 | 2023-12-19 | 16-Nov-23 A | 19-Dec-23 A
HE-PI-1330 | Receive Company Comments- Datasheet for Piping Special Items | 5 | 0 | 2023-12-19 | 2023-12-26 | 19-Dec-23 A | 26-Dec-23 A
HE-PI-1340 | Re-Issue for Approval- Datasheet for Piping Special Items | 12 | 0 | 2024-01-29 | 2024-02-14 | 29-Jan-24 A | 14-Feb-24 A
HE-PI-1350 | Obtain Company Approval- Datasheet for Piping Special Items | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-PI-1310 | Final Issue for Design/ Construction-Datasheet for Piping Special Items | 73 | 0 | 2024-03-10 | 2024-08-09 | 10-Mar-24 A | 02-Jul-24 A
Material Requisition |  | 231 | 5 | 2023-11-29 | 2024-08-09 | 29-Nov-23 A | 2024-11-01 | 96
Material Requisition for Ball/ Plug Valves |  | 70 | 0 | 2023-11-29 | 2024-03-08 | 29-Nov-23 A | 08-Mar-24 A
HE-PI-1030 | Receive Company Comments-MR for Ball valves/ Plug Valves | 7 | 0 | 2023-11-29 | 2023-12-09 | 29-Nov-23 A | 09-Dec-23 A
HE-PI-1020 | Issue ICR-MR for Ball valves/ Plug Valves | 11 | 0 | 2023-11-29 | 2023-12-15 | 29-Nov-23 A | 15-Dec-23 A
HE-PI-1040 | Re-Issue for Approval-MR for Ball valves/ Plug Valves | 53 | 0 | 2023-12-04 | 2024-02-16 | 04-Dec-23 A | 16-Feb-24 A
HE-PI-1050 | Obtain Company Approval-MR for Ball valves/ Plug Valves | 53 | 0 | 2023-12-04 | 2024-02-16 | 04-Dec-23 A | 16-Feb-24 A
HE-PI-1060 | Final Issue for Design/ Construction-Material Requisition for Ball/ Plug Valves | 15 | 0 | 2024-02-16 | 2024-03-08 | 16-Feb-24 A | 08-Mar-24 A
Material Requisition for Check Valves |  | 71 | 0 | 2023-12-06 | 2024-03-17 | 06-Dec-23 A | 17-Mar-24 A
HE-PI-3630 | Issue ICR-MR for Check Valves | 7 | 0 | 2023-12-06 | 2023-12-15 | 06-Dec-23 A | 15-Dec-23 A
HE-PI-3640 | Receive Company Comments-MR for Check Valves | 5 | 0 | 2023-12-29 | 2024-01-08 | 29-Dec-23 A | 08-Jan-24 A
HE-PI-3650 | Re-Issue for Approval-MR for Check Valves | 14 | 0 | 2024-02-26 | 2024-03-17 | 26-Feb-24 A | 17-Mar-24 A
HE-PI-3660 | Obtain Company Approval-MR for Check Valves | 9 | 0 | 2024-03-04 | 2024-03-17 | 04-Mar-24 A | 17-Mar-24 A
HE-PI-3670 | Final Issue for Design/ Construction-Material Requisition for Check Valves | 9 | 0 | 2024-03-04 | 2024-03-17 | 04-Mar-24 A | 17-Mar-24 A
Material Requisition for Piping Special Items |  | 210 | 5 | 2023-12-29 | 2024-08-09 | 29-Dec-23 A | 2024-11-01 | 96
HE-PI-3680 | Issue ICR-MR for Piping Special Items | 4 | 0 | 2023-12-29 | 2024-01-05 | 29-Dec-23 A | 05-Jan-24 A
HE-PI-3690 | Receive Company Comments-MR for Piping Special Items | 5 | 0 | 2024-01-08 | 2024-01-15 | 08-Jan-24 A | 15-Jan-24 A
HE-PI-3700 | Re-Issue for Approval-MR for Piping Special Items | 43 | 0 | 2024-01-16 | 2024-03-17 | 16-Jan-24 A | 17-Mar-24 A
HE-PI-3710 | Obtain Company Approval-MR for Piping Special Items | 16 | 0 | 2024-03-04 | 2024-03-28 | 04-Mar-24 A | 28-Mar-24 A
HE-PI-3720 | Final Issue for Design/ Construction-Material Requisition for Piping Special Items | 55 | 5 | 2024-08-05 | 2024-08-09 | 19-Aug-24 A | 2024-11-01 | 96
Material Requisition for Piping Bulk |  | 126 | 0 | 2023-12-12 | 2024-06-14 | 12-Dec-23 A | 14-Jun-24 A
HE-PI-3530 | Issue ICR-MR for Piping Bulks | 24 | 0 | 2023-12-12 | 2024-01-16 | 12-Dec-23 A | 16-Jan-24 A
HE-PI-3540 | Receive Company Comments-MR for Piping Bulks | 7 | 0 | 2024-01-17 | 2024-01-26 | 17-Jan-24 A | 26-Jan-24 A
HE-PI-3550 | Re-Issue for Approval-MR for Piping Bulks | 66 | 0 | 2024-01-16 | 2024-04-25 | 16-Jan-24 A | 25-Apr-24 A
HE-PI-3560 | Obtain Company Approval-MR for Piping Bulks | 14 | 0 | 2024-04-26 | 2024-05-16 | 26-Apr-24 A | 16-May-24 A
HE-PI-3570 | Final Issue for Design/ Construction-Material Requisition for Piping Bulks & Special Items | 8 | 0 | 2024-06-04 | 2024-06-14 | 04-Jun-24 A | 14-Jun-24 A
TBE |  | 200 | 15 | 2024-01-29 | 2024-10-11 | 29-Jan-24 A | 2024-11-15 | 238
TBE for Piping Bulks (Pipe, Flange, etc) |  | 181 | 0 | 2024-01-29 | 2024-08-16 | 29-Jan-24 A | 21-Oct-24 A
HE-PI-1360 | Issue ICR- TBE for Piping Bulks (Pipe, Flange, etc) | 46 | 0 | 2024-01-29 | 2024-04-04 | 29-Jan-24 A | 04-Apr-24 A
HE-PI-1370 | Receive Company Comments- TBE for Piping Bulks (Pipe, Flange, etc) | 12 | 0 | 2024-03-19 | 2024-04-06 | 19-Mar-24 A | 06-Apr-24 A
HE-PI-1380 | Re-Issue for Approval- TBE for Piping Bulks (Pipe, Flange, etc) | 30 | 0 | 2024-04-25 | 2024-07-29 | 25-Apr-24 A | 06-Jun-24 A
HE-PI-1390 | Obtain Company Approval- TBE for Piping Bulks (Pipe, Flange, etc) | 20 | 0 | 2024-07-29 | 2024-08-09 | 07-Jun-24 A | 10-Jul-24 A
HE-PI-1400 | Final Issue for Design/ Construction-TBE for Piping Bulks (Pipe, Flange, etc) | 6 | 0 | 2024-08-12 | 2024-08-16 | 14-Oct-24 A | 21-Oct-24 A
TBE for Piping Special Items |  | 102 | 15 | 2024-06-26 | 2024-10-11 | 26-Jun-24 A | 2024-11-15 | 91
HE-PI-1410 | Issue ICR- TBE for Piping Special Items | 22 | 0 | 2024-06-26 | 2024-08-23 | 26-Jun-24 A | 26-Jul-24 A
HE-PI-1420 | Receive Company Comments- TBE for Piping Special Items | 12 | 0 | 2024-08-26 | 2024-09-06 | 29-Jul-24 A | 13-Aug-24 A
HE-PI-1430 | Re-Issue for Approval- TBE for Piping Special Items | 31 | 0 | 2024-09-09 | 2024-09-20 | 14-Aug-24 A | 26-Sep-24 A
HE-PI-1440 | Obtain Company Approval- TBE for Piping Special Items | 10 | 10 | 2024-09-23 | 2024-10-04 | 2024-10-28 | 2024-11-08 | 91
HE-PI-1450 | Final Issue for Design/ Construction-TBE for Piping Special Items | 5 | 5 | 2024-10-07 | 2024-10-11 | 2024-11-11 | 2024-11-15 | 91
TBE for Ball valves/ Plug Valves |  | 189 | 5 | 2024-01-30 | 2024-08-02 | 30-Jan-24 A | 2024-11-01 | 248
HE-PI-1080 | Issue ICR- TBE for Ball valves/ Plug Valves | 18 | 0 | 2024-01-30 | 2024-02-23 | 30-Jan-24 A | 23-Feb-24 A
HE-PI-1090 | Receive Company Comments- TBE for Ball valves/ Plug Valves | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-PI-1100 | Re-Issue for Approval- TBE for Ball valves/ Plug Valves | 9 | 0 | 2024-03-10 | 2024-03-25 | 10-Mar-24 A | 25-Mar-24 A
HE-PI-1110 | Obtain Company Approval- TBE for Ball valves/ Plug Valves | 32 | 0 | 2024-03-26 | 2024-05-16 | 26-Mar-24 A | 16-May-24 A
HE-PI-1120 | Final Issue for Design/ Construction-TBE for Ball valves/ Plug Valves | 58 | 5 | 2024-07-29 | 2024-08-02 | 14-Aug-24 A | 2024-11-01 | 248
TBE for Check Valves |  | 115 | 0 | 2024-02-06 | 2024-08-02 | 06-Feb-24 A | 29-Jul-24 A
HE-PI-3730 | Issue ICR- TBE for Check Valves | 25 | 0 | 2024-02-06 | 2024-03-12 | 06-Feb-24 A | 12-Mar-24 A
HE-PI-3740 | Receive Company Comments- TBE for Check Valves | 9 | 0 | 2024-03-13 | 2024-03-28 | 13-Mar-24 A | 28-Mar-24 A
HE-PI-3750 | Re-Issue for Approval- TBE for Check Valves | 9 | 0 | 2024-03-31 | 2024-04-18 | 31-Mar-24 A | 18-Apr-24 A
HE-PI-3760 | Obtain Company Approval- TBE for Check Valves | 13 | 0 | 2024-04-28 | 2024-05-16 | 28-Apr-24 A | 16-May-24 A
HE-PI-3770 | Final Issue for Design/ Construction-TBE for Check Valves | 8 | 0 | 2024-07-29 | 2024-08-02 | 18-Jul-24 A | 29-Jul-24 A
Piping Stress Analysis & Report |  | 173 | 15 | 2024-03-06 | 2024-08-16 | 06-Mar-24 A | 2024-11-15 | 48
HE-PI-1140 | Issue ICR-Piping Stress Analysis & Report | 9 | 0 | 2024-03-06 | 2024-03-19 | 06-Mar-24 A | 19-Mar-24 A
HE-PI-1150 | Receive Company Comments-Piping Stress Analysis & Report | 6 | 0 | 2024-03-20 | 2024-03-29 | 20-Mar-24 A | 29-Mar-24 A
HE-PI-1160 | Re-Issue for Approval-Piping Stress Analysis & Report | 37 | 0 | 2024-04-18 | 2024-06-10 | 18-Apr-24 A | 10-Jun-24 A
HE-PI-1170 | Obtain Company Approval-Piping Stress Analysis & Report | 4 | 0 | 2024-06-11 | 2024-06-18 | 11-Jun-24 A | 18-Jun-24 A
HE-PI-1180 | Final Issue for Design/ Construction-Piping Stress Analysis & Report | 106 | 15 | 2024-06-19 | 2024-08-16 | 19-Jun-24 A | 2024-11-15 | 48
Piping Isometrics |  | 45 | 5 | 2024-08-12 | 2024-11-29 | 02-Sep-24 A | 2024-11-01 | 6
HE-PI-1200 | Issue ICR-Piping Isometrics | 29 | 0 | 2024-08-12 | 2024-08-23 | 02-Sep-24 A | 10-Oct-24 A
HE-PI-1210 | Receive Company Comments-Piping Isometrics | 21 | 0 | 2024-08-26 | 2024-09-06 | 16-Sep-24 A | 14-Oct-24 A
HE-PI-1220 | Re-Issue for Approval-Piping Isometrics | 21 | 0 | 2024-11-11 | 2024-11-15 | 21-Sep-24 A | 21-Oct-24 A
HE-PI-1230 | Obtain Company Approval-Piping Isometrics | 19 | 0 | 2024-11-18 | 2024-11-22 | 30-Sep-24 A | 24-Oct-24 A
HE-PI-1240 | Final Issue for Design/ Construction-Piping Isometrics | 6 | 5 | 2024-11-25 | 2024-11-29 | 25-Oct-24 A | 2024-11-01 | 6
Piping MTO |  | 73 | 0 | 2024-06-29 | 2024-08-23 | 29-Jun-24 A | 10-Oct-24 A
HE-PI-1260 | Piping MTO - 1st | 6 | 0 | 2024-06-29 | 2024-07-09 | 29-Jun-24 A | 09-Jul-24 A
HE-PI-1280 | Piping MTO - 2nd | 17 | 0 | 2024-07-29 | 2024-08-09 | 21-Aug-24 A | 12-Sep-24 A
HE-PI-1300 | Piping MTO - Final | 8 | 0 | 2024-08-12 | 2024-08-23 | 01-Oct-24 A | 10-Oct-24 A
Mechanical |  | 255 | 0 | 2023-08-06 | 2024-08-02 | 06-Aug-23 A | 13-Aug-24 A
Design Basis |  | 47 | 0 | 2023-08-06 | 2023-10-11 | 06-Aug-23 A | 11-Oct-23 A
HE-ME-270 | Issue ICR- Mechanical Design Basis | 10 | 0 | 2023-08-06 | 2023-08-21 | 06-Aug-23 A | 21-Aug-23 A
HE-ME-230 | Receive Company Comments- Mechanical Design Basis | 7 | 0 | 2023-08-22 | 2023-08-31 | 22-Aug-23 A | 31-Aug-23 A
HE-ME-240 | Re-Issue for Approval- Mechanical Design Basis | 10 | 0 | 2023-09-11 | 2023-09-25 | 11-Sep-23 A | 25-Sep-23 A
HE-ME-250 | Obtain Company Approval- Mechanical Design Basis | 6 | 0 | 2023-09-26 | 2023-10-04 | 26-Sep-23 A | 04-Oct-23 A
HE-ME-260 | Final Issue for Design/ Construction- Mechanical Design Basis | 4 | 0 | 2023-10-05 | 2023-10-11 | 05-Oct-23 A | 11-Oct-23 A
Addendum to DGS (Pressure Vessels) |  | 40 | 0 | 2023-09-01 | 2023-10-27 | 01-Sep-23 A | 27-Oct-23 A
HE-ME-0010 | Issue ICR- Addendum to DGS | 16 | 0 | 2023-09-01 | 2023-09-23 | 01-Sep-23 A | 23-Sep-23 A
HE-ME-0020 | Receive Company Comments- Addendum to DGS | 4 | 0 | 2023-10-01 | 2023-10-06 | 01-Oct-23 A | 06-Oct-23 A
HE-ME-0030 | Re-Issue for Approval- Addendum to DGS | 5 | 0 | 2023-10-07 | 2023-10-14 | 07-Oct-23 A | 14-Oct-23 A
HE-ME-0040 | Obtain Company Approval- Addendum to DGS | 5 | 0 | 2023-10-15 | 2023-10-21 | 15-Oct-23 A | 21-Oct-23 A
HE-ME-0050 | Final Issue for Design/ Construction- Addendum to DGS | 4 | 0 | 2023-10-22 | 2023-10-27 | 22-Oct-23 A | 27-Oct-23 A
Addendum to DGS (Launche/Receiver) |  | 24 | 0 | 2023-09-23 | 2023-10-27 | 23-Sep-23 A | 27-Oct-23 A
HE-ME-620 | Issue ICR- Addendum to DGS | 0 | 0 | 2023-09-23 | 2023-09-24 | 23-Sep-23 A | 24-Sep-23 A
HE-ME-580 | Receive Company Comments- Addendum to DGS | 2 | 0 | 2023-09-24 | 2023-09-27 | 24-Sep-23 A | 27-Sep-23 A
HE-ME-590 | Re-Issue for Approval- Addendum to DGS | 4 | 0 | 2023-09-28 | 2023-10-04 | 28-Sep-23 A | 04-Oct-23 A
HE-ME-600 | Obtain Company Approval- Addendum to DGS | 6 | 0 | 2023-10-05 | 2023-10-13 | 05-Oct-23 A | 13-Oct-23 A
HE-ME-610 | Final Issue for Design/ Construction- Addendum to DGS | 9 | 0 | 2023-10-14 | 2023-10-27 | 14-Oct-23 A | 27-Oct-23 A
Pig Launcher/Receiver Length Report |  | 62 | 0 | 2023-10-10 | 2024-01-07 | 10-Oct-23 A | 07-Jan-24 A
HE-ME-670 | Issue ICR- Pig Launcher/Receiver Length Report | 11 | 0 | 2023-10-10 | 2023-10-25 | 10-Oct-23 A | 25-Oct-23 A
HE-ME-630 | Receive Company Comments- Pig Launcher/Receiver Length Report | 4 | 0 | 2023-11-19 | 2023-11-24 | 19-Nov-23 A | 24-Nov-23 A
HE-ME-640 | Re-Issue for Approval- Pig Launcher/Receiver Length Report | 6 | 0 | 2023-11-21 | 2023-11-29 | 21-Nov-23 A | 29-Nov-23 A
HE-ME-650 | Obtain Company Approval- Pig Launcher/Receiver Length Report | 7 | 0 | 2023-11-30 | 2023-12-12 | 30-Nov-23 A | 12-Dec-23 A
HE-ME-660 | Final Issue for Design/ Construction- Pig Launcher/Receiver Length Report | 5 | 0 | 2023-12-29 | 2024-01-07 | 29-Dec-23 A | 07-Jan-24 A
Datasheets |  | 217 | 0 | 2023-09-02 | 2024-07-29 | 02-Sep-23 A | 19-Jul-24 A
Datasheet for Sals Gas CRS Filters |  | 100 | 0 | 2023-09-02 | 2024-01-24 | 02-Sep-23 A | 24-Jan-24 A
HE-ME-0070 | Issue ICR-Datasheet for Sales Gas CRS Filters | 7 | 0 | 2023-09-02 | 2023-09-13 | 02-Sep-23 A | 13-Sep-23 A
HE-ME-0080 | Receive Company Comments-Datasheet for Sales Gas CRS Filters | 12 | 0 | 2023-09-14 | 2023-10-02 | 14-Sep-23 A | 02-Oct-23 A
HE-ME-0090 | Re-Issue for Approval-Datasheet for Sales Gas CRS Filters | 13 | 0 | 2023-10-03 | 2023-10-20 | 03-Oct-23 A | 20-Oct-23 A
HE-ME-0100 | Obtain Company Approval-Datasheet for Sales Gas CRS Filters | 5 | 0 | 2023-11-07 | 2023-11-14 | 07-Nov-23 A | 14-Nov-23 A
HE-ME-0110 | Final Issue for Design/ Construction-Datasheet for Sales Gas CRS Filters | 10 | 0 | 2024-01-10 | 2024-01-24 | 10-Jan-24 A | 24-Jan-24 A
Datasheet for PIG RECEIVER (839-V-101) 52" |  | 205 | 0 | 2023-09-14 | 2024-07-29 | 14-Sep-23 A | 15-Jul-24 A
HE-ME-310 | Issue ICR-Datasheet for PIG RECEIVER (839-V-101) | 9 | 0 | 2023-09-14 | 2023-09-27 | 14-Sep-23 A | 27-Sep-23 A
HE-ME-320 | Receive Company Comments-Datasheet for PIG RECEIVER (839-V-101) | 5 | 0 | 2023-09-28 | 2023-10-05 | 28-Sep-23 A | 05-Oct-23 A
HE-ME-280 | Re-Issue for Approval-Datasheet for PIG RECEIVER (839-V-101) | 10 | 0 | 2023-10-06 | 2023-10-20 | 06-Oct-23 A | 20-Oct-23 A
HE-ME-290 | Obtain Company Approval-Datasheet for PIG RECEIVER (839-V-101) | 5 | 0 | 2023-11-07 | 2023-11-14 | 07-Nov-23 A | 14-Nov-23 A
HE-ME-300 | Final Issue for Design/ Construction-Datasheet for PIG RECEIVER (839-V-101) | 9 | 0 | 2024-07-29 | 2024-07-29 | 01-Jul-24 A | 15-Jul-24 A
Datasheet for PIG LAUNCHER (838-V-602) 52" |  | 209 | 0 | 2023-09-14 | 2024-07-29 | 14-Sep-23 A | 19-Jul-24 A
HE-ME-360 | Issue ICR-Datasheet for PIG LAUNCHER (838-V-602) | 9 | 0 | 2023-09-14 | 2023-09-27 | 14-Sep-23 A | 27-Sep-23 A
HE-ME-370 | Receive Company Comments-Datasheet for PIG LAUNCHER (838-V-602) | 5 | 0 | 2023-09-28 | 2023-10-05 | 28-Sep-23 A | 05-Oct-23 A
HE-ME-330 | Re-Issue for Approval-Datasheet for PIG LAUNCHER (838-V-602) | 10 | 0 | 2023-10-06 | 2023-10-20 | 06-Oct-23 A | 20-Oct-23 A
HE-ME-340 | Obtain Company Approval-Datasheet for PIG LAUNCHER (838-V-602) | 5 | 0 | 2023-11-07 | 2023-11-14 | 07-Nov-23 A | 14-Nov-23 A
HE-ME-350 | Final Issue for Design/ Construction-Datasheet for PIG LAUNCHER (838-V-602) | 5 | 0 | 2024-07-29 | 2024-07-29 | 12-Jul-24 A | 19-Jul-24 A
Datasheet for PIG RECEIVER (838-V-601) 56" |  | 209 | 0 | 2023-09-14 | 2024-07-29 | 14-Sep-23 A | 19-Jul-24 A
HE-ME-410 | Issue ICR-Datasheet for PIG RECEIVER (838-V-601) | 9 | 0 | 2023-09-14 | 2023-09-27 | 14-Sep-23 A | 27-Sep-23 A
HE-ME-420 | Receive Company Comments-Datasheet for PIG RECEIVER (838-V-601) | 5 | 0 | 2023-09-28 | 2023-10-05 | 28-Sep-23 A | 05-Oct-23 A
HE-ME-380 | Re-Issue for Approval-Datasheet for PIG RECEIVER (838-V-601) | 10 | 0 | 2023-10-06 | 2023-10-20 | 06-Oct-23 A | 20-Oct-23 A
HE-ME-390 | Obtain Company Approval-Datasheet for PIG RECEIVER (838-V-601) | 5 | 0 | 2023-11-07 | 2023-11-14 | 07-Nov-23 A | 14-Nov-23 A
HE-ME-400 | Final Issue for Design/ Construction-Datasheet for PIG RECEIVER (838-V-601) | 5 | 0 | 2024-07-29 | 2024-07-29 | 12-Jul-24 A | 19-Jul-24 A
Datasheet for PIG LAUNCHER (607-V-603) 56" |  | 205 | 0 | 2023-09-14 | 2024-07-29 | 14-Sep-23 A | 15-Jul-24 A
HE-ME-460 | Issue ICR-Datasheet for PIG LAUNCHER (607-V-603) | 9 | 0 | 2023-09-14 | 2023-09-27 | 14-Sep-23 A | 27-Sep-23 A
HE-ME-470 | Receive Company Comments-Datasheet for PIG LAUNCHER (607-V-603) | 5 | 0 | 2023-09-28 | 2023-10-05 | 28-Sep-23 A | 05-Oct-23 A
HE-ME-430 | Re-Issue for Approval-Datasheet for PIG LAUNCHER (607-V-603) | 10 | 0 | 2023-10-06 | 2023-10-20 | 06-Oct-23 A | 20-Oct-23 A
HE-ME-440 | Obtain Company Approval-Datasheet for PIG LAUNCHER (607-V-603) | 5 | 0 | 2023-11-07 | 2023-11-14 | 07-Nov-23 A | 14-Nov-23 A
HE-ME-450 | Final Issue for Design/ Construction-Datasheet for PIG LAUNCHER (607-V-603) | 9 | 0 | 2024-07-29 | 2024-07-29 | 01-Jul-24 A | 15-Jul-24 A
Material Requisitions |  | 119 | 0 | 2023-10-09 | 2024-03-28 | 09-Oct-23 A | 28-Mar-24 A
Material Requisitions Sals Gas CRS Filters |  | 119 | 0 | 2023-10-09 | 2024-03-28 | 09-Oct-23 A | 28-Mar-24 A
HE-ME-0130 | Issue ICR-Material Requisitions for Sales Gas CRS Filters | 8 | 0 | 2023-10-09 | 2023-10-19 | 09-Oct-23 A | 19-Oct-23 A
HE-ME-0140 | Receive Company Comments-Material Requisitions for Sales Gas CRS Filters | 8 | 0 | 2023-10-30 | 2023-11-09 | 30-Oct-23 A | 09-Nov-23 A
HE-ME-0150 | Re-Issue for Approval-Material Requisitions for Sales Gas CRS Filters | 6 | 0 | 2024-02-26 | 2024-03-05 | 26-Feb-24 A | 05-Mar-24 A
HE-ME-0160 | Obtain Company Approval-Material Requisitions for Sales Gas CRS Filters | 6 | 0 | 2024-03-06 | 2024-03-14 | 06-Mar-24 A | 14-Mar-24 A
HE-ME-0170 | Final Issue for Design/ Construction-Material Requisitions for Sales Gas CRS Filters | 8 | 0 | 2024-03-15 | 2024-03-28 | 15-Mar-24 A | 28-Mar-24 A
Material Requisitions Pig Launcher/Receiver |  | 108 | 0 | 2023-10-09 | 2024-03-09 | 09-Oct-23 A | 09-Mar-24 A
HE-ME-480 | Issue ICR-Material Requisitions for Pig Launcher/Receiver | 8 | 0 | 2023-10-09 | 2023-10-19 | 09-Oct-23 A | 19-Oct-23 A
HE-ME-490 | Receive Company Comments-Material Requisitions for Pig Launcher/Receiver | 6 | 0 | 2023-11-07 | 2023-11-15 | 07-Nov-23 A | 15-Nov-23 A
HE-ME-500 | Re-Issue for Approval-Material Requisitions for Pig Launcher/Receiver | 2 | 0 | 2023-12-29 | 2024-01-03 | 29-Dec-23 A | 03-Jan-24 A
HE-ME-510 | Obtain Company Approval-Material Requisitions for Pig Launcher/Receiver | 3 | 0 | 2024-01-04 | 2024-01-09 | 04-Jan-24 A | 09-Jan-24 A
HE-ME-520 | Final Issue for Design/ Construction-Material Requisitions for Pig Launcher/Receiver | 43 | 0 | 2024-01-10 | 2024-03-09 | 10-Jan-24 A | 09-Mar-24 A
TBE |  | 172 | 0 | 2023-11-30 | 2024-08-02 | 30-Nov-23 A | 13-Aug-24 A
TBE for Sals Gas CRS Filters |  | 64 | 0 | 2023-12-04 | 2024-03-04 | 04-Dec-23 A | 04-Mar-24 A
HE-ME-0190 | Issue ICR-TBEs for Sales Gas CRS Filters | 4 | 0 | 2023-12-04 | 2023-12-08 | 04-Dec-23 A | 08-Dec-23 A
HE-ME-0200 | Receive Company Comments-TBEs for Sales Gas CRS Filters | 6 | 0 | 2023-12-29 | 2024-01-09 | 29-Dec-23 A | 09-Jan-24 A
HE-ME-0210 | Re-Issue for Approval-TBEs for Sales Gas CRS Filters | 13 | 0 | 2024-01-10 | 2024-01-29 | 10-Jan-24 A | 29-Jan-24 A
HE-ME-0220 | Obtain Company Approval-TBEs for Sales Gas CRS Filters | 8 | 0 | 2024-01-31 | 2024-02-12 | 31-Jan-24 A | 12-Feb-24 A
HE-ME-0230 | Final Issue for Design/ Construction-TBEs for Sales Gas CRS Filters | 14 | 0 | 2024-02-13 | 2024-03-04 | 13-Feb-24 A | 04-Mar-24 A
TBE for Pig Launcher/Receiver |  | 172 | 0 | 2023-11-30 | 2024-08-02 | 30-Nov-23 A | 13-Aug-24 A
HE-ME-530 | Issue ICR-TBEs for Pig Launcher/Receiver | 6 | 0 | 2023-11-30 | 2023-12-11 | 30-Nov-23 A | 11-Dec-23 A
HE-ME-540 | Receive Company Comments-TBEs for Pig Launcher/Receiver | 0 | 0 | 2023-12-29 | 2023-12-29 | 29-Dec-23 A | 29-Dec-23 A
HE-ME-550 | Re-Issue for Approval-TBEs for Pig Launcher/Receiver | 3 | 0 | 2023-12-29 | 2024-01-04 | 29-Dec-23 A | 04-Jan-24 A
HE-ME-560 | Obtain Company Approval-TBEs for Pig Launcher/Receiver | 7 | 0 | 2024-01-05 | 2024-01-16 | 05-Jan-24 A | 16-Jan-24 A
HE-ME-570 | Final Issue for Design/ Construction-TBEs for Pig Launcher/Receiver | 9 | 0 | 2024-07-29 | 2024-08-02 | 01-Aug-24 A | 13-Aug-24 A
Civil / Structural |  | 343 | 35 | 2023-08-07 | 2024-10-18 | 07-Aug-23 A | 2024-12-17 | 84
Civil / Structural Design Basis |  | 106 | 0 | 2023-08-23 | 2024-01-22 | 23-Aug-23 A | 22-Jan-24 A
HE-CS-1560 | Issued for Review - Civil / Structural Design Basis | 5 | 0 | 2023-08-23 | 2023-08-30 | 23-Aug-23 A | 30-Aug-23 A
HE-CS-1570 | Review Company Comments - Civil / Structural Design Basis | 1 | 0 | 2023-08-31 | 2023-09-01 | 31-Aug-23 A | 01-Sep-23 A
HE-CS-1580 | Re-Issue for Approval - Civil / Structural Design Basis | 4 | 0 | 2023-11-01 | 2023-11-07 | 01-Nov-23 A | 07-Nov-23 A
HE-CS-1590 | Obtain Company Approval - Civil / Structural Design Basis | 5 | 0 | 2023-11-08 | 2023-11-15 | 08-Nov-23 A | 15-Nov-23 A
HE-CS-1600 | Final Issue for Design/ Construction-Civil / Structural Design Basis | 42 | 0 | 2023-11-21 | 2024-01-22 | 21-Nov-23 A | 22-Jan-24 A
Addendum to DGs |  | 99 | 0 | 2023-08-07 | 2023-12-25 | 07-Aug-23 A | 25-Dec-23 A
HE-CS-0010 | Issued for Review - Addendum to DGs | 44 | 0 | 2023-08-07 | 2023-10-06 | 07-Aug-23 A | 06-Oct-23 A
HE-CS-0020 | Review Company Comments - Addendum to DGs | 9 | 0 | 2023-10-09 | 2023-10-20 | 09-Oct-23 A | 20-Oct-23 A
HE-CS-0030 | Re-Issue for Approval - Addendum to DGs | 14 | 0 | 2023-10-23 | 2023-11-10 | 23-Oct-23 A | 10-Nov-23 A
HE-CS-0040 | Obtain Company Approval - Addendum to DGs | 9 | 0 | 2023-11-13 | 2023-11-24 | 13-Nov-23 A | 24-Nov-23 A
HE-CS-0050 | Final Issue for Design/ Construction-Addendum to DGs | 19 | 0 | 2023-11-27 | 2023-12-25 | 27-Nov-23 A | 25-Dec-23 A
Standard drawings for Anchor bolt |  | 148 | 10 | 2024-04-06 | 2024-09-20 | 06-Apr-24 A | 2024-11-08 | 29
HE-CS-0070 | Issued for Review - Standard drawings for Anchor bolt | 7 | 0 | 2024-04-06 | 2024-08-02 | 06-Apr-24 A | 19-Apr-24 A
HE-CS-0080 | Review Company Comments - Standard drawings for Anchor bolt | 11 | 0 | 2024-08-05 | 2024-08-16 | 22-Apr-24 A | 06-May-24 A
HE-CS-0090 | Re-Issue for Approval - Standard drawings for Anchor bolt | 19 | 0 | 2024-08-19 | 2024-08-23 | 07-May-24 A | 31-May-24 A
HE-CS-0100 | Obtain Company Approval - Standard drawings for Anchor bolt | 12 | 0 | 2024-08-26 | 2024-09-06 | 21-Jun-24 A | 09-Jul-24 A
HE-CS-0110 | Final Issue for Design/ Construction-Standard drawings for Anchor bolt | 56 | 10 | 2024-09-09 | 2024-09-20 | 23-Aug-24 A | 2024-11-08 | 29
Anchor Block Calculation |  | 157 | 15 | 2024-03-30 | 2024-09-20 | 30-Mar-24 A | 2024-11-15 | 28
HE-CS-1710 | Issued for Review - Anchor Block Calculation | 12 | 0 | 2024-03-30 | 2024-04-23 | 30-Mar-24 A | 23-Apr-24 A
HE-CS-1720 | Review Company Comments - Anchor Block Calculation | 9 | 0 | 2024-04-23 | 2024-05-06 | 23-Apr-24 A | 06-May-24 A
HE-CS-1730 | Re-Issue for Approval - Anchor Block Calculation | 13 | 0 | 2024-06-14 | 2024-08-16 | 14-Jun-24 A | 05-Jul-24 A
HE-CS-1740 | Obtain Company Approval - Anchor Block Calculation | 61 | 0 | 2024-08-19 | 2024-08-30 | 15-Jul-24 A | 07-Oct-24 A
HE-CS-1750 | Final Issue for Design/ Construction-Anchor Block Calculation | 29 | 15 | 2024-09-02 | 2024-09-20 | 08-Oct-24 A | 2024-11-15 | 28
Anchor Block Detailed Drawings |  | 157 | 5 | 2024-03-30 | 2024-09-27 | 30-Mar-24 A | 2024-11-15 | 28
HE-CS-1760 | Issued for Review - Anchor Block Detail Drawings | 12 | 0 | 2024-03-30 | 2024-04-23 | 30-Mar-24 A | 23-Apr-24 A
HE-CS-1770 | Review Company Comments - Anchor Block Detail Drawings | 42 | 0 | 2024-05-06 | 2024-08-09 | 06-May-24 A | 05-Jul-24 A
HE-CS-1780 | Re-Issue for Approval - Anchor Block Detail Drawings | 34 | 0 | 2024-08-12 | 2024-08-23 | 08-Jul-24 A | 23-Aug-24 A
HE-CS-1790 | Obtain Company Approval - Anchor Block Detail Drawings | 11 | 0 | 2024-08-26 | 2024-09-06 | 02-Sep-24 A | 16-Sep-24 A
HE-CS-1800 | Final Issue for Design/ Construction - Anchor Block Detail Drawings | 44 | 5 | 2024-09-23 | 2024-09-27 | 17-Sep-24 A | 2024-11-15 | 28
Typical trench detail drawing |  | 34 | 0 | 2023-10-27 | 2023-12-15 | 27-Oct-23 A | 15-Dec-23 A
HE-CS-0130 | Issued for Review - Typical trench detail drawing | 10 | 0 | 2023-10-27 | 2023-11-10 | 27-Oct-23 A | 10-Nov-23 A
HE-CS-0140 | Review Company Comments - Typical trench detail drawing | 14 | 0 | 2023-11-13 | 2023-12-01 | 13-Nov-23 A | 01-Dec-23 A
HE-CS-0150 | Re-Issue for Approval - Typical trench detail drawing | 0 | 0 | 2023-12-01 | 2023-12-01 | 01-Dec-23 A | 01-Dec-23 A
HE-CS-0160 | Obtain Company Approval - Typical trench detail drawing | 0 | 0 | 2023-12-01 | 2023-12-01 | 01-Dec-23 A | 01-Dec-23 A
HE-CS-0170 | Final Issue for Design/ Construction-Typical trench detail drawing | 9 | 0 | 2023-12-04 | 2023-12-15 | 04-Dec-23 A | 15-Dec-23 A
Typical duct bank detail drawing |  | 29 | 0 | 2023-08-23 | 2023-10-03 | 23-Aug-23 A | 03-Oct-23 A
HE-CS-0190 | Issued for Review - Typical duct bank detail drawing | 6 | 0 | 2023-08-23 | 2023-08-31 | 23-Aug-23 A | 31-Aug-23 A
HE-CS-0200 | Review Company Comments - Typical duct bank detail drawing | 4 | 0 | 2023-09-01 | 2023-09-07 | 01-Sep-23 A | 07-Sep-23 A
HE-CS-0210 | Re-Issue for Approval - Typical duct bank detail drawing | 5 | 0 | 2023-09-08 | 2023-09-15 | 08-Sep-23 A | 15-Sep-23 A
HE-CS-0220 | Obtain Company Approval - Typical duct bank detail drawing | 6 | 0 | 2023-09-16 | 2023-09-26 | 16-Sep-23 A | 26-Sep-23 A
HE-CS-0230 | Final Issue for Design/ Construction-Typical duct bank detail drawing | 4 | 0 | 2023-09-27 | 2023-10-03 | 27-Sep-23 A | 03-Oct-23 A
Typical Road and paving detail drawing |  | 26 | 0 | 2023-09-12 | 2023-10-18 | 12-Sep-23 A | 18-Oct-23 A
HE-CS-0250 | Issued for Review - Typical Road and paving detail drawing | 10 | 0 | 2023-09-12 | 2023-09-26 | 12-Sep-23 A | 26-Sep-23 A
HE-CS-0260 | Review Company Comments - Typical Road and paving detail drawing | 6 | 0 | 2023-09-27 | 2023-10-05 | 27-Sep-23 A | 05-Oct-23 A
HE-CS-0270 | Re-Issue for Approval - Typical Road and paving detail drawing | 2 | 0 | 2023-10-06 | 2023-10-10 | 06-Oct-23 A | 10-Oct-23 A
HE-CS-0280 | Obtain Company Approval - Typical Road and paving detail drawing | 3 | 0 | 2023-10-11 | 2023-10-15 | 11-Oct-23 A | 15-Oct-23 A
HE-CS-0290 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | 2 | 0 | 2023-10-16 | 2023-10-18 | 16-Oct-23 A | 18-Oct-23 A
Typical Fence and gate detail drawing |  | 26 | 0 | 2023-08-24 | 2023-09-29 | 24-Aug-23 A | 29-Sep-23 A
HE-CS-0310 | Issued for Review - Typical Fence and gate detail drawing | 9 | 0 | 2023-08-24 | 2023-09-06 | 24-Aug-23 A | 06-Sep-23 A
HE-CS-0320 | Review Company Comments - Typical Fence and gate detail drawing | 2 | 0 | 2023-09-07 | 2023-09-11 | 07-Sep-23 A | 11-Sep-23 A
HE-CS-0330 | Re-Issue for Approval - Typical Fence and gate detail drawing | 8 | 0 | 2023-09-12 | 2023-09-22 | 12-Sep-23 A | 22-Sep-23 A
HE-CS-0340 | Obtain Company Approval - Typical Fence and gate detail drawing | 3 | 0 | 2023-09-22 | 2023-09-27 | 22-Sep-23 A | 27-Sep-23 A
HE-CS-0350 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | 1 | 0 | 2023-09-28 | 2023-09-29 | 28-Sep-23 A | 29-Sep-23 A
Typical details of protection slab to protect existing UG pipe at road crossing |  | 210 | 0 | 2023-12-11 | 2024-08-02 | 11-Dec-23 A | 14-Oct-24 A
HE-CS-0370 | Issued for Review - Typical details of protection slab to protect existing UG pipe at road crossing | 67 | 0 | 2023-12-11 | 2024-03-15 | 11-Dec-23 A | 15-Mar-24 A
HE-CS-0380 | Review Company Comments - Typical details of protection slab to protect existing UG pipe at road crossing | 8 | 0 | 2024-03-16 | 2024-03-29 | 16-Mar-24 A | 29-Mar-24 A
HE-CS-0390 | Re-Issue for Approval - Typical details of protection slab to protect existing UG pipe at road crossing | 3 | 0 | 2024-03-30 | 2024-04-05 | 30-Mar-24 A | 05-Apr-24 A
HE-CS-0400 | Obtain Company Approval - Typical details of protection slab to protect existing UG pipe at road crossing | 7 | 0 | 2024-04-06 | 2024-04-20 | 06-Apr-24 A | 20-Apr-24 A
HE-CS-0410 | Final Issue for Design/ Construction-Typical details of protection slab to protect existing UG pipe at road crossing | 6 | 0 | 2024-07-29 | 2024-08-02 | 07-Oct-24 A | 14-Oct-24 A
Site grading, road, drainage and fence layout |  | 219 | 5 | 2023-12-18 | 2024-08-16 | 18-Dec-23 A | 2024-11-01 | 4
HE-CS-0430 | Issued for Review - Site grading, road, drainage and fence layout | 53 | 0 | 2023-12-18 | 2024-03-01 | 18-Dec-23 A | 01-Mar-24 A
HE-CS-0440 | Review Company Comments - Site grading, road, drainage and fence layout | 7 | 0 | 2024-07-18 | 2024-07-26 | 18-Jul-24 A | 26-Jul-24 A
HE-CS-0450 | Re-Issue for Approval - Site grading, road, drainage and fence layout | 6 | 0 | 2024-07-29 | 2024-08-02 | 02-Sep-24 A | 09-Sep-24 A
HE-CS-0460 | Obtain Company Approval - Site grading, road, drainage and fence layout | 8 | 0 | 2024-08-05 | 2024-08-09 | 10-Sep-24 A | 19-Sep-24 A
HE-CS-0470 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | 8 | 5 | 2024-08-12 | 2024-08-16 | 23-Oct-24 A | 2024-11-01 | 4
Civil UG layout |  | 155 | 0 | 2024-03-02 | 2024-09-06 | 02-Mar-24 A | 18-Oct-24 A
HE-CS-0490 | Issued for Review - Civil UG layout | 17 | 0 | 2024-03-02 | 2024-03-29 | 02-Mar-24 A | 29-Mar-24 A
HE-CS-0500 | Review Company Comments - Civil UG layout | 12 | 0 | 2024-03-30 | 2024-04-23 | 30-Mar-24 A | 23-Apr-24 A
HE-CS-0510 | Re-Issue for Approval - Civil UG layout | 4 | 0 | 2024-07-29 | 2024-08-09 | 01-Oct-24 A | 04-Oct-24 A
HE-CS-0520 | Obtain Company Approval - Civil UG layout | 5 | 0 | 2024-08-12 | 2024-08-23 | 05-Oct-24 A | 11-Oct-24 A
HE-CS-0530 | Final Issue for Design/ Construction-Civil UG layout | 5 | 0 | 2024-08-26 | 2024-09-06 | 12-Oct-24 A | 18-Oct-24 A
Civil GA Darawings |  | 171 | 10 | 2024-03-01 | 2024-09-06 | 01-Mar-24 A | 2024-11-08 | 42
HE-CS-1640 | Issued for Review - Civil GA Drawings | 143 | 0 | 2024-03-01 | 2024-08-02 | 01-Mar-24 A | 01-Oct-24 A
HE-CS-1650 | Review Company Comments - Civil GA Drawings | 75 | 0 | 2024-06-15 | 2024-08-02 | 15-Jun-24 A | 03-Oct-24 A
HE-CS-1610 | Re-Issue for Approval - Civil GA Drawings | 31 | 0 | 2024-08-05 | 2024-08-09 | 23-Aug-24 A | 05-Oct-24 A
HE-CS-1620 | Obtain Company Approval - Civil GA Drawings | 6 | 0 | 2024-08-12 | 2024-08-23 | 07-Oct-24 A | 14-Oct-24 A
HE-CS-1630 | Final Issue for Design/ Construction-Civil GA Drawings | 10 | 10 | 2024-08-26 | 2024-09-06 | 2024-10-28 | 2024-11-08 | 42
Calculation for Pig launcher and receiver foundations |  | 147 | 5 | 2024-03-31 | 2024-08-30 | 31-Mar-24 A | 2024-11-01 | 17
HE-CS-0550 | Issued for Review - Calculation for Pig launcher and receiver foundations | 9 | 0 | 2024-03-31 | 2024-04-18 | 31-Mar-24 A | 18-Apr-24 A
HE-CS-0560 | Review Company Comments - Calculation for Pig launcher and receiver foundations | 4 | 0 | 2024-04-19 | 2024-04-25 | 19-Apr-24 A | 25-Apr-24 A
HE-CS-0570 | Re-Issue for Approval - Calculation for Pig launcher and receiver foundations | 11 | 0 | 2024-07-29 | 2024-08-09 | 02-Sep-24 A | 16-Sep-24 A
HE-CS-0580 | Obtain Company Approval - Calculation for Pig launcher and receiver foundations | 11 | 0 | 2024-08-12 | 2024-08-23 | 16-Sep-24 A | 30-Sep-24 A
HE-CS-0590 | Final Issue for Design/ Construction-Calculation for Pig launcher and receiver foundations | 25 | 5 | 2024-08-26 | 2024-08-30 | 30-Sep-24 A | 2024-11-01 | 17
Design Calculation for Typical Skid Foundations |  | 135 | 10 | 2024-04-30 | 2024-08-30 | 30-Apr-24 A | 2024-11-08 | 19
HE-CS-0670 | Issued for Review - Design Cal. for Typical Skid Foundations | 1 | 0 | 2024-04-30 | 2024-05-01 | 30-Apr-24 A | 01-May-24 A
HE-CS-0680 | Review Company Comments - Design Cal. for Typical Skid Foundations | 12 | 0 | 2024-05-02 | 2024-05-18 | 02-May-24 A | 18-May-24 A
HE-CS-0690 | Re-Issue for Approval - Design Cal. for Typical Skid Foundations | 6 | 0 | 2024-07-29 | 2024-08-02 | 02-Sep-24 A | 09-Sep-24 A
HE-CS-0700 | Obtain Company Approval - Design Cal. for Typical Skid Foundations | 13 | 0 | 2024-08-05 | 2024-08-16 | 10-Sep-24 A | 26-Sep-24 A
HE-CS-0710 | Final Issue for Design/ Construction-Design Calculation for Typical Skid Foundations | 10 | 10 | 2024-08-19 | 2024-08-30 | 2024-10-28 | 2024-11-08 | 19
Design Calculation for Typical Lighting Pole Foundations |  | 208 | 30 | 2024-02-07 | 2024-09-20 | 07-Feb-24 A | 2024-12-10 | 9
HE-CS-2090 | Issued for Review - Design Cal. for Typical Lighting Pole Foundations | 30 | 0 | 2024-02-07 | 2024-03-21 | 07-Feb-24 A | 21-Mar-24 A
HE-CS-2100 | Review Company Comments - Design Cal. for Typical Lighting Pole Foundations | 8 | 0 | 2024-07-29 | 2024-08-09 | 21-Mar-24 A | 02-Apr-24 A
HE-CS-2060 | Re-Issue for Approval - Design Cal. for Typical Lighting Pole Foundations | 10 | 10 | 2024-08-12 | 2024-08-23 | 2024-10-28 | 2024-11-08 | 9
HE-CS-2070 | Obtain Company Approval - Design Cal. for Typical Lighting Pole Foundations | 10 | 10 | 2024-08-26 | 2024-09-06 | 2024-11-11 | 2024-11-22 | 9
HE-CS-2080 | Final Issue for Design/ Construction-Design Calculation for Typical Lighting Pole Foundations | 10 | 10 | 2024-09-09 | 2024-09-20 | 2024-11-25 | 2024-12-10 | 9
Design Calculation for Jib crane Foundation |  | 141 | 10 | 2024-04-10 | 2024-09-20 | 22-Apr-24 A | 2024-11-08 | 58
HE-CS-1990 | Issued for Review - Design Cal. for Jib Crane Foundations | 1 | 0 | 2024-04-10 | 2024-04-23 | 22-Apr-24 A | 23-Apr-24 A
HE-CS-2000 | Review Company Comments - Design Cal. for Jib Crane Foundations | 10 | 0 | 2024-05-06 | 2024-08-09 | 23-Apr-24 A | 06-May-24 A
HE-CS-1960 | Re-Issue for Approval - Design Cal. for Jib Crane Foundations | 5 | 0 | 2024-08-12 | 2024-08-23 | 30-Sep-24 A | 04-Oct-24 A
HE-CS-1970 | Obtain Company Approval - Design Cal. for Jib Crane Foundations | 14 | 0 | 2024-08-26 | 2024-09-06 | 04-Oct-24 A | 23-Oct-24 A
HE-CS-1980 | Final Issue for Design/ Construction-Design Calculation for Jib Crane Foundations | 10 | 10 | 2024-09-09 | 2024-09-20 | 2024-10-28 | 2024-11-08 | 58
Design Calculation for Filter Package Foundation |  | 171 | 6 | 2024-02-24 | 2024-09-09 | 24-Feb-24 A | 2024-11-04 | 33
HE-CS-2040 | Issued for Review - Design Cal. for Filter Package | 13 | 0 | 2024-02-24 | 2024-03-15 | 24-Feb-24 A | 15-Mar-24 A
HE-CS-2050 | Review Company Comments - Design Cal. for Filter Package | 8 | 0 | 2024-03-28 | 2024-08-09 | 16-Mar-24 A | 28-Mar-24 A
HE-CS-2010 | Re-Issue for Approval - Design Cal. for Filter Package | 6 | 0 | 2024-08-12 | 2024-08-16 | 09-Sep-24 A | 16-Sep-24 A
HE-CS-2020 | Obtain Company Approval - Design Cal. for Filter Package | 10 | 0 | 2024-08-19 | 2024-08-30 | 17-Sep-24 A | 30-Sep-24 A
HE-CS-2030 | Final Issue for Design/ Construction-Design Calculation for Filter Package | 25 | 6 | 2024-09-02 | 2024-09-09 | 01-Oct-24 A | 2024-11-04 | 33
Pressure Reduction Skid & Leak Detection System Foundation |  | 151 | 5 | 2024-04-01 | 2024-09-06 | 01-Apr-24 A | 2024-11-08 | 29
HE-CS-0730 | Issued for Review - Pressure Reduction Skid and Leak Detection Drawings | 4 | 0 | 2024-04-01 | 2024-04-11 | 01-Apr-24 A | 11-Apr-24 A
HE-CS-0740 | Review Company Comments - Pressure Reduction Skid and Leak Detection Drawings | 11 | 0 | 2024-07-29 | 2024-08-09 | 09-Sep-24 A | 23-Sep-24 A
HE-CS-0750 | Re-Issue for Approval - Pressure Reduction Skid and Leak Detection Drawings | 5 | 0 | 2024-08-12 | 2024-08-16 | 24-Sep-24 A | 30-Sep-24 A
HE-CS-0760 | Obtain Company Approval - Pressure Reduction Skid and Leak Detection Drawings | 6 | 0 | 2024-08-19 | 2024-08-30 | 30-Sep-24 A | 07-Oct-24 A
HE-CS-0770 | Final Issue for Design/ Construction - Pressure Reduction Skid and Leak Detection Drawings | 24 | 5 | 2024-09-02 | 2024-09-06 | 08-Oct-24 A | 2024-11-08 | 29
Foundation for Launcher & Receivers |  | 152 | 5 | 2024-03-31 | 2024-09-06 | 31-Mar-24 A | 2024-11-08 | 17
HE-CS-0610 | Issued for Review - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | 14 | 0 | 2024-03-31 | 2024-04-25 | 31-Mar-24 A | 25-Apr-24 A
HE-CS-0620 | Review Company Comments - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | 5 | 0 | 2024-07-29 | 2024-08-09 | 26-Apr-24 A | 02-May-24 A
HE-CS-0630 | Re-Issue for Approval - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | 6 | 0 | 2024-08-12 | 2024-08-16 | 02-Sep-24 A | 09-Sep-24 A
HE-CS-0640 | Obtain Company Approval - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | 5 | 0 | 2024-08-19 | 2024-08-30 | 10-Sep-24 A | 16-Sep-24 A
HE-CS-0650 | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | 5 | 5 | 2024-09-02 | 2024-09-06 | 2024-11-04 | 2024-11-08 | 17
Gas Metering Skid Foundation Drawings |  | 162 | 10 | 2024-03-31 | 2024-09-20 | 31-Mar-24 A | 2024-11-22 | 19
HE-CS-0790 | Issued for Review - Gas metering skid foundation drawings | 14 | 0 | 2024-03-31 | 2024-04-25 | 31-Mar-24 A | 25-Apr-24 A
HE-CS-0800 | Review Company Comments - Gas metering skid foundation drawings | 15 | 0 | 2024-07-29 | 2024-08-09 | 26-Apr-24 A | 16-May-24 A
HE-CS-0810 | Re-Issue for Approval - Gas metering skid foundation drawings | 6 | 0 | 2024-08-12 | 2024-08-23 | 02-Sep-24 A | 09-Sep-24 A
HE-CS-0820 | Obtain Company Approval - Gas metering skid foundation drawings | 13 | 0 | 2024-08-26 | 2024-09-06 | 10-Sep-24 A | 26-Sep-24 A
HE-CS-0830 | Final Issue for Design/ Construction-Gas metering skid foundation drawings | 10 | 10 | 2024-09-09 | 2024-09-20 | 2024-11-11 | 2024-11-22 | 19
Solar panel Calculation & foundation details |  | 117 | 25 | 2024-08-12 | 2024-10-18 | 14-Jun-24 A | 2024-11-29 | 43
HE-CS-0850 | Issued for Review - Solar panel foundation details | 8 | 0 | 2024-08-12 | 2024-08-23 | 14-Jun-24 A | 28-Jun-24 A
HE-CS-0860 | Review Company Comments - Solar panel foundation details | 6 | 0 | 2024-08-26 | 2024-09-06 | 28-Jun-24 A | 05-Jul-24 A
HE-CS-0870 | Re-Issue for Approval - Solar panel foundation details | 9 | 0 | 2024-09-09 | 2024-09-20 | 14-Oct-24 A | 24-Oct-24 A
HE-CS-0880 | Obtain Company Approval - Solar panel foundation details | 11 | 10 | 2024-09-23 | 2024-10-04 | 25-Oct-24 A | 2024-11-08 | 48
HE-CS-0890 | Final Issue for Design/ Construction-Solar panel foundation details | 10 | 10 | 2024-10-07 | 2024-10-18 | 2024-11-18 | 2024-11-29 | 43
Filter Foundation GA and Details |  | 89 | 10 | 2024-07-29 | 2024-10-11 | 08-Jul-24 A | 2024-11-08 | 29
HE-CS-0910 | Issued for Review - Typical Spill Pit General Arrangement And RC (type) Details | 5 | 0 | 2024-07-29 | 2024-08-16 | 08-Jul-24 A | 15-Jul-24 A
HE-CS-0920 | Review Company Comments - Typical Spill Pit General Arrangement And RC (type) Details | 4 | 0 | 2024-08-19 | 2024-08-30 | 16-Jul-24 A | 19-Jul-24 A
HE-CS-0930 | Re-Issue for Approval - Typical Spill Pit General Arrangement And RC (type) Details | 5 | 0 | 2024-09-02 | 2024-09-13 | 16-Sep-24 A | 20-Sep-24 A
HE-CS-0940 | Obtain Company Approval - Typical Spill Pit General Arrangement And RC (type) Details | 14 | 0 | 2024-09-16 | 2024-09-27 | 23-Sep-24 A | 10-Oct-24 A
HE-CS-0950 | Final Issue for Design/ Construction-FILTER FOUNDATION GA AND DETAILS | 22 | 10 | 2024-09-30 | 2024-10-11 | 10-Oct-24 A | 2024-11-08 | 29
Typical Lighting Pole Foundation Details |  | 195 | 30 | 2024-02-26 | 2024-09-20 | 26-Feb-24 A | 2024-12-10 | 9
HE-CS-0970 | Issued for Review - Lighting pole foundation details | 13 | 0 | 2024-02-26 | 2024-03-15 | 26-Feb-24 A | 15-Mar-24 A
HE-CS-0980 | Review Company Comments - Lighting pole foundation details | 86 | 0 | 2024-04-01 | 2024-08-09 | 01-Apr-24 A | 09-Aug-24 A
HE-CS-0990 | Re-Issue for Approval - Lighting pole foundation details | 10 | 10 | 2024-08-12 | 2024-08-23 | 2024-10-28 | 2024-11-08 | 9
HE-CS-1000 | Obtain Company Approval - Lighting pole foundation details | 10 | 10 | 2024-08-26 | 2024-09-06 | 2024-11-11 | 2024-11-22 | 9
HE-CS-1010 | Final Issue for Design/ Construction-TYPICAL LIGHTING POLE FOUNDATION DETAILS | 10 | 10 | 2024-09-09 | 2024-09-20 | 2024-11-25 | 2024-12-10 | 9
Typical Detailed Drawing - Jib Crane Foundation |  | 79 | 0 | 2024-03-12 | 2024-09-20 | 12-Mar-24 A | 12-Jul-24 A
HE-CS-1030 | Issued for Review - Typical Detailed Drawing - Jib Crane Foundation | 7 | 0 | 2024-03-12 | 2024-03-23 | 12-Mar-24 A | 23-Mar-24 A
HE-CS-1040 | Review Company Comments - Typical Detailed Drawing - Jib Crane Foundation | 12 | 0 | 2024-03-31 | 2024-04-23 | 31-Mar-24 A | 23-Apr-24 A
HE-CS-1050 | Re-Issue for Approval - Typical Detailed Drawing - Jib Crane Foundation | 6 | 0 | 2024-06-07 | 2024-06-18 | 07-Jun-24 A | 18-Jun-24 A
HE-CS-1060 | Obtain Company Approval - Typical Detailed Drawing - Jib Crane Foundation | 4 | 0 | 2024-07-29 | 2024-08-09 | 19-Jun-24 A | 25-Jun-24 A
HE-CS-1070 | Final Issue for Design/ Construction-Typical Detailed Drawing - Jib Crane Foundation | 12 | 0 | 2024-09-09 | 2024-09-20 | 26-Jun-24 A | 12-Jul-24 A
Design Calculation for Typical Pipe supports |  | 157 | 15 | 2024-03-31 | 2024-09-06 | 31-Mar-24 A | 2024-11-15 | 77
HE-CS-1090 | Issued for Review - Calculations for Pipe supports | 11 | 0 | 2024-03-31 | 2024-04-22 | 31-Mar-24 A | 22-Apr-24 A
HE-CS-1100 | Review Company Comments - Calculations for Pipe supports | 10 | 0 | 2024-07-29 | 2024-08-09 | 29-Jul-24 A | 09-Aug-24 A
HE-CS-1110 | Re-Issue for Approval - Calculations for Pipe supports | 21 | 0 | 2024-08-12 | 2024-08-16 | 02-Sep-24 A | 30-Sep-24 A
HE-CS-1120 | Obtain Company Approval - Calculations for Pipe supports | 42 | 10 | 2024-08-19 | 2024-08-30 | 12-Sep-24 A | 2024-11-08 | 77
HE-CS-1130 | Final Issue for Design/ Construction-Design Calculation for Typical Pipe supports | 5 | 5 | 2024-09-02 | 2024-09-06 | 2024-11-11 | 2024-11-15 | 77
Design Calculation for Typical Shelter |  | 239 | 11 | 2023-11-27 | 2024-08-12 | 27-Nov-23 A | 2024-11-11 | 23
HE-CS-1840 | Issued for Review - Calculations for Shelter | 10 | 0 | 2023-11-27 | 2023-12-12 | 27-Nov-23 A | 12-Dec-23 A
HE-CS-1850 | Review Company Comments - Calculations for Shelter | 8 | 0 | 2023-12-13 | 2023-12-25 | 13-Dec-23 A | 25-Dec-23 A
HE-CS-1810 | Re-Issue for Approval - Calculations for Shelter | 10 | 0 | 2023-12-29 | 2024-01-15 | 29-Dec-23 A | 15-Jan-24 A
HE-CS-1820 | Obtain Company Approval - Calculations for Shelter | 128 | 0 | 2024-01-16 | 2024-07-29 | 16-Jan-24 A | 26-Jul-24 A
HE-CS-1830 | Final Issue for Design/ Construction-Design Calculation for Shelter | 38 | 11 | 2024-07-29 | 2024-08-12 | 19-Sep-24 A | 2024-11-11 | 23
Design Calculation for Typical Valve Pit |  | 135 | 5 | 2024-04-23 | 2024-09-06 | 23-Apr-24 A | 2024-11-01 | 48
HE-CS-1890 | Issued for Review - Calculations for Valve Pit | 10 | 0 | 2024-04-23 | 2024-05-07 | 23-Apr-24 A | 07-May-24 A
HE-CS-1900 | Review Company Comments - Calculations for Valve Pit | 10 | 0 | 2024-07-29 | 2024-08-09 | 29-Jul-24 A | 09-Aug-24 A
HE-CS-1860 | Re-Issue for Approval - Calculations for Valve Pit | 16 | 0 | 2024-08-12 | 2024-08-16 | 12-Aug-24 A | 02-Sep-24 A
HE-CS-1870 | Obtain Company Approval - Calculations for Valve Pit | 14 | 0 | 2024-08-19 | 2024-08-30 | 03-Sep-24 A | 22-Sep-24 A
HE-CS-1880 | Final Issue for Design/ Construction-Design Calculation for Valve Pit | 25 | 5 | 2024-09-02 | 2024-09-06 | 30-Sep-24 A | 2024-11-01 | 48
Design Calculation for Impact Wall |  | 148 | 5 | 2024-03-29 | 2024-08-16 | 29-Mar-24 A | 2024-11-01 | 34
HE-CS-1940 | Issued for Review - Calculations for Impact Wall | 21 | 0 | 2024-03-29 | 2024-05-03 | 29-Mar-24 A | 03-May-24 A
HE-CS-1950 | Review Company Comments - Calculations for Impact Wall | 16 | 0 | 2024-05-16 | 2024-06-07 | 16-May-24 A | 07-Jun-24 A
HE-CS-1910 | Re-Issue for Approval - Calculations for Impact Wall | 4 | 0 | 2024-06-08 | 2024-06-14 | 08-Jun-24 A | 14-Jun-24 A
HE-CS-1920 | Obtain Company Approval - Calculations for Impact Wall | 35 | 0 | 2024-06-21 | 2024-08-09 | 21-Jun-24 A | 09-Aug-24 A
HE-CS-1930 | Final Issue for Design/ Construction-Design Calculation for Impact Wall | 25 | 5 | 2024-08-12 | 2024-08-16 | 30-Sep-24 A | 2024-11-01 | 34
Valve pit foundation GA and RC (typ) details |  | 155 | 10 | 2024-03-26 | 2024-09-20 | 26-Mar-24 A | 2024-11-08 | 43
HE-CS-1150 | Issued for Review - Valve pit foundation GA and RC (type) details | 16 | 0 | 2024-03-26 | 2024-04-24 | 26-Mar-24 A | 24-Apr-24 A
HE-CS-1160 | Review Company Comments - Valve pit foundation GA and RC (type) details | 36 | 0 | 2024-06-14 | 2024-08-09 | 14-Jun-24 A | 09-Aug-24 A
HE-CS-1170 | Re-Issue for Approval - Valve pit foundation GA and RC (type) details | 6 | 0 | 2024-08-12 | 2024-08-23 | 02-Sep-24 A | 09-Sep-24 A
HE-CS-1180 | Obtain Company Approval - Valve pit foundation GA and RC (type) details | 9 | 0 | 2024-08-26 | 2024-09-06 | 10-Sep-24 A | 21-Sep-24 A
HE-CS-1190 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | 30 | 10 | 2024-09-09 | 2024-09-20 | 30-Sep-24 A | 2024-11-08 | 43
Typical GA and RC Details of Impact Wall |  | 148 | 5 | 2024-03-29 | 2024-08-23 | 29-Mar-24 A | 2024-11-01 | 34
HE-CS-1210 | Issued for Review - Impact Wall GA and RC (type) details | 17 | 0 | 2024-03-29 | 2024-04-28 | 29-Mar-24 A | 28-Apr-24 A
HE-CS-1220 | Review Company Comments - Impact Wall GA and RC (type) details | 14 | 0 | 2024-05-16 | 2024-06-05 | 16-May-24 A | 05-Jun-24 A
HE-CS-1230 | Re-Issue for Approval - Impact Wall GA and RC (type) details | 2 | 0 | 2024-06-06 | 2024-06-08 | 06-Jun-24 A | 08-Jun-24 A
HE-CS-1240 | Obtain Company Approval - Impact Wall GA and RC (type) details | 6 | 0 | 2024-06-09 | 2024-06-21 | 09-Jun-24 A | 21-Jun-24 A
HE-CS-1250 | Final Issue for Design/ Construction-TYPICAL GA AND RC DETAILS OF IMPACT WALL | 21 | 5 | 2024-08-19 | 2024-08-23 | 04-Oct-24 A | 2024-11-01 | 34
Typical Foundation Details for Shelters |  | 241 | 5 | 2023-11-30 | 2024-08-19 | 30-Nov-23 A | 2024-11-18 | 23
HE-CS-1270 | Issued for Review - Passive cooled shelter foundation GA and details | 8 | 0 | 2023-11-30 | 2023-12-13 | 30-Nov-23 A | 13-Dec-23 A
HE-CS-1280 | Review Company Comments - Passive cooled shelter foundation GA and details | 9 | 0 | 2023-12-14 | 2023-12-27 | 14-Dec-23 A | 27-Dec-23 A
HE-CS-1290 | Re-Issue for Approval - Passive cooled shelter foundation GA and details | 3 | 0 | 2024-01-31 | 2024-02-03 | 31-Jan-24 A | 03-Feb-24 A
HE-CS-1300 | Obtain Company Approval - Passive cooled shelter foundation GA and details | 10 | 0 | 2024-07-29 | 2024-08-09 | 29-Jul-24 A | 09-Aug-24 A
HE-CS-1310 | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | 5 | 5 | 2024-08-13 | 2024-08-19 | 2024-11-12 | 2024-11-18 | 23
Typical Structural Steel and Foundation details for pipe support |  | 180 | 5 | 2024-02-10 | 2024-08-23 | 10-Feb-24 A | 2024-11-01 | 48
HE-CS-1330 | Issued for Review - Typical Structural Steel and Foundation details for pipe support | 4 | 0 | 2024-02-10 | 2024-02-16 | 10-Feb-24 A | 16-Feb-24 A
HE-CS-1340 | Review Company Comments - Typical Structural Steel and Foundation details for pipe support | 9 | 0 | 2024-03-31 | 2024-04-18 | 31-Mar-24 A | 18-Apr-24 A
HE-CS-1350 | Re-Issue for Approval - Typical Structural Steel and Foundation details for pipe support | 72 | 0 | 2024-04-19 | 2024-08-02 | 19-Apr-24 A | 02-Aug-24 A
HE-CS-1360 | Obtain Company Approval - Typical Structural Steel and Foundation details for pipe support | 10 | 0 | 2024-08-05 | 2024-08-16 | 30-Sep-24 A | 11-Oct-24 A
HE-CS-1370 | Final Issue for Design/ Construction-Typical Structural Steel and Foundation details for pipe support | 16 | 5 | 2024-08-19 | 2024-08-23 | 11-Oct-24 A | 2024-11-01 | 48
Pipe Sleeper layout and details |  | 35 | 35 | 2024-07-29 | 2024-09-20 | 2024-10-28 | 2024-12-17 | 33
HE-CS-1390 | Issued for Review - Pipe Sleeper layout and details. | 5 | 5 | 2024-07-29 | 2024-08-09 | 2024-10-28 | 2024-11-01 | 33
HE-CS-1400 | Review Company Comments - Pipe Sleeper layout and details. | 10 | 10 | 2024-08-12 | 2024-08-23 | 2024-11-04 | 2024-11-15 | 33
HE-CS-1410 | Re-Issue for Approval - Pipe Sleeper layout and details. | 5 | 5 | 2024-08-26 | 2024-08-30 | 2024-11-18 | 2024-11-22 | 33
HE-CS-1420 | Obtain Company Approval - Pipe Sleeper layout and details. | 10 | 10 | 2024-09-02 | 2024-09-13 | 2024-11-25 | 2024-12-10 | 33
HE-CS-1430 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | 5 | 5 | 2024-09-16 | 2024-09-20 | 2024-12-11 | 2024-12-17 | 33
Misc. supports |  | 181 | 5 | 2024-03-01 | 2024-08-23 | 01-Mar-24 A | 2024-11-22 | 99
HE-CS-1450 | Issued for Review - Misc. supports and civil/ structural details | 5 | 0 | 2024-03-01 | 2024-03-08 | 01-Mar-24 A | 08-Mar-24 A
HE-CS-1460 | Review Company Comments - Misc. supports and civil/ structural details | 6 | 0 | 2024-03-11 | 2024-03-21 | 11-Mar-24 A | 21-Mar-24 A
HE-CS-1470 | Re-Issue for Approval - Misc. supports and civil/ structural details | 25 | 0 | 2024-03-22 | 2024-05-03 | 22-Mar-24 A | 03-May-24 A
HE-CS-1480 | Obtain Company Approval - Misc. supports and civil/ structural details | 6 | 0 | 2024-07-29 | 2024-08-09 | 30-Sep-24 A | 07-Oct-24 A
HE-CS-1490 | Final Issue for Design/ Construction-Misc. supports | 5 | 5 | 2024-08-19 | 2024-08-23 | 2024-11-18 | 2024-11-22 | 99
Civil MTO |  | 173 | 5 | 2024-03-29 | 2024-09-27 | 29-Mar-24 A | 2024-12-10 | 28
HE-CS-1510 | Issued - Civil MTO 1 | 6 | 0 | 2024-03-29 | 2024-04-09 | 29-Mar-24 A | 09-Apr-24 A
HE-CS-1550 | Issued - Civil MTO 2 | 5 | 5 | 2024-09-23 | 2024-09-27 | 2024-12-04 | 2024-12-10 | 28
Material / Corrosion |  | 356 | 50 | 2023-08-09 | 2024-10-04 | 09-Aug-23 A | 2025-01-08 | 240
Material Selection & Corrosion Control Philosophy |  | 75 | 0 | 2023-08-09 | 2023-11-22 | 09-Aug-23 A | 22-Nov-23 A
HE-CP-50 | Issue ICR - Material Selection & Corrosion Control Philosophy | 8 | 0 | 2023-08-09 | 2023-08-21 | 09-Aug-23 A | 21-Aug-23 A
HE-CP-60 | Receive Company Comments - Material Selection & Corrosion Control Philosophy | 5 | 0 | 2023-08-22 | 2023-08-29 | 22-Aug-23 A | 29-Aug-23 A
HE-CP-70 | Re-Issue for Approval - Material Selection & Corrosion Control Philosophy | 5 | 0 | 2023-09-15 | 2023-09-22 | 15-Sep-23 A | 22-Sep-23 A
HE-CP-80 | Obtain Company Approval - Material Selection & Corrosion Control Philosophy | 3 | 0 | 2023-09-23 | 2023-09-28 | 23-Sep-23 A | 28-Sep-23 A
HE-CP-90 | Final Issue for Design/ Construction-Material Selection & Corrosion Control Philosophy | 5 | 0 | 2023-11-15 | 2023-11-22 | 15-Nov-23 A | 22-Nov-23 A
Material Selection Diagram |  | 72 | 0 | 2023-08-12 | 2023-11-22 | 12-Aug-23 A | 22-Nov-23 A
HE-CP-0010 | Issue ICR - Material Selection Diagram | 6 | 0 | 2023-08-12 | 2023-08-22 | 12-Aug-23 A | 22-Aug-23 A
HE-CP-0020 | Receive Company Comments - Material Selection Diagram | 4 | 0 | 2023-08-23 | 2023-08-29 | 23-Aug-23 A | 29-Aug-23 A
HE-CP-0030 | Re-Issue for Approval - Material Selection Diagram | 16 | 0 | 2023-09-08 | 2023-10-02 | 08-Sep-23 A | 02-Oct-23 A
HE-CP-0040 | Obtain Company Approval - Material Selection Diagram | 8 | 0 | 2023-10-03 | 2023-10-13 | 03-Oct-23 A | 13-Oct-23 A
HE-CP-0050 | Final Issue for Design/ Construction-Material Selection Diagram | 9 | 0 | 2023-11-09 | 2023-11-22 | 09-Nov-23 A | 22-Nov-23 A
Material Selection Report |  | 66 | 0 | 2023-08-22 | 2023-11-22 | 22-Aug-23 A | 22-Nov-23 A
HE-CP-200 | Issue ICR - Material Selection Report | 8 | 0 | 2023-08-22 | 2023-09-01 | 22-Aug-23 A | 01-Sep-23 A
HE-CP-210 | Receive Company Comments - Material Selection Report | 4 | 0 | 2023-09-01 | 2023-09-07 | 01-Sep-23 A | 07-Sep-23 A
HE-CP-220 | Re-Issue for Approval - Material Selection Report | 16 | 0 | 2023-09-08 | 2023-10-02 | 08-Sep-23 A | 02-Oct-23 A
HE-CP-230 | Obtain Company Approval - Material Selection Report | 8 | 0 | 2023-10-03 | 2023-10-13 | 03-Oct-23 A | 13-Oct-23 A
HE-CP-240 | Final Issue for Design/ Construction-Material Selection Report | 7 | 0 | 2023-11-11 | 2023-11-22 | 11-Nov-23 A | 22-Nov-23 A
Scope of Work |  | 75 | 0 | 2023-10-10 | 2024-01-25 | 10-Oct-23 A | 25-Jan-24 A
HE-CP-100 | Issue ICR - Scope of Work for RBI Study | 11 | 0 | 2023-10-10 | 2023-10-25 | 10-Oct-23 A | 25-Oct-23 A
HE-CP-110 | Receive Company Comments - Scope of Work for RBI Study | 6 | 0 | 2023-11-08 | 2023-11-16 | 08-Nov-23 A | 16-Nov-23 A
HE-CP-120 | Re-Issue for Approval - Scope of Work for RBI Study | 5 | 0 | 2023-11-17 | 2023-11-24 | 17-Nov-23 A | 24-Nov-23 A
HE-CP-130 | Obtain Company Approval - Scope of Work for RBI Study | 6 | 0 | 2023-12-29 | 2024-01-09 | 29-Dec-23 A | 09-Jan-24 A
HE-CP-140 | Final Issue for Design/ Construction-Scope of Work for RBI Study | 9 | 0 | 2024-01-12 | 2024-01-25 | 12-Jan-24 A | 25-Jan-24 A
Material Coating & Painting Specification |  | 71 | 0 | 2023-10-12 | 2024-01-23 | 12-Oct-23 A | 23-Jan-24 A
HE-CP-250 | Issue ICR - Material Coating & Painting Specification | 11 | 0 | 2023-10-12 | 2023-10-27 | 12-Oct-23 A | 27-Oct-23 A
HE-CP-260 | Receive Company Comments - Material Coating & Painting Specification | 4 | 0 | 2023-11-09 | 2023-11-15 | 09-Nov-23 A | 15-Nov-23 A
HE-CP-270 | Re-Issue for Approval - Material Coating & Painting Specification | 5 | 0 | 2023-11-16 | 2023-11-23 | 16-Nov-23 A | 23-Nov-23 A
HE-CP-280 | Obtain Company Approval - Material Coating & Painting Specification | 6 | 0 | 2023-12-29 | 2024-01-09 | 29-Dec-23 A | 09-Jan-24 A
HE-CP-290 | Final Issue for Design/ Construction-Material Coating & Painting Specification | 7 | 0 | 2024-01-12 | 2024-01-23 | 12-Jan-24 A | 23-Jan-24 A
TBE |  | 38 | 0 | 2024-01-29 | 2024-03-22 | 29-Jan-24 A | 22-Mar-24 A
HE-CP-150 | Issue ICR - TBE for RBI Study | 4 | 0 | 2024-01-29 | 2024-02-02 | 29-Jan-24 A | 02-Feb-24 A
HE-CP-160 | Receive Company Comments - TBE for RBI Study | 9 | 0 | 2024-02-03 | 2024-02-16 | 03-Feb-24 A | 16-Feb-24 A
HE-CP-170 | Re-Issue for Approval - TBE for RBI Study | 9 | 0 | 2024-02-17 | 2024-03-01 | 17-Feb-24 A | 01-Mar-24 A
HE-CP-180 | Obtain Company Approval - TBE for RBI Study | 8 | 0 | 2024-03-02 | 2024-03-15 | 02-Mar-24 A | 15-Mar-24 A
HE-CP-190 | Final Issue for Design/ Construction-TBE for RBI Study | 3 | 0 | 2024-03-16 | 2024-03-22 | 16-Mar-24 A | 22-Mar-24 A
RBI Study Report |  | 50 | 50 | 2024-07-29 | 2024-10-04 | 2024-10-28 | 2025-01-08 | 240
HE-CP-300 | Issue ICR - RBI Study Report | 10 | 10 | 2024-07-29 | 2024-08-09 | 2024-10-28 | 2024-11-08 | 240
HE-CP-310 | Receive Company Comments - RBI Study Report | 10 | 10 | 2024-08-12 | 2024-08-23 | 2024-11-11 | 2024-11-22 | 240
HE-CP-320 | Re-Issue for Approval - RBI Study Report | 10 | 10 | 2024-08-26 | 2024-09-06 | 2024-11-25 | 2024-12-10 | 240
HE-CP-330 | Obtain Company Approval - RBI Study Report | 10 | 10 | 2024-09-09 | 2024-09-20 | 2024-12-11 | 2024-12-24 | 240
HE-CP-340 | Final Issue for Design/ Construction-RBI Study Report | 10 | 10 | 2024-09-23 | 2024-10-04 | 2024-12-25 | 2025-01-08 | 240
Electrical |  | 357 | 50 | 2023-08-08 | 2024-10-25 | 08-Aug-23 A | 2025-01-08 | 207
Electrical Design Basis |  | 73 | 0 | 2023-08-08 | 2023-11-17 | 08-Aug-23 A | 17-Nov-23 A
HE-EL-180 | Issue ICR-Design Basis | 11 | 0 | 2023-08-08 | 2023-08-23 | 08-Aug-23 A | 23-Aug-23 A
HE-EL-190 | Receive Company Comments-Design Basis | 5 | 0 | 2023-08-24 | 2023-08-31 | 24-Aug-23 A | 31-Aug-23 A
HE-EL-150 | Re-Issue for Approval-Design Basis | 11 | 0 | 2023-09-15 | 2023-09-30 | 15-Sep-23 A | 30-Sep-23 A
HE-EL-170 | Obtain Company Approval-Design Basis | 4 | 0 | 2023-10-02 | 2023-10-06 | 02-Oct-23 A | 06-Oct-23 A
HE-EL-160 | Final Issue for Design/ Construction-Design Basis | 7 | 0 | 2023-11-08 | 2023-11-17 | 08-Nov-23 A | 17-Nov-23 A
Load List (Updates + New) |  | 114 | 0 | 2023-10-02 | 2024-03-11 | 02-Oct-23 A | 11-Mar-24 A
HE-EL-0070 | Issue ICR-Update /New Load List | 11 | 0 | 2023-10-02 | 2023-10-17 | 02-Oct-23 A | 17-Oct-23 A
HE-EL-0080 | Receive Company Comments-Update /New Load List | 6 | 0 | 2023-10-18 | 2023-10-26 | 18-Oct-23 A | 26-Oct-23 A
HE-EL-0090 | Re-Issue for Approval-Update /New Load List | 7 | 0 | 2023-11-21 | 2023-11-30 | 21-Nov-23 A | 30-Nov-23 A
HE-EL-0100 | Obtain Company Approval-Update /New Load List | 10 | 0 | 2023-12-01 | 2023-12-18 | 01-Dec-23 A | 18-Dec-23 A
HE-EL-0110 | Final Issue for Design/ Construction-Load List | 55 | 0 | 2023-12-25 | 2024-03-11 | 25-Dec-23 A | 11-Mar-24 A
Electrical Adequacy Check Report |  | 56 | 35 | 2024-07-29 | 2024-09-27 | 27-Sep-24 A | 2024-12-17 | 56
HE-EL-0130 | Issue ICR- Adequacy report of the Power supply requirements | 3 | 0 | 2024-07-29 | 2024-08-09 | 27-Sep-24 A | 01-Oct-24 A
HE-EL-0140 | Receive Company Comments- Adequacy report of the Power supply requirements | 10 | 10 | 2024-08-12 | 2024-08-23 | 2024-10-28 | 2024-11-08 | 56
HE-EL-0150 | Re-Issue for Approval- Adequacy report of the Power supply requirements | 10 | 10 | 2024-08-26 | 2024-09-06 | 2024-11-11 | 2024-11-22 | 56
HE-EL-0160 | Obtain Company Approval- Adequacy report of the Power supply requirements | 10 | 10 | 2024-09-09 | 2024-09-20 | 2024-11-25 | 2024-12-10 | 56
HE-EL-0170 | Final Issue for Design/ Construction-Electrical Adequacy Check Report | 5 | 5 | 2024-09-23 | 2024-09-27 | 2024-12-11 | 2024-12-17 | 56
Power Consumption Calculation (Instrumentation) |  | 50 | 40 | 2024-07-29 | 2024-10-04 | 14-Oct-24 A | 2024-12-24 | 118
HE-EL-5440 | Issue ICR- Power Consumption Calculation (Instrumentation) | 6 | 0 | 2024-07-29 | 2024-08-09 | 14-Oct-24 A | 21-Oct-24 A
HE-EL-5450 | Receive Company Comments- Power Consumption Calculation (Instrumentation) | 10 | 10 | 2024-08-12 | 2024-08-23 | 2024-10-28 | 2024-11-08 | 118
HE-EL-5460 | Re-Issue for Approval- Power Consumption Calculation (Instrumentation) | 5 | 5 | 2024-08-26 | 2024-08-30 | 2024-11-11 | 2024-11-15 | 118
HE-EL-5470 | Obtain Company Approval- Power Consumption Calculation (Instrumentation) | 10 | 10 | 2024-09-02 | 2024-09-13 | 2024-11-18 | 2024-11-29 | 118
HE-EL-5480 | Final Issue for Design/ Construction-Power Consumption Calculation (Instrumentation) | 5 | 5 | 2024-09-30 | 2024-10-04 | 2024-12-18 | 2024-12-24 | 118
Single Line Diagrams for LV Distribution Board |  | 165 | 0 | 2024-02-26 | 2024-08-16 | 26-Feb-24 A | 25-Oct-24 A
HE-EL-0190 | Issue ICR-Single Line Diagrams for LV Switchgear | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-EL-0200 | Receive Company Comments-Single Line Diagrams for LV Switchgear | 9 | 0 | 2024-03-10 | 2024-03-25 | 10-Mar-24 A | 25-Mar-24 A
HE-EL-0210 | Re-Issue for Approval-Single Line Diagrams for LV Switchgear | 8 | 0 | 2024-03-31 | 2024-04-17 | 31-Mar-24 A | 17-Apr-24 A
HE-EL-0220 | Obtain Company Approval-Single Line Diagrams for LV Switchgear | 27 | 0 | 2024-07-29 | 2024-08-09 | 18-Apr-24 A | 25-May-24 A
HE-EL-0230 | Final Issue for Design/ Construction-Single Line Diagrams for LV Distribution Board | 102 | 0 | 2024-08-12 | 2024-08-16 | 31-May-24 A | 25-Oct-24 A
UPS SLDs |  | 257 | 0 | 2023-10-15 | 2024-08-02 | 15-Oct-23 A | 25-Oct-24 A
HE-EL-0250 | Issue ICR - UPS SLD | 8 | 0 | 2023-10-15 | 2023-10-26 | 15-Oct-23 A | 26-Oct-23 A
HE-EL-0260 | Receive Company Comments - UPS SLD | 8 | 0 | 2023-11-13 | 2023-11-23 | 13-Nov-23 A | 23-Nov-23 A
HE-EL-0270 | Re-Issue for Approval - UPS SLD | 8 | 0 | 2024-03-30 | 2024-04-17 | 30-Mar-24 A | 17-Apr-24 A
HE-EL-0280 | Obtain Company Approval - UPS SLD | 6 | 0 | 2024-05-27 | 2024-06-04 | 27-May-24 A | 04-Jun-24 A
HE-EL-0290 | Final Issue for Design/ Construction-UPS SLD | 101 | 0 | 2024-07-29 | 2024-08-02 | 31-May-24 A | 25-Oct-24 A
Solar Panel System SLDs |  | 170 | 5 | 2024-02-26 | 2024-08-16 | 26-Feb-24 A | 2024-11-01 | 48
HE-EL-0310 | Issue ICR-Solar Panel System SLDs | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-EL-0320 | Receive Company Comments-Solar Panel System SLDs | 9 | 0 | 2024-03-10 | 2024-03-25 | 10-Mar-24 A | 25-Mar-24 A
HE-EL-0330 | Re-Issue for Approval-Solar Panel System SLDs | 4 | 0 | 2024-03-31 | 2024-04-07 | 31-Mar-24 A | 07-Apr-24 A
HE-EL-0340 | Obtain Company Approval-Solar Panel System SLDs | 7 | 0 | 2024-07-29 | 2024-08-09 | 27-May-24 A | 04-Jun-24 A
HE-EL-0350 | Final Issue for Design/ Construction-Solar Panel System SLDs | 45 | 5 | 2024-08-12 | 2024-08-16 | 02-Sep-24 A | 2024-11-01 | 48
Solar Panel Sizing |  | 156 | 15 | 2024-07-29 | 2024-09-27 | 01-Apr-24 A | 2024-11-15 | 43
HE-EL-0370 | Issue ICR-Solar Panel Sizing calculation | 6 | 0 | 2024-07-29 | 2024-08-09 | 01-Apr-24 A | 15-Apr-24 A
HE-EL-0380 | Receive Company Comments-Solar Panel Sizing calculation | 22 | 0 | 2024-08-12 | 2024-08-23 | 16-Apr-24 A | 15-May-24 A
HE-EL-0390 | Re-Issue for Approval-Solar Panel Sizing calculation | 83 | 0 | 2024-08-26 | 2024-09-06 | 16-Jun-24 A | 15-Oct-24 A
HE-EL-0400 | Obtain Company Approval-Solar Panel Sizing calculation | 10 | 10 | 2024-09-09 | 2024-09-20 | 2024-10-28 | 2024-11-08 | 43
HE-EL-0410 | Final Issue for Design/ Construction-Solar Panel Sizing | 5 | 5 | 2024-09-23 | 2024-09-27 | 2024-11-11 | 2024-11-15 | 43
Cable Sizing Calculation |  | 234 | 5 | 2023-11-24 | 2024-08-02 | 24-Nov-23 A | 2024-11-01 | 30
HE-EL-0430 | Issue ICR-Cable Sizing Calculation | 18 | 0 | 2023-11-24 | 2023-12-21 | 24-Nov-23 A | 21-Dec-23 A
HE-EL-0440 | Receive Company Comments-Cable Sizing Calculation | 10 | 0 | 2023-12-21 | 2024-01-05 | 21-Dec-23 A | 05-Jan-24 A
HE-EL-0450 | Re-Issue for Approval-Cable Sizing Calculation | 5 | 0 | 2024-01-06 | 2024-01-13 | 06-Jan-24 A | 13-Jan-24 A
HE-EL-0460 | Obtain Company Approval-Cable Sizing Calculation | 4 | 0 | 2024-01-29 | 2024-02-02 | 29-Jan-24 A | 02-Feb-24 A
HE-EL-0470 | Final Issue for Design/ Construction-Cable Sizing Calculation | 20 | 5 | 2024-07-29 | 2024-08-02 | 07-Oct-24 A | 2024-11-01 | 30
Electrical Equipment Layout |  | 195 | 0 | 2024-01-08 | 2024-09-27 | 08-Jan-24 A | 18-Oct-24 A
HE-EL-0490 | Issue ICR- Electrical Equipment Layout | 44 | 0 | 2024-01-08 | 2024-03-08 | 08-Jan-24 A | 08-Mar-24 A
HE-EL-0500 | Receive Company Comments- Electrical Equipment Layout | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-EL-0510 | Re-Issue for Approval- Electrical Equipment Layout | 4 | 0 | 2024-03-04 | 2024-03-08 | 04-Mar-24 A | 08-Mar-24 A
HE-EL-0520 | Obtain Company Approval- Electrical Equipment Layout | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-EL-0530 | Final Issue for Design/ Construction-Electrical Equipment Layout | 64 | 0 | 2024-09-23 | 2024-09-27 | 23-Jul-24 A | 18-Oct-24 A
Cable Schedule |  | 174 | 10 | 2024-02-27 | 2024-08-16 | 27-Feb-24 A | 2024-11-08 | 81
HE-EL-0560 | Receive Company Comments-Cable Schedule | 20 | 0 | 2024-02-27 | 2024-03-27 | 27-Feb-24 A | 27-Mar-24 A
HE-EL-0570 | Re-Issue for Approval-Cable Schedule | 20 | 0 | 2024-02-27 | 2024-03-27 | 27-Feb-24 A | 27-Mar-24 A
HE-EL-0580 | Obtain Company Approval-Cable Schedule | 20 | 0 | 2024-02-27 | 2024-03-27 | 27-Feb-24 A | 27-Mar-24 A
HE-EL-0550 | Issue ICR-Cable Schedule | 20 | 0 | 2024-02-27 | 2024-03-27 | 27-Feb-24 A | 27-Mar-24 A
HE-EL-0590 | Final Issue for Design/ Construction-Cable Schedule | 82 | 10 | 2024-08-05 | 2024-08-16 | 18-Jul-24 A | 2024-11-08 | 81
Hazardous Area Register |  | 40 | 40 | 2024-08-12 | 2024-10-04 | 2024-10-28 | 2024-12-24 | 66
HE-EL-5530 | Issue ICR-Hazardous Area Register | 10 | 10 | 2024-08-12 | 2024-08-23 | 2024-10-28 | 2024-11-08 | 66
HE-EL-5490 | Receive Company Comments-Hazardous Area Register | 10 | 10 | 2024-08-26 | 2024-09-06 | 2024-11-11 | 2024-11-22 | 66
HE-EL-5500 | Re-Issue for Approval-Hazardous Area Register | 5 | 5 | 2024-09-09 | 2024-09-13 | 2024-11-25 | 2024-11-29 | 66
HE-EL-5510 | Obtain Company Approval-Hazardous Area Register | 10 | 10 | 2024-09-16 | 2024-09-27 | 2024-12-04 | 2024-12-17 | 66
HE-EL-5520 | Final Issue for Design/ Construction-Hazardous Area Register | 5 | 5 | 2024-09-30 | 2024-10-04 | 2024-12-18 | 2024-12-24 | 66
Data Sheet |  | 260 | 0 | 2023-10-10 | 2024-09-27 | 10-Oct-23 A | 23-Oct-24 A
Data sheet for Distibution Transformers |  | 38 | 0 | 2023-11-15 | 2024-01-10 | 15-Nov-23 A | 10-Jan-24 A
HE-EL-0690 | Re-Issue for Approval-Data sheet for Distribution Transformer | 1 | 0 | 2023-11-15 | 2023-11-16 | 15-Nov-23 A | 16-Nov-23 A
HE-EL-0700 | Obtain Company Approval-Data sheet for Distribution Transformer | 1 | 0 | 2023-11-15 | 2023-11-16 | 15-Nov-23 A | 16-Nov-23 A
HE-EL-0670 | Issue ICR- Data sheet for Distribution Transformer | 1 | 0 | 2023-11-15 | 2023-11-16 | 15-Nov-23 A | 16-Nov-23 A
HE-EL-0680 | Receive Company Comments-Data sheet for Distribution Transformer | 1 | 0 | 2023-11-15 | 2023-11-16 | 15-Nov-23 A | 16-Nov-23 A
HE-EL-0710 | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | 7 | 0 | 2023-12-29 | 2024-01-10 | 29-Dec-23 A | 10-Jan-24 A
Data sheet for Distribution board |  | 67 | 0 | 2023-10-10 | 2024-01-14 | 10-Oct-23 A | 14-Jan-24 A
HE-EL-0610 | Issue ICR- Data sheet for LV Distribution board | 8 | 0 | 2023-10-10 | 2023-10-20 | 10-Oct-23 A | 20-Oct-23 A
HE-EL-0620 | Receive Company Comments-Data sheet for LV Distribution board | 5 | 0 | 2023-10-20 | 2023-10-27 | 20-Oct-23 A | 27-Oct-23 A
HE-EL-0630 | Re-Issue for Approval-Data sheet for LV Distribution board | 0 | 0 | 2023-12-08 | 2023-12-08 | 08-Dec-23 A | 08-Dec-23 A
HE-EL-0640 | Obtain Company Approval-Data sheet for LV Distribution board | 0 | 0 | 2023-12-08 | 2023-12-08 | 08-Dec-23 A | 08-Dec-23 A
HE-EL-0650 | Final Issue for Design/ Construction-Data sheet for LV Distribution board | 25 | 0 | 2023-12-08 | 2024-01-14 | 08-Dec-23 A | 14-Jan-24 A
Data Sheet for Solar Power System |  | 220 | 0 | 2023-11-15 | 2024-09-27 | 15-Nov-23 A | 03-Oct-24 A
HE-EL-0730 | Issue ICR- Datasheet for Solar panel system | 8 | 0 | 2023-11-15 | 2023-11-27 | 15-Nov-23 A | 27-Nov-23 A
HE-EL-0740 | Receive Company Comments- Datasheet for Solar panel system | 12 | 0 | 2023-11-28 | 2023-12-15 | 28-Nov-23 A | 15-Dec-23 A
HE-EL-0750 | Re-Issue for Approval- Datasheet for Solar panel system | 9 | 0 | 2023-12-18 | 2023-12-29 | 18-Dec-23 A | 29-Dec-23 A
HE-EL-0760 | Obtain Company Approval- Datasheet for Solar panel system | 4 | 0 | 2023-12-29 | 2024-01-05 | 29-Dec-23 A | 05-Jan-24 A
HE-EL-0770 | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | 5 | 0 | 2024-09-23 | 2024-09-27 | 27-Sep-24 A | 03-Oct-24 A
Data Sheet for HV cables |  | 49 | 0 | 2023-11-05 | 2024-01-16 | 05-Nov-23 A | 16-Jan-24 A
HE-EL-1910 | Issue ICR-Data Sheet for HV cables | 15 | 0 | 2023-11-05 | 2023-11-27 | 05-Nov-23 A | 27-Nov-23 A
HE-EL-1920 | Receive Company Comments-Data Sheet for HV cables | 1 | 0 | 2023-11-28 | 2023-11-29 | 28-Nov-23 A | 29-Nov-23 A
HE-EL-1930 | Re-Issue for Approval-Data Sheet for HV cables | 2 | 0 | 2023-12-01 | 2023-12-06 | 01-Dec-23 A | 06-Dec-23 A
HE-EL-1940 | Obtain Company Approval-Data Sheet for HV cables | 5 | 0 | 2023-12-07 | 2023-12-14 | 07-Dec-23 A | 14-Dec-23 A
HE-EL-1950 | Final Issue for Design/ Construction-Data Sheet for HV cables | 21 | 0 | 2023-12-15 | 2024-01-16 | 15-Dec-23 A | 16-Jan-24 A
Data Sheet for LV cables |  | 231 | 0 | 2023-11-20 | 2024-08-02 | 20-Nov-23 A | 23-Oct-24 A
HE-EL-0790 | Issue ICR-Data Sheet for LV cables | 7 | 0 | 2023-11-20 | 2023-11-29 | 20-Nov-23 A | 29-Nov-23 A
HE-EL-0800 | Receive Company Comments-Data Sheet for LV cables | 10 | 0 | 2023-11-30 | 2023-12-15 | 30-Nov-23 A | 15-Dec-23 A
HE-EL-0810 | Re-Issue for Approval-Data Sheet for LV cables | 3 | 0 | 2023-12-29 | 2024-01-04 | 29-Dec-23 A | 04-Jan-24 A
HE-EL-0820 | Obtain Company Approval-Data Sheet for LV cables | 14 | 0 | 2024-01-05 | 2024-01-25 | 05-Jan-24 A | 25-Jan-24 A
HE-EL-0830 | Final Issue for Design/ Construction-Data Sheet for LV cables | 8 | 0 | 2024-01-26 | 2024-08-02 | 14-Oct-24 A | 23-Oct-24 A
Data Sheet for AC UPS |  | 89 | 0 | 2023-10-10 | 2024-02-14 | 10-Oct-23 A | 14-Feb-24 A
HE-EL-1870 | Issue ICR- Datasheet for AC UPS | 8 | 0 | 2023-10-10 | 2023-10-20 | 10-Oct-23 A | 20-Oct-23 A
HE-EL-1880 | Receive Company Comments- Datasheet for AC UPS | 5 | 0 | 2023-10-20 | 2023-10-27 | 20-Oct-23 A | 27-Oct-23 A
HE-EL-1890 | Re-Issue for Approval- Datasheet for AC UPS | 4 | 0 | 2024-01-29 | 2024-02-02 | 29-Jan-24 A | 02-Feb-24 A
HE-EL-1900 | Obtain Company Approval- Datasheet for AC UPS | 4 | 0 | 2024-01-29 | 2024-02-02 | 29-Jan-24 A | 02-Feb-24 A
HE-EL-1860 | Final Issue for Design/ Construction-Data Sheet for AC UPS | 8 | 0 | 2024-02-02 | 2024-02-14 | 02-Feb-24 A | 14-Feb-24 A
Material Requisition |  | 248 | 10 | 2023-11-13 | 2024-10-04 | 13-Nov-23 A | 2024-11-08 | 130
Material Requisition for UPS System |  | 154 | 0 | 2023-12-05 | 2024-08-23 | 05-Dec-23 A | 22-Jul-24 A
HE-EL-0910 | Issue ICR-Material Requisition for UPS System | 5 | 0 | 2023-12-05 | 2023-12-12 | 05-Dec-23 A | 12-Dec-23 A
HE-EL-0920 | Receive Company Comments-Material Requisition for UPS System | 11 | 0 | 2023-12-12 | 2023-12-27 | 12-Dec-23 A | 27-Dec-23 A
HE-EL-0930 | Re-Issue for Approval-Material Requisition for UPS System | 22 | 0 | 2024-02-26 | 2024-03-29 | 26-Feb-24 A | 29-Mar-24 A
HE-EL-0940 | Obtain Company Approval-Material Requisition for UPS System | 14 | 0 | 2024-03-07 | 2024-03-29 | 07-Mar-24 A | 29-Mar-24 A
HE-EL-0950 | Final Issue for Design/ Construction-Material Requisition for UPS System | 15 | 0 | 2024-07-29 | 2024-08-23 | 01-Jul-24 A | 22-Jul-24 A
Material Requisition for Distribution Boards |  | 74 | 0 | 2024-01-29 | 2024-05-18 | 29-Jan-24 A | 18-May-24 A
HE-EL-0970 | Issue ICR-Material Requisition for Distribution Boards | 16 | 0 | 2024-01-29 | 2024-02-20 | 29-Jan-24 A | 20-Feb-24 A
HE-EL-0980 | Receive Company Comments-Material Requisition for Distribution Boards | 4 | 0 | 2024-02-26 | 2024-03-01 | 26-Feb-24 A | 01-Mar-24 A
HE-EL-0990 | Re-Issue for Approval-Material Requisition for Distribution Boards | 27 | 0 | 2024-03-04 | 2024-04-18 | 04-Mar-24 A | 18-Apr-24 A
HE-EL-1000 | Obtain Company Approval-Material Requisition for Distribution Boards | 5 | 0 | 2024-04-19 | 2024-04-26 | 19-Apr-24 A | 26-Apr-24 A
HE-EL-1010 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | 16 | 0 | 2024-04-26 | 2024-05-18 | 26-Apr-24 A | 18-May-24 A
Material Requisition for Distibution Transformers |  | 57 | 0 | 2023-11-13 | 2024-02-02 | 13-Nov-23 A | 02-Feb-24 A
HE-EL-1030 | Issue ICR-Material Requisition for Distribution Transformer | 1 | 0 | 2023-11-15 | 2023-11-16 | 15-Nov-23 A | 16-Nov-23 A
HE-EL-1040 | Receive Company Comments-Material Requisition for Distribution Transformer | 9 | 0 | 2023-11-13 | 2023-11-24 | 13-Nov-23 A | 24-Nov-23 A
HE-EL-1050 | Re-Issue for Approval-Material Requisition for Distribution Transformer | 0 | 0 | 2023-12-08 | 2023-12-08 | 08-Dec-23 A | 08-Dec-23 A
HE-EL-1060 | Obtain Company Approval-Material Requisition for Distribution Transformer | 0 | 0 | 2023-12-22 | 2023-12-22 | 22-Dec-23 A | 22-Dec-23 A
HE-EL-1070 | Final Issue for Design/ Construction-Material Requisition for Distribution Transformer | 4 | 0 | 2024-01-29 | 2024-02-02 | 29-Jan-24 A | 02-Feb-24 A
Material Requisition for Solar Panels |  | 113 | 0 | 2024-01-15 | 2024-10-04 | 15-Jan-24 A | 02-Jul-24 A
HE-EL-1090 | Issue ICR-Material Requisition for Solar Panels | 9 | 0 | 2024-01-15 | 2024-01-26 | 15-Jan-24 A | 26-Jan-24 A
HE-EL-1100 | Receive Company Comments-Material Requisition for Solar Panels | 9 | 0 | 2024-03-04 | 2024-03-17 | 04-Mar-24 A | 17-Mar-24 A
HE-EL-1110 | Re-Issue for Approval-Material Requisition for Solar Panels | 2 | 0 | 2024-06-12 | 2024-06-14 | 12-Jun-24 A | 14-Jun-24 A
HE-EL-1120 | Obtain Company Approval-Material Requisition for Solar Panels | 1 | 0 | 2024-06-14 | 2024-06-20 | 14-Jun-24 A | 20-Jun-24 A
HE-EL-1130 | Final Issue for Design/ Construction-Material Requisition for Solar Panels | 7 | 0 | 2024-09-30 | 2024-10-04 | 24-Jun-24 A | 02-Jul-24 A
Material Requisition for Power & Control Cables |  | 93 | 0 | 2024-04-09 | 2024-08-30 | 09-Apr-24 A | 26-Aug-24 A
HE-EL-1150 | Issue ICR-Material Requisition for Power & Control Cables | 7 | 0 | 2024-05-03 | 2024-05-14 | 03-May-24 A | 14-May-24 A
HE-EL-1160 | Receive Company Comments-Material Requisition for Power & Control Cables | 31 | 0 | 2024-04-09 | 2024-05-27 | 09-Apr-24 A | 27-May-24 A
HE-EL-1170 | Re-Issue for Approval-Material Requisition for Power & Control Cables | 5 | 0 | 2024-07-29 | 2024-08-09 | 01-Aug-24 A | 07-Aug-24 A
HE-EL-1180 | Obtain Company Approval-Material Requisition for Power & Control Cables | 4 | 0 | 2024-08-12 | 2024-08-23 | 08-Aug-24 A | 14-Aug-24 A
HE-EL-1190 | Final Issue for Design/ Construction-Material Requisition for Power & Control Cables | 8 | 0 | 2024-08-26 | 2024-08-30 | 15-Aug-24 A | 26-Aug-24 A
Material Requisition for LV Switchgear |  | 127 | 10 | 2024-05-10 | 2024-09-20 | 10-May-24 A | 2024-11-08 | 25
HE-EL-1960 | Issue ICR-Material Requisition for LV Switchgear | 8 | 0 | 2024-05-10 | 2024-05-22 | 10-May-24 A | 22-May-24 A
HE-EL-1970 | Receive Company Comments-Material Requisition for LV Switchgear | 2 | 0 | 2024-07-29 | 2024-08-09 | 29-May-24 A | 30-May-24 A
HE-EL-1980 | Re-Issue for Approval-Material Requisition for LV Switchgear | 5 | 0 | 2024-08-12 | 2024-08-23 | 01-Oct-24 A | 07-Oct-24 A
HE-EL-1990 | Obtain Company Approval-Material Requisition for LV Switchgear | 5 | 0 | 2024-08-26 | 2024-09-06 | 08-Oct-24 A | 14-Oct-24 A
HE-EL-2000 | Final Issue for Design/ Construction-Material Requisition for LV Switchgear | 19 | 10 | 2024-09-09 | 2024-09-20 | 15-Oct-24 A | 2024-11-08 | 25
Material Requisition for MOV Isolator |  | 56 | 0 | 2024-04-16 | 2024-08-16 | 16-Apr-24 A | 05-Jul-24 A
HE-EL-2060 | Issue ICR-Material Requisition for MOV Isolator | 7 | 0 | 2024-04-16 | 2024-04-25 | 16-Apr-24 A | 25-Apr-24 A
HE-EL-2070 | Receive Company Comments-Material Requisition for MOV Isolator | 9 | 0 | 2024-04-26 | 2024-05-09 | 26-Apr-24 A | 09-May-24 A
HE-EL-2080 | Re-Issue for Approval-Material Requisition for MOV Isolator | 9 | 0 | 2024-05-10 | 2024-05-23 | 10-May-24 A | 23-May-24 A
HE-EL-2090 | Obtain Company Approval-Material Requisition for MOV Isolator | 9 | 0 | 2024-05-24 | 2024-06-06 | 24-May-24 A | 06-Jun-24 A
HE-EL-2100 | Final Issue for Design/ Construction-Material Requisition for MOV Isolator | 12 | 0 | 2024-08-05 | 2024-08-16 | 20-Jun-24 A | 05-Jul-24 A
Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) |  | 28 | 0 | 2024-05-24 | 2024-08-16 | 24-May-24 A | 05-Jul-24 A
HE-EL-2110 | Issue ICR-Material Requisition for Electrical Bulks | 5 | 0 | 2024-05-24 | 2024-05-31 | 24-May-24 A | 31-May-24 A
HE-EL-2120 | Receive Company Comments-Material Requisition for Electrical Bulks | 5 | 0 | 2024-05-31 | 2024-06-07 | 31-May-24 A | 07-Jun-24 A
HE-EL-2130 | Re-Issue for Approval-Material Requisition for Electrical Bulks | 5 | 0 | 2024-06-07 | 2024-06-14 | 07-Jun-24 A | 14-Jun-24 A
HE-EL-2140 | Obtain Company Approval-Material Requisition for Electrical Bulks | 2 | 0 | 2024-06-14 | 2024-06-21 | 14-Jun-24 A | 21-Jun-24 A
HE-EL-2150 | Final Issue for Design/ Construction-Material Requisition for Electrical Bulks | 6 | 0 | 2024-08-05 | 2024-08-16 | 28-Jun-24 A | 05-Jul-24 A
Material Requisition for Cable Glanding & Termination |  | 59 | 0 | 2024-07-29 | 2024-09-27 | 06-May-24 A | 31-Jul-24 A
HE-EL-2010 | Issue ICR-Material Requisition for Glanding & Termination | 30 | 0 | 2024-07-29 | 2024-08-09 | 06-May-24 A | 17-Jun-24 A
HE-EL-2020 | Receive Company Comments-Material Requisition for Glanding & Termination | 7 | 0 | 2024-08-12 | 2024-08-23 | 18-Jun-24 A | 28-Jun-24 A
HE-EL-2030 | Re-Issue for Approval-Material Requisition for Glanding & Termination | 6 | 0 | 2024-08-26 | 2024-09-06 | 28-Jun-24 A | 08-Jul-24 A
HE-EL-2040 | Obtain Company Approval-Material Requisition for Glanding & Termination | 9 | 0 | 2024-09-09 | 2024-09-20 | 09-Jul-24 A | 19-Jul-24 A
HE-EL-2050 | Final Issue for Design/ Construction-Material Requisition for Glanding & Termination | 8 | 0 | 2024-09-23 | 2024-09-27 | 20-Jul-24 A | 31-Jul-24 A
Material Requisition for Modification Works |  | 70 | 0 | 2024-03-01 | 2024-06-20 | 01-Mar-24 A | 20-Jun-24 A
HE-EL-2160 | Issue ICR-Material Requisition for Modification Works | 15 | 0 | 2024-03-01 | 2024-03-24 | 01-Mar-24 A | 24-Mar-24 A
HE-EL-2170 | Receive Company Comments-Material Requisition for Modification Works | 9 | 0 | 2024-03-31 | 2024-04-18 | 31-Mar-24 A | 18-Apr-24 A
HE-EL-2180 | Re-Issue for Approval-Material Requisition for Modification Works | 3 | 0 | 2024-04-19 | 2024-04-24 | 19-Apr-24 A | 24-Apr-24 A
HE-EL-2190 | Obtain Company Approval-Material Requisition for Modification Works | 9 | 0 | 2024-04-24 | 2024-05-07 | 24-Apr-24 A | 07-May-24 A
HE-EL-2200 | Final Issue for Design/ Construction-Material Requisition for Modification Works | 2 | 0 | 2024-06-13 | 2024-06-20 | 13-Jun-24 A | 20-Jun-24 A
TBE |  | 243 | 20 | 2023-12-05 | 2024-10-25 | 05-Dec-23 A | 2024-11-22 | 237
TBE for Solar Panels |  | 146 | 0 | 2024-02-29 | 2024-10-18 | 29-Feb-24 A | 03-Oct-24 A
HE-EL-1270 | Issue ICR-TBE for Solar Panels | 46 | 0 | 2024-02-29 | 2024-05-13 | 29-Feb-24 A | 13-May-24 A
HE-EL-1280 | Receive Company Comments-TBE for Solar Panels | 5 | 0 | 2024-06-05 | 2024-06-12 | 05-Jun-24 A | 12-Jun-24 A
HE-EL-1290 | Re-Issue for Approval-TBE for Solar Panels | 10 | 0 | 2024-07-29 | 2024-08-02 | 02-Sep-24 A | 13-Sep-24 A
HE-EL-1300 | Obtain Company Approval-TBE for Solar Panels | 10 | 0 | 2024-08-05 | 2024-08-16 | 16-Sep-24 A | 27-Sep-24 A
HE-EL-1310 | Final Issue for Design/ Construction-TBE for Solar Panels | 5 | 0 | 2024-10-07 | 2024-10-18 | 27-Sep-24 A | 03-Oct-24 A
TBE for UPS System |  | 175 | 0 | 2023-12-15 | 2024-08-30 | 15-Dec-23 A | 30-Aug-24 A
HE-EL-1330 | Issue ICR-TBE for UPS System | 63 | 0 | 2023-12-15 | 2024-03-15 | 15-Dec-23 A | 15-Mar-24 A
HE-EL-1340 | Receive Company Comments-TBE for UPS System | 4 | 0 | 2024-03-19 | 2024-03-26 | 19-Mar-24 A | 26-Mar-24 A
HE-EL-1350 | Re-Issue for Approval-TBE for UPS System | 21 | 0 | 2024-03-24 | 2024-04-30 | 24-Mar-24 A | 30-Apr-24 A
HE-EL-1360 | Obtain Company Approval-TBE for UPS System | 11 | 0 | 2024-05-01 | 2024-05-16 | 01-May-24 A | 16-May-24 A
HE-EL-1370 | Final Issue for Design/ Construction-TBE for UPS System | 5 | 0 | 2024-08-26 | 2024-08-30 | 26-Aug-24 A | 30-Aug-24 A
TBE for Distribution Boards |  | 100 | 0 | 2024-06-13 | 2024-09-20 | 15-May-24 A | 07-Oct-24 A
HE-EL-1390 | Issue ICR-TBE for Distribution Boards | 11 | 0 | 2024-06-13 | 2024-08-09 | 15-May-24 A | 29-May-24 A
HE-EL-1400 | Receive Company Comments-TBE for Distribution Boards | 11 | 0 | 2024-08-12 | 2024-08-23 | 30-May-24 A | 13-Jun-24 A
HE-EL-1410 | Re-Issue for Approval-TBE for Distribution Boards | 8 | 0 | 2024-08-26 | 2024-08-30 | 14-Jun-24 A | 28-Jun-24 A
HE-EL-1420 | Obtain Company Approval-TBE for Distribution Boards | 16 | 0 | 2024-09-02 | 2024-09-13 | 01-Jul-24 A | 23-Jul-24 A
HE-EL-1430 | Final Issue for Design/ Construction-TBE for Distribution Boards | 5 | 0 | 2024-09-16 | 2024-09-20 | 01-Oct-24 A | 07-Oct-24 A
TBE for Distibution Transformers |  | 80 | 0 | 2023-12-05 | 2024-08-30 | 05-Dec-23 A | 28-Mar-24 A
HE-EL-1450 | Issue ICR-TBE for Distribution Transformer | 18 | 0 | 2023-12-05 | 2023-12-29 | 05-Dec-23 A | 29-Dec-23 A
HE-EL-1460 | Receive Company Comments-TBE for Distribution Transformer | 11 | 0 | 2023-12-29 | 2024-01-16 | 29-Dec-23 A | 16-Jan-24 A
HE-EL-1470 | Re-Issue for Approval-TBE for Distribution Transformer | 32 | 0 | 2024-07-29 | 2024-08-02 | 17-Jan-24 A | 29-Feb-24 A
HE-EL-1480 | Obtain Company Approval-TBE for Distribution Transformer | 9 | 0 | 2024-08-05 | 2024-08-16 | 01-Mar-24 A | 14-Mar-24 A
HE-EL-1490 | Final Issue for Design/ Construction-TBE for Distribution Transformer | 9 | 0 | 2024-08-19 | 2024-08-30 | 15-Mar-24 A | 28-Mar-24 A
TBE for Power & Control Cables |  | 92 | 0 | 2024-07-29 | 2024-10-25 | 01-Jun-24 A | 14-Oct-24 A
HE-EL-1510 | Issue ICR-TBE for Power & Control Cables | 3 | 0 | 2024-07-29 | 2024-09-06 | 01-Jun-24 A | 05-Jun-24 A
HE-EL-1520 | Receive Company Comments-TBE for Power & Control Cables | 3 | 0 | 2024-09-09 | 2024-09-20 | 05-Jun-24 A | 08-Jun-24 A
HE-EL-1530 | Re-Issue for Approval-TBE for Power & Control Cables | 67 | 0 | 2024-09-23 | 2024-10-04 | 09-Jun-24 A | 16-Sep-24 A
HE-EL-1540 | Obtain Company Approval-TBE for Power & Control Cables | 5 | 0 | 2024-10-07 | 2024-10-18 | 01-Oct-24 A | 07-Oct-24 A
HE-EL-1550 | Final Issue for Design/ Construction-TBE for Power & Control Cables | 5 | 0 | 2024-10-21 | 2024-10-25 | 08-Oct-24 A | 14-Oct-24 A
TBE for LV Switchgear |  | 127 | 20 | 2024-05-24 | 2024-09-27 | 24-May-24 A | 2024-11-22 | 23
HE-EL-2210 | Issue ICR-TBE for LV Switchgear | 88 | 0 | 2024-05-24 | 2024-06-17 | 24-May-24 A | 01-Oct-24 A
HE-EL-2220 | Receive Company Comments-TBE for LV Switchgear | 5 | 0 | 2024-07-29 | 2024-08-09 | 11-Oct-24 A | 18-Oct-24 A
HE-EL-2230 | Re-Issue for Approval-TBE for LV Switchgear | 5 | 5 | 2024-08-12 | 2024-08-16 | 2024-10-28 | 2024-11-01 | 23
HE-EL-2240 | Obtain Company Approval-TBE for LV Switchgear | 10 | 10 | 2024-08-19 | 2024-08-30 | 2024-11-04 | 2024-11-15 | 23
HE-EL-2250 | Final Issue for Design/ Construction-TBE for LV Switchgear | 5 | 5 | 2024-09-23 | 2024-09-27 | 2024-11-18 | 2024-11-22 | 23
TBE for MOV Isolator |  | 75 | 0 | 2024-05-24 | 2024-09-06 | 24-May-24 A | 11-Sep-24 A
HE-EL-2260 | Issue ICR-TBE for MOV Isolator | 16 | 0 | 2024-05-24 | 2024-06-17 | 24-May-24 A | 17-Jun-24 A
HE-EL-2270 | Receive Company Comments-TBE for MOV Isolator | 8 | 0 | 2024-07-29 | 2024-08-09 | 18-Jun-24 A | 01-Jul-24 A
HE-EL-2280 | Re-Issue for Approval-TBE for MOV Isolator | 9 | 0 | 2024-08-12 | 2024-08-16 | 02-Jul-24 A | 15-Jul-24 A
HE-EL-2290 | Obtain Company Approval-TBE for MOV Isolator | 10 | 0 | 2024-08-19 | 2024-08-30 | 16-Jul-24 A | 29-Jul-24 A
HE-EL-2300 | Final Issue for Design/ Construction-TBE for MOV Isolator | 8 | 0 | 2024-09-02 | 2024-09-06 | 02-Sep-24 A | 11-Sep-24 A
TBE for Electrical Bulks (JBs, Fixtures, Sockets etc) |  | 103 | 0 | 2024-05-09 | 2024-09-20 | 09-May-24 A | 04-Oct-24 A
HE-EL-2410 | Issue ICR-TBE for Electrical Bulks | 25 | 0 | 2024-05-09 | 2024-06-13 | 09-May-24 A | 13-Jun-24 A
HE-EL-2420 | Receive Company Comments-TBE for Electrical Bulks | 8 | 0 | 2024-07-29 | 2024-08-09 | 14-Jun-24 A | 29-Jun-24 A
HE-EL-2430 | Re-Issue for Approval-TBE for Electrical Bulks | 9 | 0 | 2024-08-12 | 2024-08-23 | 30-Jun-24 A | 13-Jul-24 A
HE-EL-2440 | Obtain Company Approval-TBE for Electrical Bulks | 10 | 0 | 2024-08-26 | 2024-09-06 | 14-Jul-24 A | 27-Jul-24 A
HE-EL-2450 | Final Issue for Design/ Construction-TBE for Electrical Bulks | 5 | 0 | 2024-09-09 | 2024-09-20 | 30-Sep-24 A | 04-Oct-24 A
TBE for Cable Glanding & Termination |  | 67 | 5 | 2024-08-26 | 2024-10-18 | 01-Aug-24 A | 2024-11-01 | 252
HE-EL-2360 | Issue ICR-TBE for Glanding & Termination | 6 | 0 | 2024-08-26 | 2024-09-06 | 01-Aug-24 A | 08-Aug-24 A
HE-EL-2370 | Receive Company Comments-TBE for Glanding & Termination | 5 | 0 | 2024-09-09 | 2024-09-20 | 09-Aug-24 A | 15-Aug-24 A
HE-EL-2380 | Re-Issue for Approval-TBE for Glanding & Termination | 5 | 0 | 2024-09-23 | 2024-09-27 | 01-Oct-24 A | 07-Oct-24 A
HE-EL-2390 | Obtain Company Approval-TBE for Glanding & Termination | 5 | 0 | 2024-09-30 | 2024-10-11 | 08-Oct-24 A | 14-Oct-24 A
HE-EL-2400 | Final Issue for Design/ Construction-TBE for Glanding & Termination | 14 | 5 | 2024-10-14 | 2024-10-18 | 15-Oct-24 A | 2024-11-01 | 252
TBE for Modification Works |  | 32 | 0 | 2024-05-13 | 2024-08-02 | 13-May-24 A | 28-Jun-24 A
HE-EL-2310 | Issue ICR-TBE for Modification Works | 15 | 0 | 2024-05-13 | 2024-06-03 | 13-May-24 A | 03-Jun-24 A
HE-EL-2320 | Receive Company Comments-TBE for Modification Works | 5 | 0 | 2024-06-03 | 2024-06-08 | 03-Jun-24 A | 08-Jun-24 A
HE-EL-2330 | Re-Issue for Approval-TBE for Modification Works | 4 | 0 | 2024-06-09 | 2024-06-14 | 09-Jun-24 A | 14-Jun-24 A
HE-EL-2340 | Obtain Company Approval-TBE for Modification Works | 1 | 0 | 2024-06-14 | 2024-06-15 | 14-Jun-24 A | 15-Jun-24 A
HE-EL-2350 | Final Issue for Design/ Construction-TBE for Modification Works | 6 | 0 | 2024-07-29 | 2024-08-02 | 21-Jun-24 A | 28-Jun-24 A
Cable Routing Layout |  | 193 | 5 | 2024-03-06 | 2024-09-27 | 06-Mar-24 A | 2024-12-17 | 56
HE-EL-1570 | Issue ICR-Cable Routing Layout | 4 | 0 | 2024-03-06 | 2024-03-11 | 06-Mar-24 A | 11-Mar-24 A
HE-EL-1580 | Receive Company Comments-Cable Routing Layout | 2 | 0 | 2024-03-12 | 2024-03-15 | 12-Mar-24 A | 15-Mar-24 A
HE-EL-1590 | Re-Issue for Approval-Cable Routing Layout | 49 | 0 | 2024-03-16 | 2024-05-31 | 16-Mar-24 A | 31-May-24 A
HE-EL-1600 | Obtain Company Approval-Cable Routing Layout | 4 | 0 | 2024-05-31 | 2024-06-06 | 31-May-24 A | 06-Jun-24 A
HE-EL-1610 | Final Issue for Design/ Construction-Cable Routing Layout | 5 | 5 | 2024-09-23 | 2024-09-27 | 2024-12-11 | 2024-12-17 | 56
Earthing Layout |  | 165 | 5 | 2024-03-04 | 2024-08-02 | 04-Mar-24 A | 2024-11-01 | 71
HE-EL-1640 | Receive Company Comments-Earthing Layout | 8 | 0 | 2024-03-04 | 2024-03-14 | 04-Mar-24 A | 14-Mar-24 A
HE-EL-1630 | Issue ICR-Earthing Layout | 3 | 0 | 2024-03-13 | 2024-03-18 | 13-Mar-24 A | 18-Mar-24 A
HE-EL-1650 | Re-Issue for Approval-Earthing Layout | 2 | 0 | 2024-03-15 | 2024-03-18 | 15-Mar-24 A | 18-Mar-24 A
HE-EL-1660 | Obtain Company Approval-Earthing Layout | 1 | 0 | 2024-03-19 | 2024-03-20 | 19-Mar-24 A | 20-Mar-24 A
HE-EL-1670 | Final Issue for Design/ Construction-Earthing Layout | 24 | 5 | 2024-07-29 | 2024-08-02 | 01-Oct-24 A | 2024-11-01 | 71
Lighting Layout |  | 157 | 5 | 2024-03-14 | 2024-08-30 | 14-Mar-24 A | 2024-11-01 | 71
HE-EL-1690 | Issue ICR-Lighting Layout | 9 | 0 | 2024-03-14 | 2024-03-28 | 14-Mar-24 A | 28-Mar-24 A
HE-EL-1700 | Receive Company Comments-Lighting Layout | 8 | 0 | 2024-04-10 | 2024-04-24 | 10-Apr-24 A | 24-Apr-24 A
HE-EL-1710 | Re-Issue for Approval-Lighting Layout | 7 | 0 | 2024-07-29 | 2024-08-09 | 17-Jun-24 A | 30-Jun-24 A
HE-EL-1720 | Obtain Company Approval-Lighting Layout | 10 | 0 | 2024-08-12 | 2024-08-23 | 01-Jul-24 A | 15-Jul-24 A
HE-EL-1730 | Final Issue for Design/ Construction-Lighting Layout | 15 | 5 | 2024-08-26 | 2024-08-30 | 14-Oct-24 A | 2024-11-01 | 71
Electrical Installation Drawings |  | 178 | 5 | 2024-02-14 | 2024-09-13 | 14-Feb-24 A | 2024-11-01 | 86
HE-EL-1750 | Issue ICR- Electrical Installation Drawings | 42 | 0 | 2024-02-14 | 2024-04-22 | 14-Feb-24 A | 22-Apr-24 A
HE-EL-1760 | Receive Company Comments- Electrical Installation Drawings | 16 | 0 | 2024-07-29 | 2024-08-09 | 06-May-24 A | 27-May-24 A
HE-EL-1770 | Re-Issue for Approval- Electrical Installation Drawings | 14 | 0 | 2024-08-12 | 2024-08-23 | 28-May-24 A | 14-Jun-24 A
HE-EL-1780 | Obtain Company Approval- Electrical Installation Drawings | 7 | 0 | 2024-08-26 | 2024-09-06 | 17-Jun-24 A | 28-Jun-24 A
HE-EL-1790 | Final Issue for Design/ Construction-Electrical Installation Drawings | 10 | 5 | 2024-09-09 | 2024-09-13 | 21-Oct-24 A | 2024-11-01 | 86
Electrical MTO |  | 111 | 50 | 2024-07-29 | 2024-10-18 | 02-Aug-24 A | 2025-01-08 | 56
HE-EL-1810 | Electrical 1st MTO | 10 | 0 | 2024-07-29 | 2024-08-16 | 02-Aug-24 A | 15-Aug-24 A
HE-EL-1830 | Electrical 2nd MTO | 15 | 15 | 2024-08-19 | 2024-09-06 | 2024-10-28 | 2024-11-15 | 76
HE-EL-1850 | Electrical 3rd MTO | 15 | 15 | 2024-09-30 | 2024-10-18 | 2024-12-18 | 2025-01-08 | 56
Instrumentation & Control |  | 347 | 44 | 2023-08-14 | 2024-10-25 | 14-Aug-23 A | 2024-12-30 | 225
I&C Design Basis |  | 72 | 0 | 2023-08-14 | 2023-11-22 | 14-Aug-23 A | 22-Nov-23 A
HE-IC-620 | Issue ICR- I&C Design Basis | 16 | 0 | 2023-08-14 | 2023-09-05 | 14-Aug-23 A | 05-Sep-23 A
HE-IC-580 | Receive Company Comments- I&C Design Basis | 8 | 0 | 2023-09-06 | 2023-09-16 | 06-Sep-23 A | 16-Sep-23 A
HE-IC-590 | Re-Issue for Approval- I&C Design Basis | 10 | 0 | 2023-09-17 | 2023-09-30 | 17-Sep-23 A | 30-Sep-23 A
HE-IC-600 | Obtain Company Approval- I&C Design Basis | 5 | 0 | 2023-10-02 | 2023-10-09 | 02-Oct-23 A | 09-Oct-23 A
HE-IC-610 | Final Issue for Design/ Construction- I&C Design Basis | 9 | 0 | 2023-11-09 | 2023-11-22 | 09-Nov-23 A | 22-Nov-23 A
Addendum to DGS Sales Gas Metering Station |  | 64 | 0 | 2023-09-06 | 2023-12-06 | 06-Sep-23 A | 06-Dec-23 A
HE-IC-0010 | Issue ICR- Addendum to DGs | 12 | 0 | 2023-09-06 | 2023-09-22 | 06-Sep-23 A | 22-Sep-23 A
HE-IC-0020 | Receive Company Comments- Addendum to DGs | 8 | 0 | 2023-09-23 | 2023-10-05 | 23-Sep-23 A | 05-Oct-23 A
HE-IC-0030 | Re-Issue for Approval- Addendum to DGs | 11 | 0 | 2023-10-06 | 2023-10-23 | 06-Oct-23 A | 23-Oct-23 A
HE-IC-0040 | Obtain Company Approval- Addendum to DGs | 5 | 0 | 2023-11-14 | 2023-11-21 | 14-Nov-23 A | 21-Nov-23 A
HE-IC-0050 | Final Issue for Design/ Construction-Addendum to DGs | 9 | 0 | 2023-11-22 | 2023-12-06 | 22-Nov-23 A | 06-Dec-23 A
Addendum to F&G System |  | 39 | 0 | 2024-01-29 | 2024-03-25 | 29-Jan-24 A | 25-Mar-24 A
HE-IC-2940 | Issue ICR- Addendum to DGs | 13 | 0 | 2024-01-29 | 2024-02-14 | 29-Jan-24 A | 14-Feb-24 A
HE-IC-2950 | Receive Company Comments- Addendum to DGs | 10 | 0 | 2024-02-15 | 2024-02-28 | 15-Feb-24 A | 28-Feb-24 A
HE-IC-2960 | Re-Issue for Approval- Addendum to DGs | 2 | 0 | 2024-02-29 | 2024-03-04 | 29-Feb-24 A | 04-Mar-24 A
HE-IC-2970 | Obtain Company Approval- Addendum to DGs | 9 | 0 | 2024-03-05 | 2024-03-18 | 05-Mar-24 A | 18-Mar-24 A
HE-IC-2980 | Final Issue for Design/ Construction-Addendum to DGs | 4 | 0 | 2024-03-19 | 2024-03-25 | 19-Mar-24 A | 25-Mar-24 A
Addendum to INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) |  | 36 | 0 | 2024-04-29 | 2024-06-20 | 29-Apr-24 A | 20-Jun-24 A
HE-IC-3340 | Issue ICR- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | 9 | 0 | 2024-04-29 | 2024-05-09 | 29-Apr-24 A | 09-May-24 A
HE-IC-3350 | Receive Company Comments- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | 9 | 0 | 2024-05-12 | 2024-05-23 | 12-May-24 A | 23-May-24 A
HE-IC-3360 | Re-Issue for Approval- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | 4 | 0 | 2024-05-26 | 2024-05-30 | 26-May-24 A | 30-May-24 A
HE-IC-3370 | Obtain Company Approval- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | 9 | 0 | 2024-06-02 | 2024-06-13 | 02-Jun-24 A | 13-Jun-24 A
HE-IC-3380 | Final Issue for Design/ Construction-Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | 1 | 0 | 2024-06-16 | 2024-06-20 | 16-Jun-24 A | 20-Jun-24 A
Specifications for PRS (Pressure Reduction System) |  | 67 | 0 | 2023-09-06 | 2023-12-11 | 06-Sep-23 A | 11-Dec-23 A
HE-IC-0070 | Issue ICR- Specifications for PRS (Pressure Reduction System) | 12 | 0 | 2023-09-06 | 2023-09-22 | 06-Sep-23 A | 22-Sep-23 A
HE-IC-0080 | Receive Company Comments- Specifications for PRS (Pressure Reduction System) | 8 | 0 | 2023-09-23 | 2023-10-05 | 23-Sep-23 A | 05-Oct-23 A
HE-IC-0090 | Re-Issue for Approval- Specifications for PRS (Pressure Reduction System) | 15 | 0 | 2023-10-06 | 2023-10-27 | 06-Oct-23 A | 27-Oct-23 A
HE-IC-0100 | Obtain Company Approval- Specifications for PRS (Pressure Reduction System) | 7 | 0 | 2023-11-10 | 2023-11-21 | 10-Nov-23 A | 21-Nov-23 A
HE-IC-0110 | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | 12 | 0 | 2023-11-22 | 2023-12-11 | 22-Nov-23 A | 11-Dec-23 A
Specification for RTU |  | 102 | 0 | 2023-11-17 | 2024-04-19 | 17-Nov-23 A | 19-Apr-24 A
HE-IC-0190 | Issue ICR- Specification for RTU | 4 | 0 | 2023-11-17 | 2023-11-23 | 17-Nov-23 A | 23-Nov-23 A
HE-IC-0200 | Receive Company Comments- Specification for RTU | 6 | 0 | 2023-11-24 | 2023-12-05 | 24-Nov-23 A | 05-Dec-23 A
HE-IC-0210 | Re-Issue for Approval- Specification for RTU | 6 | 0 | 2023-12-29 | 2024-01-09 | 29-Dec-23 A | 09-Jan-24 A
HE-IC-0220 | Obtain Company Approval- Specification for RTU | 3 | 0 | 2024-01-12 | 2024-01-17 | 12-Jan-24 A | 17-Jan-24 A
HE-IC-0230 | Final Issue for Design/ Construction-Specification for RTU | 10 | 0 | 2024-03-31 | 2024-04-19 | 31-Mar-24 A | 19-Apr-24 A
Specification for HYBRID PASSIVE COOLED SHELTER |  | 100 | 0 | 2023-10-20 | 2024-03-11 | 20-Oct-23 A | 11-Mar-24 A
HE-IC-3240 | Issue ICR- Specification for HYBRID PASSIVE COOLED SHELTER | 15 | 0 | 2023-10-20 | 2023-11-10 | 20-Oct-23 A | 10-Nov-23 A
HE-IC-3250 | Receive Company Comments- Specification for HYBRID PASSIVE COOLED SHELTER | 11 | 0 | 2023-11-13 | 2023-11-28 | 13-Nov-23 A | 28-Nov-23 A
HE-IC-3260 | Re-Issue for Approval- Specification for HYBRID PASSIVE COOLED SHELTER | 18 | 0 | 2023-11-29 | 2023-12-26 | 29-Nov-23 A | 26-Dec-23 A
HE-IC-3270 | Obtain Company Approval- Specification for HYBRID PASSIVE COOLED SHELTER | 2 | 0 | 2023-12-27 | 2023-12-29 | 27-Dec-23 A | 29-Dec-23 A
HE-IC-3280 | Final Issue for Design/ Construction-Specification for HYBRID PASSIVE COOLED SHELTER | 11 | 0 | 2024-02-26 | 2024-03-11 | 26-Feb-24 A | 11-Mar-24 A
Specification for HSSD |  | 68 | 0 | 2024-01-05 | 2024-04-18 | 05-Jan-24 A | 18-Apr-24 A
HE-IC-3190 | Issue ICR- Specification for HSSD | 10 | 0 | 2024-01-05 | 2024-01-19 | 05-Jan-24 A | 19-Jan-24 A
HE-IC-3200 | Receive Company Comments- Specification for HSSD | 4 | 0 | 2024-01-20 | 2024-01-26 | 20-Jan-24 A | 26-Jan-24 A
HE-IC-3210 | Re-Issue for Approval- Specification for HSSD | 14 | 0 | 2024-01-29 | 2024-02-16 | 29-Jan-24 A | 16-Feb-24 A
HE-IC-3220 | Obtain Company Approval- Specification for HSSD | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-IC-3230 | Final Issue for Design/ Construction-Specification for HSSD | 21 | 0 | 2024-03-11 | 2024-04-18 | 11-Mar-24 A | 18-Apr-24 A
Specification for Leak Detection System |  | 110 | 0 | 2023-09-27 | 2024-03-01 | 27-Sep-23 A | 01-Mar-24 A
HE-IC-0250 | Issue ICR- Specification for Leak Detection System | 3 | 0 | 2023-09-27 | 2023-10-02 | 27-Sep-23 A | 02-Oct-23 A
HE-IC-0260 | Receive Company Comments- Specification for Leak Detection System | 9 | 0 | 2023-10-03 | 2023-10-15 | 03-Oct-23 A | 15-Oct-23 A
HE-IC-0270 | Re-Issue for Approval- Specification for Leak Detection System | 28 | 0 | 2023-10-17 | 2023-11-24 | 17-Oct-23 A | 24-Nov-23 A
HE-IC-0280 | Obtain Company Approval- Specification for Leak Detection System | 10 | 0 | 2023-11-25 | 2023-12-12 | 25-Nov-23 A | 12-Dec-23 A
HE-IC-0290 | Final Issue for Design/ Construction-Specification for Leak Detection System | 4 | 0 | 2024-02-26 | 2024-03-01 | 26-Feb-24 A | 01-Mar-24 A
Instrument Index |  | 65 | 0 | 2023-12-25 | 2024-03-27 | 25-Dec-23 A | 27-Mar-24 A
HE-IC-0490 | Issue ICR-Instrument index -Update | 8 | 0 | 2023-12-25 | 2024-01-05 | 25-Dec-23 A | 05-Jan-24 A
HE-IC-0500 | Receive Company Comments-Instrument index -Update | 8 | 0 | 2023-12-25 | 2024-01-05 | 25-Dec-23 A | 05-Jan-24 A
HE-IC-0510 | Re-Issue for Approval-Instrument index -Update | 8 | 0 | 2023-12-25 | 2024-01-05 | 25-Dec-23 A | 05-Jan-24 A
HE-IC-0520 | Obtain Company Approval-Instrument index -Update | 8 | 0 | 2023-12-25 | 2024-01-05 | 25-Dec-23 A | 05-Jan-24 A
HE-IC-0530 | Final Issue for Design/ Construction-Instrument Index | 42 | 0 | 2024-01-26 | 2024-03-27 | 26-Jan-24 A | 27-Mar-24 A
I/O list |  | 182 | 10 | 2024-02-15 | 2024-08-09 | 15-Feb-24 A | 2024-11-08 | 86
HE-IC-0560 | Receive Company Comments- I/O list -Update | 10 | 0 | 2024-02-15 | 2024-02-29 | 15-Feb-24 A | 29-Feb-24 A
HE-IC-0570 | Re-Issue for Approval- I/O list -Update | 10 | 0 | 2024-02-15 | 2024-02-29 | 15-Feb-24 A | 29-Feb-24 A
HE-IC-0580 | Obtain Company Approval- I/O list -Update | 10 | 0 | 2024-02-15 | 2024-02-29 | 15-Feb-24 A | 29-Feb-24 A
HE-IC-0550 | Issue ICR- I/O list -Update | 10 | 0 | 2024-02-15 | 2024-02-29 | 15-Feb-24 A | 29-Feb-24 A
HE-IC-0590 | Final Issue for Design/ Construction-I/O list | 147 | 10 | 2024-04-09 | 2024-08-09 | 09-Apr-24 A | 2024-11-08 | 86
F&G Index |  | 189 | 10 | 2024-02-06 | 2024-08-09 | 06-Feb-24 A | 2024-11-08 | 86
HE-IC-2750 | Issue ICR-F&G index -Update | 4 | 0 | 2024-02-06 | 2024-02-12 | 06-Feb-24 A | 12-Feb-24 A
HE-IC-2760 | Receive Company Comments-F&G index -Update | 3 | 0 | 2024-02-13 | 2024-02-16 | 13-Feb-24 A | 16-Feb-24 A
HE-IC-2780 | Obtain Company Approval-F&G index -Update | 6 | 0 | 2024-02-16 | 2024-02-26 | 16-Feb-24 A | 26-Feb-24 A
HE-IC-2770 | Re-Issue for Approval-F&G index -Update | 3 | 0 | 2024-02-26 | 2024-02-29 | 26-Feb-24 A | 29-Feb-24 A
HE-IC-2740 | Final Issue for Design/ Construction-F&G Index | 30 | 10 | 2024-07-29 | 2024-08-09 | 30-Sep-24 A | 2024-11-08 | 86
F&G I/O list |  | 182 | 10 | 2024-02-15 | 2024-08-23 | 15-Feb-24 A | 2024-11-08 | 86
HE-IC-2700 | Re-Issue for Approval- I/O list -Update | 4 | 0 | 2024-02-15 | 2024-02-21 | 15-Feb-24 A | 21-Feb-24 A
HE-IC-2690 | Receive Company Comments- I/O list -Update | 9 | 0 | 2024-02-15 | 2024-02-28 | 15-Feb-24 A | 28-Feb-24 A
HE-IC-2710 | Obtain Company Approval- I/O list -Update | 9 | 0 | 2024-02-15 | 2024-02-28 | 15-Feb-24 A | 28-Feb-24 A
HE-IC-2730 | Issue ICR- I/O list -Update | 9 | 0 | 2024-02-15 | 2024-02-28 | 15-Feb-24 A | 28-Feb-24 A
HE-IC-2720 | Final Issue for Design/ Construction-I/O list | 29 | 10 | 2024-08-12 | 2024-08-23 | 01-Oct-24 A | 2024-11-08 | 86
Hook-Up Diagram |  | 185 | 5 | 2024-02-05 | 2024-08-16 | 05-Feb-24 A | 2024-11-01 | 96
HE-IC-0610 | Issue ICR - Hook-Up Diagram | 5 | 0 | 2024-02-05 | 2024-02-12 | 05-Feb-24 A | 12-Feb-24 A
HE-IC-0620 | Receive Company Comments - Hook-Up Diagram | 4 | 0 | 2024-02-13 | 2024-02-19 | 13-Feb-24 A | 19-Feb-24 A
HE-IC-0630 | Re-Issue for Approval - Hook-Up Diagram | 4 | 0 | 2024-02-20 | 2024-02-26 | 20-Feb-24 A | 26-Feb-24 A
HE-IC-0640 | Obtain Company Approval - Hook-Up Diagram | 4 | 0 | 2024-02-27 | 2024-03-04 | 27-Feb-24 A | 04-Mar-24 A
HE-IC-0650 | Final Issue for Design/ Construction-Hook-Up Diagram | 5 | 5 | 2024-08-12 | 2024-08-16 | 2024-10-28 | 2024-11-01 | 96
Instrument and F&G interconnection Wiring Diagram |  | 118 | 30 | 2024-08-12 | 2024-10-04 | 25-Jun-24 A | 2024-12-10 | 66
HE-IC-2790 | Issue ICR - interconnection Wiring Diagram | 69 | 0 | 2024-08-12 | 2024-08-23 | 25-Jun-24 A | 30-Sep-24 A
HE-IC-2800 | Receive Company Comments - interconnection Wiring Diagram | 94 | 10 | 2024-08-26 | 2024-09-06 | 29-Jun-24 A | 2024-11-08 | 66
HE-IC-2810 | Re-Issue for Approval - interconnection Wiring Diagram | 90 | 5 | 2024-09-09 | 2024-09-13 | 13-Jul-24 A | 2024-11-15 | 66
HE-IC-2820 | Obtain Company Approval - interconnection Wiring Diagram | 76 | 10 | 2024-09-16 | 2024-09-27 | 16-Aug-24 A | 2024-11-29 | 66
HE-IC-2830 | Final Issue for Design/ Construction-interconnection Wiring Diagram | 5 | 5 | 2024-09-30 | 2024-10-04 | 2024-12-04 | 2024-12-10 | 66
Typical Installation Drawings |  | 111 | 5 | 2024-05-27 | 2024-08-02 | 27-May-24 A | 2024-11-01 | 96
HE-IC-0670 | Issue ICR - Typical Installation Drawings | 4 | 0 | 2024-05-27 | 2024-05-31 | 27-May-24 A | 31-May-24 A
HE-IC-0680 | Receive Company Comments - Typical Installation Drawings | 1 | 0 | 2024-05-31 | 2024-06-03 | 31-May-24 A | 03-Jun-24 A
HE-IC-0700 | Obtain Company Approval - Typical Installation Drawings | 4 | 0 | 2024-06-04 | 2024-06-10 | 04-Jun-24 A | 10-Jun-24 A
HE-IC-0690 | Re-Issue for Approval - Typical Installation Drawings | 3 | 0 | 2024-06-11 | 2024-06-14 | 11-Jun-24 A | 14-Jun-24 A
HE-IC-0710 | Final Issue for Design/ Construction-Typical Installation Drawings | 5 | 5 | 2024-07-29 | 2024-08-02 | 2024-10-28 | 2024-11-01 | 96
Loop Diagrams |  | 137 | 40 | 2024-07-29 | 2024-10-18 | 07-Jun-24 A | 2024-12-24 | 66
HE-IC-0730 | Issue ICR - Loop Diagrams | 78 | 0 | 2024-07-29 | 2024-08-16 | 07-Jun-24 A | 30-Sep-24 A
HE-IC-0740 | Receive Company Comments - Loop Diagrams | 102 | 10 | 2024-08-19 | 2024-08-30 | 14-Jun-24 A | 2024-11-08 | 66
HE-IC-0750 | Re-Issue for Approval - Loop Diagrams | 10 | 10 | 2024-09-02 | 2024-09-13 | 2024-11-11 | 2024-11-22 | 66
HE-IC-0760 | Obtain Company Approval - Loop Diagrams | 10 | 10 | 2024-09-16 | 2024-09-27 | 2024-11-25 | 2024-12-10 | 66
HE-IC-0770 | Final Issue for Design/ Construction-Loop Diagrams | 10 | 10 | 2024-10-07 | 2024-10-18 | 2024-12-11 | 2024-12-24 | 66
Instrument and F&G Cable Block Diagram |  | 215 | 10 | 2023-12-29 | 2024-08-09 | 29-Dec-23 A | 2024-11-08 | 86
HE-IC-0790 | Issue ICR- Instrument Cable Block Diagram | 19 | 0 | 2023-12-29 | 2024-01-26 | 29-Dec-23 A | 26-Jan-24 A
HE-IC-0800 | Receive Company Comments- Instrument Cable Block Diagram | 9 | 0 | 2024-01-29 | 2024-02-09 | 29-Jan-24 A | 09-Feb-24 A
HE-IC-0810 | Re-Issue for Approval- Instrument Cable Block Diagram | 16 | 0 | 2024-02-15 | 2024-03-08 | 15-Feb-24 A | 08-Mar-24 A
HE-IC-0820 | Obtain Company Approval- Instrument Cable Block Diagram | 6 | 0 | 2024-03-11 | 2024-03-20 | 11-Mar-24 A | 20-Mar-24 A
HE-IC-0830 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | 158 | 10 | 2024-03-21 | 2024-08-09 | 21-Mar-24 A | 2024-11-08 | 86
Instrument and F&G Cable Schedule |  | 67 | 0 | 2024-05-31 | 2024-08-02 | 31-May-24 A | 08-Sep-24 A
HE-IC-0910 | Issue ICR-Instrument and F&G Cable Schedule | 1 | 0 | 2024-05-31 | 2024-06-03 | 31-May-24 A | 03-Jun-24 A
HE-IC-0920 | Receive Company Comments-Instrument and F&G Cable Schedule | 3 | 0 | 2024-06-04 | 2024-06-07 | 04-Jun-24 A | 07-Jun-24 A
HE-IC-0940 | Obtain Company Approval-Instrument and F&G Cable Schedule | 2 | 0 | 2024-06-07 | 2024-06-11 | 07-Jun-24 A | 11-Jun-24 A
HE-IC-0930 | Re-Issue for Approval-Instrument and F&G Cable Schedule | 3 | 0 | 2024-06-11 | 2024-06-14 | 11-Jun-24 A | 14-Jun-24 A
HE-IC-0950 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | 55 | 0 | 2024-07-29 | 2024-08-02 | 21-Jun-24 A | 08-Sep-24 A
Instrument Trench Layout |  | 22 | 0 | 2024-05-01 | 2024-05-31 | 01-May-24 A | 31-May-24 A
HE-IC-0970 | Issue ICR-Instrument Trench Layout | 3 | 0 | 2024-05-01 | 2024-05-06 | 01-May-24 A | 06-May-24 A
HE-IC-0980 | Receive Company Comments-Instrument Trench Layout | 4 | 0 | 2024-05-07 | 2024-05-13 | 07-May-24 A | 13-May-24 A
HE-IC-1000 | Obtain Company Approval-Instrument Trench Layout | 2 | 0 | 2024-05-14 | 2024-05-16 | 14-May-24 A | 16-May-24 A
HE-IC-0990 | Re-Issue for Approval-Instrument Trench Layout | 2 | 0 | 2024-05-17 | 2024-05-21 | 17-May-24 A | 21-May-24 A
HE-IC-1010 | Final Issue for Design/ Construction-Instrument Trench Layout | 7 | 0 | 2024-05-22 | 2024-05-31 | 22-May-24 A | 31-May-24 A
HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT |  | 175 | 10 | 2024-02-26 | 2024-08-09 | 26-Feb-24 A | 2024-11-08 | 156
HE-IC-3390 | Issue ICR-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-IC-3400 | Receive Company Comments-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-IC-3410 | Re-Issue for Approval-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-IC-3420 | Obtain Company Approval-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-IC-3430 | Final Issue for Design/ Construction-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | 29 | 10 | 2024-07-29 | 2024-08-09 | 01-Oct-24 A | 2024-11-08 | 156
Data Sheet |  | 284 | 10 | 2023-09-22 | 2024-10-11 | 22-Sep-23 A | 2024-11-08 | 259
Datasheet for MOVs |  | 74 | 0 | 2023-09-23 | 2024-01-09 | 23-Sep-23 A | 09-Jan-24 A
HE-IC-1030 | Issue ICR- Datasheet for MOV | 4 | 0 | 2023-09-23 | 2023-09-29 | 23-Sep-23 A | 29-Sep-23 A
HE-IC-1040 | Receive Company Comments- Datasheet for MOV | 9 | 0 | 2023-09-30 | 2023-10-13 | 30-Sep-23 A | 13-Oct-23 A
HE-IC-1050 | Re-Issue for Approval- Datasheet for MOV | 5 | 0 | 2023-11-13 | 2023-11-20 | 13-Nov-23 A | 20-Nov-23 A
HE-IC-1060 | Obtain Company Approval- Datasheet for MOV | 24 | 0 | 2023-11-21 | 2023-12-26 | 21-Nov-23 A | 26-Dec-23 A
HE-IC-1070 | Final Issue for Design/ Construction-Actuator Datasheet for MOVs | 8 | 0 | 2023-12-27 | 2024-01-09 | 27-Dec-23 A | 09-Jan-24 A
Datasheet for GOV & ROV |  | 74 | 0 | 2023-09-23 | 2024-01-09 | 23-Sep-23 A | 09-Jan-24 A
HE-IC-1090 | Issue ICR- Datasheet for GOV & ROV | 4 | 0 | 2023-09-23 | 2023-09-29 | 23-Sep-23 A | 29-Sep-23 A
HE-IC-1100 | Receive Company Comments- Datasheet for GOV & ROV | 9 | 0 | 2023-09-30 | 2023-10-13 | 30-Sep-23 A | 13-Oct-23 A
HE-IC-1110 | Re-Issue for Approval- Datasheet for GOV & ROV | 5 | 0 | 2023-11-13 | 2023-11-20 | 13-Nov-23 A | 20-Nov-23 A
HE-IC-1120 | Obtain Company Approval- Datasheet for GOV & ROV | 8 | 0 | 2023-11-24 | 2023-12-07 | 24-Nov-23 A | 07-Dec-23 A
HE-IC-1130 | Final Issue for Design/ Construction-Actuator Datasheet for GOV & ROV | 10 | 0 | 2023-12-24 | 2024-01-09 | 24-Dec-23 A | 09-Jan-24 A
Datasheets for Custody Flow Metering Skid |  | 273 | 5 | 2023-10-02 | 2024-08-02 | 02-Oct-23 A | 2024-11-01 | 153
HE-IC-1150 | Issue ICR- Datasheets for Metering Skid | 15 | 0 | 2023-10-02 | 2023-10-23 | 02-Oct-23 A | 23-Oct-23 A
HE-IC-1160 | Receive Company Comments- Datasheets for Metering Skid | 6 | 0 | 2023-11-16 | 2023-11-24 | 16-Nov-23 A | 24-Nov-23 A
HE-IC-1170 | Re-Issue for Approval- Datasheets for Metering Skid | 3 | 0 | 2023-11-22 | 2023-11-25 | 22-Nov-23 A | 25-Nov-23 A
HE-IC-1180 | Obtain Company Approval- Datasheets for Metering Skid | 5 | 0 | 2023-11-27 | 2023-12-05 | 27-Nov-23 A | 05-Dec-23 A
HE-IC-1190 | Final Issue for Design/ Construction-Datasheets for Custody Flow Metering Skid | 227 | 5 | 2023-12-06 | 2024-08-02 | 06-Dec-23 A | 2024-11-01 | 153
Data sheet for Pressure Reduction System |  | 254 | 0 | 2023-10-02 | 2024-08-02 | 02-Oct-23 A | 07-Oct-24 A
HE-IC-1210 | Issue ICR- Data sheet for PRS (Pressure Reduction System) | 15 | 0 | 2023-10-02 | 2023-10-23 | 02-Oct-23 A | 23-Oct-23 A
HE-IC-1220 | Receive Company Comments- Data sheet for PRS (Pressure Reduction System) | 2 | 0 | 2023-10-24 | 2023-10-26 | 24-Oct-23 A | 26-Oct-23 A
HE-IC-1230 | Re-Issue for Approval- Data sheet for PRS (Pressure Reduction System) | 9 | 0 | 2023-11-14 | 2023-11-27 | 14-Nov-23 A | 27-Nov-23 A
HE-IC-1240 | Obtain Company Approval- Data sheet for PRS (Pressure Reduction System) | 4 | 0 | 2023-11-28 | 2023-12-05 | 28-Nov-23 A | 05-Dec-23 A
HE-IC-1250 | Final Issue for Design/ Construction-Data sheet for PRS (Pressure Reduction System) | 208 | 0 | 2023-12-06 | 2024-08-02 | 06-Dec-23 A | 07-Oct-24 A
Datasheets for PSV & Orifics (incl. RO) |  | 248 | 5 | 2023-11-13 | 2024-08-16 | 13-Nov-23 A | 2024-11-08 | 156
HE-IC-1330 | Issue ICR- Datasheets for PSV & Orifice (incl. RO) | 9 | 0 | 2023-11-13 | 2023-11-24 | 13-Nov-23 A | 24-Nov-23 A
HE-IC-1340 | Receive Company Comments- Datasheets for PSV & Orifice (incl. RO) | 12 | 0 | 2023-12-21 | 2024-01-09 | 21-Dec-23 A | 09-Jan-24 A
HE-IC-1350 | Re-Issue for Approval- Datasheets for PSV & Orifice (incl. RO) | 7 | 0 | 2024-01-10 | 2024-01-19 | 10-Jan-24 A | 19-Jan-24 A
HE-IC-1360 | Obtain Company Approval- Datasheets for PSV & Orifice (incl. RO) | 0 | 0 | 2024-01-19 | 2024-01-19 | 19-Jan-24 A | 19-Jan-24 A
HE-IC-1370 | Final Issue for Design/ Construction-Datasheets for PSV & Orifice (incl. RO) | 29 | 5 | 2024-08-12 | 2024-08-16 | 01-Oct-24 A | 2024-11-08 | 156
Datasheets for PASSIVE COOLED SHELTER |  | 66 | 0 | 2023-11-29 | 2024-03-04 | 29-Nov-23 A | 04-Mar-24 A
HE-IC-3300 | Issue ICR- Datasheets for PASSIVE COOLED SHELTER | 9 | 0 | 2023-11-29 | 2023-12-13 | 29-Nov-23 A | 13-Dec-23 A
HE-IC-3310 | Receive Company Comments- Datasheets for PASSIVE COOLED SHELTER | 9 | 0 | 2023-12-14 | 2023-12-27 | 14-Dec-23 A | 27-Dec-23 A
HE-IC-3320 | Re-Issue for Approval- Datasheets for PASSIVE COOLED SHELTER | 13 | 0 | 2023-12-28 | 2024-01-17 | 28-Dec-23 A | 17-Jan-24 A
HE-IC-3330 | Obtain Company Approval- Datasheets for PASSIVE COOLED SHELTER | 2 | 0 | 2024-01-17 | 2024-01-19 | 17-Jan-24 A | 19-Jan-24 A
HE-IC-3290 | Final Issue for Design/ Construction-Datasheets for PASSIVE COOLED SHELTER | 21 | 0 | 2024-02-02 | 2024-03-04 | 02-Feb-24 A | 04-Mar-24 A
Data Sheet - Mainline Ball Valve |  | 187 | 0 | 2023-09-22 | 2024-08-16 | 22-Sep-23 A | 25-Jun-24 A
HE-PL-1210 | Issue ICR - Data Sheet - Mainline Ball Valve | 5 | 0 | 2023-09-22 | 2023-09-29 | 22-Sep-23 A | 29-Sep-23 A
HE-PL-1220 | Receive Company Comments - Data Sheet - Mainline Ball Valve | 8 | 0 | 2023-09-29 | 2023-10-11 | 29-Sep-23 A | 11-Oct-23 A
HE-PL-1230 | Re-Issue for Approval - Data Sheet - Mainline Ball Valve | 11 | 0 | 2023-10-12 | 2023-10-27 | 12-Oct-23 A | 27-Oct-23 A
HE-PL-1240 | Obtain Company Approval - Data Sheet - Mainline Ball Valve | 5 | 0 | 2023-10-27 | 2023-11-03 | 27-Oct-23 A | 03-Nov-23 A
HE-PL-1250 | Final Issue for Design/ Construction-Data Sheet - Mainline Ball Valve | 16 | 0 | 2024-07-29 | 2024-08-16 | 30-May-24 A | 25-Jun-24 A
Datasheets for Pig Signallers |  | 177 | 0 | 2023-11-08 | 2024-08-16 | 08-Nov-23 A | 29-Jul-24 A
HE-IC-1390 | Issue ICR-Datasheets for Pig Signalers | 12 | 0 | 2023-11-08 | 2023-11-24 | 08-Nov-23 A | 24-Nov-23 A
HE-IC-1400 | Receive Company Comments-Datasheets for Pig Signalers | 7 | 0 | 2023-11-25 | 2023-12-07 | 25-Nov-23 A | 07-Dec-23 A
HE-IC-1410 | Re-Issue for Approval-Datasheets for Pig Signalers | 5 | 0 | 2023-12-08 | 2023-12-15 | 08-Dec-23 A | 15-Dec-23 A
HE-IC-1420 | Obtain Company Approval-Datasheets for Pig Signalers | 1 | 0 | 2023-12-16 | 2023-12-19 | 16-Dec-23 A | 19-Dec-23 A
HE-IC-1430 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | 145 | 0 | 2023-12-24 | 2024-08-16 | 24-Dec-23 A | 29-Jul-24 A
Datasheets for Field Instruments |  | 189 | 0 | 2024-01-02 | 2024-08-09 | 02-Jan-24 A | 04-Oct-24 A
HE-IC-1450 | Issue ICR-Datasheets for Field Instruments / H2S Analyzers | 4 | 0 | 2024-01-02 | 2024-01-08 | 02-Jan-24 A | 08-Jan-24 A
HE-IC-1460 | Receive Company Comments-Datasheets for Field Instruments / H2S Analyzers | 1 | 0 | 2024-01-19 | 2024-01-22 | 19-Jan-24 A | 22-Jan-24 A
HE-IC-1470 | Re-Issue for Approval-Datasheets for Field Instruments / H2S Analyzers | 4 | 0 | 2024-02-26 | 2024-03-01 | 26-Feb-24 A | 01-Mar-24 A
HE-IC-1480 | Obtain Company Approval-Datasheets for Field Instruments / H2S Analyzers | 9 | 0 | 2024-03-04 | 2024-03-17 | 04-Mar-24 A | 17-Mar-24 A
HE-IC-1490 | Final Issue for Design/ Construction-Datasheets for Field Instruments / H2S Analyzers | 5 | 0 | 2024-07-29 | 2024-08-09 | 30-Sep-24 A | 04-Oct-24 A
Datasheets for Fire and Gas Devices |  | 170 | 0 | 2024-01-29 | 2024-10-11 | 29-Jan-24 A | 04-Oct-24 A
HE-IC-1510 | Issue ICR- Datasheets for F&G Devices | 5 | 0 | 2024-01-29 | 2024-02-03 | 29-Jan-24 A | 03-Feb-24 A
HE-IC-1520 | Receive Company Comments- Datasheets for F&G Devices | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-IC-1530 | Re-Issue for Approval- Datasheets for F&G Devices | 8 | 0 | 2024-05-24 | 2024-06-05 | 24-May-24 A | 05-Jun-24 A
HE-IC-1540 | Obtain Company Approval- Datasheets for F&G Devices | 2 | 0 | 2024-06-05 | 2024-06-07 | 05-Jun-24 A | 07-Jun-24 A
HE-IC-1550 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | 5 | 0 | 2024-10-07 | 2024-10-11 | 30-Sep-24 A | 04-Oct-24 A
Material Requisitions |  | 263 | 5 | 2023-10-15 | 2024-08-30 | 15-Oct-23 A | 2024-11-01 | 264
Material Requisitions for MOV |  | 130 | 0 | 2023-10-15 | 2024-04-25 | 15-Oct-23 A | 25-Apr-24 A
HE-IC-1570 | Issue ICR- Material Requisitions for MOV | 6 | 0 | 2023-10-15 | 2023-10-24 | 15-Oct-23 A | 24-Oct-23 A
HE-IC-1580 | Receive Company Comments- Material Requisitions for MOV | 2 | 0 | 2023-10-25 | 2023-10-27 | 25-Oct-23 A | 27-Oct-23 A
HE-IC-1590 | Re-Issue for Approval- Material Requisitions for MOV | 0 | 0 | 2024-01-18 | 2024-01-18 | 18-Jan-24 A | 18-Jan-24 A
HE-IC-1600 | Obtain Company Approval- Material Requisitions for MOV | 0 | 0 | 2024-01-18 | 2024-01-18 | 18-Jan-24 A | 18-Jan-24 A
HE-IC-1610 | Final Issue for Design/ Construction-Material Requisitions for MOV | 64 | 0 | 2024-01-18 | 2024-04-25 | 18-Jan-24 A | 25-Apr-24 A
Material Requisitions for ROV/ GOV |  | 125 | 0 | 2023-10-15 | 2024-04-18 | 15-Oct-23 A | 18-Apr-24 A
HE-IC-1630 | Issue ICR- Material Requisitions for ROV/ GOV | 6 | 0 | 2023-10-15 | 2023-10-24 | 15-Oct-23 A | 24-Oct-23 A
HE-IC-1640 | Receive Company Comments- Material Requisitions for ROV/ GOV | 1 | 0 | 2023-10-25 | 2023-10-26 | 25-Oct-23 A | 26-Oct-23 A
HE-IC-1650 | Re-Issue for Approval- Material Requisitions for ROV/ GOV | 0 | 0 | 2024-02-26 | 2024-02-26 | 26-Feb-24 A | 26-Feb-24 A
HE-IC-1660 | Obtain Company Approval- Material Requisitions for ROV/ GOV | 0 | 0 | 2024-02-26 | 2024-02-26 | 26-Feb-24 A | 26-Feb-24 A
HE-IC-1670 | Final Issue for Design/ Construction-Material Requisitions for ROV/ GOV | 9 | 0 | 2024-03-31 | 2024-04-18 | 31-Mar-24 A | 18-Apr-24 A
Material Requisition for Manual Ball Valves |  | 205 | 0 | 2023-11-17 | 2024-08-30 | 17-Nov-23 A | 16-Sep-24 A
HE-PL-1690 | Issue ICR - MR for Mainline Ball Valve | 7 | 0 | 2023-11-17 | 2023-11-28 | 17-Nov-23 A | 28-Nov-23 A
HE-PL-1700 | Receive Company Comments - MR for Mainline Ball Valve | 2 | 0 | 2023-11-29 | 2023-12-01 | 29-Nov-23 A | 01-Dec-23 A
HE-PL-1710 | Re-Issue for Approval - MR for Mainline Ball Valve | 11 | 0 | 2024-02-01 | 2024-02-16 | 01-Feb-24 A | 16-Feb-24 A
HE-PL-1720 | Obtain Company Approval - MR for Mainline Ball Valve | 5 | 0 | 2024-02-16 | 2024-02-23 | 16-Feb-24 A | 23-Feb-24 A
HE-PL-1730 | Final Issue for Design/ Construction-Material Requisition for Manual Ball Valves | 11 | 0 | 2024-08-19 | 2024-08-30 | 02-Sep-24 A | 16-Sep-24 A
Material Requisitions for PRS (Pressure Reduction Skid) |  | 263 | 5 | 2023-10-15 | 2024-08-02 | 15-Oct-23 A | 2024-11-01 | 256
HE-IC-1690 | Issue ICR-Material Requisitions for PRS | 6 | 0 | 2023-10-15 | 2023-10-24 | 15-Oct-23 A | 24-Oct-23 A
HE-IC-1700 | Receive Company Comments-Material Requisitions for PRS | 6 | 0 | 2023-11-14 | 2023-11-22 | 14-Nov-23 A | 22-Nov-23 A
HE-IC-1710 | Re-Issue for Approval-Material Requisitions for PRS | 73 | 0 | 2023-11-23 | 2024-03-07 | 23-Nov-23 A | 07-Mar-24 A
HE-IC-1720 | Obtain Company Approval-Material Requisitions for PRS | 4 | 0 | 2024-03-01 | 2024-03-07 | 01-Mar-24 A | 07-Mar-24 A
HE-IC-1730 | Final Issue for Design/ Construction-Material Requisitions for PRS | 178 | 5 | 2024-02-14 | 2024-08-02 | 14-Feb-24 A | 2024-11-01 | 256
Material Requisitions for Leak Detection System |  | 204 | 0 | 2023-11-20 | 2024-08-02 | 20-Nov-23 A | 16-Sep-24 A
HE-IC-1750 | Issue ICR-Material Requisitions for Leak Detection System | 18 | 0 | 2023-11-20 | 2023-12-15 | 20-Nov-23 A | 15-Dec-23 A
HE-IC-1760 | Receive Company Comments-Material Requisitions for Leak Detection System | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-IC-1770 | Re-Issue for Approval-Material Requisitions for Leak Detection System | 4 | 0 | 2024-03-10 | 2024-03-17 | 10-Mar-24 A | 17-Mar-24 A
HE-IC-1780 | Obtain Company Approval-Material Requisitions for Leak Detection System | 6 | 0 | 2024-03-18 | 2024-03-28 | 18-Mar-24 A | 28-Mar-24 A
HE-IC-1790 | Final Issue for Design/ Construction-Material Requisitions for Leak Detection System | 90 | 0 | 2024-05-08 | 2024-08-02 | 08-May-24 A | 16-Sep-24 A
Material Requisitions for Metering Skid |  | 243 | 5 | 2023-11-13 | 2024-08-02 | 13-Nov-23 A | 2024-11-01 | 256
HE-IC-1810 | Issue ICR- Material Requisitions for Metering Skid | 4 | 0 | 2023-11-13 | 2023-11-17 | 13-Nov-23 A | 17-Nov-23 A
HE-IC-1820 | Receive Company Comments- Material Requisitions for Metering Skid | 18 | 0 | 2023-11-20 | 2023-12-15 | 20-Nov-23 A | 15-Dec-23 A
HE-IC-1830 | Re-Issue for Approval- Material Requisitions for Metering Skid | 42 | 0 | 2023-11-14 | 2024-01-15 | 14-Nov-23 A | 15-Jan-24 A
HE-IC-1840 | Obtain Company Approval- Material Requisitions for Metering Skid | 7 | 0 | 2024-01-16 | 2024-01-25 | 16-Jan-24 A | 25-Jan-24 A
HE-IC-1850 | Final Issue for Design/ Construction-Material Requisitions for Metering Skid | 191 | 5 | 2024-01-26 | 2024-08-02 | 26-Jan-24 A | 2024-11-01 | 256
Material Requisitions for Fire & Gas Detectors |  | 189 | 5 | 2024-01-30 | 2024-08-02 | 30-Jan-24 A | 2024-11-01 | 256
HE-IC-1870 | Issue ICR- Material Requisitions for Gas Detectors | 3 | 0 | 2024-01-30 | 2024-02-02 | 30-Jan-24 A | 02-Feb-24 A
HE-IC-1880 | Receive Company Comments- Material Requisitions for Gas Detectors | 20 | 0 | 2024-03-08 | 2024-04-15 | 08-Mar-24 A | 15-Apr-24 A
HE-IC-1890 | Re-Issue for Approval- Material Requisitions for Gas Detectors | 5 | 0 | 2024-06-03 | 2024-06-10 | 03-Jun-24 A | 10-Jun-24 A
HE-IC-1900 | Obtain Company Approval- Material Requisitions for Gas Detectors | 3 | 0 | 2024-06-11 | 2024-06-14 | 11-Jun-24 A | 14-Jun-24 A
HE-IC-1910 | Final Issue for Design/ Construction-Material Requisitions for Gas Detectors | 5 | 5 | 2024-07-29 | 2024-08-02 | 2024-10-28 | 2024-11-01 | 256
Material Requisition for Pig Signaler |  | 108 | 0 | 2024-02-26 | 2024-08-16 | 26-Feb-24 A | 07-Aug-24 A
HE-PL-1930 | Issue ICR- Material Requisition for Pig Signaler | 5 | 0 | 2024-02-26 | 2024-03-04 | 26-Feb-24 A | 04-Mar-24 A
HE-PL-1940 | Receive Company Comments- Material Requisition for Pig Signaler | 10 | 0 | 2024-03-05 | 2024-03-19 | 05-Mar-24 A | 19-Mar-24 A
HE-PL-1950 | Re-Issue for Approval- Material Requisition for Pig Signaler | 25 | 0 | 2024-03-19 | 2024-05-01 | 19-Mar-24 A | 01-May-24 A
HE-PL-1960 | Obtain Company Approval- Material Requisition for Pig Signaler | 3 | 0 | 2024-05-02 | 2024-05-07 | 02-May-24 A | 07-May-24 A
HE-PL-1970 | Final Issue for Design/ Construction-Material Requisition for Pig Signaler | 39 | 0 | 2024-06-10 | 2024-08-16 | 10-Jun-24 A | 07-Aug-24 A
Material Requisition for Active/ Passive Shelters |  | 136 | 0 | 2024-01-08 | 2024-08-02 | 08-Jan-24 A | 29-Jul-24 A
HE-EL-0850 | Issue ICR - Material Requisition for Active / Passive Shelters | 14 | 0 | 2024-01-08 | 2024-01-26 | 08-Jan-24 A | 26-Jan-24 A
HE-EL-0860 | Receive Company Comments - Material Requisition for Active / Passive Shelters | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-EL-0870 | Re-Issue for Approval - Material Requisition for Active / Passive Shelters | 9 | 0 | 2024-03-10 | 2024-03-25 | 10-Mar-24 A | 25-Mar-24 A
HE-EL-0880 | Obtain Company Approval - Material Requisition for Active / Passive Shelters | 39 | 0 | 2024-03-26 | 2024-05-25 | 26-Mar-24 A | 25-May-24 A
HE-EL-0890 | Final Issue for Design/ Construction-Material Requisition for Active/ Passive Shelters | 42 | 0 | 2024-05-27 | 2024-08-02 | 27-May-24 A | 29-Jul-24 A
Material Requisitions for Field Instruments / H2S Analyzers |  | 85 | 0 | 2024-01-29 | 2024-06-04 | 29-Jan-24 A | 04-Jun-24 A
HE-IC-1930 | Issue ICR- Material Requisitions for Field Instruments / H2S Analyzers | 4 | 0 | 2024-01-29 | 2024-02-02 | 29-Jan-24 A | 02-Feb-24 A
HE-IC-1940 | Receive Company Comments- Material Requisitions for Field Instruments / H2S Analyzers | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-IC-1950 | Re-Issue for Approval- Material Requisitions for Field Instruments / H2S Analyzers | 41 | 0 | 2024-03-10 | 2024-05-15 | 10-Mar-24 A | 15-May-24 A
HE-IC-1960 | Obtain Company Approval- Material Requisitions for Field Instruments / H2S Analyzers | 6 | 0 | 2024-05-16 | 2024-05-24 | 16-May-24 A | 24-May-24 A
HE-IC-1970 | Final Issue for Design/ Construction-Material Requisitions for Field Instruments / H2S Analyzers | 7 | 0 | 2024-05-24 | 2024-06-04 | 24-May-24 A | 04-Jun-24 A
Material Requisitions for Junction Boxes |  | 112 | 0 | 2024-04-30 | 2024-08-30 | 30-Apr-24 A | 08-Oct-24 A
HE-IC-1990 | Issue ICR- Material Requisitions for Junction Boxes | 12 | 0 | 2024-04-30 | 2024-05-16 | 30-Apr-24 A | 16-May-24 A
HE-IC-2000 | Receive Company Comments- Material Requisitions for Junction Boxes | 11 | 0 | 2024-05-17 | 2024-06-03 | 17-May-24 A | 03-Jun-24 A
HE-IC-2010 | Re-Issue for Approval- Material Requisitions for Junction Boxes | 61 | 0 | 2024-06-04 | 2024-08-09 | 04-Jun-24 A | 02-Sep-24 A
HE-IC-2020 | Obtain Company Approval- Material Requisitions for Junction Boxes | 10 | 0 | 2024-08-12 | 2024-08-23 | 03-Sep-24 A | 16-Sep-24 A
HE-IC-2030 | Final Issue for Design/ Construction-Material Requisitions for Junction Boxes | 7 | 0 | 2024-08-26 | 2024-08-30 | 30-Sep-24 A | 08-Oct-24 A
Material Requisitions for Instrument Cables |  | 76 | 0 | 2024-05-08 | 2024-08-23 | 08-May-24 A | 27-Aug-24 A
HE-IC-3030 | Issue ICR- Material Requisitions for Instrument Cables | 15 | 0 | 2024-05-08 | 2024-05-29 | 08-May-24 A | 29-May-24 A
HE-IC-2990 | Receive Company Comments- Material Requisitions for Instrument Cables | 10 | 0 | 2024-05-30 | 2024-06-13 | 30-May-24 A | 13-Jun-24 A
HE-IC-3000 | Re-Issue for Approval- Material Requisitions for Instrument Cables | 42 | 0 | 2024-06-14 | 2024-08-02 | 14-Jun-24 A | 17-Aug-24 A
HE-IC-3020 | Obtain Company Approval- Material Requisitions for Instrument Cables | 2 | 0 | 2024-08-05 | 2024-08-16 | 19-Aug-24 A | 20-Aug-24 A
HE-IC-3010 | Final Issue for Design/ Construction-Material Requisitions for Instrument Cables | 5 | 0 | 2024-08-19 | 2024-08-23 | 21-Aug-24 A | 27-Aug-24 A
Material Requisitions for RTU & SCADA Modification |  | 133 | 0 | 2024-01-29 | 2024-08-02 | 29-Jan-24 A | 14-Aug-24 A
HE-IC-2880 | Issue ICR- Material Requisitions for RTU & SCADA Modification | 4 | 0 | 2024-01-29 | 2024-02-02 | 29-Jan-24 A | 02-Feb-24 A
HE-IC-2840 | Receive Company Comments- Material Requisitions for RTU & SCADA Modification | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-IC-2850 | Re-Issue for Approval- Material Requisitions for RTU & SCADA Modification | 16 | 0 | 2024-03-10 | 2024-04-05 | 10-Mar-24 A | 05-Apr-24 A
HE-IC-2870 | Obtain Company Approval- Material Requisitions for RTU & SCADA Modification | 0 | 0 | 2024-04-08 | 2024-04-12 | 08-Apr-24 A | 12-Apr-24 A
HE-IC-2860 | Final Issue for Design/ Construction-Material Requisitions for RTU & SCADA Modification | 35 | 0 | 2024-07-29 | 2024-08-02 | 26-Jun-24 A | 14-Aug-24 A
TBE |  | 253 | 15 | 2023-11-11 | 2024-10-11 | 11-Nov-23 A | 2024-11-15 | 254
TBE for MOV |  | 110 | 0 | 2023-11-11 | 2024-04-25 | 11-Nov-23 A | 25-Apr-24 A
HE-IC-2050 | Issue ICR- TBE for MOV | 47 | 0 | 2023-11-11 | 2024-01-19 | 11-Nov-23 A | 19-Jan-24 A
HE-IC-2060 | Receive Company Comments- TBE for MOV | 5 | 0 | 2024-01-19 | 2024-01-26 | 19-Jan-24 A | 26-Jan-24 A
HE-IC-2070 | Re-Issue for Approval- TBE for MOV | 18 | 0 | 2024-02-26 | 2024-03-22 | 26-Feb-24 A | 22-Mar-24 A
HE-IC-2080 | Obtain Company Approval- TBE for MOV | 4 | 0 | 2024-03-22 | 2024-03-28 | 22-Mar-24 A | 28-Mar-24 A
HE-IC-2090 | Final Issue for Design/ Construction-TBE for MOV | 9 | 0 | 2024-04-10 | 2024-04-25 | 10-Apr-24 A | 25-Apr-24 A
TBE for Mainline Ball Valve |  | 216 | 5 | 2024-01-05 | 2024-08-16 | 05-Jan-24 A | 2024-11-15 | 254
HE-PL-2270 | Issue ICR - TBE for Mainline Ball Valve | 4 | 0 | 2024-01-05 | 2024-01-11 | 05-Jan-24 A | 11-Jan-24 A
HE-PL-2280 | Receive Company Comments - TBE for Mainline Ball Valve | 36 | 0 | 2024-01-12 | 2024-03-04 | 12-Jan-24 A | 04-Mar-24 A
HE-PL-2290 | Re-Issue for Approval - TBE for Mainline Ball Valve | 27 | 0 | 2024-03-05 | 2024-04-19 | 05-Mar-24 A | 19-Apr-24 A
HE-PL-2300 | Obtain Company Approval - TBE for Mainline Ball Valve | 6 | 0 | 2024-04-20 | 2024-04-30 | 20-Apr-24 A | 30-Apr-24 A
HE-PL-2310 | Final Issue for Design/ Construction-TBE for Mainline Ball Valve | 77 | 5 | 2024-08-12 | 2024-08-16 | 01-Aug-24 A | 2024-11-15 | 254
TBE for Metering Skid |  | 103 | 0 | 2023-11-23 | 2024-04-26 | 23-Nov-23 A | 26-Apr-24 A
HE-IC-2110 | Issue ICR-TBE for Metering Skid | 44 | 0 | 2023-11-23 | 2024-01-26 | 23-Nov-23 A | 26-Jan-24 A
HE-IC-2120 | Receive Company Comments-TBE for Metering Skid | 9 | 0 | 2024-03-31 | 2024-04-18 | 31-Mar-24 A | 18-Apr-24 A
HE-IC-2130 | Re-Issue for Approval-TBE for Metering Skid | 5 | 0 | 2024-04-19 | 2024-04-26 | 19-Apr-24 A | 26-Apr-24 A
HE-IC-2140 | Obtain Company Approval-TBE for Metering Skid | 5 | 0 | 2024-04-19 | 2024-04-26 | 19-Apr-24 A | 26-Apr-24 A
HE-IC-2150 | Final Issue for Design/ Construction-TBE for Metering Skid | 5 | 0 | 2024-04-19 | 2024-04-26 | 19-Apr-24 A | 26-Apr-24 A
TBE for PRS (Pressure Reduction Skid) |  | 108 | 0 | 2023-11-16 | 2024-04-26 | 16-Nov-23 A | 26-Apr-24 A
HE-IC-2170 | Issue ICR-TBE for PRS | 37 | 0 | 2023-11-16 | 2024-01-10 | 16-Nov-23 A | 10-Jan-24 A
HE-IC-2180 | Receive Company Comments-TBE for PRS | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-IC-2190 | Re-Issue for Approval-TBE for PRS | 5 | 0 | 2024-04-19 | 2024-04-26 | 19-Apr-24 A | 26-Apr-24 A
HE-IC-2200 | Obtain Company Approval-TBE for PRS | 5 | 0 | 2024-04-19 | 2024-04-26 | 19-Apr-24 A | 26-Apr-24 A
HE-IC-2210 | Final Issue for Design/ Construction-TBE for PRS | 5 | 0 | 2024-04-19 | 2024-04-26 | 19-Apr-24 A | 26-Apr-24 A
TBE for Leak Detection System |  | 126 | 0 | 2024-02-26 | 2024-08-23 | 26-Feb-24 A | 02-Sep-24 A
HE-IC-2230 | Issue ICR-TBE for Leak Detection System | 13 | 0 | 2024-02-26 | 2024-03-14 | 26-Feb-24 A | 14-Mar-24 A
HE-IC-2240 | Receive Company Comments-TBE for Leak Detection System | 8 | 0 | 2024-03-15 | 2024-03-28 | 15-Mar-24 A | 28-Mar-24 A
HE-IC-2250 | Re-Issue for Approval-TBE for Leak Detection System | 42 | 0 | 2024-03-27 | 2024-05-31 | 27-Mar-24 A | 31-May-24 A
HE-IC-2260 | Obtain Company Approval-TBE for Leak Detection System | 16 | 0 | 2024-06-03 | 2024-08-09 | 03-Jun-24 A | 27-Jun-24 A
HE-IC-2270 | Final Issue for Design/ Construction-TBE for Leak Detection System | 15 | 0 | 2024-08-12 | 2024-08-23 | 13-Aug-24 A | 02-Sep-24 A
TBE for ROV/ GOV |  | 105 | 0 | 2023-11-11 | 2024-04-18 | 11-Nov-23 A | 18-Apr-24 A
HE-IC-2290 | Issue ICR- TBE for ROV/ GOV | 42 | 0 | 2023-11-11 | 2024-01-12 | 11-Nov-23 A | 12-Jan-24 A
HE-IC-2300 | Receive Company Comments- TBE for ROV/ GOV | 2 | 0 | 2024-02-14 | 2024-02-16 | 14-Feb-24 A | 16-Feb-24 A
HE-IC-2310 | Re-Issue for Approval- TBE for ROV/ GOV | 4 | 0 | 2024-02-26 | 2024-03-01 | 26-Feb-24 A | 01-Mar-24 A
HE-IC-2320 | Obtain Company Approval- TBE for ROV/ GOV | 9 | 0 | 2024-03-04 | 2024-03-17 | 04-Mar-24 A | 17-Mar-24 A
HE-IC-2330 | Final Issue for Design/ Construction-TBE for ROV/ GOV | 9 | 0 | 2024-03-31 | 2024-04-18 | 31-Mar-24 A | 18-Apr-24 A
TBE for Junction Boxes |  | 62 | 10 | 2024-07-29 | 2024-09-20 | 15-Aug-24 A | 2024-11-08 | 81
HE-IC-2470 | Issue ICR- TBE for Junction Boxes | 10 | 0 | 2024-07-29 | 2024-08-09 | 15-Aug-24 A | 28-Aug-24 A
HE-IC-2480 | Receive Company Comments- TBE for Junction Boxes | 9 | 0 | 2024-08-12 | 2024-08-23 | 02-Sep-24 A | 12-Sep-24 A
HE-IC-2490 | Re-Issue for Approval- TBE for Junction Boxes | 10 | 0 | 2024-08-26 | 2024-08-30 | 07-Oct-24 A | 18-Oct-24 A
HE-IC-2510 | Final Issue for Design/ Construction-TBE for Junction Boxes | 5 | 5 | 2024-09-16 | 2024-09-20 | 2024-11-04 | 2024-11-08 | 81
HE-IC-2500 | Obtain Company Approval- TBE for Junction Boxes | 16 | 10 | 2024-09-02 | 2024-09-13 | 18-Oct-24 A | 2024-11-08 | 81
TBE for Fire & Gas Detectors |  | 112 | 5 | 2024-05-24 | 2024-08-30 | 24-May-24 A | 2024-11-01 | 86
HE-IC-2350 | Issue ICR- TBE for Gas Detectors | 4 | 0 | 2024-05-24 | 2024-05-30 | 24-May-24 A | 30-May-24 A
HE-IC-2360 | Receive Company Comments- TBE for Gas Detectors | 12 | 0 | 2024-05-31 | 2024-06-21 | 31-May-24 A | 21-Jun-24 A
HE-IC-2370 | Re-Issue for Approval- TBE for Gas Detectors | 9 | 0 | 2024-06-22 | 2024-08-09 | 22-Jun-24 A | 04-Jul-24 A
HE-IC-2380 | Obtain Company Approval- TBE for Gas Detectors | 10 | 0 | 2024-08-12 | 2024-08-23 | 05-Jul-24 A | 19-Jul-24 A
HE-IC-2390 | Final Issue for Design/ Construction-TBE for Gas Detectors | 75 | 5 | 2024-08-26 | 2024-08-30 | 20-Jul-24 A | 2024-11-01 | 86
TBE for Instrument Cables |  | 88 | 10 | 2024-07-29 | 2024-10-11 | 10-Jul-24 A | 2024-11-08 | 86
HE-IC-3050 | Issue ICR- TBE for Instrument Cables | 10 | 0 | 2024-07-29 | 2024-08-16 | 10-Jul-24 A | 23-Jul-24 A
HE-IC-3060 | Receive Company Comments- TBE for Instrument Cables | 15 | 0 | 2024-08-19 | 2024-08-30 | 24-Jul-24 A | 13-Aug-24 A
HE-IC-3070 | Re-Issue for Approval- TBE for Instrument Cables | 7 | 0 | 2024-09-02 | 2024-09-13 | 30-Sep-24 A | 09-Oct-24 A
HE-IC-3080 | Obtain Company Approval- TBE for Instrument Cables | 7 | 0 | 2024-09-16 | 2024-09-27 | 10-Oct-24 A | 18-Oct-24 A
HE-IC-3040 | Final Issue for Design/ Construction-TBE for Instrument Cables | 12 | 10 | 2024-09-30 | 2024-10-11 | 24-Oct-24 A | 2024-11-08 | 86
TBE for Field Instruments / H2S Analyzers |  | 119 | 0 | 2024-04-07 | 2024-08-02 | 07-Apr-24 A | 01-Oct-24 A
HE-IC-2410 | Issue ICR- TBE for Field Instruments / H2S Analyzers | 1 | 0 | 2024-04-07 | 2024-04-12 | 07-Apr-24 A | 12-Apr-24 A
HE-IC-2420 | Receive Company Comments- TBE for Field Instruments / H2S Analyzers | 23 | 0 | 2024-04-13 | 2024-05-16 | 13-Apr-24 A | 16-May-24 A
HE-IC-2430 | Re-Issue for Approval- TBE for Field Instruments / H2S Analyzers | 10 | 0 | 2024-05-17 | 2024-05-31 | 17-May-24 A | 31-May-24 A
HE-IC-2440 | Obtain Company Approval- TBE for Field Instruments / H2S Analyzers | 9 | 0 | 2024-06-03 | 2024-06-14 | 03-Jun-24 A | 14-Jun-24 A
HE-IC-2450 | Final Issue for Design/ Construction-TBE for Field Instruments / H2S Analyzers | 72 | 0 | 2024-06-15 | 2024-08-02 | 15-Jun-24 A | 01-Oct-24 A
TBE for Pig Signaler |  | 130 | 5 | 2024-04-30 | 2024-08-16 | 30-Apr-24 A | 2024-11-01 | 264
HE-PL-2330 | Issue ICR- TBE for Pig Signaler | 8 | 0 | 2024-05-03 | 2024-05-15 | 03-May-24 A | 15-May-24 A
HE-PL-2340 | Receive Company Comments- TBE for Pig Signaler | 12 | 0 | 2024-04-30 | 2024-05-16 | 30-Apr-24 A | 16-May-24 A
HE-PL-2350 | Re-Issue for Approval- TBE for Pig Signaler | 13 | 0 | 2024-05-17 | 2024-06-05 | 17-May-24 A | 05-Jun-24 A
HE-PL-2360 | Obtain Company Approval- TBE for Pig Signaler | 8 | 0 | 2024-06-06 | 2024-06-21 | 06-Jun-24 A | 21-Jun-24 A
HE-PL-2370 | Final Issue for Design/ Construction-TBE for Pig Signaler | 94 | 5 | 2024-06-22 | 2024-08-16 | 22-Jun-24 A | 2024-11-01 | 264
TBE for RTU & SCADA Modification |  | 121 | 5 | 2024-05-13 | 2024-08-16 | 13-May-24 A | 2024-11-01 | 153
HE-IC-2900 | Issue ICR- TBE for RTU & SCADA Modification | 5 | 0 | 2024-05-13 | 2024-05-20 | 13-May-24 A | 20-May-24 A
HE-IC-2910 | Receive Company Comments- TBE for RTU & SCADA Modification | 14 | 0 | 2024-05-21 | 2024-06-10 | 21-May-24 A | 10-Jun-24 A
HE-IC-2920 | Re-Issue for Approval- TBE for RTU & SCADA Modification | 3 | 0 | 2024-06-11 | 2024-06-14 | 11-Jun-24 A | 14-Jun-24 A
HE-IC-2930 | Obtain Company Approval- TBE for RTU & SCADA Modification | 7 | 0 | 2024-07-29 | 2024-08-09 | 17-Jun-24 A | 28-Jun-24 A
HE-IC-2890 | Final Issue for Design/ Construction-TBE for RTU & SCADA Modification | 86 | 5 | 2024-08-12 | 2024-08-16 | 04-Jul-24 A | 2024-11-01 | 153
TBE for Active/ Passive Shelters |  | 103 | 0 | 2024-05-03 | 2024-08-09 | 03-May-24 A | 30-Sep-24 A
HE-EL-1210 | Issue ICR - TBE for Active / Passive Shelters | 11 | 0 | 2024-05-03 | 2024-05-20 | 03-May-24 A | 20-May-24 A
HE-EL-1220 | Receive Company Comments - TBE for Active / Passive Shelters | 9 | 0 | 2024-05-21 | 2024-06-03 | 21-May-24 A | 03-Jun-24 A
HE-EL-1230 | Re-Issue for Approval - TBE for Active / Passive Shelters | 2 | 0 | 2024-06-04 | 2024-06-06 | 04-Jun-24 A | 06-Jun-24 A
HE-EL-1240 | Obtain Company Approval - TBE for Active / Passive Shelters | 4 | 0 | 2024-06-07 | 2024-06-13 | 07-Jun-24 A | 13-Jun-24 A
HE-EL-1250 | Final Issue for Design/ Construction-TBE for Active/ Passive Shelters | 66 | 0 | 2024-06-14 | 2024-08-09 | 28-Jun-24 A | 30-Sep-24 A
Instrument location and Cable Routing Drawings |  | 123 | 10 | 2024-05-16 | 2024-09-06 | 16-May-24 A | 2024-11-08 | 66
HE-IC-2530 | Issue ICR- Instrument location and Cable Routing Drawings | 5 | 0 | 2024-05-16 | 2024-05-23 | 16-May-24 A | 23-May-24 A
HE-IC-2540 | Receive Company Comments- Instrument location and Cable Routing Drawings | 6 | 0 | 2024-05-24 | 2024-06-03 | 24-May-24 A | 03-Jun-24 A
HE-IC-2550 | Re-Issue for Approval- Instrument location and Cable Routing Drawings | 36 | 0 | 2024-06-04 | 2024-08-09 | 04-Jun-24 A | 29-Jul-24 A
HE-IC-2560 | Obtain Company Approval- Instrument location and Cable Routing Drawings | 11 | 0 | 2024-08-12 | 2024-08-23 | 30-Sep-24 A | 14-Oct-24 A
HE-IC-2570 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | 20 | 10 | 2024-08-26 | 2024-09-06 | 14-Oct-24 A | 2024-11-08 | 66
Instrument Termination Drawings |  | 39 | 39 | 2024-07-29 | 2024-09-19 | 2024-10-28 | 2024-12-23 | 52
HE-IC-3090 | Issue ICR- Instrument Termination Drawings | 10 | 10 | 2024-07-29 | 2024-08-09 | 2024-10-28 | 2024-11-08 | 52
HE-IC-3130 | Receive Company Comments- Instrument Termination Drawings | 10 | 10 | 2024-08-12 | 2024-08-23 | 2024-11-11 | 2024-11-22 | 52
HE-IC-3100 | Re-Issue for Approval- Instrument Termination Drawings | 5 | 5 | 2024-08-26 | 2024-08-30 | 2024-11-25 | 2024-11-29 | 52
HE-IC-3110 | Obtain Company Approval-Instrument Termination Drawings | 9 | 9 | 2024-09-02 | 2024-09-12 | 2024-12-04 | 2024-12-16 | 52
HE-IC-3120 | Final Issue for Design/ Construction-Instrument Termination Drawings | 5 | 5 | 2024-09-13 | 2024-09-19 | 2024-12-17 | 2024-12-23 | 52
F&G Termination Drawings |  | 34 | 34 | 2024-08-12 | 2024-09-26 | 2024-11-11 | 2024-12-30 | 52
HE-IC-3140 | Issue ICR- F&G Termination Drawings | 10 | 10 | 2024-08-12 | 2024-08-23 | 2024-11-11 | 2024-11-22 | 56
HE-IC-3180 | Receive Company Comments- F&G Termination Drawings | 5 | 5 | 2024-08-26 | 2024-08-30 | 2024-11-25 | 2024-11-29 | 56
HE-IC-3150 | Re-Issue for Approval- F&G Termination Drawings | 5 | 5 | 2024-09-02 | 2024-09-06 | 2024-12-04 | 2024-12-10 | 56
HE-IC-3160 | Obtain Company Approval- F&G Termination Drawings | 5 | 5 | 2024-09-09 | 2024-09-13 | 2024-12-11 | 2024-12-17 | 56
HE-IC-3170 | Final Issue for Design/ Construction- F&G Termination Drawings | 5 | 5 | 2024-09-20 | 2024-09-26 | 2024-12-24 | 2024-12-30 | 52
Instrument MTO |  | 34 | 10 | 2024-07-29 | 2024-10-25 | 08-Oct-24 A | 2024-11-22 | 86
HE-IC-2590 | Instrument 1st MTO | 6 | 0 | 2024-07-29 | 2024-08-09 | 08-Oct-24 A | 15-Oct-24 A
HE-IC-2610 | Instrument 2nd MTO | 5 | 5 | 2024-10-14 | 2024-10-18 | 2024-11-11 | 2024-11-15 | 86
HE-IC-2630 | Instrument 3rd MTO | 5 | 5 | 2024-10-21 | 2024-10-25 | 2024-11-18 | 2024-11-22 | 86
Telecom |  | 338 | 40 | 2023-08-20 | 2024-12-24 | 20-Aug-23 A | 2024-12-24 | 225
Telecom Design Basis |  | 60 | 0 | 2023-08-20 | 2023-11-13 | 20-Aug-23 A | 13-Nov-23 A
HE-TL-2490 | Issue ICR-Design Basis | 10 | 0 | 2023-08-20 | 2023-09-04 | 20-Aug-23 A | 04-Sep-23 A
HE-TL-2500 | Receive Company Comments-Design Basis | 9 | 0 | 2023-09-05 | 2023-09-16 | 05-Sep-23 A | 16-Sep-23 A
HE-TL-2460 | Re-Issue for Approval-Design Basis | 15 | 0 | 2023-09-17 | 2023-10-09 | 17-Sep-23 A | 09-Oct-23 A
HE-TL-2480 | Obtain Company Approval-Design Basis | 5 | 0 | 2023-10-10 | 2023-10-17 | 10-Oct-23 A | 17-Oct-23 A
HE-TL-2470 | Final Issue for Design/ Construction-Design Basis | 4 | 0 | 2023-11-07 | 2023-11-13 | 07-Nov-23 A | 13-Nov-23 A
Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS |  | 10 | 0 | 2024-02-26 | 2024-03-10 | 26-Feb-24 A | 10-Mar-24 A
HE-TL-0080 | Receive Company Comments - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | 0 | 0 | 2024-02-26 | 2024-02-26 | 26-Feb-24 A | 26-Feb-24 A
HE-TL-0090 | Re-Issue for Approval - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | 0 | 0 | 2024-02-26 | 2024-02-26 | 26-Feb-24 A | 26-Feb-24 A
HE-TL-0100 | Obtain Company Approval - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | 0 | 0 | 2024-02-26 | 2024-02-26 | 26-Feb-24 A | 26-Feb-24 A
HE-TL-0070 | Issue ICR - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | 0 | 0 | 2024-02-26 | 2024-02-26 | 26-Feb-24 A | 26-Feb-24 A
HE-TL-0110 | Final Issue for Design/ Construction-Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | 0 | 0 | 2024-03-10 | 2024-03-10 | 10-Mar-24 A | 10-Mar-24 A
Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 |  | 100 | 0 | 2023-09-21 | 2024-02-12 | 21-Sep-23 A | 12-Feb-24 A
HE-TL-0190 | Issue ICR- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 5 | 0 | 2023-09-21 | 2023-09-28 | 21-Sep-23 A | 28-Sep-23 A
HE-TL-0200 | Receive Company Comments- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 22 | 0 | 2023-09-29 | 2023-10-31 | 29-Sep-23 A | 31-Oct-23 A
HE-TL-0210 | Re-Issue for Approval- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 32 | 0 | 2023-12-05 | 2024-01-19 | 05-Dec-23 A | 19-Jan-24 A
HE-TL-0220 | Obtain Company Approval- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 7 | 0 | 2024-01-10 | 2024-01-19 | 10-Jan-24 A | 19-Jan-24 A
HE-TL-0230 | Final Issue for Design/ Construction-Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 26 | 0 | 2024-01-05 | 2024-02-12 | 05-Jan-24 A | 12-Feb-24 A
Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) |  | 81 | 0 | 2023-11-14 | 2024-03-08 | 14-Nov-23 A | 08-Mar-24 A
HE-TL-0250 | Issue ICR- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | 7 | 0 | 2023-11-14 | 2023-11-23 | 14-Nov-23 A | 23-Nov-23 A
HE-TL-0260 | Receive Company Comments- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | 9 | 0 | 2023-11-24 | 2023-12-08 | 24-Nov-23 A | 08-Dec-23 A
HE-TL-0270 | Re-Issue for Approval- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | 17 | 0 | 2023-12-29 | 2024-01-24 | 29-Dec-23 A | 24-Jan-24 A
HE-TL-0290 | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | 20 | 0 | 2024-01-26 | 2024-02-23 | 26-Jan-24 A | 23-Feb-24 A
HE-TL-0280 | Obtain Company Approval- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | 39 | 0 | 2024-01-15 | 2024-03-08 | 15-Jan-24 A | 08-Mar-24 A
Overall Telecom Block Diagram |  | 82 | 0 | 2023-11-14 | 2024-03-10 | 14-Nov-23 A | 10-Mar-24 A
HE-TL-0310 | Issue ICR- Overall Telecom Block Diagram | 7 | 0 | 2023-11-14 | 2023-11-23 | 14-Nov-23 A | 23-Nov-23 A
HE-TL-0320 | Receive Company Comments- Overall Telecom Block Diagram | 17 | 0 | 2023-11-24 | 2023-12-20 | 24-Nov-23 A | 20-Dec-23 A
HE-TL-0330 | Re-Issue for Approval- Overall Telecom Block Diagram | 44 | 0 | 2023-12-29 | 2024-03-01 | 29-Dec-23 A | 01-Mar-24 A
HE-TL-0340 | Obtain Company Approval- Overall Telecom Block Diagram | 39 | 0 | 2024-01-15 | 2024-03-08 | 15-Jan-24 A | 08-Mar-24 A
HE-TL-0350 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | 31 | 0 | 2024-01-26 | 2024-03-10 | 26-Jan-24 A | 10-Mar-24 A
Telecom Inter Connection Diagram |  | 68 | 0 | 2023-11-17 | 2024-02-23 | 17-Nov-23 A | 23-Feb-24 A
HE-TL-1000 | Issue ICR- Telecom Inter Connection Diagram | 17 | 0 | 2023-11-17 | 2023-12-13 | 17-Nov-23 A | 13-Dec-23 A
HE-TL-1010 | Receive Company Comments- Telecom Inter Connection Diagram | 10 | 0 | 2023-12-13 | 2023-12-27 | 13-Dec-23 A | 27-Dec-23 A
HE-TL-1020 | Re-Issue for Approval- Telecom Inter Connection Diagram | 9 | 0 | 2023-12-27 | 2024-01-10 | 27-Dec-23 A | 10-Jan-24 A
HE-TL-1030 | Obtain Company Approval- Telecom Inter Connection Diagram | 10 | 0 | 2024-01-10 | 2024-01-24 | 10-Jan-24 A | 24-Jan-24 A
HE-TL-990 | Final Issue for Design/ Construction-Telecom Inter Connection Diagram | 22 | 0 | 2024-01-24 | 2024-02-23 | 24-Jan-24 A | 23-Feb-24 A
Typical Inter Connection Diagram for Pig Launcher/Receiver |  | 67 | 0 | 2023-11-19 | 2024-02-23 | 19-Nov-23 A | 23-Feb-24 A
HE-TL-1050 | Issue ICR- Typical Inter Connection Diagram for Pig Launcher/Receiver | 7 | 0 | 2023-11-19 | 2023-11-29 | 19-Nov-23 A | 29-Nov-23 A
HE-TL-1060 | Receive Company Comments- Typical Inter Connection Diagram for Pig Launcher/Receiver | 8 | 0 | 2023-11-30 | 2023-12-13 | 30-Nov-23 A | 13-Dec-23 A
HE-TL-1070 | Re-Issue for Approval- Typical Inter Connection Diagram for Pig Launcher/Receiver | 9 | 0 | 2023-12-14 | 2023-12-27 | 14-Dec-23 A | 27-Dec-23 A
HE-TL-1080 | Obtain Company Approval- Typical Inter Connection Diagram for Pig Launcher/Receiver | 8 | 0 | 2023-12-28 | 2024-01-10 | 28-Dec-23 A | 10-Jan-24 A
HE-TL-1040 | Final Issue for Design/ Construction-Typical Inter Connection Diagram for Pig Launcher/Receiver | 31 | 0 | 2024-01-11 | 2024-02-23 | 11-Jan-24 A | 23-Feb-24 A
Fibre Core Allocation Diagram |  | 71 | 20 | 2024-07-29 | 2024-09-13 | 16-Aug-24 A | 2024-11-22 | 240
HE-TL-1100 | Issue ICR- Fiber Core Allocation Diagram | 6 | 0 | 2024-07-29 | 2024-08-02 | 16-Aug-24 A | 23-Aug-24 A
HE-TL-1110 | Receive Company Comments- Fiber Core Allocation Diagram | 21 | 0 | 2024-08-05 | 2024-08-16 | 26-Aug-24 A | 23-Sep-24 A
HE-TL-1120 | Re-Issue for Approval- Fiber Core Allocation Diagram | 5 | 5 | 2024-08-19 | 2024-08-23 | 2024-10-28 | 2024-11-01 | 240
HE-TL-1130 | Obtain Company Approval- Fiber Core Allocation Diagram | 10 | 10 | 2024-08-26 | 2024-09-06 | 2024-11-04 | 2024-11-15 | 240
HE-TL-1090 | Final Issue for Design/ Construction- Fiber Core Allocation Diagram | 5 | 5 | 2024-09-09 | 2024-09-13 | 2024-11-18 | 2024-11-22 | 240
Optical Power Link Loss Calculation For SDH / FOC System |  | 220 | 5 | 2024-01-08 | 2024-09-20 | 08-Jan-24 A | 2024-11-22 | 240
HE-TL-1150 | Issue ICR- Optical Power Link Loss Calculation For SDH / FOC System | 8 | 0 | 2024-01-08 | 2024-01-18 | 08-Jan-24 A | 18-Jan-24 A
HE-TL-1160 | Receive Company Comments- Optical Power Link Loss Calculation For SDH / FOC System | 16 | 0 | 2024-01-19 | 2024-02-12 | 19-Jan-24 A | 12-Feb-24 A
HE-TL-1170 | Re-Issue for Approval- Optical Power Link Loss Calculation For SDH / FOC System | 8 | 0 | 2024-02-13 | 2024-02-23 | 13-Feb-24 A | 23-Feb-24 A
HE-TL-1180 | Obtain Company Approval- Optical Power Link Loss Calculation For SDH / FOC System | 8 | 0 | 2024-02-24 | 2024-03-07 | 24-Feb-24 A | 07-Mar-24 A
HE-TL-1140 | Final Issue for Design/ Construction-Optical Power Link Loss Calculation For SDH / FOC System | 40 | 5 | 2024-09-16 | 2024-09-20 | 30-Sep-24 A | 2024-11-22 | 240
Narrative For Intrusion Detection System |  | 82 | 0 | 2023-09-09 | 2024-01-05 | 09-Sep-23 A | 05-Jan-24 A
HE-TL-1200 | Issue ICR- Overall Telecom Block Diagram | 9 | 0 | 2023-09-09 | 2023-09-22 | 09-Sep-23 A | 22-Sep-23 A
HE-TL-1210 | Receive Company Comments- Overall Telecom Block Diagram | 10 | 0 | 2023-09-23 | 2023-10-09 | 23-Sep-23 A | 09-Oct-23 A
HE-TL-1220 | Re-Issue for Approval- Overall Telecom Block Diagram | 18 | 0 | 2023-10-10 | 2023-11-03 | 10-Oct-23 A | 03-Nov-23 A
HE-TL-1230 | Obtain Company Approval- Overall Telecom Block Diagram | 6 | 0 | 2023-11-06 | 2023-11-14 | 06-Nov-23 A | 14-Nov-23 A
HE-TL-1190 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | 23 | 0 | 2023-12-02 | 2024-01-05 | 02-Dec-23 A | 05-Jan-24 A
Telecom Tie In Schedule |  | 55 | 0 | 2023-11-16 | 2024-07-29 | 16-Nov-23 A | 04-Feb-24 A
HE-TL-1250 | Issue ICR- Overall Telecom Block Diagram | 6 | 0 | 2023-11-16 | 2023-11-24 | 16-Nov-23 A | 24-Nov-23 A
HE-TL-1260 | Receive Company Comments- Overall Telecom Block Diagram | 11 | 0 | 2024-07-29 | 2024-07-29 | 24-Nov-23 A | 12-Dec-23 A
HE-TL-1280 | Obtain Company Approval- Overall Telecom Block Diagram | 7 | 0 | 2024-07-29 | 2024-07-29 | 13-Dec-23 A | 22-Dec-23 A
HE-TL-1270 | Re-Issue for Approval- Overall Telecom Block Diagram | 8 | 0 | 2024-07-29 | 2024-07-29 | 23-Dec-23 A | 05-Jan-24 A
HE-TL-1240 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | 20 | 0 | 2024-07-29 | 2024-07-29 | 06-Jan-24 A | 04-Feb-24 A
Telecom Equipment List |  | 57 | 0 | 2023-11-21 | 2024-02-12 | 21-Nov-23 A | 12-Feb-24 A
HE-TL-940 | Issue ICR- Telecom Equipment List | 23 | 0 | 2023-11-21 | 2023-12-25 | 21-Nov-23 A | 25-Dec-23 A
HE-TL-950 | Receive Company Comments- Telecom Equipment List | 14 | 0 | 2023-12-25 | 2024-01-15 | 25-Dec-23 A | 15-Jan-24 A
HE-TL-960 | Re-Issue for Approval-Telecom Equipment List | 2 | 0 | 2024-01-19 | 2024-01-23 | 19-Jan-24 A | 23-Jan-24 A
HE-TL-970 | Obtain Company Approval- Telecom Equipment List | 2 | 0 | 2024-01-19 | 2024-01-23 | 19-Jan-24 A | 23-Jan-24 A
HE-TL-980 | Final Issue for Design/ Construction-Telecom Equipment List | 14 | 0 | 2024-01-23 | 2024-02-12 | 23-Jan-24 A | 12-Feb-24 A
Telecom Tie-in Block Diagram |  | 108 | 0 | 2023-10-20 | 2024-03-25 | 20-Oct-23 A | 25-Mar-24 A
HE-TL-0370 | Issue ICR- Telecom Tie-in Block Diagram | 47 | 0 | 2023-10-20 | 2023-12-27 | 20-Oct-23 A | 27-Dec-23 A
HE-TL-0380 | Receive Company Comments- Telecom Tie-in Block Diagram | 7 | 0 | 2024-01-16 | 2024-01-25 | 16-Jan-24 A | 25-Jan-24 A
HE-TL-0390 | Re-Issue for Approval- Telecom Tie-in Block Diagram | 21 | 0 | 2024-01-26 | 2024-02-26 | 26-Jan-24 A | 26-Feb-24 A
HE-TL-0400 | Obtain Company Approval- Telecom Tie-in Block Diagram | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-TL-0410 | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | 9 | 0 | 2024-03-10 | 2024-03-25 | 10-Mar-24 A | 25-Mar-24 A
FOC Block diagram (Telecom) |  | 96 | 0 | 2023-11-08 | 2024-03-26 | 08-Nov-23 A | 26-Mar-24 A
HE-TL-0430 | Issue ICR- FOC Block diagram (Telecom) | 6 | 0 | 2023-11-08 | 2023-11-16 | 08-Nov-23 A | 16-Nov-23 A
HE-TL-0440 | Receive Company Comments- FOC Block diagram (Telecom) | 4 | 0 | 2023-11-17 | 2023-11-23 | 17-Nov-23 A | 23-Nov-23 A
HE-TL-0450 | Re-Issue for Approval- FOC Block diagram (Telecom) | 25 | 0 | 2023-11-24 | 2023-12-30 | 24-Nov-23 A | 30-Dec-23 A
HE-TL-0460 | Obtain Company Approval- FOC Block diagram (Telecom) | 9 | 0 | 2023-12-31 | 2024-01-15 | 31-Dec-23 A | 15-Jan-24 A
HE-TL-0470 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | 49 | 0 | 2024-01-16 | 2024-03-26 | 16-Jan-24 A | 26-Mar-24 A
Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) |  | 243 | 5 | 2023-11-13 | 2024-08-02 | 13-Nov-23 A | 2024-11-01 | 101
HE-TL-0490 | Issue ICR- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 6 | 0 | 2023-11-13 | 2023-11-21 | 13-Nov-23 A | 21-Nov-23 A
HE-TL-0500 | Receive Company Comments- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 19 | 0 | 2023-11-22 | 2023-12-20 | 22-Nov-23 A | 20-Dec-23 A
HE-TL-0510 | Re-Issue for Approval- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 5 | 0 | 2023-12-29 | 2024-01-08 | 29-Dec-23 A | 08-Jan-24 A
HE-TL-0520 | Obtain Company Approval- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 7 | 0 | 2024-01-08 | 2024-01-17 | 08-Jan-24 A | 17-Jan-24 A
HE-TL-0530 | Final Issue for Design/ Construction-Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 8 | 5 | 2024-07-29 | 2024-08-02 | 23-Oct-24 A | 2024-11-01 | 101
Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) |  | 242 | 5 | 2023-11-14 | 2024-08-09 | 14-Nov-23 A | 2024-11-01 | 101
HE-TL-0550 | Issue ICR- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 5 | 0 | 2023-11-14 | 2023-11-21 | 14-Nov-23 A | 21-Nov-23 A
HE-TL-0560 | Receive Company Comments- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 3 | 0 | 2023-11-22 | 2023-11-27 | 22-Nov-23 A | 27-Nov-23 A
HE-TL-0570 | Re-Issue for Approval- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 5 | 0 | 2024-05-24 | 2024-05-31 | 24-May-24 A | 31-May-24 A
HE-TL-0580 | Obtain Company Approval- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 4 | 0 | 2024-06-03 | 2024-06-07 | 03-Jun-24 A | 07-Jun-24 A
HE-TL-0590 | Final Issue for Design/ Construction-Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc. | 7 | 5 | 2024-08-05 | 2024-08-09 | 24-Oct-24 A | 2024-11-01 | 101
TBE for Telecom System |  | 180 | 5 | 2024-03-10 | 2024-09-27 | 10-Mar-24 A | 2024-11-29 | 240
HE-TL-0610 | Issue ICR-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 3 | 0 | 2024-03-10 | 2024-03-14 | 10-Mar-24 A | 14-Mar-24 A
HE-TL-0620 | Receive Company Comments-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 7 | 0 | 2024-03-15 | 2024-03-27 | 15-Mar-24 A | 27-Mar-24 A
HE-TL-0630 | Re-Issue for Approval-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 7 | 0 | 2024-05-29 | 2024-06-07 | 29-May-24 A | 07-Jun-24 A
HE-TL-0640 | Obtain Company Approval-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 10 | 0 | 2024-06-10 | 2024-08-09 | 10-Jun-24 A | 26-Jun-24 A
HE-TL-0650 | Final Issue for Design/ Construction-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 5 | 5 | 2024-09-23 | 2024-09-27 | 2024-11-25 | 2024-11-29 | 240
Telecom Cable Routing Layout |  | 53 | 0 | 2024-03-31 | 2024-08-09 | 31-Mar-24 A | 23-Jun-24 A
HE-TL-0670 | Issue ICR-Telecom Location and Cable Routing layout | 5 | 0 | 2024-03-31 | 2024-04-12 | 31-Mar-24 A | 12-Apr-24 A
HE-TL-0680 | Receive Company Comments-Telecom Location and Cable Routing layout | 10 | 0 | 2024-04-12 | 2024-04-26 | 12-Apr-24 A | 26-Apr-24 A
HE-TL-0690 | Re-Issue for Approval-Telecom Location and Cable Routing layout | 1 | 0 | 2024-04-30 | 2024-05-01 | 30-Apr-24 A | 01-May-24 A
HE-TL-0700 | Obtain Company Approval-Telecom Location and Cable Routing layout | 7 | 0 | 2024-05-01 | 2024-05-10 | 01-May-24 A | 10-May-24 A
HE-TL-0710 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | 28 | 0 | 2024-05-10 | 2024-08-09 | 10-May-24 A | 23-Jun-24 A
Telecom Equipment Layout |  | 13 | 0 | 2024-06-10 | 2024-08-09 | 10-Jun-24 A | 01-Jul-24 A
HE-TL-0730 | Issue ICR-Telecom Equipment Layout | 5 | 0 | 2024-06-10 | 2024-06-17 | 10-Jun-24 A | 17-Jun-24 A
HE-TL-0740 | Receive Company Comments-Telecom Equipment Layout | 0 | 0 | 2024-06-18 | 2024-06-20 | 18-Jun-24 A | 20-Jun-24 A
HE-TL-0750 | Re-Issue for Approval-Telecom Equipment Layout | 1 | 0 | 2024-06-20 | 2024-06-21 | 20-Jun-24 A | 21-Jun-24 A
HE-TL-0760 | Obtain Company Approval-Telecom Equipment Layout | 1 | 0 | 2024-06-21 | 2024-06-24 | 21-Jun-24 A | 24-Jun-24 A
HE-TL-0770 | Final Issue for Design/ Construction-Telecom Equipment Layout | 6 | 0 | 2024-07-29 | 2024-08-09 | 24-Jun-24 A | 01-Jul-24 A
Telecom cable schedule |  | 22 | 0 | 2024-07-29 | 2024-09-20 | 07-Jun-24 A | 12-Jul-24 A
HE-TL-0790 | Issue ICR- Telecom Cable Schedule | 6 | 0 | 2024-07-29 | 2024-08-09 | 07-Jun-24 A | 14-Jun-24 A
HE-TL-0800 | Receive Company Comments- Telecom Cable Schedule | 1 | 0 | 2024-08-12 | 2024-08-23 | 14-Jun-24 A | 18-Jun-24 A
HE-TL-0810 | Re-Issue for Approval- Telecom Cable Schedule | 2 | 0 | 2024-08-26 | 2024-08-30 | 18-Jun-24 A | 21-Jun-24 A
HE-TL-0820 | Obtain Company Approval- Telecom Cable Schedule | 5 | 0 | 2024-09-02 | 2024-09-13 | 22-Jun-24 A | 28-Jun-24 A
HE-TL-0830 | Final Issue for Design/ Construction-Telecom cable schedule | 9 | 0 | 2024-09-16 | 2024-09-20 | 29-Jun-24 A | 12-Jul-24 A
Telecom MTO |  | 59 | 40 | 2024-07-29 | 2024-11-22 | 01-Oct-24 A | 2024-12-24 | 66
HE-TL-0850 | Telecom 1st MTO | 10 | 0 | 2024-07-29 | 2024-08-09 | 01-Oct-24 A | 14-Oct-24 A
HE-TL-0870 | Telecom 2nd MTO | 5 | 5 | 2024-09-23 | 2024-09-27 | 2024-10-28 | 2024-11-01 | 66
HE-TL-0890 | Telecom 3rd MTO | 5 | 5 | 2024-11-18 | 2024-11-22 | 2024-12-18 | 2024-12-24 | 66
Telecom Typical Hookup |  | 90 | 35 | 2024-08-12 | 2024-12-24 | 12-Aug-24 A | 2024-12-17 | 71
HE-TL-890 | Issue ICR-Telecom Typical Hookup | 25 | 0 | 2024-08-12 | 2024-09-13 | 12-Aug-24 A | 13-Sep-24 A
HE-TL-900 | Receive Company Comments-Telecom Typical Hookup | 8 | 0 | 2024-09-16 | 2024-09-27 | 16-Sep-24 A | 25-Sep-24 A
HE-TL-910 | Re-Issue for Approval-Telecom Typical Hookup | 21 | 0 | 2024-09-30 | 2024-11-01 | 26-Sep-24 A | 25-Oct-24 A
HE-TL-920 | Obtain Company Approval-Telecom Typical Hookup | 11 | 10 | 2024-11-04 | 2024-11-15 | 25-Oct-24 A | 2024-11-08 | 71
HE-TL-930 | Final Issue for Design/ Construction-Telecom Typical Hookup | 25 | 25 | 2024-11-18 | 2024-12-24 | 2024-11-11 | 2024-12-17 | 71
HSE & Loss Prevention |  | 338 | 40 | 2023-08-20 | 2024-11-06 | 20-Aug-23 A | 2024-12-24 | 201
Project HSE Plan |  | 67 | 0 | 2023-08-20 | 2023-11-22 | 20-Aug-23 A | 22-Nov-23 A
HE-HS-0010 | Issue ICR-HSE Plan | 6 | 0 | 2023-08-20 | 2023-08-29 | 20-Aug-23 A | 29-Aug-23 A
HE-HS-0020 | Receive Company Comments-HSE Plan | 11 | 0 | 2023-09-01 | 2023-09-17 | 01-Sep-23 A | 17-Sep-23 A
HE-HS-0030 | Re-Issue for Approval-HSE Plan | 15 | 0 | 2023-09-18 | 2023-10-09 | 18-Sep-23 A | 09-Oct-23 A
HE-HS-0040 | Obtain Company Approval-HSE Plan | 11 | 0 | 2023-10-10 | 2023-10-25 | 10-Oct-23 A | 25-Oct-23 A
HE-HS-0050 | Final Issue for Design/ Construction-Project HSE Plan | 6 | 0 | 2023-11-14 | 2023-11-22 | 14-Nov-23 A | 22-Nov-23 A
Project HSE Philosophy |  | 61 | 0 | 2023-08-24 | 2023-11-17 | 24-Aug-23 A | 17-Nov-23 A
HE-HS-0070 | Issue ICR-HSE Philosophy | 17 | 0 | 2023-08-24 | 2023-09-18 | 24-Aug-23 A | 18-Sep-23 A
HE-HS-0080 | Receive Company Comments-HSE Philosophy | 7 | 0 | 2023-09-19 | 2023-09-28 | 19-Sep-23 A | 28-Sep-23 A
HE-HS-0090 | Re-Issue for Approval-HSE Philosophy | 6 | 0 | 2023-09-29 | 2023-10-09 | 29-Sep-23 A | 09-Oct-23 A
HE-HS-0100 | Obtain Company Approval-HSE Philosophy | 13 | 0 | 2023-10-10 | 2023-10-27 | 10-Oct-23 A | 27-Oct-23 A
HE-HS-0110 | Final Issue for Design/ Construction-Project HSE Philosophy | 4 | 0 | 2023-11-13 | 2023-11-17 | 13-Nov-23 A | 17-Nov-23 A
HAZID / ENVID / OHID Procedure |  | 37 | 0 | 2023-10-19 | 2023-12-12 | 19-Oct-23 A | 12-Dec-23 A
HE-HS-0130 | Issue ICR - HAZID / ENVID / OHID Procedure | 8 | 0 | 2023-10-19 | 2023-10-31 | 19-Oct-23 A | 31-Oct-23 A
HE-HS-0140 | Receive Company Comments - HAZID / ENVID / OHID Procedure | 4 | 0 | 2023-11-01 | 2023-11-07 | 01-Nov-23 A | 07-Nov-23 A
HE-HS-0150 | Re-Issue for Approval - HAZID / ENVID / OHID Procedure | 9 | 0 | 2023-11-08 | 2023-11-21 | 08-Nov-23 A | 21-Nov-23 A
HE-HS-0160 | Obtain Company Approval - HAZID / ENVID / OHID Procedure | 4 | 0 | 2023-11-22 | 2023-11-28 | 22-Nov-23 A | 28-Nov-23 A
HE-HS-0170 | Final Issue for Design/ Construction-HAZID / ENVID / OHID Procedure | 8 | 0 | 2023-11-29 | 2023-12-12 | 29-Nov-23 A | 12-Dec-23 A
HAZOP Procedure |  | 64 | 0 | 2023-10-19 | 2024-01-19 | 19-Oct-23 A | 19-Jan-24 A
HE-HS-0190 | Issue ICR-HAZOP Procedure | 8 | 0 | 2023-10-19 | 2023-10-31 | 19-Oct-23 A | 31-Oct-23 A
HE-HS-0200 | Receive Company Comments-HAZOP Procedure | 4 | 0 | 2023-11-01 | 2023-11-07 | 01-Nov-23 A | 07-Nov-23 A
HE-HS-0210 | Re-Issue for Approval-HAZOP Procedure | 9 | 0 | 2023-11-08 | 2023-11-21 | 08-Nov-23 A | 21-Nov-23 A
HE-HS-0220 | Obtain Company Approval-HAZOP Procedure | 24 | 0 | 2023-11-22 | 2023-12-27 | 22-Nov-23 A | 27-Dec-23 A
HE-HS-0230 | Final Issue for Design/ Construction-HAZOP Procedure | 14 | 0 | 2023-12-29 | 2024-01-19 | 29-Dec-23 A | 19-Jan-24 A
F&G layout |  | 217 | 5 | 2023-12-20 | 2024-08-30 | 20-Dec-23 A | 2024-11-01 | 128
HE-HS-0250 | Issue ICR-F&G Layout | 9 | 0 | 2023-12-20 | 2024-01-03 | 20-Dec-23 A | 03-Jan-24 A
HE-HS-0260 | Receive Company Comments-F&G Layout | 3 | 0 | 2024-01-04 | 2024-01-09 | 04-Jan-24 A | 09-Jan-24 A
HE-HS-0270 | Re-Issue for Approval-F&G Layout | 4 | 0 | 2024-04-19 | 2024-04-25 | 19-Apr-24 A | 25-Apr-24 A
HE-HS-0280 | Obtain Company Approval-F&G Layout | 5 | 0 | 2024-07-29 | 2024-08-02 | 14-Jun-24 A | 25-Jun-24 A
HE-HS-0290 | Final Issue for Design/ Construction-F&G layout | 25 | 5 | 2024-08-26 | 2024-08-30 | 30-Sep-24 A | 2024-11-01 | 128
F&G Cause and effect |  | 215 | 25 | 2024-01-22 | 2024-10-04 | 22-Jan-24 A | 2024-11-29 | 159
HE-HS-0310 | Issue ICR-F&G Cause and Effect | 97 | 0 | 2024-01-22 | 2024-08-16 | 22-Jan-24 A | 12-Jun-24 A
HE-HS-0320 | Receive Company Comments-F&G Cause and Effect | 54 | 0 | 2024-08-19 | 2024-08-30 | 13-Jun-24 A | 02-Sep-24 A
HE-HS-0330 | Re-Issue for Approval-F&G Cause and Effect | 15 | 10 | 2024-09-02 | 2024-09-13 | 21-Oct-24 A | 2024-11-08 | 159
HE-HS-0340 | Obtain Company Approval-F&G Cause and Effect | 10 | 10 | 2024-09-16 | 2024-09-27 | 2024-11-11 | 2024-11-22 | 159
HE-HS-0350 | Final Issue for Design/ Construction-F&G Cause and effect | 5 | 5 | 2024-09-30 | 2024-10-04 | 2024-11-25 | 2024-11-29 | 159
Fire fighting & Safety equipment layout |  | 61 | 0 | 2023-12-06 | 2024-03-01 | 06-Dec-23 A | 01-Mar-24 A
HE-HS-0370 | Issue ICR- Fire Fighting & Safety Eqpt. Layout | 7 | 0 | 2023-12-06 | 2023-12-15 | 06-Dec-23 A | 15-Dec-23 A
HE-HS-0380 | Receive Company Comments-Fire Fighting & Safety Eqpt. Layout | 5 | 0 | 2023-12-16 | 2023-12-25 | 16-Dec-23 A | 25-Dec-23 A
HE-HS-0390 | Re-Issue for Approval-Fire Fighting & Safety Eqpt. Layout | 16 | 0 | 2024-01-29 | 2024-02-20 | 29-Jan-24 A | 20-Feb-24 A
HE-HS-0400 | Obtain Company Approval-Fire Fighting & Safety Eqpt. Layout | 9 | 0 | 2024-02-07 | 2024-02-20 | 07-Feb-24 A | 20-Feb-24 A
HE-HS-0410 | Final Issue for Design/ Construction-Fire fighting & Safety equipment layout | 17 | 0 | 2024-02-07 | 2024-03-01 | 07-Feb-24 A | 01-Mar-24 A
Datasheets for fire fighting and safety equipment |  | 34 | 0 | 2024-02-26 | 2024-04-22 | 26-Feb-24 A | 22-Apr-24 A
HE-HS-0430 | Issue ICR-Data Sheets for Fire Fighting & Safety Eqpt | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-HS-0440 | Receive Company Comments-Data Sheets for Fire Fighting & Safety Eqpt | 9 | 0 | 2024-03-10 | 2024-03-25 | 10-Mar-24 A | 25-Mar-24 A
HE-HS-0450 | Re-Issue for Approval-Data Sheets for Fire Fighting & Safety Eqpt | 9 | 0 | 2024-03-10 | 2024-03-25 | 10-Mar-24 A | 25-Mar-24 A
HE-HS-0460 | Obtain Company Approval-Data Sheets for Fire Fighting & Safety Eqpt | 9 | 0 | 2024-03-10 | 2024-03-25 | 10-Mar-24 A | 25-Mar-24 A
HE-HS-0470 | Final Issue for Design/ Construction-Datasheets for fire fighting and safety equipment | 11 | 0 | 2024-03-31 | 2024-04-22 | 31-Mar-24 A | 22-Apr-24 A
HSEIA Study Report |  | 211 | 6 | 2023-12-29 | 2024-08-05 | 29-Dec-23 A | 2024-11-04 | 235
HE-HS-0490 | Study & Issue ICR- HSEIA Study Report | 9 | 0 | 2023-12-29 | 2024-01-12 | 29-Dec-23 A | 12-Jan-24 A
HE-HS-0500 | Receive Company Comments- HSEIA Study Report | 9 | 0 | 2024-01-13 | 2024-01-26 | 13-Jan-24 A | 26-Jan-24 A
HE-HS-0510 | Re-Issue for Approval- HSEIA Study Report | 14 | 0 | 2024-02-26 | 2024-03-17 | 26-Feb-24 A | 17-Mar-24 A
HE-HS-0520 | Obtain Company Approval- HSEIA Study Report | 31 | 0 | 2024-03-18 | 2024-05-08 | 18-Mar-24 A | 08-May-24 A
HE-HS-0530 | Final Issue for Design/ Construction-HSEIA Study Report | 124 | 6 | 2024-05-09 | 2024-08-05 | 09-May-24 A | 2024-11-04 | 235
HAZID/ ENVID/ OHID Report |  | 153 | 0 | 2023-11-01 | 2024-06-13 | 01-Nov-23 A | 13-Jun-24 A
HE-HS-0550 | Issue ICR-HAZID/ ENVID/ OHID Report | 9 | 0 | 2023-11-01 | 2023-11-14 | 01-Nov-23 A | 14-Nov-23 A
HE-HS-0560 | Receive Company Comments-HAZID/ ENVID/ OHID Report | 4 | 0 | 2023-11-15 | 2023-11-21 | 15-Nov-23 A | 21-Nov-23 A
HE-HS-0580 | Obtain Company Approval-HAZID/ ENVID/ OHID Report | 0 | 0 | 2024-01-15 | 2024-01-15 | 15-Jan-24 A | 15-Jan-24 A
HE-HS-0570 | Re-Issue for Approval-HAZID/ ENVID/ OHID Report | 36 | 0 | 2023-11-22 | 2024-01-15 | 22-Nov-23 A | 15-Jan-24 A
HE-HS-0590 | Final Issue for Design/ Construction-HAZID/ ENVID/ OHID Report | 102 | 0 | 2024-01-15 | 2024-06-13 | 15-Jan-24 A | 13-Jun-24 A
HAZID/ ENVID/ OHID Close out Report |  | 171 | 20 | 2024-03-17 | 2024-08-30 | 17-Mar-24 A | 2024-11-22 | 221
HE-HS-0610 | Issue ICR-HAZID/ ENVID/ OHID Close out Report | 31 | 0 | 2024-03-17 | 2024-05-07 | 17-Mar-24 A | 07-May-24 A
HE-HS-0620 | Receive Company Comments-HAZID/ ENVID/ OHID Close out Report | 18 | 0 | 2024-05-08 | 2024-06-03 | 08-May-24 A | 03-Jun-24 A
HE-HS-0630 | Re-Issue for Approval-HAZID/ ENVID/ OHID Close out Report | 90 | 0 | 2024-06-04 | 2024-08-02 | 04-Jun-24 A | 11-Oct-24 A
HE-HS-0640 | Obtain Company Approval-HAZID/ ENVID/ OHID Close out Report | 21 | 10 | 2024-08-05 | 2024-08-16 | 11-Oct-24 A | 2024-11-08 | 221
HE-HS-0650 | Final Issue for Design/ Construction-HAZID/ ENVID/ OHID Close out Report | 10 | 10 | 2024-08-19 | 2024-08-30 | 2024-11-11 | 2024-11-22 | 221
HAZOP Review Report |  | 116 | 0 | 2023-11-28 | 2024-08-09 | 28-Nov-23 A | 18-May-24 A
HE-HS-0670 | Issue ICR- HAZOP reviews Report for all areas | 15 | 0 | 2023-11-28 | 2023-12-20 | 28-Nov-23 A | 20-Dec-23 A
HE-HS-0680 | Receive Company Comments- HAZOP reviews Report for all areas | 6 | 0 | 2023-12-21 | 2023-12-29 | 21-Dec-23 A | 29-Dec-23 A
HE-HS-0690 | Re-Issue for Approval- HAZOP reviews Report for all areas | 13 | 0 | 2024-01-02 | 2024-01-19 | 02-Jan-24 A | 19-Jan-24 A
HE-HS-0700 | Obtain Company Approval- HAZOP reviews Report for all areas | 4 | 0 | 2024-02-26 | 2024-03-01 | 26-Feb-24 A | 01-Mar-24 A
HE-HS-0710 | Final Issue for Design/ Construction-HAZOP Review Report | 49 | 0 | 2024-07-29 | 2024-08-09 | 02-Mar-24 A | 18-May-24 A
HAZOP close out report |  | 37 | 0 | 2024-03-04 | 2024-08-09 | 04-Mar-24 A | 01-May-24 A
HE-HS-0730 | Issue ICR- HAZOP Close Out Report | 9 | 0 | 2024-03-04 | 2024-03-17 | 04-Mar-24 A | 17-Mar-24 A
HE-HS-0740 | Receive Company Comments- HAZOP Close Out Report | 4 | 0 | 2024-03-18 | 2024-03-25 | 18-Mar-24 A | 25-Mar-24 A
HE-HS-0750 | Re-Issue for Approval- HAZOP Close Out Report | 7 | 0 | 2024-03-26 | 2024-04-07 | 26-Mar-24 A | 07-Apr-24 A
HE-HS-0760 | Obtain Company Approval- HAZOP Close Out Report | 9 | 0 | 2024-04-12 | 2024-04-25 | 12-Apr-24 A | 25-Apr-24 A
HE-HS-0770 | Final Issue for Design/ Construction-HAZOP close out report | 4 | 0 | 2024-08-05 | 2024-08-09 | 26-Apr-24 A | 01-May-24 A
QRA Report |  | 131 | 0 | 2023-12-04 | 2024-06-13 | 04-Dec-23 A | 13-Jun-24 A
HE-HS-0790 | Issue ICR-QRA Report | 5 | 0 | 2023-12-04 | 2023-12-11 | 04-Dec-23 A | 11-Dec-23 A
HE-HS-0800 | Receive Company Comments-QRA Report | 9 | 0 | 2023-12-12 | 2023-12-25 | 12-Dec-23 A | 25-Dec-23 A
HE-HS-0810 | Re-Issue for Approval-QRA Report | 21 | 0 | 2023-12-26 | 2024-01-25 | 26-Dec-23 A | 25-Jan-24 A
HE-HS-0820 | Obtain Company Approval-QRA Report | 16 | 0 | 2024-02-26 | 2024-03-19 | 26-Feb-24 A | 19-Mar-24 A
HE-HS-0830 | Final Issue for Design/ Construction-QRA Report | 5 | 0 | 2024-06-06 | 2024-06-13 | 06-Jun-24 A | 13-Jun-24 A
ISD Closeout Report |  | 132 | 8 | 2024-05-01 | 2024-09-11 | 01-May-24 A | 2024-11-06 | 165
HE-HS-1300 | Issue ICR- ISD Closeout Report | 6 | 0 | 2024-05-01 | 2024-05-09 | 01-May-24 A | 09-May-24 A
HE-HS-1310 | Receive Company Comments- ISD Closeout Report | 17 | 0 | 2024-05-10 | 2024-08-09 | 10-May-24 A | 03-Jun-24 A
HE-HS-1320 | Re-Issue for Approval- ISD Closeout Report | 10 | 0 | 2024-08-12 | 2024-08-16 | 02-Sep-24 A | 14-Sep-24 A
HE-HS-1330 | Obtain Company Approval- ISD Closeout Report | 3 | 0 | 2024-08-19 | 2024-08-30 | 16-Sep-24 A | 18-Sep-24 A
HE-HS-1340 | Final Issue for Design/ Construction- ISD Closeout Report | 19 | 8 | 2024-09-02 | 2024-09-11 | 11-Oct-24 A | 2024-11-06 | 165
PHSER Report |  | 205 | 10 | 2024-01-15 | 2024-09-11 | 15-Jan-24 A | 2024-11-08 | 163
HE-HS-0850 | Issue ICR-PHSER Report | 3 | 0 | 2024-01-15 | 2024-01-18 | 15-Jan-24 A | 18-Jan-24 A
HE-HS-0860 | Receive Company Comments-PHSER Report | 14 | 0 | 2024-01-19 | 2024-02-08 | 19-Jan-24 A | 08-Feb-24 A
HE-HS-0870 | Re-Issue for Approval-PHSER Report | 5 | 0 | 2024-02-09 | 2024-02-16 | 09-Feb-24 A | 16-Feb-24 A
HE-HS-0880 | Obtain Company Approval-PHSER Report | 11 | 0 | 2024-02-16 | 2024-03-02 | 16-Feb-24 A | 02-Mar-24 A
HE-HS-0890 | Final Issue for Design/ Construction-PHSER Report | 170 | 10 | 2024-03-04 | 2024-09-11 | 04-Mar-24 A | 2024-11-08 | 163
PHSER Close Out Report |  | 51 | 40 | 2024-09-12 | 2024-11-06 | 11-Oct-24 A | 2024-12-24 | 201
HE-HS-0910 | Issue ICR- PHSER Close Out Report | 21 | 10 | 2024-09-12 | 2024-09-25 | 11-Oct-24 A | 2024-11-08 | 201
HE-HS-0920 | Receive Company Comments- PHSER Close Out Report | 10 | 10 | 2024-09-26 | 2024-10-09 | 2024-11-11 | 2024-11-22 | 201
HE-HS-0930 | Re-Issue for Approval- PHSER Close Out Report | 5 | 5 | 2024-10-10 | 2024-10-16 | 2024-11-25 | 2024-11-29 | 201
HE-HS-0940 | Obtain Company Approval- PHSER Close Out Report | 10 | 10 | 2024-10-17 | 2024-10-30 | 2024-12-04 | 2024-12-17 | 201
HE-HS-0950 | Final Issue for Design/ Construction-PHSER Close Out Report | 5 | 5 | 2024-10-31 | 2024-11-06 | 2024-12-18 | 2024-12-24 | 201
Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) |  | 44 | 0 | 2024-07-29 | 2024-09-20 | 29-Jul-24 A | 27-Sep-24 A
HE-HS-0970 | Issue ICR-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | 10 | 0 | 2024-07-29 | 2024-08-09 | 29-Jul-24 A | 09-Aug-24 A
HE-HS-0980 | Receive Company Comments-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | 10 | 0 | 2024-08-12 | 2024-08-23 | 12-Aug-24 A | 23-Aug-24 A
HE-HS-0990 | Re-Issue for Approval-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | 5 | 0 | 2024-08-26 | 2024-08-30 | 26-Aug-24 A | 30-Aug-24 A
HE-HS-1000 | Obtain Company Approval-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | 12 | 0 | 2024-09-02 | 2024-09-13 | 02-Sep-24 A | 17-Sep-24 A
HE-HS-1010 | Final Issue for Design/ Construction-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | 8 | 0 | 2024-09-16 | 2024-09-20 | 17-Sep-24 A | 27-Sep-24 A
HSE Action Tracking Register (Hazards and Effects Register) |  | 259 | 5 | 2023-10-20 | 2024-08-02 | 20-Oct-23 A | 2024-11-01 | 101
HE-HS-1030 | Issue ICR-HSE Action Tracking Register (Hazards and Effects Register) | 13 | 0 | 2023-10-20 | 2023-11-08 | 20-Oct-23 A | 08-Nov-23 A
HE-HS-1040 | Receive Company Comments-HSE Action Tracking Register (Hazards and Effects Register) | 6 | 0 | 2023-11-09 | 2023-11-17 | 09-Nov-23 A | 17-Nov-23 A
HE-HS-1050 | Re-Issue for Approval-HSE Action Tracking Register (Hazards and Effects Register) | 5 | 0 | 2023-11-17 | 2023-11-24 | 17-Nov-23 A | 24-Nov-23 A
HE-HS-1060 | Obtain Company Approval-HSE Action Tracking Register (Hazards and Effects Register) | 6 | 0 | 2024-05-15 | 2024-05-23 | 15-May-24 A | 23-May-24 A
HE-HS-1070 | Final Issue for Design/ Construction-HSE Action Tracking Register (Hazards and Effects Register) | 112 | 5 | 2024-05-24 | 2024-08-02 | 24-May-24 A | 2024-11-01 | 101
Material Requisition for Fire Fighting and Safety Equipment |  | 30 | 0 | 2024-05-03 | 2024-06-14 | 03-May-24 A | 14-Jun-24 A
HE-HS-1092 | Issue ICR-Material Requisition for Fire Fighting & Safety Eqpt | 5 | 0 | 2024-05-03 | 2024-05-10 | 03-May-24 A | 10-May-24 A
HE-HS-1100 | Receive Company Comments-Material Requisition for Fire Fighting & Safety Eqpt | 4 | 0 | 2024-05-13 | 2024-05-17 | 13-May-24 A | 17-May-24 A
HE-HS-1110 | Re-Issue for Approval-Material Requisition for Fire Fighting & Safety Eqpt | 5 | 0 | 2024-05-17 | 2024-05-24 | 17-May-24 A | 24-May-24 A
HE-HS-1120 | Obtain Company Approval-Material Requisition for Fire Fighting & Safety Eqpt | 5 | 0 | 2024-05-24 | 2024-05-31 | 24-May-24 A | 31-May-24 A
HE-HS-1130 | Final Issue for Design/ Construction-Material Requisition for fire fighting and safety equipment | 10 | 0 | 2024-05-31 | 2024-06-14 | 31-May-24 A | 14-Jun-24 A
TBE for Fire Fighting and Safety Equipment |  | 96 | 0 | 2024-05-07 | 2024-08-23 | 07-May-24 A | 23-Sep-24 A
HE-HS-1150 | Issue ICR-TBE for Fire Fighting & Safety Eqpt | 5 | 0 | 2024-05-07 | 2024-05-14 | 07-May-24 A | 14-May-24 A
HE-HS-1160 | Receive Company Comments-TBE for Fire Fighting & Safety Eqpt | 3 | 0 | 2024-05-15 | 2024-05-20 | 15-May-24 A | 20-May-24 A
HE-HS-1170 | Re-Issue for Approval-TBE for Fire Fighting & Safety Eqpt | 70 | 0 | 2024-05-22 | 2024-08-02 | 22-May-24 A | 02-Sep-24 A
HE-HS-1180 | Obtain Company Approval-TBE for Fire Fighting & Safety Eqpt | 9 | 0 | 2024-08-05 | 2024-08-16 | 03-Sep-24 A | 13-Sep-24 A
HE-HS-1190 | Final Issue for Design/ Construction-TBE for fire fighting and safety equipment | 7 | 0 | 2024-08-19 | 2024-08-23 | 13-Sep-24 A | 23-Sep-24 A
HAZOP Review Report (Vendor) |  | 74 | 5 | 2024-07-29 | 2024-09-18 | 23-Jul-24 A | 2024-11-01 | 192
HE-HS-1220 | Issue ICR- HAZOP Review Report (Vendor) | 11 | 0 | 2024-07-29 | 2024-08-07 | 23-Jul-24 A | 06-Aug-24 A
HE-HS-1230 | Receive Company Comments- HAZOP Review Report (Vendor) | 12 | 0 | 2024-08-08 | 2024-08-21 | 07-Aug-24 A | 22-Aug-24 A
HE-HS-1240 | Re-Issue for Approval- HAZOP Review Report (Vendor) | 9 | 0 | 2024-08-22 | 2024-08-28 | 03-Sep-24 A | 13-Sep-24 A
HE-HS-1200 | Obtain Company Approval- HAZOP Review Report (Vendor) | 6 | 0 | 2024-08-29 | 2024-09-11 | 13-Sep-24 A | 20-Sep-24 A
HE-HS-1210 | Final Issue for Design/ Construction-HAZOP Review Report (Vendor) | 31 | 5 | 2024-09-12 | 2024-09-18 | 20-Sep-24 A | 2024-11-01 | 192
HAZOP close out report (Vendor) |  | 65 | 5 | 2024-08-08 | 2024-09-30 | 03-Aug-24 A | 2024-11-01 | 192
HE-HS-1270 | Issue ICR- HAZOP Closeout Report (Vendor) | 10 | 0 | 2024-08-08 | 2024-08-19 | 03-Aug-24 A | 19-Aug-24 A
HE-HS-1280 | Receive Company Comments- HAZOP Closeout Report (Vendor) | 19 | 0 | 2024-08-20 | 2024-09-02 | 02-Sep-24 A | 26-Sep-24 A
HE-HS-1290 | Re-Issue for Approval- HAZOP Closeout Report (Vendor) | 16 | 0 | 2024-09-03 | 2024-09-09 | 16-Sep-24 A | 07-Oct-24 A
HE-HS-1250 | Obtain Company Approval- HAZOP Closeout Report (Vendor) | 10 | 0 | 2024-09-10 | 2024-09-23 | 08-Oct-24 A | 21-Oct-24 A
HE-HS-1260 | Final Issue for Design/ Construction-HAZOP Closeout Report (Vendor) | 9 | 5 | 2024-09-24 | 2024-09-30 | 22-Oct-24 A | 2024-11-01 | 192
Building Works |  | 313 | 35 | 2023-09-16 | 2024-10-25 | 16-Sep-23 A | 2024-12-17 | 131
HVAC Design Basis |  | 79 | 0 | 2023-09-16 | 2024-01-09 | 16-Sep-23 A | 09-Jan-24 A
HE-HV-180 | Issue ICR-Design Basis | 7 | 0 | 2023-09-16 | 2023-09-27 | 16-Sep-23 A | 27-Sep-23 A
HE-HV-190 | Receive Company Comments-Design Basis | 9 | 0 | 2023-09-28 | 2023-10-11 | 28-Sep-23 A | 11-Oct-23 A
HE-HV-150 | Re-Issue for Approval-Design Basis | 14 | 0 | 2023-11-07 | 2023-11-27 | 07-Nov-23 A | 27-Nov-23 A
HE-HV-170 | Obtain Company Approval-Design Basis | 9 | 0 | 2023-11-28 | 2023-12-12 | 28-Nov-23 A | 12-Dec-23 A
HE-HV-160 | Final Issue for Design-Design Basis | 18 | 0 | 2023-12-13 | 2024-01-09 | 13-Dec-23 A | 09-Jan-24 A
Specification for HVAC |  | 73 | 0 | 2023-11-01 | 2024-02-14 | 01-Nov-23 A | 14-Feb-24 A
HE-HV-2690 | Issue ICR- Specification for HVAC | 7 | 0 | 2023-11-01 | 2023-11-10 | 01-Nov-23 A | 10-Nov-23 A
HE-HV-2700 | Receive Company Comments- Specification for HVAC | 4 | 0 | 2023-11-11 | 2023-11-17 | 11-Nov-23 A | 17-Nov-23 A
HE-HV-2710 | Re-Issue for Approval- Specification for HVAC | 5 | 0 | 2023-11-17 | 2023-11-24 | 17-Nov-23 A | 24-Nov-23 A
HE-HV-2720 | Obtain Company Approval- Specification for HVAC | 6 | 0 | 2023-11-28 | 2023-12-07 | 28-Nov-23 A | 07-Dec-23 A
HE-HV-2730 | Final Issue for Design/ Construction-Specification for HVAC | 12 | 0 | 2024-01-29 | 2024-02-14 | 29-Jan-24 A | 14-Feb-24 A
Foundation, GA & Reinforcement Details for E&I Building at Habshan complex |  | 54 | 0 | 2024-03-29 | 2024-08-16 | 29-Mar-24 A | 23-Jun-24 A
HE-BL-1090 | Receive Company Comments-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | 6 | 0 | 2024-03-29 | 2024-04-12 | 29-Mar-24 A | 12-Apr-24 A
HE-BL-1080 | Issue ICR-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | 12 | 0 | 2024-03-31 | 2024-04-23 | 31-Mar-24 A | 23-Apr-24 A
HE-BL-1050 | Re-Issue for Approval-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | 10 | 0 | 2024-04-12 | 2024-04-26 | 12-Apr-24 A | 26-Apr-24 A
HE-BL-1070 | Obtain Company Approval-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | 10 | 0 | 2024-04-26 | 2024-05-10 | 26-Apr-24 A | 10-May-24 A
HE-BL-1060 | Final Issue for Design-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | 18 | 0 | 2024-05-24 | 2024-08-16 | 24-May-24 A | 23-Jun-24 A
Specification for Material Handling Equipment |  | 54 | 0 | 2024-02-26 | 2024-05-20 | 26-Feb-24 A | 20-May-24 A
HE-HV-2740 | Issue ICR- Specification for Material Handling | 11 | 0 | 2024-02-26 | 2024-03-11 | 26-Feb-24 A | 11-Mar-24 A
HE-HV-2750 | Receive Company Comments- Specification for Material Handling | 9 | 0 | 2024-03-12 | 2024-03-27 | 12-Mar-24 A | 27-Mar-24 A
HE-HV-2760 | Re-Issue for Approval- Specification for Material Handling | 14 | 0 | 2024-03-31 | 2024-04-25 | 31-Mar-24 A | 25-Apr-24 A
HE-HV-2770 | Obtain Company Approval- Specification for Material Handling | 1 | 0 | 2024-04-27 | 2024-04-30 | 27-Apr-24 A | 30-Apr-24 A
HE-HV-2780 | Final Issue for Design/ Construction-Specification for Material Handling | 13 | 0 | 2024-05-01 | 2024-05-20 | 01-May-24 A | 20-May-24 A
Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS |  | 190 | 10 | 2024-02-03 | 2024-08-09 | 03-Feb-24 A | 2024-11-08 | 156
HE-BL-1130 | Issue ICR-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | 10 | 0 | 2024-02-03 | 2024-02-17 | 03-Feb-24 A | 17-Feb-24 A
HE-BL-1140 | Receive Company Comments-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | 3 | 0 | 2024-03-31 | 2024-04-04 | 31-Mar-24 A | 04-Apr-24 A
HE-BL-1100 | Re-Issue for Approval-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | 2 | 0 | 2024-04-05 | 2024-04-10 | 05-Apr-24 A | 10-Apr-24 A
HE-BL-1120 | Obtain Company Approval-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | 6 | 0 | 2024-04-11 | 2024-04-22 | 11-Apr-24 A | 22-Apr-24 A
HE-BL-1110 | Final Issue for Design-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | 137 | 10 | 2024-04-26 | 2024-08-09 | 26-Apr-24 A | 2024-11-08 | 156
Datasheet for Material Handling Equipment |  | 54 | 0 | 2024-02-26 | 2024-05-20 | 26-Feb-24 A | 20-May-24 A
HE-HV-2790 | Issue ICR- Datasheet for Material Handling | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-HV-2800 | Receive Company Comments- Datasheet for Material Handling | 9 | 0 | 2024-03-10 | 2024-03-25 | 10-Mar-24 A | 25-Mar-24 A
HE-HV-2810 | Re-Issue for Approval- Datasheet for Material Handling | 18 | 0 | 2024-03-26 | 2024-04-26 | 26-Mar-24 A | 26-Apr-24 A
HE-HV-2820 | Obtain Company Approval- Datasheet for Material Handling | 9 | 0 | 2024-04-27 | 2024-05-10 | 27-Apr-24 A | 10-May-24 A
HE-HV-2830 | Final Issue for Design/ Construction-Datasheet for Material Handling | 5 | 0 | 2024-05-11 | 2024-05-20 | 11-May-24 A | 20-May-24 A
MR for Material Handling Equipment |  | 89 | 0 | 2024-03-10 | 2024-08-23 | 10-Mar-24 A | 25-Jul-24 A
HE-HV-2840 | Issue ICR- Material Requisition for Material Handling | 9 | 0 | 2024-03-10 | 2024-03-25 | 10-Mar-24 A | 25-Mar-24 A
HE-HV-2850 | Receive Company Comments- Material Requisition for Material Handling | 2 | 0 | 2024-03-26 | 2024-03-29 | 26-Mar-24 A | 29-Mar-24 A
HE-HV-2860 | Re-Issue for Approval- Material Requisition for Material Handling | 8 | 0 | 2024-07-29 | 2024-08-02 | 25-Jun-24 A | 04-Jul-24 A
HE-HV-2870 | Obtain Company Approval- Material Requisition for Material Handling | 10 | 0 | 2024-08-05 | 2024-08-16 | 05-Jul-24 A | 21-Jul-24 A
HE-HV-2880 | Final Issue for Design/ Construction-Material Requisition for Material Handling | 4 | 0 | 2024-08-19 | 2024-08-23 | 22-Jul-24 A | 25-Jul-24 A
TBE for Material Handling Equipment |  | 113 | 15 | 2024-06-06 | 2024-09-06 | 06-Jun-24 A | 2024-11-15 | 77
HE-HV-2890 | Issue ICR- TBE for Material Handling | 7 | 0 | 2024-06-06 | 2024-06-17 | 06-Jun-24 A | 17-Jun-24 A
HE-HV-2900 | Receive Company Comments- TBE for Material Handling | 9 | 0 | 2024-07-29 | 2024-08-09 | 18-Jun-24 A | 02-Jul-24 A
HE-HV-2910 | Re-Issue for Approval- TBE for Material Handling | 5 | 0 | 2024-08-12 | 2024-08-16 | 11-Oct-24 A | 17-Oct-24 A
HE-HV-2920 | Obtain Company Approval- TBE for Material Handling | 16 | 10 | 2024-08-19 | 2024-08-30 | 18-Oct-24 A | 2024-11-08 | 77
HE-HV-2930 | Final Issue for Design/ Construction- TBE for Material Handling | 5 | 5 | 2024-09-02 | 2024-09-06 | 2024-11-11 | 2024-11-15 | 77
Structural Design Calculation |  | 200 | 15 | 2024-01-29 | 2024-08-16 | 29-Jan-24 A | 2024-11-15 | 151
HE-BL-1000 | Issue ICR-Structural Design Calculation | 13 | 0 | 2024-01-29 | 2024-02-15 | 29-Jan-24 A | 15-Feb-24 A
HE-BL-1010 | Receive Company Comments-Structural Design Calculation | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HE-BL-1020 | Re-Issue for Approval-Structural Design Calculation | 3 | 0 | 2024-03-31 | 2024-04-05 | 31-Mar-24 A | 05-Apr-24 A
HE-BL-1030 | Obtain Company Approval-Structural Design Calculation | 3 | 0 | 2024-04-06 | 2024-04-16 | 06-Apr-24 A | 16-Apr-24 A
HE-BL-1040 | Final Issue for Design-Structural Design Calculation | 152 | 15 | 2024-04-11 | 2024-08-16 | 11-Apr-24 A | 2024-11-15 | 151
Plumbing Design, Calculation & Details |  | 73 | 0 | 2023-12-13 | 2024-08-16 | 13-Dec-23 A | 27-Mar-24 A
HE-BL-1180 | Issue ICR-Plumbing Design, Calculation & Details | 12 | 0 | 2023-12-13 | 2023-12-29 | 13-Dec-23 A | 29-Dec-23 A
HE-BL-1190 | Receive Company Comments-Plumbing Design, Calculation & Details | 11 | 0 | 2023-12-29 | 2024-01-16 | 29-Dec-23 A | 16-Jan-24 A
HE-BL-1150 | Re-Issue for Approval-Plumbing Design, Calculation & Details | 24 | 0 | 2024-01-26 | 2024-02-29 | 26-Jan-24 A | 29-Feb-24 A
HE-BL-1170 | Obtain Company Approval-Plumbing Design, Calculation & Details | 10 | 0 | 2024-02-29 | 2024-03-15 | 29-Feb-24 A | 15-Mar-24 A
HE-BL-1160 | Final Issue for Design-Plumbing Design, Calculation & Details | 6 | 0 | 2024-08-05 | 2024-08-16 | 16-Mar-24 A | 27-Mar-24 A
Layout, Elevation & Finishing for E&I Building at Habshan complex |  | 201 | 10 | 2024-01-19 | 2024-08-09 | 19-Jan-24 A | 2024-11-08 | 156
HE-BL-1230 | Issue ICR-Layout, Elevation & Finishing for E&I Building at Habshan complex | 20 | 0 | 2024-01-19 | 2024-02-16 | 19-Jan-24 A | 16-Feb-24 A
HE-BL-1240 | Receive Company Comments-Layout, Elevation & Finishing for E&I Building at Habshan complex | 10 | 0 | 2024-02-18 | 2024-03-02 | 18-Feb-24 A | 02-Mar-24 A
HE-BL-1200 | Re-Issue for Approval-Layout, Elevation & Finishing for E&I Building at Habshan complex | 10 | 0 | 2024-03-04 | 2024-03-18 | 04-Mar-24 A | 18-Mar-24 A
HE-BL-1220 | Obtain Company Approval-Layout, Elevation & Finishing for E&I Building at Habshan complex | 7 | 0 | 2024-03-18 | 2024-03-29 | 18-Mar-24 A | 29-Mar-24 A
HE-BL-1210 | Final Issue for Design-Layout, Elevation & Finishing for E&I Building at Habshan complex | 126 | 10 | 2024-05-13 | 2024-08-09 | 13-May-24 A | 2024-11-08 | 156
Layout, Elevation & Finishing for E&I Building at Sweihan CRS |  | 75 | 10 | 2024-07-29 | 2024-10-04 | 29-Jul-24 A | 2024-11-08 | 141
HE-BL-1280 | Issue ICR-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | 10 | 0 | 2024-07-29 | 2024-08-09 | 29-Jul-24 A | 09-Aug-24 A
HE-BL-1290 | Receive Company Comments-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | 10 | 0 | 2024-08-12 | 2024-08-23 | 12-Aug-24 A | 23-Aug-24 A
HE-BL-1250 | Re-Issue for Approval-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | 10 | 0 | 2024-08-26 | 2024-09-06 | 26-Aug-24 A | 06-Sep-24 A
HE-BL-1270 | Obtain Company Approval-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | 11 | 0 | 2024-09-09 | 2024-09-20 | 09-Sep-24 A | 23-Sep-24 A
HE-BL-1260 | Final Issue for Design-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | 35 | 10 | 2024-09-23 | 2024-10-04 | 23-Sep-24 A | 2024-11-08 | 141
Plumbing & Drainage Layout for E&I Building at Sweihan CRS |  | 234 | 15 | 2023-12-10 | 2024-09-06 | 10-Dec-23 A | 2024-11-15 | 151
HE-BL-1330 | Issue ICR-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | 14 | 0 | 2023-12-10 | 2023-12-29 | 10-Dec-23 A | 29-Dec-23 A
HE-BL-1340 | Receive Company Comments-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | 10 | 0 | 2023-12-30 | 2024-01-16 | 30-Dec-23 A | 16-Jan-24 A
HE-BL-1300 | Re-Issue for Approval-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | 14 | 0 | 2024-02-26 | 2024-03-17 | 26-Feb-24 A | 17-Mar-24 A
HE-BL-1320 | Obtain Company Approval-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | 6 | 0 | 2024-03-18 | 2024-03-27 | 18-Mar-24 A | 27-Mar-24 A
HE-BL-1310 | Final Issue for Design-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | 26 | 15 | 2024-08-19 | 2024-09-06 | 11-Oct-24 A | 2024-11-15 | 151
Instrument & Control Layouts |  | 126 | 35 | 2024-07-29 | 2024-10-25 | 16-Jun-24 A | 2024-12-17 | 131
HE-BL-1380 | Issue ICR-Instrument & Control Layouts | 2 | 0 | 2024-07-29 | 2024-08-09 | 16-Jun-24 A | 23-Jun-24 A
HE-BL-1390 | Receive Company Comments-Instrument & Control Layouts | 10 | 0 | 2024-08-12 | 2024-08-23 | 14-Oct-24 A | 25-Oct-24 A
HE-BL-1350 | Re-Issue for Approval-Instrument & Control Layouts | 10 | 10 | 2024-08-26 | 2024-09-06 | 2024-10-28 | 2024-11-08 | 131
HE-BL-1370 | Obtain Company Approval-Instrument & Control Layouts | 10 | 10 | 2024-09-09 | 2024-09-20 | 2024-11-11 | 2024-11-22 | 131
HE-BL-1360 | Final Issue for Design-Instrument & Control Layouts | 15 | 15 | 2024-10-07 | 2024-10-25 | 2024-11-25 | 2024-12-17 | 131
Procurement Services |  | 360 | 50 | 2023-08-03 | 2025-01-08 | 03-Aug-23 A | 2025-01-08 | 142
Equipment / Tagged Items |  | 248 | 0 | 2023-10-30 | 2024-10-25 | 30-Oct-23 A | 25-Oct-24 A
Long Lead Items |  | 160 | 0 | 2023-10-30 | 2024-06-24 | 30-Oct-23 A | 24-Jun-24 A
Custody Metering Skid |  | 73 | 0 | 2023-11-03 | 2024-02-16 | 03-Nov-23 A | 16-Feb-24 A
Ordering |  | 73 | 0 | 2023-11-03 | 2024-02-16 | 03-Nov-23 A | 16-Feb-24 A
HP-ME-0010 | RFQ, Receipt of Bid for Custody Metering Skid | 14 | 0 | 2023-11-03 | 2023-11-23 | 03-Nov-23 A | 23-Nov-23 A
HP-ME-0020 | Prepare TBE and Company approval for Custody Metering Skid | 43 | 0 | 2023-11-24 | 2024-01-26 | 24-Nov-23 A | 26-Jan-24 A
HP-ME-0030 | Commercial Clarifications & Placement of PO for Custody Metering Skid | 14 | 0 | 2024-01-29 | 2024-02-16 | 29-Jan-24 A | 16-Feb-24 A
Pressure Reduction Skid |  | 79 | 0 | 2023-11-02 | 2024-02-23 | 02-Nov-23 A | 23-Feb-24 A
Ordering |  | 79 | 0 | 2023-11-02 | 2024-02-23 | 02-Nov-23 A | 23-Feb-24 A
HP-ME-0060 | RFQ, Receipt of Bid for Pressure Reduction Skid | 9 | 0 | 2023-11-02 | 2023-11-15 | 02-Nov-23 A | 15-Nov-23 A
HP-ME-0070 | Prepare TBE and Company approval for Pressure Reduction Skid | 49 | 0 | 2023-11-16 | 2024-01-26 | 16-Nov-23 A | 26-Jan-24 A
HP-ME-0080 | Commercial Clarifications & Placement of PO for Pressure Reduction Skid | 19 | 0 | 2024-01-29 | 2024-02-23 | 29-Jan-24 A | 23-Feb-24 A
Leak Detection System |  | 83 | 0 | 2023-11-29 | 2024-03-29 | 29-Nov-23 A | 29-Mar-24 A
Ordering |  | 83 | 0 | 2023-11-29 | 2024-03-29 | 29-Nov-23 A | 29-Mar-24 A
HP-ME-0110 | RFQ, Receipt of Bid for Leak Detection System | 12 | 0 | 2023-11-29 | 2023-12-17 | 29-Nov-23 A | 17-Dec-23 A
HP-ME-0120 | Prepare TBE and Company approval for Leak Detection System | 68 | 0 | 2023-12-18 | 2024-03-25 | 18-Dec-23 A | 25-Mar-24 A
HP-ME-0130 | Commercial Clarifications & Placement of PO for Leak Detection System | 2 | 0 | 2024-03-26 | 2024-03-29 | 26-Mar-24 A | 29-Mar-24 A
Filter Package |  | 35 | 0 | 2023-10-30 | 2023-12-19 | 30-Oct-23 A | 19-Dec-23 A
Ordering |  | 35 | 0 | 2023-10-30 | 2023-12-19 | 30-Oct-23 A | 19-Dec-23 A
HP-ME-0160 | RFQ, Receipt of Bid for Filter Package | 6 | 0 | 2023-10-30 | 2023-11-07 | 30-Oct-23 A | 07-Nov-23 A
HP-ME-0170 | Prepare TBE and Company approval for Filter Package | 26 | 0 | 2023-11-08 | 2023-12-15 | 08-Nov-23 A | 15-Dec-23 A
HP-ME-0180 | Commercial Clarifications & Placement of PO for Filter Package | 1 | 0 | 2023-12-18 | 2023-12-19 | 18-Dec-23 A | 19-Dec-23 A
Pig Launcers & Receivers |  | 37 | 0 | 2023-11-02 | 2023-12-26 | 02-Nov-23 A | 26-Dec-23 A
Ordering |  | 37 | 0 | 2023-11-02 | 2023-12-26 | 02-Nov-23 A | 26-Dec-23 A
HP-ME-0210 | RFQ, Receipt of Bid for Pig Launchers & Receivers | 3 | 0 | 2023-11-02 | 2023-11-07 | 02-Nov-23 A | 07-Nov-23 A
HP-ME-0220 | Prepare TBE and Company approval for Pig Launchers & Receivers | 27 | 0 | 2023-11-08 | 2023-12-18 | 08-Nov-23 A | 18-Dec-23 A
HP-ME-0230 | Commercial Clarifications & Placement of PO for Pig Launchers & Receivers | 4 | 0 | 2023-12-20 | 2023-12-26 | 20-Dec-23 A | 26-Dec-23 A
ROV/ GOV |  | 102 | 0 | 2023-10-30 | 2024-03-25 | 30-Oct-23 A | 25-Mar-24 A
Ordering |  | 102 | 0 | 2023-10-30 | 2024-03-25 | 30-Oct-23 A | 25-Mar-24 A
HP-ME-0260 | RFQ, Receipt of Bid for ROV/ GOV | 9 | 0 | 2023-10-30 | 2023-11-10 | 30-Oct-23 A | 10-Nov-23 A
HP-ME-0270 | Prepare TBE and Company approval for ROV/ GOV | 52 | 0 | 2023-11-11 | 2024-01-26 | 11-Nov-23 A | 26-Jan-24 A
HP-ME-0280 | Commercial Clarifications & Placement of PO for ROV/ GOV | 9 | 0 | 2024-03-10 | 2024-03-25 | 10-Mar-24 A | 25-Mar-24 A
MOV & ISOLATOR |  | 104 | 0 | 2023-10-30 | 2024-03-27 | 30-Oct-23 A | 27-Mar-24 A
Ordering |  | 104 | 0 | 2023-10-30 | 2024-03-27 | 30-Oct-23 A | 27-Mar-24 A
HP-ME-0310 | RFQ, Receipt of Bid for MOV | 9 | 0 | 2023-10-30 | 2023-11-10 | 30-Oct-23 A | 10-Nov-23 A
HP-ME-0320 | Prepare TBE and Company approval for MOV | 87 | 0 | 2023-11-11 | 2024-03-17 | 11-Nov-23 A | 17-Mar-24 A
HP-ME-0330 | Commercial Clarifications & Placement of PO for MOV | 6 | 0 | 2024-03-18 | 2024-03-27 | 18-Mar-24 A | 27-Mar-24 A
AC UPS |  | 72 | 0 | 2023-12-12 | 2024-03-25 | 12-Dec-23 A | 25-Mar-24 A
Ordering |  | 72 | 0 | 2023-12-12 | 2024-03-25 | 12-Dec-23 A | 25-Mar-24 A
HP-ME-0360 | RFQ, Receipt of Bid for AC UPS | 3 | 0 | 2023-12-12 | 2023-12-15 | 12-Dec-23 A | 15-Dec-23 A
HP-ME-0370 | Prepare TBE and Company approval for AC UPS | 66 | 0 | 2023-12-15 | 2024-03-20 | 15-Dec-23 A | 20-Mar-24 A
HP-ME-0380 | Commercial Clarifications & Placement of PO for AC UPS | 14 | 0 | 2024-03-04 | 2024-03-25 | 04-Mar-24 A | 25-Mar-24 A
Solar Power System |  | 88 | 0 | 2024-02-03 | 2024-06-14 | 03-Feb-24 A | 14-Jun-24 A
Ordering |  | 88 | 0 | 2024-02-03 | 2024-06-14 | 03-Feb-24 A | 14-Jun-24 A
HP-ME-0510 | RFQ, Receipt of Bid for Solar PV system | 17 | 0 | 2024-02-03 | 2024-02-28 | 03-Feb-24 A | 28-Feb-24 A
HP-ME-0520 | Prepare TBE and Company approval for Solar PV system | 72 | 0 | 2024-02-23 | 2024-06-12 | 23-Feb-24 A | 12-Jun-24 A
HP-ME-0530 | Commercial Clarifications & Placement of PO for Solar PV system | 1 | 0 | 2024-06-13 | 2024-06-14 | 13-Jun-24 A | 14-Jun-24 A
Passive Cooled Shelter |  | 94 | 0 | 2024-01-26 | 2024-06-14 | 26-Jan-24 A | 14-Jun-24 A
Ordering |  | 94 | 0 | 2024-01-26 | 2024-06-14 | 26-Jan-24 A | 14-Jun-24 A
HP-ME-0560 | RFQ, Receipt of Bid for Active/ Passive Cooled Shelter | 12 | 0 | 2024-01-26 | 2024-02-13 | 26-Jan-24 A | 13-Feb-24 A
HP-ME-0570 | Prepare TBE and Company approval for Active/ Passive Cooled Shelter | 13 | 0 | 2024-05-17 | 2024-06-05 | 17-May-24 A | 05-Jun-24 A
HP-ME-0580 | Commercial Clarifications & Placement of PO for Active/ Passive Cooled Shelter | 6 | 0 | 2024-06-06 | 2024-06-14 | 06-Jun-24 A | 14-Jun-24 A
Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) |  | 129 | 0 | 2023-11-29 | 2024-06-07 | 29-Nov-23 A | 07-Jun-24 A
Ordering |  | 129 | 0 | 2023-11-29 | 2024-06-07 | 29-Nov-23 A | 07-Jun-24 A
HP-ME-0610 | RFQ, Receipt of Bid for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 16 | 0 | 2023-11-29 | 2023-12-22 | 29-Nov-23 A | 22-Dec-23 A
HP-ME-0620 | Prepare TBE and Company approval for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 94 | 0 | 2024-01-10 | 2024-05-29 | 10-Jan-24 A | 29-May-24 A
HP-ME-0630 | Commercial Clarifications & Placement of PO for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | 6 | 0 | 2024-05-30 | 2024-06-07 | 30-May-24 A | 07-Jun-24 A
Gas Detectors |  | 61 | 0 | 2024-03-20 | 2024-06-24 | 20-Mar-24 A | 24-Jun-24 A
Ordering |  | 61 | 0 | 2024-03-20 | 2024-06-24 | 20-Mar-24 A | 24-Jun-24 A
HP-ME-0710 | RFQ, Receipt of Bid for Gas Detectors | 17 | 0 | 2024-03-20 | 2024-04-19 | 20-Mar-24 A | 19-Apr-24 A
HP-ME-0720 | Prepare TBE and Company approval for Gas Detectors | 12 | 0 | 2024-05-31 | 2024-06-21 | 31-May-24 A | 21-Jun-24 A
HP-ME-0730 | Commercial Clarifications & Placement of PO for Gas Detectors | 1 | 0 | 2024-06-22 | 2024-06-24 | 22-Jun-24 A | 24-Jun-24 A
FOC Cables |  | 98 | 0 | 2023-11-29 | 2024-04-25 | 29-Nov-23 A | 25-Apr-24 A
Ordering |  | 98 | 0 | 2023-11-29 | 2024-04-25 | 29-Nov-23 A | 25-Apr-24 A
HP-BK-0060 | RFQ, Receipt of Bid for FOC Cables | 5 | 0 | 2023-11-29 | 2023-12-07 | 29-Nov-23 A | 07-Dec-23 A
HP-BK-0070 | Prepare TBE and Company approval for FOC Cables | 44 | 0 | 2024-01-23 | 2024-03-26 | 23-Jan-24 A | 26-Mar-24 A
HP-BK-0080 | Commercial Clarifications & Placement of PO for FOC Cables | 14 | 0 | 2024-03-31 | 2024-04-25 | 31-Mar-24 A | 25-Apr-24 A
Others |  | 224 | 0 | 2023-12-04 | 2024-10-25 | 04-Dec-23 A | 25-Oct-24 A
LV Switch Gear |  | 116 | 0 | 2024-05-13 | 2024-09-20 | 13-May-24 A | 25-Oct-24 A
Ordering |  | 116 | 0 | 2024-05-13 | 2024-09-20 | 13-May-24 A | 25-Oct-24 A
HP-ME-1330 | RFQ, Receipt of Bid for LV Switch Gear | 4 | 0 | 2024-05-13 | 2024-05-17 | 13-May-24 A | 17-May-24 A
HP-ME-1350 | Prepare TBE and Company approval for LV Switch Gear | 55 | 0 | 2024-08-05 | 2024-08-30 | 05-Aug-24 A | 18-Oct-24 A
HP-ME-1340 | Commercial Clarifications & Placement of PO for LV Switch Gear | 6 | 0 | 2024-09-02 | 2024-09-20 | 18-Oct-24 A | 25-Oct-24 A
Field Instruments / H2S Analyzers |  | 87 | 0 | 2024-02-02 | 2024-06-12 | 02-Feb-24 A | 12-Jun-24 A
Ordering |  | 87 | 0 | 2024-02-02 | 2024-06-12 | 02-Feb-24 A | 12-Jun-24 A
HP-ME-0760 | RFQ, Receipt of Bid for Field Instruments | 44 | 0 | 2024-02-02 | 2024-04-11 | 02-Feb-24 A | 11-Apr-24 A
HP-ME-0770 | Prepare TBE and Company approval for Field Instruments | 35 | 0 | 2024-04-12 | 2024-05-31 | 12-Apr-24 A | 31-May-24 A
HP-ME-0780 | Commercial Clarifications & Placement of PO for Field Instruments | 6 | 0 | 2024-06-04 | 2024-06-12 | 04-Jun-24 A | 12-Jun-24 A
Power Distribution Boards |  | 94 | 0 | 2024-04-05 | 2024-10-25 | 05-Apr-24 A | 23-Aug-24 A
Ordering |  | 94 | 0 | 2024-04-05 | 2024-10-25 | 05-Apr-24 A | 23-Aug-24 A
HP-ME-0410 | RFQ, Receipt of Bid for Power Distribution Boards | 26 | 0 | 2024-04-05 | 2024-05-16 | 05-Apr-24 A | 16-May-24 A
HP-ME-0420 | Prepare TBE and Company approval for Power Distribution Boards | 56 | 0 | 2024-05-27 | 2024-10-04 | 27-May-24 A | 18-Aug-24 A
HP-ME-0430 | Commercial Clarifications & Placement of PO for Power Distribution Boards | 5 | 0 | 2024-10-07 | 2024-10-25 | 19-Aug-24 A | 23-Aug-24 A
Junction Boxes |  | 95 | 0 | 2024-05-20 | 2024-10-11 | 20-May-24 A | 03-Oct-24 A
Ordering |  | 95 | 0 | 2024-05-20 | 2024-10-11 | 20-May-24 A | 03-Oct-24 A
HP-ME-0810 | RFQ, Receipt of Bid for Junction Boxes | 19 | 0 | 2024-05-20 | 2024-06-14 | 20-May-24 A | 14-Jun-24 A
HP-ME-0820 | Prepare TBE and Company approval for Junction Boxes | 66 | 0 | 2024-06-15 | 2024-09-20 | 15-Jun-24 A | 20-Sep-24 A
HP-ME-0830 | Commercial Clarifications & Placement of PO for Junction Boxes | 9 | 0 | 2024-09-23 | 2024-10-11 | 23-Sep-24 A | 03-Oct-24 A
HVAC Equipment |  | 19 | 0 | 2024-04-08 | 2024-05-09 | 08-Apr-24 A | 09-May-24 A
Ordering |  | 19 | 0 | 2024-04-08 | 2024-05-09 | 08-Apr-24 A | 09-May-24 A
HP-ME-0860 | RFQ, Receipt of Bid for HVAC Equipment | 1 | 0 | 2024-04-08 | 2024-04-15 | 08-Apr-24 A | 15-Apr-24 A
HP-ME-0870 | Prepare TBE and Company approval for HVAC Equipment | 12 | 0 | 2024-04-17 | 2024-05-03 | 17-Apr-24 A | 03-May-24 A
HP-ME-0880 | Commercial Clarifications & Placement of PO for HVAC Equipment | 4 | 0 | 2024-05-03 | 2024-05-09 | 03-May-24 A | 09-May-24 A
Distribution Transformer |  | 92 | 0 | 2023-12-04 | 2024-04-19 | 04-Dec-23 A | 19-Apr-24 A
Ordering |  | 92 | 0 | 2023-12-04 | 2024-04-19 | 04-Dec-23 A | 19-Apr-24 A
HP-ME-0460 | RFQ, Receipt of Bid for Distribution Transformer | 1 | 0 | 2023-12-04 | 2023-12-05 | 04-Dec-23 A | 05-Dec-23 A
HP-ME-0470 | Prepare TBE and Company approval for Distribution Transformer | 42 | 0 | 2024-01-05 | 2024-03-05 | 05-Jan-24 A | 05-Mar-24 A
HP-ME-0480 | Commercial Clarifications & Placement of PO for Distribution Transformer | 26 | 0 | 2024-03-06 | 2024-04-19 | 06-Mar-24 A | 19-Apr-24 A
Access Switch, Fiber Optic Patch Panel and Media Converter |  | 68 | 0 | 2024-02-26 | 2024-06-07 | 26-Feb-24 A | 07-Jun-24 A
Ordering |  | 68 | 0 | 2024-02-26 | 2024-06-07 | 26-Feb-24 A | 07-Jun-24 A
HP-ME-0660 | RFQ, Receipt of Bid for Access Switch, Fiber Optic Patch Panel and Media Converter | 9 | 0 | 2024-02-26 | 2024-03-08 | 26-Feb-24 A | 08-Mar-24 A
HP-ME-0670 | Prepare TBE and Company approval for Access Switch, Fiber Optic Patch Panel and Media Converter | 18 | 0 | 2024-05-03 | 2024-05-29 | 03-May-24 A | 29-May-24 A
HP-ME-0680 | Commercial Clarifications & Placement of PO for Access Switch, Fiber Optic Patch Panel and Media Converter | 6 | 0 | 2024-05-30 | 2024-06-07 | 30-May-24 A | 07-Jun-24 A
Fire Supression System |  | 61 | 0 | 2024-06-10 | 2024-09-20 | 10-Jun-24 A | 06-Sep-24 A
Ordering |  | 61 | 0 | 2024-06-10 | 2024-09-20 | 10-Jun-24 A | 06-Sep-24 A
HP-ME-0910 | RFQ, Receipt of Bid for Fire Suppression System | 5 | 0 | 2024-06-10 | 2024-06-17 | 10-Jun-24 A | 17-Jun-24 A
HP-ME-0920 | Prepare TBE and Company approval for Fire Suppression System | 16 | 0 | 2024-07-29 | 2024-09-06 | 15-Aug-24 A | 05-Sep-24 A
HP-ME-0930 | Commercial Clarifications & Placement of PO for Fire Suppression System | 1 | 0 | 2024-09-09 | 2024-09-20 | 06-Sep-24 A | 06-Sep-24 A
Fire Fighting & Safety Equipment |  | 83 | 0 | 2024-05-23 | 2024-09-20 | 23-May-24 A | 20-Sep-24 A
Ordering |  | 83 | 0 | 2024-05-23 | 2024-09-20 | 23-May-24 A | 20-Sep-24 A
HP-ME-0960 | RFQ, Receipt of Bid for Fire Fighting & Safety Equipment | 17 | 0 | 2024-05-23 | 2024-06-15 | 23-May-24 A | 15-Jun-24 A
HP-ME-0970 | Prepare TBE and Company approval for Fire Fighting & Safety Equipment | 10 | 0 | 2024-07-29 | 2024-09-06 | 30-Aug-24 A | 13-Sep-24 A
HP-ME-0980 | Commercial Clarifications & Placement of PO for Fire Fighting & Safety Equipment | 5 | 0 | 2024-09-09 | 2024-09-20 | 16-Sep-24 A | 20-Sep-24 A
Lifting Equipment |  | 87 | 0 | 2024-04-19 | 2024-10-07 | 19-Apr-24 A | 23-Aug-24 A
Ordering |  | 87 | 0 | 2024-04-19 | 2024-10-07 | 19-Apr-24 A | 23-Aug-24 A
HP-ME-1360 | RFQ, Receipt of Bid for Lifting Equipment | 12 | 0 | 2024-04-19 | 2024-05-07 | 19-Apr-24 A | 07-May-24 A
HP-ME-1380 | Prepare TBE and Company approval for Lifting Equipment | 31 | 0 | 2024-06-17 | 2024-09-16 | 17-Jun-24 A | 02-Aug-24 A
HP-ME-1370 | Commercial Clarifications & Placement of PO for Lifting Equipment | 15 | 0 | 2024-09-17 | 2024-10-07 | 03-Aug-24 A | 23-Aug-24 A
Pipeline Material |  | 227 | 0 | 2023-08-03 | 2024-07-01 | 03-Aug-23 A | 01-Jul-24 A
Line Pipes |  | 16 | 0 | 2023-08-03 | 2023-08-25 | 03-Aug-23 A | 25-Aug-23 A
Ordering |  | 16 | 0 | 2023-08-03 | 2023-08-25 | 03-Aug-23 A | 25-Aug-23 A
HP-ME-1020 | RFQ, Receipt of Bid for Line Pipes (Coated) | 5 | 0 | 2023-08-03 | 2023-08-10 | 03-Aug-23 A | 10-Aug-23 A
HP-ME-1030 | Prepare TBE and Company approval for Line Pipes (Coated) | 10 | 0 | 2023-08-10 | 2023-08-24 | 10-Aug-23 A | 24-Aug-23 A
HP-ME-1040 | Commercial Clarifications & Placement of PO for Line Pipes (Coated) | 0 | 0 | 2023-08-25 | 2023-08-25 | 25-Aug-23 A | 25-Aug-23 A
Pig Signler |  | 56 | 0 | 2024-02-26 | 2024-05-22 | 26-Feb-24 A | 22-May-24 A
Ordering |  | 56 | 0 | 2024-02-26 | 2024-05-22 | 26-Feb-24 A | 22-May-24 A
HP-ME-1120 | RFQ, Receipt of Bid for Pig Signaler | 18 | 0 | 2024-02-26 | 2024-03-22 | 26-Feb-24 A | 22-Mar-24 A
HP-ME-1130 | Prepare TBE and Company approval for Pig Signaler | 30 | 0 | 2024-03-18 | 2024-05-07 | 18-Mar-24 A | 07-May-24 A
HP-ME-1140 | Commercial Clarifications & Placement of PO for Pig Signaler | 10 | 0 | 2024-05-08 | 2024-05-22 | 08-May-24 A | 22-May-24 A
Hot Induction Bend |  | 19 | 0 | 2023-09-05 | 2023-10-02 | 05-Sep-23 A | 02-Oct-23 A
Ordering |  | 19 | 0 | 2023-09-05 | 2023-10-02 | 05-Sep-23 A | 02-Oct-23 A
HP-ME-1170 | RFQ, Receipt of Bid for Hot Incution Bend | 9 | 0 | 2023-09-05 | 2023-09-18 | 05-Sep-23 A | 18-Sep-23 A
HP-ME-1180 | Prepare TBE and Company approval for Hot Incution Bend | 3 | 0 | 2023-09-22 | 2023-09-27 | 22-Sep-23 A | 27-Sep-23 A
HP-ME-1190 | Commercial Clarifications & Placement of PO for Hot Induction Bend | 2 | 0 | 2023-09-28 | 2023-10-02 | 28-Sep-23 A | 02-Oct-23 A
Isolating Joints |  | 39 | 0 | 2023-09-29 | 2023-11-23 | 29-Sep-23 A | 23-Nov-23 A
Ordering |  | 39 | 0 | 2023-09-29 | 2023-11-23 | 29-Sep-23 A | 23-Nov-23 A
HP-ME-1220 | RFQ, Receipt of Bid for Isolating Joints | 7 | 0 | 2023-09-29 | 2023-10-10 | 29-Sep-23 A | 10-Oct-23 A
HP-ME-1230 | Prepare TBE and Company approval for Isolating Joints | 25 | 0 | 2023-10-11 | 2023-11-15 | 11-Oct-23 A | 15-Nov-23 A
HP-ME-1240 | Commercial Clarifications & Placement of PO for Isolating Joints | 5 | 0 | 2023-11-16 | 2023-11-23 | 16-Nov-23 A | 23-Nov-23 A
Pigging & Split Tee |  | 58 | 0 | 2024-01-26 | 2024-04-25 | 26-Jan-24 A | 25-Apr-24 A
Ordering |  | 58 | 0 | 2024-01-26 | 2024-04-25 | 26-Jan-24 A | 25-Apr-24 A
HP-ME-1270 | RFQ, Receipt of Bid for Pigging & Split Tee | 10 | 0 | 2024-01-26 | 2024-02-09 | 26-Jan-24 A | 09-Feb-24 A
HP-ME-1280 | Prepare TBE and Company approval for Pigging & Split Tee | 20 | 0 | 2024-02-26 | 2024-03-26 | 26-Feb-24 A | 26-Mar-24 A
HP-ME-1290 | Commercial Clarifications & Placement of PO for Pigging & Split Tee | 14 | 0 | 2024-03-31 | 2024-04-25 | 31-Mar-24 A | 25-Apr-24 A
Anchor Flanges |  | 53 | 0 | 2024-04-15 | 2024-07-01 | 15-Apr-24 A | 01-Jul-24 A
Ordering |  | 53 | 0 | 2024-04-15 | 2024-07-01 | 15-Apr-24 A | 01-Jul-24 A
HP-ME-1310 | RFQ, Receipt of Bid for Anchor Flanges | 19 | 0 | 2024-04-15 | 2024-05-10 | 15-Apr-24 A | 10-May-24 A
HP-ME-1320 | Prepare TBE and Company approval for Anchor Flanges | 2 | 0 | 2024-06-14 | 2024-06-21 | 14-Jun-24 A | 21-Jun-24 A
HP-ME-1300 | Commercial Clarifications & Placement of PO for Anchor Flanges | 6 | 0 | 2024-06-22 | 2024-07-01 | 22-Jun-24 A | 01-Jul-24 A
Hot Tapping |  | 38 | 0 | 2024-01-29 | 2024-03-22 | 29-Jan-24 A | 22-Mar-24 A
HS-GN-0190 | RFQ, Receipt of Bid for - Hot Tapping | 9 | 0 | 2024-01-29 | 2024-02-09 | 29-Jan-24 A | 09-Feb-24 A
HS-GN-0220 | + | 13 | 0 | 2024-02-26 | 2024-03-15 | 26-Feb-24 A | 15-Mar-24 A
HS-GN-0230 | Commercial Clarifications & Placement of PO- Hot Tapping | 18 | 0 | 2024-02-26 | 2024-03-22 | 26-Feb-24 A | 22-Mar-24 A
Bulk Material |  | 298 | 50 | 2023-10-30 | 2025-01-08 | 30-Oct-23 A | 2025-01-08 | 142
Power & Control Cables |  | 81 | 0 | 2024-04-29 | 2024-09-13 | 29-Apr-24 A | 23-Aug-24 A
Ordering |  | 81 | 0 | 2024-04-29 | 2024-09-13 | 29-Apr-24 A | 23-Aug-24 A
HP-BK-0010 | RFQ, Receipt of Bid for Power & Control Cables | 4 | 0 | 2024-04-29 | 2024-05-03 | 29-Apr-24 A | 03-May-24 A
HP-BK-0020 | Prepare TBE and Company approval for Power & Control Cables | 69 | 0 | 2024-05-03 | 2024-08-30 | 03-May-24 A | 13-Aug-24 A
HP-BK-0030 | Commercial Clarifications & Placement of PO for Power & Control Cables | 8 | 0 | 2024-09-02 | 2024-09-13 | 14-Aug-24 A | 23-Aug-24 A
Cable Trays |  | 42 | 0 | 2024-07-29 | 2024-10-11 | 30-Jul-24 A | 25-Sep-24 A
Ordering |  | 42 | 0 | 2024-07-29 | 2024-10-11 | 30-Jul-24 A | 25-Sep-24 A
HP-BK-0110 | RFQ, Receipt of Bid for Cable Trays | 9 | 0 | 2024-07-29 | 2024-08-09 | 30-Jul-24 A | 11-Aug-24 A
HP-BK-0120 | Prepare TBE and Company approval for Cable Trays | 12 | 0 | 2024-08-12 | 2024-09-27 | 14-Aug-24 A | 29-Aug-24 A
HP-BK-0130 | Commercial Clarifications & Placement of PO for Cable Trays | 16 | 0 | 2024-09-30 | 2024-10-11 | 04-Sep-24 A | 25-Sep-24 A
Earthing |  | 136 | 10 | 2024-04-29 | 2024-10-04 | 29-Apr-24 A | 2024-11-08 | 52
Ordering |  | 136 | 10 | 2024-04-29 | 2024-10-04 | 29-Apr-24 A | 2024-11-08 | 52
HP-BK-0160 | RFQ, Receipt of Bid for Earthing Material | 6 | 0 | 2024-04-29 | 2024-05-06 | 29-Apr-24 A | 06-May-24 A
HP-BK-0170 | Prepare TBE and Company approval for Earthing Material | 74 | 0 | 2024-05-06 | 2024-09-20 | 06-May-24 A | 22-Aug-24 A
HP-BK-0180 | Commercial Clarifications & Placement of PO for Earthing Material | 10 | 10 | 2024-09-23 | 2024-10-04 | 2024-10-28 | 2024-11-08 | 52
Manual/Ball/ Globe/ Check/ Plug Valves |  | 81 | 0 | 2023-12-01 | 2024-03-29 | 01-Dec-23 A | 29-Mar-24 A
Ordering |  | 81 | 0 | 2023-12-01 | 2024-03-29 | 01-Dec-23 A | 29-Mar-24 A
HP-ME-1070 | RFQ, Receipt of Bid for Manual/Ball/ Globe/ Check/ Plug Valves | 38 | 0 | 2023-12-01 | 2024-01-26 | 01-Dec-23 A | 26-Jan-24 A
HP-ME-1080 | Prepare TBE and Company approval for Manual/ Ball/ Globe/ Check/ Plug Valves | 3 | 0 | 2024-03-16 | 2024-03-22 | 16-Mar-24 A | 22-Mar-24 A
HP-ME-1090 | Commercial Clarifications & Placement of PO for Manual/ Ball/ Globe/ Check/ Plug Valves | 3 | 0 | 2024-03-23 | 2024-03-29 | 23-Mar-24 A | 29-Mar-24 A
Cable Gland & Termination |  | 25 | 0 | 2024-08-12 | 2024-10-25 | 12-Aug-24 A | 13-Sep-24 A
Ordering |  | 25 | 0 | 2024-08-12 | 2024-10-25 | 12-Aug-24 A | 13-Sep-24 A
HP-BK-550 | RFQ, Receipt of Bid for Cable Gland & Termination | 10 | 0 | 2024-08-12 | 2024-08-23 | 12-Aug-24 A | 23-Aug-24 A
HP-BK-540 | Prepare TBE and Company approval for Cable Gland & Termination | 6 | 0 | 2024-08-26 | 2024-10-18 | 26-Aug-24 A | 02-Sep-24 A
HP-BK-530 | Commercial Clarifications & Placement of PO for Cable Gland & Termination | 9 | 0 | 2024-10-21 | 2024-10-25 | 03-Sep-24 A | 13-Sep-24 A
MCT |  | 132 | 25 | 2024-05-24 | 2024-10-04 | 24-May-24 A | 2024-11-29 | 23
Ordering |  | 132 | 25 | 2024-05-24 | 2024-10-04 | 24-May-24 A | 2024-11-29 | 23
HP-BK-0210 | RFQ, Receipt of Bid for MCT | 6 | 0 | 2024-05-31 | 2024-06-09 | 31-May-24 A | 09-Jun-24 A
HP-BK-0220 | Prepare TBE and Company approval for MCT | 127 | 20 | 2024-05-24 | 2024-09-27 | 24-May-24 A | 2024-11-22 | 23
HP-BK-0230 | Commercial Clarifications & Placement of PO for MCT | 5 | 5 | 2024-09-30 | 2024-10-04 | 2024-11-25 | 2024-11-29 | 23
Modification of Existing CTMM |  | 77 | 0 | 2023-10-30 | 2024-02-16 | 30-Oct-23 A | 16-Feb-24 A
HS-GN-0250 | RFQ, Receipt of Bid - Modification of Exiting CTMM | 22 | 0 | 2023-10-30 | 2023-11-29 | 30-Oct-23 A | 29-Nov-23 A
HS-GN-0280 | Prepare TBE and Company approval - Modification of Exiting CTMM | 40 | 0 | 2023-11-30 | 2024-01-29 | 30-Nov-23 A | 29-Jan-24 A
HS-GN-0290 | Commercial Clarifications & Placement of PO - Modification of Exiting CTMM | 14 | 0 | 2024-01-29 | 2024-02-16 | 29-Jan-24 A | 16-Feb-24 A
Modification of Existing DCS |  | 90 | 0 | 2024-01-26 | 2024-06-10 | 26-Jan-24 A | 10-Jun-24 A
HS-GN-0430 | RFQ, Receipt of Bid - Modification of Existing DCS | 34 | 0 | 2024-01-26 | 2024-03-15 | 26-Jan-24 A | 15-Mar-24 A
HS-GN-0460 | Prepare TBE and Company approval - Modification of Existing DCS | 43 | 0 | 2024-03-31 | 2024-06-05 | 31-Mar-24 A | 05-Jun-24 A
HS-GN-0470 | Commercial Clarifications & Placement of PO - Modification of Existing DCS | 2 | 0 | 2024-06-06 | 2024-06-10 | 06-Jun-24 A | 10-Jun-24 A
Modification of Existing SMC/RTU |  | 91 | 0 | 2024-01-26 | 2024-08-09 | 26-Jan-24 A | 10-Jun-24 A
HS-GN-0370 | RFQ, Receipt of Bid - Modification of Exiting SMC / SCADA | 34 | 0 | 2024-01-26 | 2024-03-15 | 26-Jan-24 A | 15-Mar-24 A
HS-GN-0400 | Prepare TBE and Company approval - Modification of Exiting SMC / SCADA | 38 | 0 | 2024-04-11 | 2024-06-05 | 11-Apr-24 A | 05-Jun-24 A
HS-GN-0410 | Commercial Clarifications & Placement of PO - Modification of Exiting SMC / SCADA | 3 | 0 | 2024-07-29 | 2024-08-09 | 06-Jun-24 A | 10-Jun-24 A
Modification of Existing Telecom System |  | 129 | 0 | 2023-11-29 | 2024-06-07 | 29-Nov-23 A | 07-Jun-24 A
HS-GN-0310 | RFQ, Receipt of Bid - Modification of Existing Telecom System | 28 | 0 | 2023-11-29 | 2024-01-10 | 29-Nov-23 A | 10-Jan-24 A
HS-GN-0340 | Prepare TBE and Company approval - Modification of Existing Telecom System | 93 | 0 | 2024-01-11 | 2024-05-29 | 11-Jan-24 A | 29-May-24 A
HS-GN-0350 | Commercial Clarifications & Placement of PO - Modification of Existing Telecom System | 6 | 0 | 2024-05-30 | 2024-06-07 | 30-May-24 A | 07-Jun-24 A
Civil Bulk material |  | 153 | 15 | 2024-05-02 | 2024-10-18 | 02-May-24 A | 2024-12-10 | 40
Ordering |  | 153 | 15 | 2024-05-02 | 2024-10-18 | 02-May-24 A | 2024-12-10 | 40
HP-BK-0260 | 1st Civil Bulk material MTO | 12 | 0 | 2024-05-02 | 2024-05-19 | 02-May-24 A | 19-May-24 A
HP-BK-0270 | Final Civil Bulk material MTO | 15 | 15 | 2024-09-30 | 2024-10-18 | 2024-11-18 | 2024-12-10 | 40
Structural Bulk material |  | 45 | 45 | 2024-07-29 | 2024-10-18 | 2024-10-28 | 2024-12-31 | 28
Ordering |  | 45 | 45 | 2024-07-29 | 2024-10-18 | 2024-10-28 | 2024-12-31 | 28
HP-BK-0300 | 1st Structural Bulk material MTO | 15 | 15 | 2024-07-29 | 2024-08-16 | 2024-10-28 | 2024-11-15 | 14
HP-BK-0310 | Final Structural Bulk material MTO | 15 | 15 | 2024-09-30 | 2024-10-18 | 2024-12-11 | 2024-12-31 | 28
Piping Bulk material |  | 131 | 0 | 2024-03-31 | 2024-08-30 | 31-Mar-24 A | 10-Oct-24 A
Ordering |  | 131 | 0 | 2024-03-31 | 2024-08-30 | 31-Mar-24 A | 10-Oct-24 A
HP-BK-0340 | 1st Piping Bulk material MTO | 14 | 0 | 2024-03-31 | 2024-04-25 | 31-Mar-24 A | 25-Apr-24 A
HP-BK-0350 | Final Piping Bulk material MTO | 8 | 0 | 2024-08-26 | 2024-08-30 | 01-Oct-24 A | 10-Oct-24 A
Piping Special Items |  | 25 | 0 | 2024-07-29 | 2024-10-18 | 29-Jul-24 A | 30-Aug-24 A
Ordering |  | 25 | 0 | 2024-07-29 | 2024-10-18 | 29-Jul-24 A | 30-Aug-24 A
HP-BK-520 | 1st Piping Special Items MTO | 15 | 0 | 2024-07-29 | 2024-08-16 | 29-Jul-24 A | 16-Aug-24 A
HP-BK-510 | Final Piping Special Items MTO | 10 | 0 | 2024-10-14 | 2024-10-18 | 17-Aug-24 A | 30-Aug-24 A
Pipeline Bulk material |  | 21 | 0 | 2024-07-29 | 2024-08-02 | 29-Jul-24 A | 26-Aug-24 A
Ordering |  | 21 | 0 | 2024-07-29 | 2024-08-02 | 29-Jul-24 A | 26-Aug-24 A
HP-BK-0390 | Final Pipeline Bulk material MTO | 5 | 0 | 2024-07-29 | 2024-08-02 | 29-Jul-24 A | 02-Aug-24 A
HP-BK-0380 | 1st Pipeline Bulk material MTO | 14 | 0 | 2024-07-29 | 2024-08-02 | 07-Aug-24 A | 26-Aug-24 A
Electrical Bulk material |  | 100 | 15 | 2024-08-19 | 2024-11-08 | 19-Aug-24 A | 2025-01-08 | 69
Ordering |  | 100 | 15 | 2024-08-19 | 2024-11-08 | 19-Aug-24 A | 2025-01-08 | 69
HP-BK-0420 | 1st Electrical Bulk material MTO | 29 | 0 | 2024-08-19 | 2024-09-06 | 19-Aug-24 A | 26-Sep-24 A
HP-BK-0430 | Final Electrical Bulk material MTO | 59 | 15 | 2024-10-21 | 2024-11-08 | 15-Oct-24 A | 2025-01-08 | 69
Instrumentation Bulk material |  | 39 | 15 | 2024-08-12 | 2024-11-15 | 01-Oct-24 A | 2024-11-22 | 91
Ordering |  | 39 | 15 | 2024-08-12 | 2024-11-15 | 01-Oct-24 A | 2024-11-22 | 91
HP-BK-0460 | 1st Instrumentation Bulk material MTO | 5 | 0 | 2024-08-12 | 2024-09-20 | 15-Oct-24 A | 21-Oct-24 A
HP-BK-0470 | Final Instrumentation Bulk material MTO | 39 | 15 | 2024-10-28 | 2024-11-15 | 01-Oct-24 A | 2024-11-22 | 91
Telecom Bulk material |  | 59 | 10 | 2024-08-12 | 2025-01-08 | 01-Oct-24 A | 2024-12-24 | 84
Ordering |  | 59 | 10 | 2024-08-12 | 2025-01-08 | 01-Oct-24 A | 2024-12-24 | 84
HP-BK-0500 | 1st Telecom Bulk material MTO | 10 | 0 | 2024-08-12 | 2024-09-20 | 01-Oct-24 A | 14-Oct-24 A
HP-BK-0510 | Final Telecom Bulk material MTO | 49 | 10 | 2024-12-25 | 2025-01-08 | 15-Oct-24 A | 2024-12-24 | 84
Subcontracting |  | 227 | 0 | 2023-07-13 | 2024-06-07 | 13-Jul-23 A | 07-Jun-24 A
Subcontracting Services (General / Engineering) |  | 213 | 0 | 2023-07-13 | 2024-05-20 | 13-Jul-23 A | 20-May-24 A
HSE Studies |  | 46 | 0 | 2023-07-24 | 2023-09-26 | 24-Jul-23 A | 26-Sep-23 A
HS-GN-0070 | Prepare/Issue Scope of Work - HSE Studies | 4 | 0 | 2023-07-24 | 2023-07-28 | 24-Jul-23 A | 28-Jul-23 A
HS-GN-0080 | Receive Bids - HSE Studies | 4 | 0 | 2023-08-01 | 2023-08-07 | 01-Aug-23 A | 07-Aug-23 A
HS-GN-0100 | Complete Evaluation (Internal) - HSE Studies | 4 | 0 | 2023-08-26 | 2023-09-01 | 26-Aug-23 A | 01-Sep-23 A
HS-GN-0110 | Place LOA/FOA - HSE Studies | 17 | 0 | 2023-09-01 | 2023-09-26 | 01-Sep-23 A | 26-Sep-23 A
Topographical survey & Geotechnical Investigation |  | 37 | 0 | 2023-07-13 | 2023-09-05 | 13-Jul-23 A | 05-Sep-23 A
HS-GN-0130 | Prepare/Issue Scope of Work - Topographical survey & Geotechnical Investigation | 9 | 0 | 2023-07-13 | 2023-07-27 | 13-Jul-23 A | 27-Jul-23 A
HS-GN-0140 | Receive Bids - Topographical survey & Geotechnical Investigation | 4 | 0 | 2023-08-01 | 2023-08-07 | 01-Aug-23 A | 07-Aug-23 A
HS-GN-0160 | Complete Evaluation (Internal) - Topographical survey & Geotechnical Investigation | 4 | 0 | 2023-08-26 | 2023-09-01 | 26-Aug-23 A | 01-Sep-23 A
HS-GN-0170 | Place LOA/FOA - Topographical survey & Geotechnical Investigation | 2 | 0 | 2023-09-01 | 2023-09-05 | 01-Sep-23 A | 05-Sep-23 A
Cathodic Protection Work |  | 120 | 0 | 2023-11-22 | 2024-05-20 | 22-Nov-23 A | 20-May-24 A
HS-GN-0490 | Prepare/Issue Scope of Work - Cathodic Protection Work | 27 | 0 | 2023-11-22 | 2024-01-02 | 22-Nov-23 A | 02-Jan-24 A
HS-GN-0500 | Receive Bids - Cathodic Protection Work | 13 | 0 | 2024-02-26 | 2024-03-15 | 26-Feb-24 A | 15-Mar-24 A
HS-GN-0520 | Complete Evaluation (Internal) - Cathodic Protection Work | 9 | 0 | 2024-03-15 | 2024-03-29 | 15-Mar-24 A | 29-Mar-24 A
HS-GN-0530 | Place LOA/FOA - Cathodic Protection Work | 1 | 0 | 2024-05-17 | 2024-05-20 | 17-May-24 A | 20-May-24 A
Subcontracting Services (Construction) |  | 194 | 0 | 2023-08-30 | 2024-06-07 | 30-Aug-23 A | 07-Jun-24 A
NDRC |  | 56 | 0 | 2023-08-31 | 2023-11-17 | 31-Aug-23 A | 17-Nov-23 A
HS-CN-0060 | NDRC RFQ & Quotation Receipt | 5 | 0 | 2023-08-31 | 2023-09-07 | 31-Aug-23 A | 07-Sep-23 A
HS-CN-0080 | NDRC Complete Evaluation (Internal) | 19 | 0 | 2023-09-08 | 2023-10-05 | 08-Sep-23 A | 05-Oct-23 A
HS-CN-0090 | NDRC Subcontract Award | 30 | 0 | 2023-10-06 | 2023-11-17 | 06-Oct-23 A | 17-Nov-23 A
Testing & Precommissioning |  | 120 | 0 | 2023-11-22 | 2024-05-20 | 22-Nov-23 A | 20-May-24 A
HS-CN-0110 | Testing & Precommissioning RFQ & Quotation Receipt | 27 | 0 | 2023-11-22 | 2024-01-02 | 22-Nov-23 A | 02-Jan-24 A
HS-CN-0130 | Testing & Precommissioning Complete Evaluation (Internal) | 35 | 0 | 2024-03-06 | 2024-05-02 | 06-Mar-24 A | 02-May-24 A
HS-CN-0140 | Testing & Precommissioning Subcontract Award | 11 | 0 | 2024-05-03 | 2024-05-20 | 03-May-24 A | 20-May-24 A
NDT / PWHT |  | 51 | 0 | 2023-09-07 | 2023-11-17 | 07-Sep-23 A | 17-Nov-23 A
HS-CN-0160 | NDT / PWHT RFQ & Quotation Receipt | 20 | 0 | 2023-09-07 | 2023-10-05 | 07-Sep-23 A | 05-Oct-23 A
HS-CN-0180 | NDT / PWHT Complete Evaluation (Internal) | 20 | 0 | 2023-10-06 | 2023-11-03 | 06-Oct-23 A | 03-Nov-23 A
HS-CN-0190 | NDT / PWHT Subcontract Award | 10 | 0 | 2023-11-03 | 2023-11-17 | 03-Nov-23 A | 17-Nov-23 A
CP Drilling & Earthing Drilling |  | 87 | 0 | 2023-11-22 | 2024-03-27 | 22-Nov-23 A | 27-Mar-24 A
HS-CN-0210 | CP Drilling & Earthing Drilling RFQ & Quotation Receipt | 27 | 0 | 2023-11-22 | 2024-01-02 | 22-Nov-23 A | 02-Jan-24 A
HS-CN-0230 | CP Drilling & Earthing Drilling Complete Evaluation (Internal) | 8 | 0 | 2024-01-03 | 2024-01-15 | 03-Jan-24 A | 15-Jan-24 A
HS-CN-0240 | CP Drilling & Earthing Drilling Subcontract Award | 21 | 0 | 2024-02-26 | 2024-03-27 | 26-Feb-24 A | 27-Mar-24 A
FOC Splicing / Termination |  | 61 | 0 | 2023-12-22 | 2024-03-20 | 22-Dec-23 A | 20-Mar-24 A
HS-CN-0260 | FOC Splicing / Termination RFQ & Quotation Receipt | 5 | 0 | 2023-12-22 | 2023-12-29 | 22-Dec-23 A | 29-Dec-23 A
HS-CN-0280 | FOC Splicing / Termination Complete Evaluation (Internal) | 12 | 0 | 2024-02-26 | 2024-03-13 | 26-Feb-24 A | 13-Mar-24 A
HS-CN-0290 | FOC Splicing / Termination Subcontract Award | 4 | 0 | 2024-03-14 | 2024-03-20 | 14-Mar-24 A | 20-Mar-24 A
OHPL |  | 17 | 0 | 2024-01-03 | 2024-01-26 | 03-Jan-24 A | 26-Jan-24 A
HS-CN-0410 | OHPL RFQ & Quotation Receipt | 3 | 0 | 2024-01-03 | 2024-01-07 | 03-Jan-24 A | 07-Jan-24 A
HS-CN-0430 | OHPL Complete Evaluation (Internal) | 10 | 0 | 2024-01-08 | 2024-01-22 | 08-Jan-24 A | 22-Jan-24 A
HS-CN-0440 | OHPL Subcontract Award | 3 | 0 | 2024-01-23 | 2024-01-26 | 23-Jan-24 A | 26-Jan-24 A
Earthworks |  | 52 | 0 | 2023-08-31 | 2023-11-13 | 31-Aug-23 A | 13-Nov-23 A
HS-CN-0460 | Earthworks RFQ & Quotation Receipt | 20 | 0 | 2023-08-31 | 2023-09-28 | 31-Aug-23 A | 28-Sep-23 A
HS-CN-0480 | Earthworks Complete Evaluation (Internal) | 4 | 0 | 2023-09-29 | 2023-10-05 | 29-Sep-23 A | 05-Oct-23 A
HS-CN-0490 | Earthworks Subcontract Award | 26 | 0 | 2023-10-06 | 2023-11-13 | 06-Oct-23 A | 13-Nov-23 A
Hot Tapping |  | 61 | 0 | 2023-09-16 | 2023-12-13 | 16-Sep-23 A | 13-Dec-23 A
HS-CN-0510 | Hot Tapping RFQ & Quotation Receipt | 19 | 0 | 2023-09-16 | 2023-10-13 | 16-Sep-23 A | 13-Oct-23 A
HS-CN-0530 | Hot Tapping Complete Evaluation (Internal) | 25 | 0 | 2023-10-13 | 2023-11-17 | 13-Oct-23 A | 17-Nov-23 A
HS-CN-0540 | Hot Tapping Subcontract Award | 1 | 0 | 2023-12-12 | 2023-12-13 | 12-Dec-23 A | 13-Dec-23 A
Building |  | 99 | 0 | 2023-12-13 | 2024-05-09 | 13-Dec-23 A | 09-May-24 A
HS-CN-0560 | Building RFQ & Quotation Receipt | 14 | 0 | 2023-12-13 | 2024-01-03 | 13-Dec-23 A | 03-Jan-24 A
HS-CN-0580 | Building Complete Evaluation (Internal) | 42 | 0 | 2024-02-26 | 2024-05-02 | 26-Feb-24 A | 02-May-24 A
HS-CN-0590 | Building Subcontract Award | 4 | 0 | 2024-05-03 | 2024-05-09 | 03-May-24 A | 09-May-24 A
E&I Works |  | 123 | 0 | 2023-11-08 | 2024-05-09 | 08-Nov-23 A | 09-May-24 A
HS-CN-0610 | E&I Works RFQ & Quotation Receipt | 22 | 0 | 2023-11-08 | 2023-12-11 | 08-Nov-23 A | 11-Dec-23 A
HS-CN-0630 | E&I Works Complete Evaluation (Internal) | 14 | 0 | 2024-03-31 | 2024-04-25 | 31-Mar-24 A | 25-Apr-24 A
HS-CN-0640 | E&I Works Subcontract Award | 10 | 0 | 2024-04-25 | 2024-05-09 | 25-Apr-24 A | 09-May-24 A
Fence Works |  | 123 | 0 | 2023-12-08 | 2024-06-07 | 08-Dec-23 A | 07-Jun-24 A
HS-CN-0660 | Fence Works RFQ & Quotation Receipt | 14 | 0 | 2023-12-08 | 2023-12-28 | 08-Dec-23 A | 28-Dec-23 A
HS-CN-0680 | Fence Works Complete Evaluation (Internal) | 39 | 0 | 2024-02-26 | 2024-04-29 | 26-Feb-24 A | 29-Apr-24 A
HS-CN-0690 | Fence Works Subcontract Award | 28 | 0 | 2024-04-30 | 2024-06-07 | 30-Apr-24 A | 07-Jun-24 A
Pipe Internal Coating |  | 21 | 0 | 2023-09-11 | 2023-10-10 | 11-Sep-23 A | 10-Oct-23 A
HS-CN-750 | Pipe Internal Coating RFQ & Quotation Receipt | 7 | 0 | 2023-09-11 | 2023-09-20 | 11-Sep-23 A | 20-Sep-23 A
HS-CN-760 | Pipe Internal Coating Complete Evaluation (Internal) | 11 | 0 | 2023-09-20 | 2023-10-05 | 20-Sep-23 A | 05-Oct-23 A
HS-CN-730 | Pipe Internal Coating Subcontract Award | 3 | 0 | 2023-10-05 | 2023-10-10 | 05-Oct-23 A | 10-Oct-23 A
Automatic Welding |  | 63 | 0 | 2023-08-30 | 2023-11-25 | 30-Aug-23 A | 25-Nov-23 A
HS-CN-710 | Automatic Welding RFQ & Quotation Receipt | 26 | 0 | 2023-08-30 | 2023-10-05 | 30-Aug-23 A | 05-Oct-23 A
HS-CN-720 | Automatic Welding Complete Evaluation (Internal) | 34 | 0 | 2023-10-06 | 2023-11-23 | 06-Oct-23 A | 23-Nov-23 A
HS-CN-690 | Automatic Welding Subcontract Award | 8 | 0 | 2023-11-15 | 2023-11-25 | 15-Nov-23 A | 25-Nov-23 A
Manufacturing & Delivery |  | 681 | 271 | 2023-09-12 | 2025-07-17 | 12-Sep-23 A | 2025-07-23 | 77
Equipment / Tagged Items |  | 516 | 271 | 2024-02-24 | 2025-07-17 | 24-Feb-24 A | 2025-07-23 | 77
Long Lead Items |  | 516 | 271 | 2024-02-24 | 2025-06-30 | 24-Feb-24 A | 2025-07-23 | 77
Custody Metering Skid |  | 425 | 198 | 2024-03-13 | 2025-05-11 | 13-Mar-24 A | 2025-05-11 | 151
Manufacturing & Ready for Dispatch |  | 408 | 181 | 2024-03-13 | 2025-04-24 | 13-Mar-24 A | 2025-04-24 | 152
HM-ME-0010 | Vendor Document Review of Custody Metering Skid | 137 | 0 | 2024-03-13 | 2024-08-10 | 13-Mar-24 A | 27-Jul-24 A
HM-ME-0020 | Manufacturing & Assembly of Custody Metering Skid | 294 | 156 | 2024-08-11 | 2025-03-30 | 10-Jun-24 A | 2025-03-30 | 152
HM-ME-0030 | Factory Acceptance Test of Custody Metering Skid | 14 | 14 | 2025-03-31 | 2025-04-13 | 2025-03-31 | 2025-04-13 | 152
HM-ME-0040 | Packaging & Final Inspection-Custody Metering Skid | 7 | 7 | 2025-04-14 | 2025-04-20 | 2025-04-14 | 2025-04-20 | 152
HM-ME-0050 | Ready for Dispatch of Custody Metering Skid | 4 | 4 | 2025-04-21 | 2025-04-24 | 2025-04-21 | 2025-04-24 | 152
Delivery & receipt at Site |  | 17 | 17 | 2025-04-25 | 2025-05-11 | 2025-04-25 | 2025-05-11 | 151
HM-ME-0070 | Transportation/ Custom Clearance/ Delivery at site of Custody Metering Skid | 7 | 7 | 2025-04-25 | 2025-05-01 | 2025-04-25 | 2025-05-01 | 152
HM-ME-0080 | Receipt at site and inspection of Custody Metering Skid | 7 | 7 | 2025-05-02 | 2025-05-11 | 2025-05-02 | 2025-05-11 | 125
Pressure Reduction Skid |  | 407 | 215 | 2024-04-17 | 2025-05-28 | 17-Apr-24 A | 2025-05-28 | 99
Manufacturing & Ready for Dispatch |  | 392 | 200 | 2024-04-17 | 2025-05-13 | 17-Apr-24 A | 2025-05-13 | 99
HM-ME-0110 | Vendor Document Review of Pressure Reduction Skid | 73 | 0 | 2024-04-17 | 2024-08-25 | 17-Apr-24 A | 28-Jun-24 A
HM-ME-0120 | Manufacturing & Assembly of Pressure Reduction Skid | 312 | 175 | 2024-05-23 | 2025-04-18 | 11-Jun-24 A | 2025-04-18 | 99
HM-ME-0130 | Factory Acceptance Test of Pressure Reduction Skid | 14 | 14 | 2025-04-19 | 2025-05-02 | 2025-04-19 | 2025-05-02 | 99
HM-ME-0140 | Packaging & Final Inspection - Pressure Reduction Skid | 7 | 7 | 2025-05-03 | 2025-05-09 | 2025-05-03 | 2025-05-09 | 99
HM-ME-0150 | Ready for Dispatch of Pressure Reduction Skid | 4 | 4 | 2025-05-10 | 2025-05-13 | 2025-05-10 | 2025-05-13 | 99
Delivery & receipt at Site |  | 15 | 15 | 2025-05-14 | 2025-05-28 | 2025-05-14 | 2025-05-28 | 99
HM-ME-0170 | Transportation/ Custom Clearance/ Delivery at site of Pressure Reduction Skid | 7 | 7 | 2025-05-14 | 2025-05-20 | 2025-05-14 | 2025-05-20 | 99
HM-ME-0180 | Receipt at site and inspection of Pressure Reduction Skid | 7 | 7 | 2025-05-21 | 2025-05-28 | 2025-05-21 | 2025-05-28 | 81
Leak Detection System |  | 315 | 153 | 2024-05-17 | 2025-05-06 | 17-May-24 A | 2025-03-27 | 153
Manufacturing & Ready for Dispatch |  | 287 | 125 | 2024-05-17 | 2025-04-13 | 17-May-24 A | 2025-02-27 | 158
HM-ME-0210 | Vendor Document Review of Leak Detection System | 79 | 0 | 2024-05-17 | 2024-10-04 | 17-May-24 A | 03-Aug-24 A
HM-ME-0220 | Manufacturing & Assembly of Leak Detection System | 192 | 100 | 2024-10-05 | 2025-03-19 | 26-Jul-24 A | 2025-02-02 | 158
HM-ME-0230 | Factory Acceptance Test of Leak Detection System | 14 | 14 | 2025-03-20 | 2025-04-02 | 2025-02-03 | 2025-02-16 | 158
HM-ME-0240 | Packaging & Final Inspection - Leak Detection System | 7 | 7 | 2025-04-03 | 2025-04-09 | 2025-02-17 | 2025-02-23 | 158
HM-ME-0250 | Ready for Dispatch of Leak Detection System | 4 | 4 | 2025-04-10 | 2025-04-13 | 2025-02-24 | 2025-02-27 | 158
Delivery & receipt at Site |  | 28 | 28 | 2025-04-14 | 2025-05-06 | 2025-02-28 | 2025-03-27 | 153
HM-ME-0270 | Transportation/ Custom Clearance/ Delivery at site of Leak Detection System | 14 | 14 | 2025-04-14 | 2025-04-27 | 2025-02-28 | 2025-03-13 | 158
HM-ME-0280 | Receipt at site and inspection of Leak Detection System | 7 | 7 | 2025-04-28 | 2025-05-06 | 2025-03-14 | 2025-03-27 | 121
Filter Package |  | 322 | 118 | 2024-04-05 | 2025-02-20 | 05-Apr-24 A | 2025-02-20 | 171
Manufacturing & Ready for Dispatch |  | 307 | 103 | 2024-04-05 | 2025-02-05 | 05-Apr-24 A | 2025-02-05 | 171
HM-ME-0310 | Vendor Document Review of Filter Package | 71 | 0 | 2024-04-05 | 2024-09-04 | 05-Apr-24 A | 14-Jun-24 A
HM-ME-0320 | Manufacturing & Assembly of Filter Package | 218 | 87 | 2024-07-27 | 2025-01-20 | 17-Jun-24 A | 2025-01-20 | 171
HM-ME-0330 | Testing and Inspection of Filter Package | 6 | 6 | 2025-01-21 | 2025-01-26 | 2025-01-21 | 2025-01-26 | 171
HM-ME-0340 | Packaging & Final Inspection-Filter Package | 6 | 6 | 2025-01-27 | 2025-02-01 | 2025-01-27 | 2025-02-01 | 171
HM-ME-0350 | Ready for Dispatch of Filter Package | 4 | 4 | 2025-02-02 | 2025-02-05 | 2025-02-02 | 2025-02-05 | 171
Delivery & receipt at Site |  | 15 | 15 | 2025-02-06 | 2025-02-20 | 2025-02-06 | 2025-02-20 | 171
HM-ME-0370 | Transportation/ Custom Clearance/ Delivery at site of Filter Package | 7 | 7 | 2025-02-06 | 2025-02-12 | 2025-02-06 | 2025-02-12 | 171
HM-ME-0380 | Receipt at site and inspection of Filter Package | 7 | 7 | 2025-02-13 | 2025-02-20 | 2025-02-13 | 2025-02-20 | 128
Pig Launcers & Receivers |  | 383 | 138 | 2024-02-24 | 2025-03-12 | 24-Feb-24 A | 2025-03-12 | 105
Manufacturing & Ready for Dispatch |  | 319 | 74 | 2024-02-24 | 2025-01-07 | 24-Feb-24 A | 2025-01-07 | 105
HM-ME-0410 | Vendor Document Review of Pig Launchers & Receivers | 29 | 0 | 2024-02-24 | 2024-03-24 | 24-Feb-24 A | 24-Mar-24 A
HM-ME-0420 | Manufacturing & Assembly of Pig Launchers & Receivers | 213 | 56 | 2024-05-22 | 2024-12-20 | 22-May-24 A | 2024-12-20 | 105
HM-ME-0430 | Testing and Inspection of Pig Launchers & Receivers | 7 | 7 | 2024-12-21 | 2024-12-27 | 2024-12-21 | 2024-12-27 | 105
HM-ME-0440 | Packaging & Final Inspection-Pig Launchers & Receivers | 7 | 7 | 2024-12-28 | 2025-01-03 | 2024-12-28 | 2025-01-03 | 105
HM-ME-0450 | Ready for Dispatch of Pig Launchers & Receivers | 4 | 4 | 2025-01-04 | 2025-01-07 | 2025-01-04 | 2025-01-07 | 105
Delivery & receipt at Site |  | 64 | 64 | 2025-01-08 | 2025-03-12 | 2025-01-08 | 2025-03-12 | 105
HM-ME-0470 | Transportation/ Custom Clearance/ Delivery at site of Pig Launchers & Receivers (52" Line) | 35 | 35 | 2025-01-08 | 2025-02-11 | 2025-01-08 | 2025-02-11 | 126
HM-ME-0480 | Receipt at site and inspection of Pig Launchers & Receivers (52" Line) | 7 | 7 | 2025-02-12 | 2025-02-19 | 2025-02-12 | 2025-02-19 | 91
HM-ME-2380 | Transportation/ Custom Clearance/ Delivery at site of Pig Launchers & Receivers (56" Line) | 35 | 35 | 2025-01-29 | 2025-03-04 | 2025-01-29 | 2025-03-04 | 105
HM-ME-2390 | Receipt at site and inspection of Pig Launchers & Receivers (56" Line) | 8 | 8 | 2025-03-05 | 2025-03-12 | 2025-03-05 | 2025-03-12 | 105
Lifting Equipment |  | 221 | 207 | 2024-09-06 | 2025-04-27 | 18-Oct-24 A | 2025-05-26 | 112
Manufacturing & Ready for Dispatch |  | 206 | 192 | 2024-09-06 | 2025-04-11 | 18-Oct-24 A | 2025-05-11 | 112
HM-ME-2070 | Vendor Document Review of Filter Package | 29 | 15 | 2024-09-06 | 2024-10-06 | 18-Oct-24 A | 2024-11-15 | 112
HM-ME-2080 | Manufacturing & Assembly of Filter Package | 160 | 160 | 2024-10-06 | 2025-03-25 | 2024-11-15 | 2025-04-24 | 112
HM-ME-2090 | Testing and Inspection of Filter Package | 7 | 7 | 2025-03-25 | 2025-04-01 | 2025-04-24 | 2025-05-01 | 112
HM-ME-2100 | Packaging & Final Inspection-Filter Package | 6 | 6 | 2025-04-01 | 2025-04-07 | 2025-05-01 | 2025-05-07 | 112
HM-ME-2110 | Ready for Dispatch of Filter Package | 4 | 4 | 2025-04-07 | 2025-04-11 | 2025-05-07 | 2025-05-11 | 112
Delivery & receipt at Site |  | 15 | 15 | 2025-04-11 | 2025-04-27 | 2025-05-11 | 2025-05-26 | 112
HM-ME-2130 | Transportation/ Custom Clearance/ Delivery at site of Filter Package | 7 | 7 | 2025-04-11 | 2025-04-18 | 2025-05-11 | 2025-05-18 | 112
HM-ME-2120 | Receipt at site and inspection of Filter Package | 7 | 7 | 2025-04-20 | 2025-04-27 | 2025-05-19 | 2025-05-26 | 91
ROV/ GOV |  | 438 | 268 | 2024-05-09 | 2025-06-30 | 09-May-24 A | 2025-07-20 | 19
Manufacturing & Ready for Dispatch |  | 369 | 199 | 2024-05-09 | 2025-04-22 | 09-May-24 A | 2025-05-12 | 20
HM-ME-0510 | Vendor Document Review of ROV/ GOV | 185 | 15 | 2024-05-09 | 2024-08-10 | 09-May-24 A | 2024-11-09 | 20
HM-ME-0520 | Manufacturing & Assembly of ROV/ GOV | 320 | 169 | 2024-05-28 | 2025-03-23 | 28-May-24 A | 2025-04-12 | 20
HM-ME-0530 | Testing and Inspection of ROV/ GOV | 7 | 7 | 2025-04-05 | 2025-04-11 | 2025-04-25 | 2025-05-01 | 20
HM-ME-0540 | Packaging & Final Inspection-ROV/ GOV | 7 | 7 | 2025-04-12 | 2025-04-18 | 2025-05-02 | 2025-05-08 | 20
HM-ME-0550 | Ready for Dispatch of ROV/ GOV | 4 | 4 | 2025-04-19 | 2025-04-22 | 2025-05-09 | 2025-05-12 | 20
Delivery & receipt at Site |  | 99 | 99 | 2025-03-24 | 2025-06-30 | 2025-04-13 | 2025-07-20 | 19
HM-ME-0570 | Transportation/ Custom Clearance/ Delivery at site of ROV/ GOV (1st Lot) | 35 | 35 | 2025-03-24 | 2025-04-27 | 2025-04-13 | 2025-05-17 | 30
HM-ME-0580 | Receipt at site and inspection of ROV/ GOV (1st Lot) | 7 | 7 | 2025-04-28 | 2025-05-04 | 2025-05-18 | 2025-05-24 | 76
HM-ME-2220 | Transportation/ Custom Clearance/ Delivery at site of ROV/ GOV (2nd Lot) | 45 | 45 | 2025-05-08 | 2025-06-21 | 2025-05-28 | 2025-07-11 | 20
HM-ME-2210 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | 7 | 7 | 2025-06-22 | 2025-06-30 | 2025-07-13 | 2025-07-20 | 17
MOV & ISOLATOR |  | 411 | 271 | 2024-06-08 | 2025-06-13 | 08-Jun-24 A | 2025-07-23 | 16
Manufacturing & Ready for Dispatch |  | 353 | 213 | 2024-06-08 | 2025-05-07 | 08-Jun-24 A | 2025-05-26 | 16
HM-ME-0610 | Vendor Document Review of MOV | 147 | 7 | 2024-06-08 | 2024-08-02 | 08-Jun-24 A | 2024-11-01 | 204
HM-ME-0620 | Manufacturing & Assembly of MOV | 308 | 195 | 2024-08-03 | 2025-04-19 | 05-Jul-24 A | 2025-05-08 | 16
HM-ME-0630 | Testing and Inspection of MOV | 7 | 7 | 2025-04-20 | 2025-04-26 | 2025-05-09 | 2025-05-15 | 16
HM-ME-0640 | Packaging & Final Inspection-MOV | 7 | 7 | 2025-04-27 | 2025-05-03 | 2025-05-16 | 2025-05-22 | 16
HM-ME-0650 | Ready for Dispatch of MOV | 4 | 4 | 2025-05-04 | 2025-05-07 | 2025-05-23 | 2025-05-26 | 16
Delivery & receipt at Site |  | 76 | 76 | 2025-04-20 | 2025-06-13 | 2025-05-09 | 2025-07-23 | 16
HM-ME-2230 | Transportation/ Custom Clearance/ Delivery at site of MOV (Lot 1) | 21 | 21 | 2025-04-20 | 2025-05-10 | 2025-05-09 | 2025-05-29 | 47
HM-ME-0690 | Receipt at site and inspection of Isolator (Lot 1) | 7 | 7 | 2025-05-19 | 2025-05-26 | 2025-06-09 | 2025-06-16 | 38
HM-ME-0680 | Receipt at site and inspection of MOV (Lot 1) | 18 | 18 | 2025-05-11 | 2025-05-18 | 2025-05-30 | 2025-06-23 | 39
HM-ME-2250 | Receipt at site and inspection of Isolator (Lot 2) | 7 | 7 | 2025-06-03 | 2025-06-13 | 2025-06-17 | 2025-06-24 | 38
HM-ME-0670 | Transportation/ Custom Clearance/ Delivery at site of MOV (Lot 2) | 35 | 35 | 2025-05-08 | 2025-05-28 | 2025-05-27 | 2025-06-30 | 16
HM-ME-2240 | Receipt at site and inspection of MOV (Lot 2) | 20 | 20 | 2025-05-29 | 2025-06-09 | 2025-07-01 | 2025-07-23 | 14
AC UPS |  | 232 | 66 | 2024-05-13 | 2025-04-08 | 13-May-24 A | 2024-12-30 | 205
Manufacturing & Ready for Dispatch |  | 189 | 23 | 2024-05-13 | 2025-02-24 | 13-May-24 A | 2024-11-17 | 205
HM-ME-0720 | Vendor Document Review of AC UPS | 18 | 0 | 2024-05-13 | 2024-08-15 | 13-May-24 A | 30-May-24 A
HM-ME-0730 | Manufacturing & Assembly of AC UPS | 113 | 0 | 2024-08-23 | 2025-01-30 | 21-Jun-24 A | 11-Oct-24 A
HM-ME-0740 | Factory Acceptance Test of AC UPS | 26 | 12 | 2025-01-30 | 2025-02-13 | 12-Oct-24 A | 2024-11-06 | 205
HM-ME-0750 | Packaging & Final Inspection-AC UPS | 7 | 7 | 2025-02-13 | 2025-02-20 | 2024-11-07 | 2024-11-13 | 205
HM-ME-0760 | Ready for Dispatch of AC UPS | 4 | 4 | 2025-02-20 | 2025-02-24 | 2024-11-14 | 2024-11-17 | 205
Delivery & receipt at Site |  | 43 | 43 | 2025-02-24 | 2025-04-08 | 2024-11-18 | 2024-12-30 | 205
HM-ME-0780 | Transportation/ Custom Clearance/ Delivery at site of AC UPS | 35 | 35 | 2025-02-24 | 2025-03-31 | 2024-11-18 | 2024-12-22 | 205
HM-ME-0790 | Receipt at site and inspection of AC UPS | 8 | 8 | 2025-03-31 | 2025-04-08 | 2024-12-23 | 2024-12-30 | 205
CP System |  | 303 | 160 | 2024-06-05 | 2024-12-24 | 05-Jun-24 A | 2025-04-03 | 125
Manufacturing & Ready for Dispatch |  | 279 | 136 | 2024-06-05 | 2024-12-09 | 05-Jun-24 A | 2025-03-10 | 134
HM-PL-0350 | Vendor Document Review of CP System | 164 | 21 | 2024-06-05 | 2024-08-16 | 05-Jun-24 A | 2024-11-15 | 63
HM-PL-0360 | Manufacturing & Assembly of CP System | 90 | 90 | 2024-08-17 | 2024-11-14 | 2024-11-16 | 2025-02-13 | 63
HM-PL-0370 | Factory Acceptance Test of CP System | 14 | 14 | 2024-11-15 | 2024-11-28 | 2025-02-14 | 2025-02-27 | 134
HM-PL-0380 | Packaging & Final Inspection-CP System | 7 | 7 | 2024-11-29 | 2024-12-05 | 2025-02-28 | 2025-03-06 | 134
HM-PL-0390 | Ready for Dispatch of CP System | 4 | 4 | 2024-12-06 | 2024-12-09 | 2025-03-07 | 2025-03-10 | 134
Delivery & receipt at Site |  | 141 | 141 | 2024-08-15 | 2024-12-24 | 2024-11-14 | 2025-04-03 | 125
HM-PL-0410 | Receipt at site and inspection of CP System - Temporary Material | 7 | 7 | 2024-08-15 | 2024-08-21 | 2024-11-14 | 2024-11-20 | 75
HM-PL-0420 | Transportation/ Custom Clearance/ Delivery at site of CP System | 7 | 7 | 2024-12-10 | 2024-12-16 | 2025-03-11 | 2025-03-17 | 134
HM-PL-0430 | Receipt at site and inspection of CP System - Permanent Material | 7 | 7 | 2024-12-17 | 2024-12-24 | 2025-03-18 | 2025-04-03 | 102
Solar Power System |  | 273 | 182 | 2024-07-27 | 2025-04-24 | 27-Jul-24 A | 2025-04-25 | 97
Manufacturing & Ready for Dispatch |  | 244 | 153 | 2024-07-27 | 2025-03-14 | 27-Jul-24 A | 2025-03-27 | 97
HM-ME-1020 | Vendor Document Review of Solar PV system | 106 | 15 | 2024-07-27 | 2024-08-10 | 27-Jul-24 A | 2024-11-09 | 97
HM-ME-1030 | Manufacturing & Assembly of Solar PV system | 108 | 108 | 2024-10-04 | 2025-02-17 | 2024-11-10 | 2025-02-25 | 97
HM-ME-1040 | Factory Acceptance Test of Solar PV system | 14 | 14 | 2025-02-17 | 2025-03-03 | 2025-02-26 | 2025-03-11 | 97
HM-ME-1050 | Packaging & Final Inspection-Solar PV system | 7 | 7 | 2025-03-03 | 2025-03-10 | 2025-03-12 | 2025-03-18 | 97
HM-ME-1060 | Ready for Dispatch of Solar PV system | 9 | 9 | 2025-03-10 | 2025-03-14 | 2025-03-19 | 2025-03-27 | 97
Delivery & receipt at Site |  | 29 | 29 | 2025-03-14 | 2025-04-24 | 2025-03-28 | 2025-04-25 | 97
HM-ME-1080 | Transportation/ Custom Clearance/ Delivery at site of Solar PV system | 21 | 21 | 2025-03-14 | 2025-04-16 | 2025-03-28 | 2025-04-17 | 97
HM-ME-1090 | Receipt at site and inspection of Solar PV system | 7 | 7 | 2025-04-17 | 2025-04-24 | 2025-04-18 | 2025-04-25 | 78
Passive Cooled Shelter |  | 313 | 182 | 2024-07-27 | 2025-02-16 | 17-Jun-24 A | 2025-04-25 | 89
Manufacturing & Ready for Dispatch |  | 298 | 167 | 2024-07-27 | 2025-02-01 | 17-Jun-24 A | 2025-04-10 | 89
HM-ME-1120 | Vendor Document Review of Active/ Passive Cooled Shelter | 124 | 0 | 2024-07-27 | 2024-08-18 | 17-Jun-24 A | 18-Oct-24 A
HM-ME-1130 | Manufacturing & Assembly of Active/ Passive Cooled Shelter | 248 | 156 | 2024-08-19 | 2025-01-21 | 26-Jul-24 A | 2025-03-30 | 89
HM-ME-1140 | Factory Acceptance Test of Active/ Passive Cooled Shelter | 3 | 3 | 2025-01-22 | 2025-01-24 | 2025-03-31 | 2025-04-02 | 89
HM-ME-1150 | Packaging & Final Inspection-Active/ Passive Cooled Shelter | 4 | 4 | 2025-01-24 | 2025-01-28 | 2025-04-02 | 2025-04-06 | 89
HM-ME-1160 | Ready for Dispatch of Active/ Passive Cooled Shelter | 4 | 4 | 2025-01-28 | 2025-02-01 | 2025-04-06 | 2025-04-10 | 89
Delivery & receipt at Site |  | 15 | 15 | 2025-02-01 | 2025-02-16 | 2025-04-10 | 2025-04-25 | 89
HM-ME-1180 | Transportation/ Custom Clearance/ Delivery at site of Active/ Passive Cooled Shelter | 7 | 7 | 2025-02-01 | 2025-02-08 | 2025-04-10 | 2025-04-17 | 89
HM-ME-1190 | Receipt at site and inspection of Active/ Passive Cooled Shelter | 7 | 7 | 2025-02-09 | 2025-02-16 | 2025-04-17 | 2025-04-25 | 71
Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) |  | 335 | 214 | 2024-06-27 | 2025-05-27 | 27-Jun-24 A | 2025-05-27 | 91
Manufacturing & Ready for Dispatch |  | 286 | 165 | 2024-06-27 | 2025-04-08 | 27-Jun-24 A | 2025-04-08 | 64
HM-ME-1220 | Vendor Document Review of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | 96 | 0 | 2024-06-27 | 2024-08-10 | 27-Jun-24 A | 30-Sep-24 A
HM-ME-1230 | Manufacturing & Assembly of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | 236 | 144 | 2024-08-11 | 2025-03-18 | 26-Jul-24 A | 2025-03-18 | 64
HM-ME-1240 | Testing and Inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | 10 | 10 | 2025-03-19 | 2025-03-28 | 2025-03-19 | 2025-03-28 | 64
HM-ME-1250 | Packaging & Final Inspection-Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | 7 | 7 | 2025-03-29 | 2025-04-04 | 2025-03-29 | 2025-04-04 | 64
HM-ME-1260 | Ready for Dispatch of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | 4 | 4 | 2025-04-05 | 2025-04-08 | 2025-04-05 | 2025-04-08 | 64
Delivery & receipt at Site |  | 70 | 70 | 2025-03-19 | 2025-05-27 | 2025-03-19 | 2025-05-27 | 91
HM-ME-1280 | Transportation/ Custom Clearance/ Delivery at site of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | 21 | 21 | 2025-03-19 | 2025-04-08 | 2025-03-19 | 2025-04-08 | 132
HM-ME-1290 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | 7 | 7 | 2025-04-09 | 2025-04-16 | 2025-04-09 | 2025-04-16 | 109
HM-ME-2260 | Transportation/ Custom Clearance/ Delivery at site of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | 21 | 21 | 2025-04-29 | 2025-05-19 | 2025-04-29 | 2025-05-19 | 64
HM-ME-2270 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | 7 | 7 | 2025-05-20 | 2025-05-27 | 2025-05-20 | 2025-05-27 | 51
Gas Detectors |  | 284 | 160 | 2024-07-29 | 2025-04-03 | 24-Jun-24 A | 2025-04-03 | 119
Manufacturing & Ready for Dispatch |  | 231 | 107 | 2024-07-29 | 2025-02-09 | 24-Jun-24 A | 2025-02-09 | 119
HM-ME-1420 | Vendor Document Review of Gas Detectors | 60 | 0 | 2024-07-29 | 2024-08-22 | 24-Jun-24 A | 22-Aug-24 A
HM-ME-1430 | Manufacturing & Assembly of Gas Detectors | 160 | 96 | 2024-08-23 | 2025-01-29 | 23-Aug-24 A | 2025-01-29 | 119
HM-ME-1440 | Testing and Inspection of Gas Detectors | 3 | 3 | 2025-01-30 | 2025-02-01 | 2025-01-30 | 2025-02-01 | 119
HM-ME-1450 | Packaging & Final Inspection-Gas Detectors | 4 | 4 | 2025-02-01 | 2025-02-05 | 2025-02-01 | 2025-02-05 | 119
HM-ME-1460 | Ready for Dispatch of Gas Detectors | 4 | 4 | 2025-02-05 | 2025-02-09 | 2025-02-05 | 2025-02-09 | 119
Delivery & receipt at Site |  | 64 | 64 | 2025-01-30 | 2025-04-03 | 2025-01-30 | 2025-04-03 | 119
HM-ME-1480 | Transportation/ Custom Clearance/ Delivery at site of Gas Detectors (Lot 1) | 21 | 21 | 2025-01-30 | 2025-02-19 | 2025-01-30 | 2025-02-19 | 154
HM-ME-1490 | Receipt at site and inspection of Gas Detectors (Lot 1) | 8 | 8 | 2025-02-20 | 2025-02-27 | 2025-02-20 | 2025-02-27 | 154
HM-ME-2300 | Transportation/ Custom Clearance/ Delivery at site of Gas Detectors (Lot 2) | 21 | 21 | 2025-03-01 | 2025-03-22 | 2025-03-01 | 2025-03-22 | 119
HM-ME-2310 | Receipt at site and inspection of Gas Detectors (Lot 2) | 12 | 12 | 2025-03-22 | 2025-04-03 | 2025-03-22 | 2025-04-03 | 119
FOC Cables |  | 172 | 0 | 2024-05-15 | 2024-11-01 | 07-May-24 A | 25-Oct-24 A
Manufacturing & Ready for Dispatch |  | 147 | 0 | 2024-05-15 | 2024-09-27 | 07-May-24 A | 30-Sep-24 A
HM-EL-0110 | Vendor Document Review of FOC Cables | 8 | 0 | 2024-05-15 | 2024-05-31 | 07-May-24 A | 15-May-24 A
HM-EL-0120 | Manufacturing & Assembly of FOC Cables | 52 | 0 | 2024-07-27 | 2024-09-09 | 15-May-24 A | 05-Jul-24 A
HM-EL-0130 | Testing and Inspection of FOC Cables | 8 | 0 | 2024-09-10 | 2024-09-16 | 26-Jul-24 A | 02-Aug-24 A
HM-EL-0140 | Packaging & Final Inspection-FOC Cables | 40 | 0 | 2024-09-17 | 2024-09-23 | 05-Aug-24 A | 13-Sep-24 A
HM-EL-0150 | Ready for Dispatch of FOC Cables | 17 | 0 | 2024-09-24 | 2024-09-27 | 14-Sep-24 A | 30-Sep-24 A
Delivery & receipt at Site |  | 84 | 0 | 2024-09-10 | 2024-11-01 | 03-Aug-24 A | 25-Oct-24 A
HM-EL-0170 | Transportation/ Custom Clearance/ Delivery at site of FOC Cables (Lot 1) | 7 | 0 | 2024-09-10 | 2024-09-16 | 03-Aug-24 A | 09-Aug-24 A
HM-EL-0180 | Receipt at site and inspection of FOC Cables (Lot 1) | 8 | 0 | 2024-09-17 | 2024-09-23 | 09-Aug-24 A | 16-Aug-24 A
HM-EL-600 | Transportation/ Custom Clearance/ Delivery at site of FOC Cables (Lot 2) | 22 | 0 | 2024-10-19 | 2024-10-25 | 01-Oct-24 A | 22-Oct-24 A
HM-EL-610 | Receipt at site and inspection of FOC Cables (Lot 2) | 3 | 0 | 2024-10-26 | 2024-11-01 | 23-Oct-24 A | 25-Oct-24 A
Others |  | 358 | 238 | 2024-07-27 | 2025-07-17 | 27-Jun-24 A | 2025-06-20 | 87
Power Distribution Boards |  | 246 | 184 | 2024-10-25 | 2025-05-12 | 24-Aug-24 A | 2025-04-27 | 63
Manufacturing & Ready for Dispatch |  | 217 | 155 | 2024-10-25 | 2025-04-12 | 24-Aug-24 A | 2025-03-29 | 61
HM-ME-0820 | Vendor Document Review of Power Distribution Boards | 39 | 0 | 2024-10-25 | 2024-11-08 | 24-Aug-24 A | 02-Oct-24 A
HM-ME-0830 | Manufacturing & Assembly of Power Distribution Boards | 161 | 140 | 2024-11-08 | 2025-03-28 | 05-Oct-24 A | 2025-03-14 | 61
HM-ME-0840 | Factory Acceptance Test of Power Distribution Boards | 4 | 4 | 2025-03-28 | 2025-04-01 | 2025-03-15 | 2025-03-18 | 61
HM-ME-0850 | Packaging & Final Inspection for Power Distribution Boards | 7 | 7 | 2025-04-01 | 2025-04-08 | 2025-03-19 | 2025-03-25 | 61
HM-ME-0860 | Ready for Dispatch of Power Distribution Boards | 4 | 4 | 2025-04-08 | 2025-04-12 | 2025-03-26 | 2025-03-29 | 61
Delivery & receipt at Site |  | 29 | 29 | 2025-04-12 | 2025-05-12 | 2025-03-30 | 2025-04-27 | 63
HM-ME-0880 | Transportation/ Custom Clearance/ Delivery at site of Power Distribution Boards | 21 | 21 | 2025-04-12 | 2025-05-03 | 2025-03-30 | 2025-04-19 | 61
HM-ME-0890 | Receipt at site and inspection of Power Distribution Boards | 7 | 7 | 2025-05-04 | 2025-05-12 | 2025-04-20 | 2025-04-27 | 50
Distribution Transformer |  | 286 | 195 | 2024-07-27 | 2025-05-08 | 27-Jul-24 A | 2025-05-08 | 120
Manufacturing & Ready for Dispatch |  | 259 | 168 | 2024-07-27 | 2025-04-11 | 27-Jul-24 A | 2025-04-11 | 120
HM-ME-0920 | Vendor Document Review of Distribution Transformer | 70 | 0 | 2024-07-27 | 2024-10-04 | 27-Jul-24 A | 04-Oct-24 A
HM-ME-0930 | Manufacturing & Assembly of Distribution Transformer | 174 | 153 | 2024-10-05 | 2025-03-27 | 05-Oct-24 A | 2025-03-27 | 120
HM-ME-0940 | Factory Acceptance Test of Distribution Transformer | 4 | 4 | 2025-03-28 | 2025-03-31 | 2025-03-28 | 2025-03-31 | 120
HM-ME-0950 | Packaging & Final Inspection-Distribution Transformer | 7 | 7 | 2025-04-01 | 2025-04-07 | 2025-04-01 | 2025-04-07 | 120
HM-ME-0960 | Ready for Dispatch of Distribution Transformer | 4 | 4 | 2025-04-08 | 2025-04-11 | 2025-04-08 | 2025-04-11 | 120
Delivery & receipt at Site |  | 27 | 27 | 2025-04-12 | 2025-05-08 | 2025-04-12 | 2025-05-08 | 120
HM-ME-0980 | Transportation/ Custom Clearance/ Delivery at site of Distribution Transformer | 20 | 20 | 2025-04-12 | 2025-05-01 | 2025-04-12 | 2025-05-01 | 120
HM-ME-0990 | Receipt at site and inspection of Distribution Transformer | 7 | 7 | 2025-05-02 | 2025-05-08 | 2025-05-02 | 2025-05-08 | 120
Access Switch, Fiber Optic Patch Panel and Media Converter |  | 325 | 205 | 2024-09-27 | 2025-05-18 | 27-Jun-24 A | 2025-05-18 | 67
Manufacturing & Ready for Dispatch |  | 275 | 155 | 2024-09-27 | 2025-03-29 | 27-Jun-24 A | 2025-03-29 | 67
HM-ME-1320 | Vendor Document Review of Access Switch, Fiber Optic Patch Panel and Media Converter | 107 | 0 | 2024-09-27 | 2024-10-27 | 27-Jun-24 A | 12-Oct-24 A
HM-ME-1330 | Manufacturing & Assembly of Access Switch, Fiber Optic Patch Panel and Media Converter | 228 | 137 | 2024-10-27 | 2025-03-11 | 26-Jul-24 A | 2025-03-11 | 67
HM-ME-1340 | Factory Acceptance Test of Access Switch, Fiber Optic Patch Panel and Media Converter | 7 | 7 | 2025-03-11 | 2025-03-18 | 2025-03-12 | 2025-03-18 | 67
HM-ME-1350 | Packaging & Final Inspection-Access Switch, Fiber Optic Patch Panel and Media Converter | 7 | 7 | 2025-03-18 | 2025-03-25 | 2025-03-19 | 2025-03-25 | 67
HM-ME-1360 | Ready for Dispatch of Access Switch, Fiber Optic Patch Panel and Media Converter | 4 | 4 | 2025-03-25 | 2025-03-29 | 2025-03-26 | 2025-03-29 | 67
Delivery & receipt at Site |  | 68 | 68 | 2025-03-11 | 2025-05-18 | 2025-03-12 | 2025-05-18 | 67
HM-ME-1380 | Transportation/ Custom Clearance/ Delivery at site of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | 21 | 21 | 2025-03-11 | 2025-04-01 | 2025-03-12 | 2025-04-01 | 106
HM-ME-1390 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | 7 | 7 | 2025-04-03 | 2025-04-10 | 2025-04-03 | 2025-04-10 | 85
HM-ME-2280 | Transportation/ Custom Clearance/ Delivery at site of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | 21 | 21 | 2025-04-19 | 2025-05-10 | 2025-04-20 | 2025-05-10 | 67
HM-ME-2290 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | 7 | 7 | 2025-05-11 | 2025-05-18 | 2025-05-11 | 2025-05-18 | 54
Field Instruments / H2S Analyzers |  | 211 | 126 | 2024-08-02 | 2025-02-28 | 02-Aug-24 A | 2025-02-28 | 127
Manufacturing & Ready for Dispatch |  | 162 | 77 | 2024-08-02 | 2025-01-10 | 02-Aug-24 A | 2025-01-10 | 127
HM-ME-1520 | Vendor Document Review of Field Instruments | 70 | 0 | 2024-08-02 | 2024-09-01 | 02-Aug-24 A | 10-Oct-24 A
HM-ME-1530 | Manufacturing & Assembly of Field Instruments | 101 | 66 | 2024-09-01 | 2024-12-30 | 20-Sep-24 A | 2024-12-30 | 127
HM-ME-1540 | Testing and Inspection of Field Instruments | 3 | 3 | 2024-12-30 | 2025-01-02 | 2024-12-31 | 2025-01-02 | 127
HM-ME-1550 | Packaging & Final Inspection-Field Instruments | 4 | 4 | 2025-01-02 | 2025-01-06 | 2025-01-02 | 2025-01-06 | 127
HM-ME-1560 | Ready for Dispatch of Field Instruments | 4 | 4 | 2025-01-06 | 2025-01-10 | 2025-01-06 | 2025-01-10 | 127
Delivery & receipt at Site |  | 60 | 60 | 2024-12-30 | 2025-02-28 | 2024-12-31 | 2025-02-28 | 127
HM-ME-1580 | Transportation/ Custom Clearance/ Delivery at site of Field Instruments (Lot 1) | 21 | 21 | 2024-12-30 | 2025-01-20 | 2024-12-31 | 2025-01-20 | 158
HM-ME-1590 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | 7 | 7 | 2025-01-20 | 2025-01-27 | 2025-01-21 | 2025-01-27 | 158
HM-ME-2320 | Transportation/ Custom Clearance/ Delivery at site of Field Instruments (Lot 2) | 21 | 21 | 2025-01-31 | 2025-02-21 | 2025-01-31 | 2025-02-21 | 127
HM-ME-2330 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | 7 | 7 | 2025-02-21 | 2025-02-28 | 2025-02-21 | 2025-02-28 | 127
Junction Boxes |  | 208 | 208 | 2024-10-11 | 2025-05-17 | 2024-10-26 | 2025-05-21 | 79
Manufacturing & Ready for Dispatch |  | 180 | 180 | 2024-10-11 | 2025-04-12 | 2024-10-26 | 2025-04-23 | 79
HM-ME-1620 | Vendor Document Review of Junction Boxes | 20 | 20 | 2024-10-11 | 2024-10-31 | 2024-10-26 | 2024-11-14 | 79
HM-ME-1630 | Manufacturing & Assembly of Junction Boxes | 107 | 107 | 2024-10-31 | 2025-02-15 | 2024-11-15 | 2025-03-01 | 79
HM-ME-1640 | Testing and Inspection of Junction Boxes | 18 | 18 | 2025-02-15 | 2025-03-08 | 2025-03-02 | 2025-03-19 | 79
HM-ME-1650 | Packaging & Final Inspection-Junction Boxes | 21 | 21 | 2025-03-08 | 2025-03-29 | 2025-03-20 | 2025-04-09 | 79
HM-ME-1660 | Ready for Dispatch of Junction Boxes | 14 | 14 | 2025-03-29 | 2025-04-12 | 2025-04-10 | 2025-04-23 | 79
Delivery & receipt at Site |  | 81 | 81 | 2025-02-15 | 2025-05-17 | 2025-03-02 | 2025-05-21 | 79
HM-ME-1680 | Transportation/ Custom Clearance/ Delivery at site of Junction Boxes (Lot 1) | 21 | 21 | 2025-02-15 | 2025-03-08 | 2025-03-02 | 2025-03-22 | 125
HM-ME-1690 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | 14 | 14 | 2025-03-08 | 2025-03-22 | 2025-03-23 | 2025-04-05 | 125
HM-ME-2340 | Transportation/ Custom Clearance/ Delivery at site of Junction Boxes (Lot 2) | 14 | 14 | 2025-04-12 | 2025-05-03 | 2025-04-24 | 2025-05-07 | 79
HM-ME-2350 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | 14 | 14 | 2025-05-03 | 2025-05-17 | 2025-05-08 | 2025-05-21 | 79
HVAC Equipment |  | 245 | 154 | 2024-07-27 | 2025-02-09 | 27-Jul-24 A | 2025-03-28 | 31
Manufacturing & Ready for Dispatch |  | 196 | 105 | 2024-07-27 | 2024-12-28 | 27-Jul-24 A | 2025-02-07 | 36
HM-ME-1720 | Vendor Document Review of HVAC Equipment | 21 | 0 | 2024-07-27 | 2024-08-16 | 27-Jul-24 A | 16-Aug-24 A
HM-ME-1730 | Manufacturing & Assembly of HVAC Equipment | 150 | 80 | 2024-08-17 | 2024-12-03 | 17-Aug-24 A | 2025-01-13 | 36
HM-ME-1740 | Factory Acceptance Test of HVAC Equipment | 14 | 14 | 2024-12-04 | 2024-12-17 | 2025-01-14 | 2025-01-27 | 36
HM-ME-1750 | Packaging & Final Inspection-HVAC Equipment | 7 | 7 | 2024-12-18 | 2024-12-24 | 2025-01-28 | 2025-02-03 | 36
HM-ME-1760 | Ready for Dispatch of HVAC Equipment | 4 | 4 | 2024-12-25 | 2024-12-28 | 2025-02-04 | 2025-02-07 | 36
Delivery & receipt at Site |  | 49 | 49 | 2024-12-29 | 2025-02-09 | 2025-02-08 | 2025-03-28 | 31
HM-ME-1780 | Transportation/ Custom Clearance/ Delivery at site of HVAC Equipment | 35 | 35 | 2024-12-29 | 2025-02-01 | 2025-02-08 | 2025-03-14 | 36
HM-ME-1790 | Receipt at site and inspection of HVAC Equipment | 7 | 7 | 2025-02-02 | 2025-02-09 | 2025-03-16 | 2025-03-28 | 22
Fire Supression System |  | 187 | 155 | 2024-09-20 | 2025-02-28 | 23-Sep-24 A | 2025-03-29 | 29
Manufacturing & Ready for Dispatch |  | 152 | 120 | 2024-09-20 | 2025-01-24 | 23-Sep-24 A | 2025-02-22 | 29
HM-ME-1850 | Vendor Document Review of Fire Suppression System | 46 | 14 | 2024-09-20 | 2024-10-04 | 23-Sep-24 A | 2024-11-08 | 29
HM-ME-1860 | Manufacturing & Assembly of Fire Suppression System | 84 | 84 | 2024-10-04 | 2025-01-02 | 2024-11-09 | 2025-01-31 | 29
HM-ME-1870 | Factory Acceptance Test of Fire Suppression System | 11 | 11 | 2025-01-02 | 2025-01-13 | 2025-02-01 | 2025-02-11 | 29
HM-ME-1880 | Packaging & Final Inspection-Fire Suppression System | 7 | 7 | 2025-01-13 | 2025-01-20 | 2025-02-12 | 2025-02-18 | 29
HM-ME-1890 | Ready for Dispatch of Fire Suppression System | 4 | 4 | 2025-01-20 | 2025-01-24 | 2025-02-19 | 2025-02-22 | 29
Delivery & receipt at Site |  | 35 | 35 | 2025-01-24 | 2025-02-28 | 2025-02-23 | 2025-03-29 | 29
HM-ME-1820 | Transportation/ Custom Clearance/ Delivery at site of Fire Suppression System | 28 | 28 | 2025-01-24 | 2025-02-21 | 2025-02-23 | 2025-03-22 | 29
HM-ME-1830 | Receipt at site and inspection of Fire Suppression System | 7 | 7 | 2025-02-21 | 2025-02-28 | 2025-03-23 | 2025-03-29 | 29
Fire Fighting & Safety Equipment |  | 208 | 172 | 2024-09-20 | 2025-03-25 | 20-Sep-24 A | 2025-04-15 | 153
Manufacturing & Ready for Dispatch |  | 192 | 156 | 2024-09-20 | 2025-03-11 | 20-Sep-24 A | 2025-03-30 | 155
HM-ME-1920 | Vendor Document Review of Fire Fighting & Safety Equipment | 44 | 8 | 2024-09-20 | 2024-10-04 | 20-Sep-24 A | 2024-11-02 | 153
HM-ME-1930 | Manufacturing & Assembly of Fire Fighting & Safety Equipment | 130 | 130 | 2024-10-04 | 2025-02-21 | 2024-11-03 | 2025-03-12 | 153
HM-ME-1940 | Factory Acceptance Test of Fire Fighting & Safety Equipment | 7 | 7 | 2025-02-21 | 2025-02-28 | 2025-03-13 | 2025-03-19 | 155
HM-ME-1950 | Packaging & Final Inspection-Fire Fighting & Safety Equipment | 7 | 7 | 2025-02-28 | 2025-03-07 | 2025-03-20 | 2025-03-26 | 155
HM-ME-1960 | Ready for Dispatch of Fire Fighting & Safety Equipment | 4 | 4 | 2025-03-07 | 2025-03-11 | 2025-03-27 | 2025-03-30 | 155
Delivery & receipt at Site |  | 16 | 16 | 2025-03-03 | 2025-03-25 | 2025-03-31 | 2025-04-15 | 153
HM-ME-2360 | Transportation/ Custom Clearance/ Delivery at site of Fire Fighting & Safety Equipment (Lot 2) | 7 | 7 | 2025-03-11 | 2025-03-18 | 2025-03-31 | 2025-04-06 | 155
HM-ME-1980 | Transportation/ Custom Clearance/ Delivery at site of Fire Fighting & Safety Equipment (Lot 1) | 7 | 7 | 2025-03-03 | 2025-03-10 | 2025-04-02 | 2025-04-08 | 153
HM-ME-2370 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 2) | 7 | 7 | 2025-03-18 | 2025-03-25 | 2025-04-07 | 2025-04-13 | 155
HM-ME-1990 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 1) | 7 | 7 | 2025-03-10 | 2025-03-17 | 2025-04-09 | 2025-04-15 | 153
LV Switch Gear |  | 238 | 238 | 2024-09-20 | 2025-07-17 | 2024-10-26 | 2025-06-20 | 75
Manufacturing & Ready for Dispatch |  | 205 | 205 | 2024-09-20 | 2025-06-14 | 2024-10-26 | 2025-05-18 | 75
HM-ME-2040 | Vendor Document Review of LV Switch Gear | 30 | 30 | 2024-09-20 | 2024-10-20 | 2024-10-26 | 2024-11-24 | 75
HM-ME-2000 | Manufacturing & Assembly of LV Switch Gear | 150 | 150 | 2024-10-20 | 2025-05-20 | 2024-11-25 | 2025-04-23 | 75
HM-ME-2010 | Factory Acceptance Test of LV Switch Gear | 14 | 14 | 2025-05-20 | 2025-06-03 | 2025-04-24 | 2025-05-07 | 75
HM-ME-2020 | Packaging & Final Inspection-LV Switch Gear | 7 | 7 | 2025-06-03 | 2025-06-10 | 2025-05-08 | 2025-05-14 | 75
HM-ME-2030 | Ready for Dispatch of LV Switch Gear | 4 | 4 | 2025-06-10 | 2025-06-14 | 2025-05-15 | 2025-05-18 | 75
Delivery & receipt at Site |  | 33 | 33 | 2025-06-14 | 2025-07-17 | 2025-05-19 | 2025-06-20 | 75
HM-ME-2050 | Transportation/ Custom Clearance/ Delivery at site of LV Switch Gear | 25 | 25 | 2025-06-14 | 2025-07-09 | 2025-05-19 | 2025-06-12 | 75
HM-ME-2060 | Receipt at site and inspection of LV Switch Gear | 7 | 7 | 2025-07-10 | 2025-07-17 | 2025-06-13 | 2025-06-20 | 63
Lifting Euipment |  | 259 | 199 | 2024-10-07 | 2025-04-10 | 26-Aug-24 A | 2025-05-12 | 67
Manufacturing & Ready for Dispatch |  | 229 | 169 | 2024-10-07 | 2025-03-10 | 26-Aug-24 A | 2025-04-12 | 68
HM-ME-2180 | Vendor Document Review of Lifting Equipment | 90 | 30 | 2024-10-07 | 2024-11-06 | 26-Aug-24 A | 2024-11-24 | 68
HM-ME-2140 | Manufacturing & Assembly of LV Lifting Equipment | 90 | 90 | 2024-11-06 | 2025-01-20 | 2024-11-25 | 2025-02-22 | 68
HM-ME-2150 | Factory Acceptance Test of LV Lifting Equipment | 21 | 21 | 2025-01-20 | 2025-02-10 | 2025-02-23 | 2025-03-15 | 68
HM-ME-2160 | Packaging & Final Inspection-LV Lifting Equipment | 14 | 14 | 2025-02-10 | 2025-02-24 | 2025-03-16 | 2025-03-29 | 68
HM-ME-2170 | Ready for Dispatch of LV Lifting Equipment | 14 | 14 | 2025-02-24 | 2025-03-10 | 2025-03-30 | 2025-04-12 | 68
Delivery & receipt at Site |  | 30 | 30 | 2025-03-10 | 2025-04-10 | 2025-04-13 | 2025-05-12 | 67
HM-ME-2190 | Transportation/ Custom Clearance/ Delivery at site of Lifting Equipment | 21 | 21 | 2025-03-10 | 2025-03-31 | 2025-04-13 | 2025-05-03 | 68
HM-ME-2200 | Receipt at site and inspection of Lifting Equipment | 7 | 7 | 2025-04-03 | 2025-04-10 | 2025-05-04 | 2025-05-12 | 54
Pipeline Material |  | 606 | 196 | 2023-09-12 | 2025-05-09 | 12-Sep-23 A | 2025-05-09 | 91
Line Pipes |  | 562 | 152 | 2023-09-12 | 2025-03-26 | 12-Sep-23 A | 2025-03-26 | 24
Manufacturing & Ready for Dispatch |  | 562 | 152 | 2023-09-12 | 2025-03-03 | 12-Sep-23 A | 2025-03-26 | 24
Lot 1 |  | 257 | 0 | 2023-09-12 | 2024-05-26 | 12-Sep-23 A | 26-May-24 A
HM-PL-0010 | Vendor Document Review of Line Pipes - Lot 1 | 38 | 0 | 2023-09-12 | 2023-10-20 | 12-Sep-23 A | 20-Oct-23 A
HM-PL-0020 | Manufacturing & Receive Plates at Fabrication Shop - Lot 1 | 82 | 0 | 2023-10-20 | 2024-01-10 | 20-Oct-23 A | 10-Jan-24 A
HM-PL-0030 | Complete Line Pipe Production - Lot 1 | 62 | 0 | 2024-01-22 | 2024-03-24 | 22-Jan-24 A | 24-Mar-24 A
HM-PL-0035 | Complete External / Internal Coating - Lot 1 | 31 | 0 | 2024-03-26 | 2024-04-26 | 26-Mar-24 A | 26-Apr-24 A
HM-PL-0040 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 1 | 28 | 0 | 2024-04-27 | 2024-05-25 | 27-Apr-24 A | 25-May-24 A
HM-PL-0050 | Ready for Dispatch of Line Pipes (Coated) - Lot 1 | 0 | 0 | 2024-05-26 | 2024-05-26 | 26-May-24 A | 26-May-24 A
Lot 2 |  | 276 | 0 | 2023-09-12 | 2024-06-14 | 12-Sep-23 A | 14-Jun-24 A
HM-PL-970 | Vendor Document Review of Line Pipes - Lot 2 | 38 | 0 | 2023-09-12 | 2023-10-20 | 12-Sep-23 A | 20-Oct-23 A
HM-PL-980 | Manufacturing & Receive Plates at Fabrication Shop - Lot 2 | 56 | 0 | 2023-11-15 | 2024-01-10 | 15-Nov-23 A | 10-Jan-24 A
HM-PL-990 | Complete Line Pipe Production - Lot 2 | 20 | 0 | 2024-03-30 | 2024-04-19 | 30-Mar-24 A | 19-Apr-24 A
HM-PL-1020 | Complete External / Internal Coating - Lot 2 | 41 | 0 | 2024-04-20 | 2024-05-31 | 20-Apr-24 A | 31-May-24 A
HM-PL-1000 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 2 | 13 | 0 | 2024-06-01 | 2024-06-14 | 01-Jun-24 A | 14-Jun-24 A
HM-PL-1010 | Ready for Dispatch of Line Pipes (Coated) - Lot 2 | 0 | 0 | 2024-06-14 | 2024-06-14 | 14-Jun-24 A | 14-Jun-24 A
Lot 3 |  | 347 | 0 | 2023-09-12 | 2024-08-16 | 12-Sep-23 A | 23-Aug-24 A
HM-PL-1030 | Vendor Document Review of Line Pipes - Lot 3 | 38 | 0 | 2023-09-12 | 2023-10-20 | 12-Sep-23 A | 20-Oct-23 A
HM-PL-1040 | Manufacturing & Receive Plates at Fabrication Shop - Lot 3 | 105 | 0 | 2023-12-12 | 2024-03-26 | 12-Dec-23 A | 26-Mar-24 A
HM-PL-1050 | Complete Line Pipe Production - Lot 3 | 25 | 0 | 2024-03-30 | 2024-04-24 | 30-Mar-24 A | 24-Apr-24 A
HM-PL-1080 | Complete External / Internal Coating - Lot 3 | 116 | 0 | 2024-04-06 | 2024-08-12 | 06-Apr-24 A | 30-Jul-24 A
HM-PL-1060 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 3 | 14 | 0 | 2024-08-07 | 2024-08-14 | 01-Aug-24 A | 14-Aug-24 A
HM-PL-1070 | Ready for Dispatch of Line Pipes (Coated) - Lot 3 | 9 | 0 | 2024-08-09 | 2024-08-16 | 15-Aug-24 A | 23-Aug-24 A
Lot 4 |  | 323 | 0 | 2023-09-12 | 2024-07-31 | 12-Sep-23 A | 30-Jul-24 A
HM-PL-1330 | Vendor Document Review of Line Pipes - Lot 4 | 45 | 0 | 2023-09-12 | 2023-10-27 | 12-Sep-23 A | 27-Oct-23 A
HM-PL-1340 | Manufacturing & Receive Plates at Fabrication Shop - Lot 4 | 55 | 0 | 2024-01-25 | 2024-03-20 | 25-Jan-24 A | 20-Mar-24 A
HM-PL-1350 | Complete Line Pipe Production - Lot 4 | 67 | 0 | 2024-03-25 | 2024-05-31 | 25-Mar-24 A | 31-May-24 A
HM-PL-1380 | Complete External / Internal Coating - Lot 4 | 57 | 0 | 2024-05-30 | 2024-07-25 | 30-May-24 A | 25-Jul-24 A
HM-PL-1360 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 4 | 17 | 0 | 2024-07-10 | 2024-07-26 | 10-Jul-24 A | 26-Jul-24 A
HM-PL-1370 | Ready for Dispatch of Line Pipes (Coated) - Lot 4 | 8 | 0 | 2024-07-23 | 2024-07-31 | 23-Jul-24 A | 30-Jul-24 A
Lot 5 |  | 429 | 19 | 2023-09-12 | 2024-09-07 | 12-Sep-23 A | 2024-11-13 | 18
HM-PL-1270 | Vendor Document Review of Line Pipes - Lot 5 | 45 | 0 | 2023-09-12 | 2023-10-27 | 12-Sep-23 A | 27-Oct-23 A
HM-PL-1280 | Manufacturing & Receive Plates at Fabrication Shop - Lot 5 | 19 | 0 | 2024-04-04 | 2024-04-23 | 04-Apr-24 A | 23-Apr-24 A
HM-PL-1290 | Complete Line Pipe Production - Lot 5 | 46 | 0 | 2024-04-29 | 2024-06-14 | 29-Apr-24 A | 14-Jun-24 A
HM-PL-1320 | Complete External / Internal Coating - Lot 5 | 41 | 5 | 2024-07-27 | 2024-08-24 | 20-Sep-24 A | 2024-10-30 | 18
HM-PL-1300 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 5 | 10 | 10 | 2024-08-18 | 2024-08-31 | 2024-10-28 | 2024-11-06 | 18
HM-PL-1310 | Ready for Dispatch of Line Pipes (Coated) - Lot 5 | 10 | 10 | 2024-08-25 | 2024-09-07 | 2024-11-04 | 2024-11-13 | 18
Lot 6 |  | 447 | 27 | 2023-09-12 | 2024-11-04 | 12-Sep-23 A | 2024-12-01 | 18
HM-PL-1090 | Vendor Document Review of Line Pipes - Lot 6 | 45 | 0 | 2023-09-12 | 2023-10-27 | 12-Sep-23 A | 27-Oct-23 A
HM-PL-1100 | Manufacturing & Receive Plates at Fabrication Shop - Lot 6 | 47 | 0 | 2024-03-10 | 2024-04-26 | 10-Mar-24 A | 26-Apr-24 A
HM-PL-1110 | Complete Line Pipe Production - Lot 6 | 99 | 0 | 2024-05-27 | 2024-08-25 | 27-May-24 A | 02-Sep-24 A
HM-PL-1140 | Complete External / Internal Coating - Lot 6 | 52 | 0 | 2024-07-17 | 2024-09-22 | 17-Jul-24 A | 06-Sep-24 A
HM-PL-1120 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 6 | 14 | 14 | 2024-09-23 | 2024-10-14 | 2024-11-05 | 2024-11-18 | 18
HM-PL-1130 | Ready for Dispatch of Line Pipes (Coated) - Lot 6 | 13 | 13 | 2024-10-15 | 2024-11-04 | 2024-11-19 | 2024-12-01 | 18
Lot 7 |  | 488 | 78 | 2023-09-12 | 2024-12-18 | 12-Sep-23 A | 2025-01-11 | 24
HM-PL-1150 | Vendor Document Review of Line Pipes - Lot 7 | 45 | 0 | 2023-09-12 | 2023-10-27 | 12-Sep-23 A | 27-Oct-23 A
HM-PL-1160 | Manufacturing & Receive Plates at Fabrication Shop - Lot 7 | 27 | 0 | 2024-04-27 | 2024-05-24 | 27-Apr-24 A | 24-May-24 A
HM-PL-1170 | Complete Line Pipe Production - Lot 7 | 160 | 5 | 2024-05-24 | 2024-09-02 | 24-May-24 A | 2024-10-30 | 24
HM-PL-1200 | Complete External / Internal Coating - Lot 7 | 40 | 40 | 2024-09-03 | 2024-11-02 | 2024-10-31 | 2024-12-09 | 24
HM-PL-1180 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 7 | 21 | 21 | 2024-11-03 | 2024-11-28 | 2024-12-10 | 2024-12-30 | 24
HM-PL-1190 | Ready for Dispatch of Line Pipes (Coated) - Lot 7 | 12 | 12 | 2024-11-29 | 2024-12-18 | 2024-12-31 | 2025-01-11 | 24
Lot 8 |  | 354 | 0 | 2023-09-12 | 2025-01-25 | 12-Sep-23 A | 30-Aug-24 A
HM-PL-1390 | Vendor Document Review of Line Pipes - Lot 8 | 45 | 0 | 2023-09-12 | 2023-10-27 | 12-Sep-23 A | 27-Oct-23 A
HM-PL-1400 | Manufacturing & Receive Plates at Fabrication Shop - Lot 8 | 200 | 0 | 2023-10-28 | 2024-05-15 | 28-Oct-23 A | 15-May-24 A
HM-PL-1410 | Complete Line Pipe Production - Lot 8 | 29 | 0 | 2024-05-16 | 2024-06-14 | 16-May-24 A | 14-Jun-24 A
HM-PL-1440 | Complete External / Internal Coating - Lot 8 | 29 | 0 | 2024-06-21 | 2024-11-03 | 21-Jun-24 A | 19-Jul-24 A
HM-PL-1420 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 8 | 37 | 0 | 2024-11-04 | 2024-12-18 | 20-Jul-24 A | 26-Aug-24 A
HM-PL-1430 | Ready for Dispatch of Line Pipes (Coated) - Lot 8 | 4 | 0 | 2024-12-19 | 2025-01-25 | 27-Aug-24 A | 30-Aug-24 A
Lot 9 |  | 562 | 74 | 2023-09-12 | 2025-03-03 | 12-Sep-23 A | 2025-03-26 | 24
HM-PL-1210 | Vendor Document Review of Line Pipes - Lot 9 | 190 | 0 | 2023-09-12 | 2024-03-20 | 12-Sep-23 A | 20-Mar-24 A
HM-PL-1220 | Manufacturing & Receive Plates at Fabrication Shop - Lot 9 | 200 | 0 | 2023-10-28 | 2024-05-15 | 28-Oct-23 A | 15-May-24 A
HM-PL-1230 | Complete Line Pipe Production - Lot 9 | 65 | 0 | 2024-07-27 | 2024-09-28 | 16-May-24 A | 19-Jul-24 A
HM-PL-1260 | Complete External / Internal Coating - Lot 9 | 41 | 0 | 2024-09-29 | 2025-01-06 | 20-Jul-24 A | 30-Aug-24 A
HM-PL-1240 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 9 | 49 | 49 | 2025-01-07 | 2025-02-05 | 2025-01-12 | 2025-03-01 | 24
HM-PL-1250 | Ready for Dispatch of Line Pipes (Coated) - Lot 9 | 25 | 25 | 2025-02-06 | 2025-03-03 | 2025-03-02 | 2025-03-26 | 24
Delivery & receipt at Site |  | 265 | 133 | 2024-07-05 | 2025-03-26 | 05-Jul-24 A | 2025-03-26 | 24
HM-PL-0080 | Receipt at site and inspection of Line Pipes - Lot 1 (Coated) | 8 | 0 | 2024-07-05 | 2024-07-12 | 05-Jul-24 A | 12-Jul-24 A
HM-PL-0090 | Receipt at site and inspection of Line Pipes - Lot 2 (Coated) | 14 | 0 | 2024-07-13 | 2024-07-26 | 13-Jul-24 A | 26-Jul-24 A
HM-PL-1450 | Receipt at site and inspection of Line Pipes - Lot 4 (Coated) | 52 | 0 | 2024-07-24 | 2024-08-15 | 24-Jul-24 A | 13-Sep-24 A
HM-PL-0100 | Receipt at site and inspection of Line Pipes - Lot 3 (Coated) | 31 | 0 | 2024-07-28 | 2024-08-21 | 26-Aug-24 A | 26-Sep-24 A
HM-PL-1460 | Receipt at site and inspection of Line Pipes - Lot 5 (Coated) | 13 | 13 | 2024-09-08 | 2024-09-30 | 2024-11-14 | 2024-11-26 | 90
HM-PL-0110 | Receipt at site and inspection of Line Pipes - Lot 6 (Coated) | 25 | 25 | 2024-11-05 | 2024-11-29 | 2024-12-02 | 2024-12-26 | 18
HM-PL-0120 | Receipt at site and inspection of Line Pipes - Lot 7 (Coated) | 25 | 25 | 2024-12-19 | 2025-01-12 | 2025-01-12 | 2025-02-05 | 35
HM-PL-1470 | Receipt at site and inspection of Line Pipes - Lot 8 (Coated) | 38 | 38 | 2025-01-26 | 2025-02-19 | 2025-02-06 | 2025-03-15 | 35
HM-PL-960 | Receipt at site and inspection of Line Pipes - Lot 9 (Coated) | 23 | 23 | 2025-03-04 | 2025-03-26 | 2025-03-04 | 2025-03-26 | 24
Hot Tapping Material |  | 428 | 189 | 2024-03-01 | 2025-03-05 | 01-Mar-24 A | 2025-05-02 | 24
Manufacturing & Ready for Dispatch |  | 339 | 100 | 2024-03-01 | 2025-02-02 | 01-Mar-24 A | 2025-02-02 | 24
HM-PL-0250 | Vendor Document Review of Hot Tapping Material | 14 | 0 | 2024-03-01 | 2024-03-15 | 01-Mar-24 A | 15-Mar-24 A
HM-PL-0260 | Manufacturing & Assembly of Hot Tapping Material | 246 | 81 | 2024-07-27 | 2025-01-14 | 14-May-24 A | 2025-01-14 | 24
HM-PL-0270 | Testing and Inspection of Hot Tapping Material | 7 | 7 | 2025-01-15 | 2025-01-21 | 2025-01-15 | 2025-01-21 | 24
HM-PL-0280 | Packaging & Final Inspection-Hot Tapping Material | 7 | 7 | 2025-01-22 | 2025-01-28 | 2025-01-22 | 2025-01-28 | 24
HM-PL-0290 | Ready for Dispatch of Hot Tapping Material | 5 | 5 | 2025-01-29 | 2025-02-02 | 2025-01-29 | 2025-02-02 | 24
Delivery & receipt at Site |  | 89 | 89 | 2025-02-03 | 2025-03-05 | 2025-02-03 | 2025-05-02 | 24
HM-PL-0310 | Transportation/ Custom Clearance/ Delivery at site of Hot Tapping Material | 21 | 21 | 2025-02-03 | 2025-02-23 | 2025-02-03 | 2025-02-23 | 24
HM-PL-0320 | Receipt at site and inspection of Hot Tapping Material | 7 | 7 | 2025-02-24 | 2025-03-05 | 2025-04-25 | 2025-05-02 | 19
Pig Signler |  | 352 | 196 | 2024-07-27 | 2025-05-09 | 23-May-24 A | 2025-05-09 | 91
Manufacturing & Ready for Dispatch |  | 301 | 145 | 2024-07-27 | 2025-03-19 | 23-May-24 A | 2025-03-19 | 92
HM-PL-0460 | Vendor Document Review of Pig Signaler | 95 | 0 | 2024-07-27 | 2024-08-25 | 23-May-24 A | 25-Aug-24 A
HM-PL-0470 | Manufacturing & Assembly of Pig Signaler | 166 | 105 | 2024-08-26 | 2025-02-07 | 26-Aug-24 A | 2025-02-07 | 92
HM-PL-0480 | Testing and Inspection of Pig Signaler | 14 | 14 | 2025-02-08 | 2025-02-21 | 2025-02-08 | 2025-02-21 | 92
HM-PL-0490 | Packaging & Final Inspection-Pig Singler | 14 | 14 | 2025-02-22 | 2025-03-07 | 2025-02-22 | 2025-03-07 | 92
HM-PL-0500 | Ready for Dispatch of Pig Signaler | 12 | 12 | 2025-03-08 | 2025-03-19 | 2025-03-08 | 2025-03-19 | 92
Delivery & receipt at Site |  | 51 | 51 | 2025-03-20 | 2025-05-09 | 2025-03-20 | 2025-05-09 | 91
HM-PL-0520 | Transportation/ Custom Clearance/ Delivery at site of Pig Signaler (Lot 1) | 21 | 21 | 2025-03-20 | 2025-04-09 | 2025-03-20 | 2025-04-09 | 113
HM-PL-0530 | Receipt at site and inspection of Pig Signaler (Lot 1) | 7 | 7 | 2025-04-10 | 2025-04-17 | 2025-04-10 | 2025-04-17 | 92
HM-PL-1480 | Transportation/ Custom Clearance/ Delivery at site of Pig Signaler (Lot 2) | 21 | 21 | 2025-04-10 | 2025-04-30 | 2025-04-10 | 2025-04-30 | 92
HM-PL-1490 | Receipt at site and inspection of Pig Signaler (Lot 2) | 7 | 7 | 2025-05-01 | 2025-05-09 | 2025-05-01 | 2025-05-09 | 74
Hot Induction Bend |  | 424 | 92 | 2023-11-29 | 2024-10-31 | 29-Nov-23 A | 2025-01-26 | 61
Manufacturing & Ready for Dispatch |  | 387 | 55 | 2023-11-29 | 2024-10-06 | 29-Nov-23 A | 2024-12-19 | 60
HM-PL-0560 | Vendor Document Review of Hot Incution Bend | 58 | 0 | 2023-11-29 | 2024-01-26 | 29-Nov-23 A | 26-Jan-24 A
HM-PL-0570 | Manufacturing & Assembly of Hot Incution Bend | 300 | 20 | 2024-01-20 | 2024-08-25 | 20-Jan-24 A | 2024-11-14 | 60
HM-PL-0580 | Testing and Inspection of Hot Incution Bend | 30 | 30 | 2024-08-02 | 2024-09-15 | 2024-10-30 | 2024-11-28 | 60
HM-PL-0590 | Packaging & Final Inspection-Hot Incution Bend | 30 | 30 | 2024-08-09 | 2024-09-22 | 2024-11-06 | 2024-12-05 | 60
HM-PL-0600 | Ready for Dispatch of Hot Incution Bend | 30 | 30 | 2024-08-23 | 2024-10-06 | 2024-11-20 | 2024-12-19 | 60
Delivery & receipt at Site |  | 65 | 65 | 2024-09-04 | 2024-10-31 | 2024-11-22 | 2025-01-26 | 61
HM-PL-0630 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | 14 | 14 | 2024-09-10 | 2024-09-26 | 2024-11-22 | 2024-12-11 | 50
HM-PL-0620 | Transportation/ Custom Clearance/ Delivery at site of Hot Incution Bend | 21 | 21 | 2024-09-04 | 2024-10-13 | 2024-12-06 | 2024-12-26 | 60
HM-PL-0640 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | 21 | 21 | 2024-09-15 | 2024-10-31 | 2024-12-31 | 2025-01-26 | 43
Isolating Joints |  | 484 | 153 | 2023-11-30 | 2024-12-29 | 30-Nov-23 A | 2025-03-27 | 28
Manufacturing & Ready for Dispatch |  | 428 | 97 | 2023-11-30 | 2024-11-08 | 30-Nov-23 A | 2025-01-30 | 33
HM-PL-0670 | Vendor Document Review of Isolating Joints | 41 | 0 | 2023-11-30 | 2024-01-10 | 30-Nov-23 A | 10-Jan-24 A
HM-PL-0680 | Manufacturing & Assembly of Isolating Joints | 248 | 72 | 2024-05-03 | 2024-10-14 | 03-May-24 A | 2025-01-05 | 33
HM-PL-0690 | Testing and Inspection of Isolating Joints | 14 | 14 | 2024-10-15 | 2024-10-28 | 2025-01-06 | 2025-01-19 | 33
HM-PL-0700 | Packaging & Final Inspection-Isolating Joints | 7 | 7 | 2024-10-29 | 2024-11-04 | 2025-01-20 | 2025-01-26 | 33
HM-PL-0710 | Ready for Dispatch of Isolating Joints | 4 | 4 | 2024-11-05 | 2024-11-08 | 2025-01-27 | 2025-01-30 | 33
Delivery & receipt at Site |  | 56 | 56 | 2024-11-09 | 2024-12-29 | 2025-01-31 | 2025-03-27 | 28
HM-PL-0730 | Transportation/ Custom Clearance/ Delivery at site of Isolating Joints (Lot 1) | 7 | 7 | 2024-11-09 | 2024-11-15 | 2025-01-31 | 2025-02-06 | 68
HM-PL-0740 | Receipt at site and inspection of Isolating Joints (Lot 1) | 7 | 7 | 2024-11-17 | 2024-11-24 | 2025-02-07 | 2025-02-14 | 44
HM-PL-1500 | Transportation/ Custom Clearance/ Delivery at site of Isolating Joints (Lot 2) | 21 | 21 | 2024-11-30 | 2024-12-20 | 2025-02-21 | 2025-03-13 | 33
HM-PL-1510 | Receipt at site and inspection of Isolating Joints (Lot 2) | 7 | 7 | 2024-12-22 | 2024-12-29 | 2025-03-14 | 2025-03-27 | 19
Pigging & Split Tee |  | 305 | 153 | 2024-05-27 | 2025-03-14 | 27-May-24 A | 2025-03-27 | 101
Manufacturing & Ready for Dispatch |  | 260 | 108 | 2024-05-27 | 2025-01-31 | 27-May-24 A | 2025-02-10 | 76
HM-PL-0770 | Vendor Document Review of Pigging & Split Tee | 71 | 0 | 2024-05-27 | 2024-08-09 | 27-May-24 A | 05-Aug-24 A
HM-PL-0780 | Manufacturing & Assembly of Pigging & Split Tee | 164 | 83 | 2024-08-10 | 2025-01-06 | 06-Aug-24 A | 2025-01-16 | 76
HM-PL-0790 | Testing and Inspection of Pigging & Split Tee | 14 | 14 | 2025-01-07 | 2025-01-20 | 2025-01-17 | 2025-01-30 | 76
HM-PL-0800 | Packaging & Final Inspection-Pigging & Split Tee | 7 | 7 | 2025-01-21 | 2025-01-27 | 2025-01-31 | 2025-02-06 | 76
HM-PL-0810 | Ready for Dispatch of Pigging & Split Tee | 4 | 4 | 2025-01-28 | 2025-01-31 | 2025-02-07 | 2025-02-10 | 76
Delivery & receipt at Site |  | 45 | 45 | 2025-02-01 | 2025-03-14 | 2025-02-11 | 2025-03-27 | 101
HM-PL-0830 | Transportation/ Custom Clearance/ Delivery at site of Pigging & Split Tee (Lot 1) | 21 | 21 | 2025-02-01 | 2025-02-21 | 2025-02-11 | 2025-03-03 | 76
HM-PL-1520 | Transportation/ Custom Clearance/ Delivery at site of Pigging & Split Tee (Lot 2) | 21 | 21 | 2025-02-01 | 2025-02-21 | 2025-02-11 | 2025-03-03 | 116
HM-PL-0840 | Receipt at site and inspection of Pigging & Split Tee (Lot 1) | 7 | 7 | 2025-02-23 | 2025-03-04 | 2025-03-04 | 2025-03-17 | 52
HM-PL-1530 | Receipt at site and inspection of Pigging & Split Tee (Lot 2) | 9 | 9 | 2025-03-05 | 2025-03-14 | 2025-03-18 | 2025-03-27 | 101
Anchor Flanges |  | 268 | 152 | 2024-07-27 | 2025-01-14 | 02-Jul-24 A | 2025-03-26 | 44
Manufacturing & Ready for Dispatch |  | 216 | 100 | 2024-07-27 | 2024-11-25 | 02-Jul-24 A | 2025-02-02 | 48
HM-PL-890 | Vendor Document Review of Anchor Flanges | 53 | 0 | 2024-07-27 | 2024-08-09 | 02-Jul-24 A | 23-Aug-24 A
HM-PL-900 | Manufacturing & Assembly of Anchor Flanges | 146 | 75 | 2024-08-10 | 2024-10-31 | 16-Aug-24 A | 2025-01-08 | 48
HM-PL-930 | Testing and Inspection of Anchor Flanges | 14 | 14 | 2024-11-01 | 2024-11-14 | 2025-01-09 | 2025-01-22 | 48
HM-PL-910 | Packaging & Final Inspection-Anchor Flanges | 7 | 7 | 2024-11-15 | 2024-11-21 | 2025-01-23 | 2025-01-29 | 48
HM-PL-920 | Ready for Dispatch of Anchor Flanges | 4 | 4 | 2024-11-22 | 2024-11-25 | 2025-01-30 | 2025-02-02 | 48
Delivery & receipt at Site |  | 52 | 52 | 2024-11-26 | 2025-01-14 | 2025-02-03 | 2025-03-26 | 44
HM-PL-950 | Transportation/ Custom Clearance/ Delivery at site of Anchor Flanges (Lot 1) | 21 | 21 | 2024-11-26 | 2024-12-16 | 2025-02-03 | 2025-02-23 | 64
HM-PL-940 | Receipt at site and inspection of Anchor Flanges (Lot 1) | 7 | 7 | 2024-12-17 | 2024-12-24 | 2025-02-24 | 2025-03-05 | 41
HM-PL-1540 | Transportation/ Custom Clearance/ Delivery at site of Anchor Flanges (Lot 2) | 17 | 17 | 2024-12-17 | 2025-01-06 | 2025-02-24 | 2025-03-12 | 48
HM-PL-1550 | Receipt at site and inspection of Anchor Flanges (Lot 2) | 7 | 7 | 2025-01-07 | 2025-01-14 | 2025-03-13 | 2025-03-26 | 32
Bulk Material |  | 407 | 207 | 2024-04-09 | 2025-04-21 | 09-Apr-24 A | 2025-05-20 | 86
Power & Control Cables |  | 230 | 165 | 2024-09-13 | 2025-04-13 | 24-Aug-24 A | 2025-04-10 | 47
Manufacturing & Ready for Dispatch |  | 190 | 125 | 2024-09-13 | 2025-03-08 | 24-Aug-24 A | 2025-03-01 | 35
HM-EL-0010 | Vendor Document Review of Power & Control Cables | 48 | 0 | 2024-09-13 | 2024-10-13 | 24-Aug-24 A | 10-Oct-24 A
HM-EL-0020 | Manufacturing & Assembly of Power & Control Cables | 124 | 107 | 2024-10-13 | 2025-02-18 | 11-Oct-24 A | 2025-02-11 | 35
HM-EL-0030 | Testing and Inspection of Power & Control Cables | 7 | 7 | 2025-02-18 | 2025-02-25 | 2025-02-12 | 2025-02-18 | 35
HM-EL-0040 | Packaging & Final Inspection-Power & Control Cables | 7 | 7 | 2025-02-25 | 2025-03-04 | 2025-02-19 | 2025-02-25 | 35
HM-EL-0050 | Ready for Dispatch of Power & Control Cables | 4 | 4 | 2025-03-04 | 2025-03-08 | 2025-02-26 | 2025-03-01 | 35
Delivery & receipt at Site |  | 40 | 40 | 2025-03-08 | 2025-04-13 | 2025-03-02 | 2025-04-10 | 47
HM-EL-0070 | Transportation/ Custom Clearance/ Delivery at site of Power & Control Cables (Lot 1) | 7 | 7 | 2025-03-08 | 2025-03-15 | 2025-03-02 | 2025-03-08 | 71
HM-EL-0080 | Receipt at site and inspection of Power & Control Cables (Lot 1) | 8 | 8 | 2025-03-16 | 2025-03-24 | 2025-03-10 | 2025-03-17 | 71
HM-EL-620 | Transportation/ Custom Clearance/ Delivery at site of Power & Control Cables (Lot 2) | 7 | 7 | 2025-03-29 | 2025-04-05 | 2025-03-23 | 2025-03-29 | 35
HM-EL-630 | Receipt at site and inspection of Power & Control Cables (Lot 2) | 7 | 7 | 2025-04-06 | 2025-04-13 | 2025-04-03 | 2025-04-10 | 26
Cable Trays |  | 153 | 153 | 2024-10-11 | 2025-03-27 | 2024-10-26 | 2025-03-27 | 95
Manufacturing & Ready for Dispatch |  | 97 | 97 | 2024-10-11 | 2025-01-16 | 2024-10-26 | 2025-01-30 | 98
HM-EL-0210 | Vendor Document Review of Cable Trays | 12 | 12 | 2024-10-11 | 2024-10-23 | 2024-10-26 | 2024-11-06 | 98
HM-EL-0220 | Manufacturing & Assembly of Cable Trays | 60 | 60 | 2024-10-23 | 2024-12-22 | 2024-11-07 | 2025-01-05 | 98
HM-EL-0230 | Factory Acceptance Test of Cable Trays | 14 | 14 | 2024-12-22 | 2025-01-05 | 2025-01-06 | 2025-01-19 | 98
HM-EL-0240 | Packaging & Final Inspection-Cable Trays | 7 | 7 | 2025-01-05 | 2025-01-12 | 2025-01-20 | 2025-01-26 | 98
HM-EL-0250 | Ready for Dispatch of Cable Trays | 4 | 4 | 2025-01-12 | 2025-01-16 | 2025-01-27 | 2025-01-30 | 98
Delivery & receipt at Site |  | 81 | 81 | 2024-12-22 | 2025-03-27 | 2025-01-06 | 2025-03-27 | 95
HM-EL-0270 | Transportation/ Custom Clearance/ Delivery at site of Cable Trays (Lot 1) | 21 | 21 | 2024-12-22 | 2025-01-26 | 2025-01-06 | 2025-01-26 | 144
HM-EL-0280 | Receipt at site and inspection of Cable Trays (Lot 2) | 7 | 7 | 2025-01-27 | 2025-02-03 | 2025-01-27 | 2025-02-03 | 107
HM-EL-640 | Transportation/ Custom Clearance/ Delivery at site of Cable Trays (Lot 1) | 21 | 21 | 2025-02-06 | 2025-03-13 | 2025-02-21 | 2025-03-13 | 98
HM-EL-650 | Receipt at site and inspection of Cable Trays (Lot 2) | 7 | 7 | 2025-03-14 | 2025-03-27 | 2025-03-14 | 2025-03-27 | 71
Ball/ Globe/ Check/ Plug Valves |  | 301 | 139 | 2024-05-17 | 2025-02-16 | 17-May-24 A | 2025-03-13 | 42
Manufacturing & Ready for Dispatch |  | 252 | 90 | 2024-05-17 | 2025-01-04 | 17-May-24 A | 2025-01-23 | 47
HM-PL-0150 | Vendor Document Review of Ball/ Globe/ Check/ Plug Valves | 85 | 0 | 2024-05-17 | 2024-08-16 | 17-May-24 A | 09-Aug-24 A
HM-PL-0160 | Manufacturing & Assembly of Ball/ Globe/ Check/ Plug Valves | 142 | 65 | 2024-08-17 | 2024-12-10 | 10-Aug-24 A | 2024-12-29 | 47
HM-PL-0170 | Testing and Inspection of Ball/ Globe/ Check/ Plug Valves | 14 | 14 | 2024-12-11 | 2024-12-24 | 2024-12-30 | 2025-01-12 | 47
HM-PL-0180 | Packaging & Final Inspection-Ball/ Globe/ Check/ Plug Valves | 7 | 7 | 2024-12-25 | 2024-12-31 | 2025-01-13 | 2025-01-19 | 47
HM-PL-0190 | Ready for Dispatch of Ball/ Globe/ Check/ Plug Valves | 4 | 4 | 2025-01-01 | 2025-01-04 | 2025-01-20 | 2025-01-23 | 47
Delivery & receipt at Site |  | 74 | 74 | 2024-12-11 | 2025-02-16 | 2024-12-30 | 2025-03-13 | 42
HM-PL-0210 | Transportation/ Custom Clearance/ Delivery at site of Ball/ Globe/ Check/ Plug Valves (Lot 1) | 14 | 14 | 2024-12-11 | 2024-12-24 | 2024-12-30 | 2025-01-12 | 93
HM-PL-0220 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | 7 | 7 | 2024-12-25 | 2025-01-02 | 2025-01-13 | 2025-01-20 | 66
HM-PL-1560 | Transportation/ Custom Clearance/ Delivery at site of Ball/ Globe/ Check/ Plug Valves (Lot 2) | 14 | 14 | 2025-01-26 | 2025-02-08 | 2025-02-14 | 2025-02-27 | 47
HM-PL-1570 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | 7 | 7 | 2025-02-09 | 2025-02-16 | 2025-02-28 | 2025-03-13 | 26
Cable Gland and Termination |  | 172 | 172 | 2024-10-25 | 2025-04-21 | 2024-10-26 | 2025-04-15 | 113
Manufacturing & Ready for Dispatch |  | 108 | 108 | 2024-10-25 | 2025-02-16 | 2024-10-26 | 2025-02-10 | 110
HM-EL-530 | Vendor Document Review of Cable Gland and Termination | 10 | 10 | 2024-10-25 | 2024-11-08 | 2024-10-26 | 2024-11-04 | 110
HM-EL-540 | Manufacturing & Assembly of Cable Gland and Termination | 73 | 73 | 2024-11-08 | 2025-01-22 | 2024-11-05 | 2025-01-16 | 110
HM-EL-550 | Factory Acceptance Test of Cable Gland and Termination | 14 | 14 | 2025-01-22 | 2025-02-05 | 2025-01-17 | 2025-01-30 | 110
HM-EL-560 | Packaging & Final Inspection-Cable Gland and Termination | 7 | 7 | 2025-02-05 | 2025-02-12 | 2025-01-31 | 2025-02-06 | 110
HM-EL-570 | Ready for Dispatch of Cable Gland and Termination | 4 | 4 | 2025-02-12 | 2025-02-16 | 2025-02-07 | 2025-02-10 | 110
Delivery & receipt at Site |  | 89 | 89 | 2025-01-22 | 2025-04-21 | 2025-01-17 | 2025-04-15 | 113
HM-EL-590 | Transportation/ Custom Clearance/ Delivery at site of Cable Gland and Termination (Lot 1) | 35 | 35 | 2025-01-22 | 2025-02-26 | 2025-01-17 | 2025-02-20 | 159
HM-EL-580 | Receipt at site and inspection of Cable Gland and Termination (Lot 1) | 7 | 7 | 2025-02-27 | 2025-03-11 | 2025-02-21 | 2025-03-02 | 118
HM-EL-660 | Transportation/ Custom Clearance/ Delivery at site of Cable Gland and Termination (Lot 2) | 35 | 35 | 2025-03-09 | 2025-04-13 | 2025-03-04 | 2025-04-07 | 110
HM-EL-670 | Receipt at site and inspection of Cable Gland and Termination (Lot 2) | 7 | 7 | 2025-04-14 | 2025-04-21 | 2025-04-08 | 2025-04-15 | 90
Earthing |  | 156 | 156 | 2024-10-04 | 2025-04-12 | 2024-11-08 | 2025-04-13 | 77
Manufacturing & Ready for Dispatch |  | 91 | 91 | 2024-10-04 | 2025-02-06 | 2024-11-08 | 2025-02-07 | 77
HM-EL-0310 | Vendor Document Review of Earthing Material | 10 | 10 | 2024-10-04 | 2024-10-14 | 2024-11-08 | 2024-11-18 | 77
HM-EL-0320 | Manufacturing & Assembly of Earthing Material | 60 | 60 | 2024-10-14 | 2025-01-12 | 2024-11-18 | 2025-01-17 | 77
HM-EL-0330 | Factory Acceptance Test of Earthing Material | 10 | 10 | 2025-01-12 | 2025-01-26 | 2025-01-17 | 2025-01-27 | 77
HM-EL-0340 | Packaging & Final Inspection-Earthing Material | 7 | 7 | 2025-01-26 | 2025-02-02 | 2025-01-27 | 2025-02-03 | 77
HM-EL-0350 | Ready for Dispatch of Earthing Material | 4 | 4 | 2025-02-02 | 2025-02-06 | 2025-02-03 | 2025-02-07 | 77
Delivery & receipt at Site |  | 86 | 86 | 2025-01-12 | 2025-04-12 | 2025-01-17 | 2025-04-13 | 77
HM-EL-0370 | Transportation/ Custom Clearance/ Delivery at site of Earthing Material (Lot 1) | 31 | 31 | 2025-01-12 | 2025-02-16 | 2025-01-17 | 2025-02-17 | 122
HM-EL-0380 | Receipt at site and inspection of Earthing Material (Lot 1) | 7 | 7 | 2025-02-17 | 2025-02-24 | 2025-02-18 | 2025-02-25 | 88
HM-EL-680 | Transportation/ Custom Clearance/ Delivery at site of Earthing Material (Lot 2) | 35 | 35 | 2025-02-27 | 2025-04-03 | 2025-02-28 | 2025-04-04 | 77
HM-EL-690 | Receipt at site and inspection of Earthing Material (Lot 2) | 9 | 9 | 2025-04-03 | 2025-04-12 | 2025-04-04 | 2025-04-13 | 77
MCT |  | 172 | 172 | 2024-10-04 | 2025-04-03 | 2024-11-29 | 2025-05-20 | 40
Manufacturing & Ready for Dispatch |  | 129 | 129 | 2024-10-04 | 2025-02-10 | 2024-11-29 | 2025-04-07 | 38
HM-EL-0410 | Vendor Document Review of MCT | 14 | 14 | 2024-10-04 | 2024-10-18 | 2024-11-29 | 2024-12-13 | 38
HM-EL-0420 | Manufacturing & Assembly of MCT | 90 | 90 | 2024-10-18 | 2025-01-16 | 2024-12-13 | 2025-03-13 | 38
HM-EL-0430 | Factory Acceptance Test of MCT | 14 | 14 | 2025-01-16 | 2025-01-30 | 2025-03-13 | 2025-03-27 | 38
HM-EL-0440 | Packaging & Final Inspection-MCT | 7 | 7 | 2025-01-30 | 2025-02-06 | 2025-03-27 | 2025-04-03 | 38
HM-EL-0450 | Ready for Dispatch of MCT | 4 | 4 | 2025-02-06 | 2025-02-10 | 2025-04-03 | 2025-04-07 | 38
Delivery & receipt at Site |  | 68 | 68 | 2025-01-16 | 2025-04-03 | 2025-03-13 | 2025-05-20 | 40
HM-EL-0470 | Transportation/ Custom Clearance/ Delivery at site of MCT (Lot 1) | 35 | 35 | 2025-01-16 | 2025-02-20 | 2025-03-13 | 2025-04-17 | 65
HM-EL-0480 | Receipt at site and inspection of MCT (Lot 1) | 8 | 8 | 2025-02-20 | 2025-02-28 | 2025-04-17 | 2025-04-25 | 65
HM-EL-700 | Transportation/ Custom Clearance/ Delivery at site of MCT (Lot 2) | 14 | 14 | 2025-03-03 | 2025-03-17 | 2025-04-28 | 2025-05-12 | 38
HM-EL-710 | Receipt at site and inspection of MCT (Lot 2) | 7 | 7 | 2025-03-18 | 2025-04-03 | 2025-05-13 | 2025-05-20 | 30
Civil Bulk material |  | 260 | 59 | 2024-04-09 | 2024-12-20 | 09-Apr-24 A | 2024-12-25 | 57
Manufacturing & Ready for Dispatch |  | 253 | 47 | 2024-04-09 | 2024-10-25 | 09-Apr-24 A | 2024-12-17 | 57
HM-CS-0010 | 1st Civil Bulk material MTO | 142 | 0 | 2024-04-09 | 2024-08-25 | 09-Apr-24 A | 28-Aug-24 A
HM-CS-0020 | Final Civil Bulk material MTO | 47 | 47 | 2024-09-08 | 2024-10-25 | 2024-10-31 | 2024-12-17 | 57
Delivery & Receipt at site |  | 87 | 48 | 2024-08-26 | 2024-12-20 | 10-Sep-24 A | 2024-12-25 | 48
HM-CS-0040 | 1st Civil Bulk material MTO | 84 | 45 | 2024-08-26 | 2024-10-17 | 10-Sep-24 A | 2024-12-20 | 37
HM-CS-0050 | Final Civil Bulk material MTO | 45 | 45 | 2024-10-27 | 2024-12-20 | 2024-10-30 | 2024-12-25 | 48
Structural Bulk material |  | 116 | 116 | 2024-08-16 | 2025-01-30 | 2024-11-15 | 2025-03-12 | 41
Manufacturing & Ready for Dispatch |  | 106 | 106 | 2024-08-16 | 2024-12-17 | 2024-11-15 | 2025-03-01 | 41
HM-CS-0080 | 1st Structural Bulk material MTO | 90 | 90 | 2024-08-16 | 2024-11-14 | 2024-11-15 | 2025-02-13 | 24
HM-CS-0090 | Final Structural Bulk material MTO | 60 | 60 | 2024-10-18 | 2024-12-17 | 2024-12-31 | 2025-03-01 | 41
Delivery & Receipt at site |  | 47 | 47 | 2024-11-15 | 2025-01-30 | 2025-01-12 | 2025-03-12 | 25
HM-CS-0110 | 1st Structural Bulk material MTO | 37 | 37 | 2024-11-15 | 2024-12-31 | 2025-01-12 | 2025-02-24 | 14
HM-CS-0120 | Final Structural Bulk material MTO | 37 | 37 | 2024-12-18 | 2025-01-30 | 2025-01-23 | 2025-03-12 | 25
Piping Bulk material |  | 159 | 159 | 2024-07-27 | 2025-03-19 | 2024-10-26 | 2025-04-03 | 44
Manufacturing & Ready for Dispatch |  | 145 | 145 | 2024-07-27 | 2025-01-02 | 2024-10-26 | 2025-03-19 | 44
HM-PI-0010 | 1st Piping Bulk material MTO | 100 | 100 | 2024-07-27 | 2024-11-03 | 2024-10-26 | 2025-02-02 | 44
HM-PI-0020 | Final Piping Bulk material MTO | 106 | 106 | 2024-09-19 | 2025-01-02 | 2024-12-04 | 2025-03-19 | 44
Delivery & Receipt at site |  | 98 | 98 | 2024-11-04 | 2025-03-19 | 2024-12-26 | 2025-04-03 | 44
HM-PI-0040 | 1st Piping Bulk material MTO | 60 | 60 | 2024-11-04 | 2025-01-02 | 2024-12-26 | 2025-02-23 | 59
HM-PI-0050 | Final Piping Bulk material MTO | 58 | 58 | 2025-01-03 | 2025-03-19 | 2025-01-09 | 2025-04-03 | 37
Piping Special Items |  | 155 | 155 | 2024-08-16 | 2025-04-16 | 2024-10-26 | 2025-03-29 | 25
Manufacturing & Ready for Dispatch |  | 140 | 140 | 2024-08-16 | 2025-03-17 | 2024-10-26 | 2025-03-14 | 25
HM-PI-60 | 1st Piping Special Items MTO | 130 | 130 | 2024-08-16 | 2025-01-26 | 2024-10-26 | 2025-03-04 | 26
HM-PI-50 | Final Piping Special Items MTO | 140 | 140 | 2024-10-18 | 2025-03-17 | 2024-10-26 | 2025-03-14 | 25
Delivery & Receipt at site |  | 24 | 24 | 2025-01-27 | 2025-04-16 | 2025-03-06 | 2025-03-29 | 25
HM-PI-80 | 1st Piping Special Items MTO | 15 | 15 | 2025-01-27 | 2025-02-26 | 2025-03-06 | 2025-03-20 | 26
HM-PI-70 | Final Piping Special Items MTO | 15 | 15 | 2025-03-17 | 2025-04-16 | 2025-03-15 | 2025-03-29 | 25
Pipeline Bulk material |  | 33 | 33 | 2024-08-02 | 2024-08-25 | 2024-10-26 | 2024-11-27 | 130
Manufacturing & Ready for Dispatch |  | 17 | 17 | 2024-08-02 | 2024-08-17 | 2024-10-26 | 2024-11-11 | 117
HM-PL-0850 | 1st Pipeline Bulk material MTO | 10 | 10 | 2024-08-02 | 2024-08-17 | 2024-10-26 | 2024-11-04 | 44
HM-PL-0860 | Final Pipeline Bulk material MTO | 17 | 17 | 2024-08-02 | 2024-08-17 | 2024-10-26 | 2024-11-11 | 117
Delivery & Receipt at site |  | 20 | 20 | 2024-08-18 | 2024-08-25 | 2024-11-05 | 2024-11-27 | 93
HM-PL-0880 | 1st Pipeline Bulk material MTO | 7 | 7 | 2024-08-18 | 2024-08-25 | 2024-11-05 | 2024-11-12 | 35
HM-PL-0890 | Final Pipeline Bulk material MTO | 14 | 14 | 2024-08-18 | 2024-08-25 | 2024-11-12 | 2024-11-27 | 93
Electrical Bulk material |  | 204 | 204 | 2024-09-06 | 2025-03-21 | 2024-10-26 | 2025-05-17 | 89
Manufacturing & Ready for Dispatch |  | 165 | 165 | 2024-09-06 | 2025-02-18 | 2024-10-26 | 2025-04-08 | 97
HM-EL-0490 | 1st Electrical Bulk material MTO | 100 | 100 | 2024-09-06 | 2024-12-15 | 2024-10-26 | 2025-02-02 | 48
HM-EL-0500 | Final Electrical Bulk material MTO | 87 | 87 | 2024-11-23 | 2025-02-18 | 2025-01-12 | 2025-04-08 | 97
Delivery & Receipt at site |  | 104 | 104 | 2024-12-16 | 2025-03-21 | 2025-02-03 | 2025-05-17 | 89
HM-EL-0520 | 1st Electrical Bulk material MTO | 50 | 50 | 2024-12-16 | 2025-02-12 | 2025-02-03 | 2025-04-17 | 34
HM-EL-0530 | Final Electrical Bulk material MTO | 30 | 30 | 2025-02-19 | 2025-03-21 | 2025-04-17 | 2025-05-17 | 89
Instrumentation Bulk material |  | 168 | 168 | 2024-09-20 | 2025-03-23 | 2024-10-26 | 2025-04-11 | 125
Manufacturing & Ready for Dispatch |  | 103 | 103 | 2024-09-20 | 2025-01-29 | 2024-10-26 | 2025-02-05 | 137
HM-IC-0010 | 1st Instrumentation Bulk material MTO | 100 | 100 | 2024-09-20 | 2024-12-29 | 2024-10-26 | 2025-02-02 | 126
HM-IC-0020 | Final Instrumentation Bulk material MTO | 75 | 75 | 2024-11-15 | 2025-01-29 | 2024-11-22 | 2025-02-05 | 137
Delivery & Receipt at site |  | 68 | 68 | 2024-12-30 | 2025-03-23 | 2025-02-03 | 2025-04-11 | 125
HM-IC-0050 | Final Instrumentation Bulk material MTO | 53 | 53 | 2025-01-29 | 2025-03-23 | 2025-02-05 | 2025-03-30 | 137
HM-IC-0040 | 1st Instrumentation Bulk material MTO | 45 | 45 | 2024-12-30 | 2025-02-20 | 2025-02-03 | 2025-04-11 | 90
Telecom Bulk material |  | 165 | 165 | 2024-09-20 | 2025-04-08 | 2024-10-26 | 2025-04-08 | 107
Manufacturing & Ready for Dispatch |  | 120 | 120 | 2024-09-20 | 2025-03-09 | 2024-10-26 | 2025-02-22 | 122
HM-TL-0010 | 1st Telecom Bulk material MTO | 100 | 100 | 2024-09-20 | 2024-12-29 | 2024-10-26 | 2025-02-02 | 63
HM-TL-0020 | Final Telecom Bulk material MTO | 60 | 60 | 2025-01-08 | 2025-03-09 | 2024-12-24 | 2025-02-22 | 122
Delivery & Receipt at site |  | 65 | 65 | 2024-12-30 | 2025-04-08 | 2025-02-03 | 2025-04-08 | 107
HM-TL-0050 | Final Telecom Bulk material MTO | 30 | 30 | 2025-03-09 | 2025-04-08 | 2025-02-22 | 2025-03-24 | 122
HM-TL-0040 | 1st Telecom Bulk material MTO | 42 | 42 | 2024-12-30 | 2025-02-17 | 2025-02-03 | 2025-04-08 | 40
Construction & Commissioning |  | 905 | 440 | 2023-07-19 | 2026-01-09 | 19-Jul-23 A | 2026-01-09 | 0
General |  | 611 | 220 | 2023-10-02 | 2025-02-23 | 02-Oct-23 A | 2025-06-04 | 82
Construction NOC's |  | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1300 | Construction NOC from Musanada | 273 | 5 | 2023-10-02 | 2024-08-02 | 02-Oct-23 A | 2024-11-01 | 0
C-GOV-1000 | Construction NOC from AAM | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1010 | Construction NOC from ADM | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1020 | Construction NOC from DMT | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1030 | Construction NOC from DRM | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1040 | Construction NOC from ADDC | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1050 | Construction NOC from AADC | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1060 | Construction NOC from ADM Al Wathba | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1070 | Construction NOC from ADM Musaffah | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1080 | Construction NOC from ADM City Centre | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1090 | Construction NOC from ADM Al Shahama | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1100 | Construction NOC from ADNOC | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1110 | Construction NOC from ADSSC | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1120 | Construction NOC from DCT | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1130 | Construction NOC from AAM Parks | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1140 | Construction NOC from DRM Parks | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1150 | Construction NOC from AAM Roads | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1160 | Construction NOC from DRM Roads | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1170 | Construction NOC from DEL | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1180 | Construction NOC from DU | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1190 | Construction NOC from EAD | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1200 | Construction NOC from Ethiad Rail | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1210 | Construction NOC from Etisalat | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1220 | Construction NOC from GRQ Military | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1230 | Construction NOC from ITC ROW | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1240 | Construction NOC from MCC | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1250 | Construction NOC from TADWEER | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1260 | Construction NOC from TRANSCO | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1270 | Construction NOC from Zone Cops | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1280 | Construction NOC from CICPA | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
C-GOV-1290 | Construction NOC from BARARI | 289 | 21 | 2023-10-02 | 2024-08-26 | 02-Oct-23 A | 2024-11-25 | 0
Permits/Approvals |  | 287 | 95 | 2024-01-18 | 2024-12-10 | 18-Jan-24 A | 2025-03-12 | 89
C-PER-1050 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 4 | 42 | 0 | 2024-01-18 | 2024-03-18 | 18-Jan-24 A | 18-Mar-24 A
C-PER-1040 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 3 | 36 | 0 | 2024-02-23 | 2024-04-23 | 23-Feb-24 A | 23-Apr-24 A
C-PER-1000 | Receiving Permits-56" Pipelines & Stations,4" Pipeline | 37 | 0 | 2024-02-29 | 2024-04-29 | 29-Feb-24 A | 29-Apr-24 A
C-PER-1110 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 10 | 37 | 0 | 2024-03-07 | 2024-05-07 | 07-Mar-24 A | 07-May-24 A
C-PER-0915 | Mobilization of Job Performers-56" Pipelines & Stations,4" Pipeline | 26 | 0 | 2024-04-09 | 2024-05-17 | 09-Apr-24 A | 17-May-24 A
C-PER-1130 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 12 | 17 | 0 | 2024-05-04 | 2024-05-28 | 04-May-24 A | 28-May-24 A
C-PER-1140 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13 | 34 | 0 | 2024-05-06 | 2024-06-25 | 06-May-24 A | 25-Jun-24 A
C-PER-1090 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 8 | 39 | 0 | 2024-05-09 | 2024-07-09 | 09-May-24 A | 09-Jul-24 A
C-PER-1100 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 9 | 39 | 0 | 2024-05-09 | 2024-07-09 | 09-May-24 A | 09-Jul-24 A
C-PER-1150 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13A | 46 | 0 | 2024-05-06 | 2024-07-14 | 06-May-24 A | 14-Jul-24 A
C-PER-1160 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 14 | 28 | 0 | 2024-05-30 | 2024-07-14 | 30-May-24 A | 14-Jul-24 A
C-PER-1060 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 5 | 39 | 0 | 2024-05-15 | 2024-07-15 | 15-May-24 A | 15-Jul-24 A
C-PER-1080 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 7 | 39 | 0 | 2024-05-15 | 2024-07-15 | 15-May-24 A | 15-Jul-24 A
C-PER-1180 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | 29 | 0 | 2024-05-30 | 2024-07-15 | 30-May-24 A | 15-Jul-24 A
C-PER-1190 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 17 | 18 | 0 | 2024-06-30 | 2024-07-26 | 30-Jun-24 A | 26-Jul-24 A
C-PER-1280 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 25A | 40 | 0 | 2024-05-28 | 2024-07-26 | 28-May-24 A | 26-Jul-24 A
C-PER-1580 | NOC & Permits-BVS01-52" | 127 | 0 | 2024-04-25 | 2024-09-16 | 25-Apr-24 A | 25-Oct-24 A
C-PER-1590 | NOC & Permits-BVS02-52" | 128 | 0 | 2024-04-25 | 2024-09-16 | 25-Apr-24 A | 2024-10-28 | 18
C-PER-1600 | NOC & Permits-BVS03-52" | 128 | 0 | 2024-04-25 | 2024-09-16 | 25-Apr-24 A | 2024-10-28 | 13
C-PER-1610 | NOC & Permits-BVS04-52" | 128 | 0 | 2024-04-25 | 2024-09-16 | 25-Apr-24 A | 2024-10-28 | 8
C-PER-1440 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 10 | 83 | 5 | 2024-07-10 | 2024-10-10 | 10-Jul-24 A | 2024-11-01 | 17
C-PER-1350 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 1 | 91 | 9 | 2024-07-03 | 2024-10-02 | 03-Jul-24 A | 2024-11-07 | 62
C-PER-1210 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 19 | 7 | 7 | 2024-09-23 | 2024-11-22 | 2024-11-04 | 2024-11-12 | 48
C-PER-1220 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 20 | 7 | 7 | 2024-07-29 | 2024-10-18 | 2024-11-04 | 2024-11-12 | 66
C-PER-1620 | NOC & Permits-BVS05-52" | 143 | 15 | 2024-04-25 | 2024-09-16 | 25-Apr-24 A | 2024-11-15 | 37
C-PER-1250 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 23 | 11 | 11 | 2024-08-12 | 2024-11-01 | 2024-11-04 | 2024-11-18 | 33
C-PER-1020 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 1 | 155 | 19 | 2024-04-15 | 2024-06-15 | 15-Apr-24 A | 2024-11-21 | 94
C-PER-1340 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 31 | 96 | 20 | 2024-07-12 | 2024-10-04 | 12-Jul-24 A | 2024-11-22 | 141
C-PER-1630 | NOC & Permits-BVS06-52" | 148 | 20 | 2024-04-25 | 2024-09-16 | 25-Apr-24 A | 2024-11-22 | 39
C-PER-1460 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 12 | 88 | 21 | 2024-07-25 | 2024-10-21 | 25-Jul-24 A | 2024-11-25 | 8
C-PER-1450 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 11 | 10 | 10 | 2024-08-22 | 2024-10-02 | 2024-11-14 | 2024-11-27 | 8
C-PER-1420 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 8 | 19 | 19 | 2024-08-12 | 2024-09-20 | 2024-11-04 | 2024-11-28 | 8
C-PER-1650 | NOC & Permits-Sweihan CRS | 20 | 20 | 2024-08-26 | 2024-12-10 | 2024-11-04 | 2024-11-29 | 4
C-PER-1260 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 24 | 107 | 29 | 2024-07-10 | 2024-11-21 | 10-Jul-24 A | 2024-12-09 | 23
C-PER-1360 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 2 | 26 | 26 | 2024-08-13 | 2024-09-23 | 2024-11-05 | 2024-12-12 | 8
C-PER-1390 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 5 | 30 | 30 | 2024-09-17 | 2024-10-28 | 2024-11-04 | 2024-12-17 | 104
C-PER-1030 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 2 | 38 | 38 | 2024-07-29 | 2024-08-29 | 2024-10-28 | 2024-12-20 | 97
C-PER-1300 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 27 | 115 | 40 | 2024-07-14 | 2024-10-04 | 14-Jul-24 A | 2024-12-24 | 19
C-PER-1370 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 3 | 37 | 37 | 2024-08-13 | 2024-09-23 | 2024-11-05 | 2024-12-27 | 8
C-PER-1070 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 6 | 124 | 45 | 2024-07-09 | 2024-09-27 | 09-Jul-24 A | 2024-12-31 | 72
C-PER-1200 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 18 | 120 | 45 | 2024-07-13 | 2024-10-25 | 13-Jul-24 A | 2024-12-31 | 34
C-PER-1310 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 28 | 121 | 45 | 2024-07-12 | 2024-10-04 | 12-Jul-24 A | 2024-12-31 | 139
C-PER-1320 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 29 | 120 | 45 | 2024-07-13 | 2024-10-04 | 13-Jul-24 A | 2024-12-31 | 133
C-PER-1400 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 6 | 112 | 45 | 2024-07-25 | 2024-10-22 | 25-Jul-24 A | 2024-12-31 | 128
C-PER-1380 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 4 | 30 | 30 | 2024-10-07 | 2024-11-15 | 2024-11-22 | 2025-01-07 | 124
C-PER-1470 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 13 | 45 | 45 | 2024-08-12 | 2024-09-20 | 2024-11-04 | 2025-01-08 | 32
C-PER-1480 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 1 | 45 | 45 | 2024-07-29 | 2024-09-27 | 2024-11-04 | 2025-01-08 | 72
C-PER-1490 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 2 | 45 | 45 | 2024-08-05 | 2024-10-04 | 2024-11-04 | 2025-01-08 | 78
C-PER-1500 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 3 | 45 | 45 | 2024-08-05 | 2024-10-04 | 2024-11-04 | 2025-01-08 | 84
C-PER-1510 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 4 | 45 | 45 | 2024-08-05 | 2024-10-04 | 2024-11-04 | 2025-01-08 | 50
C-PER-1560 | Trial pit, Crossing Methodology, NOC & Permits-4" Water Pipeline-NDRC 1 | 45 | 45 | 2024-08-05 | 2024-10-04 | 2024-11-04 | 2025-01-08 | 49
C-PER-1430 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 9 | 45 | 45 | 2024-09-11 | 2024-11-12 | 2024-12-06 | 2025-02-07 | 88
C-PER-1330 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 30 | 150 | 75 | 2024-07-15 | 2024-10-04 | 15-Jul-24 A | 2025-02-12 | 3
C-PER-1520 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 5 | 45 | 45 | 2024-10-07 | 2024-12-10 | 2025-01-09 | 2025-03-12 | 50
C-PER-1530 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 6 | 45 | 45 | 2024-10-07 | 2024-12-10 | 2025-01-09 | 2025-03-12 | 56
C-PER-1540 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 7 | 45 | 45 | 2024-10-07 | 2024-12-10 | 2025-01-09 | 2025-03-12 | 61
C-PER-1550 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 8 | 45 | 45 | 2024-10-07 | 2024-12-10 | 2025-01-09 | 2025-03-12 | 66
C-PER-1570 | Trial pit, Crossing Methodology, NOC & Permits-4" Water Pipeline-NDRC 2 | 45 | 45 | 2024-10-07 | 2024-12-10 | 2025-01-09 | 2025-03-12 | 49
Construction Procedure Qualification |  | 344 | 82 | 2024-05-09 | 2024-10-17 | 09-May-24 A | 2025-04-17 | 39
C-COM-1000 | Procedure Qualification Material (56", 52", 42", 30", Test Rings etc) Receipt at Site | 0 | 0 |  | 2024-05-31 |  | 31-May-24 A
C-COM-1010 | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | 70 | 0 | 2024-05-09 | 2024-08-28 | 09-May-24 A | 30-Jul-24 A
C-COM-1020 | Procedure Qualification (PQT/WQT for Hot Tapping - 48", 42",36 & 30") | 60 | 60 | 2024-07-28 | 2024-10-17 | 2025-01-26 | 2025-04-17 | 27
Construction Procedures / Method Statements / ITPs |  | 70 | 70 | 2024-07-28 | 2024-10-25 | 2024-10-27 | 2025-01-20 | 120
C-COM-750 | Issue ICR-Construction Procedures / Method Statements / ITPs | 30 | 30 | 2024-07-28 | 2024-08-30 | 2024-10-27 | 2024-11-29 | 120
C-COM-760 | Receive Company Comments-Construction Procedures / Method Statements / ITPs | 30 | 30 | 2024-08-08 | 2024-09-11 | 2024-11-07 | 2024-12-15 | 120
C-COM-770 | Re-Issue for Approval-Construction Procedures / Method Statements / ITPs | 30 | 30 | 2024-08-20 | 2024-09-24 | 2024-11-19 | 2024-12-26 | 120
C-COM-780 | Obtain Company Approval-Construction Procedures / Method Statements / ITPs | 30 | 30 | 2024-09-01 | 2024-10-06 | 2024-12-04 | 2025-01-08 | 120
C-COM-790 | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | 10 | 10 | 2024-10-15 | 2024-10-25 | 2025-01-09 | 2025-01-20 | 120
Shutdown Requirements & Plan |  | 130 | 130 | 2024-09-08 | 2025-02-17 | 2024-12-11 | 2025-05-29 | 66
C-COM-850 | Issue ICR-Shutdown Requirements & Plan | 40 | 40 | 2024-09-08 | 2024-10-24 | 2024-12-11 | 2025-01-27 | 66
C-COM-860 | Receive Company Comments-Shutdown Requirements & Plan | 10 | 10 | 2024-10-25 | 2024-11-05 | 2025-01-28 | 2025-02-07 | 66
C-COM-870 | Re-Issue for Approval-Shutdown Requirements & Plan | 30 | 30 | 2024-11-06 | 2024-12-13 | 2025-02-09 | 2025-03-25 | 66
C-COM-880 | Obtain Company Approval-Shutdown Requirements & Plan | 10 | 10 | 2024-12-15 | 2024-12-25 | 2025-03-25 | 2025-04-11 | 66
C-COM-890 | Final Issue for Design/ Construction-Shutdown Requirements & Plan | 40 | 40 | 2025-01-02 | 2025-02-17 | 2025-04-13 | 2025-05-29 | 66
Pre-commissioning and commissioning philosophy |  | 40 | 40 | 2024-08-05 | 2024-09-27 | 2024-10-28 | 2024-12-24 | 133
HE-PR-0910 | Issue ICR - Pre-commissioning and commissioning philosophy | 10 | 10 | 2024-08-05 | 2024-08-16 | 2024-10-28 | 2024-11-08 | 133
HE-PR-0920 | Receive Company Comments - Pre-commissioning and commissioning philosophy | 10 | 10 | 2024-08-19 | 2024-08-30 | 2024-11-11 | 2024-11-22 | 133
HE-PR-0930 | Re-Issue for Approval - Pre-commissioning and commissioning philosophy | 5 | 5 | 2024-09-02 | 2024-09-06 | 2024-11-25 | 2024-11-29 | 133
HE-PR-0940 | Obtain Company Approval - Pre-commissioning and commissioning philosophy | 10 | 10 | 2024-09-09 | 2024-09-20 | 2024-12-04 | 2024-12-17 | 133
HE-PR-0950 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | 5 | 5 | 2024-09-23 | 2024-09-27 | 2024-12-18 | 2024-12-24 | 133
Pre-commissioning and Commissioning Plan |  | 49 | 49 | 2025-01-02 | 2025-02-23 | 2025-04-08 | 2025-06-04 | 66
C-COM-800 | Issue ICR-Pre-commissioning and Commissioning Plan | 10 | 10 | 2025-01-02 | 2025-01-13 | 2025-04-08 | 2025-04-18 | 75
C-COM-810 | Receive Company Comments-Pre-commissioning and Commissioning Plan | 10 | 10 | 2025-01-14 | 2025-01-24 | 2025-04-20 | 2025-04-30 | 75
C-COM-820 | Re-Issue for Approval-Pre-commissioning and Commissioning Plan | 5 | 5 | 2025-01-26 | 2025-01-30 | 2025-05-01 | 2025-05-06 | 75
C-COM-830 | Obtain Company Approval-Pre-commissioning and Commissioning Plan | 10 | 10 | 2025-01-30 | 2025-02-11 | 2025-05-06 | 2025-05-19 | 75
C-COM-840 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | 5 | 5 | 2025-02-18 | 2025-02-23 | 2025-05-29 | 2025-06-04 | 66
Temporary Site Facilities |  | 262 | 0 | 2023-07-19 | 2024-06-11 | 19-Jul-23 A | 11-Jun-24 A
Engineeirng Office |  | 40 | 0 | 2023-07-19 | 2023-09-05 | 19-Jul-23 A | 05-Sep-23 A
CTF-SO1080 | Engineering Office at NPCC | 40 | 0 | 2023-07-19 | 2023-09-05 | 19-Jul-23 A | 05-Sep-23 A
Mobilization & TSF |  | 262 | 0 | 2023-07-19 | 2024-06-11 | 19-Jul-23 A | 11-Jun-24 A
CTF-1000 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | 121 | 0 | 2023-07-19 | 2023-12-11 | 19-Jul-23 A | 11-Dec-23 A
CTF-SO1000 | Main Office | 80 | 0 | 2023-09-10 | 2023-12-15 | 10-Sep-23 A | 15-Dec-23 A
CTF-1010 | NOC's / Approval /Survey | 65 | 0 | 2023-10-02 | 2023-12-19 | 02-Oct-23 A | 19-Dec-23 A
CTF-SO1020 | Satellite Office-1 | 96 | 0 | 2023-11-22 | 2024-03-20 | 22-Nov-23 A | 20-Mar-24 A
CTF-SO1040 | Construction Plant & Equipment Facilities | 130 | 0 | 2023-12-11 | 2024-05-27 | 11-Dec-23 A | 27-May-24 A
CTF-SO1050 | Fabrication Facilities | 127 | 0 | 2023-12-15 | 2024-05-28 | 15-Dec-23 A | 28-May-24 A
CTF-SO1060 | Ware House & Storage Facilities | 128 | 0 | 2023-12-15 | 2024-05-29 | 15-Dec-23 A | 29-May-24 A
CTF-SO1030 | Satellite Office-2 | 124 | 0 | 2023-12-20 | 2024-05-30 | 20-Dec-23 A | 30-May-24 A
CTF-SO1010 | Camp Facilities | 184 | 0 | 2023-10-18 | 2024-06-07 | 18-Oct-23 A | 07-Jun-24 A
CTF-SO1070 | Laboratory Facilities | 64 | 0 | 2024-03-13 | 2024-06-11 | 13-Mar-24 A | 11-Jun-24 A
Construction & Precommissioning |  | 558 | 303 | 2023-12-18 | 2025-11-09 | 18-Dec-23 A | 2025-11-03 | 7
Construction |  | 547 | 292 | 2023-12-18 | 2025-11-01 | 18-Dec-23 A | 2025-10-21 | 17
Habshan Complex to 56” P/L Fac. (56”) |  | 379 | 232 | 2024-07-27 | 2025-09-01 | 05-Jun-24 A | 2025-09-15 | 19
Pig Launcher 607-V-603 (56'' Pipeline) |  | 372 | 211 | 2024-07-27 | 2025-09-01 | 05-Jun-24 A | 2025-09-06 | 21
Pig Launcher 607-V-603 (56'' Pipeline) |  | 372 | 211 | 2024-07-27 | 2025-09-01 | 05-Jun-24 A | 2025-09-06 | 21
Civil Works |  | 369 | 208 | 2024-07-27 | 2025-09-01 | 05-Jun-24 A | 2025-09-02 | 24
Earthworks, Site Preparation, Site Grading CCOHBCS200 |  | 270 | 109 | 2024-07-27 | 2025-03-06 | 05-Jun-24 A | 2025-05-05 | 55
C-56-PL-607-CI-1000 | Site Survey, Preparation & Grading Works | 55 | 0 | 2024-07-27 | 2024-08-12 | 05-Jun-24 A | 12-Aug-24 A
C-56-PL-607-CI-1010 | Earth Works for Equipment Foundations | 15 | 15 | 2024-09-04 | 2024-10-07 | 2024-12-18 | 2025-01-04 | 21
C-56-PL-607-CI-1020 | Earth Works for Pipe Support Foundations | 15 | 15 | 2024-10-08 | 2024-11-13 | 2025-01-06 | 2025-01-22 | 30
C-56-PL-607-CI-1030 | Earth Works for Field Instrument, JBs & Light Pole Foundations | 14 | 14 | 2024-11-30 | 2024-12-18 | 2025-01-23 | 2025-02-07 | 30
C-56-PL-607-CI-1040 | Earth Works for Access Platforms & Misc. Structural Foundations | 21 | 21 | 2024-12-27 | 2025-01-21 | 2025-02-17 | 2025-03-15 | 30
C-56-PL-607-CI-1050 | Earth Works for Thrust Anchor Block | 30 | 30 | 2025-01-30 | 2025-03-06 | 2025-03-26 | 2025-05-05 | 55
Compaction & Testing CCOHBCS201 |  | 102 | 102 | 2024-10-08 | 2025-03-18 | 2025-01-06 | 2025-05-15 | 55
C-56-PL-607-CI-1200 | Compaction & Testing for Equipment Foundations | 14 | 14 | 2024-10-08 | 2024-10-23 | 2025-01-06 | 2025-01-21 | 21
C-56-PL-607-CI-1210 | Compaction & Testing for Pipe Support Foundations | 14 | 14 | 2024-11-14 | 2024-11-29 | 2025-01-23 | 2025-02-07 | 34
C-56-PL-607-CI-1220 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | 14 | 14 | 2024-12-23 | 2025-01-08 | 2025-02-12 | 2025-02-27 | 37
C-56-PL-607-CI-1230 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | 14 | 14 | 2025-01-25 | 2025-02-10 | 2025-03-20 | 2025-04-11 | 30
C-56-PL-607-CI-1240 | Compaction & Testing for Thrust Anchor Block | 5 | 5 | 2025-03-11 | 2025-03-18 | 2025-05-09 | 2025-05-15 | 55
Concrete Works (Foundations for Equipment ) CCOHBCS202.1 |  | 92 | 92 | 2024-10-24 | 2025-03-18 | 2025-01-22 | 2025-05-20 | 26
C-56-PL-607-CI-1400 | Concrete Works for Equipment Foundations | 28 | 28 | 2024-10-24 | 2024-11-25 | 2025-01-22 | 2025-02-22 | 21
C-56-PL-607-CI-1410 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | 14 | 14 | 2025-01-18 | 2025-02-03 | 2025-03-26 | 2025-04-16 | 26
C-56-PL-607-CI-1420 | Concrete Works for Access Platforms & Misc. Structural Foundations | 21 | 21 | 2025-02-19 | 2025-03-18 | 2025-04-24 | 2025-05-20 | 26
Concrete Works (Impact Wall ) CCOHBCS202.3 |  | 29 | 0 | 2024-10-24 | 2025-01-04 | 21-Sep-24 A | 25-Oct-24 A
C-56-PL-607-CI-1500 | Concrete Works (Impact Wall ) (Deleted) | 29 | 0 | 2024-10-24 | 2025-01-04 | 21-Sep-24 A | 25-Oct-24 A
Concrete Works (Foundations for Pipe Supports) CCOHBCS202.2 |  | 15 | 15 | 2024-11-30 | 2025-01-09 | 2025-02-24 | 2025-03-15 | 21
C-56-PL-607-CI-1600 | Concrete Works for Pipe Support Foundations | 15 | 15 | 2024-11-30 | 2025-01-09 | 2025-02-24 | 2025-03-15 | 21
Trenching for Electrical cables CCOHBCS205.1 |  | 14 | 14 | 2025-03-26 | 2025-04-16 | 2025-06-02 | 2025-06-20 | 21
C-56-PL-607-CI-1800 | Electrical & Earthing Cable Trenching | 14 | 14 | 2025-03-26 | 2025-04-16 | 2025-06-02 | 2025-06-20 | 21
Fire Point Shelters CCOHBSS301 |  | 24 | 0 | 2025-01-10 | 2025-01-16 | 27-Sep-24 A | 25-Oct-24 A
C-56-PL-607-CI-2400 | Fire Point SheltersCCOHBSS301 (Deleted) | 24 | 0 | 2025-01-10 | 2025-01-16 | 27-Sep-24 A | 25-Oct-24 A
Pipe Supports Fabrication & Installation CCOHBSS300 |  | 30 | 30 | 2025-01-10 | 2025-03-03 | 2025-03-15 | 2025-04-26 | 24
C-56-PL-607-CI-2000 | Pre-Fabrication & Installation of Pipe Supports | 30 | 30 | 2025-01-10 | 2025-03-03 | 2025-03-15 | 2025-04-26 | 24
Thrust Anchor BlockCCOHBCS210 |  | 60 | 60 | 2025-03-19 | 2025-06-04 | 2025-05-20 | 2025-08-01 | 51
C-56-PL-607-CI-1510 | Concrete Works for Thrust Anchor Block | 60 | 60 | 2025-03-19 | 2025-06-04 | 2025-05-20 | 2025-08-01 | 51
Trenching for Instrument cablesCCOHBCS205.2 |  | 14 | 14 | 2025-04-16 | 2025-05-02 | 2025-06-20 | 2025-07-08 | 30
C-56-PL-607-CI-1810 | Instrument & Telecom Cable Trenching | 14 | 14 | 2025-04-16 | 2025-05-02 | 2025-06-20 | 2025-07-08 | 30
Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS304 |  | 35 | 35 | 2025-05-21 | 2025-07-04 | 2025-05-22 | 2025-07-05 | 24
C-56-PL-607-CI-3000 | Pre-Fabrication & Installation of Platforms & Crossovers | 28 | 28 | 2025-05-21 | 2025-06-25 | 2025-05-22 | 2025-06-26 | 24
C-56-PL-607-CI-3010 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | 21 | 21 | 2025-06-09 | 2025-07-04 | 2025-06-10 | 2025-07-05 | 24
Installation of Fence Type-4CCOHBCS206.1 |  | 45 | 45 | 2025-05-16 | 2025-07-29 | 2025-06-04 | 2025-07-30 | 24
C-56-PL-607-CI-2220 | Installation of Fence Type-4 (Deleted) | 45 | 45 | 2025-05-16 | 2025-07-29 | 2025-06-04 | 2025-07-30 | 24
Backfilling for CablesCCOHBCS212 |  | 20 | 20 | 2025-07-26 | 2025-08-19 | 2025-07-12 | 2025-08-04 | 39
C-56-PL-607-CI-2800 | Back Filling for Electrical & Earthing Cable | 10 | 10 | 2025-07-26 | 2025-08-07 | 2025-07-12 | 2025-07-23 | 39
C-56-PL-607-CI-2810 | Back Filling for Instrument & Telecom Cable | 10 | 10 | 2025-08-07 | 2025-08-19 | 2025-07-24 | 2025-08-04 | 39
Paving WorksCCOHBCS208 |  | 14 | 14 | 2025-08-15 | 2025-09-01 | 2025-08-16 | 2025-09-02 | 24
C-56-PL-607-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 14 | 14 | 2025-08-15 | 2025-09-01 | 2025-08-16 | 2025-09-02 | 24
Installation of 6m wide double leaf vehicular access gatesCCOHBCS206.2 |  | 10 | 10 | 2025-07-29 | 2025-08-09 | 2025-07-30 | 2025-08-11 | 24
C-56-PL-607-CI-2230 | Installation of 6m wide double leaf vehicular access gates (Deleted) | 10 | 10 | 2025-07-29 | 2025-08-09 | 2025-07-30 | 2025-08-11 | 24
Installation of 1m wide single leaf vehicular access gatesCCOHBCS206.3 |  | 5 | 5 | 2025-08-09 | 2025-08-15 | 2025-08-11 | 2025-08-16 | 24
C-56-PL-607-CI-2240 | Installation of 1m wide single leaf vehicular access gates (Deleted) | 5 | 5 | 2025-08-09 | 2025-08-15 | 2025-08-11 | 2025-08-16 | 24
Mechanical Works & Equipment Installation |  | 56 | 56 | 2025-03-19 | 2025-05-28 | 2025-03-18 | 2025-05-29 | 92
Installation of Pig Launcher (607-V-603)CCOHBME303 |  | 8 | 8 | 2025-03-19 | 2025-04-04 | 2025-03-18 | 2025-04-03 | 124
C-56-PL-607-ME-1000 | Installation of Pig Launcher (607-V-603) 56" | 8 | 8 | 2025-03-19 | 2025-04-04 | 2025-03-18 | 2025-04-03 | 124
Installation of Pig Signaler (607-V-603)CCOHBME318 |  | 3 | 3 | 2025-05-09 | 2025-05-13 | 2025-05-09 | 2025-05-13 | 93
C-56-PL-607-ME-1200 | Installation of Pig Signaler (607-V-603)CCOHBME318 (Deleted) | 3 | 3 | 2025-05-09 | 2025-05-13 | 2025-05-09 | 2025-05-13 | 93
Installation of Filter PackageCCOHBME328 |  | 3 | 3 | 2025-05-24 | 2025-05-28 | 2025-05-27 | 2025-05-29 | 92
C-56-PL-607-ME-1400 | Installation of Filter PackageCCOHBME328 (Deleted) | 3 | 3 | 2025-05-24 | 2025-05-28 | 2025-05-27 | 2025-05-29 | 92
Installation of Fire Fighting & Safety EquipmentCCOHBME338 |  | 3 | 3 | 2025-05-24 | 2025-05-28 | 2025-05-27 | 2025-05-29 | 92
C-56-PL-607-ME-1600 | Installation of Fire Fighting & Safety EquipmentCCOHBME338 (Deleted) | 3 | 3 | 2025-05-24 | 2025-05-28 | 2025-05-27 | 2025-05-29 | 92
Piping Works |  | 101 | 101 | 2025-03-03 | 2025-06-23 | 2025-03-29 | 2025-08-01 | 51
Piping Pre-FabricationCCOHBPI302 |  | 37 | 37 | 2025-03-03 | 2025-04-25 | 2025-04-26 | 2025-06-12 | 24
C-56-PL-607-PI-1000 | Piping Pre-Fabrication | 37 | 37 | 2025-03-03 | 2025-04-25 | 2025-04-26 | 2025-06-12 | 24
ErectionCCOHBPI322 |  | 24 | 24 | 2025-04-25 | 2025-05-24 | 2025-06-12 | 2025-07-11 | 35
C-56-PL-607-PI-1200 | Piping Erection | 24 | 24 | 2025-04-25 | 2025-05-24 | 2025-06-12 | 2025-07-11 | 35
Field Joint Welding & NDTCCOHBPI332 |  | 27 | 27 | 2025-05-01 | 2025-06-03 | 2025-06-18 | 2025-07-21 | 51
C-56-PL-607-PI-1400 | Field Joint Welding | 24 | 24 | 2025-05-01 | 2025-05-30 | 2025-06-18 | 2025-07-17 | 35
C-56-PL-607-PI-1410 | NDT & Coating for Field Joint Weld | 24 | 24 | 2025-05-05 | 2025-06-03 | 2025-06-21 | 2025-07-21 | 51
HydrotestingCCOHBPI342 |  | 5 | 5 | 2025-06-03 | 2025-06-11 | 2025-07-21 | 2025-07-26 | 51
C-56-PL-607-PI-1600 | Hydrotesting | 5 | 5 | 2025-06-03 | 2025-06-11 | 2025-07-21 | 2025-07-26 | 51
Installation of ValvesCCOHBPI352 |  | 5 | 5 | 2025-06-11 | 2025-06-17 | 2025-07-26 | 2025-08-01 | 51
C-56-PL-607-PI-1800 | Installation of Valves/MOV/ROV | 5 | 5 | 2025-06-11 | 2025-06-17 | 2025-07-26 | 2025-08-01 | 51
Final Bolt Torquing/ Re-InstatementCCOHBPI362 |  | 5 | 5 | 2025-06-17 | 2025-06-23 | 2025-03-29 | 2025-04-07 | 89
C-56-PL-607-PI-2000 | Final Bolt Torquing/ Re-Instatement | 5 | 5 | 2025-06-17 | 2025-06-23 | 2025-03-29 | 2025-04-07 | 89
Pipeline Works |  | 8 | 8 | 2025-06-26 | 2025-07-07 | 2025-08-11 | 2025-08-20 | 35
Pig Launcher 607-V-603 56'' Pipeline/Piping Hook-upCCOHBPI312 |  | 8 | 8 | 2025-06-26 | 2025-07-07 | 2025-08-11 | 2025-08-20 | 35
C-56-PL-607-PL-1000 | Installation of Isolation Joint | 2 | 2 | 2025-06-26 | 2025-06-30 | 2025-08-11 | 2025-08-13 | 35
C-56-PL-607-PL-1010 | Field Joint Welding (Piping/Pipeline Section including IJ) | 5 | 5 | 2025-06-28 | 2025-07-04 | 2025-08-12 | 2025-08-18 | 35
C-56-PL-607-PL-1020 | NDT for Weld Joint | 5 | 5 | 2025-06-30 | 2025-07-05 | 2025-08-13 | 2025-08-19 | 35
C-56-PL-607-PL-1030 | Ext. Coating for Weld Joint | 5 | 5 | 2025-07-01 | 2025-07-07 | 2025-08-14 | 2025-08-20 | 35
Electrical & Instrumentation Works |  | 109 | 109 | 2025-04-25 | 2025-08-02 | 2025-04-26 | 2025-09-06 | 21
E&I Cable Laying, Glanding & TerminationCCOHBEL201 |  | 62 | 62 | 2025-05-19 | 2025-08-02 | 2025-06-24 | 2025-09-06 | 21
C-56-PL-607-EI-2000 | Electrical & Earthing Cable Laying | 14 | 14 | 2025-05-19 | 2025-06-04 | 2025-06-24 | 2025-07-11 | 21
C-56-PL-607-EI-2040 | Loop Checking for Instruments | 8 | 8 | 2025-07-17 | 2025-07-26 | 2025-07-03 | 2025-07-11 | 39
C-56-PL-607-EI-2020 | Installation of Cable Trays | 6 | 6 | 2025-06-04 | 2025-06-13 | 2025-07-11 | 2025-07-18 | 21
C-56-PL-607-CA-1000 | CP Cable Laying | 6 | 6 | 2025-06-04 | 2025-06-13 | 2025-07-11 | 2025-07-18 | 57
C-56-PL-607-CA-1010 | Installation of CP Test Post | 2 | 2 | 2025-06-13 | 2025-06-16 | 2025-07-18 | 2025-07-21 | 57
C-56-PL-607-CA-1020 | Installation of CP JB's | 2 | 2 | 2025-06-16 | 2025-06-18 | 2025-07-21 | 2025-07-23 | 57
C-56-PL-607-CA-1030 | Glanding & Termination for CP S/m | 2 | 2 | 2025-06-18 | 2025-06-20 | 2025-07-23 | 2025-07-25 | 57
C-56-PL-607-EI-2010 | Instrument Cable Laying | 14 | 14 | 2025-06-13 | 2025-07-01 | 2025-07-18 | 2025-08-04 | 21
C-56-PL-607-EI-1600 | Installation RTU | 5 | 5 | 2025-07-01 | 2025-07-07 | 2025-08-04 | 2025-08-09 | 28
C-56-PL-607-EI-2030 | Instrument Tubing Works | 12 | 12 | 2025-07-01 | 2025-07-15 | 2025-08-04 | 2025-08-18 | 21
C-56-PL-607-EI-1810 | Installation of JB's & PDB's | 10 | 10 | 2025-07-16 | 2025-07-26 | 2025-08-18 | 2025-08-29 | 21
C-56-PL-607-EI-2050 | Glanding & Termination | 6 | 6 | 2025-07-28 | 2025-08-02 | 2025-08-29 | 2025-09-06 | 21
Deep Earth WellCCOHBEL200 |  | 6 | 6 | 2025-06-23 | 2025-06-30 | 2025-07-11 | 2025-07-17 | 57
C-56-PL-607-EI-1400 | Deep Earth Well Drilling | 6 | 6 | 2025-06-23 | 2025-06-30 | 2025-07-11 | 2025-07-17 | 57
Field InstrumentsCCOHBEL223 |  | 48 | 48 | 2025-04-25 | 2025-07-10 | 2025-04-26 | 2025-06-24 | 39
C-56-PL-607-EI-2210 | Pre-Fabrication & Installation of Field Instrument, JB Supports | 21 | 21 | 2025-04-25 | 2025-05-21 | 2025-04-26 | 2025-05-22 | 24
C-56-PL-607-EI-2200 | Installation of Field Instruments (Including Pig Signaller) | 14 | 14 | 2025-06-23 | 2025-07-10 | 2025-06-09 | 2025-06-24 | 39
F&G DevicesCCOHBEL233 |  | 6 | 6 | 2025-07-10 | 2025-07-17 | 2025-06-25 | 2025-07-02 | 39
C-56-PL-607-EI-2410 | Installation of F&G Device | 6 | 6 | 2025-07-10 | 2025-07-17 | 2025-06-25 | 2025-07-02 | 39
Light Pole, Lighting & FixturesCCOHBEL213 |  | 6 | 6 | 2025-07-09 | 2025-07-15 | 2025-07-19 | 2025-07-25 | 40
C-56-PL-607-EI-1800 | Installation of Light Pole, Lighting & Fixtures | 6 | 6 | 2025-07-09 | 2025-07-15 | 2025-07-19 | 2025-07-25 | 40
Telecommunication Works |  | 21 | 21 | 2025-07-01 | 2025-07-31 | 2025-08-04 | 2025-08-28 | 28
PIDS SystemCCOHBIC211 |  | 8 | 8 | 2025-07-11 | 2025-07-19 | 2025-08-07 | 2025-08-16 | 28
C-56-PL-607-TE-1200 | Installation of PIDS/ PLDS System | 8 | 8 | 2025-07-11 | 2025-07-19 | 2025-08-07 | 2025-08-16 | 28
Telephone SystemCCOHBIC221 |  | 21 | 21 | 2025-07-01 | 2025-07-31 | 2025-08-04 | 2025-08-28 | 28
C-56-PL-607-TE-1410 | Installation of Out Door FOC Splicing Box | 3 | 3 | 2025-07-01 | 2025-07-04 | 2025-08-04 | 2025-08-07 | 28
C-56-PL-607-TE-1400 | Telephone SystemCCOHBIC221 (Deleted) | 15 | 15 | 2025-07-07 | 2025-07-24 | 2025-08-09 | 2025-08-27 | 29
C-56-PL-607-TE-1420 | FO Cable OTDR Testing & Splicing | 2 | 2 | 2025-07-30 | 2025-07-31 | 2025-08-26 | 2025-08-28 | 28
CCTV SystemCCOHBIC231 |  | 8 | 8 | 2025-07-21 | 2025-07-29 | 2025-08-16 | 2025-08-26 | 28
C-56-PL-607-TE-1600 | Installation of CCTV System | 8 | 8 | 2025-07-21 | 2025-07-29 | 2025-08-16 | 2025-08-26 | 28
Electrical Building Type II |  | 316 | 224 | 2024-09-18 | 2025-08-27 | 13-Aug-24 A | 2025-09-04 | 22
L4-Electrical Building Type II |  | 316 | 224 | 2024-09-18 | 2025-08-27 | 13-Aug-24 A | 2025-09-04 | 22
Civil Works |  | 198 | 106 | 2024-09-18 | 2025-04-12 | 13-Aug-24 A | 2025-04-15 | 140
Excavation WorksCCOHBCS104 |  | 38 | 0 | 2024-09-18 | 2024-10-29 | 13-Aug-24 A | 26-Sep-24 A
C-56-EB2-CI-1000 | Site Survey, Preparation & Grading Works | 10 | 0 | 2024-09-18 | 2024-09-28 | 13-Aug-24 A | 23-Aug-24 A
C-56-EB2-CI-1010 | Earth Works for Ground Level | 22 | 0 | 2024-09-30 | 2024-10-23 | 25-Aug-24 A | 20-Sep-24 A
C-56-EB2-CI-1020 | Compaction & Testing for Ground Level | 23 | 0 | 2024-10-05 | 2024-10-29 | 30-Aug-24 A | 26-Sep-24 A
Foundation Works (for Substructure)CCOHBCS107 |  | 25 | 0 | 2024-10-30 | 2024-11-30 | 26-Sep-24 A | 25-Oct-24 A
C-56-EB2-CI-1200 | Building Foundation Works (for Substructure) | 25 | 0 | 2024-10-30 | 2024-11-30 | 26-Sep-24 A | 25-Oct-24 A
Concrete Superstructure WorksCCOHBCS109 |  | 76 | 22 | 2024-12-04 | 2024-12-28 | 27-Sep-24 A | 2024-12-26 | 53
C-56-EB2-CI-1400 | Concrete Superstructure Works | 76 | 22 | 2024-12-04 | 2024-12-28 | 27-Sep-24 A | 2024-12-26 | 53
Masonry WorksCCOHBCS113 |  | 35 | 35 | 2024-12-30 | 2025-02-08 | 2024-12-27 | 2025-02-06 | 53
C-56-EB2-CI-1600 | Masonry Works - Internal | 21 | 21 | 2024-12-30 | 2025-01-23 | 2024-12-27 | 2025-01-21 | 53
C-56-EB2-CI-1610 | Masonry Works - External | 14 | 14 | 2025-01-24 | 2025-02-08 | 2025-01-22 | 2025-02-06 | 53
Finishing WorksCCOHBCS116 |  | 24 | 24 | 2025-01-24 | 2025-02-20 | 2025-01-22 | 2025-02-18 | 144
C-56-EB2-CI-1810 | Internal Finishing Works | 14 | 14 | 2025-01-24 | 2025-02-08 | 2025-01-22 | 2025-02-06 | 104
C-56-EB2-CI-1800 | External Finishing Works | 10 | 10 | 2025-02-10 | 2025-02-20 | 2025-02-07 | 2025-02-18 | 144
Metal WorksCCOHBCS117 |  | 14 | 14 | 2025-02-21 | 2025-03-11 | 2025-02-24 | 2025-03-14 | 140
C-56-EB2-CI-2000 | Steel Structural Works | 14 | 14 | 2025-02-21 | 2025-03-11 | 2025-02-24 | 2025-03-14 | 140
Paving WorksCCOHBCS118 |  | 21 | 21 | 2025-03-11 | 2025-04-12 | 2025-03-14 | 2025-04-15 | 140
C-56-EB2-CI-2010 | Paving Works | 21 | 21 | 2025-03-11 | 2025-04-12 | 2025-03-14 | 2025-04-15 | 140
Mechanical Works |  | 54 | 54 | 2025-04-12 | 2025-06-18 | 2025-03-29 | 2025-06-04 | 45
HVAC System & Plumbing WorksCCOHBME308 |  | 42 | 42 | 2025-04-12 | 2025-06-02 | 2025-03-29 | 2025-05-21 | 45
C-56-EB2-ME-1000 | Plumbing Works | 21 | 21 | 2025-04-12 | 2025-05-08 | 2025-03-29 | 2025-04-25 | 45
C-56-EB2-ME-1010 | HVAC Works | 21 | 21 | 2025-05-08 | 2025-06-02 | 2025-04-26 | 2025-05-21 | 45
Inergen SystemCCOHBME348 |  | 12 | 12 | 2025-06-02 | 2025-06-18 | 2025-05-21 | 2025-06-04 | 45
C-56-EB2-ME-1200 | Inergen SystemCCOHBME348 (Deleted) | 12 | 12 | 2025-06-02 | 2025-06-18 | 2025-05-21 | 2025-06-04 | 45
Electrical & Instrumentation Works |  | 77 | 77 | 2025-06-04 | 2025-08-22 | 2025-05-29 | 2025-08-30 | 23
Power Distribution SystemCCOHBEL202 |  | 5 | 5 | 2025-06-20 | 2025-06-26 | 2025-05-29 | 2025-06-04 | 45
C-56-EB2-EI-1000 | Installation of Power Distribution System | 5 | 5 | 2025-06-20 | 2025-06-26 | 2025-05-29 | 2025-06-04 | 45
E&I Cable Laying, Glanding & TerminationCCOHBEL203 |  | 54 | 54 | 2025-06-04 | 2025-08-22 | 2025-06-28 | 2025-08-30 | 23
C-56-EB2-EI-1200 | Custody Metering Panel Installation | 6 | 6 | 2025-07-18 | 2025-07-25 | 2025-06-28 | 2025-07-05 | 45
C-56-EB2-EI-1210 | E&I Cable Laying | 21 | 21 | 2025-06-04 | 2025-07-02 | 2025-07-11 | 2025-08-05 | 22
C-56-EB2-EI-1220 | MCT Installation | 8 | 8 | 2025-07-30 | 2025-08-08 | 2025-08-05 | 2025-08-14 | 25
C-56-EB2-EI-1230 | Glanding & Termination | 12 | 12 | 2025-08-08 | 2025-08-22 | 2025-08-16 | 2025-08-30 | 23
Lighting SystemCCOHBEL253 |  | 14 | 14 | 2025-06-26 | 2025-07-14 | 2025-06-04 | 2025-06-23 | 46
C-56-EB2-EI-1400 | Lighting & Fixtures | 14 | 14 | 2025-06-26 | 2025-07-14 | 2025-06-04 | 2025-06-23 | 46
Earthing & Lightning Protection systemCCOHBEL263 |  | 14 | 14 | 2025-07-14 | 2025-07-30 | 2025-07-19 | 2025-08-05 | 25
C-56-EB2-EI-1600 | Earthing & Lightning Protection system | 14 | 14 | 2025-07-14 | 2025-07-30 | 2025-07-19 | 2025-08-05 | 25
F&G SystemCCOHBEL273 |  | 8 | 8 | 2025-07-02 | 2025-07-11 | 2025-08-05 | 2025-08-14 | 25
C-56-EB2-EI-1800 | Installation F&G System | 8 | 8 | 2025-07-02 | 2025-07-11 | 2025-08-05 | 2025-08-14 | 25
HSSD SystemCCOHBEL283 |  | 12 | 12 | 2025-06-26 | 2025-07-11 | 2025-06-04 | 2025-06-20 | 45
C-56-EB2-EI-2000 | Installation of HSSD System | 12 | 12 | 2025-06-26 | 2025-07-11 | 2025-06-04 | 2025-06-20 | 45
RTU SystemCCOHBEL303 |  | 6 | 6 | 2025-07-11 | 2025-07-18 | 2025-06-20 | 2025-06-28 | 45
C-56-EB2-EI-2200 | Installation of RTU System | 6 | 6 | 2025-07-11 | 2025-07-18 | 2025-06-20 | 2025-06-28 | 45
UPS (6KVA)CCOHBEL293 |  | 10 | 10 | 2025-07-02 | 2025-07-14 | 2025-08-05 | 2025-08-16 | 23
C-56-EB2-EI-2400 | UPS (10KVA) Installation | 10 | 10 | 2025-07-02 | 2025-07-14 | 2025-08-05 | 2025-08-16 | 23
Telecommunication Works |  | 25 | 25 | 2025-07-25 | 2025-08-23 | 2025-08-02 | 2025-09-01 | 22
SDH CabinetCCOHBIC201 |  | 8 | 8 | 2025-07-25 | 2025-08-04 | 2025-08-02 | 2025-08-12 | 22
C-56-EB2-TE-1000 | SDH Cabinet Installation | 8 | 8 | 2025-07-25 | 2025-08-04 | 2025-08-02 | 2025-08-12 | 22
Telecom System (Including subcontract for FOC Splicing / Termination / Testing)CCOHBIC241 |  | 9 | 9 | 2025-08-11 | 2025-08-21 | 2025-08-19 | 2025-08-29 | 22
C-56-EB2-TE-1400 | Telecom System (Including subcontract for FOC Splicing / Termination / Testing) | 9 | 9 | 2025-08-11 | 2025-08-21 | 2025-08-19 | 2025-08-29 | 22
Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOHBIC251 |  | 17 | 17 | 2025-08-04 | 2025-08-23 | 2025-08-12 | 2025-09-01 | 22
C-56-EB2-TE-1600 | CCTV Installation | 6 | 6 | 2025-08-04 | 2025-08-11 | 2025-08-12 | 2025-08-19 | 22
C-56-EB2-TE-1610 | Security System (Including subcontract for FOC Splicing / Termination / Testing ) | 9 | 9 | 2025-08-13 | 2025-08-23 | 2025-08-21 | 2025-09-01 | 22
Shut Down Work |  | 3 | 3 | 2025-08-23 | 2025-08-27 | 2025-09-01 | 2025-09-04 | 22
Shutdown Connection to Existing Substation Unit 607CCOHBST204 |  | 3 | 3 | 2025-08-23 | 2025-08-27 | 2025-09-01 | 2025-09-04 | 22
C-56-EB2-EL-1600 | Termination & Connection with Existing Power Distribution Network | 3 | 3 | 2025-08-23 | 2025-08-27 | 2025-09-01 | 2025-09-04 | 22
Gas Source Tie-ins to 56'' P/L Station (0.2 Km) (Hot Tap) |  | 286 | 189 | 2024-11-25 | 2025-08-09 | 27-Sep-24 A | 2025-09-15 | 19
Gas Source Tie-ins to 56'' P/L Station (0.2 Km) (Hot Tap) |  | 286 | 189 | 2024-11-25 | 2025-08-09 | 27-Sep-24 A | 2025-09-15 | 19
Civil Works |  | 202 | 105 | 2024-11-25 | 2025-05-22 | 27-Sep-24 A | 2025-06-04 | 49
Demolition Works (Paving)CCOHBCS300 |  | 7 | 7 | 2024-11-25 | 2024-12-09 | 2025-01-22 | 2025-01-29 | 7
C-56-G-HT-CI-0100 | Demolition of Existing Paving | 7 | 7 | 2024-11-25 | 2024-12-09 | 2025-01-22 | 2025-01-29 | 7
Excavation WorksCCOHBCS301 |  | 25 | 25 | 2024-12-09 | 2025-01-30 | 2025-01-30 | 2025-02-27 | 7
C-56-G-HT-CI-1000 | Site Survey, Preparation & Grading Works | 8 | 8 | 2024-12-09 | 2024-12-18 | 2025-01-30 | 2025-02-07 | 7
C-56-G-HT-CI-1020 | Earth Works for Pipe Support Foundations | 6 | 6 | 2024-12-18 | 2025-01-04 | 2025-02-08 | 2025-02-14 | 7
C-56-G-HT-CI-1210 | Compaction & Testing for Pipe Support Foundations | 5 | 5 | 2025-01-04 | 2025-01-14 | 2025-02-15 | 2025-02-20 | 13
C-56-G-HT-CI-1040 | Earth Works for Access Platforms & Misc. Structural Foundations | 6 | 6 | 2025-01-04 | 2025-01-21 | 2025-02-15 | 2025-02-21 | 7
C-56-G-HT-CI-1230 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | 5 | 5 | 2025-01-21 | 2025-01-30 | 2025-02-22 | 2025-02-27 | 7
Concrete WorksCCOHBCS302 |  | 7 | 7 | 2025-01-30 | 2025-02-24 | 2025-02-28 | 2025-03-09 | 7
C-56-G-HT-CI-1600 | Concrete Works for Pipe Support Foundations | 7 | 7 | 2025-01-30 | 2025-02-24 | 2025-02-28 | 2025-03-09 | 7
Concrete ProtectionCCOHBCS304 |  | 158 | 43 | 2025-01-30 | 2025-03-26 | 27-Sep-24 A | 2025-04-12 | 20
C-56-G-HT-CI-1700 | Concrete ProtectionCCOHBCS304 (Deleted) | 158 | 43 | 2025-01-30 | 2025-03-26 | 27-Sep-24 A | 2025-04-12 | 20
Pipe Supports Fabrication & InstallationCCOHBSS307 |  | 21 | 21 | 2025-04-26 | 2025-05-22 | 2025-05-10 | 2025-06-04 | 49
C-56-G-HT-CI-2000 | Pipe Supports Fabrication & Installation | 21 | 21 | 2025-04-26 | 2025-05-22 | 2025-05-10 | 2025-06-04 | 49
Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS310 |  | 21 | 21 | 2025-02-24 | 2025-03-25 | 2025-03-09 | 2025-04-11 | 7
C-56-G-HT-CI-1420 | Concrete Works for Access Platforms & Misc. Structural Foundations | 21 | 21 | 2025-02-24 | 2025-03-25 | 2025-03-09 | 2025-04-11 | 7
Paving WorksCCOHBCS305 |  | 14 | 14 | 2025-03-25 | 2025-04-15 | 2025-04-11 | 2025-04-28 | 7
C-56-G-HT-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 14 | 14 | 2025-03-25 | 2025-04-15 | 2025-04-11 | 2025-04-28 | 7
Piping Works |  | 132 | 132 | 2025-04-25 | 2025-08-05 | 2025-02-24 | 2025-08-11 | 49
Piping Pre-FabricationCCOHBPI309 |  | 28 | 28 | 2025-04-25 | 2025-05-29 | 2025-02-24 | 2025-04-07 | 98
C-56-G-HT-PI-1000 | Piping Pre-Fabrication | 28 | 28 | 2025-04-25 | 2025-05-29 | 2025-02-24 | 2025-04-07 | 98
ErectionCCOHBPI372 |  | 21 | 21 | 2025-05-29 | 2025-06-25 | 2025-06-04 | 2025-07-02 | 49
C-56-G-HT-PI-1200 | Piping Erection | 21 | 21 | 2025-05-29 | 2025-06-25 | 2025-06-04 | 2025-07-02 | 49
Field Joint Welding & NDTCCOHBPI382 |  | 31 | 31 | 2025-06-07 | 2025-07-15 | 2025-06-13 | 2025-07-21 | 49
C-56-G-HT-PI-1400 | Field Joint Welding | 28 | 28 | 2025-06-07 | 2025-07-11 | 2025-06-13 | 2025-07-17 | 49
C-56-G-HT-PI-1410 | NDT & Coating for Field Joint Weld | 28 | 28 | 2025-06-11 | 2025-07-15 | 2025-06-17 | 2025-07-21 | 49
HydrotestingCCOHBPI392 |  | 8 | 8 | 2025-07-15 | 2025-07-24 | 2025-07-21 | 2025-07-30 | 49
C-56-G-HT-PI-1600 | Hydrotesting | 8 | 8 | 2025-07-15 | 2025-07-24 | 2025-07-21 | 2025-07-30 | 49
Installation of ValvesCCOHBPI402 |  | 5 | 5 | 2025-07-24 | 2025-07-30 | 2025-07-30 | 2025-08-05 | 49
C-56-G-HT-PI-1800 | Installation of Valves/GOV/ROV | 5 | 5 | 2025-07-24 | 2025-07-30 | 2025-07-30 | 2025-08-05 | 49
Final Bolt Torquing/ Re-InstatementCCOHBPI412 |  | 6 | 6 | 2025-07-29 | 2025-08-05 | 2025-08-04 | 2025-08-11 | 49
C-56-G-HT-PI-2000 | Final Bolt Torquing/ Re-Instatement | 6 | 6 | 2025-07-29 | 2025-08-05 | 2025-08-04 | 2025-08-11 | 49
Hot Tap Tie-In 607-TP-101 (42"X42") |  | 23 | 23 | 2025-03-24 | 2025-04-24 | 2025-05-03 | 2025-05-30 | 19
Preparation, Marking & UT for Existing Line 42" LineCCOHBHT265 |  | 1 | 1 | 2025-03-24 | 2025-03-25 | 2025-05-03 | 2025-05-03 | 19
C-56-G-HT101-ME-1000 | Preparation, Marking & UT for Existing Line 42" Line | 1 | 1 | 2025-03-24 | 2025-03-25 | 2025-05-03 | 2025-05-03 | 19
Split Tee Welding (42" X 42")CCOHBHT275 |  | 6 | 6 | 2025-03-25 | 2025-04-05 | 2025-05-05 | 2025-05-12 | 19
C-56-G-HT101-ME-1010 | Split Tee Welding (42" X 42") | 6 | 6 | 2025-03-25 | 2025-04-05 | 2025-05-05 | 2025-05-12 | 19
NDT & Testing for Split Tee Weld JointCCOHBHT285 |  | 6 | 6 | 2025-03-27 | 2025-04-07 | 2025-05-06 | 2025-05-13 | 19
C-56-G-HT101-ME-1020 | NDT & Testing for Split Tee Weld Joint | 6 | 6 | 2025-03-27 | 2025-04-07 | 2025-05-06 | 2025-05-13 | 19
Installation of ValvesCCOHBHT295 |  | 1 | 1 | 2025-04-08 | 2025-04-08 | 2025-05-13 | 2025-05-14 | 19
C-56-G-HT101-ME-1030 | Installation of Valves | 1 | 1 | 2025-04-08 | 2025-04-08 | 2025-05-13 | 2025-05-14 | 19
Hot Tapping of Existing 42" LineCCOHBHT305 |  | 12 | 12 | 2025-04-09 | 2025-04-22 | 2025-05-14 | 2025-05-28 | 19
C-56-G-HT101-ME-1040 | Hot Tapping of Existing 42" Line | 12 | 12 | 2025-04-09 | 2025-04-22 | 2025-05-14 | 2025-05-28 | 19
Isolation of Hot Tap JointCCOHBHT315 |  | 2 | 2 | 2025-04-23 | 2025-04-24 | 2025-05-28 | 2025-05-30 | 19
C-56-G-HT101-ME-1050 | Isolation of Hot Tap Joint | 2 | 2 | 2025-04-23 | 2025-04-24 | 2025-05-28 | 2025-05-30 | 19
Hot Tap Tie-In 607-TP-102 (30"X30") |  | 26 | 26 | 2025-05-01 | 2025-05-31 | 2025-06-07 | 2025-07-09 | 19
Preparation, Marking & UT for Existing Line 42" LineCCOHBHT325 |  | 1 | 1 | 2025-05-01 | 2025-05-01 | 2025-06-07 | 2025-06-09 | 19
C-56-G-HT102-ME-1000 | Preparation, Marking & UT for Existing Line 30" Line | 1 | 1 | 2025-05-01 | 2025-05-01 | 2025-06-07 | 2025-06-09 | 19
Split Tee Welding (42" X 30")CCOHBHT335 |  | 7 | 7 | 2025-05-02 | 2025-05-10 | 2025-06-09 | 2025-06-17 | 19
C-56-G-HT102-ME-1010 | Split Tee Welding (30" X 30") | 7 | 7 | 2025-05-02 | 2025-05-10 | 2025-06-09 | 2025-06-17 | 19
NDT & Testing for Split Tee Weld JointCCOHBHT345 |  | 7 | 7 | 2025-05-03 | 2025-05-12 | 2025-06-10 | 2025-06-18 | 19
C-56-G-HT102-ME-1020 | NDT & Testing for Split Tee Weld Joint | 7 | 7 | 2025-05-03 | 2025-05-12 | 2025-06-10 | 2025-06-18 | 19
Installation of ValvesCCOHBHT355 |  | 2 | 2 | 2025-05-12 | 2025-05-14 | 2025-06-18 | 2025-06-20 | 19
C-56-G-HT102-ME-1030 | Installation of Valves | 2 | 2 | 2025-05-12 | 2025-05-14 | 2025-06-18 | 2025-06-20 | 19
Hot Tapping of Existing 30" LineCCOHBHT365 |  | 12 | 12 | 2025-05-15 | 2025-05-29 | 2025-06-21 | 2025-07-07 | 19
C-56-G-HT102-ME-1040 | Hot Tapping of Existing 30" Line | 12 | 12 | 2025-05-15 | 2025-05-29 | 2025-06-21 | 2025-07-07 | 19
Isolation of Hot Tap JointCCOHBHT375 |  | 2 | 2 | 2025-05-29 | 2025-05-31 | 2025-07-07 | 2025-07-09 | 19
C-56-G-HT102-ME-1050 | Isolation of Hot Tap Joint | 2 | 2 | 2025-05-29 | 2025-05-31 | 2025-07-07 | 2025-07-09 | 19
Hot Tap Tie-In 607-TP-103 (42"X42") |  | 25 | 25 | 2025-06-11 | 2025-07-11 | 2025-07-17 | 2025-08-15 | 19
Preparation, Marking & UT for Existing Line 42" LineCCOHBHT385 |  | 1 | 1 | 2025-06-11 | 2025-06-12 | 2025-07-17 | 2025-07-18 | 19
C-56-G-HT103-ME-1000 | Preparation, Marking & UT for Existing Line 42" Line | 1 | 1 | 2025-06-11 | 2025-06-12 | 2025-07-17 | 2025-07-18 | 19
Split Tee Welding (42" X 42")CCOHBHT395 |  | 7 | 7 | 2025-06-12 | 2025-06-20 | 2025-07-18 | 2025-07-26 | 19
C-56-G-HT103-ME-1010 | Split Tee Welding (42" X 42") | 7 | 7 | 2025-06-12 | 2025-06-20 | 2025-07-18 | 2025-07-26 | 19
NDT & Testing for Split Tee Weld JointCCOHBHT405 |  | 7 | 7 | 2025-06-13 | 2025-06-21 | 2025-07-19 | 2025-07-28 | 19
C-56-G-HT103-ME-1020 | NDT & Testing for Split Tee Weld Joint | 7 | 7 | 2025-06-13 | 2025-06-21 | 2025-07-19 | 2025-07-28 | 19
Installation of ValvesCCOHBHT415 |  | 2 | 2 | 2025-06-21 | 2025-06-24 | 2025-07-28 | 2025-07-30 | 19
C-56-G-HT103-ME-1030 | Installation of Valves | 2 | 2 | 2025-06-21 | 2025-06-24 | 2025-07-28 | 2025-07-30 | 19
Hot Tapping of Existing 42" LineCCOHBHT425 |  | 12 | 12 | 2025-06-24 | 2025-07-09 | 2025-07-30 | 2025-08-13 | 19
C-56-G-HT103-ME-1040 | Hot Tapping of Existing 42" Line | 12 | 12 | 2025-06-24 | 2025-07-09 | 2025-07-30 | 2025-08-13 | 19
Isolation of Hot Tap JointCCOHBHT435 |  | 2 | 2 | 2025-07-09 | 2025-07-11 | 2025-08-13 | 2025-08-15 | 19
C-56-G-HT103-ME-1050 | Isolation of Hot Tap Joint | 2 | 2 | 2025-07-09 | 2025-07-11 | 2025-08-13 | 2025-08-15 | 19
Tie-In |  | 10 | 10 | 2025-07-29 | 2025-08-09 | 2025-09-02 | 2025-09-15 | 19
Tie-insCCOHBPI311 |  | 10 | 10 | 2025-07-29 | 2025-08-09 | 2025-09-02 | 2025-09-15 | 19
C-56-G-HT-ME-2000 | Tie-In with 30" Pipeline | 10 | 10 | 2025-07-29 | 2025-08-09 | 2025-09-02 | 2025-09-15 | 19
56" P/L Facility to HGCP 56" P/R (56") |  | 438 | 266 | 2024-03-27 | 2025-09-10 | 27-Mar-24 A | 2025-09-20 | 11
56"x17.9 Km Pipeline from BVS-01 to HGCP |  | 418 | 246 | 2024-03-27 | 2025-07-14 | 27-Mar-24 A | 2025-08-27 | 27
56"x17.9 Km Pipeline from BVS-01 to HGCP at KP-30.5 |  | 418 | 246 | 2024-03-27 | 2025-07-14 | 27-Mar-24 A | 2025-08-27 | 27
Main Pipeline |  | 418 | 246 | 2024-03-27 | 2025-07-14 | 27-Mar-24 A | 2025-08-27 | 27
Surveying from BVS-01 to KP 21.3CCOPL56247.1 |  | 25 | 0 | 2024-03-30 | 2024-05-03 | 30-Mar-24 A | 03-May-24 A
C-56-01HG-PL-CI-1000 | Survey Marking | 25 | 0 | 2024-03-30 | 2024-05-03 | 30-Mar-24 A | 03-May-24 A
Surveying from KP 21.3 to HGCPCCOPL56247.2 |  | 25 | 0 | 2024-05-03 | 2024-06-01 | 03-May-24 A | 01-Jun-24 A
C-56-01HG-PL-CI-1200 | Survey Marking | 25 | 0 | 2024-05-03 | 2024-06-01 | 03-May-24 A | 01-Jun-24 A
Cut & Fill from BVS-01 to KP 21.3CCOPL56248.1 |  | 41 | 8 | 2024-09-17 | 2024-10-16 | 18-Sep-24 A | 2024-11-04 | 114
C-56-01HG-PL-CI-1400 | Cut & Fill (@ Non-Sabkha) | 41 | 8 | 2024-09-17 | 2024-10-16 | 18-Sep-24 A | 2024-11-04 | 114
Cut & Fill from KP 21.3 to HGCPCCOPL56248.2 |  | 7 | 0 | 2024-07-29 | 2024-08-27 | 29-Jul-24 A | 26-Sep-24 A
C-56-01HG-PL-CI-1600 | Cut & Fill (@ Non-Sabkha) | 18 | 0 | 2024-07-29 | 2024-08-27 | 29-Jul-24 A | 26-Sep-24 A
ROW Access RoadCCOPL56249 |  | 144 | 0 | 2024-03-27 | 2024-08-22 | 27-Mar-24 A | 24-Sep-24 A
C-56-01HG-PL-CI-1800 | Non-Sabka ROW/Grading | 144 | 0 | 2024-03-27 | 2024-08-22 | 27-Mar-24 A | 24-Sep-24 A
Sabkha Pad- Gatch LayingCCOPL56241.1 |  | 204 | 32 | 2024-03-27 | 2024-10-18 | 27-Mar-24 A | 2024-12-04 | 25
C-56-01HG-PL-CI-2000 | Sabka Gatch Laying (Including ROW) - Layer 1 | 186 | 14 | 2024-03-27 | 2024-09-27 | 27-Mar-24 A | 2024-11-11 | 25
C-56-01HG-PL-CI-2010 | Sabka Gatch Laying - Layer 2 | 175 | 16 | 2024-04-23 | 2024-10-04 | 23-Apr-24 A | 2024-11-18 | 25
C-56-01HG-PL-CI-2020 | Sabka Gatch Laying - Layer 3 | 168 | 18 | 2024-05-08 | 2024-10-11 | 08-May-24 A | 2024-11-25 | 25
C-56-01HG-PL-CI-2030 | Sabka Gatch Laying - Layer 4 | 164 | 20 | 2024-05-20 | 2024-10-18 | 20-May-24 A | 2024-12-04 | 25
Sabkha Pad- Gatch CompactionCCOPL56241.3 |  | 184 | 33 | 2024-04-30 | 2024-10-22 | 30-Apr-24 A | 2024-12-07 | 25
C-56-01HG-PL-CI-2200 | Sabka Gatch Compaction (Including ROW) - Layer 1 | 144 | 15 | 2024-05-25 | 2024-10-01 | 25-May-24 A | 2024-11-14 | 25
C-56-01HG-PL-CI-2210 | Sabka Gatch Compaction - Layer 2 | 172 | 17 | 2024-04-30 | 2024-10-08 | 30-Apr-24 A | 2024-11-21 | 25
C-56-01HG-PL-CI-2220 | Sabka Gatch Compaction - Layer 3 | 162 | 19 | 2024-05-18 | 2024-10-15 | 18-May-24 A | 2024-11-28 | 25
C-56-01HG-PL-CI-2230 | Sabka Gatch Compaction - Layer 4 | 164 | 21 | 2024-05-23 | 2024-10-22 | 23-May-24 A | 2024-12-07 | 25
Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 |  | 23 | 23 | 2024-12-10 | 2025-01-06 | 2025-02-13 | 2025-03-14 | 48
C-56-01HG-PL-CI-2400 | Trench Excavation | 20 | 20 | 2024-12-10 | 2025-01-02 | 2025-02-13 | 2025-03-09 | 23
C-56-01HG-PL-CI-2410 | Bedding | 20 | 20 | 2024-12-13 | 2025-01-06 | 2025-02-17 | 2025-03-14 | 48
Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 |  | 23 | 23 | 2025-01-10 | 2025-02-05 | 2025-01-15 | 2025-02-11 | 73
C-56-01HG-PL-CI-2600 | Trench Excavation | 20 | 20 | 2025-01-10 | 2025-02-01 | 2025-01-15 | 2025-02-07 | 73
C-56-01HG-PL-CI-2610 | Bedding | 20 | 20 | 2025-01-14 | 2025-02-05 | 2025-01-18 | 2025-02-11 | 73
Pipe Stringing from BVS-01 to KP 21.3CCOPL56250.1 |  | 42 | 42 | 2024-11-25 | 2024-12-19 | 2025-01-11 | 2025-02-28 | 17
C-56-01HG-PL-ME-2800 | Stringing (BVS-01 to KP 21.3) | 42 | 42 | 2024-11-25 | 2024-12-19 | 2025-01-11 | 2025-02-28 | 17
Pipe Stringing from KP 21.3 to HGCPCCOPL56250.2 |  | 20 | 20 | 2024-12-20 | 2025-01-13 | 2024-12-18 | 2025-01-10 | 17
C-56-01HG-PL-ME-3000 | Stringing (KP 21.3 to HGCP) | 20 | 20 | 2024-12-20 | 2025-01-13 | 2024-12-18 | 2025-01-10 | 17
Automatic Welding from BVS-01 to KP 21.3CCOPL56256.1 |  | 25 | 25 | 2024-11-28 | 2024-12-28 | 2025-02-04 | 2025-03-05 | 19
C-56-01HG-PL-ME-3600 | Automatic Welding | 25 | 25 | 2024-11-28 | 2024-12-28 | 2025-02-04 | 2025-03-05 | 19
Automatic Welding from KP 21.3 to HGCPCCOPL56256.2 |  | 21 | 21 | 2024-12-31 | 2025-01-29 | 2025-01-10 | 2025-02-04 | 19
C-56-01HG-PL-ME-3800 | Automatic Welding | 21 | 21 | 2024-12-31 | 2025-01-29 | 2025-01-10 | 2025-02-04 | 19
NDT Test from BVS-01 to KP 21.3CCOPL56245.1 |  | 25 | 25 | 2024-11-29 | 2024-12-30 | 2025-02-05 | 2025-03-07 | 33
C-56-01HG-PL-ME-4000 | NDT | 25 | 25 | 2024-11-29 | 2024-12-30 | 2025-02-05 | 2025-03-07 | 33
NDT Test from KP 21.3 to HGCPCCOPL56245.2 |  | 25 | 25 | 2025-01-02 | 2025-01-30 | 2025-03-07 | 2025-04-14 | 53
C-56-01HG-PL-ME-4200 | NDT | 25 | 25 | 2025-01-02 | 2025-01-30 | 2025-03-07 | 2025-04-14 | 53
Ext. Joint Coating from BVS-01 to KP 21.3CCOPL56258.1 |  | 59 | 59 | 2024-12-04 | 2025-02-13 | 2025-02-07 | 2025-04-26 | 26
C-56-01HG-PL-ME-4400 | Ext. Joint Coating | 25 | 25 | 2024-12-04 | 2025-01-02 | 2025-02-07 | 2025-03-09 | 33
C-56-01HG-PL-ME-4410 | Ext. Joint Coating (Tie-in Joint) | 40 | 40 | 2024-12-28 | 2025-02-13 | 2025-03-01 | 2025-04-26 | 26
Ext. Joint Coating from KP 21.3 to HGCPCCOPL56258.2 |  | 81 | 81 | 2025-01-04 | 2025-04-25 | 2025-03-09 | 2025-06-24 | 29
C-56-01HG-PL-ME-4600 | Ext. Joint Coating | 25 | 25 | 2025-01-04 | 2025-02-01 | 2025-03-09 | 2025-04-16 | 53
C-56-01HG-PL-ME-4610 | Ext. Joint Coating (Tie-in Joint) | 45 | 45 | 2025-02-22 | 2025-04-25 | 2025-04-29 | 2025-06-24 | 29
Cold Bends from BVS-01 to KP 21.3CCOPL56255.1 |  | 45 | 45 | 2024-12-20 | 2025-02-11 | 2025-02-11 | 2025-04-14 | 35
C-56-01HG-PL-ME-3200 | Cold Bends | 45 | 45 | 2024-12-20 | 2025-02-11 | 2025-02-11 | 2025-04-14 | 35
Cold Bends from KP 21.3 to HGCPCCOPL56255.2 |  | 45 | 45 | 2025-02-18 | 2025-04-21 | 2025-04-19 | 2025-06-14 | 33
C-56-01HG-PL-ME-3400 | Cold Bends | 45 | 45 | 2025-02-18 | 2025-04-21 | 2025-04-19 | 2025-06-14 | 33
Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 |  | 62 | 62 | 2024-12-20 | 2025-02-20 | 2025-02-11 | 2025-05-03 | 26
C-56-01HG-PL-ME-4800 | Lowering | 45 | 45 | 2024-12-20 | 2025-02-11 | 2025-02-11 | 2025-04-14 | 33
C-56-01HG-PL-ME-4810 | Section Tie-in Welding | 45 | 45 | 2024-12-20 | 2025-02-11 | 2025-02-21 | 2025-04-24 | 26
C-56-01HG-PL-ME-4820 | NDT (Tie-in Joint) | 45 | 45 | 2024-12-23 | 2025-02-13 | 2025-02-24 | 2025-04-26 | 26
C-56-01HG-PL-ME-4830 | Holiday Testing | 45 | 45 | 2024-12-30 | 2025-02-20 | 2025-03-02 | 2025-05-03 | 26
Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 |  | 62 | 62 | 2025-02-12 | 2025-04-26 | 2025-04-14 | 2025-06-30 | 26
C-56-01HG-PL-ME-5000 | Lowering | 50 | 50 | 2025-02-12 | 2025-04-21 | 2025-04-14 | 2025-06-14 | 33
C-56-01HG-PL-ME-5010 | Section Tie-in Welding | 45 | 45 | 2025-02-18 | 2025-04-21 | 2025-04-24 | 2025-06-19 | 29
C-56-01HG-PL-ME-5020 | NDT (Tie-in Joint) | 45 | 45 | 2025-02-20 | 2025-04-23 | 2025-04-26 | 2025-06-21 | 29
C-56-01HG-PL-ME-5030 | Holiday Testing | 45 | 45 | 2025-02-24 | 2025-04-26 | 2025-05-03 | 2025-06-30 | 26
Crossings - from UG Pipe BVS-01 to KP 21.3CCOPL56252.1 |  | 30 | 30 | 2024-12-20 | 2025-01-24 | 2025-03-01 | 2025-04-15 | 52
Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) |  | 18 | 18 | 2024-12-20 | 2025-01-10 | 2025-03-01 | 2025-03-28 | 64
C-56-01HG-CMA01-1000 | Trench Excavation | 12 | 12 | 2024-12-20 | 2025-01-03 | 2025-03-01 | 2025-03-18 | 24
C-56-01HG-CMA01-1010 | Bedding | 1 | 1 | 2025-01-03 | 2025-01-03 | 2025-03-17 | 2025-03-18 | 49
C-56-01HG-CMA01-1020 | Lowering | 1 | 1 | 2025-01-04 | 2025-01-04 | 2025-03-19 | 2025-03-20 | 49
C-56-01HG-CMA01-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-04 | 2025-01-06 | 2025-03-19 | 2025-03-22 | 49
C-56-01HG-CMA01-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-06 | 2025-01-07 | 2025-03-20 | 2025-03-23 | 64
C-56-01HG-CMA01-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-07 | 2025-01-08 | 2025-03-22 | 2025-03-24 | 64
C-56-01HG-CMA01-1060 | Holiday Testing | 1 | 1 | 2025-01-09 | 2025-01-09 | 2025-03-25 | 2025-03-26 | 64
C-56-01HG-CMA01-1070 | Padding | 1 | 1 | 2025-01-10 | 2025-01-10 | 2025-03-26 | 2025-03-28 | 64
Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) |  | 14 | 14 | 2024-12-24 | 2025-01-09 | 2025-03-05 | 2025-03-26 | 65
C-56-01HG-CMA02-1000 | Trench Excavation | 8 | 8 | 2024-12-24 | 2025-01-02 | 2025-03-05 | 2025-03-17 | 24
C-56-01HG-CMA02-1010 | Bedding | 1 | 1 | 2025-01-02 | 2025-01-02 | 2025-03-15 | 2025-03-17 | 50
C-56-01HG-CMA02-1020 | Lowering | 1 | 1 | 2025-01-03 | 2025-01-03 | 2025-03-17 | 2025-03-18 | 50
C-56-01HG-CMA02-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-03 | 2025-01-04 | 2025-03-17 | 2025-03-20 | 50
C-56-01HG-CMA02-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-04 | 2025-01-06 | 2025-03-19 | 2025-03-22 | 65
C-56-01HG-CMA02-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-06 | 2025-01-07 | 2025-03-20 | 2025-03-23 | 65
C-56-01HG-CMA02-1060 | Holiday Testing | 1 | 1 | 2025-01-08 | 2025-01-08 | 2025-03-23 | 2025-03-24 | 65
C-56-01HG-CMA02-1070 | Padding | 1 | 1 | 2025-01-09 | 2025-01-09 | 2025-03-25 | 2025-03-26 | 65
Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) |  | 13 | 13 | 2025-01-10 | 2025-01-24 | 2025-03-26 | 2025-04-15 | 52
C-56-01HG-CMA05-1000 | Trench Excavation | 7 | 7 | 2025-01-10 | 2025-01-17 | 2025-03-26 | 2025-04-08 | 24
C-56-01HG-CMA05-1010 | Bedding | 1 | 1 | 2025-01-17 | 2025-01-17 | 2025-04-07 | 2025-04-08 | 37
C-56-01HG-CMA05-1020 | Lowering | 1 | 1 | 2025-01-18 | 2025-01-18 | 2025-04-08 | 2025-04-09 | 37
C-56-01HG-CMA05-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-18 | 2025-01-20 | 2025-04-08 | 2025-04-10 | 37
C-56-01HG-CMA05-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-20 | 2025-01-21 | 2025-04-09 | 2025-04-11 | 52
C-56-01HG-CMA05-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-21 | 2025-01-22 | 2025-04-10 | 2025-04-12 | 52
C-56-01HG-CMA05-1060 | Holiday Testing | 1 | 1 | 2025-01-23 | 2025-01-23 | 2025-04-12 | 2025-04-14 | 52
C-56-01HG-CMA05-1070 | Padding | 1 | 1 | 2025-01-24 | 2025-01-24 | 2025-04-14 | 2025-04-15 | 52
Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) |  | 14 | 14 | 2024-12-24 | 2025-01-09 | 2025-03-05 | 2025-03-26 | 65
C-56-01HG-CMA03-1000 | Trench Excavation | 8 | 8 | 2024-12-24 | 2025-01-02 | 2025-03-05 | 2025-03-17 | 24
C-56-01HG-CMA03-1010 | Bedding | 1 | 1 | 2025-01-02 | 2025-01-02 | 2025-03-15 | 2025-03-17 | 50
C-56-01HG-CMA03-1020 | Lowering | 1 | 1 | 2025-01-03 | 2025-01-03 | 2025-03-17 | 2025-03-18 | 50
C-56-01HG-CMA03-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-03 | 2025-01-04 | 2025-03-17 | 2025-03-20 | 50
C-56-01HG-CMA03-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-04 | 2025-01-06 | 2025-03-19 | 2025-03-22 | 65
C-56-01HG-CMA03-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-06 | 2025-01-07 | 2025-03-20 | 2025-03-23 | 65
C-56-01HG-CMA03-1060 | Holiday Testing | 1 | 1 | 2025-01-08 | 2025-01-08 | 2025-03-23 | 2025-03-24 | 65
C-56-01HG-CMA03-1070 | Padding | 1 | 1 | 2025-01-09 | 2025-01-09 | 2025-03-25 | 2025-03-26 | 65
Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) |  | 12 | 12 | 2025-01-03 | 2025-01-16 | 2025-03-17 | 2025-04-07 | 59
C-56-01HG-CMA04-1000 | Trench Excavation | 6 | 6 | 2025-01-03 | 2025-01-09 | 2025-03-17 | 2025-03-26 | 24
C-56-01HG-CMA04-1010 | Bedding | 1 | 1 | 2025-01-09 | 2025-01-09 | 2025-03-25 | 2025-03-26 | 44
C-56-01HG-CMA04-1020 | Lowering | 1 | 1 | 2025-01-10 | 2025-01-10 | 2025-03-26 | 2025-03-28 | 44
C-56-01HG-CMA04-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-10 | 2025-01-11 | 2025-03-26 | 2025-03-29 | 44
C-56-01HG-CMA04-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-11 | 2025-01-13 | 2025-03-28 | 2025-04-03 | 59
C-56-01HG-CMA04-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-13 | 2025-01-14 | 2025-03-29 | 2025-04-04 | 59
C-56-01HG-CMA04-1060 | Holiday Testing | 1 | 1 | 2025-01-15 | 2025-01-15 | 2025-04-04 | 2025-04-05 | 59
C-56-01HG-CMA04-1070 | Padding | 1 | 1 | 2025-01-16 | 2025-01-16 | 2025-04-05 | 2025-04-07 | 59
Crossings - UG CableCCOPL56230 |  | 32 | 32 | 2024-12-24 | 2025-01-30 | 2025-03-05 | 2025-04-21 | 47
Crossing Manual @ KP 20+737 (CX-19) |  | 18 | 18 | 2024-12-30 | 2025-01-20 | 2025-03-13 | 2025-04-10 | 56
C-56-01HG-CMA06-1000 | Trench Excavation | 12 | 12 | 2024-12-30 | 2025-01-13 | 2025-03-13 | 2025-04-03 | 28
C-56-01HG-CMA06-1010 | Bedding | 1 | 1 | 2025-01-13 | 2025-01-13 | 2025-03-29 | 2025-04-03 | 41
C-56-01HG-CMA06-1020 | Lowering | 1 | 1 | 2025-01-14 | 2025-01-14 | 2025-04-03 | 2025-04-04 | 41
C-56-01HG-CMA06-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-14 | 2025-01-15 | 2025-04-03 | 2025-04-05 | 41
C-56-01HG-CMA06-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-15 | 2025-01-16 | 2025-04-04 | 2025-04-07 | 56
C-56-01HG-CMA06-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-16 | 2025-01-17 | 2025-04-05 | 2025-04-08 | 56
C-56-01HG-CMA06-1060 | Holiday Testing | 1 | 1 | 2025-01-18 | 2025-01-18 | 2025-04-08 | 2025-04-09 | 56
C-56-01HG-CMA06-1070 | Padding | 1 | 1 | 2025-01-20 | 2025-01-20 | 2025-04-09 | 2025-04-10 | 56
Crossing Manual @ KP 20+900 (CX-20) |  | 18 | 18 | 2025-01-04 | 2025-01-24 | 2025-03-19 | 2025-04-15 | 52
C-56-01HG-CMA07-1000 | Trench Excavation | 12 | 12 | 2025-01-04 | 2025-01-17 | 2025-03-19 | 2025-04-08 | 28
C-56-01HG-CMA07-1010 | Bedding | 1 | 1 | 2025-01-17 | 2025-01-17 | 2025-04-07 | 2025-04-08 | 37
C-56-01HG-CMA07-1020 | Lowering | 1 | 1 | 2025-01-18 | 2025-01-18 | 2025-04-08 | 2025-04-09 | 37
C-56-01HG-CMA07-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-18 | 2025-01-20 | 2025-04-08 | 2025-04-10 | 37
C-56-01HG-CMA07-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-20 | 2025-01-21 | 2025-04-09 | 2025-04-11 | 52
C-56-01HG-CMA07-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-21 | 2025-01-22 | 2025-04-10 | 2025-04-12 | 52
C-56-01HG-CMA07-1060 | Holiday Testing | 1 | 1 | 2025-01-23 | 2025-01-23 | 2025-04-12 | 2025-04-14 | 52
C-56-01HG-CMA07-1070 | Padding | 1 | 1 | 2025-01-24 | 2025-01-24 | 2025-04-14 | 2025-04-15 | 52
Crossing Manual @ KP 24+826 (CX-21) |  | 18 | 18 | 2025-01-03 | 2025-01-23 | 2025-03-17 | 2025-04-14 | 53
C-56-01HG-CMA08-1000 | Trench Excavation | 12 | 12 | 2025-01-03 | 2025-01-16 | 2025-03-17 | 2025-04-07 | 29
C-56-01HG-CMA08-1010 | Bedding | 1 | 1 | 2025-01-16 | 2025-01-16 | 2025-04-05 | 2025-04-07 | 38
C-56-01HG-CMA08-1020 | Lowering | 1 | 1 | 2025-01-17 | 2025-01-17 | 2025-04-07 | 2025-04-08 | 38
C-56-01HG-CMA08-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-17 | 2025-01-18 | 2025-04-07 | 2025-04-09 | 38
C-56-01HG-CMA08-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-18 | 2025-01-20 | 2025-04-08 | 2025-04-10 | 53
C-56-01HG-CMA08-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-20 | 2025-01-21 | 2025-04-09 | 2025-04-11 | 53
C-56-01HG-CMA08-1060 | Holiday Testing | 1 | 1 | 2025-01-22 | 2025-01-22 | 2025-04-11 | 2025-04-12 | 53
C-56-01HG-CMA08-1070 | Padding | 1 | 1 | 2025-01-23 | 2025-01-23 | 2025-04-12 | 2025-04-14 | 53
Crossing Manual @ KP 26+556 (CX-22) |  | 18 | 18 | 2024-12-24 | 2025-01-14 | 2025-03-05 | 2025-04-04 | 61
C-56-01HG-CMA09-1000 | Trench Excavation | 12 | 12 | 2024-12-24 | 2025-01-07 | 2025-03-05 | 2025-03-23 | 43
C-56-01HG-CMA09-1010 | Bedding | 1 | 1 | 2025-01-07 | 2025-01-07 | 2025-03-22 | 2025-03-23 | 46
C-56-01HG-CMA09-1020 | Lowering | 1 | 1 | 2025-01-08 | 2025-01-08 | 2025-03-23 | 2025-03-24 | 46
C-56-01HG-CMA09-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-08 | 2025-01-09 | 2025-03-23 | 2025-03-26 | 46
C-56-01HG-CMA09-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-09 | 2025-01-10 | 2025-03-25 | 2025-03-28 | 61
C-56-01HG-CMA09-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-10 | 2025-01-11 | 2025-03-26 | 2025-03-29 | 61
C-56-01HG-CMA09-1060 | Holiday Testing | 1 | 1 | 2025-01-13 | 2025-01-13 | 2025-03-29 | 2025-04-03 | 61
C-56-01HG-CMA09-1070 | Padding | 1 | 1 | 2025-01-14 | 2025-01-14 | 2025-04-03 | 2025-04-04 | 61
Crossing Manual @ KP 21+136 (PX-186) |  | 18 | 18 | 2025-01-10 | 2025-01-30 | 2025-03-26 | 2025-04-21 | 47
C-56-01HG-CMA10-1000 | Trench Excavation | 12 | 12 | 2025-01-10 | 2025-01-23 | 2025-03-26 | 2025-04-14 | 32
C-56-01HG-CMA10-1010 | Bedding | 1 | 1 | 2025-01-23 | 2025-01-23 | 2025-04-12 | 2025-04-14 | 32
C-56-01HG-CMA10-1020 | Lowering | 1 | 1 | 2025-01-24 | 2025-01-24 | 2025-04-14 | 2025-04-15 | 32
C-56-01HG-CMA10-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-24 | 2025-01-25 | 2025-04-14 | 2025-04-16 | 32
C-56-01HG-CMA10-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-25 | 2025-01-27 | 2025-04-15 | 2025-04-17 | 47
C-56-01HG-CMA10-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-27 | 2025-01-28 | 2025-04-16 | 2025-04-18 | 47
C-56-01HG-CMA10-1060 | Holiday Testing | 1 | 1 | 2025-01-29 | 2025-01-29 | 2025-04-18 | 2025-04-19 | 47
C-56-01HG-CMA10-1070 | Padding | 1 | 1 | 2025-01-30 | 2025-01-30 | 2025-04-19 | 2025-04-21 | 47
Crossings - AG PipeCCOPL56243 |  | 29 | 29 | 2024-12-31 | 2025-02-03 | 2025-03-14 | 2025-04-24 | 44
Crossing Manual @ KP 20+727 (PX-131) |  | 14 | 14 | 2025-01-18 | 2025-02-03 | 2025-04-08 | 2025-04-24 | 44
C-56-01HG-CMA11-1000 | Trench Excavation | 8 | 8 | 2025-01-18 | 2025-01-27 | 2025-04-08 | 2025-04-17 | 24
C-56-01HG-CMA11-1010 | Bedding | 1 | 1 | 2025-01-27 | 2025-01-27 | 2025-04-16 | 2025-04-17 | 29
C-56-01HG-CMA11-1020 | Lowering | 1 | 1 | 2025-01-28 | 2025-01-28 | 2025-04-17 | 2025-04-18 | 29
C-56-01HG-CMA11-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-28 | 2025-01-29 | 2025-04-17 | 2025-04-19 | 29
C-56-01HG-CMA11-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-29 | 2025-01-30 | 2025-04-18 | 2025-04-21 | 44
C-56-01HG-CMA11-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-30 | 2025-01-31 | 2025-04-19 | 2025-04-22 | 44
C-56-01HG-CMA11-1060 | Holiday Testing | 1 | 1 | 2025-02-01 | 2025-02-01 | 2025-04-22 | 2025-04-23 | 44
C-56-01HG-CMA11-1070 | Padding | 1 | 1 | 2025-02-03 | 2025-02-03 | 2025-04-23 | 2025-04-24 | 44
Crossing Manual @ KP 20+725 (OX-08) |  | 12 | 12 | 2025-01-14 | 2025-01-27 | 2025-04-03 | 2025-04-17 | 50
C-56-01HG-CMA12-1000 | Trench Excavation | 6 | 6 | 2025-01-14 | 2025-01-20 | 2025-04-03 | 2025-04-10 | 28
C-56-01HG-CMA12-1010 | Bedding | 1 | 1 | 2025-01-20 | 2025-01-20 | 2025-04-09 | 2025-04-10 | 35
C-56-01HG-CMA12-1020 | Lowering | 1 | 1 | 2025-01-21 | 2025-01-21 | 2025-04-10 | 2025-04-11 | 35
C-56-01HG-CMA12-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-21 | 2025-01-22 | 2025-04-10 | 2025-04-12 | 35
C-56-01HG-CMA12-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-22 | 2025-01-23 | 2025-04-11 | 2025-04-14 | 50
C-56-01HG-CMA12-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-23 | 2025-01-24 | 2025-04-12 | 2025-04-15 | 50
C-56-01HG-CMA12-1060 | Holiday Testing | 1 | 1 | 2025-01-25 | 2025-01-25 | 2025-04-15 | 2025-04-16 | 50
C-56-01HG-CMA12-1070 | Padding | 1 | 1 | 2025-01-27 | 2025-01-27 | 2025-04-16 | 2025-04-17 | 50
Crossing Manual @ KP 20+662 (PX-130) |  | 14 | 14 | 2025-01-18 | 2025-02-03 | 2025-04-08 | 2025-04-24 | 44
C-56-01HG-CMA13-1000 | Trench Excavation | 8 | 8 | 2025-01-18 | 2025-01-27 | 2025-04-08 | 2025-04-17 | 28
C-56-01HG-CMA13-1010 | Bedding | 1 | 1 | 2025-01-27 | 2025-01-27 | 2025-04-16 | 2025-04-17 | 29
C-56-01HG-CMA13-1020 | Lowering | 1 | 1 | 2025-01-28 | 2025-01-28 | 2025-04-17 | 2025-04-18 | 29
C-56-01HG-CMA13-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-28 | 2025-01-29 | 2025-04-17 | 2025-04-19 | 29
C-56-01HG-CMA13-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-29 | 2025-01-30 | 2025-04-18 | 2025-04-21 | 44
C-56-01HG-CMA13-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-30 | 2025-01-31 | 2025-04-19 | 2025-04-22 | 44
C-56-01HG-CMA13-1060 | Holiday Testing | 1 | 1 | 2025-02-01 | 2025-02-01 | 2025-04-22 | 2025-04-23 | 44
C-56-01HG-CMA13-1070 | Padding | 1 | 1 | 2025-02-03 | 2025-02-03 | 2025-04-23 | 2025-04-24 | 44
Crossing Manual @ KP 20+562 (PX-129) |  | 14 | 14 | 2025-01-17 | 2025-02-01 | 2025-04-07 | 2025-04-23 | 45
C-56-01HG-CMA14-1000 | Trench Excavation | 8 | 8 | 2025-01-17 | 2025-01-25 | 2025-04-07 | 2025-04-16 | 29
C-56-01HG-CMA14-1010 | Bedding | 1 | 1 | 2025-01-25 | 2025-01-25 | 2025-04-15 | 2025-04-16 | 30
C-56-01HG-CMA14-1020 | Lowering | 1 | 1 | 2025-01-27 | 2025-01-27 | 2025-04-16 | 2025-04-17 | 30
C-56-01HG-CMA14-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-27 | 2025-01-28 | 2025-04-16 | 2025-04-18 | 30
C-56-01HG-CMA14-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-28 | 2025-01-29 | 2025-04-17 | 2025-04-19 | 45
C-56-01HG-CMA14-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-29 | 2025-01-30 | 2025-04-18 | 2025-04-21 | 45
C-56-01HG-CMA14-1060 | Holiday Testing | 1 | 1 | 2025-01-31 | 2025-01-31 | 2025-04-21 | 2025-04-22 | 45
C-56-01HG-CMA14-1070 | Padding | 1 | 1 | 2025-02-01 | 2025-02-01 | 2025-04-22 | 2025-04-23 | 45
Crossing Manual @ KP 20+488 (PX-128) |  | 14 | 14 | 2024-12-31 | 2025-01-16 | 2025-03-14 | 2025-04-07 | 59
C-56-01HG-CMA15-1000 | Trench Excavation | 8 | 8 | 2024-12-31 | 2025-01-09 | 2025-03-14 | 2025-03-26 | 43
C-56-01HG-CMA15-1010 | Bedding | 1 | 1 | 2025-01-09 | 2025-01-09 | 2025-03-25 | 2025-03-26 | 59
C-56-01HG-CMA15-1020 | Lowering | 1 | 1 | 2025-01-10 | 2025-01-10 | 2025-03-26 | 2025-03-28 | 59
C-56-01HG-CMA15-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-10 | 2025-01-11 | 2025-03-26 | 2025-03-29 | 59
C-56-01HG-CMA15-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-11 | 2025-01-13 | 2025-03-28 | 2025-04-03 | 59
C-56-01HG-CMA15-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-13 | 2025-01-14 | 2025-03-29 | 2025-04-04 | 59
C-56-01HG-CMA15-1060 | Holiday Testing | 1 | 1 | 2025-01-15 | 2025-01-15 | 2025-04-04 | 2025-04-05 | 59
C-56-01HG-CMA15-1070 | Padding | 1 | 1 | 2025-01-16 | 2025-01-16 | 2025-04-05 | 2025-04-07 | 59
Open Cut - Rig / Track RoadCCOPL56257 |  | 50 | 50 | 2024-12-25 | 2025-02-22 | 2025-03-01 | 2025-05-09 | 32
Crossing Mechanical (TX-22 to TX-24) |  | 19 | 19 | 2024-12-25 | 2025-01-23 | 2025-03-01 | 2025-03-29 | 63
C-56-01HG-CME01-1000 | Trench Excavation | 2 | 2 | 2024-12-25 | 2024-12-27 | 2025-03-01 | 2025-03-03 | 17
C-56-01HG-CME01-1010 | Bedding | 2 | 2 | 2024-12-27 | 2024-12-30 | 2025-03-03 | 2025-03-06 | 54
C-56-01HG-CME01-1020 | Lowering | 2 | 2 | 2025-01-07 | 2025-01-08 | 2025-03-07 | 2025-03-09 | 54
C-56-01HG-CME01-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-09 | 2025-01-11 | 2025-03-09 | 2025-03-14 | 54
C-56-01HG-CME01-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-13 | 2025-01-15 | 2025-03-14 | 2025-03-18 | 63
C-56-01HG-CME01-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-01-16 | 2025-01-18 | 2025-03-19 | 2025-03-23 | 63
C-56-01HG-CME01-1060 | Holiday Testing | 2 | 2 | 2025-01-20 | 2025-01-21 | 2025-03-23 | 2025-03-26 | 63
C-56-01HG-CME01-1070 | Padding & Back Filling | 2 | 2 | 2025-01-22 | 2025-01-23 | 2025-03-26 | 2025-03-29 | 63
Crossing Mechanical (TX-25 to TX-27) |  | 19 | 19 | 2024-12-28 | 2025-01-21 | 2025-03-05 | 2025-04-05 | 60
C-56-01HG-CME02-1000 | Trench Excavation | 2 | 2 | 2024-12-28 | 2024-12-31 | 2025-03-05 | 2025-03-08 | 17
C-56-01HG-CME02-1010 | Bedding | 2 | 2 | 2024-12-31 | 2025-01-03 | 2025-03-08 | 2025-03-11 | 51
C-56-01HG-CME02-1020 | Lowering | 2 | 2 | 2025-01-03 | 2025-01-06 | 2025-03-11 | 2025-03-14 | 51
C-56-01HG-CME02-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-06 | 2025-01-09 | 2025-03-14 | 2025-03-18 | 51
C-56-01HG-CME02-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-09 | 2025-01-13 | 2025-03-19 | 2025-03-23 | 60
C-56-01HG-CME02-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-01-13 | 2025-01-16 | 2025-03-23 | 2025-03-28 | 60
C-56-01HG-CME02-1060 | Holiday Testing | 2 | 2 | 2025-01-16 | 2025-01-18 | 2025-03-28 | 2025-04-03 | 60
C-56-01HG-CME02-1070 | Padding & Back Filling | 2 | 2 | 2025-01-18 | 2025-01-21 | 2025-04-03 | 2025-04-05 | 60
Crossing Mechanical (TX-28 to TX-30) |  | 19 | 19 | 2025-01-02 | 2025-01-24 | 2025-03-09 | 2025-04-09 | 57
C-56-01HG-CME03-1000 | Trench Excavation | 2 | 2 | 2025-01-02 | 2025-01-04 | 2025-03-09 | 2025-03-12 | 17
C-56-01HG-CME03-1010 | Bedding | 2 | 2 | 2025-01-04 | 2025-01-07 | 2025-03-13 | 2025-03-15 | 48
C-56-01HG-CME03-1020 | Lowering | 2 | 2 | 2025-01-07 | 2025-01-09 | 2025-03-15 | 2025-03-18 | 48
C-56-01HG-CME03-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-09 | 2025-01-13 | 2025-03-19 | 2025-03-23 | 48
C-56-01HG-CME03-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-13 | 2025-01-16 | 2025-03-23 | 2025-03-28 | 57
C-56-01HG-CME03-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-01-16 | 2025-01-20 | 2025-03-28 | 2025-04-04 | 57
C-56-01HG-CME03-1060 | Holiday Testing | 2 | 2 | 2025-01-20 | 2025-01-22 | 2025-04-04 | 2025-04-07 | 57
C-56-01HG-CME03-1070 | Padding & Back Filling | 2 | 2 | 2025-01-22 | 2025-01-24 | 2025-04-07 | 2025-04-09 | 57
Crossing Mechanical (TX-31 to TX-33) |  | 19 | 19 | 2025-01-06 | 2025-01-28 | 2025-03-14 | 2025-04-12 | 54
C-56-01HG-CME04-1000 | Trench Excavation | 2 | 2 | 2025-01-06 | 2025-01-08 | 2025-03-14 | 2025-03-17 | 17
C-56-01HG-CME04-1010 | Bedding | 2 | 2 | 2025-01-08 | 2025-01-10 | 2025-03-17 | 2025-03-20 | 45
C-56-01HG-CME04-1020 | Lowering | 2 | 2 | 2025-01-10 | 2025-01-13 | 2025-03-20 | 2025-03-23 | 45
C-56-01HG-CME04-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-13 | 2025-01-16 | 2025-03-23 | 2025-03-28 | 45
C-56-01HG-CME04-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-16 | 2025-01-20 | 2025-03-28 | 2025-04-04 | 54
C-56-01HG-CME04-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-01-20 | 2025-01-23 | 2025-04-04 | 2025-04-08 | 54
C-56-01HG-CME04-1060 | Holiday Testing | 2 | 2 | 2025-01-23 | 2025-01-25 | 2025-04-08 | 2025-04-10 | 54
C-56-01HG-CME04-1070 | Padding & Back Filling | 2 | 2 | 2025-01-25 | 2025-01-28 | 2025-04-10 | 2025-04-12 | 54
Crossing Mechanical (TX-34 to TX-36) |  | 19 | 19 | 2025-01-09 | 2025-01-31 | 2025-03-19 | 2025-04-16 | 51
C-56-01HG-CME05-1000 | Trench Excavation | 2 | 2 | 2025-01-09 | 2025-01-11 | 2025-03-19 | 2025-03-22 | 17
C-56-01HG-CME05-1010 | Bedding | 2 | 2 | 2025-01-11 | 2025-01-14 | 2025-03-22 | 2025-03-24 | 42
C-56-01HG-CME05-1020 | Lowering | 2 | 2 | 2025-01-14 | 2025-01-16 | 2025-03-25 | 2025-03-28 | 42
C-56-01HG-CME05-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-16 | 2025-01-20 | 2025-03-28 | 2025-04-04 | 42
C-56-01HG-CME05-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-20 | 2025-01-23 | 2025-04-04 | 2025-04-08 | 51
C-56-01HG-CME05-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-01-23 | 2025-01-27 | 2025-04-08 | 2025-04-11 | 51
C-56-01HG-CME05-1060 | Holiday Testing | 2 | 2 | 2025-01-27 | 2025-01-29 | 2025-04-11 | 2025-04-14 | 51
C-56-01HG-CME05-1070 | Padding & Back Filling | 2 | 2 | 2025-01-29 | 2025-01-31 | 2025-04-14 | 2025-04-16 | 51
Crossing Mechanical (TX-37 to TX-39) |  | 19 | 19 | 2025-01-13 | 2025-02-04 | 2025-03-23 | 2025-04-19 | 48
C-56-01HG-CME06-1000 | Trench Excavation | 2 | 2 | 2025-01-13 | 2025-01-15 | 2025-03-23 | 2025-03-26 | 17
C-56-01HG-CME06-1010 | Bedding | 2 | 2 | 2025-01-15 | 2025-01-17 | 2025-03-26 | 2025-03-29 | 39
C-56-01HG-CME06-1020 | Lowering | 2 | 2 | 2025-01-17 | 2025-01-20 | 2025-03-29 | 2025-04-04 | 39
C-56-01HG-CME06-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-20 | 2025-01-23 | 2025-04-04 | 2025-04-08 | 39
C-56-01HG-CME06-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-23 | 2025-01-27 | 2025-04-08 | 2025-04-11 | 48
C-56-01HG-CME06-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-01-27 | 2025-01-30 | 2025-04-11 | 2025-04-15 | 48
C-56-01HG-CME06-1060 | Holiday Testing | 2 | 2 | 2025-01-30 | 2025-02-01 | 2025-04-15 | 2025-04-17 | 48
C-56-01HG-CME06-1070 | Padding & Back Filling | 2 | 2 | 2025-02-01 | 2025-02-04 | 2025-04-17 | 2025-04-19 | 48
Crossing Mechanical (TX-40 to TX-42) |  | 19 | 19 | 2025-01-16 | 2025-02-07 | 2025-03-28 | 2025-04-23 | 45
C-56-01HG-CME07-1000 | Trench Excavation | 2 | 2 | 2025-01-16 | 2025-01-18 | 2025-03-28 | 2025-04-03 | 17
C-56-01HG-CME07-1010 | Bedding | 2 | 2 | 2025-01-18 | 2025-01-21 | 2025-04-03 | 2025-04-05 | 36
C-56-01HG-CME07-1020 | Lowering | 2 | 2 | 2025-01-21 | 2025-01-23 | 2025-04-05 | 2025-04-08 | 36
C-56-01HG-CME07-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-23 | 2025-01-27 | 2025-04-08 | 2025-04-11 | 36
C-56-01HG-CME07-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-27 | 2025-01-30 | 2025-04-11 | 2025-04-15 | 45
C-56-01HG-CME07-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-01-30 | 2025-02-03 | 2025-04-15 | 2025-04-18 | 45
C-56-01HG-CME07-1060 | Holiday Testing | 2 | 2 | 2025-02-03 | 2025-02-05 | 2025-04-18 | 2025-04-21 | 45
C-56-01HG-CME07-1070 | Padding & Back Filling | 2 | 2 | 2025-02-05 | 2025-02-07 | 2025-04-21 | 2025-04-23 | 45
Crossing Mechanical (TX-43 to TX-45) |  | 19 | 19 | 2025-01-20 | 2025-02-11 | 2025-04-04 | 2025-04-26 | 42
C-56-01HG-CME08-1000 | Trench Excavation | 2 | 2 | 2025-01-20 | 2025-01-22 | 2025-04-04 | 2025-04-07 | 17
C-56-01HG-CME08-1010 | Bedding | 2 | 2 | 2025-01-22 | 2025-01-24 | 2025-04-07 | 2025-04-09 | 33
C-56-01HG-CME08-1020 | Lowering | 2 | 2 | 2025-01-24 | 2025-01-27 | 2025-04-09 | 2025-04-11 | 33
C-56-01HG-CME08-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-27 | 2025-01-30 | 2025-04-11 | 2025-04-15 | 33
C-56-01HG-CME08-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-30 | 2025-02-03 | 2025-04-15 | 2025-04-18 | 42
C-56-01HG-CME08-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-02-03 | 2025-02-06 | 2025-04-18 | 2025-04-22 | 42
C-56-01HG-CME08-1060 | Holiday Testing | 2 | 2 | 2025-02-06 | 2025-02-08 | 2025-04-22 | 2025-04-24 | 42
C-56-01HG-CME08-1070 | Padding & Back Filling | 2 | 2 | 2025-02-08 | 2025-02-11 | 2025-04-24 | 2025-04-26 | 42
Crossing Mechanical (TX-46,47) |  | 19 | 19 | 2025-01-23 | 2025-02-14 | 2025-04-08 | 2025-04-30 | 39
C-56-01HG-CME09-1000 | Trench Excavation | 2 | 2 | 2025-01-23 | 2025-01-25 | 2025-04-08 | 2025-04-10 | 17
C-56-01HG-CME09-1010 | Bedding | 2 | 2 | 2025-01-25 | 2025-01-28 | 2025-04-10 | 2025-04-12 | 30
C-56-01HG-CME09-1020 | Lowering | 2 | 2 | 2025-01-28 | 2025-01-30 | 2025-04-12 | 2025-04-15 | 30
C-56-01HG-CME09-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-30 | 2025-02-03 | 2025-04-15 | 2025-04-18 | 30
C-56-01HG-CME09-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-02-03 | 2025-02-06 | 2025-04-18 | 2025-04-22 | 39
C-56-01HG-CME09-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-02-06 | 2025-02-10 | 2025-04-22 | 2025-04-25 | 39
C-56-01HG-CME09-1060 | Holiday Testing | 2 | 2 | 2025-02-10 | 2025-02-12 | 2025-04-25 | 2025-04-28 | 39
C-56-01HG-CME09-1070 | Padding & Back Filling | 2 | 2 | 2025-02-12 | 2025-02-14 | 2025-04-28 | 2025-04-30 | 39
Crossing Mechanical (TX-48) |  | 23 | 23 | 2025-01-27 | 2025-02-22 | 2025-04-11 | 2025-05-09 | 30
C-56-01HG-CME10-1000 | Trench Excavation | 3 | 3 | 2025-01-27 | 2025-01-30 | 2025-04-11 | 2025-04-15 | 17
C-56-01HG-CME10-1010 | Bedding | 2 | 2 | 2025-01-30 | 2025-02-01 | 2025-04-15 | 2025-04-17 | 26
C-56-01HG-CME10-1020 | Lowering | 2 | 2 | 2025-02-01 | 2025-02-04 | 2025-04-17 | 2025-04-19 | 26
C-56-01HG-CME10-1030 | Section Tie-in Welding | 4 | 4 | 2025-02-04 | 2025-02-08 | 2025-04-19 | 2025-04-24 | 26
C-56-01HG-CME10-1040 | NDT (Tie-in Joint) | 4 | 4 | 2025-02-08 | 2025-02-13 | 2025-04-24 | 2025-04-29 | 30
C-56-01HG-CME10-1050 | Ext. Joint Coating (Tie-in Joint) | 4 | 4 | 2025-02-13 | 2025-02-18 | 2025-04-29 | 2025-05-03 | 30
C-56-01HG-CME10-1060 | Holiday Testing | 2 | 2 | 2025-02-18 | 2025-02-20 | 2025-05-03 | 2025-05-06 | 30
C-56-01HG-CME10-1070 | Padding & Back Filling | 2 | 2 | 2025-02-20 | 2025-02-22 | 2025-05-07 | 2025-05-09 | 30
Crossings - UG Pipe from KP 21.3 to HGCPCCOPL56252.2 |  | 25 | 25 | 2025-01-21 | 2025-02-18 | 2025-04-10 | 2025-05-10 | 31
Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) |  | 14 | 14 | 2025-01-24 | 2025-02-08 | 2025-04-14 | 2025-04-30 | 39
C-56-01HG-CMA16-1000 | Trench Excavation | 8 | 8 | 2025-01-24 | 2025-02-01 | 2025-04-14 | 2025-04-23 | 33
C-56-01HG-CMA16-1010 | Bedding | 1 | 1 | 2025-02-01 | 2025-02-01 | 2025-04-22 | 2025-04-23 | 39
C-56-01HG-CMA16-1020 | Lowering | 1 | 1 | 2025-02-03 | 2025-02-03 | 2025-04-23 | 2025-04-24 | 39
C-56-01HG-CMA16-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-03 | 2025-02-04 | 2025-04-23 | 2025-04-25 | 39
C-56-01HG-CMA16-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-04 | 2025-02-05 | 2025-04-24 | 2025-04-26 | 39
C-56-01HG-CMA16-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-05 | 2025-02-06 | 2025-04-25 | 2025-04-28 | 39
C-56-01HG-CMA16-1060 | Holiday Testing | 1 | 1 | 2025-02-07 | 2025-02-07 | 2025-04-28 | 2025-04-29 | 39
C-56-01HG-CMA16-1070 | Padding | 1 | 1 | 2025-02-08 | 2025-02-08 | 2025-04-29 | 2025-04-30 | 39
Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) |  | 19 | 19 | 2025-01-28 | 2025-02-18 | 2025-04-17 | 2025-05-10 | 31
C-56-01HG-CMA17-1000 | Trench Excavation | 12 | 12 | 2025-01-28 | 2025-02-10 | 2025-04-17 | 2025-05-01 | 24
C-56-01HG-CMA17-1010 | Bedding | 1 | 1 | 2025-02-10 | 2025-02-10 | 2025-04-30 | 2025-05-01 | 31
C-56-01HG-CMA17-1020 | Lowering | 1 | 1 | 2025-02-11 | 2025-02-11 | 2025-05-01 | 2025-05-02 | 31
C-56-01HG-CMA17-1030 | Section Tie-in Welding | 3 | 3 | 2025-02-11 | 2025-02-13 | 2025-05-01 | 2025-05-05 | 31
C-56-01HG-CMA17-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-02-12 | 2025-02-14 | 2025-05-02 | 2025-05-06 | 31
C-56-01HG-CMA17-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-02-13 | 2025-02-15 | 2025-05-03 | 2025-05-08 | 31
C-56-01HG-CMA17-1060 | Holiday Testing | 1 | 1 | 2025-02-17 | 2025-02-17 | 2025-05-08 | 2025-05-09 | 31
C-56-01HG-CMA17-1070 | Padding | 1 | 1 | 2025-02-18 | 2025-02-18 | 2025-05-09 | 2025-05-10 | 31
Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) |  | 14 | 14 | 2025-01-21 | 2025-02-05 | 2025-04-10 | 2025-04-26 | 42
C-56-01HG-CMA18-1000 | Trench Excavation | 8 | 8 | 2025-01-21 | 2025-01-29 | 2025-04-10 | 2025-04-19 | 28
C-56-01HG-CMA18-1010 | Bedding | 1 | 1 | 2025-01-29 | 2025-01-29 | 2025-04-18 | 2025-04-19 | 42
C-56-01HG-CMA18-1020 | Lowering | 1 | 1 | 2025-01-30 | 2025-01-30 | 2025-04-19 | 2025-04-21 | 42
C-56-01HG-CMA18-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-30 | 2025-01-31 | 2025-04-19 | 2025-04-22 | 42
C-56-01HG-CMA18-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-31 | 2025-02-01 | 2025-04-21 | 2025-04-23 | 42
C-56-01HG-CMA18-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-01 | 2025-02-03 | 2025-04-22 | 2025-04-24 | 42
C-56-01HG-CMA18-1060 | Holiday Testing | 1 | 1 | 2025-02-04 | 2025-02-04 | 2025-04-24 | 2025-04-25 | 42
C-56-01HG-CMA18-1070 | Padding | 1 | 1 | 2025-02-05 | 2025-02-05 | 2025-04-25 | 2025-04-26 | 42
Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) |  | 14 | 14 | 2025-01-28 | 2025-02-12 | 2025-04-17 | 2025-05-03 | 36
C-56-01HG-CMA19-1000 | Trench Excavation | 8 | 8 | 2025-01-28 | 2025-02-05 | 2025-04-17 | 2025-04-26 | 28
C-56-01HG-CMA19-1010 | Bedding | 1 | 1 | 2025-02-05 | 2025-02-05 | 2025-04-25 | 2025-04-26 | 36
C-56-01HG-CMA19-1020 | Lowering | 1 | 1 | 2025-02-06 | 2025-02-06 | 2025-04-26 | 2025-04-28 | 36
C-56-01HG-CMA19-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-06 | 2025-02-07 | 2025-04-26 | 2025-04-29 | 36
C-56-01HG-CMA19-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-07 | 2025-02-08 | 2025-04-28 | 2025-04-30 | 36
C-56-01HG-CMA19-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-08 | 2025-02-10 | 2025-04-29 | 2025-05-01 | 36
C-56-01HG-CMA19-1060 | Holiday Testing | 1 | 1 | 2025-02-11 | 2025-02-11 | 2025-05-01 | 2025-05-02 | 36
C-56-01HG-CMA19-1070 | Padding | 1 | 1 | 2025-02-12 | 2025-02-12 | 2025-05-02 | 2025-05-03 | 36
Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) |  | 14 | 14 | 2025-01-27 | 2025-02-11 | 2025-04-16 | 2025-05-02 | 37
C-56-01HG-CMA20-1000 | Trench Excavation | 8 | 8 | 2025-01-27 | 2025-02-04 | 2025-04-16 | 2025-04-25 | 29
C-56-01HG-CMA20-1010 | Bedding | 1 | 1 | 2025-02-04 | 2025-02-04 | 2025-04-24 | 2025-04-25 | 37
C-56-01HG-CMA20-1020 | Lowering | 1 | 1 | 2025-02-05 | 2025-02-05 | 2025-04-25 | 2025-04-26 | 37
C-56-01HG-CMA20-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-05 | 2025-02-06 | 2025-04-25 | 2025-04-28 | 37
C-56-01HG-CMA20-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-06 | 2025-02-07 | 2025-04-26 | 2025-04-29 | 37
C-56-01HG-CMA20-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-07 | 2025-02-08 | 2025-04-28 | 2025-04-30 | 37
C-56-01HG-CMA20-1060 | Holiday Testing | 1 | 1 | 2025-02-10 | 2025-02-10 | 2025-04-30 | 2025-05-01 | 37
C-56-01HG-CMA20-1070 | Padding | 1 | 1 | 2025-02-11 | 2025-02-11 | 2025-05-01 | 2025-05-02 | 37
Crossings OHPLCCOPL56246 |  | 32 | 32 | 2025-01-10 | 2025-02-15 | 2025-03-26 | 2025-05-08 | 33
Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) |  | 14 | 14 | 2025-01-10 | 2025-01-25 | 2025-03-26 | 2025-04-16 | 51
C-56-01HG-CMA21-1000 | Trench Excavation | 8 | 8 | 2025-01-10 | 2025-01-18 | 2025-03-26 | 2025-04-09 | 43
C-56-01HG-CMA21-1010 | Bedding | 1 | 1 | 2025-01-18 | 2025-01-18 | 2025-04-08 | 2025-04-09 | 51
C-56-01HG-CMA21-1020 | Lowering | 1 | 1 | 2025-01-20 | 2025-01-20 | 2025-04-09 | 2025-04-10 | 51
C-56-01HG-CMA21-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-20 | 2025-01-21 | 2025-04-09 | 2025-04-11 | 51
C-56-01HG-CMA21-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-21 | 2025-01-22 | 2025-04-10 | 2025-04-12 | 51
C-56-01HG-CMA21-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-22 | 2025-01-23 | 2025-04-11 | 2025-04-14 | 51
C-56-01HG-CMA21-1060 | Holiday Testing | 1 | 1 | 2025-01-24 | 2025-01-24 | 2025-04-14 | 2025-04-15 | 51
C-56-01HG-CMA21-1070 | Padding | 1 | 1 | 2025-01-25 | 2025-01-25 | 2025-04-15 | 2025-04-16 | 51
Crossing Manual @ KP 27+219 (OX-09) |  | 12 | 12 | 2025-02-03 | 2025-02-15 | 2025-04-23 | 2025-05-08 | 33
C-56-01HG-CMA22-1000 | Trench Excavation | 6 | 6 | 2025-02-03 | 2025-02-08 | 2025-04-23 | 2025-04-30 | 33
C-56-01HG-CMA22-1010 | Bedding | 1 | 1 | 2025-02-08 | 2025-02-08 | 2025-04-29 | 2025-04-30 | 33
C-56-01HG-CMA22-1020 | Lowering | 1 | 1 | 2025-02-10 | 2025-02-10 | 2025-04-30 | 2025-05-01 | 33
C-56-01HG-CMA22-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-10 | 2025-02-11 | 2025-04-30 | 2025-05-02 | 33
C-56-01HG-CMA22-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-11 | 2025-02-12 | 2025-05-01 | 2025-05-03 | 33
C-56-01HG-CMA22-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-12 | 2025-02-13 | 2025-05-02 | 2025-05-05 | 33
C-56-01HG-CMA22-1060 | Holiday Testing | 1 | 1 | 2025-02-14 | 2025-02-14 | 2025-05-05 | 2025-05-06 | 33
C-56-01HG-CMA22-1070 | Padding | 1 | 1 | 2025-02-15 | 2025-02-15 | 2025-05-07 | 2025-05-08 | 33
Crossings - FenceCCOPL56253 |  | 33 | 33 | 2025-01-20 | 2025-02-26 | 2025-04-09 | 2025-05-19 | 24
Crossing Manual @ KP 26+558 (FX-03) |  | 14 | 14 | 2025-02-11 | 2025-02-26 | 2025-05-01 | 2025-05-19 | 24
C-56-01HG-CMA23-1000 | Trench Excavation | 8 | 8 | 2025-02-11 | 2025-02-19 | 2025-05-01 | 2025-05-12 | 24
C-56-01HG-CMA23-1010 | Bedding | 1 | 1 | 2025-02-19 | 2025-02-19 | 2025-05-10 | 2025-05-12 | 24
C-56-01HG-CMA23-1020 | Lowering | 1 | 1 | 2025-02-20 | 2025-02-20 | 2025-05-12 | 2025-05-13 | 24
C-56-01HG-CMA23-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-20 | 2025-02-21 | 2025-05-12 | 2025-05-14 | 24
C-56-01HG-CMA23-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-21 | 2025-02-22 | 2025-05-13 | 2025-05-15 | 24
C-56-01HG-CMA23-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-22 | 2025-02-24 | 2025-05-14 | 2025-05-16 | 24
C-56-01HG-CMA23-1060 | Holiday Testing | 1 | 1 | 2025-02-25 | 2025-02-25 | 2025-05-16 | 2025-05-17 | 24
C-56-01HG-CMA23-1070 | Padding | 1 | 1 | 2025-02-26 | 2025-02-26 | 2025-05-17 | 2025-05-19 | 24
Crossing Manual @ KP 20+229 (PX-162) |  | 20 | 20 | 2025-01-30 | 2025-02-21 | 2025-04-19 | 2025-05-14 | 28
C-56-01HG-CMA24-1000 | Trench Excavation | 12 | 12 | 2025-01-30 | 2025-02-12 | 2025-04-19 | 2025-05-03 | 28
C-56-01HG-CMA24-1010 | Bedding | 2 | 2 | 2025-02-11 | 2025-02-12 | 2025-05-01 | 2025-05-03 | 28
C-56-01HG-CMA24-1020 | Lowering | 1 | 1 | 2025-02-13 | 2025-02-13 | 2025-05-03 | 2025-05-05 | 28
C-56-01HG-CMA24-1030 | Section Tie-in Welding | 4 | 4 | 2025-02-13 | 2025-02-17 | 2025-05-03 | 2025-05-09 | 28
C-56-01HG-CMA24-1040 | NDT (Tie-in Joint) | 4 | 4 | 2025-02-14 | 2025-02-18 | 2025-05-05 | 2025-05-10 | 28
C-56-01HG-CMA24-1050 | Ext. Joint Coating (Tie-in Joint) | 4 | 4 | 2025-02-15 | 2025-02-19 | 2025-05-07 | 2025-05-12 | 28
C-56-01HG-CMA24-1060 | Holiday Testing | 1 | 1 | 2025-02-20 | 2025-02-20 | 2025-05-12 | 2025-05-13 | 28
C-56-01HG-CMA24-1070 | Padding | 1 | 1 | 2025-02-21 | 2025-02-21 | 2025-05-13 | 2025-05-14 | 28
Crossing Manual @ KP 19+811 (PX-159) |  | 14 | 14 | 2025-02-06 | 2025-02-21 | 2025-04-26 | 2025-05-14 | 28
C-56-01HG-CMA25-1000 | Trench Excavation | 8 | 8 | 2025-02-06 | 2025-02-14 | 2025-04-26 | 2025-05-06 | 28
C-56-01HG-CMA25-1010 | Bedding | 1 | 1 | 2025-02-14 | 2025-02-14 | 2025-05-05 | 2025-05-06 | 28
C-56-01HG-CMA25-1020 | Lowering | 1 | 1 | 2025-02-15 | 2025-02-15 | 2025-05-07 | 2025-05-08 | 28
C-56-01HG-CMA25-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-15 | 2025-02-17 | 2025-05-07 | 2025-05-09 | 28
C-56-01HG-CMA25-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-17 | 2025-02-18 | 2025-05-08 | 2025-05-10 | 28
C-56-01HG-CMA25-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-18 | 2025-02-19 | 2025-05-09 | 2025-05-12 | 28
C-56-01HG-CMA25-1060 | Holiday Testing | 1 | 1 | 2025-02-20 | 2025-02-20 | 2025-05-12 | 2025-05-13 | 28
C-56-01HG-CMA25-1070 | Padding | 1 | 1 | 2025-02-21 | 2025-02-21 | 2025-05-13 | 2025-05-14 | 28
Crossing Manual @ KP 19+202 (PX-157) |  | 14 | 14 | 2025-02-05 | 2025-02-20 | 2025-04-25 | 2025-05-13 | 29
C-56-01HG-CMA26-1000 | Trench Excavation | 8 | 8 | 2025-02-05 | 2025-02-13 | 2025-04-25 | 2025-05-05 | 29
C-56-01HG-CMA26-1010 | Bedding | 1 | 1 | 2025-02-13 | 2025-02-13 | 2025-05-03 | 2025-05-05 | 29
C-56-01HG-CMA26-1020 | Lowering | 1 | 1 | 2025-02-14 | 2025-02-14 | 2025-05-05 | 2025-05-06 | 29
C-56-01HG-CMA26-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-14 | 2025-02-15 | 2025-05-05 | 2025-05-08 | 29
C-56-01HG-CMA26-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-15 | 2025-02-17 | 2025-05-07 | 2025-05-09 | 29
C-56-01HG-CMA26-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-17 | 2025-02-18 | 2025-05-08 | 2025-05-10 | 29
C-56-01HG-CMA26-1060 | Holiday Testing | 1 | 1 | 2025-02-19 | 2025-02-19 | 2025-05-10 | 2025-05-12 | 29
C-56-01HG-CMA26-1070 | Padding | 1 | 1 | 2025-02-20 | 2025-02-20 | 2025-05-12 | 2025-05-13 | 29
Crossing Manual @ KP 18+829 (PX-140) |  | 14 | 14 | 2025-01-20 | 2025-02-04 | 2025-04-09 | 2025-04-25 | 43
C-56-01HG-CMA27-1000 | Trench Excavation | 8 | 8 | 2025-01-20 | 2025-01-28 | 2025-04-09 | 2025-04-18 | 43
C-56-01HG-CMA27-1010 | Bedding | 1 | 1 | 2025-01-28 | 2025-01-28 | 2025-04-17 | 2025-04-18 | 43
C-56-01HG-CMA27-1020 | Lowering | 1 | 1 | 2025-01-29 | 2025-01-29 | 2025-04-18 | 2025-04-19 | 43
C-56-01HG-CMA27-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-29 | 2025-01-30 | 2025-04-18 | 2025-04-21 | 43
C-56-01HG-CMA27-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-30 | 2025-01-31 | 2025-04-19 | 2025-04-22 | 43
C-56-01HG-CMA27-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-31 | 2025-02-01 | 2025-04-21 | 2025-04-23 | 43
C-56-01HG-CMA27-1060 | Holiday Testing | 1 | 1 | 2025-02-03 | 2025-02-03 | 2025-04-23 | 2025-04-24 | 43
C-56-01HG-CMA27-1070 | Padding | 1 | 1 | 2025-02-04 | 2025-02-04 | 2025-04-24 | 2025-04-25 | 43
CP Works from BVS-01 to KP 21.3CCOP56EL23.1 |  | 36 | 36 | 2025-01-10 | 2025-03-12 | 2025-06-11 | 2025-07-24 | 53
C-56-01HG-PL-CA-5220 | Installation of Test Post for Crossing | 30 | 30 | 2025-01-10 | 2025-03-03 | 2025-06-11 | 2025-07-17 | 27
C-56-01HG-PL-CA-5230 | Installation of CP JB's | 30 | 30 | 2025-01-11 | 2025-03-05 | 2025-06-12 | 2025-07-18 | 27
C-56-01HG-PL-CA-5240 | Installation of CP TR | 30 | 30 | 2025-01-13 | 2025-03-06 | 2025-06-13 | 2025-07-19 | 27
C-56-01HG-PL-CA-5250 | CIP/DCVG Survey (Pre-Com) | 4 | 4 | 2025-03-07 | 2025-03-12 | 2025-07-19 | 2025-07-24 | 53
CP Works from KP 21.3 to HGCPCCOP56EL23.2 |  | 35 | 35 | 2025-03-03 | 2025-05-12 | 2025-07-17 | 2025-08-27 | 27
C-56-01HG-PL-CA-5420 | Installation of Test Post for Crossing | 30 | 30 | 2025-03-03 | 2025-05-05 | 2025-07-17 | 2025-08-21 | 27
C-56-01HG-PL-CA-5430 | Installation of CP JB's | 30 | 30 | 2025-03-05 | 2025-05-06 | 2025-07-18 | 2025-08-22 | 27
C-56-01HG-PL-CA-5440 | Installation of CP TR | 30 | 30 | 2025-03-07 | 2025-05-08 | 2025-07-19 | 2025-08-23 | 27
C-56-01HG-PL-CA-5450 | CIP/DCVG Survey (Pre-Com) | 3 | 3 | 2025-05-08 | 2025-05-12 | 2025-08-23 | 2025-08-27 | 27
Test Stations & Anode Beds from BVS-01 to KP 21.3CCOP56EL24.1 |  | 47 | 47 | 2024-12-30 | 2025-02-22 | 2025-03-02 | 2025-05-06 | 114
C-56-01HG-PL-CA-5600 | Installation of Temp. Anode | 45 | 45 | 2024-12-30 | 2025-02-20 | 2025-03-02 | 2025-05-03 | 26
C-56-01HG-PL-CA-5610 | Installation of CP Test Post | 45 | 45 | 2024-12-30 | 2025-02-20 | 2025-03-02 | 2025-05-03 | 73
C-56-01HG-PL-CA-5620 | Glanding & Termination of Temp. CP S/m | 2 | 2 | 2025-02-21 | 2025-02-22 | 2025-05-03 | 2025-05-06 | 114
Test Stations & Anode Beds from KP 21.3 to HGCPCCOP56EL24.2 |  | 47 | 47 | 2025-02-24 | 2025-04-29 | 2025-05-03 | 2025-07-02 | 73
C-56-01HG-PL-CA-5800 | Installation of Temp. Anode | 45 | 45 | 2025-02-24 | 2025-04-26 | 2025-05-03 | 2025-06-30 | 26
C-56-01HG-PL-CA-5810 | Installation of CP Test Post | 45 | 45 | 2025-02-24 | 2025-04-26 | 2025-05-03 | 2025-06-30 | 73
C-56-01HG-PL-CA-5820 | Glanding & Termination of Temp. CP S/m | 2 | 2 | 2025-04-26 | 2025-04-29 | 2025-06-30 | 2025-07-02 | 73
Padding from BVS-01 to KP 21.3CCOPL56251.1 |  | 45 | 45 | 2025-01-08 | 2025-02-28 | 2025-03-13 | 2025-05-13 | 26
C-56-01HG-PL-CI-6000 | Padding | 45 | 45 | 2025-01-08 | 2025-02-28 | 2025-03-13 | 2025-05-13 | 26
Padding from KP 21.3 to HGCPCCOPL56251.2 |  | 45 | 45 | 2025-02-26 | 2025-04-29 | 2025-05-07 | 2025-07-02 | 26
C-56-01HG-PL-CI-6200 | Padding | 45 | 45 | 2025-02-26 | 2025-04-29 | 2025-05-07 | 2025-07-02 | 26
Backfilling from BVS-01 to KP 21.3CCOPL56231.1 |  | 40 | 40 | 2025-01-16 | 2025-03-03 | 2025-03-23 | 2025-05-15 | 26
C-56-01HG-PL-CI-6400 | Backfilling from BVS-01 to KP 21.3 | 40 | 40 | 2025-01-16 | 2025-03-03 | 2025-03-23 | 2025-05-15 | 26
Backfilling from KP 21.3 to HGCPCCOPL56231.2 |  | 40 | 40 | 2025-03-07 | 2025-05-01 | 2025-05-15 | 2025-07-04 | 26
C-56-01HG-PL-CI-6600 | Backfilling from KP 21.3 to HGCP | 40 | 40 | 2025-03-07 | 2025-05-01 | 2025-05-15 | 2025-07-04 | 26
Berming from BVS-01 to KP 21.3CCOPL56232.1 |  | 50 | 50 | 2025-04-04 | 2025-05-24 | 2025-03-29 | 2025-05-30 | 24
C-56-01HG-PL-CI-6800 | Gatch Laying & Levelling | 40 | 40 | 2025-04-04 | 2025-05-22 | 2025-03-29 | 2025-05-20 | 24
C-56-01HG-PL-CI-6810 | Gatch Compaction | 40 | 40 | 2025-04-07 | 2025-05-24 | 2025-04-14 | 2025-05-30 | 24
Berming from KP 21.3 to HGCPCCOPL56232.2 |  | 49 | 49 | 2025-05-22 | 2025-07-14 | 2025-05-20 | 2025-07-19 | 22
C-56-01HG-PL-CI-7000 | Gatch Laying & Levelling | 38 | 38 | 2025-05-22 | 2025-07-11 | 2025-05-20 | 2025-07-07 | 24
C-56-01HG-PL-CI-7010 | Gatch Compaction | 38 | 38 | 2025-05-24 | 2025-07-14 | 2025-06-02 | 2025-07-19 | 22
NDRC by Micro Tunneling Method |  | 199 | 199 | 2024-09-21 | 2025-05-21 | 2024-11-26 | 2025-08-02 | 10
Micro Tunnelling @ CH 26+475 - 26+600 (NDRC-13) |  | 88 | 88 | 2024-09-21 | 2025-02-08 | 2025-01-09 | 2025-05-01 | 38
Entry & Exit Pit ConstructionCCOPL56916 |  | 43 | 43 | 2024-09-21 | 2024-11-29 | 2025-01-09 | 2025-02-27 | 38
C-56-01HG-CNM13-1000 | Sheet Piling for Driving & Receiving Pit | 10 | 10 | 2024-09-21 | 2024-10-22 | 2025-01-09 | 2025-01-20 | 38
C-56-01HG-CNM13-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-10-23 | 2024-10-26 | 2025-01-21 | 2025-01-24 | 38
C-56-01HG-CNM13-1010 | Driving & Receiving Pit Excavation | 14 | 14 | 2024-10-12 | 2024-10-28 | 2025-01-21 | 2025-02-05 | 38
C-56-01HG-CNM13-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 10 | 10 | 2024-10-28 | 2024-11-07 | 2025-01-25 | 2025-02-05 | 38
C-56-01HG-CNM13-1040 | Floor Blinding & French Drain in Driving Pit | 6 | 6 | 2024-11-08 | 2024-11-14 | 2025-02-06 | 2025-02-12 | 38
C-56-01HG-CNM13-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 6 | 6 | 2024-11-15 | 2024-11-21 | 2025-02-13 | 2025-02-19 | 38
C-56-01HG-CNM13-1060 | Construction of Exit Wall with Ring | 6 | 6 | 2024-11-23 | 2024-11-29 | 2025-02-21 | 2025-02-27 | 38
Tunneling & Jack UpCCOPL57962 |  | 35 | 35 | 2024-11-30 | 2025-01-23 | 2025-02-28 | 2025-04-19 | 38
C-56-01HG-CNM13-1200 | Jacking of MTBM & RC Sleeves | 7 | 7 | 2024-11-30 | 2024-12-14 | 2025-02-28 | 2025-03-09 | 38
C-56-01HG-CNM13-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2024-12-16 | 2024-12-19 | 2025-03-09 | 2025-03-15 | 38
C-56-01HG-CNM13-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-01-18 | 2025-01-23 | 2025-04-14 | 2025-04-19 | 38
Pipe Lowering, Welding, NDT & CoatingCCOPL57972 |  | 11 | 11 | 2024-12-20 | 2025-01-08 | 2025-03-15 | 2025-04-04 | 38
C-56-01HG-CNM13-1400 | Lowering & Welding of Carrier Pipe | 10 | 10 | 2024-12-20 | 2025-01-04 | 2025-03-15 | 2025-04-03 | 38
C-56-01HG-CNM13-1410 | NDT, Coating & Holiday Inspection of Carrier Pipe | 10 | 10 | 2024-12-21 | 2025-01-08 | 2025-03-17 | 2025-04-04 | 38
HydrotestingCCOPL57982 |  | 8 | 8 | 2025-01-09 | 2025-01-17 | 2025-04-04 | 2025-04-14 | 38
C-56-01HG-CNM13-1600 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 8 | 8 | 2025-01-09 | 2025-01-17 | 2025-04-04 | 2025-04-14 | 38
Re-Instatement of Entry & Exit PitCCOPL57992 |  | 10 | 10 | 2025-01-24 | 2025-02-08 | 2025-04-19 | 2025-05-01 | 38
C-56-01HG-CNM13-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 10 | 10 | 2025-01-24 | 2025-02-08 | 2025-04-19 | 2025-05-01 | 38
Micro Tunnelling @ CH 21+901 - 22+115 (NDRC-12) |  | 199 | 199 | 2024-10-22 | 2025-03-17 | 2024-11-26 | 2025-08-02 | 10
Entry & Exit Pit ConstructionCCOPL56914 |  | 83 | 83 | 2024-10-22 | 2025-01-02 | 2024-11-26 | 2025-03-06 | 10
C-56-01HG-CNM12-1000 | Sheet Piling for Driving & Receiving Pit | 35 | 35 | 2024-10-22 | 2024-11-21 | 2024-11-26 | 2025-01-08 | 10
C-56-01HG-CNM12-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-11-22 | 2024-11-26 | 2025-01-09 | 2025-01-13 | 11
C-56-01HG-CNM12-1010 | Driving & Receiving Pit Excavation | 25 | 25 | 2024-11-12 | 2024-11-27 | 2025-01-09 | 2025-02-06 | 10
C-56-01HG-CNM12-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 20 | 20 | 2024-11-27 | 2024-12-10 | 2025-01-15 | 2025-02-06 | 10
C-56-01HG-CNM12-1040 | Floor Blinding & French Drain in Driving Pit | 8 | 8 | 2024-12-11 | 2024-12-17 | 2025-02-07 | 2025-02-15 | 10
C-56-01HG-CNM12-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 8 | 8 | 2024-12-18 | 2024-12-24 | 2025-02-17 | 2025-02-25 | 10
C-56-01HG-CNM12-1060 | Construction of Exit Wall with Ring | 8 | 8 | 2024-12-26 | 2025-01-02 | 2025-02-25 | 2025-03-06 | 10
Tunneling & Jack UpCCOPL57602 |  | 102 | 102 | 2025-01-11 | 2025-02-25 | 2025-03-07 | 2025-07-17 | 10
C-56-01HG-CNM12-1200 | Jacking of MTBM & RC Sleeves | 40 | 40 | 2025-01-11 | 2025-01-20 | 2025-03-07 | 2025-05-01 | 10
C-56-01HG-CNM12-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2025-01-21 | 2025-01-24 | 2025-05-02 | 2025-05-07 | 10
C-56-01HG-CNM12-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-02-20 | 2025-02-25 | 2025-07-11 | 2025-07-17 | 10
Pipe Lowering, Welding, NDT & CoatingCCOPL57612 |  | 41 | 41 | 2025-01-25 | 2025-02-10 | 2025-05-07 | 2025-06-26 | 10
C-56-01HG-CNM12-1400 | Lowering & Welding of Carrier Pipe | 40 | 40 | 2025-01-25 | 2025-02-06 | 2025-05-07 | 2025-06-25 | 10
C-56-01HG-CNM12-1410 | NDT, Coating & Holiday Inspection of Carrier Pipe | 40 | 40 | 2025-01-27 | 2025-02-10 | 2025-05-08 | 2025-06-26 | 10
HydrotestingCCOPL57622 |  | 12 | 12 | 2025-02-11 | 2025-02-19 | 2025-06-26 | 2025-07-11 | 10
C-56-01HG-CNM12-1600 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 12 | 12 | 2025-02-11 | 2025-02-19 | 2025-06-26 | 2025-07-11 | 10
Re-Instatement of Entry & Exit PitCCOPL57632 |  | 14 | 14 | 2025-02-26 | 2025-03-17 | 2025-07-17 | 2025-08-02 | 10
C-56-01HG-CNM12-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-02-26 | 2025-03-17 | 2025-07-17 | 2025-08-02 | 10
Micro Tunnelling @ CH 20+207 - 20+481 (NDRC-11) |  | 185 | 185 | 2024-10-03 | 2025-05-21 | 2024-12-14 | 2025-08-02 | 10
Entry & Exit Pit ConstructionCCOPL56912 |  | 78 | 78 | 2024-10-03 | 2024-12-13 | 2024-12-14 | 2025-03-20 | 10
C-56-01HG-CNM11-1000 | Sheet Piling for Driving & Receiving Pit | 30 | 30 | 2024-10-03 | 2024-11-02 | 2024-12-14 | 2025-01-18 | 10
C-56-01HG-CNM11-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-11-04 | 2024-11-07 | 2025-01-20 | 2025-01-23 | 11
C-56-01HG-CNM11-1010 | Driving & Receiving Pit Excavation | 25 | 25 | 2024-10-24 | 2024-11-08 | 2025-01-20 | 2025-02-17 | 10
C-56-01HG-CNM11-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 20 | 20 | 2024-11-08 | 2024-11-19 | 2025-01-25 | 2025-02-17 | 10
C-56-01HG-CNM11-1040 | Floor Blinding & French Drain in Driving Pit | 8 | 8 | 2024-11-20 | 2024-11-26 | 2025-02-18 | 2025-02-26 | 10
C-56-01HG-CNM11-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 8 | 8 | 2024-11-27 | 2024-12-05 | 2025-02-27 | 2025-03-09 | 10
C-56-01HG-CNM11-1060 | Construction of Exit Wall with Ring | 8 | 8 | 2024-12-07 | 2024-12-13 | 2025-03-08 | 2025-03-20 | 10
Tunneling & Jack UpCCOPL57262 |  | 93 | 93 | 2025-03-02 | 2025-05-03 | 2025-03-20 | 2025-07-17 | 10
C-56-01HG-CNM11-1200 | Jacking of MTBM & RC Sleeves | 41 | 41 | 2025-03-02 | 2025-03-17 | 2025-03-20 | 2025-05-14 | 10
C-56-01HG-CNM11-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2025-03-17 | 2025-03-23 | 2025-05-14 | 2025-05-19 | 10
C-56-01HG-CNM11-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-04-28 | 2025-05-03 | 2025-07-11 | 2025-07-17 | 10
Pipe Lowering, Welding, NDT & CoatingCCOPL57272 |  | 31 | 31 | 2025-03-23 | 2025-04-18 | 2025-05-19 | 2025-06-26 | 10
C-56-01HG-CNM11-1400 | Lowering & Welding of Carrier Pipe | 30 | 30 | 2025-03-23 | 2025-04-15 | 2025-05-19 | 2025-06-25 | 10
C-56-01HG-CNM11-1410 | NDT, Coating & Holiday Inspection of Carrier Pipe | 30 | 30 | 2025-03-25 | 2025-04-18 | 2025-05-20 | 2025-06-26 | 10
HydrotestingCCOPL57282 |  | 12 | 12 | 2025-04-18 | 2025-04-28 | 2025-06-26 | 2025-07-11 | 10
C-56-01HG-CNM11-1600 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 12 | 12 | 2025-04-18 | 2025-04-28 | 2025-06-26 | 2025-07-11 | 10
Re-Instatement of Entry & Exit PitCCOPL57292 |  | 14 | 14 | 2025-05-03 | 2025-05-21 | 2025-07-17 | 2025-08-02 | 10
C-56-01HG-CNM11-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-05-03 | 2025-05-21 | 2025-07-17 | 2025-08-02 | 10
NDRC-09 (incl Hydrotest) @ CH 14+126 - 14+282 (Sabkha Const*) |  | 19 | 19 | 2025-02-04 | 2025-02-26 | 2025-04-19 | 2025-05-13 | 59
Entry & Exit Pit ConstructionCCOPL56906 |  | 2 | 2 | 2025-02-04 | 2025-02-06 | 2025-04-19 | 2025-04-22 | 17
C-56-01HG-CME09-1080 | Trench Excavation | 2 | 2 | 2025-02-04 | 2025-02-06 | 2025-04-19 | 2025-04-22 | 17
Tunneling & Jack UpCCOPL57922 |  | 2 | 2 | 2025-02-06 | 2025-02-08 | 2025-04-22 | 2025-04-24 | 59
C-56-01HG-CME09-1090 | Bedding | 2 | 2 | 2025-02-06 | 2025-02-08 | 2025-04-22 | 2025-04-24 | 59
Pipe Lowering, Welding, NDT & CoatingCCOPL57932 |  | 11 | 11 | 2025-02-08 | 2025-02-21 | 2025-04-24 | 2025-05-08 | 59
C-56-01HG-CME09-1100 | Lowering | 2 | 2 | 2025-02-08 | 2025-02-11 | 2025-04-24 | 2025-04-26 | 59
C-56-01HG-CME09-1110 | Section Tie-in Welding | 3 | 3 | 2025-02-11 | 2025-02-14 | 2025-04-26 | 2025-04-30 | 59
C-56-01HG-CME09-1120 | NDT (Tie-in Joint) | 3 | 3 | 2025-02-14 | 2025-02-18 | 2025-04-30 | 2025-05-03 | 59
C-56-01HG-CME09-1130 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-02-18 | 2025-02-21 | 2025-05-03 | 2025-05-08 | 59
HydrotestingCCOPL57942 |  | 2 | 2 | 2025-02-21 | 2025-02-24 | 2025-05-08 | 2025-05-10 | 59
C-56-01HG-CME09-1140 | Holiday Testing | 2 | 2 | 2025-02-21 | 2025-02-24 | 2025-05-08 | 2025-05-10 | 59
Re-Instatement of Entry & Exit PitCCOPL57952 |  | 2 | 2 | 2025-02-24 | 2025-02-26 | 2025-05-10 | 2025-05-13 | 59
C-56-01HG-CME09-1150 | Padding & Back Filling | 2 | 2 | 2025-02-24 | 2025-02-26 | 2025-05-10 | 2025-05-13 | 59
NDRC by Micro Tunnelling Method |  | 178 | 178 | 2024-10-11 | 2025-03-23 | 2024-12-11 | 2025-07-22 | 20
Micro Tunnelling @ CH 18+786 - 19+127 (NDRC-10) |  | 178 | 178 | 2024-10-11 | 2025-03-23 | 2024-12-11 | 2025-07-22 | 20
Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 |  | 159 | 159 | 2024-10-11 | 2025-02-24 | 2024-12-11 | 2025-06-30 | 20
C-56-01HG-CNH10-1000 | Sheet Piling for Driving & Receiving Pit | 35 | 35 | 2024-10-11 | 2024-11-08 | 2024-12-11 | 2025-01-21 | 20
C-56-01HG-CNH10-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-11-09 | 2024-11-13 | 2025-01-22 | 2025-01-25 | 25
C-56-01HG-CNH10-1010 | Driving & Receiving Pit Excavation | 26 | 26 | 2024-11-01 | 2024-11-16 | 2025-01-22 | 2025-02-21 | 20
C-56-01HG-CNH10-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 22 | 22 | 2024-11-14 | 2024-11-25 | 2025-01-27 | 2025-02-21 | 20
C-56-01HG-CNH10-1040 | Floor Blinding & French Drain in Driving Pit | 6 | 6 | 2024-11-26 | 2024-12-04 | 2025-02-21 | 2025-02-28 | 20
C-56-01HG-CNH10-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 6 | 6 | 2024-12-05 | 2024-12-11 | 2025-02-28 | 2025-03-08 | 20
C-56-01HG-CNH10-1060 | Construction of Exit Wall with Ring | 6 | 6 | 2024-12-13 | 2024-12-19 | 2025-03-10 | 2025-03-19 | 20
C-56-01HG-CNH10-1070 | Lowering & Welding of Carrier Pipe | 30 | 30 | 2025-01-16 | 2025-02-08 | 2025-05-05 | 2025-06-11 | 20
C-56-01HG-CNH10-1080 | NDT, Coating & Holiday Inspection of Carrier Pipe | 30 | 30 | 2025-01-17 | 2025-02-12 | 2025-05-06 | 2025-06-12 | 20
C-56-01HG-CNH10-1090 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 14 | 14 | 2025-02-13 | 2025-02-24 | 2025-06-12 | 2025-06-30 | 20
Tunneling & Jack UpCCOPL58342 |  | 84 | 84 | 2024-12-20 | 2025-03-01 | 2025-03-19 | 2025-07-05 | 20
C-56-01HG-CNH10-1200 | Jacking of MTBM & RC Sleeves | 30 | 30 | 2024-12-20 | 2025-01-10 | 2025-03-19 | 2025-04-29 | 20
C-56-01HG-CNH10-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2025-01-11 | 2025-01-15 | 2025-04-30 | 2025-05-03 | 20
C-56-01HG-CNH10-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-02-25 | 2025-03-01 | 2025-06-30 | 2025-07-05 | 20
Re-Instatement of Entry & Exit PitCCOPL58352 |  | 14 | 14 | 2025-03-02 | 2025-03-23 | 2025-07-05 | 2025-07-22 | 20
C-56-01HG-CNH10-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-03-02 | 2025-03-23 | 2025-07-05 | 2025-07-22 | 20
Telecommunication Works |  | 90 | 90 | 2025-01-20 | 2025-05-06 | 2025-03-28 | 2025-07-19 | 22
Telecommunication Works from BVS-01 to CCOP56IC21.1 |  | 37 | 37 | 2025-01-20 | 2025-03-03 | 2025-03-28 | 2025-05-15 | 74
C-56-01HG-PL-TE-8200 | FO - Cable Pulling/ Laying | 35 | 35 | 2025-01-20 | 2025-02-28 | 2025-03-28 | 2025-05-13 | 44
C-56-01HG-PL-TE-8210 | Termination/Splicing @ BVS | 2 | 2 | 2025-03-01 | 2025-03-03 | 2025-05-13 | 2025-05-15 | 74
Telecommunication Works from KP 21.3 t CCOP56IC21.2 |  | 34 | 34 | 2025-03-22 | 2025-05-06 | 2025-06-09 | 2025-07-19 | 22
C-56-01HG-PL-TE-8400 | FO - Cable Pulling/ Laying | 32 | 32 | 2025-03-22 | 2025-05-03 | 2025-06-09 | 2025-07-17 | 22
C-56-01HG-PL-TE-8410 | Termination/Splicing @ BVS | 2 | 2 | 2025-05-03 | 2025-05-06 | 2025-07-17 | 2025-07-19 | 22
56"x12.6 Km Pipeline from Habshan Complex to BVS-01at KP 12.6 |  | 365 | 255 | 2024-06-14 | 2025-07-21 | 14-Jun-24 A | 2025-09-08 | 19
56"x12.6 Km Pipeline from Habshan Complex to BVS-01 at KP 12.6 |  | 365 | 255 | 2024-06-14 | 2025-07-21 | 14-Jun-24 A | 2025-09-08 | 19
56" Main Pipeline Construction |  | 365 | 255 | 2024-06-14 | 2025-07-21 | 14-Jun-24 A | 2025-09-08 | 19
Main Pipeline |  | 365 | 255 | 2024-06-14 | 2025-07-21 | 14-Jun-24 A | 2025-09-08 | 19
SurveyingCCOPL56200 |  | 30 | 0 | 2024-06-14 | 2024-07-23 | 14-Jun-24 A | 23-Jul-24 A
C-56-HC01-PL-CI-1000 | Survey Marking | 30 | 0 | 2024-06-14 | 2024-07-23 | 14-Jun-24 A | 23-Jul-24 A
Cut & FillCCOPL56201 |  | 81 | 23 | 2024-10-28 | 2024-12-20 | 30-Aug-24 A | 2024-12-05 | 93
C-56-HC01-PL-CI-1400 | Cut & Fill (@ Non-Sabkha) | 81 | 23 | 2024-10-28 | 2024-12-20 | 30-Aug-24 A | 2024-12-05 | 93
ROW Access RoadCCOPL56203 |  | 64 | 23 | 2024-09-07 | 2024-10-28 | 07-Sep-24 A | 2024-11-21 | 93
C-56-HC01-PL-CI-1800 | Non-Sabka ROW/Grading | 64 | 23 | 2024-09-07 | 2024-10-28 | 07-Sep-24 A | 2024-11-21 | 93
Excavation (incl Bedding) from Habshan complex to KP 6CCOPL56206.1 |  | 35 | 35 | 2025-02-18 | 2025-04-09 | 2025-03-28 | 2025-05-13 | 26
C-56-HC01-PL-CI-2400 | Trench Excavation | 28 | 28 | 2025-02-18 | 2025-03-28 | 2025-03-28 | 2025-05-03 | 26
C-56-HC01-PL-CI-2410 | Bedding | 28 | 28 | 2025-02-26 | 2025-04-09 | 2025-04-09 | 2025-05-13 | 26
Excavation (incl Bedding) from KP 6 to KP 12.6CCOPL56206.2 |  | 35 | 35 | 2025-02-18 | 2025-04-09 | 2025-03-28 | 2025-05-13 | 40
C-56-HC01-PL-CI-2600 | Trench Excavation | 28 | 28 | 2025-02-18 | 2025-03-28 | 2025-03-28 | 2025-05-03 | 43
C-56-HC01-PL-CI-2610 | Bedding | 28 | 28 | 2025-02-26 | 2025-04-09 | 2025-04-09 | 2025-05-13 | 40
Pipe StringingCCOPL56205 |  | 21 | 21 | 2025-01-14 | 2025-02-06 | 2025-03-01 | 2025-04-04 | 21
C-56-HC01-PL-ME-2800 | Stringing (BVS-01 to HBCMPLX) | 21 | 21 | 2025-01-14 | 2025-02-06 | 2025-03-01 | 2025-04-04 | 21
Automatic WeldingCCOPL56207 |  | 40 | 40 | 2025-01-31 | 2025-03-23 | 2025-03-05 | 2025-04-30 | 19
C-56-HC01-PL-ME-3600 | Automatic Welding | 40 | 40 | 2025-01-31 | 2025-03-23 | 2025-03-05 | 2025-04-30 | 19
NDT TestCCOPL56208 |  | 22 | 22 | 2025-02-21 | 2025-03-23 | 2025-04-04 | 2025-04-30 | 20
C-56-HC01-PL-ME-4000 | NDT | 22 | 22 | 2025-02-21 | 2025-03-23 | 2025-04-04 | 2025-04-30 | 20
Ext. Joint Coating from Habshan complex to KP 6CCOPL56210.1 |  | 45 | 45 | 2025-02-24 | 2025-04-26 | 2025-04-07 | 2025-05-30 | 26
C-56-HC01-PL-ME-4400 | Ext. Joint Coating | 24 | 24 | 2025-02-24 | 2025-04-07 | 2025-04-07 | 2025-05-05 | 20
C-56-HC01-PL-ME-4410 | Ext. Joint Coating (Tie-in Joint) | 28 | 28 | 2025-03-18 | 2025-04-26 | 2025-04-26 | 2025-05-30 | 26
Ext. Joint Coating from KP 6 to KP 12.6CCOPL56210.2 |  | 41 | 41 | 2025-04-07 | 2025-05-26 | 2025-05-05 | 2025-06-25 | 20
C-56-HC01-PL-ME-4600 | Ext. Joint Coating | 28 | 28 | 2025-04-07 | 2025-05-10 | 2025-05-05 | 2025-06-10 | 20
C-56-HC01-PL-ME-4610 | Ext. Joint Coating (Tie-in Joint) | 20 | 20 | 2025-05-01 | 2025-05-26 | 2025-05-30 | 2025-06-25 | 20
Cold BendsCCOPL56209 |  | 32 | 32 | 2025-04-05 | 2025-05-14 | 2025-05-03 | 2025-06-13 | 22
C-56-HC01-PL-ME-3200 | Cold Bends | 32 | 32 | 2025-04-05 | 2025-05-14 | 2025-05-03 | 2025-06-13 | 22
Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 |  | 32 | 32 | 2025-03-15 | 2025-04-29 | 2025-04-24 | 2025-06-02 | 26
C-56-HC01-PL-ME-4800 | Lowering | 20 | 20 | 2025-03-15 | 2025-04-15 | 2025-04-24 | 2025-05-19 | 26
C-56-HC01-PL-ME-4810 | Section Tie-in Welding | 20 | 20 | 2025-03-15 | 2025-04-15 | 2025-04-24 | 2025-05-19 | 26
C-56-HC01-PL-ME-4820 | NDT (Tie-in Joint) | 20 | 20 | 2025-03-16 | 2025-04-16 | 2025-04-25 | 2025-05-20 | 26
C-56-HC01-PL-ME-4830 | Holiday Testing | 20 | 20 | 2025-04-05 | 2025-04-29 | 2025-05-09 | 2025-06-02 | 26
Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 |  | 34 | 34 | 2025-04-19 | 2025-05-30 | 2025-05-19 | 2025-07-01 | 20
C-56-HC01-PL-ME-5000 | Lowering | 20 | 20 | 2025-04-19 | 2025-05-14 | 2025-05-19 | 2025-06-13 | 20
C-56-HC01-PL-ME-5010 | Section Tie-in Welding | 20 | 20 | 2025-04-22 | 2025-05-16 | 2025-05-21 | 2025-06-16 | 20
C-56-HC01-PL-ME-5020 | NDT (Tie-in Joint) | 20 | 20 | 2025-04-26 | 2025-05-21 | 2025-05-26 | 2025-06-20 | 20
C-56-HC01-PL-ME-5030 | Holiday Testing | 20 | 20 | 2025-05-07 | 2025-05-30 | 2025-06-04 | 2025-07-01 | 20
Crossings - UG CableCCOPL56216 |  | 42 | 42 | 2025-01-14 | 2025-03-03 | 2025-03-01 | 2025-04-29 | 76
Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) |  | 14 | 14 | 2025-01-14 | 2025-01-29 | 2025-03-01 | 2025-03-22 | 104
C-56-HC01-CMA01-1000 | Trench Excavation | 8 | 8 | 2025-01-14 | 2025-01-22 | 2025-03-01 | 2025-03-12 | 61
C-56-HC01-CMA01-1010 | Bedding | 1 | 1 | 2025-01-22 | 2025-01-22 | 2025-03-11 | 2025-03-12 | 89
C-56-HC01-CMA01-1020 | Lowering | 1 | 1 | 2025-01-23 | 2025-01-23 | 2025-03-13 | 2025-03-14 | 89
C-56-HC01-CMA01-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-23 | 2025-01-24 | 2025-03-13 | 2025-03-15 | 89
C-56-HC01-CMA01-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-24 | 2025-01-25 | 2025-03-14 | 2025-03-17 | 104
C-56-HC01-CMA01-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-25 | 2025-01-27 | 2025-03-15 | 2025-03-18 | 104
C-56-HC01-CMA01-1060 | Holiday Testing | 1 | 1 | 2025-01-28 | 2025-01-28 | 2025-03-19 | 2025-03-20 | 104
C-56-HC01-CMA01-1070 | Padding | 1 | 1 | 2025-01-29 | 2025-01-29 | 2025-03-20 | 2025-03-22 | 104
Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) |  | 12 | 12 | 2025-01-14 | 2025-01-27 | 2025-03-01 | 2025-03-18 | 106
C-56-HC01-CMA06-1000 | Trench Excavation | 6 | 6 | 2025-01-14 | 2025-01-20 | 2025-03-01 | 2025-03-09 | 61
C-56-HC01-CMA06-1010 | Bedding | 1 | 1 | 2025-01-20 | 2025-01-20 | 2025-03-08 | 2025-03-09 | 91
C-56-HC01-CMA06-1020 | Lowering | 1 | 1 | 2025-01-21 | 2025-01-21 | 2025-03-09 | 2025-03-11 | 91
C-56-HC01-CMA06-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-21 | 2025-01-22 | 2025-03-09 | 2025-03-12 | 91
C-56-HC01-CMA06-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-22 | 2025-01-23 | 2025-03-11 | 2025-03-14 | 106
C-56-HC01-CMA06-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-23 | 2025-01-24 | 2025-03-13 | 2025-03-15 | 106
C-56-HC01-CMA06-1060 | Holiday Testing | 1 | 1 | 2025-01-25 | 2025-01-25 | 2025-03-15 | 2025-03-17 | 106
C-56-HC01-CMA06-1070 | Padding | 1 | 1 | 2025-01-27 | 2025-01-27 | 2025-03-17 | 2025-03-18 | 106
Crossing Manual @ KP 2+913 (CX-10) |  | 12 | 12 | 2025-01-21 | 2025-02-03 | 2025-03-09 | 2025-03-28 | 100
C-56-HC01-CMA05-1000 | Trench Excavation | 6 | 6 | 2025-01-21 | 2025-01-27 | 2025-03-09 | 2025-03-18 | 61
C-56-HC01-CMA05-1010 | Bedding | 1 | 1 | 2025-01-27 | 2025-01-27 | 2025-03-17 | 2025-03-18 | 85
C-56-HC01-CMA05-1020 | Lowering | 1 | 1 | 2025-01-28 | 2025-01-28 | 2025-03-19 | 2025-03-20 | 85
C-56-HC01-CMA05-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-28 | 2025-01-29 | 2025-03-19 | 2025-03-22 | 85
C-56-HC01-CMA05-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-29 | 2025-01-30 | 2025-03-20 | 2025-03-23 | 100
C-56-HC01-CMA05-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-30 | 2025-01-31 | 2025-03-22 | 2025-03-24 | 100
C-56-HC01-CMA05-1060 | Holiday Testing | 1 | 1 | 2025-02-01 | 2025-02-01 | 2025-03-25 | 2025-03-26 | 100
C-56-HC01-CMA05-1070 | Padding | 1 | 1 | 2025-02-03 | 2025-02-03 | 2025-03-26 | 2025-03-28 | 100
Crossing Manual @ KP 6+074 (CX-11) |  | 12 | 12 | 2025-01-28 | 2025-02-10 | 2025-03-19 | 2025-04-08 | 94
C-56-HC01-CMA07-1000 | Trench Excavation | 6 | 6 | 2025-01-28 | 2025-02-03 | 2025-03-19 | 2025-03-28 | 61
C-56-HC01-CMA07-1010 | Bedding | 1 | 1 | 2025-02-03 | 2025-02-03 | 2025-03-26 | 2025-03-28 | 79
C-56-HC01-CMA07-1020 | Lowering | 1 | 1 | 2025-02-04 | 2025-02-04 | 2025-03-28 | 2025-03-29 | 79
C-56-HC01-CMA07-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-04 | 2025-02-05 | 2025-03-28 | 2025-04-03 | 79
C-56-HC01-CMA07-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-05 | 2025-02-06 | 2025-03-29 | 2025-04-04 | 94
C-56-HC01-CMA07-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-06 | 2025-02-07 | 2025-04-03 | 2025-04-05 | 94
C-56-HC01-CMA07-1060 | Holiday Testing | 1 | 1 | 2025-02-08 | 2025-02-08 | 2025-04-05 | 2025-04-07 | 94
C-56-HC01-CMA07-1070 | Padding | 1 | 1 | 2025-02-10 | 2025-02-10 | 2025-04-07 | 2025-04-08 | 94
Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) |  | 12 | 12 | 2025-02-04 | 2025-02-17 | 2025-03-28 | 2025-04-15 | 88
C-56-HC01-CMA04-1000 | Trench Excavation | 6 | 6 | 2025-02-04 | 2025-02-10 | 2025-03-28 | 2025-04-08 | 61
C-56-HC01-CMA04-1010 | Bedding | 1 | 1 | 2025-02-10 | 2025-02-10 | 2025-04-07 | 2025-04-08 | 73
C-56-HC01-CMA04-1020 | Lowering | 1 | 1 | 2025-02-11 | 2025-02-11 | 2025-04-08 | 2025-04-09 | 73
C-56-HC01-CMA04-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-11 | 2025-02-12 | 2025-04-08 | 2025-04-10 | 73
C-56-HC01-CMA04-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-12 | 2025-02-13 | 2025-04-09 | 2025-04-11 | 88
C-56-HC01-CMA04-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-13 | 2025-02-14 | 2025-04-10 | 2025-04-12 | 88
C-56-HC01-CMA04-1060 | Holiday Testing | 1 | 1 | 2025-02-15 | 2025-02-15 | 2025-04-12 | 2025-04-14 | 88
C-56-HC01-CMA04-1070 | Padding | 1 | 1 | 2025-02-17 | 2025-02-17 | 2025-04-14 | 2025-04-15 | 88
Crossing Manual @ KP 10+050 (CX-17) |  | 12 | 12 | 2025-02-11 | 2025-02-24 | 2025-04-08 | 2025-04-22 | 82
C-56-HC01-CMA02-1000 | Trench Excavation | 6 | 6 | 2025-02-11 | 2025-02-17 | 2025-04-08 | 2025-04-15 | 61
C-56-HC01-CMA02-1010 | Bedding | 1 | 1 | 2025-02-17 | 2025-02-17 | 2025-04-14 | 2025-04-15 | 67
C-56-HC01-CMA02-1020 | Lowering | 1 | 1 | 2025-02-18 | 2025-02-18 | 2025-04-15 | 2025-04-16 | 67
C-56-HC01-CMA02-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-18 | 2025-02-19 | 2025-04-15 | 2025-04-17 | 67
C-56-HC01-CMA02-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-19 | 2025-02-20 | 2025-04-16 | 2025-04-18 | 82
C-56-HC01-CMA02-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-20 | 2025-02-21 | 2025-04-17 | 2025-04-19 | 82
C-56-HC01-CMA02-1060 | Holiday Testing | 1 | 1 | 2025-02-22 | 2025-02-22 | 2025-04-19 | 2025-04-21 | 82
C-56-HC01-CMA02-1070 | Padding | 1 | 1 | 2025-02-24 | 2025-02-24 | 2025-04-21 | 2025-04-22 | 82
Crossing Manual @ KP 11+183 (CX-18) |  | 12 | 12 | 2025-02-18 | 2025-03-03 | 2025-04-15 | 2025-04-29 | 76
C-56-HC01-CMA03-1000 | Trench Excavation | 6 | 6 | 2025-02-18 | 2025-02-24 | 2025-04-15 | 2025-04-22 | 61
C-56-HC01-CMA03-1010 | Bedding | 1 | 1 | 2025-02-24 | 2025-02-24 | 2025-04-21 | 2025-04-22 | 61
C-56-HC01-CMA03-1020 | Lowering | 1 | 1 | 2025-02-25 | 2025-02-25 | 2025-04-22 | 2025-04-23 | 61
C-56-HC01-CMA03-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-25 | 2025-02-26 | 2025-04-22 | 2025-04-24 | 61
C-56-HC01-CMA03-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-26 | 2025-02-27 | 2025-04-23 | 2025-04-25 | 76
C-56-HC01-CMA03-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-27 | 2025-02-28 | 2025-04-24 | 2025-04-26 | 76
C-56-HC01-CMA03-1060 | Holiday Testing | 1 | 1 | 2025-03-01 | 2025-03-01 | 2025-04-26 | 2025-04-28 | 76
C-56-HC01-CMA03-1070 | Padding | 1 | 1 | 2025-03-02 | 2025-03-03 | 2025-04-28 | 2025-04-29 | 76
Crossings - UG PipeCCOPL56213.1 |  | 64 | 64 | 2025-01-14 | 2025-04-08 | 2025-03-01 | 2025-05-26 | 54
Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) |  | 15 | 15 | 2025-01-14 | 2025-01-30 | 2025-03-01 | 2025-03-23 | 39
C-56-HC01-CMA08-1000 | Trench Excavation | 9 | 9 | 2025-01-14 | 2025-01-23 | 2025-03-01 | 2025-03-14 | 39
C-56-HC01-CMA08-1010 | Bedding | 1 | 1 | 2025-01-23 | 2025-01-23 | 2025-03-13 | 2025-03-14 | 39
C-56-HC01-CMA08-1020 | Lowering | 1 | 1 | 2025-01-24 | 2025-01-24 | 2025-03-14 | 2025-03-15 | 39
C-56-HC01-CMA08-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-24 | 2025-01-25 | 2025-03-14 | 2025-03-17 | 39
C-56-HC01-CMA08-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-25 | 2025-01-27 | 2025-03-15 | 2025-03-18 | 39
C-56-HC01-CMA08-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-27 | 2025-01-28 | 2025-03-17 | 2025-03-20 | 39
C-56-HC01-CMA08-1060 | Holiday Testing | 1 | 1 | 2025-01-29 | 2025-01-29 | 2025-03-20 | 2025-03-22 | 39
C-56-HC01-CMA08-1070 | Padding | 1 | 1 | 2025-01-30 | 2025-01-30 | 2025-03-22 | 2025-03-23 | 39
Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) |  | 18 | 18 | 2025-01-31 | 2025-02-20 | 2025-03-23 | 2025-04-18 | 39
C-56-HC01-CMA12-1000 | Trench Excavation | 12 | 12 | 2025-01-31 | 2025-02-13 | 2025-03-23 | 2025-04-11 | 39
C-56-HC01-CMA12-1010 | Bedding | 1 | 1 | 2025-02-13 | 2025-02-13 | 2025-04-10 | 2025-04-11 | 39
C-56-HC01-CMA12-1020 | Lowering | 1 | 1 | 2025-02-14 | 2025-02-14 | 2025-04-11 | 2025-04-12 | 39
C-56-HC01-CMA12-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-14 | 2025-02-15 | 2025-04-11 | 2025-04-14 | 39
C-56-HC01-CMA12-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-15 | 2025-02-17 | 2025-04-12 | 2025-04-15 | 39
C-56-HC01-CMA12-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-17 | 2025-02-18 | 2025-04-14 | 2025-04-16 | 39
C-56-HC01-CMA12-1060 | Holiday Testing | 1 | 1 | 2025-02-19 | 2025-02-19 | 2025-04-16 | 2025-04-17 | 39
C-56-HC01-CMA12-1070 | Padding | 1 | 1 | 2025-02-20 | 2025-02-20 | 2025-04-17 | 2025-04-18 | 39
Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) |  | 22 | 22 | 2025-02-21 | 2025-03-23 | 2025-04-18 | 2025-05-15 | 63
C-56-HC01-CMA10-1000 | Trench Excavation | 12 | 12 | 2025-02-21 | 2025-03-08 | 2025-04-18 | 2025-05-02 | 39
C-56-HC01-CMA10-1010 | Bedding | 1 | 1 | 2025-03-07 | 2025-03-08 | 2025-05-01 | 2025-05-02 | 50
C-56-HC01-CMA10-1020 | Lowering | 1 | 1 | 2025-03-08 | 2025-03-09 | 2025-05-02 | 2025-05-03 | 50
C-56-HC01-CMA10-1030 | Section Tie-in Welding | 4 | 4 | 2025-03-08 | 2025-03-14 | 2025-05-02 | 2025-05-08 | 50
C-56-HC01-CMA10-1040 | NDT (Tie-in Joint) | 4 | 4 | 2025-03-09 | 2025-03-15 | 2025-05-03 | 2025-05-09 | 63
C-56-HC01-CMA10-1050 | Ext. Joint Coating (Tie-in Joint) | 4 | 4 | 2025-03-11 | 2025-03-17 | 2025-05-05 | 2025-05-10 | 63
C-56-HC01-CMA10-1060 | Holiday Testing | 2 | 2 | 2025-03-17 | 2025-03-20 | 2025-05-10 | 2025-05-13 | 63
C-56-HC01-CMA10-1070 | Padding | 2 | 2 | 2025-03-20 | 2025-03-23 | 2025-05-13 | 2025-05-15 | 63
Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) |  | 19 | 19 | 2025-03-08 | 2025-04-08 | 2025-05-02 | 2025-05-26 | 54
C-56-HC01-CMA15-1000 | Trench Excavation | 12 | 12 | 2025-03-08 | 2025-03-26 | 2025-05-02 | 2025-05-17 | 39
C-56-HC01-CMA15-1010 | Bedding | 1 | 1 | 2025-03-25 | 2025-03-26 | 2025-05-16 | 2025-05-17 | 39
C-56-HC01-CMA15-1020 | Lowering | 1 | 1 | 2025-03-26 | 2025-03-28 | 2025-05-17 | 2025-05-19 | 39
C-56-HC01-CMA15-1030 | Section Tie-in Welding | 3 | 3 | 2025-03-26 | 2025-04-03 | 2025-05-17 | 2025-05-21 | 39
C-56-HC01-CMA15-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-03-28 | 2025-04-04 | 2025-05-19 | 2025-05-22 | 54
C-56-HC01-CMA15-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-03-29 | 2025-04-05 | 2025-05-20 | 2025-05-23 | 54
C-56-HC01-CMA15-1060 | Holiday Testing | 1 | 1 | 2025-04-05 | 2025-04-07 | 2025-05-23 | 2025-05-24 | 54
C-56-HC01-CMA15-1070 | Padding | 1 | 1 | 2025-04-07 | 2025-04-08 | 2025-05-24 | 2025-05-26 | 54
Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) |  | 18 | 18 | 2025-01-14 | 2025-02-03 | 2025-03-01 | 2025-03-28 | 100
C-56-HC01-CMA14-1000 | Trench Excavation | 12 | 12 | 2025-01-14 | 2025-01-27 | 2025-03-01 | 2025-03-18 | 67
C-56-HC01-CMA14-1010 | Bedding | 1 | 1 | 2025-01-27 | 2025-01-27 | 2025-03-17 | 2025-03-18 | 85
C-56-HC01-CMA14-1020 | Lowering | 1 | 1 | 2025-01-28 | 2025-01-28 | 2025-03-19 | 2025-03-20 | 85
C-56-HC01-CMA14-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-28 | 2025-01-29 | 2025-03-19 | 2025-03-22 | 85
C-56-HC01-CMA14-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-29 | 2025-01-30 | 2025-03-20 | 2025-03-23 | 100
C-56-HC01-CMA14-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-30 | 2025-01-31 | 2025-03-22 | 2025-03-24 | 100
C-56-HC01-CMA14-1060 | Holiday Testing | 1 | 1 | 2025-02-01 | 2025-02-01 | 2025-03-25 | 2025-03-26 | 100
C-56-HC01-CMA14-1070 | Padding | 1 | 1 | 2025-02-03 | 2025-02-03 | 2025-03-26 | 2025-03-28 | 100
Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) |  | 18 | 18 | 2025-01-28 | 2025-02-17 | 2025-03-19 | 2025-04-15 | 88
C-56-HC01-CMA11-1000 | Trench Excavation | 12 | 12 | 2025-01-28 | 2025-02-10 | 2025-03-19 | 2025-04-08 | 67
C-56-HC01-CMA11-1010 | Bedding | 1 | 1 | 2025-02-10 | 2025-02-10 | 2025-04-07 | 2025-04-08 | 73
C-56-HC01-CMA11-1020 | Lowering | 1 | 1 | 2025-02-11 | 2025-02-11 | 2025-04-08 | 2025-04-09 | 73
C-56-HC01-CMA11-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-11 | 2025-02-12 | 2025-04-08 | 2025-04-10 | 73
C-56-HC01-CMA11-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-12 | 2025-02-13 | 2025-04-09 | 2025-04-11 | 88
C-56-HC01-CMA11-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-13 | 2025-02-14 | 2025-04-10 | 2025-04-12 | 88
C-56-HC01-CMA11-1060 | Holiday Testing | 1 | 1 | 2025-02-15 | 2025-02-15 | 2025-04-12 | 2025-04-14 | 88
C-56-HC01-CMA11-1070 | Padding | 1 | 1 | 2025-02-17 | 2025-02-17 | 2025-04-14 | 2025-04-15 | 88
Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) |  | 24 | 24 | 2025-01-28 | 2025-02-24 | 2025-03-19 | 2025-04-22 | 82
C-56-HC01-CMA09-1000 | Trench Excavation | 16 | 16 | 2025-01-28 | 2025-02-14 | 2025-03-19 | 2025-04-12 | 67
C-56-HC01-CMA09-1010 | Bedding | 1 | 1 | 2025-02-14 | 2025-02-14 | 2025-04-11 | 2025-04-12 | 67
C-56-HC01-CMA09-1020 | Lowering | 1 | 1 | 2025-02-15 | 2025-02-15 | 2025-04-12 | 2025-04-14 | 67
C-56-HC01-CMA09-1030 | Section Tie-in Welding | 4 | 4 | 2025-02-15 | 2025-02-19 | 2025-04-12 | 2025-04-17 | 67
C-56-HC01-CMA09-1040 | NDT (Tie-in Joint) | 4 | 4 | 2025-02-17 | 2025-02-20 | 2025-04-14 | 2025-04-18 | 82
C-56-HC01-CMA09-1050 | Ext. Joint Coating (Tie-in Joint) | 4 | 4 | 2025-02-18 | 2025-02-21 | 2025-04-15 | 2025-04-19 | 82
C-56-HC01-CMA09-1060 | Holiday Testing | 1 | 1 | 2025-02-22 | 2025-02-22 | 2025-04-19 | 2025-04-21 | 82
C-56-HC01-CMA09-1070 | Padding | 1 | 1 | 2025-02-24 | 2025-02-24 | 2025-04-21 | 2025-04-22 | 82
Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) |  | 14 | 14 | 2025-01-28 | 2025-02-12 | 2025-03-19 | 2025-04-10 | 92
C-56-HC01-CMA13-1000 | Trench Excavation | 8 | 8 | 2025-01-28 | 2025-02-05 | 2025-03-19 | 2025-04-03 | 77
C-56-HC01-CMA13-1010 | Bedding | 1 | 1 | 2025-02-05 | 2025-02-05 | 2025-03-29 | 2025-04-03 | 77
C-56-HC01-CMA13-1020 | Lowering | 1 | 1 | 2025-02-06 | 2025-02-06 | 2025-04-03 | 2025-04-04 | 77
C-56-HC01-CMA13-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-06 | 2025-02-07 | 2025-04-03 | 2025-04-05 | 77
C-56-HC01-CMA13-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-07 | 2025-02-08 | 2025-04-04 | 2025-04-07 | 92
C-56-HC01-CMA13-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-08 | 2025-02-10 | 2025-04-05 | 2025-04-08 | 92
C-56-HC01-CMA13-1060 | Holiday Testing | 1 | 1 | 2025-02-11 | 2025-02-11 | 2025-04-08 | 2025-04-09 | 92
C-56-HC01-CMA13-1070 | Padding | 1 | 1 | 2025-02-12 | 2025-02-12 | 2025-04-09 | 2025-04-10 | 92
Crossings - UG PipeCCOPL56213.2 |  | 43 | 43 | 2025-01-14 | 2025-03-05 | 2025-03-01 | 2025-04-30 | 75
Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) |  | 14 | 14 | 2025-01-14 | 2025-01-29 | 2025-03-01 | 2025-03-22 | 104
C-56-HC01-CMA16-1000 | Trench Excavation | 8 | 8 | 2025-01-14 | 2025-01-22 | 2025-03-01 | 2025-03-12 | 65
C-56-HC01-CMA16-1010 | Bedding | 1 | 1 | 2025-01-22 | 2025-01-22 | 2025-03-11 | 2025-03-12 | 89
C-56-HC01-CMA16-1020 | Lowering | 1 | 1 | 2025-01-23 | 2025-01-23 | 2025-03-13 | 2025-03-14 | 89
C-56-HC01-CMA16-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-23 | 2025-01-24 | 2025-03-13 | 2025-03-15 | 89
C-56-HC01-CMA16-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-24 | 2025-01-25 | 2025-03-14 | 2025-03-17 | 104
C-56-HC01-CMA16-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-25 | 2025-01-27 | 2025-03-15 | 2025-03-18 | 104
C-56-HC01-CMA16-1060 | Holiday Testing | 1 | 1 | 2025-01-28 | 2025-01-28 | 2025-03-19 | 2025-03-20 | 104
C-56-HC01-CMA16-1070 | Padding | 1 | 1 | 2025-01-29 | 2025-01-29 | 2025-03-20 | 2025-03-22 | 104
Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) |  | 14 | 14 | 2025-01-23 | 2025-02-07 | 2025-03-13 | 2025-04-05 | 96
C-56-HC01-CMA17-1000 | Trench Excavation | 8 | 8 | 2025-01-23 | 2025-01-31 | 2025-03-13 | 2025-03-24 | 65
C-56-HC01-CMA17-1010 | Bedding | 1 | 1 | 2025-01-31 | 2025-01-31 | 2025-03-23 | 2025-03-24 | 81
C-56-HC01-CMA17-1020 | Lowering | 1 | 1 | 2025-02-01 | 2025-02-01 | 2025-03-25 | 2025-03-26 | 81
C-56-HC01-CMA17-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-01 | 2025-02-03 | 2025-03-25 | 2025-03-28 | 81
C-56-HC01-CMA17-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-03 | 2025-02-04 | 2025-03-26 | 2025-03-29 | 96
C-56-HC01-CMA17-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-04 | 2025-02-05 | 2025-03-28 | 2025-04-03 | 96
C-56-HC01-CMA17-1060 | Holiday Testing | 1 | 1 | 2025-02-06 | 2025-02-06 | 2025-04-03 | 2025-04-04 | 96
C-56-HC01-CMA17-1070 | Padding | 1 | 1 | 2025-02-07 | 2025-02-07 | 2025-04-04 | 2025-04-05 | 96
Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) |  | 14 | 14 | 2025-02-01 | 2025-02-17 | 2025-03-25 | 2025-04-15 | 88
C-56-HC01-CMA18-1000 | Trench Excavation | 8 | 8 | 2025-02-01 | 2025-02-10 | 2025-03-25 | 2025-04-08 | 65
C-56-HC01-CMA18-1010 | Bedding | 1 | 1 | 2025-02-10 | 2025-02-10 | 2025-04-07 | 2025-04-08 | 73
C-56-HC01-CMA18-1020 | Lowering | 1 | 1 | 2025-02-11 | 2025-02-11 | 2025-04-08 | 2025-04-09 | 73
C-56-HC01-CMA18-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-11 | 2025-02-12 | 2025-04-08 | 2025-04-10 | 73
C-56-HC01-CMA18-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-12 | 2025-02-13 | 2025-04-09 | 2025-04-11 | 88
C-56-HC01-CMA18-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-13 | 2025-02-14 | 2025-04-10 | 2025-04-12 | 88
C-56-HC01-CMA18-1060 | Holiday Testing | 1 | 1 | 2025-02-15 | 2025-02-15 | 2025-04-12 | 2025-04-14 | 88
C-56-HC01-CMA18-1070 | Padding | 1 | 1 | 2025-02-17 | 2025-02-17 | 2025-04-14 | 2025-04-15 | 88
Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) |  | 14 | 14 | 2025-02-11 | 2025-02-26 | 2025-04-08 | 2025-04-24 | 80
C-56-HC01-CMA19-1000 | Trench Excavation | 8 | 8 | 2025-02-11 | 2025-02-19 | 2025-04-08 | 2025-04-17 | 65
C-56-HC01-CMA19-1010 | Bedding | 1 | 1 | 2025-02-19 | 2025-02-19 | 2025-04-16 | 2025-04-17 | 65
C-56-HC01-CMA19-1020 | Lowering | 1 | 1 | 2025-02-20 | 2025-02-20 | 2025-04-17 | 2025-04-18 | 65
C-56-HC01-CMA19-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-20 | 2025-02-21 | 2025-04-17 | 2025-04-19 | 65
C-56-HC01-CMA19-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-21 | 2025-02-22 | 2025-04-18 | 2025-04-21 | 80
C-56-HC01-CMA19-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-22 | 2025-02-24 | 2025-04-19 | 2025-04-22 | 80
C-56-HC01-CMA19-1060 | Holiday Testing | 1 | 1 | 2025-02-25 | 2025-02-25 | 2025-04-22 | 2025-04-23 | 80
C-56-HC01-CMA19-1070 | Padding | 1 | 1 | 2025-02-26 | 2025-02-26 | 2025-04-23 | 2025-04-24 | 80
Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) |  | 18 | 18 | 2025-01-15 | 2025-02-04 | 2025-03-02 | 2025-03-29 | 99
C-56-HC01-CMA20-1000 | Trench Excavation | 12 | 12 | 2025-01-15 | 2025-01-28 | 2025-03-02 | 2025-03-20 | 60
C-56-HC01-CMA20-1010 | Bedding | 1 | 1 | 2025-01-28 | 2025-01-28 | 2025-03-19 | 2025-03-20 | 84
C-56-HC01-CMA20-1020 | Lowering | 1 | 1 | 2025-01-29 | 2025-01-29 | 2025-03-20 | 2025-03-22 | 84
C-56-HC01-CMA20-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-29 | 2025-01-30 | 2025-03-20 | 2025-03-23 | 84
C-56-HC01-CMA20-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-30 | 2025-01-31 | 2025-03-22 | 2025-03-24 | 99
C-56-HC01-CMA20-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-31 | 2025-02-01 | 2025-03-23 | 2025-03-26 | 99
C-56-HC01-CMA20-1060 | Holiday Testing | 1 | 1 | 2025-02-03 | 2025-02-03 | 2025-03-26 | 2025-03-28 | 99
C-56-HC01-CMA20-1070 | Padding | 1 | 1 | 2025-02-04 | 2025-02-04 | 2025-03-28 | 2025-03-29 | 99
Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) |  | 14 | 14 | 2025-01-29 | 2025-02-13 | 2025-03-20 | 2025-04-11 | 91
C-56-HC01-CMA21-1000 | Trench Excavation | 8 | 8 | 2025-01-29 | 2025-02-06 | 2025-03-20 | 2025-04-04 | 60
C-56-HC01-CMA21-1010 | Bedding | 1 | 1 | 2025-02-06 | 2025-02-06 | 2025-04-03 | 2025-04-04 | 76
C-56-HC01-CMA21-1020 | Lowering | 1 | 1 | 2025-02-07 | 2025-02-07 | 2025-04-04 | 2025-04-05 | 76
C-56-HC01-CMA21-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-07 | 2025-02-08 | 2025-04-04 | 2025-04-07 | 76
C-56-HC01-CMA21-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-08 | 2025-02-10 | 2025-04-05 | 2025-04-08 | 91
C-56-HC01-CMA21-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-10 | 2025-02-11 | 2025-04-07 | 2025-04-09 | 91
C-56-HC01-CMA21-1060 | Holiday Testing | 1 | 1 | 2025-02-12 | 2025-02-12 | 2025-04-09 | 2025-04-10 | 91
C-56-HC01-CMA21-1070 | Padding | 1 | 1 | 2025-02-13 | 2025-02-13 | 2025-04-10 | 2025-04-11 | 91
Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) |  | 14 | 14 | 2025-02-07 | 2025-02-22 | 2025-04-04 | 2025-04-21 | 83
C-56-HC01-CMA22-1000 | Trench Excavation | 8 | 8 | 2025-02-07 | 2025-02-15 | 2025-04-04 | 2025-04-14 | 60
C-56-HC01-CMA22-1010 | Bedding | 1 | 1 | 2025-02-15 | 2025-02-15 | 2025-04-12 | 2025-04-14 | 68
C-56-HC01-CMA22-1020 | Lowering | 1 | 1 | 2025-02-17 | 2025-02-17 | 2025-04-14 | 2025-04-15 | 68
C-56-HC01-CMA22-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-17 | 2025-02-18 | 2025-04-14 | 2025-04-16 | 68
C-56-HC01-CMA22-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-18 | 2025-02-19 | 2025-04-15 | 2025-04-17 | 83
C-56-HC01-CMA22-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-19 | 2025-02-20 | 2025-04-16 | 2025-04-18 | 83
C-56-HC01-CMA22-1060 | Holiday Testing | 1 | 1 | 2025-02-21 | 2025-02-21 | 2025-04-18 | 2025-04-19 | 83
C-56-HC01-CMA22-1070 | Padding | 1 | 1 | 2025-02-22 | 2025-02-22 | 2025-04-19 | 2025-04-21 | 83
Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) |  | 14 | 14 | 2025-02-17 | 2025-03-05 | 2025-04-14 | 2025-04-30 | 75
C-56-HC01-CMA23-1000 | Trench Excavation | 8 | 8 | 2025-02-17 | 2025-02-25 | 2025-04-14 | 2025-04-23 | 60
C-56-HC01-CMA23-1010 | Bedding | 1 | 1 | 2025-02-25 | 2025-02-25 | 2025-04-22 | 2025-04-23 | 60
C-56-HC01-CMA23-1020 | Lowering | 1 | 1 | 2025-02-26 | 2025-02-26 | 2025-04-23 | 2025-04-24 | 60
C-56-HC01-CMA23-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-26 | 2025-02-27 | 2025-04-23 | 2025-04-25 | 60
C-56-HC01-CMA23-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-27 | 2025-02-28 | 2025-04-24 | 2025-04-26 | 75
C-56-HC01-CMA23-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-28 | 2025-03-01 | 2025-04-25 | 2025-04-28 | 75
C-56-HC01-CMA23-1060 | Holiday Testing | 1 | 1 | 2025-03-02 | 2025-03-03 | 2025-04-28 | 2025-04-29 | 75
C-56-HC01-CMA23-1070 | Padding | 1 | 1 | 2025-03-03 | 2025-03-05 | 2025-04-29 | 2025-04-30 | 75
Open Cut - Rig / Track RoadCCOPL56221 |  | 56 | 56 | 2025-01-31 | 2025-05-05 | 2025-04-16 | 2025-06-24 | 31
Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) |  | 19 | 19 | 2025-01-31 | 2025-02-22 | 2025-04-16 | 2025-05-09 | 68
C-56-HC01-CME01-1000 | Trench Excavation | 2 | 2 | 2025-01-31 | 2025-02-03 | 2025-04-16 | 2025-04-18 | 17
C-56-HC01-CME01-1010 | Bedding | 2 | 2 | 2025-02-03 | 2025-02-05 | 2025-04-18 | 2025-04-21 | 59
C-56-HC01-CME01-1020 | Lowering | 2 | 2 | 2025-02-05 | 2025-02-07 | 2025-04-21 | 2025-04-23 | 59
C-56-HC01-CME01-1030 | Section Tie-in Welding | 3 | 3 | 2025-02-07 | 2025-02-11 | 2025-04-23 | 2025-04-26 | 59
C-56-HC01-CME01-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-02-11 | 2025-02-14 | 2025-04-26 | 2025-04-30 | 68
C-56-HC01-CME01-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-02-14 | 2025-02-18 | 2025-04-30 | 2025-05-03 | 68
C-56-HC01-CME01-1060 | Holiday Testing | 2 | 2 | 2025-02-18 | 2025-02-20 | 2025-05-03 | 2025-05-06 | 68
C-56-HC01-CME01-1070 | Padding & Back Filling | 2 | 2 | 2025-02-20 | 2025-02-22 | 2025-05-07 | 2025-05-09 | 68
Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) |  | 23 | 23 | 2025-02-07 | 2025-03-08 | 2025-04-23 | 2025-05-21 | 58
C-56-HC01-CME02-1000 | Trench Excavation | 4 | 4 | 2025-02-07 | 2025-02-12 | 2025-04-23 | 2025-04-28 | 17
C-56-HC01-CME02-1010 | Bedding | 4 | 4 | 2025-02-12 | 2025-02-17 | 2025-04-28 | 2025-05-02 | 45
C-56-HC01-CME02-1020 | Lowering | 4 | 4 | 2025-02-17 | 2025-02-21 | 2025-05-02 | 2025-05-08 | 45
C-56-HC01-CME02-1030 | Section Tie-in Welding | 5 | 5 | 2025-02-21 | 2025-02-27 | 2025-05-08 | 2025-05-14 | 45
C-56-HC01-CME02-1040 | NDT (Tie-in Joint) | 5 | 5 | 2025-02-22 | 2025-02-28 | 2025-05-09 | 2025-05-15 | 58
C-56-HC01-CME02-1050 | Ext. Joint Coating (Tie-in Joint) | 5 | 5 | 2025-02-24 | 2025-03-01 | 2025-05-10 | 2025-05-16 | 58
C-56-HC01-CME02-1060 | Holiday Testing | 2 | 2 | 2025-03-01 | 2025-03-05 | 2025-05-16 | 2025-05-19 | 58
C-56-HC01-CME02-1070 | Padding & Back Filling | 2 | 2 | 2025-03-05 | 2025-03-08 | 2025-05-19 | 2025-05-21 | 58
Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) |  | 19 | 19 | 2025-02-13 | 2025-03-09 | 2025-04-29 | 2025-05-22 | 57
C-56-HC01-CME03-1000 | Trench Excavation | 2 | 2 | 2025-02-13 | 2025-02-15 | 2025-04-29 | 2025-05-01 | 17
C-56-HC01-CME03-1010 | Bedding | 2 | 2 | 2025-02-15 | 2025-02-18 | 2025-05-01 | 2025-05-03 | 48
C-56-HC01-CME03-1020 | Lowering | 2 | 2 | 2025-02-18 | 2025-02-20 | 2025-05-03 | 2025-05-06 | 48
C-56-HC01-CME03-1030 | Section Tie-in Welding | 3 | 3 | 2025-02-20 | 2025-02-24 | 2025-05-07 | 2025-05-10 | 48
C-56-HC01-CME03-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-02-24 | 2025-02-27 | 2025-05-10 | 2025-05-14 | 57
C-56-HC01-CME03-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-02-27 | 2025-03-03 | 2025-05-14 | 2025-05-17 | 57
C-56-HC01-CME03-1060 | Holiday Testing | 2 | 2 | 2025-03-03 | 2025-03-06 | 2025-05-17 | 2025-05-20 | 57
C-56-HC01-CME03-1070 | Padding & Back Filling | 2 | 2 | 2025-03-06 | 2025-03-09 | 2025-05-20 | 2025-05-22 | 57
Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) |  | 19 | 19 | 2025-02-17 | 2025-03-14 | 2025-05-02 | 2025-05-26 | 54
C-56-HC01-CME04-1000 | Trench Excavation | 2 | 2 | 2025-02-17 | 2025-02-19 | 2025-05-02 | 2025-05-05 | 17
C-56-HC01-CME04-1010 | Bedding | 2 | 2 | 2025-02-19 | 2025-02-21 | 2025-05-05 | 2025-05-08 | 45
C-56-HC01-CME04-1020 | Lowering | 2 | 2 | 2025-02-21 | 2025-02-24 | 2025-05-08 | 2025-05-10 | 45
C-56-HC01-CME04-1030 | Section Tie-in Welding | 3 | 3 | 2025-02-24 | 2025-02-27 | 2025-05-10 | 2025-05-14 | 45
C-56-HC01-CME04-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-02-27 | 2025-03-03 | 2025-05-14 | 2025-05-17 | 54
C-56-HC01-CME04-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-03-03 | 2025-03-08 | 2025-05-17 | 2025-05-21 | 54
C-56-HC01-CME04-1060 | Holiday Testing | 2 | 2 | 2025-03-08 | 2025-03-11 | 2025-05-21 | 2025-05-23 | 54
C-56-HC01-CME04-1070 | Padding & Back Filling | 2 | 2 | 2025-03-11 | 2025-03-14 | 2025-05-23 | 2025-05-26 | 54
Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) |  | 19 | 19 | 2025-02-20 | 2025-03-18 | 2025-05-07 | 2025-05-29 | 51
C-56-HC01-CME05-1000 | Trench Excavation | 2 | 2 | 2025-02-20 | 2025-02-22 | 2025-05-07 | 2025-05-09 | 17
C-56-HC01-CME05-1010 | Bedding | 2 | 2 | 2025-02-22 | 2025-02-25 | 2025-05-09 | 2025-05-12 | 42
C-56-HC01-CME05-1020 | Lowering | 2 | 2 | 2025-02-25 | 2025-02-27 | 2025-05-12 | 2025-05-14 | 42
C-56-HC01-CME05-1030 | Section Tie-in Welding | 3 | 3 | 2025-02-27 | 2025-03-03 | 2025-05-14 | 2025-05-17 | 42
C-56-HC01-CME05-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-03-03 | 2025-03-08 | 2025-05-17 | 2025-05-21 | 51
C-56-HC01-CME05-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-03-08 | 2025-03-12 | 2025-05-21 | 2025-05-24 | 51
C-56-HC01-CME05-1060 | Holiday Testing | 2 | 2 | 2025-03-12 | 2025-03-15 | 2025-05-24 | 2025-05-27 | 51
C-56-HC01-CME05-1070 | Padding & Back Filling | 2 | 2 | 2025-03-15 | 2025-03-18 | 2025-05-27 | 2025-05-29 | 51
Crossing Mechanical @ KP 6+063 (TX-11) |  | 19 | 19 | 2025-02-24 | 2025-03-23 | 2025-05-10 | 2025-06-02 | 48
C-56-HC01-CME06-1000 | Trench Excavation | 2 | 2 | 2025-02-24 | 2025-02-26 | 2025-05-10 | 2025-05-13 | 17
C-56-HC01-CME06-1010 | Bedding | 2 | 2 | 2025-02-26 | 2025-02-28 | 2025-05-13 | 2025-05-15 | 39
C-56-HC01-CME06-1020 | Lowering | 2 | 2 | 2025-02-28 | 2025-03-03 | 2025-05-15 | 2025-05-17 | 39
C-56-HC01-CME06-1030 | Section Tie-in Welding | 3 | 3 | 2025-03-03 | 2025-03-08 | 2025-05-17 | 2025-05-21 | 39
C-56-HC01-CME06-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-03-08 | 2025-03-12 | 2025-05-21 | 2025-05-24 | 48
C-56-HC01-CME06-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-03-12 | 2025-03-17 | 2025-05-24 | 2025-05-28 | 48
C-56-HC01-CME06-1060 | Holiday Testing | 2 | 2 | 2025-03-17 | 2025-03-20 | 2025-05-28 | 2025-05-30 | 48
C-56-HC01-CME06-1070 | Padding & Back Filling | 2 | 2 | 2025-03-20 | 2025-03-23 | 2025-05-30 | 2025-06-02 | 48
Crossing Mechanical @ KP 6+288 (TX-12) |  | 19 | 19 | 2025-02-27 | 2025-03-28 | 2025-05-14 | 2025-06-07 | 45
C-56-HC01-CME07-1000 | Trench Excavation | 2 | 2 | 2025-02-27 | 2025-03-01 | 2025-05-14 | 2025-05-16 | 22
C-56-HC01-CME07-1010 | Bedding | 2 | 2 | 2025-03-01 | 2025-03-05 | 2025-05-16 | 2025-05-19 | 36
C-56-HC01-CME07-1020 | Lowering | 2 | 2 | 2025-03-05 | 2025-03-08 | 2025-05-19 | 2025-05-21 | 36
C-56-HC01-CME07-1030 | Section Tie-in Welding | 3 | 3 | 2025-03-08 | 2025-03-12 | 2025-05-21 | 2025-05-24 | 36
C-56-HC01-CME07-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-03-12 | 2025-03-17 | 2025-05-24 | 2025-05-28 | 45
C-56-HC01-CME07-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-03-17 | 2025-03-22 | 2025-05-28 | 2025-05-31 | 45
C-56-HC01-CME07-1060 | Holiday Testing | 2 | 2 | 2025-03-22 | 2025-03-24 | 2025-05-31 | 2025-06-03 | 45
C-56-HC01-CME07-1070 | Padding & Back Filling | 2 | 2 | 2025-03-24 | 2025-03-28 | 2025-06-03 | 2025-06-07 | 45
Crossing Mechanical @ KP 6+869 (TX-13) |  | 20 | 20 | 2025-03-03 | 2025-04-05 | 2025-05-17 | 2025-06-12 | 41
C-56-HC01-CME08-1000 | Trench Excavation | 4 | 4 | 2025-03-03 | 2025-03-09 | 2025-05-17 | 2025-05-22 | 22
C-56-HC01-CME08-1010 | Bedding | 4 | 4 | 2025-03-09 | 2025-03-15 | 2025-05-22 | 2025-05-27 | 28
C-56-HC01-CME08-1020 | Lowering | 4 | 4 | 2025-03-15 | 2025-03-22 | 2025-05-27 | 2025-05-31 | 28
C-56-HC01-CME08-1030 | Section Tie-in Welding | 5 | 5 | 2025-03-17 | 2025-03-24 | 2025-05-28 | 2025-06-03 | 28
C-56-HC01-CME08-1040 | NDT (Tie-in Joint) | 5 | 5 | 2025-03-18 | 2025-03-26 | 2025-05-29 | 2025-06-04 | 41
C-56-HC01-CME08-1050 | Ext. Joint Coating (Tie-in Joint) | 5 | 5 | 2025-03-20 | 2025-03-28 | 2025-05-30 | 2025-06-07 | 41
C-56-HC01-CME08-1060 | Holiday Testing | 2 | 2 | 2025-03-28 | 2025-04-03 | 2025-06-07 | 2025-06-10 | 41
C-56-HC01-CME08-1070 | Padding & Back Filling | 2 | 2 | 2025-04-03 | 2025-04-05 | 2025-06-10 | 2025-06-12 | 41
Crossing Mechanical @ KP 9+004 (TX-14) |  | 19 | 19 | 2025-03-11 | 2025-04-10 | 2025-05-23 | 2025-06-17 | 37
C-56-HC01-CME09-1000 | Trench Excavation | 2 | 2 | 2025-03-11 | 2025-03-14 | 2025-05-23 | 2025-05-26 | 22
C-56-HC01-CME09-1010 | Bedding | 2 | 2 | 2025-03-14 | 2025-03-17 | 2025-05-26 | 2025-05-28 | 28
C-56-HC01-CME09-1020 | Lowering | 2 | 2 | 2025-03-17 | 2025-03-20 | 2025-05-28 | 2025-05-30 | 28
C-56-HC01-CME09-1030 | Section Tie-in Welding | 3 | 3 | 2025-03-20 | 2025-03-24 | 2025-05-30 | 2025-06-03 | 28
C-56-HC01-CME09-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-03-24 | 2025-03-29 | 2025-06-03 | 2025-06-09 | 37
C-56-HC01-CME09-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-03-29 | 2025-04-05 | 2025-06-09 | 2025-06-12 | 37
C-56-HC01-CME09-1060 | Holiday Testing | 2 | 2 | 2025-04-05 | 2025-04-08 | 2025-06-12 | 2025-06-14 | 37
C-56-HC01-CME09-1070 | Padding & Back Filling | 2 | 2 | 2025-04-08 | 2025-04-10 | 2025-06-14 | 2025-06-17 | 37
Crossing Mechanical @ KP 10+019 (TX-15) |  | 19 | 19 | 2025-03-15 | 2025-04-14 | 2025-05-27 | 2025-06-20 | 34
C-56-HC01-CME10-1000 | Trench Excavation | 2 | 2 | 2025-03-15 | 2025-03-18 | 2025-05-27 | 2025-05-29 | 22
C-56-HC01-CME10-1010 | Bedding | 2 | 2 | 2025-03-18 | 2025-03-22 | 2025-05-29 | 2025-05-31 | 25
C-56-HC01-CME10-1020 | Lowering | 2 | 2 | 2025-03-22 | 2025-03-24 | 2025-05-31 | 2025-06-03 | 25
C-56-HC01-CME10-1030 | Section Tie-in Welding | 3 | 3 | 2025-03-24 | 2025-03-29 | 2025-06-03 | 2025-06-09 | 25
C-56-HC01-CME10-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-03-29 | 2025-04-05 | 2025-06-09 | 2025-06-12 | 34
C-56-HC01-CME10-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-04-05 | 2025-04-09 | 2025-06-12 | 2025-06-16 | 34
C-56-HC01-CME10-1060 | Holiday Testing | 2 | 2 | 2025-04-09 | 2025-04-11 | 2025-06-16 | 2025-06-18 | 34
C-56-HC01-CME10-1070 | Padding & Back Filling | 2 | 2 | 2025-04-11 | 2025-04-14 | 2025-06-18 | 2025-06-20 | 34
Crossing Mechanical @ KP 10+466 (TX-16) |  | 19 | 19 | 2025-03-20 | 2025-04-17 | 2025-05-30 | 2025-06-24 | 31
C-56-HC01-CME11-1000 | Trench Excavation | 2 | 2 | 2025-03-20 | 2025-03-23 | 2025-05-30 | 2025-06-02 | 22
C-56-HC01-CME11-1010 | Bedding | 2 | 2 | 2025-03-23 | 2025-03-26 | 2025-06-02 | 2025-06-04 | 22
C-56-HC01-CME11-1020 | Lowering | 2 | 2 | 2025-03-26 | 2025-03-29 | 2025-06-04 | 2025-06-09 | 22
C-56-HC01-CME11-1030 | Section Tie-in Welding | 3 | 3 | 2025-03-29 | 2025-04-05 | 2025-06-09 | 2025-06-12 | 22
C-56-HC01-CME11-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-04-05 | 2025-04-09 | 2025-06-12 | 2025-06-16 | 31
C-56-HC01-CME11-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-04-09 | 2025-04-12 | 2025-06-16 | 2025-06-19 | 31
C-56-HC01-CME11-1060 | Holiday Testing | 2 | 2 | 2025-04-12 | 2025-04-15 | 2025-06-19 | 2025-06-21 | 31
C-56-HC01-CME11-1070 | Padding & Back Filling | 2 | 2 | 2025-04-15 | 2025-04-17 | 2025-06-21 | 2025-06-24 | 31
Crossing Mechanical @ KP 10+930 (TX-17) |  | 19 | 19 | 2025-03-24 | 2025-04-21 | 2025-05-13 | 2025-06-04 | 46
C-56-HC01-CME12-1000 | Trench Excavation | 2 | 2 | 2025-03-24 | 2025-03-28 | 2025-05-13 | 2025-05-15 | 17
C-56-HC01-CME12-1010 | Bedding | 2 | 2 | 2025-03-28 | 2025-04-03 | 2025-05-15 | 2025-05-17 | 37
C-56-HC01-CME12-1020 | Lowering | 2 | 2 | 2025-04-03 | 2025-04-05 | 2025-05-17 | 2025-05-20 | 37
C-56-HC01-CME12-1030 | Section Tie-in Welding | 3 | 3 | 2025-04-05 | 2025-04-09 | 2025-05-20 | 2025-05-23 | 37
C-56-HC01-CME12-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-04-09 | 2025-04-12 | 2025-05-23 | 2025-05-27 | 46
C-56-HC01-CME12-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-04-12 | 2025-04-16 | 2025-05-27 | 2025-05-30 | 46
C-56-HC01-CME12-1060 | Holiday Testing | 2 | 2 | 2025-04-16 | 2025-04-18 | 2025-05-30 | 2025-06-02 | 46
C-56-HC01-CME12-1070 | Padding & Back Filling | 2 | 2 | 2025-04-18 | 2025-04-21 | 2025-06-02 | 2025-06-04 | 46
Crossing Mechanical @ KP 11+193 (TX-18) |  | 19 | 19 | 2025-03-29 | 2025-04-24 | 2025-05-16 | 2025-06-10 | 43
C-56-HC01-CME13-1000 | Trench Excavation | 2 | 2 | 2025-03-29 | 2025-04-04 | 2025-05-16 | 2025-05-19 | 17
C-56-HC01-CME13-1010 | Bedding | 2 | 2 | 2025-04-04 | 2025-04-07 | 2025-05-19 | 2025-05-21 | 34
C-56-HC01-CME13-1020 | Lowering | 2 | 2 | 2025-04-07 | 2025-04-09 | 2025-05-21 | 2025-05-23 | 34
C-56-HC01-CME13-1030 | Section Tie-in Welding | 3 | 3 | 2025-04-09 | 2025-04-12 | 2025-05-23 | 2025-05-27 | 34
C-56-HC01-CME13-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-04-12 | 2025-04-16 | 2025-05-27 | 2025-05-30 | 43
C-56-HC01-CME13-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-04-16 | 2025-04-19 | 2025-05-30 | 2025-06-03 | 43
C-56-HC01-CME13-1060 | Holiday Testing | 2 | 2 | 2025-04-19 | 2025-04-22 | 2025-06-03 | 2025-06-07 | 43
C-56-HC01-CME13-1070 | Padding & Back Filling | 2 | 2 | 2025-04-22 | 2025-04-24 | 2025-06-07 | 2025-06-10 | 43
Crossing Mechanical @ KP 11+615 (TX-19) |  | 19 | 19 | 2025-04-05 | 2025-04-28 | 2025-05-20 | 2025-06-13 | 40
C-56-HC01-CME14-1000 | Trench Excavation | 2 | 2 | 2025-04-05 | 2025-04-08 | 2025-05-20 | 2025-05-22 | 17
C-56-HC01-CME14-1010 | Bedding | 2 | 2 | 2025-04-08 | 2025-04-10 | 2025-05-22 | 2025-05-24 | 31
C-56-HC01-CME14-1020 | Lowering | 2 | 2 | 2025-04-10 | 2025-04-12 | 2025-05-24 | 2025-05-27 | 31
C-56-HC01-CME14-1030 | Section Tie-in Welding | 3 | 3 | 2025-04-12 | 2025-04-16 | 2025-05-27 | 2025-05-30 | 31
C-56-HC01-CME14-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-04-16 | 2025-04-19 | 2025-05-30 | 2025-06-03 | 40
C-56-HC01-CME14-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-04-19 | 2025-04-23 | 2025-06-03 | 2025-06-09 | 40
C-56-HC01-CME14-1060 | Holiday Testing | 2 | 2 | 2025-04-23 | 2025-04-25 | 2025-06-09 | 2025-06-11 | 40
C-56-HC01-CME14-1070 | Padding & Back Filling | 2 | 2 | 2025-04-25 | 2025-04-28 | 2025-06-11 | 2025-06-13 | 40
Crossing Mechanical @ KP 11+803 (TX-20) |  | 19 | 19 | 2025-04-09 | 2025-05-01 | 2025-05-23 | 2025-06-17 | 37
C-56-HC01-CME15-1000 | Trench Excavation | 2 | 2 | 2025-04-09 | 2025-04-11 | 2025-05-23 | 2025-05-26 | 17
C-56-HC01-CME15-1010 | Bedding | 2 | 2 | 2025-04-11 | 2025-04-14 | 2025-05-26 | 2025-05-28 | 28
C-56-HC01-CME15-1020 | Lowering | 2 | 2 | 2025-04-14 | 2025-04-16 | 2025-05-28 | 2025-05-30 | 28
C-56-HC01-CME15-1030 | Section Tie-in Welding | 3 | 3 | 2025-04-16 | 2025-04-19 | 2025-05-30 | 2025-06-03 | 28
C-56-HC01-CME15-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-04-19 | 2025-04-23 | 2025-06-03 | 2025-06-09 | 37
C-56-HC01-CME15-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-04-23 | 2025-04-26 | 2025-06-09 | 2025-06-12 | 37
C-56-HC01-CME15-1060 | Holiday Testing | 2 | 2 | 2025-04-26 | 2025-04-29 | 2025-06-12 | 2025-06-14 | 37
C-56-HC01-CME15-1070 | Padding & Back Filling | 2 | 2 | 2025-04-29 | 2025-05-01 | 2025-06-14 | 2025-06-17 | 37
Crossing Mechanical @ KP 12+058 (TX-21) |  | 19 | 19 | 2025-04-12 | 2025-05-05 | 2025-05-27 | 2025-06-20 | 34
C-56-HC01-CME16-1000 | Trench Excavation | 2 | 2 | 2025-04-12 | 2025-04-15 | 2025-05-27 | 2025-05-29 | 17
C-56-HC01-CME16-1010 | Bedding | 2 | 2 | 2025-04-15 | 2025-04-17 | 2025-05-29 | 2025-05-31 | 25
C-56-HC01-CME16-1020 | Lowering | 2 | 2 | 2025-04-17 | 2025-04-19 | 2025-05-31 | 2025-06-03 | 25
C-56-HC01-CME16-1030 | Section Tie-in Welding | 3 | 3 | 2025-04-19 | 2025-04-23 | 2025-06-03 | 2025-06-09 | 25
C-56-HC01-CME16-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-04-23 | 2025-04-26 | 2025-06-09 | 2025-06-12 | 34
C-56-HC01-CME16-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-04-26 | 2025-04-30 | 2025-06-12 | 2025-06-16 | 34
C-56-HC01-CME16-1060 | Holiday Testing | 2 | 2 | 2025-04-30 | 2025-05-02 | 2025-06-16 | 2025-06-18 | 34
C-56-HC01-CME16-1070 | Padding & Back Filling | 2 | 2 | 2025-05-02 | 2025-05-05 | 2025-06-18 | 2025-06-20 | 34
Crossings - AG PipeCCOPL56220 |  | 37 | 37 | 2025-01-14 | 2025-02-25 | 2025-03-01 | 2025-04-23 | 81
Crossing Manual @ KP 7+860 (PX-69) |  | 14 | 14 | 2025-01-14 | 2025-01-29 | 2025-03-01 | 2025-03-22 | 104
C-56-HC01-CMA24-1000 | Trench Excavation | 8 | 8 | 2025-01-14 | 2025-01-22 | 2025-03-01 | 2025-03-12 | 67
C-56-HC01-CMA24-1010 | Bedding | 1 | 1 | 2025-01-22 | 2025-01-22 | 2025-03-11 | 2025-03-12 | 89
C-56-HC01-CMA24-1020 | Lowering | 1 | 1 | 2025-01-23 | 2025-01-23 | 2025-03-13 | 2025-03-14 | 89
C-56-HC01-CMA24-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-23 | 2025-01-24 | 2025-03-13 | 2025-03-15 | 89
C-56-HC01-CMA24-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-24 | 2025-01-25 | 2025-03-14 | 2025-03-17 | 104
C-56-HC01-CMA24-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-25 | 2025-01-27 | 2025-03-15 | 2025-03-18 | 104
C-56-HC01-CMA24-1060 | Holiday Testing | 1 | 1 | 2025-01-28 | 2025-01-28 | 2025-03-19 | 2025-03-20 | 104
C-56-HC01-CMA24-1070 | Padding | 1 | 1 | 2025-01-29 | 2025-01-29 | 2025-03-20 | 2025-03-22 | 104
Crossing Manual @ KP 7+488 (PX-68) |  | 14 | 14 | 2025-01-23 | 2025-02-07 | 2025-03-13 | 2025-04-05 | 96
C-56-HC01-CMA25-1000 | Trench Excavation | 8 | 8 | 2025-01-23 | 2025-01-31 | 2025-03-13 | 2025-03-24 | 67
C-56-HC01-CMA25-1010 | Bedding | 1 | 1 | 2025-01-31 | 2025-01-31 | 2025-03-23 | 2025-03-24 | 81
C-56-HC01-CMA25-1020 | Lowering | 1 | 1 | 2025-02-01 | 2025-02-01 | 2025-03-25 | 2025-03-26 | 81
C-56-HC01-CMA25-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-01 | 2025-02-03 | 2025-03-25 | 2025-03-28 | 81
C-56-HC01-CMA25-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-03 | 2025-02-04 | 2025-03-26 | 2025-03-29 | 96
C-56-HC01-CMA25-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-04 | 2025-02-05 | 2025-03-28 | 2025-04-03 | 96
C-56-HC01-CMA25-1060 | Holiday Testing | 1 | 1 | 2025-02-06 | 2025-02-06 | 2025-04-03 | 2025-04-04 | 96
C-56-HC01-CMA25-1070 | Padding | 1 | 1 | 2025-02-07 | 2025-02-07 | 2025-04-04 | 2025-04-05 | 96
Crossing Manual @ KP 6+992 (PX-62) |  | 21 | 21 | 2025-02-01 | 2025-02-25 | 2025-03-25 | 2025-04-23 | 81
C-56-HC01-CMA26-1000 | Trench Excavation | 12 | 12 | 2025-02-01 | 2025-02-14 | 2025-03-25 | 2025-04-12 | 67
C-56-HC01-CMA26-1010 | Bedding | 2 | 2 | 2025-02-13 | 2025-02-14 | 2025-04-10 | 2025-04-12 | 67
C-56-HC01-CMA26-1020 | Lowering | 2 | 2 | 2025-02-15 | 2025-02-17 | 2025-04-12 | 2025-04-15 | 67
C-56-HC01-CMA26-1030 | Section Tie-in Welding | 4 | 4 | 2025-02-15 | 2025-02-19 | 2025-04-12 | 2025-04-17 | 67
C-56-HC01-CMA26-1040 | NDT (Tie-in Joint) | 4 | 4 | 2025-02-17 | 2025-02-20 | 2025-04-14 | 2025-04-18 | 81
C-56-HC01-CMA26-1050 | Ext. Joint Coating (Tie-in Joint) | 4 | 4 | 2025-02-18 | 2025-02-21 | 2025-04-15 | 2025-04-19 | 81
C-56-HC01-CMA26-1060 | Holiday Testing | 1 | 1 | 2025-02-22 | 2025-02-22 | 2025-04-19 | 2025-04-21 | 81
C-56-HC01-CMA26-1070 | Padding | 2 | 2 | 2025-02-24 | 2025-02-25 | 2025-04-21 | 2025-04-23 | 81
Crossings - FenceCCOPL56223 |  | 38 | 38 | 2025-01-14 | 2025-02-26 | 2025-03-01 | 2025-04-24 | 80
Crossing Manual @ KP 8+800 (FX-01) |  | 24 | 24 | 2025-01-14 | 2025-02-10 | 2025-03-01 | 2025-04-08 | 94
C-56-HC01-CMA27-1000 | Trench Excavation | 15 | 15 | 2025-01-14 | 2025-01-30 | 2025-03-01 | 2025-03-23 | 66
C-56-HC01-CMA27-1010 | Bedding | 1 | 1 | 2025-01-30 | 2025-01-30 | 2025-03-22 | 2025-03-23 | 80
C-56-HC01-CMA27-1020 | Lowering | 2 | 2 | 2025-01-31 | 2025-02-01 | 2025-03-23 | 2025-03-26 | 80
C-56-HC01-CMA27-1030 | Section Tie-in Welding | 4 | 4 | 2025-01-31 | 2025-02-04 | 2025-03-23 | 2025-03-29 | 80
C-56-HC01-CMA27-1040 | NDT (Tie-in Joint) | 4 | 4 | 2025-02-01 | 2025-02-05 | 2025-03-25 | 2025-04-03 | 94
C-56-HC01-CMA27-1050 | Ext. Joint Coating (Tie-in Joint) | 4 | 4 | 2025-02-03 | 2025-02-06 | 2025-03-26 | 2025-04-04 | 94
C-56-HC01-CMA27-1060 | Holiday Testing | 1 | 1 | 2025-02-07 | 2025-02-07 | 2025-04-04 | 2025-04-05 | 94
C-56-HC01-CMA27-1070 | Padding | 2 | 2 | 2025-02-08 | 2025-02-10 | 2025-04-05 | 2025-04-08 | 94
Crossing Manual @ KP 8+917 (FX-02) |  | 14 | 14 | 2025-01-22 | 2025-02-06 | 2025-03-11 | 2025-04-04 | 97
C-56-HC01-CMA28-1000 | Trench Excavation | 8 | 8 | 2025-01-22 | 2025-01-30 | 2025-03-11 | 2025-03-23 | 66
C-56-HC01-CMA28-1010 | Bedding | 1 | 1 | 2025-01-30 | 2025-01-30 | 2025-03-22 | 2025-03-23 | 82
C-56-HC01-CMA28-1020 | Lowering | 1 | 1 | 2025-01-31 | 2025-01-31 | 2025-03-23 | 2025-03-24 | 82
C-56-HC01-CMA28-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-31 | 2025-02-01 | 2025-03-23 | 2025-03-26 | 82
C-56-HC01-CMA28-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-01 | 2025-02-03 | 2025-03-25 | 2025-03-28 | 97
C-56-HC01-CMA28-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-03 | 2025-02-04 | 2025-03-26 | 2025-03-29 | 97
C-56-HC01-CMA28-1060 | Holiday Testing | 1 | 1 | 2025-02-05 | 2025-02-05 | 2025-03-29 | 2025-04-03 | 97
C-56-HC01-CMA28-1070 | Padding | 1 | 1 | 2025-02-06 | 2025-02-06 | 2025-04-03 | 2025-04-04 | 97
Crossing Manual @ KP 8+829, KP8+888 (Culvert) |  | 23 | 23 | 2025-01-31 | 2025-02-26 | 2025-03-23 | 2025-04-24 | 80
C-56-HC01-CMA29-1000 | Trench Excavation | 12 | 12 | 2025-01-31 | 2025-02-13 | 2025-03-23 | 2025-04-11 | 66
C-56-HC01-CMA29-1010 | Bedding | 1 | 1 | 2025-02-13 | 2025-02-13 | 2025-04-10 | 2025-04-11 | 66
C-56-HC01-CMA29-1020 | Lowering | 2 | 2 | 2025-02-14 | 2025-02-15 | 2025-04-11 | 2025-04-14 | 66
C-56-HC01-CMA29-1030 | Section Tie-in Welding | 6 | 6 | 2025-02-14 | 2025-02-20 | 2025-04-11 | 2025-04-18 | 66
C-56-HC01-CMA29-1040 | NDT (Tie-in Joint) | 6 | 6 | 2025-02-15 | 2025-02-21 | 2025-04-12 | 2025-04-19 | 80
C-56-HC01-CMA29-1050 | Ext. Joint Coating (Tie-in Joint) | 6 | 6 | 2025-02-17 | 2025-02-22 | 2025-04-14 | 2025-04-21 | 80
C-56-HC01-CMA29-1060 | Holiday Testing | 1 | 1 | 2025-02-24 | 2025-02-24 | 2025-04-21 | 2025-04-22 | 80
C-56-HC01-CMA29-1070 | Padding | 2 | 2 | 2025-02-25 | 2025-02-26 | 2025-04-22 | 2025-04-24 | 80
Crossings OHPLCCOPL56224 |  | 20 | 20 | 2025-01-14 | 2025-02-05 | 2025-03-01 | 2025-04-03 | 98
Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) |  | 12 | 12 | 2025-01-14 | 2025-01-27 | 2025-03-01 | 2025-03-18 | 106
C-56-HC01-CMA30-1000 | Trench Excavation | 6 | 6 | 2025-01-14 | 2025-01-20 | 2025-03-01 | 2025-03-09 | 83
C-56-HC01-CMA30-1010 | Bedding | 1 | 1 | 2025-01-20 | 2025-01-20 | 2025-03-08 | 2025-03-09 | 91
C-56-HC01-CMA30-1020 | Lowering | 1 | 1 | 2025-01-21 | 2025-01-21 | 2025-03-09 | 2025-03-11 | 91
C-56-HC01-CMA30-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-21 | 2025-01-22 | 2025-03-09 | 2025-03-12 | 91
C-56-HC01-CMA30-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-22 | 2025-01-23 | 2025-03-11 | 2025-03-14 | 106
C-56-HC01-CMA30-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-23 | 2025-01-24 | 2025-03-13 | 2025-03-15 | 106
C-56-HC01-CMA30-1060 | Holiday Testing | 1 | 1 | 2025-01-25 | 2025-01-25 | 2025-03-15 | 2025-03-17 | 106
C-56-HC01-CMA30-1070 | Padding | 1 | 1 | 2025-01-27 | 2025-01-27 | 2025-03-17 | 2025-03-18 | 106
Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) |  | 14 | 14 | 2025-01-21 | 2025-02-05 | 2025-03-09 | 2025-04-03 | 98
C-56-HC01-CMA31-1000 | Trench Excavation | 8 | 8 | 2025-01-21 | 2025-01-29 | 2025-03-09 | 2025-03-22 | 83
C-56-HC01-CMA31-1010 | Bedding | 1 | 1 | 2025-01-29 | 2025-01-29 | 2025-03-20 | 2025-03-22 | 83
C-56-HC01-CMA31-1020 | Lowering | 1 | 1 | 2025-01-30 | 2025-01-30 | 2025-03-22 | 2025-03-23 | 83
C-56-HC01-CMA31-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-30 | 2025-01-31 | 2025-03-22 | 2025-03-24 | 83
C-56-HC01-CMA31-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-31 | 2025-02-01 | 2025-03-23 | 2025-03-26 | 98
C-56-HC01-CMA31-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-01 | 2025-02-03 | 2025-03-25 | 2025-03-28 | 98
C-56-HC01-CMA31-1060 | Holiday Testing | 1 | 1 | 2025-02-04 | 2025-02-04 | 2025-03-28 | 2025-03-29 | 98
C-56-HC01-CMA31-1070 | Padding | 1 | 1 | 2025-02-05 | 2025-02-05 | 2025-03-29 | 2025-04-03 | 98
CP Works from Habshan complex to KP 6CCOP56EL21.1 |  | 87 | 87 | 2025-04-10 | 2025-05-13 | 2025-05-14 | 2025-08-27 | 25
C-56-HC01-PL-CA-5200 | Installation of CP Test Post | 20 | 20 | 2025-04-10 | 2025-05-03 | 2025-05-14 | 2025-06-09 | 70
C-56-HC01-PL-CA-5210 | Glanding & Termination of Temp. CP S/m | 2 | 2 | 2025-05-03 | 2025-05-06 | 2025-06-09 | 2025-06-11 | 86
C-56-HC01-PL-CA-5220 | Installation of Test Post for Crossing | 15 | 15 | 2025-04-11 | 2025-05-05 | 2025-08-02 | 2025-08-20 | 19
C-56-HC01-PL-CA-5230 | Installation of CP JB's | 15 | 15 | 2025-04-12 | 2025-05-06 | 2025-08-04 | 2025-08-21 | 19
C-56-HC01-PL-CA-5240 | Installation of CP TR | 15 | 15 | 2025-04-14 | 2025-05-08 | 2025-08-05 | 2025-08-22 | 19
C-56-HC01-PL-CA-5250 | CIP/DCVG Survey | 4 | 4 | 2025-05-08 | 2025-05-13 | 2025-08-22 | 2025-08-27 | 25
CP Works from KP 6 to KP 12.6CCOP56EL21.2 |  | 75 | 75 | 2025-05-07 | 2025-06-11 | 2025-06-10 | 2025-09-08 | 19
C-56-HC01-PL-CA-5430 | Installation of CP Test Post | 20 | 20 | 2025-05-10 | 2025-06-03 | 2025-06-10 | 2025-07-04 | 69
C-56-HC01-PL-CA-5440 | Glanding & Termination of Temp. CP S/m | 2 | 2 | 2025-06-03 | 2025-06-07 | 2025-07-04 | 2025-07-07 | 69
C-56-HC01-PL-CA-5400 | Installation of Test Post for Crossing | 10 | 10 | 2025-05-07 | 2025-05-30 | 2025-08-20 | 2025-09-01 | 19
C-56-HC01-PL-CA-5410 | Installation of CP JB's | 10 | 10 | 2025-05-08 | 2025-05-31 | 2025-08-21 | 2025-09-02 | 19
C-56-HC01-PL-CA-5420 | Installation of CP TR | 10 | 10 | 2025-05-09 | 2025-06-02 | 2025-08-22 | 2025-09-03 | 19
C-56-HC01-PL-CA-5450 | CIP/DCVG Survey | 3 | 3 | 2025-06-07 | 2025-06-11 | 2025-09-03 | 2025-09-08 | 19
Test Stations & Anode Beds from Habshan complex to KP 6CCOP56EL22.1 |  | 20 | 20 | 2025-04-09 | 2025-05-02 | 2025-05-13 | 2025-06-07 | 26
C-56-HC01-PL-CA-5600 | Installation of Temp. Anode | 20 | 20 | 2025-04-09 | 2025-05-02 | 2025-05-13 | 2025-06-07 | 26
Test Stations & Anode Beds from KP 6 to KP 12.6CCOP56EL22.2 |  | 20 | 20 | 2025-05-09 | 2025-06-02 | 2025-06-09 | 2025-07-03 | 20
C-56-HC01-PL-CA-5800 | Installation of Temp. Anode | 20 | 20 | 2025-05-09 | 2025-06-02 | 2025-06-09 | 2025-07-03 | 20
Padding from Habshan complex to KP 6CCOPL56211.1 |  | 20 | 20 | 2025-04-09 | 2025-05-02 | 2025-05-13 | 2025-06-07 | 26
C-56-HC01-PL-CI-6000 | Padding | 20 | 20 | 2025-04-09 | 2025-05-02 | 2025-05-13 | 2025-06-07 | 26
Padding from KP 6 to KP 12.6CCOPL56211.2 |  | 20 | 20 | 2025-05-09 | 2025-06-02 | 2025-06-12 | 2025-07-07 | 17
C-56-HC01-PL-CI-6200 | Padding | 20 | 20 | 2025-05-09 | 2025-06-02 | 2025-06-12 | 2025-07-07 | 17
Backfilling from Habshan complex to KP 6CCOPL56217.1 |  | 20 | 20 | 2025-05-02 | 2025-05-27 | 2025-06-07 | 2025-07-02 | 26
C-56-HC01-PL-CI-6400 | Backfilling from Habshan complex to KP 6 | 20 | 20 | 2025-05-02 | 2025-05-27 | 2025-06-07 | 2025-07-02 | 26
Backfilling from KP 6 to KP 12.6CCOPL56217.2 |  | 20 | 20 | 2025-05-19 | 2025-06-13 | 2025-06-21 | 2025-07-16 | 17
C-56-HC01-PL-CI-6600 | Backfilling from KP 6 to KP 12.6 | 20 | 20 | 2025-05-19 | 2025-06-13 | 2025-06-21 | 2025-07-16 | 17
Berming from Habshan complex to KP 6CCOPL56218.1 |  | 47 | 47 | 2025-05-12 | 2025-07-09 | 2025-06-21 | 2025-08-16 | 37
C-56-HC01-PL-CI-6800 | Gatch Laying & Levelling | 20 | 20 | 2025-05-12 | 2025-06-04 | 2025-06-21 | 2025-07-16 | 23
C-56-HC01-PL-CI-6810 | Gatch Compaction | 20 | 20 | 2025-05-14 | 2025-06-09 | 2025-06-24 | 2025-07-18 | 23
C-56-HC01-PL-CI-7800 | Installation of Marker Post/Sign Board | 20 | 20 | 2025-06-09 | 2025-07-03 | 2025-07-18 | 2025-08-11 | 37
C-56-HC01-PL-CI-7810 | Installation of Crash Barriers (If any) | 20 | 20 | 2025-06-14 | 2025-07-09 | 2025-07-24 | 2025-08-16 | 37
Berming from KP 6 to KP 12.6CCOPL56218.2 |  | 50 | 50 | 2025-05-23 | 2025-07-21 | 2025-06-26 | 2025-08-23 | 30
C-56-HC01-PL-CI-7000 | Gatch Laying & Levelling | 20 | 20 | 2025-05-23 | 2025-06-18 | 2025-06-26 | 2025-07-21 | 17
C-56-HC01-PL-CI-7010 | Gatch Compaction | 20 | 20 | 2025-05-26 | 2025-06-20 | 2025-07-03 | 2025-07-25 | 17
C-56-HC01-PL-CI-8000 | Installation of Marker Post/Sign Board | 20 | 20 | 2025-06-20 | 2025-07-15 | 2025-07-26 | 2025-08-18 | 30
C-56-HC01-PL-CI-8010 | Installation of Crash Barriers (If any) | 20 | 20 | 2025-06-26 | 2025-07-21 | 2025-08-01 | 2025-08-23 | 30
NDRC by Micro Tunneling Method |  | 177 | 177 | 2024-09-25 | 2025-05-13 | 2024-12-24 | 2025-08-02 | 10
Micro Tunnelling @ CH 11+421 - 11+560 (NDRC-08) |  | 177 | 177 | 2024-10-01 | 2025-02-28 | 2024-12-24 | 2025-08-02 | 10
Entry & Exit Pit ConstructionCCOPL56904 |  | 90 | 90 | 2024-10-01 | 2024-12-11 | 2024-12-24 | 2025-04-18 | 10
C-56-HC01-CNM08-1000 | Sheet Piling for Driving & Receiving Pit | 50 | 50 | 2024-10-01 | 2024-10-30 | 2024-12-24 | 2025-02-20 | 10
C-56-HC01-CNM08-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-10-30 | 2024-11-04 | 2025-02-21 | 2025-02-25 | 10
C-56-HC01-CNM08-1010 | Driving & Receiving Pit Excavation | 20 | 20 | 2024-10-26 | 2024-11-12 | 2025-02-21 | 2025-03-20 | 10
C-56-HC01-CNM08-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 16 | 16 | 2024-11-04 | 2024-11-15 | 2025-02-26 | 2025-03-20 | 10
C-56-HC01-CNM08-1040 | Floor Blinding & French Drain in Driving Pit | 6 | 6 | 2024-11-16 | 2024-11-23 | 2025-03-22 | 2025-04-03 | 10
C-56-HC01-CNM08-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 6 | 6 | 2024-11-23 | 2024-11-30 | 2025-04-03 | 2025-04-10 | 10
C-56-HC01-CNM08-1060 | Construction of Exit Wall with Ring | 6 | 6 | 2024-12-04 | 2024-12-11 | 2025-04-11 | 2025-04-18 | 10
Tunneling & Jack UpCCOPL57562 |  | 73 | 73 | 2024-12-11 | 2025-02-12 | 2025-04-18 | 2025-07-17 | 10
C-56-HC01-CNM08-1200 | Jacking of MTBM & RC Sleeves | 30 | 30 | 2024-12-11 | 2025-01-14 | 2025-04-18 | 2025-05-24 | 10
C-56-HC01-CNM08-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2025-01-14 | 2025-01-18 | 2025-05-24 | 2025-05-29 | 10
C-56-HC01-CNM08-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-02-06 | 2025-02-12 | 2025-07-11 | 2025-07-17 | 10
Pipe Lowering, Welding, NDT & CoatingCCOPL57572 |  | 22 | 22 | 2025-01-18 | 2025-01-30 | 2025-05-29 | 2025-06-26 | 10
C-56-HC01-CNM08-1400 | Lowering & Welding of Carrier Pipe | 21 | 21 | 2025-01-18 | 2025-01-27 | 2025-05-29 | 2025-06-25 | 10
C-56-HC01-CNM08-1410 | NDT, Coating & Holiday Inspection of Carrier Pipe | 21 | 21 | 2025-01-20 | 2025-01-30 | 2025-05-30 | 2025-06-26 | 10
HydrotestingCCOPL57582 |  | 12 | 12 | 2025-01-30 | 2025-02-06 | 2025-06-26 | 2025-07-11 | 10
C-56-HC01-CNM08-1600 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 12 | 12 | 2025-01-30 | 2025-02-06 | 2025-06-26 | 2025-07-11 | 10
Re-Instatement of Entry & Exit PitCCOPL57592 |  | 14 | 14 | 2025-02-12 | 2025-02-28 | 2025-07-17 | 2025-08-02 | 10
C-56-HC01-CNM08-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-02-12 | 2025-02-28 | 2025-07-17 | 2025-08-02 | 10
NDRC-06 (incl Hydrotest) @ CH 06+837 - 06+922 (Open Cut*) |  | 19 | 19 | 2025-04-16 | 2025-05-09 | 2025-05-30 | 2025-06-24 | 20
Entry & Exit Pit ConstructionCCOPL56922 |  | 2 | 2 | 2025-04-16 | 2025-04-18 | 2025-05-30 | 2025-06-02 | 17
C-56-HC01-CME10-1090 | Trench Excavation | 2 | 2 | 2025-04-16 | 2025-04-18 | 2025-05-30 | 2025-06-02 | 17
Tunneling & Jack UpCCOPL57222 |  | 2 | 2 | 2025-04-18 | 2025-04-21 | 2025-06-02 | 2025-06-04 | 20
C-56-HC01-CME10-1100 | Bedding | 2 | 2 | 2025-04-18 | 2025-04-21 | 2025-06-02 | 2025-06-04 | 20
Pipe Lowering, Welding, NDT & CoatingCCOPL57232 |  | 11 | 11 | 2025-04-21 | 2025-05-03 | 2025-06-04 | 2025-06-19 | 20
C-56-HC01-CME10-1110 | Lowering | 2 | 2 | 2025-04-21 | 2025-04-23 | 2025-06-04 | 2025-06-09 | 20
C-56-HC01-CME10-1120 | Section Tie-in Welding | 3 | 3 | 2025-04-23 | 2025-04-26 | 2025-06-09 | 2025-06-12 | 20
C-56-HC01-CME10-1130 | NDT (Tie-in Joint) | 3 | 3 | 2025-04-26 | 2025-04-30 | 2025-06-12 | 2025-06-16 | 20
C-56-HC01-CME10-1140 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-04-30 | 2025-05-03 | 2025-06-16 | 2025-06-19 | 20
HydrotestingCCOPL57242 |  | 2 | 2 | 2025-05-03 | 2025-05-06 | 2025-06-19 | 2025-06-21 | 20
C-56-HC01-CME10-1150 | Holiday Testing | 2 | 2 | 2025-05-03 | 2025-05-06 | 2025-06-19 | 2025-06-21 | 20
Re-Instatement of Entry & Exit PitCCOPL57252 |  | 2 | 2 | 2025-05-06 | 2025-05-09 | 2025-06-21 | 2025-06-24 | 20
C-56-HC01-CME10-1160 | Padding & Back Filling | 2 | 2 | 2025-05-06 | 2025-05-09 | 2025-06-21 | 2025-06-24 | 20
NDRC-04 (incl Hydrotest) @ CH 03+449 - 03+493 (Open Cut*) |  | 19 | 19 | 2025-04-19 | 2025-05-13 | 2025-06-03 | 2025-06-28 | 17
Entry & Exit Pit ConstructionCCOPL56918 |  | 2 | 2 | 2025-04-19 | 2025-04-22 | 2025-06-03 | 2025-06-07 | 17
C-56-HC01-CME10-1170 | Trench Excavation | 2 | 2 | 2025-04-19 | 2025-04-22 | 2025-06-03 | 2025-06-07 | 17
Tunneling & Jack UpCCOPL57882 |  | 2 | 2 | 2025-04-22 | 2025-04-24 | 2025-06-07 | 2025-06-10 | 17
C-56-HC01-CME10-1180 | Bedding | 2 | 2 | 2025-04-22 | 2025-04-24 | 2025-06-07 | 2025-06-10 | 17
Pipe Lowering, Welding, NDT & CoatingCCOPL57892 |  | 11 | 11 | 2025-04-24 | 2025-05-08 | 2025-06-10 | 2025-06-23 | 17
C-56-HC01-CME10-1190 | Lowering | 2 | 2 | 2025-04-24 | 2025-04-26 | 2025-06-10 | 2025-06-12 | 17
C-56-HC01-CME10-1200 | Section Tie-in Welding | 3 | 3 | 2025-04-26 | 2025-04-30 | 2025-06-12 | 2025-06-16 | 17
C-56-HC01-CME10-1210 | NDT (Tie-in Joint) | 3 | 3 | 2025-04-30 | 2025-05-03 | 2025-06-16 | 2025-06-19 | 17
C-56-HC01-CME10-1220 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-05-03 | 2025-05-08 | 2025-06-19 | 2025-06-23 | 17
HydrotestingCCOPL57902 |  | 2 | 2 | 2025-05-08 | 2025-05-10 | 2025-06-23 | 2025-06-25 | 17
C-56-HC01-CME10-1230 | Holiday Testing | 2 | 2 | 2025-05-08 | 2025-05-10 | 2025-06-23 | 2025-06-25 | 17
Re-Instatement of Entry & Exit PitCCOPL57912 |  | 2 | 2 | 2025-05-10 | 2025-05-13 | 2025-06-25 | 2025-06-28 | 17
C-56-HC01-CME10-1240 | Padding & Back Filling | 2 | 2 | 2025-05-10 | 2025-05-13 | 2025-06-25 | 2025-06-28 | 17
Micro Tunnelling @ CH 02+884 - 03+058 (NDRC-03) |  | 158 | 158 | 2024-09-25 | 2025-04-16 | 2024-12-28 | 2025-07-16 | 21
Entry & Exit Pit ConstructionCCOPL56910 |  | 71 | 71 | 2024-09-25 | 2024-12-09 | 2024-12-28 | 2025-03-28 | 21
C-56-HC01-CNM03-1000 | Sheet Piling for Driving & Receiving Pit | 30 | 30 | 2024-09-25 | 2024-10-29 | 2024-12-28 | 2025-02-01 | 21
C-56-HC01-CNM03-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-10-30 | 2024-11-02 | 2025-02-03 | 2025-02-06 | 23
C-56-HC01-CNM03-1010 | Driving & Receiving Pit Excavation | 18 | 18 | 2024-10-16 | 2024-10-31 | 2025-02-03 | 2025-02-22 | 21
C-56-HC01-CNM03-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 12 | 12 | 2024-11-04 | 2024-11-14 | 2025-02-10 | 2025-02-22 | 21
C-56-HC01-CNM03-1040 | Floor Blinding & French Drain in Driving Pit | 8 | 8 | 2024-11-15 | 2024-11-21 | 2025-02-24 | 2025-03-05 | 21
C-56-HC01-CNM03-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 8 | 8 | 2024-11-22 | 2024-11-28 | 2025-03-05 | 2025-03-17 | 21
C-56-HC01-CNM03-1060 | Construction of Exit Wall with Ring | 8 | 8 | 2024-11-30 | 2024-12-09 | 2025-03-15 | 2025-03-28 | 21
Tunneling & Jack UpCCOPL57522 |  | 73 | 73 | 2025-01-21 | 2025-03-26 | 2025-03-28 | 2025-06-30 | 21
C-56-HC01-CNM03-1200 | Jacking of MTBM & RC Sleeves | 25 | 25 | 2025-01-21 | 2025-02-05 | 2025-03-28 | 2025-04-30 | 21
C-56-HC01-CNM03-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2025-02-06 | 2025-02-10 | 2025-04-30 | 2025-05-05 | 21
C-56-HC01-CNM03-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-03-19 | 2025-03-26 | 2025-06-23 | 2025-06-30 | 21
Pipe Lowering, Welding, NDT & CoatingCCOPL57532 |  | 29 | 29 | 2025-02-11 | 2025-03-03 | 2025-05-05 | 2025-06-11 | 21
C-56-HC01-CNM03-1400 | Lowering & Welding of Carrier Pipe | 28 | 28 | 2025-02-11 | 2025-02-27 | 2025-05-05 | 2025-06-10 | 21
C-56-HC01-CNM03-1410 | NDT, Coating & Holiday Inspection of Carrier Pipe | 28 | 28 | 2025-02-12 | 2025-03-03 | 2025-05-07 | 2025-06-11 | 21
HydrotestingCCOPL57542 |  | 10 | 10 | 2025-03-03 | 2025-03-18 | 2025-06-11 | 2025-06-23 | 21
C-56-HC01-CNM03-1600 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 10 | 10 | 2025-03-03 | 2025-03-18 | 2025-06-11 | 2025-06-23 | 21
Re-Instatement of Entry & Exit PitCCOPL57552 |  | 14 | 14 | 2025-03-26 | 2025-04-16 | 2025-06-30 | 2025-07-16 | 21
C-56-HC01-CNM03-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-03-26 | 2025-04-16 | 2025-06-30 | 2025-07-16 | 21
NDRC by Micro Tunnelling |  | 200 | 200 | 2024-09-24 | 2025-06-18 | 2024-11-08 | 2025-07-17 | 20
Micro Tunnelling @ CH 06+199 - 06+426 (NDRC-05) |  | 57 | 57 | 2024-10-30 | 2025-05-17 | 2025-02-03 | 2025-04-19 | 92
Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 |  | 45 | 45 | 2024-10-30 | 2025-04-24 | 2025-02-03 | 2025-04-05 | 91
C-56-HC01-CNH05-1000 | Sheet Piling for Driving & Receiving Pit | 7 | 7 | 2024-10-30 | 2024-11-27 | 2025-02-03 | 2025-02-10 | 81
C-56-HC01-CNH05-1020 | Installation of Dewatering System for Driving & Receiving Pit | 2 | 2 | 2024-11-28 | 2024-12-04 | 2025-02-11 | 2025-02-12 | 83
C-56-HC01-CNH05-1010 | Driving & Receiving Pit Excavation | 7 | 7 | 2024-11-20 | 2024-12-07 | 2025-02-11 | 2025-02-18 | 81
C-56-HC01-CNH05-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 3 | 3 | 2024-12-05 | 2024-12-16 | 2025-02-15 | 2025-02-18 | 81
C-56-HC01-CNH05-1040 | Floor Blinding & French Drain in Driving Pit | 3 | 3 | 2024-12-17 | 2024-12-23 | 2025-02-19 | 2025-02-21 | 81
C-56-HC01-CNH05-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 3 | 3 | 2024-12-24 | 2024-12-30 | 2025-02-22 | 2025-02-25 | 81
C-56-HC01-CNH05-1060 | Construction of Exit Wall with Ring | 3 | 3 | 2025-01-02 | 2025-01-08 | 2025-02-26 | 2025-02-28 | 81
C-56-HC01-CNH05-1070 | Lowering & Welding of Carrier Pipe | 7 | 7 | 2025-03-07 | 2025-04-09 | 2025-03-17 | 2025-03-28 | 81
C-56-HC01-CNH05-1080 | NDT, Coating & Holiday Inspection of Carrier Pipe | 7 | 7 | 2025-03-08 | 2025-04-12 | 2025-03-19 | 2025-03-29 | 91
C-56-HC01-CNH05-1090 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 3 | 3 | 2025-04-12 | 2025-04-24 | 2025-03-29 | 2025-04-05 | 91
Tunneling & Jack UpCCOPL58282 |  | 27 | 27 | 2025-02-06 | 2025-04-30 | 2025-03-01 | 2025-04-11 | 91
C-56-HC01-CNH05-1200 | Jacking of MTBM & RC Sleeves | 7 | 7 | 2025-02-06 | 2025-02-28 | 2025-03-01 | 2025-03-11 | 81
C-56-HC01-CNH05-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2025-03-01 | 2025-03-06 | 2025-03-11 | 2025-03-17 | 81
C-56-HC01-CNH05-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-04-24 | 2025-04-30 | 2025-04-05 | 2025-04-11 | 91
Re-Instatement of Entry & Exit PitCCOPL58292 |  | 7 | 7 | 2025-04-30 | 2025-05-17 | 2025-04-11 | 2025-04-19 | 92
C-56-HC01-CNH05-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 7 | 7 | 2025-04-30 | 2025-05-17 | 2025-04-11 | 2025-04-19 | 92
Micro Tunnelling @ CH 00+953 - 01+303 (NDRC-02) |  | 172 | 172 | 2024-09-24 | 2025-06-18 | 2024-12-13 | 2025-07-17 | 20
Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 |  | 153 | 153 | 2024-09-24 | 2025-05-24 | 2024-12-13 | 2025-06-24 | 20
C-56-HC01-CNH02-1000 | Sheet Piling for Driving & Receiving Pit | 40 | 40 | 2024-09-24 | 2024-10-21 | 2024-12-13 | 2025-01-29 | 20
C-56-HC01-CNH02-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-10-22 | 2024-10-25 | 2025-01-30 | 2025-02-03 | 20
C-56-HC01-CNH02-1010 | Driving & Receiving Pit Excavation | 14 | 14 | 2024-10-15 | 2024-10-30 | 2025-01-30 | 2025-02-14 | 20
C-56-HC01-CNH02-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 10 | 10 | 2024-10-26 | 2024-11-06 | 2025-02-04 | 2025-02-14 | 20
C-56-HC01-CNH02-1040 | Floor Blinding & French Drain in Driving Pit | 6 | 6 | 2024-11-07 | 2024-11-13 | 2025-02-15 | 2025-02-21 | 20
C-56-HC01-CNH02-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 6 | 6 | 2024-11-14 | 2024-11-20 | 2025-02-22 | 2025-02-28 | 20
C-56-HC01-CNH02-1060 | Construction of Exit Wall with Ring | 6 | 6 | 2024-11-22 | 2024-11-28 | 2025-03-02 | 2025-03-11 | 20
C-56-HC01-CNH02-1070 | Lowering & Welding of Carrier Pipe | 30 | 30 | 2025-03-25 | 2025-05-05 | 2025-04-26 | 2025-06-02 | 20
C-56-HC01-CNH02-1080 | NDT, Coating & Holiday Inspection Carrier Pipe | 34 | 34 | 2025-03-27 | 2025-05-10 | 2025-04-28 | 2025-06-10 | 20
C-56-HC01-CNH02-1090 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 12 | 12 | 2025-05-10 | 2025-05-24 | 2025-06-10 | 2025-06-24 | 20
Tunneling & Jack UpCCOPL58222 |  | 85 | 85 | 2025-02-10 | 2025-05-30 | 2025-03-11 | 2025-07-01 | 20
C-56-HC01-CNH02-1200 | Jacking of MTBM & RC Sleeves | 29 | 29 | 2025-02-10 | 2025-03-19 | 2025-03-11 | 2025-04-22 | 20
C-56-HC01-CNH02-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2025-03-19 | 2025-03-25 | 2025-04-22 | 2025-04-26 | 20
C-56-HC01-CNH02-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-05-24 | 2025-05-30 | 2025-06-24 | 2025-07-01 | 20
Re-Instatement of Entry & Exit PitCCOPL58232 |  | 14 | 14 | 2025-05-30 | 2025-06-18 | 2025-07-01 | 2025-07-17 | 20
C-56-HC01-CNH02-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-05-30 | 2025-06-18 | 2025-07-01 | 2025-07-17 | 20
Micro Tunnelling @ CH 00+115 - 00+390 (NDRC-01) |  | 145 | 145 | 2024-10-30 | 2025-05-06 | 2024-11-08 | 2025-05-10 | 75
Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 |  | 126 | 126 | 2024-10-30 | 2025-04-14 | 2024-11-08 | 2025-04-17 | 75
C-56-HC01-CNH01-1000 | Sheet Piling for Driving & Receiving Pit | 25 | 25 | 2024-10-30 | 2024-11-28 | 2024-11-08 | 2024-12-09 | 75
C-56-HC01-CNH01-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-11-28 | 2024-12-05 | 2024-12-10 | 2024-12-13 | 77
C-56-HC01-CNH01-1010 | Driving & Receiving Pit Excavation | 28 | 28 | 2024-11-20 | 2024-12-09 | 2024-12-10 | 2025-01-11 | 75
C-56-HC01-CNH01-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 22 | 22 | 2024-12-05 | 2024-12-17 | 2024-12-17 | 2025-01-11 | 75
C-56-HC01-CNH01-1040 | Floor Blinding & French Drain in Driving Pit | 6 | 6 | 2024-12-17 | 2024-12-24 | 2025-01-13 | 2025-01-18 | 75
C-56-HC01-CNH01-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 6 | 6 | 2024-12-24 | 2024-12-31 | 2025-01-20 | 2025-01-25 | 75
C-56-HC01-CNH01-1060 | Construction of Exit Wall with Ring | 6 | 6 | 2025-01-02 | 2025-01-09 | 2025-01-28 | 2025-02-03 | 75
C-56-HC01-CNH01-1070 | Lowering & Welding of Carrier Pipe | 14 | 14 | 2025-02-14 | 2025-03-21 | 2025-03-08 | 2025-03-29 | 75
C-56-HC01-CNH01-1080 | NDT, Coating & Holiday Inspection of Carrier Pipe | 14 | 14 | 2025-02-15 | 2025-03-25 | 2025-03-09 | 2025-04-03 | 75
C-56-HC01-CNH01-1090 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 12 | 12 | 2025-03-25 | 2025-04-14 | 2025-04-03 | 2025-04-17 | 75
Tunneling & Jack UpCCOPL58162 |  | 59 | 59 | 2025-01-14 | 2025-04-19 | 2025-02-04 | 2025-04-23 | 75
C-56-HC01-CNH01-1200 | Jacking of MTBM & RC Sleeves | 23 | 23 | 2025-01-14 | 2025-02-10 | 2025-02-04 | 2025-03-01 | 75
C-56-HC01-CNH01-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2025-02-10 | 2025-02-14 | 2025-03-02 | 2025-03-08 | 75
C-56-HC01-CNH01-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-04-14 | 2025-04-19 | 2025-04-17 | 2025-04-23 | 75
Re-Instatement of Entry & Exit PitCCOPL58172 |  | 14 | 14 | 2025-04-19 | 2025-05-06 | 2025-04-23 | 2025-05-10 | 75
C-56-HC01-CNH01-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-04-19 | 2025-05-06 | 2025-04-23 | 2025-05-10 | 75
Telecommunication Works |  | 36 | 36 | 2025-04-15 | 2025-06-11 | 2025-05-29 | 2025-07-14 | 66
Telecommunication Works from Habshan CCOP56IC20.1 |  | 22 | 22 | 2025-04-15 | 2025-05-12 | 2025-05-29 | 2025-06-26 | 78
C-56-HC01-PL-TE-8200 | FO - Cable Pulling/ Laying | 20 | 20 | 2025-04-15 | 2025-05-09 | 2025-05-29 | 2025-06-24 | 31
C-56-HC01-PL-TE-8210 | Termination/Splicing @ BVS | 2 | 2 | 2025-05-09 | 2025-05-12 | 2025-06-24 | 2025-06-26 | 78
Telecommunication Works from KP 6 to KCCOP56IC20.2 |  | 22 | 22 | 2025-05-14 | 2025-06-11 | 2025-06-17 | 2025-07-14 | 66
C-56-HC01-PL-TE-8400 | FO - Cable Pulling/ Laying | 20 | 20 | 2025-05-14 | 2025-06-09 | 2025-06-17 | 2025-07-11 | 17
C-56-HC01-PL-TE-8410 | Termination/Splicing @ BVS | 2 | 2 | 2025-06-09 | 2025-06-11 | 2025-07-11 | 2025-07-14 | 66
Pig Receiver 838-V-601 (56'' Pipeline) |  | 233 | 233 | 2024-09-07 | 2025-09-03 | 2024-11-30 | 2025-09-17 | 11
Pig Receiver 838-V-601 (56'' Pipeline)-1 |  | 233 | 233 | 2024-09-07 | 2025-09-03 | 2024-11-30 | 2025-09-17 | 11
Civil Works |  | 233 | 233 | 2024-09-07 | 2025-09-03 | 2024-11-30 | 2025-09-17 | 11
Earthworks, Site Preparation, Site GradingCCOH56CS30 |  | 102 | 102 | 2024-09-07 | 2025-01-29 | 2024-11-30 | 2025-04-11 | 6
C-56-PR-838-CI-1000 | Site Survey, Preparation & Grading Works | 15 | 15 | 2024-09-07 | 2024-09-24 | 2024-11-30 | 2024-12-19 | 6
C-56-PR-838-CI-1010 | Earth Works for Equipment Foundations | 15 | 15 | 2024-09-25 | 2024-10-18 | 2024-12-20 | 2025-01-07 | 6
C-56-PR-838-CI-1020 | Earth Works for Pipe Support Foundations | 15 | 15 | 2024-10-19 | 2024-11-20 | 2025-01-08 | 2025-01-24 | 6
C-56-PR-838-CI-1030 | Earth Works for Field Instrument, JBs & Light Pole Foundations | 14 | 14 | 2024-11-21 | 2024-12-09 | 2025-01-25 | 2025-02-10 | 6
C-56-PR-838-CI-1040 | Earth Works for Access Platforms & Misc. Structural Foundations | 14 | 14 | 2024-12-10 | 2024-12-25 | 2025-02-11 | 2025-02-26 | 6
C-56-PR-838-CI-1050 | Earth Works for Thrust Anchor Block | 21 | 21 | 2024-12-26 | 2025-01-20 | 2025-02-27 | 2025-03-29 | 6
C-56-PR-838-CI-1060 | Earth Works for Impact Wall | 8 | 8 | 2025-01-21 | 2025-01-29 | 2025-03-29 | 2025-04-11 | 6
Compaction & Testing CCOH56CS31 |  | 62 | 62 | 2024-11-13 | 2025-02-04 | 2025-01-25 | 2025-04-17 | 60
C-56-PR-838-CI-1210 | Compaction & Testing for Pipe Support Foundations | 8 | 8 | 2024-11-21 | 2024-11-29 | 2025-01-25 | 2025-02-03 | 23
C-56-PR-838-CI-1200 | Compaction & Testing for Equipment Foundations | 8 | 8 | 2024-11-13 | 2024-11-21 | 2025-02-01 | 2025-02-10 | 108
C-56-PR-838-CI-1220 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | 5 | 5 | 2024-12-10 | 2024-12-14 | 2025-02-11 | 2025-02-15 | 55
C-56-PR-838-CI-1230 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | 5 | 5 | 2024-12-26 | 2024-12-31 | 2025-02-27 | 2025-03-05 | 55
C-56-PR-838-CI-1240 | Compaction & Testing for Thrust Anchor Block | 8 | 8 | 2025-01-21 | 2025-01-29 | 2025-03-29 | 2025-04-11 | 22
C-56-PR-838-CI-1250 | Compaction & Testing for Impact Wall | 5 | 5 | 2025-01-30 | 2025-02-04 | 2025-04-11 | 2025-04-17 | 47
Concrete Works (Foundations for Equipment)CCOH56CS32 |  | 64 | 64 | 2024-12-21 | 2025-03-17 | 2025-02-11 | 2025-05-06 | 65
C-56-PR-838-CI-1400 | Concrete Works for Equipment Foundations | 21 | 21 | 2024-12-21 | 2025-01-15 | 2025-02-11 | 2025-03-08 | 108
C-56-PR-838-CI-1410 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | 14 | 14 | 2025-02-01 | 2025-02-17 | 2025-03-20 | 2025-04-11 | 31
C-56-PR-838-CI-1420 | Concrete Works for Access Platforms & Misc. Structural Foundations | 21 | 21 | 2025-02-18 | 2025-03-17 | 2025-04-11 | 2025-05-06 | 31
Thrust Anchor Block/ Impact WallCCOH56CS33 |  | 120 | 120 | 2025-01-30 | 2025-07-11 | 2025-04-11 | 2025-09-03 | 22
C-56-PR-838-CI-1500 | Concrete Works for Impact Wall | 90 | 90 | 2025-03-17 | 2025-07-11 | 2025-05-07 | 2025-08-23 | 31
C-56-PR-838-CI-1510 | Concrete Works for Thrust Anchor Block | 120 | 120 | 2025-01-30 | 2025-07-03 | 2025-04-11 | 2025-09-03 | 22
Concrete Works (Foundations for Pipe Supports) CCOH56CS34 |  | 35 | 35 | 2024-12-21 | 2025-01-31 | 2025-02-04 | 2025-03-20 | 23
C-56-PR-838-CI-1600 | Concrete Works for Pipe Support Foundations | 35 | 35 | 2024-12-21 | 2025-01-31 | 2025-02-04 | 2025-03-20 | 23
Trenching for Cables CCOH56CS35 |  | 48 | 48 | 2025-03-03 | 2025-05-19 | 2025-04-22 | 2025-06-20 | 11
C-56-PR-838-CI-1800 | Electrical & Earthing Cable Trenching | 24 | 24 | 2025-03-03 | 2025-04-15 | 2025-04-22 | 2025-05-21 | 6
C-56-PR-838-CI-1810 | Instrument & Telecom Cable Trenching | 24 | 24 | 2025-04-15 | 2025-05-19 | 2025-05-21 | 2025-06-20 | 11
Backfilling for Cables CCOH56CS36 |  | 29 | 29 | 2025-06-28 | 2025-08-01 | 2025-07-23 | 2025-08-26 | 11
C-56-PR-838-CI-2800 | Back Filling for Electrical & Earthing Cable | 21 | 21 | 2025-06-28 | 2025-07-23 | 2025-07-23 | 2025-08-16 | 19
C-56-PR-838-CI-2810 | Back Filling for Instrument & Telecom Cable | 21 | 21 | 2025-07-08 | 2025-08-01 | 2025-08-01 | 2025-08-26 | 11
Paving Works CCOH56CS37 |  | 18 | 18 | 2025-08-01 | 2025-09-03 | 2025-08-26 | 2025-09-17 | 11
C-56-PR-838-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 18 | 18 | 2025-08-01 | 2025-09-03 | 2025-08-26 | 2025-09-17 | 11
Pipe Supports Fabrication & Installation CCOH56SS50 |  | 45 | 45 | 2025-02-01 | 2025-04-04 | 2025-03-20 | 2025-05-19 | 23
C-56-PR-838-CI-2000 | Pre-Fabrication & Installation of Pipe Supports | 45 | 45 | 2025-02-01 | 2025-04-04 | 2025-03-20 | 2025-05-19 | 23
Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOH56SS51 |  | 49 | 49 | 2025-04-29 | 2025-06-30 | 2025-06-14 | 2025-08-12 | 23
C-56-PR-838-CI-3000 | Pre-Fabrication & Installation of Platforms & Crossovers | 28 | 28 | 2025-04-29 | 2025-06-02 | 2025-06-14 | 2025-07-18 | 23
C-56-PR-838-CI-3010 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | 21 | 21 | 2025-06-02 | 2025-06-30 | 2025-07-18 | 2025-08-12 | 23
Mechanical Works & Equipment Installation |  | 114 | 114 | 2025-03-13 | 2025-06-09 | 2025-03-13 | 2025-08-04 | 37
Installation of Pig Receiver (838-V-601) CCOH56ME50 |  | 8 | 8 | 2025-03-13 | 2025-03-24 | 2025-03-13 | 2025-03-24 | 105
C-56-PR-838-ME-1100 | Installation of Pig Receiver (838-V-601) 56" | 8 | 8 | 2025-03-13 | 2025-03-24 | 2025-03-13 | 2025-03-24 | 105
Installation of Pig Signaler (838-V-601) CCOH56ME60 |  | 5 | 5 | 2025-05-09 | 2025-05-15 | 2025-05-09 | 2025-05-15 | 97
C-56-PR-838-ME-1200 | Installation of Pig Signaler (838-V-601) | 5 | 5 | 2025-05-09 | 2025-05-15 | 2025-05-09 | 2025-05-15 | 97
Installation/ Welding of Isolation Joints, Barred Tee & Anchor Flanges CCOH56ME70 |  | 4 | 4 | 2025-06-02 | 2025-06-09 | 2025-07-31 | 2025-08-04 | 37
C-56-PR-838-ME-1400 | Installation/ Welding of Isolation Joints, Barred Tee & Anchor FlangesCCOH56ME70 (Deleted) | 4 | 4 | 2025-06-02 | 2025-06-09 | 2025-07-31 | 2025-08-04 | 37
Piping Works |  | 124 | 124 | 2025-01-03 | 2025-05-19 | 2025-02-24 | 2025-07-31 | 37
Piping Pre-Fabrication CCOH56PI101 |  | 37 | 37 | 2025-01-03 | 2025-02-14 | 2025-02-24 | 2025-04-17 | 44
C-56-PR-838-PI-1000 | Piping Pre-Fabrication | 37 | 37 | 2025-01-03 | 2025-02-14 | 2025-02-24 | 2025-04-17 | 44
Erection CCOH56PI111 |  | 24 | 24 | 2025-02-17 | 2025-03-20 | 2025-04-04 | 2025-05-02 | 78
C-56-PR-838-PI-1200 | Piping Erection | 24 | 24 | 2025-02-17 | 2025-03-20 | 2025-04-04 | 2025-05-02 | 78
Field Joint Welding, NDT & Coating CCOH56PI121 |  | 27 | 27 | 2025-02-25 | 2025-04-07 | 2025-04-12 | 2025-05-15 | 89
C-56-PR-838-PI-1400 | Field Joint Welding | 24 | 24 | 2025-02-25 | 2025-04-03 | 2025-04-12 | 2025-05-12 | 78
C-56-PR-838-PI-1410 | NDT & Coating for Field Joint Weld | 24 | 24 | 2025-02-28 | 2025-04-07 | 2025-04-16 | 2025-05-15 | 89
Hydrotesting CCOH56PI131 |  | 5 | 5 | 2025-04-07 | 2025-04-12 | 2025-05-15 | 2025-05-21 | 89
C-56-PR-838-PI-1600 | Hydrotesting | 5 | 5 | 2025-04-07 | 2025-04-12 | 2025-05-15 | 2025-05-21 | 89
Installation of Valves CCOH56PI141 |  | 5 | 5 | 2025-04-12 | 2025-04-18 | 2025-07-24 | 2025-07-29 | 37
C-56-PR-838-PI-1800 | Installation of Valves/MOV/ROV | 5 | 5 | 2025-04-12 | 2025-04-18 | 2025-07-24 | 2025-07-29 | 37
Final Bolt Torquing/ Re-Instatement CCOH56PI151 |  | 3 | 3 | 2025-05-15 | 2025-05-19 | 2025-07-29 | 2025-07-31 | 37
C-56-PR-838-PI-2000 | Final Bolt Torquing/ Re-Instatement | 3 | 3 | 2025-05-15 | 2025-05-19 | 2025-07-29 | 2025-07-31 | 37
Pipeline Works |  | 15 | 15 | 2025-05-31 | 2025-06-20 | 2025-07-30 | 2025-08-15 | 37
Pig Receiver 838-V-601 56'' Pipeline/ Piping Hook-up CCOH56PI51 |  | 15 | 15 | 2025-05-31 | 2025-06-20 | 2025-07-30 | 2025-08-15 | 37
C-56-PR-838-PL-1000 | Installation of Isolation Joint | 2 | 2 | 2025-05-31 | 2025-06-03 | 2025-07-30 | 2025-07-31 | 37
C-56-PR-838-PL-1010 | Field Joint Welding (Piping/Pipeline Section including IJ) | 5 | 5 | 2025-06-02 | 2025-06-10 | 2025-07-31 | 2025-08-05 | 37
C-56-PR-838-PL-1020 | NDT for Weld Joint | 5 | 5 | 2025-06-09 | 2025-06-14 | 2025-08-05 | 2025-08-09 | 37
C-56-PR-838-PL-1030 | Ext. Coating for Weld Joint | 5 | 5 | 2025-06-14 | 2025-06-20 | 2025-08-11 | 2025-08-15 | 37
Electrical & Instrumentation Works |  | 85 | 85 | 2025-04-04 | 2025-07-26 | 2025-05-19 | 2025-08-29 | 26
Electrical Works CCOH56EL30 |  | 53 | 53 | 2025-05-12 | 2025-07-03 | 2025-05-23 | 2025-07-28 | 42
C-56-PR-838-EI-1400 | Deep Earth Well Drilling | 6 | 6 | 2025-05-12 | 2025-05-17 | 2025-05-23 | 2025-05-30 | 89
C-56-PR-838-EI-1810 | Installation of JB's | 5 | 5 | 2025-05-13 | 2025-05-17 | 2025-06-14 | 2025-06-20 | 67
C-56-PR-838-EI-2020 | Installation of Cable Trays | 6 | 6 | 2025-05-12 | 2025-05-17 | 2025-06-17 | 2025-06-24 | 43
C-56-PR-838-EI-1800 | Installation of Light Pole, Lighting & Fixtures | 21 | 21 | 2025-05-19 | 2025-06-13 | 2025-06-24 | 2025-07-19 | 43
C-56-PR-838-EI-2030 | Instrument Tubing Works | 6 | 6 | 2025-06-20 | 2025-06-28 | 2025-07-16 | 2025-07-23 | 34
C-56-PR-838-EI-1010 | Installation of CP Test Post | 2 | 2 | 2025-06-28 | 2025-07-01 | 2025-07-23 | 2025-07-25 | 36
C-56-PR-838-EI-1020 | Installation of CP JB's | 2 | 2 | 2025-07-01 | 2025-07-03 | 2025-07-25 | 2025-07-28 | 36
E&I Cable Laying, Glanding & Termination CCOH56EL31 |  | 83 | 83 | 2025-04-15 | 2025-07-26 | 2025-05-21 | 2025-08-29 | 26
C-56-PR-838-EI-2000 | Electrical & Earthing Cable Laying | 21 | 21 | 2025-04-15 | 2025-05-10 | 2025-05-21 | 2025-06-17 | 6
C-56-PR-838-EI-2010 | Instrument Cable Laying | 21 | 21 | 2025-05-24 | 2025-06-20 | 2025-06-20 | 2025-07-16 | 11
C-56-PR-838-CA-1000 | CP Cable Laying | 6 | 6 | 2025-06-20 | 2025-06-28 | 2025-07-16 | 2025-07-23 | 19
C-56-PR-838-CA-1030 | Glanding & Termination for CP S/m | 2 | 2 | 2025-07-03 | 2025-07-05 | 2025-07-28 | 2025-07-30 | 52
C-56-PR-838-EI-2040 | Loop Checking for Instruments | 12 | 12 | 2025-06-28 | 2025-07-12 | 2025-08-01 | 2025-08-15 | 26
C-56-PR-838-EI-2050 | Glanding & Termination | 12 | 12 | 2025-07-12 | 2025-07-26 | 2025-08-15 | 2025-08-29 | 26
RTU CCOH56EL41 |  | 12 | 12 | 2025-06-18 | 2025-07-03 | 2025-08-01 | 2025-08-15 | 26
C-56-PR-838-EI-1600 | Installation of RTUCCOH56EL41 (Deleted) | 12 | 12 | 2025-06-18 | 2025-07-03 | 2025-08-01 | 2025-08-15 | 26
Field Instruments CCOH56EL51 |  | 61 | 61 | 2025-04-04 | 2025-06-18 | 2025-05-19 | 2025-08-01 | 26
C-56-PR-838-EI-2210 | Pre-Fabrication & Installation of Field Instrument, JB Supports | 21 | 21 | 2025-04-04 | 2025-04-29 | 2025-05-19 | 2025-06-14 | 23
C-56-PR-838-EI-2200 | Installation of Field Instruments (Including Pig Signaller) | 21 | 21 | 2025-04-29 | 2025-05-24 | 2025-06-14 | 2025-07-10 | 26
C-56-PR-838-EI-2410 | Installation of F&G Device | 18 | 18 | 2025-05-26 | 2025-06-18 | 2025-07-11 | 2025-08-01 | 26
Telecommunication Works |  | 34 | 34 | 2025-06-18 | 2025-07-12 | 2025-07-16 | 2025-08-25 | 30
SDH Cabinet CCOH56IC20 |  | 14 | 14 | 2025-06-18 | 2025-07-05 | 2025-08-01 | 2025-08-18 | 30
C-56-PR-838-TE-1000 | SDH Cabinet (Deleted) | 14 | 14 | 2025-06-18 | 2025-07-05 | 2025-08-01 | 2025-08-18 | 30
CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) CCOH56IC30 |  | 34 | 34 | 2025-06-20 | 2025-07-12 | 2025-07-16 | 2025-08-25 | 30
C-56-PR-838-TE-1410 | FOC Laying | 14 | 14 | 2025-06-20 | 2025-07-08 | 2025-07-16 | 2025-08-01 | 11
C-56-PR-838-TE-1420 | FO Cable OTDR Testing & Splicing | 2 | 2 | 2025-07-10 | 2025-07-12 | 2025-08-22 | 2025-08-25 | 30
C-56-PR-838-TE-1600 | CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) (Deleted) | 6 | 6 | 2025-07-05 | 2025-07-12 | 2025-08-18 | 2025-08-25 | 30
591-BVS-01 (56'' Pipeline) |  | 199 | 199 | 2024-11-30 | 2025-09-10 | 2025-01-16 | 2025-09-20 | 11
591-BVS-01 (56'' Pipeline)-1 |  | 199 | 199 | 2024-11-30 | 2025-09-10 | 2025-01-16 | 2025-09-20 | 11
Civil Works |  | 177 | 177 | 2024-11-30 | 2025-09-10 | 2025-01-16 | 2025-08-25 | 33
Earthworks, Site Preparation, Site Grading CCOB156C10 |  | 42 | 42 | 2024-11-30 | 2025-01-21 | 2025-01-16 | 2025-03-06 | 46
C-56-591-01-CI-1000 | Site Survey, Preparation & Grading Works | 8 | 8 | 2024-11-30 | 2024-12-11 | 2025-01-16 | 2025-01-25 | 11
C-56-591-01-CI-1010 | Earth Works for Equipment Foundations & Hard Stand Area | 14 | 14 | 2024-12-07 | 2024-12-23 | 2025-01-21 | 2025-02-05 | 11
C-56-591-01-CI-1020 | Earth Works for Pipe Support Foundations | 14 | 14 | 2024-12-16 | 2024-12-31 | 2025-01-29 | 2025-02-13 | 11
C-56-591-01-CI-1030 | Earth Works for Field Instrument Foundations | 12 | 12 | 2024-12-23 | 2025-01-06 | 2025-02-05 | 2025-02-18 | 11
C-56-591-01-CI-1040 | Earth Works for Access Platforms & Misc. Structural Foundations | 14 | 14 | 2024-12-31 | 2025-01-16 | 2025-02-13 | 2025-02-28 | 16
C-56-591-01-CI-1050 | Earth Works for Light Pole, Fence & Gates Foundation | 12 | 12 | 2025-01-08 | 2025-01-21 | 2025-02-20 | 2025-03-06 | 46
Compaction & Testing CCOB156C11 |  | 29 | 29 | 2024-12-24 | 2025-01-27 | 2025-02-06 | 2025-03-14 | 108
C-56-591-01-CI-3020 | Compaction & Testing for Equipment Foundations & Hard Stand Area | 5 | 5 | 2024-12-24 | 2024-12-28 | 2025-02-06 | 2025-02-11 | 132
C-56-591-01-CI-3030 | Compaction & Testing for Pipe Support Foundations | 5 | 5 | 2025-01-02 | 2025-01-07 | 2025-02-14 | 2025-02-19 | 110
C-56-591-01-CI-3040 | Compaction & Testing for Field Instrument Foundations | 5 | 5 | 2025-01-07 | 2025-01-11 | 2025-02-19 | 2025-02-24 | 11
C-56-591-01-CI-3050 | Compaction & Testing for Access Platform & Misc. Structural Foundations | 5 | 5 | 2025-01-17 | 2025-01-22 | 2025-03-01 | 2025-03-08 | 16
C-56-591-01-CI-3060 | Compaction & Testing for Light Pole, Fence & Gates Foundation | 5 | 5 | 2025-01-22 | 2025-01-27 | 2025-03-07 | 2025-03-14 | 46
Concrete Works (Foundations for Equipment) CCOB156C30 |  | 58 | 58 | 2024-12-30 | 2025-03-09 | 2025-02-12 | 2025-04-30 | 95
C-56-591-01-CI-1400 | Concrete Works for Equipment Foundations & Hard Stand Area | 21 | 21 | 2024-12-30 | 2025-01-23 | 2025-02-12 | 2025-03-09 | 132
C-56-591-01-CI-1410 | Concrete Works for Field Instrument, JB Foundations | 14 | 14 | 2025-01-13 | 2025-01-28 | 2025-02-25 | 2025-03-15 | 11
C-56-591-01-CI-1420 | Concrete Works for Access Platform & Misc. Structural Foundations | 12 | 12 | 2025-01-29 | 2025-02-11 | 2025-03-15 | 2025-04-05 | 11
C-56-591-01-CI-1430 | Concrete Works for Light Pole, Fence & Gates Foundation | 21 | 21 | 2025-02-12 | 2025-03-09 | 2025-04-05 | 2025-04-30 | 33
Concrete Works (Foundations for Pipe Supports) CCOB156C32 |  | 21 | 21 | 2025-01-24 | 2025-02-17 | 2025-02-21 | 2025-03-22 | 109
C-56-591-01-CI-1600 | Concrete Works for Pipe Support Foundations | 21 | 21 | 2025-01-24 | 2025-02-17 | 2025-02-21 | 2025-03-22 | 109
Trenching for Cables CCOB156C33 |  | 51 | 51 | 2025-01-02 | 2025-03-01 | 2025-02-14 | 2025-04-24 | 78
C-56-591-01-CI-1800 | Electrical & Earthing Cable Trenching | 30 | 30 | 2025-01-02 | 2025-02-05 | 2025-02-14 | 2025-03-26 | 78
C-56-591-01-CI-1810 | Instrument & Telecom Cable Trenching | 21 | 21 | 2025-02-06 | 2025-03-01 | 2025-03-26 | 2025-04-24 | 78
Pipe Supports Fabrication & Installation CCOB156S50 |  | 14 | 14 | 2025-03-05 | 2025-03-26 | 2025-03-11 | 2025-04-04 | 109
C-56-591-01-CI-2000 | Pre-Fabrication & Installation of Pipe Supports | 14 | 14 | 2025-03-05 | 2025-03-26 | 2025-03-11 | 2025-04-04 | 109
Fences & Gates Construction CCOB156C31 |  | 79 | 79 | 2025-03-25 | 2025-08-09 | 2025-04-30 | 2025-08-05 | 33
C-56-591-01-CI-2200 | Installation of Concrete Pillers for Boundary Wall | 21 | 21 | 2025-03-25 | 2025-04-23 | 2025-04-30 | 2025-05-26 | 33
C-56-591-01-CI-2210 | Block Works for Boundary Wall | 21 | 21 | 2025-04-07 | 2025-05-01 | 2025-05-09 | 2025-06-03 | 33
C-56-591-01-CI-2220 | Installation of Fence Post & Mesh Works (Type-4 & 3) | 30 | 30 | 2025-06-10 | 2025-07-16 | 2025-06-03 | 2025-07-11 | 33
C-56-591-01-CI-2230 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | 21 | 21 | 2025-07-16 | 2025-08-09 | 2025-07-11 | 2025-08-05 | 33
Fire Point Shelters CCOB156S52 |  | 8 | 8 | 2025-04-08 | 2025-04-17 | 2025-04-12 | 2025-04-22 | 116
C-56-591-01-CI-2400 | Installation of Fire Point Shelters | 8 | 8 | 2025-04-08 | 2025-04-17 | 2025-04-12 | 2025-04-22 | 116
Paving Works CCOB156C35 |  | 31 | 31 | 2025-08-01 | 2025-09-10 | 2025-07-19 | 2025-08-25 | 33
C-56-591-01-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 26 | 26 | 2025-08-01 | 2025-09-01 | 2025-07-19 | 2025-08-19 | 33
C-56-591-01-CI-2610 | Rip-Rap Protection Laying | 26 | 26 | 2025-08-09 | 2025-09-10 | 2025-07-25 | 2025-08-25 | 33
Backfilling for Cables CCOB156C37 |  | 15 | 15 | 2025-05-27 | 2025-06-16 | 2025-05-17 | 2025-06-04 | 99
C-56-591-01-CI-2800 | Back Filling for Electrical & Earthing Cable | 14 | 14 | 2025-05-27 | 2025-06-14 | 2025-05-17 | 2025-06-03 | 100
C-56-591-01-CI-2810 | Back Filling for Instrument & Telecom Cable | 14 | 14 | 2025-05-28 | 2025-06-16 | 2025-05-19 | 2025-06-04 | 99
Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOB156S54 |  | 42 | 42 | 2025-03-26 | 2025-05-20 | 2025-04-04 | 2025-05-24 | 109
C-56-591-01-CI-3000 | Pre-Fabrication & Installation of Platforms & Crossovers | 28 | 28 | 2025-03-26 | 2025-05-02 | 2025-04-04 | 2025-05-08 | 109
C-56-591-01-CI-3010 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | 14 | 14 | 2025-05-02 | 2025-05-20 | 2025-05-08 | 2025-05-24 | 109
Mechanical Works & Equipment Installation |  | 8 | 8 | 2025-07-17 | 2025-07-26 | 2025-05-07 | 2025-05-16 | 116
Mechanical Works and Equipment Installation (Fire Fighting Equipment) CCOB156M50 |  | 8 | 8 | 2025-07-17 | 2025-07-26 | 2025-05-07 | 2025-05-16 | 116
C-56-591-01-ME-1000 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | 8 | 8 | 2025-07-17 | 2025-07-26 | 2025-05-07 | 2025-05-16 | 116
Piping Works |  | 121 | 121 | 2025-02-13 | 2025-04-22 | 2025-02-24 | 2025-07-28 | 56
Piping Pre-Fabrication CCOB156P100 |  | 21 | 21 | 2025-02-13 | 2025-03-11 | 2025-02-24 | 2025-03-24 | 127
C-56-591-01-PI-1000 | Piping Pre-Fabrication | 21 | 21 | 2025-02-13 | 2025-03-11 | 2025-02-24 | 2025-03-24 | 127
Erection CCOB156P110 |  | 14 | 14 | 2025-03-11 | 2025-04-04 | 2025-03-28 | 2025-04-17 | 125
C-56-591-01-PI-1200 | Piping Erection | 14 | 14 | 2025-03-11 | 2025-04-04 | 2025-03-28 | 2025-04-17 | 125
Field Joint Welding & NDT CCOB156P120 |  | 15 | 15 | 2025-03-14 | 2025-04-08 | 2025-04-03 | 2025-04-21 | 125
C-56-591-01-PI-1400 | Field Joint Welding (Including Isolation Joint) | 12 | 12 | 2025-03-14 | 2025-04-04 | 2025-04-03 | 2025-04-17 | 125
C-56-591-01-PI-1410 | NDT & Coating for Field Joint Weld | 12 | 12 | 2025-03-19 | 2025-04-08 | 2025-04-07 | 2025-04-21 | 125
Hydrotesting CCOB156P130 |  | 5 | 5 | 2025-04-08 | 2025-04-14 | 2025-04-21 | 2025-04-26 | 125
C-56-591-01-PI-1600 | Hydrotesting | 5 | 5 | 2025-04-08 | 2025-04-14 | 2025-04-21 | 2025-04-26 | 125
Installation of Valves CCOB156P140 |  | 5 | 5 | 2025-04-14 | 2025-04-19 | 2025-07-21 | 2025-07-25 | 56
C-56-591-01-PI-1800 | Installation of Valves & GOV | 5 | 5 | 2025-04-14 | 2025-04-19 | 2025-07-21 | 2025-07-25 | 56
Final Bolt Torquing/ Re-Instatement CCOB156P150 |  | 3 | 3 | 2025-04-18 | 2025-04-22 | 2025-07-25 | 2025-07-28 | 56
C-56-591-01-PI-2000 | Final Bolt Torquing/ Re-Instatement | 3 | 3 | 2025-04-18 | 2025-04-22 | 2025-07-25 | 2025-07-28 | 56
Pipeline Works |  | 98 | 98 | 2025-03-11 | 2025-04-22 | 2025-03-25 | 2025-07-25 | 58
Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 |  | 98 | 98 | 2025-03-11 | 2025-04-22 | 2025-03-25 | 2025-07-25 | 58
C-56-591-01-PL-1000 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | 5 | 5 | 2025-03-11 | 2025-03-18 | 2025-03-25 | 2025-04-04 | 127
C-56-591-01-PL-1010 | Lowering of Pipeline Section | 2 | 2 | 2025-03-19 | 2025-03-22 | 2025-04-04 | 2025-04-07 | 127
C-56-591-01-PL-1020 | Section Tie-in Welding (Including Barred Tee) | 12 | 12 | 2025-03-19 | 2025-04-08 | 2025-04-04 | 2025-04-18 | 127
C-56-591-01-PL-1030 | NDT for Tie-in Joint | 12 | 12 | 2025-03-20 | 2025-04-09 | 2025-04-05 | 2025-04-19 | 127
C-56-591-01-PL-1040 | Ext. Coating for Tie-in Joint | 12 | 12 | 2025-03-22 | 2025-04-10 | 2025-04-07 | 2025-04-21 | 127
C-56-591-01-PL-1050 | Holiday Testing of Pipeline Section | 1 | 1 | 2025-04-10 | 2025-04-11 | 2025-04-21 | 2025-04-22 | 127
C-56-591-01-PL-1060 | Installation of ROV | 1 | 1 | 2025-04-11 | 2025-04-12 | 2025-07-21 | 2025-07-21 | 58
C-56-591-01-PL-1070 | Installation of Pig Signaller Pit | 3 | 3 | 2025-04-12 | 2025-04-16 | 2025-07-22 | 2025-07-24 | 58
C-56-591-01-PL-1080 | Installation of Pig Signaller | 1 | 1 | 2025-04-16 | 2025-04-17 | 2025-07-25 | 2025-07-25 | 58
C-56-591-01-PL-1090 | Padding & Backfilling | 9 | 9 | 2025-04-11 | 2025-04-22 | 2025-07-16 | 2025-07-25 | 58
Electrical & Instrumentation Works |  | 147 | 147 | 2025-03-15 | 2025-08-29 | 2025-03-22 | 2025-09-20 | 11
Hybrid Passive Cooling Shelter Installation CCOB156E30 |  | 3 | 3 | 2025-07-21 | 2025-07-24 | 2025-08-11 | 2025-08-14 | 11
C-56-591-01-EI-1000 | Installation of Passive Cooling Shelter | 3 | 3 | 2025-07-21 | 2025-07-24 | 2025-08-11 | 2025-08-14 | 11
Solar Power System CCOB156E44 |  | 26 | 26 | 2025-07-01 | 2025-07-31 | 2025-07-22 | 2025-08-21 | 11
C-56-591-01-EI-1210 | Installation of Solar Panel Structural Supports | 12 | 12 | 2025-07-01 | 2025-07-15 | 2025-07-22 | 2025-08-05 | 11
C-56-591-01-EI-1200 | Installation of Solar S/m (Including Panels, UPS & Battery) | 14 | 14 | 2025-07-15 | 2025-07-31 | 2025-08-05 | 2025-08-21 | 11
Deep Earth Well CCOB156E32 |  | 3 | 3 | 2025-05-01 | 2025-05-03 | 2025-04-22 | 2025-04-24 | 77
C-56-591-01-EI-1400 | Deep Earth Well Drilling | 3 | 3 | 2025-05-01 | 2025-05-03 | 2025-04-22 | 2025-04-24 | 77
RTU CCOB156E84 |  | 2 | 2 | 2025-07-24 | 2025-07-26 | 2025-08-14 | 2025-08-16 | 11
C-56-591-01-EI-1600 | Installation of RTU | 2 | 2 | 2025-07-24 | 2025-07-26 | 2025-08-14 | 2025-08-16 | 11
Light Pole, Lighting & Fixtures CCOB156E54 |  | 8 | 8 | 2025-07-29 | 2025-08-07 | 2025-08-19 | 2025-08-28 | 25
C-56-591-01-EI-1810 | Installation of Lighting & Instrument JB's | 3 | 3 | 2025-07-29 | 2025-08-01 | 2025-08-19 | 2025-08-22 | 11
C-56-591-01-EI-1800 | Installation of Light Pole, Lighting & Fixtures | 6 | 6 | 2025-07-31 | 2025-08-07 | 2025-08-21 | 2025-08-28 | 25
E&I Cable Laying, Glanding & Termination CCOB156E34 |  | 129 | 129 | 2025-04-28 | 2025-08-29 | 2025-04-18 | 2025-09-20 | 11
C-56-591-01-EI-2000 | Electrical & Earthing Cable Laying | 6 | 6 | 2025-04-28 | 2025-05-03 | 2025-04-18 | 2025-04-24 | 77
C-56-591-01-CA-1000 | CP Cable Laying | 5 | 5 | 2025-05-05 | 2025-05-10 | 2025-04-25 | 2025-04-30 | 100
C-56-591-01-EI-2010 | Instrument Cable Laying | 6 | 6 | 2025-05-05 | 2025-05-12 | 2025-04-25 | 2025-05-01 | 77
C-56-591-01-CA-1010 | Installation of CP Test Post | 3 | 3 | 2025-05-10 | 2025-05-14 | 2025-05-01 | 2025-05-03 | 119
C-56-591-01-EI-2020 | Installation of Cable Trays | 6 | 6 | 2025-05-12 | 2025-05-19 | 2025-05-02 | 2025-05-09 | 77
C-56-591-01-CA-1020 | Installation of CP S/m | 6 | 6 | 2025-05-14 | 2025-05-21 | 2025-05-05 | 2025-05-12 | 119
C-56-591-01-EI-2030 | Instrument Tubing Works | 5 | 5 | 2025-05-19 | 2025-05-24 | 2025-05-09 | 2025-05-15 | 77
C-56-591-01-EI-2040 | Loop Checking for Instruments | 8 | 8 | 2025-08-14 | 2025-08-23 | 2025-09-04 | 2025-09-15 | 11
C-56-591-01-EI-2050 | Glanding & Termination | 5 | 5 | 2025-08-23 | 2025-08-29 | 2025-09-15 | 2025-09-20 | 11
Field Instruments CCOB156E64 |  | 129 | 129 | 2025-03-15 | 2025-08-08 | 2025-03-22 | 2025-08-29 | 11
C-56-591-01-EI-2210 | Pre-Fabrication & Installation of Field Instrument, JB Supports | 14 | 14 | 2025-03-15 | 2025-04-08 | 2025-03-22 | 2025-04-12 | 116
C-56-591-01-EI-2200 | Installation of Field Instruments | 6 | 6 | 2025-08-01 | 2025-08-08 | 2025-08-22 | 2025-08-29 | 11
F&G Devices CCOB156E74 |  | 16 | 16 | 2025-07-26 | 2025-08-14 | 2025-08-16 | 2025-09-04 | 11
C-56-591-01-EI-2400 | Installation of F&G Panel | 2 | 2 | 2025-07-26 | 2025-07-29 | 2025-08-16 | 2025-08-19 | 11
C-56-591-01-EI-2410 | Installation of F&G Devices | 5 | 5 | 2025-08-08 | 2025-08-14 | 2025-08-29 | 2025-09-04 | 11
Telecommunication Works |  | 17 | 17 | 2025-05-28 | 2025-06-18 | 2025-05-28 | 2025-06-18 | 89
SDH Cabinet CCOB156I20 |  | 3 | 3 | 2025-05-28 | 2025-05-30 | 2025-05-28 | 2025-05-30 | 89
C-56-591-01-TE-1000 | Installation of SDH Cabinet | 3 | 3 | 2025-05-28 | 2025-05-30 | 2025-05-28 | 2025-05-30 | 89
PIDS System CCOB156I30 |  | 3 | 3 | 2025-05-31 | 2025-06-03 | 2025-05-31 | 2025-06-03 | 89
C-56-591-01-TE-1200 | Installation of PIDS/ PLDS System | 3 | 3 | 2025-05-31 | 2025-06-03 | 2025-05-31 | 2025-06-03 | 89
Telephone System CCOB156I40 |  | 6 | 6 | 2025-06-12 | 2025-06-18 | 2025-06-12 | 2025-06-18 | 89
C-56-591-01-TE-1400 | Installation of Telephone System | 6 | 6 | 2025-06-12 | 2025-06-18 | 2025-06-12 | 2025-06-18 | 89
CCTV System CCOB156I50 |  | 5 | 5 | 2025-06-04 | 2025-06-11 | 2025-06-04 | 2025-06-11 | 89
C-56-591-01-TE-1600 | Installation of CCTV System | 5 | 5 | 2025-06-04 | 2025-06-11 | 2025-06-04 | 2025-06-11 | 89
HGCP 52" P/L to Sweihan CRS 52'' P/R (52'') |  | 547 | 292 | 2023-12-18 | 2025-11-01 | 18-Dec-23 A | 2025-10-21 | 17
Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 |  | 178 | 0 | 2023-12-18 | 2024-07-26 | 18-Dec-23 A | 26-Jul-24 A
C-52-HG01-PL-CI-1000 | Survey Marking HGCP to BVS-01 | 106 | 0 | 2023-12-18 | 2024-04-30 | 18-Dec-23 A | 30-Apr-24 A
C-52-0102-PL-CI-1000 | Survey Marking BVS-01 to BVS-02 | 45 | 0 | 2024-03-01 | 2024-05-02 | 01-Mar-24 A | 02-May-24 A
C-52-0203-PL-CI-1000 | Survey Marking BVS-02 to BVS-03 | 79 | 0 | 2024-01-26 | 2024-05-07 | 26-Jan-24 A | 07-May-24 A
C-52-0304-PL-CI-1000 | Survey Marking BVS-03 to BVS-04 | 49 | 0 | 2024-03-01 | 2024-05-07 | 01-Mar-24 A | 07-May-24 A
C-52-0405-PL-CI-1000 | Survey Marking BVS-04 to BVS-05 | 9 | 0 | 2024-04-26 | 2024-05-07 | 26-Apr-24 A | 07-May-24 A
C-52-06CR-PL-CI-1000 | Survey Marking BVS-06 to Sweihan CRS | 40 | 0 | 2024-06-06 | 2024-07-26 | 06-Jun-24 A | 26-Jul-24 A
C-52-0506-PL-CI-1000 | Survey Marking BVS-05 to BVS-06 | 39 | 0 | 2024-06-06 | 2024-07-26 | 06-Jun-24 A | 26-Jul-24 A
52"x33.4 Km Pipeline from HGCP Compressor Station to BVS-01 at KP 33.4 |  | 423 | 168 | 2023-12-18 | 2025-04-17 | 18-Dec-23 A | 2025-05-24 | 124
52"x33.4 Km Pipeline from HGCP Compressor Station to BVS-01 at KP 33.4 |  | 423 | 168 | 2023-12-18 | 2025-04-17 | 18-Dec-23 A | 2025-05-24 | 124
Main Pipeline |  | 347 | 92 | 2023-12-18 | 2025-04-17 | 18-Dec-23 A | 2025-02-14 | 56
Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 1&2)CCOPL52303.1 |  | 177 | 0 | 2023-12-18 | 2024-07-26 | 18-Dec-23 A | 26-Jul-24 A
C-52-HG01-PL-CI-1800 | Sabka ROW/Grading | 106 | 0 | 2023-12-18 | 2024-04-30 | 18-Dec-23 A | 30-Apr-24 A
C-52-HG01-PL-CI-2000 | Sabka Gatch Laying (Including ROW) - Layer 1 | 175 | 0 | 2023-12-20 | 2024-07-26 | 20-Dec-23 A | 26-Jul-24 A
C-52-HG01-PL-CI-2010 | Sabka Gatch Laying - Layer 2 | 161 | 0 | 2024-01-06 | 2024-07-26 | 06-Jan-24 A | 26-Jul-24 A
Sabkha Pad Compaction from HGCP to BVS-01 (Layer 1&2) CCOPL52303.2 |  | 155 | 0 | 2024-01-13 | 2024-07-26 | 13-Jan-24 A | 26-Jul-24 A
C-52-HG01-PL-CI-2200 | Sabka Gatch Compaction (Including ROW) - Layer 1 | 135 | 0 | 2024-02-06 | 2024-07-26 | 06-Feb-24 A | 26-Jul-24 A
C-52-HG01-PL-CI-2210 | Sabka Gatch Compaction - Layer 2 | 155 | 0 | 2024-01-13 | 2024-07-26 | 13-Jan-24 A | 26-Jul-24 A
Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 3&4)CCOPL52303.3 |  | 150 | 0 | 2024-01-19 | 2024-07-26 | 19-Jan-24 A | 26-Jul-24 A
C-52-HG01-PL-CI-2020 | Sabka Gatch Laying - Layer 3 | 150 | 0 | 2024-01-19 | 2024-07-26 | 19-Jan-24 A | 26-Jul-24 A
C-52-HG01-PL-CI-2030 | Sabka Gatch Laying - Layer 4 | 146 | 0 | 2024-01-24 | 2024-07-26 | 24-Jan-24 A | 26-Jul-24 A
Sabkha Pad Compaction from HGCP to BVS-01 (Layer 3&4)CCOPL52303.4 |  | 146 | 0 | 2024-01-24 | 2024-07-26 | 24-Jan-24 A | 26-Jul-24 A
C-52-HG01-PL-CI-2220 | Sabka Gatch Compaction - Layer 3 | 146 | 0 | 2024-01-24 | 2024-07-26 | 24-Jan-24 A | 26-Jul-24 A
C-52-HG01-PL-CI-2230 | Sabka Gatch Compaction - Layer 4 | 145 | 0 | 2024-01-25 | 2024-07-26 | 25-Jan-24 A | 26-Jul-24 A
Excavation (incl Bedding)CCOPL52306 |  | 89 | 16 | 2024-09-14 | 2025-01-09 | 14-Aug-24 A | 2024-11-27 | 69
C-52-HG01-PL-CI-2400 | Trench Excavation-Lot1 | 28 | 0 | 2024-09-14 | 2024-10-23 | 14-Aug-24 A | 18-Sep-24 A
C-52-HG01-PL-CI-2410 | Bedding-Lot1 | 34 | 0 | 2024-09-24 | 2024-10-31 | 19-Aug-24 A | 30-Sep-24 A
C-52-HG01-PL-CI-2600 | Trench Excavation-Lot2 | 58 | 14 | 2024-11-27 | 2025-01-07 | 19-Sep-24 A | 2024-11-25 | 69
C-52-HG01-PL-CI-2610 | Bedding-Lot2 | 60 | 14 | 2024-11-29 | 2025-01-09 | 19-Sep-24 A | 2024-11-27 | 69
Pipe Stringing from HGCP to KP 16.7CCOPL52305.1 |  | 30 | 0 | 2024-06-19 | 2024-07-26 | 19-Jun-24 A | 26-Jul-24 A
C-52-HG01-PL-ME-2800 | Stringing-Lot1 | 30 | 0 | 2024-06-19 | 2024-07-26 | 19-Jun-24 A | 26-Jul-24 A
Pipe Stringing from KP 16.7 to BVS-01CCOPL52305.2 |  | 97 | 20 | 2024-07-27 | 2024-08-14 | 27-Jul-24 A | 2024-11-18 | 17
C-52-HG01-PL-ME-3000 | Stringing-Lot2 | 97 | 20 | 2024-07-27 | 2024-08-14 | 27-Jul-24 A | 2024-11-18 | 17
Automatic WeldingCCOPL52308 |  | 108 | 23 | 2024-07-18 | 2024-09-28 | 18-Jul-24 A | 2024-11-21 | 20
C-52-HG01-PL-ME-3600 | Automatic Welding-Lot1 | 42 | 0 | 2024-07-18 | 2024-08-28 | 18-Jul-24 A | 05-Sep-24 A
C-52-HG01-PL-ME-3800 | Automatic Welding-Lot2 | 65 | 23 | 2024-08-28 | 2024-09-28 | 06-Sep-24 A | 2024-11-21 | 20
NDT TestCCOPL52309 |  | 110 | 14 | 2024-07-18 | 2024-10-01 | 18-Jul-24 A | 2024-11-23 | 74
C-52-HG01-PL-ME-4000 | NDT-Lot1 | 42 | 0 | 2024-07-18 | 2024-08-29 | 18-Jul-24 A | 05-Sep-24 A
C-52-HG01-PL-ME-4200 | NDT-Lot2 | 110 | 14 | 2024-08-30 | 2024-10-01 | 18-Jul-24 A | 2024-11-23 | 74
Cold BendsCCOPL52307 |  | 37 | 0 | 2024-07-18 | 2024-12-31 | 18-Jul-24 A | 29-Aug-24 A
C-52-HG01-PL-ME-3200 | Cold Bends-Lot1 | 32 | 0 | 2024-07-18 | 2024-11-29 | 18-Jul-24 A | 23-Aug-24 A
C-52-HG01-PL-ME-3400 | Cold Bends-Lot2 | 28 | 0 | 2024-11-29 | 2024-12-31 | 27-Jul-24 A | 29-Aug-24 A
Pipe Lowering & Tie-in / NDTCCOPL52313 |  | 72 | 20 | 2024-09-30 | 2025-02-24 | 13-Sep-24 A | 2024-12-09 | 70
C-52-HG01-PL-ME-4800 | Lowering-Lot1 | 19 | 0 | 2024-09-30 | 2024-11-29 | 13-Sep-24 A | 07-Oct-24 A
C-52-HG01-PL-ME-4810 | Section Tie-in Welding -Lot1 | 19 | 0 | 2024-10-15 | 2024-12-26 | 13-Sep-24 A | 07-Oct-24 A
C-52-HG01-PL-ME-4820 | NDT (Tie-in Joint)-Lot1 | 19 | 0 | 2024-10-16 | 2024-12-27 | 13-Sep-24 A | 07-Oct-24 A
C-52-HG01-PL-ME-4830 | Holiday Testing-Lot1 | 19 | 0 | 2024-10-18 | 2024-12-30 | 13-Sep-24 A | 07-Oct-24 A
C-52-HG01-PL-ME-5000 | Lowering-Lot2 | 36 | 14 | 2024-12-06 | 2025-02-06 | 19-Oct-24 A | 2024-11-29 | 69
C-52-HG01-PL-ME-5010 | Section Tie-in Welding-Lot2 | 47 | 15 | 2024-12-26 | 2025-02-18 | 08-Oct-24 A | 2024-11-30 | 70
C-52-HG01-PL-ME-5020 | NDT (Tie-in Joint)-Lot2 | 49 | 15 | 2024-12-28 | 2025-02-20 | 08-Oct-24 A | 2024-12-05 | 70
C-52-HG01-PL-ME-5030 | Holiday Testing-Lot2 | 52 | 15 | 2025-01-02 | 2025-02-24 | 08-Oct-24 A | 2024-12-09 | 70
Ext. Joint CoatingCCOPL52311 |  | 106 | 24 | 2024-08-02 | 2025-02-22 | 02-Aug-24 A | 2024-12-07 | 70
C-52-HG01-PL-ME-4400 | Ext. Joint Coating-Lot1 | 37 | 0 | 2024-08-02 | 2024-08-31 | 02-Aug-24 A | 17-Sep-24 A
C-52-HG01-PL-ME-4410 | Ext. Joint Coating (Tie-in Joint)-Lot1 | 19 | 0 | 2024-10-17 | 2024-12-28 | 13-Sep-24 A | 07-Oct-24 A
C-52-HG01-PL-ME-4600 | Ext. Joint Coating-Lot2 | 60 | 16 | 2024-08-31 | 2024-10-02 | 18-Sep-24 A | 2024-11-26 | 74
C-52-HG01-PL-ME-4610 | Ext. Joint Coating (Tie-in Joint)-Lot2 | 51 | 16 | 2024-12-31 | 2025-02-22 | 08-Oct-24 A | 2024-12-07 | 70
Crossings OHPLCCOPL52325 |  | 40 | 40 | 2024-10-29 | 2024-12-17 | 2024-10-26 | 2024-12-13 | 108
Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) |  | 40 | 40 | 2024-10-29 | 2024-12-17 | 2024-10-26 | 2024-12-13 | 108
C-52-HG01-CMA01-0970 | Excavation (Manual-Trial Pit) | 21 | 21 | 2024-10-29 | 2024-11-22 | 2024-10-26 | 2024-11-19 | 108
C-52-HG01-CMA01-0980 | Sabkha Gatch Laying | 7 | 7 | 2024-11-22 | 2024-11-30 | 2024-11-20 | 2024-11-27 | 108
C-52-HG01-CMA01-0990 | Sabka Gatch Compaction | 7 | 7 | 2024-11-23 | 2024-12-04 | 2024-11-21 | 2024-11-28 | 108
C-52-HG01-CMA01-1000 | Trench Excavation | 3 | 3 | 2024-12-04 | 2024-12-07 | 2024-11-29 | 2024-12-04 | 108
C-52-HG01-CMA01-1010 | Bedding | 2 | 2 | 2024-12-06 | 2024-12-09 | 2024-12-04 | 2024-12-05 | 108
C-52-HG01-CMA01-1020 | Lowering | 1 | 1 | 2024-12-09 | 2024-12-10 | 2024-12-06 | 2024-12-06 | 108
C-52-HG01-CMA01-1030 | Section Tie-in Welding | 3 | 3 | 2024-12-09 | 2024-12-12 | 2024-12-06 | 2024-12-09 | 108
C-52-HG01-CMA01-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-12-10 | 2024-12-13 | 2024-12-07 | 2024-12-10 | 108
C-52-HG01-CMA01-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-12-11 | 2024-12-14 | 2024-12-09 | 2024-12-11 | 108
C-52-HG01-CMA01-1060 | Holiday Testing | 1 | 1 | 2024-12-14 | 2024-12-16 | 2024-12-12 | 2024-12-12 | 108
C-52-HG01-CMA01-1070 | Padding | 1 | 1 | 2024-12-16 | 2024-12-17 | 2024-12-13 | 2024-12-13 | 108
Crossings - UG PipeCCOPL52312 |  | 123 | 22 | 2024-11-04 | 2024-12-13 | 19-Jul-24 A | 2024-12-12 | 109
Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) |  | 22 | 22 | 2024-11-04 | 2024-11-29 | 2024-11-15 | 2024-12-12 | 109
C-52-HG01-CMA02-0970 | Excavation (Manual-Trial Pit) | 8 | 8 | 2024-11-04 | 2024-11-13 | 2024-11-15 | 2024-11-23 | 109
C-52-HG01-CMA02-0980 | Sabkha Gatch Laying | 5 | 5 | 2024-11-13 | 2024-11-19 | 2024-11-25 | 2024-11-29 | 109
C-52-HG01-CMA02-0990 | Sabka Gatch Compaction | 5 | 5 | 2024-11-14 | 2024-11-20 | 2024-11-26 | 2024-11-30 | 109
C-52-HG01-CMA02-1000 | Trench Excavation | 2 | 2 | 2024-11-20 | 2024-11-22 | 2024-12-04 | 2024-12-05 | 109
C-52-HG01-CMA02-1010 | Bedding | 1 | 1 | 2024-11-21 | 2024-11-22 | 2024-12-05 | 2024-12-05 | 109
C-52-HG01-CMA02-1020 | Lowering | 1 | 1 | 2024-11-22 | 2024-11-23 | 2024-12-06 | 2024-12-06 | 109
C-52-HG01-CMA02-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-22 | 2024-11-25 | 2024-12-06 | 2024-12-07 | 109
C-52-HG01-CMA02-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-23 | 2024-11-26 | 2024-12-07 | 2024-12-09 | 109
C-52-HG01-CMA02-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-25 | 2024-11-27 | 2024-12-09 | 2024-12-10 | 109
C-52-HG01-CMA02-1060 | Holiday Testing | 1 | 1 | 2024-11-27 | 2024-11-28 | 2024-12-11 | 2024-12-11 | 109
C-52-HG01-CMA02-1070 | Padding | 1 | 1 | 2024-11-28 | 2024-11-29 | 2024-12-12 | 2024-12-12 | 109
Crossing Manual @ KP 25+127 (PX-05) |  | 44 | 2 | 2024-11-13 | 2024-12-07 | 04-Oct-24 A | 2024-11-23 | 123
C-52-HG01-CMA03-0970 | Excavation (Manual-Trial Pit) | 5 | 0 | 2024-11-13 | 2024-11-19 | 04-Oct-24 A | 09-Oct-24 A
C-52-HG01-CMA03-0980 | Sabkha Gatch Laying | 5 | 0 | 2024-11-19 | 2024-11-25 | 05-Oct-24 A | 10-Oct-24 A
C-52-HG01-CMA03-0990 | Sabka Gatch Compaction | 5 | 0 | 2024-11-20 | 2024-11-26 | 06-Oct-24 A | 11-Oct-24 A
C-52-HG01-CMA03-1000 | Trench Excavation | 5 | 0 | 2024-11-26 | 2024-11-28 | 12-Oct-24 A | 18-Oct-24 A
C-52-HG01-CMA03-1010 | Bedding | 5 | 0 | 2024-11-27 | 2024-11-28 | 12-Oct-24 A | 18-Oct-24 A
C-52-HG01-CMA03-1030 | Section Tie-in Welding | 6 | 0 | 2024-11-28 | 2024-11-30 | 18-Oct-24 A | 25-Oct-24 A
C-52-HG01-CMA03-1040 | NDT (Tie-in Joint) | 6 | 0 | 2024-11-29 | 2024-12-04 | 18-Oct-24 A | 25-Oct-24 A
C-52-HG01-CMA03-1050 | Ext. Joint Coating (Tie-in Joint) | 4 | 0 | 2024-11-30 | 2024-12-05 | 20-Oct-24 A | 25-Oct-24 A
C-52-HG01-CMA03-1060 | Holiday Testing | 4 | 0 | 2024-12-05 | 2024-12-06 | 20-Oct-24 A | 25-Oct-24 A
C-52-HG01-CMA03-1020 | Lowering | 1 | 1 | 2024-11-28 | 2024-11-29 | 2024-11-22 | 2024-11-22 | 123
C-52-HG01-CMA03-1070 | Padding | 1 | 1 | 2024-12-06 | 2024-12-07 | 2024-11-23 | 2024-11-23 | 123
Crossing Manual @ KP 28+089 (PX-06) |  | 103 | 2 | 2024-11-19 | 2024-12-13 | 19-Jul-24 A | 2024-11-16 | 129
C-52-HG01-CMA04-0970 | Excavation (Manual-Trial Pit) | 26 | 0 | 2024-11-19 | 2024-11-25 | 19-Jul-24 A | 19-Aug-24 A
C-52-HG01-CMA04-0980 | Sabkha Gatch Laying | 26 | 0 | 2024-11-25 | 2024-11-30 | 19-Jul-24 A | 19-Aug-24 A
C-52-HG01-CMA04-0990 | Sabka Gatch Compaction | 26 | 0 | 2024-11-26 | 2024-12-04 | 19-Jul-24 A | 19-Aug-24 A
C-52-HG01-CMA04-1000 | Trench Excavation | 26 | 0 | 2024-12-04 | 2024-12-06 | 19-Jul-24 A | 19-Aug-24 A
C-52-HG01-CMA04-1010 | Bedding | 26 | 0 | 2024-12-05 | 2024-12-06 | 19-Jul-24 A | 19-Aug-24 A
C-52-HG01-CMA04-1030 | Section Tie-in Welding | 6 | 0 | 2024-12-06 | 2024-12-09 | 18-Oct-24 A | 25-Oct-24 A
C-52-HG01-CMA04-1040 | NDT (Tie-in Joint) | 6 | 0 | 2024-12-07 | 2024-12-10 | 18-Oct-24 A | 25-Oct-24 A
C-52-HG01-CMA04-1050 | Ext. Joint Coating (Tie-in Joint) | 4 | 0 | 2024-12-09 | 2024-12-11 | 20-Oct-24 A | 25-Oct-24 A
C-52-HG01-CMA04-1060 | Holiday Testing | 4 | 0 | 2024-12-11 | 2024-12-12 | 20-Oct-24 A | 25-Oct-24 A
C-52-HG01-CMA04-1020 | Lowering | 1 | 1 | 2024-12-06 | 2024-12-07 | 2024-11-15 | 2024-11-15 | 129
C-52-HG01-CMA04-1070 | Padding | 1 | 1 | 2024-12-12 | 2024-12-13 | 2024-11-16 | 2024-11-16 | 129
Crossings - FenceCCOPL52323 |  | 19 | 19 | 2024-11-22 | 2024-12-20 | 2024-11-20 | 2024-12-13 | 108
Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) |  | 19 | 19 | 2024-11-22 | 2024-12-20 | 2024-11-20 | 2024-12-13 | 108
C-52-HG01-CMA05-0970 | Excavation (Manual-Trial Pit) | 5 | 5 | 2024-11-22 | 2024-12-04 | 2024-11-20 | 2024-11-25 | 108
C-52-HG01-CMA05-0980 | Sabkha Gatch Laying | 5 | 5 | 2024-12-04 | 2024-12-10 | 2024-11-26 | 2024-11-30 | 108
C-52-HG01-CMA05-0990 | Sabka Gatch Compaction | 5 | 5 | 2024-12-05 | 2024-12-11 | 2024-11-27 | 2024-12-04 | 108
C-52-HG01-CMA05-1000 | Trench Excavation | 2 | 2 | 2024-12-11 | 2024-12-13 | 2024-12-05 | 2024-12-06 | 108
C-52-HG01-CMA05-1010 | Bedding | 1 | 1 | 2024-12-12 | 2024-12-13 | 2024-12-06 | 2024-12-06 | 108
C-52-HG01-CMA05-1020 | Lowering | 1 | 1 | 2024-12-13 | 2024-12-14 | 2024-12-07 | 2024-12-07 | 108
C-52-HG01-CMA05-1030 | Section Tie-in Welding | 2 | 2 | 2024-12-13 | 2024-12-16 | 2024-12-07 | 2024-12-09 | 108
C-52-HG01-CMA05-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-12-14 | 2024-12-17 | 2024-12-09 | 2024-12-10 | 108
C-52-HG01-CMA05-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-12-16 | 2024-12-18 | 2024-12-10 | 2024-12-11 | 108
C-52-HG01-CMA05-1060 | Holiday Testing | 1 | 1 | 2024-12-18 | 2024-12-19 | 2024-12-12 | 2024-12-12 | 108
C-52-HG01-CMA05-1070 | Padding | 1 | 1 | 2024-12-19 | 2024-12-20 | 2024-12-13 | 2024-12-13 | 108
Open Cut - Rig / Track RoadCCOPL52318 |  | 60 | 22 | 2024-10-02 | 2024-10-31 | 27-Sep-24 A | 2024-12-07 | 113
Crossing Mechanical (TX-01) |  | 52 | 2 | 2024-10-02 | 2024-10-24 | 27-Sep-24 A | 2024-11-26 | 121
C-52-HG01-CME01-1000 | Trench Excavation | 8 | 0 | 2024-10-02 | 2024-10-04 | 27-Sep-24 A | 06-Oct-24 A
C-52-HG01-CME01-1010 | Bedding | 8 | 0 | 2024-10-04 | 2024-10-07 | 27-Sep-24 A | 06-Oct-24 A
C-52-HG01-CME01-1020 | Lowering | 6 | 0 | 2024-10-07 | 2024-10-09 | 01-Oct-24 A | 08-Oct-24 A
C-52-HG01-CME01-1030 | Section Tie-in Welding | 6 | 0 | 2024-10-09 | 2024-10-12 | 10-Oct-24 A | 17-Oct-24 A
C-52-HG01-CME01-1040 | NDT (Tie-in Joint) | 6 | 0 | 2024-10-12 | 2024-10-16 | 10-Oct-24 A | 17-Oct-24 A
C-52-HG01-CME01-1050 | Ext. Joint Coating (Tie-in Joint) | 7 | 0 | 2024-10-16 | 2024-10-19 | 12-Oct-24 A | 20-Oct-24 A
C-52-HG01-CME01-1060 | Holiday Testing | 7 | 0 | 2024-10-19 | 2024-10-22 | 12-Oct-24 A | 20-Oct-24 A
C-52-HG01-CME01-1070 | Padding & Back Filling | 2 | 2 | 2024-10-22 | 2024-10-24 | 2024-11-25 | 2024-11-26 | 121
Crossing Mechanical (TX-03) |  | 19 | 19 | 2024-10-05 | 2024-10-28 | 2024-11-11 | 2024-12-04 | 116
C-52-HG01-CME02-1000 | Trench Excavation | 2 | 2 | 2024-10-05 | 2024-10-08 | 2024-11-11 | 2024-11-12 | 46
C-52-HG01-CME02-1010 | Bedding | 2 | 2 | 2024-10-08 | 2024-10-10 | 2024-11-13 | 2024-11-14 | 116
C-52-HG01-CME02-1020 | Lowering | 2 | 2 | 2024-10-10 | 2024-10-12 | 2024-11-15 | 2024-11-16 | 116
C-52-HG01-CME02-1030 | Section Tie-in Welding | 3 | 3 | 2024-10-12 | 2024-10-16 | 2024-11-18 | 2024-11-20 | 116
C-52-HG01-CME02-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-10-16 | 2024-10-19 | 2024-11-21 | 2024-11-23 | 116
C-52-HG01-CME02-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-10-19 | 2024-10-23 | 2024-11-25 | 2024-11-27 | 116
C-52-HG01-CME02-1060 | Holiday Testing | 2 | 2 | 2024-10-23 | 2024-10-25 | 2024-11-28 | 2024-11-29 | 116
C-52-HG01-CME02-1070 | Padding & Back Filling | 2 | 2 | 2024-10-25 | 2024-10-28 | 2024-11-30 | 2024-12-04 | 116
Crossing Mechanical (TX-04) |  | 19 | 19 | 2024-10-09 | 2024-10-31 | 2024-11-14 | 2024-12-07 | 113
C-52-HG01-CME03-1000 | Trench Excavation | 2 | 2 | 2024-10-09 | 2024-10-11 | 2024-11-14 | 2024-11-15 | 46
C-52-HG01-CME03-1010 | Bedding | 2 | 2 | 2024-10-11 | 2024-10-14 | 2024-11-16 | 2024-11-18 | 113
C-52-HG01-CME03-1020 | Lowering | 2 | 2 | 2024-10-14 | 2024-10-16 | 2024-11-19 | 2024-11-20 | 113
C-52-HG01-CME03-1030 | Section Tie-in Welding | 3 | 3 | 2024-10-16 | 2024-10-19 | 2024-11-21 | 2024-11-23 | 113
C-52-HG01-CME03-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-10-19 | 2024-10-23 | 2024-11-25 | 2024-11-27 | 113
C-52-HG01-CME03-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-10-23 | 2024-10-26 | 2024-11-28 | 2024-11-30 | 113
C-52-HG01-CME03-1060 | Holiday Testing | 2 | 2 | 2024-10-26 | 2024-10-29 | 2024-12-04 | 2024-12-05 | 113
C-52-HG01-CME03-1070 | Padding & Back Filling | 2 | 2 | 2024-10-29 | 2024-10-31 | 2024-12-06 | 2024-12-07 | 113
Crossings - UG CableCCOPL52322 |  | 165 | 6 | 2024-11-25 | 2024-12-28 | 15-May-24 A | 2024-11-28 | 119
Crossing Manual @ KP 1+477 (CX-01) |  | 50 | 2 | 2024-11-25 | 2024-12-19 | 27-Sep-24 A | 2024-11-23 | 123
C-52-HG01-CMA06-0970 | Excavation (Manual-Trial Pit) | 5 | 0 | 2024-11-25 | 2024-11-30 | 27-Sep-24 A | 03-Oct-24 A
C-52-HG01-CMA06-0980 | Sabkha Gatch Laying | 5 | 0 | 2024-11-30 | 2024-12-09 | 04-Oct-24 A | 09-Oct-24 A
C-52-HG01-CMA06-0990 | Sabka Gatch Compaction | 5 | 0 | 2024-12-04 | 2024-12-10 | 05-Oct-24 A | 10-Oct-24 A
C-52-HG01-CMA06-1000 | Trench Excavation | 5 | 0 | 2024-12-10 | 2024-12-12 | 12-Oct-24 A | 18-Oct-24 A
C-52-HG01-CMA06-1010 | Bedding | 5 | 0 | 2024-12-11 | 2024-12-12 | 12-Oct-24 A | 18-Oct-24 A
C-52-HG01-CMA06-1030 | Section Tie-in Welding | 4 | 0 | 2024-12-12 | 2024-12-14 | 19-Oct-24 A | 24-Oct-24 A
C-52-HG01-CMA06-1050 | Ext. Joint Coating (Tie-in Joint) | 4 | 0 | 2024-12-14 | 2024-12-17 | 20-Oct-24 A | 25-Oct-24 A
C-52-HG01-CMA06-1020 | Lowering | 1 | 1 | 2024-12-12 | 2024-12-13 | 2024-11-22 | 2024-11-22 | 123
C-52-HG01-CMA06-1040 | NDT (Tie-in Joint) | 30 | 0 | 2024-12-13 | 2024-12-16 | 19-Oct-24 A | 2024-11-23 | 123
C-52-HG01-CMA06-1060 | Holiday Testing | 29 | 0 | 2024-12-17 | 2024-12-18 | 20-Oct-24 A | 2024-11-23 | 123
C-52-HG01-CMA06-1070 | Padding | 1 | 1 | 2024-12-18 | 2024-12-19 | 2024-11-23 | 2024-11-23 | 123
Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) |  | 165 | 1 | 2024-11-30 | 2024-12-28 | 15-May-24 A | 2024-11-28 | 119
C-52-HG01-CMA07-0970 | Excavation (Manual-Trial Pit) | 48 | 0 | 2024-11-30 | 2024-12-12 | 15-May-24 A | 15-Jul-24 A
C-52-HG01-CMA07-0980 | Sabkha Gatch Laying | 48 | 0 | 2024-12-12 | 2024-12-18 | 15-May-24 A | 15-Jul-24 A
C-52-HG01-CMA07-0990 | Sabka Gatch Compaction | 48 | 0 | 2024-12-13 | 2024-12-19 | 15-May-24 A | 15-Jul-24 A
C-52-HG01-CMA07-1000 | Trench Excavation | 48 | 0 | 2024-12-19 | 2024-12-21 | 15-May-24 A | 15-Jul-24 A
C-52-HG01-CMA07-1010 | Bedding | 48 | 0 | 2024-12-20 | 2024-12-21 | 15-May-24 A | 15-Jul-24 A
C-52-HG01-CMA07-1020 | Lowering | 3 | 0 | 2024-12-21 | 2024-12-23 | 27-Sep-24 A | 01-Oct-24 A
C-52-HG01-CMA07-1030 | Section Tie-in Welding | 7 | 0 | 2024-12-21 | 2024-12-24 | 02-Oct-24 A | 10-Oct-24 A
C-52-HG01-CMA07-1040 | NDT (Tie-in Joint) | 7 | 0 | 2024-12-23 | 2024-12-25 | 02-Oct-24 A | 10-Oct-24 A
C-52-HG01-CMA07-1050 | Ext. Joint Coating (Tie-in Joint) | 8 | 0 | 2024-12-24 | 2024-12-26 | 03-Oct-24 A | 12-Oct-24 A
C-52-HG01-CMA07-1060 | Holiday Testing | 8 | 0 | 2024-12-26 | 2024-12-27 | 03-Oct-24 A | 12-Oct-24 A
C-52-HG01-CMA07-1070 | Padding | 1 | 1 | 2024-12-27 | 2024-12-28 | 2024-11-28 | 2024-11-28 | 119
CP Works TemporaryCCOP52EL56 |  | 102 | 15 | 2024-10-08 | 2025-02-08 | 15-Oct-24 A | 2025-02-14 | 46
C-52-HG01-PL-CA-5210 | Glanding & Termination of Temp. CP S/m | 102 | 15 | 2024-11-21 | 2025-02-08 | 15-Oct-24 A | 2025-02-13 | 46
C-52-HG01-PL-CA-5200 | Installation of CP Test Post | 102 | 15 | 2024-10-08 | 2024-12-25 | 15-Oct-24 A | 2025-02-14 | 46
Test Stations & Anode BedsCCOP52EL31 |  | 47 | 22 | 2024-10-08 | 2024-12-19 | 15-Oct-24 A | 2024-12-10 | 69
C-52-HG01-PL-CA-5600 | Installation of Temp. Anode | 47 | 22 | 2024-10-08 | 2024-12-19 | 15-Oct-24 A | 2024-12-10 | 69
PaddingCCOPL52310 |  | 75 | 39 | 2024-12-17 | 2025-04-11 | 13-Sep-24 A | 2024-12-12 | 69
C-52-HG01-PL-CI-6000 | Padding -Lot1 | 43 | 7 | 2024-12-17 | 2025-02-08 | 13-Sep-24 A | 2024-11-02 | 84
C-52-HG01-PL-CI-6200 | Padding -Lot2 | 44 | 15 | 2025-02-08 | 2025-04-11 | 21-Oct-24 A | 2024-12-12 | 69
BermingCCOPL52316 |  | 61 | 26 | 2025-02-13 | 2025-04-17 | 03-Oct-24 A | 2024-12-14 | 69
C-52-HG01-PL-CI-6800 | Gatch Laying & Levelling | 61 | 26 | 2025-02-13 | 2025-04-16 | 03-Oct-24 A | 2024-12-14 | 69
C-52-HG01-PL-CI-6810 | Gatch Compaction | 54 | 26 | 2025-02-14 | 2025-04-17 | 11-Oct-24 A | 2024-12-14 | 69
NDRC by Micro Tunneling Method |  | 316 | 147 | 2024-04-01 | 2025-01-31 | 01-Apr-24 A | 2025-04-29 | 108
Micro Tunnelling @ CH 28+767 - 28+879 (NDRC-04) |  | 217 | 48 | 2024-04-01 | 2024-10-02 | 01-Apr-24 A | 2024-12-23 | 90
Entry & Exit Pit ConstructionCCOPL52936 |  | 117 | 0 | 2024-04-01 | 2024-07-30 | 01-Apr-24 A | 25-Aug-24 A
C-52-HG01-CNM04-1000 | Sheet Piling for Driving & Receiving Pit | 44 | 0 | 2024-04-01 | 2024-05-28 | 01-Apr-24 A | 28-May-24 A
C-52-HG01-CNM04-1020 | Installation of Dewatering System for Driving & Receiving Pit | 25 | 0 | 2024-05-01 | 2024-05-30 | 01-May-24 A | 30-May-24 A
C-52-HG01-CNM04-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 30 | 0 | 2024-05-16 | 2024-06-24 | 16-May-24 A | 24-Jun-24 A
C-52-HG01-CNM04-1010 | Driving & Receiving Pit Excavation | 36 | 0 | 2024-05-29 | 2024-07-15 | 29-May-24 A | 15-Jul-24 A
C-52-HG01-CNM04-1040 | Floor Blinding & French Drain in Driving Pit | 26 | 0 | 2024-06-25 | 2024-07-26 | 25-Jun-24 A | 26-Jul-24 A
C-52-HG01-CNM04-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 34 | 0 | 2024-07-16 | 2024-07-30 | 16-Jul-24 A | 24-Aug-24 A
C-52-HG01-CNM04-1060 | Construction of Exit Wall with Ring | 35 | 0 | 2024-07-16 | 2024-07-30 | 16-Jul-24 A | 25-Aug-24 A
Tunneling & Jack UpCCOPL57332 |  | 16 | 0 | 2024-07-31 | 2024-09-14 | 25-Aug-24 A | 13-Sep-24 A
C-52-HG01-CNM04-1200 | Jacking of MTBM & RC Sleeves | 9 | 0 | 2024-07-31 | 2024-08-09 | 25-Aug-24 A | 04-Sep-24 A
C-52-HG01-CNM04-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 8 | 0 | 2024-08-10 | 2024-08-14 | 04-Sep-24 A | 13-Sep-24 A
C-52-HG01-CNM04-1220 | Inner Grout b/w Main & RC Pipe | 8 | 0 | 2024-09-10 | 2024-09-14 | 04-Sep-24 A | 13-Sep-24 A
Pipe Lowering, Welding, NDT & CoatingCCOPL57342 |  | 17 | 14 | 2024-08-15 | 2024-08-30 | 23-Oct-24 A | 2024-11-11 | 90
C-52-HG01-CNM04-1400 | Lowering & Welding of Carrier Pipe | 13 | 10 | 2024-08-15 | 2024-08-27 | 23-Oct-24 A | 2024-11-06 | 80
C-52-HG01-CNM04-1410 | NDT, Coating & Holiday Inspection of Carrier Pipe | 17 | 14 | 2024-08-16 | 2024-08-30 | 23-Oct-24 A | 2024-11-11 | 90
HydrotestingCCOPL57352 |  | 12 | 12 | 2024-08-31 | 2024-09-09 | 2024-11-21 | 2024-12-06 | 90
C-52-HG01-CNM04-1600 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 12 | 12 | 2024-08-31 | 2024-09-09 | 2024-11-21 | 2024-12-06 | 90
Re-Instatement of Entry & Exit PitCCOPL57362 |  | 14 | 14 | 2024-09-17 | 2024-10-02 | 2024-12-07 | 2024-12-23 | 90
C-52-HG01-CNM04-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2024-09-17 | 2024-10-02 | 2024-12-07 | 2024-12-23 | 90
Micro Tunnelling @ CH 05+388 - 05+488 (NDRC-03) |  | 206 | 48 | 2024-05-01 | 2024-10-22 | 01-May-24 A | 2025-01-04 | 80
Entry & Exit Pit ConstructionCCOPL52930 |  | 116 | 0 | 2024-05-01 | 2024-08-21 | 01-May-24 A | 19-Sep-24 A
C-52-HG01-CNM03-1000 | Sheet Piling for Driving & Receiving Pit | 37 | 0 | 2024-05-01 | 2024-06-13 | 01-May-24 A | 13-Jun-24 A
C-52-HG01-CNM03-1020 | Installation of Dewatering System for Driving & Receiving Pit | 33 | 0 | 2024-05-05 | 2024-06-13 | 05-May-24 A | 13-Jun-24 A
C-52-HG01-CNM03-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 43 | 0 | 2024-06-24 | 2024-07-30 | 24-Jun-24 A | 14-Aug-24 A
C-52-HG01-CNM03-1010 | Driving & Receiving Pit Excavation | 85 | 0 | 2024-05-28 | 2024-07-31 | 28-May-24 A | 09-Sep-24 A
C-52-HG01-CNM03-1040 | Floor Blinding & French Drain in Driving Pit | 25 | 0 | 2024-07-30 | 2024-08-06 | 16-Aug-24 A | 14-Sep-24 A
C-52-HG01-CNM03-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 15 | 0 | 2024-08-06 | 2024-08-13 | 28-Aug-24 A | 14-Sep-24 A
C-52-HG01-CNM03-1060 | Construction of Exit Wall with Ring | 2 | 0 | 2024-08-14 | 2024-08-21 | 16-Sep-24 A | 19-Sep-24 A
Tunneling & Jack UpCCOPL57682 |  | 80 | 5 | 2024-08-21 | 2024-10-05 | 19-Sep-24 A | 2024-12-23 | 80
C-52-HG01-CNM03-1200 | Jacking of MTBM & RC Sleeves | 6 | 0 | 2024-08-21 | 2024-08-30 | 19-Sep-24 A | 26-Sep-24 A
C-52-HG01-CNM03-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 0 | 2024-08-30 | 2024-09-04 | 01-Oct-24 A | 05-Oct-24 A
C-52-HG01-CNM03-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2024-09-30 | 2024-10-05 | 2024-12-18 | 2024-12-23 | 80
Pipe Lowering, Welding, NDT & CoatingCCOPL57692 |  | 17 | 17 | 2024-09-04 | 2024-09-20 | 2024-11-07 | 2024-11-26 | 80
C-52-HG01-CNM03-1400 | Lowering & Welding of Carrier Pipe | 16 | 16 | 2024-09-04 | 2024-09-17 | 2024-11-07 | 2024-11-25 | 80
C-52-HG01-CNM03-1410 | NDT, Coating & Holiday Inspection of Carrier Pipe | 16 | 16 | 2024-09-05 | 2024-09-20 | 2024-11-08 | 2024-11-26 | 80
HydrotestingCCOPL57702 |  | 8 | 8 | 2024-09-20 | 2024-09-30 | 2024-12-09 | 2024-12-17 | 80
C-52-HG01-CNM03-1600 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 8 | 8 | 2024-09-20 | 2024-09-30 | 2024-12-09 | 2024-12-17 | 80
Re-Instatement of Entry & Exit PitCCOPL57712 |  | 10 | 10 | 2024-10-05 | 2024-10-22 | 2024-12-24 | 2025-01-04 | 80
C-52-HG01-CNM03-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 10 | 10 | 2024-10-05 | 2024-10-22 | 2024-12-24 | 2025-01-04 | 80
Micro Tunnelling @ CH 01+903 - 02+098 (NDRC-02) |  | 90 | 90 | 2024-08-31 | 2025-01-31 | 2024-12-21 | 2025-04-16 | 112
Entry & Exit Pit ConstructionCCOPL52902 |  | 33 | 33 | 2024-08-31 | 2024-11-08 | 2024-12-21 | 2025-01-30 | 112
C-52-HG01-CNM02-1000 | Sheet Piling for Driving & Receiving Pit | 7 | 7 | 2024-08-31 | 2024-09-30 | 2024-12-21 | 2024-12-28 | 112
C-52-HG01-CNM02-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-10-01 | 2024-10-05 | 2024-12-30 | 2025-01-04 | 112
C-52-HG01-CNM02-1010 | Driving & Receiving Pit Excavation | 7 | 7 | 2024-09-27 | 2024-10-14 | 2024-12-30 | 2025-01-07 | 112
C-52-HG01-CNM02-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 7 | 7 | 2024-10-05 | 2024-10-17 | 2024-12-30 | 2025-01-08 | 112
C-52-HG01-CNM02-1040 | Floor Blinding & French Drain in Driving Pit | 6 | 6 | 2024-10-17 | 2024-10-24 | 2025-01-08 | 2025-01-15 | 112
C-52-HG01-CNM02-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 6 | 6 | 2024-10-24 | 2024-10-31 | 2025-01-15 | 2025-01-22 | 112
C-52-HG01-CNM02-1060 | Construction of Exit Wall with Ring | 6 | 6 | 2024-11-01 | 2024-11-08 | 2025-01-23 | 2025-01-30 | 112
Tunneling & Jack UpCCOPL58042 |  | 43 | 43 | 2024-11-08 | 2025-01-15 | 2025-01-30 | 2025-03-27 | 112
C-52-HG01-CNM02-1200 | Jacking of MTBM & RC Sleeves | 10 | 10 | 2024-11-08 | 2024-11-27 | 2025-01-30 | 2025-02-11 | 112
C-52-HG01-CNM02-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2024-11-27 | 2024-12-04 | 2025-02-11 | 2025-02-15 | 112
C-52-HG01-CNM02-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-01-09 | 2025-01-15 | 2025-03-19 | 2025-03-27 | 112
Pipe Lowering, Welding, NDT & CoatingCCOPL58052 |  | 15 | 15 | 2024-12-04 | 2024-12-28 | 2025-02-15 | 2025-03-05 | 112
C-52-HG01-CNM02-1400 | Lowering & Welding of Carrier Pipe | 14 | 14 | 2024-12-04 | 2024-12-25 | 2025-02-15 | 2025-03-04 | 112
C-52-HG01-CNM02-1410 | NDT, Coating & Holiday Inspection of Carrier Pipe | 14 | 14 | 2024-12-05 | 2024-12-28 | 2025-02-17 | 2025-03-05 | 112
HydrotestingCCOPL58062 |  | 9 | 9 | 2024-12-28 | 2025-01-09 | 2025-03-05 | 2025-03-19 | 112
C-52-HG01-CNM02-1600 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 9 | 9 | 2024-12-28 | 2025-01-09 | 2025-03-05 | 2025-03-19 | 112
Re-Instatement of Entry & Exit PitCCOPL58072 |  | 14 | 14 | 2025-01-15 | 2025-01-31 | 2025-03-27 | 2025-04-16 | 112
C-52-HG01-CNM02-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-01-15 | 2025-01-31 | 2025-03-27 | 2025-04-16 | 112
Micro Tunnelling @ CH 01+544 - 01+644 (NDRC-01) |  | 124 | 124 | 2024-07-17 | 2024-11-25 | 2024-11-22 | 2025-04-29 | 108
Entry & Exit Pit ConstructionCCOPL52900 |  | 62 | 62 | 2024-07-17 | 2024-09-25 | 2024-11-22 | 2025-02-05 | 108
C-52-HG01-CNM01-1000 | Sheet Piling for Driving & Receiving Pit | 25 | 25 | 2024-07-17 | 2024-08-16 | 2024-11-22 | 2024-12-23 | 108
C-52-HG01-CNM01-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-08-17 | 2024-08-21 | 2024-12-24 | 2024-12-27 | 108
C-52-HG01-CNM01-1010 | Driving & Receiving Pit Excavation | 18 | 18 | 2024-08-10 | 2024-08-26 | 2024-12-24 | 2025-01-14 | 108
C-52-HG01-CNM01-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 14 | 14 | 2024-08-22 | 2024-09-02 | 2024-12-28 | 2025-01-14 | 108
C-52-HG01-CNM01-1040 | Floor Blinding & French Drain in Driving Pit | 6 | 6 | 2024-09-03 | 2024-09-09 | 2025-01-15 | 2025-01-21 | 108
C-52-HG01-CNM01-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 6 | 6 | 2024-09-10 | 2024-09-17 | 2025-01-22 | 2025-01-28 | 108
C-52-HG01-CNM01-1060 | Construction of Exit Wall with Ring | 6 | 6 | 2024-09-19 | 2024-09-25 | 2025-01-30 | 2025-02-05 | 108
Tunneling & Jack UpCCOPL58082 |  | 52 | 52 | 2024-09-26 | 2024-11-08 | 2025-02-06 | 2025-04-17 | 108
C-52-HG01-CNM01-1200 | Jacking of MTBM & RC Sleeves | 12 | 12 | 2024-09-26 | 2024-10-04 | 2025-02-06 | 2025-02-19 | 108
C-52-HG01-CNM01-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2024-10-05 | 2024-10-09 | 2025-02-20 | 2025-02-24 | 108
C-52-HG01-CNM01-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2024-11-04 | 2024-11-08 | 2025-04-11 | 2025-04-17 | 108
Pipe Lowering, Welding, NDT & CoatingCCOPL58092 |  | 19 | 19 | 2024-10-10 | 2024-10-24 | 2025-02-25 | 2025-03-23 | 108
C-52-HG01-CNM01-1400 | Lowering & Welding of Carrier Pipe | 18 | 18 | 2024-10-10 | 2024-10-21 | 2025-02-25 | 2025-03-22 | 108
C-52-HG01-CNM01-1410 | NDT, Coating & Holiday Inspection of Carrier Pipe | 18 | 18 | 2024-10-11 | 2024-10-24 | 2025-02-26 | 2025-03-23 | 108
HydrotestingCCOPL58102 |  | 12 | 12 | 2024-10-25 | 2024-11-02 | 2025-03-23 | 2025-04-11 | 108
C-52-HG01-CNM01-1600 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 12 | 12 | 2024-10-25 | 2024-11-02 | 2025-03-23 | 2025-04-11 | 108
Re-Instatement of Entry & Exit PitCCOPL58112 |  | 10 | 10 | 2024-11-09 | 2024-11-25 | 2025-04-17 | 2025-04-29 | 108
C-52-HG01-CNM01-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 10 | 10 | 2024-11-09 | 2024-11-25 | 2025-04-17 | 2025-04-29 | 108
Cathodic Protection |  | 66 | 66 | 2024-12-28 | 2025-03-21 | 2025-02-26 | 2025-05-24 | 124
Civil Works |  | 30 | 30 | 2025-02-10 | 2025-03-21 | 2025-04-18 | 2025-05-24 | 124
Backfilling & Reinstatement for CP (for Crossings)CCOP52CS47 |  | 30 | 30 | 2025-02-10 | 2025-03-21 | 2025-04-18 | 2025-05-24 | 124
C-52-HG01-PIPEL-5260 | Backfilling & Reinstatement for CP (for Crossings) | 30 | 30 | 2025-02-10 | 2025-03-21 | 2025-04-18 | 2025-05-24 | 124
CP Works |  | 47 | 47 | 2024-12-28 | 2025-02-22 | 2025-02-26 | 2025-05-01 | 143
CP Works (for Crossings)CCOP52EL32 |  | 47 | 47 | 2024-12-28 | 2025-02-22 | 2025-02-26 | 2025-05-01 | 143
C-52-HG01-PL-CA-5220 | Installation of Test Post for Crossing | 35 | 35 | 2024-12-28 | 2025-02-08 | 2025-02-26 | 2025-04-17 | 124
C-52-HG01-PL-CA-5230 | Installation of CP JB's | 35 | 35 | 2024-12-28 | 2025-02-08 | 2025-02-26 | 2025-04-17 | 124
C-52-HG01-PL-CA-5240 | Installation of CP TR | 5 | 5 | 2025-02-08 | 2025-02-14 | 2025-04-17 | 2025-04-23 | 124
C-52-HG01-PL-CA-5250 | CIP/DCVG Survey (Pre-Com) | 7 | 7 | 2025-02-14 | 2025-02-22 | 2025-04-23 | 2025-05-01 | 143
Telecommunication Works |  | 76 | 28 | 2025-02-22 | 2025-04-17 | 18-Sep-24 A | 2024-12-17 | 95
Telecom Works along Pipeline CCOP52IC57 |  | 76 | 28 | 2025-02-22 | 2025-04-17 | 18-Sep-24 A | 2024-12-17 | 95
C-52-HG01-PL-TE-8200 | FO - Cable Pulling/ Laying | 73 | 25 | 2025-02-22 | 2025-04-14 | 18-Sep-24 A | 2024-12-13 | 69
C-52-HG01-PL-TE-8210 | Termination/Splicing @ BVS | 3 | 3 | 2025-04-14 | 2025-04-17 | 2024-12-14 | 2024-12-17 | 95
52"x32.4 Km Pipeline from BVS-01 to BVS-02 at KP 65.8 |  | 345 | 132 | 2024-02-06 | 2025-03-18 | 06-Feb-24 A | 2025-04-11 | 161
52"x32.4 Km Pipeline from BVS-01 to BVS-02 at KP 65.8 |  | 345 | 132 | 2024-02-06 | 2025-03-18 | 06-Feb-24 A | 2025-04-11 | 161
Main Pipeline |  | 339 | 126 | 2024-02-06 | 2025-03-05 | 06-Feb-24 A | 2025-04-04 | 160
Sabkha Pad Gatch laying from BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.1 |  | 152 | 0 | 2024-02-06 | 2024-08-17 | 06-Feb-24 A | 14-Aug-24 A
C-52-0102-PL-CI-1800 | Sabka ROW/Grading | 138 | 0 | 2024-02-06 | 2024-07-29 | 06-Feb-24 A | 29-Jul-24 A
C-52-0102-PL-CI-2000 | Sabka Gatch Laying (Including ROW) - Layer 1 | 145 | 0 | 2024-02-06 | 2024-08-06 | 06-Feb-24 A | 06-Aug-24 A
C-52-0102-PL-CI-2010 | Sabka Gatch Laying - Layer 2 | 140 | 0 | 2024-02-20 | 2024-08-17 | 20-Feb-24 A | 14-Aug-24 A
Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.2 |  | 140 | 0 | 2024-02-27 | 2024-08-21 | 27-Feb-24 A | 21-Aug-24 A
C-52-0102-PL-CI-2200 | Sabka Gatch Compaction (Including ROW) - Layer 1 | 110 | 0 | 2024-03-28 | 2024-08-14 | 28-Mar-24 A | 14-Aug-24 A
C-52-0102-PL-CI-2210 | Sabka Gatch Compaction - Layer 2 | 140 | 0 | 2024-02-27 | 2024-08-21 | 27-Feb-24 A | 21-Aug-24 A
Sabkha Pad Gatch layingfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.3 |  | 147 | 0 | 2024-02-29 | 2024-08-31 | 29-Feb-24 A | 02-Sep-24 A
C-52-0102-PL-CI-2030 | Sabka Gatch Laying - Layer 3 | 141 | 0 | 2024-02-29 | 2024-08-24 | 29-Feb-24 A | 24-Aug-24 A
C-52-0102-PL-CI-2040 | Sabka Gatch Laying - Layer 4 | 141 | 0 | 2024-03-06 | 2024-08-31 | 06-Mar-24 A | 02-Sep-24 A
Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.4 |  | 143 | 0 | 2024-03-04 | 2024-09-04 | 04-Mar-24 A | 02-Sep-24 A
C-52-0102-PL-CI-2220 | Sabka Gatch Compaction - Layer 3 | 140 | 0 | 2024-03-04 | 2024-08-28 | 04-Mar-24 A | 28-Aug-24 A
C-52-0102-PL-CI-2230 | Sabka Gatch Compaction - Layer 4 | 132 | 0 | 2024-03-18 | 2024-09-04 | 18-Mar-24 A | 02-Sep-24 A
Excavation (incl Bedding)CCOPL52343 |  | 53 | 22 | 2024-10-11 | 2024-11-29 | 08-Oct-24 A | 2024-12-10 | 58
C-52-0102-PL-CI-2400 | Trench Excavation | 51 | 20 | 2024-10-11 | 2024-11-27 | 08-Oct-24 A | 2024-12-07 | 58
C-52-0102-PL-CI-2410 | Bedding | 53 | 20 | 2024-10-14 | 2024-11-29 | 08-Oct-24 A | 2024-12-10 | 58
Pipe StringingCCOPL52329 |  | 89 | 25 | 2024-08-23 | 2024-09-18 | 12-Aug-24 A | 2024-11-23 | 35
C-52-0102-PL-ME-2800 | Stringing (BVS-01 to BVS-02) | 89 | 25 | 2024-08-23 | 2024-09-18 | 12-Aug-24 A | 2024-11-23 | 35
Automatic WeldingCCOPL52336 |  | 57 | 14 | 2024-09-28 | 2024-11-23 | 24-Sep-24 A | 2024-11-28 | 20
C-52-0102-PL-ME-3600 | Automatic Welding | 57 | 14 | 2024-09-28 | 2024-11-23 | 24-Sep-24 A | 2024-11-28 | 20
NDT TestCCOPL52351 |  | 59 | 16 | 2024-09-30 | 2024-11-25 | 24-Sep-24 A | 2024-11-30 | 61
C-52-0102-PL-ME-4000 | NDT | 59 | 16 | 2024-09-30 | 2024-11-25 | 24-Sep-24 A | 2024-11-30 | 61
Ext. Joint CoatingCCOPL52334 |  | 61 | 30 | 2024-10-02 | 2025-02-04 | 08-Oct-24 A | 2024-12-19 | 59
C-52-0102-PL-ME-4400 | Ext. Joint Coating | 49 | 18 | 2024-10-02 | 2024-11-27 | 08-Oct-24 A | 2024-12-05 | 61
C-52-0102-PL-ME-4410 | Ext. Joint Coating (Tie-in Joint) | 19 | 19 | 2024-10-18 | 2025-02-04 | 2024-11-26 | 2024-12-19 | 59
Pipe Lowering & Tie-in / NDTCCOPL52344 |  | 24 | 24 | 2024-10-16 | 2025-02-05 | 2024-11-21 | 2024-12-20 | 59
C-52-0102-PL-ME-4800 | Lowering | 17 | 17 | 2024-10-16 | 2024-12-17 | 2024-11-21 | 2024-12-12 | 58
C-52-0102-PL-ME-4810 | Section Tie-in Welding | 18 | 18 | 2024-10-16 | 2025-02-01 | 2024-11-23 | 2024-12-16 | 59
C-52-0102-PL-ME-4820 | NDT (Tie-in Joint) | 19 | 19 | 2024-10-17 | 2025-02-03 | 2024-11-25 | 2024-12-18 | 59
C-52-0102-PL-ME-4830 | Holiday Testing | 19 | 19 | 2024-10-19 | 2025-02-05 | 2024-11-27 | 2024-12-20 | 59
Cold BendsCCOPL52335 |  | 77 | 14 | 2024-10-16 | 2024-12-17 | 12-Sep-24 A | 2024-12-13 | 59
C-52-0102-PL-ME-3200 | Cold Bends | 77 | 14 | 2024-10-16 | 2024-12-17 | 12-Sep-24 A | 2024-12-13 | 59
Crossings OHPLCCOPL52352 |  | 24 | 24 | 2024-10-30 | 2024-11-27 | 2024-11-01 | 2024-11-28 | 228
Crossing Manual @ KP 56+666 (OX-03) |  | 14 | 14 | 2024-10-30 | 2024-11-15 | 2024-11-01 | 2024-11-16 | 238
C-52-0102-CMA01-0980 | Sabkha Gatch Laying | 5 | 5 | 2024-10-30 | 2024-11-05 | 2024-11-01 | 2024-11-06 | 124
C-52-0102-CMA01-0990 | Sabka Gatch Compaction | 5 | 5 | 2024-10-31 | 2024-11-06 | 2024-11-02 | 2024-11-07 | 134
C-52-0102-CMA01-1000 | Trench Excavation | 2 | 2 | 2024-11-06 | 2024-11-08 | 2024-11-08 | 2024-11-09 | 134
C-52-0102-CMA01-1010 | Bedding | 1 | 1 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-09 | 134
C-52-0102-CMA01-1020 | Lowering | 1 | 1 | 2024-11-08 | 2024-11-09 | 2024-11-11 | 2024-11-11 | 134
C-52-0102-CMA01-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-08 | 2024-11-11 | 2024-11-11 | 2024-11-12 | 134
C-52-0102-CMA01-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-09 | 2024-11-12 | 2024-11-12 | 2024-11-13 | 134
C-52-0102-CMA01-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-11 | 2024-11-13 | 2024-11-13 | 2024-11-14 | 134
C-52-0102-CMA01-1060 | Holiday Testing | 1 | 1 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-15 | 134
C-52-0102-CMA01-1070 | Padding | 1 | 1 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-16 | 238
Crossing Manual @ KP 62+000 (OX-04) |  | 14 | 14 | 2024-11-05 | 2024-11-21 | 2024-11-07 | 2024-11-22 | 233
C-52-0102-CMA02-0980 | Sabkha Gatch Laying | 5 | 5 | 2024-11-05 | 2024-11-11 | 2024-11-07 | 2024-11-12 | 124
C-52-0102-CMA02-0990 | Sabka Gatch Compaction | 5 | 5 | 2024-11-06 | 2024-11-12 | 2024-11-08 | 2024-11-13 | 129
C-52-0102-CMA02-1000 | Trench Excavation | 2 | 2 | 2024-11-12 | 2024-11-14 | 2024-11-14 | 2024-11-15 | 129
C-52-0102-CMA02-1010 | Bedding | 1 | 1 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-15 | 129
C-52-0102-CMA02-1020 | Lowering | 1 | 1 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-16 | 129
C-52-0102-CMA02-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-14 | 2024-11-16 | 2024-11-16 | 2024-11-18 | 129
C-52-0102-CMA02-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-15 | 2024-11-18 | 2024-11-18 | 2024-11-19 | 129
C-52-0102-CMA02-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-16 | 2024-11-19 | 2024-11-19 | 2024-11-20 | 129
C-52-0102-CMA02-1060 | Holiday Testing | 1 | 1 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-21 | 129
C-52-0102-CMA02-1070 | Padding | 1 | 1 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-22 | 233
Crossing Manual @ KP 62+194 (OX-05) |  | 14 | 14 | 2024-11-11 | 2024-11-27 | 2024-11-13 | 2024-11-28 | 228
C-52-0102-CMA03-0980 | Sabkha Gatch Laying | 5 | 5 | 2024-11-11 | 2024-11-16 | 2024-11-13 | 2024-11-18 | 124
C-52-0102-CMA03-0990 | Sabka Gatch Compaction | 5 | 5 | 2024-11-12 | 2024-11-18 | 2024-11-14 | 2024-11-19 | 124
C-52-0102-CMA03-1000 | Trench Excavation | 2 | 2 | 2024-11-18 | 2024-11-20 | 2024-11-20 | 2024-11-21 | 124
C-52-0102-CMA03-1010 | Bedding | 1 | 1 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-21 | 124
C-52-0102-CMA03-1020 | Lowering | 1 | 1 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-22 | 124
C-52-0102-CMA03-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-20 | 2024-11-22 | 2024-11-22 | 2024-11-23 | 124
C-52-0102-CMA03-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-21 | 2024-11-23 | 2024-11-23 | 2024-11-25 | 124
C-52-0102-CMA03-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-22 | 2024-11-25 | 2024-11-25 | 2024-11-26 | 124
C-52-0102-CMA03-1060 | Holiday Testing | 1 | 1 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-27 | 124
C-52-0102-CMA03-1070 | Padding | 1 | 1 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-28 | 228
Crossings - UG PipeCCOPL52331 |  | 116 | 8 | 2024-10-15 | 2024-11-15 | 17-Jun-24 A | 2024-11-04 | 249
Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) |  | 114 | 6 | 2024-10-15 | 2024-11-09 | 17-Jun-24 A | 2024-11-01 | 251
C-52-0102-CMA04-0970 | Excavation (Manual-Trial Pit) | 22 | 0 | 2024-10-15 | 2024-10-24 | 17-Jun-24 A | 17-Jul-24 A
C-52-0102-CMA04-0980 | Sabkha Gatch Laying | 22 | 0 | 2024-10-24 | 2024-10-30 | 17-Jun-24 A | 17-Jul-24 A
C-52-0102-CMA04-0990 | Sabka Gatch Compaction | 22 | 0 | 2024-10-25 | 2024-10-31 | 17-Jun-24 A | 17-Jul-24 A
C-52-0102-CMA04-1000 | Trench Excavation | 22 | 0 | 2024-10-31 | 2024-11-02 | 17-Jun-24 A | 17-Jul-24 A
C-52-0102-CMA04-1010 | Bedding | 22 | 0 | 2024-11-01 | 2024-11-02 | 17-Jun-24 A | 17-Jul-24 A
C-52-0102-CMA04-1020 | Lowering | 1 | 1 | 2024-11-02 | 2024-11-04 | 2024-10-26 | 2024-10-26 | 133
C-52-0102-CMA04-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-02 | 2024-11-05 | 2024-10-26 | 2024-10-28 | 133
C-52-0102-CMA04-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-04 | 2024-11-06 | 2024-10-28 | 2024-10-29 | 133
C-52-0102-CMA04-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-05 | 2024-11-07 | 2024-10-29 | 2024-10-30 | 133
C-52-0102-CMA04-1060 | Holiday Testing | 1 | 1 | 2024-11-07 | 2024-11-08 | 2024-10-31 | 2024-10-31 | 133
C-52-0102-CMA04-1070 | Padding | 1 | 1 | 2024-11-08 | 2024-11-09 | 2024-11-01 | 2024-11-01 | 251
Crossing Manual @ KP 45+201 (PX-08) |  | 33 | 8 | 2024-10-24 | 2024-11-15 | 27-Sep-24 A | 2024-11-04 | 249
C-52-0102-CMA05-1000 | Trench Excavation | 16 | 2 | 2024-11-06 | 2024-11-08 | 10-Oct-24 A | 2024-10-28 | 145
C-52-0102-CMA05-1010 | Bedding | 15 | 1 | 2024-11-07 | 2024-11-08 | 11-Oct-24 A | 2024-10-28 | 145
C-52-0102-CMA05-1020 | Lowering | 1 | 1 | 2024-11-08 | 2024-11-09 | 2024-10-29 | 2024-10-29 | 145
C-52-0102-CMA05-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-08 | 2024-11-11 | 2024-10-29 | 2024-10-30 | 145
C-52-0102-CMA05-0970 | Excavation (Manual-Trial Pit) | 30 | 5 | 2024-10-24 | 2024-10-30 | 27-Sep-24 A | 2024-10-31 | 124
C-52-0102-CMA05-0980 | Sabkha Gatch Laying | 25 | 5 | 2024-10-30 | 2024-11-05 | 03-Oct-24 A | 2024-10-31 | 145
C-52-0102-CMA05-0990 | Sabka Gatch Compaction | 24 | 5 | 2024-10-31 | 2024-11-06 | 04-Oct-24 A | 2024-10-31 | 145
C-52-0102-CMA05-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-09 | 2024-11-12 | 2024-10-30 | 2024-10-31 | 145
C-52-0102-CMA05-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-11 | 2024-11-13 | 2024-10-31 | 2024-11-01 | 145
C-52-0102-CMA05-1060 | Holiday Testing | 1 | 1 | 2024-11-13 | 2024-11-14 | 2024-11-02 | 2024-11-02 | 145
C-52-0102-CMA05-1070 | Padding | 1 | 1 | 2024-11-14 | 2024-11-15 | 2024-11-04 | 2024-11-04 | 249
Open Cut - Rig / Track RoadCCOPL52333 |  | 18 | 18 | 2024-10-12 | 2024-11-16 | 2024-11-26 | 2024-12-18 | 213
Crossing Mechanical (TX-08) |  | 16 | 16 | 2024-10-12 | 2024-11-04 | 2024-11-26 | 2024-12-16 | 215
C-52-0102-CME01-1000 | Trench Excavation | 2 | 2 | 2024-10-12 | 2024-10-15 | 2024-11-26 | 2024-11-27 | 39
C-52-0102-CME01-1010 | Bedding | 2 | 2 | 2024-10-15 | 2024-10-17 | 2024-11-28 | 2024-11-29 | 112
C-52-0102-CME01-1020 | Lowering | 2 | 2 | 2024-10-17 | 2024-10-19 | 2024-11-30 | 2024-12-04 | 112
C-52-0102-CME01-1030 | Section Tie-in Welding | 2 | 2 | 2024-10-19 | 2024-10-23 | 2024-12-05 | 2024-12-06 | 112
C-52-0102-CME01-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-10-23 | 2024-10-26 | 2024-12-07 | 2024-12-09 | 112
C-52-0102-CME01-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-10-26 | 2024-10-30 | 2024-12-10 | 2024-12-11 | 112
C-52-0102-CME01-1060 | Holiday Testing | 2 | 2 | 2024-10-30 | 2024-11-01 | 2024-12-12 | 2024-12-13 | 112
C-52-0102-CME01-1070 | Padding & Back Filling | 2 | 2 | 2024-11-01 | 2024-11-04 | 2024-12-14 | 2024-12-16 | 215
Crossing Mechanical (TX-15) |  | 16 | 16 | 2024-10-16 | 2024-11-07 | 2024-11-27 | 2024-12-17 | 214
C-52-0102-CME02-1000 | Trench Excavation | 2 | 2 | 2024-10-16 | 2024-10-18 | 2024-11-27 | 2024-11-28 | 39
C-52-0102-CME02-1010 | Bedding | 2 | 2 | 2024-10-18 | 2024-10-21 | 2024-11-29 | 2024-11-30 | 111
C-52-0102-CME02-1020 | Lowering | 2 | 2 | 2024-10-21 | 2024-10-23 | 2024-12-04 | 2024-12-05 | 111
C-52-0102-CME02-1030 | Section Tie-in Welding | 2 | 2 | 2024-10-23 | 2024-10-26 | 2024-12-06 | 2024-12-07 | 111
C-52-0102-CME02-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-10-26 | 2024-10-30 | 2024-12-09 | 2024-12-10 | 111
C-52-0102-CME02-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-10-30 | 2024-11-02 | 2024-12-11 | 2024-12-12 | 111
C-52-0102-CME02-1060 | Holiday Testing | 2 | 2 | 2024-11-02 | 2024-11-05 | 2024-12-13 | 2024-12-14 | 111
C-52-0102-CME02-1070 | Padding & Back Filling | 2 | 2 | 2024-11-05 | 2024-11-07 | 2024-12-16 | 2024-12-17 | 214
Crossing Mechanical (TX-16) |  | 16 | 16 | 2024-10-19 | 2024-11-11 | 2024-11-28 | 2024-12-18 | 213
C-52-0102-CME03-1000 | Trench Excavation | 2 | 2 | 2024-10-19 | 2024-10-22 | 2024-11-28 | 2024-11-29 | 39
C-52-0102-CME03-1010 | Bedding | 2 | 2 | 2024-10-22 | 2024-10-24 | 2024-11-30 | 2024-12-04 | 110
C-52-0102-CME03-1020 | Lowering | 2 | 2 | 2024-10-24 | 2024-10-26 | 2024-12-05 | 2024-12-06 | 110
C-52-0102-CME03-1030 | Section Tie-in Welding | 2 | 2 | 2024-10-26 | 2024-10-30 | 2024-12-07 | 2024-12-09 | 110
C-52-0102-CME03-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-10-30 | 2024-11-02 | 2024-12-10 | 2024-12-11 | 110
C-52-0102-CME03-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-02 | 2024-11-06 | 2024-12-12 | 2024-12-13 | 110
C-52-0102-CME03-1060 | Holiday Testing | 2 | 2 | 2024-11-06 | 2024-11-08 | 2024-12-14 | 2024-12-16 | 110
C-52-0102-CME03-1070 | Padding & Back Filling | 2 | 2 | 2024-11-08 | 2024-11-11 | 2024-12-17 | 2024-12-18 | 213
Crossing Mechanical (TX-17) |  | 16 | 16 | 2024-10-23 | 2024-11-14 | 2024-11-28 | 2024-12-18 | 213
C-52-0102-CME04-1000 | Trench Excavation | 2 | 2 | 2024-10-23 | 2024-10-25 | 2024-11-28 | 2024-11-29 | 39
C-52-0102-CME04-1010 | Bedding | 2 | 2 | 2024-10-25 | 2024-10-28 | 2024-11-30 | 2024-12-04 | 110
C-52-0102-CME04-1020 | Lowering | 2 | 2 | 2024-10-28 | 2024-10-30 | 2024-12-05 | 2024-12-06 | 110
C-52-0102-CME04-1030 | Section Tie-in Welding | 2 | 2 | 2024-10-30 | 2024-11-02 | 2024-12-07 | 2024-12-09 | 110
C-52-0102-CME04-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-02 | 2024-11-06 | 2024-12-10 | 2024-12-11 | 110
C-52-0102-CME04-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-06 | 2024-11-09 | 2024-12-12 | 2024-12-13 | 110
C-52-0102-CME04-1060 | Holiday Testing | 2 | 2 | 2024-11-09 | 2024-11-12 | 2024-12-14 | 2024-12-16 | 110
C-52-0102-CME04-1070 | Padding & Back Filling | 2 | 2 | 2024-11-12 | 2024-11-14 | 2024-12-17 | 2024-12-18 | 213
Crossing Mechanical (TX-23) |  | 16 | 16 | 2024-10-25 | 2024-11-16 | 2024-11-28 | 2024-12-18 | 213
C-52-0102-CME05-1000 | Trench Excavation | 2 | 2 | 2024-10-25 | 2024-10-28 | 2024-11-28 | 2024-11-29 | 39
C-52-0102-CME05-1010 | Bedding | 2 | 2 | 2024-10-28 | 2024-10-30 | 2024-11-30 | 2024-12-04 | 110
C-52-0102-CME05-1020 | Lowering | 2 | 2 | 2024-10-30 | 2024-11-01 | 2024-12-05 | 2024-12-06 | 110
C-52-0102-CME05-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-01 | 2024-11-05 | 2024-12-07 | 2024-12-09 | 110
C-52-0102-CME05-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-05 | 2024-11-08 | 2024-12-10 | 2024-12-11 | 110
C-52-0102-CME05-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-08 | 2024-11-12 | 2024-12-12 | 2024-12-13 | 110
C-52-0102-CME05-1060 | Holiday Testing | 2 | 2 | 2024-11-12 | 2024-11-14 | 2024-12-14 | 2024-12-16 | 110
C-52-0102-CME05-1070 | Padding & Back Filling | 2 | 2 | 2024-11-14 | 2024-11-16 | 2024-12-17 | 2024-12-18 | 213
CP Works TemporaryCCOP52EL35 |  | 26 | 26 | 2024-10-24 | 2025-02-26 | 2024-11-29 | 2024-12-31 | 231
C-52-0102-PL-CA-5200 | Installation of CP Test Post | 25 | 25 | 2024-10-24 | 2025-01-11 | 2024-11-29 | 2024-12-30 | 231
C-52-0102-PL-CA-5210 | Glanding & Termination of Temp. CP S/m | 25 | 25 | 2024-12-11 | 2025-02-26 | 2024-11-30 | 2024-12-31 | 231
Test Stations & Anode BedsCCOP52EL34 |  | 25 | 25 | 2024-10-24 | 2025-01-11 | 2024-11-29 | 2024-12-30 | 58
C-52-0102-PL-CA-5600 | Installation of Temp. Anode | 25 | 25 | 2024-10-24 | 2025-01-11 | 2024-11-29 | 2024-12-30 | 58
PaddingCCOPL52330 |  | 30 | 30 | 2024-11-18 | 2025-02-26 | 2024-11-29 | 2025-01-06 | 58
C-52-0102-PL-CI-6000 | Padding | 30 | 30 | 2024-11-18 | 2025-02-26 | 2024-11-29 | 2025-01-06 | 58
BermingCCOPL52339 |  | 92 | 92 | 2024-11-23 | 2025-03-05 | 2024-12-07 | 2025-04-04 | 116
C-52-0102-PL-CI-6800 | Gatch Laying & Levelling | 45 | 45 | 2024-11-23 | 2025-02-28 | 2024-12-07 | 2025-01-29 | 58
C-52-0102-PL-CI-6810 | Gatch Compaction | 45 | 45 | 2024-11-26 | 2025-03-02 | 2024-12-09 | 2025-01-30 | 58
C-52-0102-PL-CI-7800 | Installation of Marker Post/Sign Board | 45 | 45 | 2024-11-27 | 2025-03-04 | 2025-01-31 | 2025-04-03 | 116
C-52-0102-PL-CI-7810 | Installation of Crash Barriers (If any) | 45 | 45 | 2024-11-28 | 2025-03-05 | 2025-02-01 | 2025-04-04 | 116
NDRC by Micro Tunneling Method |  | 167 | 123 | 2024-07-27 | 2025-02-05 | 04-Sep-24 A | 2025-03-28 | 134
Micro Tunnelling @ CH 52+059 - 52+211 (NDRC-07) |  | 147 | 123 | 2024-07-27 | 2025-01-06 | 28-Sep-24 A | 2025-03-28 | 134
Entry & Exit Pit ConstructionCCOPL52938 |  | 71 | 47 | 2024-07-27 | 2024-10-03 | 28-Sep-24 A | 2024-12-21 | 131
C-52-0102-CNM07-1000 | Sheet Piling for Driving & Receiving Pit | 36 | 12 | 2024-07-27 | 2024-08-24 | 28-Sep-24 A | 2024-11-08 | 131
C-52-0102-CNM07-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-08-26 | 2024-08-29 | 2024-11-09 | 2024-11-13 | 133
C-52-0102-CNM07-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 10 | 10 | 2024-08-30 | 2024-09-10 | 2024-11-16 | 2024-11-27 | 131
C-52-0102-CNM07-1010 | Driving & Receiving Pit Excavation | 14 | 14 | 2024-08-21 | 2024-09-05 | 2024-11-14 | 2024-11-29 | 131
C-52-0102-CNM07-1040 | Floor Blinding & French Drain in Driving Pit | 6 | 6 | 2024-09-11 | 2024-09-18 | 2024-11-28 | 2024-12-06 | 131
C-52-0102-CNM07-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 6 | 6 | 2024-09-19 | 2024-09-25 | 2024-12-07 | 2024-12-13 | 131
C-52-0102-CNM07-1060 | Construction of Exit Wall with Ring | 6 | 6 | 2024-09-27 | 2024-10-03 | 2024-12-16 | 2024-12-21 | 131
Tunneling & Jack UpCCOPL52940 |  | 62 | 62 | 2024-10-23 | 2024-12-19 | 2024-12-23 | 2025-03-06 | 134
C-52-0102-CNM07-1200 | Jacking of MTBM & RC Sleeves | 13 | 13 | 2024-10-23 | 2024-11-06 | 2024-12-23 | 2025-01-07 | 131
C-52-0102-CNM07-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2024-11-07 | 2024-11-11 | 2025-01-08 | 2025-01-11 | 134
C-52-0102-CNM07-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2024-12-14 | 2024-12-19 | 2025-02-28 | 2025-03-06 | 134
Pipe Lowering, Welding, NDT & CoatingCCOPL57302 |  | 18 | 18 | 2024-11-12 | 2024-12-04 | 2025-01-13 | 2025-02-01 | 134
C-52-0102-CNM07-1400 | Lowering & Welding of Carrier Pipe | 15 | 15 | 2024-11-12 | 2024-11-28 | 2025-01-13 | 2025-01-29 | 134
C-52-0102-CNM07-1410 | NDT, Coating & Holiday Inspection of Carrier Pipe | 17 | 17 | 2024-11-13 | 2024-12-04 | 2025-01-14 | 2025-02-01 | 134
HydrotestingCCOPL57312 |  | 12 | 12 | 2024-12-05 | 2024-12-13 | 2025-02-14 | 2025-02-27 | 134
C-52-0102-CNM07-1600 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 12 | 12 | 2024-12-05 | 2024-12-13 | 2025-02-14 | 2025-02-27 | 134
Re-Instatement of Entry & Exit PitCCOPL57322 |  | 14 | 14 | 2024-12-20 | 2025-01-06 | 2025-03-07 | 2025-03-28 | 134
C-52-0102-CNM07-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2024-12-20 | 2025-01-06 | 2025-03-07 | 2025-03-28 | 134
NDRC-06 (incl Hydrotest) @ CH 48+149 - 48+305 (Open Cut*) |  | 19 | 19 | 2024-10-28 | 2024-11-19 | 2024-11-28 | 2024-12-21 | 91
Entry & Exit Pit ConstructionCCOPL52934 |  | 2 | 2 | 2024-10-28 | 2024-10-30 | 2024-11-28 | 2024-11-29 | 39
C-52-0102-CME06-1090 | Trench Excavation | 2 | 2 | 2024-10-28 | 2024-10-30 | 2024-11-28 | 2024-11-29 | 39
Tunneling & Jack UpCCOPL57642 |  | 2 | 2 | 2024-10-30 | 2024-11-01 | 2024-11-30 | 2024-12-04 | 91
C-52-0102-CME06-1100 | Bedding | 2 | 2 | 2024-10-30 | 2024-11-01 | 2024-11-30 | 2024-12-04 | 91
Pipe Lowering, Welding, NDT & CoatingCCOPL57652 |  | 11 | 11 | 2024-11-01 | 2024-11-14 | 2024-12-05 | 2024-12-17 | 91
C-52-0102-CME06-1110 | Lowering | 2 | 2 | 2024-11-01 | 2024-11-04 | 2024-12-05 | 2024-12-06 | 91
C-52-0102-CME06-1120 | Section Tie-in Welding | 3 | 3 | 2024-11-04 | 2024-11-07 | 2024-12-07 | 2024-12-10 | 91
C-52-0102-CME06-1130 | NDT (Tie-in Joint) | 3 | 3 | 2024-11-07 | 2024-11-11 | 2024-12-11 | 2024-12-13 | 91
C-52-0102-CME06-1140 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-11-11 | 2024-11-14 | 2024-12-14 | 2024-12-17 | 91
HydrotestingCCOPL57662 |  | 2 | 2 | 2024-11-14 | 2024-11-16 | 2024-12-18 | 2024-12-19 | 91
C-52-0102-CME06-1150 | Holiday Testing | 2 | 2 | 2024-11-14 | 2024-11-16 | 2024-12-18 | 2024-12-19 | 91
Re-Instatement of Entry & Exit PitCCOPL57672 |  | 2 | 2 | 2024-11-16 | 2024-11-19 | 2024-12-20 | 2024-12-21 | 91
C-52-0102-CME06-1160 | Padding & Back Filling | 2 | 2 | 2024-11-16 | 2024-11-19 | 2024-12-20 | 2024-12-21 | 91
Micro Tunnelling @ CH 45+319 - 45+385 (NDRC-05) |  | 150 | 106 | 2024-07-27 | 2025-02-05 | 04-Sep-24 A | 2025-03-01 | 151
Entry & Exit Pit ConstructionCCOPL52932 |  | 76 | 32 | 2024-07-27 | 2024-10-03 | 04-Sep-24 A | 2024-12-04 | 114
C-52-0102-CNM05-1000 | Sheet Piling for Driving & Receiving Pit | 40 | 0 | 2024-07-27 | 2024-08-24 | 04-Sep-24 A | 22-Oct-24 A
C-52-0102-CNM05-1020 | Installation of Dewatering System for Driving & Receiving Pit | 7 | 0 | 2024-08-26 | 2024-08-29 | 15-Oct-24 A | 23-Oct-24 A
C-52-0102-CNM05-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 15 | 13 | 2024-08-30 | 2024-09-10 | 24-Oct-24 A | 2024-11-09 | 114
C-52-0102-CNM05-1010 | Driving & Receiving Pit Excavation | 23 | 14 | 2024-08-21 | 2024-09-05 | 16-Oct-24 A | 2024-11-11 | 114
C-52-0102-CNM05-1040 | Floor Blinding & French Drain in Driving Pit | 6 | 6 | 2024-09-11 | 2024-09-18 | 2024-11-11 | 2024-11-16 | 114
C-52-0102-CNM05-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 6 | 6 | 2024-09-19 | 2024-09-25 | 2024-11-18 | 2024-11-23 | 114
C-52-0102-CNM05-1060 | Construction of Exit Wall with Ring | 6 | 6 | 2024-09-27 | 2024-10-03 | 2024-11-26 | 2024-12-04 | 114
Tunneling & Jack UpCCOPL58002 |  | 60 | 60 | 2024-11-19 | 2025-01-20 | 2024-12-05 | 2025-02-13 | 151
C-52-0102-CNM05-1200 | Jacking of MTBM & RC Sleeves | 14 | 14 | 2024-11-19 | 2024-12-07 | 2024-12-05 | 2024-12-20 | 114
C-52-0102-CNM05-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2024-12-07 | 2024-12-12 | 2024-12-21 | 2024-12-25 | 151
C-52-0102-CNM05-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-01-14 | 2025-01-20 | 2025-02-08 | 2025-02-13 | 151
Pipe Lowering, Welding, NDT & CoatingCCOPL58012 |  | 19 | 19 | 2024-12-12 | 2025-01-04 | 2024-12-26 | 2025-01-17 | 151
C-52-0102-CNM05-1400 | Lowering & Welding of Carrier Pipe | 16 | 16 | 2024-12-12 | 2024-12-31 | 2024-12-26 | 2025-01-14 | 151
C-52-0102-CNM05-1410 | NDT, Coating & Holiday Inspection of Carrier Pipe | 18 | 18 | 2024-12-13 | 2025-01-04 | 2024-12-27 | 2025-01-17 | 151
HydrotestingCCOPL58022 |  | 8 | 8 | 2025-01-04 | 2025-01-14 | 2025-01-30 | 2025-02-07 | 151
C-52-0102-CNM05-1600 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 8 | 8 | 2025-01-04 | 2025-01-14 | 2025-01-30 | 2025-02-07 | 151
Re-Instatement of Entry & Exit PitCCOPL58032 |  | 14 | 14 | 2025-01-20 | 2025-02-05 | 2025-02-14 | 2025-03-01 | 151
C-52-0102-CNM05-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-01-20 | 2025-02-05 | 2025-02-14 | 2025-03-01 | 151
NDRC by Micro Tunnelling Method |  | 235 | 131 | 2024-06-25 | 2025-02-19 | 25-Jun-24 A | 2025-04-10 | 111
Micro Tunnelling @ CH 61+249 - 61+347 (NDRC-10) |  | 165 | 61 | 2024-06-25 | 2024-11-01 | 25-Jun-24 A | 2025-01-08 | 77
Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 |  | 146 | 34 | 2024-06-25 | 2024-10-10 | 25-Jun-24 A | 2024-12-16 | 77
C-52-0102-CNH10-1000 | Sheet Piling for Driving & Receiving Pit | 23 | 0 | 2024-06-25 | 2024-07-23 | 25-Jun-24 A | 23-Jul-24 A
C-52-0102-CNH10-1020 | Installation of Dewatering System for Driving & Receiving Pit | 9 | 0 | 2024-07-16 | 2024-07-26 | 16-Jul-24 A | 26-Jul-24 A
C-52-0102-CNH10-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 27 | 0 | 2024-07-26 | 2024-08-08 | 26-Jul-24 A | 27-Aug-24 A
C-52-0102-CNH10-1010 | Driving & Receiving Pit Excavation | 44 | 0 | 2024-07-26 | 2024-08-09 | 26-Jul-24 A | 17-Sep-24 A
C-52-0102-CNH10-1040 | Floor Blinding & French Drain in Driving Pit | 10 | 0 | 2024-08-09 | 2024-08-15 | 06-Sep-24 A | 19-Sep-24 A
C-52-0102-CNH10-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 15 | 0 | 2024-08-16 | 2024-08-22 | 21-Sep-24 A | 09-Oct-24 A
C-52-0102-CNH10-1060 | Construction of Exit Wall with Ring | 9 | 0 | 2024-08-24 | 2024-08-30 | 02-Oct-24 A | 12-Oct-24 A
C-52-0102-CNH10-1070 | Lowering & Welding of Carrier Pipe | 15 | 15 | 2024-09-17 | 2024-09-27 | 2024-11-05 | 2024-11-21 | 77
C-52-0102-CNH10-1080 | NDT, Coating & Holiday Inspection of Carrier Pipe | 12 | 12 | 2024-09-18 | 2024-10-01 | 2024-11-09 | 2024-11-22 | 77
C-52-0102-CNH10-1090 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 8 | 8 | 2024-10-02 | 2024-10-10 | 2024-12-07 | 2024-12-16 | 77
Tunneling & Jack UpCCOPL58202 |  | 57 | 47 | 2024-08-31 | 2024-10-16 | 15-Oct-24 A | 2024-12-21 | 77
C-52-0102-CNH10-1200 | Jacking of MTBM & RC Sleeves | 14 | 4 | 2024-08-31 | 2024-09-10 | 15-Oct-24 A | 2024-10-30 | 77
C-52-0102-CNH10-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2024-09-11 | 2024-09-14 | 2024-10-31 | 2024-11-04 | 77
C-52-0102-CNH10-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2024-10-11 | 2024-10-16 | 2024-12-17 | 2024-12-21 | 77
Re-Instatement of Entry & Exit PitCCOPL58212 |  | 14 | 14 | 2024-10-17 | 2024-11-01 | 2024-12-23 | 2025-01-08 | 77
C-52-0102-CNH10-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2024-10-17 | 2024-11-01 | 2024-12-23 | 2025-01-08 | 77
Micro Tunnelling @ CH 58+847 - 59+035 (NDRC-09) |  | 175 | 98 | 2024-07-27 | 2024-12-24 | 27-Jul-24 A | 2025-02-20 | 144
Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 |  | 156 | 79 | 2024-07-27 | 2024-11-29 | 27-Jul-24 A | 2025-01-29 | 144
C-52-0102-CNH09-1020 | Installation of Dewatering System for Driving & Receiving Pit | 25 | 0 | 2024-08-26 | 2024-08-29 | 26-Aug-24 A | 25-Sep-24 A
C-52-0102-CNH09-1000 | Sheet Piling for Driving & Receiving Pit | 52 | 0 | 2024-07-27 | 2024-08-24 | 27-Jul-24 A | 26-Sep-24 A
C-52-0102-CNH09-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 43 | 0 | 2024-08-30 | 2024-09-10 | 03-Sep-24 A | 24-Oct-24 A
C-52-0102-CNH09-1010 | Driving & Receiving Pit Excavation | 58 | 7 | 2024-08-21 | 2024-09-05 | 27-Aug-24 A | 2024-11-02 | 142
C-52-0102-CNH09-1040 | Floor Blinding & French Drain in Driving Pit | 7 | 7 | 2024-09-11 | 2024-09-18 | 2024-10-26 | 2024-11-02 | 142
C-52-0102-CNH09-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 8 | 8 | 2024-09-19 | 2024-09-25 | 2024-11-04 | 2024-11-12 | 142
C-52-0102-CNH09-1060 | Construction of Exit Wall with Ring | 6 | 6 | 2024-09-27 | 2024-10-03 | 2024-11-12 | 2024-11-18 | 142
C-52-0102-CNH09-1070 | Lowering & Welding of Carrier Pipe | 18 | 18 | 2024-10-28 | 2024-11-16 | 2024-12-14 | 2025-01-04 | 144
C-52-0102-CNH09-1080 | NDT, Coating & Holiday Inspection of Carrier Pipe | 20 | 20 | 2024-10-29 | 2024-11-20 | 2024-12-16 | 2025-01-08 | 144
C-52-0102-CNH09-1090 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 8 | 8 | 2024-11-21 | 2024-11-29 | 2025-01-21 | 2025-01-29 | 144
Tunneling & Jack UpCCOPL58262 |  | 64 | 64 | 2024-10-04 | 2024-12-07 | 2024-11-19 | 2025-02-04 | 144
C-52-0102-CNH09-1200 | Jacking of MTBM & RC Sleeves | 16 | 16 | 2024-10-04 | 2024-10-22 | 2024-11-19 | 2024-12-09 | 142
C-52-0102-CNH09-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2024-10-23 | 2024-10-26 | 2024-12-10 | 2024-12-13 | 144
C-52-0102-CNH09-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2024-11-30 | 2024-12-07 | 2025-01-30 | 2025-02-04 | 144
Re-Instatement of Entry & Exit PitCCOPL58272 |  | 14 | 14 | 2024-12-09 | 2024-12-24 | 2025-02-05 | 2025-02-20 | 144
C-52-0102-CNH09-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2024-12-09 | 2024-12-24 | 2025-02-05 | 2025-02-20 | 144
Micro Tunnelling @ CH 53+678 - 54+124 (NDRC-08) |  | 208 | 131 | 2024-07-27 | 2025-02-19 | 27-Jul-24 A | 2025-04-10 | 111
Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 |  | 189 | 112 | 2024-07-27 | 2025-01-28 | 27-Jul-24 A | 2025-03-11 | 111
C-52-0102-CNH08-1000 | Sheet Piling for Driving & Receiving Pit | 44 | 0 | 2024-07-27 | 2024-08-24 | 27-Jul-24 A | 18-Sep-24 A
C-52-0102-CNH08-1020 | Installation of Dewatering System for Driving & Receiving Pit | 15 | 0 | 2024-08-27 | 2024-08-31 | 02-Sep-24 A | 20-Sep-24 A
C-52-0102-CNH08-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 12 | 0 | 2024-08-31 | 2024-09-12 | 10-Sep-24 A | 25-Sep-24 A
C-52-0102-CNH08-1010 | Driving & Receiving Pit Excavation | 43 | 0 | 2024-08-23 | 2024-09-09 | 04-Sep-24 A | 25-Oct-24 A
C-52-0102-CNH08-1040 | Floor Blinding & French Drain in Driving Pit | 6 | 0 | 2024-09-12 | 2024-09-20 | 19-Oct-24 A | 25-Oct-24 A
C-52-0102-CNH08-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 8 | 6 | 2024-09-20 | 2024-09-27 | 24-Oct-24 A | 2024-11-01 | 111
C-52-0102-CNH08-1060 | Construction of Exit Wall with Ring | 6 | 6 | 2024-09-28 | 2024-10-05 | 2024-10-28 | 2024-11-02 | 111
C-52-0102-CNH08-1070 | Lowering & Welding of Carrier Pipe | 40 | 40 | 2024-11-23 | 2025-01-13 | 2024-12-25 | 2025-02-10 | 111
C-52-0102-CNH08-1080 | NDT, Coating & Holiday Inspection of Carrier Pipe | 42 | 42 | 2024-11-25 | 2025-01-16 | 2024-12-26 | 2025-02-13 | 111
C-52-0102-CNH08-1090 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 10 | 10 | 2025-01-16 | 2025-01-28 | 2025-02-26 | 2025-03-11 | 111
Tunneling & Jack UpCCOPL58322 |  | 110 | 110 | 2024-10-05 | 2025-02-03 | 2024-11-04 | 2025-03-18 | 111
C-52-0102-CNH08-1200 | Jacking of MTBM & RC Sleeves | 38 | 38 | 2024-10-05 | 2024-11-19 | 2024-11-04 | 2024-12-19 | 111
C-52-0102-CNH08-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2024-11-19 | 2024-11-23 | 2024-12-20 | 2024-12-24 | 111
C-52-0102-CNH08-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-01-28 | 2025-02-03 | 2025-03-11 | 2025-03-18 | 111
Re-Instatement of Entry & Exit PitCCOPL58332 |  | 14 | 14 | 2025-02-03 | 2025-02-19 | 2025-03-19 | 2025-04-10 | 111
C-52-0102-CNH08-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-02-03 | 2025-02-19 | 2025-03-19 | 2025-04-10 | 111
Cathodic Protection |  | 90 | 90 | 2024-11-26 | 2025-03-18 | 2024-12-17 | 2025-04-11 | 161
Civil Works |  | 46 | 46 | 2024-11-26 | 2025-01-22 | 2024-12-17 | 2025-02-08 | 193
Backfilling & Reinstatement for CP (for Crossings)CCOP52CS45 |  | 46 | 46 | 2024-11-26 | 2025-01-22 | 2024-12-17 | 2025-02-08 | 193
C-52-0102-PIPEL-5260 | Backfilling & Reinstatement for CP (for Crossings) | 46 | 46 | 2024-11-26 | 2025-01-22 | 2024-12-17 | 2025-02-08 | 193
CP Works |  | 90 | 90 | 2024-11-26 | 2025-03-18 | 2024-12-17 | 2025-04-11 | 161
CP Works (for Crossings)CCOP52EL55 |  | 90 | 90 | 2024-11-26 | 2025-03-18 | 2024-12-17 | 2025-04-11 | 161
C-52-0102-PL-CA-5240 | Installation of CP TR | 5 | 5 | 2025-01-22 | 2025-01-28 | 2025-02-11 | 2025-02-15 | 192
C-52-0102-PL-CA-5250 | CIP/DCVG Survey | 7 | 7 | 2025-02-26 | 2025-03-07 | 2025-02-17 | 2025-02-24 | 192
C-52-0102-PL-CA-5220 | Installation of Test Post for Crossing | 90 | 90 | 2024-11-26 | 2025-03-18 | 2024-12-17 | 2025-04-11 | 110
C-52-0102-PL-CA-5230 | Installation of CP JB's | 90 | 90 | 2024-11-26 | 2025-03-18 | 2024-12-17 | 2025-04-11 | 110
Telecommunication Works |  | 43 | 43 | 2024-11-18 | 2025-03-11 | 2024-11-29 | 2025-01-21 | 66
Telecom Works along PipelineCCOP52IC52 |  | 43 | 43 | 2024-11-18 | 2025-03-11 | 2024-11-29 | 2025-01-21 | 66
C-52-0102-PL-TE-8200 | FO - Cable Pulling/ Laying | 40 | 40 | 2024-11-18 | 2025-03-07 | 2024-11-29 | 2025-01-17 | 66
C-52-0102-PL-TE-8210 | Termination/Splicing @ BVS | 3 | 3 | 2025-03-07 | 2025-03-11 | 2025-01-18 | 2025-01-21 | 66
52"x16 Km Pipeline from BVS-02 to BVS-03 at KP 81.8 |  | 286 | 105 | 2024-03-13 | 2025-04-11 | 13-Mar-24 A | 2025-02-28 | 33
52"x16.0 Km Pipeline from BVS-02 to BVS-03 at KP 81.8 |  | 286 | 105 | 2024-03-13 | 2025-04-11 | 13-Mar-24 A | 2025-02-28 | 33
Main Pipeline |  | 286 | 105 | 2024-03-13 | 2025-04-11 | 13-Mar-24 A | 2025-02-28 | 33
Sabkha PadCCOPL52377 |  | 134 | 0 | 2024-03-13 | 2024-10-29 | 13-Mar-24 A | 30-Aug-24 A
C-52-0203-PL-CI-1800 | Sabka ROW/Grading | 109 | 0 | 2024-03-13 | 2024-08-07 | 13-Mar-24 A | 01-Aug-24 A
C-52-0203-PL-CI-2000 | Sabka Gatch Laying (Including ROW) - Layer 1 | 86 | 0 | 2024-04-23 | 2024-08-31 | 23-Apr-24 A | 05-Aug-24 A
C-52-0203-PL-CI-2200 | Sabka Gatch Compaction (Including ROW) - Layer 1 | 89 | 0 | 2024-04-24 | 2024-09-09 | 24-Apr-24 A | 09-Aug-24 A
C-52-0203-PL-CI-2010 | Sabka Gatch Laying - Layer 2 | 89 | 0 | 2024-04-26 | 2024-09-18 | 26-Apr-24 A | 12-Aug-24 A
C-52-0203-PL-CI-2210 | Sabka Gatch Compaction - Layer 2 | 93 | 0 | 2024-04-26 | 2024-09-26 | 26-Apr-24 A | 16-Aug-24 A
C-52-0203-PL-CI-2020 | Sabka Gatch Laying - Layer 3 | 84 | 0 | 2024-05-09 | 2024-10-04 | 09-May-24 A | 19-Aug-24 A
C-52-0203-PL-CI-2220 | Sabka Gatch Compaction - Layer 3 | 88 | 0 | 2024-05-09 | 2024-10-12 | 09-May-24 A | 23-Aug-24 A
C-52-0203-PL-CI-2030 | Sabka Gatch Laying - Layer 4 | 90 | 0 | 2024-05-09 | 2024-10-21 | 09-May-24 A | 26-Aug-24 A
C-52-0203-PL-CI-2230 | Sabka Gatch Compaction - Layer 4 | 94 | 0 | 2024-05-09 | 2024-10-29 | 09-May-24 A | 30-Aug-24 A
Excavation (incl Bedding)CCOPL52371 |  | 30 | 30 | 2024-12-27 | 2025-02-01 | 2024-11-23 | 2024-12-30 | 33
C-52-0203-PL-CI-2400 | Trench Excavation | 25 | 25 | 2024-12-27 | 2025-01-27 | 2024-11-23 | 2024-12-24 | 33
C-52-0203-PL-CI-2410 | Bedding | 25 | 25 | 2025-01-03 | 2025-02-01 | 2024-11-29 | 2024-12-30 | 33
Pipe StringingCCOPL52357 |  | 68 | 0 | 2024-06-19 | 2024-11-01 | 19-Jun-24 A | 08-Sep-24 A
C-52-0203-PL-ME-2800 | Stringing (BVS-02 to BVS-03) | 68 | 0 | 2024-06-19 | 2024-11-01 | 19-Jun-24 A | 08-Sep-24 A
Automatic WeldingCCOPL52364 |  | 32 | 32 | 2024-11-26 | 2025-01-23 | 2024-10-26 | 2024-12-04 | 17
C-52-0203-PL-ME-3600 | Automatic Welding | 32 | 32 | 2024-11-26 | 2025-01-23 | 2024-10-26 | 2024-12-04 | 17
NDT TestCCOPL52379 |  | 47 | 47 | 2024-11-27 | 2025-01-24 | 2024-10-28 | 2024-12-23 | 41
C-52-0203-PL-ME-4000 | NDT | 47 | 47 | 2024-11-27 | 2025-01-24 | 2024-10-28 | 2024-12-23 | 41
Ext. Joint CoatingCCOPL52362 |  | 77 | 77 | 2024-11-28 | 2025-03-02 | 2024-10-29 | 2025-01-29 | 33
C-52-0203-PL-ME-4400 | Ext. Joint Coating | 47 | 47 | 2024-11-28 | 2025-01-25 | 2024-10-29 | 2024-12-24 | 41
C-52-0203-PL-ME-4410 | Ext. Joint Coating (Tie-in Joint) | 45 | 45 | 2025-01-09 | 2025-03-02 | 2024-12-07 | 2025-01-29 | 33
Cold BendsCCOPL52363 |  | 85 | 28 | 2025-01-07 | 2025-02-08 | 27-Sep-24 A | 2025-01-07 | 50
C-52-0203-PL-ME-3200 | Cold Bends | 85 | 28 | 2025-01-07 | 2025-02-08 | 27-Sep-24 A | 2025-01-07 | 50
Pipe Lowering & Tie-in / NDTCCOPL52372 |  | 48 | 48 | 2025-01-07 | 2025-03-03 | 2024-12-05 | 2025-01-30 | 33
C-52-0203-PL-ME-4800 | Lowering | 28 | 28 | 2025-01-07 | 2025-02-08 | 2024-12-05 | 2025-01-07 | 33
C-52-0203-PL-ME-4810 | Section Tie-in Welding | 45 | 45 | 2025-01-07 | 2025-02-28 | 2024-12-05 | 2025-01-27 | 33
C-52-0203-PL-ME-4820 | NDT (Tie-in Joint) | 45 | 45 | 2025-01-08 | 2025-03-01 | 2024-12-06 | 2025-01-28 | 33
C-52-0203-PL-ME-4830 | Holiday Testing | 30 | 30 | 2025-01-28 | 2025-03-03 | 2024-12-26 | 2025-01-30 | 33
Open Cut - Rig / Track RoadCCOPL52361 |  | 61 | 36 | 2024-10-24 | 2024-11-26 | 27-Sep-24 A | 2024-12-09 | 71
Crossing Mechanical (TX-23) |  | 19 | 19 | 2024-10-24 | 2024-11-15 | 2024-10-26 | 2024-11-16 | 88
C-52-0203-CME01-1000 | Trench Excavation | 2 | 2 | 2024-10-24 | 2024-10-26 | 2024-10-26 | 2024-10-28 | 85
C-52-0203-CME01-1010 | Bedding | 2 | 2 | 2024-10-26 | 2024-10-29 | 2024-10-29 | 2024-10-30 | 88
C-52-0203-CME01-1020 | Lowering | 2 | 2 | 2024-10-29 | 2024-10-31 | 2024-10-31 | 2024-11-01 | 88
C-52-0203-CME01-1030 | Section Tie-in Welding | 3 | 3 | 2024-10-31 | 2024-11-04 | 2024-11-02 | 2024-11-05 | 88
C-52-0203-CME01-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-11-04 | 2024-11-07 | 2024-11-06 | 2024-11-08 | 88
C-52-0203-CME01-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-11-07 | 2024-11-11 | 2024-11-09 | 2024-11-12 | 88
C-52-0203-CME01-1060 | Holiday Testing | 2 | 2 | 2024-11-11 | 2024-11-13 | 2024-11-13 | 2024-11-14 | 88
C-52-0203-CME01-1070 | Padding & Back Filling | 2 | 2 | 2024-11-13 | 2024-11-15 | 2024-11-15 | 2024-11-16 | 88
Crossing Mechanical (TX-31A) |  | 19 | 19 | 2024-10-28 | 2024-11-19 | 2024-10-30 | 2024-11-20 | 85
C-52-0203-CME02-1000 | Trench Excavation | 2 | 2 | 2024-10-28 | 2024-10-30 | 2024-10-30 | 2024-10-31 | 85
C-52-0203-CME02-1010 | Bedding | 2 | 2 | 2024-10-30 | 2024-11-01 | 2024-11-01 | 2024-11-02 | 85
C-52-0203-CME02-1020 | Lowering | 2 | 2 | 2024-11-01 | 2024-11-04 | 2024-11-04 | 2024-11-05 | 85
C-52-0203-CME02-1030 | Section Tie-in Welding | 3 | 3 | 2024-11-04 | 2024-11-07 | 2024-11-06 | 2024-11-08 | 85
C-52-0203-CME02-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-11-07 | 2024-11-11 | 2024-11-09 | 2024-11-12 | 85
C-52-0203-CME02-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-11-11 | 2024-11-14 | 2024-11-13 | 2024-11-15 | 85
C-52-0203-CME02-1060 | Holiday Testing | 2 | 2 | 2024-11-14 | 2024-11-16 | 2024-11-16 | 2024-11-18 | 85
C-52-0203-CME02-1070 | Padding & Back Filling | 2 | 2 | 2024-11-16 | 2024-11-19 | 2024-11-19 | 2024-11-20 | 85
Crossing Mechanical (RX-08) |  | 61 | 18 | 2024-10-31 | 2024-11-26 | 27-Sep-24 A | 2024-12-09 | 71
C-52-0203-CME03-1000 | Road Diversion & Trench Excavation | 8 | 0 | 2024-10-31 | 2024-11-05 | 27-Sep-24 A | 07-Oct-24 A
C-52-0203-CME03-1010 | Bedding | 2 | 2 | 2024-11-05 | 2024-11-07 | 2024-11-16 | 2024-11-18 | 71
C-52-0203-CME03-1020 | Lowering | 2 | 2 | 2024-11-07 | 2024-11-09 | 2024-11-19 | 2024-11-20 | 71
C-52-0203-CME03-1030 | Section Tie-in Welding | 3 | 3 | 2024-11-09 | 2024-11-13 | 2024-11-21 | 2024-11-23 | 71
C-52-0203-CME03-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-11-13 | 2024-11-16 | 2024-11-25 | 2024-11-27 | 71
C-52-0203-CME03-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-11-16 | 2024-11-20 | 2024-11-28 | 2024-11-30 | 71
C-52-0203-CME03-1060 | Holiday Testing | 2 | 2 | 2024-11-20 | 2024-11-22 | 2024-12-04 | 2024-12-05 | 71
C-52-0203-CME03-1070 | Padding & Back Filling | 3 | 3 | 2024-11-22 | 2024-11-26 | 2024-12-06 | 2024-12-09 | 71
Crossings - UG CableCCOPL52365 |  | 69 | 17 | 2024-12-31 | 2025-01-23 | 27-Sep-24 A | 2024-12-18 | 63
Crossing Manual @ KP 74+821 (CX-17) |  | 69 | 17 | 2024-12-31 | 2025-01-23 | 27-Sep-24 A | 2024-12-18 | 63
C-52-0203-CMA01-970 | Excavation (Manual-Trial Pit) | 5 | 5 | 2024-12-31 | 2025-01-07 | 2024-11-27 | 2024-12-04 | 40
C-52-0203-CMA01-980 | Sabkha Gatch Laying | 5 | 5 | 2025-01-07 | 2025-01-13 | 2024-12-05 | 2024-12-10 | 40
C-52-0203-CMA01-990 | Sabka Gatch Compaction | 5 | 5 | 2025-01-08 | 2025-01-14 | 2024-12-06 | 2024-12-11 | 40
C-52-0203-CMA01-1000 | Trench Excavation | 63 | 2 | 2025-01-14 | 2025-01-16 | 27-Sep-24 A | 2024-12-11 | 40
C-52-0203-CMA01-1010 | Bedding | 63 | 1 | 2025-01-15 | 2025-01-16 | 27-Sep-24 A | 2024-12-11 | 40
C-52-0203-CMA01-1020 | Lowering | 1 | 1 | 2025-01-16 | 2025-01-17 | 2024-12-12 | 2024-12-12 | 40
C-52-0203-CMA01-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-16 | 2025-01-18 | 2024-12-12 | 2024-12-13 | 40
C-52-0203-CMA01-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-17 | 2025-01-20 | 2024-12-13 | 2024-12-14 | 40
C-52-0203-CMA01-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-18 | 2025-01-21 | 2024-12-14 | 2024-12-16 | 40
C-52-0203-CMA01-1060 | Holiday Testing | 1 | 1 | 2025-01-21 | 2025-01-22 | 2024-12-17 | 2024-12-17 | 40
C-52-0203-CMA01-1070 | Padding | 1 | 1 | 2025-01-22 | 2025-01-23 | 2024-12-18 | 2024-12-18 | 63
Crossing Manual @ KP 84+089 (FX-13) |  | 10 | 10 | 2025-01-07 | 2025-01-18 | 2024-12-05 | 2024-12-16 | 65
C-52-0203-CMA02-1000 | Trench Excavation | 3 | 3 | 2025-01-07 | 2025-01-10 | 2024-12-05 | 2024-12-07 | 65
C-52-0203-CMA02-1010 | Bedding | 1 | 1 | 2025-01-10 | 2025-01-11 | 2024-12-09 | 2024-12-09 | 65
C-52-0203-CMA02-1020 | Lowering | 1 | 1 | 2025-01-11 | 2025-01-13 | 2024-12-10 | 2024-12-10 | 65
C-52-0203-CMA02-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-11 | 2025-01-14 | 2024-12-10 | 2024-12-11 | 65
C-52-0203-CMA02-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-13 | 2025-01-15 | 2024-12-11 | 2024-12-12 | 65
C-52-0203-CMA02-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-14 | 2025-01-16 | 2024-12-12 | 2024-12-13 | 65
C-52-0203-CMA02-1060 | Holiday Testing | 1 | 1 | 2025-01-16 | 2025-01-17 | 2024-12-14 | 2024-12-14 | 65
C-52-0203-CMA02-1070 | Padding & Back Filling | 2 | 2 | 2025-01-16 | 2025-01-18 | 2024-12-14 | 2024-12-16 | 65
CP Works TemporaryCCOP52EL38 |  | 56 | 56 | 2025-01-10 | 2025-03-23 | 2024-12-09 | 2025-02-12 | 40
C-52-0203-PL-CA-5200 | Installation of CP Test Post | 21 | 21 | 2025-01-10 | 2025-02-04 | 2024-12-09 | 2025-01-02 | 73
C-52-0203-PL-CA-5210 | Glanding & Termination of Temp. CP S/m | 21 | 21 | 2025-02-22 | 2025-03-23 | 2025-01-20 | 2025-02-12 | 40
Test Stations & Anode BedsCCOP52EL36 |  | 21 | 21 | 2025-01-10 | 2025-02-04 | 2024-12-09 | 2025-01-02 | 49
C-52-0203-PL-CA-5600 | Installation of Temp. Anode | 21 | 21 | 2025-01-10 | 2025-02-04 | 2024-12-09 | 2025-01-02 | 49
PaddingCCOPL52358 |  | 30 | 30 | 2025-01-29 | 2025-03-05 | 2024-12-27 | 2025-01-31 | 33
C-52-0203-PL-CI-6000 | Padding | 30 | 30 | 2025-01-29 | 2025-03-05 | 2024-12-27 | 2025-01-31 | 33
BermingCCOPL52367 |  | 34 | 34 | 2025-02-01 | 2025-03-15 | 2024-12-31 | 2025-02-08 | 33
C-52-0203-PL-CI-6800 | Gatch Laying & Levelling | 32 | 32 | 2025-02-01 | 2025-03-13 | 2024-12-31 | 2025-02-06 | 33
C-52-0203-PL-CI-6810 | Gatch Compaction | 32 | 32 | 2025-02-04 | 2025-03-15 | 2025-01-03 | 2025-02-08 | 33
Marker Post & Crash Barrier |  | 48 | 48 | 2025-02-05 | 2025-04-11 | 2025-01-04 | 2025-02-28 | 33
C-52-0203-PL-CI-7800 | Installation of Marker Post/Sign Board | 47 | 47 | 2025-02-05 | 2025-04-10 | 2025-01-04 | 2025-02-27 | 33
C-52-0203-PL-CI-7810 | Installation of Crash Barriers (If any) | 47 | 47 | 2025-02-06 | 2025-04-11 | 2025-01-06 | 2025-02-28 | 33
NDRC by Micro Tunneling Method |  | 74 | 13 | 2024-11-06 | 2024-12-04 | 14-Aug-24 A | 2024-11-09 | 45
NDRC-11 (incl Hydrotest) at KP 74+979.943/(RX-10) (Open Cut*) |  | 74 | 13 | 2024-11-06 | 2024-11-28 | 14-Aug-24 A | 2024-11-09 | 45
Entry & Exit Pit ConstructionCCOPL52948 |  | 3 | 0 | 2024-11-06 | 2024-11-08 | 14-Aug-24 A | 17-Aug-24 A
C-52-0203-CME04-1000 | Trench Excavation | 3 | 0 | 2024-11-06 | 2024-11-08 | 14-Aug-24 A | 17-Aug-24 A
Tunneling & Jack UpCCOPL57182 |  | 3 | 0 | 2024-11-08 | 2024-11-11 | 19-Aug-24 A | 22-Aug-24 A
C-52-0203-CME04-1010 | Bedding | 3 | 0 | 2024-11-08 | 2024-11-11 | 19-Aug-24 A | 22-Aug-24 A
Pipe Lowering, Welding, NDT & CoatingCCOPL57192 |  | 60 | 9 | 2024-11-11 | 2024-11-23 | 26-Aug-24 A | 2024-11-05 | 45
C-52-0203-CME04-1020 | Lowering | 17 | 0 | 2024-11-11 | 2024-11-13 | 26-Aug-24 A | 15-Sep-24 A
C-52-0203-CME04-1030 | Section Tie-in Welding | 3 | 3 | 2024-11-13 | 2024-11-16 | 2024-10-26 | 2024-10-29 | 45
C-52-0203-CME04-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-11-16 | 2024-11-20 | 2024-10-30 | 2024-11-01 | 45
C-52-0203-CME04-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-11-20 | 2024-11-23 | 2024-11-02 | 2024-11-05 | 45
HydrotestingCCOPL57202 |  | 2 | 2 | 2024-11-23 | 2024-11-26 | 2024-11-06 | 2024-11-07 | 45
C-52-0203-CME04-1060 | Holiday Testing | 2 | 2 | 2024-11-23 | 2024-11-26 | 2024-11-06 | 2024-11-07 | 45
Re-Instatement of Entry & Exit PitCCOPL57212 |  | 2 | 2 | 2024-11-26 | 2024-11-28 | 2024-11-08 | 2024-11-09 | 45
C-52-0203-CME04-1070 | Padding & Back Filling | 2 | 2 | 2024-11-26 | 2024-11-28 | 2024-11-08 | 2024-11-09 | 45
NDRC-12 (incl Hydrotest) @ CH 75+320 - 75+370 (RX-09,CX-18) (Open Cut*) |  | 38 | 13 | 2024-11-09 | 2024-12-04 | 27-Sep-24 A | 2024-11-09 | 45
Entry & Exit Pit ConstructionCCOPL52950 |  | 2 | 2 | 2024-11-09 | 2024-11-12 | 2024-10-26 | 2024-10-28 | 45
C-52-0203-CME04-1080 | Trench Excavation | 2 | 2 | 2024-11-09 | 2024-11-12 | 2024-10-26 | 2024-10-28 | 45
Tunneling & Jack UpCCOPL57842 |  | 2 | 2 | 2024-11-12 | 2024-11-14 | 2024-10-29 | 2024-10-30 | 45
C-52-0203-CME04-1090 | Bedding | 2 | 2 | 2024-11-12 | 2024-11-14 | 2024-10-29 | 2024-10-30 | 45
Pipe Lowering, Welding, NDT & CoatingCCOPL57852 |  | 34 | 6 | 2024-11-14 | 2024-11-27 | 27-Sep-24 A | 2024-11-05 | 45
C-52-0203-CME04-1100 | Lowering | 2 | 2 | 2024-11-14 | 2024-11-16 | 2024-10-31 | 2024-11-01 | 45
C-52-0203-CME04-1110 | Section Tie-in Welding | 31 | 3 | 2024-11-16 | 2024-11-20 | 27-Sep-24 A | 2024-11-01 | 45
C-52-0203-CME04-1120 | NDT (Tie-in Joint) | 31 | 3 | 2024-11-20 | 2024-11-23 | 27-Sep-24 A | 2024-11-01 | 45
C-52-0203-CME04-1130 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-11-23 | 2024-11-27 | 2024-11-02 | 2024-11-05 | 45
HydrotestingCCOPL57862 |  | 2 | 2 | 2024-11-27 | 2024-11-29 | 2024-11-06 | 2024-11-07 | 45
C-52-0203-CME04-1140 | Holiday Testing | 2 | 2 | 2024-11-27 | 2024-11-29 | 2024-11-06 | 2024-11-07 | 45
Re-Instatement of Entry & Exit PitCCOPL57872 |  | 2 | 2 | 2024-11-29 | 2024-12-04 | 2024-11-08 | 2024-11-09 | 45
C-52-0203-CME04-1150 | Padding & Back Filling | 2 | 2 | 2024-11-29 | 2024-12-04 | 2024-11-08 | 2024-11-09 | 45
Cathodic Protection |  | 55 | 55 | 2025-01-22 | 2025-04-05 | 2024-12-18 | 2025-02-20 | 40
Civil Works |  | 18 | 18 | 2025-01-27 | 2025-02-17 | 2024-12-23 | 2025-01-13 | 51
Backfilling for CP (for Crossings)CCOP52CS40 |  | 18 | 18 | 2025-01-27 | 2025-02-17 | 2024-12-23 | 2025-01-13 | 51
C-52-0203-PIPEL-5260 | Backfilling for CP (for Crossings) | 18 | 18 | 2025-01-27 | 2025-02-17 | 2024-12-23 | 2025-01-13 | 51
CP Works |  | 55 | 55 | 2025-01-22 | 2025-04-05 | 2024-12-18 | 2025-02-20 | 40
CP Works (for Crossings)CCOP52EL54 |  | 55 | 55 | 2025-01-22 | 2025-04-05 | 2024-12-18 | 2025-02-20 | 40
C-52-0203-PL-CA-5220 | Installation of Test Post for Crossing | 30 | 30 | 2025-01-22 | 2025-02-26 | 2024-12-18 | 2025-01-22 | 40
C-52-0203-PL-CA-5230 | Installation of CP JB's | 30 | 30 | 2025-01-25 | 2025-03-01 | 2024-12-21 | 2025-01-25 | 40
C-52-0203-PL-CA-5240 | Installation of CP TR | 14 | 14 | 2025-03-01 | 2025-03-22 | 2025-01-27 | 2025-02-11 | 40
C-52-0203-PL-CA-5250 | CIP/DCVG Survey | 7 | 7 | 2025-03-23 | 2025-04-05 | 2025-02-13 | 2025-02-20 | 40
Telecommunication Works |  | 24 | 24 | 2025-03-05 | 2025-04-11 | 2025-02-01 | 2025-02-28 | 33
Telecom Works along PipelineCCOP52IC39 |  | 24 | 24 | 2025-03-05 | 2025-04-11 | 2025-02-01 | 2025-02-28 | 33
C-52-0203-PL-TE-8200 | FO - Cable Pulling/ Laying | 21 | 21 | 2025-03-05 | 2025-04-08 | 2025-02-01 | 2025-02-25 | 33
C-52-0203-PL-TE-8210 | Termination/Splicing @ BVS | 3 | 3 | 2025-04-08 | 2025-04-11 | 2025-02-26 | 2025-02-28 | 33
52"x16.1 Km Pipeline from BVS-03 to BVS-04 at KP 97.9 |  | 305 | 113 | 2024-03-01 | 2025-05-27 | 01-Mar-24 A | 2025-03-12 | 129
52"x16.1 Km Pipeline from BVS-03 to BVS-04 at KP 97.9-1 |  | 305 | 113 | 2024-03-01 | 2025-05-27 | 01-Mar-24 A | 2025-03-12 | 129
Main Pipeline |  | 305 | 113 | 2024-03-01 | 2025-05-27 | 01-Mar-24 A | 2025-03-12 | 129
ROW Access RoadCCOPL52384 |  | 151 | 0 | 2024-03-01 | 2024-08-13 | 01-Mar-24 A | 07-Sep-24 A
C-52-0304-PL-CI-1800 | Non-Sabka ROW/Grading | 151 | 0 | 2024-03-01 | 2024-08-13 | 01-Mar-24 A | 07-Sep-24 A
Cut & Fill in Sandy AreaCCOPL52410 |  | 76 | 7 | 2024-10-05 | 2024-10-30 | 12-Aug-24 A | 2024-11-09 | 61
C-52-0304-PL-CI-1400 | Cut & Fill (@ Non-Sabkha) | 76 | 7 | 2024-10-05 | 2024-10-30 | 12-Aug-24 A | 2024-11-09 | 61
Sabkha PadCCOPL52405 |  | 198 | 19 | 2024-03-18 | 2024-10-19 | 18-Mar-24 A | 2024-11-19 | 36
C-52-0304-PL-CI-2000 | Sabka Gatch Laying (Including ROW) - Layer 1 | 184 | 5 | 2024-03-18 | 2024-08-21 | 18-Mar-24 A | 2024-11-02 | 36
C-52-0304-PL-CI-2200 | Sabka Gatch Compaction (Including ROW) - Layer 1 | 181 | 5 | 2024-03-25 | 2024-08-29 | 25-Mar-24 A | 2024-11-05 | 36
C-52-0304-PL-CI-2010 | Sabka Gatch Laying - Layer 2 | 150 | 5 | 2024-05-10 | 2024-09-06 | 10-May-24 A | 2024-11-07 | 36
C-52-0304-PL-CI-2210 | Sabka Gatch Compaction - Layer 2 | 148 | 5 | 2024-05-15 | 2024-09-14 | 15-May-24 A | 2024-11-09 | 36
C-52-0304-PL-CI-2020 | Sabka Gatch Laying - Layer 3 | 149 | 5 | 2024-05-16 | 2024-09-24 | 16-May-24 A | 2024-11-12 | 36
C-52-0304-PL-CI-2220 | Sabka Gatch Compaction - Layer 3 | 150 | 5 | 2024-05-17 | 2024-10-02 | 17-May-24 A | 2024-11-14 | 36
C-52-0304-PL-CI-2030 | Sabka Gatch Laying - Layer 4 | 147 | 5 | 2024-05-23 | 2024-10-11 | 23-May-24 A | 2024-11-16 | 36
C-52-0304-PL-CI-2230 | Sabka Gatch Compaction - Layer 4 | 148 | 5 | 2024-05-24 | 2024-10-19 | 24-May-24 A | 2024-11-19 | 36
Excavation (incl Bedding)CCOPL52399 |  | 28 | 28 | 2025-02-20 | 2025-04-05 | 2024-12-14 | 2025-01-16 | 33
C-52-0304-PL-CI-2400 | Trench Excavation | 25 | 25 | 2025-02-20 | 2025-03-26 | 2024-12-14 | 2025-01-13 | 33
C-52-0304-PL-CI-2410 | Bedding | 25 | 25 | 2025-02-26 | 2025-04-05 | 2024-12-18 | 2025-01-16 | 33
Pipe StringingCCOPL52385 |  | 71 | 14 | 2024-10-03 | 2024-10-23 | 06-Sep-24 A | 2024-11-29 | 36
C-52-0304-PL-ME-2800 | Stringing (BVS-03 to BVS-04) | 71 | 14 | 2024-10-03 | 2024-10-23 | 06-Sep-24 A | 2024-11-29 | 36
Automatic WeldingCCOPL52392 |  | 30 | 30 | 2025-01-23 | 2025-03-22 | 2024-12-05 | 2025-01-09 | 19
C-52-0304-PL-ME-3600 | Automatic Welding | 30 | 30 | 2025-01-23 | 2025-03-22 | 2024-12-05 | 2025-01-09 | 19
NDT TestCCOPL52407 |  | 46 | 46 | 2025-01-24 | 2025-03-23 | 2024-12-06 | 2025-01-29 | 29
C-52-0304-PL-ME-4000 | NDT | 46 | 46 | 2025-01-24 | 2025-03-23 | 2024-12-06 | 2025-01-29 | 29
Ext. Joint CoatingCCOPL52390 |  | 62 | 62 | 2025-01-27 | 2025-05-08 | 2024-12-09 | 2025-02-19 | 29
C-52-0304-PL-ME-4400 | Ext. Joint Coating | 46 | 46 | 2025-01-27 | 2025-03-26 | 2024-12-09 | 2025-01-31 | 29
C-52-0304-PL-ME-4410 | Ext. Joint Coating (Tie-in Joint) | 45 | 45 | 2025-03-07 | 2025-05-08 | 2024-12-28 | 2025-02-19 | 29
Cold BendsCCOPL52391 |  | 28 | 28 | 2025-03-13 | 2025-04-22 | 2025-01-03 | 2025-02-04 | 40
C-52-0304-PL-ME-3200 | Cold Bends | 28 | 28 | 2025-03-13 | 2025-04-22 | 2025-01-03 | 2025-02-04 | 40
Pipe Lowering & Tie-in / NDTCCOPL52400 |  | 48 | 48 | 2025-03-03 | 2025-05-09 | 2024-12-26 | 2025-02-20 | 29
C-52-0304-PL-ME-4800 | Lowering | 34 | 34 | 2025-03-03 | 2025-04-22 | 2024-12-26 | 2025-02-04 | 29
C-52-0304-PL-ME-4810 | Section Tie-in Welding | 45 | 45 | 2025-03-03 | 2025-05-05 | 2024-12-26 | 2025-02-17 | 29
C-52-0304-PL-ME-4820 | NDT (Tie-in Joint) | 45 | 45 | 2025-03-05 | 2025-05-07 | 2024-12-27 | 2025-02-18 | 29
C-52-0304-PL-ME-4830 | Holiday Testing | 45 | 45 | 2025-03-08 | 2025-05-09 | 2024-12-30 | 2025-02-20 | 29
Crossings OHPLCCOPL52408 |  | 103 | 69 | 2024-08-23 | 2024-11-21 | 16-Sep-24 A | 2025-01-18 | 54
Crossing Manual @ KP 88+996 (OX-04) |  | 31 | 31 | 2024-08-23 | 2024-11-09 | 2024-11-11 | 2024-12-19 | 79
C-52-0304-CMA01-0980 | Sabkha Gatch Laying | 5 | 5 | 2024-08-23 | 2024-08-29 | 2024-11-11 | 2024-11-16 | 53
C-52-0304-CMA01-0990 | Sabka Gatch Compaction | 5 | 5 | 2024-08-24 | 2024-08-30 | 2024-11-12 | 2024-11-18 | 85
C-52-0304-CMA01-1000 | Trench Excavation | 2 | 2 | 2024-08-30 | 2024-09-02 | 2024-11-18 | 2024-11-20 | 85
C-52-0304-CMA01-1010 | Bedding | 1 | 1 | 2024-08-31 | 2024-09-02 | 2024-11-19 | 2024-11-20 | 85
C-52-0304-CMA01-1020 | Lowering | 1 | 1 | 2024-11-02 | 2024-11-04 | 2024-12-12 | 2024-12-13 | 68
C-52-0304-CMA01-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-02 | 2024-11-05 | 2024-12-12 | 2024-12-14 | 79
C-52-0304-CMA01-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-04 | 2024-11-06 | 2024-12-13 | 2024-12-16 | 79
C-52-0304-CMA01-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-05 | 2024-11-07 | 2024-12-14 | 2024-12-17 | 79
C-52-0304-CMA01-1060 | Holiday Testing | 1 | 1 | 2024-11-07 | 2024-11-08 | 2024-12-17 | 2024-12-18 | 79
C-52-0304-CMA01-1070 | Padding | 1 | 1 | 2024-11-08 | 2024-11-09 | 2024-12-18 | 2024-12-19 | 79
Crossing Manual @ KP 90+235 (OX-05) |  | 80 | 46 | 2024-09-04 | 2024-11-12 | 16-Sep-24 A | 2024-12-21 | 77
C-52-0304-CMA02-1000 | Trench Excavation | 36 | 2 | 2024-09-11 | 2024-09-13 | 16-Sep-24 A | 2024-10-28 | 106
C-52-0304-CMA02-980 | Sabkha Gatch Laying | 5 | 5 | 2024-09-04 | 2024-09-10 | 2024-11-22 | 2024-11-28 | 53
C-52-0304-CMA02-990 | Sabka Gatch Compaction | 5 | 5 | 2024-09-05 | 2024-09-11 | 2024-11-23 | 2024-11-29 | 78
C-52-0304-CMA02-1010 | Bedding | 1 | 1 | 2024-09-12 | 2024-09-13 | 2024-11-29 | 2024-11-30 | 78
C-52-0304-CMA02-1020 | Lowering | 1 | 1 | 2024-11-05 | 2024-11-06 | 2024-12-14 | 2024-12-16 | 68
C-52-0304-CMA02-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-05 | 2024-11-07 | 2024-12-14 | 2024-12-17 | 77
C-52-0304-CMA02-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-06 | 2024-11-08 | 2024-12-16 | 2024-12-18 | 77
C-52-0304-CMA02-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-07 | 2024-11-09 | 2024-12-17 | 2024-12-19 | 77
C-52-0304-CMA02-1060 | Holiday Testing | 1 | 1 | 2024-11-09 | 2024-11-11 | 2024-12-19 | 2024-12-20 | 77
C-52-0304-CMA02-1070 | Padding | 1 | 1 | 2024-11-11 | 2024-11-12 | 2024-12-20 | 2024-12-21 | 77
Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) |  | 101 | 68 | 2024-10-19 | 2024-11-21 | 19-Sep-24 A | 2025-01-18 | 54
C-52-0304-CMA03-1000 | Trench Excavation | 42 | 9 | 2024-10-19 | 2024-10-30 | 19-Sep-24 A | 2024-11-07 | 95
C-52-0304-CMA03-1010 | Bedding | 1 | 1 | 2024-10-29 | 2024-10-30 | 2024-11-06 | 2024-11-07 | 105
C-52-0304-CMA03-1020 | Lowering | 1 | 1 | 2024-11-13 | 2024-11-14 | 2025-01-10 | 2025-01-11 | 53
C-52-0304-CMA03-1030 | Section Tie-in Welding | 3 | 3 | 2024-11-13 | 2024-11-16 | 2025-01-10 | 2025-01-14 | 54
C-52-0304-CMA03-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-11-14 | 2024-11-18 | 2025-01-11 | 2025-01-15 | 54
C-52-0304-CMA03-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-11-15 | 2024-11-19 | 2025-01-13 | 2025-01-16 | 54
C-52-0304-CMA03-1060 | Holiday Testing | 1 | 1 | 2024-11-19 | 2024-11-20 | 2025-01-16 | 2025-01-17 | 54
C-52-0304-CMA03-1070 | Padding | 1 | 1 | 2024-11-20 | 2024-11-21 | 2025-01-17 | 2025-01-18 | 54
Crossings - FenceCCOPL52388 |  | 67 | 67 | 2024-08-12 | 2024-11-22 | 2024-10-30 | 2025-01-20 | 57
Crossing Manual @ KP 85+318 (CX-X1) |  | 39 | 39 | 2024-08-12 | 2024-11-07 | 2024-10-30 | 2024-12-17 | 85
C-52-0304-CMA04-0970 | Excavation (Manual-Trial Pit) | 5 | 5 | 2024-08-12 | 2024-08-17 | 2024-10-30 | 2024-11-05 | 53
C-52-0304-CMA04-0980 | Sabkha Gatch Laying | 5 | 5 | 2024-08-17 | 2024-08-23 | 2024-11-05 | 2024-11-11 | 71
C-52-0304-CMA04-0990 | Sabka Gatch Compaction | 5 | 5 | 2024-08-19 | 2024-08-24 | 2024-11-06 | 2024-11-12 | 71
C-52-0304-CMA04-1000 | Trench Excavation | 2 | 2 | 2024-08-24 | 2024-08-27 | 2024-11-12 | 2024-11-14 | 71
C-52-0304-CMA04-1010 | Bedding | 1 | 1 | 2024-08-26 | 2024-08-27 | 2024-11-13 | 2024-11-14 | 71
C-52-0304-CMA04-1020 | Lowering | 1 | 1 | 2024-10-31 | 2024-11-01 | 2024-12-10 | 2024-12-11 | 51
C-52-0304-CMA04-1030 | Section Tie-in Welding | 2 | 2 | 2024-10-31 | 2024-11-02 | 2024-12-10 | 2024-12-12 | 51
C-52-0304-CMA04-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-01 | 2024-11-04 | 2024-12-11 | 2024-12-13 | 51
C-52-0304-CMA04-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-02 | 2024-11-05 | 2024-12-12 | 2024-12-14 | 51
C-52-0304-CMA04-1060 | Holiday Testing | 1 | 1 | 2024-11-05 | 2024-11-06 | 2024-12-14 | 2024-12-16 | 51
C-52-0304-CMA04-1070 | Padding | 1 | 1 | 2024-11-06 | 2024-11-07 | 2024-12-16 | 2024-12-17 | 85
Crossing Manual @ KP 85+958 (CX-X1) |  | 35 | 35 | 2024-08-17 | 2024-11-08 | 2024-11-05 | 2024-12-18 | 84
C-52-0304-CMA05-0970 | Excavation (Manual-Trial Pit) | 5 | 5 | 2024-08-17 | 2024-08-23 | 2024-11-05 | 2024-11-11 | 53
C-52-0304-CMA05-0980 | Sabkha Gatch Laying | 5 | 5 | 2024-08-23 | 2024-08-29 | 2024-11-11 | 2024-11-16 | 84
C-52-0304-CMA05-0990 | Sabka Gatch Compaction | 5 | 5 | 2024-08-24 | 2024-08-30 | 2024-11-12 | 2024-11-18 | 84
C-52-0304-CMA05-1000 | Trench Excavation | 2 | 2 | 2024-08-30 | 2024-09-02 | 2024-11-18 | 2024-11-20 | 84
C-52-0304-CMA05-1010 | Bedding | 1 | 1 | 2024-08-31 | 2024-09-02 | 2024-11-19 | 2024-11-20 | 84
C-52-0304-CMA05-1020 | Lowering | 1 | 1 | 2024-11-01 | 2024-11-02 | 2024-12-11 | 2024-12-12 | 68
C-52-0304-CMA05-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-01 | 2024-11-04 | 2024-12-11 | 2024-12-13 | 84
C-52-0304-CMA05-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-02 | 2024-11-05 | 2024-12-12 | 2024-12-14 | 84
C-52-0304-CMA05-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-04 | 2024-11-06 | 2024-12-13 | 2024-12-16 | 84
C-52-0304-CMA05-1060 | Holiday Testing | 1 | 1 | 2024-11-06 | 2024-11-07 | 2024-12-16 | 2024-12-17 | 84
C-52-0304-CMA05-1070 | Padding | 1 | 1 | 2024-11-07 | 2024-11-08 | 2024-12-17 | 2024-12-18 | 84
Crossing Manual @ KP 93+714 (FX-16) |  | 19 | 19 | 2024-09-23 | 2024-11-15 | 2024-12-12 | 2025-01-04 | 66
C-52-0304-CMA06-0970 | Excavation (Manual-Trial Pit) | 5 | 5 | 2024-09-23 | 2024-09-28 | 2024-12-12 | 2024-12-18 | 53
C-52-0304-CMA06-0980 | Sabkha Gatch Laying | 5 | 5 | 2024-09-28 | 2024-10-04 | 2024-12-18 | 2024-12-24 | 60
C-52-0304-CMA06-0990 | Sabka Gatch Compaction | 5 | 5 | 2024-09-30 | 2024-10-05 | 2024-12-19 | 2024-12-25 | 60
C-52-0304-CMA06-1000 | Trench Excavation | 2 | 2 | 2024-10-05 | 2024-10-08 | 2024-12-25 | 2024-12-27 | 60
C-52-0304-CMA06-1010 | Bedding | 1 | 1 | 2024-10-07 | 2024-10-08 | 2024-12-26 | 2024-12-27 | 60
C-52-0304-CMA06-1020 | Lowering | 1 | 1 | 2024-11-08 | 2024-11-09 | 2024-12-27 | 2024-12-28 | 60
C-52-0304-CMA06-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-08 | 2024-11-11 | 2024-12-27 | 2024-12-30 | 66
C-52-0304-CMA06-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-09 | 2024-11-12 | 2024-12-28 | 2024-12-31 | 66
C-52-0304-CMA06-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-11 | 2024-11-13 | 2024-12-30 | 2025-01-02 | 66
C-52-0304-CMA06-1060 | Holiday Testing | 1 | 1 | 2024-11-13 | 2024-11-14 | 2025-01-02 | 2025-01-03 | 66
C-52-0304-CMA06-1070 | Padding | 1 | 1 | 2024-11-14 | 2024-11-15 | 2025-01-03 | 2025-01-04 | 66
Crossing Manual @ KP 89+994 (CX-14B) |  | 27 | 27 | 2024-08-29 | 2024-11-11 | 2024-11-16 | 2024-12-20 | 78
C-52-0304-CMA07-0970 | Excavation (Manual-Trial Pit) | 5 | 5 | 2024-08-29 | 2024-09-04 | 2024-11-16 | 2024-11-22 | 53
C-52-0304-CMA07-0980 | Sabkha Gatch Laying | 5 | 5 | 2024-09-04 | 2024-09-10 | 2024-11-22 | 2024-11-28 | 76
C-52-0304-CMA07-0990 | Sabka Gatch Compaction | 5 | 5 | 2024-09-05 | 2024-09-11 | 2024-11-23 | 2024-11-29 | 76
C-52-0304-CMA07-1000 | Trench Excavation | 2 | 2 | 2024-09-11 | 2024-09-13 | 2024-11-29 | 2024-12-04 | 76
C-52-0304-CMA07-1010 | Bedding | 1 | 1 | 2024-09-12 | 2024-09-13 | 2024-11-30 | 2024-12-04 | 76
C-52-0304-CMA07-1020 | Lowering | 1 | 1 | 2024-11-04 | 2024-11-05 | 2024-12-13 | 2024-12-14 | 68
C-52-0304-CMA07-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-04 | 2024-11-06 | 2024-12-13 | 2024-12-16 | 78
C-52-0304-CMA07-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-05 | 2024-11-07 | 2024-12-14 | 2024-12-17 | 78
C-52-0304-CMA07-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-06 | 2024-11-08 | 2024-12-16 | 2024-12-18 | 78
C-52-0304-CMA07-1060 | Holiday Testing | 1 | 1 | 2024-11-08 | 2024-11-09 | 2024-12-18 | 2024-12-19 | 78
C-52-0304-CMA07-1070 | Padding | 1 | 1 | 2024-11-09 | 2024-11-11 | 2024-12-19 | 2024-12-20 | 78
Crossing Manual @ KP 96+523 (FX-17) |  | 59 | 59 | 2024-10-30 | 2024-11-21 | 2024-11-07 | 2025-01-18 | 54
C-52-0304-CMA08-1000 | Trench Excavation | 6 | 6 | 2024-10-30 | 2024-11-06 | 2024-11-07 | 2024-11-14 | 95
C-52-0304-CMA08-1010 | Bedding | 1 | 1 | 2024-11-05 | 2024-11-06 | 2024-11-13 | 2024-11-14 | 100
C-52-0304-CMA08-1020 | Lowering | 1 | 1 | 2024-11-14 | 2024-11-15 | 2025-01-11 | 2025-01-13 | 53
C-52-0304-CMA08-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-14 | 2024-11-16 | 2025-01-11 | 2025-01-14 | 54
C-52-0304-CMA08-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-15 | 2024-11-18 | 2025-01-13 | 2025-01-15 | 54
C-52-0304-CMA08-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-16 | 2024-11-19 | 2025-01-14 | 2025-01-16 | 54
C-52-0304-CMA08-1060 | Holiday Testing | 1 | 1 | 2024-11-19 | 2024-11-20 | 2025-01-16 | 2025-01-17 | 54
C-52-0304-CMA08-1070 | Padding | 1 | 1 | 2024-11-20 | 2024-11-21 | 2025-01-17 | 2025-01-18 | 54
Crossing Manual @ KP 91+938 (CX-X1) |  | 19 | 19 | 2024-09-17 | 2024-11-14 | 2024-12-06 | 2024-12-28 | 71
C-52-0304-CMA09-0970 | Excavation (Manual-Trial Pit) | 5 | 5 | 2024-09-17 | 2024-09-23 | 2024-12-06 | 2024-12-12 | 53
C-52-0304-CMA09-0980 | Sabkha Gatch Laying | 5 | 5 | 2024-09-23 | 2024-09-28 | 2024-12-12 | 2024-12-18 | 64
C-52-0304-CMA09-0990 | Sabka Gatch Compaction | 5 | 5 | 2024-09-24 | 2024-09-30 | 2024-12-13 | 2024-12-19 | 64
C-52-0304-CMA09-1000 | Trench Excavation | 2 | 2 | 2024-09-30 | 2024-10-02 | 2024-12-19 | 2024-12-21 | 64
C-52-0304-CMA09-1010 | Bedding | 1 | 1 | 2024-10-01 | 2024-10-02 | 2024-12-20 | 2024-12-21 | 64
C-52-0304-CMA09-1020 | Lowering | 1 | 1 | 2024-11-07 | 2024-11-08 | 2024-12-21 | 2024-12-23 | 64
C-52-0304-CMA09-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-07 | 2024-11-09 | 2024-12-21 | 2024-12-24 | 71
C-52-0304-CMA09-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-08 | 2024-11-11 | 2024-12-23 | 2024-12-25 | 71
C-52-0304-CMA09-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-09 | 2024-11-12 | 2024-12-24 | 2024-12-26 | 71
C-52-0304-CMA09-1060 | Holiday Testing | 1 | 1 | 2024-11-12 | 2024-11-13 | 2024-12-26 | 2024-12-27 | 71
C-52-0304-CMA09-1070 | Padding | 1 | 1 | 2024-11-13 | 2024-11-14 | 2024-12-27 | 2024-12-28 | 71
Crossing Manual @ KP 97+341 (FX-18) |  | 54 | 54 | 2024-11-06 | 2024-11-22 | 2024-11-14 | 2025-01-20 | 53
C-52-0304-CMA10-1000 | Trench Excavation | 6 | 6 | 2024-11-06 | 2024-11-13 | 2024-11-14 | 2024-11-21 | 95
C-52-0304-CMA10-1010 | Bedding | 1 | 1 | 2024-11-12 | 2024-11-13 | 2024-11-20 | 2024-11-21 | 95
C-52-0304-CMA10-1020 | Lowering | 1 | 1 | 2024-11-15 | 2024-11-16 | 2025-01-13 | 2025-01-14 | 53
C-52-0304-CMA10-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-15 | 2024-11-18 | 2025-01-13 | 2025-01-15 | 53
C-52-0304-CMA10-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-16 | 2024-11-19 | 2025-01-14 | 2025-01-16 | 53
C-52-0304-CMA10-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-18 | 2024-11-20 | 2025-01-15 | 2025-01-17 | 53
C-52-0304-CMA10-1060 | Holiday Testing | 1 | 1 | 2024-11-20 | 2024-11-21 | 2025-01-17 | 2025-01-18 | 53
C-52-0304-CMA10-1070 | Padding | 1 | 1 | 2024-11-21 | 2024-11-22 | 2025-01-18 | 2025-01-20 | 53
Crossing Manual @ KP 95+277 (CX-17) |  | 15 | 15 | 2024-09-28 | 2024-11-16 | 2024-12-18 | 2025-01-06 | 65
C-52-0304-CMA11-1000 | Trench Excavation | 6 | 6 | 2024-09-28 | 2024-10-05 | 2024-12-18 | 2024-12-25 | 53
C-52-0304-CMA11-1010 | Bedding | 1 | 1 | 2024-10-04 | 2024-10-05 | 2024-12-24 | 2024-12-25 | 63
C-52-0304-CMA11-1020 | Lowering | 1 | 1 | 2024-11-09 | 2024-11-11 | 2024-12-28 | 2024-12-30 | 60
C-52-0304-CMA11-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-09 | 2024-11-12 | 2024-12-28 | 2024-12-31 | 65
C-52-0304-CMA11-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-11 | 2024-11-13 | 2024-12-30 | 2025-01-02 | 65
C-52-0304-CMA11-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-12 | 2024-11-14 | 2024-12-31 | 2025-01-03 | 65
C-52-0304-CMA11-1060 | Holiday Testing | 1 | 1 | 2024-11-14 | 2024-11-15 | 2025-01-03 | 2025-01-04 | 65
C-52-0304-CMA11-1070 | Padding | 1 | 1 | 2024-11-15 | 2024-11-16 | 2025-01-04 | 2025-01-06 | 65
Crossing Manual @ KP 95+304 (PX-27) |  | 12 | 12 | 2024-10-05 | 2024-11-18 | 2024-12-25 | 2025-01-09 | 62
C-52-0304-CMA12-1000 | Trench Excavation | 6 | 6 | 2024-10-05 | 2024-10-12 | 2024-12-25 | 2025-01-02 | 53
C-52-0304-CMA12-1010 | Bedding | 1 | 1 | 2024-10-11 | 2024-10-12 | 2024-12-31 | 2025-01-02 | 58
C-52-0304-CMA12-1020 | Lowering | 1 | 1 | 2024-11-11 | 2024-11-12 | 2025-01-02 | 2025-01-03 | 58
C-52-0304-CMA12-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-11 | 2024-11-13 | 2025-01-02 | 2025-01-04 | 62
C-52-0304-CMA12-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-12 | 2024-11-14 | 2025-01-03 | 2025-01-06 | 62
C-52-0304-CMA12-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-13 | 2024-11-15 | 2025-01-04 | 2025-01-07 | 62
C-52-0304-CMA12-1060 | Holiday Testing | 1 | 1 | 2024-11-15 | 2024-11-16 | 2025-01-07 | 2025-01-08 | 62
C-52-0304-CMA12-1070 | Padding | 1 | 1 | 2024-11-16 | 2024-11-18 | 2025-01-08 | 2025-01-09 | 62
Crossing Manual @ KP 95+542 (CX-X1) |  | 12 | 12 | 2024-10-12 | 2024-11-19 | 2025-01-02 | 2025-01-16 | 56
C-52-0304-CMA13-1000 | Trench Excavation | 6 | 6 | 2024-10-12 | 2024-10-19 | 2025-01-02 | 2025-01-09 | 53
C-52-0304-CMA13-1010 | Bedding | 1 | 1 | 2024-10-18 | 2024-10-19 | 2025-01-08 | 2025-01-09 | 53
C-52-0304-CMA13-1020 | Lowering | 1 | 1 | 2024-11-12 | 2024-11-13 | 2025-01-09 | 2025-01-10 | 53
C-52-0304-CMA13-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-12 | 2024-11-14 | 2025-01-09 | 2025-01-11 | 56
C-52-0304-CMA13-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-13 | 2024-11-15 | 2025-01-10 | 2025-01-13 | 56
C-52-0304-CMA13-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-14 | 2024-11-16 | 2025-01-11 | 2025-01-14 | 56
C-52-0304-CMA13-1060 | Holiday Testing | 1 | 1 | 2024-11-16 | 2024-11-18 | 2025-01-14 | 2025-01-15 | 56
C-52-0304-CMA13-1070 | Padding | 1 | 1 | 2024-11-18 | 2024-11-19 | 2025-01-15 | 2025-01-16 | 56
Crossing Manual @ KP 91+674 (FX-15) |  | 19 | 19 | 2024-09-10 | 2024-11-13 | 2024-11-28 | 2024-12-23 | 76
C-52-0304-CMA14-0970 | Excavation (Manual-Trial Pit) | 5 | 5 | 2024-09-10 | 2024-09-17 | 2024-11-28 | 2024-12-06 | 53
C-52-0304-CMA14-0980 | Sabkha Gatch Laying | 5 | 5 | 2024-09-17 | 2024-09-23 | 2024-12-06 | 2024-12-12 | 68
C-52-0304-CMA14-0990 | Sabka Gatch Compaction | 5 | 5 | 2024-09-18 | 2024-09-24 | 2024-12-07 | 2024-12-13 | 68
C-52-0304-CMA14-1000 | Trench Excavation | 2 | 2 | 2024-09-24 | 2024-09-26 | 2024-12-13 | 2024-12-16 | 68
C-52-0304-CMA14-1010 | Bedding | 1 | 1 | 2024-09-25 | 2024-09-26 | 2024-12-14 | 2024-12-16 | 68
C-52-0304-CMA14-1020 | Lowering | 1 | 1 | 2024-11-06 | 2024-11-07 | 2024-12-16 | 2024-12-17 | 68
C-52-0304-CMA14-1030 | Section Tie-in Welding | 2 | 2 | 2024-11-06 | 2024-11-08 | 2024-12-16 | 2024-12-18 | 76
C-52-0304-CMA14-1040 | NDT (Tie-in Joint) | 2 | 2 | 2024-11-07 | 2024-11-09 | 2024-12-17 | 2024-12-19 | 76
C-52-0304-CMA14-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2024-11-08 | 2024-11-11 | 2024-12-18 | 2024-12-20 | 76
C-52-0304-CMA14-1060 | Holiday Testing | 1 | 1 | 2024-11-11 | 2024-11-12 | 2024-12-20 | 2024-12-21 | 76
C-52-0304-CMA14-1070 | Padding | 1 | 1 | 2024-11-12 | 2024-11-13 | 2024-12-21 | 2024-12-23 | 76
Open Cut - Rig / Track RoadCCOPL52389 |  | 54 | 54 | 2024-10-30 | 2025-01-04 | 2024-11-30 | 2025-02-04 | 39
Crossing Mechanical (TX-31B) |  | 21 | 21 | 2024-10-30 | 2024-11-21 | 2024-11-30 | 2024-12-27 | 72
C-52-0304-CME01-1000 | Trench Excavation | 2 | 2 | 2024-10-30 | 2024-11-01 | 2024-11-30 | 2024-12-04 | 39
C-52-0304-CME01-1010 | Bedding | 2 | 2 | 2024-11-01 | 2024-11-04 | 2024-12-05 | 2024-12-06 | 52
C-52-0304-CME01-1020 | Lowering | 2 | 2 | 2024-11-04 | 2024-11-06 | 2024-12-10 | 2024-12-12 | 50
C-52-0304-CME01-1030 | Section Tie-in Welding | 3 | 3 | 2024-11-06 | 2024-11-09 | 2024-12-12 | 2024-12-16 | 72
C-52-0304-CME01-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-11-09 | 2024-11-13 | 2024-12-16 | 2024-12-19 | 72
C-52-0304-CME01-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-11-13 | 2024-11-16 | 2024-12-19 | 2024-12-23 | 72
C-52-0304-CME01-1060 | Holiday Testing | 2 | 2 | 2024-11-16 | 2024-11-19 | 2024-12-23 | 2024-12-25 | 72
C-52-0304-CME01-1070 | Padding & Back Filling | 2 | 2 | 2024-11-19 | 2024-11-21 | 2024-12-25 | 2024-12-27 | 72
Crossing Mechanical (TX-32) |  | 20 | 20 | 2024-11-02 | 2024-11-25 | 2024-12-06 | 2024-12-30 | 70
C-52-0304-CME02-1000 | Trench Excavation | 2 | 2 | 2024-11-02 | 2024-11-05 | 2024-12-06 | 2024-12-07 | 39
C-52-0304-CME02-1010 | Bedding | 2 | 2 | 2024-11-05 | 2024-11-07 | 2024-12-09 | 2024-12-10 | 51
C-52-0304-CME02-1020 | Lowering | 2 | 2 | 2024-11-07 | 2024-11-09 | 2024-12-12 | 2024-12-14 | 50
C-52-0304-CME02-1030 | Section Tie-in Welding | 3 | 3 | 2024-11-09 | 2024-11-13 | 2024-12-14 | 2024-12-18 | 70
C-52-0304-CME02-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-11-13 | 2024-11-16 | 2024-12-18 | 2024-12-21 | 70
C-52-0304-CME02-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-11-16 | 2024-11-20 | 2024-12-21 | 2024-12-25 | 70
C-52-0304-CME02-1060 | Holiday Testing | 2 | 2 | 2024-11-20 | 2024-11-22 | 2024-12-25 | 2024-12-27 | 70
C-52-0304-CME02-1070 | Padding & Back Filling | 2 | 2 | 2024-11-22 | 2024-11-25 | 2024-12-27 | 2024-12-30 | 70
Crossing Mechanical (TX-33) |  | 19 | 19 | 2024-11-06 | 2024-11-28 | 2024-12-10 | 2025-01-02 | 68
C-52-0304-CME03-1000 | Trench Excavation | 2 | 2 | 2024-11-06 | 2024-11-08 | 2024-12-10 | 2024-12-11 | 39
C-52-0304-CME03-1010 | Bedding | 2 | 2 | 2024-11-08 | 2024-11-11 | 2024-12-12 | 2024-12-13 | 50
C-52-0304-CME03-1020 | Lowering | 2 | 2 | 2024-11-11 | 2024-11-13 | 2024-12-14 | 2024-12-17 | 50
C-52-0304-CME03-1030 | Section Tie-in Welding | 3 | 3 | 2024-11-13 | 2024-11-16 | 2024-12-17 | 2024-12-20 | 68
C-52-0304-CME03-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-11-16 | 2024-11-20 | 2024-12-20 | 2024-12-24 | 68
C-52-0304-CME03-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-11-20 | 2024-11-23 | 2024-12-24 | 2024-12-27 | 68
C-52-0304-CME03-1060 | Holiday Testing | 2 | 2 | 2024-11-23 | 2024-11-26 | 2024-12-27 | 2024-12-30 | 68
C-52-0304-CME03-1070 | Padding & Back Filling | 2 | 2 | 2024-11-26 | 2024-11-28 | 2024-12-30 | 2025-01-02 | 68
Crossing Mechanical (TX-34) |  | 19 | 19 | 2024-11-09 | 2024-12-04 | 2024-12-13 | 2025-01-04 | 65
C-52-0304-CME04-1000 | Trench Excavation | 2 | 2 | 2024-11-09 | 2024-11-12 | 2024-12-13 | 2024-12-14 | 39
C-52-0304-CME04-1010 | Bedding | 2 | 2 | 2024-11-12 | 2024-11-14 | 2024-12-16 | 2024-12-17 | 49
C-52-0304-CME04-1020 | Lowering | 2 | 2 | 2024-11-14 | 2024-11-16 | 2024-12-18 | 2024-12-19 | 49
C-52-0304-CME04-1030 | Section Tie-in Welding | 3 | 3 | 2024-11-16 | 2024-11-20 | 2024-12-20 | 2024-12-23 | 65
C-52-0304-CME04-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-11-20 | 2024-11-23 | 2024-12-24 | 2024-12-26 | 65
C-52-0304-CME04-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-11-23 | 2024-11-27 | 2024-12-27 | 2024-12-30 | 65
C-52-0304-CME04-1060 | Holiday Testing | 2 | 2 | 2024-11-27 | 2024-11-29 | 2024-12-31 | 2025-01-02 | 65
C-52-0304-CME04-1070 | Padding & Back Filling | 2 | 2 | 2024-11-29 | 2024-12-04 | 2025-01-03 | 2025-01-04 | 65
Crossing Mechanical (TX-35) |  | 19 | 19 | 2024-11-13 | 2024-12-07 | 2024-12-17 | 2025-01-08 | 62
C-52-0304-CME05-1000 | Trench Excavation | 2 | 2 | 2024-11-13 | 2024-11-15 | 2024-12-17 | 2024-12-18 | 39
C-52-0304-CME05-1010 | Bedding | 2 | 2 | 2024-11-15 | 2024-11-18 | 2024-12-19 | 2024-12-20 | 48
C-52-0304-CME05-1020 | Lowering | 2 | 2 | 2024-11-18 | 2024-11-20 | 2024-12-21 | 2024-12-23 | 48
C-52-0304-CME05-1030 | Section Tie-in Welding | 3 | 3 | 2024-11-20 | 2024-11-23 | 2024-12-24 | 2024-12-26 | 62
C-52-0304-CME05-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-11-23 | 2024-11-27 | 2024-12-27 | 2024-12-30 | 62
C-52-0304-CME05-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-11-27 | 2024-11-30 | 2024-12-31 | 2025-01-03 | 62
C-52-0304-CME05-1060 | Holiday Testing | 2 | 2 | 2024-11-30 | 2024-12-05 | 2025-01-04 | 2025-01-06 | 62
C-52-0304-CME05-1070 | Padding & Back Filling | 2 | 2 | 2024-12-05 | 2024-12-07 | 2025-01-07 | 2025-01-08 | 62
Crossing Mechanical (TX-36) |  | 19 | 19 | 2024-11-16 | 2024-12-11 | 2024-12-20 | 2025-01-11 | 59
C-52-0304-CME06-1000 | Trench Excavation | 2 | 2 | 2024-11-16 | 2024-11-19 | 2024-12-20 | 2024-12-21 | 39
C-52-0304-CME06-1010 | Bedding | 2 | 2 | 2024-11-19 | 2024-11-21 | 2024-12-23 | 2024-12-24 | 47
C-52-0304-CME06-1020 | Lowering | 2 | 2 | 2024-11-21 | 2024-11-23 | 2024-12-25 | 2024-12-26 | 47
C-52-0304-CME06-1030 | Section Tie-in Welding | 3 | 3 | 2024-11-23 | 2024-11-27 | 2024-12-27 | 2024-12-30 | 59
C-52-0304-CME06-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-11-27 | 2024-11-30 | 2024-12-31 | 2025-01-03 | 59
C-52-0304-CME06-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-11-30 | 2024-12-06 | 2025-01-04 | 2025-01-07 | 59
C-52-0304-CME06-1060 | Holiday Testing | 2 | 2 | 2024-12-06 | 2024-12-09 | 2025-01-08 | 2025-01-09 | 59
C-52-0304-CME06-1070 | Padding & Back Filling | 2 | 2 | 2024-12-09 | 2024-12-11 | 2025-01-10 | 2025-01-11 | 59
Crossing Mechanical (TX-37) |  | 19 | 19 | 2024-11-20 | 2024-12-14 | 2024-12-24 | 2025-01-15 | 56
C-52-0304-CME07-1000 | Trench Excavation | 2 | 2 | 2024-11-20 | 2024-11-22 | 2024-12-24 | 2024-12-25 | 39
C-52-0304-CME07-1010 | Bedding | 2 | 2 | 2024-11-22 | 2024-11-25 | 2024-12-26 | 2024-12-27 | 46
C-52-0304-CME07-1020 | Lowering | 2 | 2 | 2024-11-25 | 2024-11-27 | 2024-12-28 | 2024-12-30 | 46
C-52-0304-CME07-1030 | Section Tie-in Welding | 3 | 3 | 2024-11-27 | 2024-11-30 | 2024-12-31 | 2025-01-03 | 56
C-52-0304-CME07-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-11-30 | 2024-12-06 | 2025-01-04 | 2025-01-07 | 56
C-52-0304-CME07-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-12-06 | 2024-12-10 | 2025-01-08 | 2025-01-10 | 56
C-52-0304-CME07-1060 | Holiday Testing | 2 | 2 | 2024-12-10 | 2024-12-12 | 2025-01-11 | 2025-01-13 | 56
C-52-0304-CME07-1070 | Padding & Back Filling | 2 | 2 | 2024-12-12 | 2024-12-14 | 2025-01-14 | 2025-01-15 | 56
Crossing Mechanical (TX-38,39) |  | 19 | 19 | 2024-11-23 | 2024-12-18 | 2024-12-27 | 2025-01-18 | 53
C-52-0304-CME08-1000 | Trench Excavation | 2 | 2 | 2024-11-23 | 2024-11-26 | 2024-12-27 | 2024-12-28 | 39
C-52-0304-CME08-1010 | Bedding | 2 | 2 | 2024-11-26 | 2024-11-28 | 2024-12-30 | 2024-12-31 | 45
C-52-0304-CME08-1020 | Lowering | 2 | 2 | 2024-11-28 | 2024-11-30 | 2025-01-02 | 2025-01-03 | 45
C-52-0304-CME08-1030 | Section Tie-in Welding | 3 | 3 | 2024-11-30 | 2024-12-06 | 2025-01-04 | 2025-01-07 | 53
C-52-0304-CME08-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-12-06 | 2024-12-10 | 2025-01-08 | 2025-01-10 | 53
C-52-0304-CME08-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-12-10 | 2024-12-13 | 2025-01-11 | 2025-01-14 | 53
C-52-0304-CME08-1060 | Holiday Testing | 2 | 2 | 2024-12-13 | 2024-12-16 | 2025-01-15 | 2025-01-16 | 53
C-52-0304-CME08-1070 | Padding & Back Filling | 2 | 2 | 2024-12-16 | 2024-12-18 | 2025-01-17 | 2025-01-18 | 53
Crossing Mechanical (TX-40) |  | 19 | 19 | 2024-11-27 | 2024-12-21 | 2024-12-31 | 2025-01-22 | 50
C-52-0304-CME09-1000 | Trench Excavation | 2 | 2 | 2024-11-27 | 2024-11-29 | 2024-12-31 | 2025-01-02 | 39
C-52-0304-CME09-1010 | Bedding | 2 | 2 | 2024-11-29 | 2024-12-04 | 2025-01-03 | 2025-01-04 | 44
C-52-0304-CME09-1020 | Lowering | 2 | 2 | 2024-12-04 | 2024-12-06 | 2025-01-06 | 2025-01-07 | 44
C-52-0304-CME09-1030 | Section Tie-in Welding | 3 | 3 | 2024-12-06 | 2024-12-10 | 2025-01-08 | 2025-01-10 | 50
C-52-0304-CME09-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-12-10 | 2024-12-13 | 2025-01-11 | 2025-01-14 | 50
C-52-0304-CME09-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-12-13 | 2024-12-17 | 2025-01-15 | 2025-01-17 | 50
C-52-0304-CME09-1060 | Holiday Testing | 2 | 2 | 2024-12-17 | 2024-12-19 | 2025-01-18 | 2025-01-20 | 50
C-52-0304-CME09-1070 | Padding & Back Filling | 2 | 2 | 2024-12-19 | 2024-12-21 | 2025-01-21 | 2025-01-22 | 50
Crossing Mechanical (RX-14) |  | 22 | 22 | 2024-11-30 | 2024-12-28 | 2025-01-04 | 2025-01-29 | 44
C-52-0304-CME10-1000 | Road Diversion & Trench Excavation | 4 | 4 | 2024-11-30 | 2024-12-07 | 2025-01-04 | 2025-01-08 | 39
C-52-0304-CME10-1010 | Bedding | 2 | 2 | 2024-12-07 | 2024-12-10 | 2025-01-09 | 2025-01-10 | 41
C-52-0304-CME10-1020 | Lowering | 2 | 2 | 2024-12-10 | 2024-12-12 | 2025-01-11 | 2025-01-13 | 41
C-52-0304-CME10-1030 | Section Tie-in Welding | 3 | 3 | 2024-12-12 | 2024-12-16 | 2025-01-14 | 2025-01-16 | 44
C-52-0304-CME10-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-12-16 | 2024-12-19 | 2025-01-17 | 2025-01-20 | 44
C-52-0304-CME10-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-12-19 | 2024-12-23 | 2025-01-21 | 2025-01-23 | 44
C-52-0304-CME10-1060 | Holiday Testing | 2 | 2 | 2024-12-23 | 2024-12-25 | 2025-01-24 | 2025-01-25 | 44
C-52-0304-CME10-1070 | Padding & Back Filling | 3 | 3 | 2024-12-25 | 2024-12-28 | 2025-01-27 | 2025-01-29 | 44
Crossing Mechanical (TX-41) |  | 19 | 19 | 2024-12-09 | 2024-12-31 | 2025-01-10 | 2025-01-31 | 42
C-52-0304-CME11-1000 | Trench Excavation | 2 | 2 | 2024-12-09 | 2024-12-11 | 2025-01-10 | 2025-01-11 | 39
C-52-0304-CME11-1010 | Bedding | 2 | 2 | 2024-12-11 | 2024-12-13 | 2025-01-13 | 2025-01-14 | 40
C-52-0304-CME11-1020 | Lowering | 2 | 2 | 2024-12-13 | 2024-12-16 | 2025-01-15 | 2025-01-16 | 40
C-52-0304-CME11-1030 | Section Tie-in Welding | 3 | 3 | 2024-12-16 | 2024-12-19 | 2025-01-17 | 2025-01-20 | 42
C-52-0304-CME11-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-12-19 | 2024-12-23 | 2025-01-21 | 2025-01-23 | 42
C-52-0304-CME11-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-12-23 | 2024-12-26 | 2025-01-24 | 2025-01-27 | 42
C-52-0304-CME11-1060 | Holiday Testing | 2 | 2 | 2024-12-26 | 2024-12-28 | 2025-01-28 | 2025-01-29 | 42
C-52-0304-CME11-1070 | Padding & Back Filling | 2 | 2 | 2024-12-28 | 2024-12-31 | 2025-01-30 | 2025-01-31 | 42
Crossing Mechanical (TX-42) |  | 19 | 19 | 2024-12-12 | 2025-01-04 | 2025-01-14 | 2025-02-04 | 39
C-52-0304-CME12-1000 | Trench Excavation | 2 | 2 | 2024-12-12 | 2024-12-14 | 2025-01-14 | 2025-01-15 | 39
C-52-0304-CME12-1010 | Bedding | 2 | 2 | 2024-12-14 | 2024-12-17 | 2025-01-16 | 2025-01-17 | 39
C-52-0304-CME12-1020 | Lowering | 2 | 2 | 2024-12-17 | 2024-12-19 | 2025-01-18 | 2025-01-20 | 39
C-52-0304-CME12-1030 | Section Tie-in Welding | 3 | 3 | 2024-12-19 | 2024-12-23 | 2025-01-21 | 2025-01-23 | 39
C-52-0304-CME12-1040 | NDT (Tie-in Joint) | 3 | 3 | 2024-12-23 | 2024-12-26 | 2025-01-24 | 2025-01-27 | 39
C-52-0304-CME12-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2024-12-26 | 2024-12-30 | 2025-01-28 | 2025-01-30 | 39
C-52-0304-CME12-1060 | Holiday Testing | 2 | 2 | 2024-12-30 | 2025-01-02 | 2025-01-31 | 2025-02-01 | 39
C-52-0304-CME12-1070 | Padding & Back Filling | 2 | 2 | 2025-01-02 | 2025-01-04 | 2025-02-03 | 2025-02-04 | 39
CP Works TemporaryCCOP52EL41 |  | 47 | 47 | 2025-03-08 | 2025-05-12 | 2024-12-30 | 2025-02-22 | 31
C-52-0304-PL-CA-5200 | Installation of CP Test Post | 45 | 45 | 2025-03-08 | 2025-05-09 | 2024-12-30 | 2025-02-20 | 31
C-52-0304-PL-CA-5210 | Glanding & Termination of Temp. CP S/m | 2 | 2 | 2025-05-09 | 2025-05-12 | 2025-02-21 | 2025-02-22 | 31
Test Stations & Anode BedsCCOP52EL39 |  | 45 | 45 | 2025-03-08 | 2025-05-09 | 2024-12-30 | 2025-02-20 | 30
C-52-0304-PL-CA-5600 | Installation of Temp. Anode | 45 | 45 | 2025-03-08 | 2025-05-09 | 2024-12-30 | 2025-02-20 | 30
PaddingCCOPL52386 |  | 45 | 45 | 2025-03-09 | 2025-05-10 | 2024-12-31 | 2025-02-21 | 29
C-52-0304-PL-CI-6000 | Padding | 45 | 45 | 2025-03-09 | 2025-05-10 | 2024-12-31 | 2025-02-21 | 29
BermingCCOPL52395 |  | 54 | 54 | 2025-03-17 | 2025-05-27 | 2025-01-07 | 2025-03-12 | 129
C-52-0304-PL-CI-6800 | Gatch Laying & Levelling | 47 | 47 | 2025-03-17 | 2025-05-19 | 2025-01-07 | 2025-03-01 | 64
C-52-0304-PL-CI-6810 | Gatch Compaction | 47 | 47 | 2025-03-25 | 2025-05-24 | 2025-01-13 | 2025-03-09 | 64
C-52-0304-PL-CI-7800 | Installation of Marker Post/Sign Board | 47 | 47 | 2025-03-26 | 2025-05-26 | 2025-01-14 | 2025-03-11 | 129
C-52-0304-PL-CI-7810 | Installation of Crash Barriers (If any) | 47 | 47 | 2025-03-28 | 2025-05-27 | 2025-01-15 | 2025-03-12 | 129
NDRC by Micro Tunneling Method |  | 57 | 32 | 2024-12-16 | 2025-01-15 | 27-Sep-24 A | 2024-12-04 | 89
NDRC-13 (incl Hydrotest) @ CH 90+070 - 90+175 (Open Cut*) |  | 57 | 2 | 2024-12-16 | 2025-01-08 | 27-Sep-24 A | 2024-12-04 | 89
Entry & Exit Pit ConstructionCCOPL52952 |  | 14 | 0 | 2024-12-16 | 2024-12-18 | 27-Sep-24 A | 14-Oct-24 A
C-52-0304-CME06-1090 | Trench Excavation | 14 | 0 | 2024-12-16 | 2024-12-18 | 27-Sep-24 A | 14-Oct-24 A
Tunneling & Jack UpCCOPL57482 |  | 14 | 0 | 2024-12-18 | 2024-12-20 | 27-Sep-24 A | 14-Oct-24 A
C-52-0304-CME06-1100 | Bedding | 14 | 0 | 2024-12-18 | 2024-12-20 | 27-Sep-24 A | 14-Oct-24 A
Pipe Lowering, Welding, NDT & CoatingCCOPL57492 |  | 41 | 0 | 2024-12-20 | 2025-01-03 | 14-Oct-24 A | 2024-11-30 | 89
C-52-0304-CME06-1110 | Lowering | 6 | 0 | 2024-12-20 | 2024-12-23 | 14-Oct-24 A | 20-Oct-24 A
C-52-0304-CME06-1120 | Section Tie-in Welding | 35 | 0 | 2024-12-23 | 2024-12-26 | 20-Oct-24 A | 2024-11-30 | 89
C-52-0304-CME06-1130 | NDT (Tie-in Joint) | 35 | 0 | 2024-12-26 | 2024-12-30 | 20-Oct-24 A | 2024-11-30 | 89
C-52-0304-CME06-1140 | Ext. Joint Coating (Tie-in Joint) | 35 | 0 | 2024-12-30 | 2025-01-03 | 20-Oct-24 A | 2024-11-30 | 89
HydrotestingCCOPL57502 |  | 35 | 0 | 2025-01-03 | 2025-01-06 | 20-Oct-24 A | 2024-11-30 | 89
C-52-0304-CME06-1150 | Holiday Testing | 35 | 0 | 2025-01-03 | 2025-01-06 | 20-Oct-24 A | 2024-11-30 | 89
Re-Instatement of Entry & Exit PitCCOPL57512 |  | 35 | 2 | 2025-01-06 | 2025-01-08 | 23-Oct-24 A | 2024-12-04 | 89
C-52-0304-CME06-1160 | Padding & Back Filling | 35 | 2 | 2025-01-06 | 2025-01-08 | 23-Oct-24 A | 2024-12-04 | 89
NDRC-13A (incl Hydrotest) @ CH 91+830 - 91+930 (Open Cut*) |  | 30 | 5 | 2024-12-19 | 2025-01-11 | 27-Sep-24 A | 2024-10-31 | 116
Entry & Exit Pit ConstructionCCOPL52954 |  | 25 | 0 | 2024-12-19 | 2024-12-21 | 27-Sep-24 A | 2024-10-26 | 110
C-52-0304-CME06-1170 | Trench Excavation | 25 | 0 | 2024-12-19 | 2024-12-21 | 27-Sep-24 A | 2024-10-26 | 110
Tunneling & Jack UpCCOPL57142 |  | 2 | 2 | 2024-12-21 | 2024-12-24 | 2024-10-26 | 2024-10-28 | 116
C-52-0304-CME06-1180 | Bedding | 2 | 2 | 2024-12-21 | 2024-12-24 | 2024-10-26 | 2024-10-28 | 116
Pipe Lowering, Welding, NDT & CoatingCCOPL5715 |  | 9 | 3 | 2024-12-24 | 2025-01-07 | 20-Oct-24 A | 2024-10-30 | 116
C-52-0304-CME06-1190 | Lowering | 2 | 2 | 2024-12-24 | 2024-12-26 | 2024-10-29 | 2024-10-30 | 116
C-52-0304-CME06-1200 | Section Tie-in Welding | 9 | 3 | 2024-12-26 | 2024-12-30 | 20-Oct-24 A | 2024-10-30 | 116
C-52-0304-CME06-1210 | NDT (Tie-in Joint) | 9 | 3 | 2024-12-30 | 2025-01-03 | 20-Oct-24 A | 2024-10-30 | 116
C-52-0304-CME06-1220 | Ext. Joint Coating (Tie-in Joint) | 9 | 3 | 2025-01-03 | 2025-01-07 | 20-Oct-24 A | 2024-10-30 | 116
HydrotestingCCOPL57162 |  | 8 | 2 | 2025-01-07 | 2025-01-09 | 20-Oct-24 A | 2024-10-29 | 116
C-52-0304-CME06-1230 | Holiday Testing | 8 | 2 | 2025-01-07 | 2025-01-09 | 20-Oct-24 A | 2024-10-29 | 116
Re-Instatement of Entry & Exit PitCCOPL57172 |  | 2 | 2 | 2025-01-09 | 2025-01-11 | 2024-10-30 | 2024-10-31 | 116
C-52-0304-CME06-1240 | Padding & Back Filling | 2 | 2 | 2025-01-09 | 2025-01-11 | 2024-10-30 | 2024-10-31 | 116
NDRC-14 (incl Hydrotest) @ CH 92+050 - 92+150 (Open Cut*) |  | 16 | 10 | 2024-12-23 | 2025-01-15 | 20-Oct-24 A | 2024-11-07 | 110
Entry & Exit Pit ConstructionCCOPL52956 |  | 2 | 2 | 2024-12-23 | 2024-12-25 | 2024-10-28 | 2024-10-29 | 110
C-52-0304-CME06-1250 | Trench Excavation | 2 | 2 | 2024-12-23 | 2024-12-25 | 2024-10-28 | 2024-10-29 | 110
Tunneling & Jack UpCCOPL57802 |  | 2 | 2 | 2024-12-25 | 2024-12-27 | 2024-10-30 | 2024-10-31 | 110
C-52-0304-CME06-1260 | Bedding | 2 | 2 | 2024-12-25 | 2024-12-27 | 2024-10-30 | 2024-10-31 | 110
Pipe Lowering, Welding, NDT & CoatingCCOPL57812 |  | 12 | 3 | 2024-12-27 | 2025-01-10 | 20-Oct-24 A | 2024-11-02 | 110
C-52-0304-CME06-1270 | Lowering | 2 | 2 | 2024-12-27 | 2024-12-30 | 2024-11-01 | 2024-11-02 | 110
C-52-0304-CME06-1280 | Section Tie-in Welding | 12 | 3 | 2024-12-30 | 2025-01-03 | 20-Oct-24 A | 2024-11-02 | 110
C-52-0304-CME06-1290 | NDT (Tie-in Joint) | 12 | 3 | 2025-01-03 | 2025-01-07 | 20-Oct-24 A | 2024-11-02 | 110
C-52-0304-CME06-1300 | Ext. Joint Coating (Tie-in Joint) | 12 | 3 | 2025-01-07 | 2025-01-10 | 20-Oct-24 A | 2024-11-02 | 110
HydrotestingCCOPL57822 |  | 2 | 2 | 2025-01-10 | 2025-01-13 | 2024-11-04 | 2024-11-05 | 110
C-52-0304-CME06-1310 | Holiday Testing | 2 | 2 | 2025-01-10 | 2025-01-13 | 2024-11-04 | 2024-11-05 | 110
Re-Instatement of Entry & Exit PitCCOPL57832 |  | 2 | 2 | 2025-01-13 | 2025-01-15 | 2024-11-06 | 2024-11-07 | 110
C-52-0304-CME06-1320 | Padding & Back Filling | 2 | 2 | 2025-01-13 | 2025-01-15 | 2024-11-06 | 2024-11-07 | 110
Cathodic Protection |  | 55 | 55 | 2024-12-25 | 2025-05-20 | 2024-12-28 | 2025-03-03 | 31
Civil Works |  | 37 | 37 | 2024-12-28 | 2025-02-10 | 2025-01-02 | 2025-02-13 | 39
Backfilling & Reinstatement for CP (for Crossings)CCOP52CS39 |  | 37 | 37 | 2024-12-28 | 2025-02-10 | 2025-01-02 | 2025-02-13 | 39
C-52-0304-PIPEL-5260 | Backfilling & Reinstatement for CP (for Crossings) | 37 | 37 | 2024-12-28 | 2025-02-10 | 2025-01-02 | 2025-02-13 | 39
CP Works |  | 55 | 55 | 2024-12-25 | 2025-05-20 | 2024-12-28 | 2025-03-03 | 31
CP Works (for Crossings)CCOP52EL53 |  | 55 | 55 | 2024-12-25 | 2025-05-20 | 2024-12-28 | 2025-03-03 | 31
C-52-0304-PL-CA-5220 | Installation of Test Post for Crossing | 32 | 32 | 2024-12-25 | 2025-01-31 | 2024-12-28 | 2025-02-04 | 39
C-52-0304-PL-CA-5230 | Installation of CP JB's | 32 | 32 | 2024-12-25 | 2025-01-31 | 2024-12-28 | 2025-02-04 | 47
C-52-0304-PL-CA-5240 | Installation of CP TR | 21 | 21 | 2025-01-17 | 2025-02-10 | 2025-01-21 | 2025-02-13 | 39
C-52-0304-PL-CA-5250 | CIP/DCVG Survey | 7 | 7 | 2025-05-12 | 2025-05-20 | 2025-02-24 | 2025-03-03 | 31
Telecommunication Works |  | 55 | 55 | 2025-03-09 | 2025-05-22 | 2024-12-31 | 2025-03-06 | 29
Telecom Works along Pipeline CCOP52IC37 |  | 55 | 55 | 2025-03-09 | 2025-05-22 | 2024-12-31 | 2025-03-06 | 29
C-52-0304-PL-TE-8200 | FO - Cable Pulling/ Laying | 52 | 52 | 2025-03-09 | 2025-05-19 | 2024-12-31 | 2025-03-01 | 29
C-52-0304-PL-TE-8210 | Termination/Splicing @ BVS | 3 | 3 | 2025-05-19 | 2025-05-22 | 2025-03-02 | 2025-03-06 | 29
52"x16.3 Km Pipeline from BVS-04 to BVS-05 at KP 114.2 |  | 400 | 246 | 2024-04-25 | 2025-09-26 | 25-Apr-24 A | 2025-08-28 | 57
52"x 16.3 Km Pipeline from BVS-04 to BVS-05 at KP 114.2-1 |  | 400 | 246 | 2024-04-25 | 2025-09-26 | 25-Apr-24 A | 2025-08-28 | 57
Main Pipeline |  | 400 | 242 | 2024-04-25 | 2025-09-26 | 25-Apr-24 A | 2025-08-28 | 57
ROW Access RoadCCOPL52412 |  | 179 | 20 | 2024-04-25 | 2024-08-26 | 25-Apr-24 A | 2024-11-25 | 36
C-52-0405-PL-CI-1800 | Non-Sabka ROW/Grading | 179 | 20 | 2024-04-25 | 2024-08-26 | 25-Apr-24 A | 2024-11-25 | 36
Cut & Fill in Sandy AreaCCOPL52438 |  | 114 | 45 | 2024-11-22 | 2024-12-27 | 12-Aug-24 A | 2024-12-26 | 71
C-52-0405-PL-CI-1400 | Cut & Fill (@ Non-Sabkha) | 114 | 45 | 2024-11-22 | 2024-12-27 | 12-Aug-24 A | 2024-12-26 | 71
Sabkha PadCCOPL52433 |  | 224 | 65 | 2024-04-25 | 2024-11-28 | 25-Apr-24 A | 2025-01-20 | 36
C-52-0405-PL-CI-2000 | Sabka Gatch Laying (Including ROW) - Layer 1 | 189 | 30 | 2024-04-25 | 2024-10-18 | 25-Apr-24 A | 2024-12-09 | 36
C-52-0405-PL-CI-2200 | Sabka Gatch Compaction (Including ROW) - Layer 1 | 194 | 30 | 2024-04-25 | 2024-10-24 | 25-Apr-24 A | 2024-12-14 | 36
C-52-0405-PL-CI-2010 | Sabka Gatch Laying - Layer 2 | 118 | 30 | 2024-10-14 | 2024-10-30 | 01-Aug-24 A | 2024-12-20 | 36
C-52-0405-PL-CI-2210 | Sabka Gatch Compaction - Layer 2 | 121 | 30 | 2024-10-19 | 2024-11-05 | 03-Aug-24 A | 2024-12-26 | 36
C-52-0405-PL-CI-2020 | Sabka Gatch Laying - Layer 3 | 125 | 30 | 2024-10-25 | 2024-11-11 | 05-Aug-24 A | 2025-01-02 | 36
C-52-0405-PL-CI-2220 | Sabka Gatch Compaction - Layer 3 | 128 | 30 | 2024-10-31 | 2024-11-16 | 07-Aug-24 A | 2025-01-08 | 36
C-52-0405-PL-CI-2030 | Sabka Gatch Laying - Layer 4 | 129 | 30 | 2024-11-06 | 2024-11-22 | 12-Aug-24 A | 2025-01-14 | 36
C-52-0405-PL-CI-2230 | Sabka Gatch Compaction - Layer 4 | 130 | 30 | 2024-11-12 | 2024-11-28 | 16-Aug-24 A | 2025-01-20 | 36
Excavation (incl Bedding)CCOPL52427 |  | 28 | 28 | 2025-04-11 | 2025-05-15 | 2025-01-29 | 2025-03-02 | 58
C-52-0405-PL-CI-2400 | Trench Excavation | 25 | 25 | 2025-04-11 | 2025-05-12 | 2025-01-29 | 2025-02-27 | 58
C-52-0405-PL-CI-2410 | Bedding | 25 | 25 | 2025-04-15 | 2025-05-15 | 2025-02-01 | 2025-03-02 | 58
Pipe StringingCCOPL52413 |  | 73 | 25 | 2024-11-28 | 2024-12-20 | 18-Oct-24 A | 2025-01-14 | 36
C-52-0405-PL-ME-2800 | Stringing (BVS-04 to BVS-05) | 73 | 25 | 2024-11-28 | 2024-12-20 | 18-Oct-24 A | 2025-01-14 | 36
Automatic WeldingCCOPL52420 |  | 35 | 35 | 2025-03-22 | 2025-05-08 | 2025-01-14 | 2025-02-24 | 36
C-52-0405-PL-ME-3600 | Automatic Welding | 35 | 35 | 2025-03-22 | 2025-05-08 | 2025-01-14 | 2025-02-24 | 36
NDT TestCCOPL52435 |  | 35 | 35 | 2025-03-23 | 2025-05-09 | 2025-01-15 | 2025-02-25 | 84
C-52-0405-PL-ME-4000 | NDT | 35 | 35 | 2025-03-23 | 2025-05-09 | 2025-01-15 | 2025-02-25 | 84
Ext. Joint CoatingCCOPL52418 |  | 100 | 100 | 2025-03-26 | 2025-06-09 | 2025-01-17 | 2025-05-24 | 27
C-52-0405-PL-ME-4400 | Ext. Joint Coating | 35 | 35 | 2025-03-26 | 2025-05-12 | 2025-01-17 | 2025-02-27 | 84
C-52-0405-PL-ME-4410 | Ext. Joint Coating (Tie-in Joint) | 25 | 25 | 2025-05-08 | 2025-06-09 | 2025-04-24 | 2025-05-24 | 27
Cold BendsCCOPL52419 |  | 30 | 30 | 2025-04-21 | 2025-05-27 | 2025-02-07 | 2025-03-18 | 76
C-52-0405-PL-ME-3200 | Cold Bends | 30 | 30 | 2025-04-21 | 2025-05-27 | 2025-02-07 | 2025-03-18 | 76
Pipe Lowering & Tie-in / NDTCCOPL52428 |  | 83 | 83 | 2025-04-21 | 2025-06-10 | 2025-02-07 | 2025-05-26 | 27
C-52-0405-PL-ME-4800 | Lowering | 25 | 25 | 2025-04-21 | 2025-05-21 | 2025-02-07 | 2025-03-10 | 76
C-52-0405-PL-ME-4810 | Section Tie-in Welding | 25 | 25 | 2025-05-05 | 2025-06-04 | 2025-04-22 | 2025-05-22 | 27
C-52-0405-PL-ME-4820 | NDT (Tie-in Joint) | 25 | 25 | 2025-05-07 | 2025-06-07 | 2025-04-23 | 2025-05-23 | 27
C-52-0405-PL-ME-4830 | Holiday Testing | 25 | 25 | 2025-05-09 | 2025-06-10 | 2025-04-25 | 2025-05-26 | 27
Crossings - UG CableCCOPL52421 |  | 63 | 63 | 2025-01-18 | 2025-06-10 | 2025-01-10 | 2025-04-04 | 97
Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) |  | 15 | 15 | 2025-04-21 | 2025-05-08 | 2025-01-29 | 2025-02-15 | 129
C-52-0405-CMA01-1000 | Trench Excavation | 8 | 8 | 2025-04-21 | 2025-04-30 | 2025-01-29 | 2025-02-07 | 77
C-52-0405-CMA01-1010 | Bedding | 1 | 1 | 2025-04-29 | 2025-04-30 | 2025-02-07 | 2025-02-08 | 102
C-52-0405-CMA01-1020 | Lowering | 1 | 1 | 2025-04-30 | 2025-05-01 | 2025-02-08 | 2025-02-10 | 102
C-52-0405-CMA01-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-30 | 2025-05-02 | 2025-02-08 | 2025-02-11 | 102
C-52-0405-CMA01-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-01 | 2025-05-03 | 2025-02-10 | 2025-02-12 | 129
C-52-0405-CMA01-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-02 | 2025-05-05 | 2025-02-11 | 2025-02-13 | 129
C-52-0405-CMA01-1060 | Holiday Testing | 1 | 1 | 2025-05-05 | 2025-05-07 | 2025-02-13 | 2025-02-14 | 129
C-52-0405-CMA01-1070 | Padding | 1 | 1 | 2025-05-07 | 2025-05-08 | 2025-02-14 | 2025-02-15 | 129
Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) |  | 22 | 22 | 2025-05-13 | 2025-06-10 | 2025-02-19 | 2025-03-21 | 104
C-52-0405-CMA02-0970 | Excavation (Manual-Trial Pit) | 8 | 8 | 2025-05-13 | 2025-05-22 | 2025-02-19 | 2025-02-28 | 77
C-52-0405-CMA02-0980 | Sabkha Gatch Laying | 5 | 5 | 2025-05-22 | 2025-05-28 | 2025-02-28 | 2025-03-07 | 77
C-52-0405-CMA02-0990 | Sabka Gatch Compaction | 5 | 5 | 2025-05-23 | 2025-05-29 | 2025-03-01 | 2025-03-08 | 77
C-52-0405-CMA02-1000 | Trench Excavation | 2 | 2 | 2025-05-29 | 2025-05-31 | 2025-03-08 | 2025-03-12 | 77
C-52-0405-CMA02-1010 | Bedding | 1 | 1 | 2025-05-30 | 2025-05-31 | 2025-03-10 | 2025-03-12 | 77
C-52-0405-CMA02-1020 | Lowering | 1 | 1 | 2025-05-31 | 2025-06-02 | 2025-03-12 | 2025-03-13 | 77
C-52-0405-CMA02-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-31 | 2025-06-03 | 2025-03-12 | 2025-03-15 | 77
C-52-0405-CMA02-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-06-02 | 2025-06-04 | 2025-03-13 | 2025-03-16 | 104
C-52-0405-CMA02-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-06-03 | 2025-06-07 | 2025-03-15 | 2025-03-18 | 104
C-52-0405-CMA02-1060 | Holiday Testing | 1 | 1 | 2025-06-07 | 2025-06-09 | 2025-03-18 | 2025-03-19 | 104
C-52-0405-CMA02-1070 | Padding | 1 | 1 | 2025-06-09 | 2025-06-10 | 2025-03-19 | 2025-03-21 | 104
Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) |  | 26 | 26 | 2025-04-15 | 2025-05-16 | 2025-02-01 | 2025-03-04 | 115
C-52-0405-CMA03-0970 | Excavation (Manual-Trial Pit) | 12 | 12 | 2025-04-15 | 2025-04-29 | 2025-02-01 | 2025-02-15 | 83
C-52-0405-CMA03-0980 | Sabkha Gatch Laying | 5 | 5 | 2025-04-29 | 2025-05-05 | 2025-02-15 | 2025-02-21 | 88
C-52-0405-CMA03-0990 | Sabka Gatch Compaction | 5 | 5 | 2025-04-30 | 2025-05-07 | 2025-02-17 | 2025-02-22 | 88
C-52-0405-CMA03-1000 | Trench Excavation | 2 | 2 | 2025-05-07 | 2025-05-09 | 2025-02-22 | 2025-02-25 | 88
C-52-0405-CMA03-1010 | Bedding | 1 | 1 | 2025-05-08 | 2025-05-09 | 2025-02-24 | 2025-02-25 | 88
C-52-0405-CMA03-1020 | Lowering | 1 | 1 | 2025-05-09 | 2025-05-10 | 2025-02-25 | 2025-02-26 | 88
C-52-0405-CMA03-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-09 | 2025-05-12 | 2025-02-25 | 2025-02-27 | 88
C-52-0405-CMA03-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-10 | 2025-05-13 | 2025-02-26 | 2025-02-28 | 115
C-52-0405-CMA03-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-12 | 2025-05-14 | 2025-02-27 | 2025-03-01 | 115
C-52-0405-CMA03-1060 | Holiday Testing | 1 | 1 | 2025-05-14 | 2025-05-15 | 2025-03-01 | 2025-03-02 | 115
C-52-0405-CMA03-1070 | Padding | 1 | 1 | 2025-05-15 | 2025-05-16 | 2025-03-02 | 2025-03-04 | 115
Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) |  | 14 | 14 | 2025-05-12 | 2025-05-28 | 2025-02-27 | 2025-03-19 | 105
C-52-0405-CMA04-1000 | Trench Excavation | 8 | 8 | 2025-05-12 | 2025-05-21 | 2025-02-27 | 2025-03-10 | 70
C-52-0405-CMA04-1010 | Bedding | 1 | 1 | 2025-05-20 | 2025-05-21 | 2025-03-08 | 2025-03-10 | 78
C-52-0405-CMA04-1020 | Lowering | 1 | 1 | 2025-05-21 | 2025-05-22 | 2025-03-10 | 2025-03-12 | 78
C-52-0405-CMA04-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-21 | 2025-05-23 | 2025-03-10 | 2025-03-13 | 78
C-52-0405-CMA04-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-22 | 2025-05-24 | 2025-03-12 | 2025-03-15 | 105
C-52-0405-CMA04-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-23 | 2025-05-26 | 2025-03-13 | 2025-03-16 | 105
C-52-0405-CMA04-1060 | Holiday Testing | 1 | 1 | 2025-05-26 | 2025-05-27 | 2025-03-16 | 2025-03-18 | 105
C-52-0405-CMA04-1070 | Padding | 1 | 1 | 2025-05-27 | 2025-05-28 | 2025-03-18 | 2025-03-19 | 105
Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) |  | 12 | 12 | 2025-01-18 | 2025-02-04 | 2025-01-10 | 2025-01-24 | 148
C-52-0405-CMA05-1000 | Trench Excavation | 6 | 6 | 2025-01-18 | 2025-01-28 | 2025-01-10 | 2025-01-17 | 79
C-52-0405-CMA05-1010 | Bedding | 1 | 1 | 2025-01-27 | 2025-01-28 | 2025-01-16 | 2025-01-17 | 121
C-52-0405-CMA05-1020 | Lowering | 1 | 1 | 2025-01-28 | 2025-01-29 | 2025-01-17 | 2025-01-18 | 121
C-52-0405-CMA05-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-28 | 2025-01-30 | 2025-01-17 | 2025-01-20 | 121
C-52-0405-CMA05-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-29 | 2025-01-31 | 2025-01-18 | 2025-01-21 | 148
C-52-0405-CMA05-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-30 | 2025-02-01 | 2025-01-20 | 2025-01-22 | 148
C-52-0405-CMA05-1060 | Holiday Testing | 1 | 1 | 2025-02-01 | 2025-02-03 | 2025-01-22 | 2025-01-23 | 148
C-52-0405-CMA05-1070 | Padding | 1 | 1 | 2025-02-03 | 2025-02-04 | 2025-01-23 | 2025-01-24 | 148
Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) |  | 14 | 14 | 2025-05-21 | 2025-06-09 | 2025-03-10 | 2025-04-04 | 97
C-52-0405-CMA06-1000 | Trench Excavation | 8 | 8 | 2025-05-21 | 2025-05-30 | 2025-03-10 | 2025-03-22 | 70
C-52-0405-CMA06-1010 | Bedding | 1 | 1 | 2025-05-29 | 2025-05-30 | 2025-03-21 | 2025-03-22 | 70
C-52-0405-CMA06-1020 | Lowering | 1 | 1 | 2025-05-30 | 2025-05-31 | 2025-03-22 | 2025-03-24 | 70
C-52-0405-CMA06-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-30 | 2025-06-02 | 2025-03-22 | 2025-03-25 | 70
C-52-0405-CMA06-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-31 | 2025-06-03 | 2025-03-24 | 2025-03-27 | 97
C-52-0405-CMA06-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-06-02 | 2025-06-04 | 2025-03-25 | 2025-03-29 | 97
C-52-0405-CMA06-1060 | Holiday Testing | 1 | 1 | 2025-06-04 | 2025-06-07 | 2025-03-29 | 2025-04-03 | 97
C-52-0405-CMA06-1070 | Padding | 1 | 1 | 2025-06-07 | 2025-06-09 | 2025-04-03 | 2025-04-04 | 97
Crossing Manual @ KP 107+585 (CX-43) |  | 12 | 12 | 2025-01-28 | 2025-02-11 | 2025-01-17 | 2025-01-31 | 142
C-52-0405-CMA07-1000 | Trench Excavation | 6 | 6 | 2025-01-28 | 2025-02-04 | 2025-01-17 | 2025-01-24 | 79
C-52-0405-CMA07-1010 | Bedding | 1 | 1 | 2025-02-03 | 2025-02-04 | 2025-01-23 | 2025-01-24 | 115
C-52-0405-CMA07-1020 | Lowering | 1 | 1 | 2025-02-04 | 2025-02-05 | 2025-01-24 | 2025-01-25 | 115
C-52-0405-CMA07-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-04 | 2025-02-06 | 2025-01-24 | 2025-01-27 | 115
C-52-0405-CMA07-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-05 | 2025-02-07 | 2025-01-25 | 2025-01-28 | 142
C-52-0405-CMA07-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-06 | 2025-02-08 | 2025-01-27 | 2025-01-29 | 142
C-52-0405-CMA07-1060 | Holiday Testing | 1 | 1 | 2025-02-08 | 2025-02-10 | 2025-01-29 | 2025-01-30 | 142
C-52-0405-CMA07-1070 | Padding | 1 | 1 | 2025-02-10 | 2025-02-11 | 2025-01-30 | 2025-01-31 | 142
Crossing Manual @ KP 107+927 (CX-43A) |  | 12 | 12 | 2025-04-11 | 2025-04-25 | 2025-01-29 | 2025-02-12 | 132
C-52-0405-CMA08-1000 | Trench Excavation | 6 | 6 | 2025-04-11 | 2025-04-18 | 2025-01-29 | 2025-02-05 | 76
C-52-0405-CMA08-1010 | Bedding | 1 | 1 | 2025-04-17 | 2025-04-18 | 2025-02-04 | 2025-02-05 | 105
C-52-0405-CMA08-1020 | Lowering | 1 | 1 | 2025-04-18 | 2025-04-19 | 2025-02-05 | 2025-02-06 | 105
C-52-0405-CMA08-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-18 | 2025-04-21 | 2025-02-05 | 2025-02-07 | 105
C-52-0405-CMA08-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-19 | 2025-04-22 | 2025-02-06 | 2025-02-08 | 132
C-52-0405-CMA08-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-21 | 2025-04-23 | 2025-02-07 | 2025-02-10 | 132
C-52-0405-CMA08-1060 | Holiday Testing | 1 | 1 | 2025-04-23 | 2025-04-24 | 2025-02-10 | 2025-02-11 | 132
C-52-0405-CMA08-1070 | Padding | 1 | 1 | 2025-04-24 | 2025-04-25 | 2025-02-11 | 2025-02-12 | 132
Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) |  | 12 | 12 | 2025-02-04 | 2025-02-20 | 2025-01-24 | 2025-02-07 | 136
C-52-0405-CMA09-1000 | Trench Excavation | 6 | 6 | 2025-02-04 | 2025-02-13 | 2025-01-24 | 2025-01-31 | 79
C-52-0405-CMA09-1010 | Bedding | 1 | 1 | 2025-02-12 | 2025-02-13 | 2025-01-30 | 2025-01-31 | 109
C-52-0405-CMA09-1020 | Lowering | 1 | 1 | 2025-02-13 | 2025-02-14 | 2025-01-31 | 2025-02-01 | 109
C-52-0405-CMA09-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-13 | 2025-02-15 | 2025-01-31 | 2025-02-03 | 109
C-52-0405-CMA09-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-14 | 2025-02-17 | 2025-02-01 | 2025-02-04 | 136
C-52-0405-CMA09-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-15 | 2025-02-18 | 2025-02-03 | 2025-02-05 | 136
C-52-0405-CMA09-1060 | Holiday Testing | 1 | 1 | 2025-02-18 | 2025-02-19 | 2025-02-05 | 2025-02-06 | 136
C-52-0405-CMA09-1070 | Padding | 1 | 1 | 2025-02-19 | 2025-02-20 | 2025-02-06 | 2025-02-07 | 136
Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) |  | 14 | 14 | 2025-04-18 | 2025-05-05 | 2025-02-05 | 2025-02-21 | 124
C-52-0405-CMA10-1000 | Trench Excavation | 8 | 8 | 2025-04-18 | 2025-04-28 | 2025-02-05 | 2025-02-14 | 76
C-52-0405-CMA10-1010 | Bedding | 1 | 1 | 2025-04-26 | 2025-04-28 | 2025-02-13 | 2025-02-14 | 97
C-52-0405-CMA10-1020 | Lowering | 1 | 1 | 2025-04-28 | 2025-04-29 | 2025-02-14 | 2025-02-15 | 97
C-52-0405-CMA10-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-28 | 2025-04-30 | 2025-02-14 | 2025-02-17 | 97
C-52-0405-CMA10-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-29 | 2025-05-01 | 2025-02-15 | 2025-02-18 | 124
C-52-0405-CMA10-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-30 | 2025-05-02 | 2025-02-17 | 2025-02-19 | 124
C-52-0405-CMA10-1060 | Holiday Testing | 1 | 1 | 2025-05-02 | 2025-05-03 | 2025-02-19 | 2025-02-20 | 124
C-52-0405-CMA10-1070 | Padding | 1 | 1 | 2025-05-03 | 2025-05-05 | 2025-02-20 | 2025-02-21 | 124
Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) |  | 12 | 12 | 2025-02-13 | 2025-03-07 | 2025-01-31 | 2025-02-14 | 130
C-52-0405-CMA11-1000 | Trench Excavation | 6 | 6 | 2025-02-13 | 2025-02-27 | 2025-01-31 | 2025-02-07 | 79
C-52-0405-CMA11-1010 | Bedding | 1 | 1 | 2025-02-26 | 2025-02-27 | 2025-02-06 | 2025-02-07 | 103
C-52-0405-CMA11-1020 | Lowering | 1 | 1 | 2025-02-27 | 2025-02-28 | 2025-02-07 | 2025-02-08 | 103
C-52-0405-CMA11-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-27 | 2025-03-01 | 2025-02-07 | 2025-02-10 | 103
C-52-0405-CMA11-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-28 | 2025-03-02 | 2025-02-08 | 2025-02-11 | 130
C-52-0405-CMA11-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-01 | 2025-03-04 | 2025-02-10 | 2025-02-12 | 130
C-52-0405-CMA11-1060 | Holiday Testing | 1 | 1 | 2025-03-04 | 2025-03-06 | 2025-02-12 | 2025-02-13 | 130
C-52-0405-CMA11-1070 | Padding | 1 | 1 | 2025-03-06 | 2025-03-07 | 2025-02-13 | 2025-02-14 | 130
Crossing Manual @ KP 109+679 (CX-45) |  | 12 | 12 | 2025-04-28 | 2025-05-13 | 2025-02-14 | 2025-02-28 | 118
C-52-0405-CMA12-1000 | Trench Excavation | 6 | 6 | 2025-04-28 | 2025-05-05 | 2025-02-14 | 2025-02-21 | 76
C-52-0405-CMA12-1010 | Bedding | 1 | 1 | 2025-05-03 | 2025-05-05 | 2025-02-20 | 2025-02-21 | 91
C-52-0405-CMA12-1020 | Lowering | 1 | 1 | 2025-05-05 | 2025-05-07 | 2025-02-21 | 2025-02-22 | 91
C-52-0405-CMA12-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-05 | 2025-05-08 | 2025-02-21 | 2025-02-24 | 91
C-52-0405-CMA12-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-07 | 2025-05-09 | 2025-02-22 | 2025-02-25 | 118
C-52-0405-CMA12-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-08 | 2025-05-10 | 2025-02-24 | 2025-02-26 | 118
C-52-0405-CMA12-1060 | Holiday Testing | 1 | 1 | 2025-05-10 | 2025-05-12 | 2025-02-26 | 2025-02-27 | 118
C-52-0405-CMA12-1070 | Padding | 1 | 1 | 2025-05-12 | 2025-05-13 | 2025-02-27 | 2025-02-28 | 118
Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) |  | 12 | 12 | 2025-02-27 | 2025-03-25 | 2025-02-07 | 2025-02-21 | 124
C-52-0405-CMA13-1000 | Trench Excavation | 6 | 6 | 2025-02-27 | 2025-03-16 | 2025-02-07 | 2025-02-14 | 79
C-52-0405-CMA13-1010 | Bedding | 1 | 1 | 2025-03-15 | 2025-03-16 | 2025-02-13 | 2025-02-14 | 97
C-52-0405-CMA13-1020 | Lowering | 1 | 1 | 2025-03-16 | 2025-03-18 | 2025-02-14 | 2025-02-15 | 97
C-52-0405-CMA13-1030 | Section Tie-in Welding | 2 | 2 | 2025-03-16 | 2025-03-19 | 2025-02-14 | 2025-02-17 | 97
C-52-0405-CMA13-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-03-18 | 2025-03-21 | 2025-02-15 | 2025-02-18 | 124
C-52-0405-CMA13-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-19 | 2025-03-22 | 2025-02-17 | 2025-02-19 | 124
C-52-0405-CMA13-1060 | Holiday Testing | 1 | 1 | 2025-03-22 | 2025-03-24 | 2025-02-19 | 2025-02-20 | 124
C-52-0405-CMA13-1070 | Padding | 1 | 1 | 2025-03-24 | 2025-03-25 | 2025-02-20 | 2025-02-21 | 124
Crossing Manual @ KP 110+339 (CX-X1) |  | 12 | 12 | 2025-04-28 | 2025-05-13 | 2025-02-14 | 2025-02-28 | 118
C-52-0405-CMA14-1000 | Trench Excavation | 6 | 6 | 2025-04-28 | 2025-05-05 | 2025-02-14 | 2025-02-21 | 76
C-52-0405-CMA14-1010 | Bedding | 1 | 1 | 2025-05-03 | 2025-05-05 | 2025-02-20 | 2025-02-21 | 91
C-52-0405-CMA14-1020 | Lowering | 1 | 1 | 2025-05-05 | 2025-05-07 | 2025-02-21 | 2025-02-22 | 91
C-52-0405-CMA14-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-05 | 2025-05-08 | 2025-02-21 | 2025-02-24 | 91
C-52-0405-CMA14-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-07 | 2025-05-09 | 2025-02-22 | 2025-02-25 | 118
C-52-0405-CMA14-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-08 | 2025-05-10 | 2025-02-24 | 2025-02-26 | 118
C-52-0405-CMA14-1060 | Holiday Testing | 1 | 1 | 2025-05-10 | 2025-05-12 | 2025-02-26 | 2025-02-27 | 118
C-52-0405-CMA14-1070 | Padding | 1 | 1 | 2025-05-12 | 2025-05-13 | 2025-02-27 | 2025-02-28 | 118
Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) |  | 12 | 12 | 2025-03-07 | 2025-03-25 | 2025-02-07 | 2025-02-21 | 124
C-52-0405-CMA15-1000 | Trench Excavation | 6 | 6 | 2025-03-07 | 2025-03-16 | 2025-02-07 | 2025-02-14 | 79
C-52-0405-CMA15-1010 | Bedding | 1 | 1 | 2025-03-15 | 2025-03-16 | 2025-02-13 | 2025-02-14 | 97
C-52-0405-CMA15-1020 | Lowering | 1 | 1 | 2025-03-16 | 2025-03-18 | 2025-02-14 | 2025-02-15 | 97
C-52-0405-CMA15-1030 | Section Tie-in Welding | 2 | 2 | 2025-03-16 | 2025-03-19 | 2025-02-14 | 2025-02-17 | 97
C-52-0405-CMA15-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-03-18 | 2025-03-21 | 2025-02-15 | 2025-02-18 | 124
C-52-0405-CMA15-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-19 | 2025-03-22 | 2025-02-17 | 2025-02-19 | 124
C-52-0405-CMA15-1060 | Holiday Testing | 1 | 1 | 2025-03-22 | 2025-03-24 | 2025-02-19 | 2025-02-20 | 124
C-52-0405-CMA15-1070 | Padding | 1 | 1 | 2025-03-24 | 2025-03-25 | 2025-02-20 | 2025-02-21 | 124
Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) |  | 12 | 12 | 2025-03-16 | 2025-04-09 | 2025-02-14 | 2025-02-28 | 118
C-52-0405-CMA16-1000 | Trench Excavation | 6 | 6 | 2025-03-16 | 2025-03-29 | 2025-02-14 | 2025-02-21 | 79
C-52-0405-CMA16-1010 | Bedding | 1 | 1 | 2025-03-27 | 2025-03-29 | 2025-02-20 | 2025-02-21 | 91
C-52-0405-CMA16-1020 | Lowering | 1 | 1 | 2025-03-29 | 2025-04-03 | 2025-02-21 | 2025-02-22 | 91
C-52-0405-CMA16-1030 | Section Tie-in Welding | 2 | 2 | 2025-03-29 | 2025-04-04 | 2025-02-21 | 2025-02-24 | 91
C-52-0405-CMA16-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-03 | 2025-04-05 | 2025-02-22 | 2025-02-25 | 118
C-52-0405-CMA16-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-04 | 2025-04-07 | 2025-02-24 | 2025-02-26 | 118
C-52-0405-CMA16-1060 | Holiday Testing | 1 | 1 | 2025-04-07 | 2025-04-08 | 2025-02-26 | 2025-02-27 | 118
C-52-0405-CMA16-1070 | Padding | 1 | 1 | 2025-04-08 | 2025-04-09 | 2025-02-27 | 2025-02-28 | 118
Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) |  | 12 | 12 | 2025-05-09 | 2025-05-23 | 2025-02-25 | 2025-03-13 | 109
C-52-0405-CMA17-1000 | Trench Excavation | 6 | 6 | 2025-05-09 | 2025-05-16 | 2025-02-25 | 2025-03-04 | 76
C-52-0405-CMA17-1010 | Bedding | 1 | 1 | 2025-05-15 | 2025-05-16 | 2025-03-02 | 2025-03-04 | 82
C-52-0405-CMA17-1020 | Lowering | 1 | 1 | 2025-05-16 | 2025-05-17 | 2025-03-04 | 2025-03-06 | 82
C-52-0405-CMA17-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-16 | 2025-05-19 | 2025-03-04 | 2025-03-07 | 82
C-52-0405-CMA17-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-17 | 2025-05-20 | 2025-03-06 | 2025-03-08 | 109
C-52-0405-CMA17-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-19 | 2025-05-21 | 2025-03-07 | 2025-03-10 | 109
C-52-0405-CMA17-1060 | Holiday Testing | 1 | 1 | 2025-05-21 | 2025-05-22 | 2025-03-10 | 2025-03-12 | 109
C-52-0405-CMA17-1070 | Padding | 1 | 1 | 2025-05-22 | 2025-05-23 | 2025-03-12 | 2025-03-13 | 109
Crossing Manual @ KP 111+445 (CX-X1) |  | 12 | 12 | 2025-03-29 | 2025-04-16 | 2025-02-21 | 2025-03-08 | 112
C-52-0405-CMA18-1000 | Trench Excavation | 6 | 6 | 2025-03-29 | 2025-04-09 | 2025-02-21 | 2025-02-28 | 79
C-52-0405-CMA18-1010 | Bedding | 1 | 1 | 2025-04-08 | 2025-04-09 | 2025-02-27 | 2025-02-28 | 85
C-52-0405-CMA18-1020 | Lowering | 1 | 1 | 2025-04-09 | 2025-04-10 | 2025-02-28 | 2025-03-01 | 85
C-52-0405-CMA18-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-09 | 2025-04-11 | 2025-02-28 | 2025-03-02 | 85
C-52-0405-CMA18-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-10 | 2025-04-12 | 2025-03-01 | 2025-03-04 | 112
C-52-0405-CMA18-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-11 | 2025-04-14 | 2025-03-02 | 2025-03-06 | 112
C-52-0405-CMA18-1060 | Holiday Testing | 1 | 1 | 2025-04-14 | 2025-04-15 | 2025-03-06 | 2025-03-07 | 112
C-52-0405-CMA18-1070 | Padding | 1 | 1 | 2025-04-15 | 2025-04-16 | 2025-03-07 | 2025-03-08 | 112
Crossing Manual @ KP 111+489 (CX-X1) |  | 12 | 12 | 2025-05-16 | 2025-05-30 | 2025-03-04 | 2025-03-22 | 103
C-52-0405-CMA19-1000 | Trench Excavation | 6 | 6 | 2025-05-16 | 2025-05-23 | 2025-03-04 | 2025-03-13 | 76
C-52-0405-CMA19-1010 | Bedding | 1 | 1 | 2025-05-22 | 2025-05-23 | 2025-03-12 | 2025-03-13 | 76
C-52-0405-CMA19-1020 | Lowering | 1 | 1 | 2025-05-23 | 2025-05-24 | 2025-03-13 | 2025-03-15 | 76
C-52-0405-CMA19-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-23 | 2025-05-26 | 2025-03-13 | 2025-03-16 | 76
C-52-0405-CMA19-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-24 | 2025-05-27 | 2025-03-15 | 2025-03-18 | 103
C-52-0405-CMA19-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-26 | 2025-05-28 | 2025-03-16 | 2025-03-19 | 103
C-52-0405-CMA19-1060 | Holiday Testing | 1 | 1 | 2025-05-28 | 2025-05-29 | 2025-03-19 | 2025-03-21 | 103
C-52-0405-CMA19-1070 | Padding | 1 | 1 | 2025-05-29 | 2025-05-30 | 2025-03-21 | 2025-03-22 | 103
Crossings OHPLCCOPL52436 |  | 24 | 24 | 2025-04-28 | 2025-05-27 | 2025-02-05 | 2025-03-06 | 114
Crossing Manual @ KP 100+684 (OX-08) |  | 12 | 12 | 2025-04-28 | 2025-05-13 | 2025-02-05 | 2025-02-19 | 126
C-52-0405-CMA20-1000 | Trench Excavation | 6 | 6 | 2025-04-28 | 2025-05-05 | 2025-02-05 | 2025-02-12 | 77
C-52-0405-CMA20-1010 | Bedding | 1 | 1 | 2025-05-03 | 2025-05-05 | 2025-02-11 | 2025-02-12 | 99
C-52-0405-CMA20-1020 | Lowering | 1 | 1 | 2025-05-05 | 2025-05-07 | 2025-02-12 | 2025-02-13 | 99
C-52-0405-CMA20-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-05 | 2025-05-08 | 2025-02-12 | 2025-02-14 | 99
C-52-0405-CMA20-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-07 | 2025-05-09 | 2025-02-13 | 2025-02-15 | 126
C-52-0405-CMA20-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-08 | 2025-05-10 | 2025-02-14 | 2025-02-17 | 126
C-52-0405-CMA20-1060 | Holiday Testing | 1 | 1 | 2025-05-10 | 2025-05-12 | 2025-02-17 | 2025-02-18 | 126
C-52-0405-CMA20-1070 | Padding | 1 | 1 | 2025-05-12 | 2025-05-13 | 2025-02-18 | 2025-02-19 | 126
Crossing Manual @ KP 100+858 (OX-09) |  | 12 | 12 | 2025-05-13 | 2025-05-27 | 2025-02-19 | 2025-03-06 | 114
C-52-0405-CMA21-1000 | Trench Excavation | 6 | 6 | 2025-05-13 | 2025-05-20 | 2025-02-19 | 2025-02-26 | 77
C-52-0405-CMA21-1010 | Bedding | 1 | 1 | 2025-05-19 | 2025-05-20 | 2025-02-25 | 2025-02-26 | 87
C-52-0405-CMA21-1020 | Lowering | 1 | 1 | 2025-05-20 | 2025-05-21 | 2025-02-26 | 2025-02-27 | 87
C-52-0405-CMA21-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-20 | 2025-05-22 | 2025-02-26 | 2025-02-28 | 87
C-52-0405-CMA21-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-21 | 2025-05-23 | 2025-02-27 | 2025-03-01 | 114
C-52-0405-CMA21-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-22 | 2025-05-24 | 2025-02-28 | 2025-03-02 | 114
C-52-0405-CMA21-1060 | Holiday Testing | 1 | 1 | 2025-05-24 | 2025-05-26 | 2025-03-02 | 2025-03-04 | 114
C-52-0405-CMA21-1070 | Padding | 1 | 1 | 2025-05-26 | 2025-05-27 | 2025-03-04 | 2025-03-06 | 114
Crossings - UG PipeCCOPL52415 |  | 41 | 41 | 2025-04-18 | 2025-05-28 | 2025-02-13 | 2025-04-12 | 90
Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) |  | 24 | 24 | 2025-04-18 | 2025-05-17 | 2025-03-06 | 2025-04-12 | 90
C-52-0405-CMA22-1000 | Excavation (Manual-Trial Pit) | 10 | 10 | 2025-04-18 | 2025-04-30 | 2025-03-06 | 2025-03-21 | 63
C-52-0405-CMA22-1010 | Sabkha Gatch Laying | 5 | 5 | 2025-04-30 | 2025-05-07 | 2025-03-21 | 2025-03-29 | 63
C-52-0405-CMA22-1020 | Sabka Gatch Compaction | 5 | 5 | 2025-05-01 | 2025-05-08 | 2025-03-22 | 2025-04-03 | 63
C-52-0405-CMA22-1030 | Trench Excavation | 2 | 2 | 2025-05-08 | 2025-05-10 | 2025-04-03 | 2025-04-05 | 63
C-52-0405-CMA22-1040 | Bedding | 1 | 1 | 2025-05-09 | 2025-05-10 | 2025-04-04 | 2025-04-05 | 63
C-52-0405-CMA22-1050 | Lowering | 1 | 1 | 2025-05-10 | 2025-05-12 | 2025-04-05 | 2025-04-07 | 63
C-52-0405-CMA22-1060 | Section Tie-in Welding | 2 | 2 | 2025-05-10 | 2025-05-13 | 2025-04-05 | 2025-04-08 | 63
C-52-0405-CMA22-1070 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-12 | 2025-05-14 | 2025-04-07 | 2025-04-09 | 90
C-52-0405-CMA22-1080 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-13 | 2025-05-15 | 2025-04-08 | 2025-04-10 | 90
C-52-0405-CMA22-1090 | Holiday Testing | 1 | 1 | 2025-05-15 | 2025-05-16 | 2025-04-10 | 2025-04-11 | 90
C-52-0405-CMA22-1100 | Padding | 1 | 1 | 2025-05-16 | 2025-05-17 | 2025-04-11 | 2025-04-12 | 90
Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) |  | 26 | 26 | 2025-04-26 | 2025-05-28 | 2025-02-13 | 2025-03-19 | 105
C-52-0405-CMA23-1000 | Excavation (Manual-Trial Pit) | 12 | 12 | 2025-04-26 | 2025-05-12 | 2025-02-13 | 2025-02-27 | 70
C-52-0405-CMA23-1010 | Sabkha Gatch Laying | 5 | 5 | 2025-05-12 | 2025-05-17 | 2025-02-27 | 2025-03-06 | 78
C-52-0405-CMA23-1020 | Sabka Gatch Compaction | 5 | 5 | 2025-05-13 | 2025-05-19 | 2025-02-28 | 2025-03-07 | 78
C-52-0405-CMA23-1030 | Trench Excavation | 2 | 2 | 2025-05-19 | 2025-05-21 | 2025-03-07 | 2025-03-10 | 78
C-52-0405-CMA23-1040 | Bedding | 1 | 1 | 2025-05-20 | 2025-05-21 | 2025-03-08 | 2025-03-10 | 78
C-52-0405-CMA23-1050 | Lowering | 1 | 1 | 2025-05-21 | 2025-05-22 | 2025-03-10 | 2025-03-12 | 78
C-52-0405-CMA23-1060 | Section Tie-in Welding | 2 | 2 | 2025-05-21 | 2025-05-23 | 2025-03-10 | 2025-03-13 | 78
C-52-0405-CMA23-1070 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-22 | 2025-05-24 | 2025-03-12 | 2025-03-15 | 105
C-52-0405-CMA23-1080 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-23 | 2025-05-26 | 2025-03-13 | 2025-03-16 | 105
C-52-0405-CMA23-1090 | Holiday Testing | 1 | 1 | 2025-05-26 | 2025-05-27 | 2025-03-16 | 2025-03-18 | 105
C-52-0405-CMA23-1100 | Padding | 1 | 1 | 2025-05-27 | 2025-05-28 | 2025-03-18 | 2025-03-19 | 105
Crossing Manual @ KP 110+988 (PX-35) |  | 15 | 15 | 2025-04-28 | 2025-05-16 | 2025-02-14 | 2025-03-04 | 115
C-52-0405-CMA24-1000 | Trench Excavation | 9 | 9 | 2025-04-28 | 2025-05-09 | 2025-02-14 | 2025-02-25 | 76
C-52-0405-CMA24-1010 | Bedding | 1 | 1 | 2025-05-08 | 2025-05-09 | 2025-02-24 | 2025-02-25 | 88
C-52-0405-CMA24-1020 | Lowering | 1 | 1 | 2025-05-09 | 2025-05-10 | 2025-02-25 | 2025-02-26 | 88
C-52-0405-CMA24-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-09 | 2025-05-12 | 2025-02-25 | 2025-02-27 | 88
C-52-0405-CMA24-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-10 | 2025-05-13 | 2025-02-26 | 2025-02-28 | 115
C-52-0405-CMA24-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-12 | 2025-05-14 | 2025-02-27 | 2025-03-01 | 115
C-52-0405-CMA24-1060 | Holiday Testing | 1 | 1 | 2025-05-14 | 2025-05-15 | 2025-03-01 | 2025-03-02 | 115
C-52-0405-CMA24-1070 | Padding | 1 | 1 | 2025-05-15 | 2025-05-16 | 2025-03-02 | 2025-03-04 | 115
Crossings - FenceCCOPL52416 |  | 60 | 60 | 2025-01-11 | 2025-05-22 | 2025-01-03 | 2025-03-18 | 106
Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) |  | 12 | 12 | 2025-04-21 | 2025-05-05 | 2025-01-29 | 2025-02-12 | 132
C-52-0405-CMA25-1000 | Trench Excavation | 6 | 6 | 2025-04-21 | 2025-04-28 | 2025-01-29 | 2025-02-05 | 77
C-52-0405-CMA25-1010 | Bedding | 1 | 1 | 2025-04-26 | 2025-04-28 | 2025-02-04 | 2025-02-05 | 105
C-52-0405-CMA25-1020 | Lowering | 1 | 1 | 2025-04-28 | 2025-04-29 | 2025-02-05 | 2025-02-06 | 105
C-52-0405-CMA25-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-28 | 2025-04-30 | 2025-02-05 | 2025-02-07 | 105
C-52-0405-CMA25-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-29 | 2025-05-01 | 2025-02-06 | 2025-02-08 | 132
C-52-0405-CMA25-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-30 | 2025-05-02 | 2025-02-07 | 2025-02-10 | 132
C-52-0405-CMA25-1060 | Holiday Testing | 1 | 1 | 2025-05-02 | 2025-05-03 | 2025-02-10 | 2025-02-11 | 132
C-52-0405-CMA25-1070 | Padding | 1 | 1 | 2025-05-03 | 2025-05-05 | 2025-02-11 | 2025-02-12 | 132
Crossing Manual @ KP 100+796 (FX-21) |  | 12 | 12 | 2025-05-05 | 2025-05-20 | 2025-02-12 | 2025-02-26 | 120
C-52-0405-CMA26-1000 | Trench Excavation | 6 | 6 | 2025-05-05 | 2025-05-13 | 2025-02-12 | 2025-02-19 | 77
C-52-0405-CMA26-1010 | Bedding | 1 | 1 | 2025-05-12 | 2025-05-13 | 2025-02-18 | 2025-02-19 | 93
C-52-0405-CMA26-1020 | Lowering | 1 | 1 | 2025-05-13 | 2025-05-14 | 2025-02-19 | 2025-02-20 | 93
C-52-0405-CMA26-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-13 | 2025-05-15 | 2025-02-19 | 2025-02-21 | 93
C-52-0405-CMA26-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-14 | 2025-05-16 | 2025-02-20 | 2025-02-22 | 120
C-52-0405-CMA26-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-15 | 2025-05-17 | 2025-02-21 | 2025-02-24 | 120
C-52-0405-CMA26-1060 | Holiday Testing | 1 | 1 | 2025-05-17 | 2025-05-19 | 2025-02-24 | 2025-02-25 | 120
C-52-0405-CMA26-1070 | Padding | 1 | 1 | 2025-05-19 | 2025-05-20 | 2025-02-25 | 2025-02-26 | 120
Crossing Manual @ KP 100+906 (FX-22) |  | 12 | 12 | 2025-04-11 | 2025-04-25 | 2025-01-29 | 2025-02-12 | 132
C-52-0405-CMA27-1000 | Trench Excavation | 6 | 6 | 2025-04-11 | 2025-04-18 | 2025-01-29 | 2025-02-05 | 97
C-52-0405-CMA27-1010 | Bedding | 1 | 1 | 2025-04-17 | 2025-04-18 | 2025-02-04 | 2025-02-05 | 105
C-52-0405-CMA27-1020 | Lowering | 1 | 1 | 2025-04-18 | 2025-04-19 | 2025-02-05 | 2025-02-06 | 105
C-52-0405-CMA27-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-18 | 2025-04-21 | 2025-02-05 | 2025-02-07 | 105
C-52-0405-CMA27-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-19 | 2025-04-22 | 2025-02-06 | 2025-02-08 | 132
C-52-0405-CMA27-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-21 | 2025-04-23 | 2025-02-07 | 2025-02-10 | 132
C-52-0405-CMA27-1060 | Holiday Testing | 1 | 1 | 2025-04-23 | 2025-04-24 | 2025-02-10 | 2025-02-11 | 132
C-52-0405-CMA27-1070 | Padding | 1 | 1 | 2025-04-24 | 2025-04-25 | 2025-02-11 | 2025-02-12 | 132
Crossing Manual @ KP 104+230 (FX-30) |  | 14 | 14 | 2025-04-29 | 2025-05-16 | 2025-02-15 | 2025-03-04 | 115
C-52-0405-CMA28-0980 | Sabkha Gatch Laying | 5 | 5 | 2025-04-29 | 2025-05-05 | 2025-02-15 | 2025-02-21 | 83
C-52-0405-CMA28-0990 | Sabka Gatch Compaction | 5 | 5 | 2025-04-30 | 2025-05-07 | 2025-02-17 | 2025-02-22 | 88
C-52-0405-CMA28-1000 | Trench Excavation | 2 | 2 | 2025-05-07 | 2025-05-09 | 2025-02-22 | 2025-02-25 | 88
C-52-0405-CMA28-1010 | Bedding | 1 | 1 | 2025-05-08 | 2025-05-09 | 2025-02-24 | 2025-02-25 | 88
C-52-0405-CMA28-1020 | Lowering | 1 | 1 | 2025-05-09 | 2025-05-10 | 2025-02-25 | 2025-02-26 | 88
C-52-0405-CMA28-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-09 | 2025-05-12 | 2025-02-25 | 2025-02-27 | 88
C-52-0405-CMA28-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-10 | 2025-05-13 | 2025-02-26 | 2025-02-28 | 115
C-52-0405-CMA28-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-12 | 2025-05-14 | 2025-02-27 | 2025-03-01 | 115
C-52-0405-CMA28-1060 | Holiday Testing | 1 | 1 | 2025-05-14 | 2025-05-15 | 2025-03-01 | 2025-03-02 | 115
C-52-0405-CMA28-1070 | Padding | 1 | 1 | 2025-05-15 | 2025-05-16 | 2025-03-02 | 2025-03-04 | 115
Crossing Manual @ KP 104+371 (FX-31) |  | 14 | 14 | 2025-05-05 | 2025-05-22 | 2025-02-21 | 2025-03-12 | 110
C-52-0405-CMA29-0980 | Sabkha Gatch Laying | 5 | 5 | 2025-05-05 | 2025-05-12 | 2025-02-21 | 2025-02-27 | 83
C-52-0405-CMA29-0990 | Sabka Gatch Compaction | 5 | 5 | 2025-05-07 | 2025-05-13 | 2025-02-22 | 2025-02-28 | 83
C-52-0405-CMA29-1000 | Trench Excavation | 2 | 2 | 2025-05-13 | 2025-05-15 | 2025-02-28 | 2025-03-02 | 83
C-52-0405-CMA29-1010 | Bedding | 1 | 1 | 2025-05-14 | 2025-05-15 | 2025-03-01 | 2025-03-02 | 83
C-52-0405-CMA29-1020 | Lowering | 1 | 1 | 2025-05-15 | 2025-05-16 | 2025-03-02 | 2025-03-04 | 83
C-52-0405-CMA29-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-15 | 2025-05-17 | 2025-03-02 | 2025-03-06 | 83
C-52-0405-CMA29-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-16 | 2025-05-19 | 2025-03-04 | 2025-03-07 | 110
C-52-0405-CMA29-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-17 | 2025-05-20 | 2025-03-06 | 2025-03-08 | 110
C-52-0405-CMA29-1060 | Holiday Testing | 1 | 1 | 2025-05-20 | 2025-05-21 | 2025-03-08 | 2025-03-10 | 110
C-52-0405-CMA29-1070 | Padding | 1 | 1 | 2025-05-21 | 2025-05-22 | 2025-03-10 | 2025-03-12 | 110
Crossing Manual @ KP 104+570 (FX-32) |  | 14 | 14 | 2025-04-18 | 2025-05-05 | 2025-02-05 | 2025-02-21 | 124
C-52-0405-CMA30-0980 | Sabkha Gatch Laying | 5 | 5 | 2025-04-18 | 2025-04-24 | 2025-02-05 | 2025-02-11 | 97
C-52-0405-CMA30-0990 | Sabka Gatch Compaction | 5 | 5 | 2025-04-19 | 2025-04-25 | 2025-02-06 | 2025-02-12 | 97
C-52-0405-CMA30-1000 | Trench Excavation | 2 | 2 | 2025-04-25 | 2025-04-28 | 2025-02-12 | 2025-02-14 | 97
C-52-0405-CMA30-1010 | Bedding | 1 | 1 | 2025-04-26 | 2025-04-28 | 2025-02-13 | 2025-02-14 | 97
C-52-0405-CMA30-1020 | Lowering | 1 | 1 | 2025-04-28 | 2025-04-29 | 2025-02-14 | 2025-02-15 | 97
C-52-0405-CMA30-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-28 | 2025-04-30 | 2025-02-14 | 2025-02-17 | 97
C-52-0405-CMA30-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-29 | 2025-05-01 | 2025-02-15 | 2025-02-18 | 124
C-52-0405-CMA30-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-30 | 2025-05-02 | 2025-02-17 | 2025-02-19 | 124
C-52-0405-CMA30-1060 | Holiday Testing | 1 | 1 | 2025-05-02 | 2025-05-03 | 2025-02-19 | 2025-02-20 | 124
C-52-0405-CMA30-1070 | Padding | 1 | 1 | 2025-05-03 | 2025-05-05 | 2025-02-20 | 2025-02-21 | 124
Crossing Manual @ KP 107+081 (FX-37) |  | 12 | 12 | 2025-01-11 | 2025-01-25 | 2025-01-03 | 2025-01-17 | 154
C-52-0405-CMA31-1000 | Trench Excavation | 6 | 6 | 2025-01-11 | 2025-01-18 | 2025-01-03 | 2025-01-10 | 79
C-52-0405-CMA31-1010 | Bedding | 1 | 1 | 2025-01-17 | 2025-01-18 | 2025-01-09 | 2025-01-10 | 127
C-52-0405-CMA31-1020 | Lowering | 1 | 1 | 2025-01-18 | 2025-01-20 | 2025-01-10 | 2025-01-11 | 127
C-52-0405-CMA31-1030 | Section Tie-in Welding | 2 | 2 | 2025-01-18 | 2025-01-21 | 2025-01-10 | 2025-01-13 | 127
C-52-0405-CMA31-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-01-20 | 2025-01-22 | 2025-01-11 | 2025-01-14 | 154
C-52-0405-CMA31-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-01-21 | 2025-01-23 | 2025-01-13 | 2025-01-15 | 154
C-52-0405-CMA31-1060 | Holiday Testing | 1 | 1 | 2025-01-23 | 2025-01-24 | 2025-01-15 | 2025-01-16 | 154
C-52-0405-CMA31-1070 | Padding | 1 | 1 | 2025-01-24 | 2025-01-25 | 2025-01-16 | 2025-01-17 | 154
Crossing Manual @ KP 111+732 (FX-38) |  | 12 | 12 | 2025-04-09 | 2025-04-23 | 2025-02-28 | 2025-03-18 | 106
C-52-0405-CMA32-1000 | Trench Excavation | 6 | 6 | 2025-04-09 | 2025-04-16 | 2025-02-28 | 2025-03-08 | 79
C-52-0405-CMA32-1010 | Bedding | 1 | 1 | 2025-04-15 | 2025-04-16 | 2025-03-07 | 2025-03-08 | 79
C-52-0405-CMA32-1020 | Lowering | 1 | 1 | 2025-04-16 | 2025-04-17 | 2025-03-08 | 2025-03-10 | 79
C-52-0405-CMA32-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-16 | 2025-04-18 | 2025-03-08 | 2025-03-12 | 79
C-52-0405-CMA32-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-17 | 2025-04-19 | 2025-03-10 | 2025-03-13 | 106
C-52-0405-CMA32-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-18 | 2025-04-21 | 2025-03-12 | 2025-03-15 | 106
C-52-0405-CMA32-1060 | Holiday Testing | 1 | 1 | 2025-04-21 | 2025-04-22 | 2025-03-15 | 2025-03-16 | 106
C-52-0405-CMA32-1070 | Padding | 1 | 1 | 2025-04-22 | 2025-04-23 | 2025-03-16 | 2025-03-18 | 106
Open Cut - Rig / Track RoadCCOPL52417 |  | 39 | 39 | 2024-12-21 | 2025-02-07 | 2024-12-14 | 2025-01-30 | 143
Crossing Mechanical (TX-43) |  | 19 | 19 | 2024-12-21 | 2025-01-14 | 2024-12-14 | 2025-01-07 | 163
C-52-0405-CME01-1000 | Trench Excavation | 2 | 2 | 2024-12-21 | 2024-12-24 | 2024-12-14 | 2024-12-17 | 63
C-52-0405-CME01-1010 | Bedding | 2 | 2 | 2024-12-24 | 2024-12-26 | 2024-12-17 | 2024-12-19 | 142
C-52-0405-CME01-1020 | Lowering | 2 | 2 | 2024-12-26 | 2024-12-28 | 2024-12-19 | 2024-12-21 | 142
C-52-0405-CME01-1030 | Section Tie-in Welding | 3 | 3 | 2024-12-28 | 2025-01-02 | 2024-12-21 | 2024-12-25 | 142
C-52-0405-CME01-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-02 | 2025-01-06 | 2024-12-25 | 2024-12-28 | 163
C-52-0405-CME01-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-01-06 | 2025-01-09 | 2024-12-28 | 2025-01-02 | 163
C-52-0405-CME01-1060 | Holiday Testing | 2 | 2 | 2025-01-09 | 2025-01-11 | 2025-01-02 | 2025-01-04 | 163
C-52-0405-CME01-1070 | Padding & Back Filling | 2 | 2 | 2025-01-11 | 2025-01-14 | 2025-01-04 | 2025-01-07 | 163
Crossing Mechanical (TX-46) |  | 19 | 19 | 2024-12-25 | 2025-01-17 | 2024-12-18 | 2025-01-10 | 160
C-52-0405-CME02-1000 | Trench Excavation | 2 | 2 | 2024-12-25 | 2024-12-27 | 2024-12-18 | 2024-12-20 | 63
C-52-0405-CME02-1010 | Bedding | 2 | 2 | 2024-12-27 | 2024-12-30 | 2024-12-20 | 2024-12-23 | 139
C-52-0405-CME02-1020 | Lowering | 2 | 2 | 2024-12-30 | 2025-01-02 | 2024-12-23 | 2024-12-25 | 139
C-52-0405-CME02-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-02 | 2025-01-06 | 2024-12-25 | 2024-12-28 | 139
C-52-0405-CME02-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-06 | 2025-01-09 | 2024-12-28 | 2025-01-02 | 160
C-52-0405-CME02-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-01-09 | 2025-01-13 | 2025-01-02 | 2025-01-06 | 160
C-52-0405-CME02-1060 | Holiday Testing | 2 | 2 | 2025-01-13 | 2025-01-15 | 2025-01-06 | 2025-01-08 | 160
C-52-0405-CME02-1070 | Padding & Back Filling | 2 | 2 | 2025-01-15 | 2025-01-17 | 2025-01-08 | 2025-01-10 | 160
Crossing Mechanical (TX-47) |  | 19 | 19 | 2024-12-28 | 2025-01-21 | 2024-12-21 | 2025-01-14 | 157
C-52-0405-CME03-1000 | Trench Excavation | 2 | 2 | 2024-12-28 | 2024-12-31 | 2024-12-21 | 2024-12-24 | 63
C-52-0405-CME03-1010 | Bedding | 2 | 2 | 2024-12-31 | 2025-01-03 | 2024-12-24 | 2024-12-26 | 136
C-52-0405-CME03-1020 | Lowering | 2 | 2 | 2025-01-03 | 2025-01-06 | 2024-12-26 | 2024-12-28 | 136
C-52-0405-CME03-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-06 | 2025-01-09 | 2024-12-28 | 2025-01-02 | 136
C-52-0405-CME03-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-09 | 2025-01-13 | 2025-01-02 | 2025-01-06 | 157
C-52-0405-CME03-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-01-13 | 2025-01-16 | 2025-01-06 | 2025-01-09 | 157
C-52-0405-CME03-1060 | Holiday Testing | 2 | 2 | 2025-01-16 | 2025-01-18 | 2025-01-09 | 2025-01-11 | 157
C-52-0405-CME03-1070 | Padding & Back Filling | 2 | 2 | 2025-01-18 | 2025-01-21 | 2025-01-11 | 2025-01-14 | 157
Crossing Mechanical (TX-48) |  | 19 | 19 | 2025-01-02 | 2025-01-24 | 2024-12-25 | 2025-01-17 | 154
C-52-0405-CME04-1000 | Trench Excavation | 2 | 2 | 2025-01-02 | 2025-01-04 | 2024-12-25 | 2024-12-27 | 63
C-52-0405-CME04-1010 | Bedding | 2 | 2 | 2025-01-04 | 2025-01-07 | 2024-12-27 | 2024-12-30 | 133
C-52-0405-CME04-1020 | Lowering | 2 | 2 | 2025-01-07 | 2025-01-09 | 2024-12-30 | 2025-01-02 | 133
C-52-0405-CME04-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-09 | 2025-01-13 | 2025-01-02 | 2025-01-06 | 133
C-52-0405-CME04-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-13 | 2025-01-16 | 2025-01-06 | 2025-01-09 | 154
C-52-0405-CME04-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-01-16 | 2025-01-20 | 2025-01-09 | 2025-01-13 | 154
C-52-0405-CME04-1060 | Holiday Testing | 2 | 2 | 2025-01-20 | 2025-01-22 | 2025-01-13 | 2025-01-15 | 154
C-52-0405-CME04-1070 | Padding & Back Filling | 2 | 2 | 2025-01-22 | 2025-01-24 | 2025-01-15 | 2025-01-17 | 154
Crossing Mechanical (TX-50) |  | 19 | 19 | 2025-01-06 | 2025-01-28 | 2024-12-28 | 2025-01-21 | 151
C-52-0405-CME05-1000 | Trench Excavation | 2 | 2 | 2025-01-06 | 2025-01-08 | 2024-12-28 | 2024-12-31 | 63
C-52-0405-CME05-1010 | Bedding | 2 | 2 | 2025-01-08 | 2025-01-10 | 2024-12-31 | 2025-01-03 | 130
C-52-0405-CME05-1020 | Lowering | 2 | 2 | 2025-01-10 | 2025-01-13 | 2025-01-03 | 2025-01-06 | 130
C-52-0405-CME05-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-13 | 2025-01-16 | 2025-01-06 | 2025-01-09 | 130
C-52-0405-CME05-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-16 | 2025-01-20 | 2025-01-09 | 2025-01-13 | 151
C-52-0405-CME05-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-01-20 | 2025-01-23 | 2025-01-13 | 2025-01-16 | 151
C-52-0405-CME05-1060 | Holiday Testing | 2 | 2 | 2025-01-23 | 2025-01-25 | 2025-01-16 | 2025-01-18 | 151
C-52-0405-CME05-1070 | Padding & Back Filling | 2 | 2 | 2025-01-25 | 2025-01-28 | 2025-01-18 | 2025-01-21 | 151
Crossing Mechanical (TX-52) |  | 19 | 19 | 2025-01-09 | 2025-01-31 | 2024-12-31 | 2025-01-23 | 149
C-52-0405-CME06-1000 | Trench Excavation | 2 | 2 | 2025-01-09 | 2025-01-11 | 2024-12-31 | 2025-01-03 | 63
C-52-0405-CME06-1010 | Bedding | 2 | 2 | 2025-01-11 | 2025-01-14 | 2025-01-03 | 2025-01-06 | 128
C-52-0405-CME06-1020 | Lowering | 2 | 2 | 2025-01-14 | 2025-01-16 | 2025-01-06 | 2025-01-08 | 128
C-52-0405-CME06-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-16 | 2025-01-20 | 2025-01-08 | 2025-01-11 | 128
C-52-0405-CME06-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-20 | 2025-01-23 | 2025-01-11 | 2025-01-15 | 149
C-52-0405-CME06-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-01-23 | 2025-01-27 | 2025-01-15 | 2025-01-18 | 149
C-52-0405-CME06-1060 | Holiday Testing | 2 | 2 | 2025-01-27 | 2025-01-29 | 2025-01-18 | 2025-01-21 | 149
C-52-0405-CME06-1070 | Padding & Back Filling | 2 | 2 | 2025-01-29 | 2025-01-31 | 2025-01-21 | 2025-01-23 | 149
Crossing Mechanical (TX-53) |  | 19 | 19 | 2025-01-13 | 2025-02-04 | 2025-01-04 | 2025-01-27 | 146
C-52-0405-CME07-1000 | Trench Excavation | 2 | 2 | 2025-01-13 | 2025-01-15 | 2025-01-04 | 2025-01-07 | 63
C-52-0405-CME07-1010 | Bedding | 2 | 2 | 2025-01-15 | 2025-01-17 | 2025-01-07 | 2025-01-09 | 125
C-52-0405-CME07-1020 | Lowering | 2 | 2 | 2025-01-17 | 2025-01-20 | 2025-01-09 | 2025-01-11 | 125
C-52-0405-CME07-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-20 | 2025-01-23 | 2025-01-11 | 2025-01-15 | 125
C-52-0405-CME07-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-23 | 2025-01-27 | 2025-01-15 | 2025-01-18 | 146
C-52-0405-CME07-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-01-27 | 2025-01-30 | 2025-01-18 | 2025-01-22 | 146
C-52-0405-CME07-1060 | Holiday Testing | 2 | 2 | 2025-01-30 | 2025-02-01 | 2025-01-22 | 2025-01-24 | 146
C-52-0405-CME07-1070 | Padding & Back Filling | 2 | 2 | 2025-02-01 | 2025-02-04 | 2025-01-24 | 2025-01-27 | 146
Crossing Mechanical (TX-56) |  | 19 | 19 | 2025-01-16 | 2025-02-07 | 2025-01-08 | 2025-01-30 | 143
C-52-0405-CME08-1000 | Trench Excavation | 2 | 2 | 2025-01-16 | 2025-01-18 | 2025-01-08 | 2025-01-10 | 63
C-52-0405-CME08-1010 | Bedding | 2 | 2 | 2025-01-18 | 2025-01-21 | 2025-01-10 | 2025-01-13 | 122
C-52-0405-CME08-1020 | Lowering | 2 | 2 | 2025-01-21 | 2025-01-23 | 2025-01-13 | 2025-01-15 | 122
C-52-0405-CME08-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-23 | 2025-01-27 | 2025-01-15 | 2025-01-18 | 122
C-52-0405-CME08-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-27 | 2025-01-30 | 2025-01-18 | 2025-01-22 | 143
C-52-0405-CME08-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-01-30 | 2025-02-03 | 2025-01-22 | 2025-01-25 | 143
C-52-0405-CME08-1060 | Holiday Testing | 2 | 2 | 2025-02-03 | 2025-02-05 | 2025-01-25 | 2025-01-28 | 143
C-52-0405-CME08-1070 | Padding & Back Filling | 2 | 2 | 2025-02-05 | 2025-02-07 | 2025-01-28 | 2025-01-30 | 143
CP Works TemporaryCCOP52EL43 |  | 52 | 52 | 2025-05-09 | 2025-07-22 | 2025-04-25 | 2025-06-30 | 101
C-52-0405-PL-CA-5200 | Installation of CP Test Post | 30 | 30 | 2025-05-09 | 2025-06-16 | 2025-04-25 | 2025-05-31 | 121
C-52-0405-PL-CA-5210 | Glanding & Termination of Temp. CP S/m | 2 | 2 | 2025-07-19 | 2025-07-22 | 2025-06-26 | 2025-06-30 | 101
Test Stations & Anode BedsCCOP52EL42 |  | 52 | 52 | 2025-05-09 | 2025-07-22 | 2025-04-25 | 2025-06-30 | 27
C-52-0405-PL-CA-5600 | Installation of Temp. Anode | 52 | 52 | 2025-05-09 | 2025-07-22 | 2025-04-25 | 2025-06-30 | 27
PaddingCCOPL52414 |  | 50 | 50 | 2025-05-21 | 2025-07-22 | 2025-04-28 | 2025-06-30 | 27
C-52-0405-PL-CI-6000 | Padding | 50 | 50 | 2025-05-21 | 2025-07-22 | 2025-04-28 | 2025-06-30 | 27
BackfillingCCOPL52422 |  | 48 | 48 | 2025-05-29 | 2025-07-28 | 2025-05-07 | 2025-07-05 | 37
C-52-0405-PL-CI-6400 | Backfilling | 48 | 48 | 2025-05-29 | 2025-07-28 | 2025-05-07 | 2025-07-05 | 37
BermingCCOPL52423 |  | 51 | 51 | 2025-07-28 | 2025-09-26 | 2025-06-30 | 2025-08-28 | 57
C-52-0405-PL-CI-6800 | Gatch Laying & Levelling | 48 | 48 | 2025-07-28 | 2025-09-23 | 2025-06-30 | 2025-08-25 | 27
C-52-0405-PL-CI-6810 | Gatch Compaction | 48 | 48 | 2025-07-30 | 2025-09-25 | 2025-07-02 | 2025-08-27 | 27
C-52-0405-PL-CI-7800 | Installation of Marker Post/Sign Board | 48 | 48 | 2025-07-30 | 2025-09-25 | 2025-07-02 | 2025-08-27 | 57
C-52-0405-PL-CI-7810 | Installation of Crash Barriers (If any) | 47 | 47 | 2025-08-01 | 2025-09-26 | 2025-07-04 | 2025-08-28 | 57
NDRC by Micro Tunneling Method |  | 185 | 185 | 2024-08-26 | 2025-04-29 | 2024-10-28 | 2025-06-17 | 50
NDRC-16 (incl Hydrotest) @ CH 99+430 - 99+560 (Open Cut*) |  | 19 | 19 | 2025-01-20 | 2025-02-11 | 2025-01-11 | 2025-02-03 | 133
Entry & Exit Pit ConstructionCCOPL52958 |  | 2 | 2 | 2025-01-20 | 2025-01-22 | 2025-01-11 | 2025-01-14 | 63
C-52-0405-CME16-1000 | Trench Excavation | 2 | 2 | 2025-01-20 | 2025-01-22 | 2025-01-11 | 2025-01-14 | 63
Tunneling & Jack UpCCOPL52960 |  | 2 | 2 | 2025-01-22 | 2025-01-24 | 2025-01-14 | 2025-01-16 | 133
C-52-0405-CME16-1010 | Bedding | 2 | 2 | 2025-01-22 | 2025-01-24 | 2025-01-14 | 2025-01-16 | 133
Pipe Lowering, Welding, NDT & CoatingCCOPL57452 |  | 11 | 11 | 2025-01-24 | 2025-02-06 | 2025-01-16 | 2025-01-29 | 133
C-52-0405-CME16-1020 | Lowering | 2 | 2 | 2025-01-24 | 2025-01-27 | 2025-01-16 | 2025-01-18 | 133
C-52-0405-CME16-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-27 | 2025-01-30 | 2025-01-18 | 2025-01-22 | 133
C-52-0405-CME16-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-01-30 | 2025-02-03 | 2025-01-22 | 2025-01-25 | 133
C-52-0405-CME16-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-02-03 | 2025-02-06 | 2025-01-25 | 2025-01-29 | 133
HydrotestingCCOPL57462 |  | 2 | 2 | 2025-02-06 | 2025-02-08 | 2025-01-29 | 2025-01-31 | 133
C-52-0405-CME16-1060 | Holiday Testing | 2 | 2 | 2025-02-06 | 2025-02-08 | 2025-01-29 | 2025-01-31 | 133
Re-Instatement of Entry & Exit PitCCOPL57472 |  | 2 | 2 | 2025-02-08 | 2025-02-11 | 2025-01-31 | 2025-02-03 | 133
C-52-0405-CME16-1070 | Padding & Back Filling | 2 | 2 | 2025-02-08 | 2025-02-11 | 2025-01-31 | 2025-02-03 | 133
Micro Tunnelling @ CH 101+434 - 101+502 (NDRC-17) |  | 127 | 127 | 2024-08-26 | 2025-04-08 | 2024-10-28 | 2025-04-07 | 108
Entry & Exit Pit ConstructionCCOPL52904 |  | 67 | 67 | 2024-08-26 | 2024-11-01 | 2024-10-28 | 2025-01-17 | 96
C-52-0405-CNM17-1000 | Sheet Piling for Driving & Receiving Pit | 30 | 30 | 2024-08-26 | 2024-09-24 | 2024-10-28 | 2024-12-04 | 96
C-52-0405-CNM17-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-09-25 | 2024-09-28 | 2024-12-04 | 2024-12-09 | 96
C-52-0405-CNM17-1010 | Driving & Receiving Pit Excavation | 18 | 18 | 2024-09-20 | 2024-10-05 | 2024-12-04 | 2024-12-25 | 96
C-52-0405-CNM17-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 14 | 14 | 2024-09-30 | 2024-10-10 | 2024-12-09 | 2024-12-25 | 96
C-52-0405-CNM17-1040 | Floor Blinding & French Drain in Driving Pit | 6 | 6 | 2024-10-11 | 2024-10-17 | 2024-12-25 | 2025-01-02 | 96
C-52-0405-CNM17-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 6 | 6 | 2024-10-18 | 2024-10-24 | 2025-01-02 | 2025-01-09 | 96
C-52-0405-CNM17-1060 | Construction of Exit Wall with Ring | 6 | 6 | 2024-10-26 | 2024-11-01 | 2025-01-10 | 2025-01-17 | 96
Tunneling & Jack UpCCOPL57102 |  | 46 | 46 | 2025-01-28 | 2025-03-15 | 2025-01-17 | 2025-03-14 | 108
C-52-0405-CNM17-1200 | Jacking of MTBM & RC Sleeves | 12 | 12 | 2025-01-28 | 2025-02-05 | 2025-01-17 | 2025-01-31 | 96
C-52-0405-CNM17-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2025-02-06 | 2025-02-10 | 2025-01-31 | 2025-02-05 | 96
C-52-0405-CNM17-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-03-08 | 2025-03-15 | 2025-03-07 | 2025-03-14 | 108
Pipe Lowering, Welding, NDT & CoatingCCOPL57112 |  | 13 | 13 | 2025-02-11 | 2025-02-25 | 2025-02-05 | 2025-02-20 | 108
C-52-0405-CNM17-1400 | Lowering & Welding of Carrier Pipe | 12 | 12 | 2025-02-11 | 2025-02-21 | 2025-02-05 | 2025-02-19 | 96
C-52-0405-CNM17-1410 | NDT, Coating & Holiday Inspection of Carrier Pipe | 12 | 12 | 2025-02-12 | 2025-02-25 | 2025-02-06 | 2025-02-20 | 108
HydrotestingCCOPL57122 |  | 12 | 12 | 2025-02-26 | 2025-03-08 | 2025-02-20 | 2025-03-07 | 108
C-52-0405-CNM17-1600 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 12 | 12 | 2025-02-26 | 2025-03-08 | 2025-02-20 | 2025-03-07 | 108
Re-Instatement of Entry & Exit PitCCOPL57132 |  | 14 | 14 | 2025-03-15 | 2025-04-08 | 2025-03-14 | 2025-04-07 | 108
C-52-0405-CNM17-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-03-15 | 2025-04-08 | 2025-03-14 | 2025-04-07 | 108
HDD @ CH 103+962 - 104+135 (NDRC-18) |  | 126 | 126 | 2024-10-26 | 2025-04-05 | 2025-01-02 | 2025-06-11 | 55
Entry & Exit Pit ConstructionCCOPL52906 |  | 62 | 62 | 2024-10-26 | 2025-01-04 | 2025-01-02 | 2025-03-18 | 41
C-52-0405-CNM18-1000 | Sheet Piling for Driving & Receiving Pit | 25 | 25 | 2024-10-26 | 2024-11-23 | 2025-01-02 | 2025-01-30 | 41
C-52-0405-CNM18-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-11-25 | 2024-11-28 | 2025-01-31 | 2025-02-04 | 41
C-52-0405-CNM18-1010 | Driving & Receiving Pit Excavation | 18 | 18 | 2024-11-20 | 2024-12-07 | 2025-01-31 | 2025-02-20 | 41
C-52-0405-CNM18-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 14 | 14 | 2024-11-29 | 2024-12-12 | 2025-02-05 | 2025-02-20 | 41
C-52-0405-CNM18-1040 | Floor Blinding & French Drain in Driving Pit | 6 | 6 | 2024-12-13 | 2024-12-19 | 2025-02-21 | 2025-02-27 | 41
C-52-0405-CNM18-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 6 | 6 | 2024-12-20 | 2024-12-26 | 2025-02-28 | 2025-03-08 | 41
C-52-0405-CNM18-1060 | Construction of Exit Wall with Ring | 6 | 6 | 2024-12-28 | 2025-01-04 | 2025-03-09 | 2025-03-18 | 41
Tunneling & Jack UpCCOPL57762 |  | 50 | 50 | 2025-01-11 | 2025-03-12 | 2025-03-19 | 2025-05-23 | 55
C-52-0405-CNM18-1200 | Jacking of MTBM & RC Sleeves | 14 | 14 | 2025-01-11 | 2025-01-27 | 2025-03-19 | 2025-04-10 | 41
C-52-0405-CNM18-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2025-01-28 | 2025-01-31 | 2025-04-10 | 2025-04-15 | 41
C-52-0405-CNM18-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-03-05 | 2025-03-12 | 2025-05-17 | 2025-05-23 | 55
Pipe Lowering, Welding, NDT & CoatingCCOPL57772 |  | 19 | 19 | 2025-02-01 | 2025-02-22 | 2025-04-15 | 2025-05-08 | 55
C-52-0405-CNM18-1400 | Lowering & Welding of Carrier Pipe | 16 | 16 | 2025-02-01 | 2025-02-19 | 2025-04-15 | 2025-05-03 | 41
C-52-0405-CNM18-1410 | NDT, Coating & Holiday Inspection of Carrier Pipe | 18 | 18 | 2025-02-03 | 2025-02-22 | 2025-04-16 | 2025-05-08 | 55
HydrotestingCCOPL57782 |  | 8 | 8 | 2025-02-24 | 2025-03-05 | 2025-05-08 | 2025-05-17 | 55
C-52-0405-CNM18-1600 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 8 | 8 | 2025-02-24 | 2025-03-05 | 2025-05-08 | 2025-05-17 | 55
Re-Instatement of Entry & Exit PitCCOPL57792 |  | 14 | 14 | 2025-03-13 | 2025-04-05 | 2025-05-23 | 2025-06-11 | 55
C-52-0405-CNM18-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-03-13 | 2025-04-05 | 2025-05-23 | 2025-06-11 | 55
Micro Tunnelling @ CH 111+570 - 111+723 (NDRC-23) |  | 166 | 166 | 2024-11-04 | 2025-04-29 | 2024-11-19 | 2025-06-17 | 50
Entry & Exit Pit ConstructionCCOPL52914 |  | 78 | 78 | 2024-11-04 | 2025-01-13 | 2024-11-19 | 2025-02-20 | 40
C-52-0405-CNM23-1000 | Sheet Piling for Driving & Receiving Pit | 35 | 35 | 2024-11-04 | 2024-12-04 | 2024-11-19 | 2024-12-31 | 40
C-52-0405-CNM23-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-12-05 | 2024-12-09 | 2025-01-02 | 2025-01-06 | 40
C-52-0405-CNM23-1010 | Driving & Receiving Pit Excavation | 25 | 25 | 2024-11-28 | 2024-12-16 | 2025-01-02 | 2025-01-30 | 40
C-52-0405-CNM23-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 21 | 21 | 2024-12-10 | 2024-12-20 | 2025-01-07 | 2025-01-30 | 40
C-52-0405-CNM23-1040 | Floor Blinding & French Drain in Driving Pit | 6 | 6 | 2024-12-21 | 2024-12-27 | 2025-01-31 | 2025-02-06 | 40
C-52-0405-CNM23-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 6 | 6 | 2024-12-28 | 2025-01-04 | 2025-02-07 | 2025-02-13 | 40
C-52-0405-CNM23-1060 | Construction of Exit Wall with Ring | 5 | 5 | 2025-01-07 | 2025-01-13 | 2025-02-15 | 2025-02-20 | 40
Tunneling & Jack UpCCOPL57722 |  | 74 | 74 | 2025-02-06 | 2025-04-12 | 2025-02-21 | 2025-05-29 | 50
C-52-0405-CNM23-1200 | Jacking of MTBM & RC Sleeves | 23 | 23 | 2025-02-06 | 2025-02-20 | 2025-02-21 | 2025-03-24 | 40
C-52-0405-CNM23-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2025-02-21 | 2025-02-25 | 2025-03-25 | 2025-04-03 | 40
C-52-0405-CNM23-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-04-07 | 2025-04-12 | 2025-05-23 | 2025-05-29 | 50
Pipe Lowering, Welding, NDT & CoatingCCOPL57732 |  | 28 | 28 | 2025-02-26 | 2025-03-23 | 2025-04-03 | 2025-05-06 | 50
C-52-0405-CNM23-1400 | Lowering & Welding of Carrier Pipe | 27 | 27 | 2025-02-26 | 2025-03-18 | 2025-04-03 | 2025-05-05 | 40
C-52-0405-CNM23-1410 | NDT, Coating & Holiday Inspection of Carrier Pipe | 27 | 27 | 2025-02-27 | 2025-03-23 | 2025-04-04 | 2025-05-06 | 50
HydrotestingCCOPL57742 |  | 14 | 14 | 2025-03-23 | 2025-04-07 | 2025-05-07 | 2025-05-23 | 50
C-52-0405-CNM23-1600 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 14 | 14 | 2025-03-23 | 2025-04-07 | 2025-05-07 | 2025-05-23 | 50
Re-Instatement of Entry & Exit PitCCOPL57752 |  | 14 | 14 | 2025-04-12 | 2025-04-29 | 2025-05-29 | 2025-06-17 | 50
C-52-0405-CNM23-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-04-12 | 2025-04-29 | 2025-05-29 | 2025-06-17 | 50
NDRC-21 (incl Hydrotest) at KP 109+870.405/RX-19 (Open Cut*) |  | 19 | 19 | 2025-01-23 | 2025-02-14 | 2025-01-15 | 2025-02-06 | 137
Entry & Exit Pit ConstructionCCOPL52910 |  | 2 | 2 | 2025-01-23 | 2025-01-25 | 2025-01-15 | 2025-01-17 | 63
C-52-0405-CME09-1000 | Trench Excavation | 2 | 2 | 2025-01-23 | 2025-01-25 | 2025-01-15 | 2025-01-17 | 63
Tunneling & Jack UpCCOPL57412 |  | 2 | 2 | 2025-01-25 | 2025-01-28 | 2025-01-17 | 2025-01-20 | 116
C-52-0405-CME09-1010 | Bedding | 2 | 2 | 2025-01-25 | 2025-01-28 | 2025-01-17 | 2025-01-20 | 116
Pipe Lowering, Welding, NDT & CoatingCCOPL57422 |  | 11 | 11 | 2025-01-28 | 2025-02-10 | 2025-01-20 | 2025-02-01 | 137
C-52-0405-CME09-1020 | Lowering | 2 | 2 | 2025-01-28 | 2025-01-30 | 2025-01-20 | 2025-01-22 | 116
C-52-0405-CME09-1030 | Section Tie-in Welding | 3 | 3 | 2025-01-30 | 2025-02-03 | 2025-01-22 | 2025-01-25 | 116
C-52-0405-CME09-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-02-03 | 2025-02-06 | 2025-01-25 | 2025-01-29 | 137
C-52-0405-CME09-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-02-06 | 2025-02-10 | 2025-01-29 | 2025-02-01 | 137
HydrotestingCCOPL57432 |  | 2 | 2 | 2025-02-10 | 2025-02-12 | 2025-02-01 | 2025-02-04 | 137
C-52-0405-CME09-1060 | Holiday Testing | 2 | 2 | 2025-02-10 | 2025-02-12 | 2025-02-01 | 2025-02-04 | 137
Re-Instatement of Entry & Exit PitCCOPL57442 |  | 2 | 2 | 2025-02-12 | 2025-02-14 | 2025-02-04 | 2025-02-06 | 137
C-52-0405-CME09-1070 | Padding & Back Filling | 2 | 2 | 2025-02-12 | 2025-02-14 | 2025-02-04 | 2025-02-06 | 137
NDRC-22 (incl Hydrotest) at KP 110+723.072/RX-20 (Open Cut*) |  | 19 | 19 | 2025-01-27 | 2025-02-18 | 2025-01-18 | 2025-02-10 | 134
Entry & Exit Pit ConstructionCCOPL52912 |  | 2 | 2 | 2025-01-27 | 2025-01-29 | 2025-01-18 | 2025-01-21 | 63
C-52-0405-CME10-1000 | Trench Excavation | 2 | 2 | 2025-01-27 | 2025-01-29 | 2025-01-18 | 2025-01-21 | 63
Tunneling & Jack UpCCOPL57062 |  | 2 | 2 | 2025-01-29 | 2025-01-31 | 2025-01-21 | 2025-01-23 | 113
C-52-0405-CME10-1010 | Bedding | 2 | 2 | 2025-01-29 | 2025-01-31 | 2025-01-21 | 2025-01-23 | 113
Pipe Lowering, Welding, NDT & CoatingCCOPL57072 |  | 11 | 11 | 2025-01-31 | 2025-02-13 | 2025-01-23 | 2025-02-05 | 134
C-52-0405-CME10-1020 | Lowering | 2 | 2 | 2025-01-31 | 2025-02-03 | 2025-01-23 | 2025-01-25 | 113
C-52-0405-CME10-1030 | Section Tie-in Welding | 3 | 3 | 2025-02-03 | 2025-02-06 | 2025-01-25 | 2025-01-29 | 113
C-52-0405-CME10-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-02-06 | 2025-02-10 | 2025-01-29 | 2025-02-01 | 134
C-52-0405-CME10-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-02-10 | 2025-02-13 | 2025-02-01 | 2025-02-05 | 134
HydrotestingCCOPL57082 |  | 2 | 2 | 2025-02-13 | 2025-02-15 | 2025-02-05 | 2025-02-07 | 134
C-52-0405-CME10-1060 | Holiday Testing | 2 | 2 | 2025-02-13 | 2025-02-15 | 2025-02-05 | 2025-02-07 | 134
Re-Instatement of Entry & Exit PitCCOPL57092 |  | 2 | 2 | 2025-02-15 | 2025-02-18 | 2025-02-07 | 2025-02-10 | 134
C-52-0405-CME10-1070 | Padding & Back Filling | 2 | 2 | 2025-02-15 | 2025-02-18 | 2025-02-07 | 2025-02-10 | 134
NDRC-25 (incl Hydrotest) at KP 114+561.682/RX-22 (Open Cut*) |  | 19 | 19 | 2025-01-30 | 2025-02-21 | 2025-01-22 | 2025-02-13 | 131
Entry & Exit Pit ConstructionCCOPL52918 |  | 2 | 2 | 2025-01-30 | 2025-02-01 | 2025-01-22 | 2025-01-24 | 63
C-52-0405-CME11-1000 | Trench Excavation | 2 | 2 | 2025-01-30 | 2025-02-01 | 2025-01-22 | 2025-01-24 | 63
Tunneling & Jack UpCCOPL57372 |  | 2 | 2 | 2025-02-01 | 2025-02-04 | 2025-01-24 | 2025-01-27 | 110
C-52-0405-CME11-1010 | Bedding | 2 | 2 | 2025-02-01 | 2025-02-04 | 2025-01-24 | 2025-01-27 | 110
Pipe Lowering, Welding, NDT & CoatingCCOPL57382 |  | 11 | 11 | 2025-02-04 | 2025-02-17 | 2025-01-27 | 2025-02-08 | 131
C-52-0405-CME11-1020 | Lowering | 2 | 2 | 2025-02-04 | 2025-02-06 | 2025-01-27 | 2025-01-29 | 110
C-52-0405-CME11-1030 | Section Tie-in Welding | 3 | 3 | 2025-02-06 | 2025-02-10 | 2025-01-29 | 2025-02-01 | 110
C-52-0405-CME11-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-02-10 | 2025-02-13 | 2025-02-01 | 2025-02-05 | 131
C-52-0405-CME11-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-02-13 | 2025-02-17 | 2025-02-05 | 2025-02-08 | 131
HydrotestingCCOPL57392 |  | 2 | 2 | 2025-02-17 | 2025-02-19 | 2025-02-08 | 2025-02-11 | 131
C-52-0405-CME11-1060 | Holiday Testing | 2 | 2 | 2025-02-17 | 2025-02-19 | 2025-02-08 | 2025-02-11 | 131
Re-Instatement of Entry & Exit PitCCOPL57402 |  | 2 | 2 | 2025-02-19 | 2025-02-21 | 2025-02-11 | 2025-02-13 | 131
C-52-0405-CME11-1070 | Padding & Back Filling | 2 | 2 | 2025-02-19 | 2025-02-21 | 2025-02-11 | 2025-02-13 | 131
NDRC by Micro Tunnelling Method |  | 179 | 179 | 2024-10-23 | 2025-07-12 | 2024-11-04 | 2025-06-17 | 50
Micro Tunnelling @ CH 105+252 - 105+523 (NDRC-19) |  | 171 | 171 | 2024-11-23 | 2025-06-03 | 2024-11-04 | 2025-06-07 | 58
Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 |  | 142 | 142 | 2024-11-23 | 2025-04-29 | 2024-11-04 | 2025-05-01 | 58
C-52-0405-CNH19-1000 | Sheet Piling for Driving & Receiving Pit | 35 | 35 | 2024-11-23 | 2024-12-24 | 2024-11-04 | 2024-12-17 | 58
C-52-0405-CNH19-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-12-25 | 2024-12-28 | 2024-12-17 | 2024-12-21 | 58
C-52-0405-CNH19-1010 | Driving & Receiving Pit Excavation | 21 | 21 | 2024-12-20 | 2025-01-06 | 2024-12-17 | 2025-01-11 | 58
C-52-0405-CNH19-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 17 | 17 | 2024-12-30 | 2025-01-10 | 2024-12-21 | 2025-01-11 | 58
C-52-0405-CNH19-1040 | Floor Blinding & French Drain in Driving Pit | 8 | 8 | 2025-01-11 | 2025-01-17 | 2025-01-11 | 2025-01-21 | 58
C-52-0405-CNH19-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 8 | 8 | 2025-01-18 | 2025-01-24 | 2025-01-21 | 2025-01-30 | 58
C-52-0405-CNH19-1060 | Construction of Exit Wall with Ring | 8 | 8 | 2025-01-27 | 2025-02-01 | 2025-01-30 | 2025-02-08 | 58
C-52-0405-CNH19-1070 | Lowering & Welding of Carrier Pipe | 25 | 25 | 2025-03-07 | 2025-04-14 | 2025-03-07 | 2025-04-14 | 58
C-52-0405-CNH19-1080 | NDT, Coating & Holiday Inspection of Carrier Pipe | 27 | 27 | 2025-03-08 | 2025-04-17 | 2025-03-08 | 2025-04-17 | 58
C-52-0405-CNH19-1090 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 12 | 12 | 2025-04-17 | 2025-04-29 | 2025-04-17 | 2025-05-01 | 58
Tunneling & Jack UpCCOPL58142 |  | 77 | 77 | 2025-02-03 | 2025-05-17 | 2025-02-08 | 2025-05-20 | 58
C-52-0405-CNH19-1200 | Jacking of MTBM & RC Sleeves | 18 | 18 | 2025-02-03 | 2025-02-28 | 2025-02-08 | 2025-03-01 | 58
C-52-0405-CNH19-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2025-03-01 | 2025-03-06 | 2025-03-01 | 2025-03-07 | 58
C-52-0405-CNH19-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-05-12 | 2025-05-17 | 2025-05-14 | 2025-05-20 | 58
Re-Instatement of Entry & Exit PitCCOPL58152 |  | 14 | 14 | 2025-05-17 | 2025-06-03 | 2025-05-20 | 2025-06-07 | 58
C-52-0405-CNH19-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-05-17 | 2025-06-03 | 2025-05-20 | 2025-06-07 | 58
Micro Tunnelling @ CH 106+335 - 106+645 (NDRC-20) |  | 137 | 137 | 2024-10-23 | 2025-05-19 | 2024-11-13 | 2025-05-05 | 84
Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 |  | 108 | 108 | 2024-10-23 | 2025-04-14 | 2024-11-13 | 2025-03-28 | 84
C-52-0405-CNH20-1000 | Sheet Piling for Driving & Receiving Pit | 15 | 15 | 2024-10-23 | 2024-11-20 | 2024-11-13 | 2024-11-29 | 80
C-52-0405-CNH20-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-11-21 | 2024-11-25 | 2024-11-30 | 2024-12-06 | 80
C-52-0405-CNH20-1010 | Driving & Receiving Pit Excavation | 14 | 14 | 2024-11-16 | 2024-12-04 | 2024-11-30 | 2024-12-18 | 80
C-52-0405-CNH20-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 10 | 10 | 2024-11-26 | 2024-12-09 | 2024-12-07 | 2024-12-18 | 80
C-52-0405-CNH20-1040 | Floor Blinding & French Drain in Driving Pit | 6 | 6 | 2024-12-10 | 2024-12-16 | 2024-12-19 | 2024-12-25 | 80
C-52-0405-CNH20-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 6 | 6 | 2024-12-17 | 2024-12-23 | 2024-12-26 | 2025-01-02 | 80
C-52-0405-CNH20-1060 | Construction of Exit Wall with Ring | 6 | 6 | 2024-12-24 | 2024-12-30 | 2025-01-03 | 2025-01-09 | 80
C-52-0405-CNH20-1070 | Lowering & Welding of Carrier Pipe | 20 | 20 | 2025-02-15 | 2025-03-24 | 2025-02-14 | 2025-03-11 | 80
C-52-0405-CNH20-1080 | NDT, Coating & Holiday Inspection of Carrier Pipe | 20 | 20 | 2025-02-17 | 2025-03-29 | 2025-02-15 | 2025-03-12 | 84
C-52-0405-CNH20-1090 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 10 | 10 | 2025-03-29 | 2025-04-14 | 2025-03-13 | 2025-03-28 | 84
Tunneling & Jack UpCCOPL58302 |  | 76 | 76 | 2025-01-11 | 2025-05-01 | 2025-01-10 | 2025-04-18 | 84
C-52-0405-CNH20-1200 | Jacking of MTBM & RC Sleeves | 26 | 26 | 2025-01-11 | 2025-02-10 | 2025-01-10 | 2025-02-08 | 80
C-52-0405-CNH20-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2025-02-11 | 2025-02-14 | 2025-02-10 | 2025-02-13 | 80
C-52-0405-CNH20-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-04-25 | 2025-05-01 | 2025-04-12 | 2025-04-18 | 84
Re-Instatement of Entry & Exit PitCCOPL58312 |  | 14 | 14 | 2025-05-01 | 2025-05-19 | 2025-04-18 | 2025-05-05 | 84
C-52-0405-CNH20-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-05-01 | 2025-05-19 | 2025-04-18 | 2025-05-05 | 84
Micro Tunnelling @ CH 112+035 - 112+360 (NDRC-24) |  | 150 | 150 | 2024-11-22 | 2025-07-12 | 2024-12-10 | 2025-06-17 | 50
Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 |  | 137 | 137 | 2024-11-22 | 2025-05-31 | 2024-12-10 | 2025-05-30 | 50
C-52-0405-CNH24-1000 | Sheet Piling for Driving & Receiving Pit | 14 | 14 | 2024-11-22 | 2024-12-23 | 2024-12-10 | 2024-12-25 | 27
C-52-0405-CNH24-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-12-24 | 2024-12-27 | 2024-12-26 | 2024-12-30 | 37
C-52-0405-CNH24-1010 | Driving & Receiving Pit Excavation | 14 | 14 | 2024-12-19 | 2025-01-04 | 2025-01-04 | 2025-01-20 | 27
C-52-0405-CNH24-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 10 | 10 | 2024-12-28 | 2025-01-09 | 2025-01-13 | 2025-01-23 | 27
C-52-0405-CNH24-1040 | Floor Blinding & French Drain in Driving Pit | 5 | 5 | 2025-01-10 | 2025-01-16 | 2025-01-24 | 2025-01-29 | 27
C-52-0405-CNH24-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 5 | 5 | 2025-01-17 | 2025-01-23 | 2025-01-30 | 2025-02-04 | 27
C-52-0405-CNH24-1060 | Construction of Exit Wall with Ring | 5 | 5 | 2025-01-25 | 2025-01-31 | 2025-02-07 | 2025-02-12 | 27
C-52-0405-CNH24-1070 | Lowering & Welding of Carrier Pipe | 40 | 40 | 2025-04-08 | 2025-05-14 | 2025-04-03 | 2025-05-21 | 27
C-52-0405-CNH24-1080 | NDT, Coating & Holiday Inspection of Carrier Pipe | 40 | 40 | 2025-04-09 | 2025-05-17 | 2025-04-04 | 2025-05-22 | 50
C-52-0405-CNH24-1090 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 7 | 7 | 2025-05-17 | 2025-05-31 | 2025-05-22 | 2025-05-30 | 50
Tunneling & Jack UpCCOPL58242 |  | 88 | 88 | 2025-02-21 | 2025-06-25 | 2025-02-13 | 2025-06-09 | 50
C-52-0405-CNH24-1200 | Jacking of MTBM & RC Sleeves | 30 | 30 | 2025-02-21 | 2025-04-03 | 2025-02-13 | 2025-03-24 | 27
C-52-0405-CNH24-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2025-04-03 | 2025-04-08 | 2025-03-25 | 2025-04-03 | 27
C-52-0405-CNH24-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-06-19 | 2025-06-25 | 2025-05-31 | 2025-06-09 | 50
Re-Instatement of Entry & Exit PitCCOPL58252 |  | 7 | 7 | 2025-06-25 | 2025-07-12 | 2025-06-09 | 2025-06-17 | 50
C-52-0405-CNH24-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 7 | 7 | 2025-06-25 | 2025-07-12 | 2025-06-09 | 2025-06-17 | 50
Cathodic Protection |  | 83 | 83 | 2025-04-23 | 2025-07-30 | 2025-03-23 | 2025-07-08 | 101
Civil Works |  | 60 | 60 | 2025-04-23 | 2025-07-07 | 2025-03-23 | 2025-06-10 | 115
Backfilling & Reinstatement for CP (for Crossings)CCOP52CS37 |  | 60 | 60 | 2025-04-23 | 2025-07-07 | 2025-03-23 | 2025-06-10 | 115
C-52-0405-PIPEL-5260 | Backfilling & Reinstatement for CP (for Crossings) | 60 | 60 | 2025-04-23 | 2025-07-07 | 2025-03-23 | 2025-06-10 | 115
CP Works |  | 73 | 73 | 2025-05-05 | 2025-07-30 | 2025-04-09 | 2025-07-08 | 101
CP Works (for Crossings)CCOP52EL52 |  | 73 | 73 | 2025-05-05 | 2025-07-30 | 2025-04-09 | 2025-07-08 | 101
C-52-0405-PL-CA-5220 | Installation of Test Post for Crossing | 50 | 50 | 2025-05-05 | 2025-07-07 | 2025-04-09 | 2025-06-10 | 115
C-52-0405-PL-CA-5230 | Installation of CP JB's | 50 | 50 | 2025-05-05 | 2025-07-07 | 2025-04-09 | 2025-06-10 | 115
C-52-0405-PL-CA-5240 | Installation of CP TR | 50 | 50 | 2025-05-05 | 2025-07-07 | 2025-04-09 | 2025-06-10 | 115
C-52-0405-PL-CA-5250 | CIP/DCVG Survey | 7 | 7 | 2025-07-22 | 2025-07-30 | 2025-06-30 | 2025-07-08 | 101
Telecommunication Works |  | 53 | 53 | 2025-05-21 | 2025-07-25 | 2025-04-28 | 2025-07-03 | 105
Telecom Works along PipelineCCOP52IC36 |  | 53 | 53 | 2025-05-21 | 2025-07-25 | 2025-04-28 | 2025-07-03 | 105
C-52-0405-PL-TE-8200 | FO - Cable Pulling/ Laying | 50 | 50 | 2025-05-21 | 2025-07-22 | 2025-04-28 | 2025-06-30 | 40
C-52-0405-PL-TE-8210 | Termination/Splicing @ BVS | 3 | 3 | 2025-07-22 | 2025-07-25 | 2025-06-30 | 2025-07-03 | 105
52"x25 Km Pipeline from BVS-05 to BVS-06 at KP 139.2 |  | 221 | 221 | 2024-08-05 | 2025-08-26 | 2024-11-01 | 2025-08-04 | 69
52"x 25.0 Km Pipeline from BVS-05 to BVS-06 at KP 139.2 |  | 221 | 221 | 2024-08-05 | 2025-08-26 | 2024-11-01 | 2025-08-04 | 69
Main Pipeline |  | 221 | 221 | 2024-08-05 | 2025-08-26 | 2024-11-01 | 2025-08-04 | 69
ROW Access Road from BVS-05 to KP 126.2CCOPL52440.1 |  | 36 | 36 | 2024-08-05 | 2024-09-14 | 2024-11-01 | 2024-12-16 | 0
C-52-0506-PL-CI-1800 | Sabka ROW/Grading | 36 | 36 | 2024-08-05 | 2024-09-14 | 2024-11-01 | 2024-12-16 | 0
ROW Access Road from BVS-05 to KP 126.2CCOPL52440.2 |  | 30 | 30 | 2024-10-21 | 2024-11-30 | 2025-01-21 | 2025-02-25 | 0
C-52-0506-PL-CI-1900 | Sabka ROW/Grading | 30 | 30 | 2024-10-21 | 2024-11-30 | 2025-01-21 | 2025-02-25 | 0
Cut & Fill in Sandy Area from BVS-05 to KP 126.2CCOPL52466.1 |  | 30 | 30 | 2024-10-21 | 2024-12-14 | 2025-01-21 | 2025-02-25 | 0
C-52-0506-PL-CI-1400 | Cut & Fill (@ Non-Sabkha) | 30 | 30 | 2024-10-21 | 2024-12-14 | 2025-01-21 | 2025-02-25 | 0
Cut & Fill in Sandy Area from KP 126.2 to BVS-06CCOPL52466.2 |  | 30 | 30 | 2024-12-14 | 2025-02-06 | 2025-02-25 | 2025-04-10 | 0
C-52-0506-PL-CI-1600 | Cut & Fill (@ Non-Sabkha) | 30 | 30 | 2024-12-14 | 2025-02-06 | 2025-02-25 | 2025-04-10 | 0
Excavation (incl Bedding)CCOPL52455 |  | 53 | 53 | 2025-05-12 | 2025-07-18 | 2025-04-21 | 2025-06-24 | 20
C-52-0506-PL-CI-2400 | Trench Excavation | 48 | 48 | 2025-05-12 | 2025-07-12 | 2025-04-21 | 2025-06-18 | 20
C-52-0506-PL-CI-2410 | Bedding | 48 | 48 | 2025-05-17 | 2025-07-18 | 2025-04-26 | 2025-06-24 | 20
Pipe StringingCCOPL52441 |  | 20 | 20 | 2025-01-11 | 2025-02-12 | 2025-03-18 | 2025-04-16 | 0
C-52-0506-PL-ME-2800 | Stringing (BVS-05 to BVS-06) | 20 | 20 | 2025-01-11 | 2025-02-12 | 2025-03-18 | 2025-04-16 | 0
Automatic WeldingCCOPL52448 |  | 48 | 48 | 2025-05-08 | 2025-07-09 | 2025-04-17 | 2025-06-14 | 0
C-52-0506-PL-ME-3600 | Automatic Welding | 48 | 48 | 2025-05-08 | 2025-07-09 | 2025-04-17 | 2025-06-14 | 0
NDT TestCCOPL52463 |  | 48 | 48 | 2025-05-10 | 2025-07-11 | 2025-04-19 | 2025-06-17 | 26
C-52-0506-PL-ME-4000 | NDT | 48 | 48 | 2025-05-10 | 2025-07-11 | 2025-04-19 | 2025-06-17 | 26
Ext. Joint CoatingCCOPL52446 |  | 61 | 61 | 2025-05-13 | 2025-07-28 | 2025-04-22 | 2025-07-05 | 20
C-52-0506-PL-ME-4400 | Ext. Joint Coating | 48 | 48 | 2025-05-13 | 2025-07-14 | 2025-04-22 | 2025-06-19 | 26
C-52-0506-PL-ME-4410 | Ext. Joint Coating (Tie-in Joint) | 48 | 48 | 2025-05-27 | 2025-07-28 | 2025-05-07 | 2025-07-05 | 20
Cold BendsCCOPL52447 |  | 42 | 42 | 2025-06-02 | 2025-07-24 | 2025-05-10 | 2025-07-02 | 20
C-52-0506-PL-ME-3200 | Cold Bends | 42 | 42 | 2025-06-02 | 2025-07-24 | 2025-05-10 | 2025-07-02 | 20
Pipe Lowering & Tie-in / NDTCCOPL52456 |  | 54 | 54 | 2025-05-23 | 2025-07-30 | 2025-05-02 | 2025-07-08 | 20
C-52-0506-PL-ME-4800 | Lowering | 48 | 48 | 2025-05-23 | 2025-07-24 | 2025-05-02 | 2025-07-01 | 20
C-52-0506-PL-ME-4810 | Section Tie-in Welding | 48 | 48 | 2025-05-23 | 2025-07-24 | 2025-05-03 | 2025-07-02 | 20
C-52-0506-PL-ME-4820 | NDT (Tie-in Joint) | 48 | 48 | 2025-05-26 | 2025-07-26 | 2025-05-06 | 2025-07-04 | 20
C-52-0506-PL-ME-4830 | Holiday Testing | 48 | 48 | 2025-05-29 | 2025-07-30 | 2025-05-09 | 2025-07-08 | 20
Crossings OHPLCCOPL52464 |  | 12 | 12 | 2025-05-07 | 2025-05-21 | 2025-04-08 | 2025-04-22 | 87
Crossing Manual @ KP 138+250 (OX-13) |  | 12 | 12 | 2025-05-07 | 2025-05-21 | 2025-04-08 | 2025-04-22 | 87
C-52-0506-CMA01-1000 | Trench Excavation | 6 | 6 | 2025-05-07 | 2025-05-14 | 2025-04-08 | 2025-04-15 | 82
C-52-0506-CMA01-1010 | Bedding | 1 | 1 | 2025-05-13 | 2025-05-14 | 2025-04-14 | 2025-04-15 | 82
C-52-0506-CMA01-1020 | Lowering | 1 | 1 | 2025-05-14 | 2025-05-15 | 2025-04-15 | 2025-04-16 | 82
C-52-0506-CMA01-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-14 | 2025-05-16 | 2025-04-15 | 2025-04-17 | 82
C-52-0506-CMA01-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-15 | 2025-05-17 | 2025-04-16 | 2025-04-18 | 87
C-52-0506-CMA01-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-16 | 2025-05-19 | 2025-04-17 | 2025-04-19 | 87
C-52-0506-CMA01-1060 | Holiday Testing | 1 | 1 | 2025-05-19 | 2025-05-20 | 2025-04-19 | 2025-04-21 | 87
C-52-0506-CMA01-1070 | Padding | 1 | 1 | 2025-05-20 | 2025-05-21 | 2025-04-21 | 2025-04-22 | 87
Crossings - UG PipeCCOPL52443 |  | 48 | 48 | 2025-02-18 | 2025-05-16 | 2025-02-10 | 2025-04-17 | 91
Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) |  | 18 | 18 | 2025-04-25 | 2025-05-16 | 2025-03-21 | 2025-04-17 | 91
C-52-0506-CMA02-1000 | Trench Excavation | 12 | 12 | 2025-04-25 | 2025-05-09 | 2025-03-21 | 2025-04-10 | 82
C-52-0506-CMA02-1010 | Bedding | 1 | 1 | 2025-05-08 | 2025-05-09 | 2025-04-09 | 2025-04-10 | 86
C-52-0506-CMA02-1020 | Lowering | 1 | 1 | 2025-05-09 | 2025-05-10 | 2025-04-10 | 2025-04-11 | 86
C-52-0506-CMA02-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-09 | 2025-05-12 | 2025-04-10 | 2025-04-12 | 86
C-52-0506-CMA02-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-10 | 2025-05-13 | 2025-04-11 | 2025-04-14 | 91
C-52-0506-CMA02-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-12 | 2025-05-14 | 2025-04-12 | 2025-04-15 | 91
C-52-0506-CMA02-1060 | Holiday Testing | 1 | 1 | 2025-05-14 | 2025-05-15 | 2025-04-15 | 2025-04-16 | 91
C-52-0506-CMA02-1070 | Padding | 1 | 1 | 2025-05-15 | 2025-05-16 | 2025-04-16 | 2025-04-17 | 91
Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) |  | 18 | 18 | 2025-02-18 | 2025-03-13 | 2025-02-10 | 2025-03-02 | 121
C-52-0506-CMA03-1000 | Trench Excavation | 12 | 12 | 2025-02-18 | 2025-03-04 | 2025-02-10 | 2025-02-24 | 110
C-52-0506-CMA03-1010 | Bedding | 1 | 1 | 2025-03-02 | 2025-03-04 | 2025-02-22 | 2025-02-24 | 116
C-52-0506-CMA03-1020 | Lowering | 1 | 1 | 2025-03-04 | 2025-03-06 | 2025-02-24 | 2025-02-25 | 116
C-52-0506-CMA03-1030 | Section Tie-in Welding | 2 | 2 | 2025-03-04 | 2025-03-07 | 2025-02-24 | 2025-02-26 | 116
C-52-0506-CMA03-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-03-06 | 2025-03-08 | 2025-02-25 | 2025-02-27 | 121
C-52-0506-CMA03-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-07 | 2025-03-10 | 2025-02-26 | 2025-02-28 | 121
C-52-0506-CMA03-1060 | Holiday Testing | 1 | 1 | 2025-03-10 | 2025-03-12 | 2025-02-28 | 2025-03-01 | 121
C-52-0506-CMA03-1070 | Padding | 1 | 1 | 2025-03-12 | 2025-03-13 | 2025-03-01 | 2025-03-02 | 121
Crossings - FenceCCOPL52444 |  | 38 | 38 | 2025-02-01 | 2025-03-22 | 2025-01-24 | 2025-03-12 | 115
Crossing Manual @ KP 136+575 (FX-39) |  | 12 | 12 | 2025-02-01 | 2025-02-15 | 2025-01-24 | 2025-02-07 | 141
C-52-0506-CMA04-1000 | Trench Excavation | 6 | 6 | 2025-02-01 | 2025-02-08 | 2025-01-24 | 2025-01-31 | 110
C-52-0506-CMA04-1010 | Bedding | 1 | 1 | 2025-02-07 | 2025-02-08 | 2025-01-30 | 2025-01-31 | 136
C-52-0506-CMA04-1020 | Lowering | 1 | 1 | 2025-02-08 | 2025-02-10 | 2025-01-31 | 2025-02-01 | 136
C-52-0506-CMA04-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-08 | 2025-02-11 | 2025-01-31 | 2025-02-03 | 136
C-52-0506-CMA04-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-10 | 2025-02-12 | 2025-02-01 | 2025-02-04 | 141
C-52-0506-CMA04-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-11 | 2025-02-13 | 2025-02-03 | 2025-02-05 | 141
C-52-0506-CMA04-1060 | Holiday Testing | 1 | 1 | 2025-02-13 | 2025-02-14 | 2025-02-05 | 2025-02-06 | 141
C-52-0506-CMA04-1070 | Padding | 1 | 1 | 2025-02-14 | 2025-02-15 | 2025-02-06 | 2025-02-07 | 141
Crossing Manual @ KP 138+261 (FX-50) |  | 12 | 12 | 2025-03-04 | 2025-03-22 | 2025-02-24 | 2025-03-12 | 115
C-52-0506-CMA05-1000 | Trench Excavation | 6 | 6 | 2025-03-04 | 2025-03-13 | 2025-02-24 | 2025-03-02 | 110
C-52-0506-CMA05-1010 | Bedding | 1 | 1 | 2025-03-12 | 2025-03-13 | 2025-03-01 | 2025-03-02 | 110
C-52-0506-CMA05-1020 | Lowering | 1 | 1 | 2025-03-13 | 2025-03-15 | 2025-03-02 | 2025-03-04 | 110
C-52-0506-CMA05-1030 | Section Tie-in Welding | 2 | 2 | 2025-03-13 | 2025-03-16 | 2025-03-02 | 2025-03-06 | 110
C-52-0506-CMA05-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-03-15 | 2025-03-18 | 2025-03-04 | 2025-03-07 | 115
C-52-0506-CMA05-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-16 | 2025-03-19 | 2025-03-06 | 2025-03-08 | 115
C-52-0506-CMA05-1060 | Holiday Testing | 1 | 1 | 2025-03-19 | 2025-03-21 | 2025-03-08 | 2025-03-10 | 115
C-52-0506-CMA05-1070 | Padding | 1 | 1 | 2025-03-21 | 2025-03-22 | 2025-03-10 | 2025-03-12 | 115
Open Cut - Rig / Track RoadCCOPL52445 |  | 46 | 46 | 2025-02-13 | 2025-04-18 | 2025-04-18 | 2025-06-13 | 44
Crossing Mechanical (TX-57) |  | 19 | 19 | 2025-02-13 | 2025-03-09 | 2025-04-18 | 2025-05-10 | 71
C-52-0506-CME01-1000 | Trench Excavation | 2 | 2 | 2025-02-13 | 2025-02-15 | 2025-04-18 | 2025-04-19 | 1
C-52-0506-CME01-1010 | Bedding | 2 | 2 | 2025-02-15 | 2025-02-18 | 2025-04-21 | 2025-04-22 | 53
C-52-0506-CME01-1020 | Lowering | 2 | 2 | 2025-02-18 | 2025-02-20 | 2025-04-23 | 2025-04-24 | 53
C-52-0506-CME01-1030 | Section Tie-in Welding | 3 | 3 | 2025-02-20 | 2025-02-24 | 2025-04-25 | 2025-04-28 | 71
C-52-0506-CME01-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-02-24 | 2025-02-27 | 2025-04-29 | 2025-05-01 | 71
C-52-0506-CME01-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-02-27 | 2025-03-03 | 2025-05-02 | 2025-05-06 | 71
C-52-0506-CME01-1060 | Holiday Testing | 2 | 2 | 2025-03-03 | 2025-03-06 | 2025-05-06 | 2025-05-08 | 71
C-52-0506-CME01-1070 | Padding & Back Filling | 2 | 2 | 2025-03-06 | 2025-03-09 | 2025-05-08 | 2025-05-10 | 71
Crossing Mechanical (TX-58) |  | 19 | 19 | 2025-02-17 | 2025-03-14 | 2025-04-22 | 2025-05-14 | 68
C-52-0506-CME02-1000 | Trench Excavation | 2 | 2 | 2025-02-17 | 2025-02-19 | 2025-04-22 | 2025-04-23 | 1
C-52-0506-CME02-1010 | Bedding | 2 | 2 | 2025-02-19 | 2025-02-21 | 2025-04-24 | 2025-04-25 | 52
C-52-0506-CME02-1020 | Lowering | 2 | 2 | 2025-02-21 | 2025-02-24 | 2025-04-26 | 2025-04-28 | 52
C-52-0506-CME02-1030 | Section Tie-in Welding | 3 | 3 | 2025-02-24 | 2025-02-27 | 2025-04-29 | 2025-05-01 | 68
C-52-0506-CME02-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-02-27 | 2025-03-03 | 2025-05-02 | 2025-05-06 | 68
C-52-0506-CME02-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-03-03 | 2025-03-08 | 2025-05-06 | 2025-05-09 | 68
C-52-0506-CME02-1060 | Holiday Testing | 2 | 2 | 2025-03-08 | 2025-03-11 | 2025-05-09 | 2025-05-12 | 68
C-52-0506-CME02-1070 | Padding & Back Filling | 2 | 2 | 2025-03-11 | 2025-03-14 | 2025-05-12 | 2025-05-14 | 68
Crossing Mechanical (TX-59) |  | 19 | 19 | 2025-02-20 | 2025-03-18 | 2025-04-25 | 2025-05-17 | 65
C-52-0506-CME03-1000 | Trench Excavation | 2 | 2 | 2025-02-20 | 2025-02-22 | 2025-04-25 | 2025-04-26 | 1
C-52-0506-CME03-1010 | Bedding | 2 | 2 | 2025-02-22 | 2025-02-25 | 2025-04-28 | 2025-04-29 | 51
C-52-0506-CME03-1020 | Lowering | 2 | 2 | 2025-02-25 | 2025-02-27 | 2025-04-30 | 2025-05-01 | 51
C-52-0506-CME03-1030 | Section Tie-in Welding | 3 | 3 | 2025-02-27 | 2025-03-03 | 2025-05-02 | 2025-05-06 | 65
C-52-0506-CME03-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-03-03 | 2025-03-08 | 2025-05-06 | 2025-05-09 | 65
C-52-0506-CME03-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-03-08 | 2025-03-12 | 2025-05-09 | 2025-05-13 | 65
C-52-0506-CME03-1060 | Holiday Testing | 2 | 2 | 2025-03-12 | 2025-03-15 | 2025-05-13 | 2025-05-15 | 65
C-52-0506-CME03-1070 | Padding & Back Filling | 2 | 2 | 2025-03-15 | 2025-03-18 | 2025-05-15 | 2025-05-17 | 65
Crossing Mechanical (TX-60) |  | 19 | 19 | 2025-02-24 | 2025-03-23 | 2025-04-29 | 2025-05-21 | 62
C-52-0506-CME04-1000 | Trench Excavation | 2 | 2 | 2025-02-24 | 2025-02-26 | 2025-04-29 | 2025-04-30 | 1
C-52-0506-CME04-1010 | Bedding | 2 | 2 | 2025-02-26 | 2025-02-28 | 2025-05-01 | 2025-05-02 | 50
C-52-0506-CME04-1020 | Lowering | 2 | 2 | 2025-02-28 | 2025-03-03 | 2025-05-03 | 2025-05-06 | 50
C-52-0506-CME04-1030 | Section Tie-in Welding | 3 | 3 | 2025-03-03 | 2025-03-08 | 2025-05-06 | 2025-05-09 | 62
C-52-0506-CME04-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-03-08 | 2025-03-12 | 2025-05-09 | 2025-05-13 | 62
C-52-0506-CME04-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-03-12 | 2025-03-17 | 2025-05-13 | 2025-05-16 | 62
C-52-0506-CME04-1060 | Holiday Testing | 2 | 2 | 2025-03-17 | 2025-03-20 | 2025-05-16 | 2025-05-19 | 62
C-52-0506-CME04-1070 | Padding & Back Filling | 2 | 2 | 2025-03-20 | 2025-03-23 | 2025-05-19 | 2025-05-21 | 62
Crossing Mechanical (TX-61) |  | 19 | 19 | 2025-02-27 | 2025-03-28 | 2025-05-02 | 2025-05-24 | 59
C-52-0506-CME05-1000 | Trench Excavation | 2 | 2 | 2025-02-27 | 2025-03-01 | 2025-05-02 | 2025-05-03 | 1
C-52-0506-CME05-1010 | Bedding | 2 | 2 | 2025-03-01 | 2025-03-05 | 2025-05-05 | 2025-05-07 | 49
C-52-0506-CME05-1020 | Lowering | 2 | 2 | 2025-03-05 | 2025-03-08 | 2025-05-07 | 2025-05-09 | 49
C-52-0506-CME05-1030 | Section Tie-in Welding | 3 | 3 | 2025-03-08 | 2025-03-12 | 2025-05-09 | 2025-05-13 | 59
C-52-0506-CME05-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-03-12 | 2025-03-17 | 2025-05-13 | 2025-05-16 | 59
C-52-0506-CME05-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-03-17 | 2025-03-22 | 2025-05-16 | 2025-05-20 | 59
C-52-0506-CME05-1060 | Holiday Testing | 2 | 2 | 2025-03-22 | 2025-03-24 | 2025-05-20 | 2025-05-22 | 59
C-52-0506-CME05-1070 | Padding & Back Filling | 2 | 2 | 2025-03-24 | 2025-03-28 | 2025-05-22 | 2025-05-24 | 59
Crossing Mechanical (TX-62) |  | 19 | 19 | 2025-03-03 | 2025-04-04 | 2025-05-06 | 2025-05-28 | 56
C-52-0506-CME06-1000 | Trench Excavation | 2 | 2 | 2025-03-03 | 2025-03-06 | 2025-05-06 | 2025-05-08 | 1
C-52-0506-CME06-1010 | Bedding | 2 | 2 | 2025-03-06 | 2025-03-09 | 2025-05-08 | 2025-05-10 | 48
C-52-0506-CME06-1020 | Lowering | 2 | 2 | 2025-03-09 | 2025-03-12 | 2025-05-10 | 2025-05-13 | 48
C-52-0506-CME06-1030 | Section Tie-in Welding | 3 | 3 | 2025-03-12 | 2025-03-17 | 2025-05-13 | 2025-05-16 | 56
C-52-0506-CME06-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-03-17 | 2025-03-22 | 2025-05-16 | 2025-05-20 | 56
C-52-0506-CME06-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-03-22 | 2025-03-26 | 2025-05-20 | 2025-05-23 | 56
C-52-0506-CME06-1060 | Holiday Testing | 2 | 2 | 2025-03-26 | 2025-03-29 | 2025-05-23 | 2025-05-26 | 56
C-52-0506-CME06-1070 | Padding & Back Filling | 2 | 2 | 2025-03-29 | 2025-04-04 | 2025-05-26 | 2025-05-28 | 56
Crossing Mechanical (TX-63) |  | 19 | 19 | 2025-03-08 | 2025-04-08 | 2025-05-09 | 2025-05-31 | 53
C-52-0506-CME07-1000 | Trench Excavation | 2 | 2 | 2025-03-08 | 2025-03-11 | 2025-05-09 | 2025-05-12 | 1
C-52-0506-CME07-1010 | Bedding | 2 | 2 | 2025-03-11 | 2025-03-14 | 2025-05-12 | 2025-05-14 | 47
C-52-0506-CME07-1020 | Lowering | 2 | 2 | 2025-03-14 | 2025-03-17 | 2025-05-14 | 2025-05-16 | 47
C-52-0506-CME07-1030 | Section Tie-in Welding | 3 | 3 | 2025-03-17 | 2025-03-22 | 2025-05-16 | 2025-05-20 | 53
C-52-0506-CME07-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-03-22 | 2025-03-26 | 2025-05-20 | 2025-05-23 | 53
C-52-0506-CME07-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-03-26 | 2025-04-03 | 2025-05-23 | 2025-05-27 | 53
C-52-0506-CME07-1060 | Holiday Testing | 2 | 2 | 2025-04-03 | 2025-04-05 | 2025-05-27 | 2025-05-29 | 53
C-52-0506-CME07-1070 | Padding & Back Filling | 2 | 2 | 2025-04-05 | 2025-04-08 | 2025-05-29 | 2025-05-31 | 53
Crossing Mechanical (TX-64) |  | 19 | 19 | 2025-03-12 | 2025-04-11 | 2025-05-13 | 2025-06-04 | 50
C-52-0506-CME08-1000 | Trench Excavation | 2 | 2 | 2025-03-12 | 2025-03-15 | 2025-05-13 | 2025-05-15 | 1
C-52-0506-CME08-1010 | Bedding | 2 | 2 | 2025-03-15 | 2025-03-18 | 2025-05-15 | 2025-05-17 | 46
C-52-0506-CME08-1020 | Lowering | 2 | 2 | 2025-03-18 | 2025-03-22 | 2025-05-17 | 2025-05-20 | 46
C-52-0506-CME08-1030 | Section Tie-in Welding | 3 | 3 | 2025-03-22 | 2025-03-26 | 2025-05-20 | 2025-05-23 | 50
C-52-0506-CME08-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-03-26 | 2025-04-03 | 2025-05-23 | 2025-05-27 | 50
C-52-0506-CME08-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-04-03 | 2025-04-07 | 2025-05-27 | 2025-05-30 | 50
C-52-0506-CME08-1060 | Holiday Testing | 2 | 2 | 2025-04-07 | 2025-04-09 | 2025-05-30 | 2025-06-02 | 50
C-52-0506-CME08-1070 | Padding & Back Filling | 2 | 2 | 2025-04-09 | 2025-04-11 | 2025-06-02 | 2025-06-04 | 50
Crossing Mechanical (TX-65) |  | 19 | 19 | 2025-03-17 | 2025-04-15 | 2025-05-16 | 2025-06-10 | 47
C-52-0506-CME09-1000 | Trench Excavation | 2 | 2 | 2025-03-17 | 2025-03-20 | 2025-05-16 | 2025-05-19 | 1
C-52-0506-CME09-1010 | Bedding | 2 | 2 | 2025-03-20 | 2025-03-23 | 2025-05-19 | 2025-05-21 | 45
C-52-0506-CME09-1020 | Lowering | 2 | 2 | 2025-03-23 | 2025-03-26 | 2025-05-21 | 2025-05-23 | 45
C-52-0506-CME09-1030 | Section Tie-in Welding | 3 | 3 | 2025-03-26 | 2025-04-03 | 2025-05-23 | 2025-05-27 | 47
C-52-0506-CME09-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-04-03 | 2025-04-07 | 2025-05-27 | 2025-05-30 | 47
C-52-0506-CME09-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-04-07 | 2025-04-10 | 2025-05-30 | 2025-06-03 | 47
C-52-0506-CME09-1060 | Holiday Testing | 2 | 2 | 2025-04-10 | 2025-04-12 | 2025-06-03 | 2025-06-07 | 47
C-52-0506-CME09-1070 | Padding & Back Filling | 2 | 2 | 2025-04-12 | 2025-04-15 | 2025-06-07 | 2025-06-10 | 47
Crossing Mechanical (TX-66) |  | 19 | 19 | 2025-03-22 | 2025-04-18 | 2025-05-20 | 2025-06-13 | 44
C-52-0506-CME10-1000 | Trench Excavation | 2 | 2 | 2025-03-22 | 2025-03-24 | 2025-05-20 | 2025-05-22 | 1
C-52-0506-CME10-1010 | Bedding | 2 | 2 | 2025-03-24 | 2025-03-28 | 2025-05-22 | 2025-05-24 | 44
C-52-0506-CME10-1020 | Lowering | 2 | 2 | 2025-03-28 | 2025-04-03 | 2025-05-24 | 2025-05-27 | 44
C-52-0506-CME10-1030 | Section Tie-in Welding | 3 | 3 | 2025-04-03 | 2025-04-07 | 2025-05-27 | 2025-05-30 | 44
C-52-0506-CME10-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-04-07 | 2025-04-10 | 2025-05-30 | 2025-06-03 | 44
C-52-0506-CME10-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-04-10 | 2025-04-14 | 2025-06-03 | 2025-06-09 | 44
C-52-0506-CME10-1060 | Holiday Testing | 2 | 2 | 2025-04-14 | 2025-04-16 | 2025-06-09 | 2025-06-11 | 44
C-52-0506-CME10-1070 | Padding & Back Filling | 2 | 2 | 2025-04-16 | 2025-04-18 | 2025-06-11 | 2025-06-13 | 44
Crossings - UG CableCCOPL52449 |  | 68 | 68 | 2025-01-23 | 2025-05-14 | 2025-01-15 | 2025-04-15 | 93
Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) |  | 14 | 14 | 2025-01-23 | 2025-02-08 | 2025-01-15 | 2025-01-31 | 147
C-52-0506-CMA06-1000 | Trench Excavation | 8 | 8 | 2025-01-23 | 2025-02-01 | 2025-01-15 | 2025-01-24 | 110
C-52-0506-CMA06-1010 | Bedding | 1 | 1 | 2025-01-31 | 2025-02-01 | 2025-01-23 | 2025-01-24 | 142
C-52-0506-CMA06-1020 | Lowering | 1 | 1 | 2025-02-01 | 2025-02-03 | 2025-01-24 | 2025-01-25 | 142
C-52-0506-CMA06-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-01 | 2025-02-04 | 2025-01-24 | 2025-01-27 | 142
C-52-0506-CMA06-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-03 | 2025-02-05 | 2025-01-25 | 2025-01-28 | 147
C-52-0506-CMA06-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-04 | 2025-02-06 | 2025-01-27 | 2025-01-29 | 147
C-52-0506-CMA06-1060 | Holiday Testing | 1 | 1 | 2025-02-06 | 2025-02-07 | 2025-01-29 | 2025-01-30 | 147
C-52-0506-CMA06-1070 | Padding | 1 | 1 | 2025-02-07 | 2025-02-08 | 2025-01-30 | 2025-01-31 | 147
Crossing Manual @ KP 131+250, (CX-X2) |  | 14 | 14 | 2025-04-16 | 2025-05-02 | 2025-03-08 | 2025-04-03 | 103
C-52-0506-CMA07-1000 | Trench Excavation | 8 | 8 | 2025-04-16 | 2025-04-25 | 2025-03-08 | 2025-03-21 | 82
C-52-0506-CMA07-1010 | Bedding | 1 | 1 | 2025-04-24 | 2025-04-25 | 2025-03-19 | 2025-03-21 | 98
C-52-0506-CMA07-1020 | Lowering | 1 | 1 | 2025-04-25 | 2025-04-26 | 2025-03-21 | 2025-03-22 | 98
C-52-0506-CMA07-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-25 | 2025-04-28 | 2025-03-21 | 2025-03-24 | 98
C-52-0506-CMA07-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-26 | 2025-04-29 | 2025-03-22 | 2025-03-25 | 103
C-52-0506-CMA07-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-28 | 2025-04-30 | 2025-03-24 | 2025-03-27 | 103
C-52-0506-CMA07-1060 | Holiday Testing | 1 | 1 | 2025-04-30 | 2025-05-01 | 2025-03-27 | 2025-03-29 | 103
C-52-0506-CMA07-1070 | Padding | 1 | 1 | 2025-05-01 | 2025-05-02 | 2025-03-29 | 2025-04-03 | 103
Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) |  | 14 | 14 | 2025-02-08 | 2025-02-25 | 2025-01-31 | 2025-02-17 | 133
C-52-0506-CMA08-1000 | Trench Excavation | 8 | 8 | 2025-02-08 | 2025-02-18 | 2025-01-31 | 2025-02-10 | 110
C-52-0506-CMA08-1010 | Bedding | 1 | 1 | 2025-02-17 | 2025-02-18 | 2025-02-08 | 2025-02-10 | 128
C-52-0506-CMA08-1020 | Lowering | 1 | 1 | 2025-02-18 | 2025-02-19 | 2025-02-10 | 2025-02-11 | 128
C-52-0506-CMA08-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-18 | 2025-02-20 | 2025-02-10 | 2025-02-12 | 128
C-52-0506-CMA08-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-19 | 2025-02-21 | 2025-02-11 | 2025-02-13 | 133
C-52-0506-CMA08-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-20 | 2025-02-22 | 2025-02-12 | 2025-02-14 | 133
C-52-0506-CMA08-1060 | Holiday Testing | 1 | 1 | 2025-02-22 | 2025-02-24 | 2025-02-14 | 2025-02-15 | 133
C-52-0506-CMA08-1070 | Padding | 1 | 1 | 2025-02-24 | 2025-02-25 | 2025-02-15 | 2025-02-17 | 133
Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) |  | 16 | 16 | 2025-04-25 | 2025-05-14 | 2025-03-21 | 2025-04-15 | 93
C-52-0506-CMA09-1000 | Trench Excavation | 10 | 10 | 2025-04-25 | 2025-05-07 | 2025-03-21 | 2025-04-08 | 82
C-52-0506-CMA09-1010 | Bedding | 1 | 1 | 2025-05-06 | 2025-05-07 | 2025-04-07 | 2025-04-08 | 88
C-52-0506-CMA09-1020 | Lowering | 1 | 1 | 2025-05-07 | 2025-05-08 | 2025-04-08 | 2025-04-09 | 88
C-52-0506-CMA09-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-07 | 2025-05-09 | 2025-04-08 | 2025-04-10 | 88
C-52-0506-CMA09-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-08 | 2025-05-10 | 2025-04-09 | 2025-04-11 | 93
C-52-0506-CMA09-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-09 | 2025-05-12 | 2025-04-10 | 2025-04-12 | 93
C-52-0506-CMA09-1060 | Holiday Testing | 1 | 1 | 2025-05-12 | 2025-05-13 | 2025-04-12 | 2025-04-14 | 93
C-52-0506-CMA09-1070 | Padding | 1 | 1 | 2025-05-13 | 2025-05-14 | 2025-04-14 | 2025-04-15 | 93
CP Works TemporaryCCOP52EL46 |  | 51 | 51 | 2025-05-30 | 2025-08-04 | 2025-05-10 | 2025-07-12 | 81
C-52-0506-PL-CA-5200 | Installation of CP Test Post | 48 | 48 | 2025-05-30 | 2025-07-31 | 2025-05-10 | 2025-07-09 | 82
C-52-0506-PL-CA-5210 | Glanding & Termination of Temp. CP S/m | 2 | 2 | 2025-08-01 | 2025-08-04 | 2025-07-10 | 2025-07-12 | 81
Test Stations & Anode BedsCCOP52EL45 |  | 48 | 48 | 2025-05-29 | 2025-07-30 | 2025-05-09 | 2025-07-08 | 24
C-52-0506-PL-CA-5600 | Installation of Temp. Anode | 48 | 48 | 2025-05-29 | 2025-07-30 | 2025-05-09 | 2025-07-08 | 24
PaddingCCOPL52442 |  | 48 | 48 | 2025-06-03 | 2025-08-04 | 2025-05-14 | 2025-07-12 | 20
C-52-0506-PL-CI-6000 | Padding | 48 | 48 | 2025-06-03 | 2025-08-04 | 2025-05-14 | 2025-07-12 | 20
BackfillingCCOPL52450 |  | 48 | 48 | 2025-06-13 | 2025-08-12 | 2025-05-22 | 2025-07-21 | 20
C-52-0506-PL-CI-6400 | Backfilling | 48 | 48 | 2025-06-13 | 2025-08-12 | 2025-05-22 | 2025-07-21 | 20
BermingCCOPL52451 |  | 52 | 52 | 2025-06-23 | 2025-08-26 | 2025-05-31 | 2025-08-04 | 69
C-52-0506-PL-CI-6800 | Gatch Laying & Levelling | 48 | 48 | 2025-06-23 | 2025-08-21 | 2025-05-31 | 2025-07-30 | 20
C-52-0506-PL-CI-6810 | Gatch Compaction | 48 | 48 | 2025-06-25 | 2025-08-23 | 2025-06-03 | 2025-08-01 | 20
C-52-0506-PL-CI-7800 | Installation of Marker Post/Sign Board | 48 | 48 | 2025-06-26 | 2025-08-25 | 2025-06-04 | 2025-08-02 | 69
C-52-0506-PL-CI-7810 | Installation of Crash Barriers (If any) | 48 | 48 | 2025-06-28 | 2025-08-26 | 2025-06-07 | 2025-08-04 | 69
NDRC by Micro Tunneling Method |  | 22 | 22 | 2025-03-26 | 2025-04-25 | 2025-05-23 | 2025-06-20 | 31
NDRC-25A (incl Hydrotest) @ CH 131+400 - 131+500 (Open Cut*) |  | 19 | 19 | 2025-03-26 | 2025-04-22 | 2025-05-23 | 2025-06-17 | 34
Entry & Exit Pit ConstructionCCOPL52920 |  | 2 | 2 | 2025-03-26 | 2025-03-29 | 2025-05-23 | 2025-05-26 | 1
C-52-0506-CME25-2000 | Trench Excavation | 2 | 2 | 2025-03-26 | 2025-03-29 | 2025-05-23 | 2025-05-26 | 1
Tunneling & Jack UpCCOPL57022 |  | 2 | 2 | 2025-03-29 | 2025-04-04 | 2025-05-26 | 2025-05-28 | 34
C-52-0506-CME25-2010 | Bedding | 2 | 2 | 2025-03-29 | 2025-04-04 | 2025-05-26 | 2025-05-28 | 34
Pipe Lowering, Welding, NDT & CoatingCCOPL57032 |  | 11 | 11 | 2025-04-04 | 2025-04-17 | 2025-05-28 | 2025-06-12 | 34
C-52-0506-CME25-2020 | Lowering | 2 | 2 | 2025-04-04 | 2025-04-07 | 2025-05-28 | 2025-05-30 | 34
C-52-0506-CME25-2030 | Section Tie-in Welding | 3 | 3 | 2025-04-07 | 2025-04-10 | 2025-05-30 | 2025-06-03 | 34
C-52-0506-CME25-2040 | NDT (Tie-in Joint) | 3 | 3 | 2025-04-10 | 2025-04-14 | 2025-06-03 | 2025-06-09 | 34
C-52-0506-CME25-2050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-04-14 | 2025-04-17 | 2025-06-09 | 2025-06-12 | 34
HydrotestingCCOPL57042 |  | 2 | 2 | 2025-04-17 | 2025-04-19 | 2025-06-12 | 2025-06-14 | 34
C-52-0506-CME25-2060 | Holiday Testing | 2 | 2 | 2025-04-17 | 2025-04-19 | 2025-06-12 | 2025-06-14 | 34
Re-Instatement of Entry & Exit PitCCOPL57052 |  | 2 | 2 | 2025-04-19 | 2025-04-22 | 2025-06-14 | 2025-06-17 | 34
C-52-0506-CME25-2070 | Padding & Back Filling | 2 | 2 | 2025-04-19 | 2025-04-22 | 2025-06-14 | 2025-06-17 | 34
NDRC-28 (incl Hydrotest) @ CH 138+780 - 138+835 (Open Cut*) |  | 19 | 19 | 2025-04-03 | 2025-04-25 | 2025-05-27 | 2025-06-20 | 31
Entry & Exit Pit ConstructionCCOPL56972 |  | 2 | 2 | 2025-04-03 | 2025-04-05 | 2025-05-27 | 2025-05-29 | 1
C-52-0506-CME28-1080 | Trench Excavation | 2 | 2 | 2025-04-03 | 2025-04-05 | 2025-05-27 | 2025-05-29 | 1
Tunneling & Jack UpCCOPL56982 |  | 2 | 2 | 2025-04-05 | 2025-04-08 | 2025-05-29 | 2025-05-31 | 31
C-52-0506-CME28-1090 | Bedding | 2 | 2 | 2025-04-05 | 2025-04-08 | 2025-05-29 | 2025-05-31 | 31
Pipe Lowering, Welding, NDT & CoatingCCOPL56992 |  | 11 | 11 | 2025-04-08 | 2025-04-21 | 2025-05-31 | 2025-06-16 | 31
C-52-0506-CME28-1100 | Lowering | 2 | 2 | 2025-04-08 | 2025-04-10 | 2025-05-31 | 2025-06-03 | 31
C-52-0506-CME28-1110 | Section Tie-in Welding | 3 | 3 | 2025-04-10 | 2025-04-14 | 2025-06-03 | 2025-06-09 | 31
C-52-0506-CME28-1120 | NDT (Tie-in Joint) | 3 | 3 | 2025-04-14 | 2025-04-17 | 2025-06-09 | 2025-06-12 | 31
C-52-0506-CME28-1130 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-04-17 | 2025-04-21 | 2025-06-12 | 2025-06-16 | 31
HydrotestingCCOPL57002 |  | 2 | 2 | 2025-04-21 | 2025-04-23 | 2025-06-16 | 2025-06-18 | 31
C-52-0506-CME28-1140 | Holiday Testing | 2 | 2 | 2025-04-21 | 2025-04-23 | 2025-06-16 | 2025-06-18 | 31
Re-Instatement of Entry & Exit PitCCOPL57012 |  | 2 | 2 | 2025-04-23 | 2025-04-25 | 2025-06-18 | 2025-06-20 | 31
C-52-0506-CME28-1150 | Padding & Back Filling | 2 | 2 | 2025-04-23 | 2025-04-25 | 2025-06-18 | 2025-06-20 | 31
NDRC by Micro Tunnelling Method |  | 155 | 155 | 2024-10-05 | 2025-03-29 | 2024-12-25 | 2025-07-09 | 23
Micro Tunnelling @ CH 137+450 - 137+706 (NDRC-27) |  | 155 | 155 | 2024-10-05 | 2025-03-29 | 2024-12-25 | 2025-07-09 | 23
Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 |  | 136 | 136 | 2024-10-05 | 2025-02-28 | 2024-12-25 | 2025-06-16 | 23
C-52-0506-CNH27-1000 | Sheet Piling for Driving & Receiving Pit | 16 | 16 | 2024-10-05 | 2024-11-02 | 2024-12-25 | 2025-01-14 | 23
C-52-0506-CNH27-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-11-04 | 2024-11-07 | 2025-01-14 | 2025-01-18 | 23
C-52-0506-CNH27-1010 | Driving & Receiving Pit Excavation | 14 | 14 | 2024-10-30 | 2024-11-14 | 2025-01-14 | 2025-01-30 | 23
C-52-0506-CNH27-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 10 | 10 | 2024-11-08 | 2024-11-19 | 2025-01-18 | 2025-01-30 | 23
C-52-0506-CNH27-1040 | Floor Blinding & French Drain in Driving Pit | 6 | 6 | 2024-11-20 | 2024-11-26 | 2025-01-30 | 2025-02-06 | 23
C-52-0506-CNH27-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 6 | 6 | 2024-11-27 | 2024-12-05 | 2025-02-06 | 2025-02-13 | 23
C-52-0506-CNH27-1060 | Construction of Exit Wall with Ring | 6 | 6 | 2024-12-07 | 2024-12-13 | 2025-02-14 | 2025-02-21 | 23
C-52-0506-CNH27-1070 | Lowering & Welding of Carrier Pipe | 40 | 40 | 2025-01-16 | 2025-02-13 | 2025-04-11 | 2025-05-29 | 23
C-52-0506-CNH27-1080 | NDT, Coating & Holiday Inspection of Carrier Pipe | 40 | 40 | 2025-01-17 | 2025-02-17 | 2025-04-12 | 2025-05-30 | 23
C-52-0506-CNH27-1090 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 12 | 12 | 2025-02-18 | 2025-02-28 | 2025-05-30 | 2025-06-16 | 23
Tunneling & Jack UpCCOPL58182 |  | 92 | 92 | 2024-12-14 | 2025-03-08 | 2025-02-21 | 2025-06-21 | 23
C-52-0506-CNH27-1200 | Jacking of MTBM & RC Sleeves | 30 | 30 | 2024-12-14 | 2025-01-10 | 2025-02-21 | 2025-04-07 | 23
C-52-0506-CNH27-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2025-01-11 | 2025-01-15 | 2025-04-07 | 2025-04-11 | 23
C-52-0506-CNH27-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-03-01 | 2025-03-08 | 2025-06-16 | 2025-06-21 | 23
Re-Instatement of Entry & Exit PitCCOPL58192 |  | 14 | 14 | 2025-03-08 | 2025-03-29 | 2025-06-21 | 2025-07-09 | 23
C-52-0506-CNH27-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-03-08 | 2025-03-29 | 2025-06-21 | 2025-07-09 | 23
Cathodic Protection |  | 72 | 72 | 2025-03-16 | 2025-08-12 | 2025-04-23 | 2025-07-21 | 81
Civil Works |  | 48 | 48 | 2025-03-21 | 2025-05-22 | 2025-04-24 | 2025-06-23 | 95
Backfilling & Reinstatement for CP (for Crossings)CCOP52CS35 |  | 48 | 48 | 2025-03-21 | 2025-05-22 | 2025-04-24 | 2025-06-23 | 95
C-52-0506-PIPEL-5260 | Backfilling & Reinstatement for CP (for Crossings) | 48 | 48 | 2025-03-21 | 2025-05-22 | 2025-04-24 | 2025-06-23 | 95
CP Works |  | 72 | 72 | 2025-03-16 | 2025-08-12 | 2025-04-23 | 2025-07-21 | 81
CP Works (for Crossings)CCOP52EL51 |  | 72 | 72 | 2025-03-16 | 2025-08-12 | 2025-04-23 | 2025-07-21 | 81
C-52-0506-PL-CA-5220 | Installation of Test Post for Crossing | 48 | 48 | 2025-03-16 | 2025-05-21 | 2025-04-23 | 2025-06-21 | 95
C-52-0506-PL-CA-5230 | Installation of CP JB's | 48 | 48 | 2025-03-16 | 2025-05-21 | 2025-04-23 | 2025-06-21 | 96
C-52-0506-PL-CA-5240 | Installation of CP TR | 48 | 48 | 2025-03-18 | 2025-05-22 | 2025-04-24 | 2025-06-23 | 95
C-52-0506-PL-CA-5250 | CIP/DCVG Survey | 7 | 7 | 2025-08-04 | 2025-08-12 | 2025-07-12 | 2025-07-21 | 81
Telecommunication Works |  | 51 | 51 | 2025-06-07 | 2025-08-09 | 2025-05-16 | 2025-07-18 | 83
Telecom Works along PipelineCCOP52IC35 |  | 51 | 51 | 2025-06-07 | 2025-08-09 | 2025-05-16 | 2025-07-18 | 83
C-52-0506-PL-TE-8200 | FO - Cable Pulling/ Laying | 48 | 48 | 2025-06-07 | 2025-08-06 | 2025-05-16 | 2025-07-15 | 20
C-52-0506-PL-TE-8210 | Termination/Splicing @ BVS | 3 | 3 | 2025-08-06 | 2025-08-09 | 2025-07-15 | 2025-07-18 | 83
52"x22.5 Km Pipeline from BVS-06 to Sweihan CRS at KP 161 |  | 262 | 262 | 2024-08-05 | 2025-10-06 | 2024-10-28 | 2025-09-17 | 39
52"x 22.5 Km Pipeline from BVS-06 to Sweihan CRS at KP 161 |  | 262 | 262 | 2024-08-05 | 2025-10-06 | 2024-10-28 | 2025-09-17 | 39
Main Pipeline |  | 262 | 262 | 2024-08-05 | 2025-10-06 | 2024-10-28 | 2025-09-17 | 39
ROW Access RoadCCOPL52468 |  | 35 | 35 | 2024-08-05 | 2024-09-14 | 2024-10-28 | 2024-12-10 | 81
C-52-06CR-PL-CI-1800 | Sabka ROW/Grading | 35 | 35 | 2024-08-05 | 2024-09-14 | 2024-10-28 | 2024-12-10 | 81
Cut & Fill in Sandy AreaCCOPL52494 |  | 28 | 28 | 2024-10-10 | 2024-11-12 | 2024-12-18 | 2025-01-21 | 96
C-52-06CR-PL-CI-1400 | Cut & Fill (@ Non-Sabkha) | 28 | 28 | 2024-10-10 | 2024-11-12 | 2024-12-18 | 2025-01-21 | 96
Sabkha PadCCOPL52489 |  | 35 | 35 | 2024-11-07 | 2024-12-20 | 2024-12-10 | 2025-01-21 | 81
C-52-06CR-PL-CI-2000 | Sabka Gatch Laying (Including ROW) - Layer 1 | 14 | 14 | 2024-11-07 | 2024-11-23 | 2024-12-10 | 2024-12-26 | 81
C-52-06CR-PL-CI-2200 | Sabka Gatch Compaction (Including ROW) - Layer 1 | 14 | 14 | 2024-11-11 | 2024-11-27 | 2024-12-13 | 2024-12-30 | 81
C-52-06CR-PL-CI-2010 | Sabka Gatch Laying - Layer 2 | 14 | 14 | 2024-11-14 | 2024-11-30 | 2024-12-17 | 2025-01-03 | 81
C-52-06CR-PL-CI-2210 | Sabka Gatch Compaction - Layer 2 | 14 | 14 | 2024-11-18 | 2024-12-06 | 2024-12-20 | 2025-01-07 | 81
C-52-06CR-PL-CI-2020 | Sabka Gatch Laying - Layer 3 | 14 | 14 | 2024-11-21 | 2024-12-10 | 2024-12-24 | 2025-01-10 | 81
C-52-06CR-PL-CI-2220 | Sabka Gatch Compaction - Layer 3 | 14 | 14 | 2024-11-25 | 2024-12-13 | 2024-12-27 | 2025-01-14 | 81
C-52-06CR-PL-CI-2030 | Sabka Gatch Laying - Layer 4 | 14 | 14 | 2024-11-28 | 2024-12-17 | 2024-12-31 | 2025-01-17 | 81
C-52-06CR-PL-CI-2230 | Sabka Gatch Compaction - Layer 4 | 14 | 14 | 2024-12-04 | 2024-12-20 | 2025-01-04 | 2025-01-21 | 81
Excavation (incl Bedding)CCOPL52483 |  | 31 | 31 | 2025-07-11 | 2025-08-29 | 2025-06-17 | 2025-07-24 | 0
C-52-06CR-PL-CI-2400 | Trench Excavation | 30 | 30 | 2025-07-11 | 2025-08-28 | 2025-06-17 | 2025-07-23 | 0
C-52-06CR-PL-CI-2410 | Bedding | 30 | 30 | 2025-07-12 | 2025-08-29 | 2025-06-18 | 2025-07-24 | 0
Pipe StringingCCOPL52469 |  | 24 | 24 | 2025-02-24 | 2025-03-29 | 2025-04-17 | 2025-05-15 | 7
C-52-06CR-PL-ME-2800 | Stringing (BVS-06 to SW CRS) | 24 | 24 | 2025-02-24 | 2025-03-29 | 2025-04-17 | 2025-05-15 | 7
Automatic WeldingCCOPL52476 |  | 30 | 30 | 2025-07-09 | 2025-08-26 | 2025-06-14 | 2025-07-21 | 0
C-52-06CR-PL-ME-3600 | Automatic Welding | 30 | 30 | 2025-07-09 | 2025-08-26 | 2025-06-14 | 2025-07-21 | 0
NDT TestCCOPL52491 |  | 30 | 30 | 2025-07-10 | 2025-08-27 | 2025-06-16 | 2025-07-22 | 4
C-52-06CR-PL-ME-4000 | NDT | 30 | 30 | 2025-07-10 | 2025-08-27 | 2025-06-16 | 2025-07-22 | 4
Ext. Joint CoatingCCOPL52474 |  | 38 | 38 | 2025-07-11 | 2025-09-02 | 2025-06-17 | 2025-08-01 | 0
C-52-06CR-PL-ME-4400 | Ext. Joint Coating | 30 | 30 | 2025-07-11 | 2025-08-28 | 2025-06-17 | 2025-07-23 | 4
C-52-06CR-PL-ME-4410 | Ext. Joint Coating (Tie-in Joint) | 30 | 30 | 2025-07-17 | 2025-09-02 | 2025-06-26 | 2025-08-01 | 0
Cold BendsCCOPL52475 |  | 30 | 30 | 2025-07-15 | 2025-08-30 | 2025-06-24 | 2025-07-30 | 0
C-52-06CR-PL-ME-3200 | Cold Bends | 30 | 30 | 2025-07-15 | 2025-08-30 | 2025-06-24 | 2025-07-30 | 0
Pipe Lowering & Tie-in / NDTCCOPL52484 |  | 34 | 34 | 2025-07-14 | 2025-09-03 | 2025-06-23 | 2025-08-02 | 0
C-52-06CR-PL-ME-4800 | Lowering | 30 | 30 | 2025-07-14 | 2025-08-29 | 2025-06-23 | 2025-07-29 | 0
C-52-06CR-PL-ME-4810 | Section Tie-in Welding | 30 | 30 | 2025-07-15 | 2025-08-30 | 2025-06-24 | 2025-07-30 | 0
C-52-06CR-PL-ME-4820 | NDT (Tie-in Joint) | 30 | 30 | 2025-07-16 | 2025-09-01 | 2025-06-25 | 2025-07-31 | 0
C-52-06CR-PL-ME-4830 | Holiday Testing | 30 | 30 | 2025-07-18 | 2025-09-03 | 2025-06-28 | 2025-08-02 | 0
Crossings - UG PipeCCOPL52471 |  | 31 | 31 | 2025-03-25 | 2025-05-06 | 2025-05-12 | 2025-06-19 | 48
Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) |  | 31 | 31 | 2025-03-25 | 2025-05-06 | 2025-05-12 | 2025-06-19 | 48
C-52-06CR-CMA01-0970 | Excavation (Manual-Trial Pit) | 12 | 12 | 2025-03-25 | 2025-04-12 | 2025-05-12 | 2025-05-26 | 7
C-52-06CR-CMA01-980 | Sabkha Gatch Laying | 5 | 5 | 2025-04-14 | 2025-04-18 | 2025-05-26 | 2025-05-31 | 34
C-52-06CR-CMA01-990 | Sabka Gatch Compaction | 5 | 5 | 2025-04-15 | 2025-04-19 | 2025-05-27 | 2025-06-02 | 34
C-52-06CR-CMA01-1000 | Trench Excavation | 2 | 2 | 2025-04-21 | 2025-04-22 | 2025-06-02 | 2025-06-04 | 34
C-52-06CR-CMA01-1010 | Bedding | 1 | 1 | 2025-04-22 | 2025-04-22 | 2025-06-03 | 2025-06-04 | 34
C-52-06CR-CMA01-1020 | Lowering | 1 | 1 | 2025-04-29 | 2025-04-29 | 2025-06-12 | 2025-06-13 | 29
C-52-06CR-CMA01-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-29 | 2025-04-30 | 2025-06-12 | 2025-06-14 | 37
C-52-06CR-CMA01-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-30 | 2025-05-01 | 2025-06-13 | 2025-06-16 | 48
C-52-06CR-CMA01-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-01 | 2025-05-02 | 2025-06-14 | 2025-06-17 | 48
C-52-06CR-CMA01-1060 | Holiday Testing | 1 | 1 | 2025-05-03 | 2025-05-03 | 2025-06-17 | 2025-06-18 | 48
C-52-06CR-CMA01-1070 | Padding | 1 | 1 | 2025-05-05 | 2025-05-06 | 2025-06-18 | 2025-06-19 | 48
Crossings - FenceCCOPL52472 |  | 55 | 55 | 2025-04-07 | 2025-06-12 | 2025-05-19 | 2025-07-25 | 18
Crossing Manual @ KP 150+043 (FX-53) |  | 33 | 33 | 2025-04-07 | 2025-05-15 | 2025-05-19 | 2025-06-30 | 40
C-52-06CR-CMA02-1000 | Trench Excavation | 6 | 6 | 2025-04-07 | 2025-04-12 | 2025-05-19 | 2025-05-26 | 7
C-52-06CR-CMA02-1010 | Bedding | 1 | 1 | 2025-04-12 | 2025-04-12 | 2025-05-24 | 2025-05-26 | 44
C-52-06CR-CMA02-1020 | Lowering | 1 | 1 | 2025-05-08 | 2025-05-09 | 2025-06-21 | 2025-06-23 | 23
C-52-06CR-CMA02-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-08 | 2025-05-10 | 2025-06-21 | 2025-06-24 | 29
C-52-06CR-CMA02-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-09 | 2025-05-12 | 2025-06-23 | 2025-06-25 | 40
C-52-06CR-CMA02-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-10 | 2025-05-13 | 2025-06-24 | 2025-06-26 | 40
C-52-06CR-CMA02-1060 | Holiday Testing | 1 | 1 | 2025-05-13 | 2025-05-14 | 2025-06-26 | 2025-06-28 | 40
C-52-06CR-CMA02-1070 | Padding | 1 | 1 | 2025-05-14 | 2025-05-15 | 2025-06-28 | 2025-06-30 | 40
Crossing Manual @ KP 150+322 (FX-54) |  | 12 | 12 | 2025-05-07 | 2025-05-21 | 2025-06-20 | 2025-07-05 | 35
C-52-06CR-CMA03-1000 | Trench Excavation | 6 | 6 | 2025-05-07 | 2025-05-14 | 2025-06-20 | 2025-06-28 | 7
C-52-06CR-CMA03-1010 | Bedding | 1 | 1 | 2025-05-13 | 2025-05-14 | 2025-06-26 | 2025-06-28 | 19
C-52-06CR-CMA03-1020 | Lowering | 1 | 1 | 2025-05-14 | 2025-05-15 | 2025-06-28 | 2025-06-30 | 19
C-52-06CR-CMA03-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-14 | 2025-05-16 | 2025-06-28 | 2025-07-01 | 24
C-52-06CR-CMA03-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-15 | 2025-05-17 | 2025-06-30 | 2025-07-02 | 35
C-52-06CR-CMA03-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-16 | 2025-05-19 | 2025-07-01 | 2025-07-03 | 35
C-52-06CR-CMA03-1060 | Holiday Testing | 1 | 1 | 2025-05-19 | 2025-05-20 | 2025-07-03 | 2025-07-04 | 35
C-52-06CR-CMA03-1070 | Padding | 1 | 1 | 2025-05-20 | 2025-05-21 | 2025-07-04 | 2025-07-05 | 35
Crossing Manual @ KP 159+862 (PX-40) |  | 41 | 41 | 2025-04-21 | 2025-06-10 | 2025-06-02 | 2025-07-23 | 20
C-52-06CR-CMA04-1000 | Trench Excavation | 8 | 8 | 2025-04-21 | 2025-04-29 | 2025-06-02 | 2025-06-13 | 24
C-52-06CR-CMA04-1010 | Bedding | 1 | 1 | 2025-04-29 | 2025-04-29 | 2025-06-12 | 2025-06-13 | 34
C-52-06CR-CMA04-1020 | Lowering | 1 | 1 | 2025-05-31 | 2025-06-02 | 2025-07-16 | 2025-07-17 | 7
C-52-06CR-CMA04-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-31 | 2025-06-03 | 2025-07-16 | 2025-07-18 | 9
C-52-06CR-CMA04-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-06-02 | 2025-06-04 | 2025-07-17 | 2025-07-19 | 20
C-52-06CR-CMA04-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-06-03 | 2025-06-07 | 2025-07-18 | 2025-07-21 | 20
C-52-06CR-CMA04-1060 | Holiday Testing | 1 | 1 | 2025-06-07 | 2025-06-09 | 2025-07-21 | 2025-07-22 | 20
C-52-06CR-CMA04-1070 | Padding | 1 | 1 | 2025-06-09 | 2025-06-10 | 2025-07-22 | 2025-07-23 | 20
Crossing Manual @ KP 160+009 (FX-55) |  | 22 | 22 | 2025-05-14 | 2025-06-11 | 2025-06-28 | 2025-07-24 | 19
C-52-06CR-CMA05-1000 | Trench Excavation | 6 | 6 | 2025-05-14 | 2025-05-21 | 2025-06-28 | 2025-07-05 | 9
C-52-06CR-CMA05-1010 | Bedding | 1 | 1 | 2025-05-20 | 2025-05-21 | 2025-07-04 | 2025-07-05 | 17
C-52-06CR-CMA05-1020 | Lowering | 1 | 1 | 2025-06-02 | 2025-06-03 | 2025-07-17 | 2025-07-18 | 7
C-52-06CR-CMA05-1030 | Section Tie-in Welding | 2 | 2 | 2025-06-02 | 2025-06-04 | 2025-07-17 | 2025-07-19 | 8
C-52-06CR-CMA05-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-06-03 | 2025-06-07 | 2025-07-18 | 2025-07-21 | 19
C-52-06CR-CMA05-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-06-04 | 2025-06-09 | 2025-07-19 | 2025-07-22 | 19
C-52-06CR-CMA05-1060 | Holiday Testing | 1 | 1 | 2025-06-09 | 2025-06-10 | 2025-07-22 | 2025-07-23 | 19
C-52-06CR-CMA05-1070 | Padding | 1 | 1 | 2025-06-10 | 2025-06-11 | 2025-07-23 | 2025-07-24 | 19
Crossing Manual @ KP 160+073 (FX-56) |  | 35 | 35 | 2025-04-30 | 2025-06-12 | 2025-06-13 | 2025-07-25 | 18
C-52-06CR-CMA06-1000 | Trench Excavation | 6 | 6 | 2025-04-30 | 2025-05-07 | 2025-06-13 | 2025-06-20 | 24
C-52-06CR-CMA06-1010 | Bedding | 1 | 1 | 2025-05-06 | 2025-05-07 | 2025-06-19 | 2025-06-20 | 30
C-52-06CR-CMA06-1020 | Lowering | 1 | 1 | 2025-06-03 | 2025-06-04 | 2025-07-18 | 2025-07-19 | 7
C-52-06CR-CMA06-1030 | Section Tie-in Welding | 2 | 2 | 2025-06-03 | 2025-06-07 | 2025-07-18 | 2025-07-21 | 7
C-52-06CR-CMA06-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-06-04 | 2025-06-09 | 2025-07-19 | 2025-07-22 | 18
C-52-06CR-CMA06-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-06-07 | 2025-06-10 | 2025-07-21 | 2025-07-23 | 18
C-52-06CR-CMA06-1060 | Holiday Testing | 1 | 1 | 2025-06-10 | 2025-06-11 | 2025-07-23 | 2025-07-24 | 18
C-52-06CR-CMA06-1070 | Padding | 1 | 1 | 2025-06-11 | 2025-06-12 | 2025-07-24 | 2025-07-25 | 18
Crossing Manual @ KP 160+851 (FX-60) |  | 27 | 27 | 2025-05-07 | 2025-06-10 | 2025-06-20 | 2025-07-23 | 20
C-52-06CR-CMA07-1000 | Trench Excavation | 6 | 6 | 2025-05-07 | 2025-05-14 | 2025-06-20 | 2025-06-28 | 24
C-52-06CR-CMA07-1010 | Bedding | 1 | 1 | 2025-05-13 | 2025-05-14 | 2025-06-26 | 2025-06-28 | 24
C-52-06CR-CMA07-1020 | Lowering | 1 | 1 | 2025-05-31 | 2025-06-02 | 2025-07-16 | 2025-07-17 | 9
C-52-06CR-CMA07-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-31 | 2025-06-03 | 2025-07-16 | 2025-07-18 | 9
C-52-06CR-CMA07-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-06-02 | 2025-06-04 | 2025-07-17 | 2025-07-19 | 20
C-52-06CR-CMA07-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-06-03 | 2025-06-07 | 2025-07-18 | 2025-07-21 | 20
C-52-06CR-CMA07-1060 | Holiday Testing | 1 | 1 | 2025-06-07 | 2025-06-09 | 2025-07-21 | 2025-07-22 | 20
C-52-06CR-CMA07-1070 | Padding | 1 | 1 | 2025-06-09 | 2025-06-10 | 2025-07-22 | 2025-07-23 | 20
Open Cut - Rig / Track RoadCCOPL52473 |  | 57 | 57 | 2025-04-07 | 2025-06-16 | 2025-05-30 | 2025-08-08 | 6
Crossing Mechanical (TX-73) |  | 19 | 19 | 2025-04-07 | 2025-04-29 | 2025-05-30 | 2025-06-24 | 44
C-52-06CR-CME01-1000 | Trench Excavation | 2 | 2 | 2025-04-07 | 2025-04-09 | 2025-05-30 | 2025-06-02 | 1
C-52-06CR-CME01-1010 | Bedding | 2 | 2 | 2025-04-09 | 2025-04-11 | 2025-06-02 | 2025-06-04 | 35
C-52-06CR-CME01-1020 | Lowering | 2 | 2 | 2025-04-11 | 2025-04-14 | 2025-06-04 | 2025-06-09 | 35
C-52-06CR-CME01-1030 | Section Tie-in Welding | 3 | 3 | 2025-04-14 | 2025-04-17 | 2025-06-09 | 2025-06-12 | 39
C-52-06CR-CME01-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-04-17 | 2025-04-21 | 2025-06-12 | 2025-06-16 | 44
C-52-06CR-CME01-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-04-21 | 2025-04-24 | 2025-06-16 | 2025-06-19 | 44
C-52-06CR-CME01-1060 | Holiday Testing | 2 | 2 | 2025-04-24 | 2025-04-26 | 2025-06-19 | 2025-06-21 | 44
C-52-06CR-CME01-1070 | Padding & Back Filling | 2 | 2 | 2025-04-26 | 2025-04-29 | 2025-06-21 | 2025-06-24 | 44
Crossing Mechanical (TX-74) |  | 19 | 19 | 2025-04-10 | 2025-05-02 | 2025-06-03 | 2025-06-28 | 41
C-52-06CR-CME02-1000 | Trench Excavation | 2 | 2 | 2025-04-10 | 2025-04-12 | 2025-06-03 | 2025-06-07 | 1
C-52-06CR-CME02-1010 | Bedding | 2 | 2 | 2025-04-12 | 2025-04-15 | 2025-06-07 | 2025-06-10 | 34
C-52-06CR-CME02-1020 | Lowering | 2 | 2 | 2025-04-15 | 2025-04-17 | 2025-06-10 | 2025-06-12 | 34
C-52-06CR-CME02-1030 | Section Tie-in Welding | 3 | 3 | 2025-04-17 | 2025-04-21 | 2025-06-12 | 2025-06-16 | 36
C-52-06CR-CME02-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-04-21 | 2025-04-24 | 2025-06-16 | 2025-06-19 | 41
C-52-06CR-CME02-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-04-24 | 2025-04-28 | 2025-06-19 | 2025-06-23 | 41
C-52-06CR-CME02-1060 | Holiday Testing | 2 | 2 | 2025-04-28 | 2025-04-30 | 2025-06-23 | 2025-06-25 | 41
C-52-06CR-CME02-1070 | Padding & Back Filling | 2 | 2 | 2025-04-30 | 2025-05-02 | 2025-06-25 | 2025-06-28 | 41
Crossing Mechanical (TX-75) |  | 19 | 19 | 2025-04-14 | 2025-05-06 | 2025-06-09 | 2025-07-02 | 38
C-52-06CR-CME03-1000 | Trench Excavation | 2 | 2 | 2025-04-14 | 2025-04-16 | 2025-06-09 | 2025-06-11 | 1
C-52-06CR-CME03-1010 | Bedding | 2 | 2 | 2025-04-16 | 2025-04-18 | 2025-06-11 | 2025-06-13 | 33
C-52-06CR-CME03-1020 | Lowering | 2 | 2 | 2025-04-18 | 2025-04-21 | 2025-06-13 | 2025-06-16 | 33
C-52-06CR-CME03-1030 | Section Tie-in Welding | 3 | 3 | 2025-04-21 | 2025-04-24 | 2025-06-16 | 2025-06-19 | 33
C-52-06CR-CME03-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-04-24 | 2025-04-28 | 2025-06-19 | 2025-06-23 | 38
C-52-06CR-CME03-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-04-28 | 2025-05-01 | 2025-06-23 | 2025-06-26 | 38
C-52-06CR-CME03-1060 | Holiday Testing | 2 | 2 | 2025-05-01 | 2025-05-03 | 2025-06-26 | 2025-06-30 | 38
C-52-06CR-CME03-1070 | Padding & Back Filling | 2 | 2 | 2025-05-03 | 2025-05-06 | 2025-06-30 | 2025-07-02 | 38
Crossing Mechanical (TX-76) |  | 19 | 19 | 2025-04-17 | 2025-05-16 | 2025-06-12 | 2025-07-05 | 35
C-52-06CR-CME04-1000 | Trench Excavation | 2 | 2 | 2025-04-17 | 2025-04-19 | 2025-06-12 | 2025-06-14 | 1
C-52-06CR-CME04-1010 | Bedding | 2 | 2 | 2025-04-19 | 2025-04-22 | 2025-06-14 | 2025-06-17 | 26
C-52-06CR-CME04-1020 | Lowering | 2 | 2 | 2025-04-29 | 2025-04-30 | 2025-06-17 | 2025-06-19 | 26
C-52-06CR-CME04-1030 | Section Tie-in Welding | 3 | 3 | 2025-05-01 | 2025-05-03 | 2025-06-19 | 2025-06-23 | 30
C-52-06CR-CME04-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-05-05 | 2025-05-08 | 2025-06-23 | 2025-06-26 | 35
C-52-06CR-CME04-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-05-08 | 2025-05-12 | 2025-06-26 | 2025-07-01 | 35
C-52-06CR-CME04-1060 | Holiday Testing | 2 | 2 | 2025-05-12 | 2025-05-14 | 2025-07-01 | 2025-07-03 | 35
C-52-06CR-CME04-1070 | Padding & Back Filling | 2 | 2 | 2025-05-14 | 2025-05-16 | 2025-07-03 | 2025-07-05 | 35
Crossing Mechanical (TX-77) |  | 19 | 19 | 2025-04-21 | 2025-05-19 | 2025-06-16 | 2025-07-09 | 32
C-52-06CR-CME05-1000 | Trench Excavation | 2 | 2 | 2025-04-21 | 2025-04-23 | 2025-06-16 | 2025-06-18 | 1
C-52-06CR-CME05-1010 | Bedding | 2 | 2 | 2025-04-23 | 2025-04-25 | 2025-06-18 | 2025-06-20 | 25
C-52-06CR-CME05-1020 | Lowering | 2 | 2 | 2025-05-01 | 2025-05-02 | 2025-06-20 | 2025-06-23 | 25
C-52-06CR-CME05-1030 | Section Tie-in Welding | 3 | 3 | 2025-05-03 | 2025-05-07 | 2025-06-23 | 2025-06-26 | 27
C-52-06CR-CME05-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-05-07 | 2025-05-10 | 2025-06-26 | 2025-07-01 | 32
C-52-06CR-CME05-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-05-10 | 2025-05-14 | 2025-07-01 | 2025-07-04 | 32
C-52-06CR-CME05-1060 | Holiday Testing | 2 | 2 | 2025-05-14 | 2025-05-16 | 2025-07-04 | 2025-07-07 | 32
C-52-06CR-CME05-1070 | Padding & Back Filling | 2 | 2 | 2025-05-16 | 2025-05-19 | 2025-07-07 | 2025-07-09 | 32
Crossing Mechanical (TX-78) |  | 19 | 19 | 2025-04-24 | 2025-05-21 | 2025-06-19 | 2025-07-12 | 29
C-52-06CR-CME06-1000 | Trench Excavation | 2 | 2 | 2025-04-24 | 2025-04-26 | 2025-06-19 | 2025-06-21 | 1
C-52-06CR-CME06-1010 | Bedding | 2 | 2 | 2025-04-26 | 2025-04-29 | 2025-06-21 | 2025-06-24 | 24
C-52-06CR-CME06-1020 | Lowering | 2 | 2 | 2025-05-03 | 2025-05-06 | 2025-06-24 | 2025-06-26 | 24
C-52-06CR-CME06-1030 | Section Tie-in Welding | 3 | 3 | 2025-05-06 | 2025-05-09 | 2025-06-26 | 2025-07-01 | 24
C-52-06CR-CME06-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-05-09 | 2025-05-13 | 2025-07-01 | 2025-07-04 | 29
C-52-06CR-CME06-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-05-13 | 2025-05-16 | 2025-07-04 | 2025-07-08 | 29
C-52-06CR-CME06-1060 | Holiday Testing | 2 | 2 | 2025-05-16 | 2025-05-19 | 2025-07-08 | 2025-07-10 | 29
C-52-06CR-CME06-1070 | Padding & Back Filling | 2 | 2 | 2025-05-19 | 2025-05-21 | 2025-07-10 | 2025-07-12 | 29
Crossing Mechanical (TX-79) |  | 19 | 19 | 2025-04-28 | 2025-05-21 | 2025-06-23 | 2025-07-16 | 26
C-52-06CR-CME07-1000 | Trench Excavation | 2 | 2 | 2025-04-28 | 2025-04-30 | 2025-06-23 | 2025-06-25 | 1
C-52-06CR-CME07-1010 | Bedding | 2 | 2 | 2025-04-30 | 2025-05-02 | 2025-06-25 | 2025-06-28 | 7
C-52-06CR-CME07-1020 | Lowering | 2 | 2 | 2025-05-02 | 2025-05-05 | 2025-06-28 | 2025-07-01 | 7
C-52-06CR-CME07-1030 | Section Tie-in Welding | 3 | 3 | 2025-05-05 | 2025-05-09 | 2025-07-01 | 2025-07-04 | 21
C-52-06CR-CME07-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-05-09 | 2025-05-13 | 2025-07-04 | 2025-07-08 | 26
C-52-06CR-CME07-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-05-13 | 2025-05-16 | 2025-07-08 | 2025-07-11 | 26
C-52-06CR-CME07-1060 | Holiday Testing | 2 | 2 | 2025-05-16 | 2025-05-19 | 2025-07-11 | 2025-07-14 | 26
C-52-06CR-CME07-1070 | Padding & Back Filling | 2 | 2 | 2025-05-19 | 2025-05-21 | 2025-07-14 | 2025-07-16 | 26
Crossing Mechanical (TX-80) |  | 18 | 18 | 2025-05-01 | 2025-05-24 | 2025-06-26 | 2025-07-18 | 24
C-52-06CR-CME08-1000 | Trench Excavation | 2 | 2 | 2025-05-01 | 2025-05-03 | 2025-06-26 | 2025-06-30 | 1
C-52-06CR-CME08-1010 | Bedding | 2 | 2 | 2025-05-03 | 2025-05-06 | 2025-06-26 | 2025-06-30 | 8
C-52-06CR-CME08-1020 | Lowering | 2 | 2 | 2025-05-06 | 2025-05-09 | 2025-07-01 | 2025-07-03 | 7
C-52-06CR-CME08-1030 | Section Tie-in Welding | 3 | 3 | 2025-05-09 | 2025-05-13 | 2025-07-03 | 2025-07-07 | 19
C-52-06CR-CME08-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-05-13 | 2025-05-16 | 2025-07-07 | 2025-07-10 | 24
C-52-06CR-CME08-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-05-16 | 2025-05-20 | 2025-07-10 | 2025-07-14 | 24
C-52-06CR-CME08-1060 | Holiday Testing | 2 | 2 | 2025-05-20 | 2025-05-22 | 2025-07-14 | 2025-07-16 | 24
C-52-06CR-CME08-1070 | Padding & Back Filling | 2 | 2 | 2025-05-22 | 2025-05-24 | 2025-07-16 | 2025-07-18 | 24
Crossing Mechanical (TX-81) |  | 19 | 19 | 2025-05-05 | 2025-05-28 | 2025-07-01 | 2025-07-23 | 20
C-52-06CR-CME09-1000 | Trench Excavation | 2 | 2 | 2025-05-05 | 2025-05-08 | 2025-07-01 | 2025-07-03 | 1
C-52-06CR-CME09-1010 | Bedding | 2 | 2 | 2025-05-08 | 2025-05-10 | 2025-07-03 | 2025-07-05 | 5
C-52-06CR-CME09-1020 | Lowering | 2 | 2 | 2025-05-10 | 2025-05-13 | 2025-07-05 | 2025-07-08 | 5
C-52-06CR-CME09-1030 | Section Tie-in Welding | 3 | 3 | 2025-05-13 | 2025-05-16 | 2025-07-08 | 2025-07-11 | 15
C-52-06CR-CME09-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-05-16 | 2025-05-20 | 2025-07-11 | 2025-07-15 | 20
C-52-06CR-CME09-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-05-20 | 2025-05-23 | 2025-07-15 | 2025-07-18 | 20
C-52-06CR-CME09-1060 | Holiday Testing | 2 | 2 | 2025-05-23 | 2025-05-26 | 2025-07-18 | 2025-07-21 | 20
C-52-06CR-CME09-1070 | Padding & Back Filling | 2 | 2 | 2025-05-26 | 2025-05-28 | 2025-07-21 | 2025-07-23 | 20
Crossing Mechanical (TX-82) |  | 19 | 19 | 2025-05-09 | 2025-05-31 | 2025-07-04 | 2025-07-26 | 17
C-52-06CR-CME10-1000 | Trench Excavation | 2 | 2 | 2025-05-09 | 2025-05-12 | 2025-07-04 | 2025-07-07 | 1
C-52-06CR-CME10-1010 | Bedding | 2 | 2 | 2025-05-12 | 2025-05-14 | 2025-07-07 | 2025-07-09 | 4
C-52-06CR-CME10-1020 | Lowering | 2 | 2 | 2025-05-14 | 2025-05-16 | 2025-07-09 | 2025-07-11 | 4
C-52-06CR-CME10-1030 | Section Tie-in Welding | 3 | 3 | 2025-05-16 | 2025-05-20 | 2025-07-11 | 2025-07-15 | 12
C-52-06CR-CME10-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-05-20 | 2025-05-23 | 2025-07-15 | 2025-07-18 | 17
C-52-06CR-CME10-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-05-23 | 2025-05-27 | 2025-07-18 | 2025-07-22 | 17
C-52-06CR-CME10-1060 | Holiday Testing | 2 | 2 | 2025-05-27 | 2025-05-29 | 2025-07-22 | 2025-07-24 | 17
C-52-06CR-CME10-1070 | Padding & Back Filling | 2 | 2 | 2025-05-29 | 2025-05-31 | 2025-07-24 | 2025-07-26 | 17
Crossing Mechanical (TX-83) |  | 19 | 19 | 2025-05-13 | 2025-06-04 | 2025-07-08 | 2025-07-30 | 14
C-52-06CR-CME11-1000 | Trench Excavation | 2 | 2 | 2025-05-13 | 2025-05-15 | 2025-07-08 | 2025-07-10 | 1
C-52-06CR-CME11-1010 | Bedding | 2 | 2 | 2025-05-15 | 2025-05-17 | 2025-07-10 | 2025-07-12 | 3
C-52-06CR-CME11-1020 | Lowering | 2 | 2 | 2025-05-17 | 2025-05-20 | 2025-07-12 | 2025-07-15 | 3
C-52-06CR-CME11-1030 | Section Tie-in Welding | 3 | 3 | 2025-05-20 | 2025-05-23 | 2025-07-15 | 2025-07-18 | 9
C-52-06CR-CME11-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-05-23 | 2025-05-27 | 2025-07-18 | 2025-07-22 | 14
C-52-06CR-CME11-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-05-27 | 2025-05-30 | 2025-07-22 | 2025-07-25 | 14
C-52-06CR-CME11-1060 | Holiday Testing | 2 | 2 | 2025-05-30 | 2025-06-02 | 2025-07-25 | 2025-07-28 | 14
C-52-06CR-CME11-1070 | Padding & Back Filling | 2 | 2 | 2025-06-02 | 2025-06-04 | 2025-07-28 | 2025-07-30 | 14
Crossing Mechanical (TX-84) |  | 19 | 19 | 2025-05-16 | 2025-06-10 | 2025-07-11 | 2025-08-02 | 11
C-52-06CR-CME12-1000 | Trench Excavation | 2 | 2 | 2025-05-16 | 2025-05-19 | 2025-07-11 | 2025-07-14 | 1
C-52-06CR-CME12-1010 | Bedding | 2 | 2 | 2025-05-19 | 2025-05-21 | 2025-07-14 | 2025-07-16 | 2
C-52-06CR-CME12-1020 | Lowering | 2 | 2 | 2025-05-21 | 2025-05-23 | 2025-07-16 | 2025-07-18 | 2
C-52-06CR-CME12-1030 | Section Tie-in Welding | 3 | 3 | 2025-05-23 | 2025-05-27 | 2025-07-18 | 2025-07-22 | 6
C-52-06CR-CME12-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-05-27 | 2025-05-30 | 2025-07-22 | 2025-07-25 | 11
C-52-06CR-CME12-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-05-30 | 2025-06-03 | 2025-07-25 | 2025-07-29 | 11
C-52-06CR-CME12-1060 | Holiday Testing | 2 | 2 | 2025-06-03 | 2025-06-07 | 2025-07-29 | 2025-07-31 | 11
C-52-06CR-CME12-1070 | Padding & Back Filling | 2 | 2 | 2025-06-07 | 2025-06-10 | 2025-07-31 | 2025-08-02 | 11
Crossing Mechanical (TX-85) |  | 19 | 19 | 2025-05-19 | 2025-06-12 | 2025-07-14 | 2025-08-05 | 9
C-52-06CR-CME13-1000 | Trench Excavation | 2 | 2 | 2025-05-19 | 2025-05-21 | 2025-07-14 | 2025-07-16 | 1
C-52-06CR-CME13-1010 | Bedding | 2 | 2 | 2025-05-21 | 2025-05-23 | 2025-07-16 | 2025-07-18 | 2
C-52-06CR-CME13-1020 | Lowering | 2 | 2 | 2025-05-23 | 2025-05-26 | 2025-07-18 | 2025-07-21 | 2
C-52-06CR-CME13-1030 | Section Tie-in Welding | 3 | 3 | 2025-05-26 | 2025-05-29 | 2025-07-21 | 2025-07-24 | 4
C-52-06CR-CME13-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-05-29 | 2025-06-02 | 2025-07-24 | 2025-07-28 | 9
C-52-06CR-CME13-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-06-02 | 2025-06-07 | 2025-07-28 | 2025-07-31 | 9
C-52-06CR-CME13-1060 | Holiday Testing | 2 | 2 | 2025-06-07 | 2025-06-10 | 2025-07-31 | 2025-08-02 | 9
C-52-06CR-CME13-1070 | Padding & Back Filling | 2 | 2 | 2025-06-10 | 2025-06-12 | 2025-08-02 | 2025-08-05 | 9
Crossing Mechanical (TX-89) |  | 19 | 19 | 2025-05-22 | 2025-06-16 | 2025-07-17 | 2025-08-08 | 6
C-52-06CR-CME14-1000 | Trench Excavation | 2 | 2 | 2025-05-22 | 2025-05-24 | 2025-07-17 | 2025-07-19 | 1
C-52-06CR-CME14-1010 | Bedding | 2 | 2 | 2025-05-24 | 2025-05-27 | 2025-07-19 | 2025-07-22 | 1
C-52-06CR-CME14-1020 | Lowering | 2 | 2 | 2025-05-27 | 2025-05-29 | 2025-07-22 | 2025-07-24 | 1
C-52-06CR-CME14-1030 | Section Tie-in Welding | 3 | 3 | 2025-05-29 | 2025-06-02 | 2025-07-24 | 2025-07-28 | 1
C-52-06CR-CME14-1040 | NDT (Tie-in Joint) | 3 | 3 | 2025-06-02 | 2025-06-07 | 2025-07-28 | 2025-07-31 | 6
C-52-06CR-CME14-1050 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-06-07 | 2025-06-11 | 2025-07-31 | 2025-08-04 | 6
C-52-06CR-CME14-1060 | Holiday Testing | 2 | 2 | 2025-06-11 | 2025-06-13 | 2025-08-04 | 2025-08-06 | 6
C-52-06CR-CME14-1070 | Padding & Back Filling | 2 | 2 | 2025-06-13 | 2025-06-16 | 2025-08-06 | 2025-08-08 | 6
Crossings - UG CableCCOPL52477 |  | 34 | 34 | 2025-04-28 | 2025-06-09 | 2025-06-11 | 2025-07-22 | 21
Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) |  | 14 | 14 | 2025-04-28 | 2025-05-14 | 2025-06-11 | 2025-06-28 | 41
C-52-06CR-CMA08-1000 | Trench Excavation | 8 | 8 | 2025-04-28 | 2025-05-07 | 2025-06-11 | 2025-06-20 | 7
C-52-06CR-CMA08-1010 | Bedding | 1 | 1 | 2025-05-06 | 2025-05-07 | 2025-06-19 | 2025-06-20 | 23
C-52-06CR-CMA08-1020 | Lowering | 1 | 1 | 2025-05-07 | 2025-05-08 | 2025-06-20 | 2025-06-21 | 23
C-52-06CR-CMA08-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-07 | 2025-05-09 | 2025-06-20 | 2025-06-23 | 30
C-52-06CR-CMA08-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-08 | 2025-05-10 | 2025-06-21 | 2025-06-24 | 41
C-52-06CR-CMA08-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-09 | 2025-05-12 | 2025-06-23 | 2025-06-25 | 41
C-52-06CR-CMA08-1060 | Holiday Testing | 1 | 1 | 2025-05-12 | 2025-05-13 | 2025-06-25 | 2025-06-26 | 41
C-52-06CR-CMA08-1070 | Padding | 1 | 1 | 2025-05-13 | 2025-05-14 | 2025-06-26 | 2025-06-28 | 41
Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) |  | 20 | 20 | 2025-05-14 | 2025-06-09 | 2025-06-28 | 2025-07-22 | 21
C-52-06CR-CMA09-1000 | Trench Excavation | 14 | 14 | 2025-05-14 | 2025-05-30 | 2025-06-28 | 2025-07-15 | 7
C-52-06CR-CMA09-1010 | Bedding | 1 | 1 | 2025-05-29 | 2025-05-30 | 2025-07-14 | 2025-07-15 | 7
C-52-06CR-CMA09-1020 | Lowering | 1 | 1 | 2025-05-30 | 2025-05-31 | 2025-07-15 | 2025-07-16 | 7
C-52-06CR-CMA09-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-30 | 2025-06-02 | 2025-07-15 | 2025-07-17 | 10
C-52-06CR-CMA09-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-31 | 2025-06-03 | 2025-07-16 | 2025-07-18 | 21
C-52-06CR-CMA09-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-06-02 | 2025-06-04 | 2025-07-17 | 2025-07-19 | 21
C-52-06CR-CMA09-1060 | Holiday Testing | 1 | 1 | 2025-06-04 | 2025-06-07 | 2025-07-19 | 2025-07-21 | 21
C-52-06CR-CMA09-1070 | Padding | 1 | 1 | 2025-06-07 | 2025-06-09 | 2025-07-21 | 2025-07-22 | 21
Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) |  | 14 | 14 | 2025-05-21 | 2025-06-09 | 2025-07-05 | 2025-07-22 | 21
C-52-06CR-CMA10-1000 | Trench Excavation | 8 | 8 | 2025-05-21 | 2025-05-30 | 2025-07-05 | 2025-07-15 | 9
C-52-06CR-CMA10-1010 | Bedding | 1 | 1 | 2025-05-29 | 2025-05-30 | 2025-07-14 | 2025-07-15 | 9
C-52-06CR-CMA10-1020 | Lowering | 1 | 1 | 2025-05-30 | 2025-05-31 | 2025-07-15 | 2025-07-16 | 9
C-52-06CR-CMA10-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-30 | 2025-06-02 | 2025-07-15 | 2025-07-17 | 10
C-52-06CR-CMA10-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-31 | 2025-06-03 | 2025-07-16 | 2025-07-18 | 21
C-52-06CR-CMA10-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-06-02 | 2025-06-04 | 2025-07-17 | 2025-07-19 | 21
C-52-06CR-CMA10-1060 | Holiday Testing | 1 | 1 | 2025-06-04 | 2025-06-07 | 2025-07-19 | 2025-07-21 | 21
C-52-06CR-CMA10-1070 | Padding | 1 | 1 | 2025-06-07 | 2025-06-09 | 2025-07-21 | 2025-07-22 | 21
Crossings OHPLCCOPL52492 |  | 48 | 48 | 2025-04-14 | 2025-06-11 | 2025-05-26 | 2025-07-24 | 19
Crossing Manual @ KP 140+403 (OX-14) |  | 12 | 12 | 2025-04-21 | 2025-05-03 | 2025-06-02 | 2025-06-18 | 49
C-52-06CR-CMA11-1000 | Trench Excavation | 6 | 6 | 2025-04-21 | 2025-04-26 | 2025-06-02 | 2025-06-11 | 7
C-52-06CR-CMA11-1010 | Bedding | 1 | 1 | 2025-04-26 | 2025-04-26 | 2025-06-10 | 2025-06-11 | 20
C-52-06CR-CMA11-1020 | Lowering | 1 | 1 | 2025-04-28 | 2025-04-28 | 2025-06-11 | 2025-06-12 | 20
C-52-06CR-CMA11-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-28 | 2025-04-29 | 2025-06-11 | 2025-06-13 | 38
C-52-06CR-CMA11-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-29 | 2025-04-30 | 2025-06-12 | 2025-06-14 | 49
C-52-06CR-CMA11-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-30 | 2025-05-01 | 2025-06-13 | 2025-06-16 | 49
C-52-06CR-CMA11-1060 | Holiday Testing | 1 | 1 | 2025-05-02 | 2025-05-02 | 2025-06-16 | 2025-06-17 | 49
C-52-06CR-CMA11-1070 | Padding | 1 | 1 | 2025-05-03 | 2025-05-03 | 2025-06-17 | 2025-06-18 | 49
Crossing Manual @ KP 155+502 (OX-15) |  | 33 | 33 | 2025-04-14 | 2025-05-22 | 2025-05-26 | 2025-07-07 | 34
C-52-06CR-CMA12-1000 | Trench Excavation | 6 | 6 | 2025-04-14 | 2025-04-19 | 2025-05-26 | 2025-06-02 | 7
C-52-06CR-CMA12-1010 | Bedding | 1 | 1 | 2025-04-19 | 2025-04-19 | 2025-05-31 | 2025-06-02 | 40
C-52-06CR-CMA12-1020 | Lowering | 1 | 1 | 2025-05-15 | 2025-05-16 | 2025-06-30 | 2025-07-01 | 19
C-52-06CR-CMA12-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-15 | 2025-05-17 | 2025-06-30 | 2025-07-02 | 23
C-52-06CR-CMA12-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-16 | 2025-05-19 | 2025-07-01 | 2025-07-03 | 34
C-52-06CR-CMA12-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-17 | 2025-05-20 | 2025-07-02 | 2025-07-04 | 34
C-52-06CR-CMA12-1060 | Holiday Testing | 1 | 1 | 2025-05-20 | 2025-05-21 | 2025-07-04 | 2025-07-05 | 34
C-52-06CR-CMA12-1070 | Padding | 1 | 1 | 2025-05-21 | 2025-05-22 | 2025-07-05 | 2025-07-07 | 34
Crossing Manual @ KP 160+979 (OX-16) |  | 16 | 16 | 2025-05-21 | 2025-06-11 | 2025-07-05 | 2025-07-24 | 17
C-52-06CR-CMA13-1000 | Trench Excavation | 6 | 6 | 2025-05-21 | 2025-05-28 | 2025-07-05 | 2025-07-12 | 13
C-52-06CR-CMA13-1010 | Bedding | 1 | 1 | 2025-05-27 | 2025-05-28 | 2025-07-11 | 2025-07-12 | 13
C-52-06CR-CMA13-1020 | Lowering | 1 | 1 | 2025-06-02 | 2025-06-03 | 2025-07-17 | 2025-07-18 | 9
C-52-06CR-CMA13-1030 | Section Tie-in Welding | 2 | 2 | 2025-06-02 | 2025-06-04 | 2025-07-17 | 2025-07-19 | 9
C-52-06CR-CMA13-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-06-03 | 2025-06-07 | 2025-07-18 | 2025-07-21 | 17
C-52-06CR-CMA13-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-06-04 | 2025-06-09 | 2025-07-19 | 2025-07-22 | 17
C-52-06CR-CMA13-1060 | Holiday Testing | 1 | 1 | 2025-06-09 | 2025-06-10 | 2025-07-22 | 2025-07-23 | 17
C-52-06CR-CMA13-1070 | Padding | 1 | 1 | 2025-06-10 | 2025-06-11 | 2025-07-23 | 2025-07-24 | 17
CP Works TemporaryCCOP52EL49 |  | 41 | 41 | 2025-07-30 | 2025-09-30 | 2025-06-28 | 2025-08-15 | 66
C-52-06CR-PL-CA-5200 | Installation of CP Test Post | 30 | 30 | 2025-07-30 | 2025-09-27 | 2025-06-28 | 2025-08-02 | 75
C-52-06CR-PL-CA-5210 | Glanding & Termination of Temp. CP S/m | 2 | 2 | 2025-09-27 | 2025-09-30 | 2025-08-13 | 2025-08-15 | 66
Test Stations & Anode BedsCCOP52EL48 |  | 30 | 30 | 2025-07-30 | 2025-09-03 | 2025-06-28 | 2025-08-02 | 0
C-52-06CR-PL-CA-5600 | Installation of Temp. Anode | 30 | 30 | 2025-07-30 | 2025-09-03 | 2025-06-28 | 2025-08-02 | 0
PaddingCCOPL52470 |  | 30 | 30 | 2025-07-31 | 2025-09-04 | 2025-07-11 | 2025-08-15 | 0
C-52-06CR-PL-CI-6000 | Padding | 30 | 30 | 2025-07-31 | 2025-09-04 | 2025-07-11 | 2025-08-15 | 0
BackfillingCCOPL52478 |  | 30 | 30 | 2025-08-02 | 2025-09-08 | 2025-07-14 | 2025-08-18 | 0
C-52-06CR-PL-CI-6400 | Backfilling | 30 | 30 | 2025-08-02 | 2025-09-08 | 2025-07-14 | 2025-08-18 | 0
BermingCCOPL52479 |  | 33 | 33 | 2025-08-04 | 2025-10-06 | 2025-08-08 | 2025-09-17 | 39
C-52-06CR-PL-CI-6800 | Gatch Laying & Levelling | 30 | 30 | 2025-08-04 | 2025-09-09 | 2025-08-08 | 2025-09-13 | 0
C-52-06CR-PL-CI-6810 | Gatch Compaction | 30 | 30 | 2025-08-05 | 2025-09-10 | 2025-08-09 | 2025-09-15 | 0
C-52-06CR-PL-CI-7800 | Installation of Marker Post/Sign Board | 30 | 30 | 2025-08-06 | 2025-10-04 | 2025-08-11 | 2025-09-16 | 39
C-52-06CR-PL-CI-7810 | Installation of Crash Barriers (If any) | 30 | 30 | 2025-08-07 | 2025-10-06 | 2025-08-12 | 2025-09-17 | 39
NDRC by Micro Tunneling Method |  | 46 | 46 | 2024-10-05 | 2025-06-18 | 2025-06-17 | 2025-08-11 | 27
NDRC-29 (incl Hydrotest) @ CH 146+000 - 146+055 (Open Cut*) |  | 19 | 19 | 2025-05-24 | 2025-06-18 | 2025-07-19 | 2025-08-11 | 2
Entry & Exit Pit ConstructionCCOPL52964 |  | 2 | 2 | 2025-05-24 | 2025-05-27 | 2025-07-19 | 2025-07-22 | 2
C-52-06CR-CME29-1080 | Trench Excavation | 2 | 2 | 2025-05-24 | 2025-05-27 | 2025-07-19 | 2025-07-22 | 2
Tunneling & Jack UpCCOPL52924 |  | 2 | 2 | 2025-05-27 | 2025-05-29 | 2025-07-22 | 2025-07-24 | 2
C-52-06CR-CME29-1090 | Bedding | 2 | 2 | 2025-05-27 | 2025-05-29 | 2025-07-22 | 2025-07-24 | 2
Pipe Lowering, Welding & NDTCCOPL52974 |  | 11 | 11 | 2025-05-29 | 2025-06-13 | 2025-07-24 | 2025-08-06 | 2
C-52-06CR-CME29-1100 | Lowering | 2 | 2 | 2025-05-29 | 2025-05-31 | 2025-07-24 | 2025-07-26 | 2
C-52-06CR-CME29-1110 | Section Tie-in Welding | 3 | 3 | 2025-05-31 | 2025-06-04 | 2025-07-26 | 2025-07-30 | 2
C-52-06CR-CME29-1120 | NDT (Tie-in Joint) | 3 | 3 | 2025-06-04 | 2025-06-10 | 2025-07-30 | 2025-08-02 | 2
C-52-06CR-CME29-1130 | Ext. Joint Coating (Tie-in Joint) | 3 | 3 | 2025-06-10 | 2025-06-13 | 2025-08-02 | 2025-08-06 | 2
HydrotestingCCOPL52984 |  | 2 | 2 | 2025-06-13 | 2025-06-16 | 2025-08-06 | 2025-08-08 | 2
C-52-06CR-CME29-1140 | Holiday Testing | 2 | 2 | 2025-06-13 | 2025-06-16 | 2025-08-06 | 2025-08-08 | 2
Re-Instatement of Entry & Exit PitCCOPL52994 |  | 2 | 2 | 2025-06-16 | 2025-06-18 | 2025-08-08 | 2025-08-11 | 2
C-52-06CR-CME29-1150 | Padding & Back Filling | 2 | 2 | 2025-06-16 | 2025-06-18 | 2025-08-08 | 2025-08-11 | 2
Micro Tunnelling @ CH 161+045 - 161+106 (NDRC-31) |  | 44 | 44 | 2024-10-05 | 2025-05-02 | 2025-06-17 | 2025-08-08 | 29
Entry & Exit Pit ConstructionCCOPL52928 |  | 21 | 21 | 2024-10-05 | 2024-12-13 | 2025-06-17 | 2025-07-12 | 3
C-52-06CR-CNM31-1000 | Sheet Piling for Driving & Receiving Pit | 4 | 4 | 2024-10-05 | 2024-11-02 | 2025-06-17 | 2025-06-21 | 3
C-52-06CR-CNM31-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-11-04 | 2024-11-07 | 2025-06-21 | 2025-06-26 | 3
C-52-06CR-CNM31-1010 | Driving & Receiving Pit Excavation | 4 | 4 | 2024-10-30 | 2024-11-14 | 2025-06-21 | 2025-06-26 | 7
C-52-06CR-CNM31-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 4 | 4 | 2024-11-08 | 2024-11-19 | 2025-06-26 | 2025-07-02 | 3
C-52-06CR-CNM31-1040 | Floor Blinding & French Drain in Driving Pit | 3 | 3 | 2024-11-20 | 2024-11-26 | 2025-07-02 | 2025-07-05 | 3
C-52-06CR-CNM31-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 3 | 3 | 2024-11-27 | 2024-12-05 | 2025-07-05 | 2025-07-09 | 3
C-52-06CR-CNM31-1060 | Construction of Exit Wall with Ring | 3 | 3 | 2024-12-07 | 2024-12-13 | 2025-07-09 | 2025-07-12 | 3
Tunneling & Jack UpCCOPL56932 |  | 19 | 19 | 2025-03-01 | 2025-04-16 | 2025-07-12 | 2025-08-04 | 10
C-52-06CR-CNM31-1200 | Jacking of MTBM & RC Sleeves | 4 | 4 | 2025-03-01 | 2025-03-08 | 2025-07-12 | 2025-07-17 | 3
C-52-06CR-CNM31-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 3 | 3 | 2025-03-08 | 2025-03-14 | 2025-07-17 | 2025-07-21 | 3
C-52-06CR-CNM31-1220 | Inner Grout b/w Main & RC Pipe | 3 | 3 | 2025-04-10 | 2025-04-16 | 2025-07-31 | 2025-08-04 | 10
Pipe Lowering, Welding & NDTCCOPL56942 |  | 5 | 5 | 2025-03-14 | 2025-04-03 | 2025-07-21 | 2025-07-26 | 10
C-52-06CR-CNM31-1400 | Lowering & Welding of Carrier Pipe | 4 | 4 | 2025-03-14 | 2025-03-26 | 2025-07-21 | 2025-07-25 | 3
C-52-06CR-CNM31-1410 | NDT, Coating & Holiday Inspection of Carrier Pipe | 4 | 4 | 2025-03-15 | 2025-04-03 | 2025-07-22 | 2025-07-26 | 10
HydrotestingCCOPL56952 |  | 4 | 4 | 2025-04-03 | 2025-04-10 | 2025-07-26 | 2025-07-31 | 10
C-52-06CR-CNM31-1600 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 4 | 4 | 2025-04-03 | 2025-04-10 | 2025-07-26 | 2025-07-31 | 10
Re-Instatement of Entry & Exit PitCCOPL56962 |  | 4 | 4 | 2025-04-16 | 2025-05-02 | 2025-08-04 | 2025-08-08 | 29
C-52-06CR-CNM31-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 4 | 4 | 2025-04-16 | 2025-05-02 | 2025-08-04 | 2025-08-08 | 29
NDRC by Micro Tunnelling Method |  | 134 | 134 | 2024-10-05 | 2025-03-23 | 2025-03-06 | 2025-08-23 | 3
Micro Tunnelling @ CH 160+299 - 160+543 (NDRC-30) |  | 134 | 134 | 2024-10-05 | 2025-03-23 | 2025-03-06 | 2025-08-23 | 3
Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 |  | 119 | 119 | 2024-10-05 | 2025-02-28 | 2025-03-06 | 2025-08-06 | 3
C-52-06CR-CNH30-1000 | Sheet Piling for Driving & Receiving Pit | 15 | 15 | 2024-10-05 | 2024-11-02 | 2025-03-06 | 2025-03-28 | 3
C-52-06CR-CNH30-1020 | Installation of Dewatering System for Driving & Receiving Pit | 4 | 4 | 2024-11-04 | 2024-11-07 | 2025-03-29 | 2025-04-05 | 3
C-52-06CR-CNH30-1010 | Driving & Receiving Pit Excavation | 14 | 14 | 2024-10-30 | 2024-11-14 | 2025-03-29 | 2025-04-17 | 3
C-52-06CR-CNH30-1030 | Welding & Installation of Bracing in Driving & Receiving Pit | 10 | 10 | 2024-11-08 | 2024-11-19 | 2025-04-07 | 2025-04-17 | 3
C-52-06CR-CNH30-1040 | Floor Blinding & French Drain in Driving Pit | 6 | 6 | 2024-11-20 | 2024-11-26 | 2025-04-18 | 2025-04-24 | 3
C-52-06CR-CNH30-1050 | Construction of Front Wall & Thrust Wall in Driving Pit | 6 | 6 | 2024-11-27 | 2024-12-05 | 2025-04-25 | 2025-05-01 | 3
C-52-06CR-CNH30-1060 | Construction of Exit Wall with Ring | 6 | 6 | 2024-12-07 | 2024-12-13 | 2025-05-03 | 2025-05-10 | 3
C-52-06CR-CNH30-1070 | Lowering & Welding of Carrier Pipe | 25 | 25 | 2025-01-16 | 2025-02-13 | 2025-06-21 | 2025-07-22 | 3
C-52-06CR-CNH30-1080 | NDT, Coating & Holiday Inspection of Carrier Pipe | 27 | 27 | 2025-01-17 | 2025-02-17 | 2025-06-23 | 2025-07-25 | 3
C-52-06CR-CNH30-1090 | Post Hydrotest/Gauging /Cleaning for NDRC Section | 10 | 10 | 2025-02-18 | 2025-02-28 | 2025-07-25 | 2025-08-06 | 3
Tunneling & Jack UpCCOPL58122 |  | 76 | 76 | 2024-12-14 | 2025-03-08 | 2025-05-10 | 2025-08-12 | 3
C-52-06CR-CNH30-1200 | Jacking of MTBM & RC Sleeves | 29 | 29 | 2024-12-14 | 2025-01-10 | 2025-05-10 | 2025-06-17 | 3
C-52-06CR-CNH30-1210 | Filling of Grout between Earth Overcut & RC Sleeve | 4 | 4 | 2025-01-11 | 2025-01-15 | 2025-06-17 | 2025-06-21 | 3
C-52-06CR-CNH30-1220 | Inner Grout b/w Main & RC Pipe | 5 | 5 | 2025-03-01 | 2025-03-08 | 2025-08-06 | 2025-08-12 | 3
Re-Instatement of Entry & Exit PitCCOPL58132 |  | 14 | 14 | 2025-03-02 | 2025-03-23 | 2025-08-07 | 2025-08-23 | 3
C-52-06CR-CNH30-1800 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | 14 | 14 | 2025-03-02 | 2025-03-23 | 2025-08-07 | 2025-08-23 | 3
Cathodic Protection |  | 38 | 38 | 2025-05-02 | 2025-09-03 | 2025-07-08 | 2025-08-21 | 61
Civil Works |  | 30 | 30 | 2025-07-09 | 2025-08-25 | 2025-07-08 | 2025-08-12 | 61
Backfilling & Reinstatement for CP (for Crossings)CCOP52CS33 |  | 30 | 30 | 2025-07-09 | 2025-08-25 | 2025-07-08 | 2025-08-12 | 61
C-52-06CR-PIPEL-5260 | Backfilling & Reinstatement for CP (for Crossings) | 30 | 30 | 2025-07-09 | 2025-08-25 | 2025-07-08 | 2025-08-12 | 61
CP Works |  | 38 | 38 | 2025-05-02 | 2025-09-03 | 2025-07-08 | 2025-08-21 | 61
CP Works (for Crossings)CCOP52EL50 |  | 38 | 38 | 2025-05-02 | 2025-09-03 | 2025-07-08 | 2025-08-21 | 61
C-52-06CR-PL-CA-5220 | Installation of Test Post for Crossing | 30 | 30 | 2025-05-02 | 2025-07-03 | 2025-07-08 | 2025-08-12 | 61
C-52-06CR-PL-CA-5230 | Installation of CP JB's | 30 | 30 | 2025-05-03 | 2025-07-04 | 2025-07-09 | 2025-08-13 | 61
C-52-06CR-PL-CA-5240 | Installation of CP TR | 30 | 30 | 2025-06-28 | 2025-08-26 | 2025-07-09 | 2025-08-13 | 61
C-52-06CR-PL-CA-5250 | CIP/DCVG Survey | 7 | 7 | 2025-08-26 | 2025-09-03 | 2025-08-13 | 2025-08-21 | 61
Telecommunication Works |  | 33 | 33 | 2025-08-01 | 2025-09-10 | 2025-07-12 | 2025-08-20 | 62
Telecom Works along Pipeline CCOP52IC30 |  | 33 | 33 | 2025-08-01 | 2025-09-10 | 2025-07-12 | 2025-08-20 | 62
C-52-06CR-PL-TE-8200 | FO - Cable Pulling/ Laying | 30 | 30 | 2025-08-01 | 2025-09-06 | 2025-07-12 | 2025-08-16 | 0
C-52-06CR-PL-TE-8210 | Termination/Splicing @ BVS | 3 | 3 | 2025-09-06 | 2025-09-10 | 2025-08-16 | 2025-08-20 | 62
Civil Works (Fence Construction) Double Sided |  | 354 | 292 | 2024-07-27 | 2025-11-01 | 14-Aug-24 A | 2025-10-21 | 17
Fence Construction- Double Sided (For 52" Pipeline from HGCP to Sweihan CRS) |  | 354 | 292 | 2024-07-27 | 2025-11-01 | 14-Aug-24 A | 2025-10-21 | 17
Civil Works |  | 354 | 292 | 2024-07-27 | 2025-11-01 | 14-Aug-24 A | 2025-10-21 | 17
Precasting for fence posts from HGCP to BVS-01CCOP52CS52.7 |  | 92 | 30 | 2024-07-27 | 2024-10-03 | 14-Aug-24 A | 2024-11-29 | 54
C-52-HG01-FENCE-1000 | Pre-Casting of Fence Foundation (BVS-01 to HGCP) | 92 | 30 | 2024-07-27 | 2024-10-03 | 14-Aug-24 A | 2024-11-29 | 54
Excavation Works for fence posts from HGCP to BVS-01CCOP52CS53.7 |  | 35 | 35 | 2025-06-12 | 2025-09-19 | 2024-11-30 | 2025-01-13 | 54
C-52-HG01-FENCE-1010 | Earth Works for Fence Foundation (BVS-01 to HGCP) | 30 | 30 | 2025-06-12 | 2025-09-13 | 2024-11-30 | 2025-01-07 | 54
C-52-HG01-FENCE-1020 | Compaction & Testing for Fence Foundation (BVS-01 to HGCP) | 30 | 30 | 2025-06-18 | 2025-09-19 | 2024-12-09 | 2025-01-13 | 54
Concrete Works for fence posts from HGCP to BVS-01CCOP52CS54.7 |  | 30 | 30 | 2025-07-07 | 2025-10-07 | 2024-12-17 | 2025-01-21 | 54
C-52-HG01-FENCE-1030 | Concrete Works (Blinding) for Fence Foundation (BVS-01 to HGCP) | 30 | 30 | 2025-07-07 | 2025-10-07 | 2024-12-17 | 2025-01-21 | 54
Concrete Protection for fence from HGCP to BVS-01CCOP52CS55.7 |  | 30 | 30 | 2025-07-09 | 2025-10-09 | 2024-12-19 | 2025-01-23 | 54
C-52-HG01-FENCE-1040 | Concrete Protection (Blinding) for Fence Foundation (BVS-01 to HGCP) | 30 | 30 | 2025-07-09 | 2025-10-09 | 2024-12-19 | 2025-01-23 | 54
Fence Installation (Type3) from HGCP to BVS-01CCOP52CS57.7 |  | 33 | 33 | 2025-08-21 | 2025-10-21 | 2024-12-27 | 2025-02-04 | 54
C-52-HG01-FENCE-1050 | Installation of Fence Post (Including Foundation) (BVS-01 to HGCP) | 30 | 30 | 2025-08-21 | 2025-10-17 | 2024-12-27 | 2025-01-31 | 54
C-52-HG01-FENCE-1070 | Installation of Fence Mesh (BVS-01 to HGCP) | 30 | 30 | 2025-08-25 | 2025-10-21 | 2024-12-31 | 2025-02-04 | 54
Backfilling for Fence from HGCP to BVS-01CCOP52CS56.7 |  | 30 | 30 | 2025-08-22 | 2025-10-18 | 2024-12-28 | 2025-02-01 | 54
C-52-HG01-FENCE-1060 | Back Filliing of Fence Post Foundation (BVS-01 to HGCP) | 30 | 30 | 2025-08-22 | 2025-10-18 | 2024-12-28 | 2025-02-01 | 54
Precasting for fence posts from BVS-02 to BVS-03CCOP52CS52.5 |  | 30 | 30 | 2024-10-04 | 2024-11-07 | 2024-11-30 | 2025-01-07 | 109
C-52-0203-FENCE-1000 | Pre-Casting of Fence Foundation (BVS-02 to BVS-03) | 30 | 30 | 2024-10-04 | 2024-11-07 | 2024-11-30 | 2025-01-07 | 109
Excavation Works for fence posts from BVS-02 to BVS-03CCOP52CS53.5 |  | 28 | 28 | 2025-03-15 | 2025-05-21 | 2025-02-10 | 2025-03-17 | 140
C-52-0203-FENCE-1010 | Earth Works for Fence Foundation (BVS-02 to BVS-03) | 25 | 25 | 2025-03-15 | 2025-05-15 | 2025-02-10 | 2025-03-12 | 140
C-52-0203-FENCE-1020 | Compaction & Testing for Fence Foundation (BVS-02 to BVS-03) | 25 | 25 | 2025-03-23 | 2025-05-21 | 2025-02-13 | 2025-03-17 | 140
Concrete Works for fence posts from BVS-02 to BVS-03CCOP52CS54.5 |  | 25 | 25 | 2025-03-28 | 2025-05-24 | 2025-02-17 | 2025-03-22 | 140
C-52-0203-FENCE-1030 | Concrete Works (Blinding) for Fence Foundation (BVS-02 to BVS-03) | 25 | 25 | 2025-03-28 | 2025-05-24 | 2025-02-17 | 2025-03-22 | 140
Concrete Protection for fence from BVS-02 to BVS-03CCOP52CS55.5 |  | 25 | 25 | 2025-04-03 | 2025-05-27 | 2025-02-19 | 2025-03-24 | 140
C-52-0203-FENCE-1040 | Concrete Protection (Blinding) for Fence Foundation (BVS-02 to BVS-03) | 25 | 25 | 2025-04-03 | 2025-05-27 | 2025-02-19 | 2025-03-24 | 140
Fence Installation (Type3) from BVS-02 to BVS-03CCOP52CS57.5 |  | 26 | 26 | 2025-05-08 | 2025-06-10 | 2025-02-25 | 2025-04-05 | 145
C-52-0203-FENCE-1050 | Installation of Fence Post (Including Foundation) (BVS-02 to BVS-03) | 23 | 23 | 2025-05-08 | 2025-06-04 | 2025-02-25 | 2025-03-29 | 140
C-52-0203-FENCE-1070 | Installation of Fence Mesh (BVS-02 to BVS-03) | 23 | 23 | 2025-05-12 | 2025-06-10 | 2025-02-28 | 2025-04-05 | 145
Backfilling for Fence from BVS-02 to BVS-03CCOP52CS56.5 |  | 23 | 23 | 2025-05-09 | 2025-06-07 | 2025-02-26 | 2025-04-03 | 145
C-52-0203-FENCE-1060 | Back Filliing of Fence Post Foundation (BVS-02 to BVS-03) | 23 | 23 | 2025-05-09 | 2025-06-07 | 2025-02-26 | 2025-04-03 | 145
Precasting for fence posts from BVS-01 to BVS-02CCOP52CS52.6 |  | 85 | 40 | 2024-11-08 | 2025-01-14 | 27-Sep-24 A | 2025-01-07 | 109
C-52-0102-FENCE-1000 | Pre-Casting of Fence Foundation (BVS-02 to BVS-01) | 85 | 40 | 2024-11-08 | 2025-01-14 | 27-Sep-24 A | 2025-01-07 | 109
Excavation Works for fence posts from BVS-01 to BVS-02CCOP52CS53.6 |  | 38 | 38 | 2025-05-03 | 2025-08-09 | 2025-01-31 | 2025-03-20 | 112
C-52-0102-FENCE-1010 | Earth Works for Fence Foundation (BVS-02 to BVS-01) | 35 | 35 | 2025-05-03 | 2025-08-04 | 2025-01-31 | 2025-03-15 | 112
C-52-0102-FENCE-1020 | Compaction & Testing for Fence Foundation (BVS-02 to BVS-01) | 35 | 35 | 2025-05-10 | 2025-08-09 | 2025-02-04 | 2025-03-20 | 112
Concrete Works for fence posts from BVS-01 to BVS-02CCOP52CS54.6 |  | 35 | 35 | 2025-07-11 | 2025-10-08 | 2025-02-08 | 2025-03-26 | 112
C-52-0102-FENCE-1030 | Concrete Works (Blinding) for Fence Foundation (BVS-02 to BVS-01) | 35 | 35 | 2025-07-11 | 2025-10-08 | 2025-02-08 | 2025-03-26 | 112
Concrete Protection for fence from BVS-01 to BVS-02CCOP52CS55.6 |  | 35 | 35 | 2025-07-14 | 2025-10-10 | 2025-02-11 | 2025-03-29 | 112
C-52-0102-FENCE-1040 | Concrete Protection (Blinding) for Fence Foundation (BVS-02 to BVS-01) | 35 | 35 | 2025-07-14 | 2025-10-10 | 2025-02-11 | 2025-03-29 | 112
Fence Installation (Type3) from BVS-01 to BVS-02CCOP52CS57.6 |  | 38 | 38 | 2025-08-23 | 2025-10-22 | 2025-02-14 | 2025-04-09 | 112
C-52-0102-FENCE-1050 | Installation of Fence Post (Including Foundation) (BVS-02 to BVS-01) | 35 | 35 | 2025-08-23 | 2025-10-18 | 2025-02-14 | 2025-04-05 | 112
C-52-0102-FENCE-1070 | Installation of Fence Mesh (BVS-02 to BVS-01) | 35 | 35 | 2025-08-27 | 2025-10-22 | 2025-02-18 | 2025-04-09 | 112
Backfilling for Fence from BVS-01 to BVS-02CCOP52CS56.6 |  | 35 | 35 | 2025-08-25 | 2025-10-20 | 2025-02-15 | 2025-04-07 | 112
C-52-0102-FENCE-1060 | Back Filliing of Fence Post Foundation (BVS-02 to BVS-01) | 35 | 35 | 2025-08-25 | 2025-10-20 | 2025-02-15 | 2025-04-07 | 112
Precasting for fence posts from BVS-03 to BVS-04CCOP52CS52.4 |  | 30 | 30 | 2025-01-15 | 2025-02-18 | 2024-11-19 | 2024-12-25 | 109
C-52-0304-FENCE-1000 | Pre-Casting of Fence Foundation (BVS-03 to BVS-04) | 30 | 30 | 2025-01-15 | 2025-02-18 | 2024-11-19 | 2024-12-25 | 109
Excavation Works for fence posts from BVS-03 to BVS-04CCOP52CS53.4 |  | 50 | 50 | 2025-07-25 | 2025-09-23 | 2025-05-16 | 2025-07-17 | 64
C-52-0304-FENCE-1010 | Earth Works for Fence Foundation (BVS-03 to BVS-04) | 45 | 45 | 2025-07-25 | 2025-09-17 | 2025-05-16 | 2025-07-11 | 64
C-52-0304-FENCE-1020 | Compaction & Testing for Fence Foundation (BVS-03 to BVS-04) | 45 | 45 | 2025-07-31 | 2025-09-23 | 2025-05-22 | 2025-07-17 | 64
Concrete Works for fence posts from BVS-03 to BVS-04CCOP52CS54.4 |  | 45 | 45 | 2025-08-04 | 2025-09-26 | 2025-05-26 | 2025-07-21 | 64
C-52-0304-FENCE-1030 | Concrete Works (Blinding) for Fence Foundation (BVS-03 to BVS-04) | 45 | 45 | 2025-08-04 | 2025-09-26 | 2025-05-26 | 2025-07-21 | 64
Concrete Protection for fence from BVS-03 to BVS-04CCOP52CS55.4 |  | 45 | 45 | 2025-08-06 | 2025-09-29 | 2025-05-28 | 2025-07-23 | 64
C-52-0304-FENCE-1040 | Concrete Protection (Blinding) for Fence Foundation (BVS-03 to BVS-04) | 45 | 45 | 2025-08-06 | 2025-09-29 | 2025-05-28 | 2025-07-23 | 64
Fence Installation (Type3) from BVS-03 to BVS-04CCOP52CS57.4 |  | 26 | 26 | 2025-09-10 | 2025-10-10 | 2025-07-04 | 2025-08-04 | 64
C-52-0304-FENCE-1050 | Installation of Fence Post (Including Foundation) (BVS-03 to BVS-04) | 23 | 23 | 2025-09-10 | 2025-10-07 | 2025-07-04 | 2025-07-31 | 64
C-52-0304-FENCE-1070 | Installation of Fence Mesh (BVS-03 to BVS-04) | 23 | 23 | 2025-09-13 | 2025-10-10 | 2025-07-08 | 2025-08-04 | 64
Backfilling for Fence from BVS-03 to BVS-04CCOP52CS56.4 |  | 23 | 23 | 2025-09-11 | 2025-10-08 | 2025-07-05 | 2025-08-01 | 64
C-52-0304-FENCE-1060 | Back Filliing of Fence Post Foundation (BVS-03 to BVS-04) | 23 | 23 | 2025-09-11 | 2025-10-08 | 2025-07-05 | 2025-08-01 | 64
Precasting for fence posts from BVS-04 to BVS-05CCOP52CS52.3 |  | 30 | 30 | 2025-02-19 | 2025-04-04 | 2024-12-26 | 2025-01-30 | 109
C-52-0405-FENCE-1000 | Pre-Casting of Fence Foundation (BVS-04 to BVS-05) | 30 | 30 | 2025-02-19 | 2025-04-04 | 2024-12-26 | 2025-01-30 | 109
Excavation Works for fence posts from BVS-04 to BVS-05CCOP52CS53.3 |  | 50 | 50 | 2025-06-25 | 2025-08-23 | 2025-05-31 | 2025-08-01 | 37
C-52-0405-FENCE-1010 | Earth Works for Fence Foundation (BVS-04 to BVS-05) | 45 | 45 | 2025-06-25 | 2025-08-18 | 2025-05-31 | 2025-07-26 | 37
C-52-0405-FENCE-1020 | Compaction & Testing for Fence Foundation (BVS-04 to BVS-05) | 45 | 45 | 2025-07-02 | 2025-08-23 | 2025-06-09 | 2025-08-01 | 37
Concrete Works for fence posts from BVS-04 to BVS-05CCOP52CS54.3 |  | 45 | 45 | 2025-07-05 | 2025-08-27 | 2025-06-12 | 2025-08-05 | 37
C-52-0405-FENCE-1030 | Concrete Works (Blinding) for Fence Foundation (BVS-04 to BVS-05) | 45 | 45 | 2025-07-05 | 2025-08-27 | 2025-06-12 | 2025-08-05 | 37
Concrete Protection for fence from BVS-04 to BVS-05CCOP52CS55.3 |  | 45 | 45 | 2025-07-08 | 2025-08-29 | 2025-06-14 | 2025-08-07 | 37
C-52-0405-FENCE-1040 | Concrete Protection (Blinding) for Fence Foundation (BVS-04 to BVS-05) | 45 | 45 | 2025-07-08 | 2025-08-29 | 2025-06-14 | 2025-08-07 | 37
Fence Installation (Type3) from BVS-04 to BVS-05CCOP52CS57.3 |  | 27 | 27 | 2025-08-26 | 2025-09-27 | 2025-08-04 | 2025-09-04 | 37
C-52-0405-FENCE-1050 | Installation of Fence Post (Including Foundation) (BVS-04 to BVS-05) | 24 | 24 | 2025-08-26 | 2025-09-24 | 2025-08-04 | 2025-09-01 | 37
C-52-0405-FENCE-1070 | Installation of Fence Mesh (BVS-04 to BVS-05) | 24 | 24 | 2025-08-29 | 2025-09-27 | 2025-08-07 | 2025-09-04 | 37
Backfilling for Fence from BVS-04 to BVS-05CCOP52CS56.3 |  | 24 | 24 | 2025-08-27 | 2025-09-25 | 2025-08-05 | 2025-09-02 | 37
C-52-0405-FENCE-1060 | Back Filliing of Fence Post Foundation (BVS-04 to BVS-05) | 24 | 24 | 2025-08-27 | 2025-09-25 | 2025-08-05 | 2025-09-02 | 37
Precasting for fence posts from BVS-05 to BVS-06CCOP52CS52.2 |  | 35 | 35 | 2025-04-04 | 2025-05-22 | 2025-01-31 | 2025-03-15 | 109
C-52-0506-FENCE-1000 | Pre-Casting of Fence Foundation (BVS-05 to BVS-06) | 35 | 35 | 2025-04-04 | 2025-05-22 | 2025-01-31 | 2025-03-15 | 109
Excavation Works for fence posts from BVS-05 to BVS-06CCOP52CS53.2 |  | 65 | 65 | 2025-06-30 | 2025-09-15 | 2025-06-09 | 2025-08-25 | 49
C-52-0506-FENCE-1010 | Earth Works for Fence Foundation (BVS-05 to BVS-06) | 60 | 60 | 2025-06-30 | 2025-09-09 | 2025-06-09 | 2025-08-19 | 49
C-52-0506-FENCE-1020 | Compaction & Testing for Fence Foundation (BVS-05 to BVS-06) | 60 | 60 | 2025-07-05 | 2025-09-15 | 2025-06-14 | 2025-08-25 | 49
Concrete Works for fence posts from BVS-05 to BVS-06CCOP52CS54.2 |  | 60 | 60 | 2025-07-09 | 2025-09-18 | 2025-06-18 | 2025-08-28 | 49
C-52-0506-FENCE-1030 | Concrete Works (Blinding) for Fence Foundation (BVS-05 to BVS-06) | 60 | 60 | 2025-07-09 | 2025-09-18 | 2025-06-18 | 2025-08-28 | 49
Concrete Protection for fence from BVS-05 to BVS-06CCOP52CS55.2 |  | 60 | 60 | 2025-07-11 | 2025-09-20 | 2025-06-20 | 2025-08-30 | 49
C-52-0506-FENCE-1040 | Concrete Protection (Blinding) for Fence Foundation (BVS-05 to BVS-06) | 60 | 60 | 2025-07-11 | 2025-09-20 | 2025-06-20 | 2025-08-30 | 49
Fence Installation (Type3) from BVS-05 to BVS-06CCOP52CS57.2 |  | 36 | 36 | 2025-08-16 | 2025-10-02 | 2025-07-31 | 2025-09-12 | 49
C-52-0506-FENCE-1050 | Installation of Fence Post (Including Foundation) (BVS-05 to BVS-06) | 33 | 33 | 2025-08-16 | 2025-09-29 | 2025-07-31 | 2025-09-09 | 49
C-52-0506-FENCE-1070 | Installation of Fence Mesh (BVS-05 to BVS-06) | 33 | 33 | 2025-08-20 | 2025-10-02 | 2025-08-04 | 2025-09-12 | 49
Backfilling for Fence from BVS-05 to BVS-06CCOP52CS56.2 |  | 36 | 36 | 2025-08-18 | 2025-09-30 | 2025-08-01 | 2025-09-13 | 49
C-52-0506-FENCE-1060 | Back Filliing of Fence Post Foundation (BVS-05 to BVS-06) | 36 | 36 | 2025-08-18 | 2025-09-30 | 2025-08-01 | 2025-09-13 | 49
Precasting for fence posts from BVS-06 to CRS SweihanCCOP52CS52.1 |  | 40 | 40 | 2025-06-10 | 2025-07-28 | 2025-04-08 | 2025-05-26 | 109
C-52-06CR-FENCE-1000 | Pre-Casting of Fence Foundation (BVS-06 to Sweihan-CRS) | 40 | 40 | 2025-06-10 | 2025-07-28 | 2025-04-08 | 2025-05-26 | 109
Excavation Works for Fence from BVS-06 to CRS SweihanCCOP52CS53.1 |  | 50 | 50 | 2025-08-05 | 2025-10-15 | 2025-08-09 | 2025-10-08 | 10
C-52-06CR-FENCE-1010 | Earth Works for Fence Foundation (BVS-06 to Sweihan-CRS) | 45 | 45 | 2025-08-05 | 2025-10-09 | 2025-08-09 | 2025-10-02 | 10
C-52-06CR-FENCE-1020 | Compaction & Testing for Fence Foundation (BVS-06 to Sweihan-CRS) | 45 | 45 | 2025-08-11 | 2025-10-15 | 2025-08-15 | 2025-10-08 | 10
Concrete Works for Fence from BVS-06 to CRS SweihanCCOP52CS54.1 |  | 45 | 45 | 2025-08-14 | 2025-10-18 | 2025-08-19 | 2025-10-11 | 10
C-52-06CR-FENCE-1030 | Concrete Works (Blinding) for Fence Foundation (BVS-06 to Sweihan-CRS) | 45 | 45 | 2025-08-14 | 2025-10-18 | 2025-08-19 | 2025-10-11 | 10
Concrete Protection for Fence from BVS-06 to CRS SweihanCCOP52CS55.1 |  | 45 | 45 | 2025-08-16 | 2025-10-21 | 2025-08-21 | 2025-10-14 | 10
C-52-06CR-FENCE-1040 | Concrete Protection (Blinding) for Fence Foundation (BVS-06 to Sweihan-CRS) | 45 | 45 | 2025-08-16 | 2025-10-21 | 2025-08-21 | 2025-10-14 | 10
Fence Installation (Type3) from BVS-06 to CRS SweihanCCOP52CS57.1 |  | 36 | 36 | 2025-09-20 | 2025-11-01 | 2025-09-09 | 2025-10-21 | 10
C-52-06CR-FENCE-1050 | Installation of Fence Post (Including Foundation) (BVS-06 to Sweihan-CRS) | 33 | 33 | 2025-09-20 | 2025-10-29 | 2025-09-09 | 2025-10-17 | 10
C-52-06CR-FENCE-1070 | Installation of Fence Mesh (BVS-06 to Sweihan-CRS) | 33 | 33 | 2025-09-24 | 2025-11-01 | 2025-09-12 | 2025-10-21 | 10
Backfilling for Fence from BVS-06 to CRS SweihanCCOP52CS56.1 |  | 35 | 35 | 2025-09-22 | 2025-10-30 | 2025-09-10 | 2025-10-21 | 10
C-52-06CR-FENCE-1060 | Back Filliing of Fence Post Foundation (BVS-06 to Sweihan-CRS) | 35 | 35 | 2025-09-22 | 2025-10-30 | 2025-09-10 | 2025-10-21 | 10
598-BVS-01 (52'' Pipeline) |  | 418 | 222 | 2024-03-26 | 2025-09-10 | 26-Mar-24 A | 2025-08-26 | 27
598-BVS-01 (52'' Pipeline)-1 |  | 418 | 222 | 2024-03-26 | 2025-09-10 | 26-Mar-24 A | 2025-08-26 | 27
Civil Works |  | 418 | 222 | 2024-03-26 | 2025-09-10 | 26-Mar-24 A | 2025-08-26 | 27
Earthworks, Site Preparation, Site GradingCCOB652C33 |  | 262 | 66 | 2024-03-26 | 2024-12-23 | 26-Mar-24 A | 2025-02-10 | 36
C-52-598-01-CI-1000 | Site Survey, Preparation & Grading Works | 61 | 0 | 2024-03-26 | 2024-06-12 | 26-Mar-24 A | 12-Jun-24 A
C-52-598-01-CI-1010 | Earth Works for Equipment Foundations & Hard Stand Area | 14 | 14 | 2024-10-05 | 2024-10-21 | 2024-11-22 | 2024-12-10 | 27
C-52-598-01-CI-1020 | Earth Works for Pipe Support Foundations | 14 | 14 | 2024-10-22 | 2024-11-06 | 2024-12-11 | 2024-12-26 | 36
C-52-598-01-CI-1030 | Earth Works for Field Instrument Foundations | 12 | 12 | 2024-11-07 | 2024-11-20 | 2024-12-27 | 2025-01-10 | 36
C-52-598-01-CI-1040 | Earth Works for Access Platforms & Misc. Structural Foundations | 14 | 14 | 2024-11-21 | 2024-12-09 | 2025-01-11 | 2025-01-27 | 36
C-52-598-01-CI-1050 | Earth Works for Light Pole, Fence & Gates Foundation | 12 | 12 | 2024-12-10 | 2024-12-23 | 2025-01-28 | 2025-02-10 | 36
Compaction & TestingCCOB652C35 |  | 43 | 43 | 2024-11-07 | 2024-12-28 | 2024-12-27 | 2025-02-15 | 84
C-52-598-01-CI-1200 | Compaction & Testing for Equipment Foundations & Hard Stand Area | 5 | 5 | 2024-11-07 | 2024-11-12 | 2024-12-27 | 2025-01-02 | 27
C-52-598-01-CI-1220 | Compaction & Testing for Field Instrument Foundations | 5 | 5 | 2024-11-21 | 2024-11-26 | 2025-01-11 | 2025-01-16 | 36
C-52-598-01-CI-1210 | Compaction & Testing for Pipe Support Foundations | 5 | 5 | 2024-11-23 | 2024-11-28 | 2025-01-14 | 2025-01-18 | 108
C-52-598-01-CI-1230 | Compaction & Testing for Access Platform & Misc. Structural Foundations | 5 | 5 | 2024-12-10 | 2024-12-14 | 2025-01-28 | 2025-02-01 | 36
C-52-598-01-CI-1240 | Compaction & Testing for Light Pole, Fence & Gates Foundation | 5 | 5 | 2024-12-24 | 2024-12-28 | 2025-02-11 | 2025-02-15 | 36
Concrete Works (Foundations for Equipment)CCOB652C36 |  | 68 | 68 | 2024-12-05 | 2025-02-22 | 2025-01-03 | 2025-03-29 | 27
C-52-598-01-CI-1400 | Concrete Works for Equipment Foundations & Hard Stand Area | 21 | 21 | 2024-12-05 | 2024-12-28 | 2025-01-03 | 2025-01-27 | 27
C-52-598-01-CI-1410 | Concrete Works for Field Instrument, JB Foundations | 14 | 14 | 2024-12-30 | 2025-01-15 | 2025-01-28 | 2025-02-12 | 27
C-52-598-01-CI-1420 | Concrete Works for Access Platform & Misc. Structural Foundations | 12 | 12 | 2025-01-16 | 2025-01-29 | 2025-02-13 | 2025-02-26 | 27
C-52-598-01-CI-1430 | Concrete Works for Light Pole, Fence & Gates Foundation | 21 | 21 | 2025-01-30 | 2025-02-22 | 2025-02-27 | 2025-03-29 | 27
Concrete Works (Foundations for Pipe Supports)CCOB652C37 |  | 21 | 21 | 2024-12-30 | 2025-01-23 | 2025-01-28 | 2025-02-20 | 101
C-52-598-01-CI-1600 | Concrete Works for Pipe Support Foundations | 21 | 21 | 2024-12-30 | 2025-01-23 | 2025-01-28 | 2025-02-20 | 101
Trenching for CablesCCOB652C40 |  | 37 | 37 | 2024-12-24 | 2025-02-14 | 2025-02-11 | 2025-04-04 | 121
C-52-598-01-CI-1800 | Electrical & Earthing Cable Trenching | 30 | 30 | 2024-12-24 | 2025-01-28 | 2025-02-11 | 2025-03-22 | 121
C-52-598-01-CI-1810 | Instrument & Telecom Cable Trenching | 30 | 30 | 2025-01-11 | 2025-02-14 | 2025-02-19 | 2025-04-04 | 121
Pipe Supports Fabrication & InstallationCCOB652S52 |  | 14 | 14 | 2025-02-17 | 2025-03-05 | 2025-03-12 | 2025-04-05 | 93
C-52-598-01-CI-2000 | Pre-Fabrication & Installation of Pipe Supports | 14 | 14 | 2025-02-17 | 2025-03-05 | 2025-03-12 | 2025-04-05 | 93
Fences & Gates ConstructionCCOB652C39 |  | 79 | 79 | 2025-02-24 | 2025-07-05 | 2025-03-29 | 2025-07-08 | 27
C-52-598-01-CI-2200 | Installation of Concrete Pillers for Boundary Wall | 21 | 21 | 2025-02-24 | 2025-03-24 | 2025-03-29 | 2025-04-26 | 27
C-52-598-01-CI-2210 | Block Works for Boundary Wall | 21 | 21 | 2025-03-25 | 2025-04-23 | 2025-04-10 | 2025-05-05 | 27
C-52-598-01-CI-2220 | Installation of Fence Post & Mesh Works (Type-4 & 3) | 30 | 30 | 2025-05-02 | 2025-06-10 | 2025-05-05 | 2025-06-12 | 27
C-52-598-01-CI-2230 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | 21 | 21 | 2025-06-10 | 2025-07-05 | 2025-06-12 | 2025-07-08 | 27
Fire Point SheltersCCOB652S54 |  | 8 | 8 | 2025-04-28 | 2025-05-07 | 2025-05-09 | 2025-05-17 | 101
C-52-598-01-CI-2400 | Installation of Fire Point Shelters | 8 | 8 | 2025-04-28 | 2025-05-07 | 2025-05-09 | 2025-05-17 | 101
Paving WorksCCOB652C42 |  | 42 | 42 | 2025-07-05 | 2025-09-10 | 2025-07-08 | 2025-08-26 | 27
C-52-598-01-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 28 | 28 | 2025-07-05 | 2025-08-07 | 2025-07-08 | 2025-08-09 | 27
C-52-598-01-CI-2610 | Rip-Rap Protection Laying | 28 | 28 | 2025-08-07 | 2025-09-10 | 2025-07-24 | 2025-08-26 | 27
Backfilling for CablesCCOB652C41 |  | 15 | 15 | 2025-05-09 | 2025-05-27 | 2025-05-07 | 2025-05-24 | 103
C-52-598-01-CI-2800 | Back Filling for Electrical & Earthing Cable | 14 | 14 | 2025-05-09 | 2025-05-26 | 2025-05-07 | 2025-05-23 | 104
C-52-598-01-CI-2810 | Back Filling for Instrument & Telecom Cable | 14 | 14 | 2025-05-10 | 2025-05-27 | 2025-05-08 | 2025-05-24 | 103
Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB652S56 |  | 42 | 42 | 2025-03-05 | 2025-05-14 | 2025-04-05 | 2025-05-24 | 103
C-52-598-01-CI-3000 | Pre-Fabrication & Installation of Platforms & Crossovers | 28 | 28 | 2025-03-05 | 2025-04-16 | 2025-04-05 | 2025-05-08 | 114
C-52-598-01-CI-3010 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | 14 | 14 | 2025-04-28 | 2025-05-14 | 2025-05-09 | 2025-05-24 | 103
Mechanical Works & Equipment Installation |  | 8 | 8 | 2025-07-08 | 2025-07-17 | 2025-05-19 | 2025-05-27 | 101
Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB652M52 |  | 8 | 8 | 2025-07-08 | 2025-07-17 | 2025-05-19 | 2025-05-27 | 101
C-52-598-01-ME-1000 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | 8 | 8 | 2025-07-08 | 2025-07-17 | 2025-05-19 | 2025-05-27 | 101
Piping Works |  | 121 | 121 | 2025-01-03 | 2025-04-29 | 2025-02-24 | 2025-07-28 | 51
Piping Pre-FabricationCCOB652P052 |  | 21 | 21 | 2025-01-03 | 2025-01-27 | 2025-02-24 | 2025-03-24 | 99
C-52-598-01-PI-1000 | Piping Pre-Fabrication | 21 | 21 | 2025-01-03 | 2025-01-27 | 2025-02-24 | 2025-03-24 | 99
ErectionCCOB652P062 |  | 14 | 14 | 2025-03-20 | 2025-04-11 | 2025-04-05 | 2025-04-22 | 93
C-52-598-01-PI-1200 | Piping Erection | 14 | 14 | 2025-03-20 | 2025-04-11 | 2025-04-05 | 2025-04-22 | 93
Field Joint Welding & NDTCCOB652P072 |  | 15 | 15 | 2025-03-22 | 2025-04-15 | 2025-04-08 | 2025-04-25 | 116
C-52-598-01-PI-1400 | Field Joint Welding (Including Isolation Joint) | 12 | 12 | 2025-03-22 | 2025-04-11 | 2025-04-08 | 2025-04-22 | 116
C-52-598-01-PI-1410 | NDT & Coating for Field Joint Weld | 12 | 12 | 2025-03-27 | 2025-04-15 | 2025-04-11 | 2025-04-25 | 116
HydrotestingCCOB652P082 |  | 5 | 5 | 2025-04-15 | 2025-04-21 | 2025-04-25 | 2025-05-01 | 116
C-52-598-01-PI-1600 | Hydrotesting | 5 | 5 | 2025-04-15 | 2025-04-21 | 2025-04-25 | 2025-05-01 | 116
Installation of ValvesCCOB652P092 |  | 5 | 5 | 2025-04-21 | 2025-04-26 | 2025-07-21 | 2025-07-25 | 51
C-52-598-01-PI-1800 | Installation of Valves & GOV | 5 | 5 | 2025-04-21 | 2025-04-26 | 2025-07-21 | 2025-07-25 | 51
Final Bolt Torquing/ Re-InstatementCCOB652P102 |  | 3 | 3 | 2025-04-25 | 2025-04-29 | 2025-07-25 | 2025-07-28 | 51
C-52-598-01-PI-2000 | Final Bolt Torquing/ Re-Instatement | 3 | 3 | 2025-04-25 | 2025-04-29 | 2025-07-25 | 2025-07-28 | 51
Pipeline Works |  | 96 | 96 | 2025-01-28 | 2025-03-01 | 2025-03-25 | 2025-07-23 | 55
Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 |  | 96 | 96 | 2025-01-28 | 2025-03-01 | 2025-03-25 | 2025-07-23 | 55
C-52-598-01-PL-1000 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | 5 | 5 | 2025-01-28 | 2025-02-01 | 2025-03-25 | 2025-04-04 | 122
C-52-598-01-PL-1010 | Lowering of Pipeline Section | 2 | 2 | 2025-02-03 | 2025-02-04 | 2025-04-04 | 2025-04-07 | 122
C-52-598-01-PL-1020 | Section Tie-in Welding (Including Barred Tee) | 12 | 12 | 2025-02-03 | 2025-02-15 | 2025-04-04 | 2025-04-18 | 122
C-52-598-01-PL-1030 | NDT for Tie-in Joint | 12 | 12 | 2025-02-04 | 2025-02-17 | 2025-04-05 | 2025-04-19 | 122
C-52-598-01-PL-1040 | Ext. Coating for Tie-in Joint | 12 | 12 | 2025-02-05 | 2025-02-18 | 2025-04-07 | 2025-04-21 | 122
C-52-598-01-PL-1050 | Holiday Testing of Pipeline Section | 1 | 1 | 2025-02-19 | 2025-02-19 | 2025-04-21 | 2025-04-22 | 122
C-52-598-01-PL-1060 | Installation of ROV | 1 | 1 | 2025-02-20 | 2025-02-20 | 2025-07-21 | 2025-07-21 | 55
C-52-598-01-PL-1070 | Installation of Pig Signaller Pit | 1 | 1 | 2025-02-21 | 2025-02-21 | 2025-07-22 | 2025-07-22 | 55
C-52-598-01-PL-1080 | Installation of Pig Signaller | 1 | 1 | 2025-02-22 | 2025-02-22 | 2025-07-23 | 2025-07-23 | 55
C-52-598-01-PL-1090 | Padding & Backfilling | 9 | 9 | 2025-02-20 | 2025-03-01 | 2025-07-14 | 2025-07-23 | 55
Electrical & Instrumentation Works |  | 61 | 61 | 2025-02-17 | 2025-07-10 | 2025-04-18 | 2025-07-02 | 73
Hybrid Passive Cooling Shelter InstallationCCOB652E51 |  | 3 | 3 | 2025-02-17 | 2025-02-19 | 2025-04-25 | 2025-04-29 | 108
C-52-598-01-EI-1000 | Installation of Passive Cooling Shelter | 3 | 3 | 2025-02-17 | 2025-02-19 | 2025-04-25 | 2025-04-29 | 108
Solar Power SystemCCOB652E65 |  | 26 | 26 | 2025-05-12 | 2025-06-13 | 2025-05-03 | 2025-06-03 | 73
C-52-598-01-EI-1210 | Installation of Solar Panel Structural Supports | 12 | 12 | 2025-05-12 | 2025-05-26 | 2025-05-03 | 2025-05-17 | 73
C-52-598-01-EI-1200 | Installation of Solar S/m (Including Panels, UPS & Battery) | 14 | 14 | 2025-05-26 | 2025-06-13 | 2025-05-19 | 2025-06-03 | 73
Deep Earth WellCCOB652E53 |  | 3 | 3 | 2025-05-29 | 2025-05-31 | 2025-05-30 | 2025-06-02 | 91
C-52-598-01-EI-1400 | Deep Earth Well Drilling | 3 | 3 | 2025-05-29 | 2025-05-31 | 2025-05-30 | 2025-06-02 | 91
RTUCCOB652E75 |  | 2 | 2 | 2025-02-20 | 2025-02-21 | 2025-04-29 | 2025-05-01 | 108
C-52-598-01-EI-1600 | Installation of RTU | 2 | 2 | 2025-02-20 | 2025-02-21 | 2025-04-29 | 2025-05-01 | 108
Light Pole, Lighting & FixturesCCOB652E85 |  | 9 | 9 | 2025-06-13 | 2025-06-24 | 2025-06-04 | 2025-06-16 | 73
C-52-598-01-EI-1800 | Installation of Light Pole, Lighting & Fixtures | 6 | 6 | 2025-06-13 | 2025-06-20 | 2025-06-04 | 2025-06-12 | 73
C-52-598-01-EI-1810 | Installation of Lighting & Instrument JB's | 3 | 3 | 2025-06-20 | 2025-06-24 | 2025-06-13 | 2025-06-16 | 73
E&I Cable Laying, Glanding & TerminationCCOB652E55 |  | 61 | 61 | 2025-04-21 | 2025-07-10 | 2025-04-18 | 2025-07-02 | 73
C-52-598-01-EI-2000 | Electrical & Earthing Cable Laying | 6 | 6 | 2025-04-21 | 2025-04-26 | 2025-04-18 | 2025-04-24 | 103
C-52-598-01-EI-2010 | Instrument Cable Laying | 6 | 6 | 2025-04-28 | 2025-05-03 | 2025-04-25 | 2025-05-01 | 103
C-52-598-01-EI-2020 | Installation of Cable Trays | 6 | 6 | 2025-05-05 | 2025-05-12 | 2025-05-02 | 2025-05-09 | 106
C-52-598-01-EI-2030 | Instrument Tubing Works | 5 | 5 | 2025-05-12 | 2025-05-17 | 2025-05-09 | 2025-05-15 | 106
C-52-598-01-EI-2040 | Loop Checking for Instruments | 8 | 8 | 2025-06-24 | 2025-07-04 | 2025-06-17 | 2025-06-25 | 73
C-52-598-01-EI-2050 | Glanding & Termination | 5 | 5 | 2025-07-04 | 2025-07-10 | 2025-06-26 | 2025-07-02 | 73
Field InstrumentsCCOB652E95 |  | 20 | 20 | 2025-04-11 | 2025-05-24 | 2025-04-22 | 2025-05-15 | 93
C-52-598-01-EI-2210 | Pre-Fabrication & Installation of Field Instrument, JB Supports | 14 | 14 | 2025-04-11 | 2025-04-28 | 2025-04-22 | 2025-05-08 | 93
C-52-598-01-EI-2200 | Installation of Field Instruments | 6 | 6 | 2025-05-17 | 2025-05-24 | 2025-05-09 | 2025-05-15 | 93
F&G DevicesCCOB652E105 |  | 16 | 16 | 2025-02-22 | 2025-05-30 | 2025-05-01 | 2025-05-21 | 93
C-52-598-01-EI-2400 | Installation of F&G Panel | 2 | 2 | 2025-02-22 | 2025-02-24 | 2025-05-01 | 2025-05-03 | 108
C-52-598-01-EI-2410 | Installation of F&G Devices | 5 | 5 | 2025-05-24 | 2025-05-30 | 2025-05-16 | 2025-05-21 | 93
Cathodic Protection Works |  | 14 | 14 | 2025-04-28 | 2025-05-14 | 2025-04-25 | 2025-05-12 | 114
CP Anode Bed Installation (subcontract)CCOB652E30 |  | 14 | 14 | 2025-04-28 | 2025-05-14 | 2025-04-25 | 2025-05-12 | 114
C-52-598-01-CA-1000 | CP Cable Laying | 5 | 5 | 2025-04-28 | 2025-05-02 | 2025-04-25 | 2025-04-30 | 104
C-52-598-01-CA-1010 | Installation of CP Test Post | 3 | 3 | 2025-05-03 | 2025-05-07 | 2025-05-01 | 2025-05-03 | 114
C-52-598-01-CA-1020 | Installation of CP S/m | 6 | 6 | 2025-05-07 | 2025-05-14 | 2025-05-05 | 2025-05-12 | 114
Telecommunication Works |  | 17 | 17 | 2025-05-31 | 2025-06-21 | 2025-05-28 | 2025-06-18 | 84
SDH CabinetCCOB652I31 |  | 3 | 3 | 2025-05-31 | 2025-06-03 | 2025-05-28 | 2025-05-30 | 84
C-52-598-01-TE-1000 | Installation of SDH Cabinet | 3 | 3 | 2025-05-31 | 2025-06-03 | 2025-05-28 | 2025-05-30 | 84
PIDS SystemCCOB652I41 |  | 3 | 3 | 2025-06-04 | 2025-06-09 | 2025-05-31 | 2025-06-03 | 84
C-52-598-01-TE-1200 | Installation of PIDS/ PLDS System | 3 | 3 | 2025-06-04 | 2025-06-09 | 2025-05-31 | 2025-06-03 | 84
Telephone SystemCCOB652I51 |  | 6 | 6 | 2025-06-16 | 2025-06-21 | 2025-06-12 | 2025-06-18 | 84
C-52-598-01-TE-1400 | Installation of Telephone System | 6 | 6 | 2025-06-16 | 2025-06-21 | 2025-06-12 | 2025-06-18 | 84
CCTV SystemCCOB652I61 |  | 5 | 5 | 2025-06-10 | 2025-06-14 | 2025-06-04 | 2025-06-11 | 84
C-52-598-01-TE-1600 | Installation of CCTV System | 5 | 5 | 2025-06-10 | 2025-06-14 | 2025-06-04 | 2025-06-11 | 84
598-BVS-02 (52'' Pipeline) |  | 386 | 220 | 2024-05-15 | 2025-08-05 | 15-May-24 A | 2025-09-01 | 22
598-BVS-02 (52'' Pipeline)-1 |  | 386 | 220 | 2024-05-15 | 2025-08-05 | 15-May-24 A | 2025-09-01 | 22
Civil Works |  | 386 | 220 | 2024-05-15 | 2025-08-05 | 15-May-24 A | 2025-09-01 | 22
Earthworks, Site Preparation, Site GradingCCOB552C33 |  | 225 | 59 | 2024-05-15 | 2024-11-23 | 15-May-24 A | 2025-02-10 | 22
C-52-598-02-CI-1000 | Site Survey, Preparation & Grading Works | 58 | 0 | 2024-05-15 | 2024-07-26 | 15-May-24 A | 26-Jul-24 A
C-52-598-02-CI-1010 | Earth Works for Equipment Foundations & Hard Stand Area | 14 | 14 | 2024-09-17 | 2024-10-02 | 2024-11-30 | 2024-12-18 | 22
C-52-598-02-CI-1020 | Earth Works for Pipe Support Foundations | 14 | 14 | 2024-09-25 | 2024-10-10 | 2024-12-11 | 2024-12-26 | 22
C-52-598-02-CI-1030 | Earth Works for Field Instrument Foundations | 12 | 12 | 2024-10-11 | 2024-10-24 | 2024-12-27 | 2025-01-10 | 22
C-52-598-02-CI-1040 | Earth Works for Access Platforms & Misc. Structural Foundations | 14 | 14 | 2024-10-25 | 2024-11-09 | 2025-01-11 | 2025-01-27 | 22
C-52-598-02-CI-1050 | Earth Works for Light Pole, Fence & Gates Foundation | 12 | 12 | 2024-11-11 | 2024-11-23 | 2025-01-28 | 2025-02-10 | 22
Compaction & TestingCCOB552C34 |  | 52 | 52 | 2024-10-28 | 2024-12-06 | 2024-12-19 | 2025-02-18 | 107
C-52-598-02-CI-1200 | Compaction & Testing for Equipment Foundations & Hard Stand Area | 5 | 5 | 2024-11-29 | 2024-12-06 | 2024-12-19 | 2024-12-24 | 154
C-52-598-02-CI-1210 | Compaction & Testing for Pipe Support Foundations | 5 | 5 | 2024-10-28 | 2024-11-01 | 2025-01-14 | 2025-01-18 | 43
C-52-598-02-CI-1220 | Compaction & Testing for Field Instrument Foundations | 5 | 5 | 2024-11-11 | 2024-11-15 | 2025-01-28 | 2025-02-01 | 78
C-52-598-02-CI-1240 | Compaction & Testing for Light Pole, Fence & Gates Foundation | 5 | 5 | 2024-11-25 | 2024-11-29 | 2025-02-11 | 2025-02-15 | 22
C-52-598-02-CI-1230 | Compaction & Testing for Access Platform & Misc. Structural Foundations | 5 | 5 | 2024-11-27 | 2024-12-04 | 2025-02-13 | 2025-02-18 | 77
Concrete Works (Foundations for Equipment)CCOB552C35 |  | 59 | 59 | 2024-12-21 | 2025-01-23 | 2025-01-03 | 2025-03-15 | 109
C-52-598-02-CI-1400 | Concrete Works for Equipment Foundations & Hard Stand Area | 21 | 21 | 2024-12-30 | 2025-01-23 | 2025-01-03 | 2025-01-27 | 147
C-52-598-02-CI-1410 | Concrete Works for Field Instrument, JB Foundations | 14 | 14 | 2025-01-08 | 2025-01-23 | 2025-02-03 | 2025-02-18 | 78
C-52-598-02-CI-1420 | Concrete Works for Access Platform & Misc. Structural Foundations | 12 | 12 | 2024-12-27 | 2025-01-10 | 2025-02-19 | 2025-03-05 | 77
C-52-598-02-CI-1430 | Concrete Works for Light Pole, Fence & Gates Foundation | 21 | 21 | 2024-12-21 | 2025-01-15 | 2025-02-17 | 2025-03-15 | 22
Concrete Works (Foundations for Pipe Supports)CCOB552C37 |  | 21 | 21 | 2024-11-27 | 2024-12-23 | 2025-02-13 | 2025-03-11 | 43
C-52-598-02-CI-1600 | Concrete Works for Pipe Support Foundations | 21 | 21 | 2024-11-27 | 2024-12-23 | 2025-02-13 | 2025-03-11 | 43
Trenching for CablesCCOB552C40 |  | 60 | 60 | 2025-01-29 | 2025-03-28 | 2025-02-11 | 2025-05-01 | 82
C-52-598-02-CI-1800 | Electrical & Earthing Cable Trenching | 30 | 30 | 2025-01-29 | 2025-03-05 | 2025-02-11 | 2025-03-22 | 82
C-52-598-02-CI-1810 | Instrument & Telecom Cable Trenching | 30 | 30 | 2025-02-15 | 2025-03-28 | 2025-03-22 | 2025-05-01 | 82
Pipe Supports Fabrication & InstallationCCOB552S51 |  | 14 | 14 | 2025-01-31 | 2025-02-15 | 2025-03-12 | 2025-04-05 | 36
C-52-598-02-CI-2000 | Pre-Fabrication & Installation of Pipe Supports | 14 | 14 | 2025-01-31 | 2025-02-15 | 2025-03-12 | 2025-04-05 | 36
Fences & Gates ConstructionCCOB552C38 |  | 79 | 79 | 2025-01-16 | 2025-05-28 | 2025-03-15 | 2025-06-26 | 22
C-52-598-02-CI-2200 | Installation of Concrete Pillers for Boundary Wall | 21 | 21 | 2025-01-16 | 2025-02-08 | 2025-03-15 | 2025-04-16 | 22
C-52-598-02-CI-2210 | Block Works for Boundary Wall | 21 | 21 | 2025-02-10 | 2025-03-06 | 2025-03-26 | 2025-04-24 | 22
C-52-598-02-CI-2220 | Installation of Fence Post & Mesh Works (Type-4 & 3) | 30 | 30 | 2025-03-23 | 2025-05-02 | 2025-04-24 | 2025-05-30 | 22
C-52-598-02-CI-2230 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | 21 | 21 | 2025-05-02 | 2025-05-28 | 2025-05-30 | 2025-06-26 | 22
Fire Point SheltersCCOB552S52 |  | 8 | 8 | 2025-04-16 | 2025-04-25 | 2025-04-26 | 2025-05-07 | 81
C-52-598-02-CI-2400 | Installation of Fire Point Shelters | 8 | 8 | 2025-04-16 | 2025-04-25 | 2025-04-26 | 2025-05-07 | 81
Paving WorksCCOB552C39 |  | 56 | 56 | 2025-05-28 | 2025-08-05 | 2025-06-26 | 2025-09-01 | 22
C-52-598-02-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 28 | 28 | 2025-05-28 | 2025-07-03 | 2025-06-26 | 2025-07-30 | 22
C-52-598-02-CI-2610 | Rip-Rap Protection Laying | 28 | 28 | 2025-07-03 | 2025-08-05 | 2025-07-30 | 2025-09-01 | 22
Backfilling for CablesCCOB552C56 |  | 25 | 25 | 2025-04-28 | 2025-05-31 | 2025-05-09 | 2025-06-09 | 92
C-52-598-02-CI-2810 | Back Filling for Instrument & Telecom Cable | 14 | 14 | 2025-04-28 | 2025-05-14 | 2025-05-09 | 2025-05-26 | 103
C-52-598-02-CI-2800 | Back Filling for Electrical & Earthing Cable | 14 | 14 | 2025-05-15 | 2025-05-31 | 2025-05-22 | 2025-06-09 | 92
Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 |  | 33 | 33 | 2025-03-03 | 2025-05-02 | 2025-04-05 | 2025-05-14 | 36
C-52-598-02-CI-3000 | Pre-Fabrication & Installation of Platforms & Crossovers | 28 | 28 | 2025-03-03 | 2025-04-15 | 2025-04-05 | 2025-05-08 | 37
C-52-598-02-CI-3010 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | 14 | 14 | 2025-04-16 | 2025-05-02 | 2025-04-26 | 2025-05-14 | 36
Mechanical Works & Equipment Installation |  | 8 | 8 | 2025-05-31 | 2025-06-12 | 2025-06-13 | 2025-06-23 | 81
Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB552M52 |  | 8 | 8 | 2025-05-31 | 2025-06-12 | 2025-06-13 | 2025-06-23 | 81
C-52-598-02-ME-1000 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | 8 | 8 | 2025-05-31 | 2025-06-12 | 2025-06-13 | 2025-06-23 | 81
Piping Works |  | 121 | 121 | 2025-01-28 | 2025-04-29 | 2025-02-24 | 2025-07-28 | 51
Piping Pre-FabricationCCOB552P051 |  | 21 | 21 | 2025-01-28 | 2025-02-20 | 2025-02-24 | 2025-03-24 | 48
C-52-598-02-PI-1000 | Piping Pre-Fabrication | 21 | 21 | 2025-01-28 | 2025-02-20 | 2025-02-24 | 2025-03-24 | 48
ErectionCCOB552P061 |  | 14 | 14 | 2025-03-20 | 2025-04-11 | 2025-04-05 | 2025-04-22 | 36
C-52-598-02-PI-1200 | Piping Erection | 14 | 14 | 2025-03-20 | 2025-04-11 | 2025-04-05 | 2025-04-22 | 36
Field Joint Welding & NDTCCOB552P071 |  | 15 | 15 | 2025-03-22 | 2025-04-15 | 2025-04-08 | 2025-04-25 | 116
C-52-598-02-PI-1400 | Field Joint Welding (Including Isolation Joint) | 12 | 12 | 2025-03-22 | 2025-04-11 | 2025-04-08 | 2025-04-22 | 48
C-52-598-02-PI-1410 | NDT & Coating for Field Joint Weld | 12 | 12 | 2025-03-27 | 2025-04-15 | 2025-04-11 | 2025-04-25 | 116
HydrotestingCCOB552P081 |  | 5 | 5 | 2025-04-15 | 2025-04-21 | 2025-04-25 | 2025-05-01 | 116
C-52-598-02-PI-1600 | Hydrotesting | 5 | 5 | 2025-04-15 | 2025-04-21 | 2025-04-25 | 2025-05-01 | 116
Installation of ValvesCCOB552P091 |  | 5 | 5 | 2025-04-21 | 2025-04-26 | 2025-07-21 | 2025-07-25 | 51
C-52-598-02-PI-1800 | Installation of Valves & GOV | 5 | 5 | 2025-04-21 | 2025-04-26 | 2025-07-21 | 2025-07-25 | 51
Final Bolt Torquing/ Re-InstatementCCOB552P101 |  | 3 | 3 | 2025-04-25 | 2025-04-29 | 2025-07-25 | 2025-07-28 | 51
C-52-598-02-PI-2000 | Final Bolt Torquing/ Re-Instatement | 3 | 3 | 2025-04-25 | 2025-04-29 | 2025-07-25 | 2025-07-28 | 51
Pipeline Works |  | 96 | 96 | 2025-02-21 | 2025-04-05 | 2025-03-25 | 2025-07-23 | 55
Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 |  | 96 | 96 | 2025-02-21 | 2025-04-05 | 2025-03-25 | 2025-07-23 | 55
C-52-598-02-PL-1000 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | 5 | 5 | 2025-02-21 | 2025-02-26 | 2025-03-25 | 2025-04-04 | 122
C-52-598-02-PL-1010 | Lowering of Pipeline Section | 2 | 2 | 2025-02-27 | 2025-02-28 | 2025-04-04 | 2025-04-07 | 122
C-52-598-02-PL-1020 | Section Tie-in Welding (Including Barred Tee) | 12 | 12 | 2025-02-27 | 2025-03-15 | 2025-04-04 | 2025-04-18 | 122
C-52-598-02-PL-1030 | NDT for Tie-in Joint | 12 | 12 | 2025-02-28 | 2025-03-17 | 2025-04-05 | 2025-04-19 | 122
C-52-598-02-PL-1040 | Ext. Coating for Tie-in Joint | 12 | 12 | 2025-03-01 | 2025-03-18 | 2025-04-07 | 2025-04-21 | 122
C-52-598-02-PL-1050 | Holiday Testing of Pipeline Section | 1 | 1 | 2025-03-19 | 2025-03-20 | 2025-04-21 | 2025-04-22 | 122
C-52-598-02-PL-1060 | Installation of ROV | 1 | 1 | 2025-03-20 | 2025-03-22 | 2025-07-21 | 2025-07-21 | 55
C-52-598-02-PL-1070 | Installation of Pig Signaller Pit | 1 | 1 | 2025-03-22 | 2025-03-23 | 2025-07-22 | 2025-07-22 | 55
C-52-598-02-PL-1080 | Installation of Pig Signaller | 1 | 1 | 2025-03-23 | 2025-03-24 | 2025-07-23 | 2025-07-23 | 55
C-52-598-02-PL-1090 | Padding & Backfilling | 9 | 9 | 2025-03-20 | 2025-04-05 | 2025-07-14 | 2025-07-23 | 55
Electrical & Instrumentation Works |  | 71 | 71 | 2025-02-20 | 2025-07-26 | 2025-04-10 | 2025-07-05 | 70
Hybrid Passive Cooling Shelter InstallationCCOB552E51 |  | 3 | 3 | 2025-02-20 | 2025-02-22 | 2025-04-25 | 2025-04-29 | 97
C-52-598-02-EI-1000 | Installation of Passive Cooling Shelter | 3 | 3 | 2025-02-20 | 2025-02-22 | 2025-04-25 | 2025-04-29 | 97
Solar Power SystemCCOB552E65 |  | 26 | 26 | 2025-05-26 | 2025-07-01 | 2025-05-07 | 2025-06-09 | 70
C-52-598-02-EI-1210 | Installation of Solar Panel Structural Supports | 12 | 12 | 2025-05-26 | 2025-06-11 | 2025-05-07 | 2025-05-22 | 70
C-52-598-02-EI-1200 | Installation of Solar S/m (Including Panels, UPS & Battery) | 14 | 14 | 2025-06-13 | 2025-07-01 | 2025-05-22 | 2025-06-09 | 70
Deep Earth WellCCOB552E53 |  | 3 | 3 | 2025-05-12 | 2025-05-15 | 2025-05-19 | 2025-05-21 | 92
C-52-598-02-EI-1400 | Deep Earth Well Drilling | 3 | 3 | 2025-05-12 | 2025-05-15 | 2025-05-19 | 2025-05-21 | 92
RTUCCOB552E75 |  | 2 | 2 | 2025-02-24 | 2025-02-25 | 2025-04-29 | 2025-05-01 | 97
C-52-598-02-EI-1600 | Installation of RTU | 2 | 2 | 2025-02-24 | 2025-02-25 | 2025-04-29 | 2025-05-01 | 97
Light Pole, Lighting & FixturesCCOB552E85 |  | 9 | 9 | 2025-07-01 | 2025-07-11 | 2025-06-10 | 2025-06-19 | 70
C-52-598-02-EI-1800 | Installation of Light Pole, Lighting & Fixtures | 6 | 6 | 2025-07-01 | 2025-07-08 | 2025-06-10 | 2025-06-16 | 70
C-52-598-02-EI-1810 | Installation of Lighting & Instrument JB's | 3 | 3 | 2025-07-08 | 2025-07-11 | 2025-06-17 | 2025-06-19 | 70
E&I Cable Laying, Glanding & TerminationCCOB552E55 |  | 64 | 64 | 2025-04-14 | 2025-07-26 | 2025-04-18 | 2025-07-05 | 70
C-52-598-02-EI-2000 | Electrical & Earthing Cable Laying | 6 | 6 | 2025-04-14 | 2025-04-19 | 2025-04-18 | 2025-04-24 | 87
C-52-598-02-CA-1000 | CP Cable Laying | 5 | 5 | 2025-04-21 | 2025-04-25 | 2025-04-25 | 2025-04-30 | 109
C-52-598-02-CA-1010 | Installation of CP Test Post | 3 | 3 | 2025-04-26 | 2025-04-29 | 2025-05-01 | 2025-05-03 | 114
C-52-598-02-EI-2010 | Instrument Cable Laying | 6 | 6 | 2025-04-21 | 2025-04-26 | 2025-05-01 | 2025-05-09 | 82
C-52-598-02-CA-1020 | Installation of CP S/m | 6 | 6 | 2025-04-30 | 2025-05-07 | 2025-05-05 | 2025-05-12 | 114
C-52-598-02-EI-2020 | Installation of Cable Trays | 6 | 6 | 2025-04-28 | 2025-05-03 | 2025-05-09 | 2025-05-16 | 82
C-52-598-02-EI-2030 | Instrument Tubing Works | 5 | 5 | 2025-05-05 | 2025-05-10 | 2025-05-16 | 2025-05-22 | 82
C-52-598-02-EI-2040 | Loop Checking for Instruments | 8 | 8 | 2025-07-11 | 2025-07-21 | 2025-06-20 | 2025-06-30 | 70
C-52-598-02-EI-2050 | Glanding & Termination | 5 | 5 | 2025-07-21 | 2025-07-26 | 2025-07-01 | 2025-07-05 | 70
Field InstrumentsCCOB552E95 |  | 41 | 41 | 2025-03-26 | 2025-05-17 | 2025-04-10 | 2025-05-29 | 82
C-52-598-02-EI-2210 | Pre-Fabrication & Installation of Field Instrument, JB Supports | 14 | 14 | 2025-03-26 | 2025-04-16 | 2025-04-10 | 2025-04-26 | 36
C-52-598-02-EI-2200 | Installation of Field Instruments | 6 | 6 | 2025-05-10 | 2025-05-17 | 2025-05-22 | 2025-05-29 | 82
F&G DevicesCCOB552E105 |  | 28 | 28 | 2025-02-26 | 2025-05-23 | 2025-05-01 | 2025-06-04 | 82
C-52-598-02-EI-2400 | Installation of F&G Panel | 2 | 2 | 2025-02-26 | 2025-02-27 | 2025-05-01 | 2025-05-03 | 97
C-52-598-02-EI-2410 | Installation of F&G Devices | 5 | 5 | 2025-05-17 | 2025-05-23 | 2025-05-29 | 2025-06-04 | 82
Telecommunication Works |  | 17 | 17 | 2025-05-28 | 2025-06-18 | 2025-05-28 | 2025-06-18 | 84
SDH CabinetCCOB552I31 |  | 3 | 3 | 2025-05-28 | 2025-05-30 | 2025-05-28 | 2025-05-30 | 84
C-52-598-02-TE-1000 | Installation of SDH Cabinet | 3 | 3 | 2025-05-28 | 2025-05-30 | 2025-05-28 | 2025-05-30 | 84
PIDS SystemCCOB552I41 |  | 3 | 3 | 2025-05-31 | 2025-06-03 | 2025-05-31 | 2025-06-03 | 84
C-52-598-02-TE-1200 | Installation of PIDS/ PLDS System | 3 | 3 | 2025-05-31 | 2025-06-03 | 2025-05-31 | 2025-06-03 | 84
Telephone SystemCCOB552I51 |  | 6 | 6 | 2025-06-12 | 2025-06-18 | 2025-06-12 | 2025-06-18 | 84
C-52-598-02-TE-1400 | Installation of Telephone System | 6 | 6 | 2025-06-12 | 2025-06-18 | 2025-06-12 | 2025-06-18 | 84
CCTV SystemCCOB552I61 |  | 5 | 5 | 2025-06-04 | 2025-06-11 | 2025-06-04 | 2025-06-11 | 84
C-52-598-02-TE-1600 | Installation of CCTV System | 5 | 5 | 2025-06-04 | 2025-06-11 | 2025-06-04 | 2025-06-11 | 84
598-BVS-03 (52'' Pipeline) |  | 348 | 234 | 2024-07-27 | 2025-08-07 | 27-Jul-24 A | 2025-09-26 | 16
598-BVS-03 (52'' Pipeline)-1 |  | 348 | 234 | 2024-07-27 | 2025-08-07 | 27-Jul-24 A | 2025-09-26 | 16
Civil Works |  | 348 | 234 | 2024-07-27 | 2025-07-23 | 27-Jul-24 A | 2025-09-26 | 16
Earthworks, Site Preparation, Site GradingCCOB452C32 |  | 173 | 59 | 2024-07-27 | 2024-11-23 | 27-Jul-24 A | 2025-02-18 | 16
C-52-598-03-CI-1000 | Site Survey, Preparation & Grading Works | 8 | 0 | 2024-07-27 | 2024-08-05 | 27-Jul-24 A | 05-Aug-24 A
C-52-598-03-CI-1010 | Earth Works for Equipment Foundations & Hard Stand Area | 14 | 14 | 2024-09-17 | 2024-10-02 | 2024-12-11 | 2024-12-26 | 16
C-52-598-03-CI-1020 | Earth Works for Pipe Support Foundations | 14 | 14 | 2024-09-25 | 2024-10-10 | 2024-12-19 | 2025-01-04 | 16
C-52-598-03-CI-1030 | Earth Works for Field Instrument Foundations | 12 | 12 | 2024-10-11 | 2024-10-24 | 2025-01-06 | 2025-01-18 | 16
C-52-598-03-CI-1040 | Earth Works for Access Platforms & Misc. Structural Foundations | 14 | 14 | 2024-10-25 | 2024-11-09 | 2025-01-20 | 2025-02-04 | 16
C-52-598-03-CI-1050 | Earth Works for Light Pole, Fence & Gates Foundation | 12 | 12 | 2024-11-11 | 2024-11-23 | 2025-02-05 | 2025-02-18 | 16
Compaction & TestingCCOB452C33 |  | 50 | 50 | 2024-10-11 | 2024-12-12 | 2024-12-27 | 2025-02-24 | 145
C-52-598-03-CI-1200 | Compaction & Testing for Equipment Foundations & Hard Stand Area | 5 | 5 | 2024-12-07 | 2024-12-12 | 2024-12-27 | 2025-01-02 | 190
C-52-598-03-CI-1210 | Compaction & Testing for Pipe Support Foundations | 5 | 5 | 2024-10-11 | 2024-10-16 | 2025-01-06 | 2025-01-10 | 103
C-52-598-03-CI-1220 | Compaction & Testing for Field Instrument Foundations | 5 | 5 | 2024-10-25 | 2024-10-30 | 2025-01-20 | 2025-01-24 | 140
C-52-598-03-CI-1230 | Compaction & Testing for Access Platform & Misc. Structural Foundations | 5 | 5 | 2024-11-11 | 2024-11-15 | 2025-02-05 | 2025-02-10 | 144
C-52-598-03-CI-1240 | Compaction & Testing for Light Pole, Fence & Gates Foundation | 5 | 5 | 2024-11-25 | 2024-11-29 | 2025-02-19 | 2025-02-24 | 16
Concrete Works (Foundations for Equipment )CCOB452C34.1 |  | 66 | 66 | 2024-12-21 | 2025-02-17 | 2025-01-03 | 2025-03-26 | 145
C-52-598-03-CI-1400 | Concrete Works for Equipment Foundations & Hard Stand Area | 21 | 21 | 2025-01-24 | 2025-02-17 | 2025-01-03 | 2025-01-27 | 190
C-52-598-03-CI-1410 | Concrete Works for Field Instrument, JB Foundations | 14 | 14 | 2025-01-24 | 2025-02-08 | 2025-01-25 | 2025-02-10 | 140
C-52-598-03-CI-1420 | Concrete Works for Access Platform & Misc. Structural Foundations | 12 | 12 | 2025-01-11 | 2025-01-24 | 2025-02-11 | 2025-02-24 | 144
C-52-598-03-CI-1430 | Concrete Works for Light Pole, Fence & Gates Foundation | 21 | 21 | 2024-12-21 | 2025-01-15 | 2025-02-25 | 2025-03-26 | 16
Concrete Works (Foundations for Pipe Supports)CCOB452C34.2 |  | 21 | 21 | 2024-12-21 | 2025-01-15 | 2025-01-11 | 2025-02-04 | 103
C-52-598-03-CI-1600 | Concrete Works for Pipe Support Foundations | 21 | 21 | 2024-12-21 | 2025-01-15 | 2025-01-11 | 2025-02-04 | 103
Trenching for CablesCCOB452C39 |  | 60 | 60 | 2025-03-05 | 2025-05-06 | 2025-02-19 | 2025-05-10 | 90
C-52-598-03-CI-1800 | Electrical & Earthing Cable Trenching | 30 | 30 | 2025-03-05 | 2025-04-18 | 2025-02-19 | 2025-04-04 | 90
C-52-598-03-CI-1810 | Instrument & Telecom Cable Trenching | 30 | 30 | 2025-03-28 | 2025-05-06 | 2025-04-04 | 2025-05-10 | 90
Pipe Supports Fabrication & InstallationCCOB452S51 |  | 14 | 14 | 2025-01-31 | 2025-02-15 | 2025-03-12 | 2025-04-05 | 67
C-52-598-03-CI-2000 | Pre-Fabrication & Installation of Pipe Supports | 14 | 14 | 2025-01-31 | 2025-02-15 | 2025-03-12 | 2025-04-05 | 67
Fences & Gates ConstructionCCOB452C37 |  | 93 | 93 | 2025-01-16 | 2025-05-15 | 2025-03-26 | 2025-07-22 | 16
C-52-598-03-CI-2200 | Installation of Concrete Pillers for Boundary Wall | 21 | 21 | 2025-01-16 | 2025-02-08 | 2025-03-26 | 2025-04-24 | 16
C-52-598-03-CI-2210 | Block Works for Boundary Wall | 21 | 21 | 2025-02-10 | 2025-03-06 | 2025-04-24 | 2025-05-20 | 16
C-52-598-03-CI-2220 | Installation of Fence Post & Mesh Works (Type-4 & 3) | 30 | 30 | 2025-03-07 | 2025-04-19 | 2025-05-20 | 2025-06-26 | 16
C-52-598-03-CI-2230 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | 21 | 21 | 2025-04-19 | 2025-05-15 | 2025-06-26 | 2025-07-22 | 16
Fire Point SheltersCCOB452S53 |  | 8 | 8 | 2025-04-28 | 2025-05-07 | 2025-06-03 | 2025-06-13 | 95
C-52-598-03-CI-2400 | Installation of Fire Point Shelters | 8 | 8 | 2025-04-28 | 2025-05-07 | 2025-06-03 | 2025-06-13 | 95
Paving WorksCCOB452C38 |  | 56 | 56 | 2025-05-15 | 2025-07-23 | 2025-07-22 | 2025-09-26 | 16
C-52-598-03-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 28 | 28 | 2025-05-15 | 2025-06-19 | 2025-07-22 | 2025-08-23 | 16
C-52-598-03-CI-2610 | Rip-Rap Protection Laying | 28 | 28 | 2025-06-19 | 2025-07-23 | 2025-08-23 | 2025-09-26 | 16
Backfilling for CablesCCOB452C40 |  | 28 | 28 | 2025-05-08 | 2025-06-12 | 2025-05-07 | 2025-06-11 | 106
C-52-598-03-CI-2800 | Back Filling for Electrical & Earthing Cable | 14 | 14 | 2025-05-08 | 2025-05-24 | 2025-05-07 | 2025-05-23 | 106
C-52-598-03-CI-2810 | Back Filling for Instrument & Telecom Cable | 14 | 14 | 2025-05-24 | 2025-06-12 | 2025-05-23 | 2025-06-11 | 106
Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB452S52 |  | 53 | 53 | 2025-03-03 | 2025-05-14 | 2025-04-17 | 2025-06-20 | 97
C-52-598-03-CI-3000 | Pre-Fabrication & Installation of Platforms & Crossovers | 28 | 28 | 2025-03-03 | 2025-04-15 | 2025-04-17 | 2025-05-20 | 108
C-52-598-03-CI-3010 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | 14 | 14 | 2025-04-28 | 2025-05-14 | 2025-06-03 | 2025-06-20 | 97
Mechanical Works & Equipment Installation |  | 8 | 8 | 2025-07-23 | 2025-08-01 | 2025-06-14 | 2025-06-23 | 95
Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB452M51 |  | 8 | 8 | 2025-07-23 | 2025-08-01 | 2025-06-14 | 2025-06-23 | 95
C-52-598-03-ME-1000 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | 8 | 8 | 2025-07-23 | 2025-08-01 | 2025-06-14 | 2025-06-23 | 95
Piping Works |  | 94 | 94 | 2025-02-17 | 2025-04-29 | 2025-04-05 | 2025-07-28 | 66
Piping Pre-FabricationCCOB452P051 |  | 21 | 21 | 2025-02-17 | 2025-03-15 | 2025-04-05 | 2025-04-30 | 67
C-52-598-03-PI-1000 | Piping Pre-Fabrication | 21 | 21 | 2025-02-17 | 2025-03-15 | 2025-04-05 | 2025-04-30 | 67
ErectionCCOB452P061 |  | 14 | 14 | 2025-03-20 | 2025-04-11 | 2025-04-30 | 2025-05-16 | 67
C-52-598-03-PI-1200 | Piping Erection | 14 | 14 | 2025-03-20 | 2025-04-11 | 2025-04-30 | 2025-05-16 | 67
Field Joint Welding & NDTCCOB452P071 |  | 15 | 15 | 2025-03-22 | 2025-04-15 | 2025-05-02 | 2025-05-20 | 110
C-52-598-03-PI-1400 | Field Joint Welding (Including Isolation Joint) | 12 | 12 | 2025-03-22 | 2025-04-11 | 2025-05-02 | 2025-05-16 | 108
C-52-598-03-PI-1410 | NDT & Coating for Field Joint Weld | 12 | 12 | 2025-03-27 | 2025-04-15 | 2025-05-06 | 2025-05-20 | 110
HydrotestingCCOB452P081 |  | 5 | 5 | 2025-04-15 | 2025-04-21 | 2025-05-21 | 2025-05-26 | 110
C-52-598-03-PI-1600 | Hydrotesting | 5 | 5 | 2025-04-15 | 2025-04-21 | 2025-05-21 | 2025-05-26 | 110
Installation of ValvesCCOB452P091 |  | 5 | 5 | 2025-04-21 | 2025-04-26 | 2025-07-21 | 2025-07-25 | 66
C-52-598-03-PI-1800 | Installation of Valves & GOV | 5 | 5 | 2025-04-21 | 2025-04-26 | 2025-07-21 | 2025-07-25 | 66
Final Bolt Torquing/ Re-InstatementCCOB452P101 |  | 3 | 3 | 2025-04-25 | 2025-04-29 | 2025-07-25 | 2025-07-28 | 66
C-52-598-03-PI-2000 | Final Bolt Torquing/ Re-Instatement | 3 | 3 | 2025-04-25 | 2025-04-29 | 2025-07-25 | 2025-07-28 | 66
Pipeline Works |  | 69 | 69 | 2025-03-15 | 2025-04-25 | 2025-04-30 | 2025-07-23 | 70
Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 |  | 69 | 69 | 2025-03-15 | 2025-04-25 | 2025-04-30 | 2025-07-23 | 70
C-52-598-03-PL-1000 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | 5 | 5 | 2025-03-15 | 2025-03-23 | 2025-04-30 | 2025-05-06 | 110
C-52-598-03-PL-1010 | Lowering of Pipeline Section | 2 | 2 | 2025-03-23 | 2025-03-26 | 2025-05-06 | 2025-05-08 | 110
C-52-598-03-PL-1020 | Section Tie-in Welding (Including Barred Tee) | 12 | 12 | 2025-03-23 | 2025-04-11 | 2025-05-06 | 2025-05-20 | 110
C-52-598-03-PL-1030 | NDT for Tie-in Joint | 12 | 12 | 2025-03-25 | 2025-04-12 | 2025-05-07 | 2025-05-21 | 110
C-52-598-03-PL-1040 | Ext. Coating for Tie-in Joint | 12 | 12 | 2025-03-26 | 2025-04-14 | 2025-05-09 | 2025-05-22 | 110
C-52-598-03-PL-1050 | Holiday Testing of Pipeline Section | 1 | 1 | 2025-04-14 | 2025-04-15 | 2025-05-23 | 2025-05-23 | 110
C-52-598-03-PL-1060 | Installation of ROV | 1 | 1 | 2025-04-15 | 2025-04-16 | 2025-07-21 | 2025-07-21 | 70
C-52-598-03-PL-1070 | Installation of Pig Signaller Pit | 1 | 1 | 2025-04-16 | 2025-04-17 | 2025-07-22 | 2025-07-22 | 70
C-52-598-03-PL-1080 | Installation of Pig Signaller | 1 | 1 | 2025-04-17 | 2025-04-18 | 2025-07-23 | 2025-07-23 | 70
C-52-598-03-PL-1090 | Padding & Backfilling | 9 | 9 | 2025-04-15 | 2025-04-25 | 2025-07-14 | 2025-07-23 | 70
Electrical & Instrumentation Works |  | 82 | 82 | 2025-02-24 | 2025-08-07 | 2025-04-18 | 2025-07-26 | 67
Hybrid Passive Cooling Shelter InstallationCCOB452E50 |  | 3 | 3 | 2025-02-24 | 2025-02-26 | 2025-04-25 | 2025-04-29 | 123
C-52-598-03-EI-1000 | Installation of Passive Cooling Shelter | 3 | 3 | 2025-02-24 | 2025-02-26 | 2025-04-25 | 2025-04-29 | 123
Solar Power SystemCCOB452E63 |  | 26 | 26 | 2025-06-11 | 2025-07-17 | 2025-06-03 | 2025-07-05 | 67
C-52-598-03-EI-1210 | Installation of Solar Panel Structural Supports | 12 | 12 | 2025-06-11 | 2025-06-25 | 2025-06-03 | 2025-06-18 | 67
C-52-598-03-EI-1200 | Installation of Solar S/m (Including Panels, UPS & Battery) | 14 | 14 | 2025-07-01 | 2025-07-17 | 2025-06-19 | 2025-07-05 | 67
Deep Earth WellCCOB452E51 |  | 3 | 3 | 2025-05-15 | 2025-05-19 | 2025-05-15 | 2025-05-17 | 124
C-52-598-03-EI-1400 | Deep Earth Well Drilling | 3 | 3 | 2025-05-15 | 2025-05-19 | 2025-05-15 | 2025-05-17 | 124
RTUCCOB452E73 |  | 2 | 2 | 2025-02-27 | 2025-02-28 | 2025-04-29 | 2025-05-01 | 123
C-52-598-03-EI-1600 | Installation of RTU | 2 | 2 | 2025-02-27 | 2025-02-28 | 2025-04-29 | 2025-05-01 | 123
Light Pole, Lighting & FixturesCCOB452E83 |  | 9 | 9 | 2025-07-12 | 2025-07-23 | 2025-07-02 | 2025-07-11 | 67
C-52-598-03-EI-1800 | Installation of Light Pole, Lighting & Fixtures | 6 | 6 | 2025-07-12 | 2025-07-19 | 2025-07-02 | 2025-07-08 | 67
C-52-598-03-EI-1810 | Installation of Lighting & Instrument JB's | 3 | 3 | 2025-07-19 | 2025-07-23 | 2025-07-09 | 2025-07-11 | 67
E&I Cable Laying, Glanding & TerminationCCOB452E53 |  | 82 | 82 | 2025-04-18 | 2025-08-07 | 2025-04-18 | 2025-07-26 | 67
C-52-598-03-EI-2000 | Electrical & Earthing Cable Laying | 6 | 6 | 2025-04-18 | 2025-04-25 | 2025-04-18 | 2025-04-24 | 103
C-52-598-03-EI-2010 | Instrument Cable Laying | 6 | 6 | 2025-05-07 | 2025-05-14 | 2025-05-10 | 2025-05-17 | 90
C-52-598-03-EI-2020 | Installation of Cable Trays | 6 | 6 | 2025-05-14 | 2025-05-21 | 2025-05-17 | 2025-05-24 | 90
C-52-598-03-EI-2030 | Instrument Tubing Works | 5 | 5 | 2025-05-21 | 2025-05-27 | 2025-05-24 | 2025-05-30 | 90
C-52-598-03-EI-2040 | Loop Checking for Instruments | 8 | 8 | 2025-07-23 | 2025-08-01 | 2025-07-12 | 2025-07-21 | 67
C-52-598-03-EI-2050 | Glanding & Termination | 5 | 5 | 2025-08-01 | 2025-08-07 | 2025-07-22 | 2025-07-26 | 67
Field InstrumentsCCOB452E93 |  | 20 | 20 | 2025-04-11 | 2025-06-03 | 2025-05-17 | 2025-06-11 | 87
C-52-598-03-EI-2210 | Pre-Fabrication & Installation of Field Instrument, JB Supports | 14 | 14 | 2025-04-11 | 2025-04-28 | 2025-05-17 | 2025-06-02 | 67
C-52-598-03-EI-2200 | Installation of Field Instruments | 6 | 6 | 2025-05-27 | 2025-06-03 | 2025-06-03 | 2025-06-11 | 87
F&G DevicesCCOB452E103 |  | 37 | 37 | 2025-03-01 | 2025-06-11 | 2025-05-01 | 2025-06-17 | 87
C-52-598-03-EI-2400 | Installation of F&G Panel | 2 | 2 | 2025-03-01 | 2025-03-03 | 2025-05-01 | 2025-05-03 | 123
C-52-598-03-EI-2410 | Installation of F&G Devices | 5 | 5 | 2025-06-03 | 2025-06-11 | 2025-06-12 | 2025-06-17 | 87
Cathodic Protection Works |  | 14 | 14 | 2025-04-25 | 2025-05-13 | 2025-04-25 | 2025-05-12 | 130
CP Anode Bed Installation (subcontract)CCOB452E30 |  | 14 | 14 | 2025-04-25 | 2025-05-13 | 2025-04-25 | 2025-05-12 | 130
C-52-598-03-CA-1000 | CP Cable Laying | 5 | 5 | 2025-04-25 | 2025-05-01 | 2025-04-25 | 2025-04-30 | 106
C-52-598-03-CA-1010 | Installation of CP Test Post | 3 | 3 | 2025-05-01 | 2025-05-05 | 2025-05-01 | 2025-05-03 | 130
C-52-598-03-CA-1020 | Installation of CP S/m | 6 | 6 | 2025-05-05 | 2025-05-13 | 2025-05-05 | 2025-05-12 | 130
Telecommunication Works |  | 17 | 17 | 2025-05-28 | 2025-06-18 | 2025-05-28 | 2025-06-18 | 99
SDH CabinetCCOB452I30 |  | 3 | 3 | 2025-05-28 | 2025-05-30 | 2025-05-28 | 2025-05-30 | 99
C-52-598-03-TE-1000 | Installation of SDH Cabinet | 3 | 3 | 2025-05-28 | 2025-05-30 | 2025-05-28 | 2025-05-30 | 99
PIDS SystemCCOB452I40 |  | 3 | 3 | 2025-05-31 | 2025-06-03 | 2025-05-31 | 2025-06-03 | 99
C-52-598-03-TE-1200 | Installation of PIDS/ PLDS System | 3 | 3 | 2025-05-31 | 2025-06-03 | 2025-05-31 | 2025-06-03 | 99
Telephone SystemCCOB452I50 |  | 6 | 6 | 2025-06-12 | 2025-06-18 | 2025-06-12 | 2025-06-18 | 99
C-52-598-03-TE-1400 | Installation of Telephone System | 6 | 6 | 2025-06-12 | 2025-06-18 | 2025-06-12 | 2025-06-18 | 99
CCTV SystemCCOB452I60 |  | 5 | 5 | 2025-06-04 | 2025-06-11 | 2025-06-04 | 2025-06-11 | 99
C-52-598-03-TE-1600 | Installation of CCTV System | 5 | 5 | 2025-06-04 | 2025-06-11 | 2025-06-04 | 2025-06-11 | 99
598-BVS-04 (52'' Pipeline) |  | 389 | 220 | 2024-05-27 | 2025-08-18 | 27-May-24 A | 2025-09-17 | 9
598-BVS-04 (52'' Pipeline)-1 |  | 389 | 220 | 2024-05-27 | 2025-08-18 | 27-May-24 A | 2025-09-17 | 9
Civil Works |  | 389 | 220 | 2024-05-27 | 2025-08-16 | 27-May-24 A | 2025-09-17 | 9
Earthworks, Site Preparation, Site GradingCCOB352C31 |  | 228 | 59 | 2024-05-27 | 2024-12-07 | 27-May-24 A | 2025-02-25 | 9
C-52-598-04-CI-1000 | Site Survey, Preparation & Grading Works | 34 | 0 | 2024-05-27 | 2024-07-10 | 27-May-24 A | 10-Jul-24 A
C-52-598-04-CI-1010 | Earth Works for Equipment Foundations & Hard Stand Area | 14 | 14 | 2024-09-28 | 2024-10-14 | 2024-12-18 | 2025-01-03 | 9
C-52-598-04-CI-1020 | Earth Works for Pipe Support Foundations | 14 | 14 | 2024-10-07 | 2024-10-22 | 2024-12-26 | 2025-01-11 | 9
C-52-598-04-CI-1030 | Earth Works for Field Instrument Foundations | 12 | 12 | 2024-10-23 | 2024-11-05 | 2025-01-13 | 2025-01-25 | 9
C-52-598-04-CI-1040 | Earth Works for Access Platforms & Misc. Structural Foundations | 14 | 14 | 2024-11-06 | 2024-11-21 | 2025-01-27 | 2025-02-11 | 9
C-52-598-04-CI-1050 | Earth Works for Light Pole, Fence & Gates Foundation | 12 | 12 | 2024-11-22 | 2024-12-07 | 2025-02-12 | 2025-02-25 | 9
Compaction & TestingCCOB352C32 |  | 50 | 50 | 2024-10-23 | 2024-12-18 | 2025-01-04 | 2025-03-03 | 124
C-52-598-04-CI-1200 | Compaction & Testing for Equipment Foundations & Hard Stand Area | 5 | 5 | 2024-12-13 | 2024-12-18 | 2025-01-04 | 2025-01-09 | 169
C-52-598-04-CI-1210 | Compaction & Testing for Pipe Support Foundations | 5 | 5 | 2024-10-23 | 2024-10-28 | 2025-01-13 | 2025-01-17 | 119
C-52-598-04-CI-1220 | Compaction & Testing for Field Instrument Foundations | 5 | 5 | 2024-11-06 | 2024-11-11 | 2025-01-27 | 2025-01-31 | 124
C-52-598-04-CI-1230 | Compaction & Testing for Access Platform & Misc. Structural Foundations | 5 | 5 | 2024-11-22 | 2024-11-27 | 2025-02-12 | 2025-02-17 | 134
C-52-598-04-CI-1240 | Compaction & Testing for Light Pole, Fence & Gates Foundation | 5 | 5 | 2024-12-09 | 2024-12-13 | 2025-02-26 | 2025-03-03 | 9
Concrete Works (Foundations for Equipment )CCOB352C33 |  | 66 | 66 | 2025-01-16 | 2025-03-17 | 2025-01-10 | 2025-04-07 | 124
C-52-598-04-CI-1400 | Concrete Works for Equipment Foundations & Hard Stand Area | 21 | 21 | 2025-02-18 | 2025-03-17 | 2025-01-10 | 2025-02-03 | 169
C-52-598-04-CI-1410 | Concrete Works for Field Instrument, JB Foundations | 14 | 14 | 2025-02-10 | 2025-02-25 | 2025-02-01 | 2025-02-17 | 124
C-52-598-04-CI-1420 | Concrete Works for Access Platform & Misc. Structural Foundations | 12 | 12 | 2025-01-25 | 2025-02-07 | 2025-02-18 | 2025-03-03 | 134
C-52-598-04-CI-1430 | Concrete Works for Light Pole, Fence & Gates Foundation | 21 | 21 | 2025-01-16 | 2025-02-08 | 2025-03-03 | 2025-04-07 | 9
Concrete Works (Foundations for Pipe Supports)CCOB352C34 |  | 21 | 21 | 2025-01-16 | 2025-02-08 | 2025-01-18 | 2025-02-11 | 119
C-52-598-04-CI-1600 | Concrete Works for Pipe Support Foundations | 21 | 21 | 2025-01-16 | 2025-02-08 | 2025-01-18 | 2025-02-11 | 119
Trenching for CablesCCOB352C38 |  | 60 | 60 | 2025-04-18 | 2025-06-13 | 2025-01-13 | 2025-03-29 | 107
C-52-598-04-CI-1800 | Electrical & Earthing Cable Trenching | 30 | 30 | 2025-04-18 | 2025-05-24 | 2025-01-13 | 2025-02-15 | 107
C-52-598-04-CI-1810 | Instrument & Telecom Cable Trenching | 30 | 30 | 2025-05-07 | 2025-06-13 | 2025-02-17 | 2025-03-29 | 107
Pipe Supports Fabrication & InstallationCCOB352S50 |  | 14 | 14 | 2025-02-17 | 2025-03-05 | 2025-03-12 | 2025-04-05 | 89
C-52-598-04-CI-2000 | Pre-Fabrication & Installation of Pipe Supports | 14 | 14 | 2025-02-17 | 2025-03-05 | 2025-03-12 | 2025-04-05 | 89
Fences & Gates ConstructionCCOB352C36 |  | 135 | 135 | 2025-02-10 | 2025-08-16 | 2025-04-07 | 2025-09-17 | 9
C-52-598-04-CI-2200 | Installation of Concrete Pillers for Boundary Wall | 21 | 21 | 2025-02-10 | 2025-03-06 | 2025-04-07 | 2025-05-01 | 9
C-52-598-04-CI-2210 | Block Works for Boundary Wall | 21 | 21 | 2025-03-07 | 2025-04-09 | 2025-04-15 | 2025-05-10 | 9
C-52-598-04-CI-2220 | Installation of Fence Post & Mesh Works (Type-4 & 3) | 30 | 30 | 2025-04-09 | 2025-05-15 | 2025-05-10 | 2025-06-17 | 9
C-52-598-04-CI-2230 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | 21 | 21 | 2025-05-15 | 2025-06-11 | 2025-06-17 | 2025-07-12 | 9
C-52-598-04-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 28 | 28 | 2025-06-11 | 2025-07-15 | 2025-07-12 | 2025-08-14 | 9
C-52-598-04-CI-2610 | Rip-Rap Protection Laying | 28 | 28 | 2025-07-15 | 2025-08-16 | 2025-08-14 | 2025-09-17 | 9
Fire Point SheltersCCOB352S51 |  | 8 | 8 | 2025-05-01 | 2025-05-10 | 2025-04-25 | 2025-05-05 | 97
C-52-598-04-CI-2400 | Installation of Fire Point Shelters | 8 | 8 | 2025-05-01 | 2025-05-10 | 2025-04-25 | 2025-05-05 | 97
Backfilling for CablesCCOB352C39 |  | 28 | 28 | 2025-06-14 | 2025-07-18 | 2025-05-07 | 2025-06-11 | 90
C-52-598-04-CI-2800 | Back Filling for Electrical & Earthing Cable | 14 | 14 | 2025-06-14 | 2025-07-02 | 2025-05-07 | 2025-05-23 | 90
C-52-598-04-CI-2810 | Back Filling for Instrument & Telecom Cable | 14 | 14 | 2025-07-02 | 2025-07-18 | 2025-05-23 | 2025-06-11 | 90
Platforms & BollardsCCOB352S52 |  | 31 | 31 | 2025-04-28 | 2025-06-03 | 2025-04-22 | 2025-05-28 | 100
C-52-598-04-CI-3000 | Pre-Fabrication & Installation of Platforms & Crossovers | 28 | 28 | 2025-04-28 | 2025-05-30 | 2025-04-22 | 2025-05-24 | 100
C-52-598-04-CI-3010 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | 14 | 14 | 2025-05-19 | 2025-06-03 | 2025-05-13 | 2025-05-28 | 100
Mechanical Works & Equipment Installation |  | 8 | 8 | 2025-08-01 | 2025-08-11 | 2025-05-23 | 2025-05-31 | 97
Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB352M51 |  | 8 | 8 | 2025-08-01 | 2025-08-11 | 2025-05-23 | 2025-05-31 | 97
C-52-598-04-ME-1000 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | 8 | 8 | 2025-08-01 | 2025-08-11 | 2025-05-23 | 2025-05-31 | 97
Piping Works |  | 121 | 121 | 2025-02-17 | 2025-05-15 | 2025-02-24 | 2025-07-28 | 51
Piping Pre-FabricationCCOB352P051 |  | 21 | 21 | 2025-02-17 | 2025-03-15 | 2025-02-24 | 2025-03-24 | 95
C-52-598-04-PI-1000 | Piping Pre-Fabrication | 21 | 21 | 2025-02-17 | 2025-03-15 | 2025-02-24 | 2025-03-24 | 95
ErectionCCOB352P061 |  | 14 | 14 | 2025-04-11 | 2025-04-28 | 2025-04-05 | 2025-04-22 | 89
C-52-598-04-PI-1200 | Piping Erection | 14 | 14 | 2025-04-11 | 2025-04-28 | 2025-04-05 | 2025-04-22 | 89
Field Joint Welding & NDTCCOB352P071 |  | 15 | 15 | 2025-04-14 | 2025-05-01 | 2025-04-08 | 2025-04-25 | 116
C-52-598-04-PI-1400 | Field Joint Welding (Including Isolation Joint) | 12 | 12 | 2025-04-14 | 2025-04-28 | 2025-04-08 | 2025-04-22 | 100
C-52-598-04-PI-1410 | NDT & Coating for Field Joint Weld | 12 | 12 | 2025-04-17 | 2025-05-01 | 2025-04-11 | 2025-04-25 | 116
HydrotestingCCOB352P081 |  | 5 | 5 | 2025-05-01 | 2025-05-07 | 2025-04-25 | 2025-05-01 | 116
C-52-598-04-PI-1600 | Hydrotesting | 5 | 5 | 2025-05-01 | 2025-05-07 | 2025-04-25 | 2025-05-01 | 116
Installation of ValvesCCOB352P091 |  | 5 | 5 | 2025-05-07 | 2025-05-13 | 2025-07-21 | 2025-07-25 | 51
C-52-598-04-PI-1800 | Installation of Valves & GOV | 5 | 5 | 2025-05-07 | 2025-05-13 | 2025-07-21 | 2025-07-25 | 51
Final Bolt Torquing/ Re-InstatementCCOB352P101 |  | 3 | 3 | 2025-05-13 | 2025-05-15 | 2025-07-25 | 2025-07-28 | 51
C-52-598-04-PI-2000 | Final Bolt Torquing/ Re-Instatement | 3 | 3 | 2025-05-13 | 2025-05-15 | 2025-07-25 | 2025-07-28 | 51
Pipeline Works |  | 96 | 96 | 2025-03-23 | 2025-05-01 | 2025-03-25 | 2025-07-23 | 55
Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 |  | 96 | 96 | 2025-03-23 | 2025-05-01 | 2025-03-25 | 2025-07-23 | 55
C-52-598-04-PL-1000 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | 5 | 5 | 2025-03-23 | 2025-04-03 | 2025-03-25 | 2025-04-04 | 122
C-52-598-04-PL-1010 | Lowering of Pipeline Section | 2 | 2 | 2025-04-03 | 2025-04-05 | 2025-04-04 | 2025-04-07 | 122
C-52-598-04-PL-1020 | Section Tie-in Welding (Including Barred Tee) | 12 | 12 | 2025-04-03 | 2025-04-17 | 2025-04-04 | 2025-04-18 | 122
C-52-598-04-PL-1030 | NDT for Tie-in Joint | 12 | 12 | 2025-04-04 | 2025-04-18 | 2025-04-05 | 2025-04-19 | 122
C-52-598-04-PL-1040 | Ext. Coating for Tie-in Joint | 12 | 12 | 2025-04-05 | 2025-04-19 | 2025-04-07 | 2025-04-21 | 122
C-52-598-04-PL-1050 | Holiday Testing of Pipeline Section | 1 | 1 | 2025-04-19 | 2025-04-21 | 2025-04-21 | 2025-04-22 | 122
C-52-598-04-PL-1060 | Installation of ROV | 1 | 1 | 2025-04-21 | 2025-04-22 | 2025-07-21 | 2025-07-21 | 55
C-52-598-04-PL-1070 | Installation of Pig Signaller Pit | 1 | 1 | 2025-04-22 | 2025-04-23 | 2025-07-22 | 2025-07-22 | 55
C-52-598-04-PL-1080 | Installation of Pig Signaller | 1 | 1 | 2025-04-23 | 2025-04-24 | 2025-07-23 | 2025-07-23 | 55
C-52-598-04-PL-1090 | Padding & Backfilling | 9 | 9 | 2025-04-21 | 2025-05-01 | 2025-07-14 | 2025-07-23 | 55
Electrical & Instrumentation Works |  | 63 | 63 | 2025-02-27 | 2025-08-18 | 2025-04-09 | 2025-06-24 | 79
Hybrid Passive Cooling Shelter InstallationCCOB352E50 |  | 3 | 3 | 2025-02-27 | 2025-03-01 | 2025-04-25 | 2025-04-29 | 108
C-52-598-04-EI-1000 | Installation of Passive Cooling Shelter | 3 | 3 | 2025-02-27 | 2025-03-01 | 2025-04-25 | 2025-04-29 | 108
Solar Power SystemCCOB352E62 |  | 26 | 26 | 2025-06-25 | 2025-08-02 | 2025-05-07 | 2025-06-09 | 79
C-52-598-04-EI-1210 | Installation of Solar Panel Structural Supports | 12 | 12 | 2025-06-25 | 2025-07-10 | 2025-05-07 | 2025-05-22 | 79
C-52-598-04-EI-1200 | Installation of Solar S/m (Including Panels, UPS & Battery) | 14 | 14 | 2025-07-17 | 2025-08-02 | 2025-05-22 | 2025-06-09 | 79
Deep Earth WellCCOB352E52 |  | 3 | 3 | 2025-05-28 | 2025-05-31 | 2025-05-15 | 2025-05-17 | 109
C-52-598-04-EI-1400 | Deep Earth Well Drilling | 3 | 3 | 2025-05-28 | 2025-05-31 | 2025-05-15 | 2025-05-17 | 109
RTUCCOB352E72 |  | 2 | 2 | 2025-03-02 | 2025-03-05 | 2025-04-29 | 2025-05-01 | 108
C-52-598-04-EI-1600 | Installation of RTU | 2 | 2 | 2025-03-02 | 2025-03-05 | 2025-04-29 | 2025-05-01 | 108
Light Pole, Lighting & FixturesCCOB352E82 |  | 34 | 34 | 2025-03-02 | 2025-08-05 | 2025-04-29 | 2025-06-11 | 85
C-52-598-04-EI-1810 | Installation of Lighting & Instrument JB's | 3 | 3 | 2025-03-02 | 2025-03-06 | 2025-04-29 | 2025-05-02 | 109
C-52-598-04-EI-1800 | Installation of Light Pole, Lighting & Fixtures | 6 | 6 | 2025-07-29 | 2025-08-05 | 2025-06-03 | 2025-06-11 | 85
E&I Cable Laying, Glanding & TerminationCCOB352E51 |  | 55 | 55 | 2025-05-24 | 2025-08-18 | 2025-04-18 | 2025-06-24 | 79
C-52-598-04-EI-2000 | Electrical & Earthing Cable Laying | 6 | 6 | 2025-05-24 | 2025-05-31 | 2025-04-18 | 2025-04-24 | 87
C-52-598-04-CA-1000 | CP Cable Laying | 5 | 5 | 2025-05-31 | 2025-06-09 | 2025-04-25 | 2025-04-30 | 90
C-52-598-04-EI-2010 | Instrument Cable Laying | 6 | 6 | 2025-06-13 | 2025-06-20 | 2025-04-25 | 2025-05-01 | 87
C-52-598-04-CA-1010 | Installation of CP Test Post | 3 | 3 | 2025-06-09 | 2025-06-12 | 2025-05-01 | 2025-05-03 | 114
C-52-598-04-EI-2020 | Installation of Cable Trays | 6 | 6 | 2025-06-20 | 2025-06-28 | 2025-05-02 | 2025-05-09 | 87
C-52-598-04-CA-1020 | Installation of CP S/m | 6 | 6 | 2025-06-12 | 2025-06-19 | 2025-05-05 | 2025-05-12 | 114
C-52-598-04-EI-2030 | Instrument Tubing Works | 5 | 5 | 2025-06-28 | 2025-07-04 | 2025-05-09 | 2025-05-15 | 87
C-52-598-04-EI-2040 | Loop Checking for Instruments | 8 | 8 | 2025-08-02 | 2025-08-12 | 2025-06-10 | 2025-06-18 | 79
C-52-598-04-EI-2050 | Glanding & Termination | 5 | 5 | 2025-08-12 | 2025-08-18 | 2025-06-19 | 2025-06-24 | 79
Field InstrumentsCCOB352E102 |  | 37 | 37 | 2025-04-15 | 2025-07-11 | 2025-04-09 | 2025-05-22 | 87
C-52-598-04-EI-2210 | Pre-Fabrication & Installation of Field Instrument, JB Supports | 14 | 14 | 2025-04-15 | 2025-05-01 | 2025-04-09 | 2025-04-25 | 89
C-52-598-04-EI-2200 | Installation of Field Instruments | 6 | 6 | 2025-07-04 | 2025-07-11 | 2025-05-15 | 2025-05-22 | 87
F&G DevicesCCOB352E92 |  | 22 | 22 | 2025-03-05 | 2025-07-17 | 2025-05-01 | 2025-05-28 | 87
C-52-598-04-EI-2400 | Installation of F&G Panel | 2 | 2 | 2025-03-05 | 2025-03-08 | 2025-05-01 | 2025-05-03 | 108
C-52-598-04-EI-2410 | Installation of F&G Devices | 5 | 5 | 2025-07-11 | 2025-07-17 | 2025-05-22 | 2025-05-28 | 87
Telecommunication Works |  | 17 | 17 | 2025-06-20 | 2025-07-11 | 2025-05-28 | 2025-06-18 | 84
SDH CabinetCCOB352I30 |  | 3 | 3 | 2025-06-20 | 2025-06-24 | 2025-05-28 | 2025-05-30 | 84
C-52-598-04-TE-1000 | Installation of SDH Cabinet | 3 | 3 | 2025-06-20 | 2025-06-24 | 2025-05-28 | 2025-05-30 | 84
PIDS SystemCCOB352I40 |  | 3 | 3 | 2025-06-24 | 2025-06-28 | 2025-05-31 | 2025-06-03 | 84
C-52-598-04-TE-1200 | Installation of PIDS/ PLDS System | 3 | 3 | 2025-06-24 | 2025-06-28 | 2025-05-31 | 2025-06-03 | 84
Telephone SystemCCOB352I50 |  | 6 | 6 | 2025-07-04 | 2025-07-11 | 2025-06-12 | 2025-06-18 | 84
C-52-598-04-TE-1400 | Installation of Telephone System | 6 | 6 | 2025-07-04 | 2025-07-11 | 2025-06-12 | 2025-06-18 | 84
CCTV SystemCCOB352I60 |  | 5 | 5 | 2025-06-28 | 2025-07-04 | 2025-06-04 | 2025-06-11 | 84
C-52-598-04-TE-1600 | Installation of CCTV System | 5 | 5 | 2025-06-28 | 2025-07-04 | 2025-06-04 | 2025-06-11 | 84
598-BVS-05 (52'' Pipeline) |  | 239 | 230 | 2024-10-29 | 2025-09-15 | 17-Oct-24 A | 2025-08-09 | 44
598-BVS-05 (52'' Pipeline)-1 |  | 239 | 230 | 2024-10-29 | 2025-09-15 | 17-Oct-24 A | 2025-08-09 | 44
Civil Works |  | 239 | 230 | 2024-10-29 | 2025-09-11 | 17-Oct-24 A | 2025-08-09 | 44
Earthworks, Site Preparation, Site GradingCCOB252C31 |  | 95 | 86 | 2024-10-29 | 2024-12-18 | 17-Oct-24 A | 2025-02-07 | 44
C-52-598-05-CI-1000 | Site Survey, Preparation & Grading Works | 30 | 21 | 2024-10-29 | 2024-11-06 | 17-Oct-24 A | 2024-11-21 | 92
C-52-598-05-CI-1010 | Earth Works for Equipment Foundations & Hard Stand Area | 14 | 14 | 2024-11-02 | 2024-11-18 | 2024-12-25 | 2025-01-10 | 44
C-52-598-05-CI-1020 | Earth Works for Pipe Support Foundations | 14 | 14 | 2024-11-11 | 2024-11-26 | 2025-01-03 | 2025-01-18 | 44
C-52-598-05-CI-1030 | Earth Works for Field Instrument Foundations | 12 | 12 | 2024-11-18 | 2024-11-30 | 2025-01-10 | 2025-01-23 | 44
C-52-598-05-CI-1040 | Earth Works for Access Platforms & Misc. Structural Foundations | 14 | 14 | 2024-11-26 | 2024-12-13 | 2025-01-18 | 2025-02-03 | 44
C-52-598-05-CI-1050 | Earth Works for Light Pole, Fence & Gates Foundation | 12 | 12 | 2024-12-05 | 2024-12-18 | 2025-01-25 | 2025-02-07 | 44
Compaction & TestingCCOB252C32 |  | 29 | 29 | 2024-11-27 | 2024-12-24 | 2025-01-11 | 2025-02-13 | 142
C-52-598-05-CI-1200 | Compaction & Testing for Equipment Foundations & Hard Stand Area | 5 | 5 | 2024-12-19 | 2024-12-24 | 2025-01-11 | 2025-01-16 | 166
C-52-598-05-CI-1210 | Compaction & Testing for Pipe Support Foundations | 5 | 5 | 2024-11-27 | 2024-12-04 | 2025-01-20 | 2025-01-24 | 93
C-52-598-05-CI-1220 | Compaction & Testing for Field Instrument Foundations | 5 | 5 | 2024-12-04 | 2024-12-09 | 2025-01-24 | 2025-01-29 | 134
C-52-598-05-CI-1230 | Compaction & Testing for Access Platform & Misc. Structural Foundations | 5 | 5 | 2024-12-14 | 2024-12-19 | 2025-02-04 | 2025-02-08 | 145
C-52-598-05-CI-1240 | Compaction & Testing for Light Pole, Fence & Gates Foundation | 5 | 5 | 2024-12-19 | 2024-12-24 | 2025-02-08 | 2025-02-13 | 44
Concrete Works (Foundations for Equipments)CCOB252C34 |  | 45 | 45 | 2025-02-10 | 2025-04-17 | 2025-01-17 | 2025-03-12 | 142
C-52-598-05-CI-1400 | Concrete Works for Equipment Foundations & Hard Stand Area | 21 | 21 | 2025-03-17 | 2025-04-17 | 2025-01-17 | 2025-02-10 | 166
C-52-598-05-CI-1410 | Concrete Works for Field Instrument, JB Foundations | 14 | 14 | 2025-02-26 | 2025-03-17 | 2025-01-30 | 2025-02-14 | 134
C-52-598-05-CI-1420 | Concrete Works for Access Platform & Misc. Structural Foundations | 12 | 12 | 2025-03-17 | 2025-04-07 | 2025-02-15 | 2025-02-28 | 140
C-52-598-05-CI-1430 | Concrete Works for Light Pole, Fence & Gates Foundation | 21 | 21 | 2025-02-10 | 2025-03-06 | 2025-02-14 | 2025-03-12 | 44
Concrete Works (Foundations for Pipe Supports)CCOB252C33 |  | 21 | 21 | 2025-02-10 | 2025-03-06 | 2025-01-25 | 2025-02-18 | 93
C-52-598-05-CI-1600 | Concrete Works for Pipe Support Foundations | 21 | 21 | 2025-02-10 | 2025-03-06 | 2025-01-25 | 2025-02-18 | 93
Trenching for CablesCCOB252C38 |  | 60 | 60 | 2025-05-24 | 2025-07-19 | 2025-01-20 | 2025-04-09 | 122
C-52-598-05-CI-1800 | Electrical & Earthing Cable Trenching | 30 | 30 | 2025-05-24 | 2025-07-02 | 2025-01-20 | 2025-02-22 | 122
C-52-598-05-CI-1810 | Instrument & Telecom Cable Trenching | 30 | 30 | 2025-06-13 | 2025-07-19 | 2025-02-24 | 2025-04-09 | 122
Pipe Supports Fabrication & InstallationCCOB252S50 |  | 14 | 14 | 2025-03-07 | 2025-03-28 | 2025-03-12 | 2025-04-05 | 76
C-52-598-05-CI-2000 | Pre-Fabrication & Installation of Pipe Supports | 14 | 14 | 2025-03-07 | 2025-03-28 | 2025-03-12 | 2025-04-05 | 76
Fences & Gates ConstructionCCOB252C36 |  | 76 | 76 | 2025-03-07 | 2025-07-07 | 2025-03-13 | 2025-06-20 | 44
C-52-598-05-CI-2200 | Installation of Concrete Pillers for Boundary Wall | 21 | 21 | 2025-03-07 | 2025-04-09 | 2025-03-13 | 2025-04-14 | 44
C-52-598-05-CI-2210 | Block Works for Boundary Wall | 21 | 21 | 2025-04-09 | 2025-05-03 | 2025-03-19 | 2025-04-18 | 44
C-52-598-05-CI-2220 | Installation of Fence Post & Mesh Works (Type-4 & 3) | 30 | 30 | 2025-05-03 | 2025-06-11 | 2025-04-18 | 2025-05-24 | 44
C-52-598-05-CI-2230 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | 21 | 21 | 2025-06-11 | 2025-07-07 | 2025-05-24 | 2025-06-20 | 44
Fire Point ShelterCCOB252S52 |  | 8 | 8 | 2025-07-24 | 2025-08-02 | 2025-05-26 | 2025-06-03 | 76
C-52-598-05-CI-2400 | Installation of Fire Point Shelters | 8 | 8 | 2025-07-24 | 2025-08-02 | 2025-05-26 | 2025-06-03 | 76
Paving WorksCCOB252C35 |  | 42 | 42 | 2025-07-07 | 2025-09-11 | 2025-06-20 | 2025-08-09 | 44
C-52-598-05-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 21 | 21 | 2025-07-07 | 2025-08-08 | 2025-06-20 | 2025-07-16 | 44
C-52-598-05-CI-2610 | Rip-Rap Protection Laying | 21 | 21 | 2025-08-08 | 2025-09-11 | 2025-07-16 | 2025-08-09 | 44
Backfilling for CablesCCOB252C40 |  | 21 | 21 | 2025-07-21 | 2025-08-25 | 2025-04-25 | 2025-05-20 | 110
C-52-598-05-CI-2800 | Back Filling for Electrical & Earthing Cable | 14 | 14 | 2025-07-21 | 2025-08-06 | 2025-04-25 | 2025-05-12 | 110
C-52-598-05-CI-2810 | Back Filling for Instrument & Telecom Cable | 14 | 14 | 2025-08-08 | 2025-08-25 | 2025-05-03 | 2025-05-20 | 110
Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB252S51 |  | 30 | 30 | 2025-05-13 | 2025-06-19 | 2025-05-17 | 2025-06-23 | 83
C-52-598-05-CI-3000 | Pre-Fabrication & Installation of Platforms & Crossovers | 28 | 28 | 2025-05-13 | 2025-06-17 | 2025-05-17 | 2025-06-20 | 83
C-52-598-05-CI-3010 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | 14 | 14 | 2025-05-31 | 2025-06-19 | 2025-06-07 | 2025-06-23 | 83
Mechanical Works & Equipment Installation |  | 8 | 8 | 2025-08-19 | 2025-08-28 | 2025-06-23 | 2025-07-02 | 76
Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB252M50 |  | 8 | 8 | 2025-08-19 | 2025-08-28 | 2025-06-23 | 2025-07-02 | 76
C-52-598-05-ME-1000 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | 8 | 8 | 2025-08-19 | 2025-08-28 | 2025-06-23 | 2025-07-02 | 76
Piping Works |  | 94 | 94 | 2025-03-28 | 2025-05-30 | 2025-04-05 | 2025-07-28 | 54
Piping Pre-FabricationCCOB252P050 |  | 21 | 21 | 2025-03-28 | 2025-04-25 | 2025-04-05 | 2025-04-30 | 76
C-52-598-05-PI-1000 | Piping Pre-Fabrication | 21 | 21 | 2025-03-28 | 2025-04-25 | 2025-04-05 | 2025-04-30 | 76
ErectionCCOB252P060 |  | 14 | 14 | 2025-04-25 | 2025-05-13 | 2025-04-30 | 2025-05-16 | 76
C-52-598-05-PI-1200 | Piping Erection | 14 | 14 | 2025-04-25 | 2025-05-13 | 2025-04-30 | 2025-05-16 | 76
Field Joint Welding & NDTCCOB252P070 |  | 15 | 15 | 2025-04-28 | 2025-05-16 | 2025-05-02 | 2025-05-20 | 98
C-52-598-05-PI-1400 | Field Joint Welding (Including Isolation Joint) | 12 | 12 | 2025-04-28 | 2025-05-13 | 2025-05-02 | 2025-05-16 | 83
C-52-598-05-PI-1410 | NDT & Coating for Field Joint Weld | 12 | 12 | 2025-05-01 | 2025-05-16 | 2025-05-06 | 2025-05-20 | 98
HydrotestingCCOB252P080 |  | 5 | 5 | 2025-05-16 | 2025-05-22 | 2025-05-21 | 2025-05-26 | 98
C-52-598-05-PI-1600 | Hydrotesting | 5 | 5 | 2025-05-16 | 2025-05-22 | 2025-05-21 | 2025-05-26 | 98
Installation of ValvesCCOB252P090 |  | 5 | 5 | 2025-05-22 | 2025-05-28 | 2025-07-21 | 2025-07-25 | 54
C-52-598-05-PI-1800 | Installation of Valves & GOV | 5 | 5 | 2025-05-22 | 2025-05-28 | 2025-07-21 | 2025-07-25 | 54
Final Bolt Torquing/ Re-InstatementCCOB252P100 |  | 3 | 3 | 2025-05-27 | 2025-05-30 | 2025-07-25 | 2025-07-28 | 54
C-52-598-05-PI-2000 | Final Bolt Torquing/ Re-Instatement | 3 | 3 | 2025-05-27 | 2025-05-30 | 2025-07-25 | 2025-07-28 | 54
Pipeline Works |  | 69 | 69 | 2025-04-25 | 2025-05-30 | 2025-04-30 | 2025-07-23 | 58
Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 |  | 69 | 69 | 2025-04-25 | 2025-05-30 | 2025-04-30 | 2025-07-23 | 58
C-52-598-05-PL-1000 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | 5 | 5 | 2025-04-25 | 2025-05-01 | 2025-04-30 | 2025-05-06 | 98
C-52-598-05-PL-1010 | Lowering of Pipeline Section | 2 | 2 | 2025-05-01 | 2025-05-03 | 2025-05-06 | 2025-05-08 | 98
C-52-598-05-PL-1020 | Section Tie-in Welding (Including Barred Tee) | 12 | 12 | 2025-05-01 | 2025-05-16 | 2025-05-06 | 2025-05-20 | 98
C-52-598-05-PL-1030 | NDT for Tie-in Joint | 12 | 12 | 2025-05-02 | 2025-05-17 | 2025-05-07 | 2025-05-21 | 98
C-52-598-05-PL-1040 | Ext. Coating for Tie-in Joint | 12 | 12 | 2025-05-03 | 2025-05-19 | 2025-05-09 | 2025-05-22 | 98
C-52-598-05-PL-1050 | Holiday Testing of Pipeline Section | 1 | 1 | 2025-05-19 | 2025-05-20 | 2025-05-23 | 2025-05-23 | 98
C-52-598-05-PL-1060 | Installation of ROV | 1 | 1 | 2025-05-20 | 2025-05-21 | 2025-07-21 | 2025-07-21 | 58
C-52-598-05-PL-1070 | Installation of Pig Signaller Pit | 1 | 1 | 2025-05-21 | 2025-05-22 | 2025-07-22 | 2025-07-22 | 58
C-52-598-05-PL-1080 | Installation of Pig Signaller | 1 | 1 | 2025-05-22 | 2025-05-23 | 2025-07-23 | 2025-07-23 | 58
C-52-598-05-PL-1090 | Padding & Backfilling | 9 | 9 | 2025-05-20 | 2025-05-30 | 2025-07-14 | 2025-07-23 | 58
Electrical & Instrumentation Works |  | 64 | 64 | 2025-04-17 | 2025-09-15 | 2025-04-18 | 2025-07-05 | 73
Hybrid Passive Cooling Shelter InstallationCCOB252E50 |  | 3 | 3 | 2025-04-17 | 2025-04-21 | 2025-06-10 | 2025-06-13 | 75
C-52-598-05-EI-1000 | Installation of Passive Cooling Shelter | 3 | 3 | 2025-04-17 | 2025-04-21 | 2025-06-10 | 2025-06-13 | 75
Solar Power SystemCCOB252E62 |  | 26 | 26 | 2025-07-10 | 2025-08-19 | 2025-05-07 | 2025-06-09 | 73
C-52-598-05-EI-1210 | Installation of Solar Panel Structural Supports | 12 | 12 | 2025-07-10 | 2025-07-24 | 2025-05-07 | 2025-05-22 | 73
C-52-598-05-EI-1200 | Installation of Solar S/m (Including Panels, UPS & Battery) | 14 | 14 | 2025-08-02 | 2025-08-19 | 2025-05-22 | 2025-06-09 | 73
Deep Earth WellCCOB252E52 |  | 3 | 3 | 2025-07-05 | 2025-07-09 | 2025-05-15 | 2025-05-17 | 112
C-52-598-05-EI-1400 | Deep Earth Well Drilling | 3 | 3 | 2025-07-05 | 2025-07-09 | 2025-05-15 | 2025-05-17 | 112
RTUCCOB252E72 |  | 2 | 2 | 2025-04-21 | 2025-04-23 | 2025-06-13 | 2025-06-16 | 75
C-52-598-05-EI-1600 | Installation of RTU | 2 | 2 | 2025-04-21 | 2025-04-23 | 2025-06-13 | 2025-06-16 | 75
Light Pole, Lighting & FixturesCCOB252E82 |  | 9 | 9 | 2025-08-19 | 2025-08-29 | 2025-06-10 | 2025-06-19 | 73
C-52-598-05-EI-1800 | Installation of Light Pole, Lighting & Fixtures | 6 | 6 | 2025-08-19 | 2025-08-26 | 2025-06-10 | 2025-06-16 | 73
C-52-598-05-EI-1810 | Installation of Lighting & Instrument JB's | 3 | 3 | 2025-08-26 | 2025-08-29 | 2025-06-17 | 2025-06-19 | 73
E&I Cable Laying, Glanding & TerminationCCOB252E51 |  | 64 | 64 | 2025-07-02 | 2025-09-15 | 2025-04-18 | 2025-07-05 | 73
C-52-598-05-EI-2000 | Electrical & Earthing Cable Laying | 6 | 6 | 2025-07-02 | 2025-07-09 | 2025-04-18 | 2025-04-24 | 110
C-52-598-05-EI-2010 | Instrument Cable Laying | 6 | 6 | 2025-07-19 | 2025-07-26 | 2025-04-18 | 2025-04-24 | 114
C-52-598-05-EI-2020 | Installation of Cable Trays | 6 | 6 | 2025-07-26 | 2025-08-02 | 2025-04-25 | 2025-05-01 | 115
C-52-598-05-EI-2030 | Instrument Tubing Works | 5 | 5 | 2025-08-02 | 2025-08-08 | 2025-05-02 | 2025-05-08 | 115
C-52-598-05-EI-2040 | Loop Checking for Instruments | 8 | 8 | 2025-08-29 | 2025-09-09 | 2025-06-20 | 2025-06-30 | 73
C-52-598-05-EI-2050 | Glanding & Termination | 5 | 5 | 2025-09-09 | 2025-09-15 | 2025-07-01 | 2025-07-05 | 73
Field InstrumentsCCOB252E92 |  | 20 | 20 | 2025-05-03 | 2025-05-28 | 2025-05-09 | 2025-05-31 | 82
C-52-598-05-EI-2210 | Pre-Fabrication & Installation of Field Instrument, JB Supports | 14 | 14 | 2025-05-03 | 2025-05-21 | 2025-05-09 | 2025-05-24 | 76
C-52-598-05-EI-2200 | Installation of Field Instruments | 6 | 6 | 2025-05-21 | 2025-05-28 | 2025-05-26 | 2025-05-31 | 82
F&G DevicesCCOB252E102 |  | 13 | 13 | 2025-04-23 | 2025-06-03 | 2025-06-02 | 2025-06-18 | 75
C-52-598-05-EI-2410 | Installation of F&G Devices | 5 | 5 | 2025-05-28 | 2025-06-03 | 2025-06-02 | 2025-06-09 | 82
C-52-598-05-EI-2400 | Installation of F&G Panel | 2 | 2 | 2025-04-23 | 2025-04-25 | 2025-06-16 | 2025-06-18 | 75
Cathodic Protection Works |  | 14 | 14 | 2025-07-09 | 2025-07-25 | 2025-04-18 | 2025-05-03 | 123
CP Anode Bed Installation (subcontract)CCOB252E30 |  | 14 | 14 | 2025-07-09 | 2025-07-25 | 2025-04-18 | 2025-05-03 | 123
C-52-598-05-CA-1000 | CP Cable Laying | 5 | 5 | 2025-07-09 | 2025-07-15 | 2025-04-18 | 2025-04-23 | 111
C-52-598-05-CA-1010 | Installation of CP Test Post | 3 | 3 | 2025-07-15 | 2025-07-18 | 2025-04-24 | 2025-04-26 | 123
C-52-598-05-CA-1020 | Installation of CP S/m | 6 | 6 | 2025-07-18 | 2025-07-25 | 2025-04-28 | 2025-05-03 | 123
Telecommunication Works |  | 17 | 17 | 2025-07-26 | 2025-08-15 | 2025-05-28 | 2025-06-18 | 87
SDH CabinetCCOB252I30 |  | 3 | 3 | 2025-07-26 | 2025-07-30 | 2025-05-28 | 2025-05-30 | 87
C-52-598-05-TE-1000 | Installation of SDH Cabinet | 3 | 3 | 2025-07-26 | 2025-07-30 | 2025-05-28 | 2025-05-30 | 87
PIDS SystemCCOB252I40 |  | 3 | 3 | 2025-07-30 | 2025-08-02 | 2025-05-31 | 2025-06-03 | 87
C-52-598-05-TE-1200 | Installation of PIDS/ PLDS System | 3 | 3 | 2025-07-30 | 2025-08-02 | 2025-05-31 | 2025-06-03 | 87
Telephone SystemCCOB252I50 |  | 6 | 6 | 2025-08-08 | 2025-08-15 | 2025-06-12 | 2025-06-18 | 87
C-52-598-05-TE-1400 | Installation of Telephone System | 6 | 6 | 2025-08-08 | 2025-08-15 | 2025-06-12 | 2025-06-18 | 87
CCTV SystemCCOB252I60 |  | 5 | 5 | 2025-08-02 | 2025-08-08 | 2025-06-04 | 2025-06-11 | 87
C-52-598-05-TE-1600 | Installation of CCTV System | 5 | 5 | 2025-08-02 | 2025-08-08 | 2025-06-04 | 2025-06-11 | 87
598-BVS-06 (52'' Pipeline) |  | 186 | 186 | 2024-11-05 | 2025-10-09 | 2025-01-04 | 2025-08-23 | 47
598-BVS-06 (52'' Pipeline)-1 |  | 186 | 186 | 2024-11-05 | 2025-10-09 | 2025-01-04 | 2025-08-23 | 47
Civil Works |  | 186 | 186 | 2024-11-05 | 2025-09-19 | 2025-01-04 | 2025-08-23 | 47
Earthworks, Site Preparation, Site GradingCCOB152C31 |  | 46 | 46 | 2024-11-05 | 2024-12-30 | 2025-01-04 | 2025-02-26 | 47
C-52-598-06-CI-1000 | Site Survey, Preparation & Grading Works | 8 | 8 | 2024-11-05 | 2024-11-13 | 2025-01-04 | 2025-01-13 | 47
C-52-598-06-CI-1010 | Earth Works for Equipment Foundations & Hard Stand Area | 14 | 14 | 2024-11-14 | 2024-11-29 | 2025-01-14 | 2025-01-29 | 47
C-52-598-06-CI-1020 | Earth Works for Pipe Support Foundations | 14 | 14 | 2024-11-22 | 2024-12-10 | 2025-01-22 | 2025-02-06 | 47
C-52-598-06-CI-1030 | Earth Works for Field Instrument Foundations | 12 | 12 | 2024-11-29 | 2024-12-14 | 2025-01-29 | 2025-02-11 | 47
C-52-598-06-CI-1040 | Earth Works for Access Platforms & Misc. Structural Foundations | 14 | 14 | 2024-12-10 | 2024-12-25 | 2025-02-06 | 2025-02-21 | 47
C-52-598-06-CI-1050 | Earth Works for Light Pole, Fence & Gates Foundation | 12 | 12 | 2024-12-17 | 2024-12-30 | 2025-02-13 | 2025-02-26 | 47
Compaction & TestingCCOB152C33 |  | 29 | 29 | 2024-12-11 | 2025-01-06 | 2025-01-30 | 2025-03-05 | 142
C-52-598-06-CI-1200 | Compaction & Testing for Equipment Foundations & Hard Stand Area | 5 | 5 | 2024-12-25 | 2024-12-30 | 2025-01-30 | 2025-02-04 | 158
C-52-598-06-CI-1210 | Compaction & Testing for Pipe Support Foundations | 5 | 5 | 2024-12-11 | 2024-12-16 | 2025-02-07 | 2025-02-12 | 91
C-52-598-06-CI-1220 | Compaction & Testing for Field Instrument Foundations | 5 | 5 | 2024-12-16 | 2024-12-20 | 2025-02-12 | 2025-02-17 | 126
C-52-598-06-CI-1230 | Compaction & Testing for Access Platform & Misc. Structural Foundations | 5 | 5 | 2024-12-26 | 2024-12-31 | 2025-02-22 | 2025-02-27 | 146
C-52-598-06-CI-1240 | Compaction & Testing for Light Pole, Fence & Gates Foundation | 5 | 5 | 2024-12-31 | 2025-01-06 | 2025-02-27 | 2025-03-05 | 47
Concrete Works (Foundations for Equipment )CCOB152C32 |  | 45 | 45 | 2025-03-07 | 2025-05-13 | 2025-02-05 | 2025-04-08 | 134
C-52-598-06-CI-1400 | Concrete Works for Equipment Foundations & Hard Stand Area | 21 | 21 | 2025-04-17 | 2025-05-13 | 2025-02-05 | 2025-02-28 | 158
C-52-598-06-CI-1410 | Concrete Works for Field Instrument, JB Foundations | 14 | 14 | 2025-03-17 | 2025-04-09 | 2025-02-18 | 2025-03-06 | 126
C-52-598-06-CI-1420 | Concrete Works for Access Platform & Misc. Structural Foundations | 12 | 12 | 2025-04-07 | 2025-04-21 | 2025-03-01 | 2025-03-18 | 145
C-52-598-06-CI-1430 | Concrete Works for Light Pole, Fence & Gates Foundation | 21 | 21 | 2025-03-07 | 2025-04-09 | 2025-03-05 | 2025-04-08 | 47
Concrete Works (Foundations for Pipe Supports)CCOB152C34 |  | 21 | 21 | 2024-12-17 | 2025-01-10 | 2025-02-13 | 2025-03-11 | 91
C-52-598-06-CI-1600 | Concrete Works for Pipe Support Foundations | 21 | 21 | 2024-12-17 | 2025-01-10 | 2025-02-13 | 2025-03-11 | 91
Trenching for CablesCCOB152C38 |  | 51 | 51 | 2024-12-11 | 2025-02-08 | 2025-02-07 | 2025-04-17 | 102
C-52-598-06-CI-1800 | Electrical & Earthing Cable Trenching | 30 | 30 | 2024-12-11 | 2025-01-15 | 2025-02-07 | 2025-03-17 | 102
C-52-598-06-CI-1810 | Instrument & Telecom Cable Trenching | 21 | 21 | 2025-01-16 | 2025-02-08 | 2025-03-17 | 2025-04-17 | 102
Pipe Supports Fabrication & InstallationCCOB152S52 |  | 14 | 14 | 2025-01-31 | 2025-02-15 | 2025-03-12 | 2025-04-05 | 90
C-52-598-06-CI-2000 | Pre-Fabrication & Installation of Pipe Supports | 14 | 14 | 2025-01-31 | 2025-02-15 | 2025-03-12 | 2025-04-05 | 90
Fences & Gates ConstructionCCOB152C36 |  | 79 | 79 | 2025-04-09 | 2025-07-15 | 2025-04-08 | 2025-07-14 | 47
C-52-598-06-CI-2200 | Installation of Concrete Pillers for Boundary Wall | 21 | 21 | 2025-04-09 | 2025-05-03 | 2025-04-08 | 2025-05-02 | 47
C-52-598-06-CI-2210 | Block Works for Boundary Wall | 21 | 21 | 2025-04-17 | 2025-05-13 | 2025-04-16 | 2025-05-12 | 47
C-52-598-06-CI-2220 | Installation of Fence Post & Mesh Works (Type-4 & 3) | 30 | 30 | 2025-05-13 | 2025-06-19 | 2025-05-12 | 2025-06-18 | 47
C-52-598-06-CI-2230 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | 21 | 21 | 2025-06-19 | 2025-07-15 | 2025-06-18 | 2025-07-14 | 47
Fire Point SheltersCCOB152S50 |  | 8 | 8 | 2025-08-07 | 2025-08-16 | 2025-05-19 | 2025-05-27 | 117
C-52-598-06-CI-2400 | Installation of Fire Point Shelters | 8 | 8 | 2025-08-07 | 2025-08-16 | 2025-05-19 | 2025-05-27 | 117
Paving WorksCCOB152C40 |  | 35 | 35 | 2025-07-15 | 2025-09-19 | 2025-07-14 | 2025-08-23 | 47
C-52-598-06-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 28 | 28 | 2025-07-15 | 2025-08-16 | 2025-07-14 | 2025-08-15 | 47
C-52-598-06-CI-2610 | Rip-Rap Protection Laying | 28 | 28 | 2025-08-16 | 2025-09-19 | 2025-07-22 | 2025-08-23 | 47
Backfilling for CablesCCOB152C37 |  | 28 | 28 | 2025-05-30 | 2025-07-05 | 2025-05-24 | 2025-06-30 | 94
C-52-598-06-CI-2800 | Back Filling for Electrical & Earthing Cable | 14 | 14 | 2025-05-30 | 2025-06-18 | 2025-05-24 | 2025-06-12 | 94
C-52-598-06-CI-2810 | Back Filling for Instrument & Telecom Cable | 14 | 14 | 2025-06-18 | 2025-07-05 | 2025-06-12 | 2025-06-30 | 94
Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB152S54 |  | 68 | 68 | 2025-04-21 | 2025-06-24 | 2025-04-05 | 2025-06-26 | 96
C-52-598-06-CI-3000 | Pre-Fabrication & Installation of Platforms & Crossovers | 28 | 28 | 2025-04-21 | 2025-05-24 | 2025-04-05 | 2025-05-08 | 135
C-52-598-06-CI-3010 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | 14 | 14 | 2025-06-07 | 2025-06-24 | 2025-06-10 | 2025-06-26 | 96
Mechanical Works & Equipment Installation |  | 8 | 8 | 2025-08-28 | 2025-09-08 | 2025-05-21 | 2025-05-29 | 117
Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB152M50 |  | 8 | 8 | 2025-08-28 | 2025-09-08 | 2025-05-21 | 2025-05-29 | 117
C-52-598-06-ME-1000 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | 8 | 8 | 2025-08-28 | 2025-09-08 | 2025-05-21 | 2025-05-29 | 117
Piping Works |  | 82 | 82 | 2025-04-17 | 2025-06-17 | 2025-04-19 | 2025-07-28 | 69
Piping Pre-FabricationCCOB152P050 |  | 21 | 21 | 2025-04-17 | 2025-05-12 | 2025-04-19 | 2025-05-14 | 79
C-52-598-06-PI-1000 | Piping Pre-Fabrication | 21 | 21 | 2025-04-17 | 2025-05-12 | 2025-04-19 | 2025-05-14 | 79
ErectionCCOB152P060 |  | 14 | 14 | 2025-05-12 | 2025-05-28 | 2025-05-14 | 2025-05-30 | 79
C-52-598-06-PI-1200 | Piping Erection | 14 | 14 | 2025-05-12 | 2025-05-28 | 2025-05-14 | 2025-05-30 | 79
Field Joint Welding & NDTCCOB152P070 |  | 15 | 15 | 2025-05-14 | 2025-05-31 | 2025-05-16 | 2025-06-03 | 102
C-52-598-06-PI-1400 | Field Joint Welding (Including Isolation Joint) | 12 | 12 | 2025-05-14 | 2025-05-28 | 2025-05-16 | 2025-05-30 | 89
C-52-598-06-PI-1410 | NDT & Coating for Field Joint Weld | 12 | 12 | 2025-05-17 | 2025-05-31 | 2025-05-20 | 2025-06-03 | 102
HydrotestingCCOB152P080 |  | 5 | 5 | 2025-05-31 | 2025-06-09 | 2025-06-03 | 2025-06-11 | 102
C-52-598-06-PI-1600 | Hydrotesting | 5 | 5 | 2025-05-31 | 2025-06-09 | 2025-06-03 | 2025-06-11 | 102
Installation of ValvesCCOB152P090 |  | 5 | 5 | 2025-06-09 | 2025-06-14 | 2025-07-21 | 2025-07-25 | 69
C-52-598-06-PI-1800 | Installation of Valves & GOV | 5 | 5 | 2025-06-09 | 2025-06-14 | 2025-07-21 | 2025-07-25 | 69
Final Bolt Torquing/ Re-InstatementCCOB152P100 |  | 3 | 3 | 2025-06-13 | 2025-06-17 | 2025-07-25 | 2025-07-28 | 69
C-52-598-06-PI-2000 | Final Bolt Torquing/ Re-Instatement | 3 | 3 | 2025-06-13 | 2025-06-17 | 2025-07-25 | 2025-07-28 | 69
Pipeline Works |  | 57 | 57 | 2025-05-12 | 2025-06-17 | 2025-05-14 | 2025-07-23 | 73
Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 |  | 57 | 57 | 2025-05-12 | 2025-06-17 | 2025-05-14 | 2025-07-23 | 73
C-52-598-06-PL-1000 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | 5 | 5 | 2025-05-12 | 2025-05-17 | 2025-05-14 | 2025-05-20 | 102
C-52-598-06-PL-1010 | Lowering of Pipeline Section | 2 | 2 | 2025-05-17 | 2025-05-20 | 2025-05-20 | 2025-05-22 | 102
C-52-598-06-PL-1020 | Section Tie-in Welding (Including Barred Tee) | 12 | 12 | 2025-05-17 | 2025-05-31 | 2025-05-20 | 2025-06-03 | 102
C-52-598-06-PL-1030 | NDT for Tie-in Joint | 12 | 12 | 2025-05-19 | 2025-06-02 | 2025-05-21 | 2025-06-04 | 102
C-52-598-06-PL-1040 | Ext. Coating for Tie-in Joint | 12 | 12 | 2025-05-20 | 2025-06-03 | 2025-05-22 | 2025-06-07 | 102
C-52-598-06-PL-1050 | Holiday Testing of Pipeline Section | 1 | 1 | 2025-06-03 | 2025-06-04 | 2025-06-07 | 2025-06-09 | 102
C-52-598-06-PL-1060 | Installation of ROV | 1 | 1 | 2025-06-04 | 2025-06-07 | 2025-07-21 | 2025-07-21 | 73
C-52-598-06-PL-1070 | Installation of Pig Signaller Pit | 1 | 1 | 2025-06-07 | 2025-06-09 | 2025-07-22 | 2025-07-22 | 73
C-52-598-06-PL-1080 | Installation of Pig Signaller | 1 | 1 | 2025-06-09 | 2025-06-10 | 2025-07-23 | 2025-07-23 | 73
C-52-598-06-PL-1090 | Padding & Backfilling | 9 | 9 | 2025-06-04 | 2025-06-17 | 2025-07-14 | 2025-07-23 | 73
Electrical & Instrumentation Works |  | 73 | 73 | 2025-04-25 | 2025-10-09 | 2025-04-19 | 2025-07-17 | 79
Hybrid Passive Cooling Shelter InstallationCCOB152E50 |  | 3 | 3 | 2025-05-13 | 2025-05-16 | 2025-06-02 | 2025-06-04 | 88
C-52-598-06-EI-1000 | Installation of Passive Cooling Shelter | 3 | 3 | 2025-05-13 | 2025-05-16 | 2025-06-02 | 2025-06-04 | 88
Solar Power SystemCCOB152E66 |  | 26 | 26 | 2025-07-24 | 2025-09-04 | 2025-05-03 | 2025-06-03 | 84
C-52-598-06-EI-1210 | Installation of Solar Panel Structural Supports | 12 | 12 | 2025-07-24 | 2025-08-07 | 2025-05-03 | 2025-05-17 | 84
C-52-598-06-EI-1200 | Installation of Solar S/m (Including Panels, UPS & Battery) | 14 | 14 | 2025-08-19 | 2025-09-04 | 2025-05-19 | 2025-06-03 | 84
Deep Earth WellCCOB152E52 |  | 3 | 3 | 2025-07-09 | 2025-07-12 | 2025-05-15 | 2025-05-17 | 117
C-52-598-06-EI-1400 | Deep Earth Well Drilling | 3 | 3 | 2025-07-09 | 2025-07-12 | 2025-05-15 | 2025-05-17 | 117
RTUCCOB152E76 |  | 2 | 2 | 2025-05-16 | 2025-05-19 | 2025-06-07 | 2025-06-09 | 88
C-52-598-06-EI-1600 | Installation of RTU | 2 | 2 | 2025-05-16 | 2025-05-19 | 2025-06-07 | 2025-06-09 | 88
Light Pole, Lighting & FixturesCCOB152E86 |  | 9 | 9 | 2025-09-04 | 2025-09-16 | 2025-06-10 | 2025-06-20 | 81
C-52-598-06-EI-1800 | Installation of Light Pole, Lighting & Fixtures | 6 | 6 | 2025-09-04 | 2025-09-12 | 2025-06-10 | 2025-06-17 | 81
C-52-598-06-EI-1810 | Installation of Lighting & Instrument JB's | 3 | 3 | 2025-09-12 | 2025-09-16 | 2025-06-17 | 2025-06-20 | 81
E&I Cable Laying, Glanding & TerminationCCOB152E54 |  | 73 | 73 | 2025-04-25 | 2025-10-09 | 2025-04-19 | 2025-07-17 | 79
C-52-598-06-EI-2000 | Electrical & Earthing Cable Laying | 10 | 10 | 2025-04-25 | 2025-05-07 | 2025-04-19 | 2025-04-30 | 91
C-52-598-06-EI-2010 | Instrument Cable Laying | 10 | 10 | 2025-05-07 | 2025-05-19 | 2025-05-01 | 2025-05-13 | 91
C-52-598-06-EI-2020 | Installation of Cable Trays | 10 | 10 | 2025-05-19 | 2025-05-30 | 2025-05-13 | 2025-05-24 | 91
C-52-598-06-EI-2030 | Instrument Tubing Works | 10 | 10 | 2025-05-30 | 2025-06-13 | 2025-05-24 | 2025-06-07 | 102
C-52-598-06-EI-2040 | Loop Checking for Instruments | 10 | 10 | 2025-09-16 | 2025-09-27 | 2025-06-23 | 2025-07-05 | 79
C-52-598-06-EI-2050 | Glanding & Termination | 10 | 10 | 2025-09-27 | 2025-10-09 | 2025-07-05 | 2025-07-17 | 79
Field InstrumentsCCOB152E96 |  | 20 | 20 | 2025-05-20 | 2025-06-14 | 2025-05-22 | 2025-06-17 | 79
C-52-598-06-EI-2210 | Pre-Fabrication & Installation of Field Instrument, JB Supports | 14 | 14 | 2025-05-20 | 2025-06-07 | 2025-05-22 | 2025-06-10 | 79
C-52-598-06-EI-2200 | Installation of Field Instruments | 6 | 6 | 2025-06-07 | 2025-06-14 | 2025-06-10 | 2025-06-17 | 79
F&G DevicesCCOB152E106 |  | 12 | 12 | 2025-05-19 | 2025-06-20 | 2025-06-10 | 2025-06-23 | 79
C-52-598-06-EI-2400 | Installation of F&G Panel | 2 | 2 | 2025-05-19 | 2025-05-21 | 2025-06-10 | 2025-06-11 | 88
C-52-598-06-EI-2410 | Installation of F&G Devices | 5 | 5 | 2025-06-14 | 2025-06-20 | 2025-06-17 | 2025-06-23 | 79
Cathodic Protection Works |  | 14 | 14 | 2025-05-19 | 2025-06-04 | 2025-05-13 | 2025-05-29 | 118
CP Anode Bed Installation (subcontract)CCOB152E56 |  | 14 | 14 | 2025-05-19 | 2025-06-04 | 2025-05-13 | 2025-05-29 | 118
C-52-598-06-CA-1000 | CP Cable Laying | 5 | 5 | 2025-05-19 | 2025-05-24 | 2025-05-13 | 2025-05-19 | 94
C-52-598-06-CA-1010 | Installation of CP Test Post | 3 | 3 | 2025-05-24 | 2025-05-28 | 2025-05-19 | 2025-05-22 | 118
C-52-598-06-CA-1020 | Installation of CP S/m | 6 | 6 | 2025-05-28 | 2025-06-04 | 2025-05-22 | 2025-05-29 | 118
Telecommunication Works |  | 17 | 17 | 2025-05-30 | 2025-06-21 | 2025-05-28 | 2025-06-18 | 102
SDH CabinetCCOB152I30 |  | 3 | 3 | 2025-05-30 | 2025-06-03 | 2025-05-28 | 2025-05-30 | 102
C-52-598-06-TE-1000 | Installation of SDH Cabinet | 3 | 3 | 2025-05-30 | 2025-06-03 | 2025-05-28 | 2025-05-30 | 102
PIDS SystemCCOB152I40 |  | 3 | 3 | 2025-06-03 | 2025-06-09 | 2025-05-31 | 2025-06-03 | 102
C-52-598-06-TE-1200 | Installation of PIDS/ PLDS System | 3 | 3 | 2025-06-03 | 2025-06-09 | 2025-05-31 | 2025-06-03 | 102
Telephone SystemCCOB152I50 |  | 6 | 6 | 2025-06-14 | 2025-06-21 | 2025-06-12 | 2025-06-18 | 102
C-52-598-06-TE-1400 | Installation of Telephone System | 6 | 6 | 2025-06-14 | 2025-06-21 | 2025-06-12 | 2025-06-18 | 102
CCTV SystemCCOB152I60 |  | 5 | 5 | 2025-06-09 | 2025-06-14 | 2025-06-04 | 2025-06-11 | 102
C-52-598-06-TE-1600 | Installation of CCTV System | 5 | 5 | 2025-06-09 | 2025-06-14 | 2025-06-04 | 2025-06-11 | 102
Sweihan CRS |  | 225 | 225 | 2024-06-14 | 2025-10-11 | 2025-01-09 | 2025-10-14 | 5
Pig Receiver 839-V-101 (52'' Pipeline) (including facilities at Sweihan CRS) |  | 215 | 215 | 2024-06-14 | 2025-08-27 | 2025-01-09 | 2025-10-01 | 14
Pig Receiver 839-V-101 & Other Packages (52'' Pipeline) |  | 215 | 215 | 2024-06-14 | 2025-08-27 | 2025-01-09 | 2025-10-01 | 14
Civil Works |  | 196 | 196 | 2024-06-14 | 2025-08-27 | 2025-01-09 | 2025-09-10 | 33
Earthworks, Site Preparation, Site GradingCCOSWCS300 |  | 80 | 80 | 2024-06-14 | 2025-02-22 | 2025-01-09 | 2025-04-22 | 65
C-52-PR-839-CI-1000 | Site Survey, Preparation & Grading Works | 14 | 14 | 2024-06-14 | 2024-10-18 | 2025-01-09 | 2025-01-24 | 51
C-52-PR-839-CI-1010 | Earth Works for Equipment Foundations | 15 | 15 | 2024-11-13 | 2024-12-09 | 2025-01-25 | 2025-02-11 | 65
C-52-PR-839-CI-1050 | Earth Works for Thrust Anchor Block | 21 | 21 | 2024-10-19 | 2024-11-12 | 2025-01-25 | 2025-02-18 | 51
C-52-PR-839-CI-1020 | Earth Works for Pipe Support Foundations | 15 | 15 | 2024-12-10 | 2025-01-11 | 2025-02-12 | 2025-02-28 | 65
C-52-PR-839-CI-1030 | Earth Works for Field Instrument, JBs & Light Pole Foundations | 14 | 14 | 2025-01-13 | 2025-01-28 | 2025-03-01 | 2025-03-22 | 65
C-52-PR-839-CI-1040 | Earth Works for Access Platforms & Misc. Structural Foundations | 14 | 14 | 2025-01-29 | 2025-02-13 | 2025-03-22 | 2025-04-12 | 65
C-52-PR-839-CI-1060 | Earth Works for Impact Wall | 8 | 8 | 2025-02-14 | 2025-02-22 | 2025-04-12 | 2025-04-22 | 65
Compaction & TestingCCOSWCS301 |  | 56 | 56 | 2024-11-13 | 2025-02-28 | 2025-02-12 | 2025-04-28 | 107
C-52-PR-839-CI-1200 | Compaction & Testing for Equipment Foundations | 8 | 8 | 2024-12-10 | 2024-12-18 | 2025-02-12 | 2025-02-20 | 75
C-52-PR-839-CI-1240 | Compaction & Testing for Thrust Anchor Block | 8 | 8 | 2024-11-13 | 2024-11-21 | 2025-02-19 | 2025-02-27 | 51
C-52-PR-839-CI-1210 | Compaction & Testing for Pipe Support Foundations | 8 | 8 | 2025-01-13 | 2025-01-21 | 2025-03-01 | 2025-03-12 | 98
C-52-PR-839-CI-1220 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | 5 | 5 | 2025-01-29 | 2025-02-03 | 2025-03-22 | 2025-03-29 | 115
C-52-PR-839-CI-1230 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | 5 | 5 | 2025-02-14 | 2025-02-19 | 2025-04-12 | 2025-04-18 | 115
C-52-PR-839-CI-1250 | Compaction & Testing for Impact Wall | 5 | 5 | 2025-02-24 | 2025-02-28 | 2025-04-22 | 2025-04-28 | 84
Concrete Works (Foundations for Equipment)CCOSWCS302.1 |  | 78 | 78 | 2024-12-19 | 2025-04-15 | 2025-02-21 | 2025-06-03 | 98
C-52-PR-839-CI-1400 | Concrete Works for Equipment Foundations | 21 | 21 | 2024-12-19 | 2025-01-13 | 2025-02-21 | 2025-03-22 | 75
C-52-PR-839-CI-1410 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | 14 | 14 | 2025-02-24 | 2025-03-14 | 2025-04-22 | 2025-05-09 | 98
C-52-PR-839-CI-1420 | Concrete Works for Access Platforms & Misc. Structural Foundations | 21 | 21 | 2025-03-14 | 2025-04-15 | 2025-05-09 | 2025-06-03 | 98
Concrete Works (Impact wall)CCOSWCS302.3 |  | 45 | 45 | 2025-06-17 | 2025-08-09 | 2025-07-01 | 2025-08-22 | 33
C-52-PR-839-CI-1500 | Concrete Works for Impact Wall | 45 | 45 | 2025-06-17 | 2025-08-09 | 2025-07-01 | 2025-08-22 | 33
Concrete Works (Foundations for Pipe Supports)CCOSWCS302.2 |  | 28 | 28 | 2025-01-22 | 2025-02-22 | 2025-03-13 | 2025-04-22 | 98
C-52-PR-839-CI-1600 | Concrete Works for Pipe Support Foundations | 28 | 28 | 2025-01-22 | 2025-02-22 | 2025-03-13 | 2025-04-22 | 98
Trenching for CablesCCOSWCS311 |  | 28 | 28 | 2025-03-07 | 2025-04-17 | 2025-03-01 | 2025-04-12 | 84
C-52-PR-839-CI-1800 | Electrical & Earthing Cable Trenching | 14 | 14 | 2025-03-07 | 2025-03-28 | 2025-03-01 | 2025-03-22 | 68
C-52-PR-839-CI-1810 | Instrument & Telecom Cable Trenching | 14 | 14 | 2025-03-28 | 2025-04-17 | 2025-03-22 | 2025-04-12 | 84
Pipe Supports Fabrication & InstallationCCOSWSS500 |  | 28 | 28 | 2025-01-02 | 2025-02-03 | 2025-02-24 | 2025-04-07 | 81
C-52-PR-839-CI-2000 | Pre-Fabrication & Installation of Pipe Supports | 28 | 28 | 2025-01-02 | 2025-02-03 | 2025-02-24 | 2025-04-07 | 81
Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS505 |  | 62 | 62 | 2025-02-04 | 2025-05-01 | 2025-04-07 | 2025-06-21 | 100
C-52-PR-839-CI-3010 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | 14 | 14 | 2025-02-04 | 2025-02-19 | 2025-04-07 | 2025-04-23 | 148
C-52-PR-839-CI-3000 | Pre-Fabrication & Installation of Platforms & Crossovers | 14 | 14 | 2025-04-15 | 2025-05-01 | 2025-06-03 | 2025-06-21 | 100
Thrust Anchor BlocklCCOSWCS317 |  | 75 | 75 | 2025-01-15 | 2025-06-17 | 2025-03-27 | 2025-07-01 | 33
C-52-PR-839-CI-1510 | Concrete Works for Thrust Anchor Block | 75 | 75 | 2025-01-15 | 2025-06-17 | 2025-03-27 | 2025-07-01 | 33
Earth Works for Paving CCOSWCS315.1 |  | 10 | 10 | 2025-02-24 | 2025-03-08 | 2025-04-22 | 2025-05-03 | 65
C-52-PR-839-CI-1070 | Earth Works for Paving of Interlock tiles & Kerb Stone Embankment | 10 | 10 | 2025-02-24 | 2025-03-08 | 2025-04-22 | 2025-05-03 | 65
Backfilling for CablesCCOSWCS320 |  | 22 | 22 | 2025-06-14 | 2025-07-10 | 2025-06-25 | 2025-07-21 | 53
C-52-PR-839-CI-2800 | Back Filling for Electrical & Earthing Cable | 8 | 8 | 2025-06-14 | 2025-06-23 | 2025-06-25 | 2025-07-04 | 59
C-52-PR-839-CI-2810 | Back Filling for Instrument & Telecom Cable | 8 | 8 | 2025-07-02 | 2025-07-10 | 2025-07-12 | 2025-07-21 | 53
Fences & Gates ConstructionCCOSWCS310 |  | 52 | 52 | 2025-03-08 | 2025-05-17 | 2025-05-03 | 2025-07-08 | 65
C-52-PR-839-CI-2220 | Fences & Gates Construction | 52 | 52 | 2025-03-08 | 2025-05-17 | 2025-05-03 | 2025-07-08 | 65
Paving interlock & barrier installationCCOSWCS315.2 |  | 10 | 10 | 2025-08-01 | 2025-08-13 | 2025-08-14 | 2025-08-26 | 33
C-52-PR-839-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 10 | 10 | 2025-08-01 | 2025-08-13 | 2025-08-14 | 2025-08-26 | 33
Fire Point SheltersCCOSWSS504 |  | 12 | 12 | 2025-02-04 | 2025-02-17 | 2025-04-07 | 2025-04-21 | 138
C-52-PR-839-CI-2400 | Fire Point Shelters | 12 | 12 | 2025-02-04 | 2025-02-17 | 2025-04-07 | 2025-04-21 | 138
FinishingCCOSWMC513 |  | 12 | 12 | 2025-08-13 | 2025-08-27 | 2025-08-26 | 2025-09-10 | 33
C-52-PR-839-CI-3200 | Finishing | 12 | 12 | 2025-08-13 | 2025-08-27 | 2025-08-26 | 2025-09-10 | 33
Mechanical Works & Equipment Installation |  | 168 | 168 | 2025-02-21 | 2025-07-09 | 2025-02-21 | 2025-09-19 | 24
Sales Gas FilterCCOSWME506 |  | 10 | 10 | 2025-02-21 | 2025-03-05 | 2025-02-21 | 2025-03-05 | 134
C-52-PR-839-ME-1800 | Installation of Sales Gas Filter (839-F-104A) | 5 | 5 | 2025-02-21 | 2025-02-26 | 2025-02-21 | 2025-02-26 | 134
C-52-PR-839-ME-1810 | Installation of Sales Gas Filter (839-F-104B) | 5 | 5 | 2025-02-27 | 2025-03-05 | 2025-02-27 | 2025-03-05 | 134
Installation of Pig Receiver (839-V-101)CCOSWME508 |  | 8 | 8 | 2025-03-13 | 2025-03-24 | 2025-03-22 | 2025-04-05 | 75
C-52-PR-839-ME-1100 | Installation of Pig Receiver (839-V-101) 52" | 8 | 8 | 2025-03-13 | 2025-03-24 | 2025-03-22 | 2025-04-05 | 75
Installation of Pig Signaler (839-V-101)CCOSWME509 |  | 4 | 4 | 2025-05-09 | 2025-05-14 | 2025-05-09 | 2025-05-14 | 76
C-52-PR-839-ME-1200 | Installation of Pig Signaler (839-V-101) | 4 | 4 | 2025-05-09 | 2025-05-14 | 2025-05-09 | 2025-05-14 | 76
Installation of Fire Fighting & Safety EquipmentCCOSWME510 |  | 4 | 4 | 2025-07-04 | 2025-07-09 | 2025-09-16 | 2025-09-19 | 14
C-52-PR-839-ME-1600 | Installation of Fire Fighting & Safety Equipment | 4 | 4 | 2025-07-04 | 2025-07-09 | 2025-09-16 | 2025-09-19 | 14
Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 |  | 8 | 8 | 2025-05-29 | 2025-06-09 | 2025-05-29 | 2025-06-09 | 110
C-52-PR-839-ME-2000 | Installation of Pressure Reducing Skid (839-ME-106) | 5 | 5 | 2025-05-29 | 2025-06-03 | 2025-05-29 | 2025-06-03 | 113
C-52-PR-839-ME-2010 | Installation of Sales Gas Custody Transfer Metering Skid Including Control Valve (839-ME-105) | 8 | 8 | 2025-05-29 | 2025-06-09 | 2025-05-29 | 2025-06-09 | 110
Piping Works |  | 101 | 101 | 2025-02-17 | 2025-05-17 | 2025-03-28 | 2025-07-31 | 14
Piping Works -FabricationCCOSWPI503.1 |  | 21 | 21 | 2025-02-17 | 2025-03-15 | 2025-03-28 | 2025-04-25 | 20
C-52-PR-839-PI-1000 | Piping Pre-Fabrication | 21 | 21 | 2025-02-17 | 2025-03-15 | 2025-03-28 | 2025-04-25 | 20
Piping Works -ErectionCCOSWPI503.2 |  | 80 | 80 | 2025-04-07 | 2025-05-17 | 2025-04-25 | 2025-07-31 | 14
C-52-PR-839-PI-1200 | Piping Erection | 14 | 14 | 2025-04-07 | 2025-04-23 | 2025-04-25 | 2025-05-13 | 65
C-52-PR-839-PI-1400 | Field Joint Welding | 12 | 12 | 2025-04-09 | 2025-04-23 | 2025-04-28 | 2025-05-13 | 65
C-52-PR-839-PI-1600 | Hydrotesting | 5 | 5 | 2025-04-26 | 2025-05-02 | 2025-05-16 | 2025-05-22 | 65
C-52-PR-839-PI-1800 | Installation of Valves/MOV/ROV | 5 | 5 | 2025-05-02 | 2025-05-09 | 2025-07-24 | 2025-07-29 | 14
C-52-PR-839-PI-2000 | Final Bolt Torquing/ Re-Instatement | 3 | 3 | 2025-05-14 | 2025-05-17 | 2025-07-29 | 2025-07-31 | 14
Piping Works -NDT & PaintingCCOSWPI503.3 |  | 12 | 12 | 2025-04-12 | 2025-04-26 | 2025-05-01 | 2025-05-16 | 65
C-52-PR-839-PI-1410 | NDT & Coating for Field Joint Weld | 12 | 12 | 2025-04-12 | 2025-04-26 | 2025-05-01 | 2025-05-16 | 65
Pipeline Works |  | 17 | 17 | 2025-04-23 | 2025-05-14 | 2025-05-13 | 2025-06-02 | 115
Pig Receiver 839-V-101 52'' Pipeline/ Piping Hook-upCCOSWPI514 |  | 17 | 17 | 2025-04-23 | 2025-05-14 | 2025-05-13 | 2025-06-02 | 115
C-52-PR-839-PL-1000 | Installation of Isolation Joint | 2 | 2 | 2025-04-23 | 2025-04-25 | 2025-05-13 | 2025-05-15 | 115
C-52-PR-839-PL-1010 | Field Joint Welding (Piping/Pipeline Section including IJ) | 5 | 5 | 2025-04-25 | 2025-05-01 | 2025-05-15 | 2025-05-21 | 115
C-52-PR-839-PL-1020 | NDT for Weld Joint | 5 | 5 | 2025-05-01 | 2025-05-08 | 2025-05-21 | 2025-05-27 | 115
C-52-PR-839-PL-1030 | Ext. Coating for Weld Joint | 5 | 5 | 2025-05-08 | 2025-05-14 | 2025-05-27 | 2025-06-02 | 115
Electrical & Instrumentation Works |  | 138 | 138 | 2025-04-14 | 2025-07-21 | 2025-04-18 | 2025-10-01 | 14
Deep Earth WellCCOSW52E10.12 |  | 5 | 5 | 2025-06-09 | 2025-06-13 | 2025-06-19 | 2025-06-24 | 87
C-52-PR-839-EI-1400 | Deep Earth Well Drilling | 5 | 5 | 2025-06-09 | 2025-06-13 | 2025-06-19 | 2025-06-24 | 87
E&I Cable Laying, Glanding & TerminationCCOSW52E12 |  | 138 | 138 | 2025-04-14 | 2025-07-21 | 2025-04-18 | 2025-10-01 | 14
C-52-PR-839-EI-2000 | Electrical & Earthing Cable Laying | 8 | 8 | 2025-04-14 | 2025-04-22 | 2025-04-18 | 2025-04-26 | 72
C-52-PR-839-EI-2020 | Installation of Cable Trays | 6 | 6 | 2025-04-23 | 2025-04-29 | 2025-04-28 | 2025-05-03 | 74
C-52-PR-839-EI-2010 | Instrument Cable Laying | 8 | 8 | 2025-04-23 | 2025-05-01 | 2025-04-28 | 2025-05-07 | 72
C-52-PR-839-EI-2030 | Instrument Tubing Works | 6 | 6 | 2025-05-02 | 2025-05-09 | 2025-05-07 | 2025-05-14 | 72
C-52-PR-839-EI-2040 | Loop Checking for Instruments | 8 | 8 | 2025-07-04 | 2025-07-14 | 2025-09-16 | 2025-09-24 | 20
C-52-PR-839-EI-2050 | Glanding & Termination | 10 | 10 | 2025-07-09 | 2025-07-21 | 2025-09-20 | 2025-10-01 | 14
Light Pole, Lighting & FixturesCCOSW52E10.1 |  | 11 | 11 | 2025-06-07 | 2025-06-19 | 2025-06-18 | 2025-07-01 | 82
C-52-PR-839-EI-1800 | Installation of Light Pole, Lighting & Fixtures | 6 | 6 | 2025-06-07 | 2025-06-13 | 2025-06-18 | 2025-06-24 | 82
C-52-PR-839-EI-1810 | Installation of JB's | 5 | 5 | 2025-06-14 | 2025-06-19 | 2025-06-25 | 2025-07-01 | 82
Field InstrumentsCCOSW52E10.32 |  | 76 | 76 | 2025-04-15 | 2025-05-21 | 2025-05-03 | 2025-08-04 | 42
C-52-PR-839-EI-2210 | Pre-Fabrication & Installation of Field Instrument, JB Supports | 21 | 21 | 2025-04-15 | 2025-05-10 | 2025-05-03 | 2025-05-29 | 97
C-52-PR-839-EI-2200 | Installation of Field Instruments (Including Pig Signaller) | 10 | 10 | 2025-05-09 | 2025-05-21 | 2025-07-24 | 2025-08-04 | 14
F&G DevicesCCOSW52E10.42 |  | 5 | 5 | 2025-06-28 | 2025-07-04 | 2025-09-10 | 2025-09-15 | 14
C-52-PR-839-EI-2410 | Installation of F&G Device | 5 | 5 | 2025-06-28 | 2025-07-04 | 2025-09-10 | 2025-09-15 | 14
Cathodic Protection Works |  | 18 | 18 | 2025-06-09 | 2025-06-30 | 2025-06-19 | 2025-07-10 | 84
CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 |  | 18 | 18 | 2025-06-09 | 2025-06-30 | 2025-06-19 | 2025-07-10 | 84
C-52-PR-839-CA-1000 | CP Cable Laying | 5 | 5 | 2025-06-09 | 2025-06-13 | 2025-06-19 | 2025-06-24 | 59
C-52-PR-839-CA-1010 | Installation of CP Test Post | 5 | 5 | 2025-06-14 | 2025-06-19 | 2025-06-25 | 2025-07-01 | 84
C-52-PR-839-CA-1020 | Installation of CP JB's | 5 | 5 | 2025-06-20 | 2025-06-25 | 2025-07-02 | 2025-07-07 | 84
C-52-PR-839-CA-1030 | Glanding & Termination for CP S/m | 3 | 3 | 2025-06-26 | 2025-06-30 | 2025-07-08 | 2025-07-10 | 84
Telecommunication Works |  | 25 | 25 | 2025-06-14 | 2025-07-14 | 2025-06-25 | 2025-07-24 | 72
PIDS System/FOC/CCTVCCOSWIC342 |  | 25 | 25 | 2025-06-14 | 2025-07-14 | 2025-06-25 | 2025-07-24 | 72
C-52-PR-839-TE-1410 | FOC Laying | 14 | 14 | 2025-06-14 | 2025-07-01 | 2025-06-25 | 2025-07-11 | 53
C-52-PR-839-TE-1600 | Installation of CCTV System | 6 | 6 | 2025-07-02 | 2025-07-08 | 2025-07-12 | 2025-07-18 | 72
C-52-PR-839-TE-1420 | FO Cable OTDR Testing & Splicing | 5 | 5 | 2025-07-09 | 2025-07-14 | 2025-07-19 | 2025-07-24 | 72
Electrical Building Type I |  | 224 | 224 | 2024-12-10 | 2025-09-13 | 2025-01-09 | 2025-10-13 | 6
Electrical Building Type I-1 |  | 224 | 224 | 2024-12-10 | 2025-09-13 | 2025-01-09 | 2025-10-13 | 6
Civil Works |  | 159 | 159 | 2024-12-10 | 2025-06-28 | 2025-01-09 | 2025-07-28 | 71
Excavation (incl Bedding)CCOSWCS303 |  | 36 | 36 | 2024-12-10 | 2025-01-21 | 2025-01-09 | 2025-02-19 | 6
C-52-EB1-CI-1000 | Site Survey, Preparation & Grading Works | 10 | 10 | 2024-12-10 | 2024-12-20 | 2025-01-09 | 2025-01-20 | 5
C-52-EB1-CI-1010 | Earth Works for Ground Level | 21 | 21 | 2024-12-21 | 2025-01-15 | 2025-01-21 | 2025-02-13 | 6
C-52-EB1-CI-1020 | Compaction & Testing for Ground Level | 21 | 21 | 2024-12-27 | 2025-01-21 | 2025-01-27 | 2025-02-19 | 6
Foundation Works (for Substructure)CCOSWCS304 |  | 28 | 28 | 2025-01-14 | 2025-02-14 | 2025-02-12 | 2025-03-20 | 6
C-52-EB1-CI-1200 | Building Foundation Works (for Substructure) | 28 | 28 | 2025-01-14 | 2025-02-14 | 2025-02-12 | 2025-03-20 | 6
Concrete Superstructure WorksCCOSWCS305 |  | 22 | 22 | 2025-02-15 | 2025-03-15 | 2025-03-20 | 2025-04-21 | 6
C-52-EB1-CI-1400 | Concrete Superstructure Works | 22 | 22 | 2025-02-15 | 2025-03-15 | 2025-03-20 | 2025-04-21 | 6
Masonry WorksCCOSWCS309 |  | 35 | 35 | 2025-03-15 | 2025-05-02 | 2025-04-21 | 2025-06-02 | 71
C-52-EB1-CI-1600 | Masonry Works - Internal | 21 | 21 | 2025-03-15 | 2025-04-16 | 2025-04-21 | 2025-05-16 | 6
C-52-EB1-CI-1610 | Masonry Works - External | 14 | 14 | 2025-04-16 | 2025-05-02 | 2025-05-16 | 2025-06-02 | 71
Finishing WorksCCOSWCS313 |  | 17 | 17 | 2025-04-24 | 2025-05-15 | 2025-05-24 | 2025-06-16 | 71
C-52-EB1-CI-1810 | Internal Finishing Works | 14 | 14 | 2025-04-24 | 2025-05-12 | 2025-05-24 | 2025-06-12 | 14
C-52-EB1-CI-1800 | External Finishing Works | 10 | 10 | 2025-05-02 | 2025-05-15 | 2025-06-02 | 2025-06-16 | 71
Metal WorksCCOSWCS318 |  | 14 | 14 | 2025-05-15 | 2025-05-31 | 2025-06-16 | 2025-07-03 | 71
C-52-EB1-CI-2000 | Steel Structural Works | 14 | 14 | 2025-05-15 | 2025-05-31 | 2025-06-16 | 2025-07-03 | 71
Paving WorksCCOSWCS319 |  | 21 | 21 | 2025-05-31 | 2025-06-28 | 2025-07-03 | 2025-07-28 | 71
C-52-EB1-CI-2010 | Paving Works | 21 | 21 | 2025-05-31 | 2025-06-28 | 2025-07-03 | 2025-07-28 | 71
Mechanical Works |  | 69 | 69 | 2025-03-15 | 2025-06-14 | 2025-04-21 | 2025-07-15 | 6
HVAC System & Plumbing WorksCCOSWME511 |  | 42 | 42 | 2025-03-15 | 2025-05-12 | 2025-04-21 | 2025-06-12 | 6
C-52-EB1-ME-1000 | Plumbing Works | 21 | 21 | 2025-03-15 | 2025-04-16 | 2025-04-21 | 2025-05-16 | 6
C-52-EB1-ME-1010 | HVAC Works | 21 | 21 | 2025-04-16 | 2025-05-12 | 2025-05-16 | 2025-06-12 | 6
Inergen SystemCCOSWME521 |  | 27 | 27 | 2025-05-12 | 2025-06-14 | 2025-06-12 | 2025-07-15 | 6
C-52-EB1-ME-1200 | Inergen System | 27 | 27 | 2025-05-12 | 2025-06-14 | 2025-06-12 | 2025-07-15 | 6
Electrical & Instrumentation Works |  | 103 | 103 | 2025-05-12 | 2025-09-13 | 2025-06-12 | 2025-10-13 | 6
Power Distribution SystemCCOSW52E16 |  | 5 | 5 | 2025-05-12 | 2025-05-17 | 2025-06-12 | 2025-06-18 | 14
C-52-EB1-EI-1000 | Installation of Power Distribution System | 5 | 5 | 2025-05-12 | 2025-05-17 | 2025-06-12 | 2025-06-18 | 14
Lighting SystemCCOSW52E32 |  | 14 | 14 | 2025-05-17 | 2025-06-03 | 2025-06-18 | 2025-07-05 | 14
C-52-EB1-EI-1400 | Lighting & Fixtures | 14 | 14 | 2025-05-17 | 2025-06-03 | 2025-06-18 | 2025-07-05 | 14
HSSD SystemCCOSW52E62 |  | 12 | 12 | 2025-06-14 | 2025-06-30 | 2025-07-15 | 2025-07-29 | 6
C-52-EB1-EI-2000 | Installation of HSSD System | 12 | 12 | 2025-06-14 | 2025-06-30 | 2025-07-15 | 2025-07-29 | 6
RTU SystemCCOSW52E82 |  | 6 | 6 | 2025-06-30 | 2025-07-07 | 2025-07-29 | 2025-08-05 | 6
C-52-EB1-EI-2200 | Installation of RTU System | 6 | 6 | 2025-06-30 | 2025-07-07 | 2025-07-29 | 2025-08-05 | 6
Custody Metering PanelCCOSW52E102 |  | 6 | 6 | 2025-07-07 | 2025-07-14 | 2025-08-05 | 2025-08-12 | 6
C-52-EB1-EI-1200 | Custody Metering Panel Installation | 6 | 6 | 2025-07-07 | 2025-07-14 | 2025-08-05 | 2025-08-12 | 6
E&I Cable Laying, Glanding & TerminationCCOSW52E18 |  | 52 | 52 | 2025-07-14 | 2025-09-13 | 2025-08-12 | 2025-10-13 | 6
C-52-EB1-EI-1210 | E&I Cable Laying | 21 | 21 | 2025-07-14 | 2025-08-07 | 2025-08-12 | 2025-09-06 | 6
C-52-EB1-EI-1220 | MCT Installation | 8 | 8 | 2025-08-20 | 2025-08-29 | 2025-09-19 | 2025-09-29 | 6
C-52-EB1-EI-1230 | Glanding & Termination | 12 | 12 | 2025-08-29 | 2025-09-13 | 2025-09-29 | 2025-10-13 | 6
Earthing & Lightning Protection systemCCOSW52E42 |  | 14 | 14 | 2025-07-14 | 2025-07-30 | 2025-08-12 | 2025-08-28 | 6
C-52-EB1-EI-1600 | Earthing & Lightning Protection system | 14 | 14 | 2025-07-14 | 2025-07-30 | 2025-08-12 | 2025-08-28 | 6
UPS (10KVA)CCOSW52E72 |  | 10 | 10 | 2025-07-30 | 2025-08-11 | 2025-08-28 | 2025-09-10 | 6
C-52-EB1-EI-2400 | UPS (10KVA) Installation | 10 | 10 | 2025-07-30 | 2025-08-11 | 2025-08-28 | 2025-09-10 | 6
F&G SystemCCOSW52E52 |  | 8 | 8 | 2025-08-11 | 2025-08-20 | 2025-09-10 | 2025-09-19 | 6
C-52-EB1-EI-1800 | Installation F&G System | 8 | 8 | 2025-08-11 | 2025-08-20 | 2025-09-10 | 2025-09-19 | 6
Telecommunication Works |  | 34 | 34 | 2025-06-30 | 2025-08-08 | 2025-07-29 | 2025-09-08 | 36
SDH CabinetCCOSWIC309 |  | 8 | 8 | 2025-06-30 | 2025-07-09 | 2025-07-29 | 2025-08-07 | 36
C-52-EB1-TE-1000 | SDH Cabinet Installation | 8 | 8 | 2025-06-30 | 2025-07-09 | 2025-07-29 | 2025-08-07 | 36
Telecom System (Including subcontract for FOC Splicing / Termination / Testing)CCOSWIC322 |  | 10 | 10 | 2025-07-16 | 2025-07-28 | 2025-08-14 | 2025-08-26 | 36
C-52-EB1-TE-1400 | Telecom System (Including subcontract for FOC Splicing / Termination / Testing) | 10 | 10 | 2025-07-16 | 2025-07-28 | 2025-08-14 | 2025-08-26 | 36
Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOSWIC332 |  | 26 | 26 | 2025-07-09 | 2025-08-08 | 2025-08-07 | 2025-09-08 | 36
C-52-EB1-TE-1600 | CCTV Installation | 6 | 6 | 2025-07-09 | 2025-07-16 | 2025-08-07 | 2025-08-14 | 36
C-52-EB1-TE-1610 | Security System (Including subcontract for FOC Splicing / Termination / Testing ) | 10 | 10 | 2025-07-28 | 2025-08-08 | 2025-08-26 | 2025-09-08 | 36
OHPL |  | 191 | 191 | 2025-01-20 | 2025-10-08 | 2025-02-18 | 2025-10-14 | 5
OHPL-1 |  | 191 | 191 | 2025-01-20 | 2025-10-08 | 2025-02-18 | 2025-10-14 | 5
Civil Works |  | 191 | 191 | 2025-01-20 | 2025-10-08 | 2025-02-18 | 2025-10-14 | 5
Concrete Works (Foundations for Equipment & Pipe Supports)CCOSWCS321 |  | 26 | 26 | 2025-01-20 | 2025-02-18 | 2025-02-18 | 2025-03-24 | 5
C-52-OHPL-CI-1000 | Concrete Works (Foundations for Equipment & Pipe Supports) | 26 | 26 | 2025-01-20 | 2025-02-18 | 2025-02-18 | 2025-03-24 | 5
Trenching for CablesCCOSWCS322 |  | 18 | 18 | 2025-03-08 | 2025-04-07 | 2025-04-10 | 2025-05-01 | 5
C-52-OHPL-CI-1200 | Trenching for Cables | 18 | 18 | 2025-03-08 | 2025-04-07 | 2025-04-10 | 2025-05-01 | 5
Backfilling for CablesCCOSWCS323 |  | 18 | 18 | 2025-09-08 | 2025-10-08 | 2025-09-23 | 2025-10-14 | 5
C-52-OHPL-CI-1400 | Backfilling for Cables | 18 | 18 | 2025-09-08 | 2025-10-08 | 2025-09-23 | 2025-10-14 | 5
Electrical Works |  | 86 | 86 | 2025-05-13 | 2025-09-03 | 2025-06-09 | 2025-09-19 | 5
OHPL Installation Works-Tower/Post installation (Subcontract)CCOSW52E20.1 |  | 46 | 46 | 2025-05-13 | 2025-07-09 | 2025-06-09 | 2025-08-02 | 5
C-52-OHPL-EL-1000 | OHPL Installation Works-Tower/Post installation (Subcontract) | 46 | 46 | 2025-05-13 | 2025-07-09 | 2025-06-09 | 2025-08-02 | 5
OHPL Installation Works - Power Line installation(Subcontract)CCOSW52E20.2 |  | 24 | 24 | 2025-07-09 | 2025-08-06 | 2025-08-02 | 2025-08-30 | 5
C-52-OHPL-EL-1200 | OHPL Installation Works - Power Line installation(Subcontract) | 24 | 24 | 2025-07-09 | 2025-08-06 | 2025-08-02 | 2025-08-30 | 5
Transformer / Directly Buried MV Cables (including testing)CCOSW52E22 |  | 16 | 16 | 2025-08-15 | 2025-09-03 | 2025-08-30 | 2025-09-19 | 5
C-52-OHPL-EL-1400 | Transformer / Directly Buried MV Cables (including testing) | 16 | 16 | 2025-08-15 | 2025-09-03 | 2025-08-30 | 2025-09-19 | 5
Shutdown Works |  | 3 | 3 | 2025-09-03 | 2025-09-08 | 2025-09-19 | 2025-09-23 | 5
Shutdown Connection of OHL & Cable TestingCCOSW52S10 |  | 3 | 3 | 2025-09-03 | 2025-09-08 | 2025-09-19 | 2025-09-23 | 5
C-52-OHPL-EL-2000 | Shutdown Connection of OHL & Cable Testing | 3 | 3 | 2025-09-03 | 2025-09-08 | 2025-09-19 | 2025-09-23 | 5
ADDC Transformer (HV) Shelter |  | 133 | 133 | 2024-10-19 | 2025-10-11 | 2025-01-25 | 2025-07-12 | 83
ADDC Transformer (HV) Shelter-1 |  | 133 | 133 | 2024-10-19 | 2025-10-11 | 2025-01-25 | 2025-07-12 | 83
Earth WorksCCOSW52E112 |  | 23 | 23 | 2024-10-19 | 2024-12-11 | 2025-01-25 | 2025-02-20 | 83
C-52-ADDC-CI-1000 | Site Survey, Preparation & Grading Works | 3 | 3 | 2024-10-19 | 2024-10-22 | 2025-01-25 | 2025-01-28 | 83
C-52-ADDC-CI-1010 | Earth Works for Ground Level | 15 | 15 | 2024-10-22 | 2024-12-05 | 2025-01-28 | 2025-02-14 | 83
C-52-ADDC-CI-1020 | Compaction & Testing Works for Ground Level | 5 | 5 | 2024-12-05 | 2024-12-11 | 2025-02-14 | 2025-02-20 | 83
Civil Structure/ Flooring WorksCCOSW52E122 |  | 20 | 20 | 2024-12-11 | 2025-02-20 | 2025-02-20 | 2025-03-19 | 83
C-52-ADDC-CI-1200 | Civil Structure/ Flooring Works | 20 | 20 | 2024-12-11 | 2025-02-20 | 2025-02-20 | 2025-03-19 | 83
Roofing WorksCCOSW52E132 |  | 20 | 20 | 2025-02-20 | 2025-05-05 | 2025-03-20 | 2025-04-18 | 83
C-52-ADDC-CI-1400 | Roofing Works | 20 | 20 | 2025-02-20 | 2025-05-05 | 2025-03-20 | 2025-04-18 | 83
Finishing WorksCCOSW52E142 |  | 20 | 20 | 2025-05-05 | 2025-07-12 | 2025-04-18 | 2025-05-12 | 83
C-52-ADDC-CI-1600 | Finishing Works for Shelter | 20 | 20 | 2025-05-05 | 2025-07-12 | 2025-04-18 | 2025-05-12 | 83
Transformer/ Switch Gear InstallationCCOSW52E152 |  | 20 | 20 | 2025-07-14 | 2025-08-05 | 2025-05-13 | 2025-06-04 | 83
C-52-ADDC-EL-1000 | Transformer/ Switch Gear Installation | 20 | 20 | 2025-07-14 | 2025-08-05 | 2025-05-13 | 2025-06-04 | 83
Cable Laying, Glanding, Termination & Hook-UpCCOSW52E162 |  | 30 | 30 | 2025-08-06 | 2025-10-11 | 2025-06-07 | 2025-07-12 | 83
C-52-ADDC-EL-1200 | Cable Laying, Glanding, Termination & Hook-Up | 30 | 30 | 2025-08-06 | 2025-10-11 | 2025-06-07 | 2025-07-12 | 83
Hot Tapping Works - DEL/TFP Pipeline |  | 157 | 157 | 2025-02-03 | 2025-10-13 | 2025-03-03 | 2025-09-18 | 44
Hot Tapping Works - DEL/TFP Pipeline-1 |  | 157 | 157 | 2025-02-03 | 2025-10-13 | 2025-03-03 | 2025-09-18 | 44
Civil Works |  | 157 | 157 | 2025-02-03 | 2025-10-13 | 2025-03-03 | 2025-09-18 | 44
Excavation (incl Bedding)CCOSWCS306 |  | 51 | 51 | 2025-02-03 | 2025-04-12 | 2025-03-03 | 2025-05-13 | 127
C-52-D-HT-CI-1000 | Site Survey, Preparation (Include Existing Dismantling Fence) & Grading Works | 10 | 10 | 2025-02-03 | 2025-02-13 | 2025-03-03 | 2025-03-18 | 44
C-52-D-HT-CI-1020 | Earth Works for Pipe Support Foundations | 14 | 14 | 2025-02-14 | 2025-03-01 | 2025-03-19 | 2025-04-10 | 44
C-52-D-HT-CI-1210 | Compaction & Testing for Pipe Support Foundations | 5 | 5 | 2025-03-02 | 2025-03-09 | 2025-04-10 | 2025-04-16 | 44
C-52-D-HT-CI-1080 | Earth Works for Hot Tap Tie in Pit | 14 | 14 | 2025-03-02 | 2025-03-23 | 2025-04-10 | 2025-04-26 | 48
C-52-D-HT-CI-1040 | Earth Works for Access Platforms & Misc. Structural Foundations | 8 | 8 | 2025-03-23 | 2025-04-07 | 2025-04-26 | 2025-05-06 | 127
C-52-D-HT-CI-1280 | Compaction & Testing for Hot Tap Tie in Pit | 8 | 8 | 2025-03-23 | 2025-04-07 | 2025-04-26 | 2025-05-06 | 48
C-52-D-HT-CI-1230 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | 5 | 5 | 2025-04-07 | 2025-04-12 | 2025-05-07 | 2025-05-13 | 127
Concrete WorksCCOSWCS308 |  | 63 | 63 | 2025-03-09 | 2025-05-31 | 2025-04-16 | 2025-07-03 | 100
C-52-D-HT-CI-1600 | Concrete Works for Pipe Support Foundations | 21 | 21 | 2025-03-09 | 2025-04-11 | 2025-04-16 | 2025-05-12 | 44
C-52-D-HT-CI-1480 | Concrete Works for Hot Tap Tie in Pit | 28 | 28 | 2025-04-11 | 2025-05-15 | 2025-05-12 | 2025-06-16 | 44
C-52-D-HT-CI-1420 | Concrete Works for Access Platforms & Misc. Structural Foundations | 14 | 14 | 2025-05-15 | 2025-05-31 | 2025-06-16 | 2025-07-03 | 100
Pipe Supports Fabrication & InstallationCCOSWSS502 |  | 12 | 12 | 2025-03-23 | 2025-04-11 | 2025-04-26 | 2025-05-12 | 104
C-52-D-HT-CI-2000 | Pipe Supports Fabrication & Installation | 12 | 12 | 2025-03-23 | 2025-04-11 | 2025-04-26 | 2025-05-12 | 104
Concrete ProtectionCCOSWCS312 |  | 12 | 12 | 2025-05-09 | 2025-05-23 | 2025-06-10 | 2025-06-24 | 44
C-52-D-HT-CI-1700 | Concrete Protection | 12 | 12 | 2025-05-09 | 2025-05-23 | 2025-06-10 | 2025-06-24 | 44
Fences & Gates ConstructionCCOSWCS314 |  | 48 | 48 | 2025-05-23 | 2025-07-22 | 2025-06-24 | 2025-08-20 | 44
C-52-D-HT-CI-2220 | Fences & Gates Construction | 48 | 48 | 2025-05-23 | 2025-07-22 | 2025-06-24 | 2025-08-20 | 44
Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS510 |  | 12 | 12 | 2025-07-22 | 2025-08-05 | 2025-08-20 | 2025-09-03 | 44
C-52-D-HT-CI-3000 | Platforms/Crossovers/ Guardrails and Bollards/ Windsock | 12 | 12 | 2025-07-22 | 2025-08-05 | 2025-08-20 | 2025-09-03 | 44
Paving WorksCCOSWCS316 |  | 12 | 12 | 2025-09-29 | 2025-10-13 | 2025-09-03 | 2025-09-18 | 44
C-52-D-HT-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment (Including Fence Re-Instatement) | 12 | 12 | 2025-09-29 | 2025-10-13 | 2025-09-03 | 2025-09-18 | 44
Piping Works |  | 54 | 54 | 2025-05-03 | 2025-07-10 | 2025-06-10 | 2025-08-13 | 56
Piping Pre-FabricationCCOSWPI509 |  | 25 | 25 | 2025-05-03 | 2025-06-03 | 2025-06-10 | 2025-07-10 | 56
C-52-D-HT-PI-1000 | Piping Pre-Fabrication | 25 | 25 | 2025-05-03 | 2025-06-03 | 2025-06-10 | 2025-07-10 | 56
ErectionCCOSWPI524 |  | 14 | 14 | 2025-06-03 | 2025-06-21 | 2025-07-10 | 2025-07-26 | 56
C-52-D-HT-PI-1200 | Piping Erection | 14 | 14 | 2025-06-03 | 2025-06-21 | 2025-07-10 | 2025-07-26 | 56
Field Joint Welding, NDT & CoatingCCOSWPI534 |  | 15 | 15 | 2025-06-07 | 2025-06-25 | 2025-07-12 | 2025-07-30 | 56
C-52-D-HT-PI-1400 | Field Joint Welding | 12 | 12 | 2025-06-07 | 2025-06-21 | 2025-07-12 | 2025-07-26 | 56
C-52-D-HT-PI-1410 | NDT & Coating for Field Joint Weld | 12 | 12 | 2025-06-11 | 2025-06-25 | 2025-07-16 | 2025-07-30 | 56
HydrotestingCCOSWPI544 |  | 5 | 5 | 2025-06-25 | 2025-07-02 | 2025-07-30 | 2025-08-05 | 56
C-52-D-HT-PI-1600 | Hydrotesting | 5 | 5 | 2025-06-25 | 2025-07-02 | 2025-07-30 | 2025-08-05 | 56
Installation of ValvesCCOSWPI554 |  | 5 | 5 | 2025-07-02 | 2025-07-08 | 2025-08-05 | 2025-08-11 | 56
C-52-D-HT-PI-1800 | Installation of Valves/GOV/ROV | 5 | 5 | 2025-07-02 | 2025-07-08 | 2025-08-05 | 2025-08-11 | 56
Final Bolt Torquing/ Re-InstatementCCOSWPI564 |  | 3 | 3 | 2025-07-07 | 2025-07-10 | 2025-08-09 | 2025-08-13 | 56
C-52-D-HT-PI-2000 | Final Bolt Torquing/ Re-Instatement | 3 | 3 | 2025-07-07 | 2025-07-10 | 2025-08-09 | 2025-08-13 | 56
Hot Tap Tie-In 839-TP-002 (48"X30") |  | 24 | 24 | 2025-09-04 | 2025-10-03 | 2025-07-03 | 2025-07-31 | 70
Preparation, Marking & UT for Existing Line 48" LineCCOSWHT461 |  | 2 | 2 | 2025-09-04 | 2025-09-08 | 2025-07-03 | 2025-07-05 | 70
C-52-D-HT002-ME-1000 | Preparation, Marking & UT for Existing Line 48" Line | 2 | 2 | 2025-09-04 | 2025-09-08 | 2025-07-03 | 2025-07-05 | 70
Split Tee Welding (48" X 30")CCOSWHT471 |  | 8 | 8 | 2025-09-08 | 2025-09-17 | 2025-07-05 | 2025-07-15 | 70
C-52-D-HT002-ME-1010 | Split Tee Welding (48" X 30") | 8 | 8 | 2025-09-08 | 2025-09-17 | 2025-07-05 | 2025-07-15 | 70
NDT & Testing for Split Tee Weld JointCCOSWHT481 |  | 8 | 8 | 2025-09-09 | 2025-09-18 | 2025-07-07 | 2025-07-16 | 70
C-52-D-HT002-ME-1020 | NDT & Testing for Split Tee Weld Joint | 8 | 8 | 2025-09-09 | 2025-09-18 | 2025-07-07 | 2025-07-16 | 70
Installation of ValvesCCOSWHT491 |  | 2 | 2 | 2025-09-18 | 2025-09-20 | 2025-07-16 | 2025-07-18 | 70
C-52-D-HT002-ME-1030 | Installation of Valves | 2 | 2 | 2025-09-18 | 2025-09-20 | 2025-07-16 | 2025-07-18 | 70
Hot Tapping of Existing 48" LineCCOSWHT501 |  | 9 | 9 | 2025-09-20 | 2025-10-01 | 2025-07-18 | 2025-07-29 | 70
C-52-D-HT002-ME-1040 | Hot Tapping of Existing 48" Line | 9 | 9 | 2025-09-20 | 2025-10-01 | 2025-07-18 | 2025-07-29 | 70
Isolation of Hot Tap JointCCOSWHT511 |  | 2 | 2 | 2025-10-01 | 2025-10-03 | 2025-07-29 | 2025-07-31 | 70
C-52-D-HT002-ME-1050 | Isolation of Hot Tap Joint | 2 | 2 | 2025-10-01 | 2025-10-03 | 2025-07-29 | 2025-07-31 | 70
Tie-In |  | 5 | 5 | 2025-10-04 | 2025-10-10 | 2025-08-01 | 2025-08-07 | 70
Tie in works to 52'' and 20'' PipelineCCOSWPI512 |  | 5 | 5 | 2025-10-04 | 2025-10-10 | 2025-08-01 | 2025-08-07 | 70
C-52-D-HT-ME-2000 | Tie-In with 30" Pipeline | 5 | 5 | 2025-10-04 | 2025-10-10 | 2025-08-01 | 2025-08-07 | 70
Pig Launcher 838-V-602 (52'' Pipeline) |  | 219 | 219 | 2024-12-11 | 2025-09-20 | 2025-01-16 | 2025-10-14 | 5
Pig Launcher 838-V-602 (52'' Pipeline) @ HGCP |  | 219 | 219 | 2024-12-11 | 2025-09-20 | 2025-01-16 | 2025-10-14 | 5
Civil Works |  | 198 | 198 | 2024-12-11 | 2025-08-27 | 2025-01-16 | 2025-09-19 | 26
Earthworks, Site Preparation, Site GradingCCOH52CS30 |  | 70 | 70 | 2024-12-11 | 2025-03-03 | 2025-01-16 | 2025-04-17 | 79
C-52-PL-838-CI-1000 | Site Survey, Preparation & Grading Works | 14 | 14 | 2024-12-11 | 2024-12-26 | 2025-01-16 | 2025-01-31 | 5
C-52-PL-838-CI-1010 | Earth Works for Equipment Foundations | 21 | 21 | 2024-12-27 | 2025-01-21 | 2025-02-01 | 2025-02-25 | 5
C-52-PL-838-CI-1050 | Earth Works for Thrust Anchor Block | 28 | 28 | 2024-12-27 | 2025-01-29 | 2025-02-01 | 2025-03-06 | 54
C-52-PL-838-CI-1020 | Earth Works for Pipe Support Foundations | 21 | 21 | 2025-01-22 | 2025-02-14 | 2025-02-26 | 2025-03-28 | 5
C-52-PL-838-CI-1030 | Earth Works for Field Instrument, JBs & Light Pole Foundations | 14 | 14 | 2025-01-30 | 2025-02-14 | 2025-03-07 | 2025-03-28 | 79
C-52-PL-838-CI-1040 | Earth Works for Access Platforms & Misc. Structural Foundations | 14 | 14 | 2025-02-15 | 2025-03-03 | 2025-03-28 | 2025-04-17 | 79
Compaction & TestingCCOH52CS32 |  | 40 | 40 | 2025-01-22 | 2025-03-11 | 2025-02-26 | 2025-04-23 | 79
C-52-PL-838-CI-1200 | Compaction & Testing for Equipment Foundations | 8 | 8 | 2025-01-22 | 2025-01-30 | 2025-02-26 | 2025-03-08 | 5
C-52-PL-838-CI-1240 | Compaction & Testing for Thrust Anchor Block | 8 | 8 | 2025-01-30 | 2025-02-07 | 2025-03-07 | 2025-03-18 | 54
C-52-PL-838-CI-1220 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | 5 | 5 | 2025-02-15 | 2025-02-20 | 2025-03-28 | 2025-04-07 | 79
C-52-PL-838-CI-1210 | Compaction & Testing for Pipe Support Foundations | 8 | 8 | 2025-02-15 | 2025-02-24 | 2025-03-28 | 2025-04-10 | 5
C-52-PL-838-CI-1230 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | 5 | 5 | 2025-03-03 | 2025-03-11 | 2025-04-17 | 2025-04-23 | 79
Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 |  | 91 | 91 | 2025-01-31 | 2025-05-28 | 2025-03-08 | 2025-07-05 | 41
C-52-PL-838-CI-1400 | Concrete Works for Equipment Foundations | 21 | 21 | 2025-01-31 | 2025-02-24 | 2025-03-08 | 2025-04-10 | 5
C-52-PL-838-CI-1600 | Concrete Works for Pipe Support Foundations | 35 | 35 | 2025-02-25 | 2025-04-16 | 2025-04-10 | 2025-05-22 | 5
C-52-PL-838-CI-1410 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | 14 | 14 | 2025-04-16 | 2025-05-02 | 2025-05-22 | 2025-06-10 | 41
C-52-PL-838-CI-1420 | Concrete Works for Access Platforms & Misc. Structural Foundations | 21 | 21 | 2025-05-02 | 2025-05-28 | 2025-06-10 | 2025-07-05 | 41
Concrete ProtectionCCOH52CS34 |  | 44 | 44 | 2025-04-11 | 2025-06-03 | 2025-05-17 | 2025-07-11 | 57
C-52-PL-838-CI-1700 | Concrete Protection | 44 | 44 | 2025-04-11 | 2025-06-03 | 2025-05-17 | 2025-07-11 | 57
Thrust Anchor BlockCCOH52SS32 |  | 120 | 120 | 2025-02-08 | 2025-07-12 | 2025-03-27 | 2025-08-22 | 49
C-52-PL-838-CI-1510 | Concrete Works for Thrust Anchor Block | 120 | 120 | 2025-02-08 | 2025-07-12 | 2025-03-27 | 2025-08-22 | 49
Pipe Supports Fabrication & InstallationCCOH52SS60 |  | 45 | 45 | 2025-04-16 | 2025-06-11 | 2025-05-22 | 2025-07-17 | 5
C-52-PL-838-CI-2000 | Pre-Fabrication & Installation of Pipe Supports | 45 | 45 | 2025-04-16 | 2025-06-11 | 2025-05-22 | 2025-07-17 | 5
Trenching for Electrical cablesCCOH52CS35.1 |  | 28 | 28 | 2025-03-28 | 2025-05-03 | 2025-03-22 | 2025-04-29 | 68
C-52-PL-838-CI-1800 | Electrical & Earthing Cable Trenching | 28 | 28 | 2025-03-28 | 2025-05-03 | 2025-03-22 | 2025-04-29 | 68
Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOH52SS61 |  | 49 | 49 | 2025-05-28 | 2025-07-28 | 2025-07-05 | 2025-09-01 | 41
C-52-PL-838-CI-3000 | Pre-Fabrication & Installation of Platforms & Crossovers | 28 | 28 | 2025-05-28 | 2025-07-03 | 2025-07-05 | 2025-08-07 | 41
C-52-PL-838-CI-3010 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | 21 | 21 | 2025-07-03 | 2025-07-28 | 2025-08-07 | 2025-09-01 | 41
Trenching for Instrument cablesCCOH52CS35.2 |  | 28 | 28 | 2025-05-03 | 2025-06-09 | 2025-04-29 | 2025-06-02 | 68
C-52-PL-838-CI-1810 | Instrument & Telecom Cable Trenching | 28 | 28 | 2025-05-03 | 2025-06-09 | 2025-04-29 | 2025-06-02 | 68
Paving WorksCCOH52CS36 |  | 28 | 28 | 2025-07-25 | 2025-08-27 | 2025-08-16 | 2025-09-19 | 26
C-52-PL-838-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 28 | 28 | 2025-07-25 | 2025-08-27 | 2025-08-16 | 2025-09-19 | 26
Backfilling for CablesCCOH52CS37 |  | 36 | 36 | 2025-07-10 | 2025-08-21 | 2025-08-01 | 2025-09-13 | 26
C-52-PL-838-CI-2800 | Back Filling for Electrical & Earthing Cable | 21 | 21 | 2025-07-10 | 2025-08-04 | 2025-08-01 | 2025-08-26 | 36
C-52-PL-838-CI-2810 | Back Filling for Instrument & Telecom Cable | 21 | 21 | 2025-07-28 | 2025-08-21 | 2025-08-19 | 2025-09-13 | 26
Mechanical Works & Equipment Installation |  | 36 | 36 | 2025-03-26 | 2025-05-23 | 2025-04-10 | 2025-05-23 | 121
Installation of Pig Launcher (838-V-602)CCOH52ME60 |  | 8 | 8 | 2025-03-26 | 2025-04-09 | 2025-04-10 | 2025-04-19 | 143
C-52-PL-838-ME-1000 | Installation of Pig Launcher (838-V-602) 52" | 8 | 8 | 2025-03-26 | 2025-04-09 | 2025-04-10 | 2025-04-19 | 143
Installation of Pig Signaler (838-V-602)CCOH52ME70 |  | 6 | 6 | 2025-05-16 | 2025-05-23 | 2025-05-16 | 2025-05-23 | 121
C-52-PL-838-ME-1200 | Installation of Pig Signaler (838-V-602) | 6 | 6 | 2025-05-16 | 2025-05-23 | 2025-05-16 | 2025-05-23 | 121
Piping Works |  | 129 | 129 | 2025-02-17 | 2025-07-30 | 2025-03-28 | 2025-09-03 | 39
Piping Works -FabricationCCOH52PI60.1 |  | 37 | 37 | 2025-02-17 | 2025-04-10 | 2025-03-28 | 2025-05-15 | 42
C-52-PL-838-PI-1000 | Piping Pre-Fabrication | 37 | 37 | 2025-02-17 | 2025-04-10 | 2025-03-28 | 2025-05-15 | 42
Piping Works -NDT and PaintingCCOH52PI60.2 |  | 24 | 24 | 2025-06-17 | 2025-07-16 | 2025-07-23 | 2025-08-20 | 5
C-52-PL-838-PI-1410 | NDT & Coating for Field Joint Weld | 24 | 24 | 2025-06-17 | 2025-07-16 | 2025-07-23 | 2025-08-20 | 5
Piping Works -ErectionCCOH52PI60.3 |  | 41 | 41 | 2025-06-11 | 2025-07-30 | 2025-07-17 | 2025-09-03 | 39
C-52-PL-838-PI-1200 | Piping Erection | 24 | 24 | 2025-06-11 | 2025-07-10 | 2025-07-17 | 2025-08-14 | 5
C-52-PL-838-PI-1400 | Field Joint Welding | 24 | 24 | 2025-06-13 | 2025-07-12 | 2025-07-19 | 2025-08-16 | 5
C-52-PL-838-PI-1600 | Hydrotesting | 5 | 5 | 2025-07-16 | 2025-07-22 | 2025-08-20 | 2025-08-26 | 5
C-52-PL-838-PI-1800 | Installation of Valves/MOV/ROV | 5 | 5 | 2025-07-22 | 2025-07-28 | 2025-08-26 | 2025-09-01 | 5
C-52-PL-838-PI-2000 | Final Bolt Torquing/ Re-Instatement | 3 | 3 | 2025-07-26 | 2025-07-30 | 2025-08-30 | 2025-09-03 | 39
Pipeline Works |  | 9 | 9 | 2025-07-16 | 2025-07-26 | 2025-08-20 | 2025-08-30 | 42
Pig Launcher 838-V-602 52'' Pipeline/Piping Hook-upCCOH52PI70 |  | 9 | 9 | 2025-07-16 | 2025-07-26 | 2025-08-20 | 2025-08-30 | 42
C-52-PL-838-PL-1000 | Installation of Isolation Joint | 2 | 2 | 2025-07-16 | 2025-07-18 | 2025-08-20 | 2025-08-22 | 42
C-52-PL-838-PL-1010 | Field Joint Welding (Piping/Pipeline Section including IJ) | 5 | 5 | 2025-07-18 | 2025-07-24 | 2025-08-22 | 2025-08-28 | 42
C-52-PL-838-PL-1020 | NDT for Weld Joint | 5 | 5 | 2025-07-19 | 2025-07-25 | 2025-08-23 | 2025-08-29 | 42
C-52-PL-838-PL-1030 | Ext. Coating for Weld Joint | 5 | 5 | 2025-07-21 | 2025-07-26 | 2025-08-25 | 2025-08-30 | 42
Electrical & Instrumentation Works |  | 69 | 69 | 2025-07-01 | 2025-09-20 | 2025-07-23 | 2025-10-13 | 6
DB & Electrical WorksCCOH52EL50 |  | 60 | 60 | 2025-07-01 | 2025-09-10 | 2025-07-23 | 2025-10-02 | 12
C-52-PL-838-EI-2000 | Electrical & Earthing Cable Laying | 21 | 21 | 2025-07-01 | 2025-07-25 | 2025-07-23 | 2025-08-16 | 6
C-52-PL-838-EI-1400 | Deep Earth Well Drilling | 6 | 6 | 2025-07-18 | 2025-07-25 | 2025-08-09 | 2025-08-16 | 42
C-52-PL-838-EI-1810 | Installation of JB's | 5 | 5 | 2025-08-26 | 2025-09-01 | 2025-09-18 | 2025-09-24 | 10
C-52-PL-838-EI-1800 | Installation of Light Pole, Lighting & Fixtures | 12 | 12 | 2025-08-26 | 2025-09-10 | 2025-09-18 | 2025-10-02 | 12
Field InstrumentsCCOH52EL72 |  | 38 | 38 | 2025-07-03 | 2025-08-29 | 2025-08-07 | 2025-09-22 | 6
C-52-PL-838-EI-2210 | Pre-Fabrication & Installation of Field Instrument, JB Supports | 21 | 21 | 2025-07-03 | 2025-07-28 | 2025-08-07 | 2025-09-01 | 5
C-52-PL-838-EI-2200 | Installation of Field Instruments (Including Pig Signaller) | 12 | 12 | 2025-08-13 | 2025-08-27 | 2025-09-04 | 2025-09-19 | 6
C-52-PL-838-EI-2410 | Installation of F&G Device | 18 | 18 | 2025-08-08 | 2025-08-29 | 2025-08-30 | 2025-09-22 | 6
E&I Cable Laying, Glanding & TerminationCCOH52EL51 |  | 48 | 48 | 2025-07-25 | 2025-09-20 | 2025-08-16 | 2025-10-13 | 6
C-52-PL-838-EI-2010 | Instrument Cable Laying | 21 | 21 | 2025-07-25 | 2025-08-19 | 2025-08-16 | 2025-09-11 | 6
C-52-PL-838-EI-2020 | Installation of Cable Trays | 6 | 6 | 2025-08-19 | 2025-08-26 | 2025-09-11 | 2025-09-18 | 6
C-52-PL-838-EI-2030 | Instrument Tubing Works | 6 | 6 | 2025-08-19 | 2025-08-26 | 2025-09-11 | 2025-09-18 | 6
C-52-PL-838-EI-2040 | Loop Checking for Instruments | 17 | 17 | 2025-08-29 | 2025-09-19 | 2025-09-22 | 2025-10-11 | 6
C-52-PL-838-EI-2050 | Glanding & Termination | 12 | 12 | 2025-09-06 | 2025-09-20 | 2025-09-29 | 2025-10-13 | 6
RTUCCOH52EL82 |  | 3 | 3 | 2025-09-01 | 2025-09-10 | 2025-10-01 | 2025-10-04 | 5
C-52-PL-838-EI-1600 | Installation of RTU (Deleted) | 3 | 3 | 2025-09-01 | 2025-09-10 | 2025-10-01 | 2025-10-04 | 5
Cathodic Protection Works |  | 12 | 12 | 2025-07-25 | 2025-08-08 | 2025-08-16 | 2025-08-30 | 42
CP Anode Bed Installation (subcontract)CCOH52EL52 |  | 12 | 12 | 2025-07-25 | 2025-08-08 | 2025-08-16 | 2025-08-30 | 42
C-52-PL-838-CA-1000 | CP Cable Laying | 6 | 6 | 2025-07-25 | 2025-08-01 | 2025-08-16 | 2025-08-23 | 36
C-52-PL-838-CA-1010 | Installation of CP Test Post | 2 | 2 | 2025-08-01 | 2025-08-04 | 2025-08-23 | 2025-08-26 | 42
C-52-PL-838-CA-1020 | Installation of CP JB's | 2 | 2 | 2025-08-04 | 2025-08-06 | 2025-08-26 | 2025-08-28 | 42
C-52-PL-838-CA-1030 | Glanding & Termination for CP S/m | 2 | 2 | 2025-08-06 | 2025-08-08 | 2025-08-28 | 2025-08-30 | 42
Telecommunication Works |  | 42 | 42 | 2025-08-02 | 2025-09-19 | 2025-08-25 | 2025-10-14 | 5
SDH CabinetCCOH52IC60 |  | 6 | 6 | 2025-09-10 | 2025-09-17 | 2025-10-04 | 2025-10-11 | 5
C-52-PL-838-TE-1000 | SDH Cabinet (Deleted) | 6 | 6 | 2025-09-10 | 2025-09-17 | 2025-10-04 | 2025-10-11 | 5
CCTV System (Including subcontract for FOC Splicing / Termination / Testing )CCOH52IC73 |  | 42 | 42 | 2025-08-02 | 2025-09-19 | 2025-08-25 | 2025-10-14 | 5
C-52-PL-838-TE-1410 | FOC Laying | 14 | 14 | 2025-08-02 | 2025-08-19 | 2025-08-25 | 2025-09-11 | 26
C-52-PL-838-TE-1600 | CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) (Deleted) | 6 | 6 | 2025-09-10 | 2025-09-17 | 2025-10-04 | 2025-10-11 | 5
C-52-PL-838-TE-1420 | FO Cable OTDR Testing & Splicing | 2 | 2 | 2025-09-17 | 2025-09-19 | 2025-10-11 | 2025-10-14 | 5
Intrusion Detection System along Critical Corridor |  | 143 | 143 | 2025-04-15 | 2025-10-13 | 2025-04-28 | 2025-10-17 | 7
Intrusion Detection System along Critical Corridor From KP96.2 to KP98.3 52'' |  | 124 | 124 | 2025-04-15 | 2025-09-12 | 2025-04-28 | 2025-09-25 | 20
Intrusion Detection System along Critical Corridor From KP96.2 to KP98.3 52''-1 |  | 124 | 124 | 2025-04-15 | 2025-09-12 | 2025-04-28 | 2025-09-25 | 20
Civil Works |  | 124 | 124 | 2025-04-15 | 2025-09-12 | 2025-04-28 | 2025-09-25 | 20
Earthworks, Site Preparation, Site GradingCCOH52CS38 |  | 51 | 51 | 2025-04-15 | 2025-06-17 | 2025-04-28 | 2025-07-01 | 7
C-52-IDS1-CI-1000 | Site Survey, Preparation & Grading Works | 10 | 10 | 2025-04-15 | 2025-04-26 | 2025-04-28 | 2025-05-10 | 7
C-52-IDS1-CI-1010 | Earth Works for Solar S/m Foundation | 12 | 12 | 2025-04-26 | 2025-05-12 | 2025-05-10 | 2025-05-24 | 7
C-52-IDS1-CI-1020 | Earth Works for Field Instruments & JBs | 8 | 8 | 2025-05-12 | 2025-05-21 | 2025-05-24 | 2025-06-03 | 7
C-52-IDS1-CI-1030 | Earth Works for CCTV Pole, Fence & Gates Foundation | 21 | 21 | 2025-05-21 | 2025-06-17 | 2025-06-03 | 2025-07-01 | 7
Compaction & TestingCCOH52CS39 |  | 43 | 43 | 2025-05-12 | 2025-07-04 | 2025-05-24 | 2025-07-17 | 14
C-52-IDS1-CI-1200 | Compaction & Testing for Solar S/m Foundation | 8 | 8 | 2025-05-12 | 2025-05-21 | 2025-05-24 | 2025-06-03 | 13
C-52-IDS1-CI-1210 | Compaction & Testing for Field Instruments & JBs | 5 | 5 | 2025-05-21 | 2025-05-27 | 2025-06-03 | 2025-06-11 | 36
C-52-IDS1-CI-1220 | Compaction & Testing for CCTV Pole, Fence & Gates Foundation | 14 | 14 | 2025-06-17 | 2025-07-04 | 2025-07-01 | 2025-07-17 | 14
Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 |  | 63 | 63 | 2025-05-21 | 2025-08-06 | 2025-06-03 | 2025-08-19 | 14
C-52-IDS1-CI-1400 | Concrete Works for Solar S/m Foundation | 28 | 28 | 2025-05-21 | 2025-06-25 | 2025-06-03 | 2025-07-09 | 13
C-52-IDS1-CI-1410 | Concrete Works for Field Instruments & JBs Foundation | 14 | 14 | 2025-06-25 | 2025-07-12 | 2025-07-09 | 2025-07-25 | 13
C-52-IDS1-CI-1420 | Concrete Works for CCTV Pole, Fence & Gates Foundation | 28 | 28 | 2025-07-04 | 2025-08-06 | 2025-07-17 | 2025-08-19 | 14
Concrete ProtectionCCOH52CS41 |  | 11 | 11 | 2025-06-26 | 2025-07-10 | 2025-07-10 | 2025-07-23 | 54
C-52-IDS1-CI-1700 | Concrete Protection | 11 | 11 | 2025-06-26 | 2025-07-10 | 2025-07-10 | 2025-07-23 | 54
Fences & Gates ConstructionCCOH52CS42 |  | 20 | 20 | 2025-07-29 | 2025-08-21 | 2025-08-11 | 2025-09-03 | 38
C-52-IDS1-CI-2220 | Installation of Fence Post & Mesh Works (Type-3) | 14 | 14 | 2025-07-29 | 2025-08-14 | 2025-08-11 | 2025-08-27 | 38
C-52-IDS1-CI-2230 | Installation of Access Gate | 6 | 6 | 2025-08-14 | 2025-08-21 | 2025-08-27 | 2025-09-03 | 38
Trenching for CablesCCOH52CS43 |  | 42 | 42 | 2025-06-17 | 2025-08-06 | 2025-07-01 | 2025-08-19 | 7
C-52-IDS1-CI-1800 | Electrical & Earthing Cable Trenching | 21 | 21 | 2025-06-17 | 2025-07-12 | 2025-07-01 | 2025-07-25 | 7
C-52-IDS1-CI-1810 | Instrument & Telecom Cable Trenching | 21 | 21 | 2025-07-12 | 2025-08-06 | 2025-07-25 | 2025-08-19 | 7
Paving WorksCCOH52CS44 |  | 30 | 30 | 2025-07-24 | 2025-08-28 | 2025-08-06 | 2025-09-11 | 32
C-52-IDS1-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 30 | 30 | 2025-07-24 | 2025-08-28 | 2025-08-06 | 2025-09-11 | 32
Backfilling for CablesCCOH52CS45 |  | 40 | 40 | 2025-07-26 | 2025-09-12 | 2025-08-08 | 2025-09-25 | 20
C-52-IDS1-CI-2800 | Back Filling for Electrical & Earthing Cable | 14 | 14 | 2025-07-26 | 2025-08-12 | 2025-08-08 | 2025-08-25 | 46
C-52-IDS1-CI-2810 | Back Filling for Instrument & Telecom Cable | 14 | 14 | 2025-08-26 | 2025-09-12 | 2025-09-09 | 2025-09-25 | 20
Electrical & Instrumentation Works |  | 37 | 37 | 2025-07-12 | 2025-08-25 | 2025-07-25 | 2025-09-08 | 35
Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 |  | 37 | 37 | 2025-07-12 | 2025-08-25 | 2025-07-25 | 2025-09-08 | 35
C-52-IDS1-EI-1190 | Installation of Solar S/m Structurals | 10 | 10 | 2025-07-12 | 2025-07-24 | 2025-07-25 | 2025-08-06 | 13
C-52-IDS1-EI-2000 | Electrical & Earthing Cable Laying | 12 | 12 | 2025-07-12 | 2025-07-26 | 2025-07-25 | 2025-08-08 | 23
C-52-IDS1-EI-1200 | Installation of Solar S/m (Including Panels, UPS & Battery) | 14 | 14 | 2025-07-24 | 2025-08-09 | 2025-08-06 | 2025-08-22 | 13
C-52-IDS1-EI-1810 | Installation of Lighting & Instrument JB's | 8 | 8 | 2025-08-09 | 2025-08-19 | 2025-08-22 | 2025-09-01 | 35
C-52-IDS1-EI-2010 | Instrument Cable Laying | 12 | 12 | 2025-08-06 | 2025-08-20 | 2025-08-19 | 2025-09-02 | 7
C-52-IDS1-EI-2050 | Glanding & Termination | 5 | 5 | 2025-08-19 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 35
Telecommunication Works |  | 13 | 13 | 2025-08-06 | 2025-08-21 | 2025-08-19 | 2025-09-03 | 14
IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 |  | 13 | 13 | 2025-08-06 | 2025-08-21 | 2025-08-19 | 2025-09-03 | 14
C-52-IDS1-TE-1590 | Installation of CCTV Poles | 5 | 5 | 2025-08-06 | 2025-08-12 | 2025-08-19 | 2025-08-25 | 14
C-52-IDS1-TE-1600 | CCTV Installation | 8 | 8 | 2025-08-12 | 2025-08-21 | 2025-08-25 | 2025-09-03 | 14
Intrusion Detection System along Critical Corridor From KP102 to KP108.9 52'' |  | 126 | 126 | 2025-04-26 | 2025-09-26 | 2025-05-10 | 2025-10-09 | 8
Intrusion Detection System along Critical Corridor From KP102 to KP108.9 52''-1 |  | 126 | 126 | 2025-04-26 | 2025-09-26 | 2025-05-10 | 2025-10-09 | 8
Civil Works |  | 126 | 126 | 2025-04-26 | 2025-09-26 | 2025-05-10 | 2025-10-09 | 8
Earthworks, Site Preparation, Site GradingCCOH52CS46 |  | 44 | 44 | 2025-04-26 | 2025-06-30 | 2025-05-10 | 2025-07-04 | 7
C-52-IDS2-CI-1000 | Site Survey, Preparation & Grading Works | 10 | 10 | 2025-04-26 | 2025-05-09 | 2025-05-10 | 2025-05-22 | 7
C-52-IDS2-CI-1010 | Earth Works for Solar S/m Foundation | 12 | 12 | 2025-05-09 | 2025-05-23 | 2025-05-22 | 2025-06-07 | 7
C-52-IDS2-CI-1020 | Earth Works for Field Instruments & JBs | 8 | 8 | 2025-05-23 | 2025-06-02 | 2025-06-07 | 2025-06-17 | 7
C-52-IDS2-CI-1030 | Earth Works for CCTV Pole, Fence & Gates Foundation | 14 | 14 | 2025-06-02 | 2025-06-30 | 2025-06-17 | 2025-07-04 | 7
Compaction & TestingCCOH52CS47 |  | 36 | 36 | 2025-05-23 | 2025-07-16 | 2025-06-07 | 2025-07-21 | 17
C-52-IDS2-CI-1200 | Compaction & Testing for Solar S/m Foundation | 8 | 8 | 2025-05-23 | 2025-06-02 | 2025-06-07 | 2025-06-17 | 17
C-52-IDS2-CI-1210 | Compaction & Testing for Field Instruments & JBs | 5 | 5 | 2025-06-02 | 2025-06-10 | 2025-06-17 | 2025-06-23 | 40
C-52-IDS2-CI-1220 | Compaction & Testing for CCTV Pole, Fence & Gates Foundation | 14 | 14 | 2025-06-30 | 2025-07-16 | 2025-07-04 | 2025-07-21 | 15
Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 |  | 56 | 56 | 2025-06-02 | 2025-08-18 | 2025-06-17 | 2025-08-22 | 15
C-52-IDS2-CI-1400 | Concrete Works for Solar S/m Foundation | 28 | 28 | 2025-06-02 | 2025-07-08 | 2025-06-17 | 2025-07-21 | 17
C-52-IDS2-CI-1410 | Concrete Works for Field Instruments & JBs Foundation | 14 | 14 | 2025-07-08 | 2025-07-24 | 2025-07-21 | 2025-08-06 | 17
C-52-IDS2-CI-1420 | Concrete Works for CCTV Pole, Fence & Gates Foundation | 28 | 28 | 2025-07-16 | 2025-08-18 | 2025-07-21 | 2025-08-22 | 15
Concrete ProtectionCCOH52CS49 |  | 16 | 16 | 2025-08-05 | 2025-08-23 | 2025-08-09 | 2025-08-28 | 15
C-52-IDS2-CI-1700 | Concrete Protection | 16 | 16 | 2025-08-05 | 2025-08-23 | 2025-08-09 | 2025-08-28 | 15
Fences & Gates ConstructionCCOH52CS50 |  | 20 | 20 | 2025-08-23 | 2025-09-17 | 2025-08-28 | 2025-09-22 | 23
C-52-IDS2-CI-2220 | Installation of Fence Post & Mesh Works (Type-3) | 14 | 14 | 2025-08-23 | 2025-09-10 | 2025-08-28 | 2025-09-15 | 15
C-52-IDS2-CI-2230 | Installation of Access Gate | 6 | 6 | 2025-09-10 | 2025-09-17 | 2025-09-15 | 2025-09-22 | 23
Trenching for CablesCCOH52CS51 |  | 42 | 42 | 2025-06-30 | 2025-08-18 | 2025-07-04 | 2025-08-22 | 7
C-52-IDS2-CI-1800 | Electrical & Earthing Cable Trenching | 21 | 21 | 2025-06-30 | 2025-07-24 | 2025-07-04 | 2025-07-29 | 7
C-52-IDS2-CI-1810 | Instrument & Telecom Cable Trenching | 21 | 21 | 2025-07-24 | 2025-08-18 | 2025-07-29 | 2025-08-22 | 7
Paving WorksCCOH52CS52 |  | 30 | 30 | 2025-08-05 | 2025-09-10 | 2025-08-18 | 2025-09-23 | 22
C-52-IDS2-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 30 | 30 | 2025-08-05 | 2025-09-10 | 2025-08-18 | 2025-09-23 | 22
Backfilling for CablesCCOH52CS53 |  | 35 | 35 | 2025-08-15 | 2025-09-26 | 2025-08-28 | 2025-10-09 | 8
C-52-IDS2-CI-2800 | Back Filling for Electrical & Earthing Cable | 14 | 14 | 2025-08-15 | 2025-09-01 | 2025-08-28 | 2025-09-15 | 29
C-52-IDS2-CI-2810 | Back Filling for Instrument & Telecom Cable | 14 | 14 | 2025-09-10 | 2025-09-26 | 2025-09-23 | 2025-10-09 | 8
Electrical & Instrumentation Works |  | 41 | 41 | 2025-07-24 | 2025-09-11 | 2025-08-06 | 2025-09-24 | 21
Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 |  | 41 | 41 | 2025-07-24 | 2025-09-11 | 2025-08-06 | 2025-09-24 | 21
C-52-IDS2-EI-1190 | Installation of Solar S/m Structurals | 10 | 10 | 2025-07-24 | 2025-08-05 | 2025-08-06 | 2025-08-18 | 17
C-52-IDS2-EI-2000 | Electrical & Earthing Cable Laying | 12 | 12 | 2025-07-26 | 2025-08-09 | 2025-08-08 | 2025-08-22 | 23
C-52-IDS2-EI-1200 | Installation of Solar S/m (Including Panels, UPS & Battery) | 14 | 14 | 2025-08-09 | 2025-08-26 | 2025-08-22 | 2025-09-09 | 13
C-52-IDS2-EI-2010 | Instrument Cable Laying | 12 | 12 | 2025-08-20 | 2025-09-03 | 2025-09-02 | 2025-09-17 | 7
C-52-IDS2-EI-1810 | Installation of Lighting & Instrument JB's | 8 | 8 | 2025-08-26 | 2025-09-04 | 2025-09-09 | 2025-09-18 | 21
C-52-IDS2-EI-2050 | Glanding & Termination | 5 | 5 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-24 | 21
Telecommunication Works |  | 18 | 18 | 2025-08-18 | 2025-09-02 | 2025-08-22 | 2025-09-13 | 14
IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 |  | 18 | 18 | 2025-08-18 | 2025-09-02 | 2025-08-22 | 2025-09-13 | 14
C-52-IDS2-TE-1590 | Installation of CCTV Poles | 5 | 5 | 2025-08-18 | 2025-08-23 | 2025-08-22 | 2025-08-28 | 19
C-52-IDS2-TE-1600 | CCTV Installation | 8 | 8 | 2025-08-23 | 2025-09-02 | 2025-09-03 | 2025-09-13 | 14
Intrusion Detection System along Critical Corridor From KP122 to KP123 52'' |  | 123 | 123 | 2025-05-09 | 2025-10-13 | 2025-05-22 | 2025-10-17 | 7
Intrusion Detection System along Critical Corridor From KP122 to KP123 52''-1 |  | 123 | 123 | 2025-05-09 | 2025-10-13 | 2025-05-22 | 2025-10-17 | 7
Civil Works |  | 123 | 123 | 2025-05-09 | 2025-10-13 | 2025-05-22 | 2025-10-17 | 7
Earthworks, Site Preparation, Site GradingCCOH52CS54 |  | 51 | 51 | 2025-05-09 | 2025-07-11 | 2025-05-22 | 2025-07-24 | 10
C-52-IDS3-CI-1000 | Site Survey, Preparation & Grading Works | 10 | 10 | 2025-05-09 | 2025-05-21 | 2025-05-22 | 2025-06-03 | 10
C-52-IDS3-CI-1010 | Earth Works for Solar S/m Foundation | 12 | 12 | 2025-05-21 | 2025-06-04 | 2025-06-03 | 2025-06-19 | 10
C-52-IDS3-CI-1020 | Earth Works for Field Instruments & JBs | 8 | 8 | 2025-06-04 | 2025-06-16 | 2025-06-19 | 2025-06-30 | 10
C-52-IDS3-CI-1030 | Earth Works for CCTV Pole, Fence & Gates Foundation | 21 | 21 | 2025-06-16 | 2025-07-11 | 2025-06-30 | 2025-07-24 | 10
Compaction & TestingCCOH52CS55 |  | 43 | 43 | 2025-06-04 | 2025-07-28 | 2025-06-19 | 2025-08-09 | 11
C-52-IDS3-CI-1200 | Compaction & Testing for Solar S/m Foundation | 8 | 8 | 2025-06-04 | 2025-06-16 | 2025-06-19 | 2025-06-30 | 18
C-52-IDS3-CI-1210 | Compaction & Testing for Field Instruments & JBs | 5 | 5 | 2025-06-16 | 2025-06-21 | 2025-06-30 | 2025-07-05 | 41
C-52-IDS3-CI-1220 | Compaction & Testing for CCTV Pole, Fence & Gates Foundation | 14 | 14 | 2025-07-11 | 2025-07-28 | 2025-07-24 | 2025-08-09 | 10
Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 |  | 63 | 63 | 2025-06-16 | 2025-08-29 | 2025-06-30 | 2025-09-12 | 10
C-52-IDS3-CI-1400 | Concrete Works for Solar S/m Foundation | 28 | 28 | 2025-06-16 | 2025-07-19 | 2025-06-30 | 2025-08-01 | 18
C-52-IDS3-CI-1410 | Concrete Works for Field Instruments & JBs Foundation | 14 | 14 | 2025-07-19 | 2025-08-05 | 2025-08-01 | 2025-08-18 | 18
C-52-IDS3-CI-1420 | Concrete Works for CCTV Pole, Fence & Gates Foundation | 28 | 28 | 2025-07-28 | 2025-08-29 | 2025-08-09 | 2025-09-12 | 10
Concrete ProtectionCCOH52CS57 |  | 18 | 18 | 2025-08-14 | 2025-09-04 | 2025-08-27 | 2025-09-18 | 12
C-52-IDS3-CI-1700 | Concrete Protection | 18 | 18 | 2025-08-14 | 2025-09-04 | 2025-08-27 | 2025-09-18 | 12
Fences & Gates ConstructionCCOH52CS58 |  | 20 | 20 | 2025-09-10 | 2025-10-03 | 2025-09-18 | 2025-10-11 | 12
C-52-IDS3-CI-2220 | Installation of Fence Post & Mesh Works (Type-3) | 14 | 14 | 2025-09-10 | 2025-09-26 | 2025-09-18 | 2025-10-04 | 12
C-52-IDS3-CI-2230 | Installation of Access Gate | 6 | 6 | 2025-09-26 | 2025-10-03 | 2025-10-04 | 2025-10-11 | 12
Trenching for CablesCCOH52CS59 |  | 42 | 42 | 2025-07-24 | 2025-09-12 | 2025-07-29 | 2025-09-17 | 7
C-52-IDS3-CI-1800 | Electrical & Earthing Cable Trenching | 21 | 21 | 2025-07-24 | 2025-08-18 | 2025-07-29 | 2025-08-22 | 7
C-52-IDS3-CI-1810 | Instrument & Telecom Cable Trenching | 21 | 21 | 2025-08-18 | 2025-09-12 | 2025-08-22 | 2025-09-17 | 7
Paving WorksCCOH52CS60 |  | 30 | 30 | 2025-08-16 | 2025-09-22 | 2025-08-29 | 2025-10-04 | 18
C-52-IDS3-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 30 | 30 | 2025-08-16 | 2025-09-22 | 2025-08-29 | 2025-10-04 | 18
Backfilling for CablesCCOH52CS61 |  | 30 | 30 | 2025-09-08 | 2025-10-13 | 2025-09-12 | 2025-10-17 | 7
C-52-IDS3-CI-2800 | Back Filling for Electrical & Earthing Cable | 14 | 14 | 2025-09-08 | 2025-09-24 | 2025-09-12 | 2025-09-29 | 23
C-52-IDS3-CI-2810 | Back Filling for Instrument & Telecom Cable | 14 | 14 | 2025-09-26 | 2025-10-13 | 2025-10-01 | 2025-10-17 | 7
Electrical & Instrumentation Works |  | 45 | 45 | 2025-08-05 | 2025-09-27 | 2025-08-18 | 2025-10-10 | 13
Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 |  | 45 | 45 | 2025-08-05 | 2025-09-27 | 2025-08-18 | 2025-10-10 | 13
C-52-IDS3-EI-1190 | Installation of Solar S/m Structurals | 10 | 10 | 2025-08-05 | 2025-08-16 | 2025-08-18 | 2025-08-29 | 18
C-52-IDS3-EI-2000 | Electrical & Earthing Cable Laying | 12 | 12 | 2025-08-18 | 2025-09-01 | 2025-08-22 | 2025-09-06 | 23
C-52-IDS3-EI-1200 | Installation of Solar S/m (Including Panels, UPS & Battery) | 14 | 14 | 2025-08-26 | 2025-09-12 | 2025-09-09 | 2025-09-25 | 13
C-52-IDS3-EI-2010 | Instrument Cable Laying | 12 | 12 | 2025-09-12 | 2025-09-26 | 2025-09-17 | 2025-10-01 | 7
C-52-IDS3-EI-1810 | Installation of Lighting & Instrument JB's | 8 | 8 | 2025-09-12 | 2025-09-22 | 2025-09-25 | 2025-10-04 | 13
C-52-IDS3-EI-2050 | Glanding & Termination | 5 | 5 | 2025-09-22 | 2025-09-27 | 2025-10-04 | 2025-10-10 | 13
Telecommunication Works |  | 13 | 13 | 2025-08-29 | 2025-09-15 | 2025-09-12 | 2025-09-27 | 10
IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 |  | 13 | 13 | 2025-08-29 | 2025-09-15 | 2025-09-12 | 2025-09-27 | 10
C-52-IDS3-TE-1590 | Installation of CCTV Poles | 5 | 5 | 2025-08-29 | 2025-09-04 | 2025-09-12 | 2025-09-18 | 10
C-52-IDS3-TE-1600 | CCTV Installation | 8 | 8 | 2025-09-04 | 2025-09-15 | 2025-09-18 | 2025-09-27 | 10
KM-42 Jump over (36") |  | 170 | 170 | 2024-12-21 | 2025-09-17 | 2025-01-21 | 2025-08-21 | 20
36'' Jump-over connection at KM-42 |  | 170 | 170 | 2024-12-21 | 2025-09-17 | 2025-01-21 | 2025-08-21 | 20
Civil Works |  | 160 | 160 | 2024-12-21 | 2025-08-12 | 2025-01-21 | 2025-08-09 | 29
Excavation (incl Bedding)CCOJ42CS20 |  | 36 | 36 | 2024-12-21 | 2025-02-01 | 2025-01-21 | 2025-03-03 | 57
C-36-KM-HT-CI-1000 | Site Survey, Preparation & Grading Works | 8 | 8 | 2024-12-21 | 2024-12-30 | 2025-01-21 | 2025-01-29 | 33
C-36-KM-HT-CI-1020 | Earth Works for Pipe Support Foundations | 14 | 14 | 2024-12-31 | 2025-01-16 | 2025-01-30 | 2025-02-14 | 33
C-36-KM-HT-CI-1030 | Earth Works for Field Instrument, JBs | 6 | 6 | 2025-01-17 | 2025-01-23 | 2025-02-15 | 2025-02-21 | 51
C-36-KM-HT-CI-1040 | Earth Works for Access Platforms & Misc. Structural Foundations | 8 | 8 | 2025-01-24 | 2025-02-01 | 2025-02-22 | 2025-03-03 | 57
C-36-KM-HT-CI-1080 | Earth Works for Hot Tap Tie in Pit | 28 | 28 | 2024-12-31 | 2025-02-01 | 2025-01-30 | 2025-03-03 | 44
Compaction & TestingCCOJ42CS22 |  | 22 | 22 | 2025-01-17 | 2025-02-11 | 2025-02-15 | 2025-03-15 | 101
C-36-KM-HT-CI-1210 | Compaction & Testing for Pipe Support Foundations | 8 | 8 | 2025-01-17 | 2025-01-25 | 2025-02-15 | 2025-02-24 | 33
C-36-KM-HT-CI-1220 | Compaction & Testing for Field Instrument, JBs | 5 | 5 | 2025-01-24 | 2025-01-29 | 2025-02-22 | 2025-02-27 | 51
C-36-KM-HT-CI-1230 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | 5 | 5 | 2025-02-03 | 2025-02-07 | 2025-03-03 | 2025-03-11 | 57
C-36-KM-HT-CI-1280 | Compaction & Testing for Hot Tap Tie in Pit | 8 | 8 | 2025-02-03 | 2025-02-11 | 2025-03-03 | 2025-03-15 | 101
Concrete Pit (For Hot Tapping)CCOJ42CS24 |  | 45 | 45 | 2025-02-20 | 2025-04-23 | 2025-03-26 | 2025-05-23 | 94
CCV-52-KM-1120 | Concrete Works for Hot Tap Tie in Pit | 45 | 45 | 2025-02-20 | 2025-04-23 | 2025-03-26 | 2025-05-23 | 94
Concrete Works (Foundations for Equipment)CCOJ42CS44 |  | 28 | 28 | 2025-02-20 | 2025-04-03 | 2025-03-26 | 2025-05-02 | 33
C-36-KM-HT-CI-1410 | Concrete Works for Field Instrument, JBs | 14 | 14 | 2025-02-20 | 2025-03-09 | 2025-03-26 | 2025-04-16 | 33
C-36-KM-HT-CI-1420 | Concrete Works for Access Platforms & Misc. Structural Foundations | 14 | 14 | 2025-03-09 | 2025-04-03 | 2025-04-16 | 2025-05-02 | 33
Concrete Works (Foundations for Pipe Supports)CCOJ42CS28 |  | 21 | 21 | 2025-01-27 | 2025-02-19 | 2025-02-25 | 2025-03-26 | 33
C-36-KM-HT-CI-1600 | Concrete Works for Pipe Support Foundations | 21 | 21 | 2025-01-27 | 2025-02-19 | 2025-02-25 | 2025-03-26 | 33
Trenching for CablesCCOJ42CS30 |  | 24 | 24 | 2025-02-03 | 2025-03-01 | 2025-03-03 | 2025-04-10 | 88
C-36-KM-HT-CI-1800 | Electrical & Earthing Cable Trenching | 12 | 12 | 2025-02-03 | 2025-02-15 | 2025-03-03 | 2025-03-22 | 88
C-36-KM-HT-CI-1810 | Instrument & Telecom Cable Trenching | 12 | 12 | 2025-02-17 | 2025-03-01 | 2025-03-22 | 2025-04-10 | 88
Pipe Supports Fabrication & InstallationCCOJ42SS70 |  | 12 | 12 | 2025-02-20 | 2025-03-06 | 2025-03-26 | 2025-04-14 | 60
C-36-KM-HT-CI-2000 | Pipe Supports Fabrication & Installation | 12 | 12 | 2025-02-20 | 2025-03-06 | 2025-03-26 | 2025-04-14 | 60
Fences & Gates ConstructionCCOJ42CS26 |  | 52 | 52 | 2025-04-03 | 2025-06-04 | 2025-05-02 | 2025-07-07 | 33
C-36-KM-HT-CI-2220 | Fences & Gates Construction | 52 | 52 | 2025-04-03 | 2025-06-04 | 2025-05-02 | 2025-07-07 | 33
Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOJ42SS72 |  | 12 | 12 | 2025-06-04 | 2025-06-20 | 2025-07-07 | 2025-07-21 | 33
C-36-KM-HT-CI-3000 | Platforms/Crossovers/ Guardrails and Bollards/ Windsock | 12 | 12 | 2025-06-04 | 2025-06-20 | 2025-07-07 | 2025-07-21 | 33
Backfilling for CablesCCOJ42CS34 |  | 20 | 20 | 2025-07-03 | 2025-07-26 | 2025-07-01 | 2025-07-24 | 29
C-36-KM-HT-CI-2800 | Back Filling for Electrical & Earthing Cable | 8 | 8 | 2025-07-03 | 2025-07-12 | 2025-07-01 | 2025-07-10 | 33
C-36-KM-HT-CI-2810 | Back Filling for Instrument & Telecom Cable | 8 | 8 | 2025-07-17 | 2025-07-26 | 2025-07-15 | 2025-07-24 | 29
Paving WorksCCOJ42CS32 |  | 14 | 14 | 2025-07-26 | 2025-08-12 | 2025-07-24 | 2025-08-09 | 29
C-36-KM-HT-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 14 | 14 | 2025-07-26 | 2025-08-12 | 2025-07-24 | 2025-08-09 | 29
Piping Works |  | 63 | 63 | 2025-04-26 | 2025-07-14 | 2025-05-31 | 2025-08-16 | 20
Piping Pre-FabricationCCOJ42PI070 |  | 28 | 28 | 2025-04-26 | 2025-05-30 | 2025-05-31 | 2025-07-07 | 20
C-36-KM-HT-PI-1000 | Piping Pre-Fabrication | 28 | 28 | 2025-04-26 | 2025-05-30 | 2025-05-31 | 2025-07-07 | 20
ErectionCCOJ42PI082 |  | 18 | 18 | 2025-05-30 | 2025-06-23 | 2025-07-07 | 2025-07-28 | 20
C-36-KM-HT-PI-1200 | Piping Erection | 18 | 18 | 2025-05-30 | 2025-06-23 | 2025-07-07 | 2025-07-28 | 20
Field Joint Welding, NDT & CoatingCCOJ42PI092 |  | 21 | 21 | 2025-06-02 | 2025-06-30 | 2025-07-09 | 2025-08-02 | 20
C-36-KM-HT-PI-1400 | Field Joint Welding | 18 | 18 | 2025-06-02 | 2025-06-25 | 2025-07-09 | 2025-07-30 | 20
C-36-KM-HT-PI-1410 | NDT & Coating for Field Joint Weld | 18 | 18 | 2025-06-07 | 2025-06-30 | 2025-07-12 | 2025-08-02 | 20
HydrotestingCCOJ42PI102 |  | 5 | 5 | 2025-06-30 | 2025-07-05 | 2025-08-02 | 2025-08-08 | 20
C-36-KM-HT-PI-1600 | Hydrotesting | 5 | 5 | 2025-06-30 | 2025-07-05 | 2025-08-02 | 2025-08-08 | 20
Installation of ValvesCCOJ42PI112 |  | 5 | 5 | 2025-07-05 | 2025-07-11 | 2025-08-08 | 2025-08-14 | 20
C-36-KM-HT-PI-1800 | Installation of Valves/GOV/ROV | 5 | 5 | 2025-07-05 | 2025-07-11 | 2025-08-08 | 2025-08-14 | 20
Final Bolt Torquing/ Re-InstatementCCOJ42PI122 |  | 3 | 3 | 2025-07-10 | 2025-07-14 | 2025-08-13 | 2025-08-16 | 20
C-36-KM-HT-PI-2000 | Final Bolt Torquing/ Re-Instatement | 3 | 3 | 2025-07-10 | 2025-07-14 | 2025-08-13 | 2025-08-16 | 20
Electrical & Instrumentation Works |  | 54 | 54 | 2025-06-12 | 2025-08-15 | 2025-06-10 | 2025-08-13 | 26
Cable Laying & TerminationCCOJ42EL53 |  | 24 | 24 | 2025-06-12 | 2025-07-11 | 2025-06-10 | 2025-07-09 | 26
C-36-KM-HT-EI-2000 | Electrical & Earthing Cable Laying | 12 | 12 | 2025-06-12 | 2025-06-26 | 2025-06-10 | 2025-06-24 | 26
C-36-KM-HT-EI-2010 | Instrument Cable Laying | 12 | 12 | 2025-06-26 | 2025-07-11 | 2025-06-24 | 2025-07-09 | 26
E&I WorksCCOJ42EL51 |  | 30 | 30 | 2025-07-11 | 2025-08-15 | 2025-07-09 | 2025-08-13 | 26
C-36-KM-HT-EI-2030 | Instrument Tubing Works | 10 | 10 | 2025-07-11 | 2025-07-23 | 2025-07-09 | 2025-07-21 | 26
C-36-KM-HT-EI-2200 | Installation of Field Instruments & JB's | 8 | 8 | 2025-07-23 | 2025-08-01 | 2025-07-21 | 2025-07-30 | 26
C-36-KM-HT-EI-2040 | Loop Checking for Instruments | 6 | 6 | 2025-08-01 | 2025-08-08 | 2025-07-30 | 2025-08-06 | 26
C-36-KM-HT-EI-2050 | Glanding & Termination | 6 | 6 | 2025-08-08 | 2025-08-15 | 2025-08-06 | 2025-08-13 | 26
Hot Tap Tie-In 560-TP-003 (36"X36") |  | 22 | 22 | 2025-07-09 | 2025-08-04 | 2025-05-03 | 2025-05-29 | 51
Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT30 |  | 2 | 2 | 2025-07-09 | 2025-07-11 | 2025-05-03 | 2025-05-06 | 51
C-36-KM-HT03-ME-1000 | Preparation, Marking & UT for Existing Line 36" Line | 2 | 2 | 2025-07-09 | 2025-07-11 | 2025-05-03 | 2025-05-06 | 51
Split Tee Welding (36" X 36")CCOJ42HT40 |  | 7 | 7 | 2025-07-11 | 2025-07-19 | 2025-05-06 | 2025-05-14 | 51
C-36-KM-HT03-ME-1010 | Split Tee Welding (36" X 36") | 7 | 7 | 2025-07-11 | 2025-07-19 | 2025-05-06 | 2025-05-14 | 51
NDT & Testing for Split Tee Weld JointCCOJ42HT50 |  | 7 | 7 | 2025-07-12 | 2025-07-21 | 2025-05-07 | 2025-05-15 | 51
C-36-KM-HT03-ME-1020 | NDT & Testing for Split Tee Weld Joint | 7 | 7 | 2025-07-12 | 2025-07-21 | 2025-05-07 | 2025-05-15 | 51
Installation of ValvesCCOJ42HT60 |  | 2 | 2 | 2025-07-21 | 2025-07-23 | 2025-05-15 | 2025-05-17 | 51
C-36-KM-HT03-ME-1030 | Installation of Valves | 2 | 2 | 2025-07-21 | 2025-07-23 | 2025-05-15 | 2025-05-17 | 51
Hot Tapping of Existing 36" LineCCOJ42HT70 |  | 8 | 8 | 2025-07-23 | 2025-08-01 | 2025-05-17 | 2025-05-27 | 51
C-36-KM-HT03-ME-1040 | Hot Tapping of Existing 36" Line | 8 | 8 | 2025-07-23 | 2025-08-01 | 2025-05-17 | 2025-05-27 | 51
Isolation of Hot Tap JointCCOJ42HT80 |  | 2 | 2 | 2025-08-01 | 2025-08-04 | 2025-05-27 | 2025-05-29 | 51
C-36-KM-HT03-ME-1050 | Isolation of Hot Tap Joint | 2 | 2 | 2025-08-01 | 2025-08-04 | 2025-05-27 | 2025-05-29 | 51
Hot Tap Tie-In 560-TP-004 (36"X36") |  | 22 | 22 | 2025-08-09 | 2025-09-04 | 2025-06-04 | 2025-07-03 | 51
Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT090 |  | 2 | 2 | 2025-08-09 | 2025-08-12 | 2025-06-04 | 2025-06-09 | 51
C-36-KM-HT04-ME-1000 | Preparation, Marking & UT for Existing Line 36" Line | 2 | 2 | 2025-08-09 | 2025-08-12 | 2025-06-04 | 2025-06-09 | 51
Split Tee Welding (36" X 36")CCOJ42HT100 |  | 7 | 7 | 2025-08-12 | 2025-08-20 | 2025-06-09 | 2025-06-17 | 51
C-36-KM-HT04-ME-1010 | Split Tee Welding (36" X 36") | 7 | 7 | 2025-08-12 | 2025-08-20 | 2025-06-09 | 2025-06-17 | 51
NDT & Testing for Split Tee Weld JointCCOJ42HT110 |  | 7 | 7 | 2025-08-13 | 2025-08-21 | 2025-06-10 | 2025-06-18 | 51
C-36-KM-HT04-ME-1020 | NDT & Testing for Split Tee Weld Joint | 7 | 7 | 2025-08-13 | 2025-08-21 | 2025-06-10 | 2025-06-18 | 51
Installation of ValvesCCOJ42HT120 |  | 2 | 2 | 2025-08-21 | 2025-08-23 | 2025-06-18 | 2025-06-20 | 51
C-36-KM-HT04-ME-1030 | Installation of Valves | 2 | 2 | 2025-08-21 | 2025-08-23 | 2025-06-18 | 2025-06-20 | 51
Hot Tapping of Existing 36" LineCCOJ42HT130 |  | 8 | 8 | 2025-08-23 | 2025-09-02 | 2025-06-20 | 2025-07-01 | 51
C-36-KM-HT04-ME-1040 | Hot Tapping of Existing 36" Line | 8 | 8 | 2025-08-23 | 2025-09-02 | 2025-06-20 | 2025-07-01 | 51
Isolation of Hot Tap JointCCOJ42HT140 |  | 2 | 2 | 2025-09-02 | 2025-09-04 | 2025-07-01 | 2025-07-03 | 51
C-36-KM-HT04-ME-1050 | Isolation of Hot Tap Joint | 2 | 2 | 2025-09-02 | 2025-09-04 | 2025-07-01 | 2025-07-03 | 51
Tie in Works |  | 4 | 4 | 2025-09-12 | 2025-09-17 | 2025-08-16 | 2025-08-21 | 20
Tie -in WorksCCOJ42PI72 |  | 4 | 4 | 2025-09-12 | 2025-09-17 | 2025-08-16 | 2025-08-21 | 20
C-36-KM-HT-ME-2000 | Tie-In with 36" Pipeline | 4 | 4 | 2025-09-12 | 2025-09-17 | 2025-08-16 | 2025-08-21 | 20
Habshan-5 4" P/L to HGCP 4" P/R (4") |  | 370 | 254 | 2024-06-14 | 2025-08-20 | 14-Jun-24 A | 2025-09-13 | 30
4'' Nitrogen 24Km from Habshan-5 to HGCP Compressor Station |  | 370 | 254 | 2024-06-14 | 2025-08-20 | 14-Jun-24 A | 2025-09-13 | 23
4" Nitrogen Line for Habshan-5 to HGCP (20.7 km) |  | 370 | 254 | 2024-06-14 | 2025-08-20 | 14-Jun-24 A | 2025-09-13 | 23
Main Pipeline |  | 370 | 254 | 2024-06-14 | 2025-08-20 | 14-Jun-24 A | 2025-09-13 | 23
SurveyingCCOPL4"100 |  | 29 | 0 | 2024-06-14 | 2024-07-23 | 14-Jun-24 A | 23-Jul-24 A
C-4N-H5HG-PIPEL-1000 | Survey Marking | 29 | 0 | 2024-06-14 | 2024-07-23 | 14-Jun-24 A | 23-Jul-24 A
ROW Access RoadCCOPL4"102 |  | 137 | 21 | 2024-06-14 | 2024-11-21 | 14-Jun-24 A | 2024-11-27 | 28
C-4N-H5HG-PIPEL-1800 | Sabka ROW/Grading | 137 | 21 | 2024-06-14 | 2024-11-21 | 14-Jun-24 A | 2024-11-27 | 28
Cut & FillCCOPL4"101 |  | 28 | 28 | 2024-11-27 | 2025-01-02 | 2024-12-05 | 2025-01-07 | 97
C-4N-H5HG-PIPEL-1400 | Cut & Fill (@ Non-Sabkha) | 28 | 28 | 2024-11-27 | 2025-01-02 | 2024-12-05 | 2025-01-07 | 97
Excavation (incl Bedding)CCOPL4"106 |  | 55 | 55 | 2024-12-10 | 2025-02-12 | 2025-02-13 | 2025-04-28 | 23
C-4N-H5HG-PIPEL-2400 | Trench Excavation | 48 | 48 | 2024-12-10 | 2025-02-04 | 2025-02-13 | 2025-04-19 | 23
C-4N-H5HG-PIPEL-2410 | Bedding | 48 | 48 | 2024-12-18 | 2025-02-12 | 2025-02-21 | 2025-04-28 | 23
Pipe StringingCCOPL4"104 |  | 42 | 42 | 2024-12-19 | 2025-02-07 | 2024-12-25 | 2025-02-13 | 38
C-4N-H5HG-PIPEL-2800 | Stringing (HB-5 to HGCP) | 42 | 42 | 2024-12-19 | 2025-02-07 | 2024-12-25 | 2025-02-13 | 38
Manual Welding from Habshan 5 to KP-12CCOPL4"105.1 |  | 23 | 23 | 2024-12-21 | 2025-01-18 | 2024-12-27 | 2025-01-23 | 96
C-4N-H5HG-PIPEL-3600 | Welding | 23 | 23 | 2024-12-21 | 2025-01-18 | 2024-12-27 | 2025-01-23 | 96
Manual Welding from KP-12 to HGCP Compressor StationCCOPL4"105.2 |  | 22 | 22 | 2025-01-18 | 2025-02-13 | 2025-01-24 | 2025-02-18 | 99
C-4N-H5HG-PIPEL-3800 | Welding | 22 | 22 | 2025-01-18 | 2025-02-13 | 2025-01-24 | 2025-02-18 | 99
NDT Test Habshan 5 to KP-12CCOPL4"107.1 |  | 23 | 23 | 2024-12-23 | 2025-01-20 | 2024-12-28 | 2025-01-24 | 96
C-4N-H5HG-PIPEL-4000 | NDT | 23 | 23 | 2024-12-23 | 2025-01-20 | 2024-12-28 | 2025-01-24 | 96
NDT Test from KP-12 to HGCP Compressor StationCCOPL4"107.2 |  | 23 | 23 | 2025-01-20 | 2025-02-15 | 2025-01-25 | 2025-02-20 | 99
C-4N-H5HG-PIPEL-4200 | NDT | 23 | 23 | 2025-01-20 | 2025-02-15 | 2025-01-25 | 2025-02-20 | 99
Ext. Joint Coating from Habshan 5 to KP-12CCOPL4"111.1 |  | 104 | 104 | 2024-12-25 | 2025-02-26 | 2024-12-31 | 2025-05-13 | 23
C-4N-H5HG-PIPEL-4400 | Ext. Joint Coating | 23 | 23 | 2024-12-25 | 2025-01-22 | 2024-12-31 | 2025-01-27 | 96
C-4N-H5HG-PIPEL-4410 | Ext. Joint Coating (Tie-in Joint) | 26 | 26 | 2025-01-28 | 2025-02-26 | 2025-04-11 | 2025-05-13 | 23
Ext. Joint Coating from KP-12 to HGCP Compressor StationCCOPL4"111.2 |  | 107 | 107 | 2025-01-22 | 2025-04-08 | 2025-01-28 | 2025-06-14 | 23
C-4N-H5HG-PIPEL-4600 | Ext. Joint Coating | 22 | 22 | 2025-01-22 | 2025-02-17 | 2025-01-28 | 2025-02-21 | 99
C-4N-H5HG-PIPEL-4610 | Ext. Joint Coating (Tie-in Joint) | 26 | 26 | 2025-02-27 | 2025-04-08 | 2025-05-13 | 2025-06-14 | 23
Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 |  | 29 | 29 | 2025-01-25 | 2025-02-27 | 2025-04-09 | 2025-05-14 | 23
C-4N-H5HG-PIPEL-4800 | Lowering | 21 | 21 | 2025-01-25 | 2025-02-18 | 2025-04-09 | 2025-05-03 | 23
C-4N-H5HG-PIPEL-4810 | Section Tie-in Welding | 26 | 26 | 2025-01-25 | 2025-02-24 | 2025-04-09 | 2025-05-10 | 23
C-4N-H5HG-PIPEL-4820 | NDT (Tie-in Joint) | 26 | 26 | 2025-01-27 | 2025-02-25 | 2025-04-10 | 2025-05-12 | 23
C-4N-H5HG-PIPEL-4830 | Holiday Testing | 26 | 26 | 2025-01-29 | 2025-02-27 | 2025-04-12 | 2025-05-14 | 23
Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 |  | 34 | 34 | 2025-02-19 | 2025-04-09 | 2025-05-03 | 2025-06-16 | 23
C-4N-H5HG-PIPEL-5000 | Lowering | 21 | 21 | 2025-02-19 | 2025-03-18 | 2025-05-03 | 2025-05-29 | 28
C-4N-H5HG-PIPEL-5010 | Section Tie-in Welding | 26 | 26 | 2025-02-25 | 2025-04-05 | 2025-05-10 | 2025-06-12 | 23
C-4N-H5HG-PIPEL-5020 | NDT (Tie-in Joint) | 26 | 26 | 2025-02-26 | 2025-04-07 | 2025-05-12 | 2025-06-13 | 23
C-4N-H5HG-PIPEL-5030 | Holiday Testing | 26 | 26 | 2025-02-28 | 2025-04-09 | 2025-05-14 | 2025-06-16 | 23
Crossings - UG PipeCCOPL4"109 |  | 72 | 72 | 2025-02-14 | 2025-05-20 | 2025-02-20 | 2025-05-26 | 40
Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) |  | 12 | 12 | 2025-02-14 | 2025-02-28 | 2025-02-20 | 2025-03-06 | 100
C-4N-H5HG-CMA01-1000 | Trench Excavation | 6 | 6 | 2025-02-14 | 2025-02-21 | 2025-02-20 | 2025-02-26 | 40
C-4N-H5HG-CMA01-1010 | Bedding | 1 | 1 | 2025-02-20 | 2025-02-21 | 2025-02-26 | 2025-02-26 | 90
C-4N-H5HG-CMA01-1020 | Lowering | 1 | 1 | 2025-02-21 | 2025-02-22 | 2025-02-27 | 2025-02-27 | 90
C-4N-H5HG-CMA01-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-21 | 2025-02-24 | 2025-02-27 | 2025-02-28 | 100
C-4N-H5HG-CMA01-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-22 | 2025-02-25 | 2025-02-28 | 2025-03-01 | 100
C-4N-H5HG-CMA01-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-24 | 2025-02-26 | 2025-03-01 | 2025-03-03 | 100
C-4N-H5HG-CMA01-1060 | Holiday Testing | 1 | 1 | 2025-02-26 | 2025-02-27 | 2025-03-03 | 2025-03-05 | 100
C-4N-H5HG-CMA01-1070 | Padding | 1 | 1 | 2025-02-27 | 2025-02-28 | 2025-03-05 | 2025-03-06 | 100
Crossing Manual @ KP 1+390 (PX-04) |  | 12 | 12 | 2025-02-21 | 2025-03-08 | 2025-02-27 | 2025-03-15 | 94
C-4N-H5HG-CMA02-1000 | Trench Excavation | 6 | 6 | 2025-02-21 | 2025-02-28 | 2025-02-27 | 2025-03-06 | 40
C-4N-H5HG-CMA02-1010 | Bedding | 1 | 1 | 2025-02-27 | 2025-02-28 | 2025-03-05 | 2025-03-06 | 85
C-4N-H5HG-CMA02-1020 | Lowering | 1 | 1 | 2025-02-28 | 2025-03-01 | 2025-03-07 | 2025-03-08 | 85
C-4N-H5HG-CMA02-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-28 | 2025-03-02 | 2025-03-07 | 2025-03-09 | 94
C-4N-H5HG-CMA02-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-03-01 | 2025-03-03 | 2025-03-08 | 2025-03-11 | 94
C-4N-H5HG-CMA02-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-02 | 2025-03-05 | 2025-03-09 | 2025-03-12 | 94
C-4N-H5HG-CMA02-1060 | Holiday Testing | 1 | 1 | 2025-03-05 | 2025-03-07 | 2025-03-13 | 2025-03-14 | 94
C-4N-H5HG-CMA02-1070 | Padding | 1 | 1 | 2025-03-07 | 2025-03-08 | 2025-03-14 | 2025-03-15 | 94
Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) |  | 12 | 12 | 2025-02-28 | 2025-03-17 | 2025-03-07 | 2025-03-24 | 88
C-4N-H5HG-CMA03-1000 | Trench Excavation | 6 | 6 | 2025-02-28 | 2025-03-08 | 2025-03-07 | 2025-03-15 | 40
C-4N-H5HG-CMA03-1010 | Bedding | 1 | 1 | 2025-03-07 | 2025-03-08 | 2025-03-14 | 2025-03-15 | 80
C-4N-H5HG-CMA03-1020 | Lowering | 1 | 1 | 2025-03-08 | 2025-03-09 | 2025-03-15 | 2025-03-17 | 80
C-4N-H5HG-CMA03-1030 | Section Tie-in Welding | 2 | 2 | 2025-03-08 | 2025-03-11 | 2025-03-15 | 2025-03-18 | 88
C-4N-H5HG-CMA03-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-03-09 | 2025-03-13 | 2025-03-17 | 2025-03-20 | 88
C-4N-H5HG-CMA03-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-11 | 2025-03-14 | 2025-03-19 | 2025-03-22 | 88
C-4N-H5HG-CMA03-1060 | Holiday Testing | 1 | 1 | 2025-03-14 | 2025-03-15 | 2025-03-22 | 2025-03-23 | 88
C-4N-H5HG-CMA03-1070 | Padding | 1 | 1 | 2025-03-15 | 2025-03-17 | 2025-03-23 | 2025-03-24 | 88
Crossing Manual @ KP 2+519 (PX-07) |  | 12 | 12 | 2025-03-08 | 2025-03-26 | 2025-03-15 | 2025-04-05 | 82
C-4N-H5HG-CMA04-1000 | Trench Excavation | 6 | 6 | 2025-03-08 | 2025-03-17 | 2025-03-15 | 2025-03-24 | 40
C-4N-H5HG-CMA04-1010 | Bedding | 1 | 1 | 2025-03-15 | 2025-03-17 | 2025-03-23 | 2025-03-24 | 75
C-4N-H5HG-CMA04-1020 | Lowering | 1 | 1 | 2025-03-17 | 2025-03-19 | 2025-03-25 | 2025-03-26 | 75
C-4N-H5HG-CMA04-1030 | Section Tie-in Welding | 2 | 2 | 2025-03-17 | 2025-03-20 | 2025-03-25 | 2025-03-28 | 82
C-4N-H5HG-CMA04-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-03-19 | 2025-03-22 | 2025-03-26 | 2025-03-29 | 82
C-4N-H5HG-CMA04-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-20 | 2025-03-23 | 2025-03-28 | 2025-04-03 | 82
C-4N-H5HG-CMA04-1060 | Holiday Testing | 1 | 1 | 2025-03-23 | 2025-03-25 | 2025-04-03 | 2025-04-04 | 82
C-4N-H5HG-CMA04-1070 | Padding | 1 | 1 | 2025-03-25 | 2025-03-26 | 2025-04-04 | 2025-04-05 | 82
Crossing Manual @ KP 3+526 (PX-19) |  | 12 | 12 | 2025-03-17 | 2025-04-07 | 2025-03-25 | 2025-04-12 | 76
C-4N-H5HG-CMA05-1000 | Trench Excavation | 6 | 6 | 2025-03-17 | 2025-03-26 | 2025-03-25 | 2025-04-05 | 40
C-4N-H5HG-CMA05-1010 | Bedding | 1 | 1 | 2025-03-25 | 2025-03-26 | 2025-04-04 | 2025-04-05 | 70
C-4N-H5HG-CMA05-1020 | Lowering | 1 | 1 | 2025-03-26 | 2025-03-28 | 2025-04-05 | 2025-04-07 | 70
C-4N-H5HG-CMA05-1030 | Section Tie-in Welding | 2 | 2 | 2025-03-26 | 2025-03-29 | 2025-04-05 | 2025-04-08 | 76
C-4N-H5HG-CMA05-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-03-28 | 2025-04-03 | 2025-04-07 | 2025-04-09 | 76
C-4N-H5HG-CMA05-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-29 | 2025-04-04 | 2025-04-08 | 2025-04-10 | 76
C-4N-H5HG-CMA05-1060 | Holiday Testing | 1 | 1 | 2025-04-04 | 2025-04-05 | 2025-04-10 | 2025-04-11 | 76
C-4N-H5HG-CMA05-1070 | Padding | 1 | 1 | 2025-04-05 | 2025-04-07 | 2025-04-11 | 2025-04-12 | 76
Crossing Manual @ KP 5+768 (PX-30) |  | 12 | 12 | 2025-03-26 | 2025-04-14 | 2025-04-05 | 2025-04-19 | 70
C-4N-H5HG-CMA06-1000 | Trench Excavation | 6 | 6 | 2025-03-26 | 2025-04-07 | 2025-04-05 | 2025-04-12 | 40
C-4N-H5HG-CMA06-1010 | Bedding | 1 | 1 | 2025-04-05 | 2025-04-07 | 2025-04-11 | 2025-04-12 | 65
C-4N-H5HG-CMA06-1020 | Lowering | 1 | 1 | 2025-04-07 | 2025-04-08 | 2025-04-12 | 2025-04-14 | 65
C-4N-H5HG-CMA06-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-07 | 2025-04-09 | 2025-04-12 | 2025-04-15 | 70
C-4N-H5HG-CMA06-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-08 | 2025-04-10 | 2025-04-14 | 2025-04-16 | 70
C-4N-H5HG-CMA06-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-09 | 2025-04-11 | 2025-04-15 | 2025-04-17 | 70
C-4N-H5HG-CMA06-1060 | Holiday Testing | 1 | 1 | 2025-04-11 | 2025-04-12 | 2025-04-17 | 2025-04-18 | 70
C-4N-H5HG-CMA06-1070 | Padding | 1 | 1 | 2025-04-12 | 2025-04-14 | 2025-04-18 | 2025-04-19 | 70
Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) |  | 12 | 12 | 2025-04-07 | 2025-04-21 | 2025-04-12 | 2025-04-26 | 64
C-4N-H5HG-CMA07-1000 | Trench Excavation | 6 | 6 | 2025-04-07 | 2025-04-14 | 2025-04-12 | 2025-04-19 | 40
C-4N-H5HG-CMA07-1010 | Bedding | 1 | 1 | 2025-04-12 | 2025-04-14 | 2025-04-18 | 2025-04-19 | 60
C-4N-H5HG-CMA07-1020 | Lowering | 1 | 1 | 2025-04-14 | 2025-04-15 | 2025-04-19 | 2025-04-21 | 60
C-4N-H5HG-CMA07-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-14 | 2025-04-16 | 2025-04-19 | 2025-04-22 | 64
C-4N-H5HG-CMA07-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-15 | 2025-04-17 | 2025-04-21 | 2025-04-23 | 64
C-4N-H5HG-CMA07-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-16 | 2025-04-18 | 2025-04-22 | 2025-04-24 | 64
C-4N-H5HG-CMA07-1060 | Holiday Testing | 1 | 1 | 2025-04-18 | 2025-04-19 | 2025-04-24 | 2025-04-25 | 64
C-4N-H5HG-CMA07-1070 | Padding | 1 | 1 | 2025-04-19 | 2025-04-21 | 2025-04-25 | 2025-04-26 | 64
Crossing Manual @ KP 7+704 (PX-33) |  | 12 | 12 | 2025-04-14 | 2025-04-28 | 2025-04-19 | 2025-05-03 | 58
C-4N-H5HG-CMA08-1000 | Trench Excavation | 6 | 6 | 2025-04-14 | 2025-04-21 | 2025-04-19 | 2025-04-26 | 40
C-4N-H5HG-CMA08-1010 | Bedding | 1 | 1 | 2025-04-19 | 2025-04-21 | 2025-04-25 | 2025-04-26 | 55
C-4N-H5HG-CMA08-1020 | Lowering | 1 | 1 | 2025-04-21 | 2025-04-22 | 2025-04-26 | 2025-04-28 | 55
C-4N-H5HG-CMA08-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-21 | 2025-04-23 | 2025-04-26 | 2025-04-29 | 58
C-4N-H5HG-CMA08-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-22 | 2025-04-24 | 2025-04-28 | 2025-04-30 | 58
C-4N-H5HG-CMA08-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-23 | 2025-04-25 | 2025-04-29 | 2025-05-01 | 58
C-4N-H5HG-CMA08-1060 | Holiday Testing | 1 | 1 | 2025-04-25 | 2025-04-26 | 2025-05-01 | 2025-05-02 | 58
C-4N-H5HG-CMA08-1070 | Padding | 1 | 1 | 2025-04-26 | 2025-04-28 | 2025-05-02 | 2025-05-03 | 58
Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) |  | 12 | 12 | 2025-04-21 | 2025-05-05 | 2025-04-26 | 2025-05-12 | 52
C-4N-H5HG-CMA09-1000 | Trench Excavation | 6 | 6 | 2025-04-21 | 2025-04-28 | 2025-04-26 | 2025-05-03 | 40
C-4N-H5HG-CMA09-1010 | Bedding | 1 | 1 | 2025-04-26 | 2025-04-28 | 2025-05-02 | 2025-05-03 | 50
C-4N-H5HG-CMA09-1020 | Lowering | 1 | 1 | 2025-04-28 | 2025-04-29 | 2025-05-03 | 2025-05-05 | 50
C-4N-H5HG-CMA09-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-28 | 2025-04-30 | 2025-05-03 | 2025-05-06 | 52
C-4N-H5HG-CMA09-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-29 | 2025-05-01 | 2025-05-05 | 2025-05-08 | 52
C-4N-H5HG-CMA09-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-30 | 2025-05-02 | 2025-05-07 | 2025-05-09 | 52
C-4N-H5HG-CMA09-1060 | Holiday Testing | 1 | 1 | 2025-05-02 | 2025-05-03 | 2025-05-09 | 2025-05-10 | 52
C-4N-H5HG-CMA09-1070 | Padding | 1 | 1 | 2025-05-03 | 2025-05-05 | 2025-05-10 | 2025-05-12 | 52
Crossing Manual @ KP 9+389 (PX-47) |  | 12 | 12 | 2025-04-28 | 2025-05-13 | 2025-05-03 | 2025-05-19 | 46
C-4N-H5HG-CMA10-1000 | Trench Excavation | 6 | 6 | 2025-04-28 | 2025-05-05 | 2025-05-03 | 2025-05-12 | 40
C-4N-H5HG-CMA10-1010 | Bedding | 1 | 1 | 2025-05-03 | 2025-05-05 | 2025-05-10 | 2025-05-12 | 45
C-4N-H5HG-CMA10-1020 | Lowering | 1 | 1 | 2025-05-05 | 2025-05-07 | 2025-05-12 | 2025-05-13 | 45
C-4N-H5HG-CMA10-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-05 | 2025-05-08 | 2025-05-12 | 2025-05-14 | 46
C-4N-H5HG-CMA10-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-07 | 2025-05-09 | 2025-05-13 | 2025-05-15 | 46
C-4N-H5HG-CMA10-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-08 | 2025-05-10 | 2025-05-14 | 2025-05-16 | 46
C-4N-H5HG-CMA10-1060 | Holiday Testing | 1 | 1 | 2025-05-10 | 2025-05-12 | 2025-05-16 | 2025-05-17 | 46
C-4N-H5HG-CMA10-1070 | Padding | 1 | 1 | 2025-05-12 | 2025-05-13 | 2025-05-17 | 2025-05-19 | 46
Crossing Manual @ KP 9+447 (PX-48) |  | 12 | 12 | 2025-05-05 | 2025-05-20 | 2025-05-12 | 2025-05-26 | 40
C-4N-H5HG-CMA11-1000 | Trench Excavation | 6 | 6 | 2025-05-05 | 2025-05-13 | 2025-05-12 | 2025-05-19 | 40
C-4N-H5HG-CMA11-1010 | Bedding | 1 | 1 | 2025-05-12 | 2025-05-13 | 2025-05-17 | 2025-05-19 | 40
C-4N-H5HG-CMA11-1020 | Lowering | 1 | 1 | 2025-05-13 | 2025-05-14 | 2025-05-19 | 2025-05-20 | 40
C-4N-H5HG-CMA11-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-13 | 2025-05-15 | 2025-05-19 | 2025-05-21 | 40
C-4N-H5HG-CMA11-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-14 | 2025-05-16 | 2025-05-20 | 2025-05-22 | 40
C-4N-H5HG-CMA11-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-15 | 2025-05-17 | 2025-05-21 | 2025-05-23 | 40
C-4N-H5HG-CMA11-1060 | Holiday Testing | 1 | 1 | 2025-05-17 | 2025-05-19 | 2025-05-23 | 2025-05-24 | 40
C-4N-H5HG-CMA11-1070 | Padding | 1 | 1 | 2025-05-19 | 2025-05-20 | 2025-05-24 | 2025-05-26 | 40
Crossing Manual @ KP 10+022 (PX-49) |  | 12 | 12 | 2025-02-14 | 2025-02-28 | 2025-02-20 | 2025-03-06 | 100
C-4N-H5HG-CMA12-1000 | Trench Excavation | 6 | 6 | 2025-02-14 | 2025-02-21 | 2025-02-20 | 2025-02-26 | 40
C-4N-H5HG-CMA12-1010 | Bedding | 1 | 1 | 2025-02-20 | 2025-02-21 | 2025-02-26 | 2025-02-26 | 90
C-4N-H5HG-CMA12-1020 | Lowering | 1 | 1 | 2025-02-21 | 2025-02-22 | 2025-02-27 | 2025-02-27 | 90
C-4N-H5HG-CMA12-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-21 | 2025-02-24 | 2025-02-27 | 2025-02-28 | 100
C-4N-H5HG-CMA12-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-22 | 2025-02-25 | 2025-02-28 | 2025-03-01 | 100
C-4N-H5HG-CMA12-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-24 | 2025-02-26 | 2025-03-01 | 2025-03-03 | 100
C-4N-H5HG-CMA12-1060 | Holiday Testing | 1 | 1 | 2025-02-26 | 2025-02-27 | 2025-03-03 | 2025-03-05 | 100
C-4N-H5HG-CMA12-1070 | Padding | 1 | 1 | 2025-02-27 | 2025-02-28 | 2025-03-05 | 2025-03-06 | 100
Crossings - UG CableCCOPL4"118 |  | 12 | 12 | 2025-02-07 | 2025-02-21 | 2025-02-13 | 2025-02-26 | 106
Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) |  | 12 | 12 | 2025-02-07 | 2025-02-21 | 2025-02-13 | 2025-02-26 | 106
C-4N-H5HG-CMA13-1000 | Trench Excavation | 6 | 6 | 2025-02-07 | 2025-02-14 | 2025-02-13 | 2025-02-19 | 38
C-4N-H5HG-CMA13-1010 | Bedding | 1 | 1 | 2025-02-13 | 2025-02-14 | 2025-02-19 | 2025-02-19 | 93
C-4N-H5HG-CMA13-1020 | Lowering | 1 | 1 | 2025-02-14 | 2025-02-15 | 2025-02-20 | 2025-02-20 | 93
C-4N-H5HG-CMA13-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-14 | 2025-02-17 | 2025-02-20 | 2025-02-21 | 106
C-4N-H5HG-CMA13-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-02-15 | 2025-02-18 | 2025-02-21 | 2025-02-22 | 106
C-4N-H5HG-CMA13-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-02-17 | 2025-02-19 | 2025-02-22 | 2025-02-24 | 106
C-4N-H5HG-CMA13-1060 | Holiday Testing | 1 | 1 | 2025-02-19 | 2025-02-20 | 2025-02-25 | 2025-02-25 | 106
C-4N-H5HG-CMA13-1070 | Padding | 1 | 1 | 2025-02-20 | 2025-02-21 | 2025-02-26 | 2025-02-26 | 106
Open Cut - Rig / Track RoadCCOPL4"110 |  | 12 | 12 | 2025-04-07 | 2025-04-21 | 2025-04-12 | 2025-04-26 | 64
Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) |  | 12 | 12 | 2025-04-07 | 2025-04-21 | 2025-04-12 | 2025-04-26 | 64
C-4N-H5HG-CMA29-1000 | Trench Excavation | 6 | 6 | 2025-04-07 | 2025-04-14 | 2025-04-12 | 2025-04-19 | 64
C-4N-H5HG-CMA29-1010 | Bedding | 1 | 1 | 2025-04-12 | 2025-04-14 | 2025-04-18 | 2025-04-19 | 64
C-4N-H5HG-CMA29-1020 | Lowering | 1 | 1 | 2025-04-14 | 2025-04-15 | 2025-04-19 | 2025-04-21 | 64
C-4N-H5HG-CMA29-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-14 | 2025-04-16 | 2025-04-19 | 2025-04-22 | 64
C-4N-H5HG-CMA29-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-15 | 2025-04-17 | 2025-04-21 | 2025-04-23 | 64
C-4N-H5HG-CMA29-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-16 | 2025-04-18 | 2025-04-22 | 2025-04-24 | 64
C-4N-H5HG-CMA29-1060 | Holiday Testing | 1 | 1 | 2025-04-18 | 2025-04-19 | 2025-04-24 | 2025-04-25 | 64
C-4N-H5HG-CMA29-1070 | Padding | 1 | 1 | 2025-04-19 | 2025-04-21 | 2025-04-25 | 2025-04-26 | 64
Crossings - AG PipeCCOPL4"120 |  | 66 | 66 | 2025-02-21 | 2025-05-20 | 2025-02-27 | 2025-05-26 | 40
Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) |  | 12 | 12 | 2025-02-21 | 2025-03-08 | 2025-02-27 | 2025-03-15 | 94
C-4N-H5HG-CMA14-1000 | Trench Excavation | 6 | 6 | 2025-02-21 | 2025-02-28 | 2025-02-27 | 2025-03-06 | 40
C-4N-H5HG-CMA14-1010 | Bedding | 1 | 1 | 2025-02-27 | 2025-02-28 | 2025-03-05 | 2025-03-06 | 85
C-4N-H5HG-CMA14-1020 | Lowering | 1 | 1 | 2025-02-28 | 2025-03-01 | 2025-03-07 | 2025-03-08 | 85
C-4N-H5HG-CMA14-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-28 | 2025-03-02 | 2025-03-07 | 2025-03-09 | 94
C-4N-H5HG-CMA14-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-03-01 | 2025-03-03 | 2025-03-08 | 2025-03-11 | 94
C-4N-H5HG-CMA14-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-02 | 2025-03-05 | 2025-03-09 | 2025-03-12 | 94
C-4N-H5HG-CMA14-1060 | Holiday Testing | 1 | 1 | 2025-03-05 | 2025-03-07 | 2025-03-13 | 2025-03-14 | 94
C-4N-H5HG-CMA14-1070 | Padding | 1 | 1 | 2025-03-07 | 2025-03-08 | 2025-03-14 | 2025-03-15 | 94
Crossing Manual @ KP 10+523 (PX-53) |  | 12 | 12 | 2025-02-28 | 2025-03-17 | 2025-03-07 | 2025-03-24 | 88
C-4N-H5HG-CMA15-1000 | Trench Excavation | 6 | 6 | 2025-02-28 | 2025-03-08 | 2025-03-07 | 2025-03-15 | 40
C-4N-H5HG-CMA15-1010 | Bedding | 1 | 1 | 2025-03-07 | 2025-03-08 | 2025-03-14 | 2025-03-15 | 80
C-4N-H5HG-CMA15-1020 | Lowering | 1 | 1 | 2025-03-08 | 2025-03-09 | 2025-03-15 | 2025-03-17 | 80
C-4N-H5HG-CMA15-1030 | Section Tie-in Welding | 2 | 2 | 2025-03-08 | 2025-03-11 | 2025-03-15 | 2025-03-18 | 88
C-4N-H5HG-CMA15-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-03-09 | 2025-03-13 | 2025-03-17 | 2025-03-20 | 88
C-4N-H5HG-CMA15-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-11 | 2025-03-14 | 2025-03-19 | 2025-03-22 | 88
C-4N-H5HG-CMA15-1060 | Holiday Testing | 1 | 1 | 2025-03-14 | 2025-03-15 | 2025-03-22 | 2025-03-23 | 88
C-4N-H5HG-CMA15-1070 | Padding | 1 | 1 | 2025-03-15 | 2025-03-17 | 2025-03-23 | 2025-03-24 | 88
Crossing Manual @ KP 10+703 (PX-67) |  | 12 | 12 | 2025-03-08 | 2025-03-26 | 2025-03-15 | 2025-04-05 | 82
C-4N-H5HG-CMA16-1000 | Trench Excavation | 6 | 6 | 2025-03-08 | 2025-03-17 | 2025-03-15 | 2025-03-24 | 40
C-4N-H5HG-CMA16-1010 | Bedding | 1 | 1 | 2025-03-15 | 2025-03-17 | 2025-03-23 | 2025-03-24 | 75
C-4N-H5HG-CMA16-1020 | Lowering | 1 | 1 | 2025-03-17 | 2025-03-19 | 2025-03-25 | 2025-03-26 | 75
C-4N-H5HG-CMA16-1030 | Section Tie-in Welding | 2 | 2 | 2025-03-17 | 2025-03-20 | 2025-03-25 | 2025-03-28 | 82
C-4N-H5HG-CMA16-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-03-19 | 2025-03-22 | 2025-03-26 | 2025-03-29 | 82
C-4N-H5HG-CMA16-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-20 | 2025-03-23 | 2025-03-28 | 2025-04-03 | 82
C-4N-H5HG-CMA16-1060 | Holiday Testing | 1 | 1 | 2025-03-23 | 2025-03-25 | 2025-04-03 | 2025-04-04 | 82
C-4N-H5HG-CMA16-1070 | Padding | 1 | 1 | 2025-03-25 | 2025-03-26 | 2025-04-04 | 2025-04-05 | 82
Crossing Manual @ KP 10+788 (PX-68) |  | 12 | 12 | 2025-03-17 | 2025-04-07 | 2025-03-25 | 2025-04-12 | 76
C-4N-H5HG-CMA17-1000 | Trench Excavation | 6 | 6 | 2025-03-17 | 2025-03-26 | 2025-03-25 | 2025-04-05 | 40
C-4N-H5HG-CMA17-1010 | Bedding | 1 | 1 | 2025-03-25 | 2025-03-26 | 2025-04-04 | 2025-04-05 | 70
C-4N-H5HG-CMA17-1020 | Lowering | 1 | 1 | 2025-03-26 | 2025-03-28 | 2025-04-05 | 2025-04-07 | 70
C-4N-H5HG-CMA17-1030 | Section Tie-in Welding | 2 | 2 | 2025-03-26 | 2025-03-29 | 2025-04-05 | 2025-04-08 | 76
C-4N-H5HG-CMA17-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-03-28 | 2025-04-03 | 2025-04-07 | 2025-04-09 | 76
C-4N-H5HG-CMA17-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-29 | 2025-04-04 | 2025-04-08 | 2025-04-10 | 76
C-4N-H5HG-CMA17-1060 | Holiday Testing | 1 | 1 | 2025-04-04 | 2025-04-05 | 2025-04-10 | 2025-04-11 | 76
C-4N-H5HG-CMA17-1070 | Padding | 1 | 1 | 2025-04-05 | 2025-04-07 | 2025-04-11 | 2025-04-12 | 76
Crossing Manual @ KP 10+882 (PX-69) |  | 12 | 12 | 2025-03-26 | 2025-04-14 | 2025-04-05 | 2025-04-19 | 70
C-4N-H5HG-CMA18-1000 | Trench Excavation | 6 | 6 | 2025-03-26 | 2025-04-07 | 2025-04-05 | 2025-04-12 | 40
C-4N-H5HG-CMA18-1010 | Bedding | 1 | 1 | 2025-04-05 | 2025-04-07 | 2025-04-11 | 2025-04-12 | 65
C-4N-H5HG-CMA18-1020 | Lowering | 1 | 1 | 2025-04-07 | 2025-04-08 | 2025-04-12 | 2025-04-14 | 65
C-4N-H5HG-CMA18-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-07 | 2025-04-09 | 2025-04-12 | 2025-04-15 | 70
C-4N-H5HG-CMA18-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-08 | 2025-04-10 | 2025-04-14 | 2025-04-16 | 70
C-4N-H5HG-CMA18-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-09 | 2025-04-11 | 2025-04-15 | 2025-04-17 | 70
C-4N-H5HG-CMA18-1060 | Holiday Testing | 1 | 1 | 2025-04-11 | 2025-04-12 | 2025-04-17 | 2025-04-18 | 70
C-4N-H5HG-CMA18-1070 | Padding | 1 | 1 | 2025-04-12 | 2025-04-14 | 2025-04-18 | 2025-04-19 | 70
Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) |  | 12 | 12 | 2025-04-14 | 2025-04-28 | 2025-04-19 | 2025-05-03 | 58
C-4N-H5HG-CMA19-1000 | Trench Excavation | 6 | 6 | 2025-04-14 | 2025-04-21 | 2025-04-19 | 2025-04-26 | 40
C-4N-H5HG-CMA19-1010 | Bedding | 1 | 1 | 2025-04-19 | 2025-04-21 | 2025-04-25 | 2025-04-26 | 55
C-4N-H5HG-CMA19-1020 | Lowering | 1 | 1 | 2025-04-21 | 2025-04-22 | 2025-04-26 | 2025-04-28 | 55
C-4N-H5HG-CMA19-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-21 | 2025-04-23 | 2025-04-26 | 2025-04-29 | 58
C-4N-H5HG-CMA19-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-22 | 2025-04-24 | 2025-04-28 | 2025-04-30 | 58
C-4N-H5HG-CMA19-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-23 | 2025-04-25 | 2025-04-29 | 2025-05-01 | 58
C-4N-H5HG-CMA19-1060 | Holiday Testing | 1 | 1 | 2025-04-25 | 2025-04-26 | 2025-05-01 | 2025-05-02 | 58
C-4N-H5HG-CMA19-1070 | Padding | 1 | 1 | 2025-04-26 | 2025-04-28 | 2025-05-02 | 2025-05-03 | 58
Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) |  | 12 | 12 | 2025-04-21 | 2025-05-05 | 2025-04-26 | 2025-05-12 | 52
C-4N-H5HG-CMA20-1000 | Trench Excavation | 6 | 6 | 2025-04-21 | 2025-04-28 | 2025-04-26 | 2025-05-03 | 40
C-4N-H5HG-CMA20-1010 | Bedding | 1 | 1 | 2025-04-26 | 2025-04-28 | 2025-05-02 | 2025-05-03 | 50
C-4N-H5HG-CMA20-1020 | Lowering | 1 | 1 | 2025-04-28 | 2025-04-29 | 2025-05-03 | 2025-05-05 | 50
C-4N-H5HG-CMA20-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-28 | 2025-04-30 | 2025-05-03 | 2025-05-06 | 52
C-4N-H5HG-CMA20-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-29 | 2025-05-01 | 2025-05-05 | 2025-05-08 | 52
C-4N-H5HG-CMA20-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-30 | 2025-05-02 | 2025-05-07 | 2025-05-09 | 52
C-4N-H5HG-CMA20-1060 | Holiday Testing | 1 | 1 | 2025-05-02 | 2025-05-03 | 2025-05-09 | 2025-05-10 | 52
C-4N-H5HG-CMA20-1070 | Padding | 1 | 1 | 2025-05-03 | 2025-05-05 | 2025-05-10 | 2025-05-12 | 52
Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) |  | 12 | 12 | 2025-04-28 | 2025-05-13 | 2025-05-03 | 2025-05-19 | 46
C-4N-H5HG-CMA21-1000 | Trench Excavation | 6 | 6 | 2025-04-28 | 2025-05-05 | 2025-05-03 | 2025-05-12 | 40
C-4N-H5HG-CMA21-1010 | Bedding | 1 | 1 | 2025-05-03 | 2025-05-05 | 2025-05-10 | 2025-05-12 | 45
C-4N-H5HG-CMA21-1020 | Lowering | 1 | 1 | 2025-05-05 | 2025-05-07 | 2025-05-12 | 2025-05-13 | 45
C-4N-H5HG-CMA21-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-05 | 2025-05-08 | 2025-05-12 | 2025-05-14 | 46
C-4N-H5HG-CMA21-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-07 | 2025-05-09 | 2025-05-13 | 2025-05-15 | 46
C-4N-H5HG-CMA21-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-08 | 2025-05-10 | 2025-05-14 | 2025-05-16 | 46
C-4N-H5HG-CMA21-1060 | Holiday Testing | 1 | 1 | 2025-05-10 | 2025-05-12 | 2025-05-16 | 2025-05-17 | 46
C-4N-H5HG-CMA21-1070 | Padding | 1 | 1 | 2025-05-12 | 2025-05-13 | 2025-05-17 | 2025-05-19 | 46
Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) |  | 12 | 12 | 2025-05-05 | 2025-05-20 | 2025-05-12 | 2025-05-26 | 40
C-4N-H5HG-CMA22-1000 | Trench Excavation | 6 | 6 | 2025-05-05 | 2025-05-13 | 2025-05-12 | 2025-05-19 | 40
C-4N-H5HG-CMA22-1010 | Bedding | 1 | 1 | 2025-05-12 | 2025-05-13 | 2025-05-17 | 2025-05-19 | 40
C-4N-H5HG-CMA22-1020 | Lowering | 1 | 1 | 2025-05-13 | 2025-05-14 | 2025-05-19 | 2025-05-20 | 40
C-4N-H5HG-CMA22-1030 | Section Tie-in Welding | 2 | 2 | 2025-05-13 | 2025-05-15 | 2025-05-19 | 2025-05-21 | 40
C-4N-H5HG-CMA22-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-05-14 | 2025-05-16 | 2025-05-20 | 2025-05-22 | 40
C-4N-H5HG-CMA22-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-05-15 | 2025-05-17 | 2025-05-21 | 2025-05-23 | 40
C-4N-H5HG-CMA22-1060 | Holiday Testing | 1 | 1 | 2025-05-17 | 2025-05-19 | 2025-05-23 | 2025-05-24 | 40
C-4N-H5HG-CMA22-1070 | Padding | 1 | 1 | 2025-05-19 | 2025-05-20 | 2025-05-24 | 2025-05-26 | 40
Crossings - FenceCCOPL4"121 |  | 36 | 36 | 2025-02-21 | 2025-04-14 | 2025-02-27 | 2025-04-19 | 70
Crossing Manual @ KP 15+082 (PX-105) |  | 12 | 12 | 2025-02-21 | 2025-03-08 | 2025-02-27 | 2025-03-15 | 94
C-4N-H5HG-CMA23-1000 | Trench Excavation | 6 | 6 | 2025-02-21 | 2025-02-28 | 2025-02-27 | 2025-03-06 | 64
C-4N-H5HG-CMA23-1010 | Bedding | 1 | 1 | 2025-02-27 | 2025-02-28 | 2025-03-05 | 2025-03-06 | 89
C-4N-H5HG-CMA23-1020 | Lowering | 1 | 1 | 2025-02-28 | 2025-03-01 | 2025-03-07 | 2025-03-08 | 89
C-4N-H5HG-CMA23-1030 | Section Tie-in Welding | 2 | 2 | 2025-02-28 | 2025-03-02 | 2025-03-07 | 2025-03-09 | 94
C-4N-H5HG-CMA23-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-03-01 | 2025-03-03 | 2025-03-08 | 2025-03-11 | 94
C-4N-H5HG-CMA23-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-02 | 2025-03-05 | 2025-03-09 | 2025-03-12 | 94
C-4N-H5HG-CMA23-1060 | Holiday Testing | 1 | 1 | 2025-03-05 | 2025-03-07 | 2025-03-13 | 2025-03-14 | 94
C-4N-H5HG-CMA23-1070 | Padding | 1 | 1 | 2025-03-07 | 2025-03-08 | 2025-03-14 | 2025-03-15 | 94
Crossing Manual @ KP 15+542 (PX-106) |  | 12 | 12 | 2025-03-08 | 2025-03-26 | 2025-03-15 | 2025-04-05 | 82
C-4N-H5HG-CMA24-1000 | Trench Excavation | 6 | 6 | 2025-03-08 | 2025-03-17 | 2025-03-15 | 2025-03-24 | 64
C-4N-H5HG-CMA24-1010 | Bedding | 1 | 1 | 2025-03-15 | 2025-03-17 | 2025-03-23 | 2025-03-24 | 79
C-4N-H5HG-CMA24-1020 | Lowering | 1 | 1 | 2025-03-17 | 2025-03-19 | 2025-03-25 | 2025-03-26 | 79
C-4N-H5HG-CMA24-1030 | Section Tie-in Welding | 2 | 2 | 2025-03-17 | 2025-03-20 | 2025-03-25 | 2025-03-28 | 82
C-4N-H5HG-CMA24-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-03-19 | 2025-03-22 | 2025-03-26 | 2025-03-29 | 82
C-4N-H5HG-CMA24-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-20 | 2025-03-23 | 2025-03-28 | 2025-04-03 | 82
C-4N-H5HG-CMA24-1060 | Holiday Testing | 1 | 1 | 2025-03-23 | 2025-03-25 | 2025-04-03 | 2025-04-04 | 82
C-4N-H5HG-CMA24-1070 | Padding | 1 | 1 | 2025-03-25 | 2025-03-26 | 2025-04-04 | 2025-04-05 | 82
Crossing Manual @ KP 16+486 (PX-107) |  | 12 | 12 | 2025-03-17 | 2025-04-07 | 2025-03-25 | 2025-04-12 | 76
C-4N-H5HG-CMA25-1000 | Trench Excavation | 6 | 6 | 2025-03-17 | 2025-03-26 | 2025-03-25 | 2025-04-05 | 64
C-4N-H5HG-CMA25-1010 | Bedding | 1 | 1 | 2025-03-25 | 2025-03-26 | 2025-04-04 | 2025-04-05 | 74
C-4N-H5HG-CMA25-1020 | Lowering | 1 | 1 | 2025-03-26 | 2025-03-28 | 2025-04-05 | 2025-04-07 | 74
C-4N-H5HG-CMA25-1030 | Section Tie-in Welding | 2 | 2 | 2025-03-26 | 2025-03-29 | 2025-04-05 | 2025-04-08 | 76
C-4N-H5HG-CMA25-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-03-28 | 2025-04-03 | 2025-04-07 | 2025-04-09 | 76
C-4N-H5HG-CMA25-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-29 | 2025-04-04 | 2025-04-08 | 2025-04-10 | 76
C-4N-H5HG-CMA25-1060 | Holiday Testing | 1 | 1 | 2025-04-04 | 2025-04-05 | 2025-04-10 | 2025-04-11 | 76
C-4N-H5HG-CMA25-1070 | Padding | 1 | 1 | 2025-04-05 | 2025-04-07 | 2025-04-11 | 2025-04-12 | 76
Crossing Manual @ KP 16+594 to 16+609(PX-108,109) |  | 12 | 12 | 2025-03-26 | 2025-04-14 | 2025-04-05 | 2025-04-19 | 70
C-4N-H5HG-CMA26-1000 | Trench Excavation | 6 | 6 | 2025-03-26 | 2025-04-07 | 2025-04-05 | 2025-04-12 | 64
C-4N-H5HG-CMA26-1010 | Bedding | 1 | 1 | 2025-04-05 | 2025-04-07 | 2025-04-11 | 2025-04-12 | 69
C-4N-H5HG-CMA26-1020 | Lowering | 1 | 1 | 2025-04-07 | 2025-04-08 | 2025-04-12 | 2025-04-14 | 69
C-4N-H5HG-CMA26-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-07 | 2025-04-09 | 2025-04-12 | 2025-04-15 | 70
C-4N-H5HG-CMA26-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-08 | 2025-04-10 | 2025-04-14 | 2025-04-16 | 70
C-4N-H5HG-CMA26-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-09 | 2025-04-11 | 2025-04-15 | 2025-04-17 | 70
C-4N-H5HG-CMA26-1060 | Holiday Testing | 1 | 1 | 2025-04-11 | 2025-04-12 | 2025-04-17 | 2025-04-18 | 70
C-4N-H5HG-CMA26-1070 | Padding | 1 | 1 | 2025-04-12 | 2025-04-14 | 2025-04-18 | 2025-04-19 | 70
Crossings OHPLCCOPL4"122 |  | 36 | 36 | 2025-02-28 | 2025-04-21 | 2025-03-07 | 2025-04-26 | 64
Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) |  | 12 | 12 | 2025-04-07 | 2025-04-21 | 2025-04-12 | 2025-04-26 | 64
C-4N-H5HG-CMA27-1000 | Trench Excavation | 6 | 6 | 2025-04-07 | 2025-04-14 | 2025-04-12 | 2025-04-19 | 40
C-4N-H5HG-CMA27-1010 | Bedding | 1 | 1 | 2025-04-12 | 2025-04-14 | 2025-04-18 | 2025-04-19 | 60
C-4N-H5HG-CMA27-1020 | Lowering | 1 | 1 | 2025-04-14 | 2025-04-15 | 2025-04-19 | 2025-04-21 | 60
C-4N-H5HG-CMA27-1030 | Section Tie-in Welding | 2 | 2 | 2025-04-14 | 2025-04-16 | 2025-04-19 | 2025-04-22 | 64
C-4N-H5HG-CMA27-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-04-15 | 2025-04-17 | 2025-04-21 | 2025-04-23 | 64
C-4N-H5HG-CMA27-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-04-16 | 2025-04-18 | 2025-04-22 | 2025-04-24 | 64
C-4N-H5HG-CMA27-1060 | Holiday Testing | 1 | 1 | 2025-04-18 | 2025-04-19 | 2025-04-24 | 2025-04-25 | 64
C-4N-H5HG-CMA27-1070 | Padding | 1 | 1 | 2025-04-19 | 2025-04-21 | 2025-04-25 | 2025-04-26 | 64
Crossing Manual @ KP 15+276 (OX-03) |  | 12 | 12 | 2025-02-28 | 2025-03-17 | 2025-03-07 | 2025-03-24 | 88
C-4N-H5HG-CMA28-1000 | Trench Excavation | 6 | 6 | 2025-02-28 | 2025-03-08 | 2025-03-07 | 2025-03-15 | 64
C-4N-H5HG-CMA28-1010 | Bedding | 1 | 1 | 2025-03-07 | 2025-03-08 | 2025-03-14 | 2025-03-15 | 84
C-4N-H5HG-CMA28-1020 | Lowering | 1 | 1 | 2025-03-08 | 2025-03-09 | 2025-03-15 | 2025-03-17 | 84
C-4N-H5HG-CMA28-1030 | Section Tie-in Welding | 2 | 2 | 2025-03-08 | 2025-03-11 | 2025-03-15 | 2025-03-18 | 88
C-4N-H5HG-CMA28-1040 | NDT (Tie-in Joint) | 2 | 2 | 2025-03-09 | 2025-03-13 | 2025-03-17 | 2025-03-20 | 88
C-4N-H5HG-CMA28-1050 | Ext. Joint Coating (Tie-in Joint) | 2 | 2 | 2025-03-11 | 2025-03-14 | 2025-03-19 | 2025-03-22 | 88
C-4N-H5HG-CMA28-1060 | Holiday Testing | 1 | 1 | 2025-03-14 | 2025-03-15 | 2025-03-22 | 2025-03-23 | 88
C-4N-H5HG-CMA28-1070 | Padding | 1 | 1 | 2025-03-15 | 2025-03-17 | 2025-03-23 | 2025-03-24 | 88
CP Works(Temporary)CCOP4"EL11.1 |  | 54 | 54 | 2025-02-28 | 2025-05-13 | 2025-05-14 | 2025-07-19 | 63
C-4N-H5HG-PIPEL-5200 | Installation of CP Test Post | 53 | 53 | 2025-02-28 | 2025-05-12 | 2025-05-14 | 2025-07-18 | 63
C-4N-H5HG-PIPEL-5210 | Glanding & Termination of Temp. CP S/m | 1 | 1 | 2025-05-12 | 2025-05-13 | 2025-07-18 | 2025-07-19 | 63
CP Works (Permanent)CCOP4"EL11.2 |  | 103 | 103 | 2025-03-11 | 2025-06-03 | 2025-03-19 | 2025-07-28 | 63
C-4N-H5HG-PIPEL-5220 | Installation of Test Post for Crossing | 55 | 55 | 2025-03-11 | 2025-05-23 | 2025-03-19 | 2025-05-29 | 102
C-4N-H5HG-PIPEL-5230 | Installation of CP JB's | 55 | 55 | 2025-03-13 | 2025-05-24 | 2025-03-20 | 2025-05-30 | 102
C-4N-H5HG-PIPEL-5240 | Installation of CP TR | 25 | 25 | 2025-04-25 | 2025-05-26 | 2025-05-01 | 2025-05-31 | 102
C-4N-H5HG-PIPEL-5250 | CIP/DCVG Survey | 7 | 7 | 2025-05-26 | 2025-06-03 | 2025-07-19 | 2025-07-28 | 63
Test Stations & Anode BedsCCOP4"EL12 |  | 53 | 53 | 2025-02-28 | 2025-05-12 | 2025-05-14 | 2025-07-18 | 23
C-4N-H5HG-PIPEL-5600 | Installation of Temp. Anode | 53 | 53 | 2025-02-28 | 2025-05-12 | 2025-05-14 | 2025-07-18 | 23
PaddingCCOPL4"112 |  | 324 | 201 | 2024-06-14 | 2025-05-14 | 14-Jun-24 A | 2025-07-21 | 23
C-4N-H5HG-PIPEL-2010 | Sabka Gatch Laying - Layer 2 | 135 | 14 | 2024-06-16 | 2024-12-10 | 16-Jun-24 A | 2024-11-26 | 74
C-4N-H5HG-PIPEL-2020 | Sabka Gatch Laying - Layer 3 | 135 | 14 | 2024-06-18 | 2024-12-10 | 18-Jun-24 A | 2024-11-26 | 74
C-4N-H5HG-PIPEL-2030 | Sabka Gatch Laying - Layer 4 | 135 | 14 | 2024-06-20 | 2024-12-10 | 20-Jun-24 A | 2024-11-26 | 74
C-4N-H5HG-PIPEL-2200 | Sabka Gatch Compaction (Including ROW) - Layer 1 | 136 | 14 | 2024-06-15 | 2024-12-10 | 15-Jun-24 A | 2024-11-26 | 74
C-4N-H5HG-PIPEL-2210 | Sabka Gatch Compaction - Layer 2 | 135 | 14 | 2024-06-17 | 2024-12-10 | 17-Jun-24 A | 2024-11-26 | 74
C-4N-H5HG-PIPEL-2220 | Sabka Gatch Compaction - Layer 3 | 135 | 14 | 2024-06-19 | 2024-12-10 | 19-Jun-24 A | 2024-11-26 | 74
C-4N-H5HG-PIPEL-2230 | Sabka Gatch Compaction - Layer 4 | 134 | 14 | 2024-06-21 | 2024-12-10 | 21-Jun-24 A | 2024-11-26 | 74
C-4N-H5HG-PIPEL-2000 | Sabka Gatch Laying (Including ROW) - Layer 1 | 137 | 14 | 2024-06-14 | 2024-12-10 | 14-Jun-24 A | 2024-11-27 | 74
C-4N-H5HG-PIPEL-6000 | Padding | 52 | 52 | 2025-03-03 | 2025-05-14 | 2025-05-17 | 2025-07-21 | 23
BackfillingCCOPL4"115 |  | 52 | 52 | 2025-03-29 | 2025-06-03 | 2025-05-31 | 2025-08-04 | 23
C-4N-H5HG-PIPEL-6400 | Backfilling | 52 | 52 | 2025-03-29 | 2025-06-03 | 2025-05-31 | 2025-08-04 | 23
BermingCCOPL4"116 |  | 52 | 52 | 2025-05-22 | 2025-07-25 | 2025-06-17 | 2025-08-18 | 23
C-4N-H5HG-PIPEL-6800 | Gatch Laying & Levelling | 50 | 50 | 2025-05-22 | 2025-07-23 | 2025-06-17 | 2025-08-15 | 23
C-4N-H5HG-PIPEL-6810 | Gatch Compaction | 50 | 50 | 2025-05-24 | 2025-07-25 | 2025-06-19 | 2025-08-18 | 23
Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 |  | 12 | 12 | 2025-07-25 | 2025-08-08 | 2025-08-18 | 2025-09-01 | 23
C-4N-H5HG-PIPEL-7400 | Cleaning & Gauging | 3 | 3 | 2025-07-25 | 2025-07-29 | 2025-08-18 | 2025-08-21 | 23
C-4N-H5HG-PIPEL-7410 | Water Filling | 5 | 5 | 2025-07-29 | 2025-08-04 | 2025-08-21 | 2025-08-27 | 23
C-4N-H5HG-PIPEL-7420 | Pressurization | 3 | 3 | 2025-08-04 | 2025-08-07 | 2025-08-27 | 2025-08-30 | 23
C-4N-H5HG-PIPEL-7430 | Holding of Test Pressure | 1 | 1 | 2025-08-07 | 2025-08-08 | 2025-08-30 | 2025-09-01 | 23
Dewatering, Swabbing, & DryingCCOPL4"124 |  | 10 | 10 | 2025-08-08 | 2025-08-20 | 2025-09-01 | 2025-09-13 | 23
C-4N-H5HG-PIPEL-7600 | De-Pressurization | 2 | 2 | 2025-08-08 | 2025-08-11 | 2025-09-01 | 2025-09-03 | 23
C-4N-H5HG-PIPEL-7610 | De-watering | 3 | 3 | 2025-08-11 | 2025-08-14 | 2025-09-03 | 2025-09-08 | 23
C-4N-H5HG-PIPEL-7620 | Swabing & Drying (Upto Dew Point Temp.) | 5 | 5 | 2025-08-14 | 2025-08-20 | 2025-09-08 | 2025-09-13 | 23
ROW Restoration/ Marker Post/ Crash BarrierCCOPL4"126 |  | 35 | 35 | 2025-06-18 | 2025-07-30 | 2025-07-12 | 2025-08-22 | 41
C-4N-H5HG-PIPEL-7800 | ROW Restoration/ Installation of Marker Post/Sign Board | 30 | 30 | 2025-06-18 | 2025-07-24 | 2025-07-12 | 2025-08-16 | 41
C-4N-H5HG-PIPEL-7810 | Installation of Crash Barriers (If any) | 30 | 30 | 2025-06-24 | 2025-07-30 | 2025-07-18 | 2025-08-22 | 41
Telecommunication Works |  | 48 | 48 | 2025-03-26 | 2025-05-27 | 2025-05-29 | 2025-07-28 | 63
Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 |  | 48 | 48 | 2025-03-26 | 2025-05-27 | 2025-05-29 | 2025-07-28 | 63
C-4N-H5HG-PIPEL-8200 | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | 45 | 45 | 2025-03-26 | 2025-05-23 | 2025-05-29 | 2025-07-24 | 63
C-4N-H5HG-PIPEL-8210 | Termination/Splicing @ HGCP | 3 | 3 | 2025-05-23 | 2025-05-27 | 2025-07-24 | 2025-07-28 | 63
Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 |  | 48 | 48 | 2025-03-26 | 2025-05-27 | 2025-05-29 | 2025-07-28 | 63
C-4N-H5HG-PIPEL-8400 | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | 45 | 45 | 2025-03-26 | 2025-05-23 | 2025-05-29 | 2025-07-24 | 23
C-4N-H5HG-PIPEL-8410 | Termination/Splicing @ HGCP | 3 | 3 | 2025-05-23 | 2025-05-27 | 2025-07-24 | 2025-07-28 | 63
NDRC |  | 81 | 81 | 2025-01-29 | 2025-05-22 | 2025-02-12 | 2025-05-28 | 38
NDRC (incl Hydrotest) at KP 0+517.009CCOPL4"902 |  | 18 | 18 | 2025-02-22 | 2025-03-19 | 2025-02-28 | 2025-03-26 | 87
HDD @ CH 0+517 - 0+556 (HDD-01) |  | 18 | 18 | 2025-02-22 | 2025-03-19 | 2025-02-28 | 2025-03-26 | 87
C-4N-H5HG-CNH01-1000 | Excavation for Entry & Exit Pit Preparation | 7 | 7 | 2025-02-22 | 2025-03-02 | 2025-02-28 | 2025-03-09 | 38
C-4N-H5HG-CNH01-1010 | HDD Section Readiness (Including hydrotest) | 7 | 7 | 2025-02-22 | 2025-03-02 | 2025-02-28 | 2025-03-09 | 87
C-4N-H5HG-CNH01-1020 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | 8 | 8 | 2025-03-02 | 2025-03-14 | 2025-03-09 | 2025-03-22 | 87
C-4N-H5HG-CNH01-1030 | Re-Instatement of Entry & Exit Pit | 3 | 3 | 2025-03-14 | 2025-03-19 | 2025-03-22 | 2025-03-26 | 87
NDRC (incl Hydrotest) at KP 1+003.190CCOPL4"904 |  | 18 | 18 | 2025-03-02 | 2025-03-29 | 2025-03-09 | 2025-04-08 | 80
HDD @ CH 1+006 - 1+056 (HDD-02) |  | 18 | 18 | 2025-03-02 | 2025-03-29 | 2025-03-09 | 2025-04-08 | 80
C-4N-H5HG-CNH02-1000 | Excavation for Entry & Exit Pit Preparation | 7 | 7 | 2025-03-02 | 2025-03-13 | 2025-03-09 | 2025-03-20 | 38
C-4N-H5HG-CNH02-1010 | HDD Section Readiness (Including hydrotest) | 7 | 7 | 2025-03-02 | 2025-03-13 | 2025-03-09 | 2025-03-20 | 80
C-4N-H5HG-CNH02-1020 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | 8 | 8 | 2025-03-13 | 2025-03-25 | 2025-03-20 | 2025-04-04 | 80
C-4N-H5HG-CNH02-1030 | Re-Instatement of Entry & Exit Pit | 3 | 3 | 2025-03-25 | 2025-03-29 | 2025-04-04 | 2025-04-08 | 80
NDRC (incl Hydrotest) at KP 2+845.653CCOPL4"914 |  | 18 | 18 | 2025-03-13 | 2025-04-10 | 2025-03-20 | 2025-04-16 | 73
HDD @ CH 2+845 - 3+029 (HDD-03) |  | 18 | 18 | 2025-03-13 | 2025-04-10 | 2025-03-20 | 2025-04-16 | 73
C-4N-H5HG-CNH03-1000 | Excavation for Entry & Exit Pit Preparation | 7 | 7 | 2025-03-13 | 2025-03-23 | 2025-03-20 | 2025-04-03 | 38
C-4N-H5HG-CNH03-1010 | HDD Section Readiness (Including hydrotest) | 7 | 7 | 2025-03-13 | 2025-03-23 | 2025-03-20 | 2025-04-03 | 73
C-4N-H5HG-CNH03-1020 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | 8 | 8 | 2025-03-23 | 2025-04-07 | 2025-04-03 | 2025-04-12 | 73
C-4N-H5HG-CNH03-1030 | Re-Instatement of Entry & Exit Pit | 3 | 3 | 2025-04-07 | 2025-04-10 | 2025-04-12 | 2025-04-16 | 73
NDRC (incl Hydrotest) at KP 4+392.899CCOPL4"916 |  | 18 | 18 | 2025-03-23 | 2025-04-18 | 2025-04-03 | 2025-04-24 | 66
HDD @ CH 4+392 - 4+477 (HDD-04) |  | 18 | 18 | 2025-03-23 | 2025-04-18 | 2025-04-03 | 2025-04-24 | 66
C-4N-H5HG-CNH04-1000 | Excavation for Entry & Exit Pit Preparation | 7 | 7 | 2025-03-23 | 2025-04-05 | 2025-04-03 | 2025-04-11 | 38
C-4N-H5HG-CNH04-1010 | HDD Section Readiness (Including hydrotest) | 7 | 7 | 2025-03-23 | 2025-04-05 | 2025-04-03 | 2025-04-11 | 66
C-4N-H5HG-CNH04-1020 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | 8 | 8 | 2025-04-05 | 2025-04-15 | 2025-04-11 | 2025-04-21 | 66
C-4N-H5HG-CNH04-1030 | Re-Instatement of Entry & Exit Pit | 3 | 3 | 2025-04-15 | 2025-04-18 | 2025-04-21 | 2025-04-24 | 66
NDRC (incl Hydrotest) at KP 9+013.362CCOPL4"918 |  | 18 | 18 | 2025-04-05 | 2025-04-26 | 2025-04-11 | 2025-05-02 | 59
HDD @ CH 9+139 - 9+322 (HDD-05) |  | 18 | 18 | 2025-04-05 | 2025-04-26 | 2025-04-11 | 2025-05-02 | 59
C-4N-H5HG-CNH05-1000 | Excavation for Entry & Exit Pit Preparation | 7 | 7 | 2025-04-05 | 2025-04-14 | 2025-04-11 | 2025-04-19 | 38
C-4N-H5HG-CNH05-1010 | HDD Section Readiness (Including hydrotest) | 7 | 7 | 2025-04-05 | 2025-04-14 | 2025-04-11 | 2025-04-19 | 59
C-4N-H5HG-CNH05-1020 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | 8 | 8 | 2025-04-14 | 2025-04-23 | 2025-04-19 | 2025-04-29 | 59
C-4N-H5HG-CNH05-1030 | Re-Instatement of Entry & Exit Pit | 3 | 3 | 2025-04-23 | 2025-04-26 | 2025-04-29 | 2025-05-02 | 59
NDRC (incl Hydrotest) at KP 10+556.880CCOPL4"908 |  | 18 | 18 | 2025-04-14 | 2025-05-05 | 2025-04-19 | 2025-05-12 | 52
HDD @ CH 10+556 - 10+647 (HDD-06) |  | 18 | 18 | 2025-04-14 | 2025-05-05 | 2025-04-19 | 2025-05-12 | 52
C-4N-H5HG-CNH06-1000 | Excavation for Entry & Exit Pit Preparation | 7 | 7 | 2025-04-14 | 2025-04-22 | 2025-04-19 | 2025-04-28 | 38
C-4N-H5HG-CNH06-1010 | HDD Section Readiness (Including hydrotest) | 7 | 7 | 2025-04-14 | 2025-04-22 | 2025-04-19 | 2025-04-28 | 52
C-4N-H5HG-CNH06-1020 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | 8 | 8 | 2025-04-22 | 2025-05-01 | 2025-04-28 | 2025-05-08 | 52
C-4N-H5HG-CNH06-1030 | Re-Instatement of Entry & Exit Pit | 3 | 3 | 2025-05-01 | 2025-05-05 | 2025-05-08 | 2025-05-12 | 52
NDRC (incl Hydrotest) at KP 12+216.899CCOPL4"910 |  | 18 | 18 | 2025-04-22 | 2025-05-14 | 2025-04-28 | 2025-05-20 | 45
HDD @ CH 12+216 - 12+275 (HDD-07) |  | 18 | 18 | 2025-04-22 | 2025-05-14 | 2025-04-28 | 2025-05-20 | 45
C-4N-H5HG-CNH07-1000 | Excavation for Entry & Exit Pit Preparation | 7 | 7 | 2025-04-22 | 2025-04-30 | 2025-04-28 | 2025-05-06 | 38
C-4N-H5HG-CNH07-1010 | HDD Section Readiness (Including hydrotest) | 7 | 7 | 2025-04-22 | 2025-04-30 | 2025-04-28 | 2025-05-06 | 45
C-4N-H5HG-CNH07-1020 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | 8 | 8 | 2025-04-30 | 2025-05-10 | 2025-05-07 | 2025-05-16 | 45
C-4N-H5HG-CNH07-1030 | Re-Instatement of Entry & Exit Pit | 3 | 3 | 2025-05-10 | 2025-05-14 | 2025-05-16 | 2025-05-20 | 45
NDRC (incl Hydrotest) at KP 16+746.436CCOPL4"912 |  | 18 | 18 | 2025-04-30 | 2025-05-22 | 2025-05-07 | 2025-05-28 | 38
HDD @ CH 16+746 - 16+764 (HDD-08) |  | 18 | 18 | 2025-04-30 | 2025-05-22 | 2025-05-07 | 2025-05-28 | 38
C-4N-H5HG-CNH08-1000 | Excavation for Entry & Exit Pit Preparation | 7 | 7 | 2025-04-30 | 2025-05-09 | 2025-05-07 | 2025-05-15 | 38
C-4N-H5HG-CNH08-1010 | HDD Section Readiness (Including hydrotest) | 7 | 7 | 2025-04-30 | 2025-05-09 | 2025-05-07 | 2025-05-15 | 38
C-4N-H5HG-CNH08-1020 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | 8 | 8 | 2025-05-09 | 2025-05-19 | 2025-05-15 | 2025-05-24 | 38
C-4N-H5HG-CNH08-1030 | Re-Instatement of Entry & Exit Pit | 3 | 3 | 2025-05-19 | 2025-05-22 | 2025-05-24 | 2025-05-28 | 38
NDRC (incl Hydrotest) at KP 1+400.892CCOPL4"906 |  | 10 | 10 | 2025-02-04 | 2025-02-14 | 2025-03-13 | 2025-03-28 | 55
HDD @ CH 1+401 - 1+551 (HDD-02) |  | 10 | 10 | 2025-02-04 | 2025-02-14 | 2025-03-13 | 2025-03-28 | 55
C-4N-H5HG-CNH2-1010 | HDD Section Readiness (Including hydrotest) | 4 | 4 | 2025-02-04 | 2025-02-07 | 2025-03-13 | 2025-03-18 | 55
C-4N-H5HG-CNH2-1000 | Excavation for Entry & Exit Pit Preparation | 5 | 5 | 2025-02-04 | 2025-02-08 | 2025-03-13 | 2025-03-20 | 55
C-4N-H5HG-CNH2-1020 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | 4 | 4 | 2025-02-08 | 2025-02-12 | 2025-03-19 | 2025-03-24 | 55
C-4N-H5HG-CNH2-1030 | Re-Instatement of Entry & Exit Pit | 2 | 2 | 2025-02-13 | 2025-02-14 | 2025-03-25 | 2025-03-28 | 55
NDRC (incl Hydrotest) at KP 0+236.998CCOPL4"900 |  | 10 | 10 | 2025-01-29 | 2025-02-08 | 2025-02-12 | 2025-02-22 | 78
HDD @ CH 0+236 - 0+389 (HDD-01) |  | 10 | 10 | 2025-01-29 | 2025-02-08 | 2025-02-12 | 2025-02-22 | 78
C-4N-H5HG-CNH1-1010 | HDD Section Readiness (Including hydrotest) | 4 | 4 | 2025-01-29 | 2025-02-01 | 2025-02-12 | 2025-02-15 | 78
C-4N-H5HG-CNH1-1000 | Excavation for Entry & Exit Pit Preparation | 5 | 5 | 2025-01-29 | 2025-02-03 | 2025-02-12 | 2025-02-17 | 73
C-4N-H5HG-CNH1-1020 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | 4 | 4 | 2025-02-03 | 2025-02-06 | 2025-02-17 | 2025-02-20 | 78
C-4N-H5HG-CNH1-1030 | Re-Instatement of Entry & Exit Pit | 2 | 2 | 2025-02-07 | 2025-02-08 | 2025-02-21 | 2025-02-22 | 78
Habshan -5 |  | 201 | 201 | 2024-10-28 | 2025-08-14 | 2025-01-02 | 2025-09-09 | 28
Temporary Pig Launcher (4'' Nitrogen Pipeline) |  | 201 | 201 | 2024-10-28 | 2025-08-14 | 2025-01-02 | 2025-09-09 | 28
Temporary Pig Launcher (4'' Nitrogen Pipeline) |  | 201 | 201 | 2024-10-28 | 2025-08-14 | 2025-01-02 | 2025-09-09 | 28
Civil Works |  | 201 | 201 | 2024-10-28 | 2025-08-14 | 2025-01-02 | 2025-09-09 | 28
Demolition Works (Paving)CCOH5CS100 |  | 6 | 6 | 2024-10-28 | 2024-11-04 | 2025-01-02 | 2025-01-08 | 28
C-4N-H5-TPL-CI-0100 | Demolition Works (Paving) | 6 | 6 | 2024-10-28 | 2024-11-04 | 2025-01-02 | 2025-01-08 | 28
Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 |  | 32 | 32 | 2024-11-04 | 2024-12-19 | 2025-01-09 | 2025-02-14 | 28
C-4N-H5-TPL-CI-1000 | Site Survey, Preparation & Grading Works | 4 | 4 | 2024-11-04 | 2024-11-11 | 2025-01-09 | 2025-01-13 | 28
C-4N-H5-TPL-CI-1010 | Earth Works for Equipment Foundations | 4 | 4 | 2024-11-11 | 2024-11-15 | 2025-01-14 | 2025-01-17 | 28
C-4N-H5-TPL-CI-1020 | Earth Works for Pipe Support Foundations | 4 | 4 | 2024-11-15 | 2024-11-21 | 2025-01-18 | 2025-01-22 | 28
C-4N-H5-TPL-CI-1030 | Earth Works for Field Instrument, JBs & Light Pole Foundations | 4 | 4 | 2024-11-21 | 2024-11-27 | 2025-01-23 | 2025-01-27 | 28
C-4N-H5-TPL-CI-1040 | Earth Works for Access Platforms & Misc. Structural Foundations | 4 | 4 | 2024-11-27 | 2024-12-05 | 2025-01-28 | 2025-01-31 | 28
C-4N-H5-TPL-CI-1200 | Compaction & Testing for Equipment Foundations | 3 | 3 | 2024-12-05 | 2024-12-09 | 2025-02-01 | 2025-02-04 | 28
C-4N-H5-TPL-CI-1210 | Compaction & Testing for Pipe Support Foundations | 3 | 3 | 2024-12-09 | 2024-12-12 | 2025-02-05 | 2025-02-07 | 28
C-4N-H5-TPL-CI-1220 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | 3 | 3 | 2024-12-12 | 2024-12-16 | 2025-02-08 | 2025-02-11 | 28
C-4N-H5-TPL-CI-1230 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | 3 | 3 | 2024-12-16 | 2024-12-19 | 2025-02-12 | 2025-02-14 | 28
Piperack - Reinforced in-situ concrete for Strengthening of existing foundationsCCOH5CS102.1 |  | 40 | 40 | 2024-12-12 | 2025-02-21 | 2025-02-08 | 2025-04-05 | 30
C-4N-H5-TPL-PR-1000 | Piperack - Reinforced in-situ concrete for Strengthening of existing foundations | 40 | 40 | 2024-12-12 | 2025-02-21 | 2025-02-08 | 2025-04-05 | 30
Piperack - Reinforced in-situ concrete for Strengthening of existing foundationsCCOH5CS102.2 |  | 50 | 50 | 2025-02-21 | 2025-04-30 | 2025-04-05 | 2025-06-04 | 30
C-4N-H5-TPL-PR-1200 | Piperack - Reinforced in-situ concrete for Strengthening of existing foundations | 50 | 50 | 2025-02-21 | 2025-04-30 | 2025-04-05 | 2025-06-04 | 30
Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 |  | 32 | 32 | 2025-01-24 | 2025-03-02 | 2025-03-05 | 2025-04-21 | 28
C-4N-H5-TPL-CI-1400 | Concrete Works for Equipment Foundations | 12 | 12 | 2025-01-24 | 2025-02-07 | 2025-03-05 | 2025-03-23 | 28
C-4N-H5-TPL-CI-1600 | Concrete Works for Pipe Support Foundations | 8 | 8 | 2025-02-07 | 2025-02-17 | 2025-03-23 | 2025-04-07 | 28
C-4N-H5-TPL-CI-1410 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | 6 | 6 | 2025-02-17 | 2025-02-24 | 2025-04-07 | 2025-04-14 | 28
C-4N-H5-TPL-CI-1420 | Concrete Works for Access Platforms & Misc. Structural Foundations | 6 | 6 | 2025-02-24 | 2025-03-02 | 2025-04-14 | 2025-04-21 | 28
Concrete ProtectionCCOH5CS104 |  | 18 | 18 | 2025-04-15 | 2025-05-07 | 2025-05-20 | 2025-06-12 | 37
C-4N-H5-TPL-CI-1700 | Concrete Protection | 18 | 18 | 2025-04-15 | 2025-05-07 | 2025-05-20 | 2025-06-12 | 37
Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 |  | 36 | 36 | 2025-04-30 | 2025-06-14 | 2025-06-04 | 2025-07-19 | 30
C-4N-H5-TPL-CI-2000 | Pre-Fabrication & Installation of Pipe Supports | 12 | 12 | 2025-04-30 | 2025-05-15 | 2025-06-04 | 2025-06-20 | 30
C-4N-H5-TPL-CI-3000 | Pre-Fabrication & Installation of Platforms & Crossovers | 8 | 8 | 2025-05-24 | 2025-06-03 | 2025-07-01 | 2025-07-10 | 30
C-4N-H5-TPL-CI-3010 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | 8 | 8 | 2025-06-03 | 2025-06-14 | 2025-07-10 | 2025-07-19 | 30
Trenching for CablesCCOH5CS105 |  | 16 | 16 | 2025-04-16 | 2025-05-05 | 2025-05-27 | 2025-06-17 | 58
C-4N-H5-TPL-CI-1800 | Electrical & Earthing Cable Trenching | 8 | 8 | 2025-04-16 | 2025-04-25 | 2025-05-27 | 2025-06-07 | 28
C-4N-H5-TPL-CI-1810 | Instrument & Telecom Cable Trenching | 8 | 8 | 2025-04-25 | 2025-05-05 | 2025-06-07 | 2025-06-17 | 58
Paving WorksCCOH5CS107 |  | 10 | 10 | 2025-08-02 | 2025-08-14 | 2025-08-27 | 2025-09-09 | 28
C-4N-H5-TPL-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 10 | 10 | 2025-08-02 | 2025-08-14 | 2025-08-27 | 2025-09-09 | 28
Backfilling for CablesCCOH5CS108 |  | 9 | 9 | 2025-07-19 | 2025-08-02 | 2025-08-28 | 2025-09-09 | 28
C-4N-H5-TPL-CI-2800 | Back Filling for Electrical & Earthing Cable | 6 | 6 | 2025-07-19 | 2025-07-26 | 2025-08-28 | 2025-09-04 | 28
C-4N-H5-TPL-CI-2810 | Back Filling for Instrument & Telecom Cable | 6 | 6 | 2025-07-26 | 2025-08-02 | 2025-09-01 | 2025-09-09 | 28
Mechanical Works & Equipment Installation |  | 3 | 3 | 2025-05-10 | 2025-05-14 | 2025-05-10 | 2025-05-14 | 105
Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH5ME502 |  | 3 | 3 | 2025-05-10 | 2025-05-14 | 2025-05-10 | 2025-05-14 | 105
C-4N-H5-TPL-ME-1000 | Installation of Pig Launcher 4" | 3 | 3 | 2025-05-10 | 2025-05-14 | 2025-05-10 | 2025-05-14 | 105
Piping Works |  | 41 | 41 | 2025-06-14 | 2025-08-11 | 2025-07-19 | 2025-09-06 | 30
Piping Pre-FabricationCCOH5PI501 |  | 21 | 21 | 2025-06-14 | 2025-07-10 | 2025-07-19 | 2025-08-13 | 30
C-4N-H5-TPL-PI-1000 | Piping Pre-Fabrication | 21 | 21 | 2025-06-14 | 2025-07-10 | 2025-07-19 | 2025-08-13 | 30
ErectionCCOH5PI515 |  | 6 | 6 | 2025-07-10 | 2025-07-17 | 2025-08-13 | 2025-08-20 | 30
C-4N-H5-TPL-PI-1200 | Piping Erection | 6 | 6 | 2025-07-10 | 2025-07-17 | 2025-08-13 | 2025-08-20 | 30
Field Joint Welding, NDT & CoatingCCOH5PI525 |  | 9 | 9 | 2025-07-17 | 2025-07-31 | 2025-08-15 | 2025-08-26 | 30
C-4N-H5-TPL-PI-1400 | Field Joint Welding | 6 | 6 | 2025-07-17 | 2025-07-24 | 2025-08-15 | 2025-08-22 | 30
C-4N-H5-TPL-PI-1410 | NDT & Coating for Field Joint Weld | 6 | 6 | 2025-07-24 | 2025-07-31 | 2025-08-19 | 2025-08-26 | 30
HydrotestingCCOH5PI535 |  | 3 | 3 | 2025-07-31 | 2025-08-04 | 2025-08-26 | 2025-08-29 | 30
C-4N-H5-TPL-PI-1600 | Hydrotesting | 3 | 3 | 2025-07-31 | 2025-08-04 | 2025-08-26 | 2025-08-29 | 30
Installation of ValvesCCOH5PI545 |  | 3 | 3 | 2025-08-04 | 2025-08-07 | 2025-08-29 | 2025-09-02 | 30
C-4N-H5-TPL-PI-1800 | Installation of Valves/MOV/ROV | 3 | 3 | 2025-08-04 | 2025-08-07 | 2025-08-29 | 2025-09-02 | 30
Final Bolt Torquing/ Re-InstatementCCOH5PI555 |  | 2 | 2 | 2025-08-08 | 2025-08-11 | 2025-09-03 | 2025-09-06 | 30
C-4N-H5-TPL-PI-2000 | Final Bolt Torquing/ Re-Instatement | 2 | 2 | 2025-08-08 | 2025-08-11 | 2025-09-03 | 2025-09-06 | 30
Electrical & Instrumentation Works |  | 58 | 58 | 2025-05-15 | 2025-07-19 | 2025-06-20 | 2025-08-28 | 28
E&I WorksCCOH5EL524 |  | 58 | 58 | 2025-05-15 | 2025-07-19 | 2025-06-20 | 2025-08-28 | 28
C-4N-H5-TPL-EI-2210 | Pre-Fabrication & Installation of Field Instrument, JB Supports | 8 | 8 | 2025-05-15 | 2025-05-24 | 2025-06-20 | 2025-07-01 | 30
C-4N-H5-TPL-EI-1800 | Installation of Light Pole, Lighting & Fixtures | 5 | 5 | 2025-06-23 | 2025-06-30 | 2025-08-02 | 2025-08-08 | 28
C-4N-H5-TPL-EI-1810 | Installation of JB's | 3 | 3 | 2025-06-30 | 2025-07-03 | 2025-08-08 | 2025-08-12 | 28
C-4N-H5-TPL-EI-2200 | Installation of Field Instruments (Including Pig Signaller) | 3 | 3 | 2025-07-03 | 2025-07-07 | 2025-08-12 | 2025-08-15 | 28
C-4N-H5-TPL-EI-2410 | Installation of F&G Device | 3 | 3 | 2025-07-07 | 2025-07-10 | 2025-08-15 | 2025-08-19 | 28
C-4N-H5-TPL-EI-2040 | Loop Checking for Instruments | 5 | 5 | 2025-07-10 | 2025-07-16 | 2025-08-19 | 2025-08-25 | 28
C-4N-H5-TPL-EI-2050 | Glanding & Termination | 3 | 3 | 2025-07-16 | 2025-07-19 | 2025-08-25 | 2025-08-28 | 28
Cable Laying & TerminationCCOH5EL526 |  | 17 | 17 | 2025-05-31 | 2025-06-23 | 2025-07-14 | 2025-08-02 | 50
C-4N-H5-TPL-EI-2000 | Electrical & Earthing Cable Laying | 5 | 5 | 2025-05-31 | 2025-06-09 | 2025-07-14 | 2025-07-19 | 28
C-4N-H5-TPL-CA-1000 | CP Cable Laying | 2 | 2 | 2025-06-09 | 2025-06-11 | 2025-07-19 | 2025-07-22 | 55
C-4N-H5-TPL-EI-2020 | Installation of Cable Trays | 3 | 3 | 2025-06-09 | 2025-06-12 | 2025-07-19 | 2025-07-23 | 28
C-4N-H5-TPL-CA-1010 | Installation of CP Test Post | 2 | 2 | 2025-06-11 | 2025-06-13 | 2025-07-22 | 2025-07-24 | 55
C-4N-H5-TPL-CA-1020 | Installation of CP JB's | 2 | 2 | 2025-06-13 | 2025-06-16 | 2025-07-24 | 2025-07-26 | 55
C-4N-H5-TPL-CA-1030 | Glanding & Termination for CP S/m | 1 | 1 | 2025-06-16 | 2025-06-17 | 2025-07-26 | 2025-07-28 | 55
C-4N-H5-TPL-EI-2010 | Instrument Cable Laying | 5 | 5 | 2025-06-12 | 2025-06-18 | 2025-07-23 | 2025-07-29 | 28
C-4N-H5-TPL-EI-2030 | Instrument Tubing Works | 4 | 4 | 2025-06-18 | 2025-06-23 | 2025-07-29 | 2025-08-02 | 28
Telecommunication Works |  | 8 | 8 | 2025-06-18 | 2025-06-28 | 2025-07-29 | 2025-08-07 | 55
Telecommunication Works CCOH5IC528 |  | 8 | 8 | 2025-06-18 | 2025-06-28 | 2025-07-29 | 2025-08-07 | 55
C-4N-H5-TPL-TE-1410 | FOC Laying | 6 | 6 | 2025-06-18 | 2025-06-25 | 2025-07-29 | 2025-08-05 | 55
C-4N-H5-TPL-TE-1420 | FO Cable OTDR Testing & Splicing | 2 | 2 | 2025-06-25 | 2025-06-28 | 2025-08-05 | 2025-08-07 | 55
Shutdown |  | 3 | 3 | 2025-06-17 | 2025-06-20 | 2025-07-28 | 2025-07-31 | 59
Electrical Shutdown (PDBs)CCOH5ST529 |  | 3 | 3 | 2025-06-17 | 2025-06-20 | 2025-07-28 | 2025-07-31 | 59
C-4N-H5-TPL-EL-1000 | Electrical Shutdown (PDBs) | 3 | 3 | 2025-06-17 | 2025-06-20 | 2025-07-28 | 2025-07-31 | 59
Tie - in / Piping Hook-up |  | 7 | 7 | 2025-04-05 | 2025-04-14 | 2025-06-12 | 2025-06-20 | 95
Tie In to existing SkidCCOH5PI504 |  | 1 | 1 | 2025-04-05 | 2025-04-07 | 2025-06-12 | 2025-06-13 | 95
C-4N-H5-TPL-PL-1000 | Installation of Isolation Joint | 1 | 1 | 2025-04-05 | 2025-04-07 | 2025-06-12 | 2025-06-13 | 95
Temporary Pig Launcher (4'' Nitrogen Pipeline) Piping Hook-upCCOH5PI505 |  | 6 | 6 | 2025-04-07 | 2025-04-14 | 2025-06-13 | 2025-06-20 | 95
C-4N-H5-TPL-PL-1010 | Field Joint Welding (Piping/Pipeline Section including IJ) | 2 | 2 | 2025-04-07 | 2025-04-09 | 2025-06-13 | 2025-06-16 | 95
C-4N-H5-TPL-PL-1020 | NDT for Weld Joint | 2 | 2 | 2025-04-09 | 2025-04-11 | 2025-06-16 | 2025-06-18 | 95
C-4N-H5-TPL-PL-1030 | Ext. Coating for Weld Joint | 2 | 2 | 2025-04-11 | 2025-04-14 | 2025-06-18 | 2025-06-20 | 95
Temporary Pig Receiver (4'' Nitrogen Pipeline) |  | 174 | 174 | 2024-12-05 | 2025-08-13 | 2025-02-01 | 2025-09-08 | 35
Temporary Pig Receiver (4'' Nitrogen Pipeline)-1 |  | 174 | 174 | 2024-12-05 | 2025-08-13 | 2025-02-01 | 2025-09-08 | 35
Civil Works |  | 174 | 174 | 2024-12-05 | 2025-08-13 | 2025-02-01 | 2025-09-08 | 35
Demolition Works (Paving)CCOH4NCS64 |  | 6 | 6 | 2024-12-05 | 2024-12-12 | 2025-02-01 | 2025-02-07 | 82
C-4N-HG-TPR-CI-0100 | Demolition Works (Paving) | 6 | 6 | 2024-12-05 | 2024-12-12 | 2025-02-01 | 2025-02-07 | 82
Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 |  | 158 | 158 | 2024-12-12 | 2025-08-01 | 2025-02-08 | 2025-08-26 | 45
C-4N-HG-TPR-CI-1000 | Site Survey, Preparation & Grading Works | 6 | 6 | 2024-12-12 | 2024-12-19 | 2025-02-08 | 2025-02-14 | 82
C-4N-HG-TPR-CI-1010 | Earth Works for Equipment Foundations | 4 | 4 | 2024-12-19 | 2024-12-24 | 2025-02-15 | 2025-02-19 | 82
C-4N-HG-TPR-CI-1200 | Compaction & Testing for Equipment Foundations | 3 | 3 | 2024-12-24 | 2024-12-27 | 2025-02-20 | 2025-02-22 | 87
C-4N-HG-TPR-CI-1020 | Earth Works for Pipe Support Foundations | 5 | 5 | 2024-12-24 | 2024-12-30 | 2025-02-20 | 2025-02-25 | 82
C-4N-HG-TPR-CI-1210 | Compaction & Testing for Pipe Support Foundations | 3 | 3 | 2024-12-30 | 2025-01-03 | 2025-02-26 | 2025-02-28 | 108
C-4N-HG-TPR-CI-1030 | Earth Works for Field Instrument, JBs & Light Pole Foundations | 5 | 5 | 2024-12-30 | 2025-01-06 | 2025-02-26 | 2025-03-03 | 82
C-4N-HG-TPR-CI-1220 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | 3 | 3 | 2025-01-06 | 2025-01-09 | 2025-03-03 | 2025-03-08 | 142
C-4N-HG-TPR-CI-1040 | Earth Works for Access Platforms & Misc. Structural Foundations | 5 | 5 | 2025-01-06 | 2025-01-11 | 2025-03-03 | 2025-03-11 | 82
C-4N-HG-TPR-CI-1400 | Concrete Works for Equipment Foundations | 12 | 12 | 2024-12-27 | 2025-01-11 | 2025-02-24 | 2025-03-11 | 87
C-4N-HG-TPR-CI-1060 | Earth Works for Impact Wall | 3 | 3 | 2025-01-11 | 2025-01-15 | 2025-03-11 | 2025-03-15 | 82
C-4N-HG-TPR-CI-1230 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | 3 | 3 | 2025-01-11 | 2025-01-15 | 2025-03-11 | 2025-03-15 | 143
C-4N-HG-TPR-CI-1250 | Compaction & Testing for Impact Wall | 2 | 2 | 2025-01-15 | 2025-01-17 | 2025-03-15 | 2025-03-18 | 82
C-4N-HG-TPR-CI-1500 | Concrete Works for Impact Wall | 14 | 14 | 2025-01-17 | 2025-02-03 | 2025-03-19 | 2025-04-10 | 82
C-4N-HG-TPR-CI-1600 | Concrete Works for Pipe Support Foundations | 8 | 8 | 2025-02-03 | 2025-02-12 | 2025-04-10 | 2025-04-19 | 82
C-4N-HG-TPR-CI-1410 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | 6 | 6 | 2025-02-12 | 2025-02-19 | 2025-04-19 | 2025-04-26 | 113
C-4N-HG-TPR-CI-1420 | Concrete Works for Access Platforms & Misc. Structural Foundations | 6 | 6 | 2025-02-19 | 2025-02-26 | 2025-04-26 | 2025-05-03 | 113
C-4N-HG-TPR-CI-2000 | Pre-Fabrication & Installation of Pipe Supports | 12 | 12 | 2025-02-12 | 2025-02-26 | 2025-04-19 | 2025-05-03 | 82
C-4N-HG-TPR-CI-1800 | Electrical & Earthing Cable Trenching | 8 | 8 | 2025-04-15 | 2025-04-24 | 2025-05-21 | 2025-05-30 | 64
C-4N-HG-TPR-CI-1810 | Instrument & Telecom Cable Trenching | 8 | 8 | 2025-04-24 | 2025-05-03 | 2025-05-30 | 2025-06-11 | 64
C-4N-HG-TPR-CI-3000 | Pre-Fabrication & Installation of Platforms & Crossovers | 8 | 8 | 2025-05-08 | 2025-05-17 | 2025-06-25 | 2025-07-05 | 71
C-4N-HG-TPR-CI-3010 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | 8 | 8 | 2025-05-17 | 2025-05-27 | 2025-07-05 | 2025-07-15 | 81
C-4N-HG-TPR-CI-2800 | Back Filling for Electrical & Earthing Cable | 6 | 6 | 2025-07-18 | 2025-07-25 | 2025-08-12 | 2025-08-19 | 35
C-4N-HG-TPR-CI-2810 | Back Filling for Instrument & Telecom Cable | 6 | 6 | 2025-07-25 | 2025-08-01 | 2025-08-19 | 2025-08-26 | 35
Concrete ProtectionCCOH4NCS66 |  | 18 | 18 | 2025-02-11 | 2025-03-03 | 2025-04-18 | 2025-05-10 | 134
C-4N-HG-TPR-CI-1700 | Concrete Protection | 18 | 18 | 2025-02-11 | 2025-03-03 | 2025-04-18 | 2025-05-10 | 134
Fences & Gates ConstructionCCOH4NCS67 |  | 18 | 18 | 2025-05-17 | 2025-06-10 | 2025-07-05 | 2025-07-26 | 71
C-4N-HG-TPR-CI-2220 | Fences & Gates Construction | 18 | 18 | 2025-05-17 | 2025-06-10 | 2025-07-05 | 2025-07-26 | 71
Paving WorksCCOH4NCS69 |  | 10 | 10 | 2025-08-01 | 2025-08-13 | 2025-08-26 | 2025-09-08 | 35
C-4N-HG-TPR-CI-2600 | Paving of Interlock tiles & Kerb Stone Embankment | 10 | 10 | 2025-08-01 | 2025-08-13 | 2025-08-26 | 2025-09-08 | 35
Mechanical Works & Equipment Installation |  | 2 | 2 | 2025-05-07 | 2025-05-09 | 2025-05-07 | 2025-05-09 | 135
Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH4NME50 |  | 2 | 2 | 2025-05-07 | 2025-05-09 | 2025-05-07 | 2025-05-09 | 135
C-4N-HG-TPR-ME-1100 | Installation of Pig Receiver 4" | 2 | 2 | 2025-05-07 | 2025-05-09 | 2025-05-07 | 2025-05-09 | 135
Piping Works |  | 48 | 48 | 2025-02-15 | 2025-04-28 | 2025-04-17 | 2025-06-16 | 71
Piping Pre-FabricationCCOH4NPI050 |  | 21 | 21 | 2025-02-15 | 2025-03-14 | 2025-04-17 | 2025-05-13 | 71
C-4N-HG-TPR-PI-1000 | Piping Pre-Fabrication | 21 | 21 | 2025-02-15 | 2025-03-14 | 2025-04-17 | 2025-05-13 | 71
ErectionCCOH4NPI060 |  | 6 | 6 | 2025-03-20 | 2025-03-29 | 2025-05-13 | 2025-05-20 | 71
C-4N-HG-TPR-PI-1200 | Piping Erection | 6 | 6 | 2025-03-20 | 2025-03-29 | 2025-05-13 | 2025-05-20 | 71
Field Joint Welding, NDT & CoatingCCOH4NPI070 |  | 12 | 12 | 2025-04-03 | 2025-04-17 | 2025-05-20 | 2025-06-03 | 71
C-4N-HG-TPR-PI-1400 | Field Joint Welding | 6 | 6 | 2025-04-03 | 2025-04-10 | 2025-05-20 | 2025-05-27 | 71
C-4N-HG-TPR-PI-1410 | NDT & Coating for Field Joint Weld | 6 | 6 | 2025-04-10 | 2025-04-17 | 2025-05-27 | 2025-06-03 | 71
HydrotestingCCOH4NPI080 |  | 3 | 3 | 2025-04-17 | 2025-04-21 | 2025-06-03 | 2025-06-09 | 71
C-4N-HG-TPR-PI-1600 | Hydrotesting | 3 | 3 | 2025-04-17 | 2025-04-21 | 2025-06-03 | 2025-06-09 | 71
Installation of ValvesCCOH4NPI090 |  | 3 | 3 | 2025-04-21 | 2025-04-24 | 2025-06-09 | 2025-06-12 | 71
C-4N-HG-TPR-PI-1800 | Installation of Valves/MOV/ROV | 3 | 3 | 2025-04-21 | 2025-04-24 | 2025-06-09 | 2025-06-12 | 71
Final Bolt Torquing/ Re-InstatementCCOH4NPI100 |  | 2 | 2 | 2025-04-25 | 2025-04-28 | 2025-06-13 | 2025-06-16 | 71
C-4N-HG-TPR-PI-2000 | Final Bolt Torquing/ Re-Instatement | 2 | 2 | 2025-04-25 | 2025-04-28 | 2025-06-13 | 2025-06-16 | 71
Electrical & Instrumentation Works |  | 56 | 56 | 2025-04-28 | 2025-07-28 | 2025-06-16 | 2025-08-21 | 49
E&I WorksCCOH4NEL51 |  | 48 | 48 | 2025-04-28 | 2025-07-18 | 2025-06-16 | 2025-08-12 | 35
C-4N-HG-TPR-EI-2210 | Pre-Fabrication & Installation of Field Instrument, JB Supports | 8 | 8 | 2025-04-28 | 2025-05-08 | 2025-06-16 | 2025-06-25 | 71
C-4N-HG-TPR-EI-1800 | Installation of Light Pole, Lighting & Fixtures | 5 | 5 | 2025-07-02 | 2025-07-08 | 2025-07-26 | 2025-08-01 | 35
C-4N-HG-TPR-EI-1810 | Installation of JB's | 3 | 3 | 2025-07-08 | 2025-07-11 | 2025-08-01 | 2025-08-05 | 35
C-4N-HG-TPR-EI-2200 | Installation of Field Instruments (Including Pig Signaller) | 3 | 3 | 2025-07-11 | 2025-07-15 | 2025-08-05 | 2025-08-08 | 35
C-4N-HG-TPR-EI-2410 | Installation of F&G Device | 3 | 3 | 2025-07-15 | 2025-07-18 | 2025-08-08 | 2025-08-12 | 35
Cable Laying & TerminationCCOH4NEL52 |  | 55 | 55 | 2025-05-10 | 2025-07-28 | 2025-06-17 | 2025-08-21 | 49
C-4N-HG-TPR-EI-2000 | Electrical & Earthing Cable Laying | 5 | 5 | 2025-05-10 | 2025-05-16 | 2025-06-17 | 2025-06-23 | 51
C-4N-HG-TPR-EI-2020 | Installation of Cable Trays | 3 | 3 | 2025-05-16 | 2025-05-20 | 2025-06-23 | 2025-06-26 | 51
C-4N-HG-TPR-EI-2010 | Instrument Cable Laying | 5 | 5 | 2025-06-20 | 2025-06-26 | 2025-07-16 | 2025-07-22 | 35
C-4N-HG-TPR-CA-1000 | CP Cable Laying | 2 | 2 | 2025-06-28 | 2025-07-01 | 2025-07-23 | 2025-07-25 | 46
C-4N-HG-TPR-EI-2030 | Instrument Tubing Works | 4 | 4 | 2025-06-26 | 2025-07-02 | 2025-07-22 | 2025-07-26 | 35
C-4N-HG-TPR-CA-1010 | Installation of CP Test Post | 2 | 2 | 2025-07-01 | 2025-07-03 | 2025-07-25 | 2025-07-28 | 46
C-4N-HG-TPR-CA-1020 | Installation of CP JB's | 2 | 2 | 2025-07-03 | 2025-07-05 | 2025-07-28 | 2025-07-30 | 46
C-4N-HG-TPR-CA-1030 | Glanding & Termination for CP S/m | 1 | 1 | 2025-07-05 | 2025-07-07 | 2025-07-30 | 2025-07-31 | 67
C-4N-HG-TPR-EI-2040 | Loop Checking for Instruments | 5 | 5 | 2025-07-18 | 2025-07-24 | 2025-08-12 | 2025-08-18 | 49
C-4N-HG-TPR-EI-2050 | Glanding & Termination | 3 | 3 | 2025-07-24 | 2025-07-28 | 2025-08-18 | 2025-08-21 | 49
Telecommunication Works |  | 22 | 22 | 2025-07-08 | 2025-07-17 | 2025-08-01 | 2025-08-27 | 44
Telecommunication Works CCOH4NIC52 |  | 22 | 22 | 2025-07-08 | 2025-07-17 | 2025-08-01 | 2025-08-27 | 44
C-4N-HG-TPR-TE-1410 | FOC Laying | 6 | 6 | 2025-07-08 | 2025-07-15 | 2025-08-01 | 2025-08-08 | 44
C-4N-HG-TPR-TE-1420 | FO Cable OTDR Testing & Splicing | 2 | 2 | 2025-07-15 | 2025-07-17 | 2025-08-25 | 2025-08-27 | 44
Piping Hook-up |  | 7 | 7 | 2025-06-03 | 2025-06-13 | 2025-08-01 | 2025-08-08 | 59
Temporary Pig Receiver (4'' Nitrogen Pipeline) Piping Hook-upCCOH4NPI51 |  | 7 | 7 | 2025-06-03 | 2025-06-13 | 2025-08-01 | 2025-08-08 | 59
C-4N-HG-TPR-PL-1000 | Installation of Isolation Joint | 1 | 1 | 2025-06-03 | 2025-06-04 | 2025-08-01 | 2025-08-01 | 59
C-4N-HG-TPR-PL-1010 | Field Joint Welding (Piping/Pipeline Section including IJ) | 2 | 2 | 2025-06-04 | 2025-06-09 | 2025-08-02 | 2025-08-04 | 59
C-4N-HG-TPR-PL-1020 | NDT for Weld Joint | 2 | 2 | 2025-06-09 | 2025-06-11 | 2025-08-05 | 2025-08-06 | 59
C-4N-HG-TPR-PL-1030 | Ext. Coating for Weld Joint | 2 | 2 | 2025-06-11 | 2025-06-13 | 2025-08-07 | 2025-08-08 | 59
SV-03 (KP 96) to HGCP (4") |  | 160 | 160 | 2024-11-30 | 2025-07-14 | 2025-01-11 | 2025-07-31 | 21
4'' Water Line from SV-03 (KP 96) to HGCP (4'') |  | 74 | 74 | 2024-11-30 | 2025-03-03 | 2025-01-11 | 2025-04-17 | 101
4'' Water Line from SV-03 (KP 96) to HGCP (1.8 km) |  | 74 | 74 | 2024-11-30 | 2025-03-03 | 2025-01-11 | 2025-04-17 | 101
Construction 4'' RTP Water LineCCOPL4"150 |  | 74 | 74 | 2024-11-30 | 2025-03-03 | 2025-01-11 | 2025-04-17 | 101
C-4W-SVHG-PIPEL-1000 | Survey Marking | 2 | 2 | 2024-11-30 | 2024-12-04 | 2025-01-11 | 2025-01-13 | 15
C-4W-SVHG-PIPEL-1800 | Sabka ROW/Grading | 2 | 2 | 2024-12-05 | 2024-12-06 | 2025-01-14 | 2025-01-15 | 15
C-4W-SVHG-PIPEL-2000 | Sabka Gatch Laying (Including ROW) - Layer 1 | 3 | 3 | 2024-12-07 | 2024-12-10 | 2025-01-16 | 2025-01-18 | 15
C-4W-SVHG-PIPEL-2200 | Sabka Gatch Compaction (Including ROW) - Layer 1 | 3 | 3 | 2024-12-09 | 2024-12-11 | 2025-01-17 | 2025-01-20 | 15
C-4W-SVHG-PIPEL-2010 | Sabka Gatch Laying - Layer 2 | 3 | 3 | 2024-12-11 | 2024-12-13 | 2025-01-20 | 2025-01-22 | 15
C-4W-SVHG-PIPEL-2210 | Sabka Gatch Compaction - Layer 2 | 3 | 3 | 2024-12-12 | 2024-12-14 | 2025-01-21 | 2025-01-23 | 15
C-4W-SVHG-PIPEL-2020 | Sabka Gatch Laying - Layer 3 | 3 | 3 | 2024-12-14 | 2024-12-17 | 2025-01-23 | 2025-01-25 | 15
C-4W-SVHG-PIPEL-2220 | Sabka Gatch Compaction - Layer 3 | 3 | 3 | 2024-12-16 | 2024-12-18 | 2025-01-24 | 2025-01-27 | 15
C-4W-SVHG-PIPEL-2030 | Sabka Gatch Laying - Layer 4 | 3 | 3 | 2024-12-18 | 2024-12-20 | 2025-01-27 | 2025-01-29 | 15
C-4W-SVHG-PIPEL-2230 | Sabka Gatch Compaction - Layer 4 | 3 | 3 | 2024-12-19 | 2024-12-21 | 2025-01-28 | 2025-01-30 | 15
C-4W-SVHG-PIPEL-2800 | Stringing (SV-03 to HGCP) | 8 | 8 | 2024-12-23 | 2024-12-31 | 2025-01-31 | 2025-02-08 | 34
C-4W-SVHG-PIPEL-3100 | Field Joint | 8 | 8 | 2024-12-23 | 2024-12-31 | 2025-01-31 | 2025-02-08 | 78
C-4W-SVHG-PIPEL-3110 | Field Joint Protection Sleeve | 8 | 8 | 2024-12-24 | 2025-01-02 | 2025-02-01 | 2025-02-10 | 78
C-4W-SVHG-PIPEL-2400 | Trench Excavation | 8 | 8 | 2024-12-25 | 2025-01-03 | 2025-02-03 | 2025-02-11 | 15
C-4W-SVHG-PIPEL-2410 | Bedding | 8 | 8 | 2024-12-25 | 2025-01-03 | 2025-02-03 | 2025-02-11 | 79
C-4W-SVHG-PIPEL-4800 | Lowering | 8 | 8 | 2024-12-27 | 2025-01-06 | 2025-02-05 | 2025-02-13 | 78
C-4W-SVHG-PIPEL-4810 | Section Tie-in Joint | 1 | 1 | 2025-01-07 | 2025-01-07 | 2025-02-14 | 2025-02-14 | 78
C-4W-SVHG-PIPEL-3120 | Field Joint Protection Sleeve | 1 | 1 | 2025-01-08 | 2025-01-08 | 2025-02-15 | 2025-02-15 | 78
C-4W-SVHG-PIPEL-6000 | Padding | 6 | 6 | 2025-01-09 | 2025-01-15 | 2025-02-17 | 2025-02-22 | 78
Crossings (Manual/Mechanical) |  | 23 | 23 | 2025-01-04 | 2025-01-30 | 2025-02-12 | 2025-03-12 | 65
Crossing Manual @ KP 0+151 (FX-02) |  | 6 | 6 | 2025-01-04 | 2025-01-10 | 2025-02-12 | 2025-02-18 | 82
CPL-4-CRMN-3320 | Trench Excavation | 4 | 4 | 2025-01-04 | 2025-01-08 | 2025-02-12 | 2025-02-15 | 15
CPL-4-CRMN-3330 | Bedding | 1 | 1 | 2025-01-08 | 2025-01-08 | 2025-02-15 | 2025-02-15 | 28
CPL-4-CRMN-3340 | Lowering | 1 | 1 | 2025-01-09 | 2025-01-09 | 2025-02-17 | 2025-02-17 | 28
CPL-4-CRMN-3350 | Section Tie-in Joint | 1 | 1 | 2025-01-09 | 2025-01-09 | 2025-02-17 | 2025-02-17 | 82
CPL-4-CRMN-3370 | Field Joint Protection Sleeve | 1 | 1 | 2025-01-09 | 2025-01-09 | 2025-02-17 | 2025-02-17 | 82
CPL-4-CRMN-3390 | Padding | 1 | 1 | 2025-01-10 | 2025-01-10 | 2025-02-18 | 2025-02-18 | 82
Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) |  | 7 | 7 | 2025-01-09 | 2025-01-16 | 2025-02-17 | 2025-02-24 | 77
CPL-4-CRMN-3400 | Trench Excavation | 5 | 5 | 2025-01-09 | 2025-01-14 | 2025-02-17 | 2025-02-21 | 15
CPL-4-CRMN-3410 | Bedding | 1 | 1 | 2025-01-14 | 2025-01-14 | 2025-02-21 | 2025-02-21 | 24
CPL-4-CRMN-3420 | Lowering | 1 | 1 | 2025-01-15 | 2025-01-15 | 2025-02-22 | 2025-02-22 | 24
CPL-4-CRMN-3430 | Section Tie-in Joint | 1 | 1 | 2025-01-15 | 2025-01-15 | 2025-02-22 | 2025-02-22 | 77
CPL-4-CRMN-3440 | Field Joint Protection Sleeve | 1 | 1 | 2025-01-15 | 2025-01-15 | 2025-02-22 | 2025-02-22 | 77
CPL-4-CRMN-3450 | Padding | 1 | 1 | 2025-01-16 | 2025-01-16 | 2025-02-24 | 2025-02-24 | 77
Crossing Manual @ KP 1+268 (CX-05) |  | 5 | 5 | 2025-01-15 | 2025-01-20 | 2025-02-22 | 2025-02-27 | 74
CPL-4-CRMN-3460 | Trench Excavation | 3 | 3 | 2025-01-15 | 2025-01-17 | 2025-02-22 | 2025-02-25 | 15
CPL-4-CRMN-3470 | Bedding | 1 | 1 | 2025-01-17 | 2025-01-17 | 2025-02-25 | 2025-02-25 | 22
CPL-4-CRMN-3480 | Lowering | 1 | 1 | 2025-01-18 | 2025-01-18 | 2025-02-26 | 2025-02-26 | 22
CPL-4-CRMN-3490 | Section Tie-in Joint | 1 | 1 | 2025-01-18 | 2025-01-18 | 2025-02-26 | 2025-02-26 | 74
CPL-4-CRMN-3500 | Field Joint Protection Sleeve | 1 | 1 | 2025-01-18 | 2025-01-18 | 2025-02-26 | 2025-02-26 | 74
CPL-4-CRMN-3510 | Padding | 1 | 1 | 2025-01-20 | 2025-01-20 | 2025-02-27 | 2025-02-27 | 74
Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) |  | 8 | 8 | 2025-01-18 | 2025-01-27 | 2025-02-26 | 2025-03-08 | 68
CPL-4-CRMN-3520 | Trench Excavation | 6 | 6 | 2025-01-18 | 2025-01-24 | 2025-02-26 | 2025-03-05 | 15
CPL-4-CRMN-3530 | Bedding | 1 | 1 | 2025-01-24 | 2025-01-24 | 2025-03-03 | 2025-03-05 | 17
CPL-4-CRMN-3540 | Lowering | 1 | 1 | 2025-01-25 | 2025-01-25 | 2025-03-05 | 2025-03-06 | 17
CPL-4-CRMN-3550 | Section Tie-in Joint | 1 | 1 | 2025-01-25 | 2025-01-25 | 2025-03-05 | 2025-03-06 | 68
CPL-4-CRMN-3560 | Field Joint Protection Sleeve | 1 | 1 | 2025-01-25 | 2025-01-25 | 2025-03-05 | 2025-03-06 | 68
CPL-4-CRMN-3570 | Padding | 1 | 1 | 2025-01-27 | 2025-01-27 | 2025-03-07 | 2025-03-08 | 68
Crossing Mechanical @ KP 1+772 (RX-02) |  | 5 | 5 | 2025-01-25 | 2025-01-30 | 2025-03-05 | 2025-03-12 | 15
CPL-4-CRMN-3580 | Trench Excavation | 3 | 3 | 2025-01-25 | 2025-01-28 | 2025-03-05 | 2025-03-09 | 15
CPL-4-CRMN-3590 | Bedding | 1 | 1 | 2025-01-28 | 2025-01-28 | 2025-03-08 | 2025-03-09 | 15
CPL-4-CRMN-3600 | Lowering | 1 | 1 | 2025-01-29 | 2025-01-29 | 2025-03-09 | 2025-03-11 | 15
CPL-4-CRMN-3610 | Section Tie-in Joint | 1 | 1 | 2025-01-29 | 2025-01-29 | 2025-03-09 | 2025-03-11 | 15
CPL-4-CRMN-3620 | Field Joint Protection Sleeve | 1 | 1 | 2025-01-29 | 2025-01-29 | 2025-03-09 | 2025-03-11 | 15
CPL-4-CRMN-3630 | Padding | 1 | 1 | 2025-01-30 | 2025-01-30 | 2025-03-11 | 2025-03-12 | 15
Hydrotesting |  | 6 | 6 | 2025-02-25 | 2025-03-03 | 2025-04-10 | 2025-04-17 | 55
C-4W-SVHG-PIPEL-7400 | Cleaning & Gauging | 1 | 1 | 2025-02-25 | 2025-02-25 | 2025-04-10 | 2025-04-11 | 55
C-4W-SVHG-PIPEL-7410 | Water Filling | 1 | 1 | 2025-02-26 | 2025-02-26 | 2025-04-11 | 2025-04-12 | 55
C-4W-SVHG-PIPEL-7420 | Pressurization | 1 | 1 | 2025-02-27 | 2025-02-27 | 2025-04-12 | 2025-04-14 | 55
C-4W-SVHG-PIPEL-7430 | Holding of Test Pressure | 1 | 1 | 2025-02-28 | 2025-02-28 | 2025-04-14 | 2025-04-15 | 55
C-4W-SVHG-PIPEL-7600 | De-Pressurization | 1 | 1 | 2025-03-01 | 2025-03-01 | 2025-04-15 | 2025-04-16 | 55
C-4W-SVHG-PIPEL-7610 | De-watering | 1 | 1 | 2025-03-02 | 2025-03-03 | 2025-04-16 | 2025-04-17 | 55
Berm Construction |  | 8 | 8 | 2025-02-15 | 2025-02-24 | 2025-03-28 | 2025-04-10 | 55
C-4W-SVHG-PIPEL-6800 | Gatch Laying & Levelling | 5 | 5 | 2025-02-15 | 2025-02-20 | 2025-03-28 | 2025-04-07 | 55
C-4W-SVHG-PIPEL-6810 | Gatch Compaction | 6 | 6 | 2025-02-18 | 2025-02-24 | 2025-04-03 | 2025-04-10 | 55
Marker Post & Crash Barrier |  | 3 | 3 | 2025-02-25 | 2025-02-27 | 2025-04-10 | 2025-04-14 | 104
C-4W-SVHG-PIPEL-7800 | Installation of Marker Post/Sign Board | 1 | 1 | 2025-02-25 | 2025-02-25 | 2025-04-10 | 2025-04-11 | 104
C-4W-SVHG-PIPEL-7810 | Installation of Crash Barriers (If any) | 2 | 2 | 2025-02-26 | 2025-02-27 | 2025-04-11 | 2025-04-14 | 104
Existing 081-SV-03 |  | 72 | 72 | 2025-01-31 | 2025-05-15 | 2025-03-13 | 2025-06-16 | 58
Existing 081-SV-1 |  | 72 | 72 | 2025-01-31 | 2025-05-15 | 2025-03-13 | 2025-06-16 | 58
Civil Works |  | 72 | 72 | 2025-01-31 | 2025-05-15 | 2025-03-13 | 2025-06-16 | 21
Demolition Works (Paving)CCOSV3CS10 |  | 14 | 14 | 2025-01-31 | 2025-02-20 | 2025-03-13 | 2025-04-05 | 15
C-4W-081-03-CI-0100 | Demolition Works (Paving) | 14 | 14 | 2025-01-31 | 2025-02-20 | 2025-03-13 | 2025-04-05 | 15
Concrete Works (Foundations for Equipment & Pipe Supports)CCOSV3CS11 |  | 14 | 14 | 2025-02-21 | 2025-03-17 | 2025-04-05 | 2025-04-22 | 15
C-4W-081-03-CI-1400 | Concrete Works (Foundations for Equipment & Pipe Supports) | 14 | 14 | 2025-02-21 | 2025-03-17 | 2025-04-05 | 2025-04-22 | 15
Concrete ProtectionCCOSV3CS12 |  | 33 | 33 | 2025-03-17 | 2025-05-01 | 2025-04-22 | 2025-05-31 | 15
C-4W-081-03-CI-1700 | Concrete Protection | 33 | 33 | 2025-03-17 | 2025-05-01 | 2025-04-22 | 2025-05-31 | 15
Paving WorksCCOSV3CS14 |  | 11 | 11 | 2025-05-01 | 2025-05-15 | 2025-05-31 | 2025-06-16 | 21
C-4W-081-03-CI-2600 | Paving Works | 11 | 11 | 2025-05-01 | 2025-05-15 | 2025-05-31 | 2025-06-16 | 21
Piping Works |  | 9 | 9 | 2025-05-01 | 2025-05-13 | 2025-05-31 | 2025-06-13 | 18
Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 |  | 9 | 9 | 2025-05-01 | 2025-05-13 | 2025-05-31 | 2025-06-13 | 18
C-4W-081-03-PI-1000 | Piping Works (RTP) | 9 | 9 | 2025-05-01 | 2025-05-13 | 2025-05-31 | 2025-06-13 | 18
Tie-In Works |  | 2 | 2 | 2025-05-13 | 2025-05-15 | 2025-06-13 | 2025-06-16 | 58
Tie - in (4'' Tie-in Connection Water Line)CCOSV3PI51 |  | 2 | 2 | 2025-05-13 | 2025-05-15 | 2025-06-13 | 2025-06-16 | 58
C-4W-081-03-PI-3000 | Tie - in (4'' Tie-in Connection Water Line) | 2 | 2 | 2025-05-13 | 2025-05-15 | 2025-06-13 | 2025-06-16 | 58
HGCP Connection (4'' Tie-in Connection Water Line) |  | 96 | 96 | 2025-02-21 | 2025-07-14 | 2025-04-05 | 2025-07-31 | 21
HGCP Connection (4" Tie-in Connection Water Line) |  | 96 | 96 | 2025-02-21 | 2025-07-14 | 2025-04-05 | 2025-07-31 | 21
Civil Works |  | 96 | 96 | 2025-02-21 | 2025-07-14 | 2025-04-05 | 2025-07-31 | 21
Demolition Works (Paving & Fence)CCOH4WCS20 |  | 6 | 6 | 2025-02-21 | 2025-02-27 | 2025-04-05 | 2025-04-12 | 29
C-4W-TI-CI-1000 | Demolition Works (Paving & Fence) | 6 | 6 | 2025-02-21 | 2025-02-27 | 2025-04-05 | 2025-04-12 | 29
Concrete Works (Foundations for Equipment & Pipe Supports)CCOH4WCS21 |  | 25 | 25 | 2025-03-17 | 2025-05-13 | 2025-04-22 | 2025-05-22 | 21
C-4W-TI-CI-1400 | Concrete Works (Foundations for Equipment & Pipe Supports) | 25 | 25 | 2025-03-17 | 2025-05-13 | 2025-04-22 | 2025-05-22 | 21
Fences & Gates ConstructionCCOH4WCS24 |  | 20 | 20 | 2025-05-15 | 2025-06-21 | 2025-06-16 | 2025-07-10 | 21
C-4W-TI-CI-2220 | Fences & Gates Construction | 20 | 20 | 2025-05-15 | 2025-06-21 | 2025-06-16 | 2025-07-10 | 21
Concrete ProtectionCCOH4WCS23 |  | 18 | 18 | 2025-05-13 | 2025-06-03 | 2025-05-31 | 2025-06-24 | 15
C-4W-TI-CI-1700 | Concrete Protection | 18 | 18 | 2025-05-13 | 2025-06-03 | 2025-05-31 | 2025-06-24 | 15
Paving WorksCCOH4WCS25 |  | 18 | 18 | 2025-06-21 | 2025-07-14 | 2025-07-10 | 2025-07-31 | 21
C-4W-TI-CI-2600 | Paving Works | 18 | 18 | 2025-06-21 | 2025-07-14 | 2025-07-10 | 2025-07-31 | 21
Piping Works |  | 24 | 24 | 2025-05-13 | 2025-06-23 | 2025-06-13 | 2025-07-12 | 36
Piping Pre-FabricationCCOH4WPI050 |  | 6 | 6 | 2025-05-13 | 2025-05-20 | 2025-06-13 | 2025-06-20 | 18
C-4W-TI-PI-1000 | Piping Pre-Fabrication | 6 | 6 | 2025-05-13 | 2025-05-20 | 2025-06-13 | 2025-06-20 | 18
ErectionCCOH4WPI060 |  | 6 | 6 | 2025-06-03 | 2025-06-12 | 2025-06-24 | 2025-07-02 | 15
C-4W-TI-PI-1200 | Piping Installation | 6 | 6 | 2025-06-03 | 2025-06-12 | 2025-06-24 | 2025-07-02 | 15
Field Joint Welding, NDT & CoatingCCOH4WPI070 |  | 6 | 6 | 2025-06-12 | 2025-06-19 | 2025-07-02 | 2025-07-09 | 36
C-4W-TI-PI-1400 | Field Joining | 6 | 6 | 2025-06-12 | 2025-06-19 | 2025-07-02 | 2025-07-09 | 36
HydrotestingCCOH4WPI080 |  | 2 | 2 | 2025-06-19 | 2025-06-21 | 2025-07-09 | 2025-07-11 | 36
C-4W-TI-PI-1600 | Hydrotesting | 2 | 2 | 2025-06-19 | 2025-06-21 | 2025-07-09 | 2025-07-11 | 36
Installation of ValvesCCOH4WPI090 |  | 1 | 1 | 2025-06-21 | 2025-06-23 | 2025-07-11 | 2025-07-12 | 36
C-4W-TI-PI-1800 | Installation of Valves | 1 | 1 | 2025-06-21 | 2025-06-23 | 2025-07-11 | 2025-07-12 | 36
Final Bolt Torquing/ Re-InstatementCCOH4WPI100 |  | 1 | 1 | 2025-06-21 | 2025-06-23 | 2025-07-11 | 2025-07-12 | 36
C-4W-TI-PI-2000 | Final Bolt Torquing/ Re-Instatement | 1 | 1 | 2025-06-21 | 2025-06-23 | 2025-07-11 | 2025-07-12 | 36
Tie-In Works |  | 1 | 1 | 2025-06-23 | 2025-06-24 | 2025-07-12 | 2025-07-14 | 36
Tie - in (4'' Tie-in Connection Water Line)CCOH4WTI50 |  | 1 | 1 | 2025-06-23 | 2025-06-24 | 2025-07-12 | 2025-07-14 | 36
C-4W-TI-3000 | Tie - in (4'' Tie-in Connection Water Line) | 1 | 1 | 2025-06-23 | 2025-06-24 | 2025-07-12 | 2025-07-14 | 36
Dolphin Existing BVS -06 |  | 43 | 43 | 2025-05-13 | 2025-08-06 | 2025-05-22 | 2025-07-15 | 55
Dolphin Existing BVS -1 |  | 43 | 43 | 2025-05-13 | 2025-08-06 | 2025-05-22 | 2025-07-15 | 55
Civil Works |  | 40 | 40 | 2025-05-13 | 2025-08-06 | 2025-05-22 | 2025-07-11 | 58
Trenching for CablesCCOB6C32 |  | 28 | 28 | 2025-05-13 | 2025-06-17 | 2025-05-22 | 2025-06-26 | 21
C-DBV6-CI-1800 | Electrical & Earthing Cable Trenching | 14 | 14 | 2025-05-13 | 2025-05-29 | 2025-05-22 | 2025-06-10 | 21
C-DBV6-CI-1810 | Instrument & Telecom Cable Trenching | 14 | 14 | 2025-05-29 | 2025-06-17 | 2025-06-10 | 2025-06-26 | 21
Backfilling for CablesCCOB6C33 |  | 15 | 15 | 2025-06-24 | 2025-08-06 | 2025-06-23 | 2025-07-11 | 58
C-DBV6-CI-2800 | Back Filling for Electrical & Earthing Cable | 6 | 6 | 2025-07-31 | 2025-08-06 | 2025-06-23 | 2025-07-01 | 67
C-DBV6-CI-2810 | Back Filling for Instrument & Telecom Cable | 6 | 6 | 2025-06-24 | 2025-07-02 | 2025-07-04 | 2025-07-11 | 58
Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 |  | 4 | 4 | 2025-06-12 | 2025-06-17 | 2025-07-02 | 2025-07-07 | 15
C-DBV6-PI-1000 | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | 4 | 4 | 2025-06-12 | 2025-06-17 | 2025-07-02 | 2025-07-07 | 15
Shelter InstallationCCOB6S10 |  | 4 | 4 | 2025-06-17 | 2025-06-21 | 2025-07-07 | 2025-07-11 | 15
C-DBV6-CI-5000 | Shelter Installation | 4 | 4 | 2025-06-17 | 2025-06-21 | 2025-07-07 | 2025-07-11 | 15
Electrical & Instrumentation Works |  | 29 | 29 | 2025-06-17 | 2025-07-28 | 2025-06-10 | 2025-07-15 | 15
Electrical & Instrumentation WorksCCOB6E10 |  | 29 | 29 | 2025-06-17 | 2025-07-28 | 2025-06-10 | 2025-07-15 | 15
C-DBV6-EI-2000 | Electrical & Earthing Cable Laying | 6 | 6 | 2025-07-18 | 2025-07-24 | 2025-06-10 | 2025-06-17 | 35
C-DBV6-EI-2010 | Instrument Cable Laying | 6 | 6 | 2025-06-17 | 2025-06-24 | 2025-06-26 | 2025-07-04 | 21
C-DBV6-EI-2500 | Installation of H2S Analyser | 3 | 3 | 2025-07-25 | 2025-07-28 | 2025-07-11 | 2025-07-15 | 15
Unit - 800 (Existing / New MAQTA Control Building) |  | 40 | 40 | 2025-07-29 | 2025-09-20 | 2025-07-15 | 2025-08-30 | 15
Unit - 800 (Existing / New MAQTA Control Building)-1 |  | 40 | 40 | 2025-07-29 | 2025-09-20 | 2025-07-15 | 2025-08-30 | 15
Electrical & Instrumentation Works |  | 36 | 36 | 2025-07-29 | 2025-09-16 | 2025-07-15 | 2025-08-26 | 19
Electrical & Instrumentation Works (ICSS, Feeder, FO Board...)CCOU800EL1 |  | 6 | 6 | 2025-07-29 | 2025-08-04 | 2025-07-15 | 2025-07-22 | 19
C-MAQTA-EI-1000 | Electrical & Instrumentation Works (ICSS, Feeder, FO Board...) | 6 | 6 | 2025-07-29 | 2025-08-04 | 2025-07-15 | 2025-07-22 | 19
Cable Laying and TerminationCCOU800EL2 |  | 36 | 36 | 2025-07-30 | 2025-09-16 | 2025-07-15 | 2025-08-26 | 19
C-MAQTA-CI-1800 | LV Cable Trenching | 10 | 10 | 2025-07-30 | 2025-08-09 | 2025-07-15 | 2025-07-26 | 15
C-MAQTA-EI-2000 | LV Cable Laying | 6 | 6 | 2025-08-11 | 2025-08-16 | 2025-07-26 | 2025-08-02 | 24
C-MAQTA-CI-1810 | Instrument Trenching | 9 | 9 | 2025-08-11 | 2025-08-26 | 2025-07-26 | 2025-08-06 | 15
C-MAQTA-EI-2010 | Instrument Cable Laying | 6 | 6 | 2025-08-27 | 2025-09-02 | 2025-08-06 | 2025-08-13 | 15
C-MAQTA-CI-2800 | Back Filling for LV Cable | 6 | 6 | 2025-08-23 | 2025-08-29 | 2025-08-08 | 2025-08-15 | 28
C-MAQTA-EI-2050 | Glanding & Termination | 3 | 3 | 2025-09-03 | 2025-09-06 | 2025-08-13 | 2025-08-16 | 15
C-MAQTA-CI-2810 | Back Filling for Instrument Cable | 6 | 6 | 2025-09-10 | 2025-09-16 | 2025-08-19 | 2025-08-26 | 19
Telecommunication Works |  | 10 | 10 | 2025-09-04 | 2025-09-16 | 2025-08-14 | 2025-08-26 | 15
Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 |  | 10 | 10 | 2025-09-04 | 2025-09-16 | 2025-08-14 | 2025-08-26 | 15
C-MAQTA-TE-1020 | Installation PIDS S/m | 6 | 6 | 2025-09-08 | 2025-09-13 | 2025-08-16 | 2025-08-23 | 15
C-MAQTA-TE-1000 | SCADA S/m Modification | 10 | 10 | 2025-09-04 | 2025-09-16 | 2025-08-14 | 2025-08-26 | 15
C-MAQTA-TE-1010 | Telecom S/m Modification | 10 | 10 | 2025-09-04 | 2025-09-16 | 2025-08-14 | 2025-08-26 | 15
ShutdownCCOU800ST4 |  | 4 | 4 | 2025-09-17 | 2025-09-20 | 2025-08-26 | 2025-08-30 | 15
C-MAQTA-EL-2000 | Shutdown | 4 | 4 | 2025-09-17 | 2025-09-20 | 2025-08-26 | 2025-08-30 | 15
Habshan CR-541 (back-up) Control Room |  | 37 | 37 | 2025-08-04 | 2025-09-16 | 2025-07-15 | 2025-08-27 | 18
Habshan CR-541 (back-up) Control Room-1 |  | 37 | 37 | 2025-08-04 | 2025-09-16 | 2025-07-15 | 2025-08-27 | 18
Electrical & Instrumentation Works |  | 32 | 32 | 2025-08-04 | 2025-09-10 | 2025-07-15 | 2025-08-21 | 23
Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 |  | 32 | 32 | 2025-08-04 | 2025-09-10 | 2025-07-15 | 2025-08-21 | 23
C-541CR-CI-1000 | LV Cable Trenching | 8 | 8 | 2025-08-04 | 2025-08-12 | 2025-07-15 | 2025-07-24 | 16
C-541CR-EI-1000 | LV Cable Laying | 5 | 5 | 2025-08-13 | 2025-08-18 | 2025-07-24 | 2025-07-30 | 26
C-541CR-CI-1010 | Instrument Trenching | 8 | 8 | 2025-08-13 | 2025-08-21 | 2025-07-24 | 2025-08-02 | 16
C-541CR-CI-1020 | Back Filling for LV Cable | 3 | 3 | 2025-08-25 | 2025-08-27 | 2025-08-05 | 2025-08-08 | 34
C-541CR-EI-1010 | Instrument Cable Laying | 5 | 5 | 2025-08-22 | 2025-08-27 | 2025-08-02 | 2025-08-08 | 18
C-541CR-EI-1020 | Installation of RTU | 3 | 3 | 2025-08-28 | 2025-08-30 | 2025-08-08 | 2025-08-12 | 18
C-541CR-CI-1030 | Back Filling for Instrument Cable | 3 | 3 | 2025-09-03 | 2025-09-06 | 2025-08-14 | 2025-08-18 | 26
C-541CR-EI-1030 | Electrical & Instrumentation Works (UPS Feeder Installation) | 5 | 5 | 2025-09-01 | 2025-09-06 | 2025-08-12 | 2025-08-18 | 18
C-541CR-EI-1040 | Glanding & Termination | 3 | 3 | 2025-09-08 | 2025-09-10 | 2025-08-18 | 2025-08-21 | 18
Telecommunication Works |  | 5 | 5 | 2025-09-11 | 2025-09-16 | 2025-08-21 | 2025-08-27 | 18
Control System Modifications and Telecommunication WorksCCOC541IC2 |  | 5 | 5 | 2025-09-11 | 2025-09-16 | 2025-08-21 | 2025-08-27 | 18
C-541CR-TE-1000 | Telecommunication Works (Modification of Existing Telecom Cabinet) | 5 | 5 | 2025-09-11 | 2025-09-16 | 2025-08-21 | 2025-08-27 | 18
Unit 577 - 577-SV-02 & 577-SV-03 |  | 12 | 12 | 2025-08-28 | 2025-09-11 | 2025-08-08 | 2025-08-22 | 22
Unit 577 - 577-SV-02 & 577-SV-1 |  | 12 | 12 | 2025-08-28 | 2025-09-11 | 2025-08-08 | 2025-08-22 | 22
Civil Works |  | 12 | 12 | 2025-08-28 | 2025-09-11 | 2025-08-08 | 2025-08-22 | 22
Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB BuildingCCOU577CS5 |  | 4 | 4 | 2025-08-28 | 2025-09-01 | 2025-08-08 | 2025-08-13 | 16
C-577-CI-1000 | Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB Building | 4 | 4 | 2025-08-28 | 2025-09-01 | 2025-08-08 | 2025-08-13 | 16
Backfilling - 577-SV-02 Passive cooling Shelter to HGCP - MCB BuildingCCOU57CS10 |  | 4 | 4 | 2025-09-08 | 2025-09-11 | 2025-08-18 | 2025-08-22 | 22
C-577-CI-1010 | Backfilling - 577-SV-02 Passive cooling Shelter to HGCP - MCB Building | 4 | 4 | 2025-09-08 | 2025-09-11 | 2025-08-18 | 2025-08-22 | 22
Telecommunication Works |  | 4 | 4 | 2025-09-02 | 2025-09-06 | 2025-08-13 | 2025-08-18 | 22
Telecommunication Works (new telecom cabinet and cable laying and terminations)CCOU577IC1 |  | 4 | 4 | 2025-09-02 | 2025-09-06 | 2025-08-13 | 2025-08-18 | 22
C-577-TE-1000 | Telecommunication Works (new telecom cabinet and cable laying and terminations) | 4 | 4 | 2025-09-02 | 2025-09-06 | 2025-08-13 | 2025-08-18 | 22
Unit - 601 (Thammama-C Manifold) |  | 18 | 18 | 2025-08-28 | 2025-09-18 | 2025-08-08 | 2025-08-29 | 16
Unit - 601 (Thammama-C Manifold)-1 |  | 18 | 18 | 2025-08-28 | 2025-09-18 | 2025-08-08 | 2025-08-29 | 16
Civil Works |  | 18 | 18 | 2025-08-28 | 2025-09-18 | 2025-08-08 | 2025-08-29 | 16
Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS1 |  | 6 | 6 | 2025-08-28 | 2025-09-03 | 2025-08-08 | 2025-08-15 | 16
C-601-CI-1000 | Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603) | 6 | 6 | 2025-08-28 | 2025-09-03 | 2025-08-08 | 2025-08-15 | 16
Backfilling - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS2 |  | 6 | 6 | 2025-09-12 | 2025-09-18 | 2025-08-22 | 2025-08-29 | 16
C-601-CI-1010 | Backfilling - Tahammama-C E&I Building to Launcher Station (607-V-603) | 6 | 6 | 2025-09-12 | 2025-09-18 | 2025-08-22 | 2025-08-29 | 16
Telecommunication Works |  | 6 | 6 | 2025-09-04 | 2025-09-11 | 2025-08-15 | 2025-08-22 | 16
Telecommunication Works (modifications of existing telecom cabinet)CCOU601IC1 |  | 6 | 6 | 2025-09-04 | 2025-09-11 | 2025-08-15 | 2025-08-22 | 16
C-601-TE-1000 | Telecommunication Works (modifications of existing telecom cabinet) | 6 | 6 | 2025-09-04 | 2025-09-11 | 2025-08-15 | 2025-08-22 | 16
Precommissioning |  | 289 | 289 | 2025-02-15 | 2025-11-09 | 2024-11-12 | 2025-11-03 | 7
Habshan Complex to 56” P/L Fac. (56”) |  | 20 | 20 | 2025-08-09 | 2025-09-23 | 2025-09-04 | 2025-09-29 | 19
Pig Launcher 607-V-603 (56'' Pipeline) |  | 18 | 18 | 2025-09-01 | 2025-09-23 | 2025-09-06 | 2025-09-27 | 21
Pig Launcher 607-V-603 (56'' Pipeline)-1 |  | 18 | 18 | 2025-09-01 | 2025-09-23 | 2025-09-06 | 2025-09-27 | 21
PrecommissioningCPC-HBS500 |  | 18 | 18 | 2025-09-01 | 2025-09-23 | 2025-09-06 | 2025-09-27 | 21
PRECOM-56-PL-1000 | Precommissioning | 18 | 18 | 2025-09-01 | 2025-09-23 | 2025-09-06 | 2025-09-27 | 21
Electrical Building Type II |  | 18 | 18 | 2025-08-27 | 2025-09-18 | 2025-09-04 | 2025-09-26 | 22
Electrical Building Type II-1 |  | 18 | 18 | 2025-08-27 | 2025-09-18 | 2025-09-04 | 2025-09-26 | 22
PrecommissioningCPC-HBS501 |  | 18 | 18 | 2025-08-27 | 2025-09-18 | 2025-09-04 | 2025-09-26 | 22
PRECOM-56-EB2-1000 | Precommissioning | 18 | 18 | 2025-08-27 | 2025-09-18 | 2025-09-04 | 2025-09-26 | 22
Gas Source Tie-ins to 56'' P/L Station (0.2 Km) (Hot Tap) |  | 12 | 12 | 2025-08-09 | 2025-08-23 | 2025-09-15 | 2025-09-29 | 19
Gas Source Tie-ins to 56'' P/L Station (0.2 Km) (Hot Tap)-1 |  | 12 | 12 | 2025-08-09 | 2025-08-23 | 2025-09-15 | 2025-09-29 | 19
PrecommissioningCPC-HBS502 |  | 12 | 12 | 2025-08-09 | 2025-08-23 | 2025-09-15 | 2025-09-29 | 19
PRECOM-56-G-1000 | Precommissioning | 12 | 12 | 2025-08-09 | 2025-08-23 | 2025-09-15 | 2025-09-29 | 19
56” P/L Facility to HGCP 56” P/R (56”) |  | 106 | 106 | 2025-05-26 | 2025-10-09 | 2025-06-03 | 2025-10-09 | 10
591-BVS-01 (56'' Pipeline) |  | 16 | 16 | 2025-09-10 | 2025-10-01 | 2025-09-20 | 2025-10-09 | 11
591-BVS-01 (56'' Pipeline)-1 |  | 16 | 16 | 2025-09-10 | 2025-10-01 | 2025-09-20 | 2025-10-09 | 11
PrecommissioningCPCB15610 |  | 16 | 16 | 2025-09-10 | 2025-10-01 | 2025-09-20 | 2025-10-09 | 11
PRECOM-56-59101-1000 | Precommissioning | 16 | 16 | 2025-09-10 | 2025-10-01 | 2025-09-20 | 2025-10-09 | 11
Pig Receiver 838-V-601 (56'' Pipeline) |  | 19 | 19 | 2025-09-03 | 2025-09-25 | 2025-09-17 | 2025-10-09 | 11
Pig Receiver 838-V-601 (56'' Pipeline)-1 |  | 19 | 19 | 2025-09-03 | 2025-09-25 | 2025-09-17 | 2025-10-09 | 11
PrecommissioningCPCHGCP561 |  | 19 | 19 | 2025-09-03 | 2025-09-25 | 2025-09-17 | 2025-10-09 | 11
PRECOM-56-PR-1000 | Precommissioning | 19 | 19 | 2025-09-03 | 2025-09-25 | 2025-09-17 | 2025-10-09 | 11
56 '' Pipeline from Habshan Complex to HGCP |  | 106 | 106 | 2025-05-26 | 2025-10-09 | 2025-06-03 | 2025-10-09 | 10
56” Pipeline from Habshan Complex to HGCP (30.5km) |  | 106 | 106 | 2025-05-26 | 2025-10-09 | 2025-06-03 | 2025-10-09 | 10
Pre-commissioningCPCPL56228 |  | 106 | 106 | 2025-05-26 | 2025-10-09 | 2025-06-03 | 2025-10-09 | 10
PRECOM-56-HGHC-1000 | Precommissioning | 19 | 19 | 2025-09-04 | 2025-10-09 | 2025-09-17 | 2025-10-09 | 10
Evaporation PondCCOPL56239 |  | 30 | 30 | 2025-06-07 | 2025-07-14 | 2025-06-13 | 2025-07-19 | 34
C-56-01HG-PL-CI-7200 | Evaporation Pond | 30 | 30 | 2025-06-07 | 2025-07-14 | 2025-06-13 | 2025-07-19 | 34
Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 |  | 30 | 30 | 2025-07-14 | 2025-08-18 | 2025-08-02 | 2025-09-08 | 10
C-56-01HG-PL-ME-7400 | Cleaning & Gauging | 12 | 12 | 2025-07-14 | 2025-07-28 | 2025-08-02 | 2025-08-16 | 10
C-56-01HG-PL-ME-7410 | Water Filling | 10 | 10 | 2025-07-28 | 2025-08-08 | 2025-08-16 | 2025-08-28 | 10
C-56-01HG-PL-ME-7420 | Stabilization & Pressurization | 7 | 7 | 2025-08-08 | 2025-08-16 | 2025-08-28 | 2025-09-06 | 10
C-56-01HG-PL-ME-7430 | Holding of Test Pressure | 1 | 1 | 2025-08-16 | 2025-08-18 | 2025-09-06 | 2025-09-08 | 10
Dewatering, Swabbing, & DryingCCOPL56235 |  | 8 | 8 | 2025-08-18 | 2025-09-04 | 2025-09-08 | 2025-09-17 | 10
C-56-01HG-PL-ME-7600 | De-Pressurization | 3 | 3 | 2025-08-18 | 2025-08-21 | 2025-09-08 | 2025-09-11 | 10
C-56-01HG-PL-ME-7610 | De-watering | 3 | 3 | 2025-08-21 | 2025-08-29 | 2025-09-10 | 2025-09-13 | 10
C-56-01HG-PL-ME-7620 | Swabing & Drying (Upto Dew Point Temp.) | 5 | 5 | 2025-08-29 | 2025-09-04 | 2025-09-11 | 2025-09-17 | 10
ROW Restoration/Marker Post/Crash BarrierCCOPL56229 |  | 52 | 52 | 2025-05-26 | 2025-07-29 | 2025-06-03 | 2025-08-06 | 45
C-56-01HG-PL-CI-7800 | ROW Restoration/ Installation of Marker Post/Sign Board | 51 | 51 | 2025-05-26 | 2025-07-28 | 2025-06-03 | 2025-08-05 | 45
C-56-01HG-PL-CI-7810 | Installation of Crash Barriers (If any) | 51 | 51 | 2025-05-27 | 2025-07-29 | 2025-06-04 | 2025-08-06 | 45
Evaporation PondCCOPL56225 |  | 30 | 30 | 2025-06-17 | 2025-07-23 | 2025-06-30 | 2025-08-02 | 22
C-56-HC01-PL-CI-7200 | Evaporation Pond | 30 | 30 | 2025-06-17 | 2025-07-23 | 2025-06-30 | 2025-08-02 | 22
Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 |  | 27 | 27 | 2025-07-24 | 2025-08-22 | 2025-08-02 | 2025-09-03 | 10
C-56-HC01-PL-ME-7400 | Cleaning & Gauging | 12 | 12 | 2025-07-24 | 2025-08-05 | 2025-08-02 | 2025-08-16 | 10
C-56-HC01-PL-ME-7410 | Water Filling | 9 | 9 | 2025-08-05 | 2025-08-15 | 2025-08-16 | 2025-08-27 | 10
C-56-HC01-PL-ME-7420 | Stabilization & Pressurization | 5 | 5 | 2025-08-15 | 2025-08-21 | 2025-08-27 | 2025-09-02 | 10
C-56-HC01-PL-ME-7430 | Holding of Test Pressure | 1 | 1 | 2025-08-21 | 2025-08-22 | 2025-09-02 | 2025-09-03 | 10
Dewatering, Swabbing, & DryingCCOPL56227 |  | 11 | 11 | 2025-08-22 | 2025-09-04 | 2025-09-03 | 2025-09-17 | 10
C-56-HC01-PL-ME-7600 | De-Pressurization | 3 | 3 | 2025-08-22 | 2025-08-26 | 2025-09-03 | 2025-09-08 | 10
C-56-HC01-PL-ME-7610 | De-watering | 4 | 4 | 2025-08-26 | 2025-08-30 | 2025-09-08 | 2025-09-12 | 10
C-56-HC01-PL-ME-7620 | Swabing & Drying (Upto Dew Point Temp.) | 4 | 4 | 2025-08-30 | 2025-09-04 | 2025-09-12 | 2025-09-17 | 10
HGCP 52” P/L to Sweihan CRS 52” P/R (52”) |  | 289 | 289 | 2025-02-15 | 2025-11-09 | 2024-11-12 | 2025-11-03 | 7
52” Pipeline from HGCP Compressor Station to BVS-01 at KP 33.4 |  | 289 | 289 | 2025-02-15 | 2025-11-04 | 2024-11-12 | 2025-11-03 | 5
52”x 33.4 Km Pipeline from BVS-01 at KP 33.4 to HGCP Compressor Station |  | 289 | 289 | 2025-02-15 | 2025-11-04 | 2024-11-12 | 2025-11-03 | 5
Precommissioning Pig Launcher 838-V-602CPCHGCP521 |  | 17 | 17 | 2025-09-20 | 2025-10-11 | 2025-10-14 | 2025-11-03 | 5
PRECOM-52-PL-1000 | Precommissioning Pig Launcher 838-V-602 | 17 | 17 | 2025-09-20 | 2025-10-11 | 2025-10-14 | 2025-11-03 | 5
Pre-commissioning from HGCP to BVS-01CPCPL52327.7 |  | 183 | 183 | 2025-02-15 | 2025-11-04 | 2024-11-12 | 2025-07-01 | 107
PRECOM-52-HG01-1000 | Pre-commissioning from HGCP to BVS-01 | 12 | 12 | 2025-10-21 | 2025-11-04 | 2025-06-16 | 2025-07-01 | 107
Evaporation PondCCOPL52319 |  | 30 | 30 | 2025-04-17 | 2025-06-12 | 2024-11-12 | 2024-12-18 | 94
C-52-HG01-PL-CI-7200 | Evaporation Pond | 30 | 30 | 2025-04-17 | 2025-06-12 | 2024-11-12 | 2024-12-18 | 94
Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 |  | 129 | 129 | 2025-07-12 | 2025-08-18 | 2024-12-16 | 2025-05-27 | 107
C-52-HG01-PL-ME-7400 | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | 114 | 114 | 2025-07-12 | 2025-07-29 | 2024-12-16 | 2025-05-09 | 107
C-52-HG01-PL-ME-7410 | Water Filling | 114 | 114 | 2025-07-29 | 2025-08-09 | 2024-12-21 | 2025-05-15 | 107
C-52-HG01-PL-ME-7420 | Stabilization & Pressurization | 114 | 114 | 2025-08-09 | 2025-08-16 | 2024-12-27 | 2025-05-21 | 107
C-52-HG01-PL-ME-7430 | Holding of Test Pressure | 114 | 114 | 2025-08-16 | 2025-08-18 | 2025-01-03 | 2025-05-27 | 107
Dewatering, Swabbing, & DryingCCOPL52326 |  | 124 | 124 | 2025-08-18 | 2025-09-03 | 2025-01-09 | 2025-06-16 | 107
C-52-HG01-PL-ME-7600 | De-Pressurization | 114 | 114 | 2025-08-18 | 2025-08-21 | 2025-01-09 | 2025-06-02 | 107
C-52-HG01-PL-ME-7610 | De-watering | 114 | 114 | 2025-08-21 | 2025-08-28 | 2025-01-15 | 2025-06-10 | 107
C-52-HG01-PL-ME-7620 | Swabing & Drying (Upto Dew Point Temp.) | 114 | 114 | 2025-08-28 | 2025-09-03 | 2025-01-21 | 2025-06-16 | 107
ROW Restoration from BVS-01 to HGCP/Marker PostCCOPL52324.1 |  | 75 | 75 | 2025-02-15 | 2025-06-02 | 2024-12-16 | 2025-03-17 | 125
C-52-HG01-PL-CI-7800 | Installation of Marker Post/Sign Board | 75 | 75 | 2025-02-15 | 2025-06-02 | 2024-12-16 | 2025-03-17 | 125
ROW Restoration from BVS-01 to HGCP/Crash BarrierCCOPL52324.2 |  | 75 | 75 | 2025-02-17 | 2025-06-03 | 2024-12-17 | 2025-03-18 | 125
C-52-HG01-PL-CI-7810 | Installation of Crash Barriers (If any) | 75 | 75 | 2025-02-17 | 2025-06-03 | 2024-12-17 | 2025-03-18 | 125
ROW Restoration from HGCP to KP 16.7 (Deleted SOW)CCOPL52324.3 |  | 75 | 75 | 2025-02-17 | 2025-06-03 | 2024-12-17 | 2025-03-18 | 125
C-52-HG01-PL-CI-7820 | Installation of Crash Barriers (If any) (Deleted SOW) | 75 | 75 | 2025-02-17 | 2025-06-03 | 2024-12-17 | 2025-03-18 | 125
52 Pipeline from BVS-01 to BVS-02 at KP 65.8 |  | 216 | 216 | 2025-04-05 | 2025-11-04 | 2024-12-26 | 2025-09-20 | 38
52”x 32.4 Km Pipeline from BVS-02 at KP 65.8 to BVS-01 |  | 216 | 216 | 2025-04-05 | 2025-11-04 | 2024-12-26 | 2025-09-20 | 38
Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 |  | 120 | 120 | 2025-04-05 | 2025-11-04 | 2024-12-26 | 2025-05-27 | 134
PRECOM-52-0201-1000 | Pre-commissioning from BVS-02 to BVS-01 | 11 | 11 | 2025-10-22 | 2025-11-04 | 2025-05-14 | 2025-05-27 | 134
Evaporation PondCCOPL52347 |  | 30 | 30 | 2025-04-05 | 2025-05-12 | 2024-12-26 | 2025-01-30 | 58
C-52-0102-PL-CI-7200 | Evaporation Pond | 30 | 30 | 2025-04-05 | 2025-05-12 | 2024-12-26 | 2025-01-30 | 58
Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 |  | 23 | 23 | 2025-08-14 | 2025-09-11 | 2025-03-28 | 2025-04-28 | 134
C-52-0102-PL-ME-7400 | Cleaning & Gauging | 10 | 10 | 2025-08-14 | 2025-08-26 | 2025-03-28 | 2025-04-12 | 134
C-52-0102-PL-ME-7410 | Water Filling | 7 | 7 | 2025-08-26 | 2025-09-03 | 2025-04-12 | 2025-04-21 | 134
C-52-0102-PL-ME-7420 | Stabilization & Pressurization | 5 | 5 | 2025-09-03 | 2025-09-10 | 2025-04-21 | 2025-04-26 | 134
C-52-0102-PL-ME-7430 | Holding of Test Pressure | 1 | 1 | 2025-09-10 | 2025-09-11 | 2025-04-26 | 2025-04-28 | 134
Dewatering, Swabbing, & DryingCCOPL52342 |  | 13 | 13 | 2025-09-11 | 2025-09-26 | 2025-04-28 | 2025-05-14 | 134
C-52-0102-PL-ME-7600 | De-Pressurization | 3 | 3 | 2025-09-11 | 2025-09-15 | 2025-04-28 | 2025-05-01 | 134
C-52-0102-PL-ME-7610 | De-watering | 5 | 5 | 2025-09-15 | 2025-09-20 | 2025-05-01 | 2025-05-08 | 134
C-52-0102-PL-ME-7620 | Swabing & Drying (Upto Dew Point Temp.) | 5 | 5 | 2025-09-20 | 2025-09-26 | 2025-05-08 | 2025-05-14 | 134
Precommissioning BVS-1CPCB65211 |  | 21 | 21 | 2025-09-10 | 2025-10-04 | 2025-08-26 | 2025-09-20 | 27
PRECOM-56-59801-1000 | Precommissioning BVS-1 | 21 | 21 | 2025-09-10 | 2025-10-04 | 2025-08-26 | 2025-09-20 | 27
52” Pipeline from BVS-02 to BVS-03 at KP 81.8 |  | 213 | 213 | 2025-03-15 | 2025-10-18 | 2025-01-06 | 2025-09-26 | 22
52”x16.0 Km Pipeline from BVS-02 to BVS-03 at KP 81.8 |  | 213 | 213 | 2025-03-15 | 2025-10-18 | 2025-01-06 | 2025-09-26 | 22
Precommissioning BVS-2CPCB55210 |  | 21 | 21 | 2025-08-05 | 2025-08-29 | 2025-09-01 | 2025-09-26 | 22
PRECOM-56-59802-1000 | Precommissioning BVS-2 | 21 | 21 | 2025-08-05 | 2025-08-29 | 2025-09-01 | 2025-09-26 | 22
Pre-commissioning from BVS-02 to BVS-03CPCPL52327.5 |  | 75 | 75 | 2025-03-15 | 2025-10-18 | 2025-01-06 | 2025-04-12 | 109
PRECOM-52-0203-1000 | Pre-commissioning from BVS-02 to BVS-03 | 9 | 9 | 2025-10-08 | 2025-10-18 | 2025-03-29 | 2025-04-12 | 109
Evaporation PondCCOPL52375 |  | 30 | 30 | 2025-03-15 | 2025-04-26 | 2025-01-06 | 2025-02-08 | 109
C-52-0203-PL-CI-7200 | Evaporation Pond | 30 | 30 | 2025-03-15 | 2025-04-26 | 2025-01-06 | 2025-02-08 | 109
Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 |  | 23 | 23 | 2025-08-26 | 2025-09-23 | 2025-02-10 | 2025-03-09 | 109
C-52-0203-PL-ME-7400 | Cleaning & Gauging | 10 | 10 | 2025-08-26 | 2025-09-08 | 2025-02-10 | 2025-02-20 | 109
C-52-0203-PL-ME-7410 | Water Filling | 7 | 7 | 2025-09-08 | 2025-09-16 | 2025-02-21 | 2025-02-28 | 109
C-52-0203-PL-ME-7420 | Stabilization & Pressurization | 5 | 5 | 2025-09-16 | 2025-09-22 | 2025-03-01 | 2025-03-08 | 109
C-52-0203-PL-ME-7430 | Holding of Test Pressure | 1 | 1 | 2025-09-22 | 2025-09-23 | 2025-03-08 | 2025-03-09 | 109
Dewatering, Swabbing, & DryingCCOPL52370 |  | 13 | 13 | 2025-09-23 | 2025-10-08 | 2025-03-09 | 2025-03-29 | 109
C-52-0203-PL-ME-7600 | De-Pressurization | 3 | 3 | 2025-09-23 | 2025-09-26 | 2025-03-09 | 2025-03-14 | 109
C-52-0203-PL-ME-7610 | De-watering | 5 | 5 | 2025-09-26 | 2025-10-02 | 2025-03-14 | 2025-03-22 | 109
C-52-0203-PL-ME-7620 | Swabing & Drying (Upto Dew Point Temp.) | 5 | 5 | 2025-10-02 | 2025-10-08 | 2025-03-22 | 2025-03-29 | 109
52” Pipeline from BVS-03 to BVS-04 at KP 97.9 |  | 181 | 181 | 2025-05-24 | 2025-10-31 | 2025-03-09 | 2025-10-21 | 16
52”x16.1 Km Pipeline from BVS-03 to BVS-04 at KP 97.9 |  | 181 | 181 | 2025-05-24 | 2025-10-31 | 2025-03-09 | 2025-10-21 | 16
Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 |  | 18 | 18 | 2025-10-10 | 2025-10-31 | 2025-09-25 | 2025-10-16 | 20
PRECOM-52-IDS1-1000 | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | 18 | 18 | 2025-10-10 | 2025-10-31 | 2025-09-25 | 2025-10-16 | 20
Precommissioning BVS-3CPCB45210 |  | 21 | 21 | 2025-08-07 | 2025-09-01 | 2025-09-26 | 2025-10-21 | 16
PRECOM-56-59803-1000 | Precommissioning BVS-3 | 21 | 21 | 2025-08-07 | 2025-09-01 | 2025-09-26 | 2025-10-21 | 16
Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 |  | 74 | 74 | 2025-05-24 | 2025-10-29 | 2025-03-09 | 2025-06-16 | 119
PRECOM-52-0304-1000 | Pre-commissioning from BVS-03 to BVS-04 | 8 | 8 | 2025-10-20 | 2025-10-29 | 2025-06-04 | 2025-06-16 | 119
Evaporation PondCCOPL52403 |  | 30 | 30 | 2025-05-24 | 2025-07-02 | 2025-03-09 | 2025-04-22 | 119
C-52-0304-PL-CI-7200 | Evaporation Pond | 30 | 30 | 2025-05-24 | 2025-07-02 | 2025-03-09 | 2025-04-22 | 119
Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 |  | 23 | 23 | 2025-09-08 | 2025-10-04 | 2025-04-22 | 2025-05-20 | 119
C-52-0304-PL-ME-7400 | Cleaning & Gauging | 10 | 10 | 2025-09-08 | 2025-09-19 | 2025-04-22 | 2025-05-03 | 119
C-52-0304-PL-ME-7410 | Water Filling | 7 | 7 | 2025-09-19 | 2025-09-27 | 2025-05-03 | 2025-05-13 | 119
C-52-0304-PL-ME-7420 | Stabilization & Pressurization | 5 | 5 | 2025-09-27 | 2025-10-03 | 2025-05-13 | 2025-05-19 | 119
C-52-0304-PL-ME-7430 | Holding of Test Pressure | 1 | 1 | 2025-10-03 | 2025-10-04 | 2025-05-19 | 2025-05-20 | 119
Dewatering, Swabbing, & DryingCCOPL52398 |  | 13 | 13 | 2025-10-04 | 2025-10-20 | 2025-05-20 | 2025-06-04 | 119
C-52-0304-PL-ME-7600 | De-Pressurization | 3 | 3 | 2025-10-04 | 2025-10-08 | 2025-05-20 | 2025-05-23 | 119
C-52-0304-PL-ME-7610 | De-watering | 5 | 5 | 2025-10-08 | 2025-10-14 | 2025-05-23 | 2025-05-29 | 119
C-52-0304-PL-ME-7620 | Swabing & Drying (Upto Dew Point Temp.) | 5 | 5 | 2025-10-14 | 2025-10-20 | 2025-05-29 | 2025-06-04 | 119
52” Pipeline from BVS-04 to BVS-05 at KP 114.2 |  | 84 | 84 | 2025-08-18 | 2025-11-09 | 2025-07-23 | 2025-10-30 | 10
52”x 16.3 Km Pipeline from BVS-04 to BVS-05 at KP 114.2 |  | 84 | 84 | 2025-08-18 | 2025-11-09 | 2025-07-23 | 2025-10-30 | 10
Precommissioning BVS-4CPCB35210 |  | 21 | 21 | 2025-08-18 | 2025-09-12 | 2025-09-17 | 2025-10-11 | 9
PRECOM-56-59804-1000 | Precommissioning BVS-4 | 21 | 21 | 2025-08-18 | 2025-09-12 | 2025-09-17 | 2025-10-11 | 9
Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 |  | 18 | 18 | 2025-09-27 | 2025-10-18 | 2025-10-09 | 2025-10-30 | 8
PRECOM-52-IDS2-1000 | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | 18 | 18 | 2025-09-27 | 2025-10-18 | 2025-10-09 | 2025-10-30 | 8
Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 |  | 67 | 67 | 2025-08-20 | 2025-11-09 | 2025-07-23 | 2025-10-10 | 27
PRECOM-52-0405-1000 | Pre-commissioning from BVS-04 to BVS-05 | 6 | 6 | 2025-11-01 | 2025-11-09 | 2025-10-03 | 2025-10-10 | 27
Evaporation PondCCOPL52431 |  | 30 | 30 | 2025-08-20 | 2025-09-25 | 2025-07-23 | 2025-08-27 | 36
C-52-0405-PL-CI-7200 | Evaporation Pond | 30 | 30 | 2025-08-20 | 2025-09-25 | 2025-07-23 | 2025-08-27 | 36
Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 |  | 19 | 19 | 2025-09-25 | 2025-10-18 | 2025-08-27 | 2025-09-19 | 27
C-52-0405-PL-ME-7400 | Cleaning & Gauging | 9 | 9 | 2025-09-25 | 2025-10-07 | 2025-08-27 | 2025-09-08 | 27
C-52-0405-PL-ME-7410 | Water Filling | 7 | 7 | 2025-10-07 | 2025-10-15 | 2025-09-08 | 2025-09-16 | 27
C-52-0405-PL-ME-7420 | Stabilization & Pressurization | 2 | 2 | 2025-10-15 | 2025-10-17 | 2025-09-16 | 2025-09-18 | 27
C-52-0405-PL-ME-7430 | Holding of Test Pressure | 1 | 1 | 2025-10-17 | 2025-10-18 | 2025-09-18 | 2025-09-19 | 27
Dewatering, Swabbing, & DryingCCOPL52426 |  | 12 | 12 | 2025-10-18 | 2025-11-01 | 2025-09-19 | 2025-10-03 | 27
C-52-0405-PL-ME-7600 | De-Pressurization | 1 | 1 | 2025-10-18 | 2025-10-20 | 2025-09-19 | 2025-09-20 | 27
C-52-0405-PL-ME-7610 | De-watering | 6 | 6 | 2025-10-20 | 2025-10-27 | 2025-09-20 | 2025-09-27 | 27
C-52-0405-PL-ME-7620 | Swabing & Drying (Upto Dew Point Temp.) | 5 | 5 | 2025-10-27 | 2025-11-01 | 2025-09-27 | 2025-10-03 | 27
52” Pipeline from BVS-05 to BVS-06 at KP 139.2 |  | 116 | 116 | 2025-07-09 | 2025-11-03 | 2025-06-16 | 2025-10-31 | 7
52”x 25.0 Km Pipeline from BVS-05 to BVS-06 at KP 139.2 |  | 116 | 116 | 2025-07-09 | 2025-11-03 | 2025-06-16 | 2025-10-31 | 7
Precommissioning BVS-5CPCB25210 |  | 18 | 18 | 2025-09-15 | 2025-10-07 | 2025-08-09 | 2025-08-30 | 44
PRECOM-56-59805-1000 | Precommissioning BVS-5 | 18 | 18 | 2025-09-15 | 2025-10-07 | 2025-08-09 | 2025-08-30 | 44
Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 |  | 12 | 12 | 2025-10-13 | 2025-11-03 | 2025-10-17 | 2025-10-31 | 7
PRECOM-52-IDS3-1000 | Pre-Commissioning Intrusion Detection KP122 to KP123 | 12 | 12 | 2025-10-13 | 2025-11-03 | 2025-10-17 | 2025-10-31 | 7
Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 |  | 99 | 99 | 2025-07-09 | 2025-11-03 | 2025-06-16 | 2025-10-11 | 20
PRECOM-52-0506-1000 | Pre-commissioning from BVS-05 to BVS-06 | 9 | 9 | 2025-10-23 | 2025-11-03 | 2025-10-01 | 2025-10-11 | 20
Evaporation PondCCOPL52459 |  | 45 | 45 | 2025-07-09 | 2025-08-30 | 2025-06-16 | 2025-08-08 | 20
C-52-0506-PL-CI-7200 | Evaporation Pond | 45 | 45 | 2025-07-09 | 2025-08-30 | 2025-06-16 | 2025-08-08 | 20
Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 |  | 31 | 31 | 2025-08-30 | 2025-10-07 | 2025-08-08 | 2025-09-15 | 20
C-52-0506-PL-ME-7400 | Cleaning & Gauging | 14 | 14 | 2025-08-30 | 2025-09-17 | 2025-08-08 | 2025-08-25 | 20
C-52-0506-PL-ME-7410 | Water Filling | 10 | 10 | 2025-09-17 | 2025-09-29 | 2025-08-25 | 2025-09-06 | 20
C-52-0506-PL-ME-7420 | Stabilization & Pressurization | 6 | 6 | 2025-09-29 | 2025-10-06 | 2025-09-06 | 2025-09-13 | 20
C-52-0506-PL-ME-7430 | Holding of Test Pressure | 1 | 1 | 2025-10-06 | 2025-10-07 | 2025-09-13 | 2025-09-15 | 20
Dewatering, Swabbing, & DryingCCOPL52454 |  | 14 | 14 | 2025-10-07 | 2025-10-23 | 2025-09-15 | 2025-10-01 | 20
C-52-0506-PL-ME-7600 | De-Pressurization | 3 | 3 | 2025-10-07 | 2025-10-10 | 2025-09-15 | 2025-09-18 | 20
C-52-0506-PL-ME-7610 | De-watering | 6 | 6 | 2025-10-10 | 2025-10-17 | 2025-09-18 | 2025-09-25 | 20
C-52-0506-PL-ME-7620 | Swabing & Drying (Upto Dew Point Temp.) | 5 | 5 | 2025-10-17 | 2025-10-23 | 2025-09-25 | 2025-10-01 | 20
Precommissioning DEL/TFP PipelineCPCHGCP522 |  | 9 | 9 | 2025-10-10 | 2025-10-21 | 2025-09-08 | 2025-09-18 | 44
PRECOM-52-D-1000 | Precommissioning DEL/TFP Pipeline | 9 | 9 | 2025-10-10 | 2025-10-21 | 2025-09-08 | 2025-09-18 | 44
52" Pipeline from BVS-06 to Sweihan CRS at KP 161 |  | 87 | 87 | 2025-07-18 | 2025-11-03 | 2025-07-23 | 2025-11-03 | 5
52”x 22.5 Km Pipeline from BVS-06 to Sweihan CRS at KP 161 |  | 87 | 87 | 2025-07-18 | 2025-11-03 | 2025-07-23 | 2025-11-03 | 5
Precommissioning BVS-6CPCB15210 |  | 18 | 18 | 2025-10-09 | 2025-10-30 | 2025-08-23 | 2025-09-15 | 47
PRECOM-52-59806-1000 | Precommissioning BVS-6 | 18 | 18 | 2025-10-09 | 2025-10-30 | 2025-08-23 | 2025-09-15 | 47
Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 |  | 87 | 87 | 2025-07-18 | 2025-11-03 | 2025-07-23 | 2025-11-03 | 0
PRECOM-52-06CR-1000 | Pre-commissioning from BVS-06 to CRS Sweihan | 1 | 1 | 2025-11-01 | 2025-11-03 | 2025-11-01 | 2025-11-03 | 0
Evaporation PondCCOPL52487 |  | 45 | 45 | 2025-07-18 | 2025-09-10 | 2025-07-23 | 2025-09-15 | 0
C-52-06CR-PL-CI-7200 | Evaporation Pond | 45 | 45 | 2025-07-18 | 2025-09-10 | 2025-07-23 | 2025-09-15 | 0
Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 |  | 27 | 27 | 2025-09-10 | 2025-10-11 | 2025-09-15 | 2025-10-16 | 0
C-52-06CR-PL-ME-7400 | Cleaning & Gauging | 14 | 14 | 2025-09-10 | 2025-09-26 | 2025-09-15 | 2025-10-01 | 0
C-52-06CR-PL-ME-7410 | Water Filling | 10 | 10 | 2025-09-26 | 2025-10-08 | 2025-10-01 | 2025-10-13 | 0
C-52-06CR-PL-ME-7420 | Stabilization & Pressurization | 2 | 2 | 2025-10-08 | 2025-10-10 | 2025-10-13 | 2025-10-15 | 0
C-52-06CR-PL-ME-7430 | Holding of Test Pressure | 1 | 1 | 2025-10-10 | 2025-10-11 | 2025-10-15 | 2025-10-16 | 0
Dewatering & DryingCCOPL52482 |  | 13 | 13 | 2025-10-11 | 2025-10-25 | 2025-10-16 | 2025-10-31 | 0
C-52-06CR-PL-ME-7600 | De-Pressurization | 1 | 1 | 2025-10-11 | 2025-10-13 | 2025-10-16 | 2025-10-17 | 0
C-52-06CR-PL-ME-7610 | De-watering | 6 | 6 | 2025-10-13 | 2025-10-20 | 2025-10-17 | 2025-10-24 | 0
C-52-06CR-PL-ME-7620 | Swabing & Drying (Upto Dew Point Temp.) | 6 | 6 | 2025-10-20 | 2025-10-25 | 2025-10-24 | 2025-10-31 | 0
Precommissioning Electrical Building Type-ICPCSW108 |  | 17 | 17 | 2025-10-13 | 2025-11-01 | 2025-10-14 | 2025-11-03 | 5
PRECOM-52-EB1-1000 | Precommissioning Electrical Building Type-I | 17 | 17 | 2025-10-13 | 2025-11-01 | 2025-10-14 | 2025-11-03 | 5
Precommissioning Pig Receiver 839-V-101CPCSW112 |  | 18 | 18 | 2025-08-27 | 2025-09-18 | 2025-10-02 | 2025-10-22 | 14
PRECOM-52-PR-1000 | Precommissioning Pig Receiver 839-V-101 | 18 | 18 | 2025-08-27 | 2025-09-18 | 2025-10-02 | 2025-10-22 | 14
36'' Jump-over connection at KM-42 |  | 12 | 12 | 2025-09-17 | 2025-10-01 | 2025-08-21 | 2025-09-04 | 20
36'' Jump-over connection at KM-1 |  | 12 | 12 | 2025-09-17 | 2025-10-01 | 2025-08-21 | 2025-09-04 | 20
PrecommissioningCPCJ421 |  | 12 | 12 | 2025-09-17 | 2025-10-01 | 2025-08-21 | 2025-09-04 | 20
PRECOM-36-KM-1000 | Precommissioning | 12 | 12 | 2025-09-17 | 2025-10-01 | 2025-08-21 | 2025-09-04 | 20
Habshan-5 4” P/L to HGCP 4” P/R (4”) |  | 19 | 19 | 2025-08-13 | 2025-09-04 | 2025-09-08 | 2025-09-30 | 28
Temporary Pig Launcher (4'' Nitrogen Pipeline) |  | 18 | 18 | 2025-08-14 | 2025-09-04 | 2025-09-09 | 2025-09-30 | 28
Temporary Pig Launcher (4'' Nitrogen Pipeline) |  | 18 | 18 | 2025-08-14 | 2025-09-04 | 2025-09-09 | 2025-09-30 | 28
PrecommissioningCPC-H51010 |  | 18 | 18 | 2025-08-14 | 2025-09-04 | 2025-09-09 | 2025-09-30 | 28
PRECOM-4NH5-TPL-1000 | Precommissioning | 18 | 18 | 2025-08-14 | 2025-09-04 | 2025-09-09 | 2025-09-30 | 28
Temporary Pig Receiver (4'' Nitrogen Pipeline) |  | 12 | 12 | 2025-08-13 | 2025-08-27 | 2025-09-08 | 2025-09-22 | 35
Temporary Pig Receiver (4'' Nitrogen Pipeline)-1 |  | 12 | 12 | 2025-08-13 | 2025-08-27 | 2025-09-08 | 2025-09-22 | 35
PrecommissioningCPC-H51000 |  | 12 | 12 | 2025-08-13 | 2025-08-27 | 2025-09-08 | 2025-09-22 | 35
PRECOM-4NHG-TPR-1000 | Precommissioning | 12 | 12 | 2025-08-13 | 2025-08-27 | 2025-09-08 | 2025-09-22 | 35
4'' Pipeline from Habshan-5 to HGCP |  | 10 | 10 | 2025-08-20 | 2025-09-01 | 2025-09-13 | 2025-09-25 | 23
4" Nitrogen Line for Habshan-5 to HGCP (20.7 km) |  | 10 | 10 | 2025-08-20 | 2025-09-01 | 2025-09-13 | 2025-09-25 | 23
Pre-commissioningCCOPL4"125 |  | 10 | 10 | 2025-08-20 | 2025-09-01 | 2025-09-13 | 2025-09-25 | 23
PRECOM-4N-H5HG-1000 | Precommissioning | 10 | 10 | 2025-08-20 | 2025-09-01 | 2025-09-13 | 2025-09-25 | 23
SV-03 (KP 96) to HGCP (4'') |  | 104 | 104 | 2025-03-03 | 2025-08-04 | 2025-04-17 | 2025-08-21 | 61
SV-03 (KP 96) to HGCP (4") |  | 4 | 4 | 2025-03-03 | 2025-03-09 | 2025-04-17 | 2025-04-22 | 101
4'' Water Line from SV-03 (KP 96) to HGCP (1.8 km) |  | 4 | 4 | 2025-03-03 | 2025-03-09 | 2025-04-17 | 2025-04-22 | 101
PRECOM-4W-SVHG-1000 | Precommissioning | 4 | 4 | 2025-03-03 | 2025-03-09 | 2025-04-17 | 2025-04-22 | 101
Existing 081-SV-03 |  | 4 | 4 | 2025-05-15 | 2025-05-20 | 2025-06-16 | 2025-06-20 | 113
Existing 081-SV-1 |  | 4 | 4 | 2025-05-15 | 2025-05-20 | 2025-06-16 | 2025-06-20 | 113
PrecommissioningCPC-SV3100 |  | 4 | 4 | 2025-05-15 | 2025-05-20 | 2025-06-16 | 2025-06-20 | 113
PRECOM-4W-08103-1000 | Precommissioning | 4 | 4 | 2025-05-15 | 2025-05-20 | 2025-06-16 | 2025-06-20 | 113
HGCP Connection (4'' Tie-in Connection) |  | 18 | 18 | 2025-07-14 | 2025-08-04 | 2025-07-31 | 2025-08-21 | 21
HGCP Connection (4" Tie-in Connection Water Line) |  | 18 | 18 | 2025-07-14 | 2025-08-04 | 2025-07-31 | 2025-08-21 | 21
PrecommissioningCPC-SV3101 |  | 18 | 18 | 2025-07-14 | 2025-08-04 | 2025-07-31 | 2025-08-21 | 21
PRE-COM1310 | Precommissioning | 18 | 18 | 2025-07-14 | 2025-08-04 | 2025-07-31 | 2025-08-21 | 21
Dolphin Existing BVS -06 |  | 4 | 4 | 2025-09-22 | 2025-09-25 | 2025-08-30 | 2025-09-04 | 15
Dolphin Existing BVS -1 |  | 4 | 4 | 2025-09-22 | 2025-09-25 | 2025-08-30 | 2025-09-04 | 15
PrecommissioningCPCB611 |  | 4 | 4 | 2025-09-22 | 2025-09-25 | 2025-08-30 | 2025-09-04 | 15
PRE-COM1330 | Precommissioning | 4 | 4 | 2025-09-22 | 2025-09-25 | 2025-08-30 | 2025-09-04 | 15
Commissioning & As-Built Documentation |  | 438 | 438 | 2024-07-29 | 2026-01-09 | 2024-10-28 | 2026-01-09 | 0
Operation & Commissioning |  | 130 | 130 | 2024-07-29 | 2025-04-21 | 2024-10-28 | 2025-05-05 | 31
Commissioning Manuals |  | 110 | 110 | 2024-07-29 | 2024-12-31 | 2024-10-28 | 2025-04-07 | 31
HE-CO-110 | Issue ICR-Commissioning Manual | 30 | 30 | 2024-07-29 | 2024-09-06 | 2024-10-28 | 2024-12-10 | 31
HE-CO-120 | Receive Company Comments-Commissioning Manual | 10 | 10 | 2024-09-09 | 2024-09-20 | 2024-12-11 | 2024-12-24 | 31
HE-CO-130 | Re-Issue for Approval-Commissioning Manual | 30 | 30 | 2024-09-23 | 2024-11-01 | 2024-12-25 | 2025-02-05 | 31
HE-CO-140 | Obtain Company Approval-Commissioning Manual | 10 | 10 | 2024-11-04 | 2024-11-15 | 2025-02-06 | 2025-02-19 | 31
HE-CO-150 | Final Issue for Design/ Construction-Commissioning Manuals | 30 | 30 | 2024-11-18 | 2024-12-31 | 2025-02-20 | 2025-04-07 | 31
Operation and Maintenance Manuals |  | 85 | 85 | 2024-12-18 | 2025-04-21 | 2025-01-02 | 2025-05-05 | 31
HE-CO-200 | Issue ICR-Operation and Maintenance Manual | 25 | 25 | 2024-12-18 | 2025-01-22 | 2025-01-02 | 2025-02-05 | 31
HE-CO-160 | Receive Company Comments-Operation and Maintenance Manual | 10 | 10 | 2025-01-23 | 2025-02-05 | 2025-02-06 | 2025-02-19 | 31
HE-CO-170 | Re-Issue for Approval-Operation and Maintenance Manual | 20 | 20 | 2025-02-06 | 2025-03-05 | 2025-02-20 | 2025-03-19 | 31
HE-CO-180 | Obtain Company Approval-Operation and Maintenance Manual | 10 | 10 | 2025-03-06 | 2025-03-19 | 2025-03-20 | 2025-04-07 | 31
HE-CO-190 | Final Issue for Design/ Construction-Operation and Maintenance Manuals | 20 | 20 | 2025-03-20 | 2025-04-21 | 2025-04-08 | 2025-05-05 | 31
Commissioning |  | 232 | 232 | 2025-04-22 | 2026-01-02 | 2025-05-06 | 2025-12-24 | 5
CCM-PM4500 | Approval of Commissioning Dossiers | 50 | 50 | 2025-04-22 | 2025-06-23 | 2025-05-06 | 2025-07-08 | 37
CCM-PM4510 | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | 40 | 40 | 2025-10-01 | 2025-11-10 | 2025-10-09 | 2025-11-18 | 23
CCM-PM4550 | Wrap up works for PAC-1 | 14 | 14 | 2025-11-10 | 2025-11-25 | 2025-11-25 | 2025-12-09 | 16
CCM-PM4520 | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | 40 | 40 | 2025-11-12 | 2025-12-22 | 2025-11-03 | 2025-12-13 | 5
CCM-PM4530 | Wrap up works for PAC-2 | 11 | 11 | 2025-12-22 | 2026-01-02 | 2025-12-13 | 2025-12-24 | 5
System Commissioninng - Habshan Complex to 56” P/L Fac. (56”) |  | 40 | 40 | 2025-09-23 | 2025-11-09 | 2025-09-28 | 2025-11-12 | 21
CCM-PM4560 | Commissioning | 40 | 40 | 2025-09-23 | 2025-11-09 | 2025-09-28 | 2025-11-12 | 21
System Commissioninng - 56” P/L Facility to HGCP 56” P/R (56”) |  | 49 | 49 | 2025-10-09 | 2025-11-25 | 2025-10-09 | 2025-12-09 | 14
CCM-PM4570 | Commissioning | 49 | 49 | 2025-10-09 | 2025-11-25 | 2025-10-09 | 2025-12-09 | 14
System Commissioninng - HGCP 52” P/L to Sweihan CRS 52” P/R (52”) |  | 30 | 30 | 2025-11-09 | 2025-12-17 | 2025-11-03 | 2025-12-11 | 6
CCM-PM4580 | Commissioning | 30 | 30 | 2025-11-09 | 2025-12-17 | 2025-11-03 | 2025-12-11 | 6
System Commissioninng - 36'' Jump-over connection at KM-42 |  | 40 | 40 | 2025-10-01 | 2025-11-17 | 2025-09-04 | 2025-10-22 | 19
CCM-PM4590 | Commissioning | 40 | 40 | 2025-10-01 | 2025-11-17 | 2025-09-04 | 2025-10-22 | 19
System Commissioninng - Habshan-5 4” P/L to HGCP 4” P/R (4”) |  | 40 | 40 | 2025-09-01 | 2025-10-19 | 2025-09-25 | 2025-11-11 | 23
CCM-PM4600 | Commissioning | 40 | 40 | 2025-09-01 | 2025-10-19 | 2025-09-25 | 2025-11-11 | 23
System Commissioninng - SV-03 (KP 96) to HGCP (4'') |  | 40 | 40 | 2025-08-04 | 2025-09-21 | 2025-08-21 | 2025-10-08 | 21
CCM-PM4610 | Commissioning | 40 | 40 | 2025-08-04 | 2025-09-21 | 2025-08-21 | 2025-10-08 | 21
System Commissioninng - Dolphin Existing BVS -06 |  | 40 | 40 | 2025-09-26 | 2025-11-11 | 2025-09-04 | 2025-10-22 | 15
CCM-PM4620 | Commissioning | 40 | 40 | 2025-09-26 | 2025-11-11 | 2025-09-04 | 2025-10-22 | 15
As-Built & Final Documentation |  | 88 | 88 | 2025-10-13 | 2026-01-09 | 2025-10-13 | 2026-01-09 | 0
A3980 | Demolitionbilization | 0 | 0 |  | 2026-01-02 |  | 2025-12-24 | 13
Commissioning & As-Built |  | 0 | 0 | 2025-11-10 | 2025-11-10 | 2025-11-03 | 2025-11-03 | 33
COM-1000 | Ready for Commissioning & As-Built Submission | 0 | 0 |  | 2025-11-10 |  | 2025-11-03 | 33
As-built Survey |  | 10 | 10 | 2025-12-22 | 2026-01-01 | 2025-12-13 | 2025-12-23 | 17
CCM-PM4540 | Intelligent Pigging Baseline Survey | 10 | 10 | 2025-12-22 | 2026-01-01 | 2025-12-13 | 2025-12-23 | 17
Discipline wise As-Built Documentation |  | 50 | 50 | 2025-10-13 | 2025-12-25 | 2025-10-13 | 2025-12-25 | 0
CAB-4400 | Process | 20 | 20 | 2025-10-13 | 2025-11-07 | 2025-10-13 | 2025-11-10 | 2
CAB-4410 | HSE | 20 | 20 | 2025-10-15 | 2025-11-12 | 2025-10-15 | 2025-11-12 | 0
CAB-4420 | Civil & Structural | 20 | 20 | 2025-10-21 | 2025-11-18 | 2025-10-21 | 2025-11-18 | 0
CAB-4430 | Mechanical | 20 | 20 | 2025-10-27 | 2025-11-24 | 2025-10-27 | 2025-11-24 | 0
CAB-4440 | Piping | 20 | 20 | 2025-10-31 | 2025-11-28 | 2025-10-31 | 2025-11-28 | 0
CAB-4450 | Electrical | 20 | 20 | 2025-11-06 | 2025-12-09 | 2025-11-06 | 2025-12-09 | 0
CAB-4460 | Instrumentation & Control | 20 | 20 | 2025-11-12 | 2025-12-15 | 2025-11-12 | 2025-12-15 | 0
CAB-4470 | Telecom | 20 | 20 | 2025-11-18 | 2025-12-19 | 2025-11-18 | 2025-12-19 | 0
CAB-4480 | Pipeline | 20 | 20 | 2025-11-24 | 2025-12-25 | 2025-11-24 | 2025-12-25 | 0
Final Documentation |  | 20 | 20 | 2025-12-11 | 2026-01-09 | 2025-12-11 | 2026-01-09 | 0
CAB-5300 | Quality Dossier | 20 | 20 | 2025-12-11 | 2026-01-09 | 2025-12-11 | 2026-01-09 | 0
CAB-5310 | Vendor Documents Package | 20 | 20 | 2025-12-11 | 2026-01-09 | 2025-12-11 | 2026-01-09 | 0
CAB-5290 | General | 20 | 20 | 2025-12-11 | 2026-01-09 | 2025-12-11 | 2026-01-09 | 0
CAB-5320 | Close-out report | 20 | 20 | 2025-12-11 | 2026-01-09 | 2025-12-11 | 2026-01-09 | 0