## TASK
task_code | status_code | wbs_id | task_name | pred_list | pred_details | succ_list | succ_details | start_date | end_date | delete_record_flag
Activity ID | Activity Status | WBS Code | Activity Name | (*)Predecessors | (*)Predecessor Details | (*)Successors | (*)Successor Details | (*)Start | (*)Finish | Delete This Row
C-52-0203-PL-CI-1000 | Completed | P2543-R01-Oct24..4.3.1.3.20 | Survey Marking BVS-02 to BVS-03 | C-52-0102-PL-CI-1000 | C-52-0102-PL-CI-1000: FS | C-52-0203-PL-CI-1800, C-52-0304-PL-CI-1000 | C-52-0203-PL-CI-1800: FS, C-52-0304-PL-CI-1000: FS | 2024-01-26 07:30 | 2024-05-07
C-52-0203-PL-CI-1800 | Completed | P2543-R01-Oct24..4.3.1.3.15.21.1.6 | Sabka ROW/Grading | C-52-0203-PL-CI-1000 | C-52-0203-PL-CI-1000: FS | C-52-0203-PL-CI-2000, C-52-0203-PL-CI-2000 | C-52-0203-PL-CI-2000: SS 21, C-52-0203-PL-CI-2000: FF 21 | 2024-03-13 | 2024-08-01 14:30
C-52-0203-PL-CI-2000 | Completed | P2543-R01-Oct24..4.3.1.3.15.21.1.6 | Sabka Gatch Laying (Including ROW) - Layer 1 | C-52-0203-PL-CI-1800, C-52-0203-PL-CI-1800 | C-52-0203-PL-CI-1800: SS 21, C-52-0203-PL-CI-1800: FF 21 | C-52-0203-PL-CI-2200, C-52-0203-PL-CI-2200 | C-52-0203-PL-CI-2200: SS 7, C-52-0203-PL-CI-2200: FF 7 | 2024-04-23 | 2024-08-05 14:30
C-52-0203-PL-CI-2010 | Completed | P2543-R01-Oct24..4.3.1.3.15.21.1.6 | Sabka Gatch Laying - Layer 2 | C-52-0203-PL-CI-2200, C-52-0203-PL-CI-2200 | C-52-0203-PL-CI-2200: SS 7, C-52-0203-PL-CI-2200: FF 7 | C-52-0203-PL-CI-2210, C-52-0203-PL-CI-2210 | C-52-0203-PL-CI-2210: SS 7, C-52-0203-PL-CI-2210: FF 7 | 2024-04-26 | 2024-08-12 14:30
C-52-0203-PL-CI-2020 | Completed | P2543-R01-Oct24..4.3.1.3.15.21.1.6 | Sabka Gatch Laying - Layer 3 | C-52-0203-PL-CI-2210, C-52-0203-PL-CI-2210 | C-52-0203-PL-CI-2210: SS 7, C-52-0203-PL-CI-2210: FF 7 | C-52-0203-PL-CI-2220, C-52-0203-PL-CI-2220 | C-52-0203-PL-CI-2220: SS 7, C-52-0203-PL-CI-2220: FF 7 | 2024-05-09 | 2024-08-19 14:30
C-52-0203-PL-CI-2030 | Completed | P2543-R01-Oct24..4.3.1.3.15.21.1.6 | Sabka Gatch Laying - Layer 4 | C-52-0203-PL-CI-2220, C-52-0203-PL-CI-2220 | C-52-0203-PL-CI-2220: SS 7, C-52-0203-PL-CI-2220: FF 7 | C-52-0203-PL-CI-2230, C-52-0203-PL-CI-2230 | C-52-0203-PL-CI-2230: SS 7, C-52-0203-PL-CI-2230: FF 7 | 2024-05-09 | 2024-08-26 14:30
C-52-0203-PL-CI-2200 | Completed | P2543-R01-Oct24..4.3.1.3.15.21.1.6 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-0203-PL-CI-2000, C-52-0203-PL-CI-2000 | C-52-0203-PL-CI-2000: SS 7, C-52-0203-PL-CI-2000: FF 7 | C-52-0203-PL-CI-2010, C-52-0203-PL-CI-2010 | C-52-0203-PL-CI-2010: SS 7, C-52-0203-PL-CI-2010: FF 7 | 2024-04-24 | 2024-08-09 14:30
C-52-0203-PL-CI-2210 | Completed | P2543-R01-Oct24..4.3.1.3.15.21.1.6 | Sabka Gatch Compaction - Layer 2 | C-52-0203-PL-CI-2010, C-52-0203-PL-CI-2010 | C-52-0203-PL-CI-2010: SS 7, C-52-0203-PL-CI-2010: FF 7 | C-52-0203-PL-CI-2020, C-52-0203-PL-CI-2020 | C-52-0203-PL-CI-2020: SS 7, C-52-0203-PL-CI-2020: FF 7 | 2024-04-26 | 2024-08-16 14:30
C-52-0203-PL-CI-2220 | Completed | P2543-R01-Oct24..4.3.1.3.15.21.1.6 | Sabka Gatch Compaction - Layer 3 | C-52-0203-PL-CI-2020, C-52-0203-PL-CI-2020 | C-52-0203-PL-CI-2020: SS 7, C-52-0203-PL-CI-2020: FF 7 | C-52-0203-PL-CI-2030, C-52-0203-PL-CI-2030 | C-52-0203-PL-CI-2030: SS 7, C-52-0203-PL-CI-2030: FF 7 | 2024-05-09 | 2024-08-23 14:30
C-52-0203-PL-CI-2230 | Completed | P2543-R01-Oct24..4.3.1.3.15.21.1.6 | Sabka Gatch Compaction - Layer 4 | C-52-0203-PL-CI-2030, C-52-0203-PL-CI-2030 | C-52-0203-PL-CI-2030: SS 7, C-52-0203-PL-CI-2030: FF 7 | C-52-0203-PL-ME-2800, C-52-0203-PL-CI-2400, C-52-0203-PL-ME-2800, ML1659-E11 | C-52-0203-PL-ME-2800: SS 7, C-52-0203-PL-CI-2400: FS, C-52-0203-PL-ME-2800: FF 3, ML1659-E11: FS | 2024-05-09 | 2024-08-30 14:30
C-52-0203-PL-ME-2800 | Completed | P2543-R01-Oct24..4.3.1.3.15.21.1.8 | Stringing (BVS-02 to BVS-03) | C-52-0203-PL-CI-2230, C-52-0203-PL-CI-2230, HM-PL-0100, C-52-HG01-PL-ME-3000 | C-52-0203-PL-CI-2230: SS 7, C-52-0203-PL-CI-2230: FF 3, HM-PL-0100: FF 7, C-52-HG01-PL-ME-3000: SS | C-52-0304-CMA02-1000, C-52-0203-PL-ME-3600, C-52-0203-CMA01-1020, C-52-0203-CME01-1020, C-52-0203-PL-CI-2400, C-52-0203-PL-ME-3600, C-52-0203-PL-CI-2400, C-52-0203-PL-ME-4810, C-52-0203-PL-CA-5220, C-52-0203-PL-TE-8200, C-52-0203-PL-ME-7400, C-52-0203-PL-C | C-52-0304-CMA02-1000: FS, C-52-0203-PL-ME-3600: SS 1, C-52-0203-CMA01-1020: SS 5, C-52-0203-CME01-1020: SS 5, C-52-0203-PL-CI-2400: SS 3, C-52-0203-PL-ME-3600: FF 1, C-52-0203-PL-CI-2400: FF 3, C-52-0203-PL-ME-4810: SF, C-52-0203-PL-CA-5220: SF, C-52-0203- | 2024-06-19 | 2024-09-08 09:30
C-52-0203-PL-ME-3600 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.10 | Automatic Welding | C-52-0203-PL-ME-2800, C-COM-1010, C-52-0203-PL-ME-2800, C-52-0102-PL-ME-3600 | C-52-0203-PL-ME-2800: SS 1, C-COM-1010: FS, C-52-0203-PL-ME-2800: FF 1, C-52-0102-PL-ME-3600: FS -32 | C-52-0203-PL-ME-4000, ML1699-E15, ML1709-E16, ML1719-E17, C-52-0203-PL-CI-2400, C-52-0203-PL-CI-2400, C-52-0203-PL-ME-4000, C-52-0304-PL-ME-3600, ML1070 | C-52-0203-PL-ME-4000: SS 1, ML1699-E15: FS, ML1709-E16: FS, ML1719-E17: FS, C-52-0203-PL-CI-2400: SS 3, C-52-0203-PL-CI-2400: FF 17, C-52-0203-PL-ME-4000: FF 1, C-52-0304-PL-ME-3600: FS, ML1070: FF 9 | 2024-10-26 07:00 | 2024-12-04 17:00
C-52-0203-PL-ME-4000 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.11 | NDT | C-52-0203-PL-ME-3600, HS-CN-0190, C-52-0203-PL-ME-3600 | C-52-0203-PL-ME-3600: SS 1, HS-CN-0190: FS, C-52-0203-PL-ME-3600: FF 1 | C-52-0203-PL-ME-4400, C-52-0203-PL-ME-4400 | C-52-0203-PL-ME-4400: SS 1, C-52-0203-PL-ME-4400: FF 1 | 2024-10-28 07:00 | 2024-12-23 17:00
C-52-0203-PL-ME-4400 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.12 | Ext. Joint Coating | C-52-0203-PL-ME-4000, C-52-0203-PL-ME-4000 | C-52-0203-PL-ME-4000: SS 1, C-52-0203-PL-ME-4000: FF 1 | C-52-0203-PL-ME-4800, C-52-0203-PL-ME-4800 | C-52-0203-PL-ME-4800: SS 3, C-52-0203-PL-ME-4800: FF 3 | 2024-10-29 07:00 | 2024-12-24 17:00
C-52-0203-PL-CI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.7 | Trench Excavation | C-52-0203-PL-CI-2230, C-52-0203-PL-ME-2800, C-52-0203-PL-ME-3600, C-52-0203-PL-ME-3600, C-52-0203-PL-ME-2800 | C-52-0203-PL-CI-2230: FS, C-52-0203-PL-ME-2800: SS 3, C-52-0203-PL-ME-3600: SS 3, C-52-0203-PL-ME-3600: FF 17, C-52-0203-PL-ME-2800: FF 3 | C-52-0203-PL-CI-2410, C-52-0203-CMA01-970, C-52-0203-PL-CI-2410 | C-52-0203-PL-CI-2410: SS 5, C-52-0203-CMA01-970: SS 3, C-52-0203-PL-CI-2410: FF 5 | 2024-11-23 07:00 | 2024-12-24 17:00
C-52-0203-PL-CI-2410 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.7 | Bedding | C-52-0203-PL-CI-2400, C-52-0203-PL-CI-2400 | C-52-0203-PL-CI-2400: SS 5, C-52-0203-PL-CI-2400: FF 5 | C-52-0203-PL-ME-4800, C-52-0203-PL-ME-4800 | C-52-0203-PL-ME-4800: FF 5, C-52-0203-PL-ME-4800: SS 3 | 2024-11-29 07:00 | 2024-12-30 17:00
C-52-0203-PL-ME-4800 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.13 | Lowering | C-52-0203-PL-CI-2410, C-52-0203-PL-ME-4400, C-52-0203-PL-CI-2410, C-52-0203-PL-ME-4400 | C-52-0203-PL-CI-2410: FF 5, C-52-0203-PL-ME-4400: SS 3, C-52-0203-PL-CI-2410: SS 3, C-52-0203-PL-ME-4400: FF 3 | C-52-0203-PL-ME-4810, C-52-0203-PL-CA-5600, ML1729-E18, C-52-0203-PL-ME-3200, C-52-0203-PL-ME-4810 | C-52-0203-PL-ME-4810: SS, C-52-0203-PL-CA-5600: SS 3, ML1729-E18: FS, C-52-0203-PL-ME-3200: FF, C-52-0203-PL-ME-4810: FF | 2024-12-05 07:00 | 2025-01-07 17:00
C-52-0203-PL-ME-4810 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.13 | Section Tie-in Welding | C-52-0203-PL-ME-4800, C-52-0203-CMA01-1030, C-52-0203-CMA02-1030, C-52-0203-CME01-1030, C-52-0203-CME02-1030, C-52-0203-CME03-1030, C-52-0203-PL-ME-3200, C-52-0203-CME04-1030, C-52-0203-PL-ME-4800, C-52-0203-PL-ME-2800, C-PER-1130 | C-52-0203-PL-ME-4800: SS, C-52-0203-CMA01-1030: FF 1, C-52-0203-CMA02-1030: FF 1, C-52-0203-CME01-1030: FF 1, C-52-0203-CME02-1030: FF 1, C-52-0203-CME03-1030: FF 1, C-52-0203-PL-ME-3200: FF, C-52-0203-CME04-1030: FF 1, C-52-0203-PL-ME-4800: FF, C-52-0203- | C-52-0203-PL-ME-4820, C-52-0203-PL-ME-4820 | C-52-0203-PL-ME-4820: SS 1, C-52-0203-PL-ME-4820: FF 1 | 2024-12-05 07:00 | 2025-01-27 17:00
C-52-0203-PL-ME-4820 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.13 | NDT (Tie-in Joint) | C-52-0203-PL-ME-4810, C-52-0203-PL-ME-4810 | C-52-0203-PL-ME-4810: SS 1, C-52-0203-PL-ME-4810: FF 1 | C-52-0203-PL-ME-4410, C-52-0203-PL-ME-4410 | C-52-0203-PL-ME-4410: SS 1, C-52-0203-PL-ME-4410: FF 1 | 2024-12-06 07:00 | 2025-01-28 17:00
C-52-0203-PL-ME-4410 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.12 | Ext. Joint Coating (Tie-in Joint) | C-52-0203-PL-ME-4820, C-52-0203-PL-ME-4820 | C-52-0203-PL-ME-4820: SS 1, C-52-0203-PL-ME-4820: FF 1 | C-52-0203-PL-ME-4830, C-52-0203-PL-ME-4830 | C-52-0203-PL-ME-4830: SS 1, C-52-0203-PL-ME-4830: FF 1 | 2024-12-07 07:00 | 2025-01-29 17:00
C-52-0203-PL-ME-4830 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.13 | Holiday Testing | C-52-0203-PL-ME-4410, C-52-0203-PL-ME-4410 | C-52-0203-PL-ME-4410: SS 1, C-52-0203-PL-ME-4410: FF 1 | C-52-0203-PL-CI-6000 | C-52-0203-PL-CI-6000: SS 1 | 2024-12-26 07:00 | 2025-01-30 17:00
C-52-0203-PL-CI-6000 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.18 | Padding | C-52-0203-PL-ME-4830, C-52-0203-CME01-1070, C-52-0203-CME02-1070, C-52-0203-CME03-1070, C-52-0203-CMA01-1070, C-52-0203-CMA02-1070, C-52-0203-CME04-1070, C-52-0203-PL-CA-5600, C-52-0203-PL-CA-5600, C-52-0203-PL-ME-2800, C-PER-1130, C-52-0203-CME04-1150 | C-52-0203-PL-ME-4830: SS 1, C-52-0203-CME01-1070: FF 7, C-52-0203-CME02-1070: FF 7, C-52-0203-CME03-1070: FF 7, C-52-0203-CMA01-1070: FF 7, C-52-0203-CMA02-1070: FF 7, C-52-0203-CME04-1070: FF 7, C-52-0203-PL-CA-5600: SS, C-52-0203-PL-CA-5600: FF, C-52-020 | C-52-0203-PL-CI-6800, C-52-0203-PL-CA-5210, C-52-0203-PL-TE-8200, C-52-0203-PL-ME-7400, PRECOM-52-0203-1000, C-52-0203-PL-CI-6800 | C-52-0203-PL-CI-6800: SS 3, C-52-0203-PL-CA-5210: FF, C-52-0203-PL-TE-8200: FS, C-52-0203-PL-ME-7400: FS, PRECOM-52-0203-1000: FS, C-52-0203-PL-CI-6800: FF | 2024-12-27 07:00 | 2025-01-31 17:00
C-52-0203-CMA01-970 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 | Excavation (Manual-Trial Pit) | C-52-0203-PL-CI-2400 | C-52-0203-PL-CI-2400: SS 3 | C-52-0203-CMA01-980, C-52-0203-CMA02-1000 | C-52-0203-CMA01-980: FS, C-52-0203-CMA02-1000: FS | 2024-11-27 07:00 | 2024-12-04 17:00
C-52-0203-CMA01-980 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 | Sabkha Gatch Laying | C-52-0203-CMA01-970 | C-52-0203-CMA01-970: FS | C-52-0203-CMA01-990 | C-52-0203-CMA01-990: SS 1 | 2024-12-05 07:00 | 2024-12-10 17:00
C-52-0203-CMA01-990 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 | Sabka Gatch Compaction | C-52-0203-CMA01-980 | C-52-0203-CMA01-980: SS 1 | C-52-0203-CMA01-1000 | C-52-0203-CMA01-1000: FF | 2024-12-06 07:00 | 2024-12-11 17:00
C-52-0203-CMA01-1000 | In Progress | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 | Trench Excavation | C-52-0203-CMA01-990 | C-52-0203-CMA01-990: FF | C-52-0203-CMA01-1010 | C-52-0203-CMA01-1010: FF | 2024-09-27 | 2024-12-11 17:00
C-52-0203-CMA01-1010 | In Progress | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 | Bedding | C-52-0203-CMA01-1000 | C-52-0203-CMA01-1000: FF | C-52-0203-CMA01-1020 | C-52-0203-CMA01-1020: FS | 2024-09-27 | 2024-12-11 17:00
C-52-0203-CMA01-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 | Lowering | C-52-0203-CMA01-1010, C-52-0203-PL-ME-2800 | C-52-0203-CMA01-1010: FS, C-52-0203-PL-ME-2800: SS 5 | C-52-0203-CMA01-1030 | C-52-0203-CMA01-1030: SS | 2024-12-12 07:00 | 2024-12-12 17:00
C-52-0203-CMA01-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 | Section Tie-in Welding | C-52-0203-CMA01-1020 | C-52-0203-CMA01-1020: SS | C-52-0203-CMA01-1040, C-52-0203-PL-ME-4810 | C-52-0203-CMA01-1040: SS 1, C-52-0203-PL-ME-4810: FF 1 | 2024-12-12 07:00 | 2024-12-13 17:00
C-52-0203-CMA01-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 | NDT (Tie-in Joint) | C-52-0203-CMA01-1030 | C-52-0203-CMA01-1030: SS 1 | C-52-0203-CMA01-1050 | C-52-0203-CMA01-1050: SS 1 | 2024-12-13 07:00 | 2024-12-14 17:00
C-52-0203-CMA01-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 | Ext. Joint Coating (Tie-in Joint) | C-52-0203-CMA01-1040 | C-52-0203-CMA01-1040: SS 1 | C-52-0203-CMA01-1060 | C-52-0203-CMA01-1060: FS | 2024-12-14 07:00 | 2024-12-16 17:00
C-52-0203-CMA01-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 | Holiday Testing | C-52-0203-CMA01-1050 | C-52-0203-CMA01-1050: FS | C-52-0203-CMA01-1070, C-52-0203-PL-CA-5220 | C-52-0203-CMA01-1070: FS, C-52-0203-PL-CA-5220: FS | 2024-12-17 07:00 | 2024-12-17 17:00
C-52-0203-CMA01-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 | Padding | C-52-0203-CMA01-1060 | C-52-0203-CMA01-1060: FS | C-52-0203-PL-TE-8200, C-52-0203-PL-ME-7400, C-52-0203-PL-CI-6800, C-52-0203-PL-CI-6000 | C-52-0203-PL-TE-8200: FF 1, C-52-0203-PL-ME-7400: FS, C-52-0203-PL-CI-6800: FF 1, C-52-0203-PL-CI-6000: FF 7 | 2024-12-18 07:00 | 2024-12-18 17:00
C-52-0203-CMA02-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 | Trench Excavation | C-52-0203-CMA01-970 | C-52-0203-CMA01-970: FS | C-52-0203-CMA02-1010 | C-52-0203-CMA02-1010: FS | 2024-12-05 07:00 | 2024-12-07 17:00
C-52-0203-CMA02-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 | Bedding | C-52-0203-CMA02-1000 | C-52-0203-CMA02-1000: FS | C-52-0203-CMA02-1020 | C-52-0203-CMA02-1020: FS | 2024-12-09 07:00 | 2024-12-09 17:00
C-52-0203-CMA02-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 | Lowering | C-52-0203-CMA02-1010 | C-52-0203-CMA02-1010: FS | C-52-0203-CMA02-1030 | C-52-0203-CMA02-1030: SS | 2024-12-10 07:00 | 2024-12-10 17:00
C-52-0203-CMA02-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 | Section Tie-in Welding | C-52-0203-CMA02-1020 | C-52-0203-CMA02-1020: SS | C-52-0203-CMA02-1040, C-52-0203-PL-ME-4810 | C-52-0203-CMA02-1040: SS 1, C-52-0203-PL-ME-4810: FF 1 | 2024-12-10 07:00 | 2024-12-11 17:00
C-52-0203-CMA02-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 | NDT (Tie-in Joint) | C-52-0203-CMA02-1030 | C-52-0203-CMA02-1030: SS 1 | C-52-0203-CMA02-1050 | C-52-0203-CMA02-1050: SS 1 | 2024-12-11 07:00 | 2024-12-12 17:00
C-52-0203-CMA02-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 | Ext. Joint Coating (Tie-in Joint) | C-52-0203-CMA02-1040 | C-52-0203-CMA02-1040: SS 1 | C-52-0203-CMA02-1060 | C-52-0203-CMA02-1060: FS | 2024-12-12 07:00 | 2024-12-13 17:00
C-52-0203-CMA02-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 | Holiday Testing | C-52-0203-CMA02-1050 | C-52-0203-CMA02-1050: FS | C-52-0203-CMA02-1070 | C-52-0203-CMA02-1070: SS | 2024-12-14 07:00 | 2024-12-14 17:00
C-52-0203-CMA02-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 | Padding & Back Filling | C-52-0203-CMA02-1060 | C-52-0203-CMA02-1060: SS | C-52-0203-PL-CA-5220, C-52-0203-PL-TE-8200, C-52-0203-PL-ME-7400, C-52-0203-PL-CI-6800, C-52-0203-PL-CI-6000 | C-52-0203-PL-CA-5220: FF 1, C-52-0203-PL-TE-8200: FF 1, C-52-0203-PL-ME-7400: FS, C-52-0203-PL-CI-6800: FF 1, C-52-0203-PL-CI-6000: FF 7 | 2024-12-14 07:00 | 2024-12-16 17:00
C-52-0203-CME01-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 | Trench Excavation | C-52-0203-PL-ME-2800 | C-52-0203-PL-ME-2800: SS 3 | C-52-0203-CME01-1010, C-52-0203-CME02-1000 | C-52-0203-CME01-1010: FS, C-52-0203-CME02-1000: FS 1 | 2024-10-26 07:00 | 2024-10-28 17:00
C-52-0203-CME01-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 | Bedding | C-52-0203-CME01-1000 | C-52-0203-CME01-1000: FS | C-52-0203-CME01-1020 | C-52-0203-CME01-1020: FS | 2024-10-29 07:00 | 2024-10-30 17:00
C-52-0203-CME01-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 | Lowering | C-52-0203-CME01-1010, C-52-0203-PL-ME-2800 | C-52-0203-CME01-1010: FS, C-52-0203-PL-ME-2800: SS 5 | C-52-0203-CME01-1030, C-52-0203-PL-CA-5600 | C-52-0203-CME01-1030: FS, C-52-0203-PL-CA-5600: FF | 2024-10-31 07:00 | 2024-11-01 17:00
C-52-0203-CME01-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 | Section Tie-in Welding | C-52-0203-CME01-1020 | C-52-0203-CME01-1020: FS | C-52-0203-CME01-1040, C-52-0203-PL-ME-4810 | C-52-0203-CME01-1040: FS, C-52-0203-PL-ME-4810: FF 1 | 2024-11-02 07:00 | 2024-11-05 17:00
C-52-0203-CME01-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 | NDT (Tie-in Joint) | C-52-0203-CME01-1030 | C-52-0203-CME01-1030: FS | C-52-0203-CME01-1050 | C-52-0203-CME01-1050: FS | 2024-11-06 07:00 | 2024-11-08 17:00
C-52-0203-CME01-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0203-CME01-1040 | C-52-0203-CME01-1040: FS | C-52-0203-CME01-1060 | C-52-0203-CME01-1060: FS | 2024-11-09 07:00 | 2024-11-12 17:00
C-52-0203-CME01-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 | Holiday Testing | C-52-0203-CME01-1050 | C-52-0203-CME01-1050: FS | C-52-0203-CME01-1070 | C-52-0203-CME01-1070: FS | 2024-11-13 07:00 | 2024-11-14 17:00
C-52-0203-CME01-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 | Padding & Back Filling | C-52-0203-CME01-1060 | C-52-0203-CME01-1060: FS | C-52-0203-PL-CA-5220, C-52-0203-PL-TE-8200, C-52-0203-PL-ME-7400, C-52-0203-PL-CI-6800, C-52-0203-PL-CI-6000 | C-52-0203-PL-CA-5220: FF 1, C-52-0203-PL-TE-8200: FF 1, C-52-0203-PL-ME-7400: FS, C-52-0203-PL-CI-6800: FF 1, C-52-0203-PL-CI-6000: FF 7 | 2024-11-15 07:00 | 2024-11-16 17:00
C-52-0203-CME03-1000 | Completed | P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 | Road Diversion & Trench Excavation | ML1002 | ML1002: FS | C-52-0203-CME03-1010 | C-52-0203-CME03-1010: FS 35 | 2024-09-27 | 2024-10-07
C-52-0203-CME03-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 | Bedding | C-52-0203-CME03-1000 | C-52-0203-CME03-1000: FS 35 | C-52-0203-CME03-1020 | C-52-0203-CME03-1020: FS | 2024-11-16 07:00 | 2024-11-18 17:00
C-52-0203-CME03-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 | Lowering | C-52-0203-CME03-1010 | C-52-0203-CME03-1010: FS | C-52-0203-CME03-1030 | C-52-0203-CME03-1030: FS | 2024-11-19 07:00 | 2024-11-20 17:00
C-52-0203-CME03-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 | Section Tie-in Welding | C-52-0203-CME03-1020 | C-52-0203-CME03-1020: FS | C-52-0203-CME03-1040, C-52-0203-PL-ME-4810 | C-52-0203-CME03-1040: FS, C-52-0203-PL-ME-4810: FF 1 | 2024-11-21 07:00 | 2024-11-23 17:00
C-52-0203-CME03-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 | NDT (Tie-in Joint) | C-52-0203-CME03-1030 | C-52-0203-CME03-1030: FS | C-52-0203-CME03-1050 | C-52-0203-CME03-1050: FS | 2024-11-25 07:00 | 2024-11-27 17:00
C-52-0203-CME03-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 | Ext. Joint Coating (Tie-in Joint) | C-52-0203-CME03-1040 | C-52-0203-CME03-1040: FS | C-52-0203-CME03-1060 | C-52-0203-CME03-1060: FS | 2024-11-28 07:00 | 2024-11-30 17:00
C-52-0203-CME03-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 | Holiday Testing | C-52-0203-CME03-1050 | C-52-0203-CME03-1050: FS | C-52-0203-CME03-1070 | C-52-0203-CME03-1070: FS | 2024-12-04 07:00 | 2024-12-05 17:00
C-52-0203-CME03-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 | Padding & Back Filling | C-52-0203-CME03-1060 | C-52-0203-CME03-1060: FS | C-52-0203-PL-CA-5220, C-52-0203-PL-TE-8200, C-52-0203-PL-ME-7400, C-52-0203-PL-CI-6800, C-52-0203-PL-CI-6000 | C-52-0203-PL-CA-5220: FF 1, C-52-0203-PL-TE-8200: FF 1, C-52-0203-PL-ME-7400: FS, C-52-0203-PL-CI-6800: FF 1, C-52-0203-PL-CI-6000: FF 7 | 2024-12-06 07:00 | 2024-12-09 17:00
C-52-0203-PL-CA-5600 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.20 | Installation of Temp. Anode | C-52-0203-PL-ME-4800, C-52-0203-CME01-1020 | C-52-0203-PL-ME-4800: SS 3, C-52-0203-CME01-1020: FF | C-52-0203-PL-CA-5200, C-52-0203-PL-CI-6000, C-52-0203-PL-CI-6000 | C-52-0203-PL-CA-5200: SS, C-52-0203-PL-CI-6000: SS, C-52-0203-PL-CI-6000: FF | 2024-12-09 07:00 | 2025-01-02 17:00
C-52-0203-PL-CA-5200 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.17 | Installation of CP Test Post | C-52-0203-PL-CA-5600, HS-CN-0090, ML1149-A07, HM-PL-0410 | C-52-0203-PL-CA-5600: SS, HS-CN-0090: FF, ML1149-A07: FF, HM-PL-0410: FS | C-52-0203-PL-CA-5210, ML1080 | C-52-0203-PL-CA-5210: FF 2, ML1080: FS | 2024-12-09 07:00 | 2025-01-02 17:00
C-52-0203-PL-CA-5210 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.17 | Glanding & Termination of Temp. CP S/m | C-52-0203-PL-CA-5200, C-52-0203-PL-CI-6000, C-52-0203-PL-CA-5240 | C-52-0203-PL-CA-5200: FF 2, C-52-0203-PL-CI-6000: FF, C-52-0203-PL-CA-5240: FF 1 | C-52-0203-PL-CA-5250 | C-52-0203-PL-CA-5250: FS | 2025-01-20 07:00 | 2025-02-12 17:00
C-52-0203-PL-CA-5220 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 | Installation of Test Post for Crossing | C-52-0203-CMA01-1060, C-52-0203-CMA02-1070, C-52-0203-CME01-1070, C-52-0203-CME02-1070, C-52-0203-CME03-1070, C-52-0203-CME04-1070, C-52-0203-PL-ME-2800, C-PER-1130, HM-PL-0410 | C-52-0203-CMA01-1060: FS, C-52-0203-CMA02-1070: FF 1, C-52-0203-CME01-1070: FF 1, C-52-0203-CME02-1070: FF 1, C-52-0203-CME03-1070: FF 1, C-52-0203-CME04-1070: FF 1, C-52-0203-PL-ME-2800: SF, C-PER-1130: FF, HM-PL-0410: FS | C-52-0203-PL-CA-5230, C-52-0203-PIPEL-5260 | C-52-0203-PL-CA-5230: SS 3, C-52-0203-PIPEL-5260: SS 4 | 2024-12-18 07:00 | 2025-01-22 17:00
C-52-0203-PL-CA-5230 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 | Installation of CP JB's | C-52-0203-PL-CA-5220 | C-52-0203-PL-CA-5220: SS 3 | C-52-0203-PL-CA-5240 | C-52-0203-PL-CA-5240: FS | 2024-12-21 07:00 | 2025-01-25 17:00
C-52-0203-PL-CA-5240 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 | Installation of CP TR | C-52-0203-PL-CA-5230, C-52-0203-PIPEL-5260 | C-52-0203-PL-CA-5230: FS, C-52-0203-PIPEL-5260: FS | C-52-0203-PL-CA-5250, C-52-0203-PL-CA-5210 | C-52-0203-PL-CA-5250: FS, C-52-0203-PL-CA-5210: FF 1 | 2025-01-27 07:00 | 2025-02-11 17:00
C-52-0203-PL-CA-5250 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 | CIP/DCVG Survey | C-52-0203-PL-CA-5240, C-52-0203-PL-CA-5210 | C-52-0203-PL-CA-5240: FS, C-52-0203-PL-CA-5210: FS | PRECOM-52-0203-1000, ML1080 | PRECOM-52-0203-1000: FS, ML1080: FS | 2025-02-13 07:00 | 2025-02-20 17:00
C-52-0203-PL-TE-8200 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.4.1 | FO - Cable Pulling/ Laying | C-52-0203-PL-CI-6000, C-52-0203-CMA01-1070, C-52-0203-CMA02-1070, C-52-0203-CME01-1070, C-52-0203-CME02-1070, C-52-0203-CME03-1070, C-52-0203-CME04-1070, HS-CN-0290, HM-EL-0180, HE-IC-3170, HM-EL-610, C-52-0203-PL-ME-2800, C-PER-1130 | C-52-0203-PL-CI-6000: FS, C-52-0203-CMA01-1070: FF 1, C-52-0203-CMA02-1070: FF 1, C-52-0203-CME01-1070: FF 1, C-52-0203-CME02-1070: FF 1, C-52-0203-CME03-1070: FF 1, C-52-0203-CME04-1070: FF 1, HS-CN-0290: FS, HM-EL-0180: FS, HE-IC-3170: FS, HM-EL-610: FS, | C-52-0203-PL-TE-8210 | C-52-0203-PL-TE-8210: FS | 2025-02-01 07:00 | 2025-02-25 17:00
C-52-0203-PL-TE-8210 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.4.1 | Termination/Splicing @ BVS | C-52-0203-PL-TE-8200 | C-52-0203-PL-TE-8200: FS | PRECOM-52-0203-1000, ML1080 | PRECOM-52-0203-1000: FS, ML1080: FS | 2025-02-26 07:00 | 2025-02-28 17:00
C-52-0203-PL-ME-7400 | Not Started | P2543-R01-Oct24..4.3.2.3.5.8.2.2 | Cleaning & Gauging | C-52-0203-PL-CI-6000, C-52-0203-CMA01-1070, C-52-0203-CMA02-1070, C-52-0203-CME01-1070, C-52-0203-CME02-1070, C-52-0203-CME03-1070, C-52-0203-CME04-1070, HS-CN-0090, ML1149-A07, C-52-0203-PL-CI-6810, C-52-0203-PL-CI-7200, C-52-0203-PL-ME-2800, C-PER-1130, | C-52-0203-PL-CI-6000: FS, C-52-0203-CMA01-1070: FS, C-52-0203-CMA02-1070: FS, C-52-0203-CME01-1070: FS, C-52-0203-CME02-1070: FS, C-52-0203-CME03-1070: FS, C-52-0203-CME04-1070: FS, HS-CN-0090: FF, ML1149-A07: FF, C-52-0203-PL-CI-6810: FS, C-52-0203-PL-CI- | C-52-0203-PL-ME-7410, C-52-0304-PL-ME-7400 | C-52-0203-PL-ME-7410: FS, C-52-0304-PL-ME-7400: FS | 2025-02-10 07:00 | 2025-02-20 17:00
C-52-0203-PL-ME-7410 | Not Started | P2543-R01-Oct24..4.3.2.3.5.8.2.2 | Water Filling | C-52-0203-PL-ME-7400 | C-52-0203-PL-ME-7400: FS | C-52-0203-PL-ME-7420 | C-52-0203-PL-ME-7420: FS | 2025-02-21 07:00 | 2025-02-28 17:00
C-52-0203-PL-ME-7420 | Not Started | P2543-R01-Oct24..4.3.2.3.5.8.2.2 | Stabilization & Pressurization | C-52-0203-PL-ME-7410, C-52-0203-PL-CI-7200 | C-52-0203-PL-ME-7410: FS, C-52-0203-PL-CI-7200: FF | C-52-0203-PL-ME-7430 | C-52-0203-PL-ME-7430: FS | 2025-03-01 07:00 | 2025-03-08 11:00
C-52-0203-PL-ME-7430 | Not Started | P2543-R01-Oct24..4.3.2.3.5.8.2.2 | Holding of Test Pressure | C-52-0203-PL-ME-7420 | C-52-0203-PL-ME-7420: FS | C-52-0203-PL-ME-7600, ML1779-E23 | C-52-0203-PL-ME-7600: FS, ML1779-E23: FS | 2025-03-08 11:00 | 2025-03-09 11:00
C-52-0203-PL-ME-7600 | Not Started | P2543-R01-Oct24..4.3.2.3.5.8.2.3 | De-Pressurization | C-52-0203-PL-ME-7430 | C-52-0203-PL-ME-7430: FS | C-52-0203-PL-ME-7610 | C-52-0203-PL-ME-7610: FS | 2025-03-09 11:00 | 2025-03-14 11:00
C-52-0203-PL-ME-7610 | Not Started | P2543-R01-Oct24..4.3.2.3.5.8.2.3 | De-watering | C-52-0203-PL-ME-7600 | C-52-0203-PL-ME-7600: FS | C-52-0203-PL-ME-7620 | C-52-0203-PL-ME-7620: FS | 2025-03-14 11:00 | 2025-03-22 09:00
C-52-0203-PL-ME-7620 | Not Started | P2543-R01-Oct24..4.3.2.3.5.8.2.3 | Swabing & Drying (Upto Dew Point Temp.) | C-52-0203-PL-ME-7610 | C-52-0203-PL-ME-7610: FS | PRECOM-52-0203-1000, ML1779-E23, ML1090 | PRECOM-52-0203-1000: FS, ML1779-E23: FS, ML1090: FS | 2025-03-22 09:00 | 2025-03-29 13:00
C-52-0203-PL-CI-6800 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.19 | Gatch Laying & Levelling | C-52-0203-PL-CI-6000, C-52-0203-CMA01-1070, C-52-0203-CMA02-1070, C-52-0203-CME01-1070, C-52-0203-CME02-1070, C-52-0203-CME03-1070, C-52-0203-CME04-1070, C-52-0203-PL-CI-6000, C-52-0203-PL-ME-2800, C-PER-1130 | C-52-0203-PL-CI-6000: SS 3, C-52-0203-CMA01-1070: FF 1, C-52-0203-CMA02-1070: FF 1, C-52-0203-CME01-1070: FF 1, C-52-0203-CME02-1070: FF 1, C-52-0203-CME03-1070: FF 1, C-52-0203-CME04-1070: FF 1, C-52-0203-PL-CI-6000: FF, C-52-0203-PL-ME-2800: SF, C-PER-11 | C-52-0203-PL-CI-6810, C-52-0203-PL-CI-6810 | C-52-0203-PL-CI-6810: SS 2, C-52-0203-PL-CI-6810: FF | 2024-12-31 07:00 | 2025-02-06 17:00
C-52-0203-PL-CI-6810 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.19 | Gatch Compaction | C-52-0203-PL-CI-6800, C-52-0203-PL-CI-6800 | C-52-0203-PL-CI-6800: SS 2, C-52-0203-PL-CI-6800: FF | C-52-0203-PL-CI-7800, C-52-0203-FENCE-1010, PRECOM-52-0203-1000, C-52-0203-PL-CI-7200, C-52-0203-PL-ME-7400 | C-52-0203-PL-CI-7800: SS 1, C-52-0203-FENCE-1010: FS, PRECOM-52-0203-1000: FS, C-52-0203-PL-CI-7200: FF, C-52-0203-PL-ME-7400: FS | 2025-01-03 07:00 | 2025-02-08 17:00
C-52-0203-PL-CI-7800 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.5 | Installation of Marker Post/Sign Board | C-52-0203-PL-CI-6810 | C-52-0203-PL-CI-6810: SS 1 | C-52-0203-PL-CI-7810, ML1080 | C-52-0203-PL-CI-7810: FF 1, ML1080: FS | 2025-01-04 07:00 | 2025-02-27 17:00
C-52-0203-PL-CI-7810 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.5 | Installation of Crash Barriers (If any) | C-52-0203-PL-CI-7800 | C-52-0203-PL-CI-7800: FF 1 | PRECOM-52-0203-1000, ML1080 | PRECOM-52-0203-1000: FS, ML1080: FS | 2025-01-06 07:00 | 2025-02-28 17:00
C-52-0203-CME02-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 | Trench Excavation | C-52-0203-CME01-1000 | C-52-0203-CME01-1000: FS 1 | C-52-0203-CME02-1010 | C-52-0203-CME02-1010: FS | 2024-10-30 07:00 | 2024-10-31 17:00
C-52-0203-CME02-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 | Bedding | C-52-0203-CME02-1000 | C-52-0203-CME02-1000: FS | C-52-0203-CME02-1020 | C-52-0203-CME02-1020: FS | 2024-11-01 07:00 | 2024-11-02 17:00
C-52-0203-CME02-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 | Lowering | C-52-0203-CME02-1010 | C-52-0203-CME02-1010: FS | C-52-0203-CME02-1030 | C-52-0203-CME02-1030: FS | 2024-11-04 07:00 | 2024-11-05 17:00
C-52-0203-CME02-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 | Section Tie-in Welding | C-52-0203-CME02-1020 | C-52-0203-CME02-1020: FS | C-52-0203-CME02-1040, C-52-0203-PL-ME-4810 | C-52-0203-CME02-1040: FS, C-52-0203-PL-ME-4810: FF 1 | 2024-11-06 07:00 | 2024-11-08 17:00
C-52-0203-CME02-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 | NDT (Tie-in Joint) | C-52-0203-CME02-1030 | C-52-0203-CME02-1030: FS | C-52-0203-CME02-1050 | C-52-0203-CME02-1050: FS | 2024-11-09 07:00 | 2024-11-12 17:00
C-52-0203-CME02-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 | Ext. Joint Coating (Tie-in Joint) | C-52-0203-CME02-1040 | C-52-0203-CME02-1040: FS | C-52-0203-CME02-1060 | C-52-0203-CME02-1060: FS | 2024-11-13 07:00 | 2024-11-15 17:00
C-52-0203-CME02-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 | Holiday Testing | C-52-0203-CME02-1050 | C-52-0203-CME02-1050: FS | C-52-0203-CME02-1070 | C-52-0203-CME02-1070: FS | 2024-11-16 07:00 | 2024-11-18 17:00
C-52-0203-CME02-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 | Padding & Back Filling | C-52-0203-CME02-1060 | C-52-0203-CME02-1060: FS | C-52-0203-PL-CA-5220, C-52-0203-PL-TE-8200, C-52-0203-PL-ME-7400, C-52-0203-PL-CI-6800, C-52-0203-PL-CI-6000 | C-52-0203-PL-CA-5220: FF 1, C-52-0203-PL-TE-8200: FF 1, C-52-0203-PL-ME-7400: FS, C-52-0203-PL-CI-6800: FF 1, C-52-0203-PL-CI-6000: FF 7 | 2024-11-19 07:00 | 2024-11-20 17:00
C-52-0304-PL-CI-1000 | Completed | P2543-R01-Oct24..4.3.1.3.20 | Survey Marking BVS-03 to BVS-04 | C-52-0203-PL-CI-1000 | C-52-0203-PL-CI-1000: FS | C-52-0304-PL-CI-1800, C-52-0405-PL-CI-1000 | C-52-0304-PL-CI-1800: FS, C-52-0405-PL-CI-1000: FS | 2024-03-01 | 2024-05-07
C-52-0304-PL-CI-1800 | Completed | P2543-R01-Oct24..4.3.1.3.16.21.1.8 | Non-Sabka ROW/Grading | C-52-0304-PL-CI-1000, C-GOV-1300 | C-52-0304-PL-CI-1000: FS, C-GOV-1300: SS | C-52-0304-CMA03-1000, C-52-0304-PL-CI-2000, C-52-0304-PL-CI-1400, C-52-0304-PL-CI-2000 | C-52-0304-CMA03-1000: FS, C-52-0304-PL-CI-2000: SS, C-52-0304-PL-CI-1400: FS 45, C-52-0304-PL-CI-2000: FF | 2024-03-01 | 2024-09-07
C-52-0304-PL-CI-2000 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.1.6 | Sabka Gatch Laying (Including ROW) - Layer 1 | C-52-0304-PL-CI-1800, C-52-0304-PL-CI-1800 | C-52-0304-PL-CI-1800: SS, C-52-0304-PL-CI-1800: FF | C-52-0304-PL-CI-2200, C-52-0304-PL-CI-2200 | C-52-0304-PL-CI-2200: SS 2, C-52-0304-PL-CI-2200: FF 2 | 2024-03-18 | 2024-11-02 07:30
C-52-0304-PL-CI-2010 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.1.6 | Sabka Gatch Laying - Layer 2 | C-52-0304-PL-CI-2200, C-52-0304-PL-CI-2200 | C-52-0304-PL-CI-2200: SS 2, C-52-0304-PL-CI-2200: FF 2 | C-52-0304-PL-CI-2210, C-52-0304-PL-CI-2210 | C-52-0304-PL-CI-2210: SS 2, C-52-0304-PL-CI-2210: FF 2 | 2024-05-10 | 2024-11-07 07:30
C-52-0304-PL-CI-2020 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.1.6 | Sabka Gatch Laying - Layer 3 | C-52-0304-PL-CI-2210, C-52-0304-PL-CI-2210 | C-52-0304-PL-CI-2210: SS 2, C-52-0304-PL-CI-2210: FF 2 | C-52-0304-PL-CI-2220, C-52-0304-PL-CI-2220 | C-52-0304-PL-CI-2220: SS 2, C-52-0304-PL-CI-2220: FF 2 | 2024-05-16 | 2024-11-12 07:30
C-52-0304-PL-CI-2030 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.1.6 | Sabka Gatch Laying - Layer 4 | C-52-0304-PL-CI-2220, C-52-0304-PL-CI-2220 | C-52-0304-PL-CI-2220: SS 2, C-52-0304-PL-CI-2220: FF 2 | C-52-0304-PL-CI-2230, C-52-0304-PL-CI-2230 | C-52-0304-PL-CI-2230: SS 2, C-52-0304-PL-CI-2230: FF 2 | 2024-05-23 | 2024-11-16 07:30
C-52-0304-PL-CI-2200 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.1.6 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-0304-PL-CI-2000, C-52-0304-PL-CI-2000 | C-52-0304-PL-CI-2000: SS 2, C-52-0304-PL-CI-2000: FF 2 | C-52-0304-CMA04-0970, C-52-0304-PL-CI-2010, C-52-0304-PL-CI-2010 | C-52-0304-CMA04-0970: SS 21, C-52-0304-PL-CI-2010: SS 2, C-52-0304-PL-CI-2010: FF 2 | 2024-03-25 | 2024-11-05 07:30
C-52-0304-PL-CI-2210 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.1.6 | Sabka Gatch Compaction - Layer 2 | C-52-0304-PL-CI-2010, C-52-0304-PL-CI-2010 | C-52-0304-PL-CI-2010: SS 2, C-52-0304-PL-CI-2010: FF 2 | C-52-0304-PL-CI-2020, C-52-0304-PL-CI-2020 | C-52-0304-PL-CI-2020: SS 2, C-52-0304-PL-CI-2020: FF 2 | 2024-05-15 | 2024-11-09 07:30
C-52-0304-PL-CI-2220 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.1.6 | Sabka Gatch Compaction - Layer 3 | C-52-0304-PL-CI-2020, C-52-0304-PL-CI-2020 | C-52-0304-PL-CI-2020: SS 2, C-52-0304-PL-CI-2020: FF 2 | C-52-0304-PL-CI-2030, C-52-0304-PL-CI-2030 | C-52-0304-PL-CI-2030: SS 2, C-52-0304-PL-CI-2030: FF 2 | 2024-05-17 | 2024-11-14 07:30
C-52-0304-PL-CI-2230 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.1.6 | Sabka Gatch Compaction - Layer 4 | C-52-0304-PL-CI-2030, C-52-0304-PL-CI-2030 | C-52-0304-PL-CI-2030: SS 2, C-52-0304-PL-CI-2030: FF 2 | C-52-0304-PL-ME-2800, C-52-0304-PL-CI-2400, ML1669-E12, C-52-0304-PL-ME-2800 | C-52-0304-PL-ME-2800: SS 2, C-52-0304-PL-CI-2400: FS, ML1669-E12: FS, C-52-0304-PL-ME-2800: FF 2 | 2024-05-24 | 2024-11-19 07:30
C-52-0304-PL-ME-2800 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.1.10 | Stringing (BVS-03 to BVS-04) | C-52-0304-PL-CI-2230, HM-PL-0100, C-52-0304-PL-CI-2230, C-52-0102-PL-ME-2800 | C-52-0304-PL-CI-2230: SS 2, HM-PL-0100: SS, C-52-0304-PL-CI-2230: FF 2, C-52-0102-PL-ME-2800: SS | C-52-0304-PL-ME-3600, C-52-0304-CMA04-1020, C-52-0304-CME01-1020, C-52-0405-PL-ME-2800, C-52-0304-PL-ME-4810, C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, PRECOM-52-0304-1000, C-52-0304-PL-CI-6000, ML1679-E13, C-5 | C-52-0304-PL-ME-3600: SS, C-52-0304-CMA04-1020: FS 7, C-52-0304-CME01-1020: FS 7, C-52-0405-PL-ME-2800: SS, C-52-0304-PL-ME-4810: SF, C-52-0304-PL-CA-5220: SF, C-52-0304-PL-TE-8200: SF, C-52-0304-PL-ME-7400: SS, C-52-0304-PL-CI-6800: SF, PRECOM-52-0304-100 | 2024-09-06 | 2024-11-29 07:30
C-52-0304-PL-ME-3600 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.12 | Automatic Welding | C-52-0304-PL-ME-2800, HM-PL-0880, C-COM-1010, C-52-0203-PL-ME-3600 | C-52-0304-PL-ME-2800: SS, HM-PL-0880: FS, C-COM-1010: FS, C-52-0203-PL-ME-3600: FS | C-52-0304-PL-ME-4000, ML1709-E16, ML1719-E17, C-52-0304-PL-CI-2400, C-52-0304-PL-ME-4000, C-52-0304-PL-CI-2400, C-52-0405-PL-ME-3600, ML1699-E15, C-56-01HG-PL-ME-3800 | C-52-0304-PL-ME-4000: SS 1, ML1709-E16: FS, ML1719-E17: FS, C-52-0304-PL-CI-2400: SS 3, C-52-0304-PL-ME-4000: FF 1, C-52-0304-PL-CI-2400: FF 3, C-52-0405-PL-ME-3600: FS, ML1699-E15: FF, C-56-01HG-PL-ME-3800: FS | 2024-12-05 07:00 | 2025-01-09 17:00
C-52-0304-PL-ME-4000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.13 | NDT | C-52-0304-PL-ME-3600, HS-CN-0190, C-52-0304-PL-ME-3600 | C-52-0304-PL-ME-3600: SS 1, HS-CN-0190: FS, C-52-0304-PL-ME-3600: FF 1 | C-52-0304-PL-ME-4400, C-52-0304-PL-ME-4400 | C-52-0304-PL-ME-4400: SS 2, C-52-0304-PL-ME-4400: FF 2 | 2024-12-06 07:00 | 2025-01-29 17:00
C-52-0304-PL-ME-4400 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.14 | Ext. Joint Coating | C-52-0304-PL-ME-4000, C-52-0304-PL-ME-4000 | C-52-0304-PL-ME-4000: SS 2, C-52-0304-PL-ME-4000: FF 2 | C-52-0304-PL-ME-4800, C-52-0304-PL-ME-4800 | C-52-0304-PL-ME-4800: SS 3, C-52-0304-PL-ME-4800: FF 3 | 2024-12-09 07:00 | 2025-01-31 17:00
C-52-0304-PL-CI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.9 | Trench Excavation | C-52-0304-PL-CI-2230, C-52-0304-PL-CI-1400, C-52-0304-PL-ME-3600, C-52-0304-PL-ME-3600 | C-52-0304-PL-CI-2230: FS, C-52-0304-PL-CI-1400: FS, C-52-0304-PL-ME-3600: SS 3, C-52-0304-PL-ME-3600: FF 3 | C-52-0304-PL-CI-2410, C-52-0304-PL-CI-2410 | C-52-0304-PL-CI-2410: SS 3, C-52-0304-PL-CI-2410: FF 3 | 2024-12-14 07:00 | 2025-01-13 17:00
C-52-0304-PL-CI-2410 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.9 | Bedding | C-52-0304-PL-CI-2400, C-52-0304-PL-CI-2400 | C-52-0304-PL-CI-2400: SS 3, C-52-0304-PL-CI-2400: FF 3 | C-52-0304-PL-ME-4800, C-52-0304-PL-ME-4800, C-52-0405-PL-CI-2410 | C-52-0304-PL-ME-4800: SS 3, C-52-0304-PL-ME-4800: FF 3, C-52-0405-PL-CI-2410: FS | 2024-12-18 07:00 | 2025-01-16 17:00
C-52-0304-PL-ME-4800 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.18 | Lowering | C-52-0304-PL-CI-2410, C-52-0304-PL-ME-4400, C-52-0304-PL-CI-2410, C-52-0304-PL-ME-4400 | C-52-0304-PL-CI-2410: SS 3, C-52-0304-PL-ME-4400: SS 3, C-52-0304-PL-CI-2410: FF 3, C-52-0304-PL-ME-4400: FF 3 | C-52-0304-PL-ME-4810, C-52-0304-PL-ME-3200, ML1729-E18, C-52-0304-PL-ME-3200, C-52-0304-PL-ME-4810 | C-52-0304-PL-ME-4810: SS, C-52-0304-PL-ME-3200: SS, ML1729-E18: FS, C-52-0304-PL-ME-3200: FF, C-52-0304-PL-ME-4810: FF | 2024-12-26 07:00 | 2025-02-04 17:00
C-52-0304-PL-ME-4810 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.18 | Section Tie-in Welding | C-52-0304-PL-ME-4800, C-52-0304-CMA04-1030, C-52-0304-CMA05-1030, C-52-0304-CMA01-1030, C-52-0304-CMA07-1030, C-52-0304-CMA02-1030, C-52-0304-CMA14-1030, C-52-0304-CMA09-1030, C-52-0304-CMA06-1030, C-52-0304-CMA11-1030, C-52-0304-CMA12-1030, C-52-0304-CMA1 | C-52-0304-PL-ME-4800: SS, C-52-0304-CMA04-1030: FF 1, C-52-0304-CMA05-1030: FF 1, C-52-0304-CMA01-1030: FF 1, C-52-0304-CMA07-1030: FF 1, C-52-0304-CMA02-1030: FF 1, C-52-0304-CMA14-1030: FF 1, C-52-0304-CMA09-1030: FF 1, C-52-0304-CMA06-1030: FF 1, C-52-0 | C-52-0304-PL-ME-4820, C-52-0304-PL-ME-4820 | C-52-0304-PL-ME-4820: SS 1, C-52-0304-PL-ME-4820: FF 1 | 2024-12-26 07:00 | 2025-02-17 17:00
C-52-0304-PL-ME-4820 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.18 | NDT (Tie-in Joint) | C-52-0304-PL-ME-4810, C-52-0304-PL-ME-4810 | C-52-0304-PL-ME-4810: SS 1, C-52-0304-PL-ME-4810: FF 1 | C-52-0304-PL-ME-4410, C-52-0304-PL-ME-4410 | C-52-0304-PL-ME-4410: SS 1, C-52-0304-PL-ME-4410: FF 1 | 2024-12-27 07:00 | 2025-02-18 17:00
C-52-0304-PL-ME-4410 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.14 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-PL-ME-4820, C-52-0304-PL-ME-4820 | C-52-0304-PL-ME-4820: SS 1, C-52-0304-PL-ME-4820: FF 1 | C-52-0304-PL-ME-4830, C-52-0304-PL-ME-4830 | C-52-0304-PL-ME-4830: SS 1, C-52-0304-PL-ME-4830: FF 1 | 2024-12-28 07:00 | 2025-02-19 17:00
C-52-0304-PL-ME-4830 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.18 | Holiday Testing | C-52-0304-PL-ME-4410, C-52-0304-PL-ME-4410 | C-52-0304-PL-ME-4410: SS 1, C-52-0304-PL-ME-4410: FF 1 | C-52-0304-PL-CI-6000, C-52-0304-PL-CA-5600, C-52-0304-PL-CI-6000 | C-52-0304-PL-CI-6000: SS 1, C-52-0304-PL-CA-5600: SS, C-52-0304-PL-CI-6000: FF 1 | 2024-12-30 07:00 | 2025-02-20 17:00
C-52-0304-PL-CI-6000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.21 | Padding | C-52-0304-PL-ME-4830, C-52-0304-CMA01-1070, C-52-0304-CMA02-1070, C-52-0304-CMA03-1070, C-52-0304-CMA04-1070, C-52-0304-CMA05-1070, C-52-0304-CMA06-1070, C-52-0304-CMA07-1070, C-52-0304-CMA08-1070, C-52-0304-CMA09-1070, C-52-0304-CMA10-1070, C-52-0304-CMA1 | C-52-0304-PL-ME-4830: SS 1, C-52-0304-CMA01-1070: FF 1, C-52-0304-CMA02-1070: FF 1, C-52-0304-CMA03-1070: FF 1, C-52-0304-CMA04-1070: FF 1, C-52-0304-CMA05-1070: FF 1, C-52-0304-CMA06-1070: FF 1, C-52-0304-CMA07-1070: FF 1, C-52-0304-CMA08-1070: FF 1, C-52 | C-52-0304-PL-CA-5210, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, PRECOM-52-0304-1000, C-52-0304-PL-CI-6800 | C-52-0304-PL-CA-5210: FF, C-52-0304-PL-TE-8200: SS, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: SS 5, PRECOM-52-0304-1000: FS, C-52-0304-PL-CI-6800: FF 5 | 2024-12-31 07:00 | 2025-02-21 17:00
C-52-0304-PL-CI-1400 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.1.7 | Cut & Fill (@ Non-Sabkha) | C-52-0304-PL-CI-1800 | C-52-0304-PL-CI-1800: FS 45 | C-52-0304-PL-CI-2400, ML1669-E12 | C-52-0304-PL-CI-2400: FS, ML1669-E12: FS | 2024-08-12 09:30 | 2024-11-09 07:30
C-52-0405-PL-CI-1000 | Completed | P2543-R01-Oct24..4.3.1.3.20 | Survey Marking BVS-04 to BVS-05 | C-52-0304-PL-CI-1000 | C-52-0304-PL-CI-1000: FS | C-52-0405-PL-CI-1800, C-52-0506-PL-CI-1000 | C-52-0405-PL-CI-1800: FS, C-52-0506-PL-CI-1000: FS | 2024-04-26 | 2024-05-07
C-52-0405-PL-CI-1800 | In Progress | P2543-R01-Oct24..4.3.1.3.17.21.1.8 | Non-Sabka ROW/Grading | C-52-0405-PL-CI-1000, C-GOV-1300, HE-PL-0230 | C-52-0405-PL-CI-1000: FS, C-GOV-1300: FF 16, HE-PL-0230: FF | C-52-0405-PL-CI-1400, C-52-0405-PL-CI-2000 | C-52-0405-PL-CI-1400: SS, C-52-0405-PL-CI-2000: SS | 2024-04-25 | 2024-11-25 12:00
C-52-0405-PL-CI-2000 | In Progress | P2543-R01-Oct24..4.3.1.3.17.21.1.6 | Sabka Gatch Laying (Including ROW) - Layer 1 | C-52-0405-PL-CI-1800 | C-52-0405-PL-CI-1800: SS | C-52-0405-PL-CI-2200, C-52-0405-PL-CI-2200 | C-52-0405-PL-CI-2200: SS 5, C-52-0405-PL-CI-2200: FF 5 | 2024-04-25 | 2024-12-09 12:00
C-52-0405-PL-CI-2010 | In Progress | P2543-R01-Oct24..4.3.1.3.17.21.1.6 | Sabka Gatch Laying - Layer 2 | C-52-0405-PL-CI-2200, C-52-0405-PL-CI-2200 | C-52-0405-PL-CI-2200: SS 5, C-52-0405-PL-CI-2200: FF 5 | C-52-0405-PL-CI-2210, C-52-0405-PL-CI-2210 | C-52-0405-PL-CI-2210: SS 5, C-52-0405-PL-CI-2210: FF 5 | 2024-08-01 12:00 | 2024-12-20 12:00
C-52-0405-PL-CI-2020 | In Progress | P2543-R01-Oct24..4.3.1.3.17.21.1.6 | Sabka Gatch Laying - Layer 3 | C-52-0405-PL-CI-2210, C-52-0405-PL-CI-2210 | C-52-0405-PL-CI-2210: SS 5, C-52-0405-PL-CI-2210: FF 5 | C-52-0405-PL-CI-2220, C-52-0405-PL-CI-2220 | C-52-0405-PL-CI-2220: SS 5, C-52-0405-PL-CI-2220: FF 5 | 2024-08-05 12:00 | 2025-01-02 12:00
C-52-0405-PL-CI-2030 | In Progress | P2543-R01-Oct24..4.3.1.3.17.21.1.6 | Sabka Gatch Laying - Layer 4 | C-52-0405-PL-CI-2220, C-52-0405-PL-CI-2220 | C-52-0405-PL-CI-2220: SS 5, C-52-0405-PL-CI-2220: FF 5 | C-52-0405-PL-CI-2230, C-52-0405-PL-CI-2230 | C-52-0405-PL-CI-2230: SS 5, C-52-0405-PL-CI-2230: FF 5 | 2024-08-12 12:00 | 2025-01-14 12:00
C-52-0405-PL-CI-2200 | In Progress | P2543-R01-Oct24..4.3.1.3.17.21.1.6 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-0405-PL-CI-2000, C-52-0405-PL-CI-2000 | C-52-0405-PL-CI-2000: SS 5, C-52-0405-PL-CI-2000: FF 5 | C-52-0405-PL-CI-2010, C-52-0405-PL-CI-2010 | C-52-0405-PL-CI-2010: SS 5, C-52-0405-PL-CI-2010: FF 5 | 2024-04-25 | 2024-12-14 12:00
C-52-0405-PL-CI-2210 | In Progress | P2543-R01-Oct24..4.3.1.3.17.21.1.6 | Sabka Gatch Compaction - Layer 2 | C-52-0405-PL-CI-2010, C-52-0405-PL-CI-2010 | C-52-0405-PL-CI-2010: SS 5, C-52-0405-PL-CI-2010: FF 5 | C-52-0405-PL-CI-2020, C-52-0405-PL-CI-2020 | C-52-0405-PL-CI-2020: SS 5, C-52-0405-PL-CI-2020: FF 5 | 2024-08-03 12:00 | 2024-12-26 12:00
C-52-0405-PL-CI-2220 | In Progress | P2543-R01-Oct24..4.3.1.3.17.21.1.6 | Sabka Gatch Compaction - Layer 3 | C-52-0405-PL-CI-2020, C-52-0405-PL-CI-2020 | C-52-0405-PL-CI-2020: SS 5, C-52-0405-PL-CI-2020: FF 5 | C-52-0405-PL-CI-2030, C-52-0405-PL-CI-2030 | C-52-0405-PL-CI-2030: SS 5, C-52-0405-PL-CI-2030: FF 5 | 2024-08-07 12:00 | 2025-01-08 12:00
C-52-0405-PL-CI-2230 | In Progress | P2543-R01-Oct24..4.3.1.3.17.21.1.6 | Sabka Gatch Compaction - Layer 4 | C-52-0405-PL-CI-2030, C-52-0405-PL-CI-2030 | C-52-0405-PL-CI-2030: SS 5, C-52-0405-PL-CI-2030: FF 5 | C-52-0405-PL-ME-2800, C-52-0405-PL-CI-2400, ML1669-E12 | C-52-0405-PL-ME-2800: SS, C-52-0405-PL-CI-2400: FS, ML1669-E12: FS | 2024-08-16 12:00 | 2025-01-20 12:00
C-52-0405-PL-ME-2800 | In Progress | P2543-R01-Oct24..4.3.1.3.17.21.1.10 | Stringing (BVS-04 to BVS-05) | C-52-0405-PL-CI-2230, HM-PL-1460, ML1509-D3, C-52-0304-PL-ME-2800, C-52-0405-PL-CI-1400 | C-52-0405-PL-CI-2230: SS, HM-PL-1460: FF, ML1509-D3: FS 5, C-52-0304-PL-ME-2800: SS, C-52-0405-PL-CI-1400: SS 7 | C-52-0405-PL-ME-3600, C-52-0405-PL-CI-2400, C-52-0405-PL-CI-2400, C-52-0506-PL-ME-2800, C-52-0405-CME01-1000 | C-52-0405-PL-ME-3600: FS, C-52-0405-PL-CI-2400: SS 3, C-52-0405-PL-CI-2400: FF 3, C-52-0506-PL-ME-2800: FS, C-52-0405-CME01-1000: SS 1 | 2024-10-18 | 2025-01-14 12:00
C-52-0405-PL-ME-3600 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.12 | Automatic Welding | C-52-0405-PL-ME-2800, HM-PL-0880, C-COM-1010, C-52-0304-PL-ME-3600 | C-52-0405-PL-ME-2800: FS, HM-PL-0880: FS, C-COM-1010: FS, C-52-0304-PL-ME-3600: FS | C-52-0405-PL-ME-4000, C-52-0405-PL-ME-4000, ML1709-E16, ML1719-E17, C-52-0405-PL-CI-2400, C-52-0405-PL-CI-2400, C-52-0506-PL-ME-3600 | C-52-0405-PL-ME-4000: SS 1, C-52-0405-PL-ME-4000: FF, ML1709-E16: FS, ML1719-E17: FS, C-52-0405-PL-CI-2400: SS 3, C-52-0405-PL-CI-2400: FF 3, C-52-0506-PL-ME-3600: FS 0 | 2025-01-14 12:00 | 2025-02-24 12:00
C-52-0405-PL-ME-4000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.13 | NDT | C-52-0405-PL-ME-3600, C-52-0405-PL-ME-3600, HS-CN-0190 | C-52-0405-PL-ME-3600: SS 1, C-52-0405-PL-ME-3600: FF, HS-CN-0190: FS | C-52-0405-PL-ME-4400, C-52-0405-PL-ME-4400 | C-52-0405-PL-ME-4400: SS 2, C-52-0405-PL-ME-4400: FF 2 | 2025-01-15 12:00 | 2025-02-25 12:00
C-52-0405-PL-ME-4400 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.19 | Ext. Joint Coating | C-52-0405-PL-ME-4000, C-52-0405-PL-ME-4000 | C-52-0405-PL-ME-4000: SS 2, C-52-0405-PL-ME-4000: FF 2 | C-52-0405-PL-ME-4800, C-52-0405-PL-ME-4800 | C-52-0405-PL-ME-4800: SS 3, C-52-0405-PL-ME-4800: FF | 2025-01-17 12:00 | 2025-02-27 12:00
C-52-0405-PL-CI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.9 | Trench Excavation | C-52-0405-PL-CI-1400, C-52-0405-PL-ME-2800, C-52-0405-PL-ME-2800, C-52-0405-PL-CI-2230, C-52-0405-PL-ME-3600, C-52-0405-PL-ME-3600 | C-52-0405-PL-CI-1400: FS, C-52-0405-PL-ME-2800: SS 3, C-52-0405-PL-ME-2800: FF 3, C-52-0405-PL-CI-2230: FS, C-52-0405-PL-ME-3600: SS 3, C-52-0405-PL-ME-3600: FF 3 | C-52-0405-PL-CI-2410, C-52-0405-PL-CI-2410, C-52-0405-CMA23-1000, C-52-0405-CMA23-1000, C-52-0405-CMA08-1000, C-52-0405-CMA27-1000, C-52-0405-CMA03-0970, C-52-0405-CMA01-1000, C-52-0405-CMA22-1000 | C-52-0405-PL-CI-2410: SS 3, C-52-0405-PL-CI-2410: FF, C-52-0405-CMA23-1000: SS, C-52-0405-CMA23-1000: FF, C-52-0405-CMA08-1000: SS, C-52-0405-CMA27-1000: SS, C-52-0405-CMA03-0970: SS 3, C-52-0405-CMA01-1000: SS, C-52-0405-CMA22-1000: SS 30 | 2025-01-29 12:00 | 2025-02-27 12:00
C-52-0405-PL-CI-2410 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.9 | Bedding | C-52-0405-PL-CI-2400, C-52-0405-PL-CI-2400, C-52-0304-PL-CI-2410 | C-52-0405-PL-CI-2400: SS 3, C-52-0405-PL-CI-2400: FF, C-52-0304-PL-CI-2410: FS | C-52-0405-PL-ME-4800, C-52-0405-PL-ME-4800, C-52-0506-PL-CI-2410 | C-52-0405-PL-ME-4800: FF 5, C-52-0405-PL-ME-4800: SS 3, C-52-0506-PL-CI-2410: FS | 2025-02-01 12:00 | 2025-03-02 12:00
C-52-0405-PL-ME-4800 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.20 | Lowering | C-52-0405-PL-CI-2410, C-52-0405-PL-ME-4400, C-52-0405-PL-ME-4400, C-52-0405-PL-CI-2410 | C-52-0405-PL-CI-2410: FF 5, C-52-0405-PL-ME-4400: SS 3, C-52-0405-PL-ME-4400: FF, C-52-0405-PL-CI-2410: SS 3 | C-52-0405-PL-ME-4810, C-52-0405-PL-ME-3200, C-52-0405-PL-ME-4810, ML1729-E18, C-52-0405-PL-ME-3200 | C-52-0405-PL-ME-4810: SS, C-52-0405-PL-ME-3200: SS, C-52-0405-PL-ME-4810: FF, ML1729-E18: FS, C-52-0405-PL-ME-3200: FF | 2025-02-07 12:00 | 2025-03-10 10:00
C-52-0405-PL-ME-4810 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.20 | Section Tie-in Welding | C-52-0405-PL-ME-4800, C-52-0405-CMA01-1030, C-52-0405-CMA25-1030, C-52-0405-CMA20-1030, C-52-0405-CMA26-1030, C-52-0405-CMA21-1030, C-52-0405-CMA27-1030, C-52-0405-CMA22-1060, C-52-0405-CMA02-1030, C-52-0405-CMA03-1030, C-52-0405-CMA28-1030, C-52-0405-CMA2 | C-52-0405-PL-ME-4800: SS, C-52-0405-CMA01-1030: FF 1, C-52-0405-CMA25-1030: FF 1, C-52-0405-CMA20-1030: FF 1, C-52-0405-CMA26-1030: FF 1, C-52-0405-CMA21-1030: FF 1, C-52-0405-CMA27-1030: FF 1, C-52-0405-CMA22-1060: FF 1, C-52-0405-CMA02-1030: FF 1, C-52-0 | C-52-0405-PL-ME-4820, C-52-0405-PL-ME-4820 | C-52-0405-PL-ME-4820: SS 1, C-52-0405-PL-ME-4820: FF | 2025-04-22 13:00 | 2025-05-22 11:00
C-52-0405-PL-ME-4820 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.20 | NDT (Tie-in Joint) | C-52-0405-PL-ME-4810, C-52-0405-PL-ME-4810 | C-52-0405-PL-ME-4810: SS 1, C-52-0405-PL-ME-4810: FF | C-52-0405-PL-ME-4410, C-52-0405-PL-ME-4410 | C-52-0405-PL-ME-4410: SS 1, C-52-0405-PL-ME-4410: FF 1 | 2025-04-23 13:00 | 2025-05-23 11:00
C-52-0405-PL-ME-4410 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.19 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-PL-ME-4820, C-52-0405-PL-ME-4820 | C-52-0405-PL-ME-4820: SS 1, C-52-0405-PL-ME-4820: FF 1 | C-52-0405-PL-ME-4830, C-52-0405-PL-ME-4830 | C-52-0405-PL-ME-4830: SS 1, C-52-0405-PL-ME-4830: FF | 2025-04-24 13:00 | 2025-05-24 11:00
C-52-0405-PL-ME-4830 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.20 | Holiday Testing | C-52-0405-PL-ME-4410, C-52-0405-PL-ME-4410 | C-52-0405-PL-ME-4410: SS 1, C-52-0405-PL-ME-4410: FF | C-52-0405-PL-CI-6000, C-52-0405-PL-CA-5600, C-52-0405-PL-CI-6000, C-52-0405-PL-CA-5600 | C-52-0405-PL-CI-6000: SS 1, C-52-0405-PL-CA-5600: SS, C-52-0405-PL-CI-6000: FF, C-52-0405-PL-CA-5600: FF | 2025-04-25 13:00 | 2025-05-26 11:00
C-52-0405-PL-CI-6000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.22 | Padding | C-52-0405-PL-ME-4830, C-52-0405-CMA01-1070, C-52-0405-CMA02-1070, C-52-0405-CMA03-1070, C-52-0405-CMA04-1070, C-52-0405-CMA05-1070, C-52-0405-CMA06-1070, C-52-0405-CMA07-1070, C-52-0405-CMA08-1070, C-52-0405-CMA09-1070, C-52-0405-CMA10-1070, C-52-0405-CMA1 | C-52-0405-PL-ME-4830: SS 1, C-52-0405-CMA01-1070: FF, C-52-0405-CMA02-1070: FF, C-52-0405-CMA03-1070: FF, C-52-0405-CMA04-1070: FF, C-52-0405-CMA05-1070: FF, C-52-0405-CMA06-1070: FF, C-52-0405-CMA07-1070: FF, C-52-0405-CMA08-1070: FF, C-52-0405-CMA09-1070 | C-52-0405-PL-CA-5210, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, PRECOM-52-0405-1000, C-52-0405-PL-CI-6400, C-52-0405-PL-CI-6800 | C-52-0405-PL-CA-5210: FF, C-52-0405-PL-TE-8200: SS, C-52-0405-PL-ME-7400: FS, PRECOM-52-0405-1000: FS, C-52-0405-PL-CI-6400: FF 5, C-52-0405-PL-CI-6800: FS | 2025-04-28 13:00 | 2025-06-30 11:00
C-52-0405-PL-CI-1400 | In Progress | P2543-R01-Oct24..4.3.1.3.17.21.1.7 | Cut & Fill (@ Non-Sabkha) | C-52-0405-PL-CI-1800 | C-52-0405-PL-CI-1800: SS | C-52-0405-PL-CI-2400, ML1669-E12, C-52-0405-PL-ME-2800 | C-52-0405-PL-CI-2400: FS, ML1669-E12: FS, C-52-0405-PL-ME-2800: SS 7 | 2024-08-12 12:00 | 2024-12-26 12:00
C-52-0506-PL-CI-1000 | Completed | P2543-R01-Oct24..4.3.1.3.20 | Survey Marking BVS-05 to BVS-06 | C-52-0405-PL-CI-1000 | C-52-0405-PL-CI-1000: FS | C-52-0506-PL-CI-1800, C-52-0506-PL-CI-1900, C-52-06CR-PL-CI-1000 | C-52-0506-PL-CI-1800: SS 7, C-52-0506-PL-CI-1900: SS 3, C-52-06CR-PL-CI-1000: FS | 2024-06-06 07:30 | 2024-07-26 07:30
C-52-0506-PL-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.7 | Sabka ROW/Grading | C-52-0506-PL-CI-1000, C-GOV-1300 | C-52-0506-PL-CI-1000: SS 7, C-GOV-1300: FS | C-52-0506-PL-CI-1400, C-52-0506-PL-ME-2800, C-52-0506-PL-CI-1900 | C-52-0506-PL-CI-1400: FS 30, C-52-0506-PL-ME-2800: SS 5, C-52-0506-PL-CI-1900: FS 30 | 2024-11-01 12:00 | 2024-12-16 11:00
C-52-0506-PL-ME-2800 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.11 | Stringing (BVS-05 to BVS-06) | C-52-0506-PL-CI-1800, C-52-0506-PL-CI-1400, C-52-0506-PL-CI-1900, C-52-0506-PL-CI-1600, HM-PL-0090, C-52-0506-PL-CI-1400, C-52-0506-PL-CI-1600, C-52-0405-PL-ME-2800 | C-52-0506-PL-CI-1800: SS 5, C-52-0506-PL-CI-1400: SS 5, C-52-0506-PL-CI-1900: SS 5, C-52-0506-PL-CI-1600: FF 5, HM-PL-0090: FS 4, C-52-0506-PL-CI-1400: FF 3, C-52-0506-PL-CI-1600: SS 3, C-52-0405-PL-ME-2800: FS | C-52-0506-PL-ME-3600, C-52-0506-CME01-1020, C-52-0506-PL-CI-2400, C-52-0506-PL-CI-2400, C-52-06CR-PL-ME-2800, C-52-0506-CME01-1000 | C-52-0506-PL-ME-3600: FS, C-52-0506-CME01-1020: SS 21, C-52-0506-PL-CI-2400: SS 7, C-52-0506-PL-CI-2400: FF 3, C-52-06CR-PL-ME-2800: FS, C-52-0506-CME01-1000: FS 1 | 2025-03-18 07:00 | 2025-04-16 17:00
C-52-0506-PL-ME-3600 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.13 | Automatic Welding | C-52-0506-PL-ME-2800, HM-PL-0880, C-COM-1010, C-52-0405-PL-ME-3600 | C-52-0506-PL-ME-2800: FS, HM-PL-0880: FS, C-COM-1010: FS, C-52-0405-PL-ME-3600: FS 0 | C-52-0506-PL-ME-4000, ML1719-E17, C-52-0506-PL-CI-2400, C-52-0506-PL-CI-2400, C-52-0506-PL-ME-4000, C-52-06CR-PL-ME-3600 | C-52-0506-PL-ME-4000: SS 2, ML1719-E17: FS, C-52-0506-PL-CI-2400: SS 3, C-52-0506-PL-CI-2400: FF 3, C-52-0506-PL-ME-4000: FF 2, C-52-06CR-PL-ME-3600: FS | 2025-04-17 07:00 | 2025-06-14 15:00
C-52-0506-PL-ME-4000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.14 | NDT | C-52-0506-PL-ME-3600, HS-CN-0190, C-52-0506-PL-ME-3600 | C-52-0506-PL-ME-3600: SS 2, HS-CN-0190: FS, C-52-0506-PL-ME-3600: FF 2 | C-52-0506-PL-ME-4400, C-52-0506-PL-ME-4400 | C-52-0506-PL-ME-4400: SS 2, C-52-0506-PL-ME-4400: FF 2 | 2025-04-19 07:00 | 2025-06-17 15:00
C-52-0506-PL-ME-4400 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.15 | Ext. Joint Coating | C-52-0506-PL-ME-4000, C-52-0506-PL-ME-4000 | C-52-0506-PL-ME-4000: SS 2, C-52-0506-PL-ME-4000: FF 2 | C-52-0506-PL-ME-4800, C-52-0506-PL-ME-4800 | C-52-0506-PL-ME-4800: SS 3, C-52-0506-PL-ME-4800: FF 3 | 2025-04-22 07:00 | 2025-06-19 15:00
C-52-0506-PL-CI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.9 | Trench Excavation | C-52-0506-PL-CI-1400, C-52-0506-PL-CI-1600, C-52-0506-PL-ME-2800, C-52-0506-PL-ME-2800, C-52-0506-PL-ME-3600, C-52-0506-PL-ME-3600 | C-52-0506-PL-CI-1400: FS, C-52-0506-PL-CI-1600: FS, C-52-0506-PL-ME-2800: SS 7, C-52-0506-PL-ME-2800: FF 3, C-52-0506-PL-ME-3600: SS 3, C-52-0506-PL-ME-3600: FF 3 | C-52-0506-PL-CI-2410, C-52-0506-PL-CI-2410 | C-52-0506-PL-CI-2410: SS 5, C-52-0506-PL-CI-2410: FF 5 | 2025-04-21 07:00 | 2025-06-18 15:00
C-52-0506-PL-CI-2410 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.9 | Bedding | C-52-0506-PL-CI-2400, C-52-0405-PL-CI-2410, C-52-0506-PL-CI-2400 | C-52-0506-PL-CI-2400: SS 5, C-52-0405-PL-CI-2410: FS, C-52-0506-PL-CI-2400: FF 5 | C-52-0506-PL-ME-4800, C-52-0506-PL-ME-4800 | C-52-0506-PL-ME-4800: FF 5, C-52-0506-PL-ME-4800: SS 5 | 2025-04-26 07:00 | 2025-06-24 15:00
C-52-0506-PL-ME-4800 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.16 | Lowering | C-52-0506-PL-CI-2410, C-52-0506-PL-ME-4400, C-52-0506-PL-ME-4400, C-52-0506-PL-CI-2410 | C-52-0506-PL-CI-2410: FF 5, C-52-0506-PL-ME-4400: SS 3, C-52-0506-PL-ME-4400: FF 3, C-52-0506-PL-CI-2410: SS 5 | C-52-0506-PL-ME-4810, C-52-0506-PL-ME-3200, ML1729-E18, C-52-0506-PL-ME-3200, C-52-0506-PL-ME-4810 | C-52-0506-PL-ME-4810: SS, C-52-0506-PL-ME-3200: SS 7, ML1729-E18: FS, C-52-0506-PL-ME-3200: FF, C-52-0506-PL-ME-4810: FF | 2025-05-02 07:00 | 2025-07-01 15:00
C-52-0506-PL-ME-4810 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.16 | Section Tie-in Welding | C-52-0506-PL-ME-4800, C-52-0506-CMA06-1030, C-52-0506-CMA07-1030, C-52-0506-CMA04-1030, C-52-0506-CMA02-1030, C-52-0506-CMA08-1030, C-52-0506-CMA09-1030, C-52-0506-CMA03-1030, C-52-0506-CMA01-1030, C-52-0506-CMA05-1030, C-52-0506-CME01-1030, C-52-0506-CME0 | C-52-0506-PL-ME-4800: SS, C-52-0506-CMA06-1030: FF, C-52-0506-CMA07-1030: FF, C-52-0506-CMA04-1030: FF, C-52-0506-CMA02-1030: FF, C-52-0506-CMA08-1030: FF, C-52-0506-CMA09-1030: FF, C-52-0506-CMA03-1030: FF, C-52-0506-CMA01-1030: FF, C-52-0506-CMA05-1030: | C-52-0506-PL-ME-4820, C-52-0506-PL-CI-7200, C-52-0506-PL-ME-4820 | C-52-0506-PL-ME-4820: SS 2, C-52-0506-PL-CI-7200: SS, C-52-0506-PL-ME-4820: FF 2 | 2025-05-03 07:00 | 2025-07-02 15:00
C-52-0506-PL-ME-4820 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.16 | NDT (Tie-in Joint) | C-52-0506-PL-ME-4810, C-52-0506-PL-ME-4810 | C-52-0506-PL-ME-4810: SS 2, C-52-0506-PL-ME-4810: FF 2 | C-52-0506-PL-ME-4410, C-52-0506-PL-ME-4410 | C-52-0506-PL-ME-4410: SS 1, C-52-0506-PL-ME-4410: FF 1 | 2025-05-06 10:00 | 2025-07-04 15:00
C-52-0506-PL-ME-4410 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.15 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-PL-ME-4820, C-52-0506-PL-ME-4820 | C-52-0506-PL-ME-4820: SS 1, C-52-0506-PL-ME-4820: FF 1 | C-52-0506-PL-ME-4830, C-52-0506-PL-ME-4830 | C-52-0506-PL-ME-4830: SS 2, C-52-0506-PL-ME-4830: FF 2 | 2025-05-07 12:00 | 2025-07-05 15:00
C-52-0506-PL-ME-4830 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.16 | Holiday Testing | C-52-0506-PL-ME-4410, C-52-0506-PL-ME-4410 | C-52-0506-PL-ME-4410: SS 2, C-52-0506-PL-ME-4410: FF 2 | C-52-0506-PL-CI-6000, C-52-0506-PL-CA-5600, C-52-0506-PL-CI-6000 | C-52-0506-PL-CI-6000: SS 4, C-52-0506-PL-CA-5600: SS, C-52-0506-PL-CI-6000: FF 4 | 2025-05-09 15:00 | 2025-07-08 15:00
C-52-0506-PL-CI-6000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.22 | Padding | C-52-0506-PL-ME-4830, C-52-0506-CMA01-1070, C-52-0506-CMA02-1070, C-52-0506-CMA03-1070, C-52-0506-CMA04-1070, C-52-0506-CMA05-1070, C-52-0506-CME01-1070, C-52-0506-CME02-1070, C-52-0506-CME03-1070, C-52-0506-CME04-1070, C-52-0506-CME05-1070, C-52-0506-CME0 | C-52-0506-PL-ME-4830: SS 4, C-52-0506-CMA01-1070: FF, C-52-0506-CMA02-1070: FF, C-52-0506-CMA03-1070: FF, C-52-0506-CMA04-1070: FF, C-52-0506-CMA05-1070: FF, C-52-0506-CME01-1070: FF, C-52-0506-CME02-1070: FF, C-52-0506-CME03-1070: FF, C-52-0506-CME04-1070 | C-52-0506-PL-CA-5210, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, PRECOM-52-0506-1000, C-52-0506-PL-CI-6400, C-52-0506-PL-CI-6400, C-52-0506-PL-CI-6800 | C-52-0506-PL-CA-5210: FF, C-52-0506-PL-TE-8200: SS 2, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: SS 5, PRECOM-52-0506-1000: FS, C-52-0506-PL-CI-6400: SS 5, C-52-0506-PL-CI-6400: FF 5, C-52-0506-PL-CI-6800: FF 5 | 2025-05-14 15:00 | 2025-07-12 15:00
C-52-0506-PL-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.6 | Cut & Fill (@ Non-Sabkha) | C-52-0506-PL-CI-1800 | C-52-0506-PL-CI-1800: FS 30 | C-52-0506-PL-CI-2400, C-52-0506-PL-ME-2800, ML1669-E12, C-52-0506-PL-ME-2800, C-52-0506-PL-CI-1600 | C-52-0506-PL-CI-2400: FS, C-52-0506-PL-ME-2800: SS 5, ML1669-E12: FS, C-52-0506-PL-ME-2800: FF 3, C-52-0506-PL-CI-1600: FS | 2025-01-21 11:00 | 2025-02-25 11:00
C-52-06CR-PL-CI-1000 | Completed | P2543-R01-Oct24..4.3.1.3.20 | Survey Marking BVS-06 to Sweihan CRS | C-52-0506-PL-CI-1000 | C-52-0506-PL-CI-1000: FS | C-52-06CR-PL-CI-1800, C-52-06CR-PL-CI-1400 | C-52-06CR-PL-CI-1800: FS, C-52-06CR-PL-CI-1400: FS 3 | 2024-06-06 | 2024-07-26
C-52-06CR-PL-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.8 | Sabka ROW/Grading | C-52-06CR-PL-CI-1000, C-GOV-1300 | C-52-06CR-PL-CI-1000: FS, C-GOV-1300: SS 60 | C-52-06CR-PL-CI-1400, C-52-06CR-PL-CI-2000 | C-52-06CR-PL-CI-1400: FS 7, C-52-06CR-PL-CI-2000: FS | 2024-10-28 07:30 | 2024-12-10 07:30
C-52-06CR-PL-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.7 | Sabka Gatch Laying (Including ROW) - Layer 1 | C-52-06CR-PL-CI-1800 | C-52-06CR-PL-CI-1800: FS | C-52-06CR-PL-CI-2200, C-52-06CR-PL-CI-2200 | C-52-06CR-PL-CI-2200: SS 3, C-52-06CR-PL-CI-2200: FF 3 | 2024-12-10 07:30 | 2024-12-26 07:30
C-52-06CR-PL-CI-2010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.7 | Sabka Gatch Laying - Layer 2 | C-52-06CR-PL-CI-2200, C-52-06CR-PL-CI-2200 | C-52-06CR-PL-CI-2200: SS 3, C-52-06CR-PL-CI-2200: FF 3 | C-52-06CR-PL-CI-2210, C-52-06CR-PL-CI-2210 | C-52-06CR-PL-CI-2210: SS 3, C-52-06CR-PL-CI-2210: FF 3 | 2024-12-17 07:30 | 2025-01-03 07:30
C-52-06CR-PL-CI-2020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.7 | Sabka Gatch Laying - Layer 3 | C-52-06CR-PL-CI-2210, C-52-06CR-PL-CI-2210 | C-52-06CR-PL-CI-2210: SS 3, C-52-06CR-PL-CI-2210: FF 3 | C-52-06CR-PL-CI-2220, C-52-06CR-PL-CI-2220 | C-52-06CR-PL-CI-2220: SS 3, C-52-06CR-PL-CI-2220: FF 3 | 2024-12-24 07:30 | 2025-01-10 07:30
C-52-06CR-PL-CI-2030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.7 | Sabka Gatch Laying - Layer 4 | C-52-06CR-PL-CI-2220, C-52-06CR-PL-CI-2220 | C-52-06CR-PL-CI-2220: SS 3, C-52-06CR-PL-CI-2220: FF 3 | C-52-06CR-PL-CI-2230, C-52-06CR-PL-CI-2230 | C-52-06CR-PL-CI-2230: SS 3, C-52-06CR-PL-CI-2230: FF 3 | 2024-12-31 07:30 | 2025-01-17 07:30
C-52-06CR-PL-CI-2200 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.7 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-06CR-PL-CI-2000, C-52-06CR-PL-CI-2000 | C-52-06CR-PL-CI-2000: SS 3, C-52-06CR-PL-CI-2000: FF 3 | C-52-06CR-PL-CI-2010, C-52-06CR-PL-CI-2010 | C-52-06CR-PL-CI-2010: SS 3, C-52-06CR-PL-CI-2010: FF 3 | 2024-12-13 07:30 | 2024-12-30 07:30
C-52-06CR-PL-CI-2210 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.7 | Sabka Gatch Compaction - Layer 2 | C-52-06CR-PL-CI-2010, C-52-06CR-PL-CI-2010 | C-52-06CR-PL-CI-2010: SS 3, C-52-06CR-PL-CI-2010: FF 3 | C-52-06CR-PL-CI-2020, C-52-06CR-PL-CI-2020 | C-52-06CR-PL-CI-2020: SS 3, C-52-06CR-PL-CI-2020: FF 3 | 2024-12-20 07:30 | 2025-01-07 07:30
C-52-06CR-PL-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.7 | Sabka Gatch Compaction - Layer 3 | C-52-06CR-PL-CI-2020, C-52-06CR-PL-CI-2020 | C-52-06CR-PL-CI-2020: SS 3, C-52-06CR-PL-CI-2020: FF 3 | C-52-06CR-PL-CI-2030, C-52-06CR-PL-CI-2030 | C-52-06CR-PL-CI-2030: SS 3, C-52-06CR-PL-CI-2030: FF 3 | 2024-12-27 07:30 | 2025-01-14 07:30
C-52-06CR-PL-CI-2230 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.7 | Sabka Gatch Compaction - Layer 4 | C-52-06CR-PL-CI-2030, C-52-06CR-PL-CI-2030 | C-52-06CR-PL-CI-2030: SS 3, C-52-06CR-PL-CI-2030: FF 3 | C-52-06CR-PL-ME-2800, C-52-06CR-PL-CI-2400, ML1669-E12, C-52-06CR-PL-ME-2800 | C-52-06CR-PL-ME-2800: SS 5, C-52-06CR-PL-CI-2400: FS, ML1669-E12: FS, C-52-06CR-PL-ME-2800: FF 3 | 2025-01-04 07:30 | 2025-01-21 07:30
C-52-06CR-PL-ME-2800 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.15 | Stringing (BVS-06 to SW CRS) | C-52-06CR-PL-CI-2230, HM-PL-0080, HS-CN-730, HE-PL-0350, HM-PL-0880, C-52-06CR-PL-CI-2230, ML1399-D5, ML1669-E12, C-52-0506-PL-ME-2800 | C-52-06CR-PL-CI-2230: SS 5, HM-PL-0080: FS 4, HS-CN-730: FS, HE-PL-0350: FS, HM-PL-0880: FF, C-52-06CR-PL-CI-2230: FF 3, ML1399-D5: FS 5, ML1669-E12: FF, C-52-0506-PL-ME-2800: FS | C-52-06CR-PL-ME-3600, C-52-06CR-CMA11-1020, C-52-06CR-CME01-1020, C-52-06CR-PL-CI-2400, C-52-06CR-PL-CI-2400, C-52-06CR-CMA01-0970, C-52-06CR-CMA01-0970, C-52-06CR-PL-ME-3600, C-52-06CR-CME01-1000 | C-52-06CR-PL-ME-3600: SS 3, C-52-06CR-CMA11-1020: SS 7, C-52-06CR-CME01-1020: SS 14, C-52-06CR-PL-CI-2400: SS 3, C-52-06CR-PL-CI-2400: FF 3, C-52-06CR-CMA01-0970: SS 21, C-52-06CR-CMA01-0970: FF, C-52-06CR-PL-ME-3600: FF, C-52-06CR-CME01-1000: FS 1 | 2025-04-17 07:00 | 2025-05-15 15:00
C-52-06CR-PL-ME-3600 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.17 | Automatic Welding | C-52-06CR-PL-ME-2800, C-COM-1010, HS-CN-690, C-52-06CR-PL-ME-2800, C-52-0506-PL-ME-3600 | C-52-06CR-PL-ME-2800: SS 3, C-COM-1010: FS, HS-CN-690: FS, C-52-06CR-PL-ME-2800: FF, C-52-0506-PL-ME-3600: FS | C-52-06CR-PL-ME-4000, C-52-06CR-PL-ME-4000, ML1719-E17, C-52-06CR-PL-CI-2400, C-52-06CR-PL-CI-2400 | C-52-06CR-PL-ME-4000: SS 1, C-52-06CR-PL-ME-4000: FF 1, ML1719-E17: FS, C-52-06CR-PL-CI-2400: SS 2, C-52-06CR-PL-CI-2400: FF 2 | 2025-06-14 15:00 | 2025-07-21 15:00
C-52-06CR-PL-ME-4000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.18 | NDT | C-52-06CR-PL-ME-3600, C-52-06CR-PL-ME-3600, HS-CN-0190 | C-52-06CR-PL-ME-3600: SS 1, C-52-06CR-PL-ME-3600: FF 1, HS-CN-0190: FS | C-52-06CR-PL-ME-4400, C-52-06CR-PL-ME-4400 | C-52-06CR-PL-ME-4400: SS 1, C-52-06CR-PL-ME-4400: FF 1 | 2025-06-16 15:00 | 2025-07-22 15:00
C-52-06CR-PL-ME-4400 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.19 | Ext. Joint Coating | C-52-06CR-PL-ME-4000, C-52-06CR-PL-ME-4000 | C-52-06CR-PL-ME-4000: SS 1, C-52-06CR-PL-ME-4000: FF 1 | C-52-06CR-PL-ME-4800, C-52-06CR-PL-ME-4800 | C-52-06CR-PL-ME-4800: SS 1, C-52-06CR-PL-ME-4800: FF 1 | 2025-06-17 15:00 | 2025-07-23 15:00
C-52-06CR-PL-CI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.9 | Trench Excavation | C-52-06CR-PL-CI-2230, C-52-06CR-PL-CI-1400, C-52-06CR-PL-ME-2800, C-52-06CR-PL-ME-3600, C-52-06CR-PL-ME-3600, C-52-06CR-PL-ME-2800, ML1719-E17 | C-52-06CR-PL-CI-2230: FS, C-52-06CR-PL-CI-1400: FS, C-52-06CR-PL-ME-2800: SS 3, C-52-06CR-PL-ME-3600: SS 2, C-52-06CR-PL-ME-3600: FF 2, C-52-06CR-PL-ME-2800: FF 3, ML1719-E17: FF | C-52-06CR-PL-CI-2410, C-52-06CR-PL-CI-2410, C-52-06CR-CNM31-1000 | C-52-06CR-PL-CI-2410: SS 1, C-52-06CR-PL-CI-2410: FF 1, C-52-06CR-CNM31-1000: SS | 2025-06-17 15:00 | 2025-07-23 15:00
C-52-06CR-PL-CI-2410 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.9 | Bedding | C-52-06CR-PL-CI-2400, C-52-06CR-PL-CI-2400 | C-52-06CR-PL-CI-2400: SS 1, C-52-06CR-PL-CI-2400: FF 1 | C-52-06CR-PL-ME-4800, C-52-06CR-PL-ME-4800 | C-52-06CR-PL-ME-4800: FF 4, C-52-06CR-PL-ME-4800: SS 1 | 2025-06-18 15:00 | 2025-07-24 15:00
C-52-06CR-PL-ME-4800 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.20 | Lowering | C-52-06CR-PL-CI-2410, C-52-06CR-PL-ME-4400, C-52-06CR-PL-CI-2410, C-52-06CR-PL-ME-4400 | C-52-06CR-PL-CI-2410: FF 4, C-52-06CR-PL-ME-4400: SS 1, C-52-06CR-PL-CI-2410: SS 1, C-52-06CR-PL-ME-4400: FF 1 | C-52-06CR-PL-ME-4810, C-52-06CR-PL-ME-4810, C-52-06CR-PL-ME-3200, ML1729-E18 | C-52-06CR-PL-ME-4810: SS, C-52-06CR-PL-ME-4810: FF, C-52-06CR-PL-ME-3200: FF 1, ML1729-E18: FS | 2025-06-23 15:00 | 2025-07-29 15:00
C-52-06CR-PL-ME-4810 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.20 | Section Tie-in Welding | C-52-06CR-PL-ME-4800, C-52-06CR-CMA11-1030, C-52-06CR-CMA01-1030, C-52-06CR-CMA08-1030, C-52-06CR-CMA02-1030, C-52-06CR-CMA03-1030, C-52-06CR-CMA12-1030, C-52-06CR-CMA09-1030, C-52-06CR-CMA04-1030, C-52-06CR-CMA05-1030, C-52-06CR-CMA06-1030, C-52-06CR-CMA1 | C-52-06CR-PL-ME-4800: SS, C-52-06CR-CMA11-1030: FF 1, C-52-06CR-CMA01-1030: FF 1, C-52-06CR-CMA08-1030: FF 1, C-52-06CR-CMA02-1030: FF 1, C-52-06CR-CMA03-1030: FF 1, C-52-06CR-CMA12-1030: FF 1, C-52-06CR-CMA09-1030: FF 1, C-52-06CR-CMA04-1030: FF 1, C-52-0 | C-52-06CR-PL-ME-4820, C-52-06CR-PL-CI-7200, C-52-06CR-PL-ME-4820 | C-52-06CR-PL-ME-4820: SS 1, C-52-06CR-PL-CI-7200: SS, C-52-06CR-PL-ME-4820: FF 1 | 2025-06-24 15:00 | 2025-07-30 15:00
C-52-06CR-PL-ME-4820 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.20 | NDT (Tie-in Joint) | C-52-06CR-PL-ME-4810, C-52-06CR-PL-ME-4810 | C-52-06CR-PL-ME-4810: SS 1, C-52-06CR-PL-ME-4810: FF 1 | C-52-06CR-PL-ME-4410, C-52-06CR-PL-ME-4410 | C-52-06CR-PL-ME-4410: SS 1, C-52-06CR-PL-ME-4410: FF 1 | 2025-06-25 15:00 | 2025-07-31 15:00
C-52-06CR-PL-ME-4410 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.19 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-PL-ME-4820, C-52-06CR-PL-ME-4820 | C-52-06CR-PL-ME-4820: SS 1, C-52-06CR-PL-ME-4820: FF 1 | C-52-06CR-PL-ME-4830, C-52-06CR-PL-ME-4830 | C-52-06CR-PL-ME-4830: SS 1, C-52-06CR-PL-ME-4830: FF 1 | 2025-06-26 15:00 | 2025-08-01 15:00
C-52-06CR-PL-ME-4830 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.20 | Holiday Testing | C-52-06CR-PL-ME-4410, C-52-06CR-PL-ME-4410 | C-52-06CR-PL-ME-4410: SS 1, C-52-06CR-PL-ME-4410: FF 1 | C-52-06CR-PL-CI-6000, C-52-06CR-PL-CA-5600, C-52-06CR-PL-CI-6000, C-52-06CR-PL-CA-5600 | C-52-06CR-PL-CI-6000: SS 1, C-52-06CR-PL-CA-5600: SS, C-52-06CR-PL-CI-6000: FF 1, C-52-06CR-PL-CA-5600: FF | 2025-06-28 15:00 | 2025-08-02 15:00
C-52-06CR-PL-CI-6000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.23 | Padding | C-52-06CR-PL-ME-4830, C-52-06CR-CMA01-1070, C-52-06CR-CMA02-1070, C-52-06CR-CMA03-1070, C-52-06CR-CMA04-1070, C-52-06CR-CMA05-1070, C-52-06CR-CMA06-1070, C-52-06CR-CMA07-1070, C-52-06CR-CME01-1070, C-52-06CR-CME02-1070, C-52-06CR-CME03-1070, C-52-06CR-CME0 | C-52-06CR-PL-ME-4830: SS 1, C-52-06CR-CMA01-1070: FF, C-52-06CR-CMA02-1070: FF, C-52-06CR-CMA03-1070: FF, C-52-06CR-CMA04-1070: FF, C-52-06CR-CMA05-1070: FF, C-52-06CR-CMA06-1070: FF, C-52-06CR-CMA07-1070: FF, C-52-06CR-CME01-1070: FF, C-52-06CR-CME02-1070 | C-52-06CR-PL-CA-5210, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, PRECOM-52-06CR-1000, C-52-06CR-PL-CI-6400, C-52-06CR-PL-CI-6400, C-52-06CR-PL-TE-8200 | C-52-06CR-PL-CA-5210: FF, C-52-06CR-PL-TE-8200: SS 1, C-52-06CR-PL-ME-7400: FS, C-52-06CR-PL-CI-6800: SS 1, PRECOM-52-06CR-1000: FS, C-52-06CR-PL-CI-6400: SS 1, C-52-06CR-PL-CI-6400: FF 1, C-52-06CR-PL-TE-8200: FF | 2025-07-11 11:30 | 2025-08-15 11:30
C-52-06CR-PL-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.6 | Cut & Fill (@ Non-Sabkha) | C-52-06CR-PL-CI-1000, C-52-06CR-PL-CI-1800, HE-HS-0500, HS-CN-0490 | C-52-06CR-PL-CI-1000: FS 3, C-52-06CR-PL-CI-1800: FS 7, HE-HS-0500: FF 21, HS-CN-0490: FS | C-52-06CR-PL-CI-2400, ML1669-E12 | C-52-06CR-PL-CI-2400: FS, ML1669-E12: FS | 2024-12-18 07:30 | 2025-01-21 07:30
C-52-HG01-PL-CI-1000 | Completed | P2543-R01-Oct24..4.3.1.3.20 | Survey Marking HGCP to BVS-01 | HE-PL-0200, CTF-1000, CTF-1010 | HE-PL-0200: FS 5, CTF-1000: FS, CTF-1010: FS | C-52-HG01-CMA07-0970, C-52-HG01-PL-CI-1800, C-52-0102-PL-CI-1000, C-52-HG01-PL-CI-1800 | C-52-HG01-CMA07-0970: FS, C-52-HG01-PL-CI-1800: SS 6, C-52-0102-PL-CI-1000: FS, C-52-HG01-PL-CI-1800: FF | 2023-12-18 | 2024-04-30
C-52-HG01-PL-CI-1800 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.6 | Sabka ROW/Grading | C-52-HG01-PL-CI-1000, C-52-HG01-PL-CI-1000 | C-52-HG01-PL-CI-1000: SS 6, C-52-HG01-PL-CI-1000: FF | C-52-HG01-PL-CI-2000 | C-52-HG01-PL-CI-2000: SS 14 | 2023-12-18 | 2024-04-30
C-52-HG01-PL-CI-2000 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.6 | Sabka Gatch Laying (Including ROW) - Layer 1 | C-52-HG01-PL-CI-1800 | C-52-HG01-PL-CI-1800: SS 14 | C-52-HG01-PL-CI-2200, C-52-HG01-PL-CI-2200 | C-52-HG01-PL-CI-2200: SS 20, C-52-HG01-PL-CI-2200: FF 20 | 2023-12-20 | 2024-07-26
C-52-HG01-PL-CI-2010 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.6 | Sabka Gatch Laying - Layer 2 | C-52-HG01-PL-CI-2200, C-52-HG01-PL-CI-2200 | C-52-HG01-PL-CI-2200: SS 10, C-52-HG01-PL-CI-2200: FF 10 | C-52-HG01-PL-CI-2210, ML1659-E11, C-52-HG01-PL-CI-2210 | C-52-HG01-PL-CI-2210: SS 10, ML1659-E11: FS, C-52-HG01-PL-CI-2210: FF 10 | 2024-01-06 | 2024-07-26
C-52-HG01-PL-CI-2020 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.9 | Sabka Gatch Laying - Layer 3 | C-52-HG01-PL-CI-2210, C-52-HG01-PL-CI-2210 | C-52-HG01-PL-CI-2210: SS 21, C-52-HG01-PL-CI-2210: FF 21 | C-52-HG01-PL-CI-2220, C-52-HG01-PL-CI-2220 | C-52-HG01-PL-CI-2220: SS 7, C-52-HG01-PL-CI-2220: FF 7 | 2024-01-19 | 2024-07-26
C-52-HG01-PL-CI-2030 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.9 | Sabka Gatch Laying - Layer 4 | C-52-HG01-PL-CI-2220, C-52-HG01-PL-CI-2220 | C-52-HG01-PL-CI-2220: SS 10, C-52-HG01-PL-CI-2220: FF 10 | C-52-HG01-PL-CI-2230, C-52-HG01-PL-CI-2230 | C-52-HG01-PL-CI-2230: SS 10, C-52-HG01-PL-CI-2230: FF 10 | 2024-01-24 | 2024-07-26
C-52-HG01-PL-CI-2200 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.7 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-HG01-PL-CI-2000, C-52-HG01-PL-CI-2000 | C-52-HG01-PL-CI-2000: SS 20, C-52-HG01-PL-CI-2000: FF 20 | C-52-HG01-PL-CI-2010, C-52-HG01-PL-CI-2010 | C-52-HG01-PL-CI-2010: SS 10, C-52-HG01-PL-CI-2010: FF 10 | 2024-02-06 | 2024-07-26
C-52-HG01-PL-CI-2210 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.7 | Sabka Gatch Compaction - Layer 2 | C-52-HG01-PL-CI-2010, C-52-HG01-PL-CI-2010 | C-52-HG01-PL-CI-2010: SS 10, C-52-HG01-PL-CI-2010: FF 10 | C-52-HG01-PL-CI-2020, C-52-HG01-PL-CI-2020, ML1659-E11 | C-52-HG01-PL-CI-2020: SS 21, C-52-HG01-PL-CI-2020: FF 21, ML1659-E11: FS | 2024-01-13 | 2024-07-26
C-52-HG01-PL-CI-2220 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.12 | Sabka Gatch Compaction - Layer 3 | C-52-HG01-PL-CI-2020, C-52-HG01-PL-CI-2020 | C-52-HG01-PL-CI-2020: SS 7, C-52-HG01-PL-CI-2020: FF 7 | C-52-HG01-PL-CI-2030, C-52-HG01-PL-CI-2030 | C-52-HG01-PL-CI-2030: SS 10, C-52-HG01-PL-CI-2030: FF 10 | 2024-01-24 | 2024-07-26
C-52-HG01-PL-CI-2230 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.12 | Sabka Gatch Compaction - Layer 4 | C-52-HG01-PL-CI-2030, C-52-HG01-PL-CI-2030 | C-52-HG01-PL-CI-2030: SS 10, C-52-HG01-PL-CI-2030: FF 10 | C-52-HG01-CMA04-0970, C-52-HG01-PL-ME-2800, C-52-HG01-PL-CI-2400, C-52-HG01-PL-CI-2600, ML1659-E11, C-52-HG01-PL-ME-2800 | C-52-HG01-CMA04-0970: FS, C-52-HG01-PL-ME-2800: SS 7, C-52-HG01-PL-CI-2400: FS, C-52-HG01-PL-CI-2600: FS, ML1659-E11: FS, C-52-HG01-PL-ME-2800: FF 3 | 2024-01-25 | 2024-07-26
C-52-HG01-PL-ME-2800 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.11 | Stringing-Lot1 | C-52-HG01-PL-CI-2230, HM-PL-0080, HM-PL-0090, C-52-HG01-PL-CI-2230 | C-52-HG01-PL-CI-2230: SS 7, HM-PL-0080: FS, HM-PL-0090: FS, C-52-HG01-PL-CI-2230: FF 3 | C-52-HG01-PL-ME-3200, C-52-HG01-PL-ME-3600, C-52-HG01-PL-CI-2400, C-52-HG01-PL-ME-3600, C-52-HG01-PL-CI-2400, C-52-HG01-PL-ME-3000 | C-52-HG01-PL-ME-3200: FS, C-52-HG01-PL-ME-3600: SS, C-52-HG01-PL-CI-2400: SS 7, C-52-HG01-PL-ME-3600: FF, C-52-HG01-PL-CI-2400: FF 3, C-52-HG01-PL-ME-3000: FS | 2024-06-19 | 2024-07-26
C-52-HG01-PL-ME-3600 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.15 | Automatic Welding-Lot1 | C-52-HG01-PL-ME-2800, C-COM-1010, C-52-HG01-PL-ME-2800 | C-52-HG01-PL-ME-2800: SS, C-COM-1010: SS, C-52-HG01-PL-ME-2800: FF | C-52-HG01-PL-ME-4000, C-52-HG01-PL-ME-4000, ML1689-E14, ML1699-E15, ML1709-E16, ML1719-E17, C-52-HG01-PL-CI-2400, C-52-HG01-PL-ME-4810, C-52-HG01-PL-ME-4810, C-52-HG01-PL-ME-3800 | C-52-HG01-PL-ME-4000: SS 1, C-52-HG01-PL-ME-4000: FF 1, ML1689-E14: FS, ML1699-E15: FS, ML1709-E16: FS, ML1719-E17: FS, C-52-HG01-PL-CI-2400: FS 15, C-52-HG01-PL-ME-4810: FF, C-52-HG01-PL-ME-4810: SS, C-52-HG01-PL-ME-3800: FS | 2024-07-18 | 2024-09-05
C-52-HG01-PL-ME-4000 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.16 | NDT-Lot1 | C-52-HG01-PL-ME-3600, C-52-HG01-PL-ME-3600, HS-CN-0190 | C-52-HG01-PL-ME-3600: SS 1, C-52-HG01-PL-ME-3600: FF 1, HS-CN-0190: FS | C-52-HG01-PL-ME-4400, C-52-HG01-PL-ME-4200, C-52-HG01-PL-ME-4400 | C-52-HG01-PL-ME-4400: SS 2, C-52-HG01-PL-ME-4200: FS, C-52-HG01-PL-ME-4400: FF 2 | 2024-07-18 | 2024-09-05
C-52-HG01-PL-ME-4400 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.18 | Ext. Joint Coating-Lot1 | C-52-HG01-PL-ME-4000, C-52-HG01-PL-ME-4000 | C-52-HG01-PL-ME-4000: SS 2, C-52-HG01-PL-ME-4000: FF 2 | C-52-HG01-PL-ME-4800, C-52-HG01-PL-ME-4600, C-52-HG01-PL-ME-4800 | C-52-HG01-PL-ME-4800: SS 3, C-52-HG01-PL-ME-4600: FS, C-52-HG01-PL-ME-4800: FF 3 | 2024-08-02 15:48 | 2024-09-17
C-52-HG01-PL-CI-2400 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.8 | Trench Excavation-Lot1 | C-52-HG01-PL-CI-2230, C-52-HG01-PL-ME-2800, HE-SS-0030, ML1002, C-52-HG01-PL-ME-3600, C-52-HG01-PL-ME-2800 | C-52-HG01-PL-CI-2230: FS, C-52-HG01-PL-ME-2800: SS 7, HE-SS-0030: SS, ML1002: FS, C-52-HG01-PL-ME-3600: FS 15, C-52-HG01-PL-ME-2800: FF 3 | C-52-HG01-PL-CI-2410, C-52-HG01-CMA01-0970, C-52-HG01-PL-CI-2410, C-52-HG01-CMA02-0970, C-52-HG01-PL-CI-2600 | C-52-HG01-PL-CI-2410: SS 7, C-52-HG01-CMA01-0970: FS 5, C-52-HG01-PL-CI-2410: FF 7, C-52-HG01-CMA02-0970: FS 50, C-52-HG01-PL-CI-2600: FS | 2024-08-14 15:48 | 2024-09-18
C-52-HG01-PL-CI-2410 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.8 | Bedding-Lot1 | C-52-HG01-PL-CI-2400, C-52-HG01-PL-CI-2400 | C-52-HG01-PL-CI-2400: SS 7, C-52-HG01-PL-CI-2400: FF 7 | C-52-HG01-PL-ME-4800, C-52-HG01-PL-CI-2610, C-52-HG01-PL-ME-4800 | C-52-HG01-PL-ME-4800: FF 5, C-52-HG01-PL-CI-2610: FF, C-52-HG01-PL-ME-4800: SS 5 | 2024-08-19 15:48 | 2024-09-30
C-52-HG01-PL-ME-4800 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.25 | Lowering-Lot1 | C-52-HG01-PL-CI-2410, C-52-HG01-PL-ME-4400, C-52-HG01-PL-CI-2410, C-52-HG01-PL-ME-4400 | C-52-HG01-PL-CI-2410: FF 5, C-52-HG01-PL-ME-4400: SS 3, C-52-HG01-PL-CI-2410: SS 5, C-52-HG01-PL-ME-4400: FF 3 | C-52-HG01-PL-ME-4810, C-52-HG01-CME01-1000, C-52-HG01-PL-CA-5600, C-52-HG01-PL-ME-5000, C-52-HG01-CMA01-1020, ML1729-E18, ML1729-E18, C-52-HG01-PL-CA-5600, C-52-HG01-PL-ME-4810 | C-52-HG01-PL-ME-4810: SS, C-52-HG01-CME01-1000: SS 2, C-52-HG01-PL-CA-5600: SS 7, C-52-HG01-PL-ME-5000: FS, C-52-HG01-CMA01-1020: FS, ML1729-E18: FS, ML1729-E18: FF, C-52-HG01-PL-CA-5600: FF, C-52-HG01-PL-ME-4810: FF | 2024-09-13 | 2024-10-07
C-52-HG01-PL-ME-4810 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.25 | Section Tie-in Welding -Lot1 | C-52-HG01-PL-ME-4800, C-52-HG01-PL-ME-3200, C-52-HG01-PL-ME-4800, C-52-HG01-PL-ME-3600, C-52-HG01-PL-ME-3600 | C-52-HG01-PL-ME-4800: SS, C-52-HG01-PL-ME-3200: FF, C-52-HG01-PL-ME-4800: FF, C-52-HG01-PL-ME-3600: FF, C-52-HG01-PL-ME-3600: SS | C-52-HG01-PL-ME-4820, C-52-HG01-PL-ME-5010, C-52-HG01-PL-ME-4820 | C-52-HG01-PL-ME-4820: SS 1, C-52-HG01-PL-ME-5010: FS, C-52-HG01-PL-ME-4820: FF 1 | 2024-09-13 | 2024-10-07
C-52-HG01-PL-ME-4820 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.25 | NDT (Tie-in Joint)-Lot1 | C-52-HG01-PL-ME-4810, C-52-HG01-PL-ME-4810 | C-52-HG01-PL-ME-4810: SS 1, C-52-HG01-PL-ME-4810: FF 1 | C-52-HG01-PL-ME-4410, C-52-HG01-PL-ME-5020, C-52-HG01-PL-ME-4410 | C-52-HG01-PL-ME-4410: SS 1, C-52-HG01-PL-ME-5020: FS, C-52-HG01-PL-ME-4410: FF 1 | 2024-09-13 | 2024-10-07
C-52-HG01-PL-ME-4410 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.18 | Ext. Joint Coating (Tie-in Joint)-Lot1 | C-52-HG01-PL-ME-4820, C-52-HG01-PL-ME-4820 | C-52-HG01-PL-ME-4820: SS 1, C-52-HG01-PL-ME-4820: FF 1 | C-52-HG01-PL-ME-4830, C-52-HG01-PL-ME-4610, C-52-HG01-PL-CI-6000, C-52-HG01-PL-ME-4830 | C-52-HG01-PL-ME-4830: SS 1, C-52-HG01-PL-ME-4610: FS, C-52-HG01-PL-CI-6000: FF 7, C-52-HG01-PL-ME-4830: FF 1 | 2024-09-13 | 2024-10-07
C-52-HG01-PL-ME-4830 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.25 | Holiday Testing-Lot1 | C-52-HG01-PL-ME-4410, C-52-HG01-PL-ME-4410 | C-52-HG01-PL-ME-4410: SS 1, C-52-HG01-PL-ME-4410: FF 1 | C-52-HG01-PL-CI-6000, C-52-HG01-PL-ME-5030, C-52-HG01-PL-CI-6000 | C-52-HG01-PL-CI-6000: SS 1, C-52-HG01-PL-ME-5030: FS, C-52-HG01-PL-CI-6000: FF 7 | 2024-09-13 | 2024-10-07
C-52-HG01-PL-CI-6000 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.24 | Padding -Lot1 | C-52-HG01-PL-ME-4830, C-52-HG01-PL-ME-4830, C-52-HG01-PL-ME-4410 | C-52-HG01-PL-ME-4830: SS 1, C-52-HG01-PL-ME-4830: FF 7, C-52-HG01-PL-ME-4410: FF 7 | C-52-HG01-PL-CA-5210, C-52-HG01-PL-TE-8200, C-52-HG01-PL-ME-7400, C-52-HG01-PL-CI-6800, PRECOM-52-HG01-1000, C-52-HG01-PL-CI-6200, C-52-HG01-PL-CA-5220, C-52-HG01-PL-CI-6800 | C-52-HG01-PL-CA-5210: FF, C-52-HG01-PL-TE-8200: FF, C-52-HG01-PL-ME-7400: FS, C-52-HG01-PL-CI-6800: SS 5, PRECOM-52-HG01-1000: FS, C-52-HG01-PL-CI-6200: SS, C-52-HG01-PL-CA-5220: FF, C-52-HG01-PL-CI-6800: FF | 2024-09-13 | 2024-11-02 17:00
C-52-0102-PL-CI-1000 | Completed | P2543-R01-Oct24..4.3.1.3.20 | Survey Marking BVS-01 to BVS-02 | C-52-HG01-PL-CI-1000 | C-52-HG01-PL-CI-1000: FS | C-52-0102-PL-CI-1800, C-52-0203-PL-CI-1000, C-52-0102-PL-CI-1800 | C-52-0102-PL-CI-1800: SS 1, C-52-0203-PL-CI-1000: FS, C-52-0102-PL-CI-1800: FF 1 | 2024-03-01 07:30 | 2024-05-02 07:30
C-52-0102-PL-CI-1800 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.1.6 | Sabka ROW/Grading | C-52-0102-PL-CI-1000, C-52-0102-PL-CI-1000 | C-52-0102-PL-CI-1000: SS 1, C-52-0102-PL-CI-1000: FF 1 | C-52-0102-CMA04-0970, C-52-0102-PL-CI-2000, C-52-0102-PL-CI-2000 | C-52-0102-CMA04-0970: FF, C-52-0102-PL-CI-2000: SS 7, C-52-0102-PL-CI-2000: FF 7 | 2024-02-06 | 2024-07-29 16:47
C-52-0102-PL-CI-2000 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.1.6 | Sabka Gatch Laying (Including ROW) - Layer 1 | C-52-0102-PL-CI-1800, C-52-0102-PL-CI-1800 | C-52-0102-PL-CI-1800: SS 7, C-52-0102-PL-CI-1800: FF 7 | C-52-0102-PL-CI-2200, C-52-0102-PL-CI-2200 | C-52-0102-PL-CI-2200: SS 7, C-52-0102-PL-CI-2200: FF 7 | 2024-02-06 | 2024-08-06 16:47
C-52-0102-PL-CI-2010 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.1.6 | Sabka Gatch Laying - Layer 2 | C-52-0102-PL-CI-2200, C-52-0102-PL-CI-2200 | C-52-0102-PL-CI-2200: SS 7, C-52-0102-PL-CI-2200: FF 3 | C-52-0102-PL-CI-2210, C-52-0102-PL-CI-2210 | C-52-0102-PL-CI-2210: SS 14, C-52-0102-PL-CI-2210: FF 3 | 2024-02-20 | 2024-08-14 16:47
C-52-0102-PL-CI-2030 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.1.9 | Sabka Gatch Laying - Layer 3 | C-52-0102-PL-CI-2210, C-52-0102-PL-CI-2210 | C-52-0102-PL-CI-2210: SS 7, C-52-0102-PL-CI-2210: FF 3 | C-52-0102-PL-CI-2220, C-52-0102-PL-CI-2220 | C-52-0102-PL-CI-2220: SS 7, C-52-0102-PL-CI-2220: FF 3 | 2024-02-29 | 2024-08-24 16:47
C-52-0102-PL-CI-2040 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.1.9 | Sabka Gatch Laying - Layer 4 | C-52-0102-PL-CI-2220, C-52-0102-PL-CI-2220 | C-52-0102-PL-CI-2220: SS 7, C-52-0102-PL-CI-2220: FF 3 | C-52-0102-PL-CI-2230, C-52-0102-PL-CI-2230 | C-52-0102-PL-CI-2230: SS 7, C-52-0102-PL-CI-2230: FF 3 | 2024-03-06 | 2024-09-02
C-52-0102-PL-CI-2200 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.1.7 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-0102-PL-CI-2000, C-52-0102-PL-CI-2000 | C-52-0102-PL-CI-2000: SS 7, C-52-0102-PL-CI-2000: FF 7 | C-52-0203-CME04-1000, C-52-0102-PL-CI-2010, C-52-0102-PL-CI-2010 | C-52-0203-CME04-1000: FS, C-52-0102-PL-CI-2010: SS 7, C-52-0102-PL-CI-2010: FF 3 | 2024-03-28 | 2024-08-14 16:47
C-52-0102-PL-CI-2210 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.1.7 | Sabka Gatch Compaction - Layer 2 | C-52-0102-PL-CI-2010, C-52-0102-PL-CI-2010 | C-52-0102-PL-CI-2010: SS 14, C-52-0102-PL-CI-2010: FF 3 | C-52-0102-PL-CI-2030, C-52-0102-PL-CI-2030 | C-52-0102-PL-CI-2030: SS 7, C-52-0102-PL-CI-2030: FF 3 | 2024-02-27 | 2024-08-21 16:47
C-52-0102-PL-CI-2220 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.1.10 | Sabka Gatch Compaction - Layer 3 | C-52-0102-PL-CI-2030, C-52-0102-PL-CI-2030 | C-52-0102-PL-CI-2030: SS 7, C-52-0102-PL-CI-2030: FF 3 | C-52-0102-PL-CI-2040, C-52-0102-PL-CI-2040 | C-52-0102-PL-CI-2040: SS 7, C-52-0102-PL-CI-2040: FF 3 | 2024-03-04 | 2024-08-28 16:47
C-52-0102-PL-CI-2230 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.1.10 | Sabka Gatch Compaction - Layer 4 | C-52-0102-PL-CI-2040, C-52-0102-PL-CI-2040 | C-52-0102-PL-CI-2040: SS 7, C-52-0102-PL-CI-2040: FF 3 | C-52-0102-PL-ME-2800, C-52-0102-PL-CI-2400, ML1659-E11, C-52-0102-PL-ME-2800 | C-52-0102-PL-ME-2800: SS 7, C-52-0102-PL-CI-2400: FS 3, ML1659-E11: FS, C-52-0102-PL-ME-2800: FF 3 | 2024-03-18 | 2024-09-02
C-52-0102-PL-ME-2800 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.1.11 | Stringing (BVS-01 to BVS-02) | C-52-0102-PL-CI-2230, HM-PL-0100, C-52-0102-PL-CI-2230, C-52-HG01-PL-ME-3000 | C-52-0102-PL-CI-2230: SS 7, HM-PL-0100: FF, C-52-0102-PL-CI-2230: FF 3, C-52-HG01-PL-ME-3000: FF | C-52-0102-PL-ME-3200, C-52-0102-PL-ME-3600, C-52-0102-PL-CI-2400, C-52-0102-PL-CI-2400, C-52-0304-PL-ME-2800, C-52-0102-CME01-1000 | C-52-0102-PL-ME-3200: FF, C-52-0102-PL-ME-3600: SS 1, C-52-0102-PL-CI-2400: SS 7, C-52-0102-PL-CI-2400: FF 3, C-52-0304-PL-ME-2800: SS, C-52-0102-CME01-1000: FS 1 | 2024-08-12 07:00 | 2024-11-23 17:00
C-52-0102-PL-ME-3600 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.1.13 | Automatic Welding | C-52-0102-PL-ME-2800, C-COM-1010, C-52-HG01-PL-ME-3800 | C-52-0102-PL-ME-2800: SS 1, C-COM-1010: FS, C-52-HG01-PL-ME-3800: FF 6 | C-52-0102-PL-ME-4000, ML1699-E15, ML1709-E16, ML1719-E17, C-52-0102-PL-CI-2400, C-52-0102-PL-CI-2400, C-52-0102-PL-ME-4000, C-52-0203-PL-ME-3600 | C-52-0102-PL-ME-4000: SS 1, ML1699-E15: FS, ML1709-E16: FS, ML1719-E17: FS, C-52-0102-PL-CI-2400: SS 3, C-52-0102-PL-CI-2400: FF 3, C-52-0102-PL-ME-4000: FF 1, C-52-0203-PL-ME-3600: FS -32 | 2024-09-24 | 2024-11-28 17:00
C-52-0102-PL-ME-4000 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.1.18 | NDT | C-52-0102-PL-ME-3600, HS-CN-0190, C-52-0102-PL-ME-3600 | C-52-0102-PL-ME-3600: SS 1, HS-CN-0190: FS, C-52-0102-PL-ME-3600: FF 1 | C-52-0102-PL-ME-4400, C-52-0102-PL-ME-4400 | C-52-0102-PL-ME-4400: SS 2, C-52-0102-PL-ME-4400: FF | 2024-09-24 | 2024-11-30 17:00
C-52-0102-PL-ME-4400 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.1.17 | Ext. Joint Coating | C-52-0102-PL-ME-4000, C-52-0102-PL-ME-4000 | C-52-0102-PL-ME-4000: SS 2, C-52-0102-PL-ME-4000: FF | C-52-0102-PL-ME-4800, C-52-0102-PL-ME-4800 | C-52-0102-PL-ME-4800: SS 3, C-52-0102-PL-ME-4800: FF 3 | 2024-10-08 | 2024-12-05 17:00
C-52-0102-PL-CI-2400 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.1.8 | Trench Excavation | C-52-0102-PL-CI-2230, C-52-0102-PL-ME-2800, C-52-0102-PL-ME-3600, C-52-0102-PL-ME-3600, C-52-0102-PL-ME-2800 | C-52-0102-PL-CI-2230: FS 3, C-52-0102-PL-ME-2800: SS 7, C-52-0102-PL-ME-3600: SS 3, C-52-0102-PL-ME-3600: FF 3, C-52-0102-PL-ME-2800: FF 3 | C-52-0102-PL-CI-2410, C-52-0102-PL-CI-2410 | C-52-0102-PL-CI-2410: SS 2, C-52-0102-PL-CI-2410: FF 2 | 2024-10-08 | 2024-12-07 17:00
C-52-0102-PL-CI-2410 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.1.8 | Bedding | C-52-0102-PL-CI-2400, C-52-0102-PL-CI-2400 | C-52-0102-PL-CI-2400: SS 2, C-52-0102-PL-CI-2400: FF 2 | C-52-0102-PL-ME-4800, C-52-0102-PL-ME-4800 | C-52-0102-PL-ME-4800: FF 2, C-52-0102-PL-ME-4800: SS 2 | 2024-10-08 | 2024-12-10 17:00
C-52-0102-PL-ME-4800 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.19 | Lowering | C-52-0102-PL-CI-2410, C-52-0102-PL-ME-4400, C-52-0102-PL-CI-2410, C-52-0102-PL-ME-4400 | C-52-0102-PL-CI-2410: FF 2, C-52-0102-PL-ME-4400: SS 3, C-52-0102-PL-CI-2410: SS 2, C-52-0102-PL-ME-4400: FF 3 | C-52-0102-PL-ME-4810, C-52-0102-PL-CA-5600, ML1729-E18, C-52-0102-PL-ME-4810, C-52-0102-PL-CA-5600, C-52-0102-PL-ME-3200 | C-52-0102-PL-ME-4810: SS, C-52-0102-PL-CA-5600: SS 7, ML1729-E18: FS, C-52-0102-PL-ME-4810: FF, C-52-0102-PL-CA-5600: FF, C-52-0102-PL-ME-3200: FF 1 | 2024-11-21 07:00 | 2024-12-12 17:00
C-52-0102-PL-ME-4810 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.19 | Section Tie-in Welding | C-52-0102-PL-ME-4800, C-52-0102-PL-ME-3200, C-52-0102-PL-ME-4800 | C-52-0102-PL-ME-4800: SS, C-52-0102-PL-ME-3200: FF 2, C-52-0102-PL-ME-4800: FF | C-52-0102-PL-ME-4820, C-52-0102-PL-ME-4820 | C-52-0102-PL-ME-4820: SS 1, C-52-0102-PL-ME-4820: FF | 2024-11-23 07:00 | 2024-12-16 17:00
C-52-0102-PL-ME-4820 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.19 | NDT (Tie-in Joint) | C-52-0102-PL-ME-4810, C-52-0102-PL-ME-4810 | C-52-0102-PL-ME-4810: SS 1, C-52-0102-PL-ME-4810: FF | C-52-0102-PL-ME-4410, C-52-0102-PL-ME-4410 | C-52-0102-PL-ME-4410: SS 1, C-52-0102-PL-ME-4410: FF | 2024-11-25 07:00 | 2024-12-18 17:00
C-52-0102-PL-ME-4410 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.17 | Ext. Joint Coating (Tie-in Joint) | C-52-0102-PL-ME-4820, C-52-0102-PL-ME-4820 | C-52-0102-PL-ME-4820: SS 1, C-52-0102-PL-ME-4820: FF | C-52-0102-PL-ME-4830, C-52-0102-PL-ME-4830 | C-52-0102-PL-ME-4830: SS 1, C-52-0102-PL-ME-4830: FF | 2024-11-26 07:00 | 2024-12-19 17:00
C-52-0102-PL-ME-4830 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.19 | Holiday Testing | C-52-0102-PL-ME-4410, C-52-0102-PL-ME-4410 | C-52-0102-PL-ME-4410: SS 1, C-52-0102-PL-ME-4410: FF | C-52-0102-PL-CI-6000, C-52-0102-PL-CI-6000 | C-52-0102-PL-CI-6000: SS 1, C-52-0102-PL-CI-6000: FF 7 | 2024-11-27 07:00 | 2024-12-20 17:00
C-52-0102-PL-CI-6000 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.22 | Padding | C-52-0102-PL-ME-4830, C-52-0102-PL-ME-4830, C-52-0102-PL-CA-5600, C-52-0102-PL-CA-5600 | C-52-0102-PL-ME-4830: SS 1, C-52-0102-PL-ME-4830: FF 7, C-52-0102-PL-CA-5600: SS, C-52-0102-PL-CA-5600: FF | C-52-0102-PL-TE-8200, C-52-0102-PL-ME-7400, C-52-0102-PL-CI-6800, PRECOM-52-0201-1000, C-52-0102-PL-CI-6800 | C-52-0102-PL-TE-8200: SS, C-52-0102-PL-ME-7400: FS, C-52-0102-PL-CI-6800: SS 5, PRECOM-52-0201-1000: FS, C-52-0102-PL-CI-6800: FF | 2024-11-29 07:00 | 2025-01-06 17:00
C-52-0304-PL-CA-5600 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.23 | Installation of Temp. Anode | C-52-0304-PL-ME-4830 | C-52-0304-PL-ME-4830: SS | C-52-0304-PL-CA-5200, C-52-0304-PL-CI-6000, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5200: SS, C-52-0304-PL-CI-6000: SS, C-52-0304-PL-CI-6000: FF | 2024-12-30 07:00 | 2025-02-20 17:00
C-52-0304-PL-CA-5200 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.19 | Installation of CP Test Post | C-52-0304-PL-CA-5600, HM-PL-0410, HS-CN-0090, ML1149-A07 | C-52-0304-PL-CA-5600: SS, HM-PL-0410: FS, HS-CN-0090: FF, ML1149-A07: FF | C-52-0304-PL-CA-5210 | C-52-0304-PL-CA-5210: FS | 2024-12-30 07:00 | 2025-02-20 17:00
C-52-0304-PL-CA-5210 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.19 | Glanding & Termination of Temp. CP S/m | C-52-0304-PL-CA-5200, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5200: FS, C-52-0304-PL-CI-6000: FF | C-52-0304-PL-CA-5250, ML1090 | C-52-0304-PL-CA-5250: FS, ML1090: FS | 2025-02-21 07:00 | 2025-02-22 17:00
C-52-0304-PL-CA-5220 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 | Installation of Test Post for Crossing | C-52-0304-CMA04-1060, C-52-0304-CMA01-1070, C-52-0304-CMA07-1070, C-52-0304-CMA02-1070, C-52-0304-CMA14-1070, C-52-0304-CMA09-1070, C-52-0304-CMA06-1070, C-52-0304-CMA11-1070, C-52-0304-CMA12-1070, C-52-0304-CMA13-1070, C-52-0304-CMA03-1070, C-52-0304-CMA0 | C-52-0304-CMA04-1060: SS, C-52-0304-CMA01-1070: FF, C-52-0304-CMA07-1070: FF, C-52-0304-CMA02-1070: FF, C-52-0304-CMA14-1070: FF, C-52-0304-CMA09-1070: FF, C-52-0304-CMA06-1070: FF, C-52-0304-CMA11-1070: FF, C-52-0304-CMA12-1070: FF, C-52-0304-CMA13-1070: | C-52-0304-PL-CA-5230, C-52-0304-PIPEL-5260 | C-52-0304-PL-CA-5230: SS, C-52-0304-PIPEL-5260: SS 3 | 2024-12-28 07:00 | 2025-02-04 17:00
C-52-0304-PL-CA-5230 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 | Installation of CP JB's | C-52-0304-PL-CA-5220 | C-52-0304-PL-CA-5220: SS | C-52-0304-PL-CA-5240, ML1080 | C-52-0304-PL-CA-5240: FF, ML1080: FS | 2024-12-28 07:00 | 2025-02-04 17:00
C-52-0304-PL-CA-5240 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 | Installation of CP TR | C-52-0304-PL-CA-5230, C-52-0304-PIPEL-5260 | C-52-0304-PL-CA-5230: FF, C-52-0304-PIPEL-5260: FF | C-52-0304-PL-CA-5250, ML1080 | C-52-0304-PL-CA-5250: FS, ML1080: FS | 2025-01-21 07:00 | 2025-02-13 17:00
C-52-0304-PL-CA-5250 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 | CIP/DCVG Survey | C-52-0304-PL-CA-5240, C-52-0304-PL-CA-5210 | C-52-0304-PL-CA-5240: FS, C-52-0304-PL-CA-5210: FS | PRECOM-52-0304-1000, ML1080 | PRECOM-52-0304-1000: FS, ML1080: FS | 2025-02-24 07:00 | 2025-03-03 11:00
C-52-0405-PL-CA-5600 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.26 | Installation of Temp. Anode | C-52-0405-PL-ME-4830, C-52-0405-PL-ME-4830 | C-52-0405-PL-ME-4830: SS, C-52-0405-PL-ME-4830: FF | C-52-0405-PL-CA-5200, C-52-0405-PL-CI-6000, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5200: SS, C-52-0405-PL-CI-6000: SS, C-52-0405-PL-CI-6000: FF | 2025-04-25 13:00 | 2025-06-30 11:00
C-52-0405-PL-CA-5200 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.21 | Installation of CP Test Post | C-52-0405-PL-CA-5600, HM-PL-0410, HS-CN-0090, ML1149-A07 | C-52-0405-PL-CA-5600: SS, HM-PL-0410: FS, HS-CN-0090: FF, ML1149-A07: FF | C-52-0405-PL-CA-5210 | C-52-0405-PL-CA-5210: FS | 2025-04-25 13:00 | 2025-05-31 11:00
C-52-0405-PL-CA-5210 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.21 | Glanding & Termination of Temp. CP S/m | C-52-0405-PL-CA-5200, C-52-0405-PL-CI-6000, C-52-0405-PL-CA-5240 | C-52-0405-PL-CA-5200: FS, C-52-0405-PL-CI-6000: FF, C-52-0405-PL-CA-5240: FS | C-52-0405-PL-CA-5250 | C-52-0405-PL-CA-5250: FS | 2025-06-26 11:00 | 2025-06-30 11:00
C-52-0405-PL-CA-5220 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 | Installation of Test Post for Crossing | C-52-0405-CMA01-1060, C-52-0405-CMA25-1070, C-52-0405-CMA20-1070, C-52-0405-CMA26-1070, C-52-0405-CMA21-1070, C-52-0405-CMA27-1070, C-52-0405-CMA22-1100, C-52-0405-CMA02-1070, C-52-0405-CMA03-1070, C-52-0405-CMA28-1070, C-52-0405-CMA29-1070, C-52-0405-CMA3 | C-52-0405-CMA01-1060: SS, C-52-0405-CMA25-1070: FF 1, C-52-0405-CMA20-1070: FF 1, C-52-0405-CMA26-1070: FF 1, C-52-0405-CMA21-1070: FF 1, C-52-0405-CMA27-1070: FF 1, C-52-0405-CMA22-1100: FF 1, C-52-0405-CMA02-1070: FF 1, C-52-0405-CMA03-1070: FF 1, C-52-0 | C-52-0405-PL-CA-5230, C-52-0405-PIPEL-5260 | C-52-0405-PL-CA-5230: SS, C-52-0405-PIPEL-5260: FF | 2025-04-09 13:00 | 2025-06-10 11:00
C-52-0405-PL-CA-5230 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 | Installation of CP JB's | C-52-0405-PL-CA-5220 | C-52-0405-PL-CA-5220: SS | C-52-0405-PL-CA-5240 | C-52-0405-PL-CA-5240: SS | 2025-04-09 13:00 | 2025-06-10 11:00
C-52-0405-PL-CA-5240 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 | Installation of CP TR | C-52-0405-PL-CA-5230, C-52-0405-PIPEL-5260 | C-52-0405-PL-CA-5230: SS, C-52-0405-PIPEL-5260: FF | C-52-0405-PL-CA-5250, C-52-0405-PL-CA-5210 | C-52-0405-PL-CA-5250: FS, C-52-0405-PL-CA-5210: FS | 2025-04-09 13:00 | 2025-06-10 11:00
C-52-0405-PL-CA-5250 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 | CIP/DCVG Survey | C-52-0405-PL-CA-5240, C-52-0405-PL-CA-5210 | C-52-0405-PL-CA-5240: FS, C-52-0405-PL-CA-5210: FS | PRECOM-52-0405-1000 | PRECOM-52-0405-1000: FS | 2025-06-30 11:00 | 2025-07-08 11:00
C-52-0506-PL-CA-5600 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.26 | Installation of Temp. Anode | C-52-0506-PL-ME-4830 | C-52-0506-PL-ME-4830: SS | C-52-0506-PL-CA-5200, C-52-0506-PL-CI-6000, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5200: SS 1, C-52-0506-PL-CI-6000: FF, C-52-0506-PL-CI-6000: SS | 2025-05-09 15:00 | 2025-07-08 15:00
C-52-0506-PL-CA-5200 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.23 | Installation of CP Test Post | C-52-0506-PL-CA-5600, HM-PL-0410, HS-CN-0090, ML1149-A07 | C-52-0506-PL-CA-5600: SS 1, HM-PL-0410: FS, HS-CN-0090: FF, ML1149-A07: FF | C-52-0506-PL-CA-5210 | C-52-0506-PL-CA-5210: FS | 2025-05-10 15:00 | 2025-07-09 15:00
C-52-0506-PL-CA-5210 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.23 | Glanding & Termination of Temp. CP S/m | C-52-0506-PL-CA-5200, C-52-0506-PL-CI-6000, C-52-0506-PL-CA-5240 | C-52-0506-PL-CA-5200: FS, C-52-0506-PL-CI-6000: FF, C-52-0506-PL-CA-5240: FS | C-52-0506-PL-CA-5250 | C-52-0506-PL-CA-5250: FS | 2025-07-10 15:00 | 2025-07-12 15:00
C-52-0506-PL-CA-5220 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 | Installation of Test Post for Crossing | C-52-0506-CMA06-1060, C-52-0506-CMA07-1070, C-52-0506-CMA04-1070, C-52-0506-CMA02-1070, C-52-0506-CMA08-1070, C-52-0506-CMA09-1070, C-52-0506-CMA03-1070, C-52-0506-CMA01-1070, C-52-0506-CMA05-1070, C-52-0506-CME01-1070, C-52-0506-CME02-1070, C-52-0506-CME0 | C-52-0506-CMA06-1060: SS, C-52-0506-CMA07-1070: FF, C-52-0506-CMA04-1070: FF, C-52-0506-CMA02-1070: FF, C-52-0506-CMA08-1070: FF, C-52-0506-CMA09-1070: FF, C-52-0506-CMA03-1070: FF, C-52-0506-CMA01-1070: FF, C-52-0506-CMA05-1070: FF, C-52-0506-CME01-1070: | C-52-0506-PL-CA-5230, C-52-0506-PIPEL-5260 | C-52-0506-PL-CA-5230: SS, C-52-0506-PIPEL-5260: FF 1 | 2025-04-23 15:30 | 2025-06-21 13:30
C-52-0506-PL-CA-5230 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 | Installation of CP JB's | C-52-0506-PL-CA-5220 | C-52-0506-PL-CA-5220: SS | C-52-0506-PL-CA-5240 | C-52-0506-PL-CA-5240: SS | 2025-04-23 15:30 | 2025-06-21 13:30
C-52-0506-PL-CA-5240 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 | Installation of CP TR | C-52-0506-PL-CA-5230, C-52-0506-PIPEL-5260 | C-52-0506-PL-CA-5230: SS, C-52-0506-PIPEL-5260: FF | C-52-0506-PL-CA-5250, C-52-0506-PL-CA-5210 | C-52-0506-PL-CA-5250: FS, C-52-0506-PL-CA-5210: FS | 2025-04-24 15:30 | 2025-06-23 13:30
C-52-0506-PL-CA-5250 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 | CIP/DCVG Survey | C-52-0506-PL-CA-5240, C-52-0506-PL-CA-5210 | C-52-0506-PL-CA-5240: FS, C-52-0506-PL-CA-5210: FS | PRECOM-52-0506-1000 | PRECOM-52-0506-1000: FS | 2025-07-12 15:00 | 2025-07-21 15:00
C-52-06CR-PL-CA-5600 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.26 | Installation of Temp. Anode | C-52-06CR-PL-ME-4830, C-52-06CR-PL-ME-4830 | C-52-06CR-PL-ME-4830: SS, C-52-06CR-PL-ME-4830: FF | C-52-06CR-PL-CA-5200, C-52-06CR-PL-CI-6000, C-52-06CR-PL-CI-6000, C-52-06CR-PL-CA-5200 | C-52-06CR-PL-CA-5200: SS, C-52-06CR-PL-CI-6000: SS 11, C-52-06CR-PL-CI-6000: FF 11, C-52-06CR-PL-CA-5200: FF | 2025-06-28 15:00 | 2025-08-02 15:00
C-52-06CR-PL-CA-5200 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.21 | Installation of CP Test Post | C-52-06CR-PL-CA-5600, HM-PL-0410, HS-CN-0090, ML1149-A07, C-52-06CR-PL-CA-5600 | C-52-06CR-PL-CA-5600: SS, HM-PL-0410: FS, HS-CN-0090: FF, ML1149-A07: FF, C-52-06CR-PL-CA-5600: FF | C-52-06CR-PL-CA-5210 | C-52-06CR-PL-CA-5210: FS | 2025-06-28 15:00 | 2025-08-02 15:00
C-52-06CR-PL-CA-5210 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.21 | Glanding & Termination of Temp. CP S/m | C-52-06CR-PL-CA-5200, C-52-06CR-PL-CI-6000, C-52-06CR-PL-CA-5240 | C-52-06CR-PL-CA-5200: FS, C-52-06CR-PL-CI-6000: FF, C-52-06CR-PL-CA-5240: FS | PRECOM-52-06CR-1000 | PRECOM-52-06CR-1000: FS | 2025-08-13 11:30 | 2025-08-15 11:30
C-52-06CR-PL-CA-5220 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 | Installation of Test Post for Crossing | C-52-06CR-CMA11-1060, C-52-06CR-CMA01-1070, C-52-06CR-CMA08-1070, C-52-06CR-CMA02-1070, C-52-06CR-CMA03-1070, C-52-06CR-CMA12-1070, C-52-06CR-CMA09-1070, C-52-06CR-CMA04-1070, C-52-06CR-CMA05-1070, C-52-06CR-CMA06-1070, C-52-06CR-CMA10-1070, C-52-06CR-CMA0 | C-52-06CR-CMA11-1060: SS, C-52-06CR-CMA01-1070: FF, C-52-06CR-CMA08-1070: FF, C-52-06CR-CMA02-1070: FF, C-52-06CR-CMA03-1070: FF, C-52-06CR-CMA12-1070: FF, C-52-06CR-CMA09-1070: FF, C-52-06CR-CMA04-1070: FF, C-52-06CR-CMA05-1070: FF, C-52-06CR-CMA06-1070: | C-52-06CR-PL-CA-5230, C-52-06CR-PIPEL-5260 | C-52-06CR-PL-CA-5230: SS 1, C-52-06CR-PIPEL-5260: FF | 2025-07-08 07:30 | 2025-08-12 07:30
C-52-06CR-PL-CA-5230 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 | Installation of CP JB's | C-52-06CR-PL-CA-5220 | C-52-06CR-PL-CA-5220: SS 1 | C-52-06CR-PL-CA-5240 | C-52-06CR-PL-CA-5240: SS | 2025-07-09 07:30 | 2025-08-13 07:30
C-52-06CR-PL-CA-5240 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 | Installation of CP TR | C-52-06CR-PL-CA-5230, C-52-06CR-PIPEL-5260 | C-52-06CR-PL-CA-5230: SS, C-52-06CR-PIPEL-5260: FF 1 | C-52-06CR-PL-CA-5250, C-52-06CR-PL-CA-5210 | C-52-06CR-PL-CA-5250: FS, C-52-06CR-PL-CA-5210: FS | 2025-07-09 07:30 | 2025-08-13 07:30
C-52-06CR-PL-CA-5250 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 | CIP/DCVG Survey | C-52-06CR-PL-CA-5240 | C-52-06CR-PL-CA-5240: FS | PRECOM-52-06CR-1000 | PRECOM-52-06CR-1000: FS | 2025-08-13 07:30 | 2025-08-21 07:30
C-52-0102-PL-CA-5600 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.24 | Installation of Temp. Anode | C-52-0102-PL-ME-4800, C-52-0102-PL-ME-4800 | C-52-0102-PL-ME-4800: SS 7, C-52-0102-PL-ME-4800: FF | C-52-0102-PL-CA-5200, C-52-0102-PL-CI-6000, C-52-0102-PL-CI-6000 | C-52-0102-PL-CA-5200: SS, C-52-0102-PL-CI-6000: SS, C-52-0102-PL-CI-6000: FF | 2024-11-29 07:00 | 2024-12-30 17:00
C-52-0102-PL-CA-5200 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.21 | Installation of CP Test Post | C-52-0102-PL-CA-5600, HS-CN-0090, ML1149-A07, HM-PL-0410 | C-52-0102-PL-CA-5600: SS, HS-CN-0090: FF, ML1149-A07: FF, HM-PL-0410: FS | C-52-0102-PL-CA-5210 | C-52-0102-PL-CA-5210: SS 1 | 2024-11-29 07:00 | 2024-12-30 17:00
C-52-0102-PL-CA-5210 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.21 | Glanding & Termination of Temp. CP S/m | C-52-0102-PL-CA-5200 | C-52-0102-PL-CA-5200: SS 1 | C-52-0102-PL-CA-5250 | C-52-0102-PL-CA-5250: FS | 2024-11-30 07:00 | 2024-12-31 17:00
C-52-0102-PL-CA-5220 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 | Installation of Test Post for Crossing | C-52-0102-CMA04-1060, C-52-0102-CMA01-1060, C-52-0102-CMA02-1060, C-52-0102-CMA03-1060, C-52-0102-CMA04-1060, C-52-0102-CMA05-1060, C-52-0102-CME01-1060, C-52-0102-CME02-1060, C-52-0102-CME03-1060, C-52-0102-CME04-1060, C-52-0102-CME05-1060, HM-PL-0410 | C-52-0102-CMA04-1060: FS 14, C-52-0102-CMA01-1060: FS, C-52-0102-CMA02-1060: FS, C-52-0102-CMA03-1060: FS, C-52-0102-CMA04-1060: FF, C-52-0102-CMA05-1060: FS, C-52-0102-CME01-1060: FS, C-52-0102-CME02-1060: FS, C-52-0102-CME03-1060: FS, C-52-0102-CME04-106 | C-52-0102-PL-CA-5230, C-52-0102-PIPEL-5260 | C-52-0102-PL-CA-5230: SS, C-52-0102-PIPEL-5260: SS | 2024-12-17 07:00 | 2025-04-11 13:00
C-52-0102-PL-CA-5230 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 | Installation of CP JB's | C-52-0102-PL-CA-5220 | C-52-0102-PL-CA-5220: SS | C-52-0102-PL-CA-5240, ML1090 | C-52-0102-PL-CA-5240: SS, ML1090: FS | 2024-12-17 07:00 | 2025-04-11 13:00
C-52-0102-PL-CA-5240 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 | Installation of CP TR | C-52-0102-PL-CA-5230, C-52-0102-CNM05-1220, C-52-0102-PIPEL-5260 | C-52-0102-PL-CA-5230: SS, C-52-0102-CNM05-1220: FF 2, C-52-0102-PIPEL-5260: FS | C-52-0102-PL-CA-5250 | C-52-0102-PL-CA-5250: FS | 2025-02-11 07:00 | 2025-02-15 17:00
C-52-0102-PL-CA-5250 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 | CIP/DCVG Survey | C-52-0102-PL-CA-5240, C-52-0102-PL-CA-5210 | C-52-0102-PL-CA-5240: FS, C-52-0102-PL-CA-5210: FS | PRECOM-52-0201-1000 | PRECOM-52-0201-1000: FS | 2025-02-17 07:00 | 2025-02-24 17:00
C-52-HG01-PL-CA-5600 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.29 | Installation of Temp. Anode | C-52-HG01-PL-ME-4800, C-52-HG01-PL-ME-4800, C-52-HG01-PL-ME-5000 | C-52-HG01-PL-ME-4800: SS 7, C-52-HG01-PL-ME-4800: FF, C-52-HG01-PL-ME-5000: FF 7 | C-52-HG01-PL-CA-5200, C-52-HG01-PL-CI-6200, C-52-HG01-PL-CI-6200 | C-52-HG01-PL-CA-5200: SS, C-52-HG01-PL-CI-6200: FF 2, C-52-HG01-PL-CI-6200: SS 2 | 2024-10-15 | 2024-12-10 17:00
C-52-HG01-PL-CA-5200 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.26 | Installation of CP Test Post | C-52-HG01-PL-CA-5600, HM-PL-0360, HS-GN-0530, HS-CN-0090, ML1149-A07, HM-PL-0410 | C-52-HG01-PL-CA-5600: SS, HM-PL-0360: FF, HS-GN-0530: FS, HS-CN-0090: FF, ML1149-A07: FF, HM-PL-0410: FF | C-52-HG01-PL-CA-5210 | C-52-HG01-PL-CA-5210: SS | 2024-10-15 | 2025-02-14 07:00
C-52-HG01-PL-CA-5210 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.26 | Glanding & Termination of Temp. CP S/m | C-52-HG01-PL-CA-5200, C-52-HG01-PL-CI-6000 | C-52-HG01-PL-CA-5200: SS, C-52-HG01-PL-CI-6000: FF | C-52-HG01-PL-CA-5250, ML1080 | C-52-HG01-PL-CA-5250: FS, ML1080: FS | 2024-10-15 | 2025-02-13 17:00
C-52-HG01-PL-CA-5220 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 | Installation of Test Post for Crossing | C-52-HG01-CMA01-1060, C-52-HG01-CMA01-1070, C-52-HG01-CMA02-1070, C-52-HG01-CMA03-1070, C-52-HG01-CMA04-1070, C-52-HG01-CMA05-1070, C-52-HG01-CME01-1070, C-52-HG01-CME02-1070, C-52-HG01-CME03-1070, C-52-HG01-CMA06-1070, C-52-HG01-CMA07-1070, C-52-HG01-PL-C | C-52-HG01-CMA01-1060: FF 7, C-52-HG01-CMA01-1070: FF, C-52-HG01-CMA02-1070: FF, C-52-HG01-CMA03-1070: FF, C-52-HG01-CMA04-1070: FF, C-52-HG01-CMA05-1070: FF, C-52-HG01-CME01-1070: FF, C-52-HG01-CME02-1070: FF, C-52-HG01-CME03-1070: FF, C-52-HG01-CMA06-1070 | C-52-HG01-PL-CA-5230 | C-52-HG01-PL-CA-5230: SS | 2025-02-26 07:00 | 2025-04-17 13:00
C-52-HG01-PL-CA-5230 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 | Installation of CP JB's | C-52-HG01-PL-CA-5220 | C-52-HG01-PL-CA-5220: SS | C-52-HG01-PL-CA-5240 | C-52-HG01-PL-CA-5240: FS | 2025-02-26 07:00 | 2025-04-17 13:00
C-52-HG01-PL-CA-5240 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 | Installation of CP TR | C-52-HG01-PL-CA-5230, C-52-HG01-CNM02-1220 | C-52-HG01-PL-CA-5230: FS, C-52-HG01-CNM02-1220: FF 2 | C-52-HG01-PL-CA-5250, C-52-HG01-PIPEL-5260 | C-52-HG01-PL-CA-5250: FS, C-52-HG01-PIPEL-5260: SS 1 | 2025-04-17 13:00 | 2025-04-23 13:00
C-52-HG01-PL-CA-5250 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 | CIP/DCVG Survey (Pre-Com) | C-52-HG01-PL-CA-5240, C-52-HG01-PL-CA-5210 | C-52-HG01-PL-CA-5240: FS, C-52-HG01-PL-CA-5210: FS | PRECOM-52-HG01-1000 | PRECOM-52-HG01-1000: FS | 2025-04-23 13:00 | 2025-05-01 13:00
C-52-0304-PL-TE-8200 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.4.1 | FO - Cable Pulling/ Laying | C-52-0304-PL-CI-6000, C-52-0304-CMA04-1070, C-52-0304-CMA05-1070, C-52-0304-CMA01-1070, C-52-0304-CMA07-1070, C-52-0304-CMA02-1070, C-52-0304-CMA14-1070, C-52-0304-CMA09-1070, C-52-0304-CMA06-1070, C-52-0304-CMA11-1070, C-52-0304-CMA12-1070, C-52-0304-CMA1 | C-52-0304-PL-CI-6000: SS, C-52-0304-CMA04-1070: FF, C-52-0304-CMA05-1070: FF, C-52-0304-CMA01-1070: FF, C-52-0304-CMA07-1070: FF, C-52-0304-CMA02-1070: FF, C-52-0304-CMA14-1070: FF, C-52-0304-CMA09-1070: FF, C-52-0304-CMA06-1070: FF, C-52-0304-CMA11-1070: | C-52-0304-PL-TE-8210, ML1080 | C-52-0304-PL-TE-8210: FS, ML1080: FS | 2024-12-31 07:00 | 2025-03-01 17:00
C-52-0304-PL-TE-8210 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.4.1 | Termination/Splicing @ BVS | C-52-0304-PL-TE-8200 | C-52-0304-PL-TE-8200: FS | PRECOM-52-0304-1000, ML1080 | PRECOM-52-0304-1000: FS, ML1080: FS | 2025-03-02 07:00 | 2025-03-06 13:00
C-52-0405-PL-TE-8200 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.4.1 | FO - Cable Pulling/ Laying | C-52-0405-PL-CI-6000, C-52-0405-CMA01-1070, C-52-0405-CMA25-1070, C-52-0405-CMA20-1070, C-52-0405-CMA26-1070, C-52-0405-CMA21-1070, C-52-0405-CMA27-1070, C-52-0405-CMA22-1100, C-52-0405-CMA02-1070, C-52-0405-CMA03-1070, C-52-0405-CMA28-1070, C-52-0405-CMA2 | C-52-0405-PL-CI-6000: SS, C-52-0405-CMA01-1070: FF, C-52-0405-CMA25-1070: FF, C-52-0405-CMA20-1070: FF, C-52-0405-CMA26-1070: FF, C-52-0405-CMA21-1070: FF, C-52-0405-CMA27-1070: FF, C-52-0405-CMA22-1100: FF, C-52-0405-CMA02-1070: FF, C-52-0405-CMA03-1070: | C-52-0405-PL-TE-8210, C-52-0405-PL-CI-6400 | C-52-0405-PL-TE-8210: FS, C-52-0405-PL-CI-6400: FF 2 | 2025-04-28 13:00 | 2025-06-30 11:00
C-52-0405-PL-TE-8210 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.4.1 | Termination/Splicing @ BVS | C-52-0405-PL-TE-8200 | C-52-0405-PL-TE-8200: FS | PRECOM-52-0405-1000 | PRECOM-52-0405-1000: FS | 2025-06-30 11:00 | 2025-07-03 11:00
C-52-0506-PL-TE-8200 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.5.1 | FO - Cable Pulling/ Laying | C-52-0506-PL-CI-6000, C-52-0506-CMA06-1070, C-52-0506-CMA07-1070, C-52-0506-CMA04-1070, C-52-0506-CMA02-1070, C-52-0506-CMA08-1070, C-52-0506-CMA09-1070, C-52-0506-CMA03-1070, C-52-0506-CMA01-1070, C-52-0506-CMA05-1070, C-52-0506-CME01-1070, C-52-0506-CME0 | C-52-0506-PL-CI-6000: SS 2, C-52-0506-CMA06-1070: FF, C-52-0506-CMA07-1070: FF, C-52-0506-CMA04-1070: FF, C-52-0506-CMA02-1070: FF, C-52-0506-CMA08-1070: FF, C-52-0506-CMA09-1070: FF, C-52-0506-CMA03-1070: FF, C-52-0506-CMA01-1070: FF, C-52-0506-CMA05-1070 | C-52-0506-PL-TE-8210, C-52-0506-PL-CI-6400, C-52-0506-PL-CI-6400 | C-52-0506-PL-TE-8210: FS, C-52-0506-PL-CI-6400: FF 5, C-52-0506-PL-CI-6400: SS 5 | 2025-05-16 15:00 | 2025-07-15 15:00
C-52-0506-PL-TE-8210 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.5.1 | Termination/Splicing @ BVS | C-52-0506-PL-TE-8200 | C-52-0506-PL-TE-8200: FS | PRECOM-52-0506-1000 | PRECOM-52-0506-1000: FS | 2025-07-15 15:00 | 2025-07-18 15:00
C-52-06CR-PL-TE-8200 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.4.1 | FO - Cable Pulling/ Laying | C-52-06CR-PL-CI-6000, C-52-06CR-CMA11-1070, C-52-06CR-CMA01-1070, C-52-06CR-CMA08-1070, C-52-06CR-CMA02-1070, C-52-06CR-CMA03-1070, C-52-06CR-CMA12-1070, C-52-06CR-CMA09-1070, C-52-06CR-CMA04-1070, C-52-06CR-CMA05-1070, C-52-06CR-CMA06-1070, C-52-06CR-CMA1 | C-52-06CR-PL-CI-6000: SS 1, C-52-06CR-CMA11-1070: FF 1, C-52-06CR-CMA01-1070: FF 1, C-52-06CR-CMA08-1070: FF 1, C-52-06CR-CMA02-1070: FF 1, C-52-06CR-CMA03-1070: FF 1, C-52-06CR-CMA12-1070: FF 1, C-52-06CR-CMA09-1070: FF 1, C-52-06CR-CMA04-1070: FF 1, C-52 | C-52-06CR-PL-TE-8210, C-52-06CR-PL-CI-6400 | C-52-06CR-PL-TE-8210: FS, C-52-06CR-PL-CI-6400: FF 1 | 2025-07-12 11:30 | 2025-08-16 11:30
C-52-06CR-PL-TE-8210 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.4.1 | Termination/Splicing @ BVS | C-52-06CR-PL-TE-8200 | C-52-06CR-PL-TE-8200: FS | PRECOM-52-06CR-1000 | PRECOM-52-06CR-1000: FS | 2025-08-16 11:30 | 2025-08-20 11:30
C-52-0102-PL-TE-8200 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.5.1 | FO - Cable Pulling/ Laying | C-52-0102-PL-CI-6000, HS-CN-0290, HM-EL-0180, HM-EL-610 | C-52-0102-PL-CI-6000: SS, HS-CN-0290: FS, HM-EL-0180: FS, HM-EL-610: FS | C-52-0102-PL-TE-8210 | C-52-0102-PL-TE-8210: FS | 2024-11-29 07:00 | 2025-01-17 17:00
C-52-0102-PL-TE-8210 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.5.1 | Termination/Splicing @ BVS | C-52-0102-PL-TE-8200 | C-52-0102-PL-TE-8200: FS | PRECOM-52-0201-1000, ML1080 | PRECOM-52-0201-1000: FS, ML1080: FS | 2025-01-18 07:00 | 2025-01-21 17:00
C-52-HG01-PL-TE-8200 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.4.1 | FO - Cable Pulling/ Laying | C-52-HG01-PL-CI-6000, HE-TL-0470, HE-TL-0830, HE-TL-0770, HM-EL-0180, HE-TL-0710, HS-CN-0290, HE-IC-0110, C-52-HG01-PL-CI-6200 | C-52-HG01-PL-CI-6000: FF, HE-TL-0470: FS, HE-TL-0830: FS, HE-TL-0770: FS, HM-EL-0180: FS, HE-TL-0710: FS, HS-CN-0290: FS, HE-IC-0110: FS, C-52-HG01-PL-CI-6200: FF 1 | C-52-HG01-PL-TE-8210, C-52-HG01-PL-CI-6800 | C-52-HG01-PL-TE-8210: FS, C-52-HG01-PL-CI-6800: FF 1 | 2024-09-18 | 2024-12-13 17:00
C-52-HG01-PL-TE-8210 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.4.1 | Termination/Splicing @ BVS | C-52-HG01-PL-TE-8200 | C-52-HG01-PL-TE-8200: FS | PRECOM-52-HG01-1000, ML1080 | PRECOM-52-HG01-1000: FS, ML1080: FS | 2024-12-14 07:00 | 2024-12-17 17:00
C-52-0304-PL-ME-7400 | Not Started | P2543-R01-Oct24..4.3.2.3.4.8.3.2 | Cleaning & Gauging | C-52-0304-PL-CI-6000, C-52-0304-CMA04-1070, C-52-0304-CMA05-1070, C-52-0304-CMA01-1070, C-52-0304-CMA07-1070, C-52-0304-CMA02-1070, C-52-0304-CMA14-1070, C-52-0304-CMA09-1070, C-52-0304-CMA06-1070, C-52-0304-CMA11-1070, C-52-0304-CMA12-1070, C-52-0304-CMA1 | C-52-0304-PL-CI-6000: FS, C-52-0304-CMA04-1070: FS, C-52-0304-CMA05-1070: FS, C-52-0304-CMA01-1070: FS, C-52-0304-CMA07-1070: FS, C-52-0304-CMA02-1070: FS, C-52-0304-CMA14-1070: FS, C-52-0304-CMA09-1070: FS, C-52-0304-CMA06-1070: FS, C-52-0304-CMA11-1070: | C-52-0304-PL-ME-7410 | C-52-0304-PL-ME-7410: FS | 2025-04-22 13:00 | 2025-05-03 13:00
C-52-0304-PL-ME-7410 | Not Started | P2543-R01-Oct24..4.3.2.3.4.8.3.2 | Water Filling | C-52-0304-PL-ME-7400 | C-52-0304-PL-ME-7400: FS | C-52-0304-PL-ME-7420 | C-52-0304-PL-ME-7420: FS | 2025-05-03 13:00 | 2025-05-13 11:00
C-52-0304-PL-ME-7420 | Not Started | P2543-R01-Oct24..4.3.2.3.4.8.3.2 | Stabilization & Pressurization | C-52-0304-PL-ME-7410, C-52-0304-PL-CI-7200 | C-52-0304-PL-ME-7410: FS, C-52-0304-PL-CI-7200: FF | C-52-0304-PL-ME-7430 | C-52-0304-PL-ME-7430: FS | 2025-05-13 11:00 | 2025-05-19 11:00
C-52-0304-PL-ME-7430 | Not Started | P2543-R01-Oct24..4.3.2.3.4.8.3.2 | Holding of Test Pressure | C-52-0304-PL-ME-7420 | C-52-0304-PL-ME-7420: FS | C-52-0304-PL-ME-7600, ML1789-E24 | C-52-0304-PL-ME-7600: FS, ML1789-E24: FS | 2025-05-19 11:00 | 2025-05-20 11:00
C-52-0304-PL-ME-7600 | Not Started | P2543-R01-Oct24..4.3.2.3.4.8.3.3 | De-Pressurization | C-52-0304-PL-ME-7430 | C-52-0304-PL-ME-7430: FS | C-52-0304-PL-ME-7610 | C-52-0304-PL-ME-7610: FS | 2025-05-20 11:00 | 2025-05-23 11:00
C-52-0304-PL-ME-7610 | Not Started | P2543-R01-Oct24..4.3.2.3.4.8.3.3 | De-watering | C-52-0304-PL-ME-7600 | C-52-0304-PL-ME-7600: FS | C-52-0304-PL-ME-7620 | C-52-0304-PL-ME-7620: FS | 2025-05-23 11:00 | 2025-05-29 11:00
C-52-0304-PL-ME-7620 | Not Started | P2543-R01-Oct24..4.3.2.3.4.8.3.3 | Swabing & Drying (Upto Dew Point Temp.) | C-52-0304-PL-ME-7610 | C-52-0304-PL-ME-7610: FS | PRECOM-52-0304-1000, ML1789-E24 | PRECOM-52-0304-1000: FS, ML1789-E24: FS | 2025-05-29 11:00 | 2025-06-04 11:00
C-52-0405-PL-ME-7400 | Not Started | P2543-R01-Oct24..4.3.2.3.3.8.3.2 | Cleaning & Gauging | C-52-0405-PL-CI-6000, C-52-0405-CMA01-1070, C-52-0405-CMA25-1070, C-52-0405-CMA20-1070, C-52-0405-CMA26-1070, C-52-0405-CMA21-1070, C-52-0405-CMA27-1070, C-52-0405-CMA22-1100, C-52-0405-CMA02-1070, C-52-0405-CMA03-1070, C-52-0405-CMA28-1070, C-52-0405-CMA2 | C-52-0405-PL-CI-6000: FS, C-52-0405-CMA01-1070: FS, C-52-0405-CMA25-1070: FS, C-52-0405-CMA20-1070: FS, C-52-0405-CMA26-1070: FS, C-52-0405-CMA21-1070: FS, C-52-0405-CMA27-1070: FS, C-52-0405-CMA22-1100: FS, C-52-0405-CMA02-1070: FS, C-52-0405-CMA03-1070: | C-52-0405-PL-ME-7410 | C-52-0405-PL-ME-7410: FS | 2025-08-27 11:00 | 2025-09-08 11:00
C-52-0405-PL-ME-7410 | Not Started | P2543-R01-Oct24..4.3.2.3.3.8.3.2 | Water Filling | C-52-0405-PL-ME-7400 | C-52-0405-PL-ME-7400: FS | C-52-0405-PL-ME-7420 | C-52-0405-PL-ME-7420: FS | 2025-09-08 11:00 | 2025-09-16 11:00
C-52-0405-PL-ME-7420 | Not Started | P2543-R01-Oct24..4.3.2.3.3.8.3.2 | Stabilization & Pressurization | C-52-0405-PL-ME-7410, C-52-0405-PL-CI-7200 | C-52-0405-PL-ME-7410: FS, C-52-0405-PL-CI-7200: FF | C-52-0405-PL-ME-7430 | C-52-0405-PL-ME-7430: FS | 2025-09-16 11:00 | 2025-09-18 11:00
C-52-0405-PL-ME-7430 | Not Started | P2543-R01-Oct24..4.3.2.3.3.8.3.2 | Holding of Test Pressure | C-52-0405-PL-ME-7420 | C-52-0405-PL-ME-7420: FS | C-52-0405-PL-ME-7600, ML1799-E25 | C-52-0405-PL-ME-7600: FS, ML1799-E25: FS | 2025-09-18 11:00 | 2025-09-19 11:00
C-52-0405-PL-ME-7600 | Not Started | P2543-R01-Oct24..4.3.2.3.3.8.3.3 | De-Pressurization | C-52-0405-PL-ME-7430 | C-52-0405-PL-ME-7430: FS | C-52-0405-PL-ME-7610 | C-52-0405-PL-ME-7610: FS | 2025-09-19 11:00 | 2025-09-20 11:00
C-52-0405-PL-ME-7610 | Not Started | P2543-R01-Oct24..4.3.2.3.3.8.3.3 | De-watering | C-52-0405-PL-ME-7600 | C-52-0405-PL-ME-7600: FS | C-52-0405-PL-ME-7620 | C-52-0405-PL-ME-7620: FS | 2025-09-20 11:00 | 2025-09-27 11:00
C-52-0405-PL-ME-7620 | Not Started | P2543-R01-Oct24..4.3.2.3.3.8.3.3 | Swabing & Drying (Upto Dew Point Temp.) | C-52-0405-PL-ME-7610 | C-52-0405-PL-ME-7610: FS | PRECOM-52-0405-1000, ML1799-E25 | PRECOM-52-0405-1000: FS, ML1799-E25: FS | 2025-09-27 11:00 | 2025-10-03 11:00
C-52-0506-PL-ME-7400 | Not Started | P2543-R01-Oct24..4.3.2.3.2.8.3.2 | Cleaning & Gauging | C-52-0506-PL-CI-6000, C-52-0506-CMA06-1070, C-52-0506-CMA07-1070, C-52-0506-CMA04-1070, C-52-0506-CMA02-1070, C-52-0506-CMA08-1070, C-52-0506-CMA09-1070, C-52-0506-CMA03-1070, C-52-0506-CMA01-1070, C-52-0506-CMA05-1070, C-52-0506-CME01-1070, C-52-0506-CME0 | C-52-0506-PL-CI-6000: FS, C-52-0506-CMA06-1070: FS, C-52-0506-CMA07-1070: FS, C-52-0506-CMA04-1070: FS, C-52-0506-CMA02-1070: FS, C-52-0506-CMA08-1070: FS, C-52-0506-CMA09-1070: FS, C-52-0506-CMA03-1070: FS, C-52-0506-CMA01-1070: FS, C-52-0506-CMA05-1070: | C-52-0506-PL-ME-7410 | C-52-0506-PL-ME-7410: FS | 2025-08-08 15:00 | 2025-08-25 15:00
C-52-0506-PL-ME-7410 | Not Started | P2543-R01-Oct24..4.3.2.3.2.8.3.2 | Water Filling | C-52-0506-PL-ME-7400 | C-52-0506-PL-ME-7400: FS | C-52-0506-PL-ME-7420 | C-52-0506-PL-ME-7420: FS | 2025-08-25 15:00 | 2025-09-06 15:00
C-52-0506-PL-ME-7420 | Not Started | P2543-R01-Oct24..4.3.2.3.2.8.3.2 | Stabilization & Pressurization | C-52-0506-PL-ME-7410, C-52-0506-PL-CI-7200 | C-52-0506-PL-ME-7410: FS, C-52-0506-PL-CI-7200: FF | C-52-0506-PL-ME-7430 | C-52-0506-PL-ME-7430: FS | 2025-09-06 15:00 | 2025-09-13 15:00
C-52-0506-PL-ME-7430 | Not Started | P2543-R01-Oct24..4.3.2.3.2.8.3.2 | Holding of Test Pressure | C-52-0506-PL-ME-7420 | C-52-0506-PL-ME-7420: FS | C-52-0506-PL-ME-7600, ML1809-E26 | C-52-0506-PL-ME-7600: FS, ML1809-E26: FS | 2025-09-13 15:00 | 2025-09-15 15:00
C-52-0506-PL-ME-7600 | Not Started | P2543-R01-Oct24..4.3.2.3.2.8.3.3 | De-Pressurization | C-52-0506-PL-ME-7430 | C-52-0506-PL-ME-7430: FS | C-52-0506-PL-ME-7610 | C-52-0506-PL-ME-7610: FS | 2025-09-15 15:00 | 2025-09-18 15:00
C-52-0506-PL-ME-7610 | Not Started | P2543-R01-Oct24..4.3.2.3.2.8.3.3 | De-watering | C-52-0506-PL-ME-7600 | C-52-0506-PL-ME-7600: FS | C-52-0506-PL-ME-7620 | C-52-0506-PL-ME-7620: FS | 2025-09-18 15:00 | 2025-09-25 15:00
C-52-0506-PL-ME-7620 | Not Started | P2543-R01-Oct24..4.3.2.3.2.8.3.3 | Swabing & Drying (Upto Dew Point Temp.) | C-52-0506-PL-ME-7610 | C-52-0506-PL-ME-7610: FS | PRECOM-52-0506-1000, ML1809-E26 | PRECOM-52-0506-1000: FS, ML1809-E26: FS 3 | 2025-09-25 15:00 | 2025-10-01 15:00
C-52-06CR-PL-ME-7400 | Not Started | P2543-R01-Oct24..4.3.2.3.1.8.2.2 | Cleaning & Gauging | C-52-06CR-PL-CI-6000, C-52-06CR-CMA11-1070, C-52-06CR-CMA01-1070, C-52-06CR-CMA08-1070, C-52-06CR-CMA02-1070, C-52-06CR-CMA03-1070, C-52-06CR-CMA12-1070, C-52-06CR-CMA09-1070, C-52-06CR-CMA04-1070, C-52-06CR-CMA05-1070, C-52-06CR-CMA06-1070, C-52-06CR-CMA1 | C-52-06CR-PL-CI-6000: FS, C-52-06CR-CMA11-1070: FF, C-52-06CR-CMA01-1070: FF, C-52-06CR-CMA08-1070: FF, C-52-06CR-CMA02-1070: FF, C-52-06CR-CMA03-1070: FF, C-52-06CR-CMA12-1070: FF, C-52-06CR-CMA09-1070: FF, C-52-06CR-CMA04-1070: FF, C-52-06CR-CMA05-1070: | C-52-06CR-PL-ME-7410 | C-52-06CR-PL-ME-7410: FS | 2025-09-15 11:30 | 2025-10-01 11:30
C-52-06CR-PL-ME-7410 | Not Started | P2543-R01-Oct24..4.3.2.3.1.8.2.2 | Water Filling | C-52-06CR-PL-ME-7400 | C-52-06CR-PL-ME-7400: FS | C-52-06CR-PL-ME-7420 | C-52-06CR-PL-ME-7420: FS | 2025-10-01 11:30 | 2025-10-13 11:30
C-52-06CR-PL-ME-7420 | Not Started | P2543-R01-Oct24..4.3.2.3.1.8.2.2 | Stabilization & Pressurization | C-52-06CR-PL-ME-7410, C-52-06CR-PL-CI-7200 | C-52-06CR-PL-ME-7410: FS, C-52-06CR-PL-CI-7200: FF | C-52-06CR-PL-ME-7430 | C-52-06CR-PL-ME-7430: FS | 2025-10-13 11:30 | 2025-10-15 11:30
C-52-06CR-PL-ME-7430 | Not Started | P2543-R01-Oct24..4.3.2.3.1.8.2.2 | Holding of Test Pressure | C-52-06CR-PL-ME-7420 | C-52-06CR-PL-ME-7420: FS | C-52-06CR-PL-ME-7600, ML1819-E27 | C-52-06CR-PL-ME-7600: FS, ML1819-E27: FS | 2025-10-15 11:30 | 2025-10-16 11:30
C-52-06CR-PL-ME-7600 | Not Started | P2543-R01-Oct24..4.3.2.3.1.8.2.3 | De-Pressurization | C-52-06CR-PL-ME-7430 | C-52-06CR-PL-ME-7430: FS | C-52-06CR-PL-ME-7610 | C-52-06CR-PL-ME-7610: FS | 2025-10-16 11:30 | 2025-10-17 11:30
C-52-06CR-PL-ME-7610 | Not Started | P2543-R01-Oct24..4.3.2.3.1.8.2.3 | De-watering | C-52-06CR-PL-ME-7600 | C-52-06CR-PL-ME-7600: FS | C-52-06CR-PL-ME-7620 | C-52-06CR-PL-ME-7620: FS | 2025-10-17 11:30 | 2025-10-24 11:30
C-52-06CR-PL-ME-7620 | Not Started | P2543-R01-Oct24..4.3.2.3.1.8.2.3 | Swabing & Drying (Upto Dew Point Temp.) | C-52-06CR-PL-ME-7610 | C-52-06CR-PL-ME-7610: FS | PRECOM-52-06CR-1000, ML1819-E27 | PRECOM-52-06CR-1000: FS 1, ML1819-E27: FS | 2025-10-24 11:30 | 2025-10-31 11:30
C-52-0102-PL-ME-7400 | Not Started | P2543-R01-Oct24..4.3.2.3.6.8.1.2 | Cleaning & Gauging | C-52-0102-CMA04-1070, C-52-0102-PL-CI-6000, C-52-0102-CMA05-1070, C-52-0102-CMA01-1070, C-52-0102-CMA02-1070, C-52-0102-CMA03-1070, C-52-0102-CME01-1070, C-52-0102-CME02-1070, C-52-0102-CME03-1070, C-52-0102-CME04-1070, C-52-0102-CME05-1070, C-52-0102-CNH1 | C-52-0102-CMA04-1070: FS, C-52-0102-PL-CI-6000: FS, C-52-0102-CMA05-1070: FS, C-52-0102-CMA01-1070: FS, C-52-0102-CMA02-1070: FS, C-52-0102-CMA03-1070: FS, C-52-0102-CME01-1070: FS, C-52-0102-CME02-1070: FS, C-52-0102-CME03-1070: FS, C-52-0102-CME04-1070: | C-52-0102-PL-ME-7410 | C-52-0102-PL-ME-7410: FS | 2025-03-28 09:00 | 2025-04-12 13:00
C-52-0102-PL-ME-7410 | Not Started | P2543-R01-Oct24..4.3.2.3.6.8.1.2 | Water Filling | C-52-0102-PL-ME-7400 | C-52-0102-PL-ME-7400: FS | C-52-0102-PL-ME-7420 | C-52-0102-PL-ME-7420: FS | 2025-04-12 13:00 | 2025-04-21 13:00
C-52-0102-PL-ME-7420 | Not Started | P2543-R01-Oct24..4.3.2.3.6.8.1.2 | Stabilization & Pressurization | C-52-0102-PL-ME-7410, C-52-0102-PL-CI-7200 | C-52-0102-PL-ME-7410: FS, C-52-0102-PL-CI-7200: FF | C-52-0102-PL-ME-7430 | C-52-0102-PL-ME-7430: FS | 2025-04-21 13:00 | 2025-04-26 13:00
C-52-0102-PL-ME-7430 | Not Started | P2543-R01-Oct24..4.3.2.3.6.8.1.2 | Holding of Test Pressure | C-52-0102-PL-ME-7420 | C-52-0102-PL-ME-7420: FS | C-52-0102-PL-ME-7600, ML1769-E22 | C-52-0102-PL-ME-7600: FS, ML1769-E22: FS | 2025-04-26 13:00 | 2025-04-28 13:00
C-52-0102-PL-ME-7600 | Not Started | P2543-R01-Oct24..4.3.2.3.6.8.1.3 | De-Pressurization | C-52-0102-PL-ME-7430 | C-52-0102-PL-ME-7430: FS | C-52-0102-PL-ME-7610 | C-52-0102-PL-ME-7610: FS | 2025-04-28 13:00 | 2025-05-01 13:00
C-52-0102-PL-ME-7610 | Not Started | P2543-R01-Oct24..4.3.2.3.6.8.1.3 | De-watering | C-52-0102-PL-ME-7600 | C-52-0102-PL-ME-7600: FS | C-52-0102-PL-ME-7620 | C-52-0102-PL-ME-7620: FS | 2025-05-01 13:00 | 2025-05-08 10:00
C-52-0102-PL-ME-7620 | Not Started | P2543-R01-Oct24..4.3.2.3.6.8.1.3 | Swabing & Drying (Upto Dew Point Temp.) | C-52-0102-PL-ME-7610 | C-52-0102-PL-ME-7610: FS | PRECOM-52-0201-1000, ML1769-E22 | PRECOM-52-0201-1000: FS, ML1769-E22: FS | 2025-05-08 10:00 | 2025-05-14 11:00
C-52-HG01-PL-ME-7400 | Not Started | P2543-R01-Oct24..4.3.2.3.10.8.2.2 | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-PL-CI-6000, C-52-HG01-CMA01-1070, C-52-HG01-CMA05-1070, C-52-HG01-CMA06-1070, C-52-HG01-CMA07-1070, C-52-HG01-CMA02-1070, C-52-HG01-CMA03-1070, C-52-HG01-CMA04-1070, C-52-HG01-CME01-1070, C-52-HG01-CME02-1070, C-52-HG01-CME03-1070, C-52-HG01-CNM0 | C-52-HG01-PL-CI-6000: FS, C-52-HG01-CMA01-1070: FS, C-52-HG01-CMA05-1070: FS, C-52-HG01-CMA06-1070: FS, C-52-HG01-CMA07-1070: FS, C-52-HG01-CMA02-1070: FS, C-52-HG01-CMA03-1070: FS, C-52-HG01-CMA04-1070: FS, C-52-HG01-CME01-1070: FS, C-52-HG01-CME02-1070: | C-52-HG01-PL-ME-7410 | C-52-HG01-PL-ME-7410: FF 5 | 2024-12-16 07:00 | 2025-05-09 11:00
C-52-HG01-PL-ME-7410 | Not Started | P2543-R01-Oct24..4.3.2.3.10.8.2.2 | Water Filling | C-52-HG01-PL-ME-7400 | C-52-HG01-PL-ME-7400: FF 5 | C-52-HG01-PL-ME-7420 | C-52-HG01-PL-ME-7420: FF 5 | 2024-12-21 07:00 | 2025-05-15 11:00
C-52-HG01-PL-ME-7420 | Not Started | P2543-R01-Oct24..4.3.2.3.10.8.2.2 | Stabilization & Pressurization | C-52-HG01-PL-ME-7410, C-52-HG01-PL-CI-7200 | C-52-HG01-PL-ME-7410: FF 5, C-52-HG01-PL-CI-7200: FF | C-52-HG01-PL-ME-7430 | C-52-HG01-PL-ME-7430: FF 5 | 2024-12-27 07:00 | 2025-05-21 11:00
C-52-HG01-PL-ME-7430 | Not Started | P2543-R01-Oct24..4.3.2.3.10.8.2.2 | Holding of Test Pressure | C-52-HG01-PL-ME-7420 | C-52-HG01-PL-ME-7420: FF 5 | C-52-HG01-PL-ME-7600, ML1759-E21 | C-52-HG01-PL-ME-7600: FF 5, ML1759-E21: FS | 2025-01-03 07:00 | 2025-05-27 11:00
C-52-HG01-PL-ME-7600 | Not Started | P2543-R01-Oct24..4.3.2.3.10.8.2.3 | De-Pressurization | C-52-HG01-PL-ME-7430 | C-52-HG01-PL-ME-7430: FF 5 | C-52-HG01-PL-ME-7610 | C-52-HG01-PL-ME-7610: FF 5 | 2025-01-09 07:00 | 2025-06-02 11:00
C-52-HG01-PL-ME-7610 | Not Started | P2543-R01-Oct24..4.3.2.3.10.8.2.3 | De-watering | C-52-HG01-PL-ME-7600 | C-52-HG01-PL-ME-7600: FF 5 | C-52-HG01-PL-ME-7620 | C-52-HG01-PL-ME-7620: FF 5 | 2025-01-15 07:00 | 2025-06-10 11:00
C-52-HG01-PL-ME-7620 | Not Started | P2543-R01-Oct24..4.3.2.3.10.8.2.3 | Swabing & Drying (Upto Dew Point Temp.) | C-52-HG01-PL-ME-7610 | C-52-HG01-PL-ME-7610: FF 5 | PRECOM-52-HG01-1000, ML1759-E21 | PRECOM-52-HG01-1000: FS, ML1759-E21: FS | 2025-01-21 07:00 | 2025-06-16 11:00
C-52-0304-PL-CI-6800 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.22 | Gatch Laying & Levelling | C-52-0304-PL-CI-6000, C-52-0304-CMA04-1070, C-52-0304-CMA05-1070, C-52-0304-CMA01-1070, C-52-0304-CMA07-1070, C-52-0304-CMA02-1070, C-52-0304-CMA14-1070, C-52-0304-CMA09-1070, C-52-0304-CMA06-1070, C-52-0304-CMA11-1070, C-52-0304-CMA12-1070, C-52-0304-CMA1 | C-52-0304-PL-CI-6000: SS 5, C-52-0304-CMA04-1070: FF 1, C-52-0304-CMA05-1070: FF 1, C-52-0304-CMA01-1070: FF 1, C-52-0304-CMA07-1070: FF 1, C-52-0304-CMA02-1070: FF 1, C-52-0304-CMA14-1070: FF 1, C-52-0304-CMA09-1070: FF 1, C-52-0304-CMA06-1070: FF 1, C-52 | C-52-0304-PL-CI-6810, C-52-0304-PL-CI-6810 | C-52-0304-PL-CI-6810: SS 2, C-52-0304-PL-CI-6810: FF 5 | 2025-01-07 07:00 | 2025-03-01 17:00
C-52-0304-PL-CI-6810 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.22 | Gatch Compaction | C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6800 | C-52-0304-PL-CI-6800: SS 2, C-52-0304-PL-CI-6800: FF 5 | C-52-0304-PL-CI-7800, C-52-0304-FENCE-1010, PRECOM-52-0304-1000, C-52-0304-PL-CI-7800, C-52-0304-PL-CI-7200, C-52-0304-PL-ME-7400 | C-52-0304-PL-CI-7800: SS 1, C-52-0304-FENCE-1010: FS 50, PRECOM-52-0304-1000: FS, C-52-0304-PL-CI-7800: FF 1, C-52-0304-PL-CI-7200: FS, C-52-0304-PL-ME-7400: FS | 2025-01-13 07:00 | 2025-03-09 11:00
C-52-0405-PL-CI-6800 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.25 | Gatch Laying & Levelling | C-52-0405-PL-CI-6400, C-52-0405-CMA01-1070, C-52-0405-CMA25-1070, C-52-0405-CMA20-1070, C-52-0405-CMA26-1070, C-52-0405-CMA21-1070, C-52-0405-CMA27-1070, C-52-0405-CMA22-1100, C-52-0405-CMA02-1070, C-52-0405-CMA03-1070, C-52-0405-CMA28-1070, C-52-0405-CMA2 | C-52-0405-PL-CI-6400: SS 7, C-52-0405-CMA01-1070: FF 1, C-52-0405-CMA25-1070: FF 1, C-52-0405-CMA20-1070: FF 1, C-52-0405-CMA26-1070: FF 1, C-52-0405-CMA21-1070: FF 1, C-52-0405-CMA27-1070: FF 1, C-52-0405-CMA22-1100: FF 1, C-52-0405-CMA02-1070: FF 1, C-52 | C-52-0405-PL-CI-6810, C-52-0405-PL-CI-6810 | C-52-0405-PL-CI-6810: SS 2, C-52-0405-PL-CI-6810: FF | 2025-06-30 11:00 | 2025-08-25 11:00
C-52-0405-PL-CI-6810 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.25 | Gatch Compaction | C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6400, C-52-0405-PL-CI-6800 | C-52-0405-PL-CI-6800: SS 2, C-52-0405-PL-CI-6400: FF 7, C-52-0405-PL-CI-6800: FF | C-52-0405-PL-CI-7800, PRECOM-52-0405-1000, C-52-0405-PL-CI-7800, C-52-0405-PL-CI-7200, C-52-0405-PL-ME-7400 | C-52-0405-PL-CI-7800: SS, PRECOM-52-0405-1000: FS, C-52-0405-PL-CI-7800: FF, C-52-0405-PL-CI-7200: FF, C-52-0405-PL-ME-7400: FS | 2025-07-02 11:00 | 2025-08-27 11:00
C-52-0506-PL-CI-6800 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.25 | Gatch Laying & Levelling | C-52-0506-PL-CI-6000, C-52-0506-CMA06-1070, C-52-0506-CMA07-1070, C-52-0506-CMA04-1070, C-52-0506-CMA02-1070, C-52-0506-CMA08-1070, C-52-0506-CMA09-1070, C-52-0506-CMA03-1070, C-52-0506-CMA01-1070, C-52-0506-CMA05-1070, C-52-0506-CME01-1070, C-52-0506-CME0 | C-52-0506-PL-CI-6000: SS 5, C-52-0506-CMA06-1070: FF 1, C-52-0506-CMA07-1070: FF 1, C-52-0506-CMA04-1070: FF 1, C-52-0506-CMA02-1070: FF 1, C-52-0506-CMA08-1070: FF 1, C-52-0506-CMA09-1070: FF 1, C-52-0506-CMA03-1070: FF 1, C-52-0506-CMA01-1070: FF 1, C-52 | C-52-0506-PL-CI-6810, C-52-0506-PL-CI-6810 | C-52-0506-PL-CI-6810: SS 2, C-52-0506-PL-CI-6810: FF 1 | 2025-05-31 15:00 | 2025-07-30 15:00
C-52-0506-PL-CI-6810 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.25 | Gatch Compaction | C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6800 | C-52-0506-PL-CI-6800: SS 2, C-52-0506-PL-CI-6800: FF 1 | C-52-0506-PL-CI-7800, C-52-0506-FENCE-1010, PRECOM-52-0506-1000, C-52-0506-PL-CI-7200, C-52-0506-PL-ME-7400 | C-52-0506-PL-CI-7800: SS 1, C-52-0506-FENCE-1010: SS 3, PRECOM-52-0506-1000: FS, C-52-0506-PL-CI-7200: FF 6, C-52-0506-PL-ME-7400: FS | 2025-06-03 15:00 | 2025-08-01 15:00
C-52-06CR-PL-CI-6800 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.25 | Gatch Laying & Levelling | C-52-06CR-PL-CI-6000, C-52-06CR-CMA11-1070, C-52-06CR-CMA01-1070, C-52-06CR-CMA08-1070, C-52-06CR-CMA02-1070, C-52-06CR-CMA03-1070, C-52-06CR-CMA12-1070, C-52-06CR-CMA09-1070, C-52-06CR-CMA04-1070, C-52-06CR-CMA05-1070, C-52-06CR-CMA06-1070, C-52-06CR-CMA1 | C-52-06CR-PL-CI-6000: SS 1, C-52-06CR-CMA11-1070: FF 1, C-52-06CR-CMA01-1070: FF 1, C-52-06CR-CMA08-1070: FF 1, C-52-06CR-CMA02-1070: FF 1, C-52-06CR-CMA03-1070: FF 1, C-52-06CR-CMA12-1070: FF 1, C-52-06CR-CMA09-1070: FF 1, C-52-06CR-CMA04-1070: FF 1, C-52 | C-52-06CR-PL-CI-6810, C-52-06CR-PL-CI-6810 | C-52-06CR-PL-CI-6810: SS 1, C-52-06CR-PL-CI-6810: FF | 2025-08-08 11:30 | 2025-09-13 11:30
C-52-06CR-PL-CI-6810 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.25 | Gatch Compaction | C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6800 | C-52-06CR-PL-CI-6800: SS 1, C-52-06CR-PL-CI-6800: FF | C-52-06CR-PL-CI-7800, C-52-06CR-FENCE-1010, PRECOM-52-06CR-1000, C-52-06CR-PL-CI-7200, C-52-06CR-PL-ME-7400 | C-52-06CR-PL-CI-7800: SS 1, C-52-06CR-FENCE-1010: SS, PRECOM-52-06CR-1000: FS, C-52-06CR-PL-CI-7200: FF, C-52-06CR-PL-ME-7400: FS | 2025-08-09 11:30 | 2025-09-15 11:30
C-52-0102-PL-CI-6800 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.23 | Gatch Laying & Levelling | C-52-0102-PL-CI-6000, C-52-0102-PL-CI-6000, C-PER-1070 | C-52-0102-PL-CI-6000: SS 5, C-52-0102-PL-CI-6000: FF, C-PER-1070: FF | C-52-0102-PL-CI-6810, C-52-0102-PL-CI-6810 | C-52-0102-PL-CI-6810: SS 1, C-52-0102-PL-CI-6810: FF | 2024-12-07 07:00 | 2025-01-29 17:00
C-52-0102-PL-CI-6810 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.23 | Gatch Compaction | C-52-0102-PL-CI-6800, C-52-0102-PL-CI-6800 | C-52-0102-PL-CI-6800: SS 1, C-52-0102-PL-CI-6800: FF | C-52-0102-PL-CI-7800, C-52-0102-FENCE-1010, PRECOM-52-0201-1000, C-52-0102-PL-ME-7400, C-52-0102-PL-CI-7200 | C-52-0102-PL-CI-7800: FS, C-52-0102-FENCE-1010: FS, PRECOM-52-0201-1000: FS, C-52-0102-PL-ME-7400: FS, C-52-0102-PL-CI-7200: FF | 2024-12-09 07:00 | 2025-01-30 17:00
C-52-HG01-PL-CI-6800 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.27 | Gatch Laying & Levelling | C-52-HG01-PL-CI-6200, C-52-HG01-PL-CI-6000, C-52-HG01-PL-CI-6000, C-52-HG01-PL-TE-8200 | C-52-HG01-PL-CI-6200: FF 2, C-52-HG01-PL-CI-6000: SS 5, C-52-HG01-PL-CI-6000: FF, C-52-HG01-PL-TE-8200: FF 1 | C-52-HG01-PL-CI-6810, C-52-HG01-PL-CI-6810 | C-52-HG01-PL-CI-6810: SS 1, C-52-HG01-PL-CI-6810: FF | 2024-10-03 | 2024-12-14 17:00
C-52-HG01-PL-CI-6810 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.27 | Gatch Compaction | C-52-HG01-PL-CI-6800, C-52-HG01-PL-CI-6800 | C-52-HG01-PL-CI-6800: SS 1, C-52-HG01-PL-CI-6800: FF | C-52-HG01-PL-CI-7800, C-52-HG01-FENCE-1010, PRECOM-52-HG01-1000, C-52-HG01-PL-ME-7400, C-52-HG01-PL-CI-7200 | C-52-HG01-PL-CI-7800: FS, C-52-HG01-FENCE-1010: SS, PRECOM-52-HG01-1000: FS, C-52-HG01-PL-ME-7400: FS, C-52-HG01-PL-CI-7200: FF 3 | 2024-10-11 | 2024-12-14 17:00
C-52-0304-PL-CI-7800 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.22 | Installation of Marker Post/Sign Board | C-52-0304-PL-CI-6810, C-52-0304-PL-CI-6810 | C-52-0304-PL-CI-6810: SS 1, C-52-0304-PL-CI-6810: FF 1 | C-52-0304-PL-CI-7810, ML1090 | C-52-0304-PL-CI-7810: FF 1, ML1090: FS | 2025-01-14 07:00 | 2025-03-11 09:00
C-52-0304-PL-CI-7810 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.22 | Installation of Crash Barriers (If any) | C-52-0304-PL-CI-7800 | C-52-0304-PL-CI-7800: FF 1 | PRECOM-52-0304-1000, ML1090 | PRECOM-52-0304-1000: FS, ML1090: FS | 2025-01-15 07:00 | 2025-03-12 13:00
C-52-0405-PL-CI-7800 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.25 | Installation of Marker Post/Sign Board | C-52-0405-PL-CI-6810, C-52-0405-PL-CI-6810 | C-52-0405-PL-CI-6810: SS, C-52-0405-PL-CI-6810: FF | C-52-0405-PL-CI-7810 | C-52-0405-PL-CI-7810: FF 1 | 2025-07-02 11:00 | 2025-08-27 11:00
C-52-0405-PL-CI-7810 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.25 | Installation of Crash Barriers (If any) | C-52-0405-PL-CI-7800 | C-52-0405-PL-CI-7800: FF 1 | PRECOM-52-0405-1000 | PRECOM-52-0405-1000: FS | 2025-07-04 11:00 | 2025-08-28 11:00
C-52-0506-PL-CI-7800 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.25 | Installation of Marker Post/Sign Board | C-52-0506-PL-CI-6810 | C-52-0506-PL-CI-6810: SS 1 | C-52-0506-PL-CI-7810 | C-52-0506-PL-CI-7810: FF 1 | 2025-06-04 15:00 | 2025-08-02 15:00
C-52-0506-PL-CI-7810 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.25 | Installation of Crash Barriers (If any) | C-52-0506-PL-CI-7800 | C-52-0506-PL-CI-7800: FF 1 | PRECOM-52-0506-1000 | PRECOM-52-0506-1000: FS | 2025-06-07 15:00 | 2025-08-04 15:00
C-52-06CR-PL-CI-7800 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.25 | Installation of Marker Post/Sign Board | C-52-06CR-PL-CI-6810 | C-52-06CR-PL-CI-6810: SS 1 | C-52-06CR-PL-CI-7810 | C-52-06CR-PL-CI-7810: FF 1 | 2025-08-11 11:30 | 2025-09-16 11:30
C-52-06CR-PL-CI-7810 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.25 | Installation of Crash Barriers (If any) | C-52-06CR-PL-CI-7800 | C-52-06CR-PL-CI-7800: FF 1 | PRECOM-52-06CR-1000 | PRECOM-52-06CR-1000: FS | 2025-08-12 11:30 | 2025-09-17 11:30
C-52-0102-PL-CI-7800 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.23 | Installation of Marker Post/Sign Board | C-52-0102-PL-CI-6810 | C-52-0102-PL-CI-6810: FS | C-52-0102-PL-CI-7810 | C-52-0102-PL-CI-7810: FF 1 | 2025-01-31 07:00 | 2025-04-03 13:00
C-52-0102-PL-CI-7810 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.23 | Installation of Crash Barriers (If any) | C-52-0102-PL-CI-7800 | C-52-0102-PL-CI-7800: FF 1 | PRECOM-52-0201-1000, ML1090 | PRECOM-52-0201-1000: FS, ML1090: FS | 2025-02-01 07:00 | 2025-04-04 13:00
C-52-HG01-PL-CI-7800 | Not Started | P2543-R01-Oct24..4.3.2.3.10.8.2.4 | Installation of Marker Post/Sign Board | C-52-HG01-PL-CI-6810 | C-52-HG01-PL-CI-6810: FS | C-52-HG01-PL-CI-7810, C-52-HG01-PL-CI-7820, ML1090 | C-52-HG01-PL-CI-7810: FF 1, C-52-HG01-PL-CI-7820: FF 1, ML1090: FS | 2024-12-16 07:00 | 2025-03-17 09:00
C-52-HG01-PL-CI-7810 | Not Started | P2543-R01-Oct24..4.3.2.3.10.8.2.5 | Installation of Crash Barriers (If any) | C-52-HG01-PL-CI-7800 | C-52-HG01-PL-CI-7800: FF 1 | PRECOM-52-HG01-1000, ML1090 | PRECOM-52-HG01-1000: FS, ML1090: FS | 2024-12-17 07:00 | 2025-03-18 13:00
C-56-01HG-PL-CI-1000 | Completed | P2543-R01-Oct24..4.3.1.2.3.12.1.7 | Survey Marking | HE-PL-0170 | HE-PL-0170: SS | C-56-01HG-PL-CI-1200, C-56-01HG-PL-CI-1800 | C-56-01HG-PL-CI-1200: FS, C-56-01HG-PL-CI-1800: FS | 2024-03-30 07:00 | 2024-05-03 15:00
C-56-01HG-PL-CI-1800 | Completed | P2543-R01-Oct24..4.3.1.2.3.12.1.10 | Non-Sabka ROW/Grading | C-56-01HG-PL-CI-1200, C-56-01HG-PL-CI-1000 | C-56-01HG-PL-CI-1200: FS 14, C-56-01HG-PL-CI-1000: FS | C-56-01HG-PL-CI-2000, C-56-01HG-PL-CI-2400, C-56-01HG-PL-CI-2000, C-56-01HG-PL-CI-2400, C-56-01HG-PL-CI-2600, C-56-01HG-PL-CI-2600, ML1569-E02, C-56-01HG-PL-CI-1400, C-56-HC01-PL-CI-1800 | C-56-01HG-PL-CI-2000: SS 30, C-56-01HG-PL-CI-2400: SS 5, C-56-01HG-PL-CI-2000: FF 30, C-56-01HG-PL-CI-2400: FF 3, C-56-01HG-PL-CI-2600: SS 5, C-56-01HG-PL-CI-2600: FF, ML1569-E02: FS, C-56-01HG-PL-CI-1400: FS, C-56-HC01-PL-CI-1800: FS 14 | 2024-03-27 | 2024-09-24 07:30
C-56-01HG-PL-CI-2000 | In Progress | P2543-R01-Oct24..4.3.1.2.3.12.1.11 | Sabka Gatch Laying (Including ROW) - Layer 1 | C-56-01HG-PL-CI-1800, C-56-01HG-PL-CI-1800, C-GOV-1300 | C-56-01HG-PL-CI-1800: SS 30, C-56-01HG-PL-CI-1800: FF 30, C-GOV-1300: FF | C-56-01HG-PL-CI-2200, C-56-01HG-PL-CI-2200 | C-56-01HG-PL-CI-2200: SS 3, C-56-01HG-PL-CI-2200: FF 3 | 2024-03-27 | 2024-11-11 17:00
C-56-01HG-PL-CI-2010 | In Progress | P2543-R01-Oct24..4.3.1.2.3.12.1.11 | Sabka Gatch Laying - Layer 2 | C-56-01HG-PL-CI-2200, C-56-01HG-PL-CI-2200 | C-56-01HG-PL-CI-2200: SS 3, C-56-01HG-PL-CI-2200: FF 3 | C-56-01HG-PL-CI-2210, C-56-01HG-PL-CI-2210 | C-56-01HG-PL-CI-2210: SS 3, C-56-01HG-PL-CI-2210: FF 3 | 2024-04-23 | 2024-11-18 17:00
C-56-01HG-PL-CI-2020 | In Progress | P2543-R01-Oct24..4.3.1.2.3.12.1.11 | Sabka Gatch Laying - Layer 3 | C-56-01HG-PL-CI-2210, C-56-01HG-PL-CI-2210 | C-56-01HG-PL-CI-2210: SS 3, C-56-01HG-PL-CI-2210: FF 3 | C-56-01HG-PL-CI-2220, C-56-01HG-PL-CI-2220 | C-56-01HG-PL-CI-2220: SS 3, C-56-01HG-PL-CI-2220: FF 3 | 2024-05-08 | 2024-11-25 17:00
C-56-01HG-PL-CI-2030 | In Progress | P2543-R01-Oct24..4.3.1.2.3.12.1.11 | Sabka Gatch Laying - Layer 4 | C-56-01HG-PL-CI-2220, C-56-01HG-PL-CI-2220 | C-56-01HG-PL-CI-2220: SS 3, C-56-01HG-PL-CI-2220: FF 3 | C-56-01HG-PL-CI-2230, C-56-01HG-PL-CI-2230 | C-56-01HG-PL-CI-2230: SS 3, C-56-01HG-PL-CI-2230: FF 3 | 2024-05-20 | 2024-12-04 17:00
C-56-01HG-PL-CI-2200 | In Progress | P2543-R01-Oct24..4.3.1.2.3.12.1.14 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-56-01HG-PL-CI-2000, C-56-01HG-PL-CI-2000 | C-56-01HG-PL-CI-2000: SS 3, C-56-01HG-PL-CI-2000: FF 3 | C-56-01HG-PL-CI-2010, C-56-01HG-PL-CI-2010 | C-56-01HG-PL-CI-2010: SS 3, C-56-01HG-PL-CI-2010: FF 3 | 2024-05-25 | 2024-11-14 17:00
C-56-01HG-PL-CI-2210 | In Progress | P2543-R01-Oct24..4.3.1.2.3.12.1.14 | Sabka Gatch Compaction - Layer 2 | C-56-01HG-PL-CI-2010, C-56-01HG-PL-CI-2010 | C-56-01HG-PL-CI-2010: SS 3, C-56-01HG-PL-CI-2010: FF 3 | C-56-01HG-PL-CI-2020, C-56-01HG-PL-CI-2020 | C-56-01HG-PL-CI-2020: SS 3, C-56-01HG-PL-CI-2020: FF 3 | 2024-04-30 | 2024-11-21 17:00
C-56-01HG-PL-CI-2220 | In Progress | P2543-R01-Oct24..4.3.1.2.3.12.1.14 | Sabka Gatch Compaction - Layer 3 | C-56-01HG-PL-CI-2020, C-56-01HG-PL-CI-2020 | C-56-01HG-PL-CI-2020: SS 3, C-56-01HG-PL-CI-2020: FF 3 | C-56-01HG-PL-CI-2030, C-56-01HG-PL-CI-2030 | C-56-01HG-PL-CI-2030: SS 3, C-56-01HG-PL-CI-2030: FF 3 | 2024-05-18 | 2024-11-28 17:00
C-56-01HG-PL-CI-2230 | In Progress | P2543-R01-Oct24..4.3.1.2.3.12.1.14 | Sabka Gatch Compaction - Layer 4 | C-56-01HG-PL-CI-2030, C-56-01HG-PL-CI-2030 | C-56-01HG-PL-CI-2030: SS 3, C-56-01HG-PL-CI-2030: FF 3 | C-56-01HG-PL-ME-2800, C-56-01HG-PL-CI-2400, C-56-01HG-PL-CI-2600, C-56-01HG-PL-CI-2600, C-56-01HG-PL-ME-3000, ML1569-E02 | C-56-01HG-PL-ME-2800: FF 5, C-56-01HG-PL-CI-2400: FS, C-56-01HG-PL-CI-2600: SS 3, C-56-01HG-PL-CI-2600: FF, C-56-01HG-PL-ME-3000: FS, ML1569-E02: FS | 2024-05-23 | 2024-12-07 17:00
C-56-01HG-PL-ME-2800 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.16 | Stringing (BVS-01 to KP 21.3) | C-56-01HG-PL-CI-2230, HM-PL-0110, C-56-01HG-PL-ME-3000 | C-56-01HG-PL-CI-2230: FF 5, HM-PL-0110: FF 20, C-56-01HG-PL-ME-3000: FS | C-56-01HG-PL-ME-3600, C-56-01HG-CME01-1020, C-56-01HG-PL-ME-3600, C-56-01HG-CMA01-1000, C-56-01HG-CME01-1000, C-56-HC01-PL-ME-2800 | C-56-01HG-PL-ME-3600: SS 2, C-56-01HG-CME01-1020: SS 14, C-56-01HG-PL-ME-3600: FF 2, C-56-01HG-CMA01-1000: FS, C-56-01HG-CME01-1000: FS, C-56-HC01-PL-ME-2800: FS | 2025-01-11 07:00 | 2025-02-28 17:00
C-56-01HG-PL-ME-3600 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.20 | Automatic Welding | C-56-01HG-PL-ME-2800, C-56-01HG-PL-ME-2800, HS-CN-720, HM-PL-0880, C-COM-1010, HM-PL-0890, C-56-01HG-PL-ME-3800 | C-56-01HG-PL-ME-2800: SS 2, C-56-01HG-PL-ME-2800: FF 2, HS-CN-720: FS, HM-PL-0880: FS, C-COM-1010: FS, HM-PL-0890: FF, C-56-01HG-PL-ME-3800: FS | C-56-01HG-PL-ME-4000, C-56-01HG-PL-ME-4200, C-56-01HG-PL-ME-4000, C-56-01HG-PL-ME-4200, C-56-01HG-PL-CI-2400, C-56-01HG-PL-CI-2400, ML1589-E04 | C-56-01HG-PL-ME-4000: SS 1, C-56-01HG-PL-ME-4200: SS 1, C-56-01HG-PL-ME-4000: FF, C-56-01HG-PL-ME-4200: FF, C-56-01HG-PL-CI-2400: SS 3, C-56-01HG-PL-CI-2400: FF 3, ML1589-E04: FS | 2025-02-04 08:30 | 2025-03-05 10:30
C-56-01HG-PL-ME-4000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.13 | NDT | C-56-01HG-PL-ME-3600, C-56-01HG-PL-ME-3600 | C-56-01HG-PL-ME-3600: SS 1, C-56-01HG-PL-ME-3600: FF | C-56-01HG-PL-ME-4400, C-56-01HG-PL-ME-4200, C-56-01HG-PL-ME-4600, C-56-01HG-PL-ME-4400, C-56-01HG-PL-ME-4600 | C-56-01HG-PL-ME-4400: SS 2, C-56-01HG-PL-ME-4200: FS, C-56-01HG-PL-ME-4600: SS 2, C-56-01HG-PL-ME-4400: FF 1, C-56-01HG-PL-ME-4600: FF | 2025-02-05 08:30 | 2025-03-07 08:30
C-56-01HG-PL-ME-4400 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.25 | Ext. Joint Coating | C-56-01HG-PL-ME-4000, C-56-01HG-PL-ME-4000 | C-56-01HG-PL-ME-4000: SS 2, C-56-01HG-PL-ME-4000: FF 1 | C-56-01HG-PL-ME-4800, C-56-01HG-PL-ME-4600, C-56-01HG-PL-ME-4800, C-56-01HG-PL-ME-5000, C-56-01HG-PL-ME-5000 | C-56-01HG-PL-ME-4800: SS 3, C-56-01HG-PL-ME-4600: FS, C-56-01HG-PL-ME-4800: FF 1, C-56-01HG-PL-ME-5000: SS 3, C-56-01HG-PL-ME-5000: FF | 2025-02-07 08:30 | 2025-03-09 12:30
C-56-01HG-PL-CI-2400 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.15 | Trench Excavation | C-56-01HG-PL-CI-2230, C-56-01HG-PL-CI-1800, C-56-01HG-PL-CI-1600, C-56-01HG-PL-CI-1800, C-56-01HG-PL-CI-1400, C-56-01HG-PL-CI-1400, C-56-01HG-PL-CI-1600, C-56-01HG-PL-ME-3600, C-56-01HG-PL-ME-3600 | C-56-01HG-PL-CI-2230: FS, C-56-01HG-PL-CI-1800: SS 5, C-56-01HG-PL-CI-1600: SS 5, C-56-01HG-PL-CI-1800: FF 3, C-56-01HG-PL-CI-1400: SS, C-56-01HG-PL-CI-1400: FF, C-56-01HG-PL-CI-1600: FF 5, C-56-01HG-PL-ME-3600: SS 3, C-56-01HG-PL-ME-3600: FF 3 | C-56-01HG-PL-CI-2410, C-56-01HG-PL-CI-2410, C-4N-H5HG-PIPEL-2400 | C-56-01HG-PL-CI-2410: SS 3, C-56-01HG-PL-CI-2410: FF 3, C-4N-H5HG-PIPEL-2400: SS | 2025-02-13 08:30 | 2025-03-09 12:30
C-56-01HG-PL-CI-2410 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.15 | Bedding | C-56-01HG-PL-CI-2400, C-56-01HG-PL-CI-2400 | C-56-01HG-PL-CI-2400: SS 3, C-56-01HG-PL-CI-2400: FF 3 | C-56-01HG-PL-ME-4800, C-56-01HG-PL-ME-5000 | C-56-01HG-PL-ME-4800: FF 5, C-56-01HG-PL-ME-5000: FF 5 | 2025-02-17 08:30 | 2025-03-14 12:30
C-56-01HG-PL-ME-4800 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.28 | Lowering | C-56-01HG-PL-CI-2410, C-56-01HG-PL-ME-4400, C-56-01HG-PL-CI-2610, C-56-01HG-PL-ME-4400, ML1149-A07, ML1139-A06, HS-CN-0090 | C-56-01HG-PL-CI-2410: FF 5, C-56-01HG-PL-ME-4400: SS 3, C-56-01HG-PL-CI-2610: FF 5, C-56-01HG-PL-ME-4400: FF 1, ML1149-A07: FF, ML1139-A06: FF, HS-CN-0090: FF | C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-3200, C-56-01HG-PL-ME-3400, C-56-01HG-PL-ME-5000, C-56-01HG-PL-ME-3200, C-56-01HG-PL-ME-3400, ML1609-E06 | C-56-01HG-PL-ME-4810: SS, C-56-01HG-PL-ME-3200: SS, C-56-01HG-PL-ME-3400: SS, C-56-01HG-PL-ME-5000: FS, C-56-01HG-PL-ME-3200: FF, C-56-01HG-PL-ME-3400: FF, ML1609-E06: FS | 2025-02-11 08:30 | 2025-04-14 14:30
C-56-01HG-PL-ME-4810 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.28 | Section Tie-in Welding | C-56-01HG-PL-ME-4800, C-56-01HG-CMA01-1030, C-56-01HG-CMA02-1030, C-56-01HG-CMA03-1030, C-56-01HG-CMA04-1030, C-56-01HG-CMA05-1030, C-56-01HG-CMA06-1030, C-56-01HG-CMA07-1030, C-56-01HG-CMA08-1030, C-56-01HG-CMA09-1030, C-56-01HG-CMA10-1030, C-56-01HG-CMA1 | C-56-01HG-PL-ME-4800: SS, C-56-01HG-CMA01-1030: FF 1, C-56-01HG-CMA02-1030: FF 1, C-56-01HG-CMA03-1030: FF 1, C-56-01HG-CMA04-1030: FF 1, C-56-01HG-CMA05-1030: FF 1, C-56-01HG-CMA06-1030: FF 1, C-56-01HG-CMA07-1030: FF 1, C-56-01HG-CMA08-1030: FF 1, C-56-0 | C-56-01HG-PL-ME-4820, C-56-01HG-PL-CI-7200, C-56-01HG-PL-ME-4820, C-56-01HG-PL-ME-5010 | C-56-01HG-PL-ME-4820: SS 2, C-56-01HG-PL-CI-7200: FF, C-56-01HG-PL-ME-4820: FF 2, C-56-01HG-PL-ME-5010: FS | 2025-02-21 07:00 | 2025-04-24 13:00
C-56-01HG-PL-ME-4820 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.28 | NDT (Tie-in Joint) | C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-4810 | C-56-01HG-PL-ME-4810: SS 2, C-56-01HG-PL-ME-4810: FF 2 | C-56-01HG-PL-ME-4410, C-56-01HG-PL-ME-4610, C-56-01HG-PL-ME-4410, C-56-01HG-PL-ME-4610, C-56-01HG-PL-ME-5020 | C-56-01HG-PL-ME-4410: SS 1, C-56-01HG-PL-ME-4610: SS 1, C-56-01HG-PL-ME-4410: FF, C-56-01HG-PL-ME-4610: FF, C-56-01HG-PL-ME-5020: FS | 2025-02-24 07:00 | 2025-04-26 13:00
C-56-01HG-PL-ME-4410 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.25 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-PL-ME-4820, C-56-01HG-PL-ME-4820 | C-56-01HG-PL-ME-4820: SS 1, C-56-01HG-PL-ME-4820: FF | C-56-01HG-PL-ME-4830, C-56-01HG-PL-ME-4610, C-56-01HG-PL-ME-4830, C-56-01HG-PL-ME-5030, C-56-01HG-PL-ME-5030 | C-56-01HG-PL-ME-4830: SS 1, C-56-01HG-PL-ME-4610: FS, C-56-01HG-PL-ME-4830: FF, C-56-01HG-PL-ME-5030: SS 1, C-56-01HG-PL-ME-5030: FF | 2025-03-01 07:00 | 2025-04-26 13:00
C-56-01HG-PL-ME-4830 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.28 | Holiday Testing | C-56-01HG-PL-ME-4410, C-56-01HG-PL-ME-4410 | C-56-01HG-PL-ME-4410: SS 1, C-56-01HG-PL-ME-4410: FF | C-56-01HG-PL-CI-6000, C-56-01HG-PL-CA-5600, C-56-01HG-PL-ME-5030, C-56-01HG-PL-CI-6000, C-56-01HG-PL-CI-6200, C-56-01HG-PL-CI-6200, C-56-01HG-PL-CA-5600 | C-56-01HG-PL-CI-6000: SS 2, C-56-01HG-PL-CA-5600: SS, C-56-01HG-PL-ME-5030: FS, C-56-01HG-PL-CI-6000: FF 2, C-56-01HG-PL-CI-6200: SS 1, C-56-01HG-PL-CI-6200: FF, C-56-01HG-PL-CA-5600: FF | 2025-03-02 07:00 | 2025-05-03 13:00
C-56-01HG-PL-CI-6000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.30 | Padding | C-56-01HG-PL-ME-4830, C-56-01HG-PL-ME-4830, C-56-01HG-PL-CA-5600, C-56-01HG-PL-CA-5600 | C-56-01HG-PL-ME-4830: SS 2, C-56-01HG-PL-ME-4830: FF 2, C-56-01HG-PL-CA-5600: SS 7, C-56-01HG-PL-CA-5600: FF 7 | C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, PRECOM-56-HGHC-1000, C-56-01HG-PL-CI-6200, C-56-01HG-PL-CI-6400, C-56-01HG-PL-CI-6800, C-56-01HG-PL-CI-7000, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8200, C-56-01HG-PL-TE-8400, C-56-01HG-PL-TE | C-56-01HG-PL-TE-8200: SS 5, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: SS 5, PRECOM-56-HGHC-1000: FS, C-56-01HG-PL-CI-6200: SS, C-56-01HG-PL-CI-6400: SS 2, C-56-01HG-PL-CI-6800: FF, C-56-01HG-PL-CI-7000: SS 5, C-56-01HG-PL-CI-7000: FF, C-56-01HG-PL-TE | 2025-03-13 07:00 | 2025-05-13 11:00
C-56-01HG-PL-CI-1400 | In Progress | P2543-R01-Oct24..4.3.1.2.3.12.1.9 | Cut & Fill (@ Non-Sabkha) | C-56-01HG-PL-CI-1800 | C-56-01HG-PL-CI-1800: FS | C-56-01HG-PL-CI-2400, C-56-01HG-PL-CI-2600, C-56-01HG-PL-CI-2600, C-56-01HG-PL-CI-2400 | C-56-01HG-PL-CI-2400: SS, C-56-01HG-PL-CI-2600: SS, C-56-01HG-PL-CI-2600: FF, C-56-01HG-PL-CI-2400: FF | 2024-09-18 07:30 | 2024-11-04 17:00
C-56-HC01-PL-CI-1000 | Completed | P2543-R01-Oct24..4.3.1.2.2.12.4.1.7 | Survey Marking | CTF-1000, CTF-1010, CTF-1000, CTF-1010 | CTF-1000: FS, CTF-1010: FS, CTF-1000: FF, CTF-1010: FF | C-56-HC01-PL-CI-1800, C-56-HC01-PL-CI-1800 | C-56-HC01-PL-CI-1800: SS 7, C-56-HC01-PL-CI-1800: FF 7 | 2024-06-14 07:00 | 2024-07-23 17:00
C-56-HC01-PL-CI-1800 | In Progress | P2543-R01-Oct24..4.3.1.2.2.12.4.1.9 | Non-Sabka ROW/Grading | C-56-HC01-PL-CI-1000, C-56-HC01-PL-CI-1000, CTF-SO1020, C-56-01HG-PL-CI-1800 | C-56-HC01-PL-CI-1000: SS 7, C-56-HC01-PL-CI-1000: FF 7, CTF-SO1020: FS, C-56-01HG-PL-CI-1800: FS 14 | C-56-HC01-PL-CI-1400, C-56-HC01-PL-CI-2600, C-56-HC01-PL-CI-2600, ML1569-E02, C-56-HC01-PL-CI-2400 | C-56-HC01-PL-CI-1400: FF 10, C-56-HC01-PL-CI-2600: SS 7, C-56-HC01-PL-CI-2600: FF, ML1569-E02: FS, C-56-HC01-PL-CI-2400: SS 7 | 2024-09-07 07:30 | 2024-11-21 17:00
C-56-HC01-PL-ME-2800 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 | Stringing (BVS-01 to HBCMPLX) | ML1439-D10, HE-PL-0350, ML1003-A03, HM-PL-0880, HM-PL-1460, C-56-01HG-PL-ME-2800, C-56-HC01-PL-CI-1400 | ML1439-D10: FF, HE-PL-0350: FF 21, ML1003-A03: FF 21, HM-PL-0880: FF, HM-PL-1460: FF 21, C-56-01HG-PL-ME-2800: FS, C-56-HC01-PL-CI-1400: FS | C-56-HC01-PL-ME-3600, C-56-HC01-PL-ME-3600, C-56-HC01-CMA01-1000, C-56-HC01-CMA08-1000, C-56-HC01-CMA16-1000, C-56-HC01-CME01-1000, C-56-HC01-CMA24-1000, C-56-HC01-CMA27-1000, C-56-HC01-CMA30-1000, C-56-HC01-CMA14-1000, C-56-HC01-CMA20-1000 | C-56-HC01-PL-ME-3600: SS 2, C-56-HC01-PL-ME-3600: FF, C-56-HC01-CMA01-1000: SS, C-56-HC01-CMA08-1000: SS, C-56-HC01-CMA16-1000: SS, C-56-HC01-CME01-1000: SS, C-56-HC01-CMA24-1000: SS, C-56-HC01-CMA27-1000: SS, C-56-HC01-CMA30-1000: SS, C-56-HC01-CMA14-1000 | 2025-03-01 07:00 | 2025-04-04 13:00
C-56-HC01-PL-ME-3600 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.16 | Automatic Welding | C-56-HC01-PL-ME-2800, C-56-HC01-PL-ME-2800, C-COM-1010, HM-PL-0880, ML1589-E04 | C-56-HC01-PL-ME-2800: SS 2, C-56-HC01-PL-ME-2800: FF, C-COM-1010: FS, HM-PL-0880: FS, ML1589-E04: FS | C-56-HC01-PL-ME-4000, ML1599-E05, C-56-HC01-PL-CI-2400, C-56-HC01-PL-ME-4000, C-56-HC01-PL-CI-2600, C-56-HC01-PL-CI-2400, C-56-HC01-PL-CI-2600 | C-56-HC01-PL-ME-4000: SS 2, ML1599-E05: FS, C-56-HC01-PL-CI-2400: SS 3, C-56-HC01-PL-ME-4000: FF, C-56-HC01-PL-CI-2600: FF 3, C-56-HC01-PL-CI-2400: FF 3, C-56-HC01-PL-CI-2600: SS 3 | 2025-03-05 10:30 | 2025-04-30 14:30
C-56-HC01-PL-ME-4000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.17 | NDT | C-56-HC01-PL-ME-3600, HS-CN-0190, ML1599-E05, C-56-HC01-PL-ME-3600 | C-56-HC01-PL-ME-3600: SS 2, HS-CN-0190: FS, ML1599-E05: FF, C-56-HC01-PL-ME-3600: FF | C-56-HC01-PL-ME-4400, C-56-HC01-PL-ME-4600, C-56-HC01-PL-ME-4400, C-56-HC01-PL-ME-4600 | C-56-HC01-PL-ME-4400: SS 2, C-56-HC01-PL-ME-4600: SS 2, C-56-HC01-PL-ME-4400: FF 2, C-56-HC01-PL-ME-4600: FF | 2025-04-04 14:30 | 2025-04-30 14:30
C-56-HC01-PL-ME-4400 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.18 | Ext. Joint Coating | C-56-HC01-PL-ME-4000, C-56-HC01-PL-ME-4000 | C-56-HC01-PL-ME-4000: SS 2, C-56-HC01-PL-ME-4000: FF 2 | C-56-HC01-PL-ME-4600, C-56-HC01-PL-ME-4800, C-56-HC01-PL-ME-5000, C-56-HC01-PL-ME-5000, C-56-HC01-PL-ME-4800 | C-56-HC01-PL-ME-4600: FS, C-56-HC01-PL-ME-4800: FF 5, C-56-HC01-PL-ME-5000: SS 3, C-56-HC01-PL-ME-5000: FF, C-56-HC01-PL-ME-4800: SS 2 | 2025-04-07 14:30 | 2025-05-05 15:30
C-56-HC01-PL-CI-2400 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.10 | Trench Excavation | C-56-HC01-PL-CI-1400, HE-SS-0030, ML1002, C-56-HC01-PL-CI-1800, C-56-HC01-PL-ME-3600, C-56-HC01-PL-ME-3600, HE-PL-0170 | C-56-HC01-PL-CI-1400: FS, HE-SS-0030: SS, ML1002: FS, C-56-HC01-PL-CI-1800: SS 7, C-56-HC01-PL-ME-3600: SS 3, C-56-HC01-PL-ME-3600: FF 3, HE-PL-0170: FS | C-56-HC01-PL-CI-2410, C-56-HC01-PL-CI-2410 | C-56-HC01-PL-CI-2410: SS 7, C-56-HC01-PL-CI-2410: FF | 2025-03-28 10:30 | 2025-05-03 14:30
C-56-HC01-PL-CI-2410 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.10 | Bedding | C-56-HC01-PL-CI-2400, C-56-HC01-PL-CI-2400 | C-56-HC01-PL-CI-2400: SS 7, C-56-HC01-PL-CI-2400: FF | C-56-HC01-PL-ME-4800, C-56-HC01-PL-CI-2610, C-56-HC01-PL-ME-5000 | C-56-HC01-PL-ME-4800: FF 5, C-56-HC01-PL-CI-2610: SS, C-56-HC01-PL-ME-5000: FF 5 | 2025-04-09 14:30 | 2025-05-13 09:30
C-56-HC01-PL-ME-4800 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 | Lowering | C-56-HC01-PL-CI-2410, C-56-HC01-PL-ME-4400, C-56-HC01-PL-ME-4400, ML1149-A07, ML1139-A06, HS-CN-0090 | C-56-HC01-PL-CI-2410: FF 5, C-56-HC01-PL-ME-4400: FF 5, C-56-HC01-PL-ME-4400: SS 2, ML1149-A07: FF, ML1139-A06: FF, HS-CN-0090: FF | C-56-HC01-PL-ME-4810, C-56-HC01-PL-ME-3200, C-56-HC01-PL-ME-3200, C-56-HC01-PL-ME-4810, C-56-HC01-PL-ME-5000 | C-56-HC01-PL-ME-4810: SS, C-56-HC01-PL-ME-3200: SS, C-56-HC01-PL-ME-3200: FF, C-56-HC01-PL-ME-4810: FF, C-56-HC01-PL-ME-5000: SS 3 | 2025-04-24 11:30 | 2025-05-19 09:30
C-56-HC01-PL-ME-4810 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 | Section Tie-in Welding | C-56-HC01-PL-ME-4800, C-56-HC01-PL-ME-4800 | C-56-HC01-PL-ME-4800: SS, C-56-HC01-PL-ME-4800: FF | C-56-HC01-PL-ME-4820, C-56-HC01-PL-CI-7200, C-56-PL-607-PL-1000, C-56-PR-838-PL-1000, C-56-HC01-PL-ME-4820, C-56-HC01-PL-ME-5010 | C-56-HC01-PL-ME-4820: SS 1, C-56-HC01-PL-CI-7200: FS, C-56-PL-607-PL-1000: FS, C-56-PR-838-PL-1000: FS 13, C-56-HC01-PL-ME-4820: FF, C-56-HC01-PL-ME-5010: SS 3 | 2025-04-24 11:30 | 2025-05-19 09:30
C-56-HC01-PL-ME-4820 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 | NDT (Tie-in Joint) | C-56-HC01-PL-ME-4810, C-56-HC01-PL-ME-4810 | C-56-HC01-PL-ME-4810: SS 1, C-56-HC01-PL-ME-4810: FF | C-56-HC01-PL-ME-4410, C-56-HC01-PL-ME-4410, C-56-HC01-PL-ME-4610, C-56-HC01-PL-ME-4610, C-56-HC01-PL-ME-5020 | C-56-HC01-PL-ME-4410: SS 1, C-56-HC01-PL-ME-4410: FF, C-56-HC01-PL-ME-4610: SS 1, C-56-HC01-PL-ME-4610: FF, C-56-HC01-PL-ME-5020: SS 3 | 2025-04-25 11:30 | 2025-05-20 09:30
C-56-HC01-PL-ME-4410 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.18 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-PL-ME-4820, C-56-HC01-PL-ME-4820 | C-56-HC01-PL-ME-4820: SS 1, C-56-HC01-PL-ME-4820: FF | C-56-HC01-PL-ME-4830, C-56-HC01-PL-ME-4610, C-56-HC01-PL-ME-4830, C-56-HC01-PL-ME-5030, C-56-HC01-PL-ME-5030 | C-56-HC01-PL-ME-4830: SS 1, C-56-HC01-PL-ME-4610: SS, C-56-HC01-PL-ME-4830: FF 2, C-56-HC01-PL-ME-5030: SS 1, C-56-HC01-PL-ME-5030: FF | 2025-04-26 11:30 | 2025-05-30 09:30
C-56-HC01-PL-ME-4830 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 | Holiday Testing | C-56-HC01-PL-ME-4410, C-56-HC01-PL-ME-4410 | C-56-HC01-PL-ME-4410: SS 1, C-56-HC01-PL-ME-4410: FF 2 | C-56-HC01-PL-CI-6000, C-56-HC01-PL-CA-5600, C-56-HC01-PL-ME-5030, C-56-HC01-PL-CI-6000, C-56-HC01-PL-CI-6200, C-56-HC01-PL-CI-6200, C-56-HC01-PL-CA-5800, C-56-HC01-PL-CA-5600 | C-56-HC01-PL-CI-6000: SS 1, C-56-HC01-PL-CA-5600: SS 3, C-56-HC01-PL-ME-5030: SS 3, C-56-HC01-PL-CI-6000: FF, C-56-HC01-PL-CI-6200: SS 1, C-56-HC01-PL-CI-6200: FF, C-56-HC01-PL-CA-5800: SS 1, C-56-HC01-PL-CA-5600: FF | 2025-05-09 09:30 | 2025-06-02 09:30
C-56-HC01-PL-CI-6000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.20 | Padding | C-56-HC01-PL-ME-4830, C-56-HC01-PL-ME-4830, C-56-HC01-PL-CA-5600, C-56-HC01-PL-CA-5600 | C-56-HC01-PL-ME-4830: SS 1, C-56-HC01-PL-ME-4830: FF, C-56-HC01-PL-CA-5600: SS, C-56-HC01-PL-CA-5600: FF | C-56-HC01-PL-TE-8200, C-56-HC01-PL-ME-7400, C-56-HC01-PL-CI-6800, PRECOM-56-HGHC-1000, C-56-HC01-PL-CI-6200, C-56-HC01-PL-TE-8200, C-56-HC01-PL-TE-8400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, C-56-HC01-PL-CI-6400 | C-56-HC01-PL-TE-8200: SS 5, C-56-HC01-PL-ME-7400: FS, C-56-HC01-PL-CI-6800: SS 5, PRECOM-56-HGHC-1000: FS, C-56-HC01-PL-CI-6200: SS 3, C-56-HC01-PL-TE-8200: FF 1, C-56-HC01-PL-TE-8400: SS 5, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: SS 5, C-56-HC01-P | 2025-05-13 09:30 | 2025-06-07 09:30
C-56-HC01-PL-CI-1400 | In Progress | P2543-R01-Oct24..4.3.1.2.2.12.4.1.8 | Cut & Fill (@ Non-Sabkha) | C-56-HC01-PL-CI-1800, CTF-SO1020, C-56-01HG-PL-CI-1600 | C-56-HC01-PL-CI-1800: FF 10, CTF-SO1020: FS, C-56-01HG-PL-CI-1600: FF | C-56-HC01-PL-CI-2400, C-56-HC01-PL-CI-2600, ML1569-E02, C-56-HC01-PL-CI-2600, C-56-HC01-PL-ME-2800 | C-56-HC01-PL-CI-2400: FS, C-56-HC01-PL-CI-2600: FF 3, ML1569-E02: FS, C-56-HC01-PL-CI-2600: SS 3, C-56-HC01-PL-ME-2800: FS | 2024-08-30 | 2024-12-05 17:00
C-56-01HG-PL-CA-5600 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.26 | Installation of Temp. Anode | C-56-01HG-PL-ME-4830, C-56-01HG-PL-ME-4830 | C-56-01HG-PL-ME-4830: SS, C-56-01HG-PL-ME-4830: FF | C-56-01HG-PL-CA-5610, C-56-01HG-PL-CA-5610, C-56-01HG-PL-CI-6000, C-56-01HG-PL-CI-6000 | C-56-01HG-PL-CA-5610: SS, C-56-01HG-PL-CA-5610: FF, C-56-01HG-PL-CI-6000: SS 7, C-56-01HG-PL-CI-6000: FF 7 | 2025-03-02 07:00 | 2025-05-03 13:00
C-56-01HG-PL-CA-5610 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.26 | Installation of CP Test Post | C-56-01HG-PL-CA-5600, C-56-01HG-PL-CA-5600 | C-56-01HG-PL-CA-5600: SS, C-56-01HG-PL-CA-5600: FF | C-56-01HG-PL-CA-5620, C-56-01HG-PL-CA-5810 | C-56-01HG-PL-CA-5620: FS, C-56-01HG-PL-CA-5810: FS | 2025-03-02 07:00 | 2025-05-03 13:00
C-56-01HG-PL-CA-5620 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.26 | Glanding & Termination of Temp. CP S/m | C-56-01HG-PL-CA-5610 | C-56-01HG-PL-CA-5610: FS | C-56-01HG-PL-CA-5250, C-56-01HG-PL-CA-5450, C-56-01HG-PL-CA-5820 | C-56-01HG-PL-CA-5250: FS, C-56-01HG-PL-CA-5450: FS, C-56-01HG-PL-CA-5820: FS | 2025-05-03 13:00 | 2025-05-06 16:00
C-56-01HG-PL-CA-5220 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.21 | Installation of Test Post for Crossing | C-56-01HG-CMA01-1070, C-56-01HG-CMA02-1070, C-56-01HG-CMA03-1070, C-56-01HG-CMA04-1070, C-56-01HG-CMA05-1070, C-56-01HG-CMA06-1070, C-56-01HG-CMA07-1070, C-56-01HG-CMA08-1070, C-56-01HG-CMA09-1070, C-56-01HG-CMA10-1070, C-56-01HG-CMA11-1070, C-56-01HG-CMA1 | C-56-01HG-CMA01-1070: SS, C-56-01HG-CMA02-1070: FF, C-56-01HG-CMA03-1070: FF, C-56-01HG-CMA04-1070: FF, C-56-01HG-CMA05-1070: FF, C-56-01HG-CMA06-1070: FF, C-56-01HG-CMA07-1070: FF, C-56-01HG-CMA08-1070: FF, C-56-01HG-CMA09-1070: FF, C-56-01HG-CMA10-1070: | C-56-01HG-PL-CA-5230, C-56-01HG-PL-CA-5420 | C-56-01HG-PL-CA-5230: SS 1, C-56-01HG-PL-CA-5420: FS | 2025-06-11 15:00 | 2025-07-17 15:00
C-56-01HG-PL-CA-5230 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.21 | Installation of CP JB's | C-56-01HG-PL-CA-5220 | C-56-01HG-PL-CA-5220: SS 1 | C-56-01HG-PL-CA-5240, C-56-01HG-PL-CA-5430 | C-56-01HG-PL-CA-5240: SS 1, C-56-01HG-PL-CA-5430: FS | 2025-06-12 15:00 | 2025-07-18 15:00
C-56-01HG-PL-CA-5240 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.21 | Installation of CP TR | C-56-01HG-PL-CA-5230 | C-56-01HG-PL-CA-5230: SS 1 | C-56-01HG-PL-CA-5250, C-56-01HG-PL-CA-5440 | C-56-01HG-PL-CA-5250: FS, C-56-01HG-PL-CA-5440: FS | 2025-06-13 15:00 | 2025-07-19 15:00
C-56-01HG-PL-CA-5250 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.21 | CIP/DCVG Survey (Pre-Com) | C-56-01HG-PL-CA-5240, C-56-01HG-PL-CA-5620 | C-56-01HG-PL-CA-5240: FS, C-56-01HG-PL-CA-5620: FS | PRECOM-56-HGHC-1000, C-56-01HG-PL-CA-5450 | PRECOM-56-HGHC-1000: FS, C-56-01HG-PL-CA-5450: FS | 2025-07-19 15:00 | 2025-07-24 15:00
C-56-HC01-PL-CA-5600 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.33 | Installation of Temp. Anode | C-56-HC01-PL-ME-4830, C-56-HC01-PL-ME-4830 | C-56-HC01-PL-ME-4830: SS 3, C-56-HC01-PL-ME-4830: FF | C-56-HC01-PL-CA-5200, C-56-HC01-PL-CA-5430, C-56-HC01-PL-CA-5800, C-56-HC01-PL-CA-5200, C-56-HC01-PL-CI-6000, C-56-HC01-PL-CI-6000 | C-56-HC01-PL-CA-5200: SS 1, C-56-HC01-PL-CA-5430: SS 1, C-56-HC01-PL-CA-5800: SS, C-56-HC01-PL-CA-5200: FF, C-56-HC01-PL-CI-6000: SS, C-56-HC01-PL-CI-6000: FF | 2025-05-13 09:30 | 2025-06-07 09:30
C-56-HC01-PL-CA-5200 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 | Installation of CP Test Post | C-56-HC01-PL-CA-5600, C-56-HC01-PL-CA-5600, HS-GN-0530, ML1549-D22, HM-PL-0410 | C-56-HC01-PL-CA-5600: SS 1, C-56-HC01-PL-CA-5600: FF, HS-GN-0530: FS, ML1549-D22: FS, HM-PL-0410: FS | C-56-HC01-PL-CA-5210, C-56-HC01-PL-CA-5430 | C-56-HC01-PL-CA-5210: FS, C-56-HC01-PL-CA-5430: FS | 2025-05-14 09:30 | 2025-06-09 09:30
C-56-HC01-PL-CA-5210 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 | Glanding & Termination of Temp. CP S/m | C-56-HC01-PL-CA-5200 | C-56-HC01-PL-CA-5200: FS | C-56-HC01-PL-CA-5250, C-56-HC01-PL-CA-5440 | C-56-HC01-PL-CA-5250: FS, C-56-HC01-PL-CA-5440: FS | 2025-06-09 09:30 | 2025-06-11 09:30
C-56-HC01-PL-CA-5220 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 | Installation of Test Post for Crossing | C-56-HC01-CMA02-1060, C-56-HC01-CMA03-1070, C-56-HC01-CMA13-1070, C-56-HC01-CMA09-1070, C-56-HC01-CMA11-1070, C-56-HC01-CMA14-1070, C-56-HC01-CMA15-1070, C-56-HC01-CMA22-1070, C-56-HC01-CMA04-1070, C-56-HC01-CMA16-1070, C-56-HC01-CMA18-1070, C-56-HC01-CMA2 | C-56-HC01-CMA02-1060: SS, C-56-HC01-CMA03-1070: FF, C-56-HC01-CMA13-1070: FF, C-56-HC01-CMA09-1070: FF, C-56-HC01-CMA11-1070: FF, C-56-HC01-CMA14-1070: FF, C-56-HC01-CMA15-1070: FF, C-56-HC01-CMA22-1070: FF, C-56-HC01-CMA04-1070: FF, C-56-HC01-CMA16-1070: | C-56-HC01-PL-CA-5230, C-56-HC01-PL-CA-5230, C-56-HC01-PL-CA-5400 | C-56-HC01-PL-CA-5230: SS 1, C-56-HC01-PL-CA-5230: FF, C-56-HC01-PL-CA-5400: FS | 2025-08-02 11:00 | 2025-08-20 11:00
C-56-HC01-PL-CA-5230 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 | Installation of CP JB's | C-56-HC01-PL-CA-5220, C-56-HC01-PL-CA-5220 | C-56-HC01-PL-CA-5220: SS 1, C-56-HC01-PL-CA-5220: FF | C-56-HC01-PL-CA-5240, C-56-HC01-PL-CA-5240, C-56-HC01-PL-CA-5410 | C-56-HC01-PL-CA-5240: SS 1, C-56-HC01-PL-CA-5240: FF, C-56-HC01-PL-CA-5410: FS | 2025-08-04 11:00 | 2025-08-21 11:00
C-56-HC01-PL-CA-5240 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 | Installation of CP TR | C-56-HC01-PL-CA-5230, C-56-HC01-PL-CA-5230 | C-56-HC01-PL-CA-5230: SS 1, C-56-HC01-PL-CA-5230: FF | C-56-HC01-PL-CA-5250, C-56-HC01-PL-CA-5420 | C-56-HC01-PL-CA-5250: FS, C-56-HC01-PL-CA-5420: FS | 2025-08-05 11:00 | 2025-08-22 11:00
C-56-HC01-PL-CA-5250 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 | CIP/DCVG Survey | C-56-HC01-PL-CA-5240, C-56-HC01-PL-CA-5210 | C-56-HC01-PL-CA-5240: FS, C-56-HC01-PL-CA-5210: FS | PRECOM-56-HGHC-1000, C-56-HC01-PL-CA-5450 | PRECOM-56-HGHC-1000: FS, C-56-HC01-PL-CA-5450: FS | 2025-08-22 11:00 | 2025-08-27 11:00
C-56-01HG-PL-TE-8200 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.3.1 | FO - Cable Pulling/ Laying | C-56-01HG-PL-CI-6000, C-56-01HG-CMA01-1070, C-56-01HG-CMA02-1070, C-56-01HG-CMA03-1070, C-56-01HG-CMA04-1070, C-56-01HG-CMA05-1070, C-56-01HG-CMA06-1070, C-56-01HG-CMA07-1070, C-56-01HG-CMA08-1070, C-56-01HG-CMA09-1070, C-56-01HG-CMA10-1070, C-56-01HG-CMA1 | C-56-01HG-PL-CI-6000: SS 5, C-56-01HG-CMA01-1070: FF, C-56-01HG-CMA02-1070: FF, C-56-01HG-CMA03-1070: FF, C-56-01HG-CMA04-1070: FF, C-56-01HG-CMA05-1070: FF, C-56-01HG-CMA06-1070: FF, C-56-01HG-CMA07-1070: FF, C-56-01HG-CMA08-1070: FF, C-56-01HG-CMA09-1070 | C-56-01HG-PL-TE-8210, C-56-01HG-PL-TE-8400 | C-56-01HG-PL-TE-8210: FS, C-56-01HG-PL-TE-8400: FS | 2025-03-28 09:00 | 2025-05-13 11:00
C-56-01HG-PL-TE-8210 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.3.1 | Termination/Splicing @ BVS | C-56-01HG-PL-TE-8200 | C-56-01HG-PL-TE-8200: FS | PRECOM-56-HGHC-1000, C-56-01HG-PL-TE-8410, C-56-01HG-PL-CI-7010 | PRECOM-56-HGHC-1000: FS, C-56-01HG-PL-TE-8410: FS, C-56-01HG-PL-CI-7010: FF | 2025-05-13 11:00 | 2025-05-15 11:00
C-56-HC01-PL-TE-8200 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.3.1 | FO - Cable Pulling/ Laying | C-56-HC01-PL-CI-6000, C-56-HC01-CMA02-1070, C-56-HC01-CMA03-1070, C-56-HC01-CMA13-1070, C-56-HC01-CMA09-1070, C-56-HC01-CMA11-1070, C-56-HC01-CMA14-1070, C-56-HC01-CMA15-1070, C-56-HC01-CMA22-1070, C-56-HC01-CMA04-1070, C-56-HC01-CMA16-1070, C-56-HC01-CMA1 | C-56-HC01-PL-CI-6000: SS 5, C-56-HC01-CMA02-1070: FF, C-56-HC01-CMA03-1070: FF, C-56-HC01-CMA13-1070: FF, C-56-HC01-CMA09-1070: FF, C-56-HC01-CMA11-1070: FF, C-56-HC01-CMA14-1070: FF, C-56-HC01-CMA15-1070: FF, C-56-HC01-CMA22-1070: FF, C-56-HC01-CMA04-1070 | C-56-HC01-PL-TE-8210, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-6400 | C-56-HC01-PL-TE-8210: FS, C-56-HC01-PL-TE-8400: SS, C-56-HC01-PL-CI-6400: FF 1 | 2025-05-29 11:00 | 2025-06-24 11:00
C-56-HC01-PL-TE-8210 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.3.1 | Termination/Splicing @ BVS | C-56-HC01-PL-TE-8200 | C-56-HC01-PL-TE-8200: FS | PRECOM-56-HGHC-1000, C-56-HC01-PL-TE-8410 | PRECOM-56-HGHC-1000: FS, C-56-HC01-PL-TE-8410: FS | 2025-06-24 11:00 | 2025-06-26 11:00
C-56-01HG-PL-ME-7400 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.2 | Cleaning & Gauging | C-56-01HG-PL-CI-6000, C-56-01HG-CMA01-1070, C-56-01HG-CMA02-1070, C-56-01HG-CMA03-1070, C-56-01HG-CMA04-1070, C-56-01HG-CMA05-1070, C-56-01HG-CMA06-1070, C-56-01HG-CMA07-1070, C-56-01HG-CMA08-1070, C-56-01HG-CMA09-1070, C-56-01HG-CMA10-1070, C-56-01HG-CMA1 | C-56-01HG-PL-CI-6000: FS, C-56-01HG-CMA01-1070: FS, C-56-01HG-CMA02-1070: FS, C-56-01HG-CMA03-1070: FS, C-56-01HG-CMA04-1070: FS, C-56-01HG-CMA05-1070: FS, C-56-01HG-CMA06-1070: FS, C-56-01HG-CMA07-1070: FS, C-56-01HG-CMA08-1070: FS, C-56-01HG-CMA09-1070: | C-56-01HG-PL-ME-7410 | C-56-01HG-PL-ME-7410: FS | 2025-08-02 15:00 | 2025-08-16 15:00
C-56-01HG-PL-ME-7410 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.2 | Water Filling | C-56-01HG-PL-ME-7400 | C-56-01HG-PL-ME-7400: FS | C-56-01HG-PL-ME-7420 | C-56-01HG-PL-ME-7420: FS | 2025-08-16 15:00 | 2025-08-28 15:00
C-56-01HG-PL-ME-7420 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.2 | Stabilization & Pressurization | C-56-01HG-PL-ME-7410, C-56-01HG-PL-CI-7200 | C-56-01HG-PL-ME-7410: FS, C-56-01HG-PL-CI-7200: FS | C-56-01HG-PL-ME-7430 | C-56-01HG-PL-ME-7430: FS | 2025-08-28 15:00 | 2025-09-06 15:00
C-56-01HG-PL-ME-7430 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.2 | Holding of Test Pressure | C-56-01HG-PL-ME-7420 | C-56-01HG-PL-ME-7420: FS | C-56-01HG-PL-ME-7600 | C-56-01HG-PL-ME-7600: FS | 2025-09-06 15:00 | 2025-09-08 15:00
C-56-01HG-PL-ME-7600 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.3 | De-Pressurization | C-56-01HG-PL-ME-7430 | C-56-01HG-PL-ME-7430: FS | C-56-01HG-PL-ME-7610, C-56-01HG-PL-ME-7610 | C-56-01HG-PL-ME-7610: SS, C-56-01HG-PL-ME-7610: FF 2 | 2025-09-08 15:00 | 2025-09-11 15:00
C-56-01HG-PL-ME-7610 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.3 | De-watering | C-56-01HG-PL-ME-7600, C-56-01HG-PL-ME-7600 | C-56-01HG-PL-ME-7600: SS, C-56-01HG-PL-ME-7600: FF 2 | C-56-01HG-PL-ME-7620 | C-56-01HG-PL-ME-7620: FF 3 | 2025-09-10 15:00 | 2025-09-13 15:00
C-56-01HG-PL-ME-7620 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.3 | Swabing & Drying (Upto Dew Point Temp.) | C-56-01HG-PL-ME-7610 | C-56-01HG-PL-ME-7610: FF 3 | PRECOM-56-HGHC-1000, ML1639-E09 | PRECOM-56-HGHC-1000: FS, ML1639-E09: FS | 2025-09-11 15:00 | 2025-09-17 15:00
C-56-HC01-PL-ME-7400 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.6 | Cleaning & Gauging | C-56-HC01-PL-CI-6000, C-56-01HG-CMA01-1070, C-56-01HG-CMA02-1070, C-56-01HG-CMA03-1070, C-56-01HG-CMA04-1070, C-56-01HG-CMA05-1070, C-56-01HG-CMA06-1070, C-56-01HG-CMA07-1070, C-56-01HG-CMA08-1070, C-56-01HG-CMA09-1070, C-56-01HG-CMA10-1070, C-56-01HG-CMA1 | C-56-HC01-PL-CI-6000: FS, C-56-01HG-CMA01-1070: FS, C-56-01HG-CMA02-1070: FS, C-56-01HG-CMA03-1070: FS, C-56-01HG-CMA04-1070: FS, C-56-01HG-CMA05-1070: FS, C-56-01HG-CMA06-1070: FS, C-56-01HG-CMA07-1070: FS, C-56-01HG-CMA08-1070: FS, C-56-01HG-CMA09-1070: | C-56-HC01-PL-ME-7410 | C-56-HC01-PL-ME-7410: FS | 2025-08-02 11:00 | 2025-08-16 11:00
C-56-HC01-PL-ME-7410 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.6 | Water Filling | C-56-HC01-PL-ME-7400 | C-56-HC01-PL-ME-7400: FS | C-56-HC01-PL-ME-7420 | C-56-HC01-PL-ME-7420: FS | 2025-08-16 11:00 | 2025-08-27 11:00
C-56-HC01-PL-ME-7420 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.6 | Stabilization & Pressurization | C-56-HC01-PL-ME-7410, C-56-HC01-PL-CI-7200 | C-56-HC01-PL-ME-7410: FS, C-56-HC01-PL-CI-7200: FF | C-56-HC01-PL-ME-7430 | C-56-HC01-PL-ME-7430: FS | 2025-08-27 11:00 | 2025-09-02 11:00
C-56-HC01-PL-ME-7430 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.6 | Holding of Test Pressure | C-56-HC01-PL-ME-7420 | C-56-HC01-PL-ME-7420: FS | C-56-HC01-PL-ME-7600 | C-56-HC01-PL-ME-7600: FS | 2025-09-02 11:00 | 2025-09-03 11:00
C-56-HC01-PL-ME-7600 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.7 | De-Pressurization | C-56-HC01-PL-ME-7430 | C-56-HC01-PL-ME-7430: FS | C-56-HC01-PL-ME-7610 | C-56-HC01-PL-ME-7610: FS | 2025-09-03 11:00 | 2025-09-08 11:00
C-56-HC01-PL-ME-7610 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.7 | De-watering | C-56-HC01-PL-ME-7600 | C-56-HC01-PL-ME-7600: FS | C-56-HC01-PL-ME-7620 | C-56-HC01-PL-ME-7620: FS | 2025-09-08 11:00 | 2025-09-12 11:00
C-56-HC01-PL-ME-7620 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.7 | Swabing & Drying (Upto Dew Point Temp.) | C-56-HC01-PL-ME-7610 | C-56-HC01-PL-ME-7610: FS | PRECOM-56-HGHC-1000, ML1639-E09, ML1959-E41 | PRECOM-56-HGHC-1000: FS 0, ML1639-E09: FS, ML1959-E41: FS | 2025-09-12 11:00 | 2025-09-17 11:00
C-56-01HG-PL-CI-6800 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.36 | Gatch Laying & Levelling | C-56-01HG-PL-CI-6000, C-56-01HG-CMA01-1070, C-56-01HG-CMA02-1070, C-56-01HG-CMA03-1070, C-56-01HG-CMA04-1070, C-56-01HG-CMA05-1070, C-56-01HG-CMA06-1070, C-56-01HG-CMA07-1070, C-56-01HG-CMA08-1070, C-56-01HG-CMA09-1070, C-56-01HG-CMA10-1070, C-56-01HG-CMA1 | C-56-01HG-PL-CI-6000: SS 5, C-56-01HG-CMA01-1070: FF 1, C-56-01HG-CMA02-1070: FF 1, C-56-01HG-CMA03-1070: FF 1, C-56-01HG-CMA04-1070: FF 1, C-56-01HG-CMA05-1070: FF 1, C-56-01HG-CMA06-1070: FF 1, C-56-01HG-CMA07-1070: FF 1, C-56-01HG-CMA08-1070: FF 1, C-56 | C-56-01HG-PL-CI-6810, C-56-01HG-PL-CI-7000 | C-56-01HG-PL-CI-6810: SS 10, C-56-01HG-PL-CI-7000: FS | 2025-03-29 13:00 | 2025-05-20 11:00
C-56-01HG-PL-CI-6810 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.36 | Gatch Compaction | C-56-01HG-PL-CI-6800 | C-56-01HG-PL-CI-6800: SS 10 | C-56-01HG-PL-CI-7800, PRECOM-56-HGHC-1000, C-56-01HG-PL-CI-7010, C-56-01HG-PL-ME-7400 | C-56-01HG-PL-CI-7800: SS 1, PRECOM-56-HGHC-1000: FS, C-56-01HG-PL-CI-7010: FS, C-56-01HG-PL-ME-7400: FS | 2025-04-14 09:00 | 2025-05-30 17:00
C-56-HC01-PL-CI-6800 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 | Gatch Laying & Levelling | C-56-HC01-PL-CI-6000, C-56-HC01-CMA02-1070, C-56-HC01-CMA03-1070, C-56-HC01-CMA13-1070, C-56-HC01-CMA09-1070, C-56-HC01-CMA11-1070, C-56-HC01-CMA14-1070, C-56-HC01-CMA15-1070, C-56-HC01-CMA22-1070, C-56-HC01-CMA04-1070, C-56-HC01-CMA16-1070, C-56-HC01-CMA1 | C-56-HC01-PL-CI-6000: SS 5, C-56-HC01-CMA02-1070: FF, C-56-HC01-CMA03-1070: FF, C-56-HC01-CMA13-1070: FF, C-56-HC01-CMA09-1070: FF, C-56-HC01-CMA11-1070: FF, C-56-HC01-CMA14-1070: FF, C-56-HC01-CMA15-1070: FF, C-56-HC01-CMA22-1070: FF, C-56-HC01-CMA04-1070 | C-56-HC01-PL-CI-6810 | C-56-HC01-PL-CI-6810: SS 2 | 2025-06-21 11:00 | 2025-07-16 11:00
C-56-HC01-PL-CI-6810 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 | Gatch Compaction | C-56-HC01-PL-CI-6800 | C-56-HC01-PL-CI-6800: SS 2 | C-56-HC01-PL-CI-7800, PRECOM-56-HGHC-1000, C-56-HC01-PL-ME-7400 | C-56-HC01-PL-CI-7800: FS, PRECOM-56-HGHC-1000: FS, C-56-HC01-PL-ME-7400: FS | 2025-06-24 11:00 | 2025-07-18 11:00
C-56-01HG-PL-CI-7800 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.4 | ROW Restoration/ Installation of Marker Post/Sign Board | C-56-01HG-PL-CI-6810, C-56-01HG-PL-CI-7010 | C-56-01HG-PL-CI-6810: SS 1, C-56-01HG-PL-CI-7010: SS 1 | C-56-01HG-PL-CI-7810, ML1959-E41, CCM-PM4510 | C-56-01HG-PL-CI-7810: FF 1, ML1959-E41: FS, CCM-PM4510: FS | 2025-06-03 15:00 | 2025-08-05 15:00
C-56-01HG-PL-CI-7810 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.4 | Installation of Crash Barriers (If any) | C-56-01HG-PL-CI-7800 | C-56-01HG-PL-CI-7800: FF 1 | PRECOM-56-HGHC-1000, ML1959-E41, CCM-PM4510 | PRECOM-56-HGHC-1000: FS, ML1959-E41: FS, CCM-PM4510: FF | 2025-06-04 15:00 | 2025-08-06 15:00
C-56-HC01-PL-CI-7800 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 | Installation of Marker Post/Sign Board | C-56-HC01-PL-CI-6810 | C-56-HC01-PL-CI-6810: FS | C-56-HC01-PL-CI-7810 | C-56-HC01-PL-CI-7810: SS 5 | 2025-07-18 11:00 | 2025-08-11 11:00
C-56-HC01-PL-CI-7810 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 | Installation of Crash Barriers (If any) | C-56-HC01-PL-CI-7800 | C-56-HC01-PL-CI-7800: SS 5 | PRECOM-56-HGHC-1000, ML1020 | PRECOM-56-HGHC-1000: FS, ML1020: FS | 2025-07-24 11:00 | 2025-08-16 11:00
C-52-0102-CMA04-0970 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 | Excavation (Manual-Trial Pit) | C-52-0102-PL-CI-1800 | C-52-0102-PL-CI-1800: FF | C-52-0102-CMA04-0980, C-52-0102-CMA05-0970 | C-52-0102-CMA04-0980: FS, C-52-0102-CMA05-0970: FS | 2024-06-17 | 2024-07-17
C-52-0102-CMA04-0980 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 | Sabkha Gatch Laying | C-52-0102-CMA04-0970 | C-52-0102-CMA04-0970: FS | C-52-0102-CMA04-0990 | C-52-0102-CMA04-0990: SS 1 | 2024-06-17 | 2024-07-17
C-52-0102-CMA04-0990 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 | Sabka Gatch Compaction | C-52-0102-CMA04-0980 | C-52-0102-CMA04-0980: SS 1 | C-52-0102-CMA04-1000 | C-52-0102-CMA04-1000: FS | 2024-06-17 | 2024-07-17
C-52-0102-CMA04-1000 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 | Trench Excavation | C-52-0102-CMA04-0990 | C-52-0102-CMA04-0990: FS | C-52-0102-CMA04-1010 | C-52-0102-CMA04-1010: FF | 2024-06-17 | 2024-07-17
C-52-0102-CMA04-1010 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 | Bedding | C-52-0102-CMA04-1000 | C-52-0102-CMA04-1000: FF | C-52-0102-CMA04-1020 | C-52-0102-CMA04-1020: FS | 2024-06-17 | 2024-07-17
C-52-0102-CMA04-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 | Lowering | C-52-0102-CMA04-1010 | C-52-0102-CMA04-1010: FS | C-52-0102-CMA04-1030 | C-52-0102-CMA04-1030: SS | 2024-10-26 07:00 | 2024-10-26 17:00
C-52-0102-CMA04-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 | Section Tie-in Welding | C-52-0102-CMA04-1020 | C-52-0102-CMA04-1020: SS | C-52-0102-CMA04-1040 | C-52-0102-CMA04-1040: SS 1 | 2024-10-26 07:00 | 2024-10-28 17:00
C-52-0102-CMA04-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 | NDT (Tie-in Joint) | C-52-0102-CMA04-1030 | C-52-0102-CMA04-1030: SS 1 | C-52-0102-CMA04-1050 | C-52-0102-CMA04-1050: SS 1 | 2024-10-28 07:00 | 2024-10-29 17:00
C-52-0102-CMA04-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CMA04-1040 | C-52-0102-CMA04-1040: SS 1 | C-52-0102-CMA04-1060 | C-52-0102-CMA04-1060: FS | 2024-10-29 07:00 | 2024-10-30 17:00
C-52-0102-CMA04-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 | Holiday Testing | C-52-0102-CMA04-1050 | C-52-0102-CMA04-1050: FS | C-52-0102-CMA04-1070, C-52-0102-PL-CA-5220, C-52-0102-PL-CA-5220 | C-52-0102-CMA04-1070: FS, C-52-0102-PL-CA-5220: FS 14, C-52-0102-PL-CA-5220: FF | 2024-10-31 07:00 | 2024-10-31 17:00
C-52-0102-CMA04-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 | Padding | C-52-0102-CMA04-1060 | C-52-0102-CMA04-1060: FS | C-52-0102-PL-ME-7400 | C-52-0102-PL-ME-7400: FS | 2024-11-01 07:00 | 2024-11-01 17:00
C-52-0102-CMA05-0970 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 | Excavation (Manual-Trial Pit) | C-52-0102-CMA04-0970 | C-52-0102-CMA04-0970: FS | C-52-0102-CMA05-0980, C-52-0102-CMA01-0980 | C-52-0102-CMA05-0980: SS, C-52-0102-CMA01-0980: FS | 2024-09-27 | 2024-10-31 17:00
C-52-0102-CMA05-0980 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 | Sabkha Gatch Laying | C-52-0102-CMA05-0970 | C-52-0102-CMA05-0970: SS | C-52-0102-CMA05-0990 | C-52-0102-CMA05-0990: SS 1 | 2024-10-03 | 2024-10-31 17:00
C-52-0102-CMA05-0990 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 | Sabka Gatch Compaction | C-52-0102-CMA05-0980 | C-52-0102-CMA05-0980: SS 1 | C-52-0102-CMA05-1000 | C-52-0102-CMA05-1000: SS | 2024-10-04 | 2024-10-31 17:00
C-52-0102-CMA05-1000 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 | Trench Excavation | C-52-0102-CMA05-0990 | C-52-0102-CMA05-0990: SS | C-52-0102-CMA05-1010 | C-52-0102-CMA05-1010: FF | 2024-10-10 | 2024-10-28 17:00
C-52-0102-CMA05-1010 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 | Bedding | C-52-0102-CMA05-1000 | C-52-0102-CMA05-1000: FF | C-52-0102-CMA05-1020 | C-52-0102-CMA05-1020: FS | 2024-10-11 | 2024-10-28 17:00
C-52-0102-CMA05-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 | Lowering | C-52-0102-CMA05-1010 | C-52-0102-CMA05-1010: FS | C-52-0102-CMA05-1030 | C-52-0102-CMA05-1030: SS | 2024-10-29 07:00 | 2024-10-29 17:00
C-52-0102-CMA05-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 | Section Tie-in Welding | C-52-0102-CMA05-1020 | C-52-0102-CMA05-1020: SS | C-52-0102-CMA05-1040 | C-52-0102-CMA05-1040: SS 1 | 2024-10-29 07:00 | 2024-10-30 17:00
C-52-0102-CMA05-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 | NDT (Tie-in Joint) | C-52-0102-CMA05-1030 | C-52-0102-CMA05-1030: SS 1 | C-52-0102-CMA05-1050 | C-52-0102-CMA05-1050: SS 1 | 2024-10-30 07:00 | 2024-10-31 17:00
C-52-0102-CMA05-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CMA05-1040 | C-52-0102-CMA05-1040: SS 1 | C-52-0102-CMA05-1060 | C-52-0102-CMA05-1060: FS | 2024-10-31 07:00 | 2024-11-01 17:00
C-52-0102-CMA05-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 | Holiday Testing | C-52-0102-CMA05-1050 | C-52-0102-CMA05-1050: FS | C-52-0102-CMA05-1070, C-52-0102-PL-CA-5220 | C-52-0102-CMA05-1070: FS, C-52-0102-PL-CA-5220: FS | 2024-11-02 07:00 | 2024-11-02 17:00
C-52-0102-CMA05-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 | Padding | C-52-0102-CMA05-1060 | C-52-0102-CMA05-1060: FS | C-52-0102-PL-ME-7400 | C-52-0102-PL-ME-7400: FS | 2024-11-04 07:00 | 2024-11-04 17:00
C-52-0102-CMA01-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 | Sabkha Gatch Laying | C-52-0102-CMA05-0970 | C-52-0102-CMA05-0970: FS | C-52-0102-CMA01-0990, C-52-0102-CMA02-0980 | C-52-0102-CMA01-0990: SS 1, C-52-0102-CMA02-0980: FS | 2024-11-01 07:00 | 2024-11-06 17:00
C-52-0102-CMA01-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 | Sabka Gatch Compaction | C-52-0102-CMA01-0980 | C-52-0102-CMA01-0980: SS 1 | C-52-0102-CMA01-1000 | C-52-0102-CMA01-1000: FS | 2024-11-02 07:00 | 2024-11-07 17:00
C-52-0102-CMA01-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 | Trench Excavation | C-52-0102-CMA01-0990 | C-52-0102-CMA01-0990: FS | C-52-0102-CMA01-1010 | C-52-0102-CMA01-1010: FF | 2024-11-08 07:00 | 2024-11-09 17:00
C-52-0102-CMA01-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 | Bedding | C-52-0102-CMA01-1000 | C-52-0102-CMA01-1000: FF | C-52-0102-CMA01-1020 | C-52-0102-CMA01-1020: FS | 2024-11-09 07:00 | 2024-11-09 17:00
C-52-0102-CMA01-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 | Lowering | C-52-0102-CMA01-1010 | C-52-0102-CMA01-1010: FS | C-52-0102-CMA01-1030 | C-52-0102-CMA01-1030: SS | 2024-11-11 07:00 | 2024-11-11 17:00
C-52-0102-CMA01-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 | Section Tie-in Welding | C-52-0102-CMA01-1020 | C-52-0102-CMA01-1020: SS | C-52-0102-CMA01-1040 | C-52-0102-CMA01-1040: SS 1 | 2024-11-11 07:00 | 2024-11-12 17:00
C-52-0102-CMA01-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 | NDT (Tie-in Joint) | C-52-0102-CMA01-1030 | C-52-0102-CMA01-1030: SS 1 | C-52-0102-CMA01-1050 | C-52-0102-CMA01-1050: SS 1 | 2024-11-12 07:00 | 2024-11-13 17:00
C-52-0102-CMA01-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CMA01-1040 | C-52-0102-CMA01-1040: SS 1 | C-52-0102-CMA01-1060 | C-52-0102-CMA01-1060: FS | 2024-11-13 07:00 | 2024-11-14 17:00
C-52-0102-CMA01-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 | Holiday Testing | C-52-0102-CMA01-1050 | C-52-0102-CMA01-1050: FS | C-52-0102-CMA01-1070, C-52-0102-PL-CA-5220 | C-52-0102-CMA01-1070: FS, C-52-0102-PL-CA-5220: FS | 2024-11-15 07:00 | 2024-11-15 17:00
C-52-0102-CMA01-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 | Padding | C-52-0102-CMA01-1060 | C-52-0102-CMA01-1060: FS | C-52-0102-PL-ME-7400 | C-52-0102-PL-ME-7400: FS | 2024-11-16 07:00 | 2024-11-16 17:00
C-52-0102-CMA02-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 | Sabkha Gatch Laying | C-52-0102-CMA01-0980 | C-52-0102-CMA01-0980: FS | C-52-0102-CMA02-0990, C-52-0102-CMA03-0980 | C-52-0102-CMA02-0990: SS 1, C-52-0102-CMA03-0980: FS | 2024-11-07 07:00 | 2024-11-12 17:00
C-52-0102-CMA02-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 | Sabka Gatch Compaction | C-52-0102-CMA02-0980 | C-52-0102-CMA02-0980: SS 1 | C-52-0102-CMA02-1000 | C-52-0102-CMA02-1000: FS | 2024-11-08 07:00 | 2024-11-13 17:00
C-52-0102-CMA02-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 | Trench Excavation | C-52-0102-CMA02-0990 | C-52-0102-CMA02-0990: FS | C-52-0102-CMA02-1010 | C-52-0102-CMA02-1010: FF | 2024-11-14 07:00 | 2024-11-15 17:00
C-52-0102-CMA02-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 | Bedding | C-52-0102-CMA02-1000 | C-52-0102-CMA02-1000: FF | C-52-0102-CMA02-1020 | C-52-0102-CMA02-1020: FS | 2024-11-15 07:00 | 2024-11-15 17:00
C-52-0102-CMA02-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 | Lowering | C-52-0102-CMA02-1010 | C-52-0102-CMA02-1010: FS | C-52-0102-CMA02-1030 | C-52-0102-CMA02-1030: SS | 2024-11-16 07:00 | 2024-11-16 17:00
C-52-0102-CMA02-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 | Section Tie-in Welding | C-52-0102-CMA02-1020 | C-52-0102-CMA02-1020: SS | C-52-0102-CMA02-1040 | C-52-0102-CMA02-1040: SS 1 | 2024-11-16 07:00 | 2024-11-18 17:00
C-52-0102-CMA02-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 | NDT (Tie-in Joint) | C-52-0102-CMA02-1030 | C-52-0102-CMA02-1030: SS 1 | C-52-0102-CMA02-1050 | C-52-0102-CMA02-1050: SS 1 | 2024-11-18 07:00 | 2024-11-19 17:00
C-52-0102-CMA02-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CMA02-1040 | C-52-0102-CMA02-1040: SS 1 | C-52-0102-CMA02-1060 | C-52-0102-CMA02-1060: FS | 2024-11-19 07:00 | 2024-11-20 17:00
C-52-0102-CMA02-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 | Holiday Testing | C-52-0102-CMA02-1050 | C-52-0102-CMA02-1050: FS | C-52-0102-CMA02-1070, C-52-0102-PL-CA-5220 | C-52-0102-CMA02-1070: FS, C-52-0102-PL-CA-5220: FS | 2024-11-21 07:00 | 2024-11-21 17:00
C-52-0102-CMA02-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 | Padding | C-52-0102-CMA02-1060 | C-52-0102-CMA02-1060: FS | C-52-0102-PL-ME-7400 | C-52-0102-PL-ME-7400: FS | 2024-11-22 07:00 | 2024-11-22 17:00
C-52-0102-CMA03-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 | Sabkha Gatch Laying | C-52-0102-CMA02-0980 | C-52-0102-CMA02-0980: FS | C-52-0102-CMA03-0990 | C-52-0102-CMA03-0990: SS 1 | 2024-11-13 07:00 | 2024-11-18 17:00
C-52-0102-CMA03-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 | Sabka Gatch Compaction | C-52-0102-CMA03-0980 | C-52-0102-CMA03-0980: SS 1 | C-52-0102-CMA03-1000 | C-52-0102-CMA03-1000: FS | 2024-11-14 07:00 | 2024-11-19 17:00
C-52-0102-CMA03-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 | Trench Excavation | C-52-0102-CMA03-0990 | C-52-0102-CMA03-0990: FS | C-52-0102-CMA03-1010 | C-52-0102-CMA03-1010: FF | 2024-11-20 07:00 | 2024-11-21 17:00
C-52-0102-CMA03-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 | Bedding | C-52-0102-CMA03-1000 | C-52-0102-CMA03-1000: FF | C-52-0102-CMA03-1020 | C-52-0102-CMA03-1020: FS | 2024-11-21 07:00 | 2024-11-21 17:00
C-52-0102-CMA03-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 | Lowering | C-52-0102-CMA03-1010 | C-52-0102-CMA03-1010: FS | C-52-0102-CMA03-1030 | C-52-0102-CMA03-1030: SS | 2024-11-22 07:00 | 2024-11-22 17:00
C-52-0102-CMA03-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 | Section Tie-in Welding | C-52-0102-CMA03-1020 | C-52-0102-CMA03-1020: SS | C-52-0102-CMA03-1040 | C-52-0102-CMA03-1040: SS 1 | 2024-11-22 07:00 | 2024-11-23 17:00
C-52-0102-CMA03-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 | NDT (Tie-in Joint) | C-52-0102-CMA03-1030 | C-52-0102-CMA03-1030: SS 1 | C-52-0102-CMA03-1050 | C-52-0102-CMA03-1050: SS 1 | 2024-11-23 07:00 | 2024-11-25 17:00
C-52-0102-CMA03-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CMA03-1040 | C-52-0102-CMA03-1040: SS 1 | C-52-0102-CMA03-1060 | C-52-0102-CMA03-1060: FS | 2024-11-25 07:00 | 2024-11-26 17:00
C-52-0102-CMA03-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 | Holiday Testing | C-52-0102-CMA03-1050 | C-52-0102-CMA03-1050: FS | C-52-0102-CMA03-1070, C-52-0102-PL-CA-5220 | C-52-0102-CMA03-1070: FS, C-52-0102-PL-CA-5220: FS | 2024-11-27 07:00 | 2024-11-27 17:00
C-52-0102-CMA03-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 | Padding | C-52-0102-CMA03-1060 | C-52-0102-CMA03-1060: FS | C-52-0102-PL-ME-7400 | C-52-0102-PL-ME-7400: FS | 2024-11-28 07:00 | 2024-11-28 17:00
C-52-0102-CME01-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 | Trench Excavation | C-52-0102-PL-ME-2800, C-52-HG01-CME03-1000 | C-52-0102-PL-ME-2800: FS 1, C-52-HG01-CME03-1000: FS 1 | C-52-0102-CME01-1010, C-52-0102-CME02-1000 | C-52-0102-CME01-1010: FS, C-52-0102-CME02-1000: SS 1 | 2024-11-26 07:00 | 2024-11-27 17:00
C-52-0102-CME01-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 | Bedding | C-52-0102-CME01-1000 | C-52-0102-CME01-1000: FS | C-52-0102-CME01-1020 | C-52-0102-CME01-1020: FS | 2024-11-28 07:00 | 2024-11-29 17:00
C-52-0102-CME01-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 | Lowering | C-52-0102-CME01-1010 | C-52-0102-CME01-1010: FS | C-52-0102-CME01-1030 | C-52-0102-CME01-1030: FS | 2024-11-30 07:00 | 2024-12-04 17:00
C-52-0102-CME01-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 | Section Tie-in Welding | C-52-0102-CME01-1020 | C-52-0102-CME01-1020: FS | C-52-0102-CME01-1040 | C-52-0102-CME01-1040: FS | 2024-12-05 07:00 | 2024-12-06 17:00
C-52-0102-CME01-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 | NDT (Tie-in Joint) | C-52-0102-CME01-1030 | C-52-0102-CME01-1030: FS | C-52-0102-CME01-1050 | C-52-0102-CME01-1050: FS | 2024-12-07 07:00 | 2024-12-09 17:00
C-52-0102-CME01-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CME01-1040 | C-52-0102-CME01-1040: FS | C-52-0102-CME01-1060 | C-52-0102-CME01-1060: FS | 2024-12-10 07:00 | 2024-12-11 17:00
C-52-0102-CME01-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 | Holiday Testing | C-52-0102-CME01-1050 | C-52-0102-CME01-1050: FS | C-52-0102-CME01-1070, C-52-0102-PL-CA-5220 | C-52-0102-CME01-1070: FS, C-52-0102-PL-CA-5220: FS | 2024-12-12 07:00 | 2024-12-13 17:00
C-52-0102-CME01-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 | Padding & Back Filling | C-52-0102-CME01-1060 | C-52-0102-CME01-1060: FS | C-52-0102-PL-ME-7400 | C-52-0102-PL-ME-7400: FS | 2024-12-14 07:00 | 2024-12-16 17:00
C-52-0102-CME02-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 | Trench Excavation | C-52-0102-CME01-1000 | C-52-0102-CME01-1000: SS 1 | C-52-0102-CME02-1010, C-52-0102-CME03-1000 | C-52-0102-CME02-1010: FS, C-52-0102-CME03-1000: SS 1 | 2024-11-27 07:00 | 2024-11-28 17:00
C-52-0102-CME02-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 | Bedding | C-52-0102-CME02-1000 | C-52-0102-CME02-1000: FS | C-52-0102-CME02-1020 | C-52-0102-CME02-1020: FS | 2024-11-29 07:00 | 2024-11-30 17:00
C-52-0102-CME02-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 | Lowering | C-52-0102-CME02-1010 | C-52-0102-CME02-1010: FS | C-52-0102-CME02-1030 | C-52-0102-CME02-1030: FS | 2024-12-04 07:00 | 2024-12-05 17:00
C-52-0102-CME02-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 | Section Tie-in Welding | C-52-0102-CME02-1020 | C-52-0102-CME02-1020: FS | C-52-0102-CME02-1040 | C-52-0102-CME02-1040: FS | 2024-12-06 07:00 | 2024-12-07 17:00
C-52-0102-CME02-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 | NDT (Tie-in Joint) | C-52-0102-CME02-1030 | C-52-0102-CME02-1030: FS | C-52-0102-CME02-1050 | C-52-0102-CME02-1050: FS | 2024-12-09 07:00 | 2024-12-10 17:00
C-52-0102-CME02-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CME02-1040 | C-52-0102-CME02-1040: FS | C-52-0102-CME02-1060 | C-52-0102-CME02-1060: FS | 2024-12-11 07:00 | 2024-12-12 17:00
C-52-0102-CME02-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 | Holiday Testing | C-52-0102-CME02-1050 | C-52-0102-CME02-1050: FS | C-52-0102-CME02-1070, C-52-0102-PL-CA-5220 | C-52-0102-CME02-1070: FS, C-52-0102-PL-CA-5220: FS | 2024-12-13 07:00 | 2024-12-14 17:00
C-52-0102-CME02-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 | Padding & Back Filling | C-52-0102-CME02-1060 | C-52-0102-CME02-1060: FS | C-52-0102-PL-ME-7400 | C-52-0102-PL-ME-7400: FS | 2024-12-16 07:00 | 2024-12-17 17:00
C-52-0102-CME03-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 | Trench Excavation | C-52-0102-CME02-1000 | C-52-0102-CME02-1000: SS 1 | C-52-0102-CME03-1010, C-52-0102-CME04-1000 | C-52-0102-CME03-1010: FS, C-52-0102-CME04-1000: SS | 2024-11-28 07:00 | 2024-11-29 17:00
C-52-0102-CME03-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 | Bedding | C-52-0102-CME03-1000 | C-52-0102-CME03-1000: FS | C-52-0102-CME03-1020 | C-52-0102-CME03-1020: FS | 2024-11-30 07:00 | 2024-12-04 17:00
C-52-0102-CME03-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 | Lowering | C-52-0102-CME03-1010 | C-52-0102-CME03-1010: FS | C-52-0102-CME03-1030 | C-52-0102-CME03-1030: FS | 2024-12-05 07:00 | 2024-12-06 17:00
C-52-0102-CME03-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 | Section Tie-in Welding | C-52-0102-CME03-1020 | C-52-0102-CME03-1020: FS | C-52-0102-CME03-1040 | C-52-0102-CME03-1040: FS | 2024-12-07 07:00 | 2024-12-09 17:00
C-52-0102-CME03-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 | NDT (Tie-in Joint) | C-52-0102-CME03-1030 | C-52-0102-CME03-1030: FS | C-52-0102-CME03-1050 | C-52-0102-CME03-1050: FS | 2024-12-10 07:00 | 2024-12-11 17:00
C-52-0102-CME03-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CME03-1040 | C-52-0102-CME03-1040: FS | C-52-0102-CME03-1060 | C-52-0102-CME03-1060: FS | 2024-12-12 07:00 | 2024-12-13 17:00
C-52-0102-CME03-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 | Holiday Testing | C-52-0102-CME03-1050 | C-52-0102-CME03-1050: FS | C-52-0102-CME03-1070, C-52-0102-PL-CA-5220 | C-52-0102-CME03-1070: FS, C-52-0102-PL-CA-5220: FS | 2024-12-14 07:00 | 2024-12-16 17:00
C-52-0102-CME03-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 | Padding & Back Filling | C-52-0102-CME03-1060 | C-52-0102-CME03-1060: FS | C-52-0102-PL-ME-7400 | C-52-0102-PL-ME-7400: FS | 2024-12-17 07:00 | 2024-12-18 17:00
C-52-0102-CME04-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 | Trench Excavation | C-52-0102-CME03-1000 | C-52-0102-CME03-1000: SS | C-52-0102-CME04-1010, C-52-0102-CME05-1000 | C-52-0102-CME04-1010: FS, C-52-0102-CME05-1000: SS | 2024-11-28 07:00 | 2024-11-29 17:00
C-52-0102-CME04-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 | Bedding | C-52-0102-CME04-1000 | C-52-0102-CME04-1000: FS | C-52-0102-CME04-1020 | C-52-0102-CME04-1020: FS | 2024-11-30 07:00 | 2024-12-04 17:00
C-52-0102-CME04-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 | Lowering | C-52-0102-CME04-1010 | C-52-0102-CME04-1010: FS | C-52-0102-CME04-1030 | C-52-0102-CME04-1030: FS | 2024-12-05 07:00 | 2024-12-06 17:00
C-52-0102-CME04-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 | Section Tie-in Welding | C-52-0102-CME04-1020 | C-52-0102-CME04-1020: FS | C-52-0102-CME04-1040 | C-52-0102-CME04-1040: FS | 2024-12-07 07:00 | 2024-12-09 17:00
C-52-0102-CME04-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 | NDT (Tie-in Joint) | C-52-0102-CME04-1030 | C-52-0102-CME04-1030: FS | C-52-0102-CME04-1050 | C-52-0102-CME04-1050: FS | 2024-12-10 07:00 | 2024-12-11 17:00
C-52-0102-CME04-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CME04-1040 | C-52-0102-CME04-1040: FS | C-52-0102-CME04-1060 | C-52-0102-CME04-1060: FS | 2024-12-12 07:00 | 2024-12-13 17:00
C-52-0102-CME04-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 | Holiday Testing | C-52-0102-CME04-1050 | C-52-0102-CME04-1050: FS | C-52-0102-CME04-1070, C-52-0102-PL-CA-5220 | C-52-0102-CME04-1070: FS, C-52-0102-PL-CA-5220: FS | 2024-12-14 07:00 | 2024-12-16 17:00
C-52-0102-CME04-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 | Padding & Back Filling | C-52-0102-CME04-1060 | C-52-0102-CME04-1060: FS | C-52-0102-PL-ME-7400 | C-52-0102-PL-ME-7400: FS | 2024-12-17 07:00 | 2024-12-18 17:00
C-52-0102-CME05-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 | Trench Excavation | C-52-0102-CME04-1000 | C-52-0102-CME04-1000: SS | C-52-0102-CME05-1010, C-52-0102-CME06-1090 | C-52-0102-CME05-1010: FS, C-52-0102-CME06-1090: SS | 2024-11-28 07:00 | 2024-11-29 17:00
C-52-0102-CME05-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 | Bedding | C-52-0102-CME05-1000 | C-52-0102-CME05-1000: FS | C-52-0102-CME05-1020 | C-52-0102-CME05-1020: FS | 2024-11-30 07:00 | 2024-12-04 17:00
C-52-0102-CME05-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 | Lowering | C-52-0102-CME05-1010 | C-52-0102-CME05-1010: FS | C-52-0102-CME05-1030 | C-52-0102-CME05-1030: FS | 2024-12-05 07:00 | 2024-12-06 17:00
C-52-0102-CME05-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 | Section Tie-in Welding | C-52-0102-CME05-1020 | C-52-0102-CME05-1020: FS | C-52-0102-CME05-1040 | C-52-0102-CME05-1040: FS | 2024-12-07 07:00 | 2024-12-09 17:00
C-52-0102-CME05-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 | NDT (Tie-in Joint) | C-52-0102-CME05-1030 | C-52-0102-CME05-1030: FS | C-52-0102-CME05-1050 | C-52-0102-CME05-1050: FS | 2024-12-10 07:00 | 2024-12-11 17:00
C-52-0102-CME05-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CME05-1040 | C-52-0102-CME05-1040: FS | C-52-0102-CME05-1060 | C-52-0102-CME05-1060: FS | 2024-12-12 07:00 | 2024-12-13 17:00
C-52-0102-CME05-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 | Holiday Testing | C-52-0102-CME05-1050 | C-52-0102-CME05-1050: FS | C-52-0102-CME05-1070, C-52-0102-PL-CA-5220 | C-52-0102-CME05-1070: FS, C-52-0102-PL-CA-5220: FS | 2024-12-14 07:00 | 2024-12-16 17:00
C-52-0102-CME05-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 | Padding & Back Filling | C-52-0102-CME05-1060 | C-52-0102-CME05-1060: FS | C-52-0102-PL-ME-7400 | C-52-0102-PL-ME-7400: FS | 2024-12-17 07:00 | 2024-12-18 17:00
C-52-0102-CNH10-1000 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1110 | C-PER-1110: FS | C-52-0102-CNH10-1020, C-52-0102-CNH10-1010 | C-52-0102-CNH10-1020: FS, C-52-0102-CNH10-1010: SS 21 | 2024-06-25 | 2024-07-23
C-52-0102-CNH10-1020 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-0102-CNH10-1000 | C-52-0102-CNH10-1000: FS | C-52-0102-CNH10-1030 | C-52-0102-CNH10-1030: FF | 2024-07-16 | 2024-07-26 09:24
C-52-0102-CNH10-1010 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 | Driving & Receiving Pit Excavation | C-52-0102-CNH10-1000 | C-52-0102-CNH10-1000: SS 21 | C-52-0102-CNH10-1030 | C-52-0102-CNH10-1030: SS 7 | 2024-07-26 | 2024-09-17
C-52-0102-CNH10-1030 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0102-CNH10-1010, C-52-0102-CNH10-1020 | C-52-0102-CNH10-1010: SS 7, C-52-0102-CNH10-1020: FF | C-52-0102-CNH10-1040 | C-52-0102-CNH10-1040: FS | 2024-07-26 | 2024-08-27
C-52-0102-CNH10-1040 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 | Floor Blinding & French Drain in Driving Pit | C-52-0102-CNH10-1030 | C-52-0102-CNH10-1030: FS | C-52-0102-CNH10-1050 | C-52-0102-CNH10-1050: FS | 2024-09-06 | 2024-09-19
C-52-0102-CNH10-1050 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0102-CNH10-1040 | C-52-0102-CNH10-1040: FS | C-52-0102-CNH10-1060 | C-52-0102-CNH10-1060: SS 7 | 2024-09-21 | 2024-10-09
C-52-0102-CNH10-1060 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 | Construction of Exit Wall with Ring | C-52-0102-CNH10-1050 | C-52-0102-CNH10-1050: SS 7 | C-52-0102-CNH10-1200 | C-52-0102-CNH10-1200: FS | 2024-10-02 | 2024-10-12
C-52-0102-CNH10-1200 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 | Jacking of MTBM & RC Sleeves | C-52-0102-CNH10-1060 | C-52-0102-CNH10-1060: FS | C-52-0102-CNH10-1210, C-52-0506-PL-ME-4810, C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, PRECOM-52-0506-1000, C-52-0506-PL-CI-6000, ML1679-E13 | C-52-0102-CNH10-1210: FS, C-52-0506-PL-ME-4810: FF, C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF, PRECOM-52-0506-1000: FS, C-52-0506-PL-CI-6000: FF, ML1679-E13: FS | 2024-10-15 | 2024-10-30 17:00
C-52-0102-CNH10-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0102-CNH10-1200 | C-52-0102-CNH10-1200: FS | C-52-0102-CNH10-1070 | C-52-0102-CNH10-1070: FS | 2024-10-31 07:00 | 2024-11-04 17:00
C-52-0102-CNH10-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 | Lowering & Welding of Carrier Pipe | C-52-0102-CNH10-1210 | C-52-0102-CNH10-1210: FS | C-52-0102-CNH10-1080, C-52-0102-CNH10-1080 | C-52-0102-CNH10-1080: SS 1, C-52-0102-CNH10-1080: FF 1 | 2024-11-05 07:00 | 2024-11-21 17:00
C-52-0102-CNH10-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0102-CNH10-1070, C-52-0102-CNH10-1070 | C-52-0102-CNH10-1070: SS 1, C-52-0102-CNH10-1070: FF 1 | C-52-0102-CNH10-1090, C-52-0102-CNH10-1220 | C-52-0102-CNH10-1090: FS 10, C-52-0102-CNH10-1220: FS | 2024-11-09 07:00 | 2024-11-22 17:00
C-52-0102-CNH10-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0102-CNH10-1080 | C-52-0102-CNH10-1080: FS 10 | C-52-0102-CNH10-1220 | C-52-0102-CNH10-1220: FS | 2024-12-07 07:00 | 2024-12-16 17:00
C-52-0102-CNH10-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 | Inner Grout b/w Main & RC Pipe | C-52-0102-CNH10-1080, C-52-0102-CNH10-1090 | C-52-0102-CNH10-1080: FS, C-52-0102-CNH10-1090: FS | C-52-0102-CNH10-1800 | C-52-0102-CNH10-1800: FS | 2024-12-17 07:00 | 2024-12-21 17:00
C-52-0102-CNH10-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.1.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0102-CNH10-1220 | C-52-0102-CNH10-1220: FS | C-52-0102-PL-ME-7400, PRECOM-52-0201-1000, ML1679-E13, ML1080 | C-52-0102-PL-ME-7400: FS, PRECOM-52-0201-1000: FS, ML1679-E13: FS, ML1080: FS | 2024-12-23 07:00 | 2025-01-08 17:00
C-52-0102-CNH09-1000 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1100 | C-PER-1100: FS | C-52-0102-CNH09-1020, C-52-0102-CNH09-1010 | C-52-0102-CNH09-1020: FS, C-52-0102-CNH09-1010: SS 21 | 2024-07-27 07:00 | 2024-09-26 17:00
C-52-0102-CNH09-1020 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-0102-CNH09-1000 | C-52-0102-CNH09-1000: FS | C-52-0102-CNH09-1030 | C-52-0102-CNH09-1030: FS | 2024-08-26 07:00 | 2024-09-25
C-52-0102-CNH09-1010 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 | Driving & Receiving Pit Excavation | C-52-0102-CNH09-1000 | C-52-0102-CNH09-1000: SS 21 | C-52-0102-CNH09-1030 | C-52-0102-CNH09-1030: SS 7 | 2024-08-27 | 2024-11-02 17:00
C-52-0102-CNH09-1030 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0102-CNH09-1010, C-52-0102-CNH09-1020 | C-52-0102-CNH09-1010: SS 7, C-52-0102-CNH09-1020: FS | C-52-0102-CNH09-1040 | C-52-0102-CNH09-1040: FS | 2024-09-03 | 2024-10-24
C-52-0102-CNH09-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 | Floor Blinding & French Drain in Driving Pit | C-52-0102-CNH09-1030 | C-52-0102-CNH09-1030: FS | C-52-0102-CNH09-1050 | C-52-0102-CNH09-1050: FS | 2024-10-26 07:00 | 2024-11-02 17:00
C-52-0102-CNH09-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0102-CNH09-1040 | C-52-0102-CNH09-1040: FS | C-52-0102-CNH09-1060 | C-52-0102-CNH09-1060: SS 7 | 2024-11-04 07:00 | 2024-11-12 17:00
C-52-0102-CNH09-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 | Construction of Exit Wall with Ring | C-52-0102-CNH09-1050 | C-52-0102-CNH09-1050: SS 7 | C-52-0102-CNH09-1200 | C-52-0102-CNH09-1200: FS | 2024-11-12 07:00 | 2024-11-18 17:00
C-52-0102-CNH09-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.2.2 | Jacking of MTBM & RC Sleeves | C-52-0102-CNH09-1060 | C-52-0102-CNH09-1060: FS | C-52-0102-CNH09-1210, C-52-0102-CNM07-1200 | C-52-0102-CNH09-1210: FS, C-52-0102-CNM07-1200: FS | 2024-11-19 07:00 | 2024-12-09 17:00
C-52-0102-CNH09-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.2.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0102-CNH09-1200 | C-52-0102-CNH09-1200: FS | C-52-0102-CNH09-1070 | C-52-0102-CNH09-1070: FS | 2024-12-10 07:00 | 2024-12-13 17:00
C-52-0102-CNH09-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 | Lowering & Welding of Carrier Pipe | C-52-0102-CNH09-1210 | C-52-0102-CNH09-1210: FS | C-52-0102-CNH09-1080 | C-52-0102-CNH09-1080: SS 1 | 2024-12-14 07:00 | 2025-01-04 17:00
C-52-0102-CNH09-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0102-CNH09-1070 | C-52-0102-CNH09-1070: SS 1 | C-52-0102-CNH09-1090 | C-52-0102-CNH09-1090: FS 10 | 2024-12-16 07:00 | 2025-01-08 17:00
C-52-0102-CNH09-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0102-CNH09-1080 | C-52-0102-CNH09-1080: FS 10 | C-52-0102-CNH09-1220 | C-52-0102-CNH09-1220: FS | 2025-01-21 07:00 | 2025-01-29 17:00
C-52-0102-CNH09-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.2.2 | Inner Grout b/w Main & RC Pipe | C-52-0102-CNH09-1090 | C-52-0102-CNH09-1090: FS | C-52-0102-CNH09-1800 | C-52-0102-CNH09-1800: FS | 2025-01-30 07:00 | 2025-02-04 17:00
C-52-0102-CNH09-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.2.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0102-CNH09-1220 | C-52-0102-CNH09-1220: FS | C-52-0102-PL-ME-7400, PRECOM-52-0201-1000, ML1679-E13, ML1090 | C-52-0102-PL-ME-7400: FS, PRECOM-52-0201-1000: FS, ML1679-E13: FS, ML1090: FS | 2025-02-05 07:00 | 2025-02-20 17:00
C-52-0102-CNH08-1000 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1090 | C-PER-1090: FS | C-52-0102-CNH08-1020, C-52-0102-CNH08-1010 | C-52-0102-CNH08-1020: FS 1, C-52-0102-CNH08-1010: SS 23 | 2024-07-27 07:00 | 2024-09-18
C-52-0102-CNH08-1020 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-0102-CNH08-1000 | C-52-0102-CNH08-1000: FS 1 | C-52-0102-CNH08-1030 | C-52-0102-CNH08-1030: FS | 2024-09-02 | 2024-09-20
C-52-0102-CNH08-1010 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 | Driving & Receiving Pit Excavation | C-52-0102-CNH08-1000 | C-52-0102-CNH08-1000: SS 23 | C-52-0102-CNH08-1030 | C-52-0102-CNH08-1030: SS 7 | 2024-09-04 | 2024-10-25
C-52-0102-CNH08-1030 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0102-CNH08-1010, C-52-0102-CNH08-1020 | C-52-0102-CNH08-1010: SS 7, C-52-0102-CNH08-1020: FS | C-52-0102-CNH08-1040 | C-52-0102-CNH08-1040: FS | 2024-09-10 | 2024-09-25
C-52-0102-CNH08-1040 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 | Floor Blinding & French Drain in Driving Pit | C-52-0102-CNH08-1030 | C-52-0102-CNH08-1030: FS | C-52-0102-CNH08-1050 | C-52-0102-CNH08-1050: FS | 2024-10-19 | 2024-10-25
C-52-0102-CNH08-1050 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0102-CNH08-1040 | C-52-0102-CNH08-1040: FS | C-52-0102-CNH08-1060 | C-52-0102-CNH08-1060: SS 3 | 2024-10-24 | 2024-11-01 17:00
C-52-0102-CNH08-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 | Construction of Exit Wall with Ring | C-52-0102-CNH08-1050 | C-52-0102-CNH08-1050: SS 3 | C-52-0102-CNH08-1200 | C-52-0102-CNH08-1200: FS | 2024-10-28 07:00 | 2024-11-02 17:00
C-52-0102-CNH08-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.3.2 | Jacking of MTBM & RC Sleeves | C-52-0102-CNH08-1060 | C-52-0102-CNH08-1060: FS | C-52-0102-CNH08-1210 | C-52-0102-CNH08-1210: FS | 2024-11-04 07:00 | 2024-12-19 17:00
C-52-0102-CNH08-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.3.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0102-CNH08-1200 | C-52-0102-CNH08-1200: FS | C-52-0102-CNH08-1070 | C-52-0102-CNH08-1070: FS | 2024-12-20 07:00 | 2024-12-24 17:00
C-52-0102-CNH08-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 | Lowering & Welding of Carrier Pipe | C-52-0102-CNH08-1210 | C-52-0102-CNH08-1210: FS | C-52-0102-CNH08-1080 | C-52-0102-CNH08-1080: SS 1 | 2024-12-25 07:00 | 2025-02-10 17:00
C-52-0102-CNH08-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0102-CNH08-1070 | C-52-0102-CNH08-1070: SS 1 | C-52-0102-CNH08-1090 | C-52-0102-CNH08-1090: FS 10 | 2024-12-26 07:00 | 2025-02-13 17:00
C-52-0102-CNH08-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0102-CNH08-1080 | C-52-0102-CNH08-1080: FS 10 | C-52-0102-CNH08-1220 | C-52-0102-CNH08-1220: FS | 2025-02-26 07:00 | 2025-03-11 09:00
C-52-0102-CNH08-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.3.2 | Inner Grout b/w Main & RC Pipe | C-52-0102-CNH08-1090 | C-52-0102-CNH08-1090: FS | C-52-0102-CNH08-1800, C-52-0102-PL-ME-7400 | C-52-0102-CNH08-1800: FS, C-52-0102-PL-ME-7400: FS | 2025-03-11 09:00 | 2025-03-18 13:00
C-52-0102-CNH08-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.3.3.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0102-CNH08-1220 | C-52-0102-CNH08-1220: FS | PRECOM-52-0201-1000, ML1679-E13, ML1090 | PRECOM-52-0201-1000: FS, ML1679-E13: FS, ML1090: FS | 2025-03-19 07:00 | 2025-04-10 13:00
C-52-0102-CNM07-1000 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1080 | C-PER-1080: FS | C-52-0102-CNM07-1020, C-52-0102-CNM07-1010, C-52-0102-CNM07-1010 | C-52-0102-CNM07-1020: FS, C-52-0102-CNM07-1010: SS 21, C-52-0102-CNM07-1010: FF 18 | 2024-09-28 | 2024-11-08 17:00
C-52-0102-CNM07-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-0102-CNM07-1000 | C-52-0102-CNM07-1000: FS | C-52-0102-CNM07-1030 | C-52-0102-CNM07-1030: FS | 2024-11-09 07:00 | 2024-11-13 17:00
C-52-0102-CNM07-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 | Driving & Receiving Pit Excavation | C-52-0102-CNM07-1000, C-52-0102-CNM07-1000 | C-52-0102-CNM07-1000: SS 21, C-52-0102-CNM07-1000: FF 18 | C-52-0102-CNM07-1030 | C-52-0102-CNM07-1030: SS 2 | 2024-11-14 07:00 | 2024-11-29 17:00
C-52-0102-CNM07-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0102-CNM07-1010, C-52-0102-CNM07-1020 | C-52-0102-CNM07-1010: SS 2, C-52-0102-CNM07-1020: FS | C-52-0102-CNM07-1040 | C-52-0102-CNM07-1040: FS | 2024-11-16 07:00 | 2024-11-27 17:00
C-52-0102-CNM07-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 | Floor Blinding & French Drain in Driving Pit | C-52-0102-CNM07-1030 | C-52-0102-CNM07-1030: FS | C-52-0102-CNM07-1050 | C-52-0102-CNM07-1050: FS | 2024-11-28 07:00 | 2024-12-06 17:00
C-52-0102-CNM07-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0102-CNM07-1040 | C-52-0102-CNM07-1040: FS | C-52-0102-CNM07-1060 | C-52-0102-CNM07-1060: SS 7 | 2024-12-07 07:00 | 2024-12-13 17:00
C-52-0102-CNM07-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 | Construction of Exit Wall with Ring | C-52-0102-CNM07-1050 | C-52-0102-CNM07-1050: SS 7 | C-52-0102-CNM07-1200 | C-52-0102-CNM07-1200: FS | 2024-12-16 07:00 | 2024-12-21 17:00
C-52-0102-CNM07-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.4.2 | Jacking of MTBM & RC Sleeves | C-52-0102-CNM07-1060, C-52-0102-CNH09-1200 | C-52-0102-CNM07-1060: FS, C-52-0102-CNH09-1200: FS | C-52-0102-CNM07-1210, C-52-HG01-CNM02-1200 | C-52-0102-CNM07-1210: FS, C-52-HG01-CNM02-1200: FS | 2024-12-23 07:00 | 2025-01-07 17:00
C-52-0102-CNM07-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.4.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0102-CNM07-1200 | C-52-0102-CNM07-1200: FS | C-52-0102-CNM07-1400 | C-52-0102-CNM07-1400: FS | 2025-01-08 07:00 | 2025-01-11 17:00
C-52-0102-CNM07-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.4.3 | Lowering & Welding of Carrier Pipe | C-52-0102-CNM07-1210 | C-52-0102-CNM07-1210: FS | C-52-0102-CNM07-1410 | C-52-0102-CNM07-1410: SS 1 | 2025-01-13 07:00 | 2025-01-29 17:00
C-52-0102-CNM07-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.4.3 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0102-CNM07-1400 | C-52-0102-CNM07-1400: SS 1 | C-52-0102-CNM07-1600 | C-52-0102-CNM07-1600: FS 10 | 2025-01-14 07:00 | 2025-02-01 17:00
C-52-0102-CNM07-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.4.4 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0102-CNM07-1410 | C-52-0102-CNM07-1410: FS 10 | C-52-0102-CNM07-1220 | C-52-0102-CNM07-1220: FS | 2025-02-14 07:00 | 2025-02-27 17:00
C-52-0102-CNM07-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.4.2 | Inner Grout b/w Main & RC Pipe | C-52-0102-CNM07-1600 | C-52-0102-CNM07-1600: FS | C-52-0102-CNM07-1800 | C-52-0102-CNM07-1800: FS | 2025-02-28 07:00 | 2025-03-06 13:00
C-52-0102-CNM07-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.4.5 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0102-CNM07-1220 | C-52-0102-CNM07-1220: FS | C-52-0102-PL-ME-7400, PRECOM-52-0201-1000, ML1679-E13 | C-52-0102-PL-ME-7400: FS, PRECOM-52-0201-1000: FS, ML1679-E13: FS | 2025-03-07 07:00 | 2025-03-28 09:00
C-52-0102-CNM05-1000 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1060 | C-PER-1060: FS | C-52-0102-CNM05-1020, C-52-0102-CNM05-1010, C-52-0102-CNM05-1010 | C-52-0102-CNM05-1020: FS, C-52-0102-CNM05-1010: SS 7, C-52-0102-CNM05-1010: FF 7 | 2024-09-04 | 2024-10-22
C-52-0102-CNM05-1020 | Completed | P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-0102-CNM05-1000 | C-52-0102-CNM05-1000: FS | C-52-0102-CNM05-1030 | C-52-0102-CNM05-1030: FS | 2024-10-15 | 2024-10-23
C-52-0102-CNM05-1010 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 | Driving & Receiving Pit Excavation | C-52-0102-CNM05-1000, C-52-0102-CNM05-1000 | C-52-0102-CNM05-1000: SS 7, C-52-0102-CNM05-1000: FF 7 | C-52-0102-CNM05-1030 | C-52-0102-CNM05-1030: SS 2 | 2024-10-16 | 2024-11-11 17:00
C-52-0102-CNM05-1030 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0102-CNM05-1010, C-52-0102-CNM05-1020 | C-52-0102-CNM05-1010: SS 2, C-52-0102-CNM05-1020: FS | C-52-0102-CNM05-1040 | C-52-0102-CNM05-1040: FS | 2024-10-24 | 2024-11-09 17:00
C-52-0102-CNM05-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 | Floor Blinding & French Drain in Driving Pit | C-52-0102-CNM05-1030 | C-52-0102-CNM05-1030: FS | C-52-0102-CNM05-1050 | C-52-0102-CNM05-1050: FS | 2024-11-11 07:00 | 2024-11-16 17:00
C-52-0102-CNM05-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0102-CNM05-1040 | C-52-0102-CNM05-1040: FS | C-52-0102-CNM05-1060 | C-52-0102-CNM05-1060: SS 7 | 2024-11-18 07:00 | 2024-11-23 17:00
C-52-0102-CNM05-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 | Construction of Exit Wall with Ring | C-52-0102-CNM05-1050 | C-52-0102-CNM05-1050: SS 7 | C-52-0102-CNM05-1200 | C-52-0102-CNM05-1200: FS | 2024-11-26 07:00 | 2024-12-04 17:00
C-52-0102-CNM05-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.6.2 | Jacking of MTBM & RC Sleeves | C-52-0102-CNM05-1060 | C-52-0102-CNM05-1060: FS | C-52-0102-CNM05-1210, C-52-06CR-CNH30-1200 | C-52-0102-CNM05-1210: FS, C-52-06CR-CNH30-1200: FS | 2024-12-05 07:00 | 2024-12-20 17:00
C-52-0102-CNM05-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.6.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0102-CNM05-1200 | C-52-0102-CNM05-1200: FS | C-52-0102-CNM05-1400 | C-52-0102-CNM05-1400: FS | 2024-12-21 07:00 | 2024-12-25 17:00
C-52-0102-CNM05-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.6.3 | Lowering & Welding of Carrier Pipe | C-52-0102-CNM05-1210 | C-52-0102-CNM05-1210: FS | C-52-0102-CNM05-1410 | C-52-0102-CNM05-1410: SS 1 | 2024-12-26 07:00 | 2025-01-14 17:00
C-52-0102-CNM05-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.6.3 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0102-CNM05-1400 | C-52-0102-CNM05-1400: SS 1 | C-52-0102-CNM05-1600 | C-52-0102-CNM05-1600: FS 10 | 2024-12-27 07:00 | 2025-01-17 17:00
C-52-0102-CNM05-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.6.4 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0102-CNM05-1410 | C-52-0102-CNM05-1410: FS 10 | C-52-0102-CNM05-1220 | C-52-0102-CNM05-1220: FS | 2025-01-30 07:00 | 2025-02-07 17:00
C-52-0102-CNM05-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.6.2 | Inner Grout b/w Main & RC Pipe | C-52-0102-CNM05-1600 | C-52-0102-CNM05-1600: FS | C-52-0102-CNM05-1800, C-52-0102-PL-CA-5240 | C-52-0102-CNM05-1800: FS, C-52-0102-PL-CA-5240: FF 2 | 2025-02-08 07:00 | 2025-02-13 17:00
C-52-0102-CNM05-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.6.5 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0102-CNM05-1220 | C-52-0102-CNM05-1220: FS | C-52-0102-PL-ME-7400, PRECOM-52-0201-1000, ML1679-E13 | C-52-0102-PL-ME-7400: FS, PRECOM-52-0201-1000: FS, ML1679-E13: FS | 2025-02-14 07:00 | 2025-03-01 17:00
C-52-HG01-CMA01-0970 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 | Excavation (Manual-Trial Pit) | C-52-HG01-PL-CI-2400 | C-52-HG01-PL-CI-2400: FS 5 | C-52-HG01-CMA01-0980, C-52-HG01-CMA05-0970 | C-52-HG01-CMA01-0980: FS, C-52-HG01-CMA05-0970: FS | 2024-10-26 07:00 | 2024-11-19 17:00
C-52-HG01-CMA01-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 | Sabkha Gatch Laying | C-52-HG01-CMA01-0970 | C-52-HG01-CMA01-0970: FS | C-52-HG01-CMA01-0990 | C-52-HG01-CMA01-0990: SS 1 | 2024-11-20 07:00 | 2024-11-27 17:00
C-52-HG01-CMA01-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 | Sabka Gatch Compaction | C-52-HG01-CMA01-0980 | C-52-HG01-CMA01-0980: SS 1 | C-52-HG01-CMA01-1000 | C-52-HG01-CMA01-1000: FS | 2024-11-21 07:00 | 2024-11-28 17:00
C-52-HG01-CMA01-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 | Trench Excavation | C-52-HG01-CMA01-0990 | C-52-HG01-CMA01-0990: FS | C-52-HG01-CMA01-1010 | C-52-HG01-CMA01-1010: FF 1 | 2024-11-29 07:00 | 2024-12-04 17:00
C-52-HG01-CMA01-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 | Bedding | C-52-HG01-CMA01-1000 | C-52-HG01-CMA01-1000: FF 1 | C-52-HG01-CMA01-1020 | C-52-HG01-CMA01-1020: FS | 2024-12-04 07:00 | 2024-12-05 17:00
C-52-HG01-CMA01-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 | Lowering | C-52-HG01-CMA01-1010, C-52-HG01-PL-ME-4800 | C-52-HG01-CMA01-1010: FS, C-52-HG01-PL-ME-4800: FS | C-52-HG01-CMA01-1030 | C-52-HG01-CMA01-1030: SS | 2024-12-06 07:00 | 2024-12-06 17:00
C-52-HG01-CMA01-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 | Section Tie-in Welding | C-52-HG01-CMA01-1020 | C-52-HG01-CMA01-1020: SS | C-52-HG01-CMA01-1040 | C-52-HG01-CMA01-1040: SS 1 | 2024-12-06 07:00 | 2024-12-09 17:00
C-52-HG01-CMA01-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 | NDT (Tie-in Joint) | C-52-HG01-CMA01-1030 | C-52-HG01-CMA01-1030: SS 1 | C-52-HG01-CMA01-1050 | C-52-HG01-CMA01-1050: SS 1 | 2024-12-07 07:00 | 2024-12-10 17:00
C-52-HG01-CMA01-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CMA01-1040 | C-52-HG01-CMA01-1040: SS 1 | C-52-HG01-CMA01-1060 | C-52-HG01-CMA01-1060: FS | 2024-12-09 07:00 | 2024-12-11 17:00
C-52-HG01-CMA01-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 | Holiday Testing | C-52-HG01-CMA01-1050 | C-52-HG01-CMA01-1050: FS | C-52-HG01-CMA01-1070, C-52-HG01-PL-CA-5220 | C-52-HG01-CMA01-1070: FS, C-52-HG01-PL-CA-5220: FF 7 | 2024-12-12 07:00 | 2024-12-12 17:00
C-52-HG01-CMA01-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 | Padding | C-52-HG01-CMA01-1060 | C-52-HG01-CMA01-1060: FS | C-52-HG01-PL-ME-7400, C-52-HG01-PL-CA-5220 | C-52-HG01-PL-ME-7400: FS, C-52-HG01-PL-CA-5220: FF | 2024-12-13 07:00 | 2024-12-13 17:00
C-52-HG01-CMA05-0970 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 | Excavation (Manual-Trial Pit) | C-52-HG01-CMA01-0970 | C-52-HG01-CMA01-0970: FS | C-52-HG01-CMA05-0980 | C-52-HG01-CMA05-0980: FS | 2024-11-20 07:00 | 2024-11-25 17:00
C-52-HG01-CMA05-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 | Sabkha Gatch Laying | C-52-HG01-CMA05-0970 | C-52-HG01-CMA05-0970: FS | C-52-HG01-CMA05-0990 | C-52-HG01-CMA05-0990: SS 1 | 2024-11-26 07:00 | 2024-11-30 17:00
C-52-HG01-CMA05-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 | Sabka Gatch Compaction | C-52-HG01-CMA05-0980 | C-52-HG01-CMA05-0980: SS 1 | C-52-HG01-CMA05-1000 | C-52-HG01-CMA05-1000: FS | 2024-11-27 07:00 | 2024-12-04 17:00
C-52-HG01-CMA05-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 | Trench Excavation | C-52-HG01-CMA05-0990 | C-52-HG01-CMA05-0990: FS | C-52-HG01-CMA05-1010 | C-52-HG01-CMA05-1010: FF | 2024-12-05 07:00 | 2024-12-06 17:00
C-52-HG01-CMA05-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 | Bedding | C-52-HG01-CMA05-1000 | C-52-HG01-CMA05-1000: FF | C-52-HG01-CMA05-1020 | C-52-HG01-CMA05-1020: FS | 2024-12-06 07:00 | 2024-12-06 17:00
C-52-HG01-CMA05-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 | Lowering | C-52-HG01-CMA05-1010 | C-52-HG01-CMA05-1010: FS | C-52-HG01-CMA05-1030 | C-52-HG01-CMA05-1030: SS | 2024-12-07 07:00 | 2024-12-07 17:00
C-52-HG01-CMA05-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 | Section Tie-in Welding | C-52-HG01-CMA05-1020 | C-52-HG01-CMA05-1020: SS | C-52-HG01-CMA05-1040 | C-52-HG01-CMA05-1040: SS 1 | 2024-12-07 07:00 | 2024-12-09 17:00
C-52-HG01-CMA05-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 | NDT (Tie-in Joint) | C-52-HG01-CMA05-1030 | C-52-HG01-CMA05-1030: SS 1 | C-52-HG01-CMA05-1050 | C-52-HG01-CMA05-1050: SS 1 | 2024-12-09 07:00 | 2024-12-10 17:00
C-52-HG01-CMA05-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CMA05-1040 | C-52-HG01-CMA05-1040: SS 1 | C-52-HG01-CMA05-1060 | C-52-HG01-CMA05-1060: FS | 2024-12-10 07:00 | 2024-12-11 17:00
C-52-HG01-CMA05-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 | Holiday Testing | C-52-HG01-CMA05-1050 | C-52-HG01-CMA05-1050: FS | C-52-HG01-CMA05-1070 | C-52-HG01-CMA05-1070: FS | 2024-12-12 07:00 | 2024-12-12 17:00
C-52-HG01-CMA05-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 | Padding | C-52-HG01-CMA05-1060 | C-52-HG01-CMA05-1060: FS | C-52-HG01-PL-ME-7400, C-52-HG01-PL-CA-5220 | C-52-HG01-PL-ME-7400: FS, C-52-HG01-PL-CA-5220: FF | 2024-12-13 07:00 | 2024-12-13 17:00
C-52-HG01-CMA06-0970 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 | Excavation (Manual-Trial Pit) | C-52-HG01-CMA04-0970 | C-52-HG01-CMA04-0970: FS | C-52-HG01-CMA06-0980 | C-52-HG01-CMA06-0980: FS | 2024-09-27 | 2024-10-03
C-52-HG01-CMA06-0980 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 | Sabkha Gatch Laying | C-52-HG01-CMA06-0970 | C-52-HG01-CMA06-0970: FS | C-52-HG01-CMA06-0990 | C-52-HG01-CMA06-0990: SS 1 | 2024-10-04 | 2024-10-09
C-52-HG01-CMA06-0990 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 | Sabka Gatch Compaction | C-52-HG01-CMA06-0980 | C-52-HG01-CMA06-0980: SS 1 | C-52-HG01-CMA06-1000 | C-52-HG01-CMA06-1000: FS | 2024-10-05 | 2024-10-10
C-52-HG01-CMA06-1000 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 | Trench Excavation | C-52-HG01-CMA06-0990 | C-52-HG01-CMA06-0990: FS | C-52-HG01-CMA06-1010 | C-52-HG01-CMA06-1010: FF | 2024-10-12 | 2024-10-18
C-52-HG01-CMA06-1010 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 | Bedding | C-52-HG01-CMA06-1000 | C-52-HG01-CMA06-1000: FF | C-52-HG01-CMA06-1020, C-52-HG01-CMA06-1030 | C-52-HG01-CMA06-1020: FS 30, C-52-HG01-CMA06-1030: FS | 2024-10-12 | 2024-10-18
C-52-HG01-CMA06-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 | Lowering | C-52-HG01-CMA06-1010 | C-52-HG01-CMA06-1010: FS 30 | C-52-HG01-CMA06-1070 | C-52-HG01-CMA06-1070: FS | 2024-11-22 07:00 | 2024-11-22 17:00
C-52-HG01-CMA06-1030 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 | Section Tie-in Welding | C-52-HG01-CMA06-1010 | C-52-HG01-CMA06-1010: FS | C-52-HG01-CMA06-1040 | C-52-HG01-CMA06-1040: SS 30 | 2024-10-19 | 2024-10-24
C-52-HG01-CMA06-1040 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 | NDT (Tie-in Joint) | C-52-HG01-CMA06-1030 | C-52-HG01-CMA06-1030: SS 30 | C-52-HG01-CMA06-1050 | C-52-HG01-CMA06-1050: SS 1 | 2024-10-19 | 2024-11-23 07:00
C-52-HG01-CMA06-1050 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CMA06-1040 | C-52-HG01-CMA06-1040: SS 1 | C-52-HG01-CMA06-1060 | C-52-HG01-CMA06-1060: FS | 2024-10-20 | 2024-10-25
C-52-HG01-CMA06-1060 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 | Holiday Testing | C-52-HG01-CMA06-1050 | C-52-HG01-CMA06-1050: FS | C-52-HG01-CMA06-1070 | C-52-HG01-CMA06-1070: FS | 2024-10-20 | 2024-11-23 07:00
C-52-HG01-CMA06-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 | Padding | C-52-HG01-CMA06-1060, C-52-HG01-CMA06-1020 | C-52-HG01-CMA06-1060: FS, C-52-HG01-CMA06-1020: FS | C-52-HG01-PL-ME-7400, C-52-HG01-PL-CA-5220 | C-52-HG01-PL-ME-7400: FS, C-52-HG01-PL-CA-5220: FF | 2024-11-23 07:00 | 2024-11-23 17:00
C-52-HG01-CMA07-0970 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 | Excavation (Manual-Trial Pit) | C-52-HG01-PL-CI-1000 | C-52-HG01-PL-CI-1000: FS | C-52-HG01-CMA07-0980 | C-52-HG01-CMA07-0980: FS | 2024-05-15 | 2024-07-15
C-52-HG01-CMA07-0980 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 | Sabkha Gatch Laying | C-52-HG01-CMA07-0970 | C-52-HG01-CMA07-0970: FS | C-52-HG01-CMA07-0990 | C-52-HG01-CMA07-0990: SS 1 | 2024-05-15 | 2024-07-15
C-52-HG01-CMA07-0990 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 | Sabka Gatch Compaction | C-52-HG01-CMA07-0980 | C-52-HG01-CMA07-0980: SS 1 | C-52-HG01-CMA07-1000 | C-52-HG01-CMA07-1000: FS | 2024-05-15 | 2024-07-15
C-52-HG01-CMA07-1000 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 | Trench Excavation | C-52-HG01-CMA07-0990 | C-52-HG01-CMA07-0990: FS | C-52-HG01-CMA07-1010 | C-52-HG01-CMA07-1010: FF | 2024-05-15 | 2024-07-15
C-52-HG01-CMA07-1010 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 | Bedding | C-52-HG01-CMA07-1000 | C-52-HG01-CMA07-1000: FF | C-52-HG01-CMA07-1020 | C-52-HG01-CMA07-1020: FS | 2024-05-15 | 2024-07-15
C-52-HG01-CMA07-1020 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 | Lowering | C-52-HG01-CMA07-1010 | C-52-HG01-CMA07-1010: FS | C-52-HG01-CMA07-1030 | C-52-HG01-CMA07-1030: SS | 2024-09-27 | 2024-10-01
C-52-HG01-CMA07-1030 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 | Section Tie-in Welding | C-52-HG01-CMA07-1020 | C-52-HG01-CMA07-1020: SS | C-52-HG01-CMA07-1040 | C-52-HG01-CMA07-1040: SS 1 | 2024-10-02 | 2024-10-10
C-52-HG01-CMA07-1040 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 | NDT (Tie-in Joint) | C-52-HG01-CMA07-1030 | C-52-HG01-CMA07-1030: SS 1 | C-52-HG01-CMA07-1050 | C-52-HG01-CMA07-1050: SS 1 | 2024-10-02 | 2024-10-10
C-52-HG01-CMA07-1050 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CMA07-1040 | C-52-HG01-CMA07-1040: SS 1 | C-52-HG01-CMA07-1060 | C-52-HG01-CMA07-1060: FS | 2024-10-03 | 2024-10-12
C-52-HG01-CMA07-1060 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 | Holiday Testing | C-52-HG01-CMA07-1050 | C-52-HG01-CMA07-1050: FS | C-52-HG01-CMA07-1070 | C-52-HG01-CMA07-1070: FS 40 | 2024-10-03 | 2024-10-12
C-52-HG01-CMA07-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 | Padding | C-52-HG01-CMA07-1060 | C-52-HG01-CMA07-1060: FS 40 | C-52-HG01-PL-ME-7400, C-52-HG01-PL-CA-5220 | C-52-HG01-PL-ME-7400: FS, C-52-HG01-PL-CA-5220: FF | 2024-11-28 07:00 | 2024-11-28 17:00
C-52-HG01-CMA02-0970 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 | Excavation (Manual-Trial Pit) | C-52-HG01-PL-CI-2400 | C-52-HG01-PL-CI-2400: FS 50 | C-52-HG01-CMA02-0980 | C-52-HG01-CMA02-0980: FS | 2024-11-15 07:00 | 2024-11-23 17:00
C-52-HG01-CMA02-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 | Sabkha Gatch Laying | C-52-HG01-CMA02-0970 | C-52-HG01-CMA02-0970: FS | C-52-HG01-CMA02-0990 | C-52-HG01-CMA02-0990: SS 1 | 2024-11-25 07:00 | 2024-11-29 17:00
C-52-HG01-CMA02-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 | Sabka Gatch Compaction | C-52-HG01-CMA02-0980 | C-52-HG01-CMA02-0980: SS 1 | C-52-HG01-CMA02-1000 | C-52-HG01-CMA02-1000: FS | 2024-11-26 07:00 | 2024-11-30 17:00
C-52-HG01-CMA02-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 | Trench Excavation | C-52-HG01-CMA02-0990 | C-52-HG01-CMA02-0990: FS | C-52-HG01-CMA02-1010 | C-52-HG01-CMA02-1010: FF | 2024-12-04 07:00 | 2024-12-05 17:00
C-52-HG01-CMA02-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 | Bedding | C-52-HG01-CMA02-1000 | C-52-HG01-CMA02-1000: FF | C-52-HG01-CMA02-1020 | C-52-HG01-CMA02-1020: FS | 2024-12-05 07:00 | 2024-12-05 17:00
C-52-HG01-CMA02-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 | Lowering | C-52-HG01-CMA02-1010 | C-52-HG01-CMA02-1010: FS | C-52-HG01-CMA02-1030 | C-52-HG01-CMA02-1030: SS | 2024-12-06 07:00 | 2024-12-06 17:00
C-52-HG01-CMA02-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 | Section Tie-in Welding | C-52-HG01-CMA02-1020 | C-52-HG01-CMA02-1020: SS | C-52-HG01-CMA02-1040 | C-52-HG01-CMA02-1040: SS 1 | 2024-12-06 07:00 | 2024-12-07 17:00
C-52-HG01-CMA02-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 | NDT (Tie-in Joint) | C-52-HG01-CMA02-1030 | C-52-HG01-CMA02-1030: SS 1 | C-52-HG01-CMA02-1050 | C-52-HG01-CMA02-1050: SS 1 | 2024-12-07 07:00 | 2024-12-09 17:00
C-52-HG01-CMA02-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CMA02-1040 | C-52-HG01-CMA02-1040: SS 1 | C-52-HG01-CMA02-1060 | C-52-HG01-CMA02-1060: FS | 2024-12-09 07:00 | 2024-12-10 17:00
C-52-HG01-CMA02-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 | Holiday Testing | C-52-HG01-CMA02-1050 | C-52-HG01-CMA02-1050: FS | C-52-HG01-CMA02-1070 | C-52-HG01-CMA02-1070: FS | 2024-12-11 07:00 | 2024-12-11 17:00
C-52-HG01-CMA02-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 | Padding | C-52-HG01-CMA02-1060 | C-52-HG01-CMA02-1060: FS | C-52-HG01-PL-ME-7400, C-52-HG01-PL-CA-5220 | C-52-HG01-PL-ME-7400: FS, C-52-HG01-PL-CA-5220: FF | 2024-12-12 07:00 | 2024-12-12 17:00
C-52-HG01-CMA03-0970 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 | Excavation (Manual-Trial Pit) | ML1002 | ML1002: FS | C-52-HG01-CMA03-0980 | C-52-HG01-CMA03-0980: FS | 2024-10-04 | 2024-10-09
C-52-HG01-CMA03-0980 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 | Sabkha Gatch Laying | C-52-HG01-CMA03-0970 | C-52-HG01-CMA03-0970: FS | C-52-HG01-CMA03-0990 | C-52-HG01-CMA03-0990: SS 1 | 2024-10-05 | 2024-10-10
C-52-HG01-CMA03-0990 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 | Sabka Gatch Compaction | C-52-HG01-CMA03-0980 | C-52-HG01-CMA03-0980: SS 1 | C-52-HG01-CMA03-1000 | C-52-HG01-CMA03-1000: FS | 2024-10-06 | 2024-10-11
C-52-HG01-CMA03-1000 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 | Trench Excavation | C-52-HG01-CMA03-0990 | C-52-HG01-CMA03-0990: FS | C-52-HG01-CMA03-1010 | C-52-HG01-CMA03-1010: FF | 2024-10-12 | 2024-10-18
C-52-HG01-CMA03-1010 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 | Bedding | C-52-HG01-CMA03-1000 | C-52-HG01-CMA03-1000: FF | C-52-HG01-CMA03-1020, C-52-HG01-CMA03-1030 | C-52-HG01-CMA03-1020: FS 30, C-52-HG01-CMA03-1030: FS | 2024-10-12 | 2024-10-18
C-52-HG01-CMA03-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 | Lowering | C-52-HG01-CMA03-1010 | C-52-HG01-CMA03-1010: FS 30 | C-52-HG01-CMA03-1070 | C-52-HG01-CMA03-1070: FS | 2024-11-22 07:00 | 2024-11-22 17:00
C-52-HG01-CMA03-1030 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 | Section Tie-in Welding | C-52-HG01-CMA03-1010 | C-52-HG01-CMA03-1010: FS | C-52-HG01-CMA03-1040 | C-52-HG01-CMA03-1040: SS 1 | 2024-10-18 | 2024-10-25
C-52-HG01-CMA03-1040 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 | NDT (Tie-in Joint) | C-52-HG01-CMA03-1030 | C-52-HG01-CMA03-1030: SS 1 | C-52-HG01-CMA03-1050 | C-52-HG01-CMA03-1050: SS 1 | 2024-10-18 | 2024-10-25
C-52-HG01-CMA03-1050 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CMA03-1040 | C-52-HG01-CMA03-1040: SS 1 | C-52-HG01-CMA03-1060 | C-52-HG01-CMA03-1060: FS | 2024-10-20 | 2024-10-25
C-52-HG01-CMA03-1060 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 | Holiday Testing | C-52-HG01-CMA03-1050 | C-52-HG01-CMA03-1050: FS | C-52-HG01-CMA03-1070 | C-52-HG01-CMA03-1070: FS | 2024-10-20 | 2024-10-25
C-52-HG01-CMA03-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 | Padding | C-52-HG01-CMA03-1060, C-52-HG01-CMA03-1020 | C-52-HG01-CMA03-1060: FS, C-52-HG01-CMA03-1020: FS | C-52-HG01-PL-ME-7400, C-52-HG01-PL-CA-5220 | C-52-HG01-PL-ME-7400: FS, C-52-HG01-PL-CA-5220: FF | 2024-11-23 07:00 | 2024-11-23 17:00
C-52-HG01-CMA04-0970 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 | Excavation (Manual-Trial Pit) | C-52-HG01-PL-CI-2230 | C-52-HG01-PL-CI-2230: FS | C-52-HG01-CMA04-0980, C-52-HG01-CMA06-0970 | C-52-HG01-CMA04-0980: FS, C-52-HG01-CMA06-0970: FS | 2024-07-19 | 2024-08-19
C-52-HG01-CMA04-0980 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 | Sabkha Gatch Laying | C-52-HG01-CMA04-0970 | C-52-HG01-CMA04-0970: FS | C-52-HG01-CMA04-0990 | C-52-HG01-CMA04-0990: SS 1 | 2024-07-19 | 2024-08-19
C-52-HG01-CMA04-0990 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 | Sabka Gatch Compaction | C-52-HG01-CMA04-0980 | C-52-HG01-CMA04-0980: SS 1 | C-52-HG01-CMA04-1000 | C-52-HG01-CMA04-1000: FS | 2024-07-19 | 2024-08-19
C-52-HG01-CMA04-1000 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 | Trench Excavation | C-52-HG01-CMA04-0990 | C-52-HG01-CMA04-0990: FS | C-52-HG01-CMA04-1010 | C-52-HG01-CMA04-1010: FF | 2024-07-19 | 2024-08-19
C-52-HG01-CMA04-1010 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 | Bedding | C-52-HG01-CMA04-1000 | C-52-HG01-CMA04-1000: FF | C-52-HG01-CMA04-1020, C-52-HG01-CMA04-1030 | C-52-HG01-CMA04-1020: FS 75, C-52-HG01-CMA04-1030: FS | 2024-07-19 | 2024-08-19
C-52-HG01-CMA04-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 | Lowering | C-52-HG01-CMA04-1010 | C-52-HG01-CMA04-1010: FS 75 | C-52-HG01-CMA04-1070 | C-52-HG01-CMA04-1070: FS | 2024-11-15 07:00 | 2024-11-15 17:00
C-52-HG01-CMA04-1030 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 | Section Tie-in Welding | C-52-HG01-CMA04-1010 | C-52-HG01-CMA04-1010: FS | C-52-HG01-CMA04-1040 | C-52-HG01-CMA04-1040: SS 1 | 2024-10-18 | 2024-10-25
C-52-HG01-CMA04-1040 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 | NDT (Tie-in Joint) | C-52-HG01-CMA04-1030 | C-52-HG01-CMA04-1030: SS 1 | C-52-HG01-CMA04-1050 | C-52-HG01-CMA04-1050: SS 1 | 2024-10-18 | 2024-10-25
C-52-HG01-CMA04-1050 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CMA04-1040 | C-52-HG01-CMA04-1040: SS 1 | C-52-HG01-CMA04-1060 | C-52-HG01-CMA04-1060: FS | 2024-10-20 | 2024-10-25
C-52-HG01-CMA04-1060 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 | Holiday Testing | C-52-HG01-CMA04-1050 | C-52-HG01-CMA04-1050: FS | C-52-HG01-CMA04-1070 | C-52-HG01-CMA04-1070: FS | 2024-10-20 | 2024-10-25
C-52-HG01-CMA04-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 | Padding | C-52-HG01-CMA04-1060, C-52-HG01-CMA04-1020 | C-52-HG01-CMA04-1060: FS, C-52-HG01-CMA04-1020: FS | C-52-HG01-PL-ME-7400, C-52-HG01-PL-CA-5220 | C-52-HG01-PL-ME-7400: FS, C-52-HG01-PL-CA-5220: FF | 2024-11-16 07:00 | 2024-11-16 17:00
C-52-HG01-CME01-1000 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 | Trench Excavation | C-52-HG01-PL-ME-4800 | C-52-HG01-PL-ME-4800: SS 2 | C-52-HG01-CME01-1010, C-52-HG01-CME02-1000 | C-52-HG01-CME01-1010: FS, C-52-HG01-CME02-1000: FS 30 | 2024-09-27 | 2024-10-06
C-52-HG01-CME01-1010 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 | Bedding | C-52-HG01-CME01-1000 | C-52-HG01-CME01-1000: FS | C-52-HG01-CME01-1020 | C-52-HG01-CME01-1020: FS | 2024-09-27 | 2024-10-06
C-52-HG01-CME01-1020 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 | Lowering | C-52-HG01-CME01-1010 | C-52-HG01-CME01-1010: FS | C-52-HG01-CME01-1030 | C-52-HG01-CME01-1030: FS | 2024-10-01 | 2024-10-08
C-52-HG01-CME01-1030 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 | Section Tie-in Welding | C-52-HG01-CME01-1020 | C-52-HG01-CME01-1020: FS | C-52-HG01-CME01-1040 | C-52-HG01-CME01-1040: FS | 2024-10-10 | 2024-10-17
C-52-HG01-CME01-1040 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 | NDT (Tie-in Joint) | C-52-HG01-CME01-1030 | C-52-HG01-CME01-1030: FS | C-52-HG01-CME01-1050 | C-52-HG01-CME01-1050: FS | 2024-10-10 | 2024-10-17
C-52-HG01-CME01-1050 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CME01-1040 | C-52-HG01-CME01-1040: FS | C-52-HG01-CME01-1060 | C-52-HG01-CME01-1060: FS | 2024-10-12 | 2024-10-20
C-52-HG01-CME01-1060 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 | Holiday Testing | C-52-HG01-CME01-1050 | C-52-HG01-CME01-1050: FS | C-52-HG01-CME01-1070 | C-52-HG01-CME01-1070: FS 30 | 2024-10-12 | 2024-10-20
C-52-HG01-CME01-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 | Padding & Back Filling | C-52-HG01-CME01-1060 | C-52-HG01-CME01-1060: FS 30 | C-52-HG01-PL-ME-7400, C-52-HG01-PL-CA-5220 | C-52-HG01-PL-ME-7400: FS, C-52-HG01-PL-CA-5220: FF | 2024-11-25 07:00 | 2024-11-26 17:00
C-52-HG01-CME02-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 | Trench Excavation | C-52-HG01-CME01-1000 | C-52-HG01-CME01-1000: FS 30 | C-52-HG01-CME02-1010, C-52-HG01-CME03-1000 | C-52-HG01-CME02-1010: FS, C-52-HG01-CME03-1000: FS 1 | 2024-11-11 07:00 | 2024-11-12 17:00
C-52-HG01-CME02-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 | Bedding | C-52-HG01-CME02-1000 | C-52-HG01-CME02-1000: FS | C-52-HG01-CME02-1020 | C-52-HG01-CME02-1020: FS | 2024-11-13 07:00 | 2024-11-14 17:00
C-52-HG01-CME02-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 | Lowering | C-52-HG01-CME02-1010 | C-52-HG01-CME02-1010: FS | C-52-HG01-CME02-1030 | C-52-HG01-CME02-1030: FS | 2024-11-15 07:00 | 2024-11-16 17:00
C-52-HG01-CME02-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 | Section Tie-in Welding | C-52-HG01-CME02-1020 | C-52-HG01-CME02-1020: FS | C-52-HG01-CME02-1040 | C-52-HG01-CME02-1040: FS | 2024-11-18 07:00 | 2024-11-20 17:00
C-52-HG01-CME02-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 | NDT (Tie-in Joint) | C-52-HG01-CME02-1030 | C-52-HG01-CME02-1030: FS | C-52-HG01-CME02-1050 | C-52-HG01-CME02-1050: FS | 2024-11-21 07:00 | 2024-11-23 17:00
C-52-HG01-CME02-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CME02-1040 | C-52-HG01-CME02-1040: FS | C-52-HG01-CME02-1060 | C-52-HG01-CME02-1060: FS | 2024-11-25 07:00 | 2024-11-27 17:00
C-52-HG01-CME02-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 | Holiday Testing | C-52-HG01-CME02-1050 | C-52-HG01-CME02-1050: FS | C-52-HG01-CME02-1070 | C-52-HG01-CME02-1070: FS | 2024-11-28 07:00 | 2024-11-29 17:00
C-52-HG01-CME02-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 | Padding & Back Filling | C-52-HG01-CME02-1060 | C-52-HG01-CME02-1060: FS | C-52-HG01-PL-ME-7400, C-52-HG01-PL-CA-5220 | C-52-HG01-PL-ME-7400: FS, C-52-HG01-PL-CA-5220: FF | 2024-11-30 07:00 | 2024-12-04 17:00
C-52-HG01-CME03-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 | Trench Excavation | C-52-HG01-CME02-1000 | C-52-HG01-CME02-1000: FS 1 | C-52-HG01-CME03-1010, C-52-0102-CME01-1000 | C-52-HG01-CME03-1010: FS, C-52-0102-CME01-1000: FS 1 | 2024-11-14 07:00 | 2024-11-15 17:00
C-52-HG01-CME03-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 | Bedding | C-52-HG01-CME03-1000 | C-52-HG01-CME03-1000: FS | C-52-HG01-CME03-1020 | C-52-HG01-CME03-1020: FS | 2024-11-16 07:00 | 2024-11-18 17:00
C-52-HG01-CME03-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 | Lowering | C-52-HG01-CME03-1010 | C-52-HG01-CME03-1010: FS | C-52-HG01-CME03-1030 | C-52-HG01-CME03-1030: FS | 2024-11-19 07:00 | 2024-11-20 17:00
C-52-HG01-CME03-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 | Section Tie-in Welding | C-52-HG01-CME03-1020 | C-52-HG01-CME03-1020: FS | C-52-HG01-CME03-1040 | C-52-HG01-CME03-1040: FS | 2024-11-21 07:00 | 2024-11-23 17:00
C-52-HG01-CME03-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 | NDT (Tie-in Joint) | C-52-HG01-CME03-1030 | C-52-HG01-CME03-1030: FS | C-52-HG01-CME03-1050 | C-52-HG01-CME03-1050: FS | 2024-11-25 07:00 | 2024-11-27 17:00
C-52-HG01-CME03-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CME03-1040 | C-52-HG01-CME03-1040: FS | C-52-HG01-CME03-1060 | C-52-HG01-CME03-1060: FS | 2024-11-28 07:00 | 2024-11-30 17:00
C-52-HG01-CME03-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 | Holiday Testing | C-52-HG01-CME03-1050 | C-52-HG01-CME03-1050: FS | C-52-HG01-CME03-1070 | C-52-HG01-CME03-1070: FS | 2024-12-04 07:00 | 2024-12-05 17:00
C-52-HG01-CME03-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 | Padding & Back Filling | C-52-HG01-CME03-1060 | C-52-HG01-CME03-1060: FS | C-52-HG01-PL-ME-7400, C-52-HG01-PL-CA-5220 | C-52-HG01-PL-ME-7400: FS, C-52-HG01-PL-CA-5220: FF | 2024-12-06 07:00 | 2024-12-07 17:00
C-52-HG01-CNM04-1000 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1050 | C-PER-1050: FS | C-52-HG01-CNM04-1020, C-52-HG01-CNM04-1010 | C-52-HG01-CNM04-1020: FS, C-52-HG01-CNM04-1010: SS 21 | 2024-04-01 | 2024-05-28
C-52-HG01-CNM04-1020 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-HG01-CNM04-1000 | C-52-HG01-CNM04-1000: FS | C-52-HG01-CNM04-1030 | C-52-HG01-CNM04-1030: FS | 2024-05-01 | 2024-05-30
C-52-HG01-CNM04-1010 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 | Driving & Receiving Pit Excavation | C-52-HG01-CNM04-1000 | C-52-HG01-CNM04-1000: SS 21 | C-52-HG01-CNM04-1030 | C-52-HG01-CNM04-1030: SS 7 | 2024-05-29 07:00 | 2024-07-15
C-52-HG01-CNM04-1030 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-HG01-CNM04-1010, C-52-HG01-CNM04-1020 | C-52-HG01-CNM04-1010: SS 7, C-52-HG01-CNM04-1020: FS | C-52-HG01-CNM04-1040 | C-52-HG01-CNM04-1040: FS | 2024-05-16 | 2024-06-24
C-52-HG01-CNM04-1040 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 | Floor Blinding & French Drain in Driving Pit | C-52-HG01-CNM04-1030 | C-52-HG01-CNM04-1030: FS | C-52-HG01-CNM04-1050 | C-52-HG01-CNM04-1050: FS | 2024-06-25 07:00 | 2024-07-26
C-52-HG01-CNM04-1050 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-HG01-CNM04-1040 | C-52-HG01-CNM04-1040: FS | C-52-HG01-CNM04-1060 | C-52-HG01-CNM04-1060: SS 7 | 2024-07-16 | 2024-08-24
C-52-HG01-CNM04-1060 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 | Construction of Exit Wall with Ring | C-52-HG01-CNM04-1050 | C-52-HG01-CNM04-1050: SS 7 | C-52-HG01-CNM04-1200 | C-52-HG01-CNM04-1200: FS | 2024-07-16 | 2024-08-25
C-52-HG01-CNM04-1200 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.1.2 | Jacking of MTBM & RC Sleeves | C-52-HG01-CNM04-1060 | C-52-HG01-CNM04-1060: FS | C-52-HG01-CNM04-1210 | C-52-HG01-CNM04-1210: FS | 2024-08-25 | 2024-09-04
C-52-HG01-CNM04-1210 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.1.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-HG01-CNM04-1200 | C-52-HG01-CNM04-1200: FS | C-52-HG01-CNM04-1220, C-52-HG01-CNM04-1400 | C-52-HG01-CNM04-1220: FS, C-52-HG01-CNM04-1400: FS | 2024-09-04 | 2024-09-13
C-52-HG01-CNM04-1400 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.2.1.3 | Lowering & Welding of Carrier Pipe | C-52-HG01-CNM04-1210 | C-52-HG01-CNM04-1210: FS | C-52-HG01-CNM04-1410, C-52-HG01-CNM03-1400 | C-52-HG01-CNM04-1410: SS 1, C-52-HG01-CNM03-1400: FS | 2024-10-23 | 2024-11-06 17:00
C-52-HG01-CNM04-1410 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.2.1.3 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-HG01-CNM04-1400 | C-52-HG01-CNM04-1400: SS 1 | C-52-HG01-CNM04-1600 | C-52-HG01-CNM04-1600: FS 8 | 2024-10-23 | 2024-11-11 17:00
C-52-HG01-CNM04-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.1.4 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-HG01-CNM04-1410 | C-52-HG01-CNM04-1410: FS 8 | C-52-HG01-CNM04-1800 | C-52-HG01-CNM04-1800: FS | 2024-11-21 07:00 | 2024-12-06 17:00
C-52-HG01-CNM04-1220 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.1.2 | Inner Grout b/w Main & RC Pipe | C-52-HG01-CNM04-1210 | C-52-HG01-CNM04-1210: FS | C-52-HG01-CNM04-1800, C-52-HG01-PL-CA-5220 | C-52-HG01-CNM04-1800: FS, C-52-HG01-PL-CA-5220: FF | 2024-09-04 | 2024-09-13
C-52-HG01-CNM04-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.1.5 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-HG01-CNM04-1600, C-52-HG01-CNM04-1220 | C-52-HG01-CNM04-1600: FS, C-52-HG01-CNM04-1220: FS | C-52-HG01-PL-ME-7400, ML1679-E13, ML1080 | C-52-HG01-PL-ME-7400: FF 14, ML1679-E13: FS, ML1080: FS | 2024-12-07 07:00 | 2024-12-23 17:00
C-52-HG01-CNM03-1000 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1040 | C-PER-1040: FS | C-52-HG01-CNM03-1020, C-52-HG01-CNM03-1010 | C-52-HG01-CNM03-1020: FS, C-52-HG01-CNM03-1010: SS 21 | 2024-05-01 | 2024-06-13
C-52-HG01-CNM03-1020 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-HG01-CNM03-1000 | C-52-HG01-CNM03-1000: FS | C-52-HG01-CNM03-1030 | C-52-HG01-CNM03-1030: FS | 2024-05-05 | 2024-06-13
C-52-HG01-CNM03-1010 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 | Driving & Receiving Pit Excavation | C-52-HG01-CNM03-1000 | C-52-HG01-CNM03-1000: SS 21 | C-52-HG01-CNM03-1030 | C-52-HG01-CNM03-1030: SS 7 | 2024-05-28 | 2024-09-09
C-52-HG01-CNM03-1030 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-HG01-CNM03-1010, C-52-HG01-CNM03-1020 | C-52-HG01-CNM03-1010: SS 7, C-52-HG01-CNM03-1020: FS | C-52-HG01-CNM03-1040 | C-52-HG01-CNM03-1040: FS | 2024-06-24 | 2024-08-14
C-52-HG01-CNM03-1040 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 | Floor Blinding & French Drain in Driving Pit | C-52-HG01-CNM03-1030 | C-52-HG01-CNM03-1030: FS | C-52-HG01-CNM03-1050 | C-52-HG01-CNM03-1050: FS | 2024-08-16 | 2024-09-14
C-52-HG01-CNM03-1050 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-HG01-CNM03-1040 | C-52-HG01-CNM03-1040: FS | C-52-HG01-CNM03-1060 | C-52-HG01-CNM03-1060: SS 7 | 2024-08-28 | 2024-09-14
C-52-HG01-CNM03-1060 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 | Construction of Exit Wall with Ring | C-52-HG01-CNM03-1050 | C-52-HG01-CNM03-1050: SS 7 | C-52-HG01-CNM03-1200 | C-52-HG01-CNM03-1200: FS | 2024-09-16 | 2024-09-19
C-52-HG01-CNM03-1200 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.2.2 | Jacking of MTBM & RC Sleeves | C-52-HG01-CNM03-1060 | C-52-HG01-CNM03-1060: FS | C-52-HG01-CNM03-1210 | C-52-HG01-CNM03-1210: FS | 2024-09-19 | 2024-09-26
C-52-HG01-CNM03-1210 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.2.2.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-HG01-CNM03-1200 | C-52-HG01-CNM03-1200: FS | C-52-HG01-CNM03-1400 | C-52-HG01-CNM03-1400: FS | 2024-10-01 | 2024-10-05
C-52-HG01-CNM03-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.2.3 | Lowering & Welding of Carrier Pipe | C-52-HG01-CNM03-1210, C-52-HG01-CNM04-1400 | C-52-HG01-CNM03-1210: FS, C-52-HG01-CNM04-1400: FS | C-52-HG01-CNM03-1410 | C-52-HG01-CNM03-1410: SS 1 | 2024-11-07 07:00 | 2024-11-25 17:00
C-52-HG01-CNM03-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.2.3 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-HG01-CNM03-1400 | C-52-HG01-CNM03-1400: SS 1 | C-52-HG01-CNM03-1600 | C-52-HG01-CNM03-1600: FS 8 | 2024-11-08 07:00 | 2024-11-26 17:00
C-52-HG01-CNM03-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.2.4 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-HG01-CNM03-1410 | C-52-HG01-CNM03-1410: FS 8 | C-52-HG01-CNM03-1220 | C-52-HG01-CNM03-1220: FS | 2024-12-09 07:00 | 2024-12-17 17:00
C-52-HG01-CNM03-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.2.2 | Inner Grout b/w Main & RC Pipe | C-52-HG01-CNM03-1600 | C-52-HG01-CNM03-1600: FS | C-52-HG01-CNM03-1800, C-52-HG01-PL-CA-5220 | C-52-HG01-CNM03-1800: FS, C-52-HG01-PL-CA-5220: FF | 2024-12-18 07:00 | 2024-12-23 17:00
C-52-HG01-CNM03-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.2.5 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-HG01-CNM03-1220 | C-52-HG01-CNM03-1220: FS | C-52-HG01-PL-ME-7400, PRECOM-52-HG01-1000, ML1679-E13, ML1080 | C-52-HG01-PL-ME-7400: FF 14, PRECOM-52-HG01-1000: FS, ML1679-E13: FS, ML1080: FS | 2024-12-24 07:00 | 2025-01-04 17:00
C-52-HG01-CNM02-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1030 | C-PER-1030: FS | C-52-HG01-CNM02-1020, C-52-HG01-CNM02-1010 | C-52-HG01-CNM02-1020: FS 0, C-52-HG01-CNM02-1010: FS | 2024-12-21 07:00 | 2024-12-28 17:00
C-52-HG01-CNM02-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-HG01-CNM02-1000 | C-52-HG01-CNM02-1000: FS 0 | C-52-HG01-CNM02-1030 | C-52-HG01-CNM02-1030: SS | 2024-12-30 09:32 | 2025-01-04 09:32
C-52-HG01-CNM02-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 | Driving & Receiving Pit Excavation | C-52-HG01-CNM02-1000 | C-52-HG01-CNM02-1000: FS | C-52-HG01-CNM02-1030 | C-52-HG01-CNM02-1030: FF | 2024-12-30 07:00 | 2025-01-07 17:00
C-52-HG01-CNM02-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-HG01-CNM02-1010, C-52-HG01-CNM02-1020 | C-52-HG01-CNM02-1010: FF, C-52-HG01-CNM02-1020: SS | C-52-HG01-CNM02-1040 | C-52-HG01-CNM02-1040: FS | 2024-12-30 09:32 | 2025-01-08 09:32
C-52-HG01-CNM02-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 | Floor Blinding & French Drain in Driving Pit | C-52-HG01-CNM02-1030 | C-52-HG01-CNM02-1030: FS | C-52-HG01-CNM02-1050 | C-52-HG01-CNM02-1050: FS | 2025-01-08 09:32 | 2025-01-15 09:32
C-52-HG01-CNM02-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-HG01-CNM02-1040 | C-52-HG01-CNM02-1040: FS | C-52-HG01-CNM02-1060 | C-52-HG01-CNM02-1060: SS 7 | 2025-01-15 09:32 | 2025-01-22 09:32
C-52-HG01-CNM02-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 | Construction of Exit Wall with Ring | C-52-HG01-CNM02-1050 | C-52-HG01-CNM02-1050: SS 7 | C-52-HG01-CNM02-1200 | C-52-HG01-CNM02-1200: FS | 2025-01-23 09:32 | 2025-01-30 09:32
C-52-HG01-CNM02-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.3.2 | Jacking of MTBM & RC Sleeves | C-52-HG01-CNM02-1060, C-52-0102-CNM07-1200 | C-52-HG01-CNM02-1060: FS, C-52-0102-CNM07-1200: FS | C-52-HG01-CNM02-1210 | C-52-HG01-CNM02-1210: FS | 2025-01-30 09:32 | 2025-02-11 09:32
C-52-HG01-CNM02-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.3.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-HG01-CNM02-1200 | C-52-HG01-CNM02-1200: FS | C-52-HG01-CNM02-1400 | C-52-HG01-CNM02-1400: FS | 2025-02-11 09:32 | 2025-02-15 09:32
C-52-HG01-CNM02-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.3.3 | Lowering & Welding of Carrier Pipe | C-52-HG01-CNM02-1210 | C-52-HG01-CNM02-1210: FS | C-52-HG01-CNM02-1410 | C-52-HG01-CNM02-1410: SS 1 | 2025-02-15 09:32 | 2025-03-04 07:32
C-52-HG01-CNM02-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.3.3 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-HG01-CNM02-1400 | C-52-HG01-CNM02-1400: SS 1 | C-52-HG01-CNM02-1600 | C-52-HG01-CNM02-1600: FS | 2025-02-17 09:32 | 2025-03-05 11:32
C-52-HG01-CNM02-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.3.4 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-HG01-CNM02-1410 | C-52-HG01-CNM02-1410: FS | C-52-HG01-CNM02-1220 | C-52-HG01-CNM02-1220: FS | 2025-03-05 11:32 | 2025-03-19 09:32
C-52-HG01-CNM02-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.3.2 | Inner Grout b/w Main & RC Pipe | C-52-HG01-CNM02-1600 | C-52-HG01-CNM02-1600: FS | C-52-HG01-CNM02-1800, C-52-HG01-PL-CA-5240, C-52-HG01-PL-CA-5220 | C-52-HG01-CNM02-1800: FS, C-52-HG01-PL-CA-5240: FF 2, C-52-HG01-PL-CA-5220: FF | 2025-03-19 09:32 | 2025-03-27 07:32
C-52-HG01-CNM02-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.3.5 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-HG01-CNM02-1220 | C-52-HG01-CNM02-1220: FS | C-52-HG01-PL-ME-7400, PRECOM-52-HG01-1000, ML1679-E13 | C-52-HG01-PL-ME-7400: FF 14, PRECOM-52-HG01-1000: FS, ML1679-E13: FS | 2025-03-27 07:32 | 2025-04-16 15:32
C-52-HG01-CNM01-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1020 | C-PER-1020: FS | C-52-HG01-CNM01-1020, C-52-HG01-CNM01-1010 | C-52-HG01-CNM01-1020: FS, C-52-HG01-CNM01-1010: FS | 2024-11-22 07:00 | 2024-12-23 17:00
C-52-HG01-CNM01-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-HG01-CNM01-1000 | C-52-HG01-CNM01-1000: FS | C-52-HG01-CNM01-1030 | C-52-HG01-CNM01-1030: FS | 2024-12-24 07:00 | 2024-12-27 17:00
C-52-HG01-CNM01-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 | Driving & Receiving Pit Excavation | C-52-HG01-CNM01-1000 | C-52-HG01-CNM01-1000: FS | C-52-HG01-CNM01-1030 | C-52-HG01-CNM01-1030: FF | 2024-12-24 07:00 | 2025-01-14 17:00
C-52-HG01-CNM01-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-HG01-CNM01-1010, C-52-HG01-CNM01-1020 | C-52-HG01-CNM01-1010: FF, C-52-HG01-CNM01-1020: FS | C-52-HG01-CNM01-1040 | C-52-HG01-CNM01-1040: FS | 2024-12-28 07:00 | 2025-01-14 17:00
C-52-HG01-CNM01-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 | Floor Blinding & French Drain in Driving Pit | C-52-HG01-CNM01-1030 | C-52-HG01-CNM01-1030: FS | C-52-HG01-CNM01-1050 | C-52-HG01-CNM01-1050: FS | 2025-01-15 07:00 | 2025-01-21 17:00
C-52-HG01-CNM01-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-HG01-CNM01-1040 | C-52-HG01-CNM01-1040: FS | C-52-HG01-CNM01-1060 | C-52-HG01-CNM01-1060: SS 7 | 2025-01-22 07:00 | 2025-01-28 17:00
C-52-HG01-CNM01-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 | Construction of Exit Wall with Ring | C-52-HG01-CNM01-1050 | C-52-HG01-CNM01-1050: SS 7 | C-52-HG01-CNM01-1200 | C-52-HG01-CNM01-1200: FS | 2025-01-30 07:00 | 2025-02-05 17:00
C-52-HG01-CNM01-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.4.2 | Jacking of MTBM & RC Sleeves | C-52-HG01-CNM01-1060 | C-52-HG01-CNM01-1060: FS | C-52-HG01-CNM01-1210 | C-52-HG01-CNM01-1210: FS | 2025-02-06 07:00 | 2025-02-19 17:00
C-52-HG01-CNM01-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.4.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-HG01-CNM01-1200 | C-52-HG01-CNM01-1200: FS | C-52-HG01-CNM01-1400 | C-52-HG01-CNM01-1400: FS | 2025-02-20 07:00 | 2025-02-24 17:00
C-52-HG01-CNM01-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.4.3 | Lowering & Welding of Carrier Pipe | C-52-HG01-CNM01-1210 | C-52-HG01-CNM01-1210: FS | C-52-HG01-CNM01-1410 | C-52-HG01-CNM01-1410: SS 1 | 2025-02-25 07:00 | 2025-03-22 09:00
C-52-HG01-CNM01-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.4.3 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-HG01-CNM01-1400 | C-52-HG01-CNM01-1400: SS 1 | C-52-HG01-CNM01-1600 | C-52-HG01-CNM01-1600: FS | 2025-02-26 07:00 | 2025-03-23 09:00
C-52-HG01-CNM01-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.4.4 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-HG01-CNM01-1410 | C-52-HG01-CNM01-1410: FS | C-52-HG01-CNM01-1220 | C-52-HG01-CNM01-1220: FS | 2025-03-23 09:00 | 2025-04-11 13:00
C-52-HG01-CNM01-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.4.2 | Inner Grout b/w Main & RC Pipe | C-52-HG01-CNM01-1600 | C-52-HG01-CNM01-1600: FS | C-52-HG01-CNM01-1800, C-52-HG01-PL-CA-5220 | C-52-HG01-CNM01-1800: FS, C-52-HG01-PL-CA-5220: FF | 2025-04-11 13:00 | 2025-04-17 13:00
C-52-HG01-CNM01-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.2.4.5 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-HG01-CNM01-1220 | C-52-HG01-CNM01-1220: FS | PRECOM-52-HG01-1000, ML1679-E13, C-52-HG01-PL-ME-7400 | PRECOM-52-HG01-1000: FS, ML1679-E13: FS, C-52-HG01-PL-ME-7400: FF 7 | 2025-04-17 13:00 | 2025-04-29 13:00
C-52-0304-CMA04-0970 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 | Excavation (Manual-Trial Pit) | C-52-0304-PL-CI-2200 | C-52-0304-PL-CI-2200: SS 21 | C-52-0304-CMA04-0980, C-52-0304-CMA05-0970 | C-52-0304-CMA04-0980: FS, C-52-0304-CMA05-0970: FS | 2024-10-30 07:30 | 2024-11-05 07:30
C-52-0304-CMA04-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 | Sabkha Gatch Laying | C-52-0304-CMA04-0970 | C-52-0304-CMA04-0970: FS | C-52-0304-CMA04-0990 | C-52-0304-CMA04-0990: SS 1 | 2024-11-05 07:30 | 2024-11-11 07:30
C-52-0304-CMA04-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 | Sabka Gatch Compaction | C-52-0304-CMA04-0980 | C-52-0304-CMA04-0980: SS 1 | C-52-0304-CMA04-1000 | C-52-0304-CMA04-1000: FS | 2024-11-06 07:30 | 2024-11-12 07:30
C-52-0304-CMA04-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 | Trench Excavation | C-52-0304-CMA04-0990 | C-52-0304-CMA04-0990: FS | C-52-0304-CMA04-1010 | C-52-0304-CMA04-1010: FF | 2024-11-12 07:30 | 2024-11-14 07:30
C-52-0304-CMA04-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 | Bedding | C-52-0304-CMA04-1000 | C-52-0304-CMA04-1000: FF | C-52-0304-CMA04-1020 | C-52-0304-CMA04-1020: FS | 2024-11-13 07:30 | 2024-11-14 07:30
C-52-0304-CMA04-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 | Lowering | C-52-0304-CMA04-1010, C-52-0304-PL-ME-2800 | C-52-0304-CMA04-1010: FS, C-52-0304-PL-ME-2800: FS 7 | C-52-0304-CMA04-1030, C-52-0304-CMA05-1020 | C-52-0304-CMA04-1030: SS, C-52-0304-CMA05-1020: FS | 2024-12-10 07:30 | 2024-12-11 07:30
C-52-0304-CMA04-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 | Section Tie-in Welding | C-52-0304-CMA04-1020 | C-52-0304-CMA04-1020: SS | C-52-0304-CMA04-1040, C-52-0304-PL-ME-4810 | C-52-0304-CMA04-1040: SS 1, C-52-0304-PL-ME-4810: FF 1 | 2024-12-10 07:30 | 2024-12-12 07:30
C-52-0304-CMA04-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 | NDT (Tie-in Joint) | C-52-0304-CMA04-1030 | C-52-0304-CMA04-1030: SS 1 | C-52-0304-CMA04-1050 | C-52-0304-CMA04-1050: SS 1 | 2024-12-11 07:30 | 2024-12-13 07:30
C-52-0304-CMA04-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA04-1040 | C-52-0304-CMA04-1040: SS 1 | C-52-0304-CMA04-1060 | C-52-0304-CMA04-1060: FS | 2024-12-12 07:30 | 2024-12-14 07:30
C-52-0304-CMA04-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 | Holiday Testing | C-52-0304-CMA04-1050 | C-52-0304-CMA04-1050: FS | C-52-0304-CMA04-1070, C-52-0304-PL-CA-5220 | C-52-0304-CMA04-1070: FS, C-52-0304-PL-CA-5220: SS | 2024-12-14 07:30 | 2024-12-16 07:30
C-52-0304-CMA04-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 | Padding | C-52-0304-CMA04-1060 | C-52-0304-CMA04-1060: FS | C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2024-12-16 07:30 | 2024-12-17 07:30
C-52-0304-CMA05-0970 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 | Excavation (Manual-Trial Pit) | C-52-0304-CMA04-0970 | C-52-0304-CMA04-0970: FS | C-52-0304-CMA05-0980, C-52-0304-CMA01-0980 | C-52-0304-CMA05-0980: FS, C-52-0304-CMA01-0980: FS | 2024-11-05 07:30 | 2024-11-11 07:30
C-52-0304-CMA05-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 | Sabkha Gatch Laying | C-52-0304-CMA05-0970 | C-52-0304-CMA05-0970: FS | C-52-0304-CMA05-0990 | C-52-0304-CMA05-0990: SS 1 | 2024-11-11 07:30 | 2024-11-16 07:30
C-52-0304-CMA05-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 | Sabka Gatch Compaction | C-52-0304-CMA05-0980 | C-52-0304-CMA05-0980: SS 1 | C-52-0304-CMA05-1000 | C-52-0304-CMA05-1000: FS | 2024-11-12 07:30 | 2024-11-18 07:30
C-52-0304-CMA05-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 | Trench Excavation | C-52-0304-CMA05-0990 | C-52-0304-CMA05-0990: FS | C-52-0304-CMA05-1010 | C-52-0304-CMA05-1010: FF | 2024-11-18 07:30 | 2024-11-20 07:30
C-52-0304-CMA05-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 | Bedding | C-52-0304-CMA05-1000 | C-52-0304-CMA05-1000: FF | C-52-0304-CMA05-1020 | C-52-0304-CMA05-1020: FS | 2024-11-19 07:30 | 2024-11-20 07:30
C-52-0304-CMA05-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 | Lowering | C-52-0304-CMA05-1010, C-52-0304-CMA04-1020 | C-52-0304-CMA05-1010: FS, C-52-0304-CMA04-1020: FS | C-52-0304-CMA05-1030, C-52-0304-CMA01-1020 | C-52-0304-CMA05-1030: SS, C-52-0304-CMA01-1020: FS | 2024-12-11 07:30 | 2024-12-12 07:30
C-52-0304-CMA05-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 | Section Tie-in Welding | C-52-0304-CMA05-1020 | C-52-0304-CMA05-1020: SS | C-52-0304-CMA05-1040, C-52-0304-PL-ME-4810 | C-52-0304-CMA05-1040: SS 1, C-52-0304-PL-ME-4810: FF 1 | 2024-12-11 07:30 | 2024-12-13 07:30
C-52-0304-CMA05-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 | NDT (Tie-in Joint) | C-52-0304-CMA05-1030 | C-52-0304-CMA05-1030: SS 1 | C-52-0304-CMA05-1050 | C-52-0304-CMA05-1050: SS 1 | 2024-12-12 07:30 | 2024-12-14 07:30
C-52-0304-CMA05-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA05-1040 | C-52-0304-CMA05-1040: SS 1 | C-52-0304-CMA05-1060 | C-52-0304-CMA05-1060: FS | 2024-12-13 07:30 | 2024-12-16 07:30
C-52-0304-CMA05-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 | Holiday Testing | C-52-0304-CMA05-1050 | C-52-0304-CMA05-1050: FS | C-52-0304-CMA05-1070 | C-52-0304-CMA05-1070: FS | 2024-12-16 07:30 | 2024-12-17 07:30
C-52-0304-CMA05-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 | Padding | C-52-0304-CMA05-1060 | C-52-0304-CMA05-1060: FS | C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2024-12-17 07:30 | 2024-12-18 07:30
C-52-0304-CMA01-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 | Sabkha Gatch Laying | C-52-0304-CMA05-0970 | C-52-0304-CMA05-0970: FS | C-52-0304-CMA01-0990, C-52-0304-CMA07-0970 | C-52-0304-CMA01-0990: SS 1, C-52-0304-CMA07-0970: FS | 2024-11-11 07:30 | 2024-11-16 07:30
C-52-0304-CMA01-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 | Sabka Gatch Compaction | C-52-0304-CMA01-0980 | C-52-0304-CMA01-0980: SS 1 | C-52-0304-CMA01-1000 | C-52-0304-CMA01-1000: FS | 2024-11-12 07:30 | 2024-11-18 07:30
C-52-0304-CMA01-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 | Trench Excavation | C-52-0304-CMA01-0990 | C-52-0304-CMA01-0990: FS | C-52-0304-CMA01-1010 | C-52-0304-CMA01-1010: FF | 2024-11-18 07:30 | 2024-11-20 07:30
C-52-0304-CMA01-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 | Bedding | C-52-0304-CMA01-1000 | C-52-0304-CMA01-1000: FF | C-52-0304-CMA01-1020 | C-52-0304-CMA01-1020: FS | 2024-11-19 07:30 | 2024-11-20 07:30
C-52-0304-CMA01-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 | Lowering | C-52-0304-CMA01-1010, C-52-0304-CMA05-1020 | C-52-0304-CMA01-1010: FS, C-52-0304-CMA05-1020: FS | C-52-0304-CMA01-1030, C-52-0304-CMA07-1020 | C-52-0304-CMA01-1030: SS, C-52-0304-CMA07-1020: FS | 2024-12-12 07:30 | 2024-12-13 07:30
C-52-0304-CMA01-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 | Section Tie-in Welding | C-52-0304-CMA01-1020 | C-52-0304-CMA01-1020: SS | C-52-0304-CMA01-1040, C-52-0304-PL-ME-4810 | C-52-0304-CMA01-1040: SS 1, C-52-0304-PL-ME-4810: FF 1 | 2024-12-12 07:30 | 2024-12-14 07:30
C-52-0304-CMA01-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 | NDT (Tie-in Joint) | C-52-0304-CMA01-1030 | C-52-0304-CMA01-1030: SS 1 | C-52-0304-CMA01-1050 | C-52-0304-CMA01-1050: SS 1 | 2024-12-13 07:30 | 2024-12-16 07:30
C-52-0304-CMA01-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA01-1040 | C-52-0304-CMA01-1040: SS 1 | C-52-0304-CMA01-1060 | C-52-0304-CMA01-1060: FS | 2024-12-14 07:30 | 2024-12-17 07:30
C-52-0304-CMA01-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 | Holiday Testing | C-52-0304-CMA01-1050 | C-52-0304-CMA01-1050: FS | C-52-0304-CMA01-1070 | C-52-0304-CMA01-1070: FS | 2024-12-17 07:30 | 2024-12-18 07:30
C-52-0304-CMA01-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 | Padding | C-52-0304-CMA01-1060 | C-52-0304-CMA01-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2024-12-18 07:30 | 2024-12-19 07:30
C-52-0304-CMA07-0970 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 | Excavation (Manual-Trial Pit) | C-52-0304-CMA01-0980 | C-52-0304-CMA01-0980: FS | C-52-0304-CMA07-0980, C-52-0304-CMA02-980 | C-52-0304-CMA07-0980: FS, C-52-0304-CMA02-980: FS | 2024-11-16 07:30 | 2024-11-22 07:30
C-52-0304-CMA07-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 | Sabkha Gatch Laying | C-52-0304-CMA07-0970 | C-52-0304-CMA07-0970: FS | C-52-0304-CMA07-0990 | C-52-0304-CMA07-0990: SS 1 | 2024-11-22 07:30 | 2024-11-28 07:30
C-52-0304-CMA07-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 | Sabka Gatch Compaction | C-52-0304-CMA07-0980 | C-52-0304-CMA07-0980: SS 1 | C-52-0304-CMA07-1000 | C-52-0304-CMA07-1000: FS | 2024-11-23 07:30 | 2024-11-29 07:30
C-52-0304-CMA07-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 | Trench Excavation | C-52-0304-CMA07-0990 | C-52-0304-CMA07-0990: FS | C-52-0304-CMA07-1010 | C-52-0304-CMA07-1010: FF | 2024-11-29 07:30 | 2024-12-04 07:30
C-52-0304-CMA07-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 | Bedding | C-52-0304-CMA07-1000 | C-52-0304-CMA07-1000: FF | C-52-0304-CMA07-1020 | C-52-0304-CMA07-1020: FS | 2024-11-30 07:30 | 2024-12-04 07:30
C-52-0304-CMA07-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 | Lowering | C-52-0304-CMA07-1010, C-52-0304-CMA01-1020 | C-52-0304-CMA07-1010: FS, C-52-0304-CMA01-1020: FS | C-52-0304-CMA07-1030, C-52-0304-CMA02-1020 | C-52-0304-CMA07-1030: SS, C-52-0304-CMA02-1020: FS | 2024-12-13 07:30 | 2024-12-14 07:30
C-52-0304-CMA07-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 | Section Tie-in Welding | C-52-0304-CMA07-1020 | C-52-0304-CMA07-1020: SS | C-52-0304-CMA07-1040, C-52-0304-PL-ME-4810 | C-52-0304-CMA07-1040: SS 1, C-52-0304-PL-ME-4810: FF 1 | 2024-12-13 07:30 | 2024-12-16 07:30
C-52-0304-CMA07-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 | NDT (Tie-in Joint) | C-52-0304-CMA07-1030 | C-52-0304-CMA07-1030: SS 1 | C-52-0304-CMA07-1050 | C-52-0304-CMA07-1050: SS 1 | 2024-12-14 07:30 | 2024-12-17 07:30
C-52-0304-CMA07-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA07-1040 | C-52-0304-CMA07-1040: SS 1 | C-52-0304-CMA07-1060 | C-52-0304-CMA07-1060: FS | 2024-12-16 07:30 | 2024-12-18 07:30
C-52-0304-CMA07-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 | Holiday Testing | C-52-0304-CMA07-1050 | C-52-0304-CMA07-1050: FS | C-52-0304-CMA07-1070 | C-52-0304-CMA07-1070: FS | 2024-12-18 07:30 | 2024-12-19 07:30
C-52-0304-CMA07-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 | Padding | C-52-0304-CMA07-1060 | C-52-0304-CMA07-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2024-12-19 07:30 | 2024-12-20 07:30
C-52-0304-CMA02-980 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 | Sabkha Gatch Laying | C-52-0304-CMA07-0970 | C-52-0304-CMA07-0970: FS | C-52-0304-CMA02-990, C-52-0304-CMA14-0970 | C-52-0304-CMA02-990: SS 1, C-52-0304-CMA14-0970: FS | 2024-11-22 07:30 | 2024-11-28 07:30
C-52-0304-CMA02-990 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 | Sabka Gatch Compaction | C-52-0304-CMA02-980 | C-52-0304-CMA02-980: SS 1 | C-52-0304-CMA02-1010 | C-52-0304-CMA02-1010: FS | 2024-11-23 07:30 | 2024-11-29 07:30
C-52-0304-CMA02-1000 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 | Trench Excavation | C-52-0203-PL-ME-2800 | C-52-0203-PL-ME-2800: FS | C-52-0304-CMA02-1010 | C-52-0304-CMA02-1010: FF | 2024-09-16 | 2024-10-28 17:00
C-52-0304-CMA02-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 | Bedding | C-52-0304-CMA02-990, C-52-0304-CMA02-1000 | C-52-0304-CMA02-990: FS, C-52-0304-CMA02-1000: FF | C-52-0304-CMA02-1020 | C-52-0304-CMA02-1020: FS | 2024-11-29 07:30 | 2024-11-30 07:30
C-52-0304-CMA02-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 | Lowering | C-52-0304-CMA02-1010, C-52-0304-CMA07-1020 | C-52-0304-CMA02-1010: FS, C-52-0304-CMA07-1020: FS | C-52-0304-CMA02-1030, C-52-0304-CMA14-1020 | C-52-0304-CMA02-1030: SS, C-52-0304-CMA14-1020: FS | 2024-12-14 07:30 | 2024-12-16 07:30
C-52-0304-CMA02-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 | Section Tie-in Welding | C-52-0304-CMA02-1020 | C-52-0304-CMA02-1020: SS | C-52-0304-CMA02-1040, C-52-0304-PL-ME-4810 | C-52-0304-CMA02-1040: SS 1, C-52-0304-PL-ME-4810: FF 1 | 2024-12-14 07:30 | 2024-12-17 07:30
C-52-0304-CMA02-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 | NDT (Tie-in Joint) | C-52-0304-CMA02-1030 | C-52-0304-CMA02-1030: SS 1 | C-52-0304-CMA02-1050 | C-52-0304-CMA02-1050: SS 1 | 2024-12-16 07:30 | 2024-12-18 07:30
C-52-0304-CMA02-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA02-1040 | C-52-0304-CMA02-1040: SS 1 | C-52-0304-CMA02-1060 | C-52-0304-CMA02-1060: FS | 2024-12-17 07:30 | 2024-12-19 07:30
C-52-0304-CMA02-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 | Holiday Testing | C-52-0304-CMA02-1050 | C-52-0304-CMA02-1050: FS | C-52-0304-CMA02-1070 | C-52-0304-CMA02-1070: FS | 2024-12-19 07:30 | 2024-12-20 07:30
C-52-0304-CMA02-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 | Padding | C-52-0304-CMA02-1060 | C-52-0304-CMA02-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2024-12-20 07:30 | 2024-12-21 07:30
C-52-0304-CMA14-0970 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 | Excavation (Manual-Trial Pit) | C-52-0304-CMA02-980 | C-52-0304-CMA02-980: FS | C-52-0304-CMA14-0980, C-52-0304-CMA09-0970 | C-52-0304-CMA14-0980: FS, C-52-0304-CMA09-0970: FS | 2024-11-28 07:30 | 2024-12-06 07:30
C-52-0304-CMA14-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 | Sabkha Gatch Laying | C-52-0304-CMA14-0970 | C-52-0304-CMA14-0970: FS | C-52-0304-CMA14-0990 | C-52-0304-CMA14-0990: SS 1 | 2024-12-06 07:30 | 2024-12-12 07:30
C-52-0304-CMA14-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 | Sabka Gatch Compaction | C-52-0304-CMA14-0980 | C-52-0304-CMA14-0980: SS 1 | C-52-0304-CMA14-1000 | C-52-0304-CMA14-1000: FS | 2024-12-07 07:30 | 2024-12-13 07:30
C-52-0304-CMA14-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 | Trench Excavation | C-52-0304-CMA14-0990 | C-52-0304-CMA14-0990: FS | C-52-0304-CMA14-1010 | C-52-0304-CMA14-1010: FF | 2024-12-13 07:30 | 2024-12-16 07:30
C-52-0304-CMA14-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 | Bedding | C-52-0304-CMA14-1000 | C-52-0304-CMA14-1000: FF | C-52-0304-CMA14-1020 | C-52-0304-CMA14-1020: FS | 2024-12-14 07:30 | 2024-12-16 07:30
C-52-0304-CMA14-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 | Lowering | C-52-0304-CMA14-1010, C-52-0304-CMA02-1020 | C-52-0304-CMA14-1010: FS, C-52-0304-CMA02-1020: FS | C-52-0304-CMA14-1030, C-52-0304-CMA09-1020 | C-52-0304-CMA14-1030: SS, C-52-0304-CMA09-1020: FS | 2024-12-16 07:30 | 2024-12-17 07:30
C-52-0304-CMA14-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 | Section Tie-in Welding | C-52-0304-CMA14-1020 | C-52-0304-CMA14-1020: SS | C-52-0304-CMA14-1040, C-52-0304-PL-ME-4810 | C-52-0304-CMA14-1040: SS 1, C-52-0304-PL-ME-4810: FF 1 | 2024-12-16 07:30 | 2024-12-18 07:30
C-52-0304-CMA14-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 | NDT (Tie-in Joint) | C-52-0304-CMA14-1030 | C-52-0304-CMA14-1030: SS 1 | C-52-0304-CMA14-1050 | C-52-0304-CMA14-1050: SS 1 | 2024-12-17 07:30 | 2024-12-19 07:30
C-52-0304-CMA14-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA14-1040 | C-52-0304-CMA14-1040: SS 1 | C-52-0304-CMA14-1060 | C-52-0304-CMA14-1060: FS | 2024-12-18 07:30 | 2024-12-20 07:30
C-52-0304-CMA14-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 | Holiday Testing | C-52-0304-CMA14-1050 | C-52-0304-CMA14-1050: FS | C-52-0304-CMA14-1070 | C-52-0304-CMA14-1070: FS | 2024-12-20 07:30 | 2024-12-21 07:30
C-52-0304-CMA14-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 | Padding | C-52-0304-CMA14-1060 | C-52-0304-CMA14-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2024-12-21 07:30 | 2024-12-23 07:30
C-52-0304-CMA09-0970 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 | Excavation (Manual-Trial Pit) | C-52-0304-CMA14-0970 | C-52-0304-CMA14-0970: FS | C-52-0304-CMA09-0980, C-52-0304-CMA06-0970 | C-52-0304-CMA09-0980: FS, C-52-0304-CMA06-0970: FS | 2024-12-06 07:30 | 2024-12-12 07:30
C-52-0304-CMA09-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 | Sabkha Gatch Laying | C-52-0304-CMA09-0970 | C-52-0304-CMA09-0970: FS | C-52-0304-CMA09-0990 | C-52-0304-CMA09-0990: SS 1 | 2024-12-12 07:30 | 2024-12-18 07:30
C-52-0304-CMA09-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 | Sabka Gatch Compaction | C-52-0304-CMA09-0980 | C-52-0304-CMA09-0980: SS 1 | C-52-0304-CMA09-1000 | C-52-0304-CMA09-1000: FS | 2024-12-13 07:30 | 2024-12-19 07:30
C-52-0304-CMA09-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 | Trench Excavation | C-52-0304-CMA09-0990 | C-52-0304-CMA09-0990: FS | C-52-0304-CMA09-1010 | C-52-0304-CMA09-1010: FF | 2024-12-19 07:30 | 2024-12-21 07:30
C-52-0304-CMA09-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 | Bedding | C-52-0304-CMA09-1000 | C-52-0304-CMA09-1000: FF | C-52-0304-CMA09-1020 | C-52-0304-CMA09-1020: FS | 2024-12-20 07:30 | 2024-12-21 07:30
C-52-0304-CMA09-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 | Lowering | C-52-0304-CMA09-1010, C-52-0304-CMA14-1020 | C-52-0304-CMA09-1010: FS, C-52-0304-CMA14-1020: FS | C-52-0304-CMA09-1030, C-52-0304-CMA06-1020 | C-52-0304-CMA09-1030: SS, C-52-0304-CMA06-1020: FS | 2024-12-21 07:30 | 2024-12-23 07:30
C-52-0304-CMA09-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 | Section Tie-in Welding | C-52-0304-CMA09-1020 | C-52-0304-CMA09-1020: SS | C-52-0304-CMA09-1040, C-52-0304-PL-ME-4810 | C-52-0304-CMA09-1040: SS 1, C-52-0304-PL-ME-4810: FF 1 | 2024-12-21 07:30 | 2024-12-24 07:30
C-52-0304-CMA09-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 | NDT (Tie-in Joint) | C-52-0304-CMA09-1030 | C-52-0304-CMA09-1030: SS 1 | C-52-0304-CMA09-1050 | C-52-0304-CMA09-1050: SS 1 | 2024-12-23 07:30 | 2024-12-25 07:30
C-52-0304-CMA09-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA09-1040 | C-52-0304-CMA09-1040: SS 1 | C-52-0304-CMA09-1060 | C-52-0304-CMA09-1060: FS | 2024-12-24 07:30 | 2024-12-26 07:30
C-52-0304-CMA09-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 | Holiday Testing | C-52-0304-CMA09-1050 | C-52-0304-CMA09-1050: FS | C-52-0304-CMA09-1070 | C-52-0304-CMA09-1070: FS | 2024-12-26 07:30 | 2024-12-27 07:30
C-52-0304-CMA09-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 | Padding | C-52-0304-CMA09-1060 | C-52-0304-CMA09-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2024-12-27 07:30 | 2024-12-28 07:30
C-52-0304-CMA06-0970 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 | Excavation (Manual-Trial Pit) | C-52-0304-CMA09-0970 | C-52-0304-CMA09-0970: FS | C-52-0304-CMA06-0980, C-52-0304-CMA11-1000 | C-52-0304-CMA06-0980: FS, C-52-0304-CMA11-1000: FS | 2024-12-12 07:30 | 2024-12-18 07:30
C-52-0304-CMA06-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 | Sabkha Gatch Laying | C-52-0304-CMA06-0970 | C-52-0304-CMA06-0970: FS | C-52-0304-CMA06-0990 | C-52-0304-CMA06-0990: SS 1 | 2024-12-18 07:30 | 2024-12-24 07:30
C-52-0304-CMA06-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 | Sabka Gatch Compaction | C-52-0304-CMA06-0980 | C-52-0304-CMA06-0980: SS 1 | C-52-0304-CMA06-1000 | C-52-0304-CMA06-1000: FS | 2024-12-19 07:30 | 2024-12-25 07:30
C-52-0304-CMA06-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 | Trench Excavation | C-52-0304-CMA06-0990 | C-52-0304-CMA06-0990: FS | C-52-0304-CMA06-1010 | C-52-0304-CMA06-1010: FF | 2024-12-25 07:30 | 2024-12-27 07:30
C-52-0304-CMA06-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 | Bedding | C-52-0304-CMA06-1000 | C-52-0304-CMA06-1000: FF | C-52-0304-CMA06-1020 | C-52-0304-CMA06-1020: FS | 2024-12-26 07:30 | 2024-12-27 07:30
C-52-0304-CMA06-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 | Lowering | C-52-0304-CMA06-1010, C-52-0304-CMA09-1020 | C-52-0304-CMA06-1010: FS, C-52-0304-CMA09-1020: FS | C-52-0304-CMA06-1030, C-52-0304-CMA11-1020 | C-52-0304-CMA06-1030: SS, C-52-0304-CMA11-1020: FS | 2024-12-27 07:30 | 2024-12-28 07:30
C-52-0304-CMA06-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 | Section Tie-in Welding | C-52-0304-CMA06-1020 | C-52-0304-CMA06-1020: SS | C-52-0304-CMA06-1040, C-52-0304-PL-ME-4810 | C-52-0304-CMA06-1040: SS 1, C-52-0304-PL-ME-4810: FF 1 | 2024-12-27 07:30 | 2024-12-30 07:30
C-52-0304-CMA06-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 | NDT (Tie-in Joint) | C-52-0304-CMA06-1030 | C-52-0304-CMA06-1030: SS 1 | C-52-0304-CMA06-1050 | C-52-0304-CMA06-1050: SS 1 | 2024-12-28 07:30 | 2024-12-31 07:30
C-52-0304-CMA06-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA06-1040 | C-52-0304-CMA06-1040: SS 1 | C-52-0304-CMA06-1060 | C-52-0304-CMA06-1060: FS | 2024-12-30 07:30 | 2025-01-02 07:30
C-52-0304-CMA06-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 | Holiday Testing | C-52-0304-CMA06-1050 | C-52-0304-CMA06-1050: FS | C-52-0304-CMA06-1070 | C-52-0304-CMA06-1070: FS | 2025-01-02 07:30 | 2025-01-03 07:30
C-52-0304-CMA06-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 | Padding | C-52-0304-CMA06-1060 | C-52-0304-CMA06-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2025-01-03 07:30 | 2025-01-04 07:30
C-52-0304-CMA11-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 | Trench Excavation | C-52-0304-CMA06-0970 | C-52-0304-CMA06-0970: FS | C-52-0304-CMA11-1010, C-52-0304-CMA12-1000 | C-52-0304-CMA11-1010: FF, C-52-0304-CMA12-1000: FS | 2024-12-18 07:30 | 2024-12-25 07:30
C-52-0304-CMA11-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 | Bedding | C-52-0304-CMA11-1000 | C-52-0304-CMA11-1000: FF | C-52-0304-CMA11-1020 | C-52-0304-CMA11-1020: FS | 2024-12-24 07:30 | 2024-12-25 07:30
C-52-0304-CMA11-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 | Lowering | C-52-0304-CMA11-1010, C-52-0304-CMA06-1020 | C-52-0304-CMA11-1010: FS, C-52-0304-CMA06-1020: FS | C-52-0304-CMA11-1030, C-52-0304-CMA12-1020 | C-52-0304-CMA11-1030: SS, C-52-0304-CMA12-1020: FS | 2024-12-28 07:30 | 2024-12-30 07:30
C-52-0304-CMA11-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 | Section Tie-in Welding | C-52-0304-CMA11-1020 | C-52-0304-CMA11-1020: SS | C-52-0304-CMA11-1040, C-52-0304-PL-ME-4810 | C-52-0304-CMA11-1040: SS 1, C-52-0304-PL-ME-4810: FF 1 | 2024-12-28 07:30 | 2024-12-31 07:30
C-52-0304-CMA11-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 | NDT (Tie-in Joint) | C-52-0304-CMA11-1030 | C-52-0304-CMA11-1030: SS 1 | C-52-0304-CMA11-1050 | C-52-0304-CMA11-1050: SS 1 | 2024-12-30 07:30 | 2025-01-02 07:30
C-52-0304-CMA11-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA11-1040 | C-52-0304-CMA11-1040: SS 1 | C-52-0304-CMA11-1060 | C-52-0304-CMA11-1060: FS | 2024-12-31 07:30 | 2025-01-03 07:30
C-52-0304-CMA11-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 | Holiday Testing | C-52-0304-CMA11-1050 | C-52-0304-CMA11-1050: FS | C-52-0304-CMA11-1070 | C-52-0304-CMA11-1070: FS | 2025-01-03 07:30 | 2025-01-04 07:30
C-52-0304-CMA11-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 | Padding | C-52-0304-CMA11-1060 | C-52-0304-CMA11-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2025-01-04 07:30 | 2025-01-06 07:30
C-52-0304-CMA12-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 | Trench Excavation | C-52-0304-CMA11-1000 | C-52-0304-CMA11-1000: FS | C-52-0304-CMA12-1010, C-52-0304-CMA13-1000 | C-52-0304-CMA12-1010: FF, C-52-0304-CMA13-1000: FS | 2024-12-25 07:30 | 2025-01-02 07:30
C-52-0304-CMA12-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 | Bedding | C-52-0304-CMA12-1000 | C-52-0304-CMA12-1000: FF | C-52-0304-CMA12-1020 | C-52-0304-CMA12-1020: FS | 2024-12-31 07:30 | 2025-01-02 07:30
C-52-0304-CMA12-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 | Lowering | C-52-0304-CMA12-1010, C-52-0304-CMA11-1020 | C-52-0304-CMA12-1010: FS, C-52-0304-CMA11-1020: FS | C-52-0304-CMA12-1030, C-52-0304-CMA13-1020 | C-52-0304-CMA12-1030: SS, C-52-0304-CMA13-1020: FS | 2025-01-02 07:30 | 2025-01-03 07:30
C-52-0304-CMA12-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 | Section Tie-in Welding | C-52-0304-CMA12-1020 | C-52-0304-CMA12-1020: SS | C-52-0304-CMA12-1040, C-52-0304-PL-ME-4810 | C-52-0304-CMA12-1040: SS 1, C-52-0304-PL-ME-4810: FF 1 | 2025-01-02 07:30 | 2025-01-04 07:30
C-52-0304-CMA12-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 | NDT (Tie-in Joint) | C-52-0304-CMA12-1030 | C-52-0304-CMA12-1030: SS 1 | C-52-0304-CMA12-1050 | C-52-0304-CMA12-1050: SS 1 | 2025-01-03 07:30 | 2025-01-06 07:30
C-52-0304-CMA12-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA12-1040 | C-52-0304-CMA12-1040: SS 1 | C-52-0304-CMA12-1060 | C-52-0304-CMA12-1060: FS | 2025-01-04 07:30 | 2025-01-07 07:30
C-52-0304-CMA12-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 | Holiday Testing | C-52-0304-CMA12-1050 | C-52-0304-CMA12-1050: FS | C-52-0304-CMA12-1070 | C-52-0304-CMA12-1070: FS | 2025-01-07 07:30 | 2025-01-08 07:30
C-52-0304-CMA12-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 | Padding | C-52-0304-CMA12-1060 | C-52-0304-CMA12-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2025-01-08 07:30 | 2025-01-09 07:30
C-52-0304-CMA13-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 | Trench Excavation | C-52-0304-CMA12-1000 | C-52-0304-CMA12-1000: FS | C-52-0304-CMA13-1010 | C-52-0304-CMA13-1010: FF | 2025-01-02 07:30 | 2025-01-09 07:30
C-52-0304-CMA13-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 | Bedding | C-52-0304-CMA13-1000 | C-52-0304-CMA13-1000: FF | C-52-0304-CMA13-1020 | C-52-0304-CMA13-1020: FS | 2025-01-08 07:30 | 2025-01-09 07:30
C-52-0304-CMA13-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 | Lowering | C-52-0304-CMA13-1010, C-52-0304-CMA12-1020 | C-52-0304-CMA13-1010: FS, C-52-0304-CMA12-1020: FS | C-52-0304-CMA13-1030, C-52-0304-CMA03-1020 | C-52-0304-CMA13-1030: SS, C-52-0304-CMA03-1020: FS | 2025-01-09 07:30 | 2025-01-10 07:30
C-52-0304-CMA13-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 | Section Tie-in Welding | C-52-0304-CMA13-1020 | C-52-0304-CMA13-1020: SS | C-52-0304-CMA13-1040, C-52-0304-PL-ME-4810 | C-52-0304-CMA13-1040: SS 1, C-52-0304-PL-ME-4810: FF 1 | 2025-01-09 07:30 | 2025-01-11 07:30
C-52-0304-CMA13-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 | NDT (Tie-in Joint) | C-52-0304-CMA13-1030 | C-52-0304-CMA13-1030: SS 1 | C-52-0304-CMA13-1050 | C-52-0304-CMA13-1050: SS 1 | 2025-01-10 07:30 | 2025-01-13 07:30
C-52-0304-CMA13-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA13-1040 | C-52-0304-CMA13-1040: SS 1 | C-52-0304-CMA13-1060 | C-52-0304-CMA13-1060: FS | 2025-01-11 07:30 | 2025-01-14 07:30
C-52-0304-CMA13-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 | Holiday Testing | C-52-0304-CMA13-1050 | C-52-0304-CMA13-1050: FS | C-52-0304-CMA13-1070 | C-52-0304-CMA13-1070: FS | 2025-01-14 07:30 | 2025-01-15 07:30
C-52-0304-CMA13-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 | Padding | C-52-0304-CMA13-1060 | C-52-0304-CMA13-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2025-01-15 07:30 | 2025-01-16 07:30
C-52-0304-CMA03-1000 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 | Trench Excavation | C-52-0304-PL-CI-1800 | C-52-0304-PL-CI-1800: FS | C-52-0304-CMA03-1010, C-52-0304-CMA08-1000 | C-52-0304-CMA03-1010: FF, C-52-0304-CMA08-1000: FS | 2024-09-19 | 2024-11-07 07:30
C-52-0304-CMA03-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 | Bedding | C-52-0304-CMA03-1000 | C-52-0304-CMA03-1000: FF | C-52-0304-CMA03-1020 | C-52-0304-CMA03-1020: FS | 2024-11-06 07:30 | 2024-11-07 07:30
C-52-0304-CMA03-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 | Lowering | C-52-0304-CMA03-1010, C-52-0304-CMA13-1020 | C-52-0304-CMA03-1010: FS, C-52-0304-CMA13-1020: FS | C-52-0304-CMA03-1030, C-52-0304-CMA08-1020 | C-52-0304-CMA03-1030: SS, C-52-0304-CMA08-1020: FS | 2025-01-10 07:30 | 2025-01-11 07:30
C-52-0304-CMA03-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 | Section Tie-in Welding | C-52-0304-CMA03-1020 | C-52-0304-CMA03-1020: SS | C-52-0304-CMA03-1040, C-52-0304-PL-ME-4810 | C-52-0304-CMA03-1040: SS 1, C-52-0304-PL-ME-4810: FF 1 | 2025-01-10 07:30 | 2025-01-14 07:30
C-52-0304-CMA03-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 | NDT (Tie-in Joint) | C-52-0304-CMA03-1030 | C-52-0304-CMA03-1030: SS 1 | C-52-0304-CMA03-1050 | C-52-0304-CMA03-1050: SS 1 | 2025-01-11 07:30 | 2025-01-15 07:30
C-52-0304-CMA03-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA03-1040 | C-52-0304-CMA03-1040: SS 1 | C-52-0304-CMA03-1060 | C-52-0304-CMA03-1060: FS | 2025-01-13 07:30 | 2025-01-16 07:30
C-52-0304-CMA03-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 | Holiday Testing | C-52-0304-CMA03-1050 | C-52-0304-CMA03-1050: FS | C-52-0304-CMA03-1070 | C-52-0304-CMA03-1070: FS | 2025-01-16 07:30 | 2025-01-17 07:30
C-52-0304-CMA03-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 | Padding | C-52-0304-CMA03-1060 | C-52-0304-CMA03-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2025-01-17 07:30 | 2025-01-18 07:30
C-52-0304-CMA08-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 | Trench Excavation | C-52-0304-CMA03-1000 | C-52-0304-CMA03-1000: FS | C-52-0304-CMA08-1010, C-52-0304-CMA10-1000 | C-52-0304-CMA08-1010: FF, C-52-0304-CMA10-1000: FS | 2024-11-07 07:30 | 2024-11-14 07:30
C-52-0304-CMA08-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 | Bedding | C-52-0304-CMA08-1000 | C-52-0304-CMA08-1000: FF | C-52-0304-CMA08-1020 | C-52-0304-CMA08-1020: FS | 2024-11-13 07:30 | 2024-11-14 07:30
C-52-0304-CMA08-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 | Lowering | C-52-0304-CMA08-1010, C-52-0304-CMA03-1020 | C-52-0304-CMA08-1010: FS, C-52-0304-CMA03-1020: FS | C-52-0304-CMA08-1030, C-52-0304-CMA10-1020 | C-52-0304-CMA08-1030: SS, C-52-0304-CMA10-1020: FS | 2025-01-11 07:30 | 2025-01-13 07:30
C-52-0304-CMA08-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 | Section Tie-in Welding | C-52-0304-CMA08-1020 | C-52-0304-CMA08-1020: SS | C-52-0304-CMA08-1040, C-52-0304-PL-ME-4810 | C-52-0304-CMA08-1040: SS 1, C-52-0304-PL-ME-4810: FF 1 | 2025-01-11 07:30 | 2025-01-14 07:30
C-52-0304-CMA08-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 | NDT (Tie-in Joint) | C-52-0304-CMA08-1030 | C-52-0304-CMA08-1030: SS 1 | C-52-0304-CMA08-1050 | C-52-0304-CMA08-1050: SS 1 | 2025-01-13 07:30 | 2025-01-15 07:30
C-52-0304-CMA08-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA08-1040 | C-52-0304-CMA08-1040: SS 1 | C-52-0304-CMA08-1060 | C-52-0304-CMA08-1060: FS | 2025-01-14 07:30 | 2025-01-16 07:30
C-52-0304-CMA08-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 | Holiday Testing | C-52-0304-CMA08-1050 | C-52-0304-CMA08-1050: FS | C-52-0304-CMA08-1070 | C-52-0304-CMA08-1070: FS | 2025-01-16 07:30 | 2025-01-17 07:30
C-52-0304-CMA08-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 | Padding | C-52-0304-CMA08-1060 | C-52-0304-CMA08-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2025-01-17 07:30 | 2025-01-18 07:30
C-52-0304-CMA10-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 | Trench Excavation | C-52-0304-CMA08-1000 | C-52-0304-CMA08-1000: FS | C-52-0304-CMA10-1010 | C-52-0304-CMA10-1010: FF | 2024-11-14 07:30 | 2024-11-21 07:30
C-52-0304-CMA10-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 | Bedding | C-52-0304-CMA10-1000 | C-52-0304-CMA10-1000: FF | C-52-0304-CMA10-1020 | C-52-0304-CMA10-1020: FS | 2024-11-20 07:30 | 2024-11-21 07:30
C-52-0304-CMA10-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 | Lowering | C-52-0304-CMA10-1010, C-52-0304-CMA08-1020 | C-52-0304-CMA10-1010: FS, C-52-0304-CMA08-1020: FS | C-52-0304-CMA10-1030 | C-52-0304-CMA10-1030: SS | 2025-01-13 07:30 | 2025-01-14 07:30
C-52-0304-CMA10-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 | Section Tie-in Welding | C-52-0304-CMA10-1020 | C-52-0304-CMA10-1020: SS | C-52-0304-CMA10-1040, C-52-0304-PL-ME-4810 | C-52-0304-CMA10-1040: SS 1, C-52-0304-PL-ME-4810: FF 1 | 2025-01-13 07:30 | 2025-01-15 07:30
C-52-0304-CMA10-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 | NDT (Tie-in Joint) | C-52-0304-CMA10-1030 | C-52-0304-CMA10-1030: SS 1 | C-52-0304-CMA10-1050 | C-52-0304-CMA10-1050: SS 1 | 2025-01-14 07:30 | 2025-01-16 07:30
C-52-0304-CMA10-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA10-1040 | C-52-0304-CMA10-1040: SS 1 | C-52-0304-CMA10-1060 | C-52-0304-CMA10-1060: FS | 2025-01-15 07:30 | 2025-01-17 07:30
C-52-0304-CMA10-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 | Holiday Testing | C-52-0304-CMA10-1050 | C-52-0304-CMA10-1050: FS | C-52-0304-CMA10-1070 | C-52-0304-CMA10-1070: FS | 2025-01-17 07:30 | 2025-01-18 07:30
C-52-0304-CMA10-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 | Padding | C-52-0304-CMA10-1060 | C-52-0304-CMA10-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2025-01-18 07:30 | 2025-01-20 07:30
C-52-0304-CME01-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 | Trench Excavation | C-52-0304-PL-ME-2800, C-52-0102-CME06-1090 | C-52-0304-PL-ME-2800: FF, C-52-0102-CME06-1090: FS | C-52-0304-CME01-1010, C-52-0304-CME02-1000 | C-52-0304-CME01-1010: FS, C-52-0304-CME02-1000: FS 1 | 2024-11-30 07:00 | 2024-12-04 17:00
C-52-0304-CME01-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 | Bedding | C-52-0304-CME01-1000 | C-52-0304-CME01-1000: FS | C-52-0304-CME01-1020 | C-52-0304-CME01-1020: FS | 2024-12-05 07:00 | 2024-12-06 17:00
C-52-0304-CME01-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 | Lowering | C-52-0304-CME01-1010, C-52-0304-PL-ME-2800 | C-52-0304-CME01-1010: FS, C-52-0304-PL-ME-2800: FS 7 | C-52-0304-CME01-1030, C-52-0304-CME02-1020 | C-52-0304-CME01-1030: FS, C-52-0304-CME02-1020: FS | 2024-12-10 07:30 | 2024-12-12 07:30
C-52-0304-CME01-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 | Section Tie-in Welding | C-52-0304-CME01-1020 | C-52-0304-CME01-1020: FS | C-52-0304-CME01-1040, C-52-0304-PL-ME-4810 | C-52-0304-CME01-1040: FS, C-52-0304-PL-ME-4810: FF 1 | 2024-12-12 07:30 | 2024-12-16 07:30
C-52-0304-CME01-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 | NDT (Tie-in Joint) | C-52-0304-CME01-1030 | C-52-0304-CME01-1030: FS | C-52-0304-CME01-1050 | C-52-0304-CME01-1050: FS | 2024-12-16 07:30 | 2024-12-19 07:30
C-52-0304-CME01-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME01-1040 | C-52-0304-CME01-1040: FS | C-52-0304-CME01-1060 | C-52-0304-CME01-1060: FS | 2024-12-19 07:30 | 2024-12-23 07:30
C-52-0304-CME01-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 | Holiday Testing | C-52-0304-CME01-1050 | C-52-0304-CME01-1050: FS | C-52-0304-CME01-1070 | C-52-0304-CME01-1070: FS | 2024-12-23 07:30 | 2024-12-25 07:30
C-52-0304-CME01-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 | Padding & Back Filling | C-52-0304-CME01-1060 | C-52-0304-CME01-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2024-12-25 07:30 | 2024-12-27 07:30
C-52-0304-CME02-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 | Trench Excavation | C-52-0304-CME01-1000 | C-52-0304-CME01-1000: FS 1 | C-52-0304-CME02-1010, C-52-0304-CME03-1000 | C-52-0304-CME02-1010: FS, C-52-0304-CME03-1000: FS 1 | 2024-12-06 07:00 | 2024-12-07 17:00
C-52-0304-CME02-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 | Bedding | C-52-0304-CME02-1000 | C-52-0304-CME02-1000: FS | C-52-0304-CME02-1020 | C-52-0304-CME02-1020: FS | 2024-12-09 07:00 | 2024-12-10 17:00
C-52-0304-CME02-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 | Lowering | C-52-0304-CME02-1010, C-52-0304-CME01-1020 | C-52-0304-CME02-1010: FS, C-52-0304-CME01-1020: FS | C-52-0304-CME02-1030, C-52-0304-CME03-1020 | C-52-0304-CME02-1030: FS, C-52-0304-CME03-1020: FS | 2024-12-12 07:30 | 2024-12-14 07:30
C-52-0304-CME02-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 | Section Tie-in Welding | C-52-0304-CME02-1020 | C-52-0304-CME02-1020: FS | C-52-0304-CME02-1040, C-52-0304-PL-ME-4810 | C-52-0304-CME02-1040: FS, C-52-0304-PL-ME-4810: FF 1 | 2024-12-14 07:30 | 2024-12-18 07:30
C-52-0304-CME02-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 | NDT (Tie-in Joint) | C-52-0304-CME02-1030 | C-52-0304-CME02-1030: FS | C-52-0304-CME02-1050 | C-52-0304-CME02-1050: FS | 2024-12-18 07:30 | 2024-12-21 07:30
C-52-0304-CME02-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME02-1040 | C-52-0304-CME02-1040: FS | C-52-0304-CME02-1060 | C-52-0304-CME02-1060: FS | 2024-12-21 07:30 | 2024-12-25 07:30
C-52-0304-CME02-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 | Holiday Testing | C-52-0304-CME02-1050 | C-52-0304-CME02-1050: FS | C-52-0304-CME02-1070 | C-52-0304-CME02-1070: FS | 2024-12-25 07:30 | 2024-12-27 07:30
C-52-0304-CME02-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 | Padding & Back Filling | C-52-0304-CME02-1060 | C-52-0304-CME02-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2024-12-27 07:30 | 2024-12-30 07:30
C-52-0304-CME03-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 | Trench Excavation | C-52-0304-CME02-1000 | C-52-0304-CME02-1000: FS 1 | C-52-0304-CME03-1010, C-52-0304-CME04-1000 | C-52-0304-CME03-1010: FS, C-52-0304-CME04-1000: FS 1 | 2024-12-10 07:00 | 2024-12-11 17:00
C-52-0304-CME03-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 | Bedding | C-52-0304-CME03-1000 | C-52-0304-CME03-1000: FS | C-52-0304-CME03-1020 | C-52-0304-CME03-1020: FS | 2024-12-12 07:00 | 2024-12-13 17:00
C-52-0304-CME03-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 | Lowering | C-52-0304-CME03-1010, C-52-0304-CME02-1020 | C-52-0304-CME03-1010: FS, C-52-0304-CME02-1020: FS | C-52-0304-CME03-1030, C-52-0304-CME04-1020 | C-52-0304-CME03-1030: FS, C-52-0304-CME04-1020: FS | 2024-12-14 07:30 | 2024-12-17 07:30
C-52-0304-CME03-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 | Section Tie-in Welding | C-52-0304-CME03-1020 | C-52-0304-CME03-1020: FS | C-52-0304-CME03-1040, C-52-0304-PL-ME-4810 | C-52-0304-CME03-1040: FS, C-52-0304-PL-ME-4810: FF 1 | 2024-12-17 07:30 | 2024-12-20 07:30
C-52-0304-CME03-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 | NDT (Tie-in Joint) | C-52-0304-CME03-1030 | C-52-0304-CME03-1030: FS | C-52-0304-CME03-1050 | C-52-0304-CME03-1050: FS | 2024-12-20 07:30 | 2024-12-24 07:30
C-52-0304-CME03-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME03-1040 | C-52-0304-CME03-1040: FS | C-52-0304-CME03-1060 | C-52-0304-CME03-1060: FS | 2024-12-24 07:30 | 2024-12-27 07:30
C-52-0304-CME03-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 | Holiday Testing | C-52-0304-CME03-1050 | C-52-0304-CME03-1050: FS | C-52-0304-CME03-1070 | C-52-0304-CME03-1070: FS | 2024-12-27 07:30 | 2024-12-30 07:30
C-52-0304-CME03-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 | Padding & Back Filling | C-52-0304-CME03-1060 | C-52-0304-CME03-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2024-12-30 07:30 | 2025-01-02 07:30
C-52-0304-CME04-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 | Trench Excavation | C-52-0304-CME03-1000 | C-52-0304-CME03-1000: FS 1 | C-52-0304-CME04-1010, C-52-0304-CME05-1000 | C-52-0304-CME04-1010: FS, C-52-0304-CME05-1000: FS 1 | 2024-12-13 07:00 | 2024-12-14 17:00
C-52-0304-CME04-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 | Bedding | C-52-0304-CME04-1000 | C-52-0304-CME04-1000: FS | C-52-0304-CME04-1020 | C-52-0304-CME04-1020: FS | 2024-12-16 07:00 | 2024-12-17 17:00
C-52-0304-CME04-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 | Lowering | C-52-0304-CME04-1010, C-52-0304-CME03-1020 | C-52-0304-CME04-1010: FS, C-52-0304-CME03-1020: FS | C-52-0304-CME04-1030, C-52-0304-CME05-1020 | C-52-0304-CME04-1030: FS, C-52-0304-CME05-1020: FS | 2024-12-18 07:00 | 2024-12-19 17:00
C-52-0304-CME04-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 | Section Tie-in Welding | C-52-0304-CME04-1020 | C-52-0304-CME04-1020: FS | C-52-0304-CME04-1040, C-52-0304-PL-ME-4810 | C-52-0304-CME04-1040: FS, C-52-0304-PL-ME-4810: FF 1 | 2024-12-20 07:00 | 2024-12-23 17:00
C-52-0304-CME04-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 | NDT (Tie-in Joint) | C-52-0304-CME04-1030 | C-52-0304-CME04-1030: FS | C-52-0304-CME04-1050 | C-52-0304-CME04-1050: FS | 2024-12-24 07:00 | 2024-12-26 17:00
C-52-0304-CME04-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME04-1040 | C-52-0304-CME04-1040: FS | C-52-0304-CME04-1060 | C-52-0304-CME04-1060: FS | 2024-12-27 07:00 | 2024-12-30 17:00
C-52-0304-CME04-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 | Holiday Testing | C-52-0304-CME04-1050 | C-52-0304-CME04-1050: FS | C-52-0304-CME04-1070 | C-52-0304-CME04-1070: FS | 2024-12-31 07:00 | 2025-01-02 17:00
C-52-0304-CME04-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 | Padding & Back Filling | C-52-0304-CME04-1060 | C-52-0304-CME04-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2025-01-03 07:00 | 2025-01-04 17:00
C-52-0304-CME05-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 | Trench Excavation | C-52-0304-CME04-1000 | C-52-0304-CME04-1000: FS 1 | C-52-0304-CME05-1010, C-52-0304-CME06-1000 | C-52-0304-CME05-1010: FS, C-52-0304-CME06-1000: FS 1 | 2024-12-17 07:00 | 2024-12-18 17:00
C-52-0304-CME05-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 | Bedding | C-52-0304-CME05-1000 | C-52-0304-CME05-1000: FS | C-52-0304-CME05-1020 | C-52-0304-CME05-1020: FS | 2024-12-19 07:00 | 2024-12-20 17:00
C-52-0304-CME05-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 | Lowering | C-52-0304-CME05-1010, C-52-0304-CME04-1020 | C-52-0304-CME05-1010: FS, C-52-0304-CME04-1020: FS | C-52-0304-CME05-1030, C-52-0304-CME06-1020 | C-52-0304-CME05-1030: FS, C-52-0304-CME06-1020: FS | 2024-12-21 07:00 | 2024-12-23 17:00
C-52-0304-CME05-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 | Section Tie-in Welding | C-52-0304-CME05-1020 | C-52-0304-CME05-1020: FS | C-52-0304-CME05-1040, C-52-0304-PL-ME-4810 | C-52-0304-CME05-1040: FS, C-52-0304-PL-ME-4810: FF 1 | 2024-12-24 07:00 | 2024-12-26 17:00
C-52-0304-CME05-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 | NDT (Tie-in Joint) | C-52-0304-CME05-1030 | C-52-0304-CME05-1030: FS | C-52-0304-CME05-1050 | C-52-0304-CME05-1050: FS | 2024-12-27 07:00 | 2024-12-30 17:00
C-52-0304-CME05-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME05-1040 | C-52-0304-CME05-1040: FS | C-52-0304-CME05-1060 | C-52-0304-CME05-1060: FS | 2024-12-31 07:00 | 2025-01-03 17:00
C-52-0304-CME05-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 | Holiday Testing | C-52-0304-CME05-1050 | C-52-0304-CME05-1050: FS | C-52-0304-CME05-1070 | C-52-0304-CME05-1070: FS | 2025-01-04 07:00 | 2025-01-06 17:00
C-52-0304-CME05-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 | Padding & Back Filling | C-52-0304-CME05-1060 | C-52-0304-CME05-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2025-01-07 07:00 | 2025-01-08 17:00
C-52-0304-CME06-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 | Trench Excavation | C-52-0304-CME05-1000 | C-52-0304-CME05-1000: FS 1 | C-52-0304-CME06-1010, C-52-0304-CME07-1000 | C-52-0304-CME06-1010: FS, C-52-0304-CME07-1000: FS 1 | 2024-12-20 07:00 | 2024-12-21 17:00
C-52-0304-CME06-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 | Bedding | C-52-0304-CME06-1000 | C-52-0304-CME06-1000: FS | C-52-0304-CME06-1020 | C-52-0304-CME06-1020: FS | 2024-12-23 07:00 | 2024-12-24 17:00
C-52-0304-CME06-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 | Lowering | C-52-0304-CME06-1010, C-52-0304-CME05-1020 | C-52-0304-CME06-1010: FS, C-52-0304-CME05-1020: FS | C-52-0304-CME06-1030, C-52-0304-CME07-1020 | C-52-0304-CME06-1030: FS, C-52-0304-CME07-1020: FS | 2024-12-25 07:00 | 2024-12-26 17:00
C-52-0304-CME06-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 | Section Tie-in Welding | C-52-0304-CME06-1020 | C-52-0304-CME06-1020: FS | C-52-0304-CME06-1040, C-52-0304-PL-ME-4810 | C-52-0304-CME06-1040: FS, C-52-0304-PL-ME-4810: FF 1 | 2024-12-27 07:00 | 2024-12-30 17:00
C-52-0304-CME06-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 | NDT (Tie-in Joint) | C-52-0304-CME06-1030 | C-52-0304-CME06-1030: FS | C-52-0304-CME06-1050 | C-52-0304-CME06-1050: FS | 2024-12-31 07:00 | 2025-01-03 17:00
C-52-0304-CME06-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME06-1040 | C-52-0304-CME06-1040: FS | C-52-0304-CME06-1060 | C-52-0304-CME06-1060: FS | 2025-01-04 07:00 | 2025-01-07 17:00
C-52-0304-CME06-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 | Holiday Testing | C-52-0304-CME06-1050 | C-52-0304-CME06-1050: FS | C-52-0304-CME06-1070 | C-52-0304-CME06-1070: FS | 2025-01-08 07:00 | 2025-01-09 17:00
C-52-0304-CME06-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 | Padding & Back Filling | C-52-0304-CME06-1060 | C-52-0304-CME06-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2025-01-10 07:00 | 2025-01-11 17:00
C-52-0304-CME07-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 | Trench Excavation | C-52-0304-CME06-1000 | C-52-0304-CME06-1000: FS 1 | C-52-0304-CME07-1010, C-52-0304-CME08-1000 | C-52-0304-CME07-1010: FS, C-52-0304-CME08-1000: FS 1 | 2024-12-24 07:00 | 2024-12-25 17:00
C-52-0304-CME07-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 | Bedding | C-52-0304-CME07-1000 | C-52-0304-CME07-1000: FS | C-52-0304-CME07-1020 | C-52-0304-CME07-1020: FS | 2024-12-26 07:00 | 2024-12-27 17:00
C-52-0304-CME07-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 | Lowering | C-52-0304-CME07-1010, C-52-0304-CME06-1020 | C-52-0304-CME07-1010: FS, C-52-0304-CME06-1020: FS | C-52-0304-CME07-1030, C-52-0304-CME08-1020 | C-52-0304-CME07-1030: FS, C-52-0304-CME08-1020: FS | 2024-12-28 07:00 | 2024-12-30 17:00
C-52-0304-CME07-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 | Section Tie-in Welding | C-52-0304-CME07-1020 | C-52-0304-CME07-1020: FS | C-52-0304-CME07-1040, C-52-0304-PL-ME-4810 | C-52-0304-CME07-1040: FS, C-52-0304-PL-ME-4810: FF 1 | 2024-12-31 07:00 | 2025-01-03 17:00
C-52-0304-CME07-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 | NDT (Tie-in Joint) | C-52-0304-CME07-1030 | C-52-0304-CME07-1030: FS | C-52-0304-CME07-1050 | C-52-0304-CME07-1050: FS | 2025-01-04 07:00 | 2025-01-07 17:00
C-52-0304-CME07-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME07-1040 | C-52-0304-CME07-1040: FS | C-52-0304-CME07-1060 | C-52-0304-CME07-1060: FS | 2025-01-08 07:00 | 2025-01-10 17:00
C-52-0304-CME07-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 | Holiday Testing | C-52-0304-CME07-1050 | C-52-0304-CME07-1050: FS | C-52-0304-CME07-1070 | C-52-0304-CME07-1070: FS | 2025-01-11 07:00 | 2025-01-13 17:00
C-52-0304-CME07-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 | Padding & Back Filling | C-52-0304-CME07-1060 | C-52-0304-CME07-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2025-01-14 07:00 | 2025-01-15 17:00
C-52-0304-CME08-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 | Trench Excavation | C-52-0304-CME07-1000 | C-52-0304-CME07-1000: FS 1 | C-52-0304-CME08-1010, C-52-0304-CME09-1000 | C-52-0304-CME08-1010: FS, C-52-0304-CME09-1000: FS 1 | 2024-12-27 07:00 | 2024-12-28 17:00
C-52-0304-CME08-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 | Bedding | C-52-0304-CME08-1000 | C-52-0304-CME08-1000: FS | C-52-0304-CME08-1020 | C-52-0304-CME08-1020: FS | 2024-12-30 07:00 | 2024-12-31 17:00
C-52-0304-CME08-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 | Lowering | C-52-0304-CME08-1010, C-52-0304-CME07-1020 | C-52-0304-CME08-1010: FS, C-52-0304-CME07-1020: FS | C-52-0304-CME08-1030, C-52-0304-CME09-1020 | C-52-0304-CME08-1030: FS, C-52-0304-CME09-1020: FS | 2025-01-02 07:00 | 2025-01-03 17:00
C-52-0304-CME08-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 | Section Tie-in Welding | C-52-0304-CME08-1020 | C-52-0304-CME08-1020: FS | C-52-0304-CME08-1040, C-52-0304-PL-ME-4810 | C-52-0304-CME08-1040: FS, C-52-0304-PL-ME-4810: FF 1 | 2025-01-04 07:00 | 2025-01-07 17:00
C-52-0304-CME08-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 | NDT (Tie-in Joint) | C-52-0304-CME08-1030 | C-52-0304-CME08-1030: FS | C-52-0304-CME08-1050 | C-52-0304-CME08-1050: FS | 2025-01-08 07:00 | 2025-01-10 17:00
C-52-0304-CME08-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME08-1040 | C-52-0304-CME08-1040: FS | C-52-0304-CME08-1060 | C-52-0304-CME08-1060: FS | 2025-01-11 07:00 | 2025-01-14 17:00
C-52-0304-CME08-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 | Holiday Testing | C-52-0304-CME08-1050 | C-52-0304-CME08-1050: FS | C-52-0304-CME08-1070 | C-52-0304-CME08-1070: FS | 2025-01-15 07:00 | 2025-01-16 17:00
C-52-0304-CME08-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 | Padding & Back Filling | C-52-0304-CME08-1060 | C-52-0304-CME08-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2025-01-17 07:00 | 2025-01-18 17:00
C-52-0304-CME09-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 | Trench Excavation | C-52-0304-CME08-1000 | C-52-0304-CME08-1000: FS 1 | C-52-0304-CME09-1010, C-52-0304-CME10-1000 | C-52-0304-CME09-1010: FS, C-52-0304-CME10-1000: FS 1 | 2024-12-31 07:00 | 2025-01-02 17:00
C-52-0304-CME09-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 | Bedding | C-52-0304-CME09-1000 | C-52-0304-CME09-1000: FS | C-52-0304-CME09-1020 | C-52-0304-CME09-1020: FS | 2025-01-03 07:00 | 2025-01-04 17:00
C-52-0304-CME09-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 | Lowering | C-52-0304-CME09-1010, C-52-0304-CME08-1020 | C-52-0304-CME09-1010: FS, C-52-0304-CME08-1020: FS | C-52-0304-CME09-1030, C-52-0304-CME10-1020 | C-52-0304-CME09-1030: FS, C-52-0304-CME10-1020: FS | 2025-01-06 07:00 | 2025-01-07 17:00
C-52-0304-CME09-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 | Section Tie-in Welding | C-52-0304-CME09-1020 | C-52-0304-CME09-1020: FS | C-52-0304-CME09-1040, C-52-0304-PL-ME-4810 | C-52-0304-CME09-1040: FS, C-52-0304-PL-ME-4810: FF 1 | 2025-01-08 07:00 | 2025-01-10 17:00
C-52-0304-CME09-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 | NDT (Tie-in Joint) | C-52-0304-CME09-1030 | C-52-0304-CME09-1030: FS | C-52-0304-CME09-1050 | C-52-0304-CME09-1050: FS | 2025-01-11 07:00 | 2025-01-14 17:00
C-52-0304-CME09-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME09-1040 | C-52-0304-CME09-1040: FS | C-52-0304-CME09-1060 | C-52-0304-CME09-1060: FS | 2025-01-15 07:00 | 2025-01-17 17:00
C-52-0304-CME09-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 | Holiday Testing | C-52-0304-CME09-1050 | C-52-0304-CME09-1050: FS | C-52-0304-CME09-1070 | C-52-0304-CME09-1070: FS | 2025-01-18 07:00 | 2025-01-20 17:00
C-52-0304-CME09-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 | Padding & Back Filling | C-52-0304-CME09-1060 | C-52-0304-CME09-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2025-01-21 07:00 | 2025-01-22 17:00
C-52-0304-CME11-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 | Trench Excavation | C-52-0304-CME10-1000 | C-52-0304-CME10-1000: FS 1 | C-52-0304-CME11-1010, C-52-0304-CME12-1000 | C-52-0304-CME11-1010: FS, C-52-0304-CME12-1000: FS 1 | 2025-01-10 07:00 | 2025-01-11 17:00
C-52-0304-CME11-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 | Bedding | C-52-0304-CME11-1000 | C-52-0304-CME11-1000: FS | C-52-0304-CME11-1020 | C-52-0304-CME11-1020: FS | 2025-01-13 07:00 | 2025-01-14 17:00
C-52-0304-CME11-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 | Lowering | C-52-0304-CME11-1010, C-52-0304-CME10-1020 | C-52-0304-CME11-1010: FS, C-52-0304-CME10-1020: FS | C-52-0304-CME11-1030, C-52-0304-CME12-1020 | C-52-0304-CME11-1030: FS, C-52-0304-CME12-1020: FS | 2025-01-15 07:00 | 2025-01-16 17:00
C-52-0304-CME11-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 | Section Tie-in Welding | C-52-0304-CME11-1020 | C-52-0304-CME11-1020: FS | C-52-0304-CME11-1040, C-52-0304-PL-ME-4810 | C-52-0304-CME11-1040: FS, C-52-0304-PL-ME-4810: FF 1 | 2025-01-17 07:00 | 2025-01-20 17:00
C-52-0304-CME11-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 | NDT (Tie-in Joint) | C-52-0304-CME11-1030 | C-52-0304-CME11-1030: FS | C-52-0304-CME11-1050 | C-52-0304-CME11-1050: FS | 2025-01-21 07:00 | 2025-01-23 17:00
C-52-0304-CME11-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME11-1040 | C-52-0304-CME11-1040: FS | C-52-0304-CME11-1060 | C-52-0304-CME11-1060: FS | 2025-01-24 07:00 | 2025-01-27 17:00
C-52-0304-CME11-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 | Holiday Testing | C-52-0304-CME11-1050 | C-52-0304-CME11-1050: FS | C-52-0304-CME11-1070 | C-52-0304-CME11-1070: FS | 2025-01-28 07:00 | 2025-01-29 17:00
C-52-0304-CME11-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 | Padding & Back Filling | C-52-0304-CME11-1060 | C-52-0304-CME11-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2025-01-30 07:00 | 2025-01-31 17:00
C-52-0304-CME12-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 | Trench Excavation | C-52-0304-CME11-1000 | C-52-0304-CME11-1000: FS 1 | C-52-0304-CME12-1010 | C-52-0304-CME12-1010: FS | 2025-01-14 07:00 | 2025-01-15 17:00
C-52-0304-CME12-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 | Bedding | C-52-0304-CME12-1000 | C-52-0304-CME12-1000: FS | C-52-0304-CME12-1020 | C-52-0304-CME12-1020: FS | 2025-01-16 07:00 | 2025-01-17 17:00
C-52-0304-CME12-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 | Lowering | C-52-0304-CME12-1010, C-52-0304-CME11-1020 | C-52-0304-CME12-1010: FS, C-52-0304-CME11-1020: FS | C-52-0304-CME12-1030 | C-52-0304-CME12-1030: FS | 2025-01-18 07:00 | 2025-01-20 17:00
C-52-0304-CME12-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 | Section Tie-in Welding | C-52-0304-CME12-1020 | C-52-0304-CME12-1020: FS | C-52-0304-CME12-1040, C-52-0304-PL-ME-4810 | C-52-0304-CME12-1040: FS, C-52-0304-PL-ME-4810: FF 1 | 2025-01-21 07:00 | 2025-01-23 17:00
C-52-0304-CME12-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 | NDT (Tie-in Joint) | C-52-0304-CME12-1030 | C-52-0304-CME12-1030: FS | C-52-0304-CME12-1050 | C-52-0304-CME12-1050: FS | 2025-01-24 07:00 | 2025-01-27 17:00
C-52-0304-CME12-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME12-1040 | C-52-0304-CME12-1040: FS | C-52-0304-CME12-1060 | C-52-0304-CME12-1060: FS | 2025-01-28 07:00 | 2025-01-30 17:00
C-52-0304-CME12-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 | Holiday Testing | C-52-0304-CME12-1050 | C-52-0304-CME12-1050: FS | C-52-0304-CME12-1070 | C-52-0304-CME12-1070: FS | 2025-01-31 07:00 | 2025-02-01 17:00
C-52-0304-CME12-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 | Padding & Back Filling | C-52-0304-CME12-1060 | C-52-0304-CME12-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2025-02-03 07:00 | 2025-02-04 17:00
C-52-0304-CME10-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 | Road Diversion & Trench Excavation | C-52-0304-CME09-1000 | C-52-0304-CME09-1000: FS 1 | C-52-0304-CME10-1010, C-52-0304-CME11-1000 | C-52-0304-CME10-1010: FS, C-52-0304-CME11-1000: FS 1 | 2025-01-04 07:00 | 2025-01-08 17:00
C-52-0304-CME10-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 | Bedding | C-52-0304-CME10-1000 | C-52-0304-CME10-1000: FS | C-52-0304-CME10-1020 | C-52-0304-CME10-1020: FS | 2025-01-09 07:00 | 2025-01-10 17:00
C-52-0304-CME10-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 | Lowering | C-52-0304-CME10-1010, C-52-0304-CME09-1020 | C-52-0304-CME10-1010: FS, C-52-0304-CME09-1020: FS | C-52-0304-CME10-1030, C-52-0304-CME11-1020 | C-52-0304-CME10-1030: FS, C-52-0304-CME11-1020: FS | 2025-01-11 07:00 | 2025-01-13 17:00
C-52-0304-CME10-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 | Section Tie-in Welding | C-52-0304-CME10-1020 | C-52-0304-CME10-1020: FS | C-52-0304-CME10-1040, C-52-0304-PL-ME-4810 | C-52-0304-CME10-1040: FS, C-52-0304-PL-ME-4810: FF 1 | 2025-01-14 07:00 | 2025-01-16 17:00
C-52-0304-CME10-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 | NDT (Tie-in Joint) | C-52-0304-CME10-1030 | C-52-0304-CME10-1030: FS | C-52-0304-CME10-1050 | C-52-0304-CME10-1050: FS | 2025-01-17 07:00 | 2025-01-20 17:00
C-52-0304-CME10-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME10-1040 | C-52-0304-CME10-1040: FS | C-52-0304-CME10-1060 | C-52-0304-CME10-1060: FS | 2025-01-21 07:00 | 2025-01-23 17:00
C-52-0304-CME10-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 | Holiday Testing | C-52-0304-CME10-1050 | C-52-0304-CME10-1050: FS | C-52-0304-CME10-1070 | C-52-0304-CME10-1070: FS | 2025-01-24 07:00 | 2025-01-25 17:00
C-52-0304-CME10-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 | Padding & Back Filling | C-52-0304-CME10-1060 | C-52-0304-CME10-1060: FS | C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF 1, C-52-0304-PL-CI-6000: FF 1 | 2025-01-27 07:00 | 2025-01-29 17:00
C-52-0405-CMA01-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 | Trench Excavation | C-52-0405-PL-CI-2400 | C-52-0405-PL-CI-2400: SS | C-52-0405-CMA01-1010, C-52-0405-CMA25-1000 | C-52-0405-CMA01-1010: FS, C-52-0405-CMA25-1000: SS | 2025-01-29 12:00 | 2025-02-07 12:00
C-52-0405-CMA01-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 | Bedding | C-52-0405-CMA01-1000 | C-52-0405-CMA01-1000: FS | C-52-0405-CMA01-1020 | C-52-0405-CMA01-1020: FS | 2025-02-07 12:00 | 2025-02-08 12:00
C-52-0405-CMA01-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 | Lowering | C-52-0405-CMA01-1010 | C-52-0405-CMA01-1010: FS | C-52-0405-CMA01-1030 | C-52-0405-CMA01-1030: SS | 2025-02-08 12:00 | 2025-02-10 12:00
C-52-0405-CMA01-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 | Section Tie-in Welding | C-52-0405-CMA01-1020 | C-52-0405-CMA01-1020: SS | C-52-0405-CMA01-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA01-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-08 12:00 | 2025-02-11 12:00
C-52-0405-CMA01-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 | NDT (Tie-in Joint) | C-52-0405-CMA01-1030 | C-52-0405-CMA01-1030: SS 1 | C-52-0405-CMA01-1050 | C-52-0405-CMA01-1050: SS 1 | 2025-02-10 12:00 | 2025-02-12 12:00
C-52-0405-CMA01-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA01-1040 | C-52-0405-CMA01-1040: SS 1 | C-52-0405-CMA01-1060 | C-52-0405-CMA01-1060: FS | 2025-02-11 12:00 | 2025-02-13 12:00
C-52-0405-CMA01-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 | Holiday Testing | C-52-0405-CMA01-1050 | C-52-0405-CMA01-1050: FS | C-52-0405-CMA01-1070, C-52-0405-PL-CA-5220 | C-52-0405-CMA01-1070: FS, C-52-0405-PL-CA-5220: SS | 2025-02-13 12:00 | 2025-02-14 12:00
C-52-0405-CMA01-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 | Padding | C-52-0405-CMA01-1060 | C-52-0405-CMA01-1060: FS | C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-14 12:00 | 2025-02-15 12:00
C-52-0405-CMA25-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 | Trench Excavation | C-52-0405-CMA01-1000 | C-52-0405-CMA01-1000: SS | C-52-0405-CMA25-1010, C-52-0405-CMA20-1000 | C-52-0405-CMA25-1010: FF, C-52-0405-CMA20-1000: FS | 2025-01-29 12:00 | 2025-02-05 12:00
C-52-0405-CMA25-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 | Bedding | C-52-0405-CMA25-1000 | C-52-0405-CMA25-1000: FF | C-52-0405-CMA25-1020 | C-52-0405-CMA25-1020: FS | 2025-02-04 12:00 | 2025-02-05 12:00
C-52-0405-CMA25-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 | Lowering | C-52-0405-CMA25-1010 | C-52-0405-CMA25-1010: FS | C-52-0405-CMA25-1030 | C-52-0405-CMA25-1030: SS | 2025-02-05 12:00 | 2025-02-06 12:00
C-52-0405-CMA25-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 | Section Tie-in Welding | C-52-0405-CMA25-1020 | C-52-0405-CMA25-1020: SS | C-52-0405-CMA25-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA25-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-05 12:00 | 2025-02-07 12:00
C-52-0405-CMA25-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 | NDT (Tie-in Joint) | C-52-0405-CMA25-1030 | C-52-0405-CMA25-1030: SS 1 | C-52-0405-CMA25-1050 | C-52-0405-CMA25-1050: SS 1 | 2025-02-06 12:00 | 2025-02-08 12:00
C-52-0405-CMA25-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA25-1040 | C-52-0405-CMA25-1040: SS 1 | C-52-0405-CMA25-1060 | C-52-0405-CMA25-1060: FS | 2025-02-07 12:00 | 2025-02-10 12:00
C-52-0405-CMA25-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 | Holiday Testing | C-52-0405-CMA25-1050 | C-52-0405-CMA25-1050: FS | C-52-0405-CMA25-1070 | C-52-0405-CMA25-1070: FS | 2025-02-10 12:00 | 2025-02-11 12:00
C-52-0405-CMA25-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 | Padding | C-52-0405-CMA25-1060 | C-52-0405-CMA25-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-11 12:00 | 2025-02-12 12:00
C-52-0405-CMA20-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 | Trench Excavation | C-52-0405-CMA25-1000 | C-52-0405-CMA25-1000: FS | C-52-0405-CMA20-1010, C-52-0405-CMA26-1000 | C-52-0405-CMA20-1010: FF, C-52-0405-CMA26-1000: FS | 2025-02-05 12:00 | 2025-02-12 12:00
C-52-0405-CMA20-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 | Bedding | C-52-0405-CMA20-1000 | C-52-0405-CMA20-1000: FF | C-52-0405-CMA20-1020 | C-52-0405-CMA20-1020: FS | 2025-02-11 12:00 | 2025-02-12 12:00
C-52-0405-CMA20-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 | Lowering | C-52-0405-CMA20-1010 | C-52-0405-CMA20-1010: FS | C-52-0405-CMA20-1030 | C-52-0405-CMA20-1030: SS | 2025-02-12 12:00 | 2025-02-13 12:00
C-52-0405-CMA20-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 | Section Tie-in Welding | C-52-0405-CMA20-1020 | C-52-0405-CMA20-1020: SS | C-52-0405-CMA20-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA20-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-12 12:00 | 2025-02-14 12:00
C-52-0405-CMA20-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 | NDT (Tie-in Joint) | C-52-0405-CMA20-1030 | C-52-0405-CMA20-1030: SS 1 | C-52-0405-CMA20-1050 | C-52-0405-CMA20-1050: SS 1 | 2025-02-13 12:00 | 2025-02-15 12:00
C-52-0405-CMA20-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA20-1040 | C-52-0405-CMA20-1040: SS 1 | C-52-0405-CMA20-1060 | C-52-0405-CMA20-1060: FS | 2025-02-14 12:00 | 2025-02-17 12:00
C-52-0405-CMA20-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 | Holiday Testing | C-52-0405-CMA20-1050 | C-52-0405-CMA20-1050: FS | C-52-0405-CMA20-1070 | C-52-0405-CMA20-1070: FS | 2025-02-17 12:00 | 2025-02-18 12:00
C-52-0405-CMA20-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 | Padding | C-52-0405-CMA20-1060 | C-52-0405-CMA20-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-18 12:00 | 2025-02-19 12:00
C-52-0405-CMA26-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 | Trench Excavation | C-52-0405-CMA20-1000 | C-52-0405-CMA20-1000: FS | C-52-0405-CMA26-1010, C-52-0405-CMA21-1000 | C-52-0405-CMA26-1010: FF, C-52-0405-CMA21-1000: FS | 2025-02-12 12:00 | 2025-02-19 12:00
C-52-0405-CMA26-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 | Bedding | C-52-0405-CMA26-1000 | C-52-0405-CMA26-1000: FF | C-52-0405-CMA26-1020 | C-52-0405-CMA26-1020: FS | 2025-02-18 12:00 | 2025-02-19 12:00
C-52-0405-CMA26-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 | Lowering | C-52-0405-CMA26-1010 | C-52-0405-CMA26-1010: FS | C-52-0405-CMA26-1030 | C-52-0405-CMA26-1030: SS | 2025-02-19 12:00 | 2025-02-20 12:00
C-52-0405-CMA26-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 | Section Tie-in Welding | C-52-0405-CMA26-1020 | C-52-0405-CMA26-1020: SS | C-52-0405-CMA26-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA26-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-19 12:00 | 2025-02-21 12:00
C-52-0405-CMA26-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 | NDT (Tie-in Joint) | C-52-0405-CMA26-1030 | C-52-0405-CMA26-1030: SS 1 | C-52-0405-CMA26-1050 | C-52-0405-CMA26-1050: SS 1 | 2025-02-20 12:00 | 2025-02-22 12:00
C-52-0405-CMA26-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA26-1040 | C-52-0405-CMA26-1040: SS 1 | C-52-0405-CMA26-1060 | C-52-0405-CMA26-1060: FS | 2025-02-21 12:00 | 2025-02-24 12:00
C-52-0405-CMA26-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 | Holiday Testing | C-52-0405-CMA26-1050 | C-52-0405-CMA26-1050: FS | C-52-0405-CMA26-1070 | C-52-0405-CMA26-1070: FS | 2025-02-24 12:00 | 2025-02-25 12:00
C-52-0405-CMA26-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 | Padding | C-52-0405-CMA26-1060 | C-52-0405-CMA26-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-25 12:00 | 2025-02-26 12:00
C-52-0405-CMA21-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 | Trench Excavation | C-52-0405-CMA26-1000 | C-52-0405-CMA26-1000: FS | C-52-0405-CMA21-1010, C-52-0405-CMA02-0970 | C-52-0405-CMA21-1010: FF, C-52-0405-CMA02-0970: SS | 2025-02-19 12:00 | 2025-02-26 12:00
C-52-0405-CMA21-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 | Bedding | C-52-0405-CMA21-1000 | C-52-0405-CMA21-1000: FF | C-52-0405-CMA21-1020 | C-52-0405-CMA21-1020: FS | 2025-02-25 12:00 | 2025-02-26 12:00
C-52-0405-CMA21-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 | Lowering | C-52-0405-CMA21-1010 | C-52-0405-CMA21-1010: FS | C-52-0405-CMA21-1030 | C-52-0405-CMA21-1030: SS | 2025-02-26 12:00 | 2025-02-27 12:00
C-52-0405-CMA21-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 | Section Tie-in Welding | C-52-0405-CMA21-1020 | C-52-0405-CMA21-1020: SS | C-52-0405-CMA21-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA21-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-26 12:00 | 2025-02-28 12:00
C-52-0405-CMA21-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 | NDT (Tie-in Joint) | C-52-0405-CMA21-1030 | C-52-0405-CMA21-1030: SS 1 | C-52-0405-CMA21-1050 | C-52-0405-CMA21-1050: SS 1 | 2025-02-27 12:00 | 2025-03-01 12:00
C-52-0405-CMA21-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA21-1040 | C-52-0405-CMA21-1040: SS 1 | C-52-0405-CMA21-1060 | C-52-0405-CMA21-1060: FS | 2025-02-28 12:00 | 2025-03-02 12:00
C-52-0405-CMA21-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 | Holiday Testing | C-52-0405-CMA21-1050 | C-52-0405-CMA21-1050: FS | C-52-0405-CMA21-1070 | C-52-0405-CMA21-1070: FS | 2025-03-02 12:00 | 2025-03-04 10:00
C-52-0405-CMA21-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 | Padding | C-52-0405-CMA21-1060 | C-52-0405-CMA21-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-03-04 10:00 | 2025-03-06 08:00
C-52-0405-CMA27-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 | Trench Excavation | C-52-0405-PL-CI-2400 | C-52-0405-PL-CI-2400: SS | C-52-0405-CMA27-1010, C-52-0405-CMA30-0980 | C-52-0405-CMA27-1010: FF, C-52-0405-CMA30-0980: FS | 2025-01-29 12:00 | 2025-02-05 12:00
C-52-0405-CMA27-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 | Bedding | C-52-0405-CMA27-1000 | C-52-0405-CMA27-1000: FF | C-52-0405-CMA27-1020 | C-52-0405-CMA27-1020: FS | 2025-02-04 12:00 | 2025-02-05 12:00
C-52-0405-CMA27-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 | Lowering | C-52-0405-CMA27-1010 | C-52-0405-CMA27-1010: FS | C-52-0405-CMA27-1030 | C-52-0405-CMA27-1030: SS | 2025-02-05 12:00 | 2025-02-06 12:00
C-52-0405-CMA27-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 | Section Tie-in Welding | C-52-0405-CMA27-1020 | C-52-0405-CMA27-1020: SS | C-52-0405-CMA27-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA27-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-05 12:00 | 2025-02-07 12:00
C-52-0405-CMA27-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 | NDT (Tie-in Joint) | C-52-0405-CMA27-1030 | C-52-0405-CMA27-1030: SS 1 | C-52-0405-CMA27-1050 | C-52-0405-CMA27-1050: SS 1 | 2025-02-06 12:00 | 2025-02-08 12:00
C-52-0405-CMA27-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA27-1040 | C-52-0405-CMA27-1040: SS 1 | C-52-0405-CMA27-1060 | C-52-0405-CMA27-1060: FS | 2025-02-07 12:00 | 2025-02-10 12:00
C-52-0405-CMA27-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 | Holiday Testing | C-52-0405-CMA27-1050 | C-52-0405-CMA27-1050: FS | C-52-0405-CMA27-1070 | C-52-0405-CMA27-1070: FS | 2025-02-10 12:00 | 2025-02-11 12:00
C-52-0405-CMA27-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 | Padding | C-52-0405-CMA27-1060 | C-52-0405-CMA27-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-11 12:00 | 2025-02-12 12:00
C-52-0405-CMA22-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 | Excavation (Manual-Trial Pit) | C-52-0405-PL-CI-2400 | C-52-0405-PL-CI-2400: SS 30 | C-52-0405-CMA22-1010 | C-52-0405-CMA22-1010: FS | 2025-03-06 08:00 | 2025-03-21 10:00
C-52-0405-CMA22-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 | Sabkha Gatch Laying | C-52-0405-CMA22-1000 | C-52-0405-CMA22-1000: FS | C-52-0405-CMA22-1020 | C-52-0405-CMA22-1020: SS 1 | 2025-03-21 10:00 | 2025-03-29 08:00
C-52-0405-CMA22-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 | Sabka Gatch Compaction | C-52-0405-CMA22-1010 | C-52-0405-CMA22-1010: SS 1 | C-52-0405-CMA22-1030 | C-52-0405-CMA22-1030: FS | 2025-03-22 14:00 | 2025-04-03 08:00
C-52-0405-CMA22-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 | Trench Excavation | C-52-0405-CMA22-1020 | C-52-0405-CMA22-1020: FS | C-52-0405-CMA22-1040 | C-52-0405-CMA22-1040: FF | 2025-04-03 08:00 | 2025-04-05 08:00
C-52-0405-CMA22-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 | Bedding | C-52-0405-CMA22-1030 | C-52-0405-CMA22-1030: FF | C-52-0405-CMA22-1050 | C-52-0405-CMA22-1050: FS | 2025-04-04 08:00 | 2025-04-05 08:00
C-52-0405-CMA22-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 | Lowering | C-52-0405-CMA22-1040 | C-52-0405-CMA22-1040: FS | C-52-0405-CMA22-1060 | C-52-0405-CMA22-1060: SS | 2025-04-05 08:00 | 2025-04-07 08:00
C-52-0405-CMA22-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 | Section Tie-in Welding | C-52-0405-CMA22-1050 | C-52-0405-CMA22-1050: SS | C-52-0405-CMA22-1070, C-52-0405-PL-ME-4810 | C-52-0405-CMA22-1070: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-04-05 08:00 | 2025-04-08 08:00
C-52-0405-CMA22-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 | NDT (Tie-in Joint) | C-52-0405-CMA22-1060 | C-52-0405-CMA22-1060: SS 1 | C-52-0405-CMA22-1080 | C-52-0405-CMA22-1080: SS 1 | 2025-04-07 08:00 | 2025-04-09 08:00
C-52-0405-CMA22-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA22-1070 | C-52-0405-CMA22-1070: SS 1 | C-52-0405-CMA22-1090 | C-52-0405-CMA22-1090: FS | 2025-04-08 08:00 | 2025-04-10 08:00
C-52-0405-CMA22-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 | Holiday Testing | C-52-0405-CMA22-1080 | C-52-0405-CMA22-1080: FS | C-52-0405-CMA22-1100 | C-52-0405-CMA22-1100: FS | 2025-04-10 08:00 | 2025-04-11 08:00
C-52-0405-CMA22-1100 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 | Padding | C-52-0405-CMA22-1090 | C-52-0405-CMA22-1090: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-04-11 08:00 | 2025-04-12 08:00
C-52-0405-CMA02-0970 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 | Excavation (Manual-Trial Pit) | C-52-0405-CMA21-1000 | C-52-0405-CMA21-1000: SS | C-52-0405-CMA02-0980 | C-52-0405-CMA02-0980: FS | 2025-02-19 12:00 | 2025-02-28 12:00
C-52-0405-CMA02-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 | Sabkha Gatch Laying | C-52-0405-CMA02-0970 | C-52-0405-CMA02-0970: FS | C-52-0405-CMA02-0990 | C-52-0405-CMA02-0990: SS 1 | 2025-02-28 12:00 | 2025-03-07 12:00
C-52-0405-CMA02-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 | Sabka Gatch Compaction | C-52-0405-CMA02-0980 | C-52-0405-CMA02-0980: SS 1 | C-52-0405-CMA02-1000 | C-52-0405-CMA02-1000: FS | 2025-03-01 12:00 | 2025-03-08 16:00
C-52-0405-CMA02-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 | Trench Excavation | C-52-0405-CMA02-0990 | C-52-0405-CMA02-0990: FS | C-52-0405-CMA02-1010 | C-52-0405-CMA02-1010: FF | 2025-03-08 16:00 | 2025-03-12 08:00
C-52-0405-CMA02-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 | Bedding | C-52-0405-CMA02-1000 | C-52-0405-CMA02-1000: FF | C-52-0405-CMA02-1020 | C-52-0405-CMA02-1020: FS | 2025-03-10 10:00 | 2025-03-12 08:00
C-52-0405-CMA02-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 | Lowering | C-52-0405-CMA02-1010 | C-52-0405-CMA02-1010: FS | C-52-0405-CMA02-1030 | C-52-0405-CMA02-1030: SS | 2025-03-12 08:00 | 2025-03-13 12:00
C-52-0405-CMA02-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 | Section Tie-in Welding | C-52-0405-CMA02-1020 | C-52-0405-CMA02-1020: SS | C-52-0405-CMA02-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA02-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-03-12 08:00 | 2025-03-15 10:00
C-52-0405-CMA02-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 | NDT (Tie-in Joint) | C-52-0405-CMA02-1030 | C-52-0405-CMA02-1030: SS 1 | C-52-0405-CMA02-1050 | C-52-0405-CMA02-1050: SS 1 | 2025-03-13 12:00 | 2025-03-16 10:00
C-52-0405-CMA02-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA02-1040 | C-52-0405-CMA02-1040: SS 1 | C-52-0405-CMA02-1060 | C-52-0405-CMA02-1060: FS | 2025-03-15 10:00 | 2025-03-18 08:00
C-52-0405-CMA02-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 | Holiday Testing | C-52-0405-CMA02-1050 | C-52-0405-CMA02-1050: FS | C-52-0405-CMA02-1070 | C-52-0405-CMA02-1070: FS | 2025-03-18 08:00 | 2025-03-19 12:00
C-52-0405-CMA02-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 | Padding | C-52-0405-CMA02-1060 | C-52-0405-CMA02-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-03-19 12:00 | 2025-03-21 10:00
C-52-0405-CMA03-0970 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 | Excavation (Manual-Trial Pit) | C-52-0405-PL-CI-2400 | C-52-0405-PL-CI-2400: SS 3 | C-52-0405-CMA03-0980, C-52-0405-CMA28-0980 | C-52-0405-CMA03-0980: FS, C-52-0405-CMA28-0980: FS | 2025-02-01 12:00 | 2025-02-15 12:00
C-52-0405-CMA03-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 | Sabkha Gatch Laying | C-52-0405-CMA03-0970 | C-52-0405-CMA03-0970: FS | C-52-0405-CMA03-0990 | C-52-0405-CMA03-0990: SS 1 | 2025-02-15 12:00 | 2025-02-21 12:00
C-52-0405-CMA03-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 | Sabka Gatch Compaction | C-52-0405-CMA03-0980 | C-52-0405-CMA03-0980: SS 1 | C-52-0405-CMA03-1000 | C-52-0405-CMA03-1000: FS | 2025-02-17 12:00 | 2025-02-22 12:00
C-52-0405-CMA03-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 | Trench Excavation | C-52-0405-CMA03-0990 | C-52-0405-CMA03-0990: FS | C-52-0405-CMA03-1010 | C-52-0405-CMA03-1010: FF | 2025-02-22 12:00 | 2025-02-25 12:00
C-52-0405-CMA03-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 | Bedding | C-52-0405-CMA03-1000 | C-52-0405-CMA03-1000: FF | C-52-0405-CMA03-1020 | C-52-0405-CMA03-1020: FS | 2025-02-24 12:00 | 2025-02-25 12:00
C-52-0405-CMA03-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 | Lowering | C-52-0405-CMA03-1010 | C-52-0405-CMA03-1010: FS | C-52-0405-CMA03-1030 | C-52-0405-CMA03-1030: SS | 2025-02-25 12:00 | 2025-02-26 12:00
C-52-0405-CMA03-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 | Section Tie-in Welding | C-52-0405-CMA03-1020 | C-52-0405-CMA03-1020: SS | C-52-0405-CMA03-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA03-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-25 12:00 | 2025-02-27 12:00
C-52-0405-CMA03-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 | NDT (Tie-in Joint) | C-52-0405-CMA03-1030 | C-52-0405-CMA03-1030: SS 1 | C-52-0405-CMA03-1050 | C-52-0405-CMA03-1050: SS 1 | 2025-02-26 12:00 | 2025-02-28 12:00
C-52-0405-CMA03-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA03-1040 | C-52-0405-CMA03-1040: SS 1 | C-52-0405-CMA03-1060 | C-52-0405-CMA03-1060: FS | 2025-02-27 12:00 | 2025-03-01 12:00
C-52-0405-CMA03-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 | Holiday Testing | C-52-0405-CMA03-1050 | C-52-0405-CMA03-1050: FS | C-52-0405-CMA03-1070 | C-52-0405-CMA03-1070: FS | 2025-03-01 12:00 | 2025-03-02 12:00
C-52-0405-CMA03-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 | Padding | C-52-0405-CMA03-1060 | C-52-0405-CMA03-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-03-02 12:00 | 2025-03-04 10:00
C-52-0405-CMA28-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 | Sabkha Gatch Laying | C-52-0405-CMA03-0970 | C-52-0405-CMA03-0970: FS | C-52-0405-CMA28-0990, C-52-0405-CMA29-0980 | C-52-0405-CMA28-0990: SS 1, C-52-0405-CMA29-0980: FS | 2025-02-15 12:00 | 2025-02-21 12:00
C-52-0405-CMA28-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 | Sabka Gatch Compaction | C-52-0405-CMA28-0980 | C-52-0405-CMA28-0980: SS 1 | C-52-0405-CMA28-1000 | C-52-0405-CMA28-1000: FS | 2025-02-17 12:00 | 2025-02-22 12:00
C-52-0405-CMA28-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 | Trench Excavation | C-52-0405-CMA28-0990 | C-52-0405-CMA28-0990: FS | C-52-0405-CMA28-1010 | C-52-0405-CMA28-1010: FF | 2025-02-22 12:00 | 2025-02-25 12:00
C-52-0405-CMA28-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 | Bedding | C-52-0405-CMA28-1000 | C-52-0405-CMA28-1000: FF | C-52-0405-CMA28-1020 | C-52-0405-CMA28-1020: FS | 2025-02-24 12:00 | 2025-02-25 12:00
C-52-0405-CMA28-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 | Lowering | C-52-0405-CMA28-1010 | C-52-0405-CMA28-1010: FS | C-52-0405-CMA28-1030 | C-52-0405-CMA28-1030: SS | 2025-02-25 12:00 | 2025-02-26 12:00
C-52-0405-CMA28-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 | Section Tie-in Welding | C-52-0405-CMA28-1020 | C-52-0405-CMA28-1020: SS | C-52-0405-CMA28-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA28-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-25 12:00 | 2025-02-27 12:00
C-52-0405-CMA28-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 | NDT (Tie-in Joint) | C-52-0405-CMA28-1030 | C-52-0405-CMA28-1030: SS 1 | C-52-0405-CMA28-1050 | C-52-0405-CMA28-1050: SS 1 | 2025-02-26 12:00 | 2025-02-28 12:00
C-52-0405-CMA28-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA28-1040 | C-52-0405-CMA28-1040: SS 1 | C-52-0405-CMA28-1060 | C-52-0405-CMA28-1060: FS | 2025-02-27 12:00 | 2025-03-01 12:00
C-52-0405-CMA28-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 | Holiday Testing | C-52-0405-CMA28-1050 | C-52-0405-CMA28-1050: FS | C-52-0405-CMA28-1070 | C-52-0405-CMA28-1070: FS | 2025-03-01 12:00 | 2025-03-02 12:00
C-52-0405-CMA28-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 | Padding | C-52-0405-CMA28-1060 | C-52-0405-CMA28-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-03-02 12:00 | 2025-03-04 10:00
C-52-0405-CMA29-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 | Sabkha Gatch Laying | C-52-0405-CMA28-0980 | C-52-0405-CMA28-0980: FS | C-52-0405-CMA29-0990 | C-52-0405-CMA29-0990: SS 1 | 2025-02-21 12:00 | 2025-02-27 12:00
C-52-0405-CMA29-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 | Sabka Gatch Compaction | C-52-0405-CMA29-0980 | C-52-0405-CMA29-0980: SS 1 | C-52-0405-CMA29-1000 | C-52-0405-CMA29-1000: FS | 2025-02-22 12:00 | 2025-02-28 12:00
C-52-0405-CMA29-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 | Trench Excavation | C-52-0405-CMA29-0990 | C-52-0405-CMA29-0990: FS | C-52-0405-CMA29-1010 | C-52-0405-CMA29-1010: FF | 2025-02-28 12:00 | 2025-03-02 12:00
C-52-0405-CMA29-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 | Bedding | C-52-0405-CMA29-1000 | C-52-0405-CMA29-1000: FF | C-52-0405-CMA29-1020 | C-52-0405-CMA29-1020: FS | 2025-03-01 12:00 | 2025-03-02 12:00
C-52-0405-CMA29-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 | Lowering | C-52-0405-CMA29-1010 | C-52-0405-CMA29-1010: FS | C-52-0405-CMA29-1030 | C-52-0405-CMA29-1030: SS | 2025-03-02 12:00 | 2025-03-04 10:00
C-52-0405-CMA29-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 | Section Tie-in Welding | C-52-0405-CMA29-1020 | C-52-0405-CMA29-1020: SS | C-52-0405-CMA29-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA29-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-03-02 12:00 | 2025-03-06 08:00
C-52-0405-CMA29-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 | NDT (Tie-in Joint) | C-52-0405-CMA29-1030 | C-52-0405-CMA29-1030: SS 1 | C-52-0405-CMA29-1050 | C-52-0405-CMA29-1050: SS 1 | 2025-03-04 10:00 | 2025-03-07 12:00
C-52-0405-CMA29-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA29-1040 | C-52-0405-CMA29-1040: SS 1 | C-52-0405-CMA29-1060 | C-52-0405-CMA29-1060: FS | 2025-03-06 08:00 | 2025-03-08 16:00
C-52-0405-CMA29-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 | Holiday Testing | C-52-0405-CMA29-1050 | C-52-0405-CMA29-1050: FS | C-52-0405-CMA29-1070 | C-52-0405-CMA29-1070: FS | 2025-03-08 16:00 | 2025-03-10 10:00
C-52-0405-CMA29-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 | Padding | C-52-0405-CMA29-1060 | C-52-0405-CMA29-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-03-10 10:00 | 2025-03-12 08:00
C-52-0405-CMA30-0980 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 | Sabkha Gatch Laying | C-52-0405-CMA27-1000 | C-52-0405-CMA27-1000: FS | C-52-0405-CMA30-0990 | C-52-0405-CMA30-0990: SS 1 | 2025-02-05 12:00 | 2025-02-11 12:00
C-52-0405-CMA30-0990 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 | Sabka Gatch Compaction | C-52-0405-CMA30-0980 | C-52-0405-CMA30-0980: SS 1 | C-52-0405-CMA30-1000 | C-52-0405-CMA30-1000: FS | 2025-02-06 12:00 | 2025-02-12 12:00
C-52-0405-CMA30-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 | Trench Excavation | C-52-0405-CMA30-0990 | C-52-0405-CMA30-0990: FS | C-52-0405-CMA30-1010 | C-52-0405-CMA30-1010: FF | 2025-02-12 12:00 | 2025-02-14 12:00
C-52-0405-CMA30-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 | Bedding | C-52-0405-CMA30-1000 | C-52-0405-CMA30-1000: FF | C-52-0405-CMA30-1020 | C-52-0405-CMA30-1020: FS | 2025-02-13 12:00 | 2025-02-14 12:00
C-52-0405-CMA30-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 | Lowering | C-52-0405-CMA30-1010 | C-52-0405-CMA30-1010: FS | C-52-0405-CMA30-1030 | C-52-0405-CMA30-1030: SS | 2025-02-14 12:00 | 2025-02-15 12:00
C-52-0405-CMA30-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 | Section Tie-in Welding | C-52-0405-CMA30-1020 | C-52-0405-CMA30-1020: SS | C-52-0405-CMA30-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA30-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-14 12:00 | 2025-02-17 12:00
C-52-0405-CMA30-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 | NDT (Tie-in Joint) | C-52-0405-CMA30-1030 | C-52-0405-CMA30-1030: SS 1 | C-52-0405-CMA30-1050 | C-52-0405-CMA30-1050: SS 1 | 2025-02-15 12:00 | 2025-02-18 12:00
C-52-0405-CMA30-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA30-1040 | C-52-0405-CMA30-1040: SS 1 | C-52-0405-CMA30-1060 | C-52-0405-CMA30-1060: FS | 2025-02-17 12:00 | 2025-02-19 12:00
C-52-0405-CMA30-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 | Holiday Testing | C-52-0405-CMA30-1050 | C-52-0405-CMA30-1050: FS | C-52-0405-CMA30-1070 | C-52-0405-CMA30-1070: FS | 2025-02-19 12:00 | 2025-02-20 12:00
C-52-0405-CMA30-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 | Padding | C-52-0405-CMA30-1060 | C-52-0405-CMA30-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-20 12:00 | 2025-02-21 12:00
C-52-0405-CMA23-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 | Excavation (Manual-Trial Pit) | C-52-0405-PL-CI-2400, C-52-0405-PL-CI-2400 | C-52-0405-PL-CI-2400: SS, C-52-0405-PL-CI-2400: FF | C-52-0405-CMA23-1010, C-52-0405-CMA04-1000 | C-52-0405-CMA23-1010: FS, C-52-0405-CMA04-1000: FS | 2025-02-13 12:00 | 2025-02-27 12:00
C-52-0405-CMA23-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 | Sabkha Gatch Laying | C-52-0405-CMA23-1000 | C-52-0405-CMA23-1000: FS | C-52-0405-CMA23-1020 | C-52-0405-CMA23-1020: SS 1 | 2025-02-27 12:00 | 2025-03-06 08:00
C-52-0405-CMA23-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 | Sabka Gatch Compaction | C-52-0405-CMA23-1010 | C-52-0405-CMA23-1010: SS 1 | C-52-0405-CMA23-1030 | C-52-0405-CMA23-1030: FS | 2025-02-28 12:00 | 2025-03-07 12:00
C-52-0405-CMA23-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 | Trench Excavation | C-52-0405-CMA23-1020 | C-52-0405-CMA23-1020: FS | C-52-0405-CMA23-1040 | C-52-0405-CMA23-1040: FF | 2025-03-07 12:00 | 2025-03-10 10:00
C-52-0405-CMA23-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 | Bedding | C-52-0405-CMA23-1030 | C-52-0405-CMA23-1030: FF | C-52-0405-CMA23-1050 | C-52-0405-CMA23-1050: FS | 2025-03-08 16:00 | 2025-03-10 10:00
C-52-0405-CMA23-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 | Lowering | C-52-0405-CMA23-1040 | C-52-0405-CMA23-1040: FS | C-52-0405-CMA23-1060 | C-52-0405-CMA23-1060: SS | 2025-03-10 10:00 | 2025-03-12 08:00
C-52-0405-CMA23-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 | Section Tie-in Welding | C-52-0405-CMA23-1050 | C-52-0405-CMA23-1050: SS | C-52-0405-CMA23-1070, C-52-0405-PL-ME-4810 | C-52-0405-CMA23-1070: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-03-10 10:00 | 2025-03-13 12:00
C-52-0405-CMA23-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 | NDT (Tie-in Joint) | C-52-0405-CMA23-1060 | C-52-0405-CMA23-1060: SS 1 | C-52-0405-CMA23-1080 | C-52-0405-CMA23-1080: SS 1 | 2025-03-12 08:00 | 2025-03-15 10:00
C-52-0405-CMA23-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA23-1070 | C-52-0405-CMA23-1070: SS 1 | C-52-0405-CMA23-1090 | C-52-0405-CMA23-1090: FS | 2025-03-13 12:00 | 2025-03-16 10:00
C-52-0405-CMA23-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 | Holiday Testing | C-52-0405-CMA23-1080 | C-52-0405-CMA23-1080: FS | C-52-0405-CMA23-1100 | C-52-0405-CMA23-1100: FS | 2025-03-16 10:00 | 2025-03-18 08:00
C-52-0405-CMA23-1100 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 | Padding | C-52-0405-CMA23-1090 | C-52-0405-CMA23-1090: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-03-18 08:00 | 2025-03-19 12:00
C-52-0405-CMA31-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 | Trench Excavation | C-52-0405-CME06-1000 | C-52-0405-CME06-1000: FS | C-52-0405-CMA31-1010, C-52-0405-CMA05-1000 | C-52-0405-CMA31-1010: FF, C-52-0405-CMA05-1000: FS | 2025-01-03 12:00 | 2025-01-10 12:00
C-52-0405-CMA31-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 | Bedding | C-52-0405-CMA31-1000 | C-52-0405-CMA31-1000: FF | C-52-0405-CMA31-1020 | C-52-0405-CMA31-1020: FS | 2025-01-09 12:00 | 2025-01-10 12:00
C-52-0405-CMA31-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 | Lowering | C-52-0405-CMA31-1010 | C-52-0405-CMA31-1010: FS | C-52-0405-CMA31-1030 | C-52-0405-CMA31-1030: SS | 2025-01-10 12:00 | 2025-01-11 12:00
C-52-0405-CMA31-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 | Section Tie-in Welding | C-52-0405-CMA31-1020 | C-52-0405-CMA31-1020: SS | C-52-0405-CMA31-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA31-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-01-10 12:00 | 2025-01-13 12:00
C-52-0405-CMA31-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 | NDT (Tie-in Joint) | C-52-0405-CMA31-1030 | C-52-0405-CMA31-1030: SS 1 | C-52-0405-CMA31-1050 | C-52-0405-CMA31-1050: SS 1 | 2025-01-11 12:00 | 2025-01-14 12:00
C-52-0405-CMA31-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA31-1040 | C-52-0405-CMA31-1040: SS 1 | C-52-0405-CMA31-1060 | C-52-0405-CMA31-1060: FS | 2025-01-13 12:00 | 2025-01-15 12:00
C-52-0405-CMA31-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 | Holiday Testing | C-52-0405-CMA31-1050 | C-52-0405-CMA31-1050: FS | C-52-0405-CMA31-1070 | C-52-0405-CMA31-1070: FS | 2025-01-15 12:00 | 2025-01-16 12:00
C-52-0405-CMA31-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 | Padding | C-52-0405-CMA31-1060 | C-52-0405-CMA31-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-01-16 12:00 | 2025-01-17 12:00
C-52-0405-CMA04-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 | Trench Excavation | C-52-0405-CMA23-1000 | C-52-0405-CMA23-1000: FS | C-52-0405-CMA04-1010, C-52-0405-CMA06-1000 | C-52-0405-CMA04-1010: FF, C-52-0405-CMA06-1000: FS | 2025-02-27 12:00 | 2025-03-10 10:00
C-52-0405-CMA04-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 | Bedding | C-52-0405-CMA04-1000 | C-52-0405-CMA04-1000: FF | C-52-0405-CMA04-1020 | C-52-0405-CMA04-1020: FS | 2025-03-08 16:00 | 2025-03-10 10:00
C-52-0405-CMA04-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 | Lowering | C-52-0405-CMA04-1010 | C-52-0405-CMA04-1010: FS | C-52-0405-CMA04-1030 | C-52-0405-CMA04-1030: SS | 2025-03-10 10:00 | 2025-03-12 08:00
C-52-0405-CMA04-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 | Section Tie-in Welding | C-52-0405-CMA04-1020 | C-52-0405-CMA04-1020: SS | C-52-0405-CMA04-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA04-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-03-10 10:00 | 2025-03-13 12:00
C-52-0405-CMA04-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 | NDT (Tie-in Joint) | C-52-0405-CMA04-1030 | C-52-0405-CMA04-1030: SS 1 | C-52-0405-CMA04-1050 | C-52-0405-CMA04-1050: SS 1 | 2025-03-12 08:00 | 2025-03-15 10:00
C-52-0405-CMA04-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA04-1040 | C-52-0405-CMA04-1040: SS 1 | C-52-0405-CMA04-1060 | C-52-0405-CMA04-1060: FS | 2025-03-13 12:00 | 2025-03-16 10:00
C-52-0405-CMA04-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 | Holiday Testing | C-52-0405-CMA04-1050 | C-52-0405-CMA04-1050: FS | C-52-0405-CMA04-1070 | C-52-0405-CMA04-1070: FS | 2025-03-16 10:00 | 2025-03-18 08:00
C-52-0405-CMA04-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 | Padding | C-52-0405-CMA04-1060 | C-52-0405-CMA04-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-03-18 08:00 | 2025-03-19 12:00
C-52-0405-CMA05-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 | Trench Excavation | C-52-0405-CMA31-1000 | C-52-0405-CMA31-1000: FS | C-52-0405-CMA05-1010, C-52-0405-CMA07-1000 | C-52-0405-CMA05-1010: FF, C-52-0405-CMA07-1000: FS | 2025-01-10 12:00 | 2025-01-17 12:00
C-52-0405-CMA05-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 | Bedding | C-52-0405-CMA05-1000 | C-52-0405-CMA05-1000: FF | C-52-0405-CMA05-1020 | C-52-0405-CMA05-1020: FS | 2025-01-16 12:00 | 2025-01-17 12:00
C-52-0405-CMA05-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 | Lowering | C-52-0405-CMA05-1010 | C-52-0405-CMA05-1010: FS | C-52-0405-CMA05-1030 | C-52-0405-CMA05-1030: SS | 2025-01-17 12:00 | 2025-01-18 12:00
C-52-0405-CMA05-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 | Section Tie-in Welding | C-52-0405-CMA05-1020 | C-52-0405-CMA05-1020: SS | C-52-0405-CMA05-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA05-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-01-17 12:00 | 2025-01-20 12:00
C-52-0405-CMA05-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 | NDT (Tie-in Joint) | C-52-0405-CMA05-1030 | C-52-0405-CMA05-1030: SS 1 | C-52-0405-CMA05-1050 | C-52-0405-CMA05-1050: SS 1 | 2025-01-18 12:00 | 2025-01-21 12:00
C-52-0405-CMA05-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA05-1040 | C-52-0405-CMA05-1040: SS 1 | C-52-0405-CMA05-1060 | C-52-0405-CMA05-1060: FS | 2025-01-20 12:00 | 2025-01-22 12:00
C-52-0405-CMA05-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 | Holiday Testing | C-52-0405-CMA05-1050 | C-52-0405-CMA05-1050: FS | C-52-0405-CMA05-1070 | C-52-0405-CMA05-1070: FS | 2025-01-22 12:00 | 2025-01-23 12:00
C-52-0405-CMA05-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 | Padding | C-52-0405-CMA05-1060 | C-52-0405-CMA05-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-01-23 12:00 | 2025-01-24 12:00
C-52-0405-CMA06-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 | Trench Excavation | C-52-0405-CMA04-1000 | C-52-0405-CMA04-1000: FS | C-52-0405-CMA06-1010 | C-52-0405-CMA06-1010: FF | 2025-03-10 10:00 | 2025-03-22 14:00
C-52-0405-CMA06-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 | Bedding | C-52-0405-CMA06-1000 | C-52-0405-CMA06-1000: FF | C-52-0405-CMA06-1020 | C-52-0405-CMA06-1020: FS | 2025-03-21 10:00 | 2025-03-22 14:00
C-52-0405-CMA06-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 | Lowering | C-52-0405-CMA06-1010 | C-52-0405-CMA06-1010: FS | C-52-0405-CMA06-1030 | C-52-0405-CMA06-1030: SS | 2025-03-22 14:00 | 2025-03-24 08:00
C-52-0405-CMA06-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 | Section Tie-in Welding | C-52-0405-CMA06-1020 | C-52-0405-CMA06-1020: SS | C-52-0405-CMA06-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA06-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-03-22 14:00 | 2025-03-25 12:00
C-52-0405-CMA06-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 | NDT (Tie-in Joint) | C-52-0405-CMA06-1030 | C-52-0405-CMA06-1030: SS 1 | C-52-0405-CMA06-1050 | C-52-0405-CMA06-1050: SS 1 | 2025-03-24 08:00 | 2025-03-27 10:00
C-52-0405-CMA06-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA06-1040 | C-52-0405-CMA06-1040: SS 1 | C-52-0405-CMA06-1060 | C-52-0405-CMA06-1060: FS | 2025-03-25 12:00 | 2025-03-29 08:00
C-52-0405-CMA06-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 | Holiday Testing | C-52-0405-CMA06-1050 | C-52-0405-CMA06-1050: FS | C-52-0405-CMA06-1070 | C-52-0405-CMA06-1070: FS | 2025-03-29 08:00 | 2025-04-03 08:00
C-52-0405-CMA06-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 | Padding | C-52-0405-CMA06-1060 | C-52-0405-CMA06-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-04-03 08:00 | 2025-04-04 08:00
C-52-0405-CMA07-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 | Trench Excavation | C-52-0405-CMA05-1000 | C-52-0405-CMA05-1000: FS | C-52-0405-CMA07-1010, C-52-0405-CMA09-1000 | C-52-0405-CMA07-1010: FF, C-52-0405-CMA09-1000: FS | 2025-01-17 12:00 | 2025-01-24 12:00
C-52-0405-CMA07-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 | Bedding | C-52-0405-CMA07-1000 | C-52-0405-CMA07-1000: FF | C-52-0405-CMA07-1020 | C-52-0405-CMA07-1020: FS | 2025-01-23 12:00 | 2025-01-24 12:00
C-52-0405-CMA07-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 | Lowering | C-52-0405-CMA07-1010 | C-52-0405-CMA07-1010: FS | C-52-0405-CMA07-1030 | C-52-0405-CMA07-1030: SS | 2025-01-24 12:00 | 2025-01-25 12:00
C-52-0405-CMA07-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 | Section Tie-in Welding | C-52-0405-CMA07-1020 | C-52-0405-CMA07-1020: SS | C-52-0405-CMA07-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA07-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-01-24 12:00 | 2025-01-27 12:00
C-52-0405-CMA07-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 | NDT (Tie-in Joint) | C-52-0405-CMA07-1030 | C-52-0405-CMA07-1030: SS 1 | C-52-0405-CMA07-1050 | C-52-0405-CMA07-1050: SS 1 | 2025-01-25 12:00 | 2025-01-28 12:00
C-52-0405-CMA07-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA07-1040 | C-52-0405-CMA07-1040: SS 1 | C-52-0405-CMA07-1060 | C-52-0405-CMA07-1060: FS | 2025-01-27 12:00 | 2025-01-29 12:00
C-52-0405-CMA07-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 | Holiday Testing | C-52-0405-CMA07-1050 | C-52-0405-CMA07-1050: FS | C-52-0405-CMA07-1070 | C-52-0405-CMA07-1070: FS | 2025-01-29 12:00 | 2025-01-30 12:00
C-52-0405-CMA07-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 | Padding | C-52-0405-CMA07-1060 | C-52-0405-CMA07-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-01-30 12:00 | 2025-01-31 12:00
C-52-0405-CMA08-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 | Trench Excavation | C-52-0405-PL-CI-2400 | C-52-0405-PL-CI-2400: SS | C-52-0405-CMA08-1010, C-52-0405-CMA10-1000 | C-52-0405-CMA08-1010: FF, C-52-0405-CMA10-1000: FS | 2025-01-29 12:00 | 2025-02-05 12:00
C-52-0405-CMA08-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 | Bedding | C-52-0405-CMA08-1000 | C-52-0405-CMA08-1000: FF | C-52-0405-CMA08-1020 | C-52-0405-CMA08-1020: FS | 2025-02-04 12:00 | 2025-02-05 12:00
C-52-0405-CMA08-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 | Lowering | C-52-0405-CMA08-1010 | C-52-0405-CMA08-1010: FS | C-52-0405-CMA08-1030 | C-52-0405-CMA08-1030: SS | 2025-02-05 12:00 | 2025-02-06 12:00
C-52-0405-CMA08-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 | Section Tie-in Welding | C-52-0405-CMA08-1020 | C-52-0405-CMA08-1020: SS | C-52-0405-CMA08-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA08-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-05 12:00 | 2025-02-07 12:00
C-52-0405-CMA08-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 | NDT (Tie-in Joint) | C-52-0405-CMA08-1030 | C-52-0405-CMA08-1030: SS 1 | C-52-0405-CMA08-1050 | C-52-0405-CMA08-1050: SS 1 | 2025-02-06 12:00 | 2025-02-08 12:00
C-52-0405-CMA08-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA08-1040 | C-52-0405-CMA08-1040: SS 1 | C-52-0405-CMA08-1060 | C-52-0405-CMA08-1060: FS | 2025-02-07 12:00 | 2025-02-10 12:00
C-52-0405-CMA08-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 | Holiday Testing | C-52-0405-CMA08-1050 | C-52-0405-CMA08-1050: FS | C-52-0405-CMA08-1070 | C-52-0405-CMA08-1070: FS | 2025-02-10 12:00 | 2025-02-11 12:00
C-52-0405-CMA08-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 | Padding | C-52-0405-CMA08-1060 | C-52-0405-CMA08-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-11 12:00 | 2025-02-12 12:00
C-52-0405-CMA09-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 | Trench Excavation | C-52-0405-CMA07-1000 | C-52-0405-CMA07-1000: FS | C-52-0405-CMA09-1010, C-52-0405-CMA11-1000 | C-52-0405-CMA09-1010: FF, C-52-0405-CMA11-1000: FS | 2025-01-24 12:00 | 2025-01-31 12:00
C-52-0405-CMA09-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 | Bedding | C-52-0405-CMA09-1000 | C-52-0405-CMA09-1000: FF | C-52-0405-CMA09-1020 | C-52-0405-CMA09-1020: FS | 2025-01-30 12:00 | 2025-01-31 12:00
C-52-0405-CMA09-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 | Lowering | C-52-0405-CMA09-1010 | C-52-0405-CMA09-1010: FS | C-52-0405-CMA09-1030 | C-52-0405-CMA09-1030: SS | 2025-01-31 12:00 | 2025-02-01 12:00
C-52-0405-CMA09-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 | Section Tie-in Welding | C-52-0405-CMA09-1020 | C-52-0405-CMA09-1020: SS | C-52-0405-CMA09-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA09-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-01-31 12:00 | 2025-02-03 12:00
C-52-0405-CMA09-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 | NDT (Tie-in Joint) | C-52-0405-CMA09-1030 | C-52-0405-CMA09-1030: SS 1 | C-52-0405-CMA09-1050 | C-52-0405-CMA09-1050: SS 1 | 2025-02-01 12:00 | 2025-02-04 12:00
C-52-0405-CMA09-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA09-1040 | C-52-0405-CMA09-1040: SS 1 | C-52-0405-CMA09-1060 | C-52-0405-CMA09-1060: FS | 2025-02-03 12:00 | 2025-02-05 12:00
C-52-0405-CMA09-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 | Holiday Testing | C-52-0405-CMA09-1050 | C-52-0405-CMA09-1050: FS | C-52-0405-CMA09-1070 | C-52-0405-CMA09-1070: FS | 2025-02-05 12:00 | 2025-02-06 12:00
C-52-0405-CMA09-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 | Padding | C-52-0405-CMA09-1060 | C-52-0405-CMA09-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-06 12:00 | 2025-02-07 12:00
C-52-0405-CMA10-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 | Trench Excavation | C-52-0405-CMA08-1000 | C-52-0405-CMA08-1000: FS | C-52-0405-CMA10-1010, C-52-0405-CMA12-1000 | C-52-0405-CMA10-1010: FF, C-52-0405-CMA12-1000: FS | 2025-02-05 12:00 | 2025-02-14 12:00
C-52-0405-CMA10-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 | Bedding | C-52-0405-CMA10-1000 | C-52-0405-CMA10-1000: FF | C-52-0405-CMA10-1020 | C-52-0405-CMA10-1020: FS | 2025-02-13 12:00 | 2025-02-14 12:00
C-52-0405-CMA10-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 | Lowering | C-52-0405-CMA10-1010 | C-52-0405-CMA10-1010: FS | C-52-0405-CMA10-1030 | C-52-0405-CMA10-1030: SS | 2025-02-14 12:00 | 2025-02-15 12:00
C-52-0405-CMA10-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 | Section Tie-in Welding | C-52-0405-CMA10-1020 | C-52-0405-CMA10-1020: SS | C-52-0405-CMA10-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA10-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-14 12:00 | 2025-02-17 12:00
C-52-0405-CMA10-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 | NDT (Tie-in Joint) | C-52-0405-CMA10-1030 | C-52-0405-CMA10-1030: SS 1 | C-52-0405-CMA10-1050 | C-52-0405-CMA10-1050: SS 1 | 2025-02-15 12:00 | 2025-02-18 12:00
C-52-0405-CMA10-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA10-1040 | C-52-0405-CMA10-1040: SS 1 | C-52-0405-CMA10-1060 | C-52-0405-CMA10-1060: FS | 2025-02-17 12:00 | 2025-02-19 12:00
C-52-0405-CMA10-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 | Holiday Testing | C-52-0405-CMA10-1050 | C-52-0405-CMA10-1050: FS | C-52-0405-CMA10-1070 | C-52-0405-CMA10-1070: FS | 2025-02-19 12:00 | 2025-02-20 12:00
C-52-0405-CMA10-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 | Padding | C-52-0405-CMA10-1060 | C-52-0405-CMA10-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-20 12:00 | 2025-02-21 12:00
C-52-0405-CMA11-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 | Trench Excavation | C-52-0405-CMA09-1000 | C-52-0405-CMA09-1000: FS | C-52-0405-CMA11-1010, C-52-0405-CMA13-1000 | C-52-0405-CMA11-1010: FF, C-52-0405-CMA13-1000: FS | 2025-01-31 12:00 | 2025-02-07 12:00
C-52-0405-CMA11-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 | Bedding | C-52-0405-CMA11-1000 | C-52-0405-CMA11-1000: FF | C-52-0405-CMA11-1020 | C-52-0405-CMA11-1020: FS | 2025-02-06 12:00 | 2025-02-07 12:00
C-52-0405-CMA11-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 | Lowering | C-52-0405-CMA11-1010 | C-52-0405-CMA11-1010: FS | C-52-0405-CMA11-1030 | C-52-0405-CMA11-1030: SS | 2025-02-07 12:00 | 2025-02-08 12:00
C-52-0405-CMA11-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 | Section Tie-in Welding | C-52-0405-CMA11-1020 | C-52-0405-CMA11-1020: SS | C-52-0405-CMA11-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA11-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-07 12:00 | 2025-02-10 12:00
C-52-0405-CMA11-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 | NDT (Tie-in Joint) | C-52-0405-CMA11-1030 | C-52-0405-CMA11-1030: SS 1 | C-52-0405-CMA11-1050 | C-52-0405-CMA11-1050: SS 1 | 2025-02-08 12:00 | 2025-02-11 12:00
C-52-0405-CMA11-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA11-1040 | C-52-0405-CMA11-1040: SS 1 | C-52-0405-CMA11-1060 | C-52-0405-CMA11-1060: FS | 2025-02-10 12:00 | 2025-02-12 12:00
C-52-0405-CMA11-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 | Holiday Testing | C-52-0405-CMA11-1050 | C-52-0405-CMA11-1050: FS | C-52-0405-CMA11-1070 | C-52-0405-CMA11-1070: FS | 2025-02-12 12:00 | 2025-02-13 12:00
C-52-0405-CMA11-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 | Padding | C-52-0405-CMA11-1060 | C-52-0405-CMA11-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-13 12:00 | 2025-02-14 12:00
C-52-0405-CMA12-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 | Trench Excavation | C-52-0405-CMA10-1000 | C-52-0405-CMA10-1000: FS | C-52-0405-CMA12-1010, C-52-0405-CMA14-1000 | C-52-0405-CMA12-1010: FF, C-52-0405-CMA14-1000: SS | 2025-02-14 12:00 | 2025-02-21 12:00
C-52-0405-CMA12-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 | Bedding | C-52-0405-CMA12-1000 | C-52-0405-CMA12-1000: FF | C-52-0405-CMA12-1020 | C-52-0405-CMA12-1020: FS | 2025-02-20 12:00 | 2025-02-21 12:00
C-52-0405-CMA12-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 | Lowering | C-52-0405-CMA12-1010 | C-52-0405-CMA12-1010: FS | C-52-0405-CMA12-1030 | C-52-0405-CMA12-1030: SS | 2025-02-21 12:00 | 2025-02-22 12:00
C-52-0405-CMA12-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 | Section Tie-in Welding | C-52-0405-CMA12-1020 | C-52-0405-CMA12-1020: SS | C-52-0405-CMA12-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA12-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-21 12:00 | 2025-02-24 12:00
C-52-0405-CMA12-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 | NDT (Tie-in Joint) | C-52-0405-CMA12-1030 | C-52-0405-CMA12-1030: SS 1 | C-52-0405-CMA12-1050 | C-52-0405-CMA12-1050: SS 1 | 2025-02-22 12:00 | 2025-02-25 12:00
C-52-0405-CMA12-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA12-1040 | C-52-0405-CMA12-1040: SS 1 | C-52-0405-CMA12-1060 | C-52-0405-CMA12-1060: FS | 2025-02-24 12:00 | 2025-02-26 12:00
C-52-0405-CMA12-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 | Holiday Testing | C-52-0405-CMA12-1050 | C-52-0405-CMA12-1050: FS | C-52-0405-CMA12-1070 | C-52-0405-CMA12-1070: FS | 2025-02-26 12:00 | 2025-02-27 12:00
C-52-0405-CMA12-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 | Padding | C-52-0405-CMA12-1060 | C-52-0405-CMA12-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-27 12:00 | 2025-02-28 12:00
C-52-0405-CMA13-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 | Trench Excavation | C-52-0405-CMA11-1000 | C-52-0405-CMA11-1000: FS | C-52-0405-CMA13-1010, C-52-0405-CMA15-1000, C-52-0405-CMA15-1000 | C-52-0405-CMA13-1010: FF, C-52-0405-CMA15-1000: SS, C-52-0405-CMA15-1000: FF | 2025-02-07 12:00 | 2025-02-14 12:00
C-52-0405-CMA13-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 | Bedding | C-52-0405-CMA13-1000 | C-52-0405-CMA13-1000: FF | C-52-0405-CMA13-1020 | C-52-0405-CMA13-1020: FS | 2025-02-13 12:00 | 2025-02-14 12:00
C-52-0405-CMA13-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 | Lowering | C-52-0405-CMA13-1010 | C-52-0405-CMA13-1010: FS | C-52-0405-CMA13-1030 | C-52-0405-CMA13-1030: SS | 2025-02-14 12:00 | 2025-02-15 12:00
C-52-0405-CMA13-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 | Section Tie-in Welding | C-52-0405-CMA13-1020 | C-52-0405-CMA13-1020: SS | C-52-0405-CMA13-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA13-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-14 12:00 | 2025-02-17 12:00
C-52-0405-CMA13-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 | NDT (Tie-in Joint) | C-52-0405-CMA13-1030 | C-52-0405-CMA13-1030: SS 1 | C-52-0405-CMA13-1050 | C-52-0405-CMA13-1050: SS 1 | 2025-02-15 12:00 | 2025-02-18 12:00
C-52-0405-CMA13-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA13-1040 | C-52-0405-CMA13-1040: SS 1 | C-52-0405-CMA13-1060 | C-52-0405-CMA13-1060: FS | 2025-02-17 12:00 | 2025-02-19 12:00
C-52-0405-CMA13-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 | Holiday Testing | C-52-0405-CMA13-1050 | C-52-0405-CMA13-1050: FS | C-52-0405-CMA13-1070 | C-52-0405-CMA13-1070: FS | 2025-02-19 12:00 | 2025-02-20 12:00
C-52-0405-CMA13-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 | Padding | C-52-0405-CMA13-1060 | C-52-0405-CMA13-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-20 12:00 | 2025-02-21 12:00
C-52-0405-CMA14-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 | Trench Excavation | C-52-0405-CMA12-1000 | C-52-0405-CMA12-1000: SS | C-52-0405-CMA14-1010, C-52-0405-CMA24-1000 | C-52-0405-CMA14-1010: FF, C-52-0405-CMA24-1000: SS | 2025-02-14 12:00 | 2025-02-21 12:00
C-52-0405-CMA14-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 | Bedding | C-52-0405-CMA14-1000 | C-52-0405-CMA14-1000: FF | C-52-0405-CMA14-1020 | C-52-0405-CMA14-1020: FS | 2025-02-20 12:00 | 2025-02-21 12:00
C-52-0405-CMA14-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 | Lowering | C-52-0405-CMA14-1010 | C-52-0405-CMA14-1010: FS | C-52-0405-CMA14-1030 | C-52-0405-CMA14-1030: SS | 2025-02-21 12:00 | 2025-02-22 12:00
C-52-0405-CMA14-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 | Section Tie-in Welding | C-52-0405-CMA14-1020 | C-52-0405-CMA14-1020: SS | C-52-0405-CMA14-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA14-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-21 12:00 | 2025-02-24 12:00
C-52-0405-CMA14-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 | NDT (Tie-in Joint) | C-52-0405-CMA14-1030 | C-52-0405-CMA14-1030: SS 1 | C-52-0405-CMA14-1050 | C-52-0405-CMA14-1050: SS 1 | 2025-02-22 12:00 | 2025-02-25 12:00
C-52-0405-CMA14-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA14-1040 | C-52-0405-CMA14-1040: SS 1 | C-52-0405-CMA14-1060 | C-52-0405-CMA14-1060: FS | 2025-02-24 12:00 | 2025-02-26 12:00
C-52-0405-CMA14-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 | Holiday Testing | C-52-0405-CMA14-1050 | C-52-0405-CMA14-1050: FS | C-52-0405-CMA14-1070 | C-52-0405-CMA14-1070: FS | 2025-02-26 12:00 | 2025-02-27 12:00
C-52-0405-CMA14-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 | Padding | C-52-0405-CMA14-1060 | C-52-0405-CMA14-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-27 12:00 | 2025-02-28 12:00
C-52-0405-CMA15-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 | Trench Excavation | C-52-0405-CMA13-1000, C-52-0405-CMA13-1000 | C-52-0405-CMA13-1000: SS, C-52-0405-CMA13-1000: FF | C-52-0405-CMA15-1010, C-52-0405-CMA16-1000 | C-52-0405-CMA15-1010: FF, C-52-0405-CMA16-1000: FS | 2025-02-07 12:00 | 2025-02-14 12:00
C-52-0405-CMA15-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 | Bedding | C-52-0405-CMA15-1000 | C-52-0405-CMA15-1000: FF | C-52-0405-CMA15-1020 | C-52-0405-CMA15-1020: FS | 2025-02-13 12:00 | 2025-02-14 12:00
C-52-0405-CMA15-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 | Lowering | C-52-0405-CMA15-1010 | C-52-0405-CMA15-1010: FS | C-52-0405-CMA15-1030 | C-52-0405-CMA15-1030: SS | 2025-02-14 12:00 | 2025-02-15 12:00
C-52-0405-CMA15-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 | Section Tie-in Welding | C-52-0405-CMA15-1020 | C-52-0405-CMA15-1020: SS | C-52-0405-CMA15-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA15-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-14 12:00 | 2025-02-17 12:00
C-52-0405-CMA15-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 | NDT (Tie-in Joint) | C-52-0405-CMA15-1030 | C-52-0405-CMA15-1030: SS 1 | C-52-0405-CMA15-1050 | C-52-0405-CMA15-1050: SS 1 | 2025-02-15 12:00 | 2025-02-18 12:00
C-52-0405-CMA15-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA15-1040 | C-52-0405-CMA15-1040: SS 1 | C-52-0405-CMA15-1060 | C-52-0405-CMA15-1060: FS | 2025-02-17 12:00 | 2025-02-19 12:00
C-52-0405-CMA15-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 | Holiday Testing | C-52-0405-CMA15-1050 | C-52-0405-CMA15-1050: FS | C-52-0405-CMA15-1070 | C-52-0405-CMA15-1070: FS | 2025-02-19 12:00 | 2025-02-20 12:00
C-52-0405-CMA15-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 | Padding | C-52-0405-CMA15-1060 | C-52-0405-CMA15-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-20 12:00 | 2025-02-21 12:00
C-52-0405-CMA24-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 | Trench Excavation | C-52-0405-CMA14-1000 | C-52-0405-CMA14-1000: SS | C-52-0405-CMA24-1010, C-52-0405-CMA17-1000 | C-52-0405-CMA24-1010: FF, C-52-0405-CMA17-1000: FS | 2025-02-14 12:00 | 2025-02-25 12:00
C-52-0405-CMA24-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 | Bedding | C-52-0405-CMA24-1000 | C-52-0405-CMA24-1000: FF | C-52-0405-CMA24-1020 | C-52-0405-CMA24-1020: FS | 2025-02-24 12:00 | 2025-02-25 12:00
C-52-0405-CMA24-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 | Lowering | C-52-0405-CMA24-1010 | C-52-0405-CMA24-1010: FS | C-52-0405-CMA24-1030 | C-52-0405-CMA24-1030: SS | 2025-02-25 12:00 | 2025-02-26 12:00
C-52-0405-CMA24-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 | Section Tie-in Welding | C-52-0405-CMA24-1020 | C-52-0405-CMA24-1020: SS | C-52-0405-CMA24-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA24-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-25 12:00 | 2025-02-27 12:00
C-52-0405-CMA24-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 | NDT (Tie-in Joint) | C-52-0405-CMA24-1030 | C-52-0405-CMA24-1030: SS 1 | C-52-0405-CMA24-1050 | C-52-0405-CMA24-1050: SS 1 | 2025-02-26 12:00 | 2025-02-28 12:00
C-52-0405-CMA24-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA24-1040 | C-52-0405-CMA24-1040: SS 1 | C-52-0405-CMA24-1060 | C-52-0405-CMA24-1060: FS | 2025-02-27 12:00 | 2025-03-01 12:00
C-52-0405-CMA24-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 | Holiday Testing | C-52-0405-CMA24-1050 | C-52-0405-CMA24-1050: FS | C-52-0405-CMA24-1070 | C-52-0405-CMA24-1070: FS | 2025-03-01 12:00 | 2025-03-02 12:00
C-52-0405-CMA24-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 | Padding | C-52-0405-CMA24-1060 | C-52-0405-CMA24-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-03-02 12:00 | 2025-03-04 10:00
C-52-0405-CMA16-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 | Trench Excavation | C-52-0405-CMA15-1000 | C-52-0405-CMA15-1000: FS | C-52-0405-CMA16-1010, C-52-0405-CMA18-1000 | C-52-0405-CMA16-1010: FF, C-52-0405-CMA18-1000: FS | 2025-02-14 12:00 | 2025-02-21 12:00
C-52-0405-CMA16-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 | Bedding | C-52-0405-CMA16-1000 | C-52-0405-CMA16-1000: FF | C-52-0405-CMA16-1020 | C-52-0405-CMA16-1020: FS | 2025-02-20 12:00 | 2025-02-21 12:00
C-52-0405-CMA16-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 | Lowering | C-52-0405-CMA16-1010 | C-52-0405-CMA16-1010: FS | C-52-0405-CMA16-1030 | C-52-0405-CMA16-1030: SS | 2025-02-21 12:00 | 2025-02-22 12:00
C-52-0405-CMA16-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 | Section Tie-in Welding | C-52-0405-CMA16-1020 | C-52-0405-CMA16-1020: SS | C-52-0405-CMA16-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA16-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-21 12:00 | 2025-02-24 12:00
C-52-0405-CMA16-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 | NDT (Tie-in Joint) | C-52-0405-CMA16-1030 | C-52-0405-CMA16-1030: SS 1 | C-52-0405-CMA16-1050 | C-52-0405-CMA16-1050: SS 1 | 2025-02-22 12:00 | 2025-02-25 12:00
C-52-0405-CMA16-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA16-1040 | C-52-0405-CMA16-1040: SS 1 | C-52-0405-CMA16-1060 | C-52-0405-CMA16-1060: FS | 2025-02-24 12:00 | 2025-02-26 12:00
C-52-0405-CMA16-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 | Holiday Testing | C-52-0405-CMA16-1050 | C-52-0405-CMA16-1050: FS | C-52-0405-CMA16-1070 | C-52-0405-CMA16-1070: FS | 2025-02-26 12:00 | 2025-02-27 12:00
C-52-0405-CMA16-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 | Padding | C-52-0405-CMA16-1060 | C-52-0405-CMA16-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-27 12:00 | 2025-02-28 12:00
C-52-0405-CMA17-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 | Trench Excavation | C-52-0405-CMA24-1000 | C-52-0405-CMA24-1000: FS | C-52-0405-CMA17-1010, C-52-0405-CMA19-1000 | C-52-0405-CMA17-1010: FF, C-52-0405-CMA19-1000: FS | 2025-02-25 12:00 | 2025-03-04 10:00
C-52-0405-CMA17-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 | Bedding | C-52-0405-CMA17-1000 | C-52-0405-CMA17-1000: FF | C-52-0405-CMA17-1020 | C-52-0405-CMA17-1020: FS | 2025-03-02 12:00 | 2025-03-04 10:00
C-52-0405-CMA17-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 | Lowering | C-52-0405-CMA17-1010 | C-52-0405-CMA17-1010: FS | C-52-0405-CMA17-1030 | C-52-0405-CMA17-1030: SS | 2025-03-04 10:00 | 2025-03-06 08:00
C-52-0405-CMA17-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 | Section Tie-in Welding | C-52-0405-CMA17-1020 | C-52-0405-CMA17-1020: SS | C-52-0405-CMA17-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA17-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-03-04 10:00 | 2025-03-07 12:00
C-52-0405-CMA17-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 | NDT (Tie-in Joint) | C-52-0405-CMA17-1030 | C-52-0405-CMA17-1030: SS 1 | C-52-0405-CMA17-1050 | C-52-0405-CMA17-1050: SS 1 | 2025-03-06 08:00 | 2025-03-08 16:00
C-52-0405-CMA17-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA17-1040 | C-52-0405-CMA17-1040: SS 1 | C-52-0405-CMA17-1060 | C-52-0405-CMA17-1060: FS | 2025-03-07 12:00 | 2025-03-10 10:00
C-52-0405-CMA17-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 | Holiday Testing | C-52-0405-CMA17-1050 | C-52-0405-CMA17-1050: FS | C-52-0405-CMA17-1070 | C-52-0405-CMA17-1070: FS | 2025-03-10 10:00 | 2025-03-12 08:00
C-52-0405-CMA17-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 | Padding | C-52-0405-CMA17-1060 | C-52-0405-CMA17-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-03-12 08:00 | 2025-03-13 12:00
C-52-0405-CMA18-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 | Trench Excavation | C-52-0405-CMA16-1000 | C-52-0405-CMA16-1000: FS | C-52-0405-CMA18-1010, C-52-0405-CMA32-1000 | C-52-0405-CMA18-1010: FF, C-52-0405-CMA32-1000: FS | 2025-02-21 12:00 | 2025-02-28 12:00
C-52-0405-CMA18-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 | Bedding | C-52-0405-CMA18-1000 | C-52-0405-CMA18-1000: FF | C-52-0405-CMA18-1020 | C-52-0405-CMA18-1020: FS | 2025-02-27 12:00 | 2025-02-28 12:00
C-52-0405-CMA18-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 | Lowering | C-52-0405-CMA18-1010 | C-52-0405-CMA18-1010: FS | C-52-0405-CMA18-1030 | C-52-0405-CMA18-1030: SS | 2025-02-28 12:00 | 2025-03-01 12:00
C-52-0405-CMA18-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 | Section Tie-in Welding | C-52-0405-CMA18-1020 | C-52-0405-CMA18-1020: SS | C-52-0405-CMA18-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA18-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-28 12:00 | 2025-03-02 12:00
C-52-0405-CMA18-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 | NDT (Tie-in Joint) | C-52-0405-CMA18-1030 | C-52-0405-CMA18-1030: SS 1 | C-52-0405-CMA18-1050 | C-52-0405-CMA18-1050: SS 1 | 2025-03-01 12:00 | 2025-03-04 10:00
C-52-0405-CMA18-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA18-1040 | C-52-0405-CMA18-1040: SS 1 | C-52-0405-CMA18-1060 | C-52-0405-CMA18-1060: FS | 2025-03-02 12:00 | 2025-03-06 08:00
C-52-0405-CMA18-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 | Holiday Testing | C-52-0405-CMA18-1050 | C-52-0405-CMA18-1050: FS | C-52-0405-CMA18-1070 | C-52-0405-CMA18-1070: FS | 2025-03-06 08:00 | 2025-03-07 12:00
C-52-0405-CMA18-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 | Padding | C-52-0405-CMA18-1060 | C-52-0405-CMA18-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-03-07 12:00 | 2025-03-08 16:00
C-52-0405-CMA19-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 | Trench Excavation | C-52-0405-CMA17-1000 | C-52-0405-CMA17-1000: FS | C-52-0405-CMA19-1010 | C-52-0405-CMA19-1010: FF | 2025-03-04 10:00 | 2025-03-13 12:00
C-52-0405-CMA19-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 | Bedding | C-52-0405-CMA19-1000 | C-52-0405-CMA19-1000: FF | C-52-0405-CMA19-1020 | C-52-0405-CMA19-1020: FS | 2025-03-12 08:00 | 2025-03-13 12:00
C-52-0405-CMA19-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 | Lowering | C-52-0405-CMA19-1010 | C-52-0405-CMA19-1010: FS | C-52-0405-CMA19-1030 | C-52-0405-CMA19-1030: SS | 2025-03-13 12:00 | 2025-03-15 10:00
C-52-0405-CMA19-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 | Section Tie-in Welding | C-52-0405-CMA19-1020 | C-52-0405-CMA19-1020: SS | C-52-0405-CMA19-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA19-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-03-13 12:00 | 2025-03-16 10:00
C-52-0405-CMA19-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 | NDT (Tie-in Joint) | C-52-0405-CMA19-1030 | C-52-0405-CMA19-1030: SS 1 | C-52-0405-CMA19-1050 | C-52-0405-CMA19-1050: SS 1 | 2025-03-15 10:00 | 2025-03-18 08:00
C-52-0405-CMA19-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA19-1040 | C-52-0405-CMA19-1040: SS 1 | C-52-0405-CMA19-1060 | C-52-0405-CMA19-1060: FS | 2025-03-16 10:00 | 2025-03-19 12:00
C-52-0405-CMA19-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 | Holiday Testing | C-52-0405-CMA19-1050 | C-52-0405-CMA19-1050: FS | C-52-0405-CMA19-1070 | C-52-0405-CMA19-1070: FS | 2025-03-19 12:00 | 2025-03-21 10:00
C-52-0405-CMA19-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 | Padding | C-52-0405-CMA19-1060 | C-52-0405-CMA19-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-03-21 10:00 | 2025-03-22 14:00
C-52-0405-CMA32-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 | Trench Excavation | C-52-0405-CMA18-1000 | C-52-0405-CMA18-1000: FS | C-52-0405-CMA32-1010, C-52-0506-CMA07-1000 | C-52-0405-CMA32-1010: FF, C-52-0506-CMA07-1000: FS | 2025-02-28 12:00 | 2025-03-08 16:00
C-52-0405-CMA32-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 | Bedding | C-52-0405-CMA32-1000 | C-52-0405-CMA32-1000: FF | C-52-0405-CMA32-1020 | C-52-0405-CMA32-1020: FS | 2025-03-07 12:00 | 2025-03-08 16:00
C-52-0405-CMA32-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 | Lowering | C-52-0405-CMA32-1010 | C-52-0405-CMA32-1010: FS | C-52-0405-CMA32-1030, C-52-0405-CMA32-1030 | C-52-0405-CMA32-1030: SS, C-52-0405-CMA32-1030: FF | 2025-03-08 16:00 | 2025-03-10 10:00
C-52-0405-CMA32-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 | Section Tie-in Welding | C-52-0405-CMA32-1020, C-52-0405-CMA32-1020 | C-52-0405-CMA32-1020: SS, C-52-0405-CMA32-1020: FF | C-52-0405-CMA32-1040, C-52-0405-PL-ME-4810 | C-52-0405-CMA32-1040: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-03-08 16:00 | 2025-03-12 08:00
C-52-0405-CMA32-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 | NDT (Tie-in Joint) | C-52-0405-CMA32-1030 | C-52-0405-CMA32-1030: SS 1 | C-52-0405-CMA32-1050 | C-52-0405-CMA32-1050: SS 1 | 2025-03-10 10:00 | 2025-03-13 12:00
C-52-0405-CMA32-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA32-1040 | C-52-0405-CMA32-1040: SS 1 | C-52-0405-CMA32-1060 | C-52-0405-CMA32-1060: FS | 2025-03-12 08:00 | 2025-03-15 10:00
C-52-0405-CMA32-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 | Holiday Testing | C-52-0405-CMA32-1050 | C-52-0405-CMA32-1050: FS | C-52-0405-CMA32-1070 | C-52-0405-CMA32-1070: FS | 2025-03-15 10:00 | 2025-03-16 10:00
C-52-0405-CMA32-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 | Padding | C-52-0405-CMA32-1060 | C-52-0405-CMA32-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-03-16 10:00 | 2025-03-18 08:00
C-52-0405-CME01-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 | Trench Excavation | C-52-0405-PL-ME-2800 | C-52-0405-PL-ME-2800: SS 1 | C-52-0405-CME01-1010, C-52-0405-CME02-1000 | C-52-0405-CME01-1010: FS, C-52-0405-CME02-1000: FS 1 | 2024-12-14 12:00 | 2024-12-17 12:00
C-52-0405-CME01-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 | Bedding | C-52-0405-CME01-1000 | C-52-0405-CME01-1000: FS | C-52-0405-CME01-1020 | C-52-0405-CME01-1020: FS | 2024-12-17 12:00 | 2024-12-19 12:00
C-52-0405-CME01-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 | Lowering | C-52-0405-CME01-1010 | C-52-0405-CME01-1010: FS | C-52-0405-CME01-1030 | C-52-0405-CME01-1030: FS | 2024-12-19 12:00 | 2024-12-21 12:00
C-52-0405-CME01-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 | Section Tie-in Welding | C-52-0405-CME01-1020 | C-52-0405-CME01-1020: FS | C-52-0405-CME01-1040, C-52-0405-PL-ME-4810 | C-52-0405-CME01-1040: FS, C-52-0405-PL-ME-4810: FF 1 | 2024-12-21 12:00 | 2024-12-25 12:00
C-52-0405-CME01-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 | NDT (Tie-in Joint) | C-52-0405-CME01-1030 | C-52-0405-CME01-1030: FS | C-52-0405-CME01-1050 | C-52-0405-CME01-1050: FS | 2024-12-25 12:00 | 2024-12-28 12:00
C-52-0405-CME01-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME01-1040 | C-52-0405-CME01-1040: FS | C-52-0405-CME01-1060 | C-52-0405-CME01-1060: FS | 2024-12-28 12:00 | 2025-01-02 12:00
C-52-0405-CME01-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 | Holiday Testing | C-52-0405-CME01-1050 | C-52-0405-CME01-1050: FS | C-52-0405-CME01-1070 | C-52-0405-CME01-1070: FS | 2025-01-02 12:00 | 2025-01-04 12:00
C-52-0405-CME01-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 | Padding & Back Filling | C-52-0405-CME01-1060 | C-52-0405-CME01-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-01-04 12:00 | 2025-01-07 12:00
C-52-0405-CME02-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 | Trench Excavation | C-52-0405-CME01-1000 | C-52-0405-CME01-1000: FS 1 | C-52-0405-CME02-1010, C-52-0405-CME03-1000 | C-52-0405-CME02-1010: FS, C-52-0405-CME03-1000: FS 1 | 2024-12-18 12:00 | 2024-12-20 12:00
C-52-0405-CME02-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 | Bedding | C-52-0405-CME02-1000 | C-52-0405-CME02-1000: FS | C-52-0405-CME02-1020 | C-52-0405-CME02-1020: FS | 2024-12-20 12:00 | 2024-12-23 12:00
C-52-0405-CME02-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 | Lowering | C-52-0405-CME02-1010 | C-52-0405-CME02-1010: FS | C-52-0405-CME02-1030 | C-52-0405-CME02-1030: FS | 2024-12-23 12:00 | 2024-12-25 12:00
C-52-0405-CME02-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 | Section Tie-in Welding | C-52-0405-CME02-1020 | C-52-0405-CME02-1020: FS | C-52-0405-CME02-1040, C-52-0405-PL-ME-4810 | C-52-0405-CME02-1040: FS, C-52-0405-PL-ME-4810: FF 1 | 2024-12-25 12:00 | 2024-12-28 12:00
C-52-0405-CME02-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 | NDT (Tie-in Joint) | C-52-0405-CME02-1030 | C-52-0405-CME02-1030: FS | C-52-0405-CME02-1050 | C-52-0405-CME02-1050: FS | 2024-12-28 12:00 | 2025-01-02 12:00
C-52-0405-CME02-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME02-1040 | C-52-0405-CME02-1040: FS | C-52-0405-CME02-1060 | C-52-0405-CME02-1060: FS | 2025-01-02 12:00 | 2025-01-06 12:00
C-52-0405-CME02-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 | Holiday Testing | C-52-0405-CME02-1050 | C-52-0405-CME02-1050: FS | C-52-0405-CME02-1070 | C-52-0405-CME02-1070: FS | 2025-01-06 12:00 | 2025-01-08 12:00
C-52-0405-CME02-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 | Padding & Back Filling | C-52-0405-CME02-1060 | C-52-0405-CME02-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-01-08 12:00 | 2025-01-10 12:00
C-52-0405-CME03-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 | Trench Excavation | C-52-0405-CME02-1000 | C-52-0405-CME02-1000: FS 1 | C-52-0405-CME03-1010, C-52-0405-CME04-1000 | C-52-0405-CME03-1010: FS, C-52-0405-CME04-1000: FS 1 | 2024-12-21 12:00 | 2024-12-24 12:00
C-52-0405-CME03-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 | Bedding | C-52-0405-CME03-1000 | C-52-0405-CME03-1000: FS | C-52-0405-CME03-1020 | C-52-0405-CME03-1020: FS | 2024-12-24 12:00 | 2024-12-26 12:00
C-52-0405-CME03-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 | Lowering | C-52-0405-CME03-1010 | C-52-0405-CME03-1010: FS | C-52-0405-CME03-1030 | C-52-0405-CME03-1030: FS | 2024-12-26 12:00 | 2024-12-28 12:00
C-52-0405-CME03-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 | Section Tie-in Welding | C-52-0405-CME03-1020 | C-52-0405-CME03-1020: FS | C-52-0405-CME03-1040, C-52-0405-PL-ME-4810 | C-52-0405-CME03-1040: FS, C-52-0405-PL-ME-4810: FF 1 | 2024-12-28 12:00 | 2025-01-02 12:00
C-52-0405-CME03-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 | NDT (Tie-in Joint) | C-52-0405-CME03-1030 | C-52-0405-CME03-1030: FS | C-52-0405-CME03-1050 | C-52-0405-CME03-1050: FS | 2025-01-02 12:00 | 2025-01-06 12:00
C-52-0405-CME03-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME03-1040 | C-52-0405-CME03-1040: FS | C-52-0405-CME03-1060 | C-52-0405-CME03-1060: FS | 2025-01-06 12:00 | 2025-01-09 12:00
C-52-0405-CME03-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 | Holiday Testing | C-52-0405-CME03-1050 | C-52-0405-CME03-1050: FS | C-52-0405-CME03-1070 | C-52-0405-CME03-1070: FS | 2025-01-09 12:00 | 2025-01-11 12:00
C-52-0405-CME03-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 | Padding & Back Filling | C-52-0405-CME03-1060 | C-52-0405-CME03-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-01-11 12:00 | 2025-01-14 12:00
C-52-0405-CME04-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 | Trench Excavation | C-52-0405-CME03-1000 | C-52-0405-CME03-1000: FS 1 | C-52-0405-CME04-1010, C-52-0405-CME05-1000 | C-52-0405-CME04-1010: FS, C-52-0405-CME05-1000: FS 1 | 2024-12-25 12:00 | 2024-12-27 12:00
C-52-0405-CME04-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 | Bedding | C-52-0405-CME04-1000 | C-52-0405-CME04-1000: FS | C-52-0405-CME04-1020 | C-52-0405-CME04-1020: FS | 2024-12-27 12:00 | 2024-12-30 12:00
C-52-0405-CME04-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 | Lowering | C-52-0405-CME04-1010 | C-52-0405-CME04-1010: FS | C-52-0405-CME04-1030 | C-52-0405-CME04-1030: FS | 2024-12-30 12:00 | 2025-01-02 12:00
C-52-0405-CME04-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 | Section Tie-in Welding | C-52-0405-CME04-1020 | C-52-0405-CME04-1020: FS | C-52-0405-CME04-1040, C-52-0405-PL-ME-4810 | C-52-0405-CME04-1040: FS, C-52-0405-PL-ME-4810: FF 1 | 2025-01-02 12:00 | 2025-01-06 12:00
C-52-0405-CME04-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 | NDT (Tie-in Joint) | C-52-0405-CME04-1030 | C-52-0405-CME04-1030: FS | C-52-0405-CME04-1050 | C-52-0405-CME04-1050: FS | 2025-01-06 12:00 | 2025-01-09 12:00
C-52-0405-CME04-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME04-1040 | C-52-0405-CME04-1040: FS | C-52-0405-CME04-1060 | C-52-0405-CME04-1060: FS | 2025-01-09 12:00 | 2025-01-13 12:00
C-52-0405-CME04-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 | Holiday Testing | C-52-0405-CME04-1050 | C-52-0405-CME04-1050: FS | C-52-0405-CME04-1070 | C-52-0405-CME04-1070: FS | 2025-01-13 12:00 | 2025-01-15 12:00
C-52-0405-CME04-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 | Padding & Back Filling | C-52-0405-CME04-1060 | C-52-0405-CME04-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-01-15 12:00 | 2025-01-17 12:00
C-52-0405-CME05-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 | Trench Excavation | C-52-0405-CME04-1000 | C-52-0405-CME04-1000: FS 1 | C-52-0405-CME05-1010, C-52-0405-CME06-1000 | C-52-0405-CME05-1010: FS, C-52-0405-CME06-1000: FS | 2024-12-28 12:00 | 2024-12-31 12:00
C-52-0405-CME05-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 | Bedding | C-52-0405-CME05-1000 | C-52-0405-CME05-1000: FS | C-52-0405-CME05-1020 | C-52-0405-CME05-1020: FS | 2024-12-31 12:00 | 2025-01-03 12:00
C-52-0405-CME05-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 | Lowering | C-52-0405-CME05-1010 | C-52-0405-CME05-1010: FS | C-52-0405-CME05-1030 | C-52-0405-CME05-1030: FS | 2025-01-03 12:00 | 2025-01-06 12:00
C-52-0405-CME05-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 | Section Tie-in Welding | C-52-0405-CME05-1020 | C-52-0405-CME05-1020: FS | C-52-0405-CME05-1040, C-52-0405-PL-ME-4810 | C-52-0405-CME05-1040: FS, C-52-0405-PL-ME-4810: FF 1 | 2025-01-06 12:00 | 2025-01-09 12:00
C-52-0405-CME05-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 | NDT (Tie-in Joint) | C-52-0405-CME05-1030 | C-52-0405-CME05-1030: FS | C-52-0405-CME05-1050 | C-52-0405-CME05-1050: FS | 2025-01-09 12:00 | 2025-01-13 12:00
C-52-0405-CME05-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME05-1040 | C-52-0405-CME05-1040: FS | C-52-0405-CME05-1060 | C-52-0405-CME05-1060: FS | 2025-01-13 12:00 | 2025-01-16 12:00
C-52-0405-CME05-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 | Holiday Testing | C-52-0405-CME05-1050 | C-52-0405-CME05-1050: FS | C-52-0405-CME05-1070 | C-52-0405-CME05-1070: FS | 2025-01-16 12:00 | 2025-01-18 12:00
C-52-0405-CME05-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 | Padding & Back Filling | C-52-0405-CME05-1060 | C-52-0405-CME05-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-01-18 12:00 | 2025-01-21 12:00
C-52-0405-CME06-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 | Trench Excavation | C-52-0405-CME05-1000 | C-52-0405-CME05-1000: FS | C-52-0405-CME06-1010, C-52-0405-CMA31-1000, C-52-0405-CME07-1000 | C-52-0405-CME06-1010: FS, C-52-0405-CMA31-1000: FS, C-52-0405-CME07-1000: FS 1 | 2024-12-31 12:00 | 2025-01-03 12:00
C-52-0405-CME06-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 | Bedding | C-52-0405-CME06-1000 | C-52-0405-CME06-1000: FS | C-52-0405-CME06-1020 | C-52-0405-CME06-1020: FS | 2025-01-03 12:00 | 2025-01-06 12:00
C-52-0405-CME06-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 | Lowering | C-52-0405-CME06-1010 | C-52-0405-CME06-1010: FS | C-52-0405-CME06-1030 | C-52-0405-CME06-1030: FS | 2025-01-06 12:00 | 2025-01-08 12:00
C-52-0405-CME06-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 | Section Tie-in Welding | C-52-0405-CME06-1020 | C-52-0405-CME06-1020: FS | C-52-0405-CME06-1040, C-52-0405-PL-ME-4810 | C-52-0405-CME06-1040: FS, C-52-0405-PL-ME-4810: FF 1 | 2025-01-08 12:00 | 2025-01-11 12:00
C-52-0405-CME06-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 | NDT (Tie-in Joint) | C-52-0405-CME06-1030 | C-52-0405-CME06-1030: FS | C-52-0405-CME06-1050 | C-52-0405-CME06-1050: FS | 2025-01-11 12:00 | 2025-01-15 12:00
C-52-0405-CME06-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME06-1040 | C-52-0405-CME06-1040: FS | C-52-0405-CME06-1060 | C-52-0405-CME06-1060: FS | 2025-01-15 12:00 | 2025-01-18 12:00
C-52-0405-CME06-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 | Holiday Testing | C-52-0405-CME06-1050 | C-52-0405-CME06-1050: FS | C-52-0405-CME06-1070 | C-52-0405-CME06-1070: FS | 2025-01-18 12:00 | 2025-01-21 12:00
C-52-0405-CME06-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 | Padding & Back Filling | C-52-0405-CME06-1060 | C-52-0405-CME06-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-01-21 12:00 | 2025-01-23 12:00
C-52-0405-CME07-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 | Trench Excavation | C-52-0405-CME06-1000 | C-52-0405-CME06-1000: FS 1 | C-52-0405-CME07-1010, C-52-0405-CME08-1000 | C-52-0405-CME07-1010: FS, C-52-0405-CME08-1000: FS 1 | 2025-01-04 12:00 | 2025-01-07 12:00
C-52-0405-CME07-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 | Bedding | C-52-0405-CME07-1000 | C-52-0405-CME07-1000: FS | C-52-0405-CME07-1020 | C-52-0405-CME07-1020: FS | 2025-01-07 12:00 | 2025-01-09 12:00
C-52-0405-CME07-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 | Lowering | C-52-0405-CME07-1010 | C-52-0405-CME07-1010: FS | C-52-0405-CME07-1030 | C-52-0405-CME07-1030: FS | 2025-01-09 12:00 | 2025-01-11 12:00
C-52-0405-CME07-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 | Section Tie-in Welding | C-52-0405-CME07-1020 | C-52-0405-CME07-1020: FS | C-52-0405-CME07-1040, C-52-0405-PL-ME-4810 | C-52-0405-CME07-1040: FS, C-52-0405-PL-ME-4810: FF 1 | 2025-01-11 12:00 | 2025-01-15 12:00
C-52-0405-CME07-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 | NDT (Tie-in Joint) | C-52-0405-CME07-1030 | C-52-0405-CME07-1030: FS | C-52-0405-CME07-1050 | C-52-0405-CME07-1050: FS | 2025-01-15 12:00 | 2025-01-18 12:00
C-52-0405-CME07-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME07-1040 | C-52-0405-CME07-1040: FS | C-52-0405-CME07-1060 | C-52-0405-CME07-1060: FS | 2025-01-18 12:00 | 2025-01-22 12:00
C-52-0405-CME07-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 | Holiday Testing | C-52-0405-CME07-1050 | C-52-0405-CME07-1050: FS | C-52-0405-CME07-1070 | C-52-0405-CME07-1070: FS | 2025-01-22 12:00 | 2025-01-24 12:00
C-52-0405-CME07-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 | Padding & Back Filling | C-52-0405-CME07-1060 | C-52-0405-CME07-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-01-24 12:00 | 2025-01-27 12:00
C-52-0405-CME08-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 | Trench Excavation | C-52-0405-CME07-1000 | C-52-0405-CME07-1000: FS 1 | C-52-0405-CME08-1010, C-52-0506-CMA06-1000, C-52-0405-CME16-1000 | C-52-0405-CME08-1010: FS, C-52-0506-CMA06-1000: FS 4, C-52-0405-CME16-1000: FS 1 | 2025-01-08 12:00 | 2025-01-10 12:00
C-52-0405-CME08-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 | Bedding | C-52-0405-CME08-1000 | C-52-0405-CME08-1000: FS | C-52-0405-CME08-1020 | C-52-0405-CME08-1020: FS | 2025-01-10 12:00 | 2025-01-13 12:00
C-52-0405-CME08-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 | Lowering | C-52-0405-CME08-1010 | C-52-0405-CME08-1010: FS | C-52-0405-CME08-1030 | C-52-0405-CME08-1030: FS | 2025-01-13 12:00 | 2025-01-15 12:00
C-52-0405-CME08-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 | Section Tie-in Welding | C-52-0405-CME08-1020 | C-52-0405-CME08-1020: FS | C-52-0405-CME08-1040, C-52-0405-PL-ME-4810 | C-52-0405-CME08-1040: FS, C-52-0405-PL-ME-4810: FF 1 | 2025-01-15 12:00 | 2025-01-18 12:00
C-52-0405-CME08-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 | NDT (Tie-in Joint) | C-52-0405-CME08-1030 | C-52-0405-CME08-1030: FS | C-52-0405-CME08-1050 | C-52-0405-CME08-1050: FS | 2025-01-18 12:00 | 2025-01-22 12:00
C-52-0405-CME08-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME08-1040 | C-52-0405-CME08-1040: FS | C-52-0405-CME08-1060 | C-52-0405-CME08-1060: FS | 2025-01-22 12:00 | 2025-01-25 12:00
C-52-0405-CME08-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 | Holiday Testing | C-52-0405-CME08-1050 | C-52-0405-CME08-1050: FS | C-52-0405-CME08-1070 | C-52-0405-CME08-1070: FS | 2025-01-25 12:00 | 2025-01-28 12:00
C-52-0405-CME08-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 | Padding & Back Filling | C-52-0405-CME08-1060 | C-52-0405-CME08-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-01-28 12:00 | 2025-01-30 12:00
C-52-0405-CNM17-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1190 | C-PER-1190: FS | C-52-0405-CNM17-1020, C-52-0405-CNM17-1010 | C-52-0405-CNM17-1020: FS, C-52-0405-CNM17-1010: FS | 2024-10-28 07:30 | 2024-12-04 07:30
C-52-0405-CNM17-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-0405-CNM17-1000 | C-52-0405-CNM17-1000: FS | C-52-0405-CNM17-1030 | C-52-0405-CNM17-1030: FS | 2024-12-04 07:30 | 2024-12-09 07:30
C-52-0405-CNM17-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 | Driving & Receiving Pit Excavation | C-52-0405-CNM17-1000 | C-52-0405-CNM17-1000: FS | C-52-0405-CNM17-1030 | C-52-0405-CNM17-1030: FF | 2024-12-04 07:30 | 2024-12-25 07:30
C-52-0405-CNM17-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNM17-1010, C-52-0405-CNM17-1020 | C-52-0405-CNM17-1010: FF, C-52-0405-CNM17-1020: FS | C-52-0405-CNM17-1040 | C-52-0405-CNM17-1040: FS | 2024-12-09 07:30 | 2024-12-25 07:30
C-52-0405-CNM17-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 | Floor Blinding & French Drain in Driving Pit | C-52-0405-CNM17-1030 | C-52-0405-CNM17-1030: FS | C-52-0405-CNM17-1050 | C-52-0405-CNM17-1050: FS | 2024-12-25 07:30 | 2025-01-02 07:30
C-52-0405-CNM17-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0405-CNM17-1040 | C-52-0405-CNM17-1040: FS | C-52-0405-CNM17-1060 | C-52-0405-CNM17-1060: SS 7 | 2025-01-02 07:30 | 2025-01-09 07:30
C-52-0405-CNM17-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 | Construction of Exit Wall with Ring | C-52-0405-CNM17-1050 | C-52-0405-CNM17-1050: SS 7 | C-52-0405-CNM17-1200 | C-52-0405-CNM17-1200: FS | 2025-01-10 07:30 | 2025-01-17 07:30
C-52-0405-CNM17-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.2.2 | Jacking of MTBM & RC Sleeves | C-52-0405-CNM17-1060 | C-52-0405-CNM17-1060: FS | C-52-0405-CNM17-1210 | C-52-0405-CNM17-1210: FS | 2025-01-17 07:30 | 2025-01-31 07:30
C-52-0405-CNM17-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.2.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0405-CNM17-1200 | C-52-0405-CNM17-1200: FS | C-52-0405-CNM17-1400 | C-52-0405-CNM17-1400: FS | 2025-01-31 07:30 | 2025-02-05 07:30
C-52-0405-CNM17-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.2.3 | Lowering & Welding of Carrier Pipe | C-52-0405-CNM17-1210 | C-52-0405-CNM17-1210: FS | C-52-0405-CNM17-1410, C-52-0405-PL-ME-4810 | C-52-0405-CNM17-1410: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-05 07:30 | 2025-02-19 07:30
C-52-0405-CNM17-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.2.3 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0405-CNM17-1400 | C-52-0405-CNM17-1400: SS 1 | C-52-0405-CNM17-1600 | C-52-0405-CNM17-1600: FS | 2025-02-06 07:30 | 2025-02-20 07:30
C-52-0405-CNM17-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.2.4 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0405-CNM17-1410 | C-52-0405-CNM17-1410: FS | C-52-0405-CNM17-1220 | C-52-0405-CNM17-1220: FS | 2025-02-20 07:30 | 2025-03-07 07:30
C-52-0405-CNM17-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.2.2 | Inner Grout b/w Main & RC Pipe | C-52-0405-CNM17-1600 | C-52-0405-CNM17-1600: FS | C-52-0405-CNM17-1800, C-52-0405-PL-CA-5220 | C-52-0405-CNM17-1800: FS, C-52-0405-PL-CA-5220: FF 1 | 2025-03-07 07:30 | 2025-03-14 11:30
C-52-0405-CNM17-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.2.5 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0405-CNM17-1220 | C-52-0405-CNM17-1220: FS | C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, PRECOM-52-0405-1000, ML1679-E13 | C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, PRECOM-52-0405-1000: FS, ML1679-E13: FS | 2025-03-14 11:30 | 2025-04-07 13:30
C-52-0405-CNM18-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1200 | C-PER-1200: FS | C-52-0405-CNM18-1020, C-52-0405-CNM18-1010 | C-52-0405-CNM18-1020: FS, C-52-0405-CNM18-1010: FS | 2025-01-02 07:00 | 2025-01-30 17:00
C-52-0405-CNM18-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-0405-CNM18-1000 | C-52-0405-CNM18-1000: FS | C-52-0405-CNM18-1030 | C-52-0405-CNM18-1030: FS | 2025-01-31 07:00 | 2025-02-04 17:00
C-52-0405-CNM18-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 | Driving & Receiving Pit Excavation | C-52-0405-CNM18-1000 | C-52-0405-CNM18-1000: FS | C-52-0405-CNM18-1030 | C-52-0405-CNM18-1030: FF | 2025-01-31 07:00 | 2025-02-20 17:00
C-52-0405-CNM18-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNM18-1010, C-52-0405-CNM18-1020 | C-52-0405-CNM18-1010: FF, C-52-0405-CNM18-1020: FS | C-52-0405-CNM18-1040 | C-52-0405-CNM18-1040: FS | 2025-02-05 07:00 | 2025-02-20 17:00
C-52-0405-CNM18-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 | Floor Blinding & French Drain in Driving Pit | C-52-0405-CNM18-1030 | C-52-0405-CNM18-1030: FS | C-52-0405-CNM18-1050 | C-52-0405-CNM18-1050: FS | 2025-02-21 07:00 | 2025-02-27 17:00
C-52-0405-CNM18-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0405-CNM18-1040 | C-52-0405-CNM18-1040: FS | C-52-0405-CNM18-1060 | C-52-0405-CNM18-1060: SS 7 | 2025-02-28 07:00 | 2025-03-08 11:00
C-52-0405-CNM18-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 | Construction of Exit Wall with Ring | C-52-0405-CNM18-1050 | C-52-0405-CNM18-1050: SS 7 | C-52-0405-CNM18-1200 | C-52-0405-CNM18-1200: FS | 2025-03-09 11:00 | 2025-03-18 13:00
C-52-0405-CNM18-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.3.2 | Jacking of MTBM & RC Sleeves | C-52-0405-CNM18-1060 | C-52-0405-CNM18-1060: FS | C-52-0405-CNM18-1210 | C-52-0405-CNM18-1210: FS | 2025-03-19 07:00 | 2025-04-10 13:00
C-52-0405-CNM18-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.3.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0405-CNM18-1200 | C-52-0405-CNM18-1200: FS | C-52-0405-CNM18-1400 | C-52-0405-CNM18-1400: FS | 2025-04-10 13:00 | 2025-04-15 13:00
C-52-0405-CNM18-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.3.3 | Lowering & Welding of Carrier Pipe | C-52-0405-CNM18-1210 | C-52-0405-CNM18-1210: FS | C-52-0405-CNM18-1410, C-52-0405-PL-ME-4810 | C-52-0405-CNM18-1410: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-04-15 13:00 | 2025-05-03 13:00
C-52-0405-CNM18-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.3.3 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0405-CNM18-1400 | C-52-0405-CNM18-1400: SS 1 | C-52-0405-CNM18-1600 | C-52-0405-CNM18-1600: FS | 2025-04-16 13:00 | 2025-05-08 10:00
C-52-0405-CNM18-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.3.4 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0405-CNM18-1410 | C-52-0405-CNM18-1410: FS | C-52-0405-CNM18-1220 | C-52-0405-CNM18-1220: FS | 2025-05-08 10:00 | 2025-05-17 11:00
C-52-0405-CNM18-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.3.2 | Inner Grout b/w Main & RC Pipe | C-52-0405-CNM18-1600 | C-52-0405-CNM18-1600: FS | C-52-0405-CNM18-1800, C-52-0405-PL-CA-5220 | C-52-0405-CNM18-1800: FS, C-52-0405-PL-CA-5220: FF 1 | 2025-05-17 11:00 | 2025-05-23 11:00
C-52-0405-CNM18-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.3.5 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0405-CNM18-1220 | C-52-0405-CNM18-1220: FS | C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, PRECOM-52-0405-1000, ML1679-E13 | C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, PRECOM-52-0405-1000: FS, ML1679-E13: FS | 2025-05-23 11:00 | 2025-06-11 11:00
C-52-0405-CNH19-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1210 | C-PER-1210: SS | C-52-0405-CNH19-1020, C-52-0405-CNH19-1010 | C-52-0405-CNH19-1020: FS, C-52-0405-CNH19-1010: FS | 2024-11-04 07:30 | 2024-12-17 07:30
C-52-0405-CNH19-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-0405-CNH19-1000 | C-52-0405-CNH19-1000: FS | C-52-0405-CNH19-1030 | C-52-0405-CNH19-1030: FS | 2024-12-17 07:30 | 2024-12-21 07:30
C-52-0405-CNH19-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 | Driving & Receiving Pit Excavation | C-52-0405-CNH19-1000 | C-52-0405-CNH19-1000: FS | C-52-0405-CNH19-1030 | C-52-0405-CNH19-1030: FF | 2024-12-17 07:30 | 2025-01-11 07:30
C-52-0405-CNH19-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNH19-1010, C-52-0405-CNH19-1020 | C-52-0405-CNH19-1010: FF, C-52-0405-CNH19-1020: FS | C-52-0405-CNH19-1040 | C-52-0405-CNH19-1040: FS | 2024-12-21 07:30 | 2025-01-11 07:30
C-52-0405-CNH19-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 | Floor Blinding & French Drain in Driving Pit | C-52-0405-CNH19-1030 | C-52-0405-CNH19-1030: FS | C-52-0405-CNH19-1050 | C-52-0405-CNH19-1050: FS | 2025-01-11 07:30 | 2025-01-21 07:30
C-52-0405-CNH19-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0405-CNH19-1040 | C-52-0405-CNH19-1040: FS | C-52-0405-CNH19-1060 | C-52-0405-CNH19-1060: FS | 2025-01-21 07:30 | 2025-01-30 07:30
C-52-0405-CNH19-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 | Construction of Exit Wall with Ring | C-52-0405-CNH19-1050 | C-52-0405-CNH19-1050: FS | C-52-0405-CNH19-1200 | C-52-0405-CNH19-1200: FS | 2025-01-30 07:30 | 2025-02-08 07:30
C-52-0405-CNH19-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.4.2 | Jacking of MTBM & RC Sleeves | C-52-0405-CNH19-1060 | C-52-0405-CNH19-1060: FS | C-52-0405-CNH19-1210, C-52-06CR-CNM31-1200 | C-52-0405-CNH19-1210: FS, C-52-06CR-CNM31-1200: FS | 2025-02-08 07:30 | 2025-03-01 07:30
C-52-0405-CNH19-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.4.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0405-CNH19-1200 | C-52-0405-CNH19-1200: FS | C-52-0405-CNH19-1070 | C-52-0405-CNH19-1070: FS | 2025-03-01 07:30 | 2025-03-07 07:30
C-52-0405-CNH19-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 | Lowering & Welding of Carrier Pipe | C-52-0405-CNH19-1210 | C-52-0405-CNH19-1210: FS | C-52-0405-CNH19-1080, C-52-0405-PL-ME-4810 | C-52-0405-CNH19-1080: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-03-07 07:30 | 2025-04-14 13:30
C-52-0405-CNH19-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0405-CNH19-1070 | C-52-0405-CNH19-1070: SS 1 | C-52-0405-CNH19-1090 | C-52-0405-CNH19-1090: FS | 2025-03-08 11:30 | 2025-04-17 13:30
C-52-0405-CNH19-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0405-CNH19-1080 | C-52-0405-CNH19-1080: FS | C-52-0405-CNH19-1220 | C-52-0405-CNH19-1220: FS 10 | 2025-04-17 13:30 | 2025-05-01 13:30
C-52-0405-CNH19-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.4.2 | Inner Grout b/w Main & RC Pipe | C-52-0405-CNH19-1090 | C-52-0405-CNH19-1090: FS 10 | C-52-0405-CNH19-1800, C-52-0405-PL-CA-5220 | C-52-0405-CNH19-1800: FS, C-52-0405-PL-CA-5220: FF 1 | 2025-05-14 11:30 | 2025-05-20 11:30
C-52-0405-CNH19-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.4.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0405-CNH19-1220 | C-52-0405-CNH19-1220: FS | C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, PRECOM-52-0405-1000, ML1679-E13 | C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, PRECOM-52-0405-1000: FS, ML1679-E13: FS | 2025-05-20 11:30 | 2025-06-07 11:30
C-52-0405-CNH20-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1220 | C-PER-1220: FS | C-52-0405-CNH20-1020, C-52-0405-CNH20-1010 | C-52-0405-CNH20-1020: FS, C-52-0405-CNH20-1010: FS | 2024-11-13 07:00 | 2024-11-29 17:00
C-52-0405-CNH20-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-0405-CNH20-1000 | C-52-0405-CNH20-1000: FS | C-52-0405-CNH20-1030 | C-52-0405-CNH20-1030: FS | 2024-11-30 07:00 | 2024-12-06 17:00
C-52-0405-CNH20-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 | Driving & Receiving Pit Excavation | C-52-0405-CNH20-1000 | C-52-0405-CNH20-1000: FS | C-52-0405-CNH20-1030 | C-52-0405-CNH20-1030: FF | 2024-11-30 07:00 | 2024-12-18 17:00
C-52-0405-CNH20-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNH20-1010, C-52-0405-CNH20-1020 | C-52-0405-CNH20-1010: FF, C-52-0405-CNH20-1020: FS | C-52-0405-CNH20-1040 | C-52-0405-CNH20-1040: FS | 2024-12-07 07:00 | 2024-12-18 17:00
C-52-0405-CNH20-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 | Floor Blinding & French Drain in Driving Pit | C-52-0405-CNH20-1030 | C-52-0405-CNH20-1030: FS | C-52-0405-CNH20-1050 | C-52-0405-CNH20-1050: FS | 2024-12-19 07:00 | 2024-12-25 17:00
C-52-0405-CNH20-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0405-CNH20-1040 | C-52-0405-CNH20-1040: FS | C-52-0405-CNH20-1060 | C-52-0405-CNH20-1060: FS | 2024-12-26 07:00 | 2025-01-02 17:00
C-52-0405-CNH20-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 | Construction of Exit Wall with Ring | C-52-0405-CNH20-1050 | C-52-0405-CNH20-1050: FS | C-52-0405-CNH20-1200 | C-52-0405-CNH20-1200: FS | 2025-01-03 07:00 | 2025-01-09 17:00
C-52-0405-CNH20-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 | Jacking of MTBM & RC Sleeves | C-52-0405-CNH20-1060 | C-52-0405-CNH20-1060: FS | C-52-0405-CNH20-1210, C-52-06CR-CNM31-1200, C-52-06CR-PL-ME-4810, C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, PRECOM-52-06CR-1000, ML1679-E13, C-52-06CR-CNM31-1200 | C-52-0405-CNH20-1210: FS, C-52-06CR-CNM31-1200: FS, C-52-06CR-PL-ME-4810: FF, C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF, PRECOM-52-06CR-1000: FS, ML1679-E13: FS, C-52-06CR-CNM31-1200: FF | 2025-01-10 07:00 | 2025-02-08 17:00
C-52-0405-CNH20-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0405-CNH20-1200 | C-52-0405-CNH20-1200: FS | C-52-0405-CNH20-1070 | C-52-0405-CNH20-1070: FS | 2025-02-10 07:00 | 2025-02-13 17:00
C-52-0405-CNH20-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 | Lowering & Welding of Carrier Pipe | C-52-0405-CNH20-1210 | C-52-0405-CNH20-1210: FS | C-52-0405-CNH20-1080, C-52-0405-PL-ME-4810 | C-52-0405-CNH20-1080: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-02-14 07:00 | 2025-03-11 09:00
C-52-0405-CNH20-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0405-CNH20-1070 | C-52-0405-CNH20-1070: SS 1 | C-52-0405-CNH20-1090 | C-52-0405-CNH20-1090: FS | 2025-02-15 07:00 | 2025-03-12 13:00
C-52-0405-CNH20-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0405-CNH20-1080 | C-52-0405-CNH20-1080: FS | C-52-0405-CNH20-1220 | C-52-0405-CNH20-1220: FS 10 | 2025-03-13 07:00 | 2025-03-28 09:00
C-52-0405-CNH20-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 | Inner Grout b/w Main & RC Pipe | C-52-0405-CNH20-1090 | C-52-0405-CNH20-1090: FS 10 | C-52-0405-CNH20-1800, C-52-0405-PL-CA-5220 | C-52-0405-CNH20-1800: FS, C-52-0405-PL-CA-5220: FF 1 | 2025-04-12 13:00 | 2025-04-18 13:00
C-52-0405-CNH20-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.5.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0405-CNH20-1220 | C-52-0405-CNH20-1220: FS | C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, PRECOM-52-0405-1000, ML1679-E13 | C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, PRECOM-52-0405-1000: FS, ML1679-E13: FS | 2025-04-18 13:00 | 2025-05-05 14:00
C-52-0405-CNM23-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1250 | C-PER-1250: FS | C-52-0405-CNM23-1020, C-52-0405-CNM23-1010 | C-52-0405-CNM23-1020: FS, C-52-0405-CNM23-1010: FS | 2024-11-19 07:00 | 2024-12-31 17:00
C-52-0405-CNM23-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-0405-CNM23-1000 | C-52-0405-CNM23-1000: FS | C-52-0405-CNM23-1030 | C-52-0405-CNM23-1030: FS | 2025-01-02 07:00 | 2025-01-06 17:00
C-52-0405-CNM23-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 | Driving & Receiving Pit Excavation | C-52-0405-CNM23-1000 | C-52-0405-CNM23-1000: FS | C-52-0405-CNM23-1030 | C-52-0405-CNM23-1030: FF | 2025-01-02 07:00 | 2025-01-30 17:00
C-52-0405-CNM23-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNM23-1010, C-52-0405-CNM23-1020 | C-52-0405-CNM23-1010: FF, C-52-0405-CNM23-1020: FS | C-52-0405-CNM23-1040 | C-52-0405-CNM23-1040: FS | 2025-01-07 07:00 | 2025-01-30 17:00
C-52-0405-CNM23-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 | Floor Blinding & French Drain in Driving Pit | C-52-0405-CNM23-1030 | C-52-0405-CNM23-1030: FS | C-52-0405-CNM23-1050 | C-52-0405-CNM23-1050: FS | 2025-01-31 07:00 | 2025-02-06 17:00
C-52-0405-CNM23-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0405-CNM23-1040 | C-52-0405-CNM23-1040: FS | C-52-0405-CNM23-1060 | C-52-0405-CNM23-1060: SS 7 | 2025-02-07 07:00 | 2025-02-13 17:00
C-52-0405-CNM23-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 | Construction of Exit Wall with Ring | C-52-0405-CNM23-1050 | C-52-0405-CNM23-1050: SS 7 | C-52-0405-CNM23-1200 | C-52-0405-CNM23-1200: FS | 2025-02-15 07:00 | 2025-02-20 17:00
C-52-0405-CNM23-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.6.2 | Jacking of MTBM & RC Sleeves | C-52-0405-CNM23-1060 | C-52-0405-CNM23-1060: FS | C-52-0405-CNM23-1210 | C-52-0405-CNM23-1210: FS | 2025-02-21 07:00 | 2025-03-24 13:00
C-52-0405-CNM23-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.6.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0405-CNM23-1200 | C-52-0405-CNM23-1200: FS | C-52-0405-CNM23-1400 | C-52-0405-CNM23-1400: FS | 2025-03-25 07:00 | 2025-04-03 13:00
C-52-0405-CNM23-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.6.3 | Lowering & Welding of Carrier Pipe | C-52-0405-CNM23-1210 | C-52-0405-CNM23-1210: FS | C-52-0405-CNM23-1410, C-52-0405-PL-ME-4810 | C-52-0405-CNM23-1410: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-04-03 13:00 | 2025-05-05 14:00
C-52-0405-CNM23-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.6.3 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0405-CNM23-1400 | C-52-0405-CNM23-1400: SS 1 | C-52-0405-CNM23-1600 | C-52-0405-CNM23-1600: FS | 2025-04-04 13:00 | 2025-05-06 16:00
C-52-0405-CNM23-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.6.4 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0405-CNM23-1410 | C-52-0405-CNM23-1410: FS | C-52-0405-CNM23-1220 | C-52-0405-CNM23-1220: FS | 2025-05-07 08:00 | 2025-05-23 11:00
C-52-0405-CNM23-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.6.2 | Inner Grout b/w Main & RC Pipe | C-52-0405-CNM23-1600 | C-52-0405-CNM23-1600: FS | C-52-0405-CNM23-1800, C-52-0405-PL-CA-5220 | C-52-0405-CNM23-1800: FS, C-52-0405-PL-CA-5220: FF 1 | 2025-05-23 11:00 | 2025-05-29 11:00
C-52-0405-CNM23-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.6.5 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0405-CNM23-1220 | C-52-0405-CNM23-1220: FS | C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, PRECOM-52-0405-1000, ML1679-E13 | C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, PRECOM-52-0405-1000: FS, ML1679-E13: FS | 2025-05-29 11:00 | 2025-06-17 11:00
C-52-0405-CNH24-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1260 | C-PER-1260: FS | C-52-0405-CNH24-1020, C-52-0405-CNH24-1010 | C-52-0405-CNH24-1020: FS, C-52-0405-CNH24-1010: SS 21 | 2024-12-10 07:00 | 2024-12-25 17:00
C-52-0405-CNH24-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-0405-CNH24-1000 | C-52-0405-CNH24-1000: FS | C-52-0405-CNH24-1030 | C-52-0405-CNH24-1030: FS | 2024-12-26 07:00 | 2024-12-30 17:00
C-52-0405-CNH24-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 | Driving & Receiving Pit Excavation | C-52-0405-CNH24-1000 | C-52-0405-CNH24-1000: SS 21 | C-52-0405-CNH24-1030 | C-52-0405-CNH24-1030: SS 7 | 2025-01-04 07:00 | 2025-01-20 17:00
C-52-0405-CNH24-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNH24-1010, C-52-0405-CNH24-1020 | C-52-0405-CNH24-1010: SS 7, C-52-0405-CNH24-1020: FS | C-52-0405-CNH24-1040 | C-52-0405-CNH24-1040: FS | 2025-01-13 07:00 | 2025-01-23 17:00
C-52-0405-CNH24-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 | Floor Blinding & French Drain in Driving Pit | C-52-0405-CNH24-1030 | C-52-0405-CNH24-1030: FS | C-52-0405-CNH24-1050 | C-52-0405-CNH24-1050: FS | 2025-01-24 07:00 | 2025-01-29 17:00
C-52-0405-CNH24-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0405-CNH24-1040 | C-52-0405-CNH24-1040: FS | C-52-0405-CNH24-1060 | C-52-0405-CNH24-1060: SS 7 | 2025-01-30 07:00 | 2025-02-04 17:00
C-52-0405-CNH24-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 | Construction of Exit Wall with Ring | C-52-0405-CNH24-1050 | C-52-0405-CNH24-1050: SS 7 | C-52-0405-CNH24-1200 | C-52-0405-CNH24-1200: FS | 2025-02-07 07:00 | 2025-02-12 17:00
C-52-0405-CNH24-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.7.2 | Jacking of MTBM & RC Sleeves | C-52-0405-CNH24-1060 | C-52-0405-CNH24-1060: FS | C-52-0405-CNH24-1210 | C-52-0405-CNH24-1210: FS | 2025-02-13 07:00 | 2025-03-24 13:00
C-52-0405-CNH24-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.7.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0405-CNH24-1200 | C-52-0405-CNH24-1200: FS | C-52-0405-CNH24-1070 | C-52-0405-CNH24-1070: FS | 2025-03-25 07:00 | 2025-04-03 13:00
C-52-0405-CNH24-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 | Lowering & Welding of Carrier Pipe | C-52-0405-CNH24-1210 | C-52-0405-CNH24-1210: FS | C-52-0405-CNH24-1080, C-52-0405-PL-ME-4810 | C-52-0405-CNH24-1080: SS 1, C-52-0405-PL-ME-4810: FF 1 | 2025-04-03 13:00 | 2025-05-21 11:00
C-52-0405-CNH24-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0405-CNH24-1070 | C-52-0405-CNH24-1070: SS 1 | C-52-0405-CNH24-1090 | C-52-0405-CNH24-1090: FS | 2025-04-04 13:00 | 2025-05-22 11:00
C-52-0405-CNH24-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0405-CNH24-1080 | C-52-0405-CNH24-1080: FS | C-52-0405-CNH24-1220 | C-52-0405-CNH24-1220: FS 1 | 2025-05-22 11:00 | 2025-05-30 11:00
C-52-0405-CNH24-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.7.2 | Inner Grout b/w Main & RC Pipe | C-52-0405-CNH24-1090 | C-52-0405-CNH24-1090: FS 1 | C-52-0405-CNH24-1800, C-52-0405-PL-CA-5220 | C-52-0405-CNH24-1800: FS, C-52-0405-PL-CA-5220: FF 1 | 2025-05-31 11:00 | 2025-06-09 11:00
C-52-0405-CNH24-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.8.7.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0405-CNH24-1220 | C-52-0405-CNH24-1220: FS | C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, PRECOM-52-0405-1000, ML1679-E13 | C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, PRECOM-52-0405-1000: FS, ML1679-E13: FS | 2025-06-09 11:00 | 2025-06-17 11:00
C-52-0506-CNH27-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1300 | C-PER-1300: FS | C-52-0506-CNH27-1020, C-52-0506-CNH27-1010 | C-52-0506-CNH27-1020: FS, C-52-0506-CNH27-1010: FS | 2024-12-25 07:00 | 2025-01-14 09:30
C-52-0506-CNH27-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-0506-CNH27-1000 | C-52-0506-CNH27-1000: FS | C-52-0506-CNH27-1030 | C-52-0506-CNH27-1030: FS | 2025-01-14 09:30 | 2025-01-18 09:30
C-52-0506-CNH27-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 | Driving & Receiving Pit Excavation | C-52-0506-CNH27-1000 | C-52-0506-CNH27-1000: FS | C-52-0506-CNH27-1030 | C-52-0506-CNH27-1030: FF | 2025-01-14 09:30 | 2025-01-30 09:30
C-52-0506-CNH27-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0506-CNH27-1010, C-52-0506-CNH27-1020 | C-52-0506-CNH27-1010: FF, C-52-0506-CNH27-1020: FS | C-52-0506-CNH27-1040 | C-52-0506-CNH27-1040: FS | 2025-01-18 09:30 | 2025-01-30 09:30
C-52-0506-CNH27-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 | Floor Blinding & French Drain in Driving Pit | C-52-0506-CNH27-1030 | C-52-0506-CNH27-1030: FS | C-52-0506-CNH27-1050 | C-52-0506-CNH27-1050: FS | 2025-01-30 09:30 | 2025-02-06 09:30
C-52-0506-CNH27-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0506-CNH27-1040 | C-52-0506-CNH27-1040: FS | C-52-0506-CNH27-1060 | C-52-0506-CNH27-1060: SS 7 | 2025-02-06 09:30 | 2025-02-13 09:30
C-52-0506-CNH27-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 | Construction of Exit Wall with Ring | C-52-0506-CNH27-1050 | C-52-0506-CNH27-1050: SS 7 | C-52-0506-CNH27-1200 | C-52-0506-CNH27-1200: FS | 2025-02-14 09:30 | 2025-02-21 09:30
C-52-0506-CNH27-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.3.1.2 | Jacking of MTBM & RC Sleeves | C-52-0506-CNH27-1060 | C-52-0506-CNH27-1060: FS | C-52-0506-CNH27-1210 | C-52-0506-CNH27-1210: FS | 2025-02-21 09:30 | 2025-04-07 15:30
C-52-0506-CNH27-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.3.1.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0506-CNH27-1200 | C-52-0506-CNH27-1200: FS | C-52-0506-CNH27-1070 | C-52-0506-CNH27-1070: FS | 2025-04-07 15:30 | 2025-04-11 15:30
C-52-0506-CNH27-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 | Lowering & Welding of Carrier Pipe | C-52-0506-CNH27-1210 | C-52-0506-CNH27-1210: FS | C-52-0506-CNH27-1080, C-52-0506-PL-ME-4810 | C-52-0506-CNH27-1080: SS 1, C-52-0506-PL-ME-4810: FF | 2025-04-11 15:30 | 2025-05-29 13:30
C-52-0506-CNH27-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0506-CNH27-1070 | C-52-0506-CNH27-1070: SS 1 | C-52-0506-CNH27-1090 | C-52-0506-CNH27-1090: FS | 2025-04-12 15:30 | 2025-05-30 13:30
C-52-0506-CNH27-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0506-CNH27-1080 | C-52-0506-CNH27-1080: FS | C-52-0506-CNH27-1220 | C-52-0506-CNH27-1220: FS | 2025-05-30 13:30 | 2025-06-16 13:30
C-52-0506-CNH27-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.3.1.2 | Inner Grout b/w Main & RC Pipe | C-52-0506-CNH27-1090 | C-52-0506-CNH27-1090: FS | C-52-0506-CNH27-1800, C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200 | C-52-0506-CNH27-1800: FS, C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF | 2025-06-16 13:30 | 2025-06-21 13:30
C-52-0506-CNH27-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.3.1.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0506-CNH27-1220 | C-52-0506-CNH27-1220: FS | C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, PRECOM-52-0506-1000, C-52-0506-PL-CI-6000, ML1679-E13 | C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, PRECOM-52-0506-1000: FS, C-52-0506-PL-CI-6000: FF, ML1679-E13: FS | 2025-06-21 13:30 | 2025-07-09 13:30
C-52-0506-CMA06-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 | Trench Excavation | C-52-0405-CME08-1000 | C-52-0405-CME08-1000: FS 4 | C-52-0506-CMA06-1010, C-52-0506-CMA04-1000 | C-52-0506-CMA06-1010: FF, C-52-0506-CMA04-1000: FS | 2025-01-15 12:00 | 2025-01-24 12:00
C-52-0506-CMA06-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 | Bedding | C-52-0506-CMA06-1000 | C-52-0506-CMA06-1000: FF | C-52-0506-CMA06-1020 | C-52-0506-CMA06-1020: FS | 2025-01-23 12:00 | 2025-01-24 12:00
C-52-0506-CMA06-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 | Lowering | C-52-0506-CMA06-1010 | C-52-0506-CMA06-1010: FS | C-52-0506-CMA06-1030 | C-52-0506-CMA06-1030: SS | 2025-01-24 12:00 | 2025-01-25 12:00
C-52-0506-CMA06-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 | Section Tie-in Welding | C-52-0506-CMA06-1020 | C-52-0506-CMA06-1020: SS | C-52-0506-CMA06-1040, C-52-0506-PL-ME-4810 | C-52-0506-CMA06-1040: SS 1, C-52-0506-PL-ME-4810: FF | 2025-01-24 12:00 | 2025-01-27 12:00
C-52-0506-CMA06-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 | NDT (Tie-in Joint) | C-52-0506-CMA06-1030 | C-52-0506-CMA06-1030: SS 1 | C-52-0506-CMA06-1050 | C-52-0506-CMA06-1050: SS 1 | 2025-01-25 12:00 | 2025-01-28 12:00
C-52-0506-CMA06-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA06-1040 | C-52-0506-CMA06-1040: SS 1 | C-52-0506-CMA06-1060 | C-52-0506-CMA06-1060: FS | 2025-01-27 12:00 | 2025-01-29 12:00
C-52-0506-CMA06-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 | Holiday Testing | C-52-0506-CMA06-1050 | C-52-0506-CMA06-1050: FS | C-52-0506-CMA06-1070, C-52-0506-PL-CA-5220 | C-52-0506-CMA06-1070: FS, C-52-0506-PL-CA-5220: SS | 2025-01-29 12:00 | 2025-01-30 12:00
C-52-0506-CMA06-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 | Padding | C-52-0506-CMA06-1060 | C-52-0506-CMA06-1060: FS | C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-01-30 12:00 | 2025-01-31 12:00
C-52-0506-CMA07-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 | Trench Excavation | C-52-0405-CMA32-1000 | C-52-0405-CMA32-1000: FS | C-52-0506-CMA07-1010, C-52-0506-CMA02-1000 | C-52-0506-CMA07-1010: FF, C-52-0506-CMA02-1000: FS | 2025-03-08 16:00 | 2025-03-21 10:00
C-52-0506-CMA07-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 | Bedding | C-52-0506-CMA07-1000 | C-52-0506-CMA07-1000: FF | C-52-0506-CMA07-1020 | C-52-0506-CMA07-1020: FS | 2025-03-19 12:00 | 2025-03-21 10:00
C-52-0506-CMA07-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 | Lowering | C-52-0506-CMA07-1010 | C-52-0506-CMA07-1010: FS | C-52-0506-CMA07-1030 | C-52-0506-CMA07-1030: SS | 2025-03-21 10:00 | 2025-03-22 14:00
C-52-0506-CMA07-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 | Section Tie-in Welding | C-52-0506-CMA07-1020 | C-52-0506-CMA07-1020: SS | C-52-0506-CMA07-1040, C-52-0506-PL-ME-4810 | C-52-0506-CMA07-1040: SS 1, C-52-0506-PL-ME-4810: FF | 2025-03-21 10:00 | 2025-03-24 08:00
C-52-0506-CMA07-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 | NDT (Tie-in Joint) | C-52-0506-CMA07-1030 | C-52-0506-CMA07-1030: SS 1 | C-52-0506-CMA07-1050 | C-52-0506-CMA07-1050: SS 1 | 2025-03-22 14:00 | 2025-03-25 12:00
C-52-0506-CMA07-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA07-1040 | C-52-0506-CMA07-1040: SS 1 | C-52-0506-CMA07-1060 | C-52-0506-CMA07-1060: FS | 2025-03-24 08:00 | 2025-03-27 10:00
C-52-0506-CMA07-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 | Holiday Testing | C-52-0506-CMA07-1050 | C-52-0506-CMA07-1050: FS | C-52-0506-CMA07-1070 | C-52-0506-CMA07-1070: FS | 2025-03-27 10:00 | 2025-03-29 08:00
C-52-0506-CMA07-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 | Padding | C-52-0506-CMA07-1060 | C-52-0506-CMA07-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-03-29 08:00 | 2025-04-03 08:00
C-52-0506-CMA04-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 | Trench Excavation | C-52-0506-CMA06-1000 | C-52-0506-CMA06-1000: FS | C-52-0506-CMA04-1010, C-52-0506-CMA08-1000 | C-52-0506-CMA04-1010: FF, C-52-0506-CMA08-1000: FS | 2025-01-24 12:00 | 2025-01-31 12:00
C-52-0506-CMA04-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 | Bedding | C-52-0506-CMA04-1000 | C-52-0506-CMA04-1000: FF | C-52-0506-CMA04-1020 | C-52-0506-CMA04-1020: FS | 2025-01-30 12:00 | 2025-01-31 12:00
C-52-0506-CMA04-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 | Lowering | C-52-0506-CMA04-1010 | C-52-0506-CMA04-1010: FS | C-52-0506-CMA04-1030 | C-52-0506-CMA04-1030: SS | 2025-01-31 12:00 | 2025-02-01 12:00
C-52-0506-CMA04-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 | Section Tie-in Welding | C-52-0506-CMA04-1020 | C-52-0506-CMA04-1020: SS | C-52-0506-CMA04-1040, C-52-0506-PL-ME-4810 | C-52-0506-CMA04-1040: SS 1, C-52-0506-PL-ME-4810: FF | 2025-01-31 12:00 | 2025-02-03 12:00
C-52-0506-CMA04-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 | NDT (Tie-in Joint) | C-52-0506-CMA04-1030 | C-52-0506-CMA04-1030: SS 1 | C-52-0506-CMA04-1050 | C-52-0506-CMA04-1050: SS 1 | 2025-02-01 12:00 | 2025-02-04 12:00
C-52-0506-CMA04-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA04-1040 | C-52-0506-CMA04-1040: SS 1 | C-52-0506-CMA04-1060 | C-52-0506-CMA04-1060: FS | 2025-02-03 12:00 | 2025-02-05 12:00
C-52-0506-CMA04-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 | Holiday Testing | C-52-0506-CMA04-1050 | C-52-0506-CMA04-1050: FS | C-52-0506-CMA04-1070 | C-52-0506-CMA04-1070: FS | 2025-02-05 12:00 | 2025-02-06 12:00
C-52-0506-CMA04-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 | Padding | C-52-0506-CMA04-1060 | C-52-0506-CMA04-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-02-06 12:00 | 2025-02-07 12:00
C-52-0506-CMA02-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 | Trench Excavation | C-52-0506-CMA07-1000 | C-52-0506-CMA07-1000: FS | C-52-0506-CMA02-1010, C-52-0506-CMA09-1000 | C-52-0506-CMA02-1010: FF, C-52-0506-CMA09-1000: SS | 2025-03-21 10:00 | 2025-04-10 08:00
C-52-0506-CMA02-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 | Bedding | C-52-0506-CMA02-1000 | C-52-0506-CMA02-1000: FF | C-52-0506-CMA02-1020 | C-52-0506-CMA02-1020: FS | 2025-04-09 08:00 | 2025-04-10 08:00
C-52-0506-CMA02-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 | Lowering | C-52-0506-CMA02-1010 | C-52-0506-CMA02-1010: FS | C-52-0506-CMA02-1030 | C-52-0506-CMA02-1030: SS | 2025-04-10 08:00 | 2025-04-11 08:00
C-52-0506-CMA02-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 | Section Tie-in Welding | C-52-0506-CMA02-1020 | C-52-0506-CMA02-1020: SS | C-52-0506-CMA02-1040, C-52-0506-PL-ME-4810 | C-52-0506-CMA02-1040: SS 1, C-52-0506-PL-ME-4810: FF | 2025-04-10 08:00 | 2025-04-12 08:00
C-52-0506-CMA02-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 | NDT (Tie-in Joint) | C-52-0506-CMA02-1030 | C-52-0506-CMA02-1030: SS 1 | C-52-0506-CMA02-1050 | C-52-0506-CMA02-1050: SS 1 | 2025-04-11 08:00 | 2025-04-14 08:00
C-52-0506-CMA02-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA02-1040 | C-52-0506-CMA02-1040: SS 1 | C-52-0506-CMA02-1060 | C-52-0506-CMA02-1060: FS | 2025-04-12 08:00 | 2025-04-15 08:00
C-52-0506-CMA02-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 | Holiday Testing | C-52-0506-CMA02-1050 | C-52-0506-CMA02-1050: FS | C-52-0506-CMA02-1070 | C-52-0506-CMA02-1070: FS | 2025-04-15 08:00 | 2025-04-16 08:00
C-52-0506-CMA02-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 | Padding | C-52-0506-CMA02-1060 | C-52-0506-CMA02-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-04-16 08:00 | 2025-04-17 08:00
C-52-0506-CMA08-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 | Trench Excavation | C-52-0506-CMA04-1000 | C-52-0506-CMA04-1000: FS | C-52-0506-CMA08-1010, C-52-0506-CMA03-1000 | C-52-0506-CMA08-1010: FF, C-52-0506-CMA03-1000: FS | 2025-01-31 12:00 | 2025-02-10 12:00
C-52-0506-CMA08-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 | Bedding | C-52-0506-CMA08-1000 | C-52-0506-CMA08-1000: FF | C-52-0506-CMA08-1020 | C-52-0506-CMA08-1020: FS | 2025-02-08 12:00 | 2025-02-10 12:00
C-52-0506-CMA08-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 | Lowering | C-52-0506-CMA08-1010 | C-52-0506-CMA08-1010: FS | C-52-0506-CMA08-1030 | C-52-0506-CMA08-1030: SS | 2025-02-10 12:00 | 2025-02-11 12:00
C-52-0506-CMA08-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 | Section Tie-in Welding | C-52-0506-CMA08-1020 | C-52-0506-CMA08-1020: SS | C-52-0506-CMA08-1040, C-52-0506-PL-ME-4810 | C-52-0506-CMA08-1040: SS 1, C-52-0506-PL-ME-4810: FF | 2025-02-10 12:00 | 2025-02-12 12:00
C-52-0506-CMA08-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 | NDT (Tie-in Joint) | C-52-0506-CMA08-1030 | C-52-0506-CMA08-1030: SS 1 | C-52-0506-CMA08-1050 | C-52-0506-CMA08-1050: SS 1 | 2025-02-11 12:00 | 2025-02-13 12:00
C-52-0506-CMA08-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA08-1040 | C-52-0506-CMA08-1040: SS 1 | C-52-0506-CMA08-1060 | C-52-0506-CMA08-1060: FS | 2025-02-12 12:00 | 2025-02-14 12:00
C-52-0506-CMA08-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 | Holiday Testing | C-52-0506-CMA08-1050 | C-52-0506-CMA08-1050: FS | C-52-0506-CMA08-1070 | C-52-0506-CMA08-1070: FS | 2025-02-14 12:00 | 2025-02-15 12:00
C-52-0506-CMA08-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 | Padding | C-52-0506-CMA08-1060 | C-52-0506-CMA08-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-02-15 12:00 | 2025-02-17 12:00
C-52-0506-CMA09-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 | Trench Excavation | C-52-0506-CMA02-1000 | C-52-0506-CMA02-1000: SS | C-52-0506-CMA09-1010, C-52-0506-CMA01-1000 | C-52-0506-CMA09-1010: FF, C-52-0506-CMA01-1000: FS | 2025-03-21 10:00 | 2025-04-08 08:00
C-52-0506-CMA09-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 | Bedding | C-52-0506-CMA09-1000 | C-52-0506-CMA09-1000: FF | C-52-0506-CMA09-1020 | C-52-0506-CMA09-1020: FS | 2025-04-07 08:00 | 2025-04-08 08:00
C-52-0506-CMA09-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 | Lowering | C-52-0506-CMA09-1010 | C-52-0506-CMA09-1010: FS | C-52-0506-CMA09-1030 | C-52-0506-CMA09-1030: SS | 2025-04-08 08:00 | 2025-04-09 08:00
C-52-0506-CMA09-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 | Section Tie-in Welding | C-52-0506-CMA09-1020 | C-52-0506-CMA09-1020: SS | C-52-0506-CMA09-1040, C-52-0506-PL-ME-4810 | C-52-0506-CMA09-1040: SS 1, C-52-0506-PL-ME-4810: FF | 2025-04-08 08:00 | 2025-04-10 08:00
C-52-0506-CMA09-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 | NDT (Tie-in Joint) | C-52-0506-CMA09-1030 | C-52-0506-CMA09-1030: SS 1 | C-52-0506-CMA09-1050 | C-52-0506-CMA09-1050: SS 1 | 2025-04-09 08:00 | 2025-04-11 08:00
C-52-0506-CMA09-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA09-1040 | C-52-0506-CMA09-1040: SS 1 | C-52-0506-CMA09-1060 | C-52-0506-CMA09-1060: FS | 2025-04-10 08:00 | 2025-04-12 08:00
C-52-0506-CMA09-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 | Holiday Testing | C-52-0506-CMA09-1050 | C-52-0506-CMA09-1050: FS | C-52-0506-CMA09-1070 | C-52-0506-CMA09-1070: FS | 2025-04-12 08:00 | 2025-04-14 08:00
C-52-0506-CMA09-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 | Padding | C-52-0506-CMA09-1060 | C-52-0506-CMA09-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-04-14 08:00 | 2025-04-15 08:00
C-52-0506-CMA03-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 | Trench Excavation | C-52-0506-CMA08-1000 | C-52-0506-CMA08-1000: FS | C-52-0506-CMA03-1010, C-52-0506-CMA05-1000 | C-52-0506-CMA03-1010: FF, C-52-0506-CMA05-1000: FS | 2025-02-10 12:00 | 2025-02-24 12:00
C-52-0506-CMA03-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 | Bedding | C-52-0506-CMA03-1000 | C-52-0506-CMA03-1000: FF | C-52-0506-CMA03-1020 | C-52-0506-CMA03-1020: FS | 2025-02-22 12:00 | 2025-02-24 12:00
C-52-0506-CMA03-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 | Lowering | C-52-0506-CMA03-1010 | C-52-0506-CMA03-1010: FS | C-52-0506-CMA03-1030 | C-52-0506-CMA03-1030: SS | 2025-02-24 12:00 | 2025-02-25 12:00
C-52-0506-CMA03-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 | Section Tie-in Welding | C-52-0506-CMA03-1020 | C-52-0506-CMA03-1020: SS | C-52-0506-CMA03-1040, C-52-0506-PL-ME-4810 | C-52-0506-CMA03-1040: SS 1, C-52-0506-PL-ME-4810: FF | 2025-02-24 12:00 | 2025-02-26 12:00
C-52-0506-CMA03-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 | NDT (Tie-in Joint) | C-52-0506-CMA03-1030 | C-52-0506-CMA03-1030: SS 1 | C-52-0506-CMA03-1050 | C-52-0506-CMA03-1050: SS 1 | 2025-02-25 12:00 | 2025-02-27 12:00
C-52-0506-CMA03-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA03-1040 | C-52-0506-CMA03-1040: SS 1 | C-52-0506-CMA03-1060 | C-52-0506-CMA03-1060: FS | 2025-02-26 12:00 | 2025-02-28 12:00
C-52-0506-CMA03-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 | Holiday Testing | C-52-0506-CMA03-1050 | C-52-0506-CMA03-1050: FS | C-52-0506-CMA03-1070 | C-52-0506-CMA03-1070: FS | 2025-02-28 12:00 | 2025-03-01 12:00
C-52-0506-CMA03-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 | Padding | C-52-0506-CMA03-1060 | C-52-0506-CMA03-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-03-01 12:00 | 2025-03-02 12:00
C-52-0506-CMA01-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 | Trench Excavation | C-52-0506-CMA09-1000 | C-52-0506-CMA09-1000: FS | C-52-0506-CMA01-1010 | C-52-0506-CMA01-1010: FF | 2025-04-08 08:00 | 2025-04-15 08:00
C-52-0506-CMA01-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 | Bedding | C-52-0506-CMA01-1000 | C-52-0506-CMA01-1000: FF | C-52-0506-CMA01-1020 | C-52-0506-CMA01-1020: FS | 2025-04-14 08:00 | 2025-04-15 08:00
C-52-0506-CMA01-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 | Lowering | C-52-0506-CMA01-1010 | C-52-0506-CMA01-1010: FS | C-52-0506-CMA01-1030 | C-52-0506-CMA01-1030: SS | 2025-04-15 08:00 | 2025-04-16 08:00
C-52-0506-CMA01-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 | Section Tie-in Welding | C-52-0506-CMA01-1020 | C-52-0506-CMA01-1020: SS | C-52-0506-CMA01-1040, C-52-0506-PL-ME-4810 | C-52-0506-CMA01-1040: SS 1, C-52-0506-PL-ME-4810: FF | 2025-04-15 08:00 | 2025-04-17 08:00
C-52-0506-CMA01-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 | NDT (Tie-in Joint) | C-52-0506-CMA01-1030 | C-52-0506-CMA01-1030: SS 1 | C-52-0506-CMA01-1050 | C-52-0506-CMA01-1050: SS 1 | 2025-04-16 08:00 | 2025-04-18 08:00
C-52-0506-CMA01-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA01-1040 | C-52-0506-CMA01-1040: SS 1 | C-52-0506-CMA01-1060 | C-52-0506-CMA01-1060: FS | 2025-04-17 08:00 | 2025-04-19 08:00
C-52-0506-CMA01-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 | Holiday Testing | C-52-0506-CMA01-1050 | C-52-0506-CMA01-1050: FS | C-52-0506-CMA01-1070 | C-52-0506-CMA01-1070: FS | 2025-04-19 08:00 | 2025-04-21 08:00
C-52-0506-CMA01-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 | Padding | C-52-0506-CMA01-1060 | C-52-0506-CMA01-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-04-21 08:00 | 2025-04-22 08:00
C-52-0506-CMA05-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 | Trench Excavation | C-52-0506-CMA03-1000 | C-52-0506-CMA03-1000: FS | C-52-0506-CMA05-1010 | C-52-0506-CMA05-1010: FF | 2025-02-24 12:00 | 2025-03-02 12:00
C-52-0506-CMA05-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 | Bedding | C-52-0506-CMA05-1000 | C-52-0506-CMA05-1000: FF | C-52-0506-CMA05-1020 | C-52-0506-CMA05-1020: FS | 2025-03-01 12:00 | 2025-03-02 12:00
C-52-0506-CMA05-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 | Lowering | C-52-0506-CMA05-1010 | C-52-0506-CMA05-1010: FS | C-52-0506-CMA05-1030 | C-52-0506-CMA05-1030: SS | 2025-03-02 12:00 | 2025-03-04 10:00
C-52-0506-CMA05-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 | Section Tie-in Welding | C-52-0506-CMA05-1020 | C-52-0506-CMA05-1020: SS | C-52-0506-CMA05-1040, C-52-0506-PL-ME-4810 | C-52-0506-CMA05-1040: SS 1, C-52-0506-PL-ME-4810: FF | 2025-03-02 12:00 | 2025-03-06 08:00
C-52-0506-CMA05-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 | NDT (Tie-in Joint) | C-52-0506-CMA05-1030 | C-52-0506-CMA05-1030: SS 1 | C-52-0506-CMA05-1050 | C-52-0506-CMA05-1050: SS 1 | 2025-03-04 10:00 | 2025-03-07 12:00
C-52-0506-CMA05-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA05-1040 | C-52-0506-CMA05-1040: SS 1 | C-52-0506-CMA05-1060 | C-52-0506-CMA05-1060: FS | 2025-03-06 08:00 | 2025-03-08 16:00
C-52-0506-CMA05-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 | Holiday Testing | C-52-0506-CMA05-1050 | C-52-0506-CMA05-1050: FS | C-52-0506-CMA05-1070 | C-52-0506-CMA05-1070: FS | 2025-03-08 16:00 | 2025-03-10 10:00
C-52-0506-CMA05-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 | Padding | C-52-0506-CMA05-1060 | C-52-0506-CMA05-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-03-10 10:00 | 2025-03-12 08:00
C-52-0506-CME01-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 | Trench Excavation | C-52-0506-PL-ME-2800, C-52-0405-CME11-1000 | C-52-0506-PL-ME-2800: FS 1, C-52-0405-CME11-1000: FS 1 | C-52-0506-CME01-1010, C-52-0506-CME02-1000 | C-52-0506-CME01-1010: FS, C-52-0506-CME02-1000: FS 1 | 2025-04-18 07:00 | 2025-04-19 17:00
C-52-0506-CME01-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 | Bedding | C-52-0506-CME01-1000 | C-52-0506-CME01-1000: FS | C-52-0506-CME01-1020 | C-52-0506-CME01-1020: FS | 2025-04-21 07:00 | 2025-04-22 17:00
C-52-0506-CME01-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 | Lowering | C-52-0506-CME01-1010, C-52-0506-PL-ME-2800 | C-52-0506-CME01-1010: FS, C-52-0506-PL-ME-2800: SS 21 | C-52-0506-CME01-1030, C-52-0506-CME02-1020 | C-52-0506-CME01-1030: FS, C-52-0506-CME02-1020: FS | 2025-04-23 07:00 | 2025-04-24 17:00
C-52-0506-CME01-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 | Section Tie-in Welding | C-52-0506-CME01-1020 | C-52-0506-CME01-1020: FS | C-52-0506-CME01-1040, C-52-0506-PL-ME-4810 | C-52-0506-CME01-1040: FS, C-52-0506-PL-ME-4810: FF | 2025-04-25 07:00 | 2025-04-28 17:00
C-52-0506-CME01-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 | NDT (Tie-in Joint) | C-52-0506-CME01-1030 | C-52-0506-CME01-1030: FS | C-52-0506-CME01-1050 | C-52-0506-CME01-1050: FS | 2025-04-29 07:00 | 2025-05-01 17:00
C-52-0506-CME01-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME01-1040 | C-52-0506-CME01-1040: FS | C-52-0506-CME01-1060 | C-52-0506-CME01-1060: FS | 2025-05-02 07:00 | 2025-05-06 10:00
C-52-0506-CME01-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 | Holiday Testing | C-52-0506-CME01-1050 | C-52-0506-CME01-1050: FS | C-52-0506-CME01-1070 | C-52-0506-CME01-1070: FS | 2025-05-06 10:00 | 2025-05-08 14:00
C-52-0506-CME01-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 | Padding & Back Filling | C-52-0506-CME01-1060 | C-52-0506-CME01-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-05-08 14:00 | 2025-05-10 15:00
C-52-0506-CME02-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 | Trench Excavation | C-52-0506-CME01-1000 | C-52-0506-CME01-1000: FS 1 | C-52-0506-CME02-1010, C-52-0506-CME03-1000 | C-52-0506-CME02-1010: FS, C-52-0506-CME03-1000: FS 1 | 2025-04-22 07:00 | 2025-04-23 17:00
C-52-0506-CME02-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 | Bedding | C-52-0506-CME02-1000 | C-52-0506-CME02-1000: FS | C-52-0506-CME02-1020 | C-52-0506-CME02-1020: FS | 2025-04-24 07:00 | 2025-04-25 17:00
C-52-0506-CME02-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 | Lowering | C-52-0506-CME02-1010, C-52-0506-CME01-1020 | C-52-0506-CME02-1010: FS, C-52-0506-CME01-1020: FS | C-52-0506-CME02-1030, C-52-0506-CME03-1020 | C-52-0506-CME02-1030: FS, C-52-0506-CME03-1020: FS | 2025-04-26 07:00 | 2025-04-28 17:00
C-52-0506-CME02-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 | Section Tie-in Welding | C-52-0506-CME02-1020 | C-52-0506-CME02-1020: FS | C-52-0506-CME02-1040, C-52-0506-PL-ME-4810 | C-52-0506-CME02-1040: FS, C-52-0506-PL-ME-4810: FF | 2025-04-29 07:00 | 2025-05-01 17:00
C-52-0506-CME02-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 | NDT (Tie-in Joint) | C-52-0506-CME02-1030 | C-52-0506-CME02-1030: FS | C-52-0506-CME02-1050 | C-52-0506-CME02-1050: FS | 2025-05-02 07:00 | 2025-05-06 10:00
C-52-0506-CME02-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME02-1040 | C-52-0506-CME02-1040: FS | C-52-0506-CME02-1060 | C-52-0506-CME02-1060: FS | 2025-05-06 10:00 | 2025-05-09 15:00
C-52-0506-CME02-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 | Holiday Testing | C-52-0506-CME02-1050 | C-52-0506-CME02-1050: FS | C-52-0506-CME02-1070 | C-52-0506-CME02-1070: FS | 2025-05-09 15:00 | 2025-05-12 15:00
C-52-0506-CME02-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 | Padding & Back Filling | C-52-0506-CME02-1060 | C-52-0506-CME02-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-05-12 15:00 | 2025-05-14 15:00
C-52-0506-CME03-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 | Trench Excavation | C-52-0506-CME02-1000 | C-52-0506-CME02-1000: FS 1 | C-52-0506-CME03-1010, C-52-0506-CME04-1000 | C-52-0506-CME03-1010: FS, C-52-0506-CME04-1000: FS 1 | 2025-04-25 07:00 | 2025-04-26 17:00
C-52-0506-CME03-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 | Bedding | C-52-0506-CME03-1000 | C-52-0506-CME03-1000: FS | C-52-0506-CME03-1020 | C-52-0506-CME03-1020: FS | 2025-04-28 07:00 | 2025-04-29 17:00
C-52-0506-CME03-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 | Lowering | C-52-0506-CME03-1010, C-52-0506-CME02-1020 | C-52-0506-CME03-1010: FS, C-52-0506-CME02-1020: FS | C-52-0506-CME03-1030, C-52-0506-CME04-1020 | C-52-0506-CME03-1030: FS, C-52-0506-CME04-1020: FS | 2025-04-30 07:00 | 2025-05-01 17:00
C-52-0506-CME03-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 | Section Tie-in Welding | C-52-0506-CME03-1020 | C-52-0506-CME03-1020: FS | C-52-0506-CME03-1040, C-52-0506-PL-ME-4810 | C-52-0506-CME03-1040: FS, C-52-0506-PL-ME-4810: FF | 2025-05-02 07:00 | 2025-05-06 10:00
C-52-0506-CME03-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 | NDT (Tie-in Joint) | C-52-0506-CME03-1030 | C-52-0506-CME03-1030: FS | C-52-0506-CME03-1050 | C-52-0506-CME03-1050: FS | 2025-05-06 10:00 | 2025-05-09 15:00
C-52-0506-CME03-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME03-1040 | C-52-0506-CME03-1040: FS | C-52-0506-CME03-1060 | C-52-0506-CME03-1060: FS | 2025-05-09 15:00 | 2025-05-13 15:00
C-52-0506-CME03-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 | Holiday Testing | C-52-0506-CME03-1050 | C-52-0506-CME03-1050: FS | C-52-0506-CME03-1070 | C-52-0506-CME03-1070: FS | 2025-05-13 15:00 | 2025-05-15 15:00
C-52-0506-CME03-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 | Padding & Back Filling | C-52-0506-CME03-1060 | C-52-0506-CME03-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-05-15 15:00 | 2025-05-17 15:00
C-52-0506-CME04-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 | Trench Excavation | C-52-0506-CME03-1000 | C-52-0506-CME03-1000: FS 1 | C-52-0506-CME04-1010, C-52-0506-CME05-1000 | C-52-0506-CME04-1010: FS, C-52-0506-CME05-1000: FS 1 | 2025-04-29 07:00 | 2025-04-30 17:00
C-52-0506-CME04-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 | Bedding | C-52-0506-CME04-1000 | C-52-0506-CME04-1000: FS | C-52-0506-CME04-1020 | C-52-0506-CME04-1020: FS | 2025-05-01 07:00 | 2025-05-02 17:00
C-52-0506-CME04-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 | Lowering | C-52-0506-CME04-1010, C-52-0506-CME03-1020 | C-52-0506-CME04-1010: FS, C-52-0506-CME03-1020: FS | C-52-0506-CME04-1030, C-52-0506-CME05-1020 | C-52-0506-CME04-1030: FS, C-52-0506-CME05-1020: FS | 2025-05-03 07:00 | 2025-05-06 10:00
C-52-0506-CME04-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 | Section Tie-in Welding | C-52-0506-CME04-1020 | C-52-0506-CME04-1020: FS | C-52-0506-CME04-1040, C-52-0506-PL-ME-4810 | C-52-0506-CME04-1040: FS, C-52-0506-PL-ME-4810: FF | 2025-05-06 10:00 | 2025-05-09 15:00
C-52-0506-CME04-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 | NDT (Tie-in Joint) | C-52-0506-CME04-1030 | C-52-0506-CME04-1030: FS | C-52-0506-CME04-1050 | C-52-0506-CME04-1050: FS | 2025-05-09 15:00 | 2025-05-13 15:00
C-52-0506-CME04-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME04-1040 | C-52-0506-CME04-1040: FS | C-52-0506-CME04-1060 | C-52-0506-CME04-1060: FS | 2025-05-13 15:00 | 2025-05-16 15:00
C-52-0506-CME04-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 | Holiday Testing | C-52-0506-CME04-1050 | C-52-0506-CME04-1050: FS | C-52-0506-CME04-1070 | C-52-0506-CME04-1070: FS | 2025-05-16 15:00 | 2025-05-19 15:00
C-52-0506-CME04-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 | Padding & Back Filling | C-52-0506-CME04-1060 | C-52-0506-CME04-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-05-19 15:00 | 2025-05-21 15:00
C-52-0506-CME05-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 | Trench Excavation | C-52-0506-CME04-1000 | C-52-0506-CME04-1000: FS 1 | C-52-0506-CME05-1010, C-52-0506-CME06-1000 | C-52-0506-CME05-1010: FS, C-52-0506-CME06-1000: FS 1 | 2025-05-02 07:00 | 2025-05-03 17:00
C-52-0506-CME05-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 | Bedding | C-52-0506-CME05-1000 | C-52-0506-CME05-1000: FS | C-52-0506-CME05-1020 | C-52-0506-CME05-1020: FS | 2025-05-05 08:00 | 2025-05-07 12:00
C-52-0506-CME05-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 | Lowering | C-52-0506-CME05-1010, C-52-0506-CME04-1020 | C-52-0506-CME05-1010: FS, C-52-0506-CME04-1020: FS | C-52-0506-CME05-1030, C-52-0506-CME06-1020 | C-52-0506-CME05-1030: FS, C-52-0506-CME06-1020: FS | 2025-05-07 12:00 | 2025-05-09 15:00
C-52-0506-CME05-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 | Section Tie-in Welding | C-52-0506-CME05-1020 | C-52-0506-CME05-1020: FS | C-52-0506-CME05-1040, C-52-0506-PL-ME-4810 | C-52-0506-CME05-1040: FS, C-52-0506-PL-ME-4810: FF | 2025-05-09 15:00 | 2025-05-13 15:00
C-52-0506-CME05-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 | NDT (Tie-in Joint) | C-52-0506-CME05-1030 | C-52-0506-CME05-1030: FS | C-52-0506-CME05-1050 | C-52-0506-CME05-1050: FS | 2025-05-13 15:00 | 2025-05-16 15:00
C-52-0506-CME05-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME05-1040 | C-52-0506-CME05-1040: FS | C-52-0506-CME05-1060 | C-52-0506-CME05-1060: FS | 2025-05-16 15:00 | 2025-05-20 15:00
C-52-0506-CME05-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 | Holiday Testing | C-52-0506-CME05-1050 | C-52-0506-CME05-1050: FS | C-52-0506-CME05-1070 | C-52-0506-CME05-1070: FS | 2025-05-20 15:00 | 2025-05-22 15:00
C-52-0506-CME05-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 | Padding & Back Filling | C-52-0506-CME05-1060 | C-52-0506-CME05-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-05-22 15:00 | 2025-05-24 15:00
C-52-0506-CME06-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 | Trench Excavation | C-52-0506-CME05-1000 | C-52-0506-CME05-1000: FS 1 | C-52-0506-CME06-1010, C-52-0506-CME07-1000 | C-52-0506-CME06-1010: FS, C-52-0506-CME07-1000: FS 1 | 2025-05-06 10:00 | 2025-05-08 14:00
C-52-0506-CME06-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 | Bedding | C-52-0506-CME06-1000 | C-52-0506-CME06-1000: FS | C-52-0506-CME06-1020 | C-52-0506-CME06-1020: FS | 2025-05-08 14:00 | 2025-05-10 15:00
C-52-0506-CME06-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 | Lowering | C-52-0506-CME06-1010, C-52-0506-CME05-1020 | C-52-0506-CME06-1010: FS, C-52-0506-CME05-1020: FS | C-52-0506-CME06-1030, C-52-0506-CME07-1020 | C-52-0506-CME06-1030: FS, C-52-0506-CME07-1020: FS | 2025-05-10 15:00 | 2025-05-13 15:00
C-52-0506-CME06-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 | Section Tie-in Welding | C-52-0506-CME06-1020 | C-52-0506-CME06-1020: FS | C-52-0506-CME06-1040, C-52-0506-PL-ME-4810 | C-52-0506-CME06-1040: FS, C-52-0506-PL-ME-4810: FF | 2025-05-13 15:00 | 2025-05-16 15:00
C-52-0506-CME06-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 | NDT (Tie-in Joint) | C-52-0506-CME06-1030 | C-52-0506-CME06-1030: FS | C-52-0506-CME06-1050 | C-52-0506-CME06-1050: FS | 2025-05-16 15:00 | 2025-05-20 15:00
C-52-0506-CME06-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME06-1040 | C-52-0506-CME06-1040: FS | C-52-0506-CME06-1060 | C-52-0506-CME06-1060: FS | 2025-05-20 15:00 | 2025-05-23 15:00
C-52-0506-CME06-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 | Holiday Testing | C-52-0506-CME06-1050 | C-52-0506-CME06-1050: FS | C-52-0506-CME06-1070 | C-52-0506-CME06-1070: FS | 2025-05-23 15:00 | 2025-05-26 15:00
C-52-0506-CME06-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 | Padding & Back Filling | C-52-0506-CME06-1060 | C-52-0506-CME06-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-05-26 15:00 | 2025-05-28 15:00
C-52-0506-CME07-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 | Trench Excavation | C-52-0506-CME06-1000 | C-52-0506-CME06-1000: FS 1 | C-52-0506-CME07-1010, C-52-0506-CME08-1000 | C-52-0506-CME07-1010: FS, C-52-0506-CME08-1000: FS 1 | 2025-05-09 15:00 | 2025-05-12 15:00
C-52-0506-CME07-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 | Bedding | C-52-0506-CME07-1000 | C-52-0506-CME07-1000: FS | C-52-0506-CME07-1020 | C-52-0506-CME07-1020: FS | 2025-05-12 15:00 | 2025-05-14 15:00
C-52-0506-CME07-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 | Lowering | C-52-0506-CME07-1010, C-52-0506-CME06-1020 | C-52-0506-CME07-1010: FS, C-52-0506-CME06-1020: FS | C-52-0506-CME07-1030, C-52-0506-CME08-1020 | C-52-0506-CME07-1030: FS, C-52-0506-CME08-1020: FS | 2025-05-14 15:00 | 2025-05-16 15:00
C-52-0506-CME07-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 | Section Tie-in Welding | C-52-0506-CME07-1020 | C-52-0506-CME07-1020: FS | C-52-0506-CME07-1040, C-52-0506-PL-ME-4810 | C-52-0506-CME07-1040: FS, C-52-0506-PL-ME-4810: FF | 2025-05-16 15:00 | 2025-05-20 15:00
C-52-0506-CME07-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 | NDT (Tie-in Joint) | C-52-0506-CME07-1030 | C-52-0506-CME07-1030: FS | C-52-0506-CME07-1050 | C-52-0506-CME07-1050: FS | 2025-05-20 15:00 | 2025-05-23 15:00
C-52-0506-CME07-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME07-1040 | C-52-0506-CME07-1040: FS | C-52-0506-CME07-1060 | C-52-0506-CME07-1060: FS | 2025-05-23 15:00 | 2025-05-27 15:00
C-52-0506-CME07-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 | Holiday Testing | C-52-0506-CME07-1050 | C-52-0506-CME07-1050: FS | C-52-0506-CME07-1070 | C-52-0506-CME07-1070: FS | 2025-05-27 15:00 | 2025-05-29 15:00
C-52-0506-CME07-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 | Padding & Back Filling | C-52-0506-CME07-1060 | C-52-0506-CME07-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-05-29 15:00 | 2025-05-31 15:00
C-52-0506-CME08-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 | Trench Excavation | C-52-0506-CME07-1000 | C-52-0506-CME07-1000: FS 1 | C-52-0506-CME08-1010, C-52-0506-CME09-1000 | C-52-0506-CME08-1010: FS, C-52-0506-CME09-1000: FS 1 | 2025-05-13 15:00 | 2025-05-15 15:00
C-52-0506-CME08-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 | Bedding | C-52-0506-CME08-1000 | C-52-0506-CME08-1000: FS | C-52-0506-CME08-1020 | C-52-0506-CME08-1020: FS | 2025-05-15 15:00 | 2025-05-17 15:00
C-52-0506-CME08-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 | Lowering | C-52-0506-CME08-1010, C-52-0506-CME07-1020 | C-52-0506-CME08-1010: FS, C-52-0506-CME07-1020: FS | C-52-0506-CME08-1030, C-52-0506-CME09-1020 | C-52-0506-CME08-1030: FS, C-52-0506-CME09-1020: FS | 2025-05-17 15:00 | 2025-05-20 15:00
C-52-0506-CME08-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 | Section Tie-in Welding | C-52-0506-CME08-1020 | C-52-0506-CME08-1020: FS | C-52-0506-CME08-1040, C-52-0506-PL-ME-4810 | C-52-0506-CME08-1040: FS, C-52-0506-PL-ME-4810: FF | 2025-05-20 15:00 | 2025-05-23 15:00
C-52-0506-CME08-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 | NDT (Tie-in Joint) | C-52-0506-CME08-1030 | C-52-0506-CME08-1030: FS | C-52-0506-CME08-1050 | C-52-0506-CME08-1050: FS | 2025-05-23 15:00 | 2025-05-27 15:00
C-52-0506-CME08-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME08-1040 | C-52-0506-CME08-1040: FS | C-52-0506-CME08-1060 | C-52-0506-CME08-1060: FS | 2025-05-27 15:00 | 2025-05-30 15:00
C-52-0506-CME08-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 | Holiday Testing | C-52-0506-CME08-1050 | C-52-0506-CME08-1050: FS | C-52-0506-CME08-1070 | C-52-0506-CME08-1070: FS | 2025-05-30 15:00 | 2025-06-02 15:00
C-52-0506-CME08-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 | Padding & Back Filling | C-52-0506-CME08-1060 | C-52-0506-CME08-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-06-02 15:00 | 2025-06-04 15:00
C-52-0506-CME09-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 | Trench Excavation | C-52-0506-CME08-1000 | C-52-0506-CME08-1000: FS 1 | C-52-0506-CME09-1010, C-52-0506-CME10-1000 | C-52-0506-CME09-1010: FS, C-52-0506-CME10-1000: FS 1 | 2025-05-16 15:00 | 2025-05-19 15:00
C-52-0506-CME09-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 | Bedding | C-52-0506-CME09-1000 | C-52-0506-CME09-1000: FS | C-52-0506-CME09-1020 | C-52-0506-CME09-1020: FS | 2025-05-19 15:00 | 2025-05-21 15:00
C-52-0506-CME09-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 | Lowering | C-52-0506-CME09-1010, C-52-0506-CME08-1020 | C-52-0506-CME09-1010: FS, C-52-0506-CME08-1020: FS | C-52-0506-CME09-1030, C-52-0506-CME10-1020 | C-52-0506-CME09-1030: FS, C-52-0506-CME10-1020: FS | 2025-05-21 15:00 | 2025-05-23 15:00
C-52-0506-CME09-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 | Section Tie-in Welding | C-52-0506-CME09-1020 | C-52-0506-CME09-1020: FS | C-52-0506-CME09-1040, C-52-0506-PL-ME-4810 | C-52-0506-CME09-1040: FS, C-52-0506-PL-ME-4810: FF | 2025-05-23 15:00 | 2025-05-27 15:00
C-52-0506-CME09-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 | NDT (Tie-in Joint) | C-52-0506-CME09-1030 | C-52-0506-CME09-1030: FS | C-52-0506-CME09-1050 | C-52-0506-CME09-1050: FS | 2025-05-27 15:00 | 2025-05-30 15:00
C-52-0506-CME09-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME09-1040 | C-52-0506-CME09-1040: FS | C-52-0506-CME09-1060 | C-52-0506-CME09-1060: FS | 2025-05-30 15:00 | 2025-06-03 15:00
C-52-0506-CME09-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 | Holiday Testing | C-52-0506-CME09-1050 | C-52-0506-CME09-1050: FS | C-52-0506-CME09-1070 | C-52-0506-CME09-1070: FS | 2025-06-03 15:00 | 2025-06-07 15:00
C-52-0506-CME09-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 | Padding & Back Filling | C-52-0506-CME09-1060 | C-52-0506-CME09-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-06-07 15:00 | 2025-06-10 15:00
C-52-0506-CME10-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 | Trench Excavation | C-52-0506-CME09-1000 | C-52-0506-CME09-1000: FS 1 | C-52-0506-CME10-1010, C-52-0506-CME25-2000 | C-52-0506-CME10-1010: FS, C-52-0506-CME25-2000: FS 1 | 2025-05-20 15:00 | 2025-05-22 15:00
C-52-0506-CME10-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 | Bedding | C-52-0506-CME10-1000 | C-52-0506-CME10-1000: FS | C-52-0506-CME10-1020 | C-52-0506-CME10-1020: FS | 2025-05-22 15:00 | 2025-05-24 15:00
C-52-0506-CME10-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 | Lowering | C-52-0506-CME10-1010, C-52-0506-CME09-1020 | C-52-0506-CME10-1010: FS, C-52-0506-CME09-1020: FS | C-52-0506-CME10-1030 | C-52-0506-CME10-1030: FS | 2025-05-24 15:00 | 2025-05-27 15:00
C-52-0506-CME10-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 | Section Tie-in Welding | C-52-0506-CME10-1020 | C-52-0506-CME10-1020: FS | C-52-0506-CME10-1040, C-52-0506-PL-ME-4810 | C-52-0506-CME10-1040: FS, C-52-0506-PL-ME-4810: FF | 2025-05-27 15:00 | 2025-05-30 15:00
C-52-0506-CME10-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 | NDT (Tie-in Joint) | C-52-0506-CME10-1030 | C-52-0506-CME10-1030: FS | C-52-0506-CME10-1050 | C-52-0506-CME10-1050: FS | 2025-05-30 15:00 | 2025-06-03 15:00
C-52-0506-CME10-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME10-1040 | C-52-0506-CME10-1040: FS | C-52-0506-CME10-1060 | C-52-0506-CME10-1060: FS | 2025-06-03 15:00 | 2025-06-09 15:00
C-52-0506-CME10-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 | Holiday Testing | C-52-0506-CME10-1050 | C-52-0506-CME10-1050: FS | C-52-0506-CME10-1070 | C-52-0506-CME10-1070: FS | 2025-06-09 15:00 | 2025-06-11 15:00
C-52-0506-CME10-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 | Padding & Back Filling | C-52-0506-CME10-1060 | C-52-0506-CME10-1060: FS | C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF 1, C-52-0506-PL-CI-6000: FF | 2025-06-11 15:00 | 2025-06-13 15:00
C-52-06CR-CNH30-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1330 | C-PER-1330: FS 15 | C-52-06CR-CNH30-1020, C-52-06CR-CNH30-1010 | C-52-06CR-CNH30-1020: FS, C-52-06CR-CNH30-1010: FS | 2025-03-06 07:00 | 2025-03-28 13:00
C-52-06CR-CNH30-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-06CR-CNH30-1000 | C-52-06CR-CNH30-1000: FS | C-52-06CR-CNH30-1030 | C-52-06CR-CNH30-1030: FS | 2025-03-29 07:00 | 2025-04-05 17:00
C-52-06CR-CNH30-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 | Driving & Receiving Pit Excavation | C-52-06CR-CNH30-1000 | C-52-06CR-CNH30-1000: FS | C-52-06CR-CNH30-1030 | C-52-06CR-CNH30-1030: FF | 2025-03-29 07:00 | 2025-04-17 17:00
C-52-06CR-CNH30-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-06CR-CNH30-1010, C-52-06CR-CNH30-1020 | C-52-06CR-CNH30-1010: FF, C-52-06CR-CNH30-1020: FS | C-52-06CR-CNH30-1040 | C-52-06CR-CNH30-1040: FS | 2025-04-07 07:00 | 2025-04-17 17:00
C-52-06CR-CNH30-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 | Floor Blinding & French Drain in Driving Pit | C-52-06CR-CNH30-1030 | C-52-06CR-CNH30-1030: FS | C-52-06CR-CNH30-1050 | C-52-06CR-CNH30-1050: FS | 2025-04-18 07:00 | 2025-04-24 17:00
C-52-06CR-CNH30-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-06CR-CNH30-1040 | C-52-06CR-CNH30-1040: FS | C-52-06CR-CNH30-1060 | C-52-06CR-CNH30-1060: SS 7 | 2025-04-25 07:00 | 2025-05-01 17:00
C-52-06CR-CNH30-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 | Construction of Exit Wall with Ring | C-52-06CR-CNH30-1050 | C-52-06CR-CNH30-1050: SS 7 | C-52-06CR-CNH30-1200 | C-52-06CR-CNH30-1200: FS | 2025-05-03 07:00 | 2025-05-10 15:00
C-52-06CR-CNH30-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.5.2.2 | Jacking of MTBM & RC Sleeves | C-52-06CR-CNH30-1060, C-52-0102-CNM05-1200 | C-52-06CR-CNH30-1060: FS, C-52-0102-CNM05-1200: FS | C-52-06CR-CNH30-1210 | C-52-06CR-CNH30-1210: FS | 2025-05-10 15:00 | 2025-06-17 07:30
C-52-06CR-CNH30-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.5.2.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-06CR-CNH30-1200 | C-52-06CR-CNH30-1200: FS | C-52-06CR-CNH30-1070 | C-52-06CR-CNH30-1070: FS | 2025-06-17 07:30 | 2025-06-21 07:30
C-52-06CR-CNH30-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 | Lowering & Welding of Carrier Pipe | C-52-06CR-CNH30-1210 | C-52-06CR-CNH30-1210: FS | C-52-06CR-CNH30-1080, C-52-06CR-PL-ME-4810 | C-52-06CR-CNH30-1080: SS 1, C-52-06CR-PL-ME-4810: FF 1 | 2025-06-21 07:30 | 2025-07-22 07:30
C-52-06CR-CNH30-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-06CR-CNH30-1070 | C-52-06CR-CNH30-1070: SS 1 | C-52-06CR-CNH30-1090 | C-52-06CR-CNH30-1090: FS | 2025-06-23 07:30 | 2025-07-25 07:30
C-52-06CR-CNH30-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-06CR-CNH30-1080 | C-52-06CR-CNH30-1080: FS | C-52-06CR-CNH30-1220 | C-52-06CR-CNH30-1220: FS | 2025-07-25 07:30 | 2025-08-06 07:30
C-52-06CR-CNH30-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.5.2.2 | Inner Grout b/w Main & RC Pipe | C-52-06CR-CNH30-1090 | C-52-06CR-CNH30-1090: FS | C-52-06CR-CNH30-1800, C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200 | C-52-06CR-CNH30-1800: SS 1, C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1 | 2025-08-06 07:30 | 2025-08-12 07:30
C-52-06CR-CNH30-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.5.2.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-06CR-CNH30-1220 | C-52-06CR-CNH30-1220: SS 1 | C-52-06CR-PL-CI-6800, PRECOM-52-06CR-1000, ML1679-E13 | C-52-06CR-PL-CI-6800: FF 14, PRECOM-52-06CR-1000: FS, ML1679-E13: FS | 2025-08-07 07:30 | 2025-08-23 07:30
C-52-06CR-CNM31-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 | Sheet Piling for Driving & Receiving Pit | C-PER-1340, C-52-06CR-PL-CI-2400 | C-PER-1340: FS, C-52-06CR-PL-CI-2400: SS | C-52-06CR-CNM31-1020, C-52-06CR-CNM31-1010 | C-52-06CR-CNM31-1020: FS, C-52-06CR-CNM31-1010: FS | 2025-06-17 15:00 | 2025-06-21 15:00
C-52-06CR-CNM31-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 | Installation of Dewatering System for Driving & Receiving Pit | C-52-06CR-CNM31-1000 | C-52-06CR-CNM31-1000: FS | C-52-06CR-CNM31-1030 | C-52-06CR-CNM31-1030: FS | 2025-06-21 15:00 | 2025-06-26 15:00
C-52-06CR-CNM31-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 | Driving & Receiving Pit Excavation | C-52-06CR-CNM31-1000 | C-52-06CR-CNM31-1000: FS | C-52-06CR-CNM31-1030 | C-52-06CR-CNM31-1030: FF | 2025-06-21 15:00 | 2025-06-26 15:00
C-52-06CR-CNM31-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-06CR-CNM31-1010, C-52-06CR-CNM31-1020 | C-52-06CR-CNM31-1010: FF, C-52-06CR-CNM31-1020: FS | C-52-06CR-CNM31-1040 | C-52-06CR-CNM31-1040: FS | 2025-06-26 15:00 | 2025-07-02 15:00
C-52-06CR-CNM31-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 | Floor Blinding & French Drain in Driving Pit | C-52-06CR-CNM31-1030 | C-52-06CR-CNM31-1030: FS | C-52-06CR-CNM31-1050 | C-52-06CR-CNM31-1050: FS | 2025-07-02 15:00 | 2025-07-05 15:00
C-52-06CR-CNM31-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-06CR-CNM31-1040 | C-52-06CR-CNM31-1040: FS | C-52-06CR-CNM31-1060 | C-52-06CR-CNM31-1060: FS | 2025-07-05 15:00 | 2025-07-09 15:00
C-52-06CR-CNM31-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 | Construction of Exit Wall with Ring | C-52-06CR-CNM31-1050 | C-52-06CR-CNM31-1050: FS | C-52-06CR-CNM31-1200 | C-52-06CR-CNM31-1200: FS | 2025-07-09 15:00 | 2025-07-12 15:00
C-52-06CR-CNM31-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.3.2 | Jacking of MTBM & RC Sleeves | C-52-06CR-CNM31-1060, C-52-0405-CNH20-1200, C-PER-1320, C-52-0405-CNH20-1200, C-52-0405-CNH19-1200 | C-52-06CR-CNM31-1060: FS, C-52-0405-CNH20-1200: FS, C-PER-1320: FS, C-52-0405-CNH20-1200: FF, C-52-0405-CNH19-1200: FS | C-52-06CR-CNM31-1210 | C-52-06CR-CNM31-1210: FS | 2025-07-12 15:00 | 2025-07-17 15:00
C-52-06CR-CNM31-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.3.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-52-06CR-CNM31-1200 | C-52-06CR-CNM31-1200: FS | C-52-06CR-CNM31-1400 | C-52-06CR-CNM31-1400: FS | 2025-07-17 15:00 | 2025-07-21 15:00
C-52-06CR-CNM31-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.3.3 | Lowering & Welding of Carrier Pipe | C-52-06CR-CNM31-1210 | C-52-06CR-CNM31-1210: FS | C-52-06CR-CNM31-1410, C-52-06CR-PL-ME-4810 | C-52-06CR-CNM31-1410: SS 1, C-52-06CR-PL-ME-4810: FF 1 | 2025-07-21 15:00 | 2025-07-25 15:00
C-52-06CR-CNM31-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.3.3 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-06CR-CNM31-1400 | C-52-06CR-CNM31-1400: SS 1 | C-52-06CR-CNM31-1600 | C-52-06CR-CNM31-1600: FS | 2025-07-22 15:00 | 2025-07-26 15:00
C-52-06CR-CNM31-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.3.4 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-06CR-CNM31-1410 | C-52-06CR-CNM31-1410: FS | C-52-06CR-CNM31-1220 | C-52-06CR-CNM31-1220: FS | 2025-07-26 15:00 | 2025-07-31 15:00
C-52-06CR-CNM31-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.3.2 | Inner Grout b/w Main & RC Pipe | C-52-06CR-CNM31-1600 | C-52-06CR-CNM31-1600: FS | C-52-06CR-CNM31-1800, C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200 | C-52-06CR-CNM31-1800: FS, C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1 | 2025-07-31 15:00 | 2025-08-04 15:00
C-52-06CR-CNM31-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.3.5 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-06CR-CNM31-1220 | C-52-06CR-CNM31-1220: FS | C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, PRECOM-52-06CR-1000, ML1679-E13 | C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, PRECOM-52-06CR-1000: FS, ML1679-E13: FS | 2025-08-04 15:00 | 2025-08-08 15:00
C-52-06CR-CMA01-0970 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 | Excavation (Manual-Trial Pit) | C-52-06CR-PL-ME-2800, C-52-06CR-PL-ME-2800 | C-52-06CR-PL-ME-2800: SS 21, C-52-06CR-PL-ME-2800: FF | C-52-06CR-CMA01-980, C-52-06CR-CMA02-1000, C-52-06CR-CMA02-1000 | C-52-06CR-CMA01-980: FS, C-52-06CR-CMA02-1000: SS, C-52-06CR-CMA02-1000: FF | 2025-05-12 15:00 | 2025-05-26 15:00
C-52-06CR-CMA01-980 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 | Sabkha Gatch Laying | C-52-06CR-CMA01-0970 | C-52-06CR-CMA01-0970: FS | C-52-06CR-CMA01-990 | C-52-06CR-CMA01-990: SS 1 | 2025-05-26 15:00 | 2025-05-31 15:00
C-52-06CR-CMA01-990 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 | Sabka Gatch Compaction | C-52-06CR-CMA01-980 | C-52-06CR-CMA01-980: SS 1 | C-52-06CR-CMA01-1000 | C-52-06CR-CMA01-1000: FS | 2025-05-27 15:00 | 2025-06-02 15:00
C-52-06CR-CMA01-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 | Trench Excavation | C-52-06CR-CMA01-990 | C-52-06CR-CMA01-990: FS | C-52-06CR-CMA01-1010 | C-52-06CR-CMA01-1010: FF | 2025-06-02 15:00 | 2025-06-04 15:00
C-52-06CR-CMA01-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 | Bedding | C-52-06CR-CMA01-1000 | C-52-06CR-CMA01-1000: FF | C-52-06CR-CMA01-1020 | C-52-06CR-CMA01-1020: FS | 2025-06-03 15:00 | 2025-06-04 15:00
C-52-06CR-CMA01-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 | Lowering | C-52-06CR-CMA01-1010, C-52-06CR-CMA11-1020 | C-52-06CR-CMA01-1010: FS, C-52-06CR-CMA11-1020: FS | C-52-06CR-CMA01-1030, C-52-06CR-CMA08-1020 | C-52-06CR-CMA01-1030: SS, C-52-06CR-CMA08-1020: FS | 2025-06-12 15:00 | 2025-06-13 15:00
C-52-06CR-CMA01-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 | Section Tie-in Welding | C-52-06CR-CMA01-1020 | C-52-06CR-CMA01-1020: SS | C-52-06CR-CMA01-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CMA01-1040: SS 1, C-52-06CR-PL-ME-4810: FF 1 | 2025-06-12 15:00 | 2025-06-14 15:00
C-52-06CR-CMA01-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 | NDT (Tie-in Joint) | C-52-06CR-CMA01-1030 | C-52-06CR-CMA01-1030: SS 1 | C-52-06CR-CMA01-1050 | C-52-06CR-CMA01-1050: SS 1 | 2025-06-13 15:00 | 2025-06-16 15:00
C-52-06CR-CMA01-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA01-1040 | C-52-06CR-CMA01-1040: SS 1 | C-52-06CR-CMA01-1060 | C-52-06CR-CMA01-1060: FS | 2025-06-14 15:00 | 2025-06-17 15:00
C-52-06CR-CMA01-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 | Holiday Testing | C-52-06CR-CMA01-1050 | C-52-06CR-CMA01-1050: FS | C-52-06CR-CMA01-1070 | C-52-06CR-CMA01-1070: FS | 2025-06-17 15:00 | 2025-06-18 15:00
C-52-06CR-CMA01-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 | Padding | C-52-06CR-CMA01-1060 | C-52-06CR-CMA01-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-06-18 15:00 | 2025-06-19 15:00
C-52-06CR-CMA11-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 | Trench Excavation | C-52-06CR-CMA12-1000 | C-52-06CR-CMA12-1000: FS | C-52-06CR-CMA11-1010, C-52-06CR-CMA08-1000 | C-52-06CR-CMA11-1010: FF, C-52-06CR-CMA08-1000: FS | 2025-06-02 15:00 | 2025-06-11 15:00
C-52-06CR-CMA11-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 | Bedding | C-52-06CR-CMA11-1000 | C-52-06CR-CMA11-1000: FF | C-52-06CR-CMA11-1020 | C-52-06CR-CMA11-1020: FS | 2025-06-10 15:00 | 2025-06-11 15:00
C-52-06CR-CMA11-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 | Lowering | C-52-06CR-CMA11-1010, C-52-06CR-PL-ME-2800 | C-52-06CR-CMA11-1010: FS, C-52-06CR-PL-ME-2800: SS 7 | C-52-06CR-CMA11-1030, C-52-06CR-CMA01-1020, C-52-06CR-CME04-1020, C-52-06CR-CMA10-1020, C-52-06CR-CME07-1020 | C-52-06CR-CMA11-1030: SS, C-52-06CR-CMA01-1020: FS, C-52-06CR-CME04-1020: FS, C-52-06CR-CMA10-1020: FS, C-52-06CR-CME07-1020: FS | 2025-06-11 15:00 | 2025-06-12 15:00
C-52-06CR-CMA11-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 | Section Tie-in Welding | C-52-06CR-CMA11-1020 | C-52-06CR-CMA11-1020: SS | C-52-06CR-CMA11-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CMA11-1040: SS 1, C-52-06CR-PL-ME-4810: FF 1 | 2025-06-11 15:00 | 2025-06-13 15:00
C-52-06CR-CMA11-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 | NDT (Tie-in Joint) | C-52-06CR-CMA11-1030 | C-52-06CR-CMA11-1030: SS 1 | C-52-06CR-CMA11-1050 | C-52-06CR-CMA11-1050: SS 1 | 2025-06-12 15:00 | 2025-06-14 15:00
C-52-06CR-CMA11-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA11-1040 | C-52-06CR-CMA11-1040: SS 1 | C-52-06CR-CMA11-1060 | C-52-06CR-CMA11-1060: FS | 2025-06-13 15:00 | 2025-06-16 15:00
C-52-06CR-CMA11-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 | Holiday Testing | C-52-06CR-CMA11-1050 | C-52-06CR-CMA11-1050: FS | C-52-06CR-CMA11-1070, C-52-06CR-PL-CA-5220 | C-52-06CR-CMA11-1070: FS, C-52-06CR-PL-CA-5220: SS | 2025-06-16 15:00 | 2025-06-17 15:00
C-52-06CR-CMA11-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 | Padding | C-52-06CR-CMA11-1060 | C-52-06CR-CMA11-1060: FS | C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-06-17 15:00 | 2025-06-18 15:00
C-52-06CR-CMA08-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 | Trench Excavation | C-52-06CR-CMA11-1000 | C-52-06CR-CMA11-1000: FS | C-52-06CR-CMA08-1010, C-52-06CR-CMA03-1000 | C-52-06CR-CMA08-1010: FF, C-52-06CR-CMA03-1000: FS | 2025-06-11 15:00 | 2025-06-20 15:00
C-52-06CR-CMA08-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 | Bedding | C-52-06CR-CMA08-1000 | C-52-06CR-CMA08-1000: FF | C-52-06CR-CMA08-1020 | C-52-06CR-CMA08-1020: FS | 2025-06-19 15:00 | 2025-06-20 15:00
C-52-06CR-CMA08-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 | Lowering | C-52-06CR-CMA08-1010, C-52-06CR-CMA01-1020 | C-52-06CR-CMA08-1010: FS, C-52-06CR-CMA01-1020: FS | C-52-06CR-CMA08-1030, C-52-06CR-CMA02-1020 | C-52-06CR-CMA08-1030: SS, C-52-06CR-CMA02-1020: FS | 2025-06-20 15:00 | 2025-06-21 15:00
C-52-06CR-CMA08-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 | Section Tie-in Welding | C-52-06CR-CMA08-1020 | C-52-06CR-CMA08-1020: SS | C-52-06CR-CMA08-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CMA08-1040: SS 1, C-52-06CR-PL-ME-4810: FF 1 | 2025-06-20 15:00 | 2025-06-23 15:00
C-52-06CR-CMA08-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 | NDT (Tie-in Joint) | C-52-06CR-CMA08-1030 | C-52-06CR-CMA08-1030: SS 1 | C-52-06CR-CMA08-1050 | C-52-06CR-CMA08-1050: SS 1 | 2025-06-21 15:00 | 2025-06-24 15:00
C-52-06CR-CMA08-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA08-1040 | C-52-06CR-CMA08-1040: SS 1 | C-52-06CR-CMA08-1060 | C-52-06CR-CMA08-1060: FS | 2025-06-23 15:00 | 2025-06-25 15:00
C-52-06CR-CMA08-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 | Holiday Testing | C-52-06CR-CMA08-1050 | C-52-06CR-CMA08-1050: FS | C-52-06CR-CMA08-1070 | C-52-06CR-CMA08-1070: FS | 2025-06-25 15:00 | 2025-06-26 15:00
C-52-06CR-CMA08-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 | Padding | C-52-06CR-CMA08-1060 | C-52-06CR-CMA08-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-06-26 15:00 | 2025-06-28 15:00
C-52-06CR-CMA02-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 | Trench Excavation | C-52-06CR-CMA01-0970, C-52-06CR-CMA01-0970 | C-52-06CR-CMA01-0970: SS, C-52-06CR-CMA01-0970: FF | C-52-06CR-CMA02-1010, C-52-06CR-CMA12-1000 | C-52-06CR-CMA02-1010: FF, C-52-06CR-CMA12-1000: FS | 2025-05-19 15:00 | 2025-05-26 15:00
C-52-06CR-CMA02-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 | Bedding | C-52-06CR-CMA02-1000 | C-52-06CR-CMA02-1000: FF | C-52-06CR-CMA02-1020 | C-52-06CR-CMA02-1020: FS | 2025-05-24 15:00 | 2025-05-26 15:00
C-52-06CR-CMA02-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 | Lowering | C-52-06CR-CMA02-1010, C-52-06CR-CMA08-1020 | C-52-06CR-CMA02-1010: FS, C-52-06CR-CMA08-1020: FS | C-52-06CR-CMA02-1030, C-52-06CR-CMA03-1020 | C-52-06CR-CMA02-1030: SS, C-52-06CR-CMA03-1020: FS | 2025-06-21 15:00 | 2025-06-23 15:00
C-52-06CR-CMA02-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 | Section Tie-in Welding | C-52-06CR-CMA02-1020 | C-52-06CR-CMA02-1020: SS | C-52-06CR-CMA02-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CMA02-1040: SS 1, C-52-06CR-PL-ME-4810: FF 1 | 2025-06-21 15:00 | 2025-06-24 15:00
C-52-06CR-CMA02-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 | NDT (Tie-in Joint) | C-52-06CR-CMA02-1030 | C-52-06CR-CMA02-1030: SS 1 | C-52-06CR-CMA02-1050 | C-52-06CR-CMA02-1050: SS 1 | 2025-06-23 15:00 | 2025-06-25 15:00
C-52-06CR-CMA02-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA02-1040 | C-52-06CR-CMA02-1040: SS 1 | C-52-06CR-CMA02-1060 | C-52-06CR-CMA02-1060: FS | 2025-06-24 15:00 | 2025-06-26 15:00
C-52-06CR-CMA02-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 | Holiday Testing | C-52-06CR-CMA02-1050 | C-52-06CR-CMA02-1050: FS | C-52-06CR-CMA02-1070 | C-52-06CR-CMA02-1070: FS | 2025-06-26 15:00 | 2025-06-28 15:00
C-52-06CR-CMA02-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 | Padding | C-52-06CR-CMA02-1060 | C-52-06CR-CMA02-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-06-28 15:00 | 2025-06-30 15:00
C-52-06CR-CMA03-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 | Trench Excavation | C-52-06CR-CMA08-1000 | C-52-06CR-CMA08-1000: FS | C-52-06CR-CMA03-1010, C-52-06CR-CMA09-1000 | C-52-06CR-CMA03-1010: FF, C-52-06CR-CMA09-1000: FS | 2025-06-20 15:00 | 2025-06-28 15:00
C-52-06CR-CMA03-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 | Bedding | C-52-06CR-CMA03-1000 | C-52-06CR-CMA03-1000: FF | C-52-06CR-CMA03-1020 | C-52-06CR-CMA03-1020: FS | 2025-06-26 15:00 | 2025-06-28 15:00
C-52-06CR-CMA03-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 | Lowering | C-52-06CR-CMA03-1010, C-52-06CR-CMA02-1020 | C-52-06CR-CMA03-1010: FS, C-52-06CR-CMA02-1020: FS | C-52-06CR-CMA03-1030, C-52-06CR-CMA12-1020, C-52-06CR-CMA03-1030 | C-52-06CR-CMA03-1030: SS, C-52-06CR-CMA12-1020: FS, C-52-06CR-CMA03-1030: FF | 2025-06-28 15:00 | 2025-06-30 15:00
C-52-06CR-CMA03-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 | Section Tie-in Welding | C-52-06CR-CMA03-1020, C-52-06CR-CMA03-1020 | C-52-06CR-CMA03-1020: SS, C-52-06CR-CMA03-1020: FF | C-52-06CR-CMA03-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CMA03-1040: SS 1, C-52-06CR-PL-ME-4810: FF 1 | 2025-06-28 15:00 | 2025-07-01 15:00
C-52-06CR-CMA03-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 | NDT (Tie-in Joint) | C-52-06CR-CMA03-1030 | C-52-06CR-CMA03-1030: SS 1 | C-52-06CR-CMA03-1050 | C-52-06CR-CMA03-1050: SS 1 | 2025-06-30 15:00 | 2025-07-02 15:00
C-52-06CR-CMA03-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA03-1040 | C-52-06CR-CMA03-1040: SS 1 | C-52-06CR-CMA03-1060 | C-52-06CR-CMA03-1060: FS | 2025-07-01 15:00 | 2025-07-03 15:00
C-52-06CR-CMA03-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 | Holiday Testing | C-52-06CR-CMA03-1050 | C-52-06CR-CMA03-1050: FS | C-52-06CR-CMA03-1070 | C-52-06CR-CMA03-1070: FS | 2025-07-03 15:00 | 2025-07-04 15:00
C-52-06CR-CMA03-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 | Padding | C-52-06CR-CMA03-1060 | C-52-06CR-CMA03-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-04 15:00 | 2025-07-05 15:00
C-52-06CR-CMA12-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 | Trench Excavation | C-52-06CR-CMA02-1000 | C-52-06CR-CMA02-1000: FS | C-52-06CR-CMA12-1010, C-52-06CR-CMA04-1000, C-52-06CR-CMA11-1000 | C-52-06CR-CMA12-1010: FF, C-52-06CR-CMA04-1000: FS, C-52-06CR-CMA11-1000: FS | 2025-05-26 15:00 | 2025-06-02 15:00
C-52-06CR-CMA12-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 | Bedding | C-52-06CR-CMA12-1000 | C-52-06CR-CMA12-1000: FF | C-52-06CR-CMA12-1020 | C-52-06CR-CMA12-1020: FS | 2025-05-31 15:00 | 2025-06-02 15:00
C-52-06CR-CMA12-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 | Lowering | C-52-06CR-CMA12-1010, C-52-06CR-CMA03-1020 | C-52-06CR-CMA12-1010: FS, C-52-06CR-CMA03-1020: FS | C-52-06CR-CMA12-1030, C-52-06CR-CMA09-1020 | C-52-06CR-CMA12-1030: SS, C-52-06CR-CMA09-1020: FS | 2025-06-30 15:00 | 2025-07-01 15:00
C-52-06CR-CMA12-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 | Section Tie-in Welding | C-52-06CR-CMA12-1020 | C-52-06CR-CMA12-1020: SS | C-52-06CR-CMA12-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CMA12-1040: SS 1, C-52-06CR-PL-ME-4810: FF 1 | 2025-06-30 15:00 | 2025-07-02 15:00
C-52-06CR-CMA12-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 | NDT (Tie-in Joint) | C-52-06CR-CMA12-1030 | C-52-06CR-CMA12-1030: SS 1 | C-52-06CR-CMA12-1050 | C-52-06CR-CMA12-1050: SS 1 | 2025-07-01 15:00 | 2025-07-03 15:00
C-52-06CR-CMA12-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA12-1040 | C-52-06CR-CMA12-1040: SS 1 | C-52-06CR-CMA12-1060 | C-52-06CR-CMA12-1060: FS | 2025-07-02 15:00 | 2025-07-04 15:00
C-52-06CR-CMA12-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 | Holiday Testing | C-52-06CR-CMA12-1050 | C-52-06CR-CMA12-1050: FS | C-52-06CR-CMA12-1070 | C-52-06CR-CMA12-1070: FS | 2025-07-04 15:00 | 2025-07-05 15:00
C-52-06CR-CMA12-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 | Padding | C-52-06CR-CMA12-1060 | C-52-06CR-CMA12-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-05 15:00 | 2025-07-07 15:00
C-52-06CR-CMA09-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 | Trench Excavation | C-52-06CR-CMA03-1000 | C-52-06CR-CMA03-1000: FS | C-52-06CR-CMA09-1010, C-52-06CR-CMA05-1000 | C-52-06CR-CMA09-1010: FF, C-52-06CR-CMA05-1000: SS | 2025-06-28 15:00 | 2025-07-15 15:00
C-52-06CR-CMA09-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 | Bedding | C-52-06CR-CMA09-1000 | C-52-06CR-CMA09-1000: FF | C-52-06CR-CMA09-1020 | C-52-06CR-CMA09-1020: FS | 2025-07-14 15:00 | 2025-07-15 15:00
C-52-06CR-CMA09-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 | Lowering | C-52-06CR-CMA09-1010, C-52-06CR-CMA12-1020 | C-52-06CR-CMA09-1010: FS, C-52-06CR-CMA12-1020: FS | C-52-06CR-CMA09-1030, C-52-06CR-CMA04-1020 | C-52-06CR-CMA09-1030: SS, C-52-06CR-CMA04-1020: FS | 2025-07-15 15:00 | 2025-07-16 15:00
C-52-06CR-CMA09-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 | Section Tie-in Welding | C-52-06CR-CMA09-1020 | C-52-06CR-CMA09-1020: SS | C-52-06CR-CMA09-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CMA09-1040: SS 1, C-52-06CR-PL-ME-4810: FF 1 | 2025-07-15 15:00 | 2025-07-17 15:00
C-52-06CR-CMA09-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 | NDT (Tie-in Joint) | C-52-06CR-CMA09-1030 | C-52-06CR-CMA09-1030: SS 1 | C-52-06CR-CMA09-1050 | C-52-06CR-CMA09-1050: SS 1 | 2025-07-16 15:00 | 2025-07-18 15:00
C-52-06CR-CMA09-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA09-1040 | C-52-06CR-CMA09-1040: SS 1 | C-52-06CR-CMA09-1060 | C-52-06CR-CMA09-1060: FS | 2025-07-17 15:00 | 2025-07-19 15:00
C-52-06CR-CMA09-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 | Holiday Testing | C-52-06CR-CMA09-1050 | C-52-06CR-CMA09-1050: FS | C-52-06CR-CMA09-1070 | C-52-06CR-CMA09-1070: FS | 2025-07-19 15:00 | 2025-07-21 15:00
C-52-06CR-CMA09-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 | Padding | C-52-06CR-CMA09-1060 | C-52-06CR-CMA09-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-21 15:00 | 2025-07-22 15:00
C-52-06CR-CMA04-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 | Trench Excavation | C-52-06CR-CMA12-1000 | C-52-06CR-CMA12-1000: FS | C-52-06CR-CMA04-1010, C-52-06CR-CMA06-1000 | C-52-06CR-CMA04-1010: FF, C-52-06CR-CMA06-1000: FS | 2025-06-02 15:00 | 2025-06-13 15:00
C-52-06CR-CMA04-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 | Bedding | C-52-06CR-CMA04-1000 | C-52-06CR-CMA04-1000: FF | C-52-06CR-CMA04-1020 | C-52-06CR-CMA04-1020: FS | 2025-06-12 15:00 | 2025-06-13 15:00
C-52-06CR-CMA04-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 | Lowering | C-52-06CR-CMA04-1010, C-52-06CR-CMA09-1020 | C-52-06CR-CMA04-1010: FS, C-52-06CR-CMA09-1020: FS | C-52-06CR-CMA04-1030, C-52-06CR-CMA05-1020 | C-52-06CR-CMA04-1030: SS, C-52-06CR-CMA05-1020: FS | 2025-07-16 15:00 | 2025-07-17 15:00
C-52-06CR-CMA04-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 | Section Tie-in Welding | C-52-06CR-CMA04-1020 | C-52-06CR-CMA04-1020: SS | C-52-06CR-CMA04-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CMA04-1040: SS 1, C-52-06CR-PL-ME-4810: FF 1 | 2025-07-16 15:00 | 2025-07-18 15:00
C-52-06CR-CMA04-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 | NDT (Tie-in Joint) | C-52-06CR-CMA04-1030 | C-52-06CR-CMA04-1030: SS 1 | C-52-06CR-CMA04-1050 | C-52-06CR-CMA04-1050: SS 1 | 2025-07-17 15:00 | 2025-07-19 15:00
C-52-06CR-CMA04-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA04-1040 | C-52-06CR-CMA04-1040: SS 1 | C-52-06CR-CMA04-1060 | C-52-06CR-CMA04-1060: FS | 2025-07-18 15:00 | 2025-07-21 15:00
C-52-06CR-CMA04-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 | Holiday Testing | C-52-06CR-CMA04-1050 | C-52-06CR-CMA04-1050: FS | C-52-06CR-CMA04-1070 | C-52-06CR-CMA04-1070: FS | 2025-07-21 15:00 | 2025-07-22 15:00
C-52-06CR-CMA04-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 | Padding | C-52-06CR-CMA04-1060 | C-52-06CR-CMA04-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-22 15:00 | 2025-07-23 15:00
C-52-06CR-CMA05-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 | Trench Excavation | C-52-06CR-CMA09-1000 | C-52-06CR-CMA09-1000: SS | C-52-06CR-CMA05-1010, C-52-06CR-CMA10-1000 | C-52-06CR-CMA05-1010: FF, C-52-06CR-CMA10-1000: FS | 2025-06-28 15:00 | 2025-07-05 15:00
C-52-06CR-CMA05-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 | Bedding | C-52-06CR-CMA05-1000 | C-52-06CR-CMA05-1000: FF | C-52-06CR-CMA05-1020 | C-52-06CR-CMA05-1020: FS | 2025-07-04 15:00 | 2025-07-05 15:00
C-52-06CR-CMA05-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 | Lowering | C-52-06CR-CMA05-1010, C-52-06CR-CMA04-1020 | C-52-06CR-CMA05-1010: FS, C-52-06CR-CMA04-1020: FS | C-52-06CR-CMA05-1030, C-52-06CR-CMA06-1020 | C-52-06CR-CMA05-1030: SS, C-52-06CR-CMA06-1020: FS | 2025-07-17 15:00 | 2025-07-18 15:00
C-52-06CR-CMA05-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 | Section Tie-in Welding | C-52-06CR-CMA05-1020 | C-52-06CR-CMA05-1020: SS | C-52-06CR-CMA05-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CMA05-1040: SS 1, C-52-06CR-PL-ME-4810: FF 1 | 2025-07-17 15:00 | 2025-07-19 15:00
C-52-06CR-CMA05-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 | NDT (Tie-in Joint) | C-52-06CR-CMA05-1030 | C-52-06CR-CMA05-1030: SS 1 | C-52-06CR-CMA05-1050 | C-52-06CR-CMA05-1050: SS 1 | 2025-07-18 15:00 | 2025-07-21 15:00
C-52-06CR-CMA05-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA05-1040 | C-52-06CR-CMA05-1040: SS 1 | C-52-06CR-CMA05-1060 | C-52-06CR-CMA05-1060: FS | 2025-07-19 15:00 | 2025-07-22 15:00
C-52-06CR-CMA05-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 | Holiday Testing | C-52-06CR-CMA05-1050 | C-52-06CR-CMA05-1050: FS | C-52-06CR-CMA05-1070 | C-52-06CR-CMA05-1070: FS | 2025-07-22 15:00 | 2025-07-23 15:00
C-52-06CR-CMA05-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 | Padding | C-52-06CR-CMA05-1060 | C-52-06CR-CMA05-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-23 15:00 | 2025-07-24 15:00
C-52-06CR-CMA06-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 | Trench Excavation | C-52-06CR-CMA04-1000 | C-52-06CR-CMA04-1000: FS | C-52-06CR-CMA06-1010, C-52-06CR-CMA07-1000 | C-52-06CR-CMA06-1010: FF, C-52-06CR-CMA07-1000: FS | 2025-06-13 15:00 | 2025-06-20 15:00
C-52-06CR-CMA06-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 | Bedding | C-52-06CR-CMA06-1000 | C-52-06CR-CMA06-1000: FF | C-52-06CR-CMA06-1020 | C-52-06CR-CMA06-1020: FS | 2025-06-19 15:00 | 2025-06-20 15:00
C-52-06CR-CMA06-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 | Lowering | C-52-06CR-CMA06-1010, C-52-06CR-CMA05-1020 | C-52-06CR-CMA06-1010: FS, C-52-06CR-CMA05-1020: FS | C-52-06CR-CMA06-1030 | C-52-06CR-CMA06-1030: SS | 2025-07-18 15:00 | 2025-07-19 15:00
C-52-06CR-CMA06-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 | Section Tie-in Welding | C-52-06CR-CMA06-1020 | C-52-06CR-CMA06-1020: SS | C-52-06CR-CMA06-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CMA06-1040: SS 1, C-52-06CR-PL-ME-4810: FF 1 | 2025-07-18 15:00 | 2025-07-21 15:00
C-52-06CR-CMA06-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 | NDT (Tie-in Joint) | C-52-06CR-CMA06-1030 | C-52-06CR-CMA06-1030: SS 1 | C-52-06CR-CMA06-1050 | C-52-06CR-CMA06-1050: SS 1 | 2025-07-19 15:00 | 2025-07-22 15:00
C-52-06CR-CMA06-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA06-1040 | C-52-06CR-CMA06-1040: SS 1 | C-52-06CR-CMA06-1060 | C-52-06CR-CMA06-1060: FS | 2025-07-21 15:00 | 2025-07-23 15:00
C-52-06CR-CMA06-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 | Holiday Testing | C-52-06CR-CMA06-1050 | C-52-06CR-CMA06-1050: FS | C-52-06CR-CMA06-1070 | C-52-06CR-CMA06-1070: FS | 2025-07-23 15:00 | 2025-07-24 15:00
C-52-06CR-CMA06-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 | Padding | C-52-06CR-CMA06-1060 | C-52-06CR-CMA06-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-24 15:00 | 2025-07-25 15:00
C-52-06CR-CMA10-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 | Trench Excavation | C-52-06CR-CMA05-1000 | C-52-06CR-CMA05-1000: FS | C-52-06CR-CMA10-1010, C-52-06CR-CMA13-1000 | C-52-06CR-CMA10-1010: FF, C-52-06CR-CMA13-1000: SS | 2025-07-05 15:00 | 2025-07-15 15:00
C-52-06CR-CMA10-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 | Bedding | C-52-06CR-CMA10-1000 | C-52-06CR-CMA10-1000: FF | C-52-06CR-CMA10-1020 | C-52-06CR-CMA10-1020: FS | 2025-07-14 15:00 | 2025-07-15 15:00
C-52-06CR-CMA10-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 | Lowering | C-52-06CR-CMA10-1010, C-52-06CR-CMA11-1020 | C-52-06CR-CMA10-1010: FS, C-52-06CR-CMA11-1020: FS | C-52-06CR-CMA10-1030, C-52-06CR-CMA07-1020 | C-52-06CR-CMA10-1030: SS, C-52-06CR-CMA07-1020: FS | 2025-07-15 15:00 | 2025-07-16 15:00
C-52-06CR-CMA10-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 | Section Tie-in Welding | C-52-06CR-CMA10-1020 | C-52-06CR-CMA10-1020: SS | C-52-06CR-CMA10-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CMA10-1040: SS 1, C-52-06CR-PL-ME-4810: FF 1 | 2025-07-15 15:00 | 2025-07-17 15:00
C-52-06CR-CMA10-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 | NDT (Tie-in Joint) | C-52-06CR-CMA10-1030 | C-52-06CR-CMA10-1030: SS 1 | C-52-06CR-CMA10-1050 | C-52-06CR-CMA10-1050: SS 1 | 2025-07-16 15:00 | 2025-07-18 15:00
C-52-06CR-CMA10-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA10-1040 | C-52-06CR-CMA10-1040: SS 1 | C-52-06CR-CMA10-1060 | C-52-06CR-CMA10-1060: FS | 2025-07-17 15:00 | 2025-07-19 15:00
C-52-06CR-CMA10-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 | Holiday Testing | C-52-06CR-CMA10-1050 | C-52-06CR-CMA10-1050: FS | C-52-06CR-CMA10-1070 | C-52-06CR-CMA10-1070: FS | 2025-07-19 15:00 | 2025-07-21 15:00
C-52-06CR-CMA10-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 | Padding | C-52-06CR-CMA10-1060 | C-52-06CR-CMA10-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-21 15:00 | 2025-07-22 15:00
C-52-06CR-CMA07-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 | Trench Excavation | C-52-06CR-CMA06-1000 | C-52-06CR-CMA06-1000: FS | C-52-06CR-CMA07-1010 | C-52-06CR-CMA07-1010: FF | 2025-06-20 15:00 | 2025-06-28 15:00
C-52-06CR-CMA07-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 | Bedding | C-52-06CR-CMA07-1000 | C-52-06CR-CMA07-1000: FF | C-52-06CR-CMA07-1020 | C-52-06CR-CMA07-1020: FS | 2025-06-26 15:00 | 2025-06-28 15:00
C-52-06CR-CMA07-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 | Lowering | C-52-06CR-CMA07-1010, C-52-06CR-CMA10-1020 | C-52-06CR-CMA07-1010: FS, C-52-06CR-CMA10-1020: FS | C-52-06CR-CMA07-1030, C-52-06CR-CMA13-1020 | C-52-06CR-CMA07-1030: SS, C-52-06CR-CMA13-1020: FS | 2025-07-16 15:00 | 2025-07-17 15:00
C-52-06CR-CMA07-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 | Section Tie-in Welding | C-52-06CR-CMA07-1020 | C-52-06CR-CMA07-1020: SS | C-52-06CR-CMA07-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CMA07-1040: SS 1, C-52-06CR-PL-ME-4810: FF 1 | 2025-07-16 15:00 | 2025-07-18 15:00
C-52-06CR-CMA07-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 | NDT (Tie-in Joint) | C-52-06CR-CMA07-1030 | C-52-06CR-CMA07-1030: SS 1 | C-52-06CR-CMA07-1050 | C-52-06CR-CMA07-1050: SS 1 | 2025-07-17 15:00 | 2025-07-19 15:00
C-52-06CR-CMA07-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA07-1040 | C-52-06CR-CMA07-1040: SS 1 | C-52-06CR-CMA07-1060 | C-52-06CR-CMA07-1060: FS | 2025-07-18 15:00 | 2025-07-21 15:00
C-52-06CR-CMA07-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 | Holiday Testing | C-52-06CR-CMA07-1050 | C-52-06CR-CMA07-1050: FS | C-52-06CR-CMA07-1070 | C-52-06CR-CMA07-1070: FS | 2025-07-21 15:00 | 2025-07-22 15:00
C-52-06CR-CMA07-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 | Padding | C-52-06CR-CMA07-1060 | C-52-06CR-CMA07-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-22 15:00 | 2025-07-23 15:00
C-52-06CR-CMA13-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 | Trench Excavation | C-52-06CR-CMA10-1000 | C-52-06CR-CMA10-1000: SS | C-52-06CR-CMA13-1010 | C-52-06CR-CMA13-1010: FF | 2025-07-05 15:00 | 2025-07-12 15:00
C-52-06CR-CMA13-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 | Bedding | C-52-06CR-CMA13-1000 | C-52-06CR-CMA13-1000: FF | C-52-06CR-CMA13-1020 | C-52-06CR-CMA13-1020: FS | 2025-07-11 15:00 | 2025-07-12 15:00
C-52-06CR-CMA13-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 | Lowering | C-52-06CR-CMA13-1010, C-52-06CR-CMA07-1020 | C-52-06CR-CMA13-1010: FS, C-52-06CR-CMA07-1020: FS | C-52-06CR-CMA13-1030, C-52-06CR-CMA13-1030 | C-52-06CR-CMA13-1030: SS, C-52-06CR-CMA13-1030: FF | 2025-07-17 15:00 | 2025-07-18 15:00
C-52-06CR-CMA13-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 | Section Tie-in Welding | C-52-06CR-CMA13-1020, C-52-06CR-CMA13-1020 | C-52-06CR-CMA13-1020: SS, C-52-06CR-CMA13-1020: FF | C-52-06CR-CMA13-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CMA13-1040: SS 1, C-52-06CR-PL-ME-4810: FF | 2025-07-17 15:00 | 2025-07-19 15:00
C-52-06CR-CMA13-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 | NDT (Tie-in Joint) | C-52-06CR-CMA13-1030 | C-52-06CR-CMA13-1030: SS 1 | C-52-06CR-CMA13-1050 | C-52-06CR-CMA13-1050: SS 1 | 2025-07-18 15:00 | 2025-07-21 15:00
C-52-06CR-CMA13-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA13-1040 | C-52-06CR-CMA13-1040: SS 1 | C-52-06CR-CMA13-1060 | C-52-06CR-CMA13-1060: FS | 2025-07-19 15:00 | 2025-07-22 15:00
C-52-06CR-CMA13-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 | Holiday Testing | C-52-06CR-CMA13-1050 | C-52-06CR-CMA13-1050: FS | C-52-06CR-CMA13-1070 | C-52-06CR-CMA13-1070: FS | 2025-07-22 15:00 | 2025-07-23 15:00
C-52-06CR-CMA13-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 | Padding | C-52-06CR-CMA13-1060 | C-52-06CR-CMA13-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF 2 | 2025-07-23 15:00 | 2025-07-24 15:00
C-52-06CR-CME01-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 | Trench Excavation | C-52-06CR-PL-ME-2800, C-52-0506-CME28-1080 | C-52-06CR-PL-ME-2800: FS 1, C-52-0506-CME28-1080: FS 1 | C-52-06CR-CME01-1010, C-52-06CR-CME02-1000 | C-52-06CR-CME01-1010: FS, C-52-06CR-CME02-1000: FS 1 | 2025-05-30 15:00 | 2025-06-02 15:00
C-52-06CR-CME01-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 | Bedding | C-52-06CR-CME01-1000 | C-52-06CR-CME01-1000: FS | C-52-06CR-CME01-1020 | C-52-06CR-CME01-1020: FS | 2025-06-02 15:00 | 2025-06-04 15:00
C-52-06CR-CME01-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 | Lowering | C-52-06CR-CME01-1010, C-52-06CR-PL-ME-2800 | C-52-06CR-CME01-1010: FS, C-52-06CR-PL-ME-2800: SS 14 | C-52-06CR-CME01-1030, C-52-06CR-CME02-1020 | C-52-06CR-CME01-1030: FS, C-52-06CR-CME02-1020: FS | 2025-06-04 15:00 | 2025-06-09 15:00
C-52-06CR-CME01-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 | Section Tie-in Welding | C-52-06CR-CME01-1020 | C-52-06CR-CME01-1020: FS | C-52-06CR-CME01-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CME01-1040: FS, C-52-06CR-PL-ME-4810: FF 1 | 2025-06-09 15:00 | 2025-06-12 15:00
C-52-06CR-CME01-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 | NDT (Tie-in Joint) | C-52-06CR-CME01-1030 | C-52-06CR-CME01-1030: FS | C-52-06CR-CME01-1050 | C-52-06CR-CME01-1050: FS | 2025-06-12 15:00 | 2025-06-16 15:00
C-52-06CR-CME01-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME01-1040 | C-52-06CR-CME01-1040: FS | C-52-06CR-CME01-1060 | C-52-06CR-CME01-1060: FS | 2025-06-16 15:00 | 2025-06-19 15:00
C-52-06CR-CME01-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 | Holiday Testing | C-52-06CR-CME01-1050 | C-52-06CR-CME01-1050: FS | C-52-06CR-CME01-1070 | C-52-06CR-CME01-1070: FS | 2025-06-19 15:00 | 2025-06-21 15:00
C-52-06CR-CME01-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 | Padding & Back Filling | C-52-06CR-CME01-1060 | C-52-06CR-CME01-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-06-21 15:00 | 2025-06-24 15:00
C-52-06CR-CME02-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 | Trench Excavation | C-52-06CR-CME01-1000 | C-52-06CR-CME01-1000: FS 1 | C-52-06CR-CME02-1010, C-52-06CR-CME03-1000 | C-52-06CR-CME02-1010: FS, C-52-06CR-CME03-1000: FS 1 | 2025-06-03 15:00 | 2025-06-07 15:00
C-52-06CR-CME02-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 | Bedding | C-52-06CR-CME02-1000 | C-52-06CR-CME02-1000: FS | C-52-06CR-CME02-1020 | C-52-06CR-CME02-1020: FS | 2025-06-07 15:00 | 2025-06-10 15:00
C-52-06CR-CME02-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 | Lowering | C-52-06CR-CME02-1010, C-52-06CR-CME01-1020 | C-52-06CR-CME02-1010: FS, C-52-06CR-CME01-1020: FS | C-52-06CR-CME02-1030, C-52-06CR-CME03-1020 | C-52-06CR-CME02-1030: FS, C-52-06CR-CME03-1020: FS | 2025-06-10 15:00 | 2025-06-12 15:00
C-52-06CR-CME02-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 | Section Tie-in Welding | C-52-06CR-CME02-1020 | C-52-06CR-CME02-1020: FS | C-52-06CR-CME02-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CME02-1040: FS, C-52-06CR-PL-ME-4810: FF 1 | 2025-06-12 15:00 | 2025-06-16 15:00
C-52-06CR-CME02-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 | NDT (Tie-in Joint) | C-52-06CR-CME02-1030 | C-52-06CR-CME02-1030: FS | C-52-06CR-CME02-1050 | C-52-06CR-CME02-1050: FS | 2025-06-16 15:00 | 2025-06-19 15:00
C-52-06CR-CME02-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME02-1040 | C-52-06CR-CME02-1040: FS | C-52-06CR-CME02-1060 | C-52-06CR-CME02-1060: FS | 2025-06-19 15:00 | 2025-06-23 15:00
C-52-06CR-CME02-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 | Holiday Testing | C-52-06CR-CME02-1050 | C-52-06CR-CME02-1050: FS | C-52-06CR-CME02-1070 | C-52-06CR-CME02-1070: FS | 2025-06-23 15:00 | 2025-06-25 15:00
C-52-06CR-CME02-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 | Padding & Back Filling | C-52-06CR-CME02-1060 | C-52-06CR-CME02-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-06-25 15:00 | 2025-06-28 15:00
C-52-06CR-CME03-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 | Trench Excavation | C-52-06CR-CME02-1000 | C-52-06CR-CME02-1000: FS 1 | C-52-06CR-CME03-1010, C-52-06CR-CME04-1000 | C-52-06CR-CME03-1010: FS, C-52-06CR-CME04-1000: FS 1 | 2025-06-09 15:00 | 2025-06-11 15:00
C-52-06CR-CME03-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 | Bedding | C-52-06CR-CME03-1000 | C-52-06CR-CME03-1000: FS | C-52-06CR-CME03-1020 | C-52-06CR-CME03-1020: FS | 2025-06-11 15:00 | 2025-06-13 15:00
C-52-06CR-CME03-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 | Lowering | C-52-06CR-CME03-1010, C-52-06CR-CME02-1020 | C-52-06CR-CME03-1010: FS, C-52-06CR-CME02-1020: FS | C-52-06CR-CME03-1030 | C-52-06CR-CME03-1030: FS | 2025-06-13 15:00 | 2025-06-16 15:00
C-52-06CR-CME03-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 | Section Tie-in Welding | C-52-06CR-CME03-1020 | C-52-06CR-CME03-1020: FS | C-52-06CR-CME03-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CME03-1040: FS, C-52-06CR-PL-ME-4810: FF 1 | 2025-06-16 15:00 | 2025-06-19 15:00
C-52-06CR-CME03-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 | NDT (Tie-in Joint) | C-52-06CR-CME03-1030 | C-52-06CR-CME03-1030: FS | C-52-06CR-CME03-1050 | C-52-06CR-CME03-1050: FS | 2025-06-19 15:00 | 2025-06-23 15:00
C-52-06CR-CME03-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME03-1040 | C-52-06CR-CME03-1040: FS | C-52-06CR-CME03-1060 | C-52-06CR-CME03-1060: FS | 2025-06-23 15:00 | 2025-06-26 15:00
C-52-06CR-CME03-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 | Holiday Testing | C-52-06CR-CME03-1050 | C-52-06CR-CME03-1050: FS | C-52-06CR-CME03-1070 | C-52-06CR-CME03-1070: FS | 2025-06-26 15:00 | 2025-06-30 15:00
C-52-06CR-CME03-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 | Padding & Back Filling | C-52-06CR-CME03-1060 | C-52-06CR-CME03-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-06-30 15:00 | 2025-07-02 15:00
C-52-06CR-CME04-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 | Trench Excavation | C-52-06CR-CME03-1000 | C-52-06CR-CME03-1000: FS 1 | C-52-06CR-CME04-1010, C-52-06CR-CME05-1000 | C-52-06CR-CME04-1010: FS, C-52-06CR-CME05-1000: FS 1 | 2025-06-12 15:00 | 2025-06-14 15:00
C-52-06CR-CME04-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 | Bedding | C-52-06CR-CME04-1000 | C-52-06CR-CME04-1000: FS | C-52-06CR-CME04-1020 | C-52-06CR-CME04-1020: FS | 2025-06-14 15:00 | 2025-06-17 15:00
C-52-06CR-CME04-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 | Lowering | C-52-06CR-CME04-1010, C-52-06CR-CMA11-1020 | C-52-06CR-CME04-1010: FS, C-52-06CR-CMA11-1020: FS | C-52-06CR-CME04-1030, C-52-06CR-CME05-1020 | C-52-06CR-CME04-1030: FS, C-52-06CR-CME05-1020: FS | 2025-06-17 15:00 | 2025-06-19 15:00
C-52-06CR-CME04-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 | Section Tie-in Welding | C-52-06CR-CME04-1020 | C-52-06CR-CME04-1020: FS | C-52-06CR-CME04-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CME04-1040: FS, C-52-06CR-PL-ME-4810: FF 1 | 2025-06-19 15:00 | 2025-06-23 15:00
C-52-06CR-CME04-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 | NDT (Tie-in Joint) | C-52-06CR-CME04-1030 | C-52-06CR-CME04-1030: FS | C-52-06CR-CME04-1050 | C-52-06CR-CME04-1050: FS | 2025-06-23 15:00 | 2025-06-26 15:00
C-52-06CR-CME04-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME04-1040 | C-52-06CR-CME04-1040: FS | C-52-06CR-CME04-1060 | C-52-06CR-CME04-1060: FS | 2025-06-26 15:00 | 2025-07-01 15:00
C-52-06CR-CME04-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 | Holiday Testing | C-52-06CR-CME04-1050 | C-52-06CR-CME04-1050: FS | C-52-06CR-CME04-1070 | C-52-06CR-CME04-1070: FS | 2025-07-01 15:00 | 2025-07-03 15:00
C-52-06CR-CME04-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 | Padding & Back Filling | C-52-06CR-CME04-1060 | C-52-06CR-CME04-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-03 15:00 | 2025-07-05 15:00
C-52-06CR-CME05-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 | Trench Excavation | C-52-06CR-CME04-1000 | C-52-06CR-CME04-1000: FS 1 | C-52-06CR-CME05-1010, C-52-06CR-CME06-1000 | C-52-06CR-CME05-1010: FS, C-52-06CR-CME06-1000: FS 1 | 2025-06-16 15:00 | 2025-06-18 15:00
C-52-06CR-CME05-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 | Bedding | C-52-06CR-CME05-1000 | C-52-06CR-CME05-1000: FS | C-52-06CR-CME05-1020 | C-52-06CR-CME05-1020: FS | 2025-06-18 15:00 | 2025-06-20 15:00
C-52-06CR-CME05-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 | Lowering | C-52-06CR-CME05-1010, C-52-06CR-CME04-1020 | C-52-06CR-CME05-1010: FS, C-52-06CR-CME04-1020: FS | C-52-06CR-CME05-1030, C-52-06CR-CME06-1020 | C-52-06CR-CME05-1030: FS, C-52-06CR-CME06-1020: FS | 2025-06-20 15:00 | 2025-06-23 15:00
C-52-06CR-CME05-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 | Section Tie-in Welding | C-52-06CR-CME05-1020 | C-52-06CR-CME05-1020: FS | C-52-06CR-CME05-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CME05-1040: FS, C-52-06CR-PL-ME-4810: FF 1 | 2025-06-23 15:00 | 2025-06-26 15:00
C-52-06CR-CME05-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 | NDT (Tie-in Joint) | C-52-06CR-CME05-1030 | C-52-06CR-CME05-1030: FS | C-52-06CR-CME05-1050 | C-52-06CR-CME05-1050: FS | 2025-06-26 15:00 | 2025-07-01 15:00
C-52-06CR-CME05-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME05-1040 | C-52-06CR-CME05-1040: FS | C-52-06CR-CME05-1060 | C-52-06CR-CME05-1060: FS | 2025-07-01 15:00 | 2025-07-04 15:00
C-52-06CR-CME05-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 | Holiday Testing | C-52-06CR-CME05-1050 | C-52-06CR-CME05-1050: FS | C-52-06CR-CME05-1070 | C-52-06CR-CME05-1070: FS | 2025-07-04 15:00 | 2025-07-07 15:00
C-52-06CR-CME05-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 | Padding & Back Filling | C-52-06CR-CME05-1060 | C-52-06CR-CME05-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-07 15:00 | 2025-07-09 15:00
C-52-06CR-CME06-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 | Trench Excavation | C-52-06CR-CME05-1000 | C-52-06CR-CME05-1000: FS 1 | C-52-06CR-CME06-1010, C-52-06CR-CME07-1000 | C-52-06CR-CME06-1010: FS, C-52-06CR-CME07-1000: FS 1 | 2025-06-19 15:00 | 2025-06-21 15:00
C-52-06CR-CME06-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 | Bedding | C-52-06CR-CME06-1000 | C-52-06CR-CME06-1000: FS | C-52-06CR-CME06-1020 | C-52-06CR-CME06-1020: FS | 2025-06-21 15:00 | 2025-06-24 15:00
C-52-06CR-CME06-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 | Lowering | C-52-06CR-CME06-1010, C-52-06CR-CME05-1020 | C-52-06CR-CME06-1010: FS, C-52-06CR-CME05-1020: FS | C-52-06CR-CME06-1030 | C-52-06CR-CME06-1030: FS | 2025-06-24 15:00 | 2025-06-26 15:00
C-52-06CR-CME06-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 | Section Tie-in Welding | C-52-06CR-CME06-1020 | C-52-06CR-CME06-1020: FS | C-52-06CR-CME06-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CME06-1040: FS, C-52-06CR-PL-ME-4810: FF 1 | 2025-06-26 15:00 | 2025-07-01 15:00
C-52-06CR-CME06-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 | NDT (Tie-in Joint) | C-52-06CR-CME06-1030 | C-52-06CR-CME06-1030: FS | C-52-06CR-CME06-1050 | C-52-06CR-CME06-1050: FS | 2025-07-01 15:00 | 2025-07-04 15:00
C-52-06CR-CME06-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME06-1040 | C-52-06CR-CME06-1040: FS | C-52-06CR-CME06-1060 | C-52-06CR-CME06-1060: FS | 2025-07-04 15:00 | 2025-07-08 15:00
C-52-06CR-CME06-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 | Holiday Testing | C-52-06CR-CME06-1050 | C-52-06CR-CME06-1050: FS | C-52-06CR-CME06-1070 | C-52-06CR-CME06-1070: FS | 2025-07-08 15:00 | 2025-07-10 15:00
C-52-06CR-CME06-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 | Padding & Back Filling | C-52-06CR-CME06-1060 | C-52-06CR-CME06-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-10 15:00 | 2025-07-12 15:00
C-52-06CR-CME07-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 | Trench Excavation | C-52-06CR-CME06-1000 | C-52-06CR-CME06-1000: FS 1 | C-52-06CR-CME07-1010, C-52-06CR-CME08-1000 | C-52-06CR-CME07-1010: FS, C-52-06CR-CME08-1000: FS 1 | 2025-06-23 15:00 | 2025-06-25 15:00
C-52-06CR-CME07-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 | Bedding | C-52-06CR-CME07-1000 | C-52-06CR-CME07-1000: FS | C-52-06CR-CME07-1020 | C-52-06CR-CME07-1020: FS | 2025-06-25 15:00 | 2025-06-28 15:00
C-52-06CR-CME07-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 | Lowering | C-52-06CR-CME07-1010, C-52-06CR-CMA11-1020 | C-52-06CR-CME07-1010: FS, C-52-06CR-CMA11-1020: FS | C-52-06CR-CME07-1030, C-52-06CR-CME08-1020 | C-52-06CR-CME07-1030: FS, C-52-06CR-CME08-1020: FS | 2025-06-28 15:00 | 2025-07-01 15:00
C-52-06CR-CME07-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 | Section Tie-in Welding | C-52-06CR-CME07-1020 | C-52-06CR-CME07-1020: FS | C-52-06CR-CME07-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CME07-1040: FS, C-52-06CR-PL-ME-4810: FF 1 | 2025-07-01 15:00 | 2025-07-04 15:00
C-52-06CR-CME07-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 | NDT (Tie-in Joint) | C-52-06CR-CME07-1030 | C-52-06CR-CME07-1030: FS | C-52-06CR-CME07-1050 | C-52-06CR-CME07-1050: FS | 2025-07-04 15:00 | 2025-07-08 15:00
C-52-06CR-CME07-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME07-1040 | C-52-06CR-CME07-1040: FS | C-52-06CR-CME07-1060 | C-52-06CR-CME07-1060: FS | 2025-07-08 15:00 | 2025-07-11 15:00
C-52-06CR-CME07-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 | Holiday Testing | C-52-06CR-CME07-1050 | C-52-06CR-CME07-1050: FS | C-52-06CR-CME07-1070 | C-52-06CR-CME07-1070: FS | 2025-07-11 15:00 | 2025-07-14 15:00
C-52-06CR-CME07-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 | Padding & Back Filling | C-52-06CR-CME07-1060 | C-52-06CR-CME07-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-14 15:00 | 2025-07-16 15:00
C-52-06CR-CME08-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 | Trench Excavation | C-52-06CR-CME07-1000 | C-52-06CR-CME07-1000: FS 1 | C-52-06CR-CME08-1010, C-52-06CR-CME09-1000 | C-52-06CR-CME08-1010: SS, C-52-06CR-CME09-1000: FS 1 | 2025-06-26 15:00 | 2025-06-30 15:00
C-52-06CR-CME08-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 | Bedding | C-52-06CR-CME08-1000 | C-52-06CR-CME08-1000: SS | C-52-06CR-CME08-1020 | C-52-06CR-CME08-1020: FS | 2025-06-26 15:00 | 2025-06-30 15:00
C-52-06CR-CME08-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 | Lowering | C-52-06CR-CME08-1010, C-52-06CR-CME07-1020 | C-52-06CR-CME08-1010: FS, C-52-06CR-CME07-1020: FS | C-52-06CR-CME08-1030, C-52-06CR-CME09-1020 | C-52-06CR-CME08-1030: FS, C-52-06CR-CME09-1020: FS | 2025-07-01 15:00 | 2025-07-03 15:00
C-52-06CR-CME08-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 | Section Tie-in Welding | C-52-06CR-CME08-1020 | C-52-06CR-CME08-1020: FS | C-52-06CR-CME08-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CME08-1040: FS, C-52-06CR-PL-ME-4810: FF 1 | 2025-07-03 15:00 | 2025-07-07 15:00
C-52-06CR-CME08-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 | NDT (Tie-in Joint) | C-52-06CR-CME08-1030 | C-52-06CR-CME08-1030: FS | C-52-06CR-CME08-1050 | C-52-06CR-CME08-1050: FS | 2025-07-07 15:00 | 2025-07-10 15:00
C-52-06CR-CME08-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME08-1040 | C-52-06CR-CME08-1040: FS | C-52-06CR-CME08-1060 | C-52-06CR-CME08-1060: FS | 2025-07-10 15:00 | 2025-07-14 15:00
C-52-06CR-CME08-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 | Holiday Testing | C-52-06CR-CME08-1050 | C-52-06CR-CME08-1050: FS | C-52-06CR-CME08-1070 | C-52-06CR-CME08-1070: FS | 2025-07-14 15:00 | 2025-07-16 15:00
C-52-06CR-CME08-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 | Padding & Back Filling | C-52-06CR-CME08-1060 | C-52-06CR-CME08-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-16 15:00 | 2025-07-18 15:00
C-52-06CR-CME09-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 | Trench Excavation | C-52-06CR-CME08-1000 | C-52-06CR-CME08-1000: FS 1 | C-52-06CR-CME09-1010, C-52-06CR-CME10-1000, C-52-06CR-CME13-1000 | C-52-06CR-CME09-1010: FS, C-52-06CR-CME10-1000: FS 1, C-52-06CR-CME13-1000: FS | 2025-07-01 15:00 | 2025-07-03 15:00
C-52-06CR-CME09-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 | Bedding | C-52-06CR-CME09-1000 | C-52-06CR-CME09-1000: FS | C-52-06CR-CME09-1020 | C-52-06CR-CME09-1020: FS | 2025-07-03 15:00 | 2025-07-05 15:00
C-52-06CR-CME09-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 | Lowering | C-52-06CR-CME09-1010, C-52-06CR-CME08-1020 | C-52-06CR-CME09-1010: FS, C-52-06CR-CME08-1020: FS | C-52-06CR-CME09-1030, C-52-06CR-CME10-1020 | C-52-06CR-CME09-1030: FS, C-52-06CR-CME10-1020: FS | 2025-07-05 15:00 | 2025-07-08 15:00
C-52-06CR-CME09-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 | Section Tie-in Welding | C-52-06CR-CME09-1020 | C-52-06CR-CME09-1020: FS | C-52-06CR-CME09-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CME09-1040: FS, C-52-06CR-PL-ME-4810: FF 1 | 2025-07-08 15:00 | 2025-07-11 15:00
C-52-06CR-CME09-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 | NDT (Tie-in Joint) | C-52-06CR-CME09-1030 | C-52-06CR-CME09-1030: FS | C-52-06CR-CME09-1050 | C-52-06CR-CME09-1050: FS | 2025-07-11 15:00 | 2025-07-15 15:00
C-52-06CR-CME09-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME09-1040 | C-52-06CR-CME09-1040: FS | C-52-06CR-CME09-1060 | C-52-06CR-CME09-1060: FS | 2025-07-15 15:00 | 2025-07-18 15:00
C-52-06CR-CME09-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 | Holiday Testing | C-52-06CR-CME09-1050 | C-52-06CR-CME09-1050: FS | C-52-06CR-CME09-1070 | C-52-06CR-CME09-1070: FS | 2025-07-18 15:00 | 2025-07-21 15:00
C-52-06CR-CME09-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 | Padding & Back Filling | C-52-06CR-CME09-1060 | C-52-06CR-CME09-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-21 15:00 | 2025-07-23 15:00
C-52-06CR-CME10-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 | Trench Excavation | C-52-06CR-CME09-1000, C-56-HC01-CME10-1170 | C-52-06CR-CME09-1000: FS 1, C-56-HC01-CME10-1170: FS 1 | C-52-06CR-CME10-1010, C-52-06CR-CME11-1000 | C-52-06CR-CME10-1010: FS, C-52-06CR-CME11-1000: FS 1 | 2025-07-04 15:00 | 2025-07-07 15:00
C-52-06CR-CME10-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 | Bedding | C-52-06CR-CME10-1000 | C-52-06CR-CME10-1000: FS | C-52-06CR-CME10-1020 | C-52-06CR-CME10-1020: FS | 2025-07-07 15:00 | 2025-07-09 15:00
C-52-06CR-CME10-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 | Lowering | C-52-06CR-CME10-1010, C-52-06CR-CME09-1020 | C-52-06CR-CME10-1010: FS, C-52-06CR-CME09-1020: FS | C-52-06CR-CME10-1030, C-52-06CR-CME11-1020 | C-52-06CR-CME10-1030: FS, C-52-06CR-CME11-1020: FS | 2025-07-09 15:00 | 2025-07-11 15:00
C-52-06CR-CME10-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 | Section Tie-in Welding | C-52-06CR-CME10-1020 | C-52-06CR-CME10-1020: FS | C-52-06CR-CME10-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CME10-1040: FS, C-52-06CR-PL-ME-4810: FF 1 | 2025-07-11 15:00 | 2025-07-15 15:00
C-52-06CR-CME10-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 | NDT (Tie-in Joint) | C-52-06CR-CME10-1030 | C-52-06CR-CME10-1030: FS | C-52-06CR-CME10-1050 | C-52-06CR-CME10-1050: FS | 2025-07-15 15:00 | 2025-07-18 15:00
C-52-06CR-CME10-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME10-1040 | C-52-06CR-CME10-1040: FS | C-52-06CR-CME10-1060 | C-52-06CR-CME10-1060: FS | 2025-07-18 15:00 | 2025-07-22 15:00
C-52-06CR-CME10-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 | Holiday Testing | C-52-06CR-CME10-1050 | C-52-06CR-CME10-1050: FS | C-52-06CR-CME10-1070 | C-52-06CR-CME10-1070: FS | 2025-07-22 15:00 | 2025-07-24 15:00
C-52-06CR-CME10-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 | Padding & Back Filling | C-52-06CR-CME10-1060 | C-52-06CR-CME10-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-24 15:00 | 2025-07-26 15:00
C-52-06CR-CME11-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 | Trench Excavation | C-52-06CR-CME10-1000 | C-52-06CR-CME10-1000: FS 1 | C-52-06CR-CME11-1010, C-52-06CR-CME12-1000 | C-52-06CR-CME11-1010: FS, C-52-06CR-CME12-1000: FS 1 | 2025-07-08 15:00 | 2025-07-10 15:00
C-52-06CR-CME11-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 | Bedding | C-52-06CR-CME11-1000 | C-52-06CR-CME11-1000: FS | C-52-06CR-CME11-1020 | C-52-06CR-CME11-1020: FS | 2025-07-10 15:00 | 2025-07-12 15:00
C-52-06CR-CME11-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 | Lowering | C-52-06CR-CME11-1010, C-52-06CR-CME10-1020 | C-52-06CR-CME11-1010: FS, C-52-06CR-CME10-1020: FS | C-52-06CR-CME11-1030, C-52-06CR-CME12-1020 | C-52-06CR-CME11-1030: FS, C-52-06CR-CME12-1020: FS | 2025-07-12 15:00 | 2025-07-15 15:00
C-52-06CR-CME11-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 | Section Tie-in Welding | C-52-06CR-CME11-1020 | C-52-06CR-CME11-1020: FS | C-52-06CR-CME11-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CME11-1040: FS, C-52-06CR-PL-ME-4810: FF 1 | 2025-07-15 15:00 | 2025-07-18 15:00
C-52-06CR-CME11-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 | NDT (Tie-in Joint) | C-52-06CR-CME11-1030 | C-52-06CR-CME11-1030: FS | C-52-06CR-CME11-1050 | C-52-06CR-CME11-1050: FS | 2025-07-18 15:00 | 2025-07-22 15:00
C-52-06CR-CME11-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME11-1040 | C-52-06CR-CME11-1040: FS | C-52-06CR-CME11-1060 | C-52-06CR-CME11-1060: FS | 2025-07-22 15:00 | 2025-07-25 15:00
C-52-06CR-CME11-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 | Holiday Testing | C-52-06CR-CME11-1050 | C-52-06CR-CME11-1050: FS | C-52-06CR-CME11-1070 | C-52-06CR-CME11-1070: FS | 2025-07-25 15:00 | 2025-07-28 15:00
C-52-06CR-CME11-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 | Padding & Back Filling | C-52-06CR-CME11-1060 | C-52-06CR-CME11-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-28 15:00 | 2025-07-30 15:00
C-52-06CR-CME12-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 | Trench Excavation | C-52-06CR-CME11-1000 | C-52-06CR-CME11-1000: FS 1 | C-52-06CR-CME12-1010, C-52-06CR-CME13-1000, C-52-06CR-CME14-1000 | C-52-06CR-CME12-1010: FS, C-52-06CR-CME13-1000: FS, C-52-06CR-CME14-1000: FS | 2025-07-11 15:00 | 2025-07-14 15:00
C-52-06CR-CME12-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 | Bedding | C-52-06CR-CME12-1000 | C-52-06CR-CME12-1000: FS | C-52-06CR-CME12-1020 | C-52-06CR-CME12-1020: FS | 2025-07-14 15:00 | 2025-07-16 15:00
C-52-06CR-CME12-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 | Lowering | C-52-06CR-CME12-1010, C-52-06CR-CME11-1020 | C-52-06CR-CME12-1010: FS, C-52-06CR-CME11-1020: FS | C-52-06CR-CME12-1030, C-52-06CR-CME13-1020 | C-52-06CR-CME12-1030: FS, C-52-06CR-CME13-1020: FS | 2025-07-16 15:00 | 2025-07-18 15:00
C-52-06CR-CME12-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 | Section Tie-in Welding | C-52-06CR-CME12-1020 | C-52-06CR-CME12-1020: FS | C-52-06CR-CME12-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CME12-1040: FS, C-52-06CR-PL-ME-4810: FF 1 | 2025-07-18 15:00 | 2025-07-22 15:00
C-52-06CR-CME12-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 | NDT (Tie-in Joint) | C-52-06CR-CME12-1030 | C-52-06CR-CME12-1030: FS | C-52-06CR-CME12-1050 | C-52-06CR-CME12-1050: FS | 2025-07-22 15:00 | 2025-07-25 15:00
C-52-06CR-CME12-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME12-1040 | C-52-06CR-CME12-1040: FS | C-52-06CR-CME12-1060 | C-52-06CR-CME12-1060: FS | 2025-07-25 15:00 | 2025-07-29 15:00
C-52-06CR-CME12-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 | Holiday Testing | C-52-06CR-CME12-1050 | C-52-06CR-CME12-1050: FS | C-52-06CR-CME12-1070 | C-52-06CR-CME12-1070: FS | 2025-07-29 15:00 | 2025-07-31 15:00
C-52-06CR-CME12-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 | Padding & Back Filling | C-52-06CR-CME12-1060 | C-52-06CR-CME12-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-07-31 15:00 | 2025-08-02 15:00
C-52-06CR-CME13-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 | Trench Excavation | C-52-06CR-CME12-1000, C-52-06CR-CME09-1000 | C-52-06CR-CME12-1000: FS, C-52-06CR-CME09-1000: FS | C-52-06CR-CME13-1010, C-52-06CR-CME14-1000, C-52-06CR-CME29-1080 | C-52-06CR-CME13-1010: FS, C-52-06CR-CME14-1000: FS 1, C-52-06CR-CME29-1080: FS | 2025-07-14 15:00 | 2025-07-16 15:00
C-52-06CR-CME13-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 | Bedding | C-52-06CR-CME13-1000 | C-52-06CR-CME13-1000: FS | C-52-06CR-CME13-1020 | C-52-06CR-CME13-1020: FS | 2025-07-16 15:00 | 2025-07-18 15:00
C-52-06CR-CME13-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 | Lowering | C-52-06CR-CME13-1010, C-52-06CR-CME12-1020 | C-52-06CR-CME13-1010: FS, C-52-06CR-CME12-1020: FS | C-52-06CR-CME13-1030, C-52-06CR-CME14-1020 | C-52-06CR-CME13-1030: FS, C-52-06CR-CME14-1020: FS | 2025-07-18 15:00 | 2025-07-21 15:00
C-52-06CR-CME13-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 | Section Tie-in Welding | C-52-06CR-CME13-1020 | C-52-06CR-CME13-1020: FS | C-52-06CR-CME13-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CME13-1040: FS, C-52-06CR-PL-ME-4810: FF 1 | 2025-07-21 15:00 | 2025-07-24 15:00
C-52-06CR-CME13-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 | NDT (Tie-in Joint) | C-52-06CR-CME13-1030 | C-52-06CR-CME13-1030: FS | C-52-06CR-CME13-1050 | C-52-06CR-CME13-1050: FS | 2025-07-24 15:00 | 2025-07-28 15:00
C-52-06CR-CME13-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME13-1040 | C-52-06CR-CME13-1040: FS | C-52-06CR-CME13-1060 | C-52-06CR-CME13-1060: FS | 2025-07-28 15:00 | 2025-07-31 15:00
C-52-06CR-CME13-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 | Holiday Testing | C-52-06CR-CME13-1050 | C-52-06CR-CME13-1050: FS | C-52-06CR-CME13-1070 | C-52-06CR-CME13-1070: FS | 2025-07-31 15:00 | 2025-08-02 15:00
C-52-06CR-CME13-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 | Padding & Back Filling | C-52-06CR-CME13-1060 | C-52-06CR-CME13-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-08-02 15:00 | 2025-08-05 15:00
C-52-06CR-CME14-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 | Trench Excavation | C-52-06CR-CME13-1000, C-52-06CR-CME12-1000 | C-52-06CR-CME13-1000: FS 1, C-52-06CR-CME12-1000: FS | C-52-06CR-CME14-1010, C-52-06CR-CME29-1080 | C-52-06CR-CME14-1010: FS, C-52-06CR-CME29-1080: FS | 2025-07-17 15:00 | 2025-07-19 15:00
C-52-06CR-CME14-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 | Bedding | C-52-06CR-CME14-1000 | C-52-06CR-CME14-1000: FS | C-52-06CR-CME14-1020 | C-52-06CR-CME14-1020: FS | 2025-07-19 15:00 | 2025-07-22 15:00
C-52-06CR-CME14-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 | Lowering | C-52-06CR-CME14-1010, C-52-06CR-CME13-1020 | C-52-06CR-CME14-1010: FS, C-52-06CR-CME13-1020: FS | C-52-06CR-CME14-1030 | C-52-06CR-CME14-1030: FS | 2025-07-22 15:00 | 2025-07-24 15:00
C-52-06CR-CME14-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 | Section Tie-in Welding | C-52-06CR-CME14-1020 | C-52-06CR-CME14-1020: FS | C-52-06CR-CME14-1040, C-52-06CR-PL-ME-4810 | C-52-06CR-CME14-1040: FS, C-52-06CR-PL-ME-4810: FF 1 | 2025-07-24 15:00 | 2025-07-28 15:00
C-52-06CR-CME14-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 | NDT (Tie-in Joint) | C-52-06CR-CME14-1030 | C-52-06CR-CME14-1030: FS | C-52-06CR-CME14-1050 | C-52-06CR-CME14-1050: FS | 2025-07-28 15:00 | 2025-07-31 15:00
C-52-06CR-CME14-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME14-1040 | C-52-06CR-CME14-1040: FS | C-52-06CR-CME14-1060 | C-52-06CR-CME14-1060: FS | 2025-07-31 15:00 | 2025-08-04 15:00
C-52-06CR-CME14-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 | Holiday Testing | C-52-06CR-CME14-1050 | C-52-06CR-CME14-1050: FS | C-52-06CR-CME14-1070 | C-52-06CR-CME14-1070: FS | 2025-08-04 15:00 | 2025-08-06 15:00
C-52-06CR-CME14-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 | Padding & Back Filling | C-52-06CR-CME14-1060 | C-52-06CR-CME14-1060: FS | C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF 1, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF 1, C-52-06CR-PL-CI-6000: FF | 2025-08-06 15:00 | 2025-08-08 15:00
C-56-01HG-CNM13-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 | Sheet Piling for Driving & Receiving Pit | HE-PL-2970, C-PER-1470 | HE-PL-2970: FS, C-PER-1470: FS | C-56-01HG-CNM13-1020, C-56-01HG-CNM13-1010 | C-56-01HG-CNM13-1020: FS, C-56-01HG-CNM13-1010: FS | 2025-01-09 07:00 | 2025-01-20 17:00
C-56-01HG-CNM13-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 | Installation of Dewatering System for Driving & Receiving Pit | C-56-01HG-CNM13-1000 | C-56-01HG-CNM13-1000: FS | C-56-01HG-CNM13-1030 | C-56-01HG-CNM13-1030: FS | 2025-01-21 07:00 | 2025-01-24 17:00
C-56-01HG-CNM13-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 | Driving & Receiving Pit Excavation | C-56-01HG-CNM13-1000 | C-56-01HG-CNM13-1000: FS | C-56-01HG-CNM13-1030 | C-56-01HG-CNM13-1030: FF | 2025-01-21 07:00 | 2025-02-05 17:00
C-56-01HG-CNM13-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-01HG-CNM13-1010, C-56-01HG-CNM13-1020 | C-56-01HG-CNM13-1010: FF, C-56-01HG-CNM13-1020: FS | C-56-01HG-CNM13-1040 | C-56-01HG-CNM13-1040: FS | 2025-01-25 07:00 | 2025-02-05 17:00
C-56-01HG-CNM13-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 | Floor Blinding & French Drain in Driving Pit | C-56-01HG-CNM13-1030 | C-56-01HG-CNM13-1030: FS | C-56-01HG-CNM13-1050 | C-56-01HG-CNM13-1050: FS | 2025-02-06 07:00 | 2025-02-12 17:00
C-56-01HG-CNM13-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-01HG-CNM13-1040 | C-56-01HG-CNM13-1040: FS | C-56-01HG-CNM13-1060 | C-56-01HG-CNM13-1060: SS 7 | 2025-02-13 07:00 | 2025-02-19 17:00
C-56-01HG-CNM13-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 | Construction of Exit Wall with Ring | C-56-01HG-CNM13-1050 | C-56-01HG-CNM13-1050: SS 7 | C-56-01HG-CNM13-1200 | C-56-01HG-CNM13-1200: FS | 2025-02-21 07:00 | 2025-02-27 17:00
C-56-01HG-CNM13-1200 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.1.2 | Jacking of MTBM & RC Sleeves | C-56-01HG-CNM13-1060 | C-56-01HG-CNM13-1060: FS | C-56-01HG-CNM13-1210 | C-56-01HG-CNM13-1210: FS | 2025-02-28 07:00 | 2025-03-09 11:00
C-56-01HG-CNM13-1210 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.1.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-56-01HG-CNM13-1200 | C-56-01HG-CNM13-1200: FS | C-56-01HG-CNM13-1400 | C-56-01HG-CNM13-1400: FS | 2025-03-09 11:00 | 2025-03-15 15:00
C-56-01HG-CNM13-1400 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.1.3 | Lowering & Welding of Carrier Pipe | C-56-01HG-CNM13-1210 | C-56-01HG-CNM13-1210: FS | C-56-01HG-CNM13-1410 | C-56-01HG-CNM13-1410: SS 1 | 2025-03-15 15:00 | 2025-04-03 13:00
C-56-01HG-CNM13-1410 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.1.3 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-56-01HG-CNM13-1400 | C-56-01HG-CNM13-1400: SS 1 | C-56-01HG-CNM13-1600 | C-56-01HG-CNM13-1600: FS | 2025-03-17 09:00 | 2025-04-04 13:00
C-56-01HG-CNM13-1600 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.1.4 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-01HG-CNM13-1410 | C-56-01HG-CNM13-1410: FS | C-56-01HG-CNM13-1220 | C-56-01HG-CNM13-1220: FS | 2025-04-04 13:00 | 2025-04-14 13:00
C-56-01HG-CNM13-1220 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.1.2 | Inner Grout b/w Main & RC Pipe | C-56-01HG-CNM13-1600 | C-56-01HG-CNM13-1600: FS | C-56-01HG-CNM13-1800, C-56-01HG-PL-CA-5220, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-TE-8400 | C-56-01HG-CNM13-1800: FS, C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-TE-8400: FF | 2025-04-14 13:00 | 2025-04-19 13:00
C-56-01HG-CNM13-1800 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.1.5 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-01HG-CNM13-1220 | C-56-01HG-CNM13-1220: FS | C-56-01HG-PL-CI-6800, C-56-01HG-PL-CI-7000, ML1579-E03, C-56-01HG-PL-ME-7400 | C-56-01HG-PL-CI-6800: FF 1, C-56-01HG-PL-CI-7000: FF 1, ML1579-E03: FS, C-56-01HG-PL-ME-7400: FS | 2025-04-19 13:00 | 2025-05-01 13:00
C-56-01HG-CNM12-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 | Sheet Piling for Driving & Receiving Pit | HE-PL-2910, HE-PL-2970, C-PER-1460 | HE-PL-2910: FS, HE-PL-2970: FS, C-PER-1460: FS | C-56-01HG-CNM12-1020, C-56-01HG-CNM12-1010 | C-56-01HG-CNM12-1020: FS, C-56-01HG-CNM12-1010: FS | 2024-11-26 07:00 | 2025-01-08 17:00
C-56-01HG-CNM12-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 | Installation of Dewatering System for Driving & Receiving Pit | C-56-01HG-CNM12-1000 | C-56-01HG-CNM12-1000: FS | C-56-01HG-CNM12-1030 | C-56-01HG-CNM12-1030: FS | 2025-01-09 07:00 | 2025-01-13 17:00
C-56-01HG-CNM12-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 | Driving & Receiving Pit Excavation | C-56-01HG-CNM12-1000 | C-56-01HG-CNM12-1000: FS | C-56-01HG-CNM12-1030 | C-56-01HG-CNM12-1030: FF | 2025-01-09 07:00 | 2025-02-06 17:00
C-56-01HG-CNM12-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-01HG-CNM12-1010, C-56-01HG-CNM12-1020 | C-56-01HG-CNM12-1010: FF, C-56-01HG-CNM12-1020: FS | C-56-01HG-CNM12-1040 | C-56-01HG-CNM12-1040: FS | 2025-01-15 07:00 | 2025-02-06 17:00
C-56-01HG-CNM12-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 | Floor Blinding & French Drain in Driving Pit | C-56-01HG-CNM12-1030 | C-56-01HG-CNM12-1030: FS | C-56-01HG-CNM12-1050 | C-56-01HG-CNM12-1050: FS | 2025-02-07 07:00 | 2025-02-15 17:00
C-56-01HG-CNM12-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-01HG-CNM12-1040 | C-56-01HG-CNM12-1040: FS | C-56-01HG-CNM12-1060 | C-56-01HG-CNM12-1060: SS 7 | 2025-02-17 07:00 | 2025-02-25 17:00
C-56-01HG-CNM12-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 | Construction of Exit Wall with Ring | C-56-01HG-CNM12-1050 | C-56-01HG-CNM12-1050: SS 7 | C-56-01HG-CNM12-1200 | C-56-01HG-CNM12-1200: FS | 2025-02-25 07:00 | 2025-03-06 13:00
C-56-01HG-CNM12-1200 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.2.2 | Jacking of MTBM & RC Sleeves | C-56-01HG-CNM12-1060 | C-56-01HG-CNM12-1060: FS | C-56-01HG-CNM12-1210 | C-56-01HG-CNM12-1210: FS | 2025-03-07 07:00 | 2025-05-01 17:00
C-56-01HG-CNM12-1210 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.2.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-56-01HG-CNM12-1200 | C-56-01HG-CNM12-1200: FS | C-56-01HG-CNM12-1400 | C-56-01HG-CNM12-1400: FS | 2025-05-02 07:00 | 2025-05-07 12:00
C-56-01HG-CNM12-1400 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.2.3 | Lowering & Welding of Carrier Pipe | C-56-01HG-CNM12-1210 | C-56-01HG-CNM12-1210: FS | C-56-01HG-CNM12-1410 | C-56-01HG-CNM12-1410: SS 1 | 2025-05-07 12:00 | 2025-06-25 15:00
C-56-01HG-CNM12-1410 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.2.3 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-56-01HG-CNM12-1400 | C-56-01HG-CNM12-1400: SS 1 | C-56-01HG-CNM12-1600 | C-56-01HG-CNM12-1600: FS | 2025-05-08 14:00 | 2025-06-26 15:00
C-56-01HG-CNM12-1600 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.2.4 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-01HG-CNM12-1410 | C-56-01HG-CNM12-1410: FS | C-56-01HG-CNM12-1220 | C-56-01HG-CNM12-1220: FS | 2025-06-26 15:00 | 2025-07-11 15:00
C-56-01HG-CNM12-1220 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.2.2 | Inner Grout b/w Main & RC Pipe | C-56-01HG-CNM12-1600 | C-56-01HG-CNM12-1600: FS | C-56-01HG-CNM12-1800, C-56-01HG-PL-CA-5220, C-56-01HG-PL-CA-5420, C-56-01HG-PL-TE-8400 | C-56-01HG-CNM12-1800: FS, C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-TE-8400: FF | 2025-07-11 15:00 | 2025-07-17 15:00
C-56-01HG-CNM12-1800 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.2.5 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-01HG-CNM12-1220 | C-56-01HG-CNM12-1220: FS | ML1579-E03, C-56-01HG-PL-ME-7400 | ML1579-E03: FS, C-56-01HG-PL-ME-7400: FS | 2025-07-17 15:00 | 2025-08-02 15:00
C-56-01HG-CNM11-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 | Sheet Piling for Driving & Receiving Pit | HE-PL-2910, HE-PL-2970, C-PER-1450 | HE-PL-2910: FS, HE-PL-2970: FS, C-PER-1450: FS 10 | C-56-01HG-CNM11-1020, C-56-01HG-CNM11-1010 | C-56-01HG-CNM11-1020: FS, C-56-01HG-CNM11-1010: FS | 2024-12-14 07:00 | 2025-01-18 17:00
C-56-01HG-CNM11-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 | Installation of Dewatering System for Driving & Receiving Pit | C-56-01HG-CNM11-1000 | C-56-01HG-CNM11-1000: FS | C-56-01HG-CNM11-1030 | C-56-01HG-CNM11-1030: FS | 2025-01-20 07:00 | 2025-01-23 17:00
C-56-01HG-CNM11-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 | Driving & Receiving Pit Excavation | C-56-01HG-CNM11-1000 | C-56-01HG-CNM11-1000: FS | C-56-01HG-CNM11-1030 | C-56-01HG-CNM11-1030: FF | 2025-01-20 07:00 | 2025-02-17 17:00
C-56-01HG-CNM11-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-01HG-CNM11-1010, C-56-01HG-CNM11-1020 | C-56-01HG-CNM11-1010: FF, C-56-01HG-CNM11-1020: FS | C-56-01HG-CNM11-1040 | C-56-01HG-CNM11-1040: FS | 2025-01-25 07:00 | 2025-02-17 17:00
C-56-01HG-CNM11-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 | Floor Blinding & French Drain in Driving Pit | C-56-01HG-CNM11-1030 | C-56-01HG-CNM11-1030: FS | C-56-01HG-CNM11-1050 | C-56-01HG-CNM11-1050: FS | 2025-02-18 07:00 | 2025-02-26 17:00
C-56-01HG-CNM11-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-01HG-CNM11-1040 | C-56-01HG-CNM11-1040: FS | C-56-01HG-CNM11-1060 | C-56-01HG-CNM11-1060: SS 7 | 2025-02-27 07:00 | 2025-03-09 11:00
C-56-01HG-CNM11-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 | Construction of Exit Wall with Ring | C-56-01HG-CNM11-1050 | C-56-01HG-CNM11-1050: SS 7 | C-56-01HG-CNM11-1200 | C-56-01HG-CNM11-1200: FS | 2025-03-08 11:00 | 2025-03-20 11:00
C-56-01HG-CNM11-1200 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.3.2 | Jacking of MTBM & RC Sleeves | C-56-01HG-CNM11-1060 | C-56-01HG-CNM11-1060: FS | C-56-01HG-CNM11-1210 | C-56-01HG-CNM11-1210: FS | 2025-03-20 11:00 | 2025-05-14 15:00
C-56-01HG-CNM11-1210 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.3.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-56-01HG-CNM11-1200 | C-56-01HG-CNM11-1200: FS | C-56-01HG-CNM11-1400 | C-56-01HG-CNM11-1400: FS | 2025-05-14 15:00 | 2025-05-19 15:00
C-56-01HG-CNM11-1400 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.3.3 | Lowering & Welding of Carrier Pipe | C-56-01HG-CNM11-1210 | C-56-01HG-CNM11-1210: FS | C-56-01HG-CNM11-1410 | C-56-01HG-CNM11-1410: SS 1 | 2025-05-19 15:00 | 2025-06-25 15:00
C-56-01HG-CNM11-1410 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.3.3 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-56-01HG-CNM11-1400 | C-56-01HG-CNM11-1400: SS 1 | C-56-01HG-CNM11-1600 | C-56-01HG-CNM11-1600: FS | 2025-05-20 15:00 | 2025-06-26 15:00
C-56-01HG-CNM11-1600 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.3.4 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-01HG-CNM11-1410 | C-56-01HG-CNM11-1410: FS | C-56-01HG-CNM11-1220 | C-56-01HG-CNM11-1220: FS | 2025-06-26 15:00 | 2025-07-11 15:00
C-56-01HG-CNM11-1220 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.3.2 | Inner Grout b/w Main & RC Pipe | C-56-01HG-CNM11-1600 | C-56-01HG-CNM11-1600: FS | C-56-01HG-CNM11-1800, C-56-01HG-PL-CA-5420, C-56-01HG-PL-TE-8400 | C-56-01HG-CNM11-1800: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-TE-8400: FF | 2025-07-11 15:00 | 2025-07-17 15:00
C-56-01HG-CNM11-1800 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.3.5 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-01HG-CNM11-1220 | C-56-01HG-CNM11-1220: FS | ML1579-E03, C-56-01HG-PL-ME-7400 | ML1579-E03: FS, C-56-01HG-PL-ME-7400: FS | 2025-07-17 15:00 | 2025-08-02 15:00
C-56-01HG-CNH10-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 | Sheet Piling for Driving & Receiving Pit | HE-PL-2910, HE-PL-2970, C-PER-1440 | HE-PL-2910: FS, HE-PL-2970: FS, C-PER-1440: FS 25 | C-56-01HG-CNH10-1020, C-56-01HG-CNH10-1010 | C-56-01HG-CNH10-1020: FS, C-56-01HG-CNH10-1010: FS | 2024-12-11 07:00 | 2025-01-21 17:00
C-56-01HG-CNH10-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 | Installation of Dewatering System for Driving & Receiving Pit | C-56-01HG-CNH10-1000 | C-56-01HG-CNH10-1000: FS | C-56-01HG-CNH10-1030 | C-56-01HG-CNH10-1030: SS | 2025-01-22 07:00 | 2025-01-25 17:00
C-56-01HG-CNH10-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 | Driving & Receiving Pit Excavation | C-56-01HG-CNH10-1000 | C-56-01HG-CNH10-1000: FS | C-56-01HG-CNH10-1030 | C-56-01HG-CNH10-1030: FF | 2025-01-22 07:00 | 2025-02-21 11:00
C-56-01HG-CNH10-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-01HG-CNH10-1010, C-56-01HG-CNH10-1020 | C-56-01HG-CNH10-1010: FF, C-56-01HG-CNH10-1020: SS | C-56-01HG-CNH10-1040 | C-56-01HG-CNH10-1040: FS | 2025-01-27 11:00 | 2025-02-21 11:00
C-56-01HG-CNH10-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 | Floor Blinding & French Drain in Driving Pit | C-56-01HG-CNH10-1030 | C-56-01HG-CNH10-1030: FS | C-56-01HG-CNH10-1050 | C-56-01HG-CNH10-1050: FS | 2025-02-21 11:00 | 2025-02-28 11:00
C-56-01HG-CNH10-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-01HG-CNH10-1040 | C-56-01HG-CNH10-1040: FS | C-56-01HG-CNH10-1060 | C-56-01HG-CNH10-1060: SS 7 | 2025-02-28 11:00 | 2025-03-08 15:00
C-56-01HG-CNH10-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 | Construction of Exit Wall with Ring | C-56-01HG-CNH10-1050 | C-56-01HG-CNH10-1050: SS 7 | C-56-01HG-CNH10-1200 | C-56-01HG-CNH10-1200: FS | 2025-03-10 09:00 | 2025-03-19 11:00
C-56-01HG-CNH10-1200 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.6.4.2 | Jacking of MTBM & RC Sleeves | C-56-01HG-CNH10-1060 | C-56-01HG-CNH10-1060: FS | C-56-01HG-CNH10-1210 | C-56-01HG-CNH10-1210: FS | 2025-03-19 11:00 | 2025-04-29 17:00
C-56-01HG-CNH10-1210 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.6.4.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-56-01HG-CNH10-1200 | C-56-01HG-CNH10-1200: FS | C-56-01HG-CNH10-1070 | C-56-01HG-CNH10-1070: FS | 2025-04-30 07:00 | 2025-05-03 17:00
C-56-01HG-CNH10-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 | Lowering & Welding of Carrier Pipe | C-56-01HG-CNH10-1210 | C-56-01HG-CNH10-1210: FS | C-56-01HG-CNH10-1080 | C-56-01HG-CNH10-1080: SS 1 | 2025-05-05 08:00 | 2025-06-11 15:00
C-56-01HG-CNH10-1080 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-56-01HG-CNH10-1070 | C-56-01HG-CNH10-1070: SS 1 | C-56-01HG-CNH10-1090 | C-56-01HG-CNH10-1090: FS | 2025-05-06 10:00 | 2025-06-12 15:00
C-56-01HG-CNH10-1090 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-01HG-CNH10-1080 | C-56-01HG-CNH10-1080: FS | C-56-01HG-CNH10-1220 | C-56-01HG-CNH10-1220: FS | 2025-06-12 15:00 | 2025-06-30 15:00
C-56-01HG-CNH10-1220 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.6.4.2 | Inner Grout b/w Main & RC Pipe | C-56-01HG-CNH10-1090 | C-56-01HG-CNH10-1090: FS | C-56-01HG-CNH10-1800, C-56-01HG-PL-CA-5220, C-56-01HG-PL-CA-5420 | C-56-01HG-CNH10-1800: FS, C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-CA-5420: FF | 2025-06-30 15:00 | 2025-07-05 15:00
C-56-01HG-CNH10-1800 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.6.4.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-01HG-CNH10-1220 | C-56-01HG-CNH10-1220: FS | ML1579-E03, C-56-01HG-PL-ME-7400 | ML1579-E03: FS, C-56-01HG-PL-ME-7400: FS | 2025-07-05 15:00 | 2025-07-22 15:00
C-56-HC01-CNM08-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 | Sheet Piling for Driving & Receiving Pit | HE-PL-2970, C-PER-1420, HE-PL-2910 | HE-PL-2970: FS, C-PER-1420: FS 15, HE-PL-2910: FS | C-56-HC01-CNM08-1020, C-56-HC01-CNM08-1010 | C-56-HC01-CNM08-1020: FS, C-56-HC01-CNM08-1010: FS | 2024-12-24 07:00 | 2025-02-20 17:00
C-56-HC01-CNM08-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 | Installation of Dewatering System for Driving & Receiving Pit | C-56-HC01-CNM08-1000 | C-56-HC01-CNM08-1000: FS | C-56-HC01-CNM08-1030 | C-56-HC01-CNM08-1030: FS | 2025-02-21 07:00 | 2025-02-25 17:00
C-56-HC01-CNM08-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 | Driving & Receiving Pit Excavation | C-56-HC01-CNM08-1000 | C-56-HC01-CNM08-1000: FS | C-56-HC01-CNM08-1030 | C-56-HC01-CNM08-1030: FF | 2025-02-21 07:00 | 2025-03-20 11:00
C-56-HC01-CNM08-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-HC01-CNM08-1010, C-56-HC01-CNM08-1020 | C-56-HC01-CNM08-1010: FF, C-56-HC01-CNM08-1020: FS | C-56-HC01-CNM08-1040 | C-56-HC01-CNM08-1040: FS 1 | 2025-02-26 07:00 | 2025-03-20 11:00
C-56-HC01-CNM08-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 | Floor Blinding & French Drain in Driving Pit | C-56-HC01-CNM08-1030 | C-56-HC01-CNM08-1030: FS 1 | C-56-HC01-CNM08-1050 | C-56-HC01-CNM08-1050: FS | 2025-03-22 07:00 | 2025-04-03 11:00
C-56-HC01-CNM08-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-HC01-CNM08-1040 | C-56-HC01-CNM08-1040: FS | C-56-HC01-CNM08-1060 | C-56-HC01-CNM08-1060: SS 7 | 2025-04-03 11:00 | 2025-04-10 11:00
C-56-HC01-CNM08-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 | Construction of Exit Wall with Ring | C-56-HC01-CNM08-1050 | C-56-HC01-CNM08-1050: SS 7 | C-56-HC01-CNM08-1200 | C-56-HC01-CNM08-1200: FS | 2025-04-11 11:00 | 2025-04-18 11:00
C-56-HC01-CNM08-1200 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.1.2 | Jacking of MTBM & RC Sleeves | C-56-HC01-CNM08-1060 | C-56-HC01-CNM08-1060: FS | C-56-HC01-CNM08-1210 | C-56-HC01-CNM08-1210: FS | 2025-04-18 11:00 | 2025-05-24 11:00
C-56-HC01-CNM08-1210 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.1.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-56-HC01-CNM08-1200 | C-56-HC01-CNM08-1200: FS | C-56-HC01-CNM08-1400 | C-56-HC01-CNM08-1400: FS | 2025-05-24 11:00 | 2025-05-29 11:00
C-56-HC01-CNM08-1400 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.1.3 | Lowering & Welding of Carrier Pipe | C-56-HC01-CNM08-1210 | C-56-HC01-CNM08-1210: FS | C-56-HC01-CNM08-1410 | C-56-HC01-CNM08-1410: SS 1 | 2025-05-29 11:00 | 2025-06-25 11:00
C-56-HC01-CNM08-1410 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.1.3 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-56-HC01-CNM08-1400 | C-56-HC01-CNM08-1400: SS 1 | C-56-HC01-CNM08-1600 | C-56-HC01-CNM08-1600: FS | 2025-05-30 11:00 | 2025-06-26 11:00
C-56-HC01-CNM08-1600 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.1.4 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-HC01-CNM08-1410 | C-56-HC01-CNM08-1410: FS | C-56-HC01-CNM08-1220 | C-56-HC01-CNM08-1220: FS | 2025-06-26 11:00 | 2025-07-11 11:00
C-56-HC01-CNM08-1220 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.1.2 | Inner Grout b/w Main & RC Pipe | C-56-HC01-CNM08-1600 | C-56-HC01-CNM08-1600: FS | C-56-HC01-CNM08-1800, C-56-HC01-PL-CA-5220, C-56-HC01-PL-CA-5400 | C-56-HC01-CNM08-1800: FS, C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-CA-5400: FF | 2025-07-11 11:00 | 2025-07-17 11:00
C-56-HC01-CNM08-1800 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.1.5 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-HC01-CNM08-1220 | C-56-HC01-CNM08-1220: FS | ML1579-E03, C-56-HC01-PL-CA-5220, C-56-HC01-PL-ME-7400 | ML1579-E03: FS, C-56-HC01-PL-CA-5220: FS, C-56-HC01-PL-ME-7400: FS | 2025-07-17 11:00 | 2025-08-02 11:00
C-56-HC01-CNH05-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 | Sheet Piling for Driving & Receiving Pit | HE-PL-2910, HE-PL-2970, C-PER-1390, C-56-HC01-CNM03-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-PER-1390: FS, C-56-HC01-CNM03-1000: FS | C-56-HC01-CNH05-1020, C-56-HC01-CNH05-1010 | C-56-HC01-CNH05-1020: FS, C-56-HC01-CNH05-1010: FS | 2025-02-03 07:00 | 2025-02-10 17:00
C-56-HC01-CNH05-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 | Installation of Dewatering System for Driving & Receiving Pit | C-56-HC01-CNH05-1000 | C-56-HC01-CNH05-1000: FS | C-56-HC01-CNH05-1030 | C-56-HC01-CNH05-1030: FS | 2025-02-11 07:00 | 2025-02-12 17:00
C-56-HC01-CNH05-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 | Driving & Receiving Pit Excavation | C-56-HC01-CNH05-1000 | C-56-HC01-CNH05-1000: FS | C-56-HC01-CNH05-1030 | C-56-HC01-CNH05-1030: FF | 2025-02-11 07:00 | 2025-02-18 17:00
C-56-HC01-CNH05-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-HC01-CNH05-1010, C-56-HC01-CNH05-1020 | C-56-HC01-CNH05-1010: FF, C-56-HC01-CNH05-1020: FS | C-56-HC01-CNH05-1040 | C-56-HC01-CNH05-1040: FS | 2025-02-15 07:00 | 2025-02-18 17:00
C-56-HC01-CNH05-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 | Floor Blinding & French Drain in Driving Pit | C-56-HC01-CNH05-1030 | C-56-HC01-CNH05-1030: FS | C-56-HC01-CNH05-1050 | C-56-HC01-CNH05-1050: FS | 2025-02-19 07:00 | 2025-02-21 17:00
C-56-HC01-CNH05-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-HC01-CNH05-1040 | C-56-HC01-CNH05-1040: FS | C-56-HC01-CNH05-1060 | C-56-HC01-CNH05-1060: FS | 2025-02-22 07:00 | 2025-02-25 17:00
C-56-HC01-CNH05-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 | Construction of Exit Wall with Ring | C-56-HC01-CNH05-1050 | C-56-HC01-CNH05-1050: FS | C-56-HC01-CNH05-1200 | C-56-HC01-CNH05-1200: FS | 2025-02-26 07:00 | 2025-02-28 17:00
C-56-HC01-CNH05-1200 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.1.2 | Jacking of MTBM & RC Sleeves | C-56-HC01-CNH05-1060 | C-56-HC01-CNH05-1060: FS | C-56-HC01-CNH05-1210 | C-56-HC01-CNH05-1210: FS | 2025-03-01 07:00 | 2025-03-11 09:00
C-56-HC01-CNH05-1210 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.1.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-56-HC01-CNH05-1200 | C-56-HC01-CNH05-1200: FS | C-56-HC01-CNH05-1070 | C-56-HC01-CNH05-1070: FS | 2025-03-11 09:00 | 2025-03-17 09:00
C-56-HC01-CNH05-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 | Lowering & Welding of Carrier Pipe | C-56-HC01-CNH05-1210 | C-56-HC01-CNH05-1210: FS | C-56-HC01-CNH05-1080, C-56-HC01-PL-ME-5010 | C-56-HC01-CNH05-1080: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-17 09:00 | 2025-03-28 09:00
C-56-HC01-CNH05-1080 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-56-HC01-CNH05-1070 | C-56-HC01-CNH05-1070: SS 1 | C-56-HC01-CNH05-1090 | C-56-HC01-CNH05-1090: FS | 2025-03-19 07:00 | 2025-03-29 13:00
C-56-HC01-CNH05-1090 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-HC01-CNH05-1080 | C-56-HC01-CNH05-1080: FS | C-56-HC01-CNH05-1220 | C-56-HC01-CNH05-1220: FS | 2025-03-29 13:00 | 2025-04-05 13:00
C-56-HC01-CNH05-1220 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.1.2 | Inner Grout b/w Main & RC Pipe | C-56-HC01-CNH05-1090 | C-56-HC01-CNH05-1090: FS | C-56-HC01-CNH05-1800, C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400 | C-56-HC01-CNH05-1800: FS, C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF | 2025-04-05 13:00 | 2025-04-11 13:00
C-56-HC01-CNH05-1800 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.1.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-HC01-CNH05-1220 | C-56-HC01-CNH05-1220: FS | C-56-HC01-PL-CI-6800, C-56-HC01-PL-CI-7000, ML1579-E03, C-56-HC01-PL-ME-7400 | C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS, C-56-HC01-PL-ME-7400: FS | 2025-04-11 13:00 | 2025-04-19 13:00
C-56-HC01-CNM03-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 | Sheet Piling for Driving & Receiving Pit | HE-PL-2910, HE-PL-2970, C-PER-1370 | HE-PL-2910: FS, HE-PL-2970: FS, C-PER-1370: FS | C-56-HC01-CNM03-1020, C-56-HC01-CNM03-1010, C-56-HC01-CNH05-1000 | C-56-HC01-CNM03-1020: FS, C-56-HC01-CNM03-1010: FS, C-56-HC01-CNH05-1000: FS | 2024-12-28 07:00 | 2025-02-01 17:00
C-56-HC01-CNM03-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 | Installation of Dewatering System for Driving & Receiving Pit | C-56-HC01-CNM03-1000 | C-56-HC01-CNM03-1000: FS | C-56-HC01-CNM03-1030 | C-56-HC01-CNM03-1030: FS | 2025-02-03 07:00 | 2025-02-06 17:00
C-56-HC01-CNM03-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 | Driving & Receiving Pit Excavation | C-56-HC01-CNM03-1000 | C-56-HC01-CNM03-1000: FS | C-56-HC01-CNM03-1030 | C-56-HC01-CNM03-1030: FF | 2025-02-03 07:00 | 2025-02-22 17:00
C-56-HC01-CNM03-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-HC01-CNM03-1010, C-56-HC01-CNM03-1020 | C-56-HC01-CNM03-1010: FF, C-56-HC01-CNM03-1020: FS | C-56-HC01-CNM03-1040 | C-56-HC01-CNM03-1040: FS | 2025-02-10 07:00 | 2025-02-22 17:00
C-56-HC01-CNM03-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 | Floor Blinding & French Drain in Driving Pit | C-56-HC01-CNM03-1030 | C-56-HC01-CNM03-1030: FS | C-56-HC01-CNM03-1050 | C-56-HC01-CNM03-1050: FS | 2025-02-24 07:00 | 2025-03-05 09:00
C-56-HC01-CNM03-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-HC01-CNM03-1040 | C-56-HC01-CNM03-1040: FS | C-56-HC01-CNM03-1060 | C-56-HC01-CNM03-1060: SS 7 | 2025-03-05 09:00 | 2025-03-17 09:00
C-56-HC01-CNM03-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 | Construction of Exit Wall with Ring | C-56-HC01-CNM03-1050 | C-56-HC01-CNM03-1050: SS 7 | C-56-HC01-CNM03-1200 | C-56-HC01-CNM03-1200: FS | 2025-03-15 15:00 | 2025-03-28 09:00
C-56-HC01-CNM03-1200 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.4.2 | Jacking of MTBM & RC Sleeves | C-56-HC01-CNM03-1060 | C-56-HC01-CNM03-1060: FS | C-56-HC01-CNM03-1210 | C-56-HC01-CNM03-1210: FS | 2025-03-28 09:00 | 2025-04-30 13:00
C-56-HC01-CNM03-1210 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.4.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-56-HC01-CNM03-1200 | C-56-HC01-CNM03-1200: FS | C-56-HC01-CNM03-1400 | C-56-HC01-CNM03-1400: FS | 2025-04-30 13:00 | 2025-05-05 14:00
C-56-HC01-CNM03-1400 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.4.3 | Lowering & Welding of Carrier Pipe | C-56-HC01-CNM03-1210 | C-56-HC01-CNM03-1210: FS | C-56-HC01-CNM03-1410 | C-56-HC01-CNM03-1410: SS 1 | 2025-05-05 14:00 | 2025-06-10 11:00
C-56-HC01-CNM03-1410 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.4.3 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-56-HC01-CNM03-1400 | C-56-HC01-CNM03-1400: SS 1 | C-56-HC01-CNM03-1600 | C-56-HC01-CNM03-1600: FS | 2025-05-07 08:00 | 2025-06-11 11:00
C-56-HC01-CNM03-1600 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.4.4 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-HC01-CNM03-1410 | C-56-HC01-CNM03-1410: FS | C-56-HC01-CNM03-1220 | C-56-HC01-CNM03-1220: FS | 2025-06-11 11:00 | 2025-06-23 11:00
C-56-HC01-CNM03-1220 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.4.2 | Inner Grout b/w Main & RC Pipe | C-56-HC01-CNM03-1600 | C-56-HC01-CNM03-1600: FS | C-56-HC01-CNM03-1800, C-56-HC01-PL-CA-5220, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400 | C-56-HC01-CNM03-1800: FS, C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF | 2025-06-23 11:00 | 2025-06-30 11:00
C-56-HC01-CNM03-1800 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.4.5 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-HC01-CNM03-1220 | C-56-HC01-CNM03-1220: FS | C-56-HC01-PL-CI-6800, C-56-HC01-PL-CI-7000, ML1579-E03, C-56-HC01-PL-ME-7400 | C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS, C-56-HC01-PL-ME-7400: FS | 2025-06-30 11:00 | 2025-07-16 11:00
C-56-HC01-CNH02-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 | Sheet Piling for Driving & Receiving Pit | HE-PL-2910, HE-PL-2970, C-PER-1360 | HE-PL-2910: FS, HE-PL-2970: FS, C-PER-1360: FS | C-56-HC01-CNH02-1020, C-56-HC01-CNH02-1010 | C-56-HC01-CNH02-1020: FS, C-56-HC01-CNH02-1010: FS | 2024-12-13 07:00 | 2025-01-29 17:00
C-56-HC01-CNH02-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 | Installation of Dewatering System for Driving & Receiving Pit | C-56-HC01-CNH02-1000 | C-56-HC01-CNH02-1000: FS | C-56-HC01-CNH02-1030 | C-56-HC01-CNH02-1030: FS | 2025-01-30 07:00 | 2025-02-03 17:00
C-56-HC01-CNH02-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 | Driving & Receiving Pit Excavation | C-56-HC01-CNH02-1000 | C-56-HC01-CNH02-1000: FS | C-56-HC01-CNH02-1030 | C-56-HC01-CNH02-1030: FF | 2025-01-30 07:00 | 2025-02-14 17:00
C-56-HC01-CNH02-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-HC01-CNH02-1010, C-56-HC01-CNH02-1020 | C-56-HC01-CNH02-1010: FF, C-56-HC01-CNH02-1020: FS | C-56-HC01-CNH02-1040 | C-56-HC01-CNH02-1040: FS | 2025-02-04 07:00 | 2025-02-14 17:00
C-56-HC01-CNH02-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 | Floor Blinding & French Drain in Driving Pit | C-56-HC01-CNH02-1030 | C-56-HC01-CNH02-1030: FS | C-56-HC01-CNH02-1050 | C-56-HC01-CNH02-1050: FS | 2025-02-15 07:00 | 2025-02-21 17:00
C-56-HC01-CNH02-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-HC01-CNH02-1040 | C-56-HC01-CNH02-1040: FS | C-56-HC01-CNH02-1060 | C-56-HC01-CNH02-1060: SS 7 | 2025-02-22 07:00 | 2025-02-28 17:00
C-56-HC01-CNH02-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 | Construction of Exit Wall with Ring | C-56-HC01-CNH02-1050 | C-56-HC01-CNH02-1050: SS 7 | C-56-HC01-CNH02-1200 | C-56-HC01-CNH02-1200: FS | 2025-03-02 07:00 | 2025-03-11 09:00
C-56-HC01-CNH02-1200 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.2.2 | Jacking of MTBM & RC Sleeves | C-56-HC01-CNH02-1060 | C-56-HC01-CNH02-1060: FS | C-56-HC01-CNH02-1210 | C-56-HC01-CNH02-1210: FS | 2025-03-11 09:00 | 2025-04-22 13:00
C-56-HC01-CNH02-1210 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.2.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-56-HC01-CNH02-1200 | C-56-HC01-CNH02-1200: FS | C-56-HC01-CNH02-1070 | C-56-HC01-CNH02-1070: FS | 2025-04-22 13:00 | 2025-04-26 13:00
C-56-HC01-CNH02-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 | Lowering & Welding of Carrier Pipe | C-56-HC01-CNH02-1210 | C-56-HC01-CNH02-1210: FS | C-56-HC01-CNH02-1080, C-56-HC01-PL-ME-5010, C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-ME-7400, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-6800, PRECOM-56-HGHC-1000, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-CNH02-1080: SS 1, C-56-HC01-PL-ME-5010: FF 1, C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-ME-7400: FS, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-6800: FF, PRECOM-56-HGHC-1000: FS, C-56-HC01-PL-CI-700 | 2025-04-26 13:00 | 2025-06-02 11:00
C-56-HC01-CNH02-1080 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 | NDT, Coating & Holiday Inspection Carrier Pipe | C-56-HC01-CNH02-1070 | C-56-HC01-CNH02-1070: SS 1 | C-56-HC01-CNH02-1090 | C-56-HC01-CNH02-1090: FS | 2025-04-28 13:00 | 2025-06-10 11:00
C-56-HC01-CNH02-1090 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-HC01-CNH02-1080 | C-56-HC01-CNH02-1080: FS | C-56-HC01-CNH02-1220 | C-56-HC01-CNH02-1220: FS | 2025-06-10 11:00 | 2025-06-24 11:00
C-56-HC01-CNH02-1220 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.2.2 | Inner Grout b/w Main & RC Pipe | C-56-HC01-CNH02-1090 | C-56-HC01-CNH02-1090: FS | C-56-HC01-CNH02-1800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400 | C-56-HC01-CNH02-1800: FS, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF | 2025-06-24 11:00 | 2025-07-01 11:00
C-56-HC01-CNH02-1800 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.2.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-HC01-CNH02-1220 | C-56-HC01-CNH02-1220: FS | C-56-HC01-PL-CI-7000, ML1579-E03, C-56-HC01-PL-ME-7400 | C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS, C-56-HC01-PL-ME-7400: FS | 2025-07-01 11:00 | 2025-07-17 11:00
C-56-HC01-CNH01-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 | Sheet Piling for Driving & Receiving Pit | HE-PL-2910, HE-PL-2970, C-PER-1350 | HE-PL-2910: FS, HE-PL-2970: FS, C-PER-1350: FS | C-56-HC01-CNH01-1020, C-56-HC01-CNH01-1010, C-56-HC01-PL-ME-5010, C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-ME-7400, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-6800, PRECOM-56-HGHC-1000, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-CNH01-1020: FS, C-56-HC01-CNH01-1010: FS, C-56-HC01-PL-ME-5010: FF, C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-ME-7400: FS, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-6800: FF, PRECOM-56-HGHC-1000: F | 2024-11-08 07:00 | 2024-12-09 17:00
C-56-HC01-CNH01-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 | Installation of Dewatering System for Driving & Receiving Pit | C-56-HC01-CNH01-1000 | C-56-HC01-CNH01-1000: FS | C-56-HC01-CNH01-1030 | C-56-HC01-CNH01-1030: FS | 2024-12-10 07:00 | 2024-12-13 17:00
C-56-HC01-CNH01-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 | Driving & Receiving Pit Excavation | C-56-HC01-CNH01-1000 | C-56-HC01-CNH01-1000: FS | C-56-HC01-CNH01-1030 | C-56-HC01-CNH01-1030: FF | 2024-12-10 07:00 | 2025-01-11 17:00
C-56-HC01-CNH01-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-HC01-CNH01-1010, C-56-HC01-CNH01-1020 | C-56-HC01-CNH01-1010: FF, C-56-HC01-CNH01-1020: FS | C-56-HC01-CNH01-1040 | C-56-HC01-CNH01-1040: FS | 2024-12-17 07:00 | 2025-01-11 17:00
C-56-HC01-CNH01-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 | Floor Blinding & French Drain in Driving Pit | C-56-HC01-CNH01-1030 | C-56-HC01-CNH01-1030: FS | C-56-HC01-CNH01-1050 | C-56-HC01-CNH01-1050: FS | 2025-01-13 07:00 | 2025-01-18 17:00
C-56-HC01-CNH01-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-HC01-CNH01-1040 | C-56-HC01-CNH01-1040: FS | C-56-HC01-CNH01-1060 | C-56-HC01-CNH01-1060: SS 7 | 2025-01-20 07:00 | 2025-01-25 17:00
C-56-HC01-CNH01-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 | Construction of Exit Wall with Ring | C-56-HC01-CNH01-1050 | C-56-HC01-CNH01-1050: SS 7 | C-56-HC01-CNH01-1200 | C-56-HC01-CNH01-1200: FS | 2025-01-28 07:00 | 2025-02-03 17:00
C-56-HC01-CNH01-1200 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.3.2 | Jacking of MTBM & RC Sleeves | C-56-HC01-CNH01-1060 | C-56-HC01-CNH01-1060: FS | C-56-HC01-CNH01-1210 | C-56-HC01-CNH01-1210: FS | 2025-02-04 07:00 | 2025-03-01 17:00
C-56-HC01-CNH01-1210 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.3.2 | Filling of Grout between Earth Overcut & RC Sleeve | C-56-HC01-CNH01-1200 | C-56-HC01-CNH01-1200: FS | C-56-HC01-CNH01-1070 | C-56-HC01-CNH01-1070: FS | 2025-03-02 07:00 | 2025-03-08 11:00
C-56-HC01-CNH01-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 | Lowering & Welding of Carrier Pipe | C-56-HC01-CNH01-1210 | C-56-HC01-CNH01-1210: FS | C-56-HC01-CNH01-1080, C-56-HC01-PL-ME-5010 | C-56-HC01-CNH01-1080: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-08 11:00 | 2025-03-29 13:00
C-56-HC01-CNH01-1080 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 | NDT, Coating & Holiday Inspection of Carrier Pipe | C-56-HC01-CNH01-1070 | C-56-HC01-CNH01-1070: SS 1 | C-56-HC01-CNH01-1090 | C-56-HC01-CNH01-1090: FS | 2025-03-09 11:00 | 2025-04-03 13:00
C-56-HC01-CNH01-1090 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-HC01-CNH01-1080 | C-56-HC01-CNH01-1080: FS | C-56-HC01-CNH01-1220 | C-56-HC01-CNH01-1220: FS | 2025-04-03 13:00 | 2025-04-17 13:00
C-56-HC01-CNH01-1220 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.3.2 | Inner Grout b/w Main & RC Pipe | C-56-HC01-CNH01-1090 | C-56-HC01-CNH01-1090: FS | C-56-HC01-CNH01-1800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400 | C-56-HC01-CNH01-1800: FS, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF | 2025-04-17 13:00 | 2025-04-23 13:00
C-56-HC01-CNH01-1800 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.8.3.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-HC01-CNH01-1220 | C-56-HC01-CNH01-1220: FS | C-56-HC01-PL-CI-7000, ML1579-E03, C-56-HC01-PL-ME-7400 | C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS, C-56-HC01-PL-ME-7400: FS | 2025-04-23 13:00 | 2025-05-10 11:00
C-56-01HG-CMA01-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-01HG-PL-ME-2800 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-01HG-PL-ME-2800: FS | C-56-01HG-CMA01-1010, C-56-01HG-CMA02-1000, C-56-01HG-CMA06-1000, C-56-01HG-CMA07-1000, C-56-01HG-CMA06-1000 | C-56-01HG-CMA01-1010: FF, C-56-01HG-CMA02-1000: SS 3, C-56-01HG-CMA06-1000: SS 8, C-56-01HG-CMA07-1000: FS, C-56-01HG-CMA06-1000: FF | 2025-03-01 07:00 | 2025-03-18 13:00
C-56-01HG-CMA01-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 | Bedding | C-56-01HG-CMA01-1000 | C-56-01HG-CMA01-1000: FF | C-56-01HG-CMA01-1020 | C-56-01HG-CMA01-1020: FS | 2025-03-17 09:00 | 2025-03-18 13:00
C-56-01HG-CMA01-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 | Lowering | C-56-01HG-CMA01-1010 | C-56-01HG-CMA01-1010: FS | C-56-01HG-CMA01-1030 | C-56-01HG-CMA01-1030: SS | 2025-03-19 07:00 | 2025-03-20 11:00
C-56-01HG-CMA01-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 | Section Tie-in Welding | C-56-01HG-CMA01-1020 | C-56-01HG-CMA01-1020: SS | C-56-01HG-CMA01-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA01-1040: SS 1, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-03-19 07:00 | 2025-03-22 09:00
C-56-01HG-CMA01-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 | NDT (Tie-in Joint) | C-56-01HG-CMA01-1030 | C-56-01HG-CMA01-1030: SS 1 | C-56-01HG-CMA01-1050 | C-56-01HG-CMA01-1050: SS 1 | 2025-03-20 11:00 | 2025-03-23 09:00
C-56-01HG-CMA01-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA01-1040 | C-56-01HG-CMA01-1040: SS 1 | C-56-01HG-CMA01-1060 | C-56-01HG-CMA01-1060: FS | 2025-03-22 09:00 | 2025-03-24 13:00
C-56-01HG-CMA01-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 | Holiday Testing | C-56-01HG-CMA01-1050 | C-56-01HG-CMA01-1050: FS | C-56-01HG-CMA01-1070 | C-56-01HG-CMA01-1070: FS | 2025-03-25 07:00 | 2025-03-26 11:00
C-56-01HG-CMA01-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 | Padding | C-56-01HG-CMA01-1060 | C-56-01HG-CMA01-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: SS, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: SS, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-03-26 11:00 | 2025-03-28 09:00
C-56-01HG-CMA02-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 | Trench Excavation | C-56-01HG-CMA01-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA01-1000: SS 3, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA02-1010, C-56-01HG-CMA08-1000, C-56-01HG-CMA03-1000 | C-56-01HG-CMA02-1010: FF, C-56-01HG-CMA08-1000: FS, C-56-01HG-CMA03-1000: SS | 2025-03-05 09:00 | 2025-03-17 09:00
C-56-01HG-CMA02-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 | Bedding | C-56-01HG-CMA02-1000 | C-56-01HG-CMA02-1000: FF | C-56-01HG-CMA02-1020 | C-56-01HG-CMA02-1020: FS | 2025-03-15 15:00 | 2025-03-17 09:00
C-56-01HG-CMA02-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 | Lowering | C-56-01HG-CMA02-1010 | C-56-01HG-CMA02-1010: FS | C-56-01HG-CMA02-1030 | C-56-01HG-CMA02-1030: SS | 2025-03-17 09:00 | 2025-03-18 13:00
C-56-01HG-CMA02-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 | Section Tie-in Welding | C-56-01HG-CMA02-1020 | C-56-01HG-CMA02-1020: SS | C-56-01HG-CMA02-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA02-1040: SS 1, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-03-17 09:00 | 2025-03-20 11:00
C-56-01HG-CMA02-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 | NDT (Tie-in Joint) | C-56-01HG-CMA02-1030 | C-56-01HG-CMA02-1030: SS 1 | C-56-01HG-CMA02-1050 | C-56-01HG-CMA02-1050: SS 1 | 2025-03-19 07:00 | 2025-03-22 09:00
C-56-01HG-CMA02-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA02-1040 | C-56-01HG-CMA02-1040: SS 1 | C-56-01HG-CMA02-1060 | C-56-01HG-CMA02-1060: FS | 2025-03-20 11:00 | 2025-03-23 09:00
C-56-01HG-CMA02-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 | Holiday Testing | C-56-01HG-CMA02-1050 | C-56-01HG-CMA02-1050: FS | C-56-01HG-CMA02-1070 | C-56-01HG-CMA02-1070: FS | 2025-03-23 09:00 | 2025-03-24 13:00
C-56-01HG-CMA02-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 | Padding | C-56-01HG-CMA02-1060 | C-56-01HG-CMA02-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-03-25 07:00 | 2025-03-26 11:00
C-56-01HG-CMA03-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-01HG-CMA02-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-01HG-CMA02-1000: SS | C-56-01HG-CMA03-1010, C-56-01HG-CMA09-1000, C-56-01HG-CMA04-1000 | C-56-01HG-CMA03-1010: FF, C-56-01HG-CMA09-1000: SS, C-56-01HG-CMA04-1000: FS | 2025-03-05 09:00 | 2025-03-17 09:00
C-56-01HG-CMA03-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 | Bedding | C-56-01HG-CMA03-1000 | C-56-01HG-CMA03-1000: FF | C-56-01HG-CMA03-1020 | C-56-01HG-CMA03-1020: FS | 2025-03-15 15:00 | 2025-03-17 09:00
C-56-01HG-CMA03-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 | Lowering | C-56-01HG-CMA03-1010 | C-56-01HG-CMA03-1010: FS | C-56-01HG-CMA03-1030 | C-56-01HG-CMA03-1030: SS | 2025-03-17 09:00 | 2025-03-18 13:00
C-56-01HG-CMA03-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 | Section Tie-in Welding | C-56-01HG-CMA03-1020 | C-56-01HG-CMA03-1020: SS | C-56-01HG-CMA03-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA03-1040: SS 1, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-03-17 09:00 | 2025-03-20 11:00
C-56-01HG-CMA03-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 | NDT (Tie-in Joint) | C-56-01HG-CMA03-1030 | C-56-01HG-CMA03-1030: SS 1 | C-56-01HG-CMA03-1050 | C-56-01HG-CMA03-1050: SS 1 | 2025-03-19 07:00 | 2025-03-22 09:00
C-56-01HG-CMA03-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA03-1040 | C-56-01HG-CMA03-1040: SS 1 | C-56-01HG-CMA03-1060 | C-56-01HG-CMA03-1060: FS | 2025-03-20 11:00 | 2025-03-23 09:00
C-56-01HG-CMA03-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 | Holiday Testing | C-56-01HG-CMA03-1050 | C-56-01HG-CMA03-1050: FS | C-56-01HG-CMA03-1070 | C-56-01HG-CMA03-1070: FS | 2025-03-23 09:00 | 2025-03-24 13:00
C-56-01HG-CMA03-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 | Padding | C-56-01HG-CMA03-1060 | C-56-01HG-CMA03-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-03-25 07:00 | 2025-03-26 11:00
C-56-01HG-CMA04-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-01HG-CMA03-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-01HG-CMA03-1000: FS | C-56-01HG-CMA04-1010, C-56-01HG-CMA10-1000, C-56-01HG-CMA05-1000 | C-56-01HG-CMA04-1010: FF, C-56-01HG-CMA10-1000: FS, C-56-01HG-CMA05-1000: FS | 2025-03-17 09:00 | 2025-03-26 11:00
C-56-01HG-CMA04-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 | Bedding | C-56-01HG-CMA04-1000 | C-56-01HG-CMA04-1000: FF | C-56-01HG-CMA04-1020 | C-56-01HG-CMA04-1020: FS | 2025-03-25 07:00 | 2025-03-26 11:00
C-56-01HG-CMA04-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 | Lowering | C-56-01HG-CMA04-1010 | C-56-01HG-CMA04-1010: FS | C-56-01HG-CMA04-1030 | C-56-01HG-CMA04-1030: SS | 2025-03-26 11:00 | 2025-03-28 09:00
C-56-01HG-CMA04-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 | Section Tie-in Welding | C-56-01HG-CMA04-1020 | C-56-01HG-CMA04-1020: SS | C-56-01HG-CMA04-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA04-1040: SS 1, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-03-26 11:00 | 2025-03-29 13:00
C-56-01HG-CMA04-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 | NDT (Tie-in Joint) | C-56-01HG-CMA04-1030 | C-56-01HG-CMA04-1030: SS 1 | C-56-01HG-CMA04-1050 | C-56-01HG-CMA04-1050: SS 1 | 2025-03-28 09:00 | 2025-04-03 13:00
C-56-01HG-CMA04-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA04-1040 | C-56-01HG-CMA04-1040: SS 1 | C-56-01HG-CMA04-1060 | C-56-01HG-CMA04-1060: FS | 2025-03-29 13:00 | 2025-04-04 13:00
C-56-01HG-CMA04-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 | Holiday Testing | C-56-01HG-CMA04-1050 | C-56-01HG-CMA04-1050: FS | C-56-01HG-CMA04-1070 | C-56-01HG-CMA04-1070: FS | 2025-04-04 13:00 | 2025-04-05 13:00
C-56-01HG-CMA04-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 | Padding | C-56-01HG-CMA04-1060 | C-56-01HG-CMA04-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-05 13:00 | 2025-04-07 13:00
C-56-01HG-CMA05-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-01HG-CMA04-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-01HG-CMA04-1000: FS | C-56-01HG-CMA05-1010, C-56-01HG-CMA11-1000 | C-56-01HG-CMA05-1010: FF, C-56-01HG-CMA11-1000: FS | 2025-03-26 11:00 | 2025-04-08 13:00
C-56-01HG-CMA05-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 | Bedding | C-56-01HG-CMA05-1000 | C-56-01HG-CMA05-1000: FF | C-56-01HG-CMA05-1020 | C-56-01HG-CMA05-1020: FS | 2025-04-07 13:00 | 2025-04-08 13:00
C-56-01HG-CMA05-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 | Lowering | C-56-01HG-CMA05-1010 | C-56-01HG-CMA05-1010: FS | C-56-01HG-CMA05-1030 | C-56-01HG-CMA05-1030: SS | 2025-04-08 13:00 | 2025-04-09 13:00
C-56-01HG-CMA05-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 | Section Tie-in Welding | C-56-01HG-CMA05-1020 | C-56-01HG-CMA05-1020: SS | C-56-01HG-CMA05-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA05-1040: SS 1, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-08 13:00 | 2025-04-10 13:00
C-56-01HG-CMA05-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 | NDT (Tie-in Joint) | C-56-01HG-CMA05-1030 | C-56-01HG-CMA05-1030: SS 1 | C-56-01HG-CMA05-1050 | C-56-01HG-CMA05-1050: SS 1 | 2025-04-09 13:00 | 2025-04-11 13:00
C-56-01HG-CMA05-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA05-1040 | C-56-01HG-CMA05-1040: SS 1 | C-56-01HG-CMA05-1060 | C-56-01HG-CMA05-1060: FS | 2025-04-10 13:00 | 2025-04-12 13:00
C-56-01HG-CMA05-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 | Holiday Testing | C-56-01HG-CMA05-1050 | C-56-01HG-CMA05-1050: FS | C-56-01HG-CMA05-1070 | C-56-01HG-CMA05-1070: FS | 2025-04-12 13:00 | 2025-04-14 13:00
C-56-01HG-CMA05-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 | Padding | C-56-01HG-CMA05-1060 | C-56-01HG-CMA05-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-14 13:00 | 2025-04-15 13:00
C-56-01HG-CMA06-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 | Trench Excavation | C-56-01HG-CMA01-1000, C-56-01HG-CMA01-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA01-1000: SS 8, C-56-01HG-CMA01-1000: FF, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA06-1010, C-56-01HG-CMA12-1000 | C-56-01HG-CMA06-1010: FF, C-56-01HG-CMA12-1000: FS | 2025-03-13 07:00 | 2025-04-03 13:00
C-56-01HG-CMA06-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 | Bedding | C-56-01HG-CMA06-1000 | C-56-01HG-CMA06-1000: FF | C-56-01HG-CMA06-1020 | C-56-01HG-CMA06-1020: FS | 2025-03-29 13:00 | 2025-04-03 13:00
C-56-01HG-CMA06-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 | Lowering | C-56-01HG-CMA06-1010 | C-56-01HG-CMA06-1010: FS | C-56-01HG-CMA06-1030 | C-56-01HG-CMA06-1030: SS | 2025-04-03 13:00 | 2025-04-04 13:00
C-56-01HG-CMA06-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 | Section Tie-in Welding | C-56-01HG-CMA06-1020 | C-56-01HG-CMA06-1020: SS | C-56-01HG-CMA06-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA06-1040: SS 1, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-03 13:00 | 2025-04-05 13:00
C-56-01HG-CMA06-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 | NDT (Tie-in Joint) | C-56-01HG-CMA06-1030 | C-56-01HG-CMA06-1030: SS 1 | C-56-01HG-CMA06-1050 | C-56-01HG-CMA06-1050: SS 1 | 2025-04-04 13:00 | 2025-04-07 13:00
C-56-01HG-CMA06-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA06-1040 | C-56-01HG-CMA06-1040: SS 1 | C-56-01HG-CMA06-1060 | C-56-01HG-CMA06-1060: FS | 2025-04-05 13:00 | 2025-04-08 13:00
C-56-01HG-CMA06-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 | Holiday Testing | C-56-01HG-CMA06-1050 | C-56-01HG-CMA06-1050: FS | C-56-01HG-CMA06-1070 | C-56-01HG-CMA06-1070: FS | 2025-04-08 13:00 | 2025-04-09 13:00
C-56-01HG-CMA06-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 | Padding | C-56-01HG-CMA06-1060 | C-56-01HG-CMA06-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-09 13:00 | 2025-04-10 13:00
C-56-01HG-CMA07-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 | Trench Excavation | C-56-01HG-CMA01-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA01-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA07-1010, C-56-01HG-CMA13-1000 | C-56-01HG-CMA07-1010: FF, C-56-01HG-CMA13-1000: FS | 2025-03-19 07:00 | 2025-04-08 13:00
C-56-01HG-CMA07-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 | Bedding | C-56-01HG-CMA07-1000 | C-56-01HG-CMA07-1000: FF | C-56-01HG-CMA07-1020 | C-56-01HG-CMA07-1020: FS | 2025-04-07 13:00 | 2025-04-08 13:00
C-56-01HG-CMA07-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 | Lowering | C-56-01HG-CMA07-1010 | C-56-01HG-CMA07-1010: FS | C-56-01HG-CMA07-1030 | C-56-01HG-CMA07-1030: SS | 2025-04-08 13:00 | 2025-04-09 13:00
C-56-01HG-CMA07-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 | Section Tie-in Welding | C-56-01HG-CMA07-1020 | C-56-01HG-CMA07-1020: SS | C-56-01HG-CMA07-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA07-1040: SS 1, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-08 13:00 | 2025-04-10 13:00
C-56-01HG-CMA07-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 | NDT (Tie-in Joint) | C-56-01HG-CMA07-1030 | C-56-01HG-CMA07-1030: SS 1 | C-56-01HG-CMA07-1050 | C-56-01HG-CMA07-1050: SS 1 | 2025-04-09 13:00 | 2025-04-11 13:00
C-56-01HG-CMA07-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA07-1040 | C-56-01HG-CMA07-1040: SS 1 | C-56-01HG-CMA07-1060 | C-56-01HG-CMA07-1060: FS | 2025-04-10 13:00 | 2025-04-12 13:00
C-56-01HG-CMA07-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 | Holiday Testing | C-56-01HG-CMA07-1050 | C-56-01HG-CMA07-1050: FS | C-56-01HG-CMA07-1070 | C-56-01HG-CMA07-1070: FS | 2025-04-12 13:00 | 2025-04-14 13:00
C-56-01HG-CMA07-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 | Padding | C-56-01HG-CMA07-1060 | C-56-01HG-CMA07-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-14 13:00 | 2025-04-15 13:00
C-56-01HG-CMA08-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 | Trench Excavation | C-56-01HG-CMA02-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA02-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA08-1010, C-56-01HG-CMA14-1000 | C-56-01HG-CMA08-1010: FF, C-56-01HG-CMA14-1000: FS | 2025-03-17 09:00 | 2025-04-07 13:00
C-56-01HG-CMA08-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 | Bedding | C-56-01HG-CMA08-1000 | C-56-01HG-CMA08-1000: FF | C-56-01HG-CMA08-1020 | C-56-01HG-CMA08-1020: FS | 2025-04-05 13:00 | 2025-04-07 13:00
C-56-01HG-CMA08-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 | Lowering | C-56-01HG-CMA08-1010 | C-56-01HG-CMA08-1010: FS | C-56-01HG-CMA08-1030 | C-56-01HG-CMA08-1030: SS | 2025-04-07 13:00 | 2025-04-08 13:00
C-56-01HG-CMA08-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 | Section Tie-in Welding | C-56-01HG-CMA08-1020 | C-56-01HG-CMA08-1020: SS | C-56-01HG-CMA08-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA08-1040: SS 1, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-07 13:00 | 2025-04-09 13:00
C-56-01HG-CMA08-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 | NDT (Tie-in Joint) | C-56-01HG-CMA08-1030 | C-56-01HG-CMA08-1030: SS 1 | C-56-01HG-CMA08-1050 | C-56-01HG-CMA08-1050: SS 1 | 2025-04-08 13:00 | 2025-04-10 13:00
C-56-01HG-CMA08-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA08-1040 | C-56-01HG-CMA08-1040: SS 1 | C-56-01HG-CMA08-1060 | C-56-01HG-CMA08-1060: FS | 2025-04-09 13:00 | 2025-04-11 13:00
C-56-01HG-CMA08-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 | Holiday Testing | C-56-01HG-CMA08-1050 | C-56-01HG-CMA08-1050: FS | C-56-01HG-CMA08-1070 | C-56-01HG-CMA08-1070: FS | 2025-04-11 13:00 | 2025-04-12 13:00
C-56-01HG-CMA08-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 | Padding | C-56-01HG-CMA08-1060 | C-56-01HG-CMA08-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-12 13:00 | 2025-04-14 13:00
C-56-01HG-CMA09-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 | Trench Excavation | C-56-01HG-CMA03-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA03-1000: SS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA09-1010, C-56-01HG-CMA15-1000 | C-56-01HG-CMA09-1010: FF, C-56-01HG-CMA15-1000: SS 6 | 2025-03-05 09:00 | 2025-03-23 09:00
C-56-01HG-CMA09-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 | Bedding | C-56-01HG-CMA09-1000 | C-56-01HG-CMA09-1000: FF | C-56-01HG-CMA09-1020 | C-56-01HG-CMA09-1020: FS | 2025-03-22 09:00 | 2025-03-23 09:00
C-56-01HG-CMA09-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 | Lowering | C-56-01HG-CMA09-1010 | C-56-01HG-CMA09-1010: FS | C-56-01HG-CMA09-1030 | C-56-01HG-CMA09-1030: SS | 2025-03-23 09:00 | 2025-03-24 13:00
C-56-01HG-CMA09-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 | Section Tie-in Welding | C-56-01HG-CMA09-1020 | C-56-01HG-CMA09-1020: SS | C-56-01HG-CMA09-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA09-1040: SS 1, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-03-23 09:00 | 2025-03-26 11:00
C-56-01HG-CMA09-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 | NDT (Tie-in Joint) | C-56-01HG-CMA09-1030 | C-56-01HG-CMA09-1030: SS 1 | C-56-01HG-CMA09-1050 | C-56-01HG-CMA09-1050: SS 1 | 2025-03-25 07:00 | 2025-03-28 09:00
C-56-01HG-CMA09-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA09-1040 | C-56-01HG-CMA09-1040: SS 1 | C-56-01HG-CMA09-1060 | C-56-01HG-CMA09-1060: FS | 2025-03-26 11:00 | 2025-03-29 13:00
C-56-01HG-CMA09-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 | Holiday Testing | C-56-01HG-CMA09-1050 | C-56-01HG-CMA09-1050: FS | C-56-01HG-CMA09-1070 | C-56-01HG-CMA09-1070: FS | 2025-03-29 13:00 | 2025-04-03 13:00
C-56-01HG-CMA09-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 | Padding | C-56-01HG-CMA09-1060 | C-56-01HG-CMA09-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-03 13:00 | 2025-04-04 13:00
C-56-01HG-CMA10-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 | Trench Excavation | C-56-01HG-CMA04-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA04-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA10-1010, C-56-01HG-CMA16-1000 | C-56-01HG-CMA10-1010: FF, C-56-01HG-CMA16-1000: FS | 2025-03-26 11:00 | 2025-04-14 13:00
C-56-01HG-CMA10-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 | Bedding | C-56-01HG-CMA10-1000 | C-56-01HG-CMA10-1000: FF | C-56-01HG-CMA10-1020 | C-56-01HG-CMA10-1020: FS | 2025-04-12 13:00 | 2025-04-14 13:00
C-56-01HG-CMA10-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 | Lowering | C-56-01HG-CMA10-1010 | C-56-01HG-CMA10-1010: FS | C-56-01HG-CMA10-1030 | C-56-01HG-CMA10-1030: SS | 2025-04-14 13:00 | 2025-04-15 13:00
C-56-01HG-CMA10-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 | Section Tie-in Welding | C-56-01HG-CMA10-1020 | C-56-01HG-CMA10-1020: SS | C-56-01HG-CMA10-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA10-1040: SS 1, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-14 13:00 | 2025-04-16 13:00
C-56-01HG-CMA10-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 | NDT (Tie-in Joint) | C-56-01HG-CMA10-1030 | C-56-01HG-CMA10-1030: SS 1 | C-56-01HG-CMA10-1050 | C-56-01HG-CMA10-1050: SS 1 | 2025-04-15 13:00 | 2025-04-17 13:00
C-56-01HG-CMA10-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA10-1040 | C-56-01HG-CMA10-1040: SS 1 | C-56-01HG-CMA10-1060 | C-56-01HG-CMA10-1060: FS | 2025-04-16 13:00 | 2025-04-18 13:00
C-56-01HG-CMA10-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 | Holiday Testing | C-56-01HG-CMA10-1050 | C-56-01HG-CMA10-1050: FS | C-56-01HG-CMA10-1070 | C-56-01HG-CMA10-1070: FS | 2025-04-18 13:00 | 2025-04-19 13:00
C-56-01HG-CMA10-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 | Padding | C-56-01HG-CMA10-1060 | C-56-01HG-CMA10-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-19 13:00 | 2025-04-21 13:00
C-56-01HG-CMA11-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 | Trench Excavation | C-56-01HG-CMA05-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA05-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA11-1010, C-56-01HG-CMA17-1000 | C-56-01HG-CMA11-1010: FF, C-56-01HG-CMA17-1000: FS | 2025-04-08 13:00 | 2025-04-17 13:00
C-56-01HG-CMA11-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 | Bedding | C-56-01HG-CMA11-1000 | C-56-01HG-CMA11-1000: FF | C-56-01HG-CMA11-1020 | C-56-01HG-CMA11-1020: FS | 2025-04-16 13:00 | 2025-04-17 13:00
C-56-01HG-CMA11-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 | Lowering | C-56-01HG-CMA11-1010 | C-56-01HG-CMA11-1010: FS | C-56-01HG-CMA11-1030 | C-56-01HG-CMA11-1030: SS | 2025-04-17 13:00 | 2025-04-18 13:00
C-56-01HG-CMA11-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 | Section Tie-in Welding | C-56-01HG-CMA11-1020 | C-56-01HG-CMA11-1020: SS | C-56-01HG-CMA11-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA11-1040: SS 1, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-17 13:00 | 2025-04-19 13:00
C-56-01HG-CMA11-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 | NDT (Tie-in Joint) | C-56-01HG-CMA11-1030 | C-56-01HG-CMA11-1030: SS 1 | C-56-01HG-CMA11-1050 | C-56-01HG-CMA11-1050: SS 1 | 2025-04-18 13:00 | 2025-04-21 13:00
C-56-01HG-CMA11-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA11-1040 | C-56-01HG-CMA11-1040: SS 1 | C-56-01HG-CMA11-1060 | C-56-01HG-CMA11-1060: FS | 2025-04-19 13:00 | 2025-04-22 13:00
C-56-01HG-CMA11-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 | Holiday Testing | C-56-01HG-CMA11-1050 | C-56-01HG-CMA11-1050: FS | C-56-01HG-CMA11-1070 | C-56-01HG-CMA11-1070: FS | 2025-04-22 13:00 | 2025-04-23 13:00
C-56-01HG-CMA11-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 | Padding | C-56-01HG-CMA11-1060 | C-56-01HG-CMA11-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-23 13:00 | 2025-04-24 13:00
C-56-01HG-CMA12-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 | Trench Excavation | C-56-01HG-CMA06-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA06-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA12-1010, C-56-01HG-CMA18-1000 | C-56-01HG-CMA12-1010: FF, C-56-01HG-CMA18-1000: FS | 2025-04-03 13:00 | 2025-04-10 13:00
C-56-01HG-CMA12-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 | Bedding | C-56-01HG-CMA12-1000 | C-56-01HG-CMA12-1000: FF | C-56-01HG-CMA12-1020 | C-56-01HG-CMA12-1020: FS | 2025-04-09 13:00 | 2025-04-10 13:00
C-56-01HG-CMA12-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 | Lowering | C-56-01HG-CMA12-1010 | C-56-01HG-CMA12-1010: FS | C-56-01HG-CMA12-1030 | C-56-01HG-CMA12-1030: SS | 2025-04-10 13:00 | 2025-04-11 13:00
C-56-01HG-CMA12-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 | Section Tie-in Welding | C-56-01HG-CMA12-1020 | C-56-01HG-CMA12-1020: SS | C-56-01HG-CMA12-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA12-1040: SS 1, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-10 13:00 | 2025-04-12 13:00
C-56-01HG-CMA12-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 | NDT (Tie-in Joint) | C-56-01HG-CMA12-1030 | C-56-01HG-CMA12-1030: SS 1 | C-56-01HG-CMA12-1050 | C-56-01HG-CMA12-1050: SS 1 | 2025-04-11 13:00 | 2025-04-14 13:00
C-56-01HG-CMA12-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA12-1040 | C-56-01HG-CMA12-1040: SS 1 | C-56-01HG-CMA12-1060 | C-56-01HG-CMA12-1060: FS | 2025-04-12 13:00 | 2025-04-15 13:00
C-56-01HG-CMA12-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 | Holiday Testing | C-56-01HG-CMA12-1050 | C-56-01HG-CMA12-1050: FS | C-56-01HG-CMA12-1070 | C-56-01HG-CMA12-1070: FS | 2025-04-15 13:00 | 2025-04-16 13:00
C-56-01HG-CMA12-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 | Padding | C-56-01HG-CMA12-1060 | C-56-01HG-CMA12-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-16 13:00 | 2025-04-17 13:00
C-56-01HG-CMA13-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 | Trench Excavation | C-56-01HG-CMA07-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA07-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA13-1010, C-56-01HG-CMA19-1000 | C-56-01HG-CMA13-1010: FF, C-56-01HG-CMA19-1000: FS | 2025-04-08 13:00 | 2025-04-17 13:00
C-56-01HG-CMA13-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 | Bedding | C-56-01HG-CMA13-1000 | C-56-01HG-CMA13-1000: FF | C-56-01HG-CMA13-1020 | C-56-01HG-CMA13-1020: FS | 2025-04-16 13:00 | 2025-04-17 13:00
C-56-01HG-CMA13-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 | Lowering | C-56-01HG-CMA13-1010 | C-56-01HG-CMA13-1010: FS | C-56-01HG-CMA13-1030 | C-56-01HG-CMA13-1030: SS | 2025-04-17 13:00 | 2025-04-18 13:00
C-56-01HG-CMA13-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 | Section Tie-in Welding | C-56-01HG-CMA13-1020 | C-56-01HG-CMA13-1020: SS | C-56-01HG-CMA13-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA13-1040: SS 1, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-17 13:00 | 2025-04-19 13:00
C-56-01HG-CMA13-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 | NDT (Tie-in Joint) | C-56-01HG-CMA13-1030 | C-56-01HG-CMA13-1030: SS 1 | C-56-01HG-CMA13-1050 | C-56-01HG-CMA13-1050: SS 1 | 2025-04-18 13:00 | 2025-04-21 13:00
C-56-01HG-CMA13-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA13-1040 | C-56-01HG-CMA13-1040: SS 1 | C-56-01HG-CMA13-1060 | C-56-01HG-CMA13-1060: FS | 2025-04-19 13:00 | 2025-04-22 13:00
C-56-01HG-CMA13-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 | Holiday Testing | C-56-01HG-CMA13-1050 | C-56-01HG-CMA13-1050: FS | C-56-01HG-CMA13-1070 | C-56-01HG-CMA13-1070: FS | 2025-04-22 13:00 | 2025-04-23 13:00
C-56-01HG-CMA13-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 | Padding | C-56-01HG-CMA13-1060 | C-56-01HG-CMA13-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-23 13:00 | 2025-04-24 13:00
C-56-01HG-CMA14-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 | Trench Excavation | C-56-01HG-CMA08-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA08-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA14-1010, C-56-01HG-CMA20-1000 | C-56-01HG-CMA14-1010: FF, C-56-01HG-CMA20-1000: FS | 2025-04-07 13:00 | 2025-04-16 13:00
C-56-01HG-CMA14-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 | Bedding | C-56-01HG-CMA14-1000 | C-56-01HG-CMA14-1000: FF | C-56-01HG-CMA14-1020 | C-56-01HG-CMA14-1020: FS | 2025-04-15 13:00 | 2025-04-16 13:00
C-56-01HG-CMA14-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 | Lowering | C-56-01HG-CMA14-1010 | C-56-01HG-CMA14-1010: FS | C-56-01HG-CMA14-1030 | C-56-01HG-CMA14-1030: SS | 2025-04-16 13:00 | 2025-04-17 13:00
C-56-01HG-CMA14-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 | Section Tie-in Welding | C-56-01HG-CMA14-1020 | C-56-01HG-CMA14-1020: SS | C-56-01HG-CMA14-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA14-1040: SS 1, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-16 13:00 | 2025-04-18 13:00
C-56-01HG-CMA14-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 | NDT (Tie-in Joint) | C-56-01HG-CMA14-1030 | C-56-01HG-CMA14-1030: SS 1 | C-56-01HG-CMA14-1050 | C-56-01HG-CMA14-1050: SS 1 | 2025-04-17 13:00 | 2025-04-19 13:00
C-56-01HG-CMA14-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA14-1040 | C-56-01HG-CMA14-1040: SS 1 | C-56-01HG-CMA14-1060 | C-56-01HG-CMA14-1060: FS | 2025-04-18 13:00 | 2025-04-21 13:00
C-56-01HG-CMA14-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 | Holiday Testing | C-56-01HG-CMA14-1050 | C-56-01HG-CMA14-1050: FS | C-56-01HG-CMA14-1070 | C-56-01HG-CMA14-1070: FS | 2025-04-21 13:00 | 2025-04-22 13:00
C-56-01HG-CMA14-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 | Padding | C-56-01HG-CMA14-1060 | C-56-01HG-CMA14-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-22 13:00 | 2025-04-23 13:00
C-56-01HG-CMA15-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 | Trench Excavation | C-56-01HG-CMA09-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA09-1000: SS 6, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA15-1010, C-56-01HG-CMA21-1000 | C-56-01HG-CMA15-1010: FF, C-56-01HG-CMA21-1000: FS | 2025-03-14 11:00 | 2025-03-26 11:00
C-56-01HG-CMA15-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 | Bedding | C-56-01HG-CMA15-1000 | C-56-01HG-CMA15-1000: FF | C-56-01HG-CMA15-1020 | C-56-01HG-CMA15-1020: FS | 2025-03-25 07:00 | 2025-03-26 11:00
C-56-01HG-CMA15-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 | Lowering | C-56-01HG-CMA15-1010 | C-56-01HG-CMA15-1010: FS | C-56-01HG-CMA15-1030 | C-56-01HG-CMA15-1030: SS | 2025-03-26 11:00 | 2025-03-28 09:00
C-56-01HG-CMA15-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 | Section Tie-in Welding | C-56-01HG-CMA15-1020 | C-56-01HG-CMA15-1020: SS | C-56-01HG-CMA15-1040, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA15-1040: SS 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-03-26 11:00 | 2025-03-29 13:00
C-56-01HG-CMA15-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 | NDT (Tie-in Joint) | C-56-01HG-CMA15-1030 | C-56-01HG-CMA15-1030: SS 1 | C-56-01HG-CMA15-1050 | C-56-01HG-CMA15-1050: SS 1 | 2025-03-28 09:00 | 2025-04-03 13:00
C-56-01HG-CMA15-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA15-1040 | C-56-01HG-CMA15-1040: SS 1 | C-56-01HG-CMA15-1060 | C-56-01HG-CMA15-1060: FS | 2025-03-29 13:00 | 2025-04-04 13:00
C-56-01HG-CMA15-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 | Holiday Testing | C-56-01HG-CMA15-1050 | C-56-01HG-CMA15-1050: FS | C-56-01HG-CMA15-1070 | C-56-01HG-CMA15-1070: FS | 2025-04-04 13:00 | 2025-04-05 13:00
C-56-01HG-CMA15-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 | Padding | C-56-01HG-CMA15-1060 | C-56-01HG-CMA15-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-05 13:00 | 2025-04-07 13:00
C-56-01HG-CMA23-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 | Trench Excavation | C-56-01HG-CMA17-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA17-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA23-1010 | C-56-01HG-CMA23-1010: FF | 2025-05-01 13:00 | 2025-05-12 11:00
C-56-01HG-CMA23-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 | Bedding | C-56-01HG-CMA23-1000 | C-56-01HG-CMA23-1000: FF | C-56-01HG-CMA23-1020 | C-56-01HG-CMA23-1020: FS | 2025-05-10 11:00 | 2025-05-12 11:00
C-56-01HG-CMA23-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 | Lowering | C-56-01HG-CMA23-1010 | C-56-01HG-CMA23-1010: FS | C-56-01HG-CMA23-1030 | C-56-01HG-CMA23-1030: SS | 2025-05-12 11:00 | 2025-05-13 11:00
C-56-01HG-CMA23-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 | Section Tie-in Welding | C-56-01HG-CMA23-1020 | C-56-01HG-CMA23-1020: SS | C-56-01HG-CMA23-1040, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA23-1040: SS 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-05-12 11:00 | 2025-05-14 11:00
C-56-01HG-CMA23-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 | NDT (Tie-in Joint) | C-56-01HG-CMA23-1030 | C-56-01HG-CMA23-1030: SS 1 | C-56-01HG-CMA23-1050 | C-56-01HG-CMA23-1050: SS 1 | 2025-05-13 11:00 | 2025-05-15 11:00
C-56-01HG-CMA23-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA23-1040 | C-56-01HG-CMA23-1040: SS 1 | C-56-01HG-CMA23-1060 | C-56-01HG-CMA23-1060: FS | 2025-05-14 11:00 | 2025-05-16 11:00
C-56-01HG-CMA23-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 | Holiday Testing | C-56-01HG-CMA23-1050 | C-56-01HG-CMA23-1050: FS | C-56-01HG-CMA23-1070 | C-56-01HG-CMA23-1070: FS | 2025-05-16 11:00 | 2025-05-17 11:00
C-56-01HG-CMA23-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 | Padding | C-56-01HG-CMA23-1060 | C-56-01HG-CMA23-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-05-17 11:00 | 2025-05-19 11:00
C-56-01HG-CMA24-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 | Trench Excavation | C-56-01HG-CMA18-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA18-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA24-1010 | C-56-01HG-CMA24-1010: FF | 2025-04-19 13:00 | 2025-05-03 13:00
C-56-01HG-CMA24-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 | Bedding | C-56-01HG-CMA24-1000 | C-56-01HG-CMA24-1000: FF | C-56-01HG-CMA24-1020 | C-56-01HG-CMA24-1020: FS | 2025-05-01 13:00 | 2025-05-03 13:00
C-56-01HG-CMA24-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 | Lowering | C-56-01HG-CMA24-1010 | C-56-01HG-CMA24-1010: FS | C-56-01HG-CMA24-1030 | C-56-01HG-CMA24-1030: SS | 2025-05-03 13:00 | 2025-05-05 14:00
C-56-01HG-CMA24-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 | Section Tie-in Welding | C-56-01HG-CMA24-1020 | C-56-01HG-CMA24-1020: SS | C-56-01HG-CMA24-1040, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA24-1040: SS 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-05-03 13:00 | 2025-05-09 11:00
C-56-01HG-CMA24-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 | NDT (Tie-in Joint) | C-56-01HG-CMA24-1030 | C-56-01HG-CMA24-1030: SS 1 | C-56-01HG-CMA24-1050 | C-56-01HG-CMA24-1050: SS 1 | 2025-05-05 14:00 | 2025-05-10 11:00
C-56-01HG-CMA24-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA24-1040 | C-56-01HG-CMA24-1040: SS 1 | C-56-01HG-CMA24-1060 | C-56-01HG-CMA24-1060: FS | 2025-05-07 08:00 | 2025-05-12 11:00
C-56-01HG-CMA24-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 | Holiday Testing | C-56-01HG-CMA24-1050 | C-56-01HG-CMA24-1050: FS | C-56-01HG-CMA24-1070 | C-56-01HG-CMA24-1070: FS | 2025-05-12 11:00 | 2025-05-13 11:00
C-56-01HG-CMA24-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 | Padding | C-56-01HG-CMA24-1060 | C-56-01HG-CMA24-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-05-13 11:00 | 2025-05-14 11:00
C-56-01HG-CMA25-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 | Trench Excavation | C-56-01HG-CMA19-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA19-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA25-1010 | C-56-01HG-CMA25-1010: FF | 2025-04-26 13:00 | 2025-05-06 16:00
C-56-01HG-CMA25-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 | Bedding | C-56-01HG-CMA25-1000 | C-56-01HG-CMA25-1000: FF | C-56-01HG-CMA25-1020 | C-56-01HG-CMA25-1020: FS | 2025-05-05 14:00 | 2025-05-06 16:00
C-56-01HG-CMA25-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 | Lowering | C-56-01HG-CMA25-1010 | C-56-01HG-CMA25-1010: FS | C-56-01HG-CMA25-1030 | C-56-01HG-CMA25-1030: SS | 2025-05-07 08:00 | 2025-05-08 10:00
C-56-01HG-CMA25-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 | Section Tie-in Welding | C-56-01HG-CMA25-1020 | C-56-01HG-CMA25-1020: SS | C-56-01HG-CMA25-1040, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA25-1040: SS 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-05-07 08:00 | 2025-05-09 11:00
C-56-01HG-CMA25-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 | NDT (Tie-in Joint) | C-56-01HG-CMA25-1030 | C-56-01HG-CMA25-1030: SS 1 | C-56-01HG-CMA25-1050 | C-56-01HG-CMA25-1050: SS 1 | 2025-05-08 10:00 | 2025-05-10 11:00
C-56-01HG-CMA25-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA25-1040 | C-56-01HG-CMA25-1040: SS 1 | C-56-01HG-CMA25-1060 | C-56-01HG-CMA25-1060: FS | 2025-05-09 11:00 | 2025-05-12 11:00
C-56-01HG-CMA25-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 | Holiday Testing | C-56-01HG-CMA25-1050 | C-56-01HG-CMA25-1050: FS | C-56-01HG-CMA25-1070 | C-56-01HG-CMA25-1070: FS | 2025-05-12 11:00 | 2025-05-13 11:00
C-56-01HG-CMA25-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 | Padding | C-56-01HG-CMA25-1060 | C-56-01HG-CMA25-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-05-13 11:00 | 2025-05-14 11:00
C-56-01HG-CMA26-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 | Trench Excavation | C-56-01HG-CMA20-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA20-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA26-1010 | C-56-01HG-CMA26-1010: FF | 2025-04-25 13:00 | 2025-05-05 14:00
C-56-01HG-CMA26-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 | Bedding | C-56-01HG-CMA26-1000 | C-56-01HG-CMA26-1000: FF | C-56-01HG-CMA26-1020 | C-56-01HG-CMA26-1020: FS | 2025-05-03 13:00 | 2025-05-05 14:00
C-56-01HG-CMA26-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 | Lowering | C-56-01HG-CMA26-1010 | C-56-01HG-CMA26-1010: FS | C-56-01HG-CMA26-1030 | C-56-01HG-CMA26-1030: SS | 2025-05-05 14:00 | 2025-05-06 16:00
C-56-01HG-CMA26-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 | Section Tie-in Welding | C-56-01HG-CMA26-1020 | C-56-01HG-CMA26-1020: SS | C-56-01HG-CMA26-1040, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA26-1040: SS 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-05-05 14:00 | 2025-05-08 10:00
C-56-01HG-CMA26-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 | NDT (Tie-in Joint) | C-56-01HG-CMA26-1030 | C-56-01HG-CMA26-1030: SS 1 | C-56-01HG-CMA26-1050 | C-56-01HG-CMA26-1050: SS 1 | 2025-05-07 08:00 | 2025-05-09 11:00
C-56-01HG-CMA26-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA26-1040 | C-56-01HG-CMA26-1040: SS 1 | C-56-01HG-CMA26-1060 | C-56-01HG-CMA26-1060: FS | 2025-05-08 10:00 | 2025-05-10 11:00
C-56-01HG-CMA26-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 | Holiday Testing | C-56-01HG-CMA26-1050 | C-56-01HG-CMA26-1050: FS | C-56-01HG-CMA26-1070 | C-56-01HG-CMA26-1070: FS | 2025-05-10 11:00 | 2025-05-12 11:00
C-56-01HG-CMA26-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 | Padding | C-56-01HG-CMA26-1060 | C-56-01HG-CMA26-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-05-12 11:00 | 2025-05-13 11:00
C-56-01HG-CMA27-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 | Trench Excavation | C-56-01HG-CMA21-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA21-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA27-1010 | C-56-01HG-CMA27-1010: FF | 2025-04-09 13:00 | 2025-04-18 13:00
C-56-01HG-CMA27-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 | Bedding | C-56-01HG-CMA27-1000 | C-56-01HG-CMA27-1000: FF | C-56-01HG-CMA27-1020 | C-56-01HG-CMA27-1020: FS | 2025-04-17 13:00 | 2025-04-18 13:00
C-56-01HG-CMA27-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 | Lowering | C-56-01HG-CMA27-1010 | C-56-01HG-CMA27-1010: FS | C-56-01HG-CMA27-1030 | C-56-01HG-CMA27-1030: SS | 2025-04-18 13:00 | 2025-04-19 13:00
C-56-01HG-CMA27-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 | Section Tie-in Welding | C-56-01HG-CMA27-1020 | C-56-01HG-CMA27-1020: SS | C-56-01HG-CMA27-1040, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA27-1040: SS 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-18 13:00 | 2025-04-21 13:00
C-56-01HG-CMA27-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 | NDT (Tie-in Joint) | C-56-01HG-CMA27-1030 | C-56-01HG-CMA27-1030: SS 1 | C-56-01HG-CMA27-1050 | C-56-01HG-CMA27-1050: SS 1 | 2025-04-19 13:00 | 2025-04-22 13:00
C-56-01HG-CMA27-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA27-1040 | C-56-01HG-CMA27-1040: SS 1 | C-56-01HG-CMA27-1060 | C-56-01HG-CMA27-1060: FS | 2025-04-21 13:00 | 2025-04-23 13:00
C-56-01HG-CMA27-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 | Holiday Testing | C-56-01HG-CMA27-1050 | C-56-01HG-CMA27-1050: FS | C-56-01HG-CMA27-1070 | C-56-01HG-CMA27-1070: FS | 2025-04-23 13:00 | 2025-04-24 13:00
C-56-01HG-CMA27-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 | Padding | C-56-01HG-CMA27-1060 | C-56-01HG-CMA27-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-24 13:00 | 2025-04-25 13:00
C-56-01HG-CMA21-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 | Trench Excavation | C-56-01HG-CMA15-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA15-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA21-1010, C-56-01HG-CMA27-1000 | C-56-01HG-CMA21-1010: FF, C-56-01HG-CMA27-1000: FS | 2025-03-26 11:00 | 2025-04-09 13:00
C-56-01HG-CMA21-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 | Bedding | C-56-01HG-CMA21-1000 | C-56-01HG-CMA21-1000: FF | C-56-01HG-CMA21-1020 | C-56-01HG-CMA21-1020: FS | 2025-04-08 13:00 | 2025-04-09 13:00
C-56-01HG-CMA21-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 | Lowering | C-56-01HG-CMA21-1010 | C-56-01HG-CMA21-1010: FS | C-56-01HG-CMA21-1030 | C-56-01HG-CMA21-1030: SS | 2025-04-09 13:00 | 2025-04-10 13:00
C-56-01HG-CMA21-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 | Section Tie-in Welding | C-56-01HG-CMA21-1020 | C-56-01HG-CMA21-1020: SS | C-56-01HG-CMA21-1040, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA21-1040: SS 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-09 13:00 | 2025-04-11 13:00
C-56-01HG-CMA21-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 | NDT (Tie-in Joint) | C-56-01HG-CMA21-1030 | C-56-01HG-CMA21-1030: SS 1 | C-56-01HG-CMA21-1050 | C-56-01HG-CMA21-1050: SS 1 | 2025-04-10 13:00 | 2025-04-12 13:00
C-56-01HG-CMA21-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA21-1040 | C-56-01HG-CMA21-1040: SS 1 | C-56-01HG-CMA21-1060 | C-56-01HG-CMA21-1060: FS | 2025-04-11 13:00 | 2025-04-14 13:00
C-56-01HG-CMA21-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 | Holiday Testing | C-56-01HG-CMA21-1050 | C-56-01HG-CMA21-1050: FS | C-56-01HG-CMA21-1070 | C-56-01HG-CMA21-1070: FS | 2025-04-14 13:00 | 2025-04-15 13:00
C-56-01HG-CMA21-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 | Padding | C-56-01HG-CMA21-1060 | C-56-01HG-CMA21-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-15 13:00 | 2025-04-16 13:00
C-56-01HG-CMA22-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 | Trench Excavation | C-56-01HG-CMA16-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA16-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA22-1010 | C-56-01HG-CMA22-1010: FF | 2025-04-23 13:00 | 2025-04-30 13:00
C-56-01HG-CMA22-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 | Bedding | C-56-01HG-CMA22-1000 | C-56-01HG-CMA22-1000: FF | C-56-01HG-CMA22-1020 | C-56-01HG-CMA22-1020: FS | 2025-04-29 13:00 | 2025-04-30 13:00
C-56-01HG-CMA22-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 | Lowering | C-56-01HG-CMA22-1010 | C-56-01HG-CMA22-1010: FS | C-56-01HG-CMA22-1030 | C-56-01HG-CMA22-1030: SS | 2025-04-30 13:00 | 2025-05-01 13:00
C-56-01HG-CMA22-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 | Section Tie-in Welding | C-56-01HG-CMA22-1020 | C-56-01HG-CMA22-1020: SS | C-56-01HG-CMA22-1040, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA22-1040: SS 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-30 13:00 | 2025-05-02 13:00
C-56-01HG-CMA22-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 | NDT (Tie-in Joint) | C-56-01HG-CMA22-1030 | C-56-01HG-CMA22-1030: SS 1 | C-56-01HG-CMA22-1050 | C-56-01HG-CMA22-1050: SS 1 | 2025-05-01 13:00 | 2025-05-03 13:00
C-56-01HG-CMA22-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA22-1040 | C-56-01HG-CMA22-1040: SS 1 | C-56-01HG-CMA22-1060 | C-56-01HG-CMA22-1060: FS | 2025-05-02 13:00 | 2025-05-05 14:00
C-56-01HG-CMA22-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 | Holiday Testing | C-56-01HG-CMA22-1050 | C-56-01HG-CMA22-1050: FS | C-56-01HG-CMA22-1070 | C-56-01HG-CMA22-1070: FS | 2025-05-05 14:00 | 2025-05-06 16:00
C-56-01HG-CMA22-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 | Padding | C-56-01HG-CMA22-1060 | C-56-01HG-CMA22-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-05-07 08:00 | 2025-05-08 10:00
C-56-01HG-CMA19-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 | Trench Excavation | C-56-01HG-CMA13-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA13-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA19-1010, C-56-01HG-CMA25-1000 | C-56-01HG-CMA19-1010: FF, C-56-01HG-CMA25-1000: FS | 2025-04-17 13:00 | 2025-04-26 13:00
C-56-01HG-CMA19-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 | Bedding | C-56-01HG-CMA19-1000 | C-56-01HG-CMA19-1000: FF | C-56-01HG-CMA19-1020 | C-56-01HG-CMA19-1020: FS | 2025-04-25 13:00 | 2025-04-26 13:00
C-56-01HG-CMA19-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 | Lowering | C-56-01HG-CMA19-1010 | C-56-01HG-CMA19-1010: FS | C-56-01HG-CMA19-1030 | C-56-01HG-CMA19-1030: SS | 2025-04-26 13:00 | 2025-04-28 13:00
C-56-01HG-CMA19-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 | Section Tie-in Welding | C-56-01HG-CMA19-1020 | C-56-01HG-CMA19-1020: SS | C-56-01HG-CMA19-1040, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA19-1040: SS 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-26 13:00 | 2025-04-29 13:00
C-56-01HG-CMA19-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 | NDT (Tie-in Joint) | C-56-01HG-CMA19-1030 | C-56-01HG-CMA19-1030: SS 1 | C-56-01HG-CMA19-1050 | C-56-01HG-CMA19-1050: SS 1 | 2025-04-28 13:00 | 2025-04-30 13:00
C-56-01HG-CMA19-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA19-1040 | C-56-01HG-CMA19-1040: SS 1 | C-56-01HG-CMA19-1060 | C-56-01HG-CMA19-1060: FS | 2025-04-29 13:00 | 2025-05-01 13:00
C-56-01HG-CMA19-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 | Holiday Testing | C-56-01HG-CMA19-1050 | C-56-01HG-CMA19-1050: FS | C-56-01HG-CMA19-1070 | C-56-01HG-CMA19-1070: FS | 2025-05-01 13:00 | 2025-05-02 13:00
C-56-01HG-CMA19-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 | Padding | C-56-01HG-CMA19-1060 | C-56-01HG-CMA19-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-05-02 13:00 | 2025-05-03 13:00
C-56-01HG-CMA17-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 | Trench Excavation | C-56-01HG-CMA11-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA11-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA17-1010, C-56-01HG-CMA23-1000 | C-56-01HG-CMA17-1010: FF, C-56-01HG-CMA23-1000: FS | 2025-04-17 13:00 | 2025-05-01 13:00
C-56-01HG-CMA17-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 | Bedding | C-56-01HG-CMA17-1000 | C-56-01HG-CMA17-1000: FF | C-56-01HG-CMA17-1020 | C-56-01HG-CMA17-1020: FS | 2025-04-30 13:00 | 2025-05-01 13:00
C-56-01HG-CMA17-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 | Lowering | C-56-01HG-CMA17-1010 | C-56-01HG-CMA17-1010: FS | C-56-01HG-CMA17-1030 | C-56-01HG-CMA17-1030: SS | 2025-05-01 13:00 | 2025-05-02 13:00
C-56-01HG-CMA17-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 | Section Tie-in Welding | C-56-01HG-CMA17-1020 | C-56-01HG-CMA17-1020: SS | C-56-01HG-CMA17-1040, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA17-1040: SS 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-05-01 13:00 | 2025-05-05 14:00
C-56-01HG-CMA17-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 | NDT (Tie-in Joint) | C-56-01HG-CMA17-1030 | C-56-01HG-CMA17-1030: SS 1 | C-56-01HG-CMA17-1050 | C-56-01HG-CMA17-1050: SS 1 | 2025-05-02 13:00 | 2025-05-06 16:00
C-56-01HG-CMA17-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA17-1040 | C-56-01HG-CMA17-1040: SS 1 | C-56-01HG-CMA17-1060 | C-56-01HG-CMA17-1060: FS | 2025-05-03 13:00 | 2025-05-08 10:00
C-56-01HG-CMA17-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 | Holiday Testing | C-56-01HG-CMA17-1050 | C-56-01HG-CMA17-1050: FS | C-56-01HG-CMA17-1070 | C-56-01HG-CMA17-1070: FS | 2025-05-08 10:00 | 2025-05-09 11:00
C-56-01HG-CMA17-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 | Padding | C-56-01HG-CMA17-1060 | C-56-01HG-CMA17-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-05-09 11:00 | 2025-05-10 11:00
C-56-01HG-CMA20-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 | Trench Excavation | C-56-01HG-CMA14-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA14-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA20-1010, C-56-01HG-CMA26-1000 | C-56-01HG-CMA20-1010: FF, C-56-01HG-CMA26-1000: FS | 2025-04-16 13:00 | 2025-04-25 13:00
C-56-01HG-CMA20-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 | Bedding | C-56-01HG-CMA20-1000 | C-56-01HG-CMA20-1000: FF | C-56-01HG-CMA20-1020 | C-56-01HG-CMA20-1020: FS | 2025-04-24 13:00 | 2025-04-25 13:00
C-56-01HG-CMA20-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 | Lowering | C-56-01HG-CMA20-1010 | C-56-01HG-CMA20-1010: FS | C-56-01HG-CMA20-1030 | C-56-01HG-CMA20-1030: SS | 2025-04-25 13:00 | 2025-04-26 13:00
C-56-01HG-CMA20-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 | Section Tie-in Welding | C-56-01HG-CMA20-1020 | C-56-01HG-CMA20-1020: SS | C-56-01HG-CMA20-1040, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA20-1040: SS 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-25 13:00 | 2025-04-28 13:00
C-56-01HG-CMA20-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 | NDT (Tie-in Joint) | C-56-01HG-CMA20-1030 | C-56-01HG-CMA20-1030: SS 1 | C-56-01HG-CMA20-1050 | C-56-01HG-CMA20-1050: SS 1 | 2025-04-26 13:00 | 2025-04-29 13:00
C-56-01HG-CMA20-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA20-1040 | C-56-01HG-CMA20-1040: SS 1 | C-56-01HG-CMA20-1060 | C-56-01HG-CMA20-1060: FS | 2025-04-28 13:00 | 2025-04-30 13:00
C-56-01HG-CMA20-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 | Holiday Testing | C-56-01HG-CMA20-1050 | C-56-01HG-CMA20-1050: FS | C-56-01HG-CMA20-1070 | C-56-01HG-CMA20-1070: FS | 2025-04-30 13:00 | 2025-05-01 13:00
C-56-01HG-CMA20-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 | Padding | C-56-01HG-CMA20-1060 | C-56-01HG-CMA20-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-05-01 13:00 | 2025-05-02 13:00
C-56-01HG-CMA16-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 | Trench Excavation | C-56-01HG-CMA10-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA10-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA16-1010, C-56-01HG-CMA22-1000 | C-56-01HG-CMA16-1010: FF, C-56-01HG-CMA22-1000: FS | 2025-04-14 13:00 | 2025-04-23 13:00
C-56-01HG-CMA16-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 | Bedding | C-56-01HG-CMA16-1000 | C-56-01HG-CMA16-1000: FF | C-56-01HG-CMA16-1020 | C-56-01HG-CMA16-1020: FS | 2025-04-22 13:00 | 2025-04-23 13:00
C-56-01HG-CMA16-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 | Lowering | C-56-01HG-CMA16-1010 | C-56-01HG-CMA16-1010: FS | C-56-01HG-CMA16-1030 | C-56-01HG-CMA16-1030: SS | 2025-04-23 13:00 | 2025-04-24 13:00
C-56-01HG-CMA16-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 | Section Tie-in Welding | C-56-01HG-CMA16-1020 | C-56-01HG-CMA16-1020: SS | C-56-01HG-CMA16-1040, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA16-1040: SS 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-23 13:00 | 2025-04-25 13:00
C-56-01HG-CMA16-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 | NDT (Tie-in Joint) | C-56-01HG-CMA16-1030 | C-56-01HG-CMA16-1030: SS 1 | C-56-01HG-CMA16-1050 | C-56-01HG-CMA16-1050: SS 1 | 2025-04-24 13:00 | 2025-04-26 13:00
C-56-01HG-CMA16-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA16-1040 | C-56-01HG-CMA16-1040: SS 1 | C-56-01HG-CMA16-1060 | C-56-01HG-CMA16-1060: FS | 2025-04-25 13:00 | 2025-04-28 13:00
C-56-01HG-CMA16-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 | Holiday Testing | C-56-01HG-CMA16-1050 | C-56-01HG-CMA16-1050: FS | C-56-01HG-CMA16-1070 | C-56-01HG-CMA16-1070: FS | 2025-04-28 13:00 | 2025-04-29 13:00
C-56-01HG-CMA16-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 | Padding | C-56-01HG-CMA16-1060 | C-56-01HG-CMA16-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-29 13:00 | 2025-04-30 13:00
C-56-01HG-CMA18-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 | Trench Excavation | C-56-01HG-CMA12-1000, HE-PL-2910, HE-PL-2970 | C-56-01HG-CMA12-1000: FS, HE-PL-2910: FS, HE-PL-2970: FS | C-56-01HG-CMA18-1010, C-56-01HG-CMA24-1000 | C-56-01HG-CMA18-1010: FF, C-56-01HG-CMA24-1000: FS | 2025-04-10 13:00 | 2025-04-19 13:00
C-56-01HG-CMA18-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 | Bedding | C-56-01HG-CMA18-1000 | C-56-01HG-CMA18-1000: FF | C-56-01HG-CMA18-1020 | C-56-01HG-CMA18-1020: FS | 2025-04-18 13:00 | 2025-04-19 13:00
C-56-01HG-CMA18-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 | Lowering | C-56-01HG-CMA18-1010 | C-56-01HG-CMA18-1010: FS | C-56-01HG-CMA18-1030 | C-56-01HG-CMA18-1030: SS | 2025-04-19 13:00 | 2025-04-21 13:00
C-56-01HG-CMA18-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 | Section Tie-in Welding | C-56-01HG-CMA18-1020 | C-56-01HG-CMA18-1020: SS | C-56-01HG-CMA18-1040, C-56-01HG-PL-ME-5010 | C-56-01HG-CMA18-1040: SS 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-19 13:00 | 2025-04-22 13:00
C-56-01HG-CMA18-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 | NDT (Tie-in Joint) | C-56-01HG-CMA18-1030 | C-56-01HG-CMA18-1030: SS 1 | C-56-01HG-CMA18-1050 | C-56-01HG-CMA18-1050: SS 1 | 2025-04-21 13:00 | 2025-04-23 13:00
C-56-01HG-CMA18-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA18-1040 | C-56-01HG-CMA18-1040: SS 1 | C-56-01HG-CMA18-1060 | C-56-01HG-CMA18-1060: FS | 2025-04-22 13:00 | 2025-04-24 13:00
C-56-01HG-CMA18-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 | Holiday Testing | C-56-01HG-CMA18-1050 | C-56-01HG-CMA18-1050: FS | C-56-01HG-CMA18-1070 | C-56-01HG-CMA18-1070: FS | 2025-04-24 13:00 | 2025-04-25 13:00
C-56-01HG-CMA18-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 | Padding | C-56-01HG-CMA18-1060 | C-56-01HG-CMA18-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-25 13:00 | 2025-04-26 13:00
C-56-HC01-CMA02-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA04-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA04-1000: FS | C-56-HC01-CMA02-1010, C-56-HC01-CMA03-1000 | C-56-HC01-CMA02-1010: FF, C-56-HC01-CMA03-1000: FS | 2025-04-08 13:00 | 2025-04-15 13:00
C-56-HC01-CMA02-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 | Bedding | C-56-HC01-CMA02-1000 | C-56-HC01-CMA02-1000: FF | C-56-HC01-CMA02-1020 | C-56-HC01-CMA02-1020: FS | 2025-04-14 13:00 | 2025-04-15 13:00
C-56-HC01-CMA02-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 | Lowering | C-56-HC01-CMA02-1010 | C-56-HC01-CMA02-1010: FS | C-56-HC01-CMA02-1030 | C-56-HC01-CMA02-1030: SS | 2025-04-15 13:00 | 2025-04-16 13:00
C-56-HC01-CMA02-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 | Section Tie-in Welding | C-56-HC01-CMA02-1020 | C-56-HC01-CMA02-1020: SS | C-56-HC01-CMA02-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA02-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-04-15 13:00 | 2025-04-17 13:00
C-56-HC01-CMA02-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 | NDT (Tie-in Joint) | C-56-HC01-CMA02-1030 | C-56-HC01-CMA02-1030: SS 1 | C-56-HC01-CMA02-1050 | C-56-HC01-CMA02-1050: SS 1 | 2025-04-16 13:00 | 2025-04-18 13:00
C-56-HC01-CMA02-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA02-1040 | C-56-HC01-CMA02-1040: SS 1 | C-56-HC01-CMA02-1060 | C-56-HC01-CMA02-1060: FS | 2025-04-17 13:00 | 2025-04-19 13:00
C-56-HC01-CMA02-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 | Holiday Testing | C-56-HC01-CMA02-1050 | C-56-HC01-CMA02-1050: FS | C-56-HC01-CMA02-1070, C-56-HC01-PL-CA-5220, C-56-HC01-PL-CA-5400 | C-56-HC01-CMA02-1070: FS, C-56-HC01-PL-CA-5220: SS, C-56-HC01-PL-CA-5400: SS | 2025-04-19 13:00 | 2025-04-21 13:00
C-56-HC01-CMA02-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 | Padding | C-56-HC01-CMA02-1060 | C-56-HC01-CMA02-1060: FS | C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-21 13:00 | 2025-04-22 13:00
C-56-HC01-CMA03-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA02-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA02-1000: FS | C-56-HC01-CMA03-1010 | C-56-HC01-CMA03-1010: FF | 2025-04-15 13:00 | 2025-04-22 13:00
C-56-HC01-CMA03-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 | Bedding | C-56-HC01-CMA03-1000 | C-56-HC01-CMA03-1000: FF | C-56-HC01-CMA03-1020 | C-56-HC01-CMA03-1020: FS | 2025-04-21 13:00 | 2025-04-22 13:00
C-56-HC01-CMA03-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 | Lowering | C-56-HC01-CMA03-1010 | C-56-HC01-CMA03-1010: FS | C-56-HC01-CMA03-1030 | C-56-HC01-CMA03-1030: SS | 2025-04-22 13:00 | 2025-04-23 13:00
C-56-HC01-CMA03-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 | Section Tie-in Welding | C-56-HC01-CMA03-1020 | C-56-HC01-CMA03-1020: SS | C-56-HC01-CMA03-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA03-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-04-22 13:00 | 2025-04-24 13:00
C-56-HC01-CMA03-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 | NDT (Tie-in Joint) | C-56-HC01-CMA03-1030 | C-56-HC01-CMA03-1030: SS 1 | C-56-HC01-CMA03-1050 | C-56-HC01-CMA03-1050: SS 1 | 2025-04-23 13:00 | 2025-04-25 13:00
C-56-HC01-CMA03-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA03-1040 | C-56-HC01-CMA03-1040: SS 1 | C-56-HC01-CMA03-1060 | C-56-HC01-CMA03-1060: FS | 2025-04-24 13:00 | 2025-04-26 13:00
C-56-HC01-CMA03-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 | Holiday Testing | C-56-HC01-CMA03-1050 | C-56-HC01-CMA03-1050: FS | C-56-HC01-CMA03-1070 | C-56-HC01-CMA03-1070: FS | 2025-04-26 13:00 | 2025-04-28 13:00
C-56-HC01-CMA03-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 | Padding | C-56-HC01-CMA03-1060 | C-56-HC01-CMA03-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-28 13:00 | 2025-04-29 13:00
C-56-HC01-CMA13-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA09-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA09-1000: SS | C-56-HC01-CMA13-1010 | C-56-HC01-CMA13-1010: FF | 2025-03-19 07:00 | 2025-04-03 13:00
C-56-HC01-CMA13-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 | Bedding | C-56-HC01-CMA13-1000 | C-56-HC01-CMA13-1000: FF | C-56-HC01-CMA13-1020 | C-56-HC01-CMA13-1020: FS | 2025-03-29 13:00 | 2025-04-03 13:00
C-56-HC01-CMA13-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 | Lowering | C-56-HC01-CMA13-1010 | C-56-HC01-CMA13-1010: FS | C-56-HC01-CMA13-1030 | C-56-HC01-CMA13-1030: SS | 2025-04-03 13:00 | 2025-04-04 13:00
C-56-HC01-CMA13-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 | Section Tie-in Welding | C-56-HC01-CMA13-1020 | C-56-HC01-CMA13-1020: SS | C-56-HC01-CMA13-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA13-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-04-03 13:00 | 2025-04-05 13:00
C-56-HC01-CMA13-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 | NDT (Tie-in Joint) | C-56-HC01-CMA13-1030 | C-56-HC01-CMA13-1030: SS 1 | C-56-HC01-CMA13-1050 | C-56-HC01-CMA13-1050: SS 1 | 2025-04-04 13:00 | 2025-04-07 13:00
C-56-HC01-CMA13-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA13-1040 | C-56-HC01-CMA13-1040: SS 1 | C-56-HC01-CMA13-1060 | C-56-HC01-CMA13-1060: FS | 2025-04-05 13:00 | 2025-04-08 13:00
C-56-HC01-CMA13-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 | Holiday Testing | C-56-HC01-CMA13-1050 | C-56-HC01-CMA13-1050: FS | C-56-HC01-CMA13-1070 | C-56-HC01-CMA13-1070: FS | 2025-04-08 13:00 | 2025-04-09 13:00
C-56-HC01-CMA13-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 | Padding | C-56-HC01-CMA13-1060 | C-56-HC01-CMA13-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-09 13:00 | 2025-04-10 13:00
C-56-HC01-CMA09-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA11-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA11-1000: SS | C-56-HC01-CMA09-1010, C-56-HC01-CMA13-1000 | C-56-HC01-CMA09-1010: FF, C-56-HC01-CMA13-1000: SS | 2025-03-19 07:00 | 2025-04-12 13:00
C-56-HC01-CMA09-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 | Bedding | C-56-HC01-CMA09-1000 | C-56-HC01-CMA09-1000: FF | C-56-HC01-CMA09-1020 | C-56-HC01-CMA09-1020: FS | 2025-04-11 13:00 | 2025-04-12 13:00
C-56-HC01-CMA09-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 | Lowering | C-56-HC01-CMA09-1010 | C-56-HC01-CMA09-1010: FS | C-56-HC01-CMA09-1030 | C-56-HC01-CMA09-1030: SS | 2025-04-12 13:00 | 2025-04-14 13:00
C-56-HC01-CMA09-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 | Section Tie-in Welding | C-56-HC01-CMA09-1020 | C-56-HC01-CMA09-1020: SS | C-56-HC01-CMA09-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA09-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-04-12 13:00 | 2025-04-17 13:00
C-56-HC01-CMA09-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 | NDT (Tie-in Joint) | C-56-HC01-CMA09-1030 | C-56-HC01-CMA09-1030: SS 1 | C-56-HC01-CMA09-1050 | C-56-HC01-CMA09-1050: SS 1 | 2025-04-14 13:00 | 2025-04-18 13:00
C-56-HC01-CMA09-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA09-1040 | C-56-HC01-CMA09-1040: SS 1 | C-56-HC01-CMA09-1060 | C-56-HC01-CMA09-1060: FS | 2025-04-15 13:00 | 2025-04-19 13:00
C-56-HC01-CMA09-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 | Holiday Testing | C-56-HC01-CMA09-1050 | C-56-HC01-CMA09-1050: FS | C-56-HC01-CMA09-1070 | C-56-HC01-CMA09-1070: FS | 2025-04-19 13:00 | 2025-04-21 13:00
C-56-HC01-CMA09-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 | Padding | C-56-HC01-CMA09-1060 | C-56-HC01-CMA09-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-21 13:00 | 2025-04-22 13:00
C-56-HC01-CMA11-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA14-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA14-1000: FS | C-56-HC01-CMA11-1010, C-56-HC01-CMA09-1000 | C-56-HC01-CMA11-1010: FF, C-56-HC01-CMA09-1000: SS | 2025-03-19 07:00 | 2025-04-08 13:00
C-56-HC01-CMA11-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 | Bedding | C-56-HC01-CMA11-1000 | C-56-HC01-CMA11-1000: FF | C-56-HC01-CMA11-1020 | C-56-HC01-CMA11-1020: FS | 2025-04-07 13:00 | 2025-04-08 13:00
C-56-HC01-CMA11-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 | Lowering | C-56-HC01-CMA11-1010 | C-56-HC01-CMA11-1010: FS | C-56-HC01-CMA11-1030 | C-56-HC01-CMA11-1030: SS | 2025-04-08 13:00 | 2025-04-09 13:00
C-56-HC01-CMA11-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 | Section Tie-in Welding | C-56-HC01-CMA11-1020 | C-56-HC01-CMA11-1020: SS | C-56-HC01-CMA11-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA11-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-04-08 13:00 | 2025-04-10 13:00
C-56-HC01-CMA11-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 | NDT (Tie-in Joint) | C-56-HC01-CMA11-1030 | C-56-HC01-CMA11-1030: SS 1 | C-56-HC01-CMA11-1050 | C-56-HC01-CMA11-1050: SS 1 | 2025-04-09 13:00 | 2025-04-11 13:00
C-56-HC01-CMA11-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA11-1040 | C-56-HC01-CMA11-1040: SS 1 | C-56-HC01-CMA11-1060 | C-56-HC01-CMA11-1060: FS | 2025-04-10 13:00 | 2025-04-12 13:00
C-56-HC01-CMA11-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 | Holiday Testing | C-56-HC01-CMA11-1050 | C-56-HC01-CMA11-1050: FS | C-56-HC01-CMA11-1070 | C-56-HC01-CMA11-1070: FS | 2025-04-12 13:00 | 2025-04-14 13:00
C-56-HC01-CMA11-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 | Padding | C-56-HC01-CMA11-1060 | C-56-HC01-CMA11-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-14 13:00 | 2025-04-15 13:00
C-56-HC01-CMA14-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-PL-ME-2800 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-PL-ME-2800: SS | C-56-HC01-CMA14-1010, C-56-HC01-CMA11-1000 | C-56-HC01-CMA14-1010: FF, C-56-HC01-CMA11-1000: FS | 2025-03-01 07:00 | 2025-03-18 13:00
C-56-HC01-CMA14-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 | Bedding | C-56-HC01-CMA14-1000 | C-56-HC01-CMA14-1000: FF | C-56-HC01-CMA14-1020 | C-56-HC01-CMA14-1020: FS | 2025-03-17 09:00 | 2025-03-18 13:00
C-56-HC01-CMA14-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 | Lowering | C-56-HC01-CMA14-1010 | C-56-HC01-CMA14-1010: FS | C-56-HC01-CMA14-1030 | C-56-HC01-CMA14-1030: SS | 2025-03-19 07:00 | 2025-03-20 11:00
C-56-HC01-CMA14-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 | Section Tie-in Welding | C-56-HC01-CMA14-1020 | C-56-HC01-CMA14-1020: SS | C-56-HC01-CMA14-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA14-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-19 07:00 | 2025-03-22 09:00
C-56-HC01-CMA14-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 | NDT (Tie-in Joint) | C-56-HC01-CMA14-1030 | C-56-HC01-CMA14-1030: SS 1 | C-56-HC01-CMA14-1050 | C-56-HC01-CMA14-1050: SS 1 | 2025-03-20 11:00 | 2025-03-23 09:00
C-56-HC01-CMA14-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA14-1040 | C-56-HC01-CMA14-1040: SS 1 | C-56-HC01-CMA14-1060 | C-56-HC01-CMA14-1060: FS | 2025-03-22 09:00 | 2025-03-24 13:00
C-56-HC01-CMA14-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 | Holiday Testing | C-56-HC01-CMA14-1050 | C-56-HC01-CMA14-1050: FS | C-56-HC01-CMA14-1070 | C-56-HC01-CMA14-1070: FS | 2025-03-25 07:00 | 2025-03-26 11:00
C-56-HC01-CMA14-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 | Padding | C-56-HC01-CMA14-1060 | C-56-HC01-CMA14-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-03-26 11:00 | 2025-03-28 09:00
C-56-HC01-CMA15-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA10-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA10-1000: FS | C-56-HC01-CMA15-1010 | C-56-HC01-CMA15-1010: FF | 2025-05-02 13:00 | 2025-05-17 11:00
C-56-HC01-CMA15-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 | Bedding | C-56-HC01-CMA15-1000 | C-56-HC01-CMA15-1000: FF | C-56-HC01-CMA15-1020 | C-56-HC01-CMA15-1020: FS | 2025-05-16 11:00 | 2025-05-17 11:00
C-56-HC01-CMA15-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 | Lowering | C-56-HC01-CMA15-1010 | C-56-HC01-CMA15-1010: FS | C-56-HC01-CMA15-1030 | C-56-HC01-CMA15-1030: SS | 2025-05-17 11:00 | 2025-05-19 11:00
C-56-HC01-CMA15-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 | Section Tie-in Welding | C-56-HC01-CMA15-1020 | C-56-HC01-CMA15-1020: SS | C-56-HC01-CMA15-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA15-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-05-17 11:00 | 2025-05-21 11:00
C-56-HC01-CMA15-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 | NDT (Tie-in Joint) | C-56-HC01-CMA15-1030 | C-56-HC01-CMA15-1030: SS 1 | C-56-HC01-CMA15-1050 | C-56-HC01-CMA15-1050: SS 1 | 2025-05-19 11:00 | 2025-05-22 11:00
C-56-HC01-CMA15-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA15-1040 | C-56-HC01-CMA15-1040: SS 1 | C-56-HC01-CMA15-1060 | C-56-HC01-CMA15-1060: FS | 2025-05-20 11:00 | 2025-05-23 11:00
C-56-HC01-CMA15-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 | Holiday Testing | C-56-HC01-CMA15-1050 | C-56-HC01-CMA15-1050: FS | C-56-HC01-CMA15-1070 | C-56-HC01-CMA15-1070: FS | 2025-05-23 11:00 | 2025-05-24 11:00
C-56-HC01-CMA15-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 | Padding | C-56-HC01-CMA15-1060 | C-56-HC01-CMA15-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-05-24 11:00 | 2025-05-26 11:00
C-56-HC01-CMA22-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA21-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA21-1000: FS | C-56-HC01-CMA22-1010, C-56-HC01-CMA23-1000 | C-56-HC01-CMA22-1010: FF, C-56-HC01-CMA23-1000: FS | 2025-04-04 13:00 | 2025-04-14 13:00
C-56-HC01-CMA22-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 | Bedding | C-56-HC01-CMA22-1000 | C-56-HC01-CMA22-1000: FF | C-56-HC01-CMA22-1020 | C-56-HC01-CMA22-1020: FS | 2025-04-12 13:00 | 2025-04-14 13:00
C-56-HC01-CMA22-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 | Lowering | C-56-HC01-CMA22-1010 | C-56-HC01-CMA22-1010: FS | C-56-HC01-CMA22-1030 | C-56-HC01-CMA22-1030: SS | 2025-04-14 13:00 | 2025-04-15 13:00
C-56-HC01-CMA22-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 | Section Tie-in Welding | C-56-HC01-CMA22-1020 | C-56-HC01-CMA22-1020: SS | C-56-HC01-CMA22-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA22-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-04-14 13:00 | 2025-04-16 13:00
C-56-HC01-CMA22-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 | NDT (Tie-in Joint) | C-56-HC01-CMA22-1030 | C-56-HC01-CMA22-1030: SS 1 | C-56-HC01-CMA22-1050 | C-56-HC01-CMA22-1050: SS 1 | 2025-04-15 13:00 | 2025-04-17 13:00
C-56-HC01-CMA22-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA22-1040 | C-56-HC01-CMA22-1040: SS 1 | C-56-HC01-CMA22-1060 | C-56-HC01-CMA22-1060: FS | 2025-04-16 13:00 | 2025-04-18 13:00
C-56-HC01-CMA22-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 | Holiday Testing | C-56-HC01-CMA22-1050 | C-56-HC01-CMA22-1050: FS | C-56-HC01-CMA22-1070 | C-56-HC01-CMA22-1070: FS | 2025-04-18 13:00 | 2025-04-19 13:00
C-56-HC01-CMA22-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 | Padding | C-56-HC01-CMA22-1060 | C-56-HC01-CMA22-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-19 13:00 | 2025-04-21 13:00
C-56-HC01-CMA04-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA07-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA07-1000: FS | C-56-HC01-CMA04-1010, C-56-HC01-CMA02-1000 | C-56-HC01-CMA04-1010: FF, C-56-HC01-CMA02-1000: FS | 2025-03-28 09:00 | 2025-04-08 13:00
C-56-HC01-CMA04-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 | Bedding | C-56-HC01-CMA04-1000 | C-56-HC01-CMA04-1000: FF | C-56-HC01-CMA04-1020 | C-56-HC01-CMA04-1020: FS | 2025-04-07 13:00 | 2025-04-08 13:00
C-56-HC01-CMA04-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 | Lowering | C-56-HC01-CMA04-1010 | C-56-HC01-CMA04-1010: FS | C-56-HC01-CMA04-1030 | C-56-HC01-CMA04-1030: SS | 2025-04-08 13:00 | 2025-04-09 13:00
C-56-HC01-CMA04-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 | Section Tie-in Welding | C-56-HC01-CMA04-1020 | C-56-HC01-CMA04-1020: SS | C-56-HC01-CMA04-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA04-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-04-08 13:00 | 2025-04-10 13:00
C-56-HC01-CMA04-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 | NDT (Tie-in Joint) | C-56-HC01-CMA04-1030 | C-56-HC01-CMA04-1030: SS 1 | C-56-HC01-CMA04-1050 | C-56-HC01-CMA04-1050: SS 1 | 2025-04-09 13:00 | 2025-04-11 13:00
C-56-HC01-CMA04-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA04-1040 | C-56-HC01-CMA04-1040: SS 1 | C-56-HC01-CMA04-1060 | C-56-HC01-CMA04-1060: FS | 2025-04-10 13:00 | 2025-04-12 13:00
C-56-HC01-CMA04-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 | Holiday Testing | C-56-HC01-CMA04-1050 | C-56-HC01-CMA04-1050: FS | C-56-HC01-CMA04-1070 | C-56-HC01-CMA04-1070: FS | 2025-04-12 13:00 | 2025-04-14 13:00
C-56-HC01-CMA04-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 | Padding | C-56-HC01-CMA04-1060 | C-56-HC01-CMA04-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-14 13:00 | 2025-04-15 13:00
C-56-HC01-CMA16-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-PL-ME-2800 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-PL-ME-2800: SS | C-56-HC01-CMA16-1010, C-56-HC01-CMA17-1000 | C-56-HC01-CMA16-1010: FF, C-56-HC01-CMA17-1000: FS | 2025-03-01 07:00 | 2025-03-12 13:00
C-56-HC01-CMA16-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 | Bedding | C-56-HC01-CMA16-1000 | C-56-HC01-CMA16-1000: FF | C-56-HC01-CMA16-1020 | C-56-HC01-CMA16-1020: FS | 2025-03-11 09:00 | 2025-03-12 13:00
C-56-HC01-CMA16-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 | Lowering | C-56-HC01-CMA16-1010 | C-56-HC01-CMA16-1010: FS | C-56-HC01-CMA16-1030 | C-56-HC01-CMA16-1030: SS | 2025-03-13 07:00 | 2025-03-14 11:00
C-56-HC01-CMA16-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 | Section Tie-in Welding | C-56-HC01-CMA16-1020 | C-56-HC01-CMA16-1020: SS | C-56-HC01-CMA16-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA16-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-13 07:00 | 2025-03-15 15:00
C-56-HC01-CMA16-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 | NDT (Tie-in Joint) | C-56-HC01-CMA16-1030 | C-56-HC01-CMA16-1030: SS 1 | C-56-HC01-CMA16-1050 | C-56-HC01-CMA16-1050: SS 1 | 2025-03-14 11:00 | 2025-03-17 09:00
C-56-HC01-CMA16-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA16-1040 | C-56-HC01-CMA16-1040: SS 1 | C-56-HC01-CMA16-1060 | C-56-HC01-CMA16-1060: FS | 2025-03-15 15:00 | 2025-03-18 13:00
C-56-HC01-CMA16-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 | Holiday Testing | C-56-HC01-CMA16-1050 | C-56-HC01-CMA16-1050: FS | C-56-HC01-CMA16-1070 | C-56-HC01-CMA16-1070: FS | 2025-03-19 07:00 | 2025-03-20 11:00
C-56-HC01-CMA16-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 | Padding | C-56-HC01-CMA16-1060 | C-56-HC01-CMA16-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-03-20 11:00 | 2025-03-22 09:00
C-56-HC01-CMA18-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA17-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA17-1000: FS | C-56-HC01-CMA18-1010, C-56-HC01-CMA19-1000 | C-56-HC01-CMA18-1010: FF, C-56-HC01-CMA19-1000: FS | 2025-03-25 07:00 | 2025-04-08 13:00
C-56-HC01-CMA18-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 | Bedding | C-56-HC01-CMA18-1000 | C-56-HC01-CMA18-1000: FF | C-56-HC01-CMA18-1020 | C-56-HC01-CMA18-1020: FS | 2025-04-07 13:00 | 2025-04-08 13:00
C-56-HC01-CMA18-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 | Lowering | C-56-HC01-CMA18-1010 | C-56-HC01-CMA18-1010: FS | C-56-HC01-CMA18-1030 | C-56-HC01-CMA18-1030: SS | 2025-04-08 13:00 | 2025-04-09 13:00
C-56-HC01-CMA18-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 | Section Tie-in Welding | C-56-HC01-CMA18-1020 | C-56-HC01-CMA18-1020: SS | C-56-HC01-CMA18-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA18-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-04-08 13:00 | 2025-04-10 13:00
C-56-HC01-CMA18-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 | NDT (Tie-in Joint) | C-56-HC01-CMA18-1030 | C-56-HC01-CMA18-1030: SS 1 | C-56-HC01-CMA18-1050 | C-56-HC01-CMA18-1050: SS 1 | 2025-04-09 13:00 | 2025-04-11 13:00
C-56-HC01-CMA18-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA18-1040 | C-56-HC01-CMA18-1040: SS 1 | C-56-HC01-CMA18-1060 | C-56-HC01-CMA18-1060: FS | 2025-04-10 13:00 | 2025-04-12 13:00
C-56-HC01-CMA18-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 | Holiday Testing | C-56-HC01-CMA18-1050 | C-56-HC01-CMA18-1050: FS | C-56-HC01-CMA18-1070 | C-56-HC01-CMA18-1070: FS | 2025-04-12 13:00 | 2025-04-14 13:00
C-56-HC01-CMA18-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 | Padding | C-56-HC01-CMA18-1060 | C-56-HC01-CMA18-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-14 13:00 | 2025-04-15 13:00
C-56-HC01-CMA20-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-PL-ME-2800 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-PL-ME-2800: SS 1 | C-56-HC01-CMA20-1010, C-56-HC01-CMA21-1000 | C-56-HC01-CMA20-1010: FF, C-56-HC01-CMA21-1000: FS | 2025-03-02 07:00 | 2025-03-20 11:00
C-56-HC01-CMA20-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 | Bedding | C-56-HC01-CMA20-1000 | C-56-HC01-CMA20-1000: FF | C-56-HC01-CMA20-1020 | C-56-HC01-CMA20-1020: FS | 2025-03-19 07:00 | 2025-03-20 11:00
C-56-HC01-CMA20-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 | Lowering | C-56-HC01-CMA20-1010 | C-56-HC01-CMA20-1010: FS | C-56-HC01-CMA20-1030, C-56-HC01-CMA20-1030 | C-56-HC01-CMA20-1030: SS, C-56-HC01-CMA20-1030: FF | 2025-03-20 11:00 | 2025-03-22 09:00
C-56-HC01-CMA20-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 | Section Tie-in Welding | C-56-HC01-CMA20-1020, C-56-HC01-CMA20-1020 | C-56-HC01-CMA20-1020: SS, C-56-HC01-CMA20-1020: FF | C-56-HC01-CMA20-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA20-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-20 11:00 | 2025-03-23 09:00
C-56-HC01-CMA20-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 | NDT (Tie-in Joint) | C-56-HC01-CMA20-1030 | C-56-HC01-CMA20-1030: SS 1 | C-56-HC01-CMA20-1050 | C-56-HC01-CMA20-1050: SS 1 | 2025-03-22 09:00 | 2025-03-24 13:00
C-56-HC01-CMA20-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA20-1040 | C-56-HC01-CMA20-1040: SS 1 | C-56-HC01-CMA20-1060 | C-56-HC01-CMA20-1060: FS | 2025-03-23 09:00 | 2025-03-26 11:00
C-56-HC01-CMA20-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 | Holiday Testing | C-56-HC01-CMA20-1050 | C-56-HC01-CMA20-1050: FS | C-56-HC01-CMA20-1070 | C-56-HC01-CMA20-1070: FS | 2025-03-26 11:00 | 2025-03-28 09:00
C-56-HC01-CMA20-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 | Padding | C-56-HC01-CMA20-1060 | C-56-HC01-CMA20-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-03-28 09:00 | 2025-03-29 13:00
C-56-HC01-CMA23-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA22-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA22-1000: FS | C-56-HC01-CMA23-1010 | C-56-HC01-CMA23-1010: FF | 2025-04-14 13:00 | 2025-04-23 13:00
C-56-HC01-CMA23-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 | Bedding | C-56-HC01-CMA23-1000 | C-56-HC01-CMA23-1000: FF | C-56-HC01-CMA23-1020 | C-56-HC01-CMA23-1020: FS | 2025-04-22 13:00 | 2025-04-23 13:00
C-56-HC01-CMA23-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 | Lowering | C-56-HC01-CMA23-1010 | C-56-HC01-CMA23-1010: FS | C-56-HC01-CMA23-1030 | C-56-HC01-CMA23-1030: SS | 2025-04-23 13:00 | 2025-04-24 13:00
C-56-HC01-CMA23-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 | Section Tie-in Welding | C-56-HC01-CMA23-1020 | C-56-HC01-CMA23-1020: SS | C-56-HC01-CMA23-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA23-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-04-23 13:00 | 2025-04-25 13:00
C-56-HC01-CMA23-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 | NDT (Tie-in Joint) | C-56-HC01-CMA23-1030 | C-56-HC01-CMA23-1030: SS 1 | C-56-HC01-CMA23-1050 | C-56-HC01-CMA23-1050: SS 1 | 2025-04-24 13:00 | 2025-04-26 13:00
C-56-HC01-CMA23-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA23-1040 | C-56-HC01-CMA23-1040: SS 1 | C-56-HC01-CMA23-1060 | C-56-HC01-CMA23-1060: FS | 2025-04-25 13:00 | 2025-04-28 13:00
C-56-HC01-CMA23-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 | Holiday Testing | C-56-HC01-CMA23-1050 | C-56-HC01-CMA23-1050: FS | C-56-HC01-CMA23-1070 | C-56-HC01-CMA23-1070: FS | 2025-04-28 13:00 | 2025-04-29 13:00
C-56-HC01-CMA23-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 | Padding | C-56-HC01-CMA23-1060 | C-56-HC01-CMA23-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-29 13:00 | 2025-04-30 13:00
C-56-HC01-CMA28-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA27-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA27-1000: SS 7 | C-56-HC01-CMA28-1010, C-56-HC01-CMA29-1000 | C-56-HC01-CMA28-1010: FF, C-56-HC01-CMA29-1000: FS | 2025-03-11 09:00 | 2025-03-23 09:00
C-56-HC01-CMA28-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 | Bedding | C-56-HC01-CMA28-1000 | C-56-HC01-CMA28-1000: FF | C-56-HC01-CMA28-1020 | C-56-HC01-CMA28-1020: FS | 2025-03-22 09:00 | 2025-03-23 09:00
C-56-HC01-CMA28-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 | Lowering | C-56-HC01-CMA28-1010 | C-56-HC01-CMA28-1010: FS | C-56-HC01-CMA28-1030 | C-56-HC01-CMA28-1030: SS | 2025-03-23 09:00 | 2025-03-24 13:00
C-56-HC01-CMA28-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 | Section Tie-in Welding | C-56-HC01-CMA28-1020 | C-56-HC01-CMA28-1020: SS | C-56-HC01-CMA28-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA28-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-23 09:00 | 2025-03-26 11:00
C-56-HC01-CMA28-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 | NDT (Tie-in Joint) | C-56-HC01-CMA28-1030 | C-56-HC01-CMA28-1030: SS 1 | C-56-HC01-CMA28-1050 | C-56-HC01-CMA28-1050: SS 1 | 2025-03-25 07:00 | 2025-03-28 09:00
C-56-HC01-CMA28-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA28-1040 | C-56-HC01-CMA28-1040: SS 1 | C-56-HC01-CMA28-1060 | C-56-HC01-CMA28-1060: FS | 2025-03-26 11:00 | 2025-03-29 13:00
C-56-HC01-CMA28-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 | Holiday Testing | C-56-HC01-CMA28-1050 | C-56-HC01-CMA28-1050: FS | C-56-HC01-CMA28-1070 | C-56-HC01-CMA28-1070: FS | 2025-03-29 13:00 | 2025-04-03 13:00
C-56-HC01-CMA28-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 | Padding | C-56-HC01-CMA28-1060 | C-56-HC01-CMA28-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-03 13:00 | 2025-04-04 13:00
C-56-HC01-CMA29-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA28-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA28-1000: FS | C-56-HC01-CMA29-1010 | C-56-HC01-CMA29-1010: FF | 2025-03-23 09:00 | 2025-04-11 13:00
C-56-HC01-CMA29-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 | Bedding | C-56-HC01-CMA29-1000 | C-56-HC01-CMA29-1000: FF | C-56-HC01-CMA29-1020 | C-56-HC01-CMA29-1020: FS | 2025-04-10 13:00 | 2025-04-11 13:00
C-56-HC01-CMA29-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 | Lowering | C-56-HC01-CMA29-1010 | C-56-HC01-CMA29-1010: FS | C-56-HC01-CMA29-1030 | C-56-HC01-CMA29-1030: SS | 2025-04-11 13:00 | 2025-04-14 13:00
C-56-HC01-CMA29-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 | Section Tie-in Welding | C-56-HC01-CMA29-1020 | C-56-HC01-CMA29-1020: SS | C-56-HC01-CMA29-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA29-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-04-11 13:00 | 2025-04-18 13:00
C-56-HC01-CMA29-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 | NDT (Tie-in Joint) | C-56-HC01-CMA29-1030 | C-56-HC01-CMA29-1030: SS 1 | C-56-HC01-CMA29-1050 | C-56-HC01-CMA29-1050: SS 1 | 2025-04-12 13:00 | 2025-04-19 13:00
C-56-HC01-CMA29-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA29-1040 | C-56-HC01-CMA29-1040: SS 1 | C-56-HC01-CMA29-1060 | C-56-HC01-CMA29-1060: FS | 2025-04-14 13:00 | 2025-04-21 13:00
C-56-HC01-CMA29-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 | Holiday Testing | C-56-HC01-CMA29-1050 | C-56-HC01-CMA29-1050: FS | C-56-HC01-CMA29-1070 | C-56-HC01-CMA29-1070: FS | 2025-04-21 13:00 | 2025-04-22 13:00
C-56-HC01-CMA29-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 | Padding | C-56-HC01-CMA29-1060 | C-56-HC01-CMA29-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-22 13:00 | 2025-04-24 13:00
C-56-HC01-CMA27-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-PL-ME-2800 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-PL-ME-2800: SS | C-56-HC01-CMA27-1010, C-56-HC01-CMA28-1000 | C-56-HC01-CMA27-1010: FF, C-56-HC01-CMA28-1000: SS 7 | 2025-03-01 07:00 | 2025-03-23 09:00
C-56-HC01-CMA27-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 | Bedding | C-56-HC01-CMA27-1000 | C-56-HC01-CMA27-1000: FF | C-56-HC01-CMA27-1020 | C-56-HC01-CMA27-1020: FS | 2025-03-22 09:00 | 2025-03-23 09:00
C-56-HC01-CMA27-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 | Lowering | C-56-HC01-CMA27-1010 | C-56-HC01-CMA27-1010: FS | C-56-HC01-CMA27-1030 | C-56-HC01-CMA27-1030: SS | 2025-03-23 09:00 | 2025-03-26 11:00
C-56-HC01-CMA27-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 | Section Tie-in Welding | C-56-HC01-CMA27-1020 | C-56-HC01-CMA27-1020: SS | C-56-HC01-CMA27-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA27-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-23 09:00 | 2025-03-29 13:00
C-56-HC01-CMA27-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 | NDT (Tie-in Joint) | C-56-HC01-CMA27-1030 | C-56-HC01-CMA27-1030: SS 1 | C-56-HC01-CMA27-1050 | C-56-HC01-CMA27-1050: SS 1 | 2025-03-25 07:00 | 2025-04-03 13:00
C-56-HC01-CMA27-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA27-1040 | C-56-HC01-CMA27-1040: SS 1 | C-56-HC01-CMA27-1060 | C-56-HC01-CMA27-1060: FS | 2025-03-26 11:00 | 2025-04-04 13:00
C-56-HC01-CMA27-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 | Holiday Testing | C-56-HC01-CMA27-1050 | C-56-HC01-CMA27-1050: FS | C-56-HC01-CMA27-1070 | C-56-HC01-CMA27-1070: FS | 2025-04-04 13:00 | 2025-04-05 13:00
C-56-HC01-CMA27-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 | Padding | C-56-HC01-CMA27-1060 | C-56-HC01-CMA27-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-05 13:00 | 2025-04-08 13:00
C-56-HC01-CMA24-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-PL-ME-2800 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-PL-ME-2800: SS | C-56-HC01-CMA24-1010, C-56-HC01-CMA25-1000 | C-56-HC01-CMA24-1010: FF, C-56-HC01-CMA25-1000: FS | 2025-03-01 07:00 | 2025-03-12 13:00
C-56-HC01-CMA24-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 | Bedding | C-56-HC01-CMA24-1000 | C-56-HC01-CMA24-1000: FF | C-56-HC01-CMA24-1020 | C-56-HC01-CMA24-1020: FS | 2025-03-11 09:00 | 2025-03-12 13:00
C-56-HC01-CMA24-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 | Lowering | C-56-HC01-CMA24-1010 | C-56-HC01-CMA24-1010: FS | C-56-HC01-CMA24-1030 | C-56-HC01-CMA24-1030: SS | 2025-03-13 07:00 | 2025-03-14 11:00
C-56-HC01-CMA24-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 | Section Tie-in Welding | C-56-HC01-CMA24-1020 | C-56-HC01-CMA24-1020: SS | C-56-HC01-CMA24-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA24-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-13 07:00 | 2025-03-15 15:00
C-56-HC01-CMA24-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 | NDT (Tie-in Joint) | C-56-HC01-CMA24-1030 | C-56-HC01-CMA24-1030: SS 1 | C-56-HC01-CMA24-1050 | C-56-HC01-CMA24-1050: SS 1 | 2025-03-14 11:00 | 2025-03-17 09:00
C-56-HC01-CMA24-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA24-1040 | C-56-HC01-CMA24-1040: SS 1 | C-56-HC01-CMA24-1060 | C-56-HC01-CMA24-1060: FS | 2025-03-15 15:00 | 2025-03-18 13:00
C-56-HC01-CMA24-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 | Holiday Testing | C-56-HC01-CMA24-1050 | C-56-HC01-CMA24-1050: FS | C-56-HC01-CMA24-1070 | C-56-HC01-CMA24-1070: FS | 2025-03-19 07:00 | 2025-03-20 11:00
C-56-HC01-CMA24-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 | Padding | C-56-HC01-CMA24-1060 | C-56-HC01-CMA24-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-03-20 11:00 | 2025-03-22 09:00
C-56-HC01-CMA25-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA24-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA24-1000: FS | C-56-HC01-CMA25-1010, C-56-HC01-CMA26-1000 | C-56-HC01-CMA25-1010: FF, C-56-HC01-CMA26-1000: FS | 2025-03-13 07:00 | 2025-03-24 13:00
C-56-HC01-CMA25-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 | Bedding | C-56-HC01-CMA25-1000 | C-56-HC01-CMA25-1000: FF | C-56-HC01-CMA25-1020 | C-56-HC01-CMA25-1020: FS | 2025-03-23 09:00 | 2025-03-24 13:00
C-56-HC01-CMA25-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 | Lowering | C-56-HC01-CMA25-1010 | C-56-HC01-CMA25-1010: FS | C-56-HC01-CMA25-1030 | C-56-HC01-CMA25-1030: SS | 2025-03-25 07:00 | 2025-03-26 11:00
C-56-HC01-CMA25-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 | Section Tie-in Welding | C-56-HC01-CMA25-1020 | C-56-HC01-CMA25-1020: SS | C-56-HC01-CMA25-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA25-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-25 07:00 | 2025-03-28 09:00
C-56-HC01-CMA25-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 | NDT (Tie-in Joint) | C-56-HC01-CMA25-1030 | C-56-HC01-CMA25-1030: SS 1 | C-56-HC01-CMA25-1050 | C-56-HC01-CMA25-1050: SS 1 | 2025-03-26 11:00 | 2025-03-29 13:00
C-56-HC01-CMA25-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA25-1040 | C-56-HC01-CMA25-1040: SS 1 | C-56-HC01-CMA25-1060 | C-56-HC01-CMA25-1060: FS | 2025-03-28 09:00 | 2025-04-03 13:00
C-56-HC01-CMA25-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 | Holiday Testing | C-56-HC01-CMA25-1050 | C-56-HC01-CMA25-1050: FS | C-56-HC01-CMA25-1070 | C-56-HC01-CMA25-1070: FS | 2025-04-03 13:00 | 2025-04-04 13:00
C-56-HC01-CMA25-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 | Padding | C-56-HC01-CMA25-1060 | C-56-HC01-CMA25-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-04 13:00 | 2025-04-05 13:00
C-56-HC01-CMA26-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA25-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA25-1000: FS | C-56-HC01-CMA26-1010 | C-56-HC01-CMA26-1010: FF | 2025-03-25 07:00 | 2025-04-12 13:00
C-56-HC01-CMA26-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 | Bedding | C-56-HC01-CMA26-1000 | C-56-HC01-CMA26-1000: FF | C-56-HC01-CMA26-1020 | C-56-HC01-CMA26-1020: FS | 2025-04-10 13:00 | 2025-04-12 13:00
C-56-HC01-CMA26-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 | Lowering | C-56-HC01-CMA26-1010 | C-56-HC01-CMA26-1010: FS | C-56-HC01-CMA26-1030 | C-56-HC01-CMA26-1030: SS | 2025-04-12 13:00 | 2025-04-15 13:00
C-56-HC01-CMA26-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 | Section Tie-in Welding | C-56-HC01-CMA26-1020 | C-56-HC01-CMA26-1020: SS | C-56-HC01-CMA26-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA26-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-04-12 13:00 | 2025-04-17 13:00
C-56-HC01-CMA26-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 | NDT (Tie-in Joint) | C-56-HC01-CMA26-1030 | C-56-HC01-CMA26-1030: SS 1 | C-56-HC01-CMA26-1050 | C-56-HC01-CMA26-1050: SS 1 | 2025-04-14 13:00 | 2025-04-18 13:00
C-56-HC01-CMA26-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA26-1040 | C-56-HC01-CMA26-1040: SS 1 | C-56-HC01-CMA26-1060 | C-56-HC01-CMA26-1060: FS | 2025-04-15 13:00 | 2025-04-19 13:00
C-56-HC01-CMA26-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 | Holiday Testing | C-56-HC01-CMA26-1050 | C-56-HC01-CMA26-1050: FS | C-56-HC01-CMA26-1070 | C-56-HC01-CMA26-1070: FS | 2025-04-19 13:00 | 2025-04-21 13:00
C-56-HC01-CMA26-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 | Padding | C-56-HC01-CMA26-1060 | C-56-HC01-CMA26-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-21 13:00 | 2025-04-23 13:00
C-56-HC01-CMA17-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA16-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA16-1000: FS | C-56-HC01-CMA17-1010, C-56-HC01-CMA18-1000 | C-56-HC01-CMA17-1010: FF, C-56-HC01-CMA18-1000: FS | 2025-03-13 07:00 | 2025-03-24 13:00
C-56-HC01-CMA17-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 | Bedding | C-56-HC01-CMA17-1000 | C-56-HC01-CMA17-1000: FF | C-56-HC01-CMA17-1020 | C-56-HC01-CMA17-1020: FS | 2025-03-23 09:00 | 2025-03-24 13:00
C-56-HC01-CMA17-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 | Lowering | C-56-HC01-CMA17-1010 | C-56-HC01-CMA17-1010: FS | C-56-HC01-CMA17-1030 | C-56-HC01-CMA17-1030: SS | 2025-03-25 07:00 | 2025-03-26 11:00
C-56-HC01-CMA17-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 | Section Tie-in Welding | C-56-HC01-CMA17-1020 | C-56-HC01-CMA17-1020: SS | C-56-HC01-CMA17-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA17-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-25 07:00 | 2025-03-28 09:00
C-56-HC01-CMA17-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 | NDT (Tie-in Joint) | C-56-HC01-CMA17-1030 | C-56-HC01-CMA17-1030: SS 1 | C-56-HC01-CMA17-1050 | C-56-HC01-CMA17-1050: SS 1 | 2025-03-26 11:00 | 2025-03-29 13:00
C-56-HC01-CMA17-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA17-1040 | C-56-HC01-CMA17-1040: SS 1 | C-56-HC01-CMA17-1060 | C-56-HC01-CMA17-1060: FS | 2025-03-28 09:00 | 2025-04-03 13:00
C-56-HC01-CMA17-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 | Holiday Testing | C-56-HC01-CMA17-1050 | C-56-HC01-CMA17-1050: FS | C-56-HC01-CMA17-1070 | C-56-HC01-CMA17-1070: FS | 2025-04-03 13:00 | 2025-04-04 13:00
C-56-HC01-CMA17-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 | Padding | C-56-HC01-CMA17-1060 | C-56-HC01-CMA17-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-04 13:00 | 2025-04-05 13:00
C-56-HC01-CMA19-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA18-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA18-1000: FS | C-56-HC01-CMA19-1010 | C-56-HC01-CMA19-1010: FF | 2025-04-08 13:00 | 2025-04-17 13:00
C-56-HC01-CMA19-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 | Bedding | C-56-HC01-CMA19-1000 | C-56-HC01-CMA19-1000: FF | C-56-HC01-CMA19-1020 | C-56-HC01-CMA19-1020: FS | 2025-04-16 13:00 | 2025-04-17 13:00
C-56-HC01-CMA19-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 | Lowering | C-56-HC01-CMA19-1010 | C-56-HC01-CMA19-1010: FS | C-56-HC01-CMA19-1030 | C-56-HC01-CMA19-1030: SS | 2025-04-17 13:00 | 2025-04-18 13:00
C-56-HC01-CMA19-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 | Section Tie-in Welding | C-56-HC01-CMA19-1020 | C-56-HC01-CMA19-1020: SS | C-56-HC01-CMA19-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA19-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-04-17 13:00 | 2025-04-19 13:00
C-56-HC01-CMA19-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 | NDT (Tie-in Joint) | C-56-HC01-CMA19-1030 | C-56-HC01-CMA19-1030: SS 1 | C-56-HC01-CMA19-1050 | C-56-HC01-CMA19-1050: SS 1 | 2025-04-18 13:00 | 2025-04-21 13:00
C-56-HC01-CMA19-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA19-1040 | C-56-HC01-CMA19-1040: SS 1 | C-56-HC01-CMA19-1060 | C-56-HC01-CMA19-1060: FS | 2025-04-19 13:00 | 2025-04-22 13:00
C-56-HC01-CMA19-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 | Holiday Testing | C-56-HC01-CMA19-1050 | C-56-HC01-CMA19-1050: FS | C-56-HC01-CMA19-1070 | C-56-HC01-CMA19-1070: FS | 2025-04-22 13:00 | 2025-04-23 13:00
C-56-HC01-CMA19-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 | Padding | C-56-HC01-CMA19-1060 | C-56-HC01-CMA19-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-23 13:00 | 2025-04-24 13:00
C-56-HC01-CMA21-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA20-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA20-1000: FS | C-56-HC01-CMA21-1010, C-56-HC01-CMA22-1000 | C-56-HC01-CMA21-1010: FF, C-56-HC01-CMA22-1000: FS | 2025-03-20 11:00 | 2025-04-04 13:00
C-56-HC01-CMA21-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 | Bedding | C-56-HC01-CMA21-1000 | C-56-HC01-CMA21-1000: FF | C-56-HC01-CMA21-1020 | C-56-HC01-CMA21-1020: FS | 2025-04-03 13:00 | 2025-04-04 13:00
C-56-HC01-CMA21-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 | Lowering | C-56-HC01-CMA21-1010 | C-56-HC01-CMA21-1010: FS | C-56-HC01-CMA21-1030 | C-56-HC01-CMA21-1030: SS | 2025-04-04 13:00 | 2025-04-05 13:00
C-56-HC01-CMA21-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 | Section Tie-in Welding | C-56-HC01-CMA21-1020 | C-56-HC01-CMA21-1020: SS | C-56-HC01-CMA21-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA21-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-04-04 13:00 | 2025-04-07 13:00
C-56-HC01-CMA21-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 | NDT (Tie-in Joint) | C-56-HC01-CMA21-1030 | C-56-HC01-CMA21-1030: SS 1 | C-56-HC01-CMA21-1050 | C-56-HC01-CMA21-1050: SS 1 | 2025-04-05 13:00 | 2025-04-08 13:00
C-56-HC01-CMA21-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA21-1040 | C-56-HC01-CMA21-1040: SS 1 | C-56-HC01-CMA21-1060 | C-56-HC01-CMA21-1060: FS | 2025-04-07 13:00 | 2025-04-09 13:00
C-56-HC01-CMA21-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 | Holiday Testing | C-56-HC01-CMA21-1050 | C-56-HC01-CMA21-1050: FS | C-56-HC01-CMA21-1070 | C-56-HC01-CMA21-1070: FS | 2025-04-09 13:00 | 2025-04-10 13:00
C-56-HC01-CMA21-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 | Padding | C-56-HC01-CMA21-1060 | C-56-HC01-CMA21-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-10 13:00 | 2025-04-11 13:00
C-56-HC01-CMA30-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-PL-ME-2800 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-PL-ME-2800: SS | C-56-HC01-CMA30-1010, C-56-HC01-CMA31-1000 | C-56-HC01-CMA30-1010: FF, C-56-HC01-CMA31-1000: FS | 2025-03-01 07:00 | 2025-03-09 11:00
C-56-HC01-CMA30-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 | Bedding | C-56-HC01-CMA30-1000 | C-56-HC01-CMA30-1000: FF | C-56-HC01-CMA30-1020 | C-56-HC01-CMA30-1020: FS | 2025-03-08 11:00 | 2025-03-09 11:00
C-56-HC01-CMA30-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 | Lowering | C-56-HC01-CMA30-1010 | C-56-HC01-CMA30-1010: FS | C-56-HC01-CMA30-1030 | C-56-HC01-CMA30-1030: SS | 2025-03-09 11:00 | 2025-03-11 09:00
C-56-HC01-CMA30-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 | Section Tie-in Welding | C-56-HC01-CMA30-1020 | C-56-HC01-CMA30-1020: SS | C-56-HC01-CMA30-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA30-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-09 11:00 | 2025-03-12 13:00
C-56-HC01-CMA30-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 | NDT (Tie-in Joint) | C-56-HC01-CMA30-1030 | C-56-HC01-CMA30-1030: SS 1 | C-56-HC01-CMA30-1050 | C-56-HC01-CMA30-1050: SS 1 | 2025-03-11 09:00 | 2025-03-14 11:00
C-56-HC01-CMA30-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA30-1040 | C-56-HC01-CMA30-1040: SS 1 | C-56-HC01-CMA30-1060 | C-56-HC01-CMA30-1060: FS | 2025-03-13 07:00 | 2025-03-15 15:00
C-56-HC01-CMA30-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 | Holiday Testing | C-56-HC01-CMA30-1050 | C-56-HC01-CMA30-1050: FS | C-56-HC01-CMA30-1070 | C-56-HC01-CMA30-1070: FS | 2025-03-15 15:00 | 2025-03-17 09:00
C-56-HC01-CMA30-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 | Padding | C-56-HC01-CMA30-1060 | C-56-HC01-CMA30-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-03-17 09:00 | 2025-03-18 13:00
C-56-HC01-CMA08-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-PL-ME-2800 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-PL-ME-2800: SS | C-56-HC01-CMA08-1010, C-56-HC01-CMA12-1000 | C-56-HC01-CMA08-1010: FF, C-56-HC01-CMA12-1000: FS | 2025-03-01 07:00 | 2025-03-14 11:00
C-56-HC01-CMA08-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 | Bedding | C-56-HC01-CMA08-1000 | C-56-HC01-CMA08-1000: FF | C-56-HC01-CMA08-1020 | C-56-HC01-CMA08-1020: FS | 2025-03-13 07:00 | 2025-03-14 11:00
C-56-HC01-CMA08-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 | Lowering | C-56-HC01-CMA08-1010 | C-56-HC01-CMA08-1010: FS | C-56-HC01-CMA08-1030 | C-56-HC01-CMA08-1030: SS | 2025-03-14 11:00 | 2025-03-15 15:00
C-56-HC01-CMA08-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 | Section Tie-in Welding | C-56-HC01-CMA08-1020 | C-56-HC01-CMA08-1020: SS | C-56-HC01-CMA08-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA08-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-14 11:00 | 2025-03-17 09:00
C-56-HC01-CMA08-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 | NDT (Tie-in Joint) | C-56-HC01-CMA08-1030 | C-56-HC01-CMA08-1030: SS 1 | C-56-HC01-CMA08-1050 | C-56-HC01-CMA08-1050: SS 1 | 2025-03-15 15:00 | 2025-03-18 13:00
C-56-HC01-CMA08-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA08-1040 | C-56-HC01-CMA08-1040: SS 1 | C-56-HC01-CMA08-1060 | C-56-HC01-CMA08-1060: FS | 2025-03-17 09:00 | 2025-03-20 11:00
C-56-HC01-CMA08-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 | Holiday Testing | C-56-HC01-CMA08-1050 | C-56-HC01-CMA08-1050: FS | C-56-HC01-CMA08-1070 | C-56-HC01-CMA08-1070: FS | 2025-03-20 11:00 | 2025-03-22 09:00
C-56-HC01-CMA08-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 | Padding | C-56-HC01-CMA08-1060 | C-56-HC01-CMA08-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03, C-56-HC01-CMA12-1000 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS, C-56-HC01-CMA12-1000: FS | 2025-03-22 09:00 | 2025-03-23 09:00
C-56-HC01-CMA10-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA12-1000, C-56-HC01-CMA12-1070 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA12-1000: SS, C-56-HC01-CMA12-1070: FS | C-56-HC01-CMA10-1010, C-56-HC01-CMA15-1000 | C-56-HC01-CMA10-1010: FF, C-56-HC01-CMA15-1000: FS | 2025-04-18 13:00 | 2025-05-02 13:00
C-56-HC01-CMA10-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 | Bedding | C-56-HC01-CMA10-1000 | C-56-HC01-CMA10-1000: FF | C-56-HC01-CMA10-1020 | C-56-HC01-CMA10-1020: FS | 2025-05-01 13:00 | 2025-05-02 13:00
C-56-HC01-CMA10-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 | Lowering | C-56-HC01-CMA10-1010 | C-56-HC01-CMA10-1010: FS | C-56-HC01-CMA10-1030 | C-56-HC01-CMA10-1030: SS | 2025-05-02 13:00 | 2025-05-03 13:00
C-56-HC01-CMA10-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 | Section Tie-in Welding | C-56-HC01-CMA10-1020 | C-56-HC01-CMA10-1020: SS | C-56-HC01-CMA10-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA10-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-05-02 13:00 | 2025-05-08 10:00
C-56-HC01-CMA10-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 | NDT (Tie-in Joint) | C-56-HC01-CMA10-1030 | C-56-HC01-CMA10-1030: SS 1 | C-56-HC01-CMA10-1050 | C-56-HC01-CMA10-1050: SS 1 | 2025-05-03 13:00 | 2025-05-09 11:00
C-56-HC01-CMA10-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA10-1040 | C-56-HC01-CMA10-1040: SS 1 | C-56-HC01-CMA10-1060 | C-56-HC01-CMA10-1060: FS | 2025-05-05 14:00 | 2025-05-10 11:00
C-56-HC01-CMA10-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 | Holiday Testing | C-56-HC01-CMA10-1050 | C-56-HC01-CMA10-1050: FS | C-56-HC01-CMA10-1070 | C-56-HC01-CMA10-1070: FS | 2025-05-10 11:00 | 2025-05-13 11:00
C-56-HC01-CMA10-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 | Padding | C-56-HC01-CMA10-1060 | C-56-HC01-CMA10-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-05-13 11:00 | 2025-05-15 11:00
C-56-HC01-CMA31-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA30-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA30-1000: FS | C-56-HC01-CMA31-1010 | C-56-HC01-CMA31-1010: FF | 2025-03-09 11:00 | 2025-03-22 09:00
C-56-HC01-CMA31-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 | Bedding | C-56-HC01-CMA31-1000 | C-56-HC01-CMA31-1000: FF | C-56-HC01-CMA31-1020 | C-56-HC01-CMA31-1020: FS | 2025-03-20 11:00 | 2025-03-22 09:00
C-56-HC01-CMA31-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 | Lowering | C-56-HC01-CMA31-1010 | C-56-HC01-CMA31-1010: FS | C-56-HC01-CMA31-1030 | C-56-HC01-CMA31-1030: SS | 2025-03-22 09:00 | 2025-03-23 09:00
C-56-HC01-CMA31-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 | Section Tie-in Welding | C-56-HC01-CMA31-1020 | C-56-HC01-CMA31-1020: SS | C-56-HC01-CMA31-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA31-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-22 09:00 | 2025-03-24 13:00
C-56-HC01-CMA31-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 | NDT (Tie-in Joint) | C-56-HC01-CMA31-1030 | C-56-HC01-CMA31-1030: SS 1 | C-56-HC01-CMA31-1050 | C-56-HC01-CMA31-1050: SS 1 | 2025-03-23 09:00 | 2025-03-26 11:00
C-56-HC01-CMA31-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA31-1040 | C-56-HC01-CMA31-1040: SS 1 | C-56-HC01-CMA31-1060 | C-56-HC01-CMA31-1060: FS | 2025-03-25 07:00 | 2025-03-28 09:00
C-56-HC01-CMA31-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 | Holiday Testing | C-56-HC01-CMA31-1050 | C-56-HC01-CMA31-1050: FS | C-56-HC01-CMA31-1070 | C-56-HC01-CMA31-1070: FS | 2025-03-28 09:00 | 2025-03-29 13:00
C-56-HC01-CMA31-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 | Padding | C-56-HC01-CMA31-1060 | C-56-HC01-CMA31-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-03-29 13:00 | 2025-04-03 13:00
C-56-HC01-CMA05-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA06-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA06-1000: FS | C-56-HC01-CMA05-1010, C-56-HC01-CMA07-1000 | C-56-HC01-CMA05-1010: FF, C-56-HC01-CMA07-1000: FS | 2025-03-09 11:00 | 2025-03-18 13:00
C-56-HC01-CMA05-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 | Bedding | C-56-HC01-CMA05-1000 | C-56-HC01-CMA05-1000: FF | C-56-HC01-CMA05-1020 | C-56-HC01-CMA05-1020: FS | 2025-03-17 09:00 | 2025-03-18 13:00
C-56-HC01-CMA05-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 | Lowering | C-56-HC01-CMA05-1010 | C-56-HC01-CMA05-1010: FS | C-56-HC01-CMA05-1030 | C-56-HC01-CMA05-1030: SS | 2025-03-19 07:00 | 2025-03-20 11:00
C-56-HC01-CMA05-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 | Section Tie-in Welding | C-56-HC01-CMA05-1020 | C-56-HC01-CMA05-1020: SS | C-56-HC01-CMA05-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA05-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-19 07:00 | 2025-03-22 09:00
C-56-HC01-CMA05-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 | NDT (Tie-in Joint) | C-56-HC01-CMA05-1030 | C-56-HC01-CMA05-1030: SS 1 | C-56-HC01-CMA05-1050 | C-56-HC01-CMA05-1050: SS 1 | 2025-03-20 11:00 | 2025-03-23 09:00
C-56-HC01-CMA05-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA05-1040 | C-56-HC01-CMA05-1040: SS 1 | C-56-HC01-CMA05-1060 | C-56-HC01-CMA05-1060: FS | 2025-03-22 09:00 | 2025-03-24 13:00
C-56-HC01-CMA05-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 | Holiday Testing | C-56-HC01-CMA05-1050 | C-56-HC01-CMA05-1050: FS | C-56-HC01-CMA05-1070 | C-56-HC01-CMA05-1070: FS | 2025-03-25 07:00 | 2025-03-26 11:00
C-56-HC01-CMA05-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 | Padding | C-56-HC01-CMA05-1060 | C-56-HC01-CMA05-1060: FS | C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-03-26 11:00 | 2025-03-28 09:00
C-56-HC01-CMA12-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA08-1000, C-56-HC01-CMA08-1070 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA08-1000: FS, C-56-HC01-CMA08-1070: FS | C-56-HC01-CMA12-1010, C-56-HC01-CMA10-1000 | C-56-HC01-CMA12-1010: FF, C-56-HC01-CMA10-1000: SS | 2025-03-23 09:00 | 2025-04-11 13:00
C-56-HC01-CMA12-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 | Bedding | C-56-HC01-CMA12-1000 | C-56-HC01-CMA12-1000: FF | C-56-HC01-CMA12-1020 | C-56-HC01-CMA12-1020: FS | 2025-04-10 13:00 | 2025-04-11 13:00
C-56-HC01-CMA12-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 | Lowering | C-56-HC01-CMA12-1010 | C-56-HC01-CMA12-1010: FS | C-56-HC01-CMA12-1030 | C-56-HC01-CMA12-1030: SS | 2025-04-11 13:00 | 2025-04-12 13:00
C-56-HC01-CMA12-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 | Section Tie-in Welding | C-56-HC01-CMA12-1020 | C-56-HC01-CMA12-1020: SS | C-56-HC01-CMA12-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA12-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-04-11 13:00 | 2025-04-14 13:00
C-56-HC01-CMA12-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 | NDT (Tie-in Joint) | C-56-HC01-CMA12-1030 | C-56-HC01-CMA12-1030: SS 1 | C-56-HC01-CMA12-1050 | C-56-HC01-CMA12-1050: SS 1 | 2025-04-12 13:00 | 2025-04-15 13:00
C-56-HC01-CMA12-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA12-1040 | C-56-HC01-CMA12-1040: SS 1 | C-56-HC01-CMA12-1060 | C-56-HC01-CMA12-1060: FS | 2025-04-14 13:00 | 2025-04-16 13:00
C-56-HC01-CMA12-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 | Holiday Testing | C-56-HC01-CMA12-1050 | C-56-HC01-CMA12-1050: FS | C-56-HC01-CMA12-1070 | C-56-HC01-CMA12-1070: FS | 2025-04-16 13:00 | 2025-04-17 13:00
C-56-HC01-CMA12-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 | Padding | C-56-HC01-CMA12-1060 | C-56-HC01-CMA12-1060: FS | C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03, C-56-HC01-CMA10-1000 | C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS, C-56-HC01-CMA10-1000: FS | 2025-04-17 13:00 | 2025-04-18 13:00
C-56-HC01-CMA06-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA01-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA01-1000: SS | C-56-HC01-CMA06-1010, C-56-HC01-CMA05-1000 | C-56-HC01-CMA06-1010: FF, C-56-HC01-CMA05-1000: FS | 2025-03-01 07:00 | 2025-03-09 11:00
C-56-HC01-CMA06-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 | Bedding | C-56-HC01-CMA06-1000 | C-56-HC01-CMA06-1000: FF | C-56-HC01-CMA06-1020 | C-56-HC01-CMA06-1020: FS | 2025-03-08 11:00 | 2025-03-09 11:00
C-56-HC01-CMA06-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 | Lowering | C-56-HC01-CMA06-1010 | C-56-HC01-CMA06-1010: FS | C-56-HC01-CMA06-1030 | C-56-HC01-CMA06-1030: SS | 2025-03-09 11:00 | 2025-03-11 09:00
C-56-HC01-CMA06-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 | Section Tie-in Welding | C-56-HC01-CMA06-1020 | C-56-HC01-CMA06-1020: SS | C-56-HC01-CMA06-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA06-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-09 11:00 | 2025-03-12 13:00
C-56-HC01-CMA06-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 | NDT (Tie-in Joint) | C-56-HC01-CMA06-1030 | C-56-HC01-CMA06-1030: SS 1 | C-56-HC01-CMA06-1050 | C-56-HC01-CMA06-1050: SS 1 | 2025-03-11 09:00 | 2025-03-14 11:00
C-56-HC01-CMA06-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA06-1040 | C-56-HC01-CMA06-1040: SS 1 | C-56-HC01-CMA06-1060 | C-56-HC01-CMA06-1060: FS | 2025-03-13 07:00 | 2025-03-15 15:00
C-56-HC01-CMA06-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 | Holiday Testing | C-56-HC01-CMA06-1050 | C-56-HC01-CMA06-1050: FS | C-56-HC01-CMA06-1070 | C-56-HC01-CMA06-1070: FS | 2025-03-15 15:00 | 2025-03-17 09:00
C-56-HC01-CMA06-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 | Padding | C-56-HC01-CMA06-1060 | C-56-HC01-CMA06-1060: FS | C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-03-17 09:00 | 2025-03-18 13:00
C-56-HC01-CMA01-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 | Trench Excavation | HE-PL-2970, HE-PL-2910, C-56-HC01-PL-ME-2800 | HE-PL-2970: FS, HE-PL-2910: FS, C-56-HC01-PL-ME-2800: SS | C-56-HC01-CMA01-1010, C-56-HC01-CMA06-1000 | C-56-HC01-CMA01-1010: FF, C-56-HC01-CMA06-1000: SS | 2025-03-01 07:00 | 2025-03-12 13:00
C-56-HC01-CMA01-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 | Bedding | C-56-HC01-CMA01-1000 | C-56-HC01-CMA01-1000: FF | C-56-HC01-CMA01-1020 | C-56-HC01-CMA01-1020: FS | 2025-03-11 09:00 | 2025-03-12 13:00
C-56-HC01-CMA01-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 | Lowering | C-56-HC01-CMA01-1010 | C-56-HC01-CMA01-1010: FS | C-56-HC01-CMA01-1030 | C-56-HC01-CMA01-1030: SS | 2025-03-13 07:00 | 2025-03-14 11:00
C-56-HC01-CMA01-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 | Section Tie-in Welding | C-56-HC01-CMA01-1020 | C-56-HC01-CMA01-1020: SS | C-56-HC01-CMA01-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA01-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-13 07:00 | 2025-03-15 15:00
C-56-HC01-CMA01-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 | NDT (Tie-in Joint) | C-56-HC01-CMA01-1030 | C-56-HC01-CMA01-1030: SS 1 | C-56-HC01-CMA01-1050 | C-56-HC01-CMA01-1050: SS 1 | 2025-03-14 11:00 | 2025-03-17 09:00
C-56-HC01-CMA01-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA01-1040 | C-56-HC01-CMA01-1040: SS 1 | C-56-HC01-CMA01-1060 | C-56-HC01-CMA01-1060: FS | 2025-03-15 15:00 | 2025-03-18 13:00
C-56-HC01-CMA01-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 | Holiday Testing | C-56-HC01-CMA01-1050 | C-56-HC01-CMA01-1050: FS | C-56-HC01-CMA01-1070 | C-56-HC01-CMA01-1070: FS | 2025-03-19 07:00 | 2025-03-20 11:00
C-56-HC01-CMA01-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 | Padding | C-56-HC01-CMA01-1060 | C-56-HC01-CMA01-1060: FS | C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-03-20 11:00 | 2025-03-22 09:00
C-56-HC01-CMA07-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CMA05-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CMA05-1000: FS | C-56-HC01-CMA07-1010, C-56-HC01-CMA04-1000 | C-56-HC01-CMA07-1010: FF, C-56-HC01-CMA04-1000: FS | 2025-03-19 07:00 | 2025-03-28 09:00
C-56-HC01-CMA07-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 | Bedding | C-56-HC01-CMA07-1000 | C-56-HC01-CMA07-1000: FF | C-56-HC01-CMA07-1020 | C-56-HC01-CMA07-1020: FS | 2025-03-26 11:00 | 2025-03-28 09:00
C-56-HC01-CMA07-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 | Lowering | C-56-HC01-CMA07-1010 | C-56-HC01-CMA07-1010: FS | C-56-HC01-CMA07-1030 | C-56-HC01-CMA07-1030: SS | 2025-03-28 09:00 | 2025-03-29 13:00
C-56-HC01-CMA07-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 | Section Tie-in Welding | C-56-HC01-CMA07-1020 | C-56-HC01-CMA07-1020: SS | C-56-HC01-CMA07-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CMA07-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-03-28 09:00 | 2025-04-03 13:00
C-56-HC01-CMA07-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 | NDT (Tie-in Joint) | C-56-HC01-CMA07-1030 | C-56-HC01-CMA07-1030: SS 1 | C-56-HC01-CMA07-1050 | C-56-HC01-CMA07-1050: SS 1 | 2025-03-29 13:00 | 2025-04-04 13:00
C-56-HC01-CMA07-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA07-1040 | C-56-HC01-CMA07-1040: SS 1 | C-56-HC01-CMA07-1060 | C-56-HC01-CMA07-1060: FS | 2025-04-03 13:00 | 2025-04-05 13:00
C-56-HC01-CMA07-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 | Holiday Testing | C-56-HC01-CMA07-1050 | C-56-HC01-CMA07-1050: FS | C-56-HC01-CMA07-1070 | C-56-HC01-CMA07-1070: FS | 2025-04-05 13:00 | 2025-04-07 13:00
C-56-HC01-CMA07-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 | Padding | C-56-HC01-CMA07-1060 | C-56-HC01-CMA07-1060: FS | C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-04-07 13:00 | 2025-04-08 13:00
C-56-01HG-CME01-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-01HG-PL-ME-2800, C-52-0304-CME06-1250 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-01HG-PL-ME-2800: FS, C-52-0304-CME06-1250: FS | C-56-01HG-CME01-1010, C-56-01HG-CME02-1000 | C-56-01HG-CME01-1010: FS, C-56-01HG-CME02-1000: FS 1 | 2025-03-01 07:00 | 2025-03-03 11:00
C-56-01HG-CME01-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 | Bedding | C-56-01HG-CME01-1000 | C-56-01HG-CME01-1000: FS | C-56-01HG-CME01-1020 | C-56-01HG-CME01-1020: FS | 2025-03-03 11:00 | 2025-03-06 13:00
C-56-01HG-CME01-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 | Lowering | C-56-01HG-CME01-1010, C-56-01HG-PL-ME-2800, C-56-01HG-PL-ME-3000 | C-56-01HG-CME01-1010: FS, C-56-01HG-PL-ME-2800: SS 14, C-56-01HG-PL-ME-3000: SS 14 | C-56-01HG-CME01-1030 | C-56-01HG-CME01-1030: FS | 2025-03-07 07:00 | 2025-03-09 11:00
C-56-01HG-CME01-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 | Section Tie-in Welding | C-56-01HG-CME01-1020 | C-56-01HG-CME01-1020: FS | C-56-01HG-CME01-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CME01-1040: FS, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-03-09 11:00 | 2025-03-14 11:00
C-56-01HG-CME01-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 | NDT (Tie-in Joint) | C-56-01HG-CME01-1030 | C-56-01HG-CME01-1030: FS | C-56-01HG-CME01-1050 | C-56-01HG-CME01-1050: FS | 2025-03-14 11:00 | 2025-03-18 13:00
C-56-01HG-CME01-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME01-1040 | C-56-01HG-CME01-1040: FS | C-56-01HG-CME01-1060 | C-56-01HG-CME01-1060: FS | 2025-03-19 07:00 | 2025-03-23 09:00
C-56-01HG-CME01-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 | Holiday Testing | C-56-01HG-CME01-1050 | C-56-01HG-CME01-1050: FS | C-56-01HG-CME01-1070 | C-56-01HG-CME01-1070: FS | 2025-03-23 09:00 | 2025-03-26 11:00
C-56-01HG-CME01-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 | Padding & Back Filling | C-56-01HG-CME01-1060 | C-56-01HG-CME01-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-03-26 11:00 | 2025-03-29 13:00
C-56-01HG-CME02-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-01HG-CME01-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-01HG-CME01-1000: FS 1 | C-56-01HG-CME02-1010, C-56-01HG-CME03-1000 | C-56-01HG-CME02-1010: FS, C-56-01HG-CME03-1000: FS 1 | 2025-03-05 09:00 | 2025-03-08 11:00
C-56-01HG-CME02-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 | Bedding | C-56-01HG-CME02-1000 | C-56-01HG-CME02-1000: FS | C-56-01HG-CME02-1020 | C-56-01HG-CME02-1020: FS | 2025-03-08 11:00 | 2025-03-11 09:00
C-56-01HG-CME02-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 | Lowering | C-56-01HG-CME02-1010 | C-56-01HG-CME02-1010: FS | C-56-01HG-CME02-1030 | C-56-01HG-CME02-1030: FS | 2025-03-11 09:00 | 2025-03-14 11:00
C-56-01HG-CME02-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 | Section Tie-in Welding | C-56-01HG-CME02-1020 | C-56-01HG-CME02-1020: FS | C-56-01HG-CME02-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CME02-1040: FS, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-03-14 11:00 | 2025-03-18 13:00
C-56-01HG-CME02-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 | NDT (Tie-in Joint) | C-56-01HG-CME02-1030 | C-56-01HG-CME02-1030: FS | C-56-01HG-CME02-1050 | C-56-01HG-CME02-1050: FS | 2025-03-19 07:00 | 2025-03-23 09:00
C-56-01HG-CME02-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME02-1040 | C-56-01HG-CME02-1040: FS | C-56-01HG-CME02-1060 | C-56-01HG-CME02-1060: FS | 2025-03-23 09:00 | 2025-03-28 09:00
C-56-01HG-CME02-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 | Holiday Testing | C-56-01HG-CME02-1050 | C-56-01HG-CME02-1050: FS | C-56-01HG-CME02-1070 | C-56-01HG-CME02-1070: FS | 2025-03-28 09:00 | 2025-04-03 13:00
C-56-01HG-CME02-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 | Padding & Back Filling | C-56-01HG-CME02-1060 | C-56-01HG-CME02-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-03 13:00 | 2025-04-05 13:00
C-56-01HG-CME03-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-01HG-CME02-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-01HG-CME02-1000: FS 1 | C-56-01HG-CME03-1010, C-56-01HG-CME04-1000 | C-56-01HG-CME03-1010: FS, C-56-01HG-CME04-1000: FS 1 | 2025-03-09 11:00 | 2025-03-12 13:00
C-56-01HG-CME03-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 | Bedding | C-56-01HG-CME03-1000 | C-56-01HG-CME03-1000: FS | C-56-01HG-CME03-1020 | C-56-01HG-CME03-1020: FS | 2025-03-13 07:00 | 2025-03-15 15:00
C-56-01HG-CME03-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 | Lowering | C-56-01HG-CME03-1010 | C-56-01HG-CME03-1010: FS | C-56-01HG-CME03-1030 | C-56-01HG-CME03-1030: FS | 2025-03-15 15:00 | 2025-03-18 13:00
C-56-01HG-CME03-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 | Section Tie-in Welding | C-56-01HG-CME03-1020 | C-56-01HG-CME03-1020: FS | C-56-01HG-CME03-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CME03-1040: FS, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-03-19 07:00 | 2025-03-23 09:00
C-56-01HG-CME03-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 | NDT (Tie-in Joint) | C-56-01HG-CME03-1030 | C-56-01HG-CME03-1030: FS | C-56-01HG-CME03-1050 | C-56-01HG-CME03-1050: FS | 2025-03-23 09:00 | 2025-03-28 09:00
C-56-01HG-CME03-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME03-1040 | C-56-01HG-CME03-1040: FS | C-56-01HG-CME03-1060 | C-56-01HG-CME03-1060: FS | 2025-03-28 09:00 | 2025-04-04 13:00
C-56-01HG-CME03-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 | Holiday Testing | C-56-01HG-CME03-1050 | C-56-01HG-CME03-1050: FS | C-56-01HG-CME03-1070 | C-56-01HG-CME03-1070: FS | 2025-04-04 13:00 | 2025-04-07 13:00
C-56-01HG-CME03-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 | Padding & Back Filling | C-56-01HG-CME03-1060 | C-56-01HG-CME03-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-07 13:00 | 2025-04-09 13:00
C-56-01HG-CME04-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-01HG-CME03-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-01HG-CME03-1000: FS 1 | C-56-01HG-CME04-1010, C-56-01HG-CME05-1000 | C-56-01HG-CME04-1010: FS, C-56-01HG-CME05-1000: FS 1 | 2025-03-14 11:00 | 2025-03-17 09:00
C-56-01HG-CME04-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 | Bedding | C-56-01HG-CME04-1000 | C-56-01HG-CME04-1000: FS | C-56-01HG-CME04-1020 | C-56-01HG-CME04-1020: FS | 2025-03-17 09:00 | 2025-03-20 11:00
C-56-01HG-CME04-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 | Lowering | C-56-01HG-CME04-1010 | C-56-01HG-CME04-1010: FS | C-56-01HG-CME04-1030 | C-56-01HG-CME04-1030: FS | 2025-03-20 11:00 | 2025-03-23 09:00
C-56-01HG-CME04-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 | Section Tie-in Welding | C-56-01HG-CME04-1020 | C-56-01HG-CME04-1020: FS | C-56-01HG-CME04-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CME04-1040: FS, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-03-23 09:00 | 2025-03-28 09:00
C-56-01HG-CME04-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 | NDT (Tie-in Joint) | C-56-01HG-CME04-1030 | C-56-01HG-CME04-1030: FS | C-56-01HG-CME04-1050 | C-56-01HG-CME04-1050: FS | 2025-03-28 09:00 | 2025-04-04 13:00
C-56-01HG-CME04-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME04-1040 | C-56-01HG-CME04-1040: FS | C-56-01HG-CME04-1060 | C-56-01HG-CME04-1060: FS | 2025-04-04 13:00 | 2025-04-08 13:00
C-56-01HG-CME04-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 | Holiday Testing | C-56-01HG-CME04-1050 | C-56-01HG-CME04-1050: FS | C-56-01HG-CME04-1070 | C-56-01HG-CME04-1070: FS | 2025-04-08 13:00 | 2025-04-10 13:00
C-56-01HG-CME04-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 | Padding & Back Filling | C-56-01HG-CME04-1060 | C-56-01HG-CME04-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-10 13:00 | 2025-04-12 13:00
C-56-01HG-CME05-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-01HG-CME04-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-01HG-CME04-1000: FS 1 | C-56-01HG-CME05-1010, C-56-01HG-CME06-1000 | C-56-01HG-CME05-1010: FS, C-56-01HG-CME06-1000: FS 1 | 2025-03-19 07:00 | 2025-03-22 09:00
C-56-01HG-CME05-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 | Bedding | C-56-01HG-CME05-1000 | C-56-01HG-CME05-1000: FS | C-56-01HG-CME05-1020 | C-56-01HG-CME05-1020: FS | 2025-03-22 09:00 | 2025-03-24 13:00
C-56-01HG-CME05-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 | Lowering | C-56-01HG-CME05-1010 | C-56-01HG-CME05-1010: FS | C-56-01HG-CME05-1030 | C-56-01HG-CME05-1030: FS | 2025-03-25 07:00 | 2025-03-28 09:00
C-56-01HG-CME05-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 | Section Tie-in Welding | C-56-01HG-CME05-1020 | C-56-01HG-CME05-1020: FS | C-56-01HG-CME05-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CME05-1040: FS, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-03-28 09:00 | 2025-04-04 13:00
C-56-01HG-CME05-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 | NDT (Tie-in Joint) | C-56-01HG-CME05-1030 | C-56-01HG-CME05-1030: FS | C-56-01HG-CME05-1050 | C-56-01HG-CME05-1050: FS | 2025-04-04 13:00 | 2025-04-08 13:00
C-56-01HG-CME05-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME05-1040 | C-56-01HG-CME05-1040: FS | C-56-01HG-CME05-1060 | C-56-01HG-CME05-1060: FS | 2025-04-08 13:00 | 2025-04-11 13:00
C-56-01HG-CME05-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 | Holiday Testing | C-56-01HG-CME05-1050 | C-56-01HG-CME05-1050: FS | C-56-01HG-CME05-1070 | C-56-01HG-CME05-1070: FS | 2025-04-11 13:00 | 2025-04-14 13:00
C-56-01HG-CME05-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 | Padding & Back Filling | C-56-01HG-CME05-1060 | C-56-01HG-CME05-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-14 13:00 | 2025-04-16 13:00
C-56-01HG-CME06-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-01HG-CME05-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-01HG-CME05-1000: FS 1 | C-56-01HG-CME06-1010, C-56-01HG-CME07-1000 | C-56-01HG-CME06-1010: FS, C-56-01HG-CME07-1000: FS 1 | 2025-03-23 09:00 | 2025-03-26 11:00
C-56-01HG-CME06-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 | Bedding | C-56-01HG-CME06-1000 | C-56-01HG-CME06-1000: FS | C-56-01HG-CME06-1020 | C-56-01HG-CME06-1020: FS | 2025-03-26 11:00 | 2025-03-29 13:00
C-56-01HG-CME06-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 | Lowering | C-56-01HG-CME06-1010 | C-56-01HG-CME06-1010: FS | C-56-01HG-CME06-1030 | C-56-01HG-CME06-1030: FS | 2025-03-29 13:00 | 2025-04-04 13:00
C-56-01HG-CME06-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 | Section Tie-in Welding | C-56-01HG-CME06-1020 | C-56-01HG-CME06-1020: FS | C-56-01HG-CME06-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CME06-1040: FS, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-04 13:00 | 2025-04-08 13:00
C-56-01HG-CME06-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 | NDT (Tie-in Joint) | C-56-01HG-CME06-1030 | C-56-01HG-CME06-1030: FS | C-56-01HG-CME06-1050 | C-56-01HG-CME06-1050: FS | 2025-04-08 13:00 | 2025-04-11 13:00
C-56-01HG-CME06-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME06-1040 | C-56-01HG-CME06-1040: FS | C-56-01HG-CME06-1060 | C-56-01HG-CME06-1060: FS | 2025-04-11 13:00 | 2025-04-15 13:00
C-56-01HG-CME06-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 | Holiday Testing | C-56-01HG-CME06-1050 | C-56-01HG-CME06-1050: FS | C-56-01HG-CME06-1070 | C-56-01HG-CME06-1070: FS | 2025-04-15 13:00 | 2025-04-17 13:00
C-56-01HG-CME06-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 | Padding & Back Filling | C-56-01HG-CME06-1060 | C-56-01HG-CME06-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-17 13:00 | 2025-04-19 13:00
C-56-01HG-CME07-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-01HG-CME06-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-01HG-CME06-1000: FS 1 | C-56-01HG-CME07-1010, C-56-01HG-CME08-1000 | C-56-01HG-CME07-1010: FS, C-56-01HG-CME08-1000: FS 1 | 2025-03-28 09:00 | 2025-04-03 13:00
C-56-01HG-CME07-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 | Bedding | C-56-01HG-CME07-1000 | C-56-01HG-CME07-1000: FS | C-56-01HG-CME07-1020 | C-56-01HG-CME07-1020: FS | 2025-04-03 13:00 | 2025-04-05 13:00
C-56-01HG-CME07-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 | Lowering | C-56-01HG-CME07-1010 | C-56-01HG-CME07-1010: FS | C-56-01HG-CME07-1030 | C-56-01HG-CME07-1030: FS | 2025-04-05 13:00 | 2025-04-08 13:00
C-56-01HG-CME07-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 | Section Tie-in Welding | C-56-01HG-CME07-1020 | C-56-01HG-CME07-1020: FS | C-56-01HG-CME07-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CME07-1040: FS, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-08 13:00 | 2025-04-11 13:00
C-56-01HG-CME07-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 | NDT (Tie-in Joint) | C-56-01HG-CME07-1030 | C-56-01HG-CME07-1030: FS | C-56-01HG-CME07-1050 | C-56-01HG-CME07-1050: FS | 2025-04-11 13:00 | 2025-04-15 13:00
C-56-01HG-CME07-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME07-1040 | C-56-01HG-CME07-1040: FS | C-56-01HG-CME07-1060 | C-56-01HG-CME07-1060: FS | 2025-04-15 13:00 | 2025-04-18 13:00
C-56-01HG-CME07-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 | Holiday Testing | C-56-01HG-CME07-1050 | C-56-01HG-CME07-1050: FS | C-56-01HG-CME07-1070 | C-56-01HG-CME07-1070: FS | 2025-04-18 13:00 | 2025-04-21 13:00
C-56-01HG-CME07-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 | Padding & Back Filling | C-56-01HG-CME07-1060 | C-56-01HG-CME07-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-21 13:00 | 2025-04-23 13:00
C-56-01HG-CME08-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-01HG-CME07-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-01HG-CME07-1000: FS 1 | C-56-01HG-CME08-1010, C-56-01HG-CME09-1000 | C-56-01HG-CME08-1010: FS, C-56-01HG-CME09-1000: FS 1 | 2025-04-04 13:00 | 2025-04-07 13:00
C-56-01HG-CME08-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 | Bedding | C-56-01HG-CME08-1000 | C-56-01HG-CME08-1000: FS | C-56-01HG-CME08-1020 | C-56-01HG-CME08-1020: FS | 2025-04-07 13:00 | 2025-04-09 13:00
C-56-01HG-CME08-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 | Lowering | C-56-01HG-CME08-1010 | C-56-01HG-CME08-1010: FS | C-56-01HG-CME08-1030 | C-56-01HG-CME08-1030: FS | 2025-04-09 13:00 | 2025-04-11 13:00
C-56-01HG-CME08-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 | Section Tie-in Welding | C-56-01HG-CME08-1020 | C-56-01HG-CME08-1020: FS | C-56-01HG-CME08-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CME08-1040: FS, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-11 13:00 | 2025-04-15 13:00
C-56-01HG-CME08-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 | NDT (Tie-in Joint) | C-56-01HG-CME08-1030 | C-56-01HG-CME08-1030: FS | C-56-01HG-CME08-1050 | C-56-01HG-CME08-1050: FS | 2025-04-15 13:00 | 2025-04-18 13:00
C-56-01HG-CME08-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME08-1040 | C-56-01HG-CME08-1040: FS | C-56-01HG-CME08-1060 | C-56-01HG-CME08-1060: FS | 2025-04-18 13:00 | 2025-04-22 13:00
C-56-01HG-CME08-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 | Holiday Testing | C-56-01HG-CME08-1050 | C-56-01HG-CME08-1050: FS | C-56-01HG-CME08-1070 | C-56-01HG-CME08-1070: FS | 2025-04-22 13:00 | 2025-04-24 13:00
C-56-01HG-CME08-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 | Padding & Back Filling | C-56-01HG-CME08-1060 | C-56-01HG-CME08-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-24 13:00 | 2025-04-26 13:00
C-56-01HG-CME09-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-01HG-CME08-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-01HG-CME08-1000: FS 1 | C-56-01HG-CME09-1010, C-56-01HG-CME10-1000 | C-56-01HG-CME09-1010: FS, C-56-01HG-CME10-1000: FS 1 | 2025-04-08 13:00 | 2025-04-10 13:00
C-56-01HG-CME09-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 | Bedding | C-56-01HG-CME09-1000 | C-56-01HG-CME09-1000: FS | C-56-01HG-CME09-1020 | C-56-01HG-CME09-1020: FS | 2025-04-10 13:00 | 2025-04-12 13:00
C-56-01HG-CME09-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 | Lowering | C-56-01HG-CME09-1010 | C-56-01HG-CME09-1010: FS | C-56-01HG-CME09-1030 | C-56-01HG-CME09-1030: FS | 2025-04-12 13:00 | 2025-04-15 13:00
C-56-01HG-CME09-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 | Section Tie-in Welding | C-56-01HG-CME09-1020 | C-56-01HG-CME09-1020: FS | C-56-01HG-CME09-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CME09-1040: FS, C-56-01HG-PL-ME-4810: FF 1, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-15 13:00 | 2025-04-18 13:00
C-56-01HG-CME09-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 | NDT (Tie-in Joint) | C-56-01HG-CME09-1030 | C-56-01HG-CME09-1030: FS | C-56-01HG-CME09-1050 | C-56-01HG-CME09-1050: FS | 2025-04-18 13:00 | 2025-04-22 13:00
C-56-01HG-CME09-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME09-1040 | C-56-01HG-CME09-1040: FS | C-56-01HG-CME09-1060 | C-56-01HG-CME09-1060: FS | 2025-04-22 13:00 | 2025-04-25 13:00
C-56-01HG-CME09-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 | Holiday Testing | C-56-01HG-CME09-1050 | C-56-01HG-CME09-1050: FS | C-56-01HG-CME09-1070 | C-56-01HG-CME09-1070: FS | 2025-04-25 13:00 | 2025-04-28 13:00
C-56-01HG-CME09-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 | Padding & Back Filling | C-56-01HG-CME09-1060 | C-56-01HG-CME09-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-TE-8200, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-TE-8200: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 1, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-04-28 13:00 | 2025-04-30 13:00
C-56-01HG-CME10-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-01HG-CME09-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-01HG-CME09-1000: FS 1 | C-56-01HG-CME10-1010, C-56-01HG-CME09-1080, C-56-HC01-CME01-1000 | C-56-01HG-CME10-1010: FS, C-56-01HG-CME09-1080: FS 1, C-56-HC01-CME01-1000: FS 1 | 2025-04-11 13:00 | 2025-04-15 13:00
C-56-01HG-CME10-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 | Bedding | C-56-01HG-CME10-1000 | C-56-01HG-CME10-1000: FS | C-56-01HG-CME10-1020 | C-56-01HG-CME10-1020: FS | 2025-04-15 13:00 | 2025-04-17 13:00
C-56-01HG-CME10-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 | Lowering | C-56-01HG-CME10-1010 | C-56-01HG-CME10-1010: FS | C-56-01HG-CME10-1030 | C-56-01HG-CME10-1030: FS | 2025-04-17 13:00 | 2025-04-19 13:00
C-56-01HG-CME10-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 | Section Tie-in Welding | C-56-01HG-CME10-1020 | C-56-01HG-CME10-1020: FS | C-56-01HG-CME10-1040, C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010 | C-56-01HG-CME10-1040: FS, C-56-01HG-PL-ME-4810: FF, C-56-01HG-PL-ME-5010: FF 1 | 2025-04-19 13:00 | 2025-04-24 13:00
C-56-01HG-CME10-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 | NDT (Tie-in Joint) | C-56-01HG-CME10-1030 | C-56-01HG-CME10-1030: FS | C-56-01HG-CME10-1050 | C-56-01HG-CME10-1050: FS | 2025-04-24 13:00 | 2025-04-29 13:00
C-56-01HG-CME10-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME10-1040 | C-56-01HG-CME10-1040: FS | C-56-01HG-CME10-1060 | C-56-01HG-CME10-1060: FS | 2025-04-29 13:00 | 2025-05-03 13:00
C-56-01HG-CME10-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 | Holiday Testing | C-56-01HG-CME10-1050 | C-56-01HG-CME10-1050: FS | C-56-01HG-CME10-1070 | C-56-01HG-CME10-1070: FS | 2025-05-03 13:00 | 2025-05-06 16:00
C-56-01HG-CME10-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 | Padding & Back Filling | C-56-01HG-CME10-1060 | C-56-01HG-CME10-1060: FS | C-56-01HG-PL-CA-5220, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-6800, C-56-HC01-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8400, ML1579-E03 | C-56-01HG-PL-CA-5220: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-6800: FF 3, C-56-HC01-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-CI-7000: FF 1, C-56-01HG-PL-TE-8400: FF, ML1579-E03: FS | 2025-05-07 08:00 | 2025-05-09 11:00
C-56-HC01-CME01-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-PL-ME-2800, C-56-01HG-CME10-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-PL-ME-2800: SS, C-56-01HG-CME10-1000: FS 1 | C-56-HC01-CME01-1010, C-56-HC01-CME02-1000, C-56-01HG-CME09-1080 | C-56-HC01-CME01-1010: FS, C-56-HC01-CME02-1000: FS 1, C-56-01HG-CME09-1080: FS 1 | 2025-04-16 13:00 | 2025-04-18 13:00
C-56-HC01-CME01-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 | Bedding | C-56-HC01-CME01-1000 | C-56-HC01-CME01-1000: FS | C-56-HC01-CME01-1020 | C-56-HC01-CME01-1020: FS | 2025-04-18 13:00 | 2025-04-21 13:00
C-56-HC01-CME01-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 | Lowering | C-56-HC01-CME01-1010 | C-56-HC01-CME01-1010: FS | C-56-HC01-CME01-1030 | C-56-HC01-CME01-1030: FS | 2025-04-21 13:00 | 2025-04-23 13:00
C-56-HC01-CME01-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 | Section Tie-in Welding | C-56-HC01-CME01-1020 | C-56-HC01-CME01-1020: FS | C-56-HC01-CME01-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CME01-1040: FS, C-56-HC01-PL-ME-5010: FF 1 | 2025-04-23 13:00 | 2025-04-26 13:00
C-56-HC01-CME01-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 | NDT (Tie-in Joint) | C-56-HC01-CME01-1030 | C-56-HC01-CME01-1030: FS | C-56-HC01-CME01-1050 | C-56-HC01-CME01-1050: FS | 2025-04-26 13:00 | 2025-04-30 13:00
C-56-HC01-CME01-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME01-1040 | C-56-HC01-CME01-1040: FS | C-56-HC01-CME01-1060 | C-56-HC01-CME01-1060: FS | 2025-04-30 13:00 | 2025-05-03 13:00
C-56-HC01-CME01-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 | Holiday Testing | C-56-HC01-CME01-1050 | C-56-HC01-CME01-1050: FS | C-56-HC01-CME01-1070 | C-56-HC01-CME01-1070: FS | 2025-05-03 13:00 | 2025-05-06 16:00
C-56-HC01-CME01-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 | Padding & Back Filling | C-56-HC01-CME01-1060 | C-56-HC01-CME01-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-05-07 08:00 | 2025-05-09 11:00
C-56-HC01-CME02-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CME01-1000, C-56-01HG-CME09-1080 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CME01-1000: FS 1, C-56-01HG-CME09-1080: FS 1 | C-56-HC01-CME02-1010, C-56-HC01-CME03-1000 | C-56-HC01-CME02-1010: FS, C-56-HC01-CME03-1000: FS 1 | 2025-04-23 13:00 | 2025-04-28 13:00
C-56-HC01-CME02-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 | Bedding | C-56-HC01-CME02-1000 | C-56-HC01-CME02-1000: FS | C-56-HC01-CME02-1020 | C-56-HC01-CME02-1020: FS | 2025-04-28 13:00 | 2025-05-02 13:00
C-56-HC01-CME02-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 | Lowering | C-56-HC01-CME02-1010 | C-56-HC01-CME02-1010: FS | C-56-HC01-CME02-1030 | C-56-HC01-CME02-1030: FS | 2025-05-02 13:00 | 2025-05-08 10:00
C-56-HC01-CME02-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 | Section Tie-in Welding | C-56-HC01-CME02-1020 | C-56-HC01-CME02-1020: FS | C-56-HC01-CME02-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CME02-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-05-08 10:00 | 2025-05-14 11:00
C-56-HC01-CME02-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 | NDT (Tie-in Joint) | C-56-HC01-CME02-1030 | C-56-HC01-CME02-1030: SS 1 | C-56-HC01-CME02-1050 | C-56-HC01-CME02-1050: SS 1 | 2025-05-09 11:00 | 2025-05-15 11:00
C-56-HC01-CME02-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME02-1040 | C-56-HC01-CME02-1040: SS 1 | C-56-HC01-CME02-1060 | C-56-HC01-CME02-1060: FS | 2025-05-10 11:00 | 2025-05-16 11:00
C-56-HC01-CME02-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 | Holiday Testing | C-56-HC01-CME02-1050 | C-56-HC01-CME02-1050: FS | C-56-HC01-CME02-1070 | C-56-HC01-CME02-1070: FS | 2025-05-16 11:00 | 2025-05-19 11:00
C-56-HC01-CME02-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 | Padding & Back Filling | C-56-HC01-CME02-1060 | C-56-HC01-CME02-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-05-19 11:00 | 2025-05-21 11:00
C-56-HC01-CME03-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CME02-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CME02-1000: FS 1 | C-56-HC01-CME03-1010, C-56-HC01-CME04-1000 | C-56-HC01-CME03-1010: FS, C-56-HC01-CME04-1000: FS 1 | 2025-04-29 13:00 | 2025-05-01 13:00
C-56-HC01-CME03-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 | Bedding | C-56-HC01-CME03-1000 | C-56-HC01-CME03-1000: FS | C-56-HC01-CME03-1020 | C-56-HC01-CME03-1020: FS | 2025-05-01 13:00 | 2025-05-03 13:00
C-56-HC01-CME03-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 | Lowering | C-56-HC01-CME03-1010 | C-56-HC01-CME03-1010: FS | C-56-HC01-CME03-1030 | C-56-HC01-CME03-1030: FS | 2025-05-03 13:00 | 2025-05-06 16:00
C-56-HC01-CME03-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 | Section Tie-in Welding | C-56-HC01-CME03-1020 | C-56-HC01-CME03-1020: FS | C-56-HC01-CME03-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CME03-1040: FS, C-56-HC01-PL-ME-5010: FF 1 | 2025-05-07 08:00 | 2025-05-10 11:00
C-56-HC01-CME03-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 | NDT (Tie-in Joint) | C-56-HC01-CME03-1030 | C-56-HC01-CME03-1030: FS | C-56-HC01-CME03-1050 | C-56-HC01-CME03-1050: FS | 2025-05-10 11:00 | 2025-05-14 11:00
C-56-HC01-CME03-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME03-1040 | C-56-HC01-CME03-1040: FS | C-56-HC01-CME03-1060 | C-56-HC01-CME03-1060: FS | 2025-05-14 11:00 | 2025-05-17 11:00
C-56-HC01-CME03-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 | Holiday Testing | C-56-HC01-CME03-1050 | C-56-HC01-CME03-1050: FS | C-56-HC01-CME03-1070 | C-56-HC01-CME03-1070: FS | 2025-05-17 11:00 | 2025-05-20 11:00
C-56-HC01-CME03-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 | Padding & Back Filling | C-56-HC01-CME03-1060 | C-56-HC01-CME03-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-05-20 11:00 | 2025-05-22 11:00
C-56-HC01-CME04-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CME03-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CME03-1000: FS 1 | C-56-HC01-CME04-1010, C-56-HC01-CME05-1000 | C-56-HC01-CME04-1010: FS, C-56-HC01-CME05-1000: FS 1 | 2025-05-02 13:00 | 2025-05-05 14:00
C-56-HC01-CME04-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 | Bedding | C-56-HC01-CME04-1000 | C-56-HC01-CME04-1000: FS | C-56-HC01-CME04-1020 | C-56-HC01-CME04-1020: FS | 2025-05-05 14:00 | 2025-05-08 10:00
C-56-HC01-CME04-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 | Lowering | C-56-HC01-CME04-1010 | C-56-HC01-CME04-1010: FS | C-56-HC01-CME04-1030 | C-56-HC01-CME04-1030: FS | 2025-05-08 10:00 | 2025-05-10 11:00
C-56-HC01-CME04-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 | Section Tie-in Welding | C-56-HC01-CME04-1020 | C-56-HC01-CME04-1020: FS | C-56-HC01-CME04-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CME04-1040: FS, C-56-HC01-PL-ME-5010: FF 1 | 2025-05-10 11:00 | 2025-05-14 11:00
C-56-HC01-CME04-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 | NDT (Tie-in Joint) | C-56-HC01-CME04-1030 | C-56-HC01-CME04-1030: FS | C-56-HC01-CME04-1050 | C-56-HC01-CME04-1050: FS | 2025-05-14 11:00 | 2025-05-17 11:00
C-56-HC01-CME04-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME04-1040 | C-56-HC01-CME04-1040: FS | C-56-HC01-CME04-1060 | C-56-HC01-CME04-1060: FS | 2025-05-17 11:00 | 2025-05-21 11:00
C-56-HC01-CME04-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 | Holiday Testing | C-56-HC01-CME04-1050 | C-56-HC01-CME04-1050: FS | C-56-HC01-CME04-1070 | C-56-HC01-CME04-1070: FS | 2025-05-21 11:00 | 2025-05-23 11:00
C-56-HC01-CME04-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 | Padding & Back Filling | C-56-HC01-CME04-1060 | C-56-HC01-CME04-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-05-23 11:00 | 2025-05-26 11:00
C-56-HC01-CME05-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CME04-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CME04-1000: FS 1 | C-56-HC01-CME05-1010, C-56-HC01-CME06-1000 | C-56-HC01-CME05-1010: FS, C-56-HC01-CME06-1000: FS 1 | 2025-05-07 08:00 | 2025-05-09 11:00
C-56-HC01-CME05-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 | Bedding | C-56-HC01-CME05-1000 | C-56-HC01-CME05-1000: FS | C-56-HC01-CME05-1020 | C-56-HC01-CME05-1020: FS | 2025-05-09 11:00 | 2025-05-12 11:00
C-56-HC01-CME05-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 | Lowering | C-56-HC01-CME05-1010 | C-56-HC01-CME05-1010: FS | C-56-HC01-CME05-1030 | C-56-HC01-CME05-1030: FS | 2025-05-12 11:00 | 2025-05-14 11:00
C-56-HC01-CME05-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 | Section Tie-in Welding | C-56-HC01-CME05-1020 | C-56-HC01-CME05-1020: FS | C-56-HC01-CME05-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CME05-1040: FS, C-56-HC01-PL-ME-5010: FF 1 | 2025-05-14 11:00 | 2025-05-17 11:00
C-56-HC01-CME05-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 | NDT (Tie-in Joint) | C-56-HC01-CME05-1030 | C-56-HC01-CME05-1030: FS | C-56-HC01-CME05-1050 | C-56-HC01-CME05-1050: FS | 2025-05-17 11:00 | 2025-05-21 11:00
C-56-HC01-CME05-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME05-1040 | C-56-HC01-CME05-1040: FS | C-56-HC01-CME05-1060 | C-56-HC01-CME05-1060: FS | 2025-05-21 11:00 | 2025-05-24 11:00
C-56-HC01-CME05-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 | Holiday Testing | C-56-HC01-CME05-1050 | C-56-HC01-CME05-1050: FS | C-56-HC01-CME05-1070 | C-56-HC01-CME05-1070: FS | 2025-05-24 11:00 | 2025-05-27 11:00
C-56-HC01-CME05-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 | Padding & Back Filling | C-56-HC01-CME05-1060 | C-56-HC01-CME05-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-05-27 11:00 | 2025-05-29 11:00
C-56-HC01-CME06-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CME05-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CME05-1000: FS 1 | C-56-HC01-CME06-1010, C-56-HC01-CME07-1000, C-56-HC01-CME12-1000 | C-56-HC01-CME06-1010: FS, C-56-HC01-CME07-1000: FS 1, C-56-HC01-CME12-1000: FS | 2025-05-10 11:00 | 2025-05-13 11:00
C-56-HC01-CME06-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 | Bedding | C-56-HC01-CME06-1000 | C-56-HC01-CME06-1000: FS | C-56-HC01-CME06-1020 | C-56-HC01-CME06-1020: FS | 2025-05-13 11:00 | 2025-05-15 11:00
C-56-HC01-CME06-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 | Lowering | C-56-HC01-CME06-1010 | C-56-HC01-CME06-1010: FS | C-56-HC01-CME06-1030 | C-56-HC01-CME06-1030: FS | 2025-05-15 11:00 | 2025-05-17 11:00
C-56-HC01-CME06-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 | Section Tie-in Welding | C-56-HC01-CME06-1020 | C-56-HC01-CME06-1020: FS | C-56-HC01-CME06-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CME06-1040: FS, C-56-HC01-PL-ME-5010: FF 1 | 2025-05-17 11:00 | 2025-05-21 11:00
C-56-HC01-CME06-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 | NDT (Tie-in Joint) | C-56-HC01-CME06-1030 | C-56-HC01-CME06-1030: FS | C-56-HC01-CME06-1050 | C-56-HC01-CME06-1050: FS | 2025-05-21 11:00 | 2025-05-24 11:00
C-56-HC01-CME06-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME06-1040 | C-56-HC01-CME06-1040: FS | C-56-HC01-CME06-1060 | C-56-HC01-CME06-1060: FS | 2025-05-24 11:00 | 2025-05-28 11:00
C-56-HC01-CME06-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 | Holiday Testing | C-56-HC01-CME06-1050 | C-56-HC01-CME06-1050: FS | C-56-HC01-CME06-1070 | C-56-HC01-CME06-1070: FS | 2025-05-28 11:00 | 2025-05-30 11:00
C-56-HC01-CME06-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 | Padding & Back Filling | C-56-HC01-CME06-1060 | C-56-HC01-CME06-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-05-30 11:00 | 2025-06-02 11:00
C-56-HC01-CME07-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CME06-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CME06-1000: FS 1 | C-56-HC01-CME07-1010, C-56-HC01-CME08-1000 | C-56-HC01-CME07-1010: FS, C-56-HC01-CME08-1000: FS 1 | 2025-05-14 11:00 | 2025-05-16 11:00
C-56-HC01-CME07-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 | Bedding | C-56-HC01-CME07-1000 | C-56-HC01-CME07-1000: FS | C-56-HC01-CME07-1020 | C-56-HC01-CME07-1020: FS | 2025-05-16 11:00 | 2025-05-19 11:00
C-56-HC01-CME07-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 | Lowering | C-56-HC01-CME07-1010 | C-56-HC01-CME07-1010: FS | C-56-HC01-CME07-1030 | C-56-HC01-CME07-1030: FS | 2025-05-19 11:00 | 2025-05-21 11:00
C-56-HC01-CME07-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 | Section Tie-in Welding | C-56-HC01-CME07-1020 | C-56-HC01-CME07-1020: FS | C-56-HC01-CME07-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CME07-1040: FS, C-56-HC01-PL-ME-5010: FF 1 | 2025-05-21 11:00 | 2025-05-24 11:00
C-56-HC01-CME07-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 | NDT (Tie-in Joint) | C-56-HC01-CME07-1030 | C-56-HC01-CME07-1030: FS | C-56-HC01-CME07-1050 | C-56-HC01-CME07-1050: FS | 2025-05-24 11:00 | 2025-05-28 11:00
C-56-HC01-CME07-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME07-1040 | C-56-HC01-CME07-1040: FS | C-56-HC01-CME07-1060 | C-56-HC01-CME07-1060: FS | 2025-05-28 11:00 | 2025-05-31 11:00
C-56-HC01-CME07-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 | Holiday Testing | C-56-HC01-CME07-1050 | C-56-HC01-CME07-1050: FS | C-56-HC01-CME07-1070 | C-56-HC01-CME07-1070: FS | 2025-05-31 11:00 | 2025-06-03 11:00
C-56-HC01-CME07-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 | Padding & Back Filling | C-56-HC01-CME07-1060 | C-56-HC01-CME07-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-06-03 11:00 | 2025-06-07 11:00
C-56-HC01-CME08-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CME07-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CME07-1000: FS 1 | C-56-HC01-CME08-1010, C-56-HC01-CME09-1000 | C-56-HC01-CME08-1010: FS, C-56-HC01-CME09-1000: FS 1 | 2025-05-17 11:00 | 2025-05-22 11:00
C-56-HC01-CME08-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 | Bedding | C-56-HC01-CME08-1000 | C-56-HC01-CME08-1000: FS | C-56-HC01-CME08-1020 | C-56-HC01-CME08-1020: FS | 2025-05-22 11:00 | 2025-05-27 11:00
C-56-HC01-CME08-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 | Lowering | C-56-HC01-CME08-1010 | C-56-HC01-CME08-1010: FS | C-56-HC01-CME08-1030 | C-56-HC01-CME08-1030: SS 1 | 2025-05-27 11:00 | 2025-05-31 11:00
C-56-HC01-CME08-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 | Section Tie-in Welding | C-56-HC01-CME08-1020 | C-56-HC01-CME08-1020: SS 1 | C-56-HC01-CME08-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CME08-1040: SS 1, C-56-HC01-PL-ME-5010: FF 1 | 2025-05-28 11:00 | 2025-06-03 11:00
C-56-HC01-CME08-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 | NDT (Tie-in Joint) | C-56-HC01-CME08-1030 | C-56-HC01-CME08-1030: SS 1 | C-56-HC01-CME08-1050 | C-56-HC01-CME08-1050: SS 1 | 2025-05-29 11:00 | 2025-06-04 11:00
C-56-HC01-CME08-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME08-1040 | C-56-HC01-CME08-1040: SS 1 | C-56-HC01-CME08-1060 | C-56-HC01-CME08-1060: FS | 2025-05-30 11:00 | 2025-06-07 11:00
C-56-HC01-CME08-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 | Holiday Testing | C-56-HC01-CME08-1050 | C-56-HC01-CME08-1050: FS | C-56-HC01-CME08-1070 | C-56-HC01-CME08-1070: FS | 2025-06-07 11:00 | 2025-06-10 11:00
C-56-HC01-CME08-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 | Padding & Back Filling | C-56-HC01-CME08-1060 | C-56-HC01-CME08-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-06-10 11:00 | 2025-06-12 11:00
C-56-HC01-CME09-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CME08-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CME08-1000: FS 1 | C-56-HC01-CME09-1010, C-56-HC01-CME10-1000 | C-56-HC01-CME09-1010: FS, C-56-HC01-CME10-1000: FS 1 | 2025-05-23 11:00 | 2025-05-26 11:00
C-56-HC01-CME09-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 | Bedding | C-56-HC01-CME09-1000 | C-56-HC01-CME09-1000: FS | C-56-HC01-CME09-1020 | C-56-HC01-CME09-1020: FS | 2025-05-26 11:00 | 2025-05-28 11:00
C-56-HC01-CME09-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 | Lowering | C-56-HC01-CME09-1010 | C-56-HC01-CME09-1010: FS | C-56-HC01-CME09-1030 | C-56-HC01-CME09-1030: FS | 2025-05-28 11:00 | 2025-05-30 11:00
C-56-HC01-CME09-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 | Section Tie-in Welding | C-56-HC01-CME09-1020 | C-56-HC01-CME09-1020: FS | C-56-HC01-CME09-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CME09-1040: FS, C-56-HC01-PL-ME-5010: FF 1 | 2025-05-30 11:00 | 2025-06-03 11:00
C-56-HC01-CME09-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 | NDT (Tie-in Joint) | C-56-HC01-CME09-1030 | C-56-HC01-CME09-1030: FS | C-56-HC01-CME09-1050 | C-56-HC01-CME09-1050: FS | 2025-06-03 11:00 | 2025-06-09 11:00
C-56-HC01-CME09-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME09-1040 | C-56-HC01-CME09-1040: FS | C-56-HC01-CME09-1060 | C-56-HC01-CME09-1060: FS | 2025-06-09 11:00 | 2025-06-12 11:00
C-56-HC01-CME09-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 | Holiday Testing | C-56-HC01-CME09-1050 | C-56-HC01-CME09-1050: FS | C-56-HC01-CME09-1070 | C-56-HC01-CME09-1070: FS | 2025-06-12 11:00 | 2025-06-14 11:00
C-56-HC01-CME09-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 | Padding & Back Filling | C-56-HC01-CME09-1060 | C-56-HC01-CME09-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-06-14 11:00 | 2025-06-17 11:00
C-56-HC01-CME10-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CME09-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CME09-1000: FS 1 | C-56-HC01-CME10-1010, C-56-HC01-CME11-1000 | C-56-HC01-CME10-1010: FS, C-56-HC01-CME11-1000: FS 1 | 2025-05-27 11:00 | 2025-05-29 11:00
C-56-HC01-CME10-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 | Bedding | C-56-HC01-CME10-1000 | C-56-HC01-CME10-1000: FS | C-56-HC01-CME10-1020 | C-56-HC01-CME10-1020: FS | 2025-05-29 11:00 | 2025-05-31 11:00
C-56-HC01-CME10-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 | Lowering | C-56-HC01-CME10-1010 | C-56-HC01-CME10-1010: FS | C-56-HC01-CME10-1030 | C-56-HC01-CME10-1030: FS | 2025-05-31 11:00 | 2025-06-03 11:00
C-56-HC01-CME10-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 | Section Tie-in Welding | C-56-HC01-CME10-1020 | C-56-HC01-CME10-1020: FS | C-56-HC01-CME10-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CME10-1040: FS, C-56-HC01-PL-ME-5010: FF 1 | 2025-06-03 11:00 | 2025-06-09 11:00
C-56-HC01-CME10-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 | NDT (Tie-in Joint) | C-56-HC01-CME10-1030 | C-56-HC01-CME10-1030: FS | C-56-HC01-CME10-1050 | C-56-HC01-CME10-1050: FS | 2025-06-09 11:00 | 2025-06-12 11:00
C-56-HC01-CME10-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME10-1040 | C-56-HC01-CME10-1040: FS | C-56-HC01-CME10-1060 | C-56-HC01-CME10-1060: FS | 2025-06-12 11:00 | 2025-06-16 11:00
C-56-HC01-CME10-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 | Holiday Testing | C-56-HC01-CME10-1050 | C-56-HC01-CME10-1050: FS | C-56-HC01-CME10-1070 | C-56-HC01-CME10-1070: FS | 2025-06-16 11:00 | 2025-06-18 11:00
C-56-HC01-CME10-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 | Padding & Back Filling | C-56-HC01-CME10-1060 | C-56-HC01-CME10-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-06-18 11:00 | 2025-06-20 11:00
C-56-HC01-CME11-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CME10-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CME10-1000: FS 1 | C-56-HC01-CME11-1010 | C-56-HC01-CME11-1010: FS | 2025-05-30 11:00 | 2025-06-02 11:00
C-56-HC01-CME11-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 | Bedding | C-56-HC01-CME11-1000 | C-56-HC01-CME11-1000: FS | C-56-HC01-CME11-1020 | C-56-HC01-CME11-1020: FS | 2025-06-02 11:00 | 2025-06-04 11:00
C-56-HC01-CME11-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 | Lowering | C-56-HC01-CME11-1010 | C-56-HC01-CME11-1010: FS | C-56-HC01-CME11-1030 | C-56-HC01-CME11-1030: FS | 2025-06-04 11:00 | 2025-06-09 11:00
C-56-HC01-CME11-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 | Section Tie-in Welding | C-56-HC01-CME11-1020 | C-56-HC01-CME11-1020: FS | C-56-HC01-CME11-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CME11-1040: FS, C-56-HC01-PL-ME-5010: FF 1 | 2025-06-09 11:00 | 2025-06-12 11:00
C-56-HC01-CME11-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 | NDT (Tie-in Joint) | C-56-HC01-CME11-1030 | C-56-HC01-CME11-1030: FS | C-56-HC01-CME11-1050 | C-56-HC01-CME11-1050: FS | 2025-06-12 11:00 | 2025-06-16 11:00
C-56-HC01-CME11-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME11-1040 | C-56-HC01-CME11-1040: FS | C-56-HC01-CME11-1060 | C-56-HC01-CME11-1060: FS | 2025-06-16 11:00 | 2025-06-19 11:00
C-56-HC01-CME11-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 | Holiday Testing | C-56-HC01-CME11-1050 | C-56-HC01-CME11-1050: FS | C-56-HC01-CME11-1070 | C-56-HC01-CME11-1070: FS | 2025-06-19 11:00 | 2025-06-21 11:00
C-56-HC01-CME11-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 | Padding & Back Filling | C-56-HC01-CME11-1060 | C-56-HC01-CME11-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-06-21 11:00 | 2025-06-24 11:00
C-56-HC01-CME12-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CME06-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CME06-1000: FS | C-56-HC01-CME12-1010, C-56-HC01-CME13-1000 | C-56-HC01-CME12-1010: FS, C-56-HC01-CME13-1000: FS 1 | 2025-05-13 11:00 | 2025-05-15 11:00
C-56-HC01-CME12-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 | Bedding | C-56-HC01-CME12-1000 | C-56-HC01-CME12-1000: FS | C-56-HC01-CME12-1020 | C-56-HC01-CME12-1020: FS | 2025-05-15 11:00 | 2025-05-17 11:00
C-56-HC01-CME12-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 | Lowering | C-56-HC01-CME12-1010 | C-56-HC01-CME12-1010: FS | C-56-HC01-CME12-1030 | C-56-HC01-CME12-1030: FS | 2025-05-17 11:00 | 2025-05-20 11:00
C-56-HC01-CME12-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 | Section Tie-in Welding | C-56-HC01-CME12-1020 | C-56-HC01-CME12-1020: FS | C-56-HC01-CME12-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CME12-1040: FS, C-56-HC01-PL-ME-5010: FF 1 | 2025-05-20 11:00 | 2025-05-23 11:00
C-56-HC01-CME12-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 | NDT (Tie-in Joint) | C-56-HC01-CME12-1030 | C-56-HC01-CME12-1030: FS | C-56-HC01-CME12-1050 | C-56-HC01-CME12-1050: FS | 2025-05-23 11:00 | 2025-05-27 11:00
C-56-HC01-CME12-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME12-1040 | C-56-HC01-CME12-1040: FS | C-56-HC01-CME12-1060 | C-56-HC01-CME12-1060: FS | 2025-05-27 11:00 | 2025-05-30 11:00
C-56-HC01-CME12-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 | Holiday Testing | C-56-HC01-CME12-1050 | C-56-HC01-CME12-1050: FS | C-56-HC01-CME12-1070 | C-56-HC01-CME12-1070: FS | 2025-05-30 11:00 | 2025-06-02 11:00
C-56-HC01-CME12-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 | Padding & Back Filling | C-56-HC01-CME12-1060 | C-56-HC01-CME12-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-06-02 11:00 | 2025-06-04 11:00
C-56-HC01-CME13-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CME12-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CME12-1000: FS 1 | C-56-HC01-CME13-1010, C-56-HC01-CME14-1000 | C-56-HC01-CME13-1010: FS, C-56-HC01-CME14-1000: FS 1 | 2025-05-16 11:00 | 2025-05-19 11:00
C-56-HC01-CME13-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 | Bedding | C-56-HC01-CME13-1000 | C-56-HC01-CME13-1000: FS | C-56-HC01-CME13-1020 | C-56-HC01-CME13-1020: FS | 2025-05-19 11:00 | 2025-05-21 11:00
C-56-HC01-CME13-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 | Lowering | C-56-HC01-CME13-1010 | C-56-HC01-CME13-1010: FS | C-56-HC01-CME13-1030 | C-56-HC01-CME13-1030: FS | 2025-05-21 11:00 | 2025-05-23 11:00
C-56-HC01-CME13-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 | Section Tie-in Welding | C-56-HC01-CME13-1020 | C-56-HC01-CME13-1020: FS | C-56-HC01-CME13-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CME13-1040: FS, C-56-HC01-PL-ME-5010: FF 1 | 2025-05-23 11:00 | 2025-05-27 11:00
C-56-HC01-CME13-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 | NDT (Tie-in Joint) | C-56-HC01-CME13-1030 | C-56-HC01-CME13-1030: FS | C-56-HC01-CME13-1050 | C-56-HC01-CME13-1050: FS | 2025-05-27 11:00 | 2025-05-30 11:00
C-56-HC01-CME13-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME13-1040 | C-56-HC01-CME13-1040: FS | C-56-HC01-CME13-1060 | C-56-HC01-CME13-1060: FS | 2025-05-30 11:00 | 2025-06-03 11:00
C-56-HC01-CME13-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 | Holiday Testing | C-56-HC01-CME13-1050 | C-56-HC01-CME13-1050: FS | C-56-HC01-CME13-1070 | C-56-HC01-CME13-1070: FS | 2025-06-03 11:00 | 2025-06-07 11:00
C-56-HC01-CME13-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 | Padding & Back Filling | C-56-HC01-CME13-1060 | C-56-HC01-CME13-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-06-07 11:00 | 2025-06-10 11:00
C-56-HC01-CME14-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CME13-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CME13-1000: FS 1 | C-56-HC01-CME14-1010, C-56-HC01-CME15-1000 | C-56-HC01-CME14-1010: FS, C-56-HC01-CME15-1000: FS 1 | 2025-05-20 11:00 | 2025-05-22 11:00
C-56-HC01-CME14-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 | Bedding | C-56-HC01-CME14-1000 | C-56-HC01-CME14-1000: FS | C-56-HC01-CME14-1020 | C-56-HC01-CME14-1020: FS | 2025-05-22 11:00 | 2025-05-24 11:00
C-56-HC01-CME14-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 | Lowering | C-56-HC01-CME14-1010 | C-56-HC01-CME14-1010: FS | C-56-HC01-CME14-1030 | C-56-HC01-CME14-1030: FS | 2025-05-24 11:00 | 2025-05-27 11:00
C-56-HC01-CME14-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 | Section Tie-in Welding | C-56-HC01-CME14-1020 | C-56-HC01-CME14-1020: FS | C-56-HC01-CME14-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CME14-1040: FS, C-56-HC01-PL-ME-5010: FF 1 | 2025-05-27 11:00 | 2025-05-30 11:00
C-56-HC01-CME14-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 | NDT (Tie-in Joint) | C-56-HC01-CME14-1030 | C-56-HC01-CME14-1030: FS | C-56-HC01-CME14-1050 | C-56-HC01-CME14-1050: FS | 2025-05-30 11:00 | 2025-06-03 11:00
C-56-HC01-CME14-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME14-1040 | C-56-HC01-CME14-1040: FS | C-56-HC01-CME14-1060 | C-56-HC01-CME14-1060: FS | 2025-06-03 11:00 | 2025-06-09 11:00
C-56-HC01-CME14-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 | Holiday Testing | C-56-HC01-CME14-1050 | C-56-HC01-CME14-1050: FS | C-56-HC01-CME14-1070 | C-56-HC01-CME14-1070: FS | 2025-06-09 11:00 | 2025-06-11 11:00
C-56-HC01-CME14-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 | Padding & Back Filling | C-56-HC01-CME14-1060 | C-56-HC01-CME14-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-06-11 11:00 | 2025-06-13 11:00
C-56-HC01-CME15-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CME14-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CME14-1000: FS 1 | C-56-HC01-CME15-1010, C-56-HC01-CME16-1000 | C-56-HC01-CME15-1010: FS, C-56-HC01-CME16-1000: FS 1 | 2025-05-23 11:00 | 2025-05-26 11:00
C-56-HC01-CME15-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 | Bedding | C-56-HC01-CME15-1000 | C-56-HC01-CME15-1000: FS | C-56-HC01-CME15-1020 | C-56-HC01-CME15-1020: FS | 2025-05-26 11:00 | 2025-05-28 11:00
C-56-HC01-CME15-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 | Lowering | C-56-HC01-CME15-1010 | C-56-HC01-CME15-1010: FS | C-56-HC01-CME15-1030 | C-56-HC01-CME15-1030: FS | 2025-05-28 11:00 | 2025-05-30 11:00
C-56-HC01-CME15-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 | Section Tie-in Welding | C-56-HC01-CME15-1020 | C-56-HC01-CME15-1020: FS | C-56-HC01-CME15-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CME15-1040: FS, C-56-HC01-PL-ME-5010: FF 1 | 2025-05-30 11:00 | 2025-06-03 11:00
C-56-HC01-CME15-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 | NDT (Tie-in Joint) | C-56-HC01-CME15-1030 | C-56-HC01-CME15-1030: FS | C-56-HC01-CME15-1050 | C-56-HC01-CME15-1050: FS | 2025-06-03 11:00 | 2025-06-09 11:00
C-56-HC01-CME15-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME15-1040 | C-56-HC01-CME15-1040: FS | C-56-HC01-CME15-1060 | C-56-HC01-CME15-1060: FS | 2025-06-09 11:00 | 2025-06-12 11:00
C-56-HC01-CME15-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 | Holiday Testing | C-56-HC01-CME15-1050 | C-56-HC01-CME15-1050: FS | C-56-HC01-CME15-1070 | C-56-HC01-CME15-1070: FS | 2025-06-12 11:00 | 2025-06-14 11:00
C-56-HC01-CME15-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 | Padding & Back Filling | C-56-HC01-CME15-1060 | C-56-HC01-CME15-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-06-14 11:00 | 2025-06-17 11:00
C-56-HC01-CME16-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 | Trench Excavation | HE-PL-2910, HE-PL-2970, C-56-HC01-CME15-1000 | HE-PL-2910: FS, HE-PL-2970: FS, C-56-HC01-CME15-1000: FS 1 | C-56-HC01-CME16-1010, C-56-HC01-CME10-1090 | C-56-HC01-CME16-1010: FS, C-56-HC01-CME10-1090: FS 1 | 2025-05-27 11:00 | 2025-05-29 11:00
C-56-HC01-CME16-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 | Bedding | C-56-HC01-CME16-1000 | C-56-HC01-CME16-1000: FS | C-56-HC01-CME16-1020 | C-56-HC01-CME16-1020: FS | 2025-05-29 11:00 | 2025-05-31 11:00
C-56-HC01-CME16-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 | Lowering | C-56-HC01-CME16-1010 | C-56-HC01-CME16-1010: FS | C-56-HC01-CME16-1030 | C-56-HC01-CME16-1030: FS | 2025-05-31 11:00 | 2025-06-03 11:00
C-56-HC01-CME16-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 | Section Tie-in Welding | C-56-HC01-CME16-1020 | C-56-HC01-CME16-1020: FS | C-56-HC01-CME16-1040, C-56-HC01-PL-ME-5010 | C-56-HC01-CME16-1040: FS, C-56-HC01-PL-ME-5010: FF 1 | 2025-06-03 11:00 | 2025-06-09 11:00
C-56-HC01-CME16-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 | NDT (Tie-in Joint) | C-56-HC01-CME16-1030 | C-56-HC01-CME16-1030: FS | C-56-HC01-CME16-1050 | C-56-HC01-CME16-1050: FS | 2025-06-09 11:00 | 2025-06-12 11:00
C-56-HC01-CME16-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME16-1040 | C-56-HC01-CME16-1040: FS | C-56-HC01-CME16-1060 | C-56-HC01-CME16-1060: FS | 2025-06-12 11:00 | 2025-06-16 11:00
C-56-HC01-CME16-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 | Holiday Testing | C-56-HC01-CME16-1050 | C-56-HC01-CME16-1050: FS | C-56-HC01-CME16-1070 | C-56-HC01-CME16-1070: FS | 2025-06-16 11:00 | 2025-06-18 11:00
C-56-HC01-CME16-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 | Padding & Back Filling | C-56-HC01-CME16-1060 | C-56-HC01-CME16-1060: FS | C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-CI-6800: FF, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2025-06-18 11:00 | 2025-06-20 11:00
C-52-598-06-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.1 | Site Survey, Preparation & Grading Works | HE-SS-0030, ML1002, HE-CS-0170, HE-CS-0470, CTF-1000, CTF-1010, C-PER-1630 | HE-SS-0030: SS, ML1002: FS, HE-CS-0170: FS, HE-CS-0470: FS 3, CTF-1000: FS, CTF-1010: FS, C-PER-1630: FS 27 | C-52-598-06-CI-1010 | C-52-598-06-CI-1010: FS | 2025-01-04 07:00 | 2025-01-13 17:00
C-52-598-06-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.1 | Earth Works for Equipment Foundations & Hard Stand Area | C-52-598-06-CI-1000 | C-52-598-06-CI-1000: FS | C-52-598-06-CI-1020, C-52-598-06-CI-1200 | C-52-598-06-CI-1020: SS 7, C-52-598-06-CI-1200: FS | 2025-01-14 07:00 | 2025-01-29 17:00
C-52-598-06-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.1 | Earth Works for Pipe Support Foundations | C-52-598-06-CI-1010 | C-52-598-06-CI-1010: SS 7 | C-52-598-06-CI-1030, C-52-598-06-CI-1210, C-52-598-06-CI-1800 | C-52-598-06-CI-1030: SS 6, C-52-598-06-CI-1210: FS, C-52-598-06-CI-1800: FS | 2025-01-22 07:00 | 2025-02-06 17:00
C-52-598-06-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.1 | Earth Works for Field Instrument Foundations | C-52-598-06-CI-1020 | C-52-598-06-CI-1020: SS 6 | C-52-598-06-CI-1040, C-52-598-06-CI-1220 | C-52-598-06-CI-1040: SS 7, C-52-598-06-CI-1220: FS | 2025-01-29 07:00 | 2025-02-11 17:00
C-52-598-06-CI-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.1 | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-598-06-CI-1030 | C-52-598-06-CI-1030: SS 7 | C-52-598-06-CI-1050, C-52-598-06-CI-1230 | C-52-598-06-CI-1050: SS 6, C-52-598-06-CI-1230: FS | 2025-02-06 07:00 | 2025-02-21 17:00
C-52-598-06-CI-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.1 | Earth Works for Light Pole, Fence & Gates Foundation | C-52-598-06-CI-1040 | C-52-598-06-CI-1040: SS 6 | C-52-598-06-CI-1240 | C-52-598-06-CI-1240: FS | 2025-02-13 07:00 | 2025-02-26 17:00
C-52-598-06-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.2 | Compaction & Testing for Equipment Foundations & Hard Stand Area | C-52-598-06-CI-1010 | C-52-598-06-CI-1010: FS | C-52-598-06-CI-1400 | C-52-598-06-CI-1400: FS | 2025-01-30 07:00 | 2025-02-04 17:00
C-52-598-06-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.2 | Compaction & Testing for Pipe Support Foundations | C-52-598-06-CI-1020 | C-52-598-06-CI-1020: FS | C-52-598-06-CI-1600 | C-52-598-06-CI-1600: FS | 2025-02-07 07:00 | 2025-02-12 17:00
C-52-598-06-CI-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.2 | Compaction & Testing for Field Instrument Foundations | C-52-598-06-CI-1030 | C-52-598-06-CI-1030: FS | C-52-598-06-CI-1410 | C-52-598-06-CI-1410: FS | 2025-02-12 07:00 | 2025-02-17 17:00
C-52-598-06-CI-1230 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.2 | Compaction & Testing for Access Platform & Misc. Structural Foundations | C-52-598-06-CI-1040 | C-52-598-06-CI-1040: FS | C-52-598-06-CI-1420 | C-52-598-06-CI-1420: FS | 2025-02-22 07:00 | 2025-02-27 17:00
C-52-598-06-CI-1240 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.2 | Compaction & Testing for Light Pole, Fence & Gates Foundation | C-52-598-06-CI-1050 | C-52-598-06-CI-1050: FS | C-52-598-06-CI-1430 | C-52-598-06-CI-1430: FS | 2025-02-27 07:00 | 2025-03-05 09:00
C-52-598-06-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.3 | Concrete Works for Equipment Foundations & Hard Stand Area | C-52-598-06-CI-1200, HE-HS-0410, HE-CS-1190, HE-HS-0290, HE-CS-0230, HE-CS-0890, HE-CS-1310, ML1034-B25, HM-CS-0040 | C-52-598-06-CI-1200: FS, HE-HS-0410: FS, HE-CS-1190: FS, HE-HS-0290: FS, HE-CS-0230: FS, HE-CS-0890: FS, HE-CS-1310: FS, ML1034-B25: FS, HM-CS-0040: FS | C-52-598-06-CI-2400, C-52-598-06-EI-1000 | C-52-598-06-CI-2400: FS, C-52-598-06-EI-1000: FS | 2025-02-05 07:00 | 2025-02-28 17:00
C-52-598-06-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.4 | Concrete Works for Pipe Support Foundations | C-52-598-06-CI-1210 | C-52-598-06-CI-1210: FS | C-52-598-06-CI-2000 | C-52-598-06-CI-2000: FS | 2025-02-13 07:00 | 2025-03-11 09:00
C-52-598-06-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.3 | Concrete Works for Field Instrument, JB Foundations | C-52-598-06-CI-1220, HE-HS-0410, HE-HS-0290, HE-CS-0230, ML1034-B25, HM-CS-0040 | C-52-598-06-CI-1220: FS, HE-HS-0410: FS, HE-HS-0290: FS, HE-CS-0230: FS, ML1034-B25: FS, HM-CS-0040: FS | C-52-598-06-EI-1210, C-52-598-06-EI-2210 | C-52-598-06-EI-1210: FS, C-52-598-06-EI-2210: FS | 2025-02-18 07:00 | 2025-03-06 13:00
C-52-598-06-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.3 | Concrete Works for Access Platform & Misc. Structural Foundations | C-52-598-06-CI-1230, HE-HS-0410, HE-HS-0290, HE-CS-0230, ML1034-B25, HE-CS-1370, HM-CS-0040, C-52-598-05-CI-1420 | C-52-598-06-CI-1230: FS, HE-HS-0410: FS, HE-HS-0290: FS, HE-CS-0230: FS, ML1034-B25: FS, HE-CS-1370: FS, HM-CS-0040: FS, C-52-598-05-CI-1420: FS | C-52-598-06-CI-3000 | C-52-598-06-CI-3000: FS | 2025-03-01 07:00 | 2025-03-18 13:00
C-52-598-06-CI-1430 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.3 | Concrete Works for Light Pole, Fence & Gates Foundation | C-52-598-06-CI-1240, HE-HS-0410, HE-HS-0290, HE-CS-0230, ML1034-B25, HE-CS-1010, HM-CS-0040 | C-52-598-06-CI-1240: FS, HE-HS-0410: FS, HE-HS-0290: FS, HE-CS-0230: FS, ML1034-B25: FS, HE-CS-1010: FS, HM-CS-0040: FS | C-52-598-06-CI-2200, C-52-598-06-EI-1800 | C-52-598-06-CI-2200: FS, C-52-598-06-EI-1800: FS | 2025-03-05 09:00 | 2025-04-08 13:00
C-52-598-06-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.5 | Electrical & Earthing Cable Trenching | C-52-598-06-CI-1020, HE-CS-0530 | C-52-598-06-CI-1020: FS, HE-CS-0530: FS | C-52-598-06-EI-2000, C-52-598-06-CI-1810 | C-52-598-06-EI-2000: FS, C-52-598-06-CI-1810: FS | 2025-02-07 07:00 | 2025-03-17 09:00
C-52-598-06-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.5 | Instrument & Telecom Cable Trenching | HE-CS-0530, C-52-598-06-CI-1800 | HE-CS-0530: FS, C-52-598-06-CI-1800: FS | C-52-598-06-EI-2010 | C-52-598-06-EI-2010: FS | 2025-03-17 09:00 | 2025-04-17 13:00
C-52-598-06-CI-2200 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.8 | Installation of Concrete Pillers for Boundary Wall | C-52-598-06-CI-1430, HE-CS-0350, HE-CS-0470 | C-52-598-06-CI-1430: FS, HE-CS-0350: FS, HE-CS-0470: FS | C-52-598-06-CI-2210 | C-52-598-06-CI-2210: SS 7 | 2025-04-08 13:00 | 2025-05-02 13:00
C-52-598-06-CI-2210 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.8 | Block Works for Boundary Wall | C-52-598-06-CI-2200 | C-52-598-06-CI-2200: SS 7 | C-52-598-06-CI-2220 | C-52-598-06-CI-2220: FS | 2025-04-16 13:00 | 2025-05-12 11:00
C-52-598-06-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.8 | Installation of Fence Post & Mesh Works (Type-4 & 3) | C-52-598-06-CI-2210 | C-52-598-06-CI-2210: FS | C-52-598-06-CI-2230, PRECOM-52-59806-1000 | C-52-598-06-CI-2230: FS, PRECOM-52-59806-1000: FS | 2025-05-12 11:00 | 2025-06-18 11:00
C-52-598-06-CI-2230 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.8 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | C-52-598-06-CI-2220 | C-52-598-06-CI-2220: FS | C-52-598-06-CI-2600, PRECOM-52-59806-1000 | C-52-598-06-CI-2600: FS, PRECOM-52-59806-1000: FS | 2025-06-18 11:00 | 2025-07-14 11:00
C-52-598-06-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.11 | Back Filling for Electrical & Earthing Cable | C-52-598-06-EI-2000, C-52-598-06-CA-1000 | C-52-598-06-EI-2000: FS 5, C-52-598-06-CA-1000: FS 5 | C-52-598-06-CI-2810, PRECOM-52-59806-1000 | C-52-598-06-CI-2810: FS, PRECOM-52-59806-1000: FS | 2025-05-24 15:00 | 2025-06-12 15:00
C-52-598-06-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.11 | Back Filling for Instrument & Telecom Cable | C-52-598-06-EI-2010, C-52-598-06-CI-2800, C-52-598-06-EI-2020 | C-52-598-06-EI-2010: FS 5, C-52-598-06-CI-2800: FS, C-52-598-06-EI-2020: FS | PRECOM-52-59806-1000 | PRECOM-52-59806-1000: FS | 2025-06-12 15:00 | 2025-06-30 15:00
C-52-598-06-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.6 | Pre-Fabrication & Installation of Pipe Supports | C-52-598-06-CI-1600, HM-CS-0110, HE-CS-1490, HS-CN-0690, HM-CS-0120, HE-CS-1430 | C-52-598-06-CI-1600: FS, HM-CS-0110: FS, HE-CS-1490: FS, HS-CN-0690: FS, HM-CS-0120: FS, HE-CS-1430: FS | C-52-598-06-EI-2210, C-52-598-06-CI-3000, C-52-598-06-PI-1200, C-52-598-06-PI-1000 | C-52-598-06-EI-2210: SS 7, C-52-598-06-CI-3000: FS, C-52-598-06-PI-1200: FS, C-52-598-06-PI-1000: FS | 2025-03-12 09:00 | 2025-04-05 09:00
C-52-598-06-EI-2210 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.6 | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-06-CI-2000, C-52-598-06-CI-1410, C-52-598-06-PI-1200 | C-52-598-06-CI-2000: SS 7, C-52-598-06-CI-1410: FS, C-52-598-06-PI-1200: FF 7 | C-52-598-06-CI-3010, C-52-598-06-EI-1800, C-52-598-06-EI-2200 | C-52-598-06-CI-3010: FS, C-52-598-06-EI-1800: FS, C-52-598-06-EI-2200: FS | 2025-05-22 15:00 | 2025-06-10 15:00
C-52-598-06-CI-3000 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.10 | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-06-CI-2000, C-52-598-06-CI-1420, HM-CS-0120, HS-CN-0690, HM-CS-0110 | C-52-598-06-CI-2000: FS, C-52-598-06-CI-1420: FS, HM-CS-0120: FS, HS-CN-0690: FS, HM-CS-0110: FS | PRECOM-52-59806-1000 | PRECOM-52-59806-1000: FS | 2025-04-05 09:00 | 2025-05-08 16:00
C-52-598-06-CI-3010 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.10 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-06-EI-2210, HM-CS-0120, HS-CN-0690, HM-CS-0110 | C-52-598-06-EI-2210: FS, HM-CS-0120: FS, HS-CN-0690: FS, HM-CS-0110: FS | PRECOM-52-59806-1000 | PRECOM-52-59806-1000: FS | 2025-06-10 15:00 | 2025-06-26 15:00
C-52-598-06-EI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.2 | Installation of Solar Panel Structural Supports | C-52-598-06-CI-1410, HM-EL-0530, HM-ME-1590, HE-IC-1550, HE-IC-0010, HM-ME-0890, HE-IC-1430, HM-EL-0080, HE-IC-2570, HE-IC-0530, HE-EL-1730, HM-EL-0520, HE-IC-0650, HS-CN-0240, HM-IC-0050, HM-ME-1690, HE-EL-0530, HE-EL-0350, HE-EL-1010, HE-IC-0770, HE-EL-1 | C-52-598-06-CI-1410: FS, HM-EL-0530: FF, HM-ME-1590: FF, HE-IC-1550: FF, HE-IC-0010: FS, HM-ME-0890: FS, HE-IC-1430: FS, HM-EL-0080: FS, HE-IC-2570: FS, HE-IC-0530: FS, HE-EL-1730: FS, HM-EL-0520: FS, HE-IC-0650: FS, HS-CN-0240: FS, HM-IC-0050: FF, HM-ME-1 | C-52-598-06-CI-2400, C-52-598-06-EI-1200 | C-52-598-06-CI-2400: FS, C-52-598-06-EI-1200: FS | 2025-05-03 09:00 | 2025-05-17 17:00
C-52-598-06-CI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.7 | Installation of Fire Point Shelters | C-52-598-06-CI-1400, C-52-598-06-EI-1210, HM-CS-0110 | C-52-598-06-CI-1400: FS, C-52-598-06-EI-1210: FS, HM-CS-0110: FS | C-52-598-06-ME-1000, PRECOM-52-59806-1000 | C-52-598-06-ME-1000: FF 2, PRECOM-52-59806-1000: FS | 2025-05-19 07:00 | 2025-05-27 17:00
C-52-598-06-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.3.1 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | C-52-598-06-CI-2400, HM-ME-1990, ML1015-B08, HM-ME-2370 | C-52-598-06-CI-2400: FF 2, HM-ME-1990: FS, ML1015-B08: FS, HM-ME-2370: FS | PRECOM-52-59806-1000 | PRECOM-52-59806-1000: FS | 2025-05-21 07:00 | 2025-05-29 17:00
C-52-598-06-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.4.1 | Piping Pre-Fabrication | ML1002, CTF-SO1050, HE-PI-0580, ML1219-B19, HM-PI-0050, HM-PI-0040, HE-PR-0890, HS-CN-0190, HE-PI-0880, HE-PR-0290, ML1179-B11, HE-PI-1240, HE-PI-1300, HM-PI-70, C-52-598-06-CI-2000 | ML1002: FS, CTF-SO1050: FS, HE-PI-0580: FS, ML1219-B19: FS, HM-PI-0050: FS 14, HM-PI-0040: FS, HE-PR-0890: FS, HS-CN-0190: FS, HE-PI-0880: FS, HE-PR-0290: FS, ML1179-B11: FS, HE-PI-1240: FS, HE-PI-1300: FS, HM-PI-70: FS, C-52-598-06-CI-2000: FS | C-52-598-06-PI-1200, C-52-598-06-PL-1000 | C-52-598-06-PI-1200: FS, C-52-598-06-PL-1000: FS | 2025-04-19 07:00 | 2025-05-14 15:00
C-52-598-06-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.4.2 | Piping Erection | C-52-598-06-PI-1000, C-52-598-06-CI-2000, ML1002, HM-PL-0630, ML1219-B19, HM-PI-0050, HM-PI-0040, HE-PR-0890, HS-CN-0190, HE-PI-0880, HE-PR-0290, ML1179-B11, HE-PI-1240, HE-PI-1300, HM-PL-0640, HM-PL-0220, HM-PL-0740, HM-PI-70, HM-PL-1510, HM-PL-1570 | C-52-598-06-PI-1000: FS, C-52-598-06-CI-2000: FS, ML1002: FS, HM-PL-0630: FS, ML1219-B19: FS, HM-PI-0050: FS, HM-PI-0040: FS, HE-PR-0890: FS, HS-CN-0190: FS, HE-PI-0880: FS, HE-PR-0290: FS, ML1179-B11: FS, HE-PI-1240: FS, HE-PI-1300: FS, HM-PL-0640: FS, HM | C-52-598-06-PI-1400, C-52-598-06-EI-2210 | C-52-598-06-PI-1400: SS 2, C-52-598-06-EI-2210: FF 7 | 2025-05-14 15:00 | 2025-05-30 15:00
C-52-598-06-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.4.3 | Field Joint Welding (Including Isolation Joint) | C-52-598-06-PI-1200, HE-PI-1300, ML1002, ML1219-B19, HS-CN-0190, ML1179-B11 | C-52-598-06-PI-1200: SS 2, HE-PI-1300: FS, ML1002: FS, ML1219-B19: FS, HS-CN-0190: FS, ML1179-B11: FS | C-52-598-06-PI-1410, C-52-598-06-EI-2200 | C-52-598-06-PI-1410: SS 3, C-52-598-06-EI-2200: FF 3 | 2025-05-16 15:00 | 2025-05-30 15:00
C-52-598-06-PI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.4.3 | NDT & Coating for Field Joint Weld | C-52-598-06-PI-1400 | C-52-598-06-PI-1400: SS 3 | C-52-598-06-PI-1600 | C-52-598-06-PI-1600: FS | 2025-05-20 15:00 | 2025-06-03 15:00
C-52-598-06-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.4.4 | Hydrotesting | C-52-598-06-PI-1410, ML1219-B19, ML1179-B11 | C-52-598-06-PI-1410: FS, ML1219-B19: FS, ML1179-B11: FS | C-52-598-06-PI-1800 | C-52-598-06-PI-1800: FS | 2025-06-03 15:00 | 2025-06-11 15:00
C-52-598-06-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.4.5 | Installation of Valves & GOV | C-52-598-06-PI-1600, HM-PL-0630, ML1219-B19, HE-PR-0890, HE-PI-0880, HE-PR-0290, ML1179-B11, HE-PI-1240, HM-PL-0640, HM-PL-0220, HM-PL-0740, HM-PL-1510, HM-PL-1570, HM-ME-0580, HM-ME-2210 | C-52-598-06-PI-1600: FS, HM-PL-0630: FS, ML1219-B19: FS, HE-PR-0890: FS, HE-PI-0880: FS, HE-PR-0290: FS, ML1179-B11: FS, HE-PI-1240: FS, HM-PL-0640: FS, HM-PL-0220: FS, HM-PL-0740: FS, HM-PL-1510: FS, HM-PL-1570: FS, HM-ME-0580: FS, HM-ME-2210: FS | C-52-598-06-PI-2000, PRECOM-52-59806-1000 | C-52-598-06-PI-2000: SS 4, PRECOM-52-59806-1000: FS | 2025-07-21 07:00 | 2025-07-25 17:00
C-52-598-06-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.4.6 | Final Bolt Torquing/ Re-Instatement | C-52-598-06-PI-1800, HE-PI-1300, ML1002, HM-PL-0630, ML1219-B19, HE-PR-0890, HS-CN-0190, HE-PI-0880, HE-PR-0290, ML1179-B11, HE-PI-1240, HM-PL-0640, HM-PL-0220, HM-PL-0740, HM-PL-1510, HM-PL-1570 | C-52-598-06-PI-1800: SS 4, HE-PI-1300: FS, ML1002: FS, HM-PL-0630: FS, ML1219-B19: FS, HE-PR-0890: FS, HS-CN-0190: FS, HE-PI-0880: FS, HE-PR-0290: FS, ML1179-B11: FS, HE-PI-1240: FS, HM-PL-0640: FS, HM-PL-0220: FS, HM-PL-0740: FS, HM-PL-1510: FS, HM-PL-157 | PRECOM-52-59806-1000 | PRECOM-52-59806-1000: FS | 2025-07-25 07:00 | 2025-07-28 17:00
C-52-598-06-PL-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.5.1 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | C-52-598-06-PI-1000 | C-52-598-06-PI-1000: FS | C-52-598-06-PL-1010 | C-52-598-06-PL-1010: FS | 2025-05-14 15:00 | 2025-05-20 15:00
C-52-598-06-PL-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.5.1 | Lowering of Pipeline Section | C-52-598-06-PL-1000 | C-52-598-06-PL-1000: FS | C-52-598-06-PL-1020 | C-52-598-06-PL-1020: SS | 2025-05-20 15:00 | 2025-05-22 15:00
C-52-598-06-PL-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.5.1 | Section Tie-in Welding (Including Barred Tee) | C-52-598-06-PL-1010 | C-52-598-06-PL-1010: SS | C-52-598-06-PL-1030 | C-52-598-06-PL-1030: SS 1 | 2025-05-20 15:00 | 2025-06-03 15:00
C-52-598-06-PL-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.5.1 | NDT for Tie-in Joint | C-52-598-06-PL-1020 | C-52-598-06-PL-1020: SS 1 | C-52-598-06-PL-1040 | C-52-598-06-PL-1040: SS 1 | 2025-05-21 15:00 | 2025-06-04 15:00
C-52-598-06-PL-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.5.1 | Ext. Coating for Tie-in Joint | C-52-598-06-PL-1030 | C-52-598-06-PL-1030: SS 1 | C-52-598-06-PL-1050, PRECOM-52-59806-1000 | C-52-598-06-PL-1050: FS, PRECOM-52-59806-1000: FS | 2025-05-22 15:00 | 2025-06-07 15:00
C-52-598-06-PL-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.5.1 | Holiday Testing of Pipeline Section | C-52-598-06-PL-1040 | C-52-598-06-PL-1040: FS | C-52-598-06-PL-1060, C-52-598-06-PL-1090 | C-52-598-06-PL-1060: FS, C-52-598-06-PL-1090: FS | 2025-06-07 15:00 | 2025-06-09 15:00
C-52-598-06-PL-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.5.1 | Installation of ROV | C-52-598-06-PL-1050, HM-ME-0580, HM-ME-2210 | C-52-598-06-PL-1050: FS, HM-ME-0580: FS, HM-ME-2210: FS | C-52-598-06-PL-1070, C-52-598-06-PL-1090, PRECOM-52-59806-1000 | C-52-598-06-PL-1070: FS, C-52-598-06-PL-1090: FF 1, PRECOM-52-59806-1000: FS | 2025-07-21 07:00 | 2025-07-21 17:00
C-52-598-06-PL-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.5.1 | Installation of Pig Signaller Pit | C-52-598-06-PL-1060 | C-52-598-06-PL-1060: FS | C-52-598-06-PL-1080, C-52-598-06-PL-1090 | C-52-598-06-PL-1080: FS, C-52-598-06-PL-1090: FF 1 | 2025-07-22 07:00 | 2025-07-22 17:00
C-52-598-06-PL-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.5.1 | Installation of Pig Signaller | C-52-598-06-PL-1070 | C-52-598-06-PL-1070: FS | C-52-598-06-PL-1090, PRECOM-52-59806-1000 | C-52-598-06-PL-1090: FF, PRECOM-52-59806-1000: FS | 2025-07-23 07:00 | 2025-07-23 17:00
C-52-598-06-PL-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.5.1 | Padding & Backfilling | C-52-598-06-PL-1080, C-52-598-06-PL-1050, C-52-598-06-PL-1060, C-52-598-06-PL-1070 | C-52-598-06-PL-1080: FF, C-52-598-06-PL-1050: FS, C-52-598-06-PL-1060: FF 1, C-52-598-06-PL-1070: FF 1 | PRECOM-52-59806-1000 | PRECOM-52-59806-1000: FS | 2025-07-14 07:00 | 2025-07-23 17:00
C-52-598-06-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.7 | Electrical & Earthing Cable Laying | C-52-598-06-CI-1800, HM-EL-0080, HE-IC-1010, HE-EL-0830, HE-EL-1610, HE-EL-0590, HE-IC-0950, HE-IC-0830, HM-EL-0520, HE-EL-0470, HE-EL-1950, HM-EL-580, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-01 | C-52-598-06-CI-1800: FS, HM-EL-0080: FS, HE-IC-1010: FS, HE-EL-0830: FS, HE-EL-1610: FS, HE-EL-0590: FS, HE-IC-0950: FS, HE-IC-0830: FS, HM-EL-0520: FS, HE-EL-0470: FS, HE-EL-1950: FS, HM-EL-580: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-05 | C-52-598-06-EI-2050, C-52-598-06-EI-1400, C-52-598-06-EI-2010, C-52-598-06-CI-2800, PRECOM-52-59806-1000 | C-52-598-06-EI-2050: FS, C-52-598-06-EI-1400: FF, C-52-598-06-EI-2010: FS, C-52-598-06-CI-2800: FS 5, PRECOM-52-59806-1000: FS | 2025-04-19 07:00 | 2025-04-30 17:00
C-52-598-06-EI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.3 | Deep Earth Well Drilling | C-52-598-06-EI-2000, HM-EL-0530, HM-ME-1590, HE-IC-1550, HE-IC-0010, HM-ME-0890, HE-IC-1430, HM-EL-0080, HE-IC-2570, HE-IC-0530, HE-EL-1730, HM-EL-0520, HE-IC-0650, HS-CN-0240, HM-IC-0050, HM-ME-1690, HE-EL-0530, HE-EL-0350, HE-EL-1010, HE-IC-0770, HE-EL-1 | C-52-598-06-EI-2000: FF, HM-EL-0530: FF, HM-ME-1590: FF, HE-IC-1550: FF, HE-IC-0010: FS, HM-ME-0890: FS, HE-IC-1430: FS, HM-EL-0080: FS, HE-IC-2570: FS, HE-IC-0530: FS, HE-EL-1730: FS, HM-EL-0520: FS, HE-IC-0650: FS, HS-CN-0240: FS, HM-IC-0050: FF, HM-ME-1 | C-52-598-06-EI-2050 | C-52-598-06-EI-2050: FS | 2025-05-15 07:00 | 2025-05-17 17:00
C-52-598-06-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.7 | Instrument Cable Laying | C-52-598-06-EI-2000, C-52-598-06-CI-1810, HM-EL-0080, HE-IC-1010, HE-EL-0830, HE-EL-1610, HE-EL-0590, HE-IC-0950, HE-IC-0830, HM-EL-0520, HE-EL-0470, HE-EL-1950, HM-EL-580, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, | C-52-598-06-EI-2000: FS, C-52-598-06-CI-1810: FS, HM-EL-0080: FS, HE-IC-1010: FS, HE-EL-0830: FS, HE-EL-1610: FS, HE-EL-0590: FS, HE-IC-0950: FS, HE-IC-0830: FS, HM-EL-0520: FS, HE-EL-0470: FS, HE-EL-1950: FS, HM-EL-580: FS, HE-IC-0230: FS, HE-IC-0290: FS, | C-52-598-06-EI-2040, C-52-598-06-EI-2050, C-52-598-06-EI-2020, C-52-598-06-EI-2200, C-52-598-06-CA-1000, C-52-598-06-CI-2810, C-52-598-06-TE-1000 | C-52-598-06-EI-2040: FS, C-52-598-06-EI-2050: FS, C-52-598-06-EI-2020: FS, C-52-598-06-EI-2200: FS, C-52-598-06-CA-1000: FS, C-52-598-06-CI-2810: FS 5, C-52-598-06-TE-1000: FS | 2025-05-01 07:00 | 2025-05-13 15:00
C-52-598-06-EI-2020 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.7 | Installation of Cable Trays | C-52-598-06-EI-2010 | C-52-598-06-EI-2010: FS | C-52-598-06-EI-2030, C-52-598-06-EI-2200, C-52-598-06-TE-1000, C-52-598-06-CI-2810 | C-52-598-06-EI-2030: FS, C-52-598-06-EI-2200: FS, C-52-598-06-TE-1000: FS, C-52-598-06-CI-2810: FS | 2025-05-13 15:00 | 2025-05-24 15:00
C-52-598-06-EI-2030 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.7 | Instrument Tubing Works | C-52-598-06-EI-2020 | C-52-598-06-EI-2020: FS | C-52-598-06-EI-2050 | C-52-598-06-EI-2050: FS | 2025-05-24 15:00 | 2025-06-07 15:00
C-52-598-06-EI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.2 | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-598-06-EI-1210 | C-52-598-06-EI-1210: FS | C-52-598-06-EI-2040, C-52-598-06-EI-2050, C-52-598-06-EI-1800 | C-52-598-06-EI-2040: FS, C-52-598-06-EI-2050: FS, C-52-598-06-EI-1800: FS | 2025-05-19 07:00 | 2025-06-03 17:00
C-52-598-06-EI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.5 | Installation of Light Pole, Lighting & Fixtures | C-52-598-06-EI-1200, C-52-598-06-EI-2210, C-52-598-06-CI-1430 | C-52-598-06-EI-1200: FS, C-52-598-06-EI-2210: FS, C-52-598-06-CI-1430: FS | C-52-598-06-EI-2050, C-52-598-06-EI-1810 | C-52-598-06-EI-2050: FS, C-52-598-06-EI-1810: FS | 2025-06-10 15:00 | 2025-06-17 15:00
C-52-598-06-EI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.1 | Installation of Passive Cooling Shelter | C-52-598-06-CI-1400, HM-ME-1190, ML1054-D09 | C-52-598-06-CI-1400: FS, HM-ME-1190: FS 30, ML1054-D09: FS | C-52-598-06-EI-1600, C-52-598-06-EI-2050 | C-52-598-06-EI-1600: FS, C-52-598-06-EI-2050: FS | 2025-06-02 07:00 | 2025-06-04 17:00
C-52-598-06-EI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.4 | Installation of RTU | C-52-598-06-EI-1000 | C-52-598-06-EI-1000: FS | C-52-598-06-EI-2400, C-52-598-06-EI-2040, C-52-598-06-EI-2050 | C-52-598-06-EI-2400: FS, C-52-598-06-EI-2040: FS, C-52-598-06-EI-2050: FS | 2025-06-07 07:00 | 2025-06-09 17:00
C-52-598-06-EI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.8 | Installation of F&G Panel | C-52-598-06-EI-1600 | C-52-598-06-EI-1600: FS | C-52-598-06-EI-2040, C-52-598-06-EI-2050 | C-52-598-06-EI-2040: FS, C-52-598-06-EI-2050: FS | 2025-06-10 07:00 | 2025-06-11 17:00
C-52-598-06-EI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.5 | Installation of Lighting & Instrument JB's | C-52-598-06-EI-1800 | C-52-598-06-EI-1800: FS | C-52-598-06-EI-2040, C-52-598-06-EI-2050 | C-52-598-06-EI-2040: FS, C-52-598-06-EI-2050: FS | 2025-06-17 15:00 | 2025-06-20 15:00
C-52-598-06-EI-2200 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.6 | Installation of Field Instruments | C-52-598-06-EI-2210, C-52-598-06-PI-1400, C-52-598-06-EI-2010, C-52-598-06-EI-2020 | C-52-598-06-EI-2210: FS, C-52-598-06-PI-1400: FF 3, C-52-598-06-EI-2010: FS, C-52-598-06-EI-2020: FS | C-52-598-06-EI-2040, C-52-598-06-EI-2050, C-52-598-06-EI-2410 | C-52-598-06-EI-2040: FS, C-52-598-06-EI-2050: FS, C-52-598-06-EI-2410: FS | 2025-06-10 15:00 | 2025-06-17 15:00
C-52-598-06-EI-2410 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.8 | Installation of F&G Devices | C-52-598-06-EI-2200, HM-ME-1490, HM-ME-2310 | C-52-598-06-EI-2200: FS, HM-ME-1490: FS, HM-ME-2310: FS | C-52-598-06-EI-2040, C-52-598-06-EI-2050 | C-52-598-06-EI-2040: FS, C-52-598-06-EI-2050: FS | 2025-06-17 15:00 | 2025-06-23 15:00
C-52-598-06-EI-2040 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.7 | Loop Checking for Instruments | C-52-598-06-EI-2410, C-52-598-06-EI-2200, C-52-598-06-EI-1810, C-52-598-06-EI-1600, C-52-598-06-EI-2400, C-52-598-06-EI-1200, C-52-598-06-EI-2010 | C-52-598-06-EI-2410: FS, C-52-598-06-EI-2200: FS, C-52-598-06-EI-1810: FS, C-52-598-06-EI-1600: FS, C-52-598-06-EI-2400: FS, C-52-598-06-EI-1200: FS, C-52-598-06-EI-2010: FS | C-52-598-06-EI-2050, PRECOM-52-59806-1000 | C-52-598-06-EI-2050: FS, PRECOM-52-59806-1000: FS | 2025-06-23 15:00 | 2025-07-05 15:00
C-52-598-06-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.6.7 | Glanding & Termination | C-52-598-06-EI-2040, C-52-598-06-EI-2000, C-52-598-06-EI-2010, C-52-598-06-EI-2030, C-52-598-06-EI-1200, C-52-598-06-EI-1800, C-52-598-06-EI-1000, C-52-598-06-EI-1810, C-52-598-06-EI-2200, C-52-598-06-EI-2410, C-52-598-06-EI-1600, C-52-598-06-EI-2400, C-52 | C-52-598-06-EI-2040: FS, C-52-598-06-EI-2000: FS, C-52-598-06-EI-2010: FS, C-52-598-06-EI-2030: FS, C-52-598-06-EI-1200: FS, C-52-598-06-EI-1800: FS, C-52-598-06-EI-1000: FS, C-52-598-06-EI-1810: FS, C-52-598-06-EI-2200: FS, C-52-598-06-EI-2410: FS, C-52-5 | PRECOM-52-59806-1000 | PRECOM-52-59806-1000: FS | 2025-07-05 15:00 | 2025-07-17 15:00
C-52-598-06-CA-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.7.1 | CP Cable Laying | C-52-598-06-EI-2010, HM-PL-0430, HS-CN-0240 | C-52-598-06-EI-2010: FS, HM-PL-0430: FS, HS-CN-0240: FS | C-52-598-06-CA-1010, C-52-598-06-CI-2800 | C-52-598-06-CA-1010: FS, C-52-598-06-CI-2800: FS 5 | 2025-05-13 15:00 | 2025-05-19 15:00
C-52-598-06-CA-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.7.1 | Installation of CP Test Post | C-52-598-06-CA-1000 | C-52-598-06-CA-1000: FS | C-52-598-06-CA-1020 | C-52-598-06-CA-1020: FS | 2025-05-19 15:00 | 2025-05-22 15:00
C-52-598-06-CA-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.7.1 | Installation of CP S/m | C-52-598-06-CA-1010 | C-52-598-06-CA-1010: FS | PRECOM-52-59806-1000 | PRECOM-52-59806-1000: FS | 2025-05-22 15:00 | 2025-05-29 15:00
C-52-598-06-TE-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.8.9 | Installation of SDH Cabinet | C-52-598-06-EI-2010, C-52-598-06-EI-2020, HM-ME-1390, HS-CN-0290, HE-TL-0350, HM-TL-0050, ML1033-B22, HM-TL-0040, HE-TL-0830, HM-EL-0180, HM-ME-1290, HE-TL-0290, HE-TL-0710, HE-TL-0410, HE-TL-0770, HE-TL-0470, HM-ME-2270, HM-ME-2290, HM-EL-610 | C-52-598-06-EI-2010: FS, C-52-598-06-EI-2020: FS, HM-ME-1390: FS, HS-CN-0290: FS, HE-TL-0350: FS, HM-TL-0050: FS, ML1033-B22: FS, HM-TL-0040: FS, HE-TL-0830: FS, HM-EL-0180: FS, HM-ME-1290: FS, HE-TL-0290: FS, HE-TL-0710: FS, HE-TL-0410: FS, HE-TL-0770: FS | C-52-598-06-TE-1200 | C-52-598-06-TE-1200: FS | 2025-05-28 07:00 | 2025-05-30 17:00
C-52-598-06-TE-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.8.1 | Installation of PIDS/ PLDS System | C-52-598-06-TE-1000 | C-52-598-06-TE-1000: FS | C-52-598-06-TE-1600 | C-52-598-06-TE-1600: FS | 2025-05-31 07:00 | 2025-06-03 17:00
C-52-598-06-TE-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.8.3 | Installation of CCTV System | C-52-598-06-TE-1200 | C-52-598-06-TE-1200: FS | C-52-598-06-TE-1400 | C-52-598-06-TE-1400: FS | 2025-06-04 07:00 | 2025-06-11 17:00
C-52-598-06-TE-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.8.2 | Installation of Telephone System | C-52-598-06-TE-1600 | C-52-598-06-TE-1600: FS | PRECOM-52-59806-1000 | PRECOM-52-59806-1000: FS | 2025-06-12 07:00 | 2025-06-18 17:00
C-52-598-05-CI-1000 | In Progress | P2543-R01-Oct24..4.3.1.3.10.21.1.1 | Site Survey, Preparation & Grading Works | HE-SS-0030, ML1002, HE-CS-0170, HE-CS-0470, C-PER-1620 | HE-SS-0030: SS, ML1002: FS, HE-CS-0170: FS, HE-CS-0470: SS, C-PER-1620: SS | C-52-598-05-CI-1010 | C-52-598-05-CI-1010: SS 4 | 2024-10-17 | 2024-11-21 07:30
C-52-598-05-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.1 | Earth Works for Equipment Foundations & Hard Stand Area | C-52-598-05-CI-1000, C-PER-1620 | C-52-598-05-CI-1000: SS 4, C-PER-1620: FS 25 | C-52-598-05-CI-1020, C-52-598-05-CI-1200 | C-52-598-05-CI-1020: SS 7, C-52-598-05-CI-1200: FS | 2024-12-25 07:00 | 2025-01-10 17:00
C-52-598-05-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.1 | Earth Works for Pipe Support Foundations | C-52-598-05-CI-1010 | C-52-598-05-CI-1010: SS 7 | C-52-598-05-CI-1030, C-52-598-05-CI-1210, C-52-598-05-CI-1800 | C-52-598-05-CI-1030: SS 6, C-52-598-05-CI-1210: FS, C-52-598-05-CI-1800: FS | 2025-01-03 07:00 | 2025-01-18 17:00
C-52-598-05-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.1 | Earth Works for Field Instrument Foundations | C-52-598-05-CI-1020 | C-52-598-05-CI-1020: SS 6 | C-52-598-05-CI-1040, C-52-598-05-CI-1220 | C-52-598-05-CI-1040: SS 7, C-52-598-05-CI-1220: FS | 2025-01-10 07:00 | 2025-01-23 17:00
C-52-598-05-CI-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.1 | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-598-05-CI-1030 | C-52-598-05-CI-1030: SS 7 | C-52-598-05-CI-1050, C-52-598-05-CI-1230 | C-52-598-05-CI-1050: SS 6, C-52-598-05-CI-1230: FS | 2025-01-18 07:00 | 2025-02-03 17:00
C-52-598-05-CI-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.1 | Earth Works for Light Pole, Fence & Gates Foundation | C-52-598-05-CI-1040 | C-52-598-05-CI-1040: SS 6 | C-52-598-05-CI-1240 | C-52-598-05-CI-1240: FS | 2025-01-25 07:00 | 2025-02-07 17:00
C-52-598-05-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.2 | Compaction & Testing for Equipment Foundations & Hard Stand Area | C-52-598-05-CI-1010 | C-52-598-05-CI-1010: FS | C-52-598-05-CI-1400 | C-52-598-05-CI-1400: FS | 2025-01-11 07:00 | 2025-01-16 17:00
C-52-598-05-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.2 | Compaction & Testing for Pipe Support Foundations | C-52-598-05-CI-1020 | C-52-598-05-CI-1020: FS | C-52-598-05-CI-1600 | C-52-598-05-CI-1600: FS | 2025-01-20 07:00 | 2025-01-24 17:00
C-52-598-05-CI-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.2 | Compaction & Testing for Field Instrument Foundations | C-52-598-05-CI-1030 | C-52-598-05-CI-1030: FS | C-52-598-05-CI-1410 | C-52-598-05-CI-1410: FS | 2025-01-24 07:00 | 2025-01-29 17:00
C-52-598-05-CI-1230 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.2 | Compaction & Testing for Access Platform & Misc. Structural Foundations | C-52-598-05-CI-1040 | C-52-598-05-CI-1040: FS | C-52-598-05-CI-1420 | C-52-598-05-CI-1420: FS | 2025-02-04 07:00 | 2025-02-08 17:00
C-52-598-05-CI-1240 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.2 | Compaction & Testing for Light Pole, Fence & Gates Foundation | C-52-598-05-CI-1050 | C-52-598-05-CI-1050: FS | C-52-598-05-CI-1430 | C-52-598-05-CI-1430: FS | 2025-02-08 07:00 | 2025-02-13 17:00
C-52-598-05-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.3 | Concrete Works for Equipment Foundations & Hard Stand Area | C-52-598-05-CI-1200, ML1034-B25, HE-CS-0890, HM-CS-0050, HE-CS-1310, HE-CS-1190, HE-CS-0230, HM-CS-0040 | C-52-598-05-CI-1200: FS, ML1034-B25: FS, HE-CS-0890: FS, HM-CS-0050: FF, HE-CS-1310: FS, HE-CS-1190: FS, HE-CS-0230: FS, HM-CS-0040: FS | C-52-598-05-ME-1000, C-52-598-05-EI-1000 | C-52-598-05-ME-1000: FS, C-52-598-05-EI-1000: FS | 2025-01-17 07:00 | 2025-02-10 17:00
C-52-598-05-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.4 | Concrete Works for Pipe Support Foundations | C-52-598-05-CI-1210 | C-52-598-05-CI-1210: FS | C-52-598-05-CI-2000 | C-52-598-05-CI-2000: FS | 2025-01-25 07:00 | 2025-02-18 17:00
C-52-598-05-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.3 | Concrete Works for Field Instrument, JB Foundations | C-52-598-05-CI-1220, ML1034-B25, HM-CS-0050, HE-CS-0230, HM-CS-0040 | C-52-598-05-CI-1220: FS, ML1034-B25: FS, HM-CS-0050: FF, HE-CS-0230: FS, HM-CS-0040: FS | C-52-598-05-CI-1420, C-52-598-05-EI-1210, C-52-598-05-EI-2210 | C-52-598-05-CI-1420: FS, C-52-598-05-EI-1210: FS, C-52-598-05-EI-2210: FS | 2025-01-30 07:00 | 2025-02-14 17:00
C-52-598-05-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.3 | Concrete Works for Access Platform & Misc. Structural Foundations | C-52-598-05-CI-1230, C-52-598-05-CI-1410, ML1034-B25, HM-CS-0050, HE-CS-0230, HE-CS-1370, HM-CS-0040 | C-52-598-05-CI-1230: FS, C-52-598-05-CI-1410: FS, ML1034-B25: FS, HM-CS-0050: FF, HE-CS-0230: FS, HE-CS-1370: FS, HM-CS-0040: FS | C-52-598-05-CI-3000, C-52-598-06-CI-1420 | C-52-598-05-CI-3000: FS, C-52-598-06-CI-1420: FS | 2025-02-15 07:00 | 2025-02-28 17:00
C-52-598-05-CI-1430 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.3 | Concrete Works for Light Pole, Fence & Gates Foundation | C-52-598-05-CI-1240, ML1034-B25, HM-CS-0050, HE-CS-1010, HE-CS-0230, HM-CS-0040 | C-52-598-05-CI-1240: FS, ML1034-B25: FS, HM-CS-0050: FF, HE-CS-1010: FS, HE-CS-0230: FS, HM-CS-0040: FS | C-52-598-05-CI-2200 | C-52-598-05-CI-2200: FS | 2025-02-14 07:00 | 2025-03-12 13:00
C-52-598-05-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.5 | Electrical & Earthing Cable Trenching | C-52-598-05-CI-1020, HE-CS-0530 | C-52-598-05-CI-1020: FS, HE-CS-0530: FS | C-52-598-05-EI-2000, C-52-598-05-CI-1810 | C-52-598-05-EI-2000: FS, C-52-598-05-CI-1810: FS | 2025-01-20 07:00 | 2025-02-22 17:00
C-52-598-05-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.5 | Instrument & Telecom Cable Trenching | HE-CS-0530, C-52-598-05-CI-1800 | HE-CS-0530: FS, C-52-598-05-CI-1800: FS | C-52-598-05-EI-2010 | C-52-598-05-EI-2010: FS | 2025-02-24 07:00 | 2025-04-09 13:00
C-52-598-05-CI-2200 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.7 | Installation of Concrete Pillers for Boundary Wall | C-52-598-05-CI-1430, HE-CS-0350, HE-CS-0470 | C-52-598-05-CI-1430: FS, HE-CS-0350: FS, HE-CS-0470: FS | C-52-598-05-CI-2210, C-52-598-05-CI-2210 | C-52-598-05-CI-2210: FF 4, C-52-598-05-CI-2210: SS 4 | 2025-03-13 07:00 | 2025-04-14 13:00
C-52-598-05-CI-2210 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.7 | Block Works for Boundary Wall | C-52-598-05-CI-2200, C-52-598-05-CI-2200 | C-52-598-05-CI-2200: FF 4, C-52-598-05-CI-2200: SS 4 | C-52-598-05-CI-2220 | C-52-598-05-CI-2220: FS | 2025-03-19 07:00 | 2025-04-18 13:00
C-52-598-05-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.7 | Installation of Fence Post & Mesh Works (Type-4 & 3) | C-52-598-05-CI-2210 | C-52-598-05-CI-2210: FS | C-52-598-05-CI-2230, PRECOM-56-59805-1000 | C-52-598-05-CI-2230: FS, PRECOM-56-59805-1000: FS | 2025-04-18 13:00 | 2025-05-24 11:00
C-52-598-05-CI-2230 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.7 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | C-52-598-05-CI-2220 | C-52-598-05-CI-2220: FS | C-52-598-05-CI-2600, PRECOM-56-59805-1000 | C-52-598-05-CI-2600: FS, PRECOM-56-59805-1000: FS | 2025-05-24 11:00 | 2025-06-20 11:00
C-52-598-05-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.10 | Back Filling for Electrical & Earthing Cable | C-52-598-05-EI-2000, C-52-598-05-CA-1000 | C-52-598-05-EI-2000: FS, C-52-598-05-CA-1000: FS | C-52-598-05-CI-2810, C-52-598-05-CI-2810, PRECOM-56-59805-1000 | C-52-598-05-CI-2810: SS 7, C-52-598-05-CI-2810: FF 7, PRECOM-56-59805-1000: FS | 2025-04-25 07:00 | 2025-05-12 15:00
C-52-598-05-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.10 | Back Filling for Instrument & Telecom Cable | C-52-598-05-CI-2800, C-52-598-05-EI-2020, C-52-598-05-CI-2800, C-52-598-05-EI-2010 | C-52-598-05-CI-2800: SS 7, C-52-598-05-EI-2020: FF 2, C-52-598-05-CI-2800: FF 7, C-52-598-05-EI-2010: FS | PRECOM-56-59805-1000 | PRECOM-56-59805-1000: FS | 2025-05-03 07:00 | 2025-05-20 15:00
C-52-598-04-CI-1000 | Completed | P2543-R01-Oct24..4.3.1.3.11.21.1.1 | Site Survey, Preparation & Grading Works | HE-SS-0030, ML1002, HE-CS-0170 | HE-SS-0030: SS, ML1002: FS, HE-CS-0170: FS | C-52-598-04-CI-1010 | C-52-598-04-CI-1010: SS 4 | 2024-05-27 | 2024-07-10
C-52-598-04-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.1 | Earth Works for Equipment Foundations & Hard Stand Area | HE-CS-1800, HE-CS-0470, C-52-598-04-CI-1000, C-PER-1610 | HE-CS-1800: FS, HE-CS-0470: FS, C-52-598-04-CI-1000: SS 4, C-PER-1610: FS 35 | C-52-598-04-CI-1020, C-52-598-04-CI-1200 | C-52-598-04-CI-1020: SS 7, C-52-598-04-CI-1200: FS | 2024-12-18 07:00 | 2025-01-03 17:00
C-52-598-04-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.1 | Earth Works for Pipe Support Foundations | C-52-598-04-CI-1010 | C-52-598-04-CI-1010: SS 7 | C-52-598-04-CI-1210, C-52-598-04-CI-1800, C-52-598-04-CI-1030 | C-52-598-04-CI-1210: FS, C-52-598-04-CI-1800: FS, C-52-598-04-CI-1030: FS | 2024-12-26 07:00 | 2025-01-11 17:00
C-52-598-04-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.1 | Earth Works for Field Instrument Foundations | C-52-598-04-CI-1020 | C-52-598-04-CI-1020: FS | C-52-598-04-CI-1220, C-52-598-04-CI-1040 | C-52-598-04-CI-1220: FS, C-52-598-04-CI-1040: FS | 2025-01-13 07:00 | 2025-01-25 17:00
C-52-598-04-CI-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.1 | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-598-04-CI-1030 | C-52-598-04-CI-1030: FS | C-52-598-04-CI-1230, C-52-598-04-CI-1050 | C-52-598-04-CI-1230: FS, C-52-598-04-CI-1050: FS | 2025-01-27 07:00 | 2025-02-11 17:00
C-52-598-04-CI-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.1 | Earth Works for Light Pole, Fence & Gates Foundation | C-52-598-04-CI-1040 | C-52-598-04-CI-1040: FS | C-52-598-04-CI-1240 | C-52-598-04-CI-1240: FS | 2025-02-12 07:00 | 2025-02-25 17:00
C-52-598-04-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.2 | Compaction & Testing for Equipment Foundations & Hard Stand Area | C-52-598-04-CI-1010 | C-52-598-04-CI-1010: FS | C-52-598-04-CI-1400 | C-52-598-04-CI-1400: FS | 2025-01-04 07:00 | 2025-01-09 17:00
C-52-598-04-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.2 | Compaction & Testing for Pipe Support Foundations | C-52-598-04-CI-1020 | C-52-598-04-CI-1020: FS | C-52-598-04-CI-1600 | C-52-598-04-CI-1600: FS | 2025-01-13 07:00 | 2025-01-17 17:00
C-52-598-04-CI-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.2 | Compaction & Testing for Field Instrument Foundations | C-52-598-04-CI-1030 | C-52-598-04-CI-1030: FS | C-52-598-04-CI-1410 | C-52-598-04-CI-1410: FS | 2025-01-27 07:00 | 2025-01-31 17:00
C-52-598-04-CI-1230 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.2 | Compaction & Testing for Access Platform & Misc. Structural Foundations | C-52-598-04-CI-1040 | C-52-598-04-CI-1040: FS | C-52-598-04-CI-1420 | C-52-598-04-CI-1420: FS | 2025-02-12 07:00 | 2025-02-17 17:00
C-52-598-04-CI-1240 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.2 | Compaction & Testing for Light Pole, Fence & Gates Foundation | C-52-598-04-CI-1050 | C-52-598-04-CI-1050: FS | C-52-598-04-CI-1430, C-52-598-04-CI-2200 | C-52-598-04-CI-1430: FS, C-52-598-04-CI-2200: FS | 2025-02-26 07:00 | 2025-03-03 11:00
C-52-598-04-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.3 | Concrete Works for Equipment Foundations & Hard Stand Area | C-52-598-04-CI-1200, HE-CS-0230, HM-CS-0040, ML1034-B25, HE-CS-1190, HE-CS-0890, HE-CS-1310, HM-CS-0050 | C-52-598-04-CI-1200: FS, HE-CS-0230: FS, HM-CS-0040: FS, ML1034-B25: FS, HE-CS-1190: FS, HE-CS-0890: FS, HE-CS-1310: FS, HM-CS-0050: FS | C-52-598-04-EI-1000 | C-52-598-04-EI-1000: FS | 2025-01-10 07:00 | 2025-02-03 17:00
C-52-598-04-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.4 | Concrete Works for Pipe Support Foundations | C-52-598-04-CI-1210 | C-52-598-04-CI-1210: FS | C-52-598-04-CI-2000 | C-52-598-04-CI-2000: FF 7 | 2025-01-18 07:00 | 2025-02-11 17:00
C-52-598-04-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.3 | Concrete Works for Field Instrument, JB Foundations | C-52-598-04-CI-1220, HE-CS-0230, HM-CS-0040, ML1034-B25, HM-CS-0050 | C-52-598-04-CI-1220: FS, HE-CS-0230: FS, HM-CS-0040: FS, ML1034-B25: FS, HM-CS-0050: FS | C-52-598-04-EI-2210 | C-52-598-04-EI-2210: FS | 2025-02-01 07:00 | 2025-02-17 17:00
C-52-598-04-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.3 | Concrete Works for Access Platform & Misc. Structural Foundations | C-52-598-04-CI-1230, HE-CS-1370, HE-CS-0230, HM-CS-0040, ML1034-B25, HM-CS-0050 | C-52-598-04-CI-1230: FS, HE-CS-1370: FS, HE-CS-0230: FS, HM-CS-0040: FS, ML1034-B25: FS, HM-CS-0050: FS | C-52-598-04-CI-3000 | C-52-598-04-CI-3000: FS | 2025-02-18 07:00 | 2025-03-03 11:00
C-52-598-04-CI-1430 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.3 | Concrete Works for Light Pole, Fence & Gates Foundation | C-52-598-04-CI-1240, HE-CS-0230, HM-CS-0040, ML1034-B25, HE-CS-1010, HM-CS-0050 | C-52-598-04-CI-1240: FS, HE-CS-0230: FS, HM-CS-0040: FS, ML1034-B25: FS, HE-CS-1010: FS, HM-CS-0050: FS | C-52-598-04-CI-2200 | C-52-598-04-CI-2200: FS | 2025-03-03 11:00 | 2025-04-07 13:00
C-52-598-04-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.5 | Electrical & Earthing Cable Trenching | C-52-598-04-CI-1020, HE-CS-0530 | C-52-598-04-CI-1020: FS, HE-CS-0530: FS | C-52-598-04-EI-2000, C-52-598-04-CI-1810 | C-52-598-04-EI-2000: FS, C-52-598-04-CI-1810: FS | 2025-01-13 07:00 | 2025-02-15 17:00
C-52-598-04-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.5 | Instrument & Telecom Cable Trenching | HE-CS-0530, C-52-598-04-CI-1800 | HE-CS-0530: FS, C-52-598-04-CI-1800: FS | C-52-598-04-EI-2010 | C-52-598-04-EI-2010: FS | 2025-02-17 07:00 | 2025-03-29 13:00
C-52-598-04-CI-2200 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.8 | Installation of Concrete Pillers for Boundary Wall | C-52-598-04-CI-1240, HE-CS-0470, HE-CS-0350, C-52-598-04-CI-1430 | C-52-598-04-CI-1240: FS, HE-CS-0470: FS, HE-CS-0350: FS, C-52-598-04-CI-1430: FS | C-52-598-04-CI-2210, C-52-598-04-CI-2210 | C-52-598-04-CI-2210: SS 7, C-52-598-04-CI-2210: FF 7 | 2025-04-07 13:00 | 2025-05-01 13:00
C-52-598-04-CI-2210 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.8 | Block Works for Boundary Wall | C-52-598-04-CI-2200, C-52-598-04-CI-2200 | C-52-598-04-CI-2200: SS 7, C-52-598-04-CI-2200: FF 7 | C-52-598-04-CI-2220 | C-52-598-04-CI-2220: FS | 2025-04-15 13:00 | 2025-05-10 11:00
C-52-598-04-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.8 | Installation of Fence Post & Mesh Works (Type-4 & 3) | C-52-598-04-CI-2210 | C-52-598-04-CI-2210: FS | C-52-598-04-CI-2230, PRECOM-56-59804-1000 | C-52-598-04-CI-2230: FS, PRECOM-56-59804-1000: FS | 2025-05-10 11:00 | 2025-06-17 11:00
C-52-598-04-CI-2230 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.8 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | C-52-598-04-CI-2220 | C-52-598-04-CI-2220: FS | C-52-598-04-CI-2600, PRECOM-56-59804-1000 | C-52-598-04-CI-2600: FS, PRECOM-56-59804-1000: FS | 2025-06-17 11:00 | 2025-07-12 11:00
C-52-598-04-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.9 | Back Filling for Electrical & Earthing Cable | C-52-598-04-EI-2000, C-52-598-04-CA-1000 | C-52-598-04-EI-2000: FS 5, C-52-598-04-CA-1000: FS 5 | C-52-598-04-CI-2810, PRECOM-56-59804-1000 | C-52-598-04-CI-2810: FS, PRECOM-56-59804-1000: FS | 2025-05-07 12:00 | 2025-05-23 15:00
C-52-598-04-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.9 | Back Filling for Instrument & Telecom Cable | C-52-598-04-EI-2010, C-52-598-04-CI-2800 | C-52-598-04-EI-2010: FS 5, C-52-598-04-CI-2800: FS | PRECOM-56-59804-1000 | PRECOM-56-59804-1000: FS | 2025-05-23 15:00 | 2025-06-11 15:00
C-52-598-03-CI-1000 | Completed | P2543-R01-Oct24..4.3.1.3.12.21.1.1 | Site Survey, Preparation & Grading Works | HE-SS-0030, ML1002, HE-CS-0170 | HE-SS-0030: SS, ML1002: FS, HE-CS-0170: FS | C-52-598-03-CI-1010 | C-52-598-03-CI-1010: SS 4 | 2024-07-27 07:00 | 2024-08-05 17:00
C-52-598-03-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.1 | Earth Works for Equipment Foundations & Hard Stand Area | C-52-598-03-CI-1000, HE-CS-0470, C-PER-1600 | C-52-598-03-CI-1000: SS 4, HE-CS-0470: FS, C-PER-1600: FS 30 | C-52-598-03-CI-1020, C-52-598-03-CI-1020, C-52-598-03-CI-1200 | C-52-598-03-CI-1020: FF, C-52-598-03-CI-1020: SS 7, C-52-598-03-CI-1200: FS | 2024-12-11 07:00 | 2024-12-26 17:00
C-52-598-03-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.1 | Earth Works for Pipe Support Foundations | C-52-598-03-CI-1010, C-52-598-03-CI-1010 | C-52-598-03-CI-1010: FF, C-52-598-03-CI-1010: SS 7 | C-52-598-03-CI-1210, C-52-598-03-CI-1800, C-52-598-03-CI-1030 | C-52-598-03-CI-1210: FS, C-52-598-03-CI-1800: FS, C-52-598-03-CI-1030: FS | 2024-12-19 07:00 | 2025-01-04 17:00
C-52-598-03-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.1 | Earth Works for Field Instrument Foundations | C-52-598-03-CI-1020 | C-52-598-03-CI-1020: FS | C-52-598-03-CI-1220, C-52-598-03-CI-1040 | C-52-598-03-CI-1220: FS, C-52-598-03-CI-1040: FS | 2025-01-06 07:00 | 2025-01-18 17:00
C-52-598-03-CI-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.1 | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-598-03-CI-1030 | C-52-598-03-CI-1030: FS | C-52-598-03-CI-1230, C-52-598-03-CI-1050 | C-52-598-03-CI-1230: FS, C-52-598-03-CI-1050: FS | 2025-01-20 07:00 | 2025-02-04 17:00
C-52-598-03-CI-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.1 | Earth Works for Light Pole, Fence & Gates Foundation | C-52-598-03-CI-1040 | C-52-598-03-CI-1040: FS | C-52-598-03-CI-1240, C-52-598-03-CI-1800 | C-52-598-03-CI-1240: FS, C-52-598-03-CI-1800: FS | 2025-02-05 07:00 | 2025-02-18 17:00
C-52-598-03-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.2 | Compaction & Testing for Equipment Foundations & Hard Stand Area | C-52-598-03-CI-1010 | C-52-598-03-CI-1010: FS | C-52-598-03-CI-1400 | C-52-598-03-CI-1400: FS | 2024-12-27 07:00 | 2025-01-02 17:00
C-52-598-03-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.2 | Compaction & Testing for Pipe Support Foundations | C-52-598-03-CI-1020 | C-52-598-03-CI-1020: FS | C-52-598-03-CI-1600 | C-52-598-03-CI-1600: FS | 2025-01-06 07:00 | 2025-01-10 17:00
C-52-598-03-CI-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.2 | Compaction & Testing for Field Instrument Foundations | C-52-598-03-CI-1030 | C-52-598-03-CI-1030: FS | C-52-598-03-CI-1410 | C-52-598-03-CI-1410: FS | 2025-01-20 07:00 | 2025-01-24 17:00
C-52-598-03-CI-1230 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.2 | Compaction & Testing for Access Platform & Misc. Structural Foundations | C-52-598-03-CI-1040 | C-52-598-03-CI-1040: FS | C-52-598-03-CI-1420 | C-52-598-03-CI-1420: FS | 2025-02-05 07:00 | 2025-02-10 17:00
C-52-598-03-CI-1240 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.2 | Compaction & Testing for Light Pole, Fence & Gates Foundation | C-52-598-03-CI-1050 | C-52-598-03-CI-1050: FS | C-52-598-03-CI-1430 | C-52-598-03-CI-1430: FS | 2025-02-19 07:00 | 2025-02-24 17:00
C-52-598-03-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.3 | Concrete Works for Equipment Foundations & Hard Stand Area | C-52-598-03-CI-1200, HE-CS-1310, HE-CS-0230, ML1034-B25, HE-CS-0890, HM-CS-0040, HE-CS-1190, HM-CS-0050 | C-52-598-03-CI-1200: FS, HE-CS-1310: FS, HE-CS-0230: FS, ML1034-B25: FS, HE-CS-0890: FS, HM-CS-0040: FS, HE-CS-1190: FS, HM-CS-0050: FS | C-52-598-03-EI-1000 | C-52-598-03-EI-1000: FS | 2025-01-03 07:00 | 2025-01-27 17:00
C-52-598-03-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.4 | Concrete Works for Pipe Support Foundations | C-52-598-03-CI-1210, HE-CS-0230, ML1034-B25, HM-CS-0040, HM-CS-0050 | C-52-598-03-CI-1210: FS, HE-CS-0230: FS, ML1034-B25: FS, HM-CS-0040: FS, HM-CS-0050: FS | C-52-598-03-CI-2000 | C-52-598-03-CI-2000: FF 7 | 2025-01-11 07:00 | 2025-02-04 17:00
C-52-598-03-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.3 | Concrete Works for Field Instrument, JB Foundations | C-52-598-03-CI-1220, HE-CS-0230, ML1034-B25, HM-CS-0040, HM-CS-0050 | C-52-598-03-CI-1220: FS, HE-CS-0230: FS, ML1034-B25: FS, HM-CS-0040: FS, HM-CS-0050: FS | C-52-598-03-EI-2210 | C-52-598-03-EI-2210: FS | 2025-01-25 07:00 | 2025-02-10 17:00
C-52-598-03-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.3 | Concrete Works for Access Platform & Misc. Structural Foundations | C-52-598-03-CI-1230, HE-CS-1370, HE-CS-0230, ML1034-B25, HM-CS-0040, HM-CS-0050 | C-52-598-03-CI-1230: FS, HE-CS-1370: FS, HE-CS-0230: FS, ML1034-B25: FS, HM-CS-0040: FS, HM-CS-0050: FS | C-52-598-03-CI-3000 | C-52-598-03-CI-3000: FS | 2025-02-11 07:00 | 2025-02-24 17:00
C-52-598-03-CI-1430 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.3 | Concrete Works for Light Pole, Fence & Gates Foundation | C-52-598-03-CI-1240, HE-CS-0230, HE-CS-1010, ML1034-B25, HM-CS-0040, HM-CS-0050 | C-52-598-03-CI-1240: FS, HE-CS-0230: FS, HE-CS-1010: FS, ML1034-B25: FS, HM-CS-0040: FS, HM-CS-0050: FS | C-52-598-03-CI-2200 | C-52-598-03-CI-2200: FS | 2025-02-25 07:00 | 2025-03-26 11:00
C-52-598-03-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.6 | Electrical & Earthing Cable Trenching | C-52-598-03-CI-1020, C-52-598-03-CI-1050, HE-CS-0530 | C-52-598-03-CI-1020: FS, C-52-598-03-CI-1050: FS, HE-CS-0530: FS | C-52-598-03-EI-2000, C-52-598-03-CI-1810 | C-52-598-03-EI-2000: FS, C-52-598-03-CI-1810: FS | 2025-02-19 07:00 | 2025-04-04 13:00
C-52-598-03-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.6 | Instrument & Telecom Cable Trenching | HE-CS-0530, C-52-598-03-CI-1800 | HE-CS-0530: FS, C-52-598-03-CI-1800: FS | C-52-598-03-EI-2010 | C-52-598-03-EI-2010: FS | 2025-04-04 13:00 | 2025-05-10 11:00
C-52-598-03-CI-2200 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.8 | Installation of Concrete Pillers for Boundary Wall | C-52-598-03-CI-1430, HE-CS-0350, HE-CS-0470 | C-52-598-03-CI-1430: FS, HE-CS-0350: FS, HE-CS-0470: FS | C-52-598-03-CI-2210 | C-52-598-03-CI-2210: FS | 2025-03-26 11:00 | 2025-04-24 13:00
C-52-598-03-CI-2210 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.8 | Block Works for Boundary Wall | C-52-598-03-CI-2200 | C-52-598-03-CI-2200: FS | C-52-598-03-CI-2220 | C-52-598-03-CI-2220: FS | 2025-04-24 13:00 | 2025-05-20 11:00
C-52-598-03-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.8 | Installation of Fence Post & Mesh Works (Type-4 & 3) | C-52-598-03-CI-2210 | C-52-598-03-CI-2210: FS | C-52-598-03-CI-2230, PRECOM-56-59803-1000 | C-52-598-03-CI-2230: FS, PRECOM-56-59803-1000: FS | 2025-05-20 11:00 | 2025-06-26 11:00
C-52-598-03-CI-2230 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.8 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | C-52-598-03-CI-2220 | C-52-598-03-CI-2220: FS | C-52-598-03-CI-2600, PRECOM-56-59803-1000 | C-52-598-03-CI-2600: FS, PRECOM-56-59803-1000: FS | 2025-06-26 11:00 | 2025-07-22 11:00
C-52-598-03-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.10 | Back Filling for Electrical & Earthing Cable | C-52-598-03-EI-2000, C-52-598-03-CA-1000 | C-52-598-03-EI-2000: FS 5, C-52-598-03-CA-1000: FS 5 | C-52-598-03-CI-2810, PRECOM-56-59803-1000 | C-52-598-03-CI-2810: FS, PRECOM-56-59803-1000: FS | 2025-05-07 12:00 | 2025-05-23 15:00
C-52-598-03-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.10 | Back Filling for Instrument & Telecom Cable | C-52-598-03-EI-2010, C-52-598-03-CI-2800 | C-52-598-03-EI-2010: FS 5, C-52-598-03-CI-2800: FS | PRECOM-56-59803-1000 | PRECOM-56-59803-1000: FS | 2025-05-23 15:00 | 2025-06-11 15:00
C-52-598-02-CI-1000 | Completed | P2543-R01-Oct24..4.3.1.3.13.21.1.1 | Site Survey, Preparation & Grading Works | HE-SS-0030, ML1002, HE-CS-0170 | HE-SS-0030: SS, ML1002: FS, HE-CS-0170: FS | C-52-598-02-CI-1010 | C-52-598-02-CI-1010: FS | 2024-05-15 | 2024-07-26
C-52-598-02-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.1 | Earth Works for Equipment Foundations & Hard Stand Area | C-52-598-02-CI-1000, C-PER-1590, HE-CS-0470 | C-52-598-02-CI-1000: FS, C-PER-1590: FS 25, HE-CS-0470: FS | C-52-598-02-CI-1020, C-52-598-02-CI-1200 | C-52-598-02-CI-1020: SS 7, C-52-598-02-CI-1200: FS | 2024-11-30 07:00 | 2024-12-18 17:00
C-52-598-02-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.1 | Earth Works for Pipe Support Foundations | C-52-598-02-CI-1010 | C-52-598-02-CI-1010: SS 7 | C-52-598-02-CI-1210, C-52-598-02-CI-1800, C-52-598-02-CI-1030 | C-52-598-02-CI-1210: FS 14, C-52-598-02-CI-1800: FS, C-52-598-02-CI-1030: FS | 2024-12-11 07:00 | 2024-12-26 17:00
C-52-598-02-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.1 | Earth Works for Field Instrument Foundations | C-52-598-02-CI-1020 | C-52-598-02-CI-1020: FS | C-52-598-02-CI-1220, C-52-598-02-CI-1040 | C-52-598-02-CI-1220: FS 14, C-52-598-02-CI-1040: FS | 2024-12-27 07:00 | 2025-01-10 17:00
C-52-598-02-CI-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.1 | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-598-02-CI-1030 | C-52-598-02-CI-1030: FS | C-52-598-02-CI-1230, C-52-598-02-CI-1050 | C-52-598-02-CI-1230: FS 14, C-52-598-02-CI-1050: FS | 2025-01-11 07:00 | 2025-01-27 17:00
C-52-598-02-CI-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.1 | Earth Works for Light Pole, Fence & Gates Foundation | C-52-598-02-CI-1040 | C-52-598-02-CI-1040: FS | C-52-598-02-CI-1240, C-52-598-02-CI-1800 | C-52-598-02-CI-1240: FS, C-52-598-02-CI-1800: FS | 2025-01-28 07:00 | 2025-02-10 17:00
C-52-598-02-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.2 | Compaction & Testing for Equipment Foundations & Hard Stand Area | C-52-598-02-CI-1010 | C-52-598-02-CI-1010: FS | C-52-598-02-CI-1400, C-52-598-02-EI-1000 | C-52-598-02-CI-1400: FS, C-52-598-02-EI-1000: FS | 2024-12-19 07:00 | 2024-12-24 17:00
C-52-598-02-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.2 | Compaction & Testing for Pipe Support Foundations | C-52-598-02-CI-1020 | C-52-598-02-CI-1020: FS 14 | C-52-598-02-CI-1600 | C-52-598-02-CI-1600: FS 21 | 2025-01-14 07:00 | 2025-01-18 17:00
C-52-598-02-CI-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.2 | Compaction & Testing for Field Instrument Foundations | C-52-598-02-CI-1030 | C-52-598-02-CI-1030: FS 14 | C-52-598-02-CI-1410 | C-52-598-02-CI-1410: FS | 2025-01-28 07:00 | 2025-02-01 17:00
C-52-598-02-CI-1230 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.2 | Compaction & Testing for Access Platform & Misc. Structural Foundations | C-52-598-02-CI-1040 | C-52-598-02-CI-1040: FS 14 | C-52-598-02-CI-1420 | C-52-598-02-CI-1420: FS | 2025-02-13 07:00 | 2025-02-18 17:00
C-52-598-02-CI-1240 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.2 | Compaction & Testing for Light Pole, Fence & Gates Foundation | C-52-598-02-CI-1050 | C-52-598-02-CI-1050: FS | C-52-598-02-CI-1430 | C-52-598-02-CI-1430: FS | 2025-02-11 07:00 | 2025-02-15 17:00
C-52-598-02-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.3 | Concrete Works for Equipment Foundations & Hard Stand Area | C-52-598-02-CI-1200, HM-CS-0040, HM-CS-0050, ML1034-B25, HE-CS-1310, HE-CS-0230, HE-CS-0890, HE-CS-1190 | C-52-598-02-CI-1200: FS, HM-CS-0040: FS, HM-CS-0050: FS 7, ML1034-B25: FS, HE-CS-1310: FS, HE-CS-0230: FS, HE-CS-0890: FS, HE-CS-1190: FS | C-52-598-02-EI-1210 | C-52-598-02-EI-1210: FS | 2025-01-03 07:00 | 2025-01-27 17:00
C-52-598-02-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.4 | Concrete Works for Pipe Support Foundations | C-52-598-02-CI-1210 | C-52-598-02-CI-1210: FS 21 | C-52-598-02-CI-2000 | C-52-598-02-CI-2000: FF 7 | 2025-02-13 07:00 | 2025-03-11 09:00
C-52-598-02-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.3 | Concrete Works for Field Instrument, JB Foundations | C-52-598-02-CI-1220, HM-CS-0040, HM-CS-0050, ML1034-B25, HE-CS-0230 | C-52-598-02-CI-1220: FS, HM-CS-0040: FS, HM-CS-0050: FS 14, ML1034-B25: FS, HE-CS-0230: FS | C-52-598-02-EI-2210 | C-52-598-02-EI-2210: FF 7 | 2025-02-03 07:00 | 2025-02-18 17:00
C-52-598-02-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.3 | Concrete Works for Access Platform & Misc. Structural Foundations | C-52-598-02-CI-1230, HM-CS-0040, HM-CS-0050, ML1034-B25, HE-CS-0230, HE-CS-1370 | C-52-598-02-CI-1230: FS, HM-CS-0040: FS, HM-CS-0050: FS 5, ML1034-B25: FS, HE-CS-0230: FS, HE-CS-1370: FS | C-52-598-02-CI-3000, C-52-598-02-CI-3010 | C-52-598-02-CI-3000: FF 7, C-52-598-02-CI-3010: FF 7 | 2025-02-19 07:00 | 2025-03-05 09:00
C-52-598-02-CI-1430 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.3 | Concrete Works for Light Pole, Fence & Gates Foundation | C-52-598-02-CI-1240, HM-CS-0040, HM-CS-0050, ML1034-B25, HE-CS-0230, HE-CS-1010 | C-52-598-02-CI-1240: FS, HM-CS-0040: FS, HM-CS-0050: FS, ML1034-B25: FS, HE-CS-0230: FS, HE-CS-1010: FS | C-52-598-02-CI-2200 | C-52-598-02-CI-2200: FS | 2025-02-17 07:00 | 2025-03-15 15:00
C-52-598-02-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.5 | Electrical & Earthing Cable Trenching | C-52-598-02-CI-1020, C-52-598-02-CI-1050, HE-CS-0530 | C-52-598-02-CI-1020: FS, C-52-598-02-CI-1050: FS, HE-CS-0530: FS | C-52-598-02-EI-2000, C-52-598-02-CI-1810 | C-52-598-02-EI-2000: FS, C-52-598-02-CI-1810: FS | 2025-02-11 07:00 | 2025-03-22 09:00
C-52-598-02-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.5 | Instrument & Telecom Cable Trenching | HE-CS-0530, C-52-598-02-CI-1800 | HE-CS-0530: FS, C-52-598-02-CI-1800: FS | C-52-598-02-CI-2800, C-52-598-02-CI-2810, C-52-598-02-EI-2010 | C-52-598-02-CI-2800: FS, C-52-598-02-CI-2810: FS, C-52-598-02-EI-2010: FS | 2025-03-22 09:00 | 2025-05-01 13:00
C-52-598-02-CI-2200 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.7 | Installation of Concrete Pillers for Boundary Wall | C-52-598-02-CI-1430, HE-CS-0470, HE-CS-0350 | C-52-598-02-CI-1430: FS, HE-CS-0470: FS, HE-CS-0350: FS | C-52-598-02-CI-2210, C-52-598-02-CI-2210 | C-52-598-02-CI-2210: FF 7, C-52-598-02-CI-2210: SS 7 | 2025-03-15 15:00 | 2025-04-16 13:00
C-52-598-02-CI-2210 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.7 | Block Works for Boundary Wall | C-52-598-02-CI-2200, C-52-598-02-CI-2200 | C-52-598-02-CI-2200: FF 7, C-52-598-02-CI-2200: SS 7 | C-52-598-02-CI-2220 | C-52-598-02-CI-2220: FS | 2025-03-26 11:00 | 2025-04-24 13:00
C-52-598-02-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.7 | Installation of Fence Post & Mesh Works (Type-4 & 3) | C-52-598-02-CI-2210, C-52-598-02-CI-3010 | C-52-598-02-CI-2210: FS, C-52-598-02-CI-3010: FF | C-52-598-02-CI-2230, PRECOM-56-59802-1000 | C-52-598-02-CI-2230: FS, PRECOM-56-59802-1000: FS | 2025-04-24 13:00 | 2025-05-30 11:00
C-52-598-02-CI-2230 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.7 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | C-52-598-02-CI-2220 | C-52-598-02-CI-2220: FS | C-52-598-02-CI-2600, PRECOM-56-59802-1000 | C-52-598-02-CI-2600: FS, PRECOM-56-59802-1000: FS | 2025-05-30 11:00 | 2025-06-26 11:00
C-52-598-02-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.10 | Back Filling for Electrical & Earthing Cable | C-52-598-02-CI-1810, C-52-598-02-EI-2000, C-52-598-02-EI-1400, C-52-598-02-CA-1000 | C-52-598-02-CI-1810: FS, C-52-598-02-EI-2000: FS, C-52-598-02-EI-1400: FS, C-52-598-02-CA-1000: FS | PRECOM-56-59802-1000 | PRECOM-56-59802-1000: FS | 2025-05-22 07:00 | 2025-06-09 17:00
C-52-598-02-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.10 | Back Filling for Instrument & Telecom Cable | C-52-598-02-CI-1810, C-52-598-02-EI-2010 | C-52-598-02-CI-1810: FS, C-52-598-02-EI-2010: FS | PRECOM-56-59802-1000 | PRECOM-56-59802-1000: FS | 2025-05-09 11:00 | 2025-05-26 11:00
C-52-598-01-CI-1000 | Completed | P2543-R01-Oct24..4.3.1.3.14.21.1.1 | Site Survey, Preparation & Grading Works | HE-SS-0030, ML1002, HE-CS-0170 | HE-SS-0030: SS, ML1002: FS, HE-CS-0170: FS | C-52-598-01-CI-1010 | C-52-598-01-CI-1010: FS | 2024-03-26 | 2024-06-12
C-52-598-01-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.1 | Earth Works for Equipment Foundations & Hard Stand Area | C-52-598-01-CI-1000, C-PER-1580, HE-CS-0470 | C-52-598-01-CI-1000: FS, C-PER-1580: FS 20, HE-CS-0470: FS | C-52-598-01-CI-1020, C-52-598-01-CI-1200, C-56-591-01-CI-1010 | C-52-598-01-CI-1020: FS, C-52-598-01-CI-1200: FS 14, C-56-591-01-CI-1010: FS | 2024-11-22 07:00 | 2024-12-10 17:00
C-52-598-01-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.1 | Earth Works for Pipe Support Foundations | C-52-598-01-CI-1010 | C-52-598-01-CI-1010: FS | C-52-598-01-CI-1030, C-52-598-01-CI-1210, C-52-598-01-CI-1800 | C-52-598-01-CI-1030: FS, C-52-598-01-CI-1210: FS 14, C-52-598-01-CI-1800: FS | 2024-12-11 07:00 | 2024-12-26 17:00
C-52-598-01-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.1 | Earth Works for Field Instrument Foundations | C-52-598-01-CI-1020 | C-52-598-01-CI-1020: FS | C-52-598-01-CI-1040, C-52-598-01-CI-1220 | C-52-598-01-CI-1040: FS, C-52-598-01-CI-1220: FS | 2024-12-27 07:00 | 2025-01-10 17:00
C-52-598-01-CI-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.1 | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-598-01-CI-1030 | C-52-598-01-CI-1030: FS | C-52-598-01-CI-1050, C-52-598-01-CI-1230 | C-52-598-01-CI-1050: FS, C-52-598-01-CI-1230: FS | 2025-01-11 07:00 | 2025-01-27 17:00
C-52-598-01-CI-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.1 | Earth Works for Light Pole, Fence & Gates Foundation | C-52-598-01-CI-1040 | C-52-598-01-CI-1040: FS | C-52-598-01-CI-1240, C-52-598-01-CI-1800 | C-52-598-01-CI-1240: FS, C-52-598-01-CI-1800: FS | 2025-01-28 07:00 | 2025-02-10 17:00
C-52-598-01-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.2 | Compaction & Testing for Equipment Foundations & Hard Stand Area | C-52-598-01-CI-1010 | C-52-598-01-CI-1010: FS 14 | C-52-598-01-CI-1400 | C-52-598-01-CI-1400: FS | 2024-12-27 07:00 | 2025-01-02 17:00
C-52-598-01-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.2 | Compaction & Testing for Pipe Support Foundations | C-52-598-01-CI-1020 | C-52-598-01-CI-1020: FS 14 | C-52-598-01-CI-1600 | C-52-598-01-CI-1600: FS | 2025-01-14 07:00 | 2025-01-18 17:00
C-52-598-01-CI-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.2 | Compaction & Testing for Field Instrument Foundations | C-52-598-01-CI-1030 | C-52-598-01-CI-1030: FS | C-52-598-01-CI-1410 | C-52-598-01-CI-1410: FS | 2025-01-11 07:00 | 2025-01-16 17:00
C-52-598-01-CI-1230 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.2 | Compaction & Testing for Access Platform & Misc. Structural Foundations | C-52-598-01-CI-1040 | C-52-598-01-CI-1040: FS | C-52-598-01-CI-1420 | C-52-598-01-CI-1420: FS | 2025-01-28 07:00 | 2025-02-01 17:00
C-52-598-01-CI-1240 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.2 | Compaction & Testing for Light Pole, Fence & Gates Foundation | C-52-598-01-CI-1050 | C-52-598-01-CI-1050: FS | C-52-598-01-CI-1430 | C-52-598-01-CI-1430: FS | 2025-02-11 07:00 | 2025-02-15 17:00
C-52-598-01-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.3 | Concrete Works for Equipment Foundations & Hard Stand Area | C-52-598-01-CI-1200, HM-CS-0050, HE-CS-1310, HE-CS-0890, ML1034-B25, HM-CS-0040, HE-CS-1190, HE-CS-0230 | C-52-598-01-CI-1200: FS, HM-CS-0050: FF 7, HE-CS-1310: FS, HE-CS-0890: FS, ML1034-B25: FS, HM-CS-0040: FS, HE-CS-1190: FS, HE-CS-0230: FS | C-52-598-01-EI-1210, C-52-598-01-EI-1000, C-52-598-01-CI-1410, C-52-598-01-CI-1600 | C-52-598-01-EI-1210: FS, C-52-598-01-EI-1000: FS, C-52-598-01-CI-1410: FS, C-52-598-01-CI-1600: FS | 2025-01-03 07:00 | 2025-01-27 17:00
C-52-598-01-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.4 | Concrete Works for Pipe Support Foundations | C-52-598-01-CI-1210, C-52-598-01-CI-1400 | C-52-598-01-CI-1210: FS, C-52-598-01-CI-1400: FS | C-52-598-01-CI-2000, C-56-591-01-CI-1600 | C-52-598-01-CI-2000: FS 7, C-56-591-01-CI-1600: FS | 2025-01-28 07:00 | 2025-02-20 17:00
C-52-598-01-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.3 | Concrete Works for Field Instrument, JB Foundations | C-52-598-01-CI-1220, C-52-598-01-CI-1400 | C-52-598-01-CI-1220: FS, C-52-598-01-CI-1400: FS | C-52-598-01-EI-2210, C-52-598-01-CI-1420 | C-52-598-01-EI-2210: FF 7, C-52-598-01-CI-1420: FS | 2025-01-28 07:00 | 2025-02-12 17:00
C-52-598-01-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.3 | Concrete Works for Access Platform & Misc. Structural Foundations | C-52-598-01-CI-1230, C-52-598-01-CI-1410, HM-CS-0050, ML1034-B25, HM-CS-0040, HE-CS-0230, HE-CS-1370 | C-52-598-01-CI-1230: FS, C-52-598-01-CI-1410: FS, HM-CS-0050: FS, ML1034-B25: FS, HM-CS-0040: FS, HE-CS-0230: FS, HE-CS-1370: FS | C-52-598-01-CI-3000, C-52-598-01-CI-3010, C-52-598-01-CI-1430 | C-52-598-01-CI-3000: FF 7, C-52-598-01-CI-3010: FF 7, C-52-598-01-CI-1430: FS | 2025-02-13 07:00 | 2025-02-26 17:00
C-52-598-01-CI-1430 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.3 | Concrete Works for Light Pole, Fence & Gates Foundation | C-52-598-01-CI-1240, C-52-598-01-CI-1420, HE-CS-1010 | C-52-598-01-CI-1240: FS, C-52-598-01-CI-1420: FS, HE-CS-1010: FS | C-52-598-01-CI-2200 | C-52-598-01-CI-2200: FS | 2025-02-27 07:00 | 2025-03-29 13:00
C-52-598-01-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.5 | Electrical & Earthing Cable Trenching | C-52-598-01-CI-1020, C-52-598-01-CI-1050, HE-CS-0530 | C-52-598-01-CI-1020: FS, C-52-598-01-CI-1050: FS, HE-CS-0530: FS | C-52-598-01-CI-1810, C-52-598-01-EI-2000, C-52-598-01-CI-1810 | C-52-598-01-CI-1810: SS 7, C-52-598-01-EI-2000: FS, C-52-598-01-CI-1810: FF | 2025-02-11 07:00 | 2025-03-22 09:00
C-52-598-01-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.5 | Instrument & Telecom Cable Trenching | C-52-598-01-CI-1800, C-52-598-01-CI-1800, HE-CS-0530 | C-52-598-01-CI-1800: SS 7, C-52-598-01-CI-1800: FF, HE-CS-0530: FS | C-52-598-01-EI-2010 | C-52-598-01-EI-2010: FS | 2025-02-19 07:00 | 2025-04-04 13:00
C-52-598-01-CI-2200 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.7 | Installation of Concrete Pillers for Boundary Wall | C-52-598-01-CI-1430, HE-CS-0350, HE-CS-0470 | C-52-598-01-CI-1430: FS, HE-CS-0350: FS, HE-CS-0470: FS | C-52-598-01-CI-2210, C-52-598-01-CI-2210 | C-52-598-01-CI-2210: FF 7, C-52-598-01-CI-2210: SS 7 | 2025-03-29 13:00 | 2025-04-26 13:00
C-52-598-01-CI-2210 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.7 | Block Works for Boundary Wall | C-52-598-01-CI-2200, C-52-598-01-CI-2200 | C-52-598-01-CI-2200: FF 7, C-52-598-01-CI-2200: SS 7 | C-52-598-01-CI-2220 | C-52-598-01-CI-2220: FS | 2025-04-10 13:00 | 2025-05-05 14:00
C-52-598-01-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.7 | Installation of Fence Post & Mesh Works (Type-4 & 3) | C-52-598-01-CI-2210 | C-52-598-01-CI-2210: FS | C-52-598-01-CI-2230, PRECOM-56-59801-1000 | C-52-598-01-CI-2230: FS, PRECOM-56-59801-1000: FS | 2025-05-05 14:00 | 2025-06-12 11:00
C-52-598-01-CI-2230 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.7 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | C-52-598-01-CI-2220 | C-52-598-01-CI-2220: FS | C-52-598-01-CI-2600, PRECOM-56-59801-1000 | C-52-598-01-CI-2600: FS, PRECOM-56-59801-1000: FS | 2025-06-12 11:00 | 2025-07-08 11:00
C-52-598-01-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.10 | Back Filling for Electrical & Earthing Cable | C-52-598-01-EI-2000, C-52-598-01-CA-1000 | C-52-598-01-EI-2000: FS 5, C-52-598-01-CA-1000: FS 5 | PRECOM-56-59801-1000 | PRECOM-56-59801-1000: FS | 2025-05-07 12:00 | 2025-05-23 15:00
C-52-598-01-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.10 | Back Filling for Instrument & Telecom Cable | C-52-598-01-EI-2010 | C-52-598-01-EI-2010: FS 5 | PRECOM-56-59801-1000 | PRECOM-56-59801-1000: FS | 2025-05-08 14:00 | 2025-05-24 15:00
C-52-598-05-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.6 | Pre-Fabrication & Installation of Pipe Supports | C-52-598-05-CI-1600, HS-CN-0690, HM-CS-0110, HE-CS-1430, HM-CS-0120, HE-CS-1490 | C-52-598-05-CI-1600: FS, HS-CN-0690: FS, HM-CS-0110: FS, HE-CS-1430: FS, HM-CS-0120: FS, HE-CS-1490: FS | C-52-598-05-EI-2210, C-52-598-05-CI-3000, C-52-598-05-PI-1000, C-52-598-05-PI-1200 | C-52-598-05-EI-2210: SS 7, C-52-598-05-CI-3000: FS, C-52-598-05-PI-1000: FS, C-52-598-05-PI-1200: FS | 2025-03-12 09:00 | 2025-04-05 09:00
C-52-598-05-EI-2210 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.8 | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-05-CI-2000, C-52-598-05-CI-1410, C-52-598-05-PI-1200 | C-52-598-05-CI-2000: SS 7, C-52-598-05-CI-1410: FS, C-52-598-05-PI-1200: FF 7 | C-52-598-05-CI-3010, C-52-598-05-CI-2400, C-52-598-05-EI-1800, C-52-598-05-EI-2200 | C-52-598-05-CI-3010: FS, C-52-598-05-CI-2400: FS, C-52-598-05-EI-1800: FS, C-52-598-05-EI-2200: FS | 2025-05-09 07:00 | 2025-05-24 17:00
C-52-598-05-CI-3000 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.11 | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-05-CI-2000, C-52-598-05-PI-1400, C-52-598-05-CI-1420, HM-CS-0110, HS-CN-0690, HM-CS-0120 | C-52-598-05-CI-2000: FS, C-52-598-05-PI-1400: FS, C-52-598-05-CI-1420: FS, HM-CS-0110: FS, HS-CN-0690: FS, HM-CS-0120: FS | C-52-598-05-CI-3010, PRECOM-56-59805-1000 | C-52-598-05-CI-3010: FF 2, PRECOM-56-59805-1000: FS | 2025-05-17 07:00 | 2025-06-20 17:00
C-52-598-05-CI-3010 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.11 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-05-EI-2210, C-52-598-05-CI-3000, HM-CS-0110, HS-CN-0690, HM-CS-0120 | C-52-598-05-EI-2210: FS, C-52-598-05-CI-3000: FF 2, HM-CS-0110: FS, HS-CN-0690: FS, HM-CS-0120: FS | PRECOM-56-59805-1000 | PRECOM-56-59805-1000: FS | 2025-06-07 07:00 | 2025-06-23 17:00
C-52-598-05-EI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.2 | Installation of Solar Panel Structural Supports | C-52-598-05-CI-1410, HM-EL-0520, HE-IC-2570, HE-IC-0650, HE-IC-0530, HM-EL-0080, HE-IC-0490, HE-EL-1790, HM-ME-1090, HM-EL-0380, HE-IC-1550, HE-EL-0640, HE-EL-0530, HS-CN-0240, HE-IC-1430, HM-ME-0890, HE-EL-1670, HM-ME-1590, HE-EL-1730, HE-IC-0770, HM-IC-0 | C-52-598-05-CI-1410: FS, HM-EL-0520: FS, HE-IC-2570: FS, HE-IC-0650: FS, HE-IC-0530: FS, HM-EL-0080: FS, HE-IC-0490: FS, HE-EL-1790: FS, HM-ME-1090: FF 12, HM-EL-0380: FS, HE-IC-1550: FF, HE-EL-0640: FS, HE-EL-0530: FS, HS-CN-0240: FS, HE-IC-1430: FS, HM-M | C-52-598-05-CI-2400, C-52-598-05-EI-1200 | C-52-598-05-CI-2400: FS, C-52-598-05-EI-1200: FS | 2025-05-07 14:00 | 2025-05-22 07:00
C-52-598-05-CI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.8 | Installation of Fire Point Shelters | C-52-598-05-EI-2210, C-52-598-05-EI-1210, HM-CS-0110 | C-52-598-05-EI-2210: FS, C-52-598-05-EI-1210: FS, HM-CS-0110: FS | C-52-598-05-ME-1000 | C-52-598-05-ME-1000: FS 14 | 2025-05-26 07:00 | 2025-06-03 17:00
C-52-598-04-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.7 | Pre-Fabrication & Installation of Pipe Supports | C-52-598-04-CI-1600, HS-CN-0690, HE-CS-1430, HM-CS-0110, HE-CS-1490, HM-CS-0120 | C-52-598-04-CI-1600: FF 7, HS-CN-0690: FS, HE-CS-1430: FS, HM-CS-0110: FS, HE-CS-1490: FS, HM-CS-0120: FS | C-52-598-04-EI-2210, C-52-598-04-CI-3000, C-52-598-04-PI-1200 | C-52-598-04-EI-2210: SS 7, C-52-598-04-CI-3000: FS, C-52-598-04-PI-1200: FS | 2025-03-12 09:00 | 2025-04-05 09:00
C-52-598-04-EI-2210 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.8 | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-04-CI-2000, C-52-598-04-CI-1410, C-52-598-04-PI-1200 | C-52-598-04-CI-2000: SS 7, C-52-598-04-CI-1410: FS, C-52-598-04-PI-1200: FF 3 | C-52-598-04-CI-3010, C-52-598-04-EI-1210, C-52-598-04-CI-2400, C-52-598-04-EI-1800 | C-52-598-04-CI-3010: FS, C-52-598-04-EI-1210: FS, C-52-598-04-CI-2400: FS, C-52-598-04-EI-1800: FS | 2025-04-09 09:00 | 2025-04-25 09:00
C-52-598-04-CI-3000 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.10 | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-04-CI-2000, C-52-598-04-CI-1420, C-52-598-04-PI-1400, HM-CS-0120, HS-CN-0690 | C-52-598-04-CI-2000: FS, C-52-598-04-CI-1420: FS, C-52-598-04-PI-1400: FS, HM-CS-0120: FS, HS-CN-0690: FS | C-52-598-04-CI-3010, PRECOM-56-59804-1000 | C-52-598-04-CI-3010: FF 3, PRECOM-56-59804-1000: FS | 2025-04-22 09:00 | 2025-05-24 17:00
C-52-598-04-CI-3010 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.10 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-04-EI-2210, C-52-598-04-CI-3000, C-52-598-04-PI-1400, HM-CS-0120, HS-CN-0690 | C-52-598-04-EI-2210: FS, C-52-598-04-CI-3000: FF 3, C-52-598-04-PI-1400: FF 3, HM-CS-0120: FS, HS-CN-0690: FS | PRECOM-56-59804-1000 | PRECOM-56-59804-1000: FS | 2025-05-13 07:00 | 2025-05-28 17:00
C-52-598-04-EI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.2 | Installation of Solar Panel Structural Supports | C-52-598-04-EI-2210, HM-EL-0080, HM-EL-0280, HM-ME-0890, HM-EL-0520, ML1032-B21, HE-EL-0770, HM-EL-0380, HE-EL-1790, HE-IC-1430, HE-EL-0640, HE-IC-0490, HE-IC-0770, HM-IC-0040, HM-ME-1090, HE-IC-0650, HE-IC-0590, HE-EL-0530, HE-EL-0350, HM-ME-1590, HE-HS-0 | C-52-598-04-EI-2210: FS, HM-EL-0080: FS, HM-EL-0280: FS, HM-ME-0890: FS, HM-EL-0520: FS, ML1032-B21: FS, HE-EL-0770: FS, HM-EL-0380: FS, HE-EL-1790: FS, HE-IC-1430: FS, HE-EL-0640: FS, HE-IC-0490: FS, HE-IC-0770: FS, HM-IC-0040: FS, HM-ME-1090: FF 12, HE-I | C-52-598-04-EI-1200 | C-52-598-04-EI-1200: FS | 2025-05-07 14:00 | 2025-05-22 07:00
C-52-598-04-CI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.6 | Installation of Fire Point Shelters | C-52-598-04-EI-2210, HM-CS-0110 | C-52-598-04-EI-2210: FS, HM-CS-0110: FS | C-52-598-04-ME-1000 | C-52-598-04-ME-1000: FS 15 | 2025-04-25 09:00 | 2025-05-05 10:00
C-52-598-03-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.5 | Pre-Fabrication & Installation of Pipe Supports | C-52-598-03-CI-1600, HE-CS-1430, HE-CS-1490, HS-CN-0690, HM-CS-0120, HM-CS-0110 | C-52-598-03-CI-1600: FF 7, HE-CS-1430: FS, HE-CS-1490: FS, HS-CN-0690: FS, HM-CS-0120: FS, HM-CS-0110: FS | C-52-598-03-EI-2210, C-52-598-03-CI-3000, C-52-598-03-PI-1200, C-52-598-03-PI-1000 | C-52-598-03-EI-2210: SS 7, C-52-598-03-CI-3000: FS, C-52-598-03-PI-1200: FS, C-52-598-03-PI-1000: FS | 2025-03-12 09:00 | 2025-04-05 09:00
C-52-598-03-EI-2210 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.6 | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-03-CI-2000, C-52-598-03-CI-1410, C-52-598-03-PI-1200 | C-52-598-03-CI-2000: SS 7, C-52-598-03-CI-1410: FS, C-52-598-03-PI-1200: FF 14 | C-52-598-03-CI-3010, C-52-598-03-EI-1210, C-52-598-03-CI-2400, C-52-598-03-EI-1800, C-52-598-03-EI-2200 | C-52-598-03-CI-3010: FS, C-52-598-03-EI-1210: FS, C-52-598-03-CI-2400: FS, C-52-598-03-EI-1800: FS, C-52-598-03-EI-2200: FS | 2025-05-17 07:00 | 2025-06-02 17:00
C-52-598-03-CI-3000 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.11 | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-03-CI-2000, C-52-598-03-PI-1400, C-52-598-03-CI-1420, HS-CN-0690, HM-CS-0120, HM-CS-0110 | C-52-598-03-CI-2000: FS, C-52-598-03-PI-1400: FF 3, C-52-598-03-CI-1420: FS, HS-CN-0690: FS, HM-CS-0120: FS, HM-CS-0110: FS | C-52-598-03-CI-3010, PRECOM-56-59803-1000 | C-52-598-03-CI-3010: FS, PRECOM-56-59803-1000: FS | 2025-04-17 09:00 | 2025-05-20 17:00
C-52-598-03-CI-3010 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.11 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-03-EI-2210, C-52-598-03-CI-3000 | C-52-598-03-EI-2210: FS, C-52-598-03-CI-3000: FS | PRECOM-56-59803-1000 | PRECOM-56-59803-1000: FS | 2025-06-03 07:00 | 2025-06-20 17:00
C-52-598-03-EI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.3 | Installation of Solar Panel Structural Supports | C-52-598-03-EI-2210, HE-HS-0350, HE-EL-0640, HE-IC-0770, HM-IC-0050, HM-ME-0890, HE-IC-1550, HE-IC-0010, HM-EL-0380, HM-EL-0520, HM-EL-0280, HE-IC-1430, HM-IC-0040, HE-EL-1010, HE-EL-0770, HE-IC-0650, HE-EL-0350, HE-IC-0530, HE-IC-2570, HE-EL-0530, HE-EL-1 | C-52-598-03-EI-2210: FS, HE-HS-0350: FS, HE-EL-0640: FS, HE-IC-0770: FS, HM-IC-0050: FF, HM-ME-0890: FS, HE-IC-1550: FF, HE-IC-0010: SS 10, HM-EL-0380: FS, HM-EL-0520: FS, HM-EL-0280: FS, HE-IC-1430: FS, HM-IC-0040: FS, HE-EL-1010: FS, HE-EL-0770: FS, HE-I | C-52-598-03-EI-1200 | C-52-598-03-EI-1200: FS | 2025-06-03 07:00 | 2025-06-18 17:00
C-52-598-03-CI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.9 | Installation of Fire Point Shelters | C-52-598-03-EI-2210, HM-CS-0110 | C-52-598-03-EI-2210: FS, HM-CS-0110: FS | C-52-598-03-ME-1000 | C-52-598-03-ME-1000: FS | 2025-06-03 07:00 | 2025-06-13 17:00
C-52-598-02-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.6 | Pre-Fabrication & Installation of Pipe Supports | C-52-598-02-CI-1600, HE-CS-1430, HS-CN-0690, HM-CS-0120, HE-CS-1490, HM-CS-0110 | C-52-598-02-CI-1600: FF 7, HE-CS-1430: FS, HS-CN-0690: FS, HM-CS-0120: FS, HE-CS-1490: FS, HM-CS-0110: FS | C-52-598-02-EI-2210, C-52-598-02-CI-3000, C-52-598-02-PI-1200 | C-52-598-02-EI-2210: SS 7, C-52-598-02-CI-3000: FS, C-52-598-02-PI-1200: FS | 2025-03-12 09:00 | 2025-04-05 09:00
C-52-598-02-EI-2210 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.6 | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-02-CI-2000, C-52-598-02-CI-1410, C-52-598-02-PI-1200 | C-52-598-02-CI-2000: SS 7, C-52-598-02-CI-1410: FF 7, C-52-598-02-PI-1200: FF 5 | C-52-598-02-CI-3010, C-52-598-02-CI-2400, C-52-598-02-EI-1800, C-52-598-02-EI-2200 | C-52-598-02-CI-3010: FS, C-52-598-02-CI-2400: FS, C-52-598-02-EI-1800: FS, C-52-598-02-EI-2200: FS | 2025-04-10 14:00 | 2025-04-26 14:00
C-52-598-02-CI-3000 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.11 | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-02-CI-2000, C-52-598-02-CI-1420, C-52-598-02-PI-1400, HM-CS-0110, HM-CS-0120, HS-CN-0690 | C-52-598-02-CI-2000: FS, C-52-598-02-CI-1420: FF 7, C-52-598-02-PI-1400: FF 3, HM-CS-0110: FS, HM-CS-0120: FS, HS-CN-0690: FS | C-52-598-02-CI-3010, PRECOM-56-59802-1000 | C-52-598-02-CI-3010: FF 3, PRECOM-56-59802-1000: FS | 2025-04-05 09:00 | 2025-05-08 16:00
C-52-598-02-CI-3010 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.11 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-02-EI-2210, C-52-598-02-CI-1420, C-52-598-02-CI-3000, HM-CS-0110, HM-CS-0120, HS-CN-0690 | C-52-598-02-EI-2210: FS, C-52-598-02-CI-1420: FF 7, C-52-598-02-CI-3000: FF 3, HM-CS-0110: FS, HM-CS-0120: FS, HS-CN-0690: FS | C-52-598-02-CI-2220, PRECOM-56-59802-1000 | C-52-598-02-CI-2220: FF, PRECOM-56-59802-1000: FS | 2025-04-26 14:00 | 2025-05-14 12:00
C-52-598-02-EI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.3 | Installation of Solar Panel Structural Supports | C-52-598-02-CI-1400, HE-IC-1550, HM-EL-0520, HE-EL-1010, HE-EL-1730, HE-IC-0710, HE-IC-1430, ML1032-B21, HE-HS-0350, HM-EL-0530, HE-IC-0770, HS-CN-0240, HM-ME-1690, HE-IC-0650, HE-IC-0490, HE-EL-1670, HM-EL-0380, HE-IC-0530, HM-ME-1090, HE-EL-1790, HE-IC-0 | C-52-598-02-CI-1400: FS, HE-IC-1550: FF, HM-EL-0520: FS, HE-EL-1010: FS, HE-EL-1730: FS, HE-IC-0710: FS, HE-IC-1430: FS, ML1032-B21: FS, HE-HS-0350: FS, HM-EL-0530: FF, HE-IC-0770: FS, HS-CN-0240: FS, HM-ME-1690: FF, HE-IC-0650: FS, HE-IC-0490: FS, HE-EL-1 | C-52-598-02-EI-1200 | C-52-598-02-EI-1200: FS | 2025-05-07 14:00 | 2025-05-22 07:00
C-52-598-02-CI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.8 | Installation of Fire Point Shelters | C-52-598-02-EI-2210, HM-CS-0110 | C-52-598-02-EI-2210: FS, HM-CS-0110: FS | C-52-598-02-ME-1000 | C-52-598-02-ME-1000: FS 30 | 2025-04-26 14:00 | 2025-05-07 09:00
C-52-598-01-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.6 | Pre-Fabrication & Installation of Pipe Supports | C-52-598-01-CI-1600, HE-CS-1490, HS-CN-0690, HE-CS-1430, HM-CS-0120, HM-CS-0110 | C-52-598-01-CI-1600: FS 7, HE-CS-1490: FS, HS-CN-0690: FS, HE-CS-1430: FS, HM-CS-0120: FS, HM-CS-0110: FS | C-52-598-01-EI-2210, C-52-598-01-CI-3000, C-52-598-01-PI-1200 | C-52-598-01-EI-2210: SS 7, C-52-598-01-CI-3000: FS, C-52-598-01-PI-1200: FS | 2025-03-12 09:00 | 2025-04-05 09:00
C-52-598-01-EI-2210 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.7 | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-01-CI-2000, C-52-598-01-CI-1410, C-52-598-01-PI-1200 | C-52-598-01-CI-2000: SS 7, C-52-598-01-CI-1410: FF 7, C-52-598-01-PI-1200: FF 14 | C-52-598-01-CI-3010, C-52-598-01-CI-2400, C-52-598-01-EI-1800, C-52-598-01-EI-2200 | C-52-598-01-CI-3010: FS, C-52-598-01-CI-2400: FS, C-52-598-01-EI-1800: FS, C-52-598-01-EI-2200: FS | 2025-04-22 09:00 | 2025-05-08 16:00
C-52-598-01-CI-3000 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.11 | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-01-CI-2000, C-52-598-01-CI-1420, C-52-598-01-PI-1400, HM-CS-0110, HS-CN-0690, HM-CS-0120 | C-52-598-01-CI-2000: FS, C-52-598-01-CI-1420: FF 7, C-52-598-01-PI-1400: FF 3, HM-CS-0110: FS, HS-CN-0690: FS, HM-CS-0120: FS | C-52-598-01-CI-3010, PRECOM-56-59801-1000 | C-52-598-01-CI-3010: FF 3, PRECOM-56-59801-1000: FS | 2025-04-05 09:00 | 2025-05-08 16:00
C-52-598-01-CI-3010 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.11 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-01-EI-2210, C-52-598-01-CI-1420, C-52-598-01-CI-3000, HM-CS-0110, HS-CN-0690, HM-CS-0120 | C-52-598-01-EI-2210: FS, C-52-598-01-CI-1420: FF 7, C-52-598-01-CI-3000: FF 3, HM-CS-0110: FS, HS-CN-0690: FS, HM-CS-0120: FS | PRECOM-56-59801-1000 | PRECOM-56-59801-1000: FS | 2025-05-09 07:00 | 2025-05-24 17:00
C-52-598-01-EI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.2 | Installation of Solar Panel Structural Supports | C-52-598-01-CI-1400, HM-ME-1590, HE-IC-1550, ML1429-D17, HE-IC-0770, HM-IC-0050, HM-EL-0380, HE-EL-0640, HE-EL-0770, ML1032-B21, HM-ME-1690, HM-EL-0530, HM-ME-1090, HE-IC-1430, HE-IC-0530, HM-IC-0040, HM-EL-0080, HE-EL-1010, HE-EL-1730, HE-IC-0710, HE-EL-0 | C-52-598-01-CI-1400: FS, HM-ME-1590: FF, HE-IC-1550: FF, ML1429-D17: FS, HE-IC-0770: FS, HM-IC-0050: FF, HM-EL-0380: FS, HE-EL-0640: FS, HE-EL-0770: FS, ML1032-B21: FS, HM-ME-1690: FF, HM-EL-0530: FF, HM-ME-1090: FS, HE-IC-1430: FS, HE-IC-0530: FS, HM-IC-0 | C-52-598-01-EI-1200 | C-52-598-01-EI-1200: FS | 2025-05-03 09:00 | 2025-05-17 17:00
C-52-598-01-CI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.8 | Installation of Fire Point Shelters | C-52-598-01-EI-2210, HM-CS-0110 | C-52-598-01-EI-2210: FS, HM-CS-0110: FS | C-52-598-01-ME-1000 | C-52-598-01-ME-1000: FS | 2025-05-09 07:00 | 2025-05-17 17:00
C-52-598-05-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.3.1 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | C-52-598-05-CI-2400, C-52-598-05-CI-1400, ML1015-B08, HM-ME-1990, HM-ME-2370 | C-52-598-05-CI-2400: FS 14, C-52-598-05-CI-1400: FS, ML1015-B08: FS, HM-ME-1990: FS, HM-ME-2370: FS | PRECOM-56-59805-1000 | PRECOM-56-59805-1000: FS | 2025-06-23 07:00 | 2025-07-02 17:00
C-52-598-04-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.3.1 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | C-52-598-04-CI-2400, ML1015-B08, HM-ME-1990, HM-ME-2370 | C-52-598-04-CI-2400: FS 15, ML1015-B08: FS, HM-ME-1990: FS, HM-ME-2370: FS | PRECOM-56-59804-1000 | PRECOM-56-59804-1000: FS | 2025-05-23 07:00 | 2025-05-31 17:00
C-52-598-03-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.3.1 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | C-52-598-03-CI-2400, HM-ME-1990, ML1015-B08, HM-ME-2370 | C-52-598-03-CI-2400: FS, HM-ME-1990: FS, ML1015-B08: FS, HM-ME-2370: FS | PRECOM-56-59803-1000 | PRECOM-56-59803-1000: FS | 2025-06-14 07:00 | 2025-06-23 17:00
C-52-598-02-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.3.1 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | C-52-598-02-CI-2400, HM-ME-1990, ML1015-B08, HM-ME-2370 | C-52-598-02-CI-2400: FS 30, HM-ME-1990: FS, ML1015-B08: FS, HM-ME-2370: FS | PRECOM-56-59802-1000 | PRECOM-56-59802-1000: FS | 2025-06-13 12:00 | 2025-06-23 12:00
C-52-598-01-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.3.1 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | C-52-598-01-CI-2400, ML1015-B08, HM-ME-1990, HM-ME-2370 | C-52-598-01-CI-2400: FS, ML1015-B08: FS, HM-ME-1990: FS, HM-ME-2370: FS | PRECOM-56-59801-1000 | PRECOM-56-59801-1000: FS | 2025-05-19 07:00 | 2025-05-27 17:00
C-52-598-05-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.4.1 | Piping Pre-Fabrication | C-52-598-05-CI-2000, ML1002, HM-PI-0040, HE-PI-0580, HM-PI-0050, ML1219-B19, HE-PI-1300, HS-CN-0190, HE-PR-0290, HE-PR-0890, HE-PI-0880, ML1179-B11, HE-PI-1240 | C-52-598-05-CI-2000: FS, ML1002: FS, HM-PI-0040: FS, HE-PI-0580: FS, HM-PI-0050: FS, ML1219-B19: FS, HE-PI-1300: FS, HS-CN-0190: FS, HE-PR-0290: FS, HE-PR-0890: FS, HE-PI-0880: FS, ML1179-B11: FS, HE-PI-1240: FS | C-52-598-05-PI-1200, C-52-598-05-PL-1000 | C-52-598-05-PI-1200: FS, C-52-598-05-PL-1000: FS | 2025-04-05 09:00 | 2025-04-30 09:00
C-52-598-05-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.4.2 | Piping Erection | C-52-598-05-PI-1000, C-52-598-05-CI-2000, ML1002, HM-PI-0040, HM-PI-0050, HM-PL-0630, ML1219-B19, HE-PI-1300, HM-PL-0740, HS-CN-0190, HM-PL-0220, HE-PR-0290, HE-PR-0890, HE-PI-0880, ML1179-B11, HM-PL-0640, HE-PI-1240, HM-PL-1510, HM-PL-1570 | C-52-598-05-PI-1000: FS, C-52-598-05-CI-2000: FS, ML1002: FS, HM-PI-0040: FS, HM-PI-0050: FS, HM-PL-0630: FS, ML1219-B19: FS, HE-PI-1300: FS, HM-PL-0740: FS, HS-CN-0190: FS, HM-PL-0220: FS, HE-PR-0290: FS, HE-PR-0890: FS, HE-PI-0880: FS, ML1179-B11: FS, HM | C-52-598-05-PI-1400, C-52-598-05-EI-2210 | C-52-598-05-PI-1400: SS 2, C-52-598-05-EI-2210: FF 7 | 2025-04-30 09:00 | 2025-05-16 17:00
C-52-598-05-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.4.3 | Field Joint Welding (Including Isolation Joint) | C-52-598-05-PI-1200, HE-PI-1300, ML1002, ML1219-B19, HS-CN-0190, ML1179-B11 | C-52-598-05-PI-1200: SS 2, HE-PI-1300: FS, ML1002: FS, ML1219-B19: FS, HS-CN-0190: FS, ML1179-B11: FS | C-52-598-05-PI-1410, C-52-598-05-CI-3000, C-52-598-05-EI-2200 | C-52-598-05-PI-1410: SS 3, C-52-598-05-CI-3000: FS, C-52-598-05-EI-2200: FF 3 | 2025-05-02 09:00 | 2025-05-16 17:00
C-52-598-05-PI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.4.3 | NDT & Coating for Field Joint Weld | C-52-598-05-PI-1400 | C-52-598-05-PI-1400: SS 3 | C-52-598-05-PI-1600 | C-52-598-05-PI-1600: FS | 2025-05-06 12:00 | 2025-05-20 17:00
C-52-598-05-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.4.4 | Hydrotesting | C-52-598-05-PI-1410, ML1219-B19, ML1179-B11 | C-52-598-05-PI-1410: FS, ML1219-B19: FS, ML1179-B11: FS | C-52-598-05-PI-1800 | C-52-598-05-PI-1800: FS | 2025-05-21 07:00 | 2025-05-26 17:00
C-52-598-05-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.4.5 | Installation of Valves & GOV | C-52-598-05-PI-1600, HM-PL-0630, ML1219-B19, HM-PL-0740, HM-PL-0220, HE-PR-0290, HE-PR-0890, HE-PI-0880, ML1179-B11, HM-PL-0640, HE-PI-1240, HM-PL-1510, HM-PL-1570, HM-ME-0580, HM-ME-2210 | C-52-598-05-PI-1600: FS, HM-PL-0630: FS, ML1219-B19: FS, HM-PL-0740: FS, HM-PL-0220: FS, HE-PR-0290: FS, HE-PR-0890: FS, HE-PI-0880: FS, ML1179-B11: FS, HM-PL-0640: FS, HE-PI-1240: FS, HM-PL-1510: FS, HM-PL-1570: FS, HM-ME-0580: FS, HM-ME-2210: FS | C-52-598-05-PI-2000, PRECOM-56-59805-1000 | C-52-598-05-PI-2000: SS 4, PRECOM-56-59805-1000: FS | 2025-07-21 07:00 | 2025-07-25 17:00
C-52-598-05-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.4.6 | Final Bolt Torquing/ Re-Instatement | C-52-598-05-PI-1800, HE-PI-1300, ML1002, HM-PL-0630, ML1219-B19, HM-PL-0740, HS-CN-0190, HM-PL-0220, HE-PR-0290, HE-PR-0890, HE-PI-0880, ML1179-B11, HM-PL-0640, HE-PI-1240, HM-PL-1510, HM-PL-1570 | C-52-598-05-PI-1800: SS 4, HE-PI-1300: FS, ML1002: FS, HM-PL-0630: FS, ML1219-B19: FS, HM-PL-0740: FS, HS-CN-0190: FS, HM-PL-0220: FS, HE-PR-0290: FS, HE-PR-0890: FS, HE-PI-0880: FS, ML1179-B11: FS, HM-PL-0640: FS, HE-PI-1240: FS, HM-PL-1510: FS, HM-PL-157 | PRECOM-56-59805-1000 | PRECOM-56-59805-1000: FS | 2025-07-25 07:00 | 2025-07-28 17:00
C-52-598-04-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.4.1 | Piping Pre-Fabrication | ML1002, ML1179-B11, HE-PR-0890, HE-PI-0580, HM-PI-0040, HE-PI-1240, HE-PI-0880, HE-PI-1300, ML1219-B19, HE-PR-0290, HS-CN-0190 | ML1002: FS, ML1179-B11: FS, HE-PR-0890: FS, HE-PI-0580: FS, HM-PI-0040: FS, HE-PI-1240: FS, HE-PI-0880: FS, HE-PI-1300: FS, ML1219-B19: FS, HE-PR-0290: FS, HS-CN-0190: FS | C-52-598-04-PI-1200, C-52-598-04-PL-1000 | C-52-598-04-PI-1200: FS, C-52-598-04-PL-1000: FS | 2025-02-24 07:00 | 2025-03-24 13:00
C-52-598-04-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.4.2 | Piping Erection | C-52-598-04-PI-1000, C-52-598-04-CI-2000, ML1002, ML1179-B11, HE-PR-0890, HM-PI-0040, HE-PI-1240, HE-PI-1300, ML1219-B19, HM-PL-0220, HM-PL-0740, HM-PL-0630, HE-PR-0290, HM-PL-0640, HS-CN-0190, HM-PI-0050, HM-PL-1510, HM-PL-1570 | C-52-598-04-PI-1000: FS, C-52-598-04-CI-2000: FS, ML1002: FS, ML1179-B11: FS, HE-PR-0890: FS, HM-PI-0040: FS, HE-PI-1240: FS, HE-PI-1300: FS, ML1219-B19: FS, HM-PL-0220: FS, HM-PL-0740: FS, HM-PL-0630: FS, HE-PR-0290: FS, HM-PL-0640: FS, HS-CN-0190: FS, HM | C-52-598-04-PI-1400, C-52-598-04-EI-2210 | C-52-598-04-PI-1400: SS 2, C-52-598-04-EI-2210: FF 3 | 2025-04-05 09:00 | 2025-04-22 09:00
C-52-598-04-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.4.3 | Field Joint Welding (Including Isolation Joint) | C-52-598-04-PI-1200, HE-PI-1300, ML1002, ML1179-B11, ML1219-B19, HS-CN-0190 | C-52-598-04-PI-1200: SS 2, HE-PI-1300: FS, ML1002: FS, ML1179-B11: FS, ML1219-B19: FS, HS-CN-0190: FS | C-52-598-04-PI-1410, C-52-598-04-CI-3000, C-52-598-04-CI-3010, C-52-598-04-EI-2200 | C-52-598-04-PI-1410: SS 3, C-52-598-04-CI-3000: FS, C-52-598-04-CI-3010: FF 3, C-52-598-04-EI-2200: FF 2 | 2025-04-08 09:00 | 2025-04-22 09:00
C-52-598-04-PI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.4.3 | NDT & Coating for Field Joint Weld | C-52-598-04-PI-1400 | C-52-598-04-PI-1400: SS 3 | C-52-598-04-PI-1600 | C-52-598-04-PI-1600: FS | 2025-04-11 09:00 | 2025-04-25 09:00
C-52-598-04-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.4.4 | Hydrotesting | C-52-598-04-PI-1410, ML1179-B11, ML1219-B19 | C-52-598-04-PI-1410: FS, ML1179-B11: FS, ML1219-B19: FS | C-52-598-04-PI-1800 | C-52-598-04-PI-1800: FS | 2025-04-25 09:00 | 2025-05-01 09:00
C-52-598-04-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.4.5 | Installation of Valves & GOV | C-52-598-04-PI-1600, HE-PI-1300, ML1002, ML1179-B11, HE-PR-0890, HE-PI-1240, ML1219-B19, HM-PL-0220, HM-PL-0740, HM-PL-0630, HE-PR-0290, HM-PL-0640, HS-CN-0190, HM-PL-1510, HM-PL-1570, HM-ME-0580, HM-ME-2210 | C-52-598-04-PI-1600: FS, HE-PI-1300: FS, ML1002: FS, ML1179-B11: FS, HE-PR-0890: FS, HE-PI-1240: FS, ML1219-B19: FS, HM-PL-0220: FS, HM-PL-0740: FS, HM-PL-0630: FS, HE-PR-0290: FS, HM-PL-0640: FS, HS-CN-0190: FS, HM-PL-1510: FS, HM-PL-1570: FS, HM-ME-0580: | C-52-598-04-PI-2000, PRECOM-56-59804-1000 | C-52-598-04-PI-2000: SS 4, PRECOM-56-59804-1000: FS | 2025-07-21 07:00 | 2025-07-25 17:00
C-52-598-04-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.4.6 | Final Bolt Torquing/ Re-Instatement | C-52-598-04-PI-1800, HE-PI-1300, ML1002, ML1179-B11, HE-PR-0890, HE-PI-1240, ML1219-B19, HM-PL-0220, HM-PL-0740, HM-PL-0630, HE-PR-0290, HM-PL-0640, HS-CN-0190, HM-PL-1510, HM-PL-1570 | C-52-598-04-PI-1800: SS 4, HE-PI-1300: FS, ML1002: FS, ML1179-B11: FS, HE-PR-0890: FS, HE-PI-1240: FS, ML1219-B19: FS, HM-PL-0220: FS, HM-PL-0740: FS, HM-PL-0630: FS, HE-PR-0290: FS, HM-PL-0640: FS, HS-CN-0190: FS, HM-PL-1510: FS, HM-PL-1570: FS | PRECOM-56-59804-1000 | PRECOM-56-59804-1000: FS | 2025-07-25 07:00 | 2025-07-28 17:00
C-52-598-03-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.4.1 | Piping Pre-Fabrication | ML1002, HE-PR-0890, HE-PR-0290, HE-PI-0580, HE-PI-0880, HE-PI-1240, HM-PI-0040, HE-PI-1300, HS-CN-0190, ML1179-B11, ML1219-B19, C-52-598-03-CI-2000 | ML1002: FS, HE-PR-0890: FS, HE-PR-0290: FS, HE-PI-0580: FS, HE-PI-0880: FS, HE-PI-1240: FS, HM-PI-0040: FS, HE-PI-1300: FS, HS-CN-0190: FS, ML1179-B11: FS, ML1219-B19: FS, C-52-598-03-CI-2000: FS | C-52-598-03-PI-1200, C-52-598-03-PL-1000 | C-52-598-03-PI-1200: FS, C-52-598-03-PL-1000: FS | 2025-04-05 09:00 | 2025-04-30 09:00
C-52-598-03-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.4.2 | Piping Erection | C-52-598-03-PI-1000, C-52-598-03-CI-2000, ML1002, HE-PR-0890, HM-PL-0740, HE-PR-0290, HM-PL-0640, HE-PI-1240, HM-PI-0040, HM-PL-0630, HE-PI-1300, HM-PI-0050, HS-CN-0190, HM-PL-0220, ML1179-B11, ML1219-B19, HM-PL-1510, HM-PL-1570 | C-52-598-03-PI-1000: FS, C-52-598-03-CI-2000: FS, ML1002: FS, HE-PR-0890: FS, HM-PL-0740: FS, HE-PR-0290: FS, HM-PL-0640: FS, HE-PI-1240: FS, HM-PI-0040: FS, HM-PL-0630: FS, HE-PI-1300: FS, HM-PI-0050: FS, HS-CN-0190: FS, HM-PL-0220: FS, ML1179-B11: FS, ML | C-52-598-03-PI-1400, C-52-598-03-EI-2210 | C-52-598-03-PI-1400: SS 2, C-52-598-03-EI-2210: FF 14 | 2025-04-30 09:00 | 2025-05-16 17:00
C-52-598-03-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.4.3 | Field Joint Welding (Including Isolation Joint) | C-52-598-03-PI-1200, HE-PI-1300, ML1002, HS-CN-0190, ML1179-B11, ML1219-B19 | C-52-598-03-PI-1200: SS 2, HE-PI-1300: FS, ML1002: FS, HS-CN-0190: FS, ML1179-B11: FS, ML1219-B19: FS | C-52-598-03-PI-1410, C-52-598-03-CI-3000 | C-52-598-03-PI-1410: SS 3, C-52-598-03-CI-3000: FF 3 | 2025-05-02 09:00 | 2025-05-16 17:00
C-52-598-03-PI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.4.3 | NDT & Coating for Field Joint Weld | C-52-598-03-PI-1400 | C-52-598-03-PI-1400: SS 3 | C-52-598-03-PI-1600 | C-52-598-03-PI-1600: FS | 2025-05-06 12:00 | 2025-05-20 17:00
C-52-598-03-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.4.4 | Hydrotesting | C-52-598-03-PI-1410, ML1179-B11, ML1219-B19 | C-52-598-03-PI-1410: FS, ML1179-B11: FS, ML1219-B19: FS | C-52-598-03-PI-1800 | C-52-598-03-PI-1800: FS | 2025-05-21 07:00 | 2025-05-26 17:00
C-52-598-03-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.4.5 | Installation of Valves & GOV | C-52-598-03-PI-1600, HE-PI-1300, ML1002, HE-PR-0890, HM-PL-0740, HE-PR-0290, HM-PL-0640, HE-PI-1240, HM-PL-0630, HS-CN-0190, HM-PL-0220, ML1179-B11, ML1219-B19, HM-PL-1510, HM-PL-1570, HM-ME-0580, HM-ME-2210 | C-52-598-03-PI-1600: FS, HE-PI-1300: FS, ML1002: FS, HE-PR-0890: FS, HM-PL-0740: FS, HE-PR-0290: FS, HM-PL-0640: FS, HE-PI-1240: FS, HM-PL-0630: FS, HS-CN-0190: FS, HM-PL-0220: FS, ML1179-B11: FS, ML1219-B19: FS, HM-PL-1510: FS, HM-PL-1570: FS, HM-ME-0580: | C-52-598-03-PI-2000, PRECOM-56-59803-1000 | C-52-598-03-PI-2000: SS 4, PRECOM-56-59803-1000: FS | 2025-07-21 07:00 | 2025-07-25 17:00
C-52-598-03-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.4.6 | Final Bolt Torquing/ Re-Instatement | C-52-598-03-PI-1800, HE-PI-1300, ML1002, HE-PR-0890, HM-PL-0740, HE-PR-0290, HM-PL-0640, HE-PI-1240, HM-PL-0630, HS-CN-0190, HM-PL-0220, ML1179-B11, ML1219-B19, HM-PL-1510, HM-PL-1570 | C-52-598-03-PI-1800: SS 4, HE-PI-1300: FS, ML1002: FS, HE-PR-0890: FS, HM-PL-0740: FS, HE-PR-0290: FS, HM-PL-0640: FS, HE-PI-1240: FS, HM-PL-0630: FS, HS-CN-0190: FS, HM-PL-0220: FS, ML1179-B11: FS, ML1219-B19: FS, HM-PL-1510: FS, HM-PL-1570: FS | PRECOM-56-59803-1000 | PRECOM-56-59803-1000: FS | 2025-07-25 07:00 | 2025-07-28 17:00
C-52-598-02-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.4.1 | Piping Pre-Fabrication | ML1002, HS-CN-0190, ML1179-B11, HE-PI-0580, HE-PR-0290, ML1219-B19, HE-PI-0880, HM-PI-0040, HE-PI-1300, HE-PI-1240, HE-PR-0890 | ML1002: FS, HS-CN-0190: FS, ML1179-B11: FS, HE-PI-0580: FS, HE-PR-0290: FS, ML1219-B19: FS, HE-PI-0880: FS, HM-PI-0040: FS, HE-PI-1300: FS, HE-PI-1240: FS, HE-PR-0890: FS | C-52-598-02-PL-1000, C-52-598-02-PI-1200, C-52-598-02-PI-1200 | C-52-598-02-PL-1000: FS, C-52-598-02-PI-1200: SS 10, C-52-598-02-PI-1200: FF 7 | 2025-02-24 07:00 | 2025-03-24 13:00
C-52-598-02-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.4.2 | Piping Erection | C-52-598-02-CI-2000, ML1002, HS-CN-0190, ML1179-B11, HM-PL-0630, HM-PL-0640, HE-PR-0290, HM-PL-0220, HM-PL-0740, HM-PI-0050, ML1219-B19, HM-PI-0040, HE-PI-1300, HE-PI-1240, HE-PR-0890, HM-PL-1510, HM-PL-1570, C-52-598-02-PI-1000, C-52-598-02-PI-1000 | C-52-598-02-CI-2000: FS, ML1002: FS, HS-CN-0190: FS, ML1179-B11: FS, HM-PL-0630: FS, HM-PL-0640: FS, HE-PR-0290: FS, HM-PL-0220: FS, HM-PL-0740: FS, HM-PI-0050: FS, ML1219-B19: FS, HM-PI-0040: FS, HE-PI-1300: FS, HE-PI-1240: FS, HE-PR-0890: FS, HM-PL-1510: | C-52-598-02-PI-1400, C-52-598-02-EI-2210 | C-52-598-02-PI-1400: SS 2, C-52-598-02-EI-2210: FF 5 | 2025-04-05 09:00 | 2025-04-22 09:00
C-52-598-02-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.4.3 | Field Joint Welding (Including Isolation Joint) | C-52-598-02-PI-1200, HE-PI-1300, ML1002, HS-CN-0190, ML1179-B11, ML1219-B19 | C-52-598-02-PI-1200: SS 2, HE-PI-1300: FS, ML1002: FS, HS-CN-0190: FS, ML1179-B11: FS, ML1219-B19: FS | C-52-598-02-PI-1410, C-52-598-02-CI-3000 | C-52-598-02-PI-1410: SS 3, C-52-598-02-CI-3000: FF 3 | 2025-04-08 09:00 | 2025-04-22 09:00
C-52-598-02-PI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.4.3 | NDT & Coating for Field Joint Weld | C-52-598-02-PI-1400 | C-52-598-02-PI-1400: SS 3 | C-52-598-02-PI-1600 | C-52-598-02-PI-1600: FS | 2025-04-11 09:00 | 2025-04-25 09:00
C-52-598-02-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.4.4 | Hydrotesting | C-52-598-02-PI-1410, ML1179-B11, ML1219-B19 | C-52-598-02-PI-1410: FS, ML1179-B11: FS, ML1219-B19: FS | C-52-598-02-PI-1800 | C-52-598-02-PI-1800: FS | 2025-04-25 09:00 | 2025-05-01 09:00
C-52-598-02-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.4.5 | Installation of Valves & GOV | C-52-598-02-PI-1600, HE-PI-1300, ML1002, HS-CN-0190, ML1179-B11, HM-PL-0630, HM-PL-0640, HE-PR-0290, HM-PL-0220, HM-PL-0740, ML1219-B19, HE-PI-1240, HE-PR-0890, HM-PL-1510, HM-PL-1570, HM-ME-0580, HM-ME-2210 | C-52-598-02-PI-1600: FS, HE-PI-1300: FS, ML1002: FS, HS-CN-0190: FS, ML1179-B11: FS, HM-PL-0630: FS, HM-PL-0640: FS, HE-PR-0290: FS, HM-PL-0220: FS, HM-PL-0740: FS, ML1219-B19: FS, HE-PI-1240: FS, HE-PR-0890: FS, HM-PL-1510: FS, HM-PL-1570: FS, HM-ME-0580: | C-52-598-02-PI-2000, PRECOM-56-59802-1000 | C-52-598-02-PI-2000: SS 4, PRECOM-56-59802-1000: FS | 2025-07-21 07:00 | 2025-07-25 17:00
C-52-598-02-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.4.6 | Final Bolt Torquing/ Re-Instatement | C-52-598-02-PI-1800, HE-PI-1300, ML1002, HS-CN-0190, ML1179-B11, HM-PL-0630, HM-PL-0640, HE-PR-0290, HM-PL-0220, HM-PL-0740, ML1219-B19, HE-PI-1240, HE-PR-0890, HM-PL-1510, HM-PL-1570 | C-52-598-02-PI-1800: SS 4, HE-PI-1300: FS, ML1002: FS, HS-CN-0190: FS, ML1179-B11: FS, HM-PL-0630: FS, HM-PL-0640: FS, HE-PR-0290: FS, HM-PL-0220: FS, HM-PL-0740: FS, ML1219-B19: FS, HE-PI-1240: FS, HE-PR-0890: FS, HM-PL-1510: FS, HM-PL-1570: FS | PRECOM-56-59802-1000 | PRECOM-56-59802-1000: FS | 2025-07-25 07:00 | 2025-07-28 17:00
C-52-598-01-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.4.1 | Piping Pre-Fabrication | ML1002, ML1219-B19, HE-PI-0580, HE-PI-0880, ML1179-B11, HE-PI-1300, HE-PR-0290, HM-PI-0040, HE-PR-0890, HE-PI-1240 | ML1002: FS, ML1219-B19: FS, HE-PI-0580: FS, HE-PI-0880: FS, ML1179-B11: FS, HE-PI-1300: FS, HE-PR-0290: FS, HM-PI-0040: FS, HE-PR-0890: FS, HE-PI-1240: FS | C-52-598-01-PI-1200, C-52-598-01-PL-1000 | C-52-598-01-PI-1200: FS, C-52-598-01-PL-1000: FS | 2025-02-24 07:00 | 2025-03-24 13:00
C-52-598-01-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.4.2 | Piping Erection | C-52-598-01-PI-1000, C-52-598-01-CI-2000, ML1002, ML1219-B19, HM-PL-0220, HM-PL-0740, ML1179-B11, HM-PL-0630, HE-PI-1300, HE-PR-0290, HM-PI-0040, HM-PI-0050, ML1539-D21, HE-PR-0890, HM-PL-0640, HE-PI-1240, HM-PL-1510, HM-PL-1570 | C-52-598-01-PI-1000: FS, C-52-598-01-CI-2000: FS, ML1002: FS, ML1219-B19: FS, HM-PL-0220: FS, HM-PL-0740: FS, ML1179-B11: FS, HM-PL-0630: FS, HE-PI-1300: FS, HE-PR-0290: FS, HM-PI-0040: FS, HM-PI-0050: FS, ML1539-D21: FS, HE-PR-0890: FS, HM-PL-0640: FS, HE | C-52-598-01-PI-1400, C-52-598-01-EI-2210 | C-52-598-01-PI-1400: SS 2, C-52-598-01-EI-2210: FF 14 | 2025-04-05 09:00 | 2025-04-22 09:00
C-52-598-01-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.4.3 | Field Joint Welding (Including Isolation Joint) | C-52-598-01-PI-1200, HE-PI-1300, ML1002 | C-52-598-01-PI-1200: SS 2, HE-PI-1300: FS, ML1002: FS | C-52-598-01-PI-1410, C-52-598-01-CI-3000 | C-52-598-01-PI-1410: SS 3, C-52-598-01-CI-3000: FF 3 | 2025-04-08 09:00 | 2025-04-22 09:00
C-52-598-01-PI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.4.3 | NDT & Coating for Field Joint Weld | C-52-598-01-PI-1400 | C-52-598-01-PI-1400: SS 3 | C-52-598-01-PI-1600 | C-52-598-01-PI-1600: FS | 2025-04-11 09:00 | 2025-04-25 09:00
C-52-598-01-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.4.4 | Hydrotesting | C-52-598-01-PI-1410, ML1219-B19, HM-PL-0220, ML1179-B11, HE-PI-1300, HE-PR-0290, HM-PI-0040, HM-PI-0050, HE-PR-0890, HE-PI-1240 | C-52-598-01-PI-1410: FS, ML1219-B19: FS, HM-PL-0220: FS, ML1179-B11: FS, HE-PI-1300: FS, HE-PR-0290: FS, HM-PI-0040: FS, HM-PI-0050: FS, HE-PR-0890: FS, HE-PI-1240: FS | C-52-598-01-PI-1800 | C-52-598-01-PI-1800: FS | 2025-04-25 09:00 | 2025-05-01 09:00
C-52-598-01-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.4.5 | Installation of Valves & GOV | C-52-598-01-PI-1600, HE-PI-1300, ML1002, ML1219-B19, HM-PL-0220, HM-PL-0740, ML1179-B11, HM-PL-0630, HE-PR-0290, ML1529-D20, ML1539-D21, HE-PR-0890, HM-PL-0640, HE-PI-1240, HM-PL-1510, HM-PL-1570, HM-ME-0580, HM-ME-2210 | C-52-598-01-PI-1600: FS, HE-PI-1300: FS, ML1002: FS, ML1219-B19: FS, HM-PL-0220: FS, HM-PL-0740: FS, ML1179-B11: FS, HM-PL-0630: FS, HE-PR-0290: FS, ML1529-D20: FS, ML1539-D21: FS, HE-PR-0890: FS, HM-PL-0640: FS, HE-PI-1240: FS, HM-PL-1510: FS, HM-PL-1570: | C-52-598-01-PI-2000, PRECOM-56-59801-1000 | C-52-598-01-PI-2000: SS 4, PRECOM-56-59801-1000: FS | 2025-07-21 07:00 | 2025-07-25 17:00
C-52-598-01-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.4.6 | Final Bolt Torquing/ Re-Instatement | C-52-598-01-PI-1800, ML1002, ML1219-B19, HM-PL-0220, HM-PL-0740, ML1179-B11, HM-PL-0630, HE-PI-1300, HE-PR-0290, HM-PI-0040, HM-PI-0050, ML1529-D20, ML1539-D21, HE-PR-0890, HM-PL-0640, HE-PI-1240, HM-PL-1510, HM-PL-1570 | C-52-598-01-PI-1800: SS 4, ML1002: FS, ML1219-B19: FS, HM-PL-0220: FS, HM-PL-0740: FS, ML1179-B11: FS, HM-PL-0630: FS, HE-PI-1300: FS, HE-PR-0290: FS, HM-PI-0040: FS, HM-PI-0050: FS, ML1529-D20: FS, ML1539-D21: FS, HE-PR-0890: FS, HM-PL-0640: FS, HE-PI-124 | PRECOM-56-59801-1000 | PRECOM-56-59801-1000: FS | 2025-07-25 07:00 | 2025-07-28 17:00
C-52-598-05-PL-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.5.1 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | C-52-598-05-PI-1000 | C-52-598-05-PI-1000: FS | C-52-598-05-PL-1010 | C-52-598-05-PL-1010: FS | 2025-04-30 09:00 | 2025-05-06 12:00
C-52-598-05-PL-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.5.1 | Lowering of Pipeline Section | C-52-598-05-PL-1000 | C-52-598-05-PL-1000: FS | C-52-598-05-PL-1020 | C-52-598-05-PL-1020: SS | 2025-05-06 12:00 | 2025-05-08 16:00
C-52-598-05-PL-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.5.1 | Section Tie-in Welding (Including Barred Tee) | C-52-598-05-PL-1010 | C-52-598-05-PL-1010: SS | C-52-598-05-PL-1030 | C-52-598-05-PL-1030: SS 1 | 2025-05-06 12:00 | 2025-05-20 17:00
C-52-598-05-PL-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.5.1 | NDT for Tie-in Joint | C-52-598-05-PL-1020 | C-52-598-05-PL-1020: SS 1 | C-52-598-05-PL-1040 | C-52-598-05-PL-1040: SS 1 | 2025-05-07 14:00 | 2025-05-21 17:00
C-52-598-05-PL-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.5.1 | Ext. Coating for Tie-in Joint | C-52-598-05-PL-1030 | C-52-598-05-PL-1030: SS 1 | C-52-598-05-PL-1050, PRECOM-56-59805-1000 | C-52-598-05-PL-1050: FS, PRECOM-56-59805-1000: FS | 2025-05-09 07:00 | 2025-05-22 17:00
C-52-598-05-PL-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.5.1 | Holiday Testing of Pipeline Section | C-52-598-05-PL-1040 | C-52-598-05-PL-1040: FS | C-52-598-05-PL-1060, C-52-598-05-PL-1090 | C-52-598-05-PL-1060: FS, C-52-598-05-PL-1090: FS | 2025-05-23 07:00 | 2025-05-23 17:00
C-52-598-05-PL-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.5.1 | Installation of ROV | C-52-598-05-PL-1050, HM-ME-0580, HM-ME-2210 | C-52-598-05-PL-1050: FS, HM-ME-0580: FS, HM-ME-2210: FS | C-52-598-05-PL-1070, C-52-598-05-PL-1090, PRECOM-56-59805-1000 | C-52-598-05-PL-1070: FS, C-52-598-05-PL-1090: FF 1, PRECOM-56-59805-1000: FS | 2025-07-21 07:00 | 2025-07-21 17:00
C-52-598-05-PL-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.5.1 | Installation of Pig Signaller Pit | C-52-598-05-PL-1060 | C-52-598-05-PL-1060: FS | C-52-598-05-PL-1080, C-52-598-05-PL-1090 | C-52-598-05-PL-1080: FS, C-52-598-05-PL-1090: FF 1 | 2025-07-22 07:00 | 2025-07-22 17:00
C-52-598-05-PL-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.5.1 | Installation of Pig Signaller | C-52-598-05-PL-1070 | C-52-598-05-PL-1070: FS | C-52-598-05-PL-1090, PRECOM-56-59805-1000 | C-52-598-05-PL-1090: FF, PRECOM-56-59805-1000: FS | 2025-07-23 07:00 | 2025-07-23 17:00
C-52-598-05-PL-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.5.1 | Padding & Backfilling | C-52-598-05-PL-1080, C-52-598-05-PL-1050, C-52-598-05-PL-1060, C-52-598-05-PL-1070 | C-52-598-05-PL-1080: FF, C-52-598-05-PL-1050: FS, C-52-598-05-PL-1060: FF 1, C-52-598-05-PL-1070: FF 1 | PRECOM-56-59805-1000 | PRECOM-56-59805-1000: FS | 2025-07-14 07:00 | 2025-07-23 17:00
C-52-598-04-PL-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.5.1 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | C-52-598-04-PI-1000 | C-52-598-04-PI-1000: FS | C-52-598-04-PL-1010 | C-52-598-04-PL-1010: FS | 2025-03-25 07:00 | 2025-04-04 13:00
C-52-598-04-PL-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.5.1 | Lowering of Pipeline Section | C-52-598-04-PL-1000 | C-52-598-04-PL-1000: FS | C-52-598-04-PL-1020 | C-52-598-04-PL-1020: SS | 2025-04-04 13:00 | 2025-04-07 13:00
C-52-598-04-PL-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.5.1 | Section Tie-in Welding (Including Barred Tee) | C-52-598-04-PL-1010 | C-52-598-04-PL-1010: SS | C-52-598-04-PL-1030 | C-52-598-04-PL-1030: SS 1 | 2025-04-04 13:00 | 2025-04-18 13:00
C-52-598-04-PL-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.5.1 | NDT for Tie-in Joint | C-52-598-04-PL-1020 | C-52-598-04-PL-1020: SS 1 | C-52-598-04-PL-1040 | C-52-598-04-PL-1040: SS 1 | 2025-04-05 13:00 | 2025-04-19 13:00
C-52-598-04-PL-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.5.1 | Ext. Coating for Tie-in Joint | C-52-598-04-PL-1030 | C-52-598-04-PL-1030: SS 1 | C-52-598-04-PL-1050, PRECOM-56-59804-1000 | C-52-598-04-PL-1050: FS, PRECOM-56-59804-1000: FS | 2025-04-07 13:00 | 2025-04-21 13:00
C-52-598-04-PL-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.5.1 | Holiday Testing of Pipeline Section | C-52-598-04-PL-1040 | C-52-598-04-PL-1040: FS | C-52-598-04-PL-1060, C-52-598-04-PL-1090 | C-52-598-04-PL-1060: FS, C-52-598-04-PL-1090: FS | 2025-04-21 13:00 | 2025-04-22 13:00
C-52-598-04-PL-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.5.1 | Installation of ROV | C-52-598-04-PL-1050, HM-ME-0580, HM-ME-2210 | C-52-598-04-PL-1050: FS, HM-ME-0580: FS, HM-ME-2210: FS | C-52-598-04-PL-1070, C-52-598-04-PL-1090, PRECOM-56-59804-1000 | C-52-598-04-PL-1070: FS, C-52-598-04-PL-1090: FF 1, PRECOM-56-59804-1000: FS | 2025-07-21 07:00 | 2025-07-21 17:00
C-52-598-04-PL-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.5.1 | Installation of Pig Signaller Pit | C-52-598-04-PL-1060 | C-52-598-04-PL-1060: FS | C-52-598-04-PL-1080, C-52-598-04-PL-1090 | C-52-598-04-PL-1080: FS, C-52-598-04-PL-1090: FF 1 | 2025-07-22 07:00 | 2025-07-22 17:00
C-52-598-04-PL-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.5.1 | Installation of Pig Signaller | C-52-598-04-PL-1070 | C-52-598-04-PL-1070: FS | C-52-598-04-PL-1090, PRECOM-56-59804-1000 | C-52-598-04-PL-1090: FF, PRECOM-56-59804-1000: FS | 2025-07-23 07:00 | 2025-07-23 17:00
C-52-598-04-PL-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.5.1 | Padding & Backfilling | C-52-598-04-PL-1080, C-52-598-04-PL-1050, C-52-598-04-PL-1060, C-52-598-04-PL-1070 | C-52-598-04-PL-1080: FF, C-52-598-04-PL-1050: FS, C-52-598-04-PL-1060: FF 1, C-52-598-04-PL-1070: FF 1 | PRECOM-56-59804-1000 | PRECOM-56-59804-1000: FS | 2025-07-14 07:00 | 2025-07-23 17:00
C-52-598-03-PL-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.5.1 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | C-52-598-03-PI-1000 | C-52-598-03-PI-1000: FS | C-52-598-03-PL-1010 | C-52-598-03-PL-1010: FS | 2025-04-30 09:00 | 2025-05-06 12:00
C-52-598-03-PL-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.5.1 | Lowering of Pipeline Section | C-52-598-03-PL-1000 | C-52-598-03-PL-1000: FS | C-52-598-03-PL-1020 | C-52-598-03-PL-1020: SS | 2025-05-06 12:00 | 2025-05-08 16:00
C-52-598-03-PL-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.5.1 | Section Tie-in Welding (Including Barred Tee) | C-52-598-03-PL-1010 | C-52-598-03-PL-1010: SS | C-52-598-03-PL-1030 | C-52-598-03-PL-1030: SS 1 | 2025-05-06 12:00 | 2025-05-20 17:00
C-52-598-03-PL-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.5.1 | NDT for Tie-in Joint | C-52-598-03-PL-1020 | C-52-598-03-PL-1020: SS 1 | C-52-598-03-PL-1040 | C-52-598-03-PL-1040: SS 1 | 2025-05-07 14:00 | 2025-05-21 17:00
C-52-598-03-PL-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.5.1 | Ext. Coating for Tie-in Joint | C-52-598-03-PL-1030 | C-52-598-03-PL-1030: SS 1 | C-52-598-03-PL-1050 | C-52-598-03-PL-1050: FS | 2025-05-09 07:00 | 2025-05-22 17:00
C-52-598-03-PL-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.5.1 | Holiday Testing of Pipeline Section | C-52-598-03-PL-1040 | C-52-598-03-PL-1040: FS | C-52-598-03-PL-1060, C-52-598-03-PL-1090 | C-52-598-03-PL-1060: FS, C-52-598-03-PL-1090: FS | 2025-05-23 07:00 | 2025-05-23 17:00
C-52-598-03-PL-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.5.1 | Installation of ROV | C-52-598-03-PL-1050, HM-ME-0580, HM-ME-2210 | C-52-598-03-PL-1050: FS, HM-ME-0580: FS, HM-ME-2210: FS | C-52-598-03-PL-1070, C-52-598-03-PL-1090, PRECOM-56-59803-1000 | C-52-598-03-PL-1070: FS, C-52-598-03-PL-1090: FF 1, PRECOM-56-59803-1000: FS | 2025-07-21 07:00 | 2025-07-21 17:00
C-52-598-03-PL-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.5.1 | Installation of Pig Signaller Pit | C-52-598-03-PL-1060 | C-52-598-03-PL-1060: FS | C-52-598-03-PL-1080, C-52-598-03-PL-1090 | C-52-598-03-PL-1080: FS, C-52-598-03-PL-1090: FF 1 | 2025-07-22 07:00 | 2025-07-22 17:00
C-52-598-03-PL-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.5.1 | Installation of Pig Signaller | C-52-598-03-PL-1070 | C-52-598-03-PL-1070: FS | C-52-598-03-PL-1090, PRECOM-56-59803-1000 | C-52-598-03-PL-1090: FF, PRECOM-56-59803-1000: FS | 2025-07-23 07:00 | 2025-07-23 17:00
C-52-598-03-PL-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.5.1 | Padding & Backfilling | C-52-598-03-PL-1080, C-52-598-03-PL-1050, C-52-598-03-PL-1060, C-52-598-03-PL-1070 | C-52-598-03-PL-1080: FF, C-52-598-03-PL-1050: FS, C-52-598-03-PL-1060: FF 1, C-52-598-03-PL-1070: FF 1 | PRECOM-56-59803-1000 | PRECOM-56-59803-1000: FS | 2025-07-14 07:00 | 2025-07-23 17:00
C-52-598-02-PL-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.5.1 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | C-52-598-02-PI-1000 | C-52-598-02-PI-1000: FS | C-52-598-02-PL-1010 | C-52-598-02-PL-1010: FS | 2025-03-25 07:00 | 2025-04-04 13:00
C-52-598-02-PL-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.5.1 | Lowering of Pipeline Section | C-52-598-02-PL-1000 | C-52-598-02-PL-1000: FS | C-52-598-02-PL-1020 | C-52-598-02-PL-1020: SS | 2025-04-04 13:00 | 2025-04-07 13:00
C-52-598-02-PL-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.5.1 | Section Tie-in Welding (Including Barred Tee) | C-52-598-02-PL-1010 | C-52-598-02-PL-1010: SS | C-52-598-02-PL-1030 | C-52-598-02-PL-1030: SS 1 | 2025-04-04 13:00 | 2025-04-18 13:00
C-52-598-02-PL-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.5.1 | NDT for Tie-in Joint | C-52-598-02-PL-1020 | C-52-598-02-PL-1020: SS 1 | C-52-598-02-PL-1040 | C-52-598-02-PL-1040: SS 1 | 2025-04-05 13:00 | 2025-04-19 13:00
C-52-598-02-PL-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.5.1 | Ext. Coating for Tie-in Joint | C-52-598-02-PL-1030 | C-52-598-02-PL-1030: SS 1 | C-52-598-02-PL-1050, PRECOM-56-59802-1000 | C-52-598-02-PL-1050: FS, PRECOM-56-59802-1000: FS | 2025-04-07 13:00 | 2025-04-21 13:00
C-52-598-02-PL-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.5.1 | Holiday Testing of Pipeline Section | C-52-598-02-PL-1040 | C-52-598-02-PL-1040: FS | C-52-598-02-PL-1060, C-52-598-02-PL-1090 | C-52-598-02-PL-1060: FS, C-52-598-02-PL-1090: FS | 2025-04-21 13:00 | 2025-04-22 13:00
C-52-598-02-PL-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.5.1 | Installation of ROV | C-52-598-02-PL-1050, HM-ME-0580, HM-ME-2210 | C-52-598-02-PL-1050: FS, HM-ME-0580: FS, HM-ME-2210: FS | C-52-598-02-PL-1070, C-52-598-02-PL-1090, PRECOM-56-59802-1000 | C-52-598-02-PL-1070: FS, C-52-598-02-PL-1090: FF 1, PRECOM-56-59802-1000: FS | 2025-07-21 07:00 | 2025-07-21 17:00
C-52-598-02-PL-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.5.1 | Installation of Pig Signaller Pit | C-52-598-02-PL-1060 | C-52-598-02-PL-1060: FS | C-52-598-02-PL-1080, C-52-598-02-PL-1090 | C-52-598-02-PL-1080: FS, C-52-598-02-PL-1090: FF 1 | 2025-07-22 07:00 | 2025-07-22 17:00
C-52-598-02-PL-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.5.1 | Installation of Pig Signaller | C-52-598-02-PL-1070 | C-52-598-02-PL-1070: FS | C-52-598-02-PL-1090, PRECOM-56-59802-1000 | C-52-598-02-PL-1090: FF, PRECOM-56-59802-1000: FS | 2025-07-23 07:00 | 2025-07-23 17:00
C-52-598-02-PL-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.5.1 | Padding & Backfilling | C-52-598-02-PL-1080, C-52-598-02-PL-1050, C-52-598-02-PL-1060, C-52-598-02-PL-1070 | C-52-598-02-PL-1080: FF, C-52-598-02-PL-1050: FS, C-52-598-02-PL-1060: FF 1, C-52-598-02-PL-1070: FF 1 | PRECOM-56-59802-1000 | PRECOM-56-59802-1000: FS | 2025-07-14 07:00 | 2025-07-23 17:00
C-52-598-01-PL-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.5.1 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | C-52-598-01-PI-1000 | C-52-598-01-PI-1000: FS | C-52-598-01-PL-1010 | C-52-598-01-PL-1010: FS | 2025-03-25 07:00 | 2025-04-04 13:00
C-52-598-01-PL-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.5.1 | Lowering of Pipeline Section | C-52-598-01-PL-1000 | C-52-598-01-PL-1000: FS | C-52-598-01-PL-1020 | C-52-598-01-PL-1020: SS | 2025-04-04 13:00 | 2025-04-07 13:00
C-52-598-01-PL-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.5.1 | Section Tie-in Welding (Including Barred Tee) | C-52-598-01-PL-1010 | C-52-598-01-PL-1010: SS | C-52-598-01-PL-1030 | C-52-598-01-PL-1030: SS 1 | 2025-04-04 13:00 | 2025-04-18 13:00
C-52-598-01-PL-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.5.1 | NDT for Tie-in Joint | C-52-598-01-PL-1020 | C-52-598-01-PL-1020: SS 1 | C-52-598-01-PL-1040 | C-52-598-01-PL-1040: SS 1 | 2025-04-05 13:00 | 2025-04-19 13:00
C-52-598-01-PL-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.5.1 | Ext. Coating for Tie-in Joint | C-52-598-01-PL-1030 | C-52-598-01-PL-1030: SS 1 | C-52-598-01-PL-1050 | C-52-598-01-PL-1050: FS | 2025-04-07 13:00 | 2025-04-21 13:00
C-52-598-01-PL-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.5.1 | Holiday Testing of Pipeline Section | C-52-598-01-PL-1040 | C-52-598-01-PL-1040: FS | C-52-598-01-PL-1060, C-52-598-01-PL-1090 | C-52-598-01-PL-1060: FS, C-52-598-01-PL-1090: FS | 2025-04-21 13:00 | 2025-04-22 13:00
C-52-598-01-PL-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.5.1 | Installation of ROV | C-52-598-01-PL-1050, HM-ME-0580, HM-ME-2210 | C-52-598-01-PL-1050: FS, HM-ME-0580: FS, HM-ME-2210: FS | C-52-598-01-PL-1070, C-52-598-01-PL-1090, PRECOM-56-59801-1000 | C-52-598-01-PL-1070: FS, C-52-598-01-PL-1090: FF 1, PRECOM-56-59801-1000: FS | 2025-07-21 07:00 | 2025-07-21 17:00
C-52-598-01-PL-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.5.1 | Installation of Pig Signaller Pit | C-52-598-01-PL-1060 | C-52-598-01-PL-1060: FS | C-52-598-01-PL-1080, C-52-598-01-PL-1090 | C-52-598-01-PL-1080: FS, C-52-598-01-PL-1090: FF 1 | 2025-07-22 07:00 | 2025-07-22 17:00
C-52-598-01-PL-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.5.1 | Installation of Pig Signaller | C-52-598-01-PL-1070 | C-52-598-01-PL-1070: FS | C-52-598-01-PL-1090, PRECOM-56-59801-1000 | C-52-598-01-PL-1090: FF, PRECOM-56-59801-1000: FS | 2025-07-23 07:00 | 2025-07-23 17:00
C-52-598-01-PL-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.5.1 | Padding & Backfilling | C-52-598-01-PL-1080, C-52-598-01-PL-1050, C-52-598-01-PL-1060, C-52-598-01-PL-1070 | C-52-598-01-PL-1080: FF, C-52-598-01-PL-1050: FS, C-52-598-01-PL-1060: FF 1, C-52-598-01-PL-1070: FF 1 | PRECOM-56-59801-1000 | PRECOM-56-59801-1000: FS | 2025-07-14 07:00 | 2025-07-23 17:00
C-52-598-05-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.7 | Electrical & Earthing Cable Laying | C-52-598-05-CI-1800, HE-EL-0470, HE-IC-0950, HE-EL-0830, HE-IC-0830, HE-IC-1010, HE-EL-1610, HM-EL-0520, HM-EL-0080, HE-EL-0590, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-6 | C-52-598-05-CI-1800: FS, HE-EL-0470: FS, HE-IC-0950: FS, HE-EL-0830: FS, HE-IC-0830: FS, HE-IC-1010: FS, HE-EL-1610: FS, HM-EL-0520: FS, HM-EL-0080: FS, HE-EL-0590: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0 | C-52-598-05-EI-2050, C-52-598-05-EI-1400, C-52-598-05-CA-1000, C-52-598-05-CI-2800 | C-52-598-05-EI-2050: FS, C-52-598-05-EI-1400: FF, C-52-598-05-CA-1000: SS, C-52-598-05-CI-2800: FS | 2025-04-18 07:00 | 2025-04-24 17:00
C-52-598-05-EI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.3 | Deep Earth Well Drilling | C-52-598-05-EI-2000, HM-EL-0520, HE-IC-2570, HE-IC-0650, HE-IC-0530, HM-EL-0080, HE-IC-0490, HE-EL-1790, HM-EL-0380, HE-IC-1550, HE-EL-0640, HE-EL-0530, HS-CN-0240, HE-IC-1430, HM-ME-0890, HE-EL-1670, HM-ME-1590, HE-EL-1730, HE-IC-0770, HM-IC-0040, HE-IC-0 | C-52-598-05-EI-2000: FF, HM-EL-0520: FS, HE-IC-2570: FS, HE-IC-0650: FS, HE-IC-0530: FS, HM-EL-0080: FS, HE-IC-0490: FS, HE-EL-1790: FS, HM-EL-0380: FS, HE-IC-1550: FF, HE-EL-0640: FS, HE-EL-0530: FS, HS-CN-0240: FS, HE-IC-1430: FS, HM-ME-0890: FS, HE-EL-1 | PRECOM-56-59805-1000 | PRECOM-56-59805-1000: FS | 2025-05-15 07:00 | 2025-05-17 17:00
C-52-598-05-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.7 | Instrument Cable Laying | C-52-598-05-CI-1810, HE-EL-0470, HE-IC-0950, HE-EL-0830, HE-IC-0830, HE-IC-1010, HE-EL-1610, HM-EL-0520, HM-EL-0080, HE-EL-0590, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-6 | C-52-598-05-CI-1810: FS, HE-EL-0470: FS, HE-IC-0950: FS, HE-EL-0830: FS, HE-IC-0830: FS, HE-IC-1010: FS, HE-EL-1610: FS, HM-EL-0520: FS, HM-EL-0080: FS, HE-EL-0590: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0 | C-52-598-05-EI-2040, C-52-598-05-EI-2050, C-52-598-05-EI-2020, C-52-598-05-TE-1000, C-52-598-05-CI-2810 | C-52-598-05-EI-2040: FS, C-52-598-05-EI-2050: FS, C-52-598-05-EI-2020: FS, C-52-598-05-TE-1000: FS, C-52-598-05-CI-2810: FS | 2025-04-18 07:00 | 2025-04-24 17:00
C-52-598-05-EI-2020 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.7 | Installation of Cable Trays | C-52-598-05-EI-2010 | C-52-598-05-EI-2010: FS | C-52-598-05-EI-2030, C-52-598-05-CI-2810 | C-52-598-05-EI-2030: FS, C-52-598-05-CI-2810: FF 2 | 2025-04-25 07:00 | 2025-05-01 17:00
C-52-598-05-EI-2030 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.7 | Instrument Tubing Works | C-52-598-05-EI-2020 | C-52-598-05-EI-2020: FS | C-52-598-05-EI-2050 | C-52-598-05-EI-2050: FS | 2025-05-02 07:00 | 2025-05-08 14:00
C-52-598-05-EI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.2 | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-598-05-EI-1210 | C-52-598-05-EI-1210: FS | C-52-598-05-EI-2040, C-52-598-05-EI-2050, C-52-598-05-EI-1800 | C-52-598-05-EI-2040: FS, C-52-598-05-EI-2050: FS, C-52-598-05-EI-1800: FS | 2025-05-22 07:00 | 2025-06-09 17:00
C-52-598-05-EI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.5 | Installation of Light Pole, Lighting & Fixtures | C-52-598-05-EI-1200, C-52-598-05-EI-2210 | C-52-598-05-EI-1200: FS, C-52-598-05-EI-2210: FS | C-52-598-05-EI-2050, C-52-598-05-EI-1810 | C-52-598-05-EI-2050: FS, C-52-598-05-EI-1810: FS | 2025-06-10 07:00 | 2025-06-16 17:00
C-52-598-05-EI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.1 | Installation of Passive Cooling Shelter | C-52-598-05-CI-1400, HM-ME-1190, ML1054-D09 | C-52-598-05-CI-1400: FS, HM-ME-1190: FS 35, ML1054-D09: FS 45 | C-52-598-05-EI-1600, C-52-598-05-EI-2050 | C-52-598-05-EI-1600: FS, C-52-598-05-EI-2050: FS | 2025-06-10 13:00 | 2025-06-13 13:00
C-52-598-05-EI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.4 | Installation of RTU | C-52-598-05-EI-1000 | C-52-598-05-EI-1000: FS | C-52-598-05-EI-2400, C-52-598-05-EI-2040, C-52-598-05-EI-2050 | C-52-598-05-EI-2400: FS, C-52-598-05-EI-2040: FS, C-52-598-05-EI-2050: FS | 2025-06-13 13:00 | 2025-06-16 13:00
C-52-598-05-EI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.6 | Installation of F&G Panel | C-52-598-05-EI-1600 | C-52-598-05-EI-1600: FS | C-52-598-05-EI-2040, C-52-598-05-EI-2050 | C-52-598-05-EI-2040: FS, C-52-598-05-EI-2050: FS | 2025-06-16 13:00 | 2025-06-18 13:00
C-52-598-05-EI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.5 | Installation of Lighting & Instrument JB's | C-52-598-05-EI-1800 | C-52-598-05-EI-1800: FS | C-52-598-05-EI-2040, C-52-598-05-EI-2050 | C-52-598-05-EI-2040: FS, C-52-598-05-EI-2050: FS | 2025-06-17 07:00 | 2025-06-19 17:00
C-52-598-05-EI-2200 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.8 | Installation of Field Instruments | C-52-598-05-EI-2210, C-52-598-05-PI-1400 | C-52-598-05-EI-2210: FS, C-52-598-05-PI-1400: FF 3 | C-52-598-05-EI-2040, C-52-598-05-EI-2050, C-52-598-05-EI-2410 | C-52-598-05-EI-2040: FS, C-52-598-05-EI-2050: FS, C-52-598-05-EI-2410: FS | 2025-05-26 07:00 | 2025-05-31 17:00
C-52-598-05-EI-2410 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.6 | Installation of F&G Devices | C-52-598-05-EI-2200, HM-ME-1490, HM-ME-2310 | C-52-598-05-EI-2200: FS, HM-ME-1490: FS, HM-ME-2310: FS | C-52-598-05-EI-2040, C-52-598-05-EI-2050 | C-52-598-05-EI-2040: FS, C-52-598-05-EI-2050: FS | 2025-06-02 07:00 | 2025-06-09 17:00
C-52-598-05-EI-2040 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.7 | Loop Checking for Instruments | C-52-598-05-EI-2410, C-52-598-05-EI-2200, C-52-598-05-EI-1810, C-52-598-05-EI-1600, C-52-598-05-EI-2400, C-52-598-05-EI-1200, C-52-598-05-EI-2010 | C-52-598-05-EI-2410: FS, C-52-598-05-EI-2200: FS, C-52-598-05-EI-1810: FS, C-52-598-05-EI-1600: FS, C-52-598-05-EI-2400: FS, C-52-598-05-EI-1200: FS, C-52-598-05-EI-2010: FS | C-52-598-05-EI-2050, PRECOM-56-59805-1000 | C-52-598-05-EI-2050: FS, PRECOM-56-59805-1000: FS | 2025-06-20 07:00 | 2025-06-30 17:00
C-52-598-05-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.6.7 | Glanding & Termination | C-52-598-05-EI-2040, C-52-598-05-EI-2000, C-52-598-05-EI-2010, C-52-598-05-EI-2030, C-52-598-05-EI-1200, C-52-598-05-EI-1800, C-52-598-05-EI-1000, C-52-598-05-EI-1810, C-52-598-05-EI-2200, C-52-598-05-EI-2410, C-52-598-05-EI-1600, C-52-598-05-EI-2400 | C-52-598-05-EI-2040: FS, C-52-598-05-EI-2000: FS, C-52-598-05-EI-2010: FS, C-52-598-05-EI-2030: FS, C-52-598-05-EI-1200: FS, C-52-598-05-EI-1800: FS, C-52-598-05-EI-1000: FS, C-52-598-05-EI-1810: FS, C-52-598-05-EI-2200: FS, C-52-598-05-EI-2410: FS, C-52-5 | PRECOM-56-59805-1000 | PRECOM-56-59805-1000: FS | 2025-07-01 07:00 | 2025-07-05 17:00
C-52-598-04-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.7 | Electrical & Earthing Cable Laying | C-52-598-04-CI-1800, HE-IC-0830, HM-EL-0520, HE-EL-1610, HE-EL-0590, HE-EL-0830, HM-EL-0080, HE-EL-0470, HE-IC-0950, HE-IC-1010, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-6 | C-52-598-04-CI-1800: FS, HE-IC-0830: FS, HM-EL-0520: FS, HE-EL-1610: FS, HE-EL-0590: FS, HE-EL-0830: FS, HM-EL-0080: FS, HE-EL-0470: FS, HE-IC-0950: FS, HE-IC-1010: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0 | C-52-598-04-EI-2050, C-52-598-04-EI-1400, C-52-598-04-EI-2010, C-52-598-04-CA-1000, C-52-598-04-CI-2800 | C-52-598-04-EI-2050: FS, C-52-598-04-EI-1400: FF, C-52-598-04-EI-2010: FS, C-52-598-04-CA-1000: FS, C-52-598-04-CI-2800: FS 5 | 2025-04-18 07:00 | 2025-04-24 17:00
C-52-598-04-EI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.3 | Deep Earth Well Drilling | C-52-598-04-EI-2000, HM-EL-0080, HM-EL-0280, HM-ME-0890, HM-EL-0520, ML1032-B21, HE-EL-0770, HM-EL-0380, HE-EL-1790, HE-IC-1430, HE-EL-0640, HE-IC-0490, HE-IC-0770, HM-IC-0040, HE-IC-0650, HE-IC-0590, HE-EL-0530, HE-EL-0350, HM-ME-1590, HE-HS-0350, HE-IC-1 | C-52-598-04-EI-2000: FF, HM-EL-0080: FS, HM-EL-0280: FS, HM-ME-0890: FS, HM-EL-0520: FS, ML1032-B21: FS, HE-EL-0770: FS, HM-EL-0380: FS, HE-EL-1790: FS, HE-IC-1430: FS, HE-EL-0640: FS, HE-IC-0490: FS, HE-IC-0770: FS, HM-IC-0040: FS, HE-IC-0650: FS, HE-IC-0 | PRECOM-56-59804-1000 | PRECOM-56-59804-1000: FS | 2025-05-15 07:00 | 2025-05-17 17:00
C-52-598-04-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.7 | Instrument Cable Laying | C-52-598-04-EI-2000, C-52-598-04-CI-1810 | C-52-598-04-EI-2000: FS, C-52-598-04-CI-1810: FS | C-52-598-04-EI-2040, C-52-598-04-EI-2050, C-52-598-04-EI-2020, C-52-598-04-EI-2200, C-52-598-04-CI-2810, C-52-598-04-TE-1000 | C-52-598-04-EI-2040: FS, C-52-598-04-EI-2050: FS, C-52-598-04-EI-2020: FS, C-52-598-04-EI-2200: FS, C-52-598-04-CI-2810: FS 5, C-52-598-04-TE-1000: FS | 2025-04-25 07:00 | 2025-05-01 17:00
C-52-598-04-EI-2020 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.7 | Installation of Cable Trays | C-52-598-04-EI-2010 | C-52-598-04-EI-2010: FS | C-52-598-04-EI-2030, C-52-598-04-EI-2200 | C-52-598-04-EI-2030: FS, C-52-598-04-EI-2200: FS | 2025-05-02 07:00 | 2025-05-09 15:00
C-52-598-04-EI-2030 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.7 | Instrument Tubing Works | C-52-598-04-EI-2020 | C-52-598-04-EI-2020: FS | C-52-598-04-EI-2050, C-52-598-04-EI-2200 | C-52-598-04-EI-2050: FS, C-52-598-04-EI-2200: FS | 2025-05-09 15:00 | 2025-05-15 15:00
C-52-598-04-EI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.2 | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-598-04-EI-1210 | C-52-598-04-EI-1210: FS | C-52-598-04-EI-2040, C-52-598-04-EI-2050, C-52-598-04-EI-1800 | C-52-598-04-EI-2040: FS, C-52-598-04-EI-2050: FS, C-52-598-04-EI-1800: FF 2 | 2025-05-22 07:00 | 2025-06-09 17:00
C-52-598-04-EI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.5 | Installation of Light Pole, Lighting & Fixtures | C-52-598-04-EI-2210, C-52-598-04-EI-1200 | C-52-598-04-EI-2210: FS, C-52-598-04-EI-1200: FF 2 | C-52-598-04-EI-2050 | C-52-598-04-EI-2050: FS | 2025-06-03 07:00 | 2025-06-11 17:00
C-52-598-04-EI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.1 | Installation of Passive Cooling Shelter | HM-ME-1190, ML1054-D09, C-52-598-04-CI-1400 | HM-ME-1190: FS, ML1054-D09: FS, C-52-598-04-CI-1400: FS | C-52-598-04-EI-1600, C-52-598-04-EI-2050, C-52-598-04-EI-1810 | C-52-598-04-EI-1600: FS, C-52-598-04-EI-2050: FS, C-52-598-04-EI-1810: FS | 2025-04-25 15:00 | 2025-04-29 15:00
C-52-598-04-EI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.4 | Installation of RTU | C-52-598-04-EI-1000 | C-52-598-04-EI-1000: FS | C-52-598-04-EI-2400, C-52-598-04-EI-2040, C-52-598-04-EI-2050 | C-52-598-04-EI-2400: FS, C-52-598-04-EI-2040: FS, C-52-598-04-EI-2050: FS | 2025-04-29 15:00 | 2025-05-01 15:00
C-52-598-04-EI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.6 | Installation of F&G Panel | C-52-598-04-EI-1600 | C-52-598-04-EI-1600: FS | C-52-598-04-EI-2040, C-52-598-04-EI-2050 | C-52-598-04-EI-2040: FS, C-52-598-04-EI-2050: FS | 2025-05-01 15:00 | 2025-05-03 15:00
C-52-598-04-EI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.5 | Installation of Lighting & Instrument JB's | C-52-598-04-EI-1000 | C-52-598-04-EI-1000: FS | C-52-598-04-EI-2040, C-52-598-04-EI-2050 | C-52-598-04-EI-2040: FS, C-52-598-04-EI-2050: FS | 2025-04-29 15:00 | 2025-05-02 15:00
C-52-598-04-EI-2200 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.8 | Installation of Field Instruments | C-52-598-04-EI-2010, C-52-598-04-EI-2020, C-52-598-04-EI-2030, C-52-598-04-PI-1400 | C-52-598-04-EI-2010: FS, C-52-598-04-EI-2020: FS, C-52-598-04-EI-2030: FS, C-52-598-04-PI-1400: FF 2 | C-52-598-04-EI-2040, C-52-598-04-EI-2050, C-52-598-04-EI-2410 | C-52-598-04-EI-2040: FS, C-52-598-04-EI-2050: FS, C-52-598-04-EI-2410: FS | 2025-05-15 15:00 | 2025-05-22 15:00
C-52-598-04-EI-2410 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.6 | Installation of F&G Devices | C-52-598-04-EI-2200, HM-ME-1490, HM-ME-2310 | C-52-598-04-EI-2200: FS, HM-ME-1490: FS, HM-ME-2310: FS | C-52-598-04-EI-2040, C-52-598-04-EI-2050 | C-52-598-04-EI-2040: FS, C-52-598-04-EI-2050: FS | 2025-05-22 15:00 | 2025-05-28 15:00
C-52-598-04-EI-2040 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.7 | Loop Checking for Instruments | C-52-598-04-EI-2410, C-52-598-04-EI-2200, C-52-598-04-EI-1810, C-52-598-04-EI-1600, C-52-598-04-EI-2400, C-52-598-04-EI-1200, C-52-598-04-EI-2010 | C-52-598-04-EI-2410: FS, C-52-598-04-EI-2200: FS, C-52-598-04-EI-1810: FS, C-52-598-04-EI-1600: FS, C-52-598-04-EI-2400: FS, C-52-598-04-EI-1200: FS, C-52-598-04-EI-2010: FS | C-52-598-04-EI-2050, PRECOM-56-59804-1000 | C-52-598-04-EI-2050: FS, PRECOM-56-59804-1000: FS | 2025-06-10 07:00 | 2025-06-18 17:00
C-52-598-04-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.7 | Glanding & Termination | C-52-598-04-EI-2040, C-52-598-04-EI-2000, C-52-598-04-EI-2010, C-52-598-04-EI-2030, C-52-598-04-EI-1200, C-52-598-04-EI-1800, C-52-598-04-EI-1000, C-52-598-04-EI-1810, C-52-598-04-EI-2200, C-52-598-04-EI-2410, C-52-598-04-EI-1600, C-52-598-04-EI-2400 | C-52-598-04-EI-2040: FS, C-52-598-04-EI-2000: FS, C-52-598-04-EI-2010: FS, C-52-598-04-EI-2030: FS, C-52-598-04-EI-1200: FS, C-52-598-04-EI-1800: FS, C-52-598-04-EI-1000: FS, C-52-598-04-EI-1810: FS, C-52-598-04-EI-2200: FS, C-52-598-04-EI-2410: FS, C-52-5 | PRECOM-56-59804-1000 | PRECOM-56-59804-1000: FS | 2025-06-19 07:00 | 2025-06-24 17:00
C-52-598-03-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.7 | Electrical & Earthing Cable Laying | C-52-598-03-CI-1800, HE-IC-0950, HE-EL-1610, HE-EL-0830, HE-IC-0830, HE-IC-1010, HE-EL-0590, HE-EL-0470, HM-EL-0080, HM-EL-0520, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-6 | C-52-598-03-CI-1800: FS, HE-IC-0950: FS, HE-EL-1610: FS, HE-EL-0830: FS, HE-IC-0830: FS, HE-IC-1010: FS, HE-EL-0590: FS, HE-EL-0470: FS, HM-EL-0080: FS, HM-EL-0520: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0 | C-52-598-03-EI-2050, C-52-598-03-EI-1400, C-52-598-03-EI-2010, C-52-598-03-CA-1000, C-52-598-03-CI-2800 | C-52-598-03-EI-2050: FS, C-52-598-03-EI-1400: FF, C-52-598-03-EI-2010: FS, C-52-598-03-CA-1000: FS, C-52-598-03-CI-2800: FS 5 | 2025-04-18 07:00 | 2025-04-24 17:00
C-52-598-03-EI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.2 | Deep Earth Well Drilling | C-52-598-03-EI-2000, HE-HS-0350, HE-EL-0640, HE-IC-0770, HM-IC-0050, HM-ME-0890, HE-IC-1550, HE-IC-0010, HM-EL-0380, HM-EL-0520, HM-EL-0280, HE-IC-1430, HM-IC-0040, HE-EL-1010, HE-EL-0770, HE-IC-0650, HE-EL-0350, HE-IC-0530, HE-IC-2570, HE-EL-0530, HE-EL-1 | C-52-598-03-EI-2000: FF, HE-HS-0350: FS, HE-EL-0640: FS, HE-IC-0770: FS, HM-IC-0050: FF, HM-ME-0890: FS, HE-IC-1550: FF, HE-IC-0010: SS 10, HM-EL-0380: FS, HM-EL-0520: FS, HM-EL-0280: FS, HE-IC-1430: FS, HM-IC-0040: FS, HE-EL-1010: FS, HE-EL-0770: FS, HE-I | PRECOM-56-59803-1000 | PRECOM-56-59803-1000: FS | 2025-05-15 07:00 | 2025-05-17 17:00
C-52-598-03-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.7 | Instrument Cable Laying | C-52-598-03-EI-2000, C-52-598-03-CI-1810 | C-52-598-03-EI-2000: FS, C-52-598-03-CI-1810: FS | C-52-598-03-EI-2040, C-52-598-03-EI-2050, C-52-598-03-EI-2020, C-52-598-03-EI-2200, C-52-598-03-CI-2810, C-52-598-03-TE-1000 | C-52-598-03-EI-2040: FS, C-52-598-03-EI-2050: FS, C-52-598-03-EI-2020: FS, C-52-598-03-EI-2200: FS, C-52-598-03-CI-2810: FS 5, C-52-598-03-TE-1000: FS | 2025-05-10 11:00 | 2025-05-17 11:00
C-52-598-03-EI-2020 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.7 | Installation of Cable Trays | C-52-598-03-EI-2010 | C-52-598-03-EI-2010: FS | C-52-598-03-EI-2030 | C-52-598-03-EI-2030: FS | 2025-05-17 11:00 | 2025-05-24 11:00
C-52-598-03-EI-2030 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.7 | Instrument Tubing Works | C-52-598-03-EI-2020 | C-52-598-03-EI-2020: FS | C-52-598-03-EI-2050, C-52-598-03-EI-2200 | C-52-598-03-EI-2050: FS, C-52-598-03-EI-2200: FS | 2025-05-24 11:00 | 2025-05-30 11:00
C-52-598-03-EI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.3 | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-598-03-EI-1210 | C-52-598-03-EI-1210: FS | C-52-598-03-EI-2040, C-52-598-03-EI-2050, C-52-598-03-EI-1800 | C-52-598-03-EI-2040: FS, C-52-598-03-EI-2050: FS, C-52-598-03-EI-1800: FF 2 | 2025-06-19 07:00 | 2025-07-05 17:00
C-52-598-03-EI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.5 | Installation of Light Pole, Lighting & Fixtures | C-52-598-03-EI-2210, C-52-598-03-EI-1200 | C-52-598-03-EI-2210: FS, C-52-598-03-EI-1200: FF 2 | C-52-598-03-EI-2050, C-52-598-03-EI-1810 | C-52-598-03-EI-2050: FS, C-52-598-03-EI-1810: FS | 2025-07-02 07:00 | 2025-07-08 17:00
C-52-598-03-EI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.1 | Installation of Passive Cooling Shelter | C-52-598-03-CI-1400, ML1054-D09, HM-ME-1190 | C-52-598-03-CI-1400: FS, ML1054-D09: FS, HM-ME-1190: FS | C-52-598-03-EI-1600, C-52-598-03-EI-2050 | C-52-598-03-EI-1600: FS, C-52-598-03-EI-2050: FS | 2025-04-25 15:00 | 2025-04-29 15:00
C-52-598-03-EI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.4 | Installation of RTU | C-52-598-03-EI-1000 | C-52-598-03-EI-1000: FS | C-52-598-03-EI-2400, C-52-598-03-EI-2040, C-52-598-03-EI-2050 | C-52-598-03-EI-2400: FS, C-52-598-03-EI-2040: FS, C-52-598-03-EI-2050: FS | 2025-04-29 15:00 | 2025-05-01 15:00
C-52-598-03-EI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.8 | Installation of F&G Panel | C-52-598-03-EI-1600 | C-52-598-03-EI-1600: FS | C-52-598-03-EI-2040, C-52-598-03-EI-2050 | C-52-598-03-EI-2040: FS, C-52-598-03-EI-2050: FS | 2025-05-01 15:00 | 2025-05-03 15:00
C-52-598-03-EI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.5 | Installation of Lighting & Instrument JB's | C-52-598-03-EI-1800 | C-52-598-03-EI-1800: FS | C-52-598-03-EI-2040, C-52-598-03-EI-2050 | C-52-598-03-EI-2040: FS, C-52-598-03-EI-2050: FS | 2025-07-09 07:00 | 2025-07-11 17:00
C-52-598-03-EI-2200 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.6 | Installation of Field Instruments | C-52-598-03-EI-2210, C-52-598-03-EI-2010, C-52-598-03-EI-2030 | C-52-598-03-EI-2210: FS, C-52-598-03-EI-2010: FS, C-52-598-03-EI-2030: FS | C-52-598-03-EI-2040, C-52-598-03-EI-2050, C-52-598-03-EI-2410 | C-52-598-03-EI-2040: FS, C-52-598-03-EI-2050: FS, C-52-598-03-EI-2410: FS | 2025-06-03 07:00 | 2025-06-11 17:00
C-52-598-03-EI-2410 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.8 | Installation of F&G Devices | C-52-598-03-EI-2200, HM-ME-1490, HM-ME-2310 | C-52-598-03-EI-2200: FS, HM-ME-1490: FS, HM-ME-2310: FS | C-52-598-03-EI-2040, C-52-598-03-EI-2050 | C-52-598-03-EI-2040: FS, C-52-598-03-EI-2050: FS | 2025-06-12 07:00 | 2025-06-17 17:00
C-52-598-03-EI-2040 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.7 | Loop Checking for Instruments | C-52-598-03-EI-2410, C-52-598-03-EI-2200, C-52-598-03-EI-1810, C-52-598-03-EI-1600, C-52-598-03-EI-2400, C-52-598-03-EI-1200, C-52-598-03-EI-2010 | C-52-598-03-EI-2410: FS, C-52-598-03-EI-2200: FS, C-52-598-03-EI-1810: FS, C-52-598-03-EI-1600: FS, C-52-598-03-EI-2400: FS, C-52-598-03-EI-1200: FS, C-52-598-03-EI-2010: FS | C-52-598-03-EI-2050, PRECOM-56-59803-1000 | C-52-598-03-EI-2050: FS, PRECOM-56-59803-1000: FS | 2025-07-12 07:00 | 2025-07-21 17:00
C-52-598-03-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.6.7 | Glanding & Termination | C-52-598-03-EI-2040, C-52-598-03-EI-2000, C-52-598-03-EI-2010, C-52-598-03-EI-2030, C-52-598-03-EI-1200, C-52-598-03-EI-1800, C-52-598-03-EI-1000, C-52-598-03-EI-1810, C-52-598-03-EI-2200, C-52-598-03-EI-2410, C-52-598-03-EI-1600, C-52-598-03-EI-2400 | C-52-598-03-EI-2040: FS, C-52-598-03-EI-2000: FS, C-52-598-03-EI-2010: FS, C-52-598-03-EI-2030: FS, C-52-598-03-EI-1200: FS, C-52-598-03-EI-1800: FS, C-52-598-03-EI-1000: FS, C-52-598-03-EI-1810: FS, C-52-598-03-EI-2200: FS, C-52-598-03-EI-2410: FS, C-52-5 | PRECOM-56-59803-1000 | PRECOM-56-59803-1000: FS | 2025-07-22 07:00 | 2025-07-26 17:00
C-52-598-02-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.7 | Electrical & Earthing Cable Laying | C-52-598-02-CI-1800, HM-EL-0520, HE-IC-1010, HM-EL-0080, HE-EL-1610, HE-IC-0950, HE-EL-0470, HE-EL-0830, HE-EL-0590, HE-IC-0830, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-6 | C-52-598-02-CI-1800: FS, HM-EL-0520: FS, HE-IC-1010: FS, HM-EL-0080: FS, HE-EL-1610: FS, HE-IC-0950: FS, HE-EL-0470: FS, HE-EL-0830: FS, HE-EL-0590: FS, HE-IC-0830: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0 | C-52-598-02-EI-2050, C-52-598-02-EI-1400, C-52-598-02-EI-2010, C-52-598-02-CA-1000, C-52-598-02-CI-2800 | C-52-598-02-EI-2050: FS, C-52-598-02-EI-1400: FF, C-52-598-02-EI-2010: FS, C-52-598-02-CA-1000: FS, C-52-598-02-CI-2800: FS | 2025-04-18 07:00 | 2025-04-24 17:00
C-52-598-02-EI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.2 | Deep Earth Well Drilling | C-52-598-02-EI-2000, HE-IC-1550, HM-EL-0520, HE-EL-1010, HE-EL-1730, HE-IC-0710, HE-IC-1430, ML1032-B21, HE-HS-0350, HM-EL-0530, HE-IC-0770, HS-CN-0240, HM-ME-1690, HE-IC-0650, HE-IC-0490, HE-EL-1670, HM-EL-0380, HE-IC-0530, HE-EL-1790, HE-IC-0010, HE-EL-0 | C-52-598-02-EI-2000: FF, HE-IC-1550: FF, HM-EL-0520: FS, HE-EL-1010: FS, HE-EL-1730: FS, HE-IC-0710: FS, HE-IC-1430: FS, ML1032-B21: FS, HE-HS-0350: FS, HM-EL-0530: FS, HE-IC-0770: FS, HS-CN-0240: FS, HM-ME-1690: FF, HE-IC-0650: FS, HE-IC-0490: FS, HE-EL-1 | C-52-598-02-CI-2800 | C-52-598-02-CI-2800: FS | 2025-05-19 07:00 | 2025-05-21 17:00
C-52-598-02-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.7 | Instrument Cable Laying | C-52-598-02-EI-2000, C-52-598-02-CI-1810 | C-52-598-02-EI-2000: FS, C-52-598-02-CI-1810: FS | C-52-598-02-EI-2040, C-52-598-02-EI-2050, C-52-598-02-EI-2020, C-52-598-02-CI-2810, C-52-598-02-TE-1000 | C-52-598-02-EI-2040: FS, C-52-598-02-EI-2050: FS, C-52-598-02-EI-2020: FS, C-52-598-02-CI-2810: FS, C-52-598-02-TE-1000: FS | 2025-05-01 13:00 | 2025-05-09 11:00
C-52-598-02-EI-2020 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.7 | Installation of Cable Trays | C-52-598-02-EI-2010 | C-52-598-02-EI-2010: FS | C-52-598-02-EI-2030 | C-52-598-02-EI-2030: FS | 2025-05-09 11:00 | 2025-05-16 11:00
C-52-598-02-EI-2030 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.7 | Instrument Tubing Works | C-52-598-02-EI-2020 | C-52-598-02-EI-2020: FS | C-52-598-02-EI-2050, C-52-598-02-EI-2200 | C-52-598-02-EI-2050: FS, C-52-598-02-EI-2200: FS | 2025-05-16 11:00 | 2025-05-22 11:00
C-52-598-02-EI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.3 | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-598-02-EI-1210 | C-52-598-02-EI-1210: FS | C-52-598-02-EI-2040, C-52-598-02-EI-2050, C-52-598-02-EI-1800 | C-52-598-02-EI-2040: FS, C-52-598-02-EI-2050: FS, C-52-598-02-EI-1800: FS | 2025-05-22 07:00 | 2025-06-09 17:00
C-52-598-02-EI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.5 | Installation of Light Pole, Lighting & Fixtures | C-52-598-02-EI-1200, C-52-598-02-EI-2210 | C-52-598-02-EI-1200: FS, C-52-598-02-EI-2210: FS | C-52-598-02-EI-2050, C-52-598-02-EI-1810 | C-52-598-02-EI-2050: FS, C-52-598-02-EI-1810: FS | 2025-06-10 07:00 | 2025-06-16 17:00
C-52-598-02-EI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.1 | Installation of Passive Cooling Shelter | C-52-598-02-CI-1200, HM-ME-1190, ML1054-D09 | C-52-598-02-CI-1200: FS, HM-ME-1190: FS, ML1054-D09: FS | C-52-598-02-EI-1600, C-52-598-02-EI-2050 | C-52-598-02-EI-1600: FS, C-52-598-02-EI-2050: FS | 2025-04-25 15:00 | 2025-04-29 15:00
C-52-598-02-EI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.4 | Installation of RTU | C-52-598-02-EI-1000 | C-52-598-02-EI-1000: FS | C-52-598-02-EI-2400, C-52-598-02-EI-2040, C-52-598-02-EI-2050 | C-52-598-02-EI-2400: FS, C-52-598-02-EI-2040: FS, C-52-598-02-EI-2050: FS | 2025-04-29 15:00 | 2025-05-01 15:00
C-52-598-02-EI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.8 | Installation of F&G Panel | C-52-598-02-EI-1600 | C-52-598-02-EI-1600: FS | C-52-598-02-EI-2040, C-52-598-02-EI-2050, C-52-598-02-EI-2200 | C-52-598-02-EI-2040: FS, C-52-598-02-EI-2050: FS, C-52-598-02-EI-2200: FS | 2025-05-01 15:00 | 2025-05-03 15:00
C-52-598-02-EI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.5 | Installation of Lighting & Instrument JB's | C-52-598-02-EI-1800 | C-52-598-02-EI-1800: FS | C-52-598-02-EI-2040, C-52-598-02-EI-2050 | C-52-598-02-EI-2040: FS, C-52-598-02-EI-2050: FS | 2025-06-17 07:00 | 2025-06-19 17:00
C-52-598-02-EI-2200 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.6 | Installation of Field Instruments | C-52-598-02-EI-2210, C-52-598-02-EI-2030, C-52-598-02-EI-2400 | C-52-598-02-EI-2210: FS, C-52-598-02-EI-2030: FS, C-52-598-02-EI-2400: FS | C-52-598-02-EI-2040, C-52-598-02-EI-2050, C-52-598-02-EI-2410 | C-52-598-02-EI-2040: FS, C-52-598-02-EI-2050: FS, C-52-598-02-EI-2410: FS | 2025-05-22 11:00 | 2025-05-29 11:00
C-52-598-02-EI-2410 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.8 | Installation of F&G Devices | C-52-598-02-EI-2200, HM-ME-1490, HM-ME-2310 | C-52-598-02-EI-2200: FS, HM-ME-1490: FS, HM-ME-2310: FS | C-52-598-02-EI-2040, C-52-598-02-EI-2050 | C-52-598-02-EI-2040: FS, C-52-598-02-EI-2050: FS | 2025-05-29 11:00 | 2025-06-04 11:00
C-52-598-02-EI-2040 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.7 | Loop Checking for Instruments | C-52-598-02-EI-2410, C-52-598-02-EI-2200, C-52-598-02-EI-1810, C-52-598-02-EI-1600, C-52-598-02-EI-2400, C-52-598-02-EI-1200, C-52-598-02-EI-2010 | C-52-598-02-EI-2410: FS, C-52-598-02-EI-2200: FS, C-52-598-02-EI-1810: FS, C-52-598-02-EI-1600: FS, C-52-598-02-EI-2400: FS, C-52-598-02-EI-1200: FS, C-52-598-02-EI-2010: FS | C-52-598-02-EI-2050, PRECOM-56-59802-1000 | C-52-598-02-EI-2050: FS, PRECOM-56-59802-1000: FS | 2025-06-20 07:00 | 2025-06-30 17:00
C-52-598-02-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.7 | Glanding & Termination | C-52-598-02-EI-2040, C-52-598-02-EI-2000, C-52-598-02-EI-2010, C-52-598-02-EI-2030, C-52-598-02-EI-1200, C-52-598-02-EI-1800, C-52-598-02-EI-1000, C-52-598-02-EI-1810, C-52-598-02-EI-2200, C-52-598-02-EI-2410, C-52-598-02-EI-1600, C-52-598-02-EI-2400 | C-52-598-02-EI-2040: FS, C-52-598-02-EI-2000: FS, C-52-598-02-EI-2010: FS, C-52-598-02-EI-2030: FS, C-52-598-02-EI-1200: FS, C-52-598-02-EI-1800: FS, C-52-598-02-EI-1000: FS, C-52-598-02-EI-1810: FS, C-52-598-02-EI-2200: FS, C-52-598-02-EI-2410: FS, C-52-5 | PRECOM-56-59802-1000 | PRECOM-56-59802-1000: FS | 2025-07-01 07:00 | 2025-07-05 17:00
C-52-598-01-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.6 | Electrical & Earthing Cable Laying | C-52-598-01-CI-1800, HM-EL-0520, HE-IC-0950, HE-EL-0590, HM-EL-0080, HE-IC-1010, HE-IC-0830, HE-EL-1610, HE-EL-0830, HE-EL-0470, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-6 | C-52-598-01-CI-1800: FS, HM-EL-0520: FS, HE-IC-0950: FS, HE-EL-0590: FS, HM-EL-0080: FS, HE-IC-1010: FS, HE-IC-0830: FS, HE-EL-1610: FS, HE-EL-0830: FS, HE-EL-0470: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0 | C-52-598-01-EI-2050, C-52-598-01-EI-1400, C-52-598-01-EI-2010, C-52-598-01-CA-1000, C-52-598-01-CI-2800 | C-52-598-01-EI-2050: FS, C-52-598-01-EI-1400: FF, C-52-598-01-EI-2010: FS, C-52-598-01-CA-1000: FS, C-52-598-01-CI-2800: FS 5 | 2025-04-18 07:00 | 2025-04-24 17:00
C-52-598-01-EI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.3 | Deep Earth Well Drilling | C-52-598-01-EI-2000, HM-ME-1590, HE-IC-1550, HE-IC-0770, HM-IC-0050, HM-EL-0380, HE-EL-0640, HE-EL-0770, ML1032-B21, HM-ME-1690, HM-EL-0530, HE-IC-1430, HE-IC-0530, HM-IC-0040, HM-EL-0080, HE-EL-1010, HE-EL-1730, HE-IC-0710, HE-EL-0350, HE-EL-0530, HE-IC-0 | C-52-598-01-EI-2000: FF, HM-ME-1590: FF, HE-IC-1550: FF, HE-IC-0770: FS, HM-IC-0050: FF, HM-EL-0380: FS, HE-EL-0640: FS, HE-EL-0770: FS, ML1032-B21: FS, HM-ME-1690: FF, HM-EL-0530: FF, HE-IC-1430: FS, HE-IC-0530: FS, HM-IC-0040: FS, HM-EL-0080: FS, HE-EL-1 | C-52-598-01-EI-2050, PRECOM-56-59801-1000 | C-52-598-01-EI-2050: FS, PRECOM-56-59801-1000: FS | 2025-05-30 07:00 | 2025-06-02 17:00
C-52-598-01-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.6 | Instrument Cable Laying | C-52-598-01-EI-2000, C-52-598-01-CI-1810 | C-52-598-01-EI-2000: FS, C-52-598-01-CI-1810: FS | C-52-598-01-EI-2040, C-52-598-01-EI-2050, C-52-598-01-EI-2020, C-52-598-01-CI-2810, C-52-598-01-TE-1000 | C-52-598-01-EI-2040: FS, C-52-598-01-EI-2050: FS, C-52-598-01-EI-2020: FS, C-52-598-01-CI-2810: FS 5, C-52-598-01-TE-1000: FS | 2025-04-25 07:00 | 2025-05-01 17:00
C-52-598-01-EI-2020 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.6 | Installation of Cable Trays | C-52-598-01-EI-2010 | C-52-598-01-EI-2010: FS | C-52-598-01-EI-2030 | C-52-598-01-EI-2030: FS | 2025-05-02 07:00 | 2025-05-09 15:00
C-52-598-01-EI-2030 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.6 | Instrument Tubing Works | C-52-598-01-EI-2020 | C-52-598-01-EI-2020: FS | C-52-598-01-EI-2050 | C-52-598-01-EI-2050: FS | 2025-05-09 15:00 | 2025-05-15 15:00
C-52-598-01-EI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.2 | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-598-01-EI-1210 | C-52-598-01-EI-1210: FS | C-52-598-01-EI-2040, C-52-598-01-EI-2050, C-52-598-01-EI-1800 | C-52-598-01-EI-2040: FS, C-52-598-01-EI-2050: FS, C-52-598-01-EI-1800: FS | 2025-05-19 07:00 | 2025-06-03 17:00
C-52-598-01-EI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.5 | Installation of Light Pole, Lighting & Fixtures | C-52-598-01-EI-2210, C-52-598-01-EI-1200 | C-52-598-01-EI-2210: FS, C-52-598-01-EI-1200: FS | C-52-598-01-EI-2050, C-52-598-01-EI-1810, PRECOM-56-59801-1000 | C-52-598-01-EI-2050: FS, C-52-598-01-EI-1810: FS, PRECOM-56-59801-1000: FS | 2025-06-04 07:00 | 2025-06-12 17:00
C-52-598-01-EI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.1 | Installation of Passive Cooling Shelter | C-52-598-01-CI-1400, ML1054-D09, HM-ME-1190, ML1054-D09 | C-52-598-01-CI-1400: FS, ML1054-D09: FS, HM-ME-1190: FS, ML1054-D09: FF | C-52-598-01-EI-1600, C-52-598-01-EI-2050 | C-52-598-01-EI-1600: FS, C-52-598-01-EI-2050: FS | 2025-04-25 15:00 | 2025-04-29 15:00
C-52-598-01-EI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.4 | Installation of RTU | C-52-598-01-EI-1000 | C-52-598-01-EI-1000: FS | C-52-598-01-EI-2400, C-52-598-01-EI-2040, C-52-598-01-EI-2050 | C-52-598-01-EI-2400: FS, C-52-598-01-EI-2040: FS, C-52-598-01-EI-2050: FS | 2025-04-29 15:00 | 2025-05-01 15:00
C-52-598-01-EI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.8 | Installation of F&G Panel | C-52-598-01-EI-1600 | C-52-598-01-EI-1600: FS | C-52-598-01-EI-2040, C-52-598-01-EI-2050 | C-52-598-01-EI-2040: FS, C-52-598-01-EI-2050: FS | 2025-05-01 15:00 | 2025-05-03 15:00
C-52-598-01-EI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.5 | Installation of Lighting & Instrument JB's | C-52-598-01-EI-1800 | C-52-598-01-EI-1800: FS | C-52-598-01-EI-2040, C-52-598-01-EI-2050, PRECOM-56-59801-1000 | C-52-598-01-EI-2040: FS, C-52-598-01-EI-2050: FS, PRECOM-56-59801-1000: FS | 2025-06-13 07:00 | 2025-06-16 17:00
C-52-598-01-EI-2200 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.7 | Installation of Field Instruments | C-52-598-01-EI-2210 | C-52-598-01-EI-2210: FS | C-52-598-01-EI-2040, C-52-598-01-EI-2050, C-52-598-01-EI-2410 | C-52-598-01-EI-2040: FS, C-52-598-01-EI-2050: FS, C-52-598-01-EI-2410: FS | 2025-05-09 07:00 | 2025-05-15 17:00
C-52-598-01-EI-2410 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.8 | Installation of F&G Devices | C-52-598-01-EI-2200, HM-ME-1490, HM-ME-2310 | C-52-598-01-EI-2200: FS, HM-ME-1490: FS, HM-ME-2310: FS | C-52-598-01-EI-2040, C-52-598-01-EI-2050 | C-52-598-01-EI-2040: FS, C-52-598-01-EI-2050: FS | 2025-05-16 07:00 | 2025-05-21 17:00
C-52-598-01-EI-2040 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.6 | Loop Checking for Instruments | C-52-598-01-EI-2410, C-52-598-01-EI-2200, C-52-598-01-EI-1810, C-52-598-01-EI-1600, C-52-598-01-EI-2400, C-52-598-01-EI-1200, C-52-598-01-EI-2010 | C-52-598-01-EI-2410: FS, C-52-598-01-EI-2200: FS, C-52-598-01-EI-1810: FS, C-52-598-01-EI-1600: FS, C-52-598-01-EI-2400: FS, C-52-598-01-EI-1200: FS, C-52-598-01-EI-2010: FS | C-52-598-01-EI-2050, PRECOM-56-59801-1000 | C-52-598-01-EI-2050: FS, PRECOM-56-59801-1000: FS | 2025-06-17 07:00 | 2025-06-25 17:00
C-52-598-01-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.6.6 | Glanding & Termination | C-52-598-01-EI-2040, C-52-598-01-EI-2000, C-52-598-01-EI-2010, C-52-598-01-EI-2030, C-52-598-01-EI-1200, C-52-598-01-EI-1800, C-52-598-01-EI-1000, C-52-598-01-EI-1810, C-52-598-01-EI-2200, C-52-598-01-EI-2410, C-52-598-01-EI-1600, C-52-598-01-EI-2400, C-52 | C-52-598-01-EI-2040: FS, C-52-598-01-EI-2000: FS, C-52-598-01-EI-2010: FS, C-52-598-01-EI-2030: FS, C-52-598-01-EI-1200: FS, C-52-598-01-EI-1800: FS, C-52-598-01-EI-1000: FS, C-52-598-01-EI-1810: FS, C-52-598-01-EI-2200: FS, C-52-598-01-EI-2410: FS, C-52-5 | PRECOM-56-59801-1000 | PRECOM-56-59801-1000: FS | 2025-06-26 07:00 | 2025-07-02 17:00
C-52-598-05-CA-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.7.1 | CP Cable Laying | C-52-598-05-EI-2000, HM-PL-0430, HS-CN-0240 | C-52-598-05-EI-2000: SS, HM-PL-0430: FS, HS-CN-0240: FS | C-52-598-05-CA-1010, C-52-598-05-CI-2800 | C-52-598-05-CA-1010: FS, C-52-598-05-CI-2800: FS | 2025-04-18 07:00 | 2025-04-23 17:00
C-52-598-05-CA-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.7.1 | Installation of CP Test Post | C-52-598-05-CA-1000 | C-52-598-05-CA-1000: FS | C-52-598-05-CA-1020 | C-52-598-05-CA-1020: FS | 2025-04-24 07:00 | 2025-04-26 17:00
C-52-598-05-CA-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.7.1 | Installation of CP S/m | C-52-598-05-CA-1010 | C-52-598-05-CA-1010: FS | PRECOM-56-59805-1000 | PRECOM-56-59805-1000: FS | 2025-04-28 07:00 | 2025-05-03 17:00
C-52-598-04-CA-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.7 | CP Cable Laying | C-52-598-04-EI-2000, HE-IC-0830, HM-EL-0520, HE-EL-1610, HE-EL-0590, HE-EL-0830, HM-EL-0080, HE-EL-0470, HE-IC-0950, HE-IC-1010, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-6 | C-52-598-04-EI-2000: FS, HE-IC-0830: FS, HM-EL-0520: FS, HE-EL-1610: FS, HE-EL-0590: FS, HE-EL-0830: FS, HM-EL-0080: FS, HE-EL-0470: FS, HE-IC-0950: FS, HE-IC-1010: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0 | C-52-598-04-CA-1010, C-52-598-04-CI-2800 | C-52-598-04-CA-1010: FS, C-52-598-04-CI-2800: FS 5 | 2025-04-25 07:00 | 2025-04-30 17:00
C-52-598-04-CA-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.7 | Installation of CP Test Post | C-52-598-04-CA-1000 | C-52-598-04-CA-1000: FS | C-52-598-04-CA-1020 | C-52-598-04-CA-1020: FS | 2025-05-01 07:00 | 2025-05-03 17:00
C-52-598-04-CA-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.6.7 | Installation of CP S/m | C-52-598-04-CA-1010 | C-52-598-04-CA-1010: FS | PRECOM-56-59804-1000 | PRECOM-56-59804-1000: FS | 2025-05-05 08:00 | 2025-05-12 15:00
C-52-598-03-CA-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.7.1 | CP Cable Laying | C-52-598-03-EI-2000, HM-PL-0430, HS-CN-0240 | C-52-598-03-EI-2000: FS, HM-PL-0430: FS, HS-CN-0240: FS | C-52-598-03-CA-1010, C-52-598-03-CI-2800 | C-52-598-03-CA-1010: FS, C-52-598-03-CI-2800: FS 5 | 2025-04-25 07:00 | 2025-04-30 17:00
C-52-598-03-CA-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.7.1 | Installation of CP Test Post | C-52-598-03-CA-1000 | C-52-598-03-CA-1000: FS | C-52-598-03-CA-1020 | C-52-598-03-CA-1020: FS | 2025-05-01 07:00 | 2025-05-03 17:00
C-52-598-03-CA-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.7.1 | Installation of CP S/m | C-52-598-03-CA-1010 | C-52-598-03-CA-1010: FS | PRECOM-56-59803-1000 | PRECOM-56-59803-1000: FS | 2025-05-05 08:00 | 2025-05-12 15:00
C-52-598-02-CA-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.7 | CP Cable Laying | C-52-598-02-EI-2000, HM-EL-0520, HE-IC-1010, HM-EL-0080, HE-EL-1610, HE-IC-0950, HE-EL-0470, HE-EL-0830, HE-EL-0590, HE-IC-0830, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-6 | C-52-598-02-EI-2000: FS, HM-EL-0520: FS, HE-IC-1010: FS, HM-EL-0080: FS, HE-EL-1610: FS, HE-IC-0950: FS, HE-EL-0470: FS, HE-EL-0830: FS, HE-EL-0590: FS, HE-IC-0830: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0 | C-52-598-02-CA-1010, C-52-598-02-CI-2800 | C-52-598-02-CA-1010: FS, C-52-598-02-CI-2800: FS | 2025-04-25 07:00 | 2025-04-30 17:00
C-52-598-02-CA-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.7 | Installation of CP Test Post | C-52-598-02-CA-1000 | C-52-598-02-CA-1000: FS | C-52-598-02-CA-1020 | C-52-598-02-CA-1020: FS | 2025-05-01 07:00 | 2025-05-03 17:00
C-52-598-02-CA-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.6.7 | Installation of CP S/m | C-52-598-02-CA-1010 | C-52-598-02-CA-1010: FS | PRECOM-56-59802-1000 | PRECOM-56-59802-1000: FS | 2025-05-05 08:00 | 2025-05-12 15:00
C-52-598-01-CA-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.7.1 | CP Cable Laying | C-52-598-01-EI-2000, HS-CN-0240, HM-PL-0430 | C-52-598-01-EI-2000: FS, HS-CN-0240: FS, HM-PL-0430: FS | C-52-598-01-CA-1010, C-52-598-01-CI-2800 | C-52-598-01-CA-1010: FS, C-52-598-01-CI-2800: FS 5 | 2025-04-25 07:00 | 2025-04-30 17:00
C-52-598-01-CA-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.7.1 | Installation of CP Test Post | C-52-598-01-CA-1000 | C-52-598-01-CA-1000: FS | C-52-598-01-CA-1020 | C-52-598-01-CA-1020: FS | 2025-05-01 07:00 | 2025-05-03 17:00
C-52-598-01-CA-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.7.1 | Installation of CP S/m | C-52-598-01-CA-1010 | C-52-598-01-CA-1010: FS | PRECOM-56-59801-1000 | PRECOM-56-59801-1000: FS | 2025-05-05 08:00 | 2025-05-12 15:00
C-52-598-05-TE-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.8.1 | Installation of SDH Cabinet | C-52-598-05-EI-2010, HE-TL-0350, HE-TL-0290, HE-TL-0830, ML1033-B22, HM-ME-1390, HM-TL-0050, HE-TL-0770, HE-TL-0410, HE-TL-0470, HM-EL-0180, HE-TL-0710, HS-CN-0290, HM-TL-0040, HM-ME-1290, HM-ME-2270, HM-ME-2290, HM-EL-610 | C-52-598-05-EI-2010: FS, HE-TL-0350: FS, HE-TL-0290: FS, HE-TL-0830: FS, ML1033-B22: FS, HM-ME-1390: FS, HM-TL-0050: FS, HE-TL-0770: FS, HE-TL-0410: FS, HE-TL-0470: FS, HM-EL-0180: FS, HE-TL-0710: FS, HS-CN-0290: FS, HM-TL-0040: FS, HM-ME-1290: FS, HM-ME-2 | C-52-598-05-TE-1200 | C-52-598-05-TE-1200: FS | 2025-05-28 07:00 | 2025-05-30 17:00
C-52-598-05-TE-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.8.2 | Installation of PIDS/ PLDS System | C-52-598-05-TE-1000 | C-52-598-05-TE-1000: FS | C-52-598-05-TE-1600 | C-52-598-05-TE-1600: FS | 2025-05-31 07:00 | 2025-06-03 17:00
C-52-598-05-TE-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.8.4 | Installation of CCTV System | C-52-598-05-TE-1200 | C-52-598-05-TE-1200: FS | C-52-598-05-TE-1400 | C-52-598-05-TE-1400: FS | 2025-06-04 07:00 | 2025-06-11 17:00
C-52-598-05-TE-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.8.3 | Installation of Telephone System | C-52-598-05-TE-1600 | C-52-598-05-TE-1600: FS | PRECOM-56-59805-1000 | PRECOM-56-59805-1000: FS | 2025-06-12 07:00 | 2025-06-18 17:00
C-52-598-04-TE-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.8.1 | Installation of SDH Cabinet | C-52-598-04-EI-2010, HM-TL-0050, HE-TL-0830, HE-TL-0410, HM-TL-0040, ML1033-B22, HE-TL-0350, HM-ME-1390, HS-CN-0290, HM-ME-1290, HM-EL-0180, HE-TL-0290, HE-IC-0110, HE-TL-0770, HE-TL-0710, HE-TL-0470, HM-ME-2270, HM-ME-2290, HM-EL-610 | C-52-598-04-EI-2010: FS, HM-TL-0050: FS, HE-TL-0830: FS, HE-TL-0410: FS, HM-TL-0040: FS, ML1033-B22: FS, HE-TL-0350: FS, HM-ME-1390: FS, HS-CN-0290: FS, HM-ME-1290: FS, HM-EL-0180: FS, HE-TL-0290: FS, HE-IC-0110: FS, HE-TL-0770: FS, HE-TL-0710: FS, HE-TL-0 | C-52-598-04-TE-1200 | C-52-598-04-TE-1200: FS | 2025-05-28 07:00 | 2025-05-30 17:00
C-52-598-04-TE-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.8.2 | Installation of PIDS/ PLDS System | C-52-598-04-TE-1000 | C-52-598-04-TE-1000: FS | C-52-598-04-TE-1600 | C-52-598-04-TE-1600: FS | 2025-05-31 07:00 | 2025-06-03 17:00
C-52-598-04-TE-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.8.4 | Installation of CCTV System | C-52-598-04-TE-1200 | C-52-598-04-TE-1200: FS | C-52-598-04-TE-1400 | C-52-598-04-TE-1400: FS | 2025-06-04 07:00 | 2025-06-11 17:00
C-52-598-04-TE-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.8.3 | Installation of Telephone System | C-52-598-04-TE-1600 | C-52-598-04-TE-1600: FS | PRECOM-56-59804-1000 | PRECOM-56-59804-1000: FS | 2025-06-12 07:00 | 2025-06-18 17:00
C-52-598-03-TE-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.8.1 | Installation of SDH Cabinet | C-52-598-03-EI-2010, HE-TL-0350, HS-CN-0290, HE-TL-0470, HM-ME-1290, HM-TL-0050, HM-EL-0180, HE-TL-0290, HE-TL-0710, ML1033-B22, HE-TL-0830, HE-TL-0770, HM-ME-1390, HM-TL-0040, HE-TL-0410, HM-ME-2270, HM-ME-2290, HM-EL-610 | C-52-598-03-EI-2010: FS, HE-TL-0350: FS, HS-CN-0290: FS, HE-TL-0470: FS, HM-ME-1290: FS, HM-TL-0050: FS, HM-EL-0180: FS, HE-TL-0290: FS, HE-TL-0710: FS, ML1033-B22: FS, HE-TL-0830: FS, HE-TL-0770: FS, HM-ME-1390: FS, HM-TL-0040: FS, HE-TL-0410: FS, HM-ME-2 | C-52-598-03-TE-1200 | C-52-598-03-TE-1200: FS | 2025-05-28 07:00 | 2025-05-30 17:00
C-52-598-03-TE-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.8.2 | Installation of PIDS/ PLDS System | C-52-598-03-TE-1000, HM-ME-0280 | C-52-598-03-TE-1000: FS, HM-ME-0280: FS | C-52-598-03-TE-1600 | C-52-598-03-TE-1600: FS | 2025-05-31 07:00 | 2025-06-03 17:00
C-52-598-03-TE-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.8.4 | Installation of CCTV System | C-52-598-03-TE-1200 | C-52-598-03-TE-1200: FS | C-52-598-03-TE-1400 | C-52-598-03-TE-1400: FS | 2025-06-04 07:00 | 2025-06-11 17:00
C-52-598-03-TE-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.8.3 | Installation of Telephone System | C-52-598-03-TE-1600 | C-52-598-03-TE-1600: FS | PRECOM-56-59803-1000 | PRECOM-56-59803-1000: FS | 2025-06-12 07:00 | 2025-06-18 17:00
C-52-598-02-TE-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.8.1 | Installation of SDH Cabinet | C-52-598-02-EI-2010, HM-ME-1390, HE-TL-0470, HM-ME-1290, HS-CN-0290, HE-TL-0770, HE-TL-0830, HM-TL-0040, HE-TL-0710, ML1033-B22, HE-TL-0410, HE-TL-0290, HM-TL-0050, HM-EL-0180, HE-TL-0350, HM-ME-2270, HM-ME-2290, HM-EL-610 | C-52-598-02-EI-2010: FS, HM-ME-1390: FS, HE-TL-0470: FS, HM-ME-1290: FS, HS-CN-0290: FS, HE-TL-0770: FS, HE-TL-0830: FS, HM-TL-0040: FS, HE-TL-0710: FS, ML1033-B22: FS, HE-TL-0410: FS, HE-TL-0290: FS, HM-TL-0050: FS, HM-EL-0180: FS, HE-TL-0350: FS, HM-ME-2 | C-52-598-02-TE-1200 | C-52-598-02-TE-1200: FS | 2025-05-28 07:00 | 2025-05-30 17:00
C-52-598-02-TE-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.8.2 | Installation of PIDS/ PLDS System | C-52-598-02-TE-1000 | C-52-598-02-TE-1000: FS | C-52-598-02-TE-1600 | C-52-598-02-TE-1600: FS | 2025-05-31 07:00 | 2025-06-03 17:00
C-52-598-02-TE-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.8.4 | Installation of CCTV System | C-52-598-02-TE-1200 | C-52-598-02-TE-1200: FS | C-52-598-02-TE-1400 | C-52-598-02-TE-1400: FS | 2025-06-04 07:00 | 2025-06-11 17:00
C-52-598-02-TE-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.8.3 | Installation of Telephone System | C-52-598-02-TE-1600 | C-52-598-02-TE-1600: FS | PRECOM-56-59802-1000 | PRECOM-56-59802-1000: FS | 2025-06-12 07:00 | 2025-06-18 17:00
C-52-598-01-TE-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.8.1 | Installation of SDH Cabinet | C-52-598-01-EI-2010, HE-TL-0770, HE-TL-0410, ML1479-D15, HE-TL-0470, HS-CN-0290, HE-TL-0350, HE-TL-0830, HM-ME-1390, HE-TL-0710, HM-TL-0050, HM-TL-0040, ML1056-D14, ML1033-B22, HM-ME-1290, HE-TL-0290, HM-ME-2270, HM-ME-2290 | C-52-598-01-EI-2010: FS, HE-TL-0770: FS, HE-TL-0410: FS, ML1479-D15: FS, HE-TL-0470: FS, HS-CN-0290: FS, HE-TL-0350: FS, HE-TL-0830: FS, HM-ME-1390: FS, HE-TL-0710: FS, HM-TL-0050: FS, HM-TL-0040: FS, ML1056-D14: FS, ML1033-B22: FS, HM-ME-1290: FS, HE-TL-0 | C-52-598-01-TE-1200 | C-52-598-01-TE-1200: FS | 2025-05-28 07:00 | 2025-05-30 17:00
C-52-598-01-TE-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.8.2 | Installation of PIDS/ PLDS System | C-52-598-01-TE-1000 | C-52-598-01-TE-1000: FS | C-52-598-01-TE-1600 | C-52-598-01-TE-1600: FS | 2025-05-31 07:00 | 2025-06-03 17:00
C-52-598-01-TE-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.8.4 | Installation of CCTV System | C-52-598-01-TE-1200 | C-52-598-01-TE-1200: FS | C-52-598-01-TE-1400 | C-52-598-01-TE-1400: FS | 2025-06-04 07:00 | 2025-06-11 17:00
C-52-598-01-TE-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.8.3 | Installation of Telephone System | C-52-598-01-TE-1600 | C-52-598-01-TE-1600: FS | PRECOM-56-59801-1000 | PRECOM-56-59801-1000: FS | 2025-06-12 07:00 | 2025-06-18 17:00
C-56-591-01-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.9 | Site Survey, Preparation & Grading Works | HE-SS-0030, ML1002, HE-CS-0470, CTF-1000, HE-CS-0170, ML1035-B26, CTF-1010, HE-CS-0530 | HE-SS-0030: SS, ML1002: FS, HE-CS-0470: FS, CTF-1000: FS, HE-CS-0170: FS, ML1035-B26: FF 32, CTF-1010: FS, HE-CS-0530: FS | C-56-591-01-CI-1010 | C-56-591-01-CI-1010: SS 4 | 2025-01-16 07:00 | 2025-01-25 07:00
C-56-591-01-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.9 | Earth Works for Equipment Foundations & Hard Stand Area | C-56-591-01-CI-1000, C-52-598-01-CI-1010 | C-56-591-01-CI-1000: SS 4, C-52-598-01-CI-1010: FS | C-56-591-01-CI-1020, C-56-591-01-CI-1400, C-56-591-01-CI-3020 | C-56-591-01-CI-1020: SS 7, C-56-591-01-CI-1400: FS, C-56-591-01-CI-3020: FS | 2025-01-21 07:00 | 2025-02-05 17:00
C-56-591-01-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.9 | Earth Works for Pipe Support Foundations | C-56-591-01-CI-1010 | C-56-591-01-CI-1010: SS 7 | C-56-591-01-CI-1030, C-56-591-01-CI-1800, C-56-591-01-CI-1600, C-56-591-01-CI-3030 | C-56-591-01-CI-1030: SS 6, C-56-591-01-CI-1800: FS, C-56-591-01-CI-1600: FS, C-56-591-01-CI-3030: FS | 2025-01-29 07:00 | 2025-02-13 17:00
C-56-591-01-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.9 | Earth Works for Field Instrument Foundations | C-56-591-01-CI-1020 | C-56-591-01-CI-1020: SS 6 | C-56-591-01-CI-1040, C-56-591-01-CI-1410, C-56-591-01-CI-3040 | C-56-591-01-CI-1040: SS 7, C-56-591-01-CI-1410: FS, C-56-591-01-CI-3040: FS | 2025-02-05 07:00 | 2025-02-18 17:00
C-56-591-01-CI-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.9 | Earth Works for Access Platforms & Misc. Structural Foundations | C-56-591-01-CI-1030 | C-56-591-01-CI-1030: SS 7 | C-56-591-01-CI-1050, C-56-591-01-CI-1420, C-56-591-01-CI-3050 | C-56-591-01-CI-1050: SS 6, C-56-591-01-CI-1420: FS, C-56-591-01-CI-3050: FS | 2025-02-13 07:00 | 2025-02-28 17:00
C-56-591-01-CI-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.9 | Earth Works for Light Pole, Fence & Gates Foundation | C-56-591-01-CI-1040 | C-56-591-01-CI-1040: SS 6 | C-56-591-01-CI-1430, C-56-591-01-CI-1430, C-56-591-01-CI-3060 | C-56-591-01-CI-1430: FS, C-56-591-01-CI-1430: FF, C-56-591-01-CI-3060: FS | 2025-02-20 07:00 | 2025-03-06 13:00
C-56-591-01-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.11 | Concrete Works for Equipment Foundations & Hard Stand Area | C-56-591-01-CI-1010, C-56-591-01-CI-3020, HE-CS-1190, HE-CS-1310, HE-HS-0410, HE-CS-0230, ML1035-B26, HM-CS-0040, HE-CS-0890 | C-56-591-01-CI-1010: FS, C-56-591-01-CI-3020: FS, HE-CS-1190: FS, HE-CS-1310: FS, HE-HS-0410: FS, HE-CS-0230: FS, ML1035-B26: FS, HM-CS-0040: FS, HE-CS-0890: FS | C-56-591-01-ME-1000, C-56-591-01-EI-1000 | C-56-591-01-ME-1000: FS, C-56-591-01-EI-1000: FS | 2025-02-12 07:00 | 2025-03-09 11:00
C-56-591-01-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.13 | Concrete Works for Pipe Support Foundations | C-52-598-01-CI-1600, C-56-591-01-CI-1020, C-56-591-01-CI-3030, HE-CS-0230 | C-52-598-01-CI-1600: FS, C-56-591-01-CI-1020: FS, C-56-591-01-CI-3030: FS, HE-CS-0230: FS | C-56-591-01-CI-2000 | C-56-591-01-CI-2000: FF 7 | 2025-02-21 07:00 | 2025-03-22 09:00
C-56-591-01-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.11 | Concrete Works for Field Instrument, JB Foundations | C-56-591-01-CI-1030, C-56-591-01-CI-3040, HE-HS-0410, HE-CS-0230, ML1035-B26, HM-CS-0040 | C-56-591-01-CI-1030: FS, C-56-591-01-CI-3040: FS, HE-HS-0410: FS, HE-CS-0230: FS, ML1035-B26: FS, HM-CS-0040: FS | C-56-591-01-CI-1420 | C-56-591-01-CI-1420: FS | 2025-02-25 07:00 | 2025-03-15 15:00
C-56-591-01-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.11 | Concrete Works for Access Platform & Misc. Structural Foundations | C-56-591-01-CI-1410, C-56-591-01-CI-1040, C-56-591-01-CI-3050 | C-56-591-01-CI-1410: FS, C-56-591-01-CI-1040: FS, C-56-591-01-CI-3050: FS | C-56-591-01-CI-1430, C-56-591-01-EI-1210 | C-56-591-01-CI-1430: FS, C-56-591-01-EI-1210: FS 88 | 2025-03-15 15:00 | 2025-04-05 13:00
C-56-591-01-CI-1430 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.11 | Concrete Works for Light Pole, Fence & Gates Foundation | C-56-591-01-CI-1420, C-56-591-01-CI-1050, C-56-591-01-CI-1050, C-56-591-01-CI-3060, HE-CS-1010 | C-56-591-01-CI-1420: FS, C-56-591-01-CI-1050: FS, C-56-591-01-CI-1050: FF, C-56-591-01-CI-3060: FS, HE-CS-1010: FS | C-56-591-01-CI-2200 | C-56-591-01-CI-2200: FS | 2025-04-05 13:00 | 2025-04-30 13:00
C-56-591-01-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.14 | Electrical & Earthing Cable Trenching | C-56-591-01-CI-1020, HE-CS-0530 | C-56-591-01-CI-1020: FS, HE-CS-0530: FS | C-56-591-01-CI-1810, C-56-591-01-EI-2000 | C-56-591-01-CI-1810: FS, C-56-591-01-EI-2000: FS | 2025-02-14 07:00 | 2025-03-26 11:00
C-56-591-01-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.14 | Instrument & Telecom Cable Trenching | C-56-591-01-CI-1800 | C-56-591-01-CI-1800: FS | C-56-591-01-EI-2010 | C-56-591-01-EI-2010: FS | 2025-03-26 11:00 | 2025-04-24 13:00
C-56-591-01-CI-2200 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.12 | Installation of Concrete Pillers for Boundary Wall | C-56-591-01-CI-1430, HE-CS-0350, HE-CS-0470 | C-56-591-01-CI-1430: FS, HE-CS-0350: FS, HE-CS-0470: FS | C-56-591-01-CI-2210 | C-56-591-01-CI-2210: SS 7 | 2025-04-30 13:00 | 2025-05-26 11:00
C-56-591-01-CI-2210 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.12 | Block Works for Boundary Wall | C-56-591-01-CI-2200 | C-56-591-01-CI-2200: SS 7 | C-56-591-01-CI-2220 | C-56-591-01-CI-2220: FS | 2025-05-09 11:00 | 2025-06-03 11:00
C-56-591-01-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.12 | Installation of Fence Post & Mesh Works (Type-4 & 3) | C-56-591-01-CI-2210 | C-56-591-01-CI-2210: FS | C-56-591-01-CI-2230, PRECOM-56-59101-1000 | C-56-591-01-CI-2230: FS, PRECOM-56-59101-1000: FS | 2025-06-03 11:00 | 2025-07-11 11:00
C-56-591-01-CI-2230 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.12 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | C-56-591-01-CI-2220 | C-56-591-01-CI-2220: FS | C-56-591-01-CI-2600, PRECOM-56-59101-1000 | C-56-591-01-CI-2600: SS 7, PRECOM-56-59101-1000: FS | 2025-07-11 11:00 | 2025-08-05 11:00
C-56-591-01-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.16 | Back Filling for Electrical & Earthing Cable | C-56-591-01-EI-2000, C-56-591-01-CA-1000 | C-56-591-01-EI-2000: FS 14, C-56-591-01-CA-1000: FS 14 | PRECOM-56-59101-1000 | PRECOM-56-59101-1000: FS | 2025-05-17 15:00 | 2025-06-03 15:00
C-56-591-01-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.16 | Back Filling for Instrument & Telecom Cable | C-56-591-01-EI-2010 | C-56-591-01-EI-2010: FS 14 | PRECOM-56-59101-1000 | PRECOM-56-59101-1000: FS | 2025-05-19 15:00 | 2025-06-04 15:00
C-56-591-01-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.17 | Pre-Fabrication & Installation of Pipe Supports | C-56-591-01-CI-1600, HM-CS-0120, HS-CN-0690, HE-CS-1490, HE-CS-1430, HM-CS-0110 | C-56-591-01-CI-1600: FF 7, HM-CS-0120: FF, HS-CN-0690: FS, HE-CS-1490: FS, HE-CS-1430: FS, HM-CS-0110: FS | C-56-591-01-EI-2210, C-56-591-01-CI-3000 | C-56-591-01-EI-2210: SS 7, C-56-591-01-CI-3000: FS | 2025-03-11 09:00 | 2025-04-04 13:00
C-56-591-01-EI-2210 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.5 | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-56-591-01-CI-2000 | C-56-591-01-CI-2000: SS 7 | C-56-591-01-CI-3010, C-56-591-01-CI-2400 | C-56-591-01-CI-3010: FS, C-56-591-01-CI-2400: FS | 2025-03-22 09:00 | 2025-04-12 13:00
C-56-591-01-CI-3000 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.19 | Pre-Fabrication & Installation of Platforms & Crossovers | C-56-591-01-CI-2000, HM-CS-0110, HS-CN-0690 | C-56-591-01-CI-2000: FS, HM-CS-0110: FS, HS-CN-0690: FS | C-56-591-01-CI-3010 | C-56-591-01-CI-3010: FS | 2025-04-04 13:00 | 2025-05-08 10:00
C-56-591-01-CI-3010 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.19 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-56-591-01-EI-2210, C-56-591-01-CI-3000 | C-56-591-01-EI-2210: FS, C-56-591-01-CI-3000: FS | PRECOM-56-59101-1000 | PRECOM-56-59101-1000: FS | 2025-05-08 10:00 | 2025-05-24 11:00
C-56-591-01-EI-1210 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.3 | Installation of Solar Panel Structural Supports | C-56-591-01-CI-1420, HM-ME-1090 | C-56-591-01-CI-1420: FS 88, HM-ME-1090: FS | C-56-591-01-EI-1200 | C-56-591-01-EI-1200: FS | 2025-07-22 11:00 | 2025-08-05 11:00
C-56-591-01-CI-2400 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.18 | Installation of Fire Point Shelters | C-56-591-01-EI-2210, HM-CS-0110 | C-56-591-01-EI-2210: FS, HM-CS-0110: FS | C-56-591-01-ME-1000 | C-56-591-01-ME-1000: FS 12 | 2025-04-12 13:00 | 2025-04-22 13:00
C-56-591-01-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.3.9 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | C-56-591-01-CI-1400, C-56-591-01-CI-2400, HM-ME-1990, ML1015-B08, HM-ME-2370 | C-56-591-01-CI-1400: FS, C-56-591-01-CI-2400: FS 12, HM-ME-1990: FS, ML1015-B08: FS, HM-ME-2370: FS | PRECOM-56-59101-1000 | PRECOM-56-59101-1000: FS | 2025-05-07 08:00 | 2025-05-16 11:00
C-56-591-01-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.4.1 | Piping Pre-Fabrication | ML1002, HE-PR-0890, HE-PR-0290, HE-PI-0820, HE-PI-1300, HM-PI-0040, HS-CN-0190, HE-PI-1240, ML1014-B10, ML1219-B19, HE-PI-0580 | ML1002: FS, HE-PR-0890: FS, HE-PR-0290: FS, HE-PI-0820: FS, HE-PI-1300: FS, HM-PI-0040: FS, HS-CN-0190: FS, HE-PI-1240: FS, ML1014-B10: FS, ML1219-B19: FS, HE-PI-0580: FS | C-56-591-01-PI-1200, C-56-591-01-PL-1000 | C-56-591-01-PI-1200: FS, C-56-591-01-PL-1000: FS | 2025-02-24 07:00 | 2025-03-24 13:00
C-56-591-01-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.4.2 | Piping Erection | C-56-591-01-PI-1000, ML1002, HM-PL-0740, HE-PR-0890, HE-PR-0290, HM-PL-0630, HE-PI-1300, HM-PI-0040, HM-PI-0050, HM-PL-0640, HS-CN-0190, HM-PL-0220, HE-PI-1240, ML1014-B10, ML1219-B19, HM-PL-1510, HM-PL-1570 | C-56-591-01-PI-1000: FS, ML1002: FS, HM-PL-0740: FS, HE-PR-0890: FS, HE-PR-0290: FS, HM-PL-0630: FS, HE-PI-1300: FS, HM-PI-0040: FS, HM-PI-0050: FF, HM-PL-0640: FS, HS-CN-0190: FS, HM-PL-0220: FS, HE-PI-1240: FS, ML1014-B10: FS, ML1219-B19: FS, HM-PL-1510: | C-56-591-01-PI-1400 | C-56-591-01-PI-1400: SS 2 | 2025-03-28 07:00 | 2025-04-17 11:00
C-56-591-01-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.4.3 | Field Joint Welding (Including Isolation Joint) | C-56-591-01-PI-1200, HE-PI-1300, ML1002, HS-CN-0190, ML1014-B10, ML1219-B19 | C-56-591-01-PI-1200: SS 2, HE-PI-1300: FS, ML1002: FS, HS-CN-0190: FS, ML1014-B10: FS, ML1219-B19: FS | C-56-591-01-PI-1410 | C-56-591-01-PI-1410: SS 3 | 2025-04-03 11:00 | 2025-04-17 11:00
C-56-591-01-PI-1410 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.4.3 | NDT & Coating for Field Joint Weld | C-56-591-01-PI-1400 | C-56-591-01-PI-1400: SS 3 | C-56-591-01-PI-1600 | C-56-591-01-PI-1600: FS | 2025-04-07 11:00 | 2025-04-21 11:00
C-56-591-01-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.4.4 | Hydrotesting | C-56-591-01-PI-1410, ML1014-B10, ML1219-B19 | C-56-591-01-PI-1410: FS, ML1014-B10: FS, ML1219-B19: FS | C-56-591-01-PI-1800 | C-56-591-01-PI-1800: FS | 2025-04-21 11:00 | 2025-04-26 11:00
C-56-591-01-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.4.5 | Installation of Valves & GOV | C-56-591-01-PI-1600, HM-PL-0740, HE-PR-0890, HE-PR-0290, HM-PL-0630, HM-PL-0640, HM-PL-0220, HE-PI-1240, ML1014-B10, ML1219-B19, HM-ME-2200, HM-PL-1510, HM-PL-1570, HM-ME-0580, HM-ME-2210 | C-56-591-01-PI-1600: FS, HM-PL-0740: FS, HE-PR-0890: FS, HE-PR-0290: FS, HM-PL-0630: FS, HM-PL-0640: FS, HM-PL-0220: FS, HE-PI-1240: FS, ML1014-B10: FS, ML1219-B19: FS, HM-ME-2200: FS, HM-PL-1510: FS, HM-PL-1570: FS, HM-ME-0580: FS, HM-ME-2210: FS | C-56-591-01-PI-2000, PRECOM-56-59101-1000 | C-56-591-01-PI-2000: SS 4, PRECOM-56-59101-1000: FS | 2025-07-21 07:00 | 2025-07-25 17:00
C-56-591-01-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.4.6 | Final Bolt Torquing/ Re-Instatement | C-56-591-01-PI-1800, HE-PI-1300, ML1002, HM-PL-0740, HE-PR-0890, HE-PR-0290, HM-PL-0630, HM-PL-0640, HS-CN-0190, HM-PL-0220, HE-PI-1240, ML1014-B10, ML1219-B19, HM-ME-2200, HM-PL-1510, HM-PL-1570 | C-56-591-01-PI-1800: SS 4, HE-PI-1300: FS, ML1002: FS, HM-PL-0740: FS, HE-PR-0890: FS, HE-PR-0290: FS, HM-PL-0630: FS, HM-PL-0640: FS, HS-CN-0190: FS, HM-PL-0220: FS, HE-PI-1240: FS, ML1014-B10: FS, ML1219-B19: FS, HM-ME-2200: FS, HM-PL-1510: FS, HM-PL-157 | PRECOM-56-59101-1000 | PRECOM-56-59101-1000: FS | 2025-07-25 07:00 | 2025-07-28 17:00
C-56-591-01-PL-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.5.1 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | C-56-591-01-PI-1000 | C-56-591-01-PI-1000: FS | C-56-591-01-PL-1010 | C-56-591-01-PL-1010: FS | 2025-03-25 07:00 | 2025-04-04 13:00
C-56-591-01-PL-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.5.1 | Lowering of Pipeline Section | C-56-591-01-PL-1000 | C-56-591-01-PL-1000: FS | C-56-591-01-PL-1020 | C-56-591-01-PL-1020: SS | 2025-04-04 13:00 | 2025-04-07 13:00
C-56-591-01-PL-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.5.1 | Section Tie-in Welding (Including Barred Tee) | C-56-591-01-PL-1010 | C-56-591-01-PL-1010: SS | C-56-591-01-PL-1030 | C-56-591-01-PL-1030: SS 1 | 2025-04-04 13:00 | 2025-04-18 13:00
C-56-591-01-PL-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.5.1 | NDT for Tie-in Joint | C-56-591-01-PL-1020 | C-56-591-01-PL-1020: SS 1 | C-56-591-01-PL-1040 | C-56-591-01-PL-1040: SS 1 | 2025-04-05 13:00 | 2025-04-19 13:00
C-56-591-01-PL-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.5.1 | Ext. Coating for Tie-in Joint | C-56-591-01-PL-1030 | C-56-591-01-PL-1030: SS 1 | C-56-591-01-PL-1050 | C-56-591-01-PL-1050: FS | 2025-04-07 13:00 | 2025-04-21 13:00
C-56-591-01-PL-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.5.1 | Holiday Testing of Pipeline Section | C-56-591-01-PL-1040 | C-56-591-01-PL-1040: FS | C-56-591-01-PL-1060, C-56-591-01-PL-1090 | C-56-591-01-PL-1060: FS, C-56-591-01-PL-1090: FS | 2025-04-21 13:00 | 2025-04-22 13:00
C-56-591-01-PL-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.5.1 | Installation of ROV | C-56-591-01-PL-1050, HM-ME-0580, HM-ME-2210 | C-56-591-01-PL-1050: FS, HM-ME-0580: FS, HM-ME-2210: FS | C-56-591-01-PL-1070, C-56-591-01-PL-1090, PRECOM-56-59101-1000 | C-56-591-01-PL-1070: FS, C-56-591-01-PL-1090: FF 1, PRECOM-56-59101-1000: FS | 2025-07-21 07:00 | 2025-07-21 17:00
C-56-591-01-PL-1070 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.5.1 | Installation of Pig Signaller Pit | C-56-591-01-PL-1060 | C-56-591-01-PL-1060: FS | C-56-591-01-PL-1080, C-56-591-01-PL-1090 | C-56-591-01-PL-1080: FS, C-56-591-01-PL-1090: FF 1 | 2025-07-22 07:00 | 2025-07-24 17:00
C-56-591-01-PL-1080 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.5.1 | Installation of Pig Signaller | C-56-591-01-PL-1070 | C-56-591-01-PL-1070: FS | C-56-591-01-PL-1090, PRECOM-56-59101-1000 | C-56-591-01-PL-1090: FF, PRECOM-56-59101-1000: FS | 2025-07-25 07:00 | 2025-07-25 17:00
C-56-591-01-PL-1090 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.5.1 | Padding & Backfilling | C-56-591-01-PL-1080, C-56-591-01-PL-1050, C-56-591-01-PL-1060, C-56-591-01-PL-1070 | C-56-591-01-PL-1080: FF, C-56-591-01-PL-1050: FS, C-56-591-01-PL-1060: FF 1, C-56-591-01-PL-1070: FF 1 | PRECOM-56-59101-1000 | PRECOM-56-59101-1000: FS | 2025-07-16 07:00 | 2025-07-25 17:00
C-56-591-01-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.2 | Electrical & Earthing Cable Laying | C-56-591-01-CI-1800, HM-EL-0080, HE-IC-1010, HE-EL-0830, HE-EL-0470, HE-IC-0830, HE-IC-0950, HM-EL-0520, HE-EL-0590, HE-EL-1610, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-6 | C-56-591-01-CI-1800: FS, HM-EL-0080: FS, HE-IC-1010: FS, HE-EL-0830: FS, HE-EL-0470: FS, HE-IC-0830: FS, HE-IC-0950: FS, HM-EL-0520: FS, HE-EL-0590: FS, HE-EL-1610: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0 | C-56-591-01-EI-2050, C-56-591-01-EI-1400, C-56-591-01-CA-1000, C-56-591-01-CI-2800 | C-56-591-01-EI-2050: FS, C-56-591-01-EI-1400: FF, C-56-591-01-CA-1000: FS, C-56-591-01-CI-2800: FS 14 | 2025-04-18 07:00 | 2025-04-24 17:00
C-56-591-01-EI-1400 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.1 | Deep Earth Well Drilling | C-56-591-01-EI-2000 | C-56-591-01-EI-2000: FF | C-56-591-01-EI-2010 | C-56-591-01-EI-2010: FS | 2025-04-22 07:00 | 2025-04-24 17:00
C-56-591-01-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.2 | Instrument Cable Laying | C-56-591-01-EI-1400, C-56-591-01-CI-1810, HM-EL-0080, HE-IC-1010, HE-EL-0830, HE-EL-0470, HE-IC-0830, HE-IC-0950, HM-EL-0520, HE-EL-0590, HE-EL-1610, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250 | C-56-591-01-EI-1400: FS, C-56-591-01-CI-1810: FS, HM-EL-0080: FS, HE-IC-1010: FS, HE-EL-0830: FS, HE-EL-0470: FS, HE-IC-0830: FS, HE-IC-0950: FS, HM-EL-0520: FS, HE-EL-0590: FS, HE-EL-1610: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS | C-56-591-01-EI-2040, C-56-591-01-EI-2050, C-56-591-01-EI-2020, C-56-591-01-CI-2810, C-56-591-01-TE-1000 | C-56-591-01-EI-2040: FS, C-56-591-01-EI-2050: FS, C-56-591-01-EI-2020: FS, C-56-591-01-CI-2810: FS 14, C-56-591-01-TE-1000: FS | 2025-04-25 07:00 | 2025-05-01 17:00
C-56-591-01-EI-2020 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.2 | Installation of Cable Trays | C-56-591-01-EI-2010 | C-56-591-01-EI-2010: FS | C-56-591-01-EI-2030 | C-56-591-01-EI-2030: FS | 2025-05-02 07:00 | 2025-05-09 15:00
C-56-591-01-EI-2030 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.2 | Instrument Tubing Works | C-56-591-01-EI-2020 | C-56-591-01-EI-2020: FS | C-56-591-01-EI-2050, C-56-591-01-EI-1200 | C-56-591-01-EI-2050: FS, C-56-591-01-EI-1200: FS | 2025-05-09 15:00 | 2025-05-15 15:00
C-56-591-01-EI-1200 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.3 | Installation of Solar S/m (Including Panels, UPS & Battery) | C-56-591-01-EI-2030, C-56-591-01-EI-1210 | C-56-591-01-EI-2030: FS, C-56-591-01-EI-1210: FS | C-56-591-01-EI-2040, C-56-591-01-EI-2050, C-56-591-01-EI-1800, C-56-591-01-EI-1000 | C-56-591-01-EI-2040: FS, C-56-591-01-EI-2050: FS, C-56-591-01-EI-1800: FS, C-56-591-01-EI-1000: SS 5 | 2025-08-05 11:00 | 2025-08-21 11:00
C-56-591-01-EI-1800 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.4 | Installation of Light Pole, Lighting & Fixtures | C-56-591-01-EI-1200 | C-56-591-01-EI-1200: FS | C-56-591-01-EI-2050, ML1629-E08 | C-56-591-01-EI-2050: FS, ML1629-E08: FS | 2025-08-21 11:00 | 2025-08-28 11:00
C-56-591-01-EI-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.9 | Installation of Passive Cooling Shelter | C-56-591-01-CI-1400, C-56-591-01-EI-1200, ML1054-D09, HM-ME-1190 | C-56-591-01-CI-1400: FS, C-56-591-01-EI-1200: SS 5, ML1054-D09: FS, HM-ME-1190: FS | C-56-591-01-EI-1600, C-56-591-01-EI-2050, C-56-591-01-EI-1600, ML1629-E08 | C-56-591-01-EI-1600: FS, C-56-591-01-EI-2050: FS, C-56-591-01-EI-1600: FF, ML1629-E08: FS | 2025-08-11 11:00 | 2025-08-14 11:00
C-56-591-01-EI-1600 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.7 | Installation of RTU | C-56-591-01-EI-1000, C-56-591-01-EI-1000, HM-EL-0080, HE-EL-1010, HM-ME-1590, HE-IC-0530, HM-ME-0890, HE-EL-1790, HE-EL-0530, HM-EL-0520, HE-IC-0490, ML1032-B21, HM-IC-0050, HM-EL-0280, HE-EL-1670, HE-HS-0350, HE-IC-1550, HE-EL-0770, HM-EL-0530, HM-EL-0380 | C-56-591-01-EI-1000: FS, C-56-591-01-EI-1000: FF, HM-EL-0080: FS, HE-EL-1010: FS, HM-ME-1590: FF, HE-IC-0530: FS, HM-ME-0890: FS, HE-EL-1790: FS, HE-EL-0530: FS, HM-EL-0520: FS, HE-IC-0490: FS, ML1032-B21: FS, HM-IC-0050: FF, HM-EL-0280: FS, HE-EL-1670: FS | C-56-591-01-EI-2400, C-56-591-01-EI-2040, C-56-591-01-EI-2050, C-56-591-01-EI-2400 | C-56-591-01-EI-2400: FS, C-56-591-01-EI-2040: FS, C-56-591-01-EI-2050: FS, C-56-591-01-EI-2400: FF | 2025-08-14 11:00 | 2025-08-16 11:00
C-56-591-01-EI-2400 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.6 | Installation of F&G Panel | C-56-591-01-EI-1600, C-56-591-01-EI-1600 | C-56-591-01-EI-1600: FS, C-56-591-01-EI-1600: FF | C-56-591-01-EI-2040, C-56-591-01-EI-2050, C-56-591-01-EI-1810, ML1629-E08 | C-56-591-01-EI-2040: FS, C-56-591-01-EI-2050: FS, C-56-591-01-EI-1810: FS, ML1629-E08: FS | 2025-08-16 11:00 | 2025-08-19 11:00
C-56-591-01-EI-1810 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.4 | Installation of Lighting & Instrument JB's | C-56-591-01-EI-2400 | C-56-591-01-EI-2400: FS | C-56-591-01-EI-2040, C-56-591-01-EI-2050, C-56-591-01-EI-2200, ML1629-E08 | C-56-591-01-EI-2040: FS, C-56-591-01-EI-2050: FS, C-56-591-01-EI-2200: FS, ML1629-E08: FS | 2025-08-19 11:00 | 2025-08-22 11:00
C-56-591-01-EI-2200 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.5 | Installation of Field Instruments | C-56-591-01-EI-1810 | C-56-591-01-EI-1810: FS | C-56-591-01-EI-2040, C-56-591-01-EI-2050, C-56-591-01-EI-2410 | C-56-591-01-EI-2040: FS, C-56-591-01-EI-2050: FS, C-56-591-01-EI-2410: FS | 2025-08-22 11:00 | 2025-08-29 11:00
C-56-591-01-EI-2410 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.6 | Installation of F&G Devices | C-56-591-01-EI-2200, HM-ME-1490, HM-ME-2310 | C-56-591-01-EI-2200: FS, HM-ME-1490: FS, HM-ME-2310: FS | C-56-591-01-EI-2040, C-56-591-01-EI-2050, C-56-591-01-EI-2040, ML1629-E08 | C-56-591-01-EI-2040: FS, C-56-591-01-EI-2050: FS, C-56-591-01-EI-2040: FF, ML1629-E08: FS | 2025-08-29 11:00 | 2025-09-04 11:00
C-56-591-01-EI-2040 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.2 | Loop Checking for Instruments | C-56-591-01-EI-2410, C-56-591-01-EI-2200, C-56-591-01-EI-1810, C-56-591-01-EI-1600, C-56-591-01-EI-2400, C-56-591-01-EI-1200, C-56-591-01-EI-2010, C-56-591-01-EI-2410 | C-56-591-01-EI-2410: FS, C-56-591-01-EI-2200: FS, C-56-591-01-EI-1810: FS, C-56-591-01-EI-1600: FS, C-56-591-01-EI-2400: FS, C-56-591-01-EI-1200: FS, C-56-591-01-EI-2010: FS, C-56-591-01-EI-2410: FF | C-56-591-01-EI-2050, C-56-591-01-EI-2050, PRECOM-56-59101-1000 | C-56-591-01-EI-2050: FS, C-56-591-01-EI-2050: FF, PRECOM-56-59101-1000: FS | 2025-09-04 11:00 | 2025-09-15 11:00
C-56-591-01-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.2 | Glanding & Termination | C-56-591-01-EI-2040, C-56-591-01-EI-2000, C-56-591-01-EI-2010, C-56-591-01-EI-2030, C-56-591-01-EI-1200, C-56-591-01-EI-1800, C-56-591-01-EI-1000, C-56-591-01-EI-1810, C-56-591-01-EI-2200, C-56-591-01-EI-2410, C-56-591-01-EI-1600, C-56-591-01-EI-2400, C-56 | C-56-591-01-EI-2040: FS, C-56-591-01-EI-2000: FS, C-56-591-01-EI-2010: FS, C-56-591-01-EI-2030: FS, C-56-591-01-EI-1200: FS, C-56-591-01-EI-1800: FS, C-56-591-01-EI-1000: FS, C-56-591-01-EI-1810: FS, C-56-591-01-EI-2200: FS, C-56-591-01-EI-2410: FS, C-56-5 | PRECOM-56-59101-1000, ML1629-E08 | PRECOM-56-59101-1000: FS, ML1629-E08: FS | 2025-09-15 11:00 | 2025-09-20 11:00
C-56-591-01-CA-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.2 | CP Cable Laying | C-56-591-01-EI-2000, HM-PL-0430 | C-56-591-01-EI-2000: FS, HM-PL-0430: FS | C-56-591-01-CA-1010, C-56-591-01-CA-1010, C-56-591-01-CI-2800 | C-56-591-01-CA-1010: FS, C-56-591-01-CA-1010: FF, C-56-591-01-CI-2800: FS 14 | 2025-04-25 07:00 | 2025-04-30 17:00
C-56-591-01-CA-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.2 | Installation of CP Test Post | C-56-591-01-CA-1000, C-56-591-01-CA-1000 | C-56-591-01-CA-1000: FS, C-56-591-01-CA-1000: FF | C-56-591-01-CA-1020, C-56-591-01-CA-1020 | C-56-591-01-CA-1020: FS, C-56-591-01-CA-1020: FF | 2025-05-01 07:00 | 2025-05-03 17:00
C-56-591-01-CA-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.6.2 | Installation of CP S/m | C-56-591-01-CA-1010, C-56-591-01-CA-1010 | C-56-591-01-CA-1010: FS, C-56-591-01-CA-1010: FF | PRECOM-56-59101-1000 | PRECOM-56-59101-1000: FS | 2025-05-05 08:00 | 2025-05-12 15:00
C-56-591-01-TE-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.8.1 | Installation of SDH Cabinet | C-56-591-01-EI-2010, HM-TL-0050, ML1033-B22, HE-TL-0830, HE-TL-0410, HE-TL-0350, HM-TL-0040, HM-ME-1290, HE-TL-0770, HS-CN-0290, HM-EL-0180, HE-TL-0710, HM-ME-1390, HE-TL-0290, HE-TL-0470, HM-ME-2270, HM-ME-2290, HM-EL-610 | C-56-591-01-EI-2010: FS, HM-TL-0050: FS, ML1033-B22: FS, HE-TL-0830: FS, HE-TL-0410: FS, HE-TL-0350: FS, HM-TL-0040: FS, HM-ME-1290: FS, HE-TL-0770: FS, HS-CN-0290: FS, HM-EL-0180: FS, HE-TL-0710: FS, HM-ME-1390: FS, HE-TL-0290: FS, HE-TL-0470: FS, HM-ME-2 | C-56-591-01-TE-1200 | C-56-591-01-TE-1200: FS | 2025-05-28 07:00 | 2025-05-30 17:00
C-56-591-01-TE-1200 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.8.2 | Installation of PIDS/ PLDS System | C-56-591-01-TE-1000 | C-56-591-01-TE-1000: FS | C-56-591-01-TE-1600 | C-56-591-01-TE-1600: FS | 2025-05-31 07:00 | 2025-06-03 17:00
C-56-591-01-TE-1600 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.8.4 | Installation of CCTV System | C-56-591-01-TE-1200 | C-56-591-01-TE-1200: FS | C-56-591-01-TE-1400 | C-56-591-01-TE-1400: FS | 2025-06-04 07:00 | 2025-06-11 17:00
C-56-591-01-TE-1400 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.8.3 | Installation of Telephone System | C-56-591-01-TE-1600 | C-56-591-01-TE-1600: FS | PRECOM-56-59101-1000 | PRECOM-56-59101-1000: FS | 2025-06-12 07:00 | 2025-06-18 17:00
C-52-0102-FENCE-1000 | In Progress | P2543-R01-Oct24..4.3.1.3.5.21.1.21 | Pre-Casting of Fence Foundation (BVS-02 to BVS-01) | C-52-0203-FENCE-1000 | C-52-0203-FENCE-1000: FF | C-52-0102-FENCE-1010, C-52-0304-FENCE-1000 | C-52-0102-FENCE-1010: FS, C-52-0304-FENCE-1000: SS | 2024-09-27 | 2025-01-07 17:00
C-52-HG01-FENCE-1000 | In Progress | P2543-R01-Oct24..4.3.1.3.5.21.1.27 | Pre-Casting of Fence Foundation (BVS-01 to HGCP) | HE-CS-0350 | HE-CS-0350: FS 90 | C-52-0203-FENCE-1000, C-52-HG01-FENCE-1010 | C-52-0203-FENCE-1000: FS, C-52-HG01-FENCE-1010: FS | 2024-08-14 07:00 | 2024-11-29 17:00
C-52-0203-FENCE-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.17 | Pre-Casting of Fence Foundation (BVS-02 to BVS-03) | C-52-HG01-FENCE-1000 | C-52-HG01-FENCE-1000: FS | C-52-0203-FENCE-1010, C-52-0102-FENCE-1000 | C-52-0203-FENCE-1010: FS, C-52-0102-FENCE-1000: FF | 2024-11-30 07:00 | 2025-01-07 17:00
C-52-0304-FENCE-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.16 | Pre-Casting of Fence Foundation (BVS-03 to BVS-04) | C-52-0102-FENCE-1000 | C-52-0102-FENCE-1000: SS | C-52-0405-FENCE-1000, C-52-0304-FENCE-1010 | C-52-0405-FENCE-1000: FS, C-52-0304-FENCE-1010: FS | 2024-11-19 07:00 | 2024-12-25 17:00
C-52-0405-FENCE-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.10 | Pre-Casting of Fence Foundation (BVS-04 to BVS-05) | C-52-0304-FENCE-1000 | C-52-0304-FENCE-1000: FS | C-52-0506-FENCE-1000, C-52-0405-FENCE-1010 | C-52-0506-FENCE-1000: FS, C-52-0405-FENCE-1010: FS | 2024-12-26 07:00 | 2025-01-30 17:00
C-52-0506-FENCE-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.9 | Pre-Casting of Fence Foundation (BVS-05 to BVS-06) | C-52-0405-FENCE-1000 | C-52-0405-FENCE-1000: FS | C-52-06CR-FENCE-1000, C-52-0506-FENCE-1010 | C-52-06CR-FENCE-1000: FS 14, C-52-0506-FENCE-1010: FS | 2025-01-31 07:00 | 2025-03-15 15:00
C-52-06CR-FENCE-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.8 | Pre-Casting of Fence Foundation (BVS-06 to Sweihan-CRS) | C-52-0506-FENCE-1000, CTF-SO1050, HE-CS-0350 | C-52-0506-FENCE-1000: FS 14, CTF-SO1050: FS, HE-CS-0350: FS 28 | C-52-06CR-FENCE-1010, C-52-06CR-FENCE-1010 | C-52-06CR-FENCE-1010: SS 3, C-52-06CR-FENCE-1010: FF | 2025-04-08 13:00 | 2025-05-26 11:00
C-52-0102-FENCE-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.40 | Earth Works for Fence Foundation (BVS-02 to BVS-01) | C-52-0102-FENCE-1000, C-52-0102-PL-CI-6810 | C-52-0102-FENCE-1000: FS, C-52-0102-PL-CI-6810: FS | C-52-0102-FENCE-1020 | C-52-0102-FENCE-1020: SS 3 | 2025-01-31 07:00 | 2025-03-15 15:00
C-52-HG01-FENCE-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.45 | Earth Works for Fence Foundation (BVS-01 to HGCP) | C-52-HG01-FENCE-1000, C-52-HG01-PL-CI-6810 | C-52-HG01-FENCE-1000: FS, C-52-HG01-PL-CI-6810: SS | C-52-HG01-FENCE-1020 | C-52-HG01-FENCE-1020: SS 5 | 2024-11-30 07:00 | 2025-01-07 17:00
C-52-0203-FENCE-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.35 | Earth Works for Fence Foundation (BVS-02 to BVS-03) | C-52-0203-FENCE-1000, C-52-0203-PL-CI-6810 | C-52-0203-FENCE-1000: FS, C-52-0203-PL-CI-6810: FS | C-52-0203-FENCE-1020 | C-52-0203-FENCE-1020: SS 3 | 2025-02-10 07:00 | 2025-03-12 13:00
C-52-0304-FENCE-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.30 | Earth Works for Fence Foundation (BVS-03 to BVS-04) | C-52-0304-FENCE-1000, C-52-0304-PL-CI-6810 | C-52-0304-FENCE-1000: FS, C-52-0304-PL-CI-6810: FS 50 | C-52-0304-FENCE-1020 | C-52-0304-FENCE-1020: SS 5 | 2025-05-16 11:00 | 2025-07-11 11:00
C-52-0405-FENCE-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.24 | Earth Works for Fence Foundation (BVS-04 to BVS-05) | C-52-0405-FENCE-1000, C-52-0405-PL-CI-6400, C-52-0405-PL-CI-6400 | C-52-0405-FENCE-1000: FS, C-52-0405-PL-CI-6400: SS 21, C-52-0405-PL-CI-6400: FF | C-52-0405-FENCE-1020, C-52-0405-FENCE-1020 | C-52-0405-FENCE-1020: SS 5, C-52-0405-FENCE-1020: FF | 2025-05-31 11:00 | 2025-07-26 11:00
C-52-0506-FENCE-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.19 | Earth Works for Fence Foundation (BVS-05 to BVS-06) | C-52-0506-FENCE-1000, C-52-0506-PL-CI-6810 | C-52-0506-FENCE-1000: FS, C-52-0506-PL-CI-6810: SS 3 | C-52-0506-FENCE-1020 | C-52-0506-FENCE-1020: SS 5 | 2025-06-09 15:00 | 2025-08-19 15:00
C-52-06CR-FENCE-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.11 | Earth Works for Fence Foundation (BVS-06 to Sweihan-CRS) | C-52-06CR-FENCE-1000, C-52-06CR-PL-CI-6810, C-52-06CR-FENCE-1000 | C-52-06CR-FENCE-1000: SS 3, C-52-06CR-PL-CI-6810: SS, C-52-06CR-FENCE-1000: FF | C-52-06CR-FENCE-1020 | C-52-06CR-FENCE-1020: SS 5 | 2025-08-09 11:30 | 2025-10-02 11:30
C-52-0102-FENCE-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.40 | Compaction & Testing for Fence Foundation (BVS-02 to BVS-01) | C-52-0102-FENCE-1010 | C-52-0102-FENCE-1010: SS 3 | C-52-0102-FENCE-1030, C-52-0102-FENCE-1030 | C-52-0102-FENCE-1030: SS 4, C-52-0102-FENCE-1030: FF | 2025-02-04 07:00 | 2025-03-20 11:00
C-52-HG01-FENCE-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.45 | Compaction & Testing for Fence Foundation (BVS-01 to HGCP) | C-52-HG01-FENCE-1010 | C-52-HG01-FENCE-1010: SS 5 | C-52-HG01-FENCE-1030 | C-52-HG01-FENCE-1030: SS 7 | 2024-12-09 07:00 | 2025-01-13 17:00
C-52-0203-FENCE-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.35 | Compaction & Testing for Fence Foundation (BVS-02 to BVS-03) | C-52-0203-FENCE-1010 | C-52-0203-FENCE-1010: SS 3 | C-52-0203-FENCE-1030 | C-52-0203-FENCE-1030: SS 3 | 2025-02-13 07:00 | 2025-03-17 09:00
C-52-0304-FENCE-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.30 | Compaction & Testing for Fence Foundation (BVS-03 to BVS-04) | C-52-0304-FENCE-1010 | C-52-0304-FENCE-1010: SS 5 | C-52-0304-FENCE-1030 | C-52-0304-FENCE-1030: SS 3 | 2025-05-22 11:00 | 2025-07-17 11:00
C-52-0405-FENCE-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.24 | Compaction & Testing for Fence Foundation (BVS-04 to BVS-05) | C-52-0405-FENCE-1010, C-52-0405-FENCE-1010 | C-52-0405-FENCE-1010: SS 5, C-52-0405-FENCE-1010: FF | C-52-0405-FENCE-1030, C-52-0405-FENCE-1030 | C-52-0405-FENCE-1030: SS 3, C-52-0405-FENCE-1030: FF | 2025-06-09 11:00 | 2025-08-01 11:00
C-52-0506-FENCE-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.19 | Compaction & Testing for Fence Foundation (BVS-05 to BVS-06) | C-52-0506-FENCE-1010 | C-52-0506-FENCE-1010: SS 5 | C-52-0506-FENCE-1030 | C-52-0506-FENCE-1030: SS 3 | 2025-06-14 15:00 | 2025-08-25 15:00
C-52-06CR-FENCE-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.11 | Compaction & Testing for Fence Foundation (BVS-06 to Sweihan-CRS) | C-52-06CR-FENCE-1010 | C-52-06CR-FENCE-1010: SS 5 | C-52-06CR-FENCE-1030 | C-52-06CR-FENCE-1030: SS 3 | 2025-08-15 11:30 | 2025-10-08 11:30
C-52-0102-FENCE-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.41 | Concrete Works (Blinding) for Fence Foundation (BVS-02 to BVS-01) | C-52-0102-FENCE-1020, C-52-0102-FENCE-1020 | C-52-0102-FENCE-1020: SS 4, C-52-0102-FENCE-1020: FF | C-52-0102-FENCE-1040 | C-52-0102-FENCE-1040: SS 2 | 2025-02-08 07:00 | 2025-03-26 11:00
C-52-HG01-FENCE-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.46 | Concrete Works (Blinding) for Fence Foundation (BVS-01 to HGCP) | C-52-HG01-FENCE-1020, HM-CS-0040 | C-52-HG01-FENCE-1020: SS 7, HM-CS-0040: FF | C-52-HG01-FENCE-1040 | C-52-HG01-FENCE-1040: SS 2 | 2024-12-17 07:00 | 2025-01-21 17:00
C-52-0203-FENCE-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.36 | Concrete Works (Blinding) for Fence Foundation (BVS-02 to BVS-03) | C-52-0203-FENCE-1020 | C-52-0203-FENCE-1020: SS 3 | C-52-0203-FENCE-1040 | C-52-0203-FENCE-1040: SS 2 | 2025-02-17 07:00 | 2025-03-22 09:00
C-52-0304-FENCE-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.31 | Concrete Works (Blinding) for Fence Foundation (BVS-03 to BVS-04) | C-52-0304-FENCE-1020 | C-52-0304-FENCE-1020: SS 3 | C-52-0304-FENCE-1040 | C-52-0304-FENCE-1040: SS 2 | 2025-05-26 11:00 | 2025-07-21 11:00
C-52-0405-FENCE-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.25 | Concrete Works (Blinding) for Fence Foundation (BVS-04 to BVS-05) | C-52-0405-FENCE-1020, C-52-0405-FENCE-1020 | C-52-0405-FENCE-1020: SS 3, C-52-0405-FENCE-1020: FF | C-52-0405-FENCE-1040, C-52-0405-FENCE-1040 | C-52-0405-FENCE-1040: SS 2, C-52-0405-FENCE-1040: FF | 2025-06-12 11:00 | 2025-08-05 11:00
C-52-0506-FENCE-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.18 | Concrete Works (Blinding) for Fence Foundation (BVS-05 to BVS-06) | C-52-0506-FENCE-1020 | C-52-0506-FENCE-1020: SS 3 | C-52-0506-FENCE-1040 | C-52-0506-FENCE-1040: SS 2 | 2025-06-18 15:00 | 2025-08-28 15:00
C-52-06CR-FENCE-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.12 | Concrete Works (Blinding) for Fence Foundation (BVS-06 to Sweihan-CRS) | C-52-06CR-FENCE-1020, HM-CS-0040 | C-52-06CR-FENCE-1020: SS 3, HM-CS-0040: FF | C-52-06CR-FENCE-1040 | C-52-06CR-FENCE-1040: SS 2 | 2025-08-19 11:30 | 2025-10-11 11:30
C-52-0102-FENCE-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.42 | Concrete Protection (Blinding) for Fence Foundation (BVS-02 to BVS-01) | C-52-0102-FENCE-1030 | C-52-0102-FENCE-1030: SS 2 | C-52-0102-FENCE-1050 | C-52-0102-FENCE-1050: FF 3 | 2025-02-11 07:00 | 2025-03-29 13:00
C-52-HG01-FENCE-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.47 | Concrete Protection (Blinding) for Fence Foundation (BVS-01 to HGCP) | C-52-HG01-FENCE-1030 | C-52-HG01-FENCE-1030: SS 2 | C-52-HG01-FENCE-1050 | C-52-HG01-FENCE-1050: FF 7 | 2024-12-19 07:00 | 2025-01-23 17:00
C-52-0203-FENCE-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.37 | Concrete Protection (Blinding) for Fence Foundation (BVS-02 to BVS-03) | C-52-0203-FENCE-1030 | C-52-0203-FENCE-1030: SS 2 | C-52-0203-FENCE-1050 | C-52-0203-FENCE-1050: FF 3 | 2025-02-19 07:00 | 2025-03-24 13:00
C-52-0304-FENCE-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.32 | Concrete Protection (Blinding) for Fence Foundation (BVS-03 to BVS-04) | C-52-0304-FENCE-1030 | C-52-0304-FENCE-1030: SS 2 | C-52-0304-FENCE-1050 | C-52-0304-FENCE-1050: FF 7 | 2025-05-28 11:00 | 2025-07-23 11:00
C-52-0405-FENCE-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.26 | Concrete Protection (Blinding) for Fence Foundation (BVS-04 to BVS-05) | C-52-0405-FENCE-1030, C-52-0405-FENCE-1030 | C-52-0405-FENCE-1030: SS 2, C-52-0405-FENCE-1030: FF | C-52-0405-FENCE-1050 | C-52-0405-FENCE-1050: FF 21 | 2025-06-14 11:00 | 2025-08-07 11:00
C-52-0506-FENCE-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.20 | Concrete Protection (Blinding) for Fence Foundation (BVS-05 to BVS-06) | C-52-0506-FENCE-1030 | C-52-0506-FENCE-1030: SS 2 | C-52-0506-FENCE-1050 | C-52-0506-FENCE-1050: FF 7 | 2025-06-20 15:00 | 2025-08-30 15:00
C-52-06CR-FENCE-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.13 | Concrete Protection (Blinding) for Fence Foundation (BVS-06 to Sweihan-CRS) | C-52-06CR-FENCE-1030 | C-52-06CR-FENCE-1030: SS 2 | C-52-06CR-FENCE-1050 | C-52-06CR-FENCE-1050: FF 3 | 2025-08-21 11:30 | 2025-10-14 11:30
C-52-0102-FENCE-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.43 | Installation of Fence Post (Including Foundation) (BVS-02 to BVS-01) | C-52-0102-FENCE-1040 | C-52-0102-FENCE-1040: FF 3 | C-52-0102-FENCE-1060 | C-52-0102-FENCE-1060: SS 1 | 2025-02-14 07:00 | 2025-04-05 13:00
C-52-HG01-FENCE-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.48 | Installation of Fence Post (Including Foundation) (BVS-01 to HGCP) | C-52-HG01-FENCE-1040 | C-52-HG01-FENCE-1040: FF 7 | C-52-HG01-FENCE-1060 | C-52-HG01-FENCE-1060: SS 1 | 2024-12-27 07:00 | 2025-01-31 17:00
C-52-0203-FENCE-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.38 | Installation of Fence Post (Including Foundation) (BVS-02 to BVS-03) | C-52-0203-FENCE-1040 | C-52-0203-FENCE-1040: FF 3 | C-52-0203-FENCE-1060, C-52-0304-FENCE-1050 | C-52-0203-FENCE-1060: SS 1, C-52-0304-FENCE-1050: FS | 2025-02-25 07:00 | 2025-03-29 13:00
C-52-0304-FENCE-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.33 | Installation of Fence Post (Including Foundation) (BVS-03 to BVS-04) | C-52-0304-FENCE-1040, C-52-0203-FENCE-1050 | C-52-0304-FENCE-1040: FF 7, C-52-0203-FENCE-1050: FS | C-52-0304-FENCE-1060 | C-52-0304-FENCE-1060: SS 1 | 2025-07-04 11:00 | 2025-07-31 11:00
C-52-0405-FENCE-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.28 | Installation of Fence Post (Including Foundation) (BVS-04 to BVS-05) | C-52-0405-FENCE-1040 | C-52-0405-FENCE-1040: FF 21 | C-52-0405-FENCE-1060, C-52-0405-FENCE-1060 | C-52-0405-FENCE-1060: SS 1, C-52-0405-FENCE-1060: FF | 2025-08-04 11:00 | 2025-09-01 11:00
C-52-0506-FENCE-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.22 | Installation of Fence Post (Including Foundation) (BVS-05 to BVS-06) | C-52-0506-FENCE-1040 | C-52-0506-FENCE-1040: FF 7 | C-52-0506-FENCE-1060 | C-52-0506-FENCE-1060: SS 1 | 2025-07-31 15:00 | 2025-09-09 15:00
C-52-06CR-FENCE-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.14 | Installation of Fence Post (Including Foundation) (BVS-06 to Sweihan-CRS) | C-52-06CR-FENCE-1040, HS-CN-0690 | C-52-06CR-FENCE-1040: FF 3, HS-CN-0690: FS | C-52-06CR-FENCE-1060 | C-52-06CR-FENCE-1060: SS 1 | 2025-09-09 11:30 | 2025-10-17 11:30
C-52-0102-FENCE-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.44 | Back Filliing of Fence Post Foundation (BVS-02 to BVS-01) | C-52-0102-FENCE-1050 | C-52-0102-FENCE-1050: SS 1 | C-52-0102-FENCE-1070, ML1090 | C-52-0102-FENCE-1070: SS 2, ML1090: FS | 2025-02-15 07:00 | 2025-04-07 13:00
C-52-HG01-FENCE-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.49 | Back Filliing of Fence Post Foundation (BVS-01 to HGCP) | C-52-HG01-FENCE-1050 | C-52-HG01-FENCE-1050: SS 1 | C-52-HG01-FENCE-1070, ML1080 | C-52-HG01-FENCE-1070: SS 2, ML1080: FS | 2024-12-28 07:00 | 2025-02-01 17:00
C-52-0203-FENCE-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.39 | Back Filliing of Fence Post Foundation (BVS-02 to BVS-03) | C-52-0203-FENCE-1050 | C-52-0203-FENCE-1050: SS 1 | C-52-0203-FENCE-1070 | C-52-0203-FENCE-1070: SS 2 | 2025-02-26 07:00 | 2025-04-03 13:00
C-52-0304-FENCE-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.34 | Back Filliing of Fence Post Foundation (BVS-03 to BVS-04) | C-52-0304-FENCE-1050 | C-52-0304-FENCE-1050: SS 1 | C-52-0304-FENCE-1070 | C-52-0304-FENCE-1070: SS 2 | 2025-07-05 11:00 | 2025-08-01 11:00
C-52-0405-FENCE-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.29 | Back Filliing of Fence Post Foundation (BVS-04 to BVS-05) | C-52-0405-FENCE-1050, C-52-0405-FENCE-1050 | C-52-0405-FENCE-1050: SS 1, C-52-0405-FENCE-1050: FF | C-52-0405-FENCE-1070, C-52-0405-FENCE-1070 | C-52-0405-FENCE-1070: SS 2, C-52-0405-FENCE-1070: FF | 2025-08-05 11:00 | 2025-09-02 11:00
C-52-0506-FENCE-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.23 | Back Filliing of Fence Post Foundation (BVS-05 to BVS-06) | C-52-0506-FENCE-1050 | C-52-0506-FENCE-1050: SS 1 | C-52-0506-FENCE-1070 | C-52-0506-FENCE-1070: SS 2 | 2025-08-01 15:00 | 2025-09-13 15:00
C-52-06CR-FENCE-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.15 | Back Filliing of Fence Post Foundation (BVS-06 to Sweihan-CRS) | C-52-06CR-FENCE-1050 | C-52-06CR-FENCE-1050: SS 1 | C-52-06CR-FENCE-1070 | C-52-06CR-FENCE-1070: SS 2 | 2025-09-10 11:30 | 2025-10-21 11:30
C-52-0102-FENCE-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.43 | Installation of Fence Mesh (BVS-02 to BVS-01) | C-52-0102-FENCE-1060 | C-52-0102-FENCE-1060: SS 2 | PRECOM-52-0201-1000, ML1090 | PRECOM-52-0201-1000: FS, ML1090: FS | 2025-02-18 07:00 | 2025-04-09 13:00
C-52-HG01-FENCE-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.48 | Installation of Fence Mesh (BVS-01 to HGCP) | C-52-HG01-FENCE-1060 | C-52-HG01-FENCE-1060: SS 2 | PRECOM-52-HG01-1000, ML1080 | PRECOM-52-HG01-1000: FS, ML1080: FS | 2024-12-31 07:00 | 2025-02-04 17:00
C-52-0203-FENCE-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.38 | Installation of Fence Mesh (BVS-02 to BVS-03) | C-52-0203-FENCE-1060 | C-52-0203-FENCE-1060: SS 2 | PRECOM-56-59802-1000 | PRECOM-56-59802-1000: FS | 2025-02-28 07:00 | 2025-04-05 13:00
C-52-0304-FENCE-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.33 | Installation of Fence Mesh (BVS-03 to BVS-04) | C-52-0304-FENCE-1060 | C-52-0304-FENCE-1060: SS 2 | PRECOM-52-IDS1-1000 | PRECOM-52-IDS1-1000: FS | 2025-07-08 11:00 | 2025-08-04 11:00
C-52-0405-FENCE-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.28 | Installation of Fence Mesh (BVS-04 to BVS-05) | C-52-0405-FENCE-1060, C-52-0405-FENCE-1060 | C-52-0405-FENCE-1060: SS 2, C-52-0405-FENCE-1060: FF | PRECOM-52-IDS2-1000 | PRECOM-52-IDS2-1000: FS | 2025-08-07 11:00 | 2025-09-04 11:00
C-52-0506-FENCE-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.22 | Installation of Fence Mesh (BVS-05 to BVS-06) | C-52-0506-FENCE-1060 | C-52-0506-FENCE-1060: SS 2 | PRECOM-52-IDS3-1000 | PRECOM-52-IDS3-1000: FF | 2025-08-04 15:00 | 2025-09-12 15:00
C-52-06CR-FENCE-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.5.21.1.14 | Installation of Fence Mesh (BVS-06 to Sweihan-CRS) | C-52-06CR-FENCE-1060 | C-52-06CR-FENCE-1060: SS 2 | PRECOM-52-06CR-1000 | PRECOM-52-06CR-1000: FF 1 | 2025-09-12 11:30 | 2025-10-21 11:30
C-52-IDS1-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 | Site Survey, Preparation & Grading Works | C-56-G-HT-CI-2600, HE-SS-0030, ML1002, CTF-1000, ML1034-B25, HE-CS-0170, HE-CS-0470, CTF-1010 | C-56-G-HT-CI-2600: FS, HE-SS-0030: SS, ML1002: FS, CTF-1000: FS, ML1034-B25: FS, HE-CS-0170: FS, HE-CS-0470: FS, CTF-1010: FS | C-52-IDS1-CI-1010, C-52-IDS2-CI-1000 | C-52-IDS1-CI-1010: FS, C-52-IDS2-CI-1000: FS | 2025-04-28 13:00 | 2025-05-10 11:00
C-52-IDS1-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 | Earth Works for Solar S/m Foundation | C-52-IDS1-CI-1000 | C-52-IDS1-CI-1000: FS | C-52-IDS1-CI-1020, C-52-IDS1-CI-1200 | C-52-IDS1-CI-1020: FS, C-52-IDS1-CI-1200: FS | 2025-05-10 11:00 | 2025-05-24 11:00
C-52-IDS1-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 | Earth Works for Field Instruments & JBs | C-52-IDS1-CI-1010 | C-52-IDS1-CI-1010: FS | C-52-IDS1-CI-1030, C-52-IDS1-CI-1210 | C-52-IDS1-CI-1030: FS, C-52-IDS1-CI-1210: FS | 2025-05-24 11:00 | 2025-06-03 11:00
C-52-IDS1-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 | Earth Works for CCTV Pole, Fence & Gates Foundation | C-52-IDS1-CI-1020 | C-52-IDS1-CI-1020: FS | C-52-IDS1-CI-1220, C-52-IDS1-CI-1800 | C-52-IDS1-CI-1220: FS, C-52-IDS1-CI-1800: FS | 2025-06-03 11:00 | 2025-07-01 11:00
C-52-IDS1-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.2 | Compaction & Testing for Solar S/m Foundation | C-52-IDS1-CI-1010 | C-52-IDS1-CI-1010: FS | C-52-IDS1-CI-1400, C-52-IDS1-CI-1700 | C-52-IDS1-CI-1400: FS, C-52-IDS1-CI-1700: FF 5 | 2025-05-24 11:00 | 2025-06-03 11:00
C-52-IDS1-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.2 | Compaction & Testing for Field Instruments & JBs | C-52-IDS1-CI-1020 | C-52-IDS1-CI-1020: FS | C-52-IDS1-CI-1410, C-52-IDS1-CI-1700 | C-52-IDS1-CI-1410: FS, C-52-IDS1-CI-1700: FF 5 | 2025-06-03 11:00 | 2025-06-11 11:00
C-52-IDS1-CI-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.2 | Compaction & Testing for CCTV Pole, Fence & Gates Foundation | C-52-IDS1-CI-1030 | C-52-IDS1-CI-1030: FS | C-52-IDS1-CI-1420, C-52-IDS1-CI-1700 | C-52-IDS1-CI-1420: FS, C-52-IDS1-CI-1700: FF 5 | 2025-07-01 11:00 | 2025-07-17 11:00
C-52-IDS1-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 | Concrete Works for Solar S/m Foundation | C-52-IDS1-CI-1200, ML1034-B25, HM-CS-0050, HM-CS-0040, HE-CS-0230 | C-52-IDS1-CI-1200: FS, ML1034-B25: FS, HM-CS-0050: FS, HM-CS-0040: FS, HE-CS-0230: FS | C-52-IDS1-CI-1410, C-52-IDS1-EI-1190 | C-52-IDS1-CI-1410: FS, C-52-IDS1-EI-1190: FS | 2025-06-03 11:00 | 2025-07-09 11:00
C-52-IDS1-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 | Concrete Works for Field Instruments & JBs Foundation | C-52-IDS1-CI-1210, C-52-IDS1-CI-1400 | C-52-IDS1-CI-1210: FS, C-52-IDS1-CI-1400: FS | C-52-IDS1-EI-1190 | C-52-IDS1-EI-1190: FS | 2025-07-09 11:00 | 2025-07-25 11:00
C-52-IDS1-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 | Concrete Works for CCTV Pole, Fence & Gates Foundation | C-52-IDS1-CI-1220, ML1034-B25, HM-CS-0050, HM-CS-0040, HE-CS-0230 | C-52-IDS1-CI-1220: FS, ML1034-B25: FS, HM-CS-0050: FS, HM-CS-0040: FS, HE-CS-0230: FS | C-52-IDS1-CI-2220, C-52-IDS1-TE-1590 | C-52-IDS1-CI-2220: SS 21, C-52-IDS1-TE-1590: FS | 2025-07-17 11:00 | 2025-08-19 11:00
C-52-IDS1-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.6 | Electrical & Earthing Cable Trenching | C-52-IDS1-CI-1030, HE-CS-0530 | C-52-IDS1-CI-1030: FS, HE-CS-0530: FS | C-52-IDS1-CI-1810, C-52-IDS1-EI-2000 | C-52-IDS1-CI-1810: FS, C-52-IDS1-EI-2000: FS | 2025-07-01 11:00 | 2025-07-25 11:00
C-52-IDS1-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.6 | Instrument & Telecom Cable Trenching | C-52-IDS1-CI-1800 | C-52-IDS1-CI-1800: FS | C-52-IDS1-EI-2010 | C-52-IDS1-EI-2010: FS | 2025-07-25 11:00 | 2025-08-19 11:00
C-52-IDS1-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.8 | Back Filling for Electrical & Earthing Cable | C-52-IDS1-EI-2000 | C-52-IDS1-EI-2000: FS | PRECOM-52-IDS1-1000 | PRECOM-52-IDS1-1000: FS | 2025-08-08 11:00 | 2025-08-25 11:00
C-52-IDS1-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.8 | Back Filling for Instrument & Telecom Cable | C-52-IDS1-EI-2010, C-52-IDS1-TE-1600 | C-52-IDS1-EI-2010: FS 5, C-52-IDS1-TE-1600: FS | PRECOM-52-IDS1-1000 | PRECOM-52-IDS1-1000: FS | 2025-09-09 11:00 | 2025-09-25 11:00
C-52-IDS1-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.5 | Installation of Fence Post & Mesh Works (Type-3) | C-52-IDS1-CI-1420, C-52-IDS1-CI-1700, HE-CS-0350, HE-CS-0470 | C-52-IDS1-CI-1420: SS 21, C-52-IDS1-CI-1700: FS, HE-CS-0350: FS, HE-CS-0470: FS | C-52-IDS1-CI-2230, PRECOM-52-IDS1-1000 | C-52-IDS1-CI-2230: FS, PRECOM-52-IDS1-1000: FS | 2025-08-11 11:00 | 2025-08-27 11:00
C-52-IDS1-CI-2230 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.5 | Installation of Access Gate | C-52-IDS1-CI-2220 | C-52-IDS1-CI-2220: FS | PRECOM-52-IDS1-1000 | PRECOM-52-IDS1-1000: FS | 2025-08-27 11:00 | 2025-09-03 11:00
C-52-IDS1-TE-1590 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 | Installation of CCTV Poles | C-52-IDS1-CI-1420, HE-TL-0830, HE-TL-0290, HE-TL-0710, HE-TL-0470, HE-TL-0350, HM-ME-1290, HE-TL-0770, HE-TL-0410, HM-TL-0040, HM-ME-2270 | C-52-IDS1-CI-1420: FS, HE-TL-0830: FS, HE-TL-0290: FS, HE-TL-0710: FS, HE-TL-0470: FS, HE-TL-0350: FS, HM-ME-1290: FS, HE-TL-0770: FS, HE-TL-0410: FS, HM-TL-0040: FS, HM-ME-2270: FS | C-52-IDS1-TE-1600 | C-52-IDS1-TE-1600: FS | 2025-08-19 11:00 | 2025-08-25 11:00
C-52-IDS1-EI-1190 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 | Installation of Solar S/m Structurals | C-52-IDS1-CI-1400, C-52-IDS1-CI-1410 | C-52-IDS1-CI-1400: FS, C-52-IDS1-CI-1410: FS | C-52-IDS1-CI-2600, C-52-IDS1-EI-1200 | C-52-IDS1-CI-2600: FS, C-52-IDS1-EI-1200: FS | 2025-07-25 11:00 | 2025-08-06 11:00
C-52-IDS1-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.7 | Paving of Interlock tiles & Kerb Stone Embankment | C-52-IDS1-EI-1190, HE-CS-0290, ML1059-B28 | C-52-IDS1-EI-1190: FS, HE-CS-0290: FS, ML1059-B28: FS | PRECOM-52-IDS1-1000 | PRECOM-52-IDS1-1000: FS | 2025-08-06 11:00 | 2025-09-11 11:00
C-52-IDS1-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 | Electrical & Earthing Cable Laying | C-52-IDS1-CI-1800, HS-CN-0240 | C-52-IDS1-CI-1800: FS, HS-CN-0240: FS | C-52-IDS1-CI-2800, C-52-IDS2-EI-2000 | C-52-IDS1-CI-2800: FS, C-52-IDS2-EI-2000: FS | 2025-07-25 11:00 | 2025-08-08 11:00
C-52-IDS1-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 | Instrument Cable Laying | C-52-IDS1-CI-1810 | C-52-IDS1-CI-1810: FS | C-52-IDS1-CI-2810, C-52-IDS2-EI-2010, PRECOM-52-IDS1-1000, C-52-IDS2-CI-2810, PRECOM-52-IDS2-1000, C-52-IDS3-CI-2810, PRECOM-52-IDS3-1000 | C-52-IDS1-CI-2810: FS 5, C-52-IDS2-EI-2010: FS, PRECOM-52-IDS1-1000: FS, C-52-IDS2-CI-2810: FS, PRECOM-52-IDS2-1000: FS, C-52-IDS3-CI-2810: FS, PRECOM-52-IDS3-1000: FS | 2025-08-19 11:00 | 2025-09-02 11:00
C-52-IDS1-EI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-IDS1-EI-1190 | C-52-IDS1-EI-1190: FS | C-52-IDS1-EI-1810, C-52-IDS2-EI-1200 | C-52-IDS1-EI-1810: FS, C-52-IDS2-EI-1200: FS | 2025-08-06 11:00 | 2025-08-22 11:00
C-52-IDS1-EI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 | Installation of Lighting & Instrument JB's | C-52-IDS1-EI-1200 | C-52-IDS1-EI-1200: FS | C-52-IDS1-EI-2050 | C-52-IDS1-EI-2050: FS | 2025-08-22 11:00 | 2025-09-01 11:00
C-52-IDS1-TE-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 | CCTV Installation | C-52-IDS1-TE-1590 | C-52-IDS1-TE-1590: FS | C-52-IDS2-TE-1600, C-52-IDS1-CI-2810, PRECOM-52-IDS1-1000, C-52-IDS2-CI-2810, PRECOM-52-IDS2-1000, C-52-IDS3-CI-2810, PRECOM-52-IDS3-1000 | C-52-IDS2-TE-1600: FS, C-52-IDS1-CI-2810: FS, PRECOM-52-IDS1-1000: FS, C-52-IDS2-CI-2810: FS, PRECOM-52-IDS2-1000: FS, C-52-IDS3-CI-2810: FS, PRECOM-52-IDS3-1000: FS | 2025-08-25 11:00 | 2025-09-03 11:00
C-52-IDS1-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 | Glanding & Termination | C-52-IDS1-EI-1810 | C-52-IDS1-EI-1810: FS | PRECOM-52-IDS1-1000 | PRECOM-52-IDS1-1000: FS | 2025-09-01 11:00 | 2025-09-08 11:00
C-52-PL-838-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.1 | Site Survey, Preparation & Grading Works | HE-SS-0030, ML1002, HE-CS-0170, HE-CS-0470, CTF-1000, CTF-1010, C-PER-1650 | HE-SS-0030: SS, ML1002: FS, HE-CS-0170: FS, HE-CS-0470: FS, CTF-1000: FS, CTF-1010: FS, C-PER-1650: FS 30 | C-52-PL-838-CI-1010, C-52-PL-838-CI-1050 | C-52-PL-838-CI-1010: FS, C-52-PL-838-CI-1050: FS | 2025-01-16 07:00 | 2025-01-31 17:00
C-52-PL-838-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.1 | Earth Works for Equipment Foundations | C-52-PL-838-CI-1000 | C-52-PL-838-CI-1000: FS | C-52-PL-838-CI-1020, C-52-PL-838-CI-1200 | C-52-PL-838-CI-1020: FS, C-52-PL-838-CI-1200: FS | 2025-02-01 07:00 | 2025-02-25 17:00
C-52-PL-838-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.1 | Earth Works for Pipe Support Foundations | C-52-PL-838-CI-1010 | C-52-PL-838-CI-1010: FS | C-52-PL-838-CI-1210 | C-52-PL-838-CI-1210: FS | 2025-02-26 07:00 | 2025-03-28 09:00
C-52-PL-838-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.1 | Earth Works for Field Instrument, JBs & Light Pole Foundations | C-52-PL-838-CI-1050 | C-52-PL-838-CI-1050: FS | C-52-PL-838-CI-1040, C-52-PL-838-CI-1220 | C-52-PL-838-CI-1040: FS, C-52-PL-838-CI-1220: FS | 2025-03-07 07:00 | 2025-03-28 09:00
C-52-PL-838-CI-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.1 | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-PL-838-CI-1030 | C-52-PL-838-CI-1030: FS | C-52-PL-838-CI-1230 | C-52-PL-838-CI-1230: FS | 2025-03-28 09:00 | 2025-04-17 13:00
C-52-598-06-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.9 | Paving of Interlock tiles & Kerb Stone Embankment | C-52-598-06-CI-2230, HE-CS-0290, ML1059-B28 | C-52-598-06-CI-2230: FS, HE-CS-0290: FS, ML1059-B28: FS | C-52-598-06-CI-2610, C-52-598-06-CI-2610, PRECOM-52-59806-1000 | C-52-598-06-CI-2610: FF 7, C-52-598-06-CI-2610: SS 7, PRECOM-52-59806-1000: FS | 2025-07-14 11:00 | 2025-08-15 11:00
C-52-598-06-CI-2610 | Not Started | P2543-R01-Oct24..4.3.1.3.9.21.1.9 | Rip-Rap Protection Laying | C-52-598-06-CI-2600, C-52-598-06-CI-2600 | C-52-598-06-CI-2600: FF 7, C-52-598-06-CI-2600: SS 7 | PRECOM-52-59806-1000 | PRECOM-52-59806-1000: FS | 2025-07-22 11:00 | 2025-08-23 11:00
C-52-598-02-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.9 | Paving of Interlock tiles & Kerb Stone Embankment | C-52-598-02-CI-2230, HE-CS-0290, ML1059-B28 | C-52-598-02-CI-2230: FS, HE-CS-0290: FS, ML1059-B28: FS | C-52-598-02-CI-2610, PRECOM-56-59802-1000 | C-52-598-02-CI-2610: FS, PRECOM-56-59802-1000: FS | 2025-06-26 11:00 | 2025-07-30 11:00
C-52-598-02-CI-2610 | Not Started | P2543-R01-Oct24..4.3.1.3.13.21.1.9 | Rip-Rap Protection Laying | C-52-598-02-CI-2600 | C-52-598-02-CI-2600: FS | PRECOM-56-59802-1000 | PRECOM-56-59802-1000: FS | 2025-07-30 11:00 | 2025-09-01 11:00
C-52-598-01-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.9 | Paving of Interlock tiles & Kerb Stone Embankment | C-52-598-01-CI-2230, ML1059-B28, HE-CS-0290 | C-52-598-01-CI-2230: FS, ML1059-B28: FS, HE-CS-0290: FS | C-52-598-01-CI-2610, C-52-598-01-CI-2610, PRECOM-56-59801-1000 | C-52-598-01-CI-2610: FF 14, C-52-598-01-CI-2610: SS 14, PRECOM-56-59801-1000: FS | 2025-07-08 11:00 | 2025-08-09 11:00
C-52-598-01-CI-2610 | Not Started | P2543-R01-Oct24..4.3.1.3.14.21.1.9 | Rip-Rap Protection Laying | C-52-598-01-CI-2600, C-52-598-01-CI-2600 | C-52-598-01-CI-2600: FF 14, C-52-598-01-CI-2600: SS 14 | PRECOM-56-59801-1000 | PRECOM-56-59801-1000: FS | 2025-07-24 11:00 | 2025-08-26 11:00
C-52-598-03-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.7 | Paving of Interlock tiles & Kerb Stone Embankment | C-52-598-03-CI-2230, HE-CS-0290, ML1059-B28 | C-52-598-03-CI-2230: FS, HE-CS-0290: FS, ML1059-B28: FS | C-52-598-03-CI-2610, PRECOM-56-59803-1000 | C-52-598-03-CI-2610: FS, PRECOM-56-59803-1000: FS | 2025-07-22 11:00 | 2025-08-23 11:00
C-52-598-03-CI-2610 | Not Started | P2543-R01-Oct24..4.3.1.3.12.21.1.7 | Rip-Rap Protection Laying | C-52-598-03-CI-2600 | C-52-598-03-CI-2600: FS | PRECOM-56-59803-1000 | PRECOM-56-59803-1000: FS | 2025-08-23 11:00 | 2025-09-26 11:00
C-52-598-04-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.8 | Paving of Interlock tiles & Kerb Stone Embankment | C-52-598-04-CI-2230 | C-52-598-04-CI-2230: FS | C-52-598-04-CI-2610, PRECOM-56-59804-1000 | C-52-598-04-CI-2610: FS, PRECOM-56-59804-1000: FS | 2025-07-12 11:00 | 2025-08-14 11:00
C-52-598-04-CI-2610 | Not Started | P2543-R01-Oct24..4.3.1.3.11.21.1.8 | Rip-Rap Protection Laying | C-52-598-04-CI-2600 | C-52-598-04-CI-2600: FS | PRECOM-56-59804-1000 | PRECOM-56-59804-1000: FS | 2025-08-14 11:00 | 2025-09-17 11:00
C-52-598-05-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.9 | Paving of Interlock tiles & Kerb Stone Embankment | C-52-598-05-CI-2230, ML1059-B28, HE-CS-0290 | C-52-598-05-CI-2230: FS, ML1059-B28: FS, HE-CS-0290: FS | C-52-598-05-CI-2610, PRECOM-56-59805-1000 | C-52-598-05-CI-2610: FS, PRECOM-56-59805-1000: FS | 2025-06-20 11:00 | 2025-07-16 11:00
C-52-598-05-CI-2610 | Not Started | P2543-R01-Oct24..4.3.1.3.10.21.1.9 | Rip-Rap Protection Laying | C-52-598-05-CI-2600 | C-52-598-05-CI-2600: FS | PRECOM-56-59805-1000 | PRECOM-56-59805-1000: FS | 2025-07-16 11:00 | 2025-08-09 11:00
C-56-591-01-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.15 | Paving of Interlock tiles & Kerb Stone Embankment | C-56-591-01-CI-2230, ML1059-B28, HE-CS-0290 | C-56-591-01-CI-2230: SS 7, ML1059-B28: FS, HE-CS-0290: FS | C-56-591-01-CI-2610, C-56-591-01-CI-2610, PRECOM-56-59101-1000 | C-56-591-01-CI-2610: FF 5, C-56-591-01-CI-2610: SS 5, PRECOM-56-59101-1000: FS | 2025-07-19 11:00 | 2025-08-19 11:00
C-56-591-01-CI-2610 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.15 | Rip-Rap Protection Laying | C-56-591-01-CI-2600, C-56-591-01-CI-2600 | C-56-591-01-CI-2600: FF 5, C-56-591-01-CI-2600: SS 5 | PRECOM-56-59101-1000 | PRECOM-56-59101-1000: FS | 2025-07-25 11:00 | 2025-08-25 11:00
C-52-PL-838-CI-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.1 | Earth Works for Thrust Anchor Block | C-52-PL-838-CI-1000 | C-52-PL-838-CI-1000: FS | C-52-PL-838-CI-1030, C-52-PL-838-CI-1240, C-52-PL-838-CI-1800 | C-52-PL-838-CI-1030: FS, C-52-PL-838-CI-1240: FS, C-52-PL-838-CI-1800: FS | 2025-02-01 07:00 | 2025-03-06 13:00
C-52-PL-838-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.2 | Compaction & Testing for Equipment Foundations | C-52-PL-838-CI-1010 | C-52-PL-838-CI-1010: FS | C-52-PL-838-CI-1400 | C-52-PL-838-CI-1400: FS | 2025-02-26 07:00 | 2025-03-08 11:00
C-52-PL-838-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.2 | Compaction & Testing for Pipe Support Foundations | C-52-PL-838-CI-1020 | C-52-PL-838-CI-1020: FS | C-52-PL-838-CI-1600 | C-52-PL-838-CI-1600: FS | 2025-03-28 09:00 | 2025-04-10 13:00
C-52-PL-838-CI-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.2 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | C-52-PL-838-CI-1030 | C-52-PL-838-CI-1030: FS | C-52-PL-838-CI-1410 | C-52-PL-838-CI-1410: FS | 2025-03-28 09:00 | 2025-04-07 13:00
C-52-PL-838-CI-1230 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.2 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-52-PL-838-CI-1040 | C-52-PL-838-CI-1040: FS | C-52-PL-838-CI-1420 | C-52-PL-838-CI-1420: FS | 2025-04-17 13:00 | 2025-04-23 13:00
C-52-PL-838-CI-1240 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.2 | Compaction & Testing for Thrust Anchor Block | C-52-PL-838-CI-1050 | C-52-PL-838-CI-1050: FS | C-52-PL-838-CI-1510 | C-52-PL-838-CI-1510: FS | 2025-03-07 07:00 | 2025-03-18 13:00
C-52-PL-838-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.3 | Concrete Works for Equipment Foundations | C-52-PL-838-CI-1200, HE-CS-0230, HE-CS-0650, HE-CS-1070, HE-CS-1190, HM-CS-0040, HE-CS-1310 | C-52-PL-838-CI-1200: FS, HE-CS-0230: FS, HE-CS-0650: FS, HE-CS-1070: FS, HE-CS-1190: FS, HM-CS-0040: FS, HE-CS-1310: FF | C-52-PL-838-CI-1600, C-52-PL-838-ME-1000, C-52-PL-838-CI-1700, ML1739-E19 | C-52-PL-838-CI-1600: FS, C-52-PL-838-ME-1000: FS, C-52-PL-838-CI-1700: FF 5, ML1739-E19: FS | 2025-03-08 11:00 | 2025-04-10 13:00
C-52-PL-838-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.3 | Concrete Works for Pipe Support Foundations | C-52-PL-838-CI-1210, C-52-PL-838-CI-1400 | C-52-PL-838-CI-1210: FS, C-52-PL-838-CI-1400: FS | C-52-PL-838-CI-1410, C-52-PL-838-CI-2000, C-52-PL-838-CI-1700, ML1739-E19 | C-52-PL-838-CI-1410: FS, C-52-PL-838-CI-2000: FS, C-52-PL-838-CI-1700: FF 5, ML1739-E19: FS | 2025-04-10 13:00 | 2025-05-22 11:00
C-52-PL-838-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.3 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-52-PL-838-CI-1220, C-52-PL-838-CI-1600 | C-52-PL-838-CI-1220: FS, C-52-PL-838-CI-1600: FS | C-52-PL-838-CI-1420, C-52-PL-838-EI-2210, C-52-PL-838-CI-1700, ML1739-E19 | C-52-PL-838-CI-1420: FS, C-52-PL-838-EI-2210: FS, C-52-PL-838-CI-1700: FF 5, ML1739-E19: FS | 2025-05-22 11:00 | 2025-06-10 11:00
C-52-PL-838-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.3 | Concrete Works for Access Platforms & Misc. Structural Foundations | C-52-PL-838-CI-1230, C-52-PL-838-CI-1410 | C-52-PL-838-CI-1230: FS, C-52-PL-838-CI-1410: FS | C-52-PL-838-CI-3000, C-52-PL-838-CI-1700, ML1739-E19 | C-52-PL-838-CI-3000: FS, C-52-PL-838-CI-1700: FF 5, ML1739-E19: FS | 2025-06-10 11:00 | 2025-07-05 11:00
C-52-PL-838-CI-1510 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.5 | Concrete Works for Thrust Anchor Block | C-52-PL-838-CI-1240, HM-PL-1550, HM-CS-0110 | C-52-PL-838-CI-1240: FS, HM-PL-1550: FS, HM-CS-0110: FS | PRECOM-52-PL-1000 | PRECOM-52-PL-1000: FS | 2025-03-27 07:00 | 2025-08-22 13:00
C-52-PL-838-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.7 | Electrical & Earthing Cable Trenching | C-52-PL-838-CI-1050, C-52-PR-839-CI-1800, HE-CS-0530 | C-52-PL-838-CI-1050: FS, C-52-PR-839-CI-1800: FS, HE-CS-0530: FS | C-52-PL-838-CI-1810 | C-52-PL-838-CI-1810: FS | 2025-03-22 09:00 | 2025-04-29 13:00
C-52-PL-838-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.9 | Instrument & Telecom Cable Trenching | C-52-PL-838-CI-1800, HE-CS-0530 | C-52-PL-838-CI-1800: FS, HE-CS-0530: FS | C-52-PL-838-EI-2010 | C-52-PL-838-EI-2010: FS | 2025-04-29 13:00 | 2025-06-02 11:00
C-52-PL-838-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.11 | Back Filling for Electrical & Earthing Cable | C-52-PL-838-EI-2000, C-52-PL-838-CA-1000 | C-52-PL-838-EI-2000: FF 5, C-52-PL-838-CA-1000: FF 2 | C-52-PL-838-CI-2810, PRECOM-52-PL-1000 | C-52-PL-838-CI-2810: FF 5, PRECOM-52-PL-1000: FS | 2025-08-01 11:00 | 2025-08-26 11:00
C-52-PL-838-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.11 | Back Filling for Instrument & Telecom Cable | C-52-PL-838-CI-2800, C-52-PL-838-EI-2010, C-52-PL-838-TE-1410 | C-52-PL-838-CI-2800: FF 5, C-52-PL-838-EI-2010: FF 2, C-52-PL-838-TE-1410: FF 2 | C-52-PL-838-CI-2600, PRECOM-52-PL-1000 | C-52-PL-838-CI-2600: FF 5, PRECOM-52-PL-1000: FS | 2025-08-19 11:00 | 2025-09-13 11:00
C-52-PL-838-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.10 | Paving of Interlock tiles & Kerb Stone Embankment | C-52-PL-838-CI-2810, C-52-PL-838-CI-1700, ML1059-B28, HE-CS-0290 | C-52-PL-838-CI-2810: FF 5, C-52-PL-838-CI-1700: FS, ML1059-B28: FS, HE-CS-0290: FS | PRECOM-52-PL-1000 | PRECOM-52-PL-1000: FS | 2025-08-16 11:00 | 2025-09-19 11:00
C-52-PL-838-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.6 | Pre-Fabrication & Installation of Pipe Supports | C-52-PL-838-CI-1600, HS-CN-0690, HE-CS-1490, HM-CS-0110, HE-CS-1430 | C-52-PL-838-CI-1600: FS, HS-CN-0690: FS, HE-CS-1490: FS, HM-CS-0110: FS, HE-CS-1430: FS | C-52-PL-838-PI-1200 | C-52-PL-838-PI-1200: FS | 2025-05-22 11:00 | 2025-07-17 11:00
C-52-PL-838-EI-2210 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.6.2 | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-PL-838-CI-1410, C-52-PL-838-PI-1800 | C-52-PL-838-CI-1410: FS, C-52-PL-838-PI-1800: FF | C-52-PL-838-EI-1800, C-52-PL-838-EI-2200, C-52-PL-838-EI-1600 | C-52-PL-838-EI-1800: FS, C-52-PL-838-EI-2200: FS, C-52-PL-838-EI-1600: FS 25 | 2025-08-07 11:00 | 2025-09-01 11:00
C-52-PL-838-CI-3000 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.8 | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-PL-838-CI-1420, HS-CN-0690, HM-CS-0110 | C-52-PL-838-CI-1420: FS, HS-CN-0690: FS, HM-CS-0110: FS | C-52-PL-838-CI-3010, PRECOM-52-PL-1000 | C-52-PL-838-CI-3010: FS, PRECOM-52-PL-1000: FS | 2025-07-05 11:00 | 2025-08-07 11:00
C-52-PL-838-CI-3010 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.8 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-PL-838-CI-3000 | C-52-PL-838-CI-3000: FS | PRECOM-52-PL-1000 | PRECOM-52-PL-1000: FS | 2025-08-07 11:00 | 2025-09-01 11:00
C-52-PL-838-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.3.1 | Installation of Pig Launcher (838-V-602) 52" | C-52-PL-838-CI-1400, C-52-PR-839-ME-1100, HM-ME-0480, ML1519-D04, ML1015-B08 | C-52-PL-838-CI-1400: FS, C-52-PR-839-ME-1100: FS 1, HM-ME-0480: FS, ML1519-D04: FS, ML1015-B08: FS | PRECOM-52-PL-1000, C-52-PL-838-ME-1200 | PRECOM-52-PL-1000: FS, C-52-PL-838-ME-1200: FS | 2025-04-10 13:00 | 2025-04-19 13:00
C-52-PL-838-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.4.1 | Piping Pre-Fabrication | C-56-PR-838-PI-1000, ML1002, HM-PL-0740, ML1219-B19, HE-PI-1300, HE-PI-1240, HS-CN-0190, HE-PR-0290, HM-PL-0640, HM-PL-0220, HM-PL-0630, HM-PI-0040, ML1179-B11, HM-PL-1510, HM-PL-1570 | C-56-PR-838-PI-1000: SS 21, ML1002: FS, HM-PL-0740: FS, ML1219-B19: FS, HE-PI-1300: FS, HE-PI-1240: FS, HS-CN-0190: FS, HE-PR-0290: FS, HM-PL-0640: FS, HM-PL-0220: FS, HM-PL-0630: FS, HM-PI-0040: FS, ML1179-B11: FS, HM-PL-1510: FS, HM-PL-1570: FS | C-52-PL-838-PI-1200 | C-52-PL-838-PI-1200: FS 14 | 2025-03-28 07:00 | 2025-05-15 09:00
C-52-PL-838-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.4.3 | Piping Erection | C-52-PL-838-PI-1000, C-52-PL-838-CI-2000, ML1002, HM-PL-0740, ML1219-B19, HE-PI-1300, HE-PI-1240, HS-CN-0190, HE-PR-0290, HM-PL-0640, HM-PL-0220, HM-PL-0630, HM-PI-0040, ML1179-B11, HM-PL-1510, HM-PL-1570 | C-52-PL-838-PI-1000: FS 14, C-52-PL-838-CI-2000: FS, ML1002: FS, HM-PL-0740: FS, ML1219-B19: FS, HE-PI-1300: FS, HE-PI-1240: FS, HS-CN-0190: FS, HE-PR-0290: FS, HM-PL-0640: FS, HM-PL-0220: FS, HM-PL-0630: FS, HM-PI-0040: FS, ML1179-B11: FS, HM-PL-1510: FS, | C-52-PL-838-PI-1400, ML1749-E20, C-52-PL-838-PL-1000 | C-52-PL-838-PI-1400: SS 2, ML1749-E20: FS, C-52-PL-838-PL-1000: FS 5 | 2025-07-17 11:00 | 2025-08-14 11:00
C-52-PL-838-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.4.3 | Field Joint Welding | C-52-PL-838-PI-1200 | C-52-PL-838-PI-1200: SS 2 | C-52-PL-838-PI-1410 | C-52-PL-838-PI-1410: SS 3 | 2025-07-19 11:00 | 2025-08-16 11:00
C-52-PL-838-PI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.4.2 | NDT & Coating for Field Joint Weld | C-52-PL-838-PI-1400 | C-52-PL-838-PI-1400: SS 3 | C-52-PL-838-PI-1600 | C-52-PL-838-PI-1600: FS | 2025-07-23 11:00 | 2025-08-20 11:00
C-52-PL-838-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.4.3 | Hydrotesting | C-52-PL-838-PI-1410 | C-52-PL-838-PI-1410: FS | C-52-PL-838-PI-1800 | C-52-PL-838-PI-1800: FS | 2025-08-20 11:00 | 2025-08-26 11:00
C-52-PL-838-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.4.3 | Installation of Valves/MOV/ROV | C-52-PL-838-PI-1600, HM-ME-0680, HM-ME-2240 | C-52-PL-838-PI-1600: FS, HM-ME-0680: FS, HM-ME-2240: FS | C-52-PL-838-PI-2000, C-52-PL-838-EI-2210 | C-52-PL-838-PI-2000: SS 4, C-52-PL-838-EI-2210: FF | 2025-08-26 11:00 | 2025-09-01 11:00
C-52-PL-838-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.4.3 | Final Bolt Torquing/ Re-Instatement | C-52-PL-838-PI-1800, C-52-PL-838-ME-1200 | C-52-PL-838-PI-1800: SS 4, C-52-PL-838-ME-1200: FS | PRECOM-52-PL-1000 | PRECOM-52-PL-1000: FS | 2025-08-30 11:00 | 2025-09-03 11:00
C-52-PL-838-PL-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.5.1 | Installation of Isolation Joint | C-52-PL-838-PI-1200 | C-52-PL-838-PI-1200: FS 5 | C-52-PL-838-PL-1010 | C-52-PL-838-PL-1010: FS | 2025-08-20 11:00 | 2025-08-22 11:00
C-52-PL-838-PL-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.5.1 | Field Joint Welding (Piping/Pipeline Section including IJ) | C-52-PL-838-PL-1000 | C-52-PL-838-PL-1000: FS | C-52-PL-838-PL-1020 | C-52-PL-838-PL-1020: SS 1 | 2025-08-22 11:00 | 2025-08-28 11:00
C-52-PL-838-PL-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.5.1 | NDT for Weld Joint | C-52-PL-838-PL-1010 | C-52-PL-838-PL-1010: SS 1 | C-52-PL-838-PL-1030 | C-52-PL-838-PL-1030: SS 1 | 2025-08-23 11:00 | 2025-08-29 11:00
C-52-PL-838-PL-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.5.1 | Ext. Coating for Weld Joint | C-52-PL-838-PL-1020 | C-52-PL-838-PL-1020: SS 1 | PRECOM-52-PL-1000, CCM-PM4520, CCM-PM4530, A3980, CCM-PM4540 | PRECOM-52-PL-1000: FS, CCM-PM4520: FS, CCM-PM4530: FS, A3980: FS, CCM-PM4540: FS | 2025-08-25 11:00 | 2025-08-30 11:00
C-52-PL-838-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.6.1 | Electrical & Earthing Cable Laying | C-56-PR-838-EI-2000, HE-EL-1010, HE-IC-0590, HE-IC-1550, HE-IC-0490, HE-IC-0530, HM-IC-0040, HE-EL-1670, HE-IC-0710, HE-IC-0770, HM-EL-0380, HE-EL-0640, HM-EL-0280, HE-IC-1430, HM-EL-0520, HE-EL-1730, HE-EL-1790, HM-ME-1690, ML1032-B21, HM-EL-0080, HE-IC-2 | C-56-PR-838-EI-2000: FS 30, HE-EL-1010: FS, HE-IC-0590: FS, HE-IC-1550: FF, HE-IC-0490: FS, HE-IC-0530: FS, HM-IC-0040: FF, HE-EL-1670: FS, HE-IC-0710: FS, HE-IC-0770: FS, HM-EL-0380: FS, HE-EL-0640: FS, HM-EL-0280: FS, HE-IC-1430: FS, HM-EL-0520: FS, HE-E | C-52-PL-838-EI-1400, C-52-PL-838-EI-2010, C-52-PL-838-EI-1800, C-52-PL-838-EI-1810, C-52-PL-838-EI-2050, C-52-PL-838-CA-1000, C-52-PL-838-CI-2800 | C-52-PL-838-EI-1400: FF, C-52-PL-838-EI-2010: FS, C-52-PL-838-EI-1800: FS, C-52-PL-838-EI-1810: FS, C-52-PL-838-EI-2050: FS, C-52-PL-838-CA-1000: FS, C-52-PL-838-CI-2800: FF 5 | 2025-07-23 11:00 | 2025-08-16 11:00
C-52-PL-838-EI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.6.1 | Deep Earth Well Drilling | C-52-PL-838-EI-2000, HE-EL-1010, HE-IC-0590, HE-IC-1550, HE-IC-0490, HE-IC-0530, HM-IC-0040, HE-EL-1670, HE-IC-0710, HE-IC-0770, HM-EL-0380, HE-EL-0640, HM-EL-0280, HE-IC-1430, HM-ME-1590, HM-EL-0520, HE-EL-1730, HE-EL-1790, HM-ME-1690, ML1032-B21, HM-EL-0 | C-52-PL-838-EI-2000: FF, HE-EL-1010: FS, HE-IC-0590: FS, HE-IC-1550: FF, HE-IC-0490: FS, HE-IC-0530: FS, HM-IC-0040: FF, HE-EL-1670: FS, HE-IC-0710: FS, HE-IC-0770: FS, HM-EL-0380: FS, HE-EL-0640: FS, HM-EL-0280: FS, HE-IC-1430: FS, HM-ME-1590: FF 10, HM-E | C-52-PL-838-EI-2050 | C-52-PL-838-EI-2050: FS | 2025-08-09 11:00 | 2025-08-16 11:00
C-52-PL-838-EI-2020 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.6.3 | Installation of Cable Trays | C-52-PL-838-EI-2010 | C-52-PL-838-EI-2010: FS | C-52-PL-838-EI-2030, C-52-PL-838-EI-1800, C-52-PL-838-EI-1810, C-52-PL-838-EI-2200 | C-52-PL-838-EI-2030: SS, C-52-PL-838-EI-1800: FS, C-52-PL-838-EI-1810: FS, C-52-PL-838-EI-2200: FF 1 | 2025-09-11 11:00 | 2025-09-18 11:00
C-52-PL-838-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.6.3 | Instrument Cable Laying | C-52-PL-838-EI-2000, C-52-PL-838-CI-1810, HE-IC-0950, HM-EL-0080, HE-IC-1010, HE-EL-0590, HE-EL-1610, HE-EL-0470, HE-EL-0830, HM-EL-0520, HE-IC-0830, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250 | C-52-PL-838-EI-2000: FS, C-52-PL-838-CI-1810: FS, HE-IC-0950: FS, HM-EL-0080: FS, HE-IC-1010: FS, HE-EL-0590: FS, HE-EL-1610: FS, HE-EL-0470: FS, HE-EL-0830: FS, HM-EL-0520: FS, HE-IC-0830: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS | C-52-PL-838-EI-2020, C-52-PL-838-EI-2200, C-52-PL-838-EI-2040, C-52-PL-838-TE-1410, C-52-PL-838-CI-2810 | C-52-PL-838-EI-2020: FS, C-52-PL-838-EI-2200: FF 2, C-52-PL-838-EI-2040: FS, C-52-PL-838-TE-1410: SS 7, C-52-PL-838-CI-2810: FF 2 | 2025-08-16 11:00 | 2025-09-11 11:00
C-52-PL-838-EI-2030 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.6.3 | Instrument Tubing Works | C-52-PL-838-EI-2020 | C-52-PL-838-EI-2020: SS | C-52-PL-838-EI-2200, C-52-PL-838-EI-2040 | C-52-PL-838-EI-2200: FF 1, C-52-PL-838-EI-2040: FS | 2025-09-11 11:00 | 2025-09-18 11:00
C-52-PL-838-EI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.6.1 | Installation of Light Pole, Lighting & Fixtures | C-52-PL-838-EI-2000, C-52-PL-838-EI-2020, C-52-PL-838-EI-2210 | C-52-PL-838-EI-2000: FS, C-52-PL-838-EI-2020: FS, C-52-PL-838-EI-2210: FS | C-52-PL-838-EI-2050 | C-52-PL-838-EI-2050: FF 3 | 2025-09-18 11:00 | 2025-10-02 11:00
C-52-PL-838-EI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.6.1 | Installation of JB's | C-52-PL-838-EI-2020, C-52-PL-838-EI-2000 | C-52-PL-838-EI-2020: FS, C-52-PL-838-EI-2000: FS | C-52-PL-838-EI-2050 | C-52-PL-838-EI-2050: FS | 2025-09-18 11:00 | 2025-09-24 11:00
C-52-PL-838-EI-2200 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.6.2 | Installation of Field Instruments (Including Pig Signaller) | C-52-PL-838-EI-2210, C-52-PL-838-EI-2010, C-52-PL-838-EI-2020, C-52-PL-838-EI-2030 | C-52-PL-838-EI-2210: FS, C-52-PL-838-EI-2010: FF 2, C-52-PL-838-EI-2020: FF 1, C-52-PL-838-EI-2030: FF 1 | C-52-PL-838-EI-2410, C-52-PL-838-EI-2040 | C-52-PL-838-EI-2410: FF 2, C-52-PL-838-EI-2040: FS | 2025-09-04 11:00 | 2025-09-19 11:00
C-52-PL-838-EI-2410 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.6.2 | Installation of F&G Device | C-52-PL-838-EI-2200, HM-ME-2310, HM-ME-1490 | C-52-PL-838-EI-2200: FF 2, HM-ME-2310: FS, HM-ME-1490: FS | C-52-PL-838-EI-2040 | C-52-PL-838-EI-2040: FS | 2025-08-30 11:00 | 2025-09-22 11:00
C-52-PL-838-EI-2040 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.6.3 | Loop Checking for Instruments | C-52-PL-838-EI-2010, C-52-PL-838-EI-2030, C-52-PL-838-EI-2200, C-52-PL-838-EI-2410 | C-52-PL-838-EI-2010: FS, C-52-PL-838-EI-2030: FS, C-52-PL-838-EI-2200: FS, C-52-PL-838-EI-2410: FS | C-52-PL-838-EI-2050, PRECOM-52-PL-1000 | C-52-PL-838-EI-2050: FF 1, PRECOM-52-PL-1000: FS | 2025-09-22 11:00 | 2025-10-11 11:00
C-52-PL-838-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.6.3 | Glanding & Termination | C-52-PL-838-EI-2000, C-52-PL-838-EI-1800, C-52-PL-838-EI-1810, C-52-PL-838-EI-1400, C-52-PL-838-EI-2040 | C-52-PL-838-EI-2000: FS, C-52-PL-838-EI-1800: FF 3, C-52-PL-838-EI-1810: FS, C-52-PL-838-EI-1400: FS, C-52-PL-838-EI-2040: FF 1 | PRECOM-52-PL-1000, ML1749-E20 | PRECOM-52-PL-1000: FS, ML1749-E20: FS | 2025-09-29 11:00 | 2025-10-13 11:00
C-52-PL-838-CA-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.7.1 | CP Cable Laying | C-52-PL-838-EI-2000, HM-PL-0430, HS-CN-0240 | C-52-PL-838-EI-2000: FS, HM-PL-0430: FS, HS-CN-0240: FS | C-52-PL-838-CA-1010, C-52-PL-838-CI-2800 | C-52-PL-838-CA-1010: FS, C-52-PL-838-CI-2800: FF 2 | 2025-08-16 11:00 | 2025-08-23 11:00
C-52-PL-838-CA-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.7.1 | Installation of CP Test Post | C-52-PL-838-CA-1000 | C-52-PL-838-CA-1000: FS | C-52-PL-838-CA-1020 | C-52-PL-838-CA-1020: FS | 2025-08-23 11:00 | 2025-08-26 11:00
C-52-PL-838-CA-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.7.1 | Installation of CP JB's | C-52-PL-838-CA-1010 | C-52-PL-838-CA-1010: FS | C-52-PL-838-CA-1030 | C-52-PL-838-CA-1030: FS | 2025-08-26 11:00 | 2025-08-28 11:00
C-52-PL-838-CA-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.7.1 | Glanding & Termination for CP S/m | C-52-PL-838-CA-1020 | C-52-PL-838-CA-1020: FS | PRECOM-52-PL-1000 | PRECOM-52-PL-1000: FS | 2025-08-28 11:00 | 2025-08-30 11:00
C-52-PL-838-TE-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.8.2 | FOC Laying | C-52-PL-838-EI-2010 | C-52-PL-838-EI-2010: SS 7 | C-52-PL-838-TE-1420, C-52-PL-838-CI-2810 | C-52-PL-838-TE-1420: FS, C-52-PL-838-CI-2810: FF 2 | 2025-08-25 11:00 | 2025-09-11 11:00
C-52-PL-838-TE-1420 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.8.2 | FO Cable OTDR Testing & Splicing | C-52-PL-838-TE-1410, C-52-PL-838-TE-1600 | C-52-PL-838-TE-1410: FS, C-52-PL-838-TE-1600: FS | PRECOM-52-PL-1000 | PRECOM-52-PL-1000: FS | 2025-10-11 11:00 | 2025-10-14 11:00
C-56-PL-607-CI-1000 | Completed | P2543-R01-Oct24..4.3.1.1.1.12.1.1 | Site Survey, Preparation & Grading Works | HE-CS-0170, HE-SS-0030, ML1002 | HE-CS-0170: FS, HE-SS-0030: SS, ML1002: FS | C-56-PL-607-CI-1010 | C-56-PL-607-CI-1010: FS | 2024-06-05 07:00 | 2024-08-12 17:00
C-56-PL-607-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.1 | Earth Works for Equipment Foundations | C-56-PL-607-CI-1000, HE-CS-0650, HE-CS-0470, HE-CS-1630 | C-56-PL-607-CI-1000: FS, HE-CS-0650: FS 25, HE-CS-0470: FS, HE-CS-1630: FS | C-56-PL-607-CI-1020, C-56-PL-607-CI-1200 | C-56-PL-607-CI-1020: FS, C-56-PL-607-CI-1200: FS | 2024-12-18 07:00 | 2025-01-04 17:00
C-56-PL-607-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.1 | Earth Works for Pipe Support Foundations | C-56-PL-607-CI-1010 | C-56-PL-607-CI-1010: FS | C-56-PL-607-CI-1030, C-56-PL-607-CI-1210 | C-56-PL-607-CI-1030: FS, C-56-PL-607-CI-1210: FS | 2025-01-06 07:00 | 2025-01-22 17:00
C-56-PL-607-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.1 | Earth Works for Field Instrument, JBs & Light Pole Foundations | C-56-PL-607-CI-1020 | C-56-PL-607-CI-1020: FS | C-56-PL-607-CI-1040, C-56-PL-607-CI-1220 | C-56-PL-607-CI-1040: FS 7, C-56-PL-607-CI-1220: FS 3 | 2025-01-23 07:00 | 2025-02-07 17:00
C-56-PL-607-CI-1040 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.1 | Earth Works for Access Platforms & Misc. Structural Foundations | C-56-PL-607-CI-1030 | C-56-PL-607-CI-1030: FS 7 | C-56-PL-607-CI-1050, C-56-PL-607-CI-1230 | C-56-PL-607-CI-1050: FS 7, C-56-PL-607-CI-1230: FS 3 | 2025-02-17 07:00 | 2025-03-15 15:00
C-56-PL-607-CI-1050 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.1 | Earth Works for Thrust Anchor Block | C-56-PL-607-CI-1040 | C-56-PL-607-CI-1040: FS 7 | C-56-PL-607-CI-1240 | C-56-PL-607-CI-1240: FS 3 | 2025-03-26 11:00 | 2025-05-05 14:00
C-56-PL-607-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.2 | Compaction & Testing for Equipment Foundations | C-56-PL-607-CI-1010 | C-56-PL-607-CI-1010: FS | C-56-PL-607-CI-1400 | C-56-PL-607-CI-1400: FS | 2025-01-06 07:00 | 2025-01-21 17:00
C-56-PL-607-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.2 | Compaction & Testing for Pipe Support Foundations | C-56-PL-607-CI-1020 | C-56-PL-607-CI-1020: FS | C-56-PL-607-CI-1600 | C-56-PL-607-CI-1600: FS | 2025-01-23 07:00 | 2025-02-07 17:00
C-56-PL-607-CI-1220 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.2 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | C-56-PL-607-CI-1030 | C-56-PL-607-CI-1030: FS 3 | C-56-PL-607-CI-1410 | C-56-PL-607-CI-1410: FS 7 | 2025-02-12 07:00 | 2025-02-27 17:00
C-56-PL-607-CI-1230 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.2 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-56-PL-607-CI-1040 | C-56-PL-607-CI-1040: FS 3 | C-56-PL-607-CI-1420 | C-56-PL-607-CI-1420: FS 7 | 2025-03-20 11:00 | 2025-04-11 13:00
C-56-PL-607-CI-1240 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.2 | Compaction & Testing for Thrust Anchor Block | C-56-PL-607-CI-1050 | C-56-PL-607-CI-1050: FS 3 | C-56-PL-607-CI-1510 | C-56-PL-607-CI-1510: FS | 2025-05-09 11:00 | 2025-05-15 11:00
C-56-PL-607-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.3 | Concrete Works for Equipment Foundations | C-56-PL-607-CI-1200, CTF-SO1030, HE-CS-0230, HE-CS-0650, HE-CS-1070, HE-CS-1190, HE-CS-1310, HM-CS-0040 | C-56-PL-607-CI-1200: FS, CTF-SO1030: FS, HE-CS-0230: FS, HE-CS-0650: FS, HE-CS-1070: FS, HE-CS-1190: FS, HE-CS-1310: FF, HM-CS-0040: FS | C-56-PL-607-CI-1600, C-56-PL-607-CI-1800, C-56-PL-607-ME-1000, ML1619-E07 | C-56-PL-607-CI-1600: FS, C-56-PL-607-CI-1800: FS, C-56-PL-607-ME-1000: FS, ML1619-E07: FS | 2025-01-22 07:00 | 2025-02-22 17:00
C-56-PL-607-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.5 | Concrete Works for Pipe Support Foundations | C-56-PL-607-CI-1210, C-56-PL-607-CI-1400, C-56-PL-607-CI-1500 | C-56-PL-607-CI-1210: FS, C-56-PL-607-CI-1400: FS, C-56-PL-607-CI-1500: FF | C-56-PL-607-CI-1410, C-56-PL-607-CI-1800, C-56-PL-607-CI-2000, ML1619-E07 | C-56-PL-607-CI-1410: FS 7, C-56-PL-607-CI-1800: FS 60, C-56-PL-607-CI-2000: FS, ML1619-E07: FS | 2025-02-24 07:00 | 2025-03-15 15:00
C-56-PL-607-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.3 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-56-PL-607-CI-1220, C-56-PL-607-CI-1600 | C-56-PL-607-CI-1220: FS 7, C-56-PL-607-CI-1600: FS 7 | C-56-PL-607-CI-1420, C-56-PL-607-EI-2210, C-56-PL-607-EI-1800, ML1619-E07 | C-56-PL-607-CI-1420: FS 7, C-56-PL-607-EI-2210: FS, C-56-PL-607-EI-1800: FS, ML1619-E07: FS | 2025-03-26 11:00 | 2025-04-16 13:00
C-56-PL-607-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.3 | Concrete Works for Access Platforms & Misc. Structural Foundations | C-56-PL-607-CI-1230, C-56-PL-607-CI-1410 | C-56-PL-607-CI-1230: FS 7, C-56-PL-607-CI-1410: FS 7 | C-56-PL-607-CI-1510, C-56-PL-607-CI-3000, ML1619-E07 | C-56-PL-607-CI-1510: FS, C-56-PL-607-CI-3000: FS, ML1619-E07: FS | 2025-04-24 13:00 | 2025-05-20 11:00
C-56-PL-607-CI-1510 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.9 | Concrete Works for Thrust Anchor Block | C-56-PL-607-CI-1240, C-56-PL-607-CI-1420, HM-PL-940 | C-56-PL-607-CI-1240: FS, C-56-PL-607-CI-1420: FS, HM-PL-940: FS | PRECOM-56-PL-1000 | PRECOM-56-PL-1000: FS | 2025-05-20 11:00 | 2025-08-01 11:00
C-56-PL-607-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.6 | Electrical & Earthing Cable Trenching | C-56-PL-607-CI-1400, C-56-PL-607-CI-1600, HE-EL-0530 | C-56-PL-607-CI-1400: FS, C-56-PL-607-CI-1600: FS 60, HE-EL-0530: FS | C-56-PL-607-EI-2000, C-56-PL-607-EI-2010, C-56-PL-607-CI-1810, C-56-PL-607-TE-1420, C-56-PL-607-TE-1410 | C-56-PL-607-EI-2000: FS 3, C-56-PL-607-EI-2010: FS, C-56-PL-607-CI-1810: FS, C-56-PL-607-TE-1420: FS, C-56-PL-607-TE-1410: FS | 2025-06-02 11:00 | 2025-06-20 11:00
C-56-PL-607-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.13 | Back Filling for Electrical & Earthing Cable | C-56-PL-607-EI-2040 | C-56-PL-607-EI-2040: FS | C-56-PL-607-CI-2810, C-56-PL-607-CI-2600, PRECOM-56-PL-1000 | C-56-PL-607-CI-2810: FS, C-56-PL-607-CI-2600: SS, PRECOM-56-PL-1000: FS | 2025-07-12 07:00 | 2025-07-23 17:00
C-56-PL-607-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.13 | Back Filling for Instrument & Telecom Cable | C-56-PL-607-CI-2800, C-56-PL-607-EI-2040 | C-56-PL-607-CI-2800: FS, C-56-PL-607-EI-2040: FS | C-56-PL-607-CI-2600, PRECOM-56-PL-1000 | C-56-PL-607-CI-2600: SS 6, PRECOM-56-PL-1000: FS | 2025-07-24 07:00 | 2025-08-04 17:00
C-56-PL-607-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.14 | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PL-607-CI-2810, C-56-PL-607-CI-2800, C-56-PL-607-CI-2220, C-56-PL-607-CI-2240, HE-CS-0290, ML1059-B28 | C-56-PL-607-CI-2810: SS 6, C-56-PL-607-CI-2800: SS, C-56-PL-607-CI-2220: FS, C-56-PL-607-CI-2240: FS, HE-CS-0290: FS, ML1059-B28: FS | PRECOM-56-PL-1000 | PRECOM-56-PL-1000: FS | 2025-08-16 11:00 | 2025-09-02 11:00
C-56-PL-607-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.8 | Pre-Fabrication & Installation of Pipe Supports | C-56-PL-607-CI-1600, C-56-PL-607-CI-2400, HE-CS-1430, HE-CS-1490, HM-CS-0110, HS-CN-0690 | C-56-PL-607-CI-1600: FS, C-56-PL-607-CI-2400: FF, HE-CS-1430: FS, HE-CS-1490: FS, HM-CS-0110: FS, HS-CN-0690: FS | C-56-PL-607-EI-2210, C-56-PL-607-PI-1000 | C-56-PL-607-EI-2210: FS, C-56-PL-607-PI-1000: FS | 2025-03-15 15:00 | 2025-04-26 13:00
C-56-PL-607-EI-2210 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.3 | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-56-PL-607-CI-1410, C-56-PL-607-CI-2000, C-56-PL-607-PI-1000 | C-56-PL-607-CI-1410: FS, C-56-PL-607-CI-2000: FS, C-56-PL-607-PI-1000: SS | C-56-PL-607-CI-3000, C-56-PL-607-EI-2200, C-56-PL-607-EI-1810, C-56-PL-607-EI-1600, ML1629-E08 | C-56-PL-607-CI-3000: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1810: FS, C-56-PL-607-EI-1600: FS, ML1629-E08: FS | 2025-04-26 13:00 | 2025-05-22 11:00
C-56-PL-607-CI-3000 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.11 | Pre-Fabrication & Installation of Platforms & Crossovers | C-56-PL-607-CI-1420, C-56-PL-607-EI-2210, HM-CS-0110, HS-CN-0690 | C-56-PL-607-CI-1420: FS, C-56-PL-607-EI-2210: FS, HM-CS-0110: FS, HS-CN-0690: FS | C-56-PL-607-CI-3010, C-56-PL-607-CI-3010, PRECOM-56-PL-1000 | C-56-PL-607-CI-3010: SS 14, C-56-PL-607-CI-3010: FF, PRECOM-56-PL-1000: FS | 2025-05-22 11:00 | 2025-06-26 11:00
C-56-PL-607-CI-3010 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.11 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-56-PL-607-CI-3000, C-56-PL-607-CI-3000 | C-56-PL-607-CI-3000: SS 14, C-56-PL-607-CI-3000: FF | PRECOM-56-PL-1000, C-56-PL-607-CI-2220 | PRECOM-56-PL-1000: FS, C-56-PL-607-CI-2220: FF 21 | 2025-06-10 11:00 | 2025-07-05 11:00
C-56-PL-607-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.4.1 | Piping Pre-Fabrication | C-56-PL-607-CI-2000, C-COM-1010, CTF-SO1050, HE-PI-0370, HE-PI-0640, HE-PI-1240, HE-PI-1300, HE-PR-0290, HE-PR-0890, HM-PI-0040, HS-CN-0190, ML1002, ML1014-B10, ML1219-B19 | C-56-PL-607-CI-2000: FS, C-COM-1010: FS, CTF-SO1050: FS, HE-PI-0370: FS, HE-PI-0640: FS, HE-PI-1240: FS, HE-PI-1300: FS, HE-PR-0290: FS, HE-PR-0890: FS, HM-PI-0040: FS, HS-CN-0190: FS, ML1002: FS, ML1014-B10: FS, ML1219-B19: FS | C-56-PL-607-PI-1200, C-56-PL-607-EI-2210 | C-56-PL-607-PI-1200: FS, C-56-PL-607-EI-2210: SS | 2025-04-26 13:00 | 2025-06-12 11:00
C-56-PL-607-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.4.2 | Piping Erection | C-56-PL-607-PI-1000, HE-PI-1240, HE-PI-1300, HE-PR-0290, HE-PR-0890, HM-PI-0040, HM-PI-0050, HM-PL-0220, HM-PL-0630, HM-PL-0740, HM-PL-1510, HM-PL-1570, ML1014-B10, ML1219-B19 | C-56-PL-607-PI-1000: FS, HE-PI-1240: FS, HE-PI-1300: FS, HE-PR-0290: FS, HE-PR-0890: FS, HM-PI-0040: FS, HM-PI-0050: FS, HM-PL-0220: FF 12, HM-PL-0630: FS, HM-PL-0740: FS, HM-PL-1510: FS, HM-PL-1570: FF 12, ML1014-B10: FS, ML1219-B19: FS | C-56-PL-607-PI-1400, C-56-PL-607-PI-1400 | C-56-PL-607-PI-1400: SS 5, C-56-PL-607-PI-1400: FF | 2025-06-12 11:00 | 2025-07-11 11:00
C-56-PL-607-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.4.3 | Field Joint Welding | C-56-PL-607-PI-1200, C-56-PL-607-PI-1200, HE-PI-1300, HS-CN-0190, ML1002, ML1014-B10, ML1219-B19 | C-56-PL-607-PI-1200: SS 5, C-56-PL-607-PI-1200: FF, HE-PI-1300: FS, HS-CN-0190: FS, ML1002: FS, ML1014-B10: FS, ML1219-B19: FS | C-56-PL-607-PI-1410, C-56-PL-607-PL-1000, C-56-PL-607-PI-1410 | C-56-PL-607-PI-1410: SS 3, C-56-PL-607-PL-1000: FS 21, C-56-PL-607-PI-1410: FF | 2025-06-18 11:00 | 2025-07-17 11:00
C-56-PL-607-PI-1410 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.4.3 | NDT & Coating for Field Joint Weld | C-56-PL-607-PI-1400, C-56-PL-607-ME-1600, C-56-PL-607-PI-1400 | C-56-PL-607-PI-1400: SS 3, C-56-PL-607-ME-1600: FF, C-56-PL-607-PI-1400: FF | C-56-PL-607-PI-1600 | C-56-PL-607-PI-1600: FS | 2025-06-21 11:00 | 2025-07-21 11:00
C-56-PL-607-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.4.4 | Hydrotesting | C-56-PL-607-PI-1410, ML1014-B10, ML1219-B19 | C-56-PL-607-PI-1410: FS, ML1014-B10: FS, ML1219-B19: FS | C-56-PL-607-PI-1800 | C-56-PL-607-PI-1800: FS | 2025-07-21 11:00 | 2025-07-26 11:00
C-56-PL-607-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.4.5 | Installation of Valves/MOV/ROV | C-56-PL-607-PI-1600, HE-PI-1240, HE-PR-0290, HE-PR-0890, HM-PL-0220, HM-PL-0630, HM-PL-0640, HM-PL-0740, HM-PL-1510, HM-PL-1570, ML1014-B10, ML1219-B19, HM-ME-0680, HM-ME-2240 | C-56-PL-607-PI-1600: FS, HE-PI-1240: FS, HE-PR-0290: FS, HE-PR-0890: FS, HM-PL-0220: FF 12, HM-PL-0630: FS, HM-PL-0640: FS, HM-PL-0740: FS, HM-PL-1510: FS, HM-PL-1570: FF 12, ML1014-B10: FS, ML1219-B19: FS, HM-ME-0680: FS, HM-ME-2240: FS | PRECOM-56-PL-1000 | PRECOM-56-PL-1000: FS | 2025-07-26 11:00 | 2025-08-01 11:00
C-56-PL-607-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.4.6 | Final Bolt Torquing/ Re-Instatement | HE-PI-1240, HE-PI-1300, HE-PR-0290, HE-PR-0890, HM-PL-0220, HM-PL-0630, HM-PL-0640, HM-PL-0740, HM-PL-1510, HM-PL-1570, HS-CN-0190, ML1002, ML1014-B10, ML1219-B19 | HE-PI-1240: FS, HE-PI-1300: FS, HE-PR-0290: FS, HE-PR-0890: FS, HM-PL-0220: FF 12, HM-PL-0630: FS, HM-PL-0640: FS, HM-PL-0740: FS, HM-PL-1510: FS, HM-PL-1570: FF 12, HS-CN-0190: FS, ML1002: FS, ML1014-B10: FS, ML1219-B19: FS | C-56-PL-607-EI-2200, PRECOM-56-PL-1000, ML1629-E08 | C-56-PL-607-EI-2200: FS, PRECOM-56-PL-1000: FS, ML1629-E08: FS | 2025-03-29 07:00 | 2025-04-07 17:00
C-56-PL-607-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.3.1 | Installation of Pig Launcher (607-V-603) 56" | C-56-PL-607-CI-1400, C-COM-790, HM-ME-2390, HM-PL-0840, HM-PL-1530, ML1015-B08, ML1519-D04 | C-56-PL-607-CI-1400: FS, C-COM-790: FS, HM-ME-2390: FS, HM-PL-0840: FF, HM-PL-1530: FF 3, ML1015-B08: FS, ML1519-D04: FS | PRECOM-56-PL-1000, C-56-PL-607-ME-1200 | PRECOM-56-PL-1000: FS, C-56-PL-607-ME-1200: FS | 2025-03-18 07:00 | 2025-04-03 07:00
C-56-PL-607-PL-1000 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.5.1 | Installation of Isolation Joint | C-56-PL-607-PI-1400, C-56-HC01-PL-ME-4810, C-56-HC01-PL-ME-5010, HM-ME-2390, ML1519-D04 | C-56-PL-607-PI-1400: FS 21, C-56-HC01-PL-ME-4810: FS, C-56-HC01-PL-ME-5010: FS, HM-ME-2390: FS, ML1519-D04: FS | C-56-PL-607-PL-1010 | C-56-PL-607-PL-1010: SS 1 | 2025-08-11 11:00 | 2025-08-13 11:00
C-56-PL-607-PL-1010 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.5.1 | Field Joint Welding (Piping/Pipeline Section including IJ) | C-56-PL-607-PL-1000 | C-56-PL-607-PL-1000: SS 1 | C-56-PL-607-PL-1020 | C-56-PL-607-PL-1020: SS 1 | 2025-08-12 11:00 | 2025-08-18 11:00
C-56-PL-607-PL-1020 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.5.1 | NDT for Weld Joint | C-56-PL-607-PL-1010 | C-56-PL-607-PL-1010: SS 1 | C-56-PL-607-PL-1030 | C-56-PL-607-PL-1030: SS 1 | 2025-08-13 11:00 | 2025-08-19 11:00
C-56-PL-607-PL-1030 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.5.1 | Ext. Coating for Weld Joint | C-56-PL-607-PL-1020 | C-56-PL-607-PL-1020: SS 1 | PRECOM-56-PL-1000, CCM-PM4510, A3980 | PRECOM-56-PL-1000: FS, CCM-PM4510: FS, A3980: FS | 2025-08-14 11:00 | 2025-08-20 11:00
C-56-PL-607-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.1 | Electrical & Earthing Cable Laying | C-56-PL-607-CI-1800, HE-EL-0470, HE-EL-0590, HE-EL-0830, HE-EL-1610, HE-EL-1950, HE-IC-0190, HE-IC-0210, HE-IC-0230, HE-IC-0250, HE-IC-0270, HE-IC-0290, HE-IC-0570, HE-IC-0590, HE-IC-0790, HE-IC-0830, HE-IC-0950, HE-IC-1010, HM-EL-0080, HM-EL-0520, HM-EL-6 | C-56-PL-607-CI-1800: FS 3, HE-EL-0470: FS, HE-EL-0590: FS, HE-EL-0830: FS, HE-EL-1610: FS, HE-EL-1950: FS, HE-IC-0190: FS, HE-IC-0210: FS, HE-IC-0230: FS, HE-IC-0250: FS, HE-IC-0270: FS, HE-IC-0290: FS, HE-IC-0570: FS, HE-IC-0590: FS, HE-IC-0790: FS, HE-IC | C-56-PL-607-EI-1400, C-56-PL-607-EI-2020, C-56-PL-607-EI-1800, C-56-PL-607-EI-2050, C-56-PL-607-CA-1000, C-56-EB2-EI-1210 | C-56-PL-607-EI-1400: SS, C-56-PL-607-EI-2020: FS, C-56-PL-607-EI-1800: FS, C-56-PL-607-EI-2050: FS, C-56-PL-607-CA-1000: FS, C-56-EB2-EI-1210: FS | 2025-06-24 11:00 | 2025-07-11 11:00
C-56-PL-607-EI-1400 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.2 | Deep Earth Well Drilling | C-56-PL-607-EI-2000, HE-EL-0290, HE-EL-0530, HE-EL-0640, HE-EL-0650, HE-EL-0710, HE-EL-1010, HE-EL-1670, HE-EL-1730, HE-EL-1790, HE-HS-0350, HE-IC-0010, HE-IC-0490, HE-IC-0530, HE-IC-0590, HE-IC-0650, HE-IC-0710, HE-IC-0770, HE-IC-1430, HE-IC-1550, HE-IC-1 | C-56-PL-607-EI-2000: SS, HE-EL-0290: FS, HE-EL-0530: FS, HE-EL-0640: FS, HE-EL-0650: FS, HE-EL-0710: FS, HE-EL-1010: FS, HE-EL-1670: FS, HE-EL-1730: FS, HE-EL-1790: FS, HE-HS-0350: FS, HE-IC-0010: SS 10, HE-IC-0490: FS, HE-IC-0530: FS, HE-IC-0590: FS, HE-I | C-56-PL-607-EI-2050, ML1629-E08 | C-56-PL-607-EI-2050: FS, ML1629-E08: FS | 2025-07-11 07:00 | 2025-07-17 17:00
C-56-PL-607-EI-2020 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.1 | Installation of Cable Trays | C-56-PL-607-EI-2000 | C-56-PL-607-EI-2000: FS | C-56-PL-607-EI-2030, C-56-PL-607-EI-1800, C-56-PL-607-EI-1810, C-56-PL-607-EI-2010 | C-56-PL-607-EI-2030: SS 3, C-56-PL-607-EI-1800: FS, C-56-PL-607-EI-1810: FS, C-56-PL-607-EI-2010: FS | 2025-07-11 11:00 | 2025-07-18 11:00
C-56-PL-607-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.1 | Instrument Cable Laying | C-56-PL-607-EI-2020, C-56-PL-607-CI-1800, C-56-PL-607-CI-1810 | C-56-PL-607-EI-2020: FS, C-56-PL-607-CI-1800: FS, C-56-PL-607-CI-1810: FS | C-56-PL-607-EI-2030, C-56-PL-607-EI-1600, C-56-PL-607-TE-1420, C-56-PL-607-TE-1410 | C-56-PL-607-EI-2030: FS, C-56-PL-607-EI-1600: FS, C-56-PL-607-TE-1420: FS, C-56-PL-607-TE-1410: FS | 2025-07-18 11:00 | 2025-08-04 11:00
C-56-PL-607-EI-2030 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.1 | Instrument Tubing Works | C-56-PL-607-EI-2020, C-56-PL-607-EI-2010 | C-56-PL-607-EI-2020: SS 3, C-56-PL-607-EI-2010: FS | C-56-PL-607-EI-1810 | C-56-PL-607-EI-1810: FS | 2025-08-04 11:00 | 2025-08-18 11:00
C-56-PL-607-EI-1800 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.5 | Installation of Light Pole, Lighting & Fixtures | C-56-PL-607-CI-1410, C-56-PL-607-EI-2020, C-56-PL-607-EI-2000, HE-EL-1670, HE-IC-0710, HE-EL-0640, HE-IC-1550, HM-ME-1590, HM-IC-0040, HE-IC-0770, HM-EL-0520, HE-IC-0490, HE-IC-2570, HE-IC-0650, HM-EL-0080, ML1032-B21, HE-EL-1730, HE-EL-0290, HE-IC-1430, H | C-56-PL-607-CI-1410: FS, C-56-PL-607-EI-2020: FS, C-56-PL-607-EI-2000: FS, HE-EL-1670: FS, HE-IC-0710: FS, HE-EL-0640: FS, HE-IC-1550: FS, HM-ME-1590: FF, HM-IC-0040: FF, HE-IC-0770: FS, HM-EL-0520: FS, HE-IC-0490: FS, HE-IC-2570: FS, HE-IC-0650: FS, HM-EL | C-56-PL-607-EI-1810, C-56-PL-607-EI-2050, ML1629-E08 | C-56-PL-607-EI-1810: FS, C-56-PL-607-EI-2050: FS, ML1629-E08: FS | 2025-07-19 07:00 | 2025-07-25 17:00
C-56-PL-607-EI-1810 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.1 | Installation of JB's & PDB's | C-56-PL-607-EI-1800, C-56-PL-607-EI-2020, C-56-PL-607-EI-2030, C-56-PL-607-EI-2210, C-56-PL-607-EI-1600 | C-56-PL-607-EI-1800: FS, C-56-PL-607-EI-2020: FS, C-56-PL-607-EI-2030: FS, C-56-PL-607-EI-2210: FS, C-56-PL-607-EI-1600: FS | C-56-PL-607-EI-2050 | C-56-PL-607-EI-2050: FS | 2025-08-18 11:00 | 2025-08-29 11:00
C-56-PL-607-EI-2200 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.3 | Installation of Field Instruments (Including Pig Signaller) | C-56-PL-607-EI-2210, C-56-PL-607-PI-2000, HE-EL-0290, HE-EL-0530, HE-EL-0640, HE-EL-0650, HE-EL-0710, HE-EL-1010, HE-EL-1670, HE-EL-1730, HE-EL-1790, HE-HS-0350, HE-IC-0010, HE-IC-0490, HE-IC-0530, HE-IC-0590, HE-IC-0650, HE-IC-0710, HE-IC-0770, HE-IC-1430 | C-56-PL-607-EI-2210: FS, C-56-PL-607-PI-2000: FS, HE-EL-0290: FS, HE-EL-0530: FS, HE-EL-0640: FS, HE-EL-0650: FS, HE-EL-0710: FS, HE-EL-1010: FS, HE-EL-1670: FS, HE-EL-1730: FS, HE-EL-1790: FS, HE-HS-0350: FS, HE-IC-0010: SS 10, HE-IC-0490: FS, HE-IC-0530: | C-56-PL-607-EI-2410, ML1629-E08 | C-56-PL-607-EI-2410: FS, ML1629-E08: FS | 2025-06-09 07:00 | 2025-06-24 17:00
C-56-PL-607-EI-2410 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.4 | Installation of F&G Device | C-56-PL-607-EI-2200, HE-EL-1670, HE-IC-0710, HE-EL-0640, HE-IC-1550, HM-ME-1590, HM-IC-0040, HE-IC-0770, HM-EL-0520, HE-IC-0490, HE-IC-2570, HE-IC-0650, HM-EL-0080, ML1032-B21, HE-EL-1730, HE-EL-0290, HM-ME-1490, HE-IC-1430, HE-HS-0350, HM-EL-0280, HE-EL-0 | C-56-PL-607-EI-2200: FS, HE-EL-1670: FS, HE-IC-0710: FS, HE-EL-0640: FS, HE-IC-1550: FF, HM-ME-1590: FF, HM-IC-0040: FF, HE-IC-0770: FS, HM-EL-0520: FS, HE-IC-0490: FS, HE-IC-2570: FS, HE-IC-0650: FS, HM-EL-0080: FS, ML1032-B21: FS, HE-EL-1730: FS, HE-EL-0 | C-56-PL-607-EI-2040, ML1629-E08 | C-56-PL-607-EI-2040: FS, ML1629-E08: FS | 2025-06-25 07:00 | 2025-07-02 17:00
C-56-PL-607-EI-2040 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.1 | Loop Checking for Instruments | C-56-PL-607-EI-2410 | C-56-PL-607-EI-2410: FS | C-56-PL-607-EI-2050, C-56-PL-607-CI-2800, C-56-PL-607-CI-2810, PRECOM-56-PL-1000 | C-56-PL-607-EI-2050: FF, C-56-PL-607-CI-2800: FS, C-56-PL-607-CI-2810: FS, PRECOM-56-PL-1000: FS | 2025-07-03 07:00 | 2025-07-11 17:00
C-56-PL-607-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.1 | Glanding & Termination | C-56-PL-607-EI-2000, C-56-PL-607-EI-1800, C-56-PL-607-EI-1810, C-56-PL-607-EI-2040, C-56-PL-607-EI-1400 | C-56-PL-607-EI-2000: FS, C-56-PL-607-EI-1800: FS, C-56-PL-607-EI-1810: FS, C-56-PL-607-EI-2040: FF, C-56-PL-607-EI-1400: FS | PRECOM-56-PL-1000, ML1629-E08 | PRECOM-56-PL-1000: FS, ML1629-E08: FS | 2025-08-29 11:00 | 2025-09-06 11:00
C-56-PL-607-CA-1000 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.1 | CP Cable Laying | C-56-PL-607-EI-2000 | C-56-PL-607-EI-2000: FS | C-56-PL-607-CA-1010 | C-56-PL-607-CA-1010: FS | 2025-07-11 11:00 | 2025-07-18 11:00
C-56-PL-607-CA-1010 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.1 | Installation of CP Test Post | C-56-PL-607-CA-1000 | C-56-PL-607-CA-1000: FS | C-56-PL-607-CA-1020 | C-56-PL-607-CA-1020: FS | 2025-07-18 11:00 | 2025-07-21 11:00
C-56-PL-607-CA-1020 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.1 | Installation of CP JB's | C-56-PL-607-CA-1010 | C-56-PL-607-CA-1010: FS | C-56-PL-607-CA-1030 | C-56-PL-607-CA-1030: FS | 2025-07-21 11:00 | 2025-07-23 11:00
C-56-PL-607-CA-1030 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.1 | Glanding & Termination for CP S/m | C-56-PL-607-CA-1020 | C-56-PL-607-CA-1020: FS | PRECOM-56-PL-1000, ML1629-E08 | PRECOM-56-PL-1000: FS, ML1629-E08: FS | 2025-07-23 11:00 | 2025-07-25 11:00
C-56-PL-607-TE-1420 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.8.2 | FO Cable OTDR Testing & Splicing | C-56-PL-607-TE-1600, C-56-PL-607-EI-2010, C-56-PL-607-CI-1800, C-56-PL-607-CI-1810, C-56-PL-607-TE-1400 | C-56-PL-607-TE-1600: FS, C-56-PL-607-EI-2010: FS, C-56-PL-607-CI-1800: FS, C-56-PL-607-CI-1810: FS, C-56-PL-607-TE-1400: FF | PRECOM-56-PL-1000 | PRECOM-56-PL-1000: FS | 2025-08-26 11:00 | 2025-08-28 11:00
C-56-PR-838-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.9 | Site Survey, Preparation & Grading Works | HE-SS-0030, ML1002, CTF-1000, HE-CS-0170, CTF-1010, HE-CS-0470 | HE-SS-0030: SS, ML1002: FS, CTF-1000: FS, HE-CS-0170: FS, CTF-1010: FS, HE-CS-0470: FS 20 | C-56-PR-838-CI-1010, C-56-PR-838-CI-1800, C-4N-HG-TPR-CI-1000 | C-56-PR-838-CI-1010: FS, C-56-PR-838-CI-1800: FS, C-4N-HG-TPR-CI-1000: FS | 2024-11-30 07:00 | 2024-12-19 17:00
C-56-PR-838-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.9 | Earth Works for Equipment Foundations | C-56-PR-838-CI-1000 | C-56-PR-838-CI-1000: FS | C-56-PR-838-CI-1020, C-56-PR-838-CI-1200 | C-56-PR-838-CI-1020: FS, C-56-PR-838-CI-1200: FS 21 | 2024-12-20 07:00 | 2025-01-07 17:00
C-56-PR-838-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.9 | Earth Works for Pipe Support Foundations | C-56-PR-838-CI-1010 | C-56-PR-838-CI-1010: FS | C-56-PR-838-CI-1030, C-56-PR-838-CI-1210 | C-56-PR-838-CI-1030: FS, C-56-PR-838-CI-1210: FS | 2025-01-08 07:00 | 2025-01-24 17:00
C-56-PR-838-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.9 | Earth Works for Field Instrument, JBs & Light Pole Foundations | C-56-PR-838-CI-1020 | C-56-PR-838-CI-1020: FS | C-56-PR-838-CI-1040, C-56-PR-838-CI-1220 | C-56-PR-838-CI-1040: FS, C-56-PR-838-CI-1220: FS | 2025-01-25 07:00 | 2025-02-10 17:00
C-56-PR-838-CI-1040 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.9 | Earth Works for Access Platforms & Misc. Structural Foundations | C-56-PR-838-CI-1030 | C-56-PR-838-CI-1030: FS | C-56-PR-838-CI-1050, C-56-PR-838-CI-1230 | C-56-PR-838-CI-1050: FS, C-56-PR-838-CI-1230: FS | 2025-02-11 07:00 | 2025-02-26 17:00
C-56-PR-838-CI-1050 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.9 | Earth Works for Thrust Anchor Block | C-56-PR-838-CI-1040 | C-56-PR-838-CI-1040: FS | C-56-PR-838-CI-1060, C-56-PR-838-CI-1240 | C-56-PR-838-CI-1060: FS, C-56-PR-838-CI-1240: FS | 2025-02-27 07:00 | 2025-03-29 13:00
C-56-PR-838-CI-1060 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.9 | Earth Works for Impact Wall | C-56-PR-838-CI-1050 | C-56-PR-838-CI-1050: FS | C-56-PR-838-CI-1250, C-56-PR-838-CI-1800 | C-56-PR-838-CI-1250: FS, C-56-PR-838-CI-1800: FS 9 | 2025-03-29 13:00 | 2025-04-11 13:00
C-56-PR-838-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.10 | Compaction & Testing for Equipment Foundations | C-56-PR-838-CI-1010 | C-56-PR-838-CI-1010: FS 21 | C-56-PR-838-CI-1400 | C-56-PR-838-CI-1400: FS | 2025-02-01 07:00 | 2025-02-10 17:00
C-56-PR-838-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.10 | Compaction & Testing for Pipe Support Foundations | C-56-PR-838-CI-1020 | C-56-PR-838-CI-1020: FS | C-56-PR-838-CI-1600 | C-56-PR-838-CI-1600: FS | 2025-01-25 07:00 | 2025-02-03 17:00
C-56-PR-838-CI-1220 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.10 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | C-56-PR-838-CI-1030 | C-56-PR-838-CI-1030: FS | C-56-PR-838-CI-1410 | C-56-PR-838-CI-1410: FS | 2025-02-11 07:00 | 2025-02-15 17:00
C-56-PR-838-CI-1230 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.10 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-56-PR-838-CI-1040 | C-56-PR-838-CI-1040: FS | C-56-PR-838-CI-1420 | C-56-PR-838-CI-1420: FS | 2025-02-27 07:00 | 2025-03-05 09:00
C-56-PR-838-CI-1240 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.10 | Compaction & Testing for Thrust Anchor Block | C-56-PR-838-CI-1050 | C-56-PR-838-CI-1050: FS | C-56-PR-838-CI-1510 | C-56-PR-838-CI-1510: FS | 2025-03-29 13:00 | 2025-04-11 13:00
C-56-PR-838-CI-1250 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.10 | Compaction & Testing for Impact Wall | C-56-PR-838-CI-1060 | C-56-PR-838-CI-1060: FS | C-56-PR-838-CI-1500 | C-56-PR-838-CI-1500: FS | 2025-04-11 13:00 | 2025-04-17 13:00
C-56-PR-838-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.11 | Concrete Works for Equipment Foundations | C-56-PR-838-CI-1200, HE-CS-0230, HM-CS-0050, HE-CS-1190, HE-CS-1070, HE-CS-0650, HE-CS-1310, HM-CS-0040 | C-56-PR-838-CI-1200: FS, HE-CS-0230: FS, HM-CS-0050: FS, HE-CS-1190: FS, HE-CS-1070: FS, HE-CS-0650: FS, HE-CS-1310: FF, HM-CS-0040: SS | C-56-PR-838-ME-1100, ML1619-E07 | C-56-PR-838-ME-1100: FS, ML1619-E07: FS | 2025-02-11 07:00 | 2025-03-08 11:00
C-56-PR-838-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.13 | Concrete Works for Pipe Support Foundations | C-56-PR-838-CI-1210, HM-CS-0050 | C-56-PR-838-CI-1210: FS, HM-CS-0050: FS | C-56-PR-838-CI-1410, C-56-PR-838-CI-2000, ML1619-E07 | C-56-PR-838-CI-1410: FS, C-56-PR-838-CI-2000: FS, ML1619-E07: FS | 2025-02-04 07:00 | 2025-03-20 11:00
C-56-PR-838-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.11 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-56-PR-838-CI-1220, C-56-PR-838-CI-1600, HE-CS-0230, HM-CS-0050, HE-CS-0650, HM-CS-0040 | C-56-PR-838-CI-1220: FS, C-56-PR-838-CI-1600: FS, HE-CS-0230: FS, HM-CS-0050: FF, HE-CS-0650: FS, HM-CS-0040: SS | C-56-PR-838-CI-1420, C-56-PR-838-EI-2210, ML1619-E07 | C-56-PR-838-CI-1420: FS, C-56-PR-838-EI-2210: FS, ML1619-E07: FS | 2025-03-20 11:00 | 2025-04-11 13:00
C-56-PR-838-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.11 | Concrete Works for Access Platforms & Misc. Structural Foundations | C-56-PR-838-CI-1230, C-56-PR-838-CI-1410, HE-CS-0230, HM-CS-0050, HE-CS-0650, HM-CS-0040 | C-56-PR-838-CI-1230: FS, C-56-PR-838-CI-1410: FS, HE-CS-0230: FS, HM-CS-0050: FF, HE-CS-0650: FS, HM-CS-0040: SS | C-56-PR-838-CI-1500, ML1619-E07 | C-56-PR-838-CI-1500: FS, ML1619-E07: FS | 2025-04-11 13:00 | 2025-05-06 16:00
C-56-PR-838-CI-1510 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.12 | Concrete Works for Thrust Anchor Block | C-56-PR-838-CI-1240, HM-PL-940, HE-CS-1800 | C-56-PR-838-CI-1240: FS, HM-PL-940: FS, HE-CS-1800: FS | PRECOM-56-PR-1000 | PRECOM-56-PR-1000: FS | 2025-04-11 13:00 | 2025-09-03 11:00
C-56-PR-838-CI-1500 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.12 | Concrete Works for Impact Wall | C-56-PR-838-CI-1250, C-56-PR-838-CI-1420, HE-CS-1250 | C-56-PR-838-CI-1250: FS, C-56-PR-838-CI-1420: FS, HE-CS-1250: FS | PRECOM-56-PR-1000 | PRECOM-56-PR-1000: FS | 2025-05-07 08:00 | 2025-08-23 11:00
C-56-PR-838-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.14 | Electrical & Earthing Cable Trenching | C-56-PR-838-CI-1000, C-56-PR-838-CI-1060, HE-CS-0530 | C-56-PR-838-CI-1000: FS, C-56-PR-838-CI-1060: FS 9, HE-CS-0530: FS | C-56-PR-838-CI-1810, C-56-PR-838-EI-2000, C-4N-HG-TPR-CI-1800 | C-56-PR-838-CI-1810: FS, C-56-PR-838-EI-2000: FS, C-4N-HG-TPR-CI-1800: FS | 2025-04-22 13:00 | 2025-05-21 11:00
C-56-PR-838-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.14 | Instrument & Telecom Cable Trenching | C-56-PR-838-CI-1800 | C-56-PR-838-CI-1800: FS | C-56-PR-838-EI-2010 | C-56-PR-838-EI-2010: FS | 2025-05-21 11:00 | 2025-06-20 11:00
C-56-PR-838-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.15 | Back Filling for Electrical & Earthing Cable | C-56-PR-838-EI-2000, C-56-PR-838-CA-1000 | C-56-PR-838-EI-2000: FS, C-56-PR-838-CA-1000: FS | C-56-PR-838-CI-2600, PRECOM-56-PR-1000 | C-56-PR-838-CI-2600: FS, PRECOM-56-PR-1000: FS | 2025-07-23 11:00 | 2025-08-16 11:00
C-56-PR-838-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.15 | Back Filling for Instrument & Telecom Cable | C-56-PR-838-EI-2010, C-56-PR-838-TE-1410 | C-56-PR-838-EI-2010: FS, C-56-PR-838-TE-1410: FS | C-56-PR-838-CI-2600, PRECOM-56-PR-1000 | C-56-PR-838-CI-2600: FS, PRECOM-56-PR-1000: FS | 2025-08-01 11:00 | 2025-08-26 11:00
C-56-PR-838-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.16 | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PR-838-CI-2800, C-56-PR-838-CI-2810, C-56-PR-838-EI-2200, C-56-PR-838-EI-1810, C-56-PR-838-EI-2410, C-56-PR-838-EI-1020, C-56-PR-838-EI-1010, C-56-PR-838-CI-2000, C-56-PR-838-EI-2210, C-56-PR-838-CI-3000, C-56-PR-838-CI-3010, ML1059-B28, HE-CS-0290, C | C-56-PR-838-CI-2800: FS, C-56-PR-838-CI-2810: FS, C-56-PR-838-EI-2200: FS, C-56-PR-838-EI-1810: FS, C-56-PR-838-EI-2410: FS, C-56-PR-838-EI-1020: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-CI-2000: FS, C-56-PR-838-EI-2210: FS, C-56-PR-838-CI-3000: FS, C-56-P | PRECOM-56-PR-1000 | PRECOM-56-PR-1000: FS | 2025-08-26 11:00 | 2025-09-17 11:00
C-56-PR-838-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.17 | Pre-Fabrication & Installation of Pipe Supports | C-56-PR-838-CI-1600, HS-CN-0690, HE-CS-1490, HM-CS-0110, HE-CS-1430, HM-CS-0120 | C-56-PR-838-CI-1600: FS, HS-CN-0690: FS, HE-CS-1490: FS, HM-CS-0110: FS, HE-CS-1430: FS, HM-CS-0120: FS | C-56-PR-838-CI-3000, C-56-PR-838-EI-2210, C-56-PR-838-CI-2600 | C-56-PR-838-CI-3000: FS, C-56-PR-838-EI-2210: FS, C-56-PR-838-CI-2600: FS | 2025-03-20 11:00 | 2025-05-19 11:00
C-56-PR-838-EI-2210 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.31 | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-56-PR-838-CI-1410, C-56-PR-838-CI-2000 | C-56-PR-838-CI-1410: FS, C-56-PR-838-CI-2000: FS | C-56-PR-838-CI-3000, C-56-PR-838-EI-1810, C-56-PR-838-EI-2200, C-56-PR-838-CI-2600 | C-56-PR-838-CI-3000: FS, C-56-PR-838-EI-1810: FS, C-56-PR-838-EI-2200: FS, C-56-PR-838-CI-2600: FS | 2025-05-19 11:00 | 2025-06-14 11:00
C-56-PR-838-CI-3000 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.18 | Pre-Fabrication & Installation of Platforms & Crossovers | C-56-PR-838-CI-2000, C-56-PR-838-EI-2210, HS-CN-0690, HM-CS-0110 | C-56-PR-838-CI-2000: FS, C-56-PR-838-EI-2210: FS, HS-CN-0690: FS, HM-CS-0110: FS | C-56-PR-838-CI-3010, C-56-PR-838-CI-2600, PRECOM-56-PR-1000 | C-56-PR-838-CI-3010: FS, C-56-PR-838-CI-2600: FS, PRECOM-56-PR-1000: FS | 2025-06-14 11:00 | 2025-07-18 11:00
C-56-PR-838-CI-3010 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.1.18 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-56-PR-838-CI-3000 | C-56-PR-838-CI-3000: FS | C-56-PR-838-CI-2600, PRECOM-56-PR-1000 | C-56-PR-838-CI-2600: FS, PRECOM-56-PR-1000: FS | 2025-07-18 11:00 | 2025-08-12 11:00
C-56-PR-838-ME-1100 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.3.19 | Installation of Pig Receiver (838-V-601) 56" | C-56-PR-838-CI-1400, ML1519-D04, ML1015-B08, HM-ME-2390 | C-56-PR-838-CI-1400: FS, ML1519-D04: FS, ML1015-B08: FS, HM-ME-2390: FS | C-4N-H5-TPL-ME-1000, C-4N-HG-TPR-ME-1100, PRECOM-56-PR-1000, C-56-PR-838-ME-1200 | C-4N-H5-TPL-ME-1000: FS 35, C-4N-HG-TPR-ME-1100: FS, PRECOM-56-PR-1000: FS, C-56-PR-838-ME-1200: FS | 2025-03-13 07:00 | 2025-03-24 13:00
C-56-PR-838-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.4.22 | Piping Pre-Fabrication | ML1002, CTF-SO1050, HE-PR-0890, HE-PR-0290, ML1219-B19, HE-PI-1300, HE-PI-1240, ML1014-B10, HS-CN-0190, HM-PI-0040 | ML1002: FS, CTF-SO1050: FS, HE-PR-0890: FS, HE-PR-0290: FS, ML1219-B19: FS, HE-PI-1300: FS, HE-PI-1240: FS, ML1014-B10: FS, HS-CN-0190: FS, HM-PI-0040: FS | C-56-PR-838-PI-1200, C-52-PL-838-PI-1000, C-4N-HG-TPR-PI-1000 | C-56-PR-838-PI-1200: SS 26, C-52-PL-838-PI-1000: SS 21, C-4N-HG-TPR-PI-1000: FS | 2025-02-24 07:00 | 2025-04-17 13:00
C-56-PR-838-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.4.23 | Piping Erection | C-56-PR-838-PI-1000, ML1002, HM-PL-0740, HM-PL-0640, HE-PR-0890, HM-PL-0220, HE-PR-0290, ML1219-B19, HE-PI-1300, HE-PI-1240, HM-PL-0630, ML1014-B10, HS-CN-0190, HM-PI-0040, HM-PL-1510, HM-PL-1570 | C-56-PR-838-PI-1000: SS 26, ML1002: FS, HM-PL-0740: FS, HM-PL-0640: FS, HE-PR-0890: FS, HM-PL-0220: FS, HE-PR-0290: FS, ML1219-B19: FS, HE-PI-1300: FS, HE-PI-1240: FS, HM-PL-0630: FS, ML1014-B10: FS, HS-CN-0190: FS, HM-PI-0040: FS, HM-PL-1510: FS, HM-PL-15 | C-56-PR-838-PI-1400, C-4N-HG-TPR-PI-1200 | C-56-PR-838-PI-1400: SS 7, C-4N-HG-TPR-PI-1200: FS | 2025-04-04 13:00 | 2025-05-02 13:00
C-56-PR-838-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.4.24 | Field Joint Welding | C-56-PR-838-PI-1200, HE-PI-1300, ML1002, ML1219-B19, ML1014-B10, HS-CN-0190 | C-56-PR-838-PI-1200: SS 7, HE-PI-1300: FS, ML1002: FS, ML1219-B19: FS, ML1014-B10: FS, HS-CN-0190: FS | C-56-PR-838-PI-1410, C-4N-HG-TPR-PI-1400 | C-56-PR-838-PI-1410: SS 3, C-4N-HG-TPR-PI-1400: FS | 2025-04-12 13:00 | 2025-05-12 11:00
C-56-PR-838-PI-1410 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.4.24 | NDT & Coating for Field Joint Weld | C-56-PR-838-PI-1400 | C-56-PR-838-PI-1400: SS 3 | C-56-PR-838-PI-1600 | C-56-PR-838-PI-1600: FS | 2025-04-16 13:00 | 2025-05-15 11:00
C-56-PR-838-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.4.25 | Hydrotesting | C-56-PR-838-PI-1410, ML1219-B19, ML1014-B10 | C-56-PR-838-PI-1410: FS, ML1219-B19: FS, ML1014-B10: FS | C-56-PR-838-PI-1800 | C-56-PR-838-PI-1800: FS | 2025-05-15 11:00 | 2025-05-21 11:00
C-56-PR-838-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.4.26 | Installation of Valves/MOV/ROV | C-56-PR-838-PI-1600, HM-PL-0740, HM-PL-0640, HE-PR-0890, HM-PL-0220, HE-PR-0290, ML1219-B19, HE-PI-1240, HM-PL-0630, ML1014-B10, HM-PL-1510, HM-PL-1570, HM-ME-0680, HM-ME-2240 | C-56-PR-838-PI-1600: FS, HM-PL-0740: FS, HM-PL-0640: FS, HE-PR-0890: FS, HM-PL-0220: FS, HE-PR-0290: FS, ML1219-B19: FS, HE-PI-1240: FS, HM-PL-0630: FS, ML1014-B10: FS, HM-PL-1510: FS, HM-PL-1570: FS, HM-ME-0680: FS, HM-ME-2240: FS | C-56-PR-838-PI-2000 | C-56-PR-838-PI-2000: SS 4 | 2025-07-24 07:00 | 2025-07-29 17:00
C-56-PR-838-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.4.27 | Final Bolt Torquing/ Re-Instatement | C-56-PR-838-PI-1800, C-56-PR-838-ME-1200, HE-PI-1300, ML1002, HM-PL-0740, HM-PL-0640, HE-PR-0890, HM-PL-0220, HE-PR-0290, ML1219-B19, HE-PI-1240, HM-PL-0630, ML1014-B10, HS-CN-0190, HM-PL-1510, HM-PL-1570 | C-56-PR-838-PI-1800: SS 4, C-56-PR-838-ME-1200: FS, HE-PI-1300: FS, ML1002: FS, HM-PL-0740: FS, HM-PL-0640: FS, HE-PR-0890: FS, HM-PL-0220: FS, HE-PR-0290: FS, ML1219-B19: FS, HE-PI-1240: FS, HM-PL-0630: FS, ML1014-B10: FS, HS-CN-0190: FS, HM-PL-1510: FS, | C-56-PR-838-PL-1000, PRECOM-56-PR-1000 | C-56-PR-838-PL-1000: FF, PRECOM-56-PR-1000: FS | 2025-07-29 07:00 | 2025-07-31 17:00
C-56-PR-838-PL-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.5.34 | Installation of Isolation Joint | C-56-HC01-PL-ME-4810, C-56-PR-838-PI-2000, C-56-HC01-PL-ME-5010 | C-56-HC01-PL-ME-4810: FS 13, C-56-PR-838-PI-2000: FF, C-56-HC01-PL-ME-5010: FS 13 | C-56-PR-838-PL-1010, C-4N-HG-TPR-PL-1000 | C-56-PR-838-PL-1010: SS 1, C-4N-HG-TPR-PL-1000: FS | 2025-07-30 07:00 | 2025-07-31 17:00
C-56-PR-838-PL-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.5.34 | Field Joint Welding (Piping/Pipeline Section including IJ) | C-56-PR-838-PL-1000 | C-56-PR-838-PL-1000: SS 1 | C-56-PR-838-PL-1020, C-56-PR-838-ME-1400 | C-56-PR-838-PL-1020: SS 1, C-56-PR-838-ME-1400: SS | 2025-07-31 07:00 | 2025-08-05 17:00
C-56-PR-838-PL-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.5.34 | NDT for Weld Joint | C-56-PR-838-PL-1010, C-56-PR-838-ME-1400 | C-56-PR-838-PL-1010: SS 1, C-56-PR-838-ME-1400: FS | C-56-PR-838-PL-1030 | C-56-PR-838-PL-1030: FS | 2025-08-05 07:00 | 2025-08-09 17:00
C-56-PR-838-PL-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.5.34 | Ext. Coating for Weld Joint | C-56-PR-838-PL-1020 | C-56-PR-838-PL-1020: FS | PRECOM-56-PR-1000, CCM-PM4510, A3980 | PRECOM-56-PR-1000: FS, CCM-PM4510: FS, A3980: FS | 2025-08-11 07:00 | 2025-08-15 17:00
C-56-PR-838-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.29 | Electrical & Earthing Cable Laying | C-56-PR-838-CI-1800, HS-CN-0640, HE-EL-0830, HE-IC-0950, HE-IC-0830, HM-EL-0080, HE-EL-0590, HE-EL-1610, HE-IC-1010, HE-EL-0470, HM-EL-0520, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0 | C-56-PR-838-CI-1800: FS, HS-CN-0640: FS, HE-EL-0830: FS, HE-IC-0950: FS, HE-IC-0830: FS, HM-EL-0080: FS, HE-EL-0590: FS, HE-EL-1610: FS, HE-IC-1010: FS, HE-EL-0470: FS, HM-EL-0520: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0 | C-56-PR-838-EI-1400, C-56-PR-838-EI-2020, C-56-PR-838-CI-2800, C-52-PL-838-EI-2000, C-4N-HG-TPR-EI-2000, C-56-PR-838-EI-1800 | C-56-PR-838-EI-1400: SS 2, C-56-PR-838-EI-2020: FS, C-56-PR-838-CI-2800: FS, C-52-PL-838-EI-2000: FS 30, C-4N-HG-TPR-EI-2000: FS, C-56-PR-838-EI-1800: FS | 2025-05-21 11:00 | 2025-06-17 11:00
C-56-PR-838-EI-1400 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.28 | Deep Earth Well Drilling | C-56-PR-838-EI-2000, HM-EL-0080, HE-EL-1790, HE-EL-0640, HE-IC-0650, HM-ME-1590, HE-IC-0710, ML1032-B21, HE-IC-2570, HE-IC-1430, HE-EL-1010, HM-EL-0380, HM-EL-0520, HE-IC-1550, HE-EL-1670, HE-EL-0530, HE-IC-0010, HE-HS-0350, HM-IC-0040, HM-ME-1690, HE-IC-0 | C-56-PR-838-EI-2000: SS 2, HM-EL-0080: FS, HE-EL-1790: FS, HE-EL-0640: FS, HE-IC-0650: FS, HM-ME-1590: FF, HE-IC-0710: FS, ML1032-B21: FS, HE-IC-2570: FS, HE-IC-1430: FS, HE-EL-1010: FS, HM-EL-0380: FS, HM-EL-0520: FS, HE-IC-1550: FF, HE-EL-1670: FS, HE-EL | C-56-PR-838-EI-2050 | C-56-PR-838-EI-2050: FS | 2025-05-23 11:00 | 2025-05-30 11:00
C-56-PR-838-EI-2020 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.28 | Installation of Cable Trays | C-56-PR-838-EI-2000, HM-EL-0080, HE-EL-1790, HE-EL-0640, HE-IC-0650, HE-IC-0710, ML1032-B21, HE-IC-2570, HE-IC-1430, HE-EL-1010, HM-EL-0380, HM-EL-0520, HE-IC-1550, HE-EL-1670, HE-EL-0530, HE-IC-0010, HE-HS-0350, HM-IC-0040, HE-IC-0490, HE-IC-0770, HM-EL-0 | C-56-PR-838-EI-2000: FS, HM-EL-0080: FS, HE-EL-1790: FS, HE-EL-0640: FS, HE-IC-0650: FS, HE-IC-0710: FS, ML1032-B21: FS, HE-IC-2570: FS, HE-IC-1430: FS, HE-EL-1010: FS, HM-EL-0380: FS, HM-EL-0520: FS, HE-IC-1550: FF, HE-EL-1670: FS, HE-EL-0530: FS, HE-IC-0 | C-56-PR-838-EI-1800 | C-56-PR-838-EI-1800: FS | 2025-06-17 11:00 | 2025-06-24 11:00
C-56-PR-838-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.29 | Instrument Cable Laying | C-56-PR-838-CI-1810, HS-CN-0640, HE-EL-0830, HE-IC-0950, HE-IC-0830, HM-EL-0080, HE-EL-0590, HE-EL-1610, HE-IC-1010, HE-EL-0470, HM-EL-0520, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0 | C-56-PR-838-CI-1810: FS, HS-CN-0640: FS, HE-EL-0830: FS, HE-IC-0950: FS, HE-IC-0830: FS, HM-EL-0080: FS, HE-EL-0590: FS, HE-EL-1610: FS, HE-IC-1010: FS, HE-EL-0470: FS, HM-EL-0520: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0 | C-56-PR-838-EI-2030, C-56-PR-838-EI-2040, C-56-PR-838-CA-1000, C-56-PR-838-TE-1410, C-56-PR-838-CI-2810, C-4N-HG-TPR-EI-2010 | C-56-PR-838-EI-2030: FS, C-56-PR-838-EI-2040: FS, C-56-PR-838-CA-1000: FS, C-56-PR-838-TE-1410: FS, C-56-PR-838-CI-2810: FS, C-4N-HG-TPR-EI-2010: FS | 2025-06-20 11:00 | 2025-07-16 11:00
C-56-PR-838-EI-2030 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.28 | Instrument Tubing Works | C-56-PR-838-EI-2010, HM-EL-0080, HE-EL-1790, HE-EL-0640, HE-IC-0650, HE-IC-0710, ML1032-B21, HE-IC-2570, HE-IC-1430, HE-EL-1010, HM-EL-0380, HM-EL-0520, HE-IC-1550, HE-EL-1670, HE-EL-0530, HE-IC-0010, HE-HS-0350, HM-IC-0040, HE-IC-0490, HE-IC-0770, HM-EL-0 | C-56-PR-838-EI-2010: FS, HM-EL-0080: FS, HE-EL-1790: FS, HE-EL-0640: FS, HE-IC-0650: FS, HE-IC-0710: FS, ML1032-B21: FS, HE-IC-2570: FS, HE-IC-1430: FS, HE-EL-1010: FS, HM-EL-0380: FS, HM-EL-0520: FS, HE-IC-1550: FF, HE-EL-1670: FS, HE-EL-0530: FS, HE-IC-0 | C-56-PR-838-EI-2040 | C-56-PR-838-EI-2040: FS | 2025-07-16 11:00 | 2025-07-23 11:00
C-56-PR-838-EI-1810 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.28 | Installation of JB's | C-56-PR-838-EI-2210, HM-EL-0080, HE-EL-1790, HE-EL-0640, HE-IC-0650, HE-IC-0710, ML1032-B21, HE-IC-2570, HE-IC-1430, HE-EL-1010, HM-EL-0380, HM-EL-0520, HE-IC-1550, HE-EL-1670, HE-EL-0530, HE-IC-0010, HE-HS-0350, HM-IC-0040, HM-ME-1690, HE-IC-0490, HE-IC-0 | C-56-PR-838-EI-2210: FS, HM-EL-0080: FS, HE-EL-1790: FS, HE-EL-0640: FS, HE-IC-0650: FS, HE-IC-0710: FS, ML1032-B21: FS, HE-IC-2570: FS, HE-IC-1430: FS, HE-EL-1010: FS, HM-EL-0380: FS, HM-EL-0520: FS, HE-IC-1550: FF, HE-EL-1670: FS, HE-EL-0530: FS, HE-IC-0 | C-56-PR-838-EI-2050, C-56-PR-838-CI-2600 | C-56-PR-838-EI-2050: FS, C-56-PR-838-CI-2600: FS | 2025-06-14 11:00 | 2025-06-20 11:00
C-56-PR-838-EI-2200 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.31 | Installation of Field Instruments (Including Pig Signaller) | C-56-PR-838-EI-2210 | C-56-PR-838-EI-2210: FS | C-56-PR-838-EI-2410, C-56-PR-838-EI-2040, C-56-PR-838-CI-2600, ML1629-E08 | C-56-PR-838-EI-2410: FS 1, C-56-PR-838-EI-2040: FS, C-56-PR-838-CI-2600: FS, ML1629-E08: FS | 2025-06-14 11:00 | 2025-07-10 11:00
C-56-PR-838-EI-2410 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.31 | Installation of F&G Device | C-56-PR-838-EI-2200, HM-ME-2310, HM-ME-1490 | C-56-PR-838-EI-2200: FS 1, HM-ME-2310: FS, HM-ME-1490: FS | C-56-PR-838-EI-2040, C-56-PR-838-CI-2600, C-56-PR-838-EI-1600, C-56-PR-838-TE-1000 | C-56-PR-838-EI-2040: FS, C-56-PR-838-CI-2600: FS, C-56-PR-838-EI-1600: FS, C-56-PR-838-TE-1000: FS | 2025-07-11 11:00 | 2025-08-01 11:00
C-56-PR-838-EI-2040 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.29 | Loop Checking for Instruments | C-56-PR-838-EI-2010, C-56-PR-838-EI-2030, C-56-PR-838-EI-2200, C-56-PR-838-EI-2410, C-56-PR-838-EI-1600, HS-CN-0640, HE-EL-0830, HE-IC-0950, HE-IC-0830, HM-EL-0080, HE-EL-0590, HE-EL-1610, HE-IC-1010, HE-EL-0470, HM-EL-0520, HE-EL-1950, HE-IC-0230, HE-IC-0 | C-56-PR-838-EI-2010: FS, C-56-PR-838-EI-2030: FS, C-56-PR-838-EI-2200: FS, C-56-PR-838-EI-2410: FS, C-56-PR-838-EI-1600: FF, HS-CN-0640: FS, HE-EL-0830: FS, HE-IC-0950: FS, HE-IC-0830: FS, HM-EL-0080: FS, HE-EL-0590: FS, HE-EL-1610: FS, HE-IC-1010: FS, HE- | C-56-PR-838-EI-2050, PRECOM-56-PR-1000 | C-56-PR-838-EI-2050: FS, PRECOM-56-PR-1000: FS | 2025-08-01 11:00 | 2025-08-15 11:00
C-56-PR-838-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.29 | Glanding & Termination | C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2040, C-56-PR-838-EI-1800 | C-56-PR-838-EI-1400: FS, C-56-PR-838-EI-1810: FS, C-56-PR-838-EI-2040: FS, C-56-PR-838-EI-1800: FS | PRECOM-56-PR-1000, ML1629-E08 | PRECOM-56-PR-1000: FS, ML1629-E08: FS | 2025-08-15 11:00 | 2025-08-29 11:00
C-56-PR-838-CA-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.29 | CP Cable Laying | C-56-PR-838-EI-2010, HS-CN-0640, HE-EL-0830, HE-IC-0950, HE-IC-0830, HM-EL-0080, HE-EL-0590, HE-EL-1610, HE-IC-1010, HE-EL-0470, HM-EL-0520, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0 | C-56-PR-838-EI-2010: FS, HS-CN-0640: FS, HE-EL-0830: FS, HE-IC-0950: FS, HE-IC-0830: FS, HM-EL-0080: FS, HE-EL-0590: FS, HE-EL-1610: FS, HE-IC-1010: FS, HE-EL-0470: FS, HM-EL-0520: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0 | C-56-PR-838-EI-1010, C-56-PR-838-CI-2800, C-4N-HG-TPR-CA-1000 | C-56-PR-838-EI-1010: FS, C-56-PR-838-CI-2800: FS, C-4N-HG-TPR-CA-1000: FS | 2025-07-16 11:00 | 2025-07-23 11:00
C-56-PR-838-EI-1010 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.28 | Installation of CP Test Post | C-56-PR-838-CA-1000, HM-EL-0080, HE-EL-1790, HE-EL-0640, HE-IC-0650, HE-IC-0710, ML1032-B21, HE-IC-2570, HE-IC-1430, HE-EL-1010, HM-EL-0380, HM-EL-0520, HE-IC-1550, HE-EL-1670, HE-EL-0530, HE-IC-0010, HE-HS-0350, HM-IC-0040, HM-ME-1690, HE-IC-0490, HE-IC-0 | C-56-PR-838-CA-1000: FS, HM-EL-0080: FS, HE-EL-1790: FS, HE-EL-0640: FS, HE-IC-0650: FS, HE-IC-0710: FS, ML1032-B21: FS, HE-IC-2570: FS, HE-IC-1430: FS, HE-EL-1010: FS, HM-EL-0380: FS, HM-EL-0520: FS, HE-IC-1550: FF, HE-EL-1670: FS, HE-EL-0530: FS, HE-IC-0 | C-56-PR-838-EI-1020, C-56-PR-838-CI-2600 | C-56-PR-838-EI-1020: FS, C-56-PR-838-CI-2600: FS | 2025-07-23 11:00 | 2025-07-25 11:00
C-56-PR-838-EI-1020 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.28 | Installation of CP JB's | C-56-PR-838-EI-1010 | C-56-PR-838-EI-1010: FS | C-56-PR-838-CA-1030, C-56-PR-838-CI-2600 | C-56-PR-838-CA-1030: FS, C-56-PR-838-CI-2600: FS | 2025-07-25 11:00 | 2025-07-28 11:00
C-56-PR-838-CA-1030 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.29 | Glanding & Termination for CP S/m | C-56-PR-838-EI-1020, HS-CN-0640, HE-EL-0830, HE-IC-0950, HE-IC-0830, HM-EL-0080, HE-EL-0590, HE-EL-1610, HE-IC-1010, HE-EL-0470, HM-EL-0520, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0 | C-56-PR-838-EI-1020: FS, HS-CN-0640: FS, HE-EL-0830: FS, HE-IC-0950: FS, HE-IC-0830: FS, HM-EL-0080: FS, HE-EL-0590: FS, HE-EL-1610: FS, HE-IC-1010: FS, HE-EL-0470: FS, HM-EL-0520: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0 | C-4N-HG-TPR-CA-1030, PRECOM-56-PR-1000 | C-4N-HG-TPR-CA-1030: FS, PRECOM-56-PR-1000: FS | 2025-07-28 11:00 | 2025-07-30 11:00
C-56-PR-838-TE-1410 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.8.33 | FOC Laying | C-56-PR-838-EI-2010 | C-56-PR-838-EI-2010: FS | C-56-PR-838-TE-1420, C-56-PR-838-CI-2810, C-4N-HG-TPR-TE-1410 | C-56-PR-838-TE-1420: FS, C-56-PR-838-CI-2810: FS, C-4N-HG-TPR-TE-1410: FS | 2025-07-16 11:00 | 2025-08-01 11:00
C-56-PR-838-TE-1420 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.8.33 | FO Cable OTDR Testing & Splicing | C-56-PR-838-TE-1410, C-56-PR-838-TE-1600 | C-56-PR-838-TE-1410: FS, C-56-PR-838-TE-1600: FF | C-4N-HG-TPR-TE-1420, PRECOM-56-PR-1000 | C-4N-HG-TPR-TE-1420: FS, PRECOM-56-PR-1000: FS | 2025-08-22 11:00 | 2025-08-25 11:00
C-52-PR-839-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 | Site Survey, Preparation & Grading Works | HE-SS-0030, ML1002, HE-CS-0470, HE-CS-0170, ML1199-B24, CTF-1000, CTF-1010, C-PER-1650 | HE-SS-0030: FS, ML1002: FS, HE-CS-0470: FF 10, HE-CS-0170: FF, ML1199-B24: FS, CTF-1000: FF, CTF-1010: FF, C-PER-1650: FS 25 | C-52-PR-839-CI-1010, C-52-PR-839-CI-1050, C-52-ADDC-CI-1000 | C-52-PR-839-CI-1010: FS, C-52-PR-839-CI-1050: FS, C-52-ADDC-CI-1000: FS | 2025-01-09 07:00 | 2025-01-24 17:00
C-52-PR-839-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 | Earth Works for Equipment Foundations | C-52-PR-839-CI-1000, C-52-PR-839-CI-1050 | C-52-PR-839-CI-1000: FS, C-52-PR-839-CI-1050: SS | C-52-PR-839-CI-1020, C-52-PR-839-CI-1200 | C-52-PR-839-CI-1020: FS, C-52-PR-839-CI-1200: FS | 2025-01-25 07:00 | 2025-02-11 17:00
C-52-PR-839-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 | Earth Works for Pipe Support Foundations | C-52-PR-839-CI-1010 | C-52-PR-839-CI-1010: FS | C-52-PR-839-CI-1030, C-52-PR-839-CI-1210, C-52-PR-839-CI-1800 | C-52-PR-839-CI-1030: FS, C-52-PR-839-CI-1210: FS, C-52-PR-839-CI-1800: FS | 2025-02-12 07:00 | 2025-02-28 17:00
C-52-PR-839-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 | Earth Works for Field Instrument, JBs & Light Pole Foundations | C-52-PR-839-CI-1020 | C-52-PR-839-CI-1020: FS | C-52-PR-839-CI-1040, C-52-PR-839-CI-1220 | C-52-PR-839-CI-1040: FS, C-52-PR-839-CI-1220: FS | 2025-03-01 07:00 | 2025-03-22 09:00
C-52-PR-839-CI-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-PR-839-CI-1030 | C-52-PR-839-CI-1030: FS | C-52-PR-839-CI-1060, C-52-PR-839-CI-1230 | C-52-PR-839-CI-1060: FS, C-52-PR-839-CI-1230: FS | 2025-03-22 09:00 | 2025-04-12 13:00
C-52-PR-839-CI-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 | Earth Works for Impact Wall | C-52-PR-839-CI-1040 | C-52-PR-839-CI-1040: FS | C-52-PR-839-CI-1250, C-52-PR-839-CI-1070 | C-52-PR-839-CI-1250: FS, C-52-PR-839-CI-1070: FS | 2025-04-12 13:00 | 2025-04-22 13:00
C-52-PR-839-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 | Compaction & Testing for Equipment Foundations | C-52-PR-839-CI-1010 | C-52-PR-839-CI-1010: FS | C-52-PR-839-CI-1400 | C-52-PR-839-CI-1400: FS | 2025-02-12 07:00 | 2025-02-20 17:00
C-52-PR-839-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 | Compaction & Testing for Pipe Support Foundations | C-52-PR-839-CI-1020 | C-52-PR-839-CI-1020: FS | C-52-PR-839-CI-1600 | C-52-PR-839-CI-1600: FS | 2025-03-01 07:00 | 2025-03-12 13:00
C-52-PR-839-CI-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | C-52-PR-839-CI-1030 | C-52-PR-839-CI-1030: FS | C-52-PR-839-CI-1410 | C-52-PR-839-CI-1410: FS | 2025-03-22 09:00 | 2025-03-29 13:00
C-52-PR-839-CI-1230 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-52-PR-839-CI-1040 | C-52-PR-839-CI-1040: FS | C-52-PR-839-CI-1420 | C-52-PR-839-CI-1420: FS | 2025-04-12 13:00 | 2025-04-18 13:00
C-52-PR-839-CI-1250 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 | Compaction & Testing for Impact Wall | C-52-PR-839-CI-1060 | C-52-PR-839-CI-1060: FS | C-52-PR-839-CI-1500 | C-52-PR-839-CI-1500: FS | 2025-04-22 13:00 | 2025-04-28 13:00
C-52-PR-839-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 | Concrete Works for Equipment Foundations | C-52-PR-839-CI-1200, HE-CS-1310, HM-CS-0040, HE-CS-1070, HE-CS-1190, HE-CS-0230, HM-CS-0050, HE-CS-0650, ML1209-B27 | C-52-PR-839-CI-1200: FS, HE-CS-1310: FS, HM-CS-0040: FS, HE-CS-1070: FS, HE-CS-1190: FS, HE-CS-0230: FS, HM-CS-0050: FF, HE-CS-0650: FS, ML1209-B27: FS | C-52-PR-839-ME-1100, ML1739-E19 | C-52-PR-839-ME-1100: FS, ML1739-E19: FS | 2025-02-21 07:00 | 2025-03-22 09:00
C-52-PR-839-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.5 | Concrete Works for Pipe Support Foundations | C-52-PR-839-CI-1210, HM-CS-0040, HE-CS-1130, HE-CS-0230, HM-CS-0050, HE-CS-0650, ML1209-B27 | C-52-PR-839-CI-1210: FS, HM-CS-0040: FS, HE-CS-1130: FS, HE-CS-0230: FS, HM-CS-0050: FF, HE-CS-0650: FS, ML1209-B27: FS | C-52-PR-839-CI-1410, ML1739-E19, ML1839-E29 | C-52-PR-839-CI-1410: FS, ML1739-E19: FS, ML1839-E29: FS | 2025-03-13 07:00 | 2025-04-22 13:00
C-52-PR-839-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-52-PR-839-CI-1220, C-52-PR-839-CI-1600, HM-CS-0040, HE-CS-0230, HM-CS-0050, HE-CS-0650, ML1209-B27 | C-52-PR-839-CI-1220: FS, C-52-PR-839-CI-1600: FS, HM-CS-0040: FS, HE-CS-0230: FS, HM-CS-0050: FF, HE-CS-0650: FS, ML1209-B27: FS | C-52-PR-839-CI-1420, ML1739-E19 | C-52-PR-839-CI-1420: FS, ML1739-E19: FS | 2025-04-22 13:00 | 2025-05-09 11:00
C-52-PR-839-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 | Concrete Works for Access Platforms & Misc. Structural Foundations | C-52-PR-839-CI-1230, C-52-PR-839-CI-1410, HM-CS-0040, HE-CS-1370, HE-CS-0230, HM-CS-0050, HE-CS-0650, ML1209-B27 | C-52-PR-839-CI-1230: FS, C-52-PR-839-CI-1410: FS, HM-CS-0040: FS, HE-CS-1370: FS, HE-CS-0230: FS, HM-CS-0050: FF, HE-CS-0650: FS, ML1209-B27: FS | C-52-PR-839-CI-3000, ML1739-E19 | C-52-PR-839-CI-3000: FS, ML1739-E19: FS | 2025-05-09 11:00 | 2025-06-03 11:00
C-52-PR-839-CI-1500 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.4 | Concrete Works for Impact Wall | C-52-PR-839-CI-1250, C-52-PR-839-CI-1510, HM-CS-0040, HE-CS-0230, HM-CS-0050, HE-CS-0650, ML1209-B27, HE-CS-1250 | C-52-PR-839-CI-1250: FS, C-52-PR-839-CI-1510: FS, HM-CS-0040: FS, HE-CS-0230: FS, HM-CS-0050: FF, HE-CS-0650: FS, ML1209-B27: FS, HE-CS-1250: FS | C-52-PR-839-CI-2600, PRECOM-52-PR-1000 | C-52-PR-839-CI-2600: FF 3, PRECOM-52-PR-1000: FS | 2025-07-01 13:00 | 2025-08-22 13:00
C-52-PR-839-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.6 | Electrical & Earthing Cable Trenching | C-52-PR-839-CI-1020, HE-CS-0530 | C-52-PR-839-CI-1020: FS, HE-CS-0530: FS | C-52-PR-839-CI-1810, C-52-PR-839-EI-2000, C-52-PL-838-CI-1800 | C-52-PR-839-CI-1810: FS, C-52-PR-839-EI-2000: FS, C-52-PL-838-CI-1800: FS | 2025-03-01 07:00 | 2025-03-22 09:00
C-52-PR-839-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.6 | Instrument & Telecom Cable Trenching | C-52-PR-839-CI-1800, HE-CS-0530 | C-52-PR-839-CI-1800: FS, HE-CS-0530: FS | C-52-PR-839-EI-2010 | C-52-PR-839-EI-2010: FS | 2025-03-22 09:00 | 2025-04-12 13:00
C-52-PR-839-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.11 | Back Filling for Electrical & Earthing Cable | C-52-PR-839-EI-2000, C-52-PR-839-CA-1000 | C-52-PR-839-EI-2000: FS, C-52-PR-839-CA-1000: FS | C-52-PR-839-CI-2810, PRECOM-52-PR-1000 | C-52-PR-839-CI-2810: FS, PRECOM-52-PR-1000: FS | 2025-06-25 07:00 | 2025-07-04 17:00
C-52-PR-839-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.11 | Back Filling for Instrument & Telecom Cable | C-52-PR-839-CI-2800, C-52-PR-839-EI-2010, C-52-PR-839-TE-1410 | C-52-PR-839-CI-2800: FS, C-52-PR-839-EI-2010: FS, C-52-PR-839-TE-1410: FS | C-52-PR-839-CI-2600, PRECOM-52-PR-1000 | C-52-PR-839-CI-2600: FS, PRECOM-52-PR-1000: FS | 2025-07-12 07:00 | 2025-07-21 17:00
C-52-PR-839-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.13 | Paving of Interlock tiles & Kerb Stone Embankment | C-52-PR-839-CI-2810, C-52-PR-839-CI-1500, C-52-PR-839-CI-2220, HE-CS-0290, ML1059-B28 | C-52-PR-839-CI-2810: FS, C-52-PR-839-CI-1500: FF 3, C-52-PR-839-CI-2220: FS, HE-CS-0290: FS, ML1059-B28: FS | PRECOM-52-PR-1000, C-52-PR-839-CI-3200 | PRECOM-52-PR-1000: FS, C-52-PR-839-CI-3200: FS | 2025-08-14 13:00 | 2025-08-26 13:00
C-52-PR-839-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.7 | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0120, HE-CS-1430, HE-CS-1490, HS-CN-0690, HM-CS-0110 | HM-CS-0120: FF, HE-CS-1430: FS, HE-CS-1490: FS, HS-CN-0690: FS, HM-CS-0110: FS | C-52-PR-839-PI-1200, C-52-PR-839-CI-2400, ML1749-E20, ML1859-E31, ML1859-E31, C-52-PR-839-CI-3010 | C-52-PR-839-PI-1200: FS, C-52-PR-839-CI-2400: FS, ML1749-E20: FS, ML1859-E31: FS, ML1859-E31: FF, C-52-PR-839-CI-3010: FS | 2025-02-24 07:00 | 2025-04-07 13:00
C-52-PR-839-EI-2210 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.6.4 | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-PR-839-PI-1200 | C-52-PR-839-PI-1200: FF 14 | C-52-PR-839-EI-1800 | C-52-PR-839-EI-1800: FS | 2025-05-03 11:00 | 2025-05-29 09:00
C-52-PR-839-CI-3000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.8 | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-PR-839-CI-1420, HM-CS-0110, HS-CN-0690 | C-52-PR-839-CI-1420: FS, HM-CS-0110: FS, HS-CN-0690: FS | PRECOM-52-PR-1000, ML1749-E20, ML1859-E31 | PRECOM-52-PR-1000: FS, ML1749-E20: FS, ML1859-E31: FS | 2025-06-03 11:00 | 2025-06-21 11:00
C-52-PR-839-CI-3010 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.8 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HM-CS-0110, HS-CN-0690, C-52-PR-839-CI-2000 | HM-CS-0110: FS, HS-CN-0690: FS, C-52-PR-839-CI-2000: FS | PRECOM-52-PR-1000, ML1749-E20, ML1859-E31 | PRECOM-52-PR-1000: FS, ML1749-E20: FS, ML1859-E31: FS | 2025-04-07 13:00 | 2025-04-23 13:00
C-52-PR-839-ME-1100 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.3.2 | Installation of Pig Receiver (839-V-101) 52" | C-52-PR-839-CI-1400, HM-ME-0480, ML1015-B08, ML1519-D04 | C-52-PR-839-CI-1400: FS, HM-ME-0480: FS, ML1015-B08: FS, ML1519-D04: FS | C-52-PR-839-PI-1200, C-52-PR-839-CA-1030, C-52-PL-838-ME-1000, PRECOM-52-PR-1000, C-52-PR-839-ME-1200, ML1749-E20, ML1859-E31 | C-52-PR-839-PI-1200: FS 7, C-52-PR-839-CA-1030: FF 2, C-52-PL-838-ME-1000: FS 1, PRECOM-52-PR-1000: FS, C-52-PR-839-ME-1200: FS, ML1749-E20: FS, ML1859-E31: FS | 2025-03-22 09:00 | 2025-04-05 13:00
C-52-PR-839-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 | Piping Pre-Fabrication | ML1002, HM-PL-0640, HE-PI-1240, HS-CN-0190, HM-PL-0630, HM-PI-0040, ML1219-B19, ML1179-B11, HM-PL-0220, HE-PI-0440, HM-PL-0740, HE-PR-0890, HE-PI-1300, HE-PI-0700, HE-PR-0290, HM-PL-1510, HM-PL-1570 | ML1002: FS, HM-PL-0640: FS, HE-PI-1240: FS, HS-CN-0190: FS, HM-PL-0630: FS, HM-PI-0040: FS, ML1219-B19: FS, ML1179-B11: FS, HM-PL-0220: FS, HE-PI-0440: FS, HM-PL-0740: FS, HE-PR-0890: FS, HE-PI-1300: FS, HE-PI-0700: FS, HE-PR-0290: FS, HM-PL-1510: FS, HM-P | C-52-PR-839-PI-1200, C-36-KM-HT-PI-1000 | C-52-PR-839-PI-1200: FS, C-36-KM-HT-PI-1000: FS 30 | 2025-03-28 07:00 | 2025-04-25 11:00
C-52-PR-839-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 | Piping Erection | C-52-PR-839-PI-1000, C-52-PR-839-ME-1100, C-52-PR-839-CI-2000 | C-52-PR-839-PI-1000: FS, C-52-PR-839-ME-1100: FS 7, C-52-PR-839-CI-2000: FS | C-52-PR-839-PI-1400, C-52-PR-839-EI-2210, C-52-PR-839-PL-1000 | C-52-PR-839-PI-1400: SS 2, C-52-PR-839-EI-2210: FF 14, C-52-PR-839-PL-1000: FS | 2025-04-25 11:00 | 2025-05-13 09:00
C-52-PR-839-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 | Field Joint Welding | C-52-PR-839-PI-1200 | C-52-PR-839-PI-1200: SS 2 | C-52-PR-839-PI-1410 | C-52-PR-839-PI-1410: SS 3 | 2025-04-28 11:00 | 2025-05-13 09:00
C-52-PR-839-PI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 | NDT & Coating for Field Joint Weld | C-52-PR-839-PI-1400, ML1002, HM-PL-0640, HE-PI-1240, HS-CN-0190, HM-PI-0040, ML1219-B19, ML1179-B11, HM-PL-0220, HM-PL-0740, HE-PR-0890, HE-PI-1300, HE-PR-0290, HM-PL-1510, HM-PL-1570 | C-52-PR-839-PI-1400: SS 3, ML1002: FS, HM-PL-0640: FS, HE-PI-1240: FS, HS-CN-0190: FS, HM-PI-0040: FS, ML1219-B19: FS, ML1179-B11: FS, HM-PL-0220: FS, HM-PL-0740: FS, HE-PR-0890: FS, HE-PI-1300: FS, HE-PR-0290: FS, HM-PL-1510: FS, HM-PL-1570: FS | C-52-PR-839-PI-1600, ML1749-E20, ML1749-E20, ML1849-E30, ML1859-E31, ML1859-E31 | C-52-PR-839-PI-1600: FS, ML1749-E20: FS, ML1749-E20: FF, ML1849-E30: FS, ML1859-E31: FS, ML1859-E31: FF | 2025-05-01 11:00 | 2025-05-16 09:00
C-52-PR-839-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 | Hydrotesting | C-52-PR-839-PI-1410 | C-52-PR-839-PI-1410: FS | C-52-PR-839-PI-1800 | C-52-PR-839-PI-1800: FS | 2025-05-16 09:00 | 2025-05-22 09:00
C-52-PR-839-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 | Installation of Valves/MOV/ROV | C-52-PR-839-PI-1600, HM-ME-0580, HM-ME-2210, HM-ME-0680, HM-ME-2240 | C-52-PR-839-PI-1600: FS, HM-ME-0580: FS, HM-ME-2210: FS, HM-ME-0680: FS, HM-ME-2240: FS | C-52-PR-839-PI-2000 | C-52-PR-839-PI-2000: SS 4 | 2025-07-24 07:00 | 2025-07-29 17:00
C-52-PR-839-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 | Final Bolt Torquing/ Re-Instatement | C-52-PR-839-PI-1800, C-52-PR-839-ME-1200 | C-52-PR-839-PI-1800: SS 4, C-52-PR-839-ME-1200: FS | C-52-PR-839-EI-2200, PRECOM-52-PR-1000 | C-52-PR-839-EI-2200: FF 3, PRECOM-52-PR-1000: FS | 2025-07-29 07:00 | 2025-07-31 17:00
C-52-PR-839-PL-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.5.1 | Installation of Isolation Joint | C-52-PR-839-PI-1200 | C-52-PR-839-PI-1200: FS | C-52-PR-839-PL-1010 | C-52-PR-839-PL-1010: FS | 2025-05-13 09:00 | 2025-05-15 09:00
C-52-PR-839-PL-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.5.1 | Field Joint Welding (Piping/Pipeline Section including IJ) | C-52-PR-839-PL-1000 | C-52-PR-839-PL-1000: FS | C-52-PR-839-PL-1020 | C-52-PR-839-PL-1020: FS | 2025-05-15 09:00 | 2025-05-21 09:00
C-52-PR-839-PL-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.5.1 | NDT for Weld Joint | C-52-PR-839-PL-1010 | C-52-PR-839-PL-1010: FS | C-52-PR-839-PL-1030 | C-52-PR-839-PL-1030: FS | 2025-05-21 09:00 | 2025-05-27 09:00
C-52-PR-839-PL-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.5.1 | Ext. Coating for Weld Joint | C-52-PR-839-PL-1020 | C-52-PR-839-PL-1020: FS | PRECOM-52-PR-1000, CCM-PM4520, CCM-PM4530, A3980, CCM-PM4540 | PRECOM-52-PR-1000: FS, CCM-PM4520: FS, CCM-PM4530: FS, A3980: FS, CCM-PM4540: FS | 2025-05-27 09:00 | 2025-06-02 09:00
C-52-PR-839-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 | Electrical & Earthing Cable Laying | C-52-PR-839-CI-1800, HM-EL-0080, HM-EL-0520, HE-EL-0830, HE-IC-0950, HE-IC-0830, HE-EL-0470, HE-EL-0590, HE-EL-1610, HE-IC-1010, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-6 | C-52-PR-839-CI-1800: FS, HM-EL-0080: FS, HM-EL-0520: FS, HE-EL-0830: FS, HE-IC-0950: FS, HE-IC-0830: FS, HE-EL-0470: FS, HE-EL-0590: FS, HE-EL-1610: FS, HE-IC-1010: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0 | C-52-PR-839-EI-1400, C-52-PR-839-EI-2010, C-52-PR-839-EI-2020, C-52-PR-839-EI-1800, C-52-PR-839-EI-2050, C-52-PR-839-CA-1000, C-52-PR-839-CI-2800 | C-52-PR-839-EI-1400: FF, C-52-PR-839-EI-2010: FS, C-52-PR-839-EI-2020: FS, C-52-PR-839-EI-1800: FS, C-52-PR-839-EI-2050: FS, C-52-PR-839-CA-1000: FS, C-52-PR-839-CI-2800: FS | 2025-04-18 07:00 | 2025-04-26 17:00
C-52-PR-839-EI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 | Deep Earth Well Drilling | C-52-PR-839-EI-2000, HE-EL-0530, HM-ME-0790, HE-IC-0770, HM-IC-0040, HE-EL-0710, HE-EL-0290, HE-IC-1550, HE-EL-0650, HM-EL-0520, HM-ME-1590, HE-EL-0640, HE-IC-0530, HE-EL-1670, HM-EL-0380, HM-ME-0690, HM-EL-0080, HE-IC-1430, HM-ME-1690, HE-IC-0590, HE-IC-0 | C-52-PR-839-EI-2000: FF, HE-EL-0530: FS, HM-ME-0790: FS, HE-IC-0770: FS, HM-IC-0040: FS, HE-EL-0710: FS, HE-EL-0290: FS, HE-IC-1550: FF, HE-EL-0650: FS, HM-EL-0520: FS, HM-ME-1590: FF, HE-EL-0640: FS, HE-IC-0530: FS, HE-EL-1670: FS, HM-EL-0380: FS, HM-ME-0 | C-52-PR-839-EI-2050, PRECOM-52-PR-1000, ML1749-E20, ML1859-E31 | C-52-PR-839-EI-2050: FS, PRECOM-52-PR-1000: FS, ML1749-E20: FS, ML1859-E31: FS | 2025-06-19 07:00 | 2025-06-24 17:00
C-52-PR-839-EI-2020 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 | Installation of Cable Trays | C-52-PR-839-EI-2000 | C-52-PR-839-EI-2000: FS | C-52-PR-839-EI-2030 | C-52-PR-839-EI-2030: FS | 2025-04-28 07:00 | 2025-05-03 17:00
C-52-PR-839-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 | Instrument Cable Laying | C-52-PR-839-EI-2000, C-52-PR-839-CI-1810 | C-52-PR-839-EI-2000: FS, C-52-PR-839-CI-1810: FS | C-52-PR-839-EI-2030, C-52-PR-839-TE-1410, C-52-PR-839-CI-2810 | C-52-PR-839-EI-2030: FS, C-52-PR-839-TE-1410: FS, C-52-PR-839-CI-2810: FS | 2025-04-28 07:00 | 2025-05-07 12:00
C-52-PR-839-EI-2030 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 | Instrument Tubing Works | C-52-PR-839-EI-2020, C-52-PR-839-EI-2010 | C-52-PR-839-EI-2020: FS, C-52-PR-839-EI-2010: FS | C-52-PR-839-EI-2200 | C-52-PR-839-EI-2200: FS | 2025-05-07 12:00 | 2025-05-14 15:00
C-52-PR-839-EI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 | Installation of Light Pole, Lighting & Fixtures | C-52-PR-839-EI-2210, C-52-PR-839-EI-2000, HE-EL-0530, HM-ME-0790, HE-IC-0770, HM-IC-0040, HE-EL-0710, HE-EL-0290, HE-IC-1550, HE-EL-0650, HM-EL-0520, HM-ME-1590, HE-EL-0640, HE-IC-0530, HE-EL-1670, HM-EL-0380, HM-ME-0690, HM-EL-0080, HE-IC-1430, HM-ME-1690 | C-52-PR-839-EI-2210: FS, C-52-PR-839-EI-2000: FS, HE-EL-0530: FS, HM-ME-0790: FS, HE-IC-0770: FS, HM-IC-0040: FS, HE-EL-0710: FS, HE-EL-0290: FS, HE-IC-1550: FF, HE-EL-0650: FS, HM-EL-0520: FS, HM-ME-1590: FF, HE-EL-0640: FS, HE-IC-0530: FS, HE-EL-1670: FS | C-52-PR-839-EI-1810, C-52-PR-839-EI-2050 | C-52-PR-839-EI-1810: FS, C-52-PR-839-EI-2050: FS | 2025-06-18 07:00 | 2025-06-24 17:00
C-52-PR-839-EI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 | Installation of JB's | C-52-PR-839-EI-1800 | C-52-PR-839-EI-1800: FS | C-52-PR-839-EI-2050 | C-52-PR-839-EI-2050: FS | 2025-06-25 07:00 | 2025-07-01 17:00
C-52-PR-839-EI-2200 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.6.4 | Installation of Field Instruments (Including Pig Signaller) | C-52-PR-839-PI-2000, C-52-PR-839-EI-2030 | C-52-PR-839-PI-2000: FF 3, C-52-PR-839-EI-2030: FS | C-52-PR-839-EI-2410 | C-52-PR-839-EI-2410: FS 30 | 2025-07-24 07:00 | 2025-08-04 17:00
C-52-PR-839-EI-2410 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.6.5 | Installation of F&G Device | C-52-PR-839-EI-2200, HM-ME-2310, HM-ME-1490 | C-52-PR-839-EI-2200: FS 30, HM-ME-2310: FS, HM-ME-1490: FS | C-52-PR-839-EI-2040, C-52-PR-839-ME-1600 | C-52-PR-839-EI-2040: FS, C-52-PR-839-ME-1600: FS | 2025-09-10 07:00 | 2025-09-15 17:00
C-52-PR-839-EI-2040 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 | Loop Checking for Instruments | C-52-PR-839-EI-2410 | C-52-PR-839-EI-2410: FS | C-52-PR-839-EI-2050, PRECOM-52-PR-1000 | C-52-PR-839-EI-2050: FF, PRECOM-52-PR-1000: FS | 2025-09-16 07:00 | 2025-09-24 17:00
C-52-PR-839-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 | Glanding & Termination | C-52-PR-839-EI-2000, C-52-PR-839-EI-1400, C-52-PR-839-EI-1800, C-52-PR-839-EI-1810, C-52-PR-839-EI-2040, C-52-PR-839-ME-1600 | C-52-PR-839-EI-2000: FS, C-52-PR-839-EI-1400: FS, C-52-PR-839-EI-1800: FS, C-52-PR-839-EI-1810: FS, C-52-PR-839-EI-2040: FF, C-52-PR-839-ME-1600: FS | PRECOM-52-PR-1000, ML1749-E20, ML1859-E31 | PRECOM-52-PR-1000: FS, ML1749-E20: FS, ML1859-E31: FS | 2025-09-20 07:00 | 2025-10-01 17:00
C-52-PR-839-CA-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 | CP Cable Laying | C-52-PR-839-EI-2000, HE-EL-0530, HM-ME-0790, HE-IC-0770, HM-IC-0040, HE-EL-0710, HE-EL-0290, HE-IC-1550, HE-EL-0650, HM-EL-0520, HE-EL-0640, HE-IC-0530, HE-EL-1670, HM-EL-0380, HM-ME-0690, HM-EL-0080, HE-IC-1430, HM-ME-1690, HE-IC-0590, HE-IC-0010, HE-EL-1 | C-52-PR-839-EI-2000: FS, HE-EL-0530: FF, HM-ME-0790: FF, HE-IC-0770: FF, HM-IC-0040: FF, HE-EL-0710: FF, HE-EL-0290: FF, HE-IC-1550: FF, HE-EL-0650: FF, HM-EL-0520: FF, HE-EL-0640: FF, HE-IC-0530: FF, HE-EL-1670: FF, HM-EL-0380: FF, HM-ME-0690: FF, HM-EL-0 | C-52-PR-839-CA-1010, C-52-PR-839-CI-2800 | C-52-PR-839-CA-1010: FS, C-52-PR-839-CI-2800: FS | 2025-06-19 07:00 | 2025-06-24 17:00
C-52-PR-839-CA-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 | Installation of CP Test Post | C-52-PR-839-CA-1000 | C-52-PR-839-CA-1000: FS | C-52-PR-839-CA-1020 | C-52-PR-839-CA-1020: FS | 2025-06-25 07:00 | 2025-07-01 17:00
C-52-PR-839-CA-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 | Installation of CP JB's | C-52-PR-839-CA-1010 | C-52-PR-839-CA-1010: FS | C-52-PR-839-CA-1030 | C-52-PR-839-CA-1030: FS | 2025-07-02 07:00 | 2025-07-07 17:00
C-52-PR-839-CA-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 | Glanding & Termination for CP S/m | C-52-PR-839-CA-1020, C-52-PR-839-ME-1100 | C-52-PR-839-CA-1020: FS, C-52-PR-839-ME-1100: FF 2 | PRECOM-52-PR-1000 | PRECOM-52-PR-1000: FS | 2025-07-08 07:00 | 2025-07-10 17:00
C-52-PR-839-TE-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 | FOC Laying | C-52-PR-839-EI-2010, HE-EL-0530, HM-ME-0790, HE-IC-0770, HM-IC-0040, HE-EL-0710, HE-EL-0290, HE-IC-1550, HE-EL-0650, HM-EL-0520, HM-ME-1590, HE-EL-0640, HE-IC-0530, HE-EL-1670, HM-EL-0380, HM-ME-0690, HM-EL-0080, HE-IC-1430, HM-ME-1690, HE-IC-0590, HE-IC-0 | C-52-PR-839-EI-2010: FS, HE-EL-0530: FS, HM-ME-0790: FS, HE-IC-0770: FS, HM-IC-0040: FS, HE-EL-0710: FS, HE-EL-0290: FS, HE-IC-1550: FS, HE-EL-0650: FS, HM-EL-0520: FS, HM-ME-1590: FS, HE-EL-0640: FS, HE-IC-0530: FS, HE-EL-1670: FS, HM-EL-0380: FS, HM-ME-0 | C-52-PR-839-TE-1600, C-52-PR-839-CI-2810 | C-52-PR-839-TE-1600: FS, C-52-PR-839-CI-2810: FS | 2025-06-25 07:00 | 2025-07-11 17:00
C-52-PR-839-TE-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 | Installation of CCTV System | C-52-PR-839-TE-1410 | C-52-PR-839-TE-1410: FS | C-52-PR-839-TE-1420 | C-52-PR-839-TE-1420: FS | 2025-07-12 07:00 | 2025-07-18 17:00
C-52-OHPL-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.4.22.1.1 | Concrete Works (Foundations for Equipment & Pipe Supports) | C-52-EB1-CI-1000 | C-52-EB1-CI-1000: FS 24 | C-52-OHPL-CI-1200 | C-52-OHPL-CI-1200: FS 10 | 2025-02-18 07:00 | 2025-03-24 13:00
C-52-OHPL-EL-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.4.22.2.1 | OHPL Installation Works-Tower/Post installation (Subcontract) | C-52-OHPL-CI-1200, HS-CN-0640 | C-52-OHPL-CI-1200: FS 30, HS-CN-0640: FS | C-52-OHPL-EL-1200 | C-52-OHPL-EL-1200: FS | 2025-06-09 11:00 | 2025-08-02 11:00
C-52-OHPL-EL-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.4.4.22.2.2 | OHPL Installation Works - Power Line installation(Subcontract) | C-52-OHPL-EL-1000 | C-52-OHPL-EL-1000: FS | C-52-OHPL-EL-1400 | C-52-OHPL-EL-1400: FS | 2025-08-02 11:00 | 2025-08-30 11:00
C-52-OHPL-EL-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.4.4.22.2.3 | Transformer / Directly Buried MV Cables (including testing) | C-52-OHPL-EL-1200, C-52-EB1-EI-1210, HS-CN-0440, HM-ME-0990 | C-52-OHPL-EL-1200: FS, C-52-EB1-EI-1210: SS 1, HS-CN-0440: FS, HM-ME-0990: FS | C-52-OHPL-EL-2000, C-52-OHPL-EL-2000, PRECOM-52-EB1-1000, CCM-PM4520, CCM-PM4530, CCM-PM4540 | C-52-OHPL-EL-2000: FS, C-52-OHPL-EL-2000: FF, PRECOM-52-EB1-1000: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-08-30 11:00 | 2025-09-19 11:00
C-52-OHPL-EL-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.4.22.3.1 | Shutdown Connection of OHL & Cable Testing | C-52-OHPL-EL-1400, C-52-OHPL-EL-1400, HM-ME-0990, C-COM-890, HS-CN-0440 | C-52-OHPL-EL-1400: FS, C-52-OHPL-EL-1400: FF, HM-ME-0990: FS, C-COM-890: FS, HS-CN-0440: FS | C-52-OHPL-CI-1400, PRECOM-52-EB1-1000, CCM-PM4520, CCM-PM4530, CCM-PM4540 | C-52-OHPL-CI-1400: FS, PRECOM-52-EB1-1000: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-09-19 11:00 | 2025-09-23 11:00
C-52-ADDC-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.5.22.1 | Site Survey, Preparation & Grading Works | C-52-PR-839-CI-1000 | C-52-PR-839-CI-1000: FS | C-52-ADDC-CI-1010 | C-52-ADDC-CI-1010: FS | 2025-01-25 07:00 | 2025-01-28 13:00
C-52-ADDC-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.4.5.22.1 | Earth Works for Ground Level | C-52-ADDC-CI-1000 | C-52-ADDC-CI-1000: FS | C-52-ADDC-CI-1020 | C-52-ADDC-CI-1020: FS | 2025-01-28 13:00 | 2025-02-14 13:00
C-52-ADDC-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.4.5.22.1 | Compaction & Testing Works for Ground Level | C-52-ADDC-CI-1010 | C-52-ADDC-CI-1010: FS | C-52-ADDC-CI-1200 | C-52-ADDC-CI-1200: FS | 2025-02-14 13:00 | 2025-02-20 13:00
C-52-ADDC-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.4.5.22.2 | Civil Structure/ Flooring Works | C-52-ADDC-CI-1020 | C-52-ADDC-CI-1020: FS | C-52-ADDC-CI-1400 | C-52-ADDC-CI-1400: FS | 2025-02-20 13:00 | 2025-03-19 13:00
C-52-ADDC-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.4.5.22.3 | Roofing Works | C-52-ADDC-CI-1200 | C-52-ADDC-CI-1200: FS | C-52-ADDC-CI-1600 | C-52-ADDC-CI-1600: FS | 2025-03-20 07:00 | 2025-04-18 09:00
C-52-ADDC-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.4.5.22.4 | Finishing Works for Shelter | C-52-ADDC-CI-1400 | C-52-ADDC-CI-1400: FS | C-52-ADDC-EL-1000, PRECOM-52-EB1-1000 | C-52-ADDC-EL-1000: FS, PRECOM-52-EB1-1000: FS | 2025-04-18 09:00 | 2025-05-12 17:00
C-52-ADDC-EL-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.5.22.5 | Transformer/ Switch Gear Installation | C-52-ADDC-CI-1600 | C-52-ADDC-CI-1600: FS | C-52-ADDC-EL-1200, PRECOM-52-EB1-1000 | C-52-ADDC-EL-1200: FS, PRECOM-52-EB1-1000: FS | 2025-05-13 07:00 | 2025-06-04 17:00
C-52-ADDC-EL-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.4.5.22.6 | Cable Laying, Glanding, Termination & Hook-Up | C-52-ADDC-EL-1000 | C-52-ADDC-EL-1000: FS | PRECOM-52-EB1-1000 | PRECOM-52-EB1-1000: FS | 2025-06-07 07:00 | 2025-07-12 17:00
C-52-EB1-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 | Site Survey, Preparation & Grading Works | HE-SS-0030, ML1002, HE-CS-0470, CTF-1000, HE-CS-0170, ML1199-B24, CTF-1010, C-PER-1650 | HE-SS-0030: SS, ML1002: FS, HE-CS-0470: FS, CTF-1000: FS, HE-CS-0170: FS, ML1199-B24: FS, CTF-1010: FS, C-PER-1650: FS 25 | C-52-EB1-CI-1010, C-52-OHPL-CI-1000, C-36-KM-HT-CI-1000 | C-52-EB1-CI-1010: FS, C-52-OHPL-CI-1000: FS 24, C-36-KM-HT-CI-1000: FS | 2025-01-09 07:00 | 2025-01-20 17:00
C-52-EB1-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 | Earth Works for Ground Level | C-52-EB1-CI-1000 | C-52-EB1-CI-1000: FS | C-52-EB1-CI-1020 | C-52-EB1-CI-1020: SS 5 | 2025-01-21 07:00 | 2025-02-13 17:00
C-52-EB1-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 | Compaction & Testing for Ground Level | C-52-EB1-CI-1010 | C-52-EB1-CI-1010: SS 5 | C-52-EB1-CI-1200, ML1839-E29 | C-52-EB1-CI-1200: SS 14, ML1839-E29: FS | 2025-01-27 07:00 | 2025-02-19 17:00
C-52-EB1-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.1.2 | Building Foundation Works (for Substructure) | C-52-EB1-CI-1020, ML1209-B27 | C-52-EB1-CI-1020: SS 14, ML1209-B27: FS | C-52-EB1-CI-1400, ML1839-E29 | C-52-EB1-CI-1400: FS, ML1839-E29: FS | 2025-02-12 07:00 | 2025-03-20 11:00
C-52-EB1-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.1.3 | Concrete Superstructure Works | C-52-EB1-CI-1200, HE-CS-0230, ML1209-B27, HM-CS-0040 | C-52-EB1-CI-1200: FS, HE-CS-0230: FS, ML1209-B27: FS, HM-CS-0040: FS | C-52-EB1-CI-1600, ML1839-E29 | C-52-EB1-CI-1600: FS, ML1839-E29: FS | 2025-03-20 11:00 | 2025-04-21 13:00
C-52-EB1-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.1.4 | Masonry Works - Internal | C-52-EB1-CI-1400 | C-52-EB1-CI-1400: FS | C-52-EB1-CI-1610, C-52-EB1-CI-1810, C-52-EB1-ME-1000 | C-52-EB1-CI-1610: FS, C-52-EB1-CI-1810: FS, C-52-EB1-ME-1000: SS | 2025-04-21 13:00 | 2025-05-16 11:00
C-52-EB1-CI-1610 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.1.4 | Masonry Works - External | C-52-EB1-CI-1600 | C-52-EB1-CI-1600: FS | C-52-EB1-CI-1800 | C-52-EB1-CI-1800: FS | 2025-05-16 11:00 | 2025-06-02 11:00
C-52-EB1-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.1.5 | External Finishing Works | C-52-EB1-CI-1610 | C-52-EB1-CI-1610: FS | C-52-EB1-CI-2000, PRECOM-52-EB1-1000 | C-52-EB1-CI-2000: FS, PRECOM-52-EB1-1000: FS | 2025-06-02 11:00 | 2025-06-16 11:00
C-52-EB1-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.1.5 | Internal Finishing Works | C-52-EB1-CI-1600, C-52-EB1-ME-1010 | C-52-EB1-CI-1600: FS, C-52-EB1-ME-1010: FF | C-52-EB1-CI-2000, C-52-EB1-EI-1000, PRECOM-52-EB1-1000 | C-52-EB1-CI-2000: FS, C-52-EB1-EI-1000: FS, PRECOM-52-EB1-1000: FS | 2025-05-24 11:00 | 2025-06-12 11:00
C-52-EB1-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.1.6 | Steel Structural Works | C-52-EB1-CI-1810, C-52-EB1-CI-1800, HM-CS-0110 | C-52-EB1-CI-1810: FS, C-52-EB1-CI-1800: FS, HM-CS-0110: FS | C-52-EB1-CI-2010, PRECOM-52-EB1-1000 | C-52-EB1-CI-2010: FS, PRECOM-52-EB1-1000: FS | 2025-06-16 11:00 | 2025-07-03 11:00
C-52-EB1-CI-2010 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.1.7 | Paving Works | C-52-EB1-CI-2000, HE-CS-0290, ML1059-B28 | C-52-EB1-CI-2000: FS, HE-CS-0290: FS, ML1059-B28: FS | PRECOM-52-EB1-1000 | PRECOM-52-EB1-1000: FS | 2025-07-03 11:00 | 2025-07-28 11:00
C-52-EB1-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.2.1 | Plumbing Works | C-52-EB1-CI-1600, HS-CN-0640, HS-CN-0590, HM-ME-1790, ML1015-B08, HM-ME-1830 | C-52-EB1-CI-1600: SS, HS-CN-0640: FS, HS-CN-0590: FS, HM-ME-1790: FS, ML1015-B08: FS, HM-ME-1830: FS | C-52-EB1-ME-1010, PRECOM-52-EB1-1000 | C-52-EB1-ME-1010: FS, PRECOM-52-EB1-1000: FS | 2025-04-21 13:00 | 2025-05-16 11:00
C-52-EB1-ME-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.2.1 | HVAC Works | C-52-EB1-ME-1000 | C-52-EB1-ME-1000: FS | C-52-EB1-CI-1810, PRECOM-52-EB1-1000, C-52-EB1-ME-1200 | C-52-EB1-CI-1810: FF, PRECOM-52-EB1-1000: FS, C-52-EB1-ME-1200: FS | 2025-05-16 11:00 | 2025-06-12 11:00
C-52-EB1-EI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 | Installation of Power Distribution System | C-52-EB1-CI-1810, HE-IC-0490, HE-IC-0770, HE-EL-1730, HE-IC-0710, HE-IC-0650, HM-ME-0890, HE-IC-0530, HE-IC-0010, HM-EL-0080, HM-EL-0480, HE-IC-0590, HM-EL-0380, HE-EL-1790, HE-EL-1670, HE-EL-0530, HM-EL-0520, HM-ME-1590, HM-EL-0280, HE-PR-0110, HM-ME-2330 | C-52-EB1-CI-1810: FS, HE-IC-0490: FF, HE-IC-0770: FF, HE-EL-1730: FS, HE-IC-0710: FF, HE-IC-0650: FF, HM-ME-0890: FS, HE-IC-0530: FF, HE-IC-0010: FF, HM-EL-0080: FF, HM-EL-0480: FS, HE-IC-0590: FF, HM-EL-0380: FS, HE-EL-1790: FS, HE-EL-1670: FS, HE-EL-0530 | C-52-EB1-EI-1400 | C-52-EB1-EI-1400: FS | 2025-06-12 11:00 | 2025-06-18 11:00
C-52-EB1-EI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.3.5 | Lighting & Fixtures | C-52-EB1-EI-1000 | C-52-EB1-EI-1000: FS | C-52-EB1-EI-2000 | C-52-EB1-EI-2000: FS | 2025-06-18 11:00 | 2025-07-05 11:00
C-52-EB1-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.3.2 | Installation of HSSD System | C-52-EB1-EI-1400, C-52-EB1-ME-1200 | C-52-EB1-EI-1400: FS, C-52-EB1-ME-1200: FS | C-52-EB1-EI-2200, C-52-EB1-TE-1000 | C-52-EB1-EI-2200: FS, C-52-EB1-TE-1000: FS | 2025-07-15 11:00 | 2025-07-29 11:00
C-52-EB1-EI-2200 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.3.3 | Installation of RTU System | C-52-EB1-EI-2000 | C-52-EB1-EI-2000: FS | C-52-EB1-EI-1200 | C-52-EB1-EI-1200: FS | 2025-07-29 11:00 | 2025-08-05 11:00
C-52-EB1-EI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.3.4 | Custody Metering Panel Installation | C-52-EB1-EI-2200 | C-52-EB1-EI-2200: FS | C-52-EB1-EI-1210 | C-52-EB1-EI-1210: FS | 2025-08-05 11:00 | 2025-08-12 11:00
C-52-EB1-EI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 | E&I Cable Laying | C-52-EB1-EI-1200, HM-EL-0520, HE-EL-0590, HM-EL-0080, HE-IC-0830, HE-IC-1010, HE-EL-1610, HE-IC-0950, HE-EL-0830, HE-EL-0470, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-630 | C-52-EB1-EI-1200: FS, HM-EL-0520: FS, HE-EL-0590: FS, HM-EL-0080: FS, HE-IC-0830: FS, HE-IC-1010: FS, HE-EL-1610: FS, HE-IC-0950: FS, HE-EL-0830: FS, HE-EL-0470: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0210 | C-52-EB1-EI-1600, C-52-OHPL-EL-1400 | C-52-EB1-EI-1600: SS, C-52-OHPL-EL-1400: SS 1 | 2025-08-12 11:00 | 2025-09-06 11:00
C-52-EB1-EI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.3.7 | Earthing & Lightning Protection system | C-52-EB1-EI-1210 | C-52-EB1-EI-1210: SS | C-52-EB1-EI-2400 | C-52-EB1-EI-2400: FS | 2025-08-12 11:00 | 2025-08-28 11:00
C-52-EB1-EI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.3.8 | UPS (10KVA) Installation | HM-ME-2060, C-52-EB1-EI-1600 | HM-ME-2060: FS, C-52-EB1-EI-1600: FS | C-52-EB1-EI-1800, ML1749-E20, ML1859-E31 | C-52-EB1-EI-1800: FS, ML1749-E20: FS, ML1859-E31: FS | 2025-08-28 11:00 | 2025-09-10 11:00
C-52-EB1-EI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.3.9 | Installation F&G System | C-52-EB1-EI-2400 | C-52-EB1-EI-2400: FS | C-52-EB1-EI-1220 | C-52-EB1-EI-1220: FS | 2025-09-10 11:00 | 2025-09-19 11:00
C-52-EB1-EI-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 | MCT Installation | C-52-EB1-EI-1800, HM-EL-0520, HE-EL-0590, HM-EL-0080, HE-IC-0830, HE-IC-1010, HE-EL-1610, HE-IC-0950, HE-EL-0830, HE-EL-0470, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-630 | C-52-EB1-EI-1800: FS, HM-EL-0520: FS, HE-EL-0590: FS, HM-EL-0080: FS, HE-IC-0830: FS, HE-IC-1010: FS, HE-EL-1610: FS, HE-IC-0950: FS, HE-EL-0830: FS, HE-EL-0470: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0210 | C-52-EB1-EI-1230 | C-52-EB1-EI-1230: FS | 2025-09-19 11:00 | 2025-09-29 11:00
C-52-EB1-EI-1230 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 | Glanding & Termination | C-52-EB1-EI-1220 | C-52-EB1-EI-1220: FS | PRECOM-52-EB1-1000, ML1749-E20, ML1859-E31 | PRECOM-52-EB1-1000: FS, ML1749-E20: FS, ML1859-E31: FS | 2025-09-29 11:00 | 2025-10-13 11:00
C-52-EB1-TE-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.4.1 | SDH Cabinet Installation | C-52-EB1-EI-2000, ML1033-B22, HM-TL-0040, HE-TL-0830, HM-ME-1390, HS-CN-0290, HE-TL-0470, HE-TL-0770, HE-TL-0710, HM-ME-2290 | C-52-EB1-EI-2000: FS, ML1033-B22: FS, HM-TL-0040: FS, HE-TL-0830: FS, HM-ME-1390: FS, HS-CN-0290: FS, HE-TL-0470: FS, HE-TL-0770: FS, HE-TL-0710: FS, HM-ME-2290: FS | C-52-EB1-TE-1600 | C-52-EB1-TE-1600: FS | 2025-07-29 11:00 | 2025-08-07 11:00
C-52-EB1-TE-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.4.3 | CCTV Installation | C-52-EB1-TE-1000 | C-52-EB1-TE-1000: FS | C-52-EB1-TE-1400, CCM-PM4520, CCM-PM4530, CCM-PM4540 | C-52-EB1-TE-1400: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-08-07 11:00 | 2025-08-14 11:00
C-52-EB1-TE-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.4.2 | Telecom System (Including subcontract for FOC Splicing / Termination / Testing) | C-52-EB1-TE-1600 | C-52-EB1-TE-1600: FS | C-52-EB1-TE-1610, PRECOM-52-EB1-1000 | C-52-EB1-TE-1610: FS, PRECOM-52-EB1-1000: FS | 2025-08-14 11:00 | 2025-08-26 11:00
C-52-EB1-TE-1610 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.4.3 | Security System (Including subcontract for FOC Splicing / Termination / Testing ) | C-52-EB1-TE-1400 | C-52-EB1-TE-1400: FS | PRECOM-52-EB1-1000, CCM-PM4520, CCM-PM4530, CCM-PM4540 | PRECOM-52-EB1-1000: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-08-26 11:00 | 2025-09-08 11:00
C-56-EB2-CI-1000 | Completed | P2543-R01-Oct24..4.3.1.1.2.12.1.1 | Site Survey, Preparation & Grading Works | HE-SS-0030, ML1002, HE-CS-0170, ML1199-B24 | HE-SS-0030: SS, ML1002: FS, HE-CS-0170: FS, ML1199-B24: FS 7 | C-56-EB2-CI-1010, C-56-G-HT-CI-0100 | C-56-EB2-CI-1010: FS, C-56-G-HT-CI-0100: SS 5 | 2024-08-13 07:00 | 2024-08-23 17:00
C-56-EB2-CI-1010 | Completed | P2543-R01-Oct24..4.3.1.1.2.12.1.1 | Earth Works for Ground Level | C-56-EB2-CI-1000 | C-56-EB2-CI-1000: FS | C-56-EB2-CI-1020 | C-56-EB2-CI-1020: SS 5 | 2024-08-25 07:00 | 2024-09-20 17:00
C-56-EB2-CI-1020 | Completed | P2543-R01-Oct24..4.3.1.1.2.12.1.1 | Compaction & Testing for Ground Level | C-56-EB2-CI-1010 | C-56-EB2-CI-1010: SS 5 | C-56-EB2-CI-1200 | C-56-EB2-CI-1200: FS | 2024-08-30 07:00 | 2024-09-26 17:00
C-56-EB2-CI-1200 | Completed | P2543-R01-Oct24..4.3.1.1.2.12.1.2 | Building Foundation Works (for Substructure) | C-56-EB2-CI-1020 | C-56-EB2-CI-1020: FS | C-56-EB2-CI-1400 | C-56-EB2-CI-1400: FF | 2024-09-26 07:00 | 2024-10-25
C-56-EB2-CI-1400 | In Progress | P2543-R01-Oct24..4.3.1.1.2.12.1.3 | Concrete Superstructure Works | C-56-EB2-CI-1200, HM-CS-0050, HM-CS-0040, HE-CS-0230 | C-56-EB2-CI-1200: FF, HM-CS-0050: FF 2, HM-CS-0040: SS, HE-CS-0230: FF | C-56-EB2-CI-1600 | C-56-EB2-CI-1600: FS | 2024-09-27 | 2024-12-26 17:00
C-56-EB2-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.1.4 | Masonry Works - Internal | C-56-EB2-CI-1400 | C-56-EB2-CI-1400: FS | C-56-EB2-CI-1610, C-56-EB2-CI-1810, C-56-EB2-ME-1000 | C-56-EB2-CI-1610: FS, C-56-EB2-CI-1810: FS, C-56-EB2-ME-1000: FS | 2024-12-27 07:00 | 2025-01-21 17:00
C-56-EB2-CI-1610 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.1.4 | Masonry Works - External | C-56-EB2-CI-1600 | C-56-EB2-CI-1600: FS | C-56-EB2-CI-1800, C-56-EB2-ME-1000 | C-56-EB2-CI-1800: FS, C-56-EB2-ME-1000: FS 30 | 2025-01-22 07:00 | 2025-02-06 17:00
C-56-EB2-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.1.5 | External Finishing Works | C-56-EB2-CI-1610 | C-56-EB2-CI-1610: FS | C-56-EB2-CI-2000, C-56-EB2-CI-2010, PRECOM-56-EB2-1000 | C-56-EB2-CI-2000: FS, C-56-EB2-CI-2010: FS, PRECOM-56-EB2-1000: FS | 2025-02-07 07:00 | 2025-02-18 17:00
C-56-EB2-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.1.5 | Internal Finishing Works | C-56-EB2-CI-1600 | C-56-EB2-CI-1600: FS | C-56-EB2-CI-2000, C-56-EB2-ME-1010, PRECOM-56-EB2-1000 | C-56-EB2-CI-2000: FS, C-56-EB2-ME-1010: FS, PRECOM-56-EB2-1000: FS | 2025-01-22 07:00 | 2025-02-06 17:00
C-56-EB2-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.1.6 | Steel Structural Works | C-56-EB2-CI-1800, C-56-EB2-CI-1810, HM-CS-0110 | C-56-EB2-CI-1800: FS, C-56-EB2-CI-1810: FS, HM-CS-0110: FS | C-56-EB2-CI-2010, PRECOM-56-EB2-1000 | C-56-EB2-CI-2010: FS, PRECOM-56-EB2-1000: FS | 2025-02-24 07:00 | 2025-03-14 11:00
C-56-EB2-CI-2010 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.1.7 | Paving Works | C-56-EB2-CI-1800, C-56-EB2-CI-2000, HE-CS-0290, ML1059-B28 | C-56-EB2-CI-1800: FS, C-56-EB2-CI-2000: FS, HE-CS-0290: FS, ML1059-B28: FS | PRECOM-56-EB2-1000 | PRECOM-56-EB2-1000: FS | 2025-03-14 11:00 | 2025-04-15 13:00
C-56-EB2-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.2.1 | Plumbing Works | C-56-EB2-CI-1600, C-56-EB2-CI-1610, HS-CN-0640, HM-ME-1790, HS-CN-0590, ML1015-B08, HM-ME-1790 | C-56-EB2-CI-1600: FS, C-56-EB2-CI-1610: FS 30, HS-CN-0640: FS, HM-ME-1790: FF, HS-CN-0590: FS, ML1015-B08: FS, HM-ME-1790: FS | C-56-EB2-ME-1010, PRECOM-56-EB2-1000 | C-56-EB2-ME-1010: FS, PRECOM-56-EB2-1000: FS | 2025-03-29 07:00 | 2025-04-25 17:00
C-56-EB2-ME-1010 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.2.1 | HVAC Works | C-56-EB2-CI-1810, C-56-EB2-ME-1000, HS-CN-0640, HM-ME-1790, HS-CN-0590, ML1015-B08, HM-ME-1790 | C-56-EB2-CI-1810: FS, C-56-EB2-ME-1000: FS, HS-CN-0640: FS, HM-ME-1790: FS, HS-CN-0590: FS, ML1015-B08: FS, HM-ME-1790: FF | C-56-EB2-EI-1000, PRECOM-56-EB2-1000, C-56-EB2-ME-1200 | C-56-EB2-EI-1000: FS 7, PRECOM-56-EB2-1000: FS, C-56-EB2-ME-1200: FS | 2025-04-26 07:00 | 2025-05-21 15:00
C-56-EB2-EI-1000 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.3.1 | Installation of Power Distribution System | C-56-EB2-ME-1010, HM-EL-0480, HE-IC-0650, HE-IC-0590, HE-EL-0530, HE-IC-0710, HM-ME-0890, HE-EL-1670, HE-EL-1730, HM-ME-1590, HM-EL-0080, HE-IC-0490, HM-EL-0380, HM-ME-1390, HE-EL-1790, HE-IC-0530, HE-IC-0010, HM-EL-0280, HE-IC-0770, HM-EL-0520, HE-PR-0110 | C-56-EB2-ME-1010: FS 7, HM-EL-0480: FS, HE-IC-0650: FS, HE-IC-0590: FS, HE-EL-0530: FS, HE-IC-0710: FS, HM-ME-0890: FS, HE-EL-1670: FS, HE-EL-1730: FS, HM-ME-1590: FF, HM-EL-0080: FF, HE-IC-0490: FS, HM-EL-0380: FS, HM-ME-1390: FS, HE-EL-1790: FS, HE-IC-05 | C-56-EB2-EI-1400, C-56-EB2-EI-2000, C-56-EB2-EI-1230 | C-56-EB2-EI-1400: FS, C-56-EB2-EI-2000: FS, C-56-EB2-EI-1230: FS | 2025-05-29 15:00 | 2025-06-04 15:00
C-56-EB2-EI-1400 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.3.3 | Lighting & Fixtures | C-56-EB2-EI-1000 | C-56-EB2-EI-1000: FS | C-56-EB2-EI-1600, C-56-EB2-EI-1230 | C-56-EB2-EI-1600: FS, C-56-EB2-EI-1230: FS | 2025-06-04 15:00 | 2025-06-23 15:00
C-56-EB2-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.3.6 | Installation of HSSD System | C-56-EB2-EI-1000, C-56-EB2-ME-1200 | C-56-EB2-EI-1000: FS, C-56-EB2-ME-1200: FS | C-56-EB2-EI-2200, C-56-EB2-EI-1230 | C-56-EB2-EI-2200: FS, C-56-EB2-EI-1230: FS | 2025-06-04 15:00 | 2025-06-20 15:00
C-56-EB2-EI-2200 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.3.7 | Installation of RTU System | C-56-EB2-EI-2000 | C-56-EB2-EI-2000: FS | C-56-EB2-EI-1200, C-56-EB2-EI-1230 | C-56-EB2-EI-1200: FS, C-56-EB2-EI-1230: FS | 2025-06-20 15:00 | 2025-06-28 15:00
C-56-EB2-EI-1200 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.3.2 | Custody Metering Panel Installation | C-56-EB2-EI-2200, HE-EL-0830, HM-EL-0080, HE-IC-0950, HM-EL-0520, HE-EL-0470, HE-IC-0830, HE-EL-1610, HE-EL-0590, HE-IC-1010, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-630 | C-56-EB2-EI-2200: FS, HE-EL-0830: FS, HM-EL-0080: FS, HE-IC-0950: FS, HM-EL-0520: FS, HE-EL-0470: FS, HE-IC-0830: FS, HE-EL-1610: FS, HE-EL-0590: FS, HE-IC-1010: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0210 | C-56-EB2-EI-1230, C-56-EB2-TE-1000 | C-56-EB2-EI-1230: FS, C-56-EB2-TE-1000: FS | 2025-06-28 15:00 | 2025-07-05 15:00
C-56-EB2-EI-1210 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.3.2 | E&I Cable Laying | C-56-PL-607-EI-2000, HE-EL-0830, HM-EL-0080, HE-IC-0950, HM-EL-0520, HE-EL-0470, HE-IC-0830, HE-EL-1610, HE-EL-0590, HE-IC-1010, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-6 | C-56-PL-607-EI-2000: FS, HE-EL-0830: FS, HM-EL-0080: FS, HE-IC-0950: FS, HM-EL-0520: FS, HE-EL-0470: FS, HE-IC-0830: FS, HE-EL-1610: FS, HE-EL-0590: FS, HE-IC-1010: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0 | C-56-EB2-EI-2400, C-56-EB2-EI-1800, C-56-EB2-EI-1600, C-56-EB2-EI-1230, C-56-EB2-TE-1000 | C-56-EB2-EI-2400: FS, C-56-EB2-EI-1800: FS, C-56-EB2-EI-1600: FF, C-56-EB2-EI-1230: FS, C-56-EB2-TE-1000: FF 6 | 2025-07-11 11:00 | 2025-08-05 11:00
C-56-EB2-EI-1600 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.3.4 | Earthing & Lightning Protection system | C-56-EB2-EI-1400, C-56-EB2-EI-1210 | C-56-EB2-EI-1400: FS, C-56-EB2-EI-1210: FF | C-56-EB2-EI-1220, C-56-EB2-EI-1230 | C-56-EB2-EI-1220: FS, C-56-EB2-EI-1230: FS | 2025-07-19 11:00 | 2025-08-05 11:00
C-56-EB2-EI-2400 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.3.8 | UPS (10KVA) Installation | C-56-EB2-EI-1210 | C-56-EB2-EI-1210: FS | C-56-EB2-EI-1230, ML1629-E08 | C-56-EB2-EI-1230: FS, ML1629-E08: FS | 2025-08-05 11:00 | 2025-08-16 11:00
C-56-EB2-EI-1800 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.3.5 | Installation F&G System | C-56-EB2-EI-1210 | C-56-EB2-EI-1210: FS | C-56-EB2-EI-1230 | C-56-EB2-EI-1230: FS | 2025-08-05 11:00 | 2025-08-14 11:00
C-56-EB2-EI-1220 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.3.2 | MCT Installation | C-56-EB2-EI-1600, HE-EL-0830, HM-EL-0080, HE-IC-0950, HM-EL-0520, HE-EL-0470, HE-IC-0830, HE-EL-1610, HE-EL-0590, HE-IC-1010, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-630 | C-56-EB2-EI-1600: FS, HE-EL-0830: FS, HM-EL-0080: FS, HE-IC-0950: FS, HM-EL-0520: FS, HE-EL-0470: FS, HE-IC-0830: FS, HE-EL-1610: FS, HE-EL-0590: FS, HE-IC-1010: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0210 | C-56-EB2-EI-1230 | C-56-EB2-EI-1230: FS | 2025-08-05 11:00 | 2025-08-14 11:00
C-56-EB2-EI-1230 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.3.2 | Glanding & Termination | C-56-EB2-EI-1000, C-56-EB2-EI-1400, C-56-EB2-EI-2000, C-56-EB2-EI-2200, C-56-EB2-EI-1200, C-56-EB2-EI-1210, C-56-EB2-EI-1600, C-56-EB2-EI-2400, C-56-EB2-EI-1800, C-56-EB2-EI-1220 | C-56-EB2-EI-1000: FS, C-56-EB2-EI-1400: FS, C-56-EB2-EI-2000: FS, C-56-EB2-EI-2200: FS, C-56-EB2-EI-1200: FS, C-56-EB2-EI-1210: FS, C-56-EB2-EI-1600: FS, C-56-EB2-EI-2400: FS, C-56-EB2-EI-1800: FS, C-56-EB2-EI-1220: FS | C-56-EB2-EL-1600, PRECOM-56-EB2-1000 | C-56-EB2-EL-1600: FS, PRECOM-56-EB2-1000: FS | 2025-08-16 11:00 | 2025-08-30 11:00
C-56-EB2-TE-1000 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.4.1 | SDH Cabinet Installation | C-56-EB2-EI-1200, C-56-EB2-EI-1210, HE-TL-0830, HM-TL-0040, HM-ME-1390, HM-EL-0180, ML1033-B22, HE-TL-0770, HE-TL-0470, HS-CN-0290, HE-TL-0710, HM-ME-2290, HM-EL-610 | C-56-EB2-EI-1200: FS, C-56-EB2-EI-1210: FF 6, HE-TL-0830: FS, HM-TL-0040: FS, HM-ME-1390: FS, HM-EL-0180: FS, ML1033-B22: FS, HE-TL-0770: FS, HE-TL-0470: FS, HS-CN-0290: FS, HE-TL-0710: FS, HM-ME-2290: FS, HM-EL-610: FS | C-56-EB2-TE-1600 | C-56-EB2-TE-1600: FS | 2025-08-02 11:00 | 2025-08-12 11:00
C-56-EB2-TE-1600 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.4.3 | CCTV Installation | C-56-EB2-TE-1000 | C-56-EB2-TE-1000: FS | C-56-EB2-TE-1400 | C-56-EB2-TE-1400: FS | 2025-08-12 11:00 | 2025-08-19 11:00
C-56-EB2-TE-1400 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.4.2 | Telecom System (Including subcontract for FOC Splicing / Termination / Testing) | C-56-EB2-TE-1600 | C-56-EB2-TE-1600: FS | C-56-EB2-TE-1610, PRECOM-56-EB2-1000 | C-56-EB2-TE-1610: SS 2, PRECOM-56-EB2-1000: FS | 2025-08-19 11:00 | 2025-08-29 11:00
C-56-EB2-TE-1610 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.4.3 | Security System (Including subcontract for FOC Splicing / Termination / Testing ) | C-56-EB2-TE-1400 | C-56-EB2-TE-1400: SS 2 | C-56-EB2-EL-1600, PRECOM-56-EB2-1000 | C-56-EB2-EL-1600: FS, PRECOM-56-EB2-1000: FS | 2025-08-21 11:00 | 2025-09-01 11:00
C-4N-H5HG-PIPEL-1000 | Completed | P2543-R01-Oct24..4.3.1.5.4.12.1.6 | Survey Marking | HE-PL-0290, ML1159-A08, HE-PL-0290, C-PER-1000 | HE-PL-0290: FF, ML1159-A08: FS, HE-PL-0290: FS, C-PER-1000: FS | C-4N-H5HG-PIPEL-1800, C-4N-H5HG-PIPEL-1400, C-4N-H5HG-PIPEL-1400 | C-4N-H5HG-PIPEL-1800: FS, C-4N-H5HG-PIPEL-1400: SS 3, C-4N-H5HG-PIPEL-1400: FF | 2024-06-14 | 2024-07-23
C-4N-H5HG-PIPEL-1800 | In Progress | P2543-R01-Oct24..4.3.1.5.4.12.1.8 | Sabka ROW/Grading | HE-PL-2550, C-4N-H5HG-PIPEL-1000, C-GOV-1300 | HE-PL-2550: FF 17, C-4N-H5HG-PIPEL-1000: FS, C-GOV-1300: FF 14 | C-4N-H5HG-PIPEL-2000, C-4N-H5HG-PIPEL-2400, C-4N-H5HG-PIPEL-2400, C-4N-H5HG-PIPEL-1400, C-4N-H5HG-PIPEL-1400, C-4N-H5-TPL-CI-0100 | C-4N-H5HG-PIPEL-2000: FF, C-4N-H5HG-PIPEL-2400: SS 5, C-4N-H5HG-PIPEL-2400: FF, C-4N-H5HG-PIPEL-1400: SS 5, C-4N-H5HG-PIPEL-1400: FS 5, C-4N-H5-TPL-CI-0100: FS 28 | 2024-06-14 | 2024-11-27 07:00
C-4N-H5HG-PIPEL-2000 | In Progress | P2543-R01-Oct24..4.3.1.5.4.12.1.14 | Sabka Gatch Laying (Including ROW) - Layer 1 | C-4N-H5HG-PIPEL-1800 | C-4N-H5HG-PIPEL-1800: FF | C-4N-H5HG-PIPEL-2200 | C-4N-H5HG-PIPEL-2200: SS 1 | 2024-06-14 | 2024-11-27 07:00
C-4N-H5HG-PIPEL-2010 | In Progress | P2543-R01-Oct24..4.3.1.5.4.12.1.14 | Sabka Gatch Laying - Layer 2 | C-4N-H5HG-PIPEL-2200 | C-4N-H5HG-PIPEL-2200: SS 3 | C-4N-H5HG-PIPEL-2210 | C-4N-H5HG-PIPEL-2210: SS 1 | 2024-06-16 | 2024-11-26 17:00
C-4N-H5HG-PIPEL-2020 | In Progress | P2543-R01-Oct24..4.3.1.5.4.12.1.14 | Sabka Gatch Laying - Layer 3 | C-4N-H5HG-PIPEL-2210 | C-4N-H5HG-PIPEL-2210: SS 3 | C-4N-H5HG-PIPEL-2220 | C-4N-H5HG-PIPEL-2220: SS 1 | 2024-06-18 | 2024-11-26 17:00
C-4N-H5HG-PIPEL-2030 | In Progress | P2543-R01-Oct24..4.3.1.5.4.12.1.14 | Sabka Gatch Laying - Layer 4 | C-4N-H5HG-PIPEL-2220 | C-4N-H5HG-PIPEL-2220: SS | C-4N-H5HG-PIPEL-2230 | C-4N-H5HG-PIPEL-2230: SS 1 | 2024-06-20 | 2024-11-26 17:00
C-4N-H5HG-PIPEL-2200 | In Progress | P2543-R01-Oct24..4.3.1.5.4.12.1.14 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-4N-H5HG-PIPEL-2000 | C-4N-H5HG-PIPEL-2000: SS 1 | C-4N-H5HG-PIPEL-2010 | C-4N-H5HG-PIPEL-2010: SS 3 | 2024-06-15 | 2024-11-26 17:00
C-4N-H5HG-PIPEL-2210 | In Progress | P2543-R01-Oct24..4.3.1.5.4.12.1.14 | Sabka Gatch Compaction - Layer 2 | C-4N-H5HG-PIPEL-2010 | C-4N-H5HG-PIPEL-2010: SS 1 | C-4N-H5HG-PIPEL-2020 | C-4N-H5HG-PIPEL-2020: SS 3 | 2024-06-17 | 2024-11-26 17:00
C-4N-H5HG-PIPEL-2220 | In Progress | P2543-R01-Oct24..4.3.1.5.4.12.1.14 | Sabka Gatch Compaction - Layer 3 | C-4N-H5HG-PIPEL-2020 | C-4N-H5HG-PIPEL-2020: SS 1 | C-4N-H5HG-PIPEL-2030 | C-4N-H5HG-PIPEL-2030: SS | 2024-06-19 | 2024-11-26 17:00
C-4N-H5HG-PIPEL-2230 | In Progress | P2543-R01-Oct24..4.3.1.5.4.12.1.14 | Sabka Gatch Compaction - Layer 4 | C-4N-H5HG-PIPEL-2030 | C-4N-H5HG-PIPEL-2030: SS 1 | C-4N-H5HG-PIPEL-2800, C-4N-H5HG-PIPEL-2400, C-4N-H5HG-PIPEL-2400, C-4N-H5HG-PIPEL-2800 | C-4N-H5HG-PIPEL-2800: SS 7, C-4N-H5HG-PIPEL-2400: SS 7, C-4N-H5HG-PIPEL-2400: FF, C-4N-H5HG-PIPEL-2800: FF | 2024-06-21 | 2024-11-26 17:00
C-4N-H5HG-PIPEL-2800 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.9 | Stringing (HB-5 to HGCP) | C-4N-H5HG-PIPEL-2230, C-4N-H5HG-PIPEL-2230, HM-PL-0120 | C-4N-H5HG-PIPEL-2230: SS 7, C-4N-H5HG-PIPEL-2230: FF, HM-PL-0120: FF 7 | C-4N-H5HG-PIPEL-3600, C-4N-H5HG-CMA13-1020, C-4N-H5HG-PIPEL-3800, C-4N-H5HG-CMA13-1000 | C-4N-H5HG-PIPEL-3600: SS 2, C-4N-H5HG-CMA13-1020: SS 5, C-4N-H5HG-PIPEL-3800: SS 2, C-4N-H5HG-CMA13-1000: FS | 2024-12-25 07:00 | 2025-02-13 07:00
C-4N-H5HG-PIPEL-3600 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.11 | Welding | C-4N-H5HG-PIPEL-2800 | C-4N-H5HG-PIPEL-2800: SS 2 | C-4N-H5HG-PIPEL-4000, C-4N-H5HG-PIPEL-4200, C-4N-H5HG-PIPEL-3800, C-4N-H5HG-PIPEL-4000, C-4N-H5HG-PIPEL-4200 | C-4N-H5HG-PIPEL-4000: SS 1, C-4N-H5HG-PIPEL-4200: SS 1, C-4N-H5HG-PIPEL-3800: FS, C-4N-H5HG-PIPEL-4000: FF, C-4N-H5HG-PIPEL-4200: FF | 2024-12-27 07:00 | 2025-01-23 17:00
C-4N-H5HG-PIPEL-4000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.12 | NDT | C-4N-H5HG-PIPEL-3600, C-4N-H5HG-PIPEL-3600 | C-4N-H5HG-PIPEL-3600: SS 1, C-4N-H5HG-PIPEL-3600: FF | C-4N-H5HG-PIPEL-4400, C-4N-H5HG-PIPEL-4600, C-4N-H5HG-PIPEL-4200, C-4N-H5HG-PIPEL-4400, C-4N-H5HG-PIPEL-4600 | C-4N-H5HG-PIPEL-4400: SS 2, C-4N-H5HG-PIPEL-4600: SS 2, C-4N-H5HG-PIPEL-4200: FS, C-4N-H5HG-PIPEL-4400: FF, C-4N-H5HG-PIPEL-4600: FF | 2024-12-28 07:00 | 2025-01-24 17:00
C-4N-H5HG-PIPEL-4400 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.21 | Ext. Joint Coating | C-4N-H5HG-PIPEL-4000, C-4N-H5HG-PIPEL-4000 | C-4N-H5HG-PIPEL-4000: SS 2, C-4N-H5HG-PIPEL-4000: FF | C-4N-H5HG-PIPEL-4800, C-4N-H5HG-PIPEL-5000, C-4N-H5HG-PIPEL-4600, C-4N-H5HG-PIPEL-4800, C-4N-H5HG-PIPEL-5000 | C-4N-H5HG-PIPEL-4800: SS 3, C-4N-H5HG-PIPEL-5000: SS 3, C-4N-H5HG-PIPEL-4600: FS, C-4N-H5HG-PIPEL-4800: FF, C-4N-H5HG-PIPEL-5000: FF | 2024-12-31 07:00 | 2025-01-27 17:00
C-4N-H5HG-PIPEL-2400 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.10 | Trench Excavation | ML1219-B59, HE-PL-3570, C-4N-H5HG-PIPEL-2230, C-4N-H5HG-PIPEL-1400, C-4N-H5HG-PIPEL-1800, C-4N-H5HG-PIPEL-1800, C-4N-H5HG-PIPEL-2230, C-56-01HG-PL-CI-2400 | ML1219-B59: FS, HE-PL-3570: FS, C-4N-H5HG-PIPEL-2230: SS 7, C-4N-H5HG-PIPEL-1400: FF 5, C-4N-H5HG-PIPEL-1800: SS 5, C-4N-H5HG-PIPEL-1800: FF, C-4N-H5HG-PIPEL-2230: FF, C-56-01HG-PL-CI-2400: SS | C-4N-H5HG-PIPEL-2410, C-4N-H5HG-PIPEL-2410 | C-4N-H5HG-PIPEL-2410: SS 7, C-4N-H5HG-PIPEL-2410: FF 7 | 2025-02-13 08:30 | 2025-04-19 14:30
C-4N-H5HG-PIPEL-2410 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.10 | Bedding | C-4N-H5HG-PIPEL-2400, C-4N-H5HG-PIPEL-2400 | C-4N-H5HG-PIPEL-2400: SS 7, C-4N-H5HG-PIPEL-2400: FF 7 | C-4N-H5HG-PIPEL-4800, C-4N-H5HG-PIPEL-5000, C-4N-H5HG-PIPEL-4800, C-4N-H5HG-PIPEL-5000 | C-4N-H5HG-PIPEL-4800: SS 5, C-4N-H5HG-PIPEL-5000: SS 5, C-4N-H5HG-PIPEL-4800: FF 5, C-4N-H5HG-PIPEL-5000: FF 5 | 2025-02-21 08:30 | 2025-04-28 14:30
C-4N-H5HG-PIPEL-4800 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.13 | Lowering | C-4N-H5HG-PIPEL-2410, C-4N-H5HG-PIPEL-4400, C-4N-H5HG-PIPEL-4400, ML1159-A08, C-4N-H5HG-PIPEL-2410 | C-4N-H5HG-PIPEL-2410: SS 5, C-4N-H5HG-PIPEL-4400: SS 3, C-4N-H5HG-PIPEL-4400: FF, ML1159-A08: FF, C-4N-H5HG-PIPEL-2410: FF 5 | C-4N-H5HG-PIPEL-4810, C-4N-H5HG-PIPEL-5010, C-4N-H5HG-PIPEL-4810, C-4N-H5HG-PIPEL-5010, C-4N-H5HG-PIPEL-5000 | C-4N-H5HG-PIPEL-4810: SS, C-4N-H5HG-PIPEL-5010: SS, C-4N-H5HG-PIPEL-4810: FF, C-4N-H5HG-PIPEL-5010: FF, C-4N-H5HG-PIPEL-5000: FS | 2025-04-09 14:30 | 2025-05-03 14:30
C-4N-H5HG-PIPEL-4810 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.13 | Section Tie-in Welding | C-4N-H5HG-PIPEL-4800, C-4N-H5HG-PIPEL-4800 | C-4N-H5HG-PIPEL-4800: SS, C-4N-H5HG-PIPEL-4800: FF | C-4N-H5HG-PIPEL-4820, C-4N-H5-TPL-PL-1000, C-4N-H5HG-PIPEL-5020, C-4N-H5HG-PIPEL-4820, C-4N-H5HG-PIPEL-5020, C-4N-H5HG-PIPEL-5010, ML1909-E36 | C-4N-H5HG-PIPEL-4820: SS 1, C-4N-H5-TPL-PL-1000: FS, C-4N-H5HG-PIPEL-5020: SS 1, C-4N-H5HG-PIPEL-4820: FF, C-4N-H5HG-PIPEL-5020: FF, C-4N-H5HG-PIPEL-5010: FS, ML1909-E36: FS | 2025-04-09 14:30 | 2025-05-10 12:30
C-4N-H5HG-PIPEL-4820 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.13 | NDT (Tie-in Joint) | C-4N-H5HG-PIPEL-4810, C-4N-H5HG-PIPEL-4810 | C-4N-H5HG-PIPEL-4810: SS 1, C-4N-H5HG-PIPEL-4810: FF | C-4N-H5HG-PIPEL-4410, C-4N-H5HG-PIPEL-4610, C-4N-H5HG-PIPEL-4410, C-4N-H5HG-PIPEL-4610, C-4N-H5HG-PIPEL-5020 | C-4N-H5HG-PIPEL-4410: SS 1, C-4N-H5HG-PIPEL-4610: SS 1, C-4N-H5HG-PIPEL-4410: FF, C-4N-H5HG-PIPEL-4610: FF, C-4N-H5HG-PIPEL-5020: FS | 2025-04-10 14:30 | 2025-05-12 12:30
C-4N-H5HG-PIPEL-4410 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.21 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-PIPEL-4820, C-4N-H5HG-PIPEL-4820 | C-4N-H5HG-PIPEL-4820: SS 1, C-4N-H5HG-PIPEL-4820: FF | C-4N-H5HG-PIPEL-4830, C-4N-H5HG-PIPEL-5030, C-4N-H5HG-PIPEL-4610, C-4N-H5HG-PIPEL-4830, C-4N-H5HG-PIPEL-5030 | C-4N-H5HG-PIPEL-4830: SS 1, C-4N-H5HG-PIPEL-5030: SS 1, C-4N-H5HG-PIPEL-4610: FS, C-4N-H5HG-PIPEL-4830: FF, C-4N-H5HG-PIPEL-5030: FF | 2025-04-11 14:30 | 2025-05-13 12:30
C-4N-H5HG-PIPEL-4830 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.13 | Holiday Testing | C-4N-H5HG-PIPEL-4410, C-4N-H5HG-PIPEL-4410 | C-4N-H5HG-PIPEL-4410: SS 1, C-4N-H5HG-PIPEL-4410: FF | C-4N-H5HG-PIPEL-6000, C-4N-H5HG-PIPEL-5600, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400, C-4N-H5HG-PIPEL-5030 | C-4N-H5HG-PIPEL-6000: SS 1, C-4N-H5HG-PIPEL-5600: SS, C-4N-H5HG-PIPEL-8200: SS, C-4N-H5HG-PIPEL-8400: SS, C-4N-H5HG-PIPEL-5030: FS | 2025-04-12 14:30 | 2025-05-14 12:30
C-4N-H5HG-PIPEL-6000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.14 | Padding | C-4N-H5HG-PIPEL-4830, C-4N-H5HG-PIPEL-5030, C-4N-H5HG-PIPEL-5600, C-4N-H5HG-PIPEL-5600 | C-4N-H5HG-PIPEL-4830: SS 1, C-4N-H5HG-PIPEL-5030: SS 1, C-4N-H5HG-PIPEL-5600: SS 2, C-4N-H5HG-PIPEL-5600: FF 2 | C-4N-H5HG-PIPEL-7400, PRECOM-4N-H5HG-1000, C-4N-H5HG-PIPEL-6400, C-4N-H5HG-PIPEL-6400, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, PRECOM-4N-H5HG-1000: FS, C-4N-H5HG-PIPEL-6400: SS 5, C-4N-H5HG-PIPEL-6400: FF 5, C-4N-H5HG-PIPEL-8200: SS 3, C-4N-H5HG-PIPEL-8200: FF 3, C-4N-H5HG-PIPEL-8400: SS 3, C-4N-H5HG-PIPEL-8400: FF 3 | 2025-05-17 12:30 | 2025-07-21 12:30
C-4N-H5HG-PIPEL-1400 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.7 | Cut & Fill (@ Non-Sabkha) | C-4N-H5HG-PIPEL-1000, C-4N-H5HG-PIPEL-1000, C-4N-H5HG-PIPEL-1800, C-4N-H5HG-PIPEL-1800 | C-4N-H5HG-PIPEL-1000: SS 3, C-4N-H5HG-PIPEL-1000: FF, C-4N-H5HG-PIPEL-1800: SS 5, C-4N-H5HG-PIPEL-1800: FS 5 | C-4N-H5HG-PIPEL-2400 | C-4N-H5HG-PIPEL-2400: FF 5 | 2024-12-05 07:00 | 2025-01-07 17:00
C-4N-H5HG-CMA13-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 | Trench Excavation | C-4N-H5HG-PIPEL-2800 | C-4N-H5HG-PIPEL-2800: FS | C-4N-H5HG-CMA13-1010, C-4N-H5HG-CMA01-1000, C-4N-H5HG-CMA12-1000, C-4N-H5HG-CNH01-1000 | C-4N-H5HG-CMA13-1010: FF, C-4N-H5HG-CMA01-1000: FS, C-4N-H5HG-CMA12-1000: FS, C-4N-H5HG-CNH01-1000: FS 7 | 2025-02-13 07:00 | 2025-02-19 17:00
C-4N-H5HG-CMA13-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 | Bedding | C-4N-H5HG-CMA13-1000 | C-4N-H5HG-CMA13-1000: FF | C-4N-H5HG-CMA13-1020 | C-4N-H5HG-CMA13-1020: FS | 2025-02-19 07:00 | 2025-02-19 17:00
C-4N-H5HG-CMA13-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 | Lowering | C-4N-H5HG-CMA13-1010, C-4N-H5HG-PIPEL-2800 | C-4N-H5HG-CMA13-1010: FS, C-4N-H5HG-PIPEL-2800: SS 5 | C-4N-H5HG-CMA13-1030, C-4N-H5HG-CMA01-1020, C-4N-H5HG-CMA12-1020 | C-4N-H5HG-CMA13-1030: SS, C-4N-H5HG-CMA01-1020: FS, C-4N-H5HG-CMA12-1020: SS 3 | 2025-02-20 07:00 | 2025-02-20 17:00
C-4N-H5HG-CMA13-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 | Section Tie-in Welding | C-4N-H5HG-CMA13-1020 | C-4N-H5HG-CMA13-1020: SS | C-4N-H5HG-CMA13-1040, ML1909-E36 | C-4N-H5HG-CMA13-1040: SS 1, ML1909-E36: FS | 2025-02-20 07:00 | 2025-02-21 17:00
C-4N-H5HG-CMA13-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 | NDT (Tie-in Joint) | C-4N-H5HG-CMA13-1030 | C-4N-H5HG-CMA13-1030: SS 1 | C-4N-H5HG-CMA13-1050 | C-4N-H5HG-CMA13-1050: SS 1 | 2025-02-21 07:00 | 2025-02-22 17:00
C-4N-H5HG-CMA13-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA13-1040 | C-4N-H5HG-CMA13-1040: SS 1 | C-4N-H5HG-CMA13-1060 | C-4N-H5HG-CMA13-1060: FS | 2025-02-22 07:00 | 2025-02-24 17:00
C-4N-H5HG-CMA13-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 | Holiday Testing | C-4N-H5HG-CMA13-1050 | C-4N-H5HG-CMA13-1050: FS | C-4N-H5HG-CMA13-1070, C-4N-H5HG-PIPEL-5220 | C-4N-H5HG-CMA13-1070: FS, C-4N-H5HG-PIPEL-5220: SS | 2025-02-25 07:00 | 2025-02-25 17:00
C-4N-H5HG-CMA13-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 | Padding | C-4N-H5HG-CMA13-1060 | C-4N-H5HG-CMA13-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-02-26 07:00 | 2025-02-26 17:00
C-4N-H5HG-CMA01-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 | Trench Excavation | C-4N-H5HG-CMA13-1000 | C-4N-H5HG-CMA13-1000: FS | C-4N-H5HG-CMA01-1010, C-4N-H5HG-CMA02-1000 | C-4N-H5HG-CMA01-1010: FF, C-4N-H5HG-CMA02-1000: FS | 2025-02-20 07:00 | 2025-02-26 17:00
C-4N-H5HG-CMA01-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 | Bedding | C-4N-H5HG-CMA01-1000 | C-4N-H5HG-CMA01-1000: FF | C-4N-H5HG-CMA01-1020 | C-4N-H5HG-CMA01-1020: FS | 2025-02-26 07:00 | 2025-02-26 17:00
C-4N-H5HG-CMA01-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 | Lowering | C-4N-H5HG-CMA01-1010, C-4N-H5HG-CMA13-1020 | C-4N-H5HG-CMA01-1010: FS, C-4N-H5HG-CMA13-1020: FS | C-4N-H5HG-CMA01-1030, C-4N-H5HG-CMA02-1020 | C-4N-H5HG-CMA01-1030: SS, C-4N-H5HG-CMA02-1020: FS | 2025-02-27 07:00 | 2025-02-27 17:00
C-4N-H5HG-CMA01-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 | Section Tie-in Welding | C-4N-H5HG-CMA01-1020 | C-4N-H5HG-CMA01-1020: SS | C-4N-H5HG-CMA01-1040, ML1909-E36 | C-4N-H5HG-CMA01-1040: SS 1, ML1909-E36: FS | 2025-02-27 07:00 | 2025-02-28 17:00
C-4N-H5HG-CMA01-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 | NDT (Tie-in Joint) | C-4N-H5HG-CMA01-1030 | C-4N-H5HG-CMA01-1030: SS 1 | C-4N-H5HG-CMA01-1050 | C-4N-H5HG-CMA01-1050: SS 1 | 2025-02-28 07:00 | 2025-03-01 17:00
C-4N-H5HG-CMA01-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA01-1040 | C-4N-H5HG-CMA01-1040: SS 1 | C-4N-H5HG-CMA01-1060 | C-4N-H5HG-CMA01-1060: FS | 2025-03-01 07:00 | 2025-03-03 11:00
C-4N-H5HG-CMA01-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 | Holiday Testing | C-4N-H5HG-CMA01-1050 | C-4N-H5HG-CMA01-1050: FS | C-4N-H5HG-CMA01-1070 | C-4N-H5HG-CMA01-1070: FS | 2025-03-03 11:00 | 2025-03-05 09:00
C-4N-H5HG-CMA01-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 | Padding | C-4N-H5HG-CMA01-1060 | C-4N-H5HG-CMA01-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-03-05 09:00 | 2025-03-06 13:00
C-4N-H5HG-CMA02-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 | Trench Excavation | C-4N-H5HG-CMA01-1000 | C-4N-H5HG-CMA01-1000: FS | C-4N-H5HG-CMA02-1010, C-4N-H5HG-CMA03-1000 | C-4N-H5HG-CMA02-1010: FF, C-4N-H5HG-CMA03-1000: FS | 2025-02-27 07:00 | 2025-03-06 13:00
C-4N-H5HG-CMA02-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 | Bedding | C-4N-H5HG-CMA02-1000 | C-4N-H5HG-CMA02-1000: FF | C-4N-H5HG-CMA02-1020 | C-4N-H5HG-CMA02-1020: FS | 2025-03-05 09:00 | 2025-03-06 13:00
C-4N-H5HG-CMA02-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 | Lowering | C-4N-H5HG-CMA02-1010, C-4N-H5HG-CMA01-1020 | C-4N-H5HG-CMA02-1010: FS, C-4N-H5HG-CMA01-1020: FS | C-4N-H5HG-CMA02-1030, C-4N-H5HG-CMA03-1020 | C-4N-H5HG-CMA02-1030: SS, C-4N-H5HG-CMA03-1020: FS | 2025-03-07 07:00 | 2025-03-08 11:00
C-4N-H5HG-CMA02-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 | Section Tie-in Welding | C-4N-H5HG-CMA02-1020 | C-4N-H5HG-CMA02-1020: SS | C-4N-H5HG-CMA02-1040, ML1909-E36 | C-4N-H5HG-CMA02-1040: SS 1, ML1909-E36: FS | 2025-03-07 07:00 | 2025-03-09 11:00
C-4N-H5HG-CMA02-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 | NDT (Tie-in Joint) | C-4N-H5HG-CMA02-1030 | C-4N-H5HG-CMA02-1030: SS 1 | C-4N-H5HG-CMA02-1050 | C-4N-H5HG-CMA02-1050: SS 1 | 2025-03-08 11:00 | 2025-03-11 09:00
C-4N-H5HG-CMA02-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA02-1040 | C-4N-H5HG-CMA02-1040: SS 1 | C-4N-H5HG-CMA02-1060 | C-4N-H5HG-CMA02-1060: FS | 2025-03-09 11:00 | 2025-03-12 13:00
C-4N-H5HG-CMA02-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 | Holiday Testing | C-4N-H5HG-CMA02-1050 | C-4N-H5HG-CMA02-1050: FS | C-4N-H5HG-CMA02-1070 | C-4N-H5HG-CMA02-1070: FS | 2025-03-13 07:00 | 2025-03-14 11:00
C-4N-H5HG-CMA02-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 | Padding | C-4N-H5HG-CMA02-1060 | C-4N-H5HG-CMA02-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-03-14 11:00 | 2025-03-15 15:00
C-4N-H5HG-CMA03-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 | Trench Excavation | C-4N-H5HG-CMA02-1000 | C-4N-H5HG-CMA02-1000: FS | C-4N-H5HG-CMA03-1010, C-4N-H5HG-CMA04-1000 | C-4N-H5HG-CMA03-1010: FF, C-4N-H5HG-CMA04-1000: FS | 2025-03-07 07:00 | 2025-03-15 15:00
C-4N-H5HG-CMA03-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 | Bedding | C-4N-H5HG-CMA03-1000 | C-4N-H5HG-CMA03-1000: FF | C-4N-H5HG-CMA03-1020 | C-4N-H5HG-CMA03-1020: FS | 2025-03-14 11:00 | 2025-03-15 15:00
C-4N-H5HG-CMA03-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 | Lowering | C-4N-H5HG-CMA03-1010, C-4N-H5HG-CMA02-1020 | C-4N-H5HG-CMA03-1010: FS, C-4N-H5HG-CMA02-1020: FS | C-4N-H5HG-CMA03-1030, C-4N-H5HG-CMA04-1020 | C-4N-H5HG-CMA03-1030: SS, C-4N-H5HG-CMA04-1020: FS | 2025-03-15 15:00 | 2025-03-17 09:00
C-4N-H5HG-CMA03-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 | Section Tie-in Welding | C-4N-H5HG-CMA03-1020 | C-4N-H5HG-CMA03-1020: SS | C-4N-H5HG-CMA03-1040, ML1909-E36 | C-4N-H5HG-CMA03-1040: SS 1, ML1909-E36: FS | 2025-03-15 15:00 | 2025-03-18 13:00
C-4N-H5HG-CMA03-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 | NDT (Tie-in Joint) | C-4N-H5HG-CMA03-1030 | C-4N-H5HG-CMA03-1030: SS 1 | C-4N-H5HG-CMA03-1050 | C-4N-H5HG-CMA03-1050: SS 1 | 2025-03-17 09:00 | 2025-03-20 11:00
C-4N-H5HG-CMA03-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA03-1040 | C-4N-H5HG-CMA03-1040: SS 1 | C-4N-H5HG-CMA03-1060 | C-4N-H5HG-CMA03-1060: FS | 2025-03-19 07:00 | 2025-03-22 09:00
C-4N-H5HG-CMA03-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 | Holiday Testing | C-4N-H5HG-CMA03-1050 | C-4N-H5HG-CMA03-1050: FS | C-4N-H5HG-CMA03-1070 | C-4N-H5HG-CMA03-1070: FS | 2025-03-22 09:00 | 2025-03-23 09:00
C-4N-H5HG-CMA03-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 | Padding | C-4N-H5HG-CMA03-1060 | C-4N-H5HG-CMA03-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-03-23 09:00 | 2025-03-24 13:00
C-4N-H5HG-CMA04-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 | Trench Excavation | C-4N-H5HG-CMA03-1000 | C-4N-H5HG-CMA03-1000: FS | C-4N-H5HG-CMA04-1010, C-4N-H5HG-CMA05-1000 | C-4N-H5HG-CMA04-1010: FF, C-4N-H5HG-CMA05-1000: FS | 2025-03-15 15:00 | 2025-03-24 13:00
C-4N-H5HG-CMA04-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 | Bedding | C-4N-H5HG-CMA04-1000 | C-4N-H5HG-CMA04-1000: FF | C-4N-H5HG-CMA04-1020 | C-4N-H5HG-CMA04-1020: FS | 2025-03-23 09:00 | 2025-03-24 13:00
C-4N-H5HG-CMA04-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 | Lowering | C-4N-H5HG-CMA04-1010, C-4N-H5HG-CMA03-1020 | C-4N-H5HG-CMA04-1010: FS, C-4N-H5HG-CMA03-1020: FS | C-4N-H5HG-CMA04-1030, C-4N-H5HG-CMA05-1020 | C-4N-H5HG-CMA04-1030: SS, C-4N-H5HG-CMA05-1020: FS | 2025-03-25 07:00 | 2025-03-26 11:00
C-4N-H5HG-CMA04-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 | Section Tie-in Welding | C-4N-H5HG-CMA04-1020 | C-4N-H5HG-CMA04-1020: SS | C-4N-H5HG-CMA04-1040, ML1909-E36 | C-4N-H5HG-CMA04-1040: SS 1, ML1909-E36: FS | 2025-03-25 07:00 | 2025-03-28 09:00
C-4N-H5HG-CMA04-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 | NDT (Tie-in Joint) | C-4N-H5HG-CMA04-1030 | C-4N-H5HG-CMA04-1030: SS 1 | C-4N-H5HG-CMA04-1050 | C-4N-H5HG-CMA04-1050: SS 1 | 2025-03-26 11:00 | 2025-03-29 13:00
C-4N-H5HG-CMA04-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA04-1040 | C-4N-H5HG-CMA04-1040: SS 1 | C-4N-H5HG-CMA04-1060 | C-4N-H5HG-CMA04-1060: FS | 2025-03-28 09:00 | 2025-04-03 13:00
C-4N-H5HG-CMA04-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 | Holiday Testing | C-4N-H5HG-CMA04-1050 | C-4N-H5HG-CMA04-1050: FS | C-4N-H5HG-CMA04-1070 | C-4N-H5HG-CMA04-1070: FS | 2025-04-03 13:00 | 2025-04-04 13:00
C-4N-H5HG-CMA04-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 | Padding | C-4N-H5HG-CMA04-1060 | C-4N-H5HG-CMA04-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-04-04 13:00 | 2025-04-05 13:00
C-4N-H5HG-CMA05-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 | Trench Excavation | C-4N-H5HG-CMA04-1000 | C-4N-H5HG-CMA04-1000: FS | C-4N-H5HG-CMA05-1010, C-4N-H5HG-CMA06-1000 | C-4N-H5HG-CMA05-1010: FF, C-4N-H5HG-CMA06-1000: FS | 2025-03-25 07:00 | 2025-04-05 13:00
C-4N-H5HG-CMA05-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 | Bedding | C-4N-H5HG-CMA05-1000 | C-4N-H5HG-CMA05-1000: FF | C-4N-H5HG-CMA05-1020 | C-4N-H5HG-CMA05-1020: FS | 2025-04-04 13:00 | 2025-04-05 13:00
C-4N-H5HG-CMA05-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 | Lowering | C-4N-H5HG-CMA05-1010, C-4N-H5HG-CMA04-1020 | C-4N-H5HG-CMA05-1010: FS, C-4N-H5HG-CMA04-1020: FS | C-4N-H5HG-CMA05-1030, C-4N-H5HG-CMA06-1020 | C-4N-H5HG-CMA05-1030: SS, C-4N-H5HG-CMA06-1020: FS | 2025-04-05 13:00 | 2025-04-07 13:00
C-4N-H5HG-CMA05-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 | Section Tie-in Welding | C-4N-H5HG-CMA05-1020 | C-4N-H5HG-CMA05-1020: SS | C-4N-H5HG-CMA05-1040, ML1909-E36 | C-4N-H5HG-CMA05-1040: SS 1, ML1909-E36: FS | 2025-04-05 13:00 | 2025-04-08 13:00
C-4N-H5HG-CMA05-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 | NDT (Tie-in Joint) | C-4N-H5HG-CMA05-1030 | C-4N-H5HG-CMA05-1030: SS 1 | C-4N-H5HG-CMA05-1050 | C-4N-H5HG-CMA05-1050: SS 1 | 2025-04-07 13:00 | 2025-04-09 13:00
C-4N-H5HG-CMA05-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA05-1040 | C-4N-H5HG-CMA05-1040: SS 1 | C-4N-H5HG-CMA05-1060 | C-4N-H5HG-CMA05-1060: FS | 2025-04-08 13:00 | 2025-04-10 13:00
C-4N-H5HG-CMA05-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 | Holiday Testing | C-4N-H5HG-CMA05-1050 | C-4N-H5HG-CMA05-1050: FS | C-4N-H5HG-CMA05-1070 | C-4N-H5HG-CMA05-1070: FS | 2025-04-10 13:00 | 2025-04-11 13:00
C-4N-H5HG-CMA05-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 | Padding | C-4N-H5HG-CMA05-1060 | C-4N-H5HG-CMA05-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-04-11 13:00 | 2025-04-12 13:00
C-4N-H5HG-CMA06-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 | Trench Excavation | C-4N-H5HG-CMA05-1000 | C-4N-H5HG-CMA05-1000: FS | C-4N-H5HG-CMA06-1010, C-4N-H5HG-CMA07-1000 | C-4N-H5HG-CMA06-1010: FF, C-4N-H5HG-CMA07-1000: FS | 2025-04-05 13:00 | 2025-04-12 13:00
C-4N-H5HG-CMA06-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 | Bedding | C-4N-H5HG-CMA06-1000 | C-4N-H5HG-CMA06-1000: FF | C-4N-H5HG-CMA06-1020 | C-4N-H5HG-CMA06-1020: FS | 2025-04-11 13:00 | 2025-04-12 13:00
C-4N-H5HG-CMA06-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 | Lowering | C-4N-H5HG-CMA06-1010, C-4N-H5HG-CMA05-1020 | C-4N-H5HG-CMA06-1010: FS, C-4N-H5HG-CMA05-1020: FS | C-4N-H5HG-CMA06-1030, C-4N-H5HG-CMA07-1020 | C-4N-H5HG-CMA06-1030: SS, C-4N-H5HG-CMA07-1020: FS | 2025-04-12 13:00 | 2025-04-14 13:00
C-4N-H5HG-CMA06-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 | Section Tie-in Welding | C-4N-H5HG-CMA06-1020 | C-4N-H5HG-CMA06-1020: SS | C-4N-H5HG-CMA06-1040, ML1909-E36 | C-4N-H5HG-CMA06-1040: SS 1, ML1909-E36: FS | 2025-04-12 13:00 | 2025-04-15 13:00
C-4N-H5HG-CMA06-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 | NDT (Tie-in Joint) | C-4N-H5HG-CMA06-1030 | C-4N-H5HG-CMA06-1030: SS 1 | C-4N-H5HG-CMA06-1050 | C-4N-H5HG-CMA06-1050: SS 1 | 2025-04-14 13:00 | 2025-04-16 13:00
C-4N-H5HG-CMA06-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA06-1040 | C-4N-H5HG-CMA06-1040: SS 1 | C-4N-H5HG-CMA06-1060 | C-4N-H5HG-CMA06-1060: FS | 2025-04-15 13:00 | 2025-04-17 13:00
C-4N-H5HG-CMA06-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 | Holiday Testing | C-4N-H5HG-CMA06-1050 | C-4N-H5HG-CMA06-1050: FS | C-4N-H5HG-CMA06-1070 | C-4N-H5HG-CMA06-1070: FS | 2025-04-17 13:00 | 2025-04-18 13:00
C-4N-H5HG-CMA06-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 | Padding | C-4N-H5HG-CMA06-1060 | C-4N-H5HG-CMA06-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-04-18 13:00 | 2025-04-19 13:00
C-4N-H5HG-CMA07-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 | Trench Excavation | C-4N-H5HG-CMA06-1000 | C-4N-H5HG-CMA06-1000: FS | C-4N-H5HG-CMA07-1010, C-4N-H5HG-CMA08-1000 | C-4N-H5HG-CMA07-1010: FF, C-4N-H5HG-CMA08-1000: FS | 2025-04-12 13:00 | 2025-04-19 13:00
C-4N-H5HG-CMA07-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 | Bedding | C-4N-H5HG-CMA07-1000 | C-4N-H5HG-CMA07-1000: FF | C-4N-H5HG-CMA07-1020 | C-4N-H5HG-CMA07-1020: FS | 2025-04-18 13:00 | 2025-04-19 13:00
C-4N-H5HG-CMA07-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 | Lowering | C-4N-H5HG-CMA07-1010, C-4N-H5HG-CMA06-1020 | C-4N-H5HG-CMA07-1010: FS, C-4N-H5HG-CMA06-1020: FS | C-4N-H5HG-CMA07-1030, C-4N-H5HG-CMA08-1020 | C-4N-H5HG-CMA07-1030: SS, C-4N-H5HG-CMA08-1020: FS | 2025-04-19 13:00 | 2025-04-21 13:00
C-4N-H5HG-CMA07-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 | Section Tie-in Welding | C-4N-H5HG-CMA07-1020 | C-4N-H5HG-CMA07-1020: SS | C-4N-H5HG-CMA07-1040, ML1909-E36 | C-4N-H5HG-CMA07-1040: SS 1, ML1909-E36: FS | 2025-04-19 13:00 | 2025-04-22 13:00
C-4N-H5HG-CMA07-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 | NDT (Tie-in Joint) | C-4N-H5HG-CMA07-1030 | C-4N-H5HG-CMA07-1030: SS 1 | C-4N-H5HG-CMA07-1050 | C-4N-H5HG-CMA07-1050: SS 1 | 2025-04-21 13:00 | 2025-04-23 13:00
C-4N-H5HG-CMA07-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA07-1040 | C-4N-H5HG-CMA07-1040: SS 1 | C-4N-H5HG-CMA07-1060 | C-4N-H5HG-CMA07-1060: FS | 2025-04-22 13:00 | 2025-04-24 13:00
C-4N-H5HG-CMA07-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 | Holiday Testing | C-4N-H5HG-CMA07-1050 | C-4N-H5HG-CMA07-1050: FS | C-4N-H5HG-CMA07-1070 | C-4N-H5HG-CMA07-1070: FS | 2025-04-24 13:00 | 2025-04-25 13:00
C-4N-H5HG-CMA07-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 | Padding | C-4N-H5HG-CMA07-1060 | C-4N-H5HG-CMA07-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-04-25 13:00 | 2025-04-26 13:00
C-4N-H5HG-CMA08-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 | Trench Excavation | C-4N-H5HG-CMA07-1000 | C-4N-H5HG-CMA07-1000: FS | C-4N-H5HG-CMA08-1010, C-4N-H5HG-CMA09-1000 | C-4N-H5HG-CMA08-1010: FF, C-4N-H5HG-CMA09-1000: FS | 2025-04-19 13:00 | 2025-04-26 13:00
C-4N-H5HG-CMA08-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 | Bedding | C-4N-H5HG-CMA08-1000 | C-4N-H5HG-CMA08-1000: FF | C-4N-H5HG-CMA08-1020 | C-4N-H5HG-CMA08-1020: FS | 2025-04-25 13:00 | 2025-04-26 13:00
C-4N-H5HG-CMA08-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 | Lowering | C-4N-H5HG-CMA08-1010, C-4N-H5HG-CMA07-1020 | C-4N-H5HG-CMA08-1010: FS, C-4N-H5HG-CMA07-1020: FS | C-4N-H5HG-CMA08-1030, C-4N-H5HG-CMA09-1020 | C-4N-H5HG-CMA08-1030: SS, C-4N-H5HG-CMA09-1020: FS | 2025-04-26 13:00 | 2025-04-28 13:00
C-4N-H5HG-CMA08-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 | Section Tie-in Welding | C-4N-H5HG-CMA08-1020 | C-4N-H5HG-CMA08-1020: SS | C-4N-H5HG-CMA08-1040, ML1909-E36 | C-4N-H5HG-CMA08-1040: SS 1, ML1909-E36: FS | 2025-04-26 13:00 | 2025-04-29 13:00
C-4N-H5HG-CMA08-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 | NDT (Tie-in Joint) | C-4N-H5HG-CMA08-1030 | C-4N-H5HG-CMA08-1030: SS 1 | C-4N-H5HG-CMA08-1050 | C-4N-H5HG-CMA08-1050: SS 1 | 2025-04-28 13:00 | 2025-04-30 13:00
C-4N-H5HG-CMA08-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA08-1040 | C-4N-H5HG-CMA08-1040: SS 1 | C-4N-H5HG-CMA08-1060 | C-4N-H5HG-CMA08-1060: FS | 2025-04-29 13:00 | 2025-05-01 13:00
C-4N-H5HG-CMA08-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 | Holiday Testing | C-4N-H5HG-CMA08-1050 | C-4N-H5HG-CMA08-1050: FS | C-4N-H5HG-CMA08-1070 | C-4N-H5HG-CMA08-1070: FS | 2025-05-01 13:00 | 2025-05-02 13:00
C-4N-H5HG-CMA08-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 | Padding | C-4N-H5HG-CMA08-1060 | C-4N-H5HG-CMA08-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-05-02 13:00 | 2025-05-03 13:00
C-4N-H5HG-CMA09-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 | Trench Excavation | C-4N-H5HG-CMA08-1000 | C-4N-H5HG-CMA08-1000: FS | C-4N-H5HG-CMA09-1010, C-4N-H5HG-CMA10-1000 | C-4N-H5HG-CMA09-1010: FF, C-4N-H5HG-CMA10-1000: FS | 2025-04-26 13:00 | 2025-05-03 13:00
C-4N-H5HG-CMA09-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 | Bedding | C-4N-H5HG-CMA09-1000 | C-4N-H5HG-CMA09-1000: FF | C-4N-H5HG-CMA09-1020 | C-4N-H5HG-CMA09-1020: FS | 2025-05-02 13:00 | 2025-05-03 13:00
C-4N-H5HG-CMA09-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 | Lowering | C-4N-H5HG-CMA09-1010, C-4N-H5HG-CMA08-1020 | C-4N-H5HG-CMA09-1010: FS, C-4N-H5HG-CMA08-1020: FS | C-4N-H5HG-CMA09-1030, C-4N-H5HG-CMA10-1020 | C-4N-H5HG-CMA09-1030: SS, C-4N-H5HG-CMA10-1020: FS | 2025-05-03 13:00 | 2025-05-05 14:00
C-4N-H5HG-CMA09-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 | Section Tie-in Welding | C-4N-H5HG-CMA09-1020 | C-4N-H5HG-CMA09-1020: SS | C-4N-H5HG-CMA09-1040, ML1909-E36 | C-4N-H5HG-CMA09-1040: SS 1, ML1909-E36: FS | 2025-05-03 13:00 | 2025-05-06 16:00
C-4N-H5HG-CMA09-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 | NDT (Tie-in Joint) | C-4N-H5HG-CMA09-1030 | C-4N-H5HG-CMA09-1030: SS 1 | C-4N-H5HG-CMA09-1050 | C-4N-H5HG-CMA09-1050: SS 1 | 2025-05-05 14:00 | 2025-05-08 10:00
C-4N-H5HG-CMA09-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA09-1040 | C-4N-H5HG-CMA09-1040: SS 1 | C-4N-H5HG-CMA09-1060 | C-4N-H5HG-CMA09-1060: FS | 2025-05-07 08:00 | 2025-05-09 11:00
C-4N-H5HG-CMA09-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 | Holiday Testing | C-4N-H5HG-CMA09-1050 | C-4N-H5HG-CMA09-1050: FS | C-4N-H5HG-CMA09-1070 | C-4N-H5HG-CMA09-1070: FS | 2025-05-09 11:00 | 2025-05-10 11:00
C-4N-H5HG-CMA09-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 | Padding | C-4N-H5HG-CMA09-1060 | C-4N-H5HG-CMA09-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-05-10 11:00 | 2025-05-12 11:00
C-4N-H5HG-CMA10-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 | Trench Excavation | C-4N-H5HG-CMA09-1000 | C-4N-H5HG-CMA09-1000: FS | C-4N-H5HG-CMA10-1010, C-4N-H5HG-CMA11-1000 | C-4N-H5HG-CMA10-1010: FF, C-4N-H5HG-CMA11-1000: FS | 2025-05-03 13:00 | 2025-05-12 11:00
C-4N-H5HG-CMA10-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 | Bedding | C-4N-H5HG-CMA10-1000 | C-4N-H5HG-CMA10-1000: FF | C-4N-H5HG-CMA10-1020 | C-4N-H5HG-CMA10-1020: FS | 2025-05-10 11:00 | 2025-05-12 11:00
C-4N-H5HG-CMA10-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 | Lowering | C-4N-H5HG-CMA10-1010, C-4N-H5HG-CMA09-1020 | C-4N-H5HG-CMA10-1010: FS, C-4N-H5HG-CMA09-1020: FS | C-4N-H5HG-CMA10-1030, C-4N-H5HG-CMA11-1020 | C-4N-H5HG-CMA10-1030: SS, C-4N-H5HG-CMA11-1020: FS | 2025-05-12 11:00 | 2025-05-13 11:00
C-4N-H5HG-CMA10-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 | Section Tie-in Welding | C-4N-H5HG-CMA10-1020 | C-4N-H5HG-CMA10-1020: SS | C-4N-H5HG-CMA10-1040, ML1909-E36 | C-4N-H5HG-CMA10-1040: SS 1, ML1909-E36: FS | 2025-05-12 11:00 | 2025-05-14 11:00
C-4N-H5HG-CMA10-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 | NDT (Tie-in Joint) | C-4N-H5HG-CMA10-1030 | C-4N-H5HG-CMA10-1030: SS 1 | C-4N-H5HG-CMA10-1050 | C-4N-H5HG-CMA10-1050: SS 1 | 2025-05-13 11:00 | 2025-05-15 11:00
C-4N-H5HG-CMA10-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA10-1040 | C-4N-H5HG-CMA10-1040: SS 1 | C-4N-H5HG-CMA10-1060 | C-4N-H5HG-CMA10-1060: FS | 2025-05-14 11:00 | 2025-05-16 11:00
C-4N-H5HG-CMA10-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 | Holiday Testing | C-4N-H5HG-CMA10-1050 | C-4N-H5HG-CMA10-1050: FS | C-4N-H5HG-CMA10-1070 | C-4N-H5HG-CMA10-1070: FS | 2025-05-16 11:00 | 2025-05-17 11:00
C-4N-H5HG-CMA10-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 | Padding | C-4N-H5HG-CMA10-1060 | C-4N-H5HG-CMA10-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-05-17 11:00 | 2025-05-19 11:00
C-4N-H5HG-CMA11-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 | Trench Excavation | C-4N-H5HG-CMA10-1000 | C-4N-H5HG-CMA10-1000: FS | C-4N-H5HG-CMA11-1010 | C-4N-H5HG-CMA11-1010: FF | 2025-05-12 11:00 | 2025-05-19 11:00
C-4N-H5HG-CMA11-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 | Bedding | C-4N-H5HG-CMA11-1000 | C-4N-H5HG-CMA11-1000: FF | C-4N-H5HG-CMA11-1020 | C-4N-H5HG-CMA11-1020: FS | 2025-05-17 11:00 | 2025-05-19 11:00
C-4N-H5HG-CMA11-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 | Lowering | C-4N-H5HG-CMA11-1010, C-4N-H5HG-CMA10-1020 | C-4N-H5HG-CMA11-1010: FS, C-4N-H5HG-CMA10-1020: FS | C-4N-H5HG-CMA11-1030 | C-4N-H5HG-CMA11-1030: SS | 2025-05-19 11:00 | 2025-05-20 11:00
C-4N-H5HG-CMA11-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 | Section Tie-in Welding | C-4N-H5HG-CMA11-1020 | C-4N-H5HG-CMA11-1020: SS | C-4N-H5HG-CMA11-1040, ML1909-E36 | C-4N-H5HG-CMA11-1040: SS 1, ML1909-E36: FS | 2025-05-19 11:00 | 2025-05-21 11:00
C-4N-H5HG-CMA11-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 | NDT (Tie-in Joint) | C-4N-H5HG-CMA11-1030 | C-4N-H5HG-CMA11-1030: SS 1 | C-4N-H5HG-CMA11-1050 | C-4N-H5HG-CMA11-1050: SS 1 | 2025-05-20 11:00 | 2025-05-22 11:00
C-4N-H5HG-CMA11-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA11-1040 | C-4N-H5HG-CMA11-1040: SS 1 | C-4N-H5HG-CMA11-1060 | C-4N-H5HG-CMA11-1060: FS | 2025-05-21 11:00 | 2025-05-23 11:00
C-4N-H5HG-CMA11-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 | Holiday Testing | C-4N-H5HG-CMA11-1050 | C-4N-H5HG-CMA11-1050: FS | C-4N-H5HG-CMA11-1070 | C-4N-H5HG-CMA11-1070: FS | 2025-05-23 11:00 | 2025-05-24 11:00
C-4N-H5HG-CMA11-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 | Padding | C-4N-H5HG-CMA11-1060 | C-4N-H5HG-CMA11-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-05-24 11:00 | 2025-05-26 11:00
C-4N-H5HG-CMA12-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 | Trench Excavation | C-4N-H5HG-CMA13-1000 | C-4N-H5HG-CMA13-1000: FS | C-4N-H5HG-CMA12-1010, C-4N-H5HG-CMA14-1000, C-4N-H5HG-CMA23-1000 | C-4N-H5HG-CMA12-1010: FF, C-4N-H5HG-CMA14-1000: FS, C-4N-H5HG-CMA23-1000: FS | 2025-02-20 07:00 | 2025-02-26 17:00
C-4N-H5HG-CMA12-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 | Bedding | C-4N-H5HG-CMA12-1000 | C-4N-H5HG-CMA12-1000: FF | C-4N-H5HG-CMA12-1020 | C-4N-H5HG-CMA12-1020: FS | 2025-02-26 07:00 | 2025-02-26 17:00
C-4N-H5HG-CMA12-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 | Lowering | C-4N-H5HG-CMA12-1010, C-4N-H5HG-CMA13-1020 | C-4N-H5HG-CMA12-1010: FS, C-4N-H5HG-CMA13-1020: SS 3 | C-4N-H5HG-CMA12-1030, C-4N-H5HG-CMA14-1020, C-4N-H5HG-CMA23-1020 | C-4N-H5HG-CMA12-1030: SS, C-4N-H5HG-CMA14-1020: FS, C-4N-H5HG-CMA23-1020: FS | 2025-02-27 07:00 | 2025-02-27 17:00
C-4N-H5HG-CMA12-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 | Section Tie-in Welding | C-4N-H5HG-CMA12-1020 | C-4N-H5HG-CMA12-1020: SS | C-4N-H5HG-CMA12-1040, ML1909-E36 | C-4N-H5HG-CMA12-1040: SS 1, ML1909-E36: FS | 2025-02-27 07:00 | 2025-02-28 17:00
C-4N-H5HG-CMA12-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 | NDT (Tie-in Joint) | C-4N-H5HG-CMA12-1030 | C-4N-H5HG-CMA12-1030: SS 1 | C-4N-H5HG-CMA12-1050 | C-4N-H5HG-CMA12-1050: SS 1 | 2025-02-28 07:00 | 2025-03-01 17:00
C-4N-H5HG-CMA12-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA12-1040 | C-4N-H5HG-CMA12-1040: SS 1 | C-4N-H5HG-CMA12-1060 | C-4N-H5HG-CMA12-1060: FS | 2025-03-01 07:00 | 2025-03-03 11:00
C-4N-H5HG-CMA12-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 | Holiday Testing | C-4N-H5HG-CMA12-1050 | C-4N-H5HG-CMA12-1050: FS | C-4N-H5HG-CMA12-1070 | C-4N-H5HG-CMA12-1070: FS | 2025-03-03 11:00 | 2025-03-05 09:00
C-4N-H5HG-CMA12-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 | Padding | C-4N-H5HG-CMA12-1060 | C-4N-H5HG-CMA12-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-03-05 09:00 | 2025-03-06 13:00
C-4N-H5HG-CMA14-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 | Trench Excavation | C-4N-H5HG-CMA12-1000 | C-4N-H5HG-CMA12-1000: FS | C-4N-H5HG-CMA14-1010, C-4N-H5HG-CMA15-1000 | C-4N-H5HG-CMA14-1010: FF, C-4N-H5HG-CMA15-1000: FS | 2025-02-27 07:00 | 2025-03-06 13:00
C-4N-H5HG-CMA14-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 | Bedding | C-4N-H5HG-CMA14-1000 | C-4N-H5HG-CMA14-1000: FF | C-4N-H5HG-CMA14-1020 | C-4N-H5HG-CMA14-1020: FS | 2025-03-05 09:00 | 2025-03-06 13:00
C-4N-H5HG-CMA14-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 | Lowering | C-4N-H5HG-CMA14-1010, C-4N-H5HG-CMA12-1020 | C-4N-H5HG-CMA14-1010: FS, C-4N-H5HG-CMA12-1020: FS | C-4N-H5HG-CMA14-1030, C-4N-H5HG-CMA15-1020 | C-4N-H5HG-CMA14-1030: SS, C-4N-H5HG-CMA15-1020: FS | 2025-03-07 07:00 | 2025-03-08 11:00
C-4N-H5HG-CMA14-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 | Section Tie-in Welding | C-4N-H5HG-CMA14-1020 | C-4N-H5HG-CMA14-1020: SS | C-4N-H5HG-CMA14-1040, ML1909-E36 | C-4N-H5HG-CMA14-1040: SS 1, ML1909-E36: FS | 2025-03-07 07:00 | 2025-03-09 11:00
C-4N-H5HG-CMA14-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 | NDT (Tie-in Joint) | C-4N-H5HG-CMA14-1030 | C-4N-H5HG-CMA14-1030: SS 1 | C-4N-H5HG-CMA14-1050 | C-4N-H5HG-CMA14-1050: SS 1 | 2025-03-08 11:00 | 2025-03-11 09:00
C-4N-H5HG-CMA14-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA14-1040 | C-4N-H5HG-CMA14-1040: SS 1 | C-4N-H5HG-CMA14-1060 | C-4N-H5HG-CMA14-1060: FS | 2025-03-09 11:00 | 2025-03-12 13:00
C-4N-H5HG-CMA14-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 | Holiday Testing | C-4N-H5HG-CMA14-1050 | C-4N-H5HG-CMA14-1050: FS | C-4N-H5HG-CMA14-1070 | C-4N-H5HG-CMA14-1070: FS | 2025-03-13 07:00 | 2025-03-14 11:00
C-4N-H5HG-CMA14-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 | Padding | C-4N-H5HG-CMA14-1060 | C-4N-H5HG-CMA14-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-03-14 11:00 | 2025-03-15 15:00
C-4N-H5HG-CMA15-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 | Trench Excavation | C-4N-H5HG-CMA14-1000 | C-4N-H5HG-CMA14-1000: FS | C-4N-H5HG-CMA15-1010, C-4N-H5HG-CMA16-1000 | C-4N-H5HG-CMA15-1010: FF, C-4N-H5HG-CMA16-1000: FS | 2025-03-07 07:00 | 2025-03-15 15:00
C-4N-H5HG-CMA15-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 | Bedding | C-4N-H5HG-CMA15-1000 | C-4N-H5HG-CMA15-1000: FF | C-4N-H5HG-CMA15-1020 | C-4N-H5HG-CMA15-1020: FS | 2025-03-14 11:00 | 2025-03-15 15:00
C-4N-H5HG-CMA15-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 | Lowering | C-4N-H5HG-CMA15-1010, C-4N-H5HG-CMA14-1020 | C-4N-H5HG-CMA15-1010: FS, C-4N-H5HG-CMA14-1020: FS | C-4N-H5HG-CMA15-1030, C-4N-H5HG-CMA16-1020 | C-4N-H5HG-CMA15-1030: SS, C-4N-H5HG-CMA16-1020: FS | 2025-03-15 15:00 | 2025-03-17 09:00
C-4N-H5HG-CMA15-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 | Section Tie-in Welding | C-4N-H5HG-CMA15-1020 | C-4N-H5HG-CMA15-1020: SS | C-4N-H5HG-CMA15-1040, ML1909-E36 | C-4N-H5HG-CMA15-1040: SS 1, ML1909-E36: FS | 2025-03-15 15:00 | 2025-03-18 13:00
C-4N-H5HG-CMA15-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 | NDT (Tie-in Joint) | C-4N-H5HG-CMA15-1030 | C-4N-H5HG-CMA15-1030: SS 1 | C-4N-H5HG-CMA15-1050 | C-4N-H5HG-CMA15-1050: SS 1 | 2025-03-17 09:00 | 2025-03-20 11:00
C-4N-H5HG-CMA15-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA15-1040 | C-4N-H5HG-CMA15-1040: SS 1 | C-4N-H5HG-CMA15-1060 | C-4N-H5HG-CMA15-1060: FS | 2025-03-19 07:00 | 2025-03-22 09:00
C-4N-H5HG-CMA15-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 | Holiday Testing | C-4N-H5HG-CMA15-1050 | C-4N-H5HG-CMA15-1050: FS | C-4N-H5HG-CMA15-1070 | C-4N-H5HG-CMA15-1070: FS | 2025-03-22 09:00 | 2025-03-23 09:00
C-4N-H5HG-CMA15-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 | Padding | C-4N-H5HG-CMA15-1060 | C-4N-H5HG-CMA15-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-03-23 09:00 | 2025-03-24 13:00
C-4N-H5HG-CMA16-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 | Trench Excavation | C-4N-H5HG-CMA15-1000 | C-4N-H5HG-CMA15-1000: FS | C-4N-H5HG-CMA16-1010, C-4N-H5HG-CMA17-1000 | C-4N-H5HG-CMA16-1010: FF, C-4N-H5HG-CMA17-1000: FS | 2025-03-15 15:00 | 2025-03-24 13:00
C-4N-H5HG-CMA16-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 | Bedding | C-4N-H5HG-CMA16-1000 | C-4N-H5HG-CMA16-1000: FF | C-4N-H5HG-CMA16-1020 | C-4N-H5HG-CMA16-1020: FS | 2025-03-23 09:00 | 2025-03-24 13:00
C-4N-H5HG-CMA16-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 | Lowering | C-4N-H5HG-CMA16-1010, C-4N-H5HG-CMA15-1020 | C-4N-H5HG-CMA16-1010: FS, C-4N-H5HG-CMA15-1020: FS | C-4N-H5HG-CMA16-1030, C-4N-H5HG-CMA17-1020 | C-4N-H5HG-CMA16-1030: SS, C-4N-H5HG-CMA17-1020: FS | 2025-03-25 07:00 | 2025-03-26 11:00
C-4N-H5HG-CMA16-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 | Section Tie-in Welding | C-4N-H5HG-CMA16-1020 | C-4N-H5HG-CMA16-1020: SS | C-4N-H5HG-CMA16-1040, ML1909-E36 | C-4N-H5HG-CMA16-1040: SS 1, ML1909-E36: FS | 2025-03-25 07:00 | 2025-03-28 09:00
C-4N-H5HG-CMA16-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 | NDT (Tie-in Joint) | C-4N-H5HG-CMA16-1030 | C-4N-H5HG-CMA16-1030: SS 1 | C-4N-H5HG-CMA16-1050 | C-4N-H5HG-CMA16-1050: SS 1 | 2025-03-26 11:00 | 2025-03-29 13:00
C-4N-H5HG-CMA16-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA16-1040 | C-4N-H5HG-CMA16-1040: SS 1 | C-4N-H5HG-CMA16-1060 | C-4N-H5HG-CMA16-1060: FS | 2025-03-28 09:00 | 2025-04-03 13:00
C-4N-H5HG-CMA16-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 | Holiday Testing | C-4N-H5HG-CMA16-1050 | C-4N-H5HG-CMA16-1050: FS | C-4N-H5HG-CMA16-1070 | C-4N-H5HG-CMA16-1070: FS | 2025-04-03 13:00 | 2025-04-04 13:00
C-4N-H5HG-CMA16-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 | Padding | C-4N-H5HG-CMA16-1060 | C-4N-H5HG-CMA16-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-04-04 13:00 | 2025-04-05 13:00
C-4N-H5HG-CMA17-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 | Trench Excavation | C-4N-H5HG-CMA16-1000 | C-4N-H5HG-CMA16-1000: FS | C-4N-H5HG-CMA17-1010, C-4N-H5HG-CMA18-1000 | C-4N-H5HG-CMA17-1010: FF, C-4N-H5HG-CMA18-1000: FS | 2025-03-25 07:00 | 2025-04-05 13:00
C-4N-H5HG-CMA17-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 | Bedding | C-4N-H5HG-CMA17-1000 | C-4N-H5HG-CMA17-1000: FF | C-4N-H5HG-CMA17-1020 | C-4N-H5HG-CMA17-1020: FS | 2025-04-04 13:00 | 2025-04-05 13:00
C-4N-H5HG-CMA17-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 | Lowering | C-4N-H5HG-CMA17-1010, C-4N-H5HG-CMA16-1020 | C-4N-H5HG-CMA17-1010: FS, C-4N-H5HG-CMA16-1020: FS | C-4N-H5HG-CMA17-1030, C-4N-H5HG-CMA18-1020 | C-4N-H5HG-CMA17-1030: SS, C-4N-H5HG-CMA18-1020: FS | 2025-04-05 13:00 | 2025-04-07 13:00
C-4N-H5HG-CMA17-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 | Section Tie-in Welding | C-4N-H5HG-CMA17-1020 | C-4N-H5HG-CMA17-1020: SS | C-4N-H5HG-CMA17-1040, ML1909-E36 | C-4N-H5HG-CMA17-1040: SS 1, ML1909-E36: FS | 2025-04-05 13:00 | 2025-04-08 13:00
C-4N-H5HG-CMA17-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 | NDT (Tie-in Joint) | C-4N-H5HG-CMA17-1030 | C-4N-H5HG-CMA17-1030: SS 1 | C-4N-H5HG-CMA17-1050 | C-4N-H5HG-CMA17-1050: SS 1 | 2025-04-07 13:00 | 2025-04-09 13:00
C-4N-H5HG-CMA17-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA17-1040 | C-4N-H5HG-CMA17-1040: SS 1 | C-4N-H5HG-CMA17-1060 | C-4N-H5HG-CMA17-1060: FS | 2025-04-08 13:00 | 2025-04-10 13:00
C-4N-H5HG-CMA17-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 | Holiday Testing | C-4N-H5HG-CMA17-1050 | C-4N-H5HG-CMA17-1050: FS | C-4N-H5HG-CMA17-1070 | C-4N-H5HG-CMA17-1070: FS | 2025-04-10 13:00 | 2025-04-11 13:00
C-4N-H5HG-CMA17-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 | Padding | C-4N-H5HG-CMA17-1060 | C-4N-H5HG-CMA17-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-04-11 13:00 | 2025-04-12 13:00
C-4N-H5HG-CMA18-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 | Trench Excavation | C-4N-H5HG-CMA17-1000 | C-4N-H5HG-CMA17-1000: FS | C-4N-H5HG-CMA18-1010, C-4N-H5HG-CMA27-1000 | C-4N-H5HG-CMA18-1010: FF, C-4N-H5HG-CMA27-1000: FS | 2025-04-05 13:00 | 2025-04-12 13:00
C-4N-H5HG-CMA18-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 | Bedding | C-4N-H5HG-CMA18-1000 | C-4N-H5HG-CMA18-1000: FF | C-4N-H5HG-CMA18-1020 | C-4N-H5HG-CMA18-1020: FS | 2025-04-11 13:00 | 2025-04-12 13:00
C-4N-H5HG-CMA18-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 | Lowering | C-4N-H5HG-CMA18-1010, C-4N-H5HG-CMA17-1020 | C-4N-H5HG-CMA18-1010: FS, C-4N-H5HG-CMA17-1020: FS | C-4N-H5HG-CMA18-1030, C-4N-H5HG-CMA27-1020 | C-4N-H5HG-CMA18-1030: SS, C-4N-H5HG-CMA27-1020: FS | 2025-04-12 13:00 | 2025-04-14 13:00
C-4N-H5HG-CMA18-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 | Section Tie-in Welding | C-4N-H5HG-CMA18-1020 | C-4N-H5HG-CMA18-1020: SS | C-4N-H5HG-CMA18-1040, ML1909-E36 | C-4N-H5HG-CMA18-1040: SS 1, ML1909-E36: FS | 2025-04-12 13:00 | 2025-04-15 13:00
C-4N-H5HG-CMA18-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 | NDT (Tie-in Joint) | C-4N-H5HG-CMA18-1030 | C-4N-H5HG-CMA18-1030: SS 1 | C-4N-H5HG-CMA18-1050 | C-4N-H5HG-CMA18-1050: SS 1 | 2025-04-14 13:00 | 2025-04-16 13:00
C-4N-H5HG-CMA18-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA18-1040 | C-4N-H5HG-CMA18-1040: SS 1 | C-4N-H5HG-CMA18-1060 | C-4N-H5HG-CMA18-1060: FS | 2025-04-15 13:00 | 2025-04-17 13:00
C-4N-H5HG-CMA18-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 | Holiday Testing | C-4N-H5HG-CMA18-1050 | C-4N-H5HG-CMA18-1050: FS | C-4N-H5HG-CMA18-1070 | C-4N-H5HG-CMA18-1070: FS | 2025-04-17 13:00 | 2025-04-18 13:00
C-4N-H5HG-CMA18-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 | Padding | C-4N-H5HG-CMA18-1060 | C-4N-H5HG-CMA18-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-04-18 13:00 | 2025-04-19 13:00
C-4N-H5HG-CMA27-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 | Trench Excavation | C-4N-H5HG-CMA18-1000 | C-4N-H5HG-CMA18-1000: FS | C-4N-H5HG-CMA27-1010, C-4N-H5HG-CMA19-1000 | C-4N-H5HG-CMA27-1010: FF, C-4N-H5HG-CMA19-1000: FS | 2025-04-12 13:00 | 2025-04-19 13:00
C-4N-H5HG-CMA27-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 | Bedding | C-4N-H5HG-CMA27-1000 | C-4N-H5HG-CMA27-1000: FF | C-4N-H5HG-CMA27-1020 | C-4N-H5HG-CMA27-1020: FS | 2025-04-18 13:00 | 2025-04-19 13:00
C-4N-H5HG-CMA27-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 | Lowering | C-4N-H5HG-CMA27-1010, C-4N-H5HG-CMA18-1020 | C-4N-H5HG-CMA27-1010: FS, C-4N-H5HG-CMA18-1020: FS | C-4N-H5HG-CMA27-1030, C-4N-H5HG-CMA19-1020 | C-4N-H5HG-CMA27-1030: SS, C-4N-H5HG-CMA19-1020: FS | 2025-04-19 13:00 | 2025-04-21 13:00
C-4N-H5HG-CMA27-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 | Section Tie-in Welding | C-4N-H5HG-CMA27-1020 | C-4N-H5HG-CMA27-1020: SS | C-4N-H5HG-CMA27-1040, ML1909-E36 | C-4N-H5HG-CMA27-1040: SS 1, ML1909-E36: FS | 2025-04-19 13:00 | 2025-04-22 13:00
C-4N-H5HG-CMA27-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 | NDT (Tie-in Joint) | C-4N-H5HG-CMA27-1030 | C-4N-H5HG-CMA27-1030: SS 1 | C-4N-H5HG-CMA27-1050 | C-4N-H5HG-CMA27-1050: SS 1 | 2025-04-21 13:00 | 2025-04-23 13:00
C-4N-H5HG-CMA27-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA27-1040 | C-4N-H5HG-CMA27-1040: SS 1 | C-4N-H5HG-CMA27-1060 | C-4N-H5HG-CMA27-1060: FS | 2025-04-22 13:00 | 2025-04-24 13:00
C-4N-H5HG-CMA27-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 | Holiday Testing | C-4N-H5HG-CMA27-1050 | C-4N-H5HG-CMA27-1050: FS | C-4N-H5HG-CMA27-1070 | C-4N-H5HG-CMA27-1070: FS | 2025-04-24 13:00 | 2025-04-25 13:00
C-4N-H5HG-CMA27-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 | Padding | C-4N-H5HG-CMA27-1060 | C-4N-H5HG-CMA27-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-04-25 13:00 | 2025-04-26 13:00
C-4N-H5HG-CMA19-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 | Trench Excavation | C-4N-H5HG-CMA27-1000 | C-4N-H5HG-CMA27-1000: FS | C-4N-H5HG-CMA19-1010, C-4N-H5HG-CMA20-1000 | C-4N-H5HG-CMA19-1010: FF, C-4N-H5HG-CMA20-1000: FS | 2025-04-19 13:00 | 2025-04-26 13:00
C-4N-H5HG-CMA19-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 | Bedding | C-4N-H5HG-CMA19-1000 | C-4N-H5HG-CMA19-1000: FF | C-4N-H5HG-CMA19-1020 | C-4N-H5HG-CMA19-1020: FS | 2025-04-25 13:00 | 2025-04-26 13:00
C-4N-H5HG-CMA19-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 | Lowering | C-4N-H5HG-CMA19-1010, C-4N-H5HG-CMA27-1020 | C-4N-H5HG-CMA19-1010: FS, C-4N-H5HG-CMA27-1020: FS | C-4N-H5HG-CMA19-1030, C-4N-H5HG-CMA20-1020 | C-4N-H5HG-CMA19-1030: SS, C-4N-H5HG-CMA20-1020: FS | 2025-04-26 13:00 | 2025-04-28 13:00
C-4N-H5HG-CMA19-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 | Section Tie-in Welding | C-4N-H5HG-CMA19-1020 | C-4N-H5HG-CMA19-1020: SS | C-4N-H5HG-CMA19-1040, ML1909-E36 | C-4N-H5HG-CMA19-1040: SS 1, ML1909-E36: FS | 2025-04-26 13:00 | 2025-04-29 13:00
C-4N-H5HG-CMA19-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 | NDT (Tie-in Joint) | C-4N-H5HG-CMA19-1030 | C-4N-H5HG-CMA19-1030: SS 1 | C-4N-H5HG-CMA19-1050 | C-4N-H5HG-CMA19-1050: SS 1 | 2025-04-28 13:00 | 2025-04-30 13:00
C-4N-H5HG-CMA19-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA19-1040 | C-4N-H5HG-CMA19-1040: SS 1 | C-4N-H5HG-CMA19-1060 | C-4N-H5HG-CMA19-1060: FS | 2025-04-29 13:00 | 2025-05-01 13:00
C-4N-H5HG-CMA19-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 | Holiday Testing | C-4N-H5HG-CMA19-1050 | C-4N-H5HG-CMA19-1050: FS | C-4N-H5HG-CMA19-1070 | C-4N-H5HG-CMA19-1070: FS | 2025-05-01 13:00 | 2025-05-02 13:00
C-4N-H5HG-CMA19-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 | Padding | C-4N-H5HG-CMA19-1060 | C-4N-H5HG-CMA19-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-05-02 13:00 | 2025-05-03 13:00
C-4N-H5HG-CMA20-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 | Trench Excavation | C-4N-H5HG-CMA19-1000 | C-4N-H5HG-CMA19-1000: FS | C-4N-H5HG-CMA20-1010, C-4N-H5HG-CMA21-1000 | C-4N-H5HG-CMA20-1010: FF, C-4N-H5HG-CMA21-1000: FS | 2025-04-26 13:00 | 2025-05-03 13:00
C-4N-H5HG-CMA20-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 | Bedding | C-4N-H5HG-CMA20-1000 | C-4N-H5HG-CMA20-1000: FF | C-4N-H5HG-CMA20-1020 | C-4N-H5HG-CMA20-1020: FS | 2025-05-02 13:00 | 2025-05-03 13:00
C-4N-H5HG-CMA20-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 | Lowering | C-4N-H5HG-CMA20-1010, C-4N-H5HG-CMA19-1020 | C-4N-H5HG-CMA20-1010: FS, C-4N-H5HG-CMA19-1020: FS | C-4N-H5HG-CMA20-1030, C-4N-H5HG-CMA21-1020 | C-4N-H5HG-CMA20-1030: SS, C-4N-H5HG-CMA21-1020: FS | 2025-05-03 13:00 | 2025-05-05 14:00
C-4N-H5HG-CMA20-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 | Section Tie-in Welding | C-4N-H5HG-CMA20-1020 | C-4N-H5HG-CMA20-1020: SS | C-4N-H5HG-CMA20-1040, ML1909-E36 | C-4N-H5HG-CMA20-1040: SS 1, ML1909-E36: FS | 2025-05-03 13:00 | 2025-05-06 16:00
C-4N-H5HG-CMA20-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 | NDT (Tie-in Joint) | C-4N-H5HG-CMA20-1030 | C-4N-H5HG-CMA20-1030: SS 1 | C-4N-H5HG-CMA20-1050 | C-4N-H5HG-CMA20-1050: SS 1 | 2025-05-05 14:00 | 2025-05-08 10:00
C-4N-H5HG-CMA20-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA20-1040 | C-4N-H5HG-CMA20-1040: SS 1 | C-4N-H5HG-CMA20-1060 | C-4N-H5HG-CMA20-1060: FS | 2025-05-07 08:00 | 2025-05-09 11:00
C-4N-H5HG-CMA20-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 | Holiday Testing | C-4N-H5HG-CMA20-1050 | C-4N-H5HG-CMA20-1050: FS | C-4N-H5HG-CMA20-1070 | C-4N-H5HG-CMA20-1070: FS | 2025-05-09 11:00 | 2025-05-10 11:00
C-4N-H5HG-CMA20-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 | Padding | C-4N-H5HG-CMA20-1060 | C-4N-H5HG-CMA20-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-05-10 11:00 | 2025-05-12 11:00
C-4N-H5HG-CMA21-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 | Trench Excavation | C-4N-H5HG-CMA20-1000 | C-4N-H5HG-CMA20-1000: FS | C-4N-H5HG-CMA21-1010, C-4N-H5HG-CMA22-1000 | C-4N-H5HG-CMA21-1010: FF, C-4N-H5HG-CMA22-1000: FS | 2025-05-03 13:00 | 2025-05-12 11:00
C-4N-H5HG-CMA21-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 | Bedding | C-4N-H5HG-CMA21-1000 | C-4N-H5HG-CMA21-1000: FF | C-4N-H5HG-CMA21-1020 | C-4N-H5HG-CMA21-1020: FS | 2025-05-10 11:00 | 2025-05-12 11:00
C-4N-H5HG-CMA21-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 | Lowering | C-4N-H5HG-CMA21-1010, C-4N-H5HG-CMA20-1020 | C-4N-H5HG-CMA21-1010: FS, C-4N-H5HG-CMA20-1020: FS | C-4N-H5HG-CMA21-1030, C-4N-H5HG-CMA22-1020 | C-4N-H5HG-CMA21-1030: SS, C-4N-H5HG-CMA22-1020: FS | 2025-05-12 11:00 | 2025-05-13 11:00
C-4N-H5HG-CMA21-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 | Section Tie-in Welding | C-4N-H5HG-CMA21-1020 | C-4N-H5HG-CMA21-1020: SS | C-4N-H5HG-CMA21-1040, ML1909-E36 | C-4N-H5HG-CMA21-1040: SS 1, ML1909-E36: FS | 2025-05-12 11:00 | 2025-05-14 11:00
C-4N-H5HG-CMA21-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 | NDT (Tie-in Joint) | C-4N-H5HG-CMA21-1030 | C-4N-H5HG-CMA21-1030: SS 1 | C-4N-H5HG-CMA21-1050 | C-4N-H5HG-CMA21-1050: SS 1 | 2025-05-13 11:00 | 2025-05-15 11:00
C-4N-H5HG-CMA21-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA21-1040 | C-4N-H5HG-CMA21-1040: SS 1 | C-4N-H5HG-CMA21-1060 | C-4N-H5HG-CMA21-1060: FS | 2025-05-14 11:00 | 2025-05-16 11:00
C-4N-H5HG-CMA21-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 | Holiday Testing | C-4N-H5HG-CMA21-1050 | C-4N-H5HG-CMA21-1050: FS | C-4N-H5HG-CMA21-1070 | C-4N-H5HG-CMA21-1070: FS | 2025-05-16 11:00 | 2025-05-17 11:00
C-4N-H5HG-CMA21-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 | Padding | C-4N-H5HG-CMA21-1060 | C-4N-H5HG-CMA21-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-05-17 11:00 | 2025-05-19 11:00
C-4N-H5HG-CMA22-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 | Trench Excavation | C-4N-H5HG-CMA21-1000 | C-4N-H5HG-CMA21-1000: FS | C-4N-H5HG-CMA22-1010 | C-4N-H5HG-CMA22-1010: FF | 2025-05-12 11:00 | 2025-05-19 11:00
C-4N-H5HG-CMA22-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 | Bedding | C-4N-H5HG-CMA22-1000 | C-4N-H5HG-CMA22-1000: FF | C-4N-H5HG-CMA22-1020 | C-4N-H5HG-CMA22-1020: FS | 2025-05-17 11:00 | 2025-05-19 11:00
C-4N-H5HG-CMA22-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 | Lowering | C-4N-H5HG-CMA22-1010, C-4N-H5HG-CMA21-1020 | C-4N-H5HG-CMA22-1010: FS, C-4N-H5HG-CMA21-1020: FS | C-4N-H5HG-CMA22-1030 | C-4N-H5HG-CMA22-1030: SS | 2025-05-19 11:00 | 2025-05-20 11:00
C-4N-H5HG-CMA22-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 | Section Tie-in Welding | C-4N-H5HG-CMA22-1020 | C-4N-H5HG-CMA22-1020: SS | C-4N-H5HG-CMA22-1040, ML1909-E36 | C-4N-H5HG-CMA22-1040: SS 1, ML1909-E36: FS | 2025-05-19 11:00 | 2025-05-21 11:00
C-4N-H5HG-CMA22-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 | NDT (Tie-in Joint) | C-4N-H5HG-CMA22-1030 | C-4N-H5HG-CMA22-1030: SS 1 | C-4N-H5HG-CMA22-1050 | C-4N-H5HG-CMA22-1050: SS 1 | 2025-05-20 11:00 | 2025-05-22 11:00
C-4N-H5HG-CMA22-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA22-1040 | C-4N-H5HG-CMA22-1040: SS 1 | C-4N-H5HG-CMA22-1060 | C-4N-H5HG-CMA22-1060: FS | 2025-05-21 11:00 | 2025-05-23 11:00
C-4N-H5HG-CMA22-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 | Holiday Testing | C-4N-H5HG-CMA22-1050 | C-4N-H5HG-CMA22-1050: FS | C-4N-H5HG-CMA22-1070 | C-4N-H5HG-CMA22-1070: FS | 2025-05-23 11:00 | 2025-05-24 11:00
C-4N-H5HG-CMA22-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 | Padding | C-4N-H5HG-CMA22-1060 | C-4N-H5HG-CMA22-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-05-24 11:00 | 2025-05-26 11:00
C-4N-H5HG-CMA23-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 | Trench Excavation | C-4N-H5HG-CMA12-1000 | C-4N-H5HG-CMA12-1000: FS | C-4N-H5HG-CMA23-1010, C-4N-H5HG-CMA28-1000 | C-4N-H5HG-CMA23-1010: FF, C-4N-H5HG-CMA28-1000: FS | 2025-02-27 07:00 | 2025-03-06 13:00
C-4N-H5HG-CMA23-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 | Bedding | C-4N-H5HG-CMA23-1000 | C-4N-H5HG-CMA23-1000: FF | C-4N-H5HG-CMA23-1020 | C-4N-H5HG-CMA23-1020: FS | 2025-03-05 09:00 | 2025-03-06 13:00
C-4N-H5HG-CMA23-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 | Lowering | C-4N-H5HG-CMA23-1010, C-4N-H5HG-CMA12-1020 | C-4N-H5HG-CMA23-1010: FS, C-4N-H5HG-CMA12-1020: FS | C-4N-H5HG-CMA23-1030, C-4N-H5HG-CMA28-1020 | C-4N-H5HG-CMA23-1030: SS, C-4N-H5HG-CMA28-1020: FS | 2025-03-07 07:00 | 2025-03-08 11:00
C-4N-H5HG-CMA23-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 | Section Tie-in Welding | C-4N-H5HG-CMA23-1020 | C-4N-H5HG-CMA23-1020: SS | C-4N-H5HG-CMA23-1040, ML1909-E36 | C-4N-H5HG-CMA23-1040: SS 1, ML1909-E36: FS | 2025-03-07 07:00 | 2025-03-09 11:00
C-4N-H5HG-CMA23-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 | NDT (Tie-in Joint) | C-4N-H5HG-CMA23-1030 | C-4N-H5HG-CMA23-1030: SS 1 | C-4N-H5HG-CMA23-1050 | C-4N-H5HG-CMA23-1050: SS 1 | 2025-03-08 11:00 | 2025-03-11 09:00
C-4N-H5HG-CMA23-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA23-1040 | C-4N-H5HG-CMA23-1040: SS 1 | C-4N-H5HG-CMA23-1060 | C-4N-H5HG-CMA23-1060: FS | 2025-03-09 11:00 | 2025-03-12 13:00
C-4N-H5HG-CMA23-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 | Holiday Testing | C-4N-H5HG-CMA23-1050 | C-4N-H5HG-CMA23-1050: FS | C-4N-H5HG-CMA23-1070 | C-4N-H5HG-CMA23-1070: FS | 2025-03-13 07:00 | 2025-03-14 11:00
C-4N-H5HG-CMA23-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 | Padding | C-4N-H5HG-CMA23-1060 | C-4N-H5HG-CMA23-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-03-14 11:00 | 2025-03-15 15:00
C-4N-H5HG-CMA28-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 | Trench Excavation | C-4N-H5HG-CMA23-1000 | C-4N-H5HG-CMA23-1000: FS | C-4N-H5HG-CMA28-1010, C-4N-H5HG-CMA24-1000 | C-4N-H5HG-CMA28-1010: FF, C-4N-H5HG-CMA24-1000: FS | 2025-03-07 07:00 | 2025-03-15 15:00
C-4N-H5HG-CMA28-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 | Bedding | C-4N-H5HG-CMA28-1000 | C-4N-H5HG-CMA28-1000: FF | C-4N-H5HG-CMA28-1020 | C-4N-H5HG-CMA28-1020: FS | 2025-03-14 11:00 | 2025-03-15 15:00
C-4N-H5HG-CMA28-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 | Lowering | C-4N-H5HG-CMA28-1010, C-4N-H5HG-CMA23-1020 | C-4N-H5HG-CMA28-1010: FS, C-4N-H5HG-CMA23-1020: FS | C-4N-H5HG-CMA28-1030, C-4N-H5HG-CMA24-1020 | C-4N-H5HG-CMA28-1030: SS, C-4N-H5HG-CMA24-1020: FS | 2025-03-15 15:00 | 2025-03-17 09:00
C-4N-H5HG-CMA28-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 | Section Tie-in Welding | C-4N-H5HG-CMA28-1020 | C-4N-H5HG-CMA28-1020: SS | C-4N-H5HG-CMA28-1040, ML1909-E36 | C-4N-H5HG-CMA28-1040: SS 1, ML1909-E36: FS | 2025-03-15 15:00 | 2025-03-18 13:00
C-4N-H5HG-CMA28-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 | NDT (Tie-in Joint) | C-4N-H5HG-CMA28-1030 | C-4N-H5HG-CMA28-1030: SS 1 | C-4N-H5HG-CMA28-1050 | C-4N-H5HG-CMA28-1050: SS 1 | 2025-03-17 09:00 | 2025-03-20 11:00
C-4N-H5HG-CMA28-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA28-1040 | C-4N-H5HG-CMA28-1040: SS 1 | C-4N-H5HG-CMA28-1060 | C-4N-H5HG-CMA28-1060: FS | 2025-03-19 07:00 | 2025-03-22 09:00
C-4N-H5HG-CMA28-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 | Holiday Testing | C-4N-H5HG-CMA28-1050 | C-4N-H5HG-CMA28-1050: FS | C-4N-H5HG-CMA28-1070 | C-4N-H5HG-CMA28-1070: FS | 2025-03-22 09:00 | 2025-03-23 09:00
C-4N-H5HG-CMA28-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 | Padding | C-4N-H5HG-CMA28-1060 | C-4N-H5HG-CMA28-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-03-23 09:00 | 2025-03-24 13:00
C-4N-H5HG-CMA24-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 | Trench Excavation | C-4N-H5HG-CMA28-1000 | C-4N-H5HG-CMA28-1000: FS | C-4N-H5HG-CMA24-1010, C-4N-H5HG-CMA25-1000 | C-4N-H5HG-CMA24-1010: FF, C-4N-H5HG-CMA25-1000: FS | 2025-03-15 15:00 | 2025-03-24 13:00
C-4N-H5HG-CMA24-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 | Bedding | C-4N-H5HG-CMA24-1000 | C-4N-H5HG-CMA24-1000: FF | C-4N-H5HG-CMA24-1020 | C-4N-H5HG-CMA24-1020: FS | 2025-03-23 09:00 | 2025-03-24 13:00
C-4N-H5HG-CMA24-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 | Lowering | C-4N-H5HG-CMA24-1010, C-4N-H5HG-CMA28-1020 | C-4N-H5HG-CMA24-1010: FS, C-4N-H5HG-CMA28-1020: FS | C-4N-H5HG-CMA24-1030, C-4N-H5HG-CMA25-1020 | C-4N-H5HG-CMA24-1030: SS, C-4N-H5HG-CMA25-1020: FS | 2025-03-25 07:00 | 2025-03-26 11:00
C-4N-H5HG-CMA24-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 | Section Tie-in Welding | C-4N-H5HG-CMA24-1020 | C-4N-H5HG-CMA24-1020: SS | C-4N-H5HG-CMA24-1040, ML1909-E36 | C-4N-H5HG-CMA24-1040: SS 1, ML1909-E36: FS | 2025-03-25 07:00 | 2025-03-28 09:00
C-4N-H5HG-CMA24-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 | NDT (Tie-in Joint) | C-4N-H5HG-CMA24-1030 | C-4N-H5HG-CMA24-1030: SS 1 | C-4N-H5HG-CMA24-1050 | C-4N-H5HG-CMA24-1050: SS 1 | 2025-03-26 11:00 | 2025-03-29 13:00
C-4N-H5HG-CMA24-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA24-1040 | C-4N-H5HG-CMA24-1040: SS 1 | C-4N-H5HG-CMA24-1060 | C-4N-H5HG-CMA24-1060: FS | 2025-03-28 09:00 | 2025-04-03 13:00
C-4N-H5HG-CMA24-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 | Holiday Testing | C-4N-H5HG-CMA24-1050 | C-4N-H5HG-CMA24-1050: FS | C-4N-H5HG-CMA24-1070 | C-4N-H5HG-CMA24-1070: FS | 2025-04-03 13:00 | 2025-04-04 13:00
C-4N-H5HG-CMA24-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 | Padding | C-4N-H5HG-CMA24-1060 | C-4N-H5HG-CMA24-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-04-04 13:00 | 2025-04-05 13:00
C-4N-H5HG-CMA25-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 | Trench Excavation | C-4N-H5HG-CMA24-1000 | C-4N-H5HG-CMA24-1000: FS | C-4N-H5HG-CMA25-1010, C-4N-H5HG-CMA26-1000 | C-4N-H5HG-CMA25-1010: FF, C-4N-H5HG-CMA26-1000: FS | 2025-03-25 07:00 | 2025-04-05 13:00
C-4N-H5HG-CMA25-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 | Bedding | C-4N-H5HG-CMA25-1000 | C-4N-H5HG-CMA25-1000: FF | C-4N-H5HG-CMA25-1020 | C-4N-H5HG-CMA25-1020: FS | 2025-04-04 13:00 | 2025-04-05 13:00
C-4N-H5HG-CMA25-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 | Lowering | C-4N-H5HG-CMA25-1010, C-4N-H5HG-CMA24-1020 | C-4N-H5HG-CMA25-1010: FS, C-4N-H5HG-CMA24-1020: FS | C-4N-H5HG-CMA25-1030, C-4N-H5HG-CMA26-1020 | C-4N-H5HG-CMA25-1030: SS, C-4N-H5HG-CMA26-1020: FS | 2025-04-05 13:00 | 2025-04-07 13:00
C-4N-H5HG-CMA25-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 | Section Tie-in Welding | C-4N-H5HG-CMA25-1020 | C-4N-H5HG-CMA25-1020: SS | C-4N-H5HG-CMA25-1040, ML1909-E36 | C-4N-H5HG-CMA25-1040: SS 1, ML1909-E36: FS | 2025-04-05 13:00 | 2025-04-08 13:00
C-4N-H5HG-CMA25-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 | NDT (Tie-in Joint) | C-4N-H5HG-CMA25-1030 | C-4N-H5HG-CMA25-1030: SS 1 | C-4N-H5HG-CMA25-1050 | C-4N-H5HG-CMA25-1050: SS 1 | 2025-04-07 13:00 | 2025-04-09 13:00
C-4N-H5HG-CMA25-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA25-1040 | C-4N-H5HG-CMA25-1040: SS 1 | C-4N-H5HG-CMA25-1060 | C-4N-H5HG-CMA25-1060: FS | 2025-04-08 13:00 | 2025-04-10 13:00
C-4N-H5HG-CMA25-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 | Holiday Testing | C-4N-H5HG-CMA25-1050 | C-4N-H5HG-CMA25-1050: FS | C-4N-H5HG-CMA25-1070 | C-4N-H5HG-CMA25-1070: FS | 2025-04-10 13:00 | 2025-04-11 13:00
C-4N-H5HG-CMA25-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 | Padding | C-4N-H5HG-CMA25-1060 | C-4N-H5HG-CMA25-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-04-11 13:00 | 2025-04-12 13:00
C-4N-H5HG-CMA26-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 | Trench Excavation | C-4N-H5HG-CMA25-1000 | C-4N-H5HG-CMA25-1000: FS | C-4N-H5HG-CMA26-1010, C-4N-H5HG-CMA29-1000 | C-4N-H5HG-CMA26-1010: FF, C-4N-H5HG-CMA29-1000: FS | 2025-04-05 13:00 | 2025-04-12 13:00
C-4N-H5HG-CMA26-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 | Bedding | C-4N-H5HG-CMA26-1000 | C-4N-H5HG-CMA26-1000: FF | C-4N-H5HG-CMA26-1020 | C-4N-H5HG-CMA26-1020: FS | 2025-04-11 13:00 | 2025-04-12 13:00
C-4N-H5HG-CMA26-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 | Lowering | C-4N-H5HG-CMA26-1010, C-4N-H5HG-CMA25-1020 | C-4N-H5HG-CMA26-1010: FS, C-4N-H5HG-CMA25-1020: FS | C-4N-H5HG-CMA26-1030, C-4N-H5HG-CMA29-1020 | C-4N-H5HG-CMA26-1030: SS, C-4N-H5HG-CMA29-1020: FS | 2025-04-12 13:00 | 2025-04-14 13:00
C-4N-H5HG-CMA26-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 | Section Tie-in Welding | C-4N-H5HG-CMA26-1020 | C-4N-H5HG-CMA26-1020: SS | C-4N-H5HG-CMA26-1040, ML1909-E36 | C-4N-H5HG-CMA26-1040: SS 1, ML1909-E36: FS | 2025-04-12 13:00 | 2025-04-15 13:00
C-4N-H5HG-CMA26-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 | NDT (Tie-in Joint) | C-4N-H5HG-CMA26-1030 | C-4N-H5HG-CMA26-1030: SS 1 | C-4N-H5HG-CMA26-1050 | C-4N-H5HG-CMA26-1050: SS 1 | 2025-04-14 13:00 | 2025-04-16 13:00
C-4N-H5HG-CMA26-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA26-1040 | C-4N-H5HG-CMA26-1040: SS 1 | C-4N-H5HG-CMA26-1060 | C-4N-H5HG-CMA26-1060: FS | 2025-04-15 13:00 | 2025-04-17 13:00
C-4N-H5HG-CMA26-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 | Holiday Testing | C-4N-H5HG-CMA26-1050 | C-4N-H5HG-CMA26-1050: FS | C-4N-H5HG-CMA26-1070 | C-4N-H5HG-CMA26-1070: FS | 2025-04-17 13:00 | 2025-04-18 13:00
C-4N-H5HG-CMA26-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 | Padding | C-4N-H5HG-CMA26-1060 | C-4N-H5HG-CMA26-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-04-18 13:00 | 2025-04-19 13:00
C-4N-H5HG-CMA29-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 | Trench Excavation | C-4N-H5HG-CMA26-1000 | C-4N-H5HG-CMA26-1000: FS | C-4N-H5HG-CMA29-1010 | C-4N-H5HG-CMA29-1010: FF | 2025-04-12 13:00 | 2025-04-19 13:00
C-4N-H5HG-CMA29-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 | Bedding | C-4N-H5HG-CMA29-1000 | C-4N-H5HG-CMA29-1000: FF | C-4N-H5HG-CMA29-1020 | C-4N-H5HG-CMA29-1020: FS | 2025-04-18 13:00 | 2025-04-19 13:00
C-4N-H5HG-CMA29-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 | Lowering | C-4N-H5HG-CMA29-1010, C-4N-H5HG-CMA26-1020 | C-4N-H5HG-CMA29-1010: FS, C-4N-H5HG-CMA26-1020: FS | C-4N-H5HG-CMA29-1030 | C-4N-H5HG-CMA29-1030: SS | 2025-04-19 13:00 | 2025-04-21 13:00
C-4N-H5HG-CMA29-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 | Section Tie-in Welding | C-4N-H5HG-CMA29-1020 | C-4N-H5HG-CMA29-1020: SS | C-4N-H5HG-CMA29-1040, ML1909-E36 | C-4N-H5HG-CMA29-1040: SS 1, ML1909-E36: FS | 2025-04-19 13:00 | 2025-04-22 13:00
C-4N-H5HG-CMA29-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 | NDT (Tie-in Joint) | C-4N-H5HG-CMA29-1030 | C-4N-H5HG-CMA29-1030: SS 1 | C-4N-H5HG-CMA29-1050 | C-4N-H5HG-CMA29-1050: SS 1 | 2025-04-21 13:00 | 2025-04-23 13:00
C-4N-H5HG-CMA29-1050 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA29-1040 | C-4N-H5HG-CMA29-1040: SS 1 | C-4N-H5HG-CMA29-1060 | C-4N-H5HG-CMA29-1060: FS | 2025-04-22 13:00 | 2025-04-24 13:00
C-4N-H5HG-CMA29-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 | Holiday Testing | C-4N-H5HG-CMA29-1050 | C-4N-H5HG-CMA29-1050: FS | C-4N-H5HG-CMA29-1070 | C-4N-H5HG-CMA29-1070: FS | 2025-04-24 13:00 | 2025-04-25 13:00
C-4N-H5HG-CMA29-1070 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 | Padding | C-4N-H5HG-CMA29-1060 | C-4N-H5HG-CMA29-1060: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-04-25 13:00 | 2025-04-26 13:00
C-4N-H5HG-CNH01-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CMA13-1000, C-PER-1480 | C-4N-H5HG-CMA13-1000: FS 7, C-PER-1480: FS | C-4N-H5HG-CNH01-1010, C-4N-H5HG-CNH02-1000 | C-4N-H5HG-CNH01-1010: SS, C-4N-H5HG-CNH02-1000: FS | 2025-02-28 07:00 | 2025-03-09 11:00
C-4N-H5HG-CNH01-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH01-1000 | C-4N-H5HG-CNH01-1000: SS | C-4N-H5HG-CNH01-1020 | C-4N-H5HG-CNH01-1020: FS | 2025-02-28 07:00 | 2025-03-09 11:00
C-4N-H5HG-CNH01-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH01-1010 | C-4N-H5HG-CNH01-1010: FS | C-4N-H5HG-CNH01-1030, ML1909-E36 | C-4N-H5HG-CNH01-1030: FS, ML1909-E36: FS | 2025-03-09 11:00 | 2025-03-22 09:00
C-4N-H5HG-CNH01-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH01-1020 | C-4N-H5HG-CNH01-1020: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, PRECOM-4N-H5HG-1000, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, PRECOM-4N-H5HG-1000: FS, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-03-22 09:00 | 2025-03-26 11:00
C-4N-H5HG-CNH02-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CNH01-1000, C-PER-1490 | C-4N-H5HG-CNH01-1000: FS, C-PER-1490: FS | C-4N-H5HG-CNH02-1010, C-4N-H5HG-CNH03-1000 | C-4N-H5HG-CNH02-1010: SS, C-4N-H5HG-CNH03-1000: FS | 2025-03-09 11:00 | 2025-03-20 11:00
C-4N-H5HG-CNH02-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH02-1000 | C-4N-H5HG-CNH02-1000: SS | C-4N-H5HG-CNH02-1020 | C-4N-H5HG-CNH02-1020: FS | 2025-03-09 11:00 | 2025-03-20 11:00
C-4N-H5HG-CNH02-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH02-1010 | C-4N-H5HG-CNH02-1010: FS | C-4N-H5HG-CNH02-1030, ML1909-E36 | C-4N-H5HG-CNH02-1030: FS, ML1909-E36: FS | 2025-03-20 11:00 | 2025-04-04 13:00
C-4N-H5HG-CNH02-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH02-1020 | C-4N-H5HG-CNH02-1020: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, PRECOM-4N-H5HG-1000, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, PRECOM-4N-H5HG-1000: FS, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-04-04 13:00 | 2025-04-08 13:00
C-4N-H5HG-CNH03-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CNH02-1000, C-PER-1500 | C-4N-H5HG-CNH02-1000: FS, C-PER-1500: FS | C-4N-H5HG-CNH03-1010, C-4N-H5HG-CNH04-1000 | C-4N-H5HG-CNH03-1010: SS, C-4N-H5HG-CNH04-1000: FS | 2025-03-20 11:00 | 2025-04-03 13:00
C-4N-H5HG-CNH03-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH03-1000 | C-4N-H5HG-CNH03-1000: SS | C-4N-H5HG-CNH03-1020 | C-4N-H5HG-CNH03-1020: FS | 2025-03-20 11:00 | 2025-04-03 13:00
C-4N-H5HG-CNH03-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH03-1010 | C-4N-H5HG-CNH03-1010: FS | C-4N-H5HG-CNH03-1030, ML1909-E36 | C-4N-H5HG-CNH03-1030: FS, ML1909-E36: FS | 2025-04-03 13:00 | 2025-04-12 13:00
C-4N-H5HG-CNH03-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH03-1020 | C-4N-H5HG-CNH03-1020: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, PRECOM-4N-H5HG-1000, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, PRECOM-4N-H5HG-1000: FS, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-04-12 13:00 | 2025-04-16 13:00
C-4N-H5HG-CNH04-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CNH03-1000, C-PER-1510 | C-4N-H5HG-CNH03-1000: FS, C-PER-1510: FS | C-4N-H5HG-CNH04-1010, C-4N-H5HG-CNH05-1000 | C-4N-H5HG-CNH04-1010: SS, C-4N-H5HG-CNH05-1000: FS | 2025-04-03 13:00 | 2025-04-11 13:00
C-4N-H5HG-CNH04-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH04-1000 | C-4N-H5HG-CNH04-1000: SS | C-4N-H5HG-CNH04-1020 | C-4N-H5HG-CNH04-1020: FS | 2025-04-03 13:00 | 2025-04-11 13:00
C-4N-H5HG-CNH04-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH04-1010 | C-4N-H5HG-CNH04-1010: FS | C-4N-H5HG-CNH04-1030, ML1909-E36 | C-4N-H5HG-CNH04-1030: FS, ML1909-E36: FS | 2025-04-11 13:00 | 2025-04-21 13:00
C-4N-H5HG-CNH04-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH04-1020 | C-4N-H5HG-CNH04-1020: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, PRECOM-4N-H5HG-1000, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, PRECOM-4N-H5HG-1000: FS, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-04-21 13:00 | 2025-04-24 13:00
C-4N-H5HG-CNH05-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CNH04-1000, C-PER-1520 | C-4N-H5HG-CNH04-1000: FS, C-PER-1520: FS | C-4N-H5HG-CNH05-1010, C-4N-H5HG-CNH06-1000 | C-4N-H5HG-CNH05-1010: SS, C-4N-H5HG-CNH06-1000: FS | 2025-04-11 13:00 | 2025-04-19 13:00
C-4N-H5HG-CNH05-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH05-1000 | C-4N-H5HG-CNH05-1000: SS | C-4N-H5HG-CNH05-1020 | C-4N-H5HG-CNH05-1020: FS | 2025-04-11 13:00 | 2025-04-19 13:00
C-4N-H5HG-CNH05-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH05-1010 | C-4N-H5HG-CNH05-1010: FS | C-4N-H5HG-CNH05-1030, ML1909-E36 | C-4N-H5HG-CNH05-1030: FS, ML1909-E36: FS | 2025-04-19 13:00 | 2025-04-29 13:00
C-4N-H5HG-CNH05-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH05-1020 | C-4N-H5HG-CNH05-1020: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, PRECOM-4N-H5HG-1000, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, PRECOM-4N-H5HG-1000: FS, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-04-29 13:00 | 2025-05-02 13:00
C-4N-H5HG-CNH06-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CNH05-1000, C-PER-1530 | C-4N-H5HG-CNH05-1000: FS, C-PER-1530: FS | C-4N-H5HG-CNH06-1010, C-4N-H5HG-CNH07-1000 | C-4N-H5HG-CNH06-1010: SS, C-4N-H5HG-CNH07-1000: FS | 2025-04-19 13:00 | 2025-04-28 13:00
C-4N-H5HG-CNH06-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH06-1000 | C-4N-H5HG-CNH06-1000: SS | C-4N-H5HG-CNH06-1020 | C-4N-H5HG-CNH06-1020: FS | 2025-04-19 13:00 | 2025-04-28 13:00
C-4N-H5HG-CNH06-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH06-1010 | C-4N-H5HG-CNH06-1010: FS | C-4N-H5HG-CNH06-1030, ML1909-E36 | C-4N-H5HG-CNH06-1030: FS, ML1909-E36: FS | 2025-04-28 13:00 | 2025-05-08 10:00
C-4N-H5HG-CNH06-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH06-1020 | C-4N-H5HG-CNH06-1020: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, PRECOM-4N-H5HG-1000, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, PRECOM-4N-H5HG-1000: FS, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-05-08 10:00 | 2025-05-12 11:00
C-4N-H5HG-CNH07-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CNH06-1000, C-PER-1540 | C-4N-H5HG-CNH06-1000: FS, C-PER-1540: FS | C-4N-H5HG-CNH07-1010, C-4N-H5HG-CNH08-1000 | C-4N-H5HG-CNH07-1010: SS, C-4N-H5HG-CNH08-1000: FS | 2025-04-28 13:00 | 2025-05-06 16:00
C-4N-H5HG-CNH07-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH07-1000 | C-4N-H5HG-CNH07-1000: SS | C-4N-H5HG-CNH07-1020 | C-4N-H5HG-CNH07-1020: FS | 2025-04-28 13:00 | 2025-05-06 16:00
C-4N-H5HG-CNH07-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH07-1010 | C-4N-H5HG-CNH07-1010: FS | C-4N-H5HG-CNH07-1030, ML1909-E36 | C-4N-H5HG-CNH07-1030: FS, ML1909-E36: FS | 2025-05-07 08:00 | 2025-05-16 11:00
C-4N-H5HG-CNH07-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH07-1020 | C-4N-H5HG-CNH07-1020: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, PRECOM-4N-H5HG-1000, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, PRECOM-4N-H5HG-1000: FS, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-05-16 11:00 | 2025-05-20 11:00
C-4N-H5HG-CNH08-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CNH07-1000, C-PER-1550 | C-4N-H5HG-CNH07-1000: FS, C-PER-1550: FS | C-4N-H5HG-CNH08-1010 | C-4N-H5HG-CNH08-1010: SS | 2025-05-07 08:00 | 2025-05-15 11:00
C-4N-H5HG-CNH08-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH08-1000 | C-4N-H5HG-CNH08-1000: SS | C-4N-H5HG-CNH08-1020 | C-4N-H5HG-CNH08-1020: FS | 2025-05-07 08:00 | 2025-05-15 11:00
C-4N-H5HG-CNH08-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH08-1010 | C-4N-H5HG-CNH08-1010: FS | C-4N-H5HG-CNH08-1030, ML1909-E36 | C-4N-H5HG-CNH08-1030: FS, ML1909-E36: FS | 2025-05-15 11:00 | 2025-05-24 11:00
C-4N-H5HG-CNH08-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH08-1020 | C-4N-H5HG-CNH08-1020: FS | C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-5220, C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-8200, PRECOM-4N-H5HG-1000, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-5220: FF 1, C-4N-H5HG-PIPEL-6800: FS, C-4N-H5HG-PIPEL-8200: FF 1, PRECOM-4N-H5HG-1000: FS, C-4N-H5HG-PIPEL-8400: FF 1 | 2025-05-24 11:00 | 2025-05-28 11:00
C-4N-H5HG-PIPEL-5600 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.19 | Installation of Temp. Anode | C-4N-H5HG-PIPEL-4830, C-4N-H5HG-PIPEL-5030 | C-4N-H5HG-PIPEL-4830: SS, C-4N-H5HG-PIPEL-5030: SS | C-4N-H5HG-PIPEL-5200, C-4N-H5HG-PIPEL-6000, C-4N-H5HG-PIPEL-6000 | C-4N-H5HG-PIPEL-5200: SS, C-4N-H5HG-PIPEL-6000: SS 2, C-4N-H5HG-PIPEL-6000: FF 2 | 2025-05-14 12:30 | 2025-07-18 12:30
C-4N-H5HG-PIPEL-5200 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.27 | Installation of CP Test Post | C-4N-H5HG-PIPEL-5600, ML1159-A08 | C-4N-H5HG-PIPEL-5600: SS, ML1159-A08: FS | C-4N-H5HG-PIPEL-5210 | C-4N-H5HG-PIPEL-5210: FS | 2025-05-14 12:30 | 2025-07-18 12:30
C-4N-H5HG-PIPEL-5210 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.27 | Glanding & Termination of Temp. CP S/m | C-4N-H5HG-PIPEL-5200 | C-4N-H5HG-PIPEL-5200: FS | C-4N-H5HG-PIPEL-5250, PRECOM-4N-H5HG-1000 | C-4N-H5HG-PIPEL-5250: FS, PRECOM-4N-H5HG-1000: FS | 2025-07-18 12:30 | 2025-07-19 12:30
C-4N-H5HG-PIPEL-5220 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.30 | Installation of Test Post for Crossing | C-4N-H5HG-CMA13-1060, C-4N-H5HG-CMA01-1070, C-4N-H5HG-CMA02-1070, C-4N-H5HG-CMA03-1070, C-4N-H5HG-CMA04-1070, C-4N-H5HG-CMA05-1070, C-4N-H5HG-CMA06-1070, C-4N-H5HG-CMA07-1070, C-4N-H5HG-CMA08-1070, C-4N-H5HG-CMA09-1070, C-4N-H5HG-CMA10-1070, C-4N-H5HG-CMA1 | C-4N-H5HG-CMA13-1060: SS, C-4N-H5HG-CMA01-1070: FF 1, C-4N-H5HG-CMA02-1070: FF 1, C-4N-H5HG-CMA03-1070: FF 1, C-4N-H5HG-CMA04-1070: FF 1, C-4N-H5HG-CMA05-1070: FF 1, C-4N-H5HG-CMA06-1070: FF 1, C-4N-H5HG-CMA07-1070: FF 1, C-4N-H5HG-CMA08-1070: FF 1, C-4N-H | C-4N-H5HG-PIPEL-5230 | C-4N-H5HG-PIPEL-5230: SS 1 | 2025-03-19 07:00 | 2025-05-29 11:00
C-4N-H5HG-PIPEL-5230 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.30 | Installation of CP JB's | C-4N-H5HG-PIPEL-5220 | C-4N-H5HG-PIPEL-5220: SS 1 | C-4N-H5HG-PIPEL-5240 | C-4N-H5HG-PIPEL-5240: FF 1 | 2025-03-20 11:00 | 2025-05-30 11:00
C-4N-H5HG-PIPEL-5240 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.30 | Installation of CP TR | C-4N-H5HG-PIPEL-5230 | C-4N-H5HG-PIPEL-5230: FF 1 | C-4N-H5HG-PIPEL-5250 | C-4N-H5HG-PIPEL-5250: FS | 2025-05-01 13:00 | 2025-05-31 11:00
C-4N-H5HG-PIPEL-5250 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.30 | CIP/DCVG Survey | C-4N-H5HG-PIPEL-5240, C-4N-H5HG-PIPEL-5210 | C-4N-H5HG-PIPEL-5240: FS, C-4N-H5HG-PIPEL-5210: FS | PRECOM-4N-H5HG-1000 | PRECOM-4N-H5HG-1000: FS | 2025-07-19 12:30 | 2025-07-28 12:30
C-4N-H5HG-PIPEL-8200 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.2.1 | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-PIPEL-4830, C-4N-H5HG-CMA13-1070, C-4N-H5HG-CMA01-1070, C-4N-H5HG-CMA02-1070, C-4N-H5HG-CMA03-1070, C-4N-H5HG-CMA04-1070, C-4N-H5HG-CMA05-1070, C-4N-H5HG-CMA06-1070, C-4N-H5HG-CMA07-1070, C-4N-H5HG-CMA08-1070, C-4N-H5HG-CMA09-1070, C-4N-H5HG-CMA1 | C-4N-H5HG-PIPEL-4830: SS, C-4N-H5HG-CMA13-1070: FF 1, C-4N-H5HG-CMA01-1070: FF 1, C-4N-H5HG-CMA02-1070: FF 1, C-4N-H5HG-CMA03-1070: FF 1, C-4N-H5HG-CMA04-1070: FF 1, C-4N-H5HG-CMA05-1070: FF 1, C-4N-H5HG-CMA06-1070: FF 1, C-4N-H5HG-CMA07-1070: FF 1, C-4N-H | C-4N-H5HG-PIPEL-8210, C-4N-H5HG-PIPEL-8410 | C-4N-H5HG-PIPEL-8210: FS, C-4N-H5HG-PIPEL-8410: FS | 2025-05-29 12:30 | 2025-07-24 12:30
C-4N-H5HG-PIPEL-8210 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.2.1 | Termination/Splicing @ HGCP | C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-8200: FS, C-4N-H5HG-PIPEL-8400: FS | PRECOM-4N-H5HG-1000 | PRECOM-4N-H5HG-1000: FS | 2025-07-24 12:30 | 2025-07-28 12:30
C-4N-H5HG-PIPEL-7400 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.31 | Cleaning & Gauging | C-4N-H5HG-PIPEL-6000, C-4N-H5HG-CMA13-1070, C-4N-H5HG-CMA01-1070, C-4N-H5HG-CMA02-1070, C-4N-H5HG-CMA03-1070, C-4N-H5HG-CMA04-1070, C-4N-H5HG-CMA05-1070, C-4N-H5HG-CMA06-1070, C-4N-H5HG-CMA07-1070, C-4N-H5HG-CMA08-1070, C-4N-H5HG-CMA09-1070, C-4N-H5HG-CMA1 | C-4N-H5HG-PIPEL-6000: FS, C-4N-H5HG-CMA13-1070: FS, C-4N-H5HG-CMA01-1070: FS, C-4N-H5HG-CMA02-1070: FS, C-4N-H5HG-CMA03-1070: FS, C-4N-H5HG-CMA04-1070: FS, C-4N-H5HG-CMA05-1070: FS, C-4N-H5HG-CMA06-1070: FS, C-4N-H5HG-CMA07-1070: FS, C-4N-H5HG-CMA08-1070: | C-4N-H5HG-PIPEL-7410 | C-4N-H5HG-PIPEL-7410: FS | 2025-08-18 12:30 | 2025-08-21 12:30
C-4N-H5HG-PIPEL-7410 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.31 | Water Filling | C-4N-H5HG-PIPEL-7400 | C-4N-H5HG-PIPEL-7400: FS | C-4N-H5HG-PIPEL-7420 | C-4N-H5HG-PIPEL-7420: FS | 2025-08-21 12:30 | 2025-08-27 12:30
C-4N-H5HG-PIPEL-7420 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.31 | Pressurization | C-4N-H5HG-PIPEL-7410 | C-4N-H5HG-PIPEL-7410: FS | C-4N-H5HG-PIPEL-7430 | C-4N-H5HG-PIPEL-7430: FS | 2025-08-27 12:30 | 2025-08-30 12:30
C-4N-H5HG-PIPEL-7430 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.31 | Holding of Test Pressure | C-4N-H5HG-PIPEL-7420 | C-4N-H5HG-PIPEL-7420: FS | C-4N-H5HG-PIPEL-7600, ML1919-E37 | C-4N-H5HG-PIPEL-7600: FS, ML1919-E37: FS | 2025-08-30 12:30 | 2025-09-01 12:30
C-4N-H5HG-PIPEL-7600 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.32 | De-Pressurization | C-4N-H5HG-PIPEL-7430 | C-4N-H5HG-PIPEL-7430: FS | C-4N-H5HG-PIPEL-7610 | C-4N-H5HG-PIPEL-7610: FS | 2025-09-01 12:30 | 2025-09-03 12:30
C-4N-H5HG-PIPEL-7610 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.32 | De-watering | C-4N-H5HG-PIPEL-7600 | C-4N-H5HG-PIPEL-7600: FS | C-4N-H5HG-PIPEL-7620 | C-4N-H5HG-PIPEL-7620: FS | 2025-09-03 12:30 | 2025-09-08 12:30
C-4N-H5HG-PIPEL-7620 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.32 | Swabing & Drying (Upto Dew Point Temp.) | C-4N-H5HG-PIPEL-7610 | C-4N-H5HG-PIPEL-7610: FS | PRECOM-4N-H5HG-1000, ML1919-E37 | PRECOM-4N-H5HG-1000: FS, ML1919-E37: FS | 2025-09-08 12:30 | 2025-09-13 12:30
C-4N-H5HG-PIPEL-6800 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.18 | Gatch Laying & Levelling | C-4N-H5HG-CMA13-1070, C-4N-H5HG-CMA01-1070, C-4N-H5HG-CMA02-1070, C-4N-H5HG-CMA03-1070, C-4N-H5HG-CMA04-1070, C-4N-H5HG-CMA05-1070, C-4N-H5HG-CMA06-1070, C-4N-H5HG-CMA07-1070, C-4N-H5HG-CMA08-1070, C-4N-H5HG-CMA09-1070, C-4N-H5HG-CMA10-1070, C-4N-H5HG-CMA1 | C-4N-H5HG-CMA13-1070: FS, C-4N-H5HG-CMA01-1070: FS, C-4N-H5HG-CMA02-1070: FS, C-4N-H5HG-CMA03-1070: FS, C-4N-H5HG-CMA04-1070: FS, C-4N-H5HG-CMA05-1070: FS, C-4N-H5HG-CMA06-1070: FS, C-4N-H5HG-CMA07-1070: FS, C-4N-H5HG-CMA08-1070: FS, C-4N-H5HG-CMA09-1070: | C-4N-H5HG-PIPEL-6810, C-4N-H5HG-PIPEL-7800 | C-4N-H5HG-PIPEL-6810: SS 2, C-4N-H5HG-PIPEL-7800: SS 21 | 2025-06-17 12:30 | 2025-08-15 12:30
C-4N-H5HG-PIPEL-6810 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.18 | Gatch Compaction | C-4N-H5HG-PIPEL-6800 | C-4N-H5HG-PIPEL-6800: SS 2 | PRECOM-4N-H5HG-1000, C-4N-H5HG-PIPEL-7400 | PRECOM-4N-H5HG-1000: FS, C-4N-H5HG-PIPEL-7400: FS | 2025-06-19 12:30 | 2025-08-18 12:30
C-4N-H5HG-PIPEL-7800 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.33 | ROW Restoration/ Installation of Marker Post/Sign Board | C-4N-H5HG-PIPEL-6800 | C-4N-H5HG-PIPEL-6800: SS 21 | C-4N-H5HG-PIPEL-7810, ML1949-E40 | C-4N-H5HG-PIPEL-7810: FF 5, ML1949-E40: FS | 2025-07-12 12:30 | 2025-08-16 12:30
C-4N-H5HG-PIPEL-7810 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.33 | Installation of Crash Barriers (If any) | C-4N-H5HG-PIPEL-7800 | C-4N-H5HG-PIPEL-7800: FF 5 | PRECOM-4N-H5HG-1000, ML1949-E40 | PRECOM-4N-H5HG-1000: FS, ML1949-E40: FS | 2025-07-18 12:30 | 2025-08-22 12:30
C-4W-SVHG-PIPEL-1000 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Survey Marking | HM-PL-0100, HM-PL-0110, HE-PL-0290, ML1169-A09, HM-PL-0110, HM-PL-0110 | HM-PL-0100: FS, HM-PL-0110: SS 21, HE-PL-0290: FS, ML1169-A09: FS, HM-PL-0110: FS 15, HM-PL-0110: FF | C-4W-SVHG-PIPEL-1800 | C-4W-SVHG-PIPEL-1800: FS | 2025-01-11 07:00 | 2025-01-13 17:00
C-4W-SVHG-PIPEL-1800 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Sabka ROW/Grading | C-4W-SVHG-PIPEL-1000 | C-4W-SVHG-PIPEL-1000: FS | C-4W-SVHG-PIPEL-2000 | C-4W-SVHG-PIPEL-2000: FS | 2025-01-14 07:00 | 2025-01-15 17:00
C-4W-SVHG-PIPEL-2000 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Sabka Gatch Laying (Including ROW) - Layer 1 | C-4W-SVHG-PIPEL-1800 | C-4W-SVHG-PIPEL-1800: FS | C-4W-SVHG-PIPEL-2200, C-4W-SVHG-PIPEL-2010 | C-4W-SVHG-PIPEL-2200: SS 1, C-4W-SVHG-PIPEL-2010: FS | 2025-01-16 07:00 | 2025-01-18 17:00
C-4W-SVHG-PIPEL-2010 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Sabka Gatch Laying - Layer 2 | C-4W-SVHG-PIPEL-2000 | C-4W-SVHG-PIPEL-2000: FS | C-4W-SVHG-PIPEL-2210, C-4W-SVHG-PIPEL-2020 | C-4W-SVHG-PIPEL-2210: SS 1, C-4W-SVHG-PIPEL-2020: FS | 2025-01-20 07:00 | 2025-01-22 17:00
C-4W-SVHG-PIPEL-2020 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Sabka Gatch Laying - Layer 3 | C-4W-SVHG-PIPEL-2010 | C-4W-SVHG-PIPEL-2010: FS | C-4W-SVHG-PIPEL-2220, C-4W-SVHG-PIPEL-2030 | C-4W-SVHG-PIPEL-2220: SS 1, C-4W-SVHG-PIPEL-2030: FS | 2025-01-23 07:00 | 2025-01-25 17:00
C-4W-SVHG-PIPEL-2030 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Sabka Gatch Laying - Layer 4 | C-4W-SVHG-PIPEL-2020 | C-4W-SVHG-PIPEL-2020: FS | C-4W-SVHG-PIPEL-2230 | C-4W-SVHG-PIPEL-2230: SS 1 | 2025-01-27 07:00 | 2025-01-29 17:00
C-4W-SVHG-PIPEL-2200 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-4W-SVHG-PIPEL-2000 | C-4W-SVHG-PIPEL-2000: SS 1 | C-4W-SVHG-PIPEL-2210 | C-4W-SVHG-PIPEL-2210: FS | 2025-01-17 07:00 | 2025-01-20 17:00
C-4W-SVHG-PIPEL-2210 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Sabka Gatch Compaction - Layer 2 | C-4W-SVHG-PIPEL-2010, C-4W-SVHG-PIPEL-2200 | C-4W-SVHG-PIPEL-2010: SS 1, C-4W-SVHG-PIPEL-2200: FS | C-4W-SVHG-PIPEL-2220 | C-4W-SVHG-PIPEL-2220: FS | 2025-01-21 07:00 | 2025-01-23 17:00
C-4W-SVHG-PIPEL-2220 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Sabka Gatch Compaction - Layer 3 | C-4W-SVHG-PIPEL-2020, C-4W-SVHG-PIPEL-2210 | C-4W-SVHG-PIPEL-2020: SS 1, C-4W-SVHG-PIPEL-2210: FS | C-4W-SVHG-PIPEL-2230 | C-4W-SVHG-PIPEL-2230: FS | 2025-01-24 07:00 | 2025-01-27 17:00
C-4W-SVHG-PIPEL-2230 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Sabka Gatch Compaction - Layer 4 | C-4W-SVHG-PIPEL-2220, C-4W-SVHG-PIPEL-2030 | C-4W-SVHG-PIPEL-2220: FS, C-4W-SVHG-PIPEL-2030: SS 1 | C-4W-SVHG-PIPEL-2800, C-4W-SVHG-PIPEL-2400, ML1869-E32 | C-4W-SVHG-PIPEL-2800: FS, C-4W-SVHG-PIPEL-2400: FS 2, ML1869-E32: FS | 2025-01-28 07:00 | 2025-01-30 17:00
C-4W-SVHG-PIPEL-2800 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Stringing (SV-03 to HGCP) | C-4W-SVHG-PIPEL-2230 | C-4W-SVHG-PIPEL-2230: FS | C-4W-SVHG-PIPEL-3100, CPL-4-CRMN-3340 | C-4W-SVHG-PIPEL-3100: SS, CPL-4-CRMN-3340: FS | 2025-01-31 07:00 | 2025-02-08 17:00
C-4W-SVHG-PIPEL-3100 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Field Joint | C-4W-SVHG-PIPEL-2800 | C-4W-SVHG-PIPEL-2800: SS | C-4W-SVHG-PIPEL-3110 | C-4W-SVHG-PIPEL-3110: SS 1 | 2025-01-31 07:00 | 2025-02-08 17:00
C-4W-SVHG-PIPEL-3110 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Field Joint Protection Sleeve | C-4W-SVHG-PIPEL-3100 | C-4W-SVHG-PIPEL-3100: SS 1 | C-4W-SVHG-PIPEL-4800 | C-4W-SVHG-PIPEL-4800: SS 3 | 2025-02-01 07:00 | 2025-02-10 17:00
C-4W-SVHG-PIPEL-2400 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Trench Excavation | C-4W-SVHG-PIPEL-2230 | C-4W-SVHG-PIPEL-2230: FS 2 | C-4W-SVHG-PIPEL-2410, CPL-4-CRMN-3320, C-4N-H5HG-CNH1-1000 | C-4W-SVHG-PIPEL-2410: SS, CPL-4-CRMN-3320: FS, C-4N-H5HG-CNH1-1000: FS | 2025-02-03 07:00 | 2025-02-11 17:00
C-4W-SVHG-PIPEL-2410 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Bedding | C-4W-SVHG-PIPEL-2400 | C-4W-SVHG-PIPEL-2400: SS | C-4W-SVHG-PIPEL-4800 | C-4W-SVHG-PIPEL-4800: FF 1 | 2025-02-03 07:00 | 2025-02-11 17:00
C-4W-SVHG-PIPEL-4800 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Lowering | C-4W-SVHG-PIPEL-2410, C-4W-SVHG-PIPEL-3110 | C-4W-SVHG-PIPEL-2410: FF 1, C-4W-SVHG-PIPEL-3110: SS 3 | C-4W-SVHG-PIPEL-4810 | C-4W-SVHG-PIPEL-4810: FS | 2025-02-05 07:00 | 2025-02-13 17:00
C-4W-SVHG-PIPEL-4810 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Section Tie-in Joint | C-4W-SVHG-PIPEL-4800 | C-4W-SVHG-PIPEL-4800: FS | C-4W-SVHG-PIPEL-3120, ML1879-E33 | C-4W-SVHG-PIPEL-3120: FS, ML1879-E33: FS | 2025-02-14 07:00 | 2025-02-14 17:00
C-4W-SVHG-PIPEL-3120 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Field Joint Protection Sleeve | C-4W-SVHG-PIPEL-4810 | C-4W-SVHG-PIPEL-4810: FS | C-4W-SVHG-PIPEL-6000 | C-4W-SVHG-PIPEL-6000: FS | 2025-02-15 07:00 | 2025-02-15 17:00
C-4W-SVHG-PIPEL-6000 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6 | Padding | C-4W-SVHG-PIPEL-3120 | C-4W-SVHG-PIPEL-3120: FS | C-4W-SVHG-PIPEL-7400, C-4W-SVHG-PIPEL-6800, PRECOM-4W-SVHG-1000 | C-4W-SVHG-PIPEL-7400: FS, C-4W-SVHG-PIPEL-6800: FS, PRECOM-4W-SVHG-1000: FS | 2025-02-17 07:00 | 2025-02-22 17:00
CPL-4-CRMN-3320 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 | Trench Excavation | C-4W-SVHG-PIPEL-2400 | C-4W-SVHG-PIPEL-2400: FS | CPL-4-CRMN-3330, CPL-4-CRMN-3400 | CPL-4-CRMN-3330: FF, CPL-4-CRMN-3400: FS | 2025-02-12 07:00 | 2025-02-15 17:00
CPL-4-CRMN-3330 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 | Bedding | CPL-4-CRMN-3320 | CPL-4-CRMN-3320: FF | CPL-4-CRMN-3340 | CPL-4-CRMN-3340: FS | 2025-02-15 07:00 | 2025-02-15 17:00
CPL-4-CRMN-3340 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 | Lowering | CPL-4-CRMN-3330, C-4W-SVHG-PIPEL-2800 | CPL-4-CRMN-3330: FS, C-4W-SVHG-PIPEL-2800: FS | CPL-4-CRMN-3350, CPL-4-CRMN-3420 | CPL-4-CRMN-3350: SS, CPL-4-CRMN-3420: FS | 2025-02-17 07:00 | 2025-02-17 17:00
CPL-4-CRMN-3350 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 | Section Tie-in Joint | CPL-4-CRMN-3340 | CPL-4-CRMN-3340: SS | CPL-4-CRMN-3370, ML1879-E33 | CPL-4-CRMN-3370: SS, ML1879-E33: FS | 2025-02-17 07:00 | 2025-02-17 17:00
CPL-4-CRMN-3370 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 | Field Joint Protection Sleeve | CPL-4-CRMN-3350 | CPL-4-CRMN-3350: SS | CPL-4-CRMN-3390 | CPL-4-CRMN-3390: FS | 2025-02-17 07:00 | 2025-02-17 17:00
CPL-4-CRMN-3390 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 | Padding | CPL-4-CRMN-3370 | CPL-4-CRMN-3370: FS | C-4W-SVHG-PIPEL-7400, C-4W-SVHG-PIPEL-6800 | C-4W-SVHG-PIPEL-7400: FS, C-4W-SVHG-PIPEL-6800: FS | 2025-02-18 07:00 | 2025-02-18 17:00
C-4N-H5HG-CNH1-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 | Excavation for Entry & Exit Pit Preparation | C-4W-SVHG-PIPEL-2400, C-PER-1560 | C-4W-SVHG-PIPEL-2400: FS, C-PER-1560: FS | C-4N-H5HG-CNH1-1010, C-4N-H5HG-CNH2-1000 | C-4N-H5HG-CNH1-1010: SS, C-4N-H5HG-CNH2-1000: FS | 2025-02-12 07:00 | 2025-02-17 17:00
C-4N-H5HG-CNH1-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH1-1000 | C-4N-H5HG-CNH1-1000: SS | C-4N-H5HG-CNH1-1020 | C-4N-H5HG-CNH1-1020: FS | 2025-02-12 07:00 | 2025-02-15 17:00
C-4N-H5HG-CNH1-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH1-1010 | C-4N-H5HG-CNH1-1010: FS | C-4N-H5HG-CNH1-1030, ML1909-E36 | C-4N-H5HG-CNH1-1030: FS, ML1909-E36: FS | 2025-02-17 07:00 | 2025-02-20 17:00
C-4N-H5HG-CNH1-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH1-1020 | C-4N-H5HG-CNH1-1020: FS | C-4W-SVHG-PIPEL-7400, C-4W-SVHG-PIPEL-6800, PRECOM-4W-SVHG-1000 | C-4W-SVHG-PIPEL-7400: FS, C-4W-SVHG-PIPEL-6800: FS, PRECOM-4W-SVHG-1000: FS | 2025-02-21 07:00 | 2025-02-22 17:00
C-4N-H5HG-CNH2-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.9.1 | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CNH1-1000, C-PER-1570 | C-4N-H5HG-CNH1-1000: FS, C-PER-1570: FS | C-4N-H5HG-CNH2-1010 | C-4N-H5HG-CNH2-1010: SS | 2025-03-13 07:00 | 2025-03-20 11:00
C-4N-H5HG-CNH2-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.9.1 | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH2-1000 | C-4N-H5HG-CNH2-1000: SS | C-4N-H5HG-CNH2-1020 | C-4N-H5HG-CNH2-1020: FS | 2025-03-13 07:00 | 2025-03-18 13:00
C-4N-H5HG-CNH2-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.9.1 | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH2-1010 | C-4N-H5HG-CNH2-1010: FS | C-4N-H5HG-CNH2-1030, ML1909-E36 | C-4N-H5HG-CNH2-1030: FS, ML1909-E36: FS | 2025-03-19 07:00 | 2025-03-24 13:00
C-4N-H5HG-CNH2-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.3.9.1 | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH2-1020 | C-4N-H5HG-CNH2-1020: FS | C-4W-SVHG-PIPEL-7400, C-4W-SVHG-PIPEL-6800, PRECOM-4W-SVHG-1000 | C-4W-SVHG-PIPEL-7400: FS, C-4W-SVHG-PIPEL-6800: FS, PRECOM-4W-SVHG-1000: FS | 2025-03-25 07:00 | 2025-03-28 09:00
C-4W-SVHG-PIPEL-7400 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.3 | Cleaning & Gauging | C-4W-SVHG-PIPEL-6000, CPL-4-CRMN-3390, CPL-4-CRMN-3450, CPL-4-CRMN-3510, CPL-4-CRMN-3570, CPL-4-CRMN-3630, C-4N-H5HG-CNH1-1030, C-4N-H5HG-CNH2-1030, C-4W-SVHG-PIPEL-6810 | C-4W-SVHG-PIPEL-6000: FS, CPL-4-CRMN-3390: FS, CPL-4-CRMN-3450: FS, CPL-4-CRMN-3510: FS, CPL-4-CRMN-3570: FS, CPL-4-CRMN-3630: FS, C-4N-H5HG-CNH1-1030: FS, C-4N-H5HG-CNH2-1030: FS, C-4W-SVHG-PIPEL-6810: FS | C-4W-SVHG-PIPEL-7410 | C-4W-SVHG-PIPEL-7410: FS | 2025-04-10 13:00 | 2025-04-11 13:00
C-4W-SVHG-PIPEL-7410 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.3 | Water Filling | C-4W-SVHG-PIPEL-7400 | C-4W-SVHG-PIPEL-7400: FS | C-4W-SVHG-PIPEL-7420 | C-4W-SVHG-PIPEL-7420: FS | 2025-04-11 13:00 | 2025-04-12 13:00
C-4W-SVHG-PIPEL-7420 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.3 | Pressurization | C-4W-SVHG-PIPEL-7410 | C-4W-SVHG-PIPEL-7410: FS | C-4W-SVHG-PIPEL-7430 | C-4W-SVHG-PIPEL-7430: FS | 2025-04-12 13:00 | 2025-04-14 13:00
C-4W-SVHG-PIPEL-7430 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.3 | Holding of Test Pressure | C-4W-SVHG-PIPEL-7420 | C-4W-SVHG-PIPEL-7420: FS | C-4W-SVHG-PIPEL-7600 | C-4W-SVHG-PIPEL-7600: FS | 2025-04-14 13:00 | 2025-04-15 13:00
C-4W-SVHG-PIPEL-7600 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.3 | De-Pressurization | C-4W-SVHG-PIPEL-7430 | C-4W-SVHG-PIPEL-7430: FS | C-4W-SVHG-PIPEL-7610 | C-4W-SVHG-PIPEL-7610: FS | 2025-04-15 13:00 | 2025-04-16 13:00
C-4W-SVHG-PIPEL-7610 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.3 | De-watering | C-4W-SVHG-PIPEL-7600 | C-4W-SVHG-PIPEL-7600: FS | PRECOM-4W-SVHG-1000, ML1889-E34, ML1939-E39 | PRECOM-4W-SVHG-1000: FS, ML1889-E34: FS, ML1939-E39: FS | 2025-04-16 13:00 | 2025-04-17 13:00
C-4W-SVHG-PIPEL-6800 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.4 | Gatch Laying & Levelling | C-4W-SVHG-PIPEL-6000, CPL-4-CRMN-3390, CPL-4-CRMN-3450, CPL-4-CRMN-3510, CPL-4-CRMN-3570, CPL-4-CRMN-3630, C-4N-H5HG-CNH1-1030, C-4N-H5HG-CNH2-1030 | C-4W-SVHG-PIPEL-6000: FS, CPL-4-CRMN-3390: FS, CPL-4-CRMN-3450: FS, CPL-4-CRMN-3510: FS, CPL-4-CRMN-3570: FS, CPL-4-CRMN-3630: FS, C-4N-H5HG-CNH1-1030: FS, C-4N-H5HG-CNH2-1030: FS | C-4W-SVHG-PIPEL-6810 | C-4W-SVHG-PIPEL-6810: SS 2 | 2025-03-28 09:00 | 2025-04-07 13:00
C-4W-SVHG-PIPEL-6810 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.4 | Gatch Compaction | C-4W-SVHG-PIPEL-6800 | C-4W-SVHG-PIPEL-6800: SS 2 | C-4W-SVHG-PIPEL-7400, C-4W-SVHG-PIPEL-7800, PRECOM-4W-SVHG-1000, ML1939-E39 | C-4W-SVHG-PIPEL-7400: FS, C-4W-SVHG-PIPEL-7800: FS, PRECOM-4W-SVHG-1000: FS, ML1939-E39: FS | 2025-04-03 13:00 | 2025-04-10 13:00
C-4W-SVHG-PIPEL-7800 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.5 | Installation of Marker Post/Sign Board | C-4W-SVHG-PIPEL-6810 | C-4W-SVHG-PIPEL-6810: FS | C-4W-SVHG-PIPEL-7810 | C-4W-SVHG-PIPEL-7810: SS 1 | 2025-04-10 13:00 | 2025-04-11 13:00
C-4W-SVHG-PIPEL-7810 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.5 | Installation of Crash Barriers (If any) | C-4W-SVHG-PIPEL-7800 | C-4W-SVHG-PIPEL-7800: SS 1 | PRECOM-4W-SVHG-1000, ML1090 | PRECOM-4W-SVHG-1000: FS, ML1090: FS | 2025-04-11 13:00 | 2025-04-14 13:00
CPL-4-CRMN-3400 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 | Trench Excavation | CPL-4-CRMN-3320 | CPL-4-CRMN-3320: FS | CPL-4-CRMN-3410, CPL-4-CRMN-3460 | CPL-4-CRMN-3410: FF, CPL-4-CRMN-3460: FS | 2025-02-17 07:00 | 2025-02-21 17:00
CPL-4-CRMN-3410 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 | Bedding | CPL-4-CRMN-3400 | CPL-4-CRMN-3400: FF | CPL-4-CRMN-3420 | CPL-4-CRMN-3420: FS | 2025-02-21 07:00 | 2025-02-21 17:00
CPL-4-CRMN-3420 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 | Lowering | CPL-4-CRMN-3410, CPL-4-CRMN-3340 | CPL-4-CRMN-3410: FS, CPL-4-CRMN-3340: FS | CPL-4-CRMN-3430, CPL-4-CRMN-3480 | CPL-4-CRMN-3430: SS, CPL-4-CRMN-3480: FS | 2025-02-22 07:00 | 2025-02-22 17:00
CPL-4-CRMN-3430 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 | Section Tie-in Joint | CPL-4-CRMN-3420 | CPL-4-CRMN-3420: SS | CPL-4-CRMN-3440, ML1879-E33 | CPL-4-CRMN-3440: SS, ML1879-E33: FS | 2025-02-22 07:00 | 2025-02-22 17:00
CPL-4-CRMN-3440 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 | Field Joint Protection Sleeve | CPL-4-CRMN-3430 | CPL-4-CRMN-3430: SS | CPL-4-CRMN-3450 | CPL-4-CRMN-3450: FS | 2025-02-22 07:00 | 2025-02-22 17:00
CPL-4-CRMN-3450 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 | Padding | CPL-4-CRMN-3440 | CPL-4-CRMN-3440: FS | C-4W-SVHG-PIPEL-7400, C-4W-SVHG-PIPEL-6800 | C-4W-SVHG-PIPEL-7400: FS, C-4W-SVHG-PIPEL-6800: FS | 2025-02-24 07:00 | 2025-02-24 17:00
CPL-4-CRMN-3460 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 | Trench Excavation | CPL-4-CRMN-3400 | CPL-4-CRMN-3400: FS | CPL-4-CRMN-3470, CPL-4-CRMN-3520 | CPL-4-CRMN-3470: FF, CPL-4-CRMN-3520: FS | 2025-02-22 07:00 | 2025-02-25 17:00
CPL-4-CRMN-3470 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 | Bedding | CPL-4-CRMN-3460 | CPL-4-CRMN-3460: FF | CPL-4-CRMN-3480 | CPL-4-CRMN-3480: FS | 2025-02-25 07:00 | 2025-02-25 17:00
CPL-4-CRMN-3480 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 | Lowering | CPL-4-CRMN-3470, CPL-4-CRMN-3420 | CPL-4-CRMN-3470: FS, CPL-4-CRMN-3420: FS | CPL-4-CRMN-3490, CPL-4-CRMN-3540 | CPL-4-CRMN-3490: SS, CPL-4-CRMN-3540: FS | 2025-02-26 07:00 | 2025-02-26 17:00
CPL-4-CRMN-3490 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 | Section Tie-in Joint | CPL-4-CRMN-3480 | CPL-4-CRMN-3480: SS | CPL-4-CRMN-3500, ML1879-E33 | CPL-4-CRMN-3500: SS, ML1879-E33: FS | 2025-02-26 07:00 | 2025-02-26 17:00
CPL-4-CRMN-3500 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 | Field Joint Protection Sleeve | CPL-4-CRMN-3490 | CPL-4-CRMN-3490: SS | CPL-4-CRMN-3510 | CPL-4-CRMN-3510: FS | 2025-02-26 07:00 | 2025-02-26 17:00
CPL-4-CRMN-3510 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 | Padding | CPL-4-CRMN-3500 | CPL-4-CRMN-3500: FS | C-4W-SVHG-PIPEL-7400, C-4W-SVHG-PIPEL-6800 | C-4W-SVHG-PIPEL-7400: FS, C-4W-SVHG-PIPEL-6800: FS | 2025-02-27 07:00 | 2025-02-27 17:00
CPL-4-CRMN-3520 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 | Trench Excavation | CPL-4-CRMN-3460 | CPL-4-CRMN-3460: FS | CPL-4-CRMN-3530, CPL-4-CRMN-3580 | CPL-4-CRMN-3530: FF, CPL-4-CRMN-3580: FS | 2025-02-26 07:00 | 2025-03-05 09:00
CPL-4-CRMN-3530 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 | Bedding | CPL-4-CRMN-3520 | CPL-4-CRMN-3520: FF | CPL-4-CRMN-3540 | CPL-4-CRMN-3540: FS | 2025-03-03 11:00 | 2025-03-05 09:00
CPL-4-CRMN-3540 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 | Lowering | CPL-4-CRMN-3530, CPL-4-CRMN-3480 | CPL-4-CRMN-3530: FS, CPL-4-CRMN-3480: FS | CPL-4-CRMN-3550, CPL-4-CRMN-3600 | CPL-4-CRMN-3550: SS, CPL-4-CRMN-3600: FS | 2025-03-05 09:00 | 2025-03-06 13:00
CPL-4-CRMN-3550 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 | Section Tie-in Joint | CPL-4-CRMN-3540 | CPL-4-CRMN-3540: SS | CPL-4-CRMN-3560, ML1879-E33 | CPL-4-CRMN-3560: SS, ML1879-E33: FS | 2025-03-05 09:00 | 2025-03-06 13:00
CPL-4-CRMN-3560 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 | Field Joint Protection Sleeve | CPL-4-CRMN-3550 | CPL-4-CRMN-3550: SS | CPL-4-CRMN-3570 | CPL-4-CRMN-3570: FS | 2025-03-05 09:00 | 2025-03-06 13:00
CPL-4-CRMN-3570 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 | Padding | CPL-4-CRMN-3560 | CPL-4-CRMN-3560: FS | C-4W-SVHG-PIPEL-7400, C-4W-SVHG-PIPEL-6800 | C-4W-SVHG-PIPEL-7400: FS, C-4W-SVHG-PIPEL-6800: FS | 2025-03-07 07:00 | 2025-03-08 11:00
CPL-4-CRMN-3580 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 | Trench Excavation | CPL-4-CRMN-3520 | CPL-4-CRMN-3520: FS | CPL-4-CRMN-3590 | CPL-4-CRMN-3590: FF | 2025-03-05 09:00 | 2025-03-09 11:00
CPL-4-CRMN-3590 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 | Bedding | CPL-4-CRMN-3580 | CPL-4-CRMN-3580: FF | CPL-4-CRMN-3600 | CPL-4-CRMN-3600: FS | 2025-03-08 11:00 | 2025-03-09 11:00
CPL-4-CRMN-3600 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 | Lowering | CPL-4-CRMN-3590, CPL-4-CRMN-3540 | CPL-4-CRMN-3590: FS, CPL-4-CRMN-3540: FS | CPL-4-CRMN-3610 | CPL-4-CRMN-3610: SS | 2025-03-09 11:00 | 2025-03-11 09:00
CPL-4-CRMN-3610 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 | Section Tie-in Joint | CPL-4-CRMN-3600 | CPL-4-CRMN-3600: SS | CPL-4-CRMN-3620, ML1879-E33 | CPL-4-CRMN-3620: SS, ML1879-E33: FS | 2025-03-09 11:00 | 2025-03-11 09:00
CPL-4-CRMN-3620 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 | Field Joint Protection Sleeve | CPL-4-CRMN-3610 | CPL-4-CRMN-3610: SS | CPL-4-CRMN-3630 | CPL-4-CRMN-3630: FS | 2025-03-09 11:00 | 2025-03-11 09:00
CPL-4-CRMN-3630 | Not Started | P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 | Padding | CPL-4-CRMN-3620 | CPL-4-CRMN-3620: FS | C-4W-SVHG-PIPEL-7400, C-4W-SVHG-PIPEL-6800, C-4W-081-03-CI-0100 | C-4W-SVHG-PIPEL-7400: FS, C-4W-SVHG-PIPEL-6800: FS, C-4W-081-03-CI-0100: FS | 2025-03-11 09:00 | 2025-03-12 13:00
C-52-PR-839-CI-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 | Earth Works for Thrust Anchor Block | C-52-PR-839-CI-1000 | C-52-PR-839-CI-1000: FS | C-52-PR-839-CI-1240, C-52-PR-839-CI-1010 | C-52-PR-839-CI-1240: FS, C-52-PR-839-CI-1010: SS | 2025-01-25 07:00 | 2025-02-18 17:00
C-52-PR-839-CI-1240 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 | Compaction & Testing for Thrust Anchor Block | C-52-PR-839-CI-1050 | C-52-PR-839-CI-1050: FS | C-52-PR-839-CI-1510 | C-52-PR-839-CI-1510: FS | 2025-02-19 07:00 | 2025-02-27 17:00
C-52-PR-839-CI-1510 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.9 | Concrete Works for Thrust Anchor Block | C-52-PR-839-CI-1240, HM-PL-1550 | C-52-PR-839-CI-1240: FS, HM-PL-1550: FS | C-52-PR-839-CI-1500, PRECOM-52-PR-1000 | C-52-PR-839-CI-1500: FS, PRECOM-52-PR-1000: FS | 2025-03-27 07:00 | 2025-07-01 13:00
C-52-PR-839-CI-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.10 | Earth Works for Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28, C-52-PR-839-CI-1060 | ML1059-B28: FS, C-52-PR-839-CI-1060: FS | PRECOM-52-PR-1000, C-52-PR-839-CI-2220 | PRECOM-52-PR-1000: FS, C-52-PR-839-CI-2220: FS | 2025-04-22 13:00 | 2025-05-03 13:00
C-52-PR-839-ME-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.3.1 | Installation of Sales Gas Filter (839-F-104A) | HM-ME-0380, HE-CS-0950, ML1036-B23, HM-ME-0380 | HM-ME-0380: FS, HE-CS-0950: FS, ML1036-B23: FS, HM-ME-0380: FF | C-52-PR-839-ME-1810, PRECOM-52-PR-1000, ML1749-E20, ML1090 | C-52-PR-839-ME-1810: FS, PRECOM-52-PR-1000: FS, ML1749-E20: FS, ML1090: FS | 2025-02-21 07:00 | 2025-02-26 17:00
C-52-PR-839-ME-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.3.1 | Installation of Sales Gas Filter (839-F-104B) | C-52-PR-839-ME-1800 | C-52-PR-839-ME-1800: FS | PRECOM-52-PR-1000, ML1749-E20, ML1859-E31, ML1090 | PRECOM-52-PR-1000: FS, ML1749-E20: FS, ML1859-E31: FS, ML1090: FS | 2025-02-27 07:00 | 2025-03-05 09:00
C-52-PR-839-ME-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 | Installation of Pressure Reducing Skid (839-ME-106) | HE-CS-0770, HE-IC-0110, HM-ME-0080, HM-ME-0180, ML1419-D08, ML1036-B23 | HE-CS-0770: FS, HE-IC-0110: FS, HM-ME-0080: FS, HM-ME-0180: FS, ML1419-D08: FS, ML1036-B23: FS | PRECOM-52-PR-1000, ML1749-E20, ML1859-E31 | PRECOM-52-PR-1000: FS, ML1749-E20: FS, ML1859-E31: FS | 2025-05-29 07:00 | 2025-06-03 17:00
C-52-PR-839-ME-2010 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 | Installation of Sales Gas Custody Transfer Metering Skid Including Control Valve (839-ME-105) | HE-CS-0770, HE-IC-0110, HM-ME-0080, HM-ME-0180, ML1419-D08, ML1036-B23, HE-CS-0830 | HE-CS-0770: FS, HE-IC-0110: FS, HM-ME-0080: FS, HM-ME-0180: FS, ML1419-D08: FS, ML1036-B23: FS, HE-CS-0830: FS | PRECOM-52-PR-1000, ML1749-E20, ML1859-E31 | PRECOM-52-PR-1000: FS, ML1749-E20: FS, ML1859-E31: FS | 2025-05-29 07:00 | 2025-06-09 17:00
C-52-D-HT-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.1.1 | Site Survey, Preparation (Include Existing Dismantling Fence) & Grading Works | C-36-KM-HT-CI-1080, HE-SS-0030, ML1002, HE-CS-0170, ML1209-B27, ML1199-B24, CTF-1000, HE-CS-0470, CTF-1010 | C-36-KM-HT-CI-1080: FS, HE-SS-0030: SS, ML1002: FS, HE-CS-0170: FS, ML1209-B27: FS, ML1199-B24: FS, CTF-1000: FS, HE-CS-0470: FS, CTF-1010: FS | C-52-D-HT-CI-1020 | C-52-D-HT-CI-1020: FS | 2025-03-03 11:00 | 2025-03-18 13:00
C-52-D-HT-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.1.1 | Earth Works for Pipe Support Foundations | C-52-D-HT-CI-1000 | C-52-D-HT-CI-1000: FS | C-52-D-HT-CI-1080, C-52-D-HT-CI-1210 | C-52-D-HT-CI-1080: FS, C-52-D-HT-CI-1210: FS | 2025-03-19 07:00 | 2025-04-10 13:00
C-52-D-HT-CI-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.1.1 | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-D-HT-CI-1080 | C-52-D-HT-CI-1080: FS | C-52-D-HT-CI-1230 | C-52-D-HT-CI-1230: FS | 2025-04-26 13:00 | 2025-05-06 16:00
C-52-D-HT-CI-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.1.1 | Earth Works for Hot Tap Tie in Pit | C-52-D-HT-CI-1020 | C-52-D-HT-CI-1020: FS | C-52-D-HT-CI-1040, C-52-D-HT-CI-1280 | C-52-D-HT-CI-1040: FS, C-52-D-HT-CI-1280: FS | 2025-04-10 13:00 | 2025-04-26 13:00
C-52-D-HT-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.1.1 | Compaction & Testing for Pipe Support Foundations | C-52-D-HT-CI-1020 | C-52-D-HT-CI-1020: FS | C-52-D-HT-CI-1600 | C-52-D-HT-CI-1600: FS | 2025-04-10 13:00 | 2025-04-16 13:00
C-52-D-HT-CI-1230 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.1.1 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-52-D-HT-CI-1040 | C-52-D-HT-CI-1040: FS | C-52-D-HT-CI-1420 | C-52-D-HT-CI-1420: FS | 2025-05-07 08:00 | 2025-05-13 11:00
C-52-D-HT-CI-1280 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.1.1 | Compaction & Testing for Hot Tap Tie in Pit | C-52-D-HT-CI-1080 | C-52-D-HT-CI-1080: FS | C-52-D-HT-CI-1480 | C-52-D-HT-CI-1480: FS | 2025-04-26 13:00 | 2025-05-06 16:00
C-52-D-HT-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.1.2 | Concrete Works for Pipe Support Foundations | C-52-D-HT-CI-1210, HM-CS-0040, HE-CS-0230, HE-CS-1130, HM-CS-0050, ML1209-B27 | C-52-D-HT-CI-1210: FS, HM-CS-0040: FS, HE-CS-0230: FS, HE-CS-1130: FS, HM-CS-0050: FS, ML1209-B27: FS | C-52-D-HT-CI-1480, C-52-D-HT-CI-2000, C-52-D-HT-CI-2000, C-52-D-HT-CI-1700 | C-52-D-HT-CI-1480: FS, C-52-D-HT-CI-2000: SS 6, C-52-D-HT-CI-2000: FF, C-52-D-HT-CI-1700: FS | 2025-04-16 13:00 | 2025-05-12 11:00
C-52-D-HT-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.1.2 | Concrete Works for Access Platforms & Misc. Structural Foundations | C-52-D-HT-CI-1230, C-52-D-HT-CI-1480 | C-52-D-HT-CI-1230: FS, C-52-D-HT-CI-1480: FS | PRECOM-52-D-1000 | PRECOM-52-D-1000: FS | 2025-06-16 11:00 | 2025-07-03 11:00
C-52-D-HT-CI-1480 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.1.2 | Concrete Works for Hot Tap Tie in Pit | C-52-D-HT-CI-1280, C-52-D-HT-CI-1600, HM-CS-0040, HE-CS-0230, HM-CS-0050, ML1209-B27 | C-52-D-HT-CI-1280: FS, C-52-D-HT-CI-1600: FS, HM-CS-0040: FS, HE-CS-0230: FS, HM-CS-0050: FS, ML1209-B27: FS | C-52-D-HT-CI-1420, C-52-D-HT-CI-2600, PRECOM-52-D-1000, C-52-D-HT-CI-1700 | C-52-D-HT-CI-1420: FS, C-52-D-HT-CI-2600: FS, PRECOM-52-D-1000: FS, C-52-D-HT-CI-1700: FF 7 | 2025-05-12 11:00 | 2025-06-16 11:00
C-52-D-HT-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.1.7 | Paving of Interlock tiles & Kerb Stone Embankment (Including Fence Re-Instatement) | C-52-D-HT-CI-1480, C-52-D-HT-PI-2000, C-52-D-HT-ME-2000, C-52-D-HT-CI-3000, HE-CS-0290, ML1059-B28 | C-52-D-HT-CI-1480: FS, C-52-D-HT-PI-2000: FF 2, C-52-D-HT-ME-2000: FF 2, C-52-D-HT-CI-3000: FS, HE-CS-0290: FS, ML1059-B28: FS | PRECOM-52-D-1000 | PRECOM-52-D-1000: FF | 2025-09-03 11:00 | 2025-09-18 11:00
C-52-D-HT-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.2.1 | Piping Pre-Fabrication | C-36-KM-HT-PI-1000, ML1002, ML1219-B19, HE-PR-0290, HE-PI-1300, HS-CN-0190, HE-PR-0890, HE-PI-1240, HM-PI-0040, HE-PI-0440, ML1179-B11, HE-PI-0700 | C-36-KM-HT-PI-1000: SS 6, ML1002: FS, ML1219-B19: FS, HE-PR-0290: FS, HE-PI-1300: FS, HS-CN-0190: FS, HE-PR-0890: FS, HE-PI-1240: FS, HM-PI-0040: FS, HE-PI-0440: FS, ML1179-B11: FS, HE-PI-0700: FS | C-52-D-HT-PI-1200 | C-52-D-HT-PI-1200: FS | 2025-06-10 09:00 | 2025-07-10 09:00
C-52-D-HT-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.2.2 | Piping Erection | C-52-D-HT-PI-1000, C-52-D-HT-CI-2000, ML1002, ML1219-B19, HE-PR-0290, HM-PL-0220, HE-PI-1300, HS-CN-0190, HE-PR-0890, HE-PI-1240, HM-PI-0040, HM-PL-0630, HM-PL-0740, ML1179-B11, HM-PL-0640, HM-PL-1510, HM-PL-1570 | C-52-D-HT-PI-1000: FS, C-52-D-HT-CI-2000: FS, ML1002: FS, ML1219-B19: FS, HE-PR-0290: FS, HM-PL-0220: FS, HE-PI-1300: FS, HS-CN-0190: FS, HE-PR-0890: FS, HE-PI-1240: FS, HM-PI-0040: FS, HM-PL-0630: FS, HM-PL-0740: FS, ML1179-B11: FS, HM-PL-0640: FS, HM-PL- | C-52-D-HT-PI-1400 | C-52-D-HT-PI-1400: SS 2 | 2025-07-10 09:00 | 2025-07-26 09:00
C-52-D-HT-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.2.3 | Field Joint Welding | C-52-D-HT-PI-1200, HE-PI-1300, ML1002, ML1219-B19, HS-CN-0190, ML1179-B11 | C-52-D-HT-PI-1200: SS 2, HE-PI-1300: FS, ML1002: FS, ML1219-B19: FS, HS-CN-0190: FS, ML1179-B11: FS | C-52-D-HT-PI-1410 | C-52-D-HT-PI-1410: SS 3 | 2025-07-12 09:00 | 2025-07-26 09:00
C-52-D-HT-PI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.2.3 | NDT & Coating for Field Joint Weld | C-52-D-HT-PI-1400 | C-52-D-HT-PI-1400: SS 3 | C-52-D-HT-PI-1600 | C-52-D-HT-PI-1600: FS | 2025-07-16 09:00 | 2025-07-30 09:00
C-52-D-HT-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.2.4 | Hydrotesting | C-52-D-HT-PI-1410, ML1219-B19, ML1179-B11 | C-52-D-HT-PI-1410: FS, ML1219-B19: FS, ML1179-B11: FS | C-52-D-HT-PI-1800 | C-52-D-HT-PI-1800: FS | 2025-07-30 09:00 | 2025-08-05 09:00
C-52-D-HT-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.2.5 | Installation of Valves/GOV/ROV | C-52-D-HT-PI-1600, ML1219-B19, HE-PR-0290, HM-PL-0220, HE-PR-0890, HE-PI-1240, HM-PI-0040, ML1179-B11, HM-PL-1570 | C-52-D-HT-PI-1600: FS, ML1219-B19: FS, HE-PR-0290: FS, HM-PL-0220: FS, HE-PR-0890: FS, HE-PI-1240: FS, HM-PI-0040: FS, ML1179-B11: FS, HM-PL-1570: FS | C-52-D-HT-PI-2000 | C-52-D-HT-PI-2000: SS 4 | 2025-08-05 09:00 | 2025-08-11 09:00
C-52-D-HT-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.2.6 | Final Bolt Torquing/ Re-Instatement | C-52-D-HT-PI-1800, ML1002, ML1219-B19, HE-PR-0290, HM-PL-0220, HE-PI-1300, HS-CN-0190, HE-PR-0890, HE-PI-1240, HM-PI-0040, ML1179-B11, HM-PL-1570 | C-52-D-HT-PI-1800: SS 4, ML1002: FS, ML1219-B19: FS, HE-PR-0290: FS, HM-PL-0220: FS, HE-PI-1300: FS, HS-CN-0190: FS, HE-PR-0890: FS, HE-PI-1240: FS, HM-PI-0040: FS, ML1179-B11: FS, HM-PL-1570: FS | C-52-D-HT-CI-2600, PRECOM-52-D-1000, ML1749-E20, ML1849-E30 | C-52-D-HT-CI-2600: FF 2, PRECOM-52-D-1000: FS, ML1749-E20: FS, ML1849-E30: FS | 2025-08-09 09:00 | 2025-08-13 09:00
C-52-D-HT002-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.3.1 | Preparation, Marking & UT for Existing Line 48" Line | C-36-KM-HT04-ME-1050, HM-PL-1530, C-COM-1020, HE-PI-3520, HE-PL-1370, HM-PI-0040, HM-PL-0220, HM-PL-0320, HM-PL-1570, HS-CN-0540, HS-GN-0230 | C-36-KM-HT04-ME-1050: FS, HM-PL-1530: FS, C-COM-1020: FS, HE-PI-3520: FS, HE-PL-1370: FS, HM-PI-0040: FS, HM-PL-0220: FS, HM-PL-0320: FF, HM-PL-1570: FS, HS-CN-0540: FS, HS-GN-0230: FS | C-52-D-HT002-ME-1010 | C-52-D-HT002-ME-1010: FS | 2025-07-03 15:00 | 2025-07-05 15:00
C-52-D-HT002-ME-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.3.2 | Split Tee Welding (48" X 30") | C-52-D-HT002-ME-1000 | C-52-D-HT002-ME-1000: FS | C-52-D-HT002-ME-1020 | C-52-D-HT002-ME-1020: SS 1 | 2025-07-05 15:00 | 2025-07-15 15:00
C-52-D-HT002-ME-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.3.3 | NDT & Testing for Split Tee Weld Joint | C-52-D-HT002-ME-1010 | C-52-D-HT002-ME-1010: SS 1 | C-52-D-HT002-ME-1030 | C-52-D-HT002-ME-1030: FS | 2025-07-07 15:00 | 2025-07-16 15:00
C-52-D-HT002-ME-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.3.4 | Installation of Valves | C-52-D-HT002-ME-1020 | C-52-D-HT002-ME-1020: FS | C-52-D-HT002-ME-1040 | C-52-D-HT002-ME-1040: FS | 2025-07-16 15:00 | 2025-07-18 15:00
C-52-D-HT002-ME-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.3.5 | Hot Tapping of Existing 48" Line | C-52-D-HT002-ME-1030 | C-52-D-HT002-ME-1030: FS | C-52-D-HT002-ME-1050, CCM-PM4520, CCM-PM4530, CCM-PM4540 | C-52-D-HT002-ME-1050: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-07-18 15:00 | 2025-07-29 15:00
C-52-D-HT002-ME-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.3.6 | Isolation of Hot Tap Joint | C-52-D-HT002-ME-1040 | C-52-D-HT002-ME-1040: FS | C-52-D-HT-ME-2000, PRECOM-52-D-1000 | C-52-D-HT-ME-2000: FS 1, PRECOM-52-D-1000: FS | 2025-07-29 15:00 | 2025-07-31 15:00
C-52-D-HT-ME-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.4.1 | Tie-In with 30" Pipeline | C-52-D-HT002-ME-1050, HE-PR-0290 | C-52-D-HT002-ME-1050: FS 1, HE-PR-0290: FS | C-52-D-HT-CI-2600, PRECOM-52-D-1000, CCM-PM4520, CCM-PM4530, CCM-PM4540 | C-52-D-HT-CI-2600: FF 2, PRECOM-52-D-1000: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-08-01 15:00 | 2025-08-07 15:00
C-36-KM-HT-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.1 | Site Survey, Preparation & Grading Works | C-52-EB1-CI-1000, HE-SS-0030, ML1002, HE-CS-0470, CTF-1000, HE-CS-0170, CTF-1010 | C-52-EB1-CI-1000: FS, HE-SS-0030: SS, ML1002: FS, HE-CS-0470: FS, CTF-1000: FS, HE-CS-0170: FS, CTF-1010: FS | C-36-KM-HT-CI-1020 | C-36-KM-HT-CI-1020: FS | 2025-01-21 07:00 | 2025-01-29 17:00
C-36-KM-HT-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.1 | Earth Works for Pipe Support Foundations | C-36-KM-HT-CI-1000 | C-36-KM-HT-CI-1000: FS | C-36-KM-HT-CI-1080, C-36-KM-HT-CI-1030, C-36-KM-HT-CI-1210 | C-36-KM-HT-CI-1080: SS, C-36-KM-HT-CI-1030: FS, C-36-KM-HT-CI-1210: FS | 2025-01-30 07:00 | 2025-02-14 17:00
C-36-KM-HT-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.1 | Earth Works for Field Instrument, JBs | C-36-KM-HT-CI-1020 | C-36-KM-HT-CI-1020: FS | C-36-KM-HT-CI-1040, C-36-KM-HT-CI-1220 | C-36-KM-HT-CI-1040: FS, C-36-KM-HT-CI-1220: FS | 2025-02-15 07:00 | 2025-02-21 17:00
C-36-KM-HT-CI-1040 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.1 | Earth Works for Access Platforms & Misc. Structural Foundations | C-36-KM-HT-CI-1030 | C-36-KM-HT-CI-1030: FS | C-36-KM-HT-CI-1230 | C-36-KM-HT-CI-1230: FS | 2025-02-22 07:00 | 2025-03-03 11:00
C-36-KM-HT-CI-1080 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.1 | Earth Works for Hot Tap Tie in Pit | C-36-KM-HT-CI-1020 | C-36-KM-HT-CI-1020: SS | C-36-KM-HT-CI-1280, C-36-KM-HT-CI-1800, C-52-D-HT-CI-1000 | C-36-KM-HT-CI-1280: FS, C-36-KM-HT-CI-1800: FS, C-52-D-HT-CI-1000: FS | 2025-01-30 07:00 | 2025-03-03 11:00
C-36-KM-HT-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.2 | Compaction & Testing for Pipe Support Foundations | C-36-KM-HT-CI-1020 | C-36-KM-HT-CI-1020: FS | C-36-KM-HT-CI-1600 | C-36-KM-HT-CI-1600: FS | 2025-02-15 07:00 | 2025-02-24 17:00
C-36-KM-HT-CI-1220 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.2 | Compaction & Testing for Field Instrument, JBs | C-36-KM-HT-CI-1030 | C-36-KM-HT-CI-1030: FS | C-36-KM-HT-CI-1410 | C-36-KM-HT-CI-1410: FS | 2025-02-22 07:00 | 2025-02-27 17:00
C-36-KM-HT-CI-1230 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.2 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-36-KM-HT-CI-1040 | C-36-KM-HT-CI-1040: FS | C-36-KM-HT-CI-1420 | C-36-KM-HT-CI-1420: FS | 2025-03-03 11:00 | 2025-03-11 09:00
C-36-KM-HT-CI-1280 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.2 | Compaction & Testing for Hot Tap Tie in Pit | C-36-KM-HT-CI-1080 | C-36-KM-HT-CI-1080: FS | CCV-52-KM-1120 | CCV-52-KM-1120: FS | 2025-03-03 11:00 | 2025-03-15 15:00
C-36-KM-HT-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.5 | Concrete Works for Pipe Support Foundations | C-36-KM-HT-CI-1210 | C-36-KM-HT-CI-1210: FS | CCV-52-KM-1120, C-36-KM-HT-CI-1410, C-36-KM-HT-CI-2000, C-36-KM-HT-CI-2000 | CCV-52-KM-1120: FS, C-36-KM-HT-CI-1410: FS, C-36-KM-HT-CI-2000: FS, C-36-KM-HT-CI-2000: FF | 2025-02-25 07:00 | 2025-03-26 11:00
C-36-KM-HT-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.4 | Concrete Works for Field Instrument, JBs | C-36-KM-HT-CI-1220, C-36-KM-HT-CI-1600, HE-CS-0230, HM-CS-0050, HM-CS-0040 | C-36-KM-HT-CI-1220: FS, C-36-KM-HT-CI-1600: FS, HE-CS-0230: FS, HM-CS-0050: FS, HM-CS-0040: FS | C-36-KM-HT-CI-1420 | C-36-KM-HT-CI-1420: FS | 2025-03-26 11:00 | 2025-04-16 13:00
C-36-KM-HT-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.4 | Concrete Works for Access Platforms & Misc. Structural Foundations | C-36-KM-HT-CI-1230, C-36-KM-HT-CI-1410 | C-36-KM-HT-CI-1230: FS, C-36-KM-HT-CI-1410: FS | C-36-KM-HT-PI-1800, C-36-KM-HT-CI-2220 | C-36-KM-HT-PI-1800: FS, C-36-KM-HT-CI-2220: FS | 2025-04-16 13:00 | 2025-05-02 13:00
CCV-52-KM-1120 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.3 | Concrete Works for Hot Tap Tie in Pit | C-36-KM-HT-CI-1280, C-36-KM-HT-CI-1600, HE-CS-0230, HM-CS-0050, HM-CS-0040, HE-CS-1190, HE-CS-0410 | C-36-KM-HT-CI-1280: FS, C-36-KM-HT-CI-1600: FS, HE-CS-0230: FS, HM-CS-0050: FS, HM-CS-0040: FS, HE-CS-1190: FS, HE-CS-0410: FS | PRECOM-36-KM-1000 | PRECOM-36-KM-1000: FS | 2025-03-26 11:00 | 2025-05-23 11:00
C-36-KM-HT-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.6 | Electrical & Earthing Cable Trenching | C-36-KM-HT-CI-1080, HE-CS-0530 | C-36-KM-HT-CI-1080: FS, HE-CS-0530: FS | C-36-KM-HT-CI-1810, C-36-KM-HT-EI-2000 | C-36-KM-HT-CI-1810: FS, C-36-KM-HT-EI-2000: FS | 2025-03-03 11:00 | 2025-03-22 09:00
C-36-KM-HT-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.6 | Instrument & Telecom Cable Trenching | C-36-KM-HT-CI-1800 | C-36-KM-HT-CI-1800: FS | C-36-KM-HT-EI-2010 | C-36-KM-HT-EI-2010: FS | 2025-03-22 09:00 | 2025-04-10 13:00
C-36-KM-HT-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.10 | Back Filling for Electrical & Earthing Cable | C-36-KM-HT-EI-2000 | C-36-KM-HT-EI-2000: FS 5 | C-36-KM-HT-CI-2810, PRECOM-36-KM-1000 | C-36-KM-HT-CI-2810: FS, PRECOM-36-KM-1000: FS | 2025-07-01 15:00 | 2025-07-10 15:00
C-36-KM-HT-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.10 | Back Filling for Instrument & Telecom Cable | C-36-KM-HT-CI-2800, C-36-KM-HT-EI-2010 | C-36-KM-HT-CI-2800: FS, C-36-KM-HT-EI-2010: FS 5 | C-36-KM-HT-CI-2600, PRECOM-36-KM-1000 | C-36-KM-HT-CI-2600: FS, PRECOM-36-KM-1000: FS | 2025-07-15 15:00 | 2025-07-24 15:00
C-36-KM-HT-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.11 | Paving of Interlock tiles & Kerb Stone Embankment | C-36-KM-HT-CI-2810, C-36-KM-HT-CI-3000, HE-CS-0290, ML1059-B28 | C-36-KM-HT-CI-2810: FS, C-36-KM-HT-CI-3000: FS, HE-CS-0290: FF, ML1059-B28: FS | PRECOM-36-KM-1000 | PRECOM-36-KM-1000: FS | 2025-07-24 15:00 | 2025-08-09 15:00
C-36-KM-HT-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.4.12.2.1 | Piping Pre-Fabrication | C-52-PR-839-PI-1000, C-36-KM-HT-CI-2000, ML1002, HE-PI-1240, ML1219-B19, HE-PI-1300, HS-CN-0190, HM-PI-0040 | C-52-PR-839-PI-1000: FS 30, C-36-KM-HT-CI-2000: FS, ML1002: FS, HE-PI-1240: FS, ML1219-B19: FS, HE-PI-1300: FS, HS-CN-0190: FS, HM-PI-0040: FS | C-36-KM-HT-PI-1200, C-52-D-HT-PI-1000 | C-36-KM-HT-PI-1200: FS, C-52-D-HT-PI-1000: SS 6 | 2025-05-31 09:00 | 2025-07-07 09:00
C-36-KM-HT-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.4.12.2.2 | Piping Erection | C-36-KM-HT-PI-1000, HM-PL-0630, HE-PI-1240, ML1219-B19, HE-PI-1300, HM-PL-0640, HM-PL-0740, HM-PL-0220, HM-PI-0040, HM-PL-1510, HM-PL-1570 | C-36-KM-HT-PI-1000: FS, HM-PL-0630: FS, HE-PI-1240: FS, ML1219-B19: FS, HE-PI-1300: FS, HM-PL-0640: FS, HM-PL-0740: FS, HM-PL-0220: FS, HM-PI-0040: FS, HM-PL-1510: FS, HM-PL-1570: FS | C-36-KM-HT-PI-1400 | C-36-KM-HT-PI-1400: SS 2 | 2025-07-07 09:00 | 2025-07-28 09:00
C-36-KM-HT-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.4.12.2.3 | Field Joint Welding | C-36-KM-HT-PI-1200, ML1002, HM-PL-0630, HE-PI-1240, ML1219-B19, HE-PI-1300, HM-PL-0640, HS-CN-0190, HM-PL-0740, HM-PI-0040, HM-PL-1510 | C-36-KM-HT-PI-1200: SS 2, ML1002: FS, HM-PL-0630: FS, HE-PI-1240: FS, ML1219-B19: FS, HE-PI-1300: FS, HM-PL-0640: FS, HS-CN-0190: FS, HM-PL-0740: FS, HM-PI-0040: FS, HM-PL-1510: FS | C-36-KM-HT-PI-1410 | C-36-KM-HT-PI-1410: SS 3 | 2025-07-09 09:00 | 2025-07-30 09:00
C-36-KM-HT-PI-1410 | Not Started | P2543-R01-Oct24..4.3.1.4.12.2.3 | NDT & Coating for Field Joint Weld | C-36-KM-HT-PI-1400 | C-36-KM-HT-PI-1400: SS 3 | C-36-KM-HT-PI-1600 | C-36-KM-HT-PI-1600: FS | 2025-07-12 09:00 | 2025-08-02 09:00
C-36-KM-HT-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.4.12.2.4 | Hydrotesting | C-36-KM-HT-PI-1410, HE-PI-1240, ML1219-B19 | C-36-KM-HT-PI-1410: FS, HE-PI-1240: FS, ML1219-B19: FS | C-36-KM-HT-PI-1800 | C-36-KM-HT-PI-1800: FS | 2025-08-02 09:00 | 2025-08-08 09:00
C-36-KM-HT-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.4.12.2.5 | Installation of Valves/GOV/ROV | C-36-KM-HT-PI-1600, C-36-KM-HT-CI-1420, HE-PI-1240, ML1219-B19 | C-36-KM-HT-PI-1600: FS, C-36-KM-HT-CI-1420: FS, HE-PI-1240: FS, ML1219-B19: FS | C-36-KM-HT-PI-2000 | C-36-KM-HT-PI-2000: SS 4 | 2025-08-08 09:00 | 2025-08-14 09:00
C-36-KM-HT-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.4.12.2.6 | Final Bolt Torquing/ Re-Instatement | C-36-KM-HT-PI-1800, ML1002, HM-PL-0630, HE-PI-1240, ML1219-B19, HE-PI-1300, HM-PL-0640, HM-PL-0740, HM-PL-0220, HM-PI-0040, HM-PL-1510, HM-PL-1570 | C-36-KM-HT-PI-1800: SS 4, ML1002: FS, HM-PL-0630: FS, HE-PI-1240: FS, ML1219-B19: FS, HE-PI-1300: FS, HM-PL-0640: FS, HM-PL-0740: FS, HM-PL-0220: FS, HM-PI-0040: FS, HM-PL-1510: FS, HM-PL-1570: FS | C-36-KM-HT-ME-2000, PRECOM-36-KM-1000, ML1899-E35, ML1969-E42 | C-36-KM-HT-ME-2000: FS, PRECOM-36-KM-1000: FS, ML1899-E35: FS, ML1969-E42: FS | 2025-08-13 09:00 | 2025-08-16 09:00
C-36-KM-HT-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.4.12.3.1 | Electrical & Earthing Cable Laying | C-36-KM-HT-CI-1800, HE-EL-0590, HE-IC-1010, HM-EL-0080, HE-IC-0950, HE-EL-0830, HE-EL-0470, HE-IC-0830, HM-EL-0520, HE-EL-1610, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-63 | C-36-KM-HT-CI-1800: FS, HE-EL-0590: FS, HE-IC-1010: FS, HM-EL-0080: FS, HE-IC-0950: FS, HE-EL-0830: FS, HE-EL-0470: FS, HE-IC-0830: FS, HM-EL-0520: FS, HE-EL-1610: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-02 | C-36-KM-HT-EI-2010, C-36-KM-HT-CI-2800 | C-36-KM-HT-EI-2010: FS, C-36-KM-HT-CI-2800: FS 5 | 2025-06-10 15:00 | 2025-06-24 15:00
C-36-KM-HT-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.4.12.3.1 | Instrument Cable Laying | C-36-KM-HT-EI-2000, C-36-KM-HT-CI-1810 | C-36-KM-HT-EI-2000: FS, C-36-KM-HT-CI-1810: FS | C-36-KM-HT-EI-2030, C-36-KM-HT-CI-2810 | C-36-KM-HT-EI-2030: FS, C-36-KM-HT-CI-2810: FS 5 | 2025-06-24 15:00 | 2025-07-09 15:00
C-36-KM-HT-EI-2030 | Not Started | P2543-R01-Oct24..4.3.1.4.12.3.2 | Instrument Tubing Works | C-36-KM-HT-EI-2010, HM-EL-0520, HE-IC-0770, HE-IC-1550, HE-IC-0490, HE-EL-1670, HM-ME-1690, HM-EL-0080, ML1032-B21, HE-IC-0590, HE-EL-0530, HE-EL-1010, HE-EL-1790, HE-IC-0530, HM-EL-0280, HE-IC-0650, HM-IC-0040, HM-EL-0380, HE-IC-1430, HE-EL-1730, HE-IC-25 | C-36-KM-HT-EI-2010: FS, HM-EL-0520: FS, HE-IC-0770: FS, HE-IC-1550: FF, HE-IC-0490: FS, HE-EL-1670: FS, HM-ME-1690: FF, HM-EL-0080: FS, ML1032-B21: FS, HE-IC-0590: FS, HE-EL-0530: FS, HE-EL-1010: FS, HE-EL-1790: FS, HE-IC-0530: FS, HM-EL-0280: FS, HE-IC-06 | C-36-KM-HT-EI-2200 | C-36-KM-HT-EI-2200: FS | 2025-07-09 15:00 | 2025-07-21 15:00
C-36-KM-HT-EI-2200 | Not Started | P2543-R01-Oct24..4.3.1.4.12.3.2 | Installation of Field Instruments & JB's | C-36-KM-HT-EI-2030 | C-36-KM-HT-EI-2030: FS | C-36-KM-HT-EI-2040 | C-36-KM-HT-EI-2040: FS | 2025-07-21 15:00 | 2025-07-30 15:00
C-36-KM-HT-EI-2040 | Not Started | P2543-R01-Oct24..4.3.1.4.12.3.2 | Loop Checking for Instruments | C-36-KM-HT-EI-2200 | C-36-KM-HT-EI-2200: FS | C-36-KM-HT-EI-2050, PRECOM-36-KM-1000 | C-36-KM-HT-EI-2050: FS, PRECOM-36-KM-1000: FS | 2025-07-30 15:00 | 2025-08-06 15:00
C-36-KM-HT-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.4.12.3.2 | Glanding & Termination | C-36-KM-HT-EI-2040 | C-36-KM-HT-EI-2040: FS | PRECOM-36-KM-1000, ML1969-E42 | PRECOM-36-KM-1000: FS, ML1969-E42: FS | 2025-08-06 15:00 | 2025-08-13 15:00
C-36-KM-HT03-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.4.12.4.1 | Preparation, Marking & UT for Existing Line 36" Line | HM-PL-1530, C-COM-1020, HE-PI-3520, HE-PL-1370, HM-PI-0040, HM-PL-0220, HM-PL-0320, HM-PL-1570, HS-CN-0540, HS-GN-0230, HM-PL-0320 | HM-PL-1530: FS, C-COM-1020: FS, HE-PI-3520: FS, HE-PL-1370: FS, HM-PI-0040: FS, HM-PL-0220: FS, HM-PL-0320: FF, HM-PL-1570: FS, HS-CN-0540: FS, HS-GN-0230: FS, HM-PL-0320: FS | C-36-KM-HT03-ME-1010 | C-36-KM-HT03-ME-1010: FS | 2025-05-03 07:00 | 2025-05-06 10:00
C-36-KM-HT03-ME-1010 | Not Started | P2543-R01-Oct24..4.3.1.4.12.4.2 | Split Tee Welding (36" X 36") | C-36-KM-HT03-ME-1000 | C-36-KM-HT03-ME-1000: FS | C-36-KM-HT03-ME-1020 | C-36-KM-HT03-ME-1020: SS 1 | 2025-05-06 10:00 | 2025-05-14 15:00
C-36-KM-HT03-ME-1020 | Not Started | P2543-R01-Oct24..4.3.1.4.12.4.3 | NDT & Testing for Split Tee Weld Joint | C-36-KM-HT03-ME-1010 | C-36-KM-HT03-ME-1010: SS 1 | C-36-KM-HT03-ME-1030 | C-36-KM-HT03-ME-1030: FS | 2025-05-07 12:00 | 2025-05-15 15:00
C-36-KM-HT03-ME-1030 | Not Started | P2543-R01-Oct24..4.3.1.4.12.4.4 | Installation of Valves | C-36-KM-HT03-ME-1020 | C-36-KM-HT03-ME-1020: FS | C-36-KM-HT03-ME-1040 | C-36-KM-HT03-ME-1040: FS | 2025-05-15 15:00 | 2025-05-17 15:00
C-36-KM-HT03-ME-1040 | Not Started | P2543-R01-Oct24..4.3.1.4.12.4.5 | Hot Tapping of Existing 36" Line | C-36-KM-HT03-ME-1030 | C-36-KM-HT03-ME-1030: FS | C-36-KM-HT03-ME-1050, ML1899-E35, CCM-PM4520, CCM-PM4530, CCM-PM4540 | C-36-KM-HT03-ME-1050: FS, ML1899-E35: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-05-17 15:00 | 2025-05-27 15:00
C-36-KM-HT03-ME-1050 | Not Started | P2543-R01-Oct24..4.3.1.4.12.4.6 | Isolation of Hot Tap Joint | C-36-KM-HT03-ME-1040 | C-36-KM-HT03-ME-1040: FS | C-36-KM-HT-ME-2000, C-36-KM-HT04-ME-1000, PRECOM-36-KM-1000, ML1969-E42 | C-36-KM-HT-ME-2000: FS, C-36-KM-HT04-ME-1000: FS 5, PRECOM-36-KM-1000: FS, ML1969-E42: FS | 2025-05-27 15:00 | 2025-05-29 15:00
C-36-KM-HT04-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.4.12.5.1 | Preparation, Marking & UT for Existing Line 36" Line | C-36-KM-HT03-ME-1050, HE-PI-3520, HE-PL-1370, HM-PI-0040, HM-PL-0220, HM-PL-0320, HM-PL-1570, HS-CN-0540, HS-GN-0230 | C-36-KM-HT03-ME-1050: FS 5, HE-PI-3520: FS, HE-PL-1370: FS, HM-PI-0040: FS, HM-PL-0220: FS, HM-PL-0320: FF, HM-PL-1570: FS, HS-CN-0540: FS, HS-GN-0230: FS | C-36-KM-HT04-ME-1010 | C-36-KM-HT04-ME-1010: FS | 2025-06-04 15:00 | 2025-06-09 15:00
C-36-KM-HT04-ME-1010 | Not Started | P2543-R01-Oct24..4.3.1.4.12.5.2 | Split Tee Welding (36" X 36") | C-36-KM-HT04-ME-1000 | C-36-KM-HT04-ME-1000: FS | C-36-KM-HT04-ME-1020 | C-36-KM-HT04-ME-1020: SS 1 | 2025-06-09 15:00 | 2025-06-17 15:00
C-36-KM-HT04-ME-1020 | Not Started | P2543-R01-Oct24..4.3.1.4.12.5.3 | NDT & Testing for Split Tee Weld Joint | C-36-KM-HT04-ME-1010 | C-36-KM-HT04-ME-1010: SS 1 | C-36-KM-HT04-ME-1030 | C-36-KM-HT04-ME-1030: FS | 2025-06-10 15:00 | 2025-06-18 15:00
C-36-KM-HT04-ME-1030 | Not Started | P2543-R01-Oct24..4.3.1.4.12.5.4 | Installation of Valves | C-36-KM-HT04-ME-1020 | C-36-KM-HT04-ME-1020: FS | C-36-KM-HT04-ME-1040 | C-36-KM-HT04-ME-1040: FS | 2025-06-18 15:00 | 2025-06-20 15:00
C-36-KM-HT04-ME-1040 | Not Started | P2543-R01-Oct24..4.3.1.4.12.5.5 | Hot Tapping of Existing 36" Line | C-36-KM-HT04-ME-1030 | C-36-KM-HT04-ME-1030: FS | C-36-KM-HT04-ME-1050, ML1899-E35, CCM-PM4520, CCM-PM4530, CCM-PM4540 | C-36-KM-HT04-ME-1050: FS, ML1899-E35: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-06-20 15:00 | 2025-07-01 15:00
C-36-KM-HT04-ME-1050 | Not Started | P2543-R01-Oct24..4.3.1.4.12.5.6 | Isolation of Hot Tap Joint | C-36-KM-HT04-ME-1040 | C-36-KM-HT04-ME-1040: FS | C-36-KM-HT-ME-2000, C-52-D-HT002-ME-1000, PRECOM-36-KM-1000, ML1969-E42 | C-36-KM-HT-ME-2000: FS 6, C-52-D-HT002-ME-1000: FS, PRECOM-36-KM-1000: FS, ML1969-E42: FS | 2025-07-01 15:00 | 2025-07-03 15:00
C-36-KM-HT-ME-2000 | Not Started | P2543-R01-Oct24..4.3.1.4.12.6.1 | Tie-In with 36" Pipeline | C-36-KM-HT04-ME-1050, C-36-KM-HT03-ME-1050, C-36-KM-HT-PI-2000 | C-36-KM-HT04-ME-1050: FS 6, C-36-KM-HT03-ME-1050: FS, C-36-KM-HT-PI-2000: FS | PRECOM-36-KM-1000, ML1969-E42, CCM-PM4520, CCM-PM4530, CCM-PM4540 | PRECOM-36-KM-1000: FS, ML1969-E42: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-08-16 09:00 | 2025-08-21 09:00
C-56-G-HT-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.40.2 | Site Survey, Preparation & Grading Works | C-56-G-HT-CI-0100, HE-SS-0030, ML1002, HE-CS-0170, HE-CS-0470 | C-56-G-HT-CI-0100: FS, HE-SS-0030: SS, ML1002: FS, HE-CS-0170: FS, HE-CS-0470: FS | C-56-G-HT-CI-1020 | C-56-G-HT-CI-1020: FS | 2025-01-30 07:00 | 2025-02-07 17:00
C-56-G-HT-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.40.2 | Earth Works for Pipe Support Foundations | C-56-G-HT-CI-1000 | C-56-G-HT-CI-1000: FS | C-56-G-HT-CI-1040, C-56-G-HT-CI-1210 | C-56-G-HT-CI-1040: FS, C-56-G-HT-CI-1210: FS | 2025-02-08 07:00 | 2025-02-14 17:00
C-56-G-HT-CI-1040 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.40.2 | Earth Works for Access Platforms & Misc. Structural Foundations | C-56-G-HT-CI-1020 | C-56-G-HT-CI-1020: FS | C-56-G-HT-CI-1230 | C-56-G-HT-CI-1230: FS | 2025-02-15 07:00 | 2025-02-21 17:00
C-56-G-HT-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.40.2 | Compaction & Testing for Pipe Support Foundations | C-56-G-HT-CI-1020 | C-56-G-HT-CI-1020: FS | C-56-G-HT-CI-1600 | C-56-G-HT-CI-1600: FS | 2025-02-15 07:00 | 2025-02-20 17:00
C-56-G-HT-CI-1230 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.40.2 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-56-G-HT-CI-1040 | C-56-G-HT-CI-1040: FS | C-56-G-HT-CI-1600 | C-56-G-HT-CI-1600: FS | 2025-02-22 07:00 | 2025-02-27 17:00
C-56-G-HT-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.40.3 | Concrete Works for Pipe Support Foundations | C-56-G-HT-CI-1230, C-56-G-HT-CI-1210, HE-CS-0230, HE-CS-1130, HM-CS-0040, HM-CS-0050 | C-56-G-HT-CI-1230: FS, C-56-G-HT-CI-1210: FS, HE-CS-0230: FS, HE-CS-1130: FS, HM-CS-0040: FS, HM-CS-0050: FS | C-56-G-HT-CI-1420, C-56-G-HT-CI-2000, C-56-G-HT-CI-1700 | C-56-G-HT-CI-1420: FS, C-56-G-HT-CI-2000: FS 45, C-56-G-HT-CI-1700: FF | 2025-02-28 07:00 | 2025-03-09 11:00
C-56-G-HT-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.40.6 | Concrete Works for Access Platforms & Misc. Structural Foundations | C-56-G-HT-CI-1600, HM-CS-0110, HS-CN-0690 | C-56-G-HT-CI-1600: FS, HM-CS-0110: FS, HS-CN-0690: FS | C-56-G-HT-CI-2600, C-56-G-HT-CI-1700 | C-56-G-HT-CI-2600: FS, C-56-G-HT-CI-1700: FF 1 | 2025-03-09 11:00 | 2025-04-11 13:00
C-56-G-HT-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.40.7 | Paving of Interlock tiles & Kerb Stone Embankment | C-56-G-HT-CI-1420, C-56-G-HT-CI-1700, ML1059-B28, HE-CS-0290 | C-56-G-HT-CI-1420: FS, C-56-G-HT-CI-1700: FF, ML1059-B28: FS, HE-CS-0290: FS | C-52-IDS1-CI-1000, PRECOM-56-G-1000 | C-52-IDS1-CI-1000: FS, PRECOM-56-G-1000: FS | 2025-04-11 13:00 | 2025-04-28 13:00
C-56-G-HT-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.2.1 | Piping Pre-Fabrication | ML1002, CTF-SO1050, HE-PR-0890, HS-CN-0190, HE-PI-1240, ML1014-B10, ML1219-B19, HE-PI-0370, HE-PI-0640, HE-PI-1300, HM-PI-0040, HE-PR-0290 | ML1002: FS, CTF-SO1050: FS, HE-PR-0890: FS, HS-CN-0190: FS, HE-PI-1240: FS, ML1014-B10: FS, ML1219-B19: FS, HE-PI-0370: FS, HE-PI-0640: FS, HE-PI-1300: FS, HM-PI-0040: FS, HE-PR-0290: FS | C-56-G-HT-PI-1200 | C-56-G-HT-PI-1200: FS | 2025-02-24 07:00 | 2025-04-07 13:00
C-56-G-HT-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.2.2 | Piping Erection | C-56-G-HT-PI-1000, C-56-G-HT-CI-2000, ML1002, HE-PR-0890, HS-CN-0190, HM-PL-0630, HE-PI-1240, ML1014-B10, ML1219-B19, HM-PL-0220, HM-PL-0640, HE-PI-1300, HM-PL-0740, HM-PI-0040, HE-PR-0290, HM-PL-1510, HM-PL-1570 | C-56-G-HT-PI-1000: FS, C-56-G-HT-CI-2000: FS, ML1002: FS, HE-PR-0890: FS, HS-CN-0190: FS, HM-PL-0630: FS, HE-PI-1240: FS, ML1014-B10: FS, ML1219-B19: FS, HM-PL-0220: FS, HM-PL-0640: FS, HE-PI-1300: FS, HM-PL-0740: FS, HM-PI-0040: FS, HE-PR-0290: FS, HM-PL- | C-56-G-HT-PI-1400 | C-56-G-HT-PI-1400: SS 6 | 2025-06-04 11:00 | 2025-07-02 11:00
C-56-G-HT-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.2.3 | Field Joint Welding | C-56-G-HT-PI-1200, HE-PI-1300, ML1002, HS-CN-0190, ML1014-B10, ML1219-B19 | C-56-G-HT-PI-1200: SS 6, HE-PI-1300: FS, ML1002: FS, HS-CN-0190: FS, ML1014-B10: FS, ML1219-B19: FS | C-56-G-HT-PI-1410 | C-56-G-HT-PI-1410: SS 3 | 2025-06-13 11:00 | 2025-07-17 11:00
C-56-G-HT-PI-1410 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.2.3 | NDT & Coating for Field Joint Weld | C-56-G-HT-PI-1400 | C-56-G-HT-PI-1400: SS 3 | C-56-G-HT-PI-1600 | C-56-G-HT-PI-1600: FS | 2025-06-17 11:00 | 2025-07-21 11:00
C-56-G-HT-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.2.4 | Hydrotesting | C-56-G-HT-PI-1410, ML1014-B10, ML1219-B19 | C-56-G-HT-PI-1410: FS, ML1014-B10: FS, ML1219-B19: FS | C-56-G-HT-PI-1800 | C-56-G-HT-PI-1800: FS | 2025-07-21 11:00 | 2025-07-30 11:00
C-56-G-HT-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.2.5 | Installation of Valves/GOV/ROV | C-56-G-HT-PI-1600, HE-PR-0890, HM-PL-0630, HE-PI-1240, ML1014-B10, ML1219-B19, HM-PL-0220, HM-PL-0640, HM-PL-0740, HE-PR-0290, HM-PL-1510, HM-PL-1570 | C-56-G-HT-PI-1600: FS, HE-PR-0890: FS, HM-PL-0630: FS, HE-PI-1240: FS, ML1014-B10: FS, ML1219-B19: FS, HM-PL-0220: FS, HM-PL-0640: FS, HM-PL-0740: FS, HE-PR-0290: FS, HM-PL-1510: FS, HM-PL-1570: FS | C-56-G-HT-PI-2000 | C-56-G-HT-PI-2000: SS 4 | 2025-07-30 11:00 | 2025-08-05 11:00
C-56-G-HT-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.2.6 | Final Bolt Torquing/ Re-Instatement | C-56-G-HT-PI-1800, HE-PI-1300, ML1002, HE-PR-0890, HS-CN-0190, HM-PL-0630, HE-PI-1240, ML1014-B10, ML1219-B19, HM-PL-0220, HM-PL-0640, HM-PL-0740, HE-PR-0290, HM-PL-1510, HM-PL-1570 | C-56-G-HT-PI-1800: SS 4, HE-PI-1300: FS, ML1002: FS, HE-PR-0890: FS, HS-CN-0190: FS, HM-PL-0630: FS, HE-PI-1240: FS, ML1014-B10: FS, ML1219-B19: FS, HM-PL-0220: FS, HM-PL-0640: FS, HM-PL-0740: FS, HE-PR-0290: FS, HM-PL-1510: FS, HM-PL-1570: FS | PRECOM-56-G-1000, ML1629-E08 | PRECOM-56-G-1000: FS, ML1629-E08: FS | 2025-08-04 11:00 | 2025-08-11 11:00
C-56-G-HT101-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.3.1 | Preparation, Marking & UT for Existing Line 42" Line | HM-PL-0840, C-COM-1020, HE-PI-3520, HE-PL-1370, HM-PI-0040, HM-PL-0220, HM-PL-0320, HM-PL-1570, HS-CN-0540, HS-GN-0230, HM-PL-0320 | HM-PL-0840: FS, C-COM-1020: FS, HE-PI-3520: FS, HE-PL-1370: FS, HM-PI-0040: FS, HM-PL-0220: FS, HM-PL-0320: FS, HM-PL-1570: FS, HS-CN-0540: FS, HS-GN-0230: FS, HM-PL-0320: FF | C-56-G-HT101-ME-1010 | C-56-G-HT101-ME-1010: FS | 2025-05-03 07:00 | 2025-05-03 17:00
C-56-G-HT101-ME-1010 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.3.2 | Split Tee Welding (42" X 42") | C-56-G-HT101-ME-1000, C-COM-1010 | C-56-G-HT101-ME-1000: FS, C-COM-1010: FS | C-56-G-HT101-ME-1020 | C-56-G-HT101-ME-1020: SS 1 | 2025-05-05 08:00 | 2025-05-12 15:00
C-56-G-HT101-ME-1020 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.3.3 | NDT & Testing for Split Tee Weld Joint | C-56-G-HT101-ME-1010 | C-56-G-HT101-ME-1010: SS 1 | C-56-G-HT101-ME-1030 | C-56-G-HT101-ME-1030: FS | 2025-05-06 10:00 | 2025-05-13 15:00
C-56-G-HT101-ME-1030 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.3.4 | Installation of Valves | C-56-G-HT101-ME-1020 | C-56-G-HT101-ME-1020: FS | C-56-G-HT101-ME-1040 | C-56-G-HT101-ME-1040: FS | 2025-05-13 15:00 | 2025-05-14 15:00
C-56-G-HT101-ME-1040 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.3.5 | Hot Tapping of Existing 42" Line | C-56-G-HT101-ME-1030 | C-56-G-HT101-ME-1030: FS | C-56-G-HT101-ME-1050, CCM-PM4510 | C-56-G-HT101-ME-1050: FS, CCM-PM4510: FS | 2025-05-14 15:00 | 2025-05-28 15:00
C-56-G-HT101-ME-1050 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.3.6 | Isolation of Hot Tap Joint | C-56-G-HT101-ME-1040 | C-56-G-HT101-ME-1040: FS | C-56-G-HT-ME-2000, C-56-G-HT102-ME-1000, PRECOM-56-G-1000 | C-56-G-HT-ME-2000: FS, C-56-G-HT102-ME-1000: FS 5, PRECOM-56-G-1000: FS | 2025-05-28 15:00 | 2025-05-30 15:00
C-56-G-HT102-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.4.1 | Preparation, Marking & UT for Existing Line 30" Line | C-56-G-HT101-ME-1050 | C-56-G-HT101-ME-1050: FS 5 | C-56-G-HT102-ME-1010 | C-56-G-HT102-ME-1010: FS | 2025-06-07 15:00 | 2025-06-09 15:00
C-56-G-HT102-ME-1010 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.4.2 | Split Tee Welding (30" X 30") | C-56-G-HT102-ME-1000 | C-56-G-HT102-ME-1000: FS | C-56-G-HT102-ME-1020 | C-56-G-HT102-ME-1020: SS 1 | 2025-06-09 15:00 | 2025-06-17 15:00
C-56-G-HT102-ME-1020 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.4.3 | NDT & Testing for Split Tee Weld Joint | C-56-G-HT102-ME-1010 | C-56-G-HT102-ME-1010: SS 1 | C-56-G-HT102-ME-1030 | C-56-G-HT102-ME-1030: FS | 2025-06-10 15:00 | 2025-06-18 15:00
C-56-G-HT102-ME-1030 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.4.4 | Installation of Valves | C-56-G-HT102-ME-1020 | C-56-G-HT102-ME-1020: FS | C-56-G-HT102-ME-1040 | C-56-G-HT102-ME-1040: FS 1 | 2025-06-18 15:00 | 2025-06-20 15:00
C-56-G-HT102-ME-1040 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.4.5 | Hot Tapping of Existing 30" Line | C-56-G-HT102-ME-1030 | C-56-G-HT102-ME-1030: FS 1 | C-56-G-HT102-ME-1050, CCM-PM4510 | C-56-G-HT102-ME-1050: FS, CCM-PM4510: FS | 2025-06-21 15:00 | 2025-07-07 15:00
C-56-G-HT102-ME-1050 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.4.6 | Isolation of Hot Tap Joint | C-56-G-HT102-ME-1040 | C-56-G-HT102-ME-1040: FS | C-56-G-HT-ME-2000, C-56-G-HT103-ME-1000, PRECOM-56-G-1000 | C-56-G-HT-ME-2000: FS, C-56-G-HT103-ME-1000: FS 7, PRECOM-56-G-1000: FS | 2025-07-07 15:00 | 2025-07-09 15:00
C-56-G-HT103-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.5.1 | Preparation, Marking & UT for Existing Line 42" Line | C-56-G-HT102-ME-1050 | C-56-G-HT102-ME-1050: FS 7 | C-56-G-HT103-ME-1010 | C-56-G-HT103-ME-1010: FS | 2025-07-17 15:00 | 2025-07-18 15:00
C-56-G-HT103-ME-1010 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.5.2 | Split Tee Welding (42" X 42") | C-56-G-HT103-ME-1000 | C-56-G-HT103-ME-1000: FS | C-56-G-HT103-ME-1020 | C-56-G-HT103-ME-1020: SS 1 | 2025-07-18 15:00 | 2025-07-26 15:00
C-56-G-HT103-ME-1020 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.5.3 | NDT & Testing for Split Tee Weld Joint | C-56-G-HT103-ME-1010 | C-56-G-HT103-ME-1010: SS 1 | C-56-G-HT103-ME-1030 | C-56-G-HT103-ME-1030: FS | 2025-07-19 15:00 | 2025-07-28 15:00
C-56-G-HT103-ME-1030 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.5.4 | Installation of Valves | C-56-G-HT103-ME-1020 | C-56-G-HT103-ME-1020: FS | C-56-G-HT103-ME-1040 | C-56-G-HT103-ME-1040: FS | 2025-07-28 15:00 | 2025-07-30 15:00
C-56-G-HT103-ME-1040 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.5.5 | Hot Tapping of Existing 42" Line | C-56-G-HT103-ME-1030 | C-56-G-HT103-ME-1030: FS | C-56-G-HT103-ME-1050, CCM-PM4510 | C-56-G-HT103-ME-1050: FS, CCM-PM4510: FS | 2025-07-30 15:00 | 2025-08-13 15:00
C-56-G-HT103-ME-1050 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.5.6 | Isolation of Hot Tap Joint | C-56-G-HT103-ME-1040 | C-56-G-HT103-ME-1040: FS | C-56-G-HT-ME-2000, PRECOM-56-G-1000 | C-56-G-HT-ME-2000: FS 15, PRECOM-56-G-1000: FS | 2025-08-13 15:00 | 2025-08-15 15:00
C-56-G-HT-ME-2000 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.6.1 | Tie-In with 30" Pipeline | C-56-G-HT101-ME-1050, C-56-G-HT102-ME-1050, C-56-G-HT103-ME-1050 | C-56-G-HT101-ME-1050: FS, C-56-G-HT102-ME-1050: FS, C-56-G-HT103-ME-1050: FS 15 | PRECOM-56-G-1000, CCM-PM4510 | PRECOM-56-G-1000: FS, CCM-PM4510: FS | 2025-09-02 15:00 | 2025-09-15 15:00
C-DBV6-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.7.12.1.1 | Instrument & Telecom Cable Trenching | C-DBV6-CI-1800 | C-DBV6-CI-1800: FS | C-DBV6-EI-2010 | C-DBV6-EI-2010: FS | 2025-06-10 11:00 | 2025-06-26 11:00
C-DBV6-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.7.12.1.2 | Back Filling for Instrument & Telecom Cable | C-DBV6-EI-2010 | C-DBV6-EI-2010: FS | PRE-COM1330 | PRE-COM1330: FS | 2025-07-04 11:00 | 2025-07-11 11:00
C-DBV6-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.7.12.1.1 | Electrical & Earthing Cable Trenching | C-4W-TI-CI-1400 | C-4W-TI-CI-1400: FS | C-DBV6-CI-1810, C-DBV6-EI-2000 | C-DBV6-CI-1810: FS, C-DBV6-EI-2000: FS | 2025-05-22 11:00 | 2025-06-10 11:00
C-DBV6-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.7.12.1.2 | Back Filling for Electrical & Earthing Cable | C-DBV6-EI-2000 | C-DBV6-EI-2000: FS 5 | PRE-COM1330 | PRE-COM1330: FS | 2025-06-23 11:00 | 2025-07-01 11:00
C-DBV6-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.7.12.2.1 | Electrical & Earthing Cable Laying | HE-EL-1550, C-DBV6-CI-1800 | HE-EL-1550: FS, C-DBV6-CI-1800: FS | C-DBV6-EI-2500, C-DBV6-CI-2800 | C-DBV6-EI-2500: FS, C-DBV6-CI-2800: FS 5 | 2025-06-10 11:00 | 2025-06-17 11:00
C-DBV6-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.7.12.2.1 | Instrument Cable Laying | C-DBV6-CI-1810 | C-DBV6-CI-1810: FS | C-DBV6-EI-2500, C-DBV6-CI-2810 | C-DBV6-EI-2500: FS, C-DBV6-CI-2810: FS | 2025-06-26 11:00 | 2025-07-04 11:00
C-DBV6-EI-2500 | Not Started | P2543-R01-Oct24..4.3.1.7.12.2.1 | Installation of H2S Analyser | C-DBV6-EI-2010, C-DBV6-EI-2000, C-DBV6-CI-5000 | C-DBV6-EI-2010: FS, C-DBV6-EI-2000: FS, C-DBV6-CI-5000: FS | C-MAQTA-CI-1800, PRE-COM1330, C-MAQTA-EI-1000 | C-MAQTA-CI-1800: FS, PRE-COM1330: FS, C-MAQTA-EI-1000: FS | 2025-07-11 11:00 | 2025-07-15 11:00
C-577-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.10.12.1.1 | Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB Building | C-541CR-CI-1010, HE-CS-0530, CTF-1000, HE-CS-0470, HE-CS-0170, CTF-1010 | C-541CR-CI-1010: FS 5, HE-CS-0530: FS, CTF-1000: FS, HE-CS-0470: FS, HE-CS-0170: FS, CTF-1010: FS | C-577-TE-1000, C-601-CI-1000, CCM-PM4520, CCM-PM4530, CCM-PM4540 | C-577-TE-1000: FS, C-601-CI-1000: SS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-08-08 11:00 | 2025-08-13 11:00
C-577-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.10.12.1.2 | Backfilling - 577-SV-02 Passive cooling Shelter to HGCP - MCB Building | C-577-TE-1000 | C-577-TE-1000: FS | PRE-COM1330, CCM-PM4520, CCM-PM4530, CCM-PM4540 | PRE-COM1330: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-08-18 11:00 | 2025-08-22 11:00
C-577-TE-1000 | Not Started | P2543-R01-Oct24..4.3.1.10.12.2.1 | Telecommunication Works (new telecom cabinet and cable laying and terminations) | C-577-CI-1000, HS-GN-0410, CTF-1000, HS-GN-0350, HM-TL-0040, HS-GN-0470, ML1033-B22, HS-CN-0290, HS-GN-0290, CTF-1010 | C-577-CI-1000: FS, HS-GN-0410: FS, CTF-1000: FS, HS-GN-0350: FS, HM-TL-0040: FS, HS-GN-0470: FS, ML1033-B22: FS, HS-CN-0290: FS, HS-GN-0290: FS, CTF-1010: FS | C-577-CI-1010, PRE-COM1330, CCM-PM4520, CCM-PM4530, CCM-PM4540 | C-577-CI-1010: FS, PRE-COM1330: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-08-13 11:00 | 2025-08-18 11:00
C-601-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.11.12.1.1 | Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603) | C-577-CI-1000, HE-CS-0470, HE-CS-0170, HE-CS-0530, CTF-1000, CTF-1010 | C-577-CI-1000: SS, HE-CS-0470: FS, HE-CS-0170: FS, HE-CS-0530: FS, CTF-1000: FS, CTF-1010: FS | C-601-TE-1000, CCM-PM4520, CCM-PM4530, CCM-PM4540 | C-601-TE-1000: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-08-08 11:00 | 2025-08-15 11:00
C-601-TE-1000 | Not Started | P2543-R01-Oct24..4.3.1.11.12.2.1 | Telecommunication Works (modifications of existing telecom cabinet) | C-601-CI-1000, CTF-1000, HS-GN-0290, HS-GN-0350, HS-CN-0290, HS-GN-0410, HM-TL-0040, HS-GN-0470, ML1033-B22, CTF-1010 | C-601-CI-1000: FS, CTF-1000: FS, HS-GN-0290: FS, HS-GN-0350: FS, HS-CN-0290: FS, HS-GN-0410: FS, HM-TL-0040: FS, HS-GN-0470: FS, ML1033-B22: FS, CTF-1010: FS | C-601-CI-1010, PRE-COM1330, CCM-PM4520, CCM-PM4530, CCM-PM4540 | C-601-CI-1010: FS, PRE-COM1330: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-08-15 11:00 | 2025-08-22 11:00
C-601-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.11.12.1.2 | Backfilling - Tahammama-C E&I Building to Launcher Station (607-V-603) | C-601-TE-1000 | C-601-TE-1000: FS | PRE-COM1330, CCM-PM4520, CCM-PM4530, CCM-PM4540 | PRE-COM1330: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-08-22 11:00 | 2025-08-29 11:00
C-4N-HG-TPR-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Site Survey, Preparation & Grading Works | C-56-PR-838-CI-1000, C-4N-HG-TPR-CI-0100 | C-56-PR-838-CI-1000: FS, C-4N-HG-TPR-CI-0100: FS | C-4N-HG-TPR-CI-1010 | C-4N-HG-TPR-CI-1010: FS | 2025-02-08 07:00 | 2025-02-14 17:00
C-4N-HG-TPR-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Earth Works for Equipment Foundations | C-4N-HG-TPR-CI-1000 | C-4N-HG-TPR-CI-1000: FS | C-4N-HG-TPR-CI-1020, C-4N-HG-TPR-CI-1200 | C-4N-HG-TPR-CI-1020: FS, C-4N-HG-TPR-CI-1200: FS | 2025-02-15 07:00 | 2025-02-19 17:00
C-4N-HG-TPR-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Earth Works for Pipe Support Foundations | C-4N-HG-TPR-CI-1010 | C-4N-HG-TPR-CI-1010: FS | C-4N-HG-TPR-CI-1030, C-4N-HG-TPR-CI-1210 | C-4N-HG-TPR-CI-1030: FS, C-4N-HG-TPR-CI-1210: FS | 2025-02-20 07:00 | 2025-02-25 17:00
C-4N-HG-TPR-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Earth Works for Field Instrument, JBs & Light Pole Foundations | C-4N-HG-TPR-CI-1020 | C-4N-HG-TPR-CI-1020: FS | C-4N-HG-TPR-CI-1040, C-4N-HG-TPR-CI-1220 | C-4N-HG-TPR-CI-1040: FS, C-4N-HG-TPR-CI-1220: FS | 2025-02-26 07:00 | 2025-03-03 11:00
C-4N-HG-TPR-CI-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Earth Works for Access Platforms & Misc. Structural Foundations | C-4N-HG-TPR-CI-1030 | C-4N-HG-TPR-CI-1030: FS | C-4N-HG-TPR-CI-1060, C-4N-HG-TPR-CI-1230 | C-4N-HG-TPR-CI-1060: FS, C-4N-HG-TPR-CI-1230: FS | 2025-03-03 11:00 | 2025-03-11 09:00
C-4N-HG-TPR-CI-1060 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Earth Works for Impact Wall | C-4N-HG-TPR-CI-1040 | C-4N-HG-TPR-CI-1040: FS | C-4N-HG-TPR-CI-1250 | C-4N-HG-TPR-CI-1250: FS | 2025-03-11 09:00 | 2025-03-15 15:00
C-4N-HG-TPR-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Compaction & Testing for Equipment Foundations | C-4N-HG-TPR-CI-1010 | C-4N-HG-TPR-CI-1010: FS | C-4N-HG-TPR-CI-1400 | C-4N-HG-TPR-CI-1400: FS | 2025-02-20 07:00 | 2025-02-22 17:00
C-4N-HG-TPR-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Compaction & Testing for Pipe Support Foundations | C-4N-HG-TPR-CI-1020 | C-4N-HG-TPR-CI-1020: FS | C-4N-HG-TPR-CI-1600 | C-4N-HG-TPR-CI-1600: FS | 2025-02-26 07:00 | 2025-02-28 17:00
C-4N-HG-TPR-CI-1220 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | C-4N-HG-TPR-CI-1030 | C-4N-HG-TPR-CI-1030: FS | C-4N-HG-TPR-CI-1410 | C-4N-HG-TPR-CI-1410: FS | 2025-03-03 11:00 | 2025-03-08 11:00
C-4N-HG-TPR-CI-1230 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-4N-HG-TPR-CI-1040 | C-4N-HG-TPR-CI-1040: FS | C-4N-HG-TPR-CI-1420 | C-4N-HG-TPR-CI-1420: FS | 2025-03-11 09:00 | 2025-03-15 15:00
C-4N-HG-TPR-CI-1250 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Compaction & Testing for Impact Wall | C-4N-HG-TPR-CI-1060 | C-4N-HG-TPR-CI-1060: FS | C-4N-HG-TPR-CI-1500 | C-4N-HG-TPR-CI-1500: FS | 2025-03-15 15:00 | 2025-03-18 13:00
C-4N-HG-TPR-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Concrete Works for Equipment Foundations | C-4N-HG-TPR-CI-1200, HE-CS-0650, HE-CS-1190, HE-CS-0470, HM-CS-0040, HE-CS-1310, HE-CS-0230 | C-4N-HG-TPR-CI-1200: FS, HE-CS-0650: FS, HE-CS-1190: FS, HE-CS-0470: FS, HM-CS-0040: FS, HE-CS-1310: FS, HE-CS-0230: FS | C-4N-HG-TPR-CI-1500, C-4N-HG-TPR-CI-1700, C-4N-HG-TPR-ME-1100 | C-4N-HG-TPR-CI-1500: FS, C-4N-HG-TPR-CI-1700: FF 5, C-4N-HG-TPR-ME-1100: FS | 2025-02-24 07:00 | 2025-03-11 09:00
C-4N-HG-TPR-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Concrete Works for Pipe Support Foundations | C-4N-HG-TPR-CI-1210, C-4N-HG-TPR-CI-1500 | C-4N-HG-TPR-CI-1210: FS, C-4N-HG-TPR-CI-1500: FS | C-4N-HG-TPR-CI-1410, C-4N-HG-TPR-CI-1700, C-4N-HG-TPR-CI-2000 | C-4N-HG-TPR-CI-1410: FS, C-4N-HG-TPR-CI-1700: FF 5, C-4N-HG-TPR-CI-2000: FS | 2025-04-10 13:00 | 2025-04-19 13:00
C-4N-HG-TPR-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-4N-HG-TPR-CI-1220, C-4N-HG-TPR-CI-1600 | C-4N-HG-TPR-CI-1220: FS, C-4N-HG-TPR-CI-1600: FS | C-4N-HG-TPR-CI-1420, C-4N-HG-TPR-CI-1700 | C-4N-HG-TPR-CI-1420: FS, C-4N-HG-TPR-CI-1700: FF 5 | 2025-04-19 13:00 | 2025-04-26 13:00
C-4N-HG-TPR-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Concrete Works for Access Platforms & Misc. Structural Foundations | C-4N-HG-TPR-CI-1230, C-4N-HG-TPR-CI-1410 | C-4N-HG-TPR-CI-1230: FS, C-4N-HG-TPR-CI-1410: FS | C-4N-HG-TPR-CI-3000, C-4N-HG-TPR-CI-1700 | C-4N-HG-TPR-CI-3000: FS, C-4N-HG-TPR-CI-1700: FF 5 | 2025-04-26 13:00 | 2025-05-03 13:00
C-4N-HG-TPR-CI-1500 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Concrete Works for Impact Wall | C-4N-HG-TPR-CI-1250, C-4N-HG-TPR-CI-1400, HE-CS-1250 | C-4N-HG-TPR-CI-1250: FS, C-4N-HG-TPR-CI-1400: FS, HE-CS-1250: FS | C-4N-HG-TPR-CI-1600, PRECOM-4NHG-TPR-1000, C-4N-HG-TPR-CI-1700 | C-4N-HG-TPR-CI-1600: FS, PRECOM-4NHG-TPR-1000: FS, C-4N-HG-TPR-CI-1700: FF 5 | 2025-03-19 07:00 | 2025-04-10 13:00
C-4N-HG-TPR-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Electrical & Earthing Cable Trenching | C-56-PR-838-CI-1800 | C-56-PR-838-CI-1800: FS | C-4N-HG-TPR-CI-1810 | C-4N-HG-TPR-CI-1810: FS | 2025-05-21 11:00 | 2025-05-30 11:00
C-4N-HG-TPR-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Instrument & Telecom Cable Trenching | C-4N-HG-TPR-CI-1800 | C-4N-HG-TPR-CI-1800: FS | C-4N-HG-TPR-EI-2010 | C-4N-HG-TPR-EI-2010: FS | 2025-05-30 11:00 | 2025-06-11 11:00
C-4N-HG-TPR-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Back Filling for Electrical & Earthing Cable | C-4N-HG-TPR-EI-2410, C-4N-HG-TPR-CA-1020 | C-4N-HG-TPR-EI-2410: FS, C-4N-HG-TPR-CA-1020: FS | C-4N-HG-TPR-CI-2810, PRECOM-4NHG-TPR-1000 | C-4N-HG-TPR-CI-2810: FS, PRECOM-4NHG-TPR-1000: FS | 2025-08-12 11:00 | 2025-08-19 11:00
C-4N-HG-TPR-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Back Filling for Instrument & Telecom Cable | C-4N-HG-TPR-TE-1410, C-4N-HG-TPR-CI-2800 | C-4N-HG-TPR-TE-1410: FS, C-4N-HG-TPR-CI-2800: FS | C-4N-HG-TPR-CI-2600, PRECOM-4NHG-TPR-1000 | C-4N-HG-TPR-CI-2600: FS, PRECOM-4NHG-TPR-1000: FS | 2025-08-19 11:00 | 2025-08-26 11:00
C-4N-HG-TPR-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.5 | Paving of Interlock tiles & Kerb Stone Embankment | C-4N-HG-TPR-CI-2810, C-4N-HG-TPR-CI-1700, C-4N-HG-TPR-CI-2220, ML1059-B28, HE-CS-0290 | C-4N-HG-TPR-CI-2810: FS, C-4N-HG-TPR-CI-1700: FF, C-4N-HG-TPR-CI-2220: FF, ML1059-B28: FS, HE-CS-0290: FS | PRECOM-4NHG-TPR-1000 | PRECOM-4NHG-TPR-1000: FS | 2025-08-26 11:00 | 2025-09-08 11:00
C-4N-HG-TPR-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Pre-Fabrication & Installation of Pipe Supports | C-4N-HG-TPR-CI-1600 | C-4N-HG-TPR-CI-1600: FS | C-4N-HG-TPR-EI-2210, C-4N-HG-TPR-PI-1200 | C-4N-HG-TPR-EI-2210: FS, C-4N-HG-TPR-PI-1200: FF 2 | 2025-04-19 13:00 | 2025-05-03 13:00
C-4N-HG-TPR-EI-2210 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.6.1 | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-4N-HG-TPR-CI-2000, C-4N-HG-TPR-PI-1000, C-4N-HG-TPR-PI-2000 | C-4N-HG-TPR-CI-2000: FS, C-4N-HG-TPR-PI-1000: FS, C-4N-HG-TPR-PI-2000: FS | C-4N-HG-TPR-CI-3000 | C-4N-HG-TPR-CI-3000: FS | 2025-06-16 11:00 | 2025-06-25 11:00
C-4N-HG-TPR-CI-3000 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Pre-Fabrication & Installation of Platforms & Crossovers | C-4N-HG-TPR-EI-2210, C-4N-HG-TPR-CI-1420 | C-4N-HG-TPR-EI-2210: FS, C-4N-HG-TPR-CI-1420: FS | C-4N-HG-TPR-CI-3010, PRECOM-4NHG-TPR-1000, C-4N-HG-TPR-CI-2220 | C-4N-HG-TPR-CI-3010: FS, PRECOM-4NHG-TPR-1000: FS, C-4N-HG-TPR-CI-2220: FS | 2025-06-25 11:00 | 2025-07-05 11:00
C-4N-HG-TPR-CI-3010 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.2 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-4N-HG-TPR-CI-3000 | C-4N-HG-TPR-CI-3000: FS | PRECOM-4NHG-TPR-1000, C-4N-HG-TPR-CI-2220 | PRECOM-4NHG-TPR-1000: FS, C-4N-HG-TPR-CI-2220: FF | 2025-07-05 11:00 | 2025-07-15 11:00
C-4N-HG-TPR-ME-1100 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.3.1 | Installation of Pig Receiver 4" | C-56-PR-838-ME-1100, C-4N-HG-TPR-CI-1400, HM-ME-2380, HM-PL-0530, HM-PL-0840, HM-PL-1490, HM-PL-1530 | C-56-PR-838-ME-1100: FS, C-4N-HG-TPR-CI-1400: FS, HM-ME-2380: FS, HM-PL-0530: FF, HM-PL-0840: FS, HM-PL-1490: FF, HM-PL-1530: FS | PRECOM-4NHG-TPR-1000, ML1949-E40 | PRECOM-4NHG-TPR-1000: FS, ML1949-E40: FS | 2025-05-07 12:00 | 2025-05-09 15:00
C-4N-HG-TPR-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.4.1 | Piping Pre-Fabrication | C-56-PR-838-PI-1000, ML1002, HE-PI-0510, HS-CN-0190, HM-PI-0040, ML1219-B19, HE-PI-1240, HE-PI-1300, HE-PI-0760 | C-56-PR-838-PI-1000: FS, ML1002: FS, HE-PI-0510: FS, HS-CN-0190: FS, HM-PI-0040: FS, ML1219-B19: FS, HE-PI-1240: FS, HE-PI-1300: FS, HE-PI-0760: FS | C-4N-HG-TPR-PI-1200, C-4N-HG-TPR-EI-2210 | C-4N-HG-TPR-PI-1200: FS, C-4N-HG-TPR-EI-2210: FS | 2025-04-17 13:00 | 2025-05-13 11:00
C-4N-HG-TPR-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.4.2 | Piping Erection | C-4N-HG-TPR-PI-1000, C-56-PR-838-PI-1200, C-4N-HG-TPR-CI-2000, HM-PL-0740, HM-PL-0220, HM-PI-0040, ML1219-B19, HE-PI-1240, ML1869-E32, HE-PI-1300, HM-PL-0640, HM-PL-0630, HM-PL-1510, HM-PL-1570 | C-4N-HG-TPR-PI-1000: FS, C-56-PR-838-PI-1200: FS, C-4N-HG-TPR-CI-2000: FF 2, HM-PL-0740: FS, HM-PL-0220: FS, HM-PI-0040: FS, ML1219-B19: FS, HE-PI-1240: FS, ML1869-E32: FS, HE-PI-1300: FS, HM-PL-0640: FS, HM-PL-0630: FS, HM-PL-1510: FS, HM-PL-1570: FS | C-4N-HG-TPR-PI-1400, C-4N-HG-TPR-PI-1400 | C-4N-HG-TPR-PI-1400: SS 2, C-4N-HG-TPR-PI-1400: FS | 2025-05-13 11:00 | 2025-05-20 11:00
C-4N-HG-TPR-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.4.3 | Field Joint Welding | C-4N-HG-TPR-PI-1200, C-4N-HG-TPR-PI-1200, C-56-PR-838-PI-1400, HE-PI-1300, ML1002, HS-CN-0190, ML1219-B19 | C-4N-HG-TPR-PI-1200: SS 2, C-4N-HG-TPR-PI-1200: FS, C-56-PR-838-PI-1400: FS, HE-PI-1300: FS, ML1002: FS, HS-CN-0190: FS, ML1219-B19: FS | C-4N-HG-TPR-PI-1410, C-4N-HG-TPR-PI-1410 | C-4N-HG-TPR-PI-1410: SS 3, C-4N-HG-TPR-PI-1410: FS | 2025-05-20 11:00 | 2025-05-27 11:00
C-4N-HG-TPR-PI-1410 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.4.3 | NDT & Coating for Field Joint Weld | C-4N-HG-TPR-PI-1400, C-4N-HG-TPR-PI-1400 | C-4N-HG-TPR-PI-1400: SS 3, C-4N-HG-TPR-PI-1400: FS | C-4N-HG-TPR-PI-1600, C-4N-HG-TPR-PI-1600 | C-4N-HG-TPR-PI-1600: FS, C-4N-HG-TPR-PI-1600: FF | 2025-05-27 11:00 | 2025-06-03 11:00
C-4N-HG-TPR-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.4.4 | Hydrotesting | C-4N-HG-TPR-PI-1410, C-4N-HG-TPR-PI-1410, ML1219-B19 | C-4N-HG-TPR-PI-1410: FS, C-4N-HG-TPR-PI-1410: FF, ML1219-B19: FS | C-4N-HG-TPR-PI-1800, C-4N-HG-TPR-PI-1800 | C-4N-HG-TPR-PI-1800: FS, C-4N-HG-TPR-PI-1800: FF | 2025-06-03 11:00 | 2025-06-09 11:00
C-4N-HG-TPR-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.4.5 | Installation of Valves/MOV/ROV | C-4N-HG-TPR-PI-1600, C-4N-HG-TPR-PI-1600, HE-PI-1300, ML1002, HM-PL-0220, HS-CN-0190, ML1219-B19, HE-PI-1240, ML1869-E32, HM-PL-1570 | C-4N-HG-TPR-PI-1600: FS, C-4N-HG-TPR-PI-1600: FF, HE-PI-1300: FS, ML1002: FS, HM-PL-0220: FS, HS-CN-0190: FS, ML1219-B19: FS, HE-PI-1240: FS, ML1869-E32: FS, HM-PL-1570: FS | C-4N-HG-TPR-PI-2000, C-4N-HG-TPR-PI-2000 | C-4N-HG-TPR-PI-2000: SS 4, C-4N-HG-TPR-PI-2000: FS | 2025-06-09 11:00 | 2025-06-12 11:00
C-4N-HG-TPR-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.4.6 | Final Bolt Torquing/ Re-Instatement | C-4N-HG-TPR-PI-1800, C-4N-HG-TPR-PI-1800, ML1002, HM-PL-0740, HM-PL-0220, HS-CN-0190, HM-PI-0040, ML1219-B19, HE-PI-1240, ML1869-E32, HE-PI-1300, HM-PL-0640, HM-PL-0630, HM-PL-1510, HM-PL-1570 | C-4N-HG-TPR-PI-1800: SS 4, C-4N-HG-TPR-PI-1800: FS, ML1002: FS, HM-PL-0740: FS, HM-PL-0220: FS, HS-CN-0190: FS, HM-PI-0040: FS, ML1219-B19: FS, HE-PI-1240: FS, ML1869-E32: FS, HE-PI-1300: FS, HM-PL-0640: FS, HM-PL-0630: FS, HM-PL-1510: FS, HM-PL-1570: FS | PRECOM-4NHG-TPR-1000, ML1949-E40, C-4N-HG-TPR-EI-2210 | PRECOM-4NHG-TPR-1000: FS, ML1949-E40: FS, C-4N-HG-TPR-EI-2210: FS | 2025-06-13 11:00 | 2025-06-16 11:00
C-4N-HG-TPR-PL-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.5.9 | Installation of Isolation Joint | C-56-PR-838-PL-1000 | C-56-PR-838-PL-1000: FS | C-4N-HG-TPR-PL-1010 | C-4N-HG-TPR-PL-1010: FS | 2025-08-01 07:00 | 2025-08-01 17:00
C-4N-HG-TPR-PL-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.5.9 | Field Joint Welding (Piping/Pipeline Section including IJ) | C-4N-HG-TPR-PL-1000 | C-4N-HG-TPR-PL-1000: FS | C-4N-HG-TPR-PL-1020 | C-4N-HG-TPR-PL-1020: FS | 2025-08-02 07:00 | 2025-08-04 17:00
C-4N-HG-TPR-PL-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.5.9 | NDT for Weld Joint | C-4N-HG-TPR-PL-1010 | C-4N-HG-TPR-PL-1010: FS | C-4N-HG-TPR-PL-1030 | C-4N-HG-TPR-PL-1030: FS | 2025-08-05 07:00 | 2025-08-06 17:00
C-4N-HG-TPR-PL-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.5.9 | Ext. Coating for Weld Joint | C-4N-HG-TPR-PL-1020 | C-4N-HG-TPR-PL-1020: FS | PRECOM-4NHG-TPR-1000, ML1929-E38, ML1949-E40, CCM-PM4510 | PRECOM-4NHG-TPR-1000: FS, ML1929-E38: FS, ML1949-E40: FS, CCM-PM4510: FS | 2025-08-07 07:00 | 2025-08-08 17:00
C-4N-HG-TPR-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.6.2 | Electrical & Earthing Cable Laying | C-56-PR-838-EI-2000, HE-EL-0830, HE-EL-0470, HE-EL-0590, HM-EL-0080, HE-EL-1610, HE-IC-0830, HM-EL-0520, HE-IC-1010, HE-IC-0950, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-6 | C-56-PR-838-EI-2000: FS, HE-EL-0830: FS, HE-EL-0470: FS, HE-EL-0590: FS, HM-EL-0080: FS, HE-EL-1610: FS, HE-IC-0830: FS, HM-EL-0520: FS, HE-IC-1010: FS, HE-IC-0950: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0 | C-4N-HG-TPR-EI-2020 | C-4N-HG-TPR-EI-2020: FS | 2025-06-17 11:00 | 2025-06-23 11:00
C-4N-HG-TPR-EI-2020 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.6.2 | Installation of Cable Trays | C-4N-HG-TPR-EI-2000 | C-4N-HG-TPR-EI-2000: FS | C-4N-HG-TPR-EI-2010 | C-4N-HG-TPR-EI-2010: FS | 2025-06-23 11:00 | 2025-06-26 11:00
C-4N-HG-TPR-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.6.2 | Instrument Cable Laying | C-4N-HG-TPR-EI-2020, C-56-PR-838-EI-2010, C-4N-HG-TPR-CI-1810 | C-4N-HG-TPR-EI-2020: FS, C-56-PR-838-EI-2010: FS, C-4N-HG-TPR-CI-1810: FS | C-4N-HG-TPR-EI-2030 | C-4N-HG-TPR-EI-2030: FS | 2025-07-16 11:00 | 2025-07-22 11:00
C-4N-HG-TPR-EI-2030 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.6.2 | Instrument Tubing Works | C-4N-HG-TPR-EI-2010 | C-4N-HG-TPR-EI-2010: FS | C-4N-HG-TPR-EI-1800 | C-4N-HG-TPR-EI-1800: FS | 2025-07-22 11:00 | 2025-07-26 11:00
C-4N-HG-TPR-EI-1800 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.6.1 | Installation of Light Pole, Lighting & Fixtures | C-4N-HG-TPR-EI-2030, HE-IC-1550, HE-IC-0650, HE-IC-1430, HM-EL-0280, HE-IC-0590, HM-EL-0380, HE-IC-2570, HE-EL-1670, HE-IC-0710, HE-IC-0770, HM-IC-0040, HE-EL-1010, HE-EL-1730, HE-EL-1790, HE-EL-0530, ML1032-B21, HE-IC-0010, HM-EL-0080, HM-EL-0520, HM-ME-1 | C-4N-HG-TPR-EI-2030: FS, HE-IC-1550: FS, HE-IC-0650: FS, HE-IC-1430: FS, HM-EL-0280: FS, HE-IC-0590: FS, HM-EL-0380: FS, HE-IC-2570: FS, HE-EL-1670: FS, HE-IC-0710: FS, HE-IC-0770: FS, HM-IC-0040: FS, HE-EL-1010: FS, HE-EL-1730: FS, HE-EL-1790: FS, HE-EL-0 | C-4N-HG-TPR-EI-1810 | C-4N-HG-TPR-EI-1810: FS | 2025-07-26 11:00 | 2025-08-01 11:00
C-4N-HG-TPR-EI-1810 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.6.1 | Installation of JB's | C-4N-HG-TPR-EI-1800 | C-4N-HG-TPR-EI-1800: FS | C-4N-HG-TPR-EI-2200 | C-4N-HG-TPR-EI-2200: FS | 2025-08-01 11:00 | 2025-08-05 11:00
C-4N-HG-TPR-EI-2200 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.6.1 | Installation of Field Instruments (Including Pig Signaller) | C-4N-HG-TPR-EI-1810 | C-4N-HG-TPR-EI-1810: FS | C-4N-HG-TPR-EI-2410 | C-4N-HG-TPR-EI-2410: FS | 2025-08-05 11:00 | 2025-08-08 11:00
C-4N-HG-TPR-EI-2410 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.6.1 | Installation of F&G Device | C-4N-HG-TPR-EI-2200 | C-4N-HG-TPR-EI-2200: FS | C-4N-HG-TPR-EI-2040, C-4N-HG-TPR-CI-2800 | C-4N-HG-TPR-EI-2040: FS, C-4N-HG-TPR-CI-2800: FS | 2025-08-08 11:00 | 2025-08-12 11:00
C-4N-HG-TPR-EI-2040 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.6.2 | Loop Checking for Instruments | C-4N-HG-TPR-EI-2410 | C-4N-HG-TPR-EI-2410: FS | C-4N-HG-TPR-EI-2050, PRECOM-4NHG-TPR-1000 | C-4N-HG-TPR-EI-2050: FS, PRECOM-4NHG-TPR-1000: FS | 2025-08-12 11:00 | 2025-08-18 11:00
C-4N-HG-TPR-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.6.2 | Glanding & Termination | C-4N-HG-TPR-EI-2040 | C-4N-HG-TPR-EI-2040: FS | PRECOM-4NHG-TPR-1000 | PRECOM-4NHG-TPR-1000: FS | 2025-08-18 11:00 | 2025-08-21 11:00
C-4N-HG-TPR-CA-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.6.2 | CP Cable Laying | C-56-PR-838-CA-1000, HE-EL-0830, HE-EL-0470, HE-EL-0590, HM-EL-0080, HE-EL-1610, HE-IC-0830, HM-EL-0520, HE-IC-1010, HE-IC-0950, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-6 | C-56-PR-838-CA-1000: FS, HE-EL-0830: FS, HE-EL-0470: FS, HE-EL-0590: FS, HM-EL-0080: FS, HE-EL-1610: FS, HE-IC-0830: FS, HM-EL-0520: FS, HE-IC-1010: FS, HE-IC-0950: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-IC-0 | C-4N-HG-TPR-CA-1010 | C-4N-HG-TPR-CA-1010: FS | 2025-07-23 11:00 | 2025-07-25 11:00
C-4N-HG-TPR-CA-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.6.2 | Installation of CP Test Post | C-4N-HG-TPR-CA-1000 | C-4N-HG-TPR-CA-1000: FS | C-4N-HG-TPR-CA-1020 | C-4N-HG-TPR-CA-1020: FS | 2025-07-25 11:00 | 2025-07-28 11:00
C-4N-HG-TPR-CA-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.6.2 | Installation of CP JB's | C-4N-HG-TPR-CA-1010 | C-4N-HG-TPR-CA-1010: FS | C-4N-HG-TPR-CA-1030, C-4N-HG-TPR-CI-2800 | C-4N-HG-TPR-CA-1030: FS, C-4N-HG-TPR-CI-2800: FS | 2025-07-28 11:00 | 2025-07-30 11:00
C-4N-HG-TPR-CA-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.6.2 | Glanding & Termination for CP S/m | C-4N-HG-TPR-CA-1020, C-56-PR-838-CA-1030 | C-4N-HG-TPR-CA-1020: FS, C-56-PR-838-CA-1030: FS | PRECOM-4NHG-TPR-1000 | PRECOM-4NHG-TPR-1000: FS | 2025-07-30 11:00 | 2025-07-31 11:00
C-4N-HG-TPR-TE-1410 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.8.1 | FOC Laying | C-56-PR-838-TE-1410, ML1033-B22, HE-TL-0710, HE-TL-0770, HM-TL-0040, HS-CN-0290, HE-TL-0830, HE-IC-0110, HE-TL-0470 | C-56-PR-838-TE-1410: FS, ML1033-B22: FS, HE-TL-0710: FS, HE-TL-0770: FS, HM-TL-0040: FS, HS-CN-0290: FS, HE-TL-0830: FS, HE-IC-0110: FS, HE-TL-0470: FS | C-4N-HG-TPR-TE-1420, C-4N-HG-TPR-CI-2810 | C-4N-HG-TPR-TE-1420: FS, C-4N-HG-TPR-CI-2810: FS | 2025-08-01 11:00 | 2025-08-08 11:00
C-4N-HG-TPR-TE-1420 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.8.1 | FO Cable OTDR Testing & Splicing | C-4N-HG-TPR-TE-1410, C-56-PR-838-TE-1420 | C-4N-HG-TPR-TE-1410: FS, C-56-PR-838-TE-1420: FS | PRECOM-4NHG-TPR-1000, ML1949-E40 | PRECOM-4NHG-TPR-1000: FS, ML1949-E40: FS | 2025-08-25 11:00 | 2025-08-27 11:00
C-4N-H5-TPL-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 | Site Survey, Preparation & Grading Works | C-4N-H5-TPL-CI-0100 | C-4N-H5-TPL-CI-0100: FS | C-4N-H5-TPL-CI-1010 | C-4N-H5-TPL-CI-1010: FS | 2025-01-09 07:00 | 2025-01-13 17:00
C-4N-H5-TPL-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 | Earth Works for Equipment Foundations | C-4N-H5-TPL-CI-1000 | C-4N-H5-TPL-CI-1000: FS | C-4N-H5-TPL-CI-1020 | C-4N-H5-TPL-CI-1020: FS | 2025-01-14 07:00 | 2025-01-17 17:00
C-4N-H5-TPL-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 | Earth Works for Pipe Support Foundations | C-4N-H5-TPL-CI-1010 | C-4N-H5-TPL-CI-1010: FS | C-4N-H5-TPL-CI-1030 | C-4N-H5-TPL-CI-1030: FS | 2025-01-18 07:00 | 2025-01-22 17:00
C-4N-H5-TPL-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 | Earth Works for Field Instrument, JBs & Light Pole Foundations | C-4N-H5-TPL-CI-1020 | C-4N-H5-TPL-CI-1020: FS | C-4N-H5-TPL-CI-1040 | C-4N-H5-TPL-CI-1040: FS | 2025-01-23 07:00 | 2025-01-27 17:00
C-4N-H5-TPL-CI-1040 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 | Earth Works for Access Platforms & Misc. Structural Foundations | C-4N-H5-TPL-CI-1030 | C-4N-H5-TPL-CI-1030: FS | C-4N-H5-TPL-CI-1200, C-4N-HG-TPR-CI-0100 | C-4N-H5-TPL-CI-1200: FS, C-4N-HG-TPR-CI-0100: FS | 2025-01-28 07:00 | 2025-01-31 17:00
C-4N-H5-TPL-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 | Compaction & Testing for Equipment Foundations | C-4N-H5-TPL-CI-1040 | C-4N-H5-TPL-CI-1040: FS | C-4N-H5-TPL-CI-1210 | C-4N-H5-TPL-CI-1210: FS | 2025-02-01 07:00 | 2025-02-04 17:00
C-4N-H5-TPL-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 | Compaction & Testing for Pipe Support Foundations | C-4N-H5-TPL-CI-1200 | C-4N-H5-TPL-CI-1200: FS | C-4N-H5-TPL-CI-1220, C-4N-H5-TPL-PR-1000 | C-4N-H5-TPL-CI-1220: FS, C-4N-H5-TPL-PR-1000: FS | 2025-02-05 07:00 | 2025-02-07 17:00
C-4N-H5-TPL-CI-1220 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | C-4N-H5-TPL-CI-1210 | C-4N-H5-TPL-CI-1210: FS | C-4N-H5-TPL-CI-1230 | C-4N-H5-TPL-CI-1230: FS | 2025-02-08 07:00 | 2025-02-11 17:00
C-4N-H5-TPL-CI-1230 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-4N-H5-TPL-CI-1220 | C-4N-H5-TPL-CI-1220: FS | C-4N-H5-TPL-CI-1400 | C-4N-H5-TPL-CI-1400: FS 15 | 2025-02-12 07:00 | 2025-02-14 17:00
C-4N-H5-TPL-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 | Concrete Works for Equipment Foundations | C-4N-H5-TPL-CI-1230, HE-CS-0650, HE-CS-1310, HE-CS-0230, HE-CS-1190, HM-CS-0040 | C-4N-H5-TPL-CI-1230: FS 15, HE-CS-0650: FS, HE-CS-1310: FS, HE-CS-0230: FS, HE-CS-1190: FS, HM-CS-0040: FS | C-4N-H5-TPL-CI-1600, C-4N-H5-TPL-ME-1000, C-4N-H5-TPL-CI-1700 | C-4N-H5-TPL-CI-1600: FS, C-4N-H5-TPL-ME-1000: FS, C-4N-H5-TPL-CI-1700: FF 5 | 2025-03-05 09:00 | 2025-03-23 09:00
C-4N-H5-TPL-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 | Concrete Works for Pipe Support Foundations | C-4N-H5-TPL-CI-1400 | C-4N-H5-TPL-CI-1400: FS | C-4N-H5-TPL-CI-1410, C-4N-H5-TPL-CI-2000, C-4N-H5-TPL-CI-1700 | C-4N-H5-TPL-CI-1410: FS, C-4N-H5-TPL-CI-2000: FS, C-4N-H5-TPL-CI-1700: FF 5 | 2025-03-23 09:00 | 2025-04-07 13:00
C-4N-H5-TPL-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-4N-H5-TPL-CI-1600 | C-4N-H5-TPL-CI-1600: FS | C-4N-H5-TPL-CI-1420, C-4N-H5-TPL-EI-2210, C-4N-H5-TPL-CI-1700 | C-4N-H5-TPL-CI-1420: FS, C-4N-H5-TPL-EI-2210: FS, C-4N-H5-TPL-CI-1700: FF 5 | 2025-04-07 13:00 | 2025-04-14 13:00
C-4N-H5-TPL-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 | Concrete Works for Access Platforms & Misc. Structural Foundations | C-4N-H5-TPL-CI-1410 | C-4N-H5-TPL-CI-1410: FS | C-4N-H5-TPL-CI-1800, C-4N-H5-TPL-CI-3000, C-4N-H5-TPL-CI-1700 | C-4N-H5-TPL-CI-1800: FS 30, C-4N-H5-TPL-CI-3000: FS, C-4N-H5-TPL-CI-1700: FF 5 | 2025-04-14 13:00 | 2025-04-21 13:00
C-4N-H5-TPL-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.8 | Electrical & Earthing Cable Trenching | C-4N-H5-TPL-CI-1420, HE-CS-0530 | C-4N-H5-TPL-CI-1420: FS 30, HE-CS-0530: FS | C-4N-H5-TPL-CI-1810, C-4N-H5-TPL-EI-2000 | C-4N-H5-TPL-CI-1810: FS, C-4N-H5-TPL-EI-2000: FS 30 | 2025-05-27 11:00 | 2025-06-07 11:00
C-4N-H5-TPL-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.8 | Instrument & Telecom Cable Trenching | C-4N-H5-TPL-CI-1800 | C-4N-H5-TPL-CI-1800: FS | C-4N-H5-TPL-EI-2010 | C-4N-H5-TPL-EI-2010: FS | 2025-06-07 11:00 | 2025-06-17 11:00
C-4N-H5-TPL-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.10 | Back Filling for Electrical & Earthing Cable | C-4N-H5-TPL-ME-1000, C-4N-H5-TPL-EI-2050, C-4N-H5-TPL-CA-1030 | C-4N-H5-TPL-ME-1000: FS, C-4N-H5-TPL-EI-2050: FS, C-4N-H5-TPL-CA-1030: FS | C-4N-H5-TPL-CI-2810, C-4N-H5-TPL-CI-2810, PRECOM-4NH5-TPL-1000 | C-4N-H5-TPL-CI-2810: FF 3, C-4N-H5-TPL-CI-2810: SS 3, PRECOM-4NH5-TPL-1000: FS | 2025-08-28 11:00 | 2025-09-04 11:00
C-4N-H5-TPL-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.10 | Back Filling for Instrument & Telecom Cable | C-4N-H5-TPL-CI-2800, C-4N-H5-TPL-CI-2800 | C-4N-H5-TPL-CI-2800: FF 3, C-4N-H5-TPL-CI-2800: SS 3 | C-4N-H5-TPL-CI-2600, PRECOM-4NH5-TPL-1000 | C-4N-H5-TPL-CI-2600: FF, PRECOM-4NH5-TPL-1000: FS | 2025-09-01 11:00 | 2025-09-09 11:00
C-4N-H5-TPL-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.9 | Paving of Interlock tiles & Kerb Stone Embankment | C-4N-H5-TPL-CI-2810, ML1059-B28, HE-CS-0290 | C-4N-H5-TPL-CI-2810: FF, ML1059-B28: FS, HE-CS-0290: FS | PRECOM-4NH5-TPL-1000 | PRECOM-4NH5-TPL-1000: FS | 2025-08-27 11:00 | 2025-09-09 11:00
C-4N-H5-TPL-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 | Pre-Fabrication & Installation of Pipe Supports | C-4N-H5-TPL-CI-1600, C-4N-H5-TPL-PR-1200, C-4N-H5-TPL-CI-1700, HS-CN-0690, HM-CS-0110, HE-CS-1490, HE-CS-1430, HM-CS-0120 | C-4N-H5-TPL-CI-1600: FS, C-4N-H5-TPL-PR-1200: FS, C-4N-H5-TPL-CI-1700: FF, HS-CN-0690: FS, HM-CS-0110: FS, HE-CS-1490: FS, HE-CS-1430: FS, HM-CS-0120: FF | C-4N-H5-TPL-EI-2210 | C-4N-H5-TPL-EI-2210: FS | 2025-06-04 11:00 | 2025-06-20 11:00
C-4N-H5-TPL-EI-2210 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-4N-H5-TPL-CI-1410, C-4N-H5-TPL-CI-2000 | C-4N-H5-TPL-CI-1410: FS, C-4N-H5-TPL-CI-2000: FS | C-4N-H5-TPL-CI-3000 | C-4N-H5-TPL-CI-3000: FS | 2025-06-20 11:00 | 2025-07-01 11:00
C-4N-H5-TPL-CI-3000 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 | Pre-Fabrication & Installation of Platforms & Crossovers | C-4N-H5-TPL-CI-1420, C-4N-H5-TPL-EI-2210, HS-CN-0690, HM-CS-0110, HE-CS-1490, HE-CS-1430, HM-CS-0120 | C-4N-H5-TPL-CI-1420: FS, C-4N-H5-TPL-EI-2210: FS, HS-CN-0690: FS, HM-CS-0110: FS, HE-CS-1490: FS, HE-CS-1430: FS, HM-CS-0120: FF | C-4N-H5-TPL-CI-3010, C-4N-H5-TPL-CI-3010, PRECOM-4NH5-TPL-1000 | C-4N-H5-TPL-CI-3010: FS, C-4N-H5-TPL-CI-3010: FF, PRECOM-4NH5-TPL-1000: FS | 2025-07-01 11:00 | 2025-07-10 11:00
C-4N-H5-TPL-CI-3010 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-4N-H5-TPL-CI-3000, C-4N-H5-TPL-CI-3000 | C-4N-H5-TPL-CI-3000: FS, C-4N-H5-TPL-CI-3000: FF | C-4N-H5-TPL-PI-1000, PRECOM-4NH5-TPL-1000 | C-4N-H5-TPL-PI-1000: FS, PRECOM-4NH5-TPL-1000: FS | 2025-07-10 11:00 | 2025-07-19 11:00
C-4N-H5-TPL-ME-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.3.1 | Installation of Pig Launcher 4" | C-4N-H5-TPL-CI-1400, C-56-PR-838-ME-1100, HM-PL-0840, HM-PL-0530, ML1015-B08, HM-PL-1490, HM-PL-1530 | C-4N-H5-TPL-CI-1400: FS, C-56-PR-838-ME-1100: FS 35, HM-PL-0840: FS, HM-PL-0530: FS, ML1015-B08: FS, HM-PL-1490: FS, HM-PL-1530: FS | C-4N-H5-TPL-PI-1200, C-4N-H5-TPL-CI-2800, PRECOM-4NH5-TPL-1000, ML1949-E40 | C-4N-H5-TPL-PI-1200: FS, C-4N-H5-TPL-CI-2800: FS, PRECOM-4NH5-TPL-1000: FS, ML1949-E40: FS | 2025-05-10 11:00 | 2025-05-14 11:00
C-4N-H5-TPL-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.4.1 | Piping Pre-Fabrication | C-4N-H5-TPL-CI-3010, ML1002, HE-PI-1300, HM-PI-0040, HE-PI-0760, ML1219-B19, HS-CN-0190, HE-PI-1240, HE-PI-0510 | C-4N-H5-TPL-CI-3010: FS, ML1002: FS, HE-PI-1300: FS, HM-PI-0040: FS, HE-PI-0760: FS, ML1219-B19: FS, HS-CN-0190: FS, HE-PI-1240: FS, HE-PI-0510: FS | C-4N-H5-TPL-PI-1200, C-4N-H5-TPL-PI-1200 | C-4N-H5-TPL-PI-1200: FS, C-4N-H5-TPL-PI-1200: FF | 2025-07-19 11:00 | 2025-08-13 11:00
C-4N-H5-TPL-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.4.2 | Piping Erection | C-4N-H5-TPL-PI-1000, C-4N-H5-TPL-PI-1000, C-4N-H5-TPL-ME-1000, HM-PL-0220, HM-PL-0630, HE-PI-1300, HM-PI-0040, ML1219-B19, HM-PL-0740, HM-PL-0640, HE-PI-1240, HM-PL-1510, HM-PL-1570 | C-4N-H5-TPL-PI-1000: FS, C-4N-H5-TPL-PI-1000: FF, C-4N-H5-TPL-ME-1000: FS, HM-PL-0220: FS, HM-PL-0630: FS, HE-PI-1300: FS, HM-PI-0040: FS, ML1219-B19: FS, HM-PL-0740: FS, HM-PL-0640: FS, HE-PI-1240: FS, HM-PL-1510: FS, HM-PL-1570: FS | C-4N-H5-TPL-PI-1400, C-4N-H5-TPL-PI-1400 | C-4N-H5-TPL-PI-1400: SS 2, C-4N-H5-TPL-PI-1400: FF | 2025-08-13 11:00 | 2025-08-20 11:00
C-4N-H5-TPL-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.4.3 | Field Joint Welding | C-4N-H5-TPL-PI-1200, C-4N-H5-TPL-PI-1200, HE-PI-1300, ML1002, ML1219-B19, HS-CN-0190 | C-4N-H5-TPL-PI-1200: SS 2, C-4N-H5-TPL-PI-1200: FF, HE-PI-1300: FS, ML1002: FS, ML1219-B19: FS, HS-CN-0190: FS | C-4N-H5-TPL-PI-1410, C-4N-H5-TPL-PI-1410 | C-4N-H5-TPL-PI-1410: SS 3, C-4N-H5-TPL-PI-1410: FF | 2025-08-15 11:00 | 2025-08-22 11:00
C-4N-H5-TPL-PI-1410 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.4.3 | NDT & Coating for Field Joint Weld | C-4N-H5-TPL-PI-1400, C-4N-H5-TPL-PI-1400 | C-4N-H5-TPL-PI-1400: SS 3, C-4N-H5-TPL-PI-1400: FF | C-4N-H5-TPL-PI-1600 | C-4N-H5-TPL-PI-1600: FS | 2025-08-19 11:00 | 2025-08-26 11:00
C-4N-H5-TPL-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.4.4 | Hydrotesting | C-4N-H5-TPL-PI-1410, ML1219-B19 | C-4N-H5-TPL-PI-1410: FS, ML1219-B19: FS | C-4N-H5-TPL-PI-1800 | C-4N-H5-TPL-PI-1800: FS | 2025-08-26 11:00 | 2025-08-29 11:00
C-4N-H5-TPL-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.4.5 | Installation of Valves/MOV/ROV | C-4N-H5-TPL-PI-1600, HM-PL-0220, ML1219-B19, HE-PI-1240, HM-PL-1570 | C-4N-H5-TPL-PI-1600: FS, HM-PL-0220: FS, ML1219-B19: FS, HE-PI-1240: FS, HM-PL-1570: FS | C-4N-H5-TPL-PI-2000, C-4N-H5-TPL-PI-2000 | C-4N-H5-TPL-PI-2000: SS 4, C-4N-H5-TPL-PI-2000: FS | 2025-08-29 11:00 | 2025-09-02 11:00
C-4N-H5-TPL-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.4.6 | Final Bolt Torquing/ Re-Instatement | C-4N-H5-TPL-PI-1800, C-4N-H5-TPL-PI-1800, HE-PI-1300, ML1002, HM-PL-0220, HM-PI-0040, ML1219-B19, HS-CN-0190, HE-PI-1240, HM-PL-1570 | C-4N-H5-TPL-PI-1800: SS 4, C-4N-H5-TPL-PI-1800: FS, HE-PI-1300: FS, ML1002: FS, HM-PL-0220: FS, HM-PI-0040: FS, ML1219-B19: FS, HS-CN-0190: FS, HE-PI-1240: FS, HM-PL-1570: FS | PRECOM-4NH5-TPL-1000, ML1949-E40 | PRECOM-4NH5-TPL-1000: FS, ML1949-E40: FS | 2025-09-03 11:00 | 2025-09-06 11:00
C-4N-H5-TPL-PL-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.5.10 | Installation of Isolation Joint | C-4N-H5HG-PIPEL-4810, C-4N-H5HG-PIPEL-5010, HE-PR-0290 | C-4N-H5HG-PIPEL-4810: FS, C-4N-H5HG-PIPEL-5010: FS, HE-PR-0290: FS | C-4N-H5-TPL-PL-1010, ML1949-E40, CCM-PM4510 | C-4N-H5-TPL-PL-1010: FS, ML1949-E40: FS, CCM-PM4510: FS | 2025-06-12 12:30 | 2025-06-13 12:30
C-4N-H5-TPL-PL-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.5.11 | Field Joint Welding (Piping/Pipeline Section including IJ) | C-4N-H5-TPL-PL-1000 | C-4N-H5-TPL-PL-1000: FS | C-4N-H5-TPL-PL-1020 | C-4N-H5-TPL-PL-1020: FS | 2025-06-13 12:30 | 2025-06-16 12:30
C-4N-H5-TPL-PL-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.5.11 | NDT for Weld Joint | C-4N-H5-TPL-PL-1010 | C-4N-H5-TPL-PL-1010: FS | C-4N-H5-TPL-PL-1030 | C-4N-H5-TPL-PL-1030: FS | 2025-06-16 12:30 | 2025-06-18 12:30
C-4N-H5-TPL-PL-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.5.11 | Ext. Coating for Weld Joint | C-4N-H5-TPL-PL-1020 | C-4N-H5-TPL-PL-1020: FS | PRECOM-4NH5-TPL-1000, ML1929-E38, ML1949-E40, CCM-PM4510, A3980 | PRECOM-4NH5-TPL-1000: FS, ML1929-E38: FS, ML1949-E40: FS, CCM-PM4510: FS, A3980: FS | 2025-06-18 12:30 | 2025-06-20 12:30
C-4N-H5-TPL-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 | Electrical & Earthing Cable Laying | C-4N-H5-TPL-CI-1800, HE-EL-0590, HE-EL-1610, HE-EL-0830, HE-EL-0470, HM-EL-0080, HM-EL-0520, HE-IC-1010, HE-IC-0950, HE-IC-0830, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HM-EL-6 | C-4N-H5-TPL-CI-1800: FS 30, HE-EL-0590: FS, HE-EL-1610: FS, HE-EL-0830: FS, HE-EL-0470: FS, HM-EL-0080: FS, HM-EL-0520: FS, HE-IC-1010: FS, HE-IC-0950: FS, HE-IC-0830: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0590: FS, HE-IC-0570: FS, HE-I | C-4N-H5-TPL-EI-2020, C-4N-H5-TPL-CA-1000 | C-4N-H5-TPL-EI-2020: FS, C-4N-H5-TPL-CA-1000: FS | 2025-07-14 11:00 | 2025-07-19 11:00
C-4N-H5-TPL-EI-2020 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 | Installation of Cable Trays | C-4N-H5-TPL-EI-2000 | C-4N-H5-TPL-EI-2000: FS | C-4N-H5-TPL-EI-2010 | C-4N-H5-TPL-EI-2010: FS | 2025-07-19 11:00 | 2025-07-23 11:00
C-4N-H5-TPL-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 | Instrument Cable Laying | C-4N-H5-TPL-EI-2020, C-4N-H5-TPL-CI-1810 | C-4N-H5-TPL-EI-2020: FS, C-4N-H5-TPL-CI-1810: FS | C-4N-H5-TPL-EI-2030, C-4N-H5-TPL-TE-1410 | C-4N-H5-TPL-EI-2030: FS, C-4N-H5-TPL-TE-1410: FS | 2025-07-23 11:00 | 2025-07-29 11:00
C-4N-H5-TPL-EI-2030 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 | Instrument Tubing Works | C-4N-H5-TPL-EI-2010 | C-4N-H5-TPL-EI-2010: FS | C-4N-H5-TPL-EI-1800 | C-4N-H5-TPL-EI-1800: FS | 2025-07-29 11:00 | 2025-08-02 11:00
C-4N-H5-TPL-EI-1800 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 | Installation of Light Pole, Lighting & Fixtures | C-4N-H5-TPL-EI-2030, HE-IC-0490, HE-EL-1010, HM-EL-0280, HE-IC-0590, HE-IC-0710, HE-EL-1790, HE-IC-1550, HE-IC-0770, HM-EL-0380, HE-EL-1670, HE-IC-0010, HM-IC-0040, HE-IC-1430, ML1032-B21, HM-ME-1590, HM-EL-0520, HE-IC-0530, HM-EL-0080, HM-ME-1690, HE-IC-2 | C-4N-H5-TPL-EI-2030: FS, HE-IC-0490: FS, HE-EL-1010: FS, HM-EL-0280: FS, HE-IC-0590: FS, HE-IC-0710: FS, HE-EL-1790: FS, HE-IC-1550: FS, HE-IC-0770: FS, HM-EL-0380: FS, HE-EL-1670: FS, HE-IC-0010: FS, HM-IC-0040: FS, HE-IC-1430: FS, ML1032-B21: FS, HM-ME-1 | C-4N-H5-TPL-EI-1810 | C-4N-H5-TPL-EI-1810: FS | 2025-08-02 11:00 | 2025-08-08 11:00
C-4N-H5-TPL-EI-1810 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 | Installation of JB's | C-4N-H5-TPL-EI-1800 | C-4N-H5-TPL-EI-1800: FS | C-4N-H5-TPL-EI-2200 | C-4N-H5-TPL-EI-2200: FS | 2025-08-08 11:00 | 2025-08-12 11:00
C-4N-H5-TPL-EI-2200 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 | Installation of Field Instruments (Including Pig Signaller) | C-4N-H5-TPL-EI-1810 | C-4N-H5-TPL-EI-1810: FS | C-4N-H5-TPL-EI-2410 | C-4N-H5-TPL-EI-2410: FS | 2025-08-12 11:00 | 2025-08-15 11:00
C-4N-H5-TPL-EI-2410 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 | Installation of F&G Device | C-4N-H5-TPL-EI-2200 | C-4N-H5-TPL-EI-2200: FS | C-4N-H5-TPL-EI-2040 | C-4N-H5-TPL-EI-2040: FS | 2025-08-15 11:00 | 2025-08-19 11:00
C-4N-H5-TPL-EI-2040 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 | Loop Checking for Instruments | C-4N-H5-TPL-EI-2410 | C-4N-H5-TPL-EI-2410: FS | C-4N-H5-TPL-EI-2050, PRECOM-4NH5-TPL-1000 | C-4N-H5-TPL-EI-2050: FS, PRECOM-4NH5-TPL-1000: FS | 2025-08-19 11:00 | 2025-08-25 11:00
C-4N-H5-TPL-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 | Glanding & Termination | C-4N-H5-TPL-EI-2040 | C-4N-H5-TPL-EI-2040: FS | C-4N-H5-TPL-CI-2800, PRECOM-4NH5-TPL-1000, ML1949-E40 | C-4N-H5-TPL-CI-2800: FS, PRECOM-4NH5-TPL-1000: FS, ML1949-E40: FS | 2025-08-25 11:00 | 2025-08-28 11:00
C-4N-H5-TPL-CA-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 | CP Cable Laying | C-4N-H5-TPL-EI-2000 | C-4N-H5-TPL-EI-2000: FS | C-4N-H5-TPL-CA-1010 | C-4N-H5-TPL-CA-1010: FS | 2025-07-19 11:00 | 2025-07-22 11:00
C-4N-H5-TPL-CA-1010 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 | Installation of CP Test Post | C-4N-H5-TPL-CA-1000 | C-4N-H5-TPL-CA-1000: FS | C-4N-H5-TPL-CA-1020 | C-4N-H5-TPL-CA-1020: FS | 2025-07-22 11:00 | 2025-07-24 11:00
C-4N-H5-TPL-CA-1020 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 | Installation of CP JB's | C-4N-H5-TPL-CA-1010 | C-4N-H5-TPL-CA-1010: FS | C-4N-H5-TPL-CA-1030 | C-4N-H5-TPL-CA-1030: FS | 2025-07-24 11:00 | 2025-07-26 11:00
C-4N-H5-TPL-CA-1030 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 | Glanding & Termination for CP S/m | C-4N-H5-TPL-CA-1020 | C-4N-H5-TPL-CA-1020: FS | C-4N-H5-TPL-CI-2800, PRECOM-4NH5-TPL-1000, C-4N-H5-TPL-EL-1000, ML1949-E40 | C-4N-H5-TPL-CI-2800: FS, PRECOM-4NH5-TPL-1000: FS, C-4N-H5-TPL-EL-1000: FS, ML1949-E40: FS | 2025-07-26 11:00 | 2025-07-28 11:00
C-4N-H5-TPL-TE-1410 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.8.1 | FOC Laying | C-4N-H5-TPL-EI-2010, ML1033-B22, HE-TL-0470, HE-TL-0830, HE-TL-0710, HS-CN-0290, HE-TL-0770, HM-TL-0040 | C-4N-H5-TPL-EI-2010: FS, ML1033-B22: FS, HE-TL-0470: FS, HE-TL-0830: FS, HE-TL-0710: FS, HS-CN-0290: FS, HE-TL-0770: FS, HM-TL-0040: FS | C-4N-H5-TPL-TE-1420 | C-4N-H5-TPL-TE-1420: FS | 2025-07-29 11:00 | 2025-08-05 11:00
C-4N-H5-TPL-TE-1420 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.8.1 | FO Cable OTDR Testing & Splicing | C-4N-H5-TPL-TE-1410, C-4N-H5-TPL-EL-1000 | C-4N-H5-TPL-TE-1410: FS, C-4N-H5-TPL-EL-1000: FS | PRECOM-4NH5-TPL-1000, ML1949-E40 | PRECOM-4NH5-TPL-1000: FS, ML1949-E40: FS | 2025-08-05 11:00 | 2025-08-07 11:00
C-MAQTA-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.8.12.2.2 | Instrument Trenching | C-MAQTA-CI-1800 | C-MAQTA-CI-1800: FS | C-MAQTA-EI-2010 | C-MAQTA-EI-2010: FS | 2025-07-26 11:00 | 2025-08-06 11:00
C-MAQTA-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.8.12.2.2 | LV Cable Trenching | C-DBV6-EI-2500, C-MAQTA-EI-1000, HE-IC-0830, HE-EL-1610, HE-EL-0590, HE-IC-1010, HE-EL-0470, CTF-1000, HM-EL-0080, HE-IC-0950, HM-EL-0520, HE-EL-0830, HE-EL-1950, HE-IC-0230, HE-IC-0290, HE-IC-0590, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-025 | C-DBV6-EI-2500: FS, C-MAQTA-EI-1000: FF, HE-IC-0830: FS, HE-EL-1610: FS, HE-EL-0590: FS, HE-IC-1010: FS, HE-EL-0470: FS, CTF-1000: FS, HM-EL-0080: FS, HE-IC-0950: FS, HM-EL-0520: FS, HE-EL-0830: FS, HE-EL-1950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-059 | C-MAQTA-CI-1810, C-MAQTA-EI-2000, C-541CR-CI-1000 | C-MAQTA-CI-1810: FS, C-MAQTA-EI-2000: FS, C-541CR-CI-1000: SS | 2025-07-15 11:00 | 2025-07-26 11:00
C-MAQTA-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.8.12.2.2 | Back Filling for Instrument Cable | C-MAQTA-EI-2010 | C-MAQTA-EI-2010: FS 5 | PRE-COM1330 | PRE-COM1330: FS | 2025-08-19 11:00 | 2025-08-26 11:00
C-MAQTA-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.8.12.2.2 | Back Filling for LV Cable | C-MAQTA-EI-2000 | C-MAQTA-EI-2000: FS 5 | PRE-COM1330 | PRE-COM1330: FS | 2025-08-08 11:00 | 2025-08-15 11:00
C-MAQTA-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.8.12.2.2 | LV Cable Laying | HE-EL-1550, C-MAQTA-CI-1800 | HE-EL-1550: FS, C-MAQTA-CI-1800: FS | C-MAQTA-EI-2050, C-MAQTA-CI-2800 | C-MAQTA-EI-2050: FS, C-MAQTA-CI-2800: FS 5 | 2025-07-26 11:00 | 2025-08-02 11:00
C-MAQTA-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.8.12.2.2 | Instrument Cable Laying | C-MAQTA-CI-1810 | C-MAQTA-CI-1810: FS | C-MAQTA-EI-2050, C-MAQTA-CI-2810 | C-MAQTA-EI-2050: FS, C-MAQTA-CI-2810: FS 5 | 2025-08-06 11:00 | 2025-08-13 11:00
C-MAQTA-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.8.12.2.2 | Glanding & Termination | C-MAQTA-EI-2010, C-MAQTA-EI-2000 | C-MAQTA-EI-2010: FS, C-MAQTA-EI-2000: FS | C-MAQTA-TE-1020, PRE-COM1330, C-MAQTA-EL-2000 | C-MAQTA-TE-1020: FS, PRE-COM1330: FS, C-MAQTA-EL-2000: FS | 2025-08-13 11:00 | 2025-08-16 11:00
C-MAQTA-TE-1000 | Not Started | P2543-R01-Oct24..4.3.1.8.12.3.1 | SCADA S/m Modification | C-MAQTA-TE-1020, C-MAQTA-TE-1010, HS-GN-0470, HS-GN-0290, HS-GN-0350, ML1033-B22, CTF-1000, HE-IC-0110, HS-GN-0410, HM-TL-0040, HS-CN-0290, CTF-1010 | C-MAQTA-TE-1020: FF 2, C-MAQTA-TE-1010: SS, HS-GN-0470: FS, HS-GN-0290: FS, HS-GN-0350: FS, ML1033-B22: FS, CTF-1000: FS, HE-IC-0110: FS, HS-GN-0410: FS, HM-TL-0040: FS, HS-CN-0290: FS, CTF-1010: FS | PRE-COM1330, C-MAQTA-EL-2000 | PRE-COM1330: FS, C-MAQTA-EL-2000: FS | 2025-08-14 11:00 | 2025-08-26 11:00
C-MAQTA-TE-1010 | Not Started | P2543-R01-Oct24..4.3.1.8.12.3.1 | Telecom S/m Modification | C-MAQTA-TE-1020, HS-GN-0470, HS-GN-0290, HS-GN-0350, ML1033-B22, CTF-1000, HE-IC-0110, HS-GN-0410, HM-TL-0040, HS-CN-0290, CTF-1010 | C-MAQTA-TE-1020: FF 2, HS-GN-0470: FS, HS-GN-0290: FS, HS-GN-0350: FS, ML1033-B22: FS, CTF-1000: FS, HE-IC-0110: FS, HS-GN-0410: FS, HM-TL-0040: FS, HS-CN-0290: FS, CTF-1010: FS | C-MAQTA-TE-1000, C-MAQTA-EL-2000 | C-MAQTA-TE-1000: SS, C-MAQTA-EL-2000: FS | 2025-08-14 11:00 | 2025-08-26 11:00
C-MAQTA-TE-1020 | Not Started | P2543-R01-Oct24..4.3.1.8.12.3.1 | Installation PIDS S/m | C-MAQTA-EI-2050 | C-MAQTA-EI-2050: FS | C-MAQTA-TE-1000, C-MAQTA-TE-1010, PRE-COM1330, C-MAQTA-EL-2000 | C-MAQTA-TE-1000: FF 2, C-MAQTA-TE-1010: FF 2, PRE-COM1330: FS, C-MAQTA-EL-2000: FS | 2025-08-16 11:00 | 2025-08-23 11:00
C-541CR-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.9.12.2.1 | Instrument Trenching | C-541CR-CI-1000 | C-541CR-CI-1000: FS | C-541CR-EI-1010, C-577-CI-1000 | C-541CR-EI-1010: FS, C-577-CI-1000: FS 5 | 2025-07-24 11:00 | 2025-08-02 11:00
C-541CR-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.9.12.2.1 | LV Cable Trenching | C-MAQTA-CI-1800 | C-MAQTA-CI-1800: SS | C-541CR-EI-1000, C-541CR-CI-1010 | C-541CR-EI-1000: FS, C-541CR-CI-1010: FS | 2025-07-15 11:00 | 2025-07-24 11:00
C-541CR-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.9.12.2.1 | Back Filling for Instrument Cable | C-541CR-EI-1010 | C-541CR-EI-1010: FS 5 | PRE-COM1330 | PRE-COM1330: FS | 2025-08-14 11:00 | 2025-08-18 11:00
C-541CR-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.9.12.2.1 | Back Filling for LV Cable | C-541CR-EI-1000 | C-541CR-EI-1000: FS 5 | PRE-COM1330 | PRE-COM1330: FS | 2025-08-05 11:00 | 2025-08-08 11:00
C-541CR-EI-1000 | Not Started | P2543-R01-Oct24..4.3.1.9.12.2.1 | LV Cable Laying | HE-EL-1550, C-541CR-CI-1000 | HE-EL-1550: FS, C-541CR-CI-1000: FS | C-541CR-EI-1020, C-541CR-CI-1020 | C-541CR-EI-1020: FS, C-541CR-CI-1020: FS 5 | 2025-07-24 11:00 | 2025-07-30 11:00
C-541CR-EI-1010 | Not Started | P2543-R01-Oct24..4.3.1.9.12.2.1 | Instrument Cable Laying | C-541CR-CI-1010 | C-541CR-CI-1010: FS | C-541CR-EI-1020, C-541CR-CI-1030 | C-541CR-EI-1020: FS, C-541CR-CI-1030: FS 5 | 2025-08-02 11:00 | 2025-08-08 11:00
C-541CR-TE-1000 | Not Started | P2543-R01-Oct24..4.3.1.9.12.3.1 | Telecommunication Works (Modification of Existing Telecom Cabinet) | C-541CR-EI-1040, HS-GN-0410, HS-GN-0470, HS-GN-0290, CTF-1000, HS-GN-0350, CTF-1010 | C-541CR-EI-1040: FS, HS-GN-0410: FS, HS-GN-0470: FS, HS-GN-0290: FS, CTF-1000: FS, HS-GN-0350: FS, CTF-1010: FS | PRE-COM1330, CCM-PM4520, CCM-PM4530, CCM-PM4540 | PRE-COM1330: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-08-21 11:00 | 2025-08-27 11:00
C-541CR-EI-1020 | Not Started | P2543-R01-Oct24..4.3.1.9.12.2.1 | Installation of RTU | C-541CR-EI-1000, C-541CR-EI-1010, HM-ME-0790, HS-GN-0350, HS-GN-0290, ML1499-D18, HS-GN-0410, HS-GN-0470, HM-ME-1590, CTF-1000, HM-ME-2330, CTF-1010 | C-541CR-EI-1000: FS, C-541CR-EI-1010: FS, HM-ME-0790: FS, HS-GN-0350: FS, HS-GN-0290: FS, ML1499-D18: FS, HS-GN-0410: FS, HS-GN-0470: FS, HM-ME-1590: FF, CTF-1000: FS, HM-ME-2330: FF, CTF-1010: FS | C-541CR-EI-1030 | C-541CR-EI-1030: FS | 2025-08-08 11:00 | 2025-08-12 11:00
C-541CR-EI-1030 | Not Started | P2543-R01-Oct24..4.3.1.9.12.2.1 | Electrical & Instrumentation Works (UPS Feeder Installation) | C-541CR-EI-1020 | C-541CR-EI-1020: FS | C-541CR-EI-1040 | C-541CR-EI-1040: FS | 2025-08-12 11:00 | 2025-08-18 11:00
C-541CR-EI-1040 | Not Started | P2543-R01-Oct24..4.3.1.9.12.2.1 | Glanding & Termination | C-541CR-EI-1030 | C-541CR-EI-1030: FS | C-541CR-TE-1000, PRE-COM1330, CCM-PM4520, CCM-PM4530, CCM-PM4540 | C-541CR-TE-1000: FS, PRE-COM1330: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-08-18 11:00 | 2025-08-21 11:00
C-52-0102-PL-ME-3200 | In Progress | P2543-R01-Oct24..4.3.1.3.8.21.1.12 | Cold Bends | C-52-0102-PL-ME-2800, C-52-0102-PL-ME-4800 | C-52-0102-PL-ME-2800: FF, C-52-0102-PL-ME-4800: FF 1 | C-52-0102-PL-ME-4810 | C-52-0102-PL-ME-4810: FF 2 | 2024-09-12 12:00 | 2024-12-13 17:00
C-52-0102-PL-CI-7200 | Not Started | P2543-R01-Oct24..4.3.2.3.6.8.1.1 | Evaporation Pond | C-52-0102-PL-CI-6810 | C-52-0102-PL-CI-6810: FF | C-52-0102-PL-ME-7420, PRECOM-52-0201-1000, C-52-0102-PL-ME-7400, ML1080 | C-52-0102-PL-ME-7420: FF, PRECOM-52-0201-1000: FS, C-52-0102-PL-ME-7400: FS, ML1080: FS | 2024-12-26 07:00 | 2025-01-30 17:00
C-52-HG01-PL-ME-3200 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.13 | Cold Bends-Lot1 | C-52-HG01-PL-ME-2800 | C-52-HG01-PL-ME-2800: FS | C-52-HG01-PL-ME-4810, C-52-HG01-PL-ME-3400 | C-52-HG01-PL-ME-4810: FF, C-52-HG01-PL-ME-3400: FS | 2024-07-18 | 2024-08-23 15:48
C-52-0203-PL-ME-3200 | In Progress | P2543-R01-Oct24..4.3.1.3.15.21.1.9 | Cold Bends | C-52-0203-PL-ME-4800 | C-52-0203-PL-ME-4800: FF | C-52-0203-PL-ME-4810 | C-52-0203-PL-ME-4810: FF | 2024-09-27 | 2025-01-07 17:00
C-52-0304-PL-ME-3200 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.1.11 | Cold Bends | C-52-0304-PL-ME-4800, C-52-0304-PL-ME-4800 | C-52-0304-PL-ME-4800: SS, C-52-0304-PL-ME-4800: FF | C-52-0304-PL-ME-4810 | C-52-0304-PL-ME-4810: FF | 2025-01-03 07:00 | 2025-02-04 17:00
C-52-0405-PL-ME-3200 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.11 | Cold Bends | C-52-0405-PL-ME-4800, C-52-0405-PL-ME-4800 | C-52-0405-PL-ME-4800: SS, C-52-0405-PL-ME-4800: FF | C-52-0405-PL-ME-4810 | C-52-0405-PL-ME-4810: FF | 2025-02-07 12:00 | 2025-03-18 08:00
C-52-0506-PL-ME-3200 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.12 | Cold Bends | C-52-0506-PL-ME-4800, C-52-0506-PL-ME-4800 | C-52-0506-PL-ME-4800: SS 7, C-52-0506-PL-ME-4800: FF | C-52-0506-PL-ME-4810 | C-52-0506-PL-ME-4810: FF | 2025-05-10 15:00 | 2025-07-02 15:00
C-52-06CR-PL-ME-3200 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.16 | Cold Bends | C-52-06CR-PL-ME-4800 | C-52-06CR-PL-ME-4800: FF 1 | C-52-06CR-PL-ME-4810 | C-52-06CR-PL-ME-4810: FF | 2025-06-24 15:00 | 2025-07-30 15:00
C-56-01HG-PL-ME-3200 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.17 | Cold Bends | C-56-01HG-PL-ME-4800, C-56-01HG-PL-ME-4800 | C-56-01HG-PL-ME-4800: SS, C-56-01HG-PL-ME-4800: FF | C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-3400, C-56-01HG-PL-ME-5010 | C-56-01HG-PL-ME-4810: FF, C-56-01HG-PL-ME-3400: FS, C-56-01HG-PL-ME-5010: FF | 2025-02-11 08:30 | 2025-04-14 14:30
C-56-HC01-PL-ME-3200 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.12 | Cold Bends | C-56-HC01-PL-ME-4800, C-56-HC01-PL-ME-4800, C-56-HC01-PL-ME-5000 | C-56-HC01-PL-ME-4800: SS, C-56-HC01-PL-ME-4800: FF, C-56-HC01-PL-ME-5000: FF | C-56-HC01-PL-ME-5010 | C-56-HC01-PL-ME-5010: FF | 2025-05-03 14:30 | 2025-06-13 12:30
C-52-HG01-PL-CI-7200 | Not Started | P2543-R01-Oct24..4.3.2.3.10.8.2.1 | Evaporation Pond | ML1002, C-52-HG01-PL-CI-6810 | ML1002: FS, C-52-HG01-PL-CI-6810: FF 3 | C-52-HG01-PL-ME-7420, PRECOM-52-HG01-1000, C-52-HG01-PL-ME-7400, ML1080 | C-52-HG01-PL-ME-7420: FF, PRECOM-52-HG01-1000: FS, C-52-HG01-PL-ME-7400: FF, ML1080: FS | 2024-11-12 07:00 | 2024-12-18 17:00
C-52-0203-PL-CI-7200 | Not Started | P2543-R01-Oct24..4.3.2.3.5.8.2.1 | Evaporation Pond | C-52-0203-PL-CI-6810 | C-52-0203-PL-CI-6810: FF | C-52-0203-PL-ME-7420, PRECOM-52-0203-1000, C-52-0203-PL-ME-7400 | C-52-0203-PL-ME-7420: FF, PRECOM-52-0203-1000: FS, C-52-0203-PL-ME-7400: FS | 2025-01-06 07:00 | 2025-02-08 17:00
C-52-0304-PL-CI-7200 | Not Started | P2543-R01-Oct24..4.3.2.3.4.8.3.1 | Evaporation Pond | C-52-0304-PL-CI-6810 | C-52-0304-PL-CI-6810: FS | C-52-0304-PL-ME-7420, PRECOM-52-0304-1000, C-52-0304-PL-ME-7400 | C-52-0304-PL-ME-7420: FF, PRECOM-52-0304-1000: FS, C-52-0304-PL-ME-7400: FS | 2025-03-09 11:00 | 2025-04-22 13:00
C-52-0405-PL-CI-7200 | Not Started | P2543-R01-Oct24..4.3.2.3.3.8.3.1 | Evaporation Pond | C-52-0405-PL-CI-6810 | C-52-0405-PL-CI-6810: FF | C-52-0405-PL-ME-7420, PRECOM-52-0405-1000, C-52-0405-PL-ME-7400 | C-52-0405-PL-ME-7420: FF, PRECOM-52-0405-1000: FS, C-52-0405-PL-ME-7400: FF | 2025-07-23 11:00 | 2025-08-27 11:00
C-52-0506-PL-CI-7200 | Not Started | P2543-R01-Oct24..4.3.2.3.2.8.3.1 | Evaporation Pond | C-52-0506-PL-ME-4810, C-52-0506-PL-CI-6810 | C-52-0506-PL-ME-4810: SS, C-52-0506-PL-CI-6810: FF 6 | C-52-0506-PL-ME-7420, PRECOM-52-0506-1000, C-52-0506-PL-ME-7400 | C-52-0506-PL-ME-7420: FF, PRECOM-52-0506-1000: FS, C-52-0506-PL-ME-7400: FS | 2025-06-16 15:00 | 2025-08-08 15:00
C-52-06CR-PL-CI-7200 | Not Started | P2543-R01-Oct24..4.3.2.3.1.8.2.1 | Evaporation Pond | C-52-06CR-PL-ME-4810, ML1002, C-52-06CR-PL-CI-6810 | C-52-06CR-PL-ME-4810: SS, ML1002: FS, C-52-06CR-PL-CI-6810: FF | C-52-06CR-PL-ME-7420, PRECOM-52-06CR-1000, C-52-06CR-PL-ME-7400 | C-52-06CR-PL-ME-7420: FF, PRECOM-52-06CR-1000: FS, C-52-06CR-PL-ME-7400: FS | 2025-07-23 11:30 | 2025-09-15 11:30
C-56-01HG-PL-CI-7200 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.1 | Evaporation Pond | C-56-01HG-PL-ME-4810, C-56-01HG-PL-ME-5010, C-56-01HG-PL-CI-7010 | C-56-01HG-PL-ME-4810: FF, C-56-01HG-PL-ME-5010: FF, C-56-01HG-PL-CI-7010: FF | C-56-01HG-PL-ME-7420, PRECOM-56-HGHC-1000, C-56-01HG-PL-ME-7400 | C-56-01HG-PL-ME-7420: FS, PRECOM-56-HGHC-1000: FS, C-56-01HG-PL-ME-7400: FF | 2025-06-13 15:00 | 2025-07-19 15:00
C-56-HC01-PL-CI-7200 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1.5 | Evaporation Pond | C-56-HC01-PL-ME-4810, C-56-HC01-PL-ME-5010, ML1002, C-56-HC01-PL-CI-7010 | C-56-HC01-PL-ME-4810: FS, C-56-HC01-PL-ME-5010: FF 7, ML1002: FS, C-56-HC01-PL-CI-7010: FF 7 | C-56-HC01-PL-ME-7420, PRECOM-56-HGHC-1000, C-56-HC01-PL-ME-7400 | C-56-HC01-PL-ME-7420: FF, PRECOM-56-HGHC-1000: FS, C-56-HC01-PL-ME-7400: FF | 2025-06-30 07:00 | 2025-08-02 17:00
C-56-PL-607-EI-1600 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.6.1 | Installation RTU | C-56-PL-607-EI-2210, C-56-PL-607-EI-2010 | C-56-PL-607-EI-2210: FS, C-56-PL-607-EI-2010: FS | C-56-PL-607-EI-1810, C-56-PL-607-TE-1400 | C-56-PL-607-EI-1810: FS, C-56-PL-607-TE-1400: FS | 2025-08-04 11:00 | 2025-08-09 11:00
C-56-PL-607-TE-1410 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.8.2 | Installation of Out Door FOC Splicing Box | C-56-PL-607-EI-2010, C-56-PL-607-CI-1800, C-56-PL-607-CI-1810 | C-56-PL-607-EI-2010: FS, C-56-PL-607-CI-1800: FS, C-56-PL-607-CI-1810: FS | C-56-PL-607-TE-1200 | C-56-PL-607-TE-1200: FS | 2025-08-04 11:00 | 2025-08-07 11:00
C-56-PL-607-TE-1200 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.8.1 | Installation of PIDS/ PLDS System | C-56-PL-607-TE-1410, HE-TL-0710, HE-TL-0770, HM-ME-1290, HE-TL-0290, HE-TL-0830, HE-TL-0470, HE-TL-0410, HE-TL-0350, HM-TL-0040, HM-EL-0180, ML1033-B22, HS-CN-0290, HM-ME-2270, HM-EL-610 | C-56-PL-607-TE-1410: FS, HE-TL-0710: FS, HE-TL-0770: FS, HM-ME-1290: FS, HE-TL-0290: FS, HE-TL-0830: FS, HE-TL-0470: FS, HE-TL-0410: FS, HE-TL-0350: FS, HM-TL-0040: FS, HM-EL-0180: FS, ML1033-B22: FS, HS-CN-0290: FS, HM-ME-2270: FS 34, HM-EL-610: FS | C-56-PL-607-TE-1600 | C-56-PL-607-TE-1600: FS | 2025-08-07 11:00 | 2025-08-16 11:00
C-56-PL-607-TE-1600 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.8.3 | Installation of CCTV System | C-56-PL-607-TE-1200, HE-TL-0290, HE-TL-0350, HE-TL-0410, HE-TL-0470, HE-TL-0710, HE-TL-0770, HE-TL-0830, HM-EL-0180, HM-EL-610, HM-ME-1290, HM-ME-2270, HM-TL-0040, HS-CN-0290, ML1033-B22 | C-56-PL-607-TE-1200: FS, HE-TL-0290: FS, HE-TL-0350: FS, HE-TL-0410: FS, HE-TL-0470: FS, HE-TL-0710: FS, HE-TL-0770: FS, HE-TL-0830: FS, HM-EL-0180: FS, HM-EL-610: FS, HM-ME-1290: FS, HM-ME-2270: FS, HM-TL-0040: FS, HS-CN-0290: FS, ML1033-B22: FS | C-56-PL-607-TE-1420 | C-56-PL-607-TE-1420: FS | 2025-08-16 11:00 | 2025-08-26 11:00
C-56-EB2-EL-1600 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.5.1 | Termination & Connection with Existing Power Distribution Network | C-56-EB2-TE-1610, C-56-EB2-EI-1230, C-COM-890 | C-56-EB2-TE-1610: FS, C-56-EB2-EI-1230: FS, C-COM-890: FS | PRECOM-56-EB2-1000, CCM-PM4510 | PRECOM-56-EB2-1000: FS, CCM-PM4510: FS | 2025-09-01 11:00 | 2025-09-04 11:00
C-56-G-HT-CI-0100 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.40.1 | Demolition of Existing Paving | C-56-EB2-CI-1000, ML1199-B24, HE-PI-3520, HE-PI-1240 | C-56-EB2-CI-1000: SS 5, ML1199-B24: FS, HE-PI-3520: FS, HE-PI-1240: SS 60 | C-56-G-HT-CI-1000 | C-56-G-HT-CI-1000: FS | 2025-01-22 07:00 | 2025-01-29 17:00
C-52-PR-839-TE-1420 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 | FO Cable OTDR Testing & Splicing | C-52-PR-839-TE-1600 | C-52-PR-839-TE-1600: FS | PRECOM-52-PR-1000 | PRECOM-52-PR-1000: FS | 2025-07-19 07:00 | 2025-07-24 17:00
C-52-OHPL-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.4.4.22.1.2 | Trenching for Cables | C-52-OHPL-CI-1000 | C-52-OHPL-CI-1000: FS 10 | C-52-OHPL-EL-1000 | C-52-OHPL-EL-1000: FS 30 | 2025-04-10 13:00 | 2025-05-01 13:00
C-52-OHPL-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.4.4.22.1.3 | Backfilling for Cables | C-52-OHPL-EL-2000 | C-52-OHPL-EL-2000: FS | PRECOM-52-EB1-1000, CCM-PM4520, CCM-PM4530, CCM-PM4540 | PRECOM-52-EB1-1000: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-09-23 11:00 | 2025-10-14 11:00
C-52-IDS2-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 | Site Survey, Preparation & Grading Works | C-52-IDS1-CI-1000, HE-SS-0030, ML1002, HE-CS-0170, CTF-1000, ML1034-B25, HE-CS-0470, CTF-1010 | C-52-IDS1-CI-1000: FS, HE-SS-0030: SS, ML1002: FS, HE-CS-0170: FS, CTF-1000: FS, ML1034-B25: FS, HE-CS-0470: FS, CTF-1010: FS | C-52-IDS2-CI-1010, C-52-IDS3-CI-1000 | C-52-IDS2-CI-1010: FS, C-52-IDS3-CI-1000: FS | 2025-05-10 11:00 | 2025-05-22 11:00
C-52-IDS2-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 | Earth Works for Solar S/m Foundation | C-52-IDS2-CI-1000 | C-52-IDS2-CI-1000: FS | C-52-IDS2-CI-1020, C-52-IDS2-CI-1200 | C-52-IDS2-CI-1020: FS, C-52-IDS2-CI-1200: FS | 2025-05-22 11:00 | 2025-06-07 11:00
C-52-IDS2-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 | Earth Works for Field Instruments & JBs | C-52-IDS2-CI-1010 | C-52-IDS2-CI-1010: FS | C-52-IDS2-CI-1030, C-52-IDS2-CI-1210 | C-52-IDS2-CI-1030: FS, C-52-IDS2-CI-1210: FS | 2025-06-07 11:00 | 2025-06-17 11:00
C-52-IDS2-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 | Earth Works for CCTV Pole, Fence & Gates Foundation | C-52-IDS2-CI-1020 | C-52-IDS2-CI-1020: FS | C-52-IDS2-CI-1220, C-52-IDS2-CI-1800 | C-52-IDS2-CI-1220: FS, C-52-IDS2-CI-1800: FS | 2025-06-17 11:00 | 2025-07-04 11:00
C-52-IDS2-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.2 | Compaction & Testing for Solar S/m Foundation | C-52-IDS2-CI-1010 | C-52-IDS2-CI-1010: FS | C-52-IDS2-CI-1400 | C-52-IDS2-CI-1400: FS | 2025-06-07 11:00 | 2025-06-17 11:00
C-52-IDS2-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.2 | Compaction & Testing for Field Instruments & JBs | C-52-IDS2-CI-1020 | C-52-IDS2-CI-1020: FS | C-52-IDS2-CI-1410 | C-52-IDS2-CI-1410: FS | 2025-06-17 11:00 | 2025-06-23 11:00
C-52-IDS2-CI-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.2 | Compaction & Testing for CCTV Pole, Fence & Gates Foundation | C-52-IDS2-CI-1030 | C-52-IDS2-CI-1030: FS | C-52-IDS2-CI-1420 | C-52-IDS2-CI-1420: FS | 2025-07-04 11:00 | 2025-07-21 11:00
C-52-IDS2-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 | Concrete Works for Solar S/m Foundation | C-52-IDS2-CI-1200, HE-CS-0230, ML1034-B25, HM-CS-0040, HM-CS-0050 | C-52-IDS2-CI-1200: FS, HE-CS-0230: FS, ML1034-B25: FS, HM-CS-0040: FS, HM-CS-0050: FS | C-52-IDS2-CI-1410, C-52-IDS2-EI-1190, C-52-IDS2-CI-1700 | C-52-IDS2-CI-1410: FS, C-52-IDS2-EI-1190: FS, C-52-IDS2-CI-1700: FF 5 | 2025-06-17 11:00 | 2025-07-21 11:00
C-52-IDS2-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 | Concrete Works for Field Instruments & JBs Foundation | C-52-IDS2-CI-1210, C-52-IDS2-CI-1400 | C-52-IDS2-CI-1210: FS, C-52-IDS2-CI-1400: FS | C-52-IDS2-EI-1190, C-52-IDS2-CI-1700 | C-52-IDS2-EI-1190: FS, C-52-IDS2-CI-1700: FF 5 | 2025-07-21 11:00 | 2025-08-06 11:00
C-52-IDS2-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 | Concrete Works for CCTV Pole, Fence & Gates Foundation | C-52-IDS2-CI-1220, HE-CS-0230, ML1034-B25, HM-CS-0040, HM-CS-0050 | C-52-IDS2-CI-1220: FS, HE-CS-0230: FS, ML1034-B25: FS, HM-CS-0040: FS, HM-CS-0050: FS | C-52-IDS2-CI-2220, C-52-IDS2-TE-1590, C-52-IDS2-CI-1700 | C-52-IDS2-CI-2220: SS 21, C-52-IDS2-TE-1590: FS, C-52-IDS2-CI-1700: FF 5 | 2025-07-21 11:00 | 2025-08-22 11:00
C-52-IDS2-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.6 | Electrical & Earthing Cable Trenching | C-52-IDS2-CI-1030, HE-CS-0530 | C-52-IDS2-CI-1030: FS, HE-CS-0530: FS | C-52-IDS2-CI-1810, C-52-IDS2-EI-2000, C-52-IDS3-CI-1800 | C-52-IDS2-CI-1810: FS, C-52-IDS2-EI-2000: FS, C-52-IDS3-CI-1800: FS | 2025-07-04 11:00 | 2025-07-29 11:00
C-52-IDS2-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.6 | Instrument & Telecom Cable Trenching | C-52-IDS2-CI-1800 | C-52-IDS2-CI-1800: FS | C-52-IDS2-EI-2010, C-52-IDS3-CI-1810 | C-52-IDS2-EI-2010: FS, C-52-IDS3-CI-1810: FS | 2025-07-29 11:00 | 2025-08-22 11:00
C-52-IDS2-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.8 | Back Filling for Electrical & Earthing Cable | C-52-IDS2-EI-2000 | C-52-IDS2-EI-2000: FS 5 | PRECOM-52-IDS2-1000 | PRECOM-52-IDS2-1000: FS | 2025-08-28 11:00 | 2025-09-15 11:00
C-52-IDS2-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.8 | Back Filling for Instrument & Telecom Cable | C-52-IDS2-EI-2010, C-52-IDS2-TE-1600, C-52-IDS1-EI-2010, C-52-IDS1-TE-1600 | C-52-IDS2-EI-2010: FS 5, C-52-IDS2-TE-1600: FS, C-52-IDS1-EI-2010: FS, C-52-IDS1-TE-1600: FS | PRECOM-52-IDS2-1000 | PRECOM-52-IDS2-1000: FS | 2025-09-23 11:00 | 2025-10-09 11:00
C-52-IDS2-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.5 | Installation of Fence Post & Mesh Works (Type-3) | C-52-IDS2-CI-1420, C-52-IDS2-CI-1700, HE-CS-0350, HE-CS-0470 | C-52-IDS2-CI-1420: SS 21, C-52-IDS2-CI-1700: FS, HE-CS-0350: FS, HE-CS-0470: FS | C-52-IDS2-CI-2230, C-52-IDS3-CI-2220, PRECOM-52-IDS2-1000 | C-52-IDS2-CI-2230: FS, C-52-IDS3-CI-2220: FS, PRECOM-52-IDS2-1000: FS | 2025-08-28 11:00 | 2025-09-15 11:00
C-52-IDS2-CI-2230 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.5 | Installation of Access Gate | C-52-IDS2-CI-2220 | C-52-IDS2-CI-2220: FS | PRECOM-52-IDS2-1000 | PRECOM-52-IDS2-1000: FS | 2025-09-15 11:00 | 2025-09-22 11:00
C-52-IDS2-TE-1590 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 | Installation of CCTV Poles | C-52-IDS2-CI-1420, HE-TL-0470, HE-TL-0350, HM-TL-0040, HE-TL-0710, HM-ME-1290, HE-TL-0770, HE-TL-0830, HE-TL-0290, HE-TL-0410, HM-ME-2270 | C-52-IDS2-CI-1420: FS, HE-TL-0470: FS, HE-TL-0350: FS, HM-TL-0040: FS, HE-TL-0710: FS, HM-ME-1290: FS, HE-TL-0770: FS, HE-TL-0830: FS, HE-TL-0290: FS, HE-TL-0410: FS, HM-ME-2270: FS | C-52-IDS2-TE-1600, C-52-IDS3-TE-1590, PRECOM-52-IDS2-1000 | C-52-IDS2-TE-1600: FS, C-52-IDS3-TE-1590: FS, PRECOM-52-IDS2-1000: FS | 2025-08-22 11:00 | 2025-08-28 11:00
C-52-IDS2-EI-1190 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 | Installation of Solar S/m Structurals | C-52-IDS2-CI-1400, C-52-IDS2-CI-1410 | C-52-IDS2-CI-1400: FS, C-52-IDS2-CI-1410: FS | C-52-IDS2-CI-2600, C-52-IDS2-EI-1200, C-52-IDS3-EI-1190 | C-52-IDS2-CI-2600: FS, C-52-IDS2-EI-1200: FS, C-52-IDS3-EI-1190: FS | 2025-08-06 11:00 | 2025-08-18 11:00
C-52-IDS2-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.7 | Paving of Interlock tiles & Kerb Stone Embankment | C-52-IDS2-EI-1190, ML1059-B28, HE-CS-0290 | C-52-IDS2-EI-1190: FS, ML1059-B28: FS, HE-CS-0290: FS | PRECOM-52-IDS2-1000 | PRECOM-52-IDS2-1000: FS | 2025-08-18 11:00 | 2025-09-23 11:00
C-52-IDS2-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 | Electrical & Earthing Cable Laying | C-52-IDS2-CI-1800, C-52-IDS1-EI-2000 | C-52-IDS2-CI-1800: FS, C-52-IDS1-EI-2000: FS | C-52-IDS2-CI-2800, C-52-IDS3-EI-2000 | C-52-IDS2-CI-2800: FS 5, C-52-IDS3-EI-2000: FS | 2025-08-08 11:00 | 2025-08-22 11:00
C-52-IDS2-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 | Instrument Cable Laying | C-52-IDS2-CI-1810, C-52-IDS1-EI-2010 | C-52-IDS2-CI-1810: FS, C-52-IDS1-EI-2010: FS | C-52-IDS2-CI-2810, C-52-IDS3-EI-2010, PRECOM-52-IDS2-1000, C-52-IDS3-CI-2810, PRECOM-52-IDS3-1000 | C-52-IDS2-CI-2810: FS 5, C-52-IDS3-EI-2010: FS, PRECOM-52-IDS2-1000: FS, C-52-IDS3-CI-2810: FS, PRECOM-52-IDS3-1000: FS | 2025-09-02 11:00 | 2025-09-17 11:00
C-52-IDS2-EI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-IDS2-EI-1190, C-52-IDS1-EI-1200 | C-52-IDS2-EI-1190: FS, C-52-IDS1-EI-1200: FS | C-52-IDS2-EI-1810, C-52-IDS3-EI-1200 | C-52-IDS2-EI-1810: FS, C-52-IDS3-EI-1200: FS | 2025-08-22 11:00 | 2025-09-09 11:00
C-52-IDS2-EI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 | Installation of Lighting & Instrument JB's | C-52-IDS2-EI-1200 | C-52-IDS2-EI-1200: FS | C-52-IDS2-EI-2050 | C-52-IDS2-EI-2050: FS | 2025-09-09 11:00 | 2025-09-18 11:00
C-52-IDS2-TE-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 | CCTV Installation | C-52-IDS2-TE-1590, C-52-IDS1-TE-1600 | C-52-IDS2-TE-1590: FS, C-52-IDS1-TE-1600: FS | C-52-IDS3-TE-1600, C-52-IDS2-CI-2810, PRECOM-52-IDS2-1000, C-52-IDS3-CI-2810, PRECOM-52-IDS3-1000 | C-52-IDS3-TE-1600: FS, C-52-IDS2-CI-2810: FS, PRECOM-52-IDS2-1000: FS, C-52-IDS3-CI-2810: FS, PRECOM-52-IDS3-1000: FS | 2025-09-03 11:00 | 2025-09-13 11:00
C-52-IDS2-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 | Glanding & Termination | C-52-IDS2-EI-1810 | C-52-IDS2-EI-1810: FS | PRECOM-52-IDS2-1000 | PRECOM-52-IDS2-1000: FS | 2025-09-18 11:00 | 2025-09-24 11:00
C-52-IDS3-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 | Site Survey, Preparation & Grading Works | C-52-IDS2-CI-1000, HE-SS-0030, ML1002, ML1034-B25, HE-CS-0470, CTF-1000, HE-CS-0170, CTF-1010 | C-52-IDS2-CI-1000: FS, HE-SS-0030: SS, ML1002: FS, ML1034-B25: FS, HE-CS-0470: FS, CTF-1000: FS, HE-CS-0170: FS, CTF-1010: FS | C-52-IDS3-CI-1010 | C-52-IDS3-CI-1010: FS | 2025-05-22 11:00 | 2025-06-03 11:00
C-52-IDS3-CI-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 | Earth Works for Solar S/m Foundation | C-52-IDS3-CI-1000 | C-52-IDS3-CI-1000: FS | C-52-IDS3-CI-1020, C-52-IDS3-CI-1200 | C-52-IDS3-CI-1020: FS, C-52-IDS3-CI-1200: FS | 2025-06-03 11:00 | 2025-06-19 11:00
C-52-IDS3-CI-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 | Earth Works for Field Instruments & JBs | C-52-IDS3-CI-1010 | C-52-IDS3-CI-1010: FS | C-52-IDS3-CI-1030, C-52-IDS3-CI-1210 | C-52-IDS3-CI-1030: FS, C-52-IDS3-CI-1210: FS | 2025-06-19 11:00 | 2025-06-30 11:00
C-52-IDS3-CI-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 | Earth Works for CCTV Pole, Fence & Gates Foundation | C-52-IDS3-CI-1020 | C-52-IDS3-CI-1020: FS | C-52-IDS3-CI-1220, C-52-IDS3-CI-1800 | C-52-IDS3-CI-1220: FS, C-52-IDS3-CI-1800: FS | 2025-06-30 11:00 | 2025-07-24 11:00
C-52-IDS3-CI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.2 | Compaction & Testing for Solar S/m Foundation | C-52-IDS3-CI-1010 | C-52-IDS3-CI-1010: FS | C-52-IDS3-CI-1400 | C-52-IDS3-CI-1400: FS | 2025-06-19 11:00 | 2025-06-30 11:00
C-52-IDS3-CI-1210 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.2 | Compaction & Testing for Field Instruments & JBs | C-52-IDS3-CI-1020 | C-52-IDS3-CI-1020: FS | C-52-IDS3-CI-1410 | C-52-IDS3-CI-1410: FS | 2025-06-30 11:00 | 2025-07-05 11:00
C-52-IDS3-CI-1220 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.2 | Compaction & Testing for CCTV Pole, Fence & Gates Foundation | C-52-IDS3-CI-1030 | C-52-IDS3-CI-1030: FS | C-52-IDS3-CI-1420 | C-52-IDS3-CI-1420: FS | 2025-07-24 11:00 | 2025-08-09 11:00
C-52-IDS3-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 | Concrete Works for Solar S/m Foundation | C-52-IDS3-CI-1200, HM-CS-0050, ML1034-B25, HE-CS-0230, HM-CS-0040 | C-52-IDS3-CI-1200: FS, HM-CS-0050: FS, ML1034-B25: FS, HE-CS-0230: FS, HM-CS-0040: FS | C-52-IDS3-CI-1410, C-52-IDS3-EI-1190, C-52-IDS3-CI-1700 | C-52-IDS3-CI-1410: FS, C-52-IDS3-EI-1190: FS, C-52-IDS3-CI-1700: FF 5 | 2025-06-30 11:00 | 2025-08-01 11:00
C-52-IDS3-CI-1410 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 | Concrete Works for Field Instruments & JBs Foundation | C-52-IDS3-CI-1210, C-52-IDS3-CI-1400 | C-52-IDS3-CI-1210: FS, C-52-IDS3-CI-1400: FS | C-52-IDS3-EI-1190, C-52-IDS3-CI-1700 | C-52-IDS3-EI-1190: FS, C-52-IDS3-CI-1700: FF 5 | 2025-08-01 11:00 | 2025-08-18 11:00
C-52-IDS3-CI-1420 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 | Concrete Works for CCTV Pole, Fence & Gates Foundation | C-52-IDS3-CI-1220, HM-CS-0050, ML1034-B25, HE-CS-0230, HM-CS-0040 | C-52-IDS3-CI-1220: FS, HM-CS-0050: FS, ML1034-B25: FS, HE-CS-0230: FS, HM-CS-0040: FS | C-52-IDS3-CI-2220, C-52-IDS3-TE-1590, C-52-IDS3-CI-1700 | C-52-IDS3-CI-2220: SS 21, C-52-IDS3-TE-1590: FS, C-52-IDS3-CI-1700: FF 5 | 2025-08-09 11:00 | 2025-09-12 11:00
C-52-IDS3-CI-1800 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.6 | Electrical & Earthing Cable Trenching | C-52-IDS3-CI-1030, C-52-IDS2-CI-1800, HE-CS-0530 | C-52-IDS3-CI-1030: FS, C-52-IDS2-CI-1800: FS, HE-CS-0530: FS | C-52-IDS3-CI-1810, C-52-IDS3-EI-2000 | C-52-IDS3-CI-1810: FS, C-52-IDS3-EI-2000: FS | 2025-07-29 11:00 | 2025-08-22 11:00
C-52-IDS3-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.6 | Instrument & Telecom Cable Trenching | C-52-IDS3-CI-1800, C-52-IDS2-CI-1810 | C-52-IDS3-CI-1800: FS, C-52-IDS2-CI-1810: FS | C-52-IDS3-EI-2010 | C-52-IDS3-EI-2010: FS | 2025-08-22 11:00 | 2025-09-17 11:00
C-52-IDS3-CI-2800 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.8 | Back Filling for Electrical & Earthing Cable | C-52-IDS3-EI-2000 | C-52-IDS3-EI-2000: FS 5 | PRECOM-52-IDS3-1000 | PRECOM-52-IDS3-1000: FS | 2025-09-12 11:00 | 2025-09-29 11:00
C-52-IDS3-CI-2810 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.8 | Back Filling for Instrument & Telecom Cable | C-52-IDS3-EI-2010, C-52-IDS3-TE-1600, C-52-IDS2-EI-2010, C-52-IDS2-TE-1600, C-52-IDS1-EI-2010, C-52-IDS1-TE-1600 | C-52-IDS3-EI-2010: FS, C-52-IDS3-TE-1600: FS, C-52-IDS2-EI-2010: FS, C-52-IDS2-TE-1600: FS, C-52-IDS1-EI-2010: FS, C-52-IDS1-TE-1600: FS | PRECOM-52-IDS3-1000 | PRECOM-52-IDS3-1000: FS | 2025-10-01 11:00 | 2025-10-17 11:00
C-52-IDS3-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.5 | Installation of Fence Post & Mesh Works (Type-3) | C-52-IDS3-CI-1420, C-52-IDS2-CI-2220, C-52-IDS3-CI-1700, HE-CS-0350, HE-CS-0470 | C-52-IDS3-CI-1420: SS 21, C-52-IDS2-CI-2220: FS, C-52-IDS3-CI-1700: FS, HE-CS-0350: FS, HE-CS-0470: FS | C-52-IDS3-CI-2230, PRECOM-52-IDS3-1000 | C-52-IDS3-CI-2230: FS, PRECOM-52-IDS3-1000: FS | 2025-09-18 11:00 | 2025-10-04 11:00
C-52-IDS3-CI-2230 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.5 | Installation of Access Gate | C-52-IDS3-CI-2220 | C-52-IDS3-CI-2220: FS | PRECOM-52-IDS3-1000 | PRECOM-52-IDS3-1000: FS | 2025-10-04 11:00 | 2025-10-11 11:00
C-52-IDS3-TE-1590 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 | Installation of CCTV Poles | C-52-IDS3-CI-1420, C-52-IDS2-TE-1590, HE-TL-0290, HE-TL-0770, HM-TL-0040, HE-TL-0710, HE-TL-0350, HM-ME-1290, HE-TL-0830, HE-TL-0470, HE-TL-0410, HM-ME-2270 | C-52-IDS3-CI-1420: FS, C-52-IDS2-TE-1590: FS, HE-TL-0290: FS, HE-TL-0770: FS, HM-TL-0040: FS, HE-TL-0710: FS, HE-TL-0350: FS, HM-ME-1290: FS, HE-TL-0830: FS, HE-TL-0470: FS, HE-TL-0410: FS, HM-ME-2270: FS | C-52-IDS3-TE-1600 | C-52-IDS3-TE-1600: FS | 2025-09-12 11:00 | 2025-09-18 11:00
C-52-IDS3-EI-1190 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 | Installation of Solar S/m Structurals | C-52-IDS3-CI-1400, C-52-IDS2-EI-1190, C-52-IDS3-CI-1410 | C-52-IDS3-CI-1400: FS, C-52-IDS2-EI-1190: FS, C-52-IDS3-CI-1410: FS | C-52-IDS3-CI-2600, C-52-IDS3-EI-1200 | C-52-IDS3-CI-2600: FS, C-52-IDS3-EI-1200: FS | 2025-08-18 11:00 | 2025-08-29 11:00
C-52-IDS3-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.7 | Paving of Interlock tiles & Kerb Stone Embankment | C-52-IDS3-EI-1190, HE-CS-0290, ML1059-B28 | C-52-IDS3-EI-1190: FS, HE-CS-0290: FS, ML1059-B28: FS | PRECOM-52-IDS3-1000 | PRECOM-52-IDS3-1000: FS | 2025-08-29 11:00 | 2025-10-04 11:00
C-52-IDS3-EI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 | Electrical & Earthing Cable Laying | C-52-IDS3-CI-1800, C-52-IDS2-EI-2000 | C-52-IDS3-CI-1800: FS, C-52-IDS2-EI-2000: FS | C-52-IDS3-CI-2800 | C-52-IDS3-CI-2800: FS 5 | 2025-08-22 11:00 | 2025-09-06 11:00
C-52-IDS3-EI-2010 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 | Instrument Cable Laying | C-52-IDS3-CI-1810, C-52-IDS2-EI-2010 | C-52-IDS3-CI-1810: FS, C-52-IDS2-EI-2010: FS | C-52-IDS3-CI-2810, PRECOM-52-IDS3-1000 | C-52-IDS3-CI-2810: FS, PRECOM-52-IDS3-1000: FS | 2025-09-17 11:00 | 2025-10-01 11:00
C-52-IDS3-EI-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-IDS3-EI-1190, C-52-IDS2-EI-1200 | C-52-IDS3-EI-1190: FS, C-52-IDS2-EI-1200: FS | C-52-IDS3-EI-1810 | C-52-IDS3-EI-1810: FS | 2025-09-09 11:00 | 2025-09-25 11:00
C-52-IDS3-EI-1810 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 | Installation of Lighting & Instrument JB's | C-52-IDS3-EI-1200 | C-52-IDS3-EI-1200: FS | C-52-IDS3-EI-2050 | C-52-IDS3-EI-2050: FS | 2025-09-25 11:00 | 2025-10-04 11:00
C-52-IDS3-TE-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 | CCTV Installation | C-52-IDS3-TE-1590, C-52-IDS2-TE-1600 | C-52-IDS3-TE-1590: FS, C-52-IDS2-TE-1600: FS | C-52-IDS3-CI-2810, PRECOM-52-IDS3-1000 | C-52-IDS3-CI-2810: FS, PRECOM-52-IDS3-1000: FS | 2025-09-18 11:00 | 2025-09-27 11:00
C-52-IDS3-EI-2050 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 | Glanding & Termination | C-52-IDS3-EI-1810 | C-52-IDS3-EI-1810: FS | PRECOM-52-IDS3-1000 | PRECOM-52-IDS3-1000: FS | 2025-10-04 11:00 | 2025-10-10 11:00
C-4W-081-03-CI-0100 | Not Started | P2543-R01-Oct24..4.3.1.6.1.12.1.1 | Demolition Works (Paving) | CPL-4-CRMN-3630, HE-CS-0470, CTF-1000, CTF-1010 | CPL-4-CRMN-3630: FS, HE-CS-0470: FS, CTF-1000: FS, CTF-1010: FS | C-4W-081-03-CI-1400, C-4W-TI-CI-1000 | C-4W-081-03-CI-1400: FS, C-4W-TI-CI-1000: FS | 2025-03-13 07:00 | 2025-04-05 13:00
C-4W-081-03-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.6.1.12.1.2 | Concrete Works (Foundations for Equipment & Pipe Supports) | C-4W-081-03-CI-0100, HM-CS-0040, HE-CS-1190, HE-CS-0230 | C-4W-081-03-CI-0100: FS, HM-CS-0040: FS, HE-CS-1190: FS, HE-CS-0230: FS | C-4W-081-03-CI-1700, C-4W-TI-CI-1400 | C-4W-081-03-CI-1700: FS, C-4W-TI-CI-1400: FS | 2025-04-05 13:00 | 2025-04-22 13:00
C-4W-081-03-CI-1700 | Not Started | P2543-R01-Oct24..4.3.1.6.1.12.1.3 | Concrete Protection | C-4W-081-03-CI-1400 | C-4W-081-03-CI-1400: FS | C-4W-081-03-CI-2600, C-4W-081-03-PI-1000, C-4W-TI-CI-1700 | C-4W-081-03-CI-2600: FS, C-4W-081-03-PI-1000: FS, C-4W-TI-CI-1700: FS | 2025-04-22 13:00 | 2025-05-31 11:00
C-4W-081-03-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.6.1.12.1.4 | Paving Works | C-4W-081-03-CI-1700, HE-CS-0290, ML1059-B28 | C-4W-081-03-CI-1700: FS, HE-CS-0290: FS, ML1059-B28: FS | C-4W-TI-CI-2220, PRECOM-4W-08103-1000 | C-4W-TI-CI-2220: FS, PRECOM-4W-08103-1000: FS | 2025-05-31 11:00 | 2025-06-16 11:00
C-4W-081-03-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.6.1.12.2.1 | Piping Works (RTP) | C-4W-081-03-CI-1700, ML1002, ML1219-B19, ML1889-E34, ML1869-E32, HS-CN-0190, HE-PI-1240, HM-PL-0220, HM-PL-0640, HM-PL-0630, HE-PI-1300, HM-PI-0040, ML1879-E33, HM-PL-0740, HM-PL-1510, HM-PL-1570 | C-4W-081-03-CI-1700: FS, ML1002: FS, ML1219-B19: FS, ML1889-E34: FS, ML1869-E32: FS, HS-CN-0190: FS, HE-PI-1240: FS, HM-PL-0220: FF 6, HM-PL-0640: FS, HM-PL-0630: FS, HE-PI-1300: FS, HM-PI-0040: FS, ML1879-E33: FS, HM-PL-0740: FS, HM-PL-1510: FS, HM-PL-157 | C-4W-081-03-PI-3000, C-4W-TI-PI-1200, PRECOM-4W-08103-1000, C-4W-TI-PI-1000, CCM-PM4510 | C-4W-081-03-PI-3000: FS, C-4W-TI-PI-1200: FS, PRECOM-4W-08103-1000: FS, C-4W-TI-PI-1000: FS, CCM-PM4510: FS | 2025-05-31 11:00 | 2025-06-13 11:00
C-4W-081-03-PI-3000 | Not Started | P2543-R01-Oct24..4.3.1.6.1.12.3.1 | Tie - in (4'' Tie-in Connection Water Line) | C-4W-081-03-PI-1000, HM-CS-0110, ML1869-E32 | C-4W-081-03-PI-1000: FS, HM-CS-0110: FS, ML1869-E32: FS | C-4W-TI-3000, PRECOM-4W-08103-1000 | C-4W-TI-3000: FS, PRECOM-4W-08103-1000: FS | 2025-06-13 11:00 | 2025-06-16 11:00
C-4W-TI-CI-1000 | Not Started | P2543-R01-Oct24..4.3.1.6.2.12.1.1 | Demolition Works (Paving & Fence) | C-4W-081-03-CI-0100, CTF-1000, CTF-1010 | C-4W-081-03-CI-0100: FS, CTF-1000: FS, CTF-1010: FS | C-4W-TI-CI-1400 | C-4W-TI-CI-1400: FS | 2025-04-05 13:00 | 2025-04-12 13:00
C-4W-TI-CI-1400 | Not Started | P2543-R01-Oct24..4.3.1.6.2.12.1.2 | Concrete Works (Foundations for Equipment & Pipe Supports) | C-4W-081-03-CI-1400, C-4W-TI-CI-1000, HM-CS-0040, HE-CS-1310, HE-CS-1190, HE-CS-0230, ML1199-B24 | C-4W-081-03-CI-1400: FS, C-4W-TI-CI-1000: FS, HM-CS-0040: FS, HE-CS-1310: FS, HE-CS-1190: FS, HE-CS-0230: FS, ML1199-B24: FS | C-DBV6-CI-1800, C-4W-TI-CI-1700 | C-DBV6-CI-1800: FS, C-4W-TI-CI-1700: FS | 2025-04-22 13:00 | 2025-05-22 11:00
C-4W-TI-CI-1700 | Not Started | P2543-R01-Oct24..4.3.1.6.2.12.1.4 | Concrete Protection | C-4W-081-03-CI-1700, C-4W-TI-CI-1400, ML1199-B24 | C-4W-081-03-CI-1700: FS, C-4W-TI-CI-1400: FS, ML1199-B24: FS | C-4W-TI-PI-1200 | C-4W-TI-PI-1200: FS | 2025-05-31 11:00 | 2025-06-24 11:00
C-4W-TI-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.6.2.12.1.3 | Fences & Gates Construction | C-4W-081-03-CI-2600, HE-CS-0350, HE-CS-0470 | C-4W-081-03-CI-2600: FS, HE-CS-0350: FS, HE-CS-0470: FS | C-4W-TI-CI-2600, PRE-COM1310 | C-4W-TI-CI-2600: FS, PRE-COM1310: FS | 2025-06-16 11:00 | 2025-07-10 11:00
C-4W-TI-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.6.2.12.1.5 | Paving Works | C-4W-TI-CI-2220, ML1059-B28, HE-CS-0290 | C-4W-TI-CI-2220: FS, ML1059-B28: FS, HE-CS-0290: FS | PRE-COM1310 | PRE-COM1310: FS | 2025-07-10 11:00 | 2025-07-31 11:00
C-4W-TI-PI-1200 | Not Started | P2543-R01-Oct24..4.3.1.6.2.12.2.3 | Piping Installation | C-4W-081-03-PI-1000, C-4W-TI-CI-1700, C-4W-TI-PI-1000, ML1219-B19, HE-PI-1240, HE-PI-1300, HM-PL-0630, HM-PL-0640, HM-PL-0740, HM-PL-0220, HM-PI-0040, HM-PL-1510, HM-PL-1570 | C-4W-081-03-PI-1000: FS, C-4W-TI-CI-1700: FS, C-4W-TI-PI-1000: FS, ML1219-B19: FS, HE-PI-1240: FS, HE-PI-1300: FS, HM-PL-0630: FS, HM-PL-0640: FS, HM-PL-0740: FS, HM-PL-0220: FS, HM-PI-0040: FS, HM-PL-1510: FS, HM-PL-1570: FS | C-4W-TI-PI-1400, C-DBV6-PI-1000 | C-4W-TI-PI-1400: FS, C-DBV6-PI-1000: FS | 2025-06-24 11:00 | 2025-07-02 11:00
C-4W-TI-PI-1400 | Not Started | P2543-R01-Oct24..4.3.1.6.2.12.2.4 | Field Joining | C-4W-TI-PI-1200, HE-PI-1300, ML1002, HS-CN-0190 | C-4W-TI-PI-1200: FS, HE-PI-1300: FS, ML1002: FS, HS-CN-0190: FS | C-4W-TI-PI-1600 | C-4W-TI-PI-1600: FS | 2025-07-02 11:00 | 2025-07-09 11:00
C-4W-TI-PI-1600 | Not Started | P2543-R01-Oct24..4.3.1.6.2.12.2.5 | Hydrotesting | C-4W-TI-PI-1400, ML1219-B19 | C-4W-TI-PI-1400: FS, ML1219-B19: FS | C-4W-TI-PI-1800 | C-4W-TI-PI-1800: FS | 2025-07-09 11:00 | 2025-07-11 11:00
C-4W-TI-PI-1800 | Not Started | P2543-R01-Oct24..4.3.1.6.2.12.2.6 | Installation of Valves | C-4W-TI-PI-1600, ML1002, ML1219-B19, ML1889-E34, ML1879-E33, HE-PI-1240, HE-PI-1300, HM-PL-0220, HM-PI-0040, HS-CN-0190, HM-PL-1570 | C-4W-TI-PI-1600: FS, ML1002: FS, ML1219-B19: FS, ML1889-E34: FS, ML1879-E33: FS, HE-PI-1240: FS, HE-PI-1300: FS, HM-PL-0220: FS, HM-PI-0040: FS, HS-CN-0190: FS, HM-PL-1570: FS | C-4W-TI-3000, PRE-COM1310, C-4W-TI-PI-2000 | C-4W-TI-3000: FS, PRE-COM1310: FS, C-4W-TI-PI-2000: FF | 2025-07-11 11:00 | 2025-07-12 11:00
C-4W-TI-3000 | Not Started | P2543-R01-Oct24..4.3.1.6.2.12.3.1 | Tie - in (4'' Tie-in Connection Water Line) | C-4W-TI-PI-1800, C-4W-081-03-PI-3000, C-4W-TI-PI-2000, HM-CS-0110, ML1869-E32 | C-4W-TI-PI-1800: FS, C-4W-081-03-PI-3000: FS, C-4W-TI-PI-2000: FS, HM-CS-0110: FS, ML1869-E32: FS | PRE-COM1310 | PRE-COM1310: FS | 2025-07-12 11:00 | 2025-07-14 11:00
PRECOM-56-PL-1000 | Not Started | P2543-R01-Oct24..4.3.2.1.1.3.1 | Precommissioning | C-56-PL-607-CI-1510, C-56-PL-607-CI-2800, C-56-PL-607-CI-2810, C-56-PL-607-CI-2600, C-56-PL-607-CI-3000, C-56-PL-607-CI-3010, C-56-PL-607-ME-1000, C-56-PL-607-PI-2000, C-56-PL-607-PL-1030, C-56-PL-607-EI-2050, C-56-PL-607-EI-2040, C-56-PL-607-CA-1030, C-56 | C-56-PL-607-CI-1510: FS, C-56-PL-607-CI-2800: FS, C-56-PL-607-CI-2810: FS, C-56-PL-607-CI-2600: FS, C-56-PL-607-CI-3000: FS, C-56-PL-607-CI-3010: FS, C-56-PL-607-ME-1000: FS, C-56-PL-607-PI-2000: FS, C-56-PL-607-PL-1030: FS, C-56-PL-607-EI-2050: FS, C-56-P | COM-1000, ML1629-E08, CCM-PM4510, CCM-PM4560, ML1020 (Internal) | COM-1000: FS, ML1629-E08: FS, CCM-PM4510: FS, CCM-PM4560: FS, ML1020 (Internal): FS | 2025-09-06 11:00 | 2025-09-27 11:00
PRECOM-56-EB2-1000 | Not Started | P2543-R01-Oct24..4.3.2.1.2.3.1 | Precommissioning | C-56-EB2-CI-1800, C-56-EB2-CI-1810, C-56-EB2-CI-2000, C-56-EB2-CI-2010, C-56-EB2-ME-1010, C-56-EB2-ME-1000, C-56-EB2-EI-1230, C-56-EB2-TE-1400, C-56-EB2-TE-1610, C-56-EB2-EL-1600, HS-CN-0140, ML1619-E07, HS-CN-0140, C-COM-840, HE-PR-0950 | C-56-EB2-CI-1800: FS, C-56-EB2-CI-1810: FS, C-56-EB2-CI-2000: FS, C-56-EB2-CI-2010: FS, C-56-EB2-ME-1010: FS, C-56-EB2-ME-1000: FS, C-56-EB2-EI-1230: FS, C-56-EB2-TE-1400: FS, C-56-EB2-TE-1610: FS, C-56-EB2-EL-1600: FS, HS-CN-0140: SS, ML1619-E07: FS, HS-C | COM-1000, ML1629-E08, CCM-PM4510, ML1020 (Internal) | COM-1000: FS, ML1629-E08: FS, CCM-PM4510: FS, ML1020 (Internal): FS | 2025-09-04 11:00 | 2025-09-26 11:00
PRECOM-56-G-1000 | Not Started | P2543-R01-Oct24..4.3.2.1.8.3.1 | Precommissioning | C-56-G-HT-CI-2600, C-56-G-HT-PI-2000, C-56-G-HT101-ME-1050, C-56-G-HT102-ME-1050, C-56-G-HT103-ME-1050, C-56-G-HT-ME-2000, HS-CN-0140, HE-PR-0950, C-COM-840 | C-56-G-HT-CI-2600: FS, C-56-G-HT-PI-2000: FS, C-56-G-HT101-ME-1050: FS, C-56-G-HT102-ME-1050: FS, C-56-G-HT103-ME-1050: FS, C-56-G-HT-ME-2000: FS, HS-CN-0140: FS, HE-PR-0950: FS, C-COM-840: FS | COM-1000, ML1629-E08, CCM-PM4510, ML1020 (Internal) | COM-1000: FS, ML1629-E08: FS, CCM-PM4510: FS, ML1020 (Internal): FS | 2025-09-15 15:00 | 2025-09-29 15:00
PRECOM-56-HGHC-1000 | Not Started | P2543-R01-Oct24..4.3.2.2.2.3.1 | Precommissioning | C-56-01HG-PL-CI-6000, C-56-01HG-PL-CI-7200, C-56-01HG-PL-ME-7620, C-56-01HG-PL-CA-5250, C-56-01HG-PL-CI-6810, C-56-01HG-PL-CI-7810, C-56-01HG-PL-TE-8210, C-56-HC01-PL-CI-6000, C-56-HC01-PL-CI-7200, C-56-HC01-PL-ME-7620, C-56-HC01-PL-CA-5250, C-56-HC01-PL-C | C-56-01HG-PL-CI-6000: FS, C-56-01HG-PL-CI-7200: FS, C-56-01HG-PL-ME-7620: FS, C-56-01HG-PL-CA-5250: FS, C-56-01HG-PL-CI-6810: FS, C-56-01HG-PL-CI-7810: FS, C-56-01HG-PL-TE-8210: FS, C-56-HC01-PL-CI-6000: FS, C-56-HC01-PL-CI-7200: FS, C-56-HC01-PL-ME-7620: | COM-1000, ML1649-E10, ML1959-E41, CCM-PM4570, CCM-PM4510, ML1020 (Internal) | COM-1000: FS, ML1649-E10: FS, ML1959-E41: FS, CCM-PM4570: FS, CCM-PM4510: FF, ML1020 (Internal): FS | 2025-09-17 15:00 | 2025-10-09 15:00
PRECOM-56-PR-1000 | Not Started | P2543-R01-Oct24..4.3.2.2.1.3.1 | Precommissioning | C-56-PR-838-CI-1510, C-56-PR-838-CI-1500, C-56-PR-838-CI-2800, C-56-PR-838-CI-2810, C-56-PR-838-CI-2600, C-56-PR-838-CI-3000, C-56-PR-838-CI-3010, C-56-PR-838-ME-1100, C-56-PR-838-PI-2000, C-56-PR-838-PL-1030, C-56-PR-838-EI-2050, C-56-PR-838-EI-2040, C-56 | C-56-PR-838-CI-1510: FS, C-56-PR-838-CI-1500: FS, C-56-PR-838-CI-2800: FS, C-56-PR-838-CI-2810: FS, C-56-PR-838-CI-2600: FS, C-56-PR-838-CI-3000: FS, C-56-PR-838-CI-3010: FS, C-56-PR-838-ME-1100: FS, C-56-PR-838-PI-2000: FS, C-56-PR-838-PL-1030: FS, C-56-P | COM-1000, ML1629-E08, CCM-PM4510, ML1020 (Internal) | COM-1000: FS, ML1629-E08: FS, CCM-PM4510: FS, ML1020 (Internal): FS | 2025-09-17 11:00 | 2025-10-09 11:00
PRECOM-56-59101-1000 | Not Started | P2543-R01-Oct24..4.3.2.2.8.3.1 | Precommissioning | C-56-591-01-CI-2800, C-56-591-01-CI-2810, C-56-591-01-CI-2220, C-56-591-01-CI-2230, C-56-591-01-CI-2600, C-56-591-01-CI-2610, C-56-591-01-CI-3010, C-56-591-01-ME-1000, C-56-591-01-PI-2000, C-56-591-01-PL-1080, C-56-591-01-PL-1090, C-56-591-01-EI-2040, C-56 | C-56-591-01-CI-2800: FS, C-56-591-01-CI-2810: FS, C-56-591-01-CI-2220: FS, C-56-591-01-CI-2230: FS, C-56-591-01-CI-2600: FS, C-56-591-01-CI-2610: FS, C-56-591-01-CI-3010: FS, C-56-591-01-ME-1000: FS, C-56-591-01-PI-2000: FS, C-56-591-01-PL-1080: FS, C-56-5 | COM-1000, ML1629-E08, CCM-PM4510, ML1649-E10, ML1020 (Internal) | COM-1000: FS, ML1629-E08: FS, CCM-PM4510: FS, ML1649-E10: FS, ML1020 (Internal): FS | 2025-09-20 11:00 | 2025-10-09 11:00
PRECOM-56-59801-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.6.8.2 | Precommissioning BVS-1 | C-52-598-01-CI-2220, C-52-598-01-CI-2800, C-52-598-01-CI-2810, C-52-598-01-CI-2230, C-52-598-01-CI-2600, C-52-598-01-CI-2610, C-52-598-01-CI-3010, C-52-598-01-CI-3000, C-52-598-01-ME-1000, C-52-598-01-PI-2000, C-52-598-01-PL-1060, C-52-598-01-PL-1090, C-52 | C-52-598-01-CI-2220: FS, C-52-598-01-CI-2800: FS, C-52-598-01-CI-2810: FS, C-52-598-01-CI-2230: FS, C-52-598-01-CI-2600: FS, C-52-598-01-CI-2610: FS, C-52-598-01-CI-3010: FS, C-52-598-01-CI-3000: FS, C-52-598-01-ME-1000: FS, C-52-598-01-PI-2000: FS, C-52-5 | COM-1000, CCM-PM4520, CCM-PM4530, CCM-PM4540, ML1020 (Internal) | COM-1000: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS, ML1020 (Internal): FS | 2025-08-26 11:00 | 2025-09-20 11:00
PRECOM-52-0201-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.6.8.1 | Pre-commissioning from BVS-02 to BVS-01 | C-52-0102-PL-CI-6000, C-52-0102-PL-CI-7200, C-52-0102-PL-ME-7620, C-52-0102-PL-CI-6810, C-52-0102-PL-CI-7810, C-52-0102-CNH10-1800, C-52-0102-CNH09-1800, C-52-0102-CNH08-1800, C-52-0102-CNM07-1800, C-52-0102-CNM05-1800, C-52-0102-PL-CA-5250, C-52-0102-PL-T | C-52-0102-PL-CI-6000: FS, C-52-0102-PL-CI-7200: FS, C-52-0102-PL-ME-7620: FS, C-52-0102-PL-CI-6810: FS, C-52-0102-PL-CI-7810: FS, C-52-0102-CNH10-1800: FS, C-52-0102-CNH09-1800: FS, C-52-0102-CNH08-1800: FS, C-52-0102-CNM07-1800: FS, C-52-0102-CNM05-1800: | COM-1000, ML1979-E43, CCM-PM4580, ML1030 (Internal) | COM-1000: FS, ML1979-E43: FS, CCM-PM4580: FS, ML1030 (Internal): FS | 2025-05-14 11:00 | 2025-05-27 11:00
PRECOM-52-PL-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.10.8.1 | Precommissioning Pig Launcher 838-V-602 | C-52-PL-838-CI-2800, C-52-PL-838-CI-2600, C-52-PL-838-CI-2810, C-52-PL-838-CI-1510, C-52-PL-838-CI-3000, C-52-PL-838-CI-3010, C-52-PL-838-ME-1000, C-52-PL-838-PI-2000, C-52-PL-838-PL-1030, C-52-PL-838-EI-2040, C-52-PL-838-EI-2050, C-52-PL-838-CA-1030, C-52 | C-52-PL-838-CI-2800: FS, C-52-PL-838-CI-2600: FS, C-52-PL-838-CI-2810: FS, C-52-PL-838-CI-1510: FS, C-52-PL-838-CI-3000: FS, C-52-PL-838-CI-3010: FS, C-52-PL-838-ME-1000: FS, C-52-PL-838-PI-2000: FS, C-52-PL-838-PL-1030: FS, C-52-PL-838-EI-2040: FS, C-52-P | COM-1000, ML1749-E20, CCM-PM4520, CCM-PM4530, CCM-PM4540, ML1100, ML1030 (Internal) | COM-1000: FS, ML1749-E20: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS, ML1100: FS, ML1030 (Internal): FS | 2025-10-14 11:00 | 2025-11-03 11:00
PRECOM-52-HG01-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.10.8.2 | Pre-commissioning from HGCP to BVS-01 | C-52-HG01-PL-CI-6000, C-52-HG01-PL-CI-7200, C-52-HG01-PL-ME-7620, C-52-HG01-PL-CI-6810, C-52-HG01-PL-CI-7810, C-52-HG01-CNM03-1800, C-52-HG01-CNM02-1800, C-52-HG01-CNM01-1800, C-52-HG01-PL-CA-5250, C-52-HG01-PL-TE-8210, C-52-HG01-FENCE-1070, C-52-HG01-PL-C | C-52-HG01-PL-CI-6000: FS, C-52-HG01-PL-CI-7200: FS, C-52-HG01-PL-ME-7620: FS, C-52-HG01-PL-CI-6810: FS, C-52-HG01-PL-CI-7810: FS, C-52-HG01-CNM03-1800: FS, C-52-HG01-CNM02-1800: FS, C-52-HG01-CNM01-1800: FS, C-52-HG01-PL-CA-5250: FS, C-52-HG01-PL-TE-8210: | COM-1000, ML1829-E28, ML1979-E43, CCM-PM4520, CCM-PM4530, CCM-PM4580, CCM-PM4540, ML1030 (Internal) | COM-1000: FS, ML1829-E28: FS 3, ML1979-E43: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4580: FS, CCM-PM4540: FS, ML1030 (Internal): FS | 2025-06-16 11:00 | 2025-07-01 11:00
PRECOM-56-59802-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.5.8.1 | Precommissioning BVS-2 | C-52-598-02-CI-2220, C-52-598-02-CI-2800, C-52-598-02-CI-2230, C-52-598-02-CI-2810, C-52-598-02-CI-2600, C-52-598-02-CI-2610, C-52-598-02-CI-3010, C-52-598-02-CI-3000, C-52-598-02-ME-1000, C-52-598-02-PI-2000, C-52-598-02-PL-1080, C-52-598-02-PL-1040, C-52 | C-52-598-02-CI-2220: FS, C-52-598-02-CI-2800: FS, C-52-598-02-CI-2230: FS, C-52-598-02-CI-2810: FS, C-52-598-02-CI-2600: FS, C-52-598-02-CI-2610: FS, C-52-598-02-CI-3010: FS, C-52-598-02-CI-3000: FS, C-52-598-02-ME-1000: FS, C-52-598-02-PI-2000: FS, C-52-5 | COM-1000, CCM-PM4520, CCM-PM4530, CCM-PM4540, ML1020 (Internal) | COM-1000: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS, ML1020 (Internal): FS | 2025-09-01 11:00 | 2025-09-26 11:00
PRECOM-52-0203-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.5.8.2 | Pre-commissioning from BVS-02 to BVS-03 | C-52-0203-PL-CI-6000, C-52-0203-PL-CI-7200, C-52-0203-PL-ME-7620, C-52-0203-PL-CI-6810, C-52-0203-PL-CI-7810, C-52-0203-PL-CA-5250, C-52-0203-PL-TE-8210, ML1779-E23, C-52-0203-PL-ME-2800, C-PER-1130 | C-52-0203-PL-CI-6000: FS, C-52-0203-PL-CI-7200: FS, C-52-0203-PL-ME-7620: FS, C-52-0203-PL-CI-6810: FS, C-52-0203-PL-CI-7810: FS, C-52-0203-PL-CA-5250: FS, C-52-0203-PL-TE-8210: FS, ML1779-E23: FF, C-52-0203-PL-ME-2800: SS, C-PER-1130: FS | COM-1000, ML1979-E43, CCM-PM4580, ML1030 (Internal), ML1090 | COM-1000: FS, ML1979-E43: FS, CCM-PM4580: FS, ML1030 (Internal): FS, ML1090: FS | 2025-03-29 13:00 | 2025-04-12 13:00
PRECOM-56-59803-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.4.8.2 | Precommissioning BVS-3 | C-52-598-03-CI-2600, C-52-598-03-CI-2610, C-52-598-03-CI-2800, C-52-598-03-CI-2810, C-52-598-03-CI-2220, C-52-598-03-CI-2230, C-52-598-03-CI-3010, C-52-598-03-CI-3000, C-52-598-03-ME-1000, C-52-598-03-PI-2000, C-52-598-03-PL-1080, C-52-598-03-PL-1090, C-52 | C-52-598-03-CI-2600: FS, C-52-598-03-CI-2610: FS, C-52-598-03-CI-2800: FS, C-52-598-03-CI-2810: FS, C-52-598-03-CI-2220: FS, C-52-598-03-CI-2230: FS, C-52-598-03-CI-3010: FS, C-52-598-03-CI-3000: FS, C-52-598-03-ME-1000: FS, C-52-598-03-PI-2000: FS, C-52-5 | COM-1000, ML1749-E20, CCM-PM4520, CCM-PM4530, CCM-PM4540 | COM-1000: FS, ML1749-E20: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-09-26 11:00 | 2025-10-21 11:00
PRECOM-52-IDS1-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.4.8.1 | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | C-52-IDS1-CI-2220, C-52-IDS1-CI-2230, C-52-IDS1-CI-2600, C-52-IDS1-CI-2800, C-52-IDS1-CI-2810, C-52-IDS1-EI-2050, C-52-0304-FENCE-1070, C-52-IDS1-EI-2010, C-52-IDS1-TE-1600, HE-PR-0950, HS-CN-0140 | C-52-IDS1-CI-2220: FS, C-52-IDS1-CI-2230: FS, C-52-IDS1-CI-2600: FS, C-52-IDS1-CI-2800: FS, C-52-IDS1-CI-2810: FS, C-52-IDS1-EI-2050: FS, C-52-0304-FENCE-1070: FS, C-52-IDS1-EI-2010: FS, C-52-IDS1-TE-1600: FS, HE-PR-0950: FS, HS-CN-0140: FS | COM-1000, ML1749-E20, CCM-PM4520, CCM-PM4530, CCM-PM4540, ML1030 (Internal) | COM-1000: FS, ML1749-E20: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS, ML1030 (Internal): FS | 2025-09-25 11:00 | 2025-10-16 11:00
PRECOM-52-0304-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.4.8.3 | Pre-commissioning from BVS-03 to BVS-04 | C-52-0304-PL-CI-6000, C-52-0304-PL-CI-7200, C-52-0304-PL-ME-7620, C-52-0304-PL-CI-6810, C-52-0304-PL-CI-7810, C-52-0304-PL-CA-5250, C-52-0304-PL-TE-8210, ML1789-E24, C-52-0304-PL-ME-2800, C-PER-1140, ML1459-D12, C-PER-1150, C-PER-1160 | C-52-0304-PL-CI-6000: FS, C-52-0304-PL-CI-7200: FS, C-52-0304-PL-ME-7620: FS, C-52-0304-PL-CI-6810: FS, C-52-0304-PL-CI-7810: FS, C-52-0304-PL-CA-5250: FS, C-52-0304-PL-TE-8210: FS, ML1789-E24: FF, C-52-0304-PL-ME-2800: SS, C-PER-1140: FS, ML1459-D12: FS, | COM-1000, ML1979-E43, CCM-PM4580, ML1030 (Internal) | COM-1000: FS, ML1979-E43: FS, CCM-PM4580: FS, ML1030 (Internal): FS | 2025-06-04 11:00 | 2025-06-16 11:00
PRECOM-56-59804-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.3.8.1 | Precommissioning BVS-4 | C-52-598-04-CI-2220, C-52-598-04-CI-2230, C-52-598-04-CI-2600, C-52-598-04-CI-2800, C-52-598-04-CI-2610, C-52-598-04-CI-2810, C-52-598-04-CI-3000, C-52-598-04-CI-3010, C-52-598-04-ME-1000, C-52-598-04-PI-2000, C-52-598-04-PL-1080, C-52-598-04-PL-1040, C-52 | C-52-598-04-CI-2220: FS, C-52-598-04-CI-2230: FS, C-52-598-04-CI-2600: FS, C-52-598-04-CI-2800: FS, C-52-598-04-CI-2610: FS, C-52-598-04-CI-2810: FS, C-52-598-04-CI-3000: FS, C-52-598-04-CI-3010: FS, C-52-598-04-ME-1000: FS, C-52-598-04-PI-2000: FS, C-52-5 | COM-1000, ML1749-E20, CCM-PM4520, CCM-PM4530, CCM-PM4540, ML1020 (Internal) | COM-1000: FS, ML1749-E20: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS, ML1020 (Internal): FS | 2025-09-17 11:00 | 2025-10-11 11:00
PRECOM-52-IDS2-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.3.8.2 | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | C-52-IDS2-CI-2220, C-52-IDS2-CI-2600, C-52-IDS2-TE-1590, C-52-IDS2-CI-2230, C-52-IDS2-CI-2800, C-52-IDS2-CI-2810, C-52-IDS2-EI-2050, C-52-0405-FENCE-1070, C-52-IDS2-EI-2010, C-52-IDS2-TE-1600, C-52-IDS1-EI-2010, C-52-IDS1-TE-1600, HE-PR-0950, HS-CN-0140 | C-52-IDS2-CI-2220: FS, C-52-IDS2-CI-2600: FS, C-52-IDS2-TE-1590: FS, C-52-IDS2-CI-2230: FS, C-52-IDS2-CI-2800: FS, C-52-IDS2-CI-2810: FS, C-52-IDS2-EI-2050: FS, C-52-0405-FENCE-1070: FS, C-52-IDS2-EI-2010: FS, C-52-IDS2-TE-1600: FS, C-52-IDS1-EI-2010: FS, | COM-1000, ML1749-E20, CCM-PM4520, CCM-PM4530, A3980, CCM-PM4540, ML1030 (Internal) | COM-1000: FS, ML1749-E20: FS, CCM-PM4520: FS, CCM-PM4530: FS, A3980: FS, CCM-PM4540: FS, ML1030 (Internal): FS | 2025-10-09 11:00 | 2025-10-30 11:00
PRECOM-52-0405-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.3.8.3 | Pre-commissioning from BVS-04 to BVS-05 | C-52-0405-PL-CI-6000, C-52-0405-PL-CI-7200, C-52-0405-PL-ME-7620, C-52-0405-PL-CI-6810, C-52-0405-PL-CI-7810, C-52-0405-CNM17-1800, C-52-0405-CNM18-1800, C-52-0405-CNH19-1800, C-52-0405-CNH20-1800, C-52-0405-CNM23-1800, C-52-0405-CNH24-1800, C-52-0405-PL-C | C-52-0405-PL-CI-6000: FS, C-52-0405-PL-CI-7200: FS, C-52-0405-PL-ME-7620: FS, C-52-0405-PL-CI-6810: FS, C-52-0405-PL-CI-7810: FS, C-52-0405-CNM17-1800: FS, C-52-0405-CNM18-1800: FS, C-52-0405-CNH19-1800: FS, C-52-0405-CNH20-1800: FS, C-52-0405-CNM23-1800: | COM-1000, CCM-PM4580, ML1030 (Internal) | COM-1000: FS, CCM-PM4580: FS, ML1030 (Internal): FS | 2025-10-03 11:00 | 2025-10-10 11:00
PRECOM-56-59805-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.2.8.1 | Precommissioning BVS-5 | C-52-598-05-CI-2800, C-52-598-05-CI-2810, C-52-598-05-CI-2610, C-52-598-05-CI-2600, C-52-598-05-CI-2230, C-52-598-05-CI-2220, C-52-598-05-CI-3000, C-52-598-05-CI-3010, C-52-598-05-ME-1000, C-52-598-05-PI-2000, C-52-598-05-PL-1080, C-52-598-05-PL-1040, C-52 | C-52-598-05-CI-2800: FS, C-52-598-05-CI-2810: FS, C-52-598-05-CI-2610: FS, C-52-598-05-CI-2600: FS, C-52-598-05-CI-2230: FS, C-52-598-05-CI-2220: FS, C-52-598-05-CI-3000: FS, C-52-598-05-CI-3010: FS, C-52-598-05-ME-1000: FS, C-52-598-05-PI-2000: FS, C-52-5 | COM-1000, ML1749-E20, CCM-PM4520, CCM-PM4530, CCM-PM4540, ML1020 (Internal) | COM-1000: FS, ML1749-E20: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS, ML1020 (Internal): FS | 2025-08-09 11:00 | 2025-08-30 11:00
PRECOM-52-D-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.2.8.4 | Precommissioning DEL/TFP Pipeline | C-52-D-HT-CI-1480, C-52-D-HT-CI-1420, C-52-D-HT-CI-2600, C-52-D-HT-PI-2000, C-52-D-HT002-ME-1050, C-52-D-HT-ME-2000, C-COM-840, HS-CN-0140, HE-PR-0950 | C-52-D-HT-CI-1480: FS, C-52-D-HT-CI-1420: FS, C-52-D-HT-CI-2600: FF, C-52-D-HT-PI-2000: FS, C-52-D-HT002-ME-1050: FS, C-52-D-HT-ME-2000: FS, C-COM-840: FS, HS-CN-0140: FS, HE-PR-0950: FS | COM-1000, ML1749-E20, CCM-PM4520, CCM-PM4530, CCM-PM4540, ML1030 (Internal) | COM-1000: FS, ML1749-E20: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS, ML1030 (Internal): FS | 2025-09-08 11:00 | 2025-09-18 11:00
PRECOM-52-IDS3-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.2.8.2 | Pre-Commissioning Intrusion Detection KP122 to KP123 | C-52-IDS3-CI-2220, C-52-IDS3-CI-2600, C-52-IDS3-CI-2230, C-52-IDS3-CI-2800, C-52-IDS3-CI-2810, C-52-IDS3-EI-2050, C-52-0506-FENCE-1070, C-52-IDS3-EI-2010, C-52-IDS3-TE-1600, C-52-IDS2-EI-2010, C-52-IDS2-TE-1600, C-52-IDS1-EI-2010, C-52-IDS1-TE-1600, HE-PR- | C-52-IDS3-CI-2220: FS, C-52-IDS3-CI-2600: FS, C-52-IDS3-CI-2230: FS, C-52-IDS3-CI-2800: FS, C-52-IDS3-CI-2810: FS, C-52-IDS3-EI-2050: FS, C-52-0506-FENCE-1070: FF, C-52-IDS3-EI-2010: FS, C-52-IDS3-TE-1600: FS, C-52-IDS2-EI-2010: FS, C-52-IDS2-TE-1600: FS, | COM-1000, ML1749-E20, CCM-PM4520, CCM-PM4530, A3980, CCM-PM4540, ML1030 (Internal) | COM-1000: FS, ML1749-E20: FS, CCM-PM4520: FS, CCM-PM4530: FS, A3980: FS, CCM-PM4540: FS, ML1030 (Internal): FS | 2025-10-17 11:00 | 2025-10-31 11:00
PRECOM-52-0506-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.2.8.3 | Pre-commissioning from BVS-05 to BVS-06 | C-52-0506-PL-CI-6000, C-52-0506-PL-CI-7200, C-52-0506-PL-ME-7620, C-52-0506-PL-CI-6810, C-52-0506-PL-CI-7810, C-52-0506-CNH27-1800, C-52-0506-PL-CA-5250, C-52-0506-PL-TE-8210, ML1809-E26, C-52-0102-CNH10-1200, C-PER-1280, C-PER-1310, C-PER-1180 | C-52-0506-PL-CI-6000: FS, C-52-0506-PL-CI-7200: FS, C-52-0506-PL-ME-7620: FS, C-52-0506-PL-CI-6810: FS, C-52-0506-PL-CI-7810: FS, C-52-0506-CNH27-1800: FS, C-52-0506-PL-CA-5250: FS, C-52-0506-PL-TE-8210: FS, ML1809-E26: FF, C-52-0102-CNH10-1200: FS, C-PER- | COM-1000, ML1979-E43, CCM-PM4580, ML1030 (Internal) | COM-1000: FS, ML1979-E43: FS, CCM-PM4580: FS, ML1030 (Internal): FS | 2025-10-01 15:00 | 2025-10-11 15:00
PRECOM-52-59806-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.1.8.1 | Precommissioning BVS-6 | C-52-598-06-CI-2220, C-52-598-06-CI-2230, C-52-598-06-CI-2600, C-52-598-06-CI-2610, C-52-598-06-CI-2800, C-52-598-06-CI-2810, C-52-598-06-CI-3000, C-52-598-06-CI-3010, C-52-598-06-CI-2400, C-52-598-06-ME-1000, C-52-598-06-PI-2000, C-52-598-06-PL-1080, C-52 | C-52-598-06-CI-2220: FS, C-52-598-06-CI-2230: FS, C-52-598-06-CI-2600: FS, C-52-598-06-CI-2610: FS, C-52-598-06-CI-2800: FS, C-52-598-06-CI-2810: FS, C-52-598-06-CI-3000: FS, C-52-598-06-CI-3010: FS, C-52-598-06-CI-2400: FS, C-52-598-06-ME-1000: FS, C-52-5 | COM-1000, ML1749-E20, CCM-PM4520, CCM-PM4530, CCM-PM4540, ML1030 (Internal) | COM-1000: FS, ML1749-E20: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS, ML1030 (Internal): FS | 2025-08-23 11:00 | 2025-09-15 11:00
PRECOM-52-06CR-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.1.8.2 | Pre-commissioning from BVS-06 to CRS Sweihan | C-52-06CR-PL-CI-6000, C-52-06CR-PL-CI-7200, C-52-06CR-PL-ME-7620, C-52-06CR-PL-CI-6810, C-52-06CR-PL-CI-7810, C-52-06CR-CNH30-1800, C-52-06CR-CNM31-1800, C-52-06CR-PL-CA-5210, C-52-06CR-PL-CA-5250, C-52-06CR-PL-TE-8210, C-52-06CR-FENCE-1070, HE-PR-0950, HS | C-52-06CR-PL-CI-6000: FS, C-52-06CR-PL-CI-7200: FS, C-52-06CR-PL-ME-7620: FS 1, C-52-06CR-PL-CI-6810: FS, C-52-06CR-PL-CI-7810: FS, C-52-06CR-CNH30-1800: FS, C-52-06CR-CNM31-1800: FS, C-52-06CR-PL-CA-5210: FS, C-52-06CR-PL-CA-5250: FS, C-52-06CR-PL-TE-8210 | COM-1000, ML1979-E43, CCM-PM4580, ML1030 (Internal), ML1100 | COM-1000: FS, ML1979-E43: FS 1, CCM-PM4580: FS, ML1030 (Internal): FS 6, ML1100: FF | 2025-11-01 11:30 | 2025-11-03 11:30
PRECOM-52-EB1-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.1.8.3 | Precommissioning Electrical Building Type-I | C-52-EB1-CI-2010, C-52-EB1-CI-1810, C-52-EB1-CI-1800, C-52-EB1-CI-2000, C-52-EB1-ME-1010, C-52-EB1-ME-1000, C-52-EB1-EI-1230, C-52-EB1-TE-1400, C-52-EB1-TE-1610, C-52-OHPL-CI-1400, C-52-OHPL-EL-1400, C-52-OHPL-EL-2000, C-52-ADDC-EL-1200, C-52-ADDC-CI-1600, | C-52-EB1-CI-2010: FS, C-52-EB1-CI-1810: FS, C-52-EB1-CI-1800: FS, C-52-EB1-CI-2000: FS, C-52-EB1-ME-1010: FS, C-52-EB1-ME-1000: FS, C-52-EB1-EI-1230: FS, C-52-EB1-TE-1400: FS, C-52-EB1-TE-1610: FS, C-52-OHPL-CI-1400: FS, C-52-OHPL-EL-1400: FS, C-52-OHPL-EL | COM-1000, ML1749-E20, ML1859-E31, ML1859-E31, CCM-PM4520, CCM-PM4530, CCM-PM4540, ML1030 (Internal), ML1100 | COM-1000: FS, ML1749-E20: FS 1, ML1859-E31: FS, ML1859-E31: FF, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS, ML1030 (Internal): FS, ML1100: FF | 2025-10-14 11:00 | 2025-11-03 11:00
PRECOM-52-PR-1000 | Not Started | P2543-R01-Oct24..4.3.2.3.1.8.4 | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-CI-1510, C-52-PR-839-CI-1070, C-52-PR-839-ME-1800, C-52-PR-839-ME-1810, C-52-PR-839-ME-2010, C-52-PR-839-ME-2000, C-52-PR-839-CI-2800, C-52-PR-839-CI-2810, C-52-PR-839-CI-1500, C-52-PR-839-CI-2600, C-52-PR-839-CI-3010, C-52-PR-839-CI-3000, C-52 | C-52-PR-839-CI-1510: FS, C-52-PR-839-CI-1070: FS, C-52-PR-839-ME-1800: FS, C-52-PR-839-ME-1810: FS, C-52-PR-839-ME-2010: FS, C-52-PR-839-ME-2000: FS, C-52-PR-839-CI-2800: FS, C-52-PR-839-CI-2810: FS, C-52-PR-839-CI-1500: FS, C-52-PR-839-CI-2600: FS, C-52-P | COM-1000, ML1749-E20, ML1859-E31, CCM-PM4520, CCM-PM4530, CCM-PM4540, ML1030 (Internal) | COM-1000: FS, ML1749-E20: FS, ML1859-E31: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS, ML1030 (Internal): FS | 2025-10-02 07:00 | 2025-10-22 17:00
PRECOM-36-KM-1000 | Not Started | P2543-R01-Oct24..4.3.2.4.8.1 | Precommissioning | C-36-KM-HT-CI-2800, C-36-KM-HT-CI-2810, C-36-KM-HT-CI-2600, CCV-52-KM-1120, C-36-KM-HT-PI-2000, C-36-KM-HT-EI-2040, C-36-KM-HT-EI-2050, C-36-KM-HT03-ME-1050, C-36-KM-HT04-ME-1050, C-36-KM-HT-ME-2000, HE-TL-0830, ML1033-B22, HS-CN-0290, HE-TL-0470, HE-TL-07 | C-36-KM-HT-CI-2800: FS, C-36-KM-HT-CI-2810: FS, C-36-KM-HT-CI-2600: FS, CCV-52-KM-1120: FS, C-36-KM-HT-PI-2000: FS, C-36-KM-HT-EI-2040: FS, C-36-KM-HT-EI-2050: FS, C-36-KM-HT03-ME-1050: FS, C-36-KM-HT04-ME-1050: FS, C-36-KM-HT-ME-2000: FS, HE-TL-0830: FS, | COM-1000, CCM-PM4520, CCM-PM4530, CCM-PM4590, CCM-PM4540 | COM-1000: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4590: FS, CCM-PM4540: FS | 2025-08-21 09:00 | 2025-09-04 09:00
PRECOM-4NH5-TPL-1000 | Not Started | P2543-R01-Oct24..4.3.2.5.1.8.1 | Precommissioning | C-4N-H5-TPL-CI-2800, C-4N-H5-TPL-CI-2810, C-4N-H5-TPL-CI-2600, C-4N-H5-TPL-CI-3010, C-4N-H5-TPL-CI-3000, C-4N-H5-TPL-ME-1000, C-4N-H5-TPL-PI-2000, C-4N-H5-TPL-PL-1030, C-4N-H5-TPL-EI-2040, C-4N-H5-TPL-EI-2050, C-4N-H5-TPL-CA-1030, C-4N-H5-TPL-TE-1420, HS-C | C-4N-H5-TPL-CI-2800: FS, C-4N-H5-TPL-CI-2810: FS, C-4N-H5-TPL-CI-2600: FS, C-4N-H5-TPL-CI-3010: FS, C-4N-H5-TPL-CI-3000: FS, C-4N-H5-TPL-ME-1000: FS, C-4N-H5-TPL-PI-2000: FS, C-4N-H5-TPL-PL-1030: FS, C-4N-H5-TPL-EI-2040: FS, C-4N-H5-TPL-EI-2050: FS, C-4N-H | COM-1000, CCM-PM4510 | COM-1000: FS, CCM-PM4510: FS | 2025-09-09 11:00 | 2025-09-30 11:00
PRECOM-4NHG-TPR-1000 | Not Started | P2543-R01-Oct24..4.3.2.5.2.8.1 | Precommissioning | C-4N-HG-TPR-CI-2800, C-4N-HG-TPR-CI-2810, C-4N-HG-TPR-CI-2600, C-4N-HG-TPR-CI-1500, C-4N-HG-TPR-CI-3010, C-4N-HG-TPR-CI-3000, C-4N-HG-TPR-ME-1100, C-4N-HG-TPR-PI-2000, C-4N-HG-TPR-PL-1030, C-4N-HG-TPR-EI-2040, C-4N-HG-TPR-EI-2050, C-4N-HG-TPR-CA-1030, C-4N | C-4N-HG-TPR-CI-2800: FS, C-4N-HG-TPR-CI-2810: FS, C-4N-HG-TPR-CI-2600: FS, C-4N-HG-TPR-CI-1500: FS, C-4N-HG-TPR-CI-3010: FS, C-4N-HG-TPR-CI-3000: FS, C-4N-HG-TPR-ME-1100: FS, C-4N-HG-TPR-PI-2000: FS, C-4N-HG-TPR-PL-1030: FS, C-4N-HG-TPR-EI-2040: FS, C-4N-H | COM-1000, CCM-PM4510 | COM-1000: FS, CCM-PM4510: FS | 2025-09-08 11:00 | 2025-09-22 11:00
PRECOM-4N-H5HG-1000 | Not Started | P2543-R01-Oct24..4.3.2.5.3.8.1 | Precommissioning | C-4N-H5HG-PIPEL-6000, C-4N-H5HG-PIPEL-7620, C-4N-H5HG-PIPEL-5210, C-4N-H5HG-PIPEL-5250, C-4N-H5HG-PIPEL-6810, C-4N-H5HG-PIPEL-7810, C-4N-H5HG-PIPEL-8210, C-4N-H5HG-CNH01-1030, C-4N-H5HG-CNH02-1030, C-4N-H5HG-CNH03-1030, C-4N-H5HG-CNH04-1030, C-4N-H5HG-CNH0 | C-4N-H5HG-PIPEL-6000: FS, C-4N-H5HG-PIPEL-7620: FS, C-4N-H5HG-PIPEL-5210: FS, C-4N-H5HG-PIPEL-5250: FS, C-4N-H5HG-PIPEL-6810: FS, C-4N-H5HG-PIPEL-7810: FS, C-4N-H5HG-PIPEL-8210: FS, C-4N-H5HG-CNH01-1030: FS, C-4N-H5HG-CNH02-1030: FS, C-4N-H5HG-CNH03-1030: | COM-1000, ML1929-E38, CCM-PM4600 | COM-1000: FS, ML1929-E38: FS, CCM-PM4600: FS | 2025-09-13 12:30 | 2025-09-25 12:30
PRECOM-4W-08103-1000 | Not Started | P2543-R01-Oct24..4.3.2.6.1.8.1 | Precommissioning | C-4W-081-03-CI-2600, C-4W-081-03-PI-1000, C-4W-081-03-PI-3000, HM-CS-0110, HS-CN-0140, HE-PR-0950 | C-4W-081-03-CI-2600: FS, C-4W-081-03-PI-1000: FS, C-4W-081-03-PI-3000: FS, HM-CS-0110: FS, HS-CN-0140: FS, HE-PR-0950: FS | COM-1000, CCM-PM4510 | COM-1000: FS, CCM-PM4510: FS | 2025-06-16 11:00 | 2025-06-20 11:00
PRE-COM1310 | Not Started | P2543-R01-Oct24..4.3.2.6.2.8.1 | Precommissioning | C-4W-TI-CI-2220, C-4W-TI-CI-2600, C-4W-TI-PI-1800, C-4W-TI-3000, HM-CS-0110, HS-CN-0140, C-COM-840, HE-PR-0950 | C-4W-TI-CI-2220: FS, C-4W-TI-CI-2600: FS, C-4W-TI-PI-1800: FS, C-4W-TI-3000: FS, HM-CS-0110: FS, HS-CN-0140: FS, C-COM-840: FS, HE-PR-0950: FS | COM-1000, CCM-PM4510, CCM-PM4610 | COM-1000: FS, CCM-PM4510: FS, CCM-PM4610: FS | 2025-07-31 11:00 | 2025-08-21 11:00
PRECOM-4W-SVHG-1000 | Not Started | P2543-R01-Oct24..4.3.2.6.8.3 | Precommissioning | C-4W-SVHG-PIPEL-6000, C-4N-H5HG-CNH1-1030, C-4N-H5HG-CNH2-1030, C-4W-SVHG-PIPEL-7610, C-4W-SVHG-PIPEL-6810, C-4W-SVHG-PIPEL-7810 | C-4W-SVHG-PIPEL-6000: FS, C-4N-H5HG-CNH1-1030: FS, C-4N-H5HG-CNH2-1030: FS, C-4W-SVHG-PIPEL-7610: FS, C-4W-SVHG-PIPEL-6810: FS, C-4W-SVHG-PIPEL-7810: FS | COM-1000, ML1090 | COM-1000: FS, ML1090: FS | 2025-04-17 13:00 | 2025-04-22 12:00
PRE-COM1330 | Not Started | P2543-R01-Oct24..4.3.2.7.8.1 | Precommissioning | C-DBV6-CI-2810, C-DBV6-CI-2800, C-DBV6-EI-2500, C-MAQTA-CI-2800, C-MAQTA-CI-2810, C-MAQTA-EI-2050, C-MAQTA-TE-1020, C-541CR-CI-1020, C-541CR-CI-1030, C-541CR-EI-1040, C-541CR-TE-1000, C-577-CI-1010, C-577-TE-1000, C-601-CI-1010, C-601-TE-1000, C-MAQTA-TE-1 | C-DBV6-CI-2810: FS, C-DBV6-CI-2800: FS, C-DBV6-EI-2500: FS, C-MAQTA-CI-2800: FS, C-MAQTA-CI-2810: FS, C-MAQTA-EI-2050: FS, C-MAQTA-TE-1020: FS, C-541CR-CI-1020: FS, C-541CR-CI-1030: FS, C-541CR-EI-1040: FS, C-541CR-TE-1000: FS, C-577-CI-1010: FS, C-577-TE- | COM-1000, CCM-PM4510, CCM-PM4620 | COM-1000: FS, CCM-PM4510: FS, CCM-PM4620: FS | 2025-08-30 11:00 | 2025-09-04 11:00
COM-1000 | Not Started | P2543-R01-Oct24..4.4.AB.4 | Ready for Commissioning & As-Built Submission | PRECOM-56-PL-1000, PRECOM-56-EB2-1000, PRECOM-56-G-1000, PRECOM-56-HGHC-1000, PRECOM-56-PR-1000, PRECOM-56-59101-1000, PRECOM-52-0201-1000, PRECOM-56-59801-1000, PRECOM-52-HG01-1000, PRECOM-52-PL-1000, PRECOM-52-0203-1000, PRECOM-56-59802-1000, PRECOM-52-0 | PRECOM-56-PL-1000: FS, PRECOM-56-EB2-1000: FS, PRECOM-56-G-1000: FS, PRECOM-56-HGHC-1000: FS, PRECOM-56-PR-1000: FS, PRECOM-56-59101-1000: FS, PRECOM-52-0201-1000: FS, PRECOM-56-59801-1000: FS, PRECOM-52-HG01-1000: FS, PRECOM-52-PL-1000: FS, PRECOM-52-0203 | CCM-PM4580 | CCM-PM4580: FF |  | 2025-11-03 11:30
PRJ-MI-1000 | Completed | P2543-R01-Oct24..ML | Project Commencement Date (Effective) | ML1000 | ML1000: FS 8 | ML1002 | ML1002: FS 8 |  | 2023-07-09 07:00
C-52-HG01-PL-ME-3000 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.14 | Stringing-Lot2 | C-52-HG01-PL-ME-2800 | C-52-HG01-PL-ME-2800: FS | C-52-HG01-PL-ME-3800, C-52-0203-PL-ME-2800, C-52-0102-PL-ME-2800 | C-52-HG01-PL-ME-3800: SS 2, C-52-0203-PL-ME-2800: SS, C-52-0102-PL-ME-2800: FF | 2024-07-27 07:00 | 2024-11-18 17:00
C-52-HG01-PL-ME-3800 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.15 | Automatic Welding-Lot2 | C-COM-1010, C-52-HG01-PL-ME-3000, C-52-HG01-PL-ME-3600 | C-COM-1010: FS, C-52-HG01-PL-ME-3000: SS 2, C-52-HG01-PL-ME-3600: FS | C-52-HG01-PL-ME-4200, C-52-HG01-PL-ME-4200, C-52-0102-PL-ME-3600, C-52-HG01-PL-CI-2600, C-52-HG01-PL-CI-2600 | C-52-HG01-PL-ME-4200: SS 2, C-52-HG01-PL-ME-4200: FF 2, C-52-0102-PL-ME-3600: FF 6, C-52-HG01-PL-CI-2600: SS 3, C-52-HG01-PL-CI-2600: FF 3 | 2024-09-06 | 2024-11-21 17:00
C-52-HG01-PL-ME-4200 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.16 | NDT-Lot2 | C-52-HG01-PL-ME-4000, C-52-HG01-PL-ME-3800, C-52-HG01-PL-ME-3800 | C-52-HG01-PL-ME-4000: FS, C-52-HG01-PL-ME-3800: SS 2, C-52-HG01-PL-ME-3800: FF 2 | C-52-HG01-PL-ME-4600, C-52-HG01-PL-ME-4600 | C-52-HG01-PL-ME-4600: SS, C-52-HG01-PL-ME-4600: FF 1 | 2024-07-18 | 2024-11-23 17:00
C-52-HG01-PL-ME-4600 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.18 | Ext. Joint Coating-Lot2 | C-52-HG01-PL-ME-4400, C-52-HG01-PL-ME-4200, C-52-HG01-PL-ME-4200 | C-52-HG01-PL-ME-4400: FS, C-52-HG01-PL-ME-4200: SS, C-52-HG01-PL-ME-4200: FF 1 | C-52-HG01-PL-ME-5000 | C-52-HG01-PL-ME-5000: SS 3 | 2024-09-18 | 2024-11-26 17:00
C-52-HG01-PL-CI-2600 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.8 | Trench Excavation-Lot2 | C-52-HG01-PL-CI-2230, C-52-HG01-PL-ME-3800, C-52-HG01-PL-ME-3800, C-52-HG01-PL-CI-2400 | C-52-HG01-PL-CI-2230: FS, C-52-HG01-PL-ME-3800: SS 3, C-52-HG01-PL-ME-3800: FF 3, C-52-HG01-PL-CI-2400: FS | C-52-HG01-PL-CI-2610, C-52-HG01-PL-CI-2610 | C-52-HG01-PL-CI-2610: FF 2, C-52-HG01-PL-CI-2610: SS 2 | 2024-09-19 | 2024-11-25 17:00
C-52-HG01-PL-CI-2610 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.8 | Bedding-Lot2 | C-52-HG01-PL-CI-2600, C-52-HG01-PL-CI-2410, C-52-HG01-PL-CI-2600 | C-52-HG01-PL-CI-2600: FF 2, C-52-HG01-PL-CI-2410: FF, C-52-HG01-PL-CI-2600: SS 2 | C-52-HG01-PL-ME-5000, C-52-HG01-PL-ME-5000 | C-52-HG01-PL-ME-5000: SS 4, C-52-HG01-PL-ME-5000: FF 2 | 2024-09-19 | 2024-11-27 17:00
C-52-HG01-PL-ME-5000 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.25 | Lowering-Lot2 | C-52-HG01-PL-ME-4800, C-52-HG01-PL-CI-2610, C-52-HG01-PL-ME-4600, C-52-HG01-PL-CI-2610 | C-52-HG01-PL-ME-4800: FS, C-52-HG01-PL-CI-2610: SS 4, C-52-HG01-PL-ME-4600: SS 3, C-52-HG01-PL-CI-2610: FF 2 | C-52-HG01-PL-ME-5010, C-52-HG01-PL-ME-5010, C-52-HG01-PL-CA-5600 | C-52-HG01-PL-ME-5010: SS, C-52-HG01-PL-ME-5010: FF, C-52-HG01-PL-CA-5600: FF 7 | 2024-10-19 | 2024-11-29 17:00
C-52-HG01-PL-ME-5010 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.25 | Section Tie-in Welding-Lot2 | C-52-HG01-PL-ME-4810, C-52-HG01-PL-ME-3400, C-52-HG01-PL-ME-5000, C-52-HG01-PL-ME-5000 | C-52-HG01-PL-ME-4810: FS, C-52-HG01-PL-ME-3400: FF 2, C-52-HG01-PL-ME-5000: SS, C-52-HG01-PL-ME-5000: FF | C-52-HG01-PL-ME-5020, C-52-HG01-PL-ME-5020 | C-52-HG01-PL-ME-5020: SS 2, C-52-HG01-PL-ME-5020: FF 2 | 2024-10-08 | 2024-11-30 17:00
C-52-HG01-PL-ME-5020 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.25 | NDT (Tie-in Joint)-Lot2 | C-52-HG01-PL-ME-4820, C-52-HG01-PL-ME-5010, C-52-HG01-PL-ME-5010 | C-52-HG01-PL-ME-4820: FS, C-52-HG01-PL-ME-5010: SS 2, C-52-HG01-PL-ME-5010: FF 2 | C-52-HG01-PL-ME-4610, C-52-HG01-PL-ME-4610 | C-52-HG01-PL-ME-4610: SS 2, C-52-HG01-PL-ME-4610: FF 2 | 2024-10-08 07:00 | 2024-12-05 17:00
C-52-HG01-PL-ME-4610 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.18 | Ext. Joint Coating (Tie-in Joint)-Lot2 | C-52-HG01-PL-ME-4410, C-52-HG01-PL-ME-5020, C-52-HG01-PL-ME-5020 | C-52-HG01-PL-ME-4410: FS, C-52-HG01-PL-ME-5020: SS 2, C-52-HG01-PL-ME-5020: FF 2 | C-52-HG01-PL-ME-5030, C-52-HG01-PL-ME-5030 | C-52-HG01-PL-ME-5030: SS 1, C-52-HG01-PL-ME-5030: FF 1 | 2024-10-08 | 2024-12-07 17:00
C-52-HG01-PL-ME-5030 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.25 | Holiday Testing-Lot2 | C-52-HG01-PL-ME-4830, C-52-HG01-PL-ME-4610, C-52-HG01-PL-ME-4610 | C-52-HG01-PL-ME-4830: FS, C-52-HG01-PL-ME-4610: SS 1, C-52-HG01-PL-ME-4610: FF 1 | C-52-HG01-PL-CI-6200, C-52-HG01-PL-CI-6200 | C-52-HG01-PL-CI-6200: SS 2, C-52-HG01-PL-CI-6200: FF 2 | 2024-10-08 | 2024-12-09 17:00
C-52-HG01-PL-CI-6200 | In Progress | P2543-R01-Oct24..4.3.1.3.2.21.1.24 | Padding -Lot2 | C-52-HG01-PL-CI-6000, C-52-HG01-PL-ME-5030, C-52-HG01-PL-ME-5030, C-52-HG01-PL-CA-5600, C-52-HG01-PL-CA-5600 | C-52-HG01-PL-CI-6000: SS, C-52-HG01-PL-ME-5030: SS 2, C-52-HG01-PL-ME-5030: FF 2, C-52-HG01-PL-CA-5600: FF 2, C-52-HG01-PL-CA-5600: SS 2 | C-52-HG01-PL-CI-6800, C-52-HG01-PL-TE-8200 | C-52-HG01-PL-CI-6800: FF 2, C-52-HG01-PL-TE-8200: FF 1 | 2024-10-21 | 2024-12-12 17:00
C-52-HG01-PL-ME-3400 | Completed | P2543-R01-Oct24..4.3.1.3.2.21.1.13 | Cold Bends-Lot2 | C-52-HG01-PL-ME-3200 | C-52-HG01-PL-ME-3200: FS | C-52-HG01-PL-ME-5010 | C-52-HG01-PL-ME-5010: FF 2 | 2024-07-27 15:48 | 2024-08-29 15:48
C-56-PL-607-CI-1500 | Completed | P2543-R01-Oct24..4.3.1.1.1.12.1.4 | Concrete Works (Impact Wall ) (Deleted) | CTF-SO1030, HE-CS-0230, HE-CS-1250 | CTF-SO1030: FS, HE-CS-0230: FS, HE-CS-1250: SS | C-56-PL-607-CI-1600, C-56-PL-607-CI-2400 | C-56-PL-607-CI-1600: FF, C-56-PL-607-CI-2400: FS | 2024-09-21 07:00 | 2024-10-25
C-56-PL-607-CI-1810 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.10 | Instrument & Telecom Cable Trenching | C-56-PL-607-CI-1800 | C-56-PL-607-CI-1800: FS | C-56-PL-607-EI-2010, C-56-PL-607-TE-1420, C-56-PL-607-TE-1410 | C-56-PL-607-EI-2010: FS, C-56-PL-607-TE-1420: FS, C-56-PL-607-TE-1410: FS | 2025-06-20 11:00 | 2025-07-08 11:00
C-56-G-HT-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.1.3.10.40.5 | Pipe Supports Fabrication & Installation | C-56-G-HT-CI-1600, CTF-SO1050, HS-CN-0690, HM-CS-0120, HE-CS-1490, HM-CS-0110, HE-CS-1430 | C-56-G-HT-CI-1600: FS 45, CTF-SO1050: FS, HS-CN-0690: FS, HM-CS-0120: FS, HE-CS-1490: FS, HM-CS-0110: FS, HE-CS-1430: FS | C-56-G-HT-PI-1200 | C-56-G-HT-PI-1200: FS | 2025-05-10 11:00 | 2025-06-04 11:00
C-56-01HG-PL-CI-1200 | Completed | P2543-R01-Oct24..4.3.1.2.3.12.1.8 | Survey Marking | C-56-01HG-PL-CI-1000 | C-56-01HG-PL-CI-1000: FS | C-56-01HG-PL-CI-1800, C-56-01HG-PL-CI-1600 | C-56-01HG-PL-CI-1800: FS 14, C-56-01HG-PL-CI-1600: FS | 2024-05-03 15:00 | 2024-06-01 15:00
C-56-01HG-PL-CI-1600 | Completed | P2543-R01-Oct24..4.3.1.2.3.12.1.12 | Cut & Fill (@ Non-Sabkha) | C-56-01HG-PL-CI-1200 | C-56-01HG-PL-CI-1200: FS | C-56-01HG-PL-CI-2400, C-56-01HG-PL-CI-2600, ML1569-E02, C-56-01HG-PL-CI-2400, C-56-01HG-PL-CI-2600, C-56-HC01-PL-CI-1400 | C-56-01HG-PL-CI-2400: SS 5, C-56-01HG-PL-CI-2600: FF 5, ML1569-E02: FS, C-56-01HG-PL-CI-2400: FF 5, C-56-01HG-PL-CI-2600: SS 5, C-56-HC01-PL-CI-1400: FF | 2024-07-29 07:30 | 2024-09-26 07:30
C-56-PL-607-CI-2400 | Completed | P2543-R01-Oct24..4.3.1.1.1.12.1.7 | Fire Point SheltersCCOHBSS301 (Deleted) | C-56-PL-607-CI-1500 | C-56-PL-607-CI-1500: FS | C-56-PL-607-CI-2000 | C-56-PL-607-CI-2000: FF | 2024-09-27 | 2024-10-25
C-56-PL-607-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.12 | Installation of Fence Type-4 (Deleted) | C-56-PL-607-CI-3010, HE-CS-0350, HE-CS-0470 | C-56-PL-607-CI-3010: FF 21, HE-CS-0350: FS, HE-CS-0470: FS | C-56-PL-607-CI-2600, C-56-PL-607-CI-2230 | C-56-PL-607-CI-2600: FS, C-56-PL-607-CI-2230: FS | 2025-06-04 11:00 | 2025-07-30 11:00
C-56-PL-607-CI-2230 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.15 | Installation of 6m wide double leaf vehicular access gates (Deleted) | C-56-PL-607-CI-2220 | C-56-PL-607-CI-2220: FS | C-56-PL-607-CI-2240 | C-56-PL-607-CI-2240: FS | 2025-07-30 11:00 | 2025-08-11 11:00
C-56-PL-607-CI-2240 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.1.16 | Installation of 1m wide single leaf vehicular access gates (Deleted) | C-56-PL-607-CI-2230 | C-56-PL-607-CI-2230: FS | C-56-PL-607-CI-2600 | C-56-PL-607-CI-2600: FS | 2025-08-11 11:00 | 2025-08-16 11:00
C-56-PL-607-ME-1200 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.3.2 | Installation of Pig Signaler (607-V-603)CCOHBME318 (Deleted) | C-56-PL-607-ME-1000, C-COM-790, HM-PL-0530, HM-PL-0840, HM-PL-1490, HM-PL-1530, ML1015-B08 | C-56-PL-607-ME-1000: FS, C-COM-790: FS, HM-PL-0530: FF 6, HM-PL-0840: FS, HM-PL-1490: FF 3, HM-PL-1530: FS, ML1015-B08: FS | C-56-PL-607-ME-1400 | C-56-PL-607-ME-1400: FS 10 | 2025-05-09 15:00 | 2025-05-13 15:00
C-56-PL-607-ME-1400 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.3.3 | Installation of Filter PackageCCOHBME328 (Deleted) | C-56-PL-607-ME-1200, C-COM-790, HM-ME-2120, ML1015-B08 | C-56-PL-607-ME-1200: FS 10, C-COM-790: FS, HM-ME-2120: FS, ML1015-B08: FS | C-56-PL-607-ME-1600 | C-56-PL-607-ME-1600: FF | 2025-05-27 07:00 | 2025-05-29 17:00
C-56-PL-607-ME-1600 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.3.4 | Installation of Fire Fighting & Safety EquipmentCCOHBME338 (Deleted) | C-56-PL-607-ME-1400, C-COM-790, HM-ME-1990, HM-ME-2370, ML1015-B08 | C-56-PL-607-ME-1400: FF, C-COM-790: FS, HM-ME-1990: FS, HM-ME-2370: FS, ML1015-B08: FS | C-56-PL-607-PI-1410 | C-56-PL-607-PI-1410: FF | 2025-05-27 07:00 | 2025-05-29 17:00
C-56-PL-607-TE-1400 | Not Started | P2543-R01-Oct24..4.3.1.1.1.12.8.2 | Telephone SystemCCOHBIC221 (Deleted) | C-56-PL-607-EI-1600, HE-TL-0290, HE-TL-0350, HE-TL-0410, HE-TL-0470, HE-TL-0710, HE-TL-0770, HE-TL-0830, HM-EL-0180, HM-EL-610, HM-ME-1290, HM-ME-2270, HM-TL-0040, HS-CN-0290, ML1033-B22 | C-56-PL-607-EI-1600: FS, HE-TL-0290: FS, HE-TL-0350: FS, HE-TL-0410: FS, HE-TL-0470: FS, HE-TL-0710: FS, HE-TL-0770: FS, HE-TL-0830: FS, HM-EL-0180: FS, HM-EL-610: FS, HM-ME-1290: FS, HM-ME-2270: FS, HM-TL-0040: FS, HS-CN-0290: FS, ML1033-B22: FS | C-56-PL-607-TE-1420 | C-56-PL-607-TE-1420: FF | 2025-08-09 11:00 | 2025-08-27 11:00
C-56-EB2-ME-1200 | Not Started | P2543-R01-Oct24..4.3.1.1.2.12.2.2 | Inergen SystemCCOHBME348 (Deleted) | C-56-EB2-ME-1010, HS-CN-0590, ML1015-B08 | C-56-EB2-ME-1010: FS, HS-CN-0590: FS, ML1015-B08: FS | C-56-EB2-EI-2000 | C-56-EB2-EI-2000: FS | 2025-05-21 15:00 | 2025-06-04 15:00
C-56-G-HT-CI-1700 | In Progress | P2543-R01-Oct24..4.3.1.1.3.10.40.4 | Concrete ProtectionCCOHBCS304 (Deleted) | C-56-G-HT-CI-1600, C-56-G-HT-CI-1420 | C-56-G-HT-CI-1600: FF, C-56-G-HT-CI-1420: FF 1 | C-56-G-HT-CI-2600 | C-56-G-HT-CI-2600: FF | 2024-09-27 | 2025-04-12 13:00
C-56-PR-838-ME-1200 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.3.20 | Installation of Pig Signaler (838-V-601) | C-56-PR-838-ME-1100, HM-PL-0840, HM-PL-0530, ML1015-B08, HM-PL-1490, HM-PL-1530 | C-56-PR-838-ME-1100: FS, HM-PL-0840: FS, HM-PL-0530: FS, ML1015-B08: FS, HM-PL-1490: FS, HM-PL-1530: FS | C-56-PR-838-PI-2000 | C-56-PR-838-PI-2000: FS | 2025-05-09 15:00 | 2025-05-15 15:00
C-56-PR-838-ME-1400 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.3.21 | Installation/ Welding of Isolation Joints, Barred Tee & Anchor FlangesCCOH56ME70 (Deleted) | C-56-PR-838-PL-1010, ML1409-D24, ML1015-B08 | C-56-PR-838-PL-1010: SS, ML1409-D24: FS, ML1015-B08: FS | C-56-PR-838-PL-1020 | C-56-PR-838-PL-1020: FS | 2025-07-31 07:00 | 2025-08-04 17:00
C-56-PR-838-EI-1600 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.30 | Installation of RTUCCOH56EL41 (Deleted) | C-56-PR-838-EI-2410 | C-56-PR-838-EI-2410: FS | C-56-PR-838-EI-2040 | C-56-PR-838-EI-2040: FF | 2025-08-01 11:00 | 2025-08-15 11:00
C-52-HG01-PIPEL-5260 | Not Started | P2543-R01-Oct24..4.3.1.3.2.21.3.2.1 | Backfilling & Reinstatement for CP (for Crossings) | C-52-HG01-PL-CA-5240 | C-52-HG01-PL-CA-5240: SS 1 | PRECOM-52-HG01-1000 | PRECOM-52-HG01-1000: FS | 2025-04-18 13:00 | 2025-05-24 11:00
C-56-01HG-PL-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.24 | Trench Excavation | C-56-01HG-PL-CI-2230, C-56-01HG-PL-CI-1800, C-56-01HG-PL-CI-1600, C-56-01HG-PL-CI-1800, C-56-01HG-PL-CI-2230, C-56-01HG-PL-CI-1400, C-56-01HG-PL-CI-1400, C-56-01HG-PL-CI-1600, C-56-01HG-PL-ME-3800, C-56-01HG-PL-ME-3800 | C-56-01HG-PL-CI-2230: SS 3, C-56-01HG-PL-CI-1800: SS 5, C-56-01HG-PL-CI-1600: FF 5, C-56-01HG-PL-CI-1800: FF, C-56-01HG-PL-CI-2230: FF, C-56-01HG-PL-CI-1400: SS, C-56-01HG-PL-CI-1400: FF, C-56-01HG-PL-CI-1600: SS 5, C-56-01HG-PL-ME-3800: SS 3, C-56-01HG-PL | C-56-01HG-PL-CI-2610, C-56-01HG-PL-CI-2610 | C-56-01HG-PL-CI-2610: SS 3, C-56-01HG-PL-CI-2610: FF 3 | 2025-01-15 08:30 | 2025-02-07 08:30
C-56-01HG-PL-CI-2610 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.24 | Bedding | C-56-01HG-PL-CI-2600, C-56-01HG-PL-CI-2600 | C-56-01HG-PL-CI-2600: SS 3, C-56-01HG-PL-CI-2600: FF 3 | C-56-01HG-PL-ME-4800, C-56-01HG-PL-ME-5000 | C-56-01HG-PL-ME-4800: FF 5, C-56-01HG-PL-ME-5000: FF 5 | 2025-01-18 08:30 | 2025-02-11 08:30
C-56-01HG-PL-ME-3000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.27 | Stringing (KP 21.3 to HGCP) | C-56-01HG-PL-CI-2230, HM-PL-0110 | C-56-01HG-PL-CI-2230: FS, HM-PL-0110: SS 16 | C-56-01HG-CME01-1020, C-56-01HG-PL-ME-3800, C-56-01HG-PL-ME-3800, C-56-01HG-PL-ME-2800 | C-56-01HG-CME01-1020: SS 14, C-56-01HG-PL-ME-3800: SS 2, C-56-01HG-PL-ME-3800: FF 2, C-56-01HG-PL-ME-2800: FS | 2024-12-18 07:00 | 2025-01-10 17:00
C-56-01HG-PL-ME-3400 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.34 | Cold Bends | C-56-01HG-PL-ME-4800, C-56-01HG-PL-ME-3200, C-56-01HG-PL-ME-5000, C-56-01HG-PL-ME-5000, C-56-01HG-PL-ME-4800 | C-56-01HG-PL-ME-4800: SS, C-56-01HG-PL-ME-3200: FS, C-56-01HG-PL-ME-5000: SS, C-56-01HG-PL-ME-5000: FF, C-56-01HG-PL-ME-4800: FF | C-56-01HG-PL-ME-5010 | C-56-01HG-PL-ME-5010: FF | 2025-04-19 14:30 | 2025-06-14 12:30
C-56-01HG-PL-ME-3800 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.31 | Automatic Welding | C-56-01HG-PL-ME-3000, C-56-01HG-PL-ME-3000, HM-PL-0880, C-COM-1010, C-52-0304-PL-ME-3600 | C-56-01HG-PL-ME-3000: SS 2, C-56-01HG-PL-ME-3000: FF 2, HM-PL-0880: FS, C-COM-1010: FS, C-52-0304-PL-ME-3600: FS | C-56-01HG-PL-ME-4200, C-56-01HG-PL-ME-4200, C-56-01HG-PL-CI-2600, C-56-01HG-PL-CI-2600, ML1589-E04, C-56-01HG-PL-ME-3600 | C-56-01HG-PL-ME-4200: SS 1, C-56-01HG-PL-ME-4200: FF, C-56-01HG-PL-CI-2600: SS 3, C-56-01HG-PL-CI-2600: FF 3, ML1589-E04: FS, C-56-01HG-PL-ME-3600: FS | 2025-01-10 07:00 | 2025-02-04 08:30
C-56-01HG-PL-ME-4200 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.32 | NDT | C-56-01HG-PL-ME-3600, C-56-01HG-PL-ME-3800, C-56-01HG-PL-ME-3600, C-56-01HG-PL-ME-3800, C-56-01HG-PL-ME-4000 | C-56-01HG-PL-ME-3600: SS 1, C-56-01HG-PL-ME-3800: SS 1, C-56-01HG-PL-ME-3600: FF, C-56-01HG-PL-ME-3800: FF, C-56-01HG-PL-ME-4000: FS | C-56-01HG-PL-ME-4600, C-56-01HG-PL-ME-4600 | C-56-01HG-PL-ME-4600: SS 2, C-56-01HG-PL-ME-4600: FF 1 | 2025-03-07 08:30 | 2025-04-14 14:30
C-56-01HG-PL-ME-4600 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.39 | Ext. Joint Coating | C-56-01HG-PL-ME-4000, C-56-01HG-PL-ME-4200, C-56-01HG-PL-ME-4400, C-56-01HG-PL-ME-4000, C-56-01HG-PL-ME-4200 | C-56-01HG-PL-ME-4000: SS 2, C-56-01HG-PL-ME-4200: SS 2, C-56-01HG-PL-ME-4400: FS, C-56-01HG-PL-ME-4000: FF, C-56-01HG-PL-ME-4200: FF 1 | C-56-01HG-PL-ME-5000, C-56-01HG-PL-ME-5000 | C-56-01HG-PL-ME-5000: SS 3, C-56-01HG-PL-ME-5000: FF | 2025-03-09 12:30 | 2025-04-16 14:30
C-56-01HG-PL-ME-4610 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.39 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-PL-ME-4820, C-56-01HG-PL-ME-4410, C-56-01HG-PL-ME-4820, C-56-01HG-PL-ME-5020, C-56-01HG-PL-ME-5020 | C-56-01HG-PL-ME-4820: SS 1, C-56-01HG-PL-ME-4410: FS, C-56-01HG-PL-ME-4820: FF, C-56-01HG-PL-ME-5020: SS 2, C-56-01HG-PL-ME-5020: FF 2 | C-56-01HG-PL-ME-5030, C-56-01HG-PL-ME-5030 | C-56-01HG-PL-ME-5030: SS 1, C-56-01HG-PL-ME-5030: FF | 2025-04-29 13:00 | 2025-06-24 11:00
C-56-01HG-PL-ME-5000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.38 | Lowering | C-56-01HG-PL-CI-2410, C-56-01HG-PL-ME-4400, C-56-01HG-PL-CI-2610, C-56-01HG-PL-ME-4600, C-56-01HG-PL-ME-4400, C-56-01HG-PL-ME-4600, C-56-01HG-PL-ME-4800, ML1569-E02, ML1149-A07, ML1139-A06, HS-CN-0090 | C-56-01HG-PL-CI-2410: FF 5, C-56-01HG-PL-ME-4400: SS 3, C-56-01HG-PL-CI-2610: FF 5, C-56-01HG-PL-ME-4600: SS 3, C-56-01HG-PL-ME-4400: FF, C-56-01HG-PL-ME-4600: FF, C-56-01HG-PL-ME-4800: FS, ML1569-E02: FS, ML1149-A07: FF, ML1139-A06: FF, HS-CN-0090: FF | C-56-01HG-PL-ME-5010, C-56-01HG-PL-ME-3400, C-56-01HG-PL-ME-3400, ML1609-E06 | C-56-01HG-PL-ME-5010: SS, C-56-01HG-PL-ME-3400: SS, C-56-01HG-PL-ME-3400: FF, ML1609-E06: FS | 2025-04-14 14:30 | 2025-06-14 12:30
C-56-01HG-PL-ME-5010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.38 | Section Tie-in Welding | C-56-01HG-PL-ME-5000, C-56-01HG-CMA01-1030, C-56-01HG-CMA02-1030, C-56-01HG-CMA03-1030, C-56-01HG-CMA04-1030, C-56-01HG-CMA05-1030, C-56-01HG-CMA06-1030, C-56-01HG-CMA07-1030, C-56-01HG-CMA08-1030, C-56-01HG-CMA09-1030, C-56-01HG-CMA10-1030, C-56-01HG-CMA1 | C-56-01HG-PL-ME-5000: SS, C-56-01HG-CMA01-1030: FF 1, C-56-01HG-CMA02-1030: FF 1, C-56-01HG-CMA03-1030: FF 1, C-56-01HG-CMA04-1030: FF 1, C-56-01HG-CMA05-1030: FF 1, C-56-01HG-CMA06-1030: FF 1, C-56-01HG-CMA07-1030: FF 1, C-56-01HG-CMA08-1030: FF 1, C-56-0 | C-56-01HG-PL-ME-5020, C-56-01HG-PL-CI-7200, C-56-01HG-PL-ME-5020 | C-56-01HG-PL-ME-5020: SS 2, C-56-01HG-PL-CI-7200: FF, C-56-01HG-PL-ME-5020: FF 2 | 2025-04-24 13:00 | 2025-06-19 11:00
C-56-01HG-PL-ME-5020 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.38 | NDT (Tie-in Joint) | C-56-01HG-PL-ME-5010, C-56-01HG-PL-ME-5010, C-56-01HG-PL-ME-4820 | C-56-01HG-PL-ME-5010: SS 2, C-56-01HG-PL-ME-5010: FF 2, C-56-01HG-PL-ME-4820: FS | C-56-01HG-PL-ME-4610, C-56-01HG-PL-ME-4610 | C-56-01HG-PL-ME-4610: SS 2, C-56-01HG-PL-ME-4610: FF 2 | 2025-04-26 13:00 | 2025-06-21 11:00
C-56-01HG-PL-ME-5030 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.38 | Holiday Testing | C-56-01HG-PL-ME-4410, C-56-01HG-PL-ME-4610, C-56-01HG-PL-ME-4410, C-56-01HG-PL-ME-4610, C-56-01HG-PL-ME-4830 | C-56-01HG-PL-ME-4410: SS 1, C-56-01HG-PL-ME-4610: SS 1, C-56-01HG-PL-ME-4410: FF, C-56-01HG-PL-ME-4610: FF, C-56-01HG-PL-ME-4830: FS | C-56-01HG-PL-CI-6200, C-56-01HG-PL-CI-6200, C-56-01HG-PL-CA-5800, C-56-01HG-PL-CA-5800 | C-56-01HG-PL-CI-6200: SS 2, C-56-01HG-PL-CI-6200: FF 2, C-56-01HG-PL-CA-5800: SS, C-56-01HG-PL-CA-5800: FF | 2025-05-03 13:00 | 2025-06-30 11:00
C-56-01HG-PL-CI-6200 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.41 | Padding | C-56-01HG-PL-ME-4830, C-56-01HG-PL-ME-5030, C-56-01HG-PL-ME-4830, C-56-01HG-PL-ME-5030, C-56-01HG-PL-CI-6000, C-56-01HG-PL-CA-5800, C-56-01HG-PL-CA-5800, C-56-01HG-CME09-1150 | C-56-01HG-PL-ME-4830: SS 1, C-56-01HG-PL-ME-5030: SS 2, C-56-01HG-PL-ME-4830: FF, C-56-01HG-PL-ME-5030: FF 2, C-56-01HG-PL-CI-6000: SS, C-56-01HG-PL-CA-5800: SS 2, C-56-01HG-PL-CA-5800: FF 2, C-56-01HG-CME09-1150: FF 7 | C-56-01HG-PL-ME-7400, PRECOM-56-HGHC-1000, C-56-01HG-PL-CI-6600, C-56-01HG-PL-CI-7000, C-56-01HG-PL-CI-7000, C-56-01HG-PL-CI-6600, C-56-01HG-PL-TE-8400, C-56-01HG-PL-TE-8400 | C-56-01HG-PL-ME-7400: FS, PRECOM-56-HGHC-1000: FS, C-56-01HG-PL-CI-6600: SS 2, C-56-01HG-PL-CI-7000: SS 5, C-56-01HG-PL-CI-7000: FF, C-56-01HG-PL-CI-6600: FF 2, C-56-01HG-PL-TE-8400: SS 5, C-56-01HG-PL-TE-8400: FF | 2025-05-07 08:00 | 2025-07-02 11:00
C-56-01HG-PL-CA-5420 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.40 | Installation of Test Post for Crossing | C-56-01HG-CMA01-1070, C-56-01HG-CMA02-1070, C-56-01HG-CMA03-1070, C-56-01HG-CMA04-1070, C-56-01HG-CMA05-1070, C-56-01HG-CMA06-1070, C-56-01HG-CMA07-1070, C-56-01HG-CMA08-1070, C-56-01HG-CMA09-1070, C-56-01HG-CMA10-1070, C-56-01HG-CMA11-1070, C-56-01HG-CMA1 | C-56-01HG-CMA01-1070: SS, C-56-01HG-CMA02-1070: FF, C-56-01HG-CMA03-1070: FF, C-56-01HG-CMA04-1070: FF, C-56-01HG-CMA05-1070: FF, C-56-01HG-CMA06-1070: FF, C-56-01HG-CMA07-1070: FF, C-56-01HG-CMA08-1070: FF, C-56-01HG-CMA09-1070: FF, C-56-01HG-CMA10-1070: | C-56-01HG-PL-CA-5430 | C-56-01HG-PL-CA-5430: SS 1 | 2025-07-17 15:00 | 2025-08-21 15:00
C-56-01HG-PL-CA-5430 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.40 | Installation of CP JB's | C-56-01HG-PL-CA-5420, C-56-01HG-PL-CA-5230 | C-56-01HG-PL-CA-5420: SS 1, C-56-01HG-PL-CA-5230: FS | C-56-01HG-PL-CA-5440 | C-56-01HG-PL-CA-5440: SS 1 | 2025-07-18 15:00 | 2025-08-22 15:00
C-56-01HG-PL-CA-5440 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.40 | Installation of CP TR | C-56-01HG-PL-CA-5430, C-56-01HG-PL-CA-5240 | C-56-01HG-PL-CA-5430: SS 1, C-56-01HG-PL-CA-5240: FS | C-56-01HG-PL-CA-5450 | C-56-01HG-PL-CA-5450: FS | 2025-07-19 15:00 | 2025-08-23 15:00
C-56-01HG-PL-CA-5450 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.40 | CIP/DCVG Survey (Pre-Com) | C-56-01HG-PL-CA-5440, C-56-01HG-PL-CA-5620, C-56-01HG-PL-CA-5250, C-56-01HG-PL-CA-5820 | C-56-01HG-PL-CA-5440: FS, C-56-01HG-PL-CA-5620: FS, C-56-01HG-PL-CA-5250: FS, C-56-01HG-PL-CA-5820: FS | PRECOM-56-HGHC-1000 | PRECOM-56-HGHC-1000: FS | 2025-08-23 15:00 | 2025-08-27 15:00
C-56-01HG-PL-CA-5800 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.46 | Installation of Temp. Anode | C-56-01HG-PL-ME-5030, C-56-01HG-PL-ME-5030 | C-56-01HG-PL-ME-5030: SS, C-56-01HG-PL-ME-5030: FF | C-56-01HG-PL-CA-5810, C-56-01HG-PL-CA-5810, C-56-01HG-PL-CI-6200, C-56-01HG-PL-CI-6200 | C-56-01HG-PL-CA-5810: SS, C-56-01HG-PL-CA-5810: FF, C-56-01HG-PL-CI-6200: SS 2, C-56-01HG-PL-CI-6200: FF 2 | 2025-05-03 13:00 | 2025-06-30 11:00
C-56-01HG-PL-CA-5810 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.46 | Installation of CP Test Post | C-56-01HG-PL-CA-5800, C-56-01HG-PL-CA-5800, C-56-01HG-PL-CA-5610 | C-56-01HG-PL-CA-5800: SS, C-56-01HG-PL-CA-5800: FF, C-56-01HG-PL-CA-5610: FS | C-56-01HG-PL-CA-5820 | C-56-01HG-PL-CA-5820: FS | 2025-05-03 13:00 | 2025-06-30 11:00
C-56-01HG-PL-CA-5820 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.46 | Glanding & Termination of Temp. CP S/m | C-56-01HG-PL-CA-5810, C-56-01HG-PL-CA-5620 | C-56-01HG-PL-CA-5810: FS, C-56-01HG-PL-CA-5620: FS | C-56-01HG-PL-CA-5450 | C-56-01HG-PL-CA-5450: FS | 2025-06-30 11:00 | 2025-07-02 11:00
C-52-HG01-PL-CI-7820 | Not Started | P2543-R01-Oct24..4.3.2.3.10.8.2.6 | Installation of Crash Barriers (If any) (Deleted SOW) | C-52-HG01-PL-CI-7800 | C-52-HG01-PL-CI-7800: FF 1 | PRECOM-52-HG01-1000, CCM-PM4520, CCM-PM4530, CCM-PM4540, ML1090 | PRECOM-52-HG01-1000: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS, ML1090: FS | 2024-12-17 07:00 | 2025-03-18 13:00
C-56-01HG-PL-CI-6400 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.33 | Backfilling from BVS-01 to KP 21.3 | C-56-01HG-PL-CI-6000, C-56-01HG-PL-CI-6000 | C-56-01HG-PL-CI-6000: SS 2, C-56-01HG-PL-CI-6000: FF 2 | C-56-01HG-PL-CI-6800, C-56-01HG-PL-CI-6800 | C-56-01HG-PL-CI-6800: SS 2, C-56-01HG-PL-CI-6800: FF 2 | 2025-03-23 09:00 | 2025-05-15 11:00
C-56-01HG-PL-CI-6600 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.43 | Backfilling from KP 21.3 to HGCP | C-56-01HG-PL-CI-6200, C-56-01HG-PL-CI-6200 | C-56-01HG-PL-CI-6200: SS 2, C-56-01HG-PL-CI-6200: FF 2 | C-56-01HG-PL-CI-7000, C-56-01HG-PL-CI-7000 | C-56-01HG-PL-CI-7000: SS, C-56-01HG-PL-CI-7000: FF | 2025-05-15 11:00 | 2025-07-04 11:00
C-52-0203-PIPEL-5260 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.3.1.5 | Backfilling for CP (for Crossings) | C-52-0203-PL-CA-5220 | C-52-0203-PL-CA-5220: SS 4 | C-52-0203-PL-CA-5240, ML1080 | C-52-0203-PL-CA-5240: FS, ML1080: FS | 2024-12-23 07:00 | 2025-01-13 17:00
C-56-01HG-PL-CI-7000 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.44 | Gatch Laying & Levelling | C-56-01HG-PL-CI-6000, C-56-01HG-CMA01-1070, C-56-01HG-CMA02-1070, C-56-01HG-CMA03-1070, C-56-01HG-CMA04-1070, C-56-01HG-CMA05-1070, C-56-01HG-CMA06-1070, C-56-01HG-CMA07-1070, C-56-01HG-CMA08-1070, C-56-01HG-CMA09-1070, C-56-01HG-CMA10-1070, C-56-01HG-CMA1 | C-56-01HG-PL-CI-6000: SS 5, C-56-01HG-CMA01-1070: FF 1, C-56-01HG-CMA02-1070: FF 1, C-56-01HG-CMA03-1070: FF 1, C-56-01HG-CMA04-1070: FF 1, C-56-01HG-CMA05-1070: FF 1, C-56-01HG-CMA06-1070: FF 1, C-56-01HG-CMA07-1070: FF 1, C-56-01HG-CMA08-1070: FF 1, C-56 | C-56-01HG-PL-CI-7010, C-56-01HG-PL-CI-7010 | C-56-01HG-PL-CI-7010: SS 10, C-56-01HG-PL-CI-7010: FF | 2025-05-20 11:00 | 2025-07-07 11:00
C-56-01HG-PL-CI-7010 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.1.44 | Gatch Compaction | C-56-01HG-PL-CI-7000, C-56-01HG-PL-CI-6810, C-56-01HG-PL-TE-8410, C-56-01HG-PL-CI-7000, C-56-01HG-PL-TE-8210 | C-56-01HG-PL-CI-7000: SS 10, C-56-01HG-PL-CI-6810: FS, C-56-01HG-PL-TE-8410: FF, C-56-01HG-PL-CI-7000: FF, C-56-01HG-PL-TE-8210: FF | C-56-01HG-PL-CI-7800, PRECOM-56-HGHC-1000, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CI-7200 | C-56-01HG-PL-CI-7800: SS 1, PRECOM-56-HGHC-1000: FS, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CI-7200: FF | 2025-06-02 15:00 | 2025-07-19 15:00
C-52-0304-PIPEL-5260 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.3.2.5 | Backfilling & Reinstatement for CP (for Crossings) | C-52-0304-PL-CA-5220 | C-52-0304-PL-CA-5220: SS 3 | C-52-0304-PL-CA-5240, ML1080 | C-52-0304-PL-CA-5240: FF, ML1080: FS | 2025-01-02 07:00 | 2025-02-13 17:00
C-52-0102-PIPEL-5260 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.4.3.1 | Backfilling & Reinstatement for CP (for Crossings) | C-52-0102-PL-CA-5220 | C-52-0102-PL-CA-5220: SS | C-52-0102-PL-CA-5240 | C-52-0102-PL-CA-5240: FS | 2024-12-17 07:00 | 2025-02-08 17:00
C-52-0506-PL-CI-1900 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.10 | Sabka ROW/Grading | C-52-0506-PL-CI-1000, C-52-0506-PL-CI-1800 | C-52-0506-PL-CI-1000: SS 3, C-52-0506-PL-CI-1800: FS 30 | C-52-0506-PL-ME-2800, C-52-0506-PL-CI-1600 | C-52-0506-PL-ME-2800: SS 5, C-52-0506-PL-CI-1600: FS | 2025-01-21 11:00 | 2025-02-25 11:00
C-52-0506-PL-CI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.8 | Cut & Fill (@ Non-Sabkha) | C-52-0506-PL-CI-1900, C-52-0506-PL-CI-1400 | C-52-0506-PL-CI-1900: FS, C-52-0506-PL-CI-1400: FS | C-52-0506-PL-CI-2400, C-52-0506-PL-ME-2800, ML1669-E12, C-52-0506-PL-ME-2800 | C-52-0506-PL-CI-2400: FS, C-52-0506-PL-ME-2800: FF 5, ML1669-E12: FS, C-52-0506-PL-ME-2800: SS 3 | 2025-02-25 11:00 | 2025-04-10 17:00
C-52-0506-PL-CI-6400 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.1.24 | Backfilling | C-52-0506-PL-CI-6000, C-52-0506-PL-CI-6000, C-52-0506-PL-TE-8200, C-52-0506-PL-TE-8200 | C-52-0506-PL-CI-6000: SS 5, C-52-0506-PL-CI-6000: FF 5, C-52-0506-PL-TE-8200: FF 5, C-52-0506-PL-TE-8200: SS 5 | C-52-0506-PL-CI-6800, C-52-0506-PL-CI-6800 | C-52-0506-PL-CI-6800: FF 8, C-52-0506-PL-CI-6800: SS 8 | 2025-05-22 15:00 | 2025-07-21 15:00
C-52-0506-PIPEL-5260 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.4.3.1 | Backfilling & Reinstatement for CP (for Crossings) | C-52-0506-PL-CA-5220 | C-52-0506-PL-CA-5220: FF 1 | C-52-0506-PL-CA-5240 | C-52-0506-PL-CA-5240: FF | 2025-04-24 15:30 | 2025-06-23 13:30
C-52-0405-PL-CI-6400 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.1.23 | Backfilling | C-52-0405-PL-CI-6000, C-52-0405-PL-TE-8200 | C-52-0405-PL-CI-6000: FF 5, C-52-0405-PL-TE-8200: FF 2 | C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6810, C-52-0405-PL-CI-6800, C-52-0405-FENCE-1010, C-52-0405-FENCE-1010 | C-52-0405-PL-CI-6800: SS 7, C-52-0405-PL-CI-6810: FF 7, C-52-0405-PL-CI-6800: FF 7, C-52-0405-FENCE-1010: SS 21, C-52-0405-FENCE-1010: FF | 2025-05-07 08:00 | 2025-07-05 11:00
C-52-0405-PIPEL-5260 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.3.3.1 | Backfilling & Reinstatement for CP (for Crossings) | C-52-0405-PL-CA-5220 | C-52-0405-PL-CA-5220: FF | C-52-0405-PL-CA-5240 | C-52-0405-PL-CA-5240: FF | 2025-03-23 09:00 | 2025-06-10 11:00
C-56-01HG-PL-TE-8400 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.3.2 | FO - Cable Pulling/ Laying | C-56-01HG-PL-CI-6000, C-56-01HG-CMA01-1070, C-56-01HG-CMA02-1070, C-56-01HG-CMA03-1070, C-56-01HG-CMA04-1070, C-56-01HG-CMA05-1070, C-56-01HG-CMA06-1070, C-56-01HG-CMA07-1070, C-56-01HG-CMA08-1070, C-56-01HG-CMA09-1070, C-56-01HG-CMA10-1070, C-56-01HG-CMA1 | C-56-01HG-PL-CI-6000: SS 5, C-56-01HG-CMA01-1070: FF, C-56-01HG-CMA02-1070: FF, C-56-01HG-CMA03-1070: FF, C-56-01HG-CMA04-1070: FF, C-56-01HG-CMA05-1070: FF, C-56-01HG-CMA06-1070: FF, C-56-01HG-CMA07-1070: FF, C-56-01HG-CMA08-1070: FF, C-56-01HG-CMA09-1070 | C-56-01HG-PL-TE-8410 | C-56-01HG-PL-TE-8410: FS | 2025-06-09 15:00 | 2025-07-17 15:00
C-56-01HG-PL-TE-8410 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.3.2 | Termination/Splicing @ BVS | C-56-01HG-PL-TE-8400, C-56-01HG-PL-TE-8210 | C-56-01HG-PL-TE-8400: FS, C-56-01HG-PL-TE-8210: FS | PRECOM-56-HGHC-1000, C-56-01HG-PL-CI-7010 | PRECOM-56-HGHC-1000: FS, C-56-01HG-PL-CI-7010: FF | 2025-07-17 15:00 | 2025-07-19 15:00
C-52-06CR-PL-CI-6400 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.1.24 | Backfilling | C-52-06CR-PL-CI-6000, C-52-06CR-PL-CI-6000, C-52-06CR-PL-TE-8200 | C-52-06CR-PL-CI-6000: SS 1, C-52-06CR-PL-CI-6000: FF 1, C-52-06CR-PL-TE-8200: FF 1 | C-52-06CR-PL-CI-6800, C-52-06CR-PL-CI-6800 | C-52-06CR-PL-CI-6800: FF 22, C-52-06CR-PL-CI-6800: SS 22 | 2025-07-14 11:30 | 2025-08-18 11:30
C-52-06CR-PIPEL-5260 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.3.1.1 | Backfilling & Reinstatement for CP (for Crossings) | C-52-06CR-PL-CA-5220 | C-52-06CR-PL-CA-5220: FF | C-52-06CR-PL-CA-5240 | C-52-06CR-PL-CA-5240: FF 1 | 2025-07-08 07:30 | 2025-08-12 07:30
C-56-HC01-PL-CI-2600 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.14 | Trench Excavation | C-56-HC01-PL-CI-1400, C-56-HC01-PL-CI-1800, C-56-HC01-PL-CI-1800, C-56-HC01-PL-CI-1400, C-56-HC01-PL-ME-3600, C-56-HC01-PL-ME-3600 | C-56-HC01-PL-CI-1400: FF 3, C-56-HC01-PL-CI-1800: SS 7, C-56-HC01-PL-CI-1800: FF, C-56-HC01-PL-CI-1400: SS 3, C-56-HC01-PL-ME-3600: FF 3, C-56-HC01-PL-ME-3600: SS 3 | C-56-HC01-PL-CI-2610, C-56-HC01-PL-CI-2610 | C-56-HC01-PL-CI-2610: SS 4, C-56-HC01-PL-CI-2610: FF 4 | 2025-03-28 10:30 | 2025-05-03 14:30
C-56-HC01-PL-CI-2610 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.14 | Bedding | C-56-HC01-PL-CI-2600, C-56-HC01-PL-CI-2410, C-56-HC01-PL-CI-2600 | C-56-HC01-PL-CI-2600: SS 4, C-56-HC01-PL-CI-2410: SS, C-56-HC01-PL-CI-2600: FF 4 | C-56-HC01-PL-ME-5000 | C-56-HC01-PL-ME-5000: FF 5 | 2025-04-09 14:30 | 2025-05-13 12:30
C-52-PR-839-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.12 | Fences & Gates Construction | C-52-PR-839-CI-1070, HE-CS-0350, HE-CS-0470 | C-52-PR-839-CI-1070: FS, HE-CS-0350: FS, HE-CS-0470: FS | C-52-PR-839-CI-2600, C-52-PR-839-CI-3200 | C-52-PR-839-CI-2600: FS, C-52-PR-839-CI-3200: FS | 2025-05-03 13:00 | 2025-07-08 11:00
C-52-PR-839-CI-2400 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.14 | Fire Point Shelters | C-52-PR-839-CI-2000, HM-CS-0110 | C-52-PR-839-CI-2000: FS, HM-CS-0110: FS | C-52-PR-839-CI-3200 | C-52-PR-839-CI-3200: FS | 2025-04-07 13:00 | 2025-04-21 13:00
C-52-PR-839-CI-3200 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.1.15 | Finishing | C-52-PR-839-CI-2400, C-52-PR-839-CI-2600, C-52-PR-839-CI-2220, HM-CS-0110 | C-52-PR-839-CI-2400: FS, C-52-PR-839-CI-2600: FS, C-52-PR-839-CI-2220: FS, HM-CS-0110: FS | PRECOM-52-PR-1000 | PRECOM-52-PR-1000: FS | 2025-08-26 13:00 | 2025-09-10 13:00
C-56-HC01-PL-ME-4600 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.24 | Ext. Joint Coating | C-56-HC01-PL-ME-4000, C-56-HC01-PL-ME-4000, C-56-HC01-PL-ME-4400 | C-56-HC01-PL-ME-4000: SS 2, C-56-HC01-PL-ME-4000: FF, C-56-HC01-PL-ME-4400: FS | C-56-HC01-PL-ME-5000, C-56-HC01-PL-ME-5000 | C-56-HC01-PL-ME-5000: SS 3, C-56-HC01-PL-ME-5000: FF 3 | 2025-05-05 15:30 | 2025-06-10 12:30
C-56-HC01-PL-ME-4610 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.24 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-PL-ME-4820, C-56-HC01-PL-ME-4820, C-56-HC01-PL-ME-4410, C-56-HC01-PL-ME-5020, C-56-HC01-PL-ME-5020 | C-56-HC01-PL-ME-4820: SS 1, C-56-HC01-PL-ME-4820: FF, C-56-HC01-PL-ME-4410: SS, C-56-HC01-PL-ME-5020: SS 4, C-56-HC01-PL-ME-5020: FF 4 | C-56-HC01-PL-ME-5030, C-56-HC01-PL-ME-5030 | C-56-HC01-PL-ME-5030: SS 4, C-56-HC01-PL-ME-5030: FF 4 | 2025-05-30 12:30 | 2025-06-25 12:30
C-52-PR-839-ME-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.3.3 | Installation of Pig Signaler (839-V-101) | C-52-PR-839-ME-1100, ML1015-B08, HM-PL-0840, HM-PL-0530, HM-PL-1490, HM-PL-1530 | C-52-PR-839-ME-1100: FS, ML1015-B08: FS, HM-PL-0840: FS, HM-PL-0530: FS, HM-PL-1490: FS, HM-PL-1530: FS | C-52-PR-839-PI-2000, ML1749-E20, ML1859-E31 | C-52-PR-839-PI-2000: FS, ML1749-E20: FS, ML1859-E31: FS | 2025-05-09 15:00 | 2025-05-14 15:00
C-52-PR-839-ME-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.4.1.22.3.4 | Installation of Fire Fighting & Safety Equipment | C-52-PR-839-EI-2410, HM-ME-1990, ML1015-B08, HM-ME-2370 | C-52-PR-839-EI-2410: FS, HM-ME-1990: FS, ML1015-B08: FS, HM-ME-2370: FS | C-52-PR-839-EI-2050, ML1749-E20, ML1859-E31 | C-52-PR-839-EI-2050: FS, ML1749-E20: FS, ML1859-E31: FS | 2025-09-16 07:00 | 2025-09-19 17:00
C-52-EB1-ME-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.4.2.22.2.2 | Inergen System | C-52-EB1-ME-1010, HM-ME-1830 | C-52-EB1-ME-1010: FS, HM-ME-1830: FS | C-52-EB1-EI-2000 | C-52-EB1-EI-2000: FS | 2025-06-12 11:00 | 2025-07-15 11:00
C-52-D-HT-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.1.3 | Pipe Supports Fabrication & Installation | C-52-D-HT-CI-1600, C-52-D-HT-CI-1600, HE-CS-1430, HS-CN-0690, HM-CS-0110, HM-CS-0120, HE-CS-1490 | C-52-D-HT-CI-1600: SS 6, C-52-D-HT-CI-1600: FF, HE-CS-1430: FS, HS-CN-0690: FS, HM-CS-0110: FS, HM-CS-0120: FS, HE-CS-1490: FS | C-52-D-HT-PI-1200 | C-52-D-HT-PI-1200: FS | 2025-04-26 13:00 | 2025-05-12 11:00
C-52-D-HT-CI-1700 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.1.4 | Concrete Protection | C-52-D-HT-CI-1600, C-52-D-HT-CI-1480, HM-CS-0050 | C-52-D-HT-CI-1600: FS, C-52-D-HT-CI-1480: FF 7, HM-CS-0050: FS | C-52-D-HT-CI-2220 | C-52-D-HT-CI-2220: FS | 2025-06-10 11:00 | 2025-06-24 11:00
C-52-D-HT-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.1.5 | Fences & Gates Construction | C-52-D-HT-CI-1700, HE-CS-0470, HE-CS-0350 | C-52-D-HT-CI-1700: FS, HE-CS-0470: FS, HE-CS-0350: FS | C-52-D-HT-CI-3000 | C-52-D-HT-CI-3000: FS | 2025-06-24 11:00 | 2025-08-20 11:00
C-56-HC01-PL-ME-5000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 | Lowering | C-56-HC01-PL-CI-2410, C-56-HC01-PL-ME-4400, C-56-HC01-PL-CI-2610, C-56-HC01-PL-ME-4600, C-56-HC01-PL-ME-4400, C-56-HC01-PL-ME-4600, C-56-HC01-PL-ME-4800, ML1569-E02 | C-56-HC01-PL-CI-2410: FF 5, C-56-HC01-PL-ME-4400: SS 3, C-56-HC01-PL-CI-2610: FF 5, C-56-HC01-PL-ME-4600: SS 3, C-56-HC01-PL-ME-4400: FF, C-56-HC01-PL-ME-4600: FF 3, C-56-HC01-PL-ME-4800: SS 3, ML1569-E02: FS | C-56-HC01-PL-ME-5010, C-56-HC01-PL-ME-3200, C-56-HC01-PL-ME-5010, ML1609-E06 | C-56-HC01-PL-ME-5010: SS 2, C-56-HC01-PL-ME-3200: FF, C-56-HC01-PL-ME-5010: FF 2, ML1609-E06: FS | 2025-05-19 12:30 | 2025-06-13 12:30
C-56-HC01-PL-ME-5010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 | Section Tie-in Welding | C-56-HC01-PL-ME-5000, C-56-HC01-CMA02-1030, C-56-HC01-CMA03-1030, C-56-HC01-CMA13-1030, C-56-HC01-CMA09-1030, C-56-HC01-CMA11-1030, C-56-HC01-CMA14-1030, C-56-HC01-CMA15-1030, C-56-HC01-CMA22-1030, C-56-HC01-CMA04-1030, C-56-HC01-CMA16-1030, C-56-HC01-CMA1 | C-56-HC01-PL-ME-5000: SS 2, C-56-HC01-CMA02-1030: FF 1, C-56-HC01-CMA03-1030: FF 1, C-56-HC01-CMA13-1030: FF 1, C-56-HC01-CMA09-1030: FF 1, C-56-HC01-CMA11-1030: FF 1, C-56-HC01-CMA14-1030: FF 1, C-56-HC01-CMA15-1030: FF 1, C-56-HC01-CMA22-1030: FF 1, C-56 | C-56-HC01-PL-ME-5020, C-56-HC01-PL-CI-7200, C-56-PL-607-PL-1000, C-56-PR-838-PL-1000, C-56-HC01-PL-ME-5020 | C-56-HC01-PL-ME-5020: SS 4, C-56-HC01-PL-CI-7200: FF 7, C-56-PL-607-PL-1000: FS, C-56-PR-838-PL-1000: FS 13, C-56-HC01-PL-ME-5020: FF 4 | 2025-05-21 12:30 | 2025-06-16 12:30
C-56-HC01-PL-ME-5020 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 | NDT (Tie-in Joint) | C-56-HC01-PL-ME-5010, C-56-HC01-PL-ME-5010, C-56-HC01-PL-ME-4820 | C-56-HC01-PL-ME-5010: SS 4, C-56-HC01-PL-ME-5010: FF 4, C-56-HC01-PL-ME-4820: SS 3 | C-56-HC01-PL-ME-4610, C-56-HC01-PL-ME-4610 | C-56-HC01-PL-ME-4610: SS 4, C-56-HC01-PL-ME-4610: FF 4 | 2025-05-26 12:30 | 2025-06-20 12:30
C-56-HC01-PL-ME-5030 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 | Holiday Testing | C-56-HC01-PL-ME-4410, C-56-HC01-PL-ME-4610, C-56-HC01-PL-ME-4410, C-56-HC01-PL-ME-4610, C-56-HC01-PL-ME-4830 | C-56-HC01-PL-ME-4410: SS 1, C-56-HC01-PL-ME-4610: SS 4, C-56-HC01-PL-ME-4410: FF, C-56-HC01-PL-ME-4610: FF 4, C-56-HC01-PL-ME-4830: SS 3 | C-56-HC01-PL-CI-6200, C-56-HC01-PL-CI-6200, C-56-HC01-PL-CA-5800 | C-56-HC01-PL-CI-6200: SS 2, C-56-HC01-PL-CI-6200: FF 1, C-56-HC01-PL-CA-5800: FF 2 | 2025-06-04 12:30 | 2025-07-01 12:30
C-52-D-HT-CI-3000 | Not Started | P2543-R01-Oct24..4.3.1.3.3.21.1.6 | Platforms/Crossovers/ Guardrails and Bollards/ Windsock | C-52-D-HT-CI-2220, HM-CS-0110, HS-CN-0690 | C-52-D-HT-CI-2220: FS, HM-CS-0110: FS, HS-CN-0690: FS | C-52-D-HT-CI-2600 | C-52-D-HT-CI-2600: FS | 2025-08-20 11:00 | 2025-09-03 11:00
C-52-PL-838-CI-1700 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.1.4 | Concrete Protection | C-52-PL-838-CI-1400, C-52-PL-838-CI-1600, C-52-PL-838-CI-1410, C-52-PL-838-CI-1420 | C-52-PL-838-CI-1400: FF 5, C-52-PL-838-CI-1600: FF 5, C-52-PL-838-CI-1410: FF 5, C-52-PL-838-CI-1420: FF 5 | C-52-PL-838-CI-2600, ML1739-E19 | C-52-PL-838-CI-2600: FS, ML1739-E19: FS | 2025-05-17 11:00 | 2025-07-11 11:00
C-52-PL-838-ME-1200 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.3.2 | Installation of Pig Signaler (838-V-602) | C-52-PL-838-ME-1000, HM-PL-0530, ML1015-B08, HM-PL-0840, HM-PL-1490, HM-PL-1530 | C-52-PL-838-ME-1000: FS, HM-PL-0530: FF 12, ML1015-B08: FS, HM-PL-0840: FS, HM-PL-1490: FF 12, HM-PL-1530: FS | C-52-PL-838-PI-2000 | C-52-PL-838-PI-2000: FS | 2025-05-16 15:00 | 2025-05-23 15:00
C-52-PL-838-EI-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.6.4 | Installation of RTU (Deleted) | C-52-PL-838-EI-2210 | C-52-PL-838-EI-2210: FS 25 | C-52-PL-838-TE-1000, ML1749-E20 | C-52-PL-838-TE-1000: FS, ML1749-E20: FS | 2025-10-01 11:00 | 2025-10-04 11:00
C-52-PL-838-TE-1600 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.8.2 | CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) (Deleted) | C-52-PL-838-TE-1000 | C-52-PL-838-TE-1000: SS | C-52-PL-838-TE-1420 | C-52-PL-838-TE-1420: FS | 2025-10-04 11:00 | 2025-10-11 11:00
C-52-PL-838-TE-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.1.21.8.1 | SDH Cabinet (Deleted) | C-52-PL-838-EI-1600, HM-ME-1290, HE-IC-0110, HE-TL-0470, ML1033-B22, HE-TL-0770, HM-TL-0040, HE-TL-0710, HE-TL-0830, HS-CN-0290, HM-ME-2270 | C-52-PL-838-EI-1600: FS, HM-ME-1290: FS, HE-IC-0110: FS, HE-TL-0470: FS, ML1033-B22: FS, HE-TL-0770: FS, HM-TL-0040: FS, HE-TL-0710: FS, HE-TL-0830: FS, HS-CN-0290: FS, HM-ME-2270: FS | C-52-PL-838-TE-1600 | C-52-PL-838-TE-1600: SS | 2025-10-04 11:00 | 2025-10-11 11:00
C-52-IDS1-CI-1700 | Not Started | P2543-R01-Oct24..4.3.1.3.7.4.21.1.4 | Concrete Protection | C-52-IDS1-CI-1200, C-52-IDS1-CI-1210, C-52-IDS1-CI-1220 | C-52-IDS1-CI-1200: FF 5, C-52-IDS1-CI-1210: FF 5, C-52-IDS1-CI-1220: FF 5 | C-52-IDS1-CI-2220 | C-52-IDS1-CI-2220: FS | 2025-07-10 11:00 | 2025-07-23 11:00
C-52-IDS2-CI-1700 | Not Started | P2543-R01-Oct24..4.3.1.3.7.6.21.1.4 | Concrete Protection | C-52-IDS2-CI-1400, C-52-IDS2-CI-1410, C-52-IDS2-CI-1420 | C-52-IDS2-CI-1400: FF 5, C-52-IDS2-CI-1410: FF 5, C-52-IDS2-CI-1420: FF 5 | C-52-IDS2-CI-2220 | C-52-IDS2-CI-2220: FS | 2025-08-09 11:00 | 2025-08-28 11:00
C-52-IDS3-CI-1700 | Not Started | P2543-R01-Oct24..4.3.1.3.7.5.21.1.4 | Concrete Protection | C-52-IDS3-CI-1400, C-52-IDS3-CI-1410, C-52-IDS3-CI-1420 | C-52-IDS3-CI-1400: FF 5, C-52-IDS3-CI-1410: FF 5, C-52-IDS3-CI-1420: FF 5 | C-52-IDS3-CI-2220 | C-52-IDS3-CI-2220: FS | 2025-08-27 11:00 | 2025-09-18 11:00
C-36-KM-HT-CI-2000 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.7 | Pipe Supports Fabrication & Installation | C-36-KM-HT-CI-1600, C-36-KM-HT-CI-1600, HM-CS-0120, HE-CS-1430, HS-CN-0690, HM-CS-0110, HE-CS-1490 | C-36-KM-HT-CI-1600: FS, C-36-KM-HT-CI-1600: FF, HM-CS-0120: FS, HE-CS-1430: FS, HS-CN-0690: FS, HM-CS-0110: FS, HE-CS-1490: FS | C-36-KM-HT-PI-1000 | C-36-KM-HT-PI-1000: FS | 2025-03-26 11:00 | 2025-04-14 13:00
C-36-KM-HT-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.8 | Fences & Gates Construction | C-36-KM-HT-CI-1420, HE-CS-0470, HE-CS-0350 | C-36-KM-HT-CI-1420: FS, HE-CS-0470: FS, HE-CS-0350: FS | C-36-KM-HT-CI-3000 | C-36-KM-HT-CI-3000: FS | 2025-05-02 13:00 | 2025-07-07 11:00
C-36-KM-HT-CI-3000 | Not Started | P2543-R01-Oct24..4.3.1.4.12.1.9 | Platforms/Crossovers/ Guardrails and Bollards/ Windsock | C-36-KM-HT-CI-2220, HM-CS-0110, HS-CN-0690 | C-36-KM-HT-CI-2220: FS, HM-CS-0110: FS, HS-CN-0690: FS | C-36-KM-HT-CI-2600 | C-36-KM-HT-CI-2600: FS | 2025-07-07 11:00 | 2025-07-21 11:00
C-56-HC01-PL-CI-6200 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 | Padding | C-56-HC01-PL-ME-4830, C-56-HC01-PL-ME-5030, C-56-HC01-PL-ME-4830, C-56-HC01-PL-ME-5030, C-56-HC01-PL-CI-6000, C-56-HC01-PL-CA-5800, C-56-HC01-PL-CA-5800, C-56-HC01-CME10-1160, C-56-HC01-CME10-1240 | C-56-HC01-PL-ME-4830: SS 1, C-56-HC01-PL-ME-5030: SS 2, C-56-HC01-PL-ME-4830: FF, C-56-HC01-PL-ME-5030: FF 1, C-56-HC01-PL-CI-6000: SS 3, C-56-HC01-PL-CA-5800: SS, C-56-HC01-PL-CA-5800: FF, C-56-HC01-CME10-1160: FF 7, C-56-HC01-CME10-1240: FF 7 | C-56-HC01-PL-ME-7400, PRECOM-56-HGHC-1000, C-56-HC01-PL-TE-8400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-7000, C-56-HC01-PL-CI-6600, C-56-HC01-PL-CI-6600 | C-56-HC01-PL-ME-7400: FF 3, PRECOM-56-HGHC-1000: FS, C-56-HC01-PL-TE-8400: SS 4, C-56-HC01-PL-TE-8400: FF 4, C-56-HC01-PL-CI-7000: SS 5, C-56-HC01-PL-CI-6600: FF 2, C-56-HC01-PL-CI-6600: SS 2 | 2025-06-12 11:00 | 2025-07-07 11:00
C-4N-H5HG-PIPEL-3800 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.20 | Welding | C-4N-H5HG-PIPEL-2800, C-4N-H5HG-PIPEL-3600 | C-4N-H5HG-PIPEL-2800: SS 2, C-4N-H5HG-PIPEL-3600: FS | C-4N-H5HG-PIPEL-4200, C-4N-H5HG-PIPEL-4200, ML1909-E36 | C-4N-H5HG-PIPEL-4200: SS 1, C-4N-H5HG-PIPEL-4200: FF, ML1909-E36: FS | 2025-01-24 07:00 | 2025-02-18 17:00
C-4N-H5HG-PIPEL-4200 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.22 | NDT | C-4N-H5HG-PIPEL-3600, C-4N-H5HG-PIPEL-3800, C-4N-H5HG-PIPEL-3600, C-4N-H5HG-PIPEL-3800, C-4N-H5HG-PIPEL-4000 | C-4N-H5HG-PIPEL-3600: SS 1, C-4N-H5HG-PIPEL-3800: SS 1, C-4N-H5HG-PIPEL-3600: FF, C-4N-H5HG-PIPEL-3800: FF, C-4N-H5HG-PIPEL-4000: FS | C-4N-H5HG-PIPEL-4600, C-4N-H5HG-PIPEL-4600 | C-4N-H5HG-PIPEL-4600: SS 2, C-4N-H5HG-PIPEL-4600: FF | 2025-01-25 07:00 | 2025-02-20 17:00
C-4N-H5HG-PIPEL-4600 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.26 | Ext. Joint Coating | C-4N-H5HG-PIPEL-4000, C-4N-H5HG-PIPEL-4200, C-4N-H5HG-PIPEL-4000, C-4N-H5HG-PIPEL-4200, C-4N-H5HG-PIPEL-4400 | C-4N-H5HG-PIPEL-4000: SS 2, C-4N-H5HG-PIPEL-4200: SS 2, C-4N-H5HG-PIPEL-4000: FF, C-4N-H5HG-PIPEL-4200: FF, C-4N-H5HG-PIPEL-4400: FS | C-4N-H5HG-PIPEL-5000, C-4N-H5HG-PIPEL-5000 | C-4N-H5HG-PIPEL-5000: SS 3, C-4N-H5HG-PIPEL-5000: FF | 2025-01-28 07:00 | 2025-02-21 17:00
C-4N-H5HG-PIPEL-4610 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.26 | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-PIPEL-4820, C-4N-H5HG-PIPEL-5020, C-4N-H5HG-PIPEL-4820, C-4N-H5HG-PIPEL-5020, C-4N-H5HG-PIPEL-4410 | C-4N-H5HG-PIPEL-4820: SS 1, C-4N-H5HG-PIPEL-5020: SS 1, C-4N-H5HG-PIPEL-4820: FF, C-4N-H5HG-PIPEL-5020: FF, C-4N-H5HG-PIPEL-4410: FS | C-4N-H5HG-PIPEL-5030, C-4N-H5HG-PIPEL-5030 | C-4N-H5HG-PIPEL-5030: SS 1, C-4N-H5HG-PIPEL-5030: FF | 2025-05-13 12:30 | 2025-06-14 12:30
C-4N-H5HG-PIPEL-5000 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.23 | Lowering | C-4N-H5HG-PIPEL-2410, C-4N-H5HG-PIPEL-4400, C-4N-H5HG-PIPEL-4600, C-4N-H5HG-PIPEL-4400, C-4N-H5HG-PIPEL-4600, C-4N-H5HG-PIPEL-4800, ML1159-A08, C-4N-H5HG-PIPEL-2410 | C-4N-H5HG-PIPEL-2410: SS 5, C-4N-H5HG-PIPEL-4400: SS 3, C-4N-H5HG-PIPEL-4600: SS 3, C-4N-H5HG-PIPEL-4400: FF, C-4N-H5HG-PIPEL-4600: FF, C-4N-H5HG-PIPEL-4800: FS, ML1159-A08: FF, C-4N-H5HG-PIPEL-2410: FF 5 | C-4N-H5HG-PIPEL-5010, C-4N-H5HG-PIPEL-5010 | C-4N-H5HG-PIPEL-5010: SS, C-4N-H5HG-PIPEL-5010: FF | 2025-05-03 14:30 | 2025-05-29 12:30
C-4N-H5HG-PIPEL-5010 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.23 | Section Tie-in Welding | C-4N-H5HG-PIPEL-4800, C-4N-H5HG-PIPEL-5000, C-4N-H5HG-PIPEL-4800, C-4N-H5HG-PIPEL-5000, C-4N-H5HG-PIPEL-4810 | C-4N-H5HG-PIPEL-4800: SS, C-4N-H5HG-PIPEL-5000: SS, C-4N-H5HG-PIPEL-4800: FF, C-4N-H5HG-PIPEL-5000: FF, C-4N-H5HG-PIPEL-4810: FS | C-4N-H5-TPL-PL-1000, C-4N-H5HG-PIPEL-5020, C-4N-H5HG-PIPEL-5020, ML1909-E36 | C-4N-H5-TPL-PL-1000: FS, C-4N-H5HG-PIPEL-5020: SS 1, C-4N-H5HG-PIPEL-5020: FF, ML1909-E36: FS | 2025-05-10 12:30 | 2025-06-12 12:30
C-4N-H5HG-PIPEL-5020 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.23 | NDT (Tie-in Joint) | C-4N-H5HG-PIPEL-4810, C-4N-H5HG-PIPEL-5010, C-4N-H5HG-PIPEL-4810, C-4N-H5HG-PIPEL-5010, C-4N-H5HG-PIPEL-4820 | C-4N-H5HG-PIPEL-4810: SS 1, C-4N-H5HG-PIPEL-5010: SS 1, C-4N-H5HG-PIPEL-4810: FF, C-4N-H5HG-PIPEL-5010: FF, C-4N-H5HG-PIPEL-4820: FS | C-4N-H5HG-PIPEL-4610, C-4N-H5HG-PIPEL-4610 | C-4N-H5HG-PIPEL-4610: SS 1, C-4N-H5HG-PIPEL-4610: FF | 2025-05-12 12:30 | 2025-06-13 12:30
C-4N-H5HG-PIPEL-5030 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.23 | Holiday Testing | C-4N-H5HG-PIPEL-4410, C-4N-H5HG-PIPEL-4610, C-4N-H5HG-PIPEL-4410, C-4N-H5HG-PIPEL-4610, C-4N-H5HG-PIPEL-4830 | C-4N-H5HG-PIPEL-4410: SS 1, C-4N-H5HG-PIPEL-4610: SS 1, C-4N-H5HG-PIPEL-4410: FF, C-4N-H5HG-PIPEL-4610: FF, C-4N-H5HG-PIPEL-4830: FS | C-4N-H5HG-PIPEL-6000, C-4N-H5HG-PIPEL-5600, C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-6000: SS 1, C-4N-H5HG-PIPEL-5600: SS, C-4N-H5HG-PIPEL-8200: SS, C-4N-H5HG-PIPEL-8400: SS | 2025-05-14 12:30 | 2025-06-16 12:30
C-4N-H5HG-PIPEL-6400 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.1.17 | Backfilling | C-4N-H5HG-PIPEL-6000, C-4N-H5HG-PIPEL-6000, C-4N-H5HG-PIPEL-8400, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-6000: SS 5, C-4N-H5HG-PIPEL-6000: FF 5, C-4N-H5HG-PIPEL-8400: SS 2, C-4N-H5HG-PIPEL-8400: FF 2 | C-4N-H5HG-PIPEL-6800, C-4N-H5HG-PIPEL-7400, C-4N-H5HG-PIPEL-6800 | C-4N-H5HG-PIPEL-6800: SS 10, C-4N-H5HG-PIPEL-7400: FS, C-4N-H5HG-PIPEL-6800: FF 10 | 2025-05-31 12:30 | 2025-08-04 12:30
C-4N-H5HG-PIPEL-8400 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.2.2 | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-PIPEL-4830, C-4N-H5HG-CMA13-1070, C-4N-H5HG-CMA01-1070, C-4N-H5HG-CMA02-1070, C-4N-H5HG-CMA03-1070, C-4N-H5HG-CMA04-1070, C-4N-H5HG-CMA05-1070, C-4N-H5HG-CMA06-1070, C-4N-H5HG-CMA07-1070, C-4N-H5HG-CMA08-1070, C-4N-H5HG-CMA09-1070, C-4N-H5HG-CMA1 | C-4N-H5HG-PIPEL-4830: SS, C-4N-H5HG-CMA13-1070: FF 1, C-4N-H5HG-CMA01-1070: FF 1, C-4N-H5HG-CMA02-1070: FF 1, C-4N-H5HG-CMA03-1070: FF 1, C-4N-H5HG-CMA04-1070: FF 1, C-4N-H5HG-CMA05-1070: FF 1, C-4N-H5HG-CMA06-1070: FF 1, C-4N-H5HG-CMA07-1070: FF 1, C-4N-H | C-4N-H5HG-PIPEL-8210, C-4N-H5HG-PIPEL-8410, C-4N-H5HG-PIPEL-6400, C-4N-H5HG-PIPEL-6400 | C-4N-H5HG-PIPEL-8210: FS, C-4N-H5HG-PIPEL-8410: FS, C-4N-H5HG-PIPEL-6400: SS 2, C-4N-H5HG-PIPEL-6400: FF 2 | 2025-05-29 12:30 | 2025-07-24 12:30
C-4N-H5HG-PIPEL-8410 | Not Started | P2543-R01-Oct24..4.3.1.5.4.12.2.2 | Termination/Splicing @ HGCP | C-4N-H5HG-PIPEL-8200, C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-8200: FS, C-4N-H5HG-PIPEL-8400: FS | PRECOM-4N-H5HG-1000 | PRECOM-4N-H5HG-1000: FS | 2025-07-24 12:30 | 2025-07-28 12:30
C-56-HC01-PL-CA-5430 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 | Installation of CP Test Post | C-56-HC01-PL-CA-5600, C-56-HC01-PL-CA-5200, C-56-HC01-PL-CA-5800, HS-GN-0530, ML1549-D22, HM-PL-0410 | C-56-HC01-PL-CA-5600: SS 1, C-56-HC01-PL-CA-5200: FS, C-56-HC01-PL-CA-5800: SS 1, HS-GN-0530: FS, ML1549-D22: FS, HM-PL-0410: FS | C-56-HC01-PL-CA-5440 | C-56-HC01-PL-CA-5440: FS | 2025-06-10 12:30 | 2025-07-04 12:30
C-56-HC01-PL-CA-5440 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 | Glanding & Termination of Temp. CP S/m | C-56-HC01-PL-CA-5430, C-56-HC01-PL-CA-5210 | C-56-HC01-PL-CA-5430: FS, C-56-HC01-PL-CA-5210: FS | C-56-HC01-PL-CA-5450 | C-56-HC01-PL-CA-5450: FS | 2025-07-04 12:30 | 2025-07-07 12:30
C-56-HC01-PL-CA-5400 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 | Installation of Test Post for Crossing | C-56-HC01-CMA02-1060, C-56-HC01-CMA02-1070, C-56-HC01-CMA03-1070, C-56-HC01-CMA13-1070, C-56-HC01-CMA09-1070, C-56-HC01-CMA11-1070, C-56-HC01-CMA14-1070, C-56-HC01-CMA15-1070, C-56-HC01-CMA22-1070, C-56-HC01-CMA04-1070, C-56-HC01-CMA16-1070, C-56-HC01-CMA1 | C-56-HC01-CMA02-1060: SS, C-56-HC01-CMA02-1070: FF, C-56-HC01-CMA03-1070: FF, C-56-HC01-CMA13-1070: FF, C-56-HC01-CMA09-1070: FF, C-56-HC01-CMA11-1070: FF, C-56-HC01-CMA14-1070: FF, C-56-HC01-CMA15-1070: FF, C-56-HC01-CMA22-1070: FF, C-56-HC01-CMA04-1070: | C-56-HC01-PL-CA-5410, C-56-HC01-PL-CA-5410 | C-56-HC01-PL-CA-5410: SS 1, C-56-HC01-PL-CA-5410: FF | 2025-08-20 11:00 | 2025-09-01 11:00
C-56-HC01-PL-CA-5410 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 | Installation of CP JB's | C-56-HC01-PL-CA-5400, C-56-HC01-PL-CA-5400, C-56-HC01-PL-CA-5230 | C-56-HC01-PL-CA-5400: SS 1, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-CA-5230: FS | C-56-HC01-PL-CA-5420, C-56-HC01-PL-CA-5420 | C-56-HC01-PL-CA-5420: SS 1, C-56-HC01-PL-CA-5420: FF | 2025-08-21 11:00 | 2025-09-02 11:00
C-56-HC01-PL-CA-5420 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 | Installation of CP TR | C-56-HC01-PL-CA-5410, C-56-HC01-PL-CA-5410, C-56-HC01-PL-CA-5240 | C-56-HC01-PL-CA-5410: SS 1, C-56-HC01-PL-CA-5410: FF, C-56-HC01-PL-CA-5240: FS | C-56-HC01-PL-CA-5450 | C-56-HC01-PL-CA-5450: FS | 2025-08-22 11:00 | 2025-09-03 11:00
C-56-HC01-PL-CA-5450 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 | CIP/DCVG Survey | C-56-HC01-PL-CA-5420, C-56-HC01-PL-CA-5440, C-56-HC01-PL-CA-5250 | C-56-HC01-PL-CA-5420: FS, C-56-HC01-PL-CA-5440: FS, C-56-HC01-PL-CA-5250: FS | PRECOM-56-HGHC-1000 | PRECOM-56-HGHC-1000: FS | 2025-09-03 11:00 | 2025-09-08 11:00
C-4N-H5-TPL-CI-0100 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.1 | Demolition Works (Paving) | ML1159-A08, HE-CS-0610, CTF-1000, CTF-1010, C-4N-H5HG-PIPEL-1800 | ML1159-A08: FS, HE-CS-0610: FS, CTF-1000: FS, CTF-1010: FS, C-4N-H5HG-PIPEL-1800: FS 28 | C-4N-H5-TPL-CI-1000 | C-4N-H5-TPL-CI-1000: FS | 2025-01-02 07:00 | 2025-01-08 17:00
C-4N-H5-TPL-PR-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.3 | Piperack - Reinforced in-situ concrete for Strengthening of existing foundations | C-4N-H5-TPL-CI-1210 | C-4N-H5-TPL-CI-1210: FS | C-4N-H5-TPL-PR-1200 | C-4N-H5-TPL-PR-1200: FS | 2025-02-08 07:00 | 2025-04-05 13:00
C-4N-H5-TPL-PR-1200 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.4 | Piperack - Reinforced in-situ concrete for Strengthening of existing foundations | C-4N-H5-TPL-PR-1000 | C-4N-H5-TPL-PR-1000: FS | C-4N-H5-TPL-CI-2000, C-4N-H5-TPL-CI-1700 | C-4N-H5-TPL-CI-2000: FS, C-4N-H5-TPL-CI-1700: FF 5 | 2025-04-05 13:00 | 2025-06-04 11:00
C-4N-H5-TPL-CI-1700 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.1.6 | Concrete Protection | C-4N-H5-TPL-CI-1400, C-4N-H5-TPL-CI-1600, C-4N-H5-TPL-CI-1410, C-4N-H5-TPL-CI-1420, C-4N-H5-TPL-PR-1200 | C-4N-H5-TPL-CI-1400: FF 5, C-4N-H5-TPL-CI-1600: FF 5, C-4N-H5-TPL-CI-1410: FF 5, C-4N-H5-TPL-CI-1420: FF 5, C-4N-H5-TPL-PR-1200: FF 5 | C-4N-H5-TPL-CI-2000 | C-4N-H5-TPL-CI-2000: FF | 2025-05-20 11:00 | 2025-06-12 11:00
C-56-HC01-PL-CA-5800 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.38 | Installation of Temp. Anode | C-56-HC01-PL-ME-4830, C-56-HC01-PL-ME-5030, C-56-HC01-PL-CA-5600 | C-56-HC01-PL-ME-4830: SS 1, C-56-HC01-PL-ME-5030: FF 2, C-56-HC01-PL-CA-5600: SS | C-56-HC01-PL-CA-5430, C-56-HC01-PL-CI-6200, C-56-HC01-PL-CI-6200 | C-56-HC01-PL-CA-5430: SS 1, C-56-HC01-PL-CI-6200: SS, C-56-HC01-PL-CI-6200: FF | 2025-06-09 12:30 | 2025-07-03 12:30
C-4W-TI-PI-2000 | Not Started | P2543-R01-Oct24..4.3.1.6.2.12.2.1 | Final Bolt Torquing/ Re-Instatement | C-4W-TI-PI-1800, ML1219-B19, ML1889-E34, ML1879-E33, HE-PI-1240, HE-PI-1300, HM-PL-0630, HM-PL-0640, ML1939-E39, HM-PL-0740, HM-PL-0220, HM-PI-0040, HM-PL-1510, HM-PL-1570 | C-4W-TI-PI-1800: FF, ML1219-B19: FS, ML1889-E34: FS, ML1879-E33: FS, HE-PI-1240: FS, HE-PI-1300: FS, HM-PL-0630: FS, HM-PL-0640: FS, ML1939-E39: FS, HM-PL-0740: FS, HM-PL-0220: FS, HM-PI-0040: FS, HM-PL-1510: FS, HM-PL-1570: FS | C-4W-TI-3000, CCM-PM4510 | C-4W-TI-3000: FS, CCM-PM4510: FS | 2025-07-11 11:00 | 2025-07-12 11:00
C-4W-TI-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.6.2.12.2.2 | Piping Pre-Fabrication | C-4W-081-03-PI-1000, ML1002, ML1219-B19, HE-PI-1240, HE-PI-1300, HM-PI-0040, HS-CN-0190 | C-4W-081-03-PI-1000: FS, ML1002: FS, ML1219-B19: FS, HE-PI-1240: FS, HE-PI-1300: FS, HM-PI-0040: FS, HS-CN-0190: FS | C-4W-TI-PI-1200 | C-4W-TI-PI-1200: FS | 2025-06-13 11:00 | 2025-06-20 11:00
C-56-HC01-PL-TE-8400 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.3.2 | FO - Cable Pulling/ Laying | C-56-HC01-PL-CI-6000, C-56-HC01-CMA02-1070, C-56-HC01-CMA03-1070, C-56-HC01-CMA13-1070, C-56-HC01-CMA09-1070, C-56-HC01-CMA11-1070, C-56-HC01-CMA14-1070, C-56-HC01-CMA15-1070, C-56-HC01-CMA22-1070, C-56-HC01-CMA04-1070, C-56-HC01-CMA16-1070, C-56-HC01-CMA1 | C-56-HC01-PL-CI-6000: SS 5, C-56-HC01-CMA02-1070: FF, C-56-HC01-CMA03-1070: FF, C-56-HC01-CMA13-1070: FF, C-56-HC01-CMA09-1070: FF, C-56-HC01-CMA11-1070: FF, C-56-HC01-CMA14-1070: FF, C-56-HC01-CMA15-1070: FF, C-56-HC01-CMA22-1070: FF, C-56-HC01-CMA04-1070 | C-56-HC01-PL-TE-8410, C-56-HC01-PL-CI-6600, C-56-HC01-PL-CI-6600 | C-56-HC01-PL-TE-8410: FS, C-56-HC01-PL-CI-6600: FF 4, C-56-HC01-PL-CI-6600: SS 4 | 2025-06-17 11:00 | 2025-07-11 11:00
C-56-HC01-PL-TE-8410 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.3.2 | Termination/Splicing @ BVS | C-56-HC01-PL-TE-8400, C-56-HC01-PL-TE-8210 | C-56-HC01-PL-TE-8400: FS, C-56-HC01-PL-TE-8210: FS | PRECOM-56-HGHC-1000 | PRECOM-56-HGHC-1000: FS | 2025-07-11 11:00 | 2025-07-14 11:00
C-MAQTA-EI-1000 | Not Started | P2543-R01-Oct24..4.3.1.8.12.2.1 | Electrical & Instrumentation Works (ICSS, Feeder, FO Board...) | C-DBV6-EI-2500, HM-ME-1590, HM-TL-0040, HS-GN-0410, CTF-1000, HM-EL-0520, HM-IC-0040, HS-GN-0290, HS-GN-0350, HS-GN-0470, HM-ME-2330, CTF-1010 | C-DBV6-EI-2500: FS, HM-ME-1590: FF, HM-TL-0040: FS, HS-GN-0410: FS, CTF-1000: FS, HM-EL-0520: FS, HM-IC-0040: FS, HS-GN-0290: FS, HS-GN-0350: FS, HS-GN-0470: FS, HM-ME-2330: FF, CTF-1010: FS | C-MAQTA-CI-1800 | C-MAQTA-CI-1800: FF | 2025-07-15 11:00 | 2025-07-22 11:00
C-56-HC01-PL-CI-7000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 | Gatch Laying & Levelling | C-56-HC01-PL-CI-6000, C-56-HC01-CMA02-1070, C-56-HC01-CMA03-1070, C-56-HC01-CMA13-1070, C-56-HC01-CMA09-1070, C-56-HC01-CMA11-1070, C-56-HC01-CMA14-1070, C-56-HC01-CMA15-1070, C-56-HC01-CMA22-1070, C-56-HC01-CMA04-1070, C-56-HC01-CMA16-1070, C-56-HC01-CMA1 | C-56-HC01-PL-CI-6000: SS 5, C-56-HC01-CMA02-1070: FF, C-56-HC01-CMA03-1070: FF, C-56-HC01-CMA13-1070: FF, C-56-HC01-CMA09-1070: FF, C-56-HC01-CMA11-1070: FF, C-56-HC01-CMA14-1070: FF, C-56-HC01-CMA15-1070: FF, C-56-HC01-CMA22-1070: FF, C-56-HC01-CMA04-1070 | C-56-HC01-PL-CI-7010 | C-56-HC01-PL-CI-7010: SS 5 | 2025-06-26 11:00 | 2025-07-21 11:00
C-56-HC01-PL-CI-7010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 | Gatch Compaction | C-56-HC01-PL-CI-7000 | C-56-HC01-PL-CI-7000: SS 5 | C-56-HC01-PL-CI-8000, PRECOM-56-HGHC-1000, C-56-HC01-PL-CI-7200, C-56-HC01-PL-ME-7400 | C-56-HC01-PL-CI-8000: FS, PRECOM-56-HGHC-1000: FS, C-56-HC01-PL-CI-7200: FF 7, C-56-HC01-PL-ME-7400: FS | 2025-07-03 07:00 | 2025-07-25 17:00
C-56-HC01-PL-CI-8000 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 | Installation of Marker Post/Sign Board | C-56-HC01-PL-CI-7010 | C-56-HC01-PL-CI-7010: FS | C-56-HC01-PL-CI-8010, ML1959-E41 | C-56-HC01-PL-CI-8010: SS 5, ML1959-E41: FS | 2025-07-26 07:00 | 2025-08-18 17:00
C-56-HC01-PL-CI-8010 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 | Installation of Crash Barriers (If any) | C-56-HC01-PL-CI-8000 | C-56-HC01-PL-CI-8000: SS 5 | PRECOM-56-HGHC-1000, ML1959-E41, ML1020 | PRECOM-56-HGHC-1000: FS, ML1959-E41: FS, ML1020: FS | 2025-08-01 07:00 | 2025-08-23 17:00
C-56-HC01-PL-CI-6400 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.21 | Backfilling from Habshan complex to KP 6 | C-56-HC01-PL-CI-6000, C-56-HC01-PL-TE-8200 | C-56-HC01-PL-CI-6000: FS, C-56-HC01-PL-TE-8200: FF 1 | C-56-HC01-PL-CI-6600, C-56-HC01-PL-CI-6800, C-56-HC01-PL-CI-6800 | C-56-HC01-PL-CI-6600: SS 3, C-56-HC01-PL-CI-6800: SS 7, C-56-HC01-PL-CI-6800: FF 7 | 2025-06-07 09:30 | 2025-07-02 09:30
C-56-HC01-PL-CI-6600 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.4.1.35 | Backfilling from KP 6 to KP 12.6 | C-56-HC01-PL-CI-6200, C-56-HC01-PL-CI-6400, C-56-HC01-PL-CI-6200, C-56-HC01-PL-TE-8400, C-56-HC01-PL-TE-8400 | C-56-HC01-PL-CI-6200: FF 2, C-56-HC01-PL-CI-6400: SS 3, C-56-HC01-PL-CI-6200: SS 2, C-56-HC01-PL-TE-8400: FF 4, C-56-HC01-PL-TE-8400: SS 4 | C-56-HC01-PL-CI-7000, C-56-HC01-PL-CI-7000 | C-56-HC01-PL-CI-7000: FF 4, C-56-HC01-PL-CI-7000: SS 4 | 2025-06-21 11:00 | 2025-07-16 11:00
C-56-PR-838-TE-1000 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.8.32 | SDH Cabinet (Deleted) | C-56-PR-838-EI-2410, HE-TL-0770, HE-TL-0710, HS-CN-0290, HM-TL-0040, HM-EL-0180, HE-TL-0470, ML1053-D23, ML1033-B22, HE-IC-0110, HE-TL-0830, ML1051-D07, HM-EL-610 | C-56-PR-838-EI-2410: FS, HE-TL-0770: FS, HE-TL-0710: FS, HS-CN-0290: FS, HM-TL-0040: FS, HM-EL-0180: FS, HE-TL-0470: FS, ML1053-D23: FS, ML1033-B22: FS, HE-IC-0110: FS, HE-TL-0830: FS, ML1051-D07: FS, HM-EL-610: FS | C-56-PR-838-TE-1600 | C-56-PR-838-TE-1600: FS | 2025-08-01 11:00 | 2025-08-18 11:00
C-56-PR-838-TE-1600 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.8.33 | CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) (Deleted) | C-56-PR-838-TE-1000 | C-56-PR-838-TE-1000: FS | C-56-PR-838-TE-1420 | C-56-PR-838-TE-1420: FF | 2025-08-18 11:00 | 2025-08-25 11:00
C-52-0405-CME11-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.7.1 | Trench Excavation | C-52-0405-CME10-1000 | C-52-0405-CME10-1000: FS 1 | C-52-0405-CME11-1010, C-52-0506-CME01-1000 | C-52-0405-CME11-1010: FS, C-52-0506-CME01-1000: FS 1 | 2025-01-22 12:00 | 2025-01-24 12:00
C-52-0405-CME11-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.7.2 | Bedding | C-52-0405-CME11-1000 | C-52-0405-CME11-1000: FS | C-52-0405-CME11-1020 | C-52-0405-CME11-1020: FS | 2025-01-24 12:00 | 2025-01-27 12:00
C-52-0405-CME11-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.7.3 | Lowering | C-52-0405-CME11-1010 | C-52-0405-CME11-1010: FS | C-52-0405-CME11-1030 | C-52-0405-CME11-1030: FS | 2025-01-27 12:00 | 2025-01-29 12:00
C-52-0405-CME11-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.7.3 | Section Tie-in Welding | C-52-0405-CME11-1020 | C-52-0405-CME11-1020: FS | C-52-0405-CME11-1040, C-52-0405-PL-ME-4810 | C-52-0405-CME11-1040: FS, C-52-0405-PL-ME-4810: FF 1 | 2025-01-29 12:00 | 2025-02-01 12:00
C-52-0405-CME11-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.7.3 | NDT (Tie-in Joint) | C-52-0405-CME11-1030 | C-52-0405-CME11-1030: FS | C-52-0405-CME11-1050 | C-52-0405-CME11-1050: FS | 2025-02-01 12:00 | 2025-02-05 12:00
C-52-0405-CME11-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.7.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME11-1040 | C-52-0405-CME11-1040: FS | C-52-0405-CME11-1060 | C-52-0405-CME11-1060: FS | 2025-02-05 12:00 | 2025-02-08 12:00
C-52-0405-CME11-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.7.4 | Holiday Testing | C-52-0405-CME11-1050 | C-52-0405-CME11-1050: FS | C-52-0405-CME11-1070 | C-52-0405-CME11-1070: FS | 2025-02-08 12:00 | 2025-02-11 12:00
C-52-0405-CME11-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.7.5 | Padding & Back Filling | C-52-0405-CME11-1060 | C-52-0405-CME11-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-11 12:00 | 2025-02-13 12:00
C-52-0405-CME10-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.5.1 | Trench Excavation | C-52-0405-CME09-1000 | C-52-0405-CME09-1000: FS 1 | C-52-0405-CME10-1010, C-52-0405-CME11-1000 | C-52-0405-CME10-1010: FS, C-52-0405-CME11-1000: FS 1 | 2025-01-18 12:00 | 2025-01-21 12:00
C-52-0405-CME10-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.5.2 | Bedding | C-52-0405-CME10-1000 | C-52-0405-CME10-1000: FS | C-52-0405-CME10-1020 | C-52-0405-CME10-1020: FS | 2025-01-21 12:00 | 2025-01-23 12:00
C-52-0405-CME10-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.5.3 | Lowering | C-52-0405-CME10-1010 | C-52-0405-CME10-1010: FS | C-52-0405-CME10-1030 | C-52-0405-CME10-1030: FS | 2025-01-23 12:00 | 2025-01-25 12:00
C-52-0405-CME10-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.5.3 | Section Tie-in Welding | C-52-0405-CME10-1020 | C-52-0405-CME10-1020: FS | C-52-0405-CME10-1040, C-52-0405-PL-ME-4810 | C-52-0405-CME10-1040: FS, C-52-0405-PL-ME-4810: FF 1 | 2025-01-25 12:00 | 2025-01-29 12:00
C-52-0405-CME10-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.5.3 | NDT (Tie-in Joint) | C-52-0405-CME10-1030 | C-52-0405-CME10-1030: FS | C-52-0405-CME10-1050 | C-52-0405-CME10-1050: FS | 2025-01-29 12:00 | 2025-02-01 12:00
C-52-0405-CME10-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.5.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME10-1040 | C-52-0405-CME10-1040: FS | C-52-0405-CME10-1060 | C-52-0405-CME10-1060: FS | 2025-02-01 12:00 | 2025-02-05 12:00
C-52-0405-CME10-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.5.4 | Holiday Testing | C-52-0405-CME10-1050 | C-52-0405-CME10-1050: FS | C-52-0405-CME10-1070 | C-52-0405-CME10-1070: FS | 2025-02-05 12:00 | 2025-02-07 12:00
C-52-0405-CME10-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.5.5 | Padding & Back Filling | C-52-0405-CME10-1060 | C-52-0405-CME10-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-07 12:00 | 2025-02-10 12:00
C-52-0405-CME09-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.4.1 | Trench Excavation | C-52-0405-CME16-1000 | C-52-0405-CME16-1000: FS 1 | C-52-0405-CME09-1010, C-52-0405-CME10-1000 | C-52-0405-CME09-1010: FS, C-52-0405-CME10-1000: FS 1 | 2025-01-15 12:00 | 2025-01-17 12:00
C-52-0405-CME09-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.4.2 | Bedding | C-52-0405-CME09-1000 | C-52-0405-CME09-1000: FS | C-52-0405-CME09-1020 | C-52-0405-CME09-1020: FS | 2025-01-17 12:00 | 2025-01-20 12:00
C-52-0405-CME09-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.4.3 | Lowering | C-52-0405-CME09-1010 | C-52-0405-CME09-1010: FS | C-52-0405-CME09-1030 | C-52-0405-CME09-1030: FS | 2025-01-20 12:00 | 2025-01-22 12:00
C-52-0405-CME09-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.4.3 | Section Tie-in Welding | C-52-0405-CME09-1020 | C-52-0405-CME09-1020: FS | C-52-0405-CME09-1040, C-52-0405-PL-ME-4810 | C-52-0405-CME09-1040: FS, C-52-0405-PL-ME-4810: FF 1 | 2025-01-22 12:00 | 2025-01-25 12:00
C-52-0405-CME09-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.4.3 | NDT (Tie-in Joint) | C-52-0405-CME09-1030 | C-52-0405-CME09-1030: FS | C-52-0405-CME09-1050 | C-52-0405-CME09-1050: FS | 2025-01-25 12:00 | 2025-01-29 12:00
C-52-0405-CME09-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.4.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME09-1040 | C-52-0405-CME09-1040: FS | C-52-0405-CME09-1060 | C-52-0405-CME09-1060: FS | 2025-01-29 12:00 | 2025-02-01 12:00
C-52-0405-CME09-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.4.4 | Holiday Testing | C-52-0405-CME09-1050 | C-52-0405-CME09-1050: FS | C-52-0405-CME09-1070 | C-52-0405-CME09-1070: FS | 2025-02-01 12:00 | 2025-02-04 12:00
C-52-0405-CME09-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.4.5 | Padding & Back Filling | C-52-0405-CME09-1060 | C-52-0405-CME09-1060: FS | C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5220: FF 1, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF 1, C-52-0405-PL-CI-6000: FF | 2025-02-04 12:00 | 2025-02-06 12:00
C-52-0203-CME04-1000 | Completed | P2543-R01-Oct24..4.3.1.3.15.21.2.12.1 | Trench Excavation | C-52-0102-PL-CI-2200 | C-52-0102-PL-CI-2200: FS | C-52-0203-CME04-1010, C-52-0203-CME04-1080 | C-52-0203-CME04-1010: FS, C-52-0203-CME04-1080: FS 1 | 2024-08-14 15:00 | 2024-08-17 15:00
C-52-0203-CME04-1010 | Completed | P2543-R01-Oct24..4.3.1.3.15.21.2.12.2 | Bedding | C-52-0203-CME04-1000 | C-52-0203-CME04-1000: FS | C-52-0203-CME04-1020 | C-52-0203-CME04-1020: FS | 2024-08-19 15:00 | 2024-08-22 15:00
C-52-0203-CME04-1020 | Completed | P2543-R01-Oct24..4.3.1.3.15.21.2.12.3 | Lowering | C-52-0203-CME04-1010 | C-52-0203-CME04-1010: FS | C-52-0203-CME04-1030 | C-52-0203-CME04-1030: FS | 2024-08-26 15:00 | 2024-09-15 07:30
C-52-0203-CME04-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.2.12.3 | Section Tie-in Welding | C-52-0203-CME04-1020 | C-52-0203-CME04-1020: FS | C-52-0203-CME04-1040, C-52-0203-PL-ME-4810 | C-52-0203-CME04-1040: FS, C-52-0203-PL-ME-4810: FF 1 | 2024-10-26 07:00 | 2024-10-29 17:00
C-52-0203-CME04-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.2.12.3 | NDT (Tie-in Joint) | C-52-0203-CME04-1030 | C-52-0203-CME04-1030: FS | C-52-0203-CME04-1050 | C-52-0203-CME04-1050: FS | 2024-10-30 07:00 | 2024-11-01 17:00
C-52-0203-CME04-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.2.12.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0203-CME04-1040 | C-52-0203-CME04-1040: FS | C-52-0203-CME04-1060 | C-52-0203-CME04-1060: FS | 2024-11-02 07:00 | 2024-11-05 17:00
C-52-0203-CME04-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.2.12.4 | Holiday Testing | C-52-0203-CME04-1050 | C-52-0203-CME04-1050: FS | C-52-0203-CME04-1070 | C-52-0203-CME04-1070: FS | 2024-11-06 07:00 | 2024-11-07 17:00
C-52-0203-CME04-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.2.12.5 | Padding & Back Filling | C-52-0203-CME04-1060 | C-52-0203-CME04-1060: FS | C-52-0203-PL-CA-5220, C-52-0203-PL-TE-8200, C-52-0203-PL-ME-7400, C-52-0203-PL-CI-6800, C-52-0203-PL-CI-6000, ML1070 | C-52-0203-PL-CA-5220: FF 1, C-52-0203-PL-TE-8200: FF 1, C-52-0203-PL-ME-7400: FS, C-52-0203-PL-CI-6800: FF 1, C-52-0203-PL-CI-6000: FF 7, ML1070: FS | 2024-11-08 07:00 | 2024-11-09 17:00
C-4N-HG-TPR-CI-0100 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.1 | Demolition Works (Paving) | ML1199-B24, CTF-1000, CTF-1010, C-4N-H5-TPL-CI-1040 | ML1199-B24: FS, CTF-1000: FS, CTF-1010: FS, C-4N-H5-TPL-CI-1040: FS | C-4N-HG-TPR-CI-1000 | C-4N-HG-TPR-CI-1000: FS | 2025-02-01 07:00 | 2025-02-07 17:00
C-4N-HG-TPR-CI-1700 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.3 | Concrete Protection | C-4N-HG-TPR-CI-1400, C-4N-HG-TPR-CI-1600, C-4N-HG-TPR-CI-1410, C-4N-HG-TPR-CI-1420, C-4N-HG-TPR-CI-1500 | C-4N-HG-TPR-CI-1400: FF 5, C-4N-HG-TPR-CI-1600: FF 5, C-4N-HG-TPR-CI-1410: FF 5, C-4N-HG-TPR-CI-1420: FF 5, C-4N-HG-TPR-CI-1500: FF 5 | C-4N-HG-TPR-CI-2600 | C-4N-HG-TPR-CI-2600: FF | 2025-04-18 13:00 | 2025-05-10 11:00
C-4N-HG-TPR-CI-2220 | Not Started | P2543-R01-Oct24..4.3.1.5.1.12.1.4 | Fences & Gates Construction | C-4N-HG-TPR-CI-3000, C-4N-HG-TPR-CI-3010, HE-CS-0470, HE-CS-0350 | C-4N-HG-TPR-CI-3000: FS, C-4N-HG-TPR-CI-3010: FF, HE-CS-0470: FS, HE-CS-0350: FS | C-4N-HG-TPR-CI-2600 | C-4N-HG-TPR-CI-2600: FF | 2025-07-05 11:00 | 2025-07-26 11:00
C-4N-H5-TPL-EL-1000 | Not Started | P2543-R01-Oct24..4.3.1.5.2.3.12.9.1 | Electrical Shutdown (PDBs) | C-4N-H5-TPL-CA-1030, HM-ME-1590, HM-ME-2330 | C-4N-H5-TPL-CA-1030: FS, HM-ME-1590: FF, HM-ME-2330: FF | C-4N-H5-TPL-TE-1420, ML1949-E40 | C-4N-H5-TPL-TE-1420: FS, ML1949-E40: FS | 2025-07-28 11:00 | 2025-07-31 11:00
C-DBV6-PI-1000 | Not Started | P2543-R01-Oct24..4.3.1.7.12.3 | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | C-4W-TI-PI-1200, ML1002, HE-PI-1300, ML1219-B19, HE-PI-1240, HM-PI-0040, HM-PL-0630, CTF-1000, HM-PL-0740, HS-CN-0190, HM-PL-0640, HM-PL-0220, HM-ME-1590, HM-ME-2200, HM-ME-2330, HM-PL-1510, HM-PL-1570, CTF-1010 | C-4W-TI-PI-1200: FS, ML1002: FS, HE-PI-1300: FS, ML1219-B19: FS, HE-PI-1240: FS, HM-PI-0040: FS, HM-PL-0630: FS, CTF-1000: FS, HM-PL-0740: FS, HS-CN-0190: FS, HM-PL-0640: FS, HM-PL-0220: FS, HM-ME-1590: FS, HM-ME-2200: FS, HM-ME-2330: FS, HM-PL-1510: FS, H | C-DBV6-CI-5000, CCM-PM4510 | C-DBV6-CI-5000: FS, CCM-PM4510: FS | 2025-07-02 11:00 | 2025-07-07 11:00
C-DBV6-CI-5000 | Not Started | P2543-R01-Oct24..4.3.1.7.12.4 | Shelter Installation | C-DBV6-PI-1000, HM-ME-1190, HM-CS-0110, HM-ME-1590, HM-ME-2330 | C-DBV6-PI-1000: FS, HM-ME-1190: FS, HM-CS-0110: FS, HM-ME-1590: FS, HM-ME-2330: FS | C-DBV6-EI-2500 | C-DBV6-EI-2500: FS | 2025-07-07 11:00 | 2025-07-11 11:00
C-MAQTA-EL-2000 | Not Started | P2543-R01-Oct24..4.3.1.8.12.4 | Shutdown | C-MAQTA-TE-1020, C-MAQTA-TE-1010, C-MAQTA-TE-1000, C-MAQTA-EI-2050, C-COM-890 | C-MAQTA-TE-1020: FS, C-MAQTA-TE-1010: FS, C-MAQTA-TE-1000: FS, C-MAQTA-EI-2050: FS, C-COM-890: FS | PRE-COM1330, CCM-PM4520, CCM-PM4530, CCM-PM4540 | PRE-COM1330: FS, CCM-PM4520: FS, CCM-PM4530: FS, CCM-PM4540: FS | 2025-08-26 11:00 | 2025-08-30 11:00
C-56-591-01-CI-3020 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.1 | Compaction & Testing for Equipment Foundations & Hard Stand Area | C-56-591-01-CI-1010 | C-56-591-01-CI-1010: FS | C-56-591-01-CI-1400 | C-56-591-01-CI-1400: FS | 2025-02-06 07:00 | 2025-02-11 17:00
C-56-591-01-CI-3030 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.1 | Compaction & Testing for Pipe Support Foundations | C-56-591-01-CI-1020 | C-56-591-01-CI-1020: FS | C-56-591-01-CI-1600 | C-56-591-01-CI-1600: FS | 2025-02-14 07:00 | 2025-02-19 17:00
C-56-591-01-CI-3040 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.1 | Compaction & Testing for Field Instrument Foundations | C-56-591-01-CI-1030 | C-56-591-01-CI-1030: FS | C-56-591-01-CI-1410 | C-56-591-01-CI-1410: FS | 2025-02-19 07:00 | 2025-02-24 17:00
C-56-591-01-CI-3050 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.1 | Compaction & Testing for Access Platform & Misc. Structural Foundations | C-56-591-01-CI-1040 | C-56-591-01-CI-1040: FS | C-56-591-01-CI-1420 | C-56-591-01-CI-1420: FS | 2025-03-01 07:00 | 2025-03-08 11:00
C-56-591-01-CI-3060 | Not Started | P2543-R01-Oct24..4.3.1.2.1.12.1.1 | Compaction & Testing for Light Pole, Fence & Gates Foundation | C-56-591-01-CI-1050 | C-56-591-01-CI-1050: FS | C-56-591-01-CI-1430 | C-56-591-01-CI-1430: FS | 2025-03-07 07:00 | 2025-03-14 11:00
CTF-SO1000 | Completed | P2543-R01-Oct24..4.2.1 | Main Office | HP-ME-1040, ML1002 | HP-ME-1040: FS, ML1002: FS | CTF-SO1010, CTF-SO1010, CTF-1010 | CTF-SO1010: FF, CTF-SO1010: SS 15, CTF-1010: SS 9 | 2023-09-10 | 2023-12-15 07:30
CTF-1000 | Completed | P2543-R01-Oct24..4.2.1 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | CTF-SO1080, ML1002 | CTF-SO1080: SS, ML1002: FS | C-COM-850, C-COM-750, C-56-HC01-PL-CI-1000, C-56-HC01-PL-CI-1000, C-56-PR-838-CI-1000, C-56-591-01-CI-1000, C-52-598-06-CI-1000, C-52-PR-839-CI-1000, C-52-EB1-CI-1000, C-52-D-HT-CI-1000, C-52-PL-838-CI-1000, C-52-IDS1-CI-1000, C-52-IDS2-CI-1000, C-52-IDS3- | C-COM-850: FS, C-COM-750: SS 6, C-56-HC01-PL-CI-1000: FS, C-56-HC01-PL-CI-1000: FF, C-56-PR-838-CI-1000: FS, C-56-591-01-CI-1000: FS, C-52-598-06-CI-1000: FS, C-52-PR-839-CI-1000: FF, C-52-EB1-CI-1000: FS, C-52-D-HT-CI-1000: FS, C-52-PL-838-CI-1000: FS, C- | 2023-07-19 08:00 | 2023-12-11 17:00
C-COM-750 | Not Started | P2543-R01-Oct24..4.1.3 | Issue ICR-Construction Procedures / Method Statements / ITPs | HE-RR-0050, HE-CS-0350, CTF-1000, ML1021-B15, ML1012-B06, HE-IC-1130, HE-CS-0230, HE-CS-0170, ML1189-B16, HE-PI-0240, HC-GN-380, HE-PR-0830, HE-PL-1370, HE-PI-3520, HE-CS-0290, HE-TL-990, HE-TL-1040, HE-TL-1190, CTF-1010 | HE-RR-0050: FS, HE-CS-0350: FF, CTF-1000: SS 6, ML1021-B15: FS, ML1012-B06: FF, HE-IC-1130: FF, HE-CS-0230: FS, HE-CS-0170: FS, ML1189-B16: FS, HE-PI-0240: FS, HC-GN-380: FS, HE-PR-0830: FS, HE-PL-1370: FS, HE-PI-3520: FS, HE-CS-0290: FS, HE-TL-990: FS, HE | C-COM-760 | C-COM-760: FF 10 | 2024-10-27 07:00 | 2024-11-29 17:00
C-COM-760 | Not Started | P2543-R01-Oct24..4.1.3 | Receive Company Comments-Construction Procedures / Method Statements / ITPs | C-COM-750 | C-COM-750: FF 10 | C-COM-770 | C-COM-770: FF 10 | 2024-11-07 07:00 | 2024-12-15 17:00
C-COM-770 | Not Started | P2543-R01-Oct24..4.1.3 | Re-Issue for Approval-Construction Procedures / Method Statements / ITPs | HE-PR-0890, HE-IC-1070, C-COM-760, HE-PR-0890, ML1010-B14 | HE-PR-0890: FS, HE-IC-1070: FS, C-COM-760: FF 10, HE-PR-0890: FF, ML1010-B14: FS | C-COM-780 | C-COM-780: FF 10 | 2024-11-19 07:00 | 2024-12-26 17:00
C-COM-780 | Not Started | P2543-R01-Oct24..4.1.3 | Obtain Company Approval-Construction Procedures / Method Statements / ITPs | C-COM-770 | C-COM-770: FF 10 | C-COM-790 | C-COM-790: FF 10 | 2024-12-04 07:00 | 2025-01-08 17:00
C-COM-790 | Not Started | P2543-R01-Oct24..4.1.3 | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-BL-1360, HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-PR-0130, HS-GN-0110, HE-HS-0190, HE-WS-0020, HE-WS-0030, ML1017-B18, HE-IC-0010, HS-GN-0410, HE-IC-0010, HE-CS-0530, HE-IC-0650, HE-IC-0490, HS-GN-0470, HE-HS-1010, HE-IC-0710, ML1033-B22, HE-I | HE-BL-1360: FF, HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-PR-0130: FS, HS-GN-0110: FS, HE-HS-0190: FS, HE-WS-0020: FS, HE-WS-0030: FS, ML1017-B18: FS, HE-IC-0010: FS, HS-GN-0410: FS, HE-IC-0010: FF, HE-CS-0530: FS, HE-IC-0650: FS, | ML1004-A04, C-56-PL-607-ME-1000, C-56-PL-607-ME-1200, C-56-PL-607-ME-1400, C-56-PL-607-ME-1600 | ML1004-A04: FS, C-56-PL-607-ME-1000: FS, C-56-PL-607-ME-1200: FS, C-56-PL-607-ME-1400: FS, C-56-PL-607-ME-1600: FS | 2025-01-09 07:00 | 2025-01-20 17:00
C-COM-850 | Not Started | P2543-R01-Oct24..4.1.4 | Issue ICR-Shutdown Requirements & Plan | CTF-1000, HE-CO-110, CTF-1010 | CTF-1000: FS, HE-CO-110: FS, CTF-1010: FS | C-COM-860 | C-COM-860: FS | 2024-12-11 07:00 | 2025-01-27 17:00
C-COM-860 | Not Started | P2543-R01-Oct24..4.1.4 | Receive Company Comments-Shutdown Requirements & Plan | C-COM-850 | C-COM-850: FS | C-COM-870 | C-COM-870: FS | 2025-01-28 07:00 | 2025-02-07 17:00
C-COM-870 | Not Started | P2543-R01-Oct24..4.1.4 | Re-Issue for Approval-Shutdown Requirements & Plan | C-COM-860, HE-CO-130 | C-COM-860: FS, HE-CO-130: FS | C-COM-880 | C-COM-880: FS | 2025-02-09 07:00 | 2025-03-25 13:00
C-COM-880 | Not Started | P2543-R01-Oct24..4.1.4 | Obtain Company Approval-Shutdown Requirements & Plan | C-COM-870 | C-COM-870: FS | C-COM-890 | C-COM-890: FS | 2025-03-25 13:00 | 2025-04-11 17:00
C-COM-890 | Not Started | P2543-R01-Oct24..4.1.4 | Final Issue for Design/ Construction-Shutdown Requirements & Plan | C-COM-880, HE-CO-150 | C-COM-880: FS, HE-CO-150: FS | CAB-5290, C-COM-840, C-56-EB2-EL-1600, C-52-OHPL-EL-2000, C-MAQTA-EL-2000 | CAB-5290: FS, C-COM-840: FS, C-56-EB2-EL-1600: FS, C-52-OHPL-EL-2000: FS, C-MAQTA-EL-2000: FS | 2025-04-13 07:00 | 2025-05-29 15:00
C-COM-800 | Not Started | P2543-R01-Oct24..4.1.6 | Issue ICR-Pre-commissioning and Commissioning Plan | HE-CO-150, ML1027-B17, HE-HS-0110, HE-PR-0830, ML1016-B12, HE-PR-0950, HE-HS-0830, HE-HS-0890, HE-PR-0770, HE-HS-0770, ML1016-B12, HE-PR-0890, HE-CO-110 | HE-CO-150: FS, ML1027-B17: FS, HE-HS-0110: FS, HE-PR-0830: FS, ML1016-B12: FS, HE-PR-0950: FS, HE-HS-0830: FS, HE-HS-0890: FS, HE-PR-0770: FS, HE-HS-0770: FS, ML1016-B12: FF, HE-PR-0890: FS, HE-CO-110: FS | C-COM-810 | C-COM-810: FS | 2025-04-08 07:00 | 2025-04-18 17:00
C-COM-810 | Not Started | P2543-R01-Oct24..4.1.6 | Receive Company Comments-Pre-commissioning and Commissioning Plan | C-COM-800 | C-COM-800: FS | C-COM-820 | C-COM-820: FS | 2025-04-20 07:00 | 2025-04-30 17:00
C-COM-820 | Not Started | P2543-R01-Oct24..4.1.6 | Re-Issue for Approval-Pre-commissioning and Commissioning Plan | C-COM-810 | C-COM-810: FS | C-COM-830 | C-COM-830: FS | 2025-05-01 07:00 | 2025-05-06 15:00
C-COM-830 | Not Started | P2543-R01-Oct24..4.1.6 | Obtain Company Approval-Pre-commissioning and Commissioning Plan | C-COM-820 | C-COM-820: FS | C-COM-840 | C-COM-840: FS | 2025-05-06 15:00 | 2025-05-19 10:00
C-COM-840 | Not Started | P2543-R01-Oct24..4.1.6 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | C-COM-830, HE-CO-150, C-COM-890 | C-COM-830: FS, HE-CO-150: FS, C-COM-890: FS | CAB-5290, PRECOM-56-PL-1000, PRECOM-56-EB2-1000, PRECOM-56-G-1000, PRECOM-56-59101-1000, PRECOM-56-PR-1000, PRECOM-52-59806-1000, PRECOM-52-EB1-1000, PRECOM-52-PR-1000, PRECOM-56-59805-1000, PRECOM-52-D-1000, PRECOM-56-59804-1000, PRECOM-56-59803-1000, PRE | CAB-5290: FS, PRECOM-56-PL-1000: FS, PRECOM-56-EB2-1000: FS, PRECOM-56-G-1000: FS, PRECOM-56-59101-1000: FS, PRECOM-56-PR-1000: FS, PRECOM-52-59806-1000: FS, PRECOM-52-EB1-1000: FS, PRECOM-52-PR-1000: FS, PRECOM-56-59805-1000: FS, PRECOM-52-D-1000: FS, PRE | 2025-05-29 15:00 | 2025-06-04 10:00
CCM-PM4500 | Not Started | P2543-R01-Oct24..4.4.2 | Approval of Commissioning Dossiers | HE-CO-190, HE-CO-150 | HE-CO-190: FS, HE-CO-150: FS | CCM-PM4540, CCM-PM4530, CCM-PM4520, HE-WS-0290 | CCM-PM4540: FS, CCM-PM4530: FS, CCM-PM4520: FS, HE-WS-0290: FS | 2025-05-06 08:00 | 2025-07-08 13:00
CCM-PM4510 | Not Started | P2543-R01-Oct24..4.4.2 | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | CCM-PM4560, CCM-PM4610, C-DBV6-PI-1000, C-4W-TI-PI-2000, C-56-PR-838-PL-1030, C-4N-H5-TPL-PL-1000, C-56-G-HT101-ME-1040, C-56-G-HT102-ME-1040, C-56-G-HT103-ME-1040, C-56-G-HT-ME-2000, C-56-PL-607-PL-1030, C-56-EB2-EL-1600, C-56-01HG-PL-CI-7800, C-4W-081-03 | CCM-PM4560: FF, CCM-PM4610: FS, C-DBV6-PI-1000: FS, C-4W-TI-PI-2000: FS, C-56-PR-838-PL-1030: FS, C-4N-H5-TPL-PL-1000: FS, C-56-G-HT101-ME-1040: FS, C-56-G-HT102-ME-1040: FS, C-56-G-HT103-ME-1040: FS, C-56-G-HT-ME-2000: FS, C-56-PL-607-PL-1030: FS, C-56-EB | CCM-PM4550, ML2019-F03, A3980, ML1999-F01, ML2039-F05, ML2029-F04, ML1040 | CCM-PM4550: FS, ML2019-F03: FS, A3980: FS, ML1999-F01: FS, ML2039-F05: FF, ML2029-F04: FS, ML1040: FS | 2025-10-09 11:00 | 2025-11-18 11:00
CCM-PM4520 | Not Started | P2543-R01-Oct24..4.4.2 | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | CCM-PM4500, CCM-PM4580, CCM-PM4590, CCM-PM4620, C-541CR-EI-1040, C-541CR-TE-1000, C-52-PL-838-PL-1030, C-36-KM-HT04-ME-1040, C-36-KM-HT03-ME-1040, C-36-KM-HT-ME-2000, C-52-OHPL-EL-1400, C-52-OHPL-EL-2000, C-52-D-HT002-ME-1040, C-52-D-HT-ME-2000, C-52-PR-83 | CCM-PM4500: FS, CCM-PM4580: FF, CCM-PM4590: FF 27, CCM-PM4620: FS, C-541CR-EI-1040: FS, C-541CR-TE-1000: FS, C-52-PL-838-PL-1030: FS, C-36-KM-HT04-ME-1040: FS, C-36-KM-HT03-ME-1040: FS, C-36-KM-HT-ME-2000: FS, C-52-OHPL-EL-1400: FS, C-52-OHPL-EL-2000: FS, | CCM-PM4540, CCM-PM4530, ML1050, ML2009-F02, ML2049-F06, A3980 | CCM-PM4540: FS, CCM-PM4530: FS, ML1050: FF, ML2009-F02: FF, ML2049-F06: FS, A3980: FS | 2025-11-03 11:00 | 2025-12-13 11:00
A3980 | Not Started | P2543-R01-Oct24..4.4.AB | Demolitionbilization | CCM-PM4540, CCM-PM4530, CCM-PM4510, CCM-PM4520, C-52-PL-838-PL-1030, C-56-PR-838-PL-1030, C-56-PL-607-PL-1030, C-52-PR-839-PL-1030, C-4N-H5-TPL-PL-1030, PRECOM-52-IDS2-1000, PRECOM-52-IDS3-1000 | CCM-PM4540: FS, CCM-PM4530: FS, CCM-PM4510: FS, CCM-PM4520: FS, C-52-PL-838-PL-1030: FS, C-56-PR-838-PL-1030: FS, C-56-PL-607-PL-1030: FS, C-52-PR-839-PL-1030: FS, C-4N-H5-TPL-PL-1030: FS, PRECOM-52-IDS2-1000: FS, PRECOM-52-IDS3-1000: FS | ML1060 | ML1060: FS |  | 2025-12-24 11:00
CAB-4400 | Not Started | P2543-R01-Oct24..4.4.AB.1 | Process | HE-PR-0610, HE-PR-0650, HE-PR-1130, ML1012-B06, HE-PR-0410, HE-PR-0590, HE-PR-0830, ML1014-B10, ML1179-B11, ML1030, HE-PR-1070, HE-PR-0470, ML1010-B14, HE-PR-0530, HE-PR-0350, HE-PR-1010, ML1219-B19, HE-PR-1300, HE-PR-1350, HE-PR-1400, HE-PR-1450, HE-PR-15 | HE-PR-0610: FS, HE-PR-0650: FS, HE-PR-1130: FS, ML1012-B06: FS, HE-PR-0410: FS, HE-PR-0590: FS, HE-PR-0830: FS, ML1014-B10: FS, ML1179-B11: FS, ML1030: FF, HE-PR-1070: FS, HE-PR-0470: FS, ML1010-B14: FS, HE-PR-0530: FS, HE-PR-0350: FS, HE-PR-1010: FS, ML12 | CAB-5310, CAB-5320, ML1060, CAB-5290, CAB-5300, CAB-4410 | CAB-5310: FF 10, CAB-5320: FF 10, ML1060: FS, CAB-5290: FF 10, CAB-5300: FF 10, CAB-4410: SS | 2025-10-13 07:30 | 2025-11-10 07:30
CAB-4410 | Not Started | P2543-R01-Oct24..4.4.AB.1 | HSE | ML1031-B20, HE-HS-0830, ML1030, HE-HS-0410, ML1013-B07, HE-HS-0170, HE-HS-0110, HE-HS-0530, HE-HS-0590, HE-HS-0950, HE-HS-0230, HE-HS-0710, HE-HS-1010, HE-HS-0050, HE-HS-0290, HE-HS-0890, ML1016-B12, HE-HS-0650, HE-HS-1070, HE-HS-0770, HE-HS-0470, HE-HS-03 | ML1031-B20: FS, HE-HS-0830: FS, ML1030: FF 3, HE-HS-0410: FS, ML1013-B07: FS, HE-HS-0170: FS, HE-HS-0110: FS, HE-HS-0530: FS, HE-HS-0590: FS, HE-HS-0950: FS, HE-HS-0230: FS, HE-HS-0710: FS, HE-HS-1010: FS, HE-HS-0050: FS, HE-HS-0290: FS, HE-HS-0890: FS, ML | CAB-5290, ML1060, CAB-5320, CAB-5310, CAB-5300, CAB-4420 | CAB-5290: FF 10, ML1060: FS, CAB-5320: FF 10, CAB-5310: FF 10, CAB-5300: FF 10, CAB-4420: SS 4 | 2025-10-15 11:30 | 2025-11-12 11:30
CAB-4420 | Not Started | P2543-R01-Oct24..4.4.AB.1 | Civil & Structural | HE-CS-1010, HE-CS-0530, HE-GS-0050, HE-CS-1310, ML1034-B25, HE-CS-1550, HE-EL-0890, ML1032-B21, HE-CS-0890, HE-CS-1490, HE-CS-0710, HE-CS-0170, HE-CS-0350, HE-CS-1250, HE-CS-1430, HE-CS-0230, HE-EL-1250, HE-CS-1370, HE-TS-0050, HE-CS-1130, ML1209-B27, HE-C | HE-CS-1010: FS, HE-CS-0530: FS, HE-GS-0050: FS, HE-CS-1310: FS, ML1034-B25: FS, HE-CS-1550: FS, HE-EL-0890: FS, ML1032-B21: FS, HE-CS-0890: FS, HE-CS-1490: FS, HE-CS-0710: FS, HE-CS-0170: FS, HE-CS-0350: FS, HE-CS-1250: FS, HE-CS-1430: FS, HE-CS-0230: FS, | ML1060, CAB-5290, CAB-5320, CAB-5310, CAB-5300, CAB-4430 | ML1060: FS, CAB-5290: FF 10, CAB-5320: FF 10, CAB-5310: FF 10, CAB-5300: FF 10, CAB-4430: SS 4 | 2025-10-21 11:30 | 2025-11-18 11:30
CAB-4430 | Not Started | P2543-R01-Oct24..4.4.AB.1 | Mechanical | ML1179-B11, HE-ME-0110, HE-ME-0170, ML1014-B10, ML1219-B19, HE-ME-0050, ML1017-B18, ML1030, HE-ME-0230, HE-ME-260, HE-ME-520, HE-ME-570, HE-IC-610, HE-ME-610, CAB-4420, HE-ME-450 | ML1179-B11: FS, HE-ME-0110: FS, HE-ME-0170: FS, ML1014-B10: FS, ML1219-B19: FS, HE-ME-0050: FS, ML1017-B18: FS, ML1030: FF 9, HE-ME-0230: FS, HE-ME-260: FS, HE-ME-520: FS, HE-ME-570: FS, HE-IC-610: FS, HE-ME-610: FS, CAB-4420: SS 4, HE-ME-450: FS | ML1060, CAB-5310, CAB-5300, CAB-5320, CAB-5290, CAB-4440 | ML1060: FS, CAB-5310: FF 10, CAB-5300: FF 10, CAB-5320: FF 10, CAB-5290: FF 10, CAB-4440: SS 4 | 2025-10-27 11:30 | 2025-11-24 11:30
CAB-4440 | Not Started | P2543-R01-Oct24..4.4.AB.1 | Piping | HE-PI-1300, HE-PI-0700, HE-PI-1180, HE-PI-0760, HE-PI-1060, HE-PR-0290, ML1015-B08, HE-PI-0940, HE-PI-0580, ML1012-B06, HE-PI-1120, HE-PI-0302, ML1017-B18, HE-PI-0050, HE-PI-0240, HE-PI-0510, ML1179-B11, HE-PI-0820, HE-PI-0880, HE-PI-1000, HE-PI-0440, HE-P | HE-PI-1300: FS, HE-PI-0700: FS, HE-PI-1180: FS, HE-PI-0760: FS, HE-PI-1060: FS, HE-PR-0290: FS, ML1015-B08: FS, HE-PI-0940: FS, HE-PI-0580: FS, ML1012-B06: FS, HE-PI-1120: FS, HE-PI-0302: FS, ML1017-B18: FS, HE-PI-0050: FS, HE-PI-0240: FS, HE-PI-0510: FS, | ML1060, CAB-5320, CAB-5290, CAB-5300, CAB-5310, CAB-4450 | ML1060: FS, CAB-5320: FF 10, CAB-5290: FF 10, CAB-5300: FF 10, CAB-5310: FF 10, CAB-4450: SS 4 | 2025-10-31 11:30 | 2025-11-28 11:30
CAB-4450 | Not Started | P2543-R01-Oct24..4.4.AB.1 | Electrical | HE-EL-0830, HE-EL-0110, HE-EL-1370, HE-EL-0710, HE-EL-0650, ML1030, ML1031-B20, HE-EL-1130, HE-EL-0950, HE-EL-0350, HE-EL-1730, HE-EL-0290, HE-EL-1850, ML1012-B06, HE-EL-1550, ML1179-B11, ML1027-B17, HE-EL-1670, HE-EL-1430, HE-EL-1310, HE-EL-1010, HE-EL-07 | HE-EL-0830: FS, HE-EL-0110: FS, HE-EL-1370: FS, HE-EL-0710: FS, HE-EL-0650: FS, ML1030: FF 15, ML1031-B20: FS, HE-EL-1130: FS, HE-EL-0950: FS, HE-EL-0350: FS, HE-EL-1730: FS, HE-EL-0290: FS, HE-EL-1850: FS, ML1012-B06: FS, HE-EL-1550: FS, ML1179-B11: FS, M | CAB-5310, ML1060, CAB-5300, CAB-5290, CAB-5320, CAB-4460 | CAB-5310: FF 10, ML1060: FS, CAB-5300: FF 10, CAB-5290: FF 10, CAB-5320: FF 10, CAB-4460: SS 4 | 2025-11-06 11:30 | 2025-12-09 11:30
CAB-4460 | Not Started | P2543-R01-Oct24..4.4.AB.1 | Instrumentation & Control | HE-IC-620, ML1014-B10, HE-IC-2150, HE-IC-0830, HE-IC-1910, HE-IC-2270, HE-IC-0590, HE-IC-0530, HE-IC-1850, ML1032-B21, ML1219-B19, HE-IC-1190, HE-IC-0110, HE-IC-2090, HE-IC-2570, ML1030, HE-IC-0950, HE-IC-0010, HE-IC-1670, HE-EL-5480, HE-IC-2390, HE-IC-025 | HE-IC-620: FS, ML1014-B10: FS, HE-IC-2150: FS, HE-IC-0830: FS, HE-IC-1910: FS, HE-IC-2270: FS, HE-IC-0590: FS, HE-IC-0530: FS, HE-IC-1850: FS, ML1032-B21: FS, ML1219-B19: FS, HE-IC-1190: FS, HE-IC-0110: FS, HE-IC-2090: FS, HE-IC-2570: FS, ML1030: FF 18, HE | ML1060, CAB-5310, CAB-5290, CAB-5300, CAB-5320, CAB-4470 | ML1060: FS, CAB-5310: FF 10, CAB-5290: FF 10, CAB-5300: FF 10, CAB-5320: FF 10, CAB-4470: SS 4 | 2025-11-12 11:30 | 2025-12-15 11:30
CAB-4470 | Not Started | P2543-R01-Oct24..4.4.AB.1 | Telecom | HE-TL-0890, HE-TL-0410, HE-TL-0230, HE-TL-0110, HE-TL-0770, HE-TL-0350, HE-TL-0290, HE-TL-0650, HE-TL-0530, HE-TL-0470, HE-TL-0710, HE-TL-0590, ML1032-B21, ML1033-B22, ML1030, ML1015-B08, HE-TL-0830, HE-TL-930, CAB-4460, HE-IC-0290, HE-IC-0230, HE-TL-2470, | HE-TL-0890: FS, HE-TL-0410: FS, HE-TL-0230: FS, HE-TL-0110: FS, HE-TL-0770: FS, HE-TL-0350: FS, HE-TL-0290: FS, HE-TL-0650: FS, HE-TL-0530: FS, HE-TL-0470: FS, HE-TL-0710: FS, HE-TL-0590: FS, ML1032-B21: FS, ML1033-B22: FS, ML1030: FF, ML1015-B08: FS, HE-T | ML1060, CAB-5320, CAB-5300, CAB-5290, CAB-5310, CAB-4480 | ML1060: FS, CAB-5320: FF 10, CAB-5300: FF 10, CAB-5290: FF 10, CAB-5310: FF 10, CAB-4480: SS 4 | 2025-11-18 11:30 | 2025-12-19 11:30
CAB-4480 | Not Started | P2543-R01-Oct24..4.4.AB.1 | Pipeline | HE-PL-3620, HE-PL-3570, HE-PL-2670, HE-PL-2730, HE-PL-2790, HE-PL-0290, HE-PL-2490, HE-PL-0710, HE-PL-0650, HE-PL-0050, HE-PL-2430, HE-PL-0230, HE-PL-2070, HE-PL-3270, HE-PL-2970, HE-PL-1430, HE-PL-2310, HE-PL-1910, HE-PL-2190, HE-PL-2850, HE-PL-3090, HE-P | HE-PL-3620: FS, HE-PL-3570: FS, HE-PL-2670: FS, HE-PL-2730: FS, HE-PL-2790: FS, HE-PL-0290: FS, HE-PL-2490: FS, HE-PL-0710: FS, HE-PL-0650: FS, HE-PL-0050: FS, HE-PL-2430: FS, HE-PL-0230: FS, HE-PL-2070: FS, HE-PL-3270: FS, HE-PL-2970: FS, HE-PL-1430: FS, | ML1989-E44, ML1060, CAB-5320, CAB-5310, CAB-5300, CAB-5290 | ML1989-E44: FF, ML1060: FS, CAB-5320: FF 10, CAB-5310: FF 10, CAB-5300: FF 10, CAB-5290: FF 10 | 2025-11-24 10:58 | 2025-12-25 10:58
CAB-5300 | Not Started | P2543-R01-Oct24..4.4.AB.2 | Quality Dossier | CAB-4430, CAB-4440, HC-GN-0230, CAB-4450, CAB-4470, HC-GN-0110, CAB-4480, CAB-4460, CAB-4410, CAB-4420, HC-GN-0050, CAB-4400 | CAB-4430: FF 10, CAB-4440: FF 10, HC-GN-0230: FS, CAB-4450: FF 10, CAB-4470: FF 10, HC-GN-0110: FS, CAB-4480: FF 10, CAB-4460: FF 10, CAB-4410: FF 10, CAB-4420: FF 10, HC-GN-0050: FS, CAB-4400: FF 10 | ML2049-F06, CAB-5310, ML1060 | ML2049-F06: FF, CAB-5310: FF, ML1060: FS | 2025-12-11 10:58 | 2026-01-09 10:58
CAB-5310 | Not Started | P2543-R01-Oct24..4.4.AB.2 | Vendor Documents Package | HM-ME-2380, HM-ME-0280, HM-PL-0220, CAB-4430, CAB-4400, CAB-4450, HM-ME-0580, CAB-4420, HM-ME-0080, HM-ME-0380, HM-ME-0480, CAB-4460, CAB-5300, CAB-4480, HM-ME-1290, HM-ME-0890, HM-ME-1090, HM-ME-0790, CAB-4470, CAB-4410, HM-ME-0180, HM-ME-0680, CAB-4440, | HM-ME-2380: FS, HM-ME-0280: FS, HM-PL-0220: FS, CAB-4430: FF 10, CAB-4400: FF 10, CAB-4450: FF 10, HM-ME-0580: FS, CAB-4420: FF 10, HM-ME-0080: FS, HM-ME-0380: FS, HM-ME-0480: FS, CAB-4460: FF 10, CAB-5300: FF, CAB-4480: FF 10, HM-ME-1290: FS, HM-ME-0890: | ML2049-F06, ML1060 | ML2049-F06: FF, ML1060: FS | 2025-12-11 10:58 | 2026-01-09 10:58
CAB-5290 | Not Started | P2543-R01-Oct24..4.4.AB.2 | General | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-PR-0130, HS-GN-0110, HE-HS-0190, HE-WS-0020, HE-WS-0030, CAB-4410, CAB-4440, C-COM-840, CAB-4420, HE-ST-0050, ML1011-A05, HE-RR-0050, ML1005-B01, HE-SV-0050, C-COM-890, CAB-4400, ML1001-A01, HC-GN-0290, CA | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-PR-0130: FS, HS-GN-0110: FS, HE-HS-0190: FS, HE-WS-0020: FS, HE-WS-0030: FS, CAB-4410: FF 10, CAB-4440: FF 10, C-COM-840: FS, CAB-4420: FF 10, HE-ST-0050: FS, ML1011-A05: FS, HE-RR-0050: FS | ML1060 | ML1060: FS | 2025-12-11 10:58 | 2026-01-09 10:58
CAB-5320 | Not Started | P2543-R01-Oct24..4.4.AB.2 | Close-out report | CAB-4440, CAB-4430, CAB-4420, CAB-4480, CAB-4400, CAB-4470, CAB-4410, CAB-4460, CAB-4450 | CAB-4440: FF 10, CAB-4430: FF 10, CAB-4420: FF 10, CAB-4480: FF 10, CAB-4400: FF 10, CAB-4470: FF 10, CAB-4410: FF 10, CAB-4460: FF 10, CAB-4450: FF 10 | ML1060, ML1989-E44 | ML1060: FS, ML1989-E44: FS | 2025-12-11 16:28 | 2026-01-09 10:58
HC-GN-0010 | Completed | P2543-R01-Oct24..1.PM.2 | Issue ICR-Planning Package | ML1002 | ML1002: FS 4 | HC-GN-0190, HC-GN-0070, HC-GN-0020 | HC-GN-0190: FS, HC-GN-0070: SS, HC-GN-0020: FS | 2023-07-31 | 2023-08-10
HC-GN-0020 | Completed | P2543-R01-Oct24..1.PM.2 | Receive Company Comments-Planning Package | HC-GN-0010 | HC-GN-0010: FS | HC-GN-0030 | HC-GN-0030: FS | 2023-08-06 | 2023-08-16
HC-GN-0030 | Completed | P2543-R01-Oct24..1.PM.2 | Re-Issue for Approval-Planning Package | HC-GN-0020 | HC-GN-0020: FS | HC-GN-0040 | HC-GN-0040: FS | 2023-08-20 | 2023-08-25
HC-GN-0040 | Completed | P2543-R01-Oct24..1.PM.2 | Obtain Company Approval-Planning Package | HC-GN-0030 | HC-GN-0030: FS | HC-GN-0050 | HC-GN-0050: FS | 2023-08-26 | 2023-09-04
HC-GN-0050 | Completed | P2543-R01-Oct24..1.PM.2 | Final Issue for Design/ Construction-Planning Package | HC-GN-0040 | HC-GN-0040: FS | HE-WS-0030, ML1002-A02, CAB-5300 | HE-WS-0030: FS, ML1002-A02: FS, CAB-5300: FS | 2023-08-28 | 2023-10-26
HC-GN-0070 | Completed | P2543-R01-Oct24..1.PM.3 | Issue ICR-Project Procedure (PEP, Numbering Procedure etc.) | HC-GN-0010 | HC-GN-0010: SS | HC-GN-0080 | HC-GN-0080: FS | 2023-07-24 | 2023-08-22
HC-GN-0080 | Completed | P2543-R01-Oct24..1.PM.3 | Receive Company Comments-Project Procedure (PEP, Numbering Procedure etc.) | HC-GN-0070 | HC-GN-0070: FS | HC-GN-0090 | HC-GN-0090: FS | 2023-08-21 | 2023-10-10
HC-GN-0090 | Completed | P2543-R01-Oct24..1.PM.3 | Re-Issue for Approval-Project Procedure (PEP, Numbering Procedure etc.) | HC-GN-0080 | HC-GN-0080: FS | HC-GN-0100 | HC-GN-0100: FS | 2023-09-10 | 2024-03-08
HC-GN-0100 | Completed | P2543-R01-Oct24..1.PM.3 | Obtain Company Approval-Project Procedure (PEP, Numbering Procedure etc.) | HC-GN-0090 | HC-GN-0090: FS | ML1003-A03, HC-GN-0110 | ML1003-A03: FF, HC-GN-0110: FS | 2023-09-20 | 2024-03-17
HC-GN-0110 | Completed | P2543-R01-Oct24..1.PM.3 | Final Issue for Design/ Construction-Project Procedure (PEP, Numbering Procedure) | HC-GN-0100 | HC-GN-0100: FS | HE-WS-0030, ML1001-A01, CAB-5300 | HE-WS-0030: FS, ML1001-A01: FS, CAB-5300: FS | 2024-03-18 | 2024-04-13
HC-GN-0200 | Completed | P2543-R01-Oct24..1.PM.6 | Receive Company Comments-QAQC procedure | HC-GN-0190 | HC-GN-0190: FS | HC-GN-0210 | HC-GN-0210: FS | 2023-10-20 | 2023-11-05
HC-GN-0190 | Completed | P2543-R01-Oct24..1.PM.6 | Issue ICR-QAQC procedure | HC-GN-0010 | HC-GN-0010: FS | HC-GN-0200 | HC-GN-0200: FS | 2023-08-07 | 2023-10-19
HC-GN-0210 | Completed | P2543-R01-Oct24..1.PM.6 | Re-Issue for Approval-QAQC procedure | HC-GN-0200 | HC-GN-0200: FS | HC-GN-0220 | HC-GN-0220: FS | 2023-11-07 | 2024-03-01
HC-GN-0220 | Completed | P2543-R01-Oct24..1.PM.6 | Obtain Company Approval-QAQC procedure | HC-GN-0210 | HC-GN-0210: FS | HC-GN-0230 | HC-GN-0230: FS | 2024-03-04 | 2024-03-17
HC-GN-0230 | Completed | P2543-R01-Oct24..1.PM.6 | Final Issue for Design/ Construction-Quality documents | HC-GN-0220 | HC-GN-0220: FS | ML1001-A01, CAB-5300 | ML1001-A01: FS, CAB-5300: FS | 2024-03-18 | 2024-04-24
HC-GN-0250 | Not Started | P2543-R01-Oct24..1.PM.4 | Issue ICR-NOC Register | HE-PI-0530, HE-PI-0320, HE-PI-0460, HE-PI-0390 | HE-PI-0530: FS, HE-PI-0320: FS, HE-PI-0460: FS, HE-PI-0390: FS | HC-GN-0260 | HC-GN-0260: FS | 2024-10-28 07:30 | 2024-11-01 17:30
HC-GN-0260 | Not Started | P2543-R01-Oct24..1.PM.4 | Receive Company Comments-NOC Register | HC-GN-0250 | HC-GN-0250: FS | HC-GN-0270 | HC-GN-0270: FS | 2024-11-04 07:30 | 2024-11-15 17:30
HC-GN-0270 | Not Started | P2543-R01-Oct24..1.PM.4 | Re-Issue for Approval-NOC Register | HC-GN-0260 | HC-GN-0260: FS | HC-GN-0280 | HC-GN-0280: FS | 2024-11-18 07:30 | 2024-11-22 17:30
HC-GN-0280 | Not Started | P2543-R01-Oct24..1.PM.4 | Obtain Company Approval-NOC Register | HC-GN-0270 | HC-GN-0270: FS | HC-GN-0290 | HC-GN-0290: FS | 2024-11-25 07:30 | 2024-12-10 17:30
HC-GN-0290 | Not Started | P2543-R01-Oct24..1.PM.4 | Final Issue for Design/ Construction-NOC Register | HC-GN-0280, HE-PI-0510, HE-PL-0290, HE-PL-0170, HE-PI-0580, HE-PL-0230 | HC-GN-0280: FS, HE-PI-0510: FS, HE-PL-0290: FS, HE-PL-0170: FS, HE-PI-0580: FS, HE-PL-0230: FS | CAB-5290 | CAB-5290: FS | 2024-12-11 07:30 | 2024-12-17 17:30
HE-CP-0010 | Completed | P2543-R01-Oct24..1.EN.15.4 | Issue ICR - Material Selection Diagram | HE-DB-0010, HE-CP-50 | HE-DB-0010: FS, HE-CP-50: FF 3 | HE-CP-0020, HE-CP-200, HE-PI-0010, HE-PI-0200 | HE-CP-0020: FS, HE-CP-200: FS, HE-PI-0010: FF 5, HE-PI-0200: FS | 2023-08-12 | 2023-08-22
HE-CP-0020 | Completed | P2543-R01-Oct24..1.EN.15.4 | Receive Company Comments - Material Selection Diagram | HE-CP-0010 | HE-CP-0010: FS | HE-CP-0030 | HE-CP-0030: FS | 2023-08-23 | 2023-08-29
HE-CP-0030 | Completed | P2543-R01-Oct24..1.EN.15.4 | Re-Issue for Approval - Material Selection Diagram | HE-CP-0020 | HE-CP-0020: FS | HE-CP-0040, HE-WS-0310 | HE-CP-0040: FS, HE-WS-0310: FS | 2023-09-08 | 2023-10-02
HE-CP-0040 | Completed | P2543-R01-Oct24..1.EN.15.4 | Obtain Company Approval - Material Selection Diagram | HE-CP-0030, HE-CP-90 | HE-CP-0030: FS, HE-CP-90: FS | HE-CP-230, HE-CP-0050 | HE-CP-230: FS, HE-CP-0050: FS | 2023-10-03 | 2023-10-13
HE-CP-0050 | Completed | P2543-R01-Oct24..1.EN.15.4 | Final Issue for Design/ Construction-Material Selection Diagram | HE-CP-0040 | HE-CP-0040: FS | HE-CP-240, CAB-4450 | HE-CP-240: FS, CAB-4450: FS | 2023-11-09 | 2023-11-22
HE-EL-0530 | Completed | P2543-R01-Oct24..1.EN.9.17 | Final Issue for Design/ Construction-Electrical Equipment Layout | HE-EL-0520 | HE-EL-0520: FS | ML1030, ML1859-E31, ML1749-E20, ML1179-B11, CAB-4450, HE-EL-1610, ML1014-B10, HE-CO-200, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1000, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C- | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1179-B11: FS, CAB-4450: FS, HE-EL-1610: SS, ML1014-B10: FS, HE-CO-200: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-EB2-EI-1000: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-E | 2024-07-23 07:30 | 2024-10-18 17:30
HE-EL-0490 | Completed | P2543-R01-Oct24..1.EN.9.17 | Issue ICR- Electrical Equipment Layout | HE-WS-0090, HE-EL-0190, HE-EL-0310 | HE-WS-0090: FS, HE-EL-0190: FS, HE-EL-0310: FS | HE-EL-1630, HE-EL-1690, HE-EL-0500, HE-EL-1570, HE-EL-1810, HE-EL-1750 | HE-EL-1630: FS 10, HE-EL-1690: FS, HE-EL-0500: FS, HE-EL-1570: FS, HE-EL-1810: FS, HE-EL-1750: FS | 2024-01-08 | 2024-03-08
HE-EL-0500 | Completed | P2543-R01-Oct24..1.EN.9.17 | Receive Company Comments- Electrical Equipment Layout | HE-EL-0490 | HE-EL-0490: FS | HE-EL-0510 | HE-EL-0510: FS | 2024-02-26 | 2024-03-08
HE-EL-0510 | Completed | P2543-R01-Oct24..1.EN.9.17 | Re-Issue for Approval- Electrical Equipment Layout | HE-EL-0210, HE-EL-0500 | HE-EL-0210: FS, HE-EL-0500: FS | HE-EL-0520, HE-EL-1590, HE-EL-1830 | HE-EL-0520: FS, HE-EL-1590: SS, HE-EL-1830: FS | 2024-03-04 | 2024-03-08
HE-EL-0520 | Completed | P2543-R01-Oct24..1.EN.9.17 | Obtain Company Approval- Electrical Equipment Layout | HE-EL-0510 | HE-EL-0510: FS | HE-EL-0530 | HE-EL-0530: FS | 2024-02-26 | 2024-03-08
HE-EL-0560 | Completed | P2543-R01-Oct24..1.EN.9.10 | Receive Company Comments-Cable Schedule | HE-EL-0550 | HE-EL-0550: FS | HE-EL-0570 | HE-EL-0570: FS | 2024-02-27 | 2024-03-27
HE-EL-0570 | Completed | P2543-R01-Oct24..1.EN.9.10 | Re-Issue for Approval-Cable Schedule | HE-EL-0560, HE-EL-0450 | HE-EL-0560: FS, HE-EL-0450: FS | HE-EL-0580 | HE-EL-0580: FS | 2024-02-27 | 2024-03-27
HE-EL-0580 | Completed | P2543-R01-Oct24..1.EN.9.10 | Obtain Company Approval-Cable Schedule | HE-EL-0570 | HE-EL-0570: FS | HE-EL-0590 | HE-EL-0590: FS | 2024-02-27 | 2024-03-27
HE-EL-0590 | In Progress | P2543-R01-Oct24..1.EN.9.10 | Final Issue for Design/ Construction-Cable Schedule | HE-EL-0580 | HE-EL-0580: FS | HE-EL-1850, ML1032-B21, CAB-4450, C-56-PL-607-EI-2000, C-56-EB2-EI-1200, C-56-EB2-EI-1210, C-56-EB2-EI-1220, C-56-PR-838-CA-1000, C-56-PR-838-CA-1030, C-56-PR-838-EI-2000, C-56-PR-838-EI-2010, C-56-PR-838-EI-2040, C-56-591-01-EI-2000, C-56-591-01-EI-2010, | HE-EL-1850: FS, ML1032-B21: FS, CAB-4450: FS, C-56-PL-607-EI-2000: FS, C-56-EB2-EI-1200: FS, C-56-EB2-EI-1210: FS, C-56-EB2-EI-1220: FS, C-56-PR-838-CA-1000: FS, C-56-PR-838-CA-1030: FS, C-56-PR-838-EI-2000: FS, C-56-PR-838-EI-2010: FS, C-56-PR-838-EI-2040 | 2024-07-18 07:30 | 2024-11-08 17:30
HE-EL-0550 | Completed | P2543-R01-Oct24..1.EN.9.10 | Issue ICR-Cable Schedule | HE-EL-0430 | HE-EL-0430: SS 5 | HE-EL-1570, HE-EL-0560 | HE-EL-1570: FS, HE-EL-0560: FS | 2024-02-27 | 2024-03-27
HE-EL-0630 | Completed | P2543-R01-Oct24..1.EN.9.31.5 | Re-Issue for Approval-Data sheet for LV Distribution board | HE-EL-0620 | HE-EL-0620: FS | HE-EL-0990, HE-EL-0640 | HE-EL-0990: FS, HE-EL-0640: FS | 2023-12-08 | 2023-12-08
HE-EL-0640 | Completed | P2543-R01-Oct24..1.EN.9.31.5 | Obtain Company Approval-Data sheet for LV Distribution board | HE-EL-0630 | HE-EL-0630: FS | ML1030, ML1859-E31, ML1749-E20, HE-EL-0650, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C-56-PR-838-EI-2030, C-56-591-01-EI-1600, C-52-598-06-EI-1210, C- | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, HE-EL-0650: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-EI-1400: FS, C-56-PR-838-EI-1810: FS, C-56-PR-838-EI-2020: FS, C-56-PR-838-EI-2030: | 2023-12-08 | 2023-12-08
HE-EL-0650 | Completed | P2543-R01-Oct24..1.EN.9.31.5 | Final Issue for Design/ Construction-Data sheet for LV Distribution board | HE-EL-0640, HE-DB-0010, HE-EL-160 | HE-EL-0640: FS, HE-DB-0010: FS, HE-EL-160: FS | HE-EL-0730, ML1030, ML1859-E31, ML1749-E20, ML1219-B29, CAB-4450, HE-EL-1010, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-52-PR-839-EI-1400, C-52-PR-839-EI-1800, C-52-PR-839-CA-1000, C-52-PR-839-TE-1410, PRECOM-52-PR-1000, C-56-PL-607- | HE-EL-0730: FS, ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1219-B29: FF 20, CAB-4450: FS, HE-EL-1010: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-52-PR-839-EI-1400: FS, C-52-PR-839-EI-1800: FS, C-52-PR-839-CA-1000: F | 2023-12-08 | 2024-01-14
HE-EL-0610 | Completed | P2543-R01-Oct24..1.EN.9.31.5 | Issue ICR- Data sheet for LV Distribution board | HE-EL-0670 | HE-EL-0670: SS | HE-EL-0970, HE-EL-0620, HE-EL-1910 | HE-EL-0970: FS, HE-EL-0620: FS, HE-EL-1910: SS | 2023-10-10 | 2023-10-20
HE-EL-0620 | Completed | P2543-R01-Oct24..1.EN.9.31.5 | Receive Company Comments-Data sheet for LV Distribution board | HE-EL-0610 | HE-EL-0610: FS | HE-EL-0630 | HE-EL-0630: FS | 2023-10-20 | 2023-10-27
HE-EL-0770 | Completed | P2543-R01-Oct24..1.EN.9.31.1 | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | HE-EL-0760, HE-DB-0010, HE-EL-160 | HE-EL-0760: FS, HE-DB-0010: FS, HE-EL-160: FS | CAB-4450, C-56-591-01-EI-1600, C-52-598-06-EI-1210, C-52-598-06-EI-1400, C-52-598-05-EI-1210, C-52-598-05-EI-1400, C-52-598-04-EI-1210, C-52-598-04-EI-1400, C-52-598-03-EI-1210, C-52-598-03-EI-1400, C-52-598-02-EI-1210, C-52-598-02-EI-1400, C-52-598-01-EI- | CAB-4450: FS, C-56-591-01-EI-1600: FS, C-52-598-06-EI-1210: FS, C-52-598-06-EI-1400: FS, C-52-598-05-EI-1210: FS, C-52-598-05-EI-1400: FS, C-52-598-04-EI-1210: FS, C-52-598-04-EI-1400: FS, C-52-598-03-EI-1210: FS, C-52-598-03-EI-1400: FS, C-52-598-02-EI-12 | 2024-09-27 07:30 | 2024-10-03 17:30
HE-EL-0730 | Completed | P2543-R01-Oct24..1.EN.9.31.1 | Issue ICR- Datasheet for Solar panel system | HE-EL-0650, HE-DB-0010, HE-EL-160 | HE-EL-0650: FS, HE-DB-0010: FS, HE-EL-160: FS | HE-EL-1870, HE-EL-0740, HE-EL-1090 | HE-EL-1870: FF 3, HE-EL-0740: FS, HE-EL-1090: FS | 2023-11-15 | 2023-11-27
HE-EL-0740 | Completed | P2543-R01-Oct24..1.EN.9.31.1 | Receive Company Comments- Datasheet for Solar panel system | HE-EL-0730 | HE-EL-0730: FS | HE-EL-0750 | HE-EL-0750: FS | 2023-11-28 | 2023-12-15
HE-EL-0750 | Completed | P2543-R01-Oct24..1.EN.9.31.1 | Re-Issue for Approval- Datasheet for Solar panel system | HE-EL-0740 | HE-EL-0740: FS | HE-EL-1090, HE-EL-0760, HE-EL-1110 | HE-EL-1090: FS, HE-EL-0760: FS, HE-EL-1110: FS | 2023-12-18 | 2023-12-29
HE-EL-0760 | Completed | P2543-R01-Oct24..1.EN.9.31.1 | Obtain Company Approval- Datasheet for Solar panel system | HE-EL-0750 | HE-EL-0750: FS | HE-EL-0770 | HE-EL-0770: FS | 2023-12-29 | 2024-01-05
HE-EL-0790 | Completed | P2543-R01-Oct24..1.EN.9.31.6 | Issue ICR-Data Sheet for LV cables | HE-EL-1910 | HE-EL-1910: FS | HE-EL-1150, HE-EL-0800, HE-EL-1960, HE-EL-2010, HE-EL-2060, HE-EL-2110, HE-EL-2160, HE-EL-1870 | HE-EL-1150: FS, HE-EL-0800: FS, HE-EL-1960: FS, HE-EL-2010: FS, HE-EL-2060: FS, HE-EL-2110: FS, HE-EL-2160: FS, HE-EL-1870: FS | 2023-11-20 | 2023-11-29
HE-EL-0800 | Completed | P2543-R01-Oct24..1.EN.9.31.6 | Receive Company Comments-Data Sheet for LV cables | HE-EL-0790 | HE-EL-0790: FS | HE-EL-0810 | HE-EL-0810: FS | 2023-11-30 | 2023-12-15
HE-EL-0810 | Completed | P2543-R01-Oct24..1.EN.9.31.6 | Re-Issue for Approval-Data Sheet for LV cables | HE-EL-0800 | HE-EL-0800: FS | HE-EL-0820 | HE-EL-0820: FS | 2023-12-29 | 2024-01-04
HE-EL-0820 | Completed | P2543-R01-Oct24..1.EN.9.31.6 | Obtain Company Approval-Data Sheet for LV cables | HE-EL-0810 | HE-EL-0810: FS | HE-EL-0830 | HE-EL-0830: FS | 2024-01-05 | 2024-01-25
HE-EL-0830 | Completed | P2543-R01-Oct24..1.EN.9.31.6 | Final Issue for Design/ Construction-Data Sheet for LV cables | HE-EL-0820, HE-DB-0010, HE-EL-160, HE-EL-1950 | HE-EL-0820: FS, HE-DB-0010: FS, HE-EL-160: FS, HE-EL-1950: FS | CAB-4450, C-56-PL-607-EI-2000, C-56-EB2-EI-1200, C-56-EB2-EI-1210, C-56-EB2-EI-1220, C-56-PR-838-CA-1000, C-56-PR-838-CA-1030, C-56-PR-838-EI-2000, C-56-PR-838-EI-2010, C-56-PR-838-EI-2040, C-56-591-01-EI-2000, C-56-591-01-EI-2010, C-52-598-06-EI-2000, C-5 | CAB-4450: FS, C-56-PL-607-EI-2000: FS, C-56-EB2-EI-1200: FS, C-56-EB2-EI-1210: FS, C-56-EB2-EI-1220: FS, C-56-PR-838-CA-1000: FS, C-56-PR-838-CA-1030: FS, C-56-PR-838-EI-2000: FS, C-56-PR-838-EI-2010: FS, C-56-PR-838-EI-2040: FS, C-56-591-01-EI-2000: FS, C | 2024-10-14 07:30 | 2024-10-23 17:30
HE-EL-0880 | Completed | P2543-R01-Oct24..1.EN.6.11.4 | Obtain Company Approval - Material Requisition for Active / Passive Shelters | HE-EL-0870 | HE-EL-0870: FS | HE-EL-0890 | HE-EL-0890: FS | 2024-03-26 | 2024-05-25
HE-EL-0890 | Completed | P2543-R01-Oct24..1.EN.6.11.4 | Final Issue for Design/ Construction-Material Requisition for Active/ Passive Shelters | HE-EL-0880, HE-CS-0050, HE-CS-1600 | HE-EL-0880: FS, HE-CS-0050: FS, HE-CS-1600: FS | ML1219-B29, CAB-4420, HM-ME-1130, HE-EL-1250 | ML1219-B29: FF, CAB-4420: FS, HM-ME-1130: FS, HE-EL-1250: FF | 2024-05-27 | 2024-07-29 17:30
HE-EL-0850 | Completed | P2543-R01-Oct24..1.EN.6.11.4 | Issue ICR - Material Requisition for Active / Passive Shelters | HE-CS-0040, HE-CS-1590 | HE-CS-0040: FS 10, HE-CS-1590: FS | HE-EL-0860, HP-ME-0560 | HE-EL-0860: FS, HP-ME-0560: FS | 2024-01-08 | 2024-01-26
HE-EL-0860 | Completed | P2543-R01-Oct24..1.EN.6.11.4 | Receive Company Comments - Material Requisition for Active / Passive Shelters | HE-EL-0850 | HE-EL-0850: FS | HE-EL-0870 | HE-EL-0870: FS | 2024-02-26 | 2024-03-08
HE-EL-0870 | Completed | P2543-R01-Oct24..1.EN.6.11.4 | Re-Issue for Approval - Material Requisition for Active / Passive Shelters | HE-EL-0860 | HE-EL-0860: FS | HE-EL-0880 | HE-EL-0880: FS | 2024-03-10 | 2024-03-25
HE-EL-0910 | Completed | P2543-R01-Oct24..1.EN.9.1.18 | Issue ICR-Material Requisition for UPS System | HE-EL-0250 | HE-EL-0250: FS | HP-ME-0360, HE-EL-0920 | HP-ME-0360: FS, HE-EL-0920: FS | 2023-12-05 | 2023-12-12
HE-EL-0920 | Completed | P2543-R01-Oct24..1.EN.9.1.18 | Receive Company Comments-Material Requisition for UPS System | HE-EL-0910 | HE-EL-0910: FS | HP-ME-0360, HE-EL-0930 | HP-ME-0360: FS, HE-EL-0930: FS | 2023-12-12 | 2023-12-27
HE-EL-0930 | Completed | P2543-R01-Oct24..1.EN.9.1.18 | Re-Issue for Approval-Material Requisition for UPS System | HE-EL-0920 | HE-EL-0920: FS | HE-EL-0940 | HE-EL-0940: FS | 2024-02-26 | 2024-03-29
HE-EL-0940 | Completed | P2543-R01-Oct24..1.EN.9.1.18 | Obtain Company Approval-Material Requisition for UPS System | HE-EL-0930 | HE-EL-0930: FS | HE-EL-0950 | HE-EL-0950: FS | 2024-03-07 | 2024-03-29
HE-EL-0950 | Completed | P2543-R01-Oct24..1.EN.9.1.18 | Final Issue for Design/ Construction-Material Requisition for UPS System | HE-EL-0940, HE-EL-1860 | HE-EL-0940: FS, HE-EL-1860: FS | CAB-4450, HM-ME-0730, HE-EL-1370 | CAB-4450: FS, HM-ME-0730: FS, HE-EL-1370: FS | 2024-07-01 07:30 | 2024-07-22 17:30
HE-EL-1010 | Completed | P2543-R01-Oct24..1.EN.9.1.15 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | HE-EL-1000, HE-EL-0650 | HE-EL-1000: FS, HE-EL-0650: FS | ML1030, ML1859-E31, ML1749-E20, ML1219-B29, ML1027-B17, CAB-4450, HE-EL-1430, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C-56-PR-838-EI-2030, C-56-591-0 | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1219-B29: FF, ML1027-B17: FS, CAB-4450: FS, HE-EL-1430: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-EI-1400: FS, C-56-PR-838-EI-1810: FS, | 2024-04-26 | 2024-05-18
HE-EL-0970 | Completed | P2543-R01-Oct24..1.EN.9.1.15 | Issue ICR-Material Requisition for Distribution Boards | HE-EL-0090, HE-EL-0610 | HE-EL-0090: FS, HE-EL-0610: FS | HE-EL-1090, HE-EL-0980, HP-ME-0410 | HE-EL-1090: FS, HE-EL-0980: FS, HP-ME-0410: FS | 2024-01-29 | 2024-02-20
HE-EL-0980 | Completed | P2543-R01-Oct24..1.EN.9.1.15 | Receive Company Comments-Material Requisition for Distribution Boards | HE-EL-0970 | HE-EL-0970: FS | HE-EL-0990 | HE-EL-0990: FS | 2024-02-26 | 2024-03-01
HE-EL-0990 | Completed | P2543-R01-Oct24..1.EN.9.1.15 | Re-Issue for Approval-Material Requisition for Distribution Boards | HE-EL-0630, HE-EL-0980 | HE-EL-0630: FS, HE-EL-0980: FS | HE-EL-1000 | HE-EL-1000: FS | 2024-03-04 | 2024-04-18
HE-EL-1000 | Completed | P2543-R01-Oct24..1.EN.9.1.15 | Obtain Company Approval-Material Requisition for Distribution Boards | HE-EL-0990 | HE-EL-0990: FS | HE-EL-1010 | HE-EL-1010: FS | 2024-04-19 | 2024-04-26
HE-EL-1130 | Completed | P2543-R01-Oct24..1.EN.9.1.24 | Final Issue for Design/ Construction-Material Requisition for Solar Panels | HE-EL-1120 | HE-EL-1120: FS | CAB-4450, HM-ME-1030, HE-EL-1310 | CAB-4450: FS, HM-ME-1030: FS, HE-EL-1310: FS | 2024-06-24 | 2024-07-02 17:30
HE-EL-1090 | Completed | P2543-R01-Oct24..1.EN.9.1.24 | Issue ICR-Material Requisition for Solar Panels | HE-EL-0970, HE-EL-0730, HE-EL-0750, HE-EL-1870, HE-EL-1890 | HE-EL-0970: FS, HE-EL-0730: FS, HE-EL-0750: FS, HE-EL-1870: FS, HE-EL-1890: FS | HE-EL-1960, HE-EL-1150, HE-EL-1100, HP-ME-0510 | HE-EL-1960: FS, HE-EL-1150: FS, HE-EL-1100: FS, HP-ME-0510: FS | 2024-01-15 | 2024-01-26
HE-EL-1100 | Completed | P2543-R01-Oct24..1.EN.9.1.24 | Receive Company Comments-Material Requisition for Solar Panels | HE-EL-1090 | HE-EL-1090: FS | HE-EL-1110 | HE-EL-1110: FS | 2024-03-04 | 2024-03-17
HE-EL-1110 | Completed | P2543-R01-Oct24..1.EN.9.1.24 | Re-Issue for Approval-Material Requisition for Solar Panels | HE-EL-0750, HE-EL-1100, HE-EL-1890 | HE-EL-0750: FS, HE-EL-1100: FS, HE-EL-1890: FS | HE-EL-1120 | HE-EL-1120: FS | 2024-06-12 | 2024-06-14
HE-EL-1120 | Completed | P2543-R01-Oct24..1.EN.9.1.24 | Obtain Company Approval-Material Requisition for Solar Panels | HE-EL-1110 | HE-EL-1110: FS | HP-ME-0520, HE-EL-1130 | HP-ME-0520: FF, HE-EL-1130: FS | 2024-06-14 | 2024-06-20
HE-EL-1150 | Completed | P2543-R01-Oct24..1.EN.9.1.20 | Issue ICR-Material Requisition for Power & Control Cables | HE-EL-1090, HE-EL-0790, HE-EL-0430, HE-EL-1910 | HE-EL-1090: FS, HE-EL-0790: FS, HE-EL-0430: FS, HE-EL-1910: FS | HP-BK-0010, HE-EL-1160 | HP-BK-0010: FS, HE-EL-1160: FS | 2024-05-03 | 2024-05-14
HE-EL-1160 | Completed | P2543-R01-Oct24..1.EN.9.1.20 | Receive Company Comments-Material Requisition for Power & Control Cables | HE-EL-1150 | HE-EL-1150: FS | HE-EL-1170 | HE-EL-1170: FS | 2024-04-09 | 2024-05-27
HE-EL-1170 | Completed | P2543-R01-Oct24..1.EN.9.1.20 | Re-Issue for Approval-Material Requisition for Power & Control Cables | HE-EL-1160, HE-EL-0450 | HE-EL-1160: FS, HE-EL-0450: FS | HE-EL-1180 | HE-EL-1180: FS | 2024-08-01 07:30 | 2024-08-07 17:30
HE-EL-1180 | Completed | P2543-R01-Oct24..1.EN.9.1.20 | Obtain Company Approval-Material Requisition for Power & Control Cables | HE-EL-1170 | HE-EL-1170: FS | HE-EL-1190 | HE-EL-1190: FS | 2024-08-08 07:30 | 2024-08-14
HE-EL-1190 | Completed | P2543-R01-Oct24..1.EN.9.1.20 | Final Issue for Design/ Construction-Material Requisition for Power & Control Cables | HE-EL-1180 | HE-EL-1180: FS | HM-EL-0020, CAB-4450, HE-EL-1550 | HM-EL-0020: FS, CAB-4450: FS, HE-EL-1550: FS | 2024-08-15 07:30 | 2024-08-26 17:30
HE-EL-1210 | Completed | P2543-R01-Oct24..1.EN.6.2.29 | Issue ICR - TBE for Active / Passive Shelters | HP-ME-0560 | HP-ME-0560: FS | HE-EL-1220, HP-ME-0570 | HE-EL-1220: FS, HP-ME-0570: SS | 2024-05-03 | 2024-05-20
HE-EL-1220 | Completed | P2543-R01-Oct24..1.EN.6.2.29 | Receive Company Comments - TBE for Active / Passive Shelters | HE-EL-1210 | HE-EL-1210: FS | HE-EL-1230 | HE-EL-1230: FS | 2024-05-21 | 2024-06-03
HE-EL-1230 | Completed | P2543-R01-Oct24..1.EN.6.2.29 | Re-Issue for Approval - TBE for Active / Passive Shelters | HE-EL-1220 | HE-EL-1220: FS | HE-EL-1240 | HE-EL-1240: FS | 2024-06-04 | 2024-06-06
HE-EL-1240 | Completed | P2543-R01-Oct24..1.EN.6.2.29 | Obtain Company Approval - TBE for Active / Passive Shelters | HE-EL-1230 | HE-EL-1230: FS | HE-EL-1250, HP-ME-0570 | HE-EL-1250: FS, HP-ME-0570: FF | 2024-06-07 | 2024-06-13
HE-EL-1250 | Completed | P2543-R01-Oct24..1.EN.6.2.29 | Final Issue for Design/ Construction-TBE for Active/ Passive Shelters | HE-EL-1240, HE-EL-0890 | HE-EL-1240: FS, HE-EL-0890: FF | CAB-4420 | CAB-4420: FS | 2024-06-28 | 2024-09-30 17:30
HE-EL-1270 | Completed | P2543-R01-Oct24..1.EN.9.6.8 | Issue ICR-TBE for Solar Panels | HP-ME-0510 | HP-ME-0510: FS | HE-EL-1280, HP-ME-0520 | HE-EL-1280: FS, HP-ME-0520: SS | 2024-02-29 | 2024-05-13
HE-EL-1280 | Completed | P2543-R01-Oct24..1.EN.9.6.8 | Receive Company Comments-TBE for Solar Panels | HE-EL-1270 | HE-EL-1270: FS | HE-EL-1290 | HE-EL-1290: FS | 2024-06-05 | 2024-06-12
HE-EL-1290 | Completed | P2543-R01-Oct24..1.EN.9.6.8 | Re-Issue for Approval-TBE for Solar Panels | HE-EL-1280 | HE-EL-1280: FS | HE-EL-1300 | HE-EL-1300: FS | 2024-09-02 07:30 | 2024-09-13 17:30
HE-EL-1300 | Completed | P2543-R01-Oct24..1.EN.9.6.8 | Obtain Company Approval-TBE for Solar Panels | HE-EL-1290 | HE-EL-1290: FS | HE-EL-1310 | HE-EL-1310: FS | 2024-09-16 07:30 | 2024-09-27 17:30
HE-EL-1310 | Completed | P2543-R01-Oct24..1.EN.9.6.8 | Final Issue for Design/ Construction-TBE for Solar Panels | HE-EL-1300, HE-EL-1130 | HE-EL-1300: FS, HE-EL-1130: FS | CAB-4450 | CAB-4450: FS | 2024-09-27 07:30 | 2024-10-03 17:30
HE-EL-1330 | Completed | P2543-R01-Oct24..1.EN.9.6.27 | Issue ICR-TBE for UPS System | HP-ME-0360 | HP-ME-0360: FS | HE-EL-1340, HP-ME-0370 | HE-EL-1340: FS, HP-ME-0370: SS | 2023-12-15 | 2024-03-15
HE-EL-1340 | Completed | P2543-R01-Oct24..1.EN.9.6.27 | Receive Company Comments-TBE for UPS System | HE-EL-1330 | HE-EL-1330: FS | HE-EL-1350 | HE-EL-1350: FS | 2024-03-19 | 2024-03-26
HE-EL-1350 | Completed | P2543-R01-Oct24..1.EN.9.6.27 | Re-Issue for Approval-TBE for UPS System | HE-EL-1340 | HE-EL-1340: FS | HE-EL-1360 | HE-EL-1360: FS | 2024-03-24 | 2024-04-30
HE-EL-1360 | Completed | P2543-R01-Oct24..1.EN.9.6.27 | Obtain Company Approval-TBE for UPS System | HE-EL-1350 | HE-EL-1350: FS | HE-EL-1370, HP-ME-0370 | HE-EL-1370: FS, HP-ME-0370: FF | 2024-05-01 | 2024-05-16
HE-EL-1370 | Completed | P2543-R01-Oct24..1.EN.9.6.27 | Final Issue for Design/ Construction-TBE for UPS System | HE-EL-1360, HE-EL-0950 | HE-EL-1360: FS, HE-EL-0950: FS | CAB-4450 | CAB-4450: FS | 2024-08-26 07:30 | 2024-08-30 17:30
HE-EL-1420 | Completed | P2543-R01-Oct24..1.EN.9.6.28 | Obtain Company Approval-TBE for Distribution Boards | HE-EL-1410 | HE-EL-1410: FS | HE-EL-1430, HP-ME-0420 | HE-EL-1430: FS, HP-ME-0420: FF | 2024-07-01 07:30 | 2024-07-23 17:30
HE-EL-1430 | Completed | P2543-R01-Oct24..1.EN.9.6.28 | Final Issue for Design/ Construction-TBE for Distribution Boards | HE-EL-1420, HE-EL-1010 | HE-EL-1420: FS, HE-EL-1010: FS | HE-EL-1550, CAB-4450 | HE-EL-1550: FS, CAB-4450: FS | 2024-10-01 07:30 | 2024-10-07 17:30
HE-EL-1390 | Completed | P2543-R01-Oct24..1.EN.9.6.28 | Issue ICR-TBE for Distribution Boards | HP-ME-0410, HP-ME-0410 | HP-ME-0410: FS, HP-ME-0410: FF | HE-EL-1400, HP-ME-0420 | HE-EL-1400: FS, HP-ME-0420: SS | 2024-05-15 | 2024-05-29 17:30
HE-EL-1400 | Completed | P2543-R01-Oct24..1.EN.9.6.28 | Receive Company Comments-TBE for Distribution Boards | HE-EL-1390 | HE-EL-1390: FS | HE-EL-1410 | HE-EL-1410: FS | 2024-05-30 07:30 | 2024-06-13 17:30
HE-EL-1410 | Completed | P2543-R01-Oct24..1.EN.9.6.28 | Re-Issue for Approval-TBE for Distribution Boards | HE-EL-1400 | HE-EL-1400: FS | HE-EL-1420 | HE-EL-1420: FS | 2024-06-14 07:30 | 2024-06-28 17:30
HE-EL-1510 | Completed | P2543-R01-Oct24..1.EN.9.6.26 | Issue ICR-TBE for Power & Control Cables | HP-BK-0010 | HP-BK-0010: FS | HE-EL-1520, HP-BK-0120 | HE-EL-1520: FS, HP-BK-0120: SS | 2024-06-01 07:30 | 2024-06-05 17:30
HE-EL-1520 | Completed | P2543-R01-Oct24..1.EN.9.6.26 | Receive Company Comments-TBE for Power & Control Cables | HE-EL-1510 | HE-EL-1510: FS | HE-EL-1530 | HE-EL-1530: FS | 2024-06-05 07:30 | 2024-06-08 17:30
HE-EL-1530 | Completed | P2543-R01-Oct24..1.EN.9.6.26 | Re-Issue for Approval-TBE for Power & Control Cables | HE-EL-1520 | HE-EL-1520: FS | HE-EL-1540 | HE-EL-1540: FS | 2024-06-09 07:30 | 2024-09-16 17:30
HE-EL-1540 | Completed | P2543-R01-Oct24..1.EN.9.6.26 | Obtain Company Approval-TBE for Power & Control Cables | HE-EL-1530 | HE-EL-1530: FS | HE-EL-1550 | HE-EL-1550: FS | 2024-10-01 07:30 | 2024-10-07 17:30
HE-EL-1550 | Completed | P2543-R01-Oct24..1.EN.9.6.26 | Final Issue for Design/ Construction-TBE for Power & Control Cables | HE-EL-1430, HE-EL-1540, HE-EL-1190 | HE-EL-1430: FS, HE-EL-1540: FS, HE-EL-1190: FS | C-DBV6-EI-2000, C-MAQTA-EI-2000, C-541CR-EI-1000, CAB-4450 | C-DBV6-EI-2000: FS, C-MAQTA-EI-2000: FS, C-541CR-EI-1000: FS, CAB-4450: FS | 2024-10-08 07:30 | 2024-10-14 17:30
HE-EL-1590 | Completed | P2543-R01-Oct24..1.EN.9.11 | Re-Issue for Approval-Cable Routing Layout | HE-EL-0510, HE-EL-1580 | HE-EL-0510: SS, HE-EL-1580: FS | HE-EL-1600 | HE-EL-1600: FS | 2024-03-16 | 2024-05-31
HE-EL-1600 | Completed | P2543-R01-Oct24..1.EN.9.11 | Obtain Company Approval-Cable Routing Layout | HE-EL-1590 | HE-EL-1590: FS | HE-EL-1610 | HE-EL-1610: FS | 2024-05-31 | 2024-06-06
HE-EL-1610 | Not Started | P2543-R01-Oct24..1.EN.9.11 | Final Issue for Design/ Construction-Cable Routing Layout | HE-EL-0170, HE-CP-190, HE-EL-1600, HE-EL-0530, HE-EL-0290 | HE-EL-0170: FF, HE-CP-190: FF, HE-EL-1600: FS, HE-EL-0530: SS, HE-EL-0290: FS | HE-EL-1850, CAB-4450, C-56-PL-607-EI-2000, C-56-EB2-EI-1200, C-56-EB2-EI-1210, C-56-EB2-EI-1220, C-56-PR-838-CA-1000, C-56-PR-838-CA-1030, C-56-PR-838-EI-2000, C-56-PR-838-EI-2010, C-56-PR-838-EI-2040, C-56-591-01-EI-2000, C-56-591-01-EI-2010, C-52-598-06- | HE-EL-1850: FS, CAB-4450: FS, C-56-PL-607-EI-2000: FS, C-56-EB2-EI-1200: FS, C-56-EB2-EI-1210: FS, C-56-EB2-EI-1220: FS, C-56-PR-838-CA-1000: FS, C-56-PR-838-CA-1030: FS, C-56-PR-838-EI-2000: FS, C-56-PR-838-EI-2010: FS, C-56-PR-838-EI-2040: FS, C-56-591-0 | 2024-12-11 07:30 | 2024-12-17 17:30
HE-EL-1570 | Completed | P2543-R01-Oct24..1.EN.9.11 | Issue ICR-Cable Routing Layout | HE-EL-0550, HE-PI-0560, HE-EL-0490 | HE-EL-0550: FS, HE-PI-0560: FS, HE-EL-0490: FS | HE-EL-1690, HE-EL-1580 | HE-EL-1690: FS, HE-EL-1580: FS | 2024-03-06 | 2024-03-11
HE-EL-1580 | Completed | P2543-R01-Oct24..1.EN.9.11 | Receive Company Comments-Cable Routing Layout | HE-EL-1570 | HE-EL-1570: FS | HE-EL-1590 | HE-EL-1590: FS | 2024-03-12 | 2024-03-15
HE-EL-1630 | Completed | P2543-R01-Oct24..1.EN.9.12 | Issue ICR-Earthing Layout | HE-PI-0560, HE-EL-0490 | HE-PI-0560: FS, HE-EL-0490: FS 10 | HP-BK-0110, HE-EL-1640, HP-BK-0160 | HP-BK-0110: FS, HE-EL-1640: FS, HP-BK-0160: FS | 2024-03-13 | 2024-03-18
HE-EL-1650 | Completed | P2543-R01-Oct24..1.EN.9.12 | Re-Issue for Approval-Earthing Layout | HE-EL-1640 | HE-EL-1640: FS | HE-EL-1660 | HE-EL-1660: FS | 2024-03-15 | 2024-03-18
HE-EL-1660 | Completed | P2543-R01-Oct24..1.EN.9.12 | Obtain Company Approval-Earthing Layout | HE-EL-1650 | HE-EL-1650: FS | HE-EL-1670 | HE-EL-1670: FS | 2024-03-19 | 2024-03-20
HE-EL-1670 | In Progress | P2543-R01-Oct24..1.EN.9.12 | Final Issue for Design/ Construction-Earthing Layout | HE-EL-1660 | HE-EL-1660: FS | HE-EL-5530, ML1030, ML1859-E31, ML1749-E20, ML1219-B29, HE-EL-1850, CAB-4450, ML1032-B21, ML1032-B21, HE-CO-200, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1000, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, | HE-EL-5530: FF, ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1219-B29: FF, HE-EL-1850: FS, CAB-4450: FS, ML1032-B21: FS, ML1032-B21: FF, HE-CO-200: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-EB2-EI-1000: FS, C-56-P | 2024-10-01 07:30 | 2024-11-01 17:30
HE-EL-1640 | Completed | P2543-R01-Oct24..1.EN.9.12 | Receive Company Comments-Earthing Layout | HE-EL-1630 | HE-EL-1630: FS | HE-EL-1650 | HE-EL-1650: FS | 2024-03-04 | 2024-03-14
HE-EL-1720 | Completed | P2543-R01-Oct24..1.EN.9.13 | Obtain Company Approval-Lighting Layout | HE-EL-1710 | HE-EL-1710: FS | HE-EL-1730 | HE-EL-1730: FS | 2024-07-01 07:30 | 2024-07-15 17:30
HE-EL-1730 | In Progress | P2543-R01-Oct24..1.EN.9.13 | Final Issue for Design/ Construction-Lighting Layout | HE-EL-1720 | HE-EL-1720: FS | ML1030, ML1859-E31, ML1749-E20, ML1219-B29, CAB-4450, HE-EL-1850, HE-CO-200, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1000, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C-56-PR-838-EI | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1219-B29: FF, CAB-4450: FS, HE-EL-1850: FS, HE-CO-200: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-EB2-EI-1000: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-EI-1400: FS, C-56 | 2024-10-14 07:30 | 2024-11-01 17:30
HE-EL-1690 | Completed | P2543-R01-Oct24..1.EN.9.13 | Issue ICR-Lighting Layout | HE-EL-1570, HE-EL-0490 | HE-EL-1570: FS, HE-EL-0490: FS | HE-EL-1700 | HE-EL-1700: FS | 2024-03-14 | 2024-03-28
HE-EL-1700 | Completed | P2543-R01-Oct24..1.EN.9.13 | Receive Company Comments-Lighting Layout | HE-EL-1690 | HE-EL-1690: FS | HE-EL-1710 | HE-EL-1710: FS | 2024-04-10 | 2024-04-24
HE-EL-1710 | Completed | P2543-R01-Oct24..1.EN.9.13 | Re-Issue for Approval-Lighting Layout | HE-EL-1700 | HE-EL-1700: FS | HE-EL-1720 | HE-EL-1720: FS | 2024-06-17 07:30 | 2024-06-30 17:30
HE-EL-1750 | Completed | P2543-R01-Oct24..1.EN.9.19 | Issue ICR- Electrical Installation Drawings | HE-EL-0490 | HE-EL-0490: FS | HE-EL-1760 | HE-EL-1760: FS | 2024-02-14 | 2024-04-22
HE-EL-1760 | Completed | P2543-R01-Oct24..1.EN.9.19 | Receive Company Comments- Electrical Installation Drawings | HE-EL-1750 | HE-EL-1750: FS | HE-EL-1770 | HE-EL-1770: FS | 2024-05-06 07:30 | 2024-05-27 17:30
HE-EL-1770 | Completed | P2543-R01-Oct24..1.EN.9.19 | Re-Issue for Approval- Electrical Installation Drawings | HE-EL-1760 | HE-EL-1760: FS | HE-EL-1780 | HE-EL-1780: FS | 2024-05-28 | 2024-06-14 17:30
HE-EL-1780 | Completed | P2543-R01-Oct24..1.EN.9.19 | Obtain Company Approval- Electrical Installation Drawings | HE-EL-1770 | HE-EL-1770: FS | HE-EL-1790 | HE-EL-1790: FS | 2024-06-17 07:30 | 2024-06-28 17:30
HE-EL-1790 | In Progress | P2543-R01-Oct24..1.EN.9.19 | Final Issue for Design/ Construction-Electrical Installation Drawings | HE-EL-1780 | HE-EL-1780: FS | ML1030, ML1859-E31, ML1749-E20, ML1219-B29, HE-EL-1850, CAB-4450, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1000, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C-56-PR-838-EI-2030, C-56 | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1219-B29: FF, HE-EL-1850: FS, CAB-4450: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-EB2-EI-1000: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-EI-1400: FS, C-56-PR-838-EI-1810 | 2024-10-21 07:30 | 2024-11-01 17:30
HE-EL-1830 | Not Started | P2543-R01-Oct24..1.EN.9.16 | Electrical 2nd MTO | HE-EL-0510, HE-EL-1810 | HE-EL-0510: FS, HE-EL-1810: FS | HE-EL-1850 | HE-EL-1850: FS | 2024-10-28 07:30 | 2024-11-15 17:30
HE-EL-1850 | Not Started | P2543-R01-Oct24..1.EN.9.16 | Electrical 3rd MTO | HE-EL-1610, HE-EL-0590, HE-EL-1670, HE-EL-1730, HE-EL-1790, HE-EL-1830 | HE-EL-1610: FS, HE-EL-0590: FS, HE-EL-1670: FS, HE-EL-1730: FS, HE-EL-1790: FS, HE-EL-1830: FS | ML1219-B29, CAB-4450, HP-BK-0430 | ML1219-B29: FF, CAB-4450: FS, HP-BK-0430: FF | 2024-12-18 07:30 | 2025-01-08 17:30
HE-EL-1810 | Completed | P2543-R01-Oct24..1.EN.9.16 | Electrical 1st MTO | HE-EL-0490 | HE-EL-0490: FS | HP-BK-0420, HE-EL-1830 | HP-BK-0420: FS, HE-EL-1830: FS | 2024-08-02 07:30 | 2024-08-15 17:30
HE-EL-0070 | Completed | P2543-R01-Oct24..1.EN.9.7 | Issue ICR-Update /New Load List | HE-PI-0530 | HE-PI-0530: FS | HE-EL-0080, HE-EL-0310, HE-EL-0190, HE-EL-0130, HE-EL-0250 | HE-EL-0080: FS, HE-EL-0310: FS, HE-EL-0190: FS, HE-EL-0130: FS, HE-EL-0250: FS | 2023-10-02 | 2023-10-17
HE-EL-0080 | Completed | P2543-R01-Oct24..1.EN.9.7 | Receive Company Comments-Update /New Load List | HE-EL-0070 | HE-EL-0070: FS | HE-EL-0090, HE-EL-0140 | HE-EL-0090: FS, HE-EL-0140: FS | 2023-10-18 | 2023-10-26
HE-EL-0090 | Completed | P2543-R01-Oct24..1.EN.9.7 | Re-Issue for Approval-Update /New Load List | HE-EL-0080, HE-PR-0140 | HE-EL-0080: FS, HE-PR-0140: FS | HE-EL-0970, HE-EL-0150, HE-EL-0100 | HE-EL-0970: FS, HE-EL-0150: FS, HE-EL-0100: FS | 2023-11-21 | 2023-11-30
HE-EL-0110 | Completed | P2543-R01-Oct24..1.EN.9.7 | Final Issue for Design/ Construction-Load List | HE-EL-0100 | HE-EL-0100: FS | HE-EL-0230, CAB-4450, HE-EL-0170 | HE-EL-0230: FS, CAB-4450: FS, HE-EL-0170: FS | 2023-12-25 | 2024-03-11
HE-EL-0100 | Completed | P2543-R01-Oct24..1.EN.9.7 | Obtain Company Approval-Update /New Load List | HE-EL-0090 | HE-EL-0090: FS | HE-EL-0110 | HE-EL-0110: FS | 2023-12-01 | 2023-12-18
HE-EL-0130 | Completed | P2543-R01-Oct24..1.EN.9.A101 | Issue ICR- Adequacy report of the Power supply requirements | HE-EL-0070, HE-DB-0010, HE-EL-160 | HE-EL-0070: FS, HE-DB-0010: FS, HE-EL-160: FS | HE-EL-0140 | HE-EL-0140: FS | 2024-09-27 07:30 | 2024-10-01 17:30
HE-EL-0140 | Not Started | P2543-R01-Oct24..1.EN.9.A101 | Receive Company Comments- Adequacy report of the Power supply requirements | HE-EL-0130, HE-EL-0080 | HE-EL-0130: FS, HE-EL-0080: FS | HE-EL-0150 | HE-EL-0150: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HE-EL-0150 | Not Started | P2543-R01-Oct24..1.EN.9.A101 | Re-Issue for Approval- Adequacy report of the Power supply requirements | HE-EL-0140, HE-EL-0090 | HE-EL-0140: FS, HE-EL-0090: FS | HE-EL-0160 | HE-EL-0160: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-EL-0160 | Not Started | P2543-R01-Oct24..1.EN.9.A101 | Obtain Company Approval- Adequacy report of the Power supply requirements | HE-EL-0150 | HE-EL-0150: FS | HE-EL-0170 | HE-EL-0170: FS | 2024-11-25 07:30 | 2024-12-10 17:30
HE-EL-0170 | Not Started | P2543-R01-Oct24..1.EN.9.A101 | Final Issue for Design/ Construction-Electrical Adequacy Check Report | HE-EL-0110, HE-EL-0160, HE-DB-0010, HE-EL-160 | HE-EL-0110: FS, HE-EL-0160: FS, HE-DB-0010: FS, HE-EL-160: FS | HE-EL-1610, ML1219-B29, CAB-4450 | HE-EL-1610: FF, ML1219-B29: FF, CAB-4450: FS | 2024-12-11 07:30 | 2024-12-17 17:30
HE-EL-0230 | Completed | P2543-R01-Oct24..1.EN.9.2 | Final Issue for Design/ Construction-Single Line Diagrams for LV Distribution Board | HE-EL-0110, HE-EL-0220, HE-DB-0010, HE-EL-160 | HE-EL-0110: FS, HE-EL-0220: FS, HE-DB-0010: FS, HE-EL-160: FS | HE-EL-5530, ML1031-B20, CAB-4450 | HE-EL-5530: FF 5, ML1031-B20: FS, CAB-4450: FS | 2024-05-31 | 2024-10-25 17:30
HE-EL-0190 | Completed | P2543-R01-Oct24..1.EN.9.2 | Issue ICR-Single Line Diagrams for LV Switchgear | HE-EL-0070, HE-DB-0010, HE-EL-160 | HE-EL-0070: FS, HE-DB-0010: FS, HE-EL-160: FS | HE-EL-0250, HE-EL-0200, HE-EL-0430, HE-EL-0490 | HE-EL-0250: FS, HE-EL-0200: FS, HE-EL-0430: FS, HE-EL-0490: FS | 2024-02-26 | 2024-03-08
HE-EL-0200 | Completed | P2543-R01-Oct24..1.EN.9.2 | Receive Company Comments-Single Line Diagrams for LV Switchgear | HE-EL-0190 | HE-EL-0190: FS | HE-EL-0210 | HE-EL-0210: FS | 2024-03-10 | 2024-03-25
HE-EL-0210 | Completed | P2543-R01-Oct24..1.EN.9.2 | Re-Issue for Approval-Single Line Diagrams for LV Switchgear | HE-EL-0200 | HE-EL-0200: FS | HE-EL-0220, HE-EL-0510 | HE-EL-0220: FS, HE-EL-0510: FS | 2024-03-31 | 2024-04-17
HE-EL-0220 | Completed | P2543-R01-Oct24..1.EN.9.2 | Obtain Company Approval-Single Line Diagrams for LV Switchgear | HE-EL-0210 | HE-EL-0210: FS | HE-EL-0230 | HE-EL-0230: FS | 2024-04-18 07:30 | 2024-05-25 17:30
HE-EL-0250 | Completed | P2543-R01-Oct24..1.EN.9.22 | Issue ICR - UPS SLD | HE-EL-0190, HE-EL-0070, HE-DB-0010, HE-EL-160 | HE-EL-0190: FS, HE-EL-0070: FS, HE-DB-0010: FS, HE-EL-160: FS | HE-EL-0910, HE-EL-0260 | HE-EL-0910: FS, HE-EL-0260: FS | 2023-10-15 | 2023-10-26
HE-EL-0260 | Completed | P2543-R01-Oct24..1.EN.9.22 | Receive Company Comments - UPS SLD | HE-EL-0250 | HE-EL-0250: FS | HE-EL-0270 | HE-EL-0270: FS 30 | 2023-11-13 | 2023-11-23
HE-EL-0270 | Completed | P2543-R01-Oct24..1.EN.9.22 | Re-Issue for Approval - UPS SLD | HE-EL-0260 | HE-EL-0260: FS 30 | HE-EL-0280 | HE-EL-0280: FS | 2024-03-30 | 2024-04-17
HE-EL-0280 | Completed | P2543-R01-Oct24..1.EN.9.22 | Obtain Company Approval - UPS SLD | HE-EL-0270 | HE-EL-0270: FS | HE-EL-0290 | HE-EL-0290: FS | 2024-05-27 | 2024-06-04
HE-EL-0290 | Completed | P2543-R01-Oct24..1.EN.9.22 | Final Issue for Design/ Construction-UPS SLD | HE-EL-0280, HE-DB-0010, HE-EL-160 | HE-EL-0280: FS, HE-DB-0010: FS, HE-EL-160: FS | ML1030, ML1859-E31, ML1749-E20, ML1219-B29, CAB-4450, ML1031-B20, HE-EL-1610, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-52-PR-839-EI-1400, C-52-PR-839-EI-1800, C-52-PR-839-CA-1000, C-52-PR-839-TE-1410, PRECOM-52-PR-1000, C-56-PL-607- | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1219-B29: FF, CAB-4450: FS, ML1031-B20: FS, HE-EL-1610: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-52-PR-839-EI-1400: FS, C-52-PR-839-EI-1800: FS, C-52-PR-839-CA-1000: FF, | 2024-05-31 07:30 | 2024-10-25
HE-EL-0310 | Completed | P2543-R01-Oct24..1.EN.9.14 | Issue ICR-Solar Panel System SLDs | HE-EL-0070, HE-DB-0010, HE-EL-160 | HE-EL-0070: FS, HE-DB-0010: FS, HE-EL-160: FS | HE-EL-0370, HE-EL-0320, HE-EL-0430, HE-EL-0490 | HE-EL-0370: FS, HE-EL-0320: FS, HE-EL-0430: FS, HE-EL-0490: FS | 2024-02-26 | 2024-03-08
HE-EL-0320 | Completed | P2543-R01-Oct24..1.EN.9.14 | Receive Company Comments-Solar Panel System SLDs | HE-EL-0310 | HE-EL-0310: FS | HE-EL-0330 | HE-EL-0330: FS | 2024-03-10 | 2024-03-25
HE-EL-0330 | Completed | P2543-R01-Oct24..1.EN.9.14 | Re-Issue for Approval-Solar Panel System SLDs | HE-EL-0320 | HE-EL-0320: FS | HE-EL-0340 | HE-EL-0340: FS | 2024-03-31 | 2024-04-07
HE-EL-0340 | Completed | P2543-R01-Oct24..1.EN.9.14 | Obtain Company Approval-Solar Panel System SLDs | HE-EL-0330 | HE-EL-0330: FS | HE-EL-0350 | HE-EL-0350: FS | 2024-05-27 07:30 | 2024-06-04 17:30
HE-EL-0350 | In Progress | P2543-R01-Oct24..1.EN.9.14 | Final Issue for Design/ Construction-Solar Panel System SLDs | HE-EL-0340, HE-DB-0010, HE-EL-160 | HE-EL-0340: FS, HE-DB-0010: FS, HE-EL-160: FS | HE-EL-0410, CAB-4450, ML1031-B20, C-56-591-01-EI-1600, C-52-598-06-EI-1210, C-52-598-06-EI-1400, C-52-598-05-EI-1210, C-52-598-05-EI-1400, C-52-598-04-EI-1210, C-52-598-04-EI-1400, C-52-598-03-EI-1210, C-52-598-03-EI-1400, C-52-598-02-EI-1210, C-52-598-02- | HE-EL-0410: FS, CAB-4450: FS, ML1031-B20: FS, C-56-591-01-EI-1600: FS, C-52-598-06-EI-1210: FS, C-52-598-06-EI-1400: FS, C-52-598-05-EI-1210: FS, C-52-598-05-EI-1400: FS, C-52-598-04-EI-1210: FS, C-52-598-04-EI-1400: FS, C-52-598-03-EI-1210: FS, C-52-598-0 | 2024-09-02 07:30 | 2024-11-01 17:30
HE-EL-0370 | Completed | P2543-R01-Oct24..1.EN.9.4 | Issue ICR-Solar Panel Sizing calculation | HE-EL-0310 | HE-EL-0310: FS | HE-CS-0850, HE-EL-0380 | HE-CS-0850: FS, HE-EL-0380: FS | 2024-04-01 07:30 | 2024-04-15 17:30
HE-EL-0390 | Completed | P2543-R01-Oct24..1.EN.9.4 | Re-Issue for Approval-Solar Panel Sizing calculation | HE-EL-0380 | HE-EL-0380: FS | HE-EL-0400 | HE-EL-0400: FS | 2024-06-16 07:30 | 2024-10-15 17:30
HE-EL-0400 | Not Started | P2543-R01-Oct24..1.EN.9.4 | Obtain Company Approval-Solar Panel Sizing calculation | HE-EL-0390 | HE-EL-0390: FS | HE-EL-0410 | HE-EL-0410: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HE-EL-0410 | Not Started | P2543-R01-Oct24..1.EN.9.4 | Final Issue for Design/ Construction-Solar Panel Sizing | HE-EL-0350, HE-EL-0400 | HE-EL-0350: FS, HE-EL-0400: FS | HE-CS-0890, CAB-4450 | HE-CS-0890: FS, CAB-4450: FS | 2024-11-11 07:30 | 2024-11-15 17:30
HE-EL-0380 | Completed | P2543-R01-Oct24..1.EN.9.4 | Receive Company Comments-Solar Panel Sizing calculation | HE-EL-0370 | HE-EL-0370: FS | HE-EL-0390 | HE-EL-0390: FS | 2024-04-16 07:30 | 2024-05-15 17:30
HE-EL-0430 | Completed | P2543-R01-Oct24..1.EN.9.9 | Issue ICR-Cable Sizing Calculation | HE-EL-0190, HE-EL-0310 | HE-EL-0190: FS, HE-EL-0310: FS | HE-EL-2010, HE-EL-1150, HE-EL-0440, HE-EL-0550, HE-EL-1960, HE-EL-2010, HE-EL-2060, HE-EL-2110, HE-EL-2160 | HE-EL-2010: FF, HE-EL-1150: FS, HE-EL-0440: FS, HE-EL-0550: SS 5, HE-EL-1960: FS, HE-EL-2010: FS, HE-EL-2060: FS, HE-EL-2110: FS, HE-EL-2160: FS | 2023-11-24 | 2023-12-21
HE-EL-0440 | Completed | P2543-R01-Oct24..1.EN.9.9 | Receive Company Comments-Cable Sizing Calculation | HE-EL-0430 | HE-EL-0430: FS | HE-EL-0450 | HE-EL-0450: FS | 2023-12-21 | 2024-01-05
HE-EL-0450 | Completed | P2543-R01-Oct24..1.EN.9.9 | Re-Issue for Approval-Cable Sizing Calculation | HE-EL-0440 | HE-EL-0440: FS | HE-EL-1170, HE-EL-0460, HE-EL-0570, HE-EL-1980, HE-EL-2030, HE-EL-2080, HE-EL-2130, HE-EL-2180 | HE-EL-1170: FS, HE-EL-0460: FS, HE-EL-0570: FS, HE-EL-1980: FS, HE-EL-2030: FS, HE-EL-2080: FS, HE-EL-2130: FS, HE-EL-2180: FS | 2024-01-06 | 2024-01-13
HE-EL-0460 | Completed | P2543-R01-Oct24..1.EN.9.9 | Obtain Company Approval-Cable Sizing Calculation | HE-EL-0450 | HE-EL-0450: FS | HE-EL-0470 | HE-EL-0470: FS | 2024-01-29 | 2024-02-02
HE-EL-0470 | In Progress | P2543-R01-Oct24..1.EN.9.9 | Final Issue for Design/ Construction-Cable Sizing Calculation | HE-EL-0460 | HE-EL-0460: FS | CAB-4450, HE-EL-2000, C-56-PL-607-EI-2000, C-56-EB2-EI-1200, C-56-EB2-EI-1210, C-56-EB2-EI-1220, C-56-PR-838-CA-1000, C-56-PR-838-CA-1030, C-56-PR-838-EI-2000, C-56-PR-838-EI-2010, C-56-PR-838-EI-2040, C-56-591-01-EI-2000, C-56-591-01-EI-2010, C-52-598-06- | CAB-4450: FS, HE-EL-2000: FF, C-56-PL-607-EI-2000: FS, C-56-EB2-EI-1200: FS, C-56-EB2-EI-1210: FS, C-56-EB2-EI-1220: FS, C-56-PR-838-CA-1000: FS, C-56-PR-838-CA-1030: FS, C-56-PR-838-EI-2000: FS, C-56-PR-838-EI-2010: FS, C-56-PR-838-EI-2040: FS, C-56-591-0 | 2024-10-07 07:30 | 2024-11-01 17:30
HE-EL-0690 | Completed | P2543-R01-Oct24..1.EN.9.31.23 | Re-Issue for Approval-Data sheet for Distribution Transformer | HE-EL-0680 | HE-EL-0680: FS | HE-EL-0700, HE-EL-1050 | HE-EL-0700: FS, HE-EL-1050: FS | 2023-11-15 | 2023-11-16
HE-EL-0700 | Completed | P2543-R01-Oct24..1.EN.9.31.23 | Obtain Company Approval-Data sheet for Distribution Transformer | HE-EL-0690 | HE-EL-0690: FS | HE-EL-0710 | HE-EL-0710: FS | 2023-11-15 | 2023-11-16
HE-EL-0710 | Completed | P2543-R01-Oct24..1.EN.9.31.23 | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | HE-EL-0700, HE-DB-0010, HE-EL-160 | HE-EL-0700: FS, HE-DB-0010: FS, HE-EL-160: FS | ML1030, ML1859-E31, ML1749-E20, ML1219-B29, CAB-4450, HE-EL-1070, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-52-PR-839-EI-1400, C-52-PR-839-EI-1800, C-52-PR-839-CA-1000, C-52-PR-839-TE-1410, PRECOM-52-PR-1000, C-56-PL-607-EI-2410 | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1219-B29: FF, CAB-4450: FS, HE-EL-1070: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-52-PR-839-EI-1400: FS, C-52-PR-839-EI-1800: FS, C-52-PR-839-CA-1000: FF, C-52-PR-839-TE-1 | 2023-12-29 | 2024-01-10
HE-EL-0670 | Completed | P2543-R01-Oct24..1.EN.9.31.23 | Issue ICR- Data sheet for Distribution Transformer | HE-EL-180 | HE-EL-180: FS 10 | HE-EL-1030, HE-EL-0680, HE-EL-0610 | HE-EL-1030: FS 15, HE-EL-0680: FS, HE-EL-0610: SS | 2023-11-15 | 2023-11-16
HE-EL-0680 | Completed | P2543-R01-Oct24..1.EN.9.31.23 | Receive Company Comments-Data sheet for Distribution Transformer | HE-EL-0670 | HE-EL-0670: FS | HE-EL-0690 | HE-EL-0690: FS | 2023-11-15 | 2023-11-16
HE-EL-1070 | Completed | P2543-R01-Oct24..1.EN.9.1.25 | Final Issue for Design/ Construction-Material Requisition for Distribution Transformer | HE-EL-1060, HE-EL-0710 | HE-EL-1060: FS, HE-EL-0710: FS | ML1219-B29, ML1027-B17, CAB-4450, HM-ME-0930, HE-EL-1490 | ML1219-B29: FF, ML1027-B17: FS, CAB-4450: FS, HM-ME-0930: FF, HE-EL-1490: FS | 2024-01-29 | 2024-02-02
HE-EL-1030 | Completed | P2543-R01-Oct24..1.EN.9.1.25 | Issue ICR-Material Requisition for Distribution Transformer | HE-EL-0670 | HE-EL-0670: FS 15 | HP-ME-0460, HE-EL-1040 | HP-ME-0460: FS, HE-EL-1040: FS | 2023-11-15 | 2023-11-16
HE-EL-1040 | Completed | P2543-R01-Oct24..1.EN.9.1.25 | Receive Company Comments-Material Requisition for Distribution Transformer | HE-EL-1030 | HE-EL-1030: FS | HE-EL-1050 | HE-EL-1050: FS | 2023-11-13 | 2023-11-24
HE-EL-1050 | Completed | P2543-R01-Oct24..1.EN.9.1.25 | Re-Issue for Approval-Material Requisition for Distribution Transformer | HE-EL-1040, HE-EL-0690 | HE-EL-1040: FS, HE-EL-0690: FS | HE-EL-1060 | HE-EL-1060: FS | 2023-12-08 | 2023-12-08
HE-EL-1060 | Completed | P2543-R01-Oct24..1.EN.9.1.25 | Obtain Company Approval-Material Requisition for Distribution Transformer | HE-EL-1050 | HE-EL-1050: FS | HE-EL-1070 | HE-EL-1070: FS | 2023-12-22 | 2023-12-22
HE-EL-1480 | Completed | P2543-R01-Oct24..1.EN.9.6.30 | Obtain Company Approval-TBE for Distribution Transformer | HE-EL-1470 | HE-EL-1470: FS | HE-EL-1490 | HE-EL-1490: FS | 2024-03-01 07:30 | 2024-03-14 17:30
HE-EL-1490 | Completed | P2543-R01-Oct24..1.EN.9.6.30 | Final Issue for Design/ Construction-TBE for Distribution Transformer | HE-EL-1480, HE-EL-1070 | HE-EL-1480: FS, HE-EL-1070: FS | CAB-4450 | CAB-4450: FS | 2024-03-15 07:30 | 2024-03-28 17:30
HE-EL-1450 | Completed | P2543-R01-Oct24..1.EN.9.6.30 | Issue ICR-TBE for Distribution Transformer | HP-ME-0460 | HP-ME-0460: FS | HE-EL-1460, HP-ME-0470 | HE-EL-1460: FS, HP-ME-0470: SS | 2023-12-05 | 2023-12-29
HE-EL-1460 | Completed | P2543-R01-Oct24..1.EN.9.6.30 | Receive Company Comments-TBE for Distribution Transformer | HE-EL-1450 | HE-EL-1450: FS | HE-EL-1470 | HE-EL-1470: FS | 2023-12-29 | 2024-01-16
HE-EL-1470 | Completed | P2543-R01-Oct24..1.EN.9.6.30 | Re-Issue for Approval-TBE for Distribution Transformer | HE-EL-1460 | HE-EL-1460: FS | HE-EL-1480 | HE-EL-1480: FS | 2024-01-17 07:30 | 2024-02-29 17:30
HE-SS-0030 | Completed | P2543-R01-Oct24..1.EN.2 | Topographical Survey | HS-GN-0170, ML1007-B02 | HS-GN-0170: FS, ML1007-B02: FS | HS-CN-0160, HE-TS-0010, HE-TS-230, HE-TS-280, HE-TS-330, C-56-PL-607-CI-1000, C-56-EB2-CI-1000, C-56-G-HT-CI-1000, C-56-HC01-PL-CI-2400, C-56-PR-838-CI-1000, C-56-591-01-CI-1000, C-52-HG01-PL-CI-2400, C-52-598-06-CI-1000, C-52-598-05-CI-1000, C-52-598-04-C | HS-CN-0160: SS, HE-TS-0010: FS, HE-TS-230: FS, HE-TS-280: FS, HE-TS-330: FS, C-56-PL-607-CI-1000: SS, C-56-EB2-CI-1000: SS, C-56-G-HT-CI-1000: SS, C-56-HC01-PL-CI-2400: SS, C-56-PR-838-CI-1000: SS, C-56-591-01-CI-1000: SS, C-52-HG01-PL-CI-2400: SS, C-52-59 | 2023-09-15 | 2024-02-22
HE-SS-0040 | Completed | P2543-R01-Oct24..1.EN.2 | Geo Technical Survey | ML1007-B02, HS-GN-0170 | ML1007-B02: FS, HS-GN-0170: FS | HE-GS-0010, HE-GS-90, HE-GS-140, HE-GS-190 | HE-GS-0010: FS, HE-GS-90: FS, HE-GS-140: FS, HE-GS-190: FS | 2023-11-15 | 2024-01-22
HE-SS-0010 | Completed | P2543-R01-Oct24..1.EN.2 | Data Acquisition | ML1002 | ML1002: FS | HE-SV-0010, HE-SS-0020 | HE-SV-0010: FS, HE-SS-0020: SS 10 | 2023-08-17 | 2023-09-20
HE-SS-0020 | Completed | P2543-R01-Oct24..1.EN.2 | Site Visit | ML1002, HE-SS-0010 | ML1002: FS, HE-SS-0010: SS 10 | HE-PL-0130, HE-PL-0190, HE-SV-0010, HE-WS-0010 | HE-PL-0130: FS 20, HE-PL-0190: FS 20, HE-SV-0010: FS, HE-WS-0010: FS 15 | 2023-08-22 | 2023-09-28
HE-WS-0020 | Completed | P2543-R01-Oct24..1.PM.12 | HAZID /ENVID/OHID/ PHSER Workshop | HS-GN-0110, HE-PI-0470, HE-DB-0020, HE-PI-0330, HE-HS-0140, HE-PR-0050, HE-HS-0130, HE-PI-0540, HE-PI-0400, HE-HS-0080, HE-PR-1250 | HS-GN-0110: FS, HE-PI-0470: FS, HE-DB-0020: FS, HE-PI-0330: FS, HE-HS-0140: FS, HE-PR-0050: FS, HE-HS-0130: FS, HE-PI-0540: FS, HE-PI-0400: FS, HE-HS-0080: FS, HE-PR-1250: FS | HE-HS-0970, HE-HS-0670, HE-WS-0050, HE-HS-0490, HE-PI-0130, C-COM-790, CAB-5290, HE-HS-0550, HE-PI-0150 | HE-HS-0970: FS, HE-HS-0670: FS, HE-WS-0050: FS, HE-HS-0490: FS, HE-PI-0130: FS, C-COM-790: FS, CAB-5290: FS, HE-HS-0550: FS, HE-PI-0150: FS | 2023-10-31 | 2023-11-02
HE-WS-0050 | Completed | P2543-R01-Oct24..1.PM.12 | Constructability Review Workshop | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-PR-0130, HE-HS-0190, HE-WS-0020, HE-WS-0030, HS-GN-0110, HE-PR-0850, HE-PI-0320, HE-WS-0010, HE-HS-0070, HE-PI-0390, HE-PI-0530, HE-HS-0010, HE-PI-0460 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-PR-0130: FS, HE-HS-0190: FS, HE-WS-0020: FS, HE-WS-0030: FS, HS-GN-0110: FS, HE-PR-0850: FS, HE-PI-0320: FS, HE-WS-0010: FS, HE-HS-0070: FS, HE-PI-0390: FS, HE-PI-0530: FS, HE-HS-0010: FS, | HE-HS-0510, HE-ST-0010, C-COM-790, CAB-5290 | HE-HS-0510: FS, HE-ST-0010: FS, C-COM-790: FS, CAB-5290: FS | 2024-05-14 | 2024-05-16
HE-WS-0030 | Completed | P2543-R01-Oct24..1.PM.12 | Design Review Workshop | HC-GN-0110, ML1002-A02, HE-PI-0320, HE-PI-0390, HE-PI-0460, HE-PR-0110, ML1005-B01, HE-PI-0530, HC-GN-0050, HE-WS-0090, ML1002 | HC-GN-0110: FS, ML1002-A02: FS, HE-PI-0320: FS, HE-PI-0390: FS, HE-PI-0460: FS, HE-PR-0110: FS, ML1005-B01: FS, HE-PI-0530: FS, HC-GN-0050: FS, HE-WS-0090: FS, ML1002: SS | ML1219-B19, HE-PR-1130, HE-PI-0170, HE-PR-0870, HE-PR-0450, HE-PR-0570, HE-PR-1280, HE-PR-1330, HE-PR-1380, HE-PR-1430, HE-PR-1480, HE-PR-1530, HE-PR-1580, ML1012-B06, HE-PR-0250, HE-WS-0210, HE-HS-0970, HE-PI-0150, HE-HS-0670, HE-WS-0050, HE-HS-0490, HE-P | ML1219-B19: FF, HE-PR-1130: FS, HE-PI-0170: FS, HE-PR-0870: FS, HE-PR-0450: FS, HE-PR-0570: FS, HE-PR-1280: FS, HE-PR-1330: FS, HE-PR-1380: FS, HE-PR-1430: FS, HE-PR-1480: FS, HE-PR-1530: FS, HE-PR-1580: FS, ML1012-B06: FS, HE-PR-0250: FS, HE-WS-0210: FS, | 2023-10-09 | 2023-10-10
HE-WS-0010 | Completed | P2543-R01-Oct24..1.PM.12 | Project Risk Review Workshop | HE-SS-0020, HE-WS-0070 | HE-SS-0020: FS 15, HE-WS-0070: FS 15 | HE-WS-0050, HE-RR-0010, C-COM-790, CAB-5290 | HE-WS-0050: FS, HE-RR-0010: FS, C-COM-790: FS, CAB-5290: FS | 2023-09-28 | 2023-09-28
HE-TS-0030 | Completed | P2543-R01-Oct24..1.EN.2.2 | Re-Issue for Approval-Topographical Survey Report (Overall) | HE-TS-0020 | HE-TS-0020: FS | HE-TS-0040 | HE-TS-0040: FS | 2024-03-08 | 2024-05-31
HE-TS-0040 | Completed | P2543-R01-Oct24..1.EN.2.2 | Obtain Company Approval-Topographical Survey Report (Overall) | HE-TS-0030 | HE-TS-0030: FS | HE-TS-0050 | HE-TS-0050: FS | 2024-06-03 | 2024-07-26 17:30
HE-TS-0050 | Completed | P2543-R01-Oct24..1.EN.2.2 | Final Issue for Design/ Construction-Topographical Survey Report (Overall) | HE-TS-0040 | HE-TS-0040: FS | HE-PL-2790, HE-PL-2670, ML1009-B04, ML1008-B03, HE-PI-0440, HE-PL-2610, CAB-4420, HE-CS-0530, HE-PI-0580, HE-PI-0370, HE-PI-0510 | HE-PL-2790: FS, HE-PL-2670: FS, ML1009-B04: FS, ML1008-B03: FS, HE-PI-0440: FS, HE-PL-2610: FS, CAB-4420: FS, HE-CS-0530: FS, HE-PI-0580: FS, HE-PI-0370: FS, HE-PI-0510: FS | 2024-07-29 07:30 | 2024-08-30
HE-TS-0010 | Completed | P2543-R01-Oct24..1.EN.2.2 | Issue ICR-Topographical Survey Report (Overall) | HE-SS-0030 | HE-SS-0030: FS | HE-PL-3580, HE-PL-3530, HE-PL-0250, HE-PL-0190, HE-PL-0130, HE-CS-0430, HE-PI-0350, HE-PI-0560, HE-PL-2750, HE-PI-0420, HE-CS-0490, HE-PL-2570, HE-PL-0210, HE-PL-2690, HE-PL-2450, HE-PI-0490, HE-PL-0270, HE-PL-2630, HE-PL-2510, HE-PL-0150, HE-PL-2390, HE-T | HE-PL-3580: FS, HE-PL-3530: FS 60, HE-PL-0250: FS, HE-PL-0190: FS, HE-PL-0130: FS, HE-CS-0430: FS, HE-PI-0350: FS, HE-PI-0560: FS, HE-PL-2750: FS, HE-PI-0420: FS, HE-CS-0490: FS, HE-PL-2570: FS, HE-PL-0210: FS, HE-PL-2690: FS, HE-PL-2450: FS 15, HE-PI-0490 | 2024-01-29 | 2024-02-29
HE-TS-0020 | Completed | P2543-R01-Oct24..1.EN.2.2 | Receive Company Comments-Topographical Survey Report (Overall) | HE-TS-0010 | HE-TS-0010: FS | HE-TS-0030 | HE-TS-0030: FS | 2024-03-01 | 2024-03-07
HE-GS-0020 | Completed | P2543-R01-Oct24..1.EN.2.3 | Receive Company Comments - Geo Technical Survey Report (Overall) | HE-GS-0010 | HE-GS-0010: FS | HE-GS-0030 | HE-GS-0030: FS | 2024-03-04 | 2024-03-08
HE-GS-0030 | Completed | P2543-R01-Oct24..1.EN.2.3 | Re-Issue for Approval - Geo Technical Survey Report (Overall) | HE-GS-0020 | HE-GS-0020: FS | HE-GS-0040 | HE-GS-0040: FS | 2024-03-10 | 2024-04-07
HE-GS-0040 | Completed | P2543-R01-Oct24..1.EN.2.3 | Obtain Company Approval - Geo Technical Survey Report (Overall) | HE-GS-0030 | HE-GS-0030: FS | HE-GS-0050 | HE-GS-0050: FS | 2024-04-12 | 2024-04-18
HE-GS-0050 | Completed | P2543-R01-Oct24..1.EN.2.3 | Final Issue for Design/ Construction-Geotechnical Survey Report (Overall) | HE-GS-0040 | HE-GS-0040: FS | HE-CS-0590, HE-CS-0710, ML1009-B04, CAB-4420, HE-CS-0830, ML1008-B03, HE-CS-1130 | HE-CS-0590: FS, HE-CS-0710: FS, ML1009-B04: FS, CAB-4420: FS, HE-CS-0830: FS, ML1008-B03: FS, HE-CS-1130: FS | 2024-07-26 07:30 | 2024-08-30 17:30
HE-GS-0010 | Completed | P2543-R01-Oct24..1.EN.2.3 | Issue ICR - Geo Technical Survey Report (Overall) | HE-SS-0040 | HE-SS-0040: FS | HE-PL-3270, HE-PL-0250, HE-PL-0190, HE-PL-0130, HE-CS-0790, HE-CS-0550, HE-CS-1090, HE-CS-0670, HE-GS-0020, HE-PL-0670, HE-PI-0340 | HE-PL-3270: FS, HE-PL-0250: FS, HE-PL-0190: FS, HE-PL-0130: FS, HE-CS-0790: FS, HE-CS-0550: FS, HE-CS-1090: FS, HE-CS-0670: FS, HE-GS-0020: FS, HE-PL-0670: FS, HE-PI-0340: FS | 2024-02-26 | 2024-03-01
HE-ST-0010 | Not Started | P2543-R01-Oct24..1.EN.2.4 | Issue ICR-Constructability Review / SIMOPS Report | HE-WS-0050 | HE-WS-0050: FS | HE-ST-0020 | HE-ST-0020: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HE-ST-0020 | Not Started | P2543-R01-Oct24..1.EN.2.4 | Receive Company Comments-Constructability Review / SIMOPS Report | HE-ST-0010 | HE-ST-0010: FS | HE-ST-0030 | HE-ST-0030: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-ST-0030 | Not Started | P2543-R01-Oct24..1.EN.2.4 | Re-Issue for Approval-Constructability Review / SIMOPS Report | HE-ST-0020 | HE-ST-0020: FS | HE-ST-0040 | HE-ST-0040: FS | 2024-11-25 07:30 | 2024-11-29 17:30
HE-ST-0040 | Not Started | P2543-R01-Oct24..1.EN.2.4 | Obtain Company Approval-Constructability Review / SIMOPS Report | HE-ST-0030 | HE-ST-0030: FS | HE-ST-0050 | HE-ST-0050: FS | 2024-12-04 07:30 | 2024-12-17 17:30
HE-ST-0050 | Not Started | P2543-R01-Oct24..1.EN.2.4 | Final Issue for Design/ Construction-Constructability Review/ SIMOPS Report | HE-ST-0040 | HE-ST-0040: FS | CAB-5290, HE-CO-170 | CAB-5290: FS, HE-CO-170: FS | 2024-12-18 07:30 | 2024-12-24 17:30
HE-SV-0010 | Completed | P2543-R01-Oct24..1.EN.2.1 | Issue ICR - Site Visit /Survey Report | HE-SS-0010, HE-SS-0020 | HE-SS-0010: FS, HE-SS-0020: FS | HE-SV-0020 | HE-SV-0020: FF 10 | 2023-11-10 | 2023-12-21 17:30
HE-SV-0020 | Completed | P2543-R01-Oct24..1.EN.2.1 | Receive Company Comments- - Site Visit /Survey Report | HE-SV-0010 | HE-SV-0010: FF 10 | HE-SV-0030 | HE-SV-0030: FF 10 | 2023-11-13 | 2024-02-08 17:30
HE-SV-0030 | Completed | P2543-R01-Oct24..1.EN.2.1 | Re-Issue for Approval - Site Visit /Survey Report | HE-SV-0020 | HE-SV-0020: FF 10 | HE-SV-0040 | HE-SV-0040: FF 10 | 2024-05-31 07:30 | 2024-06-21 17:30
HE-SV-0040 | Completed | P2543-R01-Oct24..1.EN.2.1 | Obtain Company Approval - Site Visit /Survey Report | HE-SV-0030 | HE-SV-0030: FF 10 | HE-SV-0050 | HE-SV-0050: FF 10 | 2024-06-22 07:30 | 2024-08-22 17:30
HE-SV-0050 | In Progress | P2543-R01-Oct24..1.EN.2.1 | Final Issue for Design/ Construction-Site Visit Report | HE-SV-0040 | HE-SV-0040: FF 10 | ML1219-B29, CAB-5290 | ML1219-B29: FF, CAB-5290: FS | 2024-08-22 | 2024-11-01 17:30
HE-RR-0020 | Completed | P2543-R01-Oct24..1.EN.2.6 | Receive Company Comments-Project Risk review register | HE-RR-0010 | HE-RR-0010: FS | HE-RR-0030 | HE-RR-0030: FS | 2023-09-29 | 2023-10-03
HE-RR-0010 | Completed | P2543-R01-Oct24..1.EN.2.6 | Issue ICR- Project Risk review register | HE-WS-0010 | HE-WS-0010: FS | HE-RR-0020 | HE-RR-0020: FS | 2023-09-27 | 2023-09-28
HE-RR-0030 | Completed | P2543-R01-Oct24..1.EN.2.6 | Re-Issue for Approval-Project Risk review register | HE-RR-0020 | HE-RR-0020: FS | HE-RR-0040 | HE-RR-0040: FS | 2023-10-04 | 2023-10-19
HE-RR-0040 | Completed | P2543-R01-Oct24..1.EN.2.6 | Obtain Company Approval-Project Risk review register | HE-RR-0030 | HE-RR-0030: FS | HE-RR-0050 | HE-RR-0050: FS | 2023-10-20 | 2023-10-31
HE-RR-0050 | Completed | P2543-R01-Oct24..1.EN.2.6 | Final Issue for Design/ Construction-Project Risk Review Register | HE-RR-0040 | HE-RR-0040: FS | C-COM-750, ML1219-B29, CAB-5290, HE-WS-0200 | C-COM-750: FS, ML1219-B29: FF, CAB-5290: FS, HE-WS-0200: FS | 2023-11-02 | 2023-11-15
HE-DB-0030 | Completed | P2543-R01-Oct24..1.EN.3.3 | Re-Issue for Approval-Design Basis | HE-DB-0020 | HE-DB-0020: FS | HE-DB-0040, HE-TL-2490 | HE-DB-0040: FS, HE-TL-2490: FS 2 | 2023-08-11 | 2023-09-07
HE-DB-0050 | Completed | P2543-R01-Oct24..1.EN.3.3 | Final Issue for Design-Design Basis | HE-DB-0040 | HE-DB-0040: FS | HE-HV-180, ML1005-B01 | HE-HV-180: FS, ML1005-B01: FS | 2023-11-08 | 2023-11-15
HE-DB-0040 | Completed | P2543-R01-Oct24..1.EN.3.3 | Obtain Company Approval-Design Basis | HE-DB-0030 | HE-DB-0030: FS | HE-DB-0050 | HE-DB-0050: FS | 2023-09-08 | 2023-09-19
HE-DB-0010 | Completed | P2543-R01-Oct24..1.EN.3.3 | Issue ICR-Design Basis | ML1002 | ML1002: SS 5 | HE-PR-0850, HE-PI-0010, HE-CP-0010, HE-HS-0010, HE-PL-0610, HE-PR-0110, HE-DB-0020, HE-PR-0040, HE-IC-0010, HE-CS-0010, HE-PL-0790, HE-PR-1240, HE-DB-80, HE-DB-130, HE-EL-180, HE-PR-0310, HE-PR-0430, HE-PR-0490, HE-PR-0550, HE-PR-1260, HE-ME-270, HE-CS-156 | HE-PR-0850: FS, HE-PI-0010: FS, HE-CP-0010: FS, HE-HS-0010: SS, HE-PL-0610: FS, HE-PR-0110: FS, HE-DB-0020: FS, HE-PR-0040: FF 4, HE-IC-0010: FS, HE-CS-0010: FS, HE-PL-0790: FS, HE-PR-1240: FS, HE-DB-80: FS, HE-DB-130: FS 5, HE-EL-180: FS, HE-PR-0310: FS 4 | 2023-07-23 | 2023-08-02
HE-DB-0020 | Completed | P2543-R01-Oct24..1.EN.3.3 | Receive Company Comments-Design Basis | HE-DB-0010 | HE-DB-0010: FS | HE-DB-0030, HE-WS-0020, HE-HV-180 | HE-DB-0030: FS, HE-WS-0020: FS, HE-HV-180: FS | 2023-08-02 | 2023-08-10
HE-PR-0070 | Completed | P2543-R01-Oct24..1.EN.3.7 | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | HE-PR-0630, HE-HS-0670, HE-PR-0060 | HE-PR-0630: FS, HE-HS-0670: FF, HE-PR-0060: FS | ML1219-B19, HE-PR-1130, HE-PI-0170, HE-PR-0870, HE-PR-0450, HE-PR-0570, HE-PR-1280, HE-PR-1330, HE-PR-1380, HE-PR-1430, HE-PR-1480, HE-PR-1530, HE-PR-1580, HE-PR-1050, HE-PI-0420, HE-PI-0490, HE-PI-0350, HE-PI-0560, HE-PR-0140, HE-PR-0080, HE-PI-0620, ML12 | ML1219-B19: FF, HE-PR-1130: FS, HE-PI-0170: FS, HE-PR-0870: FS, HE-PR-0450: FS, HE-PR-0570: FS, HE-PR-1280: FS, HE-PR-1330: FS, HE-PR-1380: FS, HE-PR-1430: FS, HE-PR-1480: FS, HE-PR-1530: FS, HE-PR-1580: FS, HE-PR-1050: FS, HE-PI-0420: FS, HE-PI-0490: FS, | 2023-09-11 | 2023-09-18
HE-PR-0080 | Completed | P2543-R01-Oct24..1.EN.3.7 | Obtain Company Approval- Process Flow Diagrams ( New + Existing) | HE-PR-0070 | HE-PR-0070: FS | HE-PR-0090 | HE-PR-0090: FS | 2023-09-19 | 2023-09-26
HE-PR-0090 | Completed | P2543-R01-Oct24..1.EN.3.7 | Final Issue for Design/ Construction-Process Flow Diagrams ( New + Existing) | HE-PR-0080, HE-PR-0650 | HE-PR-0080: FS, HE-PR-0650: FS | ML1219-B19, HE-PR-0160, ML1014-B10, HE-PI-0580, HE-PI-0510, HE-PI-0370, HE-PI-0440, HE-PI-0620, ML1219-B29, CAB-4400 | ML1219-B19: FF, HE-PR-0160: FS, ML1014-B10: FS, HE-PI-0580: FS, HE-PI-0510: FS, HE-PI-0370: FS, HE-PI-0440: FS, HE-PI-0620: FS, ML1219-B29: FF, CAB-4400: FS | 2023-10-23 | 2024-08-16 17:30
HE-PR-0060 | Completed | P2543-R01-Oct24..1.EN.3.7 | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | HE-WS-0030, HE-PR-0050 | HE-WS-0030: FS, HE-PR-0050: FS | ML1219-B19, HE-PR-1130, HE-PI-0170, HE-PR-0870, HE-PR-0450, HE-PR-0570, HE-PR-1280, HE-PR-1330, HE-PR-1380, HE-PR-1430, HE-PR-1480, HE-PR-1530, HE-PR-1580, HE-HS-0970, HE-PI-0150, HE-HS-0670, HE-WS-0050, HE-HS-0490, HE-PI-0130, C-COM-790, CAB-5290, HE-PR-0 | ML1219-B19: FF, HE-PR-1130: FS, HE-PI-0170: FS, HE-PR-0870: FS, HE-PR-0450: FS, HE-PR-0570: FS, HE-PR-1280: FS, HE-PR-1330: FS, HE-PR-1380: FS, HE-PR-1430: FS, HE-PR-1480: FS, HE-PR-1530: FS, HE-PR-1580: FS, HE-HS-0970: FS, HE-PI-0150: FS, HE-HS-0670: FS, | 2023-09-01 | 2023-09-27
HE-PR-0040 | Completed | P2543-R01-Oct24..1.EN.3.7 | Issue ICR- Process Flow Diagrams ( New + Existing) | HE-DB-0010 | HE-DB-0010: FF 4 | ML1219-B19, HE-PR-1130, HE-PI-0170, HE-PR-0870, HE-PR-0450, HE-PR-0570, HE-PR-1280, HE-PR-1330, HE-PR-1380, HE-PR-1430, HE-PR-1480, HE-PR-1530, HE-PR-1580, HE-HS-0970, HE-PI-0150, HE-HS-0670, HE-WS-0050, HE-HS-0490, HE-PI-0130, C-COM-790, CAB-5290, ML1012- | ML1219-B19: FF, HE-PR-1130: FS, HE-PI-0170: FS, HE-PR-0870: FS, HE-PR-0450: FS, HE-PR-0570: FS, HE-PR-1280: FS, HE-PR-1330: FS, HE-PR-1380: FS, HE-PR-1430: FS, HE-PR-1480: FS, HE-PR-1530: FS, HE-PR-1580: FS, HE-HS-0970: FS, HE-PI-0150: FS, HE-HS-0670: FS, | 2023-08-04 | 2023-08-09
HE-PR-0050 | Completed | P2543-R01-Oct24..1.EN.3.7 | Receive Company Comments- Process Flow Diagrams ( New + Existing) | HE-PR-0040 | HE-PR-0040: FS | HE-PR-0060, HE-WS-0020, HE-PI-0320, HE-PI-0390 | HE-PR-0060: FS, HE-WS-0020: FS, HE-PI-0320: FS, HE-PI-0390: FS | 2023-08-15 | 2023-08-29
HE-PR-0110 | Completed | P2543-R01-Oct24..1.EN.3.11 | Issue ICR- P&ID's | HE-PI-0010, HE-PR-0850, HE-DB-0010, HE-PR-0040, HE-PR-1240 | HE-PI-0010: SS 5, HE-PR-0850: FS, HE-DB-0010: FS, HE-PR-0040: FS, HE-PR-1240: FS 8 | ML1030, ML1859-E31, ML1749-E20, HE-IC-1210, HE-IC-1090, HE-IC-1030, HE-IC-0070, HE-IC-1330, HE-PI-0130, HE-IC-1450, HE-IC-0550, HE-PI-0960, HE-PI-0900, HE-WS-0030, HE-PL-0310, HE-IC-0250, HE-PR-0250, HE-PR-0120, HE-IC-0490, HE-IC-0190, HE-PR-1090, C-COM-79 | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, HE-IC-1210: FS, HE-IC-1090: FS, HE-IC-1030: FS, HE-IC-0070: FF 2, HE-IC-1330: FS, HE-PI-0130: FS, HE-IC-1450: FS, HE-IC-0550: FS, HE-PI-0960: FS, HE-PI-0900: FS, HE-WS-0030: FS, HE-PL-0310: FS, HE-IC-0250: SS, HE | 2023-09-10 | 2023-09-25
HE-PR-0120 | Completed | P2543-R01-Oct24..1.EN.3.11 | Receive Company Comments-P&ID's | HE-PR-0110 | HE-PR-0110: FS | HE-PR-0130, HE-PR-0170 | HE-PR-0130: FS, HE-PR-0170: FS | 2023-09-30 | 2023-10-11
HE-PR-0140 | Completed | P2543-R01-Oct24..1.EN.3.11 | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | HE-PR-0130, HE-HS-0670, HE-PR-0070, HE-PR-1200, HE-PI-0050 | HE-PR-0130: FS, HE-HS-0670: SS, HE-PR-0070: FS 20, HE-PR-1200: FS, HE-PI-0050: FS | HE-PR-0810, HE-PR-0450, HE-PR-0750, HE-PR-0150, HE-PR-0570, HE-PI-0150, HE-EL-0090, HE-PR-1280, HE-PR-1330, HE-PR-1380, HE-PR-1430, HE-PR-1480, HE-PR-1530, HE-PR-1580, HE-PR-1130, HE-PI-0620, ML1219-B29, CAB-4400 | HE-PR-0810: FS, HE-PR-0450: FS, HE-PR-0750: FS, HE-PR-0150: FS, HE-PR-0570: FS, HE-PI-0150: FS, HE-EL-0090: FS, HE-PR-1280: FS, HE-PR-1330: FS 20, HE-PR-1380: FS, HE-PR-1430: FS, HE-PR-1480: FS, HE-PR-1530: FS, HE-PR-1580: FS, HE-PR-1130: FS, HE-PI-0620: F | 2023-12-09 | 2023-12-21
HE-PR-0150 | Completed | P2543-R01-Oct24..1.EN.3.11 | Obtain Company Approval-P&ID's | HE-PR-0140 | HE-PR-0140: FS | HE-PR-0160, HE-PI-0170 | HE-PR-0160: FS, HE-PI-0170: FS | 2023-12-22 | 2024-01-10
HE-PR-0160 | In Progress | P2543-R01-Oct24..1.EN.3.11 | Final Issue for Design / Construction-P&ID's | HE-PR-0610, HE-PR-0090, HE-PR-0650, HE-PR-0150, HE-PR-1220 | HE-PR-0610: FS, HE-PR-0090: FS, HE-PR-0650: FS, HE-PR-0150: FS, HE-PR-1220: FS | ML1219-B19, ML1219-B29, CAB-4400 | ML1219-B19: FF, ML1219-B29: FF, CAB-4400: FS | 2024-02-22 07:30 | 2024-11-15 17:30
HE-PR-0130 | Completed | P2543-R01-Oct24..1.EN.3.11 | Re-Issue for HAZOP Studies- P&ID's review | HE-PR-1250, HE-PR-0120, HE-WS-0030, HE-PR-0060, HE-PR-0240 | HE-PR-1250: FF, HE-PR-0120: FS, HE-WS-0030: FS, HE-PR-0060: FF, HE-PR-0240: FS | HE-HS-0970, HE-PI-0150, HE-HS-0670, HE-WS-0050, HE-HS-0490, C-COM-790, CAB-5290, ML1012-B06, HE-PR-0140, HE-PI-0130, HE-WS-0210 | HE-HS-0970: FS, HE-PI-0150: FS, HE-HS-0670: FS, HE-WS-0050: FS, HE-HS-0490: FS, C-COM-790: FS, CAB-5290: FS, ML1012-B06: FS, HE-PR-0140: FS, HE-PI-0130: FS 10, HE-WS-0210: FS 5 | 2023-11-10 | 2023-11-16
HE-PR-0310 | Completed | P2543-R01-Oct24..1.EN.3.20.16 | Issue ICR- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | HE-DB-0010, ML1002 | HE-DB-0010: FS 4, ML1002: SS | HE-IC-1150, HE-PR-1030, HE-PR-0320, HE-PR-0370, HE-IC-1150 | HE-IC-1150: SS, HE-PR-1030: FF, HE-PR-0320: FS, HE-PR-0370: SS, HE-IC-1150: FS | 2023-08-14 | 2023-08-24
HE-PR-0320 | Completed | P2543-R01-Oct24..1.EN.3.20.16 | Receive Company Comments- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | HE-PR-0310 | HE-PR-0310: FS | HE-PR-0330 | HE-PR-0330: FS 20 | 2023-08-25 | 2023-09-03
HE-PR-0330 | Completed | P2543-R01-Oct24..1.EN.3.20.16 | Re-Issue for Approval- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | HE-PR-0320 | HE-PR-0320: FS 20 | HE-PR-0340 | HE-PR-0340: FS | 2023-10-06 | 2023-10-12
HE-PR-0340 | Completed | P2543-R01-Oct24..1.EN.3.20.16 | Obtain Company Approval- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | HE-PR-0330 | HE-PR-0330: FS | HE-PR-0350 | HE-PR-0350: FS | 2023-10-13 | 2023-10-26
HE-PR-0350 | Completed | P2543-R01-Oct24..1.EN.3.20.16 | Final Issue for Design/ Construction-Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | HE-PR-0340, HE-PR-0530 | HE-PR-0340: FS, HE-PR-0530: FS | HE-IC-1190, HE-PR-1070, CAB-4400, HE-PR-0410, HE-IC-1170 | HE-IC-1190: FS, HE-PR-1070: FS, CAB-4400: FS, HE-PR-0410: FS, HE-IC-1170: FS | 2024-01-29 | 2024-02-02
HE-PR-0370 | Completed | P2543-R01-Oct24..1.EN.3.20.12 | Issue ICR- Process Datasheets - PRS Skid (at Sweihan CRS) | HE-PR-0310, ML1002 | HE-PR-0310: SS, ML1002: SS | HE-PR-0380, HE-PR-1030, HE-IC-1210, HE-IC-1210 | HE-PR-0380: FS, HE-PR-1030: FF, HE-IC-1210: SS, HE-IC-1210: FS | 2023-08-14 | 2023-08-24
HE-PR-0380 | Completed | P2543-R01-Oct24..1.EN.3.20.12 | Receive Company Comments- Process Datasheets - PRS Skid (at Sweihan CRS) | HE-PR-0370 | HE-PR-0370: FS | HE-PR-0390 | HE-PR-0390: FS 20 | 2023-08-25 | 2023-09-03
HE-PR-0390 | Completed | P2543-R01-Oct24..1.EN.3.20.12 | Re-Issue for Approval- Process Datasheets - PRS Skid (at Sweihan CRS) | HE-PR-0380 | HE-PR-0380: FS 20 | HE-PR-0400 | HE-PR-0400: FS | 2023-09-15 | 2023-09-22
HE-PR-0400 | Completed | P2543-R01-Oct24..1.EN.3.20.12 | Obtain Company Approval- Process Datasheets - PRS Skid (at Sweihan CRS) | HE-PR-0390 | HE-PR-0390: FS | HE-PR-0410 | HE-PR-0410: FS | 2023-11-08 | 2023-11-15
HE-PR-0410 | Completed | P2543-R01-Oct24..1.EN.3.20.12 | Final Issue for Design/ Construction-Process Datasheets - PRS Skid (at Sweihan CRS) | HE-PR-0400, HE-IC-0110, HE-PR-0350 | HE-PR-0400: FS, HE-IC-0110: FS, HE-PR-0350: FS | HE-IC-1250, CAB-4400, HE-PR-1070, HE-IC-1790, CAB-4460, HE-IC-1240 | HE-IC-1250: FS, CAB-4400: FS, HE-PR-1070: FS, HE-IC-1790: FS, CAB-4460: FS, HE-IC-1240: FS | 2023-11-16 | 2024-06-14
HE-PR-0430 | Completed | P2543-R01-Oct24..1.EN.3.20.21 | Issue ICR- Process Datasheets - Filters (At Sweihan CRS) | HE-DB-0010, ML1002 | HE-DB-0010: FS 3, ML1002: SS | HE-PR-0440, HE-ME-0070, HE-PR-1030 | HE-PR-0440: FS, HE-ME-0070: FS, HE-PR-1030: FF | 2023-08-08 | 2023-08-18
HE-PR-0440 | Completed | P2543-R01-Oct24..1.EN.3.20.21 | Receive Company Comments- Process Datasheets - Filters (At Sweihan CRS) | HE-PR-0430 | HE-PR-0430: FS | HE-PR-0450, HE-ME-0070 | HE-PR-0450: FS, HE-ME-0070: FS | 2023-08-19 | 2023-08-29
HE-PR-0450 | Completed | P2543-R01-Oct24..1.EN.3.20.21 | Re-Issue for Approval- Process Datasheets - Filters (At Sweihan CRS) | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-WS-0030, HE-HS-0670, HE-PR-0070, HE-PR-1200, HE-PR-0140, HE-PR-0440 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-WS-0030: FS, HE-HS-0670: SS, HE-PR-0070: FS, HE-PR-1200: FS, HE-PR-0140: FS, HE-PR-0440: FS | HE-PR-0460 | HE-PR-0460: FS | 2023-09-14 | 2023-09-21
HE-PR-0460 | Completed | P2543-R01-Oct24..1.EN.3.20.21 | Obtain Company Approval- Process Datasheets - Filters (At Sweihan CRS) | HE-PR-0450 | HE-PR-0450: FS | HE-PR-0470 | HE-PR-0470: FS | 2023-10-06 | 2023-10-12
HE-PR-0470 | Completed | P2543-R01-Oct24..1.EN.3.20.21 | Final Issue for Design/ Construction-Process Datasheets - Filters (At Sweihan CRS) | HE-PR-0460, HE-ME-0050, HE-ME-260, HE-IC-610 | HE-PR-0460: FS, HE-ME-0050: FS, HE-ME-260: FS, HE-IC-610: FS | HE-ME-0110, HE-PR-1070, CAB-4400 | HE-ME-0110: SS, HE-PR-1070: FS, CAB-4400: FS | 2023-11-21 | 2023-11-30
HE-PR-0490 | Completed | P2543-R01-Oct24..1.EN.3.20.14 | Issue ICR- Process Datasheets - Pig Launcher / Receiver | HE-DB-0010 | HE-DB-0010: FS | HE-PR-0500, HE-PR-1030, HE-ME-310, HE-ME-360, HE-ME-410, HE-ME-460, HE-PR-0970, CAB-4480, ML1015-B08, HP-ME-0210, HM-ME-0420, ML1017-B18, HE-PR-0550 | HE-PR-0500: FS, HE-PR-1030: FF, HE-ME-310: FS, HE-ME-360: FS, HE-ME-410: FS, HE-ME-460: FS, HE-PR-0970: FS, CAB-4480: FS, ML1015-B08: FF, HP-ME-0210: FS, HM-ME-0420: FS, ML1017-B18: FS, HE-PR-0550: FS | 2023-08-14 | 2023-08-25
HE-PR-0500 | Completed | P2543-R01-Oct24..1.EN.3.20.14 | Receive Company Comments- Process Datasheets - Pig Launcher / Receiver | HE-PR-0490 | HE-PR-0490: FS | HE-PR-0510 | HE-PR-0510: FS | 2023-08-25 | 2023-08-26
HE-PR-0510 | Completed | P2543-R01-Oct24..1.EN.3.20.14 | Re-Issue for Approval- Process Datasheets - Pig Launcher / Receiver | HE-PR-0500 | HE-PR-0500: FS | HE-PR-0520 | HE-PR-0520: FS | 2023-08-27 | 2023-09-26
HE-PR-0520 | Completed | P2543-R01-Oct24..1.EN.3.20.14 | Obtain Company Approval- Process Datasheets - Pig Launcher / Receiver | HE-PR-0510 | HE-PR-0510: FS | HE-PR-0530 | HE-PR-0530: FS | 2023-10-06 | 2023-10-12
HE-PR-0530 | Completed | P2543-R01-Oct24..1.EN.3.20.14 | Final Issue for Design/ Construction-Process Datasheets - Pig Launcher / Receiver | HE-PR-0520 | HE-PR-0520: FS | HE-PR-1070, CAB-4400, CAB-4480, ML1015-B08, HM-ME-0420, ML1017-B18, HE-PR-0350, HE-ME-310 | HE-PR-1070: FS, CAB-4400: FS, CAB-4480: FS, ML1015-B08: FF, HM-ME-0420: FS, ML1017-B18: FS, HE-PR-0350: FS, HE-ME-310: FS | 2023-11-23 | 2023-11-28
HE-PR-0550 | Completed | P2543-R01-Oct24..1.EN.3.20.13 | Issue ICR- Process Datasheets | HE-DB-0010, HE-PR-0490, ML1002 | HE-DB-0010: FS 5, HE-PR-0490: FS, ML1002: SS | HE-PR-0560, HE-IC-1030, HE-PR-1260 | HE-PR-0560: FS, HE-IC-1030: FS, HE-PR-1260: FS | 2023-08-22 | 2023-09-03
HE-PR-0560 | Completed | P2543-R01-Oct24..1.EN.3.20.13 | Receive Company Comments- Process Datasheets | HE-PR-0550 | HE-PR-0550: FS | HE-PR-0570, HE-IC-1030 | HE-PR-0570: FS, HE-IC-1030: FS | 2023-09-04 | 2023-09-14
HE-PR-0570 | Completed | P2543-R01-Oct24..1.EN.3.20.13 | Re-Issue for Approval- Process Datasheets | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-WS-0030, HE-HS-0670, HE-PR-0070, HE-PR-1200, HE-PR-0560, HE-PR-0140 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-WS-0030: FS, HE-HS-0670: SS, HE-PR-0070: FS, HE-PR-1200: FS, HE-PR-0560: FS, HE-PR-0140: FS | HE-PR-0580 | HE-PR-0580: FS | 2023-09-18 | 2023-09-25
HE-PR-0580 | Completed | P2543-R01-Oct24..1.EN.3.20.13 | Obtain Company Approval- Process Datasheets | HE-PR-0570 | HE-PR-0570: FS | HE-PR-0590 | HE-PR-0590: FS | 2023-10-06 | 2023-10-12
HE-PR-0590 | Completed | P2543-R01-Oct24..1.EN.3.20.13 | Final Issue for Design/ Construction-Process Datasheets | HE-PR-0580 | HE-PR-0580: FS | HE-PR-1070, HM-ME-0120, CAB-4400, HM-ME-0420, HM-ME-0320 | HE-PR-1070: FS, HM-ME-0120: FS, CAB-4400: FS, HM-ME-0420: FS, HM-ME-0320: FS | 2023-11-14 | 2023-12-14
HE-PR-0610 | Completed | P2543-R01-Oct24..1.EN.3.1 | Issue ICR- Process Simulations Report | HE-PR-1240 | HE-PR-1240: SS | CAB-4400, HE-PR-0160, HE-PL-0650, HE-PI-0840, HE-PI-0600, HE-PR-0970, HE-PI-0720, HE-PR-0620, HE-PI-0660, HE-PR-1090, HE-PR-0730, HE-PI-0780, HE-PL-0610 | CAB-4400: FS, HE-PR-0160: FS, HE-PL-0650: FS, HE-PI-0840: FS, HE-PI-0600: FS, HE-PR-0970: FS, HE-PI-0720: FS, HE-PR-0620: FS, HE-PI-0660: FS, HE-PR-1090: FS, HE-PR-0730: FS, HE-PI-0780: FS, HE-PL-0610: FS | 2023-08-04 | 2023-08-14
HE-PR-0620 | Completed | P2543-R01-Oct24..1.EN.3.1 | Receive Company Comments- Process Simulations Report | HE-PR-0610 | HE-PR-0610: FS | HE-PR-0630 | HE-PR-0630: FS | 2023-08-14 | 2023-08-24
HE-PR-0630 | Completed | P2543-R01-Oct24..1.EN.3.1 | Re-Issue for Approval- Process Simulations Report | HE-PR-0620 | HE-PR-0620: FS | HE-PR-0070, HE-PR-0750, HE-PR-0640, HE-PR-1200 | HE-PR-0070: FS, HE-PR-0750: FS, HE-PR-0640: FS, HE-PR-1200: FS | 2023-09-06 | 2023-09-20
HE-PR-0640 | Completed | P2543-R01-Oct24..1.EN.3.1 | Obtain Company Approval- Process Simulations Report | HE-PR-0630 | HE-PR-0630: FS | HE-PR-0650 | HE-PR-0650: FS | 2023-10-06 | 2023-10-12
HE-PR-0650 | Completed | P2543-R01-Oct24..1.EN.3.1 | Final Issue for Design/ Construction-Process Simulations Report | HE-PR-0640 | HE-PR-0640: FS | CAB-4400, HE-PL-0650, ML1219-B19, HE-PI-0170, HE-PR-1130, HE-PR-1070, HE-PR-0090, HE-PR-0160, HE-PR-1220, HE-PI-0620, ML1219-B29, HE-PR-0730 | CAB-4400: FS, HE-PL-0650: FS, ML1219-B19: FF, HE-PI-0170: FS, HE-PR-1130: FS, HE-PR-1070: FS, HE-PR-0090: FS, HE-PR-0160: FS, HE-PR-1220: FS, HE-PI-0620: FS, ML1219-B29: FF, HE-PR-0730: FS | 2023-11-23 | 2023-11-24
HE-PR-0770 | Completed | P2543-R01-Oct24..1.EN.3.4 | Final Issue for Design/ Construction-Operating , control and safeguarding philosophy | HE-PR-0760 | HE-PR-0760: FS | HE-PR-0910, C-COM-800, HE-PR-0950, HE-PI-0620, ML1219-B29, CAB-4400 | HE-PR-0910: FS, C-COM-800: FS, HE-PR-0950: FS, HE-PI-0620: FS, ML1219-B29: FF, CAB-4400: FS | 2023-12-14 | 2024-10-14 17:30
HE-PR-0730 | Completed | P2543-R01-Oct24..1.EN.3.4 | Issue ICR- Operating and control philosophy, Safeguarding philosophy | HE-PR-0610, HE-PR-0110, HE-PR-0650 | HE-PR-0610: FS, HE-PR-0110: FS, HE-PR-0650: FS | HE-PR-0910, HE-PR-0740, HE-PR-0790, HE-PI-0620, ML1219-B29, CAB-4400 | HE-PR-0910: FS, HE-PR-0740: FS, HE-PR-0790: FS, HE-PI-0620: FS, ML1219-B29: FF, CAB-4400: FS | 2023-10-26 | 2023-12-01
HE-PR-0740 | Completed | P2543-R01-Oct24..1.EN.3.4 | Receive Company Comments- Operating and control philosophy , Safeguarding philosophy | HE-PR-0730 | HE-PR-0730: FS | HE-PR-0750, HE-PR-0800 | HE-PR-0750: FS, HE-PR-0800: FS | 2023-12-04 | 2023-12-11
HE-PR-0750 | Completed | P2543-R01-Oct24..1.EN.3.4 | Re-Issue for Approval- Operating and control philosophy , Safeguarding philosophy | HE-PR-0630, HE-PR-0140, HE-PR-0740 | HE-PR-0630: FS, HE-PR-0140: FS, HE-PR-0740: FS | HE-PR-0930, HE-PR-0760 | HE-PR-0930: FS, HE-PR-0760: FS | 2023-12-12 | 2023-12-28
HE-PR-0760 | Completed | P2543-R01-Oct24..1.EN.3.4 | Obtain Company Approval- Operating and control philosophy , Safeguarding philosophy | HE-PR-0750 | HE-PR-0750: FS | HE-PR-0770 | HE-PR-0770: FS | 2023-12-29 | 2024-01-09
HE-PR-0790 | Completed | P2543-R01-Oct24..1.EN.3.9 | Issue ICR - Relief, Vent and Blowdown Philosophy | HE-PR-0730 | HE-PR-0730: FS | HE-PR-0800, HE-PI-0620, ML1219-B29, CAB-4400, HE-PR-1310 | HE-PR-0800: FS, HE-PI-0620: FS, ML1219-B29: FF, CAB-4400: FS, HE-PR-1310: FS | 2023-09-06 | 2023-09-12
HE-PR-0800 | Completed | P2543-R01-Oct24..1.EN.3.9 | Receive Company Comments - Relief, Vent and Blowdown Philosophy | HE-PR-0790, HE-PR-0740 | HE-PR-0790: FS, HE-PR-0740: FS | HE-PR-0810 | HE-PR-0810: FS | 2023-09-13 | 2023-10-11
HE-PR-0810 | Completed | P2543-R01-Oct24..1.EN.3.9 | Re-Issue for Approval - Relief, Vent and Blowdown Philosophy | HE-PR-0140, HE-PR-0800 | HE-PR-0140: FS, HE-PR-0800: FS | HE-PR-0820 | HE-PR-0820: FS | 2023-11-09 | 2023-11-17
HE-PR-0820 | Completed | P2543-R01-Oct24..1.EN.3.9 | Obtain Company Approval - Relief, Vent and Blowdown Philosophy | HE-PR-0810 | HE-PR-0810: FS | HE-PR-0830 | HE-PR-0830: FS | 2023-11-22 | 2023-12-01
HE-PR-0830 | Completed | P2543-R01-Oct24..1.EN.3.9 | Final Issue for Design/ Construction-Relief, Vent and Blowdown philosophy | HE-PR-0820 | HE-PR-0820: FS | ML1219-B29, C-COM-800, CAB-4400, HE-PI-0620, C-COM-750 | ML1219-B29: FF, C-COM-800: FS, CAB-4400: FS, HE-PI-0620: FS, C-COM-750: FS | 2023-12-04 | 2023-12-20
HE-PR-0870 | Completed | P2543-R01-Oct24..1.EN.3.5 | Re-Issue for Approval-Isolation & Tie-In philosophy | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-WS-0030, HE-HS-0670, HE-PR-0070, HE-PR-1200, HE-PR-0860 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-WS-0030: FS, HE-HS-0670: SS, HE-PR-0070: FS, HE-PR-1200: FS, HE-PR-0860: FS | HE-PR-0880 | HE-PR-0880: FS | 2023-10-03 | 2023-10-13
HE-PR-0880 | Completed | P2543-R01-Oct24..1.EN.3.5 | Obtain Company Approval-Isolation & Tie-In philosophy | HE-PR-0870 | HE-PR-0870: FS | ML1010-B14, HE-PR-0890 | ML1010-B14: FF, HE-PR-0890: FS | 2023-10-13 | 2023-10-20
HE-PR-0890 | Completed | P2543-R01-Oct24..1.EN.3.5 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | HE-PR-0880 | HE-PR-0880: FS | C-COM-770, C-COM-770, C-COM-800, C-56-PL-607-PI-1000, C-56-PL-607-PI-1200, C-56-PL-607-PI-1800, C-56-PL-607-PI-2000, C-56-G-HT-PI-1000, C-56-G-HT-PI-1200, C-56-G-HT-PI-1800, C-56-G-HT-PI-2000, C-56-PR-838-PI-1000, C-56-PR-838-PI-1200, C-56-PR-838-PI-1800, | C-COM-770: FS, C-COM-770: FF, C-COM-800: FS, C-56-PL-607-PI-1000: FS, C-56-PL-607-PI-1200: FS, C-56-PL-607-PI-1800: FS, C-56-PL-607-PI-2000: FS, C-56-G-HT-PI-1000: FS, C-56-G-HT-PI-1200: FS, C-56-G-HT-PI-1800: FS, C-56-G-HT-PI-2000: FS, C-56-PR-838-PI-1000 | 2024-01-15 | 2024-01-19
HE-PR-0850 | Completed | P2543-R01-Oct24..1.EN.3.5 | Issue ICR- Isolation & Tie-In philosophy | HE-DB-0010 | HE-DB-0010: FS | HE-PR-0110, HE-WS-0050, HE-PR-0860 | HE-PR-0110: FS, HE-WS-0050: FS, HE-PR-0860: FS | 2023-08-06 | 2023-08-16
HE-PR-0860 | Completed | P2543-R01-Oct24..1.EN.3.5 | Receive Company Comments-Isolation & Tie-In philosophy | HE-PR-0850 | HE-PR-0850: FS | HE-PR-0870, HE-PR-0280, HS-CN-0510 | HE-PR-0870: FS, HE-PR-0280: FS, HS-CN-0510: FS 14 | 2023-08-15 | 2023-08-25
HE-PR-0910 | Not Started | P2543-R01-Oct24..4.1.5 | Issue ICR - Pre-commissioning and commissioning philosophy | HE-PR-0770, HE-PR-0730 | HE-PR-0770: FS, HE-PR-0730: FS | HE-PR-0920 | HE-PR-0920: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HE-PR-0920 | Not Started | P2543-R01-Oct24..4.1.5 | Receive Company Comments - Pre-commissioning and commissioning philosophy | HE-PR-0910 | HE-PR-0910: FS | HE-PR-0930 | HE-PR-0930: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-PR-0930 | Not Started | P2543-R01-Oct24..4.1.5 | Re-Issue for Approval - Pre-commissioning and commissioning philosophy | HE-PR-0750, HE-PR-0920 | HE-PR-0750: FS, HE-PR-0920: FS | HE-PR-0940 | HE-PR-0940: FS | 2024-11-25 07:30 | 2024-11-29 17:30
HE-PR-0940 | Not Started | P2543-R01-Oct24..4.1.5 | Obtain Company Approval - Pre-commissioning and commissioning philosophy | HE-PR-0930 | HE-PR-0930: FS | HE-PR-0950 | HE-PR-0950: FS | 2024-12-04 07:30 | 2024-12-17 17:30
HE-PR-0950 | Not Started | P2543-R01-Oct24..4.1.5 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | HE-PR-0940, HE-PR-0770 | HE-PR-0940: FS, HE-PR-0770: FS | C-COM-800, PRECOM-56-PL-1000, PRECOM-56-EB2-1000, PRECOM-56-G-1000, PRECOM-56-59101-1000, PRECOM-56-PR-1000, PRECOM-56-HGHC-1000, PRECOM-52-59806-1000, PRECOM-52-06CR-1000, PRECOM-52-EB1-1000, PRECOM-52-PR-1000, PRECOM-56-59805-1000, PRECOM-52-IDS3-1000, P | C-COM-800: FS, PRECOM-56-PL-1000: FS, PRECOM-56-EB2-1000: FS, PRECOM-56-G-1000: FS, PRECOM-56-59101-1000: FS, PRECOM-56-PR-1000: FS, PRECOM-56-HGHC-1000: FS, PRECOM-52-59806-1000: FS, PRECOM-52-06CR-1000: FS, PRECOM-52-EB1-1000: FS, PRECOM-52-PR-1000: FS, | 2024-12-18 07:30 | 2024-12-24 17:30
HE-PR-1010 | Completed | P2543-R01-Oct24..1.EN.3.18 | Final Issue for Design/ Construction-Vent and Depressurization Report (for new facilities) | HE-PR-1000, HE-PL-0050 | HE-PR-1000: FS, HE-PL-0050: FS | HE-PI-0440, HE-PI-0510, HE-PI-0370, HE-PI-0580, HE-PR-1130, CAB-4400 | HE-PI-0440: FS, HE-PI-0510: FS, HE-PI-0370: FS, HE-PI-0580: FS, HE-PR-1130: FS, CAB-4400: FS | 2023-12-29 | 2024-03-07
HE-PR-0970 | Completed | P2543-R01-Oct24..1.EN.3.18 | Issue ICR- Vent and Depressurization Report (for new facilities) | HE-PR-0610, HE-PI-0390, HE-PI-0320, HE-PL-0010, HE-PR-0490, HE-PR-1310 | HE-PR-0610: FS, HE-PI-0390: FS, HE-PI-0320: FS, HE-PL-0010: FS, HE-PR-0490: FS, HE-PR-1310: SS | HE-PR-0980 | HE-PR-0980: FS | 2023-11-03 | 2023-12-28
HE-PR-0980 | Completed | P2543-R01-Oct24..1.EN.3.18 | Receive Company Comments- Vent and Depressurization Report (for new facilities) | HE-PR-0970 | HE-PR-0970: FS | HE-PR-0990 | HE-PR-0990: FS | 2023-11-03 | 2023-12-28
HE-PR-0990 | Completed | P2543-R01-Oct24..1.EN.3.18 | Re-Issue for Approval- Vent and Depressurization Report (for new facilities) | HE-PR-0980 | HE-PR-0980: FS | HE-PR-1000 | HE-PR-1000: FS | 2023-11-03 | 2023-12-28
HE-PR-1000 | Completed | P2543-R01-Oct24..1.EN.3.18 | Obtain Company Approval- Vent and Depressurization Report (for new facilities) | HE-PR-0990 | HE-PR-0990: FS | HE-PR-1010 | HE-PR-1010: FS | 2023-11-03 | 2023-12-28
HE-PR-1030 | Completed | P2543-R01-Oct24..1.EN.3.10 | Issue ICR - Equipment List | HE-PR-0490, HE-PR-0370, HE-PR-0310, HE-PR-0430 | HE-PR-0490: FF, HE-PR-0370: FF, HE-PR-0310: FF, HE-PR-0430: FF | HE-PI-0130, HE-PR-1040, HE-PI-0010, HE-PI-0320 | HE-PI-0130: FS, HE-PR-1040: FS, HE-PI-0010: FF 5, HE-PI-0320: FS | 2023-08-11 | 2023-08-21
HE-PR-1040 | Completed | P2543-R01-Oct24..1.EN.3.10 | Receive Company Comments - Equipment List | HE-PR-1030 | HE-PR-1030: FS | HE-PR-1050, HE-PI-0390 | HE-PR-1050: FS, HE-PI-0390: FS | 2023-08-22 | 2023-08-31
HE-PR-1050 | Completed | P2543-R01-Oct24..1.EN.3.10 | Re-Issue for Approval - Equipment List | HE-PR-0070, HE-PR-1040, HE-PR-1200 | HE-PR-0070: FS, HE-PR-1040: FS, HE-PR-1200: FS | HE-PR-1060, ML1012-B06 | HE-PR-1060: FS, ML1012-B06: FS | 2023-09-01 | 2023-09-21
HE-PR-1060 | Completed | P2543-R01-Oct24..1.EN.3.10 | Obtain Company Approval - Equipment List | ML1012-B06, HE-PR-1050, HE-PR-1120 | ML1012-B06: FS, HE-PR-1050: FS, HE-PR-1120: FS | HE-PR-1070, HE-PL-0410 | HE-PR-1070: FS, HE-PL-0410: FF | 2023-09-22 | 2023-10-06
HE-PR-1070 | Completed | P2543-R01-Oct24..1.EN.3.10 | Final Issue for Design/ Construction-Equipment List | HE-PR-0590, HE-PR-1060, HE-PR-0470, HE-PR-0530, HE-PR-0650, HE-PR-0350, HE-PR-0410, HE-PR-1300, HE-PR-1350, HE-PR-1400, HE-PR-1450, HE-PR-1500, HE-PR-1550, HE-PR-1600 | HE-PR-0590: FS, HE-PR-1060: FS, HE-PR-0470: FS, HE-PR-0530: FS, HE-PR-0650: FS, HE-PR-0350: FS, HE-PR-0410: FS, HE-PR-1300: FS, HE-PR-1350: FS, HE-PR-1400: FS, HE-PR-1450: FS, HE-PR-1500: FS, HE-PR-1550: FS, HE-PR-1600: FS | ML1219-B29, ML1014-B10, ML1179-B11, CAB-4400 | ML1219-B29: FF, ML1014-B10: FS, ML1179-B11: FS, CAB-4400: FS | 2023-11-21 | 2023-11-29
HE-PR-1090 | Completed | P2543-R01-Oct24..1.EN.3.17 | Issue ICR- Line List | HE-PR-0040, HE-PR-1240, HE-PR-0610, HE-PR-0110 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-0610: FS, HE-PR-0110: FS | HE-PR-1100, HE-PI-0262, HE-PI-0900, HE-PI-0960 | HE-PR-1100: FS, HE-PI-0262: FS 5, HE-PI-0900: FF, HE-PI-0960: FF | 2023-10-02 | 2023-10-20
HE-PR-1100 | Completed | P2543-R01-Oct24..1.EN.3.17 | Receive Company Comments- Line List | HE-PR-1090 | HE-PR-1090: FS | HE-PR-1110 | HE-PR-1110: FS | 2023-10-20 | 2023-10-27
HE-PR-1110 | Completed | P2543-R01-Oct24..1.EN.3.17 | Re-Issue for Approval- Line List | HE-PR-1100 | HE-PR-1100: FS | HE-PR-1120, HE-PI-0262 | HE-PR-1120: FS, HE-PI-0262: FS 10 | 2023-12-01 | 2023-12-28
HE-PR-1120 | Completed | P2543-R01-Oct24..1.EN.3.17 | Obtain Company Approval- Line List | HE-PR-1110 | HE-PR-1110: FS | HE-PR-1130, HE-PR-1060 | HE-PR-1130: FS, HE-PR-1060: FS | 2023-12-29 | 2024-01-12
HE-PR-1130 | In Progress | P2543-R01-Oct24..1.EN.3.17 | Final Issue for Design/ Construction-Line List | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-WS-0030, HE-HS-0670, HE-PR-0070, HE-PR-1200, HE-PR-0650, HE-PR-1010, HE-PR-1120, HE-PR-0140 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-WS-0030: FS, HE-HS-0670: SS, HE-PR-0070: FS, HE-PR-1200: FS, HE-PR-0650: FS, HE-PR-1010: FS, HE-PR-1120: FS, HE-PR-0140: FS | ML1219-B29, CAB-4400, HE-PI-0302 | ML1219-B29: FF, CAB-4400: FS, HE-PI-0302: SS 10 | 2024-01-10 | 2024-11-22 17:30
HE-PR-0290 | Completed | P2543-R01-Oct24..1.EN.3.15 | Final Issue for Design/ Construction-Tie-In Schedule | HE-PR-0280 | HE-PR-0280: FS | ML1219-B29, CAB-4440, C-56-PL-607-PI-1000, C-56-PL-607-PI-1200, C-56-PL-607-PI-1800, C-56-PL-607-PI-2000, C-56-G-HT-PI-1000, C-56-G-HT-PI-1200, C-56-G-HT-PI-1800, C-56-G-HT-PI-2000, C-56-PR-838-PI-1000, C-56-PR-838-PI-1200, C-56-PR-838-PI-1800, C-56-PR-838 | ML1219-B29: FF, CAB-4440: FS, C-56-PL-607-PI-1000: FS, C-56-PL-607-PI-1200: FS, C-56-PL-607-PI-1800: FS, C-56-PL-607-PI-2000: FS, C-56-G-HT-PI-1000: FS, C-56-G-HT-PI-1200: FS, C-56-G-HT-PI-1800: FS, C-56-G-HT-PI-2000: FS, C-56-PR-838-PI-1000: FS, C-56-PR-8 | 2024-07-15 07:30 | 2024-07-31
HE-PR-0260 | Completed | P2543-R01-Oct24..1.EN.3.15 | Receive Company Comments-Tie-In Schedule | HE-PR-0250 | HE-PR-0250: FS | HE-PR-0270 | HE-PR-0270: FS | 2023-11-25 | 2023-12-14
HE-PR-0270 | Completed | P2543-R01-Oct24..1.EN.3.15 | Re-Issue for Approval-Tie-In Schedule | HE-PR-0260 | HE-PR-0260: FS | HE-PR-0280 | HE-PR-0280: FS | 2023-08-26 | 2023-09-27
HE-PR-0280 | Completed | P2543-R01-Oct24..1.EN.3.15 | Obtain Company Approval-Tie-In Schedule | HE-PR-0270, HE-PR-0860 | HE-PR-0270: FS, HE-PR-0860: FS | HE-PR-0290 | HE-PR-0290: FS | 2023-09-28 | 2023-10-11
HE-PR-0250 | Completed | P2543-R01-Oct24..1.EN.3.15 | Issue ICR-Tie-In Schedule | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-WS-0030, HE-PR-0110 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-WS-0030: FS, HE-PR-0110: FS 10 | HE-PR-0260 | HE-PR-0260: FS | 2023-11-16 | 2023-11-23
HE-IC-0560 | Completed | P2543-R01-Oct24..1.EN.6.A3 | Receive Company Comments- I/O list -Update | HE-IC-0550 | HE-IC-0550: FS | HE-IC-0570 | HE-IC-0570: FS | 2024-02-15 | 2024-02-29
HE-IC-0570 | Completed | P2543-R01-Oct24..1.EN.6.A3 | Re-Issue for Approval- I/O list -Update | HE-IC-0560, HE-IC-0510, HE-PR-0110 | HE-IC-0560: FS, HE-IC-0510: FS, HE-PR-0110: FS | HE-IC-0580, HE-IC-2550, HE-IC-0750, HE-IC-0930, HE-IC-0990, HE-IC-1010, HE-IC-0950, HE-IC-2570, HE-IC-0770, CAB-4460, C-56-PL-607-EI-2000, C-56-EB2-EI-1200, C-56-EB2-EI-1210, C-56-EB2-EI-1220, C-56-PR-838-CA-1000, C-56-PR-838-CA-1030, C-56-PR-838-EI-2000, | HE-IC-0580: FS, HE-IC-2550: FS, HE-IC-0750: FS, HE-IC-0930: FS, HE-IC-0990: FS, HE-IC-1010: FS, HE-IC-0950: FS, HE-IC-2570: FS, HE-IC-0770: FS, CAB-4460: FS, C-56-PL-607-EI-2000: FS, C-56-EB2-EI-1200: FS, C-56-EB2-EI-1210: FS, C-56-EB2-EI-1220: FS, C-56-PR | 2024-02-15 | 2024-02-29
HE-IC-0580 | Completed | P2543-R01-Oct24..1.EN.6.A3 | Obtain Company Approval- I/O list -Update | HE-IC-0570, HE-IC-0520 | HE-IC-0570: FS, HE-IC-0520: FS | HE-IC-0590, HE-IC-2780 | HE-IC-0590: FS, HE-IC-2780: FS | 2024-02-15 | 2024-02-29
HE-IC-0590 | In Progress | P2543-R01-Oct24..1.EN.6.A3 | Final Issue for Design/ Construction-I/O list | HE-IC-0530, HE-IC-0580, HE-PR-0110 | HE-IC-0530: FS, HE-IC-0580: FS, HE-PR-0110: FS | ML1030, ML1859-E31, ML1749-E20, CAB-4460, HE-IC-0770, HE-HS-0350, C-56-PL-607-EI-2000, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1200, C-56-EB2-EI-1000, C-56-EB2-EI-1210, C-56-EB2-EI-1220, C-56-PR-838-EI-1010, C-56-PR-838-E | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, CAB-4460: FS, HE-IC-0770: FS, HE-HS-0350: FS, C-56-PL-607-EI-2000: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-EB2-EI-1200: FS, C-56-EB2-EI-1000: FS, C-56-EB2-EI-1210: FS, | 2024-04-09 | 2024-11-08 17:30
HE-IC-0550 | Completed | P2543-R01-Oct24..1.EN.6.A3 | Issue ICR- I/O list -Update | HE-PR-0110, HE-IC-0490 | HE-PR-0110: FS, HE-IC-0490: FS | HS-GN-0430, HE-IC-0560, HE-IC-2530, HE-IC-0730, CAB-4460, HE-IC-2880 | HS-GN-0430: FS, HE-IC-0560: FS, HE-IC-2530: FS, HE-IC-0730: FS, CAB-4460: FS, HE-IC-2880: FS | 2024-02-15 | 2024-02-29
HE-IC-0610 | Completed | P2543-R01-Oct24..1.EN.6.A18 | Issue ICR - Hook-Up Diagram | HE-IC-2730, HE-IC-0490, HE-PR-0110 | HE-IC-2730: FS, HE-IC-0490: FS, HE-PR-0110: FS | HE-IC-0670, HE-IC-2790, HE-IC-0620 | HE-IC-0670: FF, HE-IC-2790: FS, HE-IC-0620: FS | 2024-02-05 | 2024-02-12
HE-IC-0620 | Completed | P2543-R01-Oct24..1.EN.6.A18 | Receive Company Comments - Hook-Up Diagram | HE-IC-0610 | HE-IC-0610: FS | HE-IC-0630 | HE-IC-0630: FS | 2024-02-13 | 2024-02-19
HE-IC-0630 | Completed | P2543-R01-Oct24..1.EN.6.A18 | Re-Issue for Approval - Hook-Up Diagram | HE-IC-1470, HE-IC-0620, HE-IC-0510, HE-PR-0110 | HE-IC-1470: FS, HE-IC-0620: FS, HE-IC-0510: FS, HE-PR-0110: FS | HE-IC-2610, HE-IC-0640 | HE-IC-2610: FS, HE-IC-0640: FS | 2024-02-20 | 2024-02-26
HE-IC-0640 | Completed | P2543-R01-Oct24..1.EN.6.A18 | Obtain Company Approval - Hook-Up Diagram | HE-IC-0630 | HE-IC-0630: FS | HE-IC-0650 | HE-IC-0650: FS | 2024-02-27 | 2024-03-04
HE-IC-0650 | Not Started | P2543-R01-Oct24..1.EN.6.A18 | Final Issue for Design/ Construction-Hook-Up Diagram | HE-IC-1490, HE-IC-0640, HE-PR-0110 | HE-IC-1490: FS, HE-IC-0640: FS, HE-PR-0110: FS | ML1030, ML1859-E31, ML1749-E20, C-COM-790, HE-IC-2630, CAB-4460, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1000, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C-56-PR-838-EI-2030, C-56- | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, C-COM-790: FS, HE-IC-2630: FS, CAB-4460: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-EB2-EI-1000: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-EI-1400: FS, C-56-PR-838-EI-1810: | 2024-10-28 07:30 | 2024-11-01 17:30
HE-IC-0670 | Completed | P2543-R01-Oct24..1.EN.6.A35 | Issue ICR - Typical Installation Drawings | HE-IC-0610, HE-IC-0490, HP-ME-0730, HP-ME-0780, HE-PR-0110 | HE-IC-0610: FF, HE-IC-0490: FS, HP-ME-0730: FF, HP-ME-0780: FS, HE-PR-0110: FS | HE-IC-0730, HE-IC-0680 | HE-IC-0730: FF, HE-IC-0680: FS | 2024-05-27 | 2024-05-31
HE-IC-0680 | Completed | P2543-R01-Oct24..1.EN.6.A35 | Receive Company Comments - Typical Installation Drawings | HE-IC-0670 | HE-IC-0670: FS | HE-IC-0690 | HE-IC-0690: FS | 2024-05-31 | 2024-06-03
HE-IC-0690 | Completed | P2543-R01-Oct24..1.EN.6.A35 | Re-Issue for Approval - Typical Installation Drawings | HE-IC-0510, HE-IC-0680, HE-PR-0110, HE-IC-2710 | HE-IC-0510: FS, HE-IC-0680: FS, HE-PR-0110: FS, HE-IC-2710: FS | HE-IC-0700, HE-IC-2610 | HE-IC-0700: FS, HE-IC-2610: FS | 2024-06-11 | 2024-06-14
HE-IC-0700 | Completed | P2543-R01-Oct24..1.EN.6.A35 | Obtain Company Approval - Typical Installation Drawings | HE-IC-0690 | HE-IC-0690: FS | HE-IC-0710 | HE-IC-0710: FS | 2024-06-04 | 2024-06-10
HE-IC-0710 | Not Started | P2543-R01-Oct24..1.EN.6.A35 | Final Issue for Design/ Construction-Typical Installation Drawings | HE-IC-0700, HE-PR-0110 | HE-IC-0700: FS, HE-PR-0110: FS | ML1030, ML1859-E31, ML1749-E20, HE-IC-2630, CAB-4460, HE-IC-2630, C-COM-790, C-COM-790, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1000, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C-5 | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, HE-IC-2630: FS, CAB-4460: FS, HE-IC-2630: FF, C-COM-790: FF, C-COM-790: SS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-EB2-EI-1000: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-EI | 2024-10-28 07:30 | 2024-11-01 17:30
HE-IC-0730 | Completed | P2543-R01-Oct24..1.EN.6.A36 | Issue ICR - Loop Diagrams | HE-IC-0670, HE-IC-0790, HE-IC-0550 | HE-IC-0670: FF, HE-IC-0790: FS, HE-IC-0550: FS | HE-IC-0740 | HE-IC-0740: FF 10 | 2024-06-07 07:30 | 2024-09-30 17:30
HE-IC-0740 | In Progress | P2543-R01-Oct24..1.EN.6.A36 | Receive Company Comments - Loop Diagrams | HE-IC-0730 | HE-IC-0730: FF 10 | HE-IC-0750 | HE-IC-0750: FS | 2024-06-14 07:30 | 2024-11-08 17:30
HE-IC-0750 | Not Started | P2543-R01-Oct24..1.EN.6.A36 | Re-Issue for Approval - Loop Diagrams | HE-IC-0810, HE-IC-0930, HE-IC-0990, HE-IC-0740, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190 | HE-IC-0810: FS, HE-IC-0930: FS, HE-IC-0990: FS, HE-IC-0740: FS, HE-IC-0570: FS, HE-IC-0210: FS, HE-IC-0270: FS, HE-IC-0790: FS, HE-IC-0250: FS, HE-IC-0190: FS | HE-IC-0760 | HE-IC-0760: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-IC-0760 | Not Started | P2543-R01-Oct24..1.EN.6.A36 | Obtain Company Approval - Loop Diagrams | HE-IC-0750 | HE-IC-0750: FS | HE-IC-0770 | HE-IC-0770: FS | 2024-11-25 07:30 | 2024-12-10 17:30
HE-IC-0770 | Not Started | P2543-R01-Oct24..1.EN.6.A36 | Final Issue for Design/ Construction-Loop Diagrams | HE-IC-2720, HE-IC-2830, HE-IC-0590, HE-IC-0760, HE-IC-0830, HE-IC-1010, HE-IC-0950, HE-IC-0230, HE-IC-0290, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190 | HE-IC-2720: FS, HE-IC-2830: FS, HE-IC-0590: FS, HE-IC-0760: FS, HE-IC-0830: FS, HE-IC-1010: FS, HE-IC-0950: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0570: FS, HE-IC-0210: FS, HE-IC-0270: FS, HE-IC-0790: FS, HE-IC-0250: FS, HE-IC-0190: FS | ML1030, ML1859-E31, ML1749-E20, ML1219-B29, CAB-4460, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1000, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C-56-PR-838-EI-2030, C-56-591-01-EI-1 | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1219-B29: FF, CAB-4460: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-EB2-EI-1000: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-EI-1400: FS, C-56-PR-838-EI-1810: FS, C-56-PR-83 | 2024-12-11 07:30 | 2024-12-24 17:30
HE-IC-0830 | In Progress | P2543-R01-Oct24..1.EN.6.A22 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | HE-IC-0290, HE-IC-0820, HE-IC-0230 | HE-IC-0290: FS, HE-IC-0820: FS, HE-IC-0230: FS | CAB-4460, HE-IC-0770, C-56-PL-607-EI-2000, C-56-EB2-EI-1200, C-56-EB2-EI-1210, C-56-EB2-EI-1220, C-56-PR-838-CA-1000, C-56-PR-838-CA-1030, C-56-PR-838-EI-2000, C-56-PR-838-EI-2010, C-56-PR-838-EI-2040, C-56-591-01-EI-2000, C-56-591-01-EI-2010, C-52-598-06- | CAB-4460: FS, HE-IC-0770: FS, C-56-PL-607-EI-2000: FS, C-56-EB2-EI-1200: FS, C-56-EB2-EI-1210: FS, C-56-EB2-EI-1220: FS, C-56-PR-838-CA-1000: FS, C-56-PR-838-CA-1030: FS, C-56-PR-838-EI-2000: FS, C-56-PR-838-EI-2010: FS, C-56-PR-838-EI-2040: FS, C-56-591-0 | 2024-03-21 | 2024-11-08 17:30
HE-IC-0790 | Completed | P2543-R01-Oct24..1.EN.6.A22 | Issue ICR- Instrument Cable Block Diagram | HE-IC-3380, HE-IC-0190, HE-IC-0250 | HE-IC-3380: FS, HE-IC-0190: FS, HE-IC-0250: FS | HE-IC-0800, HE-IC-2530, HE-IC-0730, HE-IC-0970, HE-IC-0910, HE-IC-2550, HE-IC-0750, HE-IC-0930, HE-IC-0990, HE-IC-1010, HE-IC-0950, HE-IC-2570, HE-IC-0770, CAB-4460, HE-IC-0910, C-56-PL-607-EI-2000, C-56-EB2-EI-1200, C-56-EB2-EI-1210, C-56-EB2-EI-1220, C-5 | HE-IC-0800: FS, HE-IC-2530: FS, HE-IC-0730: FS, HE-IC-0970: FS, HE-IC-0910: FS, HE-IC-2550: FS, HE-IC-0750: FS, HE-IC-0930: FS, HE-IC-0990: FS, HE-IC-1010: FS, HE-IC-0950: FS, HE-IC-2570: FS, HE-IC-0770: FS, CAB-4460: FS, HE-IC-0910: FF, C-56-PL-607-EI-200 | 2023-12-29 | 2024-01-26
HE-IC-0800 | Completed | P2543-R01-Oct24..1.EN.6.A22 | Receive Company Comments- Instrument Cable Block Diagram | HE-IC-0790 | HE-IC-0790: FS | HE-IC-0810, HE-IC-0910, HE-IC-0970 | HE-IC-0810: FS, HE-IC-0910: FS, HE-IC-0970: FS | 2024-01-29 | 2024-02-09
HE-IC-0810 | Completed | P2543-R01-Oct24..1.EN.6.A22 | Re-Issue for Approval- Instrument Cable Block Diagram | HE-IC-0800, HE-IC-0270, HE-IC-0210 | HE-IC-0800: FS, HE-IC-0270: FS, HE-IC-0210: FS | HE-IC-0750, HE-IC-0820, HE-IC-2550 | HE-IC-0750: FS, HE-IC-0820: FS, HE-IC-2550: FS | 2024-02-15 | 2024-03-08
HE-IC-0820 | Completed | P2543-R01-Oct24..1.EN.6.A22 | Obtain Company Approval- Instrument Cable Block Diagram | HE-IC-0810 | HE-IC-0810: FS | HE-IC-0990, HE-IC-0930, HE-IC-0830 | HE-IC-0990: FS, HE-IC-0930: FS, HE-IC-0830: FS | 2024-03-11 | 2024-03-20
HE-IC-0910 | Completed | P2543-R01-Oct24..1.EN.6.A34 | Issue ICR-Instrument and F&G Cable Schedule | HE-IC-2730, HE-IC-0800, HE-IC-2530, HE-IC-0790, HE-IC-0250, HE-IC-0190, HE-IC-0790, ML2069-B09 | HE-IC-2730: FS, HE-IC-0800: FS, HE-IC-2530: FS, HE-IC-0790: FS, HE-IC-0250: FS, HE-IC-0190: FS, HE-IC-0790: FF, ML2069-B09: FS | HE-IC-0920, HE-IC-0970, HE-IC-3030 | HE-IC-0920: FS, HE-IC-0970: SS, HE-IC-3030: FS | 2024-05-31 | 2024-06-03
HE-IC-0920 | Completed | P2543-R01-Oct24..1.EN.6.A34 | Receive Company Comments-Instrument and F&G Cable Schedule | HE-IC-0910 | HE-IC-0910: FS | HE-IC-0930 | HE-IC-0930: FS | 2024-06-04 | 2024-06-07
HE-IC-0930 | Completed | P2543-R01-Oct24..1.EN.6.A34 | Re-Issue for Approval-Instrument and F&G Cable Schedule | HE-TL-0450, HE-IC-0820, HE-IC-0920, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190 | HE-TL-0450: FS, HE-IC-0820: FS, HE-IC-0920: FS, HE-IC-0570: FS, HE-IC-0210: FS, HE-IC-0270: FS, HE-IC-0790: FS, HE-IC-0250: FS, HE-IC-0190: FS | HE-IC-2610, HE-IC-0750, HE-IC-0940 | HE-IC-2610: FS, HE-IC-0750: FS, HE-IC-0940: FS | 2024-06-11 | 2024-06-14
HE-IC-0940 | Completed | P2543-R01-Oct24..1.EN.6.A34 | Obtain Company Approval-Instrument and F&G Cable Schedule | HE-IC-0930, HE-IC-1000 | HE-IC-0930: FS, HE-IC-1000: FS | HE-IC-0950 | HE-IC-0950: FS | 2024-06-07 | 2024-06-11
HE-IC-0950 | Completed | P2543-R01-Oct24..1.EN.6.A34 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | HE-IC-0940, HE-IC-0230, HE-IC-0290, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190 | HE-IC-0940: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0570: FS, HE-IC-0210: FS, HE-IC-0270: FS, HE-IC-0790: FS, HE-IC-0250: FS, HE-IC-0190: FS | CAB-4460, ML1032-B21, HE-IC-0770, C-56-PL-607-EI-2000, C-56-EB2-EI-1200, C-56-EB2-EI-1210, C-56-EB2-EI-1220, C-56-PR-838-CA-1000, C-56-PR-838-CA-1030, C-56-PR-838-EI-2000, C-56-PR-838-EI-2010, C-56-PR-838-EI-2040, C-56-591-01-EI-2000, C-56-591-01-EI-2010, | CAB-4460: FS, ML1032-B21: FS, HE-IC-0770: FS, C-56-PL-607-EI-2000: FS, C-56-EB2-EI-1200: FS, C-56-EB2-EI-1210: FS, C-56-EB2-EI-1220: FS, C-56-PR-838-CA-1000: FS, C-56-PR-838-CA-1030: FS, C-56-PR-838-EI-2000: FS, C-56-PR-838-EI-2010: FS, C-56-PR-838-EI-2040 | 2024-06-21 07:30 | 2024-09-08 17:30
HE-IC-1060 | Completed | P2543-R01-Oct24..1.EN.6.4.A9 | Obtain Company Approval- Datasheet for MOV | HE-IC-1050 | HE-IC-1050: FS | HE-IC-1070 | HE-IC-1070: FS | 2023-11-21 | 2023-12-26
HE-IC-1070 | Completed | P2543-R01-Oct24..1.EN.6.4.A9 | Final Issue for Design/ Construction-Actuator Datasheet for MOVs | HE-IC-1060, HE-IC-0050 | HE-IC-1060: FS, HE-IC-0050: FF | C-COM-770, HE-IC-2630, CAB-4460 | C-COM-770: FS, HE-IC-2630: FS, CAB-4460: FS | 2023-12-27 | 2024-01-09
HE-IC-1030 | Completed | P2543-R01-Oct24..1.EN.6.4.A9 | Issue ICR- Datasheet for MOV | HE-PI-0900, HE-PR-0110, HE-PR-0550, HE-PR-0560, ML1002 | HE-PI-0900: FS, HE-PR-0110: FS, HE-PR-0550: FS, HE-PR-0560: FS, ML1002: SS | HE-IC-1570, HE-IC-1040 | HE-IC-1570: FS, HE-IC-1040: FS | 2023-09-23 | 2023-09-29
HE-IC-1040 | Completed | P2543-R01-Oct24..1.EN.6.4.A9 | Receive Company Comments- Datasheet for MOV | HE-IC-1030 | HE-IC-1030: FS | HE-IC-1050 | HE-IC-1050: FS | 2023-09-30 | 2023-10-13
HE-IC-1050 | Completed | P2543-R01-Oct24..1.EN.6.4.A9 | Re-Issue for Approval- Datasheet for MOV | HE-IC-1040 | HE-IC-1040: FS | HE-IC-1590, HE-IC-1060 | HE-IC-1590: FS, HE-IC-1060: FS | 2023-11-13 | 2023-11-20
HE-IC-1090 | Completed | P2543-R01-Oct24..1.EN.6.4.A8 | Issue ICR- Datasheet for GOV & ROV | HE-PI-0900, HE-PR-0110, HE-PR-1260, HE-PI-0960, HE-PR-1270, ML1002 | HE-PI-0900: FS, HE-PR-0110: FS, HE-PR-1260: SS 5, HE-PI-0960: FS, HE-PR-1270: FS, ML1002: SS | HE-IC-1630, HE-IC-1100 | HE-IC-1630: FS, HE-IC-1100: FS | 2023-09-23 | 2023-09-29
HE-IC-1100 | Completed | P2543-R01-Oct24..1.EN.6.4.A8 | Receive Company Comments- Datasheet for GOV & ROV | HE-IC-1090 | HE-IC-1090: FS | HE-IC-1110 | HE-IC-1110: FS | 2023-09-30 | 2023-10-13
HE-IC-1110 | Completed | P2543-R01-Oct24..1.EN.6.4.A8 | Re-Issue for Approval- Datasheet for GOV & ROV | HE-IC-1100 | HE-IC-1100: FS | HE-IC-1120 | HE-IC-1120: FS | 2023-11-13 | 2023-11-20
HE-IC-1120 | Completed | P2543-R01-Oct24..1.EN.6.4.A8 | Obtain Company Approval- Datasheet for GOV & ROV | HE-IC-1110 | HE-IC-1110: FS | HE-IC-1130, HE-IC-1660 | HE-IC-1130: FS, HE-IC-1660: FS | 2023-11-24 | 2023-12-07
HE-IC-1130 | Completed | P2543-R01-Oct24..1.EN.6.4.A8 | Final Issue for Design/ Construction-Actuator Datasheet for GOV & ROV | HE-IC-1120, HE-IC-0050, HE-PI-0050 | HE-IC-1120: FS, HE-IC-0050: FF, HE-PI-0050: FS | C-COM-750, CAB-4460 | C-COM-750: FF, CAB-4460: FS | 2023-12-24 | 2024-01-09
HE-IC-1180 | Completed | P2543-R01-Oct24..1.EN.6.4.A6 | Obtain Company Approval- Datasheets for Metering Skid | HE-IC-1170 | HE-IC-1170: FS | HE-IC-1190, HE-IC-1840 | HE-IC-1190: FS, HE-IC-1840: FS | 2023-11-27 | 2023-12-05
HE-IC-1190 | In Progress | P2543-R01-Oct24..1.EN.6.4.A6 | Final Issue for Design/ Construction-Datasheets for Custody Flow Metering Skid | HE-IC-620, HE-IC-0050, HE-IC-1180, HE-PR-0350, ML1002 | HE-IC-620: FS, HE-IC-0050: FF, HE-IC-1180: FS, HE-PR-0350: FS, ML1002: SS | CAB-4460, C-COM-790 | CAB-4460: FS, C-COM-790: FS | 2023-12-06 | 2024-11-01 17:30
HE-IC-1150 | Completed | P2543-R01-Oct24..1.EN.6.4.A6 | Issue ICR- Datasheets for Metering Skid | HE-IC-620, HE-PR-0310, HE-PR-0310, HE-PI-0960, ML1002 | HE-IC-620: FS, HE-PR-0310: SS, HE-PR-0310: FS, HE-PI-0960: FF, ML1002: SS | HE-IC-1810, HE-IC-1160 | HE-IC-1810: FS, HE-IC-1160: FS | 2023-10-02 | 2023-10-23
HE-IC-1160 | Completed | P2543-R01-Oct24..1.EN.6.4.A6 | Receive Company Comments- Datasheets for Metering Skid | HE-IC-1150 | HE-IC-1150: FS | HE-IC-1170 | HE-IC-1170: FS | 2023-11-16 | 2023-11-24
HE-IC-1170 | Completed | P2543-R01-Oct24..1.EN.6.4.A6 | Re-Issue for Approval- Datasheets for Metering Skid | HE-IC-1160, HE-PR-0350, HE-IC-0050 | HE-IC-1160: FS, HE-PR-0350: FS, HE-IC-0050: FS | HE-IC-1180 | HE-IC-1180: FS | 2023-11-22 | 2023-11-25
HE-IC-1210 | Completed | P2543-R01-Oct24..1.EN.6.4.A7 | Issue ICR- Data sheet for PRS (Pressure Reduction System) | HE-PI-0900, HE-PR-0110, HE-IC-0070, HE-PR-0370, HE-PR-0370 | HE-PI-0900: FS, HE-PR-0110: FS, HE-IC-0070: SS, HE-PR-0370: SS, HE-PR-0370: FS | HE-IC-1690, HE-IC-1220 | HE-IC-1690: SS, HE-IC-1220: FS | 2023-10-02 | 2023-10-23
HE-IC-1220 | Completed | P2543-R01-Oct24..1.EN.6.4.A7 | Receive Company Comments- Data sheet for PRS (Pressure Reduction System) | HE-IC-1210 | HE-IC-1210: FS | HE-IC-1230 | HE-IC-1230: FS | 2023-10-24 | 2023-10-26
HE-IC-1230 | Completed | P2543-R01-Oct24..1.EN.6.4.A7 | Re-Issue for Approval- Data sheet for PRS (Pressure Reduction System) | HE-IC-1220 | HE-IC-1220: FS | HE-IC-1240 | HE-IC-1240: FS | 2023-11-14 | 2023-11-27
HE-IC-1240 | Completed | P2543-R01-Oct24..1.EN.6.4.A7 | Obtain Company Approval- Data sheet for PRS (Pressure Reduction System) | HE-IC-1230, HE-PR-0410, HE-IC-0110 | HE-IC-1230: FS, HE-PR-0410: FS, HE-IC-0110: FS | HE-IC-1250, HE-IC-1720 | HE-IC-1250: FS, HE-IC-1720: FS | 2023-11-28 | 2023-12-05
HE-IC-1250 | Completed | P2543-R01-Oct24..1.EN.6.4.A7 | Final Issue for Design/ Construction-Data sheet for PRS (Pressure Reduction System) | HE-PR-0410, HE-IC-0050, HE-IC-1240, HE-HS-0670, HE-PI-0900, HE-PR-0110, HE-IC-0250 | HE-PR-0410: FS, HE-IC-0050: FF, HE-IC-1240: FS, HE-HS-0670: FS, HE-PI-0900: FS, HE-PR-0110: FS, HE-IC-0250: FS | CAB-4460, C-COM-790 | CAB-4460: FS, C-COM-790: FS | 2023-12-06 | 2024-10-07 17:30
HE-IC-1370 | In Progress | P2543-R01-Oct24..1.EN.6.4.A5 | Final Issue for Design/ Construction-Datasheets for PSV & Orifice (incl. RO) | HE-IC-3430, HE-IC-0050, HE-IC-1360 | HE-IC-3430: FF, HE-IC-0050: FS, HE-IC-1360: FS | CAB-4460, C-COM-790 | CAB-4460: FS, C-COM-790: FF | 2024-10-01 07:30 | 2024-11-08 17:30
HE-IC-1330 | Completed | P2543-R01-Oct24..1.EN.6.4.A5 | Issue ICR- Datasheets for PSV & Orifice (incl. RO) | HE-PR-0110, HE-IC-0010, HE-PR-1310 | HE-PR-0110: FS, HE-IC-0010: SS 10, HE-PR-1310: FS | HE-IC-1340, HE-IC-1930 | HE-IC-1340: FS, HE-IC-1930: FS | 2023-11-13 | 2023-11-24
HE-IC-1340 | Completed | P2543-R01-Oct24..1.EN.6.4.A5 | Receive Company Comments- Datasheets for PSV & Orifice (incl. RO) | HE-IC-1330, HE-PR-1570, HE-PR-1320 | HE-IC-1330: FS, HE-PR-1570: FS, HE-PR-1320: FS | HE-IC-1350 | HE-IC-1350: FS | 2023-12-21 | 2024-01-09
HE-IC-1350 | Completed | P2543-R01-Oct24..1.EN.6.4.A5 | Re-Issue for Approval- Datasheets for PSV & Orifice (incl. RO) | HE-IC-1340 | HE-IC-1340: FS | HE-IC-1360 | HE-IC-1360: FS | 2024-01-10 | 2024-01-19
HE-IC-1360 | Completed | P2543-R01-Oct24..1.EN.6.4.A5 | Obtain Company Approval- Datasheets for PSV & Orifice (incl. RO) | HE-IC-1350 | HE-IC-1350: FS | HE-IC-1370, HE-IC-1960 | HE-IC-1370: FS, HE-IC-1960: FS | 2024-01-19 | 2024-01-19
HE-IC-1390 | Completed | P2543-R01-Oct24..1.EN.6.4.A41 | Issue ICR-Datasheets for Pig Signalers | HE-IC-0030 | HE-IC-0030: FS | HE-IC-1400, HE-PL-1930 | HE-IC-1400: FS, HE-PL-1930: FS | 2023-11-08 | 2023-11-24
HE-IC-1400 | Completed | P2543-R01-Oct24..1.EN.6.4.A41 | Receive Company Comments-Datasheets for Pig Signalers | HE-IC-1390 | HE-IC-1390: FS | HE-IC-1410 | HE-IC-1410: FS | 2023-11-25 | 2023-12-07
HE-IC-1410 | Completed | P2543-R01-Oct24..1.EN.6.4.A41 | Re-Issue for Approval-Datasheets for Pig Signalers | HE-IC-1400 | HE-IC-1400: FS | HE-IC-1420 | HE-IC-1420: FS | 2023-12-08 | 2023-12-15
HE-IC-1420 | Completed | P2543-R01-Oct24..1.EN.6.4.A41 | Obtain Company Approval-Datasheets for Pig Signalers | HE-IC-1410 | HE-IC-1410: FS | HE-IC-1430 | HE-IC-1430: FS | 2023-12-16 | 2023-12-19
HE-IC-1430 | Completed | P2543-R01-Oct24..1.EN.6.4.A41 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | HE-IC-0050, HE-IC-1420 | HE-IC-0050: FS, HE-IC-1420: FS | ML1030, ML1859-E31, ML1749-E20, ML1219-B29, CAB-4460, HE-PL-1970, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C-56-PR-838-EI-2030, C-56-591-01-EI-1600, C | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1219-B29: FF, CAB-4460: FS, HE-PL-1970: FF, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-EI-1400: FS, C-56-PR-838-EI-1810: FS, C-56-PR-838-EI-2 | 2023-12-24 | 2024-07-29 17:30
HE-IC-1470 | Completed | P2543-R01-Oct24..1.EN.6.4.A4 | Re-Issue for Approval-Datasheets for Field Instruments / H2S Analyzers | HE-IC-1460 | HE-IC-1460: FS | HE-IC-1480, HE-IC-0630 | HE-IC-1480: FS, HE-IC-0630: FS | 2024-02-26 | 2024-03-01
HE-IC-1480 | Completed | P2543-R01-Oct24..1.EN.6.4.A4 | Obtain Company Approval-Datasheets for Field Instruments / H2S Analyzers | HE-IC-1470 | HE-IC-1470: FS | HE-IC-1490 | HE-IC-1490: FS | 2024-03-04 | 2024-03-17
HE-IC-1490 | Completed | P2543-R01-Oct24..1.EN.6.4.A4 | Final Issue for Design/ Construction-Datasheets for Field Instruments / H2S Analyzers | HE-IC-0050, HE-IC-1480, HE-PR-0110 | HE-IC-0050: FS, HE-IC-1480: FS, HE-PR-0110: FS | HE-IC-0650, CAB-4460 | HE-IC-0650: FS, CAB-4460: FS | 2024-09-30 07:30 | 2024-10-04 17:30
HE-IC-1450 | Completed | P2543-R01-Oct24..1.EN.6.4.A4 | Issue ICR-Datasheets for Field Instruments / H2S Analyzers | HE-IC-0010, HE-PR-0110, HE-PR-1460, HE-PR-1370, HE-PR-1420, HE-PR-1510 | HE-IC-0010: SS 10, HE-PR-0110: FS, HE-PR-1460: FS 5, HE-PR-1370: FS, HE-PR-1420: FS, HE-PR-1510: FS | HE-IC-1930, HE-IC-1460 | HE-IC-1930: FS, HE-IC-1460: FS | 2024-01-02 | 2024-01-08
HE-IC-1460 | Completed | P2543-R01-Oct24..1.EN.6.4.A4 | Receive Company Comments-Datasheets for Field Instruments / H2S Analyzers | HE-IC-1450, HE-PR-1470, HE-PR-1520 | HE-IC-1450: FS, HE-PR-1470: FS, HE-PR-1520: FS | HE-IC-1470 | HE-IC-1470: FS | 2024-01-19 | 2024-01-22
HE-IC-1530 | Completed | P2543-R01-Oct24..1.EN.6.4.A72 | Re-Issue for Approval- Datasheets for F&G Devices | HE-IC-1520 | HE-IC-1520: FS | HE-IC-1540 | HE-IC-1540: FS | 2024-05-24 | 2024-06-05
HE-IC-1540 | Completed | P2543-R01-Oct24..1.EN.6.4.A72 | Obtain Company Approval- Datasheets for F&G Devices | HE-IC-1530 | HE-IC-1530: FS | HE-IC-1550, HE-IC-1900 | HE-IC-1550: FS, HE-IC-1900: FS | 2024-06-05 | 2024-06-07
HE-IC-1550 | Completed | P2543-R01-Oct24..1.EN.6.4.A72 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | HE-IC-0050, HE-IC-1540, HE-IC-0530, HE-PR-0110 | HE-IC-0050: FS, HE-IC-1540: FS, HE-IC-0530: FS, HE-PR-0110: FS | ML1030, ML1859-E31, ML1749-E20, ML1219-B29, CAB-4460, C-56-PL-607-EI-1400, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-PL-607-EI-1800, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-E | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1219-B29: FF, CAB-4460: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-1400: FF, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-2200: FF, C-56-PL-607-EI-1800: FS, C-56-PL-607-EI-1800: FF, C-56-PR-838-EI-1010: FF, C-56-PR | 2024-09-30 07:30 | 2024-10-04 17:30
HE-IC-1510 | Completed | P2543-R01-Oct24..1.EN.6.4.A72 | Issue ICR- Datasheets for F&G Devices | HE-IC-0010, HE-HS-0250, HE-PR-0110 | HE-IC-0010: SS 10, HE-HS-0250: FS, HE-PR-0110: FS | HE-IC-1870, HE-IC-1520 | HE-IC-1870: FS, HE-IC-1520: FS | 2024-01-29 | 2024-02-03
HE-IC-1520 | Completed | P2543-R01-Oct24..1.EN.6.4.A72 | Receive Company Comments- Datasheets for F&G Devices | HE-IC-1510 | HE-IC-1510: FS | HE-IC-1530 | HE-IC-1530: FS | 2024-02-26 | 2024-03-08
HE-IC-1570 | Completed | P2543-R01-Oct24..1.EN.6.11.A1311 | Issue ICR- Material Requisitions for MOV | HE-IC-1030 | HE-IC-1030: FS | HP-ME-0310, HE-IC-1580 | HP-ME-0310: FS, HE-IC-1580: FS | 2023-10-15 | 2023-10-24
HE-IC-1580 | Completed | P2543-R01-Oct24..1.EN.6.11.A1311 | Receive Company Comments- Material Requisitions for MOV | HE-IC-1570 | HE-IC-1570: FS | HE-IC-1590 | HE-IC-1590: FS | 2023-10-25 | 2023-10-27
HE-IC-1590 | Completed | P2543-R01-Oct24..1.EN.6.11.A1311 | Re-Issue for Approval- Material Requisitions for MOV | HE-IC-1050, HE-IC-1580 | HE-IC-1050: FS, HE-IC-1580: FS | HE-IC-1600 | HE-IC-1600: FS | 2024-01-18 | 2024-01-18
HE-IC-1600 | Completed | P2543-R01-Oct24..1.EN.6.11.A1311 | Obtain Company Approval- Material Requisitions for MOV | HE-IC-1590 | HE-IC-1590: FS | HE-IC-1610 | HE-IC-1610: FS | 2024-01-18 | 2024-01-18
HE-IC-1610 | Completed | P2543-R01-Oct24..1.EN.6.11.A1311 | Final Issue for Design/ Construction-Material Requisitions for MOV | HE-IC-1600 | HE-IC-1600: FS | ML1027-B17, HM-ME-0620, CAB-4460, HE-IC-2090 | ML1027-B17: FS, HM-ME-0620: FS, CAB-4460: FS, HE-IC-2090: FS | 2024-01-18 | 2024-04-25
HE-IC-1630 | Completed | P2543-R01-Oct24..1.EN.6.11.A131 | Issue ICR- Material Requisitions for ROV/ GOV | HE-IC-1090 | HE-IC-1090: FS | HP-ME-0260, HE-IC-1640 | HP-ME-0260: FS, HE-IC-1640: FS | 2023-10-15 | 2023-10-24
HE-IC-1640 | Completed | P2543-R01-Oct24..1.EN.6.11.A131 | Receive Company Comments- Material Requisitions for ROV/ GOV | HE-IC-1630 | HE-IC-1630: FS | HE-IC-1650 | HE-IC-1650: FS | 2023-10-25 | 2023-10-26
HE-IC-1650 | Completed | P2543-R01-Oct24..1.EN.6.11.A131 | Re-Issue for Approval- Material Requisitions for ROV/ GOV | HE-IC-1640 | HE-IC-1640: FS | HE-IC-1660 | HE-IC-1660: FS | 2024-02-26 | 2024-02-26
HE-IC-1660 | Completed | P2543-R01-Oct24..1.EN.6.11.A131 | Obtain Company Approval- Material Requisitions for ROV/ GOV | HE-IC-1650, HE-IC-1120 | HE-IC-1650: FS, HE-IC-1120: FS | HE-IC-1670 | HE-IC-1670: FS | 2024-02-26 | 2024-02-26
HE-IC-1670 | Completed | P2543-R01-Oct24..1.EN.6.11.A131 | Final Issue for Design/ Construction-Material Requisitions for ROV/ GOV | HE-IC-1660 | HE-IC-1660: FS | ML1027-B17, CAB-4460, HP-ME-0280 | ML1027-B17: FS, CAB-4460: FS, HP-ME-0280: FS | 2024-03-31 | 2024-04-18
HE-IC-1690 | Completed | P2543-R01-Oct24..1.EN.6.11.A16 | Issue ICR-Material Requisitions for PRS | HE-IC-1210 | HE-IC-1210: SS | HP-ME-0060, HE-IC-1700 | HP-ME-0060: FS, HE-IC-1700: FS | 2023-10-15 | 2023-10-24
HE-IC-1710 | Completed | P2543-R01-Oct24..1.EN.6.11.A16 | Re-Issue for Approval-Material Requisitions for PRS | HE-IC-1700 | HE-IC-1700: FS | HE-IC-1720 | HE-IC-1720: FS | 2023-11-23 | 2024-03-07
HE-IC-1720 | Completed | P2543-R01-Oct24..1.EN.6.11.A16 | Obtain Company Approval-Material Requisitions for PRS | HE-IC-1710, HE-IC-1240 | HE-IC-1710: FS, HE-IC-1240: FS | HE-IC-1730 | HE-IC-1730: FS | 2024-03-01 | 2024-03-07
HE-IC-1730 | In Progress | P2543-R01-Oct24..1.EN.6.11.A16 | Final Issue for Design/ Construction-Material Requisitions for PRS | HE-IC-1720 | HE-IC-1720: FS | CAB-4460 | CAB-4460: FS | 2024-02-14 | 2024-11-01 17:30
HE-IC-1700 | Completed | P2543-R01-Oct24..1.EN.6.11.A16 | Receive Company Comments-Material Requisitions for PRS | HE-IC-1690 | HE-IC-1690: FS | HE-IC-1710 | HE-IC-1710: FS | 2023-11-14 | 2023-11-22
HE-IC-1810 | Completed | P2543-R01-Oct24..1.EN.6.11.A17 | Issue ICR- Material Requisitions for Metering Skid | HE-IC-1150 | HE-IC-1150: FS | HP-ME-0010, HE-IC-1820 | HP-ME-0010: FS, HE-IC-1820: FS | 2023-11-13 | 2023-11-17
HE-IC-1820 | Completed | P2543-R01-Oct24..1.EN.6.11.A17 | Receive Company Comments- Material Requisitions for Metering Skid | HE-IC-1810 | HE-IC-1810: FS | HE-IC-1830 | HE-IC-1830: FS | 2023-11-20 | 2023-12-15
HE-IC-1830 | Completed | P2543-R01-Oct24..1.EN.6.11.A17 | Re-Issue for Approval- Material Requisitions for Metering Skid | HE-IC-1820 | HE-IC-1820: FS | HE-IC-1840 | HE-IC-1840: FS | 2023-11-14 | 2024-01-15
HE-IC-1840 | Completed | P2543-R01-Oct24..1.EN.6.11.A17 | Obtain Company Approval- Material Requisitions for Metering Skid | HE-IC-1830, HE-IC-1180 | HE-IC-1830: FS, HE-IC-1180: FS | HE-IC-1850 | HE-IC-1850: FS | 2024-01-16 | 2024-01-25
HE-IC-1850 | In Progress | P2543-R01-Oct24..1.EN.6.11.A17 | Final Issue for Design/ Construction-Material Requisitions for Metering Skid | HE-IC-1840 | HE-IC-1840: FS | CAB-4460 | CAB-4460: FS | 2024-01-26 07:30 | 2024-11-01 17:30
HE-IC-1880 | Completed | P2543-R01-Oct24..1.EN.6.11.9 | Receive Company Comments- Material Requisitions for Gas Detectors | HE-IC-1870 | HE-IC-1870: FS | HE-IC-1890 | HE-IC-1890: FS | 2024-03-08 | 2024-04-15
HE-IC-1890 | Completed | P2543-R01-Oct24..1.EN.6.11.9 | Re-Issue for Approval- Material Requisitions for Gas Detectors | HE-IC-1880 | HE-IC-1880: FS | HE-IC-1900 | HE-IC-1900: FS | 2024-06-03 | 2024-06-10
HE-IC-1910 | Not Started | P2543-R01-Oct24..1.EN.6.11.9 | Final Issue for Design/ Construction-Material Requisitions for Gas Detectors | HE-IC-1900 | HE-IC-1900: FS | CAB-4460 | CAB-4460: FS | 2024-10-28 07:30 | 2024-11-01 17:30
HE-IC-1900 | Completed | P2543-R01-Oct24..1.EN.6.11.9 | Obtain Company Approval- Material Requisitions for Gas Detectors | HE-IC-1890, HE-IC-1540 | HE-IC-1890: FS, HE-IC-1540: FS | HE-IC-1910 | HE-IC-1910: FS | 2024-06-11 | 2024-06-14
HE-IC-1870 | Completed | P2543-R01-Oct24..1.EN.6.11.9 | Issue ICR- Material Requisitions for Gas Detectors | HE-IC-1510 | HE-IC-1510: FS | HP-ME-0710, HE-IC-1880 | HP-ME-0710: FS, HE-IC-1880: FS | 2024-01-30 | 2024-02-02
HE-IC-2090 | Completed | P2543-R01-Oct24..1.EN.6.2.6 | Final Issue for Design/ Construction-TBE for MOV | HE-IC-2080, HE-IC-1610 | HE-IC-2080: FS, HE-IC-1610: FS | ML1219-B29, CAB-4460, HM-ME-0620 | ML1219-B29: FF, CAB-4460: FS, HM-ME-0620: FS | 2024-04-10 | 2024-04-25
HE-IC-2080 | Completed | P2543-R01-Oct24..1.EN.6.2.6 | Obtain Company Approval- TBE for MOV | HE-IC-2070 | HE-IC-2070: FS | HE-IC-2090, HP-ME-0320 | HE-IC-2090: FS, HP-ME-0320: FF | 2024-03-22 | 2024-03-28
HE-IC-2050 | Completed | P2543-R01-Oct24..1.EN.6.2.6 | Issue ICR- TBE for MOV | HP-ME-0310 | HP-ME-0310: FS | HE-IC-2060, HP-ME-0320 | HE-IC-2060: FS, HP-ME-0320: SS | 2023-11-11 | 2024-01-19
HE-IC-2060 | Completed | P2543-R01-Oct24..1.EN.6.2.6 | Receive Company Comments- TBE for MOV | HE-IC-2050 | HE-IC-2050: FS | HP-ME-0320, HE-IC-2070 | HP-ME-0320: FF, HE-IC-2070: FS | 2024-01-19 | 2024-01-26
HE-IC-2070 | Completed | P2543-R01-Oct24..1.EN.6.2.6 | Re-Issue for Approval- TBE for MOV | HE-IC-2060 | HE-IC-2060: FS | HE-IC-2080 | HE-IC-2080: FS | 2024-02-26 | 2024-03-22
HE-IC-2110 | Completed | P2543-R01-Oct24..1.EN.6.2.A30 | Issue ICR-TBE for Metering Skid | HP-ME-0010 | HP-ME-0010: FS | HE-IC-2120, HP-ME-0020 | HE-IC-2120: FS, HP-ME-0020: SS | 2023-11-23 | 2024-01-26
HE-IC-2130 | Completed | P2543-R01-Oct24..1.EN.6.2.A30 | Re-Issue for Approval-TBE for Metering Skid | HE-IC-2120 | HE-IC-2120: FS | HE-IC-2140 | HE-IC-2140: FS | 2024-04-19 | 2024-04-26
HE-IC-2140 | Completed | P2543-R01-Oct24..1.EN.6.2.A30 | Obtain Company Approval-TBE for Metering Skid | HE-IC-2130 | HE-IC-2130: FS | HE-IC-2150, HP-ME-0020 | HE-IC-2150: FS, HP-ME-0020: FF | 2024-04-19 | 2024-04-26
HE-IC-2150 | Completed | P2543-R01-Oct24..1.EN.6.2.A30 | Final Issue for Design/ Construction-TBE for Metering Skid | HE-IC-2140 | HE-IC-2140: FS | CAB-4460, HP-ME-0030 | CAB-4460: FS, HP-ME-0030: FF | 2024-04-19 | 2024-04-26
HE-IC-2120 | Completed | P2543-R01-Oct24..1.EN.6.2.A30 | Receive Company Comments-TBE for Metering Skid | HE-IC-2110 | HE-IC-2110: FS | HE-IC-2130 | HE-IC-2130: FS | 2024-03-31 | 2024-04-18
HE-IC-2190 | Completed | P2543-R01-Oct24..1.EN.6.2.A33 | Re-Issue for Approval-TBE for PRS | HE-IC-2180 | HE-IC-2180: FS | HE-IC-2200 | HE-IC-2200: FS | 2024-04-19 | 2024-04-26
HE-IC-2200 | Completed | P2543-R01-Oct24..1.EN.6.2.A33 | Obtain Company Approval-TBE for PRS | HE-IC-2190 | HE-IC-2190: FS | HP-ME-0070, HE-IC-2210, HP-ME-0080 | HP-ME-0070: FF, HE-IC-2210: FS, HP-ME-0080: FS | 2024-04-19 | 2024-04-26
HE-IC-2210 | Completed | P2543-R01-Oct24..1.EN.6.2.A33 | Final Issue for Design/ Construction-TBE for PRS | HE-IC-2200 | HE-IC-2200: FS | CAB-4460, HP-ME-0080 | CAB-4460: FS, HP-ME-0080: FF | 2024-04-19 | 2024-04-26
HE-IC-2170 | Completed | P2543-R01-Oct24..1.EN.6.2.A33 | Issue ICR-TBE for PRS | HP-ME-0060 | HP-ME-0060: FS | HE-IC-2180, HP-ME-0070 | HE-IC-2180: FS, HP-ME-0070: SS | 2023-11-16 | 2024-01-10
HE-IC-2180 | Completed | P2543-R01-Oct24..1.EN.6.2.A33 | Receive Company Comments-TBE for PRS | HE-IC-2170 | HE-IC-2170: FS | HE-IC-2190 | HE-IC-2190: FS | 2024-02-26 | 2024-03-08
HE-IC-2290 | Completed | P2543-R01-Oct24..1.EN.6.2.5 | Issue ICR- TBE for ROV/ GOV | HP-ME-0260 | HP-ME-0260: FS | HE-IC-2300, HP-ME-0270 | HE-IC-2300: FS, HP-ME-0270: SS | 2023-11-11 | 2024-01-12
HE-IC-2300 | Completed | P2543-R01-Oct24..1.EN.6.2.5 | Receive Company Comments- TBE for ROV/ GOV | HE-IC-2290 | HE-IC-2290: FS | HE-IC-2310 | HE-IC-2310: FS | 2024-02-14 | 2024-02-16
HE-IC-2330 | Completed | P2543-R01-Oct24..1.EN.6.2.5 | Final Issue for Design/ Construction-TBE for ROV/ GOV | HE-IC-2320 | HE-IC-2320: FS | HM-ME-0510, ML1219-B29, CAB-4460 | HM-ME-0510: SS, ML1219-B29: FF, CAB-4460: FS | 2024-03-31 | 2024-04-18
HE-IC-2320 | Completed | P2543-R01-Oct24..1.EN.6.2.5 | Obtain Company Approval- TBE for ROV/ GOV | HE-IC-2310 | HE-IC-2310: FS | HP-ME-0280, HE-IC-2330, HP-ME-0270 | HP-ME-0280: FS, HE-IC-2330: FS, HP-ME-0270: FF | 2024-03-04 | 2024-03-17
HE-IC-2310 | Completed | P2543-R01-Oct24..1.EN.6.2.5 | Re-Issue for Approval- TBE for ROV/ GOV | HE-IC-2300 | HE-IC-2300: FS | HE-IC-2320 | HE-IC-2320: FS | 2024-02-26 | 2024-03-01
HE-IC-2390 | In Progress | P2543-R01-Oct24..1.EN.6.2.10 | Final Issue for Design/ Construction-TBE for Gas Detectors | HE-IC-2380 | HE-IC-2380: FS | HE-IC-2510, CAB-4460 | HE-IC-2510: FF, CAB-4460: FS | 2024-07-20 07:30 | 2024-11-01 17:30
HE-IC-2350 | Completed | P2543-R01-Oct24..1.EN.6.2.10 | Issue ICR- TBE for Gas Detectors | HP-ME-0710, HP-ME-0760 | HP-ME-0710: FS, HP-ME-0760: FS | HE-IC-2360, HP-ME-0720 | HE-IC-2360: FS, HP-ME-0720: SS | 2024-05-24 | 2024-05-30
HE-IC-2360 | Completed | P2543-R01-Oct24..1.EN.6.2.10 | Receive Company Comments- TBE for Gas Detectors | HE-IC-2350 | HE-IC-2350: FS | HE-IC-2370 | HE-IC-2370: FS | 2024-05-31 | 2024-06-21
HE-IC-2370 | Completed | P2543-R01-Oct24..1.EN.6.2.10 | Re-Issue for Approval- TBE for Gas Detectors | HE-IC-2360 | HE-IC-2360: FS | HE-IC-2380 | HE-IC-2380: FS | 2024-06-22 | 2024-07-04 17:30
HE-IC-2380 | Completed | P2543-R01-Oct24..1.EN.6.2.10 | Obtain Company Approval- TBE for Gas Detectors | HE-IC-2370 | HE-IC-2370: FS | HE-IC-2390 | HE-IC-2390: FS | 2024-07-05 07:30 | 2024-07-19 17:30
HE-IC-2530 | Completed | P2543-R01-Oct24..1.EN.6.A27 | Issue ICR- Instrument location and Cable Routing Drawings | HE-IC-0790, HE-IC-0550, HE-IC-0490, HE-IC-0250, HE-IC-0190, HE-PR-0110 | HE-IC-0790: FS, HE-IC-0550: FS, HE-IC-0490: FS, HE-IC-0250: FS, HE-IC-0190: FS, HE-PR-0110: FS | HE-IC-0910, HE-IC-0970, HE-IC-2540, HE-IC-3090 | HE-IC-0910: FS, HE-IC-0970: FS, HE-IC-2540: FS, HE-IC-3090: FS | 2024-05-16 | 2024-05-23
HE-IC-2550 | Completed | P2543-R01-Oct24..1.EN.6.A27 | Re-Issue for Approval- Instrument location and Cable Routing Drawings | HE-IC-0810, HE-IC-2540, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190 | HE-IC-0810: FS, HE-IC-2540: FS, HE-IC-0570: FS, HE-IC-0210: FS, HE-IC-0270: FS, HE-IC-0790: FS, HE-IC-0250: FS, HE-IC-0190: FS | HE-IC-2560, HE-IC-2610 | HE-IC-2560: FS, HE-IC-2610: SS | 2024-06-04 | 2024-07-29 17:30
HE-IC-2560 | Completed | P2543-R01-Oct24..1.EN.6.A27 | Obtain Company Approval- Instrument location and Cable Routing Drawings | HE-IC-2550 | HE-IC-2550: FS | HE-IC-2570 | HE-IC-2570: FS | 2024-09-30 07:30 | 2024-10-14 17:30
HE-IC-2570 | In Progress | P2543-R01-Oct24..1.EN.6.A27 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | HE-IC-2560, HE-IC-0230, HE-IC-0290, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190, HE-PR-0110 | HE-IC-2560: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0570: FS, HE-IC-0210: FS, HE-IC-0270: FS, HE-IC-0790: FS, HE-IC-0250: FS, HE-IC-0190: FS, HE-PR-0110: FS | ML1030, ML1859-E31, ML1749-E20, CAB-4460, ML1032-B21, HE-CO-200, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C-56-PR-838-EI-2030, C-56-591-01-EI-1600, C- | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, CAB-4460: FS, ML1032-B21: FS, HE-CO-200: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-EI-1400: FS, C-56-PR-838-EI-1810: FS, C-56-PR-838-EI-20 | 2024-10-14 07:30 | 2024-11-08 17:30
HE-IC-2540 | Completed | P2543-R01-Oct24..1.EN.6.A27 | Receive Company Comments- Instrument location and Cable Routing Drawings | HE-IC-2530 | HE-IC-2530: FS | HE-IC-2550 | HE-IC-2550: FS | 2024-05-24 | 2024-06-03
HE-IC-2590 | Completed | P2543-R01-Oct24..1.EN.6.A39 | Instrument 1st MTO | HE-IC-0530 | HE-IC-0530: FS | HP-BK-0460, HE-IC-2610 | HP-BK-0460: FS, HE-IC-2610: FS | 2024-10-08 07:30 | 2024-10-15 17:30
HE-IC-2610 | Not Started | P2543-R01-Oct24..1.EN.6.A39 | Instrument 2nd MTO | HE-IC-0630, HE-IC-0990, HE-IC-0930, HE-IC-2550, HE-IC-0510, HE-IC-0690, HE-IC-2590, HE-PR-0110, HE-IC-3040 | HE-IC-0630: FS, HE-IC-0990: FS, HE-IC-0930: FS, HE-IC-2550: SS, HE-IC-0510: FS, HE-IC-0690: FS, HE-IC-2590: FS, HE-PR-0110: FS, HE-IC-3040: FS | HE-IC-2630 | HE-IC-2630: FS | 2024-11-11 07:30 | 2024-11-15 17:30
HE-IC-2630 | Not Started | P2543-R01-Oct24..1.EN.6.A39 | Instrument 3rd MTO | HE-IC-0710, HE-IC-0650, HE-IC-0530, HE-IC-1070, HE-IC-0710, HE-IC-2610, ML2079-B13, HE-PR-0110 | HE-IC-0710: FS, HE-IC-0650: FS, HE-IC-0530: FS, HE-IC-1070: FS, HE-IC-0710: FF, HE-IC-2610: FS, ML2079-B13: FS, HE-PR-0110: FS | ML1219-B29, HP-BK-0470, CAB-4460 | ML1219-B29: FF, HP-BK-0470: FF, CAB-4460: FS | 2024-11-18 07:30 | 2024-11-22 17:30
HE-IC-0010 | Completed | P2543-R01-Oct24..1.EN.6.A91 | Issue ICR- Addendum to DGs | HE-DB-0010, HE-IC-620 | HE-DB-0010: FS, HE-IC-620: FS | ML1030, ML1859-E31, ML1749-E20, HE-IC-1450, C-COM-790, C-COM-790, HE-IC-0020, HE-IC-1510, CAB-4460, HE-IC-1330, HE-IC-2940, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1000, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-8 | ML1030: SS, ML1859-E31: SS, ML1749-E20: SS, HE-IC-1450: SS 10, C-COM-790: FS, C-COM-790: FF, HE-IC-0020: FS, HE-IC-1510: SS 10, CAB-4460: FS, HE-IC-1330: SS 10, HE-IC-2940: FS, C-56-PL-607-EI-1400: SS 10, C-56-PL-607-EI-2200: SS 10, C-56-PL-607-EI-1800: SS | 2023-09-06 | 2023-09-22
HE-IC-0020 | Completed | P2543-R01-Oct24..1.EN.6.A91 | Receive Company Comments- Addendum to DGs | HE-IC-0010 | HE-IC-0010: FS | HE-IC-0030 | HE-IC-0030: FS | 2023-09-23 | 2023-10-05
HE-IC-0030 | Completed | P2543-R01-Oct24..1.EN.6.A91 | Re-Issue for Approval- Addendum to DGs | HE-IC-0020 | HE-IC-0020: FS | HE-IC-0040, HE-IC-1390 | HE-IC-0040: FS, HE-IC-1390: FS | 2023-10-06 | 2023-10-23
HE-IC-0040 | Completed | P2543-R01-Oct24..1.EN.6.A91 | Obtain Company Approval- Addendum to DGs | HE-IC-0030 | HE-IC-0030: FS | HE-IC-0050 | HE-IC-0050: FS | 2023-11-14 | 2023-11-21
HE-IC-0050 | Completed | P2543-R01-Oct24..1.EN.6.A91 | Final Issue for Design/ Construction-Addendum to DGs | HE-IC-0040, HE-IC-610 | HE-IC-0040: FS, HE-IC-610: FS | HE-IC-1490, HE-IC-1370, HE-IC-1550, HE-IC-1190, HE-IC-1430, HE-IC-1130, HE-IC-1250, HE-IC-1070, CAB-4460, HE-IC-1790, HE-IC-0110, HE-IC-0230, HE-IC-0290, HE-IC-1170 | HE-IC-1490: FS, HE-IC-1370: FS, HE-IC-1550: FS, HE-IC-1190: FF, HE-IC-1430: FS, HE-IC-1130: FF, HE-IC-1250: FF, HE-IC-1070: FF, CAB-4460: FS, HE-IC-1790: FS, HE-IC-0110: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-1170: FS | 2023-11-22 | 2023-12-06
HE-IC-0080 | Completed | P2543-R01-Oct24..1.EN.6.A111 | Receive Company Comments- Specifications for PRS (Pressure Reduction System) | HE-IC-0070 | HE-IC-0070: FS | HE-IC-0090 | HE-IC-0090: FS | 2023-09-23 | 2023-10-05
HE-IC-0090 | Completed | P2543-R01-Oct24..1.EN.6.A111 | Re-Issue for Approval- Specifications for PRS (Pressure Reduction System) | HE-IC-0080 | HE-IC-0080: FS | HE-IC-0100 | HE-IC-0100: FS | 2023-10-06 | 2023-10-27
HE-IC-0100 | Completed | P2543-R01-Oct24..1.EN.6.A111 | Obtain Company Approval- Specifications for PRS (Pressure Reduction System) | HE-IC-0090 | HE-IC-0090: FS | HE-IC-0110 | HE-IC-0110: FS | 2023-11-10 | 2023-11-21
HE-IC-0110 | Completed | P2543-R01-Oct24..1.EN.6.A111 | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | HE-IC-0100, HE-IC-0050 | HE-IC-0100: FS, HE-IC-0050: FS | CAB-4460, HE-PR-0410, HE-IC-1240, C-56-HC01-PL-TE-8200, C-56-HC01-PL-TE-8400, C-56-PR-838-TE-1000, C-52-HG01-PL-TE-8200, C-52-598-04-TE-1000, C-52-PR-839-ME-2000, C-52-PR-839-ME-2010, C-52-PR-839-TE-1410, C-52-PL-838-TE-1000, C-4N-HG-TPR-TE-1410, C-MAQTA-T | CAB-4460: FS, HE-PR-0410: FS, HE-IC-1240: FS, C-56-HC01-PL-TE-8200: FS, C-56-HC01-PL-TE-8400: FS, C-56-PR-838-TE-1000: FS, C-52-HG01-PL-TE-8200: FS, C-52-598-04-TE-1000: FS, C-52-PR-839-ME-2000: FS, C-52-PR-839-ME-2010: FS, C-52-PR-839-TE-1410: FS, C-52-PL | 2023-11-22 | 2023-12-11
HE-IC-0070 | Completed | P2543-R01-Oct24..1.EN.6.A111 | Issue ICR- Specifications for PRS (Pressure Reduction System) | HE-PR-0110, HE-IC-620, ML1002 | HE-PR-0110: FF 2, HE-IC-620: FS, ML1002: SS | HE-IC-1210, HE-IC-0080 | HE-IC-1210: SS, HE-IC-0080: FS | 2023-09-06 | 2023-09-22
HE-IC-0190 | Completed | P2543-R01-Oct24..1.EN.6.A20 | Issue ICR- Specification for RTU | HE-PR-0110 | HE-PR-0110: FS 5 | HE-IC-3240, HS-GN-0430, HE-IC-0790, HE-IC-0200, CAB-4460, HE-TL-0070, HE-IC-2530, HE-IC-1990, HE-IC-0970, HE-IC-0910, HE-IC-2550, HE-IC-0750, HE-IC-0930, HE-IC-0990, HE-IC-1010, HE-IC-0950, HE-IC-2570, HE-IC-0770, HE-IC-2880, HE-TL-0370, HE-TL-0790, HE-TL- | HE-IC-3240: FS, HS-GN-0430: FS, HE-IC-0790: FS, HE-IC-0200: FS, CAB-4460: FS, HE-TL-0070: SS, HE-IC-2530: FS, HE-IC-1990: FS, HE-IC-0970: FS, HE-IC-0910: FS, HE-IC-2550: FS, HE-IC-0750: FS, HE-IC-0930: FS, HE-IC-0990: FS, HE-IC-1010: FS, HE-IC-0950: FS, HE | 2023-11-17 | 2023-11-23
HE-IC-0200 | Completed | P2543-R01-Oct24..1.EN.6.A20 | Receive Company Comments- Specification for RTU | HE-IC-0190 | HE-IC-0190: FS | HE-IC-0210 | HE-IC-0210: FS | 2023-11-24 | 2023-12-05
HE-IC-0210 | Completed | P2543-R01-Oct24..1.EN.6.A20 | Re-Issue for Approval- Specification for RTU | HE-IC-0200 | HE-IC-0200: FS | HE-EL-5440, HE-TL-0450, HE-IC-0810, HE-IC-0220, HE-IC-2550, HE-IC-0750, HE-IC-0930, HE-IC-0990, HE-IC-1010, HE-IC-0950, HE-IC-2570, HE-IC-0770, CAB-4460, C-56-PL-607-EI-2000, C-56-EB2-EI-1200, C-56-EB2-EI-1210, C-56-EB2-EI-1220, C-56-PR-838-CA-1000, C-56-P | HE-EL-5440: FS, HE-TL-0450: FS, HE-IC-0810: FS, HE-IC-0220: FS, HE-IC-2550: FS, HE-IC-0750: FS, HE-IC-0930: FS, HE-IC-0990: FS, HE-IC-1010: FS, HE-IC-0950: FS, HE-IC-2570: FS, HE-IC-0770: FS, CAB-4460: FS, C-56-PL-607-EI-2000: FS, C-56-EB2-EI-1200: FS, C-5 | 2023-12-29 | 2024-01-09
HE-IC-0220 | Completed | P2543-R01-Oct24..1.EN.6.A20 | Obtain Company Approval- Specification for RTU | HE-IC-0210 | HE-IC-0210: FS | HE-IC-0230 | HE-IC-0230: FS | 2024-01-12 | 2024-01-17
HE-IC-0230 | Completed | P2543-R01-Oct24..1.EN.6.A20 | Final Issue for Design/ Construction-Specification for RTU | HE-IC-0220, HE-IC-0050 | HE-IC-0220: FS, HE-IC-0050: FS | HE-TL-0110, CAB-4460, HS-GN-0430, HE-EL-5480, HE-IC-0830, HE-IC-1010, HE-IC-0950, HE-IC-2570, HE-IC-0770, HE-TL-0410, HE-TL-0350, HE-TL-0590, CAB-4470, HE-TL-0830, HE-TL-0470, HE-TL-0530, ML1033-B22, HE-TL-0290, HE-TL-0230, C-56-PL-607-EI-2000, C-56-EB2-EI | HE-TL-0110: FS, CAB-4460: FS, HS-GN-0430: FS, HE-EL-5480: FS, HE-IC-0830: FS, HE-IC-1010: FS, HE-IC-0950: FS, HE-IC-2570: FS, HE-IC-0770: FS, HE-TL-0410: FS, HE-TL-0350: FS, HE-TL-0590: FS, CAB-4470: FS, HE-TL-0830: FS, HE-TL-0470: FS, HE-TL-0530: FS, ML10 | 2024-03-31 | 2024-04-19
HE-IC-1970 | Completed | P2543-R01-Oct24..1.EN.6.11.2 | Final Issue for Design/ Construction-Material Requisitions for Field Instruments / H2S Analyzers | HE-IC-1960 | HE-IC-1960: FS | ML1027-B17, HP-ME-0730, CAB-4460 | ML1027-B17: FS, HP-ME-0730: FS, CAB-4460: FS | 2024-05-24 | 2024-06-04
HE-IC-1960 | Completed | P2543-R01-Oct24..1.EN.6.11.2 | Obtain Company Approval- Material Requisitions for Field Instruments / H2S Analyzers | HE-IC-1950, HE-IC-1360 | HE-IC-1950: FS, HE-IC-1360: FS | HE-IC-1970 | HE-IC-1970: FS | 2024-05-16 | 2024-05-24
HE-IC-1930 | Completed | P2543-R01-Oct24..1.EN.6.11.2 | Issue ICR- Material Requisitions for Field Instruments / H2S Analyzers | HE-IC-1450, HE-IC-1330 | HE-IC-1450: FS, HE-IC-1330: FS | HP-ME-0710, HE-IC-1940, HP-ME-0760, HS-GN-0250, HS-GN-0370 | HP-ME-0710: FS, HE-IC-1940: FS, HP-ME-0760: FS, HS-GN-0250: FS, HS-GN-0370: FS | 2024-01-29 | 2024-02-02
HE-IC-1940 | Completed | P2543-R01-Oct24..1.EN.6.11.2 | Receive Company Comments- Material Requisitions for Field Instruments / H2S Analyzers | HE-IC-1930 | HE-IC-1930: FS | HE-IC-1950 | HE-IC-1950: FS | 2024-02-26 | 2024-03-08
HE-IC-1950 | Completed | P2543-R01-Oct24..1.EN.6.11.2 | Re-Issue for Approval- Material Requisitions for Field Instruments / H2S Analyzers | HE-IC-1940 | HE-IC-1940: FS | HE-IC-1960 | HE-IC-1960: FS | 2024-03-10 | 2024-05-15
HE-EL-5440 | Completed | P2543-R01-Oct24..1.EN.9.A37 | Issue ICR- Power Consumption Calculation (Instrumentation) | HE-IC-0210, HE-IC-0270, HE-TL-0090, HE-IC-0190, HE-IC-0250 | HE-IC-0210: FS, HE-IC-0270: FS, HE-TL-0090: FS, HE-IC-0190: SS, HE-IC-0250: SS | HE-EL-5450 | HE-EL-5450: FS | 2024-10-14 07:30 | 2024-10-21 17:30
HE-EL-5450 | Not Started | P2543-R01-Oct24..1.EN.9.A37 | Receive Company Comments- Power Consumption Calculation (Instrumentation) | HE-EL-5440 | HE-EL-5440: FS | HE-EL-5460 | HE-EL-5460: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HE-EL-5460 | Not Started | P2543-R01-Oct24..1.EN.9.A37 | Re-Issue for Approval- Power Consumption Calculation (Instrumentation) | HE-EL-5450 | HE-EL-5450: FS | HE-EL-5470 | HE-EL-5470: FS | 2024-11-11 07:30 | 2024-11-15 17:30
HE-EL-5470 | Not Started | P2543-R01-Oct24..1.EN.9.A37 | Obtain Company Approval- Power Consumption Calculation (Instrumentation) | HE-EL-5460 | HE-EL-5460: FS | HE-EL-5480 | HE-EL-5480: FS 10 | 2024-11-18 07:30 | 2024-11-29 17:30
HE-EL-5480 | Not Started | P2543-R01-Oct24..1.EN.9.A37 | Final Issue for Design/ Construction-Power Consumption Calculation (Instrumentation) | HE-IC-0290, HE-IC-0230, HE-EL-5470 | HE-IC-0290: FS, HE-IC-0230: FS, HE-EL-5470: FS 10 | CAB-4460, C-COM-790 | CAB-4460: FS, C-COM-790: FS | 2024-12-18 07:30 | 2024-12-24 17:30
HE-IC-0530 | Completed | P2543-R01-Oct24..1.EN.6.A2 | Final Issue for Design/ Construction-Instrument Index | HE-IC-3230, HE-IC-3230, HE-IC-0520 | HE-IC-3230: FF, HE-IC-3230: FS, HE-IC-0520: FS | ML1030, ML1859-E31, ML1749-E20, CAB-4460, HE-IC-0590, HE-IC-2630, HE-IC-1550, HE-IC-2740, HE-IC-2590, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1000, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-83 | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, CAB-4460: FS, HE-IC-0590: FS, HE-IC-2630: FS, HE-IC-1550: FS, HE-IC-2740: FS, HE-IC-2590: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-EB2-EI-1000: FS, C-56-PR-838-EI-1010: | 2024-01-26 | 2024-03-27
HE-IC-0490 | Completed | P2543-R01-Oct24..1.EN.6.A2 | Issue ICR-Instrument index -Update | HE-IC-3380, HE-IC-3280, HE-PR-0110, HE-HS-0250 | HE-IC-3380: FS, HE-IC-3280: FS, HE-PR-0110: FS, HE-HS-0250: FS 15 | ML1030, ML1859-E31, ML1749-E20, HE-IC-0500, C-COM-790, HE-IC-0610, HE-IC-2530, HE-IC-0670, CAB-4460, C-COM-790, HE-IC-0550, HE-IC-2750, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1000, C-56-PR-838-EI-1010, C-56-PR-838-EI-140 | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, HE-IC-0500: FS, C-COM-790: FF, HE-IC-0610: FS, HE-IC-2530: FS, HE-IC-0670: FS, CAB-4460: FS, C-COM-790: FS, HE-IC-0550: FS, HE-IC-2750: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: F | 2023-12-25 | 2024-01-05
HE-IC-0500 | Completed | P2543-R01-Oct24..1.EN.6.A2 | Receive Company Comments-Instrument index -Update | HE-IC-0490 | HE-IC-0490: FS | HE-IC-0510 | HE-IC-0510: FS | 2023-12-25 | 2024-01-05
HE-IC-0510 | Completed | P2543-R01-Oct24..1.EN.6.A2 | Re-Issue for Approval-Instrument index -Update | HE-IC-0500 | HE-IC-0500: FS | HE-IC-0690, HE-TL-0450, HE-IC-2610, HE-IC-0520, HE-TL-0390, HE-IC-0570, HE-IC-0630 | HE-IC-0690: FS, HE-TL-0450: FS, HE-IC-2610: FS, HE-IC-0520: FS, HE-TL-0390: FS, HE-IC-0570: FS, HE-IC-0630: FS | 2023-12-25 | 2024-01-05
HE-IC-0520 | Completed | P2543-R01-Oct24..1.EN.6.A2 | Obtain Company Approval-Instrument index -Update | HE-IC-0510 | HE-IC-0510: FS | HE-IC-0530, HE-IC-0580 | HE-IC-0530: FS, HE-IC-0580: FS | 2023-12-25 | 2024-01-05
HE-IC-2450 | Completed | P2543-R01-Oct24..1.EN.6.2.3 | Final Issue for Design/ Construction-TBE for Field Instruments / H2S Analyzers | HE-IC-2440 | HE-IC-2440: FS | ML1219-B29, CAB-4460, HM-ME-1520 | ML1219-B29: FF, CAB-4460: FS, HM-ME-1520: FF | 2024-06-15 | 2024-10-01
HE-IC-2410 | Completed | P2543-R01-Oct24..1.EN.6.2.3 | Issue ICR- TBE for Field Instruments / H2S Analyzers | HP-ME-0760 | HP-ME-0760: FS | HE-IC-2420, HP-ME-0770 | HE-IC-2420: FS, HP-ME-0770: SS | 2024-04-07 | 2024-04-12
HE-IC-2420 | Completed | P2543-R01-Oct24..1.EN.6.2.3 | Receive Company Comments- TBE for Field Instruments / H2S Analyzers | HE-IC-2410 | HE-IC-2410: FS | HE-IC-2430 | HE-IC-2430: FS | 2024-04-13 | 2024-05-16
HE-IC-2430 | Completed | P2543-R01-Oct24..1.EN.6.2.3 | Re-Issue for Approval- TBE for Field Instruments / H2S Analyzers | HE-IC-2420 | HE-IC-2420: FS | HE-IC-2440 | HE-IC-2440: FS | 2024-05-17 | 2024-05-31
HE-IC-2440 | Completed | P2543-R01-Oct24..1.EN.6.2.3 | Obtain Company Approval- TBE for Field Instruments / H2S Analyzers | HE-IC-2430 | HE-IC-2430: FS | HE-IC-2450, HP-ME-0770, HS-GN-0280, HS-GN-0400 | HE-IC-2450: FS, HP-ME-0770: FF, HS-GN-0280: FF, HS-GN-0400: FF | 2024-06-03 | 2024-06-14
HE-IC-2000 | Completed | P2543-R01-Oct24..1.EN.6.11.7 | Receive Company Comments- Material Requisitions for Junction Boxes | HE-IC-1990 | HE-IC-1990: FS | HE-IC-2010 | HE-IC-2010: FS | 2024-05-17 | 2024-06-03
HE-IC-2010 | Completed | P2543-R01-Oct24..1.EN.6.11.7 | Re-Issue for Approval- Material Requisitions for Junction Boxes | HE-IC-2000 | HE-IC-2000: FS | HE-IC-2020 | HE-IC-2020: FS | 2024-06-04 | 2024-09-02 17:30
HE-IC-2030 | Completed | P2543-R01-Oct24..1.EN.6.11.7 | Final Issue for Design/ Construction-Material Requisitions for Junction Boxes | HE-IC-2020 | HE-IC-2020: FS | HP-ME-0830, HE-IC-2510 | HP-ME-0830: FS, HE-IC-2510: FS | 2024-09-30 07:30 | 2024-10-08 17:30
HE-IC-2020 | Completed | P2543-R01-Oct24..1.EN.6.11.7 | Obtain Company Approval- Material Requisitions for Junction Boxes | HE-IC-2010 | HE-IC-2010: FS | HE-IC-2030 | HE-IC-2030: FS | 2024-09-03 07:30 | 2024-09-16 17:30
HE-IC-1990 | Completed | P2543-R01-Oct24..1.EN.6.11.7 | Issue ICR- Material Requisitions for Junction Boxes | HE-IC-0250, HE-IC-0190 | HE-IC-0250: FS, HE-IC-0190: FS | HP-ME-0810, HE-IC-2000 | HP-ME-0810: FS, HE-IC-2000: FS | 2024-04-30 | 2024-05-16
HE-IC-2510 | Not Started | P2543-R01-Oct24..1.EN.6.2.8 | Final Issue for Design/ Construction-TBE for Junction Boxes | HE-IC-2390, HE-IC-2500, HE-IC-2030 | HE-IC-2390: FF, HE-IC-2500: FF, HE-IC-2030: FS | HE-IC-3120 | HE-IC-3120: FF | 2024-11-04 07:30 | 2024-11-08 17:30
HE-IC-2470 | Completed | P2543-R01-Oct24..1.EN.6.2.8 | Issue ICR- TBE for Junction Boxes | HP-ME-0810 | HP-ME-0810: FS | HE-IC-2480 | HE-IC-2480: FS | 2024-08-15 07:30 | 2024-08-28 17:30
HE-IC-2480 | Completed | P2543-R01-Oct24..1.EN.6.2.8 | Receive Company Comments- TBE for Junction Boxes | HE-IC-2470 | HE-IC-2470: FS | HE-IC-2490 | HE-IC-2490: FS | 2024-09-02 07:30 | 2024-09-12 17:30
HE-IC-2490 | Completed | P2543-R01-Oct24..1.EN.6.2.8 | Re-Issue for Approval- TBE for Junction Boxes | HE-IC-2480 | HE-IC-2480: FS | HE-IC-2500 | HE-IC-2500: FS | 2024-10-07 07:30 | 2024-10-18 17:30
HE-IC-2500 | In Progress | P2543-R01-Oct24..1.EN.6.2.8 | Obtain Company Approval- TBE for Junction Boxes | HE-IC-2490 | HE-IC-2490: FS | HE-IC-2510 | HE-IC-2510: FF | 2024-10-18 07:30 | 2024-11-08 17:30
HE-IC-0250 | Completed | P2543-R01-Oct24..1.EN.6.A201 | Issue ICR- Specification for Leak Detection System | HE-PR-0110, HE-IC-620 | HE-PR-0110: SS, HE-IC-620: FS | CAB-4460, HE-IC-0790, HE-TL-0070, HE-IC-0260, HS-GN-0430, HE-IC-2530, HE-IC-1990, HE-IC-0970, HE-IC-0910, HE-IC-2550, HE-IC-0750, HE-IC-0930, HE-IC-0990, HE-IC-1010, HE-IC-0950, HE-IC-2570, HE-IC-0770, HE-IC-1750, HE-IC-1770, HE-IC-1250, HE-IC-1790, HE-TL- | CAB-4460: FS, HE-IC-0790: FS, HE-TL-0070: SS, HE-IC-0260: FS, HS-GN-0430: FS, HE-IC-2530: FS, HE-IC-1990: FS, HE-IC-0970: FS, HE-IC-0910: FS, HE-IC-2550: FS, HE-IC-0750: FS, HE-IC-0930: FS, HE-IC-0990: FS, HE-IC-1010: FS, HE-IC-0950: FS, HE-IC-2570: FS, HE | 2023-09-27 | 2023-10-02
HE-IC-0260 | Completed | P2543-R01-Oct24..1.EN.6.A201 | Receive Company Comments- Specification for Leak Detection System | HE-IC-0250 | HE-IC-0250: FS | HE-IC-0270 | HE-IC-0270: FS | 2023-10-03 | 2023-10-15
HE-IC-0270 | Completed | P2543-R01-Oct24..1.EN.6.A201 | Re-Issue for Approval- Specification for Leak Detection System | HE-IC-0260 | HE-IC-0260: FS | HE-IC-0280, HE-EL-5440, HE-IC-0810, HE-TL-0450, HE-IC-2550, HE-IC-0750, HE-IC-0930, HE-IC-0990, HE-IC-1010, HE-IC-0950, HE-IC-2570, HE-IC-0770, CAB-4460, C-56-PL-607-EI-2000, C-56-EB2-EI-1200, C-56-EB2-EI-1210, C-56-EB2-EI-1220, C-56-PR-838-CA-1000, C-56-P | HE-IC-0280: FS, HE-EL-5440: FS, HE-IC-0810: FS, HE-TL-0450: FS, HE-IC-2550: FS, HE-IC-0750: FS, HE-IC-0930: FS, HE-IC-0990: FS, HE-IC-1010: FS, HE-IC-0950: FS, HE-IC-2570: FS, HE-IC-0770: FS, CAB-4460: FS, C-56-PL-607-EI-2000: FS, C-56-EB2-EI-1200: FS, C-5 | 2023-10-17 | 2023-11-24
HE-IC-0280 | Completed | P2543-R01-Oct24..1.EN.6.A201 | Obtain Company Approval- Specification for Leak Detection System | HE-IC-0270 | HE-IC-0270: FS | HE-IC-0290 | HE-IC-0290: FS | 2023-11-25 | 2023-12-12
HE-IC-0290 | Completed | P2543-R01-Oct24..1.EN.6.A201 | Final Issue for Design/ Construction-Specification for Leak Detection System | HE-IC-0280, HE-IC-0050 | HE-IC-0280: FS, HE-IC-0050: FS | HE-EL-5480, HE-IC-0830, HE-TL-0110, HS-GN-0430, CAB-4460, HE-IC-1010, HE-IC-0950, HE-IC-2570, HE-IC-0770, HE-IC-1790, HE-TL-0410, HE-TL-0350, HE-TL-0590, CAB-4470, HE-TL-0830, HE-TL-0470, HE-TL-0530, ML1033-B22, HE-TL-0290, HE-TL-0230, HE-IC-1750, C-56-PL- | HE-EL-5480: FS, HE-IC-0830: FS, HE-TL-0110: FS, HS-GN-0430: FS, CAB-4460: FS, HE-IC-1010: FS, HE-IC-0950: FS, HE-IC-2570: FS, HE-IC-0770: FS, HE-IC-1790: FS, HE-TL-0410: FS, HE-TL-0350: FS, HE-TL-0590: FS, CAB-4470: FS, HE-TL-0830: FS, HE-TL-0470: FS, HE-T | 2024-02-26 | 2024-03-01
HE-IC-0970 | Completed | P2543-R01-Oct24..1.EN.6.A341 | Issue ICR-Instrument Trench Layout | HE-IC-0800, HE-IC-2530, HE-IC-0790, HE-IC-0250, HE-IC-0190, HE-IC-0910 | HE-IC-0800: FS, HE-IC-2530: FS, HE-IC-0790: FS, HE-IC-0250: FS, HE-IC-0190: FS, HE-IC-0910: SS | HE-IC-0980 | HE-IC-0980: FS | 2024-05-01 | 2024-05-06
HE-IC-0980 | Completed | P2543-R01-Oct24..1.EN.6.A341 | Receive Company Comments-Instrument Trench Layout | HE-IC-0970 | HE-IC-0970: FS | HE-IC-0990 | HE-IC-0990: FS | 2024-05-07 | 2024-05-13
HE-IC-0990 | Completed | P2543-R01-Oct24..1.EN.6.A341 | Re-Issue for Approval-Instrument Trench Layout | HE-IC-0980, HE-IC-0820, HE-TL-0450, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190 | HE-IC-0980: FS, HE-IC-0820: FS, HE-TL-0450: FS, HE-IC-0570: FS, HE-IC-0210: FS, HE-IC-0270: FS, HE-IC-0790: FS, HE-IC-0250: FS, HE-IC-0190: FS | HE-IC-2610, HE-IC-1000, HE-IC-0750 | HE-IC-2610: FS, HE-IC-1000: FS, HE-IC-0750: FS | 2024-05-17 | 2024-05-21
HE-IC-1000 | Completed | P2543-R01-Oct24..1.EN.6.A341 | Obtain Company Approval-Instrument Trench Layout | HE-IC-0990 | HE-IC-0990: FS | HE-IC-1010, HE-IC-0940 | HE-IC-1010: FS, HE-IC-0940: FS | 2024-05-14 | 2024-05-16
HE-IC-1010 | Completed | P2543-R01-Oct24..1.EN.6.A341 | Final Issue for Design/ Construction-Instrument Trench Layout | HE-IC-1000, HE-IC-0230, HE-IC-0290, HE-IC-0570, HE-IC-0210, HE-IC-0270, HE-IC-0790, HE-IC-0250, HE-IC-0190 | HE-IC-1000: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0570: FS, HE-IC-0210: FS, HE-IC-0270: FS, HE-IC-0790: FS, HE-IC-0250: FS, HE-IC-0190: FS | HS-CN-0410, HE-IC-0770, ML1032-B21, CAB-4460, C-56-PL-607-EI-2000, C-56-EB2-EI-1200, C-56-EB2-EI-1210, C-56-EB2-EI-1220, C-56-PR-838-CA-1000, C-56-PR-838-CA-1030, C-56-PR-838-EI-2000, C-56-PR-838-EI-2010, C-56-PR-838-EI-2040, C-56-591-01-EI-2000, C-56-591- | HS-CN-0410: FS 76, HE-IC-0770: FS, ML1032-B21: FS, CAB-4460: FS, C-56-PL-607-EI-2000: FS, C-56-EB2-EI-1200: FS, C-56-EB2-EI-1210: FS, C-56-EB2-EI-1220: FS, C-56-PR-838-CA-1000: FS, C-56-PR-838-CA-1030: FS, C-56-PR-838-EI-2000: FS, C-56-PR-838-EI-2010: FS, | 2024-05-22 | 2024-05-31
HE-IC-1750 | Completed | P2543-R01-Oct24..1.EN.6.11.A161 | Issue ICR-Material Requisitions for Leak Detection System | HE-PI-0900, HE-PR-0110, HE-IC-0250, HE-PI-0940, HE-IC-0290 | HE-PI-0900: FS, HE-PR-0110: FS, HE-IC-0250: FS, HE-PI-0940: FS 10, HE-IC-0290: FS | HP-ME-0110, HE-IC-1760 | HP-ME-0110: FS, HE-IC-1760: FS | 2023-11-20 | 2023-12-15
HE-IC-1770 | Completed | P2543-R01-Oct24..1.EN.6.11.A161 | Re-Issue for Approval-Material Requisitions for Leak Detection System | HE-IC-1760, HE-HS-0670, HE-PI-0900, HE-PR-0110, HE-IC-0250 | HE-IC-1760: FS, HE-HS-0670: FS, HE-PI-0900: FS, HE-PR-0110: FS, HE-IC-0250: FS | HE-IC-1780 | HE-IC-1780: FS | 2024-03-10 | 2024-03-17
HE-IC-1780 | Completed | P2543-R01-Oct24..1.EN.6.11.A161 | Obtain Company Approval-Material Requisitions for Leak Detection System | HE-IC-1770 | HE-IC-1770: FS | HE-IC-1790 | HE-IC-1790: FS | 2024-03-18 | 2024-03-28
HE-IC-1790 | Completed | P2543-R01-Oct24..1.EN.6.11.A161 | Final Issue for Design/ Construction-Material Requisitions for Leak Detection System | HE-IC-1780, HE-PR-0410, HE-IC-0290, HE-IC-0050, HE-HS-0670, HE-PI-0900, HE-PR-0110, HE-IC-0250 | HE-IC-1780: FS, HE-PR-0410: FS, HE-IC-0290: FS, HE-IC-0050: FS, HE-HS-0670: FS, HE-PI-0900: FS, HE-PR-0110: FS, HE-IC-0250: FS | HM-ME-0220, CAB-4460 | HM-ME-0220: FS, CAB-4460: FS | 2024-05-08 | 2024-09-16 17:30
HE-IC-1760 | Completed | P2543-R01-Oct24..1.EN.6.11.A161 | Receive Company Comments-Material Requisitions for Leak Detection System | HE-IC-1750 | HE-IC-1750: FS | HE-IC-1770 | HE-IC-1770: FS | 2024-02-26 | 2024-03-08
HE-IC-2250 | Completed | P2543-R01-Oct24..1.EN.6.2.A331 | Re-Issue for Approval-TBE for Leak Detection System | HE-IC-2240 | HE-IC-2240: FS | HE-IC-2260 | HE-IC-2260: FS | 2024-03-27 | 2024-05-31
HE-IC-2260 | Completed | P2543-R01-Oct24..1.EN.6.2.A331 | Obtain Company Approval-TBE for Leak Detection System | HE-IC-2250 | HE-IC-2250: FS | HE-IC-2270 | HE-IC-2270: FS | 2024-06-03 | 2024-06-27 17:30
HE-IC-2270 | Completed | P2543-R01-Oct24..1.EN.6.2.A331 | Final Issue for Design/ Construction-TBE for Leak Detection System | HE-IC-2260 | HE-IC-2260: FS | CAB-4460 | CAB-4460: FS | 2024-08-13 07:30 | 2024-09-02 17:30
HE-IC-2230 | Completed | P2543-R01-Oct24..1.EN.6.2.A331 | Issue ICR-TBE for Leak Detection System | HP-ME-0110 | HP-ME-0110: FS | HE-IC-2240, HP-ME-0120 | HE-IC-2240: FS, HP-ME-0120: SS | 2024-02-26 | 2024-03-14
HE-IC-2240 | Completed | P2543-R01-Oct24..1.EN.6.2.A331 | Receive Company Comments-TBE for Leak Detection System | HE-IC-2230 | HE-IC-2230: FS | HE-IC-2250 | HE-IC-2250: FS | 2024-03-15 | 2024-03-28
HE-PL-2090 | Completed | P2543-R01-Oct24..1.EN.1.10.23 | Issue ICR - TBE for Hot Induction Bends | HP-ME-1170 | HP-ME-1170: FS | HE-PL-2100, HP-ME-1180 | HE-PL-2100: FS, HP-ME-1180: SS | 2023-09-07 | 2023-09-17
HE-PL-2100 | Completed | P2543-R01-Oct24..1.EN.1.10.23 | Receive Company Comments - TBE for Hot Induction Bends | HE-PL-2090 | HE-PL-2090: FS | HE-PL-2110 | HE-PL-2110: FS | 2023-09-18 | 2023-09-21
HE-PL-2130 | In Progress | P2543-R01-Oct24..1.EN.1.10.23 | Final Issue for Design/ Construction-TBE for Hot Induction Bends | HE-PL-2120 | HE-PL-2120: FS | CAB-4480 | CAB-4480: FS | 2024-02-23 | 2024-11-01 17:30
HE-PL-2110 | Completed | P2543-R01-Oct24..1.EN.1.10.23 | Re-Issue for Approval - TBE for Hot Induction Bends | HE-PL-2100 | HE-PL-2100: FS | HE-PL-2120 | HE-PL-2120: FS | 2023-11-08 | 2023-11-17
HE-PL-2120 | Completed | P2543-R01-Oct24..1.EN.1.10.23 | Obtain Company Approval - TBE for Hot Induction Bends | HE-PL-2110 | HE-PL-2110: FS | HE-PL-2130, HP-ME-1180 | HE-PL-2130: FS, HP-ME-1180: FF | 2023-11-20 | 2023-11-24
HE-PL-2180 | Completed | P2543-R01-Oct24..1.EN.1.10.24 | Obtain Company Approval - TBE for Pigging Tees | HE-PL-2170 | HE-PL-2170: FS | HE-PL-2190, HP-ME-1280 | HE-PL-2190: FS, HP-ME-1280: FF | 2024-05-26 | 2024-06-04
HE-PL-2150 | Completed | P2543-R01-Oct24..1.EN.1.10.24 | Issue ICR - TBE for Pigging Tees | HP-ME-1270 | HP-ME-1270: FS | HE-PL-2160, HP-ME-1280 | HE-PL-2160: FS, HP-ME-1280: SS | 2024-02-26 | 2024-03-15
HE-PL-2160 | Completed | P2543-R01-Oct24..1.EN.1.10.24 | Receive Company Comments - TBE for Pigging Tees | HE-PL-2150 | HE-PL-2150: FS | HE-PL-2170 | HE-PL-2170: FS | 2024-03-31 | 2024-04-18
HE-PL-2170 | Completed | P2543-R01-Oct24..1.EN.1.10.24 | Re-Issue for Approval - TBE for Pigging Tees | HE-PL-2160 | HE-PL-2160: FS | HE-PL-2180 | HE-PL-2180: FS | 2024-04-19 | 2024-05-25
HE-PL-2190 | Completed | P2543-R01-Oct24..1.EN.1.10.24 | Final Issue for Design/ Construction-TBE for Pigging Tees | HE-PL-2180 | HE-PL-2180: FS | CCM-PM4540, CAB-4480 | CCM-PM4540: FS, CAB-4480: FS | 2024-10-07 07:30 | 2024-10-23 17:30
HE-PL-2210 | Completed | P2543-R01-Oct24..1.EN.1.10.25 | Issue ICR - TBE for Isolating Joints | HP-ME-1220 | HP-ME-1220: FS | HE-PL-2220, HP-ME-1230 | HE-PL-2220: FS, HP-ME-1230: SS | 2023-11-03 | 2023-11-14
HE-PL-2220 | Completed | P2543-R01-Oct24..1.EN.1.10.25 | Receive Company Comments - TBE for Isolating Joints | HE-PL-2210 | HE-PL-2210: FS | HE-PL-2230 | HE-PL-2230: FS | 2023-11-15 | 2023-11-21
HE-PL-2230 | Completed | P2543-R01-Oct24..1.EN.1.10.25 | Re-Issue for Approval - TBE for Isolating Joints | HE-PL-2220 | HE-PL-2220: FS | HE-PL-2240 | HE-PL-2240: FS | 2023-11-22 | 2024-02-17
HE-PL-2240 | Completed | P2543-R01-Oct24..1.EN.1.10.25 | Obtain Company Approval - TBE for Isolating Joints | HE-PL-2230 | HE-PL-2230: FS | HE-PL-2250, HP-ME-1230 | HE-PL-2250: FS, HP-ME-1230: FF | 2024-02-18 | 2024-02-18
HE-PL-2250 | In Progress | P2543-R01-Oct24..1.EN.1.10.25 | Final Issue for Design/ Construction-TBE for Isolating Joints | HE-PL-2240 | HE-PL-2240: FS | HE-PL-2310, CAB-4480 | HE-PL-2310: FF 5, CAB-4480: FS | 2024-02-19 | 2024-11-08 17:30
HE-PL-2290 | Completed | P2543-R01-Oct24..1.EN.6.2.26 | Re-Issue for Approval - TBE for Mainline Ball Valve | HE-PL-2280 | HE-PL-2280: FS | HE-PL-2300 | HE-PL-2300: FS | 2024-03-05 | 2024-04-19
HE-PL-2300 | Completed | P2543-R01-Oct24..1.EN.6.2.26 | Obtain Company Approval - TBE for Mainline Ball Valve | HE-PL-2290 | HE-PL-2290: FS | HE-PL-2310, HP-ME-1080 | HE-PL-2310: FS, HP-ME-1080: FF | 2024-04-20 | 2024-04-30
HE-PL-2310 | In Progress | P2543-R01-Oct24..1.EN.6.2.26 | Final Issue for Design/ Construction-TBE for Mainline Ball Valve | HE-PL-2250, HE-PL-2300 | HE-PL-2250: FF 5, HE-PL-2300: FS | CAB-4480 | CAB-4480: FS | 2024-08-01 07:30 | 2024-11-15 17:30
HE-PL-2280 | Completed | P2543-R01-Oct24..1.EN.6.2.26 | Receive Company Comments - TBE for Mainline Ball Valve | HE-PL-2270 | HE-PL-2270: FS | HE-PL-2290 | HE-PL-2290: FS | 2024-01-12 | 2024-03-04
HE-PL-2270 | Completed | P2543-R01-Oct24..1.EN.6.2.26 | Issue ICR - TBE for Mainline Ball Valve | HP-ME-1070 | HP-ME-1070: FS | HE-PL-2280, HP-ME-1080 | HE-PL-2280: FS, HP-ME-1080: SS | 2024-01-05 | 2024-01-11
HE-PL-2330 | Completed | P2543-R01-Oct24..1.EN.6.2.54 | Issue ICR- TBE for Pig Signaler | HP-ME-1120 | HP-ME-1120: FS | HE-PL-2340, HP-ME-1130 | HE-PL-2340: FS, HP-ME-1130: SS | 2024-05-03 | 2024-05-15
HE-PL-2340 | Completed | P2543-R01-Oct24..1.EN.6.2.54 | Receive Company Comments- TBE for Pig Signaler | HE-PL-2330 | HE-PL-2330: FS | HE-PL-2350 | HE-PL-2350: FS | 2024-04-30 | 2024-05-16
HE-PL-2350 | Completed | P2543-R01-Oct24..1.EN.6.2.54 | Re-Issue for Approval- TBE for Pig Signaler | HE-PL-2340 | HE-PL-2340: FS | HE-PL-2360 | HE-PL-2360: FS | 2024-05-17 | 2024-06-05
HE-PL-2360 | Completed | P2543-R01-Oct24..1.EN.6.2.54 | Obtain Company Approval- TBE for Pig Signaler | HE-PL-2350 | HE-PL-2350: FS | HE-PL-2370, HP-ME-1130 | HE-PL-2370: FS, HP-ME-1130: FF | 2024-06-06 | 2024-06-21
HE-PL-2370 | In Progress | P2543-R01-Oct24..1.EN.6.2.54 | Final Issue for Design/ Construction-TBE for Pig Signaler | HE-PL-2360, HE-PL-1970 | HE-PL-2360: FS, HE-PL-1970: FF | CAB-4480 | CAB-4480: FS | 2024-06-22 | 2024-11-01 17:30
HE-PL-2390 | Completed | P2543-R01-Oct24..1.EN.1.29 | Issue ICR - Pipeline Alignment Sheets -56" | HE-PL-2450, HE-TS-0010, HE-TS-230 | HE-PL-2450: FF 14, HE-TS-0010: FS 10, HE-TS-230: FS 10 | HE-PL-2570, HE-PL-2400, HE-PL-2870, HE-PL-2750, HE-PL-2930, HE-PL-3230, C-PER-0915 | HE-PL-2570: FF 10, HE-PL-2400: FS, HE-PL-2870: FS, HE-PL-2750: FS, HE-PL-2930: FS, HE-PL-3230: FS, C-PER-0915: FS | 2024-01-27 | 2024-02-22
HE-PL-2400 | Completed | P2543-R01-Oct24..1.EN.1.29 | Receive Company Comments - Pipeline Alignment Sheets -56" | HE-PL-2390 | HE-PL-2390: FS | HE-PL-2410 | HE-PL-2410: FS | 2024-02-23 | 2024-03-06
HE-PL-2410 | Completed | P2543-R01-Oct24..1.EN.1.29 | Re-Issue for Approval - Pipeline Alignment Sheets -56" | HE-PL-2400 | HE-PL-2400: FS | HE-PL-2420 | HE-PL-2420: FS | 2024-03-07 | 2024-03-15
HE-PL-2420 | Completed | P2543-R01-Oct24..1.EN.1.29 | Obtain Company Approval - Pipeline Alignment Sheets -56" | HE-PL-2410 | HE-PL-2410: FS | ML1008-B03, HE-PL-2870, HS-GN-0490, HE-PL-1930, HE-PL-2430 | ML1008-B03: FF, HE-PL-2870: FS 30, HS-GN-0490: FS, HE-PL-1930: FS, HE-PL-2430: FS | 2024-03-16 | 2024-03-25
HE-PL-2430 | In Progress | P2543-R01-Oct24..1.EN.1.29 | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | HE-PL-2420 | HE-PL-2420: FS | ML1219-B39, CAB-4480, C-PER-1350, C-PER-1370, C-PER-1380, C-PER-1390, C-PER-1400, C-PER-1430, C-PER-1440, C-PER-1450, C-PER-1460, C-PER-1470, C-PER-1360, C-PER-1420 | ML1219-B39: FF, CAB-4480: FS, C-PER-1350: SS, C-PER-1370: FF 14, C-PER-1380: FS, C-PER-1390: FS, C-PER-1400: FF 14, C-PER-1430: FS, C-PER-1440: SS 14, C-PER-1450: FS, C-PER-1460: SS, C-PER-1470: FS, C-PER-1360: FS, C-PER-1420: FS | 2024-03-26 | 2024-11-01 17:30
HE-PL-2470 | Completed | P2543-R01-Oct24..1.EN.1.35 | Re-Issue for Approval - Pipeline Alignment Sheets-52" | HE-PL-2460, HE-PL-0210 | HE-PL-2460: FS, HE-PL-0210: FS | HE-PL-2990, HE-PL-2480 | HE-PL-2990: FS 2, HE-PL-2480: FS | 2024-01-26 | 2024-03-13
HE-PL-2480 | Completed | P2543-R01-Oct24..1.EN.1.35 | Obtain Company Approval - Pipeline Alignment Sheets-52" | HE-PL-2470 | HE-PL-2470: FS | ML1009-B04, HE-PL-2490, HE-PL-1930 | ML1009-B04: FF, HE-PL-2490: FS, HE-PL-1930: FS | 2024-03-04 | 2024-03-21
HE-PL-2490 | In Progress | P2543-R01-Oct24..1.EN.1.35 | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | HE-PL-2480, HE-PL-0230, HE-PL-0290 | HE-PL-2480: FS, HE-PL-0230: FF, HE-PL-0290: FF | ML1219-B49, CAB-4480, C-PER-1030, C-PER-1070, C-PER-1130, C-PER-1140, C-PER-1150, C-PER-1160, C-PER-1180, C-PER-1190, C-PER-1200, C-PER-1210, C-PER-1220, C-PER-1250, C-PER-1260, C-PER-1280, C-PER-1300, C-PER-1310, C-PER-1320, C-PER-1330, C-PER-1340, C-PER- | ML1219-B49: FF, CAB-4480: FS, C-PER-1030: FF 14, C-PER-1070: FF, C-PER-1130: SS 14, C-PER-1140: SS, C-PER-1150: SS, C-PER-1160: SS, C-PER-1180: SS, C-PER-1190: SS, C-PER-1200: SS, C-PER-1210: FF, C-PER-1220: FS, C-PER-1250: FS, C-PER-1260: SS, C-PER-1280: | 2024-03-18 | 2024-11-01 17:30
HE-PL-2450 | Completed | P2543-R01-Oct24..1.EN.1.35 | Issue ICR - Pipeline Alignment Sheets-52" | HE-TS-0010, HE-TS-280 | HE-TS-0010: FS 15, HE-TS-280: FS 15 | HE-PL-2630, HE-PL-2390, HE-PL-2990, HE-PL-3050, HE-PL-2750, HE-CS-1150, HE-PL-2460 | HE-PL-2630: FS, HE-PL-2390: FF 14, HE-PL-2990: FS, HE-PL-3050: FS, HE-PL-2750: FS, HE-CS-1150: FF, HE-PL-2460: FS | 2023-11-22 | 2024-02-11
HE-PL-2460 | Completed | P2543-R01-Oct24..1.EN.1.35 | Receive Company Comments - Pipeline Alignment Sheets-52" | HE-PL-2450 | HE-PL-2450: FS | HE-PL-2470 | HE-PL-2470: FS | 2023-12-21 | 2024-02-11
HE-PL-2510 | Completed | P2543-R01-Oct24..1.EN.1.7 | Issue ICR - Pipeline Alignment Sheets-4" | HE-TS-0010, HE-TS-330 | HE-TS-0010: FS 30, HE-TS-330: FS 30 | HE-PL-2690, HE-PL-3110, HE-PL-2520, HE-PL-3170, HE-PL-3580 | HE-PL-2690: FS, HE-PL-3110: FS, HE-PL-2520: FS, HE-PL-3170: FS, HE-PL-3580: FS | 2024-02-26 | 2024-03-08
HE-PL-2520 | Completed | P2543-R01-Oct24..1.EN.1.7 | Receive Company Comments - Pipeline Alignment Sheets-4" | HE-PL-2510 | HE-PL-2510: FS | HE-PL-2530 | HE-PL-2530: FS | 2024-03-10 | 2024-03-25
HE-PL-2530 | Completed | P2543-R01-Oct24..1.EN.1.7 | Re-Issue for Approval - Pipeline Alignment Sheets-4" | HE-PL-2520 | HE-PL-2520: FS | HE-PL-2540 | HE-PL-2540: FS | 2024-03-25 | 2024-04-07
HE-PL-2540 | Completed | P2543-R01-Oct24..1.EN.1.7 | Obtain Company Approval - Pipeline Alignment Sheets-4" | HE-PL-2530 | HE-PL-2530: FS | HE-PL-3110, HE-PL-2550 | HE-PL-3110: FS, HE-PL-2550: FS | 2024-04-12 | 2024-04-25
HE-PL-2550 | In Progress | P2543-R01-Oct24..1.EN.1.7 | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | HE-PL-2540, HE-TS-320, HE-GS-180 | HE-PL-2540: FS, HE-TS-320: FS, HE-GS-180: FS | C-4N-H5HG-PIPEL-1800, ML1219-B59, CAB-4480, C-PER-1490, C-PER-1500, C-PER-1510, C-PER-1520, C-PER-1530, C-PER-1540, C-PER-1550, C-PER-1480 | C-4N-H5HG-PIPEL-1800: FF 17, ML1219-B59: FF, CAB-4480: FS, C-PER-1490: FS, C-PER-1500: FS, C-PER-1510: FS, C-PER-1520: FS, C-PER-1530: FS, C-PER-1540: FS, C-PER-1550: FS, C-PER-1480: FS | 2024-05-10 | 2024-11-01 17:30
HE-PL-2570 | Completed | P2543-R01-Oct24..1.EN.1.31 | Issue ICR - Pipeline Station Approach drawing -56" | HE-PL-2390, HE-PI-0390, HE-TS-0010, HE-PI-0320, HE-TS-230 | HE-PL-2390: FF 10, HE-PI-0390: FS, HE-TS-0010: FS, HE-PI-0320: FS, HE-TS-230: FS | HE-PL-2580, HE-PL-2810, HE-PL-3330 | HE-PL-2580: FS, HE-PL-2810: FS, HE-PL-3330: FS | 2024-03-29 | 2024-04-07
HE-PL-2580 | Completed | P2543-R01-Oct24..1.EN.1.31 | Receive Company Comments - Pipeline Station Approach drawing -56" | HE-PL-2570 | HE-PL-2570: FS | HE-PL-2590 | HE-PL-2590: FS | 2024-04-08 | 2024-04-25
HE-PL-2590 | Completed | P2543-R01-Oct24..1.EN.1.31 | Re-Issue for Approval - Pipeline Station Approach drawing -56" | HE-PL-2580 | HE-PL-2580: FS | HE-PL-2600 | HE-PL-2600: FS | 2024-04-26 | 2024-05-31
HE-PL-2600 | Completed | P2543-R01-Oct24..1.EN.1.31 | Obtain Company Approval - Pipeline Station Approach drawing -56" | HE-PL-2590 | HE-PL-2590: FS | HE-PL-2610 | HE-PL-2610: FS | 2024-06-01 | 2024-06-14
HE-PL-2610 | In Progress | P2543-R01-Oct24..1.EN.1.31 | Final Issue for Design/ Construction-Pipeline Station approach drawing - 56" | HE-PL-2600, HE-PI-0440, HE-TS-0050, HE-TS-220 | HE-PL-2600: FS, HE-PI-0440: FF 10, HE-TS-0050: FS, HE-TS-220: FS | CAB-4480, HE-PL-2850, ML1059-B28 | CAB-4480: FS, HE-PL-2850: FF, ML1059-B28: FS | 2024-07-04 07:30 | 2024-11-15 17:30
HE-PL-2660 | Completed | P2543-R01-Oct24..1.EN.1.37 | Obtain Company Approval - Pipeline Station Approach drawing -52" | HE-PL-2650 | HE-PL-2650: FS | HE-PL-2670 | HE-PL-2670: FS | 2024-06-05 07:30 | 2024-07-04 17:30
HE-PL-2670 | In Progress | P2543-R01-Oct24..1.EN.1.37 | Final Issue for Design/ Construction-Pipeline Station approach drawing-52" | HE-TS-0050, HE-PL-2660, HE-TS-270 | HE-TS-0050: FS, HE-PL-2660: FS, HE-TS-270: FS | CAB-4480, ML1059-B28, C-PER-1590, C-PER-1600, C-PER-1610, C-PER-1620, C-PER-1630, C-PER-1650 | CAB-4480: FS, ML1059-B28: FS, C-PER-1590: SS, C-PER-1600: SS, C-PER-1610: SS, C-PER-1620: SS, C-PER-1630: SS, C-PER-1650: FS | 2024-07-05 07:30 | 2024-11-01 17:30
HE-PL-2630 | Completed | P2543-R01-Oct24..1.EN.1.37 | Issue ICR - Pipeline Station Approach drawing -52" | HE-PL-2450, HE-PI-0390, HE-TS-0010, HE-TS-280 | HE-PL-2450: FS, HE-PI-0390: FS, HE-TS-0010: FS, HE-TS-280: FS | HE-PL-2640, HE-PL-2810 | HE-PL-2640: FS, HE-PL-2810: FS | 2024-03-31 | 2024-04-26
HE-PL-2640 | Completed | P2543-R01-Oct24..1.EN.1.37 | Receive Company Comments - Pipeline Station Approach drawing -52" | HE-PL-2630 | HE-PL-2630: FS | HE-PL-2650 | HE-PL-2650: FS | 2024-04-26 07:30 | 2024-05-25 17:30
HE-PL-2650 | Completed | P2543-R01-Oct24..1.EN.1.37 | Re-Issue for Approval - Pipeline Station Approach drawing -52" | HE-PL-2640 | HE-PL-2640: FS | HE-PL-2660 | HE-PL-2660: FS | 2024-05-27 07:30 | 2024-06-04 17:30
HE-PL-2690 | Completed | P2543-R01-Oct24..1.EN.1.15 | Issue ICR - Pipeline Station Approach drawing -4" | HE-PL-2510, HE-PI-0460, HE-TS-0010, HE-TS-330 | HE-PL-2510: FS, HE-PI-0460: FS, HE-TS-0010: FS, HE-TS-330: FS | HE-PL-2700 | HE-PL-2700: FS | 2024-03-29 | 2024-05-14
HE-PL-2700 | Completed | P2543-R01-Oct24..1.EN.1.15 | Receive Company Comments - Pipeline Station Approach drawing -4" | HE-PL-2690 | HE-PL-2690: FS | HE-PL-2710 | HE-PL-2710: FS | 2024-05-15 | 2024-05-29
HE-PL-2710 | Completed | P2543-R01-Oct24..1.EN.1.15 | Re-Issue for Approval - Pipeline Station Approach drawing -4" | HE-PL-2700 | HE-PL-2700: FS | HE-PL-2720 | HE-PL-2720: FS | 2024-05-30 | 2024-07-08 17:30
HE-PL-2720 | Completed | P2543-R01-Oct24..1.EN.1.15 | Obtain Company Approval - Pipeline Station Approach drawing -4" | HE-PL-2710 | HE-PL-2710: FS | HE-PL-2730 | HE-PL-2730: FS | 2024-07-09 07:30 | 2024-07-15 17:30
HE-PL-2730 | Not Started | P2543-R01-Oct24..1.EN.1.15 | Final Issue for Design/ Construction-Pipeline Station approach drawing-4" | HE-PL-2720 | HE-PL-2720: FS | CAB-4480, ML1059-B28 | CAB-4480: FS, ML1059-B28: FF | 2024-10-28 07:30 | 2024-11-01 17:30
HE-PL-2750 | Completed | P2543-R01-Oct24..1.EN.1.1 | Issue ICR - Pipeline Route Verification and Selection Report | HE-TS-0010, HE-PL-2390, HE-PL-2450, HE-PL-3530 | HE-TS-0010: FS, HE-PL-2390: FS, HE-PL-2450: FS, HE-PL-3530: FS | HE-PL-2760 | HE-PL-2760: FS | 2024-05-06 07:30 | 2024-05-20
HE-PL-2760 | Completed | P2543-R01-Oct24..1.EN.1.1 | Receive Company Comments - Pipeline Route Verification and Selection Report | HE-PL-2750 | HE-PL-2750: FS | HE-PL-2770 | HE-PL-2770: FS | 2024-05-21 07:30 | 2024-05-31 17:30
HE-PL-2770 | Completed | P2543-R01-Oct24..1.EN.1.1 | Re-Issue for Approval - Pipeline Route Verification and Selection Report | HE-PL-2760 | HE-PL-2760: FS | HE-PL-2780 | HE-PL-2780: FS | 2024-06-03 07:30 | 2024-06-17 17:30
HE-PL-2780 | Completed | P2543-R01-Oct24..1.EN.1.1 | Obtain Company Approval - Pipeline Route Verification and Selection Report | HE-PL-2770 | HE-PL-2770: FS | HE-PL-2790 | HE-PL-2790: FS | 2024-06-18 07:30 | 2024-09-26 07:30
HE-PL-2790 | Completed | P2543-R01-Oct24..1.EN.1.1 | Final Issue for Design/ Construction-Pipeline Route Verification and Selection Report | HE-TS-0050, HE-PL-2780 | HE-TS-0050: FS, HE-PL-2780: FS | CAB-4480 | CAB-4480: FS | 2024-10-07 07:30 | 2024-10-21 17:30
HE-PL-2810 | Completed | P2543-R01-Oct24..1.EN.1.5 | Issue ICR - Pipeline Stress Analysis Report | HE-PL-0610, HE-PL-0670, HE-PL-2570, HE-PL-2630 | HE-PL-0610: FS, HE-PL-0670: FS, HE-PL-2570: FS, HE-PL-2630: FS | HE-CS-1710, HE-PI-1140, HE-PL-2820, HE-PL-1510 | HE-CS-1710: FF 10, HE-PI-1140: SS, HE-PL-2820: FS, HE-PL-1510: FS | 2024-05-06 | 2024-05-16
HE-PL-2820 | Completed | P2543-R01-Oct24..1.EN.1.5 | Receive Company Comments - Pipeline Stress Analysis Report | HE-PL-2810 | HE-PL-2810: FS | HE-PL-2830 | HE-PL-2830: FS | 2024-05-17 | 2024-05-24
HE-PL-2830 | Completed | P2543-R01-Oct24..1.EN.1.5 | Re-Issue for Approval - Pipeline Stress Analysis Report | HE-PL-2820 | HE-PL-2820: FS | HE-PI-1160, HE-PL-2840 | HE-PI-1160: SS, HE-PL-2840: FS | 2024-05-26 | 2024-05-31
HE-PL-2840 | Completed | P2543-R01-Oct24..1.EN.1.5 | Obtain Company Approval - Pipeline Stress Analysis Report | HE-PL-2830 | HE-PL-2830: FS | HE-PL-2850 | HE-PL-2850: FS | 2024-06-01 | 2024-06-21
HE-PL-2850 | In Progress | P2543-R01-Oct24..1.EN.1.5 | Final Issue for Design/ Construction-Pipeline Stress Analysis Report | HE-PL-0710, HE-PL-2840, HE-PL-2610 | HE-PL-0710: FF 5, HE-PL-2840: FS, HE-PL-2610: FF | HE-PL-1550, CAB-4480 | HE-PL-1550: FF, CAB-4480: FS | 2024-06-05 07:30 | 2024-11-15 17:30
HE-PL-2890 | Completed | P2543-R01-Oct24..1.EN.1.30 | Re-Issue for Approval - Detailed crossing drawings - 56" | HE-PL-2880 | HE-PL-2880: FF | HE-PL-2900, C-PER-1470, C-PER-1420 | HE-PL-2900: FF 10, C-PER-1470: SS 7, C-PER-1420: FF | 2024-05-13 | 2024-10-14 17:30
HE-PL-2900 | Completed | P2543-R01-Oct24..1.EN.1.30 | Obtain Company Approval - Detailed crossing drawings - 56" | HE-PL-2890 | HE-PL-2890: FF 10 | HE-PL-2910 | HE-PL-2910: FF 5 | 2024-05-26 07:30 | 2024-10-24 17:30
HE-PL-2910 | In Progress | P2543-R01-Oct24..1.EN.1.30 | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | HE-PL-2900 | HE-PL-2900: FF 5 | ML1219-B29, CAB-4480, ML1579-E03, C-56-HC01-CMA01-1000, C-56-HC01-CMA02-1000, C-56-HC01-CMA03-1000, C-56-HC01-CMA04-1000, C-56-HC01-CMA05-1000, C-56-HC01-CMA06-1000, C-56-HC01-CMA07-1000, C-56-HC01-CMA08-1000, C-56-HC01-CMA09-1000, C-56-HC01-CMA10-1000, C- | ML1219-B29: FF, CAB-4480: FS, ML1579-E03: FS, C-56-HC01-CMA01-1000: FS, C-56-HC01-CMA02-1000: FS, C-56-HC01-CMA03-1000: FS, C-56-HC01-CMA04-1000: FS, C-56-HC01-CMA05-1000: FS, C-56-HC01-CMA06-1000: FS, C-56-HC01-CMA07-1000: FS, C-56-HC01-CMA08-1000: FS, C- | 2024-06-14 07:30 | 2024-11-01 17:30
HE-PL-2880 | Completed | P2543-R01-Oct24..1.EN.1.30 | Receive Company Comments - Detailed crossing drawings - 56" | HE-PL-2870 | HE-PL-2870: FS | HE-PL-2890 | HE-PL-2890: FF | 2024-03-21 | 2024-08-13 17:30
HE-PL-2870 | Completed | P2543-R01-Oct24..1.EN.1.30 | Issue ICR - Detailed crossing drawings - 56" | HE-PL-0050, HE-PL-2420, HE-PL-2390 | HE-PL-0050: FS, HE-PL-2420: FS 30, HE-PL-2390: FS | HE-PL-2880 | HE-PL-2880: FS | 2024-02-09 | 2024-03-29
HE-PL-2930 | Completed | P2543-R01-Oct24..1.EN.1.32 | Issue ICR - Crossing Schedule - 56" | HE-PL-2390 | HE-PL-2390: FS | HE-PL-2940 | HE-PL-2940: FS | 2024-02-09 07:30 | 2024-02-16 17:30
HE-PL-2940 | Completed | P2543-R01-Oct24..1.EN.1.32 | Receive Company Comments - Crossing Schedule - 56" | HE-PL-2930 | HE-PL-2930: FS | HE-PL-2950 | HE-PL-2950: FS | 2024-02-17 07:30 | 2024-05-10 17:30
HE-PL-2950 | Completed | P2543-R01-Oct24..1.EN.1.32 | Re-Issue for Approval - Crossing Schedule - 56" | HE-PL-2940 | HE-PL-2940: FS | HE-PL-2960 | HE-PL-2960: FS | 2024-05-13 07:30 | 2024-05-31 17:30
HE-PL-2960 | Completed | P2543-R01-Oct24..1.EN.1.32 | Obtain Company Approval - Crossing Schedule - 56" | HE-PL-2950 | HE-PL-2950: FS | HE-PL-2970 | HE-PL-2970: FS | 2024-06-03 07:30 | 2024-06-14 17:30
HE-PL-2970 | Not Started | P2543-R01-Oct24..1.EN.1.32 | Final Issue for Design/ Construction-Crossing Schedule - 56" | HE-PL-2960, HE-PL-3820 | HE-PL-2960: FS, HE-PL-3820: FS | CAB-4480, ML1579-E03, C-56-HC01-CMA01-1000, C-56-HC01-CMA02-1000, C-56-HC01-CMA03-1000, C-56-HC01-CMA04-1000, C-56-HC01-CMA05-1000, C-56-HC01-CMA06-1000, C-56-HC01-CMA07-1000, C-56-HC01-CMA08-1000, C-56-HC01-CMA09-1000, C-56-HC01-CMA10-1000, C-56-HC01-CMA1 | CAB-4480: FS, ML1579-E03: FS, C-56-HC01-CMA01-1000: FS, C-56-HC01-CMA02-1000: FS, C-56-HC01-CMA03-1000: FS, C-56-HC01-CMA04-1000: FS, C-56-HC01-CMA05-1000: FS, C-56-HC01-CMA06-1000: FS, C-56-HC01-CMA07-1000: FS, C-56-HC01-CMA08-1000: FS, C-56-HC01-CMA09-10 | 2024-10-28 07:30 | 2024-11-01 17:30
HE-PL-3000 | Completed | P2543-R01-Oct24..1.EN.1.36 | Receive Company Comments - Detailed crossing drawings-52" | HE-PL-2990 | HE-PL-2990: FS | HE-PL-3010 | HE-PL-3010: FF | 2024-03-15 | 2024-09-07 17:30
HE-PL-3010 | Completed | P2543-R01-Oct24..1.EN.1.36 | Re-Issue for Approval - Detailed crossing drawings-52" | HE-PL-3000 | HE-PL-3000: FF | HE-PL-3020 | HE-PL-3020: FF 10 | 2024-03-04 | 2024-09-26 07:30
HE-PL-3020 | In Progress | P2543-R01-Oct24..1.EN.1.36 | Obtain Company Approval - Detailed crossing drawings-52" | HE-PL-3010 | HE-PL-3010: FF 10 | HE-PL-3030 | HE-PL-3030: FF 20 | 2024-05-26 07:30 | 2024-11-08 17:30
HE-PL-3030 | In Progress | P2543-R01-Oct24..1.EN.1.36 | Final Issue for Design/ Construction-Detailed crossing drawings-52" | HE-PL-3020 | HE-PL-3020: FF 20 | CAB-4480, ML1679-E13 | CAB-4480: FS, ML1679-E13: FS | 2024-06-14 07:30 | 2024-12-10 17:30
HE-PL-2990 | Completed | P2543-R01-Oct24..1.EN.1.36 | Issue ICR - Detailed crossing drawings-52" | HE-PL-2470, HE-PL-2450 | HE-PL-2470: FS 2, HE-PL-2450: FS | HE-PL-3000, C-PER-1020, C-PER-1040, C-PER-1050, C-PER-1060, C-PER-1080, C-PER-1090, C-PER-1100, C-PER-1110, C-PER-1040, C-PER-1050, C-PER-1090 | HE-PL-3000: FS, C-PER-1020: FS, C-PER-1040: FS, C-PER-1050: FS, C-PER-1060: FS, C-PER-1080: FS, C-PER-1090: FS, C-PER-1100: FS, C-PER-1110: FS, C-PER-1040: FF, C-PER-1050: FF, C-PER-1090: FF | 2024-02-09 | 2024-03-22
HE-PL-3050 | Completed | P2543-R01-Oct24..1.EN.1.38 | Issue ICR - Crossing Schedule-52" | HE-PL-2450 | HE-PL-2450: FS | HE-PL-3060 | HE-PL-3060: FS | 2024-02-23 07:30 | 2024-04-20 17:30
HE-PL-3060 | Completed | P2543-R01-Oct24..1.EN.1.38 | Receive Company Comments - Crossing Schedule-52" | HE-PL-3050 | HE-PL-3050: FS | HE-PL-3070 | HE-PL-3070: FS | 2024-04-22 07:30 | 2024-05-06 17:30
HE-PL-3070 | Completed | P2543-R01-Oct24..1.EN.1.38 | Re-Issue for Approval - Crossing Schedule-52" | HE-PL-3060 | HE-PL-3060: FS | HE-PL-3080 | HE-PL-3080: FS | 2024-05-07 07:30 | 2024-05-27 17:30
HE-PL-3080 | Completed | P2543-R01-Oct24..1.EN.1.38 | Obtain Company Approval - Crossing Schedule-52" | HE-PL-3070 | HE-PL-3070: FS | HE-PL-3090 | HE-PL-3090: FS | 2024-05-28 07:30 | 2024-09-04 17:30
HE-PL-3090 | Not Started | P2543-R01-Oct24..1.EN.1.38 | Final Issue for Design/ Construction-Crossing Schedule-52" | HE-PL-3080 | HE-PL-3080: FS | CAB-4480, ML1679-E13, C-PER-1200, C-PER-1210, C-PER-1220 | CAB-4480: FS, ML1679-E13: FS, C-PER-1200: FF 14, C-PER-1210: FS, C-PER-1220: FS | 2024-10-28 07:30 | 2024-11-01 17:30
HE-PL-3140 | Not Started | P2543-R01-Oct24..1.EN.1.44 | Obtain Company Approval - Detailed crossing drawings-4" | HE-PL-3130 | HE-PL-3130: FS | HE-PL-3150 | HE-PL-3150: FS | 2024-11-25 07:30 | 2024-11-29 17:30
HE-PL-3150 | Not Started | P2543-R01-Oct24..1.EN.1.44 | Final Issue for Design/ Construction-Detailed crossing drawings-4" | HE-PL-3140 | HE-PL-3140: FS | ML1219-B29, CAB-4480, HE-PL-3210 | ML1219-B29: FF, CAB-4480: FS, HE-PL-3210: FS | 2024-12-04 07:30 | 2024-12-10 17:30
HE-PL-3110 | Completed | P2543-R01-Oct24..1.EN.1.44 | Issue ICR - Detailed crossing drawings-4" | HE-PL-3530, HE-PL-2540, HE-PL-2510, HE-PL-3550 | HE-PL-3530: FS, HE-PL-2540: FS, HE-PL-2510: FS, HE-PL-3550: FS | HE-PL-3120, HE-PL-3170 | HE-PL-3120: FS, HE-PL-3170: FS | 2024-02-23 | 2024-03-25
HE-PL-3120 | In Progress | P2543-R01-Oct24..1.EN.1.44 | Receive Company Comments - Detailed crossing drawings-4" | HE-PL-3110 | HE-PL-3110: FS | HE-PL-3130 | HE-PL-3130: FF | 2024-04-19 | 2024-11-08 17:30
HE-PL-3130 | In Progress | P2543-R01-Oct24..1.EN.1.44 | Re-Issue for Approval - Detailed crossing drawings-4" | HE-PL-3120 | HE-PL-3120: FF | HE-PL-3140 | HE-PL-3140: FS | 2024-05-03 | 2024-11-22 17:30
HE-PL-3170 | Completed | P2543-R01-Oct24..1.EN.1.55 | Issue ICR - Crossing Schedule-4" | HE-PL-3530, HE-PL-2510, HE-PL-3110 | HE-PL-3530: FS, HE-PL-2510: FS, HE-PL-3110: FS | HE-PL-3180 | HE-PL-3180: FS | 2024-03-01 07:30 | 2024-05-01 17:30
HE-PL-3180 | Completed | P2543-R01-Oct24..1.EN.1.55 | Receive Company Comments - Crossing Schedule-4" | HE-PL-3170 | HE-PL-3170: FS | HE-PL-3190 | HE-PL-3190: FS | 2024-05-02 07:30 | 2024-05-27 17:30
HE-PL-3190 | In Progress | P2543-R01-Oct24..1.EN.1.55 | Re-Issue for Approval - Crossing Schedule-4" | HE-PL-3180 | HE-PL-3180: FS | HE-PL-3200 | HE-PL-3200: FS | 2024-05-28 07:30 | 2024-11-08 17:30
HE-PL-3200 | Not Started | P2543-R01-Oct24..1.EN.1.55 | Obtain Company Approval - Crossing Schedule-4" | HE-PL-3190 | HE-PL-3190: FS | HE-PL-3210 | HE-PL-3210: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-PL-3210 | Not Started | P2543-R01-Oct24..1.EN.1.55 | Final Issue for Design/ Construction-Crossing Schedule-4" | HE-PL-3200, HE-PL-3150 | HE-PL-3200: FS, HE-PL-3150: FS | CAB-4480 | CAB-4480: FS | 2024-12-11 07:30 | 2024-12-24 17:30
HE-PL-3230 | Completed | P2543-R01-Oct24..1.EN.1.33 | Issue ICR - Pipeline MTO - 56" | HE-PL-1630, HE-PL-2390 | HE-PL-1630: FS, HE-PL-2390: FS | HP-BK-0380, HE-PL-3240, HE-PL-3730 | HP-BK-0380: FS, HE-PL-3240: FS, HE-PL-3730: SS | 2024-02-16 | 2024-03-01
HE-PL-3240 | Completed | P2543-R01-Oct24..1.EN.1.33 | Receive Company Comments - Pipeline MTO - 56" | HE-PL-3230 | HE-PL-3230: FS | HE-PL-3250 | HE-PL-3250: FS | 2024-03-02 | 2024-03-15
HE-PL-3250 | Completed | P2543-R01-Oct24..1.EN.1.33 | Re-Issue for Approval - Pipeline MTO - 56" | HE-PL-3240 | HE-PL-3240: FS | HE-PL-3260 | HE-PL-3260: FS | 2024-03-16 | 2024-03-22
HE-PL-3260 | Completed | P2543-R01-Oct24..1.EN.1.33 | Obtain Company Approval - Pipeline MTO - 56" | HE-PL-3250 | HE-PL-3250: FS | HE-PL-3270, HP-BK-0380 | HE-PL-3270: FS, HP-BK-0380: FS | 2024-03-22 | 2024-03-22
HE-PL-3270 | Completed | P2543-R01-Oct24..1.EN.1.33 | Final Issue for Design/ Construction-Pipeline MTO - 56" and 52" | HE-GS-0010, HE-PL-3260, HE-PL-3370 | HE-GS-0010: FS, HE-PL-3260: FS, HE-PL-3370: FS | HP-BK-0390, CAB-4480 | HP-BK-0390: FS, CAB-4480: FS | 2024-03-20 | 2024-04-05
HE-PL-0030 | Completed | P2543-R01-Oct24..1.EN.1.41 | Re-Issue for Approval - Specification -Pipeline Wall Thickness Calculation Report | HE-PL-0020 | HE-PL-0020: FS | HE-PL-0040 | HE-PL-0040: FS | 2023-08-10 | 2023-08-16
HE-PL-0040 | Completed | P2543-R01-Oct24..1.EN.1.41 | Obtain Company Approval - Pipeline Wall Thickness Calculation Report | HE-PL-0030 | HE-PL-0030: FS | HE-PL-0050 | HE-PL-0050: FS | 2023-08-16 | 2023-08-22
HE-PL-0050 | Completed | P2543-R01-Oct24..1.EN.1.41 | Final Issue for Design/ Construction - Pipeline Wall Thickness Calculation Report | HE-PL-0040 | HE-PL-0040: FS | HE-PL-3860, HE-PL-3850, HE-PL-2870, CAB-4480, HE-PR-1010 | HE-PL-3860: FS 10, HE-PL-3850: FS, HE-PL-2870: FS, CAB-4480: FS, HE-PR-1010: FS | 2023-12-29 | 2024-01-12
HE-PL-0010 | Completed | P2543-R01-Oct24..1.EN.1.41 | Issue ICR - Specification - Pipeline Wall Thickness Calculation Report | HE-DB-80, ML1002 | HE-DB-80: FF, ML1002: FS | HE-PL-3860, HE-PL-0020, HE-PR-0970 | HE-PL-3860: FS, HE-PL-0020: FS, HE-PR-0970: FS | 2023-07-29 | 2023-08-03
HE-PL-0020 | Completed | P2543-R01-Oct24..1.EN.1.41 | Receive Company Comments - Pipeline Wall Thickness Calculation Report | HE-PL-0010 | HE-PL-0010: FS | HE-PL-0030 | HE-PL-0030: FS | 2023-08-03 | 2023-08-10
HE-PL-0110 | Completed | P2543-R01-Oct24..1.EN.1.8 | Final Issue for Design/ Construction-Pipeline Specifications - Addendum to DGS | HE-PL-3850, HE-PL-0100 | HE-PL-3850: FS, HE-PL-0100: FS | CAB-4480, HE-PL-1250, ML1015-B08, HM-ME-0420, ML1017-B18 | CAB-4480: FS, HE-PL-1250: FS, ML1015-B08: FF, HM-ME-0420: FS, ML1017-B18: FS | 2023-12-16 | 2024-01-15
HE-PL-0070 | Completed | P2543-R01-Oct24..1.EN.1.8 | Issue ICR - Pipeline Specifications - Addendum to DGS | ML1002, HE-DB-60 | ML1002: FS, HE-DB-60: SS | HE-PL-0370, HE-CS-0130, HE-PL-1210, HE-PL-0430, HE-PL-0080, HE-PL-0790 | HE-PL-0370: SS 5, HE-CS-0130: FS, HE-PL-1210: FS, HE-PL-0430: FS 5, HE-PL-0080: FS, HE-PL-0790: FS | 2023-10-31 | 2023-11-08
HE-PL-0080 | Completed | P2543-R01-Oct24..1.EN.1.8 | Receive Company Comments - Pipeline Specifications - Addendum to DGS | HE-PL-0070 | HE-PL-0070: FS | HE-PL-0090 | HE-PL-0090: FS | 2023-11-09 | 2023-11-17
HE-PL-0090 | Completed | P2543-R01-Oct24..1.EN.1.8 | Re-Issue for Approval - Pipeline Specifications - Addendum to DGS | HE-PL-0080 | HE-PL-0080: FS | HE-PL-0100 | HE-PL-0100: FS | 2023-11-20 | 2023-11-29
HE-PL-0100 | Completed | P2543-R01-Oct24..1.EN.1.8 | Obtain Company Approval - Pipeline Specifications - Addendum to DGS | HE-PL-0090 | HE-PL-0090: FS | HE-PL-0110 | HE-PL-0110: FS | 2023-12-01 | 2023-12-15
HE-PL-0170 | Completed | P2543-R01-Oct24..1.EN.1.28 | Final Issue for Design/ Construction-Overall Pipeline Route Map - 56" | HE-PL-0160 | HE-PL-0160: FS | HC-GN-0290, ML1139-A06, HS-CN-0060, HE-PL-0830, CAB-4480, C-PER-1000, C-56-01HG-PL-CI-1000, C-56-HC01-PL-CI-2400 | HC-GN-0290: FS, ML1139-A06: FF 50, HS-CN-0060: SS, HE-PL-0830: FF, CAB-4480: FS, C-PER-1000: SS 14, C-56-01HG-PL-CI-1000: SS, C-56-HC01-PL-CI-2400: FS | 2024-06-03 | 2024-09-26 07:30
HE-PL-0130 | Completed | P2543-R01-Oct24..1.EN.1.28 | Issue ICR - Overall Pipeline Route Map - 56" | HE-PL-0190, HE-GS-0010, HE-TS-0010, HE-SS-0020, ML1002, HE-TS-230, HE-GS-140 | HE-PL-0190: SS 5, HE-GS-0010: FS, HE-TS-0010: FS, HE-SS-0020: FS 20, ML1002: SS, HE-TS-230: FS, HE-GS-140: FS | HE-PL-0250, HE-PL-0140, C-GOV-1000 | HE-PL-0250: FS, HE-PL-0140: FS, C-GOV-1000: FF | 2024-03-18 | 2024-05-06
HE-PL-0140 | Completed | P2543-R01-Oct24..1.EN.1.28 | Receive Company Comments - Overall Pipeline Route Map - 56" | HE-PL-0130 | HE-PL-0130: FS | HE-PL-0150 | HE-PL-0150: FS | 2024-05-07 | 2024-05-25
HE-PL-0150 | Completed | P2543-R01-Oct24..1.EN.1.28 | Re-Issue for Approval - Overall Pipeline Route Map - 56" | HE-PL-0140, HE-TS-0010, HE-TS-230 | HE-PL-0140: FS, HE-TS-0010: FS, HE-TS-230: FS | HE-PL-0160 | HE-PL-0160: FS | 2024-05-26 | 2024-05-28
HE-PL-0160 | Completed | P2543-R01-Oct24..1.EN.1.28 | Obtain Company Approval - Overall Pipeline Route Map - 56" | HE-PL-0150 | HE-PL-0150: FS | ML1008-B03, HE-PL-0170 | ML1008-B03: FF, HE-PL-0170: FS | 2024-05-29 | 2024-05-31
HE-PL-0190 | Completed | P2543-R01-Oct24..1.EN.1.34 | Issue ICR - Overall Pipeline Route Map - 52" | HE-GS-0010, HE-TS-0010, HE-SS-0020, ML1002, HE-GS-90, HE-TS-280 | HE-GS-0010: FS, HE-TS-0010: FS, HE-SS-0020: FS 20, ML1002: SS, HE-GS-90: FS, HE-TS-280: FS | HE-PL-0130, HE-PL-0200, HE-PL-0310, C-GOV-1000 | HE-PL-0130: SS 5, HE-PL-0200: FS, HE-PL-0310: FS, C-GOV-1000: FS | 2024-03-30 | 2024-05-05
HE-PL-0200 | Completed | P2543-R01-Oct24..1.EN.1.34 | Receive Company Comments - Overall Pipeline Route Map - 52" | HE-PL-0190 | HE-PL-0190: FS | HE-PL-0210, C-52-HG01-PL-CI-1000 | HE-PL-0210: FS, C-52-HG01-PL-CI-1000: FS 5 | 2024-05-07 | 2024-05-27
HE-PL-0210 | Completed | P2543-R01-Oct24..1.EN.1.34 | Re-Issue for Approval - Overall Pipeline Route Map - 52" | HE-PL-0200, HE-TS-0010, HE-TS-280 | HE-PL-0200: FS, HE-TS-0010: FS, HE-TS-280: FS | HE-PL-0220, HE-PL-2470 | HE-PL-0220: FS, HE-PL-2470: FS | 2024-05-28 | 2024-06-08
HE-PL-0220 | Completed | P2543-R01-Oct24..1.EN.1.34 | Obtain Company Approval - Overall Pipeline Route Map - 52" | HE-PL-0210 | HE-PL-0210: FS | HE-PL-1930, HE-PL-0230 | HE-PL-1930: FS, HE-PL-0230: FS | 2024-06-09 | 2024-06-12
HE-PL-0230 | Completed | P2543-R01-Oct24..1.EN.1.34 | Final Issue for Design/ Construction-Overall Pipeline Route Map - 52" | HE-PL-0220 | HE-PL-0220: FS | CAB-4480, HE-PL-2490, HC-GN-0290, ML1009-B04, HE-PL-0830, ML1149-A07, C-52-0405-PL-CI-1800 | CAB-4480: FS, HE-PL-2490: FF, HC-GN-0290: FS, ML1009-B04: FF, HE-PL-0830: FS, ML1149-A07: FF, C-52-0405-PL-CI-1800: FF | 2024-06-13 | 2024-06-24 17:30
HE-PL-0250 | Completed | P2543-R01-Oct24..1.EN.1.2 | Issue ICR - Overall Pipeline Route Map - 4" | HE-PL-0130, HE-GS-0010, HE-TS-0010, ML1002, HE-GS-190, HE-TS-330 | HE-PL-0130: FS, HE-GS-0010: FS, HE-TS-0010: FS, ML1002: SS, HE-GS-190: FS, HE-TS-330: FS | HE-PL-0260, C-GOV-1000 | HE-PL-0260: FS, C-GOV-1000: FF | 2024-03-19 | 2024-05-08
HE-PL-0260 | Completed | P2543-R01-Oct24..1.EN.1.2 | Receive Company Comments - Overall Pipeline Route Map - 4" | HE-PL-0250 | HE-PL-0250: FS | HE-PL-0270 | HE-PL-0270: FS | 2024-05-09 | 2024-06-02
HE-PL-0270 | Completed | P2543-R01-Oct24..1.EN.1.2 | Re-Issue for Approval - Overall Pipeline Route Map - 4" | HE-PL-0260, HE-TS-0010, HE-TS-330 | HE-PL-0260: FS, HE-TS-0010: FS, HE-TS-330: FS | HE-PL-0280 | HE-PL-0280: FS | 2024-06-03 | 2024-06-05
HE-PL-0280 | Completed | P2543-R01-Oct24..1.EN.1.2 | Obtain Company Approval - Overall Pipeline Route Map - 4" | HE-PL-0270 | HE-PL-0270: FS | HE-PL-0290 | HE-PL-0290: FS | 2024-06-05 | 2024-06-07
HE-PL-0290 | Completed | P2543-R01-Oct24..1.EN.1.2 | Final Issue for Design/ Construction-Overall Pipeline Route Map - 4" | HE-PL-0280 | HE-PL-0280: FS | HE-PL-0830, ML1169-A09, CAB-4480, HC-GN-0290, HE-PL-2490, C-4N-H5HG-PIPEL-1000, C-4N-H5HG-PIPEL-1000, C-4W-SVHG-PIPEL-1000, C-PER-1000 | HE-PL-0830: FS, ML1169-A09: FF 40, CAB-4480: FS, HC-GN-0290: FS, HE-PL-2490: FF, C-4N-H5HG-PIPEL-1000: FF, C-4N-H5HG-PIPEL-1000: FS, C-4W-SVHG-PIPEL-1000: FS, C-PER-1000: SS 14 | 2024-06-08 | 2024-06-24 17:30
HE-PL-0340 | Completed | P2543-R01-Oct24..1.EN.1.13 | Obtain Company Approval - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | HE-PL-0330 | HE-PL-0330: FS | HE-PL-0350 | HE-PL-0350: FS | 2024-05-01 07:30 | 2024-05-17 17:30
HE-PL-0350 | Completed | P2543-R01-Oct24..1.EN.1.13 | Final Issue for Design/ Construction-Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | HE-PL-0340 | HE-PL-0340: FS | CAB-4480, C-56-HC01-PL-ME-2800, C-52-06CR-PL-ME-2800 | CAB-4480: FS, C-56-HC01-PL-ME-2800: FF 21, C-52-06CR-PL-ME-2800: FS | 2024-05-18 07:30 | 2024-05-30 17:30
HE-PL-0310 | Completed | P2543-R01-Oct24..1.EN.1.13 | Issue ICR - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | HE-PR-0110, HE-PL-0190 | HE-PR-0110: FS, HE-PL-0190: FS | HE-PL-0320 | HE-PL-0320: FS | 2024-03-22 | 2024-03-30 17:30
HE-PL-0320 | Completed | P2543-R01-Oct24..1.EN.1.13 | Receive Company Comments - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | HE-PL-0310 | HE-PL-0310: FS | HE-PL-0330 | HE-PL-0330: FS | 2024-04-01 07:30 | 2024-04-15 17:30
HE-PL-0330 | Completed | P2543-R01-Oct24..1.EN.1.13 | Re-Issue for Approval - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | HE-PL-0320 | HE-PL-0320: FS | HE-PL-0340 | HE-PL-0340: FS | 2024-04-16 07:30 | 2024-04-30 17:30
HE-PL-0400 | Completed | P2543-R01-Oct24..1.EN.1.27 | Obtain Company Approval - Pipeline Typical Drawings | HE-PL-0390 | HE-PL-0390: FS | HE-PL-0410 | HE-PL-0410: FS | 2023-12-14 | 2023-12-26
HE-PL-0410 | Completed | P2543-R01-Oct24..1.EN.1.27 | Final Issue for Design/ Construction-Pipeline Typical Drawings | HE-PL-0400, HE-PR-1060 | HE-PL-0400: FS, HE-PR-1060: FF | CAB-4480 | CAB-4480: FS | 2023-12-27 | 2024-10-18 17:30
HE-PL-0370 | Completed | P2543-R01-Oct24..1.EN.1.27 | Issue ICR - Pipeline Typical Drawings | HE-PL-0070 | HE-PL-0070: SS 5 | HE-PL-0380 | HE-PL-0380: FS | 2023-11-15 | 2023-11-23
HE-PL-0380 | Completed | P2543-R01-Oct24..1.EN.1.27 | Receive Company Comments - Pipeline Typical Drawings | HE-PL-0370 | HE-PL-0370: FS | HE-PL-0390 | HE-PL-0390: FS | 2023-11-27 | 2023-12-05
HE-PL-0390 | Completed | P2543-R01-Oct24..1.EN.1.27 | Re-Issue for Approval - Pipeline Typical Drawings | HE-PL-0380 | HE-PL-0380: FS | HE-PL-0400 | HE-PL-0400: FS | 2023-12-06 | 2023-12-13
HE-PL-0430 | Completed | P2543-R01-Oct24..1.EN.1.40 | Issue ICR - Specification - Split Tee | HE-PL-0070, HS-CN-0540 | HE-PL-0070: FS 5, HS-CN-0540: FS | HE-PL-0440, HE-PL-1330, HC-GN-340 | HE-PL-0440: FS, HE-PL-1330: SS 5, HC-GN-340: FS | 2023-11-16 | 2023-11-22
HE-PL-0450 | Completed | P2543-R01-Oct24..1.EN.1.40 | Re-Issue for Approval - Specification - Split Tee | HE-PL-0440 | HE-PL-0440: FS | HE-PL-0460 | HE-PL-0460: FS | 2023-12-29 | 2024-01-07
HE-PL-0460 | Completed | P2543-R01-Oct24..1.EN.1.40 | Obtain Company Approval - Specification - Split Tee | HE-PL-0450 | HE-PL-0450: FS | HE-PL-0470 | HE-PL-0470: FS | 2024-01-08 | 2024-01-16
HE-PL-0470 | Completed | P2543-R01-Oct24..1.EN.1.40 | Final Issue for Design/ Construction-Specification - Split Tee | HE-PL-0460 | HE-PL-0460: FS | HE-PL-1370 | HE-PL-1370: FS | 2024-02-07 | 2024-02-23
HE-PL-0440 | Completed | P2543-R01-Oct24..1.EN.1.40 | Receive Company Comments - Specification - Split Tee | HE-PL-0430 | HE-PL-0430: FS | HE-PL-0450 | HE-PL-0450: FS | 2023-12-01 | 2023-12-28
HE-PL-0610 | Completed | P2543-R01-Oct24..1.EN.1.3 | Issue ICR - Pipeline Upheaval Calculation | HE-DB-0010, HE-PR-0610, HE-TS-0010 | HE-DB-0010: FS, HE-PR-0610: FS, HE-TS-0010: FS | HE-PL-0620, HE-PL-2810, HE-PL-0670 | HE-PL-0620: FS, HE-PL-2810: FS, HE-PL-0670: FS | 2023-11-08 | 2023-11-14
HE-PL-0620 | Completed | P2543-R01-Oct24..1.EN.1.3 | Receive Company Comments - Pipeline Upheaval Calculation | HE-PL-0610 | HE-PL-0610: FS | HE-PL-0630 | HE-PL-0630: FS | 2023-11-07 | 2023-11-17
HE-PL-0630 | Completed | P2543-R01-Oct24..1.EN.1.3 | Re-Issue for Approval - Pipeline Upheaval Calculation | HE-PL-0620 | HE-PL-0620: FS | HE-PL-0640 | HE-PL-0640: FS | 2023-11-18 | 2024-01-10
HE-PL-0640 | Completed | P2543-R01-Oct24..1.EN.1.3 | Obtain Company Approval - Pipeline Upheaval Calculation | HE-PL-0630 | HE-PL-0630: FS | HE-PL-0650 | HE-PL-0650: FS | 2023-11-18 | 2024-01-10
HE-PL-0650 | Completed | P2543-R01-Oct24..1.EN.1.3 | Final Issue for Design/ Construction-Pipeline Upheaval Calculation | HE-PR-0610, HE-PR-0650, HE-PL-0640 | HE-PR-0610: FS, HE-PR-0650: FS, HE-PL-0640: FS | CAB-4480 | CAB-4480: FS | 2024-01-10 | 2024-06-04
HE-PL-0670 | Completed | P2543-R01-Oct24..1.EN.1.4 | Issue ICR - Pipeline Road Crossing Calculation Report | HE-PL-0610, HE-GS-0010, HE-TS-0010 | HE-PL-0610: FS, HE-GS-0010: FS, HE-TS-0010: FS | HE-PL-0680, HE-PL-2810 | HE-PL-0680: FS, HE-PL-2810: FS | 2023-08-25 | 2023-09-02
HE-PL-0680 | Completed | P2543-R01-Oct24..1.EN.1.4 | Receive Company Comments - Pipeline Road Crossing Calculation Report | HE-PL-0670 | HE-PL-0670: FS | HE-PL-0690 | HE-PL-0690: FS | 2023-09-03 | 2023-09-07
HE-PL-0690 | Completed | P2543-R01-Oct24..1.EN.1.4 | Re-Issue for Approval - Pipeline Road Crossing Calculation Report | HE-PL-0680 | HE-PL-0680: FS | HE-PL-0700 | HE-PL-0700: FS | 2023-09-11 | 2023-11-28
HE-PL-0700 | Completed | P2543-R01-Oct24..1.EN.1.4 | Obtain Company Approval - Pipeline Road Crossing Calculation Report | HE-PL-0690 | HE-PL-0690: FS | HE-PL-0710 | HE-PL-0710: FF 10 | 2023-11-29 | 2023-12-15 17:30
HE-PL-0710 | In Progress | P2543-R01-Oct24..1.EN.1.4 | Final Issue for Design/ Construction-Pipeline Road and Railway Crossing Calculation Report | HE-PL-0700 | HE-PL-0700: FF 10 | HE-PL-2850, CAB-4480, HE-PL-0830 | HE-PL-2850: FF 5, CAB-4480: FS, HE-PL-0830: FF | 2024-04-26 07:30 | 2024-11-08 17:30
HE-PL-0820 | Completed | P2543-R01-Oct24..1.EN.1.6 | Obtain Company Approval - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | HE-PL-0810 | HE-PL-0810: FS | HE-PL-0830 | HE-PL-0830: FS | 2024-09-09 07:30 | 2024-09-16 17:30
HE-PL-0830 | In Progress | P2543-R01-Oct24..1.EN.1.6 | Final Issue for Design/ Construction-Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | HE-PL-0290, HE-PL-0820, HE-PL-0170, HE-PL-0230, HE-PL-0710 | HE-PL-0290: FS, HE-PL-0820: FS, HE-PL-0170: FF, HE-PL-0230: FS, HE-PL-0710: FF | ML1219-B29, CAB-4480 | ML1219-B29: FF, CAB-4480: FS | 2024-09-17 07:30 | 2024-11-22 17:30
HE-PL-0790 | Completed | P2543-R01-Oct24..1.EN.1.6 | Issue ICR - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | HE-DB-0010, HE-PL-0070 | HE-DB-0010: FS, HE-PL-0070: FS | HE-PL-0800 | HE-PL-0800: FS | 2024-03-12 | 2024-03-15
HE-PL-0800 | Completed | P2543-R01-Oct24..1.EN.1.6 | Receive Company Comments - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | HE-PL-0790 | HE-PL-0790: FS | HE-PL-0810 | HE-PL-0810: FS | 2024-03-18 | 2024-03-28
HE-PL-0810 | Completed | P2543-R01-Oct24..1.EN.1.6 | Re-Issue for Approval - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | HE-PL-0800 | HE-PL-0800: FS | HE-PL-0820 | HE-PL-0820: FS | 2024-09-02 07:30 | 2024-09-08 17:30
HE-PL-1150 | Completed | P2543-R01-Oct24..1.EN.1.60.9 | Issue ICR - Data Sheet - Line pipes | ML1002 | ML1002: SS | HE-PL-1270, HE-PL-1160, HE-PL-1630 | HE-PL-1270: FS, HE-PL-1160: FS, HE-PL-1630: FS | 2023-07-30 | 2023-08-04
HE-PL-1160 | Completed | P2543-R01-Oct24..1.EN.1.60.9 | Receive Company Comments - Data Sheet - Line pipes | HE-PL-1150 | HE-PL-1150: FS | HE-PL-1170 | HE-PL-1170: FS | 2023-08-05 | 2023-08-15
HE-PL-1170 | Completed | P2543-R01-Oct24..1.EN.1.60.9 | Re-Issue for Approval - Data Sheet - Line pipes | HE-PL-1160 | HE-PL-1160: FS | HE-PL-1650, HE-PL-1180 | HE-PL-1650: FF, HE-PL-1180: FS | 2023-08-16 | 2023-08-21
HE-PL-1180 | Completed | P2543-R01-Oct24..1.EN.1.60.9 | Obtain Company Approval - Data Sheet - Line pipes | HE-PL-1170 | HE-PL-1170: FS | HE-PL-1190 | HE-PL-1190: FS | 2023-08-22 | 2023-09-14
HE-PL-1190 | Completed | P2543-R01-Oct24..1.EN.1.60.9 | Final Issue for Design/ Construction-Data Sheet - Line pipes | HE-PL-1180 | HE-PL-1180: FS | HE-PL-1670 | HE-PL-1670: FF | 2023-09-07 | 2023-11-23
HE-PL-1240 | Completed | P2543-R01-Oct24..1.EN.6.4.51 | Obtain Company Approval - Data Sheet - Mainline Ball Valve | HE-PL-1230 | HE-PL-1230: FS | HE-PL-1250 | HE-PL-1250: FS | 2023-10-27 | 2023-11-03
HE-PL-1250 | Completed | P2543-R01-Oct24..1.EN.6.4.51 | Final Issue for Design/ Construction-Data Sheet - Mainline Ball Valve | HE-IC-3290, HE-PL-1240, HE-PL-0110 | HE-IC-3290: FF, HE-PL-1240: FS, HE-PL-0110: FS | HE-PL-1730, CAB-4480 | HE-PL-1730: FS, CAB-4480: FS | 2024-05-30 07:30 | 2024-06-25 17:30
HE-PL-1220 | Completed | P2543-R01-Oct24..1.EN.6.4.51 | Receive Company Comments - Data Sheet - Mainline Ball Valve | HE-PL-1210 | HE-PL-1210: FS | HE-PL-1230 | HE-PL-1230: FS | 2023-09-29 | 2023-10-11
HE-PL-1210 | Completed | P2543-R01-Oct24..1.EN.6.4.51 | Issue ICR - Data Sheet - Mainline Ball Valve | HE-PL-0070 | HE-PL-0070: FS | HE-PL-1690, HE-PL-1220 | HE-PL-1690: FS, HE-PL-1220: FS | 2023-09-22 | 2023-09-29
HE-PL-1230 | Completed | P2543-R01-Oct24..1.EN.6.4.51 | Re-Issue for Approval - Data Sheet - Mainline Ball Valve | HE-PL-1220 | HE-PL-1220: FS | HE-PL-1240 | HE-PL-1240: FS | 2023-10-12 | 2023-10-27
HE-PL-1270 | Completed | P2543-R01-Oct24..1.EN.1.60.10 | Issue ICR - Data Sheet - Hot Induction Bends | HE-PL-1150 | HE-PL-1150: FS | HE-PL-1750, HE-PL-1390, HE-PL-1280 | HE-PL-1750: FS, HE-PL-1390: FS 15, HE-PL-1280: FS | 2023-07-25 | 2023-08-04
HE-PL-1280 | Completed | P2543-R01-Oct24..1.EN.1.60.10 | Receive Company Comments - Data Sheet - Hot Induction Bends | HE-PL-1270 | HE-PL-1270: FS | HE-PL-1290 | HE-PL-1290: FS | 2023-08-05 | 2023-08-15
HE-PL-1290 | Completed | P2543-R01-Oct24..1.EN.1.60.10 | Re-Issue for Approval - Data Sheet - Hot Induction Bends | HE-PL-1280 | HE-PL-1280: FS | HE-PL-1300, HE-PL-1770 | HE-PL-1300: FS, HE-PL-1770: FS | 2023-08-16 | 2023-08-30
HE-PL-1300 | Completed | P2543-R01-Oct24..1.EN.1.60.10 | Obtain Company Approval - Data Sheet - Hot Induction Bends | HE-PL-1290 | HE-PL-1290: FS | HE-PL-1310 | HE-PL-1310: FS | 2023-08-31 | 2023-09-05
HE-PL-1310 | Completed | P2543-R01-Oct24..1.EN.1.60.10 | Final Issue for Design/ Construction-Data Sheet - Hot Induction Bends | HE-PL-1300 | HE-PL-1300: FS | CAB-4480, HE-PL-1790, HE-PL-1430 | CAB-4480: FS, HE-PL-1790: FS, HE-PL-1430: FS | 2023-09-06 | 2023-11-20
HE-PL-1370 | Completed | P2543-R01-Oct24..1.EN.1.60.16 | Final Issue for Design/ Construction-Data Sheet - Split Tee | HE-PL-1360, HE-PL-0470, HC-GN-380 | HE-PL-1360: FS, HE-PL-0470: FS, HC-GN-380: FS | ML1219-B29, HE-PI-0180, C-COM-750, C-56-G-HT101-ME-1000, C-52-D-HT002-ME-1000, C-36-KM-HT03-ME-1000, C-36-KM-HT04-ME-1000 | ML1219-B29: FF, HE-PI-0180: FS, C-COM-750: FS, C-56-G-HT101-ME-1000: FS, C-52-D-HT002-ME-1000: FS, C-36-KM-HT03-ME-1000: FS, C-36-KM-HT04-ME-1000: FS | 2024-03-16 | 2024-03-22
HE-PL-1330 | Completed | P2543-R01-Oct24..1.EN.1.60.16 | Issue ICR - Data Sheet - Split Tee | HE-PL-0430 | HE-PL-0430: SS 5 | HE-PL-1450, HE-PL-1340, HS-GN-0190, HE-PL-3650 | HE-PL-1450: FF, HE-PL-1340: FS, HS-GN-0190: FS, HE-PL-3650: FS | 2023-11-20 | 2024-01-02
HE-PL-1340 | Completed | P2543-R01-Oct24..1.EN.1.60.16 | Receive Company Comments - Data Sheet - Split Tee | HE-PL-1330 | HE-PL-1330: FS | HE-PL-1350 | HE-PL-1350: FS | 2024-01-02 | 2024-01-15
HE-PL-1350 | Completed | P2543-R01-Oct24..1.EN.1.60.16 | Re-Issue for Approval - Data Sheet - Split Tee | HE-PL-1340 | HE-PL-1340: FS | HE-PL-1360 | HE-PL-1360: FS | 2024-01-16 | 2024-01-27
HE-PL-1360 | Completed | P2543-R01-Oct24..1.EN.1.60.16 | Obtain Company Approval - Data Sheet - Split Tee | HE-PL-1350 | HE-PL-1350: FS | HE-PL-1370 | HE-PL-1370: FS | 2024-01-28 | 2024-02-12
HE-PL-1390 | Completed | P2543-R01-Oct24..1.EN.1.60.11 | Issue ICR - Data Sheet - Isolating joints | HE-PL-1270 | HE-PL-1270: FS 15 | HE-PL-1870, HE-PL-1400 | HE-PL-1870: FS, HE-PL-1400: FS | 2023-09-10 | 2023-09-19
HE-PL-1400 | Completed | P2543-R01-Oct24..1.EN.1.60.11 | Receive Company Comments - Data Sheet - Isolating joints | HE-PL-1390 | HE-PL-1390: FS | HE-PL-1410 | HE-PL-1410: FS | 2023-09-14 | 2023-09-28
HE-PL-1410 | Completed | P2543-R01-Oct24..1.EN.1.60.11 | Re-Issue for Approval - Data Sheet - Isolating joints | HE-PL-1400 | HE-PL-1400: FS | HE-PL-1890, HE-PL-1420 | HE-PL-1890: FS, HE-PL-1420: FS | 2023-10-30 | 2023-11-03
HE-PL-1420 | Completed | P2543-R01-Oct24..1.EN.1.60.11 | Obtain Company Approval - Data Sheet - Isolating joints | HE-PL-1410 | HE-PL-1410: FS | HE-PL-1430 | HE-PL-1430: FS | 2023-11-06 | 2023-11-16
HE-PL-1430 | Completed | P2543-R01-Oct24..1.EN.1.60.11 | Final Issue for Design/ Construction-Data Sheet - Pipeline Isolating Joints | HE-PL-1420, HE-PL-1310 | HE-PL-1420: FS, HE-PL-1310: FS | CAB-4480, HE-PL-1910, HE-PL-1910 | CAB-4480: FS, HE-PL-1910: FS, HE-PL-1910: FF | 2023-11-20 | 2023-11-24
HE-PL-1470 | Completed | P2543-R01-Oct24..1.EN.1.60.12 | Re-Issue for Approval - Data Sheet - Pigging Tees | HE-PL-1460 | HE-PL-1460: FS | HE-PL-1480, HE-PL-1830 | HE-PL-1480: FS, HE-PL-1830: FS | 2023-12-29 | 2024-01-04
HE-PL-1480 | Completed | P2543-R01-Oct24..1.EN.1.60.12 | Obtain Company Approval - Data Sheet - Pigging Tees | HE-PL-1470 | HE-PL-1470: FS | HE-PL-1490 | HE-PL-1490: FS | 2024-01-05 | 2024-01-16
HE-PL-1490 | Completed | P2543-R01-Oct24..1.EN.1.60.12 | Final Issue for Design/ Construction-Data Sheet - Pipeline Pigging Tees | HE-PL-1480 | HE-PL-1480: FS | HE-PL-1850, CAB-4480 | HE-PL-1850: FS, CAB-4480: FS | 2024-01-19 | 2024-01-23
HE-PL-1450 | Completed | P2543-R01-Oct24..1.EN.1.60.12 | Issue ICR - Data Sheet - Pigging Tees | HE-PL-1330 | HE-PL-1330: FF | HE-PL-1810, HE-PL-1460, HE-PL-1510 | HE-PL-1810: FS, HE-PL-1460: FS, HE-PL-1510: SS | 2023-10-02 | 2023-10-14
HE-PL-1460 | Completed | P2543-R01-Oct24..1.EN.1.60.12 | Receive Company Comments - Data Sheet - Pigging Tees | HE-PL-1450 | HE-PL-1450: FS | HE-PL-1470 | HE-PL-1470: FS | 2023-10-15 | 2023-10-25
HE-PL-1510 | Completed | P2543-R01-Oct24..1.EN.1.60.14 | Issue ICR - Data Sheet - Anchor Flange (If Required) | HE-PL-1450, HE-PL-2810 | HE-PL-1450: SS, HE-PL-2810: FS | HE-PL-1520, HE-PL-3460 | HE-PL-1520: FS, HE-PL-3460: FS | 2024-02-05 | 2024-02-10
HE-PL-1520 | Completed | P2543-R01-Oct24..1.EN.1.60.14 | Receive Company Comments - Data Sheet - Anchor Flange (If Required) | HE-PL-1510 | HE-PL-1510: FS | HE-PL-1530 | HE-PL-1530: FS | 2024-02-26 | 2024-03-08
HE-PL-1530 | Completed | P2543-R01-Oct24..1.EN.1.60.14 | Re-Issue for Approval - Data Sheet - Anchor Flange (If Required) | HE-PL-1520, HS-GN-0230 | HE-PL-1520: FS, HS-GN-0230: FS | HE-PL-1540 | HE-PL-1540: FS | 2024-06-03 07:30 | 2024-06-10 17:30
HE-PL-1540 | Completed | P2543-R01-Oct24..1.EN.1.60.14 | Obtain Company Approval - Data Sheet - Anchor Flange (If Required) | HE-PL-1530 | HE-PL-1530: FS | HE-PL-1550 | HE-PL-1550: FS | 2024-06-11 07:30 | 2024-06-24 17:30
HE-PL-1550 | In Progress | P2543-R01-Oct24..1.EN.1.60.14 | Final Issue for Design/ Construction-Data Sheet - Anchor Flange | HE-PL-2850, HE-PL-1540 | HE-PL-2850: FF, HE-PL-1540: FS | ML1219-B29, CAB-4480, HE-PL-3450 | ML1219-B29: FF, CAB-4480: FS, HE-PL-3450: FF 10 | 2024-06-25 07:30 | 2024-11-15 17:30
HE-PL-1630 | Completed | P2543-R01-Oct24..1.EN.1.9.17 | Issue ICR - MR for Line pipes | HE-PL-1150 | HE-PL-1150: FS | HP-ME-1020, HE-PL-1640, HE-PL-3230 | HP-ME-1020: FS, HE-PL-1640: FS, HE-PL-3230: FS | 2023-08-19 | 2023-08-24
HE-PL-1640 | Completed | P2543-R01-Oct24..1.EN.1.9.17 | Receive Company Comments - MR for Line pipes | HE-PL-1630 | HE-PL-1630: FS | HE-PL-1650 | HE-PL-1650: FS | 2023-08-03 | 2023-08-17
HE-PL-1650 | Completed | P2543-R01-Oct24..1.EN.1.9.17 | Re-Issue for Approval - MR for Line pipes | HE-PL-1170, HE-PL-1640 | HE-PL-1170: FF, HE-PL-1640: FS | HE-PL-1660 | HE-PL-1660: FS | 2023-08-17 | 2023-08-24
HE-PL-1660 | Completed | P2543-R01-Oct24..1.EN.1.9.17 | Obtain Company Approval - MR for Line pipes | HE-PL-1650 | HE-PL-1650: FS | HE-PL-1670 | HE-PL-1670: FS | 2023-08-24 | 2023-08-31
HE-PL-1670 | Completed | P2543-R01-Oct24..1.EN.1.9.17 | Final Issue for Design/ Construction-MR for Line pipes | HE-PL-1190, HE-PL-1660 | HE-PL-1190: FF, HE-PL-1660: FS | HP-ME-1040, HM-PL-0010, ML1021-B15 | HP-ME-1040: FF, HM-PL-0010: FS, ML1021-B15: FS | 2023-09-20 | 2023-11-24
HE-PL-1700 | Completed | P2543-R01-Oct24..1.EN.6.11.21 | Receive Company Comments - MR for Mainline Ball Valve | HE-PL-1690 | HE-PL-1690: FS | HE-PL-1710 | HE-PL-1710: FS | 2023-11-29 | 2023-12-01
HE-PL-1710 | Completed | P2543-R01-Oct24..1.EN.6.11.21 | Re-Issue for Approval - MR for Mainline Ball Valve | HE-PL-1700 | HE-PL-1700: FS | HE-PL-1720 | HE-PL-1720: FS | 2024-02-01 | 2024-02-16
HE-PL-1720 | Completed | P2543-R01-Oct24..1.EN.6.11.21 | Obtain Company Approval - MR for Mainline Ball Valve | HE-PL-1710 | HE-PL-1710: FS | HE-PL-1730 | HE-PL-1730: FS | 2024-02-16 | 2024-02-23
HE-PL-1730 | Completed | P2543-R01-Oct24..1.EN.6.11.21 | Final Issue for Design/ Construction-Material Requisition for Manual Ball Valves | HE-PL-1720, HE-PL-1250 | HE-PL-1720: FS, HE-PL-1250: FS | CAB-4480 | CAB-4480: FS | 2024-09-02 07:30 | 2024-09-16 17:30
HE-PL-1690 | Completed | P2543-R01-Oct24..1.EN.6.11.21 | Issue ICR - MR for Mainline Ball Valve | HE-PL-1210 | HE-PL-1210: FS | HP-ME-1070, HE-PL-1700 | HP-ME-1070: FS, HE-PL-1700: FS | 2023-11-17 | 2023-11-28
HE-PL-1790 | Completed | P2543-R01-Oct24..1.EN.1.9.18 | Final Issue for Design/ Construction-MR for Hot Induction Bends | HE-PL-1780, HE-PL-1310 | HE-PL-1780: FS, HE-PL-1310: FS | HP-ME-1190, ML1189-B16, CAB-4480 | HP-ME-1190: FS, ML1189-B16: FF, CAB-4480: FS | 2023-11-17 | 2023-11-23
HE-PL-1750 | Completed | P2543-R01-Oct24..1.EN.1.9.18 | Issue ICR - MR for Hot Induction Bends | HE-PL-1270 | HE-PL-1270: FS | HP-ME-1170, HE-PL-1760 | HP-ME-1170: FS, HE-PL-1760: FS | 2023-07-31 | 2023-08-10
HE-PL-1760 | Completed | P2543-R01-Oct24..1.EN.1.9.18 | Receive Company Comments - MR for Hot Induction Bends | HE-PL-1750 | HE-PL-1750: FS | HE-PL-1770 | HE-PL-1770: FS | 2023-08-08 | 2023-08-18
HE-PL-1770 | Completed | P2543-R01-Oct24..1.EN.1.9.18 | Re-Issue for Approval - MR for Hot Induction Bends | HE-PL-1760, HE-PL-1290 | HE-PL-1760: FS, HE-PL-1290: FS | HE-PL-1780 | HE-PL-1780: FS | 2023-08-19 | 2023-11-08
HE-PL-1780 | Completed | P2543-R01-Oct24..1.EN.1.9.18 | Obtain Company Approval - MR for Hot Induction Bends | HE-PL-1770 | HE-PL-1770: FS | HE-PL-1790 | HE-PL-1790: FS | 2023-11-10 | 2023-11-16
HE-PL-1840 | Completed | P2543-R01-Oct24..1.EN.1.9.19 | Obtain Company Approval - MR for Pigging Tees | HE-PL-1830 | HE-PL-1830: FS | HE-PL-1850 | HE-PL-1850: FS | 2024-04-24 | 2024-04-28
HE-PL-1850 | Completed | P2543-R01-Oct24..1.EN.1.9.19 | Final Issue for Design/ Construction-MR for Pipeline Pigging Tees | HE-PL-1490, HE-PL-1840 | HE-PL-1490: FS, HE-PL-1840: FS | HP-ME-1290, CAB-4480 | HP-ME-1290: FS, CAB-4480: FS | 2024-04-29 | 2024-05-01
HE-PL-1810 | Completed | P2543-R01-Oct24..1.EN.1.9.19 | Issue ICR - MR for Pigging Tees | HE-PL-1450 | HE-PL-1450: FS | HP-ME-1270, HE-PL-1820 | HP-ME-1270: FS, HE-PL-1820: FS | 2024-01-03 | 2024-01-12
HE-PL-1820 | Completed | P2543-R01-Oct24..1.EN.1.9.19 | Receive Company Comments - MR for Pigging Tees | HE-PL-1810 | HE-PL-1810: FS | HE-PL-1830 | HE-PL-1830: FS | 2023-12-29 | 2024-01-09
HE-PL-1830 | Completed | P2543-R01-Oct24..1.EN.1.9.19 | Re-Issue for Approval - MR for Pigging Tees | HE-PL-1470, HE-PL-1820 | HE-PL-1470: FS, HE-PL-1820: FS | HE-PL-1840 | HE-PL-1840: FS | 2024-02-06 | 2024-04-23
HE-PL-1890 | Completed | P2543-R01-Oct24..1.EN.1.9.20 | Re-Issue for Approval - MR for Isolating Joints | HE-PL-1410, HE-PL-1880 | HE-PL-1410: FS, HE-PL-1880: FS | HE-PL-1900 | HE-PL-1900: FS | 2023-10-18 | 2023-11-01
HE-PL-1900 | Completed | P2543-R01-Oct24..1.EN.1.9.20 | Obtain Company Approval - MR for Isolating Joints | HE-PL-1890 | HE-PL-1890: FS | HE-PL-1910 | HE-PL-1910: FS | 2023-11-02 | 2023-11-13
HE-PL-1910 | Completed | P2543-R01-Oct24..1.EN.1.9.20 | Final Issue for Design/ Construction-MR for Isolating Joints | HE-PL-1900, HE-PL-1430, HE-PL-1430 | HE-PL-1900: FS, HE-PL-1430: FS, HE-PL-1430: FF | CAB-4480, HP-ME-1240 | CAB-4480: FS, HP-ME-1240: FS | 2023-11-14 | 2023-11-21
HE-PL-1870 | Completed | P2543-R01-Oct24..1.EN.1.9.20 | Issue ICR - MR for Isolating Joints | HE-PL-1390 | HE-PL-1390: FS | HP-ME-1220, HE-PL-1880 | HP-ME-1220: FS, HE-PL-1880: FS | 2023-09-14 | 2023-09-19
HE-PL-1880 | Completed | P2543-R01-Oct24..1.EN.1.9.20 | Receive Company Comments - MR for Isolating Joints | HE-PL-1870 | HE-PL-1870: FS | HE-PL-1890 | HE-PL-1890: FS | 2023-09-20 | 2023-09-28
HE-PL-1930 | Completed | P2543-R01-Oct24..1.EN.6.11.43 | Issue ICR- Material Requisition for Pig Signaler | HE-PL-2420, HE-PL-0220, HE-PL-2480, HE-IC-1390 | HE-PL-2420: FS, HE-PL-0220: FS, HE-PL-2480: FS, HE-IC-1390: FS | HE-PL-1940, HP-ME-1120 | HE-PL-1940: FS, HP-ME-1120: FS | 2024-02-26 | 2024-03-04
HE-PL-1940 | Completed | P2543-R01-Oct24..1.EN.6.11.43 | Receive Company Comments- Material Requisition for Pig Signaler | HE-PL-1930 | HE-PL-1930: FS | HE-PL-1950 | HE-PL-1950: FS | 2024-03-05 | 2024-03-19
HE-PL-1950 | Completed | P2543-R01-Oct24..1.EN.6.11.43 | Re-Issue for Approval- Material Requisition for Pig Signaler | HE-PL-1940 | HE-PL-1940: FS | HE-PL-1960 | HE-PL-1960: FS | 2024-03-19 | 2024-05-01
HE-PL-1960 | Completed | P2543-R01-Oct24..1.EN.6.11.43 | Obtain Company Approval- Material Requisition for Pig Signaler | HE-PL-1950 | HE-PL-1950: FS | HE-PL-1970 | HE-PL-1970: FS | 2024-05-02 | 2024-05-07
HE-PL-1970 | Completed | P2543-R01-Oct24..1.EN.6.11.43 | Final Issue for Design/ Construction-Material Requisition for Pig Signaler | HE-PL-1960, HE-IC-1430 | HE-PL-1960: FS, HE-IC-1430: FF | CAB-4480, HE-PL-2370 | CAB-4480: FS, HE-PL-2370: FF | 2024-06-10 | 2024-08-07 17:30
HE-PL-2050 | Completed | P2543-R01-Oct24..1.EN.1.10.22 | Issue ICR - TBE for Line pipes | HP-ME-1020 | HP-ME-1020: FS | HE-PL-2060, HP-ME-1030 | HE-PL-2060: FS, HP-ME-1030: SS | 2023-08-13 | 2023-08-18
HE-PL-2070 | Completed | P2543-R01-Oct24..1.EN.1.10.22 | Final Issue for Design/ Construction-TBE for Line pipes | HE-PL-2060 | HE-PL-2060: FS | HP-ME-1040, CAB-4480 | HP-ME-1040: FS, CAB-4480: FS | 2023-08-26 | 2024-02-29
HE-PL-2060 | Completed | P2543-R01-Oct24..1.EN.1.10.22 | Receive Company Comments - TBE for Line pipes | HE-PL-2050 | HE-PL-2050: FS | HE-PL-2070, HP-ME-1030 | HE-PL-2070: FS, HP-ME-1030: FF | 2023-08-19 | 2023-08-22
HE-TL-0290 | Completed | P2543-R01-Oct24..1.EN.10.A21 | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-TL-0110, HE-TL-0280, HE-PR-0110, HE-IC-0290, HE-IC-0230, HE-TL-2470, HE-IC-0190, HE-IC-0250 | HE-TL-0110: FS, HE-TL-0280: FS, HE-PR-0110: FS, HE-IC-0290: FS, HE-IC-0230: FS, HE-TL-2470: FS, HE-IC-0190: SS, HE-IC-0250: SS | HE-TL-0830, HE-TL-0470, ML1033-B22, CAB-4470, C-56-PL-607-TE-1200, C-56-PL-607-TE-1400, C-56-PL-607-TE-1600, C-56-591-01-TE-1000, C-52-598-06-TE-1000, C-52-598-05-TE-1000, C-52-598-04-TE-1000, C-52-598-03-TE-1000, C-52-598-02-TE-1000, C-52-598-01-TE-1000, | HE-TL-0830: FS, HE-TL-0470: FS, ML1033-B22: FS, CAB-4470: FS, C-56-PL-607-TE-1200: FS, C-56-PL-607-TE-1400: FS, C-56-PL-607-TE-1600: FS, C-56-591-01-TE-1000: FS, C-52-598-06-TE-1000: FS, C-52-598-05-TE-1000: FS, C-52-598-04-TE-1000: FS, C-52-598-03-TE-1000 | 2024-01-26 | 2024-02-23
HE-TL-0250 | Completed | P2543-R01-Oct24..1.EN.10.A21 | Issue ICR- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-TL-0070, HE-IC-0190, HE-IC-0250 | HE-TL-0070: FS, HE-IC-0190: SS, HE-IC-0250: SS | HE-TL-0310, HE-TL-0790, HE-TL-0260, HE-TL-0430 | HE-TL-0310: FS, HE-TL-0790: FS, HE-TL-0260: FS, HE-TL-0430: FS | 2023-11-14 | 2023-11-23
HE-TL-0260 | Completed | P2543-R01-Oct24..1.EN.10.A21 | Receive Company Comments- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-TL-0250 | HE-TL-0250: FS | HE-TL-0270 | HE-TL-0270: FS | 2023-11-24 | 2023-12-08
HE-TL-0270 | Completed | P2543-R01-Oct24..1.EN.10.A21 | Re-Issue for Approval- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-TL-0260, HE-TL-0090, HE-PR-0110, HE-IC-0190, HE-IC-0250 | HE-TL-0260: FS, HE-TL-0090: FS, HE-PR-0110: FS, HE-IC-0190: SS, HE-IC-0250: SS | HE-TL-0810, HE-TL-0280 | HE-TL-0810: FS, HE-TL-0280: FS | 2023-12-29 | 2024-01-24
HE-TL-0280 | Completed | P2543-R01-Oct24..1.EN.10.A21 | Obtain Company Approval- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-TL-0270 | HE-TL-0270: FS | HE-TL-0290 | HE-TL-0290: FS | 2024-01-15 | 2024-03-08
HE-TL-0430 | Completed | P2543-R01-Oct24..1.EN.10.A25 | Issue ICR- FOC Block diagram (Telecom) | HE-TL-0310, HE-TL-0370, HE-TL-0250, HE-TL-0070, HE-IC-0190, HE-IC-0250 | HE-TL-0310: FS, HE-TL-0370: FS, HE-TL-0250: FS, HE-TL-0070: FS, HE-IC-0190: SS, HE-IC-0250: SS | HE-TL-0730, HE-TL-0670, HE-TL-0550, HE-TL-0440, HE-TL-0790 | HE-TL-0730: FS, HE-TL-0670: FS, HE-TL-0550: FS 9, HE-TL-0440: FS, HE-TL-0790: FS | 2023-11-08 | 2023-11-16
HE-TL-0440 | Completed | P2543-R01-Oct24..1.EN.10.A25 | Receive Company Comments- FOC Block diagram (Telecom) | HE-TL-0430 | HE-TL-0430: FS | HE-TL-0450 | HE-TL-0450: FS | 2023-11-17 | 2023-11-23
HE-TL-0450 | Completed | P2543-R01-Oct24..1.EN.10.A25 | Re-Issue for Approval- FOC Block diagram (Telecom) | HE-TL-0440, HE-IC-0510, HE-IC-0270, HE-IC-0210, HE-TL-0090, HE-PR-0110, HE-IC-0190, HE-IC-0250 | HE-TL-0440: FS, HE-IC-0510: FS, HE-IC-0270: FS, HE-IC-0210: FS, HE-TL-0090: FS, HE-PR-0110: FS, HE-IC-0190: SS, HE-IC-0250: SS | HE-TL-0460, HE-TL-0510, HE-TL-0690, HE-IC-0930, HE-TL-0570, HE-IC-0990, HE-TL-0750 | HE-TL-0460: FS, HE-TL-0510: FS, HE-TL-0690: FS, HE-IC-0930: FS, HE-TL-0570: FS, HE-IC-0990: FS, HE-TL-0750: FS | 2023-11-24 | 2023-12-30
HE-TL-0460 | Completed | P2543-R01-Oct24..1.EN.10.A25 | Obtain Company Approval- FOC Block diagram (Telecom) | HE-TL-0450 | HE-TL-0450: FS | HE-TL-0470 | HE-TL-0470: FS | 2023-12-31 | 2024-01-15
HE-TL-0470 | Completed | P2543-R01-Oct24..1.EN.10.A25 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | HE-TL-0350, HE-TL-0460, HE-TL-0410, HE-TL-0290, HE-TL-0110, HE-PR-0110, HE-IC-0290, HE-IC-0230, HE-TL-2470, HE-IC-0190, HE-IC-0250, HE-TL-980 | HE-TL-0350: FS, HE-TL-0460: FS, HE-TL-0410: FS, HE-TL-0290: FS, HE-TL-0110: FS, HE-PR-0110: FS, HE-IC-0290: FS, HE-IC-0230: FS, HE-TL-2470: FS, HE-IC-0190: SS, HE-IC-0250: SS, HE-TL-980: FS | ML1030, HE-TL-0590, HE-TL-0770, CAB-4470, HE-TL-0710, HE-TL-0530, HE-TL-0830, ML1033-B22, C-56-PL-607-TE-1200, C-56-PL-607-TE-1400, C-56-PL-607-TE-1600, C-56-EB2-TE-1000, C-56-HC01-PL-TE-8200, C-56-HC01-PL-TE-8400, C-56-PR-838-TE-1000, C-56-591-01-TE-1000, | ML1030: FS, HE-TL-0590: FS, HE-TL-0770: FS, CAB-4470: FS, HE-TL-0710: FS, HE-TL-0530: FS, HE-TL-0830: FS, ML1033-B22: FS, C-56-PL-607-TE-1200: FS, C-56-PL-607-TE-1400: FS, C-56-PL-607-TE-1600: FS, C-56-EB2-TE-1000: FS, C-56-HC01-PL-TE-8200: FS, C-56-HC01-P | 2024-01-16 | 2024-03-26
HE-TL-0570 | Completed | P2543-R01-Oct24..1.EN.10.8 | Re-Issue for Approval- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0560, HE-TL-0450, HE-TL-0210, HE-TL-0090, HE-IC-0190, HE-IC-0250, HE-IC-620 | HE-TL-0560: FS, HE-TL-0450: FS, HE-TL-0210: FS, HE-TL-0090: FS, HE-IC-0190: SS, HE-IC-0250: SS, HE-IC-620: SS | HE-TL-0580 | HE-TL-0580: FS | 2024-05-24 | 2024-05-31
HE-TL-0580 | Completed | P2543-R01-Oct24..1.EN.10.8 | Obtain Company Approval- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0570 | HE-TL-0570: FS | HE-TL-0590 | HE-TL-0590: FS | 2024-06-03 | 2024-06-07
HE-TL-0590 | In Progress | P2543-R01-Oct24..1.EN.10.8 | Final Issue for Design/ Construction-Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc. | HE-TL-0470, HE-TL-0580, HE-TL-0110, HE-IC-0290, HE-IC-0230, HE-TL-2470, HE-IC-0190, HE-IC-0250, HE-TL-0530 | HE-TL-0470: FS, HE-TL-0580: FS, HE-TL-0110: FS, HE-IC-0290: FS, HE-IC-0230: FS, HE-TL-2470: FS, HE-IC-0190: SS, HE-IC-0250: SS, HE-TL-0530: FF | ML1219-B29, HM-ME-1330, CAB-4470, HE-TL-0650 | ML1219-B29: FF, HM-ME-1330: FF, CAB-4470: FS, HE-TL-0650: FS | 2024-10-24 07:30 | 2024-11-01 17:30
HE-TL-0550 | Completed | P2543-R01-Oct24..1.EN.10.8 | Issue ICR- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0070, HE-TL-0430, HE-TL-0190, HE-TL-0490, HE-IC-0190, HE-IC-0250, HE-IC-620 | HE-TL-0070: FS, HE-TL-0430: FS 9, HE-TL-0190: FS, HE-TL-0490: FS, HE-IC-0190: SS, HE-IC-0250: SS, HE-IC-620: SS | HP-ME-0660, HP-ME-0610, HE-TL-0560, HP-BK-0060, HE-TL-0790 | HP-ME-0660: FS, HP-ME-0610: FS, HE-TL-0560: FS, HP-BK-0060: FS, HE-TL-0790: FS | 2023-11-14 | 2023-11-21
HE-TL-0560 | Completed | P2543-R01-Oct24..1.EN.10.8 | Receive Company Comments- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0550 | HE-TL-0550: FS | HE-TL-0570 | HE-TL-0570: FS | 2023-11-22 | 2023-11-27
HE-TL-0620 | Completed | P2543-R01-Oct24..1.EN.10.11 | Receive Company Comments-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0610 | HE-TL-0610: FS | HE-TL-0630 | HE-TL-0630: FS | 2024-03-15 | 2024-03-27
HE-TL-0630 | Completed | P2543-R01-Oct24..1.EN.10.11 | Re-Issue for Approval-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0620 | HE-TL-0620: FS | HE-TL-0640, HE-TL-910 | HE-TL-0640: FS, HE-TL-910: FS | 2024-05-29 | 2024-06-07
HE-TL-0640 | Completed | P2543-R01-Oct24..1.EN.10.11 | Obtain Company Approval-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0630 | HE-TL-0630: FS | HE-TL-0650 | HE-TL-0650: FS | 2024-06-10 | 2024-06-26 17:30
HE-TL-0650 | Not Started | P2543-R01-Oct24..1.EN.10.11 | Final Issue for Design/ Construction-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0640, HE-TL-1140, HE-TL-0590 | HE-TL-0640: FS, HE-TL-1140: FS, HE-TL-0590: FS | CAB-4470 | CAB-4470: FS | 2024-11-25 07:30 | 2024-11-29 17:30
HE-TL-0610 | Completed | P2543-R01-Oct24..1.EN.10.11 | Issue ICR-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HP-ME-0660, HP-ME-0610, HP-BK-0060, HE-TL-980 | HP-ME-0660: FS, HP-ME-0610: FS, HP-BK-0060: FS, HE-TL-980: FS | HE-TL-0620, HP-ME-0620, HP-ME-0670 | HE-TL-0620: FS, HP-ME-0620: SS, HP-ME-0670: SS | 2024-03-10 | 2024-03-14
HE-TL-0670 | Completed | P2543-R01-Oct24..1.EN.10.A29 | Issue ICR-Telecom Location and Cable Routing layout | HE-TL-0430, ML2069-B09 | HE-TL-0430: FS, ML2069-B09: FS | HE-TL-0680, HE-TL-0730 | HE-TL-0680: FS, HE-TL-0730: FS | 2024-03-31 | 2024-04-12
HE-TL-0690 | Completed | P2543-R01-Oct24..1.EN.10.A29 | Re-Issue for Approval-Telecom Location and Cable Routing layout | HE-TL-0450, HE-TL-0680 | HE-TL-0450: FS, HE-TL-0680: FS | HE-TL-0810, HE-TL-0870, HE-TL-0700, HE-TL-910 | HE-TL-0810: SS, HE-TL-0870: SS, HE-TL-0700: FS, HE-TL-910: SS | 2024-04-30 | 2024-05-01
HE-TL-0710 | Completed | P2543-R01-Oct24..1.EN.10.A29 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | HE-TL-0470, HE-TL-0700 | HE-TL-0470: FS, HE-TL-0700: FS | ML1030, ML1032-B21, HE-TL-0830, CAB-4470, HE-TL-0890, HE-TL-930, HE-CO-200, C-56-PL-607-TE-1200, C-56-PL-607-TE-1400, C-56-PL-607-TE-1600, C-56-EB2-TE-1000, C-56-HC01-PL-TE-8200, C-56-HC01-PL-TE-8400, C-56-PR-838-TE-1000, C-56-591-01-TE-1000, C-52-HG01-PL- | ML1030: FS, ML1032-B21: FS, HE-TL-0830: SS, CAB-4470: FS, HE-TL-0890: FS, HE-TL-930: FS, HE-CO-200: FS, C-56-PL-607-TE-1200: FS, C-56-PL-607-TE-1400: FS, C-56-PL-607-TE-1600: FS, C-56-EB2-TE-1000: FS, C-56-HC01-PL-TE-8200: FS, C-56-HC01-PL-TE-8400: FS, C-5 | 2024-05-10 | 2024-06-23 17:30
HE-TL-0700 | Completed | P2543-R01-Oct24..1.EN.10.A29 | Obtain Company Approval-Telecom Location and Cable Routing layout | HE-TL-0690 | HE-TL-0690: FS | HE-TL-0710 | HE-TL-0710: FS | 2024-05-01 | 2024-05-10
HE-TL-0680 | Completed | P2543-R01-Oct24..1.EN.10.A29 | Receive Company Comments-Telecom Location and Cable Routing layout | HE-TL-0670 | HE-TL-0670: FS | HE-TL-0690 | HE-TL-0690: FS | 2024-04-12 | 2024-04-26
HE-TL-0790 | Completed | P2543-R01-Oct24..1.EN.10.A32 | Issue ICR- Telecom Cable Schedule | HE-TL-0370, HE-TL-0250, HE-TL-0310, HE-TL-0070, HE-TL-0430, HE-IC-0190, HE-IC-0250, HE-TL-0550, HE-TL-0730 | HE-TL-0370: FS, HE-TL-0250: FS, HE-TL-0310: FS, HE-TL-0070: FS, HE-TL-0430: FS, HE-IC-0190: SS, HE-IC-0250: SS, HE-TL-0550: FS, HE-TL-0730: FS | HE-TL-0800, HE-TL-890 | HE-TL-0800: FS, HE-TL-890: FS | 2024-06-07 07:30 | 2024-06-14 17:30
HE-TL-0800 | Completed | P2543-R01-Oct24..1.EN.10.A32 | Receive Company Comments- Telecom Cable Schedule | HE-TL-0790 | HE-TL-0790: FS | HE-TL-0810 | HE-TL-0810: FS | 2024-06-14 07:30 | 2024-06-18
HE-TL-0810 | Completed | P2543-R01-Oct24..1.EN.10.A32 | Re-Issue for Approval- Telecom Cable Schedule | HE-TL-0270, HE-TL-0690, HE-TL-0330, HE-TL-0750, HE-TL-0800, HE-TL-0390 | HE-TL-0270: FS, HE-TL-0690: SS, HE-TL-0330: FS, HE-TL-0750: SS, HE-TL-0800: FS, HE-TL-0390: FS | HE-TL-0870, HE-TL-0820, HE-TL-910 | HE-TL-0870: SS, HE-TL-0820: FS, HE-TL-910: SS | 2024-06-18 07:30 | 2024-06-21 17:30
HE-TL-0820 | Completed | P2543-R01-Oct24..1.EN.10.A32 | Obtain Company Approval- Telecom Cable Schedule | HE-TL-0810 | HE-TL-0810: FS | HE-TL-0830 | HE-TL-0830: FS | 2024-06-22 07:30 | 2024-06-28 17:30
HE-TL-0830 | Completed | P2543-R01-Oct24..1.EN.10.A32 | Final Issue for Design/ Construction-Telecom cable schedule | HE-TL-0110, HE-TL-0710, HE-TL-0350, HE-TL-0290, HE-TL-0410, HE-TL-0770, HE-TL-0470, HE-TL-0820, HE-IC-0290, HE-IC-0230, HE-TL-2470, HE-IC-0190, HE-IC-0250 | HE-TL-0110: FS, HE-TL-0710: SS, HE-TL-0350: FS, HE-TL-0290: FS, HE-TL-0410: FS, HE-TL-0770: SS, HE-TL-0470: FS, HE-TL-0820: FS, HE-IC-0290: FS, HE-IC-0230: FS, HE-TL-2470: FS, HE-IC-0190: SS, HE-IC-0250: SS | ML1030, HE-TL-0890, ML1032-B21, CAB-4470, HE-TL-930, HE-TL-0870, C-56-PL-607-TE-1200, C-56-PL-607-TE-1400, C-56-PL-607-TE-1600, C-56-EB2-TE-1000, C-56-HC01-PL-TE-8200, C-56-HC01-PL-TE-8400, C-56-PR-838-TE-1000, C-56-591-01-TE-1000, C-52-HG01-PL-TE-8200, C- | ML1030: FS, HE-TL-0890: FS, ML1032-B21: FS, CAB-4470: FS, HE-TL-930: FS, HE-TL-0870: FS, C-56-PL-607-TE-1200: FS, C-56-PL-607-TE-1400: FS, C-56-PL-607-TE-1600: FS, C-56-EB2-TE-1000: FS, C-56-HC01-PL-TE-8200: FS, C-56-HC01-PL-TE-8400: FS, C-56-PR-838-TE-100 | 2024-06-29 07:30 | 2024-07-12 17:30
HE-TL-0850 | Completed | P2543-R01-Oct24..1.EN.10.2 | Telecom 1st MTO | ML2059-B05 | ML2059-B05: FS | HP-BK-0500, HE-TL-0870 | HP-BK-0500: FS, HE-TL-0870: FS | 2024-10-01 07:30 | 2024-10-14 17:30
HE-TL-0870 | Not Started | P2543-R01-Oct24..1.EN.10.2 | Telecom 2nd MTO | HE-TL-0810, HE-TL-0750, HE-TL-0690, HE-TL-0850, ML2069-B09, HE-TL-0830 | HE-TL-0810: SS, HE-TL-0750: SS, HE-TL-0690: SS, HE-TL-0850: FS, ML2069-B09: FS, HE-TL-0830: FS | HE-TL-0890 | HE-TL-0890: FS 30 | 2024-10-28 07:30 | 2024-11-01 17:30
HE-TL-0890 | Not Started | P2543-R01-Oct24..1.EN.10.2 | Telecom 3rd MTO | HE-TL-0830, HE-TL-0770, HE-TL-0710, HE-TL-0870, ML2079-B13, HE-TL-920 | HE-TL-0830: FS, HE-TL-0770: FS, HE-TL-0710: FS, HE-TL-0870: FS 30, ML2079-B13: FS, HE-TL-920: FS | ML1219-B29, CAB-4470, HP-BK-0510 | ML1219-B29: FF, CAB-4470: FS, HP-BK-0510: FF | 2024-12-18 07:30 | 2024-12-24 17:30
HE-TL-0350 | Completed | P2543-R01-Oct24..1.EN.10.A211 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | HE-TL-0110, HE-TL-0340, HE-PR-0110, HE-IC-0290, HE-IC-0230, HE-TL-2470, HE-IC-0190, HE-IC-0250 | HE-TL-0110: FS, HE-TL-0340: FS, HE-PR-0110: FS, HE-IC-0290: FS, HE-IC-0230: FS, HE-TL-2470: FS, HE-IC-0190: SS, HE-IC-0250: SS | HE-TL-0470, HE-TL-0830, CAB-4470, ML1033-B22, C-56-PL-607-TE-1200, C-56-PL-607-TE-1400, C-56-PL-607-TE-1600, C-56-591-01-TE-1000, C-52-598-06-TE-1000, C-52-598-05-TE-1000, C-52-598-04-TE-1000, C-52-598-03-TE-1000, C-52-598-02-TE-1000, C-52-598-01-TE-1000, | HE-TL-0470: FS, HE-TL-0830: FS, CAB-4470: FS, ML1033-B22: FS, C-56-PL-607-TE-1200: FS, C-56-PL-607-TE-1400: FS, C-56-PL-607-TE-1600: FS, C-56-591-01-TE-1000: FS, C-52-598-06-TE-1000: FS, C-52-598-05-TE-1000: FS, C-52-598-04-TE-1000: FS, C-52-598-03-TE-1000 | 2024-01-26 | 2024-03-10
HE-TL-0310 | Completed | P2543-R01-Oct24..1.EN.10.A211 | Issue ICR- Overall Telecom Block Diagram | HE-TL-0250, HE-TL-0070, HE-IC-0190, HE-IC-0250 | HE-TL-0250: FS, HE-TL-0070: FS, HE-IC-0190: SS, HE-IC-0250: SS | HE-TL-0430, HE-TL-0320, HE-TL-0790, HE-TL-940, HE-TL-1000, HE-TL-1200 | HE-TL-0430: FS, HE-TL-0320: FS, HE-TL-0790: FS, HE-TL-940: FF, HE-TL-1000: SS 3, HE-TL-1200: FS | 2023-11-14 | 2023-11-23
HE-TL-0320 | Completed | P2543-R01-Oct24..1.EN.10.A211 | Receive Company Comments- Overall Telecom Block Diagram | HE-TL-0310 | HE-TL-0310: FS | HE-TL-0330 | HE-TL-0330: FS | 2023-11-24 | 2023-12-20
HE-TL-0330 | Completed | P2543-R01-Oct24..1.EN.10.A211 | Re-Issue for Approval- Overall Telecom Block Diagram | HE-TL-0320, HE-TL-0090, HE-PR-0110, HE-IC-0190, HE-IC-0250 | HE-TL-0320: FS, HE-TL-0090: FS, HE-PR-0110: FS, HE-IC-0190: SS, HE-IC-0250: SS | HE-TL-0340, HE-TL-0810 | HE-TL-0340: FS, HE-TL-0810: FS | 2023-12-29 | 2024-03-01
HE-TL-0340 | Completed | P2543-R01-Oct24..1.EN.10.A211 | Obtain Company Approval- Overall Telecom Block Diagram | HE-TL-0330 | HE-TL-0330: FS | HE-TL-0350 | HE-TL-0350: FS | 2024-01-15 | 2024-03-08
HE-TL-0410 | Completed | P2543-R01-Oct24..1.EN.10.A2111 | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | HE-TL-0110, HE-TL-0400, HE-PR-0110, HE-IC-0290, HE-IC-0230, HE-TL-2470, HE-IC-0190, HE-IC-0250 | HE-TL-0110: FS, HE-TL-0400: FS, HE-PR-0110: FS, HE-IC-0290: FS, HE-IC-0230: FS, HE-TL-2470: FS, HE-IC-0190: SS, HE-IC-0250: SS | CAB-4470, HE-TL-0470, ML1033-B22, HE-TL-0830, C-56-PL-607-TE-1200, C-56-PL-607-TE-1400, C-56-PL-607-TE-1600, C-56-591-01-TE-1000, C-52-598-06-TE-1000, C-52-598-05-TE-1000, C-52-598-04-TE-1000, C-52-598-03-TE-1000, C-52-598-02-TE-1000, C-52-598-01-TE-1000, | CAB-4470: FS, HE-TL-0470: FS, ML1033-B22: FS, HE-TL-0830: FS, C-56-PL-607-TE-1200: FS, C-56-PL-607-TE-1400: FS, C-56-PL-607-TE-1600: FS, C-56-591-01-TE-1000: FS, C-52-598-06-TE-1000: FS, C-52-598-05-TE-1000: FS, C-52-598-04-TE-1000: FS, C-52-598-03-TE-1000 | 2024-03-10 | 2024-03-25
HE-TL-0370 | Completed | P2543-R01-Oct24..1.EN.10.A2111 | Issue ICR- Telecom Tie-in Block Diagram | HE-TL-0070, HE-IC-0190, HE-IC-0250 | HE-TL-0070: FS, HE-IC-0190: SS, HE-IC-0250: SS | HE-TL-0790, HE-TL-0430, HE-TL-0380 | HE-TL-0790: FS, HE-TL-0430: FS, HE-TL-0380: FS | 2023-10-20 | 2023-12-27
HE-TL-0380 | Completed | P2543-R01-Oct24..1.EN.10.A2111 | Receive Company Comments- Telecom Tie-in Block Diagram | HE-TL-0370 | HE-TL-0370: FS | HE-TL-0390 | HE-TL-0390: FS | 2024-01-16 | 2024-01-25
HE-TL-0390 | Completed | P2543-R01-Oct24..1.EN.10.A2111 | Re-Issue for Approval- Telecom Tie-in Block Diagram | HE-TL-0090, HE-TL-0380, HE-IC-0510, HE-PR-0110, HE-IC-0190, HE-IC-0250 | HE-TL-0090: FS, HE-TL-0380: FS, HE-IC-0510: FS, HE-PR-0110: FS, HE-IC-0190: SS, HE-IC-0250: SS | HE-TL-0400, HE-TL-0810 | HE-TL-0400: FS, HE-TL-0810: FS | 2024-01-26 | 2024-02-26
HE-TL-0400 | Completed | P2543-R01-Oct24..1.EN.10.A2111 | Obtain Company Approval- Telecom Tie-in Block Diagram | HE-TL-0390 | HE-TL-0390: FS | HE-TL-0410 | HE-TL-0410: FS | 2024-02-26 | 2024-03-08
HE-TL-0190 | Completed | P2543-R01-Oct24..1.EN.10.A281 | Issue ICR- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-620 | HE-IC-620: FS | HE-TL-0490, HE-TL-0200, HE-TL-0550 | HE-TL-0490: FS 20, HE-TL-0200: FS, HE-TL-0550: FS | 2023-09-21 | 2023-09-28
HE-TL-0200 | Completed | P2543-R01-Oct24..1.EN.10.A281 | Receive Company Comments- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0190 | HE-TL-0190: FS | HE-TL-0210 | HE-TL-0210: FS | 2023-09-29 | 2023-10-31
HE-TL-0210 | Completed | P2543-R01-Oct24..1.EN.10.A281 | Re-Issue for Approval- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0200 | HE-TL-0200: FS | HE-TL-0220, HE-TL-0510, HE-TL-0570 | HE-TL-0220: FS, HE-TL-0510: FS, HE-TL-0570: FS | 2023-12-05 | 2024-01-19
HE-TL-0220 | Completed | P2543-R01-Oct24..1.EN.10.A281 | Obtain Company Approval- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0210 | HE-TL-0210: FS | HE-TL-0230 | HE-TL-0230: FS | 2024-01-10 | 2024-01-19
HE-TL-0230 | Completed | P2543-R01-Oct24..1.EN.10.A281 | Final Issue for Design/ Construction-Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0220, HE-IC-0230, HE-IC-0290, HE-IC-620, HE-TL-2470, HE-TL-0110 | HE-TL-0220: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-620: SS, HE-TL-2470: FS, HE-TL-0110: FF | CAB-4470, ML1033-B22, HE-TL-0530, HE-TL-1040, HE-TL-980 | CAB-4470: FS, ML1033-B22: FS, HE-TL-0530: FS, HE-TL-1040: SS, HE-TL-980: FS | 2024-01-05 | 2024-02-12
HE-TL-0510 | Completed | P2543-R01-Oct24..1.EN.10.1 | Re-Issue for Approval- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0500, HE-TL-0450, HE-TL-0090, HE-TL-0210, HE-IC-0190, HE-IC-0250, HE-IC-620 | HE-TL-0500: FS, HE-TL-0450: FS, HE-TL-0090: FS, HE-TL-0210: FS, HE-IC-0190: SS, HE-IC-0250: SS, HE-IC-620: SS | HE-TL-0520 | HE-TL-0520: FS | 2023-12-29 | 2024-01-08
HE-TL-0520 | Completed | P2543-R01-Oct24..1.EN.10.1 | Obtain Company Approval- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0510 | HE-TL-0510: FS | HE-TL-0530 | HE-TL-0530: FS | 2024-01-08 | 2024-01-17
HE-TL-0530 | In Progress | P2543-R01-Oct24..1.EN.10.1 | Final Issue for Design/ Construction-Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0520, HE-TL-0470, HE-TL-0110, HE-TL-0230, HE-IC-0290, HE-IC-0230, HE-TL-2470, HE-IC-0190, HE-IC-0250 | HE-TL-0520: FS, HE-TL-0470: FS, HE-TL-0110: FS, HE-TL-0230: FS, HE-IC-0290: FS, HE-IC-0230: FS, HE-TL-2470: FS, HE-IC-0190: SS, HE-IC-0250: SS | ML1219-B29, HM-ME-1330, CAB-4470, HE-TL-0590 | ML1219-B29: FF, HM-ME-1330: FF, CAB-4470: FS, HE-TL-0590: FF | 2024-10-23 07:30 | 2024-11-01 17:30
HE-TL-0490 | Completed | P2543-R01-Oct24..1.EN.10.1 | Issue ICR- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0190 | HE-TL-0190: FS 20 | HP-ME-0660, HP-ME-0610, HE-TL-0500, HE-TL-0550 | HP-ME-0660: FS, HP-ME-0610: FS, HE-TL-0500: FS, HE-TL-0550: FS | 2023-11-13 | 2023-11-21
HE-TL-0500 | Completed | P2543-R01-Oct24..1.EN.10.1 | Receive Company Comments- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0490 | HE-TL-0490: FS | HE-TL-0510 | HE-TL-0510: FS | 2023-11-22 | 2023-12-20
HE-TL-0730 | Completed | P2543-R01-Oct24..1.EN.10.A291 | Issue ICR-Telecom Equipment Layout | HE-TL-0430, HE-TL-0670 | HE-TL-0430: FS, HE-TL-0670: FS | HE-TL-0740, HE-TL-0790 | HE-TL-0740: FS, HE-TL-0790: FS | 2024-06-10 | 2024-06-17
HE-TL-0750 | Completed | P2543-R01-Oct24..1.EN.10.A291 | Re-Issue for Approval-Telecom Equipment Layout | HE-TL-0740, HE-TL-0450 | HE-TL-0740: FS, HE-TL-0450: FS | HE-TL-0870, HE-TL-0760, HE-TL-0810, HE-TL-910 | HE-TL-0870: SS, HE-TL-0760: FS, HE-TL-0810: SS, HE-TL-910: SS | 2024-06-20 | 2024-06-21
HE-TL-0770 | Completed | P2543-R01-Oct24..1.EN.10.A291 | Final Issue for Design/ Construction-Telecom Equipment Layout | HE-TL-0470, HE-TL-0760 | HE-TL-0470: FS, HE-TL-0760: FS | ML1030, HE-TL-0890, CAB-4470, ML1032-B21, HE-TL-0830, HE-TL-930, HE-CO-200, C-56-PL-607-TE-1200, C-56-PL-607-TE-1400, C-56-PL-607-TE-1600, C-56-EB2-TE-1000, C-56-HC01-PL-TE-8200, C-56-HC01-PL-TE-8400, C-56-PR-838-TE-1000, C-56-591-01-TE-1000, C-52-HG01-PL- | ML1030: FS, HE-TL-0890: FS, CAB-4470: FS, ML1032-B21: FS, HE-TL-0830: SS, HE-TL-930: FS, HE-CO-200: FS, C-56-PL-607-TE-1200: FS, C-56-PL-607-TE-1400: FS, C-56-PL-607-TE-1600: FS, C-56-EB2-TE-1000: FS, C-56-HC01-PL-TE-8200: FS, C-56-HC01-PL-TE-8400: FS, C-5 | 2024-06-24 07:30 | 2024-07-01 17:30
HE-TL-0760 | Completed | P2543-R01-Oct24..1.EN.10.A291 | Obtain Company Approval-Telecom Equipment Layout | HE-TL-0750 | HE-TL-0750: FS | HE-TL-0770 | HE-TL-0770: FS | 2024-06-21 | 2024-06-24
HE-TL-0740 | Completed | P2543-R01-Oct24..1.EN.10.A291 | Receive Company Comments-Telecom Equipment Layout | HE-TL-0730 | HE-TL-0730: FS | HE-TL-0750 | HE-TL-0750: FS | 2024-06-18 | 2024-06-20
HE-TL-0080 | Completed | P2543-R01-Oct24..1.EN.10.A191 | Receive Company Comments - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | HE-TL-0070 | HE-TL-0070: FS | HE-TL-0090 | HE-TL-0090: FS | 2024-02-26 | 2024-02-26
HE-TL-0090 | Completed | P2543-R01-Oct24..1.EN.10.A191 | Re-Issue for Approval - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | HE-TL-0080 | HE-TL-0080: FS | HE-TL-0390, HE-TL-0510, HE-TL-0100, HE-TL-0330, HE-TL-0270, HE-TL-0450, HE-EL-5440, HE-TL-0570 | HE-TL-0390: FS, HE-TL-0510: FS, HE-TL-0100: FS, HE-TL-0330: FS, HE-TL-0270: FS, HE-TL-0450: FS, HE-EL-5440: FS, HE-TL-0570: FS | 2024-02-26 | 2024-02-26
HE-TL-0100 | Completed | P2543-R01-Oct24..1.EN.10.A191 | Obtain Company Approval - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | HE-TL-0090 | HE-TL-0090: FS | HE-TL-0110 | HE-TL-0110: FS | 2024-02-26 | 2024-02-26
HE-TL-0110 | Completed | P2543-R01-Oct24..1.EN.10.A191 | Final Issue for Design/ Construction-Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | HE-IC-0230, HE-IC-0290, HE-TL-0100 | HE-IC-0230: FS, HE-IC-0290: FS, HE-TL-0100: FS | HE-TL-0830, ML1033-B22, CAB-4470, HE-TL-0410, HE-TL-0350, HE-TL-0290, HE-TL-0470, HE-TL-0590, HE-TL-0530, HE-TL-0230 | HE-TL-0830: FS, ML1033-B22: FS, CAB-4470: FS, HE-TL-0410: FS, HE-TL-0350: FS, HE-TL-0290: FS, HE-TL-0470: FS, HE-TL-0590: FS, HE-TL-0530: FS, HE-TL-0230: FF | 2024-03-10 | 2024-03-10
HE-TL-0070 | Completed | P2543-R01-Oct24..1.EN.10.A191 | Issue ICR - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | HE-IC-0250, HE-IC-0190 | HE-IC-0250: SS, HE-IC-0190: SS | HE-TL-0550, HE-TL-0250, HE-TL-0080, HE-TL-0370, HE-TL-0790, HE-TL-0310, HE-TL-0430, HE-TL-1250 | HE-TL-0550: FS, HE-TL-0250: FS, HE-TL-0080: FS, HE-TL-0370: FS, HE-TL-0790: FS, HE-TL-0310: FS, HE-TL-0430: FS, HE-TL-1250: FS | 2024-02-26 | 2024-02-26
HE-HS-0730 | Completed | P2543-R01-Oct24..1.EN.4.21 | Issue ICR- HAZOP Close Out Report | HE-HS-0670 | HE-HS-0670: FS | HE-HS-0740, HE-HS-1050 | HE-HS-0740: FS, HE-HS-1050: FS | 2024-03-04 | 2024-03-17
HE-HS-0740 | Completed | P2543-R01-Oct24..1.EN.4.21 | Receive Company Comments- HAZOP Close Out Report | HE-HS-0730 | HE-HS-0730: FS | HE-HS-0750 | HE-HS-0750: FS | 2024-03-18 | 2024-03-25
HE-HS-0750 | Completed | P2543-R01-Oct24..1.EN.4.21 | Re-Issue for Approval- HAZOP Close Out Report | HE-HS-0740 | HE-HS-0740: FS | HE-HS-0760 | HE-HS-0760: FS | 2024-03-26 | 2024-04-07
HE-HS-0760 | Completed | P2543-R01-Oct24..1.EN.4.21 | Obtain Company Approval- HAZOP Close Out Report | HE-HS-0750 | HE-HS-0750: FS | HE-HS-0770 | HE-HS-0770: FS | 2024-04-12 | 2024-04-25
HE-HS-0770 | Completed | P2543-R01-Oct24..1.EN.4.21 | Final Issue for Design/ Construction-HAZOP close out report | HE-HS-0760, HE-HS-0830, HE-HS-0710 | HE-HS-0760: FS, HE-HS-0830: FF, HE-HS-0710: FF | C-COM-800, CAB-4410 | C-COM-800: FS, CAB-4410: FS | 2024-04-26 07:30 | 2024-05-01 17:30
HE-HS-0790 | Completed | P2543-R01-Oct24..1.EN.4.11 | Issue ICR-QRA Report | HE-HS-0490 | HE-HS-0490: FS | HE-HS-0800, HE-HS-0850, HE-HS-1030, HE-HS-1300 | HE-HS-0800: FS, HE-HS-0850: FS, HE-HS-1030: FS, HE-HS-1300: FS | 2023-12-04 | 2023-12-11
HE-HS-0800 | Completed | P2543-R01-Oct24..1.EN.4.11 | Receive Company Comments-QRA Report | HE-HS-0790 | HE-HS-0790: FS | HE-HS-0810 | HE-HS-0810: FS | 2023-12-12 | 2023-12-25
HE-HS-0810 | Completed | P2543-R01-Oct24..1.EN.4.11 | Re-Issue for Approval-QRA Report | HE-HS-0800 | HE-HS-0800: FS | HE-HS-0820, ML1013-B07 | HE-HS-0820: FS, ML1013-B07: FF | 2023-12-26 | 2024-01-25
HE-HS-0820 | Completed | P2543-R01-Oct24..1.EN.4.11 | Obtain Company Approval-QRA Report | HE-HS-0810 | HE-HS-0810: FS | HE-HS-0830 | HE-HS-0830: FS | 2024-02-26 | 2024-03-19
HE-HS-0830 | Completed | P2543-R01-Oct24..1.EN.4.11 | Final Issue for Design/ Construction-QRA Report | HE-HS-0820 | HE-HS-0820: FS | CAB-4410, ML1016-B12, HE-HS-1030, C-COM-800, HE-HS-0770 | CAB-4410: FS, ML1016-B12: FS, HE-HS-1030: FS, C-COM-800: FS, HE-HS-0770: FF | 2024-06-06 | 2024-06-13
HE-HS-0850 | Completed | P2543-R01-Oct24..1.EN.4.12 | Issue ICR-PHSER Report | HE-HS-0790, HE-HS-0670 | HE-HS-0790: FS, HE-HS-0670: FS | HE-HS-1030, HE-HS-0910, HE-HS-0860 | HE-HS-1030: FS, HE-HS-0910: FS, HE-HS-0860: FS | 2024-01-15 | 2024-01-18
HE-HS-0860 | Completed | P2543-R01-Oct24..1.EN.4.12 | Receive Company Comments-PHSER Report | HE-HS-0850 | HE-HS-0850: FS | HE-HS-0870 | HE-HS-0870: FS | 2024-01-19 | 2024-02-08
HE-HS-0870 | Completed | P2543-R01-Oct24..1.EN.4.12 | Re-Issue for Approval-PHSER Report | HE-HS-0860 | HE-HS-0860: FS | ML1013-B07, HE-HS-0880 | ML1013-B07: FF, HE-HS-0880: FS | 2024-02-09 | 2024-02-16
HE-HS-0880 | Completed | P2543-R01-Oct24..1.EN.4.12 | Obtain Company Approval-PHSER Report | HE-HS-0870 | HE-HS-0870: FS | HE-HS-0890 | HE-HS-0890: FS | 2024-02-16 | 2024-03-02
HE-HS-0890 | In Progress | P2543-R01-Oct24..1.EN.4.12 | Final Issue for Design/ Construction-PHSER Report | HE-HS-0880, HE-HS-1340 | HE-HS-0880: FS, HE-HS-1340: FF | HE-HS-0910, CAB-4410, C-COM-800 | HE-HS-0910: FF, CAB-4410: FS, C-COM-800: FS | 2024-03-04 | 2024-11-08 17:30
HE-HS-0910 | In Progress | P2543-R01-Oct24..1.EN.4.17 | Issue ICR- PHSER Close Out Report | HE-HS-0850, HE-HS-0890 | HE-HS-0850: FS, HE-HS-0890: FF | HE-HS-0920 | HE-HS-0920: FS | 2024-10-11 07:30 | 2024-11-08 17:30
HE-HS-0920 | Not Started | P2543-R01-Oct24..1.EN.4.17 | Receive Company Comments- PHSER Close Out Report | HE-HS-0910 | HE-HS-0910: FS | HE-HS-0930 | HE-HS-0930: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-HS-0930 | Not Started | P2543-R01-Oct24..1.EN.4.17 | Re-Issue for Approval- PHSER Close Out Report | HE-HS-0920 | HE-HS-0920: FS | HE-HS-0940 | HE-HS-0940: FS | 2024-11-25 07:30 | 2024-11-29 17:30
HE-HS-0940 | Not Started | P2543-R01-Oct24..1.EN.4.17 | Obtain Company Approval- PHSER Close Out Report | HE-HS-0930 | HE-HS-0930: FS | HE-HS-0950 | HE-HS-0950: FS | 2024-12-04 07:30 | 2024-12-17 17:30
HE-HS-0950 | Not Started | P2543-R01-Oct24..1.EN.4.17 | Final Issue for Design/ Construction-PHSER Close Out Report | HE-HS-0940 | HE-HS-0940: FS | CAB-4410 | CAB-4410: FS | 2024-12-18 07:30 | 2024-12-24 17:30
HE-HS-0970 | Completed | P2543-R01-Oct24..1.EN.4.8 | Issue ICR-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-PR-0130, HS-GN-0110, HE-HS-0190, HE-WS-0020, HE-WS-0030, HE-HS-0490 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-PR-0130: FS, HS-GN-0110: FS, HE-HS-0190: FS, HE-WS-0020: FS, HE-WS-0030: FS, HE-HS-0490: FS | HE-HS-0980 | HE-HS-0980: FS | 2024-07-29 07:30 | 2024-08-09 17:30
HE-HS-0980 | Completed | P2543-R01-Oct24..1.EN.4.8 | Receive Company Comments-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-HS-0970 | HE-HS-0970: FS | HE-HS-0990 | HE-HS-0990: FS | 2024-08-12 07:30 | 2024-08-23 17:30
HE-HS-0990 | Completed | P2543-R01-Oct24..1.EN.4.8 | Re-Issue for Approval-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-HS-0980 | HE-HS-0980: FS | HE-HS-1000 | HE-HS-1000: FS | 2024-08-26 07:30 | 2024-08-30 17:30
HE-HS-1000 | Completed | P2543-R01-Oct24..1.EN.4.8 | Obtain Company Approval-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-HS-0990 | HE-HS-0990: FS | HE-HS-1010 | HE-HS-1010: FS | 2024-09-02 07:30 | 2024-09-17 17:30
HE-HS-1010 | Completed | P2543-R01-Oct24..1.EN.4.8 | Final Issue for Design/ Construction-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-HS-1000 | HE-HS-1000: FS | CAB-4410, C-COM-790 | CAB-4410: FS, C-COM-790: FS | 2024-09-17 07:30 | 2024-09-27
HE-HS-1030 | Completed | P2543-R01-Oct24..1.EN.4.9 | Issue ICR-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-0850, HE-HS-0830, HE-HS-0670, HE-HS-0790, HE-HS-0550 | HE-HS-0850: FS, HE-HS-0830: FS, HE-HS-0670: FS, HE-HS-0790: FS, HE-HS-0550: FS | HE-HS-1040 | HE-HS-1040: FS | 2023-10-20 | 2023-11-08
HE-HS-1040 | Completed | P2543-R01-Oct24..1.EN.4.9 | Receive Company Comments-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-1030 | HE-HS-1030: FS | HE-HS-1050 | HE-HS-1050: FS | 2023-11-09 | 2023-11-17
HE-HS-1050 | Completed | P2543-R01-Oct24..1.EN.4.9 | Re-Issue for Approval-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-1040, HE-HS-0730, HE-HS-0610 | HE-HS-1040: FS, HE-HS-0730: FS, HE-HS-0610: FS | HE-HS-1060 | HE-HS-1060: FS | 2023-11-17 | 2023-11-24
HE-HS-1070 | In Progress | P2543-R01-Oct24..1.EN.4.9 | Final Issue for Design/ Construction-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-0590, HE-HS-1060 | HE-HS-0590: FS, HE-HS-1060: FS | ML1219-B29, CAB-4410 | ML1219-B29: FF, CAB-4410: FS | 2024-05-24 | 2024-11-01 17:30
HE-HS-1060 | Completed | P2543-R01-Oct24..1.EN.4.9 | Obtain Company Approval-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-1050, HE-HS-0460 | HE-HS-1050: FS, HE-HS-0460: FS | HE-HS-1070 | HE-HS-1070: FS | 2024-05-15 | 2024-05-23
HE-HS-1110 | Completed | P2543-R01-Oct24..1.EN.4.20 | Re-Issue for Approval-Material Requisition for Fire Fighting & Safety Eqpt | HE-HS-1100 | HE-HS-1100: FS | HE-HS-1120 | HE-HS-1120: FS | 2024-05-17 | 2024-05-24
HE-HS-1120 | Completed | P2543-R01-Oct24..1.EN.4.20 | Obtain Company Approval-Material Requisition for Fire Fighting & Safety Eqpt | HE-HS-1110 | HE-HS-1110: FS | HE-HS-1130 | HE-HS-1130: FS | 2024-05-24 | 2024-05-31
HE-HS-1130 | Completed | P2543-R01-Oct24..1.EN.4.20 | Final Issue for Design/ Construction-Material Requisition for fire fighting and safety equipment | HE-HS-1120 | HE-HS-1120: FS | HP-ME-0980, HE-HS-1190 | HP-ME-0980: FS, HE-HS-1190: FS | 2024-05-31 | 2024-06-14
HE-HS-1092 | Completed | P2543-R01-Oct24..1.EN.4.20 | Issue ICR-Material Requisition for Fire Fighting & Safety Eqpt | HE-HS-0430 | HE-HS-0430: FS | HP-ME-0960, HE-HS-1100, HE-HS-1150 | HP-ME-0960: FS, HE-HS-1100: FS, HE-HS-1150: FS | 2024-05-03 | 2024-05-10
HE-HS-1100 | Completed | P2543-R01-Oct24..1.EN.4.20 | Receive Company Comments-Material Requisition for Fire Fighting & Safety Eqpt | HE-HS-1092 | HE-HS-1092: FS | HE-HS-1110 | HE-HS-1110: FS | 2024-05-13 | 2024-05-17
HE-HS-1170 | Completed | P2543-R01-Oct24..1.EN.4.15 | Re-Issue for Approval-TBE for Fire Fighting & Safety Eqpt | HE-HS-1160 | HE-HS-1160: FS | HE-HS-1180 | HE-HS-1180: FS | 2024-05-22 | 2024-09-02 17:30
HE-HS-1180 | Completed | P2543-R01-Oct24..1.EN.4.15 | Obtain Company Approval-TBE for Fire Fighting & Safety Eqpt | HE-HS-1170 | HE-HS-1170: FS | HP-ME-0920, HE-HS-1190, HP-ME-0970 | HP-ME-0920: FF, HE-HS-1190: FS, HP-ME-0970: FF | 2024-09-03 07:30 | 2024-09-13 17:30
HE-HS-1190 | Completed | P2543-R01-Oct24..1.EN.4.15 | Final Issue for Design/ Construction-TBE for fire fighting and safety equipment | HE-HS-1180, HE-HS-1130 | HE-HS-1180: FS, HE-HS-1130: FS | HM-ME-1850 | HM-ME-1850: FS | 2024-09-13 07:30 | 2024-09-23 17:30
HE-HS-1150 | Completed | P2543-R01-Oct24..1.EN.4.15 | Issue ICR-TBE for Fire Fighting & Safety Eqpt | HP-ME-0960, HE-HS-1092 | HP-ME-0960: FS, HE-HS-1092: FS | HE-HS-1160, HP-ME-0920, HP-ME-0970, HE-HS-1220 | HE-HS-1160: FS, HP-ME-0920: SS, HP-ME-0970: SS, HE-HS-1220: FS | 2024-05-07 | 2024-05-14
HE-HS-1160 | Completed | P2543-R01-Oct24..1.EN.4.15 | Receive Company Comments-TBE for Fire Fighting & Safety Eqpt | HE-HS-1150 | HE-HS-1150: FS | HE-HS-1170 | HE-HS-1170: FS | 2024-05-15 | 2024-05-20
HE-HS-0040 | Completed | P2543-R01-Oct24..1.EN.4.4 | Obtain Company Approval-HSE Plan | HE-HS-0030 | HE-HS-0030: FS | HE-HS-0050 | HE-HS-0050: FS | 2023-10-10 | 2023-10-25
HE-HS-0050 | Completed | P2543-R01-Oct24..1.EN.4.4 | Final Issue for Design/ Construction-Project HSE Plan | HE-HS-0040 | HE-HS-0040: FS | CAB-4410, ML1001-A01, HE-HS-0110 | CAB-4410: FS, ML1001-A01: FS, HE-HS-0110: FF | 2023-11-14 | 2023-11-22
HE-HS-0010 | Completed | P2543-R01-Oct24..1.EN.4.4 | Issue ICR-HSE Plan | HE-DB-0010 | HE-DB-0010: SS | HE-HS-0020, HE-HS-0070, HS-GN-0070, HE-WS-0050 | HE-HS-0020: FS, HE-HS-0070: SS, HS-GN-0070: SS, HE-WS-0050: FS | 2023-08-20 | 2023-08-29
HE-HS-0020 | Completed | P2543-R01-Oct24..1.EN.4.4 | Receive Company Comments-HSE Plan | HE-HS-0010 | HE-HS-0010: FS | HE-HS-0030 | HE-HS-0030: FS | 2023-09-01 | 2023-09-17
HE-HS-0030 | Completed | P2543-R01-Oct24..1.EN.4.4 | Re-Issue for Approval-HSE Plan | HE-HS-0020 | HE-HS-0020: FS | HE-HS-0040 | HE-HS-0040: FS | 2023-09-18 | 2023-10-09
HE-HS-0100 | Completed | P2543-R01-Oct24..1.EN.4.3 | Obtain Company Approval-HSE Philosophy | HE-HS-0090 | HE-HS-0090: FS | HE-HS-0110 | HE-HS-0110: FS | 2023-10-10 | 2023-10-27
HE-HS-0110 | Completed | P2543-R01-Oct24..1.EN.4.3 | Final Issue for Design/ Construction-Project HSE Philosophy | HE-HS-0100, HE-HS-0050 | HE-HS-0100: FS, HE-HS-0050: FF | HE-HS-0170, C-COM-800, CAB-4410, HE-HS-0350 | HE-HS-0170: FS, C-COM-800: FS, CAB-4410: FS, HE-HS-0350: FS | 2023-11-13 | 2023-11-17
HE-HS-0080 | Completed | P2543-R01-Oct24..1.EN.4.3 | Receive Company Comments-HSE Philosophy | HE-HS-0070 | HE-HS-0070: FS | HE-HS-0090, HE-WS-0020 | HE-HS-0090: FS, HE-WS-0020: FS | 2023-09-19 | 2023-09-28
HE-HS-0090 | Completed | P2543-R01-Oct24..1.EN.4.3 | Re-Issue for Approval-HSE Philosophy | HE-HS-0080 | HE-HS-0080: FS | HE-HS-0100 | HE-HS-0100: FS | 2023-09-29 | 2023-10-09
HE-HS-0070 | Completed | P2543-R01-Oct24..1.EN.4.3 | Issue ICR-HSE Philosophy | HE-HS-0010 | HE-HS-0010: SS | HE-HS-0130, HS-GN-0070, HE-HS-0080, HE-WS-0050, HE-HS-0310 | HE-HS-0130: FS, HS-GN-0070: SS, HE-HS-0080: FS, HE-WS-0050: FS, HE-HS-0310: FS | 2023-08-24 | 2023-09-18
HE-HS-0130 | Completed | P2543-R01-Oct24..1.EN.4.1 | Issue ICR - HAZID / ENVID / OHID Procedure | HE-HS-0070, HS-GN-0110 | HE-HS-0070: FS, HS-GN-0110: FS | HE-HS-0140, HE-HS-0550, HE-WS-0020 | HE-HS-0140: FS, HE-HS-0550: FS, HE-WS-0020: FS | 2023-10-19 | 2023-10-31
HE-HS-0140 | Completed | P2543-R01-Oct24..1.EN.4.1 | Receive Company Comments - HAZID / ENVID / OHID Procedure | HE-HS-0130 | HE-HS-0130: FS | HE-HS-0150, HE-WS-0020 | HE-HS-0150: FS, HE-WS-0020: FS | 2023-11-01 | 2023-11-07
HE-HS-0150 | Completed | P2543-R01-Oct24..1.EN.4.1 | Re-Issue for Approval - HAZID / ENVID / OHID Procedure | HE-HS-0140 | HE-HS-0140: FS | HE-HS-0160 | HE-HS-0160: FS | 2023-11-08 | 2023-11-21
HE-HS-0160 | Completed | P2543-R01-Oct24..1.EN.4.1 | Obtain Company Approval - HAZID / ENVID / OHID Procedure | HE-HS-0150 | HE-HS-0150: FS | HE-HS-0170 | HE-HS-0170: FS | 2023-11-22 | 2023-11-28
HE-HS-0170 | Completed | P2543-R01-Oct24..1.EN.4.1 | Final Issue for Design/ Construction-HAZID / ENVID / OHID Procedure | HE-HS-0110, HE-HS-0160 | HE-HS-0110: FS, HE-HS-0160: FS | CAB-4410, HE-HS-0230, HE-HS-0590 | CAB-4410: FS, HE-HS-0230: FS, HE-HS-0590: FS | 2023-11-29 | 2023-12-12
HE-HS-0200 | Completed | P2543-R01-Oct24..1.EN.4.2 | Receive Company Comments-HAZOP Procedure | HE-HS-0190 | HE-HS-0190: FS | HE-HS-0210 | HE-HS-0210: FS | 2023-11-01 | 2023-11-07
HE-HS-0230 | Completed | P2543-R01-Oct24..1.EN.4.2 | Final Issue for Design/ Construction-HAZOP Procedure | HE-HS-0220, HE-HS-0170 | HE-HS-0220: FS, HE-HS-0170: FS | CAB-4410, HE-HS-0710, HE-WS-0210 | CAB-4410: FS, HE-HS-0710: FS, HE-WS-0210: FS | 2023-12-29 | 2024-01-19
HE-HS-0190 | Completed | P2543-R01-Oct24..1.EN.4.2 | Issue ICR-HAZOP Procedure | HS-GN-0110 | HS-GN-0110: FS | HE-HS-0970, HE-PI-0150, HE-WS-0050, HE-HS-0490, HE-PI-0130, C-COM-790, CAB-5290, HE-HS-0200, HE-HS-0670 | HE-HS-0970: FS, HE-PI-0150: FS, HE-WS-0050: FS, HE-HS-0490: FS, HE-PI-0130: FS, C-COM-790: FS, CAB-5290: FS, HE-HS-0200: FS, HE-HS-0670: FS | 2023-10-19 | 2023-10-31
HE-HS-0210 | Completed | P2543-R01-Oct24..1.EN.4.2 | Re-Issue for Approval-HAZOP Procedure | HE-HS-0200 | HE-HS-0200: FS | HE-HS-0220 | HE-HS-0220: FS | 2023-11-08 | 2023-11-21
HE-HS-0220 | Completed | P2543-R01-Oct24..1.EN.4.2 | Obtain Company Approval-HAZOP Procedure | HE-HS-0210 | HE-HS-0210: FS | HE-HS-0230 | HE-HS-0230: FS | 2023-11-22 | 2023-12-27
HE-HS-0250 | Completed | P2543-R01-Oct24..1.EN.4.5 | Issue ICR-F&G Layout | HE-PI-0350, HE-PI-0560, HE-PI-0420, HE-PI-0490 | HE-PI-0350: FS, HE-PI-0560: FS, HE-PI-0420: FS, HE-PI-0490: FS | HE-HS-0310, HE-IC-1510, HE-HS-0260, HE-IC-0490 | HE-HS-0310: FS, HE-IC-1510: FS, HE-HS-0260: FS, HE-IC-0490: FS 15 | 2023-12-20 | 2024-01-03
HE-HS-0260 | Completed | P2543-R01-Oct24..1.EN.4.5 | Receive Company Comments-F&G Layout | HE-HS-0250 | HE-HS-0250: FS | HE-HS-0270 | HE-HS-0270: FS | 2024-01-04 | 2024-01-09
HE-HS-0280 | Completed | P2543-R01-Oct24..1.EN.4.5 | Obtain Company Approval-F&G Layout | HE-HS-0270 | HE-HS-0270: FS | HE-HS-0290, HE-HS-0330 | HE-HS-0290: FS, HE-HS-0330: FS | 2024-06-14 07:30 | 2024-06-25 17:30
HE-HS-0290 | In Progress | P2543-R01-Oct24..1.EN.4.5 | Final Issue for Design/ Construction-F&G layout | HE-HS-0280, HE-PI-0370, HE-PI-0440, HE-PI-0510, HE-PI-0580 | HE-HS-0280: FS, HE-PI-0370: FF, HE-PI-0440: FF, HE-PI-0510: FF, HE-PI-0580: FF | HE-HS-0350, CAB-4410, HE-HS-0340, C-52-598-06-CI-1400, C-52-598-06-CI-1410, C-52-598-06-CI-1420, C-52-598-06-CI-1430 | HE-HS-0350: FS, CAB-4410: FS, HE-HS-0340: FS, C-52-598-06-CI-1400: FS, C-52-598-06-CI-1410: FS, C-52-598-06-CI-1420: FS, C-52-598-06-CI-1430: FS | 2024-09-30 07:30 | 2024-11-01 17:30
HE-HS-0270 | Completed | P2543-R01-Oct24..1.EN.4.5 | Re-Issue for Approval-F&G Layout | HE-HS-0260 | HE-HS-0260: FS | HE-IC-2750, HE-HS-0280 | HE-IC-2750: FS, HE-HS-0280: FS | 2024-04-19 | 2024-04-25
HE-HS-0320 | Completed | P2543-R01-Oct24..1.EN.4.6 | Receive Company Comments-F&G Cause and Effect | HE-HS-0310 | HE-HS-0310: FS | HE-HS-0330 | HE-HS-0330: FS | 2024-06-13 07:30 | 2024-09-02 17:30
HE-HS-0330 | In Progress | P2543-R01-Oct24..1.EN.4.6 | Re-Issue for Approval-F&G Cause and Effect | HE-HS-0280, HE-HS-0320 | HE-HS-0280: FS, HE-HS-0320: FS | HE-HS-0340 | HE-HS-0340: FS | 2024-10-21 07:30 | 2024-11-08 17:30
HE-HS-0340 | Not Started | P2543-R01-Oct24..1.EN.4.6 | Obtain Company Approval-F&G Cause and Effect | HE-HS-0330, HE-HS-0290 | HE-HS-0330: FS, HE-HS-0290: FS | HE-HS-0350 | HE-HS-0350: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-HS-0310 | Completed | P2543-R01-Oct24..1.EN.4.6 | Issue ICR-F&G Cause and Effect | HE-HS-0250, HE-HS-0070 | HE-HS-0250: FS, HE-HS-0070: FS | HE-HS-0370, HE-HS-0320 | HE-HS-0370: SS, HE-HS-0320: FS | 2024-01-22 | 2024-06-12 17:30
HE-HS-0350 | Not Started | P2543-R01-Oct24..1.EN.4.6 | Final Issue for Design/ Construction-F&G Cause and effect | HE-HS-0340, HE-HS-0290, HE-IC-0590, HE-HS-0110 | HE-HS-0340: FS, HE-HS-0290: FS, HE-IC-0590: FS, HE-HS-0110: FS | ML1030, ML1859-E31, ML1749-E20, CAB-4410, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C-56-PR-838-EI-2030, C-56-591-01-EI-1600, C-52-598-06-EI-1210, C-52 | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, CAB-4410: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-EI-1400: FS, C-56-PR-838-EI-1810: FS, C-56-PR-838-EI-2020: FS, C-56-PR-838-EI-2030: FS | 2024-11-25 07:30 | 2024-11-29 17:30
HE-HS-0380 | Completed | P2543-R01-Oct24..1.EN.4.7 | Receive Company Comments-Fire Fighting & Safety Eqpt. Layout | HE-HS-0370 | HE-HS-0370: FS | HE-HS-0390 | HE-HS-0390: FS | 2023-12-16 | 2023-12-25
HE-HS-0390 | Completed | P2543-R01-Oct24..1.EN.4.7 | Re-Issue for Approval-Fire Fighting & Safety Eqpt. Layout | HE-HS-0380 | HE-HS-0380: FS | HE-HS-0400 | HE-HS-0400: FS | 2024-01-29 | 2024-02-20
HE-HS-0400 | Completed | P2543-R01-Oct24..1.EN.4.7 | Obtain Company Approval-Fire Fighting & Safety Eqpt. Layout | HE-HS-0390 | HE-HS-0390: FS | HE-HS-0410, HE-HS-0460 | HE-HS-0410: FS, HE-HS-0460: FS | 2024-02-07 | 2024-02-20
HE-HS-0410 | Completed | P2543-R01-Oct24..1.EN.4.7 | Final Issue for Design/ Construction-Fire fighting & Safety equipment layout | HE-HS-0400 | HE-HS-0400: FS | CAB-4410, HE-HS-0470, C-56-591-01-CI-1400, C-56-591-01-CI-1410, C-52-598-06-CI-1400, C-52-598-06-CI-1410, C-52-598-06-CI-1420, C-52-598-06-CI-1430 | CAB-4410: FS, HE-HS-0470: FS, C-56-591-01-CI-1400: FS, C-56-591-01-CI-1410: FS, C-52-598-06-CI-1400: FS, C-52-598-06-CI-1410: FS, C-52-598-06-CI-1420: FS, C-52-598-06-CI-1430: FS | 2024-02-07 | 2024-03-01
HE-HS-0370 | Completed | P2543-R01-Oct24..1.EN.4.7 | Issue ICR- Fire Fighting & Safety Eqpt. Layout | HE-HS-0310 | HE-HS-0310: SS | HE-HS-0380, HE-HS-0430, HP-ME-0910 | HE-HS-0380: FS, HE-HS-0430: FS, HP-ME-0910: FS | 2023-12-06 | 2023-12-15
HE-HS-0430 | Completed | P2543-R01-Oct24..1.EN.4.16 | Issue ICR-Data Sheets for Fire Fighting & Safety Eqpt | HE-HS-0370 | HE-HS-0370: FS | HE-HS-0440, HE-HS-1092 | HE-HS-0440: FS, HE-HS-1092: FS | 2024-02-26 | 2024-03-08
HE-HS-0440 | Completed | P2543-R01-Oct24..1.EN.4.16 | Receive Company Comments-Data Sheets for Fire Fighting & Safety Eqpt | HE-HS-0430 | HE-HS-0430: FS | HE-HS-0450 | HE-HS-0450: FS | 2024-03-10 | 2024-03-25
HE-HS-0450 | Completed | P2543-R01-Oct24..1.EN.4.16 | Re-Issue for Approval-Data Sheets for Fire Fighting & Safety Eqpt | HE-HS-0440 | HE-HS-0440: FS | HE-HS-0460 | HE-HS-0460: FS | 2024-03-10 | 2024-03-25
HE-HS-0460 | Completed | P2543-R01-Oct24..1.EN.4.16 | Obtain Company Approval-Data Sheets for Fire Fighting & Safety Eqpt | HE-HS-0450, HE-HS-0400 | HE-HS-0450: FS, HE-HS-0400: FS | HE-HS-0470, HE-HS-1060 | HE-HS-0470: FS, HE-HS-1060: FS | 2024-03-10 | 2024-03-25
HE-HS-0470 | Completed | P2543-R01-Oct24..1.EN.4.16 | Final Issue for Design/ Construction-Datasheets for fire fighting and safety equipment | HE-HS-0460, HE-HS-0410 | HE-HS-0460: FS, HE-HS-0410: FS | ML1219-B29, HM-PI-0020, CAB-4410 | ML1219-B29: FF, HM-PI-0020: FF, CAB-4410: FS | 2024-03-31 | 2024-04-22
HE-HS-0510 | Completed | P2543-R01-Oct24..1.EN.4.18 | Re-Issue for Approval- HSEIA Study Report | HE-WS-0050, HE-HS-0500 | HE-WS-0050: FS, HE-HS-0500: FS | HE-HS-0520 | HE-HS-0520: FS | 2024-02-26 | 2024-03-17
HE-HS-0520 | Completed | P2543-R01-Oct24..1.EN.4.18 | Obtain Company Approval- HSEIA Study Report | HE-HS-0510 | HE-HS-0510: FS | ML1016-B12, HE-HS-0530 | ML1016-B12: FF, HE-HS-0530: FS | 2024-03-18 | 2024-05-08
HE-HS-0530 | In Progress | P2543-R01-Oct24..1.EN.4.18 | Final Issue for Design/ Construction-HSEIA Study Report | HE-HS-0520 | HE-HS-0520: FS | CAB-4410 | CAB-4410: FS | 2024-05-09 | 2024-11-04 17:30
HE-HS-0500 | Completed | P2543-R01-Oct24..1.EN.4.18 | Receive Company Comments- HSEIA Study Report | HE-HS-0490 | HE-HS-0490: FS | HE-HS-0510, C-52-06CR-PL-CI-1400 | HE-HS-0510: FS, C-52-06CR-PL-CI-1400: FF 21 | 2024-01-13 | 2024-01-26
HE-HS-0490 | Completed | P2543-R01-Oct24..1.EN.4.18 | Study & Issue ICR- HSEIA Study Report | HE-WS-0200, HE-WS-0190, HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-PR-0130, HS-GN-0110, HE-HS-0190, HE-WS-0020, HE-WS-0030, HE-WS-0210 | HE-WS-0200: FF, HE-WS-0190: FS, HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-PR-0130: FS, HS-GN-0110: FS, HE-HS-0190: FS, HE-WS-0020: FS, HE-WS-0030: FS, HE-WS-0210: FS | HE-HS-0790, HE-HS-0970, HE-HS-0500 | HE-HS-0790: FS, HE-HS-0970: FS, HE-HS-0500: FS | 2023-12-29 | 2024-01-12
HE-HS-0580 | Completed | P2543-R01-Oct24..1.EN.4.10 | Obtain Company Approval-HAZID/ ENVID/ OHID Report | HE-HS-0570 | HE-HS-0570: FS | HE-HS-0590 | HE-HS-0590: FS | 2024-01-15 | 2024-01-15
HE-HS-0590 | Completed | P2543-R01-Oct24..1.EN.4.10 | Final Issue for Design/ Construction-HAZID/ ENVID/ OHID Report | HE-HS-0580, HE-HS-0170 | HE-HS-0580: FS, HE-HS-0170: FS | HE-HS-0710, HE-HS-0610, CAB-4410, HE-HS-1070, HE-HS-0710 | HE-HS-0710: FS, HE-HS-0610: FS, CAB-4410: FS, HE-HS-1070: FS, HE-HS-0710: FF | 2024-01-15 | 2024-06-13
HE-HS-0550 | Completed | P2543-R01-Oct24..1.EN.4.10 | Issue ICR-HAZID/ ENVID/ OHID Report | HE-HS-0130, HE-WS-0020 | HE-HS-0130: FS, HE-WS-0020: FS | HE-HS-0670, HE-HS-0560, HE-HS-1030 | HE-HS-0670: FS, HE-HS-0560: FS, HE-HS-1030: FS | 2023-11-01 | 2023-11-14
HE-HS-0560 | Completed | P2543-R01-Oct24..1.EN.4.10 | Receive Company Comments-HAZID/ ENVID/ OHID Report | HE-HS-0550 | HE-HS-0550: FS | HE-HS-0570 | HE-HS-0570: FS | 2023-11-15 | 2023-11-21
HE-HS-0570 | Completed | P2543-R01-Oct24..1.EN.4.10 | Re-Issue for Approval-HAZID/ ENVID/ OHID Report | HE-HS-0560 | HE-HS-0560: FS | HE-HS-0580, ML1013-B07 | HE-HS-0580: FS, ML1013-B07: FF | 2023-11-22 | 2024-01-15
HE-HS-0620 | Completed | P2543-R01-Oct24..1.EN.4.19 | Receive Company Comments-HAZID/ ENVID/ OHID Close out Report | HE-HS-0610 | HE-HS-0610: FS | HE-HS-0630 | HE-HS-0630: FS | 2024-05-08 | 2024-06-03
HE-HS-0630 | Completed | P2543-R01-Oct24..1.EN.4.19 | Re-Issue for Approval-HAZID/ ENVID/ OHID Close out Report | HE-HS-0620 | HE-HS-0620: FS | HE-HS-0640 | HE-HS-0640: FS | 2024-06-04 | 2024-10-11 17:30
HE-HS-0640 | In Progress | P2543-R01-Oct24..1.EN.4.19 | Obtain Company Approval-HAZID/ ENVID/ OHID Close out Report | HE-HS-0630 | HE-HS-0630: FS | HE-HS-0650 | HE-HS-0650: FS | 2024-10-11 07:30 | 2024-11-08 17:30
HE-HS-0650 | Not Started | P2543-R01-Oct24..1.EN.4.19 | Final Issue for Design/ Construction-HAZID/ ENVID/ OHID Close out Report | HE-HS-0640, HE-HS-0710 | HE-HS-0640: FS, HE-HS-0710: FS | CAB-4410 | CAB-4410: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-HS-0610 | Completed | P2543-R01-Oct24..1.EN.4.19 | Issue ICR-HAZID/ ENVID/ OHID Close out Report | HE-HS-0590 | HE-HS-0590: FS | HE-HS-1050, HE-HS-0620 | HE-HS-1050: FS, HE-HS-0620: FS | 2024-03-17 | 2024-05-07
HE-HS-0700 | Completed | P2543-R01-Oct24..1.EN.4.13 | Obtain Company Approval- HAZOP reviews Report for all areas | HE-HS-0690 | HE-HS-0690: FS | HE-HS-0710 | HE-HS-0710: FS | 2024-02-26 | 2024-03-01
HE-HS-0710 | Completed | P2543-R01-Oct24..1.EN.4.13 | Final Issue for Design/ Construction-HAZOP Review Report | HE-HS-0590, HE-HS-0700, HE-HS-0230, HE-HS-0590 | HE-HS-0590: FS, HE-HS-0700: FS, HE-HS-0230: FS, HE-HS-0590: FF | CAB-4410, HE-HS-0650, HE-HS-0770 | CAB-4410: FS, HE-HS-0650: FS, HE-HS-0770: FF | 2024-03-02 07:30 | 2024-05-18 17:30
HE-HS-0670 | Completed | P2543-R01-Oct24..1.EN.4.13 | Issue ICR- HAZOP reviews Report for all areas | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-PR-0130, HS-GN-0110, HE-WS-0020, HE-WS-0030, HE-HS-0550, HE-HS-0190, HE-WS-0210 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-PR-0130: FS, HS-GN-0110: FS, HE-WS-0020: FS, HE-WS-0030: FS, HE-HS-0550: FS, HE-HS-0190: FS, HE-WS-0210: FS | ML1219-B19, HE-PR-1130, HE-PI-0170, HE-PR-0870, HE-PR-0450, HE-PR-0570, HE-PR-1280, HE-PR-1330, HE-PR-1380, HE-PR-1430, HE-PR-1480, HE-PR-1530, HE-PR-1580, HE-ME-0090, HE-PR-0070, HE-PR-0140, HE-HS-0850, HE-HS-0680, HE-HS-1030, HE-PR-1200, HE-IC-1770, HE-I | ML1219-B19: FF, HE-PR-1130: SS, HE-PI-0170: SS, HE-PR-0870: SS, HE-PR-0450: SS, HE-PR-0570: SS, HE-PR-1280: SS, HE-PR-1330: SS, HE-PR-1380: SS, HE-PR-1430: SS, HE-PR-1480: SS, HE-PR-1530: SS, HE-PR-1580: SS, HE-ME-0090: FS, HE-PR-0070: FF, HE-PR-0140: SS, | 2023-11-28 | 2023-12-20
HE-HS-0680 | Completed | P2543-R01-Oct24..1.EN.4.13 | Receive Company Comments- HAZOP reviews Report for all areas | HE-HS-0670 | HE-HS-0670: FS | HE-HS-0690 | HE-HS-0690: FS | 2023-12-21 | 2023-12-29
HE-HS-0690 | Completed | P2543-R01-Oct24..1.EN.4.13 | Re-Issue for Approval- HAZOP reviews Report for all areas | HE-HS-0680 | HE-HS-0680: FS | HE-HS-0700, ML1013-B07 | HE-HS-0700: FS, ML1013-B07: FF | 2024-01-02 | 2024-01-19
HE-PI-0160 | Completed | P2543-R01-Oct24..1.EN.7.10 | 60% Model Review Report | HE-PI-0150 | HE-PI-0150: FS | HE-PI-0180, HE-PI-0170, HE-PI-0620 | HE-PI-0180: FS, HE-PI-0170: FS, HE-PI-0620: FS | 2024-03-22 | 2024-04-01
HE-PI-0170 | Completed | P2543-R01-Oct24..1.EN.7.10 | 90% Model Review | ML1027-B17, HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-WS-0030, HE-HS-0670, HE-PR-0070, HE-PR-1200, HE-PR-0650, ML2069-B09, HE-PI-0160, HM-ME-0410, HE-PR-0150 | ML1027-B17: FF, HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-WS-0030: FS, HE-HS-0670: SS, HE-PR-0070: FS, HE-PR-1200: FS, HE-PR-0650: FS, ML2069-B09: FS, HE-PI-0160: FS, HM-ME-0410: FS, HE-PR-0150: FS | HE-PI-0180, ML2079-B13, HE-PI-1220, HE-PI-1200 | HE-PI-0180: FS, ML2079-B13: FF, HE-PI-1220: FS, HE-PI-1200: FS | 2024-07-22 | 2024-07-26 17:30
HE-PI-0130 | Completed | P2543-R01-Oct24..1.EN.7.10 | 30% Model Review | HE-PR-1030, HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HS-GN-0110, HE-HS-0190, HE-WS-0020, HE-WS-0030, HE-PR-0110, HE-PI-0320, HE-PI-0460, HE-PI-0390, HE-PR-0130 | HE-PR-1030: FS, HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HS-GN-0110: FS, HE-HS-0190: FS, HE-WS-0020: FS, HE-WS-0030: FS, HE-PR-0110: FS, HE-PI-0320: FS, HE-PI-0460: FS, HE-PI-0390: FS, HE-PR-0130: FS 10 | HE-PI-1140, ML2059-B05, HE-PI-0140, HE-CS-1510 | HE-PI-1140: FS, ML2059-B05: FF, HE-PI-0140: FS, HE-CS-1510: FS | 2023-11-08 | 2023-11-09
HE-PI-0140 | Completed | P2543-R01-Oct24..1.EN.7.10 | 30% Model Review Report | HE-PI-0130 | HE-PI-0130: FS | HE-PI-0150, HE-PI-0370 | HE-PI-0150: FS, HE-PI-0370: FS | 2023-11-10 | 2023-11-22
HE-PI-0150 | Completed | P2543-R01-Oct24..1.EN.7.10 | 60% Model Review | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-PR-0130, HS-GN-0110, HE-HS-0190, HE-WS-0030, ML2059-B05, HE-PI-0140, HE-WS-0020, HE-PR-0140 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-PR-0130: FS, HS-GN-0110: FS, HE-HS-0190: FS, HE-WS-0030: FS, ML2059-B05: FS, HE-PI-0140: FS, HE-WS-0020: FS, HE-PR-0140: FS | ML2069-B09, HE-PI-0160, HE-PI-1200, HE-PI-0740 | ML2069-B09: FF, HE-PI-0160: FS, HE-PI-1200: FS, HE-PI-0740: FS | 2024-03-25 | 2024-03-27
HE-PI-0180 | Completed | P2543-R01-Oct24..1.EN.7.10 | 90% Model Review Report | HE-PI-0170, ML2079-B13, HE-PI-0160, HE-PL-1370, HE-PI-3520, HS-GN-0230 | HE-PI-0170: FS, ML2079-B13: FF, HE-PI-0160: FS, HE-PL-1370: FS, HE-PI-3520: FS, HS-GN-0230: FS | HE-PI-1200, HE-PI-0600, ML1219-B29, HE-PI-1210 | HE-PI-1200: FS, HE-PI-0600: FS 10, ML1219-B29: FF, HE-PI-1210: FS | 2024-07-27 07:30 | 2024-08-28 17:30
HE-PI-0600 | Completed | P2543-R01-Oct24..1.EN.7.11.8 | Issue ICR-Piping GA-56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0180, HE-PR-0610, HE-PI-0350, HE-PI-0320 | HE-PI-0180: FS 10, HE-PR-0610: FS, HE-PI-0350: FS, HE-PI-0320: FS | HE-PI-0610 | HE-PI-0610: FS | 2024-09-29 07:30 | 2024-10-04 17:30
HE-PI-0610 | Completed | P2543-R01-Oct24..1.EN.7.11.8 | Receive Company Comments-56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0600 | HE-PI-0600: FS | HE-PI-0620 | HE-PI-0620: FS | 2024-10-04 07:30 | 2024-10-11 17:30
HE-PI-0620 | Completed | P2543-R01-Oct24..1.EN.7.11.8 | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HM-ME-0410, HE-PI-0610, HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-WS-0030, HE-HS-0670, HE-PR-0070, HE-PR-1200, HE-PR-0090, HE-PR-0650, HE-PR-1220, HE-PR-0830, HE-PR-0770, HE-PR-0140, HE-PR-0110, HE-PR-0730, HE-PR-0790, HE-PI-0160 | HM-ME-0410: FS, HE-PI-0610: FS, HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-WS-0030: FS, HE-HS-0670: SS, HE-PR-0070: FS, HE-PR-1200: FS, HE-PR-0090: FS, HE-PR-0650: FS, HE-PR-1220: FS, HE-PR-0830: FS, HE-PR-0770: FS, HE-PR-0140: FS, | HE-PI-0630 | HE-PI-0630: FS | 2024-10-11 07:30 | 2024-10-18 17:30
HE-PI-0630 | Completed | P2543-R01-Oct24..1.EN.7.11.8 | Obtain Company Approval-Piping GA-56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0620 | HE-PI-0620: FS | HE-PI-0640 | HE-PI-0640: FS | 2024-10-18 07:30 | 2024-10-23 17:30
HE-PI-0640 | In Progress | P2543-R01-Oct24..1.EN.7.11.8 | Final Issue for Design/ Construction-Piping GA- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0630, HE-PI-0370, HE-PI-1180 | HE-PI-0630: FS, HE-PI-0370: FF, HE-PI-1180: FF | ML1219-B29, ML1219-B19, HE-CO-200, C-56-PL-607-PI-1000, C-56-G-HT-PI-1000 | ML1219-B29: FF, ML1219-B19: FF, HE-CO-200: FS, C-56-PL-607-PI-1000: FS, C-56-G-HT-PI-1000: FS | 2024-10-24 07:30 | 2024-11-15 17:30
HE-PI-0680 | Completed | P2543-R01-Oct24..1.EN.7.11.25 | Re-Issue for Approval-Piping GA for 52" Pipeline SWEIHAN CRS | HE-PI-0670, HM-ME-0410 | HE-PI-0670: FS, HM-ME-0410: FS | HE-PI-1220, HE-PI-0690 | HE-PI-1220: FS, HE-PI-0690: FS | 2024-09-16 07:30 | 2024-09-20 17:30
HE-PI-0690 | Completed | P2543-R01-Oct24..1.EN.7.11.25 | Obtain Company Approval-Piping GA for 52" Pipeline SWEIHAN CRS | HE-PI-0680 | HE-PI-0680: FS | HE-PI-0700 | HE-PI-0700: FS | 2024-09-23 07:30 | 2024-09-27 17:30
HE-PI-0700 | In Progress | P2543-R01-Oct24..1.EN.7.11.25 | Final Issue for Design/ Construction-Piping GA- 52" Pipeline SWEIHAN CRS | HE-PI-1180, HE-PI-0440, HE-PI-0690 | HE-PI-1180: FF, HE-PI-0440: FF, HE-PI-0690: FS | ML1219-B29, CAB-4440, ML1219-B19, HE-CO-200, C-52-PR-839-PI-1000, C-52-D-HT-PI-1000 | ML1219-B29: FF, CAB-4440: FS, ML1219-B19: FF, HE-CO-200: FS, C-52-PR-839-PI-1000: FS, C-52-D-HT-PI-1000: FS | 2024-10-08 07:30 | 2024-11-15 17:30
HE-PI-0660 | Completed | P2543-R01-Oct24..1.EN.7.11.25 | Issue ICR-Piping GA for 52" Pipeline SWEIHAN CRS | HE-PI-0420, HE-PR-0610 | HE-PI-0420: FS, HE-PR-0610: FS | HE-PI-0720, HE-PI-0670 | HE-PI-0720: FF, HE-PI-0670: FS | 2024-09-02 07:30 | 2024-09-06 17:30
HE-PI-0670 | Completed | P2543-R01-Oct24..1.EN.7.11.25 | Receive Company Comments-Piping GA for 52" Pipeline SWEIHAN CRS | HE-PI-0660 | HE-PI-0660: FS | HE-PI-0680, HE-PI-0750, HE-PI-0730 | HE-PI-0680: FS, HE-PI-0750: FS, HE-PI-0730: FS | 2024-09-09 07:30 | 2024-09-13 17:30
HE-PI-0720 | Not Started | P2543-R01-Oct24..1.EN.7.11.27 | Issue ICR- Piping GA for 4" N2 Source Pipeline | HE-PI-0660, HE-PR-0610, HE-PI-0490 | HE-PI-0660: FF, HE-PR-0610: FS, HE-PI-0490: FS | HE-PI-0730 | HE-PI-0730: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HE-PI-0730 | Not Started | P2543-R01-Oct24..1.EN.7.11.27 | Receive Company Comments-Piping GA for 4" N2 Source Pipeline | HE-PI-0720, HE-PI-0670 | HE-PI-0720: FS, HE-PI-0670: FS | HE-PI-0740 | HE-PI-0740: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-PI-0740 | Not Started | P2543-R01-Oct24..1.EN.7.11.27 | Re-Issue for Approval-Piping GA for 4" N2 Source Pipeline | HM-ME-0410, HE-PI-0730, HE-PI-0150 | HM-ME-0410: SS 8, HE-PI-0730: FS, HE-PI-0150: FS | HE-PI-0750 | HE-PI-0750: FS | 2024-11-25 07:30 | 2024-12-10 17:30
HE-PI-0750 | Not Started | P2543-R01-Oct24..1.EN.7.11.27 | Obtain Company Approval-Piping GA for 4" N2 Source Pipeline | HE-PI-0740, HE-PI-0670 | HE-PI-0740: FS, HE-PI-0670: FS | HE-PI-0760 | HE-PI-0760: FS | 2024-12-11 07:30 | 2024-12-24 17:30
HE-PI-0760 | Not Started | P2543-R01-Oct24..1.EN.7.11.27 | Final Issue for Design/ Construction-Piping GA for 4" N2 Source Pipeline | HE-PI-1180, HE-PI-0510, HE-PI-0750 | HE-PI-1180: FS, HE-PI-0510: FS, HE-PI-0750: FS | ML1219-B19, CAB-4440, HE-CO-200, HE-PI-0880, C-4N-H5-TPL-PI-1000, C-4N-HG-TPR-PI-1000 | ML1219-B19: FF, CAB-4440: FS, HE-CO-200: FS, HE-PI-0880: FF, C-4N-H5-TPL-PI-1000: FS, C-4N-HG-TPR-PI-1000: FS | 2024-12-25 07:30 | 2024-12-31 17:30
HE-PI-0780 | Completed | P2543-R01-Oct24..1.EN.7.11.4 | Issue ICR - Piping GA Drawings for 591-BVS-01 | HE-PI-0560, HE-PR-0610 | HE-PI-0560: FS, HE-PR-0610: FS | HE-PI-0840, HE-PI-0790 | HE-PI-0840: FS, HE-PI-0790: FS | 2024-09-02 07:30 | 2024-09-06 17:30
HE-PI-0790 | Completed | P2543-R01-Oct24..1.EN.7.11.4 | Receive Company Comments-Piping GA Drawings for 591-BVS-01 | HE-PI-0780 | HE-PI-0780: FS | HE-PI-0800, HE-PI-0850 | HE-PI-0800: FS, HE-PI-0850: FS | 2024-09-09 07:30 | 2024-09-13 17:30
HE-PI-0800 | Completed | P2543-R01-Oct24..1.EN.7.11.4 | Re-Issue for Approval-Piping GA Drawings for 591-BVS-01 | HE-PI-0790 | HE-PI-0790: FS | HE-PI-1220, HE-PI-0810 | HE-PI-1220: FS, HE-PI-0810: FS | 2024-09-16 07:30 | 2024-09-20 17:30
HE-PI-0810 | Completed | P2543-R01-Oct24..1.EN.7.11.4 | Obtain Company Approval-Piping GA Drawings for 591-BVS-01 | HE-PI-0800 | HE-PI-0800: FS | HE-PI-0820 | HE-PI-0820: FS | 2024-09-23 07:30 | 2024-09-27 17:30
HE-PI-0820 | In Progress | P2543-R01-Oct24..1.EN.7.11.4 | Final Issue for Design/ Construction-Piping GA Drawings for 591-BVS-01 | HE-PI-0810, HE-PI-0580, HE-PI-1180 | HE-PI-0810: FS, HE-PI-0580: FF, HE-PI-1180: FF | ML1219-B19, CAB-4440, HE-CO-200, C-56-591-01-PI-1000 | ML1219-B19: FF, CAB-4440: FS, HE-CO-200: FS, C-56-591-01-PI-1000: FS | 2024-09-30 07:30 | 2024-11-15 17:30
HE-PI-0850 | Completed | P2543-R01-Oct24..1.EN.7.11.28 | Receive Company Comments-Piping GA for 591-BVS-01 to 06 | HE-PI-0840, HE-PI-0790 | HE-PI-0840: FS, HE-PI-0790: FS | HE-PI-0860 | HE-PI-0860: FS | 2024-09-23 07:30 | 2024-09-26 17:30
HE-PI-0860 | Completed | P2543-R01-Oct24..1.EN.7.11.28 | Re-Issue for Approval-Piping GA for 591-BVS-01 to 06 | HE-PI-0850 | HE-PI-0850: FS | HE-PI-0870 | HE-PI-0870: FS | 2024-09-26 07:30 | 2024-09-30 17:30
HE-PI-0870 | Completed | P2543-R01-Oct24..1.EN.7.11.28 | Obtain Company Approval-Piping GA for 591-BVS-01 to 06 | HE-PI-0860 | HE-PI-0860: FS | HE-PI-0880 | HE-PI-0880: FS | 2024-09-30 07:30 | 2024-10-04 17:30
HE-PI-0880 | In Progress | P2543-R01-Oct24..1.EN.7.11.28 | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | HE-PI-0580, HE-PI-1180, HE-PI-0870, HE-PI-0760 | HE-PI-0580: FF, HE-PI-1180: FF, HE-PI-0870: FS, HE-PI-0760: FF | ML1219-B29, ML1219-B19, CAB-4440, HE-CO-200, C-52-598-06-PI-1000, C-52-598-06-PI-1200, C-52-598-06-PI-1800, C-52-598-06-PI-2000, C-52-598-05-PI-1000, C-52-598-05-PI-1200, C-52-598-05-PI-1800, C-52-598-05-PI-2000, C-52-598-04-PI-1000, C-52-598-03-PI-1000, C | ML1219-B29: FF, ML1219-B19: FF, CAB-4440: FS, HE-CO-200: FS, C-52-598-06-PI-1000: FS, C-52-598-06-PI-1200: FS, C-52-598-06-PI-1800: FS, C-52-598-06-PI-2000: FS, C-52-598-05-PI-1000: FS, C-52-598-05-PI-1200: FS, C-52-598-05-PI-1800: FS, C-52-598-05-PI-2000: | 2024-10-07 07:30 | 2024-12-31 17:30
HE-PI-0840 | Completed | P2543-R01-Oct24..1.EN.7.11.28 | Issue ICR-Piping GA for 591-BVS-01 to 06 | HE-PI-0780, HE-PR-0610, HE-PI-0550, HE-PI-0560 | HE-PI-0780: FS, HE-PR-0610: FS, HE-PI-0550: FS, HE-PI-0560: FS | HE-PI-0850 | HE-PI-0850: FS | 2024-09-16 07:30 | 2024-09-23 17:30
HE-PI-0900 | Completed | P2543-R01-Oct24..1.EN.7.4.9 | Issue ICR-Data sheet for Ball Valves | HE-PR-1090, HE-PR-0110 | HE-PR-1090: FF, HE-PR-0110: FS | HE-IC-1210, HE-IC-1090, HE-IC-1030, HE-PI-0910, HE-PI-1020, HE-PI-3580, HE-IC-1750, HE-IC-1770, HE-IC-1250, HE-IC-1790, CAB-4460 | HE-IC-1210: FS, HE-IC-1090: FS, HE-IC-1030: FS, HE-PI-0910: FS, HE-PI-1020: FS, HE-PI-3580: FS 5, HE-IC-1750: FS, HE-IC-1770: FS, HE-IC-1250: FS, HE-IC-1790: FS, CAB-4460: FS | 2023-09-22 | 2023-09-28
HE-PI-0910 | Completed | P2543-R01-Oct24..1.EN.7.4.9 | Receive Company Comments-Data sheet for Ball Valves | HE-PI-0900 | HE-PI-0900: FS | HE-PI-0920 | HE-PI-0920: FS | 2023-09-30 | 2023-10-11
HE-PI-0920 | Completed | P2543-R01-Oct24..1.EN.7.4.9 | Re-Issue for Approval-Data sheet for Ball Valves | HE-PI-0910 | HE-PI-0910: FS | HE-PI-0930, HE-PI-1040 | HE-PI-0930: FS, HE-PI-1040: FS | 2023-10-31 | 2023-11-07
HE-PI-0930 | Completed | P2543-R01-Oct24..1.EN.7.4.9 | Obtain Company Approval-Data sheet for Ball Valves | HE-PI-0920 | HE-PI-0920: FS | HE-PI-0940 | HE-PI-0940: FS | 2023-11-08 | 2023-11-14
HE-PI-0940 | Completed | P2543-R01-Oct24..1.EN.7.4.9 | Final Issue for Design/ Construction-Datasheet for Ball valves | HE-PI-0930 | HE-PI-0930: FS | HE-PI-1060, CAB-4440, HE-IC-1750 | HE-PI-1060: FS, CAB-4440: FS, HE-IC-1750: FS 10 | 2023-11-15 | 2023-11-22
HE-PI-1000 | Completed | P2543-R01-Oct24..1.EN.7.4.2 | Final Issue for Design/ Construction-Datasheet for Plug valves | HE-PI-0990 | HE-PI-0990: FS | HE-PI-1060, CAB-4440 | HE-PI-1060: FS, CAB-4440: FS | 2023-11-15 | 2023-11-22
HE-PI-0960 | Completed | P2543-R01-Oct24..1.EN.7.4.2 | Issue ICR- Datasheet for Plug Valves | HE-PR-0110, HE-PR-1090 | HE-PR-0110: FS, HE-PR-1090: FF | HE-PI-0970, HE-PI-1020, HE-PI-1320, HE-IC-1090, HE-IC-1150 | HE-PI-0970: FS, HE-PI-1020: FS, HE-PI-1320: FS, HE-IC-1090: FS, HE-IC-1150: FF | 2023-09-22 | 2023-09-28
HE-PI-0970 | Completed | P2543-R01-Oct24..1.EN.7.4.2 | Receive Company Comments- Datasheet for Plug Valves | HE-PI-0960 | HE-PI-0960: FS | HE-PI-0980 | HE-PI-0980: FS | 2023-09-30 | 2023-10-11
HE-PI-0980 | Completed | P2543-R01-Oct24..1.EN.7.4.2 | Re-Issue for Approval- Datasheet for Plug Valves | HE-PI-0970 | HE-PI-0970: FS | HE-PI-1040, HE-PI-0990 | HE-PI-1040: FS, HE-PI-0990: FS | 2023-10-31 | 2023-11-07
HE-PI-0990 | Completed | P2543-R01-Oct24..1.EN.7.4.2 | Obtain Company Approval- Datasheet for Plug Valves | HE-PI-0980 | HE-PI-0980: FS | HE-PI-1000 | HE-PI-1000: FS | 2023-11-08 | 2023-11-14
HE-PI-1020 | Completed | P2543-R01-Oct24..1.EN.7.8.18 | Issue ICR-MR for Ball valves/ Plug Valves | HE-PI-0960, HE-PI-0900, HE-DB-0010, HE-PI-0010 | HE-PI-0960: FS, HE-PI-0900: FS, HE-DB-0010: FS, HE-PI-0010: FS | HE-PI-1030, HP-ME-1070 | HE-PI-1030: FS, HP-ME-1070: FS | 2023-11-29 | 2023-12-15
HE-PI-1030 | Completed | P2543-R01-Oct24..1.EN.7.8.18 | Receive Company Comments-MR for Ball valves/ Plug Valves | HE-PI-1020 | HE-PI-1020: FS | HE-PI-1040, HE-PI-1080 | HE-PI-1040: FS, HE-PI-1080: FS | 2023-11-29 | 2023-12-09
HE-PI-1040 | Completed | P2543-R01-Oct24..1.EN.7.8.18 | Re-Issue for Approval-MR for Ball valves/ Plug Valves | HE-PI-1030, HE-PI-0980, HE-PI-0920 | HE-PI-1030: FS, HE-PI-0980: FS, HE-PI-0920: FS | HE-PI-1050 | HE-PI-1050: FS | 2023-12-04 | 2024-02-16
HE-PI-1050 | Completed | P2543-R01-Oct24..1.EN.7.8.18 | Obtain Company Approval-MR for Ball valves/ Plug Valves | HE-PI-1040 | HE-PI-1040: FS | HE-PI-1060 | HE-PI-1060: FS | 2023-12-04 | 2024-02-16
HE-PI-1060 | Completed | P2543-R01-Oct24..1.EN.7.8.18 | Final Issue for Design/ Construction-Material Requisition for Ball/ Plug Valves | HE-PI-0940, HE-PI-1050, HE-PI-1000 | HE-PI-0940: FS, HE-PI-1050: FS, HE-PI-1000: FS | CAB-4440, HP-ME-1090 | CAB-4440: FS, HP-ME-1090: FS | 2024-02-16 | 2024-03-08
HE-PI-1080 | Completed | P2543-R01-Oct24..1.EN.7.2.6 | Issue ICR- TBE for Ball valves/ Plug Valves | HP-ME-1070, HE-PI-1030 | HP-ME-1070: FS, HE-PI-1030: FS | HE-PI-1090, HP-ME-1080 | HE-PI-1090: FS, HP-ME-1080: SS | 2024-01-30 | 2024-02-23
HE-PI-1090 | Completed | P2543-R01-Oct24..1.EN.7.2.6 | Receive Company Comments- TBE for Ball valves/ Plug Valves | HE-PI-1080 | HE-PI-1080: FS | HE-PI-1100 | HE-PI-1100: FS | 2024-02-26 | 2024-03-08
HE-PI-1100 | Completed | P2543-R01-Oct24..1.EN.7.2.6 | Re-Issue for Approval- TBE for Ball valves/ Plug Valves | HE-PI-1090 | HE-PI-1090: FS | HE-PI-1110 | HE-PI-1110: FS | 2024-03-10 | 2024-03-25
HE-PI-1110 | Completed | P2543-R01-Oct24..1.EN.7.2.6 | Obtain Company Approval- TBE for Ball valves/ Plug Valves | HE-PI-1100 | HE-PI-1100: FS | HE-PI-1120, HP-ME-1090, HP-ME-1080 | HE-PI-1120: FS, HP-ME-1090: FS, HP-ME-1080: FF | 2024-03-26 | 2024-05-16
HE-PI-1120 | In Progress | P2543-R01-Oct24..1.EN.7.2.6 | Final Issue for Design/ Construction-TBE for Ball valves/ Plug Valves | HE-PI-1110 | HE-PI-1110: FS | CAB-4440 | CAB-4440: FS | 2024-08-14 07:30 | 2024-11-01 17:30
HE-PI-1160 | Completed | P2543-R01-Oct24..1.EN.7.12 | Re-Issue for Approval-Piping Stress Analysis & Report | HE-PI-0282, HE-PI-1150, HE-PL-2830 | HE-PI-0282: FS, HE-PI-1150: FS, HE-PL-2830: SS | HE-CS-1330, HE-PI-1170, HE-CS-1450, HE-CS-1390 | HE-CS-1330: SS, HE-PI-1170: FS, HE-CS-1450: FS, HE-CS-1390: FS | 2024-04-18 | 2024-06-10
HE-PI-1170 | Completed | P2543-R01-Oct24..1.EN.7.12 | Obtain Company Approval-Piping Stress Analysis & Report | HE-PI-1160 | HE-PI-1160: FS | HE-PI-1180 | HE-PI-1180: FS | 2024-06-11 | 2024-06-18
HE-PI-1180 | In Progress | P2543-R01-Oct24..1.EN.7.12 | Final Issue for Design/ Construction-Piping Stress Analysis & Report | HE-PI-0240, HE-PI-0302, HE-PI-1170, HE-PI-3770 | HE-PI-0240: FS, HE-PI-0302: FS, HE-PI-1170: FS, HE-PI-3770: FF | HE-CS-1430, HE-PI-0760, HE-PI-0700, CAB-4440, HE-PI-0880, HE-PI-0820, HE-CS-1490, HE-PI-0640 | HE-CS-1430: FS, HE-PI-0760: FS, HE-PI-0700: FF, CAB-4440: FS, HE-PI-0880: FF, HE-PI-0820: FF, HE-CS-1490: FS, HE-PI-0640: FF | 2024-06-19 | 2024-11-15 17:30
HE-PI-1140 | Completed | P2543-R01-Oct24..1.EN.7.12 | Issue ICR-Piping Stress Analysis & Report | HM-ME-0410, HE-PI-0200, HE-PI-0262, HE-PL-2810, ML2059-B05, HE-PI-0130 | HM-ME-0410: SS 15, HE-PI-0200: FS, HE-PI-0262: FS, HE-PL-2810: SS, ML2059-B05: FS, HE-PI-0130: FS | HE-PI-1150 | HE-PI-1150: FS | 2024-03-06 | 2024-03-19
HE-PI-1150 | Completed | P2543-R01-Oct24..1.EN.7.12 | Receive Company Comments-Piping Stress Analysis & Report | HE-PI-1140 | HE-PI-1140: FS | HE-PI-1160 | HE-PI-1160: FS | 2024-03-20 | 2024-03-29
HE-PI-1200 | Completed | P2543-R01-Oct24..1.EN.7.5 | Issue ICR-Piping Isometrics | HE-PI-0180, HE-PI-0150, HE-PI-0170 | HE-PI-0180: FS, HE-PI-0150: FS, HE-PI-0170: FS | HE-PI-1210 | HE-PI-1210: FF 10 | 2024-09-02 07:30 | 2024-10-10 17:30
HE-PI-1210 | Completed | P2543-R01-Oct24..1.EN.7.5 | Receive Company Comments-Piping Isometrics | HE-PI-1200, HE-PI-0180 | HE-PI-1200: FF 10, HE-PI-0180: FS | HE-PI-1220 | HE-PI-1220: FF 5 | 2024-09-16 07:30 | 2024-10-14 17:30
HE-PI-1220 | Completed | P2543-R01-Oct24..1.EN.7.5 | Re-Issue for Approval-Piping Isometrics | HE-PI-1210, HE-PI-0680, HE-PI-0800, HE-PI-0170 | HE-PI-1210: FF 5, HE-PI-0680: FS, HE-PI-0800: FS, HE-PI-0170: FS | HE-PI-1230 | HE-PI-1230: FS | 2024-09-21 07:30 | 2024-10-21 17:30
HE-PI-1240 | In Progress | P2543-R01-Oct24..1.EN.7.5 | Final Issue for Design/ Construction-Piping Isometrics | HE-PI-1230, HE-PI-3520 | HE-PI-1230: FS, HE-PI-3520: FS | ML1219-B29, CAB-4440, C-56-PL-607-PI-1000, C-56-PL-607-PI-1200, C-56-PL-607-PI-1800, C-56-PL-607-PI-2000, C-56-G-HT-PI-1000, C-56-G-HT-PI-1200, C-56-G-HT-PI-1800, C-56-G-HT-PI-2000, C-56-PR-838-PI-1000, C-56-PR-838-PI-1200, C-56-PR-838-PI-1800, C-56-PR-838 | ML1219-B29: FF, CAB-4440: FS, C-56-PL-607-PI-1000: FS, C-56-PL-607-PI-1200: FS, C-56-PL-607-PI-1800: FS, C-56-PL-607-PI-2000: FS, C-56-G-HT-PI-1000: FS, C-56-G-HT-PI-1200: FS, C-56-G-HT-PI-1800: FS, C-56-G-HT-PI-2000: FS, C-56-PR-838-PI-1000: FS, C-56-PR-8 | 2024-10-25 07:30 | 2024-11-01 17:30
HE-PI-1230 | Completed | P2543-R01-Oct24..1.EN.7.5 | Obtain Company Approval-Piping Isometrics | HE-PI-1220 | HE-PI-1220: FS | HE-PI-1240 | HE-PI-1240: FS | 2024-09-30 07:30 | 2024-10-24 17:30
HE-PI-1300 | Completed | P2543-R01-Oct24..1.EN.7.19 | Piping MTO - Final | ML2079-B13, HE-PI-1280 | ML2079-B13: FS 10, HE-PI-1280: FS | CAB-4440, HP-BK-0350, C-56-PL-607-PI-1000, C-56-PL-607-PI-1200, C-56-PL-607-PI-1400, C-56-PL-607-PI-2000, C-56-G-HT-PI-1000, C-56-G-HT-PI-1200, C-56-G-HT-PI-1400, C-56-G-HT-PI-2000, C-56-PR-838-PI-1000, C-56-PR-838-PI-1200, C-56-PR-838-PI-1400, C-56-PR-838 | CAB-4440: FS, HP-BK-0350: FF, C-56-PL-607-PI-1000: FS, C-56-PL-607-PI-1200: FS, C-56-PL-607-PI-1400: FS, C-56-PL-607-PI-2000: FS, C-56-G-HT-PI-1000: FS, C-56-G-HT-PI-1200: FS, C-56-G-HT-PI-1400: FS, C-56-G-HT-PI-2000: FS, C-56-PR-838-PI-1000: FS, C-56-PR-8 | 2024-10-01 07:30 | 2024-10-10 17:30
HE-PI-1260 | Completed | P2543-R01-Oct24..1.EN.7.19 | Piping MTO - 1st | ML2059-B05, HE-PI-3570 | ML2059-B05: FS 10, HE-PI-3570: FS | HP-BK-0340, HP-BK-520, HE-PI-1280 | HP-BK-0340: FS, HP-BK-520: FS, HE-PI-1280: FS | 2024-06-29 07:30 | 2024-07-09 17:30
HE-PI-1280 | Completed | P2543-R01-Oct24..1.EN.7.19 | Piping MTO - 2nd | ML2069-B09, HE-PI-1260 | ML2069-B09: FS 10, HE-PI-1260: FS | HE-PI-1300 | HE-PI-1300: FS | 2024-08-21 07:30 | 2024-09-12 17:30
HE-PI-0010 | Completed | P2543-R01-Oct24..1.EN.7.1 | Issue ICR-Piping Material Specifications | HE-DB-0010, HE-CP-200, HE-CP-0010, HE-PR-1030, HE-PI-0200, HE-CP-200 | HE-DB-0010: FS, HE-CP-200: FF 5, HE-CP-0010: FF 5, HE-PR-1030: FF 5, HE-PI-0200: SS 5, HE-CP-200: SS | HE-PR-0110, HE-PI-0020, HE-PI-1020 | HE-PR-0110: SS 5, HE-PI-0020: FS, HE-PI-1020: FS | 2023-08-27 | 2023-09-06
HE-PI-0020 | Completed | P2543-R01-Oct24..1.EN.7.1 | Receive Company Comments-Piping Material Specifications | HE-PI-0010 | HE-PI-0010: FS | HE-PI-0030, HE-HV-2740 | HE-PI-0030: FS, HE-HV-2740: FS | 2023-09-06 | 2023-09-16
HE-PI-0030 | Completed | P2543-R01-Oct24..1.EN.7.1 | Re-Issue for Approval-Piping Material Specifications | HE-PI-0020 | HE-PI-0020: FS | HE-PI-0040 | HE-PI-0040: FS | 2023-10-30 | 2023-11-02
HE-PI-0040 | Completed | P2543-R01-Oct24..1.EN.7.1 | Obtain Company Approval-Piping Material Specifications | HE-PI-0030 | HE-PI-0030: FS | HE-PI-0050 | HE-PI-0050: FS | 2023-11-03 | 2023-11-17
HE-PI-0050 | Completed | P2543-R01-Oct24..1.EN.7.1 | Final Issue for Design/ Construction-Piping Material Specification | HE-CP-240, HE-PI-0040 | HE-CP-240: FS, HE-PI-0040: FS | CAB-4440, HE-IC-1130, HE-PR-0140, HE-PI-0262 | CAB-4440: FS, HE-IC-1130: FS, HE-PR-0140: FS, HE-PI-0262: FS | 2023-11-21 | 2024-03-01
HE-PI-0200 | Completed | P2543-R01-Oct24..1.EN.7.3 | Issue ICR-Pipe Wall Thickness Calculation | HE-DB-130, HE-CP-0010 | HE-DB-130: FS, HE-CP-0010: FS | HE-PI-1140, HE-PI-0210, HE-PI-0010 | HE-PI-1140: FS, HE-PI-0210: FS, HE-PI-0010: SS 5 | 2023-08-15 | 2023-08-25
HE-PI-0210 | Completed | P2543-R01-Oct24..1.EN.7.3 | Receive Company Comments-Pipe Wall Thickness Calculation | HE-PI-0200 | HE-PI-0200: FS | HE-PI-0220 | HE-PI-0220: FS | 2023-09-11 | 2023-09-22
HE-PI-0220 | Completed | P2543-R01-Oct24..1.EN.7.3 | Re-Issue for Approval-Pipe Wall Thickness Calculation | HE-PI-0210 | HE-PI-0210: FS | HE-PI-0230 | HE-PI-0230: FS | 2023-09-25 | 2023-09-29
HE-PI-0230 | Completed | P2543-R01-Oct24..1.EN.7.3 | Obtain Company Approval-Pipe Wall Thickness Calculation | HE-PI-0220 | HE-PI-0220: FS | HE-PI-0240 | HE-PI-0240: FS | 2023-12-29 | 2024-01-09
HE-PI-0240 | Completed | P2543-R01-Oct24..1.EN.7.3 | Final Issue for Design/ Construction-Pipe Wall Thickness Calculation | HE-PI-0230 | HE-PI-0230: FS | HE-PI-1180, CAB-4440, C-COM-750, HE-PI-0262, HE-PI-0340 | HE-PI-1180: FS, CAB-4440: FS, C-COM-750: FS, HE-PI-0262: FS, HE-PI-0340: FS | 2024-01-12 | 2024-01-16
HE-PI-0292 | Completed | P2543-R01-Oct24..1.EN.7.16 | Obtain Company Approval-Critical line List | HE-PI-0282 | HE-PI-0282: FS | HE-PI-0302 | HE-PI-0302: FS | 2024-01-10 | 2024-01-24
HE-PI-0302 | Completed | P2543-R01-Oct24..1.EN.7.16 | Final Issue for Design/ Construction-Critical line List | HE-PI-0292, HE-PR-1130 | HE-PI-0292: FS, HE-PR-1130: SS 10 | CAB-4440, HE-PI-1180 | CAB-4440: FS, HE-PI-1180: FS | 2024-01-29 | 2024-06-19 17:30
HE-PI-0262 | Completed | P2543-R01-Oct24..1.EN.7.16 | Issue ICR-Critical line List | HE-PR-1090, HE-PR-1110, HE-PI-0240, HE-PI-0050 | HE-PR-1090: FS 5, HE-PR-1110: FS 10, HE-PI-0240: FS, HE-PI-0050: FS | HE-PI-0272, HE-PI-1140 | HE-PI-0272: FS, HE-PI-1140: FS | 2023-11-06 | 2023-11-15
HE-PI-0272 | Completed | P2543-R01-Oct24..1.EN.7.16 | Receive Company Comments-Critical line List | HE-PI-0262 | HE-PI-0262: FS | HE-PI-0282 | HE-PI-0282: FS | 2023-11-16 | 2023-11-25
HE-PI-0282 | Completed | P2543-R01-Oct24..1.EN.7.16 | Re-Issue for Approval-Critical line List | HE-PI-0272 | HE-PI-0272: FS | HE-PI-1160, HE-PI-0292 | HE-PI-1160: FS, HE-PI-0292: FS | 2023-11-28 | 2023-12-22
HE-PI-0320 | Completed | P2543-R01-Oct24..1.EN.7.24.11 | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0040, HE-PR-1240, HE-PR-0050, HE-PR-1030, HE-PI-0390 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-0050: FS, HE-PR-1030: FS, HE-PI-0390: SS 5 | HE-PI-0330, HE-PI-0130, HE-WS-0030, HE-WS-0050, HE-PL-2570, HE-PR-0970, HE-PI-0600, HC-GN-0250, HE-WS-0090, HE-PI-0460 | HE-PI-0330: FS, HE-PI-0130: FS, HE-WS-0030: FS, HE-WS-0050: FS, HE-PL-2570: FS, HE-PR-0970: FS, HE-PI-0600: FS, HC-GN-0250: FS, HE-WS-0090: FS, HE-PI-0460: SS 5 | 2023-09-15 | 2023-09-28
HE-PI-0330 | Completed | P2543-R01-Oct24..1.EN.7.24.11 | Receive Company Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0320 | HE-PI-0320: FS | HE-WS-0020, HE-PI-0340 | HE-WS-0020: FS, HE-PI-0340: FS | 2023-11-07 | 2023-11-09
HE-PI-0350 | Completed | P2543-R01-Oct24..1.EN.7.24.11 | Re-Issue after HAZOP /Review Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-TS-0010, HE-PI-0340, HE-PR-0070, HE-PR-1200, HE-TS-230 | HE-TS-0010: FS, HE-PI-0340: FS, HE-PR-0070: FS, HE-PR-1200: FS, HE-TS-230: FS | HE-HS-0250, HE-CS-1270, HE-PI-0360, HE-CS-1030, HE-PI-0600 | HE-HS-0250: FS, HE-CS-1270: FS, HE-PI-0360: FS, HE-CS-1030: FS, HE-PI-0600: FS | 2023-11-28 | 2023-12-08
HE-PI-0360 | Completed | P2543-R01-Oct24..1.EN.7.24.11 | Obtain Company Approval- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0350 | HE-PI-0350: FS | HE-PI-0370 | HE-PI-0370: FS | 2023-12-12 | 2023-12-26
HE-PI-0370 | In Progress | P2543-R01-Oct24..1.EN.7.24.11 | Final Issue for Design/ Construction-Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0360, HE-PR-1010, HE-TS-0050, HE-PR-0090, HE-PR-1220, HE-PI-0140, HE-TS-220 | HE-PI-0360: FS, HE-PR-1010: FS, HE-TS-0050: FS, HE-PR-0090: FS, HE-PR-1220: FS, HE-PI-0140: FS, HE-TS-220: FS | HE-HS-0290, CAB-4440, HE-PI-0640, HE-CO-200, C-56-PL-607-PI-1000, C-56-G-HT-PI-1000 | HE-HS-0290: FF, CAB-4440: FS, HE-PI-0640: FF, HE-CO-200: FS, C-56-PL-607-PI-1000: FS, C-56-G-HT-PI-1000: FS | 2024-08-16 07:30 | 2024-11-01 17:30
HE-PI-0340 | Completed | P2543-R01-Oct24..1.EN.7.24.11 | Re-Issue for HAZOP Studies- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-1250, HE-PR-0060, HE-PI-0330, HE-GS-0010, HE-TS-0010, HE-PI-0240, HE-TS-230, HE-GS-140 | HE-PR-1250: FS, HE-PR-0060: FS, HE-PI-0330: FS, HE-GS-0010: FS, HE-TS-0010: FS, HE-PI-0240: FS, HE-TS-230: FS, HE-GS-140: FS | HE-PI-0350, ML1012-B06 | HE-PI-0350: FS, ML1012-B06: FS | 2023-11-10 | 2023-11-15
HE-PI-0440 | In Progress | P2543-R01-Oct24..1.EN.7.24.13 | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | HE-PR-1010, HE-TS-0050, HE-PI-0430, HE-PR-0090, HE-PR-1220, HE-TS-270 | HE-PR-1010: FS, HE-TS-0050: FS, HE-PI-0430: FS, HE-PR-0090: FS, HE-PR-1220: FS, HE-TS-270: FS | ML1179-B11, HE-CS-0770, HE-PI-0700, HE-PL-2610, HE-HS-0290, CAB-4440, HE-CO-200, C-52-PR-839-PI-1000, C-52-D-HT-PI-1000 | ML1179-B11: FS, HE-CS-0770: FF, HE-PI-0700: FF, HE-PL-2610: FF 10, HE-HS-0290: FF, CAB-4440: FS, HE-CO-200: FS, C-52-PR-839-PI-1000: FS, C-52-D-HT-PI-1000: FS | 2024-08-16 07:30 | 2024-11-01 17:30
HE-PI-0410 | Completed | P2543-R01-Oct24..1.EN.7.24.13 | Re-Issue for HAZOP Studies- Overall Plot Plan - 52" Pipeline SWEIHAN CRS | HE-PR-1250, HE-PR-0060, HE-PI-0400 | HE-PR-1250: FS, HE-PR-0060: FS, HE-PI-0400: FS | HE-PI-0420, ML1012-B06 | HE-PI-0420: FS, ML1012-B06: FS | 2023-10-30 | 2023-11-07
HE-PI-0390 | Completed | P2543-R01-Oct24..1.EN.7.24.13 | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | HE-PR-0040, HE-PR-1240, HE-PR-0050, HE-PR-1040 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-0050: FS, HE-PR-1040: FS | HE-PI-0460, HE-PL-2570, HE-PR-0970, HE-PL-2630, HE-WS-0030, HE-PI-0400, HE-WS-0050, HE-PI-0130, HE-CS-0730, HC-GN-0250, HE-WS-0090, HE-PI-0320 | HE-PI-0460: SS, HE-PL-2570: FS, HE-PR-0970: FS, HE-PL-2630: FS, HE-WS-0030: FS, HE-PI-0400: FS, HE-WS-0050: FS, HE-PI-0130: FS, HE-CS-0730: FS, HC-GN-0250: FS, HE-WS-0090: FS, HE-PI-0320: SS 5 | 2023-09-20 | 2023-09-27
HE-PI-0400 | Completed | P2543-R01-Oct24..1.EN.7.24.13 | Receive Company Comments- Overall Plot Plan - 52" Pipeline SWEIHAN CRS | HE-PI-0390 | HE-PI-0390: FS | HE-PI-0410, HE-WS-0020 | HE-PI-0410: FS, HE-WS-0020: FS | 2023-10-02 | 2023-10-13
HE-PI-0420 | Completed | P2543-R01-Oct24..1.EN.7.24.13 | Re-Issue after incorporating HAZOP /Review Comments - 52" Pipeline SWEIHAN CRS | HE-PI-0410, HE-PR-0070, HE-TS-0010, HE-PR-1200 | HE-PI-0410: FS, HE-PR-0070: FS, HE-TS-0010: FS, HE-PR-1200: FS | HE-CS-1270, HE-PI-0430, HE-PI-0660, HE-HS-0250, HE-CS-1030, HE-PI-0490 | HE-CS-1270: FS, HE-PI-0430: FS, HE-PI-0660: FS, HE-HS-0250: FS, HE-CS-1030: FS, HE-PI-0490: SS | 2023-11-08 | 2023-11-22
HE-PI-0430 | Completed | P2543-R01-Oct24..1.EN.7.24.13 | Obtain Company Approval- Overall Plot Plan - 52" Pipeline SWEIHAN CRS | HE-PI-0420 | HE-PI-0420: FS | HE-PI-0440 | HE-PI-0440: FS | 2024-01-09 | 2024-01-23
HE-PI-0460 | Completed | P2543-R01-Oct24..1.EN.7.24.14 | Issue ICR- Overall Plot Plan - 4" N2 Source Pipeline | HE-PI-0390, HE-PR-0040, HE-PR-1240, HE-PI-0320 | HE-PI-0390: SS, HE-PR-0040: FS, HE-PR-1240: FS, HE-PI-0320: SS 5 | HE-PL-3580, HE-PI-0530, HE-PI-0470, HE-PL-2690, HE-WS-0030, HE-PI-0130, HE-WS-0050, HC-GN-0250, HE-WS-0090 | HE-PL-3580: FS, HE-PI-0530: SS 5, HE-PI-0470: FS, HE-PL-2690: FS, HE-WS-0030: FS, HE-PI-0130: FS, HE-WS-0050: FS, HC-GN-0250: FS, HE-WS-0090: FS | 2023-09-15 | 2023-09-28
HE-PI-0470 | Completed | P2543-R01-Oct24..1.EN.7.24.14 | Receive Company Comments- Overall Plot Plan - 4" N2 Source Pipeline | HE-PI-0460 | HE-PI-0460: FS | HE-PI-0480, HE-WS-0020 | HE-PI-0480: FS, HE-WS-0020: FS | 2023-10-02 | 2023-10-13
HE-PI-0510 | In Progress | P2543-R01-Oct24..1.EN.7.24.14 | Final Issue for Design/ Construction-Overall Plot Plan- 4" N2 Source Pipeline | HE-PR-0090, HE-PR-1010, HE-PI-0500, HE-TS-0050, HE-PR-1220, HE-TS-320 | HE-PR-0090: FS, HE-PR-1010: FS, HE-PI-0500: FS, HE-TS-0050: FS, HE-PR-1220: FS, HE-TS-320: FS | HC-GN-0290, HE-PI-0760, CAB-4440, HE-HS-0290, HE-CO-200, C-4N-H5-TPL-PI-1000, C-4N-HG-TPR-PI-1000 | HC-GN-0290: FS, HE-PI-0760: FS, CAB-4440: FS, HE-HS-0290: FF, HE-CO-200: FS, C-4N-H5-TPL-PI-1000: FS, C-4N-HG-TPR-PI-1000: FS | 2024-08-16 07:30 | 2024-11-01 17:30
HE-PI-0490 | Completed | P2543-R01-Oct24..1.EN.7.24.14 | Re-Issue after incorporating HAZOP /Review Comments - 4" N2 Source Pipeline | HE-PR-0070, HE-TS-0010, HE-PI-0480, HE-PI-0420, HE-PR-1200, HE-TS-330 | HE-PR-0070: FS, HE-TS-0010: FS, HE-PI-0480: FS, HE-PI-0420: SS, HE-PR-1200: FS, HE-TS-330: FS | HE-PI-0500, HE-CS-1030, HE-CS-1270, HE-PI-0720, HE-HS-0250 | HE-PI-0500: FS, HE-CS-1030: FS, HE-CS-1270: FS, HE-PI-0720: FS, HE-HS-0250: FS | 2023-11-08 | 2023-11-22
HE-PI-0500 | Completed | P2543-R01-Oct24..1.EN.7.24.14 | Obtain Company Approval- Overall Plot Plan - 4" N2 Source Pipeline | HE-PI-0490 | HE-PI-0490: FS | HE-PI-0510 | HE-PI-0510: FS | 2024-04-30 07:30 | 2024-05-10 17:30
HE-PI-0480 | Completed | P2543-R01-Oct24..1.EN.7.24.14 | Re-Issue for HAZOP Studies- Overall Plot Plan - 4" N2 Source Pipeline | HE-PR-1250, HE-PI-0470, HE-PR-0060 | HE-PR-1250: FS, HE-PI-0470: FS, HE-PR-0060: FS | ML1012-B06, HE-PI-0490 | ML1012-B06: FS, HE-PI-0490: FS | 2023-10-30 | 2023-11-07
HE-PI-0560 | Completed | P2543-R01-Oct24..1.EN.7.24.22 | Re-Issue after incorporating HAZOP / Review Comments- Plot plan - BVS | HE-PI-0550, HE-TS-0010, HE-PR-0070, HE-PR-1200 | HE-PI-0550: FS, HE-TS-0010: FS, HE-PR-0070: FS, HE-PR-1200: FS | HE-EL-1630, HE-EL-1570, HE-PI-0570, HE-CS-0910, HE-HS-0250, HE-PI-0840, HE-PI-0780 | HE-EL-1630: FS, HE-EL-1570: FS, HE-PI-0570: FS, HE-CS-0910: FS, HE-HS-0250: FS, HE-PI-0840: FS, HE-PI-0780: FS | 2023-11-08 | 2023-11-22
HE-PI-0570 | Completed | P2543-R01-Oct24..1.EN.7.24.22 | Obtain Company Approval- Plot plan - BVS | HE-PI-0560 | HE-PI-0560: FS | HE-PI-0580, HE-CS-0430 | HE-PI-0580: FS, HE-CS-0430: FS | 2024-01-15 | 2024-01-22
HE-PI-0550 | Completed | P2543-R01-Oct24..1.EN.7.24.22 | Re-Issue for HAZOP Studies- Plot plan - BVS | HE-PR-1250, HE-PI-0540, HE-PR-0060 | HE-PR-1250: FS, HE-PI-0540: FS, HE-PR-0060: FS | HE-PI-0560, HE-PI-0840, ML1012-B06 | HE-PI-0560: FS, HE-PI-0840: FS, ML1012-B06: FS | 2023-10-30 | 2023-11-07
HE-PI-0580 | In Progress | P2543-R01-Oct24..1.EN.7.24.22 | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | HE-PR-0090, HE-PI-0570, HE-TS-0050, HE-PR-1010, HE-PR-1220 | HE-PR-0090: FS, HE-PI-0570: FS, HE-TS-0050: FS, HE-PR-1010: FS, HE-PR-1220: FS | HE-PI-0880, ML1179-B11, CAB-4440, HE-PI-0820, HC-GN-0290, HE-HS-0290, HE-CO-200, C-56-591-01-PI-1000, C-52-598-06-PI-1000, C-52-598-05-PI-1000, C-52-598-04-PI-1000, C-52-598-03-PI-1000, C-52-598-02-PI-1000, C-52-598-01-PI-1000 | HE-PI-0880: FF, ML1179-B11: FS, CAB-4440: FS, HE-PI-0820: FF, HC-GN-0290: FS, HE-HS-0290: FF, HE-CO-200: FS, C-56-591-01-PI-1000: FS, C-52-598-06-PI-1000: FS, C-52-598-05-PI-1000: FS, C-52-598-04-PI-1000: FS, C-52-598-03-PI-1000: FS, C-52-598-02-PI-1000: F | 2024-08-16 07:30 | 2024-11-01 17:30
HE-PI-0530 | Completed | P2543-R01-Oct24..1.EN.7.24.22 | Issue ICR- Plot plan - BVS | HE-PI-0460, HE-PR-0040, HE-PR-1240 | HE-PI-0460: SS 5, HE-PR-0040: FS, HE-PR-1240: FS | HE-EL-0070, HC-GN-0250, HE-PI-0540, HE-WS-0050, HE-WS-0030, HE-CS-1150, HE-WS-0090, HE-CS-1090 | HE-EL-0070: FS, HC-GN-0250: FS, HE-PI-0540: FS, HE-WS-0050: FS, HE-WS-0030: FS, HE-CS-1150: FS, HE-WS-0090: FS, HE-CS-1090: FS | 2023-09-15 | 2023-09-28
HE-PI-0540 | Completed | P2543-R01-Oct24..1.EN.7.24.22 | Receive Company Comments- Plot plan - BVS | HE-PI-0530 | HE-PI-0530: FS | HE-PI-0550, HE-WS-0020 | HE-PI-0550: FS, HE-WS-0020: FS | 2023-10-02 | 2023-10-13
HE-ME-0020 | Completed | P2543-R01-Oct24..1.EN.5.12 | Receive Company Comments- Addendum to DGS | HE-ME-0010 | HE-ME-0010: FS | HE-ME-0030 | HE-ME-0030: FS | 2023-10-01 | 2023-10-06
HE-ME-0030 | Completed | P2543-R01-Oct24..1.EN.5.12 | Re-Issue for Approval- Addendum to DGS | HE-ME-0020 | HE-ME-0020: FS | HE-ME-0040 | HE-ME-0040: FS | 2023-10-07 | 2023-10-14
HE-ME-0040 | Completed | P2543-R01-Oct24..1.EN.5.12 | Obtain Company Approval- Addendum to DGS | HE-ME-0030 | HE-ME-0030: FS | HE-ME-0050 | HE-ME-0050: FS | 2023-10-15 | 2023-10-21
HE-ME-0050 | Completed | P2543-R01-Oct24..1.EN.5.12 | Final Issue for Design/ Construction- Addendum to DGS | HE-ME-0040, HE-ME-260 | HE-ME-0040: FS, HE-ME-260: FS | HE-ME-0110, HE-ME-0170, CAB-4430, HE-PR-0470, HE-ME-520, HE-ME-610 | HE-ME-0110: FS, HE-ME-0170: FS, CAB-4430: FS, HE-PR-0470: FS, HE-ME-520: FS, HE-ME-610: FS | 2023-10-22 | 2023-10-27
HE-ME-0010 | Completed | P2543-R01-Oct24..1.EN.5.12 | Issue ICR- Addendum to DGS | HE-ME-270, ML1002 | HE-ME-270: FS, ML1002: SS | HE-ME-0070, HP-ME-0860, HE-ME-0020, HE-ME-0130, HE-ME-480, HE-ME-620 | HE-ME-0070: FS, HP-ME-0860: FS, HE-ME-0020: FS, HE-ME-0130: SS 5, HE-ME-480: SS, HE-ME-620: SS 10 | 2023-09-01 | 2023-09-23
HE-ME-0090 | Completed | P2543-R01-Oct24..1.EN.5.2.5 | Re-Issue for Approval-Datasheet for Sales Gas CRS Filters | HE-ME-0080, HE-HS-0670 | HE-ME-0080: FS, HE-HS-0670: FS | HE-ME-0150, HE-ME-0100, HE-ME-500 | HE-ME-0150: FS, HE-ME-0100: FS, HE-ME-500: FS | 2023-10-03 | 2023-10-20
HE-ME-0100 | Completed | P2543-R01-Oct24..1.EN.5.2.5 | Obtain Company Approval-Datasheet for Sales Gas CRS Filters | HE-ME-0090 | HE-ME-0090: FS | HE-ME-0110 | HE-ME-0110: FS | 2023-11-07 | 2023-11-14
HE-ME-0110 | Completed | P2543-R01-Oct24..1.EN.5.2.5 | Final Issue for Design/ Construction-Datasheet for Sales Gas CRS Filters | HE-ME-0050, HE-PR-0470, HE-ME-0100, HE-ME-260, HE-IC-610 | HE-ME-0050: FS, HE-PR-0470: SS, HE-ME-0100: FS, HE-ME-260: FS, HE-IC-610: FS | CAB-4430, ML1015-B08, HE-ME-0170 | CAB-4430: FS, ML1015-B08: FF, HE-ME-0170: FS | 2024-01-10 | 2024-01-24
HE-ME-0070 | Completed | P2543-R01-Oct24..1.EN.5.2.5 | Issue ICR-Datasheet for Sales Gas CRS Filters | HE-ME-0010, HE-PR-0430, HE-ME-270, HE-IC-620, HE-PR-0440 | HE-ME-0010: FS, HE-PR-0430: FS, HE-ME-270: SS, HE-IC-620: SS, HE-PR-0440: FS | HE-ME-0080, HE-ME-0130, HE-ME-480 | HE-ME-0080: FS, HE-ME-0130: FS, HE-ME-480: SS | 2023-09-02 | 2023-09-13
HE-ME-0080 | Completed | P2543-R01-Oct24..1.EN.5.2.5 | Receive Company Comments-Datasheet for Sales Gas CRS Filters | HE-ME-0070 | HE-ME-0070: FS | HE-ME-0090 | HE-ME-0090: FS | 2023-09-14 | 2023-10-02
HE-ME-0130 | Completed | P2543-R01-Oct24..1.EN.5.6.7 | Issue ICR-Material Requisitions for Sales Gas CRS Filters | HE-ME-0070, HE-ME-0010, HE-ME-270, HE-IC-620 | HE-ME-0070: FS, HE-ME-0010: SS 5, HE-ME-270: SS, HE-IC-620: SS | HP-ME-0160, HE-ME-0140 | HP-ME-0160: FS, HE-ME-0140: FS | 2023-10-09 | 2023-10-19
HE-ME-0140 | Completed | P2543-R01-Oct24..1.EN.5.6.7 | Receive Company Comments-Material Requisitions for Sales Gas CRS Filters | HE-ME-0130 | HE-ME-0130: FS | HE-ME-0150 | HE-ME-0150: FS | 2023-10-30 | 2023-11-09
HE-ME-0150 | Completed | P2543-R01-Oct24..1.EN.5.6.7 | Re-Issue for Approval-Material Requisitions for Sales Gas CRS Filters | HE-ME-0090, HE-ME-0140 | HE-ME-0090: FS, HE-ME-0140: FS | HE-ME-0160 | HE-ME-0160: FS | 2024-02-26 | 2024-03-05
HE-ME-0160 | Completed | P2543-R01-Oct24..1.EN.5.6.7 | Obtain Company Approval-Material Requisitions for Sales Gas CRS Filters | HE-ME-0150 | HE-ME-0150: FS | HE-ME-0170 | HE-ME-0170: FS | 2024-03-06 | 2024-03-14
HE-ME-0170 | Completed | P2543-R01-Oct24..1.EN.5.6.7 | Final Issue for Design/ Construction-Material Requisitions for Sales Gas CRS Filters | HE-ME-0050, HE-ME-0160, HE-ME-0110, HE-ME-260, HE-IC-610 | HE-ME-0050: FS, HE-ME-0160: FS, HE-ME-0110: FS, HE-ME-260: FS, HE-IC-610: FS | CAB-4430, ML1017-B18, HM-ME-0320 | CAB-4430: FS, ML1017-B18: FS, HM-ME-0320: FS | 2024-03-15 | 2024-03-28
HE-ME-0190 | Completed | P2543-R01-Oct24..1.EN.5.3.9 | Issue ICR-TBEs for Sales Gas CRS Filters | HP-ME-0160 | HP-ME-0160: FS | HE-ME-0200, HP-ME-0170 | HE-ME-0200: FS, HP-ME-0170: SS | 2023-12-04 | 2023-12-08
HE-ME-0200 | Completed | P2543-R01-Oct24..1.EN.5.3.9 | Receive Company Comments-TBEs for Sales Gas CRS Filters | HE-ME-0190 | HE-ME-0190: FS | HE-ME-0210 | HE-ME-0210: FS | 2023-12-29 | 2024-01-09
HE-ME-0210 | Completed | P2543-R01-Oct24..1.EN.5.3.9 | Re-Issue for Approval-TBEs for Sales Gas CRS Filters | HE-ME-0200 | HE-ME-0200: FS | HE-ME-0220 | HE-ME-0220: FS | 2024-01-10 | 2024-01-29
HE-ME-0220 | Completed | P2543-R01-Oct24..1.EN.5.3.9 | Obtain Company Approval-TBEs for Sales Gas CRS Filters | HE-ME-0210 | HE-ME-0210: FS | HP-ME-0180, HE-ME-0230, HP-ME-0170 | HP-ME-0180: FS, HE-ME-0230: FS, HP-ME-0170: FF | 2024-01-31 | 2024-02-12
HE-ME-0230 | Completed | P2543-R01-Oct24..1.EN.5.3.9 | Final Issue for Design/ Construction-TBEs for Sales Gas CRS Filters | HE-ME-0220 | HE-ME-0220: FS | HP-ME-0180, CAB-4430 | HP-ME-0180: SS, CAB-4430: FS | 2024-02-13 | 2024-03-04
HE-CS-1330 | Completed | P2543-R01-Oct24..1.EN.8.40 | Issued for Review - Typical Structural Steel and Foundation details for pipe support | HE-PI-1160, HE-CS-1090 | HE-PI-1160: SS, HE-CS-1090: FF | HE-CS-1450, HE-CS-1340 | HE-CS-1450: SS, HE-CS-1340: FS | 2024-02-10 | 2024-02-16
HE-CS-1340 | Completed | P2543-R01-Oct24..1.EN.8.40 | Review Company Comments - Typical Structural Steel and Foundation details for pipe support | HE-CS-1330 | HE-CS-1330: FS | HE-CS-1350 | HE-CS-1350: FS | 2024-03-31 | 2024-04-18
HE-CS-1350 | Completed | P2543-R01-Oct24..1.EN.8.40 | Re-Issue for Approval - Typical Structural Steel and Foundation details for pipe support | HE-CS-1340 | HE-CS-1340: FS | HE-CS-1360 | HE-CS-1360: FS | 2024-04-19 | 2024-08-02 17:30
HE-CS-1360 | Completed | P2543-R01-Oct24..1.EN.8.40 | Obtain Company Approval - Typical Structural Steel and Foundation details for pipe support | HE-CS-1350 | HE-CS-1350: FS | HE-CS-1370 | HE-CS-1370: FS | 2024-09-30 07:30 | 2024-10-11 17:30
HE-CS-1370 | In Progress | P2543-R01-Oct24..1.EN.8.40 | Final Issue for Design/ Construction-Typical Structural Steel and Foundation details for pipe support | HE-CS-1360 | HE-CS-1360: FS | HE-CS-1550, CAB-4420, C-52-598-06-CI-1420, C-52-598-05-CI-1420, C-52-598-04-CI-1420, C-52-598-03-CI-1420, C-52-598-02-CI-1420, C-52-598-01-CI-1420, C-52-PR-839-CI-1420 | HE-CS-1550: FS, CAB-4420: FS, C-52-598-06-CI-1420: FS, C-52-598-05-CI-1420: FS, C-52-598-04-CI-1420: FS, C-52-598-03-CI-1420: FS, C-52-598-02-CI-1420: FS, C-52-598-01-CI-1420: FS, C-52-PR-839-CI-1420: FS | 2024-10-11 07:30 | 2024-11-01 17:30
HE-CS-1420 | Not Started | P2543-R01-Oct24..1.EN.8.38 | Obtain Company Approval - Pipe Sleeper layout and details. | HE-CS-1410 | HE-CS-1410: FS | HE-CS-1430 | HE-CS-1430: FS | 2024-11-25 07:30 | 2024-12-10 17:30
HE-CS-1430 | Not Started | P2543-R01-Oct24..1.EN.8.38 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | HE-PI-1180, HE-CS-1420 | HE-PI-1180: FS, HE-CS-1420: FS | CAB-4420, ML1034-B25, ML1209-B27, C-56-PL-607-CI-2000, C-56-G-HT-CI-2000, C-56-PR-838-CI-2000, C-56-591-01-CI-2000, C-52-598-06-CI-2000, C-52-598-05-CI-2000, C-52-598-04-CI-2000, C-52-598-03-CI-2000, C-52-598-02-CI-2000, C-52-598-01-CI-2000, C-52-PR-839-CI | CAB-4420: FS, ML1034-B25: FS, ML1209-B27: FS, C-56-PL-607-CI-2000: FS, C-56-G-HT-CI-2000: FS, C-56-PR-838-CI-2000: FS, C-56-591-01-CI-2000: FS, C-52-598-06-CI-2000: FS, C-52-598-05-CI-2000: FS, C-52-598-04-CI-2000: FS, C-52-598-03-CI-2000: FS, C-52-598-02- | 2024-12-11 07:30 | 2024-12-17 17:30
HE-CS-1390 | Not Started | P2543-R01-Oct24..1.EN.8.38 | Issued for Review - Pipe Sleeper layout and details. | HE-PI-1160 | HE-PI-1160: FS | HE-CS-1400 | HE-CS-1400: FS | 2024-10-28 07:30 | 2024-11-01 17:30
HE-CS-1400 | Not Started | P2543-R01-Oct24..1.EN.8.38 | Review Company Comments - Pipe Sleeper layout and details. | HE-CS-1390 | HE-CS-1390: FS | HE-CS-1410 | HE-CS-1410: FS | 2024-11-04 07:30 | 2024-11-15 17:30
HE-CS-1410 | Not Started | P2543-R01-Oct24..1.EN.8.38 | Re-Issue for Approval - Pipe Sleeper layout and details. | HE-CS-1400 | HE-CS-1400: FS | HE-CS-1420, HE-CS-1550 | HE-CS-1420: FS, HE-CS-1550: FS | 2024-11-18 07:30 | 2024-11-22 17:30
HE-CS-1450 | Completed | P2543-R01-Oct24..1.EN.8.41 | Issued for Review - Misc. supports and civil/ structural details | HE-CS-1330, HE-PI-1160 | HE-CS-1330: SS, HE-PI-1160: FS | HE-CS-1460 | HE-CS-1460: FS | 2024-03-01 | 2024-03-08
HE-CS-1460 | Completed | P2543-R01-Oct24..1.EN.8.41 | Review Company Comments - Misc. supports and civil/ structural details | HE-CS-1450 | HE-CS-1450: FS | HE-CS-1470 | HE-CS-1470: FS | 2024-03-11 | 2024-03-21
HE-CS-1470 | Completed | P2543-R01-Oct24..1.EN.8.41 | Re-Issue for Approval - Misc. supports and civil/ structural details | HE-CS-1460 | HE-CS-1460: FS | HE-CS-1480 | HE-CS-1480: FS | 2024-03-22 | 2024-05-03
HE-CS-1480 | Completed | P2543-R01-Oct24..1.EN.8.41 | Obtain Company Approval - Misc. supports and civil/ structural details | HE-CS-1470 | HE-CS-1470: FS | HE-CS-1490 | HE-CS-1490: FS | 2024-09-30 07:30 | 2024-10-07 17:30
HE-CS-1490 | Not Started | P2543-R01-Oct24..1.EN.8.41 | Final Issue for Design/ Construction-Misc. supports | HE-CS-1480, HE-PI-1180 | HE-CS-1480: FS, HE-PI-1180: FS | CAB-4420, C-56-PL-607-CI-2000, C-56-G-HT-CI-2000, C-56-PR-838-CI-2000, C-56-591-01-CI-2000, C-52-598-06-CI-2000, C-52-598-05-CI-2000, C-52-598-04-CI-2000, C-52-598-03-CI-2000, C-52-598-02-CI-2000, C-52-598-01-CI-2000, C-52-PR-839-CI-2000, C-52-D-HT-CI-2000 | CAB-4420: FS, C-56-PL-607-CI-2000: FS, C-56-G-HT-CI-2000: FS, C-56-PR-838-CI-2000: FS, C-56-591-01-CI-2000: FS, C-52-598-06-CI-2000: FS, C-52-598-05-CI-2000: FS, C-52-598-04-CI-2000: FS, C-52-598-03-CI-2000: FS, C-52-598-02-CI-2000: FS, C-52-598-01-CI-2000 | 2024-11-18 07:30 | 2024-11-22 17:30
HE-CS-1550 | Not Started | P2543-R01-Oct24..1.EN.8.42 | Issued - Civil MTO 2 | HE-CS-0830, HE-CS-0470, HE-CS-0230, HE-CS-0170, HE-CS-0530, HE-CS-1010, HE-CS-0650, HE-CS-1370, HE-CS-0770, HE-CS-1070, HE-CS-1310, HE-CS-0110, HE-CS-0290, HE-CS-1250, HE-CS-0410, HE-CS-1190, HE-CS-0350, HE-CS-1510, HE-CS-1410 | HE-CS-0830: FS, HE-CS-0470: FS, HE-CS-0230: FS, HE-CS-0170: FS, HE-CS-0530: FS, HE-CS-1010: FF, HE-CS-0650: FS, HE-CS-1370: FS, HE-CS-0770: FS, HE-CS-1070: FS, HE-CS-1310: FS, HE-CS-0110: FS, HE-CS-0290: FS, HE-CS-1250: FS, HE-CS-0410: FS, HE-CS-1190: FS, | CAB-4420, HP-BK-0270, HP-BK-0310 | CAB-4420: FS, HP-BK-0270: FF, HP-BK-0310: FS | 2024-12-04 07:30 | 2024-12-10 17:30
HE-CS-1510 | Completed | P2543-R01-Oct24..1.EN.8.42 | Issued - Civil MTO 1 | HE-PI-0130 | HE-PI-0130: FS | HP-BK-0300, HP-BK-0260, HE-CS-1550 | HP-BK-0300: FS, HP-BK-0260: FS, HE-CS-1550: FS | 2024-03-29 07:30 | 2024-04-09 17:30
HE-CS-0010 | Completed | P2543-R01-Oct24..1.EN.8.1 | Issued for Review - Addendum to DGs | HE-DB-0010 | HE-DB-0010: FS | HE-BL-1000, HE-CS-0110, HE-CS-0070, HE-CS-0020 | HE-BL-1000: FS, HE-CS-0110: FS, HE-CS-0070: FS, HE-CS-0020: FS | 2023-08-07 | 2023-10-06
HE-CS-0020 | Completed | P2543-R01-Oct24..1.EN.8.1 | Review Company Comments - Addendum to DGs | HE-CS-0010 | HE-CS-0010: FS | HE-CS-0030, HE-CS-0070 | HE-CS-0030: FS, HE-CS-0070: FS | 2023-10-09 | 2023-10-20
HE-CS-0030 | Completed | P2543-R01-Oct24..1.EN.8.1 | Re-Issue for Approval - Addendum to DGs | HE-CS-0020 | HE-CS-0020: FS | HE-CS-0040 | HE-CS-0040: FS | 2023-10-23 | 2023-11-10
HE-CS-0040 | Completed | P2543-R01-Oct24..1.EN.8.1 | Obtain Company Approval - Addendum to DGs | HE-CS-0030 | HE-CS-0030: FS | HE-CS-0050, HE-EL-0850 | HE-CS-0050: FS, HE-EL-0850: FS 10 | 2023-11-13 | 2023-11-24
HE-CS-0050 | Completed | P2543-R01-Oct24..1.EN.8.1 | Final Issue for Design/ Construction-Addendum to DGs | HE-CS-0040, HE-CS-1600 | HE-CS-0040: FS, HE-CS-1600: FS | HE-CS-0110, HE-EL-0890, CAB-4420, HE-CS-0110 | HE-CS-0110: FS, HE-EL-0890: FS, CAB-4420: FS, HE-CS-0110: FF | 2023-11-27 | 2023-12-25
HE-CS-0070 | Completed | P2543-R01-Oct24..1.EN.8.9 | Issued for Review - Standard drawings for Anchor bolt | HE-CS-0010, HE-CS-1560, HE-CS-0020 | HE-CS-0010: FS, HE-CS-1560: FS, HE-CS-0020: FS | HE-CS-0080 | HE-CS-0080: FS | 2024-04-06 | 2024-04-19 17:30
HE-CS-0080 | Completed | P2543-R01-Oct24..1.EN.8.9 | Review Company Comments - Standard drawings for Anchor bolt | HE-CS-0070 | HE-CS-0070: FS | HE-CS-0090 | HE-CS-0090: FS | 2024-04-22 07:30 | 2024-05-06 17:30
HE-CS-0090 | Completed | P2543-R01-Oct24..1.EN.8.9 | Re-Issue for Approval - Standard drawings for Anchor bolt | HE-CS-0080 | HE-CS-0080: FS | HE-CS-0100 | HE-CS-0100: FS | 2024-05-07 07:30 | 2024-05-31 17:30
HE-CS-0100 | Completed | P2543-R01-Oct24..1.EN.8.9 | Obtain Company Approval - Standard drawings for Anchor bolt | HE-CS-0090 | HE-CS-0090: FS | HE-CS-0110 | HE-CS-0110: FS | 2024-06-21 07:30 | 2024-07-09 17:30
HE-CS-0110 | In Progress | P2543-R01-Oct24..1.EN.8.9 | Final Issue for Design/ Construction-Standard drawings for Anchor bolt | HE-CS-0010, HE-CS-0050, HE-CS-0100, HE-CS-0050, HE-CS-1600, HE-CS-1600 | HE-CS-0010: FS, HE-CS-0050: FS, HE-CS-0100: FS, HE-CS-0050: FF, HE-CS-1600: FS, HE-CS-1600: FF | ML1034-B25, ML1209-B27, ML1035-B26, HE-CS-1550, CAB-4420 | ML1034-B25: FS, ML1209-B27: FS, ML1035-B26: FS, HE-CS-1550: FS, CAB-4420: FS | 2024-08-23 07:30 | 2024-11-08 17:30
HE-CS-0130 | Completed | P2543-R01-Oct24..1.EN.8.14 | Issued for Review - Typical trench detail drawing | HE-PL-0070 | HE-PL-0070: FS | HE-CS-0190, HE-CS-0140 | HE-CS-0190: FS, HE-CS-0140: FS | 2023-10-27 | 2023-11-10
HE-CS-0140 | Completed | P2543-R01-Oct24..1.EN.8.14 | Review Company Comments - Typical trench detail drawing | HE-CS-0130 | HE-CS-0130: FS | HE-CS-0150 | HE-CS-0150: FS | 2023-11-13 | 2023-12-01
HE-CS-0150 | Completed | P2543-R01-Oct24..1.EN.8.14 | Re-Issue for Approval - Typical trench detail drawing | HE-CS-0140 | HE-CS-0140: FS | HE-CS-0160 | HE-CS-0160: FS | 2023-12-01 | 2023-12-01
HE-CS-0160 | Completed | P2543-R01-Oct24..1.EN.8.14 | Obtain Company Approval - Typical trench detail drawing | HE-CS-0150 | HE-CS-0150: FS | HE-CS-0170 | HE-CS-0170: FS | 2023-12-01 | 2023-12-01
HE-CS-0170 | Completed | P2543-R01-Oct24..1.EN.8.14 | Final Issue for Design/ Construction-Typical trench detail drawing | HE-CS-0160 | HE-CS-0160: FS | HE-CS-1550, ML1034-B25, ML1209-B27, CAB-4420, ML1032-B21, C-COM-750, ML1035-B26, HE-CS-0230, C-56-PL-607-CI-1000, C-56-EB2-CI-1000, C-56-G-HT-CI-1000, C-56-PR-838-CI-1000, C-56-591-01-CI-1000, C-52-598-06-CI-1000, C-52-598-05-CI-1000, C-52-598-04-CI-1000, | HE-CS-1550: FS, ML1034-B25: FS, ML1209-B27: FS, CAB-4420: FS, ML1032-B21: FS, C-COM-750: FS, ML1035-B26: FS, HE-CS-0230: FS, C-56-PL-607-CI-1000: FS, C-56-EB2-CI-1000: FS, C-56-G-HT-CI-1000: FS, C-56-PR-838-CI-1000: FS, C-56-591-01-CI-1000: FS, C-52-598-06 | 2023-12-04 | 2023-12-15
HE-CS-0190 | Completed | P2543-R01-Oct24..1.EN.8.13 | Issued for Review - Typical duct bank detail drawing | HE-CS-0130 | HE-CS-0130: FS | HE-CS-0250, HE-CS-0370, HE-CS-0200 | HE-CS-0250: FS, HE-CS-0370: FS, HE-CS-0200: FS | 2023-08-23 | 2023-08-31
HE-CS-0200 | Completed | P2543-R01-Oct24..1.EN.8.13 | Review Company Comments - Typical duct bank detail drawing | HE-CS-0190 | HE-CS-0190: FS | HE-CS-0210 | HE-CS-0210: FS | 2023-09-01 | 2023-09-07
HE-CS-0210 | Completed | P2543-R01-Oct24..1.EN.8.13 | Re-Issue for Approval - Typical duct bank detail drawing | HE-CS-0200 | HE-CS-0200: FS | HE-CS-0220 | HE-CS-0220: FS | 2023-09-08 | 2023-09-15
HE-CS-0220 | Completed | P2543-R01-Oct24..1.EN.8.13 | Obtain Company Approval - Typical duct bank detail drawing | HE-CS-0210 | HE-CS-0210: FS | HE-CS-0230 | HE-CS-0230: FS | 2023-09-16 | 2023-09-26
HE-CS-0230 | Completed | P2543-R01-Oct24..1.EN.8.13 | Final Issue for Design/ Construction-Typical duct bank detail drawing | HE-CS-0220, HE-CS-0170 | HE-CS-0220: FS, HE-CS-0170: FS | HE-CS-1550, ML1034-B25, ML1035-B26, CAB-4420, C-COM-750, ML1209-B27, HP-BK-0260, HE-CS-0290, C-56-PL-607-CI-1400, C-56-PL-607-CI-1500, C-56-EB2-CI-1400, C-56-G-HT-CI-1600, C-56-PR-838-CI-1400, C-56-PR-838-CI-1410, C-56-PR-838-CI-1420, C-56-591-01-CI-1400, | HE-CS-1550: FS, ML1034-B25: FS, ML1035-B26: FS, CAB-4420: FS, C-COM-750: FS, ML1209-B27: FS, HP-BK-0260: FS, HE-CS-0290: FS, C-56-PL-607-CI-1400: FS, C-56-PL-607-CI-1500: FS, C-56-EB2-CI-1400: FF, C-56-G-HT-CI-1600: FS, C-56-PR-838-CI-1400: FS, C-56-PR-838 | 2023-09-27 | 2023-10-03
HE-CS-0250 | Completed | P2543-R01-Oct24..1.EN.8.15 | Issued for Review - Typical Road and paving detail drawing | HE-CS-0190 | HE-CS-0190: FS | HE-CS-0310, HE-CS-0260 | HE-CS-0310: FS, HE-CS-0260: FS | 2023-09-12 | 2023-09-26
HE-CS-0260 | Completed | P2543-R01-Oct24..1.EN.8.15 | Review Company Comments - Typical Road and paving detail drawing | HE-CS-0250 | HE-CS-0250: FS | HE-CS-0270 | HE-CS-0270: FS | 2023-09-27 | 2023-10-05
HE-CS-0270 | Completed | P2543-R01-Oct24..1.EN.8.15 | Re-Issue for Approval - Typical Road and paving detail drawing | HE-CS-0260 | HE-CS-0260: FS | HE-CS-0280 | HE-CS-0280: FS | 2023-10-06 | 2023-10-10
HE-CS-0280 | Completed | P2543-R01-Oct24..1.EN.8.15 | Obtain Company Approval - Typical Road and paving detail drawing | HE-CS-0270 | HE-CS-0270: FS | HE-CS-0290 | HE-CS-0290: FS | 2023-10-11 | 2023-10-15
HE-CS-0290 | Completed | P2543-R01-Oct24..1.EN.8.15 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | HE-CS-0280, HE-CS-0230 | HE-CS-0280: FS, HE-CS-0230: FS | ML1034-B25, ML1035-B26, ML1209-B27, HE-CS-1550, CAB-4420, C-COM-750, C-56-PL-607-CI-2600, C-56-EB2-CI-2010, C-56-G-HT-CI-2600, C-56-PR-838-CI-2600, C-56-591-01-CI-2600, C-52-598-06-CI-2600, C-52-598-05-CI-2600, C-52-598-03-CI-2600, C-52-598-02-CI-2600, C-5 | ML1034-B25: FS, ML1035-B26: FS, ML1209-B27: FS, HE-CS-1550: FS, CAB-4420: FS, C-COM-750: FS, C-56-PL-607-CI-2600: FS, C-56-EB2-CI-2010: FS, C-56-G-HT-CI-2600: FS, C-56-PR-838-CI-2600: FS, C-56-591-01-CI-2600: FS, C-52-598-06-CI-2600: FS, C-52-598-05-CI-260 | 2023-10-16 | 2023-10-18
HE-CS-0310 | Completed | P2543-R01-Oct24..1.EN.8.16 | Issued for Review - Typical Fence and gate detail drawing | HE-CS-0250 | HE-CS-0250: FS | HE-CS-0320 | HE-CS-0320: FS | 2023-08-24 | 2023-09-06
HE-CS-0320 | Completed | P2543-R01-Oct24..1.EN.8.16 | Review Company Comments - Typical Fence and gate detail drawing | HE-CS-0310 | HE-CS-0310: FS | HE-CS-0330 | HE-CS-0330: FS | 2023-09-07 | 2023-09-11
HE-CS-0330 | Completed | P2543-R01-Oct24..1.EN.8.16 | Re-Issue for Approval - Typical Fence and gate detail drawing | HE-CS-0320 | HE-CS-0320: FS | HE-CS-0340 | HE-CS-0340: FS | 2023-09-12 | 2023-09-22
HE-CS-0340 | Completed | P2543-R01-Oct24..1.EN.8.16 | Obtain Company Approval - Typical Fence and gate detail drawing | HE-CS-0330 | HE-CS-0330: FS | HE-CS-0350 | HE-CS-0350: FS | 2023-09-22 | 2023-09-27
HE-CS-0350 | Completed | P2543-R01-Oct24..1.EN.8.16 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | HE-CS-0340 | HE-CS-0340: FS | ML1035-B26, C-COM-750, ML1034-B25, ML1209-B27, CAB-4420, ML1034-B25, ML1209-B27, HE-CS-1550, ML1035-B26, C-56-PL-607-CI-2220, C-56-591-01-CI-2200, C-52-HG01-FENCE-1000, C-52-06CR-FENCE-1000, C-52-598-06-CI-2200, C-52-598-05-CI-2200, C-52-598-04-CI-2200, C- | ML1035-B26: FF, C-COM-750: FF, ML1034-B25: FS, ML1209-B27: FS, CAB-4420: FS, ML1034-B25: FF, ML1209-B27: FF, HE-CS-1550: FS, ML1035-B26: FS, C-56-PL-607-CI-2220: FS, C-56-591-01-CI-2200: FS, C-52-HG01-FENCE-1000: FS 90, C-52-06CR-FENCE-1000: FS 28, C-52-59 | 2023-09-28 | 2023-09-29
HE-CS-0370 | Completed | P2543-R01-Oct24..1.EN.8.17 | Issued for Review - Typical details of protection slab to protect existing UG pipe at road crossing | HE-CS-0190 | HE-CS-0190: FS | HE-CS-0380 | HE-CS-0380: FS | 2023-12-11 | 2024-03-15
HE-CS-0380 | Completed | P2543-R01-Oct24..1.EN.8.17 | Review Company Comments - Typical details of protection slab to protect existing UG pipe at road crossing | HE-CS-0370 | HE-CS-0370: FS | HE-CS-0390 | HE-CS-0390: FS | 2024-03-16 | 2024-03-29
HE-CS-0390 | Completed | P2543-R01-Oct24..1.EN.8.17 | Re-Issue for Approval - Typical details of protection slab to protect existing UG pipe at road crossing | HE-CS-0380 | HE-CS-0380: FS | HE-CS-0400 | HE-CS-0400: FS | 2024-03-30 | 2024-04-05
HE-CS-0400 | Completed | P2543-R01-Oct24..1.EN.8.17 | Obtain Company Approval - Typical details of protection slab to protect existing UG pipe at road crossing | HE-CS-0390 | HE-CS-0390: FS | HE-CS-0410 | HE-CS-0410: FS | 2024-04-06 | 2024-04-20
HE-CS-0410 | Completed | P2543-R01-Oct24..1.EN.8.17 | Final Issue for Design/ Construction-Typical details of protection slab to protect existing UG pipe at road crossing | HE-CS-0400 | HE-CS-0400: FS | ML1035-B26, HE-CS-1550, ML1209-B27, ML1034-B25, CAB-4420, CCV-52-KM-1120 | ML1035-B26: FS, HE-CS-1550: FS, ML1209-B27: FS, ML1034-B25: FS, CAB-4420: FS, CCV-52-KM-1120: FS | 2024-10-07 07:30 | 2024-10-14 17:30
HE-CS-0440 | Completed | P2543-R01-Oct24..1.EN.8.12 | Review Company Comments - Site grading, road, drainage and fence layout | HE-CS-0430 | HE-CS-0430: FS | HE-CS-0450 | HE-CS-0450: FS | 2024-07-18 07:30 | 2024-07-26 17:30
HE-CS-0450 | Completed | P2543-R01-Oct24..1.EN.8.12 | Re-Issue for Approval - Site grading, road, drainage and fence layout | HE-CS-0440 | HE-CS-0440: FS | HE-CS-0460 | HE-CS-0460: FS | 2024-09-02 07:30 | 2024-09-09 17:30
HE-CS-0460 | Completed | P2543-R01-Oct24..1.EN.8.12 | Obtain Company Approval - Site grading, road, drainage and fence layout | HE-CS-0450 | HE-CS-0450: FS | HE-CS-0470 | HE-CS-0470: FS | 2024-09-10 07:30 | 2024-09-19 17:30
HE-CS-0470 | In Progress | P2543-R01-Oct24..1.EN.8.12 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | HE-CS-0460 | HE-CS-0460: FS | C-52-598-04-CI-1010, HE-CS-1550, ML1034-B25, CAB-4420, ML1035-B26, ML1209-B27, C-56-PL-607-CI-2220, C-56-G-HT-CI-1000, C-56-591-01-CI-1000, C-56-591-01-CI-2200, C-52-598-06-CI-1000, C-52-598-06-CI-2200, C-52-598-05-CI-1000, C-52-598-05-CI-2200, C-52-598-04 | C-52-598-04-CI-1010: FS, HE-CS-1550: FS, ML1034-B25: FS, CAB-4420: FS, ML1035-B26: FS, ML1209-B27: FS, C-56-PL-607-CI-2220: FS, C-56-G-HT-CI-1000: FS, C-56-591-01-CI-1000: FS, C-56-591-01-CI-2200: FS, C-52-598-06-CI-1000: FS 3, C-52-598-06-CI-2200: FS, C-5 | 2024-10-23 07:30 | 2024-11-01 17:30
HE-CS-0430 | Completed | P2543-R01-Oct24..1.EN.8.12 | Issued for Review - Site grading, road, drainage and fence layout | HE-TS-0010, HE-PI-0570 | HE-TS-0010: FS, HE-PI-0570: FS | HE-CS-0440, HE-CS-0490 | HE-CS-0440: FS, HE-CS-0490: FS | 2023-12-18 | 2024-03-01
HE-CS-0510 | Completed | P2543-R01-Oct24..1.EN.8.11 | Re-Issue for Approval - Civil UG layout | HE-CS-0500 | HE-CS-0500: FS | HE-CS-0520 | HE-CS-0520: FS | 2024-10-01 | 2024-10-04 17:30
HE-CS-0520 | Completed | P2543-R01-Oct24..1.EN.8.11 | Obtain Company Approval - Civil UG layout | HE-CS-0510 | HE-CS-0510: FS | HE-CS-0530 | HE-CS-0530: FS | 2024-10-05 07:30 | 2024-10-11 17:30
HE-CS-0530 | Completed | P2543-R01-Oct24..1.EN.8.11 | Final Issue for Design/ Construction-Civil UG layout | HE-CS-0520, HE-TS-0050 | HE-CS-0520: FS, HE-TS-0050: FS | CAB-4420, C-COM-790, HE-CS-1550, ML1015-B08, ML1035-B26, ML1209-B27, ML1034-B25, C-56-PR-838-CI-1800, C-56-591-01-CI-1800, C-52-HG01-PL-CA-5220, C-52-598-06-CI-1800, C-52-598-06-CI-1810, C-52-598-05-CI-1800, C-52-598-05-CI-1810, C-52-598-04-CI-1800, C-52-5 | CAB-4420: FS, C-COM-790: FS, HE-CS-1550: FS, ML1015-B08: FS, ML1035-B26: FS, ML1209-B27: FS, ML1034-B25: FS, C-56-PR-838-CI-1800: FS, C-56-591-01-CI-1800: FS, C-52-HG01-PL-CA-5220: FS, C-52-598-06-CI-1800: FS, C-52-598-06-CI-1810: FS, C-52-598-05-CI-1800: | 2024-10-12 07:30 | 2024-10-18 17:30
HE-CS-0490 | Completed | P2543-R01-Oct24..1.EN.8.11 | Issued for Review - Civil UG layout | HE-TS-0010, HE-CS-0430 | HE-TS-0010: FS, HE-CS-0430: FS | HE-CS-0500, HE-CS-1640 | HE-CS-0500: FS, HE-CS-1640: SS 10 | 2024-03-02 | 2024-03-29
HE-CS-0500 | Completed | P2543-R01-Oct24..1.EN.8.11 | Review Company Comments - Civil UG layout | HE-CS-0490 | HE-CS-0490: FS | HE-CS-0510 | HE-CS-0510: FS | 2024-03-30 | 2024-04-23
HE-CS-0560 | Completed | P2543-R01-Oct24..1.EN.8.28 | Review Company Comments - Calculation for Pig launcher and receiver foundations | HE-CS-0550 | HE-CS-0550: FS | HE-CS-0570 | HE-CS-0570: FS | 2024-04-19 | 2024-04-25
HE-CS-0570 | Completed | P2543-R01-Oct24..1.EN.8.28 | Re-Issue for Approval - Calculation for Pig launcher and receiver foundations | HE-CS-0560 | HE-CS-0560: FS | HE-CS-0580 | HE-CS-0580: FS | 2024-09-02 07:30 | 2024-09-16 17:30
HE-CS-0580 | Completed | P2543-R01-Oct24..1.EN.8.28 | Obtain Company Approval - Calculation for Pig launcher and receiver foundations | HE-CS-0570 | HE-CS-0570: FS | HE-CS-0590 | HE-CS-0590: FS | 2024-09-16 07:30 | 2024-09-30 17:30
HE-CS-0590 | In Progress | P2543-R01-Oct24..1.EN.8.28 | Final Issue for Design/ Construction-Calculation for Pig launcher and receiver foundations | HE-GS-0050, HE-CS-0580 | HE-GS-0050: FS, HE-CS-0580: FS | CAB-4420, C-COM-790, HE-CS-0650 | CAB-4420: FS, C-COM-790: FS, HE-CS-0650: FS | 2024-09-30 07:30 | 2024-11-01 17:30
HE-CS-0550 | Completed | P2543-R01-Oct24..1.EN.8.28 | Issued for Review - Calculation for Pig launcher and receiver foundations | HE-GS-0010, HE-CS-0610 | HE-GS-0010: FS, HE-CS-0610: SS | HE-CS-0560, ML1199-B24 | HE-CS-0560: FS, ML1199-B24: FF | 2024-03-31 | 2024-04-18
HE-CS-0650 | Not Started | P2543-R01-Oct24..1.EN.8.27 | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | HE-CS-0640, HE-CS-0590 | HE-CS-0640: FS, HE-CS-0590: FS | ML1034-B25, HE-CS-1550, ML1209-B27, ML1035-B26, CAB-4420, C-56-PL-607-CI-1400, C-56-PR-838-CI-1400, C-56-PR-838-CI-1410, C-56-PR-838-CI-1420, C-52-PR-839-CI-1400, C-52-PR-839-CI-1410, C-52-PR-839-CI-1420, C-52-PR-839-CI-1500, C-52-PR-839-CI-1600, C-52-PL-8 | ML1034-B25: FS, HE-CS-1550: FS, ML1209-B27: FS, ML1035-B26: FS, CAB-4420: FS, C-56-PL-607-CI-1400: FS, C-56-PR-838-CI-1400: FS, C-56-PR-838-CI-1410: FS, C-56-PR-838-CI-1420: FS, C-52-PR-839-CI-1400: FS, C-52-PR-839-CI-1410: FS, C-52-PR-839-CI-1420: FS, C-5 | 2024-11-04 07:30 | 2024-11-08 17:30
HE-CS-0610 | Completed | P2543-R01-Oct24..1.EN.8.27 | Issued for Review - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | HM-ME-0410 | HM-ME-0410: FS | HE-CS-0620, HE-CS-0550, C-4N-H5-TPL-CI-0100 | HE-CS-0620: FS, HE-CS-0550: SS, C-4N-H5-TPL-CI-0100: FS | 2024-03-31 | 2024-04-25
HE-CS-0620 | Completed | P2543-R01-Oct24..1.EN.8.27 | Review Company Comments - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | HE-CS-0610 | HE-CS-0610: FS | HE-CS-0630 | HE-CS-0630: FS | 2024-04-26 07:30 | 2024-05-02 17:30
HE-CS-0630 | Completed | P2543-R01-Oct24..1.EN.8.27 | Re-Issue for Approval - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | HE-CS-0620, HM-ME-0410 | HE-CS-0620: FS, HM-ME-0410: SS 20 | HE-CS-0640 | HE-CS-0640: FS | 2024-09-02 07:30 | 2024-09-09 17:30
HE-CS-0640 | Completed | P2543-R01-Oct24..1.EN.8.27 | Obtain Company Approval - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | HE-CS-0630 | HE-CS-0630: FS | HE-CS-0650 | HE-CS-0650: FS | 2024-09-10 07:30 | 2024-09-16 17:30
HE-CS-0690 | Completed | P2543-R01-Oct24..1.EN.8.24 | Re-Issue for Approval - Design Cal. for Typical Skid Foundations | HE-CS-0680 | HE-CS-0680: FS | HE-CS-0700 | HE-CS-0700: FS | 2024-09-02 07:30 | 2024-09-09 17:30
HE-CS-0700 | Completed | P2543-R01-Oct24..1.EN.8.24 | Obtain Company Approval - Design Cal. for Typical Skid Foundations | HE-CS-0690 | HE-CS-0690: FS | HE-CS-0710 | HE-CS-0710: FS | 2024-09-10 07:30 | 2024-09-26 17:30
HE-CS-0710 | Not Started | P2543-R01-Oct24..1.EN.8.24 | Final Issue for Design/ Construction-Design Calculation for Typical Skid Foundations | HE-GS-0050, HE-CS-0700 | HE-GS-0050: FS, HE-CS-0700: FS | HE-CS-0770, CAB-4420, HE-CS-0830, HE-CS-0890 | HE-CS-0770: FF, CAB-4420: FS, HE-CS-0830: FS, HE-CS-0890: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HE-CS-0670 | Completed | P2543-R01-Oct24..1.EN.8.24 | Issued for Review - Design Cal. for Typical Skid Foundations | HE-GS-0010 | HE-GS-0010: FS | HE-CS-0680, HE-CS-0730, HE-CS-0910, HE-CS-0850, HE-CS-0790, HE-CS-2090 | HE-CS-0680: FS, HE-CS-0730: FS, HE-CS-0910: FS, HE-CS-0850: FS, HE-CS-0790: FS, HE-CS-2090: SS 5 | 2024-04-30 | 2024-05-01
HE-CS-0680 | Completed | P2543-R01-Oct24..1.EN.8.24 | Review Company Comments - Design Cal. for Typical Skid Foundations | HE-CS-0670 | HE-CS-0670: FS | HE-CS-0690 | HE-CS-0690: FS | 2024-05-02 | 2024-05-18
HE-CS-0730 | Completed | P2543-R01-Oct24..1.EN.8.23 | Issued for Review - Pressure Reduction Skid and Leak Detection Drawings | HE-CS-0670, HE-PI-0390 | HE-CS-0670: FS, HE-PI-0390: FS | HE-CS-0740 | HE-CS-0740: FS | 2024-04-01 | 2024-04-11
HE-CS-0740 | Completed | P2543-R01-Oct24..1.EN.8.23 | Review Company Comments - Pressure Reduction Skid and Leak Detection Drawings | HE-CS-0730 | HE-CS-0730: FS | HE-CS-0750 | HE-CS-0750: FS | 2024-09-09 07:30 | 2024-09-23 17:30
HE-CS-0750 | Completed | P2543-R01-Oct24..1.EN.8.23 | Re-Issue for Approval - Pressure Reduction Skid and Leak Detection Drawings | HE-CS-0740 | HE-CS-0740: FS | HE-CS-0760 | HE-CS-0760: FS | 2024-09-24 07:30 | 2024-09-30 17:30
HE-CS-0760 | Completed | P2543-R01-Oct24..1.EN.8.23 | Obtain Company Approval - Pressure Reduction Skid and Leak Detection Drawings | HE-CS-0750 | HE-CS-0750: FS | HE-CS-0770 | HE-CS-0770: FS | 2024-09-30 07:30 | 2024-10-07 17:30
HE-CS-0770 | In Progress | P2543-R01-Oct24..1.EN.8.23 | Final Issue for Design/ Construction - Pressure Reduction Skid and Leak Detection Drawings | HE-CS-0710, HE-PI-0440, HE-CS-0760 | HE-CS-0710: FF, HE-PI-0440: FF, HE-CS-0760: FS | HE-CS-1550, ML1209-B27, ML1035-B26, CAB-4420, C-52-PR-839-ME-2000, C-52-PR-839-ME-2010 | HE-CS-1550: FS, ML1209-B27: FS, ML1035-B26: FS, CAB-4420: FS, C-52-PR-839-ME-2000: FS, C-52-PR-839-ME-2010: FS | 2024-10-08 07:30 | 2024-11-08 17:30
HE-CS-0800 | Completed | P2543-R01-Oct24..1.EN.8.25 | Review Company Comments - Gas metering skid foundation drawings | HE-CS-0790 | HE-CS-0790: FS | HE-CS-0810 | HE-CS-0810: FS | 2024-04-26 07:30 | 2024-05-16 17:30
HE-CS-0810 | Completed | P2543-R01-Oct24..1.EN.8.25 | Re-Issue for Approval - Gas metering skid foundation drawings | HE-CS-0800 | HE-CS-0800: FS | HE-CS-0820 | HE-CS-0820: FS | 2024-09-02 07:30 | 2024-09-09 17:30
HE-CS-0820 | Completed | P2543-R01-Oct24..1.EN.8.25 | Obtain Company Approval - Gas metering skid foundation drawings | HE-CS-0810 | HE-CS-0810: FS | HE-CS-0830 | HE-CS-0830: FF 10 | 2024-09-10 07:30 | 2024-09-26 17:30
HE-CS-0830 | Not Started | P2543-R01-Oct24..1.EN.8.25 | Final Issue for Design/ Construction-Gas metering skid foundation drawings | HE-CS-0820, HE-GS-0050, HE-CS-0710 | HE-CS-0820: FF 10, HE-GS-0050: FS, HE-CS-0710: FS | HE-CS-1550, ML1035-B26, CAB-4420, ML1036-B23, ML1034-B25, ML1209-B27, C-52-PR-839-ME-2010 | HE-CS-1550: FS, ML1035-B26: FS, CAB-4420: FS, ML1036-B23: FF, ML1034-B25: FS, ML1209-B27: FS, C-52-PR-839-ME-2010: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-CS-0790 | Completed | P2543-R01-Oct24..1.EN.8.25 | Issued for Review - Gas metering skid foundation drawings | HE-GS-0010, HE-CS-0670, HP-ME-0010 | HE-GS-0010: FS, HE-CS-0670: FS, HP-ME-0010: FS | HE-CS-1840, HE-CS-0800 | HE-CS-1840: FF, HE-CS-0800: FS | 2024-03-31 | 2024-04-25
HE-CS-0850 | Completed | P2543-R01-Oct24..1.EN.8.20 | Issued for Review - Solar panel foundation details | HP-ME-0530, HE-EL-0370, HE-CS-0670 | HP-ME-0530: SS, HE-EL-0370: FS, HE-CS-0670: FS | HE-CS-0860 | HE-CS-0860: FS | 2024-06-14 | 2024-06-28 17:30
HE-CS-0860 | Completed | P2543-R01-Oct24..1.EN.8.20 | Review Company Comments - Solar panel foundation details | HE-CS-0850 | HE-CS-0850: FS | HE-CS-0870 | HE-CS-0870: FS | 2024-06-28 07:30 | 2024-07-05 17:30
HE-CS-0870 | Completed | P2543-R01-Oct24..1.EN.8.20 | Re-Issue for Approval - Solar panel foundation details | HE-CS-0860 | HE-CS-0860: FS | HE-CS-0880 | HE-CS-0880: FS | 2024-10-14 07:30 | 2024-10-24 17:30
HE-CS-0880 | In Progress | P2543-R01-Oct24..1.EN.8.20 | Obtain Company Approval - Solar panel foundation details | HE-CS-0870 | HE-CS-0870: FS | HE-CS-0890 | HE-CS-0890: FS | 2024-10-25 07:30 | 2024-11-08 17:30
HE-CS-0890 | Not Started | P2543-R01-Oct24..1.EN.8.20 | Final Issue for Design/ Construction-Solar panel foundation details | HE-CS-1980, HE-CS-0880, HE-EL-0410, HE-CS-0710 | HE-CS-1980: FF, HE-CS-0880: FS, HE-EL-0410: FS, HE-CS-0710: FS | CAB-4420, C-56-591-01-CI-1400, C-52-598-06-CI-1400, C-52-598-05-CI-1400, C-52-598-04-CI-1400, C-52-598-03-CI-1400, C-52-598-02-CI-1400, C-52-598-01-CI-1400 | CAB-4420: FS, C-56-591-01-CI-1400: FS, C-52-598-06-CI-1400: FS, C-52-598-05-CI-1400: FS, C-52-598-04-CI-1400: FS, C-52-598-03-CI-1400: FS, C-52-598-02-CI-1400: FS, C-52-598-01-CI-1400: FS | 2024-11-18 07:30 | 2024-11-29 17:30
HE-CS-0910 | Completed | P2543-R01-Oct24..1.EN.8.33 | Issued for Review - Typical Spill Pit General Arrangement And RC (type) Details | HE-PI-0560, HE-CS-0670, HE-CS-2040 | HE-PI-0560: FS, HE-CS-0670: FS, HE-CS-2040: FS | HE-CS-0920 | HE-CS-0920: FS | 2024-07-08 | 2024-07-15 17:30
HE-CS-0920 | Completed | P2543-R01-Oct24..1.EN.8.33 | Review Company Comments - Typical Spill Pit General Arrangement And RC (type) Details | HE-CS-0910 | HE-CS-0910: FS | HE-CS-0930 | HE-CS-0930: FS | 2024-07-16 07:30 | 2024-07-19 17:30
HE-CS-0930 | Completed | P2543-R01-Oct24..1.EN.8.33 | Re-Issue for Approval - Typical Spill Pit General Arrangement And RC (type) Details | HE-CS-0920 | HE-CS-0920: FS | HE-CS-0940 | HE-CS-0940: FS | 2024-09-16 07:30 | 2024-09-20 17:30
HE-CS-0940 | Completed | P2543-R01-Oct24..1.EN.8.33 | Obtain Company Approval - Typical Spill Pit General Arrangement And RC (type) Details | HE-CS-0930 | HE-CS-0930: FS | HE-CS-0950 | HE-CS-0950: FS | 2024-09-23 | 2024-10-10 17:30
HE-CS-0950 | In Progress | P2543-R01-Oct24..1.EN.8.33 | Final Issue for Design/ Construction-FILTER FOUNDATION GA AND DETAILS | HE-CS-0940, HE-CS-2030 | HE-CS-0940: FS, HE-CS-2030: FF | CAB-4420, ML1035-B26, ML1209-B27, C-52-PR-839-ME-1800 | CAB-4420: FS, ML1035-B26: FS, ML1209-B27: FF, C-52-PR-839-ME-1800: FS | 2024-10-10 07:30 | 2024-11-08 17:30
HE-CS-1010 | Not Started | P2543-R01-Oct24..1.EN.8.21 | Final Issue for Design/ Construction-TYPICAL LIGHTING POLE FOUNDATION DETAILS | HE-CS-1000, HE-CS-2080 | HE-CS-1000: FS, HE-CS-2080: FF | ML1209-B27, CAB-4420, HE-CS-1550, ML1035-B26, ML1034-B25, C-52-598-06-CI-1430, C-52-598-05-CI-1430, C-52-598-04-CI-1430, C-52-598-03-CI-1430, C-52-598-02-CI-1430, C-52-598-01-CI-1430, C-56-591-01-CI-1430 | ML1209-B27: FS, CAB-4420: FS, HE-CS-1550: FF, ML1035-B26: FS, ML1034-B25: FF, C-52-598-06-CI-1430: FS, C-52-598-05-CI-1430: FS, C-52-598-04-CI-1430: FS, C-52-598-03-CI-1430: FS, C-52-598-02-CI-1430: FS, C-52-598-01-CI-1430: FS, C-56-591-01-CI-1430: FS | 2024-11-25 07:30 | 2024-12-10 17:30
HE-CS-0970 | Completed | P2543-R01-Oct24..1.EN.8.21 | Issued for Review - Lighting pole foundation details | HE-CS-2090 | HE-CS-2090: FS | HE-CS-0980, HE-CS-1090 | HE-CS-0980: FS, HE-CS-1090: FS | 2024-02-26 | 2024-03-15
HE-CS-0980 | Completed | P2543-R01-Oct24..1.EN.8.21 | Review Company Comments - Lighting pole foundation details | HE-CS-0970 | HE-CS-0970: FS | HE-CS-0990 | HE-CS-0990: FS | 2024-04-01 | 2024-08-09 17:30
HE-CS-0990 | Not Started | P2543-R01-Oct24..1.EN.8.21 | Re-Issue for Approval - Lighting pole foundation details | HE-CS-0980 | HE-CS-0980: FS | HE-CS-1000 | HE-CS-1000: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HE-CS-1000 | Not Started | P2543-R01-Oct24..1.EN.8.21 | Obtain Company Approval - Lighting pole foundation details | HE-CS-0990 | HE-CS-0990: FS | HE-CS-1010 | HE-CS-1010: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-CS-1040 | Completed | P2543-R01-Oct24..1.EN.8.36 | Review Company Comments - Typical Detailed Drawing - Jib Crane Foundation | HE-CS-1030 | HE-CS-1030: FS | HE-CS-1050 | HE-CS-1050: FS | 2024-03-31 | 2024-04-23
HE-CS-1050 | Completed | P2543-R01-Oct24..1.EN.8.36 | Re-Issue for Approval - Typical Detailed Drawing - Jib Crane Foundation | HE-CS-1040 | HE-CS-1040: FS | HE-CS-1060 | HE-CS-1060: FS | 2024-06-07 | 2024-06-18
HE-CS-1060 | Completed | P2543-R01-Oct24..1.EN.8.36 | Obtain Company Approval - Typical Detailed Drawing - Jib Crane Foundation | HE-CS-1050 | HE-CS-1050: FS | HE-CS-1070 | HE-CS-1070: FS | 2024-06-19 07:30 | 2024-06-25 17:30
HE-CS-1070 | Completed | P2543-R01-Oct24..1.EN.8.36 | Final Issue for Design/ Construction-Typical Detailed Drawing - Jib Crane Foundation | HE-CS-1060 | HE-CS-1060: FS | ML1209-B27, HE-CS-1550, ML1034-B25, CAB-4420, ML1035-B26, C-56-PL-607-CI-1400, C-56-PR-838-CI-1400, C-52-PR-839-CI-1400, C-52-PL-838-CI-1400 | ML1209-B27: FS, HE-CS-1550: FS, ML1034-B25: FS, CAB-4420: FS, ML1035-B26: FS, C-56-PL-607-CI-1400: FS, C-56-PR-838-CI-1400: FS, C-52-PR-839-CI-1400: FS, C-52-PL-838-CI-1400: FS | 2024-06-26 | 2024-07-12 17:30
HE-CS-1030 | Completed | P2543-R01-Oct24..1.EN.8.36 | Issued for Review - Typical Detailed Drawing - Jib Crane Foundation | HE-PI-0490, HE-PI-0420, HE-PI-0350, HE-CS-1990 | HE-PI-0490: FS, HE-PI-0420: FS, HE-PI-0350: FS, HE-CS-1990: FF 20 | HE-CS-1040 | HE-CS-1040: FS | 2024-03-12 | 2024-03-23
HE-CS-1110 | Completed | P2543-R01-Oct24..1.EN.8.30 | Re-Issue for Approval - Calculations for Pipe supports | HE-CS-1100 | HE-CS-1100: FS | HE-CS-1120 | HE-CS-1120: FF 5 | 2024-09-02 07:30 | 2024-09-30 17:30
HE-CS-1120 | In Progress | P2543-R01-Oct24..1.EN.8.30 | Obtain Company Approval - Calculations for Pipe supports | HE-CS-1110 | HE-CS-1110: FF 5 | HE-CS-1130 | HE-CS-1130: FS | 2024-09-12 07:30 | 2024-11-08 17:30
HE-CS-1130 | Not Started | P2543-R01-Oct24..1.EN.8.30 | Final Issue for Design/ Construction-Design Calculation for Typical Pipe supports | HE-CS-1120, HE-GS-0050 | HE-CS-1120: FS, HE-GS-0050: FS | CAB-4420, C-56-G-HT-CI-1600, C-52-PR-839-CI-1600, C-52-D-HT-CI-1600 | CAB-4420: FS, C-56-G-HT-CI-1600: FS, C-52-PR-839-CI-1600: FS, C-52-D-HT-CI-1600: FS | 2024-11-11 07:30 | 2024-11-15 17:30
HE-CS-1090 | Completed | P2543-R01-Oct24..1.EN.8.30 | Issued for Review - Calculations for Pipe supports | HE-GS-0010, HE-PI-0530, HE-CS-0970 | HE-GS-0010: FS, HE-PI-0530: FS, HE-CS-0970: FS | HE-CS-1100, HE-CS-1330 | HE-CS-1100: FS, HE-CS-1330: FF | 2024-03-31 | 2024-04-22
HE-CS-1100 | Completed | P2543-R01-Oct24..1.EN.8.30 | Review Company Comments - Calculations for Pipe supports | HE-CS-1090 | HE-CS-1090: FS | HE-CS-1110 | HE-CS-1110: FS | 2024-07-29 07:30 | 2024-08-09 17:30
HE-CS-1180 | Completed | P2543-R01-Oct24..1.EN.8.22 | Obtain Company Approval - Valve pit foundation GA and RC (type) details | HE-CS-1170 | HE-CS-1170: FS | HE-CS-1190 | HE-CS-1190: FS | 2024-09-10 07:30 | 2024-09-21 17:30
HE-CS-1190 | In Progress | P2543-R01-Oct24..1.EN.8.22 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | HE-CS-1180, HE-CS-1880 | HE-CS-1180: FS, HE-CS-1880: FF | HE-CS-1550, ML1034-B25, CAB-4420, C-56-PL-607-CI-1400, C-56-PR-838-CI-1400, C-56-591-01-CI-1400, C-52-598-06-CI-1400, C-52-598-05-CI-1400, C-52-598-04-CI-1400, C-52-598-03-CI-1400, C-52-598-02-CI-1400, C-52-598-01-CI-1400, C-52-PR-839-CI-1400, C-52-PL-838- | HE-CS-1550: FS, ML1034-B25: FS, CAB-4420: FS, C-56-PL-607-CI-1400: FS, C-56-PR-838-CI-1400: FS, C-56-591-01-CI-1400: FS, C-52-598-06-CI-1400: FS, C-52-598-05-CI-1400: FS, C-52-598-04-CI-1400: FS, C-52-598-03-CI-1400: FS, C-52-598-02-CI-1400: FS, C-52-598-0 | 2024-09-30 07:30 | 2024-11-08 17:30
HE-CS-1150 | Completed | P2543-R01-Oct24..1.EN.8.22 | Issued for Review - Valve pit foundation GA and RC (type) details | HE-PL-2450, HE-PI-0530 | HE-PL-2450: FF, HE-PI-0530: FS | HE-CS-1160 | HE-CS-1160: FS | 2024-03-26 | 2024-04-24
HE-CS-1160 | Completed | P2543-R01-Oct24..1.EN.8.22 | Review Company Comments - Valve pit foundation GA and RC (type) details | HE-CS-1150 | HE-CS-1150: FS | HE-CS-1170 | HE-CS-1170: FS | 2024-06-14 | 2024-08-09
HE-CS-1170 | Completed | P2543-R01-Oct24..1.EN.8.22 | Re-Issue for Approval - Valve pit foundation GA and RC (type) details | HE-CS-1160 | HE-CS-1160: FS | HE-CS-1180 | HE-CS-1180: FS | 2024-09-02 07:30 | 2024-09-09 17:30
HE-CS-1210 | Completed | P2543-R01-Oct24..1.EN.8.29 | Issued for Review - Impact Wall GA and RC (type) details | HE-CS-1940 | HE-CS-1940: FS | HE-CS-1220 | HE-CS-1220: FS | 2024-03-29 | 2024-04-28
HE-CS-1220 | Completed | P2543-R01-Oct24..1.EN.8.29 | Review Company Comments - Impact Wall GA and RC (type) details | HE-CS-1210 | HE-CS-1210: FS | HE-CS-1230 | HE-CS-1230: FS | 2024-05-16 | 2024-06-05
HE-CS-1230 | Completed | P2543-R01-Oct24..1.EN.8.29 | Re-Issue for Approval - Impact Wall GA and RC (type) details | HE-CS-1220 | HE-CS-1220: FS | HE-CS-1240 | HE-CS-1240: FS | 2024-06-06 | 2024-06-08
HE-CS-1240 | Completed | P2543-R01-Oct24..1.EN.8.29 | Obtain Company Approval - Impact Wall GA and RC (type) details | HE-CS-1230 | HE-CS-1230: FS | HE-CS-1250 | HE-CS-1250: FS | 2024-06-09 | 2024-06-21
HE-CS-1250 | In Progress | P2543-R01-Oct24..1.EN.8.29 | Final Issue for Design/ Construction-TYPICAL GA AND RC DETAILS OF IMPACT WALL | HE-CS-1240, HE-CS-1930 | HE-CS-1240: FS, HE-CS-1930: FF | ML1035-B26, CAB-4420, ML1209-B27, HE-CS-1550, ML1034-B25, C-56-PL-607-CI-1500, C-56-PR-838-CI-1500, C-52-PR-839-CI-1500, C-4N-HG-TPR-CI-1500 | ML1035-B26: FS, CAB-4420: FS, ML1209-B27: FS, HE-CS-1550: FS, ML1034-B25: FS, C-56-PL-607-CI-1500: SS, C-56-PR-838-CI-1500: FS, C-52-PR-839-CI-1500: FS, C-4N-HG-TPR-CI-1500: FS | 2024-10-04 07:30 | 2024-11-01 17:30
HE-CS-1310 | Not Started | P2543-R01-Oct24..1.EN.8.37 | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | HE-CS-1300, HE-CS-1830 | HE-CS-1300: FS, HE-CS-1830: FS | CAB-4420, ML1034-B25, ML1035-B26, HE-CS-1550, ML1209-B27, C-56-PL-607-CI-1400, C-56-PR-838-CI-1400, C-56-591-01-CI-1400, C-52-598-06-CI-1400, C-52-598-05-CI-1400, C-52-598-04-CI-1400, C-52-598-03-CI-1400, C-52-598-02-CI-1400, C-52-598-01-CI-1400, C-52-PR-8 | CAB-4420: FS, ML1034-B25: FS, ML1035-B26: FS, HE-CS-1550: FS, ML1209-B27: FS, C-56-PL-607-CI-1400: FF, C-56-PR-838-CI-1400: FF, C-56-591-01-CI-1400: FS, C-52-598-06-CI-1400: FS, C-52-598-05-CI-1400: FS, C-52-598-04-CI-1400: FS, C-52-598-03-CI-1400: FS, C-5 | 2024-11-12 07:30 | 2024-11-18 17:30
HE-CS-1270 | Completed | P2543-R01-Oct24..1.EN.8.37 | Issued for Review - Passive cooled shelter foundation GA and details | HE-PI-0420, HE-PI-0350, HE-PI-0490, HE-CS-1840 | HE-PI-0420: FS, HE-PI-0350: FS, HE-PI-0490: FS, HE-CS-1840: FS | HE-CS-1280 | HE-CS-1280: FS | 2023-11-30 | 2023-12-13
HE-CS-1280 | Completed | P2543-R01-Oct24..1.EN.8.37 | Review Company Comments - Passive cooled shelter foundation GA and details | HE-CS-1270 | HE-CS-1270: FS | HE-CS-1290 | HE-CS-1290: FS | 2023-12-14 | 2023-12-27
HE-CS-1290 | Completed | P2543-R01-Oct24..1.EN.8.37 | Re-Issue for Approval - Passive cooled shelter foundation GA and details | HE-CS-1280 | HE-CS-1280: FS | HE-CS-1300 | HE-CS-1300: FS | 2024-01-31 | 2024-02-03
HE-CS-1300 | Completed | P2543-R01-Oct24..1.EN.8.37 | Obtain Company Approval - Passive cooled shelter foundation GA and details | HE-CS-1290 | HE-CS-1290: FS | HE-CS-1310 | HE-CS-1310: FS | 2024-07-29 07:30 | 2024-08-09 17:30
HS-GN-0170 | Completed | P2543-R01-Oct24..1.2.13.4 | Place LOA/FOA - Topographical survey & Geotechnical Investigation | HS-GN-0160 | HS-GN-0160: FS | ML1007-B02, HE-SS-0030, HE-SS-0040 | ML1007-B02: FS, HE-SS-0030: FS, HE-SS-0040: FS | 2023-09-01 | 2023-09-05
HS-GN-0130 | Completed | P2543-R01-Oct24..1.2.13.4 | Prepare/Issue Scope of Work - Topographical survey & Geotechnical Investigation | ML1001 | ML1001: SS 3 | HS-GN-0140 | HS-GN-0140: FS | 2023-07-13 | 2023-07-27
HS-GN-0160 | Completed | P2543-R01-Oct24..1.2.13.4 | Complete Evaluation (Internal) - Topographical survey & Geotechnical Investigation | HS-GN-0140 | HS-GN-0140: FS | HS-GN-0170 | HS-GN-0170: FS | 2023-08-26 | 2023-09-01
HS-GN-0140 | Completed | P2543-R01-Oct24..1.2.13.4 | Receive Bids - Topographical survey & Geotechnical Investigation | HS-GN-0130 | HS-GN-0130: FS | HS-GN-0160 | HS-GN-0160: FS | 2023-08-01 | 2023-08-07
HS-GN-0230 | Completed | P2543-R01-Oct24..1.1.1.5 | Commercial Clarifications & Placement of PO- Hot Tapping | HS-GN-0220 | HS-GN-0220: FS | HE-PL-1530, HM-PL-0250, HE-PI-0180, ML1219-B29, CAB-4480, C-56-G-HT101-ME-1000, C-52-D-HT002-ME-1000, C-36-KM-HT03-ME-1000, C-36-KM-HT04-ME-1000 | HE-PL-1530: FS, HM-PL-0250: FS, HE-PI-0180: FS, ML1219-B29: FF, CAB-4480: FS, C-56-G-HT101-ME-1000: FS, C-52-D-HT002-ME-1000: FS, C-36-KM-HT03-ME-1000: FS, C-36-KM-HT04-ME-1000: FS | 2024-02-26 | 2024-03-22
HS-GN-0190 | Completed | P2543-R01-Oct24..1.1.1.5 | RFQ, Receipt of Bid for - Hot Tapping | HE-PL-1330 | HE-PL-1330: FS | HS-GN-0220 | HS-GN-0220: FS | 2024-01-29 | 2024-02-09
HS-GN-0220 | Completed | P2543-R01-Oct24..1.1.1.5 | + | HS-GN-0190 | HS-GN-0190: FS | HS-GN-0230 | HS-GN-0230: FS | 2024-02-26 | 2024-03-15
HS-GN-0280 | Completed | P2543-R01-Oct24..1.1.BK.10 | Prepare TBE and Company approval - Modification of Exiting CTMM | HS-GN-0250, HE-IC-2440 | HS-GN-0250: FS, HE-IC-2440: FF | HS-GN-0290 | HS-GN-0290: FS | 2023-11-30 | 2024-01-29
HS-GN-0290 | Completed | P2543-R01-Oct24..1.1.BK.10 | Commercial Clarifications & Placement of PO - Modification of Exiting CTMM | HS-GN-0280 | HS-GN-0280: FS | ML1549-D32, C-MAQTA-EI-1000, C-MAQTA-TE-1000, C-MAQTA-TE-1010, C-541CR-EI-1020, C-541CR-TE-1000, C-577-TE-1000, C-601-TE-1000 | ML1549-D32: FF, C-MAQTA-EI-1000: FS, C-MAQTA-TE-1000: FS, C-MAQTA-TE-1010: FS, C-541CR-EI-1020: FS, C-541CR-TE-1000: FS, C-577-TE-1000: FS, C-601-TE-1000: FS | 2024-01-29 | 2024-02-16
HS-GN-0250 | Completed | P2543-R01-Oct24..1.1.BK.10 | RFQ, Receipt of Bid - Modification of Exiting CTMM | HE-IC-1930 | HE-IC-1930: FS | HS-GN-0280 | HS-GN-0280: FS | 2023-10-30 | 2023-11-29
HS-GN-0350 | Completed | P2543-R01-Oct24..1.1.BK.12 | Commercial Clarifications & Placement of PO - Modification of Existing Telecom System | HS-GN-0340 | HS-GN-0340: FS | ML1549-D32, C-MAQTA-EI-1000, C-MAQTA-TE-1000, C-MAQTA-TE-1010, C-541CR-EI-1020, C-541CR-TE-1000, C-577-TE-1000, C-601-TE-1000 | ML1549-D32: FF, C-MAQTA-EI-1000: FS, C-MAQTA-TE-1000: FS, C-MAQTA-TE-1010: FS, C-541CR-EI-1020: FS, C-541CR-TE-1000: FS, C-577-TE-1000: FS, C-601-TE-1000: FS | 2024-05-30 | 2024-06-07
HS-GN-0310 | Completed | P2543-R01-Oct24..1.1.BK.12 | RFQ, Receipt of Bid - Modification of Existing Telecom System | HE-IC-620, HE-IC-2730 | HE-IC-620: SS, HE-IC-2730: FS | HS-GN-0340 | HS-GN-0340: FS | 2023-11-29 | 2024-01-10
HS-GN-0340 | Completed | P2543-R01-Oct24..1.1.BK.12 | Prepare TBE and Company approval - Modification of Existing Telecom System | HS-GN-0310 | HS-GN-0310: FS | HS-GN-0350 | HS-GN-0350: FS | 2024-01-11 | 2024-05-29
HS-GN-0410 | Completed | P2543-R01-Oct24..1.1.BK.14 | Commercial Clarifications & Placement of PO - Modification of Exiting SMC / SCADA | HS-GN-0400 | HS-GN-0400: FS | C-COM-790, HE-IC-2790, C-MAQTA-EI-1000, C-MAQTA-TE-1000, C-MAQTA-TE-1010, C-541CR-EI-1020, C-541CR-TE-1000, C-577-TE-1000, C-601-TE-1000 | C-COM-790: FS, HE-IC-2790: FS, C-MAQTA-EI-1000: FS, C-MAQTA-TE-1000: FS, C-MAQTA-TE-1010: FS, C-541CR-EI-1020: FS, C-541CR-TE-1000: FS, C-577-TE-1000: FS, C-601-TE-1000: FS | 2024-06-06 07:30 | 2024-06-10 17:30
HS-GN-0370 | Completed | P2543-R01-Oct24..1.1.BK.14 | RFQ, Receipt of Bid - Modification of Exiting SMC / SCADA | HE-IC-1930, HE-IC-2880 | HE-IC-1930: FS, HE-IC-2880: FS | HS-GN-0400, HE-IC-2900 | HS-GN-0400: FS, HE-IC-2900: FS | 2024-01-26 | 2024-03-15
HS-GN-0400 | Completed | P2543-R01-Oct24..1.1.BK.14 | Prepare TBE and Company approval - Modification of Exiting SMC / SCADA | HS-GN-0370, HE-IC-2440 | HS-GN-0370: FS, HE-IC-2440: FF | HS-GN-0410 | HS-GN-0410: FS | 2024-04-11 | 2024-06-05
HS-GN-0460 | Completed | P2543-R01-Oct24..1.1.BK.18 | Prepare TBE and Company approval - Modification of Existing DCS | HS-GN-0430 | HS-GN-0430: FS | HS-GN-0470 | HS-GN-0470: FS | 2024-03-31 | 2024-06-05
HS-GN-0470 | Completed | P2543-R01-Oct24..1.1.BK.18 | Commercial Clarifications & Placement of PO - Modification of Existing DCS | HS-GN-0460 | HS-GN-0460: FS | C-COM-790, C-MAQTA-EI-1000, C-MAQTA-TE-1000, C-MAQTA-TE-1010, C-541CR-EI-1020, C-541CR-TE-1000, C-577-TE-1000, C-601-TE-1000 | C-COM-790: FS, C-MAQTA-EI-1000: FS, C-MAQTA-TE-1000: FS, C-MAQTA-TE-1010: FS, C-541CR-EI-1020: FS, C-541CR-TE-1000: FS, C-577-TE-1000: FS, C-601-TE-1000: FS | 2024-06-06 | 2024-06-10
HS-GN-0430 | Completed | P2543-R01-Oct24..1.1.BK.18 | RFQ, Receipt of Bid - Modification of Existing DCS | HE-IC-0190, HE-IC-0550, HE-IC-0230, HE-IC-0290, HE-IC-0250 | HE-IC-0190: FS, HE-IC-0550: FS, HE-IC-0230: FS, HE-IC-0290: FS, HE-IC-0250: FS | HS-GN-0460 | HS-GN-0460: FS | 2024-01-26 | 2024-03-15
HS-GN-0490 | Completed | P2543-R01-Oct24..1.2.13.11 | Prepare/Issue Scope of Work - Cathodic Protection Work | HE-PL-2420, HE-CP-150 | HE-PL-2420: FS, HE-CP-150: FS | HS-GN-0500 | HS-GN-0500: FS | 2023-11-22 | 2024-01-02
HS-GN-0520 | Completed | P2543-R01-Oct24..1.2.13.11 | Complete Evaluation (Internal) - Cathodic Protection Work | HS-GN-0500 | HS-GN-0500: FS | HS-GN-0530 | HS-GN-0530: FS | 2024-03-15 | 2024-03-29
HS-GN-0500 | Completed | P2543-R01-Oct24..1.2.13.11 | Receive Bids - Cathodic Protection Work | HS-GN-0490 | HS-GN-0490: FS | HS-GN-0520 | HS-GN-0520: FS | 2024-02-26 | 2024-03-15
HS-GN-0530 | Completed | P2543-R01-Oct24..1.2.13.11 | Place LOA/FOA - Cathodic Protection Work | HS-GN-0520 | HS-GN-0520: FS | ML1038-C10, HM-PL-0350, C-56-HC01-PL-CA-5220, C-56-HC01-PL-CA-5200, C-56-HC01-PL-CA-5400, C-56-HC01-PL-CA-5430, C-52-HG01-PL-CA-5200, C-52-HG01-PL-CA-5220 | ML1038-C10: FF, HM-PL-0350: FS, C-56-HC01-PL-CA-5220: FS, C-56-HC01-PL-CA-5200: FS, C-56-HC01-PL-CA-5400: FS, C-56-HC01-PL-CA-5430: FS, C-52-HG01-PL-CA-5200: FS, C-52-HG01-PL-CA-5220: FS | 2024-05-17 | 2024-05-20
HS-GN-0110 | Completed | P2543-R01-Oct24..1.2.13.9 | Place LOA/FOA - HSE Studies | HS-GN-0100 | HS-GN-0100: FS | HE-HS-0970, HE-PI-0150, HE-HS-0670, HE-HS-0490, HE-PI-0130, C-COM-790, CAB-5290, HE-WS-0050, HE-WS-0020, HE-HS-0190, HE-HS-0130 | HE-HS-0970: FS, HE-PI-0150: FS, HE-HS-0670: FS, HE-HS-0490: FS, HE-PI-0130: FS, C-COM-790: FS, CAB-5290: FS, HE-WS-0050: FS, HE-WS-0020: FS, HE-HS-0190: FS, HE-HS-0130: FS | 2023-09-01 | 2023-09-26
HS-GN-0070 | Completed | P2543-R01-Oct24..1.2.13.9 | Prepare/Issue Scope of Work - HSE Studies | HE-HS-0070, HE-HS-0010 | HE-HS-0070: SS, HE-HS-0010: SS | HS-GN-0080 | HS-GN-0080: FS 2 | 2023-07-24 | 2023-07-28
HS-GN-0100 | Completed | P2543-R01-Oct24..1.2.13.9 | Complete Evaluation (Internal) - HSE Studies | HS-GN-0080 | HS-GN-0080: FS | HS-GN-0110 | HS-GN-0110: FS | 2023-08-26 | 2023-09-01
HS-GN-0080 | Completed | P2543-R01-Oct24..1.2.13.9 | Receive Bids - HSE Studies | HS-GN-0070 | HS-GN-0070: FS 2 | HS-GN-0100 | HS-GN-0100: FS | 2023-08-01 | 2023-08-07
HS-CN-0060 | Completed | P2543-R01-Oct24..1.2.12.2 | NDRC RFQ & Quotation Receipt | HE-PL-0170, ML1002 | HE-PL-0170: SS, ML1002: FS | HS-CN-0080 | HS-CN-0080: FS | 2023-08-31 | 2023-09-07
HS-CN-0080 | Completed | P2543-R01-Oct24..1.2.12.2 | NDRC Complete Evaluation (Internal) | HS-CN-0060 | HS-CN-0060: FS | HS-CN-0090 | HS-CN-0090: FS | 2023-09-08 | 2023-10-05
HS-CN-0090 | Completed | P2543-R01-Oct24..1.2.12.2 | NDRC Subcontract Award | HS-CN-0080 | HS-CN-0080: FS | ML1579-E03, ML1679-E13, C-56-HC01-PL-ME-4800, C-56-01HG-PL-CA-5220, C-56-01HG-PL-CA-5420, C-56-01HG-PL-ME-4800, C-56-01HG-PL-ME-5000, C-52-06CR-PL-CA-5200, C-52-06CR-PL-ME-7400, C-52-0506-PL-CA-5200, C-52-0506-PL-ME-7400, C-52-0405-PL-CA-5200, C-52-0405-PL | ML1579-E03: FS, ML1679-E13: FS, C-56-HC01-PL-ME-4800: FF, C-56-01HG-PL-CA-5220: FS, C-56-01HG-PL-CA-5420: FS, C-56-01HG-PL-ME-4800: FF, C-56-01HG-PL-ME-5000: FF, C-52-06CR-PL-CA-5200: FF, C-52-06CR-PL-ME-7400: FF, C-52-0506-PL-CA-5200: FF, C-52-0506-PL-ME- | 2023-10-06 | 2023-11-17
HS-CN-0140 | Completed | P2543-R01-Oct24..1.2.12.3 | Testing & Precommissioning Subcontract Award | HS-CN-0130 | HS-CN-0130: FS | CCM-PM4540, PRECOM-56-PL-1000, PRECOM-56-PL-1000, PRECOM-56-EB2-1000, PRECOM-56-EB2-1000, PRECOM-56-G-1000, PRECOM-56-59101-1000, PRECOM-56-59101-1000, PRECOM-56-PR-1000, PRECOM-56-HGHC-1000, PRECOM-52-59806-1000, PRECOM-52-06CR-1000, PRECOM-52-EB1-1000, P | CCM-PM4540: SS, PRECOM-56-PL-1000: SS, PRECOM-56-PL-1000: FS, PRECOM-56-EB2-1000: SS, PRECOM-56-EB2-1000: FS, PRECOM-56-G-1000: FS, PRECOM-56-59101-1000: SS, PRECOM-56-59101-1000: FS, PRECOM-56-PR-1000: FS, PRECOM-56-HGHC-1000: FS, PRECOM-52-59806-1000: FS | 2024-05-03 | 2024-05-20
HS-CN-0110 | Completed | P2543-R01-Oct24..1.2.12.3 | Testing & Precommissioning RFQ & Quotation Receipt | ML1002 | ML1002: FS | HS-CN-0130 | HS-CN-0130: FS | 2023-11-22 | 2024-01-02
HS-CN-0130 | Completed | P2543-R01-Oct24..1.2.12.3 | Testing & Precommissioning Complete Evaluation (Internal) | HS-CN-0110 | HS-CN-0110: FS | HS-CN-0140 | HS-CN-0140: FS | 2024-03-06 | 2024-05-02
HS-CN-0160 | Completed | P2543-R01-Oct24..1.2.12.4 | NDT / PWHT RFQ & Quotation Receipt | HE-SS-0030, ML1002 | HE-SS-0030: SS, ML1002: FS | HS-CN-750, HS-CN-710, HS-CN-0180 | HS-CN-750: FS, HS-CN-710: FS 15, HS-CN-0180: FS | 2023-09-07 | 2023-10-05
HS-CN-0190 | Completed | P2543-R01-Oct24..1.2.12.4 | NDT / PWHT Subcontract Award | HS-CN-0180 | HS-CN-0180: FS | ML1559-E01, C-56-PL-607-PI-1000, C-56-PL-607-PI-1400, C-56-PL-607-PI-2000, C-56-G-HT-PI-1000, C-56-G-HT-PI-1200, C-56-G-HT-PI-1400, C-56-G-HT-PI-2000, C-56-HC01-PL-ME-4000, C-56-PR-838-PI-1000, C-56-PR-838-PI-1200, C-56-PR-838-PI-1400, C-56-PR-838-PI-2000, | ML1559-E01: FS 30, C-56-PL-607-PI-1000: FS, C-56-PL-607-PI-1400: FS, C-56-PL-607-PI-2000: FS, C-56-G-HT-PI-1000: FS, C-56-G-HT-PI-1200: FS, C-56-G-HT-PI-1400: FS, C-56-G-HT-PI-2000: FS, C-56-HC01-PL-ME-4000: FS, C-56-PR-838-PI-1000: FS, C-56-PR-838-PI-1200 | 2023-11-03 | 2023-11-17
HS-CN-0180 | Completed | P2543-R01-Oct24..1.2.12.4 | NDT / PWHT Complete Evaluation (Internal) | HS-CN-0160 | HS-CN-0160: FS | HS-CN-0190 | HS-CN-0190: FS | 2023-10-06 | 2023-11-03
HS-CN-0240 | Completed | P2543-R01-Oct24..1.2.12.5 | CP Drilling & Earthing Drilling Subcontract Award | HS-CN-0230 | HS-CN-0230: FS | C-56-591-01-EI-1600, C-52-598-06-EI-1210, C-52-598-06-EI-1400, C-52-598-06-CA-1000, C-52-598-05-EI-1210, C-52-598-05-EI-1400, C-52-598-05-CA-1000, C-52-598-04-EI-1210, C-52-598-04-EI-1400, C-52-598-03-EI-1210, C-52-598-03-EI-1400, C-52-598-03-CA-1000, C-52 | C-56-591-01-EI-1600: FS, C-52-598-06-EI-1210: FS, C-52-598-06-EI-1400: FS, C-52-598-06-CA-1000: FS, C-52-598-05-EI-1210: FS, C-52-598-05-EI-1400: FS, C-52-598-05-CA-1000: FS, C-52-598-04-EI-1210: FS, C-52-598-04-EI-1400: FS, C-52-598-03-EI-1210: FS, C-52-5 | 2024-02-26 | 2024-03-27
HS-CN-0210 | Completed | P2543-R01-Oct24..1.2.12.5 | CP Drilling & Earthing Drilling RFQ & Quotation Receipt | HE-CP-230, ML1002 | HE-CP-230: FS 10, ML1002: FS | HS-CN-0230 | HS-CN-0230: FS | 2023-11-22 | 2024-01-02
HS-CN-0230 | Completed | P2543-R01-Oct24..1.2.12.5 | CP Drilling & Earthing Drilling Complete Evaluation (Internal) | HS-CN-0210 | HS-CN-0210: FS | HS-CN-0240 | HS-CN-0240: FS | 2024-01-03 | 2024-01-15
HS-CN-0290 | Completed | P2543-R01-Oct24..1.2.12.6 | FOC Splicing / Termination Subcontract Award | HS-CN-0280 | HS-CN-0280: FS | ML1030, C-56-PL-607-TE-1200, C-56-PL-607-TE-1400, C-56-PL-607-TE-1600, C-56-EB2-TE-1000, C-56-HC01-PL-TE-8200, C-56-HC01-PL-TE-8400, C-56-01HG-PL-TE-8200, C-56-01HG-PL-TE-8400, C-56-PR-838-TE-1000, C-56-591-01-TE-1000, C-52-06CR-PL-TE-8200, C-52-0506-PL-TE | ML1030: FS, C-56-PL-607-TE-1200: FS, C-56-PL-607-TE-1400: FS, C-56-PL-607-TE-1600: FS, C-56-EB2-TE-1000: FS, C-56-HC01-PL-TE-8200: FS, C-56-HC01-PL-TE-8400: SS, C-56-01HG-PL-TE-8200: FS, C-56-01HG-PL-TE-8400: FS, C-56-PR-838-TE-1000: FS, C-56-591-01-TE-100 | 2024-03-14 | 2024-03-20
HS-CN-0260 | Completed | P2543-R01-Oct24..1.2.12.6 | FOC Splicing / Termination RFQ & Quotation Receipt | ML1002, HP-BK-0060 | ML1002: FS, HP-BK-0060: FS | HS-CN-0280 | HS-CN-0280: FS | 2023-12-22 | 2023-12-29
HS-CN-0280 | Completed | P2543-R01-Oct24..1.2.12.6 | FOC Splicing / Termination Complete Evaluation (Internal) | HS-CN-0260 | HS-CN-0260: FS | HS-CN-0290 | HS-CN-0290: FS | 2024-02-26 | 2024-03-13
HS-CN-0410 | Completed | P2543-R01-Oct24..1.2.12.7 | OHPL RFQ & Quotation Receipt | ML1002, HE-IC-1010 | ML1002: FS, HE-IC-1010: FS 76 | HS-CN-0430 | HS-CN-0430: FS | 2024-01-03 | 2024-01-07
HS-CN-0430 | Completed | P2543-R01-Oct24..1.2.12.7 | OHPL Complete Evaluation (Internal) | HS-CN-0410 | HS-CN-0410: FS | HS-CN-0440 | HS-CN-0440: FS | 2024-01-08 | 2024-01-22
HS-CN-0440 | Completed | P2543-R01-Oct24..1.2.12.7 | OHPL Subcontract Award | HS-CN-0430 | HS-CN-0430: FS | C-52-OHPL-EL-1400, C-52-OHPL-EL-2000 | C-52-OHPL-EL-1400: FS, C-52-OHPL-EL-2000: FS | 2024-01-23 | 2024-01-26
HS-CN-0490 | Completed | P2543-R01-Oct24..1.2.12.10 | Earthworks Subcontract Award | HS-CN-0480 | HS-CN-0480: FS | C-52-06CR-PL-CI-1400 | C-52-06CR-PL-CI-1400: FS | 2023-10-06 | 2023-11-13
HS-CN-0460 | Completed | P2543-R01-Oct24..1.2.12.10 | Earthworks RFQ & Quotation Receipt | HE-CS-1570, ML1002 | HE-CS-1570: FS, ML1002: FS | HS-CN-0480 | HS-CN-0480: FS | 2023-08-31 | 2023-09-28
HS-CN-0480 | Completed | P2543-R01-Oct24..1.2.12.10 | Earthworks Complete Evaluation (Internal) | HS-CN-0460 | HS-CN-0460: FS | HS-CN-0490 | HS-CN-0490: FS | 2023-09-29 | 2023-10-05
HS-CN-0540 | Completed | P2543-R01-Oct24..1.2.12.11 | Hot Tapping Subcontract Award | HS-CN-0530 | HS-CN-0530: FS | HE-PL-0430, C-56-G-HT101-ME-1000, C-52-D-HT002-ME-1000, C-36-KM-HT03-ME-1000, C-36-KM-HT04-ME-1000 | HE-PL-0430: FS, C-56-G-HT101-ME-1000: FS, C-52-D-HT002-ME-1000: FS, C-36-KM-HT03-ME-1000: FS, C-36-KM-HT04-ME-1000: FS | 2023-12-12 | 2023-12-13
HS-CN-0510 | Completed | P2543-R01-Oct24..1.2.12.11 | Hot Tapping RFQ & Quotation Receipt | ML1002, HE-PR-0860 | ML1002: FS, HE-PR-0860: FS 14 | HS-CN-0530 | HS-CN-0530: FS | 2023-09-16 | 2023-10-13
HS-CN-0530 | Completed | P2543-R01-Oct24..1.2.12.11 | Hot Tapping Complete Evaluation (Internal) | HS-CN-0510 | HS-CN-0510: FS | HS-CN-0540 | HS-CN-0540: FS | 2023-10-13 | 2023-11-17
HS-CN-0590 | Completed | P2543-R01-Oct24..1.2.12.12 | Building Subcontract Award | HS-CN-0580 | HS-CN-0580: FS | C-56-EB2-ME-1000, C-56-EB2-ME-1010, C-56-EB2-ME-1200, C-52-EB1-ME-1000 | C-56-EB2-ME-1000: FS, C-56-EB2-ME-1010: FS, C-56-EB2-ME-1200: FS, C-52-EB1-ME-1000: FS | 2024-05-03 | 2024-05-09
HS-CN-0560 | Completed | P2543-R01-Oct24..1.2.12.12 | Building RFQ & Quotation Receipt | ML1002 | ML1002: FS | HS-CN-0580 | HS-CN-0580: FS | 2023-12-13 | 2024-01-03
HS-CN-0580 | Completed | P2543-R01-Oct24..1.2.12.12 | Building Complete Evaluation (Internal) | HS-CN-0560 | HS-CN-0560: FS | HS-CN-0590 | HS-CN-0590: FS | 2024-02-26 | 2024-05-02
HS-CN-0640 | Completed | P2543-R01-Oct24..1.2.12.13 | E&I Works Subcontract Award | HS-CN-0630 | HS-CN-0630: FS | C-56-EB2-ME-1000, C-56-EB2-ME-1010, C-56-PR-838-CA-1000, C-56-PR-838-CA-1030, C-56-PR-838-EI-2000, C-56-PR-838-EI-2010, C-56-PR-838-EI-2040, C-52-06CR-PL-TE-8200, C-52-EB1-ME-1000, C-52-OHPL-EL-1000 | C-56-EB2-ME-1000: FS, C-56-EB2-ME-1010: FS, C-56-PR-838-CA-1000: FS, C-56-PR-838-CA-1030: FS, C-56-PR-838-EI-2000: FS, C-56-PR-838-EI-2010: FS, C-56-PR-838-EI-2040: FS, C-52-06CR-PL-TE-8200: FS, C-52-EB1-ME-1000: FS, C-52-OHPL-EL-1000: FS | 2024-04-25 | 2024-05-09
HS-CN-0610 | Completed | P2543-R01-Oct24..1.2.12.13 | E&I Works RFQ & Quotation Receipt | HP-ME-0860, ML1002 | HP-ME-0860: FS, ML1002: FS | HS-CN-0630 | HS-CN-0630: FS | 2023-11-08 | 2023-12-11
HS-CN-0630 | Completed | P2543-R01-Oct24..1.2.12.13 | E&I Works Complete Evaluation (Internal) | HS-CN-0610 | HS-CN-0610: FS | HS-CN-0640 | HS-CN-0640: FS | 2024-03-31 | 2024-04-25
HS-CN-0690 | Completed | P2543-R01-Oct24..1.2.12.14 | Fence Works Subcontract Award | HS-CN-0680 | HS-CN-0680: FS | C-56-PL-607-CI-2000, C-56-PL-607-CI-3000, C-56-G-HT-CI-2000, C-56-G-HT-CI-1420, C-56-PR-838-CI-2000, C-56-PR-838-CI-3000, C-56-591-01-CI-2000, C-56-591-01-CI-3000, C-52-06CR-FENCE-1050, C-52-598-06-CI-2000, C-52-598-06-CI-3000, C-52-598-06-CI-3010, C-52-59 | C-56-PL-607-CI-2000: FS, C-56-PL-607-CI-3000: FS, C-56-G-HT-CI-2000: FS, C-56-G-HT-CI-1420: FS, C-56-PR-838-CI-2000: FS, C-56-PR-838-CI-3000: FS, C-56-591-01-CI-2000: FS, C-56-591-01-CI-3000: FS, C-52-06CR-FENCE-1050: FS, C-52-598-06-CI-2000: FS, C-52-598- | 2024-04-30 | 2024-06-07
HS-CN-0660 | Completed | P2543-R01-Oct24..1.2.12.14 | Fence Works RFQ & Quotation Receipt | ML1002 | ML1002: FS | HS-CN-0680 | HS-CN-0680: FS | 2023-12-08 | 2023-12-28
HS-CN-0680 | Completed | P2543-R01-Oct24..1.2.12.14 | Fence Works Complete Evaluation (Internal) | HS-CN-0660 | HS-CN-0660: FS | HS-CN-0690 | HS-CN-0690: FS | 2024-02-26 | 2024-04-29
HP-ME-0560 | Completed | P2543-R01-Oct24..1.1.2.LL.5.1 | RFQ, Receipt of Bid for Active/ Passive Cooled Shelter | HE-EL-0850 | HE-EL-0850: FS | HP-ME-0570, HE-EL-1210 | HP-ME-0570: FS, HE-EL-1210: FS | 2024-01-26 | 2024-02-13
HP-ME-0580 | Completed | P2543-R01-Oct24..1.1.2.LL.5.1 | Commercial Clarifications & Placement of PO for Active/ Passive Cooled Shelter | HP-ME-0570 | HP-ME-0570: FS | HM-ME-1120, ML1309-C15 | HM-ME-1120: FS, ML1309-C15: FF | 2024-06-06 | 2024-06-14
HP-ME-0570 | Completed | P2543-R01-Oct24..1.1.2.LL.5.1 | Prepare TBE and Company approval for Active/ Passive Cooled Shelter | HP-ME-0560, HE-EL-1210, HE-EL-1240 | HP-ME-0560: FS, HE-EL-1210: SS, HE-EL-1240: FF | HP-ME-0580 | HP-ME-0580: FS | 2024-05-17 | 2024-06-05
HP-ME-0610 | Completed | P2543-R01-Oct24..1.1.2.LL.4.1 | RFQ, Receipt of Bid for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0490, HE-TL-0550 | HE-TL-0490: FS, HE-TL-0550: FS | HP-ME-0620, HE-TL-0610 | HP-ME-0620: FS, HE-TL-0610: FS | 2023-11-29 | 2023-12-22
HP-ME-0630 | Completed | P2543-R01-Oct24..1.1.2.LL.4.1 | Commercial Clarifications & Placement of PO for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HP-ME-0620 | HP-ME-0620: FS | ML1339-C18, ML1028-C20, HM-ME-1260, HM-ME-1220 | ML1339-C18: FF, ML1028-C20: FS, HM-ME-1260: FS, HM-ME-1220: FS | 2024-05-30 | 2024-06-07
HP-ME-0620 | Completed | P2543-R01-Oct24..1.1.2.LL.4.1 | Prepare TBE and Company approval for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HP-ME-0610, HE-TL-0610 | HP-ME-0610: FS, HE-TL-0610: SS | HP-ME-0630 | HP-ME-0630: FS | 2024-01-10 | 2024-05-29
HP-ME-0660 | Completed | P2543-R01-Oct24..1.1.2.25.14.1 | RFQ, Receipt of Bid for Access Switch, Fiber Optic Patch Panel and Media Converter | HE-TL-0550, HE-TL-0490 | HE-TL-0550: FS, HE-TL-0490: FS | HE-TL-0610, HP-ME-0670 | HE-TL-0610: FS, HP-ME-0670: FS | 2024-02-26 | 2024-03-08
HP-ME-0680 | Completed | P2543-R01-Oct24..1.1.2.25.14.1 | Commercial Clarifications & Placement of PO for Access Switch, Fiber Optic Patch Panel and Media Converter | HP-ME-0670 | HP-ME-0670: FS | HM-ME-1320, HM-ME-1360 | HM-ME-1320: FS, HM-ME-1360: FS | 2024-05-30 | 2024-06-07
HP-ME-0670 | Completed | P2543-R01-Oct24..1.1.2.25.14.1 | Prepare TBE and Company approval for Access Switch, Fiber Optic Patch Panel and Media Converter | HP-ME-0660, HE-TL-0610 | HP-ME-0660: FS, HE-TL-0610: SS | HP-ME-0680 | HP-ME-0680: FS | 2024-05-03 | 2024-05-29
HP-ME-0730 | Completed | P2543-R01-Oct24..1.1.2.LL.18.1 | Commercial Clarifications & Placement of PO for Gas Detectors | HE-IC-1970, HP-ME-0720 | HE-IC-1970: FS, HP-ME-0720: FS | HM-ME-1420, ML1269-C12, HE-IC-0670 | HM-ME-1420: FS, ML1269-C12: FF, HE-IC-0670: FF | 2024-06-22 | 2024-06-24 17:30
HP-ME-0710 | Completed | P2543-R01-Oct24..1.1.2.LL.18.1 | RFQ, Receipt of Bid for Gas Detectors | HE-IC-1930, HE-IC-1870 | HE-IC-1930: FS, HE-IC-1870: FS | HE-IC-2350, HP-ME-0720 | HE-IC-2350: FS, HP-ME-0720: FS | 2024-03-20 | 2024-04-19
HP-ME-0720 | Completed | P2543-R01-Oct24..1.1.2.LL.18.1 | Prepare TBE and Company approval for Gas Detectors | HP-ME-0710, HE-IC-2350 | HP-ME-0710: FS, HE-IC-2350: SS | HP-ME-0730 | HP-ME-0730: FS | 2024-05-31 | 2024-06-21
HP-ME-0780 | Completed | P2543-R01-Oct24..1.1.2.25.15.1 | Commercial Clarifications & Placement of PO for Field Instruments | HP-ME-0770 | HP-ME-0770: FS | ML1269-C12, HM-ME-1520, HE-IC-0670 | ML1269-C12: FF, HM-ME-1520: FS, HE-IC-0670: FS | 2024-06-04 | 2024-06-12
HP-ME-0760 | Completed | P2543-R01-Oct24..1.1.2.25.15.1 | RFQ, Receipt of Bid for Field Instruments | HE-IC-1930 | HE-IC-1930: FS | HP-ME-0770, HE-IC-2410, HE-IC-2350 | HP-ME-0770: FS, HE-IC-2410: FS, HE-IC-2350: FS | 2024-02-02 | 2024-04-11
HP-ME-0770 | Completed | P2543-R01-Oct24..1.1.2.25.15.1 | Prepare TBE and Company approval for Field Instruments | HP-ME-0760, HE-IC-2410, HE-IC-2440 | HP-ME-0760: FS, HE-IC-2410: SS, HE-IC-2440: FF | HP-ME-0780 | HP-ME-0780: FS | 2024-04-12 | 2024-05-31
HP-ME-0830 | Completed | P2543-R01-Oct24..1.1.2.25.16.1 | Commercial Clarifications & Placement of PO for Junction Boxes | HP-ME-0820, HE-IC-2030 | HP-ME-0820: FS, HE-IC-2030: FS | HM-ME-1620 | HM-ME-1620: FS | 2024-09-23 07:30 | 2024-10-03 17:30
HP-ME-0810 | Completed | P2543-R01-Oct24..1.1.2.25.16.1 | RFQ, Receipt of Bid for Junction Boxes | HE-IC-1990, HE-HV-2840 | HE-IC-1990: FS, HE-HV-2840: FS | HP-ME-0820, HE-IC-2470, HE-HV-2890 | HP-ME-0820: FS, HE-IC-2470: FS, HE-HV-2890: FS | 2024-05-20 | 2024-06-14
HP-ME-0820 | Completed | P2543-R01-Oct24..1.1.2.25.16.1 | Prepare TBE and Company approval for Junction Boxes | HP-ME-0810 | HP-ME-0810: FS | HP-ME-0830 | HP-ME-0830: FS | 2024-06-15 | 2024-09-20 17:30
HP-ME-0870 | Completed | P2543-R01-Oct24..1.1.2.25.3.1 | Prepare TBE and Company approval for HVAC Equipment | HP-ME-0860, HE-HV-2890 | HP-ME-0860: FS, HE-HV-2890: SS | HP-ME-0880 | HP-ME-0880: FS | 2024-04-17 | 2024-05-03
HP-ME-0860 | Completed | P2543-R01-Oct24..1.1.2.25.3.1 | RFQ, Receipt of Bid for HVAC Equipment | HE-ME-0010, HE-ME-270, HE-IC-620, HE-HV-2840 | HE-ME-0010: FS, HE-ME-270: FS, HE-IC-620: FS, HE-HV-2840: FS | HP-ME-0870, HS-CN-0610 | HP-ME-0870: FS, HS-CN-0610: FS | 2024-04-08 | 2024-04-15
HP-ME-0880 | Completed | P2543-R01-Oct24..1.1.2.25.3.1 | Commercial Clarifications & Placement of PO for HVAC Equipment | HP-ME-0870 | HP-ME-0870: FS | ML1038-C20, HM-ME-1720, HM-ME-1760 | ML1038-C20: FF, HM-ME-1720: FS, HM-ME-1760: FS | 2024-05-03 | 2024-05-09
HP-ME-0930 | Completed | P2543-R01-Oct24..1.1.2.25.2.1 | Commercial Clarifications & Placement of PO for Fire Suppression System | HP-ME-0920 | HP-ME-0920: FS | ML1038-C20, HM-ME-1890, HM-ME-1850 | ML1038-C20: FF 80, HM-ME-1890: FS, HM-ME-1850: FS | 2024-09-06 07:30 | 2024-09-06 17:30
HP-ME-0920 | Completed | P2543-R01-Oct24..1.1.2.25.2.1 | Prepare TBE and Company approval for Fire Suppression System | HE-HS-1180, HP-ME-0910, HE-HS-1150 | HE-HS-1180: FF, HP-ME-0910: FS, HE-HS-1150: SS | HP-ME-0930 | HP-ME-0930: FS | 2024-08-15 07:30 | 2024-09-05 17:30
HP-ME-0910 | Completed | P2543-R01-Oct24..1.1.2.25.2.1 | RFQ, Receipt of Bid for Fire Suppression System | HE-HS-0370 | HE-HS-0370: FS | ML1549-D32, HP-ME-0920 | ML1549-D32: FF, HP-ME-0920: FS | 2024-06-10 | 2024-06-17
HP-ME-0980 | Completed | P2543-R01-Oct24..1.1.2.25.13.1 | Commercial Clarifications & Placement of PO for Fire Fighting & Safety Equipment | HE-HS-1130, HP-ME-0970 | HE-HS-1130: FS, HP-ME-0970: FS | ML1038-C20, HM-ME-1920 | ML1038-C20: FF, HM-ME-1920: FS | 2024-09-16 07:30 | 2024-09-20 17:30
HP-ME-0970 | Completed | P2543-R01-Oct24..1.1.2.25.13.1 | Prepare TBE and Company approval for Fire Fighting & Safety Equipment | HP-ME-0960, HE-HS-1150, HE-HS-1180 | HP-ME-0960: FS, HE-HS-1150: SS, HE-HS-1180: FF | HP-ME-0980 | HP-ME-0980: FS | 2024-08-30 07:30 | 2024-09-13
HP-ME-0960 | Completed | P2543-R01-Oct24..1.1.2.25.13.1 | RFQ, Receipt of Bid for Fire Fighting & Safety Equipment | HE-HS-1092 | HE-HS-1092: FS | HP-ME-0970, HE-HS-1150 | HP-ME-0970: FS, HE-HS-1150: FS | 2024-05-23 07:30 | 2024-06-15 17:30
HP-BK-0070 | Completed | P2543-R01-Oct24..1.1.2.LL.19.1 | Prepare TBE and Company approval for FOC Cables | HP-BK-0060 | HP-BK-0060: FS | HP-BK-0080 | HP-BK-0080: FS | 2024-01-23 | 2024-03-26
HP-BK-0060 | Completed | P2543-R01-Oct24..1.1.2.LL.19.1 | RFQ, Receipt of Bid for FOC Cables | HE-TL-0550 | HE-TL-0550: FS | HS-CN-0260, HP-BK-0070, HE-TL-0610 | HS-CN-0260: FS, HP-BK-0070: FS, HE-TL-0610: FS | 2023-11-29 | 2023-12-07
HP-BK-0080 | Completed | P2543-R01-Oct24..1.1.2.LL.19.1 | Commercial Clarifications & Placement of PO for FOC Cables | HP-BK-0070 | HP-BK-0070: FS | HM-EL-0110, ML1329-C17 | HM-EL-0110: FS, ML1329-C17: FF | 2024-03-31 | 2024-04-25
HP-ME-0030 | Completed | P2543-R01-Oct24..1.1.2.LL.22.1 | Commercial Clarifications & Placement of PO for Custody Metering Skid | HP-ME-0020, HE-IC-2150 | HP-ME-0020: FS, HE-IC-2150: FF | ML1259-C09, HM-ME-0050, HM-ME-0010 | ML1259-C09: FS, HM-ME-0050: FS, HM-ME-0010: FS | 2024-01-29 | 2024-02-16
HP-ME-0020 | Completed | P2543-R01-Oct24..1.1.2.LL.22.1 | Prepare TBE and Company approval for Custody Metering Skid | HP-ME-0010, HE-IC-2110, HE-IC-2140 | HP-ME-0010: FS, HE-IC-2110: SS, HE-IC-2140: FF | HP-ME-0030 | HP-ME-0030: FS | 2023-11-24 | 2024-01-26
HP-ME-0010 | Completed | P2543-R01-Oct24..1.1.2.LL.22.1 | RFQ, Receipt of Bid for Custody Metering Skid | HE-IC-1810 | HE-IC-1810: FS | HP-ME-0020, HE-IC-2110, HE-CS-0790 | HP-ME-0020: FS, HE-IC-2110: FS, HE-CS-0790: FS | 2023-11-03 | 2023-11-23
HP-ME-0060 | Completed | P2543-R01-Oct24..1.1.2.LL.21.1 | RFQ, Receipt of Bid for Pressure Reduction Skid | HE-IC-1690 | HE-IC-1690: FS | HP-ME-0070, HE-IC-2170 | HP-ME-0070: FS, HE-IC-2170: FS | 2023-11-02 | 2023-11-15
HP-ME-0080 | Completed | P2543-R01-Oct24..1.1.2.LL.21.1 | Commercial Clarifications & Placement of PO for Pressure Reduction Skid | HE-IC-2200, HP-ME-0070, HE-IC-2210 | HE-IC-2200: FS, HP-ME-0070: FS, HE-IC-2210: FF | HM-ME-0150, ML1039-C08, HM-ME-0110 | HM-ME-0150: FS, ML1039-C08: FS, HM-ME-0110: FS | 2024-01-29 | 2024-02-23
HP-ME-0070 | Completed | P2543-R01-Oct24..1.1.2.LL.21.1 | Prepare TBE and Company approval for Pressure Reduction Skid | HE-IC-2200, HP-ME-0060, HE-IC-2170 | HE-IC-2200: FF, HP-ME-0060: FS, HE-IC-2170: SS | HP-ME-0080 | HP-ME-0080: FS | 2023-11-16 | 2024-01-26
HP-ME-0110 | Completed | P2543-R01-Oct24..1.1.2.LL.17.1 | RFQ, Receipt of Bid for Leak Detection System | HE-IC-1750 | HE-IC-1750: FS | HP-ME-0120, HE-IC-2230 | HP-ME-0120: FS, HE-IC-2230: FS | 2023-11-29 | 2023-12-17
HP-ME-0130 | Completed | P2543-R01-Oct24..1.1.2.LL.17.1 | Commercial Clarifications & Placement of PO for Leak Detection System | HP-ME-0120 | HP-ME-0120: FS | HM-ME-0210, ML1289-C11 | HM-ME-0210: FS, ML1289-C11: FF | 2024-03-26 | 2024-03-29
HP-ME-0120 | Completed | P2543-R01-Oct24..1.1.2.LL.17.1 | Prepare TBE and Company approval for Leak Detection System | HP-ME-0110, HE-IC-2230 | HP-ME-0110: FS, HE-IC-2230: SS | HP-ME-0130 | HP-ME-0130: FS | 2023-12-18 | 2024-03-25
HP-ME-0160 | Completed | P2543-R01-Oct24..1.1.2.LL.11.1 | RFQ, Receipt of Bid for Filter Package | HE-ME-0130 | HE-ME-0130: FS | HE-ME-0190, HP-ME-0170, HE-ME-530 | HE-ME-0190: FS, HP-ME-0170: FS, HE-ME-530: FS | 2023-10-30 | 2023-11-07
HP-ME-0180 | Completed | P2543-R01-Oct24..1.1.2.LL.11.1 | Commercial Clarifications & Placement of PO for Filter Package | HE-ME-0220, HP-ME-0170, HE-ME-0230 | HE-ME-0220: FS, HP-ME-0170: FS, HE-ME-0230: SS | HM-ME-0310, HM-ME-0350 | HM-ME-0310: FS, HM-ME-0350: FS | 2023-12-18 | 2023-12-19
HP-ME-0170 | Completed | P2543-R01-Oct24..1.1.2.LL.11.1 | Prepare TBE and Company approval for Filter Package | HP-ME-0160, HE-ME-0190, HE-ME-0220 | HP-ME-0160: FS, HE-ME-0190: SS, HE-ME-0220: FF | HP-ME-0180 | HP-ME-0180: FS | 2023-11-08 | 2023-12-15
HP-ME-0210 | Completed | P2543-R01-Oct24..1.1.2.LL.12.1 | RFQ, Receipt of Bid for Pig Launchers & Receivers | HE-ME-480, HE-PR-0490 | HE-ME-480: FS, HE-PR-0490: FS | HP-ME-0220, HP-ME-0220, HP-ME-0230, CAB-4480 | HP-ME-0220: FS, HP-ME-0220: FF, HP-ME-0230: FS, CAB-4480: FS | 2023-11-02 | 2023-11-07
HP-ME-0230 | Completed | P2543-R01-Oct24..1.1.2.LL.12.1 | Commercial Clarifications & Placement of PO for Pig Launchers & Receivers | HP-ME-0220, HP-ME-0210 | HP-ME-0220: FS, HP-ME-0210: FS | HM-ME-0410, HM-ME-0450, ML1279-C05 | HM-ME-0410: FS, HM-ME-0450: FS, ML1279-C05: FF | 2023-12-20 | 2023-12-26
HP-ME-0220 | Completed | P2543-R01-Oct24..1.1.2.LL.12.1 | Prepare TBE and Company approval for Pig Launchers & Receivers | HP-ME-0210, HP-ME-0210, HE-ME-560 | HP-ME-0210: FS, HP-ME-0210: FF, HE-ME-560: FF | HP-ME-0230 | HP-ME-0230: FS | 2023-11-08 | 2023-12-18
HP-ME-0270 | Completed | P2543-R01-Oct24..1.1.2.LL.10.1 | Prepare TBE and Company approval for ROV/ GOV | HP-ME-0260, HE-IC-2290, HE-IC-2320 | HP-ME-0260: FS, HE-IC-2290: SS, HE-IC-2320: FF | HP-ME-0280 | HP-ME-0280: FS | 2023-11-11 | 2024-01-26
HP-ME-0260 | Completed | P2543-R01-Oct24..1.1.2.LL.10.1 | RFQ, Receipt of Bid for ROV/ GOV | HE-IC-1630 | HE-IC-1630: FS | HP-ME-0270, HE-IC-2290 | HP-ME-0270: FS, HE-IC-2290: FS | 2023-10-30 | 2023-11-10
HP-ME-0280 | Completed | P2543-R01-Oct24..1.1.2.LL.10.1 | Commercial Clarifications & Placement of PO for ROV/ GOV | HE-IC-2320, HP-ME-0270, HE-IC-1670 | HE-IC-2320: FS, HP-ME-0270: FS, HE-IC-1670: FS | HM-ME-0510, ML1022-C07, HM-ME-0550, ML1349-C19 | HM-ME-0510: FS, ML1022-C07: FS, HM-ME-0550: FS, ML1349-C19: FS | 2024-03-10 | 2024-03-25
HP-ME-0310 | Completed | P2543-R01-Oct24..1.1.2.LL.9.1 | RFQ, Receipt of Bid for MOV | HE-IC-1570 | HE-IC-1570: FS | HE-IC-2050, HP-ME-0320, HP-ME-0330 | HE-IC-2050: FS, HP-ME-0320: FS, HP-ME-0330: FS 30 | 2023-10-30 | 2023-11-10
HP-ME-0330 | Completed | P2543-R01-Oct24..1.1.2.LL.9.1 | Commercial Clarifications & Placement of PO for MOV | HP-ME-0320, HP-ME-0310 | HP-ME-0320: FS, HP-ME-0310: FS 30 | ML1349-C19, HM-ME-0650, HM-ME-0610, ML1022-C07 | ML1349-C19: FS, HM-ME-0650: FS, HM-ME-0610: FS, ML1022-C07: FS | 2024-03-18 | 2024-03-27
HP-ME-0320 | Completed | P2543-R01-Oct24..1.1.2.LL.9.1 | Prepare TBE and Company approval for MOV | HE-IC-2060, HP-ME-0310, HE-IC-2050, HE-IC-2080 | HE-IC-2060: FF, HP-ME-0310: FS, HE-IC-2050: SS, HE-IC-2080: FF | ML1038-C20, HP-ME-0330 | ML1038-C20: FF, HP-ME-0330: FS | 2023-11-11 | 2024-03-17
HP-ME-0360 | Completed | P2543-R01-Oct24..1.1.2.LL.8.1 | RFQ, Receipt of Bid for AC UPS | HE-EL-0920, HE-EL-0910 | HE-EL-0920: FS, HE-EL-0910: FS | HP-ME-0370, HE-EL-1330 | HP-ME-0370: FS, HE-EL-1330: FS | 2023-12-12 | 2023-12-15
HP-ME-0380 | Completed | P2543-R01-Oct24..1.1.2.LL.8.1 | Commercial Clarifications & Placement of PO for AC UPS | HP-ME-0370 | HP-ME-0370: FS | HM-ME-0760, HM-ME-0720, ML1319-C16 | HM-ME-0760: FS, HM-ME-0720: FS, ML1319-C16: FF | 2024-03-04 | 2024-03-25
HP-ME-0370 | Completed | P2543-R01-Oct24..1.1.2.LL.8.1 | Prepare TBE and Company approval for AC UPS | HP-ME-0360, HE-EL-1330, HE-EL-1360 | HP-ME-0360: FS, HE-EL-1330: SS, HE-EL-1360: FF | HP-ME-0380 | HP-ME-0380: FS | 2023-12-15 | 2024-03-20
HP-ME-0410 | Completed | P2543-R01-Oct24..1.1.2.25.7.1 | RFQ, Receipt of Bid for Power Distribution Boards | HE-EL-0970 | HE-EL-0970: FS | HE-EL-1390, HP-ME-0420, HE-EL-1390 | HE-EL-1390: FS, HP-ME-0420: FS, HE-EL-1390: FF | 2024-04-05 | 2024-05-16
HP-ME-0430 | Completed | P2543-R01-Oct24..1.1.2.25.7.1 | Commercial Clarifications & Placement of PO for Power Distribution Boards | HP-ME-0420 | HP-ME-0420: FS | HM-ME-0860, HM-ME-0820 | HM-ME-0860: FS, HM-ME-0820: FS | 2024-08-19 07:30 | 2024-08-23 17:30
HP-ME-0420 | Completed | P2543-R01-Oct24..1.1.2.25.7.1 | Prepare TBE and Company approval for Power Distribution Boards | HP-ME-0410, HE-EL-1390, HE-EL-1420 | HP-ME-0410: FS, HE-EL-1390: SS, HE-EL-1420: FF | HP-ME-0430 | HP-ME-0430: FS | 2024-05-27 | 2024-08-18 17:30
HP-ME-0460 | Completed | P2543-R01-Oct24..1.1.2.25.1.1 | RFQ, Receipt of Bid for Distribution Transformer | HE-EL-1030 | HE-EL-1030: FS | HP-ME-0470, HE-EL-1450 | HP-ME-0470: FS, HE-EL-1450: FS | 2023-12-04 | 2023-12-05
HP-ME-0480 | Completed | P2543-R01-Oct24..1.1.2.25.1.1 | Commercial Clarifications & Placement of PO for Distribution Transformer | HP-ME-0470 | HP-ME-0470: FS | HM-ME-0920, HM-ME-0960 | HM-ME-0920: FS, HM-ME-0960: FS | 2024-03-06 | 2024-04-19
HP-ME-0470 | Completed | P2543-R01-Oct24..1.1.2.25.1.1 | Prepare TBE and Company approval for Distribution Transformer | HP-ME-0460, HE-EL-1450 | HP-ME-0460: FS, HE-EL-1450: SS | HP-ME-0480 | HP-ME-0480: FS | 2024-01-05 | 2024-03-05
HP-ME-0510 | Completed | P2543-R01-Oct24..1.1.2.LL.6.1 | RFQ, Receipt of Bid for Solar PV system | HE-EL-1090 | HE-EL-1090: FS | HP-ME-0520, HE-EL-1270 | HP-ME-0520: FS, HE-EL-1270: FS | 2024-02-03 | 2024-02-28
HP-ME-0530 | Completed | P2543-R01-Oct24..1.1.2.LL.6.1 | Commercial Clarifications & Placement of PO for Solar PV system | HP-ME-0520 | HP-ME-0520: FS | HE-CS-0850, HM-ME-1020, ML1026-C13, HM-ME-1060 | HE-CS-0850: SS, HM-ME-1020: FS, ML1026-C13: FF, HM-ME-1060: FS | 2024-06-13 | 2024-06-14
HP-ME-0520 | Completed | P2543-R01-Oct24..1.1.2.LL.6.1 | Prepare TBE and Company approval for Solar PV system | HP-ME-0510, HE-EL-1120, HE-EL-1270 | HP-ME-0510: FS, HE-EL-1120: FF, HE-EL-1270: SS | HP-ME-0530 | HP-ME-0530: FS | 2024-02-23 | 2024-06-12
HP-ME-1020 | Completed | P2543-R01-Oct24..1.1.1.16.1 | RFQ, Receipt of Bid for Line Pipes (Coated) | HE-PL-1630 | HE-PL-1630: FS | HP-ME-1030, HE-PL-2050 | HP-ME-1030: FS, HE-PL-2050: FS | 2023-08-03 | 2023-08-10
HP-ME-1040 | Completed | P2543-R01-Oct24..1.1.1.16.1 | Commercial Clarifications & Placement of PO for Line Pipes (Coated) | HE-PL-1670, HE-PL-2070, HP-ME-1030 | HE-PL-1670: FF, HE-PL-2070: FS, HP-ME-1030: FS | CTF-SO1000, HM-PL-0050, ML1040-C01, HM-PL-0010 | CTF-SO1000: FS, HM-PL-0050: FS, ML1040-C01: FS, HM-PL-0010: FS | 2023-08-25 | 2023-08-25
HP-ME-1030 | Completed | P2543-R01-Oct24..1.1.1.16.1 | Prepare TBE and Company approval for Line Pipes (Coated) | HP-ME-1020, HE-PL-2060, HE-PL-2050 | HP-ME-1020: FS, HE-PL-2060: FF, HE-PL-2050: SS | HP-ME-1040 | HP-ME-1040: FS | 2023-08-10 | 2023-08-24
HP-ME-1070 | Completed | P2543-R01-Oct24..1.1.BK.1.1 | RFQ, Receipt of Bid for Manual/Ball/ Globe/ Check/ Plug Valves | HE-PI-1020, HE-PL-1690 | HE-PI-1020: FS, HE-PL-1690: FS | HP-ME-1080, HE-PI-1080, HE-PL-2270 | HP-ME-1080: FS, HE-PI-1080: FS, HE-PL-2270: FS | 2023-12-01 | 2024-01-26
HP-ME-1090 | Completed | P2543-R01-Oct24..1.1.BK.1.1 | Commercial Clarifications & Placement of PO for Manual/ Ball/ Globe/ Check/ Plug Valves | HP-ME-1080, HE-PI-1060, HE-PI-1110 | HP-ME-1080: FS, HE-PI-1060: FS, HE-PI-1110: FS | HM-PL-0190, HM-PL-0150, ML1043-C14, ML1369-C21 | HM-PL-0190: FS, HM-PL-0150: FS, ML1043-C14: FF, ML1369-C21: FF | 2024-03-23 | 2024-03-29
HP-ME-1080 | Completed | P2543-R01-Oct24..1.1.BK.1.1 | Prepare TBE and Company approval for Manual/ Ball/ Globe/ Check/ Plug Valves | HP-ME-1070, HE-PI-1080, HE-PI-1110, HE-PL-2270, HE-PL-2300 | HP-ME-1070: FS, HE-PI-1080: SS, HE-PI-1110: FF, HE-PL-2270: SS, HE-PL-2300: FF | HP-ME-1090 | HP-ME-1090: FS | 2024-03-16 | 2024-03-22
HP-ME-1140 | Completed | P2543-R01-Oct24..1.1.1.19.1 | Commercial Clarifications & Placement of PO for Pig Signaler | HP-ME-1130 | HP-ME-1130: FS | HM-PL-0460 | HM-PL-0460: FS | 2024-05-08 | 2024-05-22
HP-ME-1120 | Completed | P2543-R01-Oct24..1.1.1.19.1 | RFQ, Receipt of Bid for Pig Signaler | HE-PL-1930 | HE-PL-1930: FS | HE-PL-2330, HP-ME-1130 | HE-PL-2330: FS, HP-ME-1130: FS | 2024-02-26 | 2024-03-22
HP-ME-1130 | Completed | P2543-R01-Oct24..1.1.1.19.1 | Prepare TBE and Company approval for Pig Signaler | HP-ME-1120, HE-PL-2330, HE-PL-2360 | HP-ME-1120: FS, HE-PL-2330: SS, HE-PL-2360: FF | HP-ME-1140 | HP-ME-1140: FS | 2024-03-18 | 2024-05-07
HP-ME-1190 | Completed | P2543-R01-Oct24..1.1.1.1.1 | Commercial Clarifications & Placement of PO for Hot Induction Bend | HE-PL-1790, HP-ME-1180, ML1189-B16 | HE-PL-1790: FS, HP-ME-1180: FS, ML1189-B16: FS | HM-PL-0560, ML1229-C02, HM-PL-0600 | HM-PL-0560: FS, ML1229-C02: FS, HM-PL-0600: FS | 2023-09-28 | 2023-10-02
HP-ME-1180 | Completed | P2543-R01-Oct24..1.1.1.1.1 | Prepare TBE and Company approval for Hot Incution Bend | HP-ME-1170, HE-PL-2090, HE-PL-2120 | HP-ME-1170: FS, HE-PL-2090: SS, HE-PL-2120: FF | HP-ME-1190 | HP-ME-1190: FS | 2023-09-22 | 2023-09-27
HP-ME-1170 | Completed | P2543-R01-Oct24..1.1.1.1.1 | RFQ, Receipt of Bid for Hot Incution Bend | HE-PL-1750 | HE-PL-1750: FS | HP-ME-1180, HE-PL-2090 | HP-ME-1180: FS, HE-PL-2090: FS | 2023-09-05 | 2023-09-18
HP-ME-1230 | Completed | P2543-R01-Oct24..1.1.1.3.1 | Prepare TBE and Company approval for Isolating Joints | HP-ME-1220, HE-PL-2210, HE-PL-2240 | HP-ME-1220: FS, HE-PL-2210: SS, HE-PL-2240: FF | HP-ME-1240 | HP-ME-1240: FS | 2023-10-11 | 2023-11-15
HP-ME-1240 | Completed | P2543-R01-Oct24..1.1.1.3.1 | Commercial Clarifications & Placement of PO for Isolating Joints | HP-ME-1230, HE-PL-1910 | HP-ME-1230: FS, HE-PL-1910: FS | ML1249-C06, HM-PL-0670, HM-PL-0710, ML1041-C03 | ML1249-C06: FF, HM-PL-0670: FS, HM-PL-0710: FS, ML1041-C03: FS | 2023-11-16 | 2023-11-23
HP-ME-1220 | Completed | P2543-R01-Oct24..1.1.1.3.1 | RFQ, Receipt of Bid for Isolating Joints | HE-PL-1870 | HE-PL-1870: FS | HE-PL-2210, HP-ME-1230 | HE-PL-2210: FS, HP-ME-1230: FS | 2023-09-29 | 2023-10-10
HP-ME-1290 | Completed | P2543-R01-Oct24..1.1.1.2.1 | Commercial Clarifications & Placement of PO for Pigging & Split Tee | HP-ME-1280, HE-PL-1850 | HP-ME-1280: FS, HE-PL-1850: FS | ML1239-C04, HM-PL-0770, HM-PL-0810 | ML1239-C04: FF, HM-PL-0770: FS, HM-PL-0810: FS | 2024-03-31 | 2024-04-25
HP-ME-1270 | Completed | P2543-R01-Oct24..1.1.1.2.1 | RFQ, Receipt of Bid for Pigging & Split Tee | HE-PL-1810, HE-PL-3650 | HE-PL-1810: FS, HE-PL-3650: FS | HE-PL-2150, HP-ME-1280 | HE-PL-2150: FS, HP-ME-1280: FS | 2024-01-26 | 2024-02-09
HP-ME-1280 | Completed | P2543-R01-Oct24..1.1.1.2.1 | Prepare TBE and Company approval for Pigging & Split Tee | HP-ME-1270, HE-PL-2150, HE-PL-2180, HE-PL-3680 | HP-ME-1270: FS, HE-PL-2150: SS, HE-PL-2180: FF, HE-PL-3680: FF | HP-ME-1290 | HP-ME-1290: FS | 2024-02-26 | 2024-03-26
HP-BK-0020 | Completed | P2543-R01-Oct24..1.1.BK.17.1 | Prepare TBE and Company approval for Power & Control Cables | HP-BK-0010 | HP-BK-0010: FS | HP-BK-0030 | HP-BK-0030: FS | 2024-05-03 | 2024-08-13 17:30
HP-BK-0010 | Completed | P2543-R01-Oct24..1.1.BK.17.1 | RFQ, Receipt of Bid for Power & Control Cables | HE-EL-1150 | HE-EL-1150: FS | HE-EL-1510, HP-BK-0020, HE-EL-2260, HE-EL-2310, HE-EL-2360, HE-EL-2410 | HE-EL-1510: FS, HP-BK-0020: FS, HE-EL-2260: FS, HE-EL-2310: FS, HE-EL-2360: FS, HE-EL-2410: FS | 2024-04-29 | 2024-05-03
HP-BK-0030 | Completed | P2543-R01-Oct24..1.1.BK.17.1 | Commercial Clarifications & Placement of PO for Power & Control Cables | HP-BK-0020 | HP-BK-0020: FS | HM-EL-0010 | HM-EL-0010: FS | 2024-08-14 07:30 | 2024-08-23 17:30
HP-BK-0130 | Completed | P2543-R01-Oct24..1.1.BK.13.1 | Commercial Clarifications & Placement of PO for Cable Trays | HP-BK-0120 | HP-BK-0120: FS | HM-EL-0250, HM-EL-0210 | HM-EL-0250: FS, HM-EL-0210: FS | 2024-09-04 07:30 | 2024-09-25 17:30
HP-BK-0120 | Completed | P2543-R01-Oct24..1.1.BK.13.1 | Prepare TBE and Company approval for Cable Trays | HP-BK-0110, HE-EL-1510 | HP-BK-0110: FS, HE-EL-1510: SS | HP-BK-0130 | HP-BK-0130: FS | 2024-08-14 07:30 | 2024-08-29 17:30
HP-BK-0110 | Completed | P2543-R01-Oct24..1.1.BK.13.1 | RFQ, Receipt of Bid for Cable Trays | HE-EL-1630 | HE-EL-1630: FS | ML1549-D32, HP-BK-0120 | ML1549-D32: FF, HP-BK-0120: FS | 2024-07-30 07:30 | 2024-08-11 17:30
HP-BK-0160 | Completed | P2543-R01-Oct24..1.1.BK.15.1 | RFQ, Receipt of Bid for Earthing Material | HE-EL-1630 | HE-EL-1630: FS | ML1549-D32, HP-BK-0170 | ML1549-D32: FF, HP-BK-0170: FS | 2024-04-29 07:30 | 2024-05-06 17:30
HP-BK-0180 | Not Started | P2543-R01-Oct24..1.1.BK.15.1 | Commercial Clarifications & Placement of PO for Earthing Material | HP-BK-0170, HE-EL-2450 | HP-BK-0170: FS, HE-EL-2450: FS | HM-EL-0350, HM-EL-0310 | HM-EL-0350: FS, HM-EL-0310: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HP-BK-0170 | Completed | P2543-R01-Oct24..1.1.BK.15.1 | Prepare TBE and Company approval for Earthing Material | HP-BK-0160, HE-EL-2410, HE-EL-2440 | HP-BK-0160: FS, HE-EL-2410: SS, HE-EL-2440: FF | HP-BK-0180 | HP-BK-0180: FS | 2024-05-06 17:30 | 2024-08-22 17:30
HP-BK-0230 | Not Started | P2543-R01-Oct24..1.1.BK.16.1 | Commercial Clarifications & Placement of PO for MCT | HP-BK-0220, HE-EL-2250 | HP-BK-0220: FS, HE-EL-2250: FS | HM-EL-0410, HM-EL-0450 | HM-EL-0410: FS, HM-EL-0450: FS | 2024-11-25 07:30 | 2024-11-29 17:30
HP-BK-0220 | In Progress | P2543-R01-Oct24..1.1.BK.16.1 | Prepare TBE and Company approval for MCT | HP-BK-0210, HE-EL-2210 | HP-BK-0210: FS, HE-EL-2210: SS | HP-BK-0230 | HP-BK-0230: FS | 2024-05-24 | 2024-11-22 17:30
HP-BK-0210 | Completed | P2543-R01-Oct24..1.1.BK.16.1 | RFQ, Receipt of Bid for MCT | HE-EL-1960 | HE-EL-1960: FS | ML1549-D32, HP-BK-0220 | ML1549-D32: FF, HP-BK-0220: FS | 2024-05-31 07:30 | 2024-06-09 17:30
HP-BK-0270 | Not Started | P2543-R01-Oct24..1.1.BK.11.1 | Final Civil Bulk material MTO | HE-CS-1550 | HE-CS-1550: FF | HM-CS-0020 | HM-CS-0020: FF 5 | 2024-11-18 07:30 | 2024-12-10 17:30
HP-BK-0260 | Completed | P2543-R01-Oct24..1.1.BK.11.1 | 1st Civil Bulk material MTO | HE-CS-1510, HE-CS-0230 | HE-CS-1510: FS, HE-CS-0230: FS | HM-CS-0010 | HM-CS-0010: FS | 2024-05-02 07:30 | 2024-05-19 17:30
HP-BK-0310 | Not Started | P2543-R01-Oct24..1.1.BK.5.1 | Final Structural Bulk material MTO | HE-CS-1550 | HE-CS-1550: FS | HM-CS-0090 | HM-CS-0090: FS | 2024-12-11 07:30 | 2024-12-31 17:30
HP-BK-0300 | Not Started | P2543-R01-Oct24..1.1.BK.5.1 | 1st Structural Bulk material MTO | HE-CS-1510 | HE-CS-1510: FS | HM-CS-0080 | HM-CS-0080: FS | 2024-10-28 07:30 | 2024-11-15 17:30
HP-BK-0350 | Completed | P2543-R01-Oct24..1.1.BK.4.1 | Final Piping Bulk material MTO | HE-PI-1300, HE-PI-1400 | HE-PI-1300: FF, HE-PI-1400: FS | HM-PI-0020 | HM-PI-0020: FS | 2024-10-01 07:30 | 2024-10-10 17:30
HP-BK-0340 | Completed | P2543-R01-Oct24..1.1.BK.4.1 | 1st Piping Bulk material MTO | HE-PI-1260 | HE-PI-1260: FS | HM-PI-0010 | HM-PI-0010: FS | 2024-03-31 | 2024-04-25
HP-BK-0390 | Completed | P2543-R01-Oct24..1.1.BK.6.1 | Final Pipeline Bulk material MTO | HE-PL-3270 | HE-PL-3270: FS | HM-PL-0860 | HM-PL-0860: FS | 2024-07-29 07:30 | 2024-08-02 17:30
HP-BK-0380 | Completed | P2543-R01-Oct24..1.1.BK.6.1 | 1st Pipeline Bulk material MTO | HE-PL-3230, HE-PL-3260 | HE-PL-3230: FS, HE-PL-3260: FS | HM-PL-0850 | HM-PL-0850: FS | 2024-08-07 07:30 | 2024-08-26 17:30
HP-BK-0430 | In Progress | P2543-R01-Oct24..1.1.BK.7.1 | Final Electrical Bulk material MTO | HE-EL-1850 | HE-EL-1850: FF | HM-EL-0500 | HM-EL-0500: FS | 2024-10-15 07:30 | 2025-01-08 17:30
HP-BK-0420 | Completed | P2543-R01-Oct24..1.1.BK.7.1 | 1st Electrical Bulk material MTO | HE-EL-1810 | HE-EL-1810: FS | HM-EL-0490 | HM-EL-0490: FS | 2024-08-19 07:30 | 2024-09-26 17:30
HP-BK-0470 | In Progress | P2543-R01-Oct24..1.1.BK.8.1 | Final Instrumentation Bulk material MTO | HE-IC-2630 | HE-IC-2630: FF | HM-IC-0020 | HM-IC-0020: FS | 2024-10-01 07:30 | 2024-11-22 17:30
HP-BK-0460 | Completed | P2543-R01-Oct24..1.1.BK.8.1 | 1st Instrumentation Bulk material MTO | HE-IC-2590 | HE-IC-2590: FS | HM-IC-0010 | HM-IC-0010: FS | 2024-10-15 07:30 | 2024-10-21 17:30
HP-BK-0510 | In Progress | P2543-R01-Oct24..1.1.BK.9.1 | Final Telecom Bulk material MTO | HE-TL-0890, HE-TL-930 | HE-TL-0890: FF, HE-TL-930: FF | HM-TL-0020 | HM-TL-0020: FS | 2024-10-15 07:30 | 2024-12-24 17:30
HP-BK-0500 | Completed | P2543-R01-Oct24..1.1.BK.9.1 | 1st Telecom Bulk material MTO | HE-TL-0850 | HE-TL-0850: FS | HM-TL-0010 | HM-TL-0010: FS | 2024-10-01 07:30 | 2024-10-14 17:30
ML1050 | Not Started | P2543-R01-Oct24..ML | Achieve PAC-2 for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | CCM-PM4540, CCM-PM4530, CCM-PM4520, ML2049-F06 | CCM-PM4540: FF, CCM-PM4530: FF, CCM-PM4520: FF, ML2049-F06: FF | ML1060 | ML1060: FF |  | 2026-01-09 10:58
ML1002 | Completed | P2543-R01-Oct24..ML | Project Kick off Meeting | ML1001, PRJ-MI-1000 | ML1001: SS 9, PRJ-MI-1000: FS 8 | HE-PL-1150, HM-PL-0080, CTF-SO1080, HE-WS-0070, HC-GN-300, CTF-SO1000, HS-CN-0410, HE-SS-0020, HS-CN-0460, HS-CN-0260, HS-CN-0660, HS-CN-0510, HE-SS-0010, HM-ME-1690, HM-ME-1590, ML1559-E01, HS-CN-0560, HC-GN-0010, HS-CN-0610, HS-CN-0210, HE-PL-0070, HE-PL | HE-PL-1150: SS, HM-PL-0080: FS, CTF-SO1080: FS, HE-WS-0070: SS 45, HC-GN-300: SS 30, CTF-SO1000: FS, HS-CN-0410: FS, HE-SS-0020: FS, HS-CN-0460: FS, HS-CN-0260: FS, HS-CN-0660: FS, HS-CN-0510: FS, HE-SS-0010: FS, HM-ME-1690: FS, HM-ME-1590: FS, ML1559-E01: | 2023-07-19
ML1060 | Not Started | P2543-R01-Oct24..ML | Project Finish | HM-PL-0120, CAB-4420, CAB-5290, CAB-4460, CAB-4430, CAB-4440, ML1799-E25, ML1056-D14, CAB-4470, ML1459-D12, ML1054-D09, ML1899-E35, ML1429-D17, CAB-5320, ML1469-D13, ML1689-E14, ML1629-E08, ML1729-E18, ML1959-E41, ML1819-E27, CAB-4480, ML1030, ML1789-E24, | HM-PL-0120: FS, CAB-4420: FS, CAB-5290: FS, CAB-4460: FS, CAB-4430: FS, CAB-4440: FS, ML1799-E25: FS, ML1056-D14: FS, CAB-4470: FS, ML1459-D12: FS, ML1054-D09: FS, ML1899-E35: FS, ML1429-D17: FS, CAB-5320: FS, ML1469-D13: FS, ML1689-E14: FS, ML1629-E08: FS |  |  |  | 2026-01-09 10:58
ML1020 | Not Started | P2543-R01-Oct24..ML | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | HM-CS-0110, ML1959-E41, C-56-HC01-PL-CI-7810, C-56-HC01-PL-CI-8010 | HM-CS-0110: FS, ML1959-E41: FF, C-56-HC01-PL-CI-7810: FS, C-56-HC01-PL-CI-8010: FS | ML1030, ML1040 | ML1030: FF, ML1040: FF |  | 2025-10-09 15:00
ML1030 | Not Started | P2543-R01-Oct24..ML | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-TL-0830, ML1033-B22, HS-CN-0290, HE-TL-0470, HE-TL-0770, HM-TL-0040, HE-TL-0710, HM-CS-0110, HE-EL-0530, HM-ME-0790, HE-IC-0770, HM-IC-0040, HE-EL-0710, HE-EL-0290, HE-IC-1550, HE-EL-0650, HM-EL-0520, HM-ME-1590, HE-EL-0640, HE-IC-0530, HE-EL-1670, HM-E | HE-TL-0830: FS, ML1033-B22: FS, HS-CN-0290: FS, HE-TL-0470: FS, HE-TL-0770: FS, HM-TL-0040: FS, HE-TL-0710: FS, HM-CS-0110: FS, HE-EL-0530: FS, HM-ME-0790: FS, HE-IC-0770: FS, HM-IC-0040: FS, HE-EL-0710: FS, HE-EL-0290: FS, HE-IC-1550: FS, HE-EL-0650: FS, | ML1040, ML1060, CAB-4450, CAB-4410, CAB-4460, CAB-4430, CAB-4480, CAB-4400, CAB-4470, CAB-4440, CAB-4420 | ML1040: FF, ML1060: FF 1, CAB-4450: FF 15, CAB-4410: FF 3, CAB-4460: FF 18, CAB-4430: FF 9, CAB-4480: FF, CAB-4400: FF, CAB-4470: FF, CAB-4440: FF 12, CAB-4420: FF 6 |  | 2025-11-09 11:30
ML1040 | Not Started | P2543-R01-Oct24..ML | Achieve PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | ML1030, CCM-PM4550, ML2019-F03, ML1999-F01, ML1020, ML2029-F04, CCM-PM4510, HE-CP-340 | ML1030: FF, CCM-PM4550: FF, ML2019-F03: FF, ML1999-F01: FF, ML1020: FF, ML2029-F04: FF, CCM-PM4510: FS, HE-CP-340: FF | ML1060 | ML1060: FF 14 |  | 2025-12-09 15:00
ML1139-A06 | Completed | P2543-R01-Oct24..ML.GE | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (56" Pipeline) | HE-PL-0170 | HE-PL-0170: FF 50 | ML1579-E03, C-56-HC01-PL-ME-4800, C-56-01HG-PL-CA-5220, C-56-01HG-PL-CA-5420, C-56-01HG-PL-ME-4800, C-56-01HG-PL-ME-5000 | ML1579-E03: FS, C-56-HC01-PL-ME-4800: FF, C-56-01HG-PL-CA-5220: FS, C-56-01HG-PL-CA-5420: FS, C-56-01HG-PL-ME-4800: FF, C-56-01HG-PL-ME-5000: FF |  | 2024-08-28
ML1149-A07 | Completed | P2543-R01-Oct24..ML.GE | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | ML1011-A05, HE-PL-0230, ML1001-A01 | ML1011-A05: FF, HE-PL-0230: FF, ML1001-A01: FF | ML1579-E03, ML1679-E13, C-56-HC01-PL-ME-4800, C-56-01HG-PL-CA-5220, C-56-01HG-PL-CA-5420, C-56-01HG-PL-ME-4800, C-56-01HG-PL-ME-5000, C-52-06CR-PL-CA-5200, C-52-06CR-PL-ME-7400, C-52-0506-PL-CA-5200, C-52-0506-PL-ME-7400, C-52-0405-PL-CA-5200, C-52-0405-PL | ML1579-E03: FS, ML1679-E13: FS, C-56-HC01-PL-ME-4800: FF, C-56-01HG-PL-CA-5220: FS, C-56-01HG-PL-CA-5420: FS, C-56-01HG-PL-ME-4800: FF, C-56-01HG-PL-ME-5000: FF, C-52-06CR-PL-CA-5200: FF, C-52-06CR-PL-ME-7400: FF, C-52-0506-PL-CA-5200: FF, C-52-0506-PL-ME- |  | 2024-08-28 17:30
ML1159-A08 | Completed | P2543-R01-Oct24..ML.GE | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (4" Nitrogen Pipeline) | CTF-1010 | CTF-1010: FF | ML1011-A05, C-4N-H5HG-PIPEL-1000, C-4N-H5HG-PIPEL-4800, C-4N-H5HG-PIPEL-5000, C-4N-H5HG-PIPEL-5200, C-4N-H5HG-PIPEL-5220, C-4N-H5-TPL-CI-0100 | ML1011-A05: FF, C-4N-H5HG-PIPEL-1000: FS, C-4N-H5HG-PIPEL-4800: FF, C-4N-H5HG-PIPEL-5000: FF, C-4N-H5HG-PIPEL-5200: FS, C-4N-H5HG-PIPEL-5220: FS, C-4N-H5-TPL-CI-0100: FS |  | 2024-03-15 07:30
ML1169-A09 | Completed | P2543-R01-Oct24..ML.GE | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (4" Water line) | HE-PL-0290 | HE-PL-0290: FF 40 | C-4W-SVHG-PIPEL-1000 | C-4W-SVHG-PIPEL-1000: FS |  | 2024-03-15 07:30
ML1001-A01 | Completed | P2543-R01-Oct24..ML.GE | Issue Project Execution Plan (PEP), Coordination, Engineering, Procurement, HSE and Quality Procedures-Final Issue | HC-GN-0110, HC-GN-0230, HE-HS-0050 | HC-GN-0110: FS, HC-GN-0230: FS, HE-HS-0050: FS | HM-PL-0080, CAB-5290, ML1149-A07 | HM-PL-0080: FS, CAB-5290: FS, ML1149-A07: FF |  | 2024-04-13 15:30
ML1002-A02 | Completed | P2543-R01-Oct24..ML.GE | Issue Project Control, PMS and Planning Dossier covering Baseline Schedule, Histograms, S-Curves, etc. - Final Issue | HC-GN-0050 | HC-GN-0050: FS | HE-WS-0030, CAB-5290 | HE-WS-0030: FS, CAB-5290: FS |  | 2023-10-20 07:30
ML1003-A03 | Completed | P2543-R01-Oct24..ML.GE | Issue Construction Execution Plan/ Procedures/ Method Statements along with Procedures & Philosophies-Final Issue | HC-GN-0100 | HC-GN-0100: FF | C-56-HC01-PL-ME-2800 | C-56-HC01-PL-ME-2800: FF 21 |  | 2024-03-22 07:30
ML1004-A04 | Not Started | P2543-R01-Oct24..ML.GE | Issue cleaning & gauging, hydrotesting , Drying, Purging, Pre-commissioning and commissioning Procedure (Final Issue) | C-COM-790 | C-COM-790: FS | CAB-5290, C-52-06CR-PL-ME-7400, C-52-0506-PL-ME-7400, C-52-0405-PL-ME-7400, C-52-0304-PL-ME-7400, C-52-0203-PL-ME-7400, C-52-0102-PL-ME-7400 | CAB-5290: FS, C-52-06CR-PL-ME-7400: FS, C-52-0506-PL-ME-7400: FS, C-52-0405-PL-ME-7400: FS, C-52-0304-PL-ME-7400: FS, C-52-0203-PL-ME-7400: FS, C-52-0102-PL-ME-7400: FS |  | 2025-01-20 17:00
ML1011-A05 | Completed | P2543-R01-Oct24..ML.GE | Obtain Final Route Approval from Authorities | ML1159-A08 | ML1159-A08: FF | ML1149-A07, CAB-5290, CAB-4480 | ML1149-A07: FF, CAB-5290: FS, CAB-4480: FS |  | 2024-02-28 17:30
ML2059-B05 | Completed | P2543-R01-Oct24..ML.EN | 30% Model Review | HE-WS-0210, HE-PI-0130 | HE-WS-0210: FF, HE-PI-0130: FF | HE-PI-0150, HE-PI-1140, HE-PI-1260, HE-TL-0850 | HE-PI-0150: FS, HE-PI-1140: FS, HE-PI-1260: FS 10, HE-TL-0850: FS |  | 2023-11-28 07:30
ML2069-B09 | Completed | P2543-R01-Oct24..ML.EN | 60% Model Review | HE-PI-0150 | HE-PI-0150: FF | HE-PI-0170, HE-PI-1280, HE-TL-0870, HE-WS-0270, HE-IC-0910, HE-TL-0670 | HE-PI-0170: FS, HE-PI-1280: FS 10, HE-TL-0870: FS, HE-WS-0270: FS 30, HE-IC-0910: FS, HE-TL-0670: FS |  | 2024-03-27 08:30
ML2079-B13 | Completed | P2543-R01-Oct24..ML.EN | 90% Model Review | HE-PI-0170 | HE-PI-0170: FF | HE-PI-0180, HE-PI-1300, HE-IC-2630, HE-TL-0890 | HE-PI-0180: FF, HE-PI-1300: FS 10, HE-IC-2630: FS, HE-TL-0890: FS |  | 2024-07-26 07:30
ML1059-B28 | Not Started | P2543-R01-Oct24..ML.EN | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | HE-PL-3620, HE-PL-2730, HE-PL-2670, HE-PL-2610, ML1219-B39 | HE-PL-3620: FF, HE-PL-2730: FF, HE-PL-2670: FS, HE-PL-2610: FS, ML1219-B39: FF | CAB-4480, C-56-PL-607-CI-2600, C-56-EB2-CI-2010, C-56-G-HT-CI-2600, C-56-PR-838-CI-2600, C-56-591-01-CI-2600, C-52-598-06-CI-2600, C-52-598-05-CI-2600, C-52-598-03-CI-2600, C-52-598-02-CI-2600, C-52-598-01-CI-2600, C-52-PR-839-CI-1070, C-52-PR-839-CI-2600, | CAB-4480: FS, C-56-PL-607-CI-2600: FS, C-56-EB2-CI-2010: FS, C-56-G-HT-CI-2600: FS, C-56-PR-838-CI-2600: FS, C-56-591-01-CI-2600: FS, C-52-598-06-CI-2600: FS, C-52-598-05-CI-2600: FS, C-52-598-03-CI-2600: FS, C-52-598-02-CI-2600: FS, C-52-598-01-CI-2600: F |  | 2024-11-15 17:30
ML1179-B11 | Not Started | P2543-R01-Oct24..ML.EN | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | HE-PI-0440, HE-PI-0580, HE-EL-0530, HE-PR-1070 | HE-PI-0440: FS, HE-PI-0580: FS, HE-EL-0530: FS, HE-PR-1070: FS | CAB-4430, CAB-4450, CAB-4440, CAB-4400, CAB-4460, C-52-598-06-PI-1000, C-52-598-06-PI-1200, C-52-598-06-PI-1400, C-52-598-06-PI-1600, C-52-598-06-PI-1800, C-52-598-06-PI-2000, C-52-598-05-PI-1000, C-52-598-05-PI-1200, C-52-598-05-PI-1400, C-52-598-05-PI-16 | CAB-4430: FS, CAB-4450: FS, CAB-4440: FS, CAB-4400: FS, CAB-4460: FS, C-52-598-06-PI-1000: FS, C-52-598-06-PI-1200: FS, C-52-598-06-PI-1400: FS, C-52-598-06-PI-1600: FS, C-52-598-06-PI-1800: FS, C-52-598-06-PI-2000: FS, C-52-598-05-PI-1000: FS, C-52-598-05 |  | 2024-11-01 17:30
ML1189-B16 | Completed | P2543-R01-Oct24..ML.EN | Issue MR (Final) - Hot Bends | HE-PL-1790 | HE-PL-1790: FF | HP-ME-1190, C-COM-750, CAB-4480 | HP-ME-1190: FS, C-COM-750: FS, CAB-4480: FS |  | 2023-11-23 07:30
ML1199-B24 | Completed | P2543-R01-Oct24..ML.EN | Issue Civil / Structural Drawings for Launcher/ Receiver facilities | HE-CS-0550 | HE-CS-0550: FF | CAB-4420, C-56-EB2-CI-1000, C-56-G-HT-CI-0100, C-52-PR-839-CI-1000, C-52-EB1-CI-1000, C-52-D-HT-CI-1000, C-4N-HG-TPR-CI-0100, C-4W-TI-CI-1400, C-4W-TI-CI-1700 | CAB-4420: FS, C-56-EB2-CI-1000: FS 7, C-56-G-HT-CI-0100: FS, C-52-PR-839-CI-1000: FS, C-52-EB1-CI-1000: FS, C-52-D-HT-CI-1000: FS, C-4N-HG-TPR-CI-0100: FS, C-4W-TI-CI-1400: FS, C-4W-TI-CI-1700: FS |  | 2024-04-06 17:30
ML1209-B27 | Not Started | P2543-R01-Oct24..ML.EN | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-0170, HE-CS-1010, HE-CS-1070, HE-CS-0350, HE-CS-0110, HE-CS-0290, HE-CS-0650, HE-CS-1250, HE-CS-0230, HE-CS-1430, HE-CS-0410, HE-CS-0350, HE-CS-0770, HE-CS-0530, HE-CS-1310, HE-CS-0950, HE-CS-0830, HE-CS-0470 | HE-CS-0170: FS, HE-CS-1010: FS, HE-CS-1070: FS, HE-CS-0350: FS, HE-CS-0110: FS, HE-CS-0290: FS, HE-CS-0650: FS, HE-CS-1250: FS, HE-CS-0230: FS, HE-CS-1430: FS, HE-CS-0410: FS, HE-CS-0350: FF, HE-CS-0770: FS, HE-CS-0530: FS, HE-CS-1310: FS, HE-CS-0950: FF, | CAB-4420, C-52-PR-839-CI-1400, C-52-PR-839-CI-1410, C-52-PR-839-CI-1420, C-52-PR-839-CI-1500, C-52-PR-839-CI-1600, C-52-EB1-CI-1200, C-52-EB1-CI-1400, C-52-D-HT-CI-1000, C-52-D-HT-CI-1480, C-52-D-HT-CI-1600 | CAB-4420: FS, C-52-PR-839-CI-1400: FS, C-52-PR-839-CI-1410: FS, C-52-PR-839-CI-1420: FS, C-52-PR-839-CI-1500: FS, C-52-PR-839-CI-1600: FS, C-52-EB1-CI-1200: FS, C-52-EB1-CI-1400: FS, C-52-D-HT-CI-1000: FS, C-52-D-HT-CI-1480: FS, C-52-D-HT-CI-1600: FS |  | 2024-12-17 17:30
ML1219-B19 | Not Started | P2543-R01-Oct24..ML.EN | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-WS-0030, HE-HS-0670, HE-PR-0070, HE-PR-1200, HE-PR-0090, HE-PR-0650, HE-PR-1220, HE-PI-0760, HE-PI-0700, HE-PI-0820, HE-PI-0880, HE-PR-0160, HE-PI-0640 | HE-PR-0040: FF, HE-PR-1240: FF, HE-PR-1250: FF, HE-PR-0060: FF, HE-WS-0030: FF, HE-HS-0670: FF, HE-PR-0070: FF, HE-PR-1200: FF, HE-PR-0090: FF, HE-PR-0650: FF, HE-PR-1220: FF, HE-PI-0760: FF, HE-PI-0700: FF, HE-PI-0820: FF, HE-PI-0880: FF, HE-PR-0160: FF, | CAB-4460, CAB-4430, CAB-4450, CAB-4440, CAB-4400, C-56-PL-607-PI-1000, C-56-PL-607-PI-1200, C-56-PL-607-PI-1400, C-56-PL-607-PI-1600, C-56-PL-607-PI-1800, C-56-PL-607-PI-2000, C-56-G-HT-PI-1000, C-56-G-HT-PI-1200, C-56-G-HT-PI-1400, C-56-G-HT-PI-1600, C-56 | CAB-4460: FS, CAB-4430: FS, CAB-4450: FS, CAB-4440: FS, CAB-4400: FS, C-56-PL-607-PI-1000: FS, C-56-PL-607-PI-1200: FS, C-56-PL-607-PI-1400: FS, C-56-PL-607-PI-1600: FS, C-56-PL-607-PI-1800: FS, C-56-PL-607-PI-2000: FS, C-56-G-HT-PI-1000: FS, C-56-G-HT-PI- |  | 2024-12-31 17:30
ML1005-B01 | Completed | P2543-R01-Oct24..ML.EN | Prepare Design Basis for all Engineering Disciplines and Issue to COMPANY - Final Issue | HE-DB-0050 | HE-DB-0050: FS | HE-WS-0030, CAB-5290 | HE-WS-0030: FS, CAB-5290: FS |  | 2024-03-25 08:30
ML1007-B02 | Completed | P2543-R01-Oct24..ML.EN | Award Subcontracts for Topographical Survey/ Geotechnical Investigation Studies | HS-GN-0170 | HS-GN-0170: FS | HE-SS-0030, HE-SS-0040 | HE-SS-0030: FS, HE-SS-0040: FS |  | 2023-09-05
ML1008-B03 | Completed | P2543-R01-Oct24..ML.EN | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 56" Pipeline(IFC) | HE-PL-2420, HE-PL-0160, HE-GS-0050, HE-TS-0050, HE-TS-220, HE-GS-130 | HE-PL-2420: FF, HE-PL-0160: FF, HE-GS-0050: FS, HE-TS-0050: FS, HE-TS-220: FS, HE-GS-130: FS | CAB-4480 | CAB-4480: FS |  | 2024-02-26 17:30
ML1009-B04 | Completed | P2543-R01-Oct24..ML.EN | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 52" Pipeline(IFC) | HE-PL-2480, HE-GS-0050, HE-TS-0050, HE-PL-0230, HE-GS-80, HE-TS-270 | HE-PL-2480: FF, HE-GS-0050: FS, HE-TS-0050: FS, HE-PL-0230: FF, HE-GS-80: FS, HE-TS-270: FS | CAB-4480 | CAB-4480: FS |  | 2024-05-06
ML1010-B14 | Completed | P2543-R01-Oct24..ML.EN | Issue Tie-in Philosophy for all new facilities - IFC | HE-PR-0880 | HE-PR-0880: FF | CAB-4400, C-COM-770, HE-CO-110, HE-CO-110 | CAB-4400: FS, C-COM-770: FS, HE-CO-110: FS, HE-CO-110: FF |  | 2023-11-29 07:30
ML1012-B06 | Completed | P2543-R01-Oct24..ML.EN | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | HE-PR-0040, HE-PR-1240, HE-WS-0030, HE-PR-1250, HE-PR-0130, HE-PI-0480, HE-PI-0340, HE-PR-1050, HE-PI-0410, HE-PI-0550, HE-PR-0060 | HE-PR-0040: FS, HE-PR-1240: FS, HE-WS-0030: FS, HE-PR-1250: FS, HE-PR-0130: FS, HE-PI-0480: FS, HE-PI-0340: FS, HE-PR-1050: FS, HE-PI-0410: FS, HE-PI-0550: FS, HE-PR-0060: FS | HE-PR-1060, C-COM-750, CAB-4450, CAB-4440, CAB-4400 | HE-PR-1060: FS, C-COM-750: FF, CAB-4450: FS, CAB-4440: FS, CAB-4400: FS |  | 2023-11-22 07:30
ML1013-B07 | Completed | P2543-R01-Oct24..ML.EN | Complete HAZOP/ SIL/ LOPA Review as applicable and Submit final Report after incorporating Company comments (IFA) | HE-HS-0870, HE-HS-0810, HE-HS-0690, HE-HS-0570 | HE-HS-0870: FF, HE-HS-0810: FF, HE-HS-0690: FF, HE-HS-0570: FF | CAB-4410 | CAB-4410: FS |  | 2024-02-26 07:30
ML1014-B10 | Completed | P2543-R01-Oct24..ML.EN | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | HE-PR-0090, HE-PR-1070, HE-EL-0530, HE-PR-1220 | HE-PR-0090: FS, HE-PR-1070: FS, HE-EL-0530: FS, HE-PR-1220: FS | CAB-4460, CAB-4430, CAB-4400, CAB-4450, CAB-4440, C-56-PL-607-PI-1000, C-56-PL-607-PI-1200, C-56-PL-607-PI-1400, C-56-PL-607-PI-1600, C-56-PL-607-PI-1800, C-56-PL-607-PI-2000, C-56-G-HT-PI-1000, C-56-G-HT-PI-1200, C-56-G-HT-PI-1400, C-56-G-HT-PI-1600, C-56 | CAB-4460: FS, CAB-4430: FS, CAB-4400: FS, CAB-4450: FS, CAB-4440: FS, C-56-PL-607-PI-1000: FS, C-56-PL-607-PI-1200: FS, C-56-PL-607-PI-1400: FS, C-56-PL-607-PI-1600: FS, C-56-PL-607-PI-1800: FS, C-56-PL-607-PI-2000: FS, C-56-G-HT-PI-1000: FS, C-56-G-HT-PI- |  | 2024-10-18 17:30
ML1015-B08 | Completed | P2543-R01-Oct24..ML.EN | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | HE-CS-0530, HE-ME-0110, HE-PR-0530, HE-PL-0110, HE-PR-0490 | HE-CS-0530: FS, HE-ME-0110: FF, HE-PR-0530: FF, HE-PL-0110: FF, HE-PR-0490: FF | CAB-4440, CAB-4470, CAB-4450, CAB-4420, CAB-4460, C-56-PL-607-ME-1000, C-56-PL-607-ME-1200, C-56-PL-607-ME-1400, C-56-PL-607-ME-1600, C-56-EB2-ME-1000, C-56-EB2-ME-1010, C-56-EB2-ME-1200, C-56-PR-838-ME-1100, C-56-PR-838-ME-1200, C-56-PR-838-ME-1400, C-56- | CAB-4440: FS, CAB-4470: FS, CAB-4450: FS, CAB-4420: FS, CAB-4460: FS, C-56-PL-607-ME-1000: FS, C-56-PL-607-ME-1200: FS, C-56-PL-607-ME-1400: FS, C-56-PL-607-ME-1600: FS, C-56-EB2-ME-1000: FS, C-56-EB2-ME-1010: FS, C-56-EB2-ME-1200: FS, C-56-PR-838-ME-1100: |  | 2024-10-18
ML1016-B12 | Completed | P2543-R01-Oct24..ML.EN | Complete HSEIA, QRA, and Gas Dispersion Studies after review / approval by Company and Submit Final Reports | HE-HS-0520, HE-HS-0830 | HE-HS-0520: FF, HE-HS-0830: FS | C-COM-800, CAB-4410, C-COM-790, C-COM-800 | C-COM-800: FS, CAB-4410: FS, C-COM-790: FS, C-COM-800: FF |  | 2024-05-07 17:30
ML1017-B18 | Completed | P2543-R01-Oct24..ML.EN | Issue MRs for All Mechanical Equipment & Packages (Final Issue) | HE-ME-0170, HE-ME-520, HE-PL-0110, HE-PR-0530, HE-PR-0490 | HE-ME-0170: FS, HE-ME-520: FS, HE-PL-0110: FS, HE-PR-0530: FS, HE-PR-0490: FS | C-COM-790, HM-ME-0120, CAB-4440, CAB-4430 | C-COM-790: FS, HM-ME-0120: FS, CAB-4440: FS, CAB-4430: FS |  | 2024-04-16 17:30
ML1021-B15 | Completed | P2543-R01-Oct24..ML.EN | Issue MR (Final) - Line pipes | HE-PL-1670 | HE-PL-1670: FS | C-COM-750, HM-PL-0010 | C-COM-750: FS, HM-PL-0010: FS |  | 2023-09-21
ML1027-B17 | Completed | P2543-R01-Oct24..ML.EN | Issue MRs for All E&I Equipment & Packages (Final Issue) | HE-IC-1670, HE-EL-1070, HE-IC-1970, HE-EL-1010, HE-IC-1610 | HE-IC-1670: FS, HE-EL-1070: FS, HE-IC-1970: FS, HE-EL-1010: FS, HE-IC-1610: FS | HE-PI-0170, C-COM-800, CAB-4450, CAB-4460 | HE-PI-0170: FF, C-COM-800: FS, CAB-4450: FS, CAB-4460: FS |  | 2024-04-16 17:30
ML1031-B20 | Not Started | P2543-R01-Oct24..ML.EN | Issue SLD, Hazardous Area Classification Details for All Areas - IFC | HE-EL-0350, HE-EL-0230, HE-EL-0290 | HE-EL-0350: FS, HE-EL-0230: FS, HE-EL-0290: FS | ML1219-B29, CAB-4410, CAB-4450 | ML1219-B29: FF, CAB-4410: FS, CAB-4450: FS |  | 2024-11-01 17:30
ML1032-B21 | Not Started | P2543-R01-Oct24..ML.EN | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | HE-TL-0710, HE-EL-0590, HE-IC-2570, HE-CS-0170, HE-TL-0830, HE-IC-1010, HE-EL-1670, HE-IC-0950, HE-TL-0770, HE-EL-1670 | HE-TL-0710: FS, HE-EL-0590: FS, HE-IC-2570: FS, HE-CS-0170: FS, HE-TL-0830: FS, HE-IC-1010: FS, HE-EL-1670: FS, HE-IC-0950: FS, HE-TL-0770: FS, HE-EL-1670: FF | ML1030, ML1859-E31, ML1749-E20, ML1219-B29, CAB-4460, CAB-4420, CAB-4450, CAB-4470, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C-56-PR-838-EI-2030, C-56 | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1219-B29: FF, CAB-4460: FS, CAB-4420: FS, CAB-4450: FS, CAB-4470: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-EI-1400: FS, C-56-PR-838-EI- |  | 2024-11-08 17:30
ML1033-B22 | Not Started | P2543-R01-Oct24..ML.EN | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | HE-TL-0110, HE-TL-0230, HE-TL-0290, HE-TL-0350, HE-TL-0410, HE-TL-0470, HE-IC-0290, HE-IC-0230, HE-TL-2470, HE-IC-0190, HE-IC-0250, HE-IC-620 | HE-TL-0110: FS, HE-TL-0230: FS, HE-TL-0290: FS, HE-TL-0350: FS, HE-TL-0410: FS, HE-TL-0470: FS, HE-IC-0290: FS, HE-IC-0230: FS, HE-TL-2470: FS, HE-IC-0190: SS, HE-IC-0250: SS, HE-IC-620: SS | ML1030, CAB-4470, C-COM-790, C-56-PL-607-TE-1200, C-56-PL-607-TE-1400, C-56-PL-607-TE-1600, C-56-EB2-TE-1000, C-56-HC01-PL-TE-8200, C-56-HC01-PL-TE-8400, C-56-PR-838-TE-1000, C-56-591-01-TE-1000, C-52-598-06-TE-1000, C-52-598-05-TE-1000, C-52-598-04-TE-100 | ML1030: FS, CAB-4470: FS, C-COM-790: FS, C-56-PL-607-TE-1200: FS, C-56-PL-607-TE-1400: FS, C-56-PL-607-TE-1600: FS, C-56-EB2-TE-1000: FS, C-56-HC01-PL-TE-8200: FS, C-56-HC01-PL-TE-8400: FS, C-56-PR-838-TE-1000: FS, C-56-591-01-TE-1000: FS, C-52-598-06-TE-1 |  | 2024-10-28 07:30
ML1034-B25 | Not Started | P2543-R01-Oct24..ML.EN | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-0170, HE-CS-0110, HE-CS-0470, HE-CS-0350, HE-CS-0650, HE-CS-0290, HE-CS-0230, HE-CS-1310, HE-CS-0350, HE-CS-1070, HE-CS-1430, HE-CS-1010, HE-CS-0830, HE-CS-0410, HE-CS-1190, HE-CS-1250, HE-CS-0530 | HE-CS-0170: FS, HE-CS-0110: FS, HE-CS-0470: FS, HE-CS-0350: FS, HE-CS-0650: FS, HE-CS-0290: FS, HE-CS-0230: FS, HE-CS-1310: FS, HE-CS-0350: FF, HE-CS-1070: FS, HE-CS-1430: FS, HE-CS-1010: FF, HE-CS-0830: FS, HE-CS-0410: FS, HE-CS-1190: FS, HE-CS-1250: FS, | CAB-4420, C-52-598-06-CI-1400, C-52-598-06-CI-1410, C-52-598-06-CI-1420, C-52-598-06-CI-1430, C-52-598-05-CI-1400, C-52-598-05-CI-1410, C-52-598-05-CI-1420, C-52-598-05-CI-1430, C-52-598-04-CI-1400, C-52-598-04-CI-1410, C-52-598-04-CI-1420, C-52-598-04-CI- | CAB-4420: FS, C-52-598-06-CI-1400: FS, C-52-598-06-CI-1410: FS, C-52-598-06-CI-1420: FS, C-52-598-06-CI-1430: FS, C-52-598-05-CI-1400: FS, C-52-598-05-CI-1410: FS, C-52-598-05-CI-1420: FS, C-52-598-05-CI-1430: FS, C-52-598-04-CI-1400: FS, C-52-598-04-CI-14 |  | 2024-12-17 17:30
ML1035-B26 | Not Started | P2543-R01-Oct24..ML.EN | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-0350, HE-CS-1250, HE-CS-0290, HE-CS-0410, HE-CS-0110, HE-CS-0230, HE-CS-1310, HE-CS-0530, HE-CS-1010, HE-CS-0830, HE-CS-0950, HE-CS-0650, HE-CS-0170, HE-CS-0770, HE-CS-1070, HE-CS-0350, HE-CS-0470 | HE-CS-0350: FF, HE-CS-1250: FS, HE-CS-0290: FS, HE-CS-0410: FS, HE-CS-0110: FS, HE-CS-0230: FS, HE-CS-1310: FS, HE-CS-0530: FS, HE-CS-1010: FS, HE-CS-0830: FS, HE-CS-0950: FS, HE-CS-0650: FS, HE-CS-0170: FS, HE-CS-0770: FS, HE-CS-1070: FS, HE-CS-0350: FS, | CAB-4420, C-56-591-01-CI-1000, C-56-591-01-CI-1400, C-56-591-01-CI-1410 | CAB-4420: FS, C-56-591-01-CI-1000: FF 32, C-56-591-01-CI-1400: FS, C-56-591-01-CI-1410: FS |  | 2024-12-10 17:30
ML1036-B23 | Not Started | P2543-R01-Oct24..ML.EN | Issue Civil / Structural Drawings for Gas Filters, Pressure Reducing Skids and Metering Skids facilities - IFC. | HE-CS-0830 | HE-CS-0830: FF | CAB-4420, C-52-PR-839-ME-1800, C-52-PR-839-ME-2000, C-52-PR-839-ME-2010 | CAB-4420: FS, C-52-PR-839-ME-1800: FS, C-52-PR-839-ME-2000: FS, C-52-PR-839-ME-2010: FS |  | 2024-11-22 17:30
ML1041-C03 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - Isolation Joints | HP-ME-1240 | HP-ME-1240: FS | HM-PL-0350, HM-PL-0460 | HM-PL-0350: FS, HM-PL-0460: FS |  | 2023-11-23 07:30
ML1043-C14 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - Manual Ball Valves | HP-ME-1090 | HP-ME-1090: FF | HM-PL-0150 | HM-PL-0150: FS |  | 2024-04-04 08:30
ML1229-C02 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - Hot Bends | HP-ME-1190 | HP-ME-1190: FS | HM-PL-0150 | HM-PL-0150: FS |  | 2023-10-02 07:30
ML1239-C04 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - Barred Tee | HP-ME-1290 | HP-ME-1290: FF | HM-PL-0150 | HM-PL-0150: FS |  | 2024-04-25 07:30
ML1249-C06 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - Anchor Flanges | HP-ME-1240 | HP-ME-1240: FF | HM-PL-0150 | HM-PL-0150: FS |  | 2024-07-01 07:30
ML1259-C09 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - Sales Gas Metering Skids | HP-ME-0030 | HP-ME-0030: FS | HM-ME-0010 | HM-ME-0010: FS |  | 2024-02-16 08:30
ML1269-C12 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - F & G System | HP-ME-0780, HP-ME-0730 | HP-ME-0780: FF, HP-ME-0730: FF | HM-ME-1520, HM-ME-1420 | HM-ME-1520: FS, HM-ME-1420: FS |  | 2024-06-24 07:30
ML1279-C05 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - Pig Launcher & Receiver | HP-ME-0230 | HP-ME-0230: FF | HM-ME-0410 | HM-ME-0410: FF |  | 2023-12-21 07:30
ML1289-C11 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - Leak Detection System | HP-ME-0130 | HP-ME-0130: FF | HM-ME-0210 | HM-ME-0210: FF |  | 2024-03-28 08:30
ML1309-C15 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - Passive Cooling Shelters | HP-ME-0580 | HP-ME-0580: FF | HM-ME-1120 | HM-ME-1120: FS |  | 2024-06-14 17:30
ML1319-C16 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - AC UPS System | HP-ME-0380 | HP-ME-0380: FF | HM-ME-0720 | HM-ME-0720: FS |  | 2024-03-26 08:30
ML1329-C17 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - Fiber Optic Cable | HP-BK-0080 | HP-BK-0080: FF | HM-ME-1320 | HM-ME-1320: FS |  | 2024-04-26 08:30
ML1339-C18 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - IDS & PIDS System | HP-ME-0630 | HP-ME-0630: FF | HM-ME-1320 | HM-ME-1320: FS |  | 2024-06-07 07:30
ML1349-C19 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - RTUs | HP-ME-0330, HP-ME-0280 | HP-ME-0330: FS, HP-ME-0280: FS | HM-ME-0510 | HM-ME-0510: FF |  | 2024-06-10 17:30
ML1369-C21 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - Valves – Globe/Check/Plug | HP-ME-1090 | HP-ME-1090: FF | HM-PL-0150 | HM-PL-0150: FS |  | 2024-03-29 08:30
ML1026-C13 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - Solar Power System | HP-ME-0530 | HP-ME-0530: FF | HM-ME-1020 | HM-ME-1020: FS |  | 2024-06-14 17:30
ML1022-C07 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - MOV/ROV/GOV Valves | HP-ME-0280, HP-ME-0330 | HP-ME-0280: FS, HP-ME-0330: FS | HM-ME-0610, HM-ME-0510 | HM-ME-0610: FF, HM-ME-0510: FF |  | 2024-03-27 08:30
ML1028-C20 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - CCTV Systems | HP-ME-0630 | HP-ME-0630: FS | HM-ME-1420, HM-ME-1520 | HM-ME-1420: FS, HM-ME-1520: FS |  | 2024-06-07 07:30
ML1038-C10 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - CP System | HS-GN-0530 | HS-GN-0530: FF | HM-PL-0360 | HM-PL-0360: FF |  | 2024-05-20 07:30
ML1039-C08 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - Pressure Reduction Skids | HP-ME-0080 | HP-ME-0080: FS | HM-ME-0110 | HM-ME-0110: FS |  | 2024-02-23 08:30
ML1040-C01 | Completed | P2543-R01-Oct24..ML.PR | Issue Purchase Order (Final) - Line pipes | HP-ME-1040 | HP-ME-1040: FS | HM-PL-0150, HM-PL-0010 | HM-PL-0150: FS, HM-PL-0010: FS |  | 2023-08-25
ML1057-D19 | Completed | P2543-R01-Oct24..ML.2 | Receive at Site - Fiber Optic Cable | HM-EL-0180, HM-EL-610 | HM-EL-0180: FF, HM-EL-610: FF | C-52-06CR-PL-TE-8200 | C-52-06CR-PL-TE-8200: FS |  | 2024-10-25 08:00
ML1024-D06 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - MOV/ROV/GOV Valves | HM-ME-0580, HM-ME-0680, HM-ME-2210, HM-ME-2240 | HM-ME-0580: FS, HM-ME-0680: FS, HM-ME-2210: FS, HM-ME-2240: FS | ML1060 | ML1060: FS |  | 2025-07-23 17:00
ML1051-D07 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - Pressure Reduction Skids | HM-ME-0180 | HM-ME-0180: FS | ML1060, C-56-PR-838-TE-1000 | ML1060: FS, C-56-PR-838-TE-1000: FS |  | 2025-05-28 17:00
ML1053-D23 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - Leak Detection System | HM-ME-0280 | HM-ME-0280: FF | ML1499-D18, ML1060, C-56-PR-838-TE-1000 | ML1499-D18: FF, ML1060: FS, C-56-PR-838-TE-1000: FS |  | 2025-03-27 13:00
ML1519-D04 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - Pig Launcher & Receiver | HM-ME-0480, HM-ME-2390 | HM-ME-0480: FF, HM-ME-2390: FF | ML1060, C-56-PL-607-ME-1000, C-56-PL-607-PL-1000, C-56-PR-838-ME-1100, C-52-PR-839-ME-1100, C-52-PL-838-ME-1000 | ML1060: FS, C-56-PL-607-ME-1000: FS, C-56-PL-607-PL-1000: FS, C-56-PR-838-ME-1100: FS, C-52-PR-839-ME-1100: FS, C-52-PL-838-ME-1000: FS |  | 2025-03-12 18:00
ML1529-D20 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - Valves – Globe/Check/Plug | HM-PL-0220, HM-PL-1570 | HM-PL-0220: FF, HM-PL-1570: FF | ML1060, C-52-598-01-PI-1800, C-52-598-01-PI-2000 | ML1060: FS, C-52-598-01-PI-1800: FS, C-52-598-01-PI-2000: FS |  | 2025-03-13 13:00
ML1549-D22 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - Cathodic Protection (CP) System | HM-PL-0430 | HM-PL-0430: FF | ML1060, C-56-HC01-PL-CA-5220, C-56-HC01-PL-CA-5200, C-56-HC01-PL-CA-5400, C-56-HC01-PL-CA-5430 | ML1060: FS, C-56-HC01-PL-CA-5220: FS, C-56-HC01-PL-CA-5200: FS, C-56-HC01-PL-CA-5400: FS, C-56-HC01-PL-CA-5430: FS |  | 2025-04-03 17:00
ML1409-D24 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - Isolation Joints, Barred Tee, and Anchor Flanges | HM-PL-0530, HM-PL-0430, HM-PL-0840, HM-PL-0740, HM-PL-0320, HM-PL-1490, HM-PL-1510, HM-PL-1530 | HM-PL-0530: FS, HM-PL-0430: FS, HM-PL-0840: FS, HM-PL-0740: FS, HM-PL-0320: FS, HM-PL-1490: FS, HM-PL-1510: FS, HM-PL-1530: FS | ML1060, C-56-PR-838-ME-1400 | ML1060: FS, C-56-PR-838-ME-1400: FS |  | 2025-05-09 15:00
ML1419-D08 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - Sales Gas Metering Skids | ML1499-D18, HM-ME-0080 | ML1499-D18: FF, HM-ME-0080: FS | ML1060, C-52-PR-839-ME-2000, C-52-PR-839-ME-2010 | ML1060: FS, C-52-PR-839-ME-2000: FS, C-52-PR-839-ME-2010: FS |  | 2025-05-11 15:00
ML1429-D17 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - Solar Power System | HM-ME-1090 | HM-ME-1090: FS | ML1060, C-52-598-01-EI-1210 | ML1060: FS, C-52-598-01-EI-1210: FS |  | 2025-04-25 17:00
ML1439-D10 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - Hot Bends for 56" Pipeline | HM-PL-0630 | HM-PL-0630: FF 9 | C-56-HC01-PL-ME-2800 | C-56-HC01-PL-ME-2800: FF |  | 2024-12-22 17:00
ML1449-D11 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - Hot Bends for 52" Pipeline (50% to total Qty) | HM-PL-0630 | HM-PL-0630: FF | C-52-0405-PL-ME-4810, C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-52-0405-PL-CI-6800, PRECOM-52-0405-1000, ML1679-E13 | C-52-0405-PL-ME-4810: FF, C-52-0405-PL-CA-5220: FF, C-52-0405-PL-TE-8200: FF, C-52-0405-PL-ME-7400: FS, C-52-0405-PL-CI-6800: FF, PRECOM-52-0405-1000: FS, ML1679-E13: FS |  | 2024-12-11 17:00
ML1459-D12 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - Hot Bends for 52" Pipeline (100% to total Qty) | ML1219-B29, HM-PL-0640 | ML1219-B29: FF, HM-PL-0640: FF | ML1060, C-52-0304-PL-ME-4810, C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, PRECOM-52-0304-1000, C-52-0304-PL-CI-6000, ML1679-E13 | ML1060: FS, C-52-0304-PL-ME-4810: FF, C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF, PRECOM-52-0304-1000: FS, C-52-0304-PL-CI-6000: FF, ML1679-E13: FS |  | 2025-01-26 08:00
ML1469-D13 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - E&I Equipment's (RTUs) | HM-ME-0680, HM-ME-0580, HM-ME-2210, HM-ME-2240 | HM-ME-0680: FS, HM-ME-0580: FS, HM-ME-2210: FS, HM-ME-2240: FS | ML1060 | ML1060: FS |  | 2025-07-23 17:00
ML1479-D15 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - E&I Equipment's (IDS & PIDS System) | HM-ME-1390, HM-ME-1290, HM-ME-2270, HM-ME-2290 | HM-ME-1390: FS, HM-ME-1290: FF, HM-ME-2270: FF, HM-ME-2290: FS | ML1060, C-52-598-01-TE-1000 | ML1060: FS, C-52-598-01-TE-1000: FS |  | 2025-05-27 17:00
ML1499-D18 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - UPS System | ML1053-D23, HM-ME-0790 | ML1053-D23: FF, HM-ME-0790: FF | ML1419-D08, ML1060, C-541CR-EI-1020 | ML1419-D08: FF, ML1060: FS, C-541CR-EI-1020: FS |  | 2025-03-27 13:00
ML1539-D21 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - Manual Valves | HM-PL-0220, HM-PL-1570 | HM-PL-0220: FF, HM-PL-1570: FF | ML1060, C-52-598-01-PI-1200, C-52-598-01-PI-1800, C-52-598-01-PI-2000 | ML1060: FS, C-52-598-01-PI-1200: FS, C-52-598-01-PI-1800: FS, C-52-598-01-PI-2000: FS |  | 2025-03-13 13:00
ML2089-D16 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - F & G System | HM-ME-1490, HM-ME-1590, HM-ME-2310, HM-ME-2330 | HM-ME-1490: FF, HM-ME-1590: FF, HM-ME-2310: FF, HM-ME-2330: FF | C-52-598-01-EI-1210, C-52-598-01-EI-1400 | C-52-598-01-EI-1210: FS, C-52-598-01-EI-1400: FS |  | 2025-04-03 15:00
ML1054-D09 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - Passive Cooling Shelter | HM-ME-1190 | HM-ME-1190: FS | ML1060, C-56-591-01-EI-1000, C-52-598-06-EI-1000, C-52-598-05-EI-1000, C-52-598-04-EI-1000, C-52-598-03-EI-1000, C-52-598-02-EI-1000, C-52-598-01-EI-1000, C-52-598-01-EI-1000 | ML1060: FS, C-56-591-01-EI-1000: FS, C-52-598-06-EI-1000: FS, C-52-598-05-EI-1000: FS 45, C-52-598-04-EI-1000: FS, C-52-598-03-EI-1000: FS, C-52-598-02-EI-1000: FS, C-52-598-01-EI-1000: FS, C-52-598-01-EI-1000: FF |  | 2025-04-25 15:00
ML1056-D14 | Not Started | P2543-R01-Oct24..ML.2 | Receive at Site - E&I Equipment's (CCTV System) | HM-ME-1290, HM-ME-2270 | HM-ME-1290: FS, HM-ME-2270: FS | ML1060, C-52-598-01-TE-1000 | ML1060: FS, C-52-598-01-TE-1000: FS |  | 2025-05-27 17:00
ML1629-E08 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-591-01-EI-1000, C-56-591-01-EI-2050, C-56-591-01-EI-1800, C-56-591-01-EI-1810, C-56-591-01-EI-2410, C-56-591-01-EI-2400, C-56-PR-838-EI-2050, C-56-PR-838-EI-2200, C-56-PL-607-EI-1400, C-56-PL-607-EI-2050, C-56-PL-607-CA-1030, C-56-PL-607-EI-1800, C-56 | C-56-591-01-EI-1000: FS, C-56-591-01-EI-2050: FS, C-56-591-01-EI-1800: FS, C-56-591-01-EI-1810: FS, C-56-591-01-EI-2410: FS, C-56-591-01-EI-2400: FS, C-56-PR-838-EI-2050: FS, C-56-PR-838-EI-2200: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2050: FS, C-56-P | ML1060 | ML1060: FS |  | 2025-10-09 11:00
ML1639-E09 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Hydrotesting - 56" Sales Gas Pipeline | C-56-HC01-PL-ME-7620, C-56-01HG-PL-ME-7620, ML1589-E04, ML1599-E05 | C-56-HC01-PL-ME-7620: FS, C-56-01HG-PL-ME-7620: FS, ML1589-E04: FS, ML1599-E05: FS | ML1060, PRECOM-56-HGHC-1000 | ML1060: FS, PRECOM-56-HGHC-1000: FF |  | 2025-09-17 15:00
ML1649-E10 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Drying & Purging of all facilities including Pipeline & Block Valve Stations- 56" Sales Gas Pipeline | PRECOM-56-HGHC-1000, PRECOM-56-59101-1000 | PRECOM-56-HGHC-1000: FS, PRECOM-56-59101-1000: FS | ML1060 | ML1060: FS |  | 2025-10-09 15:00
ML1669-E12 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -BVS-3 to Sweihan CRS | C-52-06CR-PL-CI-2230, C-52-06CR-PL-CI-1400, C-52-0304-PL-CI-2230, C-52-0304-PL-CI-1400, C-52-0405-PL-CI-2230, C-52-0506-PL-CI-1400, C-52-0506-PL-CI-1600, C-52-0405-PL-CI-1400 | C-52-06CR-PL-CI-2230: FS, C-52-06CR-PL-CI-1400: FS, C-52-0304-PL-CI-2230: FS, C-52-0304-PL-CI-1400: FS, C-52-0405-PL-CI-2230: FS, C-52-0506-PL-CI-1400: FS, C-52-0506-PL-CI-1600: FS, C-52-0405-PL-CI-1400: FS | C-52-06CR-PL-ME-2800 | C-52-06CR-PL-ME-2800: FF |  | 2025-04-10 17:00
ML1679-E13 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | HS-CN-0090, HE-PL-3030, ML1149-A07, HE-PL-3090, C-52-06CR-CNM31-1800, C-52-06CR-CNH30-1800, C-52-0506-CNH27-1800, C-52-0405-CNM17-1800, C-52-0405-CNM18-1800, C-52-0405-CNM23-1800, C-52-0405-CNH19-1800, C-52-0405-CNH20-1800, C-52-0405-CNH24-1800, C-52-0102- | HS-CN-0090: FS, HE-PL-3030: FS, ML1149-A07: FS, HE-PL-3090: FS, C-52-06CR-CNM31-1800: FS, C-52-06CR-CNH30-1800: FS, C-52-0506-CNH27-1800: FS, C-52-0405-CNM17-1800: FS, C-52-0405-CNM18-1800: FS, C-52-0405-CNM23-1800: FS, C-52-0405-CNH19-1800: FS, C-52-0405- | ML1060, PRECOM-52-06CR-1000 | ML1060: FS, PRECOM-52-06CR-1000: FF |  | 2025-08-24 07:00
ML1689-E14 | Completed | P2543-R01-Oct24..ML.CO1 | Complete Pipeline welding - 52" Sales Gas Pipeline - 25% Welding | C-52-HG01-PL-ME-3600 | C-52-HG01-PL-ME-3600: FS | ML1060, ML1699-E15 | ML1060: FS, ML1699-E15: FS |  | 2024-10-18 10:00
ML1699-E15 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Pipeline welding - 52" Sales Gas Pipeline - 50% Welding | C-52-0203-PL-ME-3600, C-52-0102-PL-ME-3600, C-52-HG01-PL-ME-3600, ML1689-E14, C-52-0304-PL-ME-3600 | C-52-0203-PL-ME-3600: FS, C-52-0102-PL-ME-3600: FS, C-52-HG01-PL-ME-3600: FS, ML1689-E14: FS, C-52-0304-PL-ME-3600: FF | ML1060, ML1709-E16 | ML1060: FS, ML1709-E16: FS 49 |  | 2025-01-09 17:00
ML1809-E26 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 05 to BVS-06 | C-52-0506-PL-ME-7430, C-52-0506-PL-ME-7620 | C-52-0506-PL-ME-7430: FS, C-52-0506-PL-ME-7620: FS 3 | ML1060, PRECOM-52-0506-1000 | ML1060: FS, PRECOM-52-0506-1000: FF |  | 2025-10-05 07:00
ML1819-E27 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 06 to Sweihan Receiver | C-52-06CR-PL-ME-7430, C-52-06CR-PL-ME-7620 | C-52-06CR-PL-ME-7430: FS, C-52-06CR-PL-ME-7620: FS | ML1060, PRECOM-52-06CR-1000 | ML1060: FS, PRECOM-52-06CR-1000: FF |  | 2025-10-31 11:30
ML1829-E28 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Drying & Purging of all facilities including Pipeline & Block Valve Stations - 52" Sales Gas Pipeline | ML1719-E17, PRECOM-52-HG01-1000 | ML1719-E17: FS, PRECOM-52-HG01-1000: FS 3 | ML1060, CCM-PM4580 | ML1060: FS, CCM-PM4580: FS |  | 2025-07-21 15:00
ML1839-E29 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Civil works for CRS Building & equipment's foundations at Sweihan CRS | C-52-PR-839-CI-1600, C-52-EB1-CI-1020, C-52-EB1-CI-1200, C-52-EB1-CI-1400 | C-52-PR-839-CI-1600: FS, C-52-EB1-CI-1020: FS, C-52-EB1-CI-1200: FS, C-52-EB1-CI-1400: FS | ML1060, PRECOM-52-EB1-1000, PRECOM-52-PR-1000 | ML1060: FS, PRECOM-52-EB1-1000: FS, PRECOM-52-PR-1000: FS |  | 2025-04-22 13:00
ML1849-E30 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Piping works at Sweihan CRS | C-52-PR-839-PI-1410, C-52-D-HT-PI-2000 | C-52-PR-839-PI-1410: FS, C-52-D-HT-PI-2000: FS | ML1060, PRECOM-52-EB1-1000, PRECOM-52-PR-1000 | ML1060: FS, PRECOM-52-EB1-1000: FS, PRECOM-52-PR-1000: FS |  | 2025-08-13 09:00
ML1859-E31 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete E&I Installation Works - Sweihan CRS | HE-EL-0530, HM-ME-0790, HE-IC-0770, HM-IC-0040, HE-EL-0710, HE-EL-0290, HE-IC-1550, HE-EL-0650, HM-EL-0520, HM-ME-1590, HE-EL-0640, HE-IC-0530, HE-EL-1670, HM-EL-0380, HM-ME-0690, HM-EL-0080, HE-IC-1430, HM-ME-1690, HE-IC-0590, HE-IC-0010, HE-EL-1790, HE-E | HE-EL-0530: FS, HM-ME-0790: FS, HE-IC-0770: FS, HM-IC-0040: FS, HE-EL-0710: FS, HE-EL-0290: FS, HE-IC-1550: FS, HE-EL-0650: FS, HM-EL-0520: FS, HM-ME-1590: FS, HE-EL-0640: FS, HE-IC-0530: FS, HE-EL-1670: FS, HM-EL-0380: FS, HM-ME-0690: FS, HM-EL-0080: FS, | ML1060 | ML1060: FS |  | 2025-11-03 11:00
ML1869-E32 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Site Grading & ROW along the Pipeline - 4" Water line | C-4W-SVHG-PIPEL-2230 | C-4W-SVHG-PIPEL-2230: FS | ML1060, C-4N-HG-TPR-PI-1200, C-4N-HG-TPR-PI-1800, C-4N-HG-TPR-PI-2000, C-4W-081-03-PI-1000, C-4W-081-03-PI-3000, C-4W-TI-3000 | ML1060: FS, C-4N-HG-TPR-PI-1200: FS, C-4N-HG-TPR-PI-1800: FS, C-4N-HG-TPR-PI-2000: FS, C-4W-081-03-PI-1000: FS, C-4W-081-03-PI-3000: FS, C-4W-TI-3000: FS |  | 2025-01-30 17:00
ML1879-E33 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Pipeline Jointing - 4" Waterline | C-4W-SVHG-PIPEL-4810, CPL-4-CRMN-3350, CPL-4-CRMN-3430, CPL-4-CRMN-3490, CPL-4-CRMN-3550, CPL-4-CRMN-3610 | C-4W-SVHG-PIPEL-4810: FS, CPL-4-CRMN-3350: FS, CPL-4-CRMN-3430: FS, CPL-4-CRMN-3490: FS, CPL-4-CRMN-3550: FS, CPL-4-CRMN-3610: FS | ML1060, C-4W-081-03-PI-1000, C-4W-TI-PI-1800, C-4W-TI-PI-2000 | ML1060: FS, C-4W-081-03-PI-1000: FS, C-4W-TI-PI-1800: FS, C-4W-TI-PI-2000: FS |  | 2025-03-11 09:00
ML1889-E34 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Hydrotesting - 4" Water line | C-4W-SVHG-PIPEL-7610 | C-4W-SVHG-PIPEL-7610: FS | ML1060, C-4W-081-03-PI-1000, C-4W-TI-PI-1800, C-4W-TI-PI-2000 | ML1060: FS, C-4W-081-03-PI-1000: FS, C-4W-TI-PI-1800: FS, C-4W-TI-PI-2000: FS |  | 2025-04-17 13:00
ML1899-E35 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Pipeline Welding - 36"Jump-over line | C-36-KM-HT04-ME-1040, C-36-KM-HT03-ME-1040, C-36-KM-HT-PI-2000 | C-36-KM-HT04-ME-1040: FS, C-36-KM-HT03-ME-1040: FS, C-36-KM-HT-PI-2000: FS | ML1060, PRECOM-36-KM-1000 | ML1060: FS, PRECOM-36-KM-1000: FS |  | 2025-08-17 07:00
ML1909-E36 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-PIPEL-3800, C-4N-H5HG-PIPEL-4810, C-4N-H5HG-PIPEL-5010, C-4N-H5HG-CMA01-1030, C-4N-H5HG-CMA02-1030, C-4N-H5HG-CMA03-1030, C-4N-H5HG-CMA04-1030, C-4N-H5HG-CMA05-1030, C-4N-H5HG-CMA06-1030, C-4N-H5HG-CMA07-1030, C-4N-H5HG-CMA08-1030, C-4N-H5HG-CMA0 | C-4N-H5HG-PIPEL-3800: FS, C-4N-H5HG-PIPEL-4810: FS, C-4N-H5HG-PIPEL-5010: FS, C-4N-H5HG-CMA01-1030: FS, C-4N-H5HG-CMA02-1030: FS, C-4N-H5HG-CMA03-1030: FS, C-4N-H5HG-CMA04-1030: FS, C-4N-H5HG-CMA05-1030: FS, C-4N-H5HG-CMA06-1030: FS, C-4N-H5HG-CMA07-1030: | ML1060, PRECOM-4N-H5HG-1000 | ML1060: FS, PRECOM-4N-H5HG-1000: FS |  | 2025-06-12 12:30
ML1919-E37 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Hydrotesting - 4" Nitrogen Pipeline | C-4N-H5HG-PIPEL-7430, C-4N-H5HG-PIPEL-7620 | C-4N-H5HG-PIPEL-7430: FS, C-4N-H5HG-PIPEL-7620: FS | ML1060, PRECOM-4N-H5HG-1000 | ML1060: FS, PRECOM-4N-H5HG-1000: FF |  | 2025-09-14 07:00
ML1929-E38 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Drying & Purging of all facilities including Pipeline - 4" Nitrogen Pipeline | C-4N-HG-TPR-PL-1030, C-4N-H5-TPL-PL-1030, PRECOM-4N-H5HG-1000 | C-4N-HG-TPR-PL-1030: FS, C-4N-H5-TPL-PL-1030: FS, PRECOM-4N-H5HG-1000: FS | ML1060 | ML1060: FS |  | 2025-09-25 12:30
ML1939-E39 | Not Started | P2543-R01-Oct24..ML.CO1 | Achieve Mechanical Completion of PL & facilities- ( 4" Water line) | C-4W-SVHG-PIPEL-6810, C-4W-SVHG-PIPEL-7610 | C-4W-SVHG-PIPEL-6810: FS, C-4W-SVHG-PIPEL-7610: FS | ML1060, C-4W-TI-PI-2000 | ML1060: FS, C-4W-TI-PI-2000: FS |  | 2025-04-17 13:00
ML1949-E40 | Not Started | P2543-R01-Oct24..ML.CO1 | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | C-4N-HG-TPR-PL-1030, C-4N-HG-TPR-TE-1420, C-4N-HG-TPR-PI-2000, C-4N-HG-TPR-ME-1100, C-4N-H5-TPL-PL-1030, C-4N-H5-TPL-TE-1420, C-4N-H5-TPL-EL-1000, C-4N-H5-TPL-PL-1000, C-4N-H5-TPL-CA-1030, C-4N-H5-TPL-EI-2050, C-4N-H5-TPL-PI-2000, C-4N-H5-TPL-ME-1000, C-4N | C-4N-HG-TPR-PL-1030: FS, C-4N-HG-TPR-TE-1420: FS, C-4N-HG-TPR-PI-2000: FS, C-4N-HG-TPR-ME-1100: FS, C-4N-H5-TPL-PL-1030: FS, C-4N-H5-TPL-TE-1420: FS, C-4N-H5-TPL-EL-1000: FS, C-4N-H5-TPL-PL-1000: FS, C-4N-H5-TPL-CA-1030: FS, C-4N-H5-TPL-EI-2050: FS, C-4N-H | ML1060 | ML1060: FS |  | 2025-09-07 07:00
ML1959-E41 | Not Started | P2543-R01-Oct24..ML.CO1 | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | C-56-01HG-PL-CI-7800, C-56-01HG-PL-CI-7810, C-56-HC01-PL-ME-7620, C-56-HC01-PL-CI-8010, C-56-HC01-PL-CI-8000, PRECOM-56-HGHC-1000 | C-56-01HG-PL-CI-7800: FS, C-56-01HG-PL-CI-7810: FS, C-56-HC01-PL-ME-7620: FS, C-56-HC01-PL-CI-8010: FS, C-56-HC01-PL-CI-8000: FS, PRECOM-56-HGHC-1000: FS | ML1060, ML1020 | ML1060: FS, ML1020: FF |  | 2025-10-09 15:00
ML1969-E42 | Not Started | P2543-R01-Oct24..ML.CO1 | Achieve Mechanical Completion of PL & facilities- ( 36"Jump over Line) | C-36-KM-HT-ME-2000, C-36-KM-HT04-ME-1050, C-36-KM-HT03-ME-1050, C-36-KM-HT-EI-2050, C-36-KM-HT-PI-2000 | C-36-KM-HT-ME-2000: FS, C-36-KM-HT04-ME-1050: FS, C-36-KM-HT03-ME-1050: FS, C-36-KM-HT-EI-2050: FS, C-36-KM-HT-PI-2000: FS | ML1060 | ML1060: FS |  | 2025-08-21 09:00
ML1979-E43 | Not Started | P2543-R01-Oct24..ML.CO1 | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-HG01-1000, PRECOM-52-0201-1000, PRECOM-52-0203-1000, PRECOM-52-0304-1000, PRECOM-52-0506-1000, PRECOM-52-06CR-1000 | PRECOM-52-HG01-1000: FS, PRECOM-52-0201-1000: FS, PRECOM-52-0203-1000: FS, PRECOM-52-0304-1000: FS, PRECOM-52-0506-1000: FS, PRECOM-52-06CR-1000: FS 1 | ML1060, ML1030 | ML1060: FS, ML1030: FF 5 |  | 2025-11-04 11:30
ML1989-E44 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete As-Built drawings including Project close out report and submit to COMPANY | CAB-4480, CAB-5320 | CAB-4480: FF, CAB-5320: FS | ML1060 | ML1060: FS |  | 2026-01-09 10:58
ML1709-E16 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Pipeline welding - 52" Sales Gas Pipeline - 75% Welding | ML1699-E15, C-52-HG01-PL-ME-3600, C-52-0203-PL-ME-3600, C-52-0102-PL-ME-3600, C-52-0304-PL-ME-3600, C-52-0405-PL-ME-3600 | ML1699-E15: FS 49, C-52-HG01-PL-ME-3600: FS, C-52-0203-PL-ME-3600: FS, C-52-0102-PL-ME-3600: FS, C-52-0304-PL-ME-3600: FS, C-52-0405-PL-ME-3600: FS | ML1719-E17, ML1060 | ML1719-E17: FS, ML1060: FS |  | 2025-03-13 13:00
ML1659-E11 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -HGCP to BVS-3 | C-52-HG01-PL-CI-2210, C-52-HG01-PL-CI-2230, C-52-HG01-PL-CI-2010, C-52-0102-PL-CI-2230, C-52-0203-PL-CI-2230 | C-52-HG01-PL-CI-2210: FS, C-52-HG01-PL-CI-2230: FS, C-52-HG01-PL-CI-2010: FS, C-52-0102-PL-CI-2230: FS, C-52-0203-PL-CI-2230: FS | ML1060, ML1070 | ML1060: FS, ML1070: FS |  | 2024-10-27 07:00
ML1719-E17 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Pipeline welding - 52" Sales Gas Pipeline - 100% Welding | ML1709-E16, C-52-HG01-PL-ME-3600, C-52-0102-PL-ME-3600, C-52-0203-PL-ME-3600, C-52-0304-PL-ME-3600, C-52-0405-PL-ME-3600, C-52-0506-PL-ME-3600, C-52-06CR-PL-ME-3600 | ML1709-E16: FS, C-52-HG01-PL-ME-3600: FS, C-52-0102-PL-ME-3600: FS, C-52-0203-PL-ME-3600: FS, C-52-0304-PL-ME-3600: FS, C-52-0405-PL-ME-3600: FS, C-52-0506-PL-ME-3600: FS, C-52-06CR-PL-ME-3600: FS | ML1829-E28, ML1060, C-52-06CR-PL-CI-2400 | ML1829-E28: FS, ML1060: FS, C-52-06CR-PL-CI-2400: FF |  | 2025-07-21 15:00
ML1729-E18 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Construction of Anchor Blocks - 52" Sales Gas Pipeline | C-52-HG01-PL-ME-4800, C-52-0102-PL-ME-4800, C-52-0203-PL-ME-4800, C-52-0304-PL-ME-4800, C-52-0405-PL-ME-4800, C-52-0506-PL-ME-4800, C-52-06CR-PL-ME-4800, C-52-HG01-PL-ME-4800 | C-52-HG01-PL-ME-4800: FS, C-52-0102-PL-ME-4800: FS, C-52-0203-PL-ME-4800: FS, C-52-0304-PL-ME-4800: FS, C-52-0405-PL-ME-4800: FS, C-52-0506-PL-ME-4800: FS, C-52-06CR-PL-ME-4800: FS, C-52-HG01-PL-ME-4800: FF | ML1060 | ML1060: FS |  | 2025-07-29 15:00
ML1739-E19 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete foundations for Launchers and Receiver- 52" Sales Gas Pipeline | C-52-PL-838-CI-1400, C-52-PL-838-CI-1410, C-52-PL-838-CI-1420, C-52-PL-838-CI-1600, C-52-PR-839-CI-1600, C-52-PR-839-CI-1400, C-52-PR-839-CI-1410, C-52-PR-839-CI-1420, C-52-PL-838-CI-1700 | C-52-PL-838-CI-1400: FS, C-52-PL-838-CI-1410: FS, C-52-PL-838-CI-1420: FS, C-52-PL-838-CI-1600: FS, C-52-PR-839-CI-1600: FS, C-52-PR-839-CI-1400: FS, C-52-PR-839-CI-1410: FS, C-52-PR-839-CI-1420: FS, C-52-PL-838-CI-1700: FS | ML1060, PRECOM-56-PL-1000, PRECOM-56-PR-1000, PRECOM-52-PR-1000, PRECOM-52-PL-1000 | ML1060: FS, PRECOM-56-PL-1000: FS, PRECOM-56-PR-1000: FS, PRECOM-52-PR-1000: FS, PRECOM-52-PL-1000: FS |  | 2025-07-11 11:00
ML1749-E20 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-EL-0530, HM-ME-0790, HE-IC-0770, HM-IC-0040, HE-EL-0710, HE-EL-0290, HE-IC-1550, HE-EL-0650, HM-EL-0520, HM-ME-1590, HE-EL-0640, HE-IC-0530, HE-EL-1670, HM-EL-0380, HM-ME-0690, HM-EL-0080, HE-IC-1430, HM-ME-1690, HE-IC-0590, HE-IC-0010, HE-EL-1790, HE-E | HE-EL-0530: FS, HM-ME-0790: FS, HE-IC-0770: FS, HM-IC-0040: FS, HE-EL-0710: FS, HE-EL-0290: FS, HE-IC-1550: FS, HE-EL-0650: FS, HM-EL-0520: FS, HM-ME-1590: FS, HE-EL-0640: FS, HE-IC-0530: FS, HE-EL-1670: FS, HM-EL-0380: FS, HM-ME-0690: FS, HM-EL-0080: FS, | ML1060 | ML1060: FS |  | 2025-11-03 16:00
ML1759-E21 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Hydrotesting - 52" Sales Gas Pipeline -Launcher to BVS-01 | C-52-HG01-PL-ME-7430, C-52-HG01-PL-ME-7620 | C-52-HG01-PL-ME-7430: FS, C-52-HG01-PL-ME-7620: FS | ML1060, PRECOM-52-HG01-1000 | ML1060: FS, PRECOM-52-HG01-1000: FS |  | 2025-06-16 11:00
ML1769-E22 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 01 to BVS-02 | C-52-0102-PL-ME-7430, C-52-0102-PL-ME-7620 | C-52-0102-PL-ME-7430: FS, C-52-0102-PL-ME-7620: FS | ML1060, PRECOM-52-0201-1000 | ML1060: FS, PRECOM-52-0201-1000: FF |  | 2025-05-14 11:00
ML1779-E23 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 02 to BVS-03 | C-52-0203-PL-ME-7430, C-52-0203-PL-ME-7620 | C-52-0203-PL-ME-7430: FS, C-52-0203-PL-ME-7620: FS | ML1060, PRECOM-52-0203-1000 | ML1060: FS, PRECOM-52-0203-1000: FF |  | 2025-04-03 07:00
ML1789-E24 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 03 to BVS-04 | C-52-0304-PL-ME-7430, C-52-0304-PL-ME-7620 | C-52-0304-PL-ME-7430: FS, C-52-0304-PL-ME-7620: FS | ML1060, PRECOM-52-0304-1000 | ML1060: FS, PRECOM-52-0304-1000: FF |  | 2025-06-04 11:00
ML1799-E25 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 04 to BVS-05 | C-52-0405-PL-ME-7430, C-52-0405-PL-ME-7620 | C-52-0405-PL-ME-7430: FS, C-52-0405-PL-ME-7620: FS | ML1060, PRECOM-52-0405-1000 | ML1060: FS, PRECOM-52-0405-1000: FF |  | 2025-10-03 11:00
ML1559-E01 | Completed | P2543-R01-Oct24..ML.CO1 | Mobilization of Automatic Welding Machines at site | ML1002, HS-CN-0190 | ML1002: FS, HS-CN-0190: FS 30 | ML1060, C-COM-1010 | ML1060: FS, C-COM-1010: FS | 2024-03-11 07:00
ML1569-E02 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Site Grading & ROW along the Pipeline - 56" Sales Gas Pipeline | C-56-HC01-PL-CI-1800, C-56-01HG-PL-CI-1800, C-56-HC01-PL-CI-1400, C-56-01HG-PL-CI-1600, C-56-01HG-PL-CI-2230 | C-56-HC01-PL-CI-1800: FS, C-56-01HG-PL-CI-1800: FS, C-56-HC01-PL-CI-1400: FS, C-56-01HG-PL-CI-1600: FS, C-56-01HG-PL-CI-2230: FS | ML1060, C-56-01HG-PL-ME-5000, C-56-HC01-PL-ME-5000 | ML1060: FS, C-56-01HG-PL-ME-5000: FS, C-56-HC01-PL-ME-5000: FS |  | 2024-12-08 07:00
ML1579-E03 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | HE-PL-2970, ML1149-A07, ML1139-A06, HS-CN-0090, HE-PL-2910, C-56-HC01-CNM08-1800, C-56-HC01-CNM03-1800, C-56-HC01-CNH05-1800, C-56-HC01-CNH02-1800, C-56-HC01-CNH01-1800, C-56-01HG-CNM13-1800, C-56-01HG-CNM12-1800, C-56-01HG-CNM11-1800, C-56-01HG-CNH10-1800 | HE-PL-2970: FS, ML1149-A07: FS, ML1139-A06: FS, HS-CN-0090: FS, HE-PL-2910: FS, C-56-HC01-CNM08-1800: FS, C-56-HC01-CNM03-1800: FS, C-56-HC01-CNH05-1800: FS, C-56-HC01-CNH02-1800: FS, C-56-HC01-CNH01-1800: FS, C-56-01HG-CNM13-1800: FS, C-56-01HG-CNM12-1800 | ML1060, PRECOM-56-HGHC-1000 | ML1060: FS, PRECOM-56-HGHC-1000: FS |  | 2025-08-03 07:00
ML1589-E04 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Pipeline welding - 56" Sales Gas Pipeline (50% Welding) | C-56-01HG-PL-ME-3600, C-56-01HG-PL-ME-3800 | C-56-01HG-PL-ME-3600: FS, C-56-01HG-PL-ME-3800: FS | ML1060, ML1639-E09, C-56-HC01-PL-ME-3600 | ML1060: FS, ML1639-E09: FS, C-56-HC01-PL-ME-3600: FS |  | 2025-03-05 10:30
ML1599-E05 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Pipeline welding - 56" Sales Gas Pipeline (100% Welding) | C-56-HC01-PL-ME-3600 | C-56-HC01-PL-ME-3600: FS | ML1060, C-56-01HG-PL-ME-7400, ML1639-E09, C-56-HC01-PL-ME-4000 | ML1060: FS, C-56-01HG-PL-ME-7400: FS, ML1639-E09: FS, C-56-HC01-PL-ME-4000: FF |  | 2025-04-30 14:30
ML1609-E06 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete Construction of Anchor Blocks - 56" Sales Gas Pipeline | C-56-01HG-PL-ME-4800, C-56-01HG-PL-ME-5000, C-56-HC01-PL-ME-5000 | C-56-01HG-PL-ME-4800: FS, C-56-01HG-PL-ME-5000: FS, C-56-HC01-PL-ME-5000: FS | ML1060, PRECOM-56-HGHC-1000 | ML1060: FS, PRECOM-56-HGHC-1000: FS |  | 2025-06-15 07:00
ML1619-E07 | Not Started | P2543-R01-Oct24..ML.CO1 | Complete foundations for Launchers and Receiver- 56" Sales Gas Pipeline | C-56-PR-838-CI-1400, C-56-PR-838-CI-1410, C-56-PR-838-CI-1420, C-56-PR-838-CI-1600, C-56-PL-607-CI-1600, C-56-PL-607-CI-1420, C-56-PL-607-CI-1410, C-56-PL-607-CI-1400 | C-56-PR-838-CI-1400: FS, C-56-PR-838-CI-1410: FS, C-56-PR-838-CI-1420: FS, C-56-PR-838-CI-1600: FS, C-56-PL-607-CI-1600: FS, C-56-PL-607-CI-1420: FS, C-56-PL-607-CI-1410: FS, C-56-PL-607-CI-1400: FS | ML1060, PRECOM-56-EB2-1000, PRECOM-56-PR-1000 | ML1060: FS, PRECOM-56-EB2-1000: FS, PRECOM-56-PR-1000: FS |  | 2025-05-20 11:00
ML2009-F02 | Not Started | P2543-R01-Oct24..ML.4 | Commission New pipeline system -52" Sales Gas Pipeline | CCM-PM4520 | CCM-PM4520: FF | ML1060 | ML1060: FF |  | 2025-12-13 11:00
ML2019-F03 | Not Started | P2543-R01-Oct24..ML.4 | Commission New pipelines system - 4" Nitrogen Pipeline | CCM-PM4510 | CCM-PM4510: FS | ML1040 | ML1040: FF |  | 2025-11-18 11:00
ML2029-F04 | Not Started | P2543-R01-Oct24..ML.4 | Commission New pipelines system - 4" Water line | CCM-PM4510 | CCM-PM4510: FS | ML1040 | ML1040: FF |  | 2025-11-18 11:00
ML2039-F05 | Not Started | P2543-R01-Oct24..ML.4 | Achieve (PAC-1) for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | CCM-PM4510, CCM-PM4550, ML-PAC1 (Internal) | CCM-PM4510: FF, CCM-PM4550: FF, ML-PAC1 (Internal): FF | ML1060 | ML1060: FF 14 |  | 2025-12-09 15:00
ML2049-F06 | Not Started | P2543-R01-Oct24..ML.4 | Achieve (PAC-2) for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | CCM-PM4540, CCM-PM4530, CAB-5310, CAB-5300, CCM-PM4520, ML-PAC2 (Internal) | CCM-PM4540: FS, CCM-PM4530: FS, CAB-5310: FF, CAB-5300: FF, CCM-PM4520: FS, ML-PAC2 (Internal): FF | ML1050, ML1060 | ML1050: FF, ML1060: FF |  | 2026-01-09 10:58
ML1999-F01 | Not Started | P2543-R01-Oct24..ML.4 | Commission New pipeline system - 56" Sales Gas Pipeline | CCM-PM4510 | CCM-PM4510: FS | ML1040 | ML1040: FF |  | 2025-11-18 11:00
HM-EL-0410 | Not Started | P2543-R01-Oct24..PR.BK.16.2 | Vendor Document Review of MCT | HP-BK-0230 | HP-BK-0230: FS | HM-EL-0420 | HM-EL-0420: FS | 2024-11-29 17:30 | 2024-12-13 17:30
HM-EL-0420 | Not Started | P2543-R01-Oct24..PR.BK.16.2 | Manufacturing & Assembly of MCT | HM-EL-0410 | HM-EL-0410: FS | HM-EL-0430, HM-EL-0470 | HM-EL-0430: FS, HM-EL-0470: FS | 2024-12-13 17:30 | 2025-03-13 17:30
HM-EL-0430 | Not Started | P2543-R01-Oct24..PR.BK.16.2 | Factory Acceptance Test of MCT | HM-EL-0420 | HM-EL-0420: FS | HM-EL-0440 | HM-EL-0440: FS | 2025-03-13 17:30 | 2025-03-27 17:30
HM-EL-0440 | Not Started | P2543-R01-Oct24..PR.BK.16.2 | Packaging & Final Inspection-MCT | HM-EL-0430 | HM-EL-0430: FS | HM-EL-0450 | HM-EL-0450: FS | 2025-03-27 17:30 | 2025-04-03 17:30
HM-EL-0450 | Not Started | P2543-R01-Oct24..PR.BK.16.2 | Ready for Dispatch of MCT | HM-EL-0440, HP-BK-0230 | HM-EL-0440: FS, HP-BK-0230: FS | HM-EL-700 | HM-EL-700: FS 21 | 2025-04-03 17:30 | 2025-04-07 17:30
HM-EL-0480 | Not Started | P2543-R01-Oct24..PR.BK.16.3 | Receipt at site and inspection of MCT (Lot 1) | HM-EL-0470, HM-EL-0470 | HM-EL-0470: FS, HM-EL-0470: FF | ML1549-D32, C-56-EB2-EI-1000, C-52-EB1-EI-1000 | ML1549-D32: FF, C-56-EB2-EI-1000: FS, C-52-EB1-EI-1000: FS | 2025-04-17 17:30 | 2025-04-25 17:30
HM-EL-0470 | Not Started | P2543-R01-Oct24..PR.BK.16.3 | Transportation/ Custom Clearance/ Delivery at site of MCT (Lot 1) | HM-EL-0420 | HM-EL-0420: FS | HM-EL-0480, HM-EL-0480 | HM-EL-0480: FS, HM-EL-0480: FF | 2025-03-13 17:30 | 2025-04-17 17:30
HM-EL-0050 | Not Started | P2543-R01-Oct24..PR.BK.17.2 | Ready for Dispatch of Power & Control Cables | HM-EL-0040 | HM-EL-0040: FS | HM-EL-0070, HM-EL-620 | HM-EL-0070: FS, HM-EL-620: FS 21 | 2025-02-26 08:00 | 2025-03-01 18:00
HM-EL-0010 | Completed | P2543-R01-Oct24..PR.BK.17.2 | Vendor Document Review of Power & Control Cables | HP-BK-0030 | HP-BK-0030: FS | HM-EL-0020 | HM-EL-0020: FS | 2024-08-24 08:00 | 2024-10-10 18:00
HM-EL-0020 | In Progress | P2543-R01-Oct24..PR.BK.17.2 | Manufacturing & Assembly of Power & Control Cables | HE-EL-1190, HM-EL-0010, HE-EL-2000, HE-EL-2050, HE-EL-2100, HE-EL-2150, HE-EL-2200 | HE-EL-1190: FS, HM-EL-0010: FS, HE-EL-2000: SS, HE-EL-2050: FS, HE-EL-2100: FS, HE-EL-2150: FS, HE-EL-2200: FS | HM-EL-0030, HM-EL-0070 | HM-EL-0030: FS, HM-EL-0070: FS | 2024-10-11 | 2025-02-11 18:00
HM-EL-0030 | Not Started | P2543-R01-Oct24..PR.BK.17.2 | Testing and Inspection of Power & Control Cables | HM-EL-0020 | HM-EL-0020: FS | HM-EL-0040 | HM-EL-0040: FS | 2025-02-12 08:00 | 2025-02-18 18:00
HM-EL-0040 | Not Started | P2543-R01-Oct24..PR.BK.17.2 | Packaging & Final Inspection-Power & Control Cables | HM-EL-0030 | HM-EL-0030: FS | HM-EL-0050 | HM-EL-0050: FS | 2025-02-19 08:00 | 2025-02-25 18:00
HM-EL-0080 | Not Started | P2543-R01-Oct24..PR.BK.17.3 | Receipt at site and inspection of Power & Control Cables (Lot 1) | HM-EL-0070 | HM-EL-0070: FS 1 | ML1030, ML1859-E31, ML1749-E20, ML1549-D32, C-56-PL-607-EI-2000, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1200, C-56-EB2-EI-1000, C-56-EB2-EI-1210, C-56-EB2-EI-1220, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1549-D32: FF, C-56-PL-607-EI-2000: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-EB2-EI-1200: FS, C-56-EB2-EI-1000: FF, C-56-EB2-EI-1210: FS, C-56-EB2-EI-1220: FS, C-56-PR- | 2025-03-10 08:00 | 2025-03-17 18:00
HM-EL-0070 | Not Started | P2543-R01-Oct24..PR.BK.17.3 | Transportation/ Custom Clearance/ Delivery at site of Power & Control Cables (Lot 1) | HM-EL-0050, HM-EL-0020 | HM-EL-0050: FS, HM-EL-0020: FS | HM-EL-0080 | HM-EL-0080: FS 1 | 2025-03-02 08:00 | 2025-03-08 18:00
HM-EL-0210 | Not Started | P2543-R01-Oct24..PR.BK.13.2 | Vendor Document Review of Cable Trays | HP-BK-0130 | HP-BK-0130: FS | HM-EL-0220 | HM-EL-0220: FS | 2024-10-26 08:00 | 2024-11-06 18:00
HM-EL-0220 | Not Started | P2543-R01-Oct24..PR.BK.13.2 | Manufacturing & Assembly of Cable Trays | HM-EL-0210 | HM-EL-0210: FS | HM-EL-0230, HM-EL-0270 | HM-EL-0230: FS, HM-EL-0270: FS | 2024-11-07 08:00 | 2025-01-05 18:00
HM-EL-0230 | Not Started | P2543-R01-Oct24..PR.BK.13.2 | Factory Acceptance Test of Cable Trays | HM-EL-0220 | HM-EL-0220: FS | HM-EL-0240 | HM-EL-0240: FS | 2025-01-06 08:00 | 2025-01-19 18:00
HM-EL-0240 | Not Started | P2543-R01-Oct24..PR.BK.13.2 | Packaging & Final Inspection-Cable Trays | HM-EL-0230 | HM-EL-0230: FS | HM-EL-0250 | HM-EL-0250: FS | 2025-01-20 08:00 | 2025-01-26 18:00
HM-EL-0250 | Not Started | P2543-R01-Oct24..PR.BK.13.2 | Ready for Dispatch of Cable Trays | HP-BK-0130, HM-EL-0240 | HP-BK-0130: FS, HM-EL-0240: FS | HM-EL-640 | HM-EL-640: FS 21 | 2025-01-27 08:00 | 2025-01-30 18:00
HM-EL-0280 | Not Started | P2543-R01-Oct24..PR.BK.13.3 | Receipt at site and inspection of Cable Trays (Lot 2) | HM-EL-0270, HM-EL-0270 | HM-EL-0270: FF, HM-EL-0270: FS | ML1030, ML1859-E31, ML1749-E20, ML1549-D32, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1000, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C-56-PR-838-EI-2030, C-56-591-01-EI-1600, C-52- | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1549-D32: FF, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-EB2-EI-1000: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-EI-1400: FS, C-56-PR-838-EI-1810: FS, C-56-PR-838-EI-2020: FS, | 2025-01-27 07:00 | 2025-02-03 17:00
HM-EL-0270 | Not Started | P2543-R01-Oct24..PR.BK.13.3 | Transportation/ Custom Clearance/ Delivery at site of Cable Trays (Lot 1) | HM-EL-0220 | HM-EL-0220: FS | HM-EL-0280, HM-EL-0280 | HM-EL-0280: FF, HM-EL-0280: FS | 2025-01-06 08:00 | 2025-01-26 18:00
HM-CS-0020 | Not Started | P2543-R01-Oct24..PR.BK.11.2 | Final Civil Bulk material MTO | HP-BK-0270 | HP-BK-0270: FF 5 | HM-CS-0050 | HM-CS-0050: FF 7 | 2024-10-31 17:30 | 2024-12-17 17:30
HM-CS-0010 | Completed | P2543-R01-Oct24..PR.BK.11.2 | 1st Civil Bulk material MTO | HP-BK-0260 | HP-BK-0260: FS | HM-CS-0040 | HM-CS-0040: FS | 2024-04-09 | 2024-08-28 18:00
HM-CS-0050 | Not Started | P2543-R01-Oct24..PR.BK.11.3 | Final Civil Bulk material MTO | HM-CS-0020 | HM-CS-0020: FF 7 | C-56-EB2-CI-1400, C-56-G-HT-CI-1600, C-56-PR-838-CI-1400, C-56-PR-838-CI-1410, C-56-PR-838-CI-1420, C-56-PR-838-CI-1600, C-52-598-05-CI-1400, C-52-598-05-CI-1410, C-52-598-05-CI-1420, C-52-598-05-CI-1430, C-52-598-04-CI-1400, C-52-598-04-CI-1410, C-52-598- | C-56-EB2-CI-1400: FF 2, C-56-G-HT-CI-1600: FS, C-56-PR-838-CI-1400: FS, C-56-PR-838-CI-1410: FF, C-56-PR-838-CI-1420: FF, C-56-PR-838-CI-1600: FS, C-52-598-05-CI-1400: FF, C-52-598-05-CI-1410: FF, C-52-598-05-CI-1420: FF, C-52-598-05-CI-1430: FF, C-52-598- | 2024-10-30 07:00 | 2024-12-25 07:00
HM-CS-0040 | In Progress | P2543-R01-Oct24..PR.BK.11.3 | 1st Civil Bulk material MTO | HM-CS-0010 | HM-CS-0010: FS | C-56-PL-607-CI-1400, C-56-EB2-CI-1400, C-56-G-HT-CI-1600, C-56-PR-838-CI-1400, C-56-PR-838-CI-1410, C-56-PR-838-CI-1420, C-56-591-01-CI-1400, C-56-591-01-CI-1410, C-52-HG01-FENCE-1030, C-52-06CR-FENCE-1030, C-52-598-06-CI-1400, C-52-598-06-CI-1410, C-52-59 | C-56-PL-607-CI-1400: FS, C-56-EB2-CI-1400: SS, C-56-G-HT-CI-1600: FS, C-56-PR-838-CI-1400: SS, C-56-PR-838-CI-1410: SS, C-56-PR-838-CI-1420: SS, C-56-591-01-CI-1400: FS, C-56-591-01-CI-1410: FS, C-52-HG01-FENCE-1030: FF, C-52-06CR-FENCE-1030: FF, C-52-598- | 2024-09-10 07:00 | 2024-12-20 17:00
HM-CS-0090 | Not Started | P2543-R01-Oct24..PR.BK.5.2 | Final Structural Bulk material MTO | HP-BK-0310 | HP-BK-0310: FS | HM-CS-0120 | HM-CS-0120: FF 10 | 2024-12-31 17:30 | 2025-03-01 17:30
HM-CS-0080 | Not Started | P2543-R01-Oct24..PR.BK.5.2 | 1st Structural Bulk material MTO | HP-BK-0300 | HP-BK-0300: FS | HM-CS-0110 | HM-CS-0110: FF 10 | 2024-11-15 17:30 | 2025-02-13 17:30
HM-CS-0110 | Not Started | P2543-R01-Oct24..PR.BK.5.3 | 1st Structural Bulk material MTO | HM-CS-0080 | HM-CS-0080: FF 10 | ML1030, ML1020, C-56-PL-607-CI-2000, C-56-PL-607-CI-3000, C-56-EB2-CI-2000, C-56-G-HT-CI-2000, C-56-G-HT-CI-1420, C-56-PR-838-CI-2000, C-56-PR-838-CI-3000, C-56-591-01-CI-2000, C-56-591-01-CI-2400, C-56-591-01-CI-3000, C-52-598-06-CI-2000, C-52-598-06-CI-2 | ML1030: FS, ML1020: FS, C-56-PL-607-CI-2000: FS, C-56-PL-607-CI-3000: FS, C-56-EB2-CI-2000: FS, C-56-G-HT-CI-2000: FS, C-56-G-HT-CI-1420: FS, C-56-PR-838-CI-2000: FS, C-56-PR-838-CI-3000: FS, C-56-591-01-CI-2000: FS, C-56-591-01-CI-2400: FS, C-56-591-01-CI | 2025-01-12 07:00 | 2025-02-24 07:00
HM-CS-0120 | Not Started | P2543-R01-Oct24..PR.BK.5.3 | Final Structural Bulk material MTO | HM-CS-0090 | HM-CS-0090: FF 10 | C-56-G-HT-CI-2000, C-56-PR-838-CI-2000, C-56-591-01-CI-2000, C-52-598-06-CI-2000, C-52-598-06-CI-3000, C-52-598-06-CI-3010, C-52-598-05-CI-2000, C-52-598-05-CI-3000, C-52-598-05-CI-3010, C-52-598-04-CI-2000, C-52-598-04-CI-3000, C-52-598-04-CI-3010, C-52-5 | C-56-G-HT-CI-2000: FS, C-56-PR-838-CI-2000: FS, C-56-591-01-CI-2000: FF, C-52-598-06-CI-2000: FS, C-52-598-06-CI-3000: FS, C-52-598-06-CI-3010: FS, C-52-598-05-CI-2000: FS, C-52-598-05-CI-3000: FS, C-52-598-05-CI-3010: FS, C-52-598-04-CI-2000: FS, C-52-598 | 2025-01-23 07:00 | 2025-03-12 09:00
HM-PI-0020 | Not Started | P2543-R01-Oct24..PR.BK.4.2 | Final Piping Bulk material MTO | HP-BK-0350, HE-HS-0470, HM-PI-0010 | HP-BK-0350: FS, HE-HS-0470: FF, HM-PI-0010: FF 45 | HM-PI-0050 | HM-PI-0050: FF 14 | 2024-12-04 08:00 | 2025-03-19 18:00
HM-PI-0010 | Not Started | P2543-R01-Oct24..PR.BK.4.2 | 1st Piping Bulk material MTO | HP-BK-0340 | HP-BK-0340: FS | HM-PI-0040, HM-PI-0020 | HM-PI-0040: FF 21, HM-PI-0020: FF 45 | 2024-10-26 08:00 | 2025-02-02 18:00
HM-PI-0050 | Not Started | P2543-R01-Oct24..PR.BK.4.3 | Final Piping Bulk material MTO | HM-PI-0020 | HM-PI-0020: FF 14 | ML1549-D32, C-56-PL-607-PI-1200, C-56-591-01-PI-1200, C-52-598-06-PI-1000, C-52-598-06-PI-1200, C-52-598-05-PI-1000, C-52-598-05-PI-1200, C-52-598-04-PI-1200, C-52-598-03-PI-1200, C-52-598-02-PI-1200, C-52-598-01-PI-1200, C-52-598-01-PI-1600, C-52-598-01-P | ML1549-D32: FF, C-56-PL-607-PI-1200: FS, C-56-591-01-PI-1200: FF, C-52-598-06-PI-1000: FS 14, C-52-598-06-PI-1200: FS, C-52-598-05-PI-1000: FS, C-52-598-05-PI-1200: FS, C-52-598-04-PI-1200: FS, C-52-598-03-PI-1200: FS, C-52-598-02-PI-1200: FS, C-52-598-01- | 2025-01-09 07:00 | 2025-04-03 07:00
HM-PI-0040 | Not Started | P2543-R01-Oct24..PR.BK.4.3 | 1st Piping Bulk material MTO | HM-PI-0010 | HM-PI-0010: FF 21 | C-56-PL-607-PI-1000, C-56-PL-607-PI-1200, C-56-G-HT-PI-1000, C-56-G-HT-PI-1200, C-56-G-HT101-ME-1000, C-56-PR-838-PI-1000, C-56-PR-838-PI-1200, C-56-591-01-PI-1000, C-56-591-01-PI-1200, C-52-598-06-PI-1000, C-52-598-06-PI-1200, C-52-598-05-PI-1000, C-52-59 | C-56-PL-607-PI-1000: FS, C-56-PL-607-PI-1200: FS, C-56-G-HT-PI-1000: FS, C-56-G-HT-PI-1200: FS, C-56-G-HT101-ME-1000: FS, C-56-PR-838-PI-1000: FS, C-56-PR-838-PI-1200: FS, C-56-591-01-PI-1000: FS, C-56-591-01-PI-1200: FS, C-52-598-06-PI-1000: FS, C-52-598- | 2024-12-26 08:00 | 2025-02-23 18:00
HM-PL-0860 | Not Started | P2543-R01-Oct24..PR.BK.6.2 | Final Pipeline Bulk material MTO | HP-BK-0390 | HP-BK-0390: FS | HM-PL-0890 | HM-PL-0890: FS | 2024-10-26 08:00 | 2024-11-11 18:00
HM-PL-0850 | Not Started | P2543-R01-Oct24..PR.BK.6.2 | 1st Pipeline Bulk material MTO | HP-BK-0380 | HP-BK-0380: FS | HM-PL-0880 | HM-PL-0880: FS | 2024-10-26 08:00 | 2024-11-04 18:00
HM-PL-0880 | Not Started | P2543-R01-Oct24..PR.BK.6.3 | 1st Pipeline Bulk material MTO | HM-PL-0850 | HM-PL-0850: FS | C-56-HC01-PL-ME-2800, C-56-HC01-PL-ME-3600, C-56-01HG-PL-ME-3600, C-56-01HG-PL-ME-3800, C-52-06CR-PL-ME-2800, C-52-0506-PL-ME-3600, C-52-0405-PL-ME-3600, C-52-0304-PL-ME-3600 | C-56-HC01-PL-ME-2800: FF, C-56-HC01-PL-ME-3600: FS, C-56-01HG-PL-ME-3600: FS, C-56-01HG-PL-ME-3800: FS, C-52-06CR-PL-ME-2800: FF, C-52-0506-PL-ME-3600: FS, C-52-0405-PL-ME-3600: FS, C-52-0304-PL-ME-3600: FS | 2024-11-05 07:00 | 2024-11-12 17:00
HM-PL-0890 | Not Started | P2543-R01-Oct24..PR.BK.6.3 | Final Pipeline Bulk material MTO | HM-PL-0860 | HM-PL-0860: FS | C-56-01HG-PL-ME-3600 | C-56-01HG-PL-ME-3600: FF | 2024-11-12 07:00 | 2024-11-27 17:00
HM-EL-0500 | Not Started | P2543-R01-Oct24..PR.BK.7.2 | Final Electrical Bulk material MTO | HM-EL-0490, HP-BK-0430 | HM-EL-0490: FF 65, HP-BK-0430: FS | HM-EL-0530 | HM-EL-0530: FS 1 | 2025-01-12 08:00 | 2025-04-08 18:00
HM-EL-0490 | Not Started | P2543-R01-Oct24..PR.BK.7.2 | 1st Electrical Bulk material MTO | HP-BK-0420 | HP-BK-0420: FS | HM-EL-0500, HM-EL-0520 | HM-EL-0500: FF 65, HM-EL-0520: FS | 2024-10-26 08:00 | 2025-02-02 18:00
HM-EL-0530 | Not Started | P2543-R01-Oct24..PR.BK.7.3 | Final Electrical Bulk material MTO | HM-EL-0520, HM-EL-0500 | HM-EL-0520: FS, HM-EL-0500: FS 1 | ML1549-D32, C-56-591-01-EI-1600, C-52-598-06-EI-1210, C-52-598-06-EI-1400, C-52-598-05-EI-1210, C-52-598-05-EI-1400, C-52-598-04-EI-1210, C-52-598-04-EI-1400, C-52-598-03-EI-1210, C-52-598-03-EI-1400, C-52-598-02-EI-1210, C-52-598-02-EI-1400, C-52-598-01-E | ML1549-D32: FF, C-56-591-01-EI-1600: FF, C-52-598-06-EI-1210: FF, C-52-598-06-EI-1400: FF, C-52-598-05-EI-1210: FF, C-52-598-05-EI-1400: FF, C-52-598-04-EI-1210: FF, C-52-598-04-EI-1400: FF, C-52-598-03-EI-1210: FF, C-52-598-03-EI-1400: FF, C-52-598-02-EI- | 2025-04-17 17:00 | 2025-05-17 17:00
HM-EL-0520 | Not Started | P2543-R01-Oct24..PR.BK.7.3 | 1st Electrical Bulk material MTO | HM-EL-0490 | HM-EL-0490: FS | ML1030, ML1859-E31, ML1749-E20, HM-EL-0530, C-56-PL-607-EI-2000, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1200, C-56-EB2-EI-1000, C-56-EB2-EI-1210, C-56-EB2-EI-1220, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, HM-EL-0530: FS, C-56-PL-607-EI-2000: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-EB2-EI-1200: FS, C-56-EB2-EI-1000: FS, C-56-EB2-EI-1210: FS, C-56-EB2-EI-1220: FS, C-56-PR- | 2025-02-03 07:00 | 2025-04-17 17:00
HM-IC-0020 | Not Started | P2543-R01-Oct24..PR.BK.8.2 | Final Instrumentation Bulk material MTO | HP-BK-0470 | HP-BK-0470: FS | HM-IC-0050 | HM-IC-0050: FS | 2024-11-22 17:30 | 2025-02-05 17:30
HM-IC-0010 | Not Started | P2543-R01-Oct24..PR.BK.8.2 | 1st Instrumentation Bulk material MTO | HP-BK-0460 | HP-BK-0460: FS | HM-IC-0040 | HM-IC-0040: FS | 2024-10-26 08:00 | 2025-02-02 18:00
HM-IC-0050 | Not Started | P2543-R01-Oct24..PR.BK.8.3 | Final Instrumentation Bulk material MTO | HM-IC-0020 | HM-IC-0020: FS | ML1549-D32, C-56-591-01-EI-1600, C-52-598-06-EI-1210, C-52-598-06-EI-1400, C-52-598-05-EI-1210, C-52-598-05-EI-1400, C-52-598-04-EI-1210, C-52-598-04-EI-1400, C-52-598-03-EI-1210, C-52-598-03-EI-1400, C-52-598-02-EI-1210, C-52-598-02-EI-1400, C-52-598-01-E | ML1549-D32: FF, C-56-591-01-EI-1600: FF, C-52-598-06-EI-1210: FF, C-52-598-06-EI-1400: FF, C-52-598-05-EI-1210: FF, C-52-598-05-EI-1400: FF, C-52-598-04-EI-1210: FF, C-52-598-04-EI-1400: FF, C-52-598-03-EI-1210: FF, C-52-598-03-EI-1400: FF, C-52-598-02-EI- | 2025-02-05 17:30 | 2025-03-30 17:30
HM-IC-0040 | Not Started | P2543-R01-Oct24..PR.BK.8.3 | 1st Instrumentation Bulk material MTO | HM-IC-0010 | HM-IC-0010: FS | ML1030, ML1859-E31, ML1749-E20, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C-56-PR-838-EI-2030, C-56-591-01-EI-1600, C-52-598-06-EI-1210, C-52-598-06-EI | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, C-56-PL-607-EI-1400: FF, C-56-PL-607-EI-2200: FF, C-56-PL-607-EI-1800: FF, C-56-PR-838-EI-1010: FS, C-56-PR-838-EI-1400: FS, C-56-PR-838-EI-1810: FS, C-56-PR-838-EI-2020: FS, C-56-PR-838-EI-2030: FS, C-56-591-01- | 2025-02-03 07:00 | 2025-04-11 17:00
HM-TL-0020 | Not Started | P2543-R01-Oct24..PR.BK.9.2 | Final Telecom Bulk material MTO | HP-BK-0510 | HP-BK-0510: FS | HM-TL-0050 | HM-TL-0050: FS | 2024-12-24 17:30 | 2025-02-22 17:30
HM-TL-0010 | Not Started | P2543-R01-Oct24..PR.BK.9.2 | 1st Telecom Bulk material MTO | HP-BK-0500 | HP-BK-0500: FS | HM-TL-0040 | HM-TL-0040: FS | 2024-10-26 08:00 | 2025-02-02 18:00
HM-TL-0050 | Not Started | P2543-R01-Oct24..PR.BK.9.3 | Final Telecom Bulk material MTO | HM-TL-0020 | HM-TL-0020: FS | ML1549-D32, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-591-01-TE-1000, C-52-598-06-TE-1000, C-52-598-05-TE-1000, C-52-598-04-TE-1000, C-52-598-03-TE-1000, C-52-598-02-TE-1000, C-52-598-01-TE-1000, C-56-PL-607-EI-2410 | ML1549-D32: FF, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-591-01-TE-1000: FS, C-52-598-06-TE-1000: FS, C-52-598-05-TE-1000: FS, C-52-598-04-TE-1000: FS, C-52-598-03-TE-1000: FS, C-52-598-02-TE-1000: FS, C-52-598-01-TE- | 2025-02-22 17:30 | 2025-03-24 17:30
HM-TL-0040 | Not Started | P2543-R01-Oct24..PR.BK.9.3 | 1st Telecom Bulk material MTO | HM-TL-0010 | HM-TL-0010: FS | ML1030, C-56-PL-607-TE-1200, C-56-PL-607-TE-1400, C-56-PL-607-TE-1600, C-56-EB2-TE-1000, C-56-HC01-PL-TE-8200, C-56-HC01-PL-TE-8400, C-56-PR-838-TE-1000, C-56-591-01-TE-1000, C-52-598-06-TE-1000, C-52-598-05-TE-1000, C-52-598-04-TE-1000, C-52-598-03-TE-100 | ML1030: FS, C-56-PL-607-TE-1200: FS, C-56-PL-607-TE-1400: FS, C-56-PL-607-TE-1600: FS, C-56-EB2-TE-1000: FS, C-56-HC01-PL-TE-8200: FS 32, C-56-HC01-PL-TE-8400: FS, C-56-PR-838-TE-1000: FS, C-56-591-01-TE-1000: FS, C-52-598-06-TE-1000: FS, C-52-598-05-TE-10 | 2025-02-03 07:00 | 2025-04-08 17:00
HM-EL-0310 | Not Started | P2543-R01-Oct24..PR.BK.15.2 | Vendor Document Review of Earthing Material | HP-BK-0180 | HP-BK-0180: FS | HM-EL-0320 | HM-EL-0320: FS | 2024-11-08 17:30 | 2024-11-18 17:30
HM-EL-0320 | Not Started | P2543-R01-Oct24..PR.BK.15.2 | Manufacturing & Assembly of Earthing Material | HM-EL-0310 | HM-EL-0310: FS | HM-EL-0330, HM-EL-0370 | HM-EL-0330: FS, HM-EL-0370: FS | 2024-11-18 17:30 | 2025-01-17 17:30
HM-EL-0330 | Not Started | P2543-R01-Oct24..PR.BK.15.2 | Factory Acceptance Test of Earthing Material | HM-EL-0320 | HM-EL-0320: FS | HM-EL-0340 | HM-EL-0340: FS | 2025-01-17 17:30 | 2025-01-27 17:30
HM-EL-0340 | Not Started | P2543-R01-Oct24..PR.BK.15.2 | Packaging & Final Inspection-Earthing Material | HM-EL-0330 | HM-EL-0330: FS | HM-EL-0350 | HM-EL-0350: FS | 2025-01-27 17:30 | 2025-02-03 17:30
HM-EL-0350 | Not Started | P2543-R01-Oct24..PR.BK.15.2 | Ready for Dispatch of Earthing Material | HP-BK-0180, HM-EL-0340 | HP-BK-0180: FS, HM-EL-0340: FS | HM-EL-680 | HM-EL-680: FS 21 | 2025-02-03 17:30 | 2025-02-07 17:30
HM-EL-0380 | Not Started | P2543-R01-Oct24..PR.BK.15.3 | Receipt at site and inspection of Earthing Material (Lot 1) | HM-EL-0370, HM-EL-0370 | HM-EL-0370: FF, HM-EL-0370: FS | ML1030, ML1859-E31, ML1749-E20, ML1549-D32, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1000, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C-56-PR-838-EI-2030, C-56-591-01-EI-1600, C-52- | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1549-D32: FF, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-EB2-EI-1000: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-EI-1400: FS, C-56-PR-838-EI-1810: FS, C-56-PR-838-EI-2020: FS, | 2025-02-18 07:00 | 2025-02-25 17:00
HM-EL-0370 | Not Started | P2543-R01-Oct24..PR.BK.15.3 | Transportation/ Custom Clearance/ Delivery at site of Earthing Material (Lot 1) | HM-EL-0320 | HM-EL-0320: FS | HM-EL-0380, HM-EL-0380 | HM-EL-0380: FF, HM-EL-0380: FS | 2025-01-17 17:30 | 2025-02-17 17:30
HM-ME-0310 | Completed | P2543-R01-Oct24..PR.26.LL.11.2 | Vendor Document Review of Filter Package | HP-ME-0180 | HP-ME-0180: FS | HM-ME-0320 | HM-ME-0320: SS | 2024-04-05 | 2024-06-14 18:00
HM-ME-0320 | In Progress | P2543-R01-Oct24..PR.26.LL.11.2 | Manufacturing & Assembly of Filter Package | HE-PR-0590, HM-ME-0310, HE-ME-0170, HE-PR-1300, HE-PR-1350, HE-PR-1400, HE-PR-1450, HE-PR-1500, HE-PR-1550, HE-PR-1600, HE-ME-520 | HE-PR-0590: FS, HM-ME-0310: SS, HE-ME-0170: FS, HE-PR-1300: FS, HE-PR-1350: FS, HE-PR-1400: FS, HE-PR-1450: FS, HE-PR-1500: FS, HE-PR-1550: FS, HE-PR-1600: FS, HE-ME-520: FS | HM-ME-0330 | HM-ME-0330: FS | 2024-06-17 08:00 | 2025-01-20 18:00
HM-ME-0330 | Not Started | P2543-R01-Oct24..PR.26.LL.11.2 | Testing and Inspection of Filter Package | HM-ME-0320 | HM-ME-0320: FS | HM-ME-0340 | HM-ME-0340: FS | 2025-01-21 08:00 | 2025-01-26 18:00
HM-ME-0340 | Not Started | P2543-R01-Oct24..PR.26.LL.11.2 | Packaging & Final Inspection-Filter Package | HM-ME-0330 | HM-ME-0330: FS | HM-ME-0350 | HM-ME-0350: FS | 2025-01-27 08:00 | 2025-02-01 18:00
HM-ME-0350 | Not Started | P2543-R01-Oct24..PR.26.LL.11.2 | Ready for Dispatch of Filter Package | HM-ME-0340, HP-ME-0180 | HM-ME-0340: FS, HP-ME-0180: FS | HM-ME-0370 | HM-ME-0370: FS | 2025-02-02 08:00 | 2025-02-05 18:00
HM-ME-0380 | Not Started | P2543-R01-Oct24..PR.26.LL.11.3 | Receipt at site and inspection of Filter Package | HM-ME-0370 | HM-ME-0370: FS | CAB-5310, C-52-PR-839-ME-1800, C-52-PR-839-ME-1800 | CAB-5310: FS, C-52-PR-839-ME-1800: FS, C-52-PR-839-ME-1800: FF | 2025-02-13 07:00 | 2025-02-20 17:00
HM-ME-0370 | Not Started | P2543-R01-Oct24..PR.26.LL.11.3 | Transportation/ Custom Clearance/ Delivery at site of Filter Package | HM-ME-0350 | HM-ME-0350: FS | HM-ME-0380 | HM-ME-0380: FS | 2025-02-06 08:00 | 2025-02-12 18:00
HM-ME-1220 | Completed | P2543-R01-Oct24..PR.26.LL.4.2 | Vendor Document Review of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | HP-ME-0630 | HP-ME-0630: FS | HM-ME-1230 | HM-ME-1230: FF | 2024-06-27 | 2024-09-30 18:00
HM-ME-1230 | In Progress | P2543-R01-Oct24..PR.26.LL.4.2 | Manufacturing & Assembly of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | HM-ME-1220 | HM-ME-1220: FF | HM-ME-1240, HM-ME-1280 | HM-ME-1240: FS, HM-ME-1280: FS | 2024-07-26 08:00 | 2025-03-18 18:00
HM-ME-1240 | Not Started | P2543-R01-Oct24..PR.26.LL.4.2 | Testing and Inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | HM-ME-1230 | HM-ME-1230: FS | HM-ME-1250 | HM-ME-1250: FS | 2025-03-19 08:00 | 2025-03-28 18:00
HM-ME-1250 | Not Started | P2543-R01-Oct24..PR.26.LL.4.2 | Packaging & Final Inspection-Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | HM-ME-1240 | HM-ME-1240: FS | HM-ME-1260 | HM-ME-1260: FS | 2025-03-29 08:00 | 2025-04-04 18:00
HM-ME-1260 | Not Started | P2543-R01-Oct24..PR.26.LL.4.2 | Ready for Dispatch of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | HP-ME-0630, HM-ME-1250 | HP-ME-0630: FS, HM-ME-1250: FS | HM-ME-2260 | HM-ME-2260: FS 20 | 2025-04-05 08:00 | 2025-04-08 18:00
HM-ME-1290 | Not Started | P2543-R01-Oct24..PR.26.LL.4.3 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | HM-ME-1280 | HM-ME-1280: FS | ML1479-D15, CAB-5310, ML1056-D14, C-56-PL-607-TE-1200, C-56-PL-607-TE-1400, C-56-PL-607-TE-1600, C-56-591-01-TE-1000, C-52-598-06-TE-1000, C-52-598-05-TE-1000, C-52-598-04-TE-1000, C-52-598-03-TE-1000, C-52-598-02-TE-1000, C-52-598-01-TE-1000, C-52-PR-839- | ML1479-D15: FF, CAB-5310: FS, ML1056-D14: FS, C-56-PL-607-TE-1200: FS, C-56-PL-607-TE-1400: FS, C-56-PL-607-TE-1600: FS, C-56-591-01-TE-1000: FS, C-52-598-06-TE-1000: FS, C-52-598-05-TE-1000: FS, C-52-598-04-TE-1000: FS, C-52-598-03-TE-1000: FS, C-52-598-0 | 2025-04-09 07:00 | 2025-04-16 17:00
HM-ME-1280 | Not Started | P2543-R01-Oct24..PR.26.LL.4.3 | Transportation/ Custom Clearance/ Delivery at site of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | HM-ME-1230 | HM-ME-1230: FS | HM-ME-1290 | HM-ME-1290: FS | 2025-03-19 08:00 | 2025-04-08 18:00
HM-ME-1390 | Not Started | P2543-R01-Oct24..PR.26.1.14.3 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | HM-ME-1380 | HM-ME-1380: FS | ML1479-D15, CAB-5310, C-56-EB2-EI-1000, C-56-EB2-TE-1000, C-56-591-01-TE-1000, C-52-598-06-TE-1000, C-52-598-05-TE-1000, C-52-598-04-TE-1000, C-52-598-03-TE-1000, C-52-598-02-TE-1000, C-52-598-01-TE-1000, C-52-EB1-TE-1000 | ML1479-D15: FS, CAB-5310: FS, C-56-EB2-EI-1000: FS, C-56-EB2-TE-1000: FS, C-56-591-01-TE-1000: FS, C-52-598-06-TE-1000: FS, C-52-598-05-TE-1000: FS, C-52-598-04-TE-1000: FS, C-52-598-03-TE-1000: FS, C-52-598-02-TE-1000: FS, C-52-598-01-TE-1000: FS, C-52-EB | 2025-04-03 07:00 | 2025-04-10 17:00
HM-ME-1380 | Not Started | P2543-R01-Oct24..PR.26.1.14.3 | Transportation/ Custom Clearance/ Delivery at site of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | HM-ME-1330 | HM-ME-1330: FS | HM-ME-1390 | HM-ME-1390: FS | 2025-03-12 08:00 | 2025-04-01 18:00
HM-ME-1320 | Completed | P2543-R01-Oct24..PR.26.1.14.2 | Vendor Document Review of Access Switch, Fiber Optic Patch Panel and Media Converter | ML1329-C17, HP-ME-0680, ML1339-C18 | ML1329-C17: FS, HP-ME-0680: FS, ML1339-C18: FS | HM-ME-1330 | HM-ME-1330: FF | 2024-06-27 17:30 | 2024-10-12 18:00
HM-ME-1330 | In Progress | P2543-R01-Oct24..PR.26.1.14.2 | Manufacturing & Assembly of Access Switch, Fiber Optic Patch Panel and Media Converter | HE-TL-0590, HM-ME-1320, HE-TL-0530 | HE-TL-0590: FF, HM-ME-1320: FF, HE-TL-0530: FF | HM-ME-1340, HM-ME-1380 | HM-ME-1340: FS, HM-ME-1380: FS | 2024-07-26 17:30 | 2025-03-11 18:00
HM-ME-1340 | Not Started | P2543-R01-Oct24..PR.26.1.14.2 | Factory Acceptance Test of Access Switch, Fiber Optic Patch Panel and Media Converter | HM-ME-1330 | HM-ME-1330: FS | HM-ME-1350 | HM-ME-1350: FS | 2025-03-12 08:00 | 2025-03-18 18:00
HM-ME-1350 | Not Started | P2543-R01-Oct24..PR.26.1.14.2 | Packaging & Final Inspection-Access Switch, Fiber Optic Patch Panel and Media Converter | HM-ME-1340 | HM-ME-1340: FS | HM-ME-1360 | HM-ME-1360: FS | 2025-03-19 08:00 | 2025-03-25 18:00
HM-ME-1360 | Not Started | P2543-R01-Oct24..PR.26.1.14.2 | Ready for Dispatch of Access Switch, Fiber Optic Patch Panel and Media Converter | HM-ME-1350, HP-ME-0680 | HM-ME-1350: FS, HP-ME-0680: FS | HM-ME-2280 | HM-ME-2280: FS 21 | 2025-03-26 08:00 | 2025-03-29 18:00
HM-EL-0150 | Completed | P2543-R01-Oct24..PR.26.LL.19.2 | Ready for Dispatch of FOC Cables | HM-EL-0140 | HM-EL-0140: FS | HM-EL-600 | HM-EL-600: FS 21 | 2024-09-14 08:00 | 2024-09-30 18:00
HM-EL-0110 | Completed | P2543-R01-Oct24..PR.26.LL.19.2 | Vendor Document Review of FOC Cables | HP-BK-0080 | HP-BK-0080: FS | HM-EL-0120 | HM-EL-0120: FS | 2024-05-07 | 2024-05-15
HM-EL-0120 | Completed | P2543-R01-Oct24..PR.26.LL.19.2 | Manufacturing & Assembly of FOC Cables | HM-EL-0110 | HM-EL-0110: FS | HM-EL-0130, HM-EL-0170 | HM-EL-0130: FS, HM-EL-0170: FS | 2024-05-15 | 2024-07-05 18:00
HM-EL-0130 | Completed | P2543-R01-Oct24..PR.26.LL.19.2 | Testing and Inspection of FOC Cables | HM-EL-0120 | HM-EL-0120: FS | HM-EL-0140 | HM-EL-0140: FS | 2024-07-26 | 2024-08-02 18:00
HM-EL-0140 | Completed | P2543-R01-Oct24..PR.26.LL.19.2 | Packaging & Final Inspection-FOC Cables | HM-EL-0130 | HM-EL-0130: FS | HM-EL-0150 | HM-EL-0150: FS | 2024-08-05 08:00 | 2024-09-13 18:00
HM-EL-0170 | Completed | P2543-R01-Oct24..PR.26.LL.19.3 | Transportation/ Custom Clearance/ Delivery at site of FOC Cables (Lot 1) | HM-EL-0120 | HM-EL-0120: FS | HM-EL-0180 | HM-EL-0180: FS | 2024-08-03 08:00 | 2024-08-09 18:00
HM-EL-0180 | Completed | P2543-R01-Oct24..PR.26.LL.19.3 | Receipt at site and inspection of FOC Cables (Lot 1) | HM-EL-0170 | HM-EL-0170: FS | ML1057-D19, C-56-PL-607-TE-1200, C-56-PL-607-TE-1400, C-56-PL-607-TE-1600, C-56-EB2-TE-1000, C-56-HC01-PL-TE-8200, C-56-HC01-PL-TE-8400, C-56-01HG-PL-TE-8200, C-56-01HG-PL-TE-8400, C-56-PR-838-TE-1000, C-56-591-01-TE-1000, C-52-06CR-PL-TE-8200, C-52-0506-P | ML1057-D19: FF, C-56-PL-607-TE-1200: FS, C-56-PL-607-TE-1400: FS, C-56-PL-607-TE-1600: FS, C-56-EB2-TE-1000: FS, C-56-HC01-PL-TE-8200: FS, C-56-HC01-PL-TE-8400: FS, C-56-01HG-PL-TE-8200: FS, C-56-01HG-PL-TE-8400: FS, C-56-PR-838-TE-1000: FS, C-56-591-01-TE | 2024-08-09 08:00 | 2024-08-16 18:00
HM-ME-1920 | In Progress | P2543-R01-Oct24..PR.26.1.13.2 | Vendor Document Review of Fire Fighting & Safety Equipment | HP-ME-0980 | HP-ME-0980: FS | HM-ME-1930 | HM-ME-1930: FS | 2024-09-20 08:00 | 2024-11-02 18:00
HM-ME-1930 | Not Started | P2543-R01-Oct24..PR.26.1.13.2 | Manufacturing & Assembly of Fire Fighting & Safety Equipment | HM-ME-1920, HE-HS-1260 | HM-ME-1920: FS, HE-HS-1260: FF | HM-ME-1940, HM-ME-1980 | HM-ME-1940: FS, HM-ME-1980: SS 150 | 2024-11-03 08:00 | 2025-03-12 18:00
HM-ME-1940 | Not Started | P2543-R01-Oct24..PR.26.1.13.2 | Factory Acceptance Test of Fire Fighting & Safety Equipment | HM-ME-1930 | HM-ME-1930: FS | HM-ME-1950 | HM-ME-1950: FS | 2025-03-13 08:00 | 2025-03-19 18:00
HM-ME-1950 | Not Started | P2543-R01-Oct24..PR.26.1.13.2 | Packaging & Final Inspection-Fire Fighting & Safety Equipment | HM-ME-1940 | HM-ME-1940: FS | HM-ME-1960 | HM-ME-1960: FS | 2025-03-20 08:00 | 2025-03-26 18:00
HM-ME-1960 | Not Started | P2543-R01-Oct24..PR.26.1.13.2 | Ready for Dispatch of Fire Fighting & Safety Equipment | HM-ME-1950 | HM-ME-1950: FS | HM-ME-2360 | HM-ME-2360: FS | 2025-03-27 08:00 | 2025-03-30 18:00
HM-ME-1990 | Not Started | P2543-R01-Oct24..PR.26.1.13.3 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 1) | HM-ME-1980 | HM-ME-1980: FS | C-56-PL-607-ME-1600, C-56-591-01-ME-1000, C-52-598-06-ME-1000, C-52-598-05-ME-1000, C-52-598-04-ME-1000, C-52-598-03-ME-1000, C-52-598-02-ME-1000, C-52-598-01-ME-1000, C-52-PR-839-ME-1600 | C-56-PL-607-ME-1600: FS, C-56-591-01-ME-1000: FS, C-52-598-06-ME-1000: FS, C-52-598-05-ME-1000: FS, C-52-598-04-ME-1000: FS, C-52-598-03-ME-1000: FS, C-52-598-02-ME-1000: FS, C-52-598-01-ME-1000: FS, C-52-PR-839-ME-1600: FS | 2025-04-09 08:00 | 2025-04-15 18:00
HM-ME-1980 | Not Started | P2543-R01-Oct24..PR.26.1.13.3 | Transportation/ Custom Clearance/ Delivery at site of Fire Fighting & Safety Equipment (Lot 1) | HM-ME-1930 | HM-ME-1930: SS 150 | HM-ME-1990 | HM-ME-1990: FS | 2025-04-02 08:00 | 2025-04-08 18:00
HM-ME-1520 | Completed | P2543-R01-Oct24..PR.26.1.15.2 | Vendor Document Review of Field Instruments | ML1269-C12, ML1028-C20, HP-ME-0780, HE-IC-2450 | ML1269-C12: FS, ML1028-C20: FS, HP-ME-0780: FS, HE-IC-2450: FF | HM-ME-1530 | HM-ME-1530: FF | 2024-08-02 | 2024-10-10 18:00
HM-ME-1530 | In Progress | P2543-R01-Oct24..PR.26.1.15.2 | Manufacturing & Assembly of Field Instruments | HM-ME-1520 | HM-ME-1520: FF | HM-ME-1540, HM-ME-1580 | HM-ME-1540: FS, HM-ME-1580: FS | 2024-09-20 17:30 | 2024-12-30 18:00
HM-ME-1540 | Not Started | P2543-R01-Oct24..PR.26.1.15.2 | Testing and Inspection of Field Instruments | HM-ME-1530 | HM-ME-1530: FS | HM-ME-1550 | HM-ME-1550: FS | 2024-12-31 08:00 | 2025-01-02 15:00
HM-ME-1550 | Not Started | P2543-R01-Oct24..PR.26.1.15.2 | Packaging & Final Inspection-Field Instruments | HM-ME-1540 | HM-ME-1540: FS | HM-ME-1560 | HM-ME-1560: FS | 2025-01-02 15:00 | 2025-01-06 15:00
HM-ME-1560 | Not Started | P2543-R01-Oct24..PR.26.1.15.2 | Ready for Dispatch of Field Instruments | HM-ME-1550 | HM-ME-1550: FS | HM-ME-2320 | HM-ME-2320: FS 21 | 2025-01-06 15:00 | 2025-01-10 15:00
HM-ME-1580 | Not Started | P2543-R01-Oct24..PR.26.1.15.3 | Transportation/ Custom Clearance/ Delivery at site of Field Instruments (Lot 1) | HM-ME-1530 | HM-ME-1530: FS | HM-ME-1590 | HM-ME-1590: FS | 2024-12-31 08:00 | 2025-01-20 18:00
HM-ME-1590 | Not Started | P2543-R01-Oct24..PR.26.1.15.3 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | ML1002, HM-ME-1580 | ML1002: FS, HM-ME-1580: FS | ML1030, ML1859-E31, ML1749-E20, ML2089-D16, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1000, C-56-PR-838-EI-1400, C-56-591-01-EI-1600, C-52-598-06-EI-1210, C-52-598-06-EI-1400, C-52-598-05-EI-1210, C-52-598-05-EI-1400, C-52- | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML2089-D16: FF, C-56-PL-607-EI-1400: FF, C-56-PL-607-EI-2200: FF, C-56-PL-607-EI-1800: FF, C-56-EB2-EI-1000: FF, C-56-PR-838-EI-1400: FF, C-56-591-01-EI-1600: FF, C-52-598-06-EI-1210: FF, C-52-598-06-EI-1400: FF, | 2025-01-21 08:00 | 2025-01-27 18:00
HM-ME-0940 | Not Started | P2543-R01-Oct24..PR.26.1.1.2 | Factory Acceptance Test of Distribution Transformer | HM-ME-0930 | HM-ME-0930: FS | HM-ME-0950 | HM-ME-0950: FS | 2025-03-28 08:00 | 2025-03-31 18:00
HM-ME-0950 | Not Started | P2543-R01-Oct24..PR.26.1.1.2 | Packaging & Final Inspection-Distribution Transformer | HM-ME-0940 | HM-ME-0940: FS | HM-ME-0960 | HM-ME-0960: FS | 2025-04-01 08:00 | 2025-04-07 18:00
HM-ME-0960 | Not Started | P2543-R01-Oct24..PR.26.1.1.2 | Ready for Dispatch of Distribution Transformer | HM-ME-0950, HP-ME-0480 | HM-ME-0950: FS, HP-ME-0480: FS | HM-ME-0980 | HM-ME-0980: FS | 2025-04-08 08:00 | 2025-04-11 18:00
HM-ME-0920 | Completed | P2543-R01-Oct24..PR.26.1.1.2 | Vendor Document Review of Distribution Transformer | HP-ME-0480 | HP-ME-0480: FS | HM-ME-0930 | HM-ME-0930: FS | 2024-07-27 08:00 | 2024-10-04 18:00
HM-ME-0930 | In Progress | P2543-R01-Oct24..PR.26.1.1.2 | Manufacturing & Assembly of Distribution Transformer | HM-ME-0920, HE-EL-1070 | HM-ME-0920: FS, HE-EL-1070: FF | HM-ME-0940 | HM-ME-0940: FS | 2024-10-05 08:00 | 2025-03-27 18:00
HM-ME-0990 | Not Started | P2543-R01-Oct24..PR.26.1.1.3 | Receipt at site and inspection of Distribution Transformer | HM-ME-0980 | HM-ME-0980: FS | C-52-OHPL-EL-1400, C-52-OHPL-EL-2000 | C-52-OHPL-EL-1400: FS, C-52-OHPL-EL-2000: FS | 2025-05-02 08:00 | 2025-05-08 18:00
HM-ME-0980 | Not Started | P2543-R01-Oct24..PR.26.1.1.3 | Transportation/ Custom Clearance/ Delivery at site of Distribution Transformer | HM-ME-0960 | HM-ME-0960: FS | HM-ME-0990 | HM-ME-0990: FS | 2025-04-12 08:00 | 2025-05-01 18:00
HM-ME-1620 | Not Started | P2543-R01-Oct24..PR.26.1.16.2 | Vendor Document Review of Junction Boxes | HP-ME-0830 | HP-ME-0830: FS | HM-ME-1630 | HM-ME-1630: FS | 2024-10-26 08:00 | 2024-11-14 18:00
HM-ME-1630 | Not Started | P2543-R01-Oct24..PR.26.1.16.2 | Manufacturing & Assembly of Junction Boxes | HM-ME-1620 | HM-ME-1620: FS | HM-ME-1640, HM-ME-1680 | HM-ME-1640: FS, HM-ME-1680: FS | 2024-11-15 08:00 | 2025-03-01 18:00
HM-ME-1640 | Not Started | P2543-R01-Oct24..PR.26.1.16.2 | Testing and Inspection of Junction Boxes | HM-ME-1630 | HM-ME-1630: FS | HM-ME-1650 | HM-ME-1650: FS | 2025-03-02 08:00 | 2025-03-19 18:00
HM-ME-1650 | Not Started | P2543-R01-Oct24..PR.26.1.16.2 | Packaging & Final Inspection-Junction Boxes | HM-ME-1640 | HM-ME-1640: FS | HM-ME-1660 | HM-ME-1660: FS | 2025-03-20 08:00 | 2025-04-09 18:00
HM-ME-1660 | Not Started | P2543-R01-Oct24..PR.26.1.16.2 | Ready for Dispatch of Junction Boxes | HM-ME-1650 | HM-ME-1650: FS | HM-ME-2340 | HM-ME-2340: FS | 2025-04-10 08:00 | 2025-04-23 18:00
HM-ME-1680 | Not Started | P2543-R01-Oct24..PR.26.1.16.3 | Transportation/ Custom Clearance/ Delivery at site of Junction Boxes (Lot 1) | HM-ME-1630 | HM-ME-1630: FS | HM-ME-1690 | HM-ME-1690: FS | 2025-03-02 08:00 | 2025-03-22 18:00
HM-ME-1690 | Not Started | P2543-R01-Oct24..PR.26.1.16.3 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | ML1002, HM-ME-1680 | ML1002: FS, HM-ME-1680: FS | ML1030, ML1859-E31, ML1749-E20, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-591-01-EI-1600, C-52-598-06-EI-1210, C-52-598-06-EI-1400, C-52-598-05-EI-1210, C-52-598-05-EI | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, C-56-PL-607-EI-1400: FF, C-56-PL-607-EI-2200: FF, C-56-PL-607-EI-1800: FF, C-56-PR-838-EI-1010: FF, C-56-PR-838-EI-1400: FF, C-56-PR-838-EI-1810: FF, C-56-591-01-EI-1600: FF, C-52-598-06-EI-1210: FF, C-52-598-06- | 2025-03-23 08:00 | 2025-04-05 18:00
HM-ME-0210 | Completed | P2543-R01-Oct24..PR.26.LL.17.2 | Vendor Document Review of Leak Detection System | HP-ME-0130, ML1289-C11 | HP-ME-0130: FS, ML1289-C11: FF | HM-ME-0220 | HM-ME-0220: FS | 2024-05-17 | 2024-08-03 18:00
HM-ME-0220 | In Progress | P2543-R01-Oct24..PR.26.LL.17.2 | Manufacturing & Assembly of Leak Detection System | HM-ME-0210, HE-IC-1790 | HM-ME-0210: FS, HE-IC-1790: FS | HM-ME-0230 | HM-ME-0230: FS | 2024-07-26 08:00 | 2025-02-02 18:00
HM-ME-0250 | Not Started | P2543-R01-Oct24..PR.26.LL.17.2 | Ready for Dispatch of Leak Detection System | HM-ME-0240 | HM-ME-0240: FS | HM-ME-0270 | HM-ME-0270: FS | 2025-02-24 08:00 | 2025-02-27 18:00
HM-ME-0230 | Not Started | P2543-R01-Oct24..PR.26.LL.17.2 | Factory Acceptance Test of Leak Detection System | HM-ME-0220 | HM-ME-0220: FS | HM-ME-0240 | HM-ME-0240: FS | 2025-02-03 08:00 | 2025-02-16 18:00
HM-ME-0240 | Not Started | P2543-R01-Oct24..PR.26.LL.17.2 | Packaging & Final Inspection - Leak Detection System | HM-ME-0230 | HM-ME-0230: FS | HM-ME-0250 | HM-ME-0250: FS | 2025-02-17 08:00 | 2025-02-23 18:00
HM-ME-0280 | Not Started | P2543-R01-Oct24..PR.26.LL.17.3 | Receipt at site and inspection of Leak Detection System | HM-ME-0270 | HM-ME-0270: FS | CAB-5310, ML1053-D23, C-52-PR-839-TE-1410, C-52-598-03-TE-1200 | CAB-5310: FS, ML1053-D23: FF, C-52-PR-839-TE-1410: FS, C-52-598-03-TE-1200: FS | 2025-03-14 09:00 | 2025-03-27 13:00
HM-ME-0270 | Not Started | P2543-R01-Oct24..PR.26.LL.17.3 | Transportation/ Custom Clearance/ Delivery at site of Leak Detection System | HM-ME-0250 | HM-ME-0250: FS | HM-ME-0280 | HM-ME-0280: FS | 2025-02-28 08:00 | 2025-03-13 18:00
HM-ME-1420 | Completed | P2543-R01-Oct24..PR.26.LL.18.2 | Vendor Document Review of Gas Detectors | ML1028-C20, HP-ME-0730, ML1269-C12 | ML1028-C20: FS, HP-ME-0730: FS, ML1269-C12: FS | HM-ME-1430 | HM-ME-1430: FS | 2024-06-24 08:00 | 2024-08-22 18:00
HM-ME-1430 | In Progress | P2543-R01-Oct24..PR.26.LL.18.2 | Manufacturing & Assembly of Gas Detectors | HM-ME-1420 | HM-ME-1420: FS | HM-ME-1440, HM-ME-1480 | HM-ME-1440: FS, HM-ME-1480: FS | 2024-08-23 | 2025-01-29 18:00
HM-ME-1440 | Not Started | P2543-R01-Oct24..PR.26.LL.18.2 | Testing and Inspection of Gas Detectors | HM-ME-1430 | HM-ME-1430: FS | HM-ME-1450 | HM-ME-1450: FS | 2025-01-30 08:00 | 2025-02-01 15:00
HM-ME-1450 | Not Started | P2543-R01-Oct24..PR.26.LL.18.2 | Packaging & Final Inspection-Gas Detectors | HM-ME-1440 | HM-ME-1440: FS | HM-ME-1460 | HM-ME-1460: FS | 2025-02-01 15:00 | 2025-02-05 15:00
HM-ME-1460 | Not Started | P2543-R01-Oct24..PR.26.LL.18.2 | Ready for Dispatch of Gas Detectors | HM-ME-1450 | HM-ME-1450: FS | HM-ME-2300 | HM-ME-2300: FS 20 | 2025-02-05 15:00 | 2025-02-09 15:00
HM-ME-1490 | Not Started | P2543-R01-Oct24..PR.26.LL.18.3 | Receipt at site and inspection of Gas Detectors (Lot 1) | HM-ME-1480 | HM-ME-1480: FS | ML1030, ML1859-E31, ML1749-E20, ML2089-D16, PRECOM-52-PR-1000, C-56-PL-607-EI-2410, C-52-598-01-EI-2410, C-52-598-02-EI-2410, C-52-598-03-EI-2410, C-52-598-04-EI-2410, C-52-598-05-EI-2410, C-52-598-06-EI-2410, C-56-591-01-EI-2410, C-52-PL-838-EI-2410, C-52 | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML2089-D16: FF, PRECOM-52-PR-1000: FS, C-56-PL-607-EI-2410: FS, C-52-598-01-EI-2410: FS, C-52-598-02-EI-2410: FS, C-52-598-03-EI-2410: FS, C-52-598-04-EI-2410: FS, C-52-598-05-EI-2410: FS, C-52-598-06-EI-2410: FS | 2025-02-20 08:00 | 2025-02-27 18:00
HM-ME-1480 | Not Started | P2543-R01-Oct24..PR.26.LL.18.3 | Transportation/ Custom Clearance/ Delivery at site of Gas Detectors (Lot 1) | HM-ME-1430 | HM-ME-1430: FS | HM-ME-1490 | HM-ME-1490: FS | 2025-01-30 08:00 | 2025-02-19 18:00
HM-ME-0010 | Completed | P2543-R01-Oct24..PR.26.LL.22.2 | Vendor Document Review of Custody Metering Skid | ML1259-C09, HP-ME-0030 | ML1259-C09: FS, HP-ME-0030: FS | HM-ME-0020 | HM-ME-0020: FS | 2024-03-13 | 2024-07-27 18:00
HM-ME-0020 | In Progress | P2543-R01-Oct24..PR.26.LL.22.2 | Manufacturing & Assembly of Custody Metering Skid | HM-ME-0010 | HM-ME-0010: FS | HM-ME-0030 | HM-ME-0030: FS | 2024-06-10 08:00 | 2025-03-30 18:00
HM-ME-0030 | Not Started | P2543-R01-Oct24..PR.26.LL.22.2 | Factory Acceptance Test of Custody Metering Skid | HM-ME-0020 | HM-ME-0020: FS | HM-ME-0040 | HM-ME-0040: FS | 2025-03-31 08:00 | 2025-04-13 18:00
HM-ME-0040 | Not Started | P2543-R01-Oct24..PR.26.LL.22.2 | Packaging & Final Inspection-Custody Metering Skid | HM-ME-0030 | HM-ME-0030: FS | HM-ME-0050 | HM-ME-0050: FS | 2025-04-14 08:00 | 2025-04-20 18:00
HM-ME-0050 | Not Started | P2543-R01-Oct24..PR.26.LL.22.2 | Ready for Dispatch of Custody Metering Skid | HM-ME-0040, HP-ME-0030 | HM-ME-0040: FS, HP-ME-0030: FS | HM-ME-0070 | HM-ME-0070: FS | 2025-04-21 08:00 | 2025-04-24 18:00
HM-ME-0080 | Not Started | P2543-R01-Oct24..PR.26.LL.22.3 | Receipt at site and inspection of Custody Metering Skid | HM-ME-0070, HM-ME-0070 | HM-ME-0070: FF, HM-ME-0070: FS | CAB-5310, ML1419-D08, C-52-PR-839-ME-2000, C-52-PR-839-ME-2010 | CAB-5310: FS, ML1419-D08: FS, C-52-PR-839-ME-2000: FS, C-52-PR-839-ME-2010: FS | 2025-05-02 07:00 | 2025-05-11 15:00
HM-ME-0070 | Not Started | P2543-R01-Oct24..PR.26.LL.22.3 | Transportation/ Custom Clearance/ Delivery at site of Custody Metering Skid | HM-ME-0050 | HM-ME-0050: FS | HM-ME-0080, HM-ME-0080 | HM-ME-0080: FF, HM-ME-0080: FS | 2025-04-25 08:00 | 2025-05-01 18:00
HM-ME-0180 | Not Started | P2543-R01-Oct24..PR.26.LL.21.3 | Receipt at site and inspection of Pressure Reduction Skid | HM-ME-0170 | HM-ME-0170: FS | ML1051-D07, CAB-5310, C-52-PR-839-ME-2000, C-52-PR-839-ME-2010 | ML1051-D07: FS, CAB-5310: FS, C-52-PR-839-ME-2000: FS, C-52-PR-839-ME-2010: FS | 2025-05-21 07:00 | 2025-05-28 17:00
HM-ME-0170 | Not Started | P2543-R01-Oct24..PR.26.LL.21.3 | Transportation/ Custom Clearance/ Delivery at site of Pressure Reduction Skid | HM-ME-0150 | HM-ME-0150: FS | HM-ME-0180 | HM-ME-0180: FS | 2025-05-14 08:00 | 2025-05-20 18:00
HM-ME-0110 | Completed | P2543-R01-Oct24..PR.26.LL.21.2 | Vendor Document Review of Pressure Reduction Skid | ML1039-C08, HP-ME-0080 | ML1039-C08: FS, HP-ME-0080: FS | HM-ME-0120 | HM-ME-0120: SS | 2024-04-17 | 2024-06-28 18:00
HM-ME-0120 | In Progress | P2543-R01-Oct24..PR.26.LL.21.2 | Manufacturing & Assembly of Pressure Reduction Skid | HM-ME-0110, HE-PR-0590, ML1017-B18, HE-PR-1300, HE-PR-1350, HE-PR-1400, HE-PR-1450, HE-PR-1500, HE-PR-1550, HE-PR-1600 | HM-ME-0110: SS, HE-PR-0590: FS, ML1017-B18: FS, HE-PR-1300: FS, HE-PR-1350: FS, HE-PR-1400: FS, HE-PR-1450: FS, HE-PR-1500: FS, HE-PR-1550: FS, HE-PR-1600: FS | HM-ME-0130 | HM-ME-0130: FS | 2024-06-11 | 2025-04-18 18:00
HM-ME-0150 | Not Started | P2543-R01-Oct24..PR.26.LL.21.2 | Ready for Dispatch of Pressure Reduction Skid | HP-ME-0080, HM-ME-0140 | HP-ME-0080: FS, HM-ME-0140: FS | HM-ME-0170 | HM-ME-0170: FS | 2025-05-10 08:00 | 2025-05-13 18:00
HM-ME-0130 | Not Started | P2543-R01-Oct24..PR.26.LL.21.2 | Factory Acceptance Test of Pressure Reduction Skid | HM-ME-0120 | HM-ME-0120: FS | HM-ME-0140 | HM-ME-0140: FS | 2025-04-19 08:00 | 2025-05-02 18:00
HM-ME-0140 | Not Started | P2543-R01-Oct24..PR.26.LL.21.2 | Packaging & Final Inspection - Pressure Reduction Skid | HM-ME-0130 | HM-ME-0130: FS | HM-ME-0150 | HM-ME-0150: FS | 2025-05-03 08:00 | 2025-05-09 18:00
HM-ME-1850 | In Progress | P2543-R01-Oct24..PR.26.1.2.2 | Vendor Document Review of Fire Suppression System | HE-HS-1190, HP-ME-0930 | HE-HS-1190: FS, HP-ME-0930: FS | HM-ME-1860 | HM-ME-1860: FS | 2024-09-23 17:30 | 2024-11-08 18:00
HM-ME-1860 | Not Started | P2543-R01-Oct24..PR.26.1.2.2 | Manufacturing & Assembly of Fire Suppression System | HM-ME-1850 | HM-ME-1850: FS | HM-ME-1870 | HM-ME-1870: FS | 2024-11-09 08:00 | 2025-01-31 18:00
HM-ME-1870 | Not Started | P2543-R01-Oct24..PR.26.1.2.2 | Factory Acceptance Test of Fire Suppression System | HM-ME-1860 | HM-ME-1860: FS | HM-ME-1880 | HM-ME-1880: FS | 2025-02-01 08:00 | 2025-02-11 18:00
HM-ME-1880 | Not Started | P2543-R01-Oct24..PR.26.1.2.2 | Packaging & Final Inspection-Fire Suppression System | HM-ME-1870 | HM-ME-1870: FS | HM-ME-1890 | HM-ME-1890: FS | 2025-02-12 08:00 | 2025-02-18 18:00
HM-ME-1890 | Not Started | P2543-R01-Oct24..PR.26.1.2.2 | Ready for Dispatch of Fire Suppression System | HP-ME-0930, HM-ME-1880 | HP-ME-0930: FS, HM-ME-1880: FS | HM-ME-1820 | HM-ME-1820: FS | 2025-02-19 08:00 | 2025-02-22 18:00
HM-ME-1830 | Not Started | P2543-R01-Oct24..PR.26.1.2.3 | Receipt at site and inspection of Fire Suppression System | HM-ME-1820, HM-ME-1820 | HM-ME-1820: FS, HM-ME-1820: FF | C-52-EB1-ME-1000, C-52-EB1-ME-1200 | C-52-EB1-ME-1000: FS, C-52-EB1-ME-1200: FS | 2025-03-23 08:00 | 2025-03-29 18:00
HM-ME-1820 | Not Started | P2543-R01-Oct24..PR.26.1.2.3 | Transportation/ Custom Clearance/ Delivery at site of Fire Suppression System | HM-ME-1890 | HM-ME-1890: FS | HM-ME-1830, HM-ME-1830 | HM-ME-1830: FS, HM-ME-1830: FF | 2025-02-23 08:00 | 2025-03-22 18:00
HM-ME-1790 | Not Started | P2543-R01-Oct24..PR.26.1.3.3 | Receipt at site and inspection of HVAC Equipment | HM-ME-1780, HM-ME-1780 | HM-ME-1780: FF, HM-ME-1780: FS | C-56-EB2-ME-1000, C-56-EB2-ME-1010, C-56-EB2-ME-1000, C-56-EB2-ME-1010, C-52-EB1-ME-1000 | C-56-EB2-ME-1000: FF, C-56-EB2-ME-1010: FS, C-56-EB2-ME-1000: FS, C-56-EB2-ME-1010: FF, C-52-EB1-ME-1000: FS | 2025-03-16 09:00 | 2025-03-28 13:00
HM-ME-1780 | Not Started | P2543-R01-Oct24..PR.26.1.3.3 | Transportation/ Custom Clearance/ Delivery at site of HVAC Equipment | HM-ME-1760 | HM-ME-1760: FS | HM-ME-1790, HM-ME-1790 | HM-ME-1790: FF, HM-ME-1790: FS | 2025-02-08 08:00 | 2025-03-14 18:00
HM-ME-1740 | Not Started | P2543-R01-Oct24..PR.26.1.3.2 | Factory Acceptance Test of HVAC Equipment | HM-ME-1730 | HM-ME-1730: FS | HM-ME-1750 | HM-ME-1750: FS | 2025-01-14 08:00 | 2025-01-27 18:00
HM-ME-1750 | Not Started | P2543-R01-Oct24..PR.26.1.3.2 | Packaging & Final Inspection-HVAC Equipment | HM-ME-1740 | HM-ME-1740: FS | HM-ME-1760 | HM-ME-1760: FS | 2025-01-28 08:00 | 2025-02-03 18:00
HM-ME-1760 | Not Started | P2543-R01-Oct24..PR.26.1.3.2 | Ready for Dispatch of HVAC Equipment | HM-ME-1750, HP-ME-0880 | HM-ME-1750: FS, HP-ME-0880: FS | HM-ME-1780 | HM-ME-1780: FS | 2025-02-04 08:00 | 2025-02-07 18:00
HM-ME-1720 | Completed | P2543-R01-Oct24..PR.26.1.3.2 | Vendor Document Review of HVAC Equipment | HP-ME-0880 | HP-ME-0880: FS | HM-ME-1730 | HM-ME-1730: FS | 2024-07-27 08:00 | 2024-08-16 18:00
HM-ME-1730 | In Progress | P2543-R01-Oct24..PR.26.1.3.2 | Manufacturing & Assembly of HVAC Equipment | HM-ME-1720 | HM-ME-1720: FS | HM-ME-1740 | HM-ME-1740: FS | 2024-08-17 08:00 | 2025-01-13 18:00
HM-ME-0450 | Not Started | P2543-R01-Oct24..PR.26.LL.12.2 | Ready for Dispatch of Pig Launchers & Receivers | HM-ME-0440, HP-ME-0230 | HM-ME-0440: FS, HP-ME-0230: FS | HM-ME-0470, HM-ME-2380 | HM-ME-0470: FS, HM-ME-2380: FS 21 | 2025-01-04 08:00 | 2025-01-07 18:00
HM-ME-0410 | Completed | P2543-R01-Oct24..PR.26.LL.12.2 | Vendor Document Review of Pig Launchers & Receivers | HP-ME-0230, ML1279-C05 | HP-ME-0230: FS, ML1279-C05: FF | HE-PI-1140, HE-CS-0630, HE-PI-0620, HM-ME-0420, HE-PI-0740, HE-PI-0680, HE-PI-0170, HE-CO-170, HE-CS-0610 | HE-PI-1140: SS 15, HE-CS-0630: SS 20, HE-PI-0620: FS, HM-ME-0420: FS, HE-PI-0740: SS 8, HE-PI-0680: FS, HE-PI-0170: FS, HE-CO-170: FS, HE-CS-0610: FS | 2024-02-24 | 2024-03-24
HM-ME-0420 | In Progress | P2543-R01-Oct24..PR.26.LL.12.2 | Manufacturing & Assembly of Pig Launchers & Receivers | HM-ME-0410, HE-PR-0590, HE-PR-1300, HE-PR-1350, HE-PR-1400, HE-PR-1450, HE-PR-1500, HE-PR-1550, HE-PR-1600, HE-PL-0110, HE-PR-0530, HE-PR-0490 | HM-ME-0410: FS, HE-PR-0590: FS, HE-PR-1300: FS, HE-PR-1350: FS, HE-PR-1400: FS, HE-PR-1450: FS, HE-PR-1500: FS, HE-PR-1550: FS, HE-PR-1600: FS, HE-PL-0110: FS, HE-PR-0530: FS, HE-PR-0490: FS | HM-ME-0430 | HM-ME-0430: FS | 2024-05-22 | 2024-12-20 18:00
HM-ME-0430 | Not Started | P2543-R01-Oct24..PR.26.LL.12.2 | Testing and Inspection of Pig Launchers & Receivers | HM-ME-0420 | HM-ME-0420: FS | HM-ME-0440 | HM-ME-0440: FS | 2024-12-21 08:00 | 2024-12-27 18:00
HM-ME-0440 | Not Started | P2543-R01-Oct24..PR.26.LL.12.2 | Packaging & Final Inspection-Pig Launchers & Receivers | HM-ME-0430 | HM-ME-0430: FS | HM-ME-0450 | HM-ME-0450: FS | 2024-12-28 08:00 | 2025-01-03 18:00
HM-ME-0480 | Not Started | P2543-R01-Oct24..PR.26.LL.12.3 | Receipt at site and inspection of Pig Launchers & Receivers (52" Line) | HM-ME-0470 | HM-ME-0470: FS | CAB-5310, ML1519-D04, C-52-PR-839-ME-1100, C-52-PL-838-ME-1000 | CAB-5310: FS, ML1519-D04: FF, C-52-PR-839-ME-1100: FS, C-52-PL-838-ME-1000: FS | 2025-02-12 07:00 | 2025-02-19 17:00
HM-ME-0470 | Not Started | P2543-R01-Oct24..PR.26.LL.12.3 | Transportation/ Custom Clearance/ Delivery at site of Pig Launchers & Receivers (52" Line) | HM-ME-0450 | HM-ME-0450: FS | HM-ME-0480 | HM-ME-0480: FS | 2025-01-08 08:00 | 2025-02-11 18:00
HM-ME-0510 | In Progress | P2543-R01-Oct24..PR.26.LL.10.2 | Vendor Document Review of ROV/ GOV | HE-IC-2330, HP-ME-0280, ML1349-C19, ML1022-C07 | HE-IC-2330: SS, HP-ME-0280: FS, ML1349-C19: FF, ML1022-C07: FF | HM-ME-0520 | HM-ME-0520: SS | 2024-05-09 | 2024-11-09 18:00
HM-ME-0520 | In Progress | P2543-R01-Oct24..PR.26.LL.10.2 | Manufacturing & Assembly of ROV/ GOV | HM-ME-0510 | HM-ME-0510: SS | HM-ME-0530, HM-ME-0570 | HM-ME-0530: FS 12, HM-ME-0570: FS | 2024-05-28 08:00 | 2025-04-12 18:00
HM-ME-0530 | Not Started | P2543-R01-Oct24..PR.26.LL.10.2 | Testing and Inspection of ROV/ GOV | HM-ME-0520 | HM-ME-0520: FS 12 | HM-ME-0540 | HM-ME-0540: FS | 2025-04-25 08:00 | 2025-05-01 18:00
HM-ME-0540 | Not Started | P2543-R01-Oct24..PR.26.LL.10.2 | Packaging & Final Inspection-ROV/ GOV | HM-ME-0530 | HM-ME-0530: FS | HM-ME-0550 | HM-ME-0550: FS | 2025-05-02 08:00 | 2025-05-08 18:00
HM-ME-0550 | Not Started | P2543-R01-Oct24..PR.26.LL.10.2 | Ready for Dispatch of ROV/ GOV | HM-ME-0540, HP-ME-0280 | HM-ME-0540: FS, HP-ME-0280: FS | HM-ME-2220 | HM-ME-2220: FS 15 | 2025-05-09 08:00 | 2025-05-12 18:00
HM-ME-0580 | Not Started | P2543-R01-Oct24..PR.26.LL.10.3 | Receipt at site and inspection of ROV/ GOV (1st Lot) | HM-ME-0570 | HM-ME-0570: FS | CAB-5310, ML1024-D06, ML1469-D13, C-52-598-01-PI-1800, C-52-598-01-PL-1060, C-52-598-02-PI-1800, C-52-598-02-PL-1060, C-52-598-03-PI-1800, C-52-598-03-PL-1060, C-52-598-04-PI-1800, C-52-598-04-PL-1060, C-52-598-05-PI-1800, C-52-598-05-PL-1060, C-52-598-06- | CAB-5310: FS, ML1024-D06: FS, ML1469-D13: FS, C-52-598-01-PI-1800: FS, C-52-598-01-PL-1060: FS, C-52-598-02-PI-1800: FS, C-52-598-02-PL-1060: FS, C-52-598-03-PI-1800: FS, C-52-598-03-PL-1060: FS, C-52-598-04-PI-1800: FS, C-52-598-04-PL-1060: FS, C-52-598-0 | 2025-05-18 08:00 | 2025-05-24 18:00
HM-ME-0570 | Not Started | P2543-R01-Oct24..PR.26.LL.10.3 | Transportation/ Custom Clearance/ Delivery at site of ROV/ GOV (1st Lot) | HM-ME-0520 | HM-ME-0520: FS | HM-ME-0580, HM-ME-2220 | HM-ME-0580: FS, HM-ME-2220: FS | 2025-04-13 08:00 | 2025-05-17 18:00
HM-ME-0610 | In Progress | P2543-R01-Oct24..PR.26.LL.9.2 | Vendor Document Review of MOV | ML1022-C07, HP-ME-0330 | ML1022-C07: FF, HP-ME-0330: FS | HM-ME-0620 | HM-ME-0620: FF | 2024-06-08 | 2024-11-01 18:00
HM-ME-0620 | In Progress | P2543-R01-Oct24..PR.26.LL.9.2 | Manufacturing & Assembly of MOV | HE-IC-1610, HE-IC-2090, HM-ME-0610 | HE-IC-1610: FS, HE-IC-2090: FS, HM-ME-0610: FF | HM-ME-0630, HM-ME-2230 | HM-ME-0630: FS, HM-ME-2230: FS | 2024-07-05 08:00 | 2025-05-08 18:00
HM-ME-0630 | Not Started | P2543-R01-Oct24..PR.26.LL.9.2 | Testing and Inspection of MOV | HM-ME-0620 | HM-ME-0620: FS | HM-ME-0640 | HM-ME-0640: FS | 2025-05-09 08:00 | 2025-05-15 18:00
HM-ME-0640 | Not Started | P2543-R01-Oct24..PR.26.LL.9.2 | Packaging & Final Inspection-MOV | HM-ME-0630 | HM-ME-0630: FS | HM-ME-0650 | HM-ME-0650: FS | 2025-05-16 08:00 | 2025-05-22 18:00
HM-ME-0650 | Not Started | P2543-R01-Oct24..PR.26.LL.9.2 | Ready for Dispatch of MOV | HP-ME-0330, HM-ME-0640 | HP-ME-0330: FS, HM-ME-0640: FS | HM-ME-0670 | HM-ME-0670: FS | 2025-05-23 08:00 | 2025-05-26 18:00
HM-ME-0680 | Not Started | P2543-R01-Oct24..PR.26.LL.9.3 | Receipt at site and inspection of MOV (Lot 1) | HM-ME-2230 | HM-ME-2230: FS | ML1469-D13, ML1024-D06, CAB-5310, C-52-PR-839-PI-1800, C-52-PL-838-PI-1800, C-56-PR-838-PI-1800, C-56-PL-607-PI-1800 | ML1469-D13: FS, ML1024-D06: FS, CAB-5310: FS, C-52-PR-839-PI-1800: FS, C-52-PL-838-PI-1800: FS, C-56-PR-838-PI-1800: FS, C-56-PL-607-PI-1800: FS | 2025-05-30 07:00 | 2025-06-23 17:00
HM-ME-0670 | Not Started | P2543-R01-Oct24..PR.26.LL.9.3 | Transportation/ Custom Clearance/ Delivery at site of MOV (Lot 2) | HM-ME-0650 | HM-ME-0650: FS | HM-ME-2240 | HM-ME-2240: FS | 2025-05-27 08:00 | 2025-06-30 18:00
HM-ME-0690 | Not Started | P2543-R01-Oct24..PR.26.LL.9.3 | Receipt at site and inspection of Isolator (Lot 1) | HM-ME-2230 | HM-ME-2230: FS 8 | HM-ME-2250, ML1030, ML1859-E31, ML1749-E20, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-52-PR-839-EI-1400, C-52-PR-839-EI-1800, C-52-PR-839-CA-1000, C-52-PR-839-TE-1410, PRECOM-52-PR-1000, C-56-PL-607-EI-2410 | HM-ME-2250: FS, ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, C-56-PL-607-EI-1400: FF 26, C-56-PL-607-EI-2200: FF, C-56-PL-607-EI-1800: FF 26, C-52-PR-839-EI-1400: FF, C-52-PR-839-EI-1800: FF, C-52-PR-839-CA-1000: FF, C-52-PR-839-TE-1410: FS, PRECOM-52-PR-10 | 2025-06-09 07:00 | 2025-06-16 17:00
HM-ME-0730 | Completed | P2543-R01-Oct24..PR.26.LL.8.2 | Manufacturing & Assembly of AC UPS | HM-ME-0720, HE-EL-0950 | HM-ME-0720: FS, HE-EL-0950: FS | HM-ME-0740 | HM-ME-0740: FS | 2024-06-21 08:00 | 2024-10-11 18:00
HM-ME-0740 | In Progress | P2543-R01-Oct24..PR.26.LL.8.2 | Factory Acceptance Test of AC UPS | HM-ME-0730 | HM-ME-0730: FS | HM-ME-0750 | HM-ME-0750: FS | 2024-10-12 08:00 | 2024-11-06 18:00
HM-ME-0750 | Not Started | P2543-R01-Oct24..PR.26.LL.8.2 | Packaging & Final Inspection-AC UPS | HM-ME-0740 | HM-ME-0740: FS | HM-ME-0760 | HM-ME-0760: FS | 2024-11-07 08:00 | 2024-11-13 18:00
HM-ME-0760 | Not Started | P2543-R01-Oct24..PR.26.LL.8.2 | Ready for Dispatch of AC UPS | HP-ME-0380, HM-ME-0750 | HP-ME-0380: FS, HM-ME-0750: FS | HM-ME-0780 | HM-ME-0780: FS | 2024-11-14 08:00 | 2024-11-17 18:00
HM-ME-0720 | Completed | P2543-R01-Oct24..PR.26.LL.8.2 | Vendor Document Review of AC UPS | HP-ME-0380, ML1319-C16 | HP-ME-0380: FS, ML1319-C16: FS | HM-ME-0730 | HM-ME-0730: FS | 2024-05-13 | 2024-05-30 18:00
HM-ME-0780 | Not Started | P2543-R01-Oct24..PR.26.LL.8.3 | Transportation/ Custom Clearance/ Delivery at site of AC UPS | HM-ME-0760 | HM-ME-0760: FS | HM-ME-0790 | HM-ME-0790: FS | 2024-11-18 08:00 | 2024-12-22 18:00
HM-ME-0790 | Not Started | P2543-R01-Oct24..PR.26.LL.8.3 | Receipt at site and inspection of AC UPS | HM-ME-0780 | HM-ME-0780: FS | ML1030, ML1859-E31, ML1749-E20, ML1499-D18, CAB-5310, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-52-PR-839-EI-1400, C-52-PR-839-EI-1800, C-52-PR-839-CA-1000, C-52-PR-839-TE-1410, C-541CR-EI-1020, C-56-PL-607-EI-2410 | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1499-D18: FF, CAB-5310: FS, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-52-PR-839-EI-1400: FS, C-52-PR-839-EI-1800: FS, C-52-PR-839-CA-1000: FF, C-52-PR-839-TE-1410: FS, C-541CR-EI-1020: FS, C-56-PL-607 | 2024-12-23 08:00 | 2024-12-30 18:00
HM-ME-0840 | Not Started | P2543-R01-Oct24..PR.26.1.7.2 | Factory Acceptance Test of Power Distribution Boards | HM-ME-0830 | HM-ME-0830: FS | HM-ME-0850 | HM-ME-0850: FS | 2025-03-15 08:00 | 2025-03-18 18:00
HM-ME-0850 | Not Started | P2543-R01-Oct24..PR.26.1.7.2 | Packaging & Final Inspection for Power Distribution Boards | HM-ME-0840 | HM-ME-0840: FS | HM-ME-0860 | HM-ME-0860: FS | 2025-03-19 08:00 | 2025-03-25 18:00
HM-ME-0860 | Not Started | P2543-R01-Oct24..PR.26.1.7.2 | Ready for Dispatch of Power Distribution Boards | HM-ME-0850, HP-ME-0430 | HM-ME-0850: FS, HP-ME-0430: FS | HM-ME-0880 | HM-ME-0880: FS | 2025-03-26 08:00 | 2025-03-29 18:00
HM-ME-0820 | Completed | P2543-R01-Oct24..PR.26.1.7.2 | Vendor Document Review of Power Distribution Boards | HP-ME-0430 | HP-ME-0430: FS | HM-ME-0830 | HM-ME-0830: FS | 2024-08-24 17:30 | 2024-10-02 18:00
HM-ME-0830 | In Progress | P2543-R01-Oct24..PR.26.1.7.2 | Manufacturing & Assembly of Power Distribution Boards | HM-ME-0820 | HM-ME-0820: FS | HM-ME-0840 | HM-ME-0840: FS | 2024-10-05 08:00 | 2025-03-14 18:00
HM-ME-0890 | Not Started | P2543-R01-Oct24..PR.26.1.7.3 | Receipt at site and inspection of Power Distribution Boards | HM-ME-0880 | HM-ME-0880: FS | CAB-5310, C-56-EB2-EI-1000, C-56-591-01-EI-1600, C-52-598-06-EI-1210, C-52-598-06-EI-1400, C-52-598-05-EI-1210, C-52-598-05-EI-1400, C-52-598-04-EI-1210, C-52-598-04-EI-1400, C-52-598-03-EI-1210, C-52-598-03-EI-1400, C-52-598-02-EI-1210, C-52-598-02-EI-140 | CAB-5310: FS, C-56-EB2-EI-1000: FS, C-56-591-01-EI-1600: FS, C-52-598-06-EI-1210: FS, C-52-598-06-EI-1400: FS, C-52-598-05-EI-1210: FS, C-52-598-05-EI-1400: FS, C-52-598-04-EI-1210: FS, C-52-598-04-EI-1400: FS, C-52-598-03-EI-1210: FS, C-52-598-03-EI-1400: | 2025-04-20 07:00 | 2025-04-27 17:00
HM-ME-0880 | Not Started | P2543-R01-Oct24..PR.26.1.7.3 | Transportation/ Custom Clearance/ Delivery at site of Power Distribution Boards | HM-ME-0860 | HM-ME-0860: FS | HM-ME-0890 | HM-ME-0890: FS | 2025-03-30 08:00 | 2025-04-19 18:00
HM-ME-1020 | In Progress | P2543-R01-Oct24..PR.26.LL.6.2 | Vendor Document Review of Solar PV system | HP-ME-0530, ML1026-C13 | HP-ME-0530: FS, ML1026-C13: FS | HM-ME-1030 | HM-ME-1030: FS | 2024-07-27 08:00 | 2024-11-09 18:00
HM-ME-1030 | Not Started | P2543-R01-Oct24..PR.26.LL.6.2 | Manufacturing & Assembly of Solar PV system | HE-EL-1130, HM-ME-1020 | HE-EL-1130: FS, HM-ME-1020: FS | HM-ME-1040 | HM-ME-1040: FS | 2024-11-10 08:00 | 2025-02-25 18:00
HM-ME-1040 | Not Started | P2543-R01-Oct24..PR.26.LL.6.2 | Factory Acceptance Test of Solar PV system | HM-ME-1030 | HM-ME-1030: FS | HM-ME-1050 | HM-ME-1050: FS | 2025-02-26 08:00 | 2025-03-11 18:00
HM-ME-1050 | Not Started | P2543-R01-Oct24..PR.26.LL.6.2 | Packaging & Final Inspection-Solar PV system | HM-ME-1040 | HM-ME-1040: FS | HM-ME-1060 | HM-ME-1060: FS | 2025-03-12 08:00 | 2025-03-18 18:00
HM-ME-1060 | Not Started | P2543-R01-Oct24..PR.26.LL.6.2 | Ready for Dispatch of Solar PV system | HM-ME-1050, HP-ME-0530 | HM-ME-1050: FS, HP-ME-0530: FS | HM-ME-1080 | HM-ME-1080: FS | 2025-03-19 08:00 | 2025-03-27 18:00
HM-ME-1090 | Not Started | P2543-R01-Oct24..PR.26.LL.6.3 | Receipt at site and inspection of Solar PV system | HM-ME-1080 | HM-ME-1080: FS | ML1429-D17, CAB-5310, C-52-598-06-EI-1210, C-52-598-05-EI-1210, C-52-598-04-EI-1210, C-52-598-03-EI-1210, C-52-598-02-EI-1210, C-52-598-01-EI-1210, C-56-591-01-EI-1210 | ML1429-D17: FS, CAB-5310: FS, C-52-598-06-EI-1210: FF 12, C-52-598-05-EI-1210: FF 12, C-52-598-04-EI-1210: FF 12, C-52-598-03-EI-1210: FS, C-52-598-02-EI-1210: FS, C-52-598-01-EI-1210: FS, C-56-591-01-EI-1210: FS | 2025-04-18 07:00 | 2025-04-25 17:00
HM-ME-1080 | Not Started | P2543-R01-Oct24..PR.26.LL.6.3 | Transportation/ Custom Clearance/ Delivery at site of Solar PV system | HM-ME-1060 | HM-ME-1060: FS | HM-ME-1090 | HM-ME-1090: FS | 2025-03-28 08:00 | 2025-04-17 18:00
HM-ME-1160 | Not Started | P2543-R01-Oct24..PR.26.LL.5.2 | Ready for Dispatch of Active/ Passive Cooled Shelter | HM-ME-1150 | HM-ME-1150: FS | HM-ME-1180 | HM-ME-1180: FS | 2025-04-06 15:00 | 2025-04-10 15:00
HM-ME-1120 | Completed | P2543-R01-Oct24..PR.26.LL.5.2 | Vendor Document Review of Active/ Passive Cooled Shelter | HP-ME-0580, ML1309-C15 | HP-ME-0580: FS, ML1309-C15: FS | HM-ME-1130 | HM-ME-1130: FF 20 | 2024-06-17 | 2024-10-18 18:00
HM-ME-1130 | In Progress | P2543-R01-Oct24..PR.26.LL.5.2 | Manufacturing & Assembly of Active/ Passive Cooled Shelter | HM-ME-1120, HE-EL-0890 | HM-ME-1120: FF 20, HE-EL-0890: FS | HM-ME-1140 | HM-ME-1140: FS | 2024-07-26 08:00 | 2025-03-30 18:00
HM-ME-1140 | Not Started | P2543-R01-Oct24..PR.26.LL.5.2 | Factory Acceptance Test of Active/ Passive Cooled Shelter | HM-ME-1130 | HM-ME-1130: FS | HM-ME-1150 | HM-ME-1150: FS | 2025-03-31 08:00 | 2025-04-02 15:00
HM-ME-1150 | Not Started | P2543-R01-Oct24..PR.26.LL.5.2 | Packaging & Final Inspection-Active/ Passive Cooled Shelter | HM-ME-1140 | HM-ME-1140: FS | HM-ME-1160 | HM-ME-1160: FS | 2025-04-02 15:00 | 2025-04-06 15:00
HM-ME-1190 | Not Started | P2543-R01-Oct24..PR.26.LL.5.3 | Receipt at site and inspection of Active/ Passive Cooled Shelter | HM-ME-1180 | HM-ME-1180: FS | ML1054-D09, C-56-591-01-EI-1000, C-52-598-06-EI-1000, C-52-598-05-EI-1000, C-52-598-04-EI-1000, C-52-598-03-EI-1000, C-52-598-02-EI-1000, C-52-598-01-EI-1000, C-DBV6-CI-5000 | ML1054-D09: FS, C-56-591-01-EI-1000: FS, C-52-598-06-EI-1000: FS 30, C-52-598-05-EI-1000: FS 35, C-52-598-04-EI-1000: FS, C-52-598-03-EI-1000: FS, C-52-598-02-EI-1000: FS, C-52-598-01-EI-1000: FS, C-DBV6-CI-5000: FS | 2025-04-17 15:00 | 2025-04-25 15:00
HM-ME-1180 | Not Started | P2543-R01-Oct24..PR.26.LL.5.3 | Transportation/ Custom Clearance/ Delivery at site of Active/ Passive Cooled Shelter | HM-ME-1160 | HM-ME-1160: FS | HM-ME-1190 | HM-ME-1190: FS | 2025-04-10 15:00 | 2025-04-17 15:00
HM-PL-0190 | Not Started | P2543-R01-Oct24..PR.BK.1.2 | Ready for Dispatch of Ball/ Globe/ Check/ Plug Valves | HP-ME-1090, HM-PL-0180 | HP-ME-1090: FS, HM-PL-0180: FS | HM-PL-1560 | HM-PL-1560: FS 21 | 2025-01-20 08:00 | 2025-01-23 18:00
HM-PL-0150 | Completed | P2543-R01-Oct24..PR.BK.1.2 | Vendor Document Review of Ball/ Globe/ Check/ Plug Valves | ML1249-C06, HP-ME-1090, ML1369-C21, ML1043-C14, ML1239-C04, ML1040-C01, ML1229-C02 | ML1249-C06: FS, HP-ME-1090: FS, ML1369-C21: FS, ML1043-C14: FS, ML1239-C04: FS, ML1040-C01: FS, ML1229-C02: FS | HM-PL-0160 | HM-PL-0160: FS | 2024-05-17 | 2024-08-09 18:00
HM-PL-0170 | Not Started | P2543-R01-Oct24..PR.BK.1.2 | Testing and Inspection of Ball/ Globe/ Check/ Plug Valves | HM-PL-0160 | HM-PL-0160: FS | HM-PL-0180 | HM-PL-0180: FS | 2024-12-30 08:00 | 2025-01-12 18:00
HM-PL-0180 | Not Started | P2543-R01-Oct24..PR.BK.1.2 | Packaging & Final Inspection-Ball/ Globe/ Check/ Plug Valves | HM-PL-0170 | HM-PL-0170: FS | HM-PL-0190 | HM-PL-0190: FS | 2025-01-13 08:00 | 2025-01-19 18:00
HM-PL-0160 | In Progress | P2543-R01-Oct24..PR.BK.1.2 | Manufacturing & Assembly of Ball/ Globe/ Check/ Plug Valves | HM-PL-0150 | HM-PL-0150: FS | HM-PL-0170, HM-PL-0210 | HM-PL-0170: FS, HM-PL-0210: FS | 2024-08-10 08:00 | 2024-12-29 18:00
HM-PL-0220 | Not Started | P2543-R01-Oct24..PR.BK.1.3 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | HM-PL-0210 | HM-PL-0210: FS | CAB-5310, ML1539-D21, ML1529-D20, C-56-PL-607-PI-1200, C-56-PL-607-PI-1800, C-56-PL-607-PI-2000, C-56-G-HT-PI-1200, C-56-G-HT-PI-1800, C-56-G-HT-PI-2000, C-56-G-HT101-ME-1000, C-56-PR-838-PI-1200, C-56-PR-838-PI-1800, C-56-PR-838-PI-2000, C-56-591-01-PI-12 | CAB-5310: FS, ML1539-D21: FF, ML1529-D20: FF, C-56-PL-607-PI-1200: FF 12, C-56-PL-607-PI-1800: FF 12, C-56-PL-607-PI-2000: FF 12, C-56-G-HT-PI-1200: FS, C-56-G-HT-PI-1800: FS, C-56-G-HT-PI-2000: FS, C-56-G-HT101-ME-1000: FS, C-56-PR-838-PI-1200: FS, C-56-P | 2025-01-13 07:00 | 2025-01-20 17:00
HM-PL-0210 | Not Started | P2543-R01-Oct24..PR.BK.1.3 | Transportation/ Custom Clearance/ Delivery at site of Ball/ Globe/ Check/ Plug Valves (Lot 1) | HM-PL-0160 | HM-PL-0160: FS | HM-PL-0220 | HM-PL-0220: FS | 2024-12-30 08:00 | 2025-01-12 18:00
HM-PL-0290 | Not Started | P2543-R01-Oct24..PR.1.24.1 | Ready for Dispatch of Hot Tapping Material | HM-PL-0280 | HM-PL-0280: FS | HM-PL-0310 | HM-PL-0310: FS | 2025-01-29 08:00 | 2025-02-02 18:00
HM-PL-0250 | Completed | P2543-R01-Oct24..PR.1.24.1 | Vendor Document Review of Hot Tapping Material | HS-GN-0230 | HS-GN-0230: FS | HM-PL-0260 | HM-PL-0260: FS | 2024-03-01 | 2024-03-15
HM-PL-0260 | In Progress | P2543-R01-Oct24..PR.1.24.1 | Manufacturing & Assembly of Hot Tapping Material | HM-PL-0250 | HM-PL-0250: FS | HM-PL-0270 | HM-PL-0270: FS | 2024-05-14 08:00 | 2025-01-14 18:00
HM-PL-0270 | Not Started | P2543-R01-Oct24..PR.1.24.1 | Testing and Inspection of Hot Tapping Material | HM-PL-0260 | HM-PL-0260: FS | HM-PL-0280 | HM-PL-0280: FS | 2025-01-15 08:00 | 2025-01-21 18:00
HM-PL-0280 | Not Started | P2543-R01-Oct24..PR.1.24.1 | Packaging & Final Inspection-Hot Tapping Material | HM-PL-0270 | HM-PL-0270: FS | HM-PL-0290 | HM-PL-0290: FS | 2025-01-22 08:00 | 2025-01-28 18:00
HM-PL-0320 | Not Started | P2543-R01-Oct24..PR.1.24.2 | Receipt at site and inspection of Hot Tapping Material | HM-PL-0310 | HM-PL-0310: FS 60 | ML1549-D32, ML1409-D24, C-56-G-HT101-ME-1000, C-56-G-HT101-ME-1000, C-52-D-HT002-ME-1000, C-36-KM-HT03-ME-1000, C-36-KM-HT03-ME-1000, C-36-KM-HT04-ME-1000 | ML1549-D32: FF, ML1409-D24: FS, C-56-G-HT101-ME-1000: FS, C-56-G-HT101-ME-1000: FF, C-52-D-HT002-ME-1000: FF, C-36-KM-HT03-ME-1000: FF, C-36-KM-HT03-ME-1000: FS, C-36-KM-HT04-ME-1000: FF | 2025-04-25 07:00 | 2025-05-02 17:00
HM-PL-0310 | Not Started | P2543-R01-Oct24..PR.1.24.2 | Transportation/ Custom Clearance/ Delivery at site of Hot Tapping Material | HM-PL-0290 | HM-PL-0290: FS | HM-PL-0320 | HM-PL-0320: FS 60 | 2025-02-03 08:00 | 2025-02-23 18:00
HM-PL-0410 | Not Started | P2543-R01-Oct24..PR.26.LL.20.3 | Receipt at site and inspection of CP System - Temporary Material | HM-PL-0350 | HM-PL-0350: FF 5 | C-56-HC01-PL-CA-5220, C-56-HC01-PL-CA-5200, C-56-HC01-PL-CA-5400, C-56-HC01-PL-CA-5430, C-52-06CR-PL-CA-5200, C-52-06CR-PL-CA-5220, C-52-0506-PL-CA-5200, C-52-0506-PL-CA-5220, C-52-0405-PL-CA-5200, C-52-0405-PL-CA-5220, C-52-0304-PL-CA-5200, C-52-0304-PL-C | C-56-HC01-PL-CA-5220: FS, C-56-HC01-PL-CA-5200: FS, C-56-HC01-PL-CA-5400: FS, C-56-HC01-PL-CA-5430: FS, C-52-06CR-PL-CA-5200: FS, C-52-06CR-PL-CA-5220: FS, C-52-0506-PL-CA-5200: FS, C-52-0506-PL-CA-5220: FS, C-52-0405-PL-CA-5200: FS, C-52-0405-PL-CA-5220: | 2024-11-14 08:00 | 2024-11-20 18:00
HM-PL-0430 | Not Started | P2543-R01-Oct24..PR.26.LL.20.3 | Receipt at site and inspection of CP System - Permanent Material | HM-PL-0420 | HM-PL-0420: FS | ML1549-D22, ML1409-D24, C-52-598-06-CA-1000, C-52-598-05-CA-1000, C-52-598-03-CA-1000, C-52-598-01-CA-1000, C-52-PR-839-CA-1000, C-52-PL-838-CA-1000, C-52-598-02-CA-1000, C-52-598-04-CA-1000, C-56-591-01-CA-1000 | ML1549-D22: FF, ML1409-D24: FS, C-52-598-06-CA-1000: FS, C-52-598-05-CA-1000: FS, C-52-598-03-CA-1000: FS, C-52-598-01-CA-1000: FS, C-52-PR-839-CA-1000: FS, C-52-PL-838-CA-1000: FS, C-52-598-02-CA-1000: FS, C-52-598-04-CA-1000: FS, C-56-591-01-CA-1000: FS | 2025-03-18 09:00 | 2025-04-03 17:00
HM-PL-0420 | Not Started | P2543-R01-Oct24..PR.26.LL.20.3 | Transportation/ Custom Clearance/ Delivery at site of CP System | HM-PL-0390 | HM-PL-0390: FS | HM-PL-0430 | HM-PL-0430: FS | 2025-03-11 08:00 | 2025-03-17 18:00
HM-PL-0390 | Not Started | P2543-R01-Oct24..PR.26.LL.20.2 | Ready for Dispatch of CP System | HM-PL-0380 | HM-PL-0380: FS | HM-PL-0420 | HM-PL-0420: FS | 2025-03-07 08:00 | 2025-03-10 18:00
HM-PL-0350 | In Progress | P2543-R01-Oct24..PR.26.LL.20.2 | Vendor Document Review of CP System | ML1041-C03, HS-GN-0530 | ML1041-C03: FS, HS-GN-0530: FS | HM-PL-0360, HM-PL-0410 | HM-PL-0360: FS, HM-PL-0410: FF 5 | 2024-06-05 | 2024-11-15 18:00
HM-PL-0360 | Not Started | P2543-R01-Oct24..PR.26.LL.20.2 | Manufacturing & Assembly of CP System | HM-PL-0350, ML1038-C10 | HM-PL-0350: FS, ML1038-C10: FF | HM-PL-0370, C-52-HG01-PL-CA-5200, C-52-HG01-PL-CA-5220 | HM-PL-0370: FS, C-52-HG01-PL-CA-5200: FF, C-52-HG01-PL-CA-5220: SS | 2024-11-16 08:00 | 2025-02-13 18:00
HM-PL-0370 | Not Started | P2543-R01-Oct24..PR.26.LL.20.2 | Factory Acceptance Test of CP System | HM-PL-0360 | HM-PL-0360: FS | HM-PL-0380 | HM-PL-0380: FS | 2025-02-14 08:00 | 2025-02-27 18:00
HM-PL-0380 | Not Started | P2543-R01-Oct24..PR.26.LL.20.2 | Packaging & Final Inspection-CP System | HM-PL-0370 | HM-PL-0370: FS | HM-PL-0390 | HM-PL-0390: FS | 2025-02-28 08:00 | 2025-03-06 18:00
HM-PL-0500 | Not Started | P2543-R01-Oct24..PR.1.19.2 | Ready for Dispatch of Pig Signaler | HM-PL-0490 | HM-PL-0490: FS | HM-PL-0520, HM-PL-1480 | HM-PL-0520: FS, HM-PL-1480: FS 21 | 2025-03-08 08:00 | 2025-03-19 18:00
HM-PL-0460 | Completed | P2543-R01-Oct24..PR.1.19.2 | Vendor Document Review of Pig Signaler | ML1041-C03, HP-ME-1140 | ML1041-C03: FS, HP-ME-1140: FS | HM-PL-0470 | HM-PL-0470: FS | 2024-05-23 | 2024-08-25 18:00
HM-PL-0470 | In Progress | P2543-R01-Oct24..PR.1.19.2 | Manufacturing & Assembly of Pig Signaler | HM-PL-0460 | HM-PL-0460: FS | HM-PL-0480, HM-PL-0520 | HM-PL-0480: FS, HM-PL-0520: FS | 2024-08-26 08:00 | 2025-02-07 18:00
HM-PL-0480 | Not Started | P2543-R01-Oct24..PR.1.19.2 | Testing and Inspection of Pig Signaler | HM-PL-0470 | HM-PL-0470: FS | HM-PL-0490 | HM-PL-0490: FS | 2025-02-08 08:00 | 2025-02-21 18:00
HM-PL-0490 | Not Started | P2543-R01-Oct24..PR.1.19.2 | Packaging & Final Inspection-Pig Singler | HM-PL-0480 | HM-PL-0480: FS | HM-PL-0500 | HM-PL-0500: FS | 2025-02-22 08:00 | 2025-03-07 18:00
HM-PL-0530 | Not Started | P2543-R01-Oct24..PR.1.19.3 | Receipt at site and inspection of Pig Signaler (Lot 1) | HM-PL-0520 | HM-PL-0520: FS | ML1549-D32, ML1409-D24, C-56-PL-607-ME-1200, C-56-PR-838-ME-1200, C-52-PR-839-ME-1200, C-52-PL-838-ME-1200, C-4N-H5-TPL-ME-1000, C-4N-HG-TPR-ME-1100 | ML1549-D32: FF, ML1409-D24: FS, C-56-PL-607-ME-1200: FF 6, C-56-PR-838-ME-1200: FS, C-52-PR-839-ME-1200: FS, C-52-PL-838-ME-1200: FF 12, C-4N-H5-TPL-ME-1000: FS, C-4N-HG-TPR-ME-1100: FF | 2025-04-10 07:00 | 2025-04-17 17:00
HM-PL-0520 | Not Started | P2543-R01-Oct24..PR.1.19.3 | Transportation/ Custom Clearance/ Delivery at site of Pig Signaler (Lot 1) | HM-PL-0500, HM-PL-0470 | HM-PL-0500: FS, HM-PL-0470: FS | HM-PL-0530 | HM-PL-0530: FS | 2025-03-20 08:00 | 2025-04-09 18:00
HM-PL-0600 | Not Started | P2543-R01-Oct24..PR.1.1.2 | Ready for Dispatch of Hot Incution Bend | HM-PL-0590, HP-ME-1190 | HM-PL-0590: FF 14, HP-ME-1190: FS | HM-PL-0620 | HM-PL-0620: FF 7 | 2024-11-20 08:00 | 2024-12-19 18:00
HM-PL-0560 | Completed | P2543-R01-Oct24..PR.1.1.2 | Vendor Document Review of Hot Incution Bend | HP-ME-1190 | HP-ME-1190: FS | HM-PL-0570 | HM-PL-0570: FS | 2023-11-29 | 2024-01-26
HM-PL-0570 | In Progress | P2543-R01-Oct24..PR.1.1.2 | Manufacturing & Assembly of Hot Incution Bend | HM-PL-0020, HM-PL-0560 | HM-PL-0020: SS 150, HM-PL-0560: FS | HM-PL-0580 | HM-PL-0580: FF 14 | 2024-01-20 | 2024-11-14 18:00
HM-PL-0580 | Not Started | P2543-R01-Oct24..PR.1.1.2 | Testing and Inspection of Hot Incution Bend | HM-PL-0570 | HM-PL-0570: FF 14 | HM-PL-0630, HM-PL-0590 | HM-PL-0630: SS 23, HM-PL-0590: FF 7 | 2024-10-30 08:00 | 2024-11-28 18:00
HM-PL-0590 | Not Started | P2543-R01-Oct24..PR.1.1.2 | Packaging & Final Inspection-Hot Incution Bend | HM-PL-0580 | HM-PL-0580: FF 7 | HM-PL-0600 | HM-PL-0600: FF 14 | 2024-11-06 08:00 | 2024-12-05 18:00
HM-PL-0640 | Not Started | P2543-R01-Oct24..PR.1.1.3 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | HM-PL-0630, HM-PL-0620 | HM-PL-0630: FF 30, HM-PL-0620: FF 30 | ML1459-D12, C-56-PL-607-PI-1800, C-56-PL-607-PI-2000, C-56-G-HT-PI-1200, C-56-G-HT-PI-1800, C-56-G-HT-PI-2000, C-56-PR-838-PI-1200, C-56-PR-838-PI-1800, C-56-PR-838-PI-2000, C-56-591-01-PI-1200, C-56-591-01-PI-1800, C-56-591-01-PI-2000, C-52-598-06-PI-1200 | ML1459-D12: FF, C-56-PL-607-PI-1800: FS, C-56-PL-607-PI-2000: FS, C-56-G-HT-PI-1200: FS, C-56-G-HT-PI-1800: FS, C-56-G-HT-PI-2000: FS, C-56-PR-838-PI-1200: FS, C-56-PR-838-PI-1800: FS, C-56-PR-838-PI-2000: FS, C-56-591-01-PI-1200: FS, C-56-591-01-PI-1800: | 2024-12-31 07:00 | 2025-01-26 07:00
HM-PL-0630 | Not Started | P2543-R01-Oct24..PR.1.1.3 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | HM-PL-0580 | HM-PL-0580: SS 23 | ML1449-D11, HM-PL-0640, ML1439-D10, C-56-PL-607-PI-1200, C-56-PL-607-PI-1800, C-56-PL-607-PI-2000, C-56-G-HT-PI-1200, C-56-G-HT-PI-1800, C-56-G-HT-PI-2000, C-56-PR-838-PI-1200, C-56-PR-838-PI-1800, C-56-PR-838-PI-2000, C-56-591-01-PI-1200, C-56-591-01-PI-1 | ML1449-D11: FF, HM-PL-0640: FF 30, ML1439-D10: FF 9, C-56-PL-607-PI-1200: FS, C-56-PL-607-PI-1800: FS, C-56-PL-607-PI-2000: FS, C-56-G-HT-PI-1200: FS, C-56-G-HT-PI-1800: FS, C-56-G-HT-PI-2000: FS, C-56-PR-838-PI-1200: FS, C-56-PR-838-PI-1800: FS, C-56-PR-8 | 2024-11-22 07:00 | 2024-12-11 17:00
HM-PL-0620 | Not Started | P2543-R01-Oct24..PR.1.1.3 | Transportation/ Custom Clearance/ Delivery at site of Hot Incution Bend | HM-PL-0600 | HM-PL-0600: FF 7 | HM-PL-0640 | HM-PL-0640: FF 30 | 2024-12-06 08:00 | 2024-12-26 18:00
HM-PL-0710 | Not Started | P2543-R01-Oct24..PR.1.3.2 | Ready for Dispatch of Isolating Joints | HM-PL-0700, HP-ME-1240 | HM-PL-0700: FS, HP-ME-1240: FS | HM-PL-0730, HM-PL-1500 | HM-PL-0730: FS, HM-PL-1500: FS 21 | 2025-01-27 08:00 | 2025-01-30 18:00
HM-PL-0670 | Completed | P2543-R01-Oct24..PR.1.3.2 | Vendor Document Review of Isolating Joints | HP-ME-1240 | HP-ME-1240: FS | HM-PL-0680 | HM-PL-0680: FS | 2023-11-30 | 2024-01-10
HM-PL-0680 | In Progress | P2543-R01-Oct24..PR.1.3.2 | Manufacturing & Assembly of Isolating Joints | HM-PL-0670 | HM-PL-0670: FS | HM-PL-0690, HM-PL-0730 | HM-PL-0690: FS, HM-PL-0730: FS | 2024-05-03 | 2025-01-05 18:00
HM-PL-0690 | Not Started | P2543-R01-Oct24..PR.1.3.2 | Testing and Inspection of Isolating Joints | HM-PL-0680 | HM-PL-0680: FS | HM-PL-0700 | HM-PL-0700: FS | 2025-01-06 08:00 | 2025-01-19 18:00
HM-PL-0700 | Not Started | P2543-R01-Oct24..PR.1.3.2 | Packaging & Final Inspection-Isolating Joints | HM-PL-0690 | HM-PL-0690: FS | HM-PL-0710 | HM-PL-0710: FS | 2025-01-20 08:00 | 2025-01-26 18:00
HM-PL-0740 | Not Started | P2543-R01-Oct24..PR.1.3.3 | Receipt at site and inspection of Isolating Joints (Lot 1) | HM-PL-0730 | HM-PL-0730: FS | ML1549-D32, ML1409-D24, C-56-PL-607-PI-1200, C-56-PL-607-PI-1800, C-56-PL-607-PI-2000, C-56-G-HT-PI-1200, C-56-G-HT-PI-1800, C-56-G-HT-PI-2000, C-56-PR-838-PI-1200, C-56-PR-838-PI-1800, C-56-PR-838-PI-2000, C-56-591-01-PI-1200, C-56-591-01-PI-1800, C-56-59 | ML1549-D32: FF, ML1409-D24: FS, C-56-PL-607-PI-1200: FS, C-56-PL-607-PI-1800: FS, C-56-PL-607-PI-2000: FS, C-56-G-HT-PI-1200: FS, C-56-G-HT-PI-1800: FS, C-56-G-HT-PI-2000: FS, C-56-PR-838-PI-1200: FS, C-56-PR-838-PI-1800: FS, C-56-PR-838-PI-2000: FS, C-56- | 2025-02-07 07:00 | 2025-02-14 17:00
HM-PL-0730 | Not Started | P2543-R01-Oct24..PR.1.3.3 | Transportation/ Custom Clearance/ Delivery at site of Isolating Joints (Lot 1) | HM-PL-0710, HM-PL-0680 | HM-PL-0710: FS, HM-PL-0680: FS | HM-PL-0740 | HM-PL-0740: FS | 2025-01-31 08:00 | 2025-02-06 18:00
HM-PL-0770 | Completed | P2543-R01-Oct24..PR.1.2.2 | Vendor Document Review of Pigging & Split Tee | HP-ME-1290, HE-PL-3720 | HP-ME-1290: FS, HE-PL-3720: FS | HM-PL-0780 | HM-PL-0780: FS | 2024-05-27 | 2024-08-05 18:00
HM-PL-0780 | In Progress | P2543-R01-Oct24..PR.1.2.2 | Manufacturing & Assembly of Pigging & Split Tee | HM-PL-0770 | HM-PL-0770: FS | HM-PL-0790, HM-PL-0830 | HM-PL-0790: FS, HM-PL-0830: FS | 2024-08-06 | 2025-01-16 18:00
HM-PL-0800 | Not Started | P2543-R01-Oct24..PR.1.2.2 | Packaging & Final Inspection-Pigging & Split Tee | HM-PL-0790 | HM-PL-0790: FS | HM-PL-0810 | HM-PL-0810: FS | 2025-01-31 08:00 | 2025-02-06 18:00
HM-PL-0810 | Not Started | P2543-R01-Oct24..PR.1.2.2 | Ready for Dispatch of Pigging & Split Tee | HM-PL-0800, HP-ME-1290 | HM-PL-0800: FS, HP-ME-1290: FS | HM-PL-1520, HM-PL-0830 | HM-PL-1520: FS, HM-PL-0830: FS | 2025-02-07 08:00 | 2025-02-10 18:00
HM-PL-0790 | Not Started | P2543-R01-Oct24..PR.1.2.2 | Testing and Inspection of Pigging & Split Tee | HM-PL-0780 | HM-PL-0780: FS | HM-PL-0800 | HM-PL-0800: FS | 2025-01-17 08:00 | 2025-01-30 18:00
HM-PL-0840 | Not Started | P2543-R01-Oct24..PR.1.2.3 | Receipt at site and inspection of Pigging & Split Tee (Lot 1) | HM-PL-0830 | HM-PL-0830: FS | ML1549-D32, ML1409-D24, C-56-PL-607-ME-1000, C-56-PL-607-ME-1200, C-56-G-HT101-ME-1000, C-56-PR-838-ME-1200, C-52-PR-839-ME-1200, C-52-PL-838-ME-1200, C-4N-H5-TPL-ME-1000, C-4N-HG-TPR-ME-1100, HM-PL-1530 | ML1549-D32: FF, ML1409-D24: FS, C-56-PL-607-ME-1000: FF, C-56-PL-607-ME-1200: FS, C-56-G-HT101-ME-1000: FS, C-56-PR-838-ME-1200: FS, C-52-PR-839-ME-1200: FS, C-52-PL-838-ME-1200: FS, C-4N-H5-TPL-ME-1000: FS, C-4N-HG-TPR-ME-1100: FS, HM-PL-1530: FF 6 | 2025-03-04 09:00 | 2025-03-17 13:00
HM-PL-0830 | Not Started | P2543-R01-Oct24..PR.1.2.3 | Transportation/ Custom Clearance/ Delivery at site of Pigging & Split Tee (Lot 1) | HM-PL-0780, HM-PL-0810 | HM-PL-0780: FS, HM-PL-0810: FS | HM-PL-0840 | HM-PL-0840: FS | 2025-02-11 08:00 | 2025-03-03 18:00
HM-PL-0010 | Completed | P2543-R01-Oct24..PR.1.16.2.1 | Vendor Document Review of Line Pipes - Lot 1 | HE-PL-1670, HP-ME-1040, ML1021-B15, ML1040-C01 | HE-PL-1670: FS, HP-ME-1040: FS, ML1021-B15: FS, ML1040-C01: FS | HM-PL-970, HM-PL-0020 | HM-PL-970: SS, HM-PL-0020: FS | 2023-09-12 | 2023-10-20
HM-PL-0020 | Completed | P2543-R01-Oct24..PR.1.16.2.1 | Manufacturing & Receive Plates at Fabrication Shop - Lot 1 | HM-PL-0010 | HM-PL-0010: FS | HM-PL-980, HM-PL-0570, HM-PL-0030 | HM-PL-980: FF 10, HM-PL-0570: SS 150, HM-PL-0030: FS | 2023-10-20 | 2024-01-10
HM-PL-0030 | Completed | P2543-R01-Oct24..PR.1.16.2.1 | Complete Line Pipe Production - Lot 1 | HM-PL-0020 | HM-PL-0020: FS | C-COM-1000, HM-PL-0035 | C-COM-1000: FF 0, HM-PL-0035: FF 19 | 2024-01-22 | 2024-03-24
HM-PL-0040 | Completed | P2543-R01-Oct24..PR.1.16.2.1 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 1 | HM-PL-0035 | HM-PL-0035: FS | HM-PL-0050 | HM-PL-0050: FS | 2024-04-27 | 2024-05-25
HM-PL-0050 | Completed | P2543-R01-Oct24..PR.1.16.2.1 | Ready for Dispatch of Line Pipes (Coated) - Lot 1 | HP-ME-1040, HM-PL-0040 | HP-ME-1040: FS, HM-PL-0040: FS | HM-PL-1010, HM-PL-0080 | HM-PL-1010: FF, HM-PL-0080: SS 4 | 2024-05-26 | 2024-05-26
HM-PL-0100 | Completed | P2543-R01-Oct24..PR.1.16.3 | Receipt at site and inspection of Line Pipes - Lot 3 (Coated) | HM-PL-1070, HM-PL-0090 | HM-PL-1070: FF 5, HM-PL-0090: FS | C-4W-SVHG-PIPEL-1000, C-52-0102-PL-ME-2800, C-52-0203-PL-ME-2800, C-52-0304-PL-ME-2800 | C-4W-SVHG-PIPEL-1000: FS, C-52-0102-PL-ME-2800: FF, C-52-0203-PL-ME-2800: FF 7, C-52-0304-PL-ME-2800: SS | 2024-08-26 08:00 | 2024-09-26 08:00
HM-PL-0110 | Not Started | P2543-R01-Oct24..PR.1.16.3 | Receipt at site and inspection of Line Pipes - Lot 6 (Coated) | HM-PL-1130 | HM-PL-1130: FS | HM-PL-0120, C-56-01HG-PL-ME-3000, C-4W-SVHG-PIPEL-1000, C-56-01HG-PL-ME-2800, C-4W-SVHG-PIPEL-1000, C-4W-SVHG-PIPEL-1000, ML1052-D1 | HM-PL-0120: FS, C-56-01HG-PL-ME-3000: SS 16, C-4W-SVHG-PIPEL-1000: SS 21, C-56-01HG-PL-ME-2800: FF 20, C-4W-SVHG-PIPEL-1000: FS 15, C-4W-SVHG-PIPEL-1000: FF, ML1052-D1: FF 17 | 2024-12-02 08:00 | 2024-12-26 18:00
HM-PL-0120 | Not Started | P2543-R01-Oct24..PR.1.16.3 | Receipt at site and inspection of Line Pipes - Lot 7 (Coated) | HM-PL-1190, HM-PL-0110 | HM-PL-1190: FS, HM-PL-0110: FS | ML1060, HM-PL-1470, ML1399-D5, HM-PL-960, C-4N-H5HG-PIPEL-2800, ML1389-D2 | ML1060: FS, HM-PL-1470: FS, ML1399-D5: FF, HM-PL-960: FS, C-4N-H5HG-PIPEL-2800: FF 7, ML1389-D2: FF 14 | 2025-01-12 08:00 | 2025-02-05 18:00
HM-PL-0080 | Completed | P2543-R01-Oct24..PR.1.16.3 | Receipt at site and inspection of Line Pipes - Lot 1 (Coated) | ML1001-A01, ML1002, HM-PL-0050 | ML1001-A01: FS, ML1002: FS, HM-PL-0050: SS 4 | HM-PL-0090, C-52-06CR-PL-ME-2800, C-52-HG01-PL-ME-2800 | HM-PL-0090: FS, C-52-06CR-PL-ME-2800: FS 4, C-52-HG01-PL-ME-2800: FS | 2024-07-05 08:00 | 2024-07-12 18:00
HM-PL-0090 | Completed | P2543-R01-Oct24..PR.1.16.3 | Receipt at site and inspection of Line Pipes - Lot 2 (Coated) | HM-PL-1010, HM-PL-0080 | HM-PL-1010: FS, HM-PL-0080: FS | HM-PL-0100, C-52-0506-PL-ME-2800, C-52-HG01-PL-ME-2800 | HM-PL-0100: FS, C-52-0506-PL-ME-2800: FS 4, C-52-HG01-PL-ME-2800: FS | 2024-07-13 08:00 | 2024-07-26 18:00
ML1000 | Completed | P2543-R01-Oct24..ML | Award / Project Start |  |  | ML1001, PRJ-MI-1000 | ML1001: SS 7, PRJ-MI-1000: FS 8 | 2023-07-03
ML1001 | Completed | P2543-R01-Oct24..ML | Project Effective Date | ML1000 | ML1000: SS 7 | HS-GN-0130, ML1002 | HS-GN-0130: SS 3, ML1002: SS 9 | 2023-07-10
HE-PR-1200 | Completed | P2543-R01-Oct24..1.EN.3.19 | Re-Issue after incorporating Review Comments- H&MB Report | HE-PR-1250, HE-PR-0630, HE-HS-0670 | HE-PR-1250: FS, HE-PR-0630: FS, HE-HS-0670: FF | ML1219-B19, HE-PR-1130, HE-PI-0170, HE-PR-0870, HE-PR-0450, HE-PR-0570, HE-PR-1280, HE-PR-1330, HE-PR-1380, HE-PR-1430, HE-PR-1480, HE-PR-1530, HE-PR-1580, HE-PR-1050, HE-PI-0420, HE-PI-0490, HE-PI-0350, HE-PI-0560, HE-PR-0140, HE-PR-1210, HE-PI-0620, ML12 | ML1219-B19: FF, HE-PR-1130: FS, HE-PI-0170: FS, HE-PR-0870: FS, HE-PR-0450: FS, HE-PR-0570: FS, HE-PR-1280: FS, HE-PR-1330: FS, HE-PR-1380: FS, HE-PR-1430: FS, HE-PR-1480: FS, HE-PR-1530: FS, HE-PR-1580: FS, HE-PR-1050: FS, HE-PI-0420: FS, HE-PI-0490: FS, | 2023-09-13 | 2023-09-29
HE-PR-1210 | Completed | P2543-R01-Oct24..1.EN.3.19 | Obtain Company Approval- H&MB Report | HE-PR-1200 | HE-PR-1200: FS | HE-PR-1220 | HE-PR-1220: FS | 2023-10-03 | 2023-10-16
HE-PR-1220 | Completed | P2543-R01-Oct24..1.EN.3.19 | Final Issue for Design/ Construction- H&MB Report | HE-PR-1210, HE-PR-0650 | HE-PR-1210: FS, HE-PR-0650: FS | ML1219-B19, HE-PR-0160, ML1014-B10, HE-PI-0580, HE-PI-0510, HE-PI-0370, HE-PI-0440, HE-PI-0620, ML1219-B29, CAB-4400 | ML1219-B19: FF, HE-PR-0160: FS, ML1014-B10: FS, HE-PI-0580: FS, HE-PI-0510: FS, HE-PI-0370: FS, HE-PI-0440: FS, HE-PI-0620: FS, ML1219-B29: FF, CAB-4400: FS | 2024-05-28 07:30 | 2024-07-08 17:30
HE-PR-1240 | Completed | P2543-R01-Oct24..1.EN.3.19 | Issue ICR- H&MB Report | HE-DB-0010 | HE-DB-0010: FS | ML1219-B19, HE-PR-1130, HE-PI-0170, HE-PR-0870, HE-PR-0450, HE-PR-0570, HE-PR-1280, HE-PR-1330, HE-PR-1380, HE-PR-1430, HE-PR-1480, HE-PR-1530, HE-PR-1580, HE-HS-0970, HE-PI-0150, HE-HS-0670, HE-WS-0050, HE-HS-0490, HE-PI-0130, C-COM-790, CAB-5290, ML1012- | ML1219-B19: FF, HE-PR-1130: FS, HE-PI-0170: FS, HE-PR-0870: FS, HE-PR-0450: FS, HE-PR-0570: FS, HE-PR-1280: FS, HE-PR-1330: FS, HE-PR-1380: FS, HE-PR-1430: FS, HE-PR-1480: FS, HE-PR-1530: FS, HE-PR-1580: FS, HE-HS-0970: FS, HE-PI-0150: FS, HE-HS-0670: FS, | 2023-08-04 | 2023-08-14
HE-PR-1250 | Completed | P2543-R01-Oct24..1.EN.3.19 | Receive Company Comments- H&MB Report | HE-PR-1240 | HE-PR-1240: FS | ML1219-B19, HE-PR-1130, HE-PI-0170, HE-PR-0870, HE-PR-0450, HE-PR-0570, HE-PR-1280, HE-PR-1330, HE-PR-1380, HE-PR-1430, HE-PR-1480, HE-PR-1530, HE-PR-1580, HE-HS-0970, HE-PI-0150, HE-HS-0670, HE-WS-0050, HE-HS-0490, HE-PI-0130, C-COM-790, CAB-5290, HE-PR-0 | ML1219-B19: FF, HE-PR-1130: FS, HE-PI-0170: FS, HE-PR-0870: FS, HE-PR-0450: FS, HE-PR-0570: FS, HE-PR-1280: FS, HE-PR-1330: FS, HE-PR-1380: FS, HE-PR-1430: FS, HE-PR-1480: FS, HE-PR-1530: FS, HE-PR-1580: FS, HE-HS-0970: FS, HE-PI-0150: FS, HE-HS-0670: FS, | 2023-08-14 | 2023-08-24
HE-ME-230 | Completed | P2543-R01-Oct24..1.EN.5.1 | Receive Company Comments- Mechanical Design Basis | HE-ME-270 | HE-ME-270: FS | HE-ME-240 | HE-ME-240: FS | 2023-08-22 | 2023-08-31
HE-ME-240 | Completed | P2543-R01-Oct24..1.EN.5.1 | Re-Issue for Approval- Mechanical Design Basis | HE-ME-230 | HE-ME-230: FS | HE-ME-250 | HE-ME-250: FS | 2023-09-11 | 2023-09-25
HE-ME-250 | Completed | P2543-R01-Oct24..1.EN.5.1 | Obtain Company Approval- Mechanical Design Basis | HE-ME-240 | HE-ME-240: FS | HE-ME-260 | HE-ME-260: FS | 2023-09-26 | 2023-10-04
HE-ME-260 | Completed | P2543-R01-Oct24..1.EN.5.1 | Final Issue for Design/ Construction- Mechanical Design Basis | HE-ME-250 | HE-ME-250: FS | HE-ME-0110, HE-ME-0170, CAB-4430, HE-PR-0470, HE-ME-520, HE-ME-0050 | HE-ME-0110: FS, HE-ME-0170: FS, CAB-4430: FS, HE-PR-0470: FS, HE-ME-520: FS, HE-ME-0050: FS | 2023-10-05 | 2023-10-11
HE-ME-270 | Completed | P2543-R01-Oct24..1.EN.5.1 | Issue ICR- Mechanical Design Basis | HE-DB-0010, ML1002 | HE-DB-0010: FS, ML1002: SS | HP-ME-0860, HE-ME-0070, HE-ME-230, HE-ME-0130, HE-ME-480, HE-ME-0010 | HP-ME-0860: FS, HE-ME-0070: SS, HE-ME-230: FS, HE-ME-0130: SS, HE-ME-480: SS, HE-ME-0010: FS | 2023-08-06 | 2023-08-21
HE-PR-1260 | Completed | P2543-R01-Oct24..1.EN.3.20.1 | Issue ICR- Process Datasheets | HE-DB-0010, HE-PR-0550, ML1002 | HE-DB-0010: FS, HE-PR-0550: FS, ML1002: SS | HE-PR-1270, HE-PR-1310, HE-IC-1090, HE-PR-1360, HE-PR-1560 | HE-PR-1270: FS, HE-PR-1310: FS 10, HE-IC-1090: SS 5, HE-PR-1360: FS, HE-PR-1560: FS | 2023-09-04 | 2023-09-11
HE-PR-1270 | Completed | P2543-R01-Oct24..1.EN.3.20.1 | Receive Company Comments- Process Datasheets | HE-PR-1260 | HE-PR-1260: FS | HE-PR-1280, HE-IC-1090 | HE-PR-1280: FS, HE-IC-1090: FS | 2023-09-12 | 2023-09-22
HE-PR-1280 | Completed | P2543-R01-Oct24..1.EN.3.20.1 | Re-Issue for Approval- Process Datasheets | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-WS-0030, HE-HS-0670, HE-PR-0070, HE-PR-1200, HE-PR-1270, HE-PR-0140 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-WS-0030: FS, HE-HS-0670: SS, HE-PR-0070: FS, HE-PR-1200: FS, HE-PR-1270: FS, HE-PR-0140: FS | HE-PR-1290 | HE-PR-1290: FS | 2023-11-01 | 2023-11-07
HE-PR-1290 | Completed | P2543-R01-Oct24..1.EN.3.20.1 | Obtain Company Approval- Process Datasheets | HE-PR-1280 | HE-PR-1280: FS | HE-PR-1300 | HE-PR-1300: FS | 2023-11-08 | 2023-11-16
HE-PR-1300 | Completed | P2543-R01-Oct24..1.EN.3.20.1 | Final Issue for Design/ Construction-Process Datasheets | HE-PR-1290 | HE-PR-1290: FS | HE-PR-1070, HM-ME-0120, CAB-4400, HM-ME-0420, HM-ME-0320 | HE-PR-1070: FS, HM-ME-0120: FS, CAB-4400: FS, HM-ME-0420: FS, HM-ME-0320: FS | 2023-11-17 | 2023-12-20
HE-PR-1310 | Completed | P2543-R01-Oct24..1.EN.3.20.2 | Issue ICR- Process Datasheets | HE-PR-1260, HE-PR-0790, ML1002 | HE-PR-1260: FS 10, HE-PR-0790: FS, ML1002: SS | HE-PR-1320, HE-PR-0970, HE-IC-1330 | HE-PR-1320: FS, HE-PR-0970: SS, HE-IC-1330: FS | 2023-11-17 | 2023-11-23
HE-PR-1320 | Completed | P2543-R01-Oct24..1.EN.3.20.2 | Receive Company Comments- Process Datasheets | HE-PR-1310 | HE-PR-1310: FS | HE-PR-1330, HE-IC-1340 | HE-PR-1330: FS, HE-IC-1340: FS | 2023-11-27 | 2023-12-01
HE-PR-1330 | Completed | P2543-R01-Oct24..1.EN.3.20.2 | Re-Issue for Approval- Process Datasheets | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-WS-0030, HE-HS-0670, HE-PR-0070, HE-PR-1200, HE-PR-1320, HE-PR-0140 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-WS-0030: FS, HE-HS-0670: SS, HE-PR-0070: FS, HE-PR-1200: FS, HE-PR-1320: FS, HE-PR-0140: FS 20 | HE-PR-1340 | HE-PR-1340: FS | 2023-12-29 | 2024-01-15
HE-PR-1340 | Completed | P2543-R01-Oct24..1.EN.3.20.2 | Obtain Company Approval- Process Datasheets | HE-PR-1330 | HE-PR-1330: FS | HE-PR-1350 | HE-PR-1350: FS | 2024-02-26 | 2024-03-01
HE-PR-1350 | Completed | P2543-R01-Oct24..1.EN.3.20.2 | Final Issue for Design/ Construction-Process Datasheets | HE-PR-1340 | HE-PR-1340: FS | HE-PR-1070, HM-ME-0120, CAB-4400, HM-ME-0420, HM-ME-0320 | HE-PR-1070: FS, HM-ME-0120: FS, CAB-4400: FS, HM-ME-0420: FS, HM-ME-0320: FS | 2024-03-02 | 2024-03-11
HE-PR-1360 | Completed | P2543-R01-Oct24..1.EN.3.20.3 | Issue ICR- Process Datasheets | HE-PR-1260, HE-PR-1560, ML1002 | HE-PR-1260: FS, HE-PR-1560: FS, ML1002: SS | HE-PR-1370, HE-PR-1410 | HE-PR-1370: FS, HE-PR-1410: FS | 2023-10-02 | 2023-10-13
HE-PR-1370 | Completed | P2543-R01-Oct24..1.EN.3.20.3 | Receive Company Comments- Process Datasheets | HE-PR-1360 | HE-PR-1360: FS | HE-PR-1380, HE-IC-1450 | HE-PR-1380: FS, HE-IC-1450: FS | 2023-10-16 | 2023-10-27
HE-PR-1380 | Completed | P2543-R01-Oct24..1.EN.3.20.3 | Re-Issue for Approval- Process Datasheets | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-WS-0030, HE-HS-0670, HE-PR-0070, HE-PR-1200, HE-PR-1370, HE-PR-0140 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-WS-0030: FS, HE-HS-0670: SS, HE-PR-0070: FS, HE-PR-1200: FS, HE-PR-1370: FS, HE-PR-0140: FS | HE-PR-1390 | HE-PR-1390: FS | 2023-11-15 | 2023-11-21
HE-PR-1390 | Completed | P2543-R01-Oct24..1.EN.3.20.3 | Obtain Company Approval- Process Datasheets | HE-PR-1380 | HE-PR-1380: FS | HE-PR-1400 | HE-PR-1400: FS | 2023-12-04 | 2023-12-15
HE-PR-1400 | Completed | P2543-R01-Oct24..1.EN.3.20.3 | Final Issue for Design/ Construction-Process Datasheets | HE-PR-1390 | HE-PR-1390: FS | HE-PR-1070, HM-ME-0120, CAB-4400, HM-ME-0420, HM-ME-0320 | HE-PR-1070: FS, HM-ME-0120: FS, CAB-4400: FS, HM-ME-0420: FS, HM-ME-0320: FS | 2023-12-29 | 2024-01-16
HE-PR-1410 | Completed | P2543-R01-Oct24..1.EN.3.20.4 | Issue ICR- Process Datasheets | HE-PR-1360, ML1002 | HE-PR-1360: FS, ML1002: SS | HE-PR-1420, HE-PR-1460 | HE-PR-1420: FS, HE-PR-1460: FS | 2023-11-02 | 2023-11-14
HE-PR-1420 | Completed | P2543-R01-Oct24..1.EN.3.20.4 | Receive Company Comments- Process Datasheets | HE-PR-1410 | HE-PR-1410: FS | HE-PR-1430, HE-IC-1450 | HE-PR-1430: FS, HE-IC-1450: FS | 2023-11-15 | 2023-11-20
HE-PR-1430 | Completed | P2543-R01-Oct24..1.EN.3.20.4 | Re-Issue for Approval- Process Datasheets | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-WS-0030, HE-HS-0670, HE-PR-0070, HE-PR-1200, HE-PR-1420, HE-PR-0140 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-WS-0030: FS, HE-HS-0670: SS, HE-PR-0070: FS, HE-PR-1200: FS, HE-PR-1420: FS, HE-PR-0140: FS | HE-PR-1440 | HE-PR-1440: FS | 2023-11-21 | 2023-11-24
HE-PR-1440 | Completed | P2543-R01-Oct24..1.EN.3.20.4 | Obtain Company Approval- Process Datasheets | HE-PR-1430 | HE-PR-1430: FS | HE-PR-1450 | HE-PR-1450: FS | 2023-12-04 | 2023-12-15
HE-PR-1450 | Completed | P2543-R01-Oct24..1.EN.3.20.4 | Final Issue for Design/ Construction-Process Datasheets | HE-PR-1440 | HE-PR-1440: FS | HE-PR-1070, HM-ME-0120, CAB-4400, HM-ME-0420, HM-ME-0320 | HE-PR-1070: FS, HM-ME-0120: FS, CAB-4400: FS, HM-ME-0420: FS, HM-ME-0320: FS | 2023-12-29 | 2024-01-16
HE-PR-1460 | Completed | P2543-R01-Oct24..1.EN.3.20.5 | Issue ICR- Process Datasheets | HE-PR-1410, ML1002 | HE-PR-1410: FS, ML1002: SS | HE-PR-1470, HE-PR-1510, HE-IC-1450 | HE-PR-1470: FS, HE-PR-1510: FS, HE-IC-1450: FS 5 | 2023-11-02 | 2023-11-14
HE-PR-1470 | Completed | P2543-R01-Oct24..1.EN.3.20.5 | Receive Company Comments- Process Datasheets | HE-PR-1460 | HE-PR-1460: FS | HE-PR-1480, HE-IC-1460 | HE-PR-1480: FS, HE-IC-1460: FS | 2023-11-15 | 2023-11-20
HE-PR-1480 | Completed | P2543-R01-Oct24..1.EN.3.20.5 | Re-Issue for Approval- Process Datasheets | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-WS-0030, HE-HS-0670, HE-PR-0070, HE-PR-1200, HE-PR-1470, HE-PR-0140 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-WS-0030: FS, HE-HS-0670: SS, HE-PR-0070: FS, HE-PR-1200: FS, HE-PR-1470: FS, HE-PR-0140: FS | HE-PR-1490 | HE-PR-1490: FS | 2023-11-21 | 2023-11-24
HE-PR-1490 | Completed | P2543-R01-Oct24..1.EN.3.20.5 | Obtain Company Approval- Process Datasheets | HE-PR-1480 | HE-PR-1480: FS | HE-PR-1500 | HE-PR-1500: FS | 2023-12-04 | 2023-12-15
HE-PR-1500 | Completed | P2543-R01-Oct24..1.EN.3.20.5 | Final Issue for Design/ Construction-Process Datasheets | HE-PR-1490 | HE-PR-1490: FS | HE-PR-1070, HM-ME-0120, CAB-4400, HM-ME-0420, HM-ME-0320 | HE-PR-1070: FS, HM-ME-0120: FS, CAB-4400: FS, HM-ME-0420: FS, HM-ME-0320: FS | 2023-12-29 | 2024-01-16
HE-PR-1510 | Completed | P2543-R01-Oct24..1.EN.3.20.6 | Issue ICR- Process Datasheets | HE-PR-1460, ML1002 | HE-PR-1460: FS, ML1002: SS | HE-PR-1520, HE-IC-1450 | HE-PR-1520: FS, HE-IC-1450: FS | 2023-11-16 | 2023-11-22
HE-PR-1520 | Completed | P2543-R01-Oct24..1.EN.3.20.6 | Receive Company Comments- Process Datasheets | HE-PR-1510 | HE-PR-1510: FS | HE-PR-1530, HE-IC-1460 | HE-PR-1530: FS, HE-IC-1460: FS | 2023-11-23 | 2023-12-05
HE-PR-1530 | Completed | P2543-R01-Oct24..1.EN.3.20.6 | Re-Issue for Approval- Process Datasheets | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-WS-0030, HE-HS-0670, HE-PR-0070, HE-PR-1200, HE-PR-1520, HE-PR-0140 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-WS-0030: FS, HE-HS-0670: SS, HE-PR-0070: FS, HE-PR-1200: FS, HE-PR-1520: FS, HE-PR-0140: FS | HE-PR-1540 | HE-PR-1540: FS | 2023-12-06 | 2023-12-11
HE-PR-1540 | Completed | P2543-R01-Oct24..1.EN.3.20.6 | Obtain Company Approval- Process Datasheets | HE-PR-1530 | HE-PR-1530: FS | HE-PR-1550 | HE-PR-1550: FS | 2023-12-12 | 2023-12-22
HE-PR-1550 | Completed | P2543-R01-Oct24..1.EN.3.20.6 | Final Issue for Design/ Construction-Process Datasheets | HE-PR-1540 | HE-PR-1540: FS | HE-PR-1070, HM-ME-0120, CAB-4400, HM-ME-0420, HM-ME-0320 | HE-PR-1070: FS, HM-ME-0120: FS, CAB-4400: FS, HM-ME-0420: FS, HM-ME-0320: FS | 2023-12-29 | 2024-01-16
HE-PR-1560 | Completed | P2543-R01-Oct24..1.EN.3.20.7 | Issue ICR- Process Datasheets | HE-PR-1260, ML1002 | HE-PR-1260: FS, ML1002: SS | HE-PR-1570, HE-PR-1360 | HE-PR-1570: FS, HE-PR-1360: FS | 2023-11-14 | 2023-11-17
HE-PR-1570 | Completed | P2543-R01-Oct24..1.EN.3.20.7 | Receive Company Comments- Process Datasheets | HE-PR-1560 | HE-PR-1560: FS | HE-PR-1580, HE-IC-1340 | HE-PR-1580: FS, HE-IC-1340: FS | 2023-11-21 | 2023-11-23
HE-PR-1580 | Completed | P2543-R01-Oct24..1.EN.3.20.7 | Re-Issue for Approval- Process Datasheets | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-WS-0030, HE-HS-0670, HE-PR-0070, HE-PR-1200, HE-PR-1570, HE-PR-0140 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-WS-0030: FS, HE-HS-0670: SS, HE-PR-0070: FS, HE-PR-1200: FS, HE-PR-1570: FS, HE-PR-0140: FS | HE-PR-1590 | HE-PR-1590: FS | 2023-12-29 | 2024-01-15
HE-PR-1590 | Completed | P2543-R01-Oct24..1.EN.3.20.7 | Obtain Company Approval- Process Datasheets | HE-PR-1580 | HE-PR-1580: FS | HE-PR-1600 | HE-PR-1600: FS | 2024-02-26 | 2024-03-12
HE-PR-1600 | Completed | P2543-R01-Oct24..1.EN.3.20.7 | Final Issue for Design/ Construction-Process Datasheets | HE-PR-1590 | HE-PR-1590: FS | HE-PR-1070, HM-ME-0120, CAB-4400, HM-ME-0420, HM-ME-0320 | HE-PR-1070: FS, HM-ME-0120: FS, CAB-4400: FS, HM-ME-0420: FS, HM-ME-0320: FS | 2024-03-12 | 2024-03-25
HE-DB-50 | Completed | P2543-R01-Oct24..1.EN.1.56 | Re-Issue for Approval-Design Basis | HE-DB-90 | HE-DB-90: FS | HE-DB-70 | HE-DB-70: FS | 2023-08-26 | 2023-10-30
HE-DB-60 | Completed | P2543-R01-Oct24..1.EN.1.56 | Final Issue for Design/ Construction-Design Basis | HE-DB-70 | HE-DB-70: FS | HE-PL-0070 | HE-PL-0070: SS | 2023-11-17 | 2024-07-02 17:30
HE-DB-70 | Completed | P2543-R01-Oct24..1.EN.1.56 | Obtain Company Approval-Design Basis | HE-DB-50 | HE-DB-50: FS | HE-DB-60 | HE-DB-60: FS | 2023-10-31 | 2023-11-16
HE-DB-80 | Completed | P2543-R01-Oct24..1.EN.1.56 | Issue ICR- Pipeline Design Basis | HE-DB-0010 | HE-DB-0010: FS | HE-PL-0010, HE-PL-3860, HE-DB-90 | HE-PL-0010: FF, HE-PL-3860: FS, HE-DB-90: FS | 2023-08-06 | 2023-08-16
HE-DB-90 | Completed | P2543-R01-Oct24..1.EN.1.56 | Receive Company Comments-Design Basis | HE-DB-80 | HE-DB-80: FS | HE-DB-50 | HE-DB-50: FS | 2023-08-15 | 2023-08-25
HE-PL-3330 | Completed | P2543-R01-Oct24..1.EN.1.58 | Issue ICR - Pipeline Tie In List | HE-PL-2570 | HE-PL-2570: FS | HE-PL-3340, HE-PL-3780 | HE-PL-3340: FS, HE-PL-3780: FS | 2024-02-26 | 2024-03-17
HE-PL-3340 | Completed | P2543-R01-Oct24..1.EN.1.58 | Receive Company Comments - Pipeline Tie In List | HE-PL-3330 | HE-PL-3330: FS | HE-PL-3350 | HE-PL-3350: FS | 2024-03-31 | 2024-04-09
HE-PL-3350 | Completed | P2543-R01-Oct24..1.EN.1.58 | Re-Issue for Approval - Pipeline Tie In List | HE-PL-3340 | HE-PL-3340: FS | HE-PL-3360 | HE-PL-3360: FS | 2024-04-10 | 2024-04-16
HE-PL-3360 | Completed | P2543-R01-Oct24..1.EN.1.58 | Obtain Company Approval - Pipeline Tie In List | HE-PL-3350 | HE-PL-3350: FS | HE-PL-3370 | HE-PL-3370: FS | 2024-04-17 | 2024-04-30
HE-PL-3370 | Completed | P2543-R01-Oct24..1.EN.1.58 | Final Issue for Design/ Construction-Pipeline Tie In List | HE-PL-3360 | HE-PL-3360: FS | HE-PL-3270 | HE-PL-3270: FS | 2024-05-14 | 2024-06-13
HE-DB-100 | Completed | P2543-R01-Oct24..1.EN.7.56 | Re-Issue for Approval-Design Basis | HE-DB-140 | HE-DB-140: FS | HE-DB-120 | HE-DB-120: FS | 2023-09-11 | 2023-09-15
HE-DB-110 | Completed | P2543-R01-Oct24..1.EN.7.56 | Final Issue for Design/ Construction-Design Basis | HE-DB-120 | HE-DB-120: FS | HE-PI-3440 | HE-PI-3440: FS | 2023-11-09 | 2023-11-20
HE-DB-120 | Completed | P2543-R01-Oct24..1.EN.7.56 | Obtain Company Approval-Design Basis | HE-DB-100 | HE-DB-100: FS | HE-DB-110 | HE-DB-110: FS | 2023-09-18 | 2023-09-25
HE-DB-130 | Completed | P2543-R01-Oct24..1.EN.7.56 | Issue ICR-Design Basis | HE-DB-0010 | HE-DB-0010: FS 5 | HE-DB-140, HE-PI-3440, HE-PI-0200 | HE-DB-140: FS, HE-PI-3440: FS, HE-PI-0200: FS | 2023-08-06 | 2023-08-16
HE-DB-140 | Completed | P2543-R01-Oct24..1.EN.7.56 | Receive Company Comments-Design Basis | HE-DB-130 | HE-DB-130: FS | HE-DB-100 | HE-DB-100: FS | 2023-08-16 | 2023-08-25
HE-PI-1310 | Completed | P2543-R01-Oct24..1.EN.7.4.15 | Final Issue for Design/ Construction-Datasheet for Piping Special Items | HE-PI-1350 | HE-PI-1350: FS | HE-PI-3720 | HE-PI-3720: FF | 2024-03-10 | 2024-07-02 17:30
HE-PI-1320 | Completed | P2543-R01-Oct24..1.EN.7.4.15 | Issue ICR- Datasheet for Piping Special Items | HE-PI-0960 | HE-PI-0960: FS | HE-PI-1330, HE-PI-3530 | HE-PI-1330: FS, HE-PI-3530: FS | 2023-11-16 | 2023-12-19
HE-PI-1330 | Completed | P2543-R01-Oct24..1.EN.7.4.15 | Receive Company Comments- Datasheet for Piping Special Items | HE-PI-1320 | HE-PI-1320: FS | HE-PI-1340 | HE-PI-1340: FS | 2023-12-19 | 2023-12-26
HE-PI-1340 | Completed | P2543-R01-Oct24..1.EN.7.4.15 | Re-Issue for Approval- Datasheet for Piping Special Items | HE-PI-1330 | HE-PI-1330: FS | HE-PI-1350 | HE-PI-1350: FS | 2024-01-29 | 2024-02-14
HE-PI-1350 | Completed | P2543-R01-Oct24..1.EN.7.4.15 | Obtain Company Approval- Datasheet for Piping Special Items | HE-PI-1340 | HE-PI-1340: FS | HE-PI-1310 | HE-PI-1310: FS | 2024-02-26 | 2024-03-08
HE-PI-1360 | Completed | P2543-R01-Oct24..1.EN.7.2.17 | Issue ICR- TBE for Piping Bulks (Pipe, Flange, etc) | HE-PI-3530, HE-PI-3540 | HE-PI-3530: FS, HE-PI-3540: FS | HE-PI-1370 | HE-PI-1370: FS | 2024-01-29 | 2024-04-04
HE-PI-1370 | Completed | P2543-R01-Oct24..1.EN.7.2.17 | Receive Company Comments- TBE for Piping Bulks (Pipe, Flange, etc) | HE-PI-1360 | HE-PI-1360: FS | HE-PI-1380 | HE-PI-1380: FS | 2024-03-19 | 2024-04-06
HE-PI-1380 | Completed | P2543-R01-Oct24..1.EN.7.2.17 | Re-Issue for Approval- TBE for Piping Bulks (Pipe, Flange, etc) | HE-PI-1370 | HE-PI-1370: FS | HE-PI-1390 | HE-PI-1390: FS | 2024-04-25 | 2024-06-06 07:30
HE-PI-1390 | Completed | P2543-R01-Oct24..1.EN.7.2.17 | Obtain Company Approval- TBE for Piping Bulks (Pipe, Flange, etc) | HE-PI-1380 | HE-PI-1380: FS | HE-PI-1400 | HE-PI-1400: FS | 2024-06-07 07:30 | 2024-07-10 17:30
HE-PI-1400 | Completed | P2543-R01-Oct24..1.EN.7.2.17 | Final Issue for Design/ Construction-TBE for Piping Bulks (Pipe, Flange, etc) | HE-PI-1390, HE-PI-3570 | HE-PI-1390: FS, HE-PI-3570: FS | ML1219-B29, HP-BK-0350 | ML1219-B29: FF, HP-BK-0350: FS | 2024-10-14 07:30 | 2024-10-21 17:30
HE-PI-1410 | Completed | P2543-R01-Oct24..1.EN.7.2.20 | Issue ICR- TBE for Piping Special Items | HE-PI-3680, HE-PI-3690 | HE-PI-3680: FS, HE-PI-3690: FS | HE-PI-1420 | HE-PI-1420: FS | 2024-06-26 | 2024-07-26 17:30
HE-PI-1420 | Completed | P2543-R01-Oct24..1.EN.7.2.20 | Receive Company Comments- TBE for Piping Special Items | HE-PI-1410 | HE-PI-1410: FS | HE-PI-1430 | HE-PI-1430: FS | 2024-07-29 07:30 | 2024-08-13 17:30
HE-PI-1430 | Completed | P2543-R01-Oct24..1.EN.7.2.20 | Re-Issue for Approval- TBE for Piping Special Items | HE-PI-1420 | HE-PI-1420: FS | HE-PI-1440 | HE-PI-1440: FS | 2024-08-14 07:30 | 2024-09-26 07:30
HE-PI-1440 | Not Started | P2543-R01-Oct24..1.EN.7.2.20 | Obtain Company Approval- TBE for Piping Special Items | HE-PI-1430 | HE-PI-1430: FS | HE-PI-1450 | HE-PI-1450: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HE-PI-1450 | Not Started | P2543-R01-Oct24..1.EN.7.2.20 | Final Issue for Design/ Construction-TBE for Piping Special Items | HE-PI-1440, HE-PI-3570, HE-PI-3570, HE-PI-3720 | HE-PI-1440: FS, HE-PI-3570: FS, HE-PI-3570: FF, HE-PI-3720: FS | ML1219-B29 | ML1219-B29: FF | 2024-11-11 07:30 | 2024-11-15 17:30
HE-PI-3430 | Completed | P2543-R01-Oct24..1.EN.7.21 | Final Issue for Design/ Construction-Piping Specifications - Addendum to DGS | HE-PI-3470 | HE-PI-3470: FS | HE-PI-3480, HE-PI-3520 | HE-PI-3480: FS, HE-PI-3520: FS | 2023-11-24 | 2024-03-15
HE-PI-3440 | Completed | P2543-R01-Oct24..1.EN.7.21 | Issue ICR - Piping Specifications - Addendum to DGS | HE-DB-130, HE-DB-110 | HE-DB-130: FS, HE-DB-110: FS | HE-PI-3450 | HE-PI-3450: FS | 2023-10-20 | 2023-10-25
HE-PI-3450 | Completed | P2543-R01-Oct24..1.EN.7.21 | Receive Company Comments - Piping Specifications - Addendum to DGS | HE-PI-3440 | HE-PI-3440: FS | HE-PI-3460 | HE-PI-3460: FS | 2023-10-30 | 2023-11-06
HE-PI-3460 | Completed | P2543-R01-Oct24..1.EN.7.21 | Re-Issue for Approval - Piping Specifications - Addendum to DGS | HE-PI-3450 | HE-PI-3450: FS | HE-PI-3470 | HE-PI-3470: FS | 2023-11-07 | 2023-11-21
HE-PI-3470 | Completed | P2543-R01-Oct24..1.EN.7.21 | Obtain Company Approval - Piping Specifications - Addendum to DGS | HE-PI-3460 | HE-PI-3460: FS | HE-PI-3430 | HE-PI-3430: FS | 2023-11-22 | 2023-12-13
HE-PI-3480 | Completed | P2543-R01-Oct24..1.EN.7.23 | Issue ICR-Piping Tie In Schedule | HE-PI-3430 | HE-PI-3430: FS | HE-PI-3490 | HE-PI-3490: FS | 2023-12-04 | 2023-12-23
HE-PI-3490 | Completed | P2543-R01-Oct24..1.EN.7.23 | Receive Company Comments-Piping Tie In Schedule | HE-PI-3480 | HE-PI-3480: FS | HE-PI-3500 | HE-PI-3500: FS | 2023-12-25 | 2024-01-15
HE-PI-3500 | Completed | P2543-R01-Oct24..1.EN.7.23 | Re-Issue for Approval-Piping Tie In Schedule | HE-PI-3490 | HE-PI-3490: FS | HE-PI-3510 | HE-PI-3510: FS | 2024-02-26 | 2024-03-18
HE-PI-3510 | Completed | P2543-R01-Oct24..1.EN.7.23 | Obtain Company Approval-Piping Tie In Schedule | HE-PI-3500 | HE-PI-3500: FS | HE-PI-3520 | HE-PI-3520: FS | 2024-03-19 | 2024-03-30
HE-PI-3520 | Completed | P2543-R01-Oct24..1.EN.7.23 | Final Issue for Design/ Construction-Piping Tie In Schedule | HE-PI-3510, HE-PI-3430 | HE-PI-3510: FS, HE-PI-3430: FS | ML1219-B29, HE-PI-1240, HE-PI-0180, CAB-4480, C-COM-750, C-56-G-HT101-ME-1000, C-52-D-HT002-ME-1000, C-36-KM-HT03-ME-1000, C-36-KM-HT04-ME-1000, C-56-G-HT-CI-0100 | ML1219-B29: FF, HE-PI-1240: FS, HE-PI-0180: FS, CAB-4480: FS, C-COM-750: FS, C-56-G-HT101-ME-1000: FS, C-52-D-HT002-ME-1000: FS, C-36-KM-HT03-ME-1000: FS, C-36-KM-HT04-ME-1000: FS, C-56-G-HT-CI-0100: FS | 2024-04-03 | 2024-04-10
HE-ME-280 | Completed | P2543-R01-Oct24..1.EN.5.2.1 | Re-Issue for Approval-Datasheet for PIG RECEIVER (839-V-101) | HE-ME-320 | HE-ME-320: FS | HE-ME-290 | HE-ME-290: FS | 2023-10-06 | 2023-10-20
HE-ME-290 | Completed | P2543-R01-Oct24..1.EN.5.2.1 | Obtain Company Approval-Datasheet for PIG RECEIVER (839-V-101) | HE-ME-280 | HE-ME-280: FS | HE-ME-300 | HE-ME-300: FS | 2023-11-07 | 2023-11-14
HE-ME-300 | Completed | P2543-R01-Oct24..1.EN.5.2.1 | Final Issue for Design/ Construction-Datasheet for PIG RECEIVER (839-V-101) | HE-ME-290, HE-ME-620 | HE-ME-290: FS, HE-ME-620: FS | HE-ME-350 | HE-ME-350: FS | 2024-07-01 07:30 | 2024-07-15 07:30
HE-ME-310 | Completed | P2543-R01-Oct24..1.EN.5.2.1 | Issue ICR-Datasheet for PIG RECEIVER (839-V-101) | HE-PR-0490, HE-ME-670, HE-PR-0530 | HE-PR-0490: FS, HE-ME-670: FS, HE-PR-0530: FS | HE-ME-320, HE-ME-360 | HE-ME-320: FS, HE-ME-360: SS 3 | 2023-09-14 | 2023-09-27
HE-ME-320 | Completed | P2543-R01-Oct24..1.EN.5.2.1 | Receive Company Comments-Datasheet for PIG RECEIVER (839-V-101) | HE-ME-310 | HE-ME-310: FS | HE-ME-280 | HE-ME-280: FS | 2023-09-28 | 2023-10-05
HE-ME-330 | Completed | P2543-R01-Oct24..1.EN.5.2.2 | Re-Issue for Approval-Datasheet for PIG LAUNCHER (838-V-602) | HE-ME-370 | HE-ME-370: FS | HE-ME-340 | HE-ME-340: FS | 2023-10-06 | 2023-10-20
HE-ME-340 | Completed | P2543-R01-Oct24..1.EN.5.2.2 | Obtain Company Approval-Datasheet for PIG LAUNCHER (838-V-602) | HE-ME-330 | HE-ME-330: FS | HE-ME-350 | HE-ME-350: FS | 2023-11-07 | 2023-11-14
HE-ME-350 | Completed | P2543-R01-Oct24..1.EN.5.2.2 | Final Issue for Design/ Construction-Datasheet for PIG LAUNCHER (838-V-602) | HE-ME-340, HE-ME-300 | HE-ME-340: FS, HE-ME-300: FS | HE-ME-400 | HE-ME-400: FS | 2024-07-12 07:30 | 2024-07-19 07:30
HE-ME-360 | Completed | P2543-R01-Oct24..1.EN.5.2.2 | Issue ICR-Datasheet for PIG LAUNCHER (838-V-602) | HE-PR-0490, HE-ME-310 | HE-PR-0490: FS, HE-ME-310: SS 3 | HE-ME-370, HE-ME-410 | HE-ME-370: FS, HE-ME-410: SS 3 | 2023-09-14 | 2023-09-27
HE-ME-370 | Completed | P2543-R01-Oct24..1.EN.5.2.2 | Receive Company Comments-Datasheet for PIG LAUNCHER (838-V-602) | HE-ME-360 | HE-ME-360: FS | HE-ME-330 | HE-ME-330: FS | 2023-09-28 | 2023-10-05
HE-ME-380 | Completed | P2543-R01-Oct24..1.EN.5.2.3 | Re-Issue for Approval-Datasheet for PIG RECEIVER (838-V-601) | HE-ME-420 | HE-ME-420: FS | HE-ME-390 | HE-ME-390: FS | 2023-10-06 | 2023-10-20
HE-ME-390 | Completed | P2543-R01-Oct24..1.EN.5.2.3 | Obtain Company Approval-Datasheet for PIG RECEIVER (838-V-601) | HE-ME-380 | HE-ME-380: FS | HE-ME-400 | HE-ME-400: FS | 2023-11-07 | 2023-11-14
HE-ME-400 | Completed | P2543-R01-Oct24..1.EN.5.2.3 | Final Issue for Design/ Construction-Datasheet for PIG RECEIVER (838-V-601) | HE-ME-390, HE-ME-610, HE-ME-350 | HE-ME-390: FS, HE-ME-610: FS, HE-ME-350: FS | HE-ME-450 | HE-ME-450: FS | 2024-07-12 07:30 | 2024-07-19 07:30
HE-ME-410 | Completed | P2543-R01-Oct24..1.EN.5.2.3 | Issue ICR-Datasheet for PIG RECEIVER (838-V-601) | HE-PR-0490, HE-ME-360 | HE-PR-0490: FS, HE-ME-360: SS 3 | HE-ME-420, HE-ME-460 | HE-ME-420: FS, HE-ME-460: SS 3 | 2023-09-14 | 2023-09-27
HE-ME-420 | Completed | P2543-R01-Oct24..1.EN.5.2.3 | Receive Company Comments-Datasheet for PIG RECEIVER (838-V-601) | HE-ME-410 | HE-ME-410: FS | HE-ME-380 | HE-ME-380: FS | 2023-09-28 | 2023-10-05
HE-ME-430 | Completed | P2543-R01-Oct24..1.EN.5.2.4 | Re-Issue for Approval-Datasheet for PIG LAUNCHER (607-V-603) | HE-ME-470 | HE-ME-470: FS | HE-ME-440 | HE-ME-440: FS | 2023-10-06 | 2023-10-20
HE-ME-440 | Completed | P2543-R01-Oct24..1.EN.5.2.4 | Obtain Company Approval-Datasheet for PIG LAUNCHER (607-V-603) | HE-ME-430 | HE-ME-430: FS | HE-ME-450 | HE-ME-450: FS | 2023-11-07 | 2023-11-14
HE-ME-450 | Completed | P2543-R01-Oct24..1.EN.5.2.4 | Final Issue for Design/ Construction-Datasheet for PIG LAUNCHER (607-V-603) | HE-ME-440, HE-ME-400 | HE-ME-440: FS, HE-ME-400: FS | CAB-4430 | CAB-4430: FS | 2024-07-01 07:30 | 2024-07-15 07:30
HE-ME-460 | Completed | P2543-R01-Oct24..1.EN.5.2.4 | Issue ICR-Datasheet for PIG LAUNCHER (607-V-603) | HE-PR-0490, HE-ME-410 | HE-PR-0490: FS, HE-ME-410: SS 3 | HE-ME-470, HE-ME-480 | HE-ME-470: FS, HE-ME-480: FS | 2023-09-14 | 2023-09-27
HE-ME-470 | Completed | P2543-R01-Oct24..1.EN.5.2.4 | Receive Company Comments-Datasheet for PIG LAUNCHER (607-V-603) | HE-ME-460 | HE-ME-460: FS | HE-ME-430 | HE-ME-430: FS | 2023-09-28 | 2023-10-05
HE-ME-480 | Completed | P2543-R01-Oct24..1.EN.5.6.3 | Issue ICR-Material Requisitions for Pig Launcher/Receiver | HE-ME-0070, HE-ME-0010, HE-ME-270, HE-IC-620, HE-ME-460 | HE-ME-0070: SS, HE-ME-0010: SS, HE-ME-270: SS, HE-IC-620: SS, HE-ME-460: FS | HP-ME-0210, HE-ME-490 | HP-ME-0210: FS, HE-ME-490: FS | 2023-10-09 | 2023-10-19
HE-ME-490 | Completed | P2543-R01-Oct24..1.EN.5.6.3 | Receive Company Comments-Material Requisitions for Pig Launcher/Receiver | HE-ME-480 | HE-ME-480: FS | HE-ME-500 | HE-ME-500: FS | 2023-11-07 | 2023-11-15
HE-ME-500 | Completed | P2543-R01-Oct24..1.EN.5.6.3 | Re-Issue for Approval-Material Requisitions for Pig Launcher/Receiver | HE-ME-0090, HE-ME-490 | HE-ME-0090: FS, HE-ME-490: FS | HE-ME-510 | HE-ME-510: FS | 2023-12-29 | 2024-01-03
HE-ME-510 | Completed | P2543-R01-Oct24..1.EN.5.6.3 | Obtain Company Approval-Material Requisitions for Pig Launcher/Receiver | HE-ME-500 | HE-ME-500: FS | HE-ME-520 | HE-ME-520: FS | 2024-01-04 | 2024-01-09
HE-ME-520 | Completed | P2543-R01-Oct24..1.EN.5.6.3 | Final Issue for Design/ Construction-Material Requisitions for Pig Launcher/Receiver | HE-ME-0050, HE-ME-510, HE-ME-260, HE-IC-610, HE-ME-660 | HE-ME-0050: FS, HE-ME-510: FS, HE-ME-260: FS, HE-IC-610: FS, HE-ME-660: FS | CAB-4430, ML1017-B18, HM-ME-0320, HE-ME-570 | CAB-4430: FS, ML1017-B18: FS, HM-ME-0320: FS, HE-ME-570: FS | 2024-01-10 | 2024-03-09
HE-ME-530 | Completed | P2543-R01-Oct24..1.EN.5.3.3 | Issue ICR-TBEs for Pig Launcher/Receiver | HP-ME-0160, HE-ME-660 | HP-ME-0160: FS, HE-ME-660: FF | HE-ME-540 | HE-ME-540: FS | 2023-11-30 | 2023-12-11
HE-ME-540 | Completed | P2543-R01-Oct24..1.EN.5.3.3 | Receive Company Comments-TBEs for Pig Launcher/Receiver | HE-ME-530 | HE-ME-530: FS | HE-ME-550 | HE-ME-550: FS | 2023-12-29 | 2023-12-29
HE-ME-550 | Completed | P2543-R01-Oct24..1.EN.5.3.3 | Re-Issue for Approval-TBEs for Pig Launcher/Receiver | HE-ME-540 | HE-ME-540: FS | HE-ME-560 | HE-ME-560: FS | 2023-12-29 | 2024-01-04
HE-ME-560 | Completed | P2543-R01-Oct24..1.EN.5.3.3 | Obtain Company Approval-TBEs for Pig Launcher/Receiver | HE-ME-550 | HE-ME-550: FS | HE-ME-570, HP-ME-0220 | HE-ME-570: FS, HP-ME-0220: FF | 2024-01-05 | 2024-01-16
HE-ME-570 | Completed | P2543-R01-Oct24..1.EN.5.3.3 | Final Issue for Design/ Construction-TBEs for Pig Launcher/Receiver | HE-ME-560, HE-ME-520 | HE-ME-560: FS, HE-ME-520: FS | ML1219-B29, CAB-4430 | ML1219-B29: FF, CAB-4430: FS | 2024-08-01 07:30 | 2024-08-13 17:30
HE-EL-150 | Completed | P2543-R01-Oct24..1.EN.9.56 | Re-Issue for Approval-Design Basis | HE-EL-190 | HE-EL-190: FS | HE-EL-170 | HE-EL-170: FS | 2023-09-15 | 2023-09-30
HE-EL-160 | Completed | P2543-R01-Oct24..1.EN.9.56 | Final Issue for Design/ Construction-Design Basis | HE-EL-170 | HE-EL-170: FS | HE-EL-0130, HE-EL-0250, HE-EL-0310, HE-EL-0190, HE-EL-0730, HE-EL-1870, HE-EL-0170, CAB-4450, HE-EL-0290, HE-EL-0830, HE-EL-0770, HE-EL-0650, HE-EL-0710, HE-EL-0350, HE-EL-0230, HE-EL-1950, HE-EL-1860 | HE-EL-0130: FS, HE-EL-0250: FS, HE-EL-0310: FS, HE-EL-0190: FS, HE-EL-0730: FS, HE-EL-1870: FS, HE-EL-0170: FS, CAB-4450: FS, HE-EL-0290: FS, HE-EL-0830: FS, HE-EL-0770: FS, HE-EL-0650: FS, HE-EL-0710: FS, HE-EL-0350: FS, HE-EL-0230: FS, HE-EL-1950: FS, HE | 2023-11-08 | 2023-11-17
HE-EL-170 | Completed | P2543-R01-Oct24..1.EN.9.56 | Obtain Company Approval-Design Basis | HE-EL-150 | HE-EL-150: FS | HE-EL-160 | HE-EL-160: FS | 2023-10-02 | 2023-10-06
HE-EL-180 | Completed | P2543-R01-Oct24..1.EN.9.56 | Issue ICR-Design Basis | HE-DB-0010 | HE-DB-0010: FS | HE-EL-190, HE-EL-0670 | HE-EL-190: FS, HE-EL-0670: FS 10 | 2023-08-08 | 2023-08-23
HE-EL-190 | Completed | P2543-R01-Oct24..1.EN.9.56 | Receive Company Comments-Design Basis | HE-EL-180 | HE-EL-180: FS | HE-EL-150 | HE-EL-150: FS | 2023-08-24 | 2023-08-31
HE-EL-1860 | Completed | P2543-R01-Oct24..1.EN.9.31.2 | Final Issue for Design/ Construction-Data Sheet for AC UPS | HE-EL-1900, HE-DB-0010, HE-EL-160 | HE-EL-1900: FS, HE-DB-0010: FS, HE-EL-160: FS | CAB-4450, HE-EL-0950, C-56-591-01-EI-1600, C-52-598-06-EI-1210, C-52-598-06-EI-1400, C-52-598-05-EI-1210, C-52-598-05-EI-1400, C-52-598-04-EI-1210, C-52-598-04-EI-1400, C-52-598-03-EI-1210, C-52-598-03-EI-1400, C-52-598-02-EI-1210, C-52-598-02-EI-1400, C-5 | CAB-4450: FS, HE-EL-0950: FS, C-56-591-01-EI-1600: FS, C-52-598-06-EI-1210: FS, C-52-598-06-EI-1400: FS, C-52-598-05-EI-1210: FS, C-52-598-05-EI-1400: FS, C-52-598-04-EI-1210: FS, C-52-598-04-EI-1400: FS, C-52-598-03-EI-1210: FS, C-52-598-03-EI-1400: FS, C | 2024-02-02 | 2024-02-14
HE-EL-1870 | Completed | P2543-R01-Oct24..1.EN.9.31.2 | Issue ICR- Datasheet for AC UPS | HE-EL-0730, HE-DB-0010, HE-EL-160, HE-EL-0790 | HE-EL-0730: FF 3, HE-DB-0010: FS, HE-EL-160: FS, HE-EL-0790: FS | HE-EL-1880, HE-EL-1090 | HE-EL-1880: FS, HE-EL-1090: FS | 2023-10-10 | 2023-10-20
HE-EL-1880 | Completed | P2543-R01-Oct24..1.EN.9.31.2 | Receive Company Comments- Datasheet for AC UPS | HE-EL-1870 | HE-EL-1870: FS | HE-EL-1890 | HE-EL-1890: FS | 2023-10-20 | 2023-10-27
HE-EL-1890 | Completed | P2543-R01-Oct24..1.EN.9.31.2 | Re-Issue for Approval- Datasheet for AC UPS | HE-EL-1880 | HE-EL-1880: FS | HE-EL-1090, HE-EL-1900, HE-EL-1110 | HE-EL-1090: FS, HE-EL-1900: FS, HE-EL-1110: FS | 2024-01-29 | 2024-02-02
HE-EL-1900 | Completed | P2543-R01-Oct24..1.EN.9.31.2 | Obtain Company Approval- Datasheet for AC UPS | HE-EL-1890 | HE-EL-1890: FS | HE-EL-1860 | HE-EL-1860: FS | 2024-01-29 | 2024-02-02
HE-EL-1910 | Completed | P2543-R01-Oct24..1.EN.9.31.3 | Issue ICR-Data Sheet for HV cables | HE-EL-0610 | HE-EL-0610: SS | HE-EL-1150, HE-EL-1920, HE-EL-1960, HE-EL-2010, HE-EL-2060, HE-EL-2110, HE-EL-2160, HE-EL-0790 | HE-EL-1150: FS, HE-EL-1920: FS 15, HE-EL-1960: FS, HE-EL-2010: FS, HE-EL-2060: FS, HE-EL-2110: FS, HE-EL-2160: FS, HE-EL-0790: FS | 2023-11-05 | 2023-11-27
HE-EL-1920 | Completed | P2543-R01-Oct24..1.EN.9.31.3 | Receive Company Comments-Data Sheet for HV cables | HE-EL-1910 | HE-EL-1910: FS 15 | HE-EL-1930 | HE-EL-1930: FS | 2023-11-28 | 2023-11-29
HE-EL-1930 | Completed | P2543-R01-Oct24..1.EN.9.31.3 | Re-Issue for Approval-Data Sheet for HV cables | HE-EL-1920 | HE-EL-1920: FS | HE-EL-1940 | HE-EL-1940: FS | 2023-12-01 | 2023-12-06
HE-EL-1940 | Completed | P2543-R01-Oct24..1.EN.9.31.3 | Obtain Company Approval-Data Sheet for HV cables | HE-EL-1930 | HE-EL-1930: FS | HE-EL-1950 | HE-EL-1950: FS | 2023-12-07 | 2023-12-14
HE-EL-1950 | Completed | P2543-R01-Oct24..1.EN.9.31.3 | Final Issue for Design/ Construction-Data Sheet for HV cables | HE-EL-1940, HE-DB-0010, HE-EL-160 | HE-EL-1940: FS, HE-DB-0010: FS, HE-EL-160: FS | CAB-4450, HE-EL-2050, HE-EL-2100, HE-EL-2150, HE-EL-2200, HE-EL-0830, C-56-PL-607-EI-2000, C-56-EB2-EI-1200, C-56-EB2-EI-1210, C-56-EB2-EI-1220, C-56-PR-838-CA-1000, C-56-PR-838-CA-1030, C-56-PR-838-EI-2000, C-56-PR-838-EI-2010, C-56-PR-838-EI-2040, C-56-5 | CAB-4450: FS, HE-EL-2050: FS, HE-EL-2100: FS, HE-EL-2150: FS, HE-EL-2200: FS, HE-EL-0830: FS, C-56-PL-607-EI-2000: FS, C-56-EB2-EI-1200: FS, C-56-EB2-EI-1210: FS, C-56-EB2-EI-1220: FS, C-56-PR-838-CA-1000: FS, C-56-PR-838-CA-1030: FS, C-56-PR-838-EI-2000: | 2023-12-15 | 2024-01-16
HE-EL-1960 | Completed | P2543-R01-Oct24..1.EN.9.1.1 | Issue ICR-Material Requisition for LV Switchgear | HE-EL-1090, HE-EL-0790, HE-EL-0430, HE-EL-1910 | HE-EL-1090: FS, HE-EL-0790: FS, HE-EL-0430: FS, HE-EL-1910: FS | HE-EL-2060, HP-ME-1330, HE-EL-1970, HP-BK-0210 | HE-EL-2060: FS, HP-ME-1330: FS, HE-EL-1970: FS, HP-BK-0210: FS | 2024-05-10 | 2024-05-22
HE-EL-1970 | Completed | P2543-R01-Oct24..1.EN.9.1.1 | Receive Company Comments-Material Requisition for LV Switchgear | HE-EL-1960 | HE-EL-1960: FS | HE-EL-1980 | HE-EL-1980: FS | 2024-05-29 07:30 | 2024-05-30 17:30
HE-EL-1980 | Completed | P2543-R01-Oct24..1.EN.9.1.1 | Re-Issue for Approval-Material Requisition for LV Switchgear | HE-EL-1970, HE-EL-0450 | HE-EL-1970: FS, HE-EL-0450: FS | HE-EL-1990 | HE-EL-1990: FS | 2024-10-01 07:30 | 2024-10-07 17:30
HE-EL-1990 | Completed | P2543-R01-Oct24..1.EN.9.1.1 | Obtain Company Approval-Material Requisition for LV Switchgear | HE-EL-1980 | HE-EL-1980: FS | HE-EL-2000 | HE-EL-2000: FS | 2024-10-08 07:30 | 2024-10-14 17:30
HE-EL-2000 | In Progress | P2543-R01-Oct24..1.EN.9.1.1 | Final Issue for Design/ Construction-Material Requisition for LV Switchgear | HE-EL-0470, HE-EL-1990 | HE-EL-0470: FF, HE-EL-1990: FS | HM-EL-0020, CAB-4450, HE-EL-2250 | HM-EL-0020: SS, CAB-4450: FS, HE-EL-2250: FS | 2024-10-15 07:30 | 2024-11-08 17:30
HE-EL-2010 | Completed | P2543-R01-Oct24..1.EN.9.1.2 | Issue ICR-Material Requisition for Glanding & Termination | HE-EL-2110, HE-EL-0430, HE-EL-0790, HE-EL-0430, HE-EL-1910 | HE-EL-2110: SS, HE-EL-0430: FF, HE-EL-0790: FS, HE-EL-0430: FS, HE-EL-1910: FS | HE-EL-2020, HP-BK-550 | HE-EL-2020: FS, HP-BK-550: FS | 2024-05-06 07:30 | 2024-06-17 17:30
HE-EL-2020 | Completed | P2543-R01-Oct24..1.EN.9.1.2 | Receive Company Comments-Material Requisition for Glanding & Termination | HE-EL-2010 | HE-EL-2010: FS | HE-EL-2030 | HE-EL-2030: FS | 2024-06-18 | 2024-06-28 17:30
HE-EL-2030 | Completed | P2543-R01-Oct24..1.EN.9.1.2 | Re-Issue for Approval-Material Requisition for Glanding & Termination | HE-EL-2020, HE-EL-0450 | HE-EL-2020: FS, HE-EL-0450: FS | HE-EL-2040 | HE-EL-2040: FS | 2024-06-28 | 2024-07-08 17:30
HE-EL-2040 | Completed | P2543-R01-Oct24..1.EN.9.1.2 | Obtain Company Approval-Material Requisition for Glanding & Termination | HE-EL-2030 | HE-EL-2030: FS | HE-EL-2050 | HE-EL-2050: FS | 2024-07-09 07:30 | 2024-07-19 17:30
HE-EL-2050 | Completed | P2543-R01-Oct24..1.EN.9.1.2 | Final Issue for Design/ Construction-Material Requisition for Glanding & Termination | HE-EL-2040, HE-EL-1950 | HE-EL-2040: FS, HE-EL-1950: FS | HM-EL-0020, CAB-4450, HE-EL-2400 | HM-EL-0020: FS, CAB-4450: FS, HE-EL-2400: FS | 2024-07-20 07:30 | 2024-07-31 17:30
HE-EL-2060 | Completed | P2543-R01-Oct24..1.EN.9.1.3 | Issue ICR-Material Requisition for MOV Isolator | HE-EL-1960, HE-EL-0790, HE-EL-0430, HE-EL-1910 | HE-EL-1960: FS, HE-EL-0790: FS, HE-EL-0430: FS, HE-EL-1910: FS | HE-EL-2110, HE-EL-2070 | HE-EL-2110: FS, HE-EL-2070: FS | 2024-04-16 | 2024-04-25
HE-EL-2070 | Completed | P2543-R01-Oct24..1.EN.9.1.3 | Receive Company Comments-Material Requisition for MOV Isolator | HE-EL-2060 | HE-EL-2060: FS | HE-EL-2080 | HE-EL-2080: FS | 2024-04-26 | 2024-05-09
HE-EL-2080 | Completed | P2543-R01-Oct24..1.EN.9.1.3 | Re-Issue for Approval-Material Requisition for MOV Isolator | HE-EL-2070, HE-EL-0450 | HE-EL-2070: FS, HE-EL-0450: FS | HE-EL-2090 | HE-EL-2090: FS | 2024-05-10 | 2024-05-23
HE-EL-2090 | Completed | P2543-R01-Oct24..1.EN.9.1.3 | Obtain Company Approval-Material Requisition for MOV Isolator | HE-EL-2080 | HE-EL-2080: FS | HE-EL-2100 | HE-EL-2100: FS | 2024-05-24 | 2024-06-06
HE-EL-2100 | Completed | P2543-R01-Oct24..1.EN.9.1.3 | Final Issue for Design/ Construction-Material Requisition for MOV Isolator | HE-EL-2090, HE-EL-1950 | HE-EL-2090: FS, HE-EL-1950: FS | HM-EL-0020, CAB-4450, HE-EL-2300 | HM-EL-0020: FS, CAB-4450: FS, HE-EL-2300: FS | 2024-06-20 07:30 | 2024-07-05 17:30
HE-EL-2110 | Completed | P2543-R01-Oct24..1.EN.9.1.4 | Issue ICR-Material Requisition for Electrical Bulks | HE-EL-2060, HE-EL-0790, HE-EL-0430, HE-EL-1910 | HE-EL-2060: FS, HE-EL-0790: FS, HE-EL-0430: FS, HE-EL-1910: FS | HE-EL-2010, HE-EL-2120 | HE-EL-2010: SS, HE-EL-2120: FS | 2024-05-24 | 2024-05-31
HE-EL-2120 | Completed | P2543-R01-Oct24..1.EN.9.1.4 | Receive Company Comments-Material Requisition for Electrical Bulks | HE-EL-2110 | HE-EL-2110: FS | HE-EL-2130 | HE-EL-2130: FS | 2024-05-31 | 2024-06-07
HE-EL-2130 | Completed | P2543-R01-Oct24..1.EN.9.1.4 | Re-Issue for Approval-Material Requisition for Electrical Bulks | HE-EL-2120, HE-EL-0450 | HE-EL-2120: FS, HE-EL-0450: FS | HE-EL-2140 | HE-EL-2140: FS | 2024-06-07 | 2024-06-14
HE-EL-2140 | Completed | P2543-R01-Oct24..1.EN.9.1.4 | Obtain Company Approval-Material Requisition for Electrical Bulks | HE-EL-2130 | HE-EL-2130: FS | HE-EL-2150 | HE-EL-2150: FS | 2024-06-14 | 2024-06-21
HE-EL-2150 | Completed | P2543-R01-Oct24..1.EN.9.1.4 | Final Issue for Design/ Construction-Material Requisition for Electrical Bulks | HE-EL-2140, HE-EL-1950 | HE-EL-2140: FS, HE-EL-1950: FS | HM-EL-0020, CAB-4450, HE-EL-2450 | HM-EL-0020: FS, CAB-4450: FS, HE-EL-2450: FS | 2024-06-28 07:30 | 2024-07-05 17:30
HE-EL-2160 | Completed | P2543-R01-Oct24..1.EN.9.1.5 | Issue ICR-Material Requisition for Modification Works | HE-EL-0790, HE-EL-0430, HE-EL-1910 | HE-EL-0790: FS, HE-EL-0430: FS, HE-EL-1910: FS | HE-EL-2170 | HE-EL-2170: FS | 2024-03-01 | 2024-03-24
HE-EL-2170 | Completed | P2543-R01-Oct24..1.EN.9.1.5 | Receive Company Comments-Material Requisition for Modification Works | HE-EL-2160 | HE-EL-2160: FS | HE-EL-2180 | HE-EL-2180: FS | 2024-03-31 | 2024-04-18
HE-EL-2180 | Completed | P2543-R01-Oct24..1.EN.9.1.5 | Re-Issue for Approval-Material Requisition for Modification Works | HE-EL-2170, HE-EL-0450 | HE-EL-2170: FS, HE-EL-0450: FS | HE-EL-2190 | HE-EL-2190: FS | 2024-04-19 | 2024-04-24
HE-EL-2190 | Completed | P2543-R01-Oct24..1.EN.9.1.5 | Obtain Company Approval-Material Requisition for Modification Works | HE-EL-2180 | HE-EL-2180: FS | HE-EL-2200 | HE-EL-2200: FS | 2024-04-24 | 2024-05-07
HE-EL-2200 | Completed | P2543-R01-Oct24..1.EN.9.1.5 | Final Issue for Design/ Construction-Material Requisition for Modification Works | HE-EL-2190, HE-EL-1950 | HE-EL-2190: FS, HE-EL-1950: FS | HM-EL-0020, CAB-4450, HE-EL-2350 | HM-EL-0020: FS, CAB-4450: FS, HE-EL-2350: FS | 2024-06-13 | 2024-06-20
HE-EL-2210 | Completed | P2543-R01-Oct24..1.EN.9.6.1 | Issue ICR-TBE for LV Switchgear | HP-ME-1330 | HP-ME-1330: FS | HP-ME-1350, HE-EL-2220, HP-BK-0220 | HP-ME-1350: FS, HE-EL-2220: FS, HP-BK-0220: SS | 2024-05-24 | 2024-10-01
HE-EL-2220 | Completed | P2543-R01-Oct24..1.EN.9.6.1 | Receive Company Comments-TBE for LV Switchgear | HE-EL-2210 | HE-EL-2210: FS | HE-EL-2230, HP-ME-1350 | HE-EL-2230: FS, HP-ME-1350: FF | 2024-10-11 | 2024-10-18
HE-EL-2230 | Not Started | P2543-R01-Oct24..1.EN.9.6.1 | Re-Issue for Approval-TBE for LV Switchgear | HE-EL-2220 | HE-EL-2220: FS | HE-EL-2240 | HE-EL-2240: FS | 2024-10-28 07:30 | 2024-11-01 17:30
HE-EL-2240 | Not Started | P2543-R01-Oct24..1.EN.9.6.1 | Obtain Company Approval-TBE for LV Switchgear | HE-EL-2230 | HE-EL-2230: FS | HE-EL-2250 | HE-EL-2250: FS | 2024-11-04 07:30 | 2024-11-15 17:30
HE-EL-2250 | Not Started | P2543-R01-Oct24..1.EN.9.6.1 | Final Issue for Design/ Construction-TBE for LV Switchgear | HE-EL-2240, HE-EL-2000 | HE-EL-2240: FS, HE-EL-2000: FS | CAB-4450, HP-BK-0230 | CAB-4450: FS, HP-BK-0230: FS | 2024-11-18 07:30 | 2024-11-22 17:30
HE-EL-2260 | Completed | P2543-R01-Oct24..1.EN.9.6.2 | Issue ICR-TBE for MOV Isolator | HP-BK-0010 | HP-BK-0010: FS | HE-EL-2270 | HE-EL-2270: FS | 2024-05-24 | 2024-06-17
HE-EL-2270 | Completed | P2543-R01-Oct24..1.EN.9.6.2 | Receive Company Comments-TBE for MOV Isolator | HE-EL-2260 | HE-EL-2260: FS | HE-EL-2280 | HE-EL-2280: FS | 2024-06-18 07:30 | 2024-07-01 17:30
HE-EL-2280 | Completed | P2543-R01-Oct24..1.EN.9.6.2 | Re-Issue for Approval-TBE for MOV Isolator | HE-EL-2270 | HE-EL-2270: FS | HE-EL-2290 | HE-EL-2290: FS | 2024-07-02 07:30 | 2024-07-15 17:30
HE-EL-2290 | Completed | P2543-R01-Oct24..1.EN.9.6.2 | Obtain Company Approval-TBE for MOV Isolator | HE-EL-2280 | HE-EL-2280: FS | HE-EL-2300 | HE-EL-2300: FS | 2024-07-16 07:30 | 2024-07-29 17:30
HE-EL-2300 | Completed | P2543-R01-Oct24..1.EN.9.6.2 | Final Issue for Design/ Construction-TBE for MOV Isolator | HE-EL-2290, HE-EL-2100 | HE-EL-2290: FS, HE-EL-2100: FS | CAB-4450 | CAB-4450: FS | 2024-09-02 07:30 | 2024-09-11 17:30
HE-EL-2310 | Completed | P2543-R01-Oct24..1.EN.9.6.3 | Issue ICR-TBE for Modification Works | HP-BK-0010 | HP-BK-0010: FS | HE-EL-2320 | HE-EL-2320: FS | 2024-05-13 | 2024-06-03
HE-EL-2320 | Completed | P2543-R01-Oct24..1.EN.9.6.3 | Receive Company Comments-TBE for Modification Works | HE-EL-2310 | HE-EL-2310: FS | HE-EL-2330 | HE-EL-2330: FS | 2024-06-03 | 2024-06-08
HE-EL-2330 | Completed | P2543-R01-Oct24..1.EN.9.6.3 | Re-Issue for Approval-TBE for Modification Works | HE-EL-2320 | HE-EL-2320: FS | HE-EL-2340 | HE-EL-2340: FS | 2024-06-09 | 2024-06-14
HE-EL-2340 | Completed | P2543-R01-Oct24..1.EN.9.6.3 | Obtain Company Approval-TBE for Modification Works | HE-EL-2330 | HE-EL-2330: FS | HE-EL-2350 | HE-EL-2350: FS | 2024-06-14 | 2024-06-15
HE-EL-2350 | Completed | P2543-R01-Oct24..1.EN.9.6.3 | Final Issue for Design/ Construction-TBE for Modification Works | HE-EL-2340, HE-EL-2200 | HE-EL-2340: FS, HE-EL-2200: FS | CAB-4450 | CAB-4450: FS | 2024-06-21 07:30 | 2024-06-28 17:30
HE-EL-2360 | Completed | P2543-R01-Oct24..1.EN.9.6.5 | Issue ICR-TBE for Glanding & Termination | HP-BK-0010, HP-BK-550 | HP-BK-0010: FS, HP-BK-550: FS | HE-EL-2370, HP-BK-540 | HE-EL-2370: FS, HP-BK-540: FF | 2024-08-01 07:30 | 2024-08-08 17:30
HE-EL-2370 | Completed | P2543-R01-Oct24..1.EN.9.6.5 | Receive Company Comments-TBE for Glanding & Termination | HE-EL-2360 | HE-EL-2360: FS | HE-EL-2380 | HE-EL-2380: FS | 2024-08-09 07:30 | 2024-08-15 17:30
HE-EL-2380 | Completed | P2543-R01-Oct24..1.EN.9.6.5 | Re-Issue for Approval-TBE for Glanding & Termination | HE-EL-2370 | HE-EL-2370: FS | HE-EL-2390 | HE-EL-2390: FS | 2024-10-01 07:30 | 2024-10-07 17:30
HE-EL-2390 | Completed | P2543-R01-Oct24..1.EN.9.6.5 | Obtain Company Approval-TBE for Glanding & Termination | HE-EL-2380 | HE-EL-2380: FS | HE-EL-2400 | HE-EL-2400: FS | 2024-10-08 07:30 | 2024-10-14 17:30
HE-EL-2400 | In Progress | P2543-R01-Oct24..1.EN.9.6.5 | Final Issue for Design/ Construction-TBE for Glanding & Termination | HE-EL-2390, HE-EL-2050 | HE-EL-2390: FS, HE-EL-2050: FS | CAB-4450 | CAB-4450: FS | 2024-10-15 07:30 | 2024-11-01 17:30
HE-EL-2410 | Completed | P2543-R01-Oct24..1.EN.9.6.4 | Issue ICR-TBE for Electrical Bulks | HP-BK-0010 | HP-BK-0010: FS | HE-EL-2420, HP-BK-0170 | HE-EL-2420: FS, HP-BK-0170: SS | 2024-05-09 | 2024-06-13
HE-EL-2420 | Completed | P2543-R01-Oct24..1.EN.9.6.4 | Receive Company Comments-TBE for Electrical Bulks | HE-EL-2410 | HE-EL-2410: FS | HE-EL-2430 | HE-EL-2430: FS | 2024-06-14 07:30 | 2024-06-29 17:30
HE-EL-2430 | Completed | P2543-R01-Oct24..1.EN.9.6.4 | Re-Issue for Approval-TBE for Electrical Bulks | HE-EL-2420 | HE-EL-2420: FS | HE-EL-2440 | HE-EL-2440: FS | 2024-06-30 07:30 | 2024-07-13 17:30
HE-EL-2440 | Completed | P2543-R01-Oct24..1.EN.9.6.4 | Obtain Company Approval-TBE for Electrical Bulks | HE-EL-2430 | HE-EL-2430: FS | HE-EL-2450, HP-BK-0170 | HE-EL-2450: FS, HP-BK-0170: FF | 2024-07-14 07:30 | 2024-07-27 17:30
HE-EL-2450 | Completed | P2543-R01-Oct24..1.EN.9.6.4 | Final Issue for Design/ Construction-TBE for Electrical Bulks | HE-EL-2440, HE-EL-2150 | HE-EL-2440: FS, HE-EL-2150: FS | CAB-4450, HP-BK-0180 | CAB-4450: FS, HP-BK-0180: FS | 2024-09-30 07:30 | 2024-10-04 17:30
HE-IC-580 | Completed | P2543-R01-Oct24..1.EN.6.3 | Receive Company Comments- I&C Design Basis | HE-IC-620 | HE-IC-620: FS | HE-IC-590 | HE-IC-590: FS | 2023-09-06 | 2023-09-16
HE-IC-590 | Completed | P2543-R01-Oct24..1.EN.6.3 | Re-Issue for Approval- I&C Design Basis | HE-IC-580 | HE-IC-580: FS | HE-IC-600 | HE-IC-600: FS | 2023-09-17 | 2023-09-30
HE-IC-600 | Completed | P2543-R01-Oct24..1.EN.6.3 | Obtain Company Approval- I&C Design Basis | HE-IC-590 | HE-IC-590: FS | HE-IC-610 | HE-IC-610: FS | 2023-10-02 | 2023-10-09
HE-IC-610 | Completed | P2543-R01-Oct24..1.EN.6.3 | Final Issue for Design/ Construction- I&C Design Basis | HE-IC-600 | HE-IC-600: FS | HE-ME-0110, HE-ME-0170, CAB-4430, HE-PR-0470, HE-ME-520, HE-IC-0050 | HE-ME-0110: FS, HE-ME-0170: FS, CAB-4430: FS, HE-PR-0470: FS, HE-ME-520: FS, HE-IC-0050: FS | 2023-11-09 | 2023-11-22
HE-IC-620 | Completed | P2543-R01-Oct24..1.EN.6.3 | Issue ICR- I&C Design Basis | HE-DB-0010, ML1002 | HE-DB-0010: FS 5, ML1002: SS | CAB-4460, HE-IC-1190, HE-IC-1150, HP-ME-0860, HE-ME-0070, HE-IC-580, HE-ME-0130, HE-ME-480, HE-IC-0010, HE-IC-0070, HE-IC-0250, HS-GN-0310, HE-TL-0550, HE-TL-0190, HE-TL-0510, HE-TL-0570, HE-TL-0230, CAB-4470, ML1033-B22 | CAB-4460: FS, HE-IC-1190: FS, HE-IC-1150: FS, HP-ME-0860: FS, HE-ME-0070: SS, HE-IC-580: FS, HE-ME-0130: SS, HE-ME-480: SS, HE-IC-0010: FS, HE-IC-0070: FS, HE-IC-0250: FS, HS-GN-0310: SS, HE-TL-0550: SS, HE-TL-0190: FS, HE-TL-0510: SS, HE-TL-0570: SS, HE-T | 2023-08-14 | 2023-09-05
HE-TL-2460 | Completed | P2543-R01-Oct24..1.EN.10.56 | Re-Issue for Approval-Design Basis | HE-TL-2500 | HE-TL-2500: FS | HE-TL-2480 | HE-TL-2480: FS | 2023-09-17 | 2023-10-09
HE-TL-2470 | Completed | P2543-R01-Oct24..1.EN.10.56 | Final Issue for Design/ Construction-Design Basis | HE-TL-2480 | HE-TL-2480: FS | HE-TL-0410, HE-TL-0350, HE-TL-0590, CAB-4470, HE-TL-0830, HE-TL-0470, HE-TL-0530, ML1033-B22, HE-TL-0290, HE-TL-1050, HE-TL-0230 | HE-TL-0410: FS, HE-TL-0350: FS, HE-TL-0590: FS, CAB-4470: FS, HE-TL-0830: FS, HE-TL-0470: FS, HE-TL-0530: FS, ML1033-B22: FS, HE-TL-0290: FS, HE-TL-1050: FS, HE-TL-0230: FS | 2023-11-07 | 2023-11-13
HE-TL-2480 | Completed | P2543-R01-Oct24..1.EN.10.56 | Obtain Company Approval-Design Basis | HE-TL-2460 | HE-TL-2460: FS | HE-TL-2470 | HE-TL-2470: FS | 2023-10-10 | 2023-10-17
HE-TL-2490 | Completed | P2543-R01-Oct24..1.EN.10.56 | Issue ICR-Design Basis | HE-DB-0030 | HE-DB-0030: FS 2 | HE-TL-2500 | HE-TL-2500: FS | 2023-08-20 | 2023-09-04
HE-TL-2500 | Completed | P2543-R01-Oct24..1.EN.10.56 | Receive Company Comments-Design Basis | HE-TL-2490 | HE-TL-2490: FS | HE-TL-2460 | HE-TL-2460: FS | 2023-09-05 | 2023-09-16
HE-TL-890 | Completed | P2543-R01-Oct24..1.EN.10.3 | Issue ICR-Telecom Typical Hookup | HE-TL-0790 | HE-TL-0790: FS | HE-TL-900 | HE-TL-900: FS | 2024-08-12 07:30 | 2024-09-13 17:30
HE-TL-900 | Completed | P2543-R01-Oct24..1.EN.10.3 | Receive Company Comments-Telecom Typical Hookup | HE-TL-890 | HE-TL-890: FS | HE-TL-910 | HE-TL-910: FS | 2024-09-16 07:30 | 2024-09-25 17:30
HE-TL-910 | Completed | P2543-R01-Oct24..1.EN.10.3 | Re-Issue for Approval-Telecom Typical Hookup | HE-TL-0810, HE-TL-0750, HE-TL-900, HE-TL-0690, HE-TL-0630 | HE-TL-0810: SS, HE-TL-0750: SS, HE-TL-900: FS, HE-TL-0690: SS, HE-TL-0630: FS | HE-TL-920 | HE-TL-920: FS | 2024-09-26 | 2024-10-25 07:30
HE-TL-920 | In Progress | P2543-R01-Oct24..1.EN.10.3 | Obtain Company Approval-Telecom Typical Hookup | HE-TL-910 | HE-TL-910: FS | HE-TL-930, HE-TL-0890 | HE-TL-930: FS, HE-TL-0890: FS | 2024-10-25 07:30 | 2024-11-08 17:30
HE-TL-930 | Not Started | P2543-R01-Oct24..1.EN.10.3 | Final Issue for Design/ Construction-Telecom Typical Hookup | HE-TL-0830, HE-TL-0770, HE-TL-920, HE-TL-0710 | HE-TL-0830: FS, HE-TL-0770: FS, HE-TL-920: FS, HE-TL-0710: FS | ML1219-B29, CAB-4470, HP-BK-0510 | ML1219-B29: FF, CAB-4470: FS, HP-BK-0510: FF | 2024-11-11 07:30 | 2024-12-17 17:30
HE-WS-0070 | Completed | P2543-R01-Oct24..1.PM.12 | Lesson Learned Workshop | ML1002 | ML1002: SS 45 | HE-WS-0010 | HE-WS-0010: FS 15 | 2023-08-31 | 2023-08-31
HE-WS-0090 | Completed | P2543-R01-Oct24..1.PM.12 | Plot Plan Layout Review Workshop | HE-PI-0320, HE-PI-0390, HE-PI-0460, HE-PI-0530 | HE-PI-0320: FS, HE-PI-0390: FS, HE-PI-0460: FS, HE-PI-0530: FS | HE-EL-0490, HE-WS-0030 | HE-EL-0490: FS, HE-WS-0030: FS | 2023-10-24 | 2023-10-25
HE-WS-0170 | Not Started | P2543-R01-Oct24..1.PM.12 | SIMOPS Workshop | HE-WS-0200 | HE-WS-0200: FS 30 | HE-WS-0270 | HE-WS-0270: FS | 2024-10-28 07:30 | 2024-10-29 17:30
HE-WS-0190 | Completed | P2543-R01-Oct24..1.PM.12 | Bow Tie Workshop | HE-WS-0310 | HE-WS-0310: FS 2 | HE-HS-0490, HE-WS-0200 | HE-HS-0490: FS, HE-WS-0200: FS | 2023-11-23 | 2023-11-24
HE-WS-0200 | Completed | P2543-R01-Oct24..1.PM.12 | ALARP Workshop | HE-WS-0190, HE-RR-0050 | HE-WS-0190: FS, HE-RR-0050: FS | HE-HS-0490, HE-WS-0170 | HE-HS-0490: FF, HE-WS-0170: FS 30 | 2023-11-23 | 2023-11-24
HE-WS-0210 | Completed | P2543-R01-Oct24..1.PM.12 | HAZOP Workshop | HE-PR-0040, HE-PR-1240, HE-PR-1250, HE-PR-0060, HE-WS-0030, HE-PR-0130, HE-HS-0230 | HE-PR-0040: FS, HE-PR-1240: FS, HE-PR-1250: FS, HE-PR-0060: FS, HE-WS-0030: FS, HE-PR-0130: FS 5, HE-HS-0230: FS | ML2059-B05, HE-WS-0310, HE-HS-0490, HE-HS-0670 | ML2059-B05: FF, HE-WS-0310: FS, HE-HS-0490: FS, HE-HS-0670: FS | 2023-11-21 | 2023-11-23
HE-WS-0270 | Not Started | P2543-R01-Oct24..1.PM.12 | PHSER III Workshop | ML2069-B09, HE-WS-0170 | ML2069-B09: FS 30, HE-WS-0170: FS | HE-WS-0280 | HE-WS-0280: FS | 2024-10-30 07:30 | 2024-10-31 17:30
HE-WS-0280 | Not Started | P2543-R01-Oct24..1.PM.12 | PHSER IV Workshop | HE-WS-0270 | HE-WS-0270: FS | HE-WS-0290 | HE-WS-0290: FS | 2024-11-01 07:30 | 2024-11-04 17:30
HE-WS-0290 | Not Started | P2543-R01-Oct24..1.PM.12 | PHSER V Workshop | CCM-PM4500, HE-WS-0280 | CCM-PM4500: FS, HE-WS-0280: FS | ML1060, ML1090 | ML1060: FF, ML1090: FF | 2025-07-08 13:00 | 2025-07-10 12:00
HE-WS-0310 | Completed | P2543-R01-Oct24..1.PM.12 | CRAS Workshop | HE-WS-0210, HE-CP-0030, HE-CP-220 | HE-WS-0210: FS, HE-CP-0030: FS, HE-CP-220: FS | HE-WS-0190 | HE-WS-0190: FS 2 | 2023-11-23 | 2023-11-24
HE-PL-3430 | Completed | P2543-R01-Oct24..1.EN.1.9.1 | Re-Issue for Approval - MR for Anchor Flanges | HE-PL-3470 | HE-PL-3470: FS | HE-PL-3440 | HE-PL-3440: FS | 2024-06-13 07:30 | 2024-06-26 17:30
HE-PL-3440 | Completed | P2543-R01-Oct24..1.EN.1.9.1 | Obtain Company Approval - MR for Anchor Flanges | HE-PL-3430 | HE-PL-3430: FS | HE-PL-3450 | HE-PL-3450: FS | 2024-06-27 07:30 | 2024-07-21 17:30
HE-PL-3450 | In Progress | P2543-R01-Oct24..1.EN.1.9.1 | Final Issue for Design/ Construction-MR for Anchor Flanges | HE-PL-3440, HE-PL-1550 | HE-PL-3440: FS, HE-PL-1550: FF 10 | ML1219-B29, HE-PL-3520 | ML1219-B29: FF, HE-PL-3520: FS | 2024-07-22 07:30 | 2024-11-29 17:30
HE-PL-3460 | Completed | P2543-R01-Oct24..1.EN.1.9.1 | Issue ICR - MR for Anchor Flanges | HE-PL-1510 | HE-PL-1510: FS | HE-PL-3470, HE-PL-3480, HP-ME-1310 | HE-PL-3470: FS, HE-PL-3480: FS, HP-ME-1310: FS | 2024-02-26 | 2024-04-06
HE-PL-3470 | Completed | P2543-R01-Oct24..1.EN.1.9.1 | Receive Company Comments - MR for Anchor Flanges | HE-PL-3460 | HE-PL-3460: FS | HE-PL-3430 | HE-PL-3430: FS | 2024-04-08 07:30 | 2024-06-12 17:30
HE-PL-3480 | Completed | P2543-R01-Oct24..1.EN.1.10.1 | Issue ICR - TBE for Anchor Flanges | HE-PL-3460 | HE-PL-3460: FS | HE-PL-3490, HP-ME-1320 | HE-PL-3490: FS, HP-ME-1320: SS | 2024-06-10 | 2024-06-14
HE-PL-3490 | Completed | P2543-R01-Oct24..1.EN.1.10.1 | Receive Company Comments - TBE for Anchor Flanges | HE-PL-3480 | HE-PL-3480: FS | HE-PL-3500 | HE-PL-3500: FS | 2024-06-15 07:30 | 2024-06-28 17:30
HE-PL-3500 | Completed | P2543-R01-Oct24..1.EN.1.10.1 | Re-Issue for Approval - TBE for Anchor Flanges | HE-PL-3490 | HE-PL-3490: FS | HE-PL-3510 | HE-PL-3510: FS | 2024-09-30 07:30 | 2024-10-17 17:30
HE-PL-3510 | Not Started | P2543-R01-Oct24..1.EN.1.10.1 | Obtain Company Approval - TBE for Anchor Flanges | HE-PL-3500 | HE-PL-3500: FS | HE-PL-3520 | HE-PL-3520: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HE-PL-3520 | Not Started | P2543-R01-Oct24..1.EN.1.10.1 | Final Issue for Design/ Construction-TBE for Anchor Flanges | HE-PL-3510, HE-PL-3450 | HE-PL-3510: FS, HE-PL-3450: FS | ML1219-B29 | ML1219-B29: FF | 2024-12-04 07:30 | 2024-12-16 17:30
HP-ME-1300 | Completed | P2543-R01-Oct24..1.1.1.4.1 | Commercial Clarifications & Placement of PO for Anchor Flanges | HP-ME-1320 | HP-ME-1320: FS | HM-PL-890 | HM-PL-890: FS | 2024-06-22 | 2024-07-01 17:30
HP-ME-1310 | Completed | P2543-R01-Oct24..1.1.1.4.1 | RFQ, Receipt of Bid for Anchor Flanges | HE-PL-3460 | HE-PL-3460: FS | ML1549-D32, HP-ME-1320 | ML1549-D32: FF, HP-ME-1320: FS | 2024-04-15 | 2024-05-10
HP-ME-1320 | Completed | P2543-R01-Oct24..1.1.1.4.1 | Prepare TBE and Company approval for Anchor Flanges | HP-ME-1310, HE-PL-3480 | HP-ME-1310: FS, HE-PL-3480: SS | HP-ME-1300 | HP-ME-1300: FS | 2024-06-14 | 2024-06-21
HM-PL-890 | Completed | P2543-R01-Oct24..PR.1.4.2 | Vendor Document Review of Anchor Flanges | HP-ME-1300 | HP-ME-1300: FS | HM-PL-900 | HM-PL-900: FS | 2024-07-02 08:00 | 2024-08-23 18:00
HM-PL-900 | In Progress | P2543-R01-Oct24..PR.1.4.2 | Manufacturing & Assembly of Anchor Flanges | HM-PL-890 | HM-PL-890: FS | HM-PL-930, HM-PL-950 | HM-PL-930: FS, HM-PL-950: FS | 2024-08-16 08:00 | 2025-01-08 18:00
HM-PL-910 | Not Started | P2543-R01-Oct24..PR.1.4.2 | Packaging & Final Inspection-Anchor Flanges | HM-PL-930 | HM-PL-930: FS | HM-PL-920 | HM-PL-920: FS | 2025-01-23 08:00 | 2025-01-29 18:00
HM-PL-920 | Not Started | P2543-R01-Oct24..PR.1.4.2 | Ready for Dispatch of Anchor Flanges | HM-PL-910 | HM-PL-910: FS | HM-PL-950, HM-PL-1540 | HM-PL-950: FS, HM-PL-1540: FS 21 | 2025-01-30 08:00 | 2025-02-02 18:00
HM-PL-930 | Not Started | P2543-R01-Oct24..PR.1.4.2 | Testing and Inspection of Anchor Flanges | HM-PL-900 | HM-PL-900: FS | HM-PL-910 | HM-PL-910: FS | 2025-01-09 08:00 | 2025-01-22 18:00
HM-PL-940 | Not Started | P2543-R01-Oct24..PR.1.4.3 | Receipt at site and inspection of Anchor Flanges (Lot 1) | HM-PL-950 | HM-PL-950: FS | ML1549-D32, C-56-PL-607-CI-1510, C-56-PR-838-CI-1510 | ML1549-D32: FF, C-56-PL-607-CI-1510: FS, C-56-PR-838-CI-1510: FS | 2025-02-24 07:00 | 2025-03-05 15:00
HM-PL-950 | Not Started | P2543-R01-Oct24..PR.1.4.3 | Transportation/ Custom Clearance/ Delivery at site of Anchor Flanges (Lot 1) | HM-PL-920, HM-PL-900 | HM-PL-920: FS, HM-PL-900: FS | HM-PL-940 | HM-PL-940: FS | 2025-02-03 08:00 | 2025-02-23 18:00
HP-BK-510 | Completed | P2543-R01-Oct24..1.1.BK.2.1 | Final Piping Special Items MTO | HP-BK-520 | HP-BK-520: FS | HM-PI-50 | HM-PI-50: FS | 2024-08-17 07:30 | 2024-08-30 17:30
HP-BK-520 | Completed | P2543-R01-Oct24..1.1.BK.2.1 | 1st Piping Special Items MTO | HE-PI-1260 | HE-PI-1260: FS | HM-PI-60, HP-BK-510 | HM-PI-60: FS, HP-BK-510: FS | 2024-07-29 07:30 | 2024-08-16 17:30
HM-PI-50 | Not Started | P2543-R01-Oct24..PR.BK.2.2 | Final Piping Special Items MTO | HP-BK-510 | HP-BK-510: FS | HM-PI-70 | HM-PI-70: FS | 2024-10-26 08:00 | 2025-03-14 18:00
HM-PI-60 | Not Started | P2543-R01-Oct24..PR.BK.2.2 | 1st Piping Special Items MTO | HP-BK-520 | HP-BK-520: FS | HM-PI-80 | HM-PI-80: FS 1 | 2024-10-26 08:00 | 2025-03-04 18:00
HM-PI-70 | Not Started | P2543-R01-Oct24..PR.BK.2.3 | Final Piping Special Items MTO | HM-PI-80, HM-PI-50, HM-PI-80 | HM-PI-80: FF 8, HM-PI-50: FS, HM-PI-80: SS 7 | ML1549-D32, C-52-598-06-PI-1000, C-52-598-06-PI-1200 | ML1549-D32: FF 199, C-52-598-06-PI-1000: FS, C-52-598-06-PI-1200: FS | 2025-03-15 08:00 | 2025-03-29 18:00
HM-PI-80 | Not Started | P2543-R01-Oct24..PR.BK.2.3 | 1st Piping Special Items MTO | HM-PI-60 | HM-PI-60: FS 1 | HM-PI-70, HM-PI-70 | HM-PI-70: FF 8, HM-PI-70: SS 7 | 2025-03-06 08:00 | 2025-03-20 18:00
HP-BK-530 | Completed | P2543-R01-Oct24..1.1.BK.3.1 | Commercial Clarifications & Placement of PO for Cable Gland & Termination | HP-BK-540 | HP-BK-540: FS | HM-EL-530 | HM-EL-530: FS | 2024-09-03 07:30 | 2024-09-13 17:30
HP-BK-540 | Completed | P2543-R01-Oct24..1.1.BK.3.1 | Prepare TBE and Company approval for Cable Gland & Termination | HP-BK-550, HE-EL-2360 | HP-BK-550: FS, HE-EL-2360: FF | HP-BK-530 | HP-BK-530: FS | 2024-08-26 07:30 | 2024-09-02 17:30
HP-BK-550 | Completed | P2543-R01-Oct24..1.1.BK.3.1 | RFQ, Receipt of Bid for Cable Gland & Termination | HE-EL-2010 | HE-EL-2010: FS | HP-BK-540, HE-EL-2360 | HP-BK-540: FS, HE-EL-2360: FS | 2024-08-12 07:30 | 2024-08-23 17:30
HM-EL-530 | Not Started | P2543-R01-Oct24..PR.BK.3.2 | Vendor Document Review of Cable Gland and Termination | HP-BK-530 | HP-BK-530: FS | HM-EL-540 | HM-EL-540: FS | 2024-10-26 08:00 | 2024-11-04 18:00
HM-EL-540 | Not Started | P2543-R01-Oct24..PR.BK.3.2 | Manufacturing & Assembly of Cable Gland and Termination | HM-EL-530 | HM-EL-530: FS | HM-EL-550, HM-EL-590 | HM-EL-550: FS, HM-EL-590: FS | 2024-11-05 08:00 | 2025-01-16 18:00
HM-EL-550 | Not Started | P2543-R01-Oct24..PR.BK.3.2 | Factory Acceptance Test of Cable Gland and Termination | HM-EL-540 | HM-EL-540: FS | HM-EL-560 | HM-EL-560: FS | 2025-01-17 08:00 | 2025-01-30 18:00
HM-EL-560 | Not Started | P2543-R01-Oct24..PR.BK.3.2 | Packaging & Final Inspection-Cable Gland and Termination | HM-EL-550 | HM-EL-550: FS | HM-EL-570 | HM-EL-570: FS | 2025-01-31 08:00 | 2025-02-06 18:00
HM-EL-570 | Not Started | P2543-R01-Oct24..PR.BK.3.2 | Ready for Dispatch of Cable Gland and Termination | HM-EL-560 | HM-EL-560: FS | HM-EL-660 | HM-EL-660: FS 21 | 2025-02-07 08:00 | 2025-02-10 18:00
HM-EL-580 | Not Started | P2543-R01-Oct24..PR.BK.3.3 | Receipt at site and inspection of Cable Gland and Termination (Lot 1) | HM-EL-590, HM-EL-590 | HM-EL-590: FF, HM-EL-590: FS | ML1549-D32, C-52-598-06-EI-2000, C-52-598-06-EI-2010 | ML1549-D32: FF, C-52-598-06-EI-2000: FS, C-52-598-06-EI-2010: FS | 2025-02-21 07:00 | 2025-03-02 13:00
HM-EL-590 | Not Started | P2543-R01-Oct24..PR.BK.3.3 | Transportation/ Custom Clearance/ Delivery at site of Cable Gland and Termination (Lot 1) | HM-EL-540 | HM-EL-540: FS | HM-EL-580, HM-EL-580 | HM-EL-580: FF, HM-EL-580: FS | 2025-01-17 08:00 | 2025-02-20 18:00
HE-PI-3530 | Completed | P2543-R01-Oct24..1.EN.7.8.6 | Issue ICR-MR for Piping Bulks | HE-PI-1320 | HE-PI-1320: FS | HE-PI-3540, HE-PI-1360, HE-PI-3680 | HE-PI-3540: FS, HE-PI-1360: FS, HE-PI-3680: SS 5 | 2023-12-12 | 2024-01-16
HE-PI-3540 | Completed | P2543-R01-Oct24..1.EN.7.8.6 | Receive Company Comments-MR for Piping Bulks | HE-PI-3530 | HE-PI-3530: FS | HE-PI-3550, HE-PI-1360 | HE-PI-3550: FS, HE-PI-1360: FS | 2024-01-17 | 2024-01-26
HE-PI-3550 | Completed | P2543-R01-Oct24..1.EN.7.8.6 | Re-Issue for Approval-MR for Piping Bulks | HE-PI-3540 | HE-PI-3540: FS | HE-PI-3560 | HE-PI-3560: FS | 2024-01-16 | 2024-04-25
HE-PI-3560 | Completed | P2543-R01-Oct24..1.EN.7.8.6 | Obtain Company Approval-MR for Piping Bulks | HE-PI-3550 | HE-PI-3550: FS | HE-PI-3570 | HE-PI-3570: FS | 2024-04-26 | 2024-05-16
HE-PI-3570 | Completed | P2543-R01-Oct24..1.EN.7.8.6 | Final Issue for Design/ Construction-Material Requisition for Piping Bulks & Special Items | HE-PI-3560 | HE-PI-3560: FS | HE-PI-1400, HE-PI-1450, HE-PI-1450, HE-PI-1260 | HE-PI-1400: FS, HE-PI-1450: FS, HE-PI-1450: FF, HE-PI-1260: FS | 2024-06-04 | 2024-06-14
HE-PR-0170 | Completed | P2543-R01-Oct24..1.EN.3.11 | Issues for Design Review | HE-PR-0120 | HE-PR-0120: FS | HE-PR-0240 | HE-PR-0240: FS | 2023-10-16 | 2023-10-23
HE-PR-0240 | Completed | P2543-R01-Oct24..1.EN.3.11 | Receive comments from Design Review | HE-PR-0170 | HE-PR-0170: FS | HE-PR-0130 | HE-PR-0130: FS | 2023-10-24 | 2023-10-27
HE-CS-1560 | Completed | P2543-R01-Oct24..1.EN.8.2 | Issued for Review - Civil / Structural Design Basis | HE-DB-0010 | HE-DB-0010: FS | HE-CS-0070, HE-CS-1570 | HE-CS-0070: FS, HE-CS-1570: FS | 2023-08-23 | 2023-08-30
HE-CS-1570 | Completed | P2543-R01-Oct24..1.EN.8.2 | Review Company Comments - Civil / Structural Design Basis | HE-CS-1560 | HE-CS-1560: FS | HS-CN-0460, HE-CS-1580 | HS-CN-0460: FS, HE-CS-1580: FS | 2023-08-31 | 2023-09-01
HE-CS-1580 | Completed | P2543-R01-Oct24..1.EN.8.2 | Re-Issue for Approval - Civil / Structural Design Basis | HE-CS-1570 | HE-CS-1570: FS | HE-CS-1590 | HE-CS-1590: FS | 2023-11-01 | 2023-11-07
HE-CS-1590 | Completed | P2543-R01-Oct24..1.EN.8.2 | Obtain Company Approval - Civil / Structural Design Basis | HE-CS-1580 | HE-CS-1580: FS | HE-CS-1600, HE-EL-0850 | HE-CS-1600: FS, HE-EL-0850: FS | 2023-11-08 | 2023-11-15
HE-CS-1600 | Completed | P2543-R01-Oct24..1.EN.8.2 | Final Issue for Design/ Construction-Civil / Structural Design Basis | HE-CS-1590 | HE-CS-1590: FS | HE-CS-0110, HE-EL-0890, CAB-4420, HE-CS-0110, HE-CS-0050 | HE-CS-0110: FS, HE-EL-0890: FS, CAB-4420: FS, HE-CS-0110: FF, HE-CS-0050: FS | 2023-11-21 | 2024-01-22
HE-CP-50 | Completed | P2543-R01-Oct24..1.EN.15.1 | Issue ICR - Material Selection & Corrosion Control Philosophy | HE-PR-0040 | HE-PR-0040: FF 6 | HE-CP-60, HE-CP-0010, HE-CP-100 | HE-CP-60: FS, HE-CP-0010: FF 3, HE-CP-100: FS | 2023-08-09 | 2023-08-21
HE-CP-60 | Completed | P2543-R01-Oct24..1.EN.15.1 | Receive Company Comments - Material Selection & Corrosion Control Philosophy | HE-CP-50 | HE-CP-50: FS | HE-CP-70 | HE-CP-70: FS | 2023-08-22 | 2023-08-29
HE-CP-70 | Completed | P2543-R01-Oct24..1.EN.15.1 | Re-Issue for Approval - Material Selection & Corrosion Control Philosophy | HE-CP-60 | HE-CP-60: FS | HE-CP-80 | HE-CP-80: FS | 2023-09-15 | 2023-09-22
HE-CP-80 | Completed | P2543-R01-Oct24..1.EN.15.1 | Obtain Company Approval - Material Selection & Corrosion Control Philosophy | HE-CP-70 | HE-CP-70: FS | HE-CP-90 | HE-CP-90: FS | 2023-09-23 | 2023-09-28
HE-CP-90 | Completed | P2543-R01-Oct24..1.EN.15.1 | Final Issue for Design/ Construction-Material Selection & Corrosion Control Philosophy | HE-CP-80 | HE-CP-80: FS | HE-CP-0040 | HE-CP-0040: FS | 2023-11-15 | 2023-11-22
HE-CP-100 | Completed | P2543-R01-Oct24..1.EN.15.2 | Issue ICR - Scope of Work for RBI Study | HE-CP-200, HE-CP-50 | HE-CP-200: FS, HE-CP-50: FS | HE-CP-250, HE-CP-110 | HE-CP-250: SS 10, HE-CP-110: FS | 2023-10-10 | 2023-10-25
HE-CP-110 | Completed | P2543-R01-Oct24..1.EN.15.2 | Receive Company Comments - Scope of Work for RBI Study | HE-CP-100 | HE-CP-100: FS | HE-CP-120 | HE-CP-120: FS | 2023-11-08 | 2023-11-16
HE-CP-120 | Completed | P2543-R01-Oct24..1.EN.15.2 | Re-Issue for Approval - Scope of Work for RBI Study | HE-CP-110 | HE-CP-110: FS | HE-CP-130 | HE-CP-130: FS | 2023-11-17 | 2023-11-24
HE-CP-130 | Completed | P2543-R01-Oct24..1.EN.15.2 | Obtain Company Approval - Scope of Work for RBI Study | HE-CP-120 | HE-CP-120: FS | HE-CP-140 | HE-CP-140: FS | 2023-12-29 | 2024-01-09
HE-CP-140 | Completed | P2543-R01-Oct24..1.EN.15.2 | Final Issue for Design/ Construction-Scope of Work for RBI Study | HE-CP-130 | HE-CP-130: FS | HE-CP-300, HE-CP-150 | HE-CP-300: FS, HE-CP-150: FS 20 | 2024-01-12 | 2024-01-25
HE-CP-150 | Completed | P2543-R01-Oct24..1.EN.15.3 | Issue ICR - TBE for RBI Study | HE-CP-140, HE-CP-290 | HE-CP-140: FS 20, HE-CP-290: FS | HE-CP-160, HS-GN-0490 | HE-CP-160: FS, HS-GN-0490: FS | 2024-01-29 | 2024-02-02
HE-CP-160 | Completed | P2543-R01-Oct24..1.EN.15.3 | Receive Company Comments - TBE for RBI Study | HE-CP-150 | HE-CP-150: FS | HE-CP-170 | HE-CP-170: FS | 2024-02-03 | 2024-02-16
HE-CP-170 | Completed | P2543-R01-Oct24..1.EN.15.3 | Re-Issue for Approval - TBE for RBI Study | HE-CP-160 | HE-CP-160: FS | HE-CP-180 | HE-CP-180: FS | 2024-02-17 | 2024-03-01
HE-CP-180 | Completed | P2543-R01-Oct24..1.EN.15.3 | Obtain Company Approval - TBE for RBI Study | HE-CP-170 | HE-CP-170: FS | HE-CP-190 | HE-CP-190: FS | 2024-03-02 | 2024-03-15
HE-CP-190 | Completed | P2543-R01-Oct24..1.EN.15.3 | Final Issue for Design/ Construction-TBE for RBI Study | HE-CP-180 | HE-CP-180: FS | HE-EL-1610, HE-CP-300 | HE-EL-1610: FF, HE-CP-300: FS | 2024-03-16 | 2024-03-22
HE-CP-200 | Completed | P2543-R01-Oct24..1.EN.15.5 | Issue ICR - Material Selection Report | HE-CP-0010 | HE-CP-0010: FS | HE-CP-100, HE-CP-210, HE-PI-0010, HE-PI-0010 | HE-CP-100: FS, HE-CP-210: FS, HE-PI-0010: FF 5, HE-PI-0010: SS | 2023-08-22 | 2023-09-01
HE-CP-210 | Completed | P2543-R01-Oct24..1.EN.15.5 | Receive Company Comments - Material Selection Report | HE-CP-200 | HE-CP-200: FS | HE-CP-220 | HE-CP-220: FS | 2023-09-01 | 2023-09-07
HE-CP-220 | Completed | P2543-R01-Oct24..1.EN.15.5 | Re-Issue for Approval - Material Selection Report | HE-CP-210 | HE-CP-210: FS | HE-CP-230, HE-WS-0310 | HE-CP-230: FS, HE-WS-0310: FS | 2023-09-08 | 2023-10-02
HE-CP-230 | Completed | P2543-R01-Oct24..1.EN.15.5 | Obtain Company Approval - Material Selection Report | HE-CP-0040, HE-CP-220 | HE-CP-0040: FS, HE-CP-220: FS | HS-CN-0210, HE-CP-240 | HS-CN-0210: FS 10, HE-CP-240: FS | 2023-10-03 | 2023-10-13
HE-CP-240 | Completed | P2543-R01-Oct24..1.EN.15.5 | Final Issue for Design/ Construction-Material Selection Report | HE-CP-0050, HE-CP-230 | HE-CP-0050: FS, HE-CP-230: FS | HE-PI-0050 | HE-PI-0050: FS | 2023-11-11 | 2023-11-22
HE-CP-250 | Completed | P2543-R01-Oct24..1.EN.15.6 | Issue ICR - Material Coating & Painting Specification | HE-CP-100 | HE-CP-100: SS 10 | HE-CP-260 | HE-CP-260: FS | 2023-10-12 | 2023-10-27
HE-CP-260 | Completed | P2543-R01-Oct24..1.EN.15.6 | Receive Company Comments - Material Coating & Painting Specification | HE-CP-250 | HE-CP-250: FS | HE-CP-270 | HE-CP-270: FS | 2023-11-09 | 2023-11-15
HE-CP-270 | Completed | P2543-R01-Oct24..1.EN.15.6 | Re-Issue for Approval - Material Coating & Painting Specification | HE-CP-260 | HE-CP-260: FS | HE-CP-280 | HE-CP-280: FS | 2023-11-16 | 2023-11-23
HE-CP-280 | Completed | P2543-R01-Oct24..1.EN.15.6 | Obtain Company Approval - Material Coating & Painting Specification | HE-CP-270 | HE-CP-270: FS | HE-CP-290 | HE-CP-290: FS | 2023-12-29 | 2024-01-09
HE-CP-290 | Completed | P2543-R01-Oct24..1.EN.15.6 | Final Issue for Design/ Construction-Material Coating & Painting Specification | HE-CP-280 | HE-CP-280: FS | HE-CP-340, HE-CP-150 | HE-CP-340: FS, HE-CP-150: FS | 2024-01-12 | 2024-01-23
HE-CP-300 | Not Started | P2543-R01-Oct24..1.EN.15.7 | Issue ICR - RBI Study Report | HE-CP-140, HE-CP-190 | HE-CP-140: FS, HE-CP-190: FS | HE-CP-310 | HE-CP-310: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HE-CP-310 | Not Started | P2543-R01-Oct24..1.EN.15.7 | Receive Company Comments - RBI Study Report | HE-CP-300 | HE-CP-300: FS | HE-CP-320 | HE-CP-320: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-CP-320 | Not Started | P2543-R01-Oct24..1.EN.15.7 | Re-Issue for Approval - RBI Study Report | HE-CP-310 | HE-CP-310: FS | HE-CP-330 | HE-CP-330: FS | 2024-11-25 07:30 | 2024-12-10 17:30
HE-CP-330 | Not Started | P2543-R01-Oct24..1.EN.15.7 | Obtain Company Approval - RBI Study Report | HE-CP-320 | HE-CP-320: FS | HE-CP-340 | HE-CP-340: FS | 2024-12-11 07:30 | 2024-12-24 17:30
HE-CP-340 | Not Started | P2543-R01-Oct24..1.EN.15.7 | Final Issue for Design/ Construction-RBI Study Report | HE-CP-330, HE-CP-290 | HE-CP-330: FS, HE-CP-290: FS | ML1040 | ML1040: FF | 2024-12-25 07:30 | 2025-01-08 17:30
HE-CO-110 | Not Started | P2543-R01-Oct24..4.4.1.1 | Issue ICR-Commissioning Manual | ML1010-B14, ML1010-B14 | ML1010-B14: FS, ML1010-B14: FF | C-COM-800, HE-CO-200, HE-CO-120, C-COM-850 | C-COM-800: FS, HE-CO-200: FS, HE-CO-120: FS, C-COM-850: FS | 2024-10-28 07:30 | 2024-12-10 17:30
HE-CO-120 | Not Started | P2543-R01-Oct24..4.4.1.1 | Receive Company Comments-Commissioning Manual | HE-CO-110 | HE-CO-110: FS | HE-CO-130 | HE-CO-130: FS | 2024-12-11 07:30 | 2024-12-24 17:30
HE-CO-130 | Not Started | P2543-R01-Oct24..4.4.1.1 | Re-Issue for Approval-Commissioning Manual | HE-CO-120 | HE-CO-120: FS | C-COM-870, HE-CO-140 | C-COM-870: FS, HE-CO-140: FS | 2024-12-25 07:30 | 2025-02-05 17:30
HE-CO-140 | Not Started | P2543-R01-Oct24..4.4.1.1 | Obtain Company Approval-Commissioning Manual | HE-CO-130 | HE-CO-130: FS | HE-CO-150 | HE-CO-150: FS | 2025-02-06 07:30 | 2025-02-19 17:30
HE-CO-150 | Not Started | P2543-R01-Oct24..4.4.1.1 | Final Issue for Design/ Construction-Commissioning Manuals | HE-CO-140 | HE-CO-140: FS | C-COM-800, C-COM-840, HE-CO-190, CCM-PM4500, C-COM-890 | C-COM-800: FS, C-COM-840: FS, HE-CO-190: FS, CCM-PM4500: FS, C-COM-890: FS | 2025-02-20 07:30 | 2025-04-07 17:30
HE-CO-160 | Not Started | P2543-R01-Oct24..4.4.1.2 | Receive Company Comments-Operation and Maintenance Manual | HE-CO-200 | HE-CO-200: FS | HE-CO-170 | HE-CO-170: FS | 2025-02-06 07:30 | 2025-02-19 17:30
HE-CO-170 | Not Started | P2543-R01-Oct24..4.4.1.2 | Re-Issue for Approval-Operation and Maintenance Manual | HM-ME-0410, HE-CO-160, HE-ST-0050 | HM-ME-0410: FS, HE-CO-160: FS, HE-ST-0050: FS | HE-CO-180 | HE-CO-180: FS | 2025-02-20 07:30 | 2025-03-19 17:30
HE-CO-180 | Not Started | P2543-R01-Oct24..4.4.1.2 | Obtain Company Approval-Operation and Maintenance Manual | HE-CO-170 | HE-CO-170: FS | HE-CO-190 | HE-CO-190: FS | 2025-03-20 07:30 | 2025-04-07 17:30
HE-CO-190 | Not Started | P2543-R01-Oct24..4.4.1.2 | Final Issue for Design/ Construction-Operation and Maintenance Manuals | HE-CO-180, HE-CO-150 | HE-CO-180: FS, HE-CO-150: FS | CCM-PM4500 | CCM-PM4500: FS | 2025-04-08 07:30 | 2025-05-05 17:30
HE-CO-200 | Not Started | P2543-R01-Oct24..4.4.1.2 | Issue ICR-Operation and Maintenance Manual | HE-EL-1730, HE-PI-0640, HE-TL-0710, HE-PI-0580, HE-TL-0770, HE-PI-0760, HE-PI-0820, HE-PI-0700, HE-CO-110, HE-PI-0440, HE-PI-0880, HE-PI-0510, HE-EL-0530, HE-EL-1670, HE-IC-2570, HE-PI-0370 | HE-EL-1730: FS, HE-PI-0640: FS, HE-TL-0710: FS, HE-PI-0580: FS, HE-TL-0770: FS, HE-PI-0760: FS, HE-PI-0820: FS, HE-PI-0700: FS, HE-CO-110: FS, HE-PI-0440: FS, HE-PI-0880: FS, HE-PI-0510: FS, HE-EL-0530: FS, HE-EL-1670: FS, HE-IC-2570: FS, HE-PI-0370: FS | HE-CO-160 | HE-CO-160: FS | 2025-01-02 07:30 | 2025-02-05 17:30
HE-HV-150 | Completed | P2543-R01-Oct24..1.EN.12.9 | Re-Issue for Approval-Design Basis | HE-HV-190 | HE-HV-190: FS | HE-HV-170 | HE-HV-170: FS | 2023-11-07 | 2023-11-27
HE-HV-160 | Completed | P2543-R01-Oct24..1.EN.12.9 | Final Issue for Design-Design Basis | HE-HV-170 | HE-HV-170: FS | HE-HV-2780 | HE-HV-2780: FS | 2023-12-13 | 2024-01-09
HE-HV-170 | Completed | P2543-R01-Oct24..1.EN.12.9 | Obtain Company Approval-Design Basis | HE-HV-150 | HE-HV-150: FS | HE-HV-160 | HE-HV-160: FS | 2023-11-28 | 2023-12-12
HE-HV-180 | Completed | P2543-R01-Oct24..1.EN.12.9 | Issue ICR-Design Basis | HE-DB-0050, HE-DB-0020 | HE-DB-0050: FS, HE-DB-0020: FS | HE-HV-190, HE-HV-2690 | HE-HV-190: FS, HE-HV-2690: FS | 2023-09-16 | 2023-09-27
HE-HV-190 | Completed | P2543-R01-Oct24..1.EN.12.9 | Receive Company Comments-Design Basis | HE-HV-180 | HE-HV-180: FS | HE-HV-150 | HE-HV-150: FS | 2023-09-28 | 2023-10-11
HE-HV-2690 | Completed | P2543-R01-Oct24..1.EN.12.A11 | Issue ICR- Specification for HVAC | HE-HV-180 | HE-HV-180: FS | HE-HV-2700 | HE-HV-2700: FS | 2023-11-01 | 2023-11-10
HE-HV-2700 | Completed | P2543-R01-Oct24..1.EN.12.A11 | Receive Company Comments- Specification for HVAC | HE-HV-2690 | HE-HV-2690: FS | HE-HV-2710 | HE-HV-2710: FS | 2023-11-11 | 2023-11-17
HE-HV-2710 | Completed | P2543-R01-Oct24..1.EN.12.A11 | Re-Issue for Approval- Specification for HVAC | HE-HV-2700 | HE-HV-2700: FS | HE-HV-2720 | HE-HV-2720: FS | 2023-11-17 | 2023-11-24
HE-HV-2720 | Completed | P2543-R01-Oct24..1.EN.12.A11 | Obtain Company Approval- Specification for HVAC | HE-HV-2710 | HE-HV-2710: FS | HE-HV-2730 | HE-HV-2730: FS | 2023-11-28 | 2023-12-07
HE-HV-2730 | Completed | P2543-R01-Oct24..1.EN.12.A11 | Final Issue for Design/ Construction-Specification for HVAC | HE-HV-2720 | HE-HV-2720: FS | HE-HV-2780 | HE-HV-2780: FS | 2024-01-29 | 2024-02-14
HE-HV-2740 | Completed | P2543-R01-Oct24..1.EN.12.A111 | Issue ICR- Specification for Material Handling | HE-PI-0020 | HE-PI-0020: FS | HE-HV-2750, HE-HV-2790 | HE-HV-2750: FS, HE-HV-2790: FS | 2024-02-26 | 2024-03-11
HE-HV-2750 | Completed | P2543-R01-Oct24..1.EN.12.A111 | Receive Company Comments- Specification for Material Handling | HE-HV-2740 | HE-HV-2740: FS | HE-HV-2760 | HE-HV-2760: FS | 2024-03-12 | 2024-03-27
HE-HV-2760 | Completed | P2543-R01-Oct24..1.EN.12.A111 | Re-Issue for Approval- Specification for Material Handling | HE-HV-2750 | HE-HV-2750: FS | HE-HV-2770 | HE-HV-2770: FS | 2024-03-31 | 2024-04-25
HE-HV-2770 | Completed | P2543-R01-Oct24..1.EN.12.A111 | Obtain Company Approval- Specification for Material Handling | HE-HV-2760 | HE-HV-2760: FS | HE-HV-2780 | HE-HV-2780: FS | 2024-04-27 | 2024-04-30
HE-HV-2780 | Completed | P2543-R01-Oct24..1.EN.12.A111 | Final Issue for Design/ Construction-Specification for Material Handling | HE-HV-2770, HE-HV-160, HE-HV-2730 | HE-HV-2770: FS, HE-HV-160: FS, HE-HV-2730: FS | HE-HV-2830 | HE-HV-2830: FS | 2024-05-01 | 2024-05-20
HE-HV-2790 | Completed | P2543-R01-Oct24..1.EN.12.A1111 | Issue ICR- Datasheet for Material Handling | HE-HV-2740 | HE-HV-2740: FS | HE-HV-2800, HE-HV-2840 | HE-HV-2800: FS, HE-HV-2840: FS | 2024-02-26 | 2024-03-08
HE-HV-2800 | Completed | P2543-R01-Oct24..1.EN.12.A1111 | Receive Company Comments- Datasheet for Material Handling | HE-HV-2790 | HE-HV-2790: FS | HE-HV-2810 | HE-HV-2810: FS | 2024-03-10 | 2024-03-25
HE-HV-2810 | Completed | P2543-R01-Oct24..1.EN.12.A1111 | Re-Issue for Approval- Datasheet for Material Handling | HE-HV-2800 | HE-HV-2800: FS | HE-HV-2820 | HE-HV-2820: FS | 2024-03-26 | 2024-04-26
HE-HV-2820 | Completed | P2543-R01-Oct24..1.EN.12.A1111 | Obtain Company Approval- Datasheet for Material Handling | HE-HV-2810 | HE-HV-2810: FS | HE-HV-2830 | HE-HV-2830: FS | 2024-04-27 | 2024-05-10
HE-HV-2830 | Completed | P2543-R01-Oct24..1.EN.12.A1111 | Final Issue for Design/ Construction-Datasheet for Material Handling | HE-HV-2820, HE-HV-2780 | HE-HV-2820: FS, HE-HV-2780: FS | HE-HV-2880 | HE-HV-2880: FS | 2024-05-11 | 2024-05-20
HE-HV-2840 | Completed | P2543-R01-Oct24..1.EN.12.A11111 | Issue ICR- Material Requisition for Material Handling | HE-HV-2790 | HE-HV-2790: FS | HP-ME-1360, HE-HV-2850, HP-ME-0810, HP-ME-0860 | HP-ME-1360: FS, HE-HV-2850: FS, HP-ME-0810: FS, HP-ME-0860: FS | 2024-03-10 | 2024-03-25
HE-HV-2850 | Completed | P2543-R01-Oct24..1.EN.12.A11111 | Receive Company Comments- Material Requisition for Material Handling | HE-HV-2840 | HE-HV-2840: FS | HE-HV-2860 | HE-HV-2860: FS | 2024-03-26 | 2024-03-29
HE-HV-2860 | Completed | P2543-R01-Oct24..1.EN.12.A11111 | Re-Issue for Approval- Material Requisition for Material Handling | HE-HV-2850 | HE-HV-2850: FS | HE-HV-2870 | HE-HV-2870: FS | 2024-06-25 | 2024-07-04 17:30
HE-HV-2870 | Completed | P2543-R01-Oct24..1.EN.12.A11111 | Obtain Company Approval- Material Requisition for Material Handling | HE-HV-2860 | HE-HV-2860: FS | HE-HV-2880 | HE-HV-2880: FS | 2024-07-05 07:30 | 2024-07-21 17:30
HE-HV-2880 | Completed | P2543-R01-Oct24..1.EN.12.A11111 | Final Issue for Design/ Construction-Material Requisition for Material Handling | HE-HV-2870, HE-HV-2830 | HE-HV-2870: FS, HE-HV-2830: FS | HE-HV-2930 | HE-HV-2930: FS | 2024-07-22 07:30 | 2024-07-25 17:30
HE-HV-2890 | Completed | P2543-R01-Oct24..1.EN.12.A111111 | Issue ICR- TBE for Material Handling | HP-ME-0810 | HP-ME-0810: FS | HP-ME-1380, HE-HV-2900, HP-ME-0870 | HP-ME-1380: FS, HE-HV-2900: FS, HP-ME-0870: SS | 2024-06-06 | 2024-06-17
HE-HV-2900 | Completed | P2543-R01-Oct24..1.EN.12.A111111 | Receive Company Comments- TBE for Material Handling | HE-HV-2890 | HE-HV-2890: FS | HP-ME-1370, HE-HV-2910 | HP-ME-1370: FS, HE-HV-2910: FS | 2024-06-18 07:30 | 2024-07-02 17:30
HE-HV-2910 | Completed | P2543-R01-Oct24..1.EN.12.A111111 | Re-Issue for Approval- TBE for Material Handling | HE-HV-2900 | HE-HV-2900: FS | HE-HV-2920 | HE-HV-2920: FS | 2024-10-11 07:30 | 2024-10-17 17:30
HE-HV-2920 | In Progress | P2543-R01-Oct24..1.EN.12.A111111 | Obtain Company Approval- TBE for Material Handling | HE-HV-2910 | HE-HV-2910: FS | HE-HV-2930 | HE-HV-2930: FS | 2024-10-18 07:30 | 2024-11-08 17:30
HE-HV-2930 | Not Started | P2543-R01-Oct24..1.EN.12.A111111 | Final Issue for Design/ Construction- TBE for Material Handling | HE-HV-2920, HE-HV-2880 | HE-HV-2920: FS, HE-HV-2880: FS | HM-ME-2070 | HM-ME-2070: FF | 2024-11-11 07:30 | 2024-11-15 17:30
HE-CS-1610 | Completed | P2543-R01-Oct24..1.EN.8.3 | Re-Issue for Approval - Civil GA Drawings | HE-CS-1650, HE-CS-1650 | HE-CS-1650: FF, HE-CS-1650: FS | HE-CS-1620, HE-CS-1620 | HE-CS-1620: FF, HE-CS-1620: FS | 2024-08-23 | 2024-10-05
HE-CS-1620 | Completed | P2543-R01-Oct24..1.EN.8.3 | Obtain Company Approval - Civil GA Drawings | HE-CS-1610, HE-CS-1610 | HE-CS-1610: FF, HE-CS-1610: FS | HE-CS-1630 | HE-CS-1630: FS | 2024-10-07 07:30 | 2024-10-14 17:30
HE-CS-1630 | Not Started | P2543-R01-Oct24..1.EN.8.3 | Final Issue for Design/ Construction-Civil GA Drawings | HE-CS-1620 | HE-CS-1620: FS | C-56-PL-607-CI-1010 | C-56-PL-607-CI-1010: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HE-CS-1640 | Completed | P2543-R01-Oct24..1.EN.8.3 | Issued for Review - Civil GA Drawings | HE-CS-0490 | HE-CS-0490: SS 10 | HE-CS-1650 | HE-CS-1650: FF | 2024-03-01 | 2024-10-01 17:30
HE-CS-1650 | Completed | P2543-R01-Oct24..1.EN.8.3 | Review Company Comments - Civil GA Drawings | HE-CS-1640 | HE-CS-1640: FF | HE-CS-1610, HE-CS-1610 | HE-CS-1610: FF, HE-CS-1610: FS | 2024-06-15 | 2024-10-03 17:30
HE-ME-580 | Completed | P2543-R01-Oct24..1.EN.5.4 | Receive Company Comments- Addendum to DGS | HE-ME-620 | HE-ME-620: FS | HE-ME-590 | HE-ME-590: FS | 2023-09-24 | 2023-09-27
HE-ME-590 | Completed | P2543-R01-Oct24..1.EN.5.4 | Re-Issue for Approval- Addendum to DGS | HE-ME-580 | HE-ME-580: FS | HE-ME-600 | HE-ME-600: FS | 2023-09-28 | 2023-10-04
HE-ME-600 | Completed | P2543-R01-Oct24..1.EN.5.4 | Obtain Company Approval- Addendum to DGS | HE-ME-590 | HE-ME-590: FS | HE-ME-610 | HE-ME-610: FS | 2023-10-05 | 2023-10-13
HE-ME-610 | Completed | P2543-R01-Oct24..1.EN.5.4 | Final Issue for Design/ Construction- Addendum to DGS | HE-ME-600, HE-ME-0050 | HE-ME-600: FS, HE-ME-0050: FS | ML1219-B29, CAB-4430, HE-ME-400 | ML1219-B29: FF, CAB-4430: FS, HE-ME-400: FS | 2023-10-14 | 2023-10-27
HE-ME-620 | Completed | P2543-R01-Oct24..1.EN.5.4 | Issue ICR- Addendum to DGS | HE-ME-0010 | HE-ME-0010: SS 10 | HE-ME-580, HE-ME-670, HE-ME-300 | HE-ME-580: FS, HE-ME-670: SS 15, HE-ME-300: FS | 2023-09-23 | 2023-09-24
HE-ME-630 | Completed | P2543-R01-Oct24..1.EN.5.5 | Receive Company Comments- Pig Launcher/Receiver Length Report | HE-ME-670 | HE-ME-670: FS | HE-ME-640 | HE-ME-640: FS | 2023-11-19 | 2023-11-24
HE-ME-640 | Completed | P2543-R01-Oct24..1.EN.5.5 | Re-Issue for Approval- Pig Launcher/Receiver Length Report | HE-ME-630 | HE-ME-630: FS | HE-ME-650 | HE-ME-650: FS | 2023-11-21 | 2023-11-29
HE-ME-650 | Completed | P2543-R01-Oct24..1.EN.5.5 | Obtain Company Approval- Pig Launcher/Receiver Length Report | HE-ME-640 | HE-ME-640: FS | HE-ME-660 | HE-ME-660: FS | 2023-11-30 | 2023-12-12
HE-ME-660 | Completed | P2543-R01-Oct24..1.EN.5.5 | Final Issue for Design/ Construction- Pig Launcher/Receiver Length Report | HE-ME-650 | HE-ME-650: FS | HE-ME-520, HE-ME-530 | HE-ME-520: FS, HE-ME-530: FF | 2023-12-29 | 2024-01-07
HE-ME-670 | Completed | P2543-R01-Oct24..1.EN.5.5 | Issue ICR- Pig Launcher/Receiver Length Report | HE-ME-620 | HE-ME-620: SS 15 | HE-ME-630, HE-ME-310 | HE-ME-630: FS, HE-ME-310: FS | 2023-10-10 | 2023-10-25
HE-PI-3580 | Completed | P2543-R01-Oct24..1.EN.7.4.1 | Issue ICR-Data sheet for Check Valves | HE-PI-0900 | HE-PI-0900: FS 5 | HE-PI-3590, HE-PI-3630 | HE-PI-3590: FS, HE-PI-3630: FS | 2023-09-22 | 2023-09-28
HE-PI-3590 | Completed | P2543-R01-Oct24..1.EN.7.4.1 | Receive Company Comments-Data sheet for Check Valves | HE-PI-3580 | HE-PI-3580: FS | HE-PI-3600 | HE-PI-3600: FS | 2023-10-05 | 2023-10-17
HE-PI-3600 | Completed | P2543-R01-Oct24..1.EN.7.4.1 | Re-Issue for Approval-Data sheet for Check Valves | HE-PI-3590 | HE-PI-3590: FS | HE-PI-3610 | HE-PI-3610: FS | 2023-10-31 | 2023-11-07
HE-PI-3610 | Completed | P2543-R01-Oct24..1.EN.7.4.1 | Obtain Company Approval-Data sheet for Check Valves | HE-PI-3600 | HE-PI-3600: FS | HE-PI-3620 | HE-PI-3620: FS | 2023-11-08 | 2023-11-14
HE-PI-3620 | Completed | P2543-R01-Oct24..1.EN.7.4.1 | Final Issue for Design/ Construction-Datasheet for Check valves | HE-PI-3610 | HE-PI-3610: FS | HE-PI-3670 | HE-PI-3670: FS | 2023-11-15 | 2023-11-22
HE-PI-3630 | Completed | P2543-R01-Oct24..1.EN.7.8.1 | Issue ICR-MR for Check Valves | HE-PI-3580 | HE-PI-3580: FS | HE-PI-3640, HE-PI-3730 | HE-PI-3640: FS, HE-PI-3730: FS | 2023-12-06 | 2023-12-15
HE-PI-3640 | Completed | P2543-R01-Oct24..1.EN.7.8.1 | Receive Company Comments-MR for Check Valves | HE-PI-3630 | HE-PI-3630: FS | HE-PI-3650, HE-PI-3730 | HE-PI-3650: FS, HE-PI-3730: FS | 2023-12-29 | 2024-01-08
HE-PI-3650 | Completed | P2543-R01-Oct24..1.EN.7.8.1 | Re-Issue for Approval-MR for Check Valves | HE-PI-3640 | HE-PI-3640: FS | HE-PI-3660 | HE-PI-3660: FS | 2024-02-26 | 2024-03-17
HE-PI-3660 | Completed | P2543-R01-Oct24..1.EN.7.8.1 | Obtain Company Approval-MR for Check Valves | HE-PI-3650 | HE-PI-3650: FS | HE-PI-3670 | HE-PI-3670: FS | 2024-03-04 | 2024-03-17
HE-PI-3670 | Completed | P2543-R01-Oct24..1.EN.7.8.1 | Final Issue for Design/ Construction-Material Requisition for Check Valves | HE-PI-3660, HE-PI-3620 | HE-PI-3660: FS, HE-PI-3620: FS | HE-PI-3770 | HE-PI-3770: FS | 2024-03-04 | 2024-03-17
HE-PI-3680 | Completed | P2543-R01-Oct24..1.EN.7.8.2 | Issue ICR-MR for Piping Special Items | HE-PI-3530 | HE-PI-3530: SS 5 | HE-PI-3690, HE-PI-1410 | HE-PI-3690: FS, HE-PI-1410: FS | 2023-12-29 | 2024-01-05
HE-PI-3690 | Completed | P2543-R01-Oct24..1.EN.7.8.2 | Receive Company Comments-MR for Piping Special Items | HE-PI-3680 | HE-PI-3680: FS | HE-PI-3700, HE-PI-1410 | HE-PI-3700: FS, HE-PI-1410: FS | 2024-01-08 | 2024-01-15
HE-PI-3700 | Completed | P2543-R01-Oct24..1.EN.7.8.2 | Re-Issue for Approval-MR for Piping Special Items | HE-PI-3690 | HE-PI-3690: FS | HE-PI-3710 | HE-PI-3710: FS | 2024-01-16 | 2024-03-17
HE-PI-3710 | Completed | P2543-R01-Oct24..1.EN.7.8.2 | Obtain Company Approval-MR for Piping Special Items | HE-PI-3700 | HE-PI-3700: FS | HE-PI-3720 | HE-PI-3720: FS | 2024-03-04 | 2024-03-28
HE-PI-3720 | In Progress | P2543-R01-Oct24..1.EN.7.8.2 | Final Issue for Design/ Construction-Material Requisition for Piping Special Items | HE-PI-3710, HE-PI-1310 | HE-PI-3710: FS, HE-PI-1310: FF | HE-PI-1450 | HE-PI-1450: FS | 2024-08-19 07:30 | 2024-11-01 17:30
HE-PI-3730 | Completed | P2543-R01-Oct24..1.EN.7.2.1 | Issue ICR- TBE for Check Valves | HE-PI-3630, HE-PI-3640 | HE-PI-3630: FS, HE-PI-3640: FS | HE-PI-3740 | HE-PI-3740: FS | 2024-02-06 | 2024-03-12
HE-PI-3740 | Completed | P2543-R01-Oct24..1.EN.7.2.1 | Receive Company Comments- TBE for Check Valves | HE-PI-3730 | HE-PI-3730: FS | HE-PI-3750 | HE-PI-3750: FS | 2024-03-13 | 2024-03-28
HE-PI-3750 | Completed | P2543-R01-Oct24..1.EN.7.2.1 | Re-Issue for Approval- TBE for Check Valves | HE-PI-3740 | HE-PI-3740: FS | HE-PI-3760 | HE-PI-3760: FS | 2024-03-31 | 2024-04-18
HE-PI-3760 | Completed | P2543-R01-Oct24..1.EN.7.2.1 | Obtain Company Approval- TBE for Check Valves | HE-PI-3750 | HE-PI-3750: FS | HE-PI-3770 | HE-PI-3770: FS | 2024-04-28 | 2024-05-16
HE-PI-3770 | Completed | P2543-R01-Oct24..1.EN.7.2.1 | Final Issue for Design/ Construction-TBE for Check Valves | HE-PI-3760, HE-PI-3670 | HE-PI-3760: FS, HE-PI-3670: FS | HE-PI-1180 | HE-PI-1180: FF | 2024-07-18 07:30 | 2024-07-29 17:30
ML1052-D1 | Not Started | P2543-R01-Oct24..ML | Receive at Site - Coated / Painted Line pipes- 56" | ML1509-D3, HM-PL-0110 | ML1509-D3: FF, HM-PL-0110: FF 17 | ML1389-D2 | ML1389-D2: FF |  | 2025-01-12 18:00
ML1509-D3 | Completed | P2543-R01-Oct24..ML | Receive at Site - Coated / Painted Line pipes- 52" (50% to total Qty) | HM-PL-1450 | HM-PL-1450: FF | ML1052-D1, C-52-0405-PL-ME-2800 | ML1052-D1: FF, C-52-0405-PL-ME-2800: FS 5 |  | 2024-09-13
ML1389-D2 | Not Started | P2543-R01-Oct24..ML | Receive at Site - Coated / Painted Line pipes- 4" (Nitrogen & Water line) | ML1052-D1, HM-PL-0120 | ML1052-D1: FF, HM-PL-0120: FF 14 | ML1399-D5, ML1060 | ML1399-D5: FF 21, ML1060: FS |  | 2025-02-19 18:00
ML1399-D5 | Not Started | P2543-R01-Oct24..ML | Receive at Site - Coated / Painted Line pipes- 52" (100% to total Qty) | ML1389-D2, HM-PL-0120, HM-PL-960 | ML1389-D2: FF 21, HM-PL-0120: FF, HM-PL-960: FF | C-52-06CR-PL-ME-2800 | C-52-06CR-PL-ME-2800: FS 5 |  | 2025-03-26 18:00
ML1100 | Not Started | P2543-R01-Oct24..ML | Complete 100% Construction & Pre-commissioning | ML1090, PRECOM-52-PL-1000, PRECOM-52-06CR-1000, PRECOM-52-EB1-1000 | ML1090: FF 90, PRECOM-52-PL-1000: FS, PRECOM-52-06CR-1000: FF, PRECOM-52-EB1-1000: FF | ML1030 (Internal) | ML1030 (Internal): FS |  | 2025-11-03 11:30
ML1070 | Not Started | P2543-R01-Oct24..ML | Complete 25% Construction & Pre-commissioning | ML1659-E11, C-52-0203-PL-ME-3600, C-52-0203-CME04-1070, C-52-0203-CME04-1150 | ML1659-E11: FS, C-52-0203-PL-ME-3600: FF 9, C-52-0203-CME04-1070: FS, C-52-0203-CME04-1150: FS | ML1080 | ML1080: FF 102 |  | 2024-12-14 17:00
ML1080 | Not Started | P2543-R01-Oct24..ML | Complete 50% Construction & Pre-commissioning | ML1070, C-52-HG01-CNM04-1800, C-52-HG01-PL-TE-8210, C-52-0102-CME06-1160, C-52-0102-PL-TE-8210, C-52-0203-PL-CA-5200, C-52-0203-PIPEL-5260, C-52-0304-PL-CA-5230, C-52-HG01-FENCE-1060, C-52-HG01-FENCE-1070, C-52-HG01-PL-CI-7200, C-52-0102-PL-CI-7200, C-52-0 | ML1070: FF 102, C-52-HG01-CNM04-1800: FS, C-52-HG01-PL-TE-8210: FS, C-52-0102-CME06-1160: FS, C-52-0102-PL-TE-8210: FS, C-52-0203-PL-CA-5200: FS, C-52-0203-PIPEL-5260: FS, C-52-0304-PL-CA-5230: FS, C-52-HG01-FENCE-1060: FS, C-52-HG01-FENCE-1070: FS, C-52-H | ML1090 | ML1090: FF 126 |  | 2025-03-26 17:00
ML1090 | Not Started | P2543-R01-Oct24..ML | Complete 75% Construction & Pre-commissioning | ML1080, HE-WS-0290, C-52-0102-PL-CA-5230, C-4W-SVHG-PIPEL-7810, C-52-0203-PL-ME-7620, PRECOM-4W-SVHG-1000, PRECOM-52-0203-1000, C-52-HG01-PL-CI-7800, C-52-HG01-PL-CI-7810, C-52-HG01-PL-CI-7820, C-52-PR-839-ME-1800, C-52-PR-839-ME-1810, C-52-0102-FENCE-1070 | ML1080: FF 126, HE-WS-0290: FF, C-52-0102-PL-CA-5230: FS, C-4W-SVHG-PIPEL-7810: FS, C-52-0203-PL-ME-7620: FS, PRECOM-4W-SVHG-1000: FS, PRECOM-52-0203-1000: FS, C-52-HG01-PL-CI-7800: FS, C-52-HG01-PL-CI-7810: FS, C-52-HG01-PL-CI-7820: FS, C-52-PR-839-ME-180 | ML1100 | ML1100: FF 90 |  | 2025-07-30 17:00
HM-PL-960 | Not Started | P2543-R01-Oct24..PR.1.16.3 | Receipt at site and inspection of Line Pipes - Lot 9 (Coated) | HM-PL-1250, HM-PL-1260, HM-PL-0120, HM-PL-1470 | HM-PL-1250: FF, HM-PL-1260: FS, HM-PL-0120: FS, HM-PL-1470: FF | ML1399-D5 | ML1399-D5: FF | 2025-03-04 08:00 | 2025-03-26 18:00
ML1219-B29 | Not Started | P2543-R01-Oct24..ML.EN | Completion of all Detailed Engineering | ML1032-B21, HE-CS-1800, ML1031-B20, HE-IC-1430, HE-TL-0530, HE-EL-0710, HE-HS-0470, HE-HS-1070, HE-TL-930, HE-TL-0890, HE-TL-0590, HE-IC-1550, HE-EL-0650, HE-IC-2630, HE-IC-2450, HE-IC-2330, HE-IC-0770, HE-IC-2090, HE-EL-1850, HE-EL-1790, HE-EL-1730, HE-EL | ML1032-B21: FF, HE-CS-1800: FF, ML1031-B20: FF, HE-IC-1430: FF, HE-TL-0530: FF, HE-EL-0710: FF, HE-HS-0470: FF, HE-HS-1070: FF, HE-TL-930: FF, HE-TL-0890: FF, HE-TL-0590: FF, HE-IC-1550: FF, HE-EL-0650: FF 20, HE-IC-2630: FF, HE-IC-2450: FF, HE-IC-2330: FF | ML1459-D12 | ML1459-D12: FF |  | 2025-01-08 17:30
ML1038-C20 | Not Started | P2543-R01-Oct24..ML.PR | Completion of Procurement Services | HP-ME-0320, HP-ME-0980, HP-ME-0930, HP-ME-0880 | HP-ME-0320: FF, HP-ME-0980: FF, HP-ME-0930: FF 80, HP-ME-0880: FF | ML1060, ML1219-B29 | ML1060: FS, ML1219-B29: FF |  | 2024-12-31 17:30
ML1549-D32 | Not Started | P2543-R01-Oct24..ML.2 | Complete Delivery to Site | HP-ME-0910, HS-GN-0350, HS-GN-0290, HP-BK-0210, HP-BK-0160, HP-BK-0110, HP-ME-1310, HM-EL-0080, HM-EL-0280, HM-EL-580, HM-EL-0380, HM-EL-0480, HM-PI-0050, HM-PI-70, HM-EL-0530, HM-IC-0050, HM-TL-0050, HM-PL-0840, HM-PL-0740, HM-PL-0530, HM-PL-0320, HM-PL-9 | HP-ME-0910: FF, HS-GN-0350: FF, HS-GN-0290: FF, HP-BK-0210: FF, HP-BK-0160: FF, HP-BK-0110: FF, HP-ME-1310: FF, HM-EL-0080: FF, HM-EL-0280: FF, HM-EL-580: FF, HM-EL-0380: FF, HM-EL-0480: FF, HM-PI-0050: FF, HM-PI-70: FF 199, HM-EL-0530: FF, HM-IC-0050: FF, | ML1030 | ML1030: FF |  | 2025-10-14 18:00
HS-CN-690 | Completed | P2543-R01-Oct24..1.2.12.15 | Automatic Welding Subcontract Award | HS-CN-720 | HS-CN-720: FS | C-52-06CR-PL-ME-3600 | C-52-06CR-PL-ME-3600: FS | 2023-11-15 | 2023-11-25
HS-CN-710 | Completed | P2543-R01-Oct24..1.2.12.15 | Automatic Welding RFQ & Quotation Receipt | HS-CN-0160 | HS-CN-0160: FS 15 | HS-CN-720 | HS-CN-720: FS | 2023-08-30 | 2023-10-05
HS-CN-720 | Completed | P2543-R01-Oct24..1.2.12.15 | Automatic Welding Complete Evaluation (Internal) | HS-CN-710 | HS-CN-710: FS | HS-CN-690, C-56-01HG-PL-ME-3600 | HS-CN-690: FS, C-56-01HG-PL-ME-3600: FS | 2023-10-06 | 2023-11-23
HS-CN-730 | Completed | P2543-R01-Oct24..1.2.12.16 | Pipe Internal Coating Subcontract Award | HS-CN-760 | HS-CN-760: FS | C-52-06CR-PL-ME-2800 | C-52-06CR-PL-ME-2800: FS | 2023-10-05 | 2023-10-10
HS-CN-750 | Completed | P2543-R01-Oct24..1.2.12.16 | Pipe Internal Coating RFQ & Quotation Receipt | HS-CN-0160 | HS-CN-0160: FS | HS-CN-760 | HS-CN-760: FS | 2023-09-11 | 2023-09-20
HS-CN-760 | Completed | P2543-R01-Oct24..1.2.12.16 | Pipe Internal Coating Complete Evaluation (Internal) | HS-CN-750 | HS-CN-750: FS | HS-CN-730 | HS-CN-730: FS | 2023-09-20 | 2023-10-05
CCM-PM4530 | Not Started | P2543-R01-Oct24..4.4.2 | Wrap up works for PAC-2 | CCM-PM4520, CCM-PM4500, C-541CR-EI-1040, C-541CR-TE-1000, C-52-PL-838-PL-1030, C-36-KM-HT04-ME-1040, C-36-KM-HT03-ME-1040, C-36-KM-HT-ME-2000, C-52-OHPL-EL-1400, C-52-OHPL-EL-2000, C-52-D-HT002-ME-1040, C-52-D-HT-ME-2000, C-52-PR-839-PL-1030, C-577-CI-1000 | CCM-PM4520: FS, CCM-PM4500: FS, C-541CR-EI-1040: FS, C-541CR-TE-1000: FS, C-52-PL-838-PL-1030: FS, C-36-KM-HT04-ME-1040: FS, C-36-KM-HT03-ME-1040: FS, C-36-KM-HT-ME-2000: FS, C-52-OHPL-EL-1400: FS, C-52-OHPL-EL-2000: FS, C-52-D-HT002-ME-1040: FS, C-52-D-HT | ML1050, ML2049-F06, A3980, ML-PAC2 (Internal) | ML1050: FF, ML2049-F06: FS, A3980: FS, ML-PAC2 (Internal): FS 11 | 2025-12-13 11:00 | 2025-12-24 11:00
CCM-PM4540 | Not Started | P2543-R01-Oct24..4.4.AB.3 | Intelligent Pigging Baseline Survey | HS-CN-0140, HE-PL-2190, CCM-PM4520, CCM-PM4500, C-541CR-EI-1040, C-541CR-TE-1000, C-52-PL-838-PL-1030, C-36-KM-HT04-ME-1040, C-36-KM-HT03-ME-1040, C-36-KM-HT-ME-2000, C-52-OHPL-EL-1400, C-52-OHPL-EL-2000, C-52-D-HT002-ME-1040, C-52-D-HT-ME-2000, C-52-PR-83 | HS-CN-0140: SS, HE-PL-2190: FS, CCM-PM4520: FS, CCM-PM4500: FS, C-541CR-EI-1040: FS, C-541CR-TE-1000: FS, C-52-PL-838-PL-1030: FS, C-36-KM-HT04-ME-1040: FS, C-36-KM-HT03-ME-1040: FS, C-36-KM-HT-ME-2000: FS, C-52-OHPL-EL-1400: FS, C-52-OHPL-EL-2000: FS, C-5 | ML1050, ML2049-F06, A3980 | ML1050: FF, ML2049-F06: FS, A3980: FS | 2025-12-13 11:00 | 2025-12-23 11:00
ML1219-B39 | Not Started | P2543-R01-Oct24..ML.EN | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | HE-PL-2430, ML1219-B49 | HE-PL-2430: FF, ML1219-B49: FF | ML1059-B28 | ML1059-B28: FF |  | 2024-11-01 17:30
ML1219-B49 | Not Started | P2543-R01-Oct24..ML.EN | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | HE-PL-2490 | HE-PL-2490: FF | ML1219-B39 | ML1219-B39: FF |  | 2024-11-01 17:30
ML1219-B59 | Not Started | P2543-R01-Oct24..ML.EN | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | HE-PL-3570, HE-PL-2550 | HE-PL-3570: FF, HE-PL-2550: FF | C-4N-H5HG-PIPEL-2400 | C-4N-H5HG-PIPEL-2400: FS |  | 2024-11-01 17:30
HE-CS-1710 | Completed | P2543-R01-Oct24..1.EN.8.5 | Issued for Review - Anchor Block Calculation | HE-PL-2810 | HE-PL-2810: FF 10 | HE-CS-1760, HE-CS-1720 | HE-CS-1760: FS, HE-CS-1720: FS | 2024-03-30 | 2024-04-23
HE-CS-1720 | Completed | P2543-R01-Oct24..1.EN.8.5 | Review Company Comments - Anchor Block Calculation | HE-CS-1710 | HE-CS-1710: FS | HE-CS-1730 | HE-CS-1730: FS | 2024-04-23 | 2024-05-06
HE-CS-1730 | Completed | P2543-R01-Oct24..1.EN.8.5 | Re-Issue for Approval - Anchor Block Calculation | HE-CS-1720 | HE-CS-1720: FS | HE-CS-1740 | HE-CS-1740: FS | 2024-06-14 | 2024-07-05 17:30
HE-CS-1740 | Completed | P2543-R01-Oct24..1.EN.8.5 | Obtain Company Approval - Anchor Block Calculation | HE-CS-1730 | HE-CS-1730: FS | HE-CS-1750 | HE-CS-1750: FS | 2024-07-15 07:30 | 2024-10-07 17:30
HE-CS-1750 | In Progress | P2543-R01-Oct24..1.EN.8.5 | Final Issue for Design/ Construction-Anchor Block Calculation | HE-CS-1740 | HE-CS-1740: FS | HE-CS-1800 | HE-CS-1800: FF | 2024-10-08 07:30 | 2024-11-15 17:30
HE-CS-1760 | Completed | P2543-R01-Oct24..1.EN.8.6 | Issued for Review - Anchor Block Detail Drawings | HE-CS-1710 | HE-CS-1710: FS | HE-CS-1770 | HE-CS-1770: FS | 2024-03-30 | 2024-04-23
HE-CS-1770 | Completed | P2543-R01-Oct24..1.EN.8.6 | Review Company Comments - Anchor Block Detail Drawings | HE-CS-1760 | HE-CS-1760: FS | HE-CS-1780 | HE-CS-1780: FS | 2024-05-06 | 2024-07-05 17:30
HE-CS-1780 | Completed | P2543-R01-Oct24..1.EN.8.6 | Re-Issue for Approval - Anchor Block Detail Drawings | HE-CS-1770 | HE-CS-1770: FS | HE-CS-1790 | HE-CS-1790: FS | 2024-07-08 07:30 | 2024-08-23 17:30
HE-CS-1790 | Completed | P2543-R01-Oct24..1.EN.8.6 | Obtain Company Approval - Anchor Block Detail Drawings | HE-CS-1780 | HE-CS-1780: FS | HE-CS-1800 | HE-CS-1800: FS | 2024-09-02 07:30 | 2024-09-16 17:30
HE-CS-1800 | In Progress | P2543-R01-Oct24..1.EN.8.6 | Final Issue for Design/ Construction - Anchor Block Detail Drawings | HE-CS-1750, HE-CS-1790 | HE-CS-1750: FF, HE-CS-1790: FS | C-52-598-04-CI-1010, ML1219-B29, C-56-PR-838-CI-1510 | C-52-598-04-CI-1010: FS, ML1219-B29: FF, C-56-PR-838-CI-1510: FS | 2024-09-17 07:30 | 2024-11-15 17:30
HM-ME-2000 | Not Started | P2543-R01-Oct24..PR.26.1.23.2 | Manufacturing & Assembly of LV Switch Gear | HM-ME-2040 | HM-ME-2040: FS | HM-ME-2010 | HM-ME-2010: FS | 2024-11-25 08:00 | 2025-04-23 18:00
HM-ME-2010 | Not Started | P2543-R01-Oct24..PR.26.1.23.2 | Factory Acceptance Test of LV Switch Gear | HM-ME-2000 | HM-ME-2000: FS | HM-ME-2020 | HM-ME-2020: FS | 2025-04-24 08:00 | 2025-05-07 18:00
HM-ME-2020 | Not Started | P2543-R01-Oct24..PR.26.1.23.2 | Packaging & Final Inspection-LV Switch Gear | HM-ME-2010 | HM-ME-2010: FS | HM-ME-2030 | HM-ME-2030: FS | 2025-05-08 08:00 | 2025-05-14 18:00
HM-ME-2030 | Not Started | P2543-R01-Oct24..PR.26.1.23.2 | Ready for Dispatch of LV Switch Gear | HM-ME-2020 | HM-ME-2020: FS | HM-ME-2050 | HM-ME-2050: FS | 2025-05-15 08:00 | 2025-05-18 18:00
HM-ME-2040 | Not Started | P2543-R01-Oct24..PR.26.1.23.2 | Vendor Document Review of LV Switch Gear | HP-ME-1340 | HP-ME-1340: FS | HM-ME-2000 | HM-ME-2000: FS | 2024-10-26 08:00 | 2024-11-24 18:00
HM-ME-2050 | Not Started | P2543-R01-Oct24..PR.26.1.23.3 | Transportation/ Custom Clearance/ Delivery at site of LV Switch Gear | HM-ME-2030 | HM-ME-2030: FS | HM-ME-2060 | HM-ME-2060: FS | 2025-05-19 08:00 | 2025-06-12 18:00
HM-ME-2060 | Not Started | P2543-R01-Oct24..PR.26.1.23.3 | Receipt at site and inspection of LV Switch Gear | HM-ME-2050 | HM-ME-2050: FS | C-52-EB1-EI-2400 | C-52-EB1-EI-2400: FS | 2025-06-13 07:00 | 2025-06-20 17:00
HP-ME-1330 | Completed | P2543-R01-Oct24..1.1.2.25.23.1 | RFQ, Receipt of Bid for LV Switch Gear | HE-EL-1960 | HE-EL-1960: FS | HP-ME-1340, HP-ME-1350, HE-EL-2210 | HP-ME-1340: FS, HP-ME-1350: FS, HE-EL-2210: FS | 2024-05-13 | 2024-05-17
HP-ME-1340 | Completed | P2543-R01-Oct24..1.1.2.25.23.1 | Commercial Clarifications & Placement of PO for LV Switch Gear | HP-ME-1330, HP-ME-1350 | HP-ME-1330: FS, HP-ME-1350: FS | HM-ME-2040 | HM-ME-2040: FS | 2024-10-18 07:30 | 2024-10-25 17:30
HP-ME-1350 | Completed | P2543-R01-Oct24..1.1.2.25.23.1 | Prepare TBE and Company approval for LV Switch Gear | HE-EL-2210, HP-ME-1330, HE-EL-2220 | HE-EL-2210: FS, HP-ME-1330: FS, HE-EL-2220: FF | HP-ME-1340 | HP-ME-1340: FS | 2024-08-05 07:30 | 2024-10-18 17:30
HP-ME-1360 | Completed | P2543-R01-Oct24..1.1.2.25.24.1 | RFQ, Receipt of Bid for Lifting Equipment | HE-HV-2840 | HE-HV-2840: FS | HP-ME-1380, HP-ME-1380, HP-ME-1370 | HP-ME-1380: FS, HP-ME-1380: FF, HP-ME-1370: FS | 2024-04-19 | 2024-05-07
HP-ME-1370 | Completed | P2543-R01-Oct24..1.1.2.25.24.1 | Commercial Clarifications & Placement of PO for Lifting Equipment | HE-HV-2900, HP-ME-1380, HP-ME-1360 | HE-HV-2900: FS, HP-ME-1380: FS, HP-ME-1360: FS | HM-ME-2180, HM-ME-2070 | HM-ME-2180: FS, HM-ME-2070: FS | 2024-08-03 07:30 | 2024-08-23 17:30
HP-ME-1380 | Completed | P2543-R01-Oct24..1.1.2.25.24.1 | Prepare TBE and Company approval for Lifting Equipment | HE-HV-2890, HP-ME-1360, HP-ME-1360 | HE-HV-2890: FS, HP-ME-1360: FS, HP-ME-1360: FF | HP-ME-1370 | HP-ME-1370: FS | 2024-06-17 | 2024-08-02 17:30
HM-ME-2070 | In Progress | P2543-R01-Oct24..PR.26.LL.24.2 | Vendor Document Review of Filter Package | HE-HV-2930, HP-ME-1370 | HE-HV-2930: FF, HP-ME-1370: FS | HM-ME-2080 | HM-ME-2080: FS | 2024-10-18 08:00 | 2024-11-15 17:30
HM-ME-2080 | Not Started | P2543-R01-Oct24..PR.26.LL.24.2 | Manufacturing & Assembly of Filter Package | HM-ME-2070 | HM-ME-2070: FS | HM-ME-2090 | HM-ME-2090: FS | 2024-11-15 17:30 | 2025-04-24 17:30
HM-ME-2090 | Not Started | P2543-R01-Oct24..PR.26.LL.24.2 | Testing and Inspection of Filter Package | HM-ME-2080 | HM-ME-2080: FS | HM-ME-2100 | HM-ME-2100: FS | 2025-04-24 17:30 | 2025-05-01 17:30
HM-ME-2100 | Not Started | P2543-R01-Oct24..PR.26.LL.24.2 | Packaging & Final Inspection-Filter Package | HM-ME-2090 | HM-ME-2090: FS | HM-ME-2110 | HM-ME-2110: FS | 2025-05-01 17:30 | 2025-05-07 17:30
HM-ME-2110 | Not Started | P2543-R01-Oct24..PR.26.LL.24.2 | Ready for Dispatch of Filter Package | HM-ME-2100 | HM-ME-2100: FS | HM-ME-2130 | HM-ME-2130: FS | 2025-05-07 17:30 | 2025-05-11 17:30
HM-ME-2120 | Not Started | P2543-R01-Oct24..PR.26.LL.24.3 | Receipt at site and inspection of Filter Package | HM-ME-2130 | HM-ME-2130: FS | C-56-PL-607-ME-1400 | C-56-PL-607-ME-1400: FS | 2025-05-19 07:00 | 2025-05-26 17:00
HM-ME-2130 | Not Started | P2543-R01-Oct24..PR.26.LL.24.3 | Transportation/ Custom Clearance/ Delivery at site of Filter Package | HM-ME-2110 | HM-ME-2110: FS | HM-ME-2120 | HM-ME-2120: FS | 2025-05-11 17:30 | 2025-05-18 17:30
CCM-PM4550 | Not Started | P2543-R01-Oct24..4.4.2 | Wrap up works for PAC-1 | CCM-PM4510, CCM-PM4570, CCM-PM4600 | CCM-PM4510: FS, CCM-PM4570: FF, CCM-PM4600: FS | ML1040, ML2039-F05, ML-PAC1 (Internal) | ML1040: FF, ML2039-F05: FF, ML-PAC1 (Internal): FS | 2025-11-25 15:00 | 2025-12-09 15:00
HC-GN-290 | Completed | P2543-R01-Oct24..1.PM.1 | Final Issue for Design/ Construction-Smart Plant | HC-GN-330 | HC-GN-330: FS | CAB-5290 | CAB-5290: FS | 2023-12-15 07:30 | 2024-04-22 17:30
HC-GN-300 | Completed | P2543-R01-Oct24..1.PM.1 | Issue ICR-Smart Plant | ML1002 | ML1002: SS 30 | HC-GN-310 | HC-GN-310: FS | 2023-08-18 | 2024-02-09 17:30
HC-GN-310 | Completed | P2543-R01-Oct24..1.PM.1 | Receive Company Comments-Smart Plant | HC-GN-300 | HC-GN-300: FS | HC-GN-320 | HC-GN-320: FS | 2023-09-18 07:30 | 2024-02-23 17:30
HC-GN-320 | Completed | P2543-R01-Oct24..1.PM.1 | Re-Issue for Approval-Smart Plant | HC-GN-310 | HC-GN-310: FS | HC-GN-330 | HC-GN-330: FS | 2023-11-10 07:30 | 2024-03-08 17:30
HC-GN-330 | Completed | P2543-R01-Oct24..1.PM.1 | Obtain Company Approval-Smart Plant | HC-GN-320 | HC-GN-320: FS | HC-GN-290 | HC-GN-290: FS | 2023-11-22 07:30 | 2024-03-22 17:30
HM-PL-0035 | Completed | P2543-R01-Oct24..PR.1.16.2.1 | Complete External / Internal Coating - Lot 1 | HM-PL-0030, HE-PL-3770 | HM-PL-0030: FF 19, HE-PL-3770: FS | HM-PL-0040 | HM-PL-0040: FS | 2024-03-26 | 2024-04-26
HM-PL-970 | Completed | P2543-R01-Oct24..PR.1.16.2.2 | Vendor Document Review of Line Pipes - Lot 2 | HM-PL-0010 | HM-PL-0010: SS | HM-PL-1030, HM-PL-980 | HM-PL-1030: SS, HM-PL-980: FS | 2023-09-12 | 2023-10-20
HM-PL-980 | Completed | P2543-R01-Oct24..PR.1.16.2.2 | Manufacturing & Receive Plates at Fabrication Shop - Lot 2 | HM-PL-0020, HM-PL-970 | HM-PL-0020: FF 10, HM-PL-970: FS | HM-PL-1040, HM-PL-990 | HM-PL-1040: FF 20, HM-PL-990: FS | 2023-11-15 | 2024-01-10
HM-PL-990 | Completed | P2543-R01-Oct24..PR.1.16.2.2 | Complete Line Pipe Production - Lot 2 | HM-PL-980 | HM-PL-980: FS | HM-PL-1020 | HM-PL-1020: FS | 2024-03-30 | 2024-04-19
HM-PL-1000 | Completed | P2543-R01-Oct24..PR.1.16.2.2 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 2 | HM-PL-1020 | HM-PL-1020: FS | HM-PL-1010 | HM-PL-1010: FS | 2024-06-01 | 2024-06-14
HM-PL-1010 | Completed | P2543-R01-Oct24..PR.1.16.2.2 | Ready for Dispatch of Line Pipes (Coated) - Lot 2 | HM-PL-0050, HM-PL-1000 | HM-PL-0050: FF, HM-PL-1000: FS | HM-PL-0090 | HM-PL-0090: FS | 2024-06-14 | 2024-06-14
HM-PL-1020 | Completed | P2543-R01-Oct24..PR.1.16.2.2 | Complete External / Internal Coating - Lot 2 | HM-PL-990 | HM-PL-990: FS | HM-PL-1000 | HM-PL-1000: FS | 2024-04-20 | 2024-05-31
HM-PL-1030 | Completed | P2543-R01-Oct24..PR.1.16.2.3 | Vendor Document Review of Line Pipes - Lot 3 | HM-PL-970 | HM-PL-970: SS | HM-PL-1330, HM-PL-1090, HM-PL-1040 | HM-PL-1330: SS, HM-PL-1090: SS, HM-PL-1040: FS | 2023-09-12 | 2023-10-20
HM-PL-1040 | Completed | P2543-R01-Oct24..PR.1.16.2.3 | Manufacturing & Receive Plates at Fabrication Shop - Lot 3 | HM-PL-980, HM-PL-1030 | HM-PL-980: FF 20, HM-PL-1030: FS | HM-PL-1340, HM-PL-1050 | HM-PL-1340: FF 12, HM-PL-1050: FS | 2023-12-12 | 2024-03-26
HM-PL-1050 | Completed | P2543-R01-Oct24..PR.1.16.2.3 | Complete Line Pipe Production - Lot 3 | HM-PL-1040 | HM-PL-1040: FS | HM-PL-1080 | HM-PL-1080: FS | 2024-03-30 | 2024-04-24
HM-PL-1060 | Completed | P2543-R01-Oct24..PR.1.16.2.3 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 3 | HM-PL-1080 | HM-PL-1080: FF 2 | HM-PL-1070 | HM-PL-1070: FF 2 | 2024-08-01 08:00 | 2024-08-14 18:00
HM-PL-1070 | Completed | P2543-R01-Oct24..PR.1.16.2.3 | Ready for Dispatch of Line Pipes (Coated) - Lot 3 | HM-PL-1060 | HM-PL-1060: FF 2 | HM-PL-0100 | HM-PL-0100: FF 5 | 2024-08-15 08:00 | 2024-08-23 18:00
HM-PL-1080 | Completed | P2543-R01-Oct24..PR.1.16.2.3 | Complete External / Internal Coating - Lot 3 | HM-PL-1050 | HM-PL-1050: FS | HM-PL-1060 | HM-PL-1060: FF 2 | 2024-04-06 | 2024-07-30 18:00
HM-PL-1090 | Completed | P2543-R01-Oct24..PR.1.16.2.4 | Vendor Document Review of Line Pipes - Lot 6 | HM-PL-1030 | HM-PL-1030: SS | HM-PL-1150, HM-PL-1100 | HM-PL-1150: SS, HM-PL-1100: FS | 2023-09-12 | 2023-10-27
HM-PL-1100 | Completed | P2543-R01-Oct24..PR.1.16.2.4 | Manufacturing & Receive Plates at Fabrication Shop - Lot 6 | HM-PL-1280, HM-PL-1090 | HM-PL-1280: FF 20, HM-PL-1090: FS | HM-PL-1160, HM-PL-1110 | HM-PL-1160: FF 25, HM-PL-1110: FS 10 | 2024-03-10 | 2024-04-26
HM-PL-1110 | Completed | P2543-R01-Oct24..PR.1.16.2.4 | Complete Line Pipe Production - Lot 6 | HM-PL-1100 | HM-PL-1100: FS 10 | HM-PL-1140 | HM-PL-1140: FF 28 | 2024-05-27 | 2024-09-02 18:00
HM-PL-1120 | Not Started | P2543-R01-Oct24..PR.1.16.2.4 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 6 | HM-PL-1140, HM-PL-1310 | HM-PL-1140: FS, HM-PL-1310: FF 5 | HM-PL-1130 | HM-PL-1130: FS | 2024-11-05 08:00 | 2024-11-18 18:00
HM-PL-1130 | Not Started | P2543-R01-Oct24..PR.1.16.2.4 | Ready for Dispatch of Line Pipes (Coated) - Lot 6 | HM-PL-1120 | HM-PL-1120: FS | HM-PL-0110 | HM-PL-0110: FS | 2024-11-19 08:00 | 2024-12-01 18:00
HM-PL-1140 | Completed | P2543-R01-Oct24..PR.1.16.2.4 | Complete External / Internal Coating - Lot 6 | HM-PL-1110 | HM-PL-1110: FF 28 | HM-PL-1120 | HM-PL-1120: FS | 2024-07-17 08:00 | 2024-09-06 18:00
HM-PL-1150 | Completed | P2543-R01-Oct24..PR.1.16.2.5 | Vendor Document Review of Line Pipes - Lot 7 | HM-PL-1090 | HM-PL-1090: SS | HM-PL-1390, HM-PL-1210, HM-PL-1160 | HM-PL-1390: SS, HM-PL-1210: SS, HM-PL-1160: FS | 2023-09-12 | 2023-10-27
HM-PL-1160 | Completed | P2543-R01-Oct24..PR.1.16.2.5 | Manufacturing & Receive Plates at Fabrication Shop - Lot 7 | HM-PL-1100, HM-PL-1150 | HM-PL-1100: FF 25, HM-PL-1150: FS | HM-PL-1400, HM-PL-1170 | HM-PL-1400: FF 14, HM-PL-1170: FS | 2024-04-27 | 2024-05-24
HM-PL-1170 | In Progress | P2543-R01-Oct24..PR.1.16.2.5 | Complete Line Pipe Production - Lot 7 | HM-PL-1160 | HM-PL-1160: FS | HM-PL-1200 | HM-PL-1200: FS | 2024-05-24 | 2024-10-30 18:00
HM-PL-1180 | Not Started | P2543-R01-Oct24..PR.1.16.2.5 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 7 | HM-PL-1200 | HM-PL-1200: FS | HM-PL-1190 | HM-PL-1190: FS | 2024-12-10 08:00 | 2024-12-30 18:00
HM-PL-1190 | Not Started | P2543-R01-Oct24..PR.1.16.2.5 | Ready for Dispatch of Line Pipes (Coated) - Lot 7 | HM-PL-1180 | HM-PL-1180: FS | HM-PL-0120, HM-PL-1240 | HM-PL-0120: FS, HM-PL-1240: FS | 2024-12-31 08:00 | 2025-01-11 18:00
HM-PL-1200 | Not Started | P2543-R01-Oct24..PR.1.16.2.5 | Complete External / Internal Coating - Lot 7 | HM-PL-1170 | HM-PL-1170: FS | HM-PL-1180 | HM-PL-1180: FS | 2024-10-31 08:00 | 2024-12-09 18:00
HM-PL-1210 | Completed | P2543-R01-Oct24..PR.1.16.2.6 | Vendor Document Review of Line Pipes - Lot 9 | HM-PL-1150 | HM-PL-1150: SS | HM-PL-1220 | HM-PL-1220: FS | 2023-09-12 | 2024-03-20
HM-PL-1220 | Completed | P2543-R01-Oct24..PR.1.16.2.6 | Manufacturing & Receive Plates at Fabrication Shop - Lot 9 | HM-PL-1400, HM-PL-1210 | HM-PL-1400: FF 21, HM-PL-1210: FS | HM-PL-1230 | HM-PL-1230: FS | 2023-10-28 | 2024-05-15
HM-PL-1230 | Completed | P2543-R01-Oct24..PR.1.16.2.6 | Complete Line Pipe Production - Lot 9 | HM-PL-1220 | HM-PL-1220: FS | HM-PL-1260 | HM-PL-1260: FS | 2024-05-16 08:00 | 2024-07-19 18:00
HM-PL-1240 | Not Started | P2543-R01-Oct24..PR.1.16.2.6 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 9 | HM-PL-1260, HM-PL-1190 | HM-PL-1260: FS, HM-PL-1190: FS | HM-PL-1250 | HM-PL-1250: FS | 2025-01-12 08:00 | 2025-03-01 18:00
HM-PL-1250 | Not Started | P2543-R01-Oct24..PR.1.16.2.6 | Ready for Dispatch of Line Pipes (Coated) - Lot 9 | HM-PL-1260, HM-PL-1240 | HM-PL-1260: FS, HM-PL-1240: FS | HM-PL-960 | HM-PL-960: FF | 2025-03-02 08:00 | 2025-03-26 18:00
HM-PL-1260 | Completed | P2543-R01-Oct24..PR.1.16.2.6 | Complete External / Internal Coating - Lot 9 | HM-PL-1230 | HM-PL-1230: FS | HM-PL-1250, HM-PL-960, HM-PL-1240 | HM-PL-1250: FS, HM-PL-960: FS, HM-PL-1240: FS | 2024-07-20 08:00 | 2024-08-30
HE-IC-2690 | Completed | P2543-R01-Oct24..1.EN.6.A31 | Receive Company Comments- I/O list -Update | HE-IC-2730 | HE-IC-2730: FS | HE-IC-2700 | HE-IC-2700: FS | 2024-02-15 | 2024-02-28
HE-IC-2700 | Completed | P2543-R01-Oct24..1.EN.6.A31 | Re-Issue for Approval- I/O list -Update | HE-IC-2690, HE-IC-2770 | HE-IC-2690: FS, HE-IC-2770: FS | HE-IC-2710 | HE-IC-2710: FS | 2024-02-15 | 2024-02-21
HE-IC-2710 | Completed | P2543-R01-Oct24..1.EN.6.A31 | Obtain Company Approval- I/O list -Update | HE-IC-2700, HE-IC-2780 | HE-IC-2700: FS, HE-IC-2780: FS | HE-IC-2720, HE-IC-0690 | HE-IC-2720: FS, HE-IC-0690: FS | 2024-02-15 | 2024-02-28
HE-IC-2720 | In Progress | P2543-R01-Oct24..1.EN.6.A31 | Final Issue for Design/ Construction-I/O list | HE-IC-2740, HE-IC-2710 | HE-IC-2740: FF, HE-IC-2710: FS | HE-IC-0770 | HE-IC-0770: FS | 2024-10-01 07:30 | 2024-11-08 17:30
HE-IC-2730 | Completed | P2543-R01-Oct24..1.EN.6.A31 | Issue ICR- I/O list -Update | HE-IC-2750 | HE-IC-2750: FS | HE-IC-3190, HE-IC-0610, HE-IC-0910, HE-IC-2690, HS-GN-0310 | HE-IC-3190: FS, HE-IC-0610: FS, HE-IC-0910: FS, HE-IC-2690: FS, HS-GN-0310: FS | 2024-02-15 | 2024-02-28
HE-IC-2740 | In Progress | P2543-R01-Oct24..1.EN.6.A23 | Final Issue for Design/ Construction-F&G Index | HE-IC-2780, HE-IC-0530 | HE-IC-2780: FS, HE-IC-0530: FS | HE-IC-2720 | HE-IC-2720: FF | 2024-09-30 07:30 | 2024-11-08 17:30
HE-IC-2750 | Completed | P2543-R01-Oct24..1.EN.6.A23 | Issue ICR-F&G index -Update | HE-HS-0270, HE-IC-0490, HE-IC-2980 | HE-HS-0270: FS, HE-IC-0490: FS, HE-IC-2980: FS | HE-IC-2730, HE-IC-2760 | HE-IC-2730: FS, HE-IC-2760: FS | 2024-02-06 | 2024-02-12
HE-IC-2760 | Completed | P2543-R01-Oct24..1.EN.6.A23 | Receive Company Comments-F&G index -Update | HE-IC-2750 | HE-IC-2750: FS | HE-IC-2770 | HE-IC-2770: FS | 2024-02-13 | 2024-02-16
HE-IC-2770 | Completed | P2543-R01-Oct24..1.EN.6.A23 | Re-Issue for Approval-F&G index -Update | HE-IC-2760 | HE-IC-2760: FS | HE-IC-2780, HE-IC-2700 | HE-IC-2780: FS, HE-IC-2700: FS | 2024-02-26 | 2024-02-29
HE-IC-2780 | Completed | P2543-R01-Oct24..1.EN.6.A23 | Obtain Company Approval-F&G index -Update | HE-IC-2770, HE-IC-0580 | HE-IC-2770: FS, HE-IC-0580: FS | HE-IC-2740, HE-IC-2710 | HE-IC-2740: FS, HE-IC-2710: FS | 2024-02-16 | 2024-02-26
HE-IC-2790 | Completed | P2543-R01-Oct24..1.EN.6.A181 | Issue ICR - interconnection Wiring Diagram | HE-IC-0610, HS-GN-0410 | HE-IC-0610: FS, HS-GN-0410: FS | HE-IC-2800 | HE-IC-2800: FF 10 | 2024-06-25 07:30 | 2024-09-30 17:30
HE-IC-2800 | In Progress | P2543-R01-Oct24..1.EN.6.A181 | Receive Company Comments - interconnection Wiring Diagram | HE-IC-2790 | HE-IC-2790: FF 10 | HE-IC-2810 | HE-IC-2810: FF 5 | 2024-06-29 07:30 | 2024-11-08 17:30
HE-IC-2810 | In Progress | P2543-R01-Oct24..1.EN.6.A181 | Re-Issue for Approval - interconnection Wiring Diagram | HE-IC-2800 | HE-IC-2800: FF 5 | HE-IC-2820 | HE-IC-2820: FF 10 | 2024-07-13 07:30 | 2024-11-15 17:30
HE-IC-2820 | In Progress | P2543-R01-Oct24..1.EN.6.A181 | Obtain Company Approval - interconnection Wiring Diagram | HE-IC-2810 | HE-IC-2810: FF 10 | HE-IC-2830 | HE-IC-2830: FS | 2024-08-16 07:30 | 2024-11-29 17:30
HE-IC-2830 | Not Started | P2543-R01-Oct24..1.EN.6.A181 | Final Issue for Design/ Construction-interconnection Wiring Diagram | HE-IC-2820 | HE-IC-2820: FS | HE-IC-0770 | HE-IC-0770: FS | 2024-12-04 07:30 | 2024-12-10 17:30
HM-PL-1270 | Completed | P2543-R01-Oct24..PR.1.16.2.8 | Vendor Document Review of Line Pipes - Lot 5 | HM-PL-1330 | HM-PL-1330: SS | HM-PL-1280 | HM-PL-1280: FS | 2023-09-12 | 2023-10-27
HM-PL-1280 | Completed | P2543-R01-Oct24..PR.1.16.2.8 | Manufacturing & Receive Plates at Fabrication Shop - Lot 5 | HM-PL-1340, HM-PL-1270 | HM-PL-1340: FF 13, HM-PL-1270: FS | HM-PL-1100, HM-PL-1290 | HM-PL-1100: FF 20, HM-PL-1290: FS | 2024-04-04 | 2024-04-23
HM-PL-1290 | Completed | P2543-R01-Oct24..PR.1.16.2.8 | Complete Line Pipe Production - Lot 5 | HM-PL-1280 | HM-PL-1280: FS | HM-PL-1320 | HM-PL-1320: FS | 2024-04-29 | 2024-06-14
HM-PL-1300 | Not Started | P2543-R01-Oct24..PR.1.16.2.8 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 5 | HM-PL-1320 | HM-PL-1320: FF 7 | HM-PL-1310 | HM-PL-1310: FF 7 | 2024-10-28 08:00 | 2024-11-06 18:00
HM-PL-1310 | Not Started | P2543-R01-Oct24..PR.1.16.2.8 | Ready for Dispatch of Line Pipes (Coated) - Lot 5 | HM-PL-1300 | HM-PL-1300: FF 7 | HM-PL-1460, HM-PL-1120 | HM-PL-1460: FS, HM-PL-1120: FF 5 | 2024-11-04 08:00 | 2024-11-13 18:00
HM-PL-1320 | In Progress | P2543-R01-Oct24..PR.1.16.2.8 | Complete External / Internal Coating - Lot 5 | HM-PL-1290 | HM-PL-1290: FS | HM-PL-1300 | HM-PL-1300: FF 7 | 2024-09-20 08:00 | 2024-10-30 18:00
HM-PL-1330 | Completed | P2543-R01-Oct24..PR.1.16.2.7 | Vendor Document Review of Line Pipes - Lot 4 | HM-PL-1030 | HM-PL-1030: SS | HM-PL-1270, HM-PL-1340 | HM-PL-1270: SS, HM-PL-1340: FS | 2023-09-12 | 2023-10-27
HM-PL-1340 | Completed | P2543-R01-Oct24..PR.1.16.2.7 | Manufacturing & Receive Plates at Fabrication Shop - Lot 4 | HM-PL-1040, HM-PL-1330 | HM-PL-1040: FF 12, HM-PL-1330: FS | HM-PL-1280, HM-PL-1350 | HM-PL-1280: FF 13, HM-PL-1350: FS | 2024-01-25 | 2024-03-20
HM-PL-1350 | Completed | P2543-R01-Oct24..PR.1.16.2.7 | Complete Line Pipe Production - Lot 4 | HM-PL-1340 | HM-PL-1340: FS | HM-PL-1380 | HM-PL-1380: FS | 2024-03-25 | 2024-05-31
HM-PL-1360 | Completed | P2543-R01-Oct24..PR.1.16.2.7 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 4 | HM-PL-1380 | HM-PL-1380: FS | HM-PL-1370 | HM-PL-1370: FS | 2024-07-10 08:00 | 2024-07-26 18:00
HM-PL-1370 | Completed | P2543-R01-Oct24..PR.1.16.2.7 | Ready for Dispatch of Line Pipes (Coated) - Lot 4 | HM-PL-1360 | HM-PL-1360: FS | HM-PL-1450 | HM-PL-1450: FF 15 | 2024-07-23 08:00 | 2024-07-30 18:00
HM-PL-1380 | Completed | P2543-R01-Oct24..PR.1.16.2.7 | Complete External / Internal Coating - Lot 4 | HM-PL-1350 | HM-PL-1350: FS | HM-PL-1360 | HM-PL-1360: FS | 2024-05-30 | 2024-07-25 18:00
HM-PL-1390 | Completed | P2543-R01-Oct24..PR.1.16.2.9 | Vendor Document Review of Line Pipes - Lot 8 | HM-PL-1150 | HM-PL-1150: SS | HM-PL-1400 | HM-PL-1400: FS | 2023-09-12 | 2023-10-27
HM-PL-1400 | Completed | P2543-R01-Oct24..PR.1.16.2.9 | Manufacturing & Receive Plates at Fabrication Shop - Lot 8 | HM-PL-1160, HM-PL-1390 | HM-PL-1160: FF 14, HM-PL-1390: FS | HM-PL-1220, HM-PL-1410 | HM-PL-1220: FF 21, HM-PL-1410: FS | 2023-10-28 | 2024-05-15
HM-PL-1410 | Completed | P2543-R01-Oct24..PR.1.16.2.9 | Complete Line Pipe Production - Lot 8 | HM-PL-1400 | HM-PL-1400: FS | HM-PL-1440 | HM-PL-1440: FS | 2024-05-16 | 2024-06-14
HM-PL-1420 | Completed | P2543-R01-Oct24..PR.1.16.2.9 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 8 | HM-PL-1440 | HM-PL-1440: FS | HM-PL-1430 | HM-PL-1430: FS | 2024-07-20 08:00 | 2024-08-26
HM-PL-1430 | Completed | P2543-R01-Oct24..PR.1.16.2.9 | Ready for Dispatch of Line Pipes (Coated) - Lot 8 | HM-PL-1420 | HM-PL-1420: FS | HM-PL-1470 | HM-PL-1470: FS | 2024-08-27 08:00 | 2024-08-30 18:00
HM-PL-1440 | Completed | P2543-R01-Oct24..PR.1.16.2.9 | Complete External / Internal Coating - Lot 8 | HM-PL-1410 | HM-PL-1410: FS | HM-PL-1420 | HM-PL-1420: FS | 2024-06-21 | 2024-07-19 18:00
HM-PL-1450 | Completed | P2543-R01-Oct24..PR.1.16.3 | Receipt at site and inspection of Line Pipes - Lot 4 (Coated) | HM-PL-1370 | HM-PL-1370: FF 15 | ML1509-D3 | ML1509-D3: FF | 2024-07-24 08:00 | 2024-09-13 18:00
HM-PL-1460 | Not Started | P2543-R01-Oct24..PR.1.16.3 | Receipt at site and inspection of Line Pipes - Lot 5 (Coated) | HM-PL-1310 | HM-PL-1310: FS | C-52-0405-PL-ME-2800, C-56-HC01-PL-ME-2800 | C-52-0405-PL-ME-2800: FF, C-56-HC01-PL-ME-2800: FF 21 | 2024-11-14 08:00 | 2024-11-26 18:00
HM-PL-1470 | Not Started | P2543-R01-Oct24..PR.1.16.3 | Receipt at site and inspection of Line Pipes - Lot 8 (Coated) | HM-PL-1430, HM-PL-0120 | HM-PL-1430: FS, HM-PL-0120: FS | HM-PL-960 | HM-PL-960: FF | 2025-02-06 08:00 | 2025-03-15 18:00
HE-PL-3530 | Completed | P2543-R01-Oct24..1.EN.1.11 | Issue ICR - Pipeline Alignment Sheets-4" | HE-TS-0010, HE-TS-330 | HE-TS-0010: FS 60, HE-TS-330: FS 60 | HE-PL-3110, HE-PL-3540, HE-PL-3170, HE-PL-2750 | HE-PL-3110: FS, HE-PL-3540: FS, HE-PL-3170: FS, HE-PL-2750: FS | 2024-02-26 | 2024-03-08
HE-PL-3540 | Completed | P2543-R01-Oct24..1.EN.1.11 | Receive Company Comments - Pipeline Alignment Sheets-4" | HE-PL-3530 | HE-PL-3530: FS | HE-PL-3550 | HE-PL-3550: FS | 2024-03-10 | 2024-03-25
HE-PL-3550 | Completed | P2543-R01-Oct24..1.EN.1.11 | Re-Issue for Approval - Pipeline Alignment Sheets-4" | HE-PL-3540 | HE-PL-3540: FS | HE-PL-3560, HE-PL-3110 | HE-PL-3560: FS, HE-PL-3110: FS | 2024-03-26 | 2024-04-07
HE-PL-3560 | Completed | P2543-R01-Oct24..1.EN.1.11 | Obtain Company Approval - Pipeline Alignment Sheets-4" | HE-PL-3550 | HE-PL-3550: FS | HE-PL-3570 | HE-PL-3570: FS | 2024-04-12 | 2024-04-25
HE-PL-3570 | Not Started | P2543-R01-Oct24..1.EN.1.11 | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | HE-PL-3560, HE-TS-320, HE-GS-180 | HE-PL-3560: FS, HE-TS-320: FS, HE-GS-180: FS | C-4N-H5HG-PIPEL-2400, ML1219-B59, CAB-4480, C-PER-1560, C-PER-1570 | C-4N-H5HG-PIPEL-2400: FS, ML1219-B59: FF, CAB-4480: FS, C-PER-1560: FS, C-PER-1570: FS | 2024-10-28 07:30 | 2024-11-01 17:30
HE-PL-3580 | Completed | P2543-R01-Oct24..1.EN.1.12 | Issue ICR - Pipeline Station Approach drawing -4" | HE-PI-0460, HE-TS-0010, HE-PL-2510, HE-TS-330 | HE-PI-0460: FS, HE-TS-0010: FS, HE-PL-2510: FS, HE-TS-330: FS | HE-PL-3590 | HE-PL-3590: FS | 2024-03-29 07:30 | 2024-05-14 17:30
HE-PL-3590 | Completed | P2543-R01-Oct24..1.EN.1.12 | Receive Company Comments - Pipeline Station Approach drawing -4" | HE-PL-3580 | HE-PL-3580: FS | HE-PL-3600 | HE-PL-3600: FS | 2024-05-15 07:30 | 2024-05-29 17:30
HE-PL-3600 | Completed | P2543-R01-Oct24..1.EN.1.12 | Re-Issue for Approval - Pipeline Station Approach drawing -4" | HE-PL-3590 | HE-PL-3590: FS | HE-PL-3610 | HE-PL-3610: FS | 2024-05-30 07:30 | 2024-09-02
HE-PL-3610 | Completed | P2543-R01-Oct24..1.EN.1.12 | Obtain Company Approval - Pipeline Station Approach drawing -4" | HE-PL-3600 | HE-PL-3600: FS | HE-PL-3620 | HE-PL-3620: FS | 2024-09-03 07:30 | 2024-09-13 17:30
HE-PL-3620 | Not Started | P2543-R01-Oct24..1.EN.1.12 | Final Issue for Design/ Construction-Pipeline Station approach drawing-4" | HE-PL-3610 | HE-PL-3610: FS | CAB-4480, ML1059-B28 | CAB-4480: FS, ML1059-B28: FF | 2024-10-28 07:30 | 2024-11-01 17:30
HM-ME-2140 | Not Started | P2543-R01-Oct24..PR.26.1.25.2 | Manufacturing & Assembly of LV Lifting Equipment | HM-ME-2180 | HM-ME-2180: FS | HM-ME-2150 | HM-ME-2150: FS | 2024-11-25 08:00 | 2025-02-22 18:00
HM-ME-2150 | Not Started | P2543-R01-Oct24..PR.26.1.25.2 | Factory Acceptance Test of LV Lifting Equipment | HM-ME-2140 | HM-ME-2140: FS | HM-ME-2160 | HM-ME-2160: FS | 2025-02-23 08:00 | 2025-03-15 18:00
HM-ME-2160 | Not Started | P2543-R01-Oct24..PR.26.1.25.2 | Packaging & Final Inspection-LV Lifting Equipment | HM-ME-2150 | HM-ME-2150: FS | HM-ME-2170 | HM-ME-2170: FS | 2025-03-16 08:00 | 2025-03-29 18:00
HM-ME-2170 | Not Started | P2543-R01-Oct24..PR.26.1.25.2 | Ready for Dispatch of LV Lifting Equipment | HM-ME-2160 | HM-ME-2160: FS | HM-ME-2190 | HM-ME-2190: FS | 2025-03-30 08:00 | 2025-04-12 18:00
HM-ME-2180 | In Progress | P2543-R01-Oct24..PR.26.1.25.2 | Vendor Document Review of Lifting Equipment | HP-ME-1370 | HP-ME-1370: FS | HM-ME-2140 | HM-ME-2140: FS | 2024-08-26 17:30 | 2024-11-24 18:00
HM-ME-2190 | Not Started | P2543-R01-Oct24..PR.26.1.25.3 | Transportation/ Custom Clearance/ Delivery at site of Lifting Equipment | HM-ME-2170 | HM-ME-2170: FS | HM-ME-2200 | HM-ME-2200: FS | 2025-04-13 08:00 | 2025-05-03 18:00
HM-ME-2200 | Not Started | P2543-R01-Oct24..PR.26.1.25.3 | Receipt at site and inspection of Lifting Equipment | HM-ME-2190 | HM-ME-2190: FS | C-56-591-01-PI-1800, C-56-591-01-PI-2000, C-DBV6-PI-1000 | C-56-591-01-PI-1800: FS, C-56-591-01-PI-2000: FS, C-DBV6-PI-1000: FS | 2025-05-04 07:00 | 2025-05-12 15:00
HE-CS-1810 | Completed | P2543-R01-Oct24..1.EN.8.7 | Re-Issue for Approval - Calculations for Shelter | HE-CS-1850 | HE-CS-1850: FS | HE-CS-1820 | HE-CS-1820: FS | 2023-12-29 | 2024-01-15
HE-CS-1820 | Completed | P2543-R01-Oct24..1.EN.8.7 | Obtain Company Approval - Calculations for Shelter | HE-CS-1810 | HE-CS-1810: FS | HE-CS-1830 | HE-CS-1830: FS | 2024-01-16 | 2024-07-26 07:30
HE-CS-1830 | In Progress | P2543-R01-Oct24..1.EN.8.7 | Final Issue for Design/ Construction-Design Calculation for Shelter | HE-CS-1820 | HE-CS-1820: FS | HE-CS-1310 | HE-CS-1310: FS | 2024-09-19 07:30 | 2024-11-11 17:30
HE-CS-1840 | Completed | P2543-R01-Oct24..1.EN.8.7 | Issued for Review - Calculations for Shelter | HE-CS-0790 | HE-CS-0790: FF | HE-CS-1850, HE-CS-1890, HE-CS-1270 | HE-CS-1850: FS, HE-CS-1890: SS 5, HE-CS-1270: FS | 2023-11-27 | 2023-12-12
HE-CS-1850 | Completed | P2543-R01-Oct24..1.EN.8.7 | Review Company Comments - Calculations for Shelter | HE-CS-1840 | HE-CS-1840: FS | HE-CS-1810 | HE-CS-1810: FS | 2023-12-13 | 2023-12-25
HE-CS-1860 | Completed | P2543-R01-Oct24..1.EN.8.8 | Re-Issue for Approval - Calculations for Valve Pit | HE-CS-1900 | HE-CS-1900: FS | HE-CS-1870 | HE-CS-1870: FS | 2024-08-12 07:30 | 2024-09-02 17:30
HE-CS-1870 | Completed | P2543-R01-Oct24..1.EN.8.8 | Obtain Company Approval - Calculations for Valve Pit | HE-CS-1860 | HE-CS-1860: FS | HE-CS-1880 | HE-CS-1880: FS | 2024-09-03 07:30 | 2024-09-22 17:30
HE-CS-1880 | In Progress | P2543-R01-Oct24..1.EN.8.8 | Final Issue for Design/ Construction-Design Calculation for Valve Pit | HE-CS-1870 | HE-CS-1870: FS | HE-CS-1190 | HE-CS-1190: FF | 2024-09-30 07:30 | 2024-11-01 17:30
HE-CS-1890 | Completed | P2543-R01-Oct24..1.EN.8.8 | Issued for Review - Calculations for Valve Pit | HE-CS-1840 | HE-CS-1840: SS 5 | HE-CS-1900, HE-CS-1940 | HE-CS-1900: FS, HE-CS-1940: FS 5 | 2024-04-23 | 2024-05-07
HE-CS-1900 | Completed | P2543-R01-Oct24..1.EN.8.8 | Review Company Comments - Calculations for Valve Pit | HE-CS-1890 | HE-CS-1890: FS | HE-CS-1860 | HE-CS-1860: FS | 2024-07-29 07:30 | 2024-08-09 17:30
HE-CS-1910 | Completed | P2543-R01-Oct24..1.EN.8.10 | Re-Issue for Approval - Calculations for Impact Wall | HE-CS-1950 | HE-CS-1950: FS | HE-CS-1920 | HE-CS-1920: FS | 2024-06-08 | 2024-06-14
HE-CS-1920 | Completed | P2543-R01-Oct24..1.EN.8.10 | Obtain Company Approval - Calculations for Impact Wall | HE-CS-1910 | HE-CS-1910: FS | HE-CS-1930 | HE-CS-1930: FS | 2024-06-21 | 2024-08-09 17:30
HE-CS-1930 | In Progress | P2543-R01-Oct24..1.EN.8.10 | Final Issue for Design/ Construction-Design Calculation for Impact Wall | HE-CS-1920 | HE-CS-1920: FS | HE-CS-1250 | HE-CS-1250: FF | 2024-09-30 07:30 | 2024-11-01 17:30
HE-CS-1940 | Completed | P2543-R01-Oct24..1.EN.8.10 | Issued for Review - Calculations for Impact Wall | HE-CS-1890 | HE-CS-1890: FS 5 | HE-CS-1950, HE-CS-1210 | HE-CS-1950: FS, HE-CS-1210: FS | 2024-03-29 | 2024-05-03
HE-CS-1950 | Completed | P2543-R01-Oct24..1.EN.8.10 | Review Company Comments - Calculations for Impact Wall | HE-CS-1940 | HE-CS-1940: FS | HE-CS-1910 | HE-CS-1910: FS | 2024-05-16 | 2024-06-07
HE-CS-1960 | Completed | P2543-R01-Oct24..1.EN.8.18 | Re-Issue for Approval - Design Cal. for Jib Crane Foundations | HE-CS-2000 | HE-CS-2000: FS | HE-CS-1970 | HE-CS-1970: FS | 2024-09-30 07:30 | 2024-10-04 17:30
HE-CS-1970 | Completed | P2543-R01-Oct24..1.EN.8.18 | Obtain Company Approval - Design Cal. for Jib Crane Foundations | HE-CS-1960 | HE-CS-1960: FS | HE-CS-1980 | HE-CS-1980: FS | 2024-10-04 07:30 | 2024-10-23 17:30
HE-CS-1980 | Not Started | P2543-R01-Oct24..1.EN.8.18 | Final Issue for Design/ Construction-Design Calculation for Jib Crane Foundations | HE-CS-1970 | HE-CS-1970: FS | HE-CS-0890 | HE-CS-0890: FF | 2024-10-28 07:30 | 2024-11-08 17:30
HE-CS-1990 | Completed | P2543-R01-Oct24..1.EN.8.18 | Issued for Review - Design Cal. for Jib Crane Foundations | HE-CS-2090 | HE-CS-2090: FS 30 | HE-CS-2000, HE-CS-2040, HE-CS-1030 | HE-CS-2000: FS, HE-CS-2040: SS 5, HE-CS-1030: FF 20 | 2024-04-22 | 2024-04-23
HE-CS-2000 | Completed | P2543-R01-Oct24..1.EN.8.18 | Review Company Comments - Design Cal. for Jib Crane Foundations | HE-CS-1990 | HE-CS-1990: FS | HE-CS-1960 | HE-CS-1960: FS | 2024-04-23 | 2024-05-06 17:30
HE-CS-2010 | Completed | P2543-R01-Oct24..1.EN.8.19 | Re-Issue for Approval - Design Cal. for Filter Package | HE-CS-2050 | HE-CS-2050: FS | HE-CS-2020 | HE-CS-2020: FS | 2024-09-09 07:30 | 2024-09-16 17:30
HE-CS-2020 | Completed | P2543-R01-Oct24..1.EN.8.19 | Obtain Company Approval - Design Cal. for Filter Package | HE-CS-2010 | HE-CS-2010: FS | HE-CS-2030 | HE-CS-2030: FS | 2024-09-17 | 2024-09-30 17:30
HE-CS-2030 | In Progress | P2543-R01-Oct24..1.EN.8.19 | Final Issue for Design/ Construction-Design Calculation for Filter Package | HE-CS-2020 | HE-CS-2020: FS | HE-CS-0950 | HE-CS-0950: FF | 2024-10-01 07:30 | 2024-11-04 17:30
HE-CS-2040 | Completed | P2543-R01-Oct24..1.EN.8.19 | Issued for Review - Design Cal. for Filter Package | HE-CS-1990 | HE-CS-1990: SS 5 | HE-CS-2050, HE-CS-0910 | HE-CS-2050: FS, HE-CS-0910: FS | 2024-02-24 | 2024-03-15
HE-CS-2050 | Completed | P2543-R01-Oct24..1.EN.8.19 | Review Company Comments - Design Cal. for Filter Package | HE-CS-2040 | HE-CS-2040: FS | HE-CS-2010 | HE-CS-2010: FS | 2024-03-16 | 2024-03-28 17:30
HE-CS-2060 | Not Started | P2543-R01-Oct24..1.EN.8.26 | Re-Issue for Approval - Design Cal. for Typical Lighting Pole Foundations | HE-CS-2100 | HE-CS-2100: FS | HE-CS-2070 | HE-CS-2070: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HE-CS-2070 | Not Started | P2543-R01-Oct24..1.EN.8.26 | Obtain Company Approval - Design Cal. for Typical Lighting Pole Foundations | HE-CS-2060 | HE-CS-2060: FS | HE-CS-2080 | HE-CS-2080: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-CS-2080 | Not Started | P2543-R01-Oct24..1.EN.8.26 | Final Issue for Design/ Construction-Design Calculation for Typical Lighting Pole Foundations | HE-CS-2070 | HE-CS-2070: FS | HE-CS-1010 | HE-CS-1010: FF | 2024-11-25 07:30 | 2024-12-10 17:30
HE-CS-2090 | Completed | P2543-R01-Oct24..1.EN.8.26 | Issued for Review - Design Cal. for Typical Lighting Pole Foundations | HE-CS-0670 | HE-CS-0670: SS 5 | HE-CS-2100, HE-CS-1990, HE-CS-0970 | HE-CS-2100: FS, HE-CS-1990: FS 30, HE-CS-0970: FS | 2024-02-07 | 2024-03-21
HE-CS-2100 | Completed | P2543-R01-Oct24..1.EN.8.26 | Review Company Comments - Design Cal. for Typical Lighting Pole Foundations | HE-CS-2090 | HE-CS-2090: FS | HE-CS-2060 | HE-CS-2060: FS | 2024-03-21 07:30 | 2024-04-02 17:30
HE-IC-2840 | Completed | P2543-R01-Oct24..1.EN.6.11.1 | Receive Company Comments- Material Requisitions for RTU & SCADA Modification | HE-IC-2880 | HE-IC-2880: FS | HE-IC-2850 | HE-IC-2850: FS | 2024-02-26 | 2024-03-08
HE-IC-2850 | Completed | P2543-R01-Oct24..1.EN.6.11.1 | Re-Issue for Approval- Material Requisitions for RTU & SCADA Modification | HE-IC-2840 | HE-IC-2840: FS | HE-IC-2870 | HE-IC-2870: FS | 2024-03-10 | 2024-04-05
HE-IC-2860 | Completed | P2543-R01-Oct24..1.EN.6.11.1 | Final Issue for Design/ Construction-Material Requisitions for RTU & SCADA Modification | HE-IC-2870 | HE-IC-2870: FS | HE-IC-2890 | HE-IC-2890: FS | 2024-06-26 07:30 | 2024-08-14 17:30
HE-IC-2870 | Completed | P2543-R01-Oct24..1.EN.6.11.1 | Obtain Company Approval- Material Requisitions for RTU & SCADA Modification | HE-IC-2850 | HE-IC-2850: FS | HE-IC-2860 | HE-IC-2860: FS | 2024-04-08 | 2024-04-12
HE-IC-2880 | Completed | P2543-R01-Oct24..1.EN.6.11.1 | Issue ICR- Material Requisitions for RTU & SCADA Modification | HE-IC-0550, HE-IC-0190 | HE-IC-0550: FS, HE-IC-0190: FS | HE-IC-2840, HS-GN-0370 | HE-IC-2840: FS, HS-GN-0370: FS | 2024-01-29 | 2024-02-02
HE-IC-2890 | In Progress | P2543-R01-Oct24..1.EN.6.2.1 | Final Issue for Design/ Construction-TBE for RTU & SCADA Modification | HE-IC-2930, HE-IC-2860 | HE-IC-2930: FS, HE-IC-2860: FS | C-COM-790 | C-COM-790: FS | 2024-07-04 07:30 | 2024-11-01 17:30
HE-IC-2900 | Completed | P2543-R01-Oct24..1.EN.6.2.1 | Issue ICR- TBE for RTU & SCADA Modification | HS-GN-0370 | HS-GN-0370: FS | HE-IC-2910 | HE-IC-2910: FS | 2024-05-13 | 2024-05-20
HE-IC-2910 | Completed | P2543-R01-Oct24..1.EN.6.2.1 | Receive Company Comments- TBE for RTU & SCADA Modification | HE-IC-2900 | HE-IC-2900: FS | HE-IC-2920 | HE-IC-2920: FS | 2024-05-21 | 2024-06-10
HE-IC-2920 | Completed | P2543-R01-Oct24..1.EN.6.2.1 | Re-Issue for Approval- TBE for RTU & SCADA Modification | HE-IC-2910 | HE-IC-2910: FS | HE-IC-2930 | HE-IC-2930: FS | 2024-06-11 | 2024-06-14
HE-IC-2930 | Completed | P2543-R01-Oct24..1.EN.6.2.1 | Obtain Company Approval- TBE for RTU & SCADA Modification | HE-IC-2920 | HE-IC-2920: FS | HE-IC-2890 | HE-IC-2890: FS | 2024-06-17 07:30 | 2024-06-28 17:30
HE-TL-940 | Completed | P2543-R01-Oct24..1.EN.10.A321 | Issue ICR- Telecom Equipment List | HE-TL-0310 | HE-TL-0310: FF | HE-TL-950 | HE-TL-950: FS | 2023-11-21 | 2023-12-25
HE-TL-950 | Completed | P2543-R01-Oct24..1.EN.10.A321 | Receive Company Comments- Telecom Equipment List | HE-TL-940 | HE-TL-940: FS | HE-TL-960 | HE-TL-960: FS | 2023-12-25 | 2024-01-15
HE-TL-960 | Completed | P2543-R01-Oct24..1.EN.10.A321 | Re-Issue for Approval-Telecom Equipment List | HE-TL-950 | HE-TL-950: FS | HE-TL-970 | HE-TL-970: FS | 2024-01-19 | 2024-01-23
HE-TL-970 | Completed | P2543-R01-Oct24..1.EN.10.A321 | Obtain Company Approval- Telecom Equipment List | HE-TL-960 | HE-TL-960: FS | HE-TL-980 | HE-TL-980: FS | 2024-01-19 | 2024-01-23
HE-TL-980 | Completed | P2543-R01-Oct24..1.EN.10.A321 | Final Issue for Design/ Construction-Telecom Equipment List | HE-TL-970, HE-TL-0230 | HE-TL-970: FS, HE-TL-0230: FS | HE-TL-0470, HE-TL-0610 | HE-TL-0470: FS, HE-TL-0610: FS | 2024-01-23 | 2024-02-12
HE-TL-990 | Completed | P2543-R01-Oct24..1.EN.10.A2112 | Final Issue for Design/ Construction-Telecom Inter Connection Diagram | HE-TL-1030 | HE-TL-1030: FS | HE-TL-1040, C-COM-750 | HE-TL-1040: FS, C-COM-750: FS | 2024-01-24 | 2024-02-23
HE-TL-1000 | Completed | P2543-R01-Oct24..1.EN.10.A2112 | Issue ICR- Telecom Inter Connection Diagram | HE-TL-0310 | HE-TL-0310: SS 3 | HE-TL-1010, HE-TL-1050 | HE-TL-1010: FS, HE-TL-1050: SS 3 | 2023-11-17 | 2023-12-13
HE-TL-1010 | Completed | P2543-R01-Oct24..1.EN.10.A2112 | Receive Company Comments- Telecom Inter Connection Diagram | HE-TL-1000 | HE-TL-1000: FS | HE-TL-1020 | HE-TL-1020: FS | 2023-12-13 | 2023-12-27
HE-TL-1020 | Completed | P2543-R01-Oct24..1.EN.10.A2112 | Re-Issue for Approval- Telecom Inter Connection Diagram | HE-TL-1010 | HE-TL-1010: FS | HE-TL-1030 | HE-TL-1030: FS | 2023-12-27 | 2024-01-10
HE-TL-1030 | Completed | P2543-R01-Oct24..1.EN.10.A2112 | Obtain Company Approval- Telecom Inter Connection Diagram | HE-TL-1020 | HE-TL-1020: FS | HE-TL-990 | HE-TL-990: FS | 2024-01-10 | 2024-01-24
HE-TL-1040 | Completed | P2543-R01-Oct24..1.EN.10.A21121 | Final Issue for Design/ Construction-Typical Inter Connection Diagram for Pig Launcher/Receiver | HE-TL-1080, HE-TL-990, HE-TL-0230 | HE-TL-1080: FS, HE-TL-990: FS, HE-TL-0230: SS | HE-TL-1090, C-COM-750 | HE-TL-1090: FS, C-COM-750: FS | 2024-01-11 | 2024-02-23
HE-TL-1050 | Completed | P2543-R01-Oct24..1.EN.10.A21121 | Issue ICR- Typical Inter Connection Diagram for Pig Launcher/Receiver | HE-TL-1000, HE-TL-2470 | HE-TL-1000: SS 3, HE-TL-2470: FS | HE-TL-1060, HE-TL-1100, HE-TL-1150 | HE-TL-1060: FS, HE-TL-1100: SS 5, HE-TL-1150: FS | 2023-11-19 | 2023-11-29
HE-TL-1060 | Completed | P2543-R01-Oct24..1.EN.10.A21121 | Receive Company Comments- Typical Inter Connection Diagram for Pig Launcher/Receiver | HE-TL-1050 | HE-TL-1050: FS | HE-TL-1070 | HE-TL-1070: FS | 2023-11-30 | 2023-12-13
HE-TL-1070 | Completed | P2543-R01-Oct24..1.EN.10.A21121 | Re-Issue for Approval- Typical Inter Connection Diagram for Pig Launcher/Receiver | HE-TL-1060 | HE-TL-1060: FS | HE-TL-1080 | HE-TL-1080: FS | 2023-12-14 | 2023-12-27
HE-TL-1080 | Completed | P2543-R01-Oct24..1.EN.10.A21121 | Obtain Company Approval- Typical Inter Connection Diagram for Pig Launcher/Receiver | HE-TL-1070 | HE-TL-1070: FS | HE-TL-1040 | HE-TL-1040: FS | 2023-12-28 | 2024-01-10
HE-TL-1090 | Not Started | P2543-R01-Oct24..1.EN.10.A211211 | Final Issue for Design/ Construction- Fiber Core Allocation Diagram | HE-TL-1130, HE-TL-1040 | HE-TL-1130: FS, HE-TL-1040: FS | HE-TL-1140 | HE-TL-1140: FF | 2024-11-18 07:30 | 2024-11-22 17:30
HE-TL-1100 | Completed | P2543-R01-Oct24..1.EN.10.A211211 | Issue ICR- Fiber Core Allocation Diagram | HE-TL-1050 | HE-TL-1050: SS 5 | HE-TL-1110 | HE-TL-1110: FS | 2024-08-16 07:30 | 2024-08-23 17:30
HE-TL-1110 | Completed | P2543-R01-Oct24..1.EN.10.A211211 | Receive Company Comments- Fiber Core Allocation Diagram | HE-TL-1100 | HE-TL-1100: FS | HE-TL-1120 | HE-TL-1120: FS | 2024-08-26 07:30 | 2024-09-23 17:30
HE-TL-1120 | Not Started | P2543-R01-Oct24..1.EN.10.A211211 | Re-Issue for Approval- Fiber Core Allocation Diagram | HE-TL-1110 | HE-TL-1110: FS | HE-TL-1130 | HE-TL-1130: FS | 2024-10-28 07:30 | 2024-11-01 17:30
HE-TL-1130 | Not Started | P2543-R01-Oct24..1.EN.10.A211211 | Obtain Company Approval- Fiber Core Allocation Diagram | HE-TL-1120 | HE-TL-1120: FS | HE-TL-1090 | HE-TL-1090: FS | 2024-11-04 07:30 | 2024-11-15 17:30
HE-TL-1140 | In Progress | P2543-R01-Oct24..1.EN.10.A2112111 | Final Issue for Design/ Construction-Optical Power Link Loss Calculation For SDH / FOC System | HE-TL-1180, HE-TL-1190, HE-TL-1240, HE-TL-1090 | HE-TL-1180: FS, HE-TL-1190: FS, HE-TL-1240: FS, HE-TL-1090: FF | HE-TL-0650 | HE-TL-0650: FS | 2024-09-30 07:30 | 2024-11-22 17:30
HE-TL-1150 | Completed | P2543-R01-Oct24..1.EN.10.A2112111 | Issue ICR- Optical Power Link Loss Calculation For SDH / FOC System | HE-TL-1050 | HE-TL-1050: FS | HE-TL-1160 | HE-TL-1160: FS | 2024-01-08 | 2024-01-18
HE-TL-1160 | Completed | P2543-R01-Oct24..1.EN.10.A2112111 | Receive Company Comments- Optical Power Link Loss Calculation For SDH / FOC System | HE-TL-1150 | HE-TL-1150: FS | HE-TL-1170 | HE-TL-1170: FS | 2024-01-19 | 2024-02-12
HE-TL-1170 | Completed | P2543-R01-Oct24..1.EN.10.A2112111 | Re-Issue for Approval- Optical Power Link Loss Calculation For SDH / FOC System | HE-TL-1160 | HE-TL-1160: FS | HE-TL-1180 | HE-TL-1180: FS | 2024-02-13 | 2024-02-23
HE-TL-1180 | Completed | P2543-R01-Oct24..1.EN.10.A2112111 | Obtain Company Approval- Optical Power Link Loss Calculation For SDH / FOC System | HE-TL-1170 | HE-TL-1170: FS | HE-TL-1140 | HE-TL-1140: FS | 2024-02-24 | 2024-03-07
HE-TL-1190 | Completed | P2543-R01-Oct24..1.EN.10.A21121111 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | HE-TL-1230 | HE-TL-1230: FS | HE-TL-1140, C-COM-750 | HE-TL-1140: FS, C-COM-750: FS | 2023-12-02 | 2024-01-05
HE-TL-1200 | Completed | P2543-R01-Oct24..1.EN.10.A21121111 | Issue ICR- Overall Telecom Block Diagram | HE-TL-0310 | HE-TL-0310: FS | HE-TL-1210 | HE-TL-1210: FS | 2023-09-09 | 2023-09-22
HE-TL-1210 | Completed | P2543-R01-Oct24..1.EN.10.A21121111 | Receive Company Comments- Overall Telecom Block Diagram | HE-TL-1200 | HE-TL-1200: FS | HE-TL-1220 | HE-TL-1220: FS | 2023-09-23 | 2023-10-09
HE-TL-1220 | Completed | P2543-R01-Oct24..1.EN.10.A21121111 | Re-Issue for Approval- Overall Telecom Block Diagram | HE-TL-1210 | HE-TL-1210: FS | HE-TL-1230 | HE-TL-1230: FS | 2023-10-10 | 2023-11-03
HE-TL-1230 | Completed | P2543-R01-Oct24..1.EN.10.A21121111 | Obtain Company Approval- Overall Telecom Block Diagram | HE-TL-1220 | HE-TL-1220: FS | HE-TL-1190 | HE-TL-1190: FS | 2023-11-06 | 2023-11-14
HE-TL-1240 | Completed | P2543-R01-Oct24..1.EN.10.A211211111 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | HE-TL-1280 | HE-TL-1280: FS | HE-TL-1140 | HE-TL-1140: FS | 2024-01-06 07:30 | 2024-02-04 07:30
HE-TL-1250 | Completed | P2543-R01-Oct24..1.EN.10.A211211111 | Issue ICR- Overall Telecom Block Diagram | HE-TL-0070 | HE-TL-0070: FS | HE-TL-1260 | HE-TL-1260: FS | 2023-11-16 | 2023-11-24
HE-TL-1260 | Completed | P2543-R01-Oct24..1.EN.10.A211211111 | Receive Company Comments- Overall Telecom Block Diagram | HE-TL-1250 | HE-TL-1250: FS | HE-TL-1270 | HE-TL-1270: FS | 2023-11-24 07:30 | 2023-12-12 07:30
HE-TL-1270 | Completed | P2543-R01-Oct24..1.EN.10.A211211111 | Re-Issue for Approval- Overall Telecom Block Diagram | HE-TL-1260 | HE-TL-1260: FS | HE-TL-1280 | HE-TL-1280: FS | 2023-12-23 07:30 | 2024-01-05 07:30
HE-TL-1280 | Completed | P2543-R01-Oct24..1.EN.10.A211211111 | Obtain Company Approval- Overall Telecom Block Diagram | HE-TL-1270 | HE-TL-1270: FS | HE-TL-1240 | HE-TL-1240: FS | 2023-12-13 07:30 | 2023-12-22 07:30
HC-GN-340 | Completed | P2543-R01-Oct24..1.PM.7 | Issue ICR-Hot Tap SOW | HE-PL-0430 | HE-PL-0430: FS | HC-GN-350 | HC-GN-350: FS | 2023-11-01 | 2023-11-10
HC-GN-350 | Completed | P2543-R01-Oct24..1.PM.7 | Receive Company Comments-Hot Tap SOW | HC-GN-340 | HC-GN-340: FS | HC-GN-360 | HC-GN-360: FS | 2023-11-13 | 2023-11-22
HC-GN-360 | Completed | P2543-R01-Oct24..1.PM.7 | Re-Issue for Approval-Hot Tap SOW | HC-GN-350 | HC-GN-350: FS | HC-GN-370 | HC-GN-370: FS | 2023-11-23 | 2024-03-08
HC-GN-370 | Completed | P2543-R01-Oct24..1.PM.7 | Obtain Company Approval-Hot Tap SOW | HC-GN-360 | HC-GN-360: FS | HC-GN-380 | HC-GN-380: FS | 2024-03-10 | 2024-03-25
HC-GN-380 | Completed | P2543-R01-Oct24..1.PM.7 | Final Issue for Design/ Construction-Hot Tap SOW | HC-GN-370 | HC-GN-370: FS | HE-PL-1370, C-COM-750 | HE-PL-1370: FS, C-COM-750: FS | 2024-03-26 | 2024-03-29
HE-PL-3630 | Completed | P2543-R01-Oct24..1.EN.1.9.2 | Obtain Company Approval - MR for Split Tee | HE-PL-3670 | HE-PL-3670: FS | HE-PL-3640 | HE-PL-3640: FS | 2024-01-15 | 2024-02-26
HE-PL-3640 | Completed | P2543-R01-Oct24..1.EN.1.9.2 | Final Issue for Design/ Construction-MR for Split Tee | HE-PL-3630 | HE-PL-3630: FS | HE-PL-3720 | HE-PL-3720: FS | 2024-02-26 | 2024-03-01
HE-PL-3650 | Completed | P2543-R01-Oct24..1.EN.1.9.2 | Issue ICR - MR for Split Tee | HE-PL-1330 | HE-PL-1330: FS | HE-PL-3660, HE-PL-3690, HP-ME-1270 | HE-PL-3660: FS, HE-PL-3690: FS, HP-ME-1270: FS | 2023-12-08 | 2023-12-22
HE-PL-3660 | Completed | P2543-R01-Oct24..1.EN.1.9.2 | Receive Company Comments - MR for Split Tee | HE-PL-3650 | HE-PL-3650: FS | HE-PL-3670 | HE-PL-3670: FS | 2023-12-22 | 2024-01-08
HE-PL-3670 | Completed | P2543-R01-Oct24..1.EN.1.9.2 | Re-Issue for Approval - MR for Split Tee | HE-PL-3660 | HE-PL-3660: FS | HE-PL-3630 | HE-PL-3630: FS | 2024-01-08 | 2024-01-15
HE-PL-3680 | Completed | P2543-R01-Oct24..1.EN.1.10.2 | Obtain Company Approval - TBE for Split Tee | HE-PL-3710 | HE-PL-3710: FS | HE-PL-3720, HP-ME-1280 | HE-PL-3720: FS, HP-ME-1280: FF | 2024-03-10 | 2024-03-17
HE-PL-3690 | Completed | P2543-R01-Oct24..1.EN.1.10.2 | Issue ICR - TBE for Split Tee | HE-PL-3650 | HE-PL-3650: FS | HE-PL-3700 | HE-PL-3700: FS | 2024-01-29 | 2024-02-23
HE-PL-3700 | Completed | P2543-R01-Oct24..1.EN.1.10.2 | Receive Company Comments - TBE for Split Tee | HE-PL-3690 | HE-PL-3690: FS | HE-PL-3710 | HE-PL-3710: FS | 2024-02-26 | 2024-03-01
HE-PL-3710 | Completed | P2543-R01-Oct24..1.EN.1.10.2 | Re-Issue for Approval - TBE for Split Tee | HE-PL-3700 | HE-PL-3700: FS | HE-PL-3680 | HE-PL-3680: FS | 2024-03-04 | 2024-03-08
HE-PL-3720 | Completed | P2543-R01-Oct24..1.EN.1.10.2 | Final Issue for Design/ Construction-TBE for Split Tee | HE-PL-3680, HE-PL-3640 | HE-PL-3680: FS, HE-PL-3640: FS | HM-PL-0770 | HM-PL-0770: FS | 2024-03-18 | 2024-03-25
HE-PL-3730 | Completed | P2543-R01-Oct24..1.EN.1.14 | Issue ICR - Pipeline Coating MTO | HE-PL-3230 | HE-PL-3230: SS | HE-PL-3740 | HE-PL-3740: FS | 2024-02-16 | 2024-03-01
HE-PL-3740 | Completed | P2543-R01-Oct24..1.EN.1.14 | Receive Company Comments - Pipeline Coating MTO | HE-PL-3730 | HE-PL-3730: FS | HE-PL-3750 | HE-PL-3750: FS | 2024-03-02 | 2024-03-15
HE-PL-3750 | Completed | P2543-R01-Oct24..1.EN.1.14 | Re-Issue for Approval - Pipeline Coating MTO | HE-PL-3740 | HE-PL-3740: FS | HE-PL-3760 | HE-PL-3760: FS | 2024-03-16 | 2024-03-22
HE-PL-3760 | Completed | P2543-R01-Oct24..1.EN.1.14 | Obtain Company Approval - Pipeline Coating MTO | HE-PL-3750 | HE-PL-3750: FS | HE-PL-3770 | HE-PL-3770: FS | 2024-03-20 | 2024-03-22
HE-PL-3770 | Completed | P2543-R01-Oct24..1.EN.1.14 | Final Issue for Design/ Construction-Pipeline Coating MTO | HE-PL-3760 | HE-PL-3760: FS | HM-PL-0035 | HM-PL-0035: FS | 2024-03-22 | 2024-04-05
HE-PL-3780 | Completed | P2543-R01-Oct24..1.EN.1.16 | Issue ICR - Pipeline Support Schedule | HE-PL-3330 | HE-PL-3330: FS | HE-PL-3790 | HE-PL-3790: FS | 2024-04-05 | 2024-04-12
HE-PL-3790 | Completed | P2543-R01-Oct24..1.EN.1.16 | Receive Company Comments - Pipeline Support Schedule | HE-PL-3780 | HE-PL-3780: FS | HE-PL-3800 | HE-PL-3800: FS | 2024-04-13 | 2024-04-26
HE-PL-3800 | Completed | P2543-R01-Oct24..1.EN.1.16 | Re-Issue for Approval - Pipeline Support Schedule | HE-PL-3790 | HE-PL-3790: FS | HE-PL-3810 | HE-PL-3810: FS | 2024-04-27 | 2024-05-10
HE-PL-3810 | Completed | P2543-R01-Oct24..1.EN.1.16 | Obtain Company Approval - Pipeline Support Schedule | HE-PL-3800 | HE-PL-3800: FS | HE-PL-3820 | HE-PL-3820: FS | 2024-05-11 | 2024-05-24
HE-PL-3820 | Completed | P2543-R01-Oct24..1.EN.1.16 | Final Issue for Design/ Construction- Pipeline Support Schedule | HE-PL-3810 | HE-PL-3810: FS | HE-PL-2970 | HE-PL-2970: FS | 2024-06-07 | 2024-09-02 17:30
HE-EL-5490 | Not Started | P2543-R01-Oct24..1.EN.9.3 | Receive Company Comments-Hazardous Area Register | HE-EL-5530 | HE-EL-5530: FS | HE-EL-5500 | HE-EL-5500: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-EL-5500 | Not Started | P2543-R01-Oct24..1.EN.9.3 | Re-Issue for Approval-Hazardous Area Register | HE-EL-5490 | HE-EL-5490: FS | HE-EL-5510 | HE-EL-5510: FS | 2024-11-25 07:30 | 2024-11-29 17:30
HE-EL-5510 | Not Started | P2543-R01-Oct24..1.EN.9.3 | Obtain Company Approval-Hazardous Area Register | HE-EL-5500 | HE-EL-5500: FS | HE-EL-5520 | HE-EL-5520: FS | 2024-12-04 07:30 | 2024-12-17 17:30
HE-EL-5520 | Not Started | P2543-R01-Oct24..1.EN.9.3 | Final Issue for Design/ Construction-Hazardous Area Register | HE-EL-5510 | HE-EL-5510: FS | ML1219-B29 | ML1219-B29: FF | 2024-12-18 07:30 | 2024-12-24 17:30
HE-EL-5530 | Not Started | P2543-R01-Oct24..1.EN.9.3 | Issue ICR-Hazardous Area Register | HE-EL-1670, HE-EL-0230 | HE-EL-1670: FF, HE-EL-0230: FF 5 | HE-EL-5490 | HE-EL-5490: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HE-HS-1200 | Completed | P2543-R01-Oct24..1.EN.4.14 | Obtain Company Approval- HAZOP Review Report (Vendor) | HE-HS-1240 | HE-HS-1240: FS | HE-HS-1210 | HE-HS-1210: FS | 2024-09-13 07:30 | 2024-09-20 17:30
HE-HS-1210 | In Progress | P2543-R01-Oct24..1.EN.4.14 | Final Issue for Design/ Construction-HAZOP Review Report (Vendor) | HE-HS-1200 | HE-HS-1200: FS | HE-HS-1260 | HE-HS-1260: FF | 2024-09-20 07:30 | 2024-11-01 17:30
HE-HS-1220 | Completed | P2543-R01-Oct24..1.EN.4.14 | Issue ICR- HAZOP Review Report (Vendor) | HE-HS-1150 | HE-HS-1150: FS | HE-HS-1230, HE-HS-1270 | HE-HS-1230: FS, HE-HS-1270: FS | 2024-07-23 07:30 | 2024-08-06 17:30
HE-HS-1230 | Completed | P2543-R01-Oct24..1.EN.4.14 | Receive Company Comments- HAZOP Review Report (Vendor) | HE-HS-1220 | HE-HS-1220: FS | HE-HS-1240 | HE-HS-1240: FF 5 | 2024-08-07 07:30 | 2024-08-22 17:30
HE-HS-1240 | Completed | P2543-R01-Oct24..1.EN.4.14 | Re-Issue for Approval- HAZOP Review Report (Vendor) | HE-HS-1230 | HE-HS-1230: FF 5 | HE-HS-1200 | HE-HS-1200: FS | 2024-09-03 07:30 | 2024-09-13 17:30
HE-HS-1250 | Completed | P2543-R01-Oct24..1.EN.4.22 | Obtain Company Approval- HAZOP Closeout Report (Vendor) | HE-HS-1290 | HE-HS-1290: FS | HE-HS-1260 | HE-HS-1260: FS | 2024-10-08 07:30 | 2024-10-21 17:30
HE-HS-1260 | In Progress | P2543-R01-Oct24..1.EN.4.22 | Final Issue for Design/ Construction-HAZOP Closeout Report (Vendor) | HE-HS-1250, HE-HS-1210 | HE-HS-1250: FS, HE-HS-1210: FF | HM-ME-1930 | HM-ME-1930: FF | 2024-10-22 07:30 | 2024-11-01 17:30
HE-HS-1270 | Completed | P2543-R01-Oct24..1.EN.4.22 | Issue ICR- HAZOP Closeout Report (Vendor) | HE-HS-1220 | HE-HS-1220: FS | HE-HS-1280 | HE-HS-1280: FF 10 | 2024-08-03 07:30 | 2024-08-19
HE-HS-1280 | Completed | P2543-R01-Oct24..1.EN.4.22 | Receive Company Comments- HAZOP Closeout Report (Vendor) | HE-HS-1270 | HE-HS-1270: FF 10 | HE-HS-1290 | HE-HS-1290: FF 5 | 2024-09-02 07:30 | 2024-09-26 17:30
HE-HS-1290 | Completed | P2543-R01-Oct24..1.EN.4.22 | Re-Issue for Approval- HAZOP Closeout Report (Vendor) | HE-HS-1280 | HE-HS-1280: FF 5 | HE-HS-1250 | HE-HS-1250: FS | 2024-09-16 07:30 | 2024-10-07 17:30
HE-IC-2940 | Completed | P2543-R01-Oct24..1.EN.6.A911 | Issue ICR- Addendum to DGs | HE-IC-0010 | HE-IC-0010: FS | HE-IC-2950 | HE-IC-2950: FS | 2024-01-29 07:30 | 2024-02-14 17:30
HE-IC-2950 | Completed | P2543-R01-Oct24..1.EN.6.A911 | Receive Company Comments- Addendum to DGs | HE-IC-2940 | HE-IC-2940: FS | HE-IC-2960 | HE-IC-2960: FS | 2024-02-15 | 2024-02-28
HE-IC-2960 | Completed | P2543-R01-Oct24..1.EN.6.A911 | Re-Issue for Approval- Addendum to DGs | HE-IC-2950 | HE-IC-2950: FS | HE-IC-2970 | HE-IC-2970: FS | 2024-02-29 | 2024-03-04
HE-IC-2970 | Completed | P2543-R01-Oct24..1.EN.6.A911 | Obtain Company Approval- Addendum to DGs | HE-IC-2960 | HE-IC-2960: FS | HE-IC-2980 | HE-IC-2980: FS | 2024-03-05 | 2024-03-18
HE-IC-2980 | Completed | P2543-R01-Oct24..1.EN.6.A911 | Final Issue for Design/ Construction-Addendum to DGs | HE-IC-2970 | HE-IC-2970: FS | HE-IC-2750 | HE-IC-2750: FS | 2024-03-19 | 2024-03-25
HE-IC-2990 | Completed | P2543-R01-Oct24..1.EN.6.11.3 | Receive Company Comments- Material Requisitions for Instrument Cables | HE-IC-3030 | HE-IC-3030: FS | HE-IC-3000 | HE-IC-3000: FS | 2024-05-30 | 2024-06-13
HE-IC-3000 | Completed | P2543-R01-Oct24..1.EN.6.11.3 | Re-Issue for Approval- Material Requisitions for Instrument Cables | HE-IC-2990 | HE-IC-2990: FS | HE-IC-3020 | HE-IC-3020: FS | 2024-06-14 | 2024-08-17 17:30
HE-IC-3010 | Completed | P2543-R01-Oct24..1.EN.6.11.3 | Final Issue for Design/ Construction-Material Requisitions for Instrument Cables | HE-IC-3020 | HE-IC-3020: FS | HE-IC-3040 | HE-IC-3040: FS | 2024-08-21 07:30 | 2024-08-27 17:30
HE-IC-3020 | Completed | P2543-R01-Oct24..1.EN.6.11.3 | Obtain Company Approval- Material Requisitions for Instrument Cables | HE-IC-3000 | HE-IC-3000: FS | HE-IC-3010 | HE-IC-3010: FS | 2024-08-19 07:30 | 2024-08-20 17:30
HE-IC-3030 | Completed | P2543-R01-Oct24..1.EN.6.11.3 | Issue ICR- Material Requisitions for Instrument Cables | HE-IC-0910 | HE-IC-0910: FS | HE-IC-2990, HE-IC-3050 | HE-IC-2990: FS, HE-IC-3050: FS 20 | 2024-05-08 | 2024-05-29
HE-IC-3040 | In Progress | P2543-R01-Oct24..1.EN.6.2.2 | Final Issue for Design/ Construction-TBE for Instrument Cables | HE-IC-3080, HE-IC-3010 | HE-IC-3080: FS, HE-IC-3010: FS | HE-IC-2610 | HE-IC-2610: FS | 2024-10-24 07:30 | 2024-11-08 17:30
HE-IC-3050 | Completed | P2543-R01-Oct24..1.EN.6.2.2 | Issue ICR- TBE for Instrument Cables | HE-IC-3030 | HE-IC-3030: FS 20 | HE-IC-3060 | HE-IC-3060: FS | 2024-07-10 07:30 | 2024-07-23 17:30
HE-IC-3060 | Completed | P2543-R01-Oct24..1.EN.6.2.2 | Receive Company Comments- TBE for Instrument Cables | HE-IC-3050 | HE-IC-3050: FS | HE-IC-3070 | HE-IC-3070: FS | 2024-07-24 07:30 | 2024-08-13 17:30
HE-IC-3070 | Completed | P2543-R01-Oct24..1.EN.6.2.2 | Re-Issue for Approval- TBE for Instrument Cables | HE-IC-3060 | HE-IC-3060: FS | HE-IC-3080 | HE-IC-3080: FS | 2024-09-30 07:30 | 2024-10-09
HE-IC-3080 | Completed | P2543-R01-Oct24..1.EN.6.2.2 | Obtain Company Approval- TBE for Instrument Cables | HE-IC-3070 | HE-IC-3070: FS | HE-IC-3040 | HE-IC-3040: FS | 2024-10-10 | 2024-10-18 17:30
HE-IC-3090 | Not Started | P2543-R01-Oct24..1.EN.6.A271 | Issue ICR- Instrument Termination Drawings | HE-IC-2530 | HE-IC-2530: FS | HE-IC-3130, HE-IC-3140 | HE-IC-3130: FS, HE-IC-3140: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HE-IC-3100 | Not Started | P2543-R01-Oct24..1.EN.6.A271 | Re-Issue for Approval- Instrument Termination Drawings | HE-IC-3130 | HE-IC-3130: FS | HE-IC-3110 | HE-IC-3110: FS | 2024-11-25 07:30 | 2024-11-29 17:30
HE-IC-3110 | Not Started | P2543-R01-Oct24..1.EN.6.A271 | Obtain Company Approval-Instrument Termination Drawings | HE-IC-3100 | HE-IC-3100: FS | HE-IC-3120 | HE-IC-3120: FS | 2024-12-04 07:30 | 2024-12-16 17:30
HE-IC-3120 | Not Started | P2543-R01-Oct24..1.EN.6.A271 | Final Issue for Design/ Construction-Instrument Termination Drawings | HE-IC-3110, HE-IC-2510 | HE-IC-3110: FS, HE-IC-2510: FF | HE-IC-3170 | HE-IC-3170: FS | 2024-12-17 07:30 | 2024-12-23 17:30
HE-IC-3130 | Not Started | P2543-R01-Oct24..1.EN.6.A271 | Receive Company Comments- Instrument Termination Drawings | HE-IC-3090 | HE-IC-3090: FS | HE-IC-3100 | HE-IC-3100: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-IC-3140 | Not Started | P2543-R01-Oct24..1.EN.6.A2711 | Issue ICR- F&G Termination Drawings | HE-IC-3090 | HE-IC-3090: FS | HE-IC-3180 | HE-IC-3180: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-IC-3150 | Not Started | P2543-R01-Oct24..1.EN.6.A2711 | Re-Issue for Approval- F&G Termination Drawings | HE-IC-3180 | HE-IC-3180: FS | HE-IC-3160 | HE-IC-3160: FS | 2024-12-04 07:30 | 2024-12-10 17:30
HE-IC-3160 | Not Started | P2543-R01-Oct24..1.EN.6.A2711 | Obtain Company Approval- F&G Termination Drawings | HE-IC-3150 | HE-IC-3150: FS | HE-IC-3170 | HE-IC-3170: FS | 2024-12-11 07:30 | 2024-12-17 17:30
HE-IC-3170 | Not Started | P2543-R01-Oct24..1.EN.6.A2711 | Final Issue for Design/ Construction- F&G Termination Drawings | HE-IC-3160, HE-IC-3120 | HE-IC-3160: FS, HE-IC-3120: FS | C-52-0203-PL-TE-8200 | C-52-0203-PL-TE-8200: FS | 2024-12-24 07:30 | 2024-12-30 17:30
HE-IC-3180 | Not Started | P2543-R01-Oct24..1.EN.6.A2711 | Receive Company Comments- F&G Termination Drawings | HE-IC-3140 | HE-IC-3140: FS | HE-IC-3150 | HE-IC-3150: FS | 2024-11-25 07:30 | 2024-11-29 17:30
HE-HS-1300 | Completed | P2543-R01-Oct24..1.EN.4.23 | Issue ICR- ISD Closeout Report | HE-HS-0790 | HE-HS-0790: FS | HE-HS-1310 | HE-HS-1310: FS | 2024-05-01 | 2024-05-09
HE-HS-1310 | Completed | P2543-R01-Oct24..1.EN.4.23 | Receive Company Comments- ISD Closeout Report | HE-HS-1300 | HE-HS-1300: FS | HE-HS-1320 | HE-HS-1320: FS | 2024-05-10 | 2024-06-03 17:30
HE-HS-1320 | Completed | P2543-R01-Oct24..1.EN.4.23 | Re-Issue for Approval- ISD Closeout Report | HE-HS-1310 | HE-HS-1310: FS | HE-HS-1330 | HE-HS-1330: FS | 2024-09-02 07:30 | 2024-09-14 17:30
HE-HS-1330 | Completed | P2543-R01-Oct24..1.EN.4.23 | Obtain Company Approval- ISD Closeout Report | HE-HS-1320 | HE-HS-1320: FS | HE-HS-1340 | HE-HS-1340: FS | 2024-09-16 07:30 | 2024-09-18 17:30
HE-HS-1340 | In Progress | P2543-R01-Oct24..1.EN.4.23 | Final Issue for Design/ Construction- ISD Closeout Report | HE-HS-1330 | HE-HS-1330: FS | HE-HS-0890 | HE-HS-0890: FF | 2024-10-11 07:30 | 2024-11-06 17:30
HM-ME-2210 | Not Started | P2543-R01-Oct24..PR.26.LL.10.3 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | HM-ME-2220 | HM-ME-2220: FS | CAB-5310, ML1024-D06, ML1469-D13, C-56-591-01-PI-1800, C-56-591-01-PL-1060, C-52-PR-839-PI-1800, C-52-598-06-PI-1800, C-52-598-06-PL-1060, C-52-598-05-PI-1800, C-52-598-05-PL-1060, C-52-598-04-PI-1800, C-52-598-04-PL-1060, C-52-598-03-PI-1800, C-52-598-03- | CAB-5310: FS, ML1024-D06: FS, ML1469-D13: FS, C-56-591-01-PI-1800: FS, C-56-591-01-PL-1060: FS, C-52-PR-839-PI-1800: FS, C-52-598-06-PI-1800: FS, C-52-598-06-PL-1060: FS, C-52-598-05-PI-1800: FS, C-52-598-05-PL-1060: FS, C-52-598-04-PI-1800: FS, C-52-598-0 | 2025-07-13 07:00 | 2025-07-20 17:00
HM-ME-2220 | Not Started | P2543-R01-Oct24..PR.26.LL.10.3 | Transportation/ Custom Clearance/ Delivery at site of ROV/ GOV (2nd Lot) | HM-ME-0550, HM-ME-0570 | HM-ME-0550: FS 15, HM-ME-0570: FS | HM-ME-2210 | HM-ME-2210: FS | 2025-05-28 08:00 | 2025-07-11 18:00
HM-ME-2230 | Not Started | P2543-R01-Oct24..PR.26.LL.9.3 | Transportation/ Custom Clearance/ Delivery at site of MOV (Lot 1) | HM-ME-0620 | HM-ME-0620: FS | HM-ME-0690, HM-ME-0680 | HM-ME-0690: FS 8, HM-ME-0680: FS | 2025-05-09 08:00 | 2025-05-29 18:00
HM-ME-2240 | Not Started | P2543-R01-Oct24..PR.26.LL.9.3 | Receipt at site and inspection of MOV (Lot 2) | HM-ME-0670 | HM-ME-0670: FS | ML1469-D13, ML1024-D06, CAB-5310, C-56-PL-607-PI-1800, C-56-PR-838-PI-1800, C-52-PR-839-PI-1800, C-52-PL-838-PI-1800 | ML1469-D13: FS, ML1024-D06: FS, CAB-5310: FS, C-56-PL-607-PI-1800: FS, C-56-PR-838-PI-1800: FS, C-52-PR-839-PI-1800: FS, C-52-PL-838-PI-1800: FS | 2025-07-01 07:00 | 2025-07-23 17:00
HM-ME-2250 | Not Started | P2543-R01-Oct24..PR.26.LL.9.3 | Receipt at site and inspection of Isolator (Lot 2) | HM-ME-0690 | HM-ME-0690: FS | ML1030, ML1859-E31, ML1749-E20, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-52-PR-839-EI-1400, C-52-PR-839-EI-1800, C-52-PR-839-CA-1000, C-52-PR-839-TE-1410, PRECOM-52-PR-1000 | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, C-56-PL-607-EI-2200: FF, C-56-PL-607-EI-1800: FF 26, C-52-PR-839-EI-1400: FF, C-52-PR-839-EI-1800: FF, C-52-PR-839-CA-1000: FF, C-52-PR-839-TE-1410: FS, PRECOM-52-PR-1000: FS | 2025-06-17 07:00 | 2025-06-24 17:00
HM-ME-2270 | Not Started | P2543-R01-Oct24..PR.26.LL.4.3 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | HM-ME-2260 | HM-ME-2260: FS | ML1479-D15, CAB-5310, ML1056-D14, C-56-PL-607-TE-1200, C-56-PL-607-TE-1400, C-56-PL-607-TE-1600, C-56-591-01-TE-1000, C-52-598-06-TE-1000, C-52-598-05-TE-1000, C-52-598-04-TE-1000, C-52-598-03-TE-1000, C-52-598-02-TE-1000, C-52-598-01-TE-1000, C-52-PR-839- | ML1479-D15: FF, CAB-5310: FS, ML1056-D14: FS, C-56-PL-607-TE-1200: FS 34, C-56-PL-607-TE-1400: FS, C-56-PL-607-TE-1600: FS, C-56-591-01-TE-1000: FS, C-52-598-06-TE-1000: FS, C-52-598-05-TE-1000: FS, C-52-598-04-TE-1000: FS, C-52-598-03-TE-1000: FS, C-52-59 | 2025-05-20 07:00 | 2025-05-27 17:00
HM-ME-2260 | Not Started | P2543-R01-Oct24..PR.26.LL.4.3 | Transportation/ Custom Clearance/ Delivery at site of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | HM-ME-1260 | HM-ME-1260: FS 20 | HM-ME-2270 | HM-ME-2270: FS | 2025-04-29 08:00 | 2025-05-19 18:00
HM-ME-2290 | Not Started | P2543-R01-Oct24..PR.26.1.14.3 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | HM-ME-2280 | HM-ME-2280: FS | ML1479-D15, CAB-5310, C-56-EB2-EI-1000, C-56-EB2-TE-1000, C-56-591-01-TE-1000, C-52-598-06-TE-1000, C-52-598-05-TE-1000, C-52-598-04-TE-1000, C-52-598-03-TE-1000, C-52-598-02-TE-1000, C-52-598-01-TE-1000, C-52-EB1-TE-1000 | ML1479-D15: FS, CAB-5310: FS, C-56-EB2-EI-1000: FS, C-56-EB2-TE-1000: FS, C-56-591-01-TE-1000: FS, C-52-598-06-TE-1000: FS, C-52-598-05-TE-1000: FS, C-52-598-04-TE-1000: FS, C-52-598-03-TE-1000: FS, C-52-598-02-TE-1000: FS, C-52-598-01-TE-1000: FS, C-52-EB | 2025-05-11 07:00 | 2025-05-18 17:00
HM-ME-2280 | Not Started | P2543-R01-Oct24..PR.26.1.14.3 | Transportation/ Custom Clearance/ Delivery at site of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | HM-ME-1360 | HM-ME-1360: FS 21 | HM-ME-2290 | HM-ME-2290: FS | 2025-04-20 08:00 | 2025-05-10 18:00
HM-ME-2310 | Not Started | P2543-R01-Oct24..PR.26.LL.18.3 | Receipt at site and inspection of Gas Detectors (Lot 2) | HM-ME-2300 | HM-ME-2300: FS | ML1030, ML1859-E31, ML1749-E20, ML2089-D16, PRECOM-52-PR-1000, C-56-PL-607-EI-2410, C-52-598-01-EI-2410, C-52-598-02-EI-2410, C-52-598-03-EI-2410, C-52-598-04-EI-2410, C-52-598-05-EI-2410, C-52-598-06-EI-2410, C-56-591-01-EI-2410, C-56-PR-838-EI-2410, C-52 | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML2089-D16: FF, PRECOM-52-PR-1000: FS, C-56-PL-607-EI-2410: FS, C-52-598-01-EI-2410: FS, C-52-598-02-EI-2410: FS, C-52-598-03-EI-2410: FS, C-52-598-04-EI-2410: FS, C-52-598-05-EI-2410: FS, C-52-598-06-EI-2410: FS | 2025-03-22 15:00 | 2025-04-03 15:00
HM-ME-2300 | Not Started | P2543-R01-Oct24..PR.26.LL.18.3 | Transportation/ Custom Clearance/ Delivery at site of Gas Detectors (Lot 2) | HM-ME-1460 | HM-ME-1460: FS 20 | HM-ME-2310 | HM-ME-2310: FS | 2025-03-01 15:00 | 2025-03-22 15:00
HM-ME-2320 | Not Started | P2543-R01-Oct24..PR.26.1.15.3 | Transportation/ Custom Clearance/ Delivery at site of Field Instruments (Lot 2) | HM-ME-1560 | HM-ME-1560: FS 21 | HM-ME-2330 | HM-ME-2330: FS | 2025-01-31 15:00 | 2025-02-21 15:00
HM-ME-2330 | Not Started | P2543-R01-Oct24..PR.26.1.15.3 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | ML1002, HM-ME-2320 | ML1002: FS, HM-ME-2320: FS | ML1030, ML1859-E31, ML1749-E20, ML2089-D16, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1000, C-56-PR-838-EI-1400, C-56-591-01-EI-1600, C-52-598-06-EI-1210, C-52-598-06-EI-1400, C-52-598-05-EI-1210, C-52-598-05-EI-1400, C-52- | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML2089-D16: FF, C-56-PL-607-EI-1400: FF, C-56-PL-607-EI-2200: FF, C-56-PL-607-EI-1800: FF, C-56-EB2-EI-1000: FF, C-56-PR-838-EI-1400: FF, C-56-591-01-EI-1600: FF, C-52-598-06-EI-1210: FF, C-52-598-06-EI-1400: FF, | 2025-02-21 15:00 | 2025-02-28 15:00
HM-ME-2340 | Not Started | P2543-R01-Oct24..PR.26.1.16.3 | Transportation/ Custom Clearance/ Delivery at site of Junction Boxes (Lot 2) | HM-ME-1660 | HM-ME-1660: FS | HM-ME-2350 | HM-ME-2350: FS | 2025-04-24 08:00 | 2025-05-07 18:00
HM-ME-2350 | Not Started | P2543-R01-Oct24..PR.26.1.16.3 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | ML1002, HM-ME-2340 | ML1002: FS, HM-ME-2340: FS | ML1030, ML1859-E31, ML1749-E20, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-591-01-EI-1600, C-52-598-05-EI-1210, C-52-598-04-EI-1210, C-52-598-03-EI-1210, C-52-598-02-EI-1210, C-52-PR-839-EI | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, C-56-PL-607-EI-2200: FF, C-56-PL-607-EI-1800: FF, C-56-PR-838-EI-1010: FF, C-56-PR-838-EI-1400: FF, C-56-PR-838-EI-1810: FF, C-56-591-01-EI-1600: FF, C-52-598-05-EI-1210: FF, C-52-598-04-EI-1210: FF, C-52-598-03- | 2025-05-08 08:00 | 2025-05-21 18:00
HM-ME-2370 | Not Started | P2543-R01-Oct24..PR.26.1.13.3 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 2) | HM-ME-2360 | HM-ME-2360: FS | C-56-PL-607-ME-1600, C-56-591-01-ME-1000, C-52-598-06-ME-1000, C-52-598-05-ME-1000, C-52-598-04-ME-1000, C-52-598-03-ME-1000, C-52-598-02-ME-1000, C-52-598-01-ME-1000, C-52-PR-839-ME-1600 | C-56-PL-607-ME-1600: FS, C-56-591-01-ME-1000: FS, C-52-598-06-ME-1000: FS, C-52-598-05-ME-1000: FS, C-52-598-04-ME-1000: FS, C-52-598-03-ME-1000: FS, C-52-598-02-ME-1000: FS, C-52-598-01-ME-1000: FS, C-52-PR-839-ME-1600: FS | 2025-04-07 08:00 | 2025-04-13 18:00
HM-ME-2360 | Not Started | P2543-R01-Oct24..PR.26.1.13.3 | Transportation/ Custom Clearance/ Delivery at site of Fire Fighting & Safety Equipment (Lot 2) | HM-ME-1960 | HM-ME-1960: FS | HM-ME-2370 | HM-ME-2370: FS | 2025-03-31 08:00 | 2025-04-06 18:00
HM-EL-600 | Completed | P2543-R01-Oct24..PR.26.LL.19.3 | Transportation/ Custom Clearance/ Delivery at site of FOC Cables (Lot 2) | HM-EL-0150 | HM-EL-0150: FS 21 | HM-EL-610 | HM-EL-610: FS | 2024-10-01 | 2024-10-22 18:00
HM-EL-610 | Completed | P2543-R01-Oct24..PR.26.LL.19.3 | Receipt at site and inspection of FOC Cables (Lot 2) | HM-EL-600 | HM-EL-600: FS | ML1057-D19, C-56-PL-607-TE-1200, C-56-PL-607-TE-1400, C-56-PL-607-TE-1600, C-56-EB2-TE-1000, C-56-HC01-PL-TE-8200, C-56-HC01-PL-TE-8400, C-56-01HG-PL-TE-8200, C-56-01HG-PL-TE-8400, C-56-PR-838-TE-1000, C-56-591-01-TE-1000, C-52-06CR-PL-TE-8200, C-52-0506-P | ML1057-D19: FF, C-56-PL-607-TE-1200: FS, C-56-PL-607-TE-1400: FS, C-56-PL-607-TE-1600: FS, C-56-EB2-TE-1000: FS, C-56-HC01-PL-TE-8200: FS, C-56-HC01-PL-TE-8400: FS, C-56-01HG-PL-TE-8200: FS, C-56-01HG-PL-TE-8400: FS, C-56-PR-838-TE-1000: FS, C-56-591-01-TE | 2024-10-23 08:00 | 2024-10-25 18:00
HM-PL-1490 | Not Started | P2543-R01-Oct24..PR.1.19.3 | Receipt at site and inspection of Pig Signaler (Lot 2) | HM-PL-1480 | HM-PL-1480: FS | ML1549-D32, ML1409-D24, C-56-PL-607-ME-1200, C-56-PR-838-ME-1200, C-52-PR-839-ME-1200, C-52-PL-838-ME-1200, C-4N-H5-TPL-ME-1000, C-4N-HG-TPR-ME-1100 | ML1549-D32: FF, ML1409-D24: FS, C-56-PL-607-ME-1200: FF 3, C-56-PR-838-ME-1200: FS, C-52-PR-839-ME-1200: FS, C-52-PL-838-ME-1200: FF 12, C-4N-H5-TPL-ME-1000: FS, C-4N-HG-TPR-ME-1100: FF | 2025-05-01 07:00 | 2025-05-09 15:00
HM-PL-1480 | Not Started | P2543-R01-Oct24..PR.1.19.3 | Transportation/ Custom Clearance/ Delivery at site of Pig Signaler (Lot 2) | HM-PL-0500 | HM-PL-0500: FS 21 | HM-PL-1490 | HM-PL-1490: FS | 2025-04-10 08:00 | 2025-04-30 18:00
HM-PL-1510 | Not Started | P2543-R01-Oct24..PR.1.3.3 | Receipt at site and inspection of Isolating Joints (Lot 2) | HM-PL-1500 | HM-PL-1500: FS | ML1549-D32, ML1409-D24, C-56-PL-607-PI-1200, C-56-PL-607-PI-1800, C-56-PL-607-PI-2000, C-56-G-HT-PI-1200, C-56-G-HT-PI-1800, C-56-G-HT-PI-2000, C-56-PR-838-PI-1200, C-56-PR-838-PI-1800, C-56-PR-838-PI-2000, C-56-591-01-PI-1200, C-56-591-01-PI-1800, C-56-59 | ML1549-D32: FF, ML1409-D24: FS, C-56-PL-607-PI-1200: FS, C-56-PL-607-PI-1800: FS, C-56-PL-607-PI-2000: FS, C-56-G-HT-PI-1200: FS, C-56-G-HT-PI-1800: FS, C-56-G-HT-PI-2000: FS, C-56-PR-838-PI-1200: FS, C-56-PR-838-PI-1800: FS, C-56-PR-838-PI-2000: FS, C-56- | 2025-03-14 09:00 | 2025-03-27 13:00
HM-PL-1500 | Not Started | P2543-R01-Oct24..PR.1.3.3 | Transportation/ Custom Clearance/ Delivery at site of Isolating Joints (Lot 2) | HM-PL-0710 | HM-PL-0710: FS 21 | HM-PL-1510 | HM-PL-1510: FS | 2025-02-21 08:00 | 2025-03-13 18:00
HM-PL-1530 | Not Started | P2543-R01-Oct24..PR.1.2.3 | Receipt at site and inspection of Pigging & Split Tee (Lot 2) | HM-PL-1520, HM-PL-0840 | HM-PL-1520: FS, HM-PL-0840: FF 6 | ML1549-D32, ML1409-D24, C-56-PL-607-ME-1000, C-56-PL-607-ME-1200, C-56-PR-838-ME-1200, C-52-PR-839-ME-1200, C-52-D-HT002-ME-1000, C-52-PL-838-ME-1200, C-36-KM-HT03-ME-1000, C-4N-H5-TPL-ME-1000, C-4N-HG-TPR-ME-1100 | ML1549-D32: FF, ML1409-D24: FS, C-56-PL-607-ME-1000: FF 3, C-56-PL-607-ME-1200: FS, C-56-PR-838-ME-1200: FS, C-52-PR-839-ME-1200: FS, C-52-D-HT002-ME-1000: FS, C-52-PL-838-ME-1200: FS, C-36-KM-HT03-ME-1000: FS, C-4N-H5-TPL-ME-1000: FS, C-4N-HG-TPR-ME-1100: | 2025-03-18 14:00 | 2025-03-27 14:00
HM-PL-1520 | Not Started | P2543-R01-Oct24..PR.1.2.3 | Transportation/ Custom Clearance/ Delivery at site of Pigging & Split Tee (Lot 2) | HM-PL-0810 | HM-PL-0810: FS | HM-PL-1530 | HM-PL-1530: FS | 2025-02-11 08:00 | 2025-03-03 18:00
HM-PL-1550 | Not Started | P2543-R01-Oct24..PR.1.4.3 | Receipt at site and inspection of Anchor Flanges (Lot 2) | HM-PL-1540 | HM-PL-1540: FS | ML1549-D32, C-52-PR-839-CI-1510, C-52-PL-838-CI-1510 | ML1549-D32: FF, C-52-PR-839-CI-1510: FS, C-52-PL-838-CI-1510: FS | 2025-03-13 09:00 | 2025-03-26 13:00
HM-PL-1540 | Not Started | P2543-R01-Oct24..PR.1.4.3 | Transportation/ Custom Clearance/ Delivery at site of Anchor Flanges (Lot 2) | HM-PL-920 | HM-PL-920: FS 21 | HM-PL-1550 | HM-PL-1550: FS | 2025-02-24 08:00 | 2025-03-12 18:00
HM-EL-630 | Not Started | P2543-R01-Oct24..PR.BK.17.3 | Receipt at site and inspection of Power & Control Cables (Lot 2) | HM-EL-620 | HM-EL-620: FS | ML1030, ML1859-E31, ML1749-E20, ML1549-D32, C-56-PL-607-EI-2000, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1200, C-56-EB2-EI-1000, C-56-EB2-EI-1210, C-56-EB2-EI-1220, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1549-D32: FF, C-56-PL-607-EI-2000: FS 30, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-EB2-EI-1200: FS, C-56-EB2-EI-1000: FF, C-56-EB2-EI-1210: FS, C-56-EB2-EI-1220: FS, C-56- | 2025-04-03 07:00 | 2025-04-10 17:00
HM-EL-620 | Not Started | P2543-R01-Oct24..PR.BK.17.3 | Transportation/ Custom Clearance/ Delivery at site of Power & Control Cables (Lot 2) | HM-EL-0050 | HM-EL-0050: FS 21 | HM-EL-630 | HM-EL-630: FS | 2025-03-23 08:00 | 2025-03-29 18:00
HM-EL-650 | Not Started | P2543-R01-Oct24..PR.BK.13.3 | Receipt at site and inspection of Cable Trays (Lot 2) | HM-EL-640, HM-EL-640 | HM-EL-640: FF, HM-EL-640: FS | ML1030, ML1859-E31, ML1749-E20, ML1549-D32, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1000, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C-56-PR-838-EI-2030, C-56-591-01-EI-1600, C-52- | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1549-D32: FF, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-EB2-EI-1000: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-EI-1400: FS, C-56-PR-838-EI-1810: FS, C-56-PR-838-EI-2020: FS, | 2025-03-14 09:00 | 2025-03-27 13:00
HM-EL-640 | Not Started | P2543-R01-Oct24..PR.BK.13.3 | Transportation/ Custom Clearance/ Delivery at site of Cable Trays (Lot 1) | HM-EL-0250 | HM-EL-0250: FS 21 | HM-EL-650, HM-EL-650 | HM-EL-650: FF, HM-EL-650: FS | 2025-02-21 08:00 | 2025-03-13 18:00
HM-PL-1570 | Not Started | P2543-R01-Oct24..PR.BK.1.3 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | HM-PL-1560 | HM-PL-1560: FS | CAB-5310, ML1539-D21, ML1529-D20, C-56-PL-607-PI-1200, C-56-PL-607-PI-1800, C-56-PL-607-PI-2000, C-56-G-HT-PI-1200, C-56-G-HT-PI-1800, C-56-G-HT-PI-2000, C-56-G-HT101-ME-1000, C-56-PR-838-PI-1200, C-56-PR-838-PI-1800, C-56-PR-838-PI-2000, C-56-591-01-PI-12 | CAB-5310: FS, ML1539-D21: FF, ML1529-D20: FF, C-56-PL-607-PI-1200: FF 12, C-56-PL-607-PI-1800: FF 12, C-56-PL-607-PI-2000: FF 12, C-56-G-HT-PI-1200: FS, C-56-G-HT-PI-1800: FS, C-56-G-HT-PI-2000: FS, C-56-G-HT101-ME-1000: FS, C-56-PR-838-PI-1200: FS, C-56-P | 2025-02-28 09:00 | 2025-03-13 13:00
HM-PL-1560 | Not Started | P2543-R01-Oct24..PR.BK.1.3 | Transportation/ Custom Clearance/ Delivery at site of Ball/ Globe/ Check/ Plug Valves (Lot 2) | HM-PL-0190 | HM-PL-0190: FS 21 | HM-PL-1570 | HM-PL-1570: FS | 2025-02-14 08:00 | 2025-02-27 18:00
HM-EL-670 | Not Started | P2543-R01-Oct24..PR.BK.3.3 | Receipt at site and inspection of Cable Gland and Termination (Lot 2) | HM-EL-660, HM-EL-660 | HM-EL-660: FF, HM-EL-660: FS | ML1549-D32, C-52-598-06-EI-2000, C-52-598-06-EI-2010 | ML1549-D32: FF, C-52-598-06-EI-2000: FS 3, C-52-598-06-EI-2010: FS 3 | 2025-04-08 07:00 | 2025-04-15 17:00
HM-EL-660 | Not Started | P2543-R01-Oct24..PR.BK.3.3 | Transportation/ Custom Clearance/ Delivery at site of Cable Gland and Termination (Lot 2) | HM-EL-570 | HM-EL-570: FS 21 | HM-EL-670, HM-EL-670 | HM-EL-670: FF, HM-EL-670: FS | 2025-03-04 08:00 | 2025-04-07 18:00
HM-EL-690 | Not Started | P2543-R01-Oct24..PR.BK.15.3 | Receipt at site and inspection of Earthing Material (Lot 2) | HM-EL-680, HM-EL-680 | HM-EL-680: FF, HM-EL-680: FS | ML1030, ML1859-E31, ML1749-E20, ML1549-D32, C-56-PL-607-EI-1400, C-56-PL-607-EI-2200, C-56-PL-607-EI-1800, C-56-EB2-EI-1000, C-56-PR-838-EI-1010, C-56-PR-838-EI-1400, C-56-PR-838-EI-1810, C-56-PR-838-EI-2020, C-56-PR-838-EI-2030, C-56-591-01-EI-1600, C-52- | ML1030: FS, ML1859-E31: FS, ML1749-E20: FS, ML1549-D32: FF, C-56-PL-607-EI-1400: FS, C-56-PL-607-EI-2200: FS, C-56-PL-607-EI-1800: FS, C-56-EB2-EI-1000: FS, C-56-PR-838-EI-1010: FS, C-56-PR-838-EI-1400: FS, C-56-PR-838-EI-1810: FS, C-56-PR-838-EI-2020: FS, | 2025-04-04 17:30 | 2025-04-13 17:30
HM-EL-680 | Not Started | P2543-R01-Oct24..PR.BK.15.3 | Transportation/ Custom Clearance/ Delivery at site of Earthing Material (Lot 2) | HM-EL-0350 | HM-EL-0350: FS 21 | HM-EL-690, HM-EL-690 | HM-EL-690: FF, HM-EL-690: FS | 2025-02-28 17:30 | 2025-04-04 17:30
HM-EL-710 | Not Started | P2543-R01-Oct24..PR.BK.16.3 | Receipt at site and inspection of MCT (Lot 2) | HM-EL-700, HM-EL-700 | HM-EL-700: FS, HM-EL-700: FF | ML1549-D32, C-56-EB2-EI-1000, C-52-EB1-EI-1000 | ML1549-D32: FF, C-56-EB2-EI-1000: FS, C-52-EB1-EI-1000: FS | 2025-05-13 07:00 | 2025-05-20 17:00
HM-EL-700 | Not Started | P2543-R01-Oct24..PR.BK.16.3 | Transportation/ Custom Clearance/ Delivery at site of MCT (Lot 2) | HM-EL-0450 | HM-EL-0450: FS 21 | HM-EL-710, HM-EL-710 | HM-EL-710: FS, HM-EL-710: FF | 2025-04-28 17:30 | 2025-05-12 17:30
HM-ME-2390 | Not Started | P2543-R01-Oct24..PR.26.LL.12.3 | Receipt at site and inspection of Pig Launchers & Receivers (56" Line) | HM-ME-2380 | HM-ME-2380: FS | CAB-5310, ML1519-D04, C-56-PL-607-ME-1000, C-56-PL-607-PL-1000, C-56-PR-838-ME-1100 | CAB-5310: FS, ML1519-D04: FF, C-56-PL-607-ME-1000: FS, C-56-PL-607-PL-1000: FS, C-56-PR-838-ME-1100: FS | 2025-03-05 08:00 | 2025-03-12 18:00
HM-ME-2380 | Not Started | P2543-R01-Oct24..PR.26.LL.12.3 | Transportation/ Custom Clearance/ Delivery at site of Pig Launchers & Receivers (56" Line) | HM-ME-0450 | HM-ME-0450: FS 21 | CAB-5310, HM-ME-2390, C-4N-HG-TPR-ME-1100 | CAB-5310: FS, HM-ME-2390: FS, C-4N-HG-TPR-ME-1100: FS | 2025-01-29 08:00 | 2025-03-04 18:00
CTF-SO1010 | Completed | P2543-R01-Oct24..4.2.1 | Camp Facilities | CTF-SO1000, CTF-SO1080, CTF-SO1000 | CTF-SO1000: FF, CTF-SO1080: FS, CTF-SO1000: SS 15 | CTF-SO1020, CTF-SO1020 | CTF-SO1020: FF, CTF-SO1020: SS 45 | 2023-10-18 07:00 | 2024-06-07 13:00
CTF-SO1020 | Completed | P2543-R01-Oct24..4.2.1 | Satellite Office-1 | CTF-SO1010, CTF-SO1010 | CTF-SO1010: FF, CTF-SO1010: SS 45 | CTF-SO1040, C-56-HC01-PL-CI-1400, C-56-HC01-PL-CI-1800 | CTF-SO1040: SS 14, C-56-HC01-PL-CI-1400: FS, C-56-HC01-PL-CI-1800: FS | 2023-11-22 07:00 | 2024-03-20 13:00
CTF-SO1030 | Completed | P2543-R01-Oct24..4.2.1 | Satellite Office-2 | CTF-SO1070, CTF-SO1070 | CTF-SO1070: FF, CTF-SO1070: SS 2 | C-56-PL-607-CI-1400, C-56-PL-607-CI-1500 | C-56-PL-607-CI-1400: FS, C-56-PL-607-CI-1500: FS | 2023-12-20 07:30 | 2024-05-30 08:12
C-GOV-1000 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from AAM | HE-PL-0190, HE-PL-0130, HE-PL-0250 | HE-PL-0190: FS, HE-PL-0130: FF, HE-PL-0250: FF | C-GOV-1010 | C-GOV-1010: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1010 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from ADM | C-GOV-1000 | C-GOV-1000: SS | C-GOV-1020 | C-GOV-1020: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1020 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from DMT | C-GOV-1010 | C-GOV-1010: SS | C-GOV-1030 | C-GOV-1030: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1030 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from DRM | C-GOV-1020 | C-GOV-1020: SS | C-GOV-1040 | C-GOV-1040: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1040 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from ADDC | C-GOV-1030 | C-GOV-1030: SS | C-GOV-1050 | C-GOV-1050: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1050 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from AADC | C-GOV-1040 | C-GOV-1040: SS | C-GOV-1060 | C-GOV-1060: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1060 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from ADM Al Wathba | C-GOV-1050 | C-GOV-1050: SS | C-GOV-1070 | C-GOV-1070: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1070 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from ADM Musaffah | C-GOV-1060 | C-GOV-1060: SS | C-GOV-1080 | C-GOV-1080: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1080 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from ADM City Centre | C-GOV-1070 | C-GOV-1070: SS | C-GOV-1090 | C-GOV-1090: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1090 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from ADM Al Shahama | C-GOV-1080 | C-GOV-1080: SS | C-GOV-1100 | C-GOV-1100: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1100 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from ADNOC | C-GOV-1090 | C-GOV-1090: SS | C-GOV-1110 | C-GOV-1110: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1110 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from ADSSC | C-GOV-1100 | C-GOV-1100: SS | C-GOV-1120 | C-GOV-1120: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1120 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from DCT | C-GOV-1110 | C-GOV-1110: SS | C-GOV-1130 | C-GOV-1130: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1130 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from AAM Parks | C-GOV-1120 | C-GOV-1120: SS | C-GOV-1140 | C-GOV-1140: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1140 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from DRM Parks | C-GOV-1130 | C-GOV-1130: SS | C-GOV-1150 | C-GOV-1150: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1150 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from AAM Roads | C-GOV-1140 | C-GOV-1140: SS | C-GOV-1160 | C-GOV-1160: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1160 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from DRM Roads | C-GOV-1150 | C-GOV-1150: SS | C-GOV-1170 | C-GOV-1170: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1170 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from DEL | C-GOV-1160 | C-GOV-1160: SS | C-GOV-1180 | C-GOV-1180: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1180 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from DU | C-GOV-1170 | C-GOV-1170: SS | C-GOV-1190 | C-GOV-1190: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1190 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from EAD | C-GOV-1180 | C-GOV-1180: SS | C-GOV-1200 | C-GOV-1200: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1200 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from Ethiad Rail | C-GOV-1190 | C-GOV-1190: SS | C-GOV-1210 | C-GOV-1210: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1210 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from Etisalat | C-GOV-1200 | C-GOV-1200: SS | C-GOV-1220 | C-GOV-1220: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1220 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from GRQ Military | C-GOV-1210 | C-GOV-1210: SS | C-GOV-1230 | C-GOV-1230: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1230 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from ITC ROW | C-GOV-1220 | C-GOV-1220: SS | C-GOV-1240 | C-GOV-1240: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1240 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from MCC | C-GOV-1230 | C-GOV-1230: SS | C-GOV-1250 | C-GOV-1250: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1250 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from TADWEER | C-GOV-1240 | C-GOV-1240: SS | C-GOV-1260 | C-GOV-1260: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1260 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from TRANSCO | C-GOV-1250 | C-GOV-1250: SS | C-GOV-1270 | C-GOV-1270: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1270 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from Zone Cops | C-GOV-1260 | C-GOV-1260: SS | C-GOV-1280 | C-GOV-1280: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1280 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from CICPA | C-GOV-1270 | C-GOV-1270: SS | C-GOV-1290 | C-GOV-1290: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1290 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from BARARI | C-GOV-1280 | C-GOV-1280: SS | C-GOV-1300 | C-GOV-1300: SS | 2023-10-02 | 2024-11-25 14:48
C-GOV-1300 | In Progress | P2543-R01-Oct24..4.1.1 | Construction NOC from Musanada | C-GOV-1290 | C-GOV-1290: SS | C-52-06CR-PL-CI-1800, C-52-0506-PL-CI-1800, C-52-0405-PL-CI-1800, C-52-0304-PL-CI-1800, C-4N-H5HG-PIPEL-1800, C-56-01HG-PL-CI-2000 | C-52-06CR-PL-CI-1800: SS 60, C-52-0506-PL-CI-1800: FS, C-52-0405-PL-CI-1800: FF 16, C-52-0304-PL-CI-1800: SS, C-4N-H5HG-PIPEL-1800: FF 14, C-56-01HG-PL-CI-2000: FF | 2023-10-02 | 2024-11-01 12:00
HE-GS-50 | Completed | P2543-R01-Oct24..1.EN.2.3.3 | Receive Company Comments - Geo Technical Survey Report 52" Line | HE-GS-90 | HE-GS-90: FS | HE-GS-60 | HE-GS-60: FS | 2024-03-04 | 2024-03-08
HE-GS-60 | Completed | P2543-R01-Oct24..1.EN.2.3.3 | Re-Issue for Approval - Geo Technical Survey Report 52" Line | HE-GS-50 | HE-GS-50: FS | HE-GS-70 | HE-GS-70: FS | 2024-03-10 | 2024-05-31 17:30
HE-GS-70 | Completed | P2543-R01-Oct24..1.EN.2.3.3 | Obtain Company Approval - Geo Technical Survey Report 52" Line | HE-GS-60 | HE-GS-60: FS | HE-GS-80 | HE-GS-80: FS | 2024-06-03 07:30 | 2024-07-26 17:30
HE-GS-80 | Completed | P2543-R01-Oct24..1.EN.2.3.3 | Final Issue for Design/ Construction-Geotechnical Survey Report 52" Line | HE-GS-70 | HE-GS-70: FS | ML1009-B04 | ML1009-B04: FS | 2024-07-29 07:30 | 2024-08-30 17:30
HE-GS-90 | Completed | P2543-R01-Oct24..1.EN.2.3.3 | Issue ICR - Geo Technical Survey Report 52" Line | HE-SS-0040 | HE-SS-0040: FS | HE-PL-0190, HE-GS-50, HE-GS-140 | HE-PL-0190: FS, HE-GS-50: FS, HE-GS-140: FS | 2024-02-26 | 2024-03-01
HE-TS-200 | Completed | P2543-R01-Oct24..1.EN.2.2.5 | Re-Issue for Approval-Topographical Survey Report 56" Line | HE-TS-240 | HE-TS-240: FS | HE-TS-210 | HE-TS-210: FS | 2024-03-18 | 2024-05-31 17:30
HE-TS-210 | Completed | P2543-R01-Oct24..1.EN.2.2.5 | Obtain Company Approval-Topographical Survey Report 56" Line | HE-TS-200 | HE-TS-200: FS | HE-TS-220 | HE-TS-220: FS | 2024-06-03 07:30 | 2024-07-26 17:30
HE-TS-220 | Completed | P2543-R01-Oct24..1.EN.2.2.5 | Final Issue for Design/ Construction-Topographical Survey Report 56" Line | HE-TS-210 | HE-TS-210: FS | ML1008-B03, HE-PL-2610, HE-PI-0370 | ML1008-B03: FS, HE-PL-2610: FS, HE-PI-0370: FS | 2024-07-29 07:30 | 2024-08-30 17:30
HE-TS-230 | Completed | P2543-R01-Oct24..1.EN.2.2.5 | Issue ICR-Topographical Survey Report 56" Line | HE-SS-0030, HE-TS-280 | HE-SS-0030: FS, HE-TS-280: FS | HE-PL-0130, HE-PI-0350, HE-PL-2570, HE-PL-0150, HE-PL-2390, HE-TS-240, HE-PI-0340, HE-TS-330 | HE-PL-0130: FS, HE-PI-0350: FS, HE-PL-2570: FS, HE-PL-0150: FS, HE-PL-2390: FS 10, HE-TS-240: FS, HE-PI-0340: FS, HE-TS-330: FS | 2024-03-04 | 2024-03-08
HE-TS-240 | Completed | P2543-R01-Oct24..1.EN.2.2.5 | Receive Company Comments-Topographical Survey Report 56" Line | HE-TS-230 | HE-TS-230: FS | HE-TS-200 | HE-TS-200: FS | 2024-03-10 | 2024-03-17
HE-TS-250 | Completed | P2543-R01-Oct24..1.EN.2.2.1 | Re-Issue for Approval-Topographical Survey Report 52" Line | HE-TS-290 | HE-TS-290: FS | HE-TS-260 | HE-TS-260: FF | 2024-03-18 | 2024-05-31 17:30
HE-TS-260 | Completed | P2543-R01-Oct24..1.EN.2.2.1 | Obtain Company Approval-Topographical Survey Report 52" Line | HE-TS-250 | HE-TS-250: FF | HE-TS-270 | HE-TS-270: FF | 2024-04-12 | 2024-07-26 17:30
HE-TS-270 | Completed | P2543-R01-Oct24..1.EN.2.2.1 | Final Issue for Design/ Construction-Topographical Survey Report 52" Line | HE-TS-260 | HE-TS-260: FF | HE-PL-2670, ML1009-B04, HE-PI-0440 | HE-PL-2670: FS, ML1009-B04: FS, HE-PI-0440: FS | 2024-04-19 | 2024-08-30 17:30
HE-TS-280 | Completed | P2543-R01-Oct24..1.EN.2.2.1 | Issue ICR-Topographical Survey Report 52" Line | HE-SS-0030 | HE-SS-0030: FS | HE-PL-0190, HE-PL-0210, HE-PL-2450, HE-PL-2630, HE-TS-290, HE-TS-230 | HE-PL-0190: FS, HE-PL-0210: FS, HE-PL-2450: FS 15, HE-PL-2630: FS, HE-TS-290: FS, HE-TS-230: FS | 2024-02-26 | 2024-03-08
HE-TS-290 | Completed | P2543-R01-Oct24..1.EN.2.2.1 | Receive Company Comments-Topographical Survey Report 52" Line | HE-TS-280 | HE-TS-280: FS | HE-TS-250 | HE-TS-250: FS | 2024-03-10 | 2024-03-17
HE-GS-100 | Completed | P2543-R01-Oct24..1.EN.2.3.1 | Receive Company Comments - Geo Technical Survey Report 56" Line | HE-GS-140 | HE-GS-140: FS | HE-GS-110 | HE-GS-110: FS | 2024-03-10 | 2024-03-17
HE-GS-110 | Completed | P2543-R01-Oct24..1.EN.2.3.1 | Re-Issue for Approval - Geo Technical Survey Report 56" Line | HE-GS-100 | HE-GS-100: FS | HE-GS-120 | HE-GS-120: FS | 2024-03-18 | 2024-05-31
HE-GS-120 | Completed | P2543-R01-Oct24..1.EN.2.3.1 | Obtain Company Approval - Geo Technical Survey Report 56" Line | HE-GS-110 | HE-GS-110: FS | HE-GS-130 | HE-GS-130: FS | 2024-06-03 07:30 | 2024-07-26 17:30
HE-GS-130 | Completed | P2543-R01-Oct24..1.EN.2.3.1 | Final Issue for Design/ Construction-Geotechnical Survey Report 56" Line | HE-GS-120 | HE-GS-120: FS | ML1008-B03 | ML1008-B03: FS | 2024-07-29 07:30 | 2024-08-30 17:30
HE-GS-140 | Completed | P2543-R01-Oct24..1.EN.2.3.1 | Issue ICR - Geo Technical Survey Report 56" Line | HE-SS-0040, HE-GS-90 | HE-SS-0040: FS, HE-GS-90: FS | HE-PL-0130, HE-GS-100, HE-PI-0340, HE-GS-190 | HE-PL-0130: FS, HE-GS-100: FS, HE-PI-0340: FS, HE-GS-190: FS | 2024-03-04 | 2024-03-08
HE-GS-150 | Completed | P2543-R01-Oct24..1.EN.2.3.2 | Receive Company Comments - Geo Technical Survey Report 4" Line | HE-GS-190 | HE-GS-190: FS | HE-GS-160 | HE-GS-160: FS | 2024-03-18 | 2024-03-25
HE-GS-160 | Completed | P2543-R01-Oct24..1.EN.2.3.2 | Re-Issue for Approval - Geo Technical Survey Report 4" Line | HE-GS-150 | HE-GS-150: FS | HE-GS-170 | HE-GS-170: FS | 2024-03-26 | 2024-05-01 17:30
HE-GS-170 | Completed | P2543-R01-Oct24..1.EN.2.3.2 | Obtain Company Approval - Geo Technical Survey Report 4" Line | HE-GS-160 | HE-GS-160: FS | HE-GS-180 | HE-GS-180: FS | 2024-05-10 | 2024-05-14
HE-GS-180 | Completed | P2543-R01-Oct24..1.EN.2.3.2 | Final Issue for Design/ Construction-Geotechnical Survey Report 4" Line | HE-GS-170 | HE-GS-170: FS | HE-PL-2550, HE-PL-3570 | HE-PL-2550: FS, HE-PL-3570: FS | 2024-05-20 | 2024-05-26
HE-GS-190 | Completed | P2543-R01-Oct24..1.EN.2.3.2 | Issue ICR - Geo Technical Survey Report 4" Line | HE-SS-0040, HE-GS-140 | HE-SS-0040: FS, HE-GS-140: FS | HE-PL-0250, HE-GS-150 | HE-PL-0250: FS, HE-GS-150: FS | 2024-03-10 | 2024-03-17
HE-TS-300 | Completed | P2543-R01-Oct24..1.EN.2.2.3 | Re-Issue for Approval-Topographical Survey Report 4" Line | HE-TS-340 | HE-TS-340: FS | HE-TS-310 | HE-TS-310: SS | 2024-03-18 | 2024-08-30 17:30
HE-TS-310 | Completed | P2543-R01-Oct24..1.EN.2.2.3 | Obtain Company Approval-Topographical Survey Report 4" Line | HE-TS-300 | HE-TS-300: SS | HE-TS-320 | HE-TS-320: FS | 2024-05-10 | 2024-05-14
HE-TS-320 | Completed | P2543-R01-Oct24..1.EN.2.2.3 | Final Issue for Design/ Construction-Topographical Survey Report 4" Line | HE-TS-310 | HE-TS-310: FS | HE-PI-0510, HE-PL-2550, HE-PL-3570 | HE-PI-0510: FS, HE-PL-2550: FS, HE-PL-3570: FS | 2024-05-20 | 2024-05-26
HE-TS-330 | Completed | P2543-R01-Oct24..1.EN.2.2.3 | Issue ICR-Topographical Survey Report 4" Line | HE-SS-0030, HE-TS-230 | HE-SS-0030: FS, HE-TS-230: FS | HE-PL-3580, HE-PL-3530, HE-PL-0250, HE-PL-2690, HE-PI-0490, HE-PL-0270, HE-PL-2510, HE-TS-340 | HE-PL-3580: FS, HE-PL-3530: FS 60, HE-PL-0250: FS, HE-PL-2690: FS, HE-PI-0490: FS, HE-PL-0270: FS, HE-PL-2510: FS 30, HE-TS-340: FS | 2024-03-04 | 2024-03-08
HE-TS-340 | Completed | P2543-R01-Oct24..1.EN.2.2.3 | Receive Company Comments-Topographical Survey Report 4" Line | HE-TS-330 | HE-TS-330: FS | HE-TS-300 | HE-TS-300: FS | 2024-03-10 | 2024-03-17
CCM-PM4560 | Not Started | P2543-R01-Oct24..4.4.2.1 | Commissioning | PRECOM-56-PL-1000 | PRECOM-56-PL-1000: FS | CCM-PM4510 | CCM-PM4510: FF | 2025-09-28 07:00 | 2025-11-12 17:00
CCM-PM4570 | Not Started | P2543-R01-Oct24..4.4.2.2 | Commissioning | PRECOM-56-HGHC-1000 | PRECOM-56-HGHC-1000: FS | CCM-PM4550, ML-PAC1 (Internal) | CCM-PM4550: FF, ML-PAC1 (Internal): FS | 2025-10-09 15:00 | 2025-12-09 15:00
CCM-PM4580 | Not Started | P2543-R01-Oct24..4.4.2.3 | Commissioning | PRECOM-52-HG01-1000, PRECOM-52-06CR-1000, PRECOM-52-0203-1000, PRECOM-52-0201-1000, PRECOM-52-0304-1000, PRECOM-52-0405-1000, PRECOM-52-0506-1000, COM-1000, ML1829-E28 | PRECOM-52-HG01-1000: FS, PRECOM-52-06CR-1000: FS, PRECOM-52-0203-1000: FS, PRECOM-52-0201-1000: FS, PRECOM-52-0304-1000: FS, PRECOM-52-0405-1000: FS, PRECOM-52-0506-1000: FS, COM-1000: FF, ML1829-E28: FS | CCM-PM4520, CCM-PM4530, ML-PAC2 (Internal) | CCM-PM4520: FF, CCM-PM4530: FS, ML-PAC2 (Internal): FS | 2025-11-03 11:30 | 2025-12-11 11:30
CCM-PM4590 | Not Started | P2543-R01-Oct24..4.4.2.4 | Commissioning | PRECOM-36-KM-1000 | PRECOM-36-KM-1000: FS | CCM-PM4520 | CCM-PM4520: FF 27 | 2025-09-04 09:00 | 2025-10-22 09:00
CCM-PM4600 | Not Started | P2543-R01-Oct24..4.4.2.5 | Commissioning | PRECOM-4N-H5HG-1000 | PRECOM-4N-H5HG-1000: FS | CCM-PM4550 | CCM-PM4550: FS | 2025-09-25 12:30 | 2025-11-11 12:30
CCM-PM4610 | Not Started | P2543-R01-Oct24..4.4.2.6 | Commissioning | PRE-COM1310 | PRE-COM1310: FS | CCM-PM4510 | CCM-PM4510: FS | 2025-08-21 11:00 | 2025-10-08 11:00
CCM-PM4620 | Not Started | P2543-R01-Oct24..4.4.2.7 | Commissioning | PRE-COM1330 | PRE-COM1330: FS | CCM-PM4520 | CCM-PM4520: FS | 2025-09-04 11:00 | 2025-10-22 11:00
C-COM-1000 | Completed | P2543-R01-Oct24..4.1.2 | Procedure Qualification Material (56", 52", 42", 30", Test Rings etc) Receipt at Site | HM-PL-0030 | HM-PL-0030: FF 0 | C-COM-1020, C-COM-1010 | C-COM-1020: FS 205, C-COM-1010: FS |  | 2024-05-31 07:00
C-COM-1010 | Completed | P2543-R01-Oct24..4.1.2 | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | C-COM-1000, ML1559-E01 | C-COM-1000: FS, ML1559-E01: FS | C-56-PL-607-PI-1000, C-56-G-HT101-ME-1010, C-56-HC01-PL-ME-3600, C-52-06CR-PL-ME-3600, C-56-01HG-PL-ME-3600, C-56-01HG-PL-ME-3800, C-52-0506-PL-ME-3600, C-52-0405-PL-ME-3600, C-52-0304-PL-ME-3600, C-52-0203-PL-ME-3600, C-52-0102-PL-ME-3600, C-52-HG01-PL-ME | C-56-PL-607-PI-1000: FS, C-56-G-HT101-ME-1010: FS, C-56-HC01-PL-ME-3600: FS, C-52-06CR-PL-ME-3600: FS, C-56-01HG-PL-ME-3600: FS, C-56-01HG-PL-ME-3800: FS, C-52-0506-PL-ME-3600: FS, C-52-0405-PL-ME-3600: FS, C-52-0304-PL-ME-3600: FS, C-52-0203-PL-ME-3600: F | 2024-05-09 07:00 | 2024-07-30 09:48
HE-BL-1020 | Completed | P2543-R01-Oct24..1.EN.12.3 | Re-Issue for Approval-Structural Design Calculation | HE-BL-1010 | HE-BL-1010: FS | HE-BL-1030 | HE-BL-1030: FS | 2024-03-31 | 2024-04-05
HE-BL-1040 | In Progress | P2543-R01-Oct24..1.EN.12.3 | Final Issue for Design-Structural Design Calculation | HE-BL-1030 | HE-BL-1030: FS | HE-BL-1310 | HE-BL-1310: FF | 2024-04-11 | 2024-11-15 17:30
HE-BL-1030 | Completed | P2543-R01-Oct24..1.EN.12.3 | Obtain Company Approval-Structural Design Calculation | HE-BL-1020 | HE-BL-1020: FS | HE-BL-1040 | HE-BL-1040: FS | 2024-04-06 | 2024-04-16
HE-BL-1000 | Completed | P2543-R01-Oct24..1.EN.12.3 | Issue ICR-Structural Design Calculation | HE-CS-0010 | HE-CS-0010: FS | HE-BL-1230, HE-BL-1180, HE-BL-1130, HE-BL-1010 | HE-BL-1230: FF 10, HE-BL-1180: FF 2, HE-BL-1130: FS 10, HE-BL-1010: FS | 2024-01-29 | 2024-02-15
HE-BL-1010 | Completed | P2543-R01-Oct24..1.EN.12.3 | Receive Company Comments-Structural Design Calculation | HE-BL-1000 | HE-BL-1000: FS | HE-BL-1020 | HE-BL-1020: FS | 2024-02-26 | 2024-03-08
HE-BL-1050 | Completed | P2543-R01-Oct24..1.EN.12.1 | Re-Issue for Approval-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | HE-BL-1090 | HE-BL-1090: FS | HE-BL-1070 | HE-BL-1070: FS | 2024-04-12 | 2024-04-26
HE-BL-1060 | Completed | P2543-R01-Oct24..1.EN.12.1 | Final Issue for Design-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | HE-BL-1070 | HE-BL-1070: FS | HE-BL-1360 | HE-BL-1360: FF | 2024-05-24 | 2024-06-23 17:30
HE-BL-1070 | Completed | P2543-R01-Oct24..1.EN.12.1 | Obtain Company Approval-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | HE-BL-1050 | HE-BL-1050: FS | HE-BL-1060 | HE-BL-1060: FS | 2024-04-26 | 2024-05-10
HE-BL-1080 | Completed | P2543-R01-Oct24..1.EN.12.1 | Issue ICR-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | HE-BL-1130 | HE-BL-1130: FS 10 | HE-BL-1380, HE-BL-1090 | HE-BL-1380: FF 1, HE-BL-1090: FS | 2024-03-31 | 2024-04-23
HE-BL-1090 | Completed | P2543-R01-Oct24..1.EN.12.1 | Receive Company Comments-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | HE-BL-1080 | HE-BL-1080: FS | HE-BL-1050 | HE-BL-1050: FS | 2024-03-29 | 2024-04-12
HE-BL-1100 | Completed | P2543-R01-Oct24..1.EN.12.2 | Re-Issue for Approval-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | HE-BL-1140 | HE-BL-1140: FS | HE-BL-1120 | HE-BL-1120: FS | 2024-04-05 | 2024-04-10
HE-BL-1110 | In Progress | P2543-R01-Oct24..1.EN.12.2 | Final Issue for Design-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | HE-BL-1120 | HE-BL-1120: FS | HE-BL-1310 | HE-BL-1310: FF | 2024-04-26 | 2024-11-08 17:30
HE-BL-1120 | Completed | P2543-R01-Oct24..1.EN.12.2 | Obtain Company Approval-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | HE-BL-1100 | HE-BL-1100: FS | HE-BL-1110 | HE-BL-1110: FS | 2024-04-11 | 2024-04-22
HE-BL-1130 | Completed | P2543-R01-Oct24..1.EN.12.2 | Issue ICR-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | HE-BL-1000 | HE-BL-1000: FS 10 | HE-BL-1080, HE-BL-1140 | HE-BL-1080: FS 10, HE-BL-1140: FS | 2024-02-03 | 2024-02-17
HE-BL-1140 | Completed | P2543-R01-Oct24..1.EN.12.2 | Receive Company Comments-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | HE-BL-1130 | HE-BL-1130: FS | HE-BL-1100 | HE-BL-1100: FS | 2024-03-31 | 2024-04-04
HE-BL-1150 | Completed | P2543-R01-Oct24..1.EN.12.4 | Re-Issue for Approval-Plumbing Design, Calculation & Details | HE-BL-1190 | HE-BL-1190: FS | HE-BL-1170 | HE-BL-1170: FS | 2024-01-26 | 2024-02-29
HE-BL-1160 | Completed | P2543-R01-Oct24..1.EN.12.4 | Final Issue for Design-Plumbing Design, Calculation & Details | HE-BL-1170 | HE-BL-1170: FS | HE-BL-1310 | HE-BL-1310: FS | 2024-03-16 | 2024-03-27
HE-BL-1170 | Completed | P2543-R01-Oct24..1.EN.12.4 | Obtain Company Approval-Plumbing Design, Calculation & Details | HE-BL-1150 | HE-BL-1150: FS | HE-BL-1160 | HE-BL-1160: FS | 2024-02-29 | 2024-03-15
HE-BL-1180 | Completed | P2543-R01-Oct24..1.EN.12.4 | Issue ICR-Plumbing Design, Calculation & Details | HE-BL-1000 | HE-BL-1000: FF 2 | HE-BL-1190 | HE-BL-1190: FS | 2023-12-13 | 2023-12-29
HE-BL-1190 | Completed | P2543-R01-Oct24..1.EN.12.4 | Receive Company Comments-Plumbing Design, Calculation & Details | HE-BL-1180 | HE-BL-1180: FS | HE-BL-1150 | HE-BL-1150: FS | 2023-12-29 | 2024-01-16
HE-BL-1200 | Completed | P2543-R01-Oct24..1.EN.12.5 | Re-Issue for Approval-Layout, Elevation & Finishing for E&I Building at Habshan complex | HE-BL-1240 | HE-BL-1240: FS | HE-BL-1220 | HE-BL-1220: FS | 2024-03-04 | 2024-03-18
HE-BL-1210 | In Progress | P2543-R01-Oct24..1.EN.12.5 | Final Issue for Design-Layout, Elevation & Finishing for E&I Building at Habshan complex | HE-BL-1220 | HE-BL-1220: FS | HE-BL-1310 | HE-BL-1310: FF | 2024-05-13 | 2024-11-08 17:30
HE-BL-1220 | Completed | P2543-R01-Oct24..1.EN.12.5 | Obtain Company Approval-Layout, Elevation & Finishing for E&I Building at Habshan complex | HE-BL-1200 | HE-BL-1200: FS | HE-BL-1210 | HE-BL-1210: FS | 2024-03-18 | 2024-03-29
HE-BL-1230 | Completed | P2543-R01-Oct24..1.EN.12.5 | Issue ICR-Layout, Elevation & Finishing for E&I Building at Habshan complex | HE-BL-1000 | HE-BL-1000: FF 10 | HE-BL-1280, HE-BL-1240, HE-BL-1330 | HE-BL-1280: FS, HE-BL-1240: FS, HE-BL-1330: FS | 2024-01-19 | 2024-02-16
HE-BL-1240 | Completed | P2543-R01-Oct24..1.EN.12.5 | Receive Company Comments-Layout, Elevation & Finishing for E&I Building at Habshan complex | HE-BL-1230 | HE-BL-1230: FS | HE-BL-1200 | HE-BL-1200: FS | 2024-02-18 | 2024-03-02
HE-BL-1250 | Completed | P2543-R01-Oct24..1.EN.12.6 | Re-Issue for Approval-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | HE-BL-1290 | HE-BL-1290: FS | HE-BL-1270 | HE-BL-1270: FS | 2024-08-26 07:30 | 2024-09-06 17:30
HE-BL-1260 | In Progress | P2543-R01-Oct24..1.EN.12.6 | Final Issue for Design-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | HE-BL-1270 | HE-BL-1270: FS | HE-BL-1360 | HE-BL-1360: FS | 2024-09-23 07:30 | 2024-11-08 17:30
HE-BL-1270 | Completed | P2543-R01-Oct24..1.EN.12.6 | Obtain Company Approval-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | HE-BL-1250 | HE-BL-1250: FS | HE-BL-1260 | HE-BL-1260: FS | 2024-09-09 07:30 | 2024-09-23 17:30
HE-BL-1280 | Completed | P2543-R01-Oct24..1.EN.12.6 | Issue ICR-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | HE-BL-1230 | HE-BL-1230: FS | HE-BL-1290 | HE-BL-1290: FS | 2024-07-29 07:30 | 2024-08-09 17:30
HE-BL-1290 | Completed | P2543-R01-Oct24..1.EN.12.6 | Receive Company Comments-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | HE-BL-1280 | HE-BL-1280: FS | HE-BL-1250 | HE-BL-1250: FS | 2024-08-12 07:30 | 2024-08-23 17:30
HE-BL-1300 | Completed | P2543-R01-Oct24..1.EN.12.7 | Re-Issue for Approval-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | HE-BL-1340 | HE-BL-1340: FS | HE-BL-1320 | HE-BL-1320: FS | 2024-02-26 | 2024-03-17
HE-BL-1310 | In Progress | P2543-R01-Oct24..1.EN.12.7 | Final Issue for Design-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | HE-BL-1040, HE-BL-1210, HE-BL-1160, HE-BL-1110, HE-BL-1320 | HE-BL-1040: FF, HE-BL-1210: FF, HE-BL-1160: FS, HE-BL-1110: FF, HE-BL-1320: FS | HE-BL-1360, HE-BL-1360 | HE-BL-1360: FF, HE-BL-1360: SS | 2024-10-11 07:30 | 2024-11-15 17:30
HE-BL-1320 | Completed | P2543-R01-Oct24..1.EN.12.7 | Obtain Company Approval-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | HE-BL-1300 | HE-BL-1300: FS | HE-BL-1310 | HE-BL-1310: FS | 2024-03-18 | 2024-03-27
HE-BL-1330 | Completed | P2543-R01-Oct24..1.EN.12.7 | Issue ICR-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | HE-BL-1230 | HE-BL-1230: FS | HE-BL-1340 | HE-BL-1340: FS | 2023-12-10 | 2023-12-29
HE-BL-1340 | Completed | P2543-R01-Oct24..1.EN.12.7 | Receive Company Comments-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | HE-BL-1330 | HE-BL-1330: FS | HE-BL-1300 | HE-BL-1300: FS | 2023-12-30 | 2024-01-16
HE-BL-1350 | Not Started | P2543-R01-Oct24..1.EN.12.8 | Re-Issue for Approval-Instrument & Control Layouts | HE-BL-1390 | HE-BL-1390: FS | HE-BL-1370 | HE-BL-1370: FS | 2024-10-28 07:30 | 2024-11-08 17:30
HE-BL-1360 | Not Started | P2543-R01-Oct24..1.EN.12.8 | Final Issue for Design-Instrument & Control Layouts | HE-BL-1310, HE-BL-1310, HE-BL-1260, HE-BL-1060, HE-BL-1370 | HE-BL-1310: FF, HE-BL-1310: SS, HE-BL-1260: FS, HE-BL-1060: FF, HE-BL-1370: FS | C-COM-790 | C-COM-790: FF | 2024-11-25 07:30 | 2024-12-17 17:30
HE-BL-1370 | Not Started | P2543-R01-Oct24..1.EN.12.8 | Obtain Company Approval-Instrument & Control Layouts | HE-BL-1350 | HE-BL-1350: FS | HE-BL-1360 | HE-BL-1360: FS | 2024-11-11 07:30 | 2024-11-22 17:30
HE-BL-1380 | Completed | P2543-R01-Oct24..1.EN.12.8 | Issue ICR-Instrument & Control Layouts | HE-BL-1080 | HE-BL-1080: FF 1 | HE-BL-1390 | HE-BL-1390: FS | 2024-06-16 07:30 | 2024-06-23 17:30
HE-BL-1390 | Completed | P2543-R01-Oct24..1.EN.12.8 | Receive Company Comments-Instrument & Control Layouts | HE-BL-1380 | HE-BL-1380: FS | HE-BL-1350 | HE-BL-1350: FS | 2024-10-14 | 2024-10-25 17:30
HE-IC-3190 | Completed | P2543-R01-Oct24..1.EN.6.A202 | Issue ICR- Specification for HSSD | HE-IC-2730 | HE-IC-2730: FS | HE-IC-3390, HE-IC-3200 | HE-IC-3390: FF, HE-IC-3200: FS | 2024-01-05 | 2024-01-19
HE-IC-3200 | Completed | P2543-R01-Oct24..1.EN.6.A202 | Receive Company Comments- Specification for HSSD | HE-IC-3190 | HE-IC-3190: FS | HE-IC-3210 | HE-IC-3210: FS | 2024-01-20 | 2024-01-26
HE-IC-3210 | Completed | P2543-R01-Oct24..1.EN.6.A202 | Re-Issue for Approval- Specification for HSSD | HE-IC-3200 | HE-IC-3200: FS | HE-IC-3220 | HE-IC-3220: FS | 2024-01-29 | 2024-02-16
HE-IC-3220 | Completed | P2543-R01-Oct24..1.EN.6.A202 | Obtain Company Approval- Specification for HSSD | HE-IC-3210 | HE-IC-3210: FS | HE-IC-3230 | HE-IC-3230: FS | 2024-02-26 | 2024-03-08
HE-IC-3230 | Completed | P2543-R01-Oct24..1.EN.6.A202 | Final Issue for Design/ Construction-Specification for HSSD | HE-IC-3220 | HE-IC-3220: FS | HE-IC-0530, HE-IC-0530 | HE-IC-0530: FF, HE-IC-0530: FS | 2024-03-11 | 2024-04-18
HE-IC-3240 | Completed | P2543-R01-Oct24..1.EN.6.A2021 | Issue ICR- Specification for HYBRID PASSIVE COOLED SHELTER | HE-IC-0190 | HE-IC-0190: FS | HE-IC-3390, HE-IC-3340, HE-IC-3250 | HE-IC-3390: FS, HE-IC-3340: FS 7, HE-IC-3250: FS | 2023-10-20 | 2023-11-10
HE-IC-3250 | Completed | P2543-R01-Oct24..1.EN.6.A2021 | Receive Company Comments- Specification for HYBRID PASSIVE COOLED SHELTER | HE-IC-3240 | HE-IC-3240: FS | HE-IC-3260 | HE-IC-3260: FS | 2023-11-13 | 2023-11-28
HE-IC-3260 | Completed | P2543-R01-Oct24..1.EN.6.A2021 | Re-Issue for Approval- Specification for HYBRID PASSIVE COOLED SHELTER | HE-IC-3250 | HE-IC-3250: FS | HE-IC-3270 | HE-IC-3270: FS | 2023-11-29 | 2023-12-26
HE-IC-3270 | Completed | P2543-R01-Oct24..1.EN.6.A2021 | Obtain Company Approval- Specification for HYBRID PASSIVE COOLED SHELTER | HE-IC-3260 | HE-IC-3260: FS | HE-IC-3280 | HE-IC-3280: FS | 2023-12-27 | 2023-12-29
HE-IC-3280 | Completed | P2543-R01-Oct24..1.EN.6.A2021 | Final Issue for Design/ Construction-Specification for HYBRID PASSIVE COOLED SHELTER | HE-IC-3270 | HE-IC-3270: FS | HE-IC-0490 | HE-IC-0490: FS | 2024-02-26 | 2024-03-11
HE-IC-3290 | Completed | P2543-R01-Oct24..1.EN.6.4.A51 | Final Issue for Design/ Construction-Datasheets for PASSIVE COOLED SHELTER | HE-IC-3330 | HE-IC-3330: FS | HE-PL-1250 | HE-PL-1250: FF | 2024-02-02 | 2024-03-04
HE-IC-3300 | Completed | P2543-R01-Oct24..1.EN.6.4.A51 | Issue ICR- Datasheets for PASSIVE COOLED SHELTER | HE-IC-3340 | HE-IC-3340: FS | HE-IC-3310 | HE-IC-3310: FS | 2023-11-29 | 2023-12-13
HE-IC-3310 | Completed | P2543-R01-Oct24..1.EN.6.4.A51 | Receive Company Comments- Datasheets for PASSIVE COOLED SHELTER | HE-IC-3300 | HE-IC-3300: FS | HE-IC-3320 | HE-IC-3320: FS | 2023-12-14 | 2023-12-27
HE-IC-3320 | Completed | P2543-R01-Oct24..1.EN.6.4.A51 | Re-Issue for Approval- Datasheets for PASSIVE COOLED SHELTER | HE-IC-3310 | HE-IC-3310: FS | HE-IC-3330 | HE-IC-3330: FS | 2023-12-28 | 2024-01-17
HE-IC-3330 | Completed | P2543-R01-Oct24..1.EN.6.4.A51 | Obtain Company Approval- Datasheets for PASSIVE COOLED SHELTER | HE-IC-3320 | HE-IC-3320: FS | HE-IC-3290 | HE-IC-3290: FS | 2024-01-17 | 2024-01-19
HE-IC-3340 | Completed | P2543-R01-Oct24..1.EN.6.A9111 | Issue ICR- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | HE-IC-3240 | HE-IC-3240: FS 7 | HE-IC-3300, HE-IC-3350 | HE-IC-3300: FS, HE-IC-3350: FS | 2024-04-29 07:30 | 2024-05-09 17:30
HE-IC-3350 | Completed | P2543-R01-Oct24..1.EN.6.A9111 | Receive Company Comments- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | HE-IC-3340 | HE-IC-3340: FS | HE-IC-3360 | HE-IC-3360: FS | 2024-05-12 07:30 | 2024-05-23 17:30
HE-IC-3360 | Completed | P2543-R01-Oct24..1.EN.6.A9111 | Re-Issue for Approval- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | HE-IC-3350 | HE-IC-3350: FS | HE-IC-3370 | HE-IC-3370: FS | 2024-05-26 07:30 | 2024-05-30 17:30
HE-IC-3370 | Completed | P2543-R01-Oct24..1.EN.6.A9111 | Obtain Company Approval- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | HE-IC-3360 | HE-IC-3360: FS | HE-IC-3380 | HE-IC-3380: FS | 2024-06-02 07:30 | 2024-06-13 17:30
HE-IC-3380 | Completed | P2543-R01-Oct24..1.EN.6.A9111 | Final Issue for Design/ Construction-Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | HE-IC-3370 | HE-IC-3370: FS | HE-IC-0790, HE-IC-0490 | HE-IC-0790: FS, HE-IC-0490: FS | 2024-06-16 07:30 | 2024-06-20 17:30
HE-IC-3390 | Completed | P2543-R01-Oct24..1.EN.6.A3411 | Issue ICR-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | HE-IC-3190, HE-IC-3240 | HE-IC-3190: FF, HE-IC-3240: FS | HE-IC-3400 | HE-IC-3400: FS | 2024-02-26 | 2024-03-08
HE-IC-3400 | Completed | P2543-R01-Oct24..1.EN.6.A3411 | Receive Company Comments-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | HE-IC-3390 | HE-IC-3390: FS | HE-IC-3410 | HE-IC-3410: FS | 2024-02-26 | 2024-03-08
HE-IC-3410 | Completed | P2543-R01-Oct24..1.EN.6.A3411 | Re-Issue for Approval-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | HE-IC-3400 | HE-IC-3400: FS | HE-IC-3420 | HE-IC-3420: FS | 2024-02-26 | 2024-03-08
HE-IC-3420 | Completed | P2543-R01-Oct24..1.EN.6.A3411 | Obtain Company Approval-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | HE-IC-3410 | HE-IC-3410: FS | HE-IC-3430 | HE-IC-3430: FS | 2024-02-26 | 2024-03-08
HE-IC-3430 | In Progress | P2543-R01-Oct24..1.EN.6.A3411 | Final Issue for Design/ Construction-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | HE-IC-3420 | HE-IC-3420: FS | HE-IC-1370 | HE-IC-1370: FF | 2024-10-01 07:30 | 2024-11-08 17:30
HE-PL-3830 | Completed | P2543-R01-Oct24..1.EN.1.17 | Re-Issue for Approval - Specification -PIPELINE CROSSING CALCULATION REPORT | HE-PL-3870 | HE-PL-3870: FS | HE-PL-3840 | HE-PL-3840: FS | 2023-11-28 | 2023-11-28
HE-PL-3840 | Completed | P2543-R01-Oct24..1.EN.1.17 | Obtain Company Approval - PIPELINE CROSSING CALCULATION REPORT | HE-PL-3830 | HE-PL-3830: FS | HE-PL-3850 | HE-PL-3850: FS | 2023-11-28 | 2023-11-28
HE-PL-3850 | Completed | P2543-R01-Oct24..1.EN.1.17 | Final Issue for Design/ Construction - PIPELINE CROSSING CALCULATION REPORT | HE-PL-0050, HE-PL-3840 | HE-PL-0050: FS, HE-PL-3840: FS | HE-PL-0110 | HE-PL-0110: FS | 2023-11-28 | 2024-01-08
HE-PL-3860 | Completed | P2543-R01-Oct24..1.EN.1.17 | Issue ICR - Specification - PIPELINE CROSSING CALCULATION REPORT | HE-PL-0050, HE-PL-0010, HE-DB-80 | HE-PL-0050: FS 10, HE-PL-0010: FS, HE-DB-80: FS | HE-PL-3870 | HE-PL-3870: FS | 2023-08-23 | 2023-09-08
HE-PL-3870 | Completed | P2543-R01-Oct24..1.EN.1.17 | Receive Company Comments - PIPELINE CROSSING CALCULATION REPORT | HE-PL-3860 | HE-PL-3860: FS | HE-PL-3830 | HE-PL-3830: FS | 2023-09-11 | 2023-09-28
CTF-SO1040 | Completed | P2543-R01-Oct24..4.2.1 | Construction Plant & Equipment Facilities | CTF-SO1020 | CTF-SO1020: SS 14 | CTF-SO1050, CTF-SO1050 | CTF-SO1050: FF, CTF-SO1050: SS | 2023-12-11 07:30 | 2024-05-27 16:36
CTF-SO1050 | Completed | P2543-R01-Oct24..4.2.1 | Fabrication Facilities | CTF-SO1040, CTF-SO1040 | CTF-SO1040: FF, CTF-SO1040: SS | CTF-SO1060, C-56-PL-607-PI-1000, C-56-G-HT-CI-2000, C-56-G-HT-PI-1000, C-56-PR-838-PI-1000, C-52-06CR-FENCE-1000, C-52-598-06-PI-1000 | CTF-SO1060: SS 7, C-56-PL-607-PI-1000: FS, C-56-G-HT-CI-2000: FS, C-56-G-HT-PI-1000: FS, C-56-PR-838-PI-1000: FS, C-52-06CR-FENCE-1000: FS, C-52-598-06-PI-1000: FS | 2023-12-15 07:30 | 2024-05-28 16:36
CTF-SO1060 | Completed | P2543-R01-Oct24..4.2.1 | Ware House & Storage Facilities | CTF-SO1050 | CTF-SO1050: SS 7 | CTF-SO1070, CTF-SO1070 | CTF-SO1070: FF, CTF-SO1070: SS | 2023-12-15 07:30 | 2024-05-29 13:48
CTF-SO1070 | Completed | P2543-R01-Oct24..4.2.1 | Laboratory Facilities | CTF-SO1060, CTF-SO1060 | CTF-SO1060: FF, CTF-SO1060: SS | CTF-SO1030, CTF-SO1030 | CTF-SO1030: FF, CTF-SO1030: SS 2 | 2024-03-13 08:12 | 2024-06-11 08:12
C-COM-1020 | Not Started | P2543-R01-Oct24..4.1.2 | Procedure Qualification (PQT/WQT for Hot Tapping - 48", 42",36 & 30") | C-COM-1000 | C-COM-1000: FS 205 | C-56-G-HT101-ME-1000, C-52-D-HT002-ME-1000, C-36-KM-HT03-ME-1000 | C-56-G-HT101-ME-1000: FS, C-52-D-HT002-ME-1000: FS, C-36-KM-HT03-ME-1000: FS | 2025-01-26 08:00 | 2025-04-17 16:00
CTF-SO1080 | Completed | P2543-R01-Oct24..4.2.5 | Engineering Office at NPCC | ML1002 | ML1002: FS | CTF-1000, CTF-SO1010, CTF-1010 | CTF-1000: SS, CTF-SO1010: FS, CTF-1010: FS | 2023-07-19 | 2023-09-05
CTF-1010 | Completed | P2543-R01-Oct24..4.2.1 | NOC's / Approval /Survey | CTF-SO1080, ML1002, CTF-SO1000 | CTF-SO1080: FS, ML1002: FS, CTF-SO1000: SS 9 | ML1159-A08, C-COM-850, C-COM-750, C-56-HC01-PL-CI-1000, C-56-HC01-PL-CI-1000, C-56-PR-838-CI-1000, C-56-591-01-CI-1000, C-52-598-06-CI-1000, C-52-PR-839-CI-1000, C-52-EB1-CI-1000, C-52-D-HT-CI-1000, C-52-PL-838-CI-1000, C-52-IDS1-CI-1000, C-52-IDS2-CI-1000 | ML1159-A08: FF, C-COM-850: FS, C-COM-750: SS 6, C-56-HC01-PL-CI-1000: FS, C-56-HC01-PL-CI-1000: FF, C-56-PR-838-CI-1000: FS, C-56-591-01-CI-1000: FS, C-52-598-06-CI-1000: FS, C-52-PR-839-CI-1000: FF, C-52-EB1-CI-1000: FS, C-52-D-HT-CI-1000: FS, C-52-PL-838 | 2023-10-02 07:00 | 2023-12-19 07:30
C-56-PR-838-EI-1800 | Not Started | P2543-R01-Oct24..4.3.1.2.21.12.6.28 | Installation of Light Pole, Lighting & Fixtures | C-56-PR-838-EI-2000, C-56-PR-838-EI-2020 | C-56-PR-838-EI-2000: FS, C-56-PR-838-EI-2020: FS | C-56-PR-838-CI-2600, C-56-PR-838-EI-2050 | C-56-PR-838-CI-2600: FS, C-56-PR-838-EI-2050: FS | 2025-06-24 11:00 | 2025-07-19 11:00
C-PER-1020 | In Progress | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 1 | HE-PL-2990, HE-PL-2490 | HE-PL-2990: FS, HE-PL-2490: SS | C-52-HG01-CNM01-1000 | C-52-HG01-CNM01-1000: FS | 2024-04-15 | 2024-11-21 17:30
C-PER-1030 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 2 | HE-PL-2490 | HE-PL-2490: FF 14 | C-52-HG01-CNM02-1000 | C-52-HG01-CNM02-1000: FS | 2024-10-28 07:30 | 2024-12-20 17:30
C-PER-1040 | Completed | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 3 | HE-PL-2990, HE-PL-2990 | HE-PL-2990: FS, HE-PL-2990: FF | C-52-HG01-CNM03-1000, C-PER-1160, C-PER-1180 | C-52-HG01-CNM03-1000: FS, C-PER-1160: FS, C-PER-1180: FS | 2024-02-23 | 2024-04-23
C-PER-1050 | Completed | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 4 | HE-PL-2990, HE-PL-2990 | HE-PL-2990: FS, HE-PL-2990: FF | C-52-HG01-CNM04-1000, C-PER-1140, C-PER-1150 | C-52-HG01-CNM04-1000: FS, C-PER-1140: FS, C-PER-1150: FS | 2024-01-18 | 2024-03-18
C-PER-1060 | Completed | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 5 | HE-PL-2990 | HE-PL-2990: FS | C-52-0102-CNM05-1000 | C-52-0102-CNM05-1000: FS | 2024-05-15 | 2024-07-15
C-PER-1070 | In Progress | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 6 | HE-PL-2490, C-PER-1080, C-PER-1080 | HE-PL-2490: FF, C-PER-1080: SS 7, C-PER-1080: FF | C-52-0102-PL-ME-7400, C-52-0102-PL-CI-6800, PRECOM-52-0201-1000, ML1679-E13 | C-52-0102-PL-ME-7400: FS, C-52-0102-PL-CI-6800: FF, PRECOM-52-0201-1000: FS, ML1679-E13: FS | 2024-07-09 07:30 | 2024-12-31 17:30
C-PER-1080 | Completed | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 7 | HE-PL-2990 | HE-PL-2990: FS | C-52-0102-CNM07-1000, C-PER-1070, C-PER-1070 | C-52-0102-CNM07-1000: FS, C-PER-1070: SS 7, C-PER-1070: FF | 2024-05-15 | 2024-07-15
C-PER-1090 | Completed | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 8 | HE-PL-2990, HE-PL-2990 | HE-PL-2990: FS, HE-PL-2990: FF | C-52-0102-CNH08-1000 | C-52-0102-CNH08-1000: FS | 2024-05-09 | 2024-07-09
C-PER-1100 | Completed | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 9 | HE-PL-2990 | HE-PL-2990: FS | C-52-0102-CNH09-1000 | C-52-0102-CNH09-1000: FS | 2024-05-09 | 2024-07-09
C-PER-1110 | Completed | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 10 | HE-PL-2990 | HE-PL-2990: FS | C-52-0102-CNH10-1000 | C-52-0102-CNH10-1000: FS | 2024-03-07 | 2024-05-07
C-PER-1130 | Completed | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 12 | HE-PL-2490 | HE-PL-2490: SS 14 | C-52-0203-PL-ME-4810, C-52-0203-PL-CA-5220, C-52-0203-PL-TE-8200, C-52-0203-PL-ME-7400, C-52-0203-PL-CI-6800, PRECOM-52-0203-1000, C-52-0203-PL-CI-6000, ML1679-E13, C-PER-1580 | C-52-0203-PL-ME-4810: FF, C-52-0203-PL-CA-5220: FF, C-52-0203-PL-TE-8200: FF, C-52-0203-PL-ME-7400: FS, C-52-0203-PL-CI-6800: FF, PRECOM-52-0203-1000: FS, C-52-0203-PL-CI-6000: FF, ML1679-E13: FS, C-PER-1580: FS | 2024-05-04 | 2024-05-28 17:30
C-PER-1140 | Completed | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13 | HE-PL-2490, C-PER-1050 | HE-PL-2490: SS, C-PER-1050: FS | C-52-0304-PL-ME-4810, C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, PRECOM-52-0304-1000, C-52-0304-PL-CI-6000, ML1679-E13 | C-52-0304-PL-ME-4810: FF, C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF, PRECOM-52-0304-1000: FS, C-52-0304-PL-CI-6000: FF, ML1679-E13: FS | 2024-05-06 07:30 | 2024-06-25 17:30
C-PER-1150 | Completed | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13A | HE-PL-2490, C-PER-1050 | HE-PL-2490: SS, C-PER-1050: FS | C-52-0304-PL-ME-4810, C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, PRECOM-52-0304-1000, C-52-0304-PL-CI-6000, ML1679-E13 | C-52-0304-PL-ME-4810: FF, C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF, PRECOM-52-0304-1000: FS, C-52-0304-PL-CI-6000: FF, ML1679-E13: FS | 2024-05-06 07:30 | 2024-07-14 17:30
C-PER-1160 | Completed | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 14 | HE-PL-2490, C-PER-1040 | HE-PL-2490: SS, C-PER-1040: FS | C-PER-1310, C-PER-1320, C-PER-1340, C-52-0304-PL-ME-4810, C-52-0304-PL-CA-5220, C-52-0304-PL-TE-8200, C-52-0304-PL-ME-7400, C-52-0304-PL-CI-6800, PRECOM-52-0304-1000, C-52-0304-PL-CI-6000, ML1679-E13 | C-PER-1310: FS, C-PER-1320: FS, C-PER-1340: FS, C-52-0304-PL-ME-4810: FF, C-52-0304-PL-CA-5220: FF, C-52-0304-PL-TE-8200: FF, C-52-0304-PL-ME-7400: FS, C-52-0304-PL-CI-6800: FF, PRECOM-52-0304-1000: FS, C-52-0304-PL-CI-6000: FF, ML1679-E13: FS | 2024-05-30 07:30 | 2024-07-14 17:30
C-PER-1180 | Completed | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | HE-PL-2490, C-PER-1040 | HE-PL-2490: SS, C-PER-1040: FS | C-52-0506-PL-ME-4810, C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, PRECOM-52-0506-1000, C-52-0506-PL-CI-6000, ML1679-E13, C-52-0405-PL-ME-4810, C-52-0405-PL-CA-5220, C-52-0405-PL-TE-8200, C-52-0405-PL-ME-7400, C-5 | C-52-0506-PL-ME-4810: FF, C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF, PRECOM-52-0506-1000: FS, C-52-0506-PL-CI-6000: FF, ML1679-E13: FS, C-52-0405-PL-ME-4810: FF, C-52-0405-PL-CA-5220: FF, C-52-04 | 2024-05-30 07:30 | 2024-07-15 17:30
C-PER-1190 | Completed | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 17 | HE-PL-2490 | HE-PL-2490: SS | C-52-0405-CNM17-1000 | C-52-0405-CNM17-1000: FS | 2024-06-30 07:30 | 2024-07-26
C-PER-1200 | In Progress | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 18 | HE-PL-2490, HE-PL-3090 | HE-PL-2490: SS, HE-PL-3090: FF 14 | C-52-0405-CNM18-1000 | C-52-0405-CNM18-1000: FS | 2024-07-13 07:30 | 2024-12-31 17:30
C-PER-1210 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 19 | HE-PL-2490, HE-PL-3090 | HE-PL-2490: FF, HE-PL-3090: FS | C-52-0405-CNH19-1000 | C-52-0405-CNH19-1000: SS | 2024-11-04 07:30 | 2024-11-12 17:30
C-PER-1220 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 20 | HE-PL-2490, HE-PL-3090 | HE-PL-2490: FS, HE-PL-3090: FS | C-52-0405-CNH20-1000 | C-52-0405-CNH20-1000: FS | 2024-11-04 07:30 | 2024-11-12 17:30
C-PER-1250 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 23 | HE-PL-2490 | HE-PL-2490: FS | C-52-0405-CNM23-1000 | C-52-0405-CNM23-1000: FS | 2024-11-04 07:30 | 2024-11-18 17:30
C-PER-1260 | In Progress | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 24 | HE-PL-2490 | HE-PL-2490: SS | C-52-0405-CNH24-1000 | C-52-0405-CNH24-1000: FS | 2024-07-10 07:30 | 2024-12-09 17:30
C-PER-1280 | Completed | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 25A | HE-PL-2490 | HE-PL-2490: SS | C-52-0506-PL-ME-4810, C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, PRECOM-52-0506-1000, C-52-0506-PL-CI-6000, ML1679-E13 | C-52-0506-PL-ME-4810: FF, C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF, PRECOM-52-0506-1000: FS, C-52-0506-PL-CI-6000: FF, ML1679-E13: FS | 2024-05-28 07:30 | 2024-07-26 17:30
C-PER-1300 | In Progress | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 27 | HE-PL-2490 | HE-PL-2490: SS 14 | C-52-0506-CNH27-1000 | C-52-0506-CNH27-1000: FS | 2024-07-14 07:30 | 2024-12-24 17:30
C-PER-1310 | In Progress | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 28 | HE-PL-2490, C-PER-1160 | HE-PL-2490: FF 14, C-PER-1160: FS | C-52-0506-PL-ME-4810, C-52-0506-PL-CA-5220, C-52-0506-PL-TE-8200, C-52-0506-PL-ME-7400, C-52-0506-PL-CI-6800, PRECOM-52-0506-1000, C-52-0506-PL-CI-6000, ML1679-E13 | C-52-0506-PL-ME-4810: FF, C-52-0506-PL-CA-5220: FF, C-52-0506-PL-TE-8200: FF, C-52-0506-PL-ME-7400: FS, C-52-0506-PL-CI-6800: FF, PRECOM-52-0506-1000: FS, C-52-0506-PL-CI-6000: FF, ML1679-E13: FS | 2024-07-12 07:30 | 2024-12-31 17:30
C-PER-1320 | In Progress | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 29 | HE-PL-2490, C-PER-1160 | HE-PL-2490: FF 14, C-PER-1160: FS | C-52-06CR-CNM31-1200, C-52-06CR-PL-ME-4810, C-52-06CR-PL-CA-5220, C-52-06CR-PL-TE-8200, C-52-06CR-PL-ME-7400, C-52-06CR-PL-CI-6800, PRECOM-52-06CR-1000, ML1679-E13 | C-52-06CR-CNM31-1200: FS, C-52-06CR-PL-ME-4810: FF, C-52-06CR-PL-CA-5220: FF, C-52-06CR-PL-TE-8200: FF, C-52-06CR-PL-ME-7400: FF, C-52-06CR-PL-CI-6800: FF, PRECOM-52-06CR-1000: FS, ML1679-E13: FS | 2024-07-13 07:30 | 2024-12-31 17:30
C-PER-1330 | In Progress | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 30 | HE-PL-2490 | HE-PL-2490: SS | C-52-06CR-CNH30-1000 | C-52-06CR-CNH30-1000: FS 15 | 2024-07-15 07:30 | 2025-02-12 17:30
C-PER-1340 | In Progress | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 31 | HE-PL-2490, C-PER-1160 | HE-PL-2490: FF 14, C-PER-1160: FS | C-52-06CR-CNM31-1000 | C-52-06CR-CNM31-1000: FS | 2024-07-12 07:30 | 2024-11-22 17:30
C-PER-1350 | In Progress | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 1 | HE-PL-2430 | HE-PL-2430: SS | C-56-HC01-CNH01-1000, C-PER-1400 | C-56-HC01-CNH01-1000: FS, C-PER-1400: FF 14 | 2024-07-03 07:30 | 2024-11-07 17:30
C-PER-1360 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 2 | C-PER-1000, C-PER-1420, HE-PL-2430 | C-PER-1000: FS, C-PER-1420: SS 1, HE-PL-2430: FS | C-56-HC01-CNH02-1000, C-PER-1370 | C-56-HC01-CNH02-1000: FS, C-PER-1370: SS | 2024-11-05 07:30 | 2024-12-12 17:30
C-PER-1370 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 3 | HE-PL-2430, C-PER-1000, C-PER-1360 | HE-PL-2430: FF 14, C-PER-1000: FS, C-PER-1360: SS | C-56-HC01-CNM03-1000, C-PER-1450 | C-56-HC01-CNM03-1000: FS, C-PER-1450: SS 7 | 2024-11-05 07:30 | 2024-12-27 17:30
C-PER-1380 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 4 | HE-PL-2430, C-PER-1000, C-PER-1390 | HE-PL-2430: FS, C-PER-1000: FS, C-PER-1390: SS 14 | C-56-HC01-PL-ME-5010, C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-ME-7400, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-6800, PRECOM-56-HGHC-1000, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-ME-5010: FF, C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-ME-7400: FS, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-6800: FF, PRECOM-56-HGHC-1000: FS, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2024-11-22 07:30 | 2025-01-07 17:30
C-PER-1390 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 5 | HE-PL-2430, C-PER-1000, C-PER-1460 | HE-PL-2430: FS, C-PER-1000: FS, C-PER-1460: SS 7 | C-56-HC01-CNH05-1000, C-PER-1380 | C-56-HC01-CNH05-1000: FS, C-PER-1380: SS 14 | 2024-11-04 07:30 | 2024-12-17 17:30
C-PER-1400 | In Progress | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 6 | HE-PL-2430, C-PER-1000, C-PER-1350 | HE-PL-2430: FF 14, C-PER-1000: FS, C-PER-1350: FF 14 | C-56-HC01-PL-ME-5010, C-56-HC01-PL-CA-5220, C-56-HC01-PL-TE-8200, C-56-HC01-PL-ME-7400, C-56-HC01-PL-CA-5400, C-56-HC01-PL-TE-8400, C-56-HC01-PL-CI-6800, PRECOM-56-HGHC-1000, C-56-HC01-PL-CI-7000, ML1579-E03 | C-56-HC01-PL-ME-5010: FF, C-56-HC01-PL-CA-5220: FF, C-56-HC01-PL-TE-8200: FF, C-56-HC01-PL-ME-7400: FS, C-56-HC01-PL-CA-5400: FF, C-56-HC01-PL-TE-8400: FF, C-56-HC01-PL-CI-6800: FF, PRECOM-56-HGHC-1000: FS, C-56-HC01-PL-CI-7000: FF, ML1579-E03: FS | 2024-07-25 07:30 | 2024-12-31 17:30
C-PER-1420 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 8 | C-PER-1000, HE-PL-2890, HE-PL-2430 | C-PER-1000: FS, HE-PL-2890: FF, HE-PL-2430: FS | C-56-HC01-CNM08-1000, C-PER-1360 | C-56-HC01-CNM08-1000: FS 15, C-PER-1360: SS 1 | 2024-11-04 07:30 | 2024-11-28 17:30
C-PER-1430 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 9 | HE-PL-2430, C-PER-1000, C-PER-1450 | HE-PL-2430: FS, C-PER-1000: FS, C-PER-1450: SS 14 | C-56-01HG-PL-ME-5010, C-56-01HG-PL-ME-7400, C-56-01HG-PL-CA-5420, C-56-01HG-PL-TE-8400, C-56-01HG-PL-CI-6800, PRECOM-56-HGHC-1000, C-56-01HG-PL-CI-7000, ML1579-E03 | C-56-01HG-PL-ME-5010: FF, C-56-01HG-PL-ME-7400: FS, C-56-01HG-PL-CA-5420: FF, C-56-01HG-PL-TE-8400: FF, C-56-01HG-PL-CI-6800: FF, PRECOM-56-HGHC-1000: FS, C-56-01HG-PL-CI-7000: FF, ML1579-E03: FS | 2024-12-06 07:30 | 2025-02-07 17:30
C-PER-1440 | In Progress | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 10 | HE-PL-2430 | HE-PL-2430: SS 14 | C-56-01HG-CNH10-1000 | C-56-01HG-CNH10-1000: FS 25 | 2024-07-10 07:30 | 2024-11-01 17:30
C-PER-1450 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 11 | HE-PL-2430, C-PER-1000, C-PER-1370 | HE-PL-2430: FS, C-PER-1000: FS, C-PER-1370: SS 7 | C-56-01HG-CNM11-1000, C-PER-1430 | C-56-01HG-CNM11-1000: FS 10, C-PER-1430: SS 14 | 2024-11-14 07:30 | 2024-11-27 17:30
C-PER-1460 | In Progress | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 12 | HE-PL-2430 | HE-PL-2430: SS | C-56-01HG-CNM12-1000, C-PER-1390 | C-56-01HG-CNM12-1000: FS, C-PER-1390: SS 7 | 2024-07-25 07:30 | 2024-11-25 17:30
C-PER-1470 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 13 | HE-PL-2430, C-PER-1000, HE-PL-2890 | HE-PL-2430: FS, C-PER-1000: FS, HE-PL-2890: SS 7 | C-56-01HG-CNM13-1000 | C-56-01HG-CNM13-1000: FS | 2024-11-04 07:30 | 2025-01-08 17:30
C-PER-1480 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 1 | C-PER-1000, HE-PL-2550 | C-PER-1000: FS, HE-PL-2550: FS | C-4N-H5HG-CNH01-1000 | C-4N-H5HG-CNH01-1000: FS | 2024-11-04 07:30 | 2025-01-08 17:30
C-PER-1490 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 2 | HE-PL-2550, C-PER-1000 | HE-PL-2550: FS, C-PER-1000: FS | C-4N-H5HG-CNH02-1000 | C-4N-H5HG-CNH02-1000: FS | 2024-11-04 07:30 | 2025-01-08 17:30
C-PER-1500 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 3 | HE-PL-2550, C-PER-1000 | HE-PL-2550: FS, C-PER-1000: FS | C-4N-H5HG-CNH03-1000 | C-4N-H5HG-CNH03-1000: FS | 2024-11-04 07:30 | 2025-01-08 17:30
C-PER-1510 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 4 | HE-PL-2550, C-PER-1000 | HE-PL-2550: FS, C-PER-1000: FS | C-4N-H5HG-CNH04-1000, C-PER-1520, C-PER-1530, C-PER-1540, C-PER-1550 | C-4N-H5HG-CNH04-1000: FS, C-PER-1520: FS, C-PER-1530: FS, C-PER-1540: FS, C-PER-1550: FS | 2024-11-04 07:30 | 2025-01-08 17:30
C-PER-1520 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 5 | HE-PL-2550, C-PER-1000, C-PER-1510 | HE-PL-2550: FS, C-PER-1000: FS, C-PER-1510: FS | C-4N-H5HG-CNH05-1000 | C-4N-H5HG-CNH05-1000: FS | 2025-01-09 07:30 | 2025-03-12 17:30
C-PER-1530 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 6 | HE-PL-2550, C-PER-1000, C-PER-1510 | HE-PL-2550: FS, C-PER-1000: FS, C-PER-1510: FS | C-4N-H5HG-CNH06-1000 | C-4N-H5HG-CNH06-1000: FS | 2025-01-09 07:30 | 2025-03-12 17:30
C-PER-1540 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 7 | HE-PL-2550, C-PER-1000, C-PER-1510 | HE-PL-2550: FS, C-PER-1000: FS, C-PER-1510: FS | C-4N-H5HG-CNH07-1000 | C-4N-H5HG-CNH07-1000: FS | 2025-01-09 07:30 | 2025-03-12 17:30
C-PER-1550 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 8 | HE-PL-2550, C-PER-1000, C-PER-1510 | HE-PL-2550: FS, C-PER-1000: FS, C-PER-1510: FS | C-4N-H5HG-CNH08-1000 | C-4N-H5HG-CNH08-1000: FS | 2025-01-09 07:30 | 2025-03-12 17:30
C-PER-1560 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-4" Water Pipeline-NDRC 1 | HE-PL-3570, C-PER-1000 | HE-PL-3570: FS, C-PER-1000: FS | C-4N-H5HG-CNH1-1000, C-PER-1570 | C-4N-H5HG-CNH1-1000: FS, C-PER-1570: FS | 2024-11-04 07:30 | 2025-01-08 17:30
C-PER-1570 | Not Started | P2543-R01-Oct24..4.1.7 | Trial pit, Crossing Methodology, NOC & Permits-4" Water Pipeline-NDRC 2 | HE-PL-3570, C-PER-1000, C-PER-1560 | HE-PL-3570: FS, C-PER-1000: FS, C-PER-1560: FS | C-4N-H5HG-CNH2-1000 | C-4N-H5HG-CNH2-1000: FS | 2025-01-09 07:30 | 2025-03-12 17:30
C-PER-1580 | Completed | P2543-R01-Oct24..4.1.7 | NOC & Permits-BVS01-52" | C-PER-1130 | C-PER-1130: FS | C-52-598-01-CI-1010 | C-52-598-01-CI-1010: FS 20 | 2024-04-25 07:30 | 2024-10-25
C-PER-1590 | In Progress | P2543-R01-Oct24..4.1.7 | NOC & Permits-BVS02-52" | HE-PL-2670 | HE-PL-2670: SS | C-52-598-02-CI-1010 | C-52-598-02-CI-1010: FS 25 | 2024-04-25 07:30 | 2024-10-28 07:30
C-PER-1600 | In Progress | P2543-R01-Oct24..4.1.7 | NOC & Permits-BVS03-52" | HE-PL-2670 | HE-PL-2670: SS | C-52-598-03-CI-1010 | C-52-598-03-CI-1010: FS 30 | 2024-04-25 07:30 | 2024-10-28 07:30
C-PER-1610 | In Progress | P2543-R01-Oct24..4.1.7 | NOC & Permits-BVS04-52" | HE-PL-2670 | HE-PL-2670: SS | C-52-598-04-CI-1010 | C-52-598-04-CI-1010: FS 35 | 2024-04-25 07:30 | 2024-10-28 07:30
C-PER-1620 | In Progress | P2543-R01-Oct24..4.1.7 | NOC & Permits-BVS05-52" | HE-PL-2670 | HE-PL-2670: SS | C-52-598-05-CI-1000, C-52-598-05-CI-1010 | C-52-598-05-CI-1000: SS, C-52-598-05-CI-1010: FS 25 | 2024-04-25 07:30 | 2024-11-15 17:30
C-PER-1630 | In Progress | P2543-R01-Oct24..4.1.7 | NOC & Permits-BVS06-52" | HE-PL-2670 | HE-PL-2670: SS | C-52-598-06-CI-1000 | C-52-598-06-CI-1000: FS 27 | 2024-04-25 07:30 | 2024-11-22 17:30
C-PER-1650 | Not Started | P2543-R01-Oct24..4.1.7 | NOC & Permits-Sweihan CRS | HE-PL-2670 | HE-PL-2670: FS | C-52-PL-838-CI-1000, C-52-PR-839-CI-1000, C-52-EB1-CI-1000 | C-52-PL-838-CI-1000: FS 30, C-52-PR-839-CI-1000: FS 25, C-52-EB1-CI-1000: FS 25 | 2024-11-04 07:30 | 2024-11-29 17:30
C-PER-0915 | Completed | P2543-R01-Oct24..4.1.7 | Mobilization of Job Performers-56" Pipelines & Stations,4" Pipeline | HE-PL-2390 | HE-PL-2390: FS | C-PER-1000 | C-PER-1000: FS | 2024-04-09 07:30 | 2024-05-17 17:30
C-PER-1000 | Completed | P2543-R01-Oct24..4.1.7 | Receiving Permits-56" Pipelines & Stations,4" Pipeline | C-PER-0915, HE-PL-0170, HE-PL-0290 | C-PER-0915: FS, HE-PL-0170: SS 14, HE-PL-0290: SS 14 | C-PER-1360, C-PER-1370, C-PER-1380, C-PER-1390, C-PER-1400, C-PER-1420, C-PER-1430, C-PER-1450, C-PER-1470, C-PER-1480, C-PER-1490, C-PER-1500, C-PER-1510, C-PER-1520, C-PER-1530, C-PER-1540, C-PER-1550, C-PER-1560, C-PER-1570, C-4N-H5HG-PIPEL-1000 | C-PER-1360: FS, C-PER-1370: FS, C-PER-1380: FS, C-PER-1390: FS, C-PER-1400: FS, C-PER-1420: FS, C-PER-1430: FS, C-PER-1450: FS, C-PER-1470: FS, C-PER-1480: FS, C-PER-1490: FS, C-PER-1500: FS, C-PER-1510: FS, C-PER-1520: FS, C-PER-1530: FS, C-PER-1540: FS, | 2024-02-29 07:30 | 2024-04-29 17:30
ML1020 (Internal) | Not Started | P2543-R01-Oct24..ML.CO1 | Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | PRECOM-56-PL-1000, PRECOM-56-EB2-1000, PRECOM-56-G-1000, PRECOM-56-HGHC-1000, PRECOM-56-PR-1000, PRECOM-56-59101-1000, PRECOM-56-59801-1000, PRECOM-56-59802-1000, PRECOM-56-59804-1000, PRECOM-56-59805-1000 | PRECOM-56-PL-1000: FS, PRECOM-56-EB2-1000: FS, PRECOM-56-G-1000: FS, PRECOM-56-HGHC-1000: FS, PRECOM-56-PR-1000: FS, PRECOM-56-59101-1000: FS, PRECOM-56-59801-1000: FS, PRECOM-56-59802-1000: FS, PRECOM-56-59804-1000: FS, PRECOM-56-59805-1000: FS | ML1060 | ML1060: FF 65 |  | 2025-10-11 11:00
ML1030 (Internal) | Not Started | P2543-R01-Oct24..ML.CO1 | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-0201-1000, PRECOM-52-PL-1000, PRECOM-52-HG01-1000, PRECOM-52-0203-1000, PRECOM-52-IDS1-1000, PRECOM-52-0304-1000, PRECOM-52-IDS2-1000, PRECOM-52-0405-1000, PRECOM-52-D-1000, PRECOM-52-IDS3-1000, PRECOM-52-0506-1000, PRECOM-52-59806-1000, PRECOM-5 | PRECOM-52-0201-1000: FS, PRECOM-52-PL-1000: FS, PRECOM-52-HG01-1000: FS, PRECOM-52-0203-1000: FS, PRECOM-52-IDS1-1000: FS, PRECOM-52-0304-1000: FS, PRECOM-52-IDS2-1000: FS, PRECOM-52-0405-1000: FS, PRECOM-52-D-1000: FS, PRECOM-52-IDS3-1000: FS, PRECOM-52-0 | ML1060 | ML1060: FS 39 |  | 2025-11-09 12:30
ML-PAC1 (Internal) | Not Started | P2543-R01-Oct24..ML.4 | PAC 1 - 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | CCM-PM4550, CCM-PM4570 | CCM-PM4550: FS, CCM-PM4570: FS | ML1060, ML2039-F05 | ML1060: FS 12, ML2039-F05: FF |  | 2025-12-09 15:00
ML-PAC2 (Internal) | Not Started | P2543-R01-Oct24..ML.4 | PAC 2 - 52" Sales Gas Pipeline & 36"Jump-over Line | CCM-PM4530, CCM-PM4580 | CCM-PM4530: FS 11, CCM-PM4580: FS | ML1060, ML2049-F06 | ML1060: FS, ML2049-F06: FF |  | 2026-01-05 07:00
C-56-01HG-CME09-1080 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.5.1 | Trench Excavation | C-56-01HG-CME10-1000, C-56-HC01-CME01-1000 | C-56-01HG-CME10-1000: FS 1, C-56-HC01-CME01-1000: FS 1 | C-56-01HG-CME09-1090, C-56-HC01-CME02-1000 | C-56-01HG-CME09-1090: FS, C-56-HC01-CME02-1000: FS 1 | 2025-04-19 13:00 | 2025-04-22 13:00
C-56-01HG-CME09-1090 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.5.2 | Bedding | C-56-01HG-CME09-1080 | C-56-01HG-CME09-1080: FS | C-56-01HG-CME09-1100 | C-56-01HG-CME09-1100: FS | 2025-04-22 13:00 | 2025-04-24 13:00
C-56-01HG-CME09-1100 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.5.3 | Lowering | C-56-01HG-CME09-1090 | C-56-01HG-CME09-1090: FS | C-56-01HG-CME09-1110 | C-56-01HG-CME09-1110: FS | 2025-04-24 13:00 | 2025-04-26 13:00
C-56-01HG-CME09-1110 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.5.3 | Section Tie-in Welding | C-56-01HG-CME09-1100 | C-56-01HG-CME09-1100: FS | C-56-01HG-CME09-1120 | C-56-01HG-CME09-1120: FS | 2025-04-26 13:00 | 2025-04-30 13:00
C-56-01HG-CME09-1120 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.5.3 | NDT (Tie-in Joint) | C-56-01HG-CME09-1110 | C-56-01HG-CME09-1110: FS | C-56-01HG-CME09-1130 | C-56-01HG-CME09-1130: FS | 2025-04-30 13:00 | 2025-05-03 13:00
C-56-01HG-CME09-1130 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.5.3 | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME09-1120 | C-56-01HG-CME09-1120: FS | C-56-01HG-CME09-1140 | C-56-01HG-CME09-1140: FS | 2025-05-03 13:00 | 2025-05-08 10:00
C-56-01HG-CME09-1140 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.5.4 | Holiday Testing | C-56-01HG-CME09-1130 | C-56-01HG-CME09-1130: FS | C-56-01HG-CME09-1150 | C-56-01HG-CME09-1150: FS | 2025-05-08 10:00 | 2025-05-10 11:00
C-56-01HG-CME09-1150 | Not Started | P2543-R01-Oct24..4.3.1.2.3.12.2.5.5 | Padding & Back Filling | C-56-01HG-CME09-1140 | C-56-01HG-CME09-1140: FS | C-56-01HG-PL-CI-6200 | C-56-01HG-PL-CI-6200: FF 7 | 2025-05-10 11:00 | 2025-05-13 11:00
C-56-HC01-CME10-1090 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.2.1 | Trench Excavation | C-56-HC01-CME16-1000 | C-56-HC01-CME16-1000: FS 1 | C-56-HC01-CME10-1100, C-56-HC01-CME10-1170 | C-56-HC01-CME10-1100: FS, C-56-HC01-CME10-1170: FS 1 | 2025-05-30 11:00 | 2025-06-02 11:00
C-56-HC01-CME10-1100 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.2.2 | Bedding | C-56-HC01-CME10-1090 | C-56-HC01-CME10-1090: FS | C-56-HC01-CME10-1110 | C-56-HC01-CME10-1110: FS | 2025-06-02 11:00 | 2025-06-04 11:00
C-56-HC01-CME10-1110 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.2.3 | Lowering | C-56-HC01-CME10-1100 | C-56-HC01-CME10-1100: FS | C-56-HC01-CME10-1120 | C-56-HC01-CME10-1120: FS | 2025-06-04 11:00 | 2025-06-09 11:00
C-56-HC01-CME10-1120 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.2.3 | Section Tie-in Welding | C-56-HC01-CME10-1110 | C-56-HC01-CME10-1110: FS | C-56-HC01-CME10-1130 | C-56-HC01-CME10-1130: FS | 2025-06-09 11:00 | 2025-06-12 11:00
C-56-HC01-CME10-1130 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.2.3 | NDT (Tie-in Joint) | C-56-HC01-CME10-1120 | C-56-HC01-CME10-1120: FS | C-56-HC01-CME10-1140 | C-56-HC01-CME10-1140: FS | 2025-06-12 11:00 | 2025-06-16 11:00
C-56-HC01-CME10-1140 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.2.3 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME10-1130 | C-56-HC01-CME10-1130: FS | C-56-HC01-CME10-1150 | C-56-HC01-CME10-1150: FS | 2025-06-16 11:00 | 2025-06-19 11:00
C-56-HC01-CME10-1150 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.2.4 | Holiday Testing | C-56-HC01-CME10-1140 | C-56-HC01-CME10-1140: FS | C-56-HC01-CME10-1160 | C-56-HC01-CME10-1160: FS | 2025-06-19 11:00 | 2025-06-21 11:00
C-56-HC01-CME10-1160 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.2.5 | Padding & Back Filling | C-56-HC01-CME10-1150 | C-56-HC01-CME10-1150: FS | C-56-HC01-PL-CI-6200 | C-56-HC01-PL-CI-6200: FF 7 | 2025-06-21 11:00 | 2025-06-24 11:00
C-56-HC01-CME10-1170 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.3.1 | Trench Excavation | C-56-HC01-CME10-1090 | C-56-HC01-CME10-1090: FS 1 | C-56-HC01-CME10-1180, C-52-06CR-CME10-1000 | C-56-HC01-CME10-1180: FS, C-52-06CR-CME10-1000: FS 1 | 2025-06-03 11:00 | 2025-06-07 11:00
C-56-HC01-CME10-1180 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.3.2 | Bedding | C-56-HC01-CME10-1170 | C-56-HC01-CME10-1170: FS | C-56-HC01-CME10-1190 | C-56-HC01-CME10-1190: FS | 2025-06-07 11:00 | 2025-06-10 11:00
C-56-HC01-CME10-1190 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.3.3 | Lowering | C-56-HC01-CME10-1180 | C-56-HC01-CME10-1180: FS | C-56-HC01-CME10-1200 | C-56-HC01-CME10-1200: FS | 2025-06-10 11:00 | 2025-06-12 11:00
C-56-HC01-CME10-1200 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.3.3 | Section Tie-in Welding | C-56-HC01-CME10-1190 | C-56-HC01-CME10-1190: FS | C-56-HC01-CME10-1210 | C-56-HC01-CME10-1210: FS | 2025-06-12 11:00 | 2025-06-16 11:00
C-56-HC01-CME10-1210 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.3.3 | NDT (Tie-in Joint) | C-56-HC01-CME10-1200 | C-56-HC01-CME10-1200: FS | C-56-HC01-CME10-1220 | C-56-HC01-CME10-1220: FS | 2025-06-16 11:00 | 2025-06-19 11:00
C-56-HC01-CME10-1220 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.3.3 | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME10-1210 | C-56-HC01-CME10-1210: FS | C-56-HC01-CME10-1230 | C-56-HC01-CME10-1230: FS | 2025-06-19 11:00 | 2025-06-23 11:00
C-56-HC01-CME10-1230 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.3.4 | Holiday Testing | C-56-HC01-CME10-1220 | C-56-HC01-CME10-1220: FS | C-56-HC01-CME10-1240 | C-56-HC01-CME10-1240: FS | 2025-06-23 11:00 | 2025-06-25 11:00
C-56-HC01-CME10-1240 | Not Started | P2543-R01-Oct24..4.3.1.2.2.12.2.3.5 | Padding & Back Filling | C-56-HC01-CME10-1230 | C-56-HC01-CME10-1230: FS | C-56-HC01-PL-CI-6200 | C-56-HC01-PL-CI-6200: FF 7 | 2025-06-25 11:00 | 2025-06-28 11:00
C-52-0102-CME06-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.5.1 | Trench Excavation | C-52-0102-CME05-1000 | C-52-0102-CME05-1000: SS | C-52-0102-CME06-1100, C-52-0304-CME01-1000 | C-52-0102-CME06-1100: FS, C-52-0304-CME01-1000: FS | 2024-11-28 07:00 | 2024-11-29 17:00
C-52-0102-CME06-1100 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.5.2 | Bedding | C-52-0102-CME06-1090 | C-52-0102-CME06-1090: FS | C-52-0102-CME06-1110 | C-52-0102-CME06-1110: FS | 2024-11-30 07:00 | 2024-12-04 17:00
C-52-0102-CME06-1110 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.5.3 | Lowering | C-52-0102-CME06-1100 | C-52-0102-CME06-1100: FS | C-52-0102-CME06-1120 | C-52-0102-CME06-1120: FS | 2024-12-05 07:00 | 2024-12-06 17:00
C-52-0102-CME06-1120 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.5.3 | Section Tie-in Welding | C-52-0102-CME06-1110 | C-52-0102-CME06-1110: FS | C-52-0102-CME06-1130 | C-52-0102-CME06-1130: FS | 2024-12-07 07:00 | 2024-12-10 17:00
C-52-0102-CME06-1130 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.5.3 | NDT (Tie-in Joint) | C-52-0102-CME06-1120 | C-52-0102-CME06-1120: FS | C-52-0102-CME06-1140 | C-52-0102-CME06-1140: FS | 2024-12-11 07:00 | 2024-12-13 17:00
C-52-0102-CME06-1140 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.5.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CME06-1130 | C-52-0102-CME06-1130: FS | C-52-0102-CME06-1150 | C-52-0102-CME06-1150: FS | 2024-12-14 07:00 | 2024-12-17 17:00
C-52-0102-CME06-1150 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.5.4 | Holiday Testing | C-52-0102-CME06-1140 | C-52-0102-CME06-1140: FS | C-52-0102-CME06-1160 | C-52-0102-CME06-1160: FS | 2024-12-18 07:00 | 2024-12-19 17:00
C-52-0102-CME06-1160 | Not Started | P2543-R01-Oct24..4.3.1.3.8.21.2.5.5 | Padding & Back Filling | C-52-0102-CME06-1150 | C-52-0102-CME06-1150: FS | C-52-0102-PL-ME-7400, ML1080 | C-52-0102-PL-ME-7400: FS, ML1080: FS | 2024-12-20 07:00 | 2024-12-21 17:00
C-52-0203-CME04-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.2.1.1 | Trench Excavation | C-52-0203-CME04-1000 | C-52-0203-CME04-1000: FS 1 | C-52-0203-CME04-1090 | C-52-0203-CME04-1090: FS | 2024-10-26 07:00 | 2024-10-28 17:00
C-52-0203-CME04-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.2.1.2 | Bedding | C-52-0203-CME04-1080 | C-52-0203-CME04-1080: FS | C-52-0203-CME04-1100 | C-52-0203-CME04-1100: FS | 2024-10-29 07:00 | 2024-10-30 17:00
C-52-0203-CME04-1100 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.2.1.3 | Lowering | C-52-0203-CME04-1090 | C-52-0203-CME04-1090: FS | C-52-0203-CME04-1110 | C-52-0203-CME04-1110: FF | 2024-10-31 07:00 | 2024-11-01 17:00
C-52-0203-CME04-1110 | In Progress | P2543-R01-Oct24..4.3.1.3.15.21.2.1.3 | Section Tie-in Welding | C-52-0203-CME04-1100 | C-52-0203-CME04-1100: FF | C-52-0203-CME04-1120 | C-52-0203-CME04-1120: SS | 2024-09-27 | 2024-11-01 17:00
C-52-0203-CME04-1120 | In Progress | P2543-R01-Oct24..4.3.1.3.15.21.2.1.3 | NDT (Tie-in Joint) | C-52-0203-CME04-1110 | C-52-0203-CME04-1110: SS | C-52-0203-CME04-1130 | C-52-0203-CME04-1130: FS | 2024-09-27 | 2024-11-01 17:00
C-52-0203-CME04-1130 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.2.1.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0203-CME04-1120 | C-52-0203-CME04-1120: FS | C-52-0203-CME04-1140 | C-52-0203-CME04-1140: FS | 2024-11-02 07:00 | 2024-11-05 17:00
C-52-0203-CME04-1140 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.2.1.4 | Holiday Testing | C-52-0203-CME04-1130 | C-52-0203-CME04-1130: FS | C-52-0203-CME04-1150 | C-52-0203-CME04-1150: FS | 2024-11-06 07:00 | 2024-11-07 17:00
C-52-0203-CME04-1150 | Not Started | P2543-R01-Oct24..4.3.1.3.15.21.2.1.5 | Padding & Back Filling | C-52-0203-CME04-1140 | C-52-0203-CME04-1140: FS | C-52-0203-PL-CI-6000, ML1070 | C-52-0203-PL-CI-6000: FF 7, ML1070: FS | 2024-11-08 07:00 | 2024-11-09 17:00
C-52-0304-CME06-1090 | Completed | P2543-R01-Oct24..4.3.1.3.16.21.2.1.1 | Trench Excavation | ML1002 | ML1002: FS | C-52-0304-CME06-1100, C-52-0304-CME06-1170 | C-52-0304-CME06-1100: FS, C-52-0304-CME06-1170: FS 1 | 2024-09-27 | 2024-10-14
C-52-0304-CME06-1100 | Completed | P2543-R01-Oct24..4.3.1.3.16.21.2.1.2 | Bedding | C-52-0304-CME06-1090 | C-52-0304-CME06-1090: FS | C-52-0304-CME06-1110 | C-52-0304-CME06-1110: FS | 2024-09-27 | 2024-10-14
C-52-0304-CME06-1110 | Completed | P2543-R01-Oct24..4.3.1.3.16.21.2.1.3 | Lowering | C-52-0304-CME06-1100 | C-52-0304-CME06-1100: FS | C-52-0304-CME06-1120 | C-52-0304-CME06-1120: FS 35 | 2024-10-14 | 2024-10-20
C-52-0304-CME06-1120 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.2.1.3 | Section Tie-in Welding | C-52-0304-CME06-1110 | C-52-0304-CME06-1110: FS 35 | C-52-0304-CME06-1130 | C-52-0304-CME06-1130: SS | 2024-10-20 | 2024-11-30 07:00
C-52-0304-CME06-1130 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.2.1.3 | NDT (Tie-in Joint) | C-52-0304-CME06-1120 | C-52-0304-CME06-1120: SS | C-52-0304-CME06-1140 | C-52-0304-CME06-1140: SS | 2024-10-20 | 2024-11-30 07:00
C-52-0304-CME06-1140 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.2.1.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME06-1130 | C-52-0304-CME06-1130: SS | C-52-0304-CME06-1150 | C-52-0304-CME06-1150: SS | 2024-10-20 | 2024-11-30 07:00
C-52-0304-CME06-1150 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.2.1.4 | Holiday Testing | C-52-0304-CME06-1140 | C-52-0304-CME06-1140: SS | C-52-0304-CME06-1160 | C-52-0304-CME06-1160: SS | 2024-10-20 | 2024-11-30 07:00
C-52-0304-CME06-1160 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.2.1.5 | Padding & Back Filling | C-52-0304-CME06-1150 | C-52-0304-CME06-1150: SS | C-52-0304-PL-CI-6000 | C-52-0304-PL-CI-6000: FF 7 | 2024-10-23 | 2024-12-04 17:00
C-52-0304-CME06-1170 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.2.2.1 | Trench Excavation | C-52-0304-CME06-1090 | C-52-0304-CME06-1090: FS 1 | C-52-0304-CME06-1180, C-52-0304-CME06-1250 | C-52-0304-CME06-1180: FS, C-52-0304-CME06-1250: FS 1 | 2024-09-27 | 2024-10-26 07:00
C-52-0304-CME06-1180 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.2.2.2 | Bedding | C-52-0304-CME06-1170 | C-52-0304-CME06-1170: FS | C-52-0304-CME06-1190 | C-52-0304-CME06-1190: FS | 2024-10-26 07:00 | 2024-10-28 17:00
C-52-0304-CME06-1190 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.2.2.3 | Lowering | C-52-0304-CME06-1180 | C-52-0304-CME06-1180: FS | C-52-0304-CME06-1200 | C-52-0304-CME06-1200: FF | 2024-10-29 07:00 | 2024-10-30 17:00
C-52-0304-CME06-1200 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.2.2.3 | Section Tie-in Welding | C-52-0304-CME06-1190 | C-52-0304-CME06-1190: FF | C-52-0304-CME06-1210 | C-52-0304-CME06-1210: SS | 2024-10-20 | 2024-10-30 17:00
C-52-0304-CME06-1210 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.2.2.3 | NDT (Tie-in Joint) | C-52-0304-CME06-1200 | C-52-0304-CME06-1200: SS | C-52-0304-CME06-1220 | C-52-0304-CME06-1220: SS | 2024-10-20 | 2024-10-30 17:00
C-52-0304-CME06-1220 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.2.2.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME06-1210 | C-52-0304-CME06-1210: SS | C-52-0304-CME06-1230 | C-52-0304-CME06-1230: SS | 2024-10-20 | 2024-10-30 17:00
C-52-0304-CME06-1230 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.2.2.4 | Holiday Testing | C-52-0304-CME06-1220 | C-52-0304-CME06-1220: SS | C-52-0304-CME06-1240 | C-52-0304-CME06-1240: FS | 2024-10-20 | 2024-10-29 17:00
C-52-0304-CME06-1240 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.2.2.5 | Padding & Back Filling | C-52-0304-CME06-1230 | C-52-0304-CME06-1230: FS | C-52-0304-PL-CI-6000 | C-52-0304-PL-CI-6000: FF 7 | 2024-10-30 07:00 | 2024-10-31 17:00
C-52-0304-CME06-1250 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.2.3.1 | Trench Excavation | C-52-0304-CME06-1170 | C-52-0304-CME06-1170: FS 1 | C-52-0304-CME06-1260, C-56-01HG-CME01-1000 | C-52-0304-CME06-1260: FS, C-56-01HG-CME01-1000: FS | 2024-10-28 07:00 | 2024-10-29 17:00
C-52-0304-CME06-1260 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.2.3.2 | Bedding | C-52-0304-CME06-1250 | C-52-0304-CME06-1250: FS | C-52-0304-CME06-1270 | C-52-0304-CME06-1270: FS | 2024-10-30 07:00 | 2024-10-31 17:00
C-52-0304-CME06-1270 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.2.3.3 | Lowering | C-52-0304-CME06-1260 | C-52-0304-CME06-1260: FS | C-52-0304-CME06-1280 | C-52-0304-CME06-1280: FF | 2024-11-01 07:00 | 2024-11-02 17:00
C-52-0304-CME06-1280 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.2.3.3 | Section Tie-in Welding | C-52-0304-CME06-1270 | C-52-0304-CME06-1270: FF | C-52-0304-CME06-1290 | C-52-0304-CME06-1290: SS | 2024-10-20 | 2024-11-02 17:00
C-52-0304-CME06-1290 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.2.3.3 | NDT (Tie-in Joint) | C-52-0304-CME06-1280 | C-52-0304-CME06-1280: SS | C-52-0304-CME06-1300 | C-52-0304-CME06-1300: SS | 2024-10-20 | 2024-11-02 17:00
C-52-0304-CME06-1300 | In Progress | P2543-R01-Oct24..4.3.1.3.16.21.2.3.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME06-1290 | C-52-0304-CME06-1290: SS | C-52-0304-CME06-1310 | C-52-0304-CME06-1310: FS | 2024-10-20 | 2024-11-02 17:00
C-52-0304-CME06-1310 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.2.3.4 | Holiday Testing | C-52-0304-CME06-1300 | C-52-0304-CME06-1300: FS | C-52-0304-CME06-1320 | C-52-0304-CME06-1320: FS | 2024-11-04 07:00 | 2024-11-05 17:00
C-52-0304-CME06-1320 | Not Started | P2543-R01-Oct24..4.3.1.3.16.21.2.3.5 | Padding & Back Filling | C-52-0304-CME06-1310 | C-52-0304-CME06-1310: FS | C-52-0304-PL-CI-6000 | C-52-0304-PL-CI-6000: FF 7 | 2024-11-06 07:00 | 2024-11-07 17:00
C-52-0506-CME25-2000 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.2.1.1 | Trench Excavation | C-52-0506-CME10-1000 | C-52-0506-CME10-1000: FS 1 | C-52-0506-CME25-2010, C-52-0506-CME28-1080 | C-52-0506-CME25-2010: FS, C-52-0506-CME28-1080: FS 1 | 2025-05-23 15:00 | 2025-05-26 15:00
C-52-0506-CME25-2010 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.2.1.2 | Bedding | C-52-0506-CME25-2000 | C-52-0506-CME25-2000: FS | C-52-0506-CME25-2020 | C-52-0506-CME25-2020: FS | 2025-05-26 15:00 | 2025-05-28 15:00
C-52-0506-CME25-2020 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.2.1.3 | Lowering | C-52-0506-CME25-2010 | C-52-0506-CME25-2010: FS | C-52-0506-CME25-2030 | C-52-0506-CME25-2030: FS | 2025-05-28 15:00 | 2025-05-30 15:00
C-52-0506-CME25-2030 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.2.1.3 | Section Tie-in Welding | C-52-0506-CME25-2020 | C-52-0506-CME25-2020: FS | C-52-0506-CME25-2040 | C-52-0506-CME25-2040: FS | 2025-05-30 15:00 | 2025-06-03 15:00
C-52-0506-CME25-2040 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.2.1.3 | NDT (Tie-in Joint) | C-52-0506-CME25-2030 | C-52-0506-CME25-2030: FS | C-52-0506-CME25-2050 | C-52-0506-CME25-2050: FS | 2025-06-03 15:00 | 2025-06-09 15:00
C-52-0506-CME25-2050 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.2.1.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME25-2040 | C-52-0506-CME25-2040: FS | C-52-0506-CME25-2060 | C-52-0506-CME25-2060: FS | 2025-06-09 15:00 | 2025-06-12 15:00
C-52-0506-CME25-2060 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.2.1.4 | Holiday Testing | C-52-0506-CME25-2050 | C-52-0506-CME25-2050: FS | C-52-0506-CME25-2070 | C-52-0506-CME25-2070: FS | 2025-06-12 15:00 | 2025-06-14 15:00
C-52-0506-CME25-2070 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.2.1.5 | Padding & Back Filling | C-52-0506-CME25-2060 | C-52-0506-CME25-2060: FS | C-52-0506-PL-CI-6000 | C-52-0506-PL-CI-6000: FF 7 | 2025-06-14 15:00 | 2025-06-17 15:00
C-52-0506-CME28-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.2.2.1 | Trench Excavation | C-52-0506-CME25-2000 | C-52-0506-CME25-2000: FS 1 | C-52-0506-CME28-1090, C-52-06CR-CME01-1000 | C-52-0506-CME28-1090: FS, C-52-06CR-CME01-1000: FS 1 | 2025-05-27 15:00 | 2025-05-29 15:00
C-52-0506-CME28-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.2.2.2 | Bedding | C-52-0506-CME28-1080 | C-52-0506-CME28-1080: FS | C-52-0506-CME28-1100 | C-52-0506-CME28-1100: FS | 2025-05-29 15:00 | 2025-05-31 15:00
C-52-0506-CME28-1100 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.2.2.3 | Lowering | C-52-0506-CME28-1090 | C-52-0506-CME28-1090: FS | C-52-0506-CME28-1110 | C-52-0506-CME28-1110: FS | 2025-05-31 15:00 | 2025-06-03 15:00
C-52-0506-CME28-1110 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.2.2.3 | Section Tie-in Welding | C-52-0506-CME28-1100 | C-52-0506-CME28-1100: FS | C-52-0506-CME28-1120 | C-52-0506-CME28-1120: FS | 2025-06-03 15:00 | 2025-06-09 15:00
C-52-0506-CME28-1120 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.2.2.3 | NDT (Tie-in Joint) | C-52-0506-CME28-1110 | C-52-0506-CME28-1110: FS | C-52-0506-CME28-1130 | C-52-0506-CME28-1130: FS | 2025-06-09 15:00 | 2025-06-12 15:00
C-52-0506-CME28-1130 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.2.2.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME28-1120 | C-52-0506-CME28-1120: FS | C-52-0506-CME28-1140 | C-52-0506-CME28-1140: FS | 2025-06-12 15:00 | 2025-06-16 15:00
C-52-0506-CME28-1140 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.2.2.4 | Holiday Testing | C-52-0506-CME28-1130 | C-52-0506-CME28-1130: FS | C-52-0506-CME28-1150 | C-52-0506-CME28-1150: FS | 2025-06-16 15:00 | 2025-06-18 15:00
C-52-0506-CME28-1150 | Not Started | P2543-R01-Oct24..4.3.1.3.18.21.2.2.5 | Padding & Back Filling | C-52-0506-CME28-1140 | C-52-0506-CME28-1140: FS | C-52-0506-PL-CI-6000 | C-52-0506-PL-CI-6000: FF 7 | 2025-06-18 15:00 | 2025-06-20 15:00
C-52-06CR-CME29-1080 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.1.1 | Trench Excavation | C-52-06CR-CME14-1000, C-52-06CR-CME13-1000 | C-52-06CR-CME14-1000: FS, C-52-06CR-CME13-1000: FS | C-52-06CR-CME29-1090 | C-52-06CR-CME29-1090: FS | 2025-07-19 15:00 | 2025-07-22 15:00
C-52-06CR-CME29-1090 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.1.2 | Bedding | C-52-06CR-CME29-1080 | C-52-06CR-CME29-1080: FS | C-52-06CR-CME29-1100 | C-52-06CR-CME29-1100: FS | 2025-07-22 15:00 | 2025-07-24 15:00
C-52-06CR-CME29-1100 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.1.3 | Lowering | C-52-06CR-CME29-1090 | C-52-06CR-CME29-1090: FS | C-52-06CR-CME29-1110 | C-52-06CR-CME29-1110: FS | 2025-07-24 15:00 | 2025-07-26 15:00
C-52-06CR-CME29-1110 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.1.3 | Section Tie-in Welding | C-52-06CR-CME29-1100 | C-52-06CR-CME29-1100: FS | C-52-06CR-CME29-1120 | C-52-06CR-CME29-1120: FS | 2025-07-26 15:00 | 2025-07-30 15:00
C-52-06CR-CME29-1120 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.1.3 | NDT (Tie-in Joint) | C-52-06CR-CME29-1110 | C-52-06CR-CME29-1110: FS | C-52-06CR-CME29-1130 | C-52-06CR-CME29-1130: FS | 2025-07-30 15:00 | 2025-08-02 15:00
C-52-06CR-CME29-1130 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.1.3 | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME29-1120 | C-52-06CR-CME29-1120: FS | C-52-06CR-CME29-1140 | C-52-06CR-CME29-1140: FS | 2025-08-02 15:00 | 2025-08-06 15:00
C-52-06CR-CME29-1140 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.1.4 | Holiday Testing | C-52-06CR-CME29-1130 | C-52-06CR-CME29-1130: FS | C-52-06CR-CME29-1150 | C-52-06CR-CME29-1150: FS | 2025-08-06 15:00 | 2025-08-08 15:00
C-52-06CR-CME29-1150 | Not Started | P2543-R01-Oct24..4.3.1.3.19.8.2.1.5 | Padding & Back Filling | C-52-06CR-CME29-1140 | C-52-06CR-CME29-1140: FS | C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CI-6000: FF 2 | 2025-08-08 15:00 | 2025-08-11 15:00
C-52-0405-CME16-1000 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.1.1 | Trench Excavation | C-52-0405-CME08-1000 | C-52-0405-CME08-1000: FS 1 | C-52-0405-CME16-1010, C-52-0405-CME09-1000 | C-52-0405-CME16-1010: FS, C-52-0405-CME09-1000: FS 1 | 2025-01-11 12:00 | 2025-01-14 12:00
C-52-0405-CME16-1010 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.1.2 | Bedding | C-52-0405-CME16-1000 | C-52-0405-CME16-1000: FS | C-52-0405-CME16-1020 | C-52-0405-CME16-1020: FS | 2025-01-14 12:00 | 2025-01-16 12:00
C-52-0405-CME16-1020 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.1.3 | Lowering | C-52-0405-CME16-1010 | C-52-0405-CME16-1010: FS | C-52-0405-CME16-1030 | C-52-0405-CME16-1030: FS | 2025-01-16 12:00 | 2025-01-18 12:00
C-52-0405-CME16-1030 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.1.3 | Section Tie-in Welding | C-52-0405-CME16-1020 | C-52-0405-CME16-1020: FS | C-52-0405-CME16-1040 | C-52-0405-CME16-1040: FS | 2025-01-18 12:00 | 2025-01-22 12:00
C-52-0405-CME16-1040 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.1.3 | NDT (Tie-in Joint) | C-52-0405-CME16-1030 | C-52-0405-CME16-1030: FS | C-52-0405-CME16-1050 | C-52-0405-CME16-1050: FS | 2025-01-22 12:00 | 2025-01-25 12:00
C-52-0405-CME16-1050 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.1.3 | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME16-1040 | C-52-0405-CME16-1040: FS | C-52-0405-CME16-1060 | C-52-0405-CME16-1060: FS | 2025-01-25 12:00 | 2025-01-29 12:00
C-52-0405-CME16-1060 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.1.4 | Holiday Testing | C-52-0405-CME16-1050 | C-52-0405-CME16-1050: FS | C-52-0405-CME16-1070 | C-52-0405-CME16-1070: FS | 2025-01-29 12:00 | 2025-01-31 12:00
C-52-0405-CME16-1070 | Not Started | P2543-R01-Oct24..4.3.1.3.17.21.2.1.5 | Padding & Back Filling | C-52-0405-CME16-1060 | C-52-0405-CME16-1060: FS | C-52-0405-PL-CI-6000 | C-52-0405-PL-CI-6000: FF 7 | 2025-01-31 12:00 | 2025-02-03 12:00

## TASKPRED
predtask__projwbs__wbs_full_name | task__projwbs__wbs_full_name | predtask__task_name | task__task_name | pred_task_id | task_id | pred_type | PREDTASK__status_code | TASK__status_code | lag_hr_cnt | delete_record_flag
(*)Predecessor WBS | (*)Successor WBS | (*)Predecessor Activity Name | (*)Successor Activity Name | Predecessor | Successor | Relationship Type | (*)Predecessor Activity Status | (*)Successor Activity Status | Lag(d) | Delete This Row
P2543-R01-Oct24..4.3.1.3.16.21.1.8 ROW Access RoadCCOPL52384 | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | Non-Sabka ROW/Grading | Trench Excavation | C-52-0304-PL-CI-1800 | C-52-0304-CMA03-1000 | FS | Completed | In Progress | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.4.12.1.10 Excavation (incl Bedding)CCOPL4"106 | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Trench Excavation | ML1219-B59 | C-4N-H5HG-PIPEL-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | P2543-R01-Oct24..4.3.1.5.4.12.1.10 Excavation (incl Bedding)CCOPL4"106 | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Trench Excavation | HE-PL-3570 | C-4N-H5HG-PIPEL-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | P2543-R01-Oct24..4.3.1.3.2.21.1.27 BermingCCOPL52316 | Padding -Lot2 | Gatch Laying & Levelling | C-52-HG01-PL-CI-6200 | C-52-HG01-PL-CI-6800 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | Sabka Gatch Compaction | Bedding | C-52-0304-CMA02-990 | C-52-0304-CMA02-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..ML.GE General | NOC's / Approval /Survey | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (4" Nitrogen Pipeline) | CTF-1010 | ML1159-A08 | FF | Completed | Completed | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..ML.GE General | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (4" Nitrogen Pipeline) | Obtain Final Route Approval from Authorities | ML1159-A08 | ML1011-A05 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.PM.3 Project Procedure (PEP, Numbering Procedure) | P2543-R01-Oct24..ML.GE General | Obtain Company Approval-Project Procedure (PEP, Numbering Procedure etc.) | Issue Construction Execution Plan/ Procedures/ Method Statements along with Procedures & Philosophies-Final Issue | HC-GN-0100 | ML1003-A03 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.11 Pipe Stringing from HGCP to KP 16.7CCOPL52305.1 | P2543-R01-Oct24..4.3.1.3.2.21.1.13 Cold BendsCCOPL52307 | Stringing-Lot1 | Cold Bends-Lot1 | C-52-HG01-PL-ME-2800 | C-52-HG01-PL-ME-3200 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | Trench Excavation-Lot2 | Bedding-Lot2 | C-52-HG01-PL-CI-2600 | C-52-HG01-PL-CI-2610 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.2.21.2.1.4 HydrotestingCCOPL57352 | P2543-R01-Oct24..4.3.1.3.2.21.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57362 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-HG01-CNM04-1600 | C-52-HG01-CNM04-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.1.2 Tunneling & Jack UpCCOPL57332 | P2543-R01-Oct24..4.3.1.3.2.21.2.1.2 Tunneling & Jack UpCCOPL57332 | Filling of Grout between Earth Overcut & RC Sleeve | Inner Grout b/w Main & RC Pipe | C-52-HG01-CNM04-1210 | C-52-HG01-CNM04-1220 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | Survey Marking HGCP to BVS-01 | Excavation (Manual-Trial Pit) | C-52-HG01-PL-CI-1000 | C-52-HG01-CMA07-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.12 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 3&4)CCOPL52303.4 | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | Sabka Gatch Compaction - Layer 4 | Excavation (Manual-Trial Pit) | C-52-HG01-PL-CI-2230 | C-52-HG01-CMA04-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.6 Anchor Block Detailed Drawings | P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | Final Issue for Design/ Construction - Anchor Block Detail Drawings | Earth Works for Equipment Foundations & Hard Stand Area | HE-CS-1800 | C-52-598-04-CI-1010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Earth Works for Equipment Foundations & Hard Stand Area | HE-CS-0470 | C-52-598-04-CI-1010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | Stringing (BVS-02 to BVS-03) | Trench Excavation | C-52-0203-PL-ME-2800 | C-52-0304-CMA02-1000 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.7 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.2 | P2543-R01-Oct24..4.3.1.3.15.21.2.12.1 Entry & Exit Pit ConstructionCCOPL52948 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Trench Excavation | C-52-0102-PL-CI-2200 | C-52-0203-CME04-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.11 Pipe StringingCCOPL52329 | P2543-R01-Oct24..4.3.1.3.8.21.1.12 Cold BendsCCOPL52335 | Stringing (BVS-01 to BVS-02) | Cold Bends | C-52-0102-PL-ME-2800 | C-52-0102-PL-ME-3200 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.6 Sabkha Pad Gatch laying from BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.1 | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | Sabka ROW/Grading | Excavation (Manual-Trial Pit) | C-52-0102-PL-CI-1800 | C-52-0102-CMA04-0970 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..4.3.1.5.4.12.1.8 ROW Access RoadCCOPL4"102 | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Sabka ROW/Grading | HE-PL-2550 | C-4N-H5HG-PIPEL-1800 | FF | In Progress | In Progress | 17
P2543-R01-Oct24..4.3.2.2.2.3.1.3 Dewatering, Swabbing, & DryingCCOPL56235 | P2543-R01-Oct24..4.3.2.2.2.3.1.3 Dewatering, Swabbing, & DryingCCOPL56235 | De-Pressurization | De-watering | C-56-01HG-PL-ME-7600 | C-56-01HG-PL-ME-7610 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | Earth Works for Equipment Foundations & Hard Stand Area | Earth Works for Pipe Support Foundations | C-52-598-03-CI-1010 | C-52-598-03-CI-1020 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.9 Paving WorksCCOB152C40 | P2543-R01-Oct24..4.3.1.3.9.21.1.9 Paving WorksCCOB152C40 | Paving of Interlock tiles & Kerb Stone Embankment | Rip-Rap Protection Laying | C-52-598-06-CI-2600 | C-52-598-06-CI-2610 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.13.21.1.7 Fences & Gates ConstructionCCOB552C38 | P2543-R01-Oct24..4.3.1.3.13.21.1.7 Fences & Gates ConstructionCCOB552C38 | Installation of Concrete Pillers for Boundary Wall | Block Works for Boundary Wall | C-52-598-02-CI-2200 | C-52-598-02-CI-2210 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.17.21.1.23 BackfillingCCOPL52422 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Backfilling | Gatch Laying & Levelling | C-52-0405-PL-CI-6400 | C-52-0405-PL-CI-6800 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.14.21.1.7 Fences & Gates ConstructionCCOB652C39 | P2543-R01-Oct24..4.3.1.3.14.21.1.7 Fences & Gates ConstructionCCOB652C39 | Installation of Concrete Pillers for Boundary Wall | Block Works for Boundary Wall | C-52-598-01-CI-2200 | C-52-598-01-CI-2210 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.1.12.1.15 Paving Works CCOB156C35 | P2543-R01-Oct24..4.3.1.2.1.12.1.15 Paving Works CCOB156C35 | Paving of Interlock tiles & Kerb Stone Embankment | Rip-Rap Protection Laying | C-56-591-01-CI-2600 | C-56-591-01-CI-2610 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.14.21.1.9 Paving WorksCCOB652C42 | P2543-R01-Oct24..4.3.1.3.14.21.1.9 Paving WorksCCOB652C42 | Paving of Interlock tiles & Kerb Stone Embankment | Rip-Rap Protection Laying | C-52-598-01-CI-2600 | C-52-598-01-CI-2610 | FF | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.5.2.3.12.1.10 Backfilling for CablesCCOH5CS108 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.10 Backfilling for CablesCCOH5CS108 | Back Filling for Electrical & Earthing Cable | Back Filling for Instrument & Telecom Cable | C-4N-H5-TPL-CI-2800 | C-4N-H5-TPL-CI-2810 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.10.21.1.7 Fences & Gates ConstructionCCOB252C36 | P2543-R01-Oct24..4.3.1.3.10.21.1.7 Fences & Gates ConstructionCCOB252C36 | Installation of Concrete Pillers for Boundary Wall | Block Works for Boundary Wall | C-52-598-05-CI-2200 | C-52-598-05-CI-2210 | FF | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | Installation of Concrete Pillers for Boundary Wall | Block Works for Boundary Wall | C-52-598-04-CI-2200 | C-52-598-04-CI-2210 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.10.21.1.10 Backfilling for CablesCCOB252C40 | P2543-R01-Oct24..4.3.1.3.10.21.1.10 Backfilling for CablesCCOB252C40 | Back Filling for Electrical & Earthing Cable | Back Filling for Instrument & Telecom Cable | C-52-598-05-CI-2800 | C-52-598-05-CI-2810 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..PR.26.1.23.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.8 UPS (10KVA)CCOSW52E72 | Receipt at site and inspection of LV Switch Gear | UPS (10KVA) Installation | HM-ME-2060 | C-52-EB1-EI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | P2543-R01-Oct24..ML.EN Detail Engineering | Obtain Company Approval- HSEIA Study Report | Complete HSEIA, QRA, and Gas Dispersion Studies after review / approval by Company and Submit Final Reports | HE-HS-0520 | ML1016-B12 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..ML.EN Detail Engineering | Obtain Company Approval-Isolation & Tie-In philosophy | Issue Tie-in Philosophy for all new facilities - IFC | HE-PR-0880 | ML1010-B14 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..ML.EN Detail Engineering | Obtain Company Approval - Pipeline Alignment Sheets-52" | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 52" Pipeline(IFC) | HE-PL-2480 | ML1009-B04 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..ML.EN Detail Engineering | Obtain Company Approval - Pipeline Alignment Sheets -56" | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 56" Pipeline(IFC) | HE-PL-2420 | ML1008-B03 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | P2543-R01-Oct24..ML.EN Detail Engineering | Obtain Company Approval - Overall Pipeline Route Map - 56" | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 56" Pipeline(IFC) | HE-PL-0160 | ML1008-B03 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A111111 TBE for Material Handling Equipment | P2543-R01-Oct24..1.1.2.25.24.1 Ordering | Receive Company Comments- TBE for Material Handling | Commercial Clarifications & Placement of PO for Lifting Equipment | HE-HV-2900 | HP-ME-1370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.26 TBE for Power & Control Cables | P2543-R01-Oct24..4.3.1.7.12.2.1 Electrical & Instrumentation WorksCCOB6E10 | Final Issue for Design/ Construction-TBE for Power & Control Cables | Electrical & Earthing Cable Laying | HE-EL-1550 | C-DBV6-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.26 TBE for Power & Control Cables | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Final Issue for Design/ Construction-TBE for Power & Control Cables | LV Cable Laying | HE-EL-1550 | C-MAQTA-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.26 TBE for Power & Control Cables | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | Final Issue for Design/ Construction-TBE for Power & Control Cables | LV Cable Laying | HE-EL-1550 | C-541CR-EI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.28 TBE for Distribution Boards | P2543-R01-Oct24..1.EN.9.6.26 TBE for Power & Control Cables | Final Issue for Design/ Construction-TBE for Distribution Boards | Final Issue for Design/ Construction-TBE for Power & Control Cables | HE-EL-1430 | HE-EL-1550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.10 TBE for Fire & Gas Detectors | P2543-R01-Oct24..1.EN.6.2.8 TBE for Junction Boxes | Final Issue for Design/ Construction-TBE for Gas Detectors | Final Issue for Design/ Construction-TBE for Junction Boxes | HE-IC-2390 | HE-IC-2510 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.18 Design Calculation for Jib crane Foundation | P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | Final Issue for Design/ Construction-Design Calculation for Jib Crane Foundations | Final Issue for Design/ Construction-Solar panel foundation details | HE-CS-1980 | HE-CS-0890 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.12.3 Structural Design Calculation | P2543-R01-Oct24..1.EN.12.7 Plumbing & Drainage Layout for E&I Building at Sweihan CRS | Final Issue for Design-Structural Design Calculation | Final Issue for Design-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | HE-BL-1040 | HE-BL-1310 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..PR.1.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | Testing and Inspection of Hot Incution Bend | Receipt at site and inspection of Hot Incution Bend (50% Qty) | HM-PL-0580 | HM-PL-0630 | SS | Not Started | Not Started | 23
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | Receipt at site and inspection of Isolator (Lot 1) | Receipt at site and inspection of Isolator (Lot 2) | HM-ME-0690 | HM-ME-2250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Survey Marking BVS-02 to BVS-03 | Sabka ROW/Grading | C-52-0203-PL-CI-1000 | C-52-0203-PL-CI-1800 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Sabka ROW/Grading | Sabka Gatch Laying (Including ROW) - Layer 1 | C-52-0203-PL-CI-1800 | C-52-0203-PL-CI-2000 | SS | Completed | Completed | 21
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | Sabka Gatch Compaction - Layer 4 | Stringing (BVS-02 to BVS-03) | C-52-0203-PL-CI-2230 | C-52-0203-PL-ME-2800 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | P2543-R01-Oct24..4.3.1.3.15.21.1.10 Automatic WeldingCCOPL52364 | Stringing (BVS-02 to BVS-03) | Automatic Welding | C-52-0203-PL-ME-2800 | C-52-0203-PL-ME-3600 | SS | Completed | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.10 Automatic WeldingCCOPL52364 | P2543-R01-Oct24..4.3.1.3.15.21.1.11 NDT TestCCOPL52379 | Automatic Welding | NDT | C-52-0203-PL-ME-3600 | C-52-0203-PL-ME-4000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.11 NDT TestCCOPL52379 | P2543-R01-Oct24..4.3.1.3.15.21.1.12 Ext. Joint CoatingCCOPL52362 | NDT | Ext. Joint Coating | C-52-0203-PL-ME-4000 | C-52-0203-PL-ME-4400 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.7 Excavation (incl Bedding)CCOPL52371 | P2543-R01-Oct24..4.3.1.3.15.21.1.7 Excavation (incl Bedding)CCOPL52371 | Trench Excavation | Bedding | C-52-0203-PL-CI-2400 | C-52-0203-PL-CI-2410 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.15.21.1.7 Excavation (incl Bedding)CCOPL52371 | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Bedding | Lowering | C-52-0203-PL-CI-2410 | C-52-0203-PL-ME-4800 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Lowering | Section Tie-in Welding | C-52-0203-PL-ME-4800 | C-52-0203-PL-ME-4810 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0203-PL-ME-4810 | C-52-0203-PL-ME-4820 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | P2543-R01-Oct24..4.3.1.3.15.21.1.12 Ext. Joint CoatingCCOPL52362 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0203-PL-ME-4820 | C-52-0203-PL-ME-4410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.12 Ext. Joint CoatingCCOPL52362 | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0203-PL-ME-4410 | C-52-0203-PL-ME-4830 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | Holiday Testing | Padding | C-52-0203-PL-ME-4830 | C-52-0203-PL-CI-6000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-0203-PL-CI-2000 | C-52-0203-PL-CI-2200 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Compaction - Layer 2 | C-52-0203-PL-CI-2010 | C-52-0203-PL-CI-2210 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Compaction - Layer 3 | C-52-0203-PL-CI-2020 | C-52-0203-PL-CI-2220 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Sabka Gatch Laying - Layer 4 | Sabka Gatch Compaction - Layer 4 | C-52-0203-PL-CI-2030 | C-52-0203-PL-CI-2230 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.7 Excavation (incl Bedding)CCOPL52371 | Sabka Gatch Compaction - Layer 4 | Trench Excavation | C-52-0203-PL-CI-2230 | C-52-0203-PL-CI-2400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.12 Ext. Joint CoatingCCOPL52362 | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Ext. Joint Coating | Lowering | C-52-0203-PL-ME-4400 | C-52-0203-PL-ME-4800 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0203-CMA01-970 | C-52-0203-CMA01-980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0203-CMA01-980 | C-52-0203-CMA01-990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | Sabka Gatch Compaction | Trench Excavation | C-52-0203-CMA01-990 | C-52-0203-CMA01-1000 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | Trench Excavation | Bedding | C-52-0203-CMA01-1000 | C-52-0203-CMA01-1010 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | Bedding | Lowering | C-52-0203-CMA01-1010 | C-52-0203-CMA01-1020 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | Lowering | Section Tie-in Welding | C-52-0203-CMA01-1020 | C-52-0203-CMA01-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0203-CMA01-1030 | C-52-0203-CMA01-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0203-CMA01-1040 | C-52-0203-CMA01-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0203-CMA01-1050 | C-52-0203-CMA01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | Holiday Testing | Padding | C-52-0203-CMA01-1060 | C-52-0203-CMA01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | Trench Excavation | Bedding | C-52-0203-CMA02-1000 | C-52-0203-CMA02-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | Bedding | Lowering | C-52-0203-CMA02-1010 | C-52-0203-CMA02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | Lowering | Section Tie-in Welding | C-52-0203-CMA02-1020 | C-52-0203-CMA02-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0203-CMA02-1030 | C-52-0203-CMA02-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0203-CMA02-1040 | C-52-0203-CMA02-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0203-CMA02-1050 | C-52-0203-CMA02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | Holiday Testing | Padding & Back Filling | C-52-0203-CMA02-1060 | C-52-0203-CMA02-1070 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | Trench Excavation | Bedding | C-52-0203-CME01-1000 | C-52-0203-CME01-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | Bedding | Lowering | C-52-0203-CME01-1010 | C-52-0203-CME01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | Lowering | Section Tie-in Welding | C-52-0203-CME01-1020 | C-52-0203-CME01-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0203-CME01-1030 | C-52-0203-CME01-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0203-CME01-1040 | C-52-0203-CME01-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0203-CME01-1050 | C-52-0203-CME01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | Holiday Testing | Padding & Back Filling | C-52-0203-CME01-1060 | C-52-0203-CME01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | Trench Excavation | Bedding | C-52-0203-CME02-1000 | C-52-0203-CME02-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | Bedding | Lowering | C-52-0203-CME02-1010 | C-52-0203-CME02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | Lowering | Section Tie-in Welding | C-52-0203-CME02-1020 | C-52-0203-CME02-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0203-CME02-1030 | C-52-0203-CME02-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0203-CME02-1040 | C-52-0203-CME02-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0203-CME02-1050 | C-52-0203-CME02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | Holiday Testing | Padding & Back Filling | C-52-0203-CME02-1060 | C-52-0203-CME02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | Road Diversion & Trench Excavation | Bedding | C-52-0203-CME03-1000 | C-52-0203-CME03-1010 | FS | Completed | Not Started | 35
P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | Bedding | Lowering | C-52-0203-CME03-1010 | C-52-0203-CME03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | Lowering | Section Tie-in Welding | C-52-0203-CME03-1020 | C-52-0203-CME03-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0203-CME03-1030 | C-52-0203-CME03-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0203-CME03-1040 | C-52-0203-CME03-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0203-CME03-1050 | C-52-0203-CME03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | Holiday Testing | Padding & Back Filling | C-52-0203-CME03-1060 | C-52-0203-CME03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.20 Test Stations & Anode BedsCCOP52EL36 | P2543-R01-Oct24..4.3.1.3.15.21.1.17 CP Works TemporaryCCOP52EL38 | Installation of Temp. Anode | Installation of CP Test Post | C-52-0203-PL-CA-5600 | C-52-0203-PL-CA-5200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.17 CP Works TemporaryCCOP52EL38 | P2543-R01-Oct24..4.3.1.3.15.21.1.17 CP Works TemporaryCCOP52EL38 | Installation of CP Test Post | Glanding & Termination of Temp. CP S/m | C-52-0203-PL-CA-5200 | C-52-0203-PL-CA-5210 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | Installation of Test Post for Crossing | Installation of CP JB's | C-52-0203-PL-CA-5220 | C-52-0203-PL-CA-5230 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | Installation of CP JB's | Installation of CP TR | C-52-0203-PL-CA-5230 | C-52-0203-PL-CA-5240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | Installation of CP TR | CIP/DCVG Survey | C-52-0203-PL-CA-5240 | C-52-0203-PL-CA-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | FO - Cable Pulling/ Laying | Termination/Splicing @ BVS | C-52-0203-PL-TE-8200 | C-52-0203-PL-TE-8210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Cleaning & Gauging | Water Filling | C-52-0203-PL-ME-7400 | C-52-0203-PL-ME-7410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Water Filling | Stabilization & Pressurization | C-52-0203-PL-ME-7410 | C-52-0203-PL-ME-7420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Stabilization & Pressurization | Holding of Test Pressure | C-52-0203-PL-ME-7420 | C-52-0203-PL-ME-7430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | P2543-R01-Oct24..4.3.2.3.5.8.2.3 Dewatering, Swabbing, & DryingCCOPL52370 | Holding of Test Pressure | De-Pressurization | C-52-0203-PL-ME-7430 | C-52-0203-PL-ME-7600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2.3 Dewatering, Swabbing, & DryingCCOPL52370 | P2543-R01-Oct24..4.3.2.3.5.8.2.3 Dewatering, Swabbing, & DryingCCOPL52370 | De-Pressurization | De-watering | C-52-0203-PL-ME-7600 | C-52-0203-PL-ME-7610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2.3 Dewatering, Swabbing, & DryingCCOPL52370 | P2543-R01-Oct24..4.3.2.3.5.8.2.3 Dewatering, Swabbing, & DryingCCOPL52370 | De-watering | Swabing & Drying (Upto Dew Point Temp.) | C-52-0203-PL-ME-7610 | C-52-0203-PL-ME-7620 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | Gatch Laying & Levelling | Gatch Compaction | C-52-0203-PL-CI-6800 | C-52-0203-PL-CI-6810 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.15.21.1.5 Marker Post & Crash Barrier | P2543-R01-Oct24..4.3.1.3.15.21.1.5 Marker Post & Crash Barrier | Installation of Marker Post/Sign Board | Installation of Crash Barriers (If any) | C-52-0203-PL-CI-7800 | C-52-0203-PL-CI-7810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | Stringing (BVS-02 to BVS-03) | Lowering | C-52-0203-PL-ME-2800 | C-52-0203-CMA01-1020 | SS | Completed | Not Started | 5
P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | Padding | Gatch Laying & Levelling | C-52-0203-PL-CI-6000 | C-52-0203-PL-CI-6800 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | P2543-R01-Oct24..4.3.1.3.15.21.1.5 Marker Post & Crash Barrier | Gatch Compaction | Installation of Marker Post/Sign Board | C-52-0203-PL-CI-6810 | C-52-0203-PL-CI-7800 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.16.21.1.8 ROW Access RoadCCOPL52384 | Survey Marking BVS-03 to BVS-04 | Non-Sabka ROW/Grading | C-52-0304-PL-CI-1000 | C-52-0304-PL-CI-1800 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.8 ROW Access RoadCCOPL52384 | P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | Non-Sabka ROW/Grading | Sabka Gatch Laying (Including ROW) - Layer 1 | C-52-0304-PL-CI-1800 | C-52-0304-PL-CI-2000 | SS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | Sabka Gatch Compaction - Layer 4 | Stringing (BVS-03 to BVS-04) | C-52-0304-PL-CI-2230 | C-52-0304-PL-ME-2800 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | P2543-R01-Oct24..4.3.1.3.16.21.1.12 Automatic WeldingCCOPL52392 | Stringing (BVS-03 to BVS-04) | Automatic Welding | C-52-0304-PL-ME-2800 | C-52-0304-PL-ME-3600 | SS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.12 Automatic WeldingCCOPL52392 | P2543-R01-Oct24..4.3.1.3.16.21.1.13 NDT TestCCOPL52407 | Automatic Welding | NDT | C-52-0304-PL-ME-3600 | C-52-0304-PL-ME-4000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.13 NDT TestCCOPL52407 | P2543-R01-Oct24..4.3.1.3.16.21.1.14 Ext. Joint CoatingCCOPL52390 | NDT | Ext. Joint Coating | C-52-0304-PL-ME-4000 | C-52-0304-PL-ME-4400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.9 Excavation (incl Bedding)CCOPL52399 | P2543-R01-Oct24..4.3.1.3.16.21.1.9 Excavation (incl Bedding)CCOPL52399 | Trench Excavation | Bedding | C-52-0304-PL-CI-2400 | C-52-0304-PL-CI-2410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.16.21.1.9 Excavation (incl Bedding)CCOPL52399 | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Bedding | Lowering | C-52-0304-PL-CI-2410 | C-52-0304-PL-ME-4800 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Lowering | Section Tie-in Welding | C-52-0304-PL-ME-4800 | C-52-0304-PL-ME-4810 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-PL-ME-4810 | C-52-0304-PL-ME-4820 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | P2543-R01-Oct24..4.3.1.3.16.21.1.14 Ext. Joint CoatingCCOPL52390 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-PL-ME-4820 | C-52-0304-PL-ME-4410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.14 Ext. Joint CoatingCCOPL52390 | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-PL-ME-4410 | C-52-0304-PL-ME-4830 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Holiday Testing | Padding | C-52-0304-PL-ME-4830 | C-52-0304-PL-CI-6000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-0304-PL-CI-2000 | C-52-0304-PL-CI-2200 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Compaction - Layer 2 | C-52-0304-PL-CI-2010 | C-52-0304-PL-CI-2210 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Compaction - Layer 3 | C-52-0304-PL-CI-2020 | C-52-0304-PL-CI-2220 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | Sabka Gatch Laying - Layer 4 | Sabka Gatch Compaction - Layer 4 | C-52-0304-PL-CI-2030 | C-52-0304-PL-CI-2230 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.9 Excavation (incl Bedding)CCOPL52399 | Sabka Gatch Compaction - Layer 4 | Trench Excavation | C-52-0304-PL-CI-2230 | C-52-0304-PL-CI-2400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.14 Ext. Joint CoatingCCOPL52390 | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Ext. Joint Coating | Lowering | C-52-0304-PL-ME-4400 | C-52-0304-PL-ME-4800 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.16.21.1.7 Cut & Fill in Sandy AreaCCOPL52410 | P2543-R01-Oct24..4.3.1.3.16.21.1.9 Excavation (incl Bedding)CCOPL52399 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-52-0304-PL-CI-1400 | C-52-0304-PL-CI-2400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.17.21.1.8 ROW Access RoadCCOPL52412 | Survey Marking BVS-04 to BVS-05 | Non-Sabka ROW/Grading | C-52-0405-PL-CI-1000 | C-52-0405-PL-CI-1800 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..4.3.1.3.17.21.1.10 Pipe StringingCCOPL52413 | Sabka Gatch Compaction - Layer 4 | Stringing (BVS-04 to BVS-05) | C-52-0405-PL-CI-2230 | C-52-0405-PL-ME-2800 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.10 Pipe StringingCCOPL52413 | P2543-R01-Oct24..4.3.1.3.17.21.1.12 Automatic WeldingCCOPL52420 | Stringing (BVS-04 to BVS-05) | Automatic Welding | C-52-0405-PL-ME-2800 | C-52-0405-PL-ME-3600 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.12 Automatic WeldingCCOPL52420 | P2543-R01-Oct24..4.3.1.3.17.21.1.13 NDT TestCCOPL52435 | Automatic Welding | NDT | C-52-0405-PL-ME-3600 | C-52-0405-PL-ME-4000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.13 NDT TestCCOPL52435 | P2543-R01-Oct24..4.3.1.3.17.21.1.19 Ext. Joint CoatingCCOPL52418 | NDT | Ext. Joint Coating | C-52-0405-PL-ME-4000 | C-52-0405-PL-ME-4400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | Trench Excavation | Bedding | C-52-0405-PL-CI-2400 | C-52-0405-PL-CI-2410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Bedding | Lowering | C-52-0405-PL-CI-2410 | C-52-0405-PL-ME-4800 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Lowering | Section Tie-in Welding | C-52-0405-PL-ME-4800 | C-52-0405-PL-ME-4810 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-PL-ME-4810 | C-52-0405-PL-ME-4820 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | P2543-R01-Oct24..4.3.1.3.17.21.1.19 Ext. Joint CoatingCCOPL52418 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-PL-ME-4820 | C-52-0405-PL-ME-4410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.19 Ext. Joint CoatingCCOPL52418 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-PL-ME-4410 | C-52-0405-PL-ME-4830 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Holiday Testing | Padding | C-52-0405-PL-ME-4830 | C-52-0405-PL-CI-6000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-0405-PL-CI-2000 | C-52-0405-PL-CI-2200 | SS | In Progress | In Progress | 5
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Compaction - Layer 2 | C-52-0405-PL-CI-2010 | C-52-0405-PL-CI-2210 | SS | In Progress | In Progress | 5
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Compaction - Layer 3 | C-52-0405-PL-CI-2020 | C-52-0405-PL-CI-2220 | SS | In Progress | In Progress | 5
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | Sabka Gatch Laying - Layer 4 | Sabka Gatch Compaction - Layer 4 | C-52-0405-PL-CI-2030 | C-52-0405-PL-CI-2230 | SS | In Progress | In Progress | 5
P2543-R01-Oct24..4.3.1.3.17.21.1.19 Ext. Joint CoatingCCOPL52418 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Ext. Joint Coating | Lowering | C-52-0405-PL-ME-4400 | C-52-0405-PL-ME-4800 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.17.21.1.7 Cut & Fill in Sandy AreaCCOPL52438 | P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-52-0405-PL-CI-1400 | C-52-0405-PL-CI-2400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.18.21.1.7 ROW Access Road from BVS-05 to KP 126.2CCOPL52440.1 | Survey Marking BVS-05 to BVS-06 | Sabka ROW/Grading | C-52-0506-PL-CI-1000 | C-52-0506-PL-CI-1800 | SS | Completed | Not Started | 7
P2543-R01-Oct24..4.3.1.3.18.21.1.11 Pipe StringingCCOPL52441 | P2543-R01-Oct24..4.3.1.3.18.21.1.13 Automatic WeldingCCOPL52448 | Stringing (BVS-05 to BVS-06) | Automatic Welding | C-52-0506-PL-ME-2800 | C-52-0506-PL-ME-3600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.13 Automatic WeldingCCOPL52448 | P2543-R01-Oct24..4.3.1.3.18.21.1.14 NDT TestCCOPL52463 | Automatic Welding | NDT | C-52-0506-PL-ME-3600 | C-52-0506-PL-ME-4000 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.18.21.1.14 NDT TestCCOPL52463 | P2543-R01-Oct24..4.3.1.3.18.21.1.15 Ext. Joint CoatingCCOPL52446 | NDT | Ext. Joint Coating | C-52-0506-PL-ME-4000 | C-52-0506-PL-ME-4400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.18.21.1.9 Excavation (incl Bedding)CCOPL52455 | P2543-R01-Oct24..4.3.1.3.18.21.1.9 Excavation (incl Bedding)CCOPL52455 | Trench Excavation | Bedding | C-52-0506-PL-CI-2400 | C-52-0506-PL-CI-2410 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.18.21.1.9 Excavation (incl Bedding)CCOPL52455 | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Bedding | Lowering | C-52-0506-PL-CI-2410 | C-52-0506-PL-ME-4800 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Lowering | Section Tie-in Welding | C-52-0506-PL-ME-4800 | C-52-0506-PL-ME-4810 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-PL-ME-4810 | C-52-0506-PL-ME-4820 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | P2543-R01-Oct24..4.3.1.3.18.21.1.15 Ext. Joint CoatingCCOPL52446 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-PL-ME-4820 | C-52-0506-PL-ME-4410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.15 Ext. Joint CoatingCCOPL52446 | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-PL-ME-4410 | C-52-0506-PL-ME-4830 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Holiday Testing | Padding | C-52-0506-PL-ME-4830 | C-52-0506-PL-CI-6000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.18.21.1.15 Ext. Joint CoatingCCOPL52446 | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Ext. Joint Coating | Lowering | C-52-0506-PL-ME-4400 | C-52-0506-PL-ME-4800 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.18.21.1.6 Cut & Fill in Sandy Area from BVS-05 to KP 126.2CCOPL52466.1 | P2543-R01-Oct24..4.3.1.3.18.21.1.9 Excavation (incl Bedding)CCOPL52455 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-52-0506-PL-CI-1400 | C-52-0506-PL-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.7 ROW Access Road from BVS-05 to KP 126.2CCOPL52440.1 | P2543-R01-Oct24..4.3.1.3.18.21.1.6 Cut & Fill in Sandy Area from BVS-05 to KP 126.2CCOPL52466.1 | Sabka ROW/Grading | Cut & Fill (@ Non-Sabkha) | C-52-0506-PL-CI-1800 | C-52-0506-PL-CI-1400 | FS | Not Started | Not Started | 30
P2543-R01-Oct24..4.3.1.3.18.21.1.7 ROW Access Road from BVS-05 to KP 126.2CCOPL52440.1 | P2543-R01-Oct24..4.3.1.3.18.21.1.11 Pipe StringingCCOPL52441 | Sabka ROW/Grading | Stringing (BVS-05 to BVS-06) | C-52-0506-PL-CI-1800 | C-52-0506-PL-ME-2800 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.18.21.1.6 Cut & Fill in Sandy Area from BVS-05 to KP 126.2CCOPL52466.1 | P2543-R01-Oct24..4.3.1.3.18.21.1.11 Pipe StringingCCOPL52441 | Cut & Fill (@ Non-Sabkha) | Stringing (BVS-05 to BVS-06) | C-52-0506-PL-CI-1400 | C-52-0506-PL-ME-2800 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.19.8.1.8 ROW Access RoadCCOPL52468 | Survey Marking BVS-06 to Sweihan CRS | Sabka ROW/Grading | C-52-06CR-PL-CI-1000 | C-52-06CR-PL-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | Sabka Gatch Compaction - Layer 4 | Stringing (BVS-06 to SW CRS) | C-52-06CR-PL-CI-2230 | C-52-06CR-PL-ME-2800 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | P2543-R01-Oct24..4.3.1.3.19.8.1.17 Automatic WeldingCCOPL52476 | Stringing (BVS-06 to SW CRS) | Automatic Welding | C-52-06CR-PL-ME-2800 | C-52-06CR-PL-ME-3600 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.17 Automatic WeldingCCOPL52476 | P2543-R01-Oct24..4.3.1.3.19.8.1.18 NDT TestCCOPL52491 | Automatic Welding | NDT | C-52-06CR-PL-ME-3600 | C-52-06CR-PL-ME-4000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.18 NDT TestCCOPL52491 | P2543-R01-Oct24..4.3.1.3.19.8.1.19 Ext. Joint CoatingCCOPL52474 | NDT | Ext. Joint Coating | C-52-06CR-PL-ME-4000 | C-52-06CR-PL-ME-4400 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.9 Excavation (incl Bedding)CCOPL52483 | P2543-R01-Oct24..4.3.1.3.19.8.1.9 Excavation (incl Bedding)CCOPL52483 | Trench Excavation | Bedding | C-52-06CR-PL-CI-2400 | C-52-06CR-PL-CI-2410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.9 Excavation (incl Bedding)CCOPL52483 | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Bedding | Lowering | C-52-06CR-PL-CI-2410 | C-52-06CR-PL-ME-4800 | FF | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Lowering | Section Tie-in Welding | C-52-06CR-PL-ME-4800 | C-52-06CR-PL-ME-4810 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-PL-ME-4810 | C-52-06CR-PL-ME-4820 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | P2543-R01-Oct24..4.3.1.3.19.8.1.19 Ext. Joint CoatingCCOPL52474 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-PL-ME-4820 | C-52-06CR-PL-ME-4410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.19 Ext. Joint CoatingCCOPL52474 | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-PL-ME-4410 | C-52-06CR-PL-ME-4830 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Holiday Testing | Padding | C-52-06CR-PL-ME-4830 | C-52-06CR-PL-CI-6000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-06CR-PL-CI-2000 | C-52-06CR-PL-CI-2200 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Compaction - Layer 2 | C-52-06CR-PL-CI-2010 | C-52-06CR-PL-CI-2210 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Compaction - Layer 3 | C-52-06CR-PL-CI-2020 | C-52-06CR-PL-CI-2220 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | Sabka Gatch Laying - Layer 4 | Sabka Gatch Compaction - Layer 4 | C-52-06CR-PL-CI-2030 | C-52-06CR-PL-CI-2230 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.9 Excavation (incl Bedding)CCOPL52483 | Sabka Gatch Compaction - Layer 4 | Trench Excavation | C-52-06CR-PL-CI-2230 | C-52-06CR-PL-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.19 Ext. Joint CoatingCCOPL52474 | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Ext. Joint Coating | Lowering | C-52-06CR-PL-ME-4400 | C-52-06CR-PL-ME-4800 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.19.8.1.6 Cut & Fill in Sandy AreaCCOPL52494 | Survey Marking BVS-06 to Sweihan CRS | Cut & Fill (@ Non-Sabkha) | C-52-06CR-PL-CI-1000 | C-52-06CR-PL-CI-1400 | FS | Completed | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.6 Cut & Fill in Sandy AreaCCOPL52494 | P2543-R01-Oct24..4.3.1.3.19.8.1.9 Excavation (incl Bedding)CCOPL52483 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-52-06CR-PL-CI-1400 | C-52-06CR-PL-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.8 ROW Access RoadCCOPL52468 | P2543-R01-Oct24..4.3.1.3.19.8.1.6 Cut & Fill in Sandy AreaCCOPL52494 | Sabka ROW/Grading | Cut & Fill (@ Non-Sabkha) | C-52-06CR-PL-CI-1800 | C-52-06CR-PL-CI-1400 | FS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.2.21.1.6 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 1&2)CCOPL52303.1 | Survey Marking HGCP to BVS-01 | Sabka ROW/Grading | C-52-HG01-PL-CI-1000 | C-52-HG01-PL-CI-1800 | SS | Completed | Completed | 6
P2543-R01-Oct24..4.3.1.3.2.21.1.6 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 1&2)CCOPL52303.1 | P2543-R01-Oct24..4.3.1.3.2.21.1.6 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 1&2)CCOPL52303.1 | Sabka ROW/Grading | Sabka Gatch Laying (Including ROW) - Layer 1 | C-52-HG01-PL-CI-1800 | C-52-HG01-PL-CI-2000 | SS | Completed | Completed | 14
P2543-R01-Oct24..4.3.1.3.2.21.1.12 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 3&4)CCOPL52303.4 | P2543-R01-Oct24..4.3.1.3.2.21.1.11 Pipe Stringing from HGCP to KP 16.7CCOPL52305.1 | Sabka Gatch Compaction - Layer 4 | Stringing-Lot1 | C-52-HG01-PL-CI-2230 | C-52-HG01-PL-ME-2800 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.2.21.1.11 Pipe Stringing from HGCP to KP 16.7CCOPL52305.1 | P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | Stringing-Lot1 | Automatic Welding-Lot1 | C-52-HG01-PL-ME-2800 | C-52-HG01-PL-ME-3600 | SS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | P2543-R01-Oct24..4.3.1.3.2.21.1.16 NDT TestCCOPL52309 | Automatic Welding-Lot1 | NDT-Lot1 | C-52-HG01-PL-ME-3600 | C-52-HG01-PL-ME-4000 | SS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.16 NDT TestCCOPL52309 | P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | NDT-Lot1 | Ext. Joint Coating-Lot1 | C-52-HG01-PL-ME-4000 | C-52-HG01-PL-ME-4400 | SS | Completed | Completed | 2
P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | Trench Excavation-Lot1 | Bedding-Lot1 | C-52-HG01-PL-CI-2400 | C-52-HG01-PL-CI-2410 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Bedding-Lot1 | Lowering-Lot1 | C-52-HG01-PL-CI-2410 | C-52-HG01-PL-ME-4800 | FF | Completed | Completed | 5
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Lowering-Lot1 | Section Tie-in Welding -Lot1 | C-52-HG01-PL-ME-4800 | C-52-HG01-PL-ME-4810 | SS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Section Tie-in Welding -Lot1 | NDT (Tie-in Joint)-Lot1 | C-52-HG01-PL-ME-4810 | C-52-HG01-PL-ME-4820 | SS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | NDT (Tie-in Joint)-Lot1 | Ext. Joint Coating (Tie-in Joint)-Lot1 | C-52-HG01-PL-ME-4820 | C-52-HG01-PL-ME-4410 | SS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Ext. Joint Coating (Tie-in Joint)-Lot1 | Holiday Testing-Lot1 | C-52-HG01-PL-ME-4410 | C-52-HG01-PL-ME-4830 | SS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | Holiday Testing-Lot1 | Padding -Lot1 | C-52-HG01-PL-ME-4830 | C-52-HG01-PL-CI-6000 | SS | Completed | In Progress | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.6 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 1&2)CCOPL52303.1 | P2543-R01-Oct24..4.3.1.3.2.21.1.7 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 1&2) CCOPL52303.2 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-HG01-PL-CI-2000 | C-52-HG01-PL-CI-2200 | SS | Completed | Completed | 20
P2543-R01-Oct24..4.3.1.3.2.21.1.6 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 1&2)CCOPL52303.1 | P2543-R01-Oct24..4.3.1.3.2.21.1.7 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 1&2) CCOPL52303.2 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Compaction - Layer 2 | C-52-HG01-PL-CI-2010 | C-52-HG01-PL-CI-2210 | SS | Completed | Completed | 10
P2543-R01-Oct24..4.3.1.3.2.21.1.9 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 3&4)CCOPL52303.3 | P2543-R01-Oct24..4.3.1.3.2.21.1.12 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 3&4)CCOPL52303.4 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Compaction - Layer 3 | C-52-HG01-PL-CI-2020 | C-52-HG01-PL-CI-2220 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.2.21.1.9 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 3&4)CCOPL52303.3 | P2543-R01-Oct24..4.3.1.3.2.21.1.12 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 3&4)CCOPL52303.4 | Sabka Gatch Laying - Layer 4 | Sabka Gatch Compaction - Layer 4 | C-52-HG01-PL-CI-2030 | C-52-HG01-PL-CI-2230 | SS | Completed | Completed | 10
P2543-R01-Oct24..4.3.1.3.2.21.1.12 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 3&4)CCOPL52303.4 | P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | Sabka Gatch Compaction - Layer 4 | Trench Excavation-Lot1 | C-52-HG01-PL-CI-2230 | C-52-HG01-PL-CI-2400 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Ext. Joint Coating-Lot1 | Lowering-Lot1 | C-52-HG01-PL-ME-4400 | C-52-HG01-PL-ME-4800 | SS | Completed | Completed | 3
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.8.21.1.6 Sabkha Pad Gatch laying from BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.1 | Survey Marking BVS-01 to BVS-02 | Sabka ROW/Grading | C-52-0102-PL-CI-1000 | C-52-0102-PL-CI-1800 | SS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.6 Sabkha Pad Gatch laying from BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.1 | P2543-R01-Oct24..4.3.1.3.8.21.1.6 Sabkha Pad Gatch laying from BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.1 | Sabka ROW/Grading | Sabka Gatch Laying (Including ROW) - Layer 1 | C-52-0102-PL-CI-1800 | C-52-0102-PL-CI-2000 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.8.21.1.10 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.4 | P2543-R01-Oct24..4.3.1.3.8.21.1.11 Pipe StringingCCOPL52329 | Sabka Gatch Compaction - Layer 4 | Stringing (BVS-01 to BVS-02) | C-52-0102-PL-CI-2230 | C-52-0102-PL-ME-2800 | SS | Completed | In Progress | 7
P2543-R01-Oct24..4.3.1.3.8.21.1.11 Pipe StringingCCOPL52329 | P2543-R01-Oct24..4.3.1.3.8.21.1.13 Automatic WeldingCCOPL52336 | Stringing (BVS-01 to BVS-02) | Automatic Welding | C-52-0102-PL-ME-2800 | C-52-0102-PL-ME-3600 | SS | In Progress | In Progress | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.13 Automatic WeldingCCOPL52336 | P2543-R01-Oct24..4.3.1.3.8.21.1.18 NDT TestCCOPL52351 | Automatic Welding | NDT | C-52-0102-PL-ME-3600 | C-52-0102-PL-ME-4000 | SS | In Progress | In Progress | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.18 NDT TestCCOPL52351 | P2543-R01-Oct24..4.3.1.3.8.21.1.17 Ext. Joint CoatingCCOPL52334 | NDT | Ext. Joint Coating | C-52-0102-PL-ME-4000 | C-52-0102-PL-ME-4400 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.8.21.1.8 Excavation (incl Bedding)CCOPL52343 | P2543-R01-Oct24..4.3.1.3.8.21.1.8 Excavation (incl Bedding)CCOPL52343 | Trench Excavation | Bedding | C-52-0102-PL-CI-2400 | C-52-0102-PL-CI-2410 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.8.21.1.8 Excavation (incl Bedding)CCOPL52343 | P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | Bedding | Lowering | C-52-0102-PL-CI-2410 | C-52-0102-PL-ME-4800 | FF | In Progress | Not Started | 2
P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | Lowering | Section Tie-in Welding | C-52-0102-PL-ME-4800 | C-52-0102-PL-ME-4810 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0102-PL-ME-4810 | C-52-0102-PL-ME-4820 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | P2543-R01-Oct24..4.3.1.3.8.21.1.17 Ext. Joint CoatingCCOPL52334 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0102-PL-ME-4820 | C-52-0102-PL-ME-4410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.17 Ext. Joint CoatingCCOPL52334 | P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0102-PL-ME-4410 | C-52-0102-PL-ME-4830 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | P2543-R01-Oct24..4.3.1.3.8.21.1.22 PaddingCCOPL52330 | Holiday Testing | Padding | C-52-0102-PL-ME-4830 | C-52-0102-PL-CI-6000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.6 Sabkha Pad Gatch laying from BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.1 | P2543-R01-Oct24..4.3.1.3.8.21.1.7 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.2 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-0102-PL-CI-2000 | C-52-0102-PL-CI-2200 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.8.21.1.6 Sabkha Pad Gatch laying from BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.1 | P2543-R01-Oct24..4.3.1.3.8.21.1.7 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.2 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Compaction - Layer 2 | C-52-0102-PL-CI-2010 | C-52-0102-PL-CI-2210 | SS | Completed | Completed | 14
P2543-R01-Oct24..4.3.1.3.8.21.1.9 Sabkha Pad Gatch layingfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.3 | P2543-R01-Oct24..4.3.1.3.8.21.1.10 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.4 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Compaction - Layer 3 | C-52-0102-PL-CI-2030 | C-52-0102-PL-CI-2220 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.8.21.1.9 Sabkha Pad Gatch layingfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.3 | P2543-R01-Oct24..4.3.1.3.8.21.1.10 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.4 | Sabka Gatch Laying - Layer 4 | Sabka Gatch Compaction - Layer 4 | C-52-0102-PL-CI-2040 | C-52-0102-PL-CI-2230 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.8.21.1.10 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.4 | P2543-R01-Oct24..4.3.1.3.8.21.1.8 Excavation (incl Bedding)CCOPL52343 | Sabka Gatch Compaction - Layer 4 | Trench Excavation | C-52-0102-PL-CI-2230 | C-52-0102-PL-CI-2400 | FS | Completed | In Progress | 3
P2543-R01-Oct24..4.3.1.3.8.21.1.17 Ext. Joint CoatingCCOPL52334 | P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | Ext. Joint Coating | Lowering | C-52-0102-PL-ME-4400 | C-52-0102-PL-ME-4800 | SS | In Progress | Not Started | 3
P2543-R01-Oct24..4.3.1.3.16.21.1.23 Test Stations & Anode BedsCCOP52EL39 | P2543-R01-Oct24..4.3.1.3.16.21.1.19 CP Works TemporaryCCOP52EL41 | Installation of Temp. Anode | Installation of CP Test Post | C-52-0304-PL-CA-5600 | C-52-0304-PL-CA-5200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.19 CP Works TemporaryCCOP52EL41 | P2543-R01-Oct24..4.3.1.3.16.21.1.19 CP Works TemporaryCCOP52EL41 | Installation of CP Test Post | Glanding & Termination of Temp. CP S/m | C-52-0304-PL-CA-5200 | C-52-0304-PL-CA-5210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Installation of Test Post for Crossing | Installation of CP JB's | C-52-0304-PL-CA-5220 | C-52-0304-PL-CA-5230 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Installation of CP JB's | Installation of CP TR | C-52-0304-PL-CA-5230 | C-52-0304-PL-CA-5240 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Installation of CP TR | CIP/DCVG Survey | C-52-0304-PL-CA-5240 | C-52-0304-PL-CA-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.26 Test Stations & Anode BedsCCOP52EL42 | P2543-R01-Oct24..4.3.1.3.17.21.1.21 CP Works TemporaryCCOP52EL43 | Installation of Temp. Anode | Installation of CP Test Post | C-52-0405-PL-CA-5600 | C-52-0405-PL-CA-5200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.21 CP Works TemporaryCCOP52EL43 | P2543-R01-Oct24..4.3.1.3.17.21.1.21 CP Works TemporaryCCOP52EL43 | Installation of CP Test Post | Glanding & Termination of Temp. CP S/m | C-52-0405-PL-CA-5200 | C-52-0405-PL-CA-5210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Installation of Test Post for Crossing | Installation of CP JB's | C-52-0405-PL-CA-5220 | C-52-0405-PL-CA-5230 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Installation of CP JB's | Installation of CP TR | C-52-0405-PL-CA-5230 | C-52-0405-PL-CA-5240 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Installation of CP TR | CIP/DCVG Survey | C-52-0405-PL-CA-5240 | C-52-0405-PL-CA-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.26 Test Stations & Anode BedsCCOP52EL45 | P2543-R01-Oct24..4.3.1.3.18.21.1.23 CP Works TemporaryCCOP52EL46 | Installation of Temp. Anode | Installation of CP Test Post | C-52-0506-PL-CA-5600 | C-52-0506-PL-CA-5200 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.23 CP Works TemporaryCCOP52EL46 | P2543-R01-Oct24..4.3.1.3.18.21.1.23 CP Works TemporaryCCOP52EL46 | Installation of CP Test Post | Glanding & Termination of Temp. CP S/m | C-52-0506-PL-CA-5200 | C-52-0506-PL-CA-5210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Installation of Test Post for Crossing | Installation of CP JB's | C-52-0506-PL-CA-5220 | C-52-0506-PL-CA-5230 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Installation of CP JB's | Installation of CP TR | C-52-0506-PL-CA-5230 | C-52-0506-PL-CA-5240 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Installation of CP TR | CIP/DCVG Survey | C-52-0506-PL-CA-5240 | C-52-0506-PL-CA-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.26 Test Stations & Anode BedsCCOP52EL48 | P2543-R01-Oct24..4.3.1.3.19.8.1.21 CP Works TemporaryCCOP52EL49 | Installation of Temp. Anode | Installation of CP Test Post | C-52-06CR-PL-CA-5600 | C-52-06CR-PL-CA-5200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.21 CP Works TemporaryCCOP52EL49 | P2543-R01-Oct24..4.3.1.3.19.8.1.21 CP Works TemporaryCCOP52EL49 | Installation of CP Test Post | Glanding & Termination of Temp. CP S/m | C-52-06CR-PL-CA-5200 | C-52-06CR-PL-CA-5210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Installation of Test Post for Crossing | Installation of CP JB's | C-52-06CR-PL-CA-5220 | C-52-06CR-PL-CA-5230 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Installation of CP JB's | Installation of CP TR | C-52-06CR-PL-CA-5230 | C-52-06CR-PL-CA-5240 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Installation of CP TR | CIP/DCVG Survey | C-52-06CR-PL-CA-5240 | C-52-06CR-PL-CA-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.24 Test Stations & Anode BedsCCOP52EL34 | P2543-R01-Oct24..4.3.1.3.8.21.1.21 CP Works TemporaryCCOP52EL35 | Installation of Temp. Anode | Installation of CP Test Post | C-52-0102-PL-CA-5600 | C-52-0102-PL-CA-5200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.21 CP Works TemporaryCCOP52EL35 | P2543-R01-Oct24..4.3.1.3.8.21.1.21 CP Works TemporaryCCOP52EL35 | Installation of CP Test Post | Glanding & Termination of Temp. CP S/m | C-52-0102-PL-CA-5200 | C-52-0102-PL-CA-5210 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Installation of Test Post for Crossing | Installation of CP JB's | C-52-0102-PL-CA-5220 | C-52-0102-PL-CA-5230 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Installation of CP JB's | Installation of CP TR | C-52-0102-PL-CA-5230 | C-52-0102-PL-CA-5240 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Installation of CP TR | CIP/DCVG Survey | C-52-0102-PL-CA-5240 | C-52-0102-PL-CA-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.29 Test Stations & Anode BedsCCOP52EL31 | P2543-R01-Oct24..4.3.1.3.2.21.1.26 CP Works TemporaryCCOP52EL56 | Installation of Temp. Anode | Installation of CP Test Post | C-52-HG01-PL-CA-5600 | C-52-HG01-PL-CA-5200 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.26 CP Works TemporaryCCOP52EL56 | P2543-R01-Oct24..4.3.1.3.2.21.1.26 CP Works TemporaryCCOP52EL56 | Installation of CP Test Post | Glanding & Termination of Temp. CP S/m | C-52-HG01-PL-CA-5200 | C-52-HG01-PL-CA-5210 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Installation of Test Post for Crossing | Installation of CP JB's | C-52-HG01-PL-CA-5220 | C-52-HG01-PL-CA-5230 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Installation of CP JB's | Installation of CP TR | C-52-HG01-PL-CA-5230 | C-52-HG01-PL-CA-5240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Installation of CP TR | CIP/DCVG Survey (Pre-Com) | C-52-HG01-PL-CA-5240 | C-52-HG01-PL-CA-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | FO - Cable Pulling/ Laying | Termination/Splicing @ BVS | C-52-0304-PL-TE-8200 | C-52-0304-PL-TE-8210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | FO - Cable Pulling/ Laying | Termination/Splicing @ BVS | C-52-0405-PL-TE-8200 | C-52-0405-PL-TE-8210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | FO - Cable Pulling/ Laying | Termination/Splicing @ BVS | C-52-0506-PL-TE-8200 | C-52-0506-PL-TE-8210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | FO - Cable Pulling/ Laying | Termination/Splicing @ BVS | C-52-06CR-PL-TE-8200 | C-52-06CR-PL-TE-8210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.5.1 Telecom Works along PipelineCCOP52IC52 | P2543-R01-Oct24..4.3.1.3.8.21.5.1 Telecom Works along PipelineCCOP52IC52 | FO - Cable Pulling/ Laying | Termination/Splicing @ BVS | C-52-0102-PL-TE-8200 | C-52-0102-PL-TE-8210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.4.1 Telecom Works along Pipeline CCOP52IC57 | P2543-R01-Oct24..4.3.1.3.2.21.4.1 Telecom Works along Pipeline CCOP52IC57 | FO - Cable Pulling/ Laying | Termination/Splicing @ BVS | C-52-HG01-PL-TE-8200 | C-52-HG01-PL-TE-8210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Cleaning & Gauging | Water Filling | C-52-0304-PL-ME-7400 | C-52-0304-PL-ME-7410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Water Filling | Stabilization & Pressurization | C-52-0304-PL-ME-7410 | C-52-0304-PL-ME-7420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Stabilization & Pressurization | Holding of Test Pressure | C-52-0304-PL-ME-7420 | C-52-0304-PL-ME-7430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | P2543-R01-Oct24..4.3.2.3.4.8.3.3 Dewatering, Swabbing, & DryingCCOPL52398 | Holding of Test Pressure | De-Pressurization | C-52-0304-PL-ME-7430 | C-52-0304-PL-ME-7600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.3.3 Dewatering, Swabbing, & DryingCCOPL52398 | P2543-R01-Oct24..4.3.2.3.4.8.3.3 Dewatering, Swabbing, & DryingCCOPL52398 | De-Pressurization | De-watering | C-52-0304-PL-ME-7600 | C-52-0304-PL-ME-7610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.3.3 Dewatering, Swabbing, & DryingCCOPL52398 | P2543-R01-Oct24..4.3.2.3.4.8.3.3 Dewatering, Swabbing, & DryingCCOPL52398 | De-watering | Swabing & Drying (Upto Dew Point Temp.) | C-52-0304-PL-ME-7610 | C-52-0304-PL-ME-7620 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Cleaning & Gauging | Water Filling | C-52-0405-PL-ME-7400 | C-52-0405-PL-ME-7410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Water Filling | Stabilization & Pressurization | C-52-0405-PL-ME-7410 | C-52-0405-PL-ME-7420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Stabilization & Pressurization | Holding of Test Pressure | C-52-0405-PL-ME-7420 | C-52-0405-PL-ME-7430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | P2543-R01-Oct24..4.3.2.3.3.8.3.3 Dewatering, Swabbing, & DryingCCOPL52426 | Holding of Test Pressure | De-Pressurization | C-52-0405-PL-ME-7430 | C-52-0405-PL-ME-7600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.3.3 Dewatering, Swabbing, & DryingCCOPL52426 | P2543-R01-Oct24..4.3.2.3.3.8.3.3 Dewatering, Swabbing, & DryingCCOPL52426 | De-Pressurization | De-watering | C-52-0405-PL-ME-7600 | C-52-0405-PL-ME-7610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.3.3 Dewatering, Swabbing, & DryingCCOPL52426 | P2543-R01-Oct24..4.3.2.3.3.8.3.3 Dewatering, Swabbing, & DryingCCOPL52426 | De-watering | Swabing & Drying (Upto Dew Point Temp.) | C-52-0405-PL-ME-7610 | C-52-0405-PL-ME-7620 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Cleaning & Gauging | Water Filling | C-52-0506-PL-ME-7400 | C-52-0506-PL-ME-7410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Water Filling | Stabilization & Pressurization | C-52-0506-PL-ME-7410 | C-52-0506-PL-ME-7420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Stabilization & Pressurization | Holding of Test Pressure | C-52-0506-PL-ME-7420 | C-52-0506-PL-ME-7430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | P2543-R01-Oct24..4.3.2.3.2.8.3.3 Dewatering, Swabbing, & DryingCCOPL52454 | Holding of Test Pressure | De-Pressurization | C-52-0506-PL-ME-7430 | C-52-0506-PL-ME-7600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.3.3 Dewatering, Swabbing, & DryingCCOPL52454 | P2543-R01-Oct24..4.3.2.3.2.8.3.3 Dewatering, Swabbing, & DryingCCOPL52454 | De-Pressurization | De-watering | C-52-0506-PL-ME-7600 | C-52-0506-PL-ME-7610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.3.3 Dewatering, Swabbing, & DryingCCOPL52454 | P2543-R01-Oct24..4.3.2.3.2.8.3.3 Dewatering, Swabbing, & DryingCCOPL52454 | De-watering | Swabing & Drying (Upto Dew Point Temp.) | C-52-0506-PL-ME-7610 | C-52-0506-PL-ME-7620 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Cleaning & Gauging | Water Filling | C-52-06CR-PL-ME-7400 | C-52-06CR-PL-ME-7410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Water Filling | Stabilization & Pressurization | C-52-06CR-PL-ME-7410 | C-52-06CR-PL-ME-7420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Stabilization & Pressurization | Holding of Test Pressure | C-52-06CR-PL-ME-7420 | C-52-06CR-PL-ME-7430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | P2543-R01-Oct24..4.3.2.3.1.8.2.3 Dewatering & DryingCCOPL52482 | Holding of Test Pressure | De-Pressurization | C-52-06CR-PL-ME-7430 | C-52-06CR-PL-ME-7600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.2.3 Dewatering & DryingCCOPL52482 | P2543-R01-Oct24..4.3.2.3.1.8.2.3 Dewatering & DryingCCOPL52482 | De-Pressurization | De-watering | C-52-06CR-PL-ME-7600 | C-52-06CR-PL-ME-7610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.2.3 Dewatering & DryingCCOPL52482 | P2543-R01-Oct24..4.3.2.3.1.8.2.3 Dewatering & DryingCCOPL52482 | De-watering | Swabing & Drying (Upto Dew Point Temp.) | C-52-06CR-PL-ME-7610 | C-52-06CR-PL-ME-7620 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Cleaning & Gauging | Water Filling | C-52-0102-PL-ME-7400 | C-52-0102-PL-ME-7410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Water Filling | Stabilization & Pressurization | C-52-0102-PL-ME-7410 | C-52-0102-PL-ME-7420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Stabilization & Pressurization | Holding of Test Pressure | C-52-0102-PL-ME-7420 | C-52-0102-PL-ME-7430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | P2543-R01-Oct24..4.3.2.3.6.8.1.3 Dewatering, Swabbing, & DryingCCOPL52342 | Holding of Test Pressure | De-Pressurization | C-52-0102-PL-ME-7430 | C-52-0102-PL-ME-7600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.1.3 Dewatering, Swabbing, & DryingCCOPL52342 | P2543-R01-Oct24..4.3.2.3.6.8.1.3 Dewatering, Swabbing, & DryingCCOPL52342 | De-Pressurization | De-watering | C-52-0102-PL-ME-7600 | C-52-0102-PL-ME-7610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.1.3 Dewatering, Swabbing, & DryingCCOPL52342 | P2543-R01-Oct24..4.3.2.3.6.8.1.3 Dewatering, Swabbing, & DryingCCOPL52342 | De-watering | Swabing & Drying (Upto Dew Point Temp.) | C-52-0102-PL-ME-7610 | C-52-0102-PL-ME-7620 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | Water Filling | C-52-HG01-PL-ME-7400 | C-52-HG01-PL-ME-7410 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Water Filling | Stabilization & Pressurization | C-52-HG01-PL-ME-7410 | C-52-HG01-PL-ME-7420 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Stabilization & Pressurization | Holding of Test Pressure | C-52-HG01-PL-ME-7420 | C-52-HG01-PL-ME-7430 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | P2543-R01-Oct24..4.3.2.3.10.8.2.3 Dewatering, Swabbing, & DryingCCOPL52326 | Holding of Test Pressure | De-Pressurization | C-52-HG01-PL-ME-7430 | C-52-HG01-PL-ME-7600 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.2.3.10.8.2.3 Dewatering, Swabbing, & DryingCCOPL52326 | P2543-R01-Oct24..4.3.2.3.10.8.2.3 Dewatering, Swabbing, & DryingCCOPL52326 | De-Pressurization | De-watering | C-52-HG01-PL-ME-7600 | C-52-HG01-PL-ME-7610 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.2.3.10.8.2.3 Dewatering, Swabbing, & DryingCCOPL52326 | P2543-R01-Oct24..4.3.2.3.10.8.2.3 Dewatering, Swabbing, & DryingCCOPL52326 | De-watering | Swabing & Drying (Upto Dew Point Temp.) | C-52-HG01-PL-ME-7610 | C-52-HG01-PL-ME-7620 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Gatch Laying & Levelling | Gatch Compaction | C-52-0304-PL-CI-6800 | C-52-0304-PL-CI-6810 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Gatch Laying & Levelling | Gatch Compaction | C-52-0405-PL-CI-6800 | C-52-0405-PL-CI-6810 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Gatch Laying & Levelling | Gatch Compaction | C-52-0506-PL-CI-6800 | C-52-0506-PL-CI-6810 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Gatch Laying & Levelling | Gatch Compaction | C-52-06CR-PL-CI-6800 | C-52-06CR-PL-CI-6810 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | Gatch Laying & Levelling | Gatch Compaction | C-52-0102-PL-CI-6800 | C-52-0102-PL-CI-6810 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.27 BermingCCOPL52316 | P2543-R01-Oct24..4.3.1.3.2.21.1.27 BermingCCOPL52316 | Gatch Laying & Levelling | Gatch Compaction | C-52-HG01-PL-CI-6800 | C-52-HG01-PL-CI-6810 | SS | In Progress | In Progress | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Installation of Marker Post/Sign Board | Installation of Crash Barriers (If any) | C-52-0304-PL-CI-7800 | C-52-0304-PL-CI-7810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Installation of Marker Post/Sign Board | Installation of Crash Barriers (If any) | C-52-0405-PL-CI-7800 | C-52-0405-PL-CI-7810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Installation of Marker Post/Sign Board | Installation of Crash Barriers (If any) | C-52-0506-PL-CI-7800 | C-52-0506-PL-CI-7810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Installation of Marker Post/Sign Board | Installation of Crash Barriers (If any) | C-52-06CR-PL-CI-7800 | C-52-06CR-PL-CI-7810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | Installation of Marker Post/Sign Board | Installation of Crash Barriers (If any) | C-52-0102-PL-CI-7800 | C-52-0102-PL-CI-7810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.2.3.10.8.2.4 ROW Restoration from BVS-01 to HGCP/Marker PostCCOPL52324.1 | P2543-R01-Oct24..4.3.2.3.10.8.2.5 ROW Restoration from BVS-01 to HGCP/Crash BarrierCCOPL52324.2 | Installation of Marker Post/Sign Board | Installation of Crash Barriers (If any) | C-52-HG01-PL-CI-7800 | C-52-HG01-PL-CI-7810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.10 ROW Access RoadCCOPL56249 | P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | Non-Sabka ROW/Grading | Sabka Gatch Laying (Including ROW) - Layer 1 | C-56-01HG-PL-CI-1800 | C-56-01HG-PL-CI-2000 | SS | Completed | In Progress | 30
P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | P2543-R01-Oct24..4.3.1.2.3.12.1.16 Pipe Stringing from BVS-01 to KP 21.3CCOPL56250.1 | Sabka Gatch Compaction - Layer 4 | Stringing (BVS-01 to KP 21.3) | C-56-01HG-PL-CI-2230 | C-56-01HG-PL-ME-2800 | FF | In Progress | Not Started | 5
P2543-R01-Oct24..4.3.1.2.3.12.1.16 Pipe Stringing from BVS-01 to KP 21.3CCOPL56250.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.20 Automatic Welding from BVS-01 to KP 21.3CCOPL56256.1 | Stringing (BVS-01 to KP 21.3) | Automatic Welding | C-56-01HG-PL-ME-2800 | C-56-01HG-PL-ME-3600 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.20 Automatic Welding from BVS-01 to KP 21.3CCOPL56256.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.13 NDT Test from BVS-01 to KP 21.3CCOPL56245.1 | Automatic Welding | NDT | C-56-01HG-PL-ME-3600 | C-56-01HG-PL-ME-4000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.13 NDT Test from BVS-01 to KP 21.3CCOPL56245.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.25 Ext. Joint Coating from BVS-01 to KP 21.3CCOPL56258.1 | NDT | Ext. Joint Coating | C-56-01HG-PL-ME-4000 | C-56-01HG-PL-ME-4400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.15 Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.15 Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 | Trench Excavation | Bedding | C-56-01HG-PL-CI-2400 | C-56-01HG-PL-CI-2410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.15 Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Bedding | Lowering | C-56-01HG-PL-CI-2410 | C-56-01HG-PL-ME-4800 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Lowering | Section Tie-in Welding | C-56-01HG-PL-ME-4800 | C-56-01HG-PL-ME-4810 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-PL-ME-4810 | C-56-01HG-PL-ME-4820 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.25 Ext. Joint Coating from BVS-01 to KP 21.3CCOPL56258.1 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-PL-ME-4820 | C-56-01HG-PL-ME-4410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.25 Ext. Joint Coating from BVS-01 to KP 21.3CCOPL56258.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-PL-ME-4410 | C-56-01HG-PL-ME-4830 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | Holiday Testing | Padding | C-56-01HG-PL-ME-4830 | C-56-01HG-PL-CI-6000 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-56-01HG-PL-CI-2000 | C-56-01HG-PL-CI-2200 | SS | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Compaction - Layer 2 | C-56-01HG-PL-CI-2010 | C-56-01HG-PL-CI-2210 | SS | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Compaction - Layer 3 | C-56-01HG-PL-CI-2020 | C-56-01HG-PL-CI-2220 | SS | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | Sabka Gatch Laying - Layer 4 | Sabka Gatch Compaction - Layer 4 | C-56-01HG-PL-CI-2030 | C-56-01HG-PL-CI-2230 | SS | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | P2543-R01-Oct24..4.3.1.2.3.12.1.15 Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 | Sabka Gatch Compaction - Layer 4 | Trench Excavation | C-56-01HG-PL-CI-2230 | C-56-01HG-PL-CI-2400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.25 Ext. Joint Coating from BVS-01 to KP 21.3CCOPL56258.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Ext. Joint Coating | Lowering | C-56-01HG-PL-ME-4400 | C-56-01HG-PL-ME-4800 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.10 ROW Access RoadCCOPL56249 | P2543-R01-Oct24..4.3.1.2.3.12.1.15 Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 | Non-Sabka ROW/Grading | Trench Excavation | C-56-01HG-PL-CI-1800 | C-56-01HG-PL-CI-2400 | SS | Completed | Not Started | 5
P2543-R01-Oct24..4.3.1.2.2.12.4.1.7 SurveyingCCOPL56200 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.9 ROW Access RoadCCOPL56203 | Survey Marking | Non-Sabka ROW/Grading | C-56-HC01-PL-CI-1000 | C-56-HC01-PL-CI-1800 | SS | Completed | In Progress | 7
P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.16 Automatic WeldingCCOPL56207 | Stringing (BVS-01 to HBCMPLX) | Automatic Welding | C-56-HC01-PL-ME-2800 | C-56-HC01-PL-ME-3600 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.2.12.4.1.16 Automatic WeldingCCOPL56207 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.17 NDT TestCCOPL56208 | Automatic Welding | NDT | C-56-HC01-PL-ME-3600 | C-56-HC01-PL-ME-4000 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.2.12.4.1.17 NDT TestCCOPL56208 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.18 Ext. Joint Coating from Habshan complex to KP 6CCOPL56210.1 | NDT | Ext. Joint Coating | C-56-HC01-PL-ME-4000 | C-56-HC01-PL-ME-4400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.2.12.4.1.10 Excavation (incl Bedding) from Habshan complex to KP 6CCOPL56206.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.10 Excavation (incl Bedding) from Habshan complex to KP 6CCOPL56206.1 | Trench Excavation | Bedding | C-56-HC01-PL-CI-2400 | C-56-HC01-PL-CI-2410 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.2.12.4.1.10 Excavation (incl Bedding) from Habshan complex to KP 6CCOPL56206.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | Bedding | Lowering | C-56-HC01-PL-CI-2410 | C-56-HC01-PL-ME-4800 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | Lowering | Section Tie-in Welding | C-56-HC01-PL-ME-4800 | C-56-HC01-PL-ME-4810 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-PL-ME-4810 | C-56-HC01-PL-ME-4820 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.18 Ext. Joint Coating from Habshan complex to KP 6CCOPL56210.1 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-PL-ME-4820 | C-56-HC01-PL-ME-4410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.18 Ext. Joint Coating from Habshan complex to KP 6CCOPL56210.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-PL-ME-4410 | C-56-HC01-PL-ME-4830 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.20 Padding from Habshan complex to KP 6CCOPL56211.1 | Holiday Testing | Padding | C-56-HC01-PL-ME-4830 | C-56-HC01-PL-CI-6000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.8 Cut & FillCCOPL56201 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.10 Excavation (incl Bedding) from Habshan complex to KP 6CCOPL56206.1 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-56-HC01-PL-CI-1400 | C-56-HC01-PL-CI-2400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.9 ROW Access RoadCCOPL56203 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.8 Cut & FillCCOPL56201 | Non-Sabka ROW/Grading | Cut & Fill (@ Non-Sabkha) | C-56-HC01-PL-CI-1800 | C-56-HC01-PL-CI-1400 | FF | In Progress | In Progress | 10
P2543-R01-Oct24..4.3.1.2.3.12.1.26 Test Stations & Anode Beds from BVS-01 to KP 21.3CCOP56EL24.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.26 Test Stations & Anode Beds from BVS-01 to KP 21.3CCOP56EL24.1 | Installation of Temp. Anode | Installation of CP Test Post | C-56-01HG-PL-CA-5600 | C-56-01HG-PL-CA-5610 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.26 Test Stations & Anode Beds from BVS-01 to KP 21.3CCOP56EL24.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.26 Test Stations & Anode Beds from BVS-01 to KP 21.3CCOP56EL24.1 | Installation of CP Test Post | Glanding & Termination of Temp. CP S/m | C-56-01HG-PL-CA-5610 | C-56-01HG-PL-CA-5620 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Installation of Test Post for Crossing | Installation of CP JB's | C-56-01HG-PL-CA-5220 | C-56-01HG-PL-CA-5230 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Installation of CP JB's | Installation of CP TR | C-56-01HG-PL-CA-5230 | C-56-01HG-PL-CA-5240 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Installation of CP TR | CIP/DCVG Survey (Pre-Com) | C-56-01HG-PL-CA-5240 | C-56-01HG-PL-CA-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.33 Test Stations & Anode Beds from Habshan complex to KP 6CCOP56EL22.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Installation of Temp. Anode | Installation of CP Test Post | C-56-HC01-PL-CA-5600 | C-56-HC01-PL-CA-5200 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Installation of CP Test Post | Glanding & Termination of Temp. CP S/m | C-56-HC01-PL-CA-5200 | C-56-HC01-PL-CA-5210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Installation of Test Post for Crossing | Installation of CP JB's | C-56-HC01-PL-CA-5220 | C-56-HC01-PL-CA-5230 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Installation of CP JB's | Installation of CP TR | C-56-HC01-PL-CA-5230 | C-56-HC01-PL-CA-5240 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Installation of CP TR | CIP/DCVG Survey | C-56-HC01-PL-CA-5240 | C-56-HC01-PL-CA-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | FO - Cable Pulling/ Laying | Termination/Splicing @ BVS | C-56-01HG-PL-TE-8200 | C-56-01HG-PL-TE-8210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | FO - Cable Pulling/ Laying | Termination/Splicing @ BVS | C-56-HC01-PL-TE-8200 | C-56-HC01-PL-TE-8210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Cleaning & Gauging | Water Filling | C-56-01HG-PL-ME-7400 | C-56-01HG-PL-ME-7410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Water Filling | Stabilization & Pressurization | C-56-01HG-PL-ME-7410 | C-56-01HG-PL-ME-7420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Stabilization & Pressurization | Holding of Test Pressure | C-56-01HG-PL-ME-7420 | C-56-01HG-PL-ME-7430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | P2543-R01-Oct24..4.3.2.2.2.3.1.3 Dewatering, Swabbing, & DryingCCOPL56235 | Holding of Test Pressure | De-Pressurization | C-56-01HG-PL-ME-7430 | C-56-01HG-PL-ME-7600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.3 Dewatering, Swabbing, & DryingCCOPL56235 | P2543-R01-Oct24..4.3.2.2.2.3.1.3 Dewatering, Swabbing, & DryingCCOPL56235 | De-Pressurization | De-watering | C-56-01HG-PL-ME-7600 | C-56-01HG-PL-ME-7610 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.2.2.2.3.1.3 Dewatering, Swabbing, & DryingCCOPL56235 | P2543-R01-Oct24..4.3.2.2.2.3.1.3 Dewatering, Swabbing, & DryingCCOPL56235 | De-watering | Swabing & Drying (Upto Dew Point Temp.) | C-56-01HG-PL-ME-7610 | C-56-01HG-PL-ME-7620 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Cleaning & Gauging | Water Filling | C-56-HC01-PL-ME-7400 | C-56-HC01-PL-ME-7410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Water Filling | Stabilization & Pressurization | C-56-HC01-PL-ME-7410 | C-56-HC01-PL-ME-7420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Stabilization & Pressurization | Holding of Test Pressure | C-56-HC01-PL-ME-7420 | C-56-HC01-PL-ME-7430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | P2543-R01-Oct24..4.3.2.2.2.3.1.7 Dewatering, Swabbing, & DryingCCOPL56227 | Holding of Test Pressure | De-Pressurization | C-56-HC01-PL-ME-7430 | C-56-HC01-PL-ME-7600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.7 Dewatering, Swabbing, & DryingCCOPL56227 | P2543-R01-Oct24..4.3.2.2.2.3.1.7 Dewatering, Swabbing, & DryingCCOPL56227 | De-Pressurization | De-watering | C-56-HC01-PL-ME-7600 | C-56-HC01-PL-ME-7610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.7 Dewatering, Swabbing, & DryingCCOPL56227 | P2543-R01-Oct24..4.3.2.2.2.3.1.7 Dewatering, Swabbing, & DryingCCOPL56227 | De-watering | Swabing & Drying (Upto Dew Point Temp.) | C-56-HC01-PL-ME-7610 | C-56-HC01-PL-ME-7620 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Gatch Laying & Levelling | Gatch Compaction | C-56-01HG-PL-CI-6800 | C-56-01HG-PL-CI-6810 | SS | Not Started | Not Started | 10
P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Gatch Laying & Levelling | Gatch Compaction | C-56-HC01-PL-CI-6800 | C-56-HC01-PL-CI-6810 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.2.2.2.3.1.4 ROW Restoration/Marker Post/Crash BarrierCCOPL56229 | P2543-R01-Oct24..4.3.2.2.2.3.1.4 ROW Restoration/Marker Post/Crash BarrierCCOPL56229 | ROW Restoration/ Installation of Marker Post/Sign Board | Installation of Crash Barriers (If any) | C-56-01HG-PL-CI-7800 | C-56-01HG-PL-CI-7810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Installation of Marker Post/Sign Board | Installation of Crash Barriers (If any) | C-56-HC01-PL-CI-7800 | C-56-HC01-PL-CI-7810 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0102-CMA04-0970 | C-52-0102-CMA04-0980 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0102-CMA04-0980 | C-52-0102-CMA04-0990 | SS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | Sabka Gatch Compaction | Trench Excavation | C-52-0102-CMA04-0990 | C-52-0102-CMA04-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | Trench Excavation | Bedding | C-52-0102-CMA04-1000 | C-52-0102-CMA04-1010 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | Bedding | Lowering | C-52-0102-CMA04-1010 | C-52-0102-CMA04-1020 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | Lowering | Section Tie-in Welding | C-52-0102-CMA04-1020 | C-52-0102-CMA04-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0102-CMA04-1030 | C-52-0102-CMA04-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CMA04-1040 | C-52-0102-CMA04-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0102-CMA04-1050 | C-52-0102-CMA04-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | Holiday Testing | Padding | C-52-0102-CMA04-1060 | C-52-0102-CMA04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0102-CMA05-0970 | C-52-0102-CMA05-0980 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0102-CMA05-0980 | C-52-0102-CMA05-0990 | SS | In Progress | In Progress | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | Sabka Gatch Compaction | Trench Excavation | C-52-0102-CMA05-0990 | C-52-0102-CMA05-1000 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | Trench Excavation | Bedding | C-52-0102-CMA05-1000 | C-52-0102-CMA05-1010 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | Bedding | Lowering | C-52-0102-CMA05-1010 | C-52-0102-CMA05-1020 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | Lowering | Section Tie-in Welding | C-52-0102-CMA05-1020 | C-52-0102-CMA05-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0102-CMA05-1030 | C-52-0102-CMA05-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CMA05-1040 | C-52-0102-CMA05-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0102-CMA05-1050 | C-52-0102-CMA05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | Holiday Testing | Padding | C-52-0102-CMA05-1060 | C-52-0102-CMA05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0102-CMA01-0980 | C-52-0102-CMA01-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | Sabka Gatch Compaction | Trench Excavation | C-52-0102-CMA01-0990 | C-52-0102-CMA01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | Trench Excavation | Bedding | C-52-0102-CMA01-1000 | C-52-0102-CMA01-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | Bedding | Lowering | C-52-0102-CMA01-1010 | C-52-0102-CMA01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | Lowering | Section Tie-in Welding | C-52-0102-CMA01-1020 | C-52-0102-CMA01-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0102-CMA01-1030 | C-52-0102-CMA01-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CMA01-1040 | C-52-0102-CMA01-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0102-CMA01-1050 | C-52-0102-CMA01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | Holiday Testing | Padding | C-52-0102-CMA01-1060 | C-52-0102-CMA01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0102-CMA02-0980 | C-52-0102-CMA02-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | Sabka Gatch Compaction | Trench Excavation | C-52-0102-CMA02-0990 | C-52-0102-CMA02-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | Trench Excavation | Bedding | C-52-0102-CMA02-1000 | C-52-0102-CMA02-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | Bedding | Lowering | C-52-0102-CMA02-1010 | C-52-0102-CMA02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | Lowering | Section Tie-in Welding | C-52-0102-CMA02-1020 | C-52-0102-CMA02-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0102-CMA02-1030 | C-52-0102-CMA02-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CMA02-1040 | C-52-0102-CMA02-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0102-CMA02-1050 | C-52-0102-CMA02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | Holiday Testing | Padding | C-52-0102-CMA02-1060 | C-52-0102-CMA02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0102-CMA03-0980 | C-52-0102-CMA03-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | Sabka Gatch Compaction | Trench Excavation | C-52-0102-CMA03-0990 | C-52-0102-CMA03-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | Trench Excavation | Bedding | C-52-0102-CMA03-1000 | C-52-0102-CMA03-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | Bedding | Lowering | C-52-0102-CMA03-1010 | C-52-0102-CMA03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | Lowering | Section Tie-in Welding | C-52-0102-CMA03-1020 | C-52-0102-CMA03-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0102-CMA03-1030 | C-52-0102-CMA03-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CMA03-1040 | C-52-0102-CMA03-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0102-CMA03-1050 | C-52-0102-CMA03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | Holiday Testing | Padding | C-52-0102-CMA03-1060 | C-52-0102-CMA03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | Trench Excavation | Bedding | C-52-0102-CME01-1000 | C-52-0102-CME01-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | Bedding | Lowering | C-52-0102-CME01-1010 | C-52-0102-CME01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | Lowering | Section Tie-in Welding | C-52-0102-CME01-1020 | C-52-0102-CME01-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0102-CME01-1030 | C-52-0102-CME01-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CME01-1040 | C-52-0102-CME01-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0102-CME01-1050 | C-52-0102-CME01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | Holiday Testing | Padding & Back Filling | C-52-0102-CME01-1060 | C-52-0102-CME01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | Trench Excavation | Bedding | C-52-0102-CME02-1000 | C-52-0102-CME02-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | Bedding | Lowering | C-52-0102-CME02-1010 | C-52-0102-CME02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | Lowering | Section Tie-in Welding | C-52-0102-CME02-1020 | C-52-0102-CME02-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0102-CME02-1030 | C-52-0102-CME02-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CME02-1040 | C-52-0102-CME02-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0102-CME02-1050 | C-52-0102-CME02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | Holiday Testing | Padding & Back Filling | C-52-0102-CME02-1060 | C-52-0102-CME02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | Trench Excavation | Bedding | C-52-0102-CME03-1000 | C-52-0102-CME03-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | Bedding | Lowering | C-52-0102-CME03-1010 | C-52-0102-CME03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | Lowering | Section Tie-in Welding | C-52-0102-CME03-1020 | C-52-0102-CME03-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0102-CME03-1030 | C-52-0102-CME03-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CME03-1040 | C-52-0102-CME03-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0102-CME03-1050 | C-52-0102-CME03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | Holiday Testing | Padding & Back Filling | C-52-0102-CME03-1060 | C-52-0102-CME03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | Trench Excavation | Bedding | C-52-0102-CME04-1000 | C-52-0102-CME04-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | Bedding | Lowering | C-52-0102-CME04-1010 | C-52-0102-CME04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | Lowering | Section Tie-in Welding | C-52-0102-CME04-1020 | C-52-0102-CME04-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0102-CME04-1030 | C-52-0102-CME04-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CME04-1040 | C-52-0102-CME04-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0102-CME04-1050 | C-52-0102-CME04-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | Holiday Testing | Padding & Back Filling | C-52-0102-CME04-1060 | C-52-0102-CME04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | Trench Excavation | Bedding | C-52-0102-CME05-1000 | C-52-0102-CME05-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | Bedding | Lowering | C-52-0102-CME05-1010 | C-52-0102-CME05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | Lowering | Section Tie-in Welding | C-52-0102-CME05-1020 | C-52-0102-CME05-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0102-CME05-1030 | C-52-0102-CME05-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CME05-1040 | C-52-0102-CME05-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0102-CME05-1050 | C-52-0102-CME05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | Holiday Testing | Padding & Back Filling | C-52-0102-CME05-1060 | C-52-0102-CME05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-0102-CNH10-1000 | C-52-0102-CNH10-1020 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0102-CNH10-1010 | C-52-0102-CNH10-1030 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-0102-CNH10-1030 | C-52-0102-CNH10-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0102-CNH10-1040 | C-52-0102-CNH10-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-0102-CNH10-1050 | C-52-0102-CNH10-1060 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 Tunneling & Jack UpCCOPL58202 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-0102-CNH10-1060 | C-52-0102-CNH10-1200 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 Tunneling & Jack UpCCOPL58202 | P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 Tunneling & Jack UpCCOPL58202 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0102-CNH10-1200 | C-52-0102-CNH10-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 Tunneling & Jack UpCCOPL58202 | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-0102-CNH10-1210 | C-52-0102-CNH10-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0102-CNH10-1070 | C-52-0102-CNH10-1080 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0102-CNH10-1080 | C-52-0102-CNH10-1090 | FS | Not Started | Not Started | 10
P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 Tunneling & Jack UpCCOPL58202 | P2543-R01-Oct24..4.3.1.3.8.21.3.1.3 Re-Instatement of Entry & Exit PitCCOPL58212 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0102-CNH10-1220 | C-52-0102-CNH10-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-0102-CNH10-1000 | C-52-0102-CNH10-1010 | SS | Completed | Completed | 21
P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0102-CNH10-1020 | C-52-0102-CNH10-1030 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-0102-CNH09-1000 | C-52-0102-CNH09-1020 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0102-CNH09-1010 | C-52-0102-CNH09-1030 | SS | In Progress | Completed | 7
P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-0102-CNH09-1030 | C-52-0102-CNH09-1040 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0102-CNH09-1040 | C-52-0102-CNH09-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-0102-CNH09-1050 | C-52-0102-CNH09-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | P2543-R01-Oct24..4.3.1.3.8.21.3.2.2 Tunneling & Jack UpCCOPL58262 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-0102-CNH09-1060 | C-52-0102-CNH09-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.2.2 Tunneling & Jack UpCCOPL58262 | P2543-R01-Oct24..4.3.1.3.8.21.3.2.2 Tunneling & Jack UpCCOPL58262 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0102-CNH09-1200 | C-52-0102-CNH09-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.2.2 Tunneling & Jack UpCCOPL58262 | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-0102-CNH09-1210 | C-52-0102-CNH09-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0102-CNH09-1070 | C-52-0102-CNH09-1080 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0102-CNH09-1080 | C-52-0102-CNH09-1090 | FS | Not Started | Not Started | 10
P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | P2543-R01-Oct24..4.3.1.3.8.21.3.2.2 Tunneling & Jack UpCCOPL58262 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-0102-CNH09-1090 | C-52-0102-CNH09-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.2.2 Tunneling & Jack UpCCOPL58262 | P2543-R01-Oct24..4.3.1.3.8.21.3.2.3 Re-Instatement of Entry & Exit PitCCOPL58272 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0102-CNH09-1220 | C-52-0102-CNH09-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-0102-CNH09-1000 | C-52-0102-CNH09-1010 | SS | Completed | In Progress | 21
P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0102-CNH09-1020 | C-52-0102-CNH09-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-0102-CNH08-1000 | C-52-0102-CNH08-1020 | FS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0102-CNH08-1010 | C-52-0102-CNH08-1030 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-0102-CNH08-1030 | C-52-0102-CNH08-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0102-CNH08-1040 | C-52-0102-CNH08-1050 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-0102-CNH08-1050 | C-52-0102-CNH08-1060 | SS | In Progress | Not Started | 3
P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | P2543-R01-Oct24..4.3.1.3.8.21.3.3.2 Tunneling & Jack UpCCOPL58322 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-0102-CNH08-1060 | C-52-0102-CNH08-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.3.2 Tunneling & Jack UpCCOPL58322 | P2543-R01-Oct24..4.3.1.3.8.21.3.3.2 Tunneling & Jack UpCCOPL58322 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0102-CNH08-1200 | C-52-0102-CNH08-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.3.2 Tunneling & Jack UpCCOPL58322 | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-0102-CNH08-1210 | C-52-0102-CNH08-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0102-CNH08-1070 | C-52-0102-CNH08-1080 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0102-CNH08-1080 | C-52-0102-CNH08-1090 | FS | Not Started | Not Started | 10
P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | P2543-R01-Oct24..4.3.1.3.8.21.3.3.2 Tunneling & Jack UpCCOPL58322 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-0102-CNH08-1090 | C-52-0102-CNH08-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.3.2 Tunneling & Jack UpCCOPL58322 | P2543-R01-Oct24..4.3.1.3.8.21.3.3.3 Re-Instatement of Entry & Exit PitCCOPL58332 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0102-CNH08-1220 | C-52-0102-CNH08-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-0102-CNH08-1000 | C-52-0102-CNH08-1010 | SS | Completed | Completed | 23
P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0102-CNH08-1020 | C-52-0102-CNH08-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-0102-CNM07-1000 | C-52-0102-CNM07-1020 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0102-CNM07-1010 | C-52-0102-CNM07-1030 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-0102-CNM07-1030 | C-52-0102-CNM07-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0102-CNM07-1040 | C-52-0102-CNM07-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-0102-CNM07-1050 | C-52-0102-CNM07-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | P2543-R01-Oct24..4.3.1.3.8.21.2.4.2 Tunneling & Jack UpCCOPL52940 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-0102-CNM07-1060 | C-52-0102-CNM07-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.4.2 Tunneling & Jack UpCCOPL52940 | P2543-R01-Oct24..4.3.1.3.8.21.2.4.2 Tunneling & Jack UpCCOPL52940 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0102-CNM07-1200 | C-52-0102-CNM07-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.4.2 Tunneling & Jack UpCCOPL52940 | P2543-R01-Oct24..4.3.1.3.8.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57302 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-0102-CNM07-1210 | C-52-0102-CNM07-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57302 | P2543-R01-Oct24..4.3.1.3.8.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57302 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0102-CNM07-1400 | C-52-0102-CNM07-1410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57302 | P2543-R01-Oct24..4.3.1.3.8.21.2.4.4 HydrotestingCCOPL57312 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0102-CNM07-1410 | C-52-0102-CNM07-1600 | FS | Not Started | Not Started | 10
P2543-R01-Oct24..4.3.1.3.8.21.2.4.4 HydrotestingCCOPL57312 | P2543-R01-Oct24..4.3.1.3.8.21.2.4.2 Tunneling & Jack UpCCOPL52940 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-0102-CNM07-1600 | C-52-0102-CNM07-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.4.2 Tunneling & Jack UpCCOPL52940 | P2543-R01-Oct24..4.3.1.3.8.21.2.4.5 Re-Instatement of Entry & Exit PitCCOPL57322 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0102-CNM07-1220 | C-52-0102-CNM07-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-0102-CNM07-1000 | C-52-0102-CNM07-1010 | SS | In Progress | Not Started | 21
P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0102-CNM07-1020 | C-52-0102-CNM07-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-0102-CNM05-1000 | C-52-0102-CNM05-1020 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0102-CNM05-1010 | C-52-0102-CNM05-1030 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-0102-CNM05-1030 | C-52-0102-CNM05-1040 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0102-CNM05-1040 | C-52-0102-CNM05-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-0102-CNM05-1050 | C-52-0102-CNM05-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | P2543-R01-Oct24..4.3.1.3.8.21.2.6.2 Tunneling & Jack UpCCOPL58002 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-0102-CNM05-1060 | C-52-0102-CNM05-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.6.2 Tunneling & Jack UpCCOPL58002 | P2543-R01-Oct24..4.3.1.3.8.21.2.6.2 Tunneling & Jack UpCCOPL58002 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0102-CNM05-1200 | C-52-0102-CNM05-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.6.2 Tunneling & Jack UpCCOPL58002 | P2543-R01-Oct24..4.3.1.3.8.21.2.6.3 Pipe Lowering, Welding, NDT & CoatingCCOPL58012 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-0102-CNM05-1210 | C-52-0102-CNM05-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.6.3 Pipe Lowering, Welding, NDT & CoatingCCOPL58012 | P2543-R01-Oct24..4.3.1.3.8.21.2.6.3 Pipe Lowering, Welding, NDT & CoatingCCOPL58012 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0102-CNM05-1400 | C-52-0102-CNM05-1410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.2.6.3 Pipe Lowering, Welding, NDT & CoatingCCOPL58012 | P2543-R01-Oct24..4.3.1.3.8.21.2.6.4 HydrotestingCCOPL58022 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0102-CNM05-1410 | C-52-0102-CNM05-1600 | FS | Not Started | Not Started | 10
P2543-R01-Oct24..4.3.1.3.8.21.2.6.4 HydrotestingCCOPL58022 | P2543-R01-Oct24..4.3.1.3.8.21.2.6.2 Tunneling & Jack UpCCOPL58002 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-0102-CNM05-1600 | C-52-0102-CNM05-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.6.2 Tunneling & Jack UpCCOPL58002 | P2543-R01-Oct24..4.3.1.3.8.21.2.6.5 Re-Instatement of Entry & Exit PitCCOPL58032 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0102-CNM05-1220 | C-52-0102-CNM05-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-0102-CNM05-1000 | C-52-0102-CNM05-1010 | SS | Completed | In Progress | 7
P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0102-CNM05-1020 | C-52-0102-CNM05-1030 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-HG01-CMA01-0970 | C-52-HG01-CMA01-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-HG01-CMA01-0980 | C-52-HG01-CMA01-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | Sabka Gatch Compaction | Trench Excavation | C-52-HG01-CMA01-0990 | C-52-HG01-CMA01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | Trench Excavation | Bedding | C-52-HG01-CMA01-1000 | C-52-HG01-CMA01-1010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | Bedding | Lowering | C-52-HG01-CMA01-1010 | C-52-HG01-CMA01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | Lowering | Section Tie-in Welding | C-52-HG01-CMA01-1020 | C-52-HG01-CMA01-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-HG01-CMA01-1030 | C-52-HG01-CMA01-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CMA01-1040 | C-52-HG01-CMA01-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-HG01-CMA01-1050 | C-52-HG01-CMA01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | Holiday Testing | Padding | C-52-HG01-CMA01-1060 | C-52-HG01-CMA01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-HG01-CMA05-0970 | C-52-HG01-CMA05-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-HG01-CMA05-0980 | C-52-HG01-CMA05-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | Sabka Gatch Compaction | Trench Excavation | C-52-HG01-CMA05-0990 | C-52-HG01-CMA05-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | Trench Excavation | Bedding | C-52-HG01-CMA05-1000 | C-52-HG01-CMA05-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | Bedding | Lowering | C-52-HG01-CMA05-1010 | C-52-HG01-CMA05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | Lowering | Section Tie-in Welding | C-52-HG01-CMA05-1020 | C-52-HG01-CMA05-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-HG01-CMA05-1030 | C-52-HG01-CMA05-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CMA05-1040 | C-52-HG01-CMA05-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-HG01-CMA05-1050 | C-52-HG01-CMA05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | Holiday Testing | Padding | C-52-HG01-CMA05-1060 | C-52-HG01-CMA05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-HG01-CMA06-0970 | C-52-HG01-CMA06-0980 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-HG01-CMA06-0980 | C-52-HG01-CMA06-0990 | SS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | Sabka Gatch Compaction | Trench Excavation | C-52-HG01-CMA06-0990 | C-52-HG01-CMA06-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | Trench Excavation | Bedding | C-52-HG01-CMA06-1000 | C-52-HG01-CMA06-1010 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | Bedding | Lowering | C-52-HG01-CMA06-1010 | C-52-HG01-CMA06-1020 | FS | Completed | Not Started | 30
P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-HG01-CMA06-1030 | C-52-HG01-CMA06-1040 | SS | Completed | In Progress | 30
P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CMA06-1040 | C-52-HG01-CMA06-1050 | SS | In Progress | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-HG01-CMA06-1050 | C-52-HG01-CMA06-1060 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | Holiday Testing | Padding | C-52-HG01-CMA06-1060 | C-52-HG01-CMA06-1070 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-HG01-CMA07-0970 | C-52-HG01-CMA07-0980 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-HG01-CMA07-0980 | C-52-HG01-CMA07-0990 | SS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | Sabka Gatch Compaction | Trench Excavation | C-52-HG01-CMA07-0990 | C-52-HG01-CMA07-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | Trench Excavation | Bedding | C-52-HG01-CMA07-1000 | C-52-HG01-CMA07-1010 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | Bedding | Lowering | C-52-HG01-CMA07-1010 | C-52-HG01-CMA07-1020 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | Lowering | Section Tie-in Welding | C-52-HG01-CMA07-1020 | C-52-HG01-CMA07-1030 | SS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-HG01-CMA07-1030 | C-52-HG01-CMA07-1040 | SS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CMA07-1040 | C-52-HG01-CMA07-1050 | SS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-HG01-CMA07-1050 | C-52-HG01-CMA07-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | Holiday Testing | Padding | C-52-HG01-CMA07-1060 | C-52-HG01-CMA07-1070 | FS | Completed | Not Started | 40
P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-HG01-CMA02-0970 | C-52-HG01-CMA02-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-HG01-CMA02-0980 | C-52-HG01-CMA02-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | Sabka Gatch Compaction | Trench Excavation | C-52-HG01-CMA02-0990 | C-52-HG01-CMA02-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | Trench Excavation | Bedding | C-52-HG01-CMA02-1000 | C-52-HG01-CMA02-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | Bedding | Lowering | C-52-HG01-CMA02-1010 | C-52-HG01-CMA02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | Lowering | Section Tie-in Welding | C-52-HG01-CMA02-1020 | C-52-HG01-CMA02-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-HG01-CMA02-1030 | C-52-HG01-CMA02-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CMA02-1040 | C-52-HG01-CMA02-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-HG01-CMA02-1050 | C-52-HG01-CMA02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | Holiday Testing | Padding | C-52-HG01-CMA02-1060 | C-52-HG01-CMA02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-HG01-CMA03-0970 | C-52-HG01-CMA03-0980 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-HG01-CMA03-0980 | C-52-HG01-CMA03-0990 | SS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | Sabka Gatch Compaction | Trench Excavation | C-52-HG01-CMA03-0990 | C-52-HG01-CMA03-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | Trench Excavation | Bedding | C-52-HG01-CMA03-1000 | C-52-HG01-CMA03-1010 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | Bedding | Lowering | C-52-HG01-CMA03-1010 | C-52-HG01-CMA03-1020 | FS | Completed | Not Started | 30
P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-HG01-CMA03-1030 | C-52-HG01-CMA03-1040 | SS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CMA03-1040 | C-52-HG01-CMA03-1050 | SS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-HG01-CMA03-1050 | C-52-HG01-CMA03-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | Holiday Testing | Padding | C-52-HG01-CMA03-1060 | C-52-HG01-CMA03-1070 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-HG01-CMA04-0970 | C-52-HG01-CMA04-0980 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-HG01-CMA04-0980 | C-52-HG01-CMA04-0990 | SS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | Sabka Gatch Compaction | Trench Excavation | C-52-HG01-CMA04-0990 | C-52-HG01-CMA04-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | Trench Excavation | Bedding | C-52-HG01-CMA04-1000 | C-52-HG01-CMA04-1010 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | Bedding | Lowering | C-52-HG01-CMA04-1010 | C-52-HG01-CMA04-1020 | FS | Completed | Not Started | 75
P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-HG01-CMA04-1030 | C-52-HG01-CMA04-1040 | SS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CMA04-1040 | C-52-HG01-CMA04-1050 | SS | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-HG01-CMA04-1050 | C-52-HG01-CMA04-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | Holiday Testing | Padding | C-52-HG01-CMA04-1060 | C-52-HG01-CMA04-1070 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | Trench Excavation | Bedding | C-52-HG01-CME01-1000 | C-52-HG01-CME01-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | Bedding | Lowering | C-52-HG01-CME01-1010 | C-52-HG01-CME01-1020 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | Lowering | Section Tie-in Welding | C-52-HG01-CME01-1020 | C-52-HG01-CME01-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-HG01-CME01-1030 | C-52-HG01-CME01-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CME01-1040 | C-52-HG01-CME01-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-HG01-CME01-1050 | C-52-HG01-CME01-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | Holiday Testing | Padding & Back Filling | C-52-HG01-CME01-1060 | C-52-HG01-CME01-1070 | FS | Completed | Not Started | 30
P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | Trench Excavation | Bedding | C-52-HG01-CME02-1000 | C-52-HG01-CME02-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | Bedding | Lowering | C-52-HG01-CME02-1010 | C-52-HG01-CME02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | Lowering | Section Tie-in Welding | C-52-HG01-CME02-1020 | C-52-HG01-CME02-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-HG01-CME02-1030 | C-52-HG01-CME02-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CME02-1040 | C-52-HG01-CME02-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-HG01-CME02-1050 | C-52-HG01-CME02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | Holiday Testing | Padding & Back Filling | C-52-HG01-CME02-1060 | C-52-HG01-CME02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | Trench Excavation | Bedding | C-52-HG01-CME03-1000 | C-52-HG01-CME03-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | Bedding | Lowering | C-52-HG01-CME03-1010 | C-52-HG01-CME03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | Lowering | Section Tie-in Welding | C-52-HG01-CME03-1020 | C-52-HG01-CME03-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-HG01-CME03-1030 | C-52-HG01-CME03-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-HG01-CME03-1040 | C-52-HG01-CME03-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-HG01-CME03-1050 | C-52-HG01-CME03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | Holiday Testing | Padding & Back Filling | C-52-HG01-CME03-1060 | C-52-HG01-CME03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52936 | P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52936 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-HG01-CNM04-1000 | C-52-HG01-CNM04-1020 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52936 | P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52936 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-HG01-CNM04-1010 | C-52-HG01-CNM04-1030 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52936 | P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52936 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-HG01-CNM04-1030 | C-52-HG01-CNM04-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52936 | P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52936 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-HG01-CNM04-1040 | C-52-HG01-CNM04-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52936 | P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52936 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-HG01-CNM04-1050 | C-52-HG01-CNM04-1060 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52936 | P2543-R01-Oct24..4.3.1.3.2.21.2.1.2 Tunneling & Jack UpCCOPL57332 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-HG01-CNM04-1060 | C-52-HG01-CNM04-1200 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.1.2 Tunneling & Jack UpCCOPL57332 | P2543-R01-Oct24..4.3.1.3.2.21.2.1.2 Tunneling & Jack UpCCOPL57332 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-HG01-CNM04-1200 | C-52-HG01-CNM04-1210 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.1.2 Tunneling & Jack UpCCOPL57332 | P2543-R01-Oct24..4.3.1.3.2.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57342 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-HG01-CNM04-1210 | C-52-HG01-CNM04-1400 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57342 | P2543-R01-Oct24..4.3.1.3.2.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57342 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-HG01-CNM04-1400 | C-52-HG01-CNM04-1410 | SS | In Progress | In Progress | 1
P2543-R01-Oct24..4.3.1.3.2.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57342 | P2543-R01-Oct24..4.3.1.3.2.21.2.1.4 HydrotestingCCOPL57352 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-HG01-CNM04-1410 | C-52-HG01-CNM04-1600 | FS | In Progress | Not Started | 8
P2543-R01-Oct24..4.3.1.3.2.21.2.1.2 Tunneling & Jack UpCCOPL57332 | P2543-R01-Oct24..4.3.1.3.2.21.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57362 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-HG01-CNM04-1220 | C-52-HG01-CNM04-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52936 | P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52936 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-HG01-CNM04-1000 | C-52-HG01-CNM04-1010 | SS | Completed | Completed | 21
P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52936 | P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52936 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-HG01-CNM04-1020 | C-52-HG01-CNM04-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52930 | P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52930 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-HG01-CNM03-1000 | C-52-HG01-CNM03-1020 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52930 | P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52930 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-HG01-CNM03-1010 | C-52-HG01-CNM03-1030 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52930 | P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52930 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-HG01-CNM03-1030 | C-52-HG01-CNM03-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52930 | P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52930 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-HG01-CNM03-1040 | C-52-HG01-CNM03-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52930 | P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52930 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-HG01-CNM03-1050 | C-52-HG01-CNM03-1060 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52930 | P2543-R01-Oct24..4.3.1.3.2.21.2.2.2 Tunneling & Jack UpCCOPL57682 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-HG01-CNM03-1060 | C-52-HG01-CNM03-1200 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.2.2 Tunneling & Jack UpCCOPL57682 | P2543-R01-Oct24..4.3.1.3.2.21.2.2.2 Tunneling & Jack UpCCOPL57682 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-HG01-CNM03-1200 | C-52-HG01-CNM03-1210 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.2.2 Tunneling & Jack UpCCOPL57682 | P2543-R01-Oct24..4.3.1.3.2.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57692 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-HG01-CNM03-1210 | C-52-HG01-CNM03-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57692 | P2543-R01-Oct24..4.3.1.3.2.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57692 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-HG01-CNM03-1400 | C-52-HG01-CNM03-1410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57692 | P2543-R01-Oct24..4.3.1.3.2.21.2.2.4 HydrotestingCCOPL57702 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-HG01-CNM03-1410 | C-52-HG01-CNM03-1600 | FS | Not Started | Not Started | 8
P2543-R01-Oct24..4.3.1.3.2.21.2.2.4 HydrotestingCCOPL57702 | P2543-R01-Oct24..4.3.1.3.2.21.2.2.2 Tunneling & Jack UpCCOPL57682 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-HG01-CNM03-1600 | C-52-HG01-CNM03-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.2.2 Tunneling & Jack UpCCOPL57682 | P2543-R01-Oct24..4.3.1.3.2.21.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57712 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-HG01-CNM03-1220 | C-52-HG01-CNM03-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52930 | P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52930 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-HG01-CNM03-1000 | C-52-HG01-CNM03-1010 | SS | Completed | Completed | 21
P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52930 | P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52930 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-HG01-CNM03-1020 | C-52-HG01-CNM03-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52902 | P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52902 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-HG01-CNM02-1000 | C-52-HG01-CNM02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52902 | P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52902 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-HG01-CNM02-1010 | C-52-HG01-CNM02-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52902 | P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52902 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-HG01-CNM02-1030 | C-52-HG01-CNM02-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52902 | P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52902 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-HG01-CNM02-1040 | C-52-HG01-CNM02-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52902 | P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52902 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-HG01-CNM02-1050 | C-52-HG01-CNM02-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52902 | P2543-R01-Oct24..4.3.1.3.2.21.2.3.2 Tunneling & Jack UpCCOPL58042 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-HG01-CNM02-1060 | C-52-HG01-CNM02-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.3.2 Tunneling & Jack UpCCOPL58042 | P2543-R01-Oct24..4.3.1.3.2.21.2.3.2 Tunneling & Jack UpCCOPL58042 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-HG01-CNM02-1200 | C-52-HG01-CNM02-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.3.2 Tunneling & Jack UpCCOPL58042 | P2543-R01-Oct24..4.3.1.3.2.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL58052 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-HG01-CNM02-1210 | C-52-HG01-CNM02-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL58052 | P2543-R01-Oct24..4.3.1.3.2.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL58052 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-HG01-CNM02-1400 | C-52-HG01-CNM02-1410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL58052 | P2543-R01-Oct24..4.3.1.3.2.21.2.3.4 HydrotestingCCOPL58062 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-HG01-CNM02-1410 | C-52-HG01-CNM02-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.3.4 HydrotestingCCOPL58062 | P2543-R01-Oct24..4.3.1.3.2.21.2.3.2 Tunneling & Jack UpCCOPL58042 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-HG01-CNM02-1600 | C-52-HG01-CNM02-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.3.2 Tunneling & Jack UpCCOPL58042 | P2543-R01-Oct24..4.3.1.3.2.21.2.3.5 Re-Instatement of Entry & Exit PitCCOPL58072 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-HG01-CNM02-1220 | C-52-HG01-CNM02-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52902 | P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52902 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-HG01-CNM02-1020 | C-52-HG01-CNM02-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52900 | P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52900 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-HG01-CNM01-1000 | C-52-HG01-CNM01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52900 | P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52900 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-HG01-CNM01-1010 | C-52-HG01-CNM01-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52900 | P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52900 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-HG01-CNM01-1030 | C-52-HG01-CNM01-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52900 | P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52900 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-HG01-CNM01-1040 | C-52-HG01-CNM01-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52900 | P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52900 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-HG01-CNM01-1050 | C-52-HG01-CNM01-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52900 | P2543-R01-Oct24..4.3.1.3.2.21.2.4.2 Tunneling & Jack UpCCOPL58082 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-HG01-CNM01-1060 | C-52-HG01-CNM01-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.4.2 Tunneling & Jack UpCCOPL58082 | P2543-R01-Oct24..4.3.1.3.2.21.2.4.2 Tunneling & Jack UpCCOPL58082 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-HG01-CNM01-1200 | C-52-HG01-CNM01-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.4.2 Tunneling & Jack UpCCOPL58082 | P2543-R01-Oct24..4.3.1.3.2.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL58092 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-HG01-CNM01-1210 | C-52-HG01-CNM01-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL58092 | P2543-R01-Oct24..4.3.1.3.2.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL58092 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-HG01-CNM01-1400 | C-52-HG01-CNM01-1410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL58092 | P2543-R01-Oct24..4.3.1.3.2.21.2.4.4 HydrotestingCCOPL58102 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-HG01-CNM01-1410 | C-52-HG01-CNM01-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.4.4 HydrotestingCCOPL58102 | P2543-R01-Oct24..4.3.1.3.2.21.2.4.2 Tunneling & Jack UpCCOPL58082 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-HG01-CNM01-1600 | C-52-HG01-CNM01-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.4.2 Tunneling & Jack UpCCOPL58082 | P2543-R01-Oct24..4.3.1.3.2.21.2.4.5 Re-Instatement of Entry & Exit PitCCOPL58112 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-HG01-CNM01-1220 | C-52-HG01-CNM01-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52900 | P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52900 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-HG01-CNM01-1000 | C-52-HG01-CNM01-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52900 | P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52900 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-HG01-CNM01-1020 | C-52-HG01-CNM01-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0304-CMA04-0970 | C-52-0304-CMA04-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0304-CMA04-0980 | C-52-0304-CMA04-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | Sabka Gatch Compaction | Trench Excavation | C-52-0304-CMA04-0990 | C-52-0304-CMA04-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | Trench Excavation | Bedding | C-52-0304-CMA04-1000 | C-52-0304-CMA04-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | Bedding | Lowering | C-52-0304-CMA04-1010 | C-52-0304-CMA04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | Lowering | Section Tie-in Welding | C-52-0304-CMA04-1020 | C-52-0304-CMA04-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CMA04-1030 | C-52-0304-CMA04-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA04-1040 | C-52-0304-CMA04-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CMA04-1050 | C-52-0304-CMA04-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | Holiday Testing | Padding | C-52-0304-CMA04-1060 | C-52-0304-CMA04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0304-CMA05-0970 | C-52-0304-CMA05-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0304-CMA05-0980 | C-52-0304-CMA05-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | Sabka Gatch Compaction | Trench Excavation | C-52-0304-CMA05-0990 | C-52-0304-CMA05-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | Trench Excavation | Bedding | C-52-0304-CMA05-1000 | C-52-0304-CMA05-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | Bedding | Lowering | C-52-0304-CMA05-1010 | C-52-0304-CMA05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | Lowering | Section Tie-in Welding | C-52-0304-CMA05-1020 | C-52-0304-CMA05-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CMA05-1030 | C-52-0304-CMA05-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA05-1040 | C-52-0304-CMA05-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CMA05-1050 | C-52-0304-CMA05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | Holiday Testing | Padding | C-52-0304-CMA05-1060 | C-52-0304-CMA05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0304-CMA01-0980 | C-52-0304-CMA01-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | Sabka Gatch Compaction | Trench Excavation | C-52-0304-CMA01-0990 | C-52-0304-CMA01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | Trench Excavation | Bedding | C-52-0304-CMA01-1000 | C-52-0304-CMA01-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | Bedding | Lowering | C-52-0304-CMA01-1010 | C-52-0304-CMA01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | Lowering | Section Tie-in Welding | C-52-0304-CMA01-1020 | C-52-0304-CMA01-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CMA01-1030 | C-52-0304-CMA01-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA01-1040 | C-52-0304-CMA01-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CMA01-1050 | C-52-0304-CMA01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | Holiday Testing | Padding | C-52-0304-CMA01-1060 | C-52-0304-CMA01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0304-CMA07-0970 | C-52-0304-CMA07-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0304-CMA07-0980 | C-52-0304-CMA07-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | Sabka Gatch Compaction | Trench Excavation | C-52-0304-CMA07-0990 | C-52-0304-CMA07-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | Trench Excavation | Bedding | C-52-0304-CMA07-1000 | C-52-0304-CMA07-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | Bedding | Lowering | C-52-0304-CMA07-1010 | C-52-0304-CMA07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | Lowering | Section Tie-in Welding | C-52-0304-CMA07-1020 | C-52-0304-CMA07-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CMA07-1030 | C-52-0304-CMA07-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA07-1040 | C-52-0304-CMA07-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CMA07-1050 | C-52-0304-CMA07-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | Holiday Testing | Padding | C-52-0304-CMA07-1060 | C-52-0304-CMA07-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0304-CMA02-980 | C-52-0304-CMA02-990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | Trench Excavation | Bedding | C-52-0304-CMA02-1000 | C-52-0304-CMA02-1010 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | Bedding | Lowering | C-52-0304-CMA02-1010 | C-52-0304-CMA02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | Lowering | Section Tie-in Welding | C-52-0304-CMA02-1020 | C-52-0304-CMA02-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CMA02-1030 | C-52-0304-CMA02-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA02-1040 | C-52-0304-CMA02-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CMA02-1050 | C-52-0304-CMA02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | Holiday Testing | Padding | C-52-0304-CMA02-1060 | C-52-0304-CMA02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0304-CMA14-0970 | C-52-0304-CMA14-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0304-CMA14-0980 | C-52-0304-CMA14-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | Sabka Gatch Compaction | Trench Excavation | C-52-0304-CMA14-0990 | C-52-0304-CMA14-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | Trench Excavation | Bedding | C-52-0304-CMA14-1000 | C-52-0304-CMA14-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | Bedding | Lowering | C-52-0304-CMA14-1010 | C-52-0304-CMA14-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | Lowering | Section Tie-in Welding | C-52-0304-CMA14-1020 | C-52-0304-CMA14-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CMA14-1030 | C-52-0304-CMA14-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA14-1040 | C-52-0304-CMA14-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CMA14-1050 | C-52-0304-CMA14-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | Holiday Testing | Padding | C-52-0304-CMA14-1060 | C-52-0304-CMA14-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0304-CMA09-0970 | C-52-0304-CMA09-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0304-CMA09-0980 | C-52-0304-CMA09-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | Sabka Gatch Compaction | Trench Excavation | C-52-0304-CMA09-0990 | C-52-0304-CMA09-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | Trench Excavation | Bedding | C-52-0304-CMA09-1000 | C-52-0304-CMA09-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | Bedding | Lowering | C-52-0304-CMA09-1010 | C-52-0304-CMA09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | Lowering | Section Tie-in Welding | C-52-0304-CMA09-1020 | C-52-0304-CMA09-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CMA09-1030 | C-52-0304-CMA09-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA09-1040 | C-52-0304-CMA09-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CMA09-1050 | C-52-0304-CMA09-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | Holiday Testing | Padding | C-52-0304-CMA09-1060 | C-52-0304-CMA09-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0304-CMA06-0970 | C-52-0304-CMA06-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0304-CMA06-0980 | C-52-0304-CMA06-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | Sabka Gatch Compaction | Trench Excavation | C-52-0304-CMA06-0990 | C-52-0304-CMA06-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | Trench Excavation | Bedding | C-52-0304-CMA06-1000 | C-52-0304-CMA06-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | Bedding | Lowering | C-52-0304-CMA06-1010 | C-52-0304-CMA06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | Lowering | Section Tie-in Welding | C-52-0304-CMA06-1020 | C-52-0304-CMA06-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CMA06-1030 | C-52-0304-CMA06-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA06-1040 | C-52-0304-CMA06-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CMA06-1050 | C-52-0304-CMA06-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | Holiday Testing | Padding | C-52-0304-CMA06-1060 | C-52-0304-CMA06-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | Trench Excavation | Bedding | C-52-0304-CMA11-1000 | C-52-0304-CMA11-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | Bedding | Lowering | C-52-0304-CMA11-1010 | C-52-0304-CMA11-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | Lowering | Section Tie-in Welding | C-52-0304-CMA11-1020 | C-52-0304-CMA11-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CMA11-1030 | C-52-0304-CMA11-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA11-1040 | C-52-0304-CMA11-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CMA11-1050 | C-52-0304-CMA11-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | Holiday Testing | Padding | C-52-0304-CMA11-1060 | C-52-0304-CMA11-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | Trench Excavation | Bedding | C-52-0304-CMA12-1000 | C-52-0304-CMA12-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | Bedding | Lowering | C-52-0304-CMA12-1010 | C-52-0304-CMA12-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | Lowering | Section Tie-in Welding | C-52-0304-CMA12-1020 | C-52-0304-CMA12-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CMA12-1030 | C-52-0304-CMA12-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA12-1040 | C-52-0304-CMA12-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CMA12-1050 | C-52-0304-CMA12-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | Holiday Testing | Padding | C-52-0304-CMA12-1060 | C-52-0304-CMA12-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | Trench Excavation | Bedding | C-52-0304-CMA13-1000 | C-52-0304-CMA13-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | Bedding | Lowering | C-52-0304-CMA13-1010 | C-52-0304-CMA13-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | Lowering | Section Tie-in Welding | C-52-0304-CMA13-1020 | C-52-0304-CMA13-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CMA13-1030 | C-52-0304-CMA13-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA13-1040 | C-52-0304-CMA13-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CMA13-1050 | C-52-0304-CMA13-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | Holiday Testing | Padding | C-52-0304-CMA13-1060 | C-52-0304-CMA13-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | Trench Excavation | Bedding | C-52-0304-CMA03-1000 | C-52-0304-CMA03-1010 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | Bedding | Lowering | C-52-0304-CMA03-1010 | C-52-0304-CMA03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | Lowering | Section Tie-in Welding | C-52-0304-CMA03-1020 | C-52-0304-CMA03-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CMA03-1030 | C-52-0304-CMA03-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA03-1040 | C-52-0304-CMA03-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CMA03-1050 | C-52-0304-CMA03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | Holiday Testing | Padding | C-52-0304-CMA03-1060 | C-52-0304-CMA03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | Trench Excavation | Bedding | C-52-0304-CMA08-1000 | C-52-0304-CMA08-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | Bedding | Lowering | C-52-0304-CMA08-1010 | C-52-0304-CMA08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | Lowering | Section Tie-in Welding | C-52-0304-CMA08-1020 | C-52-0304-CMA08-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CMA08-1030 | C-52-0304-CMA08-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA08-1040 | C-52-0304-CMA08-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CMA08-1050 | C-52-0304-CMA08-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | Holiday Testing | Padding | C-52-0304-CMA08-1060 | C-52-0304-CMA08-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | Trench Excavation | Bedding | C-52-0304-CMA10-1000 | C-52-0304-CMA10-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | Bedding | Lowering | C-52-0304-CMA10-1010 | C-52-0304-CMA10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | Lowering | Section Tie-in Welding | C-52-0304-CMA10-1020 | C-52-0304-CMA10-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CMA10-1030 | C-52-0304-CMA10-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CMA10-1040 | C-52-0304-CMA10-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CMA10-1050 | C-52-0304-CMA10-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | Holiday Testing | Padding | C-52-0304-CMA10-1060 | C-52-0304-CMA10-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | Trench Excavation | Bedding | C-52-0304-CME01-1000 | C-52-0304-CME01-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | Bedding | Lowering | C-52-0304-CME01-1010 | C-52-0304-CME01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | Lowering | Section Tie-in Welding | C-52-0304-CME01-1020 | C-52-0304-CME01-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CME01-1030 | C-52-0304-CME01-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME01-1040 | C-52-0304-CME01-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CME01-1050 | C-52-0304-CME01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | Holiday Testing | Padding & Back Filling | C-52-0304-CME01-1060 | C-52-0304-CME01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | Trench Excavation | Bedding | C-52-0304-CME02-1000 | C-52-0304-CME02-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | Bedding | Lowering | C-52-0304-CME02-1010 | C-52-0304-CME02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | Lowering | Section Tie-in Welding | C-52-0304-CME02-1020 | C-52-0304-CME02-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CME02-1030 | C-52-0304-CME02-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME02-1040 | C-52-0304-CME02-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CME02-1050 | C-52-0304-CME02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | Holiday Testing | Padding & Back Filling | C-52-0304-CME02-1060 | C-52-0304-CME02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | Trench Excavation | Bedding | C-52-0304-CME03-1000 | C-52-0304-CME03-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | Bedding | Lowering | C-52-0304-CME03-1010 | C-52-0304-CME03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | Lowering | Section Tie-in Welding | C-52-0304-CME03-1020 | C-52-0304-CME03-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CME03-1030 | C-52-0304-CME03-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME03-1040 | C-52-0304-CME03-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CME03-1050 | C-52-0304-CME03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | Holiday Testing | Padding & Back Filling | C-52-0304-CME03-1060 | C-52-0304-CME03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | Trench Excavation | Bedding | C-52-0304-CME04-1000 | C-52-0304-CME04-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | Bedding | Lowering | C-52-0304-CME04-1010 | C-52-0304-CME04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | Lowering | Section Tie-in Welding | C-52-0304-CME04-1020 | C-52-0304-CME04-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CME04-1030 | C-52-0304-CME04-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME04-1040 | C-52-0304-CME04-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CME04-1050 | C-52-0304-CME04-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | Holiday Testing | Padding & Back Filling | C-52-0304-CME04-1060 | C-52-0304-CME04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | Trench Excavation | Bedding | C-52-0304-CME05-1000 | C-52-0304-CME05-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | Bedding | Lowering | C-52-0304-CME05-1010 | C-52-0304-CME05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | Lowering | Section Tie-in Welding | C-52-0304-CME05-1020 | C-52-0304-CME05-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CME05-1030 | C-52-0304-CME05-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME05-1040 | C-52-0304-CME05-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CME05-1050 | C-52-0304-CME05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | Holiday Testing | Padding & Back Filling | C-52-0304-CME05-1060 | C-52-0304-CME05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | Trench Excavation | Bedding | C-52-0304-CME06-1000 | C-52-0304-CME06-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | Bedding | Lowering | C-52-0304-CME06-1010 | C-52-0304-CME06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | Lowering | Section Tie-in Welding | C-52-0304-CME06-1020 | C-52-0304-CME06-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CME06-1030 | C-52-0304-CME06-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME06-1040 | C-52-0304-CME06-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CME06-1050 | C-52-0304-CME06-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | Holiday Testing | Padding & Back Filling | C-52-0304-CME06-1060 | C-52-0304-CME06-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | Trench Excavation | Bedding | C-52-0304-CME07-1000 | C-52-0304-CME07-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | Bedding | Lowering | C-52-0304-CME07-1010 | C-52-0304-CME07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | Lowering | Section Tie-in Welding | C-52-0304-CME07-1020 | C-52-0304-CME07-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CME07-1030 | C-52-0304-CME07-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME07-1040 | C-52-0304-CME07-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CME07-1050 | C-52-0304-CME07-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | Holiday Testing | Padding & Back Filling | C-52-0304-CME07-1060 | C-52-0304-CME07-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | Trench Excavation | Bedding | C-52-0304-CME08-1000 | C-52-0304-CME08-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | Bedding | Lowering | C-52-0304-CME08-1010 | C-52-0304-CME08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | Lowering | Section Tie-in Welding | C-52-0304-CME08-1020 | C-52-0304-CME08-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CME08-1030 | C-52-0304-CME08-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME08-1040 | C-52-0304-CME08-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CME08-1050 | C-52-0304-CME08-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | Holiday Testing | Padding & Back Filling | C-52-0304-CME08-1060 | C-52-0304-CME08-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | Trench Excavation | Bedding | C-52-0304-CME09-1000 | C-52-0304-CME09-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | Bedding | Lowering | C-52-0304-CME09-1010 | C-52-0304-CME09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | Lowering | Section Tie-in Welding | C-52-0304-CME09-1020 | C-52-0304-CME09-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CME09-1030 | C-52-0304-CME09-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME09-1040 | C-52-0304-CME09-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CME09-1050 | C-52-0304-CME09-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | Holiday Testing | Padding & Back Filling | C-52-0304-CME09-1060 | C-52-0304-CME09-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | Trench Excavation | Bedding | C-52-0304-CME11-1000 | C-52-0304-CME11-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | Bedding | Lowering | C-52-0304-CME11-1010 | C-52-0304-CME11-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | Lowering | Section Tie-in Welding | C-52-0304-CME11-1020 | C-52-0304-CME11-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CME11-1030 | C-52-0304-CME11-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME11-1040 | C-52-0304-CME11-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CME11-1050 | C-52-0304-CME11-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | Holiday Testing | Padding & Back Filling | C-52-0304-CME11-1060 | C-52-0304-CME11-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | Trench Excavation | Bedding | C-52-0304-CME12-1000 | C-52-0304-CME12-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | Bedding | Lowering | C-52-0304-CME12-1010 | C-52-0304-CME12-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | Lowering | Section Tie-in Welding | C-52-0304-CME12-1020 | C-52-0304-CME12-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CME12-1030 | C-52-0304-CME12-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME12-1040 | C-52-0304-CME12-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CME12-1050 | C-52-0304-CME12-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | Holiday Testing | Padding & Back Filling | C-52-0304-CME12-1060 | C-52-0304-CME12-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | Road Diversion & Trench Excavation | Bedding | C-52-0304-CME10-1000 | C-52-0304-CME10-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | Bedding | Lowering | C-52-0304-CME10-1010 | C-52-0304-CME10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | Lowering | Section Tie-in Welding | C-52-0304-CME10-1020 | C-52-0304-CME10-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CME10-1030 | C-52-0304-CME10-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME10-1040 | C-52-0304-CME10-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CME10-1050 | C-52-0304-CME10-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | Holiday Testing | Padding & Back Filling | C-52-0304-CME10-1060 | C-52-0304-CME10-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | Trench Excavation | Bedding | C-52-0405-CMA01-1000 | C-52-0405-CMA01-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | Bedding | Lowering | C-52-0405-CMA01-1010 | C-52-0405-CMA01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | Lowering | Section Tie-in Welding | C-52-0405-CMA01-1020 | C-52-0405-CMA01-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA01-1030 | C-52-0405-CMA01-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA01-1040 | C-52-0405-CMA01-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA01-1050 | C-52-0405-CMA01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | Holiday Testing | Padding | C-52-0405-CMA01-1060 | C-52-0405-CMA01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | Trench Excavation | Bedding | C-52-0405-CMA25-1000 | C-52-0405-CMA25-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | Bedding | Lowering | C-52-0405-CMA25-1010 | C-52-0405-CMA25-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | Lowering | Section Tie-in Welding | C-52-0405-CMA25-1020 | C-52-0405-CMA25-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA25-1030 | C-52-0405-CMA25-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA25-1040 | C-52-0405-CMA25-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA25-1050 | C-52-0405-CMA25-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | Holiday Testing | Padding | C-52-0405-CMA25-1060 | C-52-0405-CMA25-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | Trench Excavation | Bedding | C-52-0405-CMA20-1000 | C-52-0405-CMA20-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | Bedding | Lowering | C-52-0405-CMA20-1010 | C-52-0405-CMA20-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | Lowering | Section Tie-in Welding | C-52-0405-CMA20-1020 | C-52-0405-CMA20-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA20-1030 | C-52-0405-CMA20-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA20-1040 | C-52-0405-CMA20-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA20-1050 | C-52-0405-CMA20-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | Holiday Testing | Padding | C-52-0405-CMA20-1060 | C-52-0405-CMA20-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | Trench Excavation | Bedding | C-52-0405-CMA26-1000 | C-52-0405-CMA26-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | Bedding | Lowering | C-52-0405-CMA26-1010 | C-52-0405-CMA26-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | Lowering | Section Tie-in Welding | C-52-0405-CMA26-1020 | C-52-0405-CMA26-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA26-1030 | C-52-0405-CMA26-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA26-1040 | C-52-0405-CMA26-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA26-1050 | C-52-0405-CMA26-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | Holiday Testing | Padding | C-52-0405-CMA26-1060 | C-52-0405-CMA26-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | Trench Excavation | Bedding | C-52-0405-CMA21-1000 | C-52-0405-CMA21-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | Bedding | Lowering | C-52-0405-CMA21-1010 | C-52-0405-CMA21-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | Lowering | Section Tie-in Welding | C-52-0405-CMA21-1020 | C-52-0405-CMA21-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA21-1030 | C-52-0405-CMA21-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA21-1040 | C-52-0405-CMA21-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA21-1050 | C-52-0405-CMA21-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | Holiday Testing | Padding | C-52-0405-CMA21-1060 | C-52-0405-CMA21-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | Trench Excavation | Bedding | C-52-0405-CMA27-1000 | C-52-0405-CMA27-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | Bedding | Lowering | C-52-0405-CMA27-1010 | C-52-0405-CMA27-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | Lowering | Section Tie-in Welding | C-52-0405-CMA27-1020 | C-52-0405-CMA27-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA27-1030 | C-52-0405-CMA27-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA27-1040 | C-52-0405-CMA27-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA27-1050 | C-52-0405-CMA27-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | Holiday Testing | Padding | C-52-0405-CMA27-1060 | C-52-0405-CMA27-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0405-CMA22-1000 | C-52-0405-CMA22-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0405-CMA22-1010 | C-52-0405-CMA22-1020 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | Sabka Gatch Compaction | Trench Excavation | C-52-0405-CMA22-1020 | C-52-0405-CMA22-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | Trench Excavation | Bedding | C-52-0405-CMA22-1030 | C-52-0405-CMA22-1040 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | Bedding | Lowering | C-52-0405-CMA22-1040 | C-52-0405-CMA22-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | Lowering | Section Tie-in Welding | C-52-0405-CMA22-1050 | C-52-0405-CMA22-1060 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA22-1060 | C-52-0405-CMA22-1070 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA22-1070 | C-52-0405-CMA22-1080 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA22-1080 | C-52-0405-CMA22-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | Holiday Testing | Padding | C-52-0405-CMA22-1090 | C-52-0405-CMA22-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0405-CMA02-0970 | C-52-0405-CMA02-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0405-CMA02-0980 | C-52-0405-CMA02-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | Sabka Gatch Compaction | Trench Excavation | C-52-0405-CMA02-0990 | C-52-0405-CMA02-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | Trench Excavation | Bedding | C-52-0405-CMA02-1000 | C-52-0405-CMA02-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | Bedding | Lowering | C-52-0405-CMA02-1010 | C-52-0405-CMA02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | Lowering | Section Tie-in Welding | C-52-0405-CMA02-1020 | C-52-0405-CMA02-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA02-1030 | C-52-0405-CMA02-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA02-1040 | C-52-0405-CMA02-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA02-1050 | C-52-0405-CMA02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | Holiday Testing | Padding | C-52-0405-CMA02-1060 | C-52-0405-CMA02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0405-CMA03-0970 | C-52-0405-CMA03-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0405-CMA03-0980 | C-52-0405-CMA03-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | Sabka Gatch Compaction | Trench Excavation | C-52-0405-CMA03-0990 | C-52-0405-CMA03-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | Trench Excavation | Bedding | C-52-0405-CMA03-1000 | C-52-0405-CMA03-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | Bedding | Lowering | C-52-0405-CMA03-1010 | C-52-0405-CMA03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | Lowering | Section Tie-in Welding | C-52-0405-CMA03-1020 | C-52-0405-CMA03-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA03-1030 | C-52-0405-CMA03-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA03-1040 | C-52-0405-CMA03-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA03-1050 | C-52-0405-CMA03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | Holiday Testing | Padding | C-52-0405-CMA03-1060 | C-52-0405-CMA03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0405-CMA28-0980 | C-52-0405-CMA28-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | Sabka Gatch Compaction | Trench Excavation | C-52-0405-CMA28-0990 | C-52-0405-CMA28-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | Trench Excavation | Bedding | C-52-0405-CMA28-1000 | C-52-0405-CMA28-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | Bedding | Lowering | C-52-0405-CMA28-1010 | C-52-0405-CMA28-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | Lowering | Section Tie-in Welding | C-52-0405-CMA28-1020 | C-52-0405-CMA28-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA28-1030 | C-52-0405-CMA28-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA28-1040 | C-52-0405-CMA28-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA28-1050 | C-52-0405-CMA28-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | Holiday Testing | Padding | C-52-0405-CMA28-1060 | C-52-0405-CMA28-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0405-CMA29-0980 | C-52-0405-CMA29-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | Sabka Gatch Compaction | Trench Excavation | C-52-0405-CMA29-0990 | C-52-0405-CMA29-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | Trench Excavation | Bedding | C-52-0405-CMA29-1000 | C-52-0405-CMA29-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | Bedding | Lowering | C-52-0405-CMA29-1010 | C-52-0405-CMA29-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | Lowering | Section Tie-in Welding | C-52-0405-CMA29-1020 | C-52-0405-CMA29-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA29-1030 | C-52-0405-CMA29-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA29-1040 | C-52-0405-CMA29-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA29-1050 | C-52-0405-CMA29-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | Holiday Testing | Padding | C-52-0405-CMA29-1060 | C-52-0405-CMA29-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0405-CMA30-0980 | C-52-0405-CMA30-0990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | Sabka Gatch Compaction | Trench Excavation | C-52-0405-CMA30-0990 | C-52-0405-CMA30-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | Trench Excavation | Bedding | C-52-0405-CMA30-1000 | C-52-0405-CMA30-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | Bedding | Lowering | C-52-0405-CMA30-1010 | C-52-0405-CMA30-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | Lowering | Section Tie-in Welding | C-52-0405-CMA30-1020 | C-52-0405-CMA30-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA30-1030 | C-52-0405-CMA30-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA30-1040 | C-52-0405-CMA30-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA30-1050 | C-52-0405-CMA30-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | Holiday Testing | Padding | C-52-0405-CMA30-1060 | C-52-0405-CMA30-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0405-CMA23-1000 | C-52-0405-CMA23-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-0405-CMA23-1010 | C-52-0405-CMA23-1020 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | Sabka Gatch Compaction | Trench Excavation | C-52-0405-CMA23-1020 | C-52-0405-CMA23-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | Trench Excavation | Bedding | C-52-0405-CMA23-1030 | C-52-0405-CMA23-1040 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | Bedding | Lowering | C-52-0405-CMA23-1040 | C-52-0405-CMA23-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | Lowering | Section Tie-in Welding | C-52-0405-CMA23-1050 | C-52-0405-CMA23-1060 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA23-1060 | C-52-0405-CMA23-1070 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA23-1070 | C-52-0405-CMA23-1080 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA23-1080 | C-52-0405-CMA23-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | Holiday Testing | Padding | C-52-0405-CMA23-1090 | C-52-0405-CMA23-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | Trench Excavation | Bedding | C-52-0405-CMA31-1000 | C-52-0405-CMA31-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | Bedding | Lowering | C-52-0405-CMA31-1010 | C-52-0405-CMA31-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | Lowering | Section Tie-in Welding | C-52-0405-CMA31-1020 | C-52-0405-CMA31-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA31-1030 | C-52-0405-CMA31-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA31-1040 | C-52-0405-CMA31-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA31-1050 | C-52-0405-CMA31-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | Holiday Testing | Padding | C-52-0405-CMA31-1060 | C-52-0405-CMA31-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | Trench Excavation | Bedding | C-52-0405-CMA04-1000 | C-52-0405-CMA04-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | Bedding | Lowering | C-52-0405-CMA04-1010 | C-52-0405-CMA04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | Lowering | Section Tie-in Welding | C-52-0405-CMA04-1020 | C-52-0405-CMA04-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA04-1030 | C-52-0405-CMA04-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA04-1040 | C-52-0405-CMA04-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA04-1050 | C-52-0405-CMA04-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | Holiday Testing | Padding | C-52-0405-CMA04-1060 | C-52-0405-CMA04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | Trench Excavation | Bedding | C-52-0405-CMA05-1000 | C-52-0405-CMA05-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | Bedding | Lowering | C-52-0405-CMA05-1010 | C-52-0405-CMA05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | Lowering | Section Tie-in Welding | C-52-0405-CMA05-1020 | C-52-0405-CMA05-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA05-1030 | C-52-0405-CMA05-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA05-1040 | C-52-0405-CMA05-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA05-1050 | C-52-0405-CMA05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | Holiday Testing | Padding | C-52-0405-CMA05-1060 | C-52-0405-CMA05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | Trench Excavation | Bedding | C-52-0405-CMA06-1000 | C-52-0405-CMA06-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | Bedding | Lowering | C-52-0405-CMA06-1010 | C-52-0405-CMA06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | Lowering | Section Tie-in Welding | C-52-0405-CMA06-1020 | C-52-0405-CMA06-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA06-1030 | C-52-0405-CMA06-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA06-1040 | C-52-0405-CMA06-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA06-1050 | C-52-0405-CMA06-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | Holiday Testing | Padding | C-52-0405-CMA06-1060 | C-52-0405-CMA06-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | Trench Excavation | Bedding | C-52-0405-CMA07-1000 | C-52-0405-CMA07-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | Bedding | Lowering | C-52-0405-CMA07-1010 | C-52-0405-CMA07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | Lowering | Section Tie-in Welding | C-52-0405-CMA07-1020 | C-52-0405-CMA07-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA07-1030 | C-52-0405-CMA07-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA07-1040 | C-52-0405-CMA07-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA07-1050 | C-52-0405-CMA07-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | Holiday Testing | Padding | C-52-0405-CMA07-1060 | C-52-0405-CMA07-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | Trench Excavation | Bedding | C-52-0405-CMA08-1000 | C-52-0405-CMA08-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | Bedding | Lowering | C-52-0405-CMA08-1010 | C-52-0405-CMA08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | Lowering | Section Tie-in Welding | C-52-0405-CMA08-1020 | C-52-0405-CMA08-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA08-1030 | C-52-0405-CMA08-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA08-1040 | C-52-0405-CMA08-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA08-1050 | C-52-0405-CMA08-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | Holiday Testing | Padding | C-52-0405-CMA08-1060 | C-52-0405-CMA08-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | Trench Excavation | Bedding | C-52-0405-CMA09-1000 | C-52-0405-CMA09-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | Bedding | Lowering | C-52-0405-CMA09-1010 | C-52-0405-CMA09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | Lowering | Section Tie-in Welding | C-52-0405-CMA09-1020 | C-52-0405-CMA09-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA09-1030 | C-52-0405-CMA09-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA09-1040 | C-52-0405-CMA09-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA09-1050 | C-52-0405-CMA09-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | Holiday Testing | Padding | C-52-0405-CMA09-1060 | C-52-0405-CMA09-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | Trench Excavation | Bedding | C-52-0405-CMA10-1000 | C-52-0405-CMA10-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | Bedding | Lowering | C-52-0405-CMA10-1010 | C-52-0405-CMA10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | Lowering | Section Tie-in Welding | C-52-0405-CMA10-1020 | C-52-0405-CMA10-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA10-1030 | C-52-0405-CMA10-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA10-1040 | C-52-0405-CMA10-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA10-1050 | C-52-0405-CMA10-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | Holiday Testing | Padding | C-52-0405-CMA10-1060 | C-52-0405-CMA10-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | Trench Excavation | Bedding | C-52-0405-CMA11-1000 | C-52-0405-CMA11-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | Bedding | Lowering | C-52-0405-CMA11-1010 | C-52-0405-CMA11-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | Lowering | Section Tie-in Welding | C-52-0405-CMA11-1020 | C-52-0405-CMA11-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA11-1030 | C-52-0405-CMA11-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA11-1040 | C-52-0405-CMA11-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA11-1050 | C-52-0405-CMA11-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | Holiday Testing | Padding | C-52-0405-CMA11-1060 | C-52-0405-CMA11-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | Trench Excavation | Bedding | C-52-0405-CMA12-1000 | C-52-0405-CMA12-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | Bedding | Lowering | C-52-0405-CMA12-1010 | C-52-0405-CMA12-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | Lowering | Section Tie-in Welding | C-52-0405-CMA12-1020 | C-52-0405-CMA12-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA12-1030 | C-52-0405-CMA12-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA12-1040 | C-52-0405-CMA12-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA12-1050 | C-52-0405-CMA12-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | Holiday Testing | Padding | C-52-0405-CMA12-1060 | C-52-0405-CMA12-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | Trench Excavation | Bedding | C-52-0405-CMA13-1000 | C-52-0405-CMA13-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | Bedding | Lowering | C-52-0405-CMA13-1010 | C-52-0405-CMA13-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | Lowering | Section Tie-in Welding | C-52-0405-CMA13-1020 | C-52-0405-CMA13-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA13-1030 | C-52-0405-CMA13-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA13-1040 | C-52-0405-CMA13-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA13-1050 | C-52-0405-CMA13-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | Holiday Testing | Padding | C-52-0405-CMA13-1060 | C-52-0405-CMA13-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | Trench Excavation | Bedding | C-52-0405-CMA14-1000 | C-52-0405-CMA14-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | Bedding | Lowering | C-52-0405-CMA14-1010 | C-52-0405-CMA14-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | Lowering | Section Tie-in Welding | C-52-0405-CMA14-1020 | C-52-0405-CMA14-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA14-1030 | C-52-0405-CMA14-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA14-1040 | C-52-0405-CMA14-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA14-1050 | C-52-0405-CMA14-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | Holiday Testing | Padding | C-52-0405-CMA14-1060 | C-52-0405-CMA14-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | Trench Excavation | Bedding | C-52-0405-CMA15-1000 | C-52-0405-CMA15-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | Bedding | Lowering | C-52-0405-CMA15-1010 | C-52-0405-CMA15-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | Lowering | Section Tie-in Welding | C-52-0405-CMA15-1020 | C-52-0405-CMA15-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA15-1030 | C-52-0405-CMA15-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA15-1040 | C-52-0405-CMA15-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA15-1050 | C-52-0405-CMA15-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | Holiday Testing | Padding | C-52-0405-CMA15-1060 | C-52-0405-CMA15-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | Trench Excavation | Bedding | C-52-0405-CMA24-1000 | C-52-0405-CMA24-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | Bedding | Lowering | C-52-0405-CMA24-1010 | C-52-0405-CMA24-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | Lowering | Section Tie-in Welding | C-52-0405-CMA24-1020 | C-52-0405-CMA24-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA24-1030 | C-52-0405-CMA24-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA24-1040 | C-52-0405-CMA24-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA24-1050 | C-52-0405-CMA24-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | Holiday Testing | Padding | C-52-0405-CMA24-1060 | C-52-0405-CMA24-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | Trench Excavation | Bedding | C-52-0405-CMA16-1000 | C-52-0405-CMA16-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | Bedding | Lowering | C-52-0405-CMA16-1010 | C-52-0405-CMA16-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | Lowering | Section Tie-in Welding | C-52-0405-CMA16-1020 | C-52-0405-CMA16-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA16-1030 | C-52-0405-CMA16-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA16-1040 | C-52-0405-CMA16-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA16-1050 | C-52-0405-CMA16-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | Holiday Testing | Padding | C-52-0405-CMA16-1060 | C-52-0405-CMA16-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | Trench Excavation | Bedding | C-52-0405-CMA17-1000 | C-52-0405-CMA17-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | Bedding | Lowering | C-52-0405-CMA17-1010 | C-52-0405-CMA17-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | Lowering | Section Tie-in Welding | C-52-0405-CMA17-1020 | C-52-0405-CMA17-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA17-1030 | C-52-0405-CMA17-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA17-1040 | C-52-0405-CMA17-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA17-1050 | C-52-0405-CMA17-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | Holiday Testing | Padding | C-52-0405-CMA17-1060 | C-52-0405-CMA17-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | Trench Excavation | Bedding | C-52-0405-CMA18-1000 | C-52-0405-CMA18-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | Bedding | Lowering | C-52-0405-CMA18-1010 | C-52-0405-CMA18-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | Lowering | Section Tie-in Welding | C-52-0405-CMA18-1020 | C-52-0405-CMA18-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA18-1030 | C-52-0405-CMA18-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA18-1040 | C-52-0405-CMA18-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA18-1050 | C-52-0405-CMA18-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | Holiday Testing | Padding | C-52-0405-CMA18-1060 | C-52-0405-CMA18-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | Trench Excavation | Bedding | C-52-0405-CMA19-1000 | C-52-0405-CMA19-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | Bedding | Lowering | C-52-0405-CMA19-1010 | C-52-0405-CMA19-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | Lowering | Section Tie-in Welding | C-52-0405-CMA19-1020 | C-52-0405-CMA19-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA19-1030 | C-52-0405-CMA19-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA19-1040 | C-52-0405-CMA19-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA19-1050 | C-52-0405-CMA19-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | Holiday Testing | Padding | C-52-0405-CMA19-1060 | C-52-0405-CMA19-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | Trench Excavation | Bedding | C-52-0405-CMA32-1000 | C-52-0405-CMA32-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | Bedding | Lowering | C-52-0405-CMA32-1010 | C-52-0405-CMA32-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | Lowering | Section Tie-in Welding | C-52-0405-CMA32-1020 | C-52-0405-CMA32-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CMA32-1030 | C-52-0405-CMA32-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CMA32-1040 | C-52-0405-CMA32-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CMA32-1050 | C-52-0405-CMA32-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | Holiday Testing | Padding | C-52-0405-CMA32-1060 | C-52-0405-CMA32-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | Trench Excavation | Bedding | C-52-0405-CME01-1000 | C-52-0405-CME01-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | Bedding | Lowering | C-52-0405-CME01-1010 | C-52-0405-CME01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | Lowering | Section Tie-in Welding | C-52-0405-CME01-1020 | C-52-0405-CME01-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CME01-1030 | C-52-0405-CME01-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME01-1040 | C-52-0405-CME01-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CME01-1050 | C-52-0405-CME01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | Holiday Testing | Padding & Back Filling | C-52-0405-CME01-1060 | C-52-0405-CME01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | Trench Excavation | Bedding | C-52-0405-CME02-1000 | C-52-0405-CME02-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | Bedding | Lowering | C-52-0405-CME02-1010 | C-52-0405-CME02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | Lowering | Section Tie-in Welding | C-52-0405-CME02-1020 | C-52-0405-CME02-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CME02-1030 | C-52-0405-CME02-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME02-1040 | C-52-0405-CME02-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CME02-1050 | C-52-0405-CME02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | Holiday Testing | Padding & Back Filling | C-52-0405-CME02-1060 | C-52-0405-CME02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | Trench Excavation | Bedding | C-52-0405-CME03-1000 | C-52-0405-CME03-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | Bedding | Lowering | C-52-0405-CME03-1010 | C-52-0405-CME03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | Lowering | Section Tie-in Welding | C-52-0405-CME03-1020 | C-52-0405-CME03-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CME03-1030 | C-52-0405-CME03-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME03-1040 | C-52-0405-CME03-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CME03-1050 | C-52-0405-CME03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | Holiday Testing | Padding & Back Filling | C-52-0405-CME03-1060 | C-52-0405-CME03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | Trench Excavation | Bedding | C-52-0405-CME04-1000 | C-52-0405-CME04-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | Bedding | Lowering | C-52-0405-CME04-1010 | C-52-0405-CME04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | Lowering | Section Tie-in Welding | C-52-0405-CME04-1020 | C-52-0405-CME04-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CME04-1030 | C-52-0405-CME04-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME04-1040 | C-52-0405-CME04-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CME04-1050 | C-52-0405-CME04-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | Holiday Testing | Padding & Back Filling | C-52-0405-CME04-1060 | C-52-0405-CME04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | Trench Excavation | Bedding | C-52-0405-CME05-1000 | C-52-0405-CME05-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | Bedding | Lowering | C-52-0405-CME05-1010 | C-52-0405-CME05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | Lowering | Section Tie-in Welding | C-52-0405-CME05-1020 | C-52-0405-CME05-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CME05-1030 | C-52-0405-CME05-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME05-1040 | C-52-0405-CME05-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CME05-1050 | C-52-0405-CME05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | Holiday Testing | Padding & Back Filling | C-52-0405-CME05-1060 | C-52-0405-CME05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | Trench Excavation | Bedding | C-52-0405-CME06-1000 | C-52-0405-CME06-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | Bedding | Lowering | C-52-0405-CME06-1010 | C-52-0405-CME06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | Lowering | Section Tie-in Welding | C-52-0405-CME06-1020 | C-52-0405-CME06-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CME06-1030 | C-52-0405-CME06-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME06-1040 | C-52-0405-CME06-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CME06-1050 | C-52-0405-CME06-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | Holiday Testing | Padding & Back Filling | C-52-0405-CME06-1060 | C-52-0405-CME06-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | Trench Excavation | Bedding | C-52-0405-CME07-1000 | C-52-0405-CME07-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | Bedding | Lowering | C-52-0405-CME07-1010 | C-52-0405-CME07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | Lowering | Section Tie-in Welding | C-52-0405-CME07-1020 | C-52-0405-CME07-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CME07-1030 | C-52-0405-CME07-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME07-1040 | C-52-0405-CME07-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CME07-1050 | C-52-0405-CME07-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | Holiday Testing | Padding & Back Filling | C-52-0405-CME07-1060 | C-52-0405-CME07-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | Trench Excavation | Bedding | C-52-0405-CME08-1000 | C-52-0405-CME08-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | Bedding | Lowering | C-52-0405-CME08-1010 | C-52-0405-CME08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | Lowering | Section Tie-in Welding | C-52-0405-CME08-1020 | C-52-0405-CME08-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CME08-1030 | C-52-0405-CME08-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME08-1040 | C-52-0405-CME08-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CME08-1050 | C-52-0405-CME08-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | Holiday Testing | Padding & Back Filling | C-52-0405-CME08-1060 | C-52-0405-CME08-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52904 | P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52904 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-0405-CNM17-1000 | C-52-0405-CNM17-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52904 | P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52904 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNM17-1010 | C-52-0405-CNM17-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52904 | P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52904 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-0405-CNM17-1030 | C-52-0405-CNM17-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52904 | P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52904 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0405-CNM17-1040 | C-52-0405-CNM17-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52904 | P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52904 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-0405-CNM17-1050 | C-52-0405-CNM17-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52904 | P2543-R01-Oct24..4.3.1.3.17.21.2.2.2 Tunneling & Jack UpCCOPL57102 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-0405-CNM17-1060 | C-52-0405-CNM17-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.2.2 Tunneling & Jack UpCCOPL57102 | P2543-R01-Oct24..4.3.1.3.17.21.2.2.2 Tunneling & Jack UpCCOPL57102 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0405-CNM17-1200 | C-52-0405-CNM17-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.2.2 Tunneling & Jack UpCCOPL57102 | P2543-R01-Oct24..4.3.1.3.17.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57112 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-0405-CNM17-1210 | C-52-0405-CNM17-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57112 | P2543-R01-Oct24..4.3.1.3.17.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57112 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0405-CNM17-1400 | C-52-0405-CNM17-1410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57112 | P2543-R01-Oct24..4.3.1.3.17.21.2.2.4 HydrotestingCCOPL57122 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0405-CNM17-1410 | C-52-0405-CNM17-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.2.4 HydrotestingCCOPL57122 | P2543-R01-Oct24..4.3.1.3.17.21.2.2.2 Tunneling & Jack UpCCOPL57102 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-0405-CNM17-1600 | C-52-0405-CNM17-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.2.2 Tunneling & Jack UpCCOPL57102 | P2543-R01-Oct24..4.3.1.3.17.21.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57132 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0405-CNM17-1220 | C-52-0405-CNM17-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52904 | P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52904 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-0405-CNM17-1000 | C-52-0405-CNM17-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52904 | P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52904 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNM17-1020 | C-52-0405-CNM17-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52906 | P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52906 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-0405-CNM18-1000 | C-52-0405-CNM18-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52906 | P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52906 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNM18-1010 | C-52-0405-CNM18-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52906 | P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52906 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-0405-CNM18-1030 | C-52-0405-CNM18-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52906 | P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52906 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0405-CNM18-1040 | C-52-0405-CNM18-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52906 | P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52906 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-0405-CNM18-1050 | C-52-0405-CNM18-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52906 | P2543-R01-Oct24..4.3.1.3.17.21.2.3.2 Tunneling & Jack UpCCOPL57762 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-0405-CNM18-1060 | C-52-0405-CNM18-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.3.2 Tunneling & Jack UpCCOPL57762 | P2543-R01-Oct24..4.3.1.3.17.21.2.3.2 Tunneling & Jack UpCCOPL57762 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0405-CNM18-1200 | C-52-0405-CNM18-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.3.2 Tunneling & Jack UpCCOPL57762 | P2543-R01-Oct24..4.3.1.3.17.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57772 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-0405-CNM18-1210 | C-52-0405-CNM18-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57772 | P2543-R01-Oct24..4.3.1.3.17.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57772 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0405-CNM18-1400 | C-52-0405-CNM18-1410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57772 | P2543-R01-Oct24..4.3.1.3.17.21.2.3.4 HydrotestingCCOPL57782 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0405-CNM18-1410 | C-52-0405-CNM18-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.3.4 HydrotestingCCOPL57782 | P2543-R01-Oct24..4.3.1.3.17.21.2.3.2 Tunneling & Jack UpCCOPL57762 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-0405-CNM18-1600 | C-52-0405-CNM18-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.3.2 Tunneling & Jack UpCCOPL57762 | P2543-R01-Oct24..4.3.1.3.17.21.2.3.5 Re-Instatement of Entry & Exit PitCCOPL57792 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0405-CNM18-1220 | C-52-0405-CNM18-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52906 | P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52906 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-0405-CNM18-1000 | C-52-0405-CNM18-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52906 | P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52906 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNM18-1020 | C-52-0405-CNM18-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-0405-CNH19-1000 | C-52-0405-CNH19-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNH19-1010 | C-52-0405-CNH19-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-0405-CNH19-1030 | C-52-0405-CNH19-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0405-CNH19-1040 | C-52-0405-CNH19-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-0405-CNH19-1050 | C-52-0405-CNH19-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | P2543-R01-Oct24..4.3.1.3.17.21.8.4.2 Tunneling & Jack UpCCOPL58142 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-0405-CNH19-1060 | C-52-0405-CNH19-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.2 Tunneling & Jack UpCCOPL58142 | P2543-R01-Oct24..4.3.1.3.17.21.8.4.2 Tunneling & Jack UpCCOPL58142 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0405-CNH19-1200 | C-52-0405-CNH19-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.2 Tunneling & Jack UpCCOPL58142 | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-0405-CNH19-1210 | C-52-0405-CNH19-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0405-CNH19-1070 | C-52-0405-CNH19-1080 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0405-CNH19-1080 | C-52-0405-CNH19-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | P2543-R01-Oct24..4.3.1.3.17.21.8.4.2 Tunneling & Jack UpCCOPL58142 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-0405-CNH19-1090 | C-52-0405-CNH19-1220 | FS | Not Started | Not Started | 10
P2543-R01-Oct24..4.3.1.3.17.21.8.4.2 Tunneling & Jack UpCCOPL58142 | P2543-R01-Oct24..4.3.1.3.17.21.8.4.3 Re-Instatement of Entry & Exit PitCCOPL58152 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0405-CNH19-1220 | C-52-0405-CNH19-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-0405-CNH19-1000 | C-52-0405-CNH19-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNH19-1020 | C-52-0405-CNH19-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-0405-CNH20-1000 | C-52-0405-CNH20-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNH20-1010 | C-52-0405-CNH20-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-0405-CNH20-1030 | C-52-0405-CNH20-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0405-CNH20-1040 | C-52-0405-CNH20-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-0405-CNH20-1050 | C-52-0405-CNH20-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 Tunneling & Jack UpCCOPL58302 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-0405-CNH20-1060 | C-52-0405-CNH20-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 Tunneling & Jack UpCCOPL58302 | P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 Tunneling & Jack UpCCOPL58302 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0405-CNH20-1200 | C-52-0405-CNH20-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 Tunneling & Jack UpCCOPL58302 | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-0405-CNH20-1210 | C-52-0405-CNH20-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0405-CNH20-1070 | C-52-0405-CNH20-1080 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0405-CNH20-1080 | C-52-0405-CNH20-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 Tunneling & Jack UpCCOPL58302 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-0405-CNH20-1090 | C-52-0405-CNH20-1220 | FS | Not Started | Not Started | 10
P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 Tunneling & Jack UpCCOPL58302 | P2543-R01-Oct24..4.3.1.3.17.21.8.5.3 Re-Instatement of Entry & Exit PitCCOPL58312 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0405-CNH20-1220 | C-52-0405-CNH20-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-0405-CNH20-1000 | C-52-0405-CNH20-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNH20-1020 | C-52-0405-CNH20-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52914 | P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52914 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-0405-CNM23-1000 | C-52-0405-CNM23-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52914 | P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52914 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNM23-1010 | C-52-0405-CNM23-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52914 | P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52914 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-0405-CNM23-1030 | C-52-0405-CNM23-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52914 | P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52914 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0405-CNM23-1040 | C-52-0405-CNM23-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52914 | P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52914 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-0405-CNM23-1050 | C-52-0405-CNM23-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52914 | P2543-R01-Oct24..4.3.1.3.17.21.2.6.2 Tunneling & Jack UpCCOPL57722 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-0405-CNM23-1060 | C-52-0405-CNM23-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.6.2 Tunneling & Jack UpCCOPL57722 | P2543-R01-Oct24..4.3.1.3.17.21.2.6.2 Tunneling & Jack UpCCOPL57722 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0405-CNM23-1200 | C-52-0405-CNM23-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.6.2 Tunneling & Jack UpCCOPL57722 | P2543-R01-Oct24..4.3.1.3.17.21.2.6.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57732 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-0405-CNM23-1210 | C-52-0405-CNM23-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.6.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57732 | P2543-R01-Oct24..4.3.1.3.17.21.2.6.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57732 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0405-CNM23-1400 | C-52-0405-CNM23-1410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.6.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57732 | P2543-R01-Oct24..4.3.1.3.17.21.2.6.4 HydrotestingCCOPL57742 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0405-CNM23-1410 | C-52-0405-CNM23-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.6.4 HydrotestingCCOPL57742 | P2543-R01-Oct24..4.3.1.3.17.21.2.6.2 Tunneling & Jack UpCCOPL57722 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-0405-CNM23-1600 | C-52-0405-CNM23-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.6.2 Tunneling & Jack UpCCOPL57722 | P2543-R01-Oct24..4.3.1.3.17.21.2.6.5 Re-Instatement of Entry & Exit PitCCOPL57752 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0405-CNM23-1220 | C-52-0405-CNM23-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52914 | P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52914 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-0405-CNM23-1000 | C-52-0405-CNM23-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52914 | P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52914 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNM23-1020 | C-52-0405-CNM23-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-0405-CNH24-1000 | C-52-0405-CNH24-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNH24-1010 | C-52-0405-CNH24-1030 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-0405-CNH24-1030 | C-52-0405-CNH24-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0405-CNH24-1040 | C-52-0405-CNH24-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-0405-CNH24-1050 | C-52-0405-CNH24-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | P2543-R01-Oct24..4.3.1.3.17.21.8.7.2 Tunneling & Jack UpCCOPL58242 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-0405-CNH24-1060 | C-52-0405-CNH24-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.7.2 Tunneling & Jack UpCCOPL58242 | P2543-R01-Oct24..4.3.1.3.17.21.8.7.2 Tunneling & Jack UpCCOPL58242 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0405-CNH24-1200 | C-52-0405-CNH24-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.7.2 Tunneling & Jack UpCCOPL58242 | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-0405-CNH24-1210 | C-52-0405-CNH24-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0405-CNH24-1070 | C-52-0405-CNH24-1080 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0405-CNH24-1080 | C-52-0405-CNH24-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | P2543-R01-Oct24..4.3.1.3.17.21.8.7.2 Tunneling & Jack UpCCOPL58242 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-0405-CNH24-1090 | C-52-0405-CNH24-1220 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.8.7.2 Tunneling & Jack UpCCOPL58242 | P2543-R01-Oct24..4.3.1.3.17.21.8.7.3 Re-Instatement of Entry & Exit PitCCOPL58252 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0405-CNH24-1220 | C-52-0405-CNH24-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-0405-CNH24-1000 | C-52-0405-CNH24-1010 | SS | Not Started | Not Started | 21
P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0405-CNH24-1020 | C-52-0405-CNH24-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-0506-CNH27-1000 | C-52-0506-CNH27-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0506-CNH27-1010 | C-52-0506-CNH27-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-0506-CNH27-1030 | C-52-0506-CNH27-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-0506-CNH27-1040 | C-52-0506-CNH27-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-0506-CNH27-1050 | C-52-0506-CNH27-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | P2543-R01-Oct24..4.3.1.3.18.21.3.1.2 Tunneling & Jack UpCCOPL58182 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-0506-CNH27-1060 | C-52-0506-CNH27-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.2 Tunneling & Jack UpCCOPL58182 | P2543-R01-Oct24..4.3.1.3.18.21.3.1.2 Tunneling & Jack UpCCOPL58182 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-0506-CNH27-1200 | C-52-0506-CNH27-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.2 Tunneling & Jack UpCCOPL58182 | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-0506-CNH27-1210 | C-52-0506-CNH27-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0506-CNH27-1070 | C-52-0506-CNH27-1080 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-0506-CNH27-1080 | C-52-0506-CNH27-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | P2543-R01-Oct24..4.3.1.3.18.21.3.1.2 Tunneling & Jack UpCCOPL58182 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-0506-CNH27-1090 | C-52-0506-CNH27-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.2 Tunneling & Jack UpCCOPL58182 | P2543-R01-Oct24..4.3.1.3.18.21.3.1.3 Re-Instatement of Entry & Exit PitCCOPL58192 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-0506-CNH27-1220 | C-52-0506-CNH27-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-0506-CNH27-1000 | C-52-0506-CNH27-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-0506-CNH27-1020 | C-52-0506-CNH27-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | Trench Excavation | Bedding | C-52-0506-CMA06-1000 | C-52-0506-CMA06-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | Bedding | Lowering | C-52-0506-CMA06-1010 | C-52-0506-CMA06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | Lowering | Section Tie-in Welding | C-52-0506-CMA06-1020 | C-52-0506-CMA06-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CMA06-1030 | C-52-0506-CMA06-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA06-1040 | C-52-0506-CMA06-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CMA06-1050 | C-52-0506-CMA06-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | Holiday Testing | Padding | C-52-0506-CMA06-1060 | C-52-0506-CMA06-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | Trench Excavation | Bedding | C-52-0506-CMA07-1000 | C-52-0506-CMA07-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | Bedding | Lowering | C-52-0506-CMA07-1010 | C-52-0506-CMA07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | Lowering | Section Tie-in Welding | C-52-0506-CMA07-1020 | C-52-0506-CMA07-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CMA07-1030 | C-52-0506-CMA07-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA07-1040 | C-52-0506-CMA07-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CMA07-1050 | C-52-0506-CMA07-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | Holiday Testing | Padding | C-52-0506-CMA07-1060 | C-52-0506-CMA07-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | Trench Excavation | Bedding | C-52-0506-CMA04-1000 | C-52-0506-CMA04-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | Bedding | Lowering | C-52-0506-CMA04-1010 | C-52-0506-CMA04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | Lowering | Section Tie-in Welding | C-52-0506-CMA04-1020 | C-52-0506-CMA04-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CMA04-1030 | C-52-0506-CMA04-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA04-1040 | C-52-0506-CMA04-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CMA04-1050 | C-52-0506-CMA04-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | Holiday Testing | Padding | C-52-0506-CMA04-1060 | C-52-0506-CMA04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | Trench Excavation | Bedding | C-52-0506-CMA02-1000 | C-52-0506-CMA02-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | Bedding | Lowering | C-52-0506-CMA02-1010 | C-52-0506-CMA02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | Lowering | Section Tie-in Welding | C-52-0506-CMA02-1020 | C-52-0506-CMA02-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CMA02-1030 | C-52-0506-CMA02-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA02-1040 | C-52-0506-CMA02-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CMA02-1050 | C-52-0506-CMA02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | Holiday Testing | Padding | C-52-0506-CMA02-1060 | C-52-0506-CMA02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | Trench Excavation | Bedding | C-52-0506-CMA08-1000 | C-52-0506-CMA08-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | Bedding | Lowering | C-52-0506-CMA08-1010 | C-52-0506-CMA08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | Lowering | Section Tie-in Welding | C-52-0506-CMA08-1020 | C-52-0506-CMA08-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CMA08-1030 | C-52-0506-CMA08-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA08-1040 | C-52-0506-CMA08-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CMA08-1050 | C-52-0506-CMA08-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | Holiday Testing | Padding | C-52-0506-CMA08-1060 | C-52-0506-CMA08-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | Trench Excavation | Bedding | C-52-0506-CMA09-1000 | C-52-0506-CMA09-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | Bedding | Lowering | C-52-0506-CMA09-1010 | C-52-0506-CMA09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | Lowering | Section Tie-in Welding | C-52-0506-CMA09-1020 | C-52-0506-CMA09-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CMA09-1030 | C-52-0506-CMA09-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA09-1040 | C-52-0506-CMA09-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CMA09-1050 | C-52-0506-CMA09-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | Holiday Testing | Padding | C-52-0506-CMA09-1060 | C-52-0506-CMA09-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | Trench Excavation | Bedding | C-52-0506-CMA03-1000 | C-52-0506-CMA03-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | Bedding | Lowering | C-52-0506-CMA03-1010 | C-52-0506-CMA03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | Lowering | Section Tie-in Welding | C-52-0506-CMA03-1020 | C-52-0506-CMA03-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CMA03-1030 | C-52-0506-CMA03-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA03-1040 | C-52-0506-CMA03-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CMA03-1050 | C-52-0506-CMA03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | Holiday Testing | Padding | C-52-0506-CMA03-1060 | C-52-0506-CMA03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | Trench Excavation | Bedding | C-52-0506-CMA01-1000 | C-52-0506-CMA01-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | Bedding | Lowering | C-52-0506-CMA01-1010 | C-52-0506-CMA01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | Lowering | Section Tie-in Welding | C-52-0506-CMA01-1020 | C-52-0506-CMA01-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CMA01-1030 | C-52-0506-CMA01-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA01-1040 | C-52-0506-CMA01-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CMA01-1050 | C-52-0506-CMA01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | Holiday Testing | Padding | C-52-0506-CMA01-1060 | C-52-0506-CMA01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | Trench Excavation | Bedding | C-52-0506-CMA05-1000 | C-52-0506-CMA05-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | Bedding | Lowering | C-52-0506-CMA05-1010 | C-52-0506-CMA05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | Lowering | Section Tie-in Welding | C-52-0506-CMA05-1020 | C-52-0506-CMA05-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CMA05-1030 | C-52-0506-CMA05-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CMA05-1040 | C-52-0506-CMA05-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CMA05-1050 | C-52-0506-CMA05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | Holiday Testing | Padding | C-52-0506-CMA05-1060 | C-52-0506-CMA05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | Trench Excavation | Bedding | C-52-0506-CME01-1000 | C-52-0506-CME01-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | Bedding | Lowering | C-52-0506-CME01-1010 | C-52-0506-CME01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | Lowering | Section Tie-in Welding | C-52-0506-CME01-1020 | C-52-0506-CME01-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CME01-1030 | C-52-0506-CME01-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME01-1040 | C-52-0506-CME01-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CME01-1050 | C-52-0506-CME01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | Holiday Testing | Padding & Back Filling | C-52-0506-CME01-1060 | C-52-0506-CME01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | Trench Excavation | Bedding | C-52-0506-CME02-1000 | C-52-0506-CME02-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | Bedding | Lowering | C-52-0506-CME02-1010 | C-52-0506-CME02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | Lowering | Section Tie-in Welding | C-52-0506-CME02-1020 | C-52-0506-CME02-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CME02-1030 | C-52-0506-CME02-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME02-1040 | C-52-0506-CME02-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CME02-1050 | C-52-0506-CME02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | Holiday Testing | Padding & Back Filling | C-52-0506-CME02-1060 | C-52-0506-CME02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | Trench Excavation | Bedding | C-52-0506-CME03-1000 | C-52-0506-CME03-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | Bedding | Lowering | C-52-0506-CME03-1010 | C-52-0506-CME03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | Lowering | Section Tie-in Welding | C-52-0506-CME03-1020 | C-52-0506-CME03-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CME03-1030 | C-52-0506-CME03-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME03-1040 | C-52-0506-CME03-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CME03-1050 | C-52-0506-CME03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | Holiday Testing | Padding & Back Filling | C-52-0506-CME03-1060 | C-52-0506-CME03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | Trench Excavation | Bedding | C-52-0506-CME04-1000 | C-52-0506-CME04-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | Bedding | Lowering | C-52-0506-CME04-1010 | C-52-0506-CME04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | Lowering | Section Tie-in Welding | C-52-0506-CME04-1020 | C-52-0506-CME04-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CME04-1030 | C-52-0506-CME04-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME04-1040 | C-52-0506-CME04-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CME04-1050 | C-52-0506-CME04-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | Holiday Testing | Padding & Back Filling | C-52-0506-CME04-1060 | C-52-0506-CME04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | Trench Excavation | Bedding | C-52-0506-CME05-1000 | C-52-0506-CME05-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | Bedding | Lowering | C-52-0506-CME05-1010 | C-52-0506-CME05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | Lowering | Section Tie-in Welding | C-52-0506-CME05-1020 | C-52-0506-CME05-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CME05-1030 | C-52-0506-CME05-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME05-1040 | C-52-0506-CME05-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CME05-1050 | C-52-0506-CME05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | Holiday Testing | Padding & Back Filling | C-52-0506-CME05-1060 | C-52-0506-CME05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | Trench Excavation | Bedding | C-52-0506-CME06-1000 | C-52-0506-CME06-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | Bedding | Lowering | C-52-0506-CME06-1010 | C-52-0506-CME06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | Lowering | Section Tie-in Welding | C-52-0506-CME06-1020 | C-52-0506-CME06-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CME06-1030 | C-52-0506-CME06-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME06-1040 | C-52-0506-CME06-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CME06-1050 | C-52-0506-CME06-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | Holiday Testing | Padding & Back Filling | C-52-0506-CME06-1060 | C-52-0506-CME06-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | Trench Excavation | Bedding | C-52-0506-CME07-1000 | C-52-0506-CME07-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | Bedding | Lowering | C-52-0506-CME07-1010 | C-52-0506-CME07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | Lowering | Section Tie-in Welding | C-52-0506-CME07-1020 | C-52-0506-CME07-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CME07-1030 | C-52-0506-CME07-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME07-1040 | C-52-0506-CME07-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CME07-1050 | C-52-0506-CME07-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | Holiday Testing | Padding & Back Filling | C-52-0506-CME07-1060 | C-52-0506-CME07-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | Trench Excavation | Bedding | C-52-0506-CME08-1000 | C-52-0506-CME08-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | Bedding | Lowering | C-52-0506-CME08-1010 | C-52-0506-CME08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | Lowering | Section Tie-in Welding | C-52-0506-CME08-1020 | C-52-0506-CME08-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CME08-1030 | C-52-0506-CME08-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME08-1040 | C-52-0506-CME08-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CME08-1050 | C-52-0506-CME08-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | Holiday Testing | Padding & Back Filling | C-52-0506-CME08-1060 | C-52-0506-CME08-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | Trench Excavation | Bedding | C-52-0506-CME09-1000 | C-52-0506-CME09-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | Bedding | Lowering | C-52-0506-CME09-1010 | C-52-0506-CME09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | Lowering | Section Tie-in Welding | C-52-0506-CME09-1020 | C-52-0506-CME09-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CME09-1030 | C-52-0506-CME09-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME09-1040 | C-52-0506-CME09-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CME09-1050 | C-52-0506-CME09-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | Holiday Testing | Padding & Back Filling | C-52-0506-CME09-1060 | C-52-0506-CME09-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | Trench Excavation | Bedding | C-52-0506-CME10-1000 | C-52-0506-CME10-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | Bedding | Lowering | C-52-0506-CME10-1010 | C-52-0506-CME10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | Lowering | Section Tie-in Welding | C-52-0506-CME10-1020 | C-52-0506-CME10-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CME10-1030 | C-52-0506-CME10-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME10-1040 | C-52-0506-CME10-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CME10-1050 | C-52-0506-CME10-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | Holiday Testing | Padding & Back Filling | C-52-0506-CME10-1060 | C-52-0506-CME10-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-06CR-CNH30-1000 | C-52-06CR-CNH30-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-06CR-CNH30-1010 | C-52-06CR-CNH30-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-06CR-CNH30-1030 | C-52-06CR-CNH30-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-06CR-CNH30-1040 | C-52-06CR-CNH30-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-06CR-CNH30-1050 | C-52-06CR-CNH30-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | P2543-R01-Oct24..4.3.1.3.19.8.5.2.2 Tunneling & Jack UpCCOPL58122 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-06CR-CNH30-1060 | C-52-06CR-CNH30-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.5.2.2 Tunneling & Jack UpCCOPL58122 | P2543-R01-Oct24..4.3.1.3.19.8.5.2.2 Tunneling & Jack UpCCOPL58122 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-06CR-CNH30-1200 | C-52-06CR-CNH30-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.5.2.2 Tunneling & Jack UpCCOPL58122 | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-06CR-CNH30-1210 | C-52-06CR-CNH30-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-06CR-CNH30-1070 | C-52-06CR-CNH30-1080 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-06CR-CNH30-1080 | C-52-06CR-CNH30-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | P2543-R01-Oct24..4.3.1.3.19.8.5.2.2 Tunneling & Jack UpCCOPL58122 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-06CR-CNH30-1090 | C-52-06CR-CNH30-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.5.2.2 Tunneling & Jack UpCCOPL58122 | P2543-R01-Oct24..4.3.1.3.19.8.5.2.3 Re-Instatement of Entry & Exit PitCCOPL58132 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-06CR-CNH30-1220 | C-52-06CR-CNH30-1800 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-06CR-CNH30-1000 | C-52-06CR-CNH30-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-06CR-CNH30-1020 | C-52-06CR-CNH30-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-52-06CR-CNM31-1000 | C-52-06CR-CNM31-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-06CR-CNM31-1010 | C-52-06CR-CNM31-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-52-06CR-CNM31-1030 | C-52-06CR-CNM31-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-52-06CR-CNM31-1040 | C-52-06CR-CNM31-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-52-06CR-CNM31-1050 | C-52-06CR-CNM31-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.2 Tunneling & Jack UpCCOPL56932 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-52-06CR-CNM31-1060 | C-52-06CR-CNM31-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.2 Tunneling & Jack UpCCOPL56932 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.2 Tunneling & Jack UpCCOPL56932 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-52-06CR-CNM31-1200 | C-52-06CR-CNM31-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.2 Tunneling & Jack UpCCOPL56932 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.3 Pipe Lowering, Welding & NDTCCOPL56942 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-52-06CR-CNM31-1210 | C-52-06CR-CNM31-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.3 Pipe Lowering, Welding & NDTCCOPL56942 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.3 Pipe Lowering, Welding & NDTCCOPL56942 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-06CR-CNM31-1400 | C-52-06CR-CNM31-1410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.2.3.3 Pipe Lowering, Welding & NDTCCOPL56942 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.4 HydrotestingCCOPL56952 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-52-06CR-CNM31-1410 | C-52-06CR-CNM31-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.4 HydrotestingCCOPL56952 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.2 Tunneling & Jack UpCCOPL56932 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-06CR-CNM31-1600 | C-52-06CR-CNM31-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.2 Tunneling & Jack UpCCOPL56932 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.5 Re-Instatement of Entry & Exit PitCCOPL56962 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-52-06CR-CNM31-1220 | C-52-06CR-CNM31-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-06CR-CNM31-1000 | C-52-06CR-CNM31-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-52-06CR-CNM31-1020 | C-52-06CR-CNM31-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-06CR-CMA01-0970 | C-52-06CR-CMA01-980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | Sabkha Gatch Laying | Sabka Gatch Compaction | C-52-06CR-CMA01-980 | C-52-06CR-CMA01-990 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | Sabka Gatch Compaction | Trench Excavation | C-52-06CR-CMA01-990 | C-52-06CR-CMA01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | Trench Excavation | Bedding | C-52-06CR-CMA01-1000 | C-52-06CR-CMA01-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | Bedding | Lowering | C-52-06CR-CMA01-1010 | C-52-06CR-CMA01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | Lowering | Section Tie-in Welding | C-52-06CR-CMA01-1020 | C-52-06CR-CMA01-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CMA01-1030 | C-52-06CR-CMA01-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA01-1040 | C-52-06CR-CMA01-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CMA01-1050 | C-52-06CR-CMA01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | Holiday Testing | Padding | C-52-06CR-CMA01-1060 | C-52-06CR-CMA01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | Trench Excavation | Bedding | C-52-06CR-CMA11-1000 | C-52-06CR-CMA11-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | Bedding | Lowering | C-52-06CR-CMA11-1010 | C-52-06CR-CMA11-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | Lowering | Section Tie-in Welding | C-52-06CR-CMA11-1020 | C-52-06CR-CMA11-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CMA11-1030 | C-52-06CR-CMA11-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA11-1040 | C-52-06CR-CMA11-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CMA11-1050 | C-52-06CR-CMA11-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | Holiday Testing | Padding | C-52-06CR-CMA11-1060 | C-52-06CR-CMA11-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | Trench Excavation | Bedding | C-52-06CR-CMA08-1000 | C-52-06CR-CMA08-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | Bedding | Lowering | C-52-06CR-CMA08-1010 | C-52-06CR-CMA08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | Lowering | Section Tie-in Welding | C-52-06CR-CMA08-1020 | C-52-06CR-CMA08-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CMA08-1030 | C-52-06CR-CMA08-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA08-1040 | C-52-06CR-CMA08-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CMA08-1050 | C-52-06CR-CMA08-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | Holiday Testing | Padding | C-52-06CR-CMA08-1060 | C-52-06CR-CMA08-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | Trench Excavation | Bedding | C-52-06CR-CMA02-1000 | C-52-06CR-CMA02-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | Bedding | Lowering | C-52-06CR-CMA02-1010 | C-52-06CR-CMA02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | Lowering | Section Tie-in Welding | C-52-06CR-CMA02-1020 | C-52-06CR-CMA02-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CMA02-1030 | C-52-06CR-CMA02-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA02-1040 | C-52-06CR-CMA02-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CMA02-1050 | C-52-06CR-CMA02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | Holiday Testing | Padding | C-52-06CR-CMA02-1060 | C-52-06CR-CMA02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | Trench Excavation | Bedding | C-52-06CR-CMA03-1000 | C-52-06CR-CMA03-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | Bedding | Lowering | C-52-06CR-CMA03-1010 | C-52-06CR-CMA03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | Lowering | Section Tie-in Welding | C-52-06CR-CMA03-1020 | C-52-06CR-CMA03-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CMA03-1030 | C-52-06CR-CMA03-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA03-1040 | C-52-06CR-CMA03-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CMA03-1050 | C-52-06CR-CMA03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | Holiday Testing | Padding | C-52-06CR-CMA03-1060 | C-52-06CR-CMA03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | Trench Excavation | Bedding | C-52-06CR-CMA12-1000 | C-52-06CR-CMA12-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | Bedding | Lowering | C-52-06CR-CMA12-1010 | C-52-06CR-CMA12-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | Lowering | Section Tie-in Welding | C-52-06CR-CMA12-1020 | C-52-06CR-CMA12-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CMA12-1030 | C-52-06CR-CMA12-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA12-1040 | C-52-06CR-CMA12-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CMA12-1050 | C-52-06CR-CMA12-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | Holiday Testing | Padding | C-52-06CR-CMA12-1060 | C-52-06CR-CMA12-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | Trench Excavation | Bedding | C-52-06CR-CMA09-1000 | C-52-06CR-CMA09-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | Bedding | Lowering | C-52-06CR-CMA09-1010 | C-52-06CR-CMA09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | Lowering | Section Tie-in Welding | C-52-06CR-CMA09-1020 | C-52-06CR-CMA09-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CMA09-1030 | C-52-06CR-CMA09-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA09-1040 | C-52-06CR-CMA09-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CMA09-1050 | C-52-06CR-CMA09-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | Holiday Testing | Padding | C-52-06CR-CMA09-1060 | C-52-06CR-CMA09-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | Trench Excavation | Bedding | C-52-06CR-CMA04-1000 | C-52-06CR-CMA04-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | Bedding | Lowering | C-52-06CR-CMA04-1010 | C-52-06CR-CMA04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | Lowering | Section Tie-in Welding | C-52-06CR-CMA04-1020 | C-52-06CR-CMA04-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CMA04-1030 | C-52-06CR-CMA04-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA04-1040 | C-52-06CR-CMA04-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CMA04-1050 | C-52-06CR-CMA04-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | Holiday Testing | Padding | C-52-06CR-CMA04-1060 | C-52-06CR-CMA04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | Trench Excavation | Bedding | C-52-06CR-CMA05-1000 | C-52-06CR-CMA05-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | Bedding | Lowering | C-52-06CR-CMA05-1010 | C-52-06CR-CMA05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | Lowering | Section Tie-in Welding | C-52-06CR-CMA05-1020 | C-52-06CR-CMA05-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CMA05-1030 | C-52-06CR-CMA05-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA05-1040 | C-52-06CR-CMA05-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CMA05-1050 | C-52-06CR-CMA05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | Holiday Testing | Padding | C-52-06CR-CMA05-1060 | C-52-06CR-CMA05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | Trench Excavation | Bedding | C-52-06CR-CMA06-1000 | C-52-06CR-CMA06-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | Bedding | Lowering | C-52-06CR-CMA06-1010 | C-52-06CR-CMA06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | Lowering | Section Tie-in Welding | C-52-06CR-CMA06-1020 | C-52-06CR-CMA06-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CMA06-1030 | C-52-06CR-CMA06-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA06-1040 | C-52-06CR-CMA06-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CMA06-1050 | C-52-06CR-CMA06-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | Holiday Testing | Padding | C-52-06CR-CMA06-1060 | C-52-06CR-CMA06-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | Trench Excavation | Bedding | C-52-06CR-CMA10-1000 | C-52-06CR-CMA10-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | Bedding | Lowering | C-52-06CR-CMA10-1010 | C-52-06CR-CMA10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | Lowering | Section Tie-in Welding | C-52-06CR-CMA10-1020 | C-52-06CR-CMA10-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CMA10-1030 | C-52-06CR-CMA10-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA10-1040 | C-52-06CR-CMA10-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CMA10-1050 | C-52-06CR-CMA10-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | Holiday Testing | Padding | C-52-06CR-CMA10-1060 | C-52-06CR-CMA10-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | Trench Excavation | Bedding | C-52-06CR-CMA07-1000 | C-52-06CR-CMA07-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | Bedding | Lowering | C-52-06CR-CMA07-1010 | C-52-06CR-CMA07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | Lowering | Section Tie-in Welding | C-52-06CR-CMA07-1020 | C-52-06CR-CMA07-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CMA07-1030 | C-52-06CR-CMA07-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA07-1040 | C-52-06CR-CMA07-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CMA07-1050 | C-52-06CR-CMA07-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | Holiday Testing | Padding | C-52-06CR-CMA07-1060 | C-52-06CR-CMA07-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | Trench Excavation | Bedding | C-52-06CR-CMA13-1000 | C-52-06CR-CMA13-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | Bedding | Lowering | C-52-06CR-CMA13-1010 | C-52-06CR-CMA13-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | Lowering | Section Tie-in Welding | C-52-06CR-CMA13-1020 | C-52-06CR-CMA13-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CMA13-1030 | C-52-06CR-CMA13-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CMA13-1040 | C-52-06CR-CMA13-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CMA13-1050 | C-52-06CR-CMA13-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | Holiday Testing | Padding | C-52-06CR-CMA13-1060 | C-52-06CR-CMA13-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | Trench Excavation | Bedding | C-52-06CR-CME01-1000 | C-52-06CR-CME01-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | Bedding | Lowering | C-52-06CR-CME01-1010 | C-52-06CR-CME01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | Lowering | Section Tie-in Welding | C-52-06CR-CME01-1020 | C-52-06CR-CME01-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CME01-1030 | C-52-06CR-CME01-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME01-1040 | C-52-06CR-CME01-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CME01-1050 | C-52-06CR-CME01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | Holiday Testing | Padding & Back Filling | C-52-06CR-CME01-1060 | C-52-06CR-CME01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | Trench Excavation | Bedding | C-52-06CR-CME02-1000 | C-52-06CR-CME02-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | Bedding | Lowering | C-52-06CR-CME02-1010 | C-52-06CR-CME02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | Lowering | Section Tie-in Welding | C-52-06CR-CME02-1020 | C-52-06CR-CME02-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CME02-1030 | C-52-06CR-CME02-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME02-1040 | C-52-06CR-CME02-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CME02-1050 | C-52-06CR-CME02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | Holiday Testing | Padding & Back Filling | C-52-06CR-CME02-1060 | C-52-06CR-CME02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | Trench Excavation | Bedding | C-52-06CR-CME03-1000 | C-52-06CR-CME03-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | Bedding | Lowering | C-52-06CR-CME03-1010 | C-52-06CR-CME03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | Lowering | Section Tie-in Welding | C-52-06CR-CME03-1020 | C-52-06CR-CME03-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CME03-1030 | C-52-06CR-CME03-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME03-1040 | C-52-06CR-CME03-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CME03-1050 | C-52-06CR-CME03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | Holiday Testing | Padding & Back Filling | C-52-06CR-CME03-1060 | C-52-06CR-CME03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | Trench Excavation | Bedding | C-52-06CR-CME04-1000 | C-52-06CR-CME04-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | Bedding | Lowering | C-52-06CR-CME04-1010 | C-52-06CR-CME04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | Lowering | Section Tie-in Welding | C-52-06CR-CME04-1020 | C-52-06CR-CME04-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CME04-1030 | C-52-06CR-CME04-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME04-1040 | C-52-06CR-CME04-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CME04-1050 | C-52-06CR-CME04-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | Holiday Testing | Padding & Back Filling | C-52-06CR-CME04-1060 | C-52-06CR-CME04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | Trench Excavation | Bedding | C-52-06CR-CME05-1000 | C-52-06CR-CME05-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | Bedding | Lowering | C-52-06CR-CME05-1010 | C-52-06CR-CME05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | Lowering | Section Tie-in Welding | C-52-06CR-CME05-1020 | C-52-06CR-CME05-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CME05-1030 | C-52-06CR-CME05-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME05-1040 | C-52-06CR-CME05-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CME05-1050 | C-52-06CR-CME05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | Holiday Testing | Padding & Back Filling | C-52-06CR-CME05-1060 | C-52-06CR-CME05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | Trench Excavation | Bedding | C-52-06CR-CME06-1000 | C-52-06CR-CME06-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | Bedding | Lowering | C-52-06CR-CME06-1010 | C-52-06CR-CME06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | Lowering | Section Tie-in Welding | C-52-06CR-CME06-1020 | C-52-06CR-CME06-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CME06-1030 | C-52-06CR-CME06-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME06-1040 | C-52-06CR-CME06-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CME06-1050 | C-52-06CR-CME06-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | Holiday Testing | Padding & Back Filling | C-52-06CR-CME06-1060 | C-52-06CR-CME06-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | Trench Excavation | Bedding | C-52-06CR-CME07-1000 | C-52-06CR-CME07-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | Bedding | Lowering | C-52-06CR-CME07-1010 | C-52-06CR-CME07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | Lowering | Section Tie-in Welding | C-52-06CR-CME07-1020 | C-52-06CR-CME07-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CME07-1030 | C-52-06CR-CME07-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME07-1040 | C-52-06CR-CME07-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CME07-1050 | C-52-06CR-CME07-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | Holiday Testing | Padding & Back Filling | C-52-06CR-CME07-1060 | C-52-06CR-CME07-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | Trench Excavation | Bedding | C-52-06CR-CME08-1000 | C-52-06CR-CME08-1010 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | Bedding | Lowering | C-52-06CR-CME08-1010 | C-52-06CR-CME08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | Lowering | Section Tie-in Welding | C-52-06CR-CME08-1020 | C-52-06CR-CME08-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CME08-1030 | C-52-06CR-CME08-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME08-1040 | C-52-06CR-CME08-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CME08-1050 | C-52-06CR-CME08-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | Holiday Testing | Padding & Back Filling | C-52-06CR-CME08-1060 | C-52-06CR-CME08-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | Trench Excavation | Bedding | C-52-06CR-CME09-1000 | C-52-06CR-CME09-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | Bedding | Lowering | C-52-06CR-CME09-1010 | C-52-06CR-CME09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | Lowering | Section Tie-in Welding | C-52-06CR-CME09-1020 | C-52-06CR-CME09-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CME09-1030 | C-52-06CR-CME09-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME09-1040 | C-52-06CR-CME09-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CME09-1050 | C-52-06CR-CME09-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | Holiday Testing | Padding & Back Filling | C-52-06CR-CME09-1060 | C-52-06CR-CME09-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | Trench Excavation | Bedding | C-52-06CR-CME10-1000 | C-52-06CR-CME10-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | Bedding | Lowering | C-52-06CR-CME10-1010 | C-52-06CR-CME10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | Lowering | Section Tie-in Welding | C-52-06CR-CME10-1020 | C-52-06CR-CME10-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CME10-1030 | C-52-06CR-CME10-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME10-1040 | C-52-06CR-CME10-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CME10-1050 | C-52-06CR-CME10-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | Holiday Testing | Padding & Back Filling | C-52-06CR-CME10-1060 | C-52-06CR-CME10-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | Trench Excavation | Bedding | C-52-06CR-CME11-1000 | C-52-06CR-CME11-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | Bedding | Lowering | C-52-06CR-CME11-1010 | C-52-06CR-CME11-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | Lowering | Section Tie-in Welding | C-52-06CR-CME11-1020 | C-52-06CR-CME11-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CME11-1030 | C-52-06CR-CME11-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME11-1040 | C-52-06CR-CME11-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CME11-1050 | C-52-06CR-CME11-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | Holiday Testing | Padding & Back Filling | C-52-06CR-CME11-1060 | C-52-06CR-CME11-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | Trench Excavation | Bedding | C-52-06CR-CME12-1000 | C-52-06CR-CME12-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | Bedding | Lowering | C-52-06CR-CME12-1010 | C-52-06CR-CME12-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | Lowering | Section Tie-in Welding | C-52-06CR-CME12-1020 | C-52-06CR-CME12-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CME12-1030 | C-52-06CR-CME12-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME12-1040 | C-52-06CR-CME12-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CME12-1050 | C-52-06CR-CME12-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | Holiday Testing | Padding & Back Filling | C-52-06CR-CME12-1060 | C-52-06CR-CME12-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | Trench Excavation | Bedding | C-52-06CR-CME13-1000 | C-52-06CR-CME13-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | Bedding | Lowering | C-52-06CR-CME13-1010 | C-52-06CR-CME13-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | Lowering | Section Tie-in Welding | C-52-06CR-CME13-1020 | C-52-06CR-CME13-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CME13-1030 | C-52-06CR-CME13-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME13-1040 | C-52-06CR-CME13-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CME13-1050 | C-52-06CR-CME13-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | Holiday Testing | Padding & Back Filling | C-52-06CR-CME13-1060 | C-52-06CR-CME13-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | Trench Excavation | Bedding | C-52-06CR-CME14-1000 | C-52-06CR-CME14-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | Bedding | Lowering | C-52-06CR-CME14-1010 | C-52-06CR-CME14-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | Lowering | Section Tie-in Welding | C-52-06CR-CME14-1020 | C-52-06CR-CME14-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CME14-1030 | C-52-06CR-CME14-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME14-1040 | C-52-06CR-CME14-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CME14-1050 | C-52-06CR-CME14-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | Holiday Testing | Padding & Back Filling | C-52-06CR-CME14-1060 | C-52-06CR-CME14-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-56-01HG-CNM13-1000 | C-56-01HG-CNM13-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-01HG-CNM13-1010 | C-56-01HG-CNM13-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-56-01HG-CNM13-1030 | C-56-01HG-CNM13-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-01HG-CNM13-1040 | C-56-01HG-CNM13-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-56-01HG-CNM13-1050 | C-56-01HG-CNM13-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | P2543-R01-Oct24..4.3.1.2.3.12.2.1.2 Tunneling & Jack UpCCOPL57962 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-56-01HG-CNM13-1060 | C-56-01HG-CNM13-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.2 Tunneling & Jack UpCCOPL57962 | P2543-R01-Oct24..4.3.1.2.3.12.2.1.2 Tunneling & Jack UpCCOPL57962 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-56-01HG-CNM13-1200 | C-56-01HG-CNM13-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.2 Tunneling & Jack UpCCOPL57962 | P2543-R01-Oct24..4.3.1.2.3.12.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57972 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-56-01HG-CNM13-1210 | C-56-01HG-CNM13-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57972 | P2543-R01-Oct24..4.3.1.2.3.12.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57972 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-56-01HG-CNM13-1400 | C-56-01HG-CNM13-1410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57972 | P2543-R01-Oct24..4.3.1.2.3.12.2.1.4 HydrotestingCCOPL57982 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-01HG-CNM13-1410 | C-56-01HG-CNM13-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.4 HydrotestingCCOPL57982 | P2543-R01-Oct24..4.3.1.2.3.12.2.1.2 Tunneling & Jack UpCCOPL57962 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-56-01HG-CNM13-1600 | C-56-01HG-CNM13-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.2 Tunneling & Jack UpCCOPL57962 | P2543-R01-Oct24..4.3.1.2.3.12.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57992 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-01HG-CNM13-1220 | C-56-01HG-CNM13-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-56-01HG-CNM13-1000 | C-56-01HG-CNM13-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-01HG-CNM13-1020 | C-56-01HG-CNM13-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-56-01HG-CNM12-1000 | C-56-01HG-CNM12-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-01HG-CNM12-1010 | C-56-01HG-CNM12-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-56-01HG-CNM12-1030 | C-56-01HG-CNM12-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-01HG-CNM12-1040 | C-56-01HG-CNM12-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-56-01HG-CNM12-1050 | C-56-01HG-CNM12-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | P2543-R01-Oct24..4.3.1.2.3.12.2.2.2 Tunneling & Jack UpCCOPL57602 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-56-01HG-CNM12-1060 | C-56-01HG-CNM12-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.2 Tunneling & Jack UpCCOPL57602 | P2543-R01-Oct24..4.3.1.2.3.12.2.2.2 Tunneling & Jack UpCCOPL57602 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-56-01HG-CNM12-1200 | C-56-01HG-CNM12-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.2 Tunneling & Jack UpCCOPL57602 | P2543-R01-Oct24..4.3.1.2.3.12.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57612 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-56-01HG-CNM12-1210 | C-56-01HG-CNM12-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57612 | P2543-R01-Oct24..4.3.1.2.3.12.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57612 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-56-01HG-CNM12-1400 | C-56-01HG-CNM12-1410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57612 | P2543-R01-Oct24..4.3.1.2.3.12.2.2.4 HydrotestingCCOPL57622 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-01HG-CNM12-1410 | C-56-01HG-CNM12-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.4 HydrotestingCCOPL57622 | P2543-R01-Oct24..4.3.1.2.3.12.2.2.2 Tunneling & Jack UpCCOPL57602 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-56-01HG-CNM12-1600 | C-56-01HG-CNM12-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.2 Tunneling & Jack UpCCOPL57602 | P2543-R01-Oct24..4.3.1.2.3.12.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57632 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-01HG-CNM12-1220 | C-56-01HG-CNM12-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-56-01HG-CNM12-1000 | C-56-01HG-CNM12-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-01HG-CNM12-1020 | C-56-01HG-CNM12-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-56-01HG-CNM11-1000 | C-56-01HG-CNM11-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-01HG-CNM11-1010 | C-56-01HG-CNM11-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-56-01HG-CNM11-1030 | C-56-01HG-CNM11-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-01HG-CNM11-1040 | C-56-01HG-CNM11-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-56-01HG-CNM11-1050 | C-56-01HG-CNM11-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | P2543-R01-Oct24..4.3.1.2.3.12.2.3.2 Tunneling & Jack UpCCOPL57262 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-56-01HG-CNM11-1060 | C-56-01HG-CNM11-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.3.2 Tunneling & Jack UpCCOPL57262 | P2543-R01-Oct24..4.3.1.2.3.12.2.3.2 Tunneling & Jack UpCCOPL57262 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-56-01HG-CNM11-1200 | C-56-01HG-CNM11-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.3.2 Tunneling & Jack UpCCOPL57262 | P2543-R01-Oct24..4.3.1.2.3.12.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57272 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-56-01HG-CNM11-1210 | C-56-01HG-CNM11-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57272 | P2543-R01-Oct24..4.3.1.2.3.12.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57272 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-56-01HG-CNM11-1400 | C-56-01HG-CNM11-1410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57272 | P2543-R01-Oct24..4.3.1.2.3.12.2.3.4 HydrotestingCCOPL57282 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-01HG-CNM11-1410 | C-56-01HG-CNM11-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.3.4 HydrotestingCCOPL57282 | P2543-R01-Oct24..4.3.1.2.3.12.2.3.2 Tunneling & Jack UpCCOPL57262 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-56-01HG-CNM11-1600 | C-56-01HG-CNM11-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.3.2 Tunneling & Jack UpCCOPL57262 | P2543-R01-Oct24..4.3.1.2.3.12.2.3.5 Re-Instatement of Entry & Exit PitCCOPL57292 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-01HG-CNM11-1220 | C-56-01HG-CNM11-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-56-01HG-CNM11-1000 | C-56-01HG-CNM11-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-01HG-CNM11-1020 | C-56-01HG-CNM11-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-56-01HG-CNH10-1000 | C-56-01HG-CNH10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-01HG-CNH10-1010 | C-56-01HG-CNH10-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-56-01HG-CNH10-1030 | C-56-01HG-CNH10-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-01HG-CNH10-1040 | C-56-01HG-CNH10-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-56-01HG-CNH10-1050 | C-56-01HG-CNH10-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | P2543-R01-Oct24..4.3.1.2.3.12.6.4.2 Tunneling & Jack UpCCOPL58342 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-56-01HG-CNH10-1060 | C-56-01HG-CNH10-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.6.4.2 Tunneling & Jack UpCCOPL58342 | P2543-R01-Oct24..4.3.1.2.3.12.6.4.2 Tunneling & Jack UpCCOPL58342 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-56-01HG-CNH10-1200 | C-56-01HG-CNH10-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.6.4.2 Tunneling & Jack UpCCOPL58342 | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-56-01HG-CNH10-1210 | C-56-01HG-CNH10-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-56-01HG-CNH10-1070 | C-56-01HG-CNH10-1080 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-01HG-CNH10-1080 | C-56-01HG-CNH10-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | P2543-R01-Oct24..4.3.1.2.3.12.6.4.2 Tunneling & Jack UpCCOPL58342 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-56-01HG-CNH10-1090 | C-56-01HG-CNH10-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.6.4.2 Tunneling & Jack UpCCOPL58342 | P2543-R01-Oct24..4.3.1.2.3.12.6.4.3 Re-Instatement of Entry & Exit PitCCOPL58352 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-01HG-CNH10-1220 | C-56-01HG-CNH10-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-56-01HG-CNH10-1000 | C-56-01HG-CNH10-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-01HG-CNH10-1020 | C-56-01HG-CNH10-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-56-HC01-CNM08-1000 | C-56-HC01-CNM08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-HC01-CNM08-1010 | C-56-HC01-CNM08-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-56-HC01-CNM08-1030 | C-56-HC01-CNM08-1040 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-HC01-CNM08-1040 | C-56-HC01-CNM08-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-56-HC01-CNM08-1050 | C-56-HC01-CNM08-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | P2543-R01-Oct24..4.3.1.2.2.12.2.1.2 Tunneling & Jack UpCCOPL57562 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-56-HC01-CNM08-1060 | C-56-HC01-CNM08-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.1.2 Tunneling & Jack UpCCOPL57562 | P2543-R01-Oct24..4.3.1.2.2.12.2.1.2 Tunneling & Jack UpCCOPL57562 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-56-HC01-CNM08-1200 | C-56-HC01-CNM08-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.1.2 Tunneling & Jack UpCCOPL57562 | P2543-R01-Oct24..4.3.1.2.2.12.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57572 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-56-HC01-CNM08-1210 | C-56-HC01-CNM08-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57572 | P2543-R01-Oct24..4.3.1.2.2.12.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57572 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-56-HC01-CNM08-1400 | C-56-HC01-CNM08-1410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57572 | P2543-R01-Oct24..4.3.1.2.2.12.2.1.4 HydrotestingCCOPL57582 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-HC01-CNM08-1410 | C-56-HC01-CNM08-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.1.4 HydrotestingCCOPL57582 | P2543-R01-Oct24..4.3.1.2.2.12.2.1.2 Tunneling & Jack UpCCOPL57562 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-56-HC01-CNM08-1600 | C-56-HC01-CNM08-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.1.2 Tunneling & Jack UpCCOPL57562 | P2543-R01-Oct24..4.3.1.2.2.12.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57592 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-HC01-CNM08-1220 | C-56-HC01-CNM08-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-56-HC01-CNM08-1000 | C-56-HC01-CNM08-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-HC01-CNM08-1020 | C-56-HC01-CNM08-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-56-HC01-CNH05-1000 | C-56-HC01-CNH05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-HC01-CNH05-1010 | C-56-HC01-CNH05-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-56-HC01-CNH05-1030 | C-56-HC01-CNH05-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-HC01-CNH05-1040 | C-56-HC01-CNH05-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-56-HC01-CNH05-1050 | C-56-HC01-CNH05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | P2543-R01-Oct24..4.3.1.2.2.12.8.1.2 Tunneling & Jack UpCCOPL58282 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-56-HC01-CNH05-1060 | C-56-HC01-CNH05-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.2 Tunneling & Jack UpCCOPL58282 | P2543-R01-Oct24..4.3.1.2.2.12.8.1.2 Tunneling & Jack UpCCOPL58282 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-56-HC01-CNH05-1200 | C-56-HC01-CNH05-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.2 Tunneling & Jack UpCCOPL58282 | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-56-HC01-CNH05-1210 | C-56-HC01-CNH05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-56-HC01-CNH05-1070 | C-56-HC01-CNH05-1080 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-HC01-CNH05-1080 | C-56-HC01-CNH05-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | P2543-R01-Oct24..4.3.1.2.2.12.8.1.2 Tunneling & Jack UpCCOPL58282 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-56-HC01-CNH05-1090 | C-56-HC01-CNH05-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.2 Tunneling & Jack UpCCOPL58282 | P2543-R01-Oct24..4.3.1.2.2.12.8.1.3 Re-Instatement of Entry & Exit PitCCOPL58292 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-HC01-CNH05-1220 | C-56-HC01-CNH05-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-56-HC01-CNH05-1000 | C-56-HC01-CNH05-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-HC01-CNH05-1020 | C-56-HC01-CNH05-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-56-HC01-CNM03-1000 | C-56-HC01-CNM03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-HC01-CNM03-1010 | C-56-HC01-CNM03-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-56-HC01-CNM03-1030 | C-56-HC01-CNM03-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-HC01-CNM03-1040 | C-56-HC01-CNM03-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-56-HC01-CNM03-1050 | C-56-HC01-CNM03-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | P2543-R01-Oct24..4.3.1.2.2.12.2.4.2 Tunneling & Jack UpCCOPL57522 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-56-HC01-CNM03-1060 | C-56-HC01-CNM03-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.2 Tunneling & Jack UpCCOPL57522 | P2543-R01-Oct24..4.3.1.2.2.12.2.4.2 Tunneling & Jack UpCCOPL57522 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-56-HC01-CNM03-1200 | C-56-HC01-CNM03-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.2 Tunneling & Jack UpCCOPL57522 | P2543-R01-Oct24..4.3.1.2.2.12.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57532 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-56-HC01-CNM03-1210 | C-56-HC01-CNM03-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57532 | P2543-R01-Oct24..4.3.1.2.2.12.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57532 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-56-HC01-CNM03-1400 | C-56-HC01-CNM03-1410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57532 | P2543-R01-Oct24..4.3.1.2.2.12.2.4.4 HydrotestingCCOPL57542 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-HC01-CNM03-1410 | C-56-HC01-CNM03-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.4 HydrotestingCCOPL57542 | P2543-R01-Oct24..4.3.1.2.2.12.2.4.2 Tunneling & Jack UpCCOPL57522 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-56-HC01-CNM03-1600 | C-56-HC01-CNM03-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.2 Tunneling & Jack UpCCOPL57522 | P2543-R01-Oct24..4.3.1.2.2.12.2.4.5 Re-Instatement of Entry & Exit PitCCOPL57552 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-HC01-CNM03-1220 | C-56-HC01-CNM03-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-56-HC01-CNM03-1000 | C-56-HC01-CNM03-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-HC01-CNM03-1020 | C-56-HC01-CNM03-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-56-HC01-CNH02-1000 | C-56-HC01-CNH02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-HC01-CNH02-1010 | C-56-HC01-CNH02-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-56-HC01-CNH02-1030 | C-56-HC01-CNH02-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-HC01-CNH02-1040 | C-56-HC01-CNH02-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-56-HC01-CNH02-1050 | C-56-HC01-CNH02-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.8.2.2 Tunneling & Jack UpCCOPL58222 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-56-HC01-CNH02-1060 | C-56-HC01-CNH02-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.2 Tunneling & Jack UpCCOPL58222 | P2543-R01-Oct24..4.3.1.2.2.12.8.2.2 Tunneling & Jack UpCCOPL58222 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-56-HC01-CNH02-1200 | C-56-HC01-CNH02-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.2 Tunneling & Jack UpCCOPL58222 | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-56-HC01-CNH02-1210 | C-56-HC01-CNH02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection Carrier Pipe | C-56-HC01-CNH02-1070 | C-56-HC01-CNH02-1080 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | NDT, Coating & Holiday Inspection Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-HC01-CNH02-1080 | C-56-HC01-CNH02-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.8.2.2 Tunneling & Jack UpCCOPL58222 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-56-HC01-CNH02-1090 | C-56-HC01-CNH02-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.2 Tunneling & Jack UpCCOPL58222 | P2543-R01-Oct24..4.3.1.2.2.12.8.2.3 Re-Instatement of Entry & Exit PitCCOPL58232 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-HC01-CNH02-1220 | C-56-HC01-CNH02-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-56-HC01-CNH02-1000 | C-56-HC01-CNH02-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-HC01-CNH02-1020 | C-56-HC01-CNH02-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | Sheet Piling for Driving & Receiving Pit | Installation of Dewatering System for Driving & Receiving Pit | C-56-HC01-CNH01-1000 | C-56-HC01-CNH01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | Driving & Receiving Pit Excavation | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-HC01-CNH01-1010 | C-56-HC01-CNH01-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | Welding & Installation of Bracing in Driving & Receiving Pit | Floor Blinding & French Drain in Driving Pit | C-56-HC01-CNH01-1030 | C-56-HC01-CNH01-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | Floor Blinding & French Drain in Driving Pit | Construction of Front Wall & Thrust Wall in Driving Pit | C-56-HC01-CNH01-1040 | C-56-HC01-CNH01-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | Construction of Front Wall & Thrust Wall in Driving Pit | Construction of Exit Wall with Ring | C-56-HC01-CNH01-1050 | C-56-HC01-CNH01-1060 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.8.3.2 Tunneling & Jack UpCCOPL58162 | Construction of Exit Wall with Ring | Jacking of MTBM & RC Sleeves | C-56-HC01-CNH01-1060 | C-56-HC01-CNH01-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.2 Tunneling & Jack UpCCOPL58162 | P2543-R01-Oct24..4.3.1.2.2.12.8.3.2 Tunneling & Jack UpCCOPL58162 | Jacking of MTBM & RC Sleeves | Filling of Grout between Earth Overcut & RC Sleeve | C-56-HC01-CNH01-1200 | C-56-HC01-CNH01-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.2 Tunneling & Jack UpCCOPL58162 | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | Filling of Grout between Earth Overcut & RC Sleeve | Lowering & Welding of Carrier Pipe | C-56-HC01-CNH01-1210 | C-56-HC01-CNH01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-56-HC01-CNH01-1070 | C-56-HC01-CNH01-1080 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | NDT, Coating & Holiday Inspection of Carrier Pipe | Post Hydrotest/Gauging /Cleaning for NDRC Section | C-56-HC01-CNH01-1080 | C-56-HC01-CNH01-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.8.3.2 Tunneling & Jack UpCCOPL58162 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-56-HC01-CNH01-1090 | C-56-HC01-CNH01-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.2 Tunneling & Jack UpCCOPL58162 | P2543-R01-Oct24..4.3.1.2.2.12.8.3.3 Re-Instatement of Entry & Exit PitCCOPL58172 | Inner Grout b/w Main & RC Pipe | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | C-56-HC01-CNH01-1220 | C-56-HC01-CNH01-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-56-HC01-CNH01-1000 | C-56-HC01-CNH01-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | Installation of Dewatering System for Driving & Receiving Pit | Welding & Installation of Bracing in Driving & Receiving Pit | C-56-HC01-CNH01-1020 | C-56-HC01-CNH01-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | Trench Excavation | Bedding | C-56-01HG-CMA01-1000 | C-56-01HG-CMA01-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | Bedding | Lowering | C-56-01HG-CMA01-1010 | C-56-01HG-CMA01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | Lowering | Section Tie-in Welding | C-56-01HG-CMA01-1020 | C-56-01HG-CMA01-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA01-1030 | C-56-01HG-CMA01-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA01-1040 | C-56-01HG-CMA01-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA01-1050 | C-56-01HG-CMA01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | Holiday Testing | Padding | C-56-01HG-CMA01-1060 | C-56-01HG-CMA01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | Trench Excavation | Bedding | C-56-01HG-CMA02-1000 | C-56-01HG-CMA02-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | Bedding | Lowering | C-56-01HG-CMA02-1010 | C-56-01HG-CMA02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | Lowering | Section Tie-in Welding | C-56-01HG-CMA02-1020 | C-56-01HG-CMA02-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA02-1030 | C-56-01HG-CMA02-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA02-1040 | C-56-01HG-CMA02-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA02-1050 | C-56-01HG-CMA02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | Holiday Testing | Padding | C-56-01HG-CMA02-1060 | C-56-01HG-CMA02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | Trench Excavation | Bedding | C-56-01HG-CMA03-1000 | C-56-01HG-CMA03-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | Bedding | Lowering | C-56-01HG-CMA03-1010 | C-56-01HG-CMA03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | Lowering | Section Tie-in Welding | C-56-01HG-CMA03-1020 | C-56-01HG-CMA03-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA03-1030 | C-56-01HG-CMA03-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA03-1040 | C-56-01HG-CMA03-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA03-1050 | C-56-01HG-CMA03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | Holiday Testing | Padding | C-56-01HG-CMA03-1060 | C-56-01HG-CMA03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | Trench Excavation | Bedding | C-56-01HG-CMA04-1000 | C-56-01HG-CMA04-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | Bedding | Lowering | C-56-01HG-CMA04-1010 | C-56-01HG-CMA04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | Lowering | Section Tie-in Welding | C-56-01HG-CMA04-1020 | C-56-01HG-CMA04-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA04-1030 | C-56-01HG-CMA04-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA04-1040 | C-56-01HG-CMA04-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA04-1050 | C-56-01HG-CMA04-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | Holiday Testing | Padding | C-56-01HG-CMA04-1060 | C-56-01HG-CMA04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | Trench Excavation | Bedding | C-56-01HG-CMA05-1000 | C-56-01HG-CMA05-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | Bedding | Lowering | C-56-01HG-CMA05-1010 | C-56-01HG-CMA05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | Lowering | Section Tie-in Welding | C-56-01HG-CMA05-1020 | C-56-01HG-CMA05-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA05-1030 | C-56-01HG-CMA05-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA05-1040 | C-56-01HG-CMA05-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA05-1050 | C-56-01HG-CMA05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | Holiday Testing | Padding | C-56-01HG-CMA05-1060 | C-56-01HG-CMA05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | Trench Excavation | Bedding | C-56-01HG-CMA06-1000 | C-56-01HG-CMA06-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | Bedding | Lowering | C-56-01HG-CMA06-1010 | C-56-01HG-CMA06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | Lowering | Section Tie-in Welding | C-56-01HG-CMA06-1020 | C-56-01HG-CMA06-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA06-1030 | C-56-01HG-CMA06-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA06-1040 | C-56-01HG-CMA06-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA06-1050 | C-56-01HG-CMA06-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | Holiday Testing | Padding | C-56-01HG-CMA06-1060 | C-56-01HG-CMA06-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | Trench Excavation | Bedding | C-56-01HG-CMA07-1000 | C-56-01HG-CMA07-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | Bedding | Lowering | C-56-01HG-CMA07-1010 | C-56-01HG-CMA07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | Lowering | Section Tie-in Welding | C-56-01HG-CMA07-1020 | C-56-01HG-CMA07-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA07-1030 | C-56-01HG-CMA07-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA07-1040 | C-56-01HG-CMA07-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA07-1050 | C-56-01HG-CMA07-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | Holiday Testing | Padding | C-56-01HG-CMA07-1060 | C-56-01HG-CMA07-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | Trench Excavation | Bedding | C-56-01HG-CMA08-1000 | C-56-01HG-CMA08-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | Bedding | Lowering | C-56-01HG-CMA08-1010 | C-56-01HG-CMA08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | Lowering | Section Tie-in Welding | C-56-01HG-CMA08-1020 | C-56-01HG-CMA08-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA08-1030 | C-56-01HG-CMA08-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA08-1040 | C-56-01HG-CMA08-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA08-1050 | C-56-01HG-CMA08-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | Holiday Testing | Padding | C-56-01HG-CMA08-1060 | C-56-01HG-CMA08-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | Trench Excavation | Bedding | C-56-01HG-CMA09-1000 | C-56-01HG-CMA09-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | Bedding | Lowering | C-56-01HG-CMA09-1010 | C-56-01HG-CMA09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | Lowering | Section Tie-in Welding | C-56-01HG-CMA09-1020 | C-56-01HG-CMA09-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA09-1030 | C-56-01HG-CMA09-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA09-1040 | C-56-01HG-CMA09-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA09-1050 | C-56-01HG-CMA09-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | Holiday Testing | Padding | C-56-01HG-CMA09-1060 | C-56-01HG-CMA09-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | Trench Excavation | Bedding | C-56-01HG-CMA10-1000 | C-56-01HG-CMA10-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | Bedding | Lowering | C-56-01HG-CMA10-1010 | C-56-01HG-CMA10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | Lowering | Section Tie-in Welding | C-56-01HG-CMA10-1020 | C-56-01HG-CMA10-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA10-1030 | C-56-01HG-CMA10-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA10-1040 | C-56-01HG-CMA10-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA10-1050 | C-56-01HG-CMA10-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | Holiday Testing | Padding | C-56-01HG-CMA10-1060 | C-56-01HG-CMA10-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | Trench Excavation | Bedding | C-56-01HG-CMA11-1000 | C-56-01HG-CMA11-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | Bedding | Lowering | C-56-01HG-CMA11-1010 | C-56-01HG-CMA11-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | Lowering | Section Tie-in Welding | C-56-01HG-CMA11-1020 | C-56-01HG-CMA11-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA11-1030 | C-56-01HG-CMA11-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA11-1040 | C-56-01HG-CMA11-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA11-1050 | C-56-01HG-CMA11-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | Holiday Testing | Padding | C-56-01HG-CMA11-1060 | C-56-01HG-CMA11-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | Trench Excavation | Bedding | C-56-01HG-CMA12-1000 | C-56-01HG-CMA12-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | Bedding | Lowering | C-56-01HG-CMA12-1010 | C-56-01HG-CMA12-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | Lowering | Section Tie-in Welding | C-56-01HG-CMA12-1020 | C-56-01HG-CMA12-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA12-1030 | C-56-01HG-CMA12-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA12-1040 | C-56-01HG-CMA12-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA12-1050 | C-56-01HG-CMA12-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | Holiday Testing | Padding | C-56-01HG-CMA12-1060 | C-56-01HG-CMA12-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | Trench Excavation | Bedding | C-56-01HG-CMA13-1000 | C-56-01HG-CMA13-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | Bedding | Lowering | C-56-01HG-CMA13-1010 | C-56-01HG-CMA13-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | Lowering | Section Tie-in Welding | C-56-01HG-CMA13-1020 | C-56-01HG-CMA13-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA13-1030 | C-56-01HG-CMA13-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA13-1040 | C-56-01HG-CMA13-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA13-1050 | C-56-01HG-CMA13-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | Holiday Testing | Padding | C-56-01HG-CMA13-1060 | C-56-01HG-CMA13-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | Trench Excavation | Bedding | C-56-01HG-CMA14-1000 | C-56-01HG-CMA14-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | Bedding | Lowering | C-56-01HG-CMA14-1010 | C-56-01HG-CMA14-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | Lowering | Section Tie-in Welding | C-56-01HG-CMA14-1020 | C-56-01HG-CMA14-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA14-1030 | C-56-01HG-CMA14-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA14-1040 | C-56-01HG-CMA14-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA14-1050 | C-56-01HG-CMA14-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | Holiday Testing | Padding | C-56-01HG-CMA14-1060 | C-56-01HG-CMA14-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | Trench Excavation | Bedding | C-56-01HG-CMA15-1000 | C-56-01HG-CMA15-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | Bedding | Lowering | C-56-01HG-CMA15-1010 | C-56-01HG-CMA15-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | Lowering | Section Tie-in Welding | C-56-01HG-CMA15-1020 | C-56-01HG-CMA15-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA15-1030 | C-56-01HG-CMA15-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA15-1040 | C-56-01HG-CMA15-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA15-1050 | C-56-01HG-CMA15-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | Holiday Testing | Padding | C-56-01HG-CMA15-1060 | C-56-01HG-CMA15-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | Trench Excavation | Bedding | C-56-01HG-CMA23-1000 | C-56-01HG-CMA23-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | Bedding | Lowering | C-56-01HG-CMA23-1010 | C-56-01HG-CMA23-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | Lowering | Section Tie-in Welding | C-56-01HG-CMA23-1020 | C-56-01HG-CMA23-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA23-1030 | C-56-01HG-CMA23-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA23-1040 | C-56-01HG-CMA23-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA23-1050 | C-56-01HG-CMA23-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | Holiday Testing | Padding | C-56-01HG-CMA23-1060 | C-56-01HG-CMA23-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | Trench Excavation | Bedding | C-56-01HG-CMA24-1000 | C-56-01HG-CMA24-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | Bedding | Lowering | C-56-01HG-CMA24-1010 | C-56-01HG-CMA24-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | Lowering | Section Tie-in Welding | C-56-01HG-CMA24-1020 | C-56-01HG-CMA24-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA24-1030 | C-56-01HG-CMA24-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA24-1040 | C-56-01HG-CMA24-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA24-1050 | C-56-01HG-CMA24-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | Holiday Testing | Padding | C-56-01HG-CMA24-1060 | C-56-01HG-CMA24-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | Trench Excavation | Bedding | C-56-01HG-CMA25-1000 | C-56-01HG-CMA25-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | Bedding | Lowering | C-56-01HG-CMA25-1010 | C-56-01HG-CMA25-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | Lowering | Section Tie-in Welding | C-56-01HG-CMA25-1020 | C-56-01HG-CMA25-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA25-1030 | C-56-01HG-CMA25-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA25-1040 | C-56-01HG-CMA25-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA25-1050 | C-56-01HG-CMA25-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | Holiday Testing | Padding | C-56-01HG-CMA25-1060 | C-56-01HG-CMA25-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | Trench Excavation | Bedding | C-56-01HG-CMA26-1000 | C-56-01HG-CMA26-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | Bedding | Lowering | C-56-01HG-CMA26-1010 | C-56-01HG-CMA26-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | Lowering | Section Tie-in Welding | C-56-01HG-CMA26-1020 | C-56-01HG-CMA26-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA26-1030 | C-56-01HG-CMA26-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA26-1040 | C-56-01HG-CMA26-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA26-1050 | C-56-01HG-CMA26-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | Holiday Testing | Padding | C-56-01HG-CMA26-1060 | C-56-01HG-CMA26-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | Trench Excavation | Bedding | C-56-01HG-CMA27-1000 | C-56-01HG-CMA27-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | Bedding | Lowering | C-56-01HG-CMA27-1010 | C-56-01HG-CMA27-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | Lowering | Section Tie-in Welding | C-56-01HG-CMA27-1020 | C-56-01HG-CMA27-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA27-1030 | C-56-01HG-CMA27-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA27-1040 | C-56-01HG-CMA27-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA27-1050 | C-56-01HG-CMA27-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | Holiday Testing | Padding | C-56-01HG-CMA27-1060 | C-56-01HG-CMA27-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | Trench Excavation | Bedding | C-56-01HG-CMA21-1000 | C-56-01HG-CMA21-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | Bedding | Lowering | C-56-01HG-CMA21-1010 | C-56-01HG-CMA21-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | Lowering | Section Tie-in Welding | C-56-01HG-CMA21-1020 | C-56-01HG-CMA21-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA21-1030 | C-56-01HG-CMA21-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA21-1040 | C-56-01HG-CMA21-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA21-1050 | C-56-01HG-CMA21-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | Holiday Testing | Padding | C-56-01HG-CMA21-1060 | C-56-01HG-CMA21-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | Trench Excavation | Bedding | C-56-01HG-CMA22-1000 | C-56-01HG-CMA22-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | Bedding | Lowering | C-56-01HG-CMA22-1010 | C-56-01HG-CMA22-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | Lowering | Section Tie-in Welding | C-56-01HG-CMA22-1020 | C-56-01HG-CMA22-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA22-1030 | C-56-01HG-CMA22-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA22-1040 | C-56-01HG-CMA22-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA22-1050 | C-56-01HG-CMA22-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | Holiday Testing | Padding | C-56-01HG-CMA22-1060 | C-56-01HG-CMA22-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | Trench Excavation | Bedding | C-56-01HG-CMA19-1000 | C-56-01HG-CMA19-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | Bedding | Lowering | C-56-01HG-CMA19-1010 | C-56-01HG-CMA19-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | Lowering | Section Tie-in Welding | C-56-01HG-CMA19-1020 | C-56-01HG-CMA19-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA19-1030 | C-56-01HG-CMA19-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA19-1040 | C-56-01HG-CMA19-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA19-1050 | C-56-01HG-CMA19-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | Holiday Testing | Padding | C-56-01HG-CMA19-1060 | C-56-01HG-CMA19-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | Trench Excavation | Bedding | C-56-01HG-CMA17-1000 | C-56-01HG-CMA17-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | Bedding | Lowering | C-56-01HG-CMA17-1010 | C-56-01HG-CMA17-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | Lowering | Section Tie-in Welding | C-56-01HG-CMA17-1020 | C-56-01HG-CMA17-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA17-1030 | C-56-01HG-CMA17-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA17-1040 | C-56-01HG-CMA17-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA17-1050 | C-56-01HG-CMA17-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | Holiday Testing | Padding | C-56-01HG-CMA17-1060 | C-56-01HG-CMA17-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | Trench Excavation | Bedding | C-56-01HG-CMA20-1000 | C-56-01HG-CMA20-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | Bedding | Lowering | C-56-01HG-CMA20-1010 | C-56-01HG-CMA20-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | Lowering | Section Tie-in Welding | C-56-01HG-CMA20-1020 | C-56-01HG-CMA20-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA20-1030 | C-56-01HG-CMA20-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA20-1040 | C-56-01HG-CMA20-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA20-1050 | C-56-01HG-CMA20-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | Holiday Testing | Padding | C-56-01HG-CMA20-1060 | C-56-01HG-CMA20-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | Trench Excavation | Bedding | C-56-01HG-CMA16-1000 | C-56-01HG-CMA16-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | Bedding | Lowering | C-56-01HG-CMA16-1010 | C-56-01HG-CMA16-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | Lowering | Section Tie-in Welding | C-56-01HG-CMA16-1020 | C-56-01HG-CMA16-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA16-1030 | C-56-01HG-CMA16-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA16-1040 | C-56-01HG-CMA16-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA16-1050 | C-56-01HG-CMA16-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | Holiday Testing | Padding | C-56-01HG-CMA16-1060 | C-56-01HG-CMA16-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | Trench Excavation | Bedding | C-56-01HG-CMA18-1000 | C-56-01HG-CMA18-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | Bedding | Lowering | C-56-01HG-CMA18-1010 | C-56-01HG-CMA18-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | Lowering | Section Tie-in Welding | C-56-01HG-CMA18-1020 | C-56-01HG-CMA18-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CMA18-1030 | C-56-01HG-CMA18-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CMA18-1040 | C-56-01HG-CMA18-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CMA18-1050 | C-56-01HG-CMA18-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | Holiday Testing | Padding | C-56-01HG-CMA18-1060 | C-56-01HG-CMA18-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | Trench Excavation | Bedding | C-56-HC01-CMA02-1000 | C-56-HC01-CMA02-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | Bedding | Lowering | C-56-HC01-CMA02-1010 | C-56-HC01-CMA02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | Lowering | Section Tie-in Welding | C-56-HC01-CMA02-1020 | C-56-HC01-CMA02-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA02-1030 | C-56-HC01-CMA02-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA02-1040 | C-56-HC01-CMA02-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA02-1050 | C-56-HC01-CMA02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | Holiday Testing | Padding | C-56-HC01-CMA02-1060 | C-56-HC01-CMA02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | Trench Excavation | Bedding | C-56-HC01-CMA03-1000 | C-56-HC01-CMA03-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | Bedding | Lowering | C-56-HC01-CMA03-1010 | C-56-HC01-CMA03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | Lowering | Section Tie-in Welding | C-56-HC01-CMA03-1020 | C-56-HC01-CMA03-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA03-1030 | C-56-HC01-CMA03-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA03-1040 | C-56-HC01-CMA03-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA03-1050 | C-56-HC01-CMA03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | Holiday Testing | Padding | C-56-HC01-CMA03-1060 | C-56-HC01-CMA03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | Trench Excavation | Bedding | C-56-HC01-CMA13-1000 | C-56-HC01-CMA13-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | Bedding | Lowering | C-56-HC01-CMA13-1010 | C-56-HC01-CMA13-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | Lowering | Section Tie-in Welding | C-56-HC01-CMA13-1020 | C-56-HC01-CMA13-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA13-1030 | C-56-HC01-CMA13-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA13-1040 | C-56-HC01-CMA13-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA13-1050 | C-56-HC01-CMA13-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | Holiday Testing | Padding | C-56-HC01-CMA13-1060 | C-56-HC01-CMA13-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | Trench Excavation | Bedding | C-56-HC01-CMA09-1000 | C-56-HC01-CMA09-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | Bedding | Lowering | C-56-HC01-CMA09-1010 | C-56-HC01-CMA09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | Lowering | Section Tie-in Welding | C-56-HC01-CMA09-1020 | C-56-HC01-CMA09-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA09-1030 | C-56-HC01-CMA09-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA09-1040 | C-56-HC01-CMA09-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA09-1050 | C-56-HC01-CMA09-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | Holiday Testing | Padding | C-56-HC01-CMA09-1060 | C-56-HC01-CMA09-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | Trench Excavation | Bedding | C-56-HC01-CMA11-1000 | C-56-HC01-CMA11-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | Bedding | Lowering | C-56-HC01-CMA11-1010 | C-56-HC01-CMA11-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | Lowering | Section Tie-in Welding | C-56-HC01-CMA11-1020 | C-56-HC01-CMA11-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA11-1030 | C-56-HC01-CMA11-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA11-1040 | C-56-HC01-CMA11-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA11-1050 | C-56-HC01-CMA11-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | Holiday Testing | Padding | C-56-HC01-CMA11-1060 | C-56-HC01-CMA11-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | Trench Excavation | Bedding | C-56-HC01-CMA14-1000 | C-56-HC01-CMA14-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | Bedding | Lowering | C-56-HC01-CMA14-1010 | C-56-HC01-CMA14-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | Lowering | Section Tie-in Welding | C-56-HC01-CMA14-1020 | C-56-HC01-CMA14-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA14-1030 | C-56-HC01-CMA14-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA14-1040 | C-56-HC01-CMA14-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA14-1050 | C-56-HC01-CMA14-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | Holiday Testing | Padding | C-56-HC01-CMA14-1060 | C-56-HC01-CMA14-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | Trench Excavation | Bedding | C-56-HC01-CMA15-1000 | C-56-HC01-CMA15-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | Bedding | Lowering | C-56-HC01-CMA15-1010 | C-56-HC01-CMA15-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | Lowering | Section Tie-in Welding | C-56-HC01-CMA15-1020 | C-56-HC01-CMA15-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA15-1030 | C-56-HC01-CMA15-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA15-1040 | C-56-HC01-CMA15-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA15-1050 | C-56-HC01-CMA15-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | Holiday Testing | Padding | C-56-HC01-CMA15-1060 | C-56-HC01-CMA15-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | Trench Excavation | Bedding | C-56-HC01-CMA22-1000 | C-56-HC01-CMA22-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | Bedding | Lowering | C-56-HC01-CMA22-1010 | C-56-HC01-CMA22-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | Lowering | Section Tie-in Welding | C-56-HC01-CMA22-1020 | C-56-HC01-CMA22-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA22-1030 | C-56-HC01-CMA22-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA22-1040 | C-56-HC01-CMA22-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA22-1050 | C-56-HC01-CMA22-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | Holiday Testing | Padding | C-56-HC01-CMA22-1060 | C-56-HC01-CMA22-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | Trench Excavation | Bedding | C-56-HC01-CMA04-1000 | C-56-HC01-CMA04-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | Bedding | Lowering | C-56-HC01-CMA04-1010 | C-56-HC01-CMA04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | Lowering | Section Tie-in Welding | C-56-HC01-CMA04-1020 | C-56-HC01-CMA04-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA04-1030 | C-56-HC01-CMA04-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA04-1040 | C-56-HC01-CMA04-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA04-1050 | C-56-HC01-CMA04-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | Holiday Testing | Padding | C-56-HC01-CMA04-1060 | C-56-HC01-CMA04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | Trench Excavation | Bedding | C-56-HC01-CMA16-1000 | C-56-HC01-CMA16-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | Bedding | Lowering | C-56-HC01-CMA16-1010 | C-56-HC01-CMA16-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | Lowering | Section Tie-in Welding | C-56-HC01-CMA16-1020 | C-56-HC01-CMA16-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA16-1030 | C-56-HC01-CMA16-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA16-1040 | C-56-HC01-CMA16-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA16-1050 | C-56-HC01-CMA16-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | Holiday Testing | Padding | C-56-HC01-CMA16-1060 | C-56-HC01-CMA16-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | Trench Excavation | Bedding | C-56-HC01-CMA18-1000 | C-56-HC01-CMA18-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | Bedding | Lowering | C-56-HC01-CMA18-1010 | C-56-HC01-CMA18-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | Lowering | Section Tie-in Welding | C-56-HC01-CMA18-1020 | C-56-HC01-CMA18-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA18-1030 | C-56-HC01-CMA18-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA18-1040 | C-56-HC01-CMA18-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA18-1050 | C-56-HC01-CMA18-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | Holiday Testing | Padding | C-56-HC01-CMA18-1060 | C-56-HC01-CMA18-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | Trench Excavation | Bedding | C-56-HC01-CMA20-1000 | C-56-HC01-CMA20-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | Bedding | Lowering | C-56-HC01-CMA20-1010 | C-56-HC01-CMA20-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | Lowering | Section Tie-in Welding | C-56-HC01-CMA20-1020 | C-56-HC01-CMA20-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA20-1030 | C-56-HC01-CMA20-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA20-1040 | C-56-HC01-CMA20-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA20-1050 | C-56-HC01-CMA20-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | Holiday Testing | Padding | C-56-HC01-CMA20-1060 | C-56-HC01-CMA20-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | Trench Excavation | Bedding | C-56-HC01-CMA23-1000 | C-56-HC01-CMA23-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | Bedding | Lowering | C-56-HC01-CMA23-1010 | C-56-HC01-CMA23-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | Lowering | Section Tie-in Welding | C-56-HC01-CMA23-1020 | C-56-HC01-CMA23-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA23-1030 | C-56-HC01-CMA23-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA23-1040 | C-56-HC01-CMA23-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA23-1050 | C-56-HC01-CMA23-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | Holiday Testing | Padding | C-56-HC01-CMA23-1060 | C-56-HC01-CMA23-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | Trench Excavation | Bedding | C-56-HC01-CMA28-1000 | C-56-HC01-CMA28-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | Bedding | Lowering | C-56-HC01-CMA28-1010 | C-56-HC01-CMA28-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | Lowering | Section Tie-in Welding | C-56-HC01-CMA28-1020 | C-56-HC01-CMA28-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA28-1030 | C-56-HC01-CMA28-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA28-1040 | C-56-HC01-CMA28-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA28-1050 | C-56-HC01-CMA28-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | Holiday Testing | Padding | C-56-HC01-CMA28-1060 | C-56-HC01-CMA28-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | Trench Excavation | Bedding | C-56-HC01-CMA29-1000 | C-56-HC01-CMA29-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | Bedding | Lowering | C-56-HC01-CMA29-1010 | C-56-HC01-CMA29-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | Lowering | Section Tie-in Welding | C-56-HC01-CMA29-1020 | C-56-HC01-CMA29-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA29-1030 | C-56-HC01-CMA29-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA29-1040 | C-56-HC01-CMA29-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA29-1050 | C-56-HC01-CMA29-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | Holiday Testing | Padding | C-56-HC01-CMA29-1060 | C-56-HC01-CMA29-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | Trench Excavation | Bedding | C-56-HC01-CMA27-1000 | C-56-HC01-CMA27-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | Bedding | Lowering | C-56-HC01-CMA27-1010 | C-56-HC01-CMA27-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | Lowering | Section Tie-in Welding | C-56-HC01-CMA27-1020 | C-56-HC01-CMA27-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA27-1030 | C-56-HC01-CMA27-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA27-1040 | C-56-HC01-CMA27-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA27-1050 | C-56-HC01-CMA27-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | Holiday Testing | Padding | C-56-HC01-CMA27-1060 | C-56-HC01-CMA27-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | Trench Excavation | Bedding | C-56-HC01-CMA24-1000 | C-56-HC01-CMA24-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | Bedding | Lowering | C-56-HC01-CMA24-1010 | C-56-HC01-CMA24-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | Lowering | Section Tie-in Welding | C-56-HC01-CMA24-1020 | C-56-HC01-CMA24-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA24-1030 | C-56-HC01-CMA24-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA24-1040 | C-56-HC01-CMA24-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA24-1050 | C-56-HC01-CMA24-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | Holiday Testing | Padding | C-56-HC01-CMA24-1060 | C-56-HC01-CMA24-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | Trench Excavation | Bedding | C-56-HC01-CMA25-1000 | C-56-HC01-CMA25-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | Bedding | Lowering | C-56-HC01-CMA25-1010 | C-56-HC01-CMA25-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | Lowering | Section Tie-in Welding | C-56-HC01-CMA25-1020 | C-56-HC01-CMA25-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA25-1030 | C-56-HC01-CMA25-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA25-1040 | C-56-HC01-CMA25-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA25-1050 | C-56-HC01-CMA25-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | Holiday Testing | Padding | C-56-HC01-CMA25-1060 | C-56-HC01-CMA25-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | Trench Excavation | Bedding | C-56-HC01-CMA26-1000 | C-56-HC01-CMA26-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | Bedding | Lowering | C-56-HC01-CMA26-1010 | C-56-HC01-CMA26-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | Lowering | Section Tie-in Welding | C-56-HC01-CMA26-1020 | C-56-HC01-CMA26-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA26-1030 | C-56-HC01-CMA26-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA26-1040 | C-56-HC01-CMA26-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA26-1050 | C-56-HC01-CMA26-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | Holiday Testing | Padding | C-56-HC01-CMA26-1060 | C-56-HC01-CMA26-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | Trench Excavation | Bedding | C-56-HC01-CMA17-1000 | C-56-HC01-CMA17-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | Bedding | Lowering | C-56-HC01-CMA17-1010 | C-56-HC01-CMA17-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | Lowering | Section Tie-in Welding | C-56-HC01-CMA17-1020 | C-56-HC01-CMA17-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA17-1030 | C-56-HC01-CMA17-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA17-1040 | C-56-HC01-CMA17-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA17-1050 | C-56-HC01-CMA17-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | Holiday Testing | Padding | C-56-HC01-CMA17-1060 | C-56-HC01-CMA17-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | Trench Excavation | Bedding | C-56-HC01-CMA19-1000 | C-56-HC01-CMA19-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | Bedding | Lowering | C-56-HC01-CMA19-1010 | C-56-HC01-CMA19-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | Lowering | Section Tie-in Welding | C-56-HC01-CMA19-1020 | C-56-HC01-CMA19-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA19-1030 | C-56-HC01-CMA19-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA19-1040 | C-56-HC01-CMA19-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA19-1050 | C-56-HC01-CMA19-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | Holiday Testing | Padding | C-56-HC01-CMA19-1060 | C-56-HC01-CMA19-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | Trench Excavation | Bedding | C-56-HC01-CMA21-1000 | C-56-HC01-CMA21-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | Bedding | Lowering | C-56-HC01-CMA21-1010 | C-56-HC01-CMA21-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | Lowering | Section Tie-in Welding | C-56-HC01-CMA21-1020 | C-56-HC01-CMA21-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA21-1030 | C-56-HC01-CMA21-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA21-1040 | C-56-HC01-CMA21-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA21-1050 | C-56-HC01-CMA21-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | Holiday Testing | Padding | C-56-HC01-CMA21-1060 | C-56-HC01-CMA21-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | Trench Excavation | Bedding | C-56-HC01-CMA30-1000 | C-56-HC01-CMA30-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | Bedding | Lowering | C-56-HC01-CMA30-1010 | C-56-HC01-CMA30-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | Lowering | Section Tie-in Welding | C-56-HC01-CMA30-1020 | C-56-HC01-CMA30-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA30-1030 | C-56-HC01-CMA30-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA30-1040 | C-56-HC01-CMA30-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA30-1050 | C-56-HC01-CMA30-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | Holiday Testing | Padding | C-56-HC01-CMA30-1060 | C-56-HC01-CMA30-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | Trench Excavation | Bedding | C-56-HC01-CMA08-1000 | C-56-HC01-CMA08-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | Bedding | Lowering | C-56-HC01-CMA08-1010 | C-56-HC01-CMA08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | Lowering | Section Tie-in Welding | C-56-HC01-CMA08-1020 | C-56-HC01-CMA08-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA08-1030 | C-56-HC01-CMA08-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA08-1040 | C-56-HC01-CMA08-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA08-1050 | C-56-HC01-CMA08-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | Holiday Testing | Padding | C-56-HC01-CMA08-1060 | C-56-HC01-CMA08-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | Trench Excavation | Bedding | C-56-HC01-CMA10-1000 | C-56-HC01-CMA10-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | Bedding | Lowering | C-56-HC01-CMA10-1010 | C-56-HC01-CMA10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA10-1030 | C-56-HC01-CMA10-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA10-1040 | C-56-HC01-CMA10-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA10-1050 | C-56-HC01-CMA10-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | Holiday Testing | Padding | C-56-HC01-CMA10-1060 | C-56-HC01-CMA10-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | Trench Excavation | Bedding | C-56-HC01-CMA31-1000 | C-56-HC01-CMA31-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | Bedding | Lowering | C-56-HC01-CMA31-1010 | C-56-HC01-CMA31-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | Lowering | Section Tie-in Welding | C-56-HC01-CMA31-1020 | C-56-HC01-CMA31-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA31-1030 | C-56-HC01-CMA31-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA31-1040 | C-56-HC01-CMA31-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA31-1050 | C-56-HC01-CMA31-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | Holiday Testing | Padding | C-56-HC01-CMA31-1060 | C-56-HC01-CMA31-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | Trench Excavation | Bedding | C-56-HC01-CMA05-1000 | C-56-HC01-CMA05-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | Bedding | Lowering | C-56-HC01-CMA05-1010 | C-56-HC01-CMA05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | Lowering | Section Tie-in Welding | C-56-HC01-CMA05-1020 | C-56-HC01-CMA05-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA05-1030 | C-56-HC01-CMA05-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA05-1040 | C-56-HC01-CMA05-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA05-1050 | C-56-HC01-CMA05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | Holiday Testing | Padding | C-56-HC01-CMA05-1060 | C-56-HC01-CMA05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | Trench Excavation | Bedding | C-56-HC01-CMA12-1000 | C-56-HC01-CMA12-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | Bedding | Lowering | C-56-HC01-CMA12-1010 | C-56-HC01-CMA12-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | Lowering | Section Tie-in Welding | C-56-HC01-CMA12-1020 | C-56-HC01-CMA12-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA12-1030 | C-56-HC01-CMA12-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA12-1040 | C-56-HC01-CMA12-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA12-1050 | C-56-HC01-CMA12-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | Holiday Testing | Padding | C-56-HC01-CMA12-1060 | C-56-HC01-CMA12-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | Trench Excavation | Bedding | C-56-HC01-CMA06-1000 | C-56-HC01-CMA06-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | Bedding | Lowering | C-56-HC01-CMA06-1010 | C-56-HC01-CMA06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | Lowering | Section Tie-in Welding | C-56-HC01-CMA06-1020 | C-56-HC01-CMA06-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA06-1030 | C-56-HC01-CMA06-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA06-1040 | C-56-HC01-CMA06-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA06-1050 | C-56-HC01-CMA06-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | Holiday Testing | Padding | C-56-HC01-CMA06-1060 | C-56-HC01-CMA06-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | Trench Excavation | Bedding | C-56-HC01-CMA01-1000 | C-56-HC01-CMA01-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | Bedding | Lowering | C-56-HC01-CMA01-1010 | C-56-HC01-CMA01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | Lowering | Section Tie-in Welding | C-56-HC01-CMA01-1020 | C-56-HC01-CMA01-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA01-1030 | C-56-HC01-CMA01-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA01-1040 | C-56-HC01-CMA01-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA01-1050 | C-56-HC01-CMA01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | Holiday Testing | Padding | C-56-HC01-CMA01-1060 | C-56-HC01-CMA01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | Trench Excavation | Bedding | C-56-HC01-CMA07-1000 | C-56-HC01-CMA07-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | Bedding | Lowering | C-56-HC01-CMA07-1010 | C-56-HC01-CMA07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CMA07-1030 | C-56-HC01-CMA07-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CMA07-1040 | C-56-HC01-CMA07-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CMA07-1050 | C-56-HC01-CMA07-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | Holiday Testing | Padding | C-56-HC01-CMA07-1060 | C-56-HC01-CMA07-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | Trench Excavation | Bedding | C-56-01HG-CME01-1000 | C-56-01HG-CME01-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | Bedding | Lowering | C-56-01HG-CME01-1010 | C-56-01HG-CME01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | Lowering | Section Tie-in Welding | C-56-01HG-CME01-1020 | C-56-01HG-CME01-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CME01-1030 | C-56-01HG-CME01-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME01-1040 | C-56-01HG-CME01-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CME01-1050 | C-56-01HG-CME01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | Holiday Testing | Padding & Back Filling | C-56-01HG-CME01-1060 | C-56-01HG-CME01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | Trench Excavation | Bedding | C-56-01HG-CME02-1000 | C-56-01HG-CME02-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | Bedding | Lowering | C-56-01HG-CME02-1010 | C-56-01HG-CME02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | Lowering | Section Tie-in Welding | C-56-01HG-CME02-1020 | C-56-01HG-CME02-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CME02-1030 | C-56-01HG-CME02-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME02-1040 | C-56-01HG-CME02-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CME02-1050 | C-56-01HG-CME02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | Holiday Testing | Padding & Back Filling | C-56-01HG-CME02-1060 | C-56-01HG-CME02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | Trench Excavation | Bedding | C-56-01HG-CME03-1000 | C-56-01HG-CME03-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | Bedding | Lowering | C-56-01HG-CME03-1010 | C-56-01HG-CME03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | Lowering | Section Tie-in Welding | C-56-01HG-CME03-1020 | C-56-01HG-CME03-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CME03-1030 | C-56-01HG-CME03-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME03-1040 | C-56-01HG-CME03-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CME03-1050 | C-56-01HG-CME03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | Holiday Testing | Padding & Back Filling | C-56-01HG-CME03-1060 | C-56-01HG-CME03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | Trench Excavation | Bedding | C-56-01HG-CME04-1000 | C-56-01HG-CME04-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | Bedding | Lowering | C-56-01HG-CME04-1010 | C-56-01HG-CME04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | Lowering | Section Tie-in Welding | C-56-01HG-CME04-1020 | C-56-01HG-CME04-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CME04-1030 | C-56-01HG-CME04-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME04-1040 | C-56-01HG-CME04-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CME04-1050 | C-56-01HG-CME04-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | Holiday Testing | Padding & Back Filling | C-56-01HG-CME04-1060 | C-56-01HG-CME04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | Trench Excavation | Bedding | C-56-01HG-CME05-1000 | C-56-01HG-CME05-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | Bedding | Lowering | C-56-01HG-CME05-1010 | C-56-01HG-CME05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | Lowering | Section Tie-in Welding | C-56-01HG-CME05-1020 | C-56-01HG-CME05-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CME05-1030 | C-56-01HG-CME05-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME05-1040 | C-56-01HG-CME05-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CME05-1050 | C-56-01HG-CME05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | Holiday Testing | Padding & Back Filling | C-56-01HG-CME05-1060 | C-56-01HG-CME05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | Trench Excavation | Bedding | C-56-01HG-CME06-1000 | C-56-01HG-CME06-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | Bedding | Lowering | C-56-01HG-CME06-1010 | C-56-01HG-CME06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | Lowering | Section Tie-in Welding | C-56-01HG-CME06-1020 | C-56-01HG-CME06-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CME06-1030 | C-56-01HG-CME06-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME06-1040 | C-56-01HG-CME06-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CME06-1050 | C-56-01HG-CME06-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | Holiday Testing | Padding & Back Filling | C-56-01HG-CME06-1060 | C-56-01HG-CME06-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | Trench Excavation | Bedding | C-56-01HG-CME07-1000 | C-56-01HG-CME07-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | Bedding | Lowering | C-56-01HG-CME07-1010 | C-56-01HG-CME07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | Lowering | Section Tie-in Welding | C-56-01HG-CME07-1020 | C-56-01HG-CME07-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CME07-1030 | C-56-01HG-CME07-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME07-1040 | C-56-01HG-CME07-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CME07-1050 | C-56-01HG-CME07-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | Holiday Testing | Padding & Back Filling | C-56-01HG-CME07-1060 | C-56-01HG-CME07-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | Trench Excavation | Bedding | C-56-01HG-CME08-1000 | C-56-01HG-CME08-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | Bedding | Lowering | C-56-01HG-CME08-1010 | C-56-01HG-CME08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | Lowering | Section Tie-in Welding | C-56-01HG-CME08-1020 | C-56-01HG-CME08-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CME08-1030 | C-56-01HG-CME08-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME08-1040 | C-56-01HG-CME08-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CME08-1050 | C-56-01HG-CME08-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | Holiday Testing | Padding & Back Filling | C-56-01HG-CME08-1060 | C-56-01HG-CME08-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | Trench Excavation | Bedding | C-56-01HG-CME09-1000 | C-56-01HG-CME09-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | Bedding | Lowering | C-56-01HG-CME09-1010 | C-56-01HG-CME09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | Lowering | Section Tie-in Welding | C-56-01HG-CME09-1020 | C-56-01HG-CME09-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CME09-1030 | C-56-01HG-CME09-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME09-1040 | C-56-01HG-CME09-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CME09-1050 | C-56-01HG-CME09-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | Holiday Testing | Padding & Back Filling | C-56-01HG-CME09-1060 | C-56-01HG-CME09-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | Trench Excavation | Bedding | C-56-01HG-CME10-1000 | C-56-01HG-CME10-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | Bedding | Lowering | C-56-01HG-CME10-1010 | C-56-01HG-CME10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | Lowering | Section Tie-in Welding | C-56-01HG-CME10-1020 | C-56-01HG-CME10-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CME10-1030 | C-56-01HG-CME10-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME10-1040 | C-56-01HG-CME10-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CME10-1050 | C-56-01HG-CME10-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | Holiday Testing | Padding & Back Filling | C-56-01HG-CME10-1060 | C-56-01HG-CME10-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | Trench Excavation | Bedding | C-56-HC01-CME01-1000 | C-56-HC01-CME01-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | Bedding | Lowering | C-56-HC01-CME01-1010 | C-56-HC01-CME01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | Lowering | Section Tie-in Welding | C-56-HC01-CME01-1020 | C-56-HC01-CME01-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME01-1030 | C-56-HC01-CME01-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME01-1040 | C-56-HC01-CME01-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME01-1050 | C-56-HC01-CME01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | Holiday Testing | Padding & Back Filling | C-56-HC01-CME01-1060 | C-56-HC01-CME01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | Trench Excavation | Bedding | C-56-HC01-CME02-1000 | C-56-HC01-CME02-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | Bedding | Lowering | C-56-HC01-CME02-1010 | C-56-HC01-CME02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | Lowering | Section Tie-in Welding | C-56-HC01-CME02-1020 | C-56-HC01-CME02-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME02-1030 | C-56-HC01-CME02-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME02-1040 | C-56-HC01-CME02-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME02-1050 | C-56-HC01-CME02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | Holiday Testing | Padding & Back Filling | C-56-HC01-CME02-1060 | C-56-HC01-CME02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | Trench Excavation | Bedding | C-56-HC01-CME03-1000 | C-56-HC01-CME03-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | Bedding | Lowering | C-56-HC01-CME03-1010 | C-56-HC01-CME03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | Lowering | Section Tie-in Welding | C-56-HC01-CME03-1020 | C-56-HC01-CME03-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME03-1030 | C-56-HC01-CME03-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME03-1040 | C-56-HC01-CME03-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME03-1050 | C-56-HC01-CME03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | Holiday Testing | Padding & Back Filling | C-56-HC01-CME03-1060 | C-56-HC01-CME03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | Trench Excavation | Bedding | C-56-HC01-CME04-1000 | C-56-HC01-CME04-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | Bedding | Lowering | C-56-HC01-CME04-1010 | C-56-HC01-CME04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | Lowering | Section Tie-in Welding | C-56-HC01-CME04-1020 | C-56-HC01-CME04-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME04-1030 | C-56-HC01-CME04-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME04-1040 | C-56-HC01-CME04-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME04-1050 | C-56-HC01-CME04-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | Holiday Testing | Padding & Back Filling | C-56-HC01-CME04-1060 | C-56-HC01-CME04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | Trench Excavation | Bedding | C-56-HC01-CME05-1000 | C-56-HC01-CME05-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | Bedding | Lowering | C-56-HC01-CME05-1010 | C-56-HC01-CME05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | Lowering | Section Tie-in Welding | C-56-HC01-CME05-1020 | C-56-HC01-CME05-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME05-1030 | C-56-HC01-CME05-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME05-1040 | C-56-HC01-CME05-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME05-1050 | C-56-HC01-CME05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | Holiday Testing | Padding & Back Filling | C-56-HC01-CME05-1060 | C-56-HC01-CME05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | Trench Excavation | Bedding | C-56-HC01-CME06-1000 | C-56-HC01-CME06-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | Bedding | Lowering | C-56-HC01-CME06-1010 | C-56-HC01-CME06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | Lowering | Section Tie-in Welding | C-56-HC01-CME06-1020 | C-56-HC01-CME06-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME06-1030 | C-56-HC01-CME06-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME06-1040 | C-56-HC01-CME06-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME06-1050 | C-56-HC01-CME06-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | Holiday Testing | Padding & Back Filling | C-56-HC01-CME06-1060 | C-56-HC01-CME06-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | Trench Excavation | Bedding | C-56-HC01-CME07-1000 | C-56-HC01-CME07-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | Bedding | Lowering | C-56-HC01-CME07-1010 | C-56-HC01-CME07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | Lowering | Section Tie-in Welding | C-56-HC01-CME07-1020 | C-56-HC01-CME07-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME07-1030 | C-56-HC01-CME07-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME07-1040 | C-56-HC01-CME07-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME07-1050 | C-56-HC01-CME07-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | Holiday Testing | Padding & Back Filling | C-56-HC01-CME07-1060 | C-56-HC01-CME07-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | Trench Excavation | Bedding | C-56-HC01-CME08-1000 | C-56-HC01-CME08-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | Bedding | Lowering | C-56-HC01-CME08-1010 | C-56-HC01-CME08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | Lowering | Section Tie-in Welding | C-56-HC01-CME08-1020 | C-56-HC01-CME08-1030 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME08-1030 | C-56-HC01-CME08-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME08-1040 | C-56-HC01-CME08-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME08-1050 | C-56-HC01-CME08-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | Holiday Testing | Padding & Back Filling | C-56-HC01-CME08-1060 | C-56-HC01-CME08-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | Trench Excavation | Bedding | C-56-HC01-CME09-1000 | C-56-HC01-CME09-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | Bedding | Lowering | C-56-HC01-CME09-1010 | C-56-HC01-CME09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | Lowering | Section Tie-in Welding | C-56-HC01-CME09-1020 | C-56-HC01-CME09-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME09-1030 | C-56-HC01-CME09-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME09-1040 | C-56-HC01-CME09-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME09-1050 | C-56-HC01-CME09-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | Holiday Testing | Padding & Back Filling | C-56-HC01-CME09-1060 | C-56-HC01-CME09-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | Trench Excavation | Bedding | C-56-HC01-CME10-1000 | C-56-HC01-CME10-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | Bedding | Lowering | C-56-HC01-CME10-1010 | C-56-HC01-CME10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | Lowering | Section Tie-in Welding | C-56-HC01-CME10-1020 | C-56-HC01-CME10-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME10-1030 | C-56-HC01-CME10-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME10-1040 | C-56-HC01-CME10-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME10-1050 | C-56-HC01-CME10-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | Holiday Testing | Padding & Back Filling | C-56-HC01-CME10-1060 | C-56-HC01-CME10-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | Trench Excavation | Bedding | C-56-HC01-CME11-1000 | C-56-HC01-CME11-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | Bedding | Lowering | C-56-HC01-CME11-1010 | C-56-HC01-CME11-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | Lowering | Section Tie-in Welding | C-56-HC01-CME11-1020 | C-56-HC01-CME11-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME11-1030 | C-56-HC01-CME11-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME11-1040 | C-56-HC01-CME11-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME11-1050 | C-56-HC01-CME11-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | Holiday Testing | Padding & Back Filling | C-56-HC01-CME11-1060 | C-56-HC01-CME11-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | Trench Excavation | Bedding | C-56-HC01-CME12-1000 | C-56-HC01-CME12-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | Bedding | Lowering | C-56-HC01-CME12-1010 | C-56-HC01-CME12-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | Lowering | Section Tie-in Welding | C-56-HC01-CME12-1020 | C-56-HC01-CME12-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME12-1030 | C-56-HC01-CME12-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME12-1040 | C-56-HC01-CME12-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME12-1050 | C-56-HC01-CME12-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | Holiday Testing | Padding & Back Filling | C-56-HC01-CME12-1060 | C-56-HC01-CME12-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | Trench Excavation | Bedding | C-56-HC01-CME13-1000 | C-56-HC01-CME13-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | Bedding | Lowering | C-56-HC01-CME13-1010 | C-56-HC01-CME13-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | Lowering | Section Tie-in Welding | C-56-HC01-CME13-1020 | C-56-HC01-CME13-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME13-1030 | C-56-HC01-CME13-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME13-1040 | C-56-HC01-CME13-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME13-1050 | C-56-HC01-CME13-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | Holiday Testing | Padding & Back Filling | C-56-HC01-CME13-1060 | C-56-HC01-CME13-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | Trench Excavation | Bedding | C-56-HC01-CME14-1000 | C-56-HC01-CME14-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | Bedding | Lowering | C-56-HC01-CME14-1010 | C-56-HC01-CME14-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | Lowering | Section Tie-in Welding | C-56-HC01-CME14-1020 | C-56-HC01-CME14-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME14-1030 | C-56-HC01-CME14-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME14-1040 | C-56-HC01-CME14-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME14-1050 | C-56-HC01-CME14-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | Holiday Testing | Padding & Back Filling | C-56-HC01-CME14-1060 | C-56-HC01-CME14-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | Trench Excavation | Bedding | C-56-HC01-CME15-1000 | C-56-HC01-CME15-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | Bedding | Lowering | C-56-HC01-CME15-1010 | C-56-HC01-CME15-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | Lowering | Section Tie-in Welding | C-56-HC01-CME15-1020 | C-56-HC01-CME15-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME15-1030 | C-56-HC01-CME15-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME15-1040 | C-56-HC01-CME15-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME15-1050 | C-56-HC01-CME15-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | Holiday Testing | Padding & Back Filling | C-56-HC01-CME15-1060 | C-56-HC01-CME15-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | Trench Excavation | Bedding | C-56-HC01-CME16-1000 | C-56-HC01-CME16-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | Bedding | Lowering | C-56-HC01-CME16-1010 | C-56-HC01-CME16-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | Lowering | Section Tie-in Welding | C-56-HC01-CME16-1020 | C-56-HC01-CME16-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME16-1030 | C-56-HC01-CME16-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME16-1040 | C-56-HC01-CME16-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME16-1050 | C-56-HC01-CME16-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | Holiday Testing | Padding & Back Filling | C-56-HC01-CME16-1060 | C-56-HC01-CME16-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | Earth Works for Equipment Foundations & Hard Stand Area | Earth Works for Pipe Support Foundations | C-52-598-06-CI-1010 | C-52-598-06-CI-1020 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | Earth Works for Pipe Support Foundations | Earth Works for Field Instrument Foundations | C-52-598-06-CI-1020 | C-52-598-06-CI-1030 | SS | Not Started | Not Started | 6
P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | Earth Works for Field Instrument Foundations | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-598-06-CI-1030 | C-52-598-06-CI-1040 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | Earth Works for Access Platforms & Misc. Structural Foundations | Earth Works for Light Pole, Fence & Gates Foundation | C-52-598-06-CI-1040 | C-52-598-06-CI-1050 | SS | Not Started | Not Started | 6
P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | P2543-R01-Oct24..4.3.1.3.9.21.1.2 Compaction & TestingCCOB152C33 | Earth Works for Equipment Foundations & Hard Stand Area | Compaction & Testing for Equipment Foundations & Hard Stand Area | C-52-598-06-CI-1010 | C-52-598-06-CI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | P2543-R01-Oct24..4.3.1.3.9.21.1.2 Compaction & TestingCCOB152C33 | Earth Works for Pipe Support Foundations | Compaction & Testing for Pipe Support Foundations | C-52-598-06-CI-1020 | C-52-598-06-CI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | P2543-R01-Oct24..4.3.1.3.9.21.1.2 Compaction & TestingCCOB152C33 | Earth Works for Field Instrument Foundations | Compaction & Testing for Field Instrument Foundations | C-52-598-06-CI-1030 | C-52-598-06-CI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | P2543-R01-Oct24..4.3.1.3.9.21.1.2 Compaction & TestingCCOB152C33 | Earth Works for Access Platforms & Misc. Structural Foundations | Compaction & Testing for Access Platform & Misc. Structural Foundations | C-52-598-06-CI-1040 | C-52-598-06-CI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | P2543-R01-Oct24..4.3.1.3.9.21.1.2 Compaction & TestingCCOB152C33 | Earth Works for Light Pole, Fence & Gates Foundation | Compaction & Testing for Light Pole, Fence & Gates Foundation | C-52-598-06-CI-1050 | C-52-598-06-CI-1240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.2 Compaction & TestingCCOB152C33 | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Compaction & Testing for Equipment Foundations & Hard Stand Area | Concrete Works for Equipment Foundations & Hard Stand Area | C-52-598-06-CI-1200 | C-52-598-06-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.2 Compaction & TestingCCOB152C33 | P2543-R01-Oct24..4.3.1.3.9.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB152C34 | Compaction & Testing for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-52-598-06-CI-1210 | C-52-598-06-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.2 Compaction & TestingCCOB152C33 | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Compaction & Testing for Field Instrument Foundations | Concrete Works for Field Instrument, JB Foundations | C-52-598-06-CI-1220 | C-52-598-06-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.2 Compaction & TestingCCOB152C33 | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Compaction & Testing for Access Platform & Misc. Structural Foundations | Concrete Works for Access Platform & Misc. Structural Foundations | C-52-598-06-CI-1230 | C-52-598-06-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.2 Compaction & TestingCCOB152C33 | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Compaction & Testing for Light Pole, Fence & Gates Foundation | Concrete Works for Light Pole, Fence & Gates Foundation | C-52-598-06-CI-1240 | C-52-598-06-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | P2543-R01-Oct24..4.3.1.3.9.21.1.5 Trenching for CablesCCOB152C38 | Earth Works for Pipe Support Foundations | Electrical & Earthing Cable Trenching | C-52-598-06-CI-1020 | C-52-598-06-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.6 Pipe Supports Fabrication & InstallationCCOB152S52 | P2543-R01-Oct24..4.3.1.3.9.21.6.6 Field InstrumentsCCOB152E96 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-06-CI-2000 | C-52-598-06-EI-2210 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.9.21.1.6 Pipe Supports Fabrication & InstallationCCOB152S52 | P2543-R01-Oct24..4.3.1.3.9.21.1.10 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB152S54 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-06-CI-2000 | C-52-598-06-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.6 Field InstrumentsCCOB152E96 | P2543-R01-Oct24..4.3.1.3.9.21.1.10 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB152S54 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-06-EI-2210 | C-52-598-06-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Concrete Works for Field Instrument, JB Foundations | Installation of Solar Panel Structural Supports | C-52-598-06-CI-1410 | C-52-598-06-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | P2543-R01-Oct24..4.3.1.3.9.21.1.7 Fire Point SheltersCCOB152S50 | Concrete Works for Equipment Foundations & Hard Stand Area | Installation of Fire Point Shelters | C-52-598-06-CI-1400 | C-52-598-06-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.7 Fire Point SheltersCCOB152S50 | P2543-R01-Oct24..4.3.1.3.9.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB152M50 | Installation of Fire Point Shelters | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | C-52-598-06-CI-2400 | C-52-598-06-ME-1000 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Piping Pre-Fabrication | Piping Erection | C-52-598-06-PI-1000 | C-52-598-06-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | P2543-R01-Oct24..4.3.1.3.9.21.4.3 Field Joint Welding & NDTCCOB152P070 | Piping Erection | Field Joint Welding (Including Isolation Joint) | C-52-598-06-PI-1200 | C-52-598-06-PI-1400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.9.21.4.3 Field Joint Welding & NDTCCOB152P070 | P2543-R01-Oct24..4.3.1.3.9.21.4.3 Field Joint Welding & NDTCCOB152P070 | Field Joint Welding (Including Isolation Joint) | NDT & Coating for Field Joint Weld | C-52-598-06-PI-1400 | C-52-598-06-PI-1410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.9.21.4.3 Field Joint Welding & NDTCCOB152P070 | P2543-R01-Oct24..4.3.1.3.9.21.4.4 HydrotestingCCOB152P080 | NDT & Coating for Field Joint Weld | Hydrotesting | C-52-598-06-PI-1410 | C-52-598-06-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.4.4 HydrotestingCCOB152P080 | P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | Hydrotesting | Installation of Valves & GOV | C-52-598-06-PI-1600 | C-52-598-06-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | Installation of Valves & GOV | Final Bolt Torquing/ Re-Instatement | C-52-598-06-PI-1800 | C-52-598-06-PI-2000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | Lowering of Pipeline Section | C-52-598-06-PL-1000 | C-52-598-06-PL-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | Lowering of Pipeline Section | Section Tie-in Welding (Including Barred Tee) | C-52-598-06-PL-1010 | C-52-598-06-PL-1020 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | Section Tie-in Welding (Including Barred Tee) | NDT for Tie-in Joint | C-52-598-06-PL-1020 | C-52-598-06-PL-1030 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | NDT for Tie-in Joint | Ext. Coating for Tie-in Joint | C-52-598-06-PL-1030 | C-52-598-06-PL-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | Ext. Coating for Tie-in Joint | Holiday Testing of Pipeline Section | C-52-598-06-PL-1040 | C-52-598-06-PL-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | Holiday Testing of Pipeline Section | Installation of ROV | C-52-598-06-PL-1050 | C-52-598-06-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | Installation of ROV | Installation of Pig Signaller Pit | C-52-598-06-PL-1060 | C-52-598-06-PL-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | Installation of Pig Signaller Pit | Installation of Pig Signaller | C-52-598-06-PL-1070 | C-52-598-06-PL-1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | Installation of Pig Signaller | Padding & Backfilling | C-52-598-06-PL-1080 | C-52-598-06-PL-1090 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | Holiday Testing of Pipeline Section | Padding & Backfilling | C-52-598-06-PL-1050 | C-52-598-06-PL-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | Installation of ROV | Padding & Backfilling | C-52-598-06-PL-1060 | C-52-598-06-PL-1090 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | Installation of Pig Signaller Pit | Padding & Backfilling | C-52-598-06-PL-1070 | C-52-598-06-PL-1090 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.9.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB152E50 | P2543-R01-Oct24..4.3.1.3.9.21.6.4 RTUCCOB152E76 | Installation of Passive Cooling Shelter | Installation of RTU | C-52-598-06-EI-1000 | C-52-598-06-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.4 RTUCCOB152E76 | P2543-R01-Oct24..4.3.1.3.9.21.6.8 F&G DevicesCCOB152E106 | Installation of RTU | Installation of F&G Panel | C-52-598-06-EI-1600 | C-52-598-06-EI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.8 F&G DevicesCCOB152E106 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Installation of F&G Devices | Loop Checking for Instruments | C-52-598-06-EI-2410 | C-52-598-06-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.6 Field InstrumentsCCOB152E96 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Installation of Field Instruments | Loop Checking for Instruments | C-52-598-06-EI-2200 | C-52-598-06-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.5 Light Pole, Lighting & FixturesCCOB152E86 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Installation of Lighting & Instrument JB's | Loop Checking for Instruments | C-52-598-06-EI-1810 | C-52-598-06-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.4 RTUCCOB152E76 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Installation of RTU | Loop Checking for Instruments | C-52-598-06-EI-1600 | C-52-598-06-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.8 F&G DevicesCCOB152E106 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Installation of F&G Panel | Loop Checking for Instruments | C-52-598-06-EI-2400 | C-52-598-06-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Installation of Solar S/m (Including Panels, UPS & Battery) | Loop Checking for Instruments | C-52-598-06-EI-1200 | C-52-598-06-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Instrument Cable Laying | Loop Checking for Instruments | C-52-598-06-EI-2010 | C-52-598-06-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Loop Checking for Instruments | Glanding & Termination | C-52-598-06-EI-2040 | C-52-598-06-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Electrical & Earthing Cable Laying | Glanding & Termination | C-52-598-06-EI-2000 | C-52-598-06-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Instrument Cable Laying | Glanding & Termination | C-52-598-06-EI-2010 | C-52-598-06-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Instrument Tubing Works | Glanding & Termination | C-52-598-06-EI-2030 | C-52-598-06-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Installation of Solar S/m (Including Panels, UPS & Battery) | Glanding & Termination | C-52-598-06-EI-1200 | C-52-598-06-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.5 Light Pole, Lighting & FixturesCCOB152E86 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Installation of Light Pole, Lighting & Fixtures | Glanding & Termination | C-52-598-06-EI-1800 | C-52-598-06-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB152E50 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Installation of Passive Cooling Shelter | Glanding & Termination | C-52-598-06-EI-1000 | C-52-598-06-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.5 Light Pole, Lighting & FixturesCCOB152E86 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Installation of Lighting & Instrument JB's | Glanding & Termination | C-52-598-06-EI-1810 | C-52-598-06-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.6 Field InstrumentsCCOB152E96 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Installation of Field Instruments | Glanding & Termination | C-52-598-06-EI-2200 | C-52-598-06-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.8 F&G DevicesCCOB152E106 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Installation of F&G Devices | Glanding & Termination | C-52-598-06-EI-2410 | C-52-598-06-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.4 RTUCCOB152E76 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Installation of RTU | Glanding & Termination | C-52-598-06-EI-1600 | C-52-598-06-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.8 F&G DevicesCCOB152E106 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Installation of F&G Panel | Glanding & Termination | C-52-598-06-EI-2400 | C-52-598-06-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | P2543-R01-Oct24..4.3.1.3.9.21.8.1 PIDS SystemCCOB152I40 | Installation of SDH Cabinet | Installation of PIDS/ PLDS System | C-52-598-06-TE-1000 | C-52-598-06-TE-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.8.1 PIDS SystemCCOB152I40 | P2543-R01-Oct24..4.3.1.3.9.21.8.3 CCTV SystemCCOB152I60 | Installation of PIDS/ PLDS System | Installation of CCTV System | C-52-598-06-TE-1200 | C-52-598-06-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.8.3 CCTV SystemCCOB152I60 | P2543-R01-Oct24..4.3.1.3.9.21.8.2 Telephone SystemCCOB152I50 | Installation of CCTV System | Installation of Telephone System | C-52-598-06-TE-1600 | C-52-598-06-TE-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.7.1 CP Anode Bed Installation (subcontract)CCOB152E56 | P2543-R01-Oct24..4.3.1.3.9.21.7.1 CP Anode Bed Installation (subcontract)CCOB152E56 | CP Cable Laying | Installation of CP Test Post | C-52-598-06-CA-1000 | C-52-598-06-CA-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.7.1 CP Anode Bed Installation (subcontract)CCOB152E56 | P2543-R01-Oct24..4.3.1.3.9.21.7.1 CP Anode Bed Installation (subcontract)CCOB152E56 | Installation of CP Test Post | Installation of CP S/m | C-52-598-06-CA-1010 | C-52-598-06-CA-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | Site Survey, Preparation & Grading Works | Earth Works for Equipment Foundations & Hard Stand Area | C-52-598-05-CI-1000 | C-52-598-05-CI-1010 | SS | In Progress | Not Started | 4
P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | Earth Works for Equipment Foundations & Hard Stand Area | Earth Works for Pipe Support Foundations | C-52-598-05-CI-1010 | C-52-598-05-CI-1020 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | Earth Works for Pipe Support Foundations | Earth Works for Field Instrument Foundations | C-52-598-05-CI-1020 | C-52-598-05-CI-1030 | SS | Not Started | Not Started | 6
P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | Earth Works for Field Instrument Foundations | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-598-05-CI-1030 | C-52-598-05-CI-1040 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | Earth Works for Access Platforms & Misc. Structural Foundations | Earth Works for Light Pole, Fence & Gates Foundation | C-52-598-05-CI-1040 | C-52-598-05-CI-1050 | SS | Not Started | Not Started | 6
P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | P2543-R01-Oct24..4.3.1.3.10.21.1.2 Compaction & TestingCCOB252C32 | Earth Works for Equipment Foundations & Hard Stand Area | Compaction & Testing for Equipment Foundations & Hard Stand Area | C-52-598-05-CI-1010 | C-52-598-05-CI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | P2543-R01-Oct24..4.3.1.3.10.21.1.2 Compaction & TestingCCOB252C32 | Earth Works for Pipe Support Foundations | Compaction & Testing for Pipe Support Foundations | C-52-598-05-CI-1020 | C-52-598-05-CI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | P2543-R01-Oct24..4.3.1.3.10.21.1.2 Compaction & TestingCCOB252C32 | Earth Works for Field Instrument Foundations | Compaction & Testing for Field Instrument Foundations | C-52-598-05-CI-1030 | C-52-598-05-CI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | P2543-R01-Oct24..4.3.1.3.10.21.1.2 Compaction & TestingCCOB252C32 | Earth Works for Access Platforms & Misc. Structural Foundations | Compaction & Testing for Access Platform & Misc. Structural Foundations | C-52-598-05-CI-1040 | C-52-598-05-CI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | P2543-R01-Oct24..4.3.1.3.10.21.1.2 Compaction & TestingCCOB252C32 | Earth Works for Light Pole, Fence & Gates Foundation | Compaction & Testing for Light Pole, Fence & Gates Foundation | C-52-598-05-CI-1050 | C-52-598-05-CI-1240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.2 Compaction & TestingCCOB252C32 | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Compaction & Testing for Equipment Foundations & Hard Stand Area | Concrete Works for Equipment Foundations & Hard Stand Area | C-52-598-05-CI-1200 | C-52-598-05-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.2 Compaction & TestingCCOB252C32 | P2543-R01-Oct24..4.3.1.3.10.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB252C33 | Compaction & Testing for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-52-598-05-CI-1210 | C-52-598-05-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.2 Compaction & TestingCCOB252C32 | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Compaction & Testing for Field Instrument Foundations | Concrete Works for Field Instrument, JB Foundations | C-52-598-05-CI-1220 | C-52-598-05-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.2 Compaction & TestingCCOB252C32 | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Compaction & Testing for Access Platform & Misc. Structural Foundations | Concrete Works for Access Platform & Misc. Structural Foundations | C-52-598-05-CI-1230 | C-52-598-05-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.2 Compaction & TestingCCOB252C32 | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Compaction & Testing for Light Pole, Fence & Gates Foundation | Concrete Works for Light Pole, Fence & Gates Foundation | C-52-598-05-CI-1240 | C-52-598-05-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | P2543-R01-Oct24..4.3.1.3.10.21.1.5 Trenching for CablesCCOB252C38 | Earth Works for Pipe Support Foundations | Electrical & Earthing Cable Trenching | C-52-598-05-CI-1020 | C-52-598-05-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | Site Survey, Preparation & Grading Works | Earth Works for Equipment Foundations & Hard Stand Area | C-52-598-04-CI-1000 | C-52-598-04-CI-1010 | SS | Completed | Not Started | 4
P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | Earth Works for Equipment Foundations & Hard Stand Area | Earth Works for Pipe Support Foundations | C-52-598-04-CI-1010 | C-52-598-04-CI-1020 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | P2543-R01-Oct24..4.3.1.3.11.21.1.2 Compaction & TestingCCOB352C32 | Earth Works for Equipment Foundations & Hard Stand Area | Compaction & Testing for Equipment Foundations & Hard Stand Area | C-52-598-04-CI-1010 | C-52-598-04-CI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | P2543-R01-Oct24..4.3.1.3.11.21.1.2 Compaction & TestingCCOB352C32 | Earth Works for Pipe Support Foundations | Compaction & Testing for Pipe Support Foundations | C-52-598-04-CI-1020 | C-52-598-04-CI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | P2543-R01-Oct24..4.3.1.3.11.21.1.2 Compaction & TestingCCOB352C32 | Earth Works for Field Instrument Foundations | Compaction & Testing for Field Instrument Foundations | C-52-598-04-CI-1030 | C-52-598-04-CI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | P2543-R01-Oct24..4.3.1.3.11.21.1.2 Compaction & TestingCCOB352C32 | Earth Works for Access Platforms & Misc. Structural Foundations | Compaction & Testing for Access Platform & Misc. Structural Foundations | C-52-598-04-CI-1040 | C-52-598-04-CI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | P2543-R01-Oct24..4.3.1.3.11.21.1.2 Compaction & TestingCCOB352C32 | Earth Works for Light Pole, Fence & Gates Foundation | Compaction & Testing for Light Pole, Fence & Gates Foundation | C-52-598-04-CI-1050 | C-52-598-04-CI-1240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.2 Compaction & TestingCCOB352C32 | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Compaction & Testing for Equipment Foundations & Hard Stand Area | Concrete Works for Equipment Foundations & Hard Stand Area | C-52-598-04-CI-1200 | C-52-598-04-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.2 Compaction & TestingCCOB352C32 | P2543-R01-Oct24..4.3.1.3.11.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB352C34 | Compaction & Testing for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-52-598-04-CI-1210 | C-52-598-04-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.2 Compaction & TestingCCOB352C32 | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Compaction & Testing for Field Instrument Foundations | Concrete Works for Field Instrument, JB Foundations | C-52-598-04-CI-1220 | C-52-598-04-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.2 Compaction & TestingCCOB352C32 | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Compaction & Testing for Access Platform & Misc. Structural Foundations | Concrete Works for Access Platform & Misc. Structural Foundations | C-52-598-04-CI-1230 | C-52-598-04-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.2 Compaction & TestingCCOB352C32 | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Compaction & Testing for Light Pole, Fence & Gates Foundation | Concrete Works for Light Pole, Fence & Gates Foundation | C-52-598-04-CI-1240 | C-52-598-04-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | P2543-R01-Oct24..4.3.1.3.11.21.1.5 Trenching for CablesCCOB352C38 | Earth Works for Pipe Support Foundations | Electrical & Earthing Cable Trenching | C-52-598-04-CI-1020 | C-52-598-04-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | Site Survey, Preparation & Grading Works | Earth Works for Equipment Foundations & Hard Stand Area | C-52-598-03-CI-1000 | C-52-598-03-CI-1010 | SS | Completed | Not Started | 4
P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | Earth Works for Equipment Foundations & Hard Stand Area | Earth Works for Pipe Support Foundations | C-52-598-03-CI-1010 | C-52-598-03-CI-1020 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | P2543-R01-Oct24..4.3.1.3.12.21.1.2 Compaction & TestingCCOB452C33 | Earth Works for Equipment Foundations & Hard Stand Area | Compaction & Testing for Equipment Foundations & Hard Stand Area | C-52-598-03-CI-1010 | C-52-598-03-CI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | P2543-R01-Oct24..4.3.1.3.12.21.1.2 Compaction & TestingCCOB452C33 | Earth Works for Pipe Support Foundations | Compaction & Testing for Pipe Support Foundations | C-52-598-03-CI-1020 | C-52-598-03-CI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | P2543-R01-Oct24..4.3.1.3.12.21.1.2 Compaction & TestingCCOB452C33 | Earth Works for Field Instrument Foundations | Compaction & Testing for Field Instrument Foundations | C-52-598-03-CI-1030 | C-52-598-03-CI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | P2543-R01-Oct24..4.3.1.3.12.21.1.2 Compaction & TestingCCOB452C33 | Earth Works for Access Platforms & Misc. Structural Foundations | Compaction & Testing for Access Platform & Misc. Structural Foundations | C-52-598-03-CI-1040 | C-52-598-03-CI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | P2543-R01-Oct24..4.3.1.3.12.21.1.2 Compaction & TestingCCOB452C33 | Earth Works for Light Pole, Fence & Gates Foundation | Compaction & Testing for Light Pole, Fence & Gates Foundation | C-52-598-03-CI-1050 | C-52-598-03-CI-1240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.2 Compaction & TestingCCOB452C33 | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Compaction & Testing for Equipment Foundations & Hard Stand Area | Concrete Works for Equipment Foundations & Hard Stand Area | C-52-598-03-CI-1200 | C-52-598-03-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.2 Compaction & TestingCCOB452C33 | P2543-R01-Oct24..4.3.1.3.12.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB452C34.2 | Compaction & Testing for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-52-598-03-CI-1210 | C-52-598-03-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.2 Compaction & TestingCCOB452C33 | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Compaction & Testing for Field Instrument Foundations | Concrete Works for Field Instrument, JB Foundations | C-52-598-03-CI-1220 | C-52-598-03-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.2 Compaction & TestingCCOB452C33 | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Compaction & Testing for Access Platform & Misc. Structural Foundations | Concrete Works for Access Platform & Misc. Structural Foundations | C-52-598-03-CI-1230 | C-52-598-03-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.2 Compaction & TestingCCOB452C33 | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Compaction & Testing for Light Pole, Fence & Gates Foundation | Concrete Works for Light Pole, Fence & Gates Foundation | C-52-598-03-CI-1240 | C-52-598-03-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | P2543-R01-Oct24..4.3.1.3.12.21.1.6 Trenching for CablesCCOB452C39 | Earth Works for Pipe Support Foundations | Electrical & Earthing Cable Trenching | C-52-598-03-CI-1020 | C-52-598-03-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | Earth Works for Equipment Foundations & Hard Stand Area | Earth Works for Pipe Support Foundations | C-52-598-02-CI-1010 | C-52-598-02-CI-1020 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | P2543-R01-Oct24..4.3.1.3.13.21.1.2 Compaction & TestingCCOB552C34 | Earth Works for Equipment Foundations & Hard Stand Area | Compaction & Testing for Equipment Foundations & Hard Stand Area | C-52-598-02-CI-1010 | C-52-598-02-CI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | P2543-R01-Oct24..4.3.1.3.13.21.1.2 Compaction & TestingCCOB552C34 | Earth Works for Pipe Support Foundations | Compaction & Testing for Pipe Support Foundations | C-52-598-02-CI-1020 | C-52-598-02-CI-1210 | FS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | P2543-R01-Oct24..4.3.1.3.13.21.1.2 Compaction & TestingCCOB552C34 | Earth Works for Field Instrument Foundations | Compaction & Testing for Field Instrument Foundations | C-52-598-02-CI-1030 | C-52-598-02-CI-1220 | FS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | P2543-R01-Oct24..4.3.1.3.13.21.1.2 Compaction & TestingCCOB552C34 | Earth Works for Access Platforms & Misc. Structural Foundations | Compaction & Testing for Access Platform & Misc. Structural Foundations | C-52-598-02-CI-1040 | C-52-598-02-CI-1230 | FS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | P2543-R01-Oct24..4.3.1.3.13.21.1.2 Compaction & TestingCCOB552C34 | Earth Works for Light Pole, Fence & Gates Foundation | Compaction & Testing for Light Pole, Fence & Gates Foundation | C-52-598-02-CI-1050 | C-52-598-02-CI-1240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.2 Compaction & TestingCCOB552C34 | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Compaction & Testing for Equipment Foundations & Hard Stand Area | Concrete Works for Equipment Foundations & Hard Stand Area | C-52-598-02-CI-1200 | C-52-598-02-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.2 Compaction & TestingCCOB552C34 | P2543-R01-Oct24..4.3.1.3.13.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB552C37 | Compaction & Testing for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-52-598-02-CI-1210 | C-52-598-02-CI-1600 | FS | Not Started | Not Started | 21
P2543-R01-Oct24..4.3.1.3.13.21.1.2 Compaction & TestingCCOB552C34 | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Compaction & Testing for Field Instrument Foundations | Concrete Works for Field Instrument, JB Foundations | C-52-598-02-CI-1220 | C-52-598-02-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.2 Compaction & TestingCCOB552C34 | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Compaction & Testing for Access Platform & Misc. Structural Foundations | Concrete Works for Access Platform & Misc. Structural Foundations | C-52-598-02-CI-1230 | C-52-598-02-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.2 Compaction & TestingCCOB552C34 | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Compaction & Testing for Light Pole, Fence & Gates Foundation | Concrete Works for Light Pole, Fence & Gates Foundation | C-52-598-02-CI-1240 | C-52-598-02-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | P2543-R01-Oct24..4.3.1.3.13.21.1.5 Trenching for CablesCCOB552C40 | Earth Works for Pipe Support Foundations | Electrical & Earthing Cable Trenching | C-52-598-02-CI-1020 | C-52-598-02-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | Site Survey, Preparation & Grading Works | Earth Works for Equipment Foundations & Hard Stand Area | C-52-598-01-CI-1000 | C-52-598-01-CI-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | Earth Works for Equipment Foundations & Hard Stand Area | Earth Works for Pipe Support Foundations | C-52-598-01-CI-1010 | C-52-598-01-CI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | Earth Works for Pipe Support Foundations | Earth Works for Field Instrument Foundations | C-52-598-01-CI-1020 | C-52-598-01-CI-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | Earth Works for Field Instrument Foundations | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-598-01-CI-1030 | C-52-598-01-CI-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | Earth Works for Access Platforms & Misc. Structural Foundations | Earth Works for Light Pole, Fence & Gates Foundation | C-52-598-01-CI-1040 | C-52-598-01-CI-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | P2543-R01-Oct24..4.3.1.3.14.21.1.2 Compaction & TestingCCOB652C35 | Earth Works for Equipment Foundations & Hard Stand Area | Compaction & Testing for Equipment Foundations & Hard Stand Area | C-52-598-01-CI-1010 | C-52-598-01-CI-1200 | FS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | P2543-R01-Oct24..4.3.1.3.14.21.1.2 Compaction & TestingCCOB652C35 | Earth Works for Pipe Support Foundations | Compaction & Testing for Pipe Support Foundations | C-52-598-01-CI-1020 | C-52-598-01-CI-1210 | FS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | P2543-R01-Oct24..4.3.1.3.14.21.1.2 Compaction & TestingCCOB652C35 | Earth Works for Field Instrument Foundations | Compaction & Testing for Field Instrument Foundations | C-52-598-01-CI-1030 | C-52-598-01-CI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | P2543-R01-Oct24..4.3.1.3.14.21.1.2 Compaction & TestingCCOB652C35 | Earth Works for Access Platforms & Misc. Structural Foundations | Compaction & Testing for Access Platform & Misc. Structural Foundations | C-52-598-01-CI-1040 | C-52-598-01-CI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | P2543-R01-Oct24..4.3.1.3.14.21.1.2 Compaction & TestingCCOB652C35 | Earth Works for Light Pole, Fence & Gates Foundation | Compaction & Testing for Light Pole, Fence & Gates Foundation | C-52-598-01-CI-1050 | C-52-598-01-CI-1240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.2 Compaction & TestingCCOB652C35 | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Compaction & Testing for Equipment Foundations & Hard Stand Area | Concrete Works for Equipment Foundations & Hard Stand Area | C-52-598-01-CI-1200 | C-52-598-01-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.2 Compaction & TestingCCOB652C35 | P2543-R01-Oct24..4.3.1.3.14.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB652C37 | Compaction & Testing for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-52-598-01-CI-1210 | C-52-598-01-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.2 Compaction & TestingCCOB652C35 | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Compaction & Testing for Field Instrument Foundations | Concrete Works for Field Instrument, JB Foundations | C-52-598-01-CI-1220 | C-52-598-01-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.2 Compaction & TestingCCOB652C35 | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Compaction & Testing for Access Platform & Misc. Structural Foundations | Concrete Works for Access Platform & Misc. Structural Foundations | C-52-598-01-CI-1230 | C-52-598-01-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.2 Compaction & TestingCCOB652C35 | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Compaction & Testing for Light Pole, Fence & Gates Foundation | Concrete Works for Light Pole, Fence & Gates Foundation | C-52-598-01-CI-1240 | C-52-598-01-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | P2543-R01-Oct24..4.3.1.3.14.21.1.5 Trenching for CablesCCOB652C40 | Earth Works for Pipe Support Foundations | Electrical & Earthing Cable Trenching | C-52-598-01-CI-1020 | C-52-598-01-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.5 Trenching for CablesCCOB652C40 | P2543-R01-Oct24..4.3.1.3.14.21.1.5 Trenching for CablesCCOB652C40 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-52-598-01-CI-1800 | C-52-598-01-CI-1810 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.10.21.1.6 Pipe Supports Fabrication & InstallationCCOB252S50 | P2543-R01-Oct24..4.3.1.3.10.21.6.8 Field InstrumentsCCOB252E92 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-05-CI-2000 | C-52-598-05-EI-2210 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.10.21.1.6 Pipe Supports Fabrication & InstallationCCOB252S50 | P2543-R01-Oct24..4.3.1.3.10.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB252S51 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-05-CI-2000 | C-52-598-05-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.8 Field InstrumentsCCOB252E92 | P2543-R01-Oct24..4.3.1.3.10.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB252S51 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-05-EI-2210 | C-52-598-05-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.7 Pipe Supports Fabrication & InstallationCCOB352S50 | P2543-R01-Oct24..4.3.1.3.11.21.6.8 Field InstrumentsCCOB352E102 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-04-CI-2000 | C-52-598-04-EI-2210 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.11.21.1.7 Pipe Supports Fabrication & InstallationCCOB352S50 | P2543-R01-Oct24..4.3.1.3.11.21.1.10 Platforms & BollardsCCOB352S52 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-04-CI-2000 | C-52-598-04-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.8 Field InstrumentsCCOB352E102 | P2543-R01-Oct24..4.3.1.3.11.21.1.10 Platforms & BollardsCCOB352S52 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-04-EI-2210 | C-52-598-04-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.5 Pipe Supports Fabrication & InstallationCCOB452S51 | P2543-R01-Oct24..4.3.1.3.12.21.6.6 Field InstrumentsCCOB452E93 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-03-CI-2000 | C-52-598-03-EI-2210 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.12.21.1.5 Pipe Supports Fabrication & InstallationCCOB452S51 | P2543-R01-Oct24..4.3.1.3.12.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB452S52 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-03-CI-2000 | C-52-598-03-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.6 Field InstrumentsCCOB452E93 | P2543-R01-Oct24..4.3.1.3.12.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB452S52 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-03-EI-2210 | C-52-598-03-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.6 Pipe Supports Fabrication & InstallationCCOB552S51 | P2543-R01-Oct24..4.3.1.3.13.21.6.6 Field InstrumentsCCOB552E95 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-02-CI-2000 | C-52-598-02-EI-2210 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.13.21.1.6 Pipe Supports Fabrication & InstallationCCOB552S51 | P2543-R01-Oct24..4.3.1.3.13.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-02-CI-2000 | C-52-598-02-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.6 Field InstrumentsCCOB552E95 | P2543-R01-Oct24..4.3.1.3.13.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-02-EI-2210 | C-52-598-02-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.6 Pipe Supports Fabrication & InstallationCCOB652S52 | P2543-R01-Oct24..4.3.1.3.14.21.6.7 Field InstrumentsCCOB652E95 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-01-CI-2000 | C-52-598-01-EI-2210 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.14.21.1.6 Pipe Supports Fabrication & InstallationCCOB652S52 | P2543-R01-Oct24..4.3.1.3.14.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB652S56 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-01-CI-2000 | C-52-598-01-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.7 Field InstrumentsCCOB652E95 | P2543-R01-Oct24..4.3.1.3.14.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB652S56 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-01-EI-2210 | C-52-598-01-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.4.1 Piping Pre-FabricationCCOB252P050 | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Piping Pre-Fabrication | Piping Erection | C-52-598-05-PI-1000 | C-52-598-05-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | P2543-R01-Oct24..4.3.1.3.10.21.4.3 Field Joint Welding & NDTCCOB252P070 | Piping Erection | Field Joint Welding (Including Isolation Joint) | C-52-598-05-PI-1200 | C-52-598-05-PI-1400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.10.21.4.3 Field Joint Welding & NDTCCOB252P070 | P2543-R01-Oct24..4.3.1.3.10.21.4.3 Field Joint Welding & NDTCCOB252P070 | Field Joint Welding (Including Isolation Joint) | NDT & Coating for Field Joint Weld | C-52-598-05-PI-1400 | C-52-598-05-PI-1410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.10.21.4.3 Field Joint Welding & NDTCCOB252P070 | P2543-R01-Oct24..4.3.1.3.10.21.4.4 HydrotestingCCOB252P080 | NDT & Coating for Field Joint Weld | Hydrotesting | C-52-598-05-PI-1410 | C-52-598-05-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.4.4 HydrotestingCCOB252P080 | P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | Hydrotesting | Installation of Valves & GOV | C-52-598-05-PI-1600 | C-52-598-05-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | Installation of Valves & GOV | Final Bolt Torquing/ Re-Instatement | C-52-598-05-PI-1800 | C-52-598-05-PI-2000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.11.21.4.1 Piping Pre-FabricationCCOB352P051 | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | Piping Pre-Fabrication | Piping Erection | C-52-598-04-PI-1000 | C-52-598-04-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | P2543-R01-Oct24..4.3.1.3.11.21.4.3 Field Joint Welding & NDTCCOB352P071 | Piping Erection | Field Joint Welding (Including Isolation Joint) | C-52-598-04-PI-1200 | C-52-598-04-PI-1400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.11.21.4.3 Field Joint Welding & NDTCCOB352P071 | P2543-R01-Oct24..4.3.1.3.11.21.4.3 Field Joint Welding & NDTCCOB352P071 | Field Joint Welding (Including Isolation Joint) | NDT & Coating for Field Joint Weld | C-52-598-04-PI-1400 | C-52-598-04-PI-1410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.11.21.4.3 Field Joint Welding & NDTCCOB352P071 | P2543-R01-Oct24..4.3.1.3.11.21.4.4 HydrotestingCCOB352P081 | NDT & Coating for Field Joint Weld | Hydrotesting | C-52-598-04-PI-1410 | C-52-598-04-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.4.4 HydrotestingCCOB352P081 | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | Hydrotesting | Installation of Valves & GOV | C-52-598-04-PI-1600 | C-52-598-04-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | P2543-R01-Oct24..4.3.1.3.11.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB352P101 | Installation of Valves & GOV | Final Bolt Torquing/ Re-Instatement | C-52-598-04-PI-1800 | C-52-598-04-PI-2000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.12.21.4.1 Piping Pre-FabricationCCOB452P051 | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | Piping Pre-Fabrication | Piping Erection | C-52-598-03-PI-1000 | C-52-598-03-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | P2543-R01-Oct24..4.3.1.3.12.21.4.3 Field Joint Welding & NDTCCOB452P071 | Piping Erection | Field Joint Welding (Including Isolation Joint) | C-52-598-03-PI-1200 | C-52-598-03-PI-1400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.12.21.4.3 Field Joint Welding & NDTCCOB452P071 | P2543-R01-Oct24..4.3.1.3.12.21.4.3 Field Joint Welding & NDTCCOB452P071 | Field Joint Welding (Including Isolation Joint) | NDT & Coating for Field Joint Weld | C-52-598-03-PI-1400 | C-52-598-03-PI-1410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.12.21.4.3 Field Joint Welding & NDTCCOB452P071 | P2543-R01-Oct24..4.3.1.3.12.21.4.4 HydrotestingCCOB452P081 | NDT & Coating for Field Joint Weld | Hydrotesting | C-52-598-03-PI-1410 | C-52-598-03-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.4.4 HydrotestingCCOB452P081 | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | Hydrotesting | Installation of Valves & GOV | C-52-598-03-PI-1600 | C-52-598-03-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | P2543-R01-Oct24..4.3.1.3.12.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB452P101 | Installation of Valves & GOV | Final Bolt Torquing/ Re-Instatement | C-52-598-03-PI-1800 | C-52-598-03-PI-2000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | P2543-R01-Oct24..4.3.1.3.13.21.4.3 Field Joint Welding & NDTCCOB552P071 | Piping Erection | Field Joint Welding (Including Isolation Joint) | C-52-598-02-PI-1200 | C-52-598-02-PI-1400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.13.21.4.3 Field Joint Welding & NDTCCOB552P071 | P2543-R01-Oct24..4.3.1.3.13.21.4.3 Field Joint Welding & NDTCCOB552P071 | Field Joint Welding (Including Isolation Joint) | NDT & Coating for Field Joint Weld | C-52-598-02-PI-1400 | C-52-598-02-PI-1410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.13.21.4.3 Field Joint Welding & NDTCCOB552P071 | P2543-R01-Oct24..4.3.1.3.13.21.4.4 HydrotestingCCOB552P081 | NDT & Coating for Field Joint Weld | Hydrotesting | C-52-598-02-PI-1410 | C-52-598-02-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.4.4 HydrotestingCCOB552P081 | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | Hydrotesting | Installation of Valves & GOV | C-52-598-02-PI-1600 | C-52-598-02-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | P2543-R01-Oct24..4.3.1.3.13.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB552P101 | Installation of Valves & GOV | Final Bolt Torquing/ Re-Instatement | C-52-598-02-PI-1800 | C-52-598-02-PI-2000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.14.21.4.1 Piping Pre-FabricationCCOB652P052 | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Piping Pre-Fabrication | Piping Erection | C-52-598-01-PI-1000 | C-52-598-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | P2543-R01-Oct24..4.3.1.3.14.21.4.3 Field Joint Welding & NDTCCOB652P072 | Piping Erection | Field Joint Welding (Including Isolation Joint) | C-52-598-01-PI-1200 | C-52-598-01-PI-1400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.14.21.4.3 Field Joint Welding & NDTCCOB652P072 | P2543-R01-Oct24..4.3.1.3.14.21.4.3 Field Joint Welding & NDTCCOB652P072 | Field Joint Welding (Including Isolation Joint) | NDT & Coating for Field Joint Weld | C-52-598-01-PI-1400 | C-52-598-01-PI-1410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.14.21.4.3 Field Joint Welding & NDTCCOB652P072 | P2543-R01-Oct24..4.3.1.3.14.21.4.4 HydrotestingCCOB652P082 | NDT & Coating for Field Joint Weld | Hydrotesting | C-52-598-01-PI-1410 | C-52-598-01-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.4.4 HydrotestingCCOB652P082 | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Hydrotesting | Installation of Valves & GOV | C-52-598-01-PI-1600 | C-52-598-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Installation of Valves & GOV | Final Bolt Torquing/ Re-Instatement | C-52-598-01-PI-1800 | C-52-598-01-PI-2000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | Lowering of Pipeline Section | C-52-598-05-PL-1000 | C-52-598-05-PL-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | Lowering of Pipeline Section | Section Tie-in Welding (Including Barred Tee) | C-52-598-05-PL-1010 | C-52-598-05-PL-1020 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | Section Tie-in Welding (Including Barred Tee) | NDT for Tie-in Joint | C-52-598-05-PL-1020 | C-52-598-05-PL-1030 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | NDT for Tie-in Joint | Ext. Coating for Tie-in Joint | C-52-598-05-PL-1030 | C-52-598-05-PL-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | Ext. Coating for Tie-in Joint | Holiday Testing of Pipeline Section | C-52-598-05-PL-1040 | C-52-598-05-PL-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | Holiday Testing of Pipeline Section | Installation of ROV | C-52-598-05-PL-1050 | C-52-598-05-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | Installation of ROV | Installation of Pig Signaller Pit | C-52-598-05-PL-1060 | C-52-598-05-PL-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | Installation of Pig Signaller Pit | Installation of Pig Signaller | C-52-598-05-PL-1070 | C-52-598-05-PL-1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | Installation of Pig Signaller | Padding & Backfilling | C-52-598-05-PL-1080 | C-52-598-05-PL-1090 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | Holiday Testing of Pipeline Section | Padding & Backfilling | C-52-598-05-PL-1050 | C-52-598-05-PL-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | Installation of ROV | Padding & Backfilling | C-52-598-05-PL-1060 | C-52-598-05-PL-1090 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | Installation of Pig Signaller Pit | Padding & Backfilling | C-52-598-05-PL-1070 | C-52-598-05-PL-1090 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | Lowering of Pipeline Section | C-52-598-04-PL-1000 | C-52-598-04-PL-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | Lowering of Pipeline Section | Section Tie-in Welding (Including Barred Tee) | C-52-598-04-PL-1010 | C-52-598-04-PL-1020 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | Section Tie-in Welding (Including Barred Tee) | NDT for Tie-in Joint | C-52-598-04-PL-1020 | C-52-598-04-PL-1030 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | NDT for Tie-in Joint | Ext. Coating for Tie-in Joint | C-52-598-04-PL-1030 | C-52-598-04-PL-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | Ext. Coating for Tie-in Joint | Holiday Testing of Pipeline Section | C-52-598-04-PL-1040 | C-52-598-04-PL-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | Holiday Testing of Pipeline Section | Installation of ROV | C-52-598-04-PL-1050 | C-52-598-04-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | Installation of ROV | Installation of Pig Signaller Pit | C-52-598-04-PL-1060 | C-52-598-04-PL-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | Installation of Pig Signaller Pit | Installation of Pig Signaller | C-52-598-04-PL-1070 | C-52-598-04-PL-1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | Installation of Pig Signaller | Padding & Backfilling | C-52-598-04-PL-1080 | C-52-598-04-PL-1090 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | Holiday Testing of Pipeline Section | Padding & Backfilling | C-52-598-04-PL-1050 | C-52-598-04-PL-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | Installation of ROV | Padding & Backfilling | C-52-598-04-PL-1060 | C-52-598-04-PL-1090 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | Installation of Pig Signaller Pit | Padding & Backfilling | C-52-598-04-PL-1070 | C-52-598-04-PL-1090 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | Lowering of Pipeline Section | C-52-598-03-PL-1000 | C-52-598-03-PL-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | Lowering of Pipeline Section | Section Tie-in Welding (Including Barred Tee) | C-52-598-03-PL-1010 | C-52-598-03-PL-1020 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | Section Tie-in Welding (Including Barred Tee) | NDT for Tie-in Joint | C-52-598-03-PL-1020 | C-52-598-03-PL-1030 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | NDT for Tie-in Joint | Ext. Coating for Tie-in Joint | C-52-598-03-PL-1030 | C-52-598-03-PL-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | Ext. Coating for Tie-in Joint | Holiday Testing of Pipeline Section | C-52-598-03-PL-1040 | C-52-598-03-PL-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | Holiday Testing of Pipeline Section | Installation of ROV | C-52-598-03-PL-1050 | C-52-598-03-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | Installation of ROV | Installation of Pig Signaller Pit | C-52-598-03-PL-1060 | C-52-598-03-PL-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | Installation of Pig Signaller Pit | Installation of Pig Signaller | C-52-598-03-PL-1070 | C-52-598-03-PL-1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | Installation of Pig Signaller | Padding & Backfilling | C-52-598-03-PL-1080 | C-52-598-03-PL-1090 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | Holiday Testing of Pipeline Section | Padding & Backfilling | C-52-598-03-PL-1050 | C-52-598-03-PL-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | Installation of ROV | Padding & Backfilling | C-52-598-03-PL-1060 | C-52-598-03-PL-1090 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | Installation of Pig Signaller Pit | Padding & Backfilling | C-52-598-03-PL-1070 | C-52-598-03-PL-1090 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | Lowering of Pipeline Section | C-52-598-02-PL-1000 | C-52-598-02-PL-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | Lowering of Pipeline Section | Section Tie-in Welding (Including Barred Tee) | C-52-598-02-PL-1010 | C-52-598-02-PL-1020 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | Section Tie-in Welding (Including Barred Tee) | NDT for Tie-in Joint | C-52-598-02-PL-1020 | C-52-598-02-PL-1030 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | NDT for Tie-in Joint | Ext. Coating for Tie-in Joint | C-52-598-02-PL-1030 | C-52-598-02-PL-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | Ext. Coating for Tie-in Joint | Holiday Testing of Pipeline Section | C-52-598-02-PL-1040 | C-52-598-02-PL-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | Holiday Testing of Pipeline Section | Installation of ROV | C-52-598-02-PL-1050 | C-52-598-02-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | Installation of ROV | Installation of Pig Signaller Pit | C-52-598-02-PL-1060 | C-52-598-02-PL-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | Installation of Pig Signaller Pit | Installation of Pig Signaller | C-52-598-02-PL-1070 | C-52-598-02-PL-1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | Installation of Pig Signaller | Padding & Backfilling | C-52-598-02-PL-1080 | C-52-598-02-PL-1090 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | Holiday Testing of Pipeline Section | Padding & Backfilling | C-52-598-02-PL-1050 | C-52-598-02-PL-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | Installation of ROV | Padding & Backfilling | C-52-598-02-PL-1060 | C-52-598-02-PL-1090 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | Installation of Pig Signaller Pit | Padding & Backfilling | C-52-598-02-PL-1070 | C-52-598-02-PL-1090 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | Lowering of Pipeline Section | C-52-598-01-PL-1000 | C-52-598-01-PL-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | Lowering of Pipeline Section | Section Tie-in Welding (Including Barred Tee) | C-52-598-01-PL-1010 | C-52-598-01-PL-1020 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | Section Tie-in Welding (Including Barred Tee) | NDT for Tie-in Joint | C-52-598-01-PL-1020 | C-52-598-01-PL-1030 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | NDT for Tie-in Joint | Ext. Coating for Tie-in Joint | C-52-598-01-PL-1030 | C-52-598-01-PL-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | Ext. Coating for Tie-in Joint | Holiday Testing of Pipeline Section | C-52-598-01-PL-1040 | C-52-598-01-PL-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | Holiday Testing of Pipeline Section | Installation of ROV | C-52-598-01-PL-1050 | C-52-598-01-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | Installation of ROV | Installation of Pig Signaller Pit | C-52-598-01-PL-1060 | C-52-598-01-PL-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | Installation of Pig Signaller Pit | Installation of Pig Signaller | C-52-598-01-PL-1070 | C-52-598-01-PL-1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | Installation of Pig Signaller | Padding & Backfilling | C-52-598-01-PL-1080 | C-52-598-01-PL-1090 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | Holiday Testing of Pipeline Section | Padding & Backfilling | C-52-598-01-PL-1050 | C-52-598-01-PL-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | Installation of ROV | Padding & Backfilling | C-52-598-01-PL-1060 | C-52-598-01-PL-1090 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | Installation of Pig Signaller Pit | Padding & Backfilling | C-52-598-01-PL-1070 | C-52-598-01-PL-1090 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.10.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB252E50 | P2543-R01-Oct24..4.3.1.3.10.21.6.4 RTUCCOB252E72 | Installation of Passive Cooling Shelter | Installation of RTU | C-52-598-05-EI-1000 | C-52-598-05-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.4 RTUCCOB252E72 | P2543-R01-Oct24..4.3.1.3.10.21.6.6 F&G DevicesCCOB252E102 | Installation of RTU | Installation of F&G Panel | C-52-598-05-EI-1600 | C-52-598-05-EI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.6 F&G DevicesCCOB252E102 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Installation of F&G Devices | Loop Checking for Instruments | C-52-598-05-EI-2410 | C-52-598-05-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.8 Field InstrumentsCCOB252E92 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Installation of Field Instruments | Loop Checking for Instruments | C-52-598-05-EI-2200 | C-52-598-05-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.5 Light Pole, Lighting & FixturesCCOB252E82 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Installation of Lighting & Instrument JB's | Loop Checking for Instruments | C-52-598-05-EI-1810 | C-52-598-05-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.4 RTUCCOB252E72 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Installation of RTU | Loop Checking for Instruments | C-52-598-05-EI-1600 | C-52-598-05-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.6 F&G DevicesCCOB252E102 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Installation of F&G Panel | Loop Checking for Instruments | C-52-598-05-EI-2400 | C-52-598-05-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Installation of Solar S/m (Including Panels, UPS & Battery) | Loop Checking for Instruments | C-52-598-05-EI-1200 | C-52-598-05-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Instrument Cable Laying | Loop Checking for Instruments | C-52-598-05-EI-2010 | C-52-598-05-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Loop Checking for Instruments | Glanding & Termination | C-52-598-05-EI-2040 | C-52-598-05-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Electrical & Earthing Cable Laying | Glanding & Termination | C-52-598-05-EI-2000 | C-52-598-05-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Instrument Cable Laying | Glanding & Termination | C-52-598-05-EI-2010 | C-52-598-05-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Instrument Tubing Works | Glanding & Termination | C-52-598-05-EI-2030 | C-52-598-05-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Installation of Solar S/m (Including Panels, UPS & Battery) | Glanding & Termination | C-52-598-05-EI-1200 | C-52-598-05-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.5 Light Pole, Lighting & FixturesCCOB252E82 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Installation of Light Pole, Lighting & Fixtures | Glanding & Termination | C-52-598-05-EI-1800 | C-52-598-05-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB252E50 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Installation of Passive Cooling Shelter | Glanding & Termination | C-52-598-05-EI-1000 | C-52-598-05-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.5 Light Pole, Lighting & FixturesCCOB252E82 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Installation of Lighting & Instrument JB's | Glanding & Termination | C-52-598-05-EI-1810 | C-52-598-05-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.8 Field InstrumentsCCOB252E92 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Installation of Field Instruments | Glanding & Termination | C-52-598-05-EI-2200 | C-52-598-05-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.6 F&G DevicesCCOB252E102 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Installation of F&G Devices | Glanding & Termination | C-52-598-05-EI-2410 | C-52-598-05-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.4 RTUCCOB252E72 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Installation of RTU | Glanding & Termination | C-52-598-05-EI-1600 | C-52-598-05-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.6 F&G DevicesCCOB252E102 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Installation of F&G Panel | Glanding & Termination | C-52-598-05-EI-2400 | C-52-598-05-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB352E50 | P2543-R01-Oct24..4.3.1.3.11.21.6.4 RTUCCOB352E72 | Installation of Passive Cooling Shelter | Installation of RTU | C-52-598-04-EI-1000 | C-52-598-04-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.4 RTUCCOB352E72 | P2543-R01-Oct24..4.3.1.3.11.21.6.6 F&G DevicesCCOB352E92 | Installation of RTU | Installation of F&G Panel | C-52-598-04-EI-1600 | C-52-598-04-EI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.6 F&G DevicesCCOB352E92 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Installation of F&G Devices | Loop Checking for Instruments | C-52-598-04-EI-2410 | C-52-598-04-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.8 Field InstrumentsCCOB352E102 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Installation of Field Instruments | Loop Checking for Instruments | C-52-598-04-EI-2200 | C-52-598-04-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.5 Light Pole, Lighting & FixturesCCOB352E82 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Installation of Lighting & Instrument JB's | Loop Checking for Instruments | C-52-598-04-EI-1810 | C-52-598-04-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.4 RTUCCOB352E72 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Installation of RTU | Loop Checking for Instruments | C-52-598-04-EI-1600 | C-52-598-04-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.6 F&G DevicesCCOB352E92 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Installation of F&G Panel | Loop Checking for Instruments | C-52-598-04-EI-2400 | C-52-598-04-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Installation of Solar S/m (Including Panels, UPS & Battery) | Loop Checking for Instruments | C-52-598-04-EI-1200 | C-52-598-04-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Instrument Cable Laying | Loop Checking for Instruments | C-52-598-04-EI-2010 | C-52-598-04-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Loop Checking for Instruments | Glanding & Termination | C-52-598-04-EI-2040 | C-52-598-04-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Electrical & Earthing Cable Laying | Glanding & Termination | C-52-598-04-EI-2000 | C-52-598-04-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Instrument Cable Laying | Glanding & Termination | C-52-598-04-EI-2010 | C-52-598-04-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Instrument Tubing Works | Glanding & Termination | C-52-598-04-EI-2030 | C-52-598-04-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Installation of Solar S/m (Including Panels, UPS & Battery) | Glanding & Termination | C-52-598-04-EI-1200 | C-52-598-04-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.5 Light Pole, Lighting & FixturesCCOB352E82 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Installation of Light Pole, Lighting & Fixtures | Glanding & Termination | C-52-598-04-EI-1800 | C-52-598-04-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB352E50 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Installation of Passive Cooling Shelter | Glanding & Termination | C-52-598-04-EI-1000 | C-52-598-04-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.5 Light Pole, Lighting & FixturesCCOB352E82 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Installation of Lighting & Instrument JB's | Glanding & Termination | C-52-598-04-EI-1810 | C-52-598-04-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.8 Field InstrumentsCCOB352E102 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Installation of Field Instruments | Glanding & Termination | C-52-598-04-EI-2200 | C-52-598-04-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.6 F&G DevicesCCOB352E92 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Installation of F&G Devices | Glanding & Termination | C-52-598-04-EI-2410 | C-52-598-04-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.4 RTUCCOB352E72 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Installation of RTU | Glanding & Termination | C-52-598-04-EI-1600 | C-52-598-04-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.6 F&G DevicesCCOB352E92 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Installation of F&G Panel | Glanding & Termination | C-52-598-04-EI-2400 | C-52-598-04-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB452E50 | P2543-R01-Oct24..4.3.1.3.12.21.6.4 RTUCCOB452E73 | Installation of Passive Cooling Shelter | Installation of RTU | C-52-598-03-EI-1000 | C-52-598-03-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.4 RTUCCOB452E73 | P2543-R01-Oct24..4.3.1.3.12.21.6.8 F&G DevicesCCOB452E103 | Installation of RTU | Installation of F&G Panel | C-52-598-03-EI-1600 | C-52-598-03-EI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.8 F&G DevicesCCOB452E103 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Installation of F&G Devices | Loop Checking for Instruments | C-52-598-03-EI-2410 | C-52-598-03-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.6 Field InstrumentsCCOB452E93 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Installation of Field Instruments | Loop Checking for Instruments | C-52-598-03-EI-2200 | C-52-598-03-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.5 Light Pole, Lighting & FixturesCCOB452E83 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Installation of Lighting & Instrument JB's | Loop Checking for Instruments | C-52-598-03-EI-1810 | C-52-598-03-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.4 RTUCCOB452E73 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Installation of RTU | Loop Checking for Instruments | C-52-598-03-EI-1600 | C-52-598-03-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.8 F&G DevicesCCOB452E103 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Installation of F&G Panel | Loop Checking for Instruments | C-52-598-03-EI-2400 | C-52-598-03-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Installation of Solar S/m (Including Panels, UPS & Battery) | Loop Checking for Instruments | C-52-598-03-EI-1200 | C-52-598-03-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Instrument Cable Laying | Loop Checking for Instruments | C-52-598-03-EI-2010 | C-52-598-03-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Loop Checking for Instruments | Glanding & Termination | C-52-598-03-EI-2040 | C-52-598-03-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Electrical & Earthing Cable Laying | Glanding & Termination | C-52-598-03-EI-2000 | C-52-598-03-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Instrument Cable Laying | Glanding & Termination | C-52-598-03-EI-2010 | C-52-598-03-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Instrument Tubing Works | Glanding & Termination | C-52-598-03-EI-2030 | C-52-598-03-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Installation of Solar S/m (Including Panels, UPS & Battery) | Glanding & Termination | C-52-598-03-EI-1200 | C-52-598-03-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.5 Light Pole, Lighting & FixturesCCOB452E83 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Installation of Light Pole, Lighting & Fixtures | Glanding & Termination | C-52-598-03-EI-1800 | C-52-598-03-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB452E50 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Installation of Passive Cooling Shelter | Glanding & Termination | C-52-598-03-EI-1000 | C-52-598-03-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.5 Light Pole, Lighting & FixturesCCOB452E83 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Installation of Lighting & Instrument JB's | Glanding & Termination | C-52-598-03-EI-1810 | C-52-598-03-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.6 Field InstrumentsCCOB452E93 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Installation of Field Instruments | Glanding & Termination | C-52-598-03-EI-2200 | C-52-598-03-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.8 F&G DevicesCCOB452E103 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Installation of F&G Devices | Glanding & Termination | C-52-598-03-EI-2410 | C-52-598-03-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.4 RTUCCOB452E73 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Installation of RTU | Glanding & Termination | C-52-598-03-EI-1600 | C-52-598-03-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.8 F&G DevicesCCOB452E103 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Installation of F&G Panel | Glanding & Termination | C-52-598-03-EI-2400 | C-52-598-03-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB552E51 | P2543-R01-Oct24..4.3.1.3.13.21.6.4 RTUCCOB552E75 | Installation of Passive Cooling Shelter | Installation of RTU | C-52-598-02-EI-1000 | C-52-598-02-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.4 RTUCCOB552E75 | P2543-R01-Oct24..4.3.1.3.13.21.6.8 F&G DevicesCCOB552E105 | Installation of RTU | Installation of F&G Panel | C-52-598-02-EI-1600 | C-52-598-02-EI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.8 F&G DevicesCCOB552E105 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Installation of F&G Devices | Loop Checking for Instruments | C-52-598-02-EI-2410 | C-52-598-02-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.6 Field InstrumentsCCOB552E95 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Installation of Field Instruments | Loop Checking for Instruments | C-52-598-02-EI-2200 | C-52-598-02-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.5 Light Pole, Lighting & FixturesCCOB552E85 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Installation of Lighting & Instrument JB's | Loop Checking for Instruments | C-52-598-02-EI-1810 | C-52-598-02-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.4 RTUCCOB552E75 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Installation of RTU | Loop Checking for Instruments | C-52-598-02-EI-1600 | C-52-598-02-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.8 F&G DevicesCCOB552E105 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Installation of F&G Panel | Loop Checking for Instruments | C-52-598-02-EI-2400 | C-52-598-02-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Installation of Solar S/m (Including Panels, UPS & Battery) | Loop Checking for Instruments | C-52-598-02-EI-1200 | C-52-598-02-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Instrument Cable Laying | Loop Checking for Instruments | C-52-598-02-EI-2010 | C-52-598-02-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Loop Checking for Instruments | Glanding & Termination | C-52-598-02-EI-2040 | C-52-598-02-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Electrical & Earthing Cable Laying | Glanding & Termination | C-52-598-02-EI-2000 | C-52-598-02-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Instrument Cable Laying | Glanding & Termination | C-52-598-02-EI-2010 | C-52-598-02-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Instrument Tubing Works | Glanding & Termination | C-52-598-02-EI-2030 | C-52-598-02-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Installation of Solar S/m (Including Panels, UPS & Battery) | Glanding & Termination | C-52-598-02-EI-1200 | C-52-598-02-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.5 Light Pole, Lighting & FixturesCCOB552E85 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Installation of Light Pole, Lighting & Fixtures | Glanding & Termination | C-52-598-02-EI-1800 | C-52-598-02-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB552E51 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Installation of Passive Cooling Shelter | Glanding & Termination | C-52-598-02-EI-1000 | C-52-598-02-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.5 Light Pole, Lighting & FixturesCCOB552E85 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Installation of Lighting & Instrument JB's | Glanding & Termination | C-52-598-02-EI-1810 | C-52-598-02-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.6 Field InstrumentsCCOB552E95 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Installation of Field Instruments | Glanding & Termination | C-52-598-02-EI-2200 | C-52-598-02-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.8 F&G DevicesCCOB552E105 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Installation of F&G Devices | Glanding & Termination | C-52-598-02-EI-2410 | C-52-598-02-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.4 RTUCCOB552E75 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Installation of RTU | Glanding & Termination | C-52-598-02-EI-1600 | C-52-598-02-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.8 F&G DevicesCCOB552E105 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Installation of F&G Panel | Glanding & Termination | C-52-598-02-EI-2400 | C-52-598-02-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB652E51 | P2543-R01-Oct24..4.3.1.3.14.21.6.4 RTUCCOB652E75 | Installation of Passive Cooling Shelter | Installation of RTU | C-52-598-01-EI-1000 | C-52-598-01-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.4 RTUCCOB652E75 | P2543-R01-Oct24..4.3.1.3.14.21.6.8 F&G DevicesCCOB652E105 | Installation of RTU | Installation of F&G Panel | C-52-598-01-EI-1600 | C-52-598-01-EI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.8 F&G DevicesCCOB652E105 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Installation of F&G Devices | Loop Checking for Instruments | C-52-598-01-EI-2410 | C-52-598-01-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.7 Field InstrumentsCCOB652E95 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Installation of Field Instruments | Loop Checking for Instruments | C-52-598-01-EI-2200 | C-52-598-01-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.5 Light Pole, Lighting & FixturesCCOB652E85 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Installation of Lighting & Instrument JB's | Loop Checking for Instruments | C-52-598-01-EI-1810 | C-52-598-01-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.4 RTUCCOB652E75 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Installation of RTU | Loop Checking for Instruments | C-52-598-01-EI-1600 | C-52-598-01-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.8 F&G DevicesCCOB652E105 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Installation of F&G Panel | Loop Checking for Instruments | C-52-598-01-EI-2400 | C-52-598-01-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Installation of Solar S/m (Including Panels, UPS & Battery) | Loop Checking for Instruments | C-52-598-01-EI-1200 | C-52-598-01-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Instrument Cable Laying | Loop Checking for Instruments | C-52-598-01-EI-2010 | C-52-598-01-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Loop Checking for Instruments | Glanding & Termination | C-52-598-01-EI-2040 | C-52-598-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Electrical & Earthing Cable Laying | Glanding & Termination | C-52-598-01-EI-2000 | C-52-598-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Instrument Cable Laying | Glanding & Termination | C-52-598-01-EI-2010 | C-52-598-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Instrument Tubing Works | Glanding & Termination | C-52-598-01-EI-2030 | C-52-598-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Installation of Solar S/m (Including Panels, UPS & Battery) | Glanding & Termination | C-52-598-01-EI-1200 | C-52-598-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.5 Light Pole, Lighting & FixturesCCOB652E85 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Installation of Light Pole, Lighting & Fixtures | Glanding & Termination | C-52-598-01-EI-1800 | C-52-598-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB652E51 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Installation of Passive Cooling Shelter | Glanding & Termination | C-52-598-01-EI-1000 | C-52-598-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.5 Light Pole, Lighting & FixturesCCOB652E85 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Installation of Lighting & Instrument JB's | Glanding & Termination | C-52-598-01-EI-1810 | C-52-598-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.7 Field InstrumentsCCOB652E95 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Installation of Field Instruments | Glanding & Termination | C-52-598-01-EI-2200 | C-52-598-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.8 F&G DevicesCCOB652E105 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Installation of F&G Devices | Glanding & Termination | C-52-598-01-EI-2410 | C-52-598-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.4 RTUCCOB652E75 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Installation of RTU | Glanding & Termination | C-52-598-01-EI-1600 | C-52-598-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.8 F&G DevicesCCOB652E105 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Installation of F&G Panel | Glanding & Termination | C-52-598-01-EI-2400 | C-52-598-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.7.1 CP Anode Bed Installation (subcontract)CCOB252E30 | P2543-R01-Oct24..4.3.1.3.10.21.7.1 CP Anode Bed Installation (subcontract)CCOB252E30 | CP Cable Laying | Installation of CP Test Post | C-52-598-05-CA-1000 | C-52-598-05-CA-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.7.1 CP Anode Bed Installation (subcontract)CCOB252E30 | P2543-R01-Oct24..4.3.1.3.10.21.7.1 CP Anode Bed Installation (subcontract)CCOB252E30 | Installation of CP Test Post | Installation of CP S/m | C-52-598-05-CA-1010 | C-52-598-05-CA-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | CP Cable Laying | Installation of CP Test Post | C-52-598-04-CA-1000 | C-52-598-04-CA-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Installation of CP Test Post | Installation of CP S/m | C-52-598-04-CA-1010 | C-52-598-04-CA-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.7.1 CP Anode Bed Installation (subcontract)CCOB452E30 | P2543-R01-Oct24..4.3.1.3.12.21.7.1 CP Anode Bed Installation (subcontract)CCOB452E30 | CP Cable Laying | Installation of CP Test Post | C-52-598-03-CA-1000 | C-52-598-03-CA-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.7.1 CP Anode Bed Installation (subcontract)CCOB452E30 | P2543-R01-Oct24..4.3.1.3.12.21.7.1 CP Anode Bed Installation (subcontract)CCOB452E30 | Installation of CP Test Post | Installation of CP S/m | C-52-598-03-CA-1010 | C-52-598-03-CA-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | CP Cable Laying | Installation of CP Test Post | C-52-598-02-CA-1000 | C-52-598-02-CA-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Installation of CP Test Post | Installation of CP S/m | C-52-598-02-CA-1010 | C-52-598-02-CA-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.7.1 CP Anode Bed Installation (subcontract)CCOB652E30 | P2543-R01-Oct24..4.3.1.3.14.21.7.1 CP Anode Bed Installation (subcontract)CCOB652E30 | CP Cable Laying | Installation of CP Test Post | C-52-598-01-CA-1000 | C-52-598-01-CA-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.7.1 CP Anode Bed Installation (subcontract)CCOB652E30 | P2543-R01-Oct24..4.3.1.3.14.21.7.1 CP Anode Bed Installation (subcontract)CCOB652E30 | Installation of CP Test Post | Installation of CP S/m | C-52-598-01-CA-1010 | C-52-598-01-CA-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | P2543-R01-Oct24..4.3.1.3.10.21.8.2 PIDS SystemCCOB252I40 | Installation of SDH Cabinet | Installation of PIDS/ PLDS System | C-52-598-05-TE-1000 | C-52-598-05-TE-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.8.2 PIDS SystemCCOB252I40 | P2543-R01-Oct24..4.3.1.3.10.21.8.4 CCTV SystemCCOB252I60 | Installation of PIDS/ PLDS System | Installation of CCTV System | C-52-598-05-TE-1200 | C-52-598-05-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.8.4 CCTV SystemCCOB252I60 | P2543-R01-Oct24..4.3.1.3.10.21.8.3 Telephone SystemCCOB252I50 | Installation of CCTV System | Installation of Telephone System | C-52-598-05-TE-1600 | C-52-598-05-TE-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | P2543-R01-Oct24..4.3.1.3.11.21.8.2 PIDS SystemCCOB352I40 | Installation of SDH Cabinet | Installation of PIDS/ PLDS System | C-52-598-04-TE-1000 | C-52-598-04-TE-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.8.2 PIDS SystemCCOB352I40 | P2543-R01-Oct24..4.3.1.3.11.21.8.4 CCTV SystemCCOB352I60 | Installation of PIDS/ PLDS System | Installation of CCTV System | C-52-598-04-TE-1200 | C-52-598-04-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.8.4 CCTV SystemCCOB352I60 | P2543-R01-Oct24..4.3.1.3.11.21.8.3 Telephone SystemCCOB352I50 | Installation of CCTV System | Installation of Telephone System | C-52-598-04-TE-1600 | C-52-598-04-TE-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | P2543-R01-Oct24..4.3.1.3.12.21.8.2 PIDS SystemCCOB452I40 | Installation of SDH Cabinet | Installation of PIDS/ PLDS System | C-52-598-03-TE-1000 | C-52-598-03-TE-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.8.2 PIDS SystemCCOB452I40 | P2543-R01-Oct24..4.3.1.3.12.21.8.4 CCTV SystemCCOB452I60 | Installation of PIDS/ PLDS System | Installation of CCTV System | C-52-598-03-TE-1200 | C-52-598-03-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.8.4 CCTV SystemCCOB452I60 | P2543-R01-Oct24..4.3.1.3.12.21.8.3 Telephone SystemCCOB452I50 | Installation of CCTV System | Installation of Telephone System | C-52-598-03-TE-1600 | C-52-598-03-TE-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | P2543-R01-Oct24..4.3.1.3.13.21.8.2 PIDS SystemCCOB552I41 | Installation of SDH Cabinet | Installation of PIDS/ PLDS System | C-52-598-02-TE-1000 | C-52-598-02-TE-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.8.2 PIDS SystemCCOB552I41 | P2543-R01-Oct24..4.3.1.3.13.21.8.4 CCTV SystemCCOB552I61 | Installation of PIDS/ PLDS System | Installation of CCTV System | C-52-598-02-TE-1200 | C-52-598-02-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.8.4 CCTV SystemCCOB552I61 | P2543-R01-Oct24..4.3.1.3.13.21.8.3 Telephone SystemCCOB552I51 | Installation of CCTV System | Installation of Telephone System | C-52-598-02-TE-1600 | C-52-598-02-TE-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | P2543-R01-Oct24..4.3.1.3.14.21.8.2 PIDS SystemCCOB652I41 | Installation of SDH Cabinet | Installation of PIDS/ PLDS System | C-52-598-01-TE-1000 | C-52-598-01-TE-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.8.2 PIDS SystemCCOB652I41 | P2543-R01-Oct24..4.3.1.3.14.21.8.4 CCTV SystemCCOB652I61 | Installation of PIDS/ PLDS System | Installation of CCTV System | C-52-598-01-TE-1200 | C-52-598-01-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.8.4 CCTV SystemCCOB652I61 | P2543-R01-Oct24..4.3.1.3.14.21.8.3 Telephone SystemCCOB652I51 | Installation of CCTV System | Installation of Telephone System | C-52-598-01-TE-1600 | C-52-598-01-TE-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | Site Survey, Preparation & Grading Works | Earth Works for Equipment Foundations & Hard Stand Area | C-56-591-01-CI-1000 | C-56-591-01-CI-1010 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | Earth Works for Equipment Foundations & Hard Stand Area | Earth Works for Pipe Support Foundations | C-56-591-01-CI-1010 | C-56-591-01-CI-1020 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | Earth Works for Pipe Support Foundations | Earth Works for Field Instrument Foundations | C-56-591-01-CI-1020 | C-56-591-01-CI-1030 | SS | Not Started | Not Started | 6
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | Earth Works for Field Instrument Foundations | Earth Works for Access Platforms & Misc. Structural Foundations | C-56-591-01-CI-1030 | C-56-591-01-CI-1040 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | Earth Works for Access Platforms & Misc. Structural Foundations | Earth Works for Light Pole, Fence & Gates Foundation | C-56-591-01-CI-1040 | C-56-591-01-CI-1050 | SS | Not Started | Not Started | 6
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.14 Trenching for Cables CCOB156C33 | Earth Works for Pipe Support Foundations | Electrical & Earthing Cable Trenching | C-56-591-01-CI-1020 | C-56-591-01-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.14 Trenching for Cables CCOB156C33 | P2543-R01-Oct24..4.3.1.2.1.12.1.14 Trenching for Cables CCOB156C33 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-56-591-01-CI-1800 | C-56-591-01-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.17 Pipe Supports Fabrication & Installation CCOB156S50 | P2543-R01-Oct24..4.3.1.2.1.12.6.5 Field Instruments CCOB156E64 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-56-591-01-CI-2000 | C-56-591-01-EI-2210 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.1.12.1.17 Pipe Supports Fabrication & Installation CCOB156S50 | P2543-R01-Oct24..4.3.1.2.1.12.1.19 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOB156S54 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Platforms & Crossovers | C-56-591-01-CI-2000 | C-56-591-01-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.5 Field Instruments CCOB156E64 | P2543-R01-Oct24..4.3.1.2.1.12.1.19 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOB156S54 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-56-591-01-EI-2210 | C-56-591-01-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.4.1 Piping Pre-Fabrication CCOB156P100 | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | Piping Pre-Fabrication | Piping Erection | C-56-591-01-PI-1000 | C-56-591-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | P2543-R01-Oct24..4.3.1.2.1.12.4.3 Field Joint Welding & NDT CCOB156P120 | Piping Erection | Field Joint Welding (Including Isolation Joint) | C-56-591-01-PI-1200 | C-56-591-01-PI-1400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.1.12.4.3 Field Joint Welding & NDT CCOB156P120 | P2543-R01-Oct24..4.3.1.2.1.12.4.3 Field Joint Welding & NDT CCOB156P120 | Field Joint Welding (Including Isolation Joint) | NDT & Coating for Field Joint Weld | C-56-591-01-PI-1400 | C-56-591-01-PI-1410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.1.12.4.3 Field Joint Welding & NDT CCOB156P120 | P2543-R01-Oct24..4.3.1.2.1.12.4.4 Hydrotesting CCOB156P130 | NDT & Coating for Field Joint Weld | Hydrotesting | C-56-591-01-PI-1410 | C-56-591-01-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.4.4 Hydrotesting CCOB156P130 | P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | Hydrotesting | Installation of Valves & GOV | C-56-591-01-PI-1600 | C-56-591-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | Installation of Valves & GOV | Final Bolt Torquing/ Re-Instatement | C-56-591-01-PI-1800 | C-56-591-01-PI-2000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | Lowering of Pipeline Section | C-56-591-01-PL-1000 | C-56-591-01-PL-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | Lowering of Pipeline Section | Section Tie-in Welding (Including Barred Tee) | C-56-591-01-PL-1010 | C-56-591-01-PL-1020 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | Section Tie-in Welding (Including Barred Tee) | NDT for Tie-in Joint | C-56-591-01-PL-1020 | C-56-591-01-PL-1030 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | NDT for Tie-in Joint | Ext. Coating for Tie-in Joint | C-56-591-01-PL-1030 | C-56-591-01-PL-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | Ext. Coating for Tie-in Joint | Holiday Testing of Pipeline Section | C-56-591-01-PL-1040 | C-56-591-01-PL-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | Holiday Testing of Pipeline Section | Installation of ROV | C-56-591-01-PL-1050 | C-56-591-01-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | Installation of ROV | Installation of Pig Signaller Pit | C-56-591-01-PL-1060 | C-56-591-01-PL-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | Installation of Pig Signaller Pit | Installation of Pig Signaller | C-56-591-01-PL-1070 | C-56-591-01-PL-1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | Installation of Pig Signaller | Padding & Backfilling | C-56-591-01-PL-1080 | C-56-591-01-PL-1090 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | Holiday Testing of Pipeline Section | Padding & Backfilling | C-56-591-01-PL-1050 | C-56-591-01-PL-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | Installation of ROV | Padding & Backfilling | C-56-591-01-PL-1060 | C-56-591-01-PL-1090 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | Installation of Pig Signaller Pit | Padding & Backfilling | C-56-591-01-PL-1070 | C-56-591-01-PL-1090 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.1.12.6.9 Hybrid Passive Cooling Shelter Installation CCOB156E30 | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Installation of Passive Cooling Shelter | Installation of RTU | C-56-591-01-EI-1000 | C-56-591-01-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | P2543-R01-Oct24..4.3.1.2.1.12.6.6 F&G Devices CCOB156E74 | Installation of RTU | Installation of F&G Panel | C-56-591-01-EI-1600 | C-56-591-01-EI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.6 F&G Devices CCOB156E74 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of F&G Devices | Loop Checking for Instruments | C-56-591-01-EI-2410 | C-56-591-01-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.5 Field Instruments CCOB156E64 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of Field Instruments | Loop Checking for Instruments | C-56-591-01-EI-2200 | C-56-591-01-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.4 Light Pole, Lighting & Fixtures CCOB156E54 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of Lighting & Instrument JB's | Loop Checking for Instruments | C-56-591-01-EI-1810 | C-56-591-01-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of RTU | Loop Checking for Instruments | C-56-591-01-EI-1600 | C-56-591-01-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.6 F&G Devices CCOB156E74 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of F&G Panel | Loop Checking for Instruments | C-56-591-01-EI-2400 | C-56-591-01-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.3 Solar Power System CCOB156E44 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of Solar S/m (Including Panels, UPS & Battery) | Loop Checking for Instruments | C-56-591-01-EI-1200 | C-56-591-01-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Instrument Cable Laying | Loop Checking for Instruments | C-56-591-01-EI-2010 | C-56-591-01-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Loop Checking for Instruments | Glanding & Termination | C-56-591-01-EI-2040 | C-56-591-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Electrical & Earthing Cable Laying | Glanding & Termination | C-56-591-01-EI-2000 | C-56-591-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Instrument Cable Laying | Glanding & Termination | C-56-591-01-EI-2010 | C-56-591-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Instrument Tubing Works | Glanding & Termination | C-56-591-01-EI-2030 | C-56-591-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.3 Solar Power System CCOB156E44 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of Solar S/m (Including Panels, UPS & Battery) | Glanding & Termination | C-56-591-01-EI-1200 | C-56-591-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.4 Light Pole, Lighting & Fixtures CCOB156E54 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of Light Pole, Lighting & Fixtures | Glanding & Termination | C-56-591-01-EI-1800 | C-56-591-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.9 Hybrid Passive Cooling Shelter Installation CCOB156E30 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of Passive Cooling Shelter | Glanding & Termination | C-56-591-01-EI-1000 | C-56-591-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.4 Light Pole, Lighting & Fixtures CCOB156E54 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of Lighting & Instrument JB's | Glanding & Termination | C-56-591-01-EI-1810 | C-56-591-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.5 Field Instruments CCOB156E64 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of Field Instruments | Glanding & Termination | C-56-591-01-EI-2200 | C-56-591-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.6 F&G Devices CCOB156E74 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of F&G Devices | Glanding & Termination | C-56-591-01-EI-2410 | C-56-591-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of RTU | Glanding & Termination | C-56-591-01-EI-1600 | C-56-591-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.6 F&G Devices CCOB156E74 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of F&G Panel | Glanding & Termination | C-56-591-01-EI-2400 | C-56-591-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | CP Cable Laying | Installation of CP Test Post | C-56-591-01-CA-1000 | C-56-591-01-CA-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of CP Test Post | Installation of CP S/m | C-56-591-01-CA-1010 | C-56-591-01-CA-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | P2543-R01-Oct24..4.3.1.2.1.12.8.2 PIDS System CCOB156I30 | Installation of SDH Cabinet | Installation of PIDS/ PLDS System | C-56-591-01-TE-1000 | C-56-591-01-TE-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.8.2 PIDS System CCOB156I30 | P2543-R01-Oct24..4.3.1.2.1.12.8.4 CCTV System CCOB156I50 | Installation of PIDS/ PLDS System | Installation of CCTV System | C-56-591-01-TE-1200 | C-56-591-01-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.8.4 CCTV System CCOB156I50 | P2543-R01-Oct24..4.3.1.2.1.12.8.3 Telephone System CCOB156I40 | Installation of CCTV System | Installation of Telephone System | C-56-591-01-TE-1600 | C-56-591-01-TE-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.4.1 Piping Works -FabricationCCOH52PI60.1 | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Piping Pre-Fabrication | Piping Erection | C-52-PL-838-PI-1000 | C-52-PL-838-PI-1200 | FS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Piping Erection | Field Joint Welding | C-52-PL-838-PI-1200 | C-52-PL-838-PI-1400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | P2543-R01-Oct24..4.3.1.3.1.21.4.2 Piping Works -NDT and PaintingCCOH52PI60.2 | Field Joint Welding | NDT & Coating for Field Joint Weld | C-52-PL-838-PI-1400 | C-52-PL-838-PI-1410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.1.21.4.2 Piping Works -NDT and PaintingCCOH52PI60.2 | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | NDT & Coating for Field Joint Weld | Hydrotesting | C-52-PL-838-PI-1410 | C-52-PL-838-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Hydrotesting | Installation of Valves/MOV/ROV | C-52-PL-838-PI-1600 | C-52-PL-838-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Installation of Valves/MOV/ROV | Final Bolt Torquing/ Re-Instatement | C-52-PL-838-PI-1800 | C-52-PL-838-PI-2000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.1.1.12.4.1 Piping Pre-FabricationCCOHBPI302 | P2543-R01-Oct24..4.3.1.1.1.12.4.2 ErectionCCOHBPI322 | Piping Pre-Fabrication | Piping Erection | C-56-PL-607-PI-1000 | C-56-PL-607-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.4.2 ErectionCCOHBPI322 | P2543-R01-Oct24..4.3.1.1.1.12.4.3 Field Joint Welding & NDTCCOHBPI332 | Piping Erection | Field Joint Welding | C-56-PL-607-PI-1200 | C-56-PL-607-PI-1400 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.1.1.12.4.3 Field Joint Welding & NDTCCOHBPI332 | P2543-R01-Oct24..4.3.1.1.1.12.4.3 Field Joint Welding & NDTCCOHBPI332 | Field Joint Welding | NDT & Coating for Field Joint Weld | C-56-PL-607-PI-1400 | C-56-PL-607-PI-1410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.1.1.12.4.3 Field Joint Welding & NDTCCOHBPI332 | P2543-R01-Oct24..4.3.1.1.1.12.4.4 HydrotestingCCOHBPI342 | NDT & Coating for Field Joint Weld | Hydrotesting | C-56-PL-607-PI-1410 | C-56-PL-607-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.4.4 HydrotestingCCOHBPI342 | P2543-R01-Oct24..4.3.1.1.1.12.4.5 Installation of ValvesCCOHBPI352 | Hydrotesting | Installation of Valves/MOV/ROV | C-56-PL-607-PI-1600 | C-56-PL-607-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.4.22 Piping Pre-Fabrication CCOH56PI101 | P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | Piping Pre-Fabrication | Piping Erection | C-56-PR-838-PI-1000 | C-56-PR-838-PI-1200 | SS | Not Started | Not Started | 26
P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | P2543-R01-Oct24..4.3.1.2.21.12.4.24 Field Joint Welding, NDT & Coating CCOH56PI121 | Piping Erection | Field Joint Welding | C-56-PR-838-PI-1200 | C-56-PR-838-PI-1400 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.21.12.4.24 Field Joint Welding, NDT & Coating CCOH56PI121 | P2543-R01-Oct24..4.3.1.2.21.12.4.24 Field Joint Welding, NDT & Coating CCOH56PI121 | Field Joint Welding | NDT & Coating for Field Joint Weld | C-56-PR-838-PI-1400 | C-56-PR-838-PI-1410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.21.12.4.24 Field Joint Welding, NDT & Coating CCOH56PI121 | P2543-R01-Oct24..4.3.1.2.21.12.4.25 Hydrotesting CCOH56PI131 | NDT & Coating for Field Joint Weld | Hydrotesting | C-56-PR-838-PI-1410 | C-56-PR-838-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.4.25 Hydrotesting CCOH56PI131 | P2543-R01-Oct24..4.3.1.2.21.12.4.26 Installation of Valves CCOH56PI141 | Hydrotesting | Installation of Valves/MOV/ROV | C-56-PR-838-PI-1600 | C-56-PR-838-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.4.26 Installation of Valves CCOH56PI141 | P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | Installation of Valves/MOV/ROV | Final Bolt Torquing/ Re-Instatement | C-56-PR-838-PI-1800 | C-56-PR-838-PI-2000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | Piping Pre-Fabrication | Piping Erection | C-52-PR-839-PI-1000 | C-52-PR-839-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | Piping Erection | Field Joint Welding | C-52-PR-839-PI-1200 | C-52-PR-839-PI-1400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | Field Joint Welding | NDT & Coating for Field Joint Weld | C-52-PR-839-PI-1400 | C-52-PR-839-PI-1410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | NDT & Coating for Field Joint Weld | Hydrotesting | C-52-PR-839-PI-1410 | C-52-PR-839-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | Hydrotesting | Installation of Valves/MOV/ROV | C-52-PR-839-PI-1600 | C-52-PR-839-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | Installation of Valves/MOV/ROV | Final Bolt Torquing/ Re-Instatement | C-52-PR-839-PI-1800 | C-52-PR-839-PI-2000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.4.4.22.2.1 OHPL Installation Works-Tower/Post installation (Subcontract)CCOSW52E20.1 | P2543-R01-Oct24..4.3.1.3.4.4.22.2.2 OHPL Installation Works - Power Line installation(Subcontract)CCOSW52E20.2 | OHPL Installation Works-Tower/Post installation (Subcontract) | OHPL Installation Works - Power Line installation(Subcontract) | C-52-OHPL-EL-1000 | C-52-OHPL-EL-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.4.22.2.2 OHPL Installation Works - Power Line installation(Subcontract)CCOSW52E20.2 | P2543-R01-Oct24..4.3.1.3.4.4.22.2.3 Transformer / Directly Buried MV Cables (including testing)CCOSW52E22 | OHPL Installation Works - Power Line installation(Subcontract) | Transformer / Directly Buried MV Cables (including testing) | C-52-OHPL-EL-1200 | C-52-OHPL-EL-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.4.22.2.3 Transformer / Directly Buried MV Cables (including testing)CCOSW52E22 | P2543-R01-Oct24..4.3.1.3.4.4.22.3.1 Shutdown Connection of OHL & Cable TestingCCOSW52S10 | Transformer / Directly Buried MV Cables (including testing) | Shutdown Connection of OHL & Cable Testing | C-52-OHPL-EL-1400 | C-52-OHPL-EL-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.5.22.1 Earth WorksCCOSW52E112 | P2543-R01-Oct24..4.3.1.3.4.5.22.1 Earth WorksCCOSW52E112 | Site Survey, Preparation & Grading Works | Earth Works for Ground Level | C-52-ADDC-CI-1000 | C-52-ADDC-CI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.5.22.1 Earth WorksCCOSW52E112 | P2543-R01-Oct24..4.3.1.3.4.5.22.1 Earth WorksCCOSW52E112 | Earth Works for Ground Level | Compaction & Testing Works for Ground Level | C-52-ADDC-CI-1010 | C-52-ADDC-CI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.5.22.1 Earth WorksCCOSW52E112 | P2543-R01-Oct24..4.3.1.3.4.5.22.2 Civil Structure/ Flooring WorksCCOSW52E122 | Compaction & Testing Works for Ground Level | Civil Structure/ Flooring Works | C-52-ADDC-CI-1020 | C-52-ADDC-CI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.5.22.2 Civil Structure/ Flooring WorksCCOSW52E122 | P2543-R01-Oct24..4.3.1.3.4.5.22.3 Roofing WorksCCOSW52E132 | Civil Structure/ Flooring Works | Roofing Works | C-52-ADDC-CI-1200 | C-52-ADDC-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.5.22.3 Roofing WorksCCOSW52E132 | P2543-R01-Oct24..4.3.1.3.4.5.22.4 Finishing WorksCCOSW52E142 | Roofing Works | Finishing Works for Shelter | C-52-ADDC-CI-1400 | C-52-ADDC-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.5.22.4 Finishing WorksCCOSW52E142 | P2543-R01-Oct24..4.3.1.3.4.5.22.5 Transformer/ Switch Gear InstallationCCOSW52E152 | Finishing Works for Shelter | Transformer/ Switch Gear Installation | C-52-ADDC-CI-1600 | C-52-ADDC-EL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.5.22.5 Transformer/ Switch Gear InstallationCCOSW52E152 | P2543-R01-Oct24..4.3.1.3.4.5.22.6 Cable Laying, Glanding, Termination & Hook-UpCCOSW52E162 | Transformer/ Switch Gear Installation | Cable Laying, Glanding, Termination & Hook-Up | C-52-ADDC-EL-1000 | C-52-ADDC-EL-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.6 SurveyingCCOPL4"100 | P2543-R01-Oct24..4.3.1.5.4.12.1.8 ROW Access RoadCCOPL4"102 | Survey Marking | Sabka ROW/Grading | C-4N-H5HG-PIPEL-1000 | C-4N-H5HG-PIPEL-1800 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.8 ROW Access RoadCCOPL4"102 | P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | Sabka ROW/Grading | Sabka Gatch Laying (Including ROW) - Layer 1 | C-4N-H5HG-PIPEL-1800 | C-4N-H5HG-PIPEL-2000 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.1.9 Pipe StringingCCOPL4"104 | Sabka Gatch Compaction - Layer 4 | Stringing (HB-5 to HGCP) | C-4N-H5HG-PIPEL-2230 | C-4N-H5HG-PIPEL-2800 | SS | In Progress | Not Started | 7
P2543-R01-Oct24..4.3.1.5.4.12.1.9 Pipe StringingCCOPL4"104 | P2543-R01-Oct24..4.3.1.5.4.12.1.11 Manual Welding from Habshan 5 to KP-12CCOPL4"105.1 | Stringing (HB-5 to HGCP) | Welding | C-4N-H5HG-PIPEL-2800 | C-4N-H5HG-PIPEL-3600 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.5.4.12.1.11 Manual Welding from Habshan 5 to KP-12CCOPL4"105.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.12 NDT Test Habshan 5 to KP-12CCOPL4"107.1 | Welding | NDT | C-4N-H5HG-PIPEL-3600 | C-4N-H5HG-PIPEL-4000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.12 NDT Test Habshan 5 to KP-12CCOPL4"107.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.21 Ext. Joint Coating from Habshan 5 to KP-12CCOPL4"111.1 | NDT | Ext. Joint Coating | C-4N-H5HG-PIPEL-4000 | C-4N-H5HG-PIPEL-4400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.5.4.12.1.10 Excavation (incl Bedding)CCOPL4"106 | P2543-R01-Oct24..4.3.1.5.4.12.1.10 Excavation (incl Bedding)CCOPL4"106 | Trench Excavation | Bedding | C-4N-H5HG-PIPEL-2400 | C-4N-H5HG-PIPEL-2410 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.5.4.12.1.10 Excavation (incl Bedding)CCOPL4"106 | P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | Bedding | Lowering | C-4N-H5HG-PIPEL-2410 | C-4N-H5HG-PIPEL-4800 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | Lowering | Section Tie-in Welding | C-4N-H5HG-PIPEL-4800 | C-4N-H5HG-PIPEL-4810 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-PIPEL-4810 | C-4N-H5HG-PIPEL-4820 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.21 Ext. Joint Coating from Habshan 5 to KP-12CCOPL4"111.1 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-PIPEL-4820 | C-4N-H5HG-PIPEL-4410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.21 Ext. Joint Coating from Habshan 5 to KP-12CCOPL4"111.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-PIPEL-4410 | C-4N-H5HG-PIPEL-4830 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | Holiday Testing | Padding | C-4N-H5HG-PIPEL-4830 | C-4N-H5HG-PIPEL-6000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-4N-H5HG-PIPEL-2000 | C-4N-H5HG-PIPEL-2200 | SS | In Progress | In Progress | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Compaction - Layer 2 | C-4N-H5HG-PIPEL-2010 | C-4N-H5HG-PIPEL-2210 | SS | In Progress | In Progress | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Compaction - Layer 3 | C-4N-H5HG-PIPEL-2020 | C-4N-H5HG-PIPEL-2220 | SS | In Progress | In Progress | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | Sabka Gatch Laying - Layer 4 | Sabka Gatch Compaction - Layer 4 | C-4N-H5HG-PIPEL-2030 | C-4N-H5HG-PIPEL-2230 | SS | In Progress | In Progress | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.1.10 Excavation (incl Bedding)CCOPL4"106 | Sabka Gatch Compaction - Layer 4 | Trench Excavation | C-4N-H5HG-PIPEL-2230 | C-4N-H5HG-PIPEL-2400 | SS | In Progress | Not Started | 7
P2543-R01-Oct24..4.3.1.5.4.12.1.21 Ext. Joint Coating from Habshan 5 to KP-12CCOPL4"111.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | Ext. Joint Coating | Lowering | C-4N-H5HG-PIPEL-4400 | C-4N-H5HG-PIPEL-4800 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.5.4.12.1.6 SurveyingCCOPL4"100 | P2543-R01-Oct24..4.3.1.5.4.12.1.7 Cut & FillCCOPL4"101 | Survey Marking | Cut & Fill (@ Non-Sabkha) | C-4N-H5HG-PIPEL-1000 | C-4N-H5HG-PIPEL-1400 | SS | Completed | Not Started | 3
P2543-R01-Oct24..4.3.1.5.4.12.1.7 Cut & FillCCOPL4"101 | P2543-R01-Oct24..4.3.1.5.4.12.1.10 Excavation (incl Bedding)CCOPL4"106 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-4N-H5HG-PIPEL-1400 | C-4N-H5HG-PIPEL-2400 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.4.12.1.8 ROW Access RoadCCOPL4"102 | P2543-R01-Oct24..4.3.1.5.4.12.1.10 Excavation (incl Bedding)CCOPL4"106 | Sabka ROW/Grading | Trench Excavation | C-4N-H5HG-PIPEL-1800 | C-4N-H5HG-PIPEL-2400 | SS | In Progress | Not Started | 5
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | Trench Excavation | Bedding | C-4N-H5HG-CMA13-1000 | C-4N-H5HG-CMA13-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | Bedding | Lowering | C-4N-H5HG-CMA13-1010 | C-4N-H5HG-CMA13-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA13-1020 | C-4N-H5HG-CMA13-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA13-1030 | C-4N-H5HG-CMA13-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA13-1040 | C-4N-H5HG-CMA13-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA13-1050 | C-4N-H5HG-CMA13-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | Holiday Testing | Padding | C-4N-H5HG-CMA13-1060 | C-4N-H5HG-CMA13-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | Trench Excavation | Bedding | C-4N-H5HG-CMA01-1000 | C-4N-H5HG-CMA01-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | Bedding | Lowering | C-4N-H5HG-CMA01-1010 | C-4N-H5HG-CMA01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA01-1020 | C-4N-H5HG-CMA01-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA01-1030 | C-4N-H5HG-CMA01-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA01-1040 | C-4N-H5HG-CMA01-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA01-1050 | C-4N-H5HG-CMA01-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | Holiday Testing | Padding | C-4N-H5HG-CMA01-1060 | C-4N-H5HG-CMA01-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | Trench Excavation | Bedding | C-4N-H5HG-CMA02-1000 | C-4N-H5HG-CMA02-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | Bedding | Lowering | C-4N-H5HG-CMA02-1010 | C-4N-H5HG-CMA02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA02-1020 | C-4N-H5HG-CMA02-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA02-1030 | C-4N-H5HG-CMA02-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA02-1040 | C-4N-H5HG-CMA02-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA02-1050 | C-4N-H5HG-CMA02-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | Holiday Testing | Padding | C-4N-H5HG-CMA02-1060 | C-4N-H5HG-CMA02-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | Trench Excavation | Bedding | C-4N-H5HG-CMA03-1000 | C-4N-H5HG-CMA03-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | Bedding | Lowering | C-4N-H5HG-CMA03-1010 | C-4N-H5HG-CMA03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA03-1020 | C-4N-H5HG-CMA03-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA03-1030 | C-4N-H5HG-CMA03-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA03-1040 | C-4N-H5HG-CMA03-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA03-1050 | C-4N-H5HG-CMA03-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | Holiday Testing | Padding | C-4N-H5HG-CMA03-1060 | C-4N-H5HG-CMA03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | Trench Excavation | Bedding | C-4N-H5HG-CMA04-1000 | C-4N-H5HG-CMA04-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | Bedding | Lowering | C-4N-H5HG-CMA04-1010 | C-4N-H5HG-CMA04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA04-1020 | C-4N-H5HG-CMA04-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA04-1030 | C-4N-H5HG-CMA04-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA04-1040 | C-4N-H5HG-CMA04-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA04-1050 | C-4N-H5HG-CMA04-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | Holiday Testing | Padding | C-4N-H5HG-CMA04-1060 | C-4N-H5HG-CMA04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | Trench Excavation | Bedding | C-4N-H5HG-CMA05-1000 | C-4N-H5HG-CMA05-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | Bedding | Lowering | C-4N-H5HG-CMA05-1010 | C-4N-H5HG-CMA05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA05-1020 | C-4N-H5HG-CMA05-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA05-1030 | C-4N-H5HG-CMA05-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA05-1040 | C-4N-H5HG-CMA05-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA05-1050 | C-4N-H5HG-CMA05-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | Holiday Testing | Padding | C-4N-H5HG-CMA05-1060 | C-4N-H5HG-CMA05-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | Trench Excavation | Bedding | C-4N-H5HG-CMA06-1000 | C-4N-H5HG-CMA06-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | Bedding | Lowering | C-4N-H5HG-CMA06-1010 | C-4N-H5HG-CMA06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA06-1020 | C-4N-H5HG-CMA06-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA06-1030 | C-4N-H5HG-CMA06-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA06-1040 | C-4N-H5HG-CMA06-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA06-1050 | C-4N-H5HG-CMA06-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | Holiday Testing | Padding | C-4N-H5HG-CMA06-1060 | C-4N-H5HG-CMA06-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | Trench Excavation | Bedding | C-4N-H5HG-CMA07-1000 | C-4N-H5HG-CMA07-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | Bedding | Lowering | C-4N-H5HG-CMA07-1010 | C-4N-H5HG-CMA07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA07-1020 | C-4N-H5HG-CMA07-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA07-1030 | C-4N-H5HG-CMA07-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA07-1040 | C-4N-H5HG-CMA07-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA07-1050 | C-4N-H5HG-CMA07-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | Holiday Testing | Padding | C-4N-H5HG-CMA07-1060 | C-4N-H5HG-CMA07-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | Trench Excavation | Bedding | C-4N-H5HG-CMA08-1000 | C-4N-H5HG-CMA08-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | Bedding | Lowering | C-4N-H5HG-CMA08-1010 | C-4N-H5HG-CMA08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA08-1020 | C-4N-H5HG-CMA08-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA08-1030 | C-4N-H5HG-CMA08-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA08-1040 | C-4N-H5HG-CMA08-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA08-1050 | C-4N-H5HG-CMA08-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | Holiday Testing | Padding | C-4N-H5HG-CMA08-1060 | C-4N-H5HG-CMA08-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | Trench Excavation | Bedding | C-4N-H5HG-CMA09-1000 | C-4N-H5HG-CMA09-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | Bedding | Lowering | C-4N-H5HG-CMA09-1010 | C-4N-H5HG-CMA09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA09-1020 | C-4N-H5HG-CMA09-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA09-1030 | C-4N-H5HG-CMA09-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA09-1040 | C-4N-H5HG-CMA09-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA09-1050 | C-4N-H5HG-CMA09-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | Holiday Testing | Padding | C-4N-H5HG-CMA09-1060 | C-4N-H5HG-CMA09-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | Trench Excavation | Bedding | C-4N-H5HG-CMA10-1000 | C-4N-H5HG-CMA10-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | Bedding | Lowering | C-4N-H5HG-CMA10-1010 | C-4N-H5HG-CMA10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA10-1020 | C-4N-H5HG-CMA10-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA10-1030 | C-4N-H5HG-CMA10-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA10-1040 | C-4N-H5HG-CMA10-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA10-1050 | C-4N-H5HG-CMA10-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | Holiday Testing | Padding | C-4N-H5HG-CMA10-1060 | C-4N-H5HG-CMA10-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | Trench Excavation | Bedding | C-4N-H5HG-CMA11-1000 | C-4N-H5HG-CMA11-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | Bedding | Lowering | C-4N-H5HG-CMA11-1010 | C-4N-H5HG-CMA11-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA11-1020 | C-4N-H5HG-CMA11-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA11-1030 | C-4N-H5HG-CMA11-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA11-1040 | C-4N-H5HG-CMA11-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA11-1050 | C-4N-H5HG-CMA11-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | Holiday Testing | Padding | C-4N-H5HG-CMA11-1060 | C-4N-H5HG-CMA11-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | Trench Excavation | Bedding | C-4N-H5HG-CMA12-1000 | C-4N-H5HG-CMA12-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | Bedding | Lowering | C-4N-H5HG-CMA12-1010 | C-4N-H5HG-CMA12-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA12-1020 | C-4N-H5HG-CMA12-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA12-1030 | C-4N-H5HG-CMA12-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA12-1040 | C-4N-H5HG-CMA12-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA12-1050 | C-4N-H5HG-CMA12-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | Holiday Testing | Padding | C-4N-H5HG-CMA12-1060 | C-4N-H5HG-CMA12-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | Trench Excavation | Bedding | C-4N-H5HG-CMA14-1000 | C-4N-H5HG-CMA14-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | Bedding | Lowering | C-4N-H5HG-CMA14-1010 | C-4N-H5HG-CMA14-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA14-1020 | C-4N-H5HG-CMA14-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA14-1030 | C-4N-H5HG-CMA14-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA14-1040 | C-4N-H5HG-CMA14-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA14-1050 | C-4N-H5HG-CMA14-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | Holiday Testing | Padding | C-4N-H5HG-CMA14-1060 | C-4N-H5HG-CMA14-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | Trench Excavation | Bedding | C-4N-H5HG-CMA15-1000 | C-4N-H5HG-CMA15-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | Bedding | Lowering | C-4N-H5HG-CMA15-1010 | C-4N-H5HG-CMA15-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA15-1020 | C-4N-H5HG-CMA15-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA15-1030 | C-4N-H5HG-CMA15-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA15-1040 | C-4N-H5HG-CMA15-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA15-1050 | C-4N-H5HG-CMA15-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | Holiday Testing | Padding | C-4N-H5HG-CMA15-1060 | C-4N-H5HG-CMA15-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | Trench Excavation | Bedding | C-4N-H5HG-CMA16-1000 | C-4N-H5HG-CMA16-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | Bedding | Lowering | C-4N-H5HG-CMA16-1010 | C-4N-H5HG-CMA16-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA16-1020 | C-4N-H5HG-CMA16-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA16-1030 | C-4N-H5HG-CMA16-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA16-1040 | C-4N-H5HG-CMA16-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA16-1050 | C-4N-H5HG-CMA16-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | Holiday Testing | Padding | C-4N-H5HG-CMA16-1060 | C-4N-H5HG-CMA16-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | Trench Excavation | Bedding | C-4N-H5HG-CMA17-1000 | C-4N-H5HG-CMA17-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | Bedding | Lowering | C-4N-H5HG-CMA17-1010 | C-4N-H5HG-CMA17-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA17-1020 | C-4N-H5HG-CMA17-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA17-1030 | C-4N-H5HG-CMA17-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA17-1040 | C-4N-H5HG-CMA17-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA17-1050 | C-4N-H5HG-CMA17-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | Holiday Testing | Padding | C-4N-H5HG-CMA17-1060 | C-4N-H5HG-CMA17-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | Trench Excavation | Bedding | C-4N-H5HG-CMA18-1000 | C-4N-H5HG-CMA18-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | Bedding | Lowering | C-4N-H5HG-CMA18-1010 | C-4N-H5HG-CMA18-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA18-1020 | C-4N-H5HG-CMA18-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA18-1030 | C-4N-H5HG-CMA18-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA18-1040 | C-4N-H5HG-CMA18-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA18-1050 | C-4N-H5HG-CMA18-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | Holiday Testing | Padding | C-4N-H5HG-CMA18-1060 | C-4N-H5HG-CMA18-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | Trench Excavation | Bedding | C-4N-H5HG-CMA27-1000 | C-4N-H5HG-CMA27-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | Bedding | Lowering | C-4N-H5HG-CMA27-1010 | C-4N-H5HG-CMA27-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA27-1020 | C-4N-H5HG-CMA27-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA27-1030 | C-4N-H5HG-CMA27-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA27-1040 | C-4N-H5HG-CMA27-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA27-1050 | C-4N-H5HG-CMA27-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | Holiday Testing | Padding | C-4N-H5HG-CMA27-1060 | C-4N-H5HG-CMA27-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | Trench Excavation | Bedding | C-4N-H5HG-CMA19-1000 | C-4N-H5HG-CMA19-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | Bedding | Lowering | C-4N-H5HG-CMA19-1010 | C-4N-H5HG-CMA19-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA19-1020 | C-4N-H5HG-CMA19-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA19-1030 | C-4N-H5HG-CMA19-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA19-1040 | C-4N-H5HG-CMA19-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA19-1050 | C-4N-H5HG-CMA19-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | Holiday Testing | Padding | C-4N-H5HG-CMA19-1060 | C-4N-H5HG-CMA19-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | Trench Excavation | Bedding | C-4N-H5HG-CMA20-1000 | C-4N-H5HG-CMA20-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | Bedding | Lowering | C-4N-H5HG-CMA20-1010 | C-4N-H5HG-CMA20-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA20-1020 | C-4N-H5HG-CMA20-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA20-1030 | C-4N-H5HG-CMA20-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA20-1040 | C-4N-H5HG-CMA20-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA20-1050 | C-4N-H5HG-CMA20-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | Holiday Testing | Padding | C-4N-H5HG-CMA20-1060 | C-4N-H5HG-CMA20-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | Trench Excavation | Bedding | C-4N-H5HG-CMA21-1000 | C-4N-H5HG-CMA21-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | Bedding | Lowering | C-4N-H5HG-CMA21-1010 | C-4N-H5HG-CMA21-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA21-1020 | C-4N-H5HG-CMA21-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA21-1030 | C-4N-H5HG-CMA21-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA21-1040 | C-4N-H5HG-CMA21-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA21-1050 | C-4N-H5HG-CMA21-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | Holiday Testing | Padding | C-4N-H5HG-CMA21-1060 | C-4N-H5HG-CMA21-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | Trench Excavation | Bedding | C-4N-H5HG-CMA22-1000 | C-4N-H5HG-CMA22-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | Bedding | Lowering | C-4N-H5HG-CMA22-1010 | C-4N-H5HG-CMA22-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA22-1020 | C-4N-H5HG-CMA22-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA22-1030 | C-4N-H5HG-CMA22-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA22-1040 | C-4N-H5HG-CMA22-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA22-1050 | C-4N-H5HG-CMA22-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | Holiday Testing | Padding | C-4N-H5HG-CMA22-1060 | C-4N-H5HG-CMA22-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | Trench Excavation | Bedding | C-4N-H5HG-CMA23-1000 | C-4N-H5HG-CMA23-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | Bedding | Lowering | C-4N-H5HG-CMA23-1010 | C-4N-H5HG-CMA23-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA23-1020 | C-4N-H5HG-CMA23-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA23-1030 | C-4N-H5HG-CMA23-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA23-1040 | C-4N-H5HG-CMA23-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA23-1050 | C-4N-H5HG-CMA23-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | Holiday Testing | Padding | C-4N-H5HG-CMA23-1060 | C-4N-H5HG-CMA23-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | Trench Excavation | Bedding | C-4N-H5HG-CMA28-1000 | C-4N-H5HG-CMA28-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | Bedding | Lowering | C-4N-H5HG-CMA28-1010 | C-4N-H5HG-CMA28-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA28-1020 | C-4N-H5HG-CMA28-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA28-1030 | C-4N-H5HG-CMA28-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA28-1040 | C-4N-H5HG-CMA28-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA28-1050 | C-4N-H5HG-CMA28-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | Holiday Testing | Padding | C-4N-H5HG-CMA28-1060 | C-4N-H5HG-CMA28-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | Trench Excavation | Bedding | C-4N-H5HG-CMA24-1000 | C-4N-H5HG-CMA24-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | Bedding | Lowering | C-4N-H5HG-CMA24-1010 | C-4N-H5HG-CMA24-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA24-1020 | C-4N-H5HG-CMA24-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA24-1030 | C-4N-H5HG-CMA24-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA24-1040 | C-4N-H5HG-CMA24-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA24-1050 | C-4N-H5HG-CMA24-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | Holiday Testing | Padding | C-4N-H5HG-CMA24-1060 | C-4N-H5HG-CMA24-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | Trench Excavation | Bedding | C-4N-H5HG-CMA25-1000 | C-4N-H5HG-CMA25-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | Bedding | Lowering | C-4N-H5HG-CMA25-1010 | C-4N-H5HG-CMA25-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA25-1020 | C-4N-H5HG-CMA25-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA25-1030 | C-4N-H5HG-CMA25-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA25-1040 | C-4N-H5HG-CMA25-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA25-1050 | C-4N-H5HG-CMA25-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | Holiday Testing | Padding | C-4N-H5HG-CMA25-1060 | C-4N-H5HG-CMA25-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | Trench Excavation | Bedding | C-4N-H5HG-CMA26-1000 | C-4N-H5HG-CMA26-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | Bedding | Lowering | C-4N-H5HG-CMA26-1010 | C-4N-H5HG-CMA26-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA26-1020 | C-4N-H5HG-CMA26-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA26-1030 | C-4N-H5HG-CMA26-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA26-1040 | C-4N-H5HG-CMA26-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA26-1050 | C-4N-H5HG-CMA26-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | Holiday Testing | Padding | C-4N-H5HG-CMA26-1060 | C-4N-H5HG-CMA26-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | Trench Excavation | Bedding | C-4N-H5HG-CMA29-1000 | C-4N-H5HG-CMA29-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | Bedding | Lowering | C-4N-H5HG-CMA29-1010 | C-4N-H5HG-CMA29-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | Lowering | Section Tie-in Welding | C-4N-H5HG-CMA29-1020 | C-4N-H5HG-CMA29-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-CMA29-1030 | C-4N-H5HG-CMA29-1040 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-CMA29-1040 | C-4N-H5HG-CMA29-1050 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-CMA29-1050 | C-4N-H5HG-CMA29-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | Holiday Testing | Padding | C-4N-H5HG-CMA29-1060 | C-4N-H5HG-CMA29-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 HDD @ CH 0+517 - 0+556 (HDD-01) | P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 HDD @ CH 0+517 - 0+556 (HDD-01) | Excavation for Entry & Exit Pit Preparation | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH01-1000 | C-4N-H5HG-CNH01-1010 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 HDD @ CH 0+517 - 0+556 (HDD-01) | P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 HDD @ CH 0+517 - 0+556 (HDD-01) | HDD Section Readiness (Including hydrotest) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH01-1010 | C-4N-H5HG-CNH01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 HDD @ CH 0+517 - 0+556 (HDD-01) | P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 HDD @ CH 0+517 - 0+556 (HDD-01) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH01-1020 | C-4N-H5HG-CNH01-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 HDD @ CH 1+006 - 1+056 (HDD-02) | P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 HDD @ CH 1+006 - 1+056 (HDD-02) | Excavation for Entry & Exit Pit Preparation | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH02-1000 | C-4N-H5HG-CNH02-1010 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 HDD @ CH 1+006 - 1+056 (HDD-02) | P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 HDD @ CH 1+006 - 1+056 (HDD-02) | HDD Section Readiness (Including hydrotest) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH02-1010 | C-4N-H5HG-CNH02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 HDD @ CH 1+006 - 1+056 (HDD-02) | P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 HDD @ CH 1+006 - 1+056 (HDD-02) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH02-1020 | C-4N-H5HG-CNH02-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 HDD @ CH 2+845 - 3+029 (HDD-03) | P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 HDD @ CH 2+845 - 3+029 (HDD-03) | Excavation for Entry & Exit Pit Preparation | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH03-1000 | C-4N-H5HG-CNH03-1010 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 HDD @ CH 2+845 - 3+029 (HDD-03) | P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 HDD @ CH 2+845 - 3+029 (HDD-03) | HDD Section Readiness (Including hydrotest) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH03-1010 | C-4N-H5HG-CNH03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 HDD @ CH 2+845 - 3+029 (HDD-03) | P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 HDD @ CH 2+845 - 3+029 (HDD-03) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH03-1020 | C-4N-H5HG-CNH03-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 HDD @ CH 4+392 - 4+477 (HDD-04) | P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 HDD @ CH 4+392 - 4+477 (HDD-04) | Excavation for Entry & Exit Pit Preparation | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH04-1000 | C-4N-H5HG-CNH04-1010 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 HDD @ CH 4+392 - 4+477 (HDD-04) | P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 HDD @ CH 4+392 - 4+477 (HDD-04) | HDD Section Readiness (Including hydrotest) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH04-1010 | C-4N-H5HG-CNH04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 HDD @ CH 4+392 - 4+477 (HDD-04) | P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 HDD @ CH 4+392 - 4+477 (HDD-04) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH04-1020 | C-4N-H5HG-CNH04-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 HDD @ CH 9+139 - 9+322 (HDD-05) | P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 HDD @ CH 9+139 - 9+322 (HDD-05) | Excavation for Entry & Exit Pit Preparation | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH05-1000 | C-4N-H5HG-CNH05-1010 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 HDD @ CH 9+139 - 9+322 (HDD-05) | P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 HDD @ CH 9+139 - 9+322 (HDD-05) | HDD Section Readiness (Including hydrotest) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH05-1010 | C-4N-H5HG-CNH05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 HDD @ CH 9+139 - 9+322 (HDD-05) | P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 HDD @ CH 9+139 - 9+322 (HDD-05) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH05-1020 | C-4N-H5HG-CNH05-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 HDD @ CH 10+556 - 10+647 (HDD-06) | P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 HDD @ CH 10+556 - 10+647 (HDD-06) | Excavation for Entry & Exit Pit Preparation | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH06-1000 | C-4N-H5HG-CNH06-1010 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 HDD @ CH 10+556 - 10+647 (HDD-06) | P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 HDD @ CH 10+556 - 10+647 (HDD-06) | HDD Section Readiness (Including hydrotest) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH06-1010 | C-4N-H5HG-CNH06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 HDD @ CH 10+556 - 10+647 (HDD-06) | P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 HDD @ CH 10+556 - 10+647 (HDD-06) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH06-1020 | C-4N-H5HG-CNH06-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 HDD @ CH 12+216 - 12+275 (HDD-07) | P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 HDD @ CH 12+216 - 12+275 (HDD-07) | Excavation for Entry & Exit Pit Preparation | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH07-1000 | C-4N-H5HG-CNH07-1010 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 HDD @ CH 12+216 - 12+275 (HDD-07) | P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 HDD @ CH 12+216 - 12+275 (HDD-07) | HDD Section Readiness (Including hydrotest) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH07-1010 | C-4N-H5HG-CNH07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 HDD @ CH 12+216 - 12+275 (HDD-07) | P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 HDD @ CH 12+216 - 12+275 (HDD-07) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH07-1020 | C-4N-H5HG-CNH07-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 HDD @ CH 16+746 - 16+764 (HDD-08) | P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 HDD @ CH 16+746 - 16+764 (HDD-08) | Excavation for Entry & Exit Pit Preparation | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH08-1000 | C-4N-H5HG-CNH08-1010 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 HDD @ CH 16+746 - 16+764 (HDD-08) | P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 HDD @ CH 16+746 - 16+764 (HDD-08) | HDD Section Readiness (Including hydrotest) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH08-1010 | C-4N-H5HG-CNH08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 HDD @ CH 16+746 - 16+764 (HDD-08) | P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 HDD @ CH 16+746 - 16+764 (HDD-08) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH08-1020 | C-4N-H5HG-CNH08-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.19 Test Stations & Anode BedsCCOP4"EL12 | P2543-R01-Oct24..4.3.1.5.4.12.1.27 CP Works(Temporary)CCOP4"EL11.1 | Installation of Temp. Anode | Installation of CP Test Post | C-4N-H5HG-PIPEL-5600 | C-4N-H5HG-PIPEL-5200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.27 CP Works(Temporary)CCOP4"EL11.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.27 CP Works(Temporary)CCOP4"EL11.1 | Installation of CP Test Post | Glanding & Termination of Temp. CP S/m | C-4N-H5HG-PIPEL-5200 | C-4N-H5HG-PIPEL-5210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Installation of Test Post for Crossing | Installation of CP JB's | C-4N-H5HG-PIPEL-5220 | C-4N-H5HG-PIPEL-5230 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Installation of CP JB's | Installation of CP TR | C-4N-H5HG-PIPEL-5230 | C-4N-H5HG-PIPEL-5240 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Installation of CP TR | CIP/DCVG Survey | C-4N-H5HG-PIPEL-5240 | C-4N-H5HG-PIPEL-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | Termination/Splicing @ HGCP | C-4N-H5HG-PIPEL-8200 | C-4N-H5HG-PIPEL-8210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Cleaning & Gauging | Water Filling | C-4N-H5HG-PIPEL-7400 | C-4N-H5HG-PIPEL-7410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Water Filling | Pressurization | C-4N-H5HG-PIPEL-7410 | C-4N-H5HG-PIPEL-7420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Pressurization | Holding of Test Pressure | C-4N-H5HG-PIPEL-7420 | C-4N-H5HG-PIPEL-7430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | P2543-R01-Oct24..4.3.1.5.4.12.1.32 Dewatering, Swabbing, & DryingCCOPL4"124 | Holding of Test Pressure | De-Pressurization | C-4N-H5HG-PIPEL-7430 | C-4N-H5HG-PIPEL-7600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.32 Dewatering, Swabbing, & DryingCCOPL4"124 | P2543-R01-Oct24..4.3.1.5.4.12.1.32 Dewatering, Swabbing, & DryingCCOPL4"124 | De-Pressurization | De-watering | C-4N-H5HG-PIPEL-7600 | C-4N-H5HG-PIPEL-7610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.32 Dewatering, Swabbing, & DryingCCOPL4"124 | P2543-R01-Oct24..4.3.1.5.4.12.1.32 Dewatering, Swabbing, & DryingCCOPL4"124 | De-watering | Swabing & Drying (Upto Dew Point Temp.) | C-4N-H5HG-PIPEL-7610 | C-4N-H5HG-PIPEL-7620 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Gatch Laying & Levelling | Gatch Compaction | C-4N-H5HG-PIPEL-6800 | C-4N-H5HG-PIPEL-6810 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.5.4.12.1.33 ROW Restoration/ Marker Post/ Crash BarrierCCOPL4"126 | P2543-R01-Oct24..4.3.1.5.4.12.1.33 ROW Restoration/ Marker Post/ Crash BarrierCCOPL4"126 | ROW Restoration/ Installation of Marker Post/Sign Board | Installation of Crash Barriers (If any) | C-4N-H5HG-PIPEL-7800 | C-4N-H5HG-PIPEL-7810 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Sabka Gatch Compaction - Layer 3 | Sabka Gatch Compaction - Layer 4 | C-4W-SVHG-PIPEL-2220 | C-4W-SVHG-PIPEL-2230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Sabka Gatch Compaction - Layer 4 | Stringing (SV-03 to HGCP) | C-4W-SVHG-PIPEL-2230 | C-4W-SVHG-PIPEL-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Stringing (SV-03 to HGCP) | Field Joint | C-4W-SVHG-PIPEL-2800 | C-4W-SVHG-PIPEL-3100 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Trench Excavation | Bedding | C-4W-SVHG-PIPEL-2400 | C-4W-SVHG-PIPEL-2410 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Bedding | Lowering | C-4W-SVHG-PIPEL-2410 | C-4W-SVHG-PIPEL-4800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Lowering | Section Tie-in Joint | C-4W-SVHG-PIPEL-4800 | C-4W-SVHG-PIPEL-4810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-4W-SVHG-PIPEL-2000 | C-4W-SVHG-PIPEL-2200 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Compaction - Layer 2 | C-4W-SVHG-PIPEL-2010 | C-4W-SVHG-PIPEL-2210 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Compaction - Layer 3 | C-4W-SVHG-PIPEL-2020 | C-4W-SVHG-PIPEL-2220 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Sabka Gatch Laying - Layer 4 | Sabka Gatch Compaction - Layer 4 | C-4W-SVHG-PIPEL-2030 | C-4W-SVHG-PIPEL-2230 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Sabka Gatch Compaction - Layer 4 | Trench Excavation | C-4W-SVHG-PIPEL-2230 | C-4W-SVHG-PIPEL-2400 | FS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Field Joint Protection Sleeve | Lowering | C-4W-SVHG-PIPEL-3110 | C-4W-SVHG-PIPEL-4800 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | Trench Excavation | Bedding | CPL-4-CRMN-3320 | CPL-4-CRMN-3330 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | Bedding | Lowering | CPL-4-CRMN-3330 | CPL-4-CRMN-3340 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | Lowering | Section Tie-in Joint | CPL-4-CRMN-3340 | CPL-4-CRMN-3350 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 HDD @ CH 0+236 - 0+389 (HDD-01) | P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 HDD @ CH 0+236 - 0+389 (HDD-01) | Excavation for Entry & Exit Pit Preparation | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH1-1000 | C-4N-H5HG-CNH1-1010 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 HDD @ CH 0+236 - 0+389 (HDD-01) | P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 HDD @ CH 0+236 - 0+389 (HDD-01) | HDD Section Readiness (Including hydrotest) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH1-1010 | C-4N-H5HG-CNH1-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 HDD @ CH 0+236 - 0+389 (HDD-01) | P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 HDD @ CH 0+236 - 0+389 (HDD-01) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH1-1020 | C-4N-H5HG-CNH1-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.9.1 HDD @ CH 1+401 - 1+551 (HDD-02) | P2543-R01-Oct24..4.3.1.5.4.12.3.9.1 HDD @ CH 1+401 - 1+551 (HDD-02) | Excavation for Entry & Exit Pit Preparation | HDD Section Readiness (Including hydrotest) | C-4N-H5HG-CNH2-1000 | C-4N-H5HG-CNH2-1010 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.9.1 HDD @ CH 1+401 - 1+551 (HDD-02) | P2543-R01-Oct24..4.3.1.5.4.12.3.9.1 HDD @ CH 1+401 - 1+551 (HDD-02) | HDD Section Readiness (Including hydrotest) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | C-4N-H5HG-CNH2-1010 | C-4N-H5HG-CNH2-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.9.1 HDD @ CH 1+401 - 1+551 (HDD-02) | P2543-R01-Oct24..4.3.1.5.4.12.3.9.1 HDD @ CH 1+401 - 1+551 (HDD-02) | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Re-Instatement of Entry & Exit Pit | C-4N-H5HG-CNH2-1020 | C-4N-H5HG-CNH2-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | Cleaning & Gauging | Water Filling | C-4W-SVHG-PIPEL-7400 | C-4W-SVHG-PIPEL-7410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | Water Filling | Pressurization | C-4W-SVHG-PIPEL-7410 | C-4W-SVHG-PIPEL-7420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | Pressurization | Holding of Test Pressure | C-4W-SVHG-PIPEL-7420 | C-4W-SVHG-PIPEL-7430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | Holding of Test Pressure | De-Pressurization | C-4W-SVHG-PIPEL-7430 | C-4W-SVHG-PIPEL-7600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | De-Pressurization | De-watering | C-4W-SVHG-PIPEL-7600 | C-4W-SVHG-PIPEL-7610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.4 Berm Construction | P2543-R01-Oct24..4.3.1.6.4.12.6.4 Berm Construction | Gatch Laying & Levelling | Gatch Compaction | C-4W-SVHG-PIPEL-6800 | C-4W-SVHG-PIPEL-6810 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.6.4.12.6.5 Marker Post & Crash Barrier | P2543-R01-Oct24..4.3.1.6.4.12.6.5 Marker Post & Crash Barrier | Installation of Marker Post/Sign Board | Installation of Crash Barriers (If any) | C-4W-SVHG-PIPEL-7800 | C-4W-SVHG-PIPEL-7810 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Survey Marking | Sabka ROW/Grading | C-4W-SVHG-PIPEL-1000 | C-4W-SVHG-PIPEL-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Sabka ROW/Grading | Sabka Gatch Laying (Including ROW) - Layer 1 | C-4W-SVHG-PIPEL-1800 | C-4W-SVHG-PIPEL-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Laying - Layer 2 | C-4W-SVHG-PIPEL-2000 | C-4W-SVHG-PIPEL-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Laying - Layer 3 | C-4W-SVHG-PIPEL-2010 | C-4W-SVHG-PIPEL-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Laying - Layer 4 | C-4W-SVHG-PIPEL-2020 | C-4W-SVHG-PIPEL-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Sabka Gatch Compaction - Layer 2 | C-4W-SVHG-PIPEL-2200 | C-4W-SVHG-PIPEL-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Sabka Gatch Compaction - Layer 2 | Sabka Gatch Compaction - Layer 3 | C-4W-SVHG-PIPEL-2210 | C-4W-SVHG-PIPEL-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Field Joint | Field Joint Protection Sleeve | C-4W-SVHG-PIPEL-3100 | C-4W-SVHG-PIPEL-3110 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Section Tie-in Joint | Field Joint Protection Sleeve | C-4W-SVHG-PIPEL-4810 | C-4W-SVHG-PIPEL-3120 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Field Joint Protection Sleeve | Padding | C-4W-SVHG-PIPEL-3120 | C-4W-SVHG-PIPEL-6000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | Section Tie-in Joint | Field Joint Protection Sleeve | CPL-4-CRMN-3350 | CPL-4-CRMN-3370 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | Field Joint Protection Sleeve | Padding | CPL-4-CRMN-3370 | CPL-4-CRMN-3390 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | Trench Excavation | Bedding | CPL-4-CRMN-3400 | CPL-4-CRMN-3410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | Bedding | Lowering | CPL-4-CRMN-3410 | CPL-4-CRMN-3420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | Lowering | Section Tie-in Joint | CPL-4-CRMN-3420 | CPL-4-CRMN-3430 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | Section Tie-in Joint | Field Joint Protection Sleeve | CPL-4-CRMN-3430 | CPL-4-CRMN-3440 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | Field Joint Protection Sleeve | Padding | CPL-4-CRMN-3440 | CPL-4-CRMN-3450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | Trench Excavation | Bedding | CPL-4-CRMN-3460 | CPL-4-CRMN-3470 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | Bedding | Lowering | CPL-4-CRMN-3470 | CPL-4-CRMN-3480 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | Lowering | Section Tie-in Joint | CPL-4-CRMN-3480 | CPL-4-CRMN-3490 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | Section Tie-in Joint | Field Joint Protection Sleeve | CPL-4-CRMN-3490 | CPL-4-CRMN-3500 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | Field Joint Protection Sleeve | Padding | CPL-4-CRMN-3500 | CPL-4-CRMN-3510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | Trench Excavation | Bedding | CPL-4-CRMN-3520 | CPL-4-CRMN-3530 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | Bedding | Lowering | CPL-4-CRMN-3530 | CPL-4-CRMN-3540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | Lowering | Section Tie-in Joint | CPL-4-CRMN-3540 | CPL-4-CRMN-3550 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | Section Tie-in Joint | Field Joint Protection Sleeve | CPL-4-CRMN-3550 | CPL-4-CRMN-3560 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | Field Joint Protection Sleeve | Padding | CPL-4-CRMN-3560 | CPL-4-CRMN-3570 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 Crossing Mechanical @ KP 1+772 (RX-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 Crossing Mechanical @ KP 1+772 (RX-02) | Trench Excavation | Bedding | CPL-4-CRMN-3580 | CPL-4-CRMN-3590 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 Crossing Mechanical @ KP 1+772 (RX-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 Crossing Mechanical @ KP 1+772 (RX-02) | Bedding | Lowering | CPL-4-CRMN-3590 | CPL-4-CRMN-3600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 Crossing Mechanical @ KP 1+772 (RX-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 Crossing Mechanical @ KP 1+772 (RX-02) | Lowering | Section Tie-in Joint | CPL-4-CRMN-3600 | CPL-4-CRMN-3610 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 Crossing Mechanical @ KP 1+772 (RX-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 Crossing Mechanical @ KP 1+772 (RX-02) | Section Tie-in Joint | Field Joint Protection Sleeve | CPL-4-CRMN-3610 | CPL-4-CRMN-3620 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 Crossing Mechanical @ KP 1+772 (RX-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 Crossing Mechanical @ KP 1+772 (RX-02) | Field Joint Protection Sleeve | Padding | CPL-4-CRMN-3620 | CPL-4-CRMN-3630 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.2.1 Piping Pre-FabricationCCOSWPI509 | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | Piping Pre-Fabrication | Piping Erection | C-52-D-HT-PI-1000 | C-52-D-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | P2543-R01-Oct24..4.3.1.3.3.21.2.3 Field Joint Welding, NDT & CoatingCCOSWPI534 | Piping Erection | Field Joint Welding | C-52-D-HT-PI-1200 | C-52-D-HT-PI-1400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.3.21.2.3 Field Joint Welding, NDT & CoatingCCOSWPI534 | P2543-R01-Oct24..4.3.1.3.3.21.2.3 Field Joint Welding, NDT & CoatingCCOSWPI534 | Field Joint Welding | NDT & Coating for Field Joint Weld | C-52-D-HT-PI-1400 | C-52-D-HT-PI-1410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.3.21.2.3 Field Joint Welding, NDT & CoatingCCOSWPI534 | P2543-R01-Oct24..4.3.1.3.3.21.2.4 HydrotestingCCOSWPI544 | NDT & Coating for Field Joint Weld | Hydrotesting | C-52-D-HT-PI-1410 | C-52-D-HT-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.2.4 HydrotestingCCOSWPI544 | P2543-R01-Oct24..4.3.1.3.3.21.2.5 Installation of ValvesCCOSWPI554 | Hydrotesting | Installation of Valves/GOV/ROV | C-52-D-HT-PI-1600 | C-52-D-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.2.5 Installation of ValvesCCOSWPI554 | P2543-R01-Oct24..4.3.1.3.3.21.2.6 Final Bolt Torquing/ Re-InstatementCCOSWPI564 | Installation of Valves/GOV/ROV | Final Bolt Torquing/ Re-Instatement | C-52-D-HT-PI-1800 | C-52-D-HT-PI-2000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.4.12.2.1 Piping Pre-FabricationCCOJ42PI070 | P2543-R01-Oct24..4.3.1.4.12.2.2 ErectionCCOJ42PI082 | Piping Pre-Fabrication | Piping Erection | C-36-KM-HT-PI-1000 | C-36-KM-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.2.2 ErectionCCOJ42PI082 | P2543-R01-Oct24..4.3.1.4.12.2.3 Field Joint Welding, NDT & CoatingCCOJ42PI092 | Piping Erection | Field Joint Welding | C-36-KM-HT-PI-1200 | C-36-KM-HT-PI-1400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.4.12.2.3 Field Joint Welding, NDT & CoatingCCOJ42PI092 | P2543-R01-Oct24..4.3.1.4.12.2.3 Field Joint Welding, NDT & CoatingCCOJ42PI092 | Field Joint Welding | NDT & Coating for Field Joint Weld | C-36-KM-HT-PI-1400 | C-36-KM-HT-PI-1410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.4.12.2.3 Field Joint Welding, NDT & CoatingCCOJ42PI092 | P2543-R01-Oct24..4.3.1.4.12.2.4 HydrotestingCCOJ42PI102 | NDT & Coating for Field Joint Weld | Hydrotesting | C-36-KM-HT-PI-1410 | C-36-KM-HT-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.2.4 HydrotestingCCOJ42PI102 | P2543-R01-Oct24..4.3.1.4.12.2.5 Installation of ValvesCCOJ42PI112 | Hydrotesting | Installation of Valves/GOV/ROV | C-36-KM-HT-PI-1600 | C-36-KM-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.2.5 Installation of ValvesCCOJ42PI112 | P2543-R01-Oct24..4.3.1.4.12.2.6 Final Bolt Torquing/ Re-InstatementCCOJ42PI122 | Installation of Valves/GOV/ROV | Final Bolt Torquing/ Re-Instatement | C-36-KM-HT-PI-1800 | C-36-KM-HT-PI-2000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.4.12.4.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT30 | P2543-R01-Oct24..4.3.1.4.12.4.2 Split Tee Welding (36" X 36")CCOJ42HT40 | Preparation, Marking & UT for Existing Line 36" Line | Split Tee Welding (36" X 36") | C-36-KM-HT03-ME-1000 | C-36-KM-HT03-ME-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.4.2 Split Tee Welding (36" X 36")CCOJ42HT40 | P2543-R01-Oct24..4.3.1.4.12.4.3 NDT & Testing for Split Tee Weld JointCCOJ42HT50 | Split Tee Welding (36" X 36") | NDT & Testing for Split Tee Weld Joint | C-36-KM-HT03-ME-1010 | C-36-KM-HT03-ME-1020 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.4.12.4.3 NDT & Testing for Split Tee Weld JointCCOJ42HT50 | P2543-R01-Oct24..4.3.1.4.12.4.4 Installation of ValvesCCOJ42HT60 | NDT & Testing for Split Tee Weld Joint | Installation of Valves | C-36-KM-HT03-ME-1020 | C-36-KM-HT03-ME-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.4.4 Installation of ValvesCCOJ42HT60 | P2543-R01-Oct24..4.3.1.4.12.4.5 Hot Tapping of Existing 36" LineCCOJ42HT70 | Installation of Valves | Hot Tapping of Existing 36" Line | C-36-KM-HT03-ME-1030 | C-36-KM-HT03-ME-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.4.5 Hot Tapping of Existing 36" LineCCOJ42HT70 | P2543-R01-Oct24..4.3.1.4.12.4.6 Isolation of Hot Tap JointCCOJ42HT80 | Hot Tapping of Existing 36" Line | Isolation of Hot Tap Joint | C-36-KM-HT03-ME-1040 | C-36-KM-HT03-ME-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.5.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT090 | P2543-R01-Oct24..4.3.1.4.12.5.2 Split Tee Welding (36" X 36")CCOJ42HT100 | Preparation, Marking & UT for Existing Line 36" Line | Split Tee Welding (36" X 36") | C-36-KM-HT04-ME-1000 | C-36-KM-HT04-ME-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.5.2 Split Tee Welding (36" X 36")CCOJ42HT100 | P2543-R01-Oct24..4.3.1.4.12.5.3 NDT & Testing for Split Tee Weld JointCCOJ42HT110 | Split Tee Welding (36" X 36") | NDT & Testing for Split Tee Weld Joint | C-36-KM-HT04-ME-1010 | C-36-KM-HT04-ME-1020 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.4.12.5.3 NDT & Testing for Split Tee Weld JointCCOJ42HT110 | P2543-R01-Oct24..4.3.1.4.12.5.4 Installation of ValvesCCOJ42HT120 | NDT & Testing for Split Tee Weld Joint | Installation of Valves | C-36-KM-HT04-ME-1020 | C-36-KM-HT04-ME-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.5.4 Installation of ValvesCCOJ42HT120 | P2543-R01-Oct24..4.3.1.4.12.5.5 Hot Tapping of Existing 36" LineCCOJ42HT130 | Installation of Valves | Hot Tapping of Existing 36" Line | C-36-KM-HT04-ME-1030 | C-36-KM-HT04-ME-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.5.5 Hot Tapping of Existing 36" LineCCOJ42HT130 | P2543-R01-Oct24..4.3.1.4.12.5.6 Isolation of Hot Tap JointCCOJ42HT140 | Hot Tapping of Existing 36" Line | Isolation of Hot Tap Joint | C-36-KM-HT04-ME-1040 | C-36-KM-HT04-ME-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.3.1 Preparation, Marking & UT for Existing Line 48" LineCCOSWHT461 | P2543-R01-Oct24..4.3.1.3.3.21.3.2 Split Tee Welding (48" X 30")CCOSWHT471 | Preparation, Marking & UT for Existing Line 48" Line | Split Tee Welding (48" X 30") | C-52-D-HT002-ME-1000 | C-52-D-HT002-ME-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.3.2 Split Tee Welding (48" X 30")CCOSWHT471 | P2543-R01-Oct24..4.3.1.3.3.21.3.3 NDT & Testing for Split Tee Weld JointCCOSWHT481 | Split Tee Welding (48" X 30") | NDT & Testing for Split Tee Weld Joint | C-52-D-HT002-ME-1010 | C-52-D-HT002-ME-1020 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.3.21.3.3 NDT & Testing for Split Tee Weld JointCCOSWHT481 | P2543-R01-Oct24..4.3.1.3.3.21.3.4 Installation of ValvesCCOSWHT491 | NDT & Testing for Split Tee Weld Joint | Installation of Valves | C-52-D-HT002-ME-1020 | C-52-D-HT002-ME-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.3.4 Installation of ValvesCCOSWHT491 | P2543-R01-Oct24..4.3.1.3.3.21.3.5 Hot Tapping of Existing 48" LineCCOSWHT501 | Installation of Valves | Hot Tapping of Existing 48" Line | C-52-D-HT002-ME-1030 | C-52-D-HT002-ME-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.3.5 Hot Tapping of Existing 48" LineCCOSWHT501 | P2543-R01-Oct24..4.3.1.3.3.21.3.6 Isolation of Hot Tap JointCCOSWHT511 | Hot Tapping of Existing 48" Line | Isolation of Hot Tap Joint | C-52-D-HT002-ME-1040 | C-52-D-HT002-ME-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.5.6 Isolation of Hot Tap JointCCOJ42HT140 | P2543-R01-Oct24..4.3.1.4.12.6.1 Tie -in WorksCCOJ42PI72 | Isolation of Hot Tap Joint | Tie-In with 36" Pipeline | C-36-KM-HT04-ME-1050 | C-36-KM-HT-ME-2000 | FS | Not Started | Not Started | 6
P2543-R01-Oct24..4.3.1.4.12.4.6 Isolation of Hot Tap JointCCOJ42HT80 | P2543-R01-Oct24..4.3.1.4.12.6.1 Tie -in WorksCCOJ42PI72 | Isolation of Hot Tap Joint | Tie-In with 36" Pipeline | C-36-KM-HT03-ME-1050 | C-36-KM-HT-ME-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.2.1 Piping Pre-FabricationCCOHBPI309 | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | Piping Pre-Fabrication | Piping Erection | C-56-G-HT-PI-1000 | C-56-G-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | P2543-R01-Oct24..4.3.1.1.3.10.2.3 Field Joint Welding & NDTCCOHBPI382 | Piping Erection | Field Joint Welding | C-56-G-HT-PI-1200 | C-56-G-HT-PI-1400 | SS | Not Started | Not Started | 6
P2543-R01-Oct24..4.3.1.1.3.10.2.3 Field Joint Welding & NDTCCOHBPI382 | P2543-R01-Oct24..4.3.1.1.3.10.2.3 Field Joint Welding & NDTCCOHBPI382 | Field Joint Welding | NDT & Coating for Field Joint Weld | C-56-G-HT-PI-1400 | C-56-G-HT-PI-1410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.1.3.10.2.3 Field Joint Welding & NDTCCOHBPI382 | P2543-R01-Oct24..4.3.1.1.3.10.2.4 HydrotestingCCOHBPI392 | NDT & Coating for Field Joint Weld | Hydrotesting | C-56-G-HT-PI-1410 | C-56-G-HT-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.2.4 HydrotestingCCOHBPI392 | P2543-R01-Oct24..4.3.1.1.3.10.2.5 Installation of ValvesCCOHBPI402 | Hydrotesting | Installation of Valves/GOV/ROV | C-56-G-HT-PI-1600 | C-56-G-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.2.5 Installation of ValvesCCOHBPI402 | P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | Installation of Valves/GOV/ROV | Final Bolt Torquing/ Re-Instatement | C-56-G-HT-PI-1800 | C-56-G-HT-PI-2000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.1.3.10.3.1 Preparation, Marking & UT for Existing Line 42" LineCCOHBHT265 | P2543-R01-Oct24..4.3.1.1.3.10.3.2 Split Tee Welding (42" X 42")CCOHBHT275 | Preparation, Marking & UT for Existing Line 42" Line | Split Tee Welding (42" X 42") | C-56-G-HT101-ME-1000 | C-56-G-HT101-ME-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.3.2 Split Tee Welding (42" X 42")CCOHBHT275 | P2543-R01-Oct24..4.3.1.1.3.10.3.3 NDT & Testing for Split Tee Weld JointCCOHBHT285 | Split Tee Welding (42" X 42") | NDT & Testing for Split Tee Weld Joint | C-56-G-HT101-ME-1010 | C-56-G-HT101-ME-1020 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.1.3.10.3.3 NDT & Testing for Split Tee Weld JointCCOHBHT285 | P2543-R01-Oct24..4.3.1.1.3.10.3.4 Installation of ValvesCCOHBHT295 | NDT & Testing for Split Tee Weld Joint | Installation of Valves | C-56-G-HT101-ME-1020 | C-56-G-HT101-ME-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.3.4 Installation of ValvesCCOHBHT295 | P2543-R01-Oct24..4.3.1.1.3.10.3.5 Hot Tapping of Existing 42" LineCCOHBHT305 | Installation of Valves | Hot Tapping of Existing 42" Line | C-56-G-HT101-ME-1030 | C-56-G-HT101-ME-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.3.5 Hot Tapping of Existing 42" LineCCOHBHT305 | P2543-R01-Oct24..4.3.1.1.3.10.3.6 Isolation of Hot Tap JointCCOHBHT315 | Hot Tapping of Existing 42" Line | Isolation of Hot Tap Joint | C-56-G-HT101-ME-1040 | C-56-G-HT101-ME-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.4.1 Preparation, Marking & UT for Existing Line 42" LineCCOHBHT325 | P2543-R01-Oct24..4.3.1.1.3.10.4.2 Split Tee Welding (42" X 30")CCOHBHT335 | Preparation, Marking & UT for Existing Line 30" Line | Split Tee Welding (30" X 30") | C-56-G-HT102-ME-1000 | C-56-G-HT102-ME-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.4.2 Split Tee Welding (42" X 30")CCOHBHT335 | P2543-R01-Oct24..4.3.1.1.3.10.4.3 NDT & Testing for Split Tee Weld JointCCOHBHT345 | Split Tee Welding (30" X 30") | NDT & Testing for Split Tee Weld Joint | C-56-G-HT102-ME-1010 | C-56-G-HT102-ME-1020 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.1.3.10.4.3 NDT & Testing for Split Tee Weld JointCCOHBHT345 | P2543-R01-Oct24..4.3.1.1.3.10.4.4 Installation of ValvesCCOHBHT355 | NDT & Testing for Split Tee Weld Joint | Installation of Valves | C-56-G-HT102-ME-1020 | C-56-G-HT102-ME-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.4.4 Installation of ValvesCCOHBHT355 | P2543-R01-Oct24..4.3.1.1.3.10.4.5 Hot Tapping of Existing 30" LineCCOHBHT365 | Installation of Valves | Hot Tapping of Existing 30" Line | C-56-G-HT102-ME-1030 | C-56-G-HT102-ME-1040 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.1.3.10.4.5 Hot Tapping of Existing 30" LineCCOHBHT365 | P2543-R01-Oct24..4.3.1.1.3.10.4.6 Isolation of Hot Tap JointCCOHBHT375 | Hot Tapping of Existing 30" Line | Isolation of Hot Tap Joint | C-56-G-HT102-ME-1040 | C-56-G-HT102-ME-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.5.1 Preparation, Marking & UT for Existing Line 42" LineCCOHBHT385 | P2543-R01-Oct24..4.3.1.1.3.10.5.2 Split Tee Welding (42" X 42")CCOHBHT395 | Preparation, Marking & UT for Existing Line 42" Line | Split Tee Welding (42" X 42") | C-56-G-HT103-ME-1000 | C-56-G-HT103-ME-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.5.2 Split Tee Welding (42" X 42")CCOHBHT395 | P2543-R01-Oct24..4.3.1.1.3.10.5.3 NDT & Testing for Split Tee Weld JointCCOHBHT405 | Split Tee Welding (42" X 42") | NDT & Testing for Split Tee Weld Joint | C-56-G-HT103-ME-1010 | C-56-G-HT103-ME-1020 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.1.3.10.5.3 NDT & Testing for Split Tee Weld JointCCOHBHT405 | P2543-R01-Oct24..4.3.1.1.3.10.5.4 Installation of ValvesCCOHBHT415 | NDT & Testing for Split Tee Weld Joint | Installation of Valves | C-56-G-HT103-ME-1020 | C-56-G-HT103-ME-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.5.4 Installation of ValvesCCOHBHT415 | P2543-R01-Oct24..4.3.1.1.3.10.5.5 Hot Tapping of Existing 42" LineCCOHBHT425 | Installation of Valves | Hot Tapping of Existing 42" Line | C-56-G-HT103-ME-1030 | C-56-G-HT103-ME-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.5.5 Hot Tapping of Existing 42" LineCCOHBHT425 | P2543-R01-Oct24..4.3.1.1.3.10.5.6 Isolation of Hot Tap JointCCOHBHT435 | Hot Tapping of Existing 42" Line | Isolation of Hot Tap Joint | C-56-G-HT103-ME-1040 | C-56-G-HT103-ME-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.3.6 Isolation of Hot Tap JointCCOHBHT315 | P2543-R01-Oct24..4.3.1.1.3.10.6.1 Tie-insCCOHBPI311 | Isolation of Hot Tap Joint | Tie-In with 30" Pipeline | C-56-G-HT101-ME-1050 | C-56-G-HT-ME-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.4.6 Isolation of Hot Tap JointCCOHBHT375 | P2543-R01-Oct24..4.3.1.1.3.10.6.1 Tie-insCCOHBPI311 | Isolation of Hot Tap Joint | Tie-In with 30" Pipeline | C-56-G-HT102-ME-1050 | C-56-G-HT-ME-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.5.6 Isolation of Hot Tap JointCCOHBHT435 | P2543-R01-Oct24..4.3.1.1.3.10.6.1 Tie-insCCOHBPI311 | Isolation of Hot Tap Joint | Tie-In with 30" Pipeline | C-56-G-HT103-ME-1050 | C-56-G-HT-ME-2000 | FS | Not Started | Not Started | 15
P2543-R01-Oct24..4.3.1.5.1.12.4.1 Piping Pre-FabricationCCOH4NPI050 | P2543-R01-Oct24..4.3.1.5.1.12.4.2 ErectionCCOH4NPI060 | Piping Pre-Fabrication | Piping Erection | C-4N-HG-TPR-PI-1000 | C-4N-HG-TPR-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.4.2 ErectionCCOH4NPI060 | P2543-R01-Oct24..4.3.1.5.1.12.4.3 Field Joint Welding, NDT & CoatingCCOH4NPI070 | Piping Erection | Field Joint Welding | C-4N-HG-TPR-PI-1200 | C-4N-HG-TPR-PI-1400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.5.1.12.4.3 Field Joint Welding, NDT & CoatingCCOH4NPI070 | P2543-R01-Oct24..4.3.1.5.1.12.4.3 Field Joint Welding, NDT & CoatingCCOH4NPI070 | Field Joint Welding | NDT & Coating for Field Joint Weld | C-4N-HG-TPR-PI-1400 | C-4N-HG-TPR-PI-1410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.5.1.12.4.3 Field Joint Welding, NDT & CoatingCCOH4NPI070 | P2543-R01-Oct24..4.3.1.5.1.12.4.4 HydrotestingCCOH4NPI080 | NDT & Coating for Field Joint Weld | Hydrotesting | C-4N-HG-TPR-PI-1410 | C-4N-HG-TPR-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.4.4 HydrotestingCCOH4NPI080 | P2543-R01-Oct24..4.3.1.5.1.12.4.5 Installation of ValvesCCOH4NPI090 | Hydrotesting | Installation of Valves/MOV/ROV | C-4N-HG-TPR-PI-1600 | C-4N-HG-TPR-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.4.5 Installation of ValvesCCOH4NPI090 | P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | Installation of Valves/MOV/ROV | Final Bolt Torquing/ Re-Instatement | C-4N-HG-TPR-PI-1800 | C-4N-HG-TPR-PI-2000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.5.2.3.12.4.1 Piping Pre-FabricationCCOH5PI501 | P2543-R01-Oct24..4.3.1.5.2.3.12.4.2 ErectionCCOH5PI515 | Piping Pre-Fabrication | Piping Erection | C-4N-H5-TPL-PI-1000 | C-4N-H5-TPL-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.4.2 ErectionCCOH5PI515 | P2543-R01-Oct24..4.3.1.5.2.3.12.4.3 Field Joint Welding, NDT & CoatingCCOH5PI525 | Piping Erection | Field Joint Welding | C-4N-H5-TPL-PI-1200 | C-4N-H5-TPL-PI-1400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.5.2.3.12.4.3 Field Joint Welding, NDT & CoatingCCOH5PI525 | P2543-R01-Oct24..4.3.1.5.2.3.12.4.3 Field Joint Welding, NDT & CoatingCCOH5PI525 | Field Joint Welding | NDT & Coating for Field Joint Weld | C-4N-H5-TPL-PI-1400 | C-4N-H5-TPL-PI-1410 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.5.2.3.12.4.3 Field Joint Welding, NDT & CoatingCCOH5PI525 | P2543-R01-Oct24..4.3.1.5.2.3.12.4.4 HydrotestingCCOH5PI535 | NDT & Coating for Field Joint Weld | Hydrotesting | C-4N-H5-TPL-PI-1410 | C-4N-H5-TPL-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.4.4 HydrotestingCCOH5PI535 | P2543-R01-Oct24..4.3.1.5.2.3.12.4.5 Installation of ValvesCCOH5PI545 | Hydrotesting | Installation of Valves/MOV/ROV | C-4N-H5-TPL-PI-1600 | C-4N-H5-TPL-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.4.5 Installation of ValvesCCOH5PI545 | P2543-R01-Oct24..4.3.1.5.2.3.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH5PI555 | Installation of Valves/MOV/ROV | Final Bolt Torquing/ Re-Instatement | C-4N-H5-TPL-PI-1800 | C-4N-H5-TPL-PI-2000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | Excavation (Manual-Trial Pit) | Excavation (Manual-Trial Pit) | C-52-0102-CMA04-0970 | C-52-0102-CMA05-0970 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0102-CMA05-0970 | C-52-0102-CMA01-0980 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | Sabkha Gatch Laying | Sabkha Gatch Laying | C-52-0102-CMA01-0980 | C-52-0102-CMA02-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | Sabkha Gatch Laying | Sabkha Gatch Laying | C-52-0102-CMA02-0980 | C-52-0102-CMA03-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | P2543-R01-Oct24..4.3.1.3.8.21.1.24 Test Stations & Anode BedsCCOP52EL34 | Lowering | Installation of Temp. Anode | C-52-0102-PL-ME-4800 | C-52-0102-PL-CA-5600 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Holiday Testing | Installation of Test Post for Crossing | C-52-0102-CMA04-1060 | C-52-0102-PL-CA-5220 | FS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.8.21.2.6.2 Tunneling & Jack UpCCOPL58002 | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Inner Grout b/w Main & RC Pipe | Installation of CP TR | C-52-0102-CNM05-1220 | C-52-0102-PL-CA-5240 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.8.21.1.22 PaddingCCOPL52330 | P2543-R01-Oct24..4.3.1.3.8.21.5.1 Telecom Works along PipelineCCOP52IC52 | Padding | FO - Cable Pulling/ Laying | C-52-0102-PL-CI-6000 | C-52-0102-PL-TE-8200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Padding | Cleaning & Gauging | C-52-0102-CMA04-1070 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.22 PaddingCCOPL52330 | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Padding | Cleaning & Gauging | C-52-0102-PL-CI-6000 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Padding | Cleaning & Gauging | C-52-0102-CMA05-1070 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Padding | Cleaning & Gauging | C-52-0102-CMA01-1070 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Padding | Cleaning & Gauging | C-52-0102-CMA02-1070 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Padding | Cleaning & Gauging | C-52-0102-CMA03-1070 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Padding & Back Filling | Cleaning & Gauging | C-52-0102-CME01-1070 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Padding & Back Filling | Cleaning & Gauging | C-52-0102-CME02-1070 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Padding & Back Filling | Cleaning & Gauging | C-52-0102-CME03-1070 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Padding & Back Filling | Cleaning & Gauging | C-52-0102-CME04-1070 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Padding & Back Filling | Cleaning & Gauging | C-52-0102-CME05-1070 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.3 Re-Instatement of Entry & Exit PitCCOPL58212 | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-52-0102-CNH10-1800 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.2.3 Re-Instatement of Entry & Exit PitCCOPL58272 | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-52-0102-CNH09-1800 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.4.5 Re-Instatement of Entry & Exit PitCCOPL57322 | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-52-0102-CNM07-1800 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.6.5 Re-Instatement of Entry & Exit PitCCOPL58032 | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-52-0102-CNM05-1800 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.3.2 Tunneling & Jack UpCCOPL58322 | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Inner Grout b/w Main & RC Pipe | Cleaning & Gauging | C-52-0102-CNH08-1220 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.22 PaddingCCOPL52330 | P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | Padding | Gatch Laying & Levelling | C-52-0102-PL-CI-6000 | C-52-0102-PL-CI-6800 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | Gatch Compaction | Installation of Marker Post/Sign Board | C-52-0102-PL-CI-6810 | C-52-0102-PL-CI-7800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | Trench Excavation-Lot1 | Excavation (Manual-Trial Pit) | C-52-HG01-PL-CI-2400 | C-52-HG01-CMA01-0970 | FS | Completed | Not Started | 5
P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | Excavation (Manual-Trial Pit) | Excavation (Manual-Trial Pit) | C-52-HG01-CMA01-0970 | C-52-HG01-CMA05-0970 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | Lowering-Lot1 | Trench Excavation | C-52-HG01-PL-ME-4800 | C-52-HG01-CME01-1000 | SS | Completed | Completed | 2
P2543-R01-Oct24..4.3.1.3.8.21.1.21 CP Works TemporaryCCOP52EL35 | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Glanding & Termination of Temp. CP S/m | CIP/DCVG Survey | C-52-0102-PL-CA-5210 | C-52-0102-PL-CA-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.29 Test Stations & Anode BedsCCOP52EL31 | Lowering-Lot1 | Installation of Temp. Anode | C-52-HG01-PL-ME-4800 | C-52-HG01-PL-CA-5600 | SS | Completed | In Progress | 7
P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Holiday Testing | Installation of Test Post for Crossing | C-52-HG01-CMA01-1060 | C-52-HG01-PL-CA-5220 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | P2543-R01-Oct24..4.3.1.3.2.21.1.26 CP Works TemporaryCCOP52EL56 | Padding -Lot1 | Glanding & Termination of Temp. CP S/m | C-52-HG01-PL-CI-6000 | C-52-HG01-PL-CA-5210 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.26 CP Works TemporaryCCOP52EL56 | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Glanding & Termination of Temp. CP S/m | CIP/DCVG Survey (Pre-Com) | C-52-HG01-PL-CA-5210 | C-52-HG01-PL-CA-5250 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.3.2 Tunneling & Jack UpCCOPL58042 | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Inner Grout b/w Main & RC Pipe | Installation of CP TR | C-52-HG01-CNM02-1220 | C-52-HG01-PL-CA-5240 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | P2543-R01-Oct24..4.3.1.3.2.21.4.1 Telecom Works along Pipeline CCOP52IC57 | Padding -Lot1 | FO - Cable Pulling/ Laying | C-52-HG01-PL-CI-6000 | C-52-HG01-PL-TE-8200 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Padding -Lot1 | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-PL-CI-6000 | C-52-HG01-PL-ME-7400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Padding | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-CMA01-1070 | C-52-HG01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Padding | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-CMA05-1070 | C-52-HG01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Padding | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-CMA06-1070 | C-52-HG01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Padding | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-CMA07-1070 | C-52-HG01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Padding | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-CMA02-1070 | C-52-HG01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Padding | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-CMA03-1070 | C-52-HG01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Padding | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-CMA04-1070 | C-52-HG01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Padding & Back Filling | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-CME01-1070 | C-52-HG01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Padding & Back Filling | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-CME02-1070 | C-52-HG01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Padding & Back Filling | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-CME03-1070 | C-52-HG01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57362 | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-CNM04-1800 | C-52-HG01-PL-ME-7400 | FF | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.2.21.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57712 | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-CNM03-1800 | C-52-HG01-PL-ME-7400 | FF | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.2.21.2.3.5 Re-Instatement of Entry & Exit PitCCOPL58072 | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-CNM02-1800 | C-52-HG01-PL-ME-7400 | FF | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | P2543-R01-Oct24..4.3.1.3.2.21.1.27 BermingCCOPL52316 | Padding -Lot1 | Gatch Laying & Levelling | C-52-HG01-PL-CI-6000 | C-52-HG01-PL-CI-6800 | SS | In Progress | In Progress | 5
P2543-R01-Oct24..4.3.1.3.2.21.1.27 BermingCCOPL52316 | P2543-R01-Oct24..4.3.2.3.10.8.2.4 ROW Restoration from BVS-01 to HGCP/Marker PostCCOPL52324.1 | Gatch Compaction | Installation of Marker Post/Sign Board | C-52-HG01-PL-CI-6810 | C-52-HG01-PL-CI-7800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.7 Excavation (incl Bedding)CCOPL52371 | P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | Trench Excavation | Excavation (Manual-Trial Pit) | C-52-0203-PL-CI-2400 | C-52-0203-CMA01-970 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | Excavation (Manual-Trial Pit) | Trench Excavation | C-52-0203-CMA01-970 | C-52-0203-CMA02-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | P2543-R01-Oct24..4.3.1.3.15.21.1.20 Test Stations & Anode BedsCCOP52EL36 | Lowering | Installation of Temp. Anode | C-52-0203-PL-ME-4800 | C-52-0203-PL-CA-5600 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | P2543-R01-Oct24..4.3.1.3.15.21.1.17 CP Works TemporaryCCOP52EL38 | Padding | Glanding & Termination of Temp. CP S/m | C-52-0203-PL-CI-6000 | C-52-0203-PL-CA-5210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | Holiday Testing | Installation of Test Post for Crossing | C-52-0203-CMA01-1060 | C-52-0203-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0203-CMA02-1070 | C-52-0203-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0203-CME01-1070 | C-52-0203-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0203-CME02-1070 | C-52-0203-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0203-CME03-1070 | C-52-0203-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | P2543-R01-Oct24..4.3.1.3.15.21.1.17 CP Works TemporaryCCOP52EL38 | Installation of CP TR | Glanding & Termination of Temp. CP S/m | C-52-0203-PL-CA-5240 | C-52-0203-PL-CA-5210 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Section Tie-in Welding | Section Tie-in Welding | C-52-0203-CMA01-1030 | C-52-0203-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Section Tie-in Welding | Section Tie-in Welding | C-52-0203-CMA02-1030 | C-52-0203-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Section Tie-in Welding | Section Tie-in Welding | C-52-0203-CME01-1030 | C-52-0203-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Section Tie-in Welding | Section Tie-in Welding | C-52-0203-CME02-1030 | C-52-0203-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Section Tie-in Welding | Section Tie-in Welding | C-52-0203-CME03-1030 | C-52-0203-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | Padding | FO - Cable Pulling/ Laying | C-52-0203-PL-CI-6000 | C-52-0203-PL-TE-8200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | Padding | FO - Cable Pulling/ Laying | C-52-0203-CMA01-1070 | C-52-0203-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0203-CMA02-1070 | C-52-0203-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0203-CME01-1070 | C-52-0203-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0203-CME02-1070 | C-52-0203-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0203-CME03-1070 | C-52-0203-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Padding | Cleaning & Gauging | C-52-0203-PL-CI-6000 | C-52-0203-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Padding | Cleaning & Gauging | C-52-0203-CMA01-1070 | C-52-0203-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Padding & Back Filling | Cleaning & Gauging | C-52-0203-CMA02-1070 | C-52-0203-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Padding & Back Filling | Cleaning & Gauging | C-52-0203-CME01-1070 | C-52-0203-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Padding & Back Filling | Cleaning & Gauging | C-52-0203-CME02-1070 | C-52-0203-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Padding & Back Filling | Cleaning & Gauging | C-52-0203-CME03-1070 | C-52-0203-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | Padding | Gatch Laying & Levelling | C-52-0203-CMA01-1070 | C-52-0203-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0203-CMA02-1070 | C-52-0203-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0203-CME01-1070 | C-52-0203-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0203-CME02-1070 | C-52-0203-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0203-CME03-1070 | C-52-0203-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | Stringing (BVS-02 to BVS-03) | Lowering | C-52-0203-PL-ME-2800 | C-52-0203-CME01-1020 | SS | Completed | Not Started | 5
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | Sabka Gatch Compaction (Including ROW) - Layer 1 | Excavation (Manual-Trial Pit) | C-52-0304-PL-CI-2200 | C-52-0304-CMA04-0970 | SS | In Progress | Not Started | 21
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | Excavation (Manual-Trial Pit) | Excavation (Manual-Trial Pit) | C-52-0304-CMA04-0970 | C-52-0304-CMA05-0970 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0304-CMA05-0970 | C-52-0304-CMA01-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | Sabkha Gatch Laying | Excavation (Manual-Trial Pit) | C-52-0304-CMA01-0980 | C-52-0304-CMA07-0970 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0304-CMA07-0970 | C-52-0304-CMA02-980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | Sabkha Gatch Laying | Excavation (Manual-Trial Pit) | C-52-0304-CMA02-980 | C-52-0304-CMA14-0970 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | Excavation (Manual-Trial Pit) | Excavation (Manual-Trial Pit) | C-52-0304-CMA14-0970 | C-52-0304-CMA09-0970 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | Excavation (Manual-Trial Pit) | Excavation (Manual-Trial Pit) | C-52-0304-CMA09-0970 | C-52-0304-CMA06-0970 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | Excavation (Manual-Trial Pit) | Trench Excavation | C-52-0304-CMA06-0970 | C-52-0304-CMA11-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | Trench Excavation | Trench Excavation | C-52-0304-CMA11-1000 | C-52-0304-CMA12-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | Trench Excavation | Trench Excavation | C-52-0304-CMA12-1000 | C-52-0304-CMA13-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | Trench Excavation | Trench Excavation | C-52-0304-CMA03-1000 | C-52-0304-CMA08-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | Trench Excavation | Trench Excavation | C-52-0304-CMA08-1000 | C-52-0304-CMA10-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | Trench Excavation | Trench Excavation | C-52-0304-CME04-1000 | C-52-0304-CME05-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | Lowering | Lowering | C-52-0304-CME01-1020 | C-52-0304-CME02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | Lowering | Lowering | C-52-0304-CME02-1020 | C-52-0304-CME03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | Lowering | Lowering | C-52-0304-CME03-1020 | C-52-0304-CME04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | Lowering | Lowering | C-52-0304-CME04-1020 | C-52-0304-CME05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | Lowering | Lowering | C-52-0304-CME05-1020 | C-52-0304-CME06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | Lowering | Lowering | C-52-0304-CME06-1020 | C-52-0304-CME07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | Lowering | Lowering | C-52-0304-CME07-1020 | C-52-0304-CME08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | Lowering | Lowering | C-52-0304-CME08-1020 | C-52-0304-CME09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | Lowering | Lowering | C-52-0304-CME09-1020 | C-52-0304-CME10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | Lowering | Lowering | C-52-0304-CME10-1020 | C-52-0304-CME11-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | Lowering | Lowering | C-52-0304-CME11-1020 | C-52-0304-CME12-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | Stringing (BVS-03 to BVS-04) | Lowering | C-52-0304-PL-ME-2800 | C-52-0304-CMA04-1020 | FS | In Progress | Not Started | 7
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | Lowering | Lowering | C-52-0304-CMA04-1020 | C-52-0304-CMA05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | Lowering | Lowering | C-52-0304-CMA05-1020 | C-52-0304-CMA01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | Lowering | Lowering | C-52-0304-CMA01-1020 | C-52-0304-CMA07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | Lowering | Lowering | C-52-0304-CMA07-1020 | C-52-0304-CMA02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | Lowering | Lowering | C-52-0304-CMA02-1020 | C-52-0304-CMA14-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | Lowering | Lowering | C-52-0304-CMA14-1020 | C-52-0304-CMA09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | Lowering | Lowering | C-52-0304-CMA09-1020 | C-52-0304-CMA06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | Lowering | Lowering | C-52-0304-CMA06-1020 | C-52-0304-CMA11-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | Lowering | Lowering | C-52-0304-CMA11-1020 | C-52-0304-CMA12-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | Lowering | Lowering | C-52-0304-CMA12-1020 | C-52-0304-CMA13-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | Lowering | Lowering | C-52-0304-CMA13-1020 | C-52-0304-CMA03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | Lowering | Lowering | C-52-0304-CMA03-1020 | C-52-0304-CMA08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | Lowering | Lowering | C-52-0304-CMA08-1020 | C-52-0304-CMA10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | Stringing (BVS-03 to BVS-04) | Lowering | C-52-0304-PL-ME-2800 | C-52-0304-CME01-1020 | FS | In Progress | Not Started | 7
P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | P2543-R01-Oct24..4.3.1.3.16.21.1.23 Test Stations & Anode BedsCCOP52EL39 | Holiday Testing | Installation of Temp. Anode | C-52-0304-PL-ME-4830 | C-52-0304-PL-CA-5600 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | P2543-R01-Oct24..4.3.1.3.16.21.1.19 CP Works TemporaryCCOP52EL41 | Padding | Glanding & Termination of Temp. CP S/m | C-52-0304-PL-CI-6000 | C-52-0304-PL-CA-5210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Holiday Testing | Installation of Test Post for Crossing | C-52-0304-CMA04-1060 | C-52-0304-PL-CA-5220 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding | Installation of Test Post for Crossing | C-52-0304-CMA01-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding | Installation of Test Post for Crossing | C-52-0304-CMA07-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding | Installation of Test Post for Crossing | C-52-0304-CMA02-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding | Installation of Test Post for Crossing | C-52-0304-CMA14-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding | Installation of Test Post for Crossing | C-52-0304-CMA09-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding | Installation of Test Post for Crossing | C-52-0304-CMA06-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding | Installation of Test Post for Crossing | C-52-0304-CMA11-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding | Installation of Test Post for Crossing | C-52-0304-CMA12-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding | Installation of Test Post for Crossing | C-52-0304-CMA13-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding | Installation of Test Post for Crossing | C-52-0304-CMA03-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding | Installation of Test Post for Crossing | C-52-0304-CMA08-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding | Installation of Test Post for Crossing | C-52-0304-CMA10-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0304-CME01-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0304-CME02-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0304-CME03-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0304-CME04-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0304-CME05-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0304-CME06-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0304-CME07-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0304-CME08-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0304-CME09-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0304-CME10-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0304-CME11-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0304-CME12-1070 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding | FO - Cable Pulling/ Laying | C-52-0304-PL-CI-6000 | C-52-0304-PL-TE-8200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding | FO - Cable Pulling/ Laying | C-52-0304-CMA04-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding | FO - Cable Pulling/ Laying | C-52-0304-CMA05-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding | FO - Cable Pulling/ Laying | C-52-0304-CMA01-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding | FO - Cable Pulling/ Laying | C-52-0304-CMA07-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding | FO - Cable Pulling/ Laying | C-52-0304-CMA02-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding | FO - Cable Pulling/ Laying | C-52-0304-CMA14-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding | FO - Cable Pulling/ Laying | C-52-0304-CMA09-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding | FO - Cable Pulling/ Laying | C-52-0304-CMA06-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding | FO - Cable Pulling/ Laying | C-52-0304-CMA11-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding | FO - Cable Pulling/ Laying | C-52-0304-CMA12-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding | FO - Cable Pulling/ Laying | C-52-0304-CMA13-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding | FO - Cable Pulling/ Laying | C-52-0304-CMA03-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding | FO - Cable Pulling/ Laying | C-52-0304-CMA08-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding | FO - Cable Pulling/ Laying | C-52-0304-CMA10-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0304-CME01-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0304-CME02-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0304-CME03-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0304-CME04-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0304-CME05-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0304-CME06-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0304-CME07-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0304-CME08-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0304-CME09-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0304-CME10-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0304-CME11-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0304-CME12-1070 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CMA04-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CMA05-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CMA01-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CMA07-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CMA02-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CMA14-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CMA09-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CMA06-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CMA11-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CMA12-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CMA13-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CMA03-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CMA08-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CMA10-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CME01-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CME02-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CME03-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CME04-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CME05-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CME06-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CME07-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CME08-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CME09-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CME10-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CME11-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | Section Tie-in Welding | C-52-0304-CME12-1030 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding | Cleaning & Gauging | C-52-0304-PL-CI-6000 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding | Cleaning & Gauging | C-52-0304-CMA04-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding | Cleaning & Gauging | C-52-0304-CMA05-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding | Cleaning & Gauging | C-52-0304-CMA01-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding | Cleaning & Gauging | C-52-0304-CMA07-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding | Cleaning & Gauging | C-52-0304-CMA02-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding | Cleaning & Gauging | C-52-0304-CMA14-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding | Cleaning & Gauging | C-52-0304-CMA09-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding | Cleaning & Gauging | C-52-0304-CMA06-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding | Cleaning & Gauging | C-52-0304-CMA11-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding | Cleaning & Gauging | C-52-0304-CMA12-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding | Cleaning & Gauging | C-52-0304-CMA13-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding | Cleaning & Gauging | C-52-0304-CMA03-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding | Cleaning & Gauging | C-52-0304-CMA08-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding | Cleaning & Gauging | C-52-0304-CMA10-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding & Back Filling | Cleaning & Gauging | C-52-0304-CME01-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding & Back Filling | Cleaning & Gauging | C-52-0304-CME02-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding & Back Filling | Cleaning & Gauging | C-52-0304-CME03-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding & Back Filling | Cleaning & Gauging | C-52-0304-CME04-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding & Back Filling | Cleaning & Gauging | C-52-0304-CME05-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding & Back Filling | Cleaning & Gauging | C-52-0304-CME06-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding & Back Filling | Cleaning & Gauging | C-52-0304-CME07-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding & Back Filling | Cleaning & Gauging | C-52-0304-CME08-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding & Back Filling | Cleaning & Gauging | C-52-0304-CME09-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding & Back Filling | Cleaning & Gauging | C-52-0304-CME10-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding & Back Filling | Cleaning & Gauging | C-52-0304-CME11-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Padding & Back Filling | Cleaning & Gauging | C-52-0304-CME12-1070 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding | Gatch Laying & Levelling | C-52-0304-PL-CI-6000 | C-52-0304-PL-CI-6800 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding | Gatch Laying & Levelling | C-52-0304-CMA04-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding | Gatch Laying & Levelling | C-52-0304-CMA05-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding | Gatch Laying & Levelling | C-52-0304-CMA01-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding | Gatch Laying & Levelling | C-52-0304-CMA07-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding | Gatch Laying & Levelling | C-52-0304-CMA02-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding | Gatch Laying & Levelling | C-52-0304-CMA14-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding | Gatch Laying & Levelling | C-52-0304-CMA09-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding | Gatch Laying & Levelling | C-52-0304-CMA06-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding | Gatch Laying & Levelling | C-52-0304-CMA11-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding | Gatch Laying & Levelling | C-52-0304-CMA12-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding | Gatch Laying & Levelling | C-52-0304-CMA13-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding | Gatch Laying & Levelling | C-52-0304-CMA03-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding | Gatch Laying & Levelling | C-52-0304-CMA08-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding | Gatch Laying & Levelling | C-52-0304-CMA10-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0304-CME01-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0304-CME02-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0304-CME03-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0304-CME04-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0304-CME05-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0304-CME06-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0304-CME07-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0304-CME08-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0304-CME09-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0304-CME10-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0304-CME11-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0304-CME12-1070 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Gatch Compaction | Installation of Marker Post/Sign Board | C-52-0304-PL-CI-6810 | C-52-0304-PL-CI-7800 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | Trench Excavation | Trench Excavation | C-52-0405-CMA01-1000 | C-52-0405-CMA25-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | Trench Excavation | Trench Excavation | C-52-0405-CMA25-1000 | C-52-0405-CMA20-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | Trench Excavation | Trench Excavation | C-52-0405-CMA20-1000 | C-52-0405-CMA26-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | Trench Excavation | Trench Excavation | C-52-0405-CMA26-1000 | C-52-0405-CMA21-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | Excavation (Manual-Trial Pit) | Sabkha Gatch Laying | C-52-0405-CMA03-0970 | C-52-0405-CMA28-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | Sabkha Gatch Laying | Sabkha Gatch Laying | C-52-0405-CMA28-0980 | C-52-0405-CMA29-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | Excavation (Manual-Trial Pit) | Trench Excavation | C-52-0405-CMA23-1000 | C-52-0405-CMA04-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | Trench Excavation | Trench Excavation | C-52-0405-CMA31-1000 | C-52-0405-CMA05-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | Trench Excavation | Trench Excavation | C-52-0405-CMA04-1000 | C-52-0405-CMA06-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | Trench Excavation | Trench Excavation | C-52-0405-CMA05-1000 | C-52-0405-CMA07-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | Trench Excavation | Trench Excavation | C-52-0405-CMA07-1000 | C-52-0405-CMA09-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | Trench Excavation | Trench Excavation | C-52-0405-CMA08-1000 | C-52-0405-CMA10-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | Trench Excavation | Trench Excavation | C-52-0405-CMA09-1000 | C-52-0405-CMA11-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | Trench Excavation | Trench Excavation | C-52-0405-CMA10-1000 | C-52-0405-CMA12-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | Trench Excavation | Trench Excavation | C-52-0405-CMA11-1000 | C-52-0405-CMA13-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | Trench Excavation | Trench Excavation | C-52-0405-CMA12-1000 | C-52-0405-CMA14-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | Trench Excavation | Trench Excavation | C-52-0405-CMA13-1000 | C-52-0405-CMA15-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | Trench Excavation | Trench Excavation | C-52-0405-CMA14-1000 | C-52-0405-CMA24-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | Trench Excavation | Trench Excavation | C-52-0405-CMA15-1000 | C-52-0405-CMA16-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | Trench Excavation | Trench Excavation | C-52-0405-CMA24-1000 | C-52-0405-CMA17-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | Trench Excavation | Trench Excavation | C-52-0405-CMA16-1000 | C-52-0405-CMA18-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | Trench Excavation | Trench Excavation | C-52-0405-CMA17-1000 | C-52-0405-CMA19-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | Trench Excavation | Trench Excavation | C-52-0405-CMA18-1000 | C-52-0405-CMA32-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | P2543-R01-Oct24..4.3.1.3.17.21.1.26 Test Stations & Anode BedsCCOP52EL42 | Holiday Testing | Installation of Temp. Anode | C-52-0405-PL-ME-4830 | C-52-0405-PL-CA-5600 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA01-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA25-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA20-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA26-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA21-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA27-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA22-1060 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA02-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA03-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA28-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA29-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA30-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA23-1060 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA31-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA04-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA05-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA06-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA07-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA08-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA09-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA10-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA11-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA12-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA13-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA14-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA15-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA24-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA16-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA17-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA18-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA19-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CMA32-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CME01-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CME02-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CME03-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CME04-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CME05-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CME06-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CME07-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CME08-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57112 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Lowering & Welding of Carrier Pipe | Section Tie-in Welding | C-52-0405-CNM17-1400 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57772 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Lowering & Welding of Carrier Pipe | Section Tie-in Welding | C-52-0405-CNM18-1400 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Lowering & Welding of Carrier Pipe | Section Tie-in Welding | C-52-0405-CNH19-1070 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Lowering & Welding of Carrier Pipe | Section Tie-in Welding | C-52-0405-CNH20-1070 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.6.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57732 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Lowering & Welding of Carrier Pipe | Section Tie-in Welding | C-52-0405-CNM23-1400 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Lowering & Welding of Carrier Pipe | Section Tie-in Welding | C-52-0405-CNH24-1070 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | P2543-R01-Oct24..4.3.1.3.17.21.1.21 CP Works TemporaryCCOP52EL43 | Padding | Glanding & Termination of Temp. CP S/m | C-52-0405-PL-CI-6000 | C-52-0405-PL-CA-5210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Holiday Testing | Installation of Test Post for Crossing | C-52-0405-CMA01-1060 | C-52-0405-PL-CA-5220 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA25-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA20-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA26-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA21-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA27-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA22-1100 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA02-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA03-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA28-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA29-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA30-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA23-1100 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA31-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA04-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA05-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA06-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA07-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA08-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA09-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA10-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA11-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA12-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA13-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA14-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA15-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA24-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA16-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA17-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA18-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA19-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding | Installation of Test Post for Crossing | C-52-0405-CMA32-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0405-CME01-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0405-CME02-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0405-CME03-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0405-CME04-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0405-CME05-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0405-CME06-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0405-CME07-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0405-CME08-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.2.2 Tunneling & Jack UpCCOPL57102 | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-52-0405-CNM17-1220 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.3.2 Tunneling & Jack UpCCOPL57762 | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-52-0405-CNM18-1220 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.8.4.2 Tunneling & Jack UpCCOPL58142 | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-52-0405-CNH19-1220 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 Tunneling & Jack UpCCOPL58302 | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-52-0405-CNH20-1220 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.6.2 Tunneling & Jack UpCCOPL57722 | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-52-0405-CNM23-1220 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.8.7.2 Tunneling & Jack UpCCOPL58242 | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-52-0405-CNH24-1220 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | P2543-R01-Oct24..4.3.1.3.17.21.1.21 CP Works TemporaryCCOP52EL43 | Installation of CP TR | Glanding & Termination of Temp. CP S/m | C-52-0405-PL-CA-5240 | C-52-0405-PL-CA-5210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-PL-CI-6000 | C-52-0405-PL-TE-8200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA01-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA25-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA20-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA26-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA21-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA27-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA22-1100 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA02-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA03-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA28-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA29-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA30-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA23-1100 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA31-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA04-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA05-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA06-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA07-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA08-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA09-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA10-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA11-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA12-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA13-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA14-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA15-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA24-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA16-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA17-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA18-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA19-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding | FO - Cable Pulling/ Laying | C-52-0405-CMA32-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0405-CME01-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0405-CME02-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0405-CME03-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0405-CME04-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0405-CME05-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0405-CME06-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0405-CME07-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0405-CME08-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57132 | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | FO - Cable Pulling/ Laying | C-52-0405-CNM17-1800 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.3.5 Re-Instatement of Entry & Exit PitCCOPL57792 | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | FO - Cable Pulling/ Laying | C-52-0405-CNM18-1800 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.3 Re-Instatement of Entry & Exit PitCCOPL58152 | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | FO - Cable Pulling/ Laying | C-52-0405-CNH19-1800 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.3 Re-Instatement of Entry & Exit PitCCOPL58312 | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | FO - Cable Pulling/ Laying | C-52-0405-CNH20-1800 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.6.5 Re-Instatement of Entry & Exit PitCCOPL57752 | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | FO - Cable Pulling/ Laying | C-52-0405-CNM23-1800 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.7.3 Re-Instatement of Entry & Exit PitCCOPL58252 | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | FO - Cable Pulling/ Laying | C-52-0405-CNH24-1800 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-PL-CI-6000 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA01-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA25-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA20-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA26-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA21-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA27-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA22-1100 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA02-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA03-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA28-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA29-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA30-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA23-1100 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA31-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA04-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA05-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA06-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA07-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA08-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA09-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA10-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA11-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA12-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA13-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA14-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA15-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA24-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA16-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA17-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA18-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA19-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding | Cleaning & Gauging | C-52-0405-CMA32-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding & Back Filling | Cleaning & Gauging | C-52-0405-CME01-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding & Back Filling | Cleaning & Gauging | C-52-0405-CME02-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding & Back Filling | Cleaning & Gauging | C-52-0405-CME03-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding & Back Filling | Cleaning & Gauging | C-52-0405-CME04-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding & Back Filling | Cleaning & Gauging | C-52-0405-CME05-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding & Back Filling | Cleaning & Gauging | C-52-0405-CME06-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding & Back Filling | Cleaning & Gauging | C-52-0405-CME07-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding & Back Filling | Cleaning & Gauging | C-52-0405-CME08-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57132 | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-52-0405-CNM17-1800 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.3.5 Re-Instatement of Entry & Exit PitCCOPL57792 | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-52-0405-CNM18-1800 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.3 Re-Instatement of Entry & Exit PitCCOPL58152 | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-52-0405-CNH19-1800 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.3 Re-Instatement of Entry & Exit PitCCOPL58312 | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-52-0405-CNH20-1800 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.6.5 Re-Instatement of Entry & Exit PitCCOPL57752 | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-52-0405-CNM23-1800 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.7.3 Re-Instatement of Entry & Exit PitCCOPL58252 | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-52-0405-CNH24-1800 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA01-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA25-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA20-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA26-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA21-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA27-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA22-1100 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA02-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA03-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA28-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA29-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA30-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA23-1100 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA31-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA04-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA05-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA06-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA07-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA08-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA09-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA10-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA11-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA12-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA13-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA14-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA15-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA24-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA16-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA17-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA18-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA19-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-CMA32-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0405-CME01-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0405-CME02-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0405-CME03-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0405-CME04-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0405-CME05-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0405-CME06-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0405-CME07-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0405-CME08-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57132 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-52-0405-CNM17-1800 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.3.5 Re-Instatement of Entry & Exit PitCCOPL57792 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-52-0405-CNM18-1800 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.8.4.3 Re-Instatement of Entry & Exit PitCCOPL58152 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-52-0405-CNH19-1800 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.8.5.3 Re-Instatement of Entry & Exit PitCCOPL58312 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-52-0405-CNH20-1800 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.6.5 Re-Instatement of Entry & Exit PitCCOPL57752 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-52-0405-CNM23-1800 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.8.7.3 Re-Instatement of Entry & Exit PitCCOPL58252 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-52-0405-CNH24-1800 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Gatch Compaction | Installation of Marker Post/Sign Board | C-52-0405-PL-CI-6810 | C-52-0405-PL-CI-7800 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | Trench Excavation | Trench Excavation | C-52-0405-CMA32-1000 | C-52-0506-CMA07-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | Trench Excavation | Trench Excavation | C-52-0506-CMA06-1000 | C-52-0506-CMA04-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | Trench Excavation | Trench Excavation | C-52-0506-CMA07-1000 | C-52-0506-CMA02-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | Trench Excavation | Trench Excavation | C-52-0506-CMA04-1000 | C-52-0506-CMA08-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | Trench Excavation | Trench Excavation | C-52-0506-CMA02-1000 | C-52-0506-CMA09-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | Trench Excavation | Trench Excavation | C-52-0506-CMA08-1000 | C-52-0506-CMA03-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | Trench Excavation | Trench Excavation | C-52-0506-CMA09-1000 | C-52-0506-CMA01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | Trench Excavation | Trench Excavation | C-52-0506-CMA03-1000 | C-52-0506-CMA05-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | Lowering | Lowering | C-52-0506-CME01-1020 | C-52-0506-CME02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | Lowering | Lowering | C-52-0506-CME02-1020 | C-52-0506-CME03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | Lowering | Lowering | C-52-0506-CME03-1020 | C-52-0506-CME04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | Lowering | Lowering | C-52-0506-CME04-1020 | C-52-0506-CME05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | Lowering | Lowering | C-52-0506-CME05-1020 | C-52-0506-CME06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | Lowering | Lowering | C-52-0506-CME06-1020 | C-52-0506-CME07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | Lowering | Lowering | C-52-0506-CME07-1020 | C-52-0506-CME08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | Lowering | Lowering | C-52-0506-CME08-1020 | C-52-0506-CME09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | Lowering | Lowering | C-52-0506-CME09-1020 | C-52-0506-CME10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.11 Pipe StringingCCOPL52441 | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | Stringing (BVS-05 to BVS-06) | Lowering | C-52-0506-PL-ME-2800 | C-52-0506-CME01-1020 | SS | Not Started | Not Started | 21
P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | P2543-R01-Oct24..4.3.1.3.18.21.1.26 Test Stations & Anode BedsCCOP52EL45 | Holiday Testing | Installation of Temp. Anode | C-52-0506-PL-ME-4830 | C-52-0506-PL-CA-5600 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | P2543-R01-Oct24..4.3.1.3.18.21.1.23 CP Works TemporaryCCOP52EL46 | Padding | Glanding & Termination of Temp. CP S/m | C-52-0506-PL-CI-6000 | C-52-0506-PL-CA-5210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Holiday Testing | Installation of Test Post for Crossing | C-52-0506-CMA06-1060 | C-52-0506-PL-CA-5220 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding | Installation of Test Post for Crossing | C-52-0506-CMA07-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding | Installation of Test Post for Crossing | C-52-0506-CMA04-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding | Installation of Test Post for Crossing | C-52-0506-CMA02-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding | Installation of Test Post for Crossing | C-52-0506-CMA08-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding | Installation of Test Post for Crossing | C-52-0506-CMA09-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding | Installation of Test Post for Crossing | C-52-0506-CMA03-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding | Installation of Test Post for Crossing | C-52-0506-CMA01-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding | Installation of Test Post for Crossing | C-52-0506-CMA05-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0506-CME01-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0506-CME02-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0506-CME03-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0506-CME04-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0506-CME05-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0506-CME06-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0506-CME07-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0506-CME08-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0506-CME09-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0506-CME10-1070 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.2 Tunneling & Jack UpCCOPL58182 | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-52-0506-CNH27-1220 | C-52-0506-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | P2543-R01-Oct24..4.3.1.3.18.21.1.23 CP Works TemporaryCCOP52EL46 | Installation of CP TR | Glanding & Termination of Temp. CP S/m | C-52-0506-PL-CA-5240 | C-52-0506-PL-CA-5210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.23 CP Works TemporaryCCOP52EL46 | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Glanding & Termination of Temp. CP S/m | CIP/DCVG Survey | C-52-0506-PL-CA-5210 | C-52-0506-PL-CA-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding | FO - Cable Pulling/ Laying | C-52-0506-PL-CI-6000 | C-52-0506-PL-TE-8200 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding | FO - Cable Pulling/ Laying | C-52-0506-CMA06-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding | FO - Cable Pulling/ Laying | C-52-0506-CMA07-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding | FO - Cable Pulling/ Laying | C-52-0506-CMA04-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding | FO - Cable Pulling/ Laying | C-52-0506-CMA02-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding | FO - Cable Pulling/ Laying | C-52-0506-CMA08-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding | FO - Cable Pulling/ Laying | C-52-0506-CMA09-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding | FO - Cable Pulling/ Laying | C-52-0506-CMA03-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding | FO - Cable Pulling/ Laying | C-52-0506-CMA01-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding | FO - Cable Pulling/ Laying | C-52-0506-CMA05-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0506-CME01-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0506-CME02-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0506-CME03-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0506-CME04-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0506-CME05-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0506-CME06-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0506-CME07-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0506-CME08-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0506-CME09-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0506-CME10-1070 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.2 Tunneling & Jack UpCCOPL58182 | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Inner Grout b/w Main & RC Pipe | FO - Cable Pulling/ Laying | C-52-0506-CNH27-1220 | C-52-0506-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CMA06-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CMA07-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CMA04-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CMA02-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CMA08-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CMA09-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CMA03-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CMA01-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CMA05-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CME01-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CME02-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CME03-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CME04-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CME05-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CME06-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CME07-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CME08-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CME09-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | Section Tie-in Welding | C-52-0506-CME10-1030 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Lowering & Welding of Carrier Pipe | Section Tie-in Welding | C-52-0506-CNH27-1070 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding | Cleaning & Gauging | C-52-0506-PL-CI-6000 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding | Cleaning & Gauging | C-52-0506-CMA06-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding | Cleaning & Gauging | C-52-0506-CMA07-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding | Cleaning & Gauging | C-52-0506-CMA04-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding | Cleaning & Gauging | C-52-0506-CMA02-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding | Cleaning & Gauging | C-52-0506-CMA08-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding | Cleaning & Gauging | C-52-0506-CMA09-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding | Cleaning & Gauging | C-52-0506-CMA03-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding | Cleaning & Gauging | C-52-0506-CMA01-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding | Cleaning & Gauging | C-52-0506-CMA05-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding & Back Filling | Cleaning & Gauging | C-52-0506-CME01-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding & Back Filling | Cleaning & Gauging | C-52-0506-CME02-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding & Back Filling | Cleaning & Gauging | C-52-0506-CME03-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding & Back Filling | Cleaning & Gauging | C-52-0506-CME04-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding & Back Filling | Cleaning & Gauging | C-52-0506-CME05-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding & Back Filling | Cleaning & Gauging | C-52-0506-CME06-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding & Back Filling | Cleaning & Gauging | C-52-0506-CME07-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding & Back Filling | Cleaning & Gauging | C-52-0506-CME08-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding & Back Filling | Cleaning & Gauging | C-52-0506-CME09-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Padding & Back Filling | Cleaning & Gauging | C-52-0506-CME10-1070 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.3 Re-Instatement of Entry & Exit PitCCOPL58192 | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-52-0506-CNH27-1800 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding | Gatch Laying & Levelling | C-52-0506-PL-CI-6000 | C-52-0506-PL-CI-6800 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding | Gatch Laying & Levelling | C-52-0506-CMA06-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding | Gatch Laying & Levelling | C-52-0506-CMA07-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding | Gatch Laying & Levelling | C-52-0506-CMA04-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding | Gatch Laying & Levelling | C-52-0506-CMA02-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding | Gatch Laying & Levelling | C-52-0506-CMA08-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding | Gatch Laying & Levelling | C-52-0506-CMA09-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding | Gatch Laying & Levelling | C-52-0506-CMA03-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding | Gatch Laying & Levelling | C-52-0506-CMA01-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding | Gatch Laying & Levelling | C-52-0506-CMA05-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0506-CME01-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0506-CME02-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0506-CME03-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0506-CME04-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0506-CME05-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0506-CME06-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0506-CME07-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0506-CME08-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0506-CME09-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0506-CME10-1070 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.3.1.3 Re-Instatement of Entry & Exit PitCCOPL58192 | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-52-0506-CNH27-1800 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Gatch Compaction | Installation of Marker Post/Sign Board | C-52-0506-PL-CI-6810 | C-52-0506-PL-CI-7800 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | Trench Excavation | Trench Excavation | C-52-06CR-CMA11-1000 | C-52-06CR-CMA08-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | Excavation (Manual-Trial Pit) | Trench Excavation | C-52-06CR-CMA01-0970 | C-52-06CR-CMA02-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | Trench Excavation | Trench Excavation | C-52-06CR-CMA08-1000 | C-52-06CR-CMA03-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | Trench Excavation | Trench Excavation | C-52-06CR-CMA02-1000 | C-52-06CR-CMA12-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | Trench Excavation | Trench Excavation | C-52-06CR-CMA03-1000 | C-52-06CR-CMA09-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | Trench Excavation | Trench Excavation | C-52-06CR-CMA12-1000 | C-52-06CR-CMA04-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | Trench Excavation | Trench Excavation | C-52-06CR-CMA09-1000 | C-52-06CR-CMA05-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | Trench Excavation | Trench Excavation | C-52-06CR-CMA04-1000 | C-52-06CR-CMA06-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | Trench Excavation | Trench Excavation | C-52-06CR-CMA05-1000 | C-52-06CR-CMA10-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | Trench Excavation | Trench Excavation | C-52-06CR-CMA06-1000 | C-52-06CR-CMA07-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | Trench Excavation | Trench Excavation | C-52-06CR-CMA10-1000 | C-52-06CR-CMA13-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | Lowering | Lowering | C-52-06CR-CME01-1020 | C-52-06CR-CME02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | Lowering | Lowering | C-52-06CR-CME02-1020 | C-52-06CR-CME03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | Lowering | Lowering | C-52-06CR-CME04-1020 | C-52-06CR-CME05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | Lowering | Lowering | C-52-06CR-CME05-1020 | C-52-06CR-CME06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | Lowering | Lowering | C-52-06CR-CME07-1020 | C-52-06CR-CME08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | Lowering | Lowering | C-52-06CR-CME08-1020 | C-52-06CR-CME09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | Lowering | Lowering | C-52-06CR-CME09-1020 | C-52-06CR-CME10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | Lowering | Lowering | C-52-06CR-CME10-1020 | C-52-06CR-CME11-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | Lowering | Lowering | C-52-06CR-CME11-1020 | C-52-06CR-CME12-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | Lowering | Lowering | C-52-06CR-CME12-1020 | C-52-06CR-CME13-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | Lowering | Lowering | C-52-06CR-CME13-1020 | C-52-06CR-CME14-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | Lowering | Lowering | C-52-06CR-CMA11-1020 | C-52-06CR-CMA01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | Lowering | Lowering | C-52-06CR-CMA01-1020 | C-52-06CR-CMA08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | Lowering | Lowering | C-52-06CR-CMA08-1020 | C-52-06CR-CMA02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | Lowering | Lowering | C-52-06CR-CMA02-1020 | C-52-06CR-CMA03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | Lowering | Lowering | C-52-06CR-CMA03-1020 | C-52-06CR-CMA12-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | Lowering | Lowering | C-52-06CR-CMA12-1020 | C-52-06CR-CMA09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | Lowering | Lowering | C-52-06CR-CMA09-1020 | C-52-06CR-CMA04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | Lowering | Lowering | C-52-06CR-CMA04-1020 | C-52-06CR-CMA05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | Lowering | Lowering | C-52-06CR-CMA05-1020 | C-52-06CR-CMA06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | Lowering | Lowering | C-52-06CR-CMA10-1020 | C-52-06CR-CMA07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | Lowering | Lowering | C-52-06CR-CMA07-1020 | C-52-06CR-CMA13-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | Stringing (BVS-06 to SW CRS) | Lowering | C-52-06CR-PL-ME-2800 | C-52-06CR-CMA11-1020 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | Stringing (BVS-06 to SW CRS) | Lowering | C-52-06CR-PL-ME-2800 | C-52-06CR-CME01-1020 | SS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CMA11-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CMA01-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CMA08-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CMA02-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CMA03-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CMA12-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CMA09-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CMA04-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CMA05-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CMA06-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CMA10-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CMA07-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CMA13-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CME01-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CME02-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CME03-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CME04-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CME05-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CME06-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CME07-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CME08-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CME09-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CME10-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CME11-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CME12-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CME13-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | Section Tie-in Welding | C-52-06CR-CME14-1030 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Lowering & Welding of Carrier Pipe | Section Tie-in Welding | C-52-06CR-CNH30-1070 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.2.3.3 Pipe Lowering, Welding & NDTCCOPL56942 | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Lowering & Welding of Carrier Pipe | Section Tie-in Welding | C-52-06CR-CNM31-1400 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | P2543-R01-Oct24..4.3.1.3.19.8.1.26 Test Stations & Anode BedsCCOP52EL48 | Holiday Testing | Installation of Temp. Anode | C-52-06CR-PL-ME-4830 | C-52-06CR-PL-CA-5600 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | P2543-R01-Oct24..4.3.1.3.19.8.1.21 CP Works TemporaryCCOP52EL49 | Padding | Glanding & Termination of Temp. CP S/m | C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CA-5210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Holiday Testing | Installation of Test Post for Crossing | C-52-06CR-CMA11-1060 | C-52-06CR-PL-CA-5220 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding | Installation of Test Post for Crossing | C-52-06CR-CMA01-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding | Installation of Test Post for Crossing | C-52-06CR-CMA08-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding | Installation of Test Post for Crossing | C-52-06CR-CMA02-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding | Installation of Test Post for Crossing | C-52-06CR-CMA03-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding | Installation of Test Post for Crossing | C-52-06CR-CMA12-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding | Installation of Test Post for Crossing | C-52-06CR-CMA09-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding | Installation of Test Post for Crossing | C-52-06CR-CMA04-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding | Installation of Test Post for Crossing | C-52-06CR-CMA05-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding | Installation of Test Post for Crossing | C-52-06CR-CMA06-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding | Installation of Test Post for Crossing | C-52-06CR-CMA10-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding | Installation of Test Post for Crossing | C-52-06CR-CMA07-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding | Installation of Test Post for Crossing | C-52-06CR-CMA13-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-06CR-CME01-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-06CR-CME02-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-06CR-CME03-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-06CR-CME04-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-06CR-CME05-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-06CR-CME06-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-06CR-CME07-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-06CR-CME08-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-06CR-CME09-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-06CR-CME10-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-06CR-CME11-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-06CR-CME12-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-06CR-CME13-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-06CR-CME14-1070 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.5.2.2 Tunneling & Jack UpCCOPL58122 | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-52-06CR-CNH30-1220 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.2 Tunneling & Jack UpCCOPL56932 | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-52-06CR-CNM31-1220 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | P2543-R01-Oct24..4.3.1.3.19.8.1.21 CP Works TemporaryCCOP52EL49 | Installation of CP TR | Glanding & Termination of Temp. CP S/m | C-52-06CR-PL-CA-5240 | C-52-06CR-PL-CA-5210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding | FO - Cable Pulling/ Laying | C-52-06CR-PL-CI-6000 | C-52-06CR-PL-TE-8200 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding | FO - Cable Pulling/ Laying | C-52-06CR-CMA11-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding | FO - Cable Pulling/ Laying | C-52-06CR-CMA01-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding | FO - Cable Pulling/ Laying | C-52-06CR-CMA08-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding | FO - Cable Pulling/ Laying | C-52-06CR-CMA02-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding | FO - Cable Pulling/ Laying | C-52-06CR-CMA03-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding | FO - Cable Pulling/ Laying | C-52-06CR-CMA12-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding | FO - Cable Pulling/ Laying | C-52-06CR-CMA09-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding | FO - Cable Pulling/ Laying | C-52-06CR-CMA04-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding | FO - Cable Pulling/ Laying | C-52-06CR-CMA05-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding | FO - Cable Pulling/ Laying | C-52-06CR-CMA06-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding | FO - Cable Pulling/ Laying | C-52-06CR-CMA10-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding | FO - Cable Pulling/ Laying | C-52-06CR-CMA07-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding | FO - Cable Pulling/ Laying | C-52-06CR-CMA13-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-06CR-CME01-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-06CR-CME02-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-06CR-CME03-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-06CR-CME04-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-06CR-CME05-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-06CR-CME06-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-06CR-CME07-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-06CR-CME08-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-06CR-CME09-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-06CR-CME10-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-06CR-CME11-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-06CR-CME12-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-06CR-CME13-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-06CR-CME14-1070 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.5.2.2 Tunneling & Jack UpCCOPL58122 | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Inner Grout b/w Main & RC Pipe | FO - Cable Pulling/ Laying | C-52-06CR-CNH30-1220 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.2.3.2 Tunneling & Jack UpCCOPL56932 | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Inner Grout b/w Main & RC Pipe | FO - Cable Pulling/ Laying | C-52-06CR-CNM31-1220 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding | Cleaning & Gauging | C-52-06CR-PL-CI-6000 | C-52-06CR-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding | Cleaning & Gauging | C-52-06CR-CMA11-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding | Cleaning & Gauging | C-52-06CR-CMA01-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding | Cleaning & Gauging | C-52-06CR-CMA08-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding | Cleaning & Gauging | C-52-06CR-CMA02-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding | Cleaning & Gauging | C-52-06CR-CMA03-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding | Cleaning & Gauging | C-52-06CR-CMA12-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding | Cleaning & Gauging | C-52-06CR-CMA09-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding | Cleaning & Gauging | C-52-06CR-CMA04-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding | Cleaning & Gauging | C-52-06CR-CMA05-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding | Cleaning & Gauging | C-52-06CR-CMA06-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding | Cleaning & Gauging | C-52-06CR-CMA10-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding | Cleaning & Gauging | C-52-06CR-CMA07-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding | Cleaning & Gauging | C-52-06CR-CMA13-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding & Back Filling | Cleaning & Gauging | C-52-06CR-CME01-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding & Back Filling | Cleaning & Gauging | C-52-06CR-CME02-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding & Back Filling | Cleaning & Gauging | C-52-06CR-CME03-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding & Back Filling | Cleaning & Gauging | C-52-06CR-CME04-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding & Back Filling | Cleaning & Gauging | C-52-06CR-CME05-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding & Back Filling | Cleaning & Gauging | C-52-06CR-CME06-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding & Back Filling | Cleaning & Gauging | C-52-06CR-CME07-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding & Back Filling | Cleaning & Gauging | C-52-06CR-CME08-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding & Back Filling | Cleaning & Gauging | C-52-06CR-CME09-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding & Back Filling | Cleaning & Gauging | C-52-06CR-CME10-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding & Back Filling | Cleaning & Gauging | C-52-06CR-CME11-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding & Back Filling | Cleaning & Gauging | C-52-06CR-CME12-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding & Back Filling | Cleaning & Gauging | C-52-06CR-CME13-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Padding & Back Filling | Cleaning & Gauging | C-52-06CR-CME14-1070 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.5 Re-Instatement of Entry & Exit PitCCOPL56962 | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-52-06CR-CNM31-1800 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding | Gatch Laying & Levelling | C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CI-6800 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding | Gatch Laying & Levelling | C-52-06CR-CMA11-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding | Gatch Laying & Levelling | C-52-06CR-CMA01-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding | Gatch Laying & Levelling | C-52-06CR-CMA08-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding | Gatch Laying & Levelling | C-52-06CR-CMA02-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding | Gatch Laying & Levelling | C-52-06CR-CMA03-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding | Gatch Laying & Levelling | C-52-06CR-CMA12-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding | Gatch Laying & Levelling | C-52-06CR-CMA09-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding | Gatch Laying & Levelling | C-52-06CR-CMA04-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding | Gatch Laying & Levelling | C-52-06CR-CMA05-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding | Gatch Laying & Levelling | C-52-06CR-CMA06-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding | Gatch Laying & Levelling | C-52-06CR-CMA10-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding | Gatch Laying & Levelling | C-52-06CR-CMA07-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding | Gatch Laying & Levelling | C-52-06CR-CMA13-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding & Back Filling | Gatch Laying & Levelling | C-52-06CR-CME01-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding & Back Filling | Gatch Laying & Levelling | C-52-06CR-CME02-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding & Back Filling | Gatch Laying & Levelling | C-52-06CR-CME03-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding & Back Filling | Gatch Laying & Levelling | C-52-06CR-CME04-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding & Back Filling | Gatch Laying & Levelling | C-52-06CR-CME05-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding & Back Filling | Gatch Laying & Levelling | C-52-06CR-CME06-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding & Back Filling | Gatch Laying & Levelling | C-52-06CR-CME07-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding & Back Filling | Gatch Laying & Levelling | C-52-06CR-CME08-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding & Back Filling | Gatch Laying & Levelling | C-52-06CR-CME09-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding & Back Filling | Gatch Laying & Levelling | C-52-06CR-CME10-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding & Back Filling | Gatch Laying & Levelling | C-52-06CR-CME11-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding & Back Filling | Gatch Laying & Levelling | C-52-06CR-CME12-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding & Back Filling | Gatch Laying & Levelling | C-52-06CR-CME13-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Padding & Back Filling | Gatch Laying & Levelling | C-52-06CR-CME14-1070 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.5.2.3 Re-Instatement of Entry & Exit PitCCOPL58132 | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-52-06CR-CNH30-1800 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.19.8.2.3.5 Re-Instatement of Entry & Exit PitCCOPL56962 | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-52-06CR-CNM31-1800 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Gatch Compaction | Installation of Marker Post/Sign Board | C-52-06CR-PL-CI-6810 | C-52-06CR-PL-CI-7800 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | Trench Excavation | Trench Excavation | C-56-01HG-CMA01-1000 | C-56-01HG-CMA02-1000 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.26 Test Stations & Anode Beds from BVS-01 to KP 21.3CCOP56EL24.1 | Holiday Testing | Installation of Temp. Anode | C-56-01HG-PL-ME-4830 | C-56-01HG-PL-CA-5600 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA01-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA02-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA03-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA04-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA05-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA06-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA07-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA08-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA09-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA10-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA11-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA12-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA13-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA14-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME01-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME02-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME03-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME04-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME05-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME06-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME07-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME08-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME09-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME10-1030 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA01-1070 | C-56-01HG-PL-CA-5220 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA02-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA03-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA04-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA05-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA06-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA07-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA08-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA09-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA10-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA11-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA12-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA13-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA14-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA15-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA23-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA24-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA25-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA26-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA27-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA21-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA22-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA19-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA17-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA20-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA16-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA18-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME01-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME02-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME03-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME04-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME05-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME06-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME07-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME08-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME09-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME10-1070 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.2 Tunneling & Jack UpCCOPL57962 | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-56-01HG-CNM13-1220 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.2 Tunneling & Jack UpCCOPL57602 | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-56-01HG-CNM12-1220 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.6.4.2 Tunneling & Jack UpCCOPL58342 | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-56-01HG-CNH10-1220 | C-56-01HG-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-PL-CI-6000 | C-56-01HG-PL-TE-8200 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA01-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA02-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA03-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA04-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA05-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA06-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA07-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA08-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA09-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA10-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA11-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA12-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA13-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA14-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA15-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA22-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA19-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA17-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA20-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA16-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA18-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME01-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME02-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME03-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME04-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME05-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME06-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME07-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME08-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME09-1070 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-PL-CI-6000 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA01-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA02-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA03-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA04-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA05-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA06-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA07-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA08-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA09-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA10-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA11-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA12-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA13-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA14-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA15-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA23-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA24-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA25-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA26-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA27-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA21-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA22-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA19-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA17-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA20-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA16-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-CMA18-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME01-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME02-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME03-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME04-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME05-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME06-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME07-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME08-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME09-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME10-1070 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-PL-CI-6000 | C-56-01HG-PL-CI-6800 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA01-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA02-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA03-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA04-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA05-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA06-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA07-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA08-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA09-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA10-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA11-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA12-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA13-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA14-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA15-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA23-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA24-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA25-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA26-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA27-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA21-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA22-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA19-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA17-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA20-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA16-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA18-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME01-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME02-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME03-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME04-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME05-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME06-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME07-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME08-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME09-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME10-1070 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.3.12.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57992 | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-56-01HG-CNM13-1800 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | P2543-R01-Oct24..4.3.2.2.2.3.1.4 ROW Restoration/Marker Post/Crash BarrierCCOPL56229 | Gatch Compaction | ROW Restoration/ Installation of Marker Post/Sign Board | C-56-01HG-PL-CI-6810 | C-56-01HG-PL-CI-7800 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.16 Pipe Stringing from BVS-01 to KP 21.3CCOPL56250.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | Stringing (BVS-01 to KP 21.3) | Lowering | C-56-01HG-PL-ME-2800 | C-56-01HG-CME01-1020 | SS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.33 Test Stations & Anode Beds from Habshan complex to KP 6CCOP56EL22.1 | Holiday Testing | Installation of Temp. Anode | C-56-HC01-PL-ME-4830 | C-56-HC01-PL-CA-5600 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Holiday Testing | Installation of Test Post for Crossing | C-56-HC01-CMA02-1060 | C-56-HC01-PL-CA-5220 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA03-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA13-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA09-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA11-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA14-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA15-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA22-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA04-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA16-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA18-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA20-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA23-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA28-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA29-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA27-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA24-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA25-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA26-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA17-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA19-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA21-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA30-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA08-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA10-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA31-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME01-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME02-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME03-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME04-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME05-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME06-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME07-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME08-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME09-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME10-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME11-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME12-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME13-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME14-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME15-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME16-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.1.2 Tunneling & Jack UpCCOPL57562 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-56-HC01-CNM08-1220 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.2 Tunneling & Jack UpCCOPL58282 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-56-HC01-CNH05-1220 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.2 Tunneling & Jack UpCCOPL57522 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-56-HC01-CNM03-1220 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.20 Padding from Habshan complex to KP 6CCOPL56211.1 | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-PL-CI-6000 | C-56-HC01-PL-TE-8200 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA02-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA03-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA13-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA09-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA11-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA14-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA15-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA22-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA04-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA16-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA18-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA20-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA23-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA28-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA29-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA27-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA24-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA25-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA26-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA17-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA19-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA21-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA30-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA08-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA10-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA31-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA05-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA12-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA06-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA01-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA07-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME01-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME02-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME03-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME04-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME05-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME06-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME07-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME08-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME09-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME10-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME11-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME12-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME13-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME14-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME15-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME16-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.2 Tunneling & Jack UpCCOPL58282 | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Inner Grout b/w Main & RC Pipe | FO - Cable Pulling/ Laying | C-56-HC01-CNH05-1220 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.20 Padding from Habshan complex to KP 6CCOPL56211.1 | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-HC01-PL-CI-6000 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA01-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA02-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA03-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA04-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA05-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA06-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA07-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA08-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA09-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA10-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA11-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA12-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA13-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA14-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA15-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA23-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA24-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA25-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA26-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA27-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA21-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA22-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA19-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA17-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA20-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA16-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-01HG-CMA18-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME01-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME02-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME03-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME04-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME05-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME06-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME07-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME08-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME09-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding & Back Filling | Cleaning & Gauging | C-56-01HG-CME10-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.20 Padding from Habshan complex to KP 6CCOPL56211.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-PL-CI-6000 | C-56-HC01-PL-CI-6800 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA02-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA03-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA13-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA09-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA11-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA14-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA15-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA22-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA04-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA16-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA18-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA20-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA23-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA28-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA29-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA27-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA24-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA25-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA26-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA17-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA19-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA21-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA30-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA08-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA10-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA31-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA05-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA12-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA06-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA01-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA07-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME01-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME02-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME03-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME04-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME05-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME06-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME07-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME08-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME09-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME10-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME11-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME12-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME13-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME14-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME15-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME16-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.3 Re-Instatement of Entry & Exit PitCCOPL58292 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-56-HC01-CNH05-1800 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.5 Re-Instatement of Entry & Exit PitCCOPL57552 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-56-HC01-CNM03-1800 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Gatch Compaction | Installation of Marker Post/Sign Board | C-56-HC01-PL-CI-6810 | C-56-HC01-PL-CI-7800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.12 Cold BendsCCOPL52335 | P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | Cold Bends | Section Tie-in Welding | C-52-0102-PL-ME-3200 | C-52-0102-PL-ME-4810 | FF | In Progress | Not Started | 2
P2543-R01-Oct24..4.3.2.3.6.8.1.1 Evaporation PondCCOPL52347 | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Evaporation Pond | Stabilization & Pressurization | C-52-0102-PL-CI-7200 | C-52-0102-PL-ME-7420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.13 Cold BendsCCOPL52307 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Cold Bends-Lot1 | Section Tie-in Welding -Lot1 | C-52-HG01-PL-ME-3200 | C-52-HG01-PL-ME-4810 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.3.2.3.10.8.2.1 Evaporation PondCCOPL52319 | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Evaporation Pond | Stabilization & Pressurization | C-52-HG01-PL-CI-7200 | C-52-HG01-PL-ME-7420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.9 Cold BendsCCOPL52363 | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Cold Bends | Section Tie-in Welding | C-52-0203-PL-ME-3200 | C-52-0203-PL-ME-4810 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2.1 Evaporation PondCCOPL52375 | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Evaporation Pond | Stabilization & Pressurization | C-52-0203-PL-CI-7200 | C-52-0203-PL-ME-7420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | P2543-R01-Oct24..4.3.1.3.16.21.1.11 Cold BendsCCOPL52391 | Lowering | Cold Bends | C-52-0304-PL-ME-4800 | C-52-0304-PL-ME-3200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.11 Cold BendsCCOPL52391 | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Cold Bends | Section Tie-in Welding | C-52-0304-PL-ME-3200 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.3.1 Evaporation PondCCOPL52403 | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Evaporation Pond | Stabilization & Pressurization | C-52-0304-PL-CI-7200 | C-52-0304-PL-ME-7420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | P2543-R01-Oct24..4.3.1.3.17.21.1.11 Cold BendsCCOPL52419 | Lowering | Cold Bends | C-52-0405-PL-ME-4800 | C-52-0405-PL-ME-3200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.11 Cold BendsCCOPL52419 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Cold Bends | Section Tie-in Welding | C-52-0405-PL-ME-3200 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.3.1 Evaporation PondCCOPL52431 | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Evaporation Pond | Stabilization & Pressurization | C-52-0405-PL-CI-7200 | C-52-0405-PL-ME-7420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | P2543-R01-Oct24..4.3.1.3.18.21.1.12 Cold BendsCCOPL52447 | Lowering | Cold Bends | C-52-0506-PL-ME-4800 | C-52-0506-PL-ME-3200 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.18.21.1.12 Cold BendsCCOPL52447 | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Cold Bends | Section Tie-in Welding | C-52-0506-PL-ME-3200 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | P2543-R01-Oct24..4.3.2.3.2.8.3.1 Evaporation PondCCOPL52459 | Section Tie-in Welding | Evaporation Pond | C-52-0506-PL-ME-4810 | C-52-0506-PL-CI-7200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.3.1 Evaporation PondCCOPL52459 | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Evaporation Pond | Stabilization & Pressurization | C-52-0506-PL-CI-7200 | C-52-0506-PL-ME-7420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.16 Cold BendsCCOPL52475 | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Cold Bends | Section Tie-in Welding | C-52-06CR-PL-ME-3200 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | P2543-R01-Oct24..4.3.2.3.1.8.2.1 Evaporation PondCCOPL52487 | Section Tie-in Welding | Evaporation Pond | C-52-06CR-PL-ME-4810 | C-52-06CR-PL-CI-7200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.2.1 Evaporation PondCCOPL52487 | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Evaporation Pond | Stabilization & Pressurization | C-52-06CR-PL-CI-7200 | C-52-06CR-PL-ME-7420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.17 Cold Bends from BVS-01 to KP 21.3CCOPL56255.1 | Lowering | Cold Bends | C-56-01HG-PL-ME-4800 | C-56-01HG-PL-ME-3200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.17 Cold Bends from BVS-01 to KP 21.3CCOPL56255.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Cold Bends | Section Tie-in Welding | C-56-01HG-PL-ME-3200 | C-56-01HG-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.2.2.2.3.1.1 Evaporation PondCCOPL56239 | Section Tie-in Welding | Evaporation Pond | C-56-01HG-PL-ME-4810 | C-56-01HG-PL-CI-7200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.1 Evaporation PondCCOPL56239 | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Evaporation Pond | Stabilization & Pressurization | C-56-01HG-PL-CI-7200 | C-56-01HG-PL-ME-7420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.12 Cold BendsCCOPL56209 | Lowering | Cold Bends | C-56-HC01-PL-ME-4800 | C-56-HC01-PL-ME-3200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.2.2.2.3.1.5 Evaporation PondCCOPL56225 | Section Tie-in Welding | Evaporation Pond | C-56-HC01-PL-ME-4810 | C-56-HC01-PL-CI-7200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.5 Evaporation PondCCOPL56225 | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Evaporation Pond | Stabilization & Pressurization | C-56-HC01-PL-CI-7200 | C-56-HC01-PL-ME-7420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | Site Survey, Preparation & Grading Works | Earth Works for Equipment Foundations | C-56-PL-607-CI-1000 | C-56-PL-607-CI-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | Earth Works for Equipment Foundations | Earth Works for Pipe Support Foundations | C-56-PL-607-CI-1010 | C-56-PL-607-CI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | Earth Works for Pipe Support Foundations | Earth Works for Field Instrument, JBs & Light Pole Foundations | C-56-PL-607-CI-1020 | C-56-PL-607-CI-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | Earth Works for Field Instrument, JBs & Light Pole Foundations | Earth Works for Access Platforms & Misc. Structural Foundations | C-56-PL-607-CI-1030 | C-56-PL-607-CI-1040 | FS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | Earth Works for Access Platforms & Misc. Structural Foundations | Earth Works for Thrust Anchor Block | C-56-PL-607-CI-1040 | C-56-PL-607-CI-1050 | FS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | P2543-R01-Oct24..4.3.1.1.1.12.1.2 Compaction & Testing CCOHBCS201 | Earth Works for Equipment Foundations | Compaction & Testing for Equipment Foundations | C-56-PL-607-CI-1010 | C-56-PL-607-CI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.2 Compaction & Testing CCOHBCS201 | P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | Compaction & Testing for Equipment Foundations | Concrete Works for Equipment Foundations | C-56-PL-607-CI-1200 | C-56-PL-607-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | P2543-R01-Oct24..4.3.1.1.1.12.1.2 Compaction & Testing CCOHBCS201 | Earth Works for Pipe Support Foundations | Compaction & Testing for Pipe Support Foundations | C-56-PL-607-CI-1020 | C-56-PL-607-CI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.2 Compaction & Testing CCOHBCS201 | P2543-R01-Oct24..4.3.1.1.1.12.1.5 Concrete Works (Foundations for Pipe Supports) CCOHBCS202.2 | Compaction & Testing for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-56-PL-607-CI-1210 | C-56-PL-607-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | P2543-R01-Oct24..4.3.1.1.1.12.1.2 Compaction & Testing CCOHBCS201 | Earth Works for Field Instrument, JBs & Light Pole Foundations | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | C-56-PL-607-CI-1030 | C-56-PL-607-CI-1220 | FS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.1.1.12.1.2 Compaction & Testing CCOHBCS201 | P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-56-PL-607-CI-1220 | C-56-PL-607-CI-1410 | FS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | P2543-R01-Oct24..4.3.1.1.1.12.1.2 Compaction & Testing CCOHBCS201 | Earth Works for Access Platforms & Misc. Structural Foundations | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-56-PL-607-CI-1040 | C-56-PL-607-CI-1230 | FS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.1.1.12.1.2 Compaction & Testing CCOHBCS201 | P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | Concrete Works for Access Platforms & Misc. Structural Foundations | C-56-PL-607-CI-1230 | C-56-PL-607-CI-1420 | FS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | P2543-R01-Oct24..4.3.1.1.1.12.1.2 Compaction & Testing CCOHBCS201 | Earth Works for Thrust Anchor Block | Compaction & Testing for Thrust Anchor Block | C-56-PL-607-CI-1050 | C-56-PL-607-CI-1240 | FS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.1.1.12.1.2 Compaction & Testing CCOHBCS201 | P2543-R01-Oct24..4.3.1.1.1.12.1.9 Thrust Anchor BlockCCOHBCS210 | Compaction & Testing for Thrust Anchor Block | Concrete Works for Thrust Anchor Block | C-56-PL-607-CI-1240 | C-56-PL-607-CI-1510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | P2543-R01-Oct24..4.3.1.1.1.12.1.5 Concrete Works (Foundations for Pipe Supports) CCOHBCS202.2 | Concrete Works for Equipment Foundations | Concrete Works for Pipe Support Foundations | C-56-PL-607-CI-1400 | C-56-PL-607-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.5 Concrete Works (Foundations for Pipe Supports) CCOHBCS202.2 | P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | Concrete Works for Pipe Support Foundations | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-56-PL-607-CI-1600 | C-56-PL-607-CI-1410 | FS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Concrete Works for Access Platforms & Misc. Structural Foundations | C-56-PL-607-CI-1410 | C-56-PL-607-CI-1420 | FS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | P2543-R01-Oct24..4.3.1.1.1.12.1.9 Thrust Anchor BlockCCOHBCS210 | Concrete Works for Access Platforms & Misc. Structural Foundations | Concrete Works for Thrust Anchor Block | C-56-PL-607-CI-1420 | C-56-PL-607-CI-1510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | P2543-R01-Oct24..4.3.1.1.1.12.1.6 Trenching for Electrical cables CCOHBCS205.1 | Concrete Works for Equipment Foundations | Electrical & Earthing Cable Trenching | C-56-PL-607-CI-1400 | C-56-PL-607-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.5 Concrete Works (Foundations for Pipe Supports) CCOHBCS202.2 | P2543-R01-Oct24..4.3.1.1.1.12.1.6 Trenching for Electrical cables CCOHBCS205.1 | Concrete Works for Pipe Support Foundations | Electrical & Earthing Cable Trenching | C-56-PL-607-CI-1600 | C-56-PL-607-CI-1800 | FS | Not Started | Not Started | 60
P2543-R01-Oct24..4.3.1.1.1.12.1.13 Backfilling for CablesCCOHBCS212 | P2543-R01-Oct24..4.3.1.1.1.12.1.13 Backfilling for CablesCCOHBCS212 | Back Filling for Electrical & Earthing Cable | Back Filling for Instrument & Telecom Cable | C-56-PL-607-CI-2800 | C-56-PL-607-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.13 Backfilling for CablesCCOHBCS212 | P2543-R01-Oct24..4.3.1.1.1.12.1.14 Paving WorksCCOHBCS208 | Back Filling for Instrument & Telecom Cable | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PL-607-CI-2810 | C-56-PL-607-CI-2600 | SS | Not Started | Not Started | 6
P2543-R01-Oct24..4.3.1.1.1.12.1.5 Concrete Works (Foundations for Pipe Supports) CCOHBCS202.2 | P2543-R01-Oct24..4.3.1.1.1.12.1.8 Pipe Supports Fabrication & Installation CCOHBSS300 | Concrete Works for Pipe Support Foundations | Pre-Fabrication & Installation of Pipe Supports | C-56-PL-607-CI-1600 | C-56-PL-607-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-56-PL-607-CI-1410 | C-56-PL-607-EI-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | P2543-R01-Oct24..4.3.1.1.1.12.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS304 | Concrete Works for Access Platforms & Misc. Structural Foundations | Pre-Fabrication & Installation of Platforms & Crossovers | C-56-PL-607-CI-1420 | C-56-PL-607-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS304 | P2543-R01-Oct24..4.3.1.1.1.12.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS304 | Pre-Fabrication & Installation of Platforms & Crossovers | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-56-PL-607-CI-3000 | C-56-PL-607-CI-3010 | SS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.1.1.12.1.8 Pipe Supports Fabrication & Installation CCOHBSS300 | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-56-PL-607-CI-2000 | C-56-PL-607-EI-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | P2543-R01-Oct24..4.3.1.1.1.12.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS304 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Pre-Fabrication & Installation of Platforms & Crossovers | C-56-PL-607-EI-2210 | C-56-PL-607-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS304 | P2543-R01-Oct24..4.3.1.1.1.12.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS304 | Pre-Fabrication & Installation of Platforms & Crossovers | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-56-PL-607-CI-3000 | C-56-PL-607-CI-3010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.5.1 Pig Launcher 607-V-603 56'' Pipeline/Piping Hook-upCCOHBPI312 | P2543-R01-Oct24..4.3.1.1.1.12.5.1 Pig Launcher 607-V-603 56'' Pipeline/Piping Hook-upCCOHBPI312 | Installation of Isolation Joint | Field Joint Welding (Piping/Pipeline Section including IJ) | C-56-PL-607-PL-1000 | C-56-PL-607-PL-1010 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.1.1.12.5.1 Pig Launcher 607-V-603 56'' Pipeline/Piping Hook-upCCOHBPI312 | P2543-R01-Oct24..4.3.1.1.1.12.5.1 Pig Launcher 607-V-603 56'' Pipeline/Piping Hook-upCCOHBPI312 | Field Joint Welding (Piping/Pipeline Section including IJ) | NDT for Weld Joint | C-56-PL-607-PL-1010 | C-56-PL-607-PL-1020 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.1.1.12.5.1 Pig Launcher 607-V-603 56'' Pipeline/Piping Hook-upCCOHBPI312 | P2543-R01-Oct24..4.3.1.1.1.12.5.1 Pig Launcher 607-V-603 56'' Pipeline/Piping Hook-upCCOHBPI312 | NDT for Weld Joint | Ext. Coating for Weld Joint | C-56-PL-607-PL-1020 | C-56-PL-607-PL-1030 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | P2543-R01-Oct24..4.3.1.1.1.12.3.1 Installation of Pig Launcher (607-V-603)CCOHBME303 | Concrete Works for Equipment Foundations | Installation of Pig Launcher (607-V-603) 56" | C-56-PL-607-CI-1400 | C-56-PL-607-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.8 Pipe Supports Fabrication & Installation CCOHBSS300 | P2543-R01-Oct24..4.3.1.1.1.12.4.1 Piping Pre-FabricationCCOHBPI302 | Pre-Fabrication & Installation of Pipe Supports | Piping Pre-Fabrication | C-56-PL-607-CI-2000 | C-56-PL-607-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.6 Trenching for Electrical cables CCOHBCS205.1 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Laying | C-56-PL-607-CI-1800 | C-56-PL-607-EI-2000 | FS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Electrical & Earthing Cable Laying | Deep Earth Well Drilling | C-56-PL-607-EI-2000 | C-56-PL-607-EI-1400 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | CP Cable Laying | Installation of CP Test Post | C-56-PL-607-CA-1000 | C-56-PL-607-CA-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Installation of CP Test Post | Installation of CP JB's | C-56-PL-607-CA-1010 | C-56-PL-607-CA-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Installation of CP JB's | Glanding & Termination for CP S/m | C-56-PL-607-CA-1020 | C-56-PL-607-CA-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Electrical & Earthing Cable Laying | Installation of Cable Trays | C-56-PL-607-EI-2000 | C-56-PL-607-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Installation of Cable Trays | Instrument Tubing Works | C-56-PL-607-EI-2020 | C-56-PL-607-EI-2030 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Installation of Light Pole, Lighting & Fixtures | C-56-PL-607-CI-1410 | C-56-PL-607-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Installation of Cable Trays | Installation of Light Pole, Lighting & Fixtures | C-56-PL-607-EI-2020 | C-56-PL-607-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Installation of Light Pole, Lighting & Fixtures | Installation of JB's & PDB's | C-56-PL-607-EI-1800 | C-56-PL-607-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Installation of Cable Trays | Installation of JB's & PDB's | C-56-PL-607-EI-2020 | C-56-PL-607-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Electrical & Earthing Cable Laying | Installation of Light Pole, Lighting & Fixtures | C-56-PL-607-EI-2000 | C-56-PL-607-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Installation of Cable Trays | Instrument Cable Laying | C-56-PL-607-EI-2020 | C-56-PL-607-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Instrument Cable Laying | Instrument Tubing Works | C-56-PL-607-EI-2010 | C-56-PL-607-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Instrument Tubing Works | Installation of JB's & PDB's | C-56-PL-607-EI-2030 | C-56-PL-607-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Field Instruments (Including Pig Signaller) | C-56-PL-607-EI-2210 | C-56-PL-607-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of JB's & PDB's | C-56-PL-607-EI-2210 | C-56-PL-607-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Installation of Field Instruments (Including Pig Signaller) | Installation of F&G Device | C-56-PL-607-EI-2200 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Installation of F&G Device | Loop Checking for Instruments | C-56-PL-607-EI-2410 | C-56-PL-607-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Electrical & Earthing Cable Laying | Glanding & Termination | C-56-PL-607-EI-2000 | C-56-PL-607-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Installation of Light Pole, Lighting & Fixtures | Glanding & Termination | C-56-PL-607-EI-1800 | C-56-PL-607-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Installation of JB's & PDB's | Glanding & Termination | C-56-PL-607-EI-1810 | C-56-PL-607-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Loop Checking for Instruments | Glanding & Termination | C-56-PL-607-EI-2040 | C-56-PL-607-EI-2050 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Bolt Torquing/ Re-Instatement | Installation of Field Instruments (Including Pig Signaller) | C-56-PL-607-PI-2000 | C-56-PL-607-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.1.13 Backfilling for CablesCCOHBCS212 | Loop Checking for Instruments | Back Filling for Electrical & Earthing Cable | C-56-PL-607-EI-2040 | C-56-PL-607-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.1.13 Backfilling for CablesCCOHBCS212 | Loop Checking for Instruments | Back Filling for Instrument & Telecom Cable | C-56-PL-607-EI-2040 | C-56-PL-607-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Electrical & Earthing Cable Laying | CP Cable Laying | C-56-PL-607-EI-2000 | C-56-PL-607-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.13 Backfilling for CablesCCOHBCS212 | P2543-R01-Oct24..4.3.1.1.1.12.1.14 Paving WorksCCOHBCS208 | Back Filling for Electrical & Earthing Cable | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PL-607-CI-2800 | C-56-PL-607-CI-2600 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.4.3 Field Joint Welding & NDTCCOHBPI332 | P2543-R01-Oct24..4.3.1.1.1.12.5.1 Pig Launcher 607-V-603 56'' Pipeline/Piping Hook-upCCOHBPI312 | Field Joint Welding | Installation of Isolation Joint | C-56-PL-607-PI-1400 | C-56-PL-607-PL-1000 | FS | Not Started | Not Started | 21
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.1.1.12.5.1 Pig Launcher 607-V-603 56'' Pipeline/Piping Hook-upCCOHBPI312 | Section Tie-in Welding | Installation of Isolation Joint | C-56-HC01-PL-ME-4810 | C-56-PL-607-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation RTU | C-56-PL-607-EI-2210 | C-56-PL-607-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Installation RTU | Installation of JB's & PDB's | C-56-PL-607-EI-1600 | C-56-PL-607-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Instrument Cable Laying | Installation RTU | C-56-PL-607-EI-2010 | C-56-PL-607-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | P2543-R01-Oct24..4.3.1.1.1.12.8.1 PIDS SystemCCOHBIC211 | Installation of Out Door FOC Splicing Box | Installation of PIDS/ PLDS System | C-56-PL-607-TE-1410 | C-56-PL-607-TE-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.8.1 PIDS SystemCCOHBIC211 | P2543-R01-Oct24..4.3.1.1.1.12.8.3 CCTV SystemCCOHBIC231 | Installation of PIDS/ PLDS System | Installation of CCTV System | C-56-PL-607-TE-1200 | C-56-PL-607-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.8.3 CCTV SystemCCOHBIC231 | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Installation of CCTV System | FO Cable OTDR Testing & Splicing | C-56-PL-607-TE-1600 | C-56-PL-607-TE-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.1 Excavation WorksCCOHBCS104 | P2543-R01-Oct24..4.3.1.1.2.12.1.1 Excavation WorksCCOHBCS104 | Site Survey, Preparation & Grading Works | Earth Works for Ground Level | C-56-EB2-CI-1000 | C-56-EB2-CI-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.1 Excavation WorksCCOHBCS104 | P2543-R01-Oct24..4.3.1.1.2.12.1.1 Excavation WorksCCOHBCS104 | Earth Works for Ground Level | Compaction & Testing for Ground Level | C-56-EB2-CI-1010 | C-56-EB2-CI-1020 | SS | Completed | Completed | 5
P2543-R01-Oct24..4.3.1.1.2.12.1.1 Excavation WorksCCOHBCS104 | P2543-R01-Oct24..4.3.1.1.2.12.1.2 Foundation Works (for Substructure)CCOHBCS107 | Compaction & Testing for Ground Level | Building Foundation Works (for Substructure) | C-56-EB2-CI-1020 | C-56-EB2-CI-1200 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.2 Foundation Works (for Substructure)CCOHBCS107 | P2543-R01-Oct24..4.3.1.1.2.12.1.3 Concrete Superstructure WorksCCOHBCS109 | Building Foundation Works (for Substructure) | Concrete Superstructure Works | C-56-EB2-CI-1200 | C-56-EB2-CI-1400 | FF | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.3 Concrete Superstructure WorksCCOHBCS109 | P2543-R01-Oct24..4.3.1.1.2.12.1.4 Masonry WorksCCOHBCS113 | Concrete Superstructure Works | Masonry Works - Internal | C-56-EB2-CI-1400 | C-56-EB2-CI-1600 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.4 Masonry WorksCCOHBCS113 | P2543-R01-Oct24..4.3.1.1.2.12.1.4 Masonry WorksCCOHBCS113 | Masonry Works - Internal | Masonry Works - External | C-56-EB2-CI-1600 | C-56-EB2-CI-1610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.4 Masonry WorksCCOHBCS113 | P2543-R01-Oct24..4.3.1.1.2.12.1.5 Finishing WorksCCOHBCS116 | Masonry Works - Internal | Internal Finishing Works | C-56-EB2-CI-1600 | C-56-EB2-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.4 Masonry WorksCCOHBCS113 | P2543-R01-Oct24..4.3.1.1.2.12.1.5 Finishing WorksCCOHBCS116 | Masonry Works - External | External Finishing Works | C-56-EB2-CI-1610 | C-56-EB2-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.5 Finishing WorksCCOHBCS116 | P2543-R01-Oct24..4.3.1.1.2.12.1.6 Metal WorksCCOHBCS117 | External Finishing Works | Steel Structural Works | C-56-EB2-CI-1800 | C-56-EB2-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.5 Finishing WorksCCOHBCS116 | P2543-R01-Oct24..4.3.1.1.2.12.1.6 Metal WorksCCOHBCS117 | Internal Finishing Works | Steel Structural Works | C-56-EB2-CI-1810 | C-56-EB2-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.5 Finishing WorksCCOHBCS116 | P2543-R01-Oct24..4.3.1.1.2.12.1.7 Paving WorksCCOHBCS118 | External Finishing Works | Paving Works | C-56-EB2-CI-1800 | C-56-EB2-CI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.6 Metal WorksCCOHBCS117 | P2543-R01-Oct24..4.3.1.1.2.12.1.7 Paving WorksCCOHBCS118 | Steel Structural Works | Paving Works | C-56-EB2-CI-2000 | C-56-EB2-CI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.4 Masonry WorksCCOHBCS113 | P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | Masonry Works - Internal | Plumbing Works | C-56-EB2-CI-1600 | C-56-EB2-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.4 Masonry WorksCCOHBCS113 | P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | Masonry Works - External | Plumbing Works | C-56-EB2-CI-1610 | C-56-EB2-ME-1000 | FS | Not Started | Not Started | 30
P2543-R01-Oct24..4.3.1.1.2.12.1.5 Finishing WorksCCOHBCS116 | P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | Internal Finishing Works | HVAC Works | C-56-EB2-CI-1810 | C-56-EB2-ME-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | Plumbing Works | HVAC Works | C-56-EB2-ME-1000 | C-56-EB2-ME-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | HVAC Works | Installation of Power Distribution System | C-56-EB2-ME-1010 | C-56-EB2-EI-1000 | FS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | P2543-R01-Oct24..4.3.1.1.2.12.3.3 Lighting SystemCCOHBEL253 | Installation of Power Distribution System | Lighting & Fixtures | C-56-EB2-EI-1000 | C-56-EB2-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | P2543-R01-Oct24..4.3.1.1.2.12.3.6 HSSD SystemCCOHBEL283 | Installation of Power Distribution System | Installation of HSSD System | C-56-EB2-EI-1000 | C-56-EB2-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.6 HSSD SystemCCOHBEL283 | P2543-R01-Oct24..4.3.1.1.2.12.3.7 RTU SystemCCOHBEL303 | Installation of HSSD System | Installation of RTU System | C-56-EB2-EI-2000 | C-56-EB2-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.7 RTU SystemCCOHBEL303 | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Installation of RTU System | Custody Metering Panel Installation | C-56-EB2-EI-2200 | C-56-EB2-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Electrical & Earthing Cable Laying | E&I Cable Laying | C-56-PL-607-EI-2000 | C-56-EB2-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.3 Lighting SystemCCOHBEL253 | P2543-R01-Oct24..4.3.1.1.2.12.3.4 Earthing & Lightning Protection systemCCOHBEL263 | Lighting & Fixtures | Earthing & Lightning Protection system | C-56-EB2-EI-1400 | C-56-EB2-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | P2543-R01-Oct24..4.3.1.1.2.12.3.8 UPS (6KVA)CCOHBEL293 | E&I Cable Laying | UPS (10KVA) Installation | C-56-EB2-EI-1210 | C-56-EB2-EI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | P2543-R01-Oct24..4.3.1.1.2.12.3.5 F&G SystemCCOHBEL273 | E&I Cable Laying | Installation F&G System | C-56-EB2-EI-1210 | C-56-EB2-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | P2543-R01-Oct24..4.3.1.1.2.12.3.4 Earthing & Lightning Protection systemCCOHBEL263 | E&I Cable Laying | Earthing & Lightning Protection system | C-56-EB2-EI-1210 | C-56-EB2-EI-1600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.4 Earthing & Lightning Protection systemCCOHBEL263 | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Earthing & Lightning Protection system | MCT Installation | C-56-EB2-EI-1600 | C-56-EB2-EI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Installation of Power Distribution System | Glanding & Termination | C-56-EB2-EI-1000 | C-56-EB2-EI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.3 Lighting SystemCCOHBEL253 | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Lighting & Fixtures | Glanding & Termination | C-56-EB2-EI-1400 | C-56-EB2-EI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.6 HSSD SystemCCOHBEL283 | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Installation of HSSD System | Glanding & Termination | C-56-EB2-EI-2000 | C-56-EB2-EI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.7 RTU SystemCCOHBEL303 | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Installation of RTU System | Glanding & Termination | C-56-EB2-EI-2200 | C-56-EB2-EI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Custody Metering Panel Installation | Glanding & Termination | C-56-EB2-EI-1200 | C-56-EB2-EI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | E&I Cable Laying | Glanding & Termination | C-56-EB2-EI-1210 | C-56-EB2-EI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.4 Earthing & Lightning Protection systemCCOHBEL263 | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Earthing & Lightning Protection system | Glanding & Termination | C-56-EB2-EI-1600 | C-56-EB2-EI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.8 UPS (6KVA)CCOHBEL293 | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | UPS (10KVA) Installation | Glanding & Termination | C-56-EB2-EI-2400 | C-56-EB2-EI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.5 F&G SystemCCOHBEL273 | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Installation F&G System | Glanding & Termination | C-56-EB2-EI-1800 | C-56-EB2-EI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | MCT Installation | Glanding & Termination | C-56-EB2-EI-1220 | C-56-EB2-EI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | P2543-R01-Oct24..4.3.1.1.2.12.4.1 SDH CabinetCCOHBIC201 | Custody Metering Panel Installation | SDH Cabinet Installation | C-56-EB2-EI-1200 | C-56-EB2-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | P2543-R01-Oct24..4.3.1.1.2.12.4.1 SDH CabinetCCOHBIC201 | E&I Cable Laying | SDH Cabinet Installation | C-56-EB2-EI-1210 | C-56-EB2-TE-1000 | FF | Not Started | Not Started | 6
P2543-R01-Oct24..4.3.1.1.2.12.4.1 SDH CabinetCCOHBIC201 | P2543-R01-Oct24..4.3.1.1.2.12.4.3 Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOHBIC251 | SDH Cabinet Installation | CCTV Installation | C-56-EB2-TE-1000 | C-56-EB2-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.4.3 Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOHBIC251 | P2543-R01-Oct24..4.3.1.1.2.12.4.2 Telecom System (Including subcontract for FOC Splicing / Termination / Testing)CCOHBIC241 | CCTV Installation | Telecom System (Including subcontract for FOC Splicing / Termination / Testing) | C-56-EB2-TE-1600 | C-56-EB2-TE-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.4.2 Telecom System (Including subcontract for FOC Splicing / Termination / Testing)CCOHBIC241 | P2543-R01-Oct24..4.3.1.1.2.12.4.3 Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOHBIC251 | Telecom System (Including subcontract for FOC Splicing / Termination / Testing) | Security System (Including subcontract for FOC Splicing / Termination / Testing ) | C-56-EB2-TE-1400 | C-56-EB2-TE-1610 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.1.2.12.4.3 Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOHBIC251 | P2543-R01-Oct24..4.3.1.1.2.12.5.1 Shutdown Connection to Existing Substation Unit 607CCOHBST204 | Security System (Including subcontract for FOC Splicing / Termination / Testing ) | Termination & Connection with Existing Power Distribution Network | C-56-EB2-TE-1610 | C-56-EB2-EL-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | P2543-R01-Oct24..4.3.1.1.2.12.5.1 Shutdown Connection to Existing Substation Unit 607CCOHBST204 | Glanding & Termination | Termination & Connection with Existing Power Distribution Network | C-56-EB2-EI-1230 | C-56-EB2-EL-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.40.2 Excavation WorksCCOHBCS301 | P2543-R01-Oct24..4.3.1.1.3.10.40.2 Excavation WorksCCOHBCS301 | Earth Works for Pipe Support Foundations | Earth Works for Access Platforms & Misc. Structural Foundations | C-56-G-HT-CI-1020 | C-56-G-HT-CI-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.40.2 Excavation WorksCCOHBCS301 | P2543-R01-Oct24..4.3.1.1.3.10.40.3 Concrete WorksCCOHBCS302 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | Concrete Works for Pipe Support Foundations | C-56-G-HT-CI-1230 | C-56-G-HT-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.40.3 Concrete WorksCCOHBCS302 | P2543-R01-Oct24..4.3.1.1.3.10.40.6 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS310 | Concrete Works for Pipe Support Foundations | Concrete Works for Access Platforms & Misc. Structural Foundations | C-56-G-HT-CI-1600 | C-56-G-HT-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.40.6 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS310 | P2543-R01-Oct24..4.3.1.1.3.10.40.7 Paving WorksCCOHBCS305 | Concrete Works for Access Platforms & Misc. Structural Foundations | Paving of Interlock tiles & Kerb Stone Embankment | C-56-G-HT-CI-1420 | C-56-G-HT-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.40.1 Demolition Works (Paving)CCOHBCS300 | P2543-R01-Oct24..4.3.1.1.3.10.40.2 Excavation WorksCCOHBCS301 | Demolition of Existing Paving | Site Survey, Preparation & Grading Works | C-56-G-HT-CI-0100 | C-56-G-HT-CI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.1 Excavation WorksCCOHBCS104 | P2543-R01-Oct24..4.3.1.1.3.10.40.1 Demolition Works (Paving)CCOHBCS300 | Site Survey, Preparation & Grading Works | Demolition of Existing Paving | C-56-EB2-CI-1000 | C-56-G-HT-CI-0100 | SS | Completed | Not Started | 5
P2543-R01-Oct24..4.3.1.1.3.10.40.2 Excavation WorksCCOHBCS301 | P2543-R01-Oct24..4.3.1.1.3.10.40.2 Excavation WorksCCOHBCS301 | Site Survey, Preparation & Grading Works | Earth Works for Pipe Support Foundations | C-56-G-HT-CI-1000 | C-56-G-HT-CI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.40.2 Excavation WorksCCOHBCS301 | P2543-R01-Oct24..4.3.1.1.3.10.40.2 Excavation WorksCCOHBCS301 | Earth Works for Pipe Support Foundations | Compaction & Testing for Pipe Support Foundations | C-56-G-HT-CI-1020 | C-56-G-HT-CI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.40.2 Excavation WorksCCOHBCS301 | P2543-R01-Oct24..4.3.1.1.3.10.40.2 Excavation WorksCCOHBCS301 | Earth Works for Access Platforms & Misc. Structural Foundations | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-56-G-HT-CI-1040 | C-56-G-HT-CI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.3.6 Isolation of Hot Tap JointCCOHBHT315 | P2543-R01-Oct24..4.3.1.1.3.10.4.1 Preparation, Marking & UT for Existing Line 42" LineCCOHBHT325 | Isolation of Hot Tap Joint | Preparation, Marking & UT for Existing Line 30" Line | C-56-G-HT101-ME-1050 | C-56-G-HT102-ME-1000 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.1.3.10.4.6 Isolation of Hot Tap JointCCOHBHT375 | P2543-R01-Oct24..4.3.1.1.3.10.5.1 Preparation, Marking & UT for Existing Line 42" LineCCOHBHT385 | Isolation of Hot Tap Joint | Preparation, Marking & UT for Existing Line 42" Line | C-56-G-HT102-ME-1050 | C-56-G-HT103-ME-1000 | FS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.3.12.2.1.2 Tunneling & Jack UpCCOPL57962 | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Inner Grout b/w Main & RC Pipe | Cleaning & Gauging | C-56-01HG-CNM13-1220 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.8.33 CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) CCOH56IC30 | P2543-R01-Oct24..4.3.1.2.21.12.8.33 CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) CCOH56IC30 | FOC Laying | FO Cable OTDR Testing & Splicing | C-56-PR-838-TE-1410 | C-56-PR-838-TE-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | Site Survey, Preparation & Grading Works | Earth Works for Equipment Foundations | C-56-PR-838-CI-1000 | C-56-PR-838-CI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | Earth Works for Equipment Foundations | Earth Works for Pipe Support Foundations | C-56-PR-838-CI-1010 | C-56-PR-838-CI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | Earth Works for Pipe Support Foundations | Earth Works for Field Instrument, JBs & Light Pole Foundations | C-56-PR-838-CI-1020 | C-56-PR-838-CI-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | Earth Works for Field Instrument, JBs & Light Pole Foundations | Earth Works for Access Platforms & Misc. Structural Foundations | C-56-PR-838-CI-1030 | C-56-PR-838-CI-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | Earth Works for Access Platforms & Misc. Structural Foundations | Earth Works for Thrust Anchor Block | C-56-PR-838-CI-1040 | C-56-PR-838-CI-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | Earth Works for Thrust Anchor Block | Earth Works for Impact Wall | C-56-PR-838-CI-1050 | C-56-PR-838-CI-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | P2543-R01-Oct24..4.3.1.2.21.12.1.10 Compaction & Testing CCOH56CS31 | Earth Works for Equipment Foundations | Compaction & Testing for Equipment Foundations | C-56-PR-838-CI-1010 | C-56-PR-838-CI-1200 | FS | Not Started | Not Started | 21
P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | P2543-R01-Oct24..4.3.1.2.21.12.1.10 Compaction & Testing CCOH56CS31 | Earth Works for Pipe Support Foundations | Compaction & Testing for Pipe Support Foundations | C-56-PR-838-CI-1020 | C-56-PR-838-CI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | P2543-R01-Oct24..4.3.1.2.21.12.1.10 Compaction & Testing CCOH56CS31 | Earth Works for Field Instrument, JBs & Light Pole Foundations | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | C-56-PR-838-CI-1030 | C-56-PR-838-CI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | P2543-R01-Oct24..4.3.1.2.21.12.1.10 Compaction & Testing CCOH56CS31 | Earth Works for Access Platforms & Misc. Structural Foundations | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-56-PR-838-CI-1040 | C-56-PR-838-CI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | P2543-R01-Oct24..4.3.1.2.21.12.1.10 Compaction & Testing CCOH56CS31 | Earth Works for Thrust Anchor Block | Compaction & Testing for Thrust Anchor Block | C-56-PR-838-CI-1050 | C-56-PR-838-CI-1240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | P2543-R01-Oct24..4.3.1.2.21.12.1.10 Compaction & Testing CCOH56CS31 | Earth Works for Impact Wall | Compaction & Testing for Impact Wall | C-56-PR-838-CI-1060 | C-56-PR-838-CI-1250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.10 Compaction & Testing CCOH56CS31 | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Compaction & Testing for Equipment Foundations | Concrete Works for Equipment Foundations | C-56-PR-838-CI-1200 | C-56-PR-838-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.10 Compaction & Testing CCOH56CS31 | P2543-R01-Oct24..4.3.1.2.21.12.1.13 Concrete Works (Foundations for Pipe Supports) CCOH56CS34 | Compaction & Testing for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-56-PR-838-CI-1210 | C-56-PR-838-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.10 Compaction & Testing CCOH56CS31 | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-56-PR-838-CI-1220 | C-56-PR-838-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.10 Compaction & Testing CCOH56CS31 | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | Concrete Works for Access Platforms & Misc. Structural Foundations | C-56-PR-838-CI-1230 | C-56-PR-838-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.10 Compaction & Testing CCOH56CS31 | P2543-R01-Oct24..4.3.1.2.21.12.1.12 Thrust Anchor Block/ Impact WallCCOH56CS33 | Compaction & Testing for Thrust Anchor Block | Concrete Works for Thrust Anchor Block | C-56-PR-838-CI-1240 | C-56-PR-838-CI-1510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.10 Compaction & Testing CCOH56CS31 | P2543-R01-Oct24..4.3.1.2.21.12.1.12 Thrust Anchor Block/ Impact WallCCOH56CS33 | Compaction & Testing for Impact Wall | Concrete Works for Impact Wall | C-56-PR-838-CI-1250 | C-56-PR-838-CI-1500 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.13 Concrete Works (Foundations for Pipe Supports) CCOH56CS34 | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Concrete Works for Pipe Support Foundations | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-56-PR-838-CI-1600 | C-56-PR-838-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Concrete Works for Access Platforms & Misc. Structural Foundations | C-56-PR-838-CI-1410 | C-56-PR-838-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | P2543-R01-Oct24..4.3.1.2.21.12.1.12 Thrust Anchor Block/ Impact WallCCOH56CS33 | Concrete Works for Access Platforms & Misc. Structural Foundations | Concrete Works for Impact Wall | C-56-PR-838-CI-1420 | C-56-PR-838-CI-1500 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | P2543-R01-Oct24..4.3.1.2.21.12.1.14 Trenching for Cables CCOH56CS35 | Site Survey, Preparation & Grading Works | Electrical & Earthing Cable Trenching | C-56-PR-838-CI-1000 | C-56-PR-838-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.14 Trenching for Cables CCOH56CS35 | P2543-R01-Oct24..4.3.1.2.21.12.1.14 Trenching for Cables CCOH56CS35 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-56-PR-838-CI-1800 | C-56-PR-838-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.13 Concrete Works (Foundations for Pipe Supports) CCOH56CS34 | P2543-R01-Oct24..4.3.1.2.21.12.1.17 Pipe Supports Fabrication & Installation CCOH56SS50 | Concrete Works for Pipe Support Foundations | Pre-Fabrication & Installation of Pipe Supports | C-56-PR-838-CI-1600 | C-56-PR-838-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-56-PR-838-CI-1410 | C-56-PR-838-EI-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.17 Pipe Supports Fabrication & Installation CCOH56SS50 | P2543-R01-Oct24..4.3.1.2.21.12.1.18 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOH56SS51 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Platforms & Crossovers | C-56-PR-838-CI-2000 | C-56-PR-838-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | P2543-R01-Oct24..4.3.1.2.21.12.1.18 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOH56SS51 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Pre-Fabrication & Installation of Platforms & Crossovers | C-56-PR-838-EI-2210 | C-56-PR-838-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.18 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOH56SS51 | P2543-R01-Oct24..4.3.1.2.21.12.1.18 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOH56SS51 | Pre-Fabrication & Installation of Platforms & Crossovers | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-56-PR-838-CI-3000 | C-56-PR-838-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | P2543-R01-Oct24..4.3.1.2.21.12.3.19 Installation of Pig Receiver (838-V-601) CCOH56ME50 | Concrete Works for Equipment Foundations | Installation of Pig Receiver (838-V-601) 56" | C-56-PR-838-CI-1400 | C-56-PR-838-ME-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.21.12.5.34 Pig Receiver 838-V-601 56'' Pipeline/ Piping Hook-up CCOH56PI51 | Section Tie-in Welding | Installation of Isolation Joint | C-56-HC01-PL-ME-4810 | C-56-PR-838-PL-1000 | FS | Not Started | Not Started | 13
P2543-R01-Oct24..4.3.1.2.21.12.5.34 Pig Receiver 838-V-601 56'' Pipeline/ Piping Hook-up CCOH56PI51 | P2543-R01-Oct24..4.3.1.2.21.12.5.34 Pig Receiver 838-V-601 56'' Pipeline/ Piping Hook-up CCOH56PI51 | Installation of Isolation Joint | Field Joint Welding (Piping/Pipeline Section including IJ) | C-56-PR-838-PL-1000 | C-56-PR-838-PL-1010 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.21.12.5.34 Pig Receiver 838-V-601 56'' Pipeline/ Piping Hook-up CCOH56PI51 | P2543-R01-Oct24..4.3.1.2.21.12.5.34 Pig Receiver 838-V-601 56'' Pipeline/ Piping Hook-up CCOH56PI51 | Field Joint Welding (Piping/Pipeline Section including IJ) | NDT for Weld Joint | C-56-PR-838-PL-1010 | C-56-PR-838-PL-1020 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.21.12.5.34 Pig Receiver 838-V-601 56'' Pipeline/ Piping Hook-up CCOH56PI51 | P2543-R01-Oct24..4.3.1.2.21.12.5.34 Pig Receiver 838-V-601 56'' Pipeline/ Piping Hook-up CCOH56PI51 | NDT for Weld Joint | Ext. Coating for Weld Joint | C-56-PR-838-PL-1020 | C-56-PR-838-PL-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | P2543-R01-Oct24..4.3.1.2.21.12.5.34 Pig Receiver 838-V-601 56'' Pipeline/ Piping Hook-up CCOH56PI51 | Final Bolt Torquing/ Re-Instatement | Installation of Isolation Joint | C-56-PR-838-PI-2000 | C-56-PR-838-PL-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.14 Trenching for Cables CCOH56CS35 | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Laying | C-56-PR-838-CI-1800 | C-56-PR-838-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Electrical & Earthing Cable Laying | Deep Earth Well Drilling | C-56-PR-838-EI-2000 | C-56-PR-838-EI-1400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.21.12.1.14 Trenching for Cables CCOH56CS35 | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-56-PR-838-CI-1810 | C-56-PR-838-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Electrical & Earthing Cable Laying | Installation of Cable Trays | C-56-PR-838-EI-2000 | C-56-PR-838-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Instrument Cable Laying | Instrument Tubing Works | C-56-PR-838-EI-2010 | C-56-PR-838-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of JB's | C-56-PR-838-EI-2210 | C-56-PR-838-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.17 Pipe Supports Fabrication & Installation CCOH56SS50 | P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-56-PR-838-CI-2000 | C-56-PR-838-EI-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Field Instruments (Including Pig Signaller) | C-56-PR-838-EI-2210 | C-56-PR-838-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | Installation of Field Instruments (Including Pig Signaller) | Installation of F&G Device | C-56-PR-838-EI-2200 | C-56-PR-838-EI-2410 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Instrument Cable Laying | Loop Checking for Instruments | C-56-PR-838-EI-2010 | C-56-PR-838-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Instrument Tubing Works | Loop Checking for Instruments | C-56-PR-838-EI-2030 | C-56-PR-838-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Installation of Field Instruments (Including Pig Signaller) | Loop Checking for Instruments | C-56-PR-838-EI-2200 | C-56-PR-838-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Installation of F&G Device | Loop Checking for Instruments | C-56-PR-838-EI-2410 | C-56-PR-838-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Deep Earth Well Drilling | Glanding & Termination | C-56-PR-838-EI-1400 | C-56-PR-838-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Installation of JB's | Glanding & Termination | C-56-PR-838-EI-1810 | C-56-PR-838-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Loop Checking for Instruments | Glanding & Termination | C-56-PR-838-EI-2040 | C-56-PR-838-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Instrument Cable Laying | CP Cable Laying | C-56-PR-838-EI-2010 | C-56-PR-838-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | CP Cable Laying | Installation of CP Test Post | C-56-PR-838-CA-1000 | C-56-PR-838-EI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Installation of CP Test Post | Installation of CP JB's | C-56-PR-838-EI-1010 | C-56-PR-838-EI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Installation of CP JB's | Glanding & Termination for CP S/m | C-56-PR-838-EI-1020 | C-56-PR-838-CA-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.2.21.12.8.33 CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) CCOH56IC30 | Instrument Cable Laying | FOC Laying | C-56-PR-838-EI-2010 | C-56-PR-838-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | P2543-R01-Oct24..4.3.1.2.1.12.1.12 Fences & Gates Construction CCOB156C31 | Concrete Works for Light Pole, Fence & Gates Foundation | Installation of Concrete Pillers for Boundary Wall | C-56-591-01-CI-1430 | C-56-591-01-CI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.12 Fences & Gates Construction CCOB156C31 | P2543-R01-Oct24..4.3.1.2.1.12.1.12 Fences & Gates Construction CCOB156C31 | Installation of Concrete Pillers for Boundary Wall | Block Works for Boundary Wall | C-56-591-01-CI-2200 | C-56-591-01-CI-2210 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.1.12.1.12 Fences & Gates Construction CCOB156C31 | P2543-R01-Oct24..4.3.1.2.1.12.1.12 Fences & Gates Construction CCOB156C31 | Block Works for Boundary Wall | Installation of Fence Post & Mesh Works (Type-4 & 3) | C-56-591-01-CI-2210 | C-56-591-01-CI-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.12 Fences & Gates Construction CCOB156C31 | P2543-R01-Oct24..4.3.1.2.1.12.1.12 Fences & Gates Construction CCOB156C31 | Installation of Fence Post & Mesh Works (Type-4 & 3) | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | C-56-591-01-CI-2220 | C-56-591-01-CI-2230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.12 Fences & Gates Construction CCOB156C31 | P2543-R01-Oct24..4.3.1.2.1.12.1.15 Paving Works CCOB156C35 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | Paving of Interlock tiles & Kerb Stone Embankment | C-56-591-01-CI-2230 | C-56-591-01-CI-2600 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.1.12.1.15 Paving Works CCOB156C35 | P2543-R01-Oct24..4.3.1.2.1.12.1.15 Paving Works CCOB156C35 | Paving of Interlock tiles & Kerb Stone Embankment | Rip-Rap Protection Laying | C-56-591-01-CI-2600 | C-56-591-01-CI-2610 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.1.12.1.13 Concrete Works (Foundations for Pipe Supports) CCOB156C32 | P2543-R01-Oct24..4.3.1.2.1.12.1.17 Pipe Supports Fabrication & Installation CCOB156S50 | Concrete Works for Pipe Support Foundations | Pre-Fabrication & Installation of Pipe Supports | C-56-591-01-CI-1600 | C-56-591-01-CI-2000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | P2543-R01-Oct24..4.3.1.2.1.12.3.9 Mechanical Works and Equipment Installation (Fire Fighting Equipment) CCOB156M50 | Concrete Works for Equipment Foundations & Hard Stand Area | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | C-56-591-01-CI-1400 | C-56-591-01-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.18 Fire Point Shelters CCOB156S52 | P2543-R01-Oct24..4.3.1.2.1.12.3.9 Mechanical Works and Equipment Installation (Fire Fighting Equipment) CCOB156M50 | Installation of Fire Point Shelters | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | C-56-591-01-CI-2400 | C-56-591-01-ME-1000 | FS | Not Started | Not Started | 12
P2543-R01-Oct24..4.3.1.2.1.12.6.5 Field Instruments CCOB156E64 | P2543-R01-Oct24..4.3.1.2.1.12.1.18 Fire Point Shelters CCOB156S52 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Fire Point Shelters | C-56-591-01-EI-2210 | C-56-591-01-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.6.1 Deep Earth Well CCOB156E32 | Electrical & Earthing Cable Laying | Deep Earth Well Drilling | C-56-591-01-EI-2000 | C-56-591-01-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.1 Deep Earth Well CCOB156E32 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Deep Earth Well Drilling | Instrument Cable Laying | C-56-591-01-EI-1400 | C-56-591-01-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Instrument Cable Laying | Installation of Cable Trays | C-56-591-01-EI-2010 | C-56-591-01-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of Cable Trays | Instrument Tubing Works | C-56-591-01-EI-2020 | C-56-591-01-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.6.3 Solar Power System CCOB156E44 | Instrument Tubing Works | Installation of Solar S/m (Including Panels, UPS & Battery) | C-56-591-01-EI-2030 | C-56-591-01-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.3 Solar Power System CCOB156E44 | P2543-R01-Oct24..4.3.1.2.1.12.6.4 Light Pole, Lighting & Fixtures CCOB156E54 | Installation of Solar S/m (Including Panels, UPS & Battery) | Installation of Light Pole, Lighting & Fixtures | C-56-591-01-EI-1200 | C-56-591-01-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.9 Hybrid Passive Cooling Shelter Installation CCOB156E30 | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Installation of Passive Cooling Shelter | Installation of RTU | C-56-591-01-EI-1000 | C-56-591-01-EI-1600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | P2543-R01-Oct24..4.3.1.2.1.12.6.6 F&G Devices CCOB156E74 | Installation of RTU | Installation of F&G Panel | C-56-591-01-EI-1600 | C-56-591-01-EI-2400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.6 F&G Devices CCOB156E74 | P2543-R01-Oct24..4.3.1.2.1.12.6.4 Light Pole, Lighting & Fixtures CCOB156E54 | Installation of F&G Panel | Installation of Lighting & Instrument JB's | C-56-591-01-EI-2400 | C-56-591-01-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.4 Light Pole, Lighting & Fixtures CCOB156E54 | P2543-R01-Oct24..4.3.1.2.1.12.6.5 Field Instruments CCOB156E64 | Installation of Lighting & Instrument JB's | Installation of Field Instruments | C-56-591-01-EI-1810 | C-56-591-01-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.5 Field Instruments CCOB156E64 | P2543-R01-Oct24..4.3.1.2.1.12.6.6 F&G Devices CCOB156E74 | Installation of Field Instruments | Installation of F&G Devices | C-56-591-01-EI-2200 | C-56-591-01-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.6 F&G Devices CCOB156E74 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of F&G Devices | Loop Checking for Instruments | C-56-591-01-EI-2410 | C-56-591-01-EI-2040 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Loop Checking for Instruments | Glanding & Termination | C-56-591-01-EI-2040 | C-56-591-01-EI-2050 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.14 Trenching for Cables CCOB156C33 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Laying | C-56-591-01-CI-1800 | C-56-591-01-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.14 Trenching for Cables CCOB156C33 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-56-591-01-CI-1810 | C-56-591-01-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.3 Solar Power System CCOB156E44 | P2543-R01-Oct24..4.3.1.2.1.12.6.3 Solar Power System CCOB156E44 | Installation of Solar Panel Structural Supports | Installation of Solar S/m (Including Panels, UPS & Battery) | C-56-591-01-EI-1210 | C-56-591-01-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | P2543-R01-Oct24..4.3.1.2.1.12.6.9 Hybrid Passive Cooling Shelter Installation CCOB156E30 | Concrete Works for Equipment Foundations & Hard Stand Area | Installation of Passive Cooling Shelter | C-56-591-01-CI-1400 | C-56-591-01-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.3 Solar Power System CCOB156E44 | P2543-R01-Oct24..4.3.1.2.1.12.6.9 Hybrid Passive Cooling Shelter Installation CCOB156E30 | Installation of Solar S/m (Including Panels, UPS & Battery) | Installation of Passive Cooling Shelter | C-56-591-01-EI-1200 | C-56-591-01-EI-1000 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | CP Cable Laying | Installation of CP Test Post | C-56-591-01-CA-1000 | C-56-591-01-CA-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Installation of CP Test Post | Installation of CP S/m | C-56-591-01-CA-1010 | C-56-591-01-CA-1020 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Electrical & Earthing Cable Laying | CP Cable Laying | C-56-591-01-EI-2000 | C-56-591-01-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.1.16 Backfilling for Cables CCOB156C37 | Electrical & Earthing Cable Laying | Back Filling for Electrical & Earthing Cable | C-56-591-01-EI-2000 | C-56-591-01-CI-2800 | FS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.1.16 Backfilling for Cables CCOB156C37 | CP Cable Laying | Back Filling for Electrical & Earthing Cable | C-56-591-01-CA-1000 | C-56-591-01-CI-2800 | FS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.1.16 Backfilling for Cables CCOB156C37 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-56-591-01-EI-2010 | C-56-591-01-CI-2810 | FS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.5.21.1.27 Precasting for fence posts from HGCP to BVS-01CCOP52CS52.7 | P2543-R01-Oct24..4.3.1.3.5.21.1.17 Precasting for fence posts from BVS-02 to BVS-03CCOP52CS52.5 | Pre-Casting of Fence Foundation (BVS-01 to HGCP) | Pre-Casting of Fence Foundation (BVS-02 to BVS-03) | C-52-HG01-FENCE-1000 | C-52-0203-FENCE-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.16 Precasting for fence posts from BVS-03 to BVS-04CCOP52CS52.4 | P2543-R01-Oct24..4.3.1.3.5.21.1.10 Precasting for fence posts from BVS-04 to BVS-05CCOP52CS52.3 | Pre-Casting of Fence Foundation (BVS-03 to BVS-04) | Pre-Casting of Fence Foundation (BVS-04 to BVS-05) | C-52-0304-FENCE-1000 | C-52-0405-FENCE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.10 Precasting for fence posts from BVS-04 to BVS-05CCOP52CS52.3 | P2543-R01-Oct24..4.3.1.3.5.21.1.9 Precasting for fence posts from BVS-05 to BVS-06CCOP52CS52.2 | Pre-Casting of Fence Foundation (BVS-04 to BVS-05) | Pre-Casting of Fence Foundation (BVS-05 to BVS-06) | C-52-0405-FENCE-1000 | C-52-0506-FENCE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.9 Precasting for fence posts from BVS-05 to BVS-06CCOP52CS52.2 | P2543-R01-Oct24..4.3.1.3.5.21.1.8 Precasting for fence posts from BVS-06 to CRS SweihanCCOP52CS52.1 | Pre-Casting of Fence Foundation (BVS-05 to BVS-06) | Pre-Casting of Fence Foundation (BVS-06 to Sweihan-CRS) | C-52-0506-FENCE-1000 | C-52-06CR-FENCE-1000 | FS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.5.21.1.21 Precasting for fence posts from BVS-01 to BVS-02CCOP52CS52.6 | P2543-R01-Oct24..4.3.1.3.5.21.1.40 Excavation Works for fence posts from BVS-01 to BVS-02CCOP52CS53.6 | Pre-Casting of Fence Foundation (BVS-02 to BVS-01) | Earth Works for Fence Foundation (BVS-02 to BVS-01) | C-52-0102-FENCE-1000 | C-52-0102-FENCE-1010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.40 Excavation Works for fence posts from BVS-01 to BVS-02CCOP52CS53.6 | P2543-R01-Oct24..4.3.1.3.5.21.1.40 Excavation Works for fence posts from BVS-01 to BVS-02CCOP52CS53.6 | Earth Works for Fence Foundation (BVS-02 to BVS-01) | Compaction & Testing for Fence Foundation (BVS-02 to BVS-01) | C-52-0102-FENCE-1010 | C-52-0102-FENCE-1020 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.5.21.1.40 Excavation Works for fence posts from BVS-01 to BVS-02CCOP52CS53.6 | P2543-R01-Oct24..4.3.1.3.5.21.1.41 Concrete Works for fence posts from BVS-01 to BVS-02CCOP52CS54.6 | Compaction & Testing for Fence Foundation (BVS-02 to BVS-01) | Concrete Works (Blinding) for Fence Foundation (BVS-02 to BVS-01) | C-52-0102-FENCE-1020 | C-52-0102-FENCE-1030 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.5.21.1.41 Concrete Works for fence posts from BVS-01 to BVS-02CCOP52CS54.6 | P2543-R01-Oct24..4.3.1.3.5.21.1.42 Concrete Protection for fence from BVS-01 to BVS-02CCOP52CS55.6 | Concrete Works (Blinding) for Fence Foundation (BVS-02 to BVS-01) | Concrete Protection (Blinding) for Fence Foundation (BVS-02 to BVS-01) | C-52-0102-FENCE-1030 | C-52-0102-FENCE-1040 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.5.21.1.42 Concrete Protection for fence from BVS-01 to BVS-02CCOP52CS55.6 | P2543-R01-Oct24..4.3.1.3.5.21.1.43 Fence Installation (Type3) from BVS-01 to BVS-02CCOP52CS57.6 | Concrete Protection (Blinding) for Fence Foundation (BVS-02 to BVS-01) | Installation of Fence Post (Including Foundation) (BVS-02 to BVS-01) | C-52-0102-FENCE-1040 | C-52-0102-FENCE-1050 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.5.21.1.43 Fence Installation (Type3) from BVS-01 to BVS-02CCOP52CS57.6 | P2543-R01-Oct24..4.3.1.3.5.21.1.44 Backfilling for Fence from BVS-01 to BVS-02CCOP52CS56.6 | Installation of Fence Post (Including Foundation) (BVS-02 to BVS-01) | Back Filliing of Fence Post Foundation (BVS-02 to BVS-01) | C-52-0102-FENCE-1050 | C-52-0102-FENCE-1060 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.5.21.1.44 Backfilling for Fence from BVS-01 to BVS-02CCOP52CS56.6 | P2543-R01-Oct24..4.3.1.3.5.21.1.43 Fence Installation (Type3) from BVS-01 to BVS-02CCOP52CS57.6 | Back Filliing of Fence Post Foundation (BVS-02 to BVS-01) | Installation of Fence Mesh (BVS-02 to BVS-01) | C-52-0102-FENCE-1060 | C-52-0102-FENCE-1070 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.5.21.1.27 Precasting for fence posts from HGCP to BVS-01CCOP52CS52.7 | P2543-R01-Oct24..4.3.1.3.5.21.1.45 Excavation Works for fence posts from HGCP to BVS-01CCOP52CS53.7 | Pre-Casting of Fence Foundation (BVS-01 to HGCP) | Earth Works for Fence Foundation (BVS-01 to HGCP) | C-52-HG01-FENCE-1000 | C-52-HG01-FENCE-1010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.45 Excavation Works for fence posts from HGCP to BVS-01CCOP52CS53.7 | P2543-R01-Oct24..4.3.1.3.5.21.1.45 Excavation Works for fence posts from HGCP to BVS-01CCOP52CS53.7 | Earth Works for Fence Foundation (BVS-01 to HGCP) | Compaction & Testing for Fence Foundation (BVS-01 to HGCP) | C-52-HG01-FENCE-1010 | C-52-HG01-FENCE-1020 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.5.21.1.45 Excavation Works for fence posts from HGCP to BVS-01CCOP52CS53.7 | P2543-R01-Oct24..4.3.1.3.5.21.1.46 Concrete Works for fence posts from HGCP to BVS-01CCOP52CS54.7 | Compaction & Testing for Fence Foundation (BVS-01 to HGCP) | Concrete Works (Blinding) for Fence Foundation (BVS-01 to HGCP) | C-52-HG01-FENCE-1020 | C-52-HG01-FENCE-1030 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.5.21.1.46 Concrete Works for fence posts from HGCP to BVS-01CCOP52CS54.7 | P2543-R01-Oct24..4.3.1.3.5.21.1.47 Concrete Protection for fence from HGCP to BVS-01CCOP52CS55.7 | Concrete Works (Blinding) for Fence Foundation (BVS-01 to HGCP) | Concrete Protection (Blinding) for Fence Foundation (BVS-01 to HGCP) | C-52-HG01-FENCE-1030 | C-52-HG01-FENCE-1040 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.5.21.1.47 Concrete Protection for fence from HGCP to BVS-01CCOP52CS55.7 | P2543-R01-Oct24..4.3.1.3.5.21.1.48 Fence Installation (Type3) from HGCP to BVS-01CCOP52CS57.7 | Concrete Protection (Blinding) for Fence Foundation (BVS-01 to HGCP) | Installation of Fence Post (Including Foundation) (BVS-01 to HGCP) | C-52-HG01-FENCE-1040 | C-52-HG01-FENCE-1050 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.5.21.1.48 Fence Installation (Type3) from HGCP to BVS-01CCOP52CS57.7 | P2543-R01-Oct24..4.3.1.3.5.21.1.49 Backfilling for Fence from HGCP to BVS-01CCOP52CS56.7 | Installation of Fence Post (Including Foundation) (BVS-01 to HGCP) | Back Filliing of Fence Post Foundation (BVS-01 to HGCP) | C-52-HG01-FENCE-1050 | C-52-HG01-FENCE-1060 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.5.21.1.49 Backfilling for Fence from HGCP to BVS-01CCOP52CS56.7 | P2543-R01-Oct24..4.3.1.3.5.21.1.48 Fence Installation (Type3) from HGCP to BVS-01CCOP52CS57.7 | Back Filliing of Fence Post Foundation (BVS-01 to HGCP) | Installation of Fence Mesh (BVS-01 to HGCP) | C-52-HG01-FENCE-1060 | C-52-HG01-FENCE-1070 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.5.21.1.17 Precasting for fence posts from BVS-02 to BVS-03CCOP52CS52.5 | P2543-R01-Oct24..4.3.1.3.5.21.1.35 Excavation Works for fence posts from BVS-02 to BVS-03CCOP52CS53.5 | Pre-Casting of Fence Foundation (BVS-02 to BVS-03) | Earth Works for Fence Foundation (BVS-02 to BVS-03) | C-52-0203-FENCE-1000 | C-52-0203-FENCE-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.35 Excavation Works for fence posts from BVS-02 to BVS-03CCOP52CS53.5 | P2543-R01-Oct24..4.3.1.3.5.21.1.35 Excavation Works for fence posts from BVS-02 to BVS-03CCOP52CS53.5 | Earth Works for Fence Foundation (BVS-02 to BVS-03) | Compaction & Testing for Fence Foundation (BVS-02 to BVS-03) | C-52-0203-FENCE-1010 | C-52-0203-FENCE-1020 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.5.21.1.35 Excavation Works for fence posts from BVS-02 to BVS-03CCOP52CS53.5 | P2543-R01-Oct24..4.3.1.3.5.21.1.36 Concrete Works for fence posts from BVS-02 to BVS-03CCOP52CS54.5 | Compaction & Testing for Fence Foundation (BVS-02 to BVS-03) | Concrete Works (Blinding) for Fence Foundation (BVS-02 to BVS-03) | C-52-0203-FENCE-1020 | C-52-0203-FENCE-1030 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.5.21.1.36 Concrete Works for fence posts from BVS-02 to BVS-03CCOP52CS54.5 | P2543-R01-Oct24..4.3.1.3.5.21.1.37 Concrete Protection for fence from BVS-02 to BVS-03CCOP52CS55.5 | Concrete Works (Blinding) for Fence Foundation (BVS-02 to BVS-03) | Concrete Protection (Blinding) for Fence Foundation (BVS-02 to BVS-03) | C-52-0203-FENCE-1030 | C-52-0203-FENCE-1040 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.5.21.1.37 Concrete Protection for fence from BVS-02 to BVS-03CCOP52CS55.5 | P2543-R01-Oct24..4.3.1.3.5.21.1.38 Fence Installation (Type3) from BVS-02 to BVS-03CCOP52CS57.5 | Concrete Protection (Blinding) for Fence Foundation (BVS-02 to BVS-03) | Installation of Fence Post (Including Foundation) (BVS-02 to BVS-03) | C-52-0203-FENCE-1040 | C-52-0203-FENCE-1050 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.5.21.1.38 Fence Installation (Type3) from BVS-02 to BVS-03CCOP52CS57.5 | P2543-R01-Oct24..4.3.1.3.5.21.1.39 Backfilling for Fence from BVS-02 to BVS-03CCOP52CS56.5 | Installation of Fence Post (Including Foundation) (BVS-02 to BVS-03) | Back Filliing of Fence Post Foundation (BVS-02 to BVS-03) | C-52-0203-FENCE-1050 | C-52-0203-FENCE-1060 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.5.21.1.39 Backfilling for Fence from BVS-02 to BVS-03CCOP52CS56.5 | P2543-R01-Oct24..4.3.1.3.5.21.1.38 Fence Installation (Type3) from BVS-02 to BVS-03CCOP52CS57.5 | Back Filliing of Fence Post Foundation (BVS-02 to BVS-03) | Installation of Fence Mesh (BVS-02 to BVS-03) | C-52-0203-FENCE-1060 | C-52-0203-FENCE-1070 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.5.21.1.16 Precasting for fence posts from BVS-03 to BVS-04CCOP52CS52.4 | P2543-R01-Oct24..4.3.1.3.5.21.1.30 Excavation Works for fence posts from BVS-03 to BVS-04CCOP52CS53.4 | Pre-Casting of Fence Foundation (BVS-03 to BVS-04) | Earth Works for Fence Foundation (BVS-03 to BVS-04) | C-52-0304-FENCE-1000 | C-52-0304-FENCE-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.30 Excavation Works for fence posts from BVS-03 to BVS-04CCOP52CS53.4 | P2543-R01-Oct24..4.3.1.3.5.21.1.30 Excavation Works for fence posts from BVS-03 to BVS-04CCOP52CS53.4 | Earth Works for Fence Foundation (BVS-03 to BVS-04) | Compaction & Testing for Fence Foundation (BVS-03 to BVS-04) | C-52-0304-FENCE-1010 | C-52-0304-FENCE-1020 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.5.21.1.30 Excavation Works for fence posts from BVS-03 to BVS-04CCOP52CS53.4 | P2543-R01-Oct24..4.3.1.3.5.21.1.31 Concrete Works for fence posts from BVS-03 to BVS-04CCOP52CS54.4 | Compaction & Testing for Fence Foundation (BVS-03 to BVS-04) | Concrete Works (Blinding) for Fence Foundation (BVS-03 to BVS-04) | C-52-0304-FENCE-1020 | C-52-0304-FENCE-1030 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.5.21.1.31 Concrete Works for fence posts from BVS-03 to BVS-04CCOP52CS54.4 | P2543-R01-Oct24..4.3.1.3.5.21.1.32 Concrete Protection for fence from BVS-03 to BVS-04CCOP52CS55.4 | Concrete Works (Blinding) for Fence Foundation (BVS-03 to BVS-04) | Concrete Protection (Blinding) for Fence Foundation (BVS-03 to BVS-04) | C-52-0304-FENCE-1030 | C-52-0304-FENCE-1040 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.5.21.1.32 Concrete Protection for fence from BVS-03 to BVS-04CCOP52CS55.4 | P2543-R01-Oct24..4.3.1.3.5.21.1.33 Fence Installation (Type3) from BVS-03 to BVS-04CCOP52CS57.4 | Concrete Protection (Blinding) for Fence Foundation (BVS-03 to BVS-04) | Installation of Fence Post (Including Foundation) (BVS-03 to BVS-04) | C-52-0304-FENCE-1040 | C-52-0304-FENCE-1050 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.5.21.1.33 Fence Installation (Type3) from BVS-03 to BVS-04CCOP52CS57.4 | P2543-R01-Oct24..4.3.1.3.5.21.1.34 Backfilling for Fence from BVS-03 to BVS-04CCOP52CS56.4 | Installation of Fence Post (Including Foundation) (BVS-03 to BVS-04) | Back Filliing of Fence Post Foundation (BVS-03 to BVS-04) | C-52-0304-FENCE-1050 | C-52-0304-FENCE-1060 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.5.21.1.34 Backfilling for Fence from BVS-03 to BVS-04CCOP52CS56.4 | P2543-R01-Oct24..4.3.1.3.5.21.1.33 Fence Installation (Type3) from BVS-03 to BVS-04CCOP52CS57.4 | Back Filliing of Fence Post Foundation (BVS-03 to BVS-04) | Installation of Fence Mesh (BVS-03 to BVS-04) | C-52-0304-FENCE-1060 | C-52-0304-FENCE-1070 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.5.21.1.10 Precasting for fence posts from BVS-04 to BVS-05CCOP52CS52.3 | P2543-R01-Oct24..4.3.1.3.5.21.1.24 Excavation Works for fence posts from BVS-04 to BVS-05CCOP52CS53.3 | Pre-Casting of Fence Foundation (BVS-04 to BVS-05) | Earth Works for Fence Foundation (BVS-04 to BVS-05) | C-52-0405-FENCE-1000 | C-52-0405-FENCE-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.24 Excavation Works for fence posts from BVS-04 to BVS-05CCOP52CS53.3 | P2543-R01-Oct24..4.3.1.3.5.21.1.24 Excavation Works for fence posts from BVS-04 to BVS-05CCOP52CS53.3 | Earth Works for Fence Foundation (BVS-04 to BVS-05) | Compaction & Testing for Fence Foundation (BVS-04 to BVS-05) | C-52-0405-FENCE-1010 | C-52-0405-FENCE-1020 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.5.21.1.24 Excavation Works for fence posts from BVS-04 to BVS-05CCOP52CS53.3 | P2543-R01-Oct24..4.3.1.3.5.21.1.25 Concrete Works for fence posts from BVS-04 to BVS-05CCOP52CS54.3 | Compaction & Testing for Fence Foundation (BVS-04 to BVS-05) | Concrete Works (Blinding) for Fence Foundation (BVS-04 to BVS-05) | C-52-0405-FENCE-1020 | C-52-0405-FENCE-1030 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.5.21.1.25 Concrete Works for fence posts from BVS-04 to BVS-05CCOP52CS54.3 | P2543-R01-Oct24..4.3.1.3.5.21.1.26 Concrete Protection for fence from BVS-04 to BVS-05CCOP52CS55.3 | Concrete Works (Blinding) for Fence Foundation (BVS-04 to BVS-05) | Concrete Protection (Blinding) for Fence Foundation (BVS-04 to BVS-05) | C-52-0405-FENCE-1030 | C-52-0405-FENCE-1040 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.5.21.1.26 Concrete Protection for fence from BVS-04 to BVS-05CCOP52CS55.3 | P2543-R01-Oct24..4.3.1.3.5.21.1.28 Fence Installation (Type3) from BVS-04 to BVS-05CCOP52CS57.3 | Concrete Protection (Blinding) for Fence Foundation (BVS-04 to BVS-05) | Installation of Fence Post (Including Foundation) (BVS-04 to BVS-05) | C-52-0405-FENCE-1040 | C-52-0405-FENCE-1050 | FF | Not Started | Not Started | 21
P2543-R01-Oct24..4.3.1.3.5.21.1.28 Fence Installation (Type3) from BVS-04 to BVS-05CCOP52CS57.3 | P2543-R01-Oct24..4.3.1.3.5.21.1.29 Backfilling for Fence from BVS-04 to BVS-05CCOP52CS56.3 | Installation of Fence Post (Including Foundation) (BVS-04 to BVS-05) | Back Filliing of Fence Post Foundation (BVS-04 to BVS-05) | C-52-0405-FENCE-1050 | C-52-0405-FENCE-1060 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.5.21.1.29 Backfilling for Fence from BVS-04 to BVS-05CCOP52CS56.3 | P2543-R01-Oct24..4.3.1.3.5.21.1.28 Fence Installation (Type3) from BVS-04 to BVS-05CCOP52CS57.3 | Back Filliing of Fence Post Foundation (BVS-04 to BVS-05) | Installation of Fence Mesh (BVS-04 to BVS-05) | C-52-0405-FENCE-1060 | C-52-0405-FENCE-1070 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.5.21.1.9 Precasting for fence posts from BVS-05 to BVS-06CCOP52CS52.2 | P2543-R01-Oct24..4.3.1.3.5.21.1.19 Excavation Works for fence posts from BVS-05 to BVS-06CCOP52CS53.2 | Pre-Casting of Fence Foundation (BVS-05 to BVS-06) | Earth Works for Fence Foundation (BVS-05 to BVS-06) | C-52-0506-FENCE-1000 | C-52-0506-FENCE-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.19 Excavation Works for fence posts from BVS-05 to BVS-06CCOP52CS53.2 | P2543-R01-Oct24..4.3.1.3.5.21.1.19 Excavation Works for fence posts from BVS-05 to BVS-06CCOP52CS53.2 | Earth Works for Fence Foundation (BVS-05 to BVS-06) | Compaction & Testing for Fence Foundation (BVS-05 to BVS-06) | C-52-0506-FENCE-1010 | C-52-0506-FENCE-1020 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.5.21.1.19 Excavation Works for fence posts from BVS-05 to BVS-06CCOP52CS53.2 | P2543-R01-Oct24..4.3.1.3.5.21.1.18 Concrete Works for fence posts from BVS-05 to BVS-06CCOP52CS54.2 | Compaction & Testing for Fence Foundation (BVS-05 to BVS-06) | Concrete Works (Blinding) for Fence Foundation (BVS-05 to BVS-06) | C-52-0506-FENCE-1020 | C-52-0506-FENCE-1030 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.5.21.1.18 Concrete Works for fence posts from BVS-05 to BVS-06CCOP52CS54.2 | P2543-R01-Oct24..4.3.1.3.5.21.1.20 Concrete Protection for fence from BVS-05 to BVS-06CCOP52CS55.2 | Concrete Works (Blinding) for Fence Foundation (BVS-05 to BVS-06) | Concrete Protection (Blinding) for Fence Foundation (BVS-05 to BVS-06) | C-52-0506-FENCE-1030 | C-52-0506-FENCE-1040 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.5.21.1.20 Concrete Protection for fence from BVS-05 to BVS-06CCOP52CS55.2 | P2543-R01-Oct24..4.3.1.3.5.21.1.22 Fence Installation (Type3) from BVS-05 to BVS-06CCOP52CS57.2 | Concrete Protection (Blinding) for Fence Foundation (BVS-05 to BVS-06) | Installation of Fence Post (Including Foundation) (BVS-05 to BVS-06) | C-52-0506-FENCE-1040 | C-52-0506-FENCE-1050 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.5.21.1.22 Fence Installation (Type3) from BVS-05 to BVS-06CCOP52CS57.2 | P2543-R01-Oct24..4.3.1.3.5.21.1.23 Backfilling for Fence from BVS-05 to BVS-06CCOP52CS56.2 | Installation of Fence Post (Including Foundation) (BVS-05 to BVS-06) | Back Filliing of Fence Post Foundation (BVS-05 to BVS-06) | C-52-0506-FENCE-1050 | C-52-0506-FENCE-1060 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.5.21.1.23 Backfilling for Fence from BVS-05 to BVS-06CCOP52CS56.2 | P2543-R01-Oct24..4.3.1.3.5.21.1.22 Fence Installation (Type3) from BVS-05 to BVS-06CCOP52CS57.2 | Back Filliing of Fence Post Foundation (BVS-05 to BVS-06) | Installation of Fence Mesh (BVS-05 to BVS-06) | C-52-0506-FENCE-1060 | C-52-0506-FENCE-1070 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.5.21.1.8 Precasting for fence posts from BVS-06 to CRS SweihanCCOP52CS52.1 | P2543-R01-Oct24..4.3.1.3.5.21.1.11 Excavation Works for Fence from BVS-06 to CRS SweihanCCOP52CS53.1 | Pre-Casting of Fence Foundation (BVS-06 to Sweihan-CRS) | Earth Works for Fence Foundation (BVS-06 to Sweihan-CRS) | C-52-06CR-FENCE-1000 | C-52-06CR-FENCE-1010 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.5.21.1.11 Excavation Works for Fence from BVS-06 to CRS SweihanCCOP52CS53.1 | P2543-R01-Oct24..4.3.1.3.5.21.1.11 Excavation Works for Fence from BVS-06 to CRS SweihanCCOP52CS53.1 | Earth Works for Fence Foundation (BVS-06 to Sweihan-CRS) | Compaction & Testing for Fence Foundation (BVS-06 to Sweihan-CRS) | C-52-06CR-FENCE-1010 | C-52-06CR-FENCE-1020 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.5.21.1.11 Excavation Works for Fence from BVS-06 to CRS SweihanCCOP52CS53.1 | P2543-R01-Oct24..4.3.1.3.5.21.1.12 Concrete Works for Fence from BVS-06 to CRS SweihanCCOP52CS54.1 | Compaction & Testing for Fence Foundation (BVS-06 to Sweihan-CRS) | Concrete Works (Blinding) for Fence Foundation (BVS-06 to Sweihan-CRS) | C-52-06CR-FENCE-1020 | C-52-06CR-FENCE-1030 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.5.21.1.12 Concrete Works for Fence from BVS-06 to CRS SweihanCCOP52CS54.1 | P2543-R01-Oct24..4.3.1.3.5.21.1.13 Concrete Protection for Fence from BVS-06 to CRS SweihanCCOP52CS55.1 | Concrete Works (Blinding) for Fence Foundation (BVS-06 to Sweihan-CRS) | Concrete Protection (Blinding) for Fence Foundation (BVS-06 to Sweihan-CRS) | C-52-06CR-FENCE-1030 | C-52-06CR-FENCE-1040 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.5.21.1.13 Concrete Protection for Fence from BVS-06 to CRS SweihanCCOP52CS55.1 | P2543-R01-Oct24..4.3.1.3.5.21.1.14 Fence Installation (Type3) from BVS-06 to CRS SweihanCCOP52CS57.1 | Concrete Protection (Blinding) for Fence Foundation (BVS-06 to Sweihan-CRS) | Installation of Fence Post (Including Foundation) (BVS-06 to Sweihan-CRS) | C-52-06CR-FENCE-1040 | C-52-06CR-FENCE-1050 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.5.21.1.14 Fence Installation (Type3) from BVS-06 to CRS SweihanCCOP52CS57.1 | P2543-R01-Oct24..4.3.1.3.5.21.1.15 Backfilling for Fence from BVS-06 to CRS SweihanCCOP52CS56.1 | Installation of Fence Post (Including Foundation) (BVS-06 to Sweihan-CRS) | Back Filliing of Fence Post Foundation (BVS-06 to Sweihan-CRS) | C-52-06CR-FENCE-1050 | C-52-06CR-FENCE-1060 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.5.21.1.15 Backfilling for Fence from BVS-06 to CRS SweihanCCOP52CS56.1 | P2543-R01-Oct24..4.3.1.3.5.21.1.14 Fence Installation (Type3) from BVS-06 to CRS SweihanCCOP52CS57.1 | Back Filliing of Fence Post Foundation (BVS-06 to Sweihan-CRS) | Installation of Fence Mesh (BVS-06 to Sweihan-CRS) | C-52-06CR-FENCE-1060 | C-52-06CR-FENCE-1070 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | P2543-R01-Oct24..4.3.1.3.5.21.1.40 Excavation Works for fence posts from BVS-01 to BVS-02CCOP52CS53.6 | Gatch Compaction | Earth Works for Fence Foundation (BVS-02 to BVS-01) | C-52-0102-PL-CI-6810 | C-52-0102-FENCE-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.27 BermingCCOPL52316 | P2543-R01-Oct24..4.3.1.3.5.21.1.45 Excavation Works for fence posts from HGCP to BVS-01CCOP52CS53.7 | Gatch Compaction | Earth Works for Fence Foundation (BVS-01 to HGCP) | C-52-HG01-PL-CI-6810 | C-52-HG01-FENCE-1010 | SS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | P2543-R01-Oct24..4.3.1.3.5.21.1.35 Excavation Works for fence posts from BVS-02 to BVS-03CCOP52CS53.5 | Gatch Compaction | Earth Works for Fence Foundation (BVS-02 to BVS-03) | C-52-0203-PL-CI-6810 | C-52-0203-FENCE-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | P2543-R01-Oct24..4.3.1.3.5.21.1.30 Excavation Works for fence posts from BVS-03 to BVS-04CCOP52CS53.4 | Gatch Compaction | Earth Works for Fence Foundation (BVS-03 to BVS-04) | C-52-0304-PL-CI-6810 | C-52-0304-FENCE-1010 | FS | Not Started | Not Started | 50
P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | P2543-R01-Oct24..4.3.1.3.5.21.1.19 Excavation Works for fence posts from BVS-05 to BVS-06CCOP52CS53.2 | Gatch Compaction | Earth Works for Fence Foundation (BVS-05 to BVS-06) | C-52-0506-PL-CI-6810 | C-52-0506-FENCE-1010 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | P2543-R01-Oct24..4.3.1.3.5.21.1.11 Excavation Works for Fence from BVS-06 to CRS SweihanCCOP52CS53.1 | Gatch Compaction | Earth Works for Fence Foundation (BVS-06 to Sweihan-CRS) | C-52-06CR-PL-CI-6810 | C-52-06CR-FENCE-1010 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.2.21.12.1.15 Backfilling for Cables CCOH56CS36 | Electrical & Earthing Cable Laying | Back Filling for Electrical & Earthing Cable | C-56-PR-838-EI-2000 | C-56-PR-838-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.2.21.12.1.15 Backfilling for Cables CCOH56CS36 | CP Cable Laying | Back Filling for Electrical & Earthing Cable | C-56-PR-838-CA-1000 | C-56-PR-838-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.2.21.12.1.15 Backfilling for Cables CCOH56CS36 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-56-PR-838-EI-2010 | C-56-PR-838-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.8.33 CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) CCOH56IC30 | P2543-R01-Oct24..4.3.1.2.21.12.1.15 Backfilling for Cables CCOH56CS36 | FOC Laying | Back Filling for Instrument & Telecom Cable | C-56-PR-838-TE-1410 | C-56-PR-838-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.15 Backfilling for Cables CCOH56CS36 | P2543-R01-Oct24..4.3.1.2.21.12.1.16 Paving Works CCOH56CS37 | Back Filling for Electrical & Earthing Cable | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PR-838-CI-2800 | C-56-PR-838-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.15 Backfilling for Cables CCOH56CS36 | P2543-R01-Oct24..4.3.1.2.21.12.1.16 Paving Works CCOH56CS37 | Back Filling for Instrument & Telecom Cable | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PR-838-CI-2810 | C-56-PR-838-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | P2543-R01-Oct24..4.3.1.2.21.12.1.16 Paving Works CCOH56CS37 | Installation of Field Instruments (Including Pig Signaller) | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PR-838-EI-2200 | C-56-PR-838-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | P2543-R01-Oct24..4.3.1.2.21.12.1.16 Paving Works CCOH56CS37 | Installation of JB's | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PR-838-EI-1810 | C-56-PR-838-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | P2543-R01-Oct24..4.3.1.2.21.12.1.16 Paving Works CCOH56CS37 | Installation of F&G Device | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PR-838-EI-2410 | C-56-PR-838-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | P2543-R01-Oct24..4.3.1.2.21.12.1.16 Paving Works CCOH56CS37 | Installation of CP JB's | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PR-838-EI-1020 | C-56-PR-838-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | P2543-R01-Oct24..4.3.1.2.21.12.1.16 Paving Works CCOH56CS37 | Installation of CP Test Post | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PR-838-EI-1010 | C-56-PR-838-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.17 Pipe Supports Fabrication & Installation CCOH56SS50 | P2543-R01-Oct24..4.3.1.2.21.12.1.16 Paving Works CCOH56CS37 | Pre-Fabrication & Installation of Pipe Supports | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PR-838-CI-2000 | C-56-PR-838-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | P2543-R01-Oct24..4.3.1.2.21.12.1.16 Paving Works CCOH56CS37 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PR-838-EI-2210 | C-56-PR-838-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.18 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOH56SS51 | P2543-R01-Oct24..4.3.1.2.21.12.1.16 Paving Works CCOH56CS37 | Pre-Fabrication & Installation of Platforms & Crossovers | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PR-838-CI-3000 | C-56-PR-838-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.18 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOH56SS51 | P2543-R01-Oct24..4.3.1.2.21.12.1.16 Paving Works CCOH56CS37 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PR-838-CI-3010 | C-56-PR-838-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.38 Fence Installation (Type3) from BVS-02 to BVS-03CCOP52CS57.5 | P2543-R01-Oct24..4.3.1.3.5.21.1.33 Fence Installation (Type3) from BVS-03 to BVS-04CCOP52CS57.4 | Installation of Fence Post (Including Foundation) (BVS-02 to BVS-03) | Installation of Fence Post (Including Foundation) (BVS-03 to BVS-04) | C-52-0203-FENCE-1050 | C-52-0304-FENCE-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB552C37 | P2543-R01-Oct24..4.3.1.3.13.21.1.6 Pipe Supports Fabrication & InstallationCCOB552S51 | Concrete Works for Pipe Support Foundations | Pre-Fabrication & Installation of Pipe Supports | C-52-598-02-CI-1600 | C-52-598-02-CI-2000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.13.21.6.6 Field InstrumentsCCOB552E95 | P2543-R01-Oct24..4.3.1.3.13.21.1.8 Fire Point SheltersCCOB552S52 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Fire Point Shelters | C-52-598-02-EI-2210 | C-52-598-02-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.8 Fire Point SheltersCCOB552S52 | P2543-R01-Oct24..4.3.1.3.13.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB552M52 | Installation of Fire Point Shelters | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | C-52-598-02-CI-2400 | C-52-598-02-ME-1000 | FS | Not Started | Not Started | 30
P2543-R01-Oct24..4.3.1.3.13.21.1.5 Trenching for CablesCCOB552C40 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Laying | C-52-598-02-CI-1800 | C-52-598-02-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Electrical & Earthing Cable Laying | Deep Earth Well Drilling | C-52-598-02-EI-2000 | C-52-598-02-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Electrical & Earthing Cable Laying | Instrument Cable Laying | C-52-598-02-EI-2000 | C-52-598-02-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Instrument Cable Laying | Installation of Cable Trays | C-52-598-02-EI-2010 | C-52-598-02-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Installation of Cable Trays | Instrument Tubing Works | C-52-598-02-EI-2020 | C-52-598-02-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Installation of Solar Panel Structural Supports | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-598-02-EI-1210 | C-52-598-02-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | P2543-R01-Oct24..4.3.1.3.13.21.6.5 Light Pole, Lighting & FixturesCCOB552E85 | Installation of Solar S/m (Including Panels, UPS & Battery) | Installation of Light Pole, Lighting & Fixtures | C-52-598-02-EI-1200 | C-52-598-02-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.2 Compaction & TestingCCOB552C34 | P2543-R01-Oct24..4.3.1.3.13.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB552E51 | Compaction & Testing for Equipment Foundations & Hard Stand Area | Installation of Passive Cooling Shelter | C-52-598-02-CI-1200 | C-52-598-02-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Concrete Works for Equipment Foundations & Hard Stand Area | Installation of Solar Panel Structural Supports | C-52-598-02-CI-1400 | C-52-598-02-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.6 Field InstrumentsCCOB552E95 | P2543-R01-Oct24..4.3.1.3.13.21.6.5 Light Pole, Lighting & FixturesCCOB552E85 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Light Pole, Lighting & Fixtures | C-52-598-02-EI-2210 | C-52-598-02-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.5 Light Pole, Lighting & FixturesCCOB552E85 | P2543-R01-Oct24..4.3.1.3.13.21.6.5 Light Pole, Lighting & FixturesCCOB552E85 | Installation of Light Pole, Lighting & Fixtures | Installation of Lighting & Instrument JB's | C-52-598-02-EI-1800 | C-52-598-02-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.6 Field InstrumentsCCOB552E95 | P2543-R01-Oct24..4.3.1.3.13.21.6.6 Field InstrumentsCCOB552E95 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Field Instruments | C-52-598-02-EI-2210 | C-52-598-02-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | P2543-R01-Oct24..4.3.1.3.13.21.6.6 Field InstrumentsCCOB552E95 | Concrete Works for Field Instrument, JB Foundations | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-02-CI-1410 | C-52-598-02-EI-2210 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.6.6 Field InstrumentsCCOB552E95 | Instrument Tubing Works | Installation of Field Instruments | C-52-598-02-EI-2030 | C-52-598-02-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.6 Field InstrumentsCCOB552E95 | P2543-R01-Oct24..4.3.1.3.13.21.6.8 F&G DevicesCCOB552E105 | Installation of Field Instruments | Installation of F&G Devices | C-52-598-02-EI-2200 | C-52-598-02-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.8 F&G DevicesCCOB552E105 | P2543-R01-Oct24..4.3.1.3.13.21.6.6 Field InstrumentsCCOB552E95 | Installation of F&G Panel | Installation of Field Instruments | C-52-598-02-EI-2400 | C-52-598-02-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Electrical & Earthing Cable Laying | CP Cable Laying | C-52-598-02-EI-2000 | C-52-598-02-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.5 Trenching for CablesCCOB552C40 | P2543-R01-Oct24..4.3.1.3.13.21.1.10 Backfilling for CablesCCOB552C56 | Instrument & Telecom Cable Trenching | Back Filling for Electrical & Earthing Cable | C-52-598-02-CI-1810 | C-52-598-02-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.1.10 Backfilling for CablesCCOB552C56 | Electrical & Earthing Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-598-02-EI-2000 | C-52-598-02-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | P2543-R01-Oct24..4.3.1.3.13.21.1.10 Backfilling for CablesCCOB552C56 | Deep Earth Well Drilling | Back Filling for Electrical & Earthing Cable | C-52-598-02-EI-1400 | C-52-598-02-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.1.10 Backfilling for CablesCCOB552C56 | CP Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-598-02-CA-1000 | C-52-598-02-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.5 Trenching for CablesCCOB552C40 | P2543-R01-Oct24..4.3.1.3.13.21.1.10 Backfilling for CablesCCOB552C56 | Instrument & Telecom Cable Trenching | Back Filling for Instrument & Telecom Cable | C-52-598-02-CI-1810 | C-52-598-02-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.1.10 Backfilling for CablesCCOB552C56 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-52-598-02-EI-2010 | C-52-598-02-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | P2543-R01-Oct24..4.3.1.3.13.21.1.7 Fences & Gates ConstructionCCOB552C38 | Concrete Works for Light Pole, Fence & Gates Foundation | Installation of Concrete Pillers for Boundary Wall | C-52-598-02-CI-1430 | C-52-598-02-CI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.7 Fences & Gates ConstructionCCOB552C38 | P2543-R01-Oct24..4.3.1.3.13.21.1.7 Fences & Gates ConstructionCCOB552C38 | Installation of Concrete Pillers for Boundary Wall | Block Works for Boundary Wall | C-52-598-02-CI-2200 | C-52-598-02-CI-2210 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.13.21.1.7 Fences & Gates ConstructionCCOB552C38 | P2543-R01-Oct24..4.3.1.3.13.21.1.7 Fences & Gates ConstructionCCOB552C38 | Block Works for Boundary Wall | Installation of Fence Post & Mesh Works (Type-4 & 3) | C-52-598-02-CI-2210 | C-52-598-02-CI-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 | P2543-R01-Oct24..4.3.1.3.13.21.1.7 Fences & Gates ConstructionCCOB552C38 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Installation of Fence Post & Mesh Works (Type-4 & 3) | C-52-598-02-CI-3010 | C-52-598-02-CI-2220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.7 Fences & Gates ConstructionCCOB552C38 | P2543-R01-Oct24..4.3.1.3.13.21.1.9 Paving WorksCCOB552C39 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | Paving of Interlock tiles & Kerb Stone Embankment | C-52-598-02-CI-2230 | C-52-598-02-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.9 Paving WorksCCOB552C39 | P2543-R01-Oct24..4.3.1.3.13.21.1.9 Paving WorksCCOB552C39 | Paving of Interlock tiles & Kerb Stone Embankment | Rip-Rap Protection Laying | C-52-598-02-CI-2600 | C-52-598-02-CI-2610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.7 Fences & Gates ConstructionCCOB552C38 | P2543-R01-Oct24..4.3.1.3.13.21.1.7 Fences & Gates ConstructionCCOB552C38 | Installation of Fence Post & Mesh Works (Type-4 & 3) | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | C-52-598-02-CI-2220 | C-52-598-02-CI-2230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | P2543-R01-Oct24..4.3.1.3.14.21.1.7 Fences & Gates ConstructionCCOB652C39 | Concrete Works for Light Pole, Fence & Gates Foundation | Installation of Concrete Pillers for Boundary Wall | C-52-598-01-CI-1430 | C-52-598-01-CI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.7 Fences & Gates ConstructionCCOB652C39 | P2543-R01-Oct24..4.3.1.3.14.21.1.7 Fences & Gates ConstructionCCOB652C39 | Installation of Concrete Pillers for Boundary Wall | Block Works for Boundary Wall | C-52-598-01-CI-2200 | C-52-598-01-CI-2210 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.14.21.1.7 Fences & Gates ConstructionCCOB652C39 | P2543-R01-Oct24..4.3.1.3.14.21.1.7 Fences & Gates ConstructionCCOB652C39 | Block Works for Boundary Wall | Installation of Fence Post & Mesh Works (Type-4 & 3) | C-52-598-01-CI-2210 | C-52-598-01-CI-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.7 Fences & Gates ConstructionCCOB652C39 | P2543-R01-Oct24..4.3.1.3.14.21.1.7 Fences & Gates ConstructionCCOB652C39 | Installation of Fence Post & Mesh Works (Type-4 & 3) | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | C-52-598-01-CI-2220 | C-52-598-01-CI-2230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.7 Fences & Gates ConstructionCCOB652C39 | P2543-R01-Oct24..4.3.1.3.14.21.1.9 Paving WorksCCOB652C42 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | Paving of Interlock tiles & Kerb Stone Embankment | C-52-598-01-CI-2230 | C-52-598-01-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.9 Paving WorksCCOB652C42 | P2543-R01-Oct24..4.3.1.3.14.21.1.9 Paving WorksCCOB652C42 | Paving of Interlock tiles & Kerb Stone Embankment | Rip-Rap Protection Laying | C-52-598-01-CI-2600 | C-52-598-01-CI-2610 | SS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.14.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB652C37 | P2543-R01-Oct24..4.3.1.3.14.21.1.6 Pipe Supports Fabrication & InstallationCCOB652S52 | Concrete Works for Pipe Support Foundations | Pre-Fabrication & Installation of Pipe Supports | C-52-598-01-CI-1600 | C-52-598-01-CI-2000 | FS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | P2543-R01-Oct24..4.3.1.3.14.21.6.7 Field InstrumentsCCOB652E95 | Concrete Works for Field Instrument, JB Foundations | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-01-CI-1410 | C-52-598-01-EI-2210 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | P2543-R01-Oct24..4.3.1.3.14.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB652S56 | Concrete Works for Access Platform & Misc. Structural Foundations | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-01-CI-1420 | C-52-598-01-CI-3000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | P2543-R01-Oct24..4.3.1.3.13.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 | Concrete Works for Access Platform & Misc. Structural Foundations | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-02-CI-1420 | C-52-598-02-CI-3000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | P2543-R01-Oct24..4.3.1.3.13.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 | Concrete Works for Access Platform & Misc. Structural Foundations | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-02-CI-1420 | C-52-598-02-CI-3010 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | P2543-R01-Oct24..4.3.1.3.14.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB652S56 | Concrete Works for Access Platform & Misc. Structural Foundations | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-01-CI-1420 | C-52-598-01-CI-3010 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Concrete Works for Equipment Foundations & Hard Stand Area | Installation of Solar Panel Structural Supports | C-52-598-01-CI-1400 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.7 Field InstrumentsCCOB652E95 | P2543-R01-Oct24..4.3.1.3.14.21.1.8 Fire Point SheltersCCOB652S54 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Fire Point Shelters | C-52-598-01-EI-2210 | C-52-598-01-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.8 Fire Point SheltersCCOB652S54 | P2543-R01-Oct24..4.3.1.3.14.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB652M52 | Installation of Fire Point Shelters | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | C-52-598-01-CI-2400 | C-52-598-01-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.6 Pipe Supports Fabrication & InstallationCCOB552S51 | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Pre-Fabrication & Installation of Pipe Supports | Piping Erection | C-52-598-02-CI-2000 | C-52-598-02-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.6 Pipe Supports Fabrication & InstallationCCOB652S52 | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Pre-Fabrication & Installation of Pipe Supports | Piping Erection | C-52-598-01-CI-2000 | C-52-598-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Electrical & Earthing Cable Laying | Deep Earth Well Drilling | C-52-598-01-EI-2000 | C-52-598-01-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.5 Trenching for CablesCCOB652C40 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Laying | C-52-598-01-CI-1800 | C-52-598-01-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.5 Trenching for CablesCCOB552C40 | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-52-598-02-CI-1810 | C-52-598-02-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Electrical & Earthing Cable Laying | Instrument Cable Laying | C-52-598-01-EI-2000 | C-52-598-01-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.5 Trenching for CablesCCOB652C40 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-52-598-01-CI-1810 | C-52-598-01-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Instrument Cable Laying | Installation of Cable Trays | C-52-598-01-EI-2010 | C-52-598-01-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Installation of Cable Trays | Instrument Tubing Works | C-52-598-01-EI-2020 | C-52-598-01-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Installation of Solar Panel Structural Supports | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-598-01-EI-1210 | C-52-598-01-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.7 Field InstrumentsCCOB652E95 | P2543-R01-Oct24..4.3.1.3.14.21.6.5 Light Pole, Lighting & FixturesCCOB652E85 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Light Pole, Lighting & Fixtures | C-52-598-01-EI-2210 | C-52-598-01-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | P2543-R01-Oct24..4.3.1.3.14.21.6.5 Light Pole, Lighting & FixturesCCOB652E85 | Installation of Solar S/m (Including Panels, UPS & Battery) | Installation of Light Pole, Lighting & Fixtures | C-52-598-01-EI-1200 | C-52-598-01-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | P2543-R01-Oct24..4.3.1.3.14.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB652E51 | Concrete Works for Equipment Foundations & Hard Stand Area | Installation of Passive Cooling Shelter | C-52-598-01-CI-1400 | C-52-598-01-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.5 Light Pole, Lighting & FixturesCCOB652E85 | P2543-R01-Oct24..4.3.1.3.14.21.6.5 Light Pole, Lighting & FixturesCCOB652E85 | Installation of Light Pole, Lighting & Fixtures | Installation of Lighting & Instrument JB's | C-52-598-01-EI-1800 | C-52-598-01-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.7 Field InstrumentsCCOB652E95 | P2543-R01-Oct24..4.3.1.3.14.21.6.7 Field InstrumentsCCOB652E95 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Field Instruments | C-52-598-01-EI-2210 | C-52-598-01-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.7 Field InstrumentsCCOB652E95 | P2543-R01-Oct24..4.3.1.3.14.21.6.8 F&G DevicesCCOB652E105 | Installation of Field Instruments | Installation of F&G Devices | C-52-598-01-EI-2200 | C-52-598-01-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | P2543-R01-Oct24..4.3.1.3.14.21.7.1 CP Anode Bed Installation (subcontract)CCOB652E30 | Electrical & Earthing Cable Laying | CP Cable Laying | C-52-598-01-EI-2000 | C-52-598-01-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | P2543-R01-Oct24..4.3.1.3.14.21.1.10 Backfilling for CablesCCOB652C41 | Electrical & Earthing Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-598-01-EI-2000 | C-52-598-01-CI-2800 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.14.21.7.1 CP Anode Bed Installation (subcontract)CCOB652E30 | P2543-R01-Oct24..4.3.1.3.14.21.1.10 Backfilling for CablesCCOB652C41 | CP Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-598-01-CA-1000 | C-52-598-01-CI-2800 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | P2543-R01-Oct24..4.3.1.3.14.21.1.10 Backfilling for CablesCCOB652C41 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-52-598-01-EI-2010 | C-52-598-01-CI-2810 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | Earth Works for Equipment Foundations & Hard Stand Area | Earth Works for Equipment Foundations & Hard Stand Area | C-52-598-01-CI-1010 | C-56-591-01-CI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB652C37 | P2543-R01-Oct24..4.3.1.2.1.12.1.13 Concrete Works (Foundations for Pipe Supports) CCOB156C32 | Concrete Works for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-52-598-01-CI-1600 | C-56-591-01-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Concrete Works for Field Instrument, JB Foundations | Concrete Works for Access Platform & Misc. Structural Foundations | C-56-591-01-CI-1410 | C-56-591-01-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Concrete Works for Access Platform & Misc. Structural Foundations | Concrete Works for Light Pole, Fence & Gates Foundation | C-56-591-01-CI-1420 | C-56-591-01-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | P2543-R01-Oct24..4.3.1.3.12.21.1.8 Fences & Gates ConstructionCCOB452C37 | Concrete Works for Light Pole, Fence & Gates Foundation | Installation of Concrete Pillers for Boundary Wall | C-52-598-03-CI-1430 | C-52-598-03-CI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.8 Fences & Gates ConstructionCCOB452C37 | P2543-R01-Oct24..4.3.1.3.12.21.1.8 Fences & Gates ConstructionCCOB452C37 | Installation of Concrete Pillers for Boundary Wall | Block Works for Boundary Wall | C-52-598-03-CI-2200 | C-52-598-03-CI-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.8 Fences & Gates ConstructionCCOB452C37 | P2543-R01-Oct24..4.3.1.3.12.21.1.8 Fences & Gates ConstructionCCOB452C37 | Block Works for Boundary Wall | Installation of Fence Post & Mesh Works (Type-4 & 3) | C-52-598-03-CI-2210 | C-52-598-03-CI-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.8 Fences & Gates ConstructionCCOB452C37 | P2543-R01-Oct24..4.3.1.3.12.21.1.8 Fences & Gates ConstructionCCOB452C37 | Installation of Fence Post & Mesh Works (Type-4 & 3) | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | C-52-598-03-CI-2220 | C-52-598-03-CI-2230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.8 Fences & Gates ConstructionCCOB452C37 | P2543-R01-Oct24..4.3.1.3.12.21.1.7 Paving WorksCCOB452C38 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | Paving of Interlock tiles & Kerb Stone Embankment | C-52-598-03-CI-2230 | C-52-598-03-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.7 Paving WorksCCOB452C38 | P2543-R01-Oct24..4.3.1.3.12.21.1.7 Paving WorksCCOB452C38 | Paving of Interlock tiles & Kerb Stone Embankment | Rip-Rap Protection Laying | C-52-598-03-CI-2600 | C-52-598-03-CI-2610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB452C34.2 | P2543-R01-Oct24..4.3.1.3.12.21.1.5 Pipe Supports Fabrication & InstallationCCOB452S51 | Concrete Works for Pipe Support Foundations | Pre-Fabrication & Installation of Pipe Supports | C-52-598-03-CI-1600 | C-52-598-03-CI-2000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.12.21.6.6 Field InstrumentsCCOB452E93 | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Solar Panel Structural Supports | C-52-598-03-EI-2210 | C-52-598-03-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.6 Field InstrumentsCCOB452E93 | P2543-R01-Oct24..4.3.1.3.12.21.1.9 Fire Point SheltersCCOB452S53 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Fire Point Shelters | C-52-598-03-EI-2210 | C-52-598-03-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.9 Fire Point SheltersCCOB452S53 | P2543-R01-Oct24..4.3.1.3.12.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB452M51 | Installation of Fire Point Shelters | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | C-52-598-03-CI-2400 | C-52-598-03-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.6 Trenching for CablesCCOB452C39 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Laying | C-52-598-03-CI-1800 | C-52-598-03-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Electrical & Earthing Cable Laying | Deep Earth Well Drilling | C-52-598-03-EI-2000 | C-52-598-03-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Electrical & Earthing Cable Laying | Instrument Cable Laying | C-52-598-03-EI-2000 | C-52-598-03-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.6 Trenching for CablesCCOB452C39 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-52-598-03-CI-1810 | C-52-598-03-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Instrument Cable Laying | Installation of Cable Trays | C-52-598-03-EI-2010 | C-52-598-03-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Installation of Cable Trays | Instrument Tubing Works | C-52-598-03-EI-2020 | C-52-598-03-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Installation of Solar Panel Structural Supports | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-598-03-EI-1210 | C-52-598-03-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.6 Field InstrumentsCCOB452E93 | P2543-R01-Oct24..4.3.1.3.12.21.6.5 Light Pole, Lighting & FixturesCCOB452E83 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Light Pole, Lighting & Fixtures | C-52-598-03-EI-2210 | C-52-598-03-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | P2543-R01-Oct24..4.3.1.3.12.21.6.5 Light Pole, Lighting & FixturesCCOB452E83 | Installation of Solar S/m (Including Panels, UPS & Battery) | Installation of Light Pole, Lighting & Fixtures | C-52-598-03-EI-1200 | C-52-598-03-EI-1800 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | P2543-R01-Oct24..4.3.1.3.12.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB452E50 | Concrete Works for Equipment Foundations & Hard Stand Area | Installation of Passive Cooling Shelter | C-52-598-03-CI-1400 | C-52-598-03-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.5 Light Pole, Lighting & FixturesCCOB452E83 | P2543-R01-Oct24..4.3.1.3.12.21.6.5 Light Pole, Lighting & FixturesCCOB452E83 | Installation of Light Pole, Lighting & Fixtures | Installation of Lighting & Instrument JB's | C-52-598-03-EI-1800 | C-52-598-03-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.6 Field InstrumentsCCOB452E93 | P2543-R01-Oct24..4.3.1.3.12.21.6.6 Field InstrumentsCCOB452E93 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Field Instruments | C-52-598-03-EI-2210 | C-52-598-03-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.1.3.12.21.6.6 Field InstrumentsCCOB452E93 | Instrument Cable Laying | Installation of Field Instruments | C-52-598-03-EI-2010 | C-52-598-03-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.6 Field InstrumentsCCOB452E93 | P2543-R01-Oct24..4.3.1.3.12.21.6.8 F&G DevicesCCOB452E103 | Installation of Field Instruments | Installation of F&G Devices | C-52-598-03-EI-2200 | C-52-598-03-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.1.3.12.21.6.6 Field InstrumentsCCOB452E93 | Instrument Tubing Works | Installation of Field Instruments | C-52-598-03-EI-2030 | C-52-598-03-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.1.3.12.21.7.1 CP Anode Bed Installation (subcontract)CCOB452E30 | Electrical & Earthing Cable Laying | CP Cable Laying | C-52-598-03-EI-2000 | C-52-598-03-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.1.3.12.21.1.10 Backfilling for CablesCCOB452C40 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-52-598-03-EI-2010 | C-52-598-03-CI-2810 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.1.3.12.21.1.10 Backfilling for CablesCCOB452C40 | Electrical & Earthing Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-598-03-EI-2000 | C-52-598-03-CI-2800 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.12.21.7.1 CP Anode Bed Installation (subcontract)CCOB452E30 | P2543-R01-Oct24..4.3.1.3.12.21.1.10 Backfilling for CablesCCOB452C40 | CP Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-598-03-CA-1000 | C-52-598-03-CI-2800 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.12.21.1.10 Backfilling for CablesCCOB452C40 | P2543-R01-Oct24..4.3.1.3.12.21.1.10 Backfilling for CablesCCOB452C40 | Back Filling for Electrical & Earthing Cable | Back Filling for Instrument & Telecom Cable | C-52-598-03-CI-2800 | C-52-598-03-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.2 Compaction & TestingCCOB352C32 | P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | Compaction & Testing for Light Pole, Fence & Gates Foundation | Installation of Concrete Pillers for Boundary Wall | C-52-598-04-CI-1240 | C-52-598-04-CI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | Installation of Concrete Pillers for Boundary Wall | Block Works for Boundary Wall | C-52-598-04-CI-2200 | C-52-598-04-CI-2210 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | Block Works for Boundary Wall | Installation of Fence Post & Mesh Works (Type-4 & 3) | C-52-598-04-CI-2210 | C-52-598-04-CI-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | Installation of Fence Post & Mesh Works (Type-4 & 3) | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | C-52-598-04-CI-2220 | C-52-598-04-CI-2230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | Paving of Interlock tiles & Kerb Stone Embankment | C-52-598-04-CI-2230 | C-52-598-04-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | Paving of Interlock tiles & Kerb Stone Embankment | Rip-Rap Protection Laying | C-52-598-04-CI-2600 | C-52-598-04-CI-2610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB352C34 | P2543-R01-Oct24..4.3.1.3.11.21.1.7 Pipe Supports Fabrication & InstallationCCOB352S50 | Concrete Works for Pipe Support Foundations | Pre-Fabrication & Installation of Pipe Supports | C-52-598-04-CI-1600 | C-52-598-04-CI-2000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.11.21.6.8 Field InstrumentsCCOB352E102 | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Solar Panel Structural Supports | C-52-598-04-EI-2210 | C-52-598-04-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.8 Field InstrumentsCCOB352E102 | P2543-R01-Oct24..4.3.1.3.11.21.1.6 Fire Point SheltersCCOB352S51 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Fire Point Shelters | C-52-598-04-EI-2210 | C-52-598-04-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.6 Fire Point SheltersCCOB352S51 | P2543-R01-Oct24..4.3.1.3.11.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB352M51 | Installation of Fire Point Shelters | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | C-52-598-04-CI-2400 | C-52-598-04-ME-1000 | FS | Not Started | Not Started | 15
P2543-R01-Oct24..4.3.1.3.12.21.1.5 Pipe Supports Fabrication & InstallationCCOB452S51 | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | Pre-Fabrication & Installation of Pipe Supports | Piping Erection | C-52-598-03-CI-2000 | C-52-598-03-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.7 Pipe Supports Fabrication & InstallationCCOB352S50 | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | Pre-Fabrication & Installation of Pipe Supports | Piping Erection | C-52-598-04-CI-2000 | C-52-598-04-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | P2543-R01-Oct24..4.3.1.3.11.21.1.10 Platforms & BollardsCCOB352S52 | Concrete Works for Access Platform & Misc. Structural Foundations | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-04-CI-1420 | C-52-598-04-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.10 Platforms & BollardsCCOB352S52 | P2543-R01-Oct24..4.3.1.3.11.21.1.10 Platforms & BollardsCCOB352S52 | Pre-Fabrication & Installation of Platforms & Crossovers | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-04-CI-3000 | C-52-598-04-CI-3010 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.11.21.4.3 Field Joint Welding & NDTCCOB352P071 | P2543-R01-Oct24..4.3.1.3.11.21.1.10 Platforms & BollardsCCOB352S52 | Field Joint Welding (Including Isolation Joint) | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-04-PI-1400 | C-52-598-04-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.4.3 Field Joint Welding & NDTCCOB352P071 | P2543-R01-Oct24..4.3.1.3.11.21.1.10 Platforms & BollardsCCOB352S52 | Field Joint Welding (Including Isolation Joint) | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-04-PI-1400 | C-52-598-04-CI-3010 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.12.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB452S52 | P2543-R01-Oct24..4.3.1.3.12.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB452S52 | Pre-Fabrication & Installation of Platforms & Crossovers | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-03-CI-3000 | C-52-598-03-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.4.3 Field Joint Welding & NDTCCOB452P071 | P2543-R01-Oct24..4.3.1.3.12.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB452S52 | Field Joint Welding (Including Isolation Joint) | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-03-PI-1400 | C-52-598-03-CI-3000 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.14.21.4.3 Field Joint Welding & NDTCCOB652P072 | P2543-R01-Oct24..4.3.1.3.14.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB652S56 | Field Joint Welding (Including Isolation Joint) | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-01-PI-1400 | C-52-598-01-CI-3000 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.14.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB652S56 | P2543-R01-Oct24..4.3.1.3.14.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB652S56 | Pre-Fabrication & Installation of Platforms & Crossovers | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-01-CI-3000 | C-52-598-01-CI-3010 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.13.21.4.3 Field Joint Welding & NDTCCOB552P071 | P2543-R01-Oct24..4.3.1.3.13.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 | Field Joint Welding (Including Isolation Joint) | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-02-PI-1400 | C-52-598-02-CI-3000 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.13.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 | P2543-R01-Oct24..4.3.1.3.13.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 | Pre-Fabrication & Installation of Platforms & Crossovers | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-02-CI-3000 | C-52-598-02-CI-3010 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.11.21.1.5 Trenching for CablesCCOB352C38 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Laying | C-52-598-04-CI-1800 | C-52-598-04-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Electrical & Earthing Cable Laying | Deep Earth Well Drilling | C-52-598-04-EI-2000 | C-52-598-04-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Electrical & Earthing Cable Laying | Instrument Cable Laying | C-52-598-04-EI-2000 | C-52-598-04-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.5 Trenching for CablesCCOB352C38 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-52-598-04-CI-1810 | C-52-598-04-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Instrument Cable Laying | Installation of Cable Trays | C-52-598-04-EI-2010 | C-52-598-04-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Installation of Cable Trays | Instrument Tubing Works | C-52-598-04-EI-2020 | C-52-598-04-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Installation of Solar Panel Structural Supports | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-598-04-EI-1210 | C-52-598-04-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.8 Field InstrumentsCCOB352E102 | P2543-R01-Oct24..4.3.1.3.11.21.6.5 Light Pole, Lighting & FixturesCCOB352E82 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Light Pole, Lighting & Fixtures | C-52-598-04-EI-2210 | C-52-598-04-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | P2543-R01-Oct24..4.3.1.3.11.21.6.5 Light Pole, Lighting & FixturesCCOB352E82 | Installation of Solar S/m (Including Panels, UPS & Battery) | Installation of Light Pole, Lighting & Fixtures | C-52-598-04-EI-1200 | C-52-598-04-EI-1800 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.11.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB352E50 | P2543-R01-Oct24..4.3.1.3.11.21.6.5 Light Pole, Lighting & FixturesCCOB352E82 | Installation of Passive Cooling Shelter | Installation of Lighting & Instrument JB's | C-52-598-04-EI-1000 | C-52-598-04-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.6.8 Field InstrumentsCCOB352E102 | Instrument Cable Laying | Installation of Field Instruments | C-52-598-04-EI-2010 | C-52-598-04-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.6.8 Field InstrumentsCCOB352E102 | Installation of Cable Trays | Installation of Field Instruments | C-52-598-04-EI-2020 | C-52-598-04-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.6.8 Field InstrumentsCCOB352E102 | Instrument Tubing Works | Installation of Field Instruments | C-52-598-04-EI-2030 | C-52-598-04-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.8 Field InstrumentsCCOB352E102 | P2543-R01-Oct24..4.3.1.3.11.21.6.6 F&G DevicesCCOB352E92 | Installation of Field Instruments | Installation of F&G Devices | C-52-598-04-EI-2200 | C-52-598-04-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.4.3 Field Joint Welding & NDTCCOB352P071 | P2543-R01-Oct24..4.3.1.3.11.21.6.8 Field InstrumentsCCOB352E102 | Field Joint Welding (Including Isolation Joint) | Installation of Field Instruments | C-52-598-04-PI-1400 | C-52-598-04-EI-2200 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Electrical & Earthing Cable Laying | CP Cable Laying | C-52-598-04-EI-2000 | C-52-598-04-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.1.9 Backfilling for CablesCCOB352C39 | Electrical & Earthing Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-598-04-EI-2000 | C-52-598-04-CI-2800 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.1.9 Backfilling for CablesCCOB352C39 | CP Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-598-04-CA-1000 | C-52-598-04-CI-2800 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.1.9 Backfilling for CablesCCOB352C39 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-52-598-04-EI-2010 | C-52-598-04-CI-2810 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.11.21.1.9 Backfilling for CablesCCOB352C39 | P2543-R01-Oct24..4.3.1.3.11.21.1.9 Backfilling for CablesCCOB352C39 | Back Filling for Electrical & Earthing Cable | Back Filling for Instrument & Telecom Cable | C-52-598-04-CI-2800 | C-52-598-04-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Concrete Works for Field Instrument, JB Foundations | Concrete Works for Access Platform & Misc. Structural Foundations | C-52-598-05-CI-1410 | C-52-598-05-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.7 Fences & Gates ConstructionCCOB252C36 | P2543-R01-Oct24..4.3.1.3.10.21.1.7 Fences & Gates ConstructionCCOB252C36 | Installation of Concrete Pillers for Boundary Wall | Block Works for Boundary Wall | C-52-598-05-CI-2200 | C-52-598-05-CI-2210 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.10.21.1.7 Fences & Gates ConstructionCCOB252C36 | P2543-R01-Oct24..4.3.1.3.10.21.1.7 Fences & Gates ConstructionCCOB252C36 | Block Works for Boundary Wall | Installation of Fence Post & Mesh Works (Type-4 & 3) | C-52-598-05-CI-2210 | C-52-598-05-CI-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.7 Fences & Gates ConstructionCCOB252C36 | P2543-R01-Oct24..4.3.1.3.10.21.1.7 Fences & Gates ConstructionCCOB252C36 | Installation of Fence Post & Mesh Works (Type-4 & 3) | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | C-52-598-05-CI-2220 | C-52-598-05-CI-2230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.7 Fences & Gates ConstructionCCOB252C36 | P2543-R01-Oct24..4.3.1.3.10.21.1.9 Paving WorksCCOB252C35 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | Paving of Interlock tiles & Kerb Stone Embankment | C-52-598-05-CI-2230 | C-52-598-05-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.9 Paving WorksCCOB252C35 | P2543-R01-Oct24..4.3.1.3.10.21.1.9 Paving WorksCCOB252C35 | Paving of Interlock tiles & Kerb Stone Embankment | Rip-Rap Protection Laying | C-52-598-05-CI-2600 | C-52-598-05-CI-2610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | P2543-R01-Oct24..4.3.1.3.10.21.1.7 Fences & Gates ConstructionCCOB252C36 | Concrete Works for Light Pole, Fence & Gates Foundation | Installation of Concrete Pillers for Boundary Wall | C-52-598-05-CI-1430 | C-52-598-05-CI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB252C33 | P2543-R01-Oct24..4.3.1.3.10.21.1.6 Pipe Supports Fabrication & InstallationCCOB252S50 | Concrete Works for Pipe Support Foundations | Pre-Fabrication & Installation of Pipe Supports | C-52-598-05-CI-1600 | C-52-598-05-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Concrete Works for Field Instrument, JB Foundations | Installation of Solar Panel Structural Supports | C-52-598-05-CI-1410 | C-52-598-05-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | P2543-R01-Oct24..4.3.1.3.10.21.6.8 Field InstrumentsCCOB252E92 | Concrete Works for Field Instrument, JB Foundations | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-05-CI-1410 | C-52-598-05-EI-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.8 Field InstrumentsCCOB252E92 | P2543-R01-Oct24..4.3.1.3.10.21.1.8 Fire Point ShelterCCOB252S52 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Fire Point Shelters | C-52-598-05-EI-2210 | C-52-598-05-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.8 Fire Point ShelterCCOB252S52 | P2543-R01-Oct24..4.3.1.3.10.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB252M50 | Installation of Fire Point Shelters | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | C-52-598-05-CI-2400 | C-52-598-05-ME-1000 | FS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.10.21.1.6 Pipe Supports Fabrication & InstallationCCOB252S50 | P2543-R01-Oct24..4.3.1.3.10.21.4.1 Piping Pre-FabricationCCOB252P050 | Pre-Fabrication & Installation of Pipe Supports | Piping Pre-Fabrication | C-52-598-05-CI-2000 | C-52-598-05-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | P2543-R01-Oct24..4.3.1.3.10.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB252M50 | Concrete Works for Equipment Foundations & Hard Stand Area | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | C-52-598-05-CI-1400 | C-52-598-05-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.6 Pipe Supports Fabrication & InstallationCCOB252S50 | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Pre-Fabrication & Installation of Pipe Supports | Piping Erection | C-52-598-05-CI-2000 | C-52-598-05-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.4.3 Field Joint Welding & NDTCCOB252P070 | P2543-R01-Oct24..4.3.1.3.10.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB252S51 | Field Joint Welding (Including Isolation Joint) | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-05-PI-1400 | C-52-598-05-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB252S51 | P2543-R01-Oct24..4.3.1.3.10.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB252S51 | Pre-Fabrication & Installation of Platforms & Crossovers | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-598-05-CI-3000 | C-52-598-05-CI-3010 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | P2543-R01-Oct24..4.3.1.3.10.21.1.8 Fire Point ShelterCCOB252S52 | Installation of Solar Panel Structural Supports | Installation of Fire Point Shelters | C-52-598-05-EI-1210 | C-52-598-05-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.5 Trenching for CablesCCOB252C38 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Laying | C-52-598-05-CI-1800 | C-52-598-05-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Electrical & Earthing Cable Laying | Deep Earth Well Drilling | C-52-598-05-EI-2000 | C-52-598-05-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.5 Trenching for CablesCCOB252C38 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-52-598-05-CI-1810 | C-52-598-05-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Instrument Cable Laying | Installation of Cable Trays | C-52-598-05-EI-2010 | C-52-598-05-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Installation of Cable Trays | Instrument Tubing Works | C-52-598-05-EI-2020 | C-52-598-05-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Installation of Solar Panel Structural Supports | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-598-05-EI-1210 | C-52-598-05-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | P2543-R01-Oct24..4.3.1.3.10.21.6.5 Light Pole, Lighting & FixturesCCOB252E82 | Installation of Solar S/m (Including Panels, UPS & Battery) | Installation of Light Pole, Lighting & Fixtures | C-52-598-05-EI-1200 | C-52-598-05-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.8 Field InstrumentsCCOB252E92 | P2543-R01-Oct24..4.3.1.3.10.21.6.5 Light Pole, Lighting & FixturesCCOB252E82 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Light Pole, Lighting & Fixtures | C-52-598-05-EI-2210 | C-52-598-05-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | P2543-R01-Oct24..4.3.1.3.10.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB252E50 | Concrete Works for Equipment Foundations & Hard Stand Area | Installation of Passive Cooling Shelter | C-52-598-05-CI-1400 | C-52-598-05-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.8 Field InstrumentsCCOB252E92 | P2543-R01-Oct24..4.3.1.3.10.21.6.8 Field InstrumentsCCOB252E92 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Field Instruments | C-52-598-05-EI-2210 | C-52-598-05-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.4.3 Field Joint Welding & NDTCCOB252P070 | P2543-R01-Oct24..4.3.1.3.10.21.6.8 Field InstrumentsCCOB252E92 | Field Joint Welding (Including Isolation Joint) | Installation of Field Instruments | C-52-598-05-PI-1400 | C-52-598-05-EI-2200 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.10.21.6.8 Field InstrumentsCCOB252E92 | P2543-R01-Oct24..4.3.1.3.10.21.6.6 F&G DevicesCCOB252E102 | Installation of Field Instruments | Installation of F&G Devices | C-52-598-05-EI-2200 | C-52-598-05-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.5 Light Pole, Lighting & FixturesCCOB252E82 | P2543-R01-Oct24..4.3.1.3.10.21.6.5 Light Pole, Lighting & FixturesCCOB252E82 | Installation of Light Pole, Lighting & Fixtures | Installation of Lighting & Instrument JB's | C-52-598-05-EI-1800 | C-52-598-05-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | P2543-R01-Oct24..4.3.1.3.10.21.7.1 CP Anode Bed Installation (subcontract)CCOB252E30 | Electrical & Earthing Cable Laying | CP Cable Laying | C-52-598-05-EI-2000 | C-52-598-05-CA-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | P2543-R01-Oct24..4.3.1.3.10.21.1.10 Backfilling for CablesCCOB252C40 | Electrical & Earthing Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-598-05-EI-2000 | C-52-598-05-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.7.1 CP Anode Bed Installation (subcontract)CCOB252E30 | P2543-R01-Oct24..4.3.1.3.10.21.1.10 Backfilling for CablesCCOB252C40 | CP Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-598-05-CA-1000 | C-52-598-05-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | P2543-R01-Oct24..4.3.1.3.10.21.1.10 Backfilling for CablesCCOB252C40 | Installation of Cable Trays | Back Filling for Instrument & Telecom Cable | C-52-598-05-EI-2020 | C-52-598-05-CI-2810 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.10.21.1.10 Backfilling for CablesCCOB252C40 | P2543-R01-Oct24..4.3.1.3.10.21.1.10 Backfilling for CablesCCOB252C40 | Back Filling for Electrical & Earthing Cable | Back Filling for Instrument & Telecom Cable | C-52-598-05-CI-2800 | C-52-598-05-CI-2810 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | P2543-R01-Oct24..4.3.1.3.9.21.1.8 Fences & Gates ConstructionCCOB152C36 | Concrete Works for Light Pole, Fence & Gates Foundation | Installation of Concrete Pillers for Boundary Wall | C-52-598-06-CI-1430 | C-52-598-06-CI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.8 Fences & Gates ConstructionCCOB152C36 | P2543-R01-Oct24..4.3.1.3.9.21.1.8 Fences & Gates ConstructionCCOB152C36 | Installation of Concrete Pillers for Boundary Wall | Block Works for Boundary Wall | C-52-598-06-CI-2200 | C-52-598-06-CI-2210 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.9.21.1.8 Fences & Gates ConstructionCCOB152C36 | P2543-R01-Oct24..4.3.1.3.9.21.1.8 Fences & Gates ConstructionCCOB152C36 | Block Works for Boundary Wall | Installation of Fence Post & Mesh Works (Type-4 & 3) | C-52-598-06-CI-2210 | C-52-598-06-CI-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.8 Fences & Gates ConstructionCCOB152C36 | P2543-R01-Oct24..4.3.1.3.9.21.1.8 Fences & Gates ConstructionCCOB152C36 | Installation of Fence Post & Mesh Works (Type-4 & 3) | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | C-52-598-06-CI-2220 | C-52-598-06-CI-2230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.8 Fences & Gates ConstructionCCOB152C36 | P2543-R01-Oct24..4.3.1.3.9.21.1.9 Paving WorksCCOB152C40 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | Paving of Interlock tiles & Kerb Stone Embankment | C-52-598-06-CI-2230 | C-52-598-06-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.9 Paving WorksCCOB152C40 | P2543-R01-Oct24..4.3.1.3.9.21.1.9 Paving WorksCCOB152C40 | Paving of Interlock tiles & Kerb Stone Embankment | Rip-Rap Protection Laying | C-52-598-06-CI-2600 | C-52-598-06-CI-2610 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.9.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB152C34 | P2543-R01-Oct24..4.3.1.3.9.21.1.6 Pipe Supports Fabrication & InstallationCCOB152S52 | Concrete Works for Pipe Support Foundations | Pre-Fabrication & Installation of Pipe Supports | C-52-598-06-CI-1600 | C-52-598-06-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | P2543-R01-Oct24..4.3.1.3.9.21.6.6 Field InstrumentsCCOB152E96 | Concrete Works for Field Instrument, JB Foundations | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-06-CI-1410 | C-52-598-06-EI-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | P2543-R01-Oct24..4.3.1.3.9.21.1.7 Fire Point SheltersCCOB152S50 | Installation of Solar Panel Structural Supports | Installation of Fire Point Shelters | C-52-598-06-EI-1210 | C-52-598-06-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.5 Trenching for CablesCCOB152C38 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Laying | C-52-598-06-CI-1800 | C-52-598-06-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Electrical & Earthing Cable Laying | Deep Earth Well Drilling | C-52-598-06-EI-2000 | C-52-598-06-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Electrical & Earthing Cable Laying | Instrument Cable Laying | C-52-598-06-EI-2000 | C-52-598-06-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.5 Trenching for CablesCCOB152C38 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-52-598-06-CI-1810 | C-52-598-06-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Instrument Cable Laying | Installation of Cable Trays | C-52-598-06-EI-2010 | C-52-598-06-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Installation of Cable Trays | Instrument Tubing Works | C-52-598-06-EI-2020 | C-52-598-06-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Installation of Solar Panel Structural Supports | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-598-06-EI-1210 | C-52-598-06-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | P2543-R01-Oct24..4.3.1.3.9.21.6.5 Light Pole, Lighting & FixturesCCOB152E86 | Installation of Solar S/m (Including Panels, UPS & Battery) | Installation of Light Pole, Lighting & Fixtures | C-52-598-06-EI-1200 | C-52-598-06-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.6 Field InstrumentsCCOB152E96 | P2543-R01-Oct24..4.3.1.3.9.21.6.5 Light Pole, Lighting & FixturesCCOB152E86 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Light Pole, Lighting & Fixtures | C-52-598-06-EI-2210 | C-52-598-06-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | P2543-R01-Oct24..4.3.1.3.9.21.6.5 Light Pole, Lighting & FixturesCCOB152E86 | Concrete Works for Light Pole, Fence & Gates Foundation | Installation of Light Pole, Lighting & Fixtures | C-52-598-06-CI-1430 | C-52-598-06-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | P2543-R01-Oct24..4.3.1.3.9.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB152E50 | Concrete Works for Equipment Foundations & Hard Stand Area | Installation of Passive Cooling Shelter | C-52-598-06-CI-1400 | C-52-598-06-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.5 Light Pole, Lighting & FixturesCCOB152E86 | P2543-R01-Oct24..4.3.1.3.9.21.6.5 Light Pole, Lighting & FixturesCCOB152E86 | Installation of Light Pole, Lighting & Fixtures | Installation of Lighting & Instrument JB's | C-52-598-06-EI-1800 | C-52-598-06-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.6 Field InstrumentsCCOB152E96 | P2543-R01-Oct24..4.3.1.3.9.21.6.6 Field InstrumentsCCOB152E96 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Field Instruments | C-52-598-06-EI-2210 | C-52-598-06-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.4.3 Field Joint Welding & NDTCCOB152P070 | P2543-R01-Oct24..4.3.1.3.9.21.6.6 Field InstrumentsCCOB152E96 | Field Joint Welding (Including Isolation Joint) | Installation of Field Instruments | C-52-598-06-PI-1400 | C-52-598-06-EI-2200 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.9.21.6.6 Field InstrumentsCCOB152E96 | P2543-R01-Oct24..4.3.1.3.9.21.6.8 F&G DevicesCCOB152E106 | Installation of Field Instruments | Installation of F&G Devices | C-52-598-06-EI-2200 | C-52-598-06-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.6.6 Field InstrumentsCCOB152E96 | Instrument Cable Laying | Installation of Field Instruments | C-52-598-06-EI-2010 | C-52-598-06-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.6.6 Field InstrumentsCCOB152E96 | Installation of Cable Trays | Installation of Field Instruments | C-52-598-06-EI-2020 | C-52-598-06-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.7.1 CP Anode Bed Installation (subcontract)CCOB152E56 | Instrument Cable Laying | CP Cable Laying | C-52-598-06-EI-2010 | C-52-598-06-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.1.11 Backfilling for CablesCCOB152C37 | Electrical & Earthing Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-598-06-EI-2000 | C-52-598-06-CI-2800 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.9.21.7.1 CP Anode Bed Installation (subcontract)CCOB152E56 | P2543-R01-Oct24..4.3.1.3.9.21.1.11 Backfilling for CablesCCOB152C37 | CP Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-598-06-CA-1000 | C-52-598-06-CI-2800 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.1.11 Backfilling for CablesCCOB152C37 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-52-598-06-EI-2010 | C-52-598-06-CI-2810 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.9.21.1.11 Backfilling for CablesCCOB152C37 | P2543-R01-Oct24..4.3.1.3.9.21.1.11 Backfilling for CablesCCOB152C37 | Back Filling for Electrical & Earthing Cable | Back Filling for Instrument & Telecom Cable | C-52-598-06-CI-2800 | C-52-598-06-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 Compaction & TestingCCOSWCS301 | Earth Works for Thrust Anchor Block | Compaction & Testing for Thrust Anchor Block | C-52-PR-839-CI-1050 | C-52-PR-839-CI-1240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 Compaction & TestingCCOSWCS301 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.9 Thrust Anchor BlocklCCOSWCS317 | Compaction & Testing for Thrust Anchor Block | Concrete Works for Thrust Anchor Block | C-52-PR-839-CI-1240 | C-52-PR-839-CI-1510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.1 Sales Gas FilterCCOSWME506 | P2543-R01-Oct24..4.3.1.3.4.1.22.3.1 Sales Gas FilterCCOSWME506 | Installation of Sales Gas Filter (839-F-104A) | Installation of Sales Gas Filter (839-F-104B) | C-52-PR-839-ME-1800 | C-52-PR-839-ME-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | Site Survey, Preparation & Grading Works | Earth Works for Equipment Foundations | C-52-PR-839-CI-1000 | C-52-PR-839-CI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | Earth Works for Equipment Foundations | Earth Works for Pipe Support Foundations | C-52-PR-839-CI-1010 | C-52-PR-839-CI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | Earth Works for Pipe Support Foundations | Earth Works for Field Instrument, JBs & Light Pole Foundations | C-52-PR-839-CI-1020 | C-52-PR-839-CI-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | Earth Works for Field Instrument, JBs & Light Pole Foundations | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-PR-839-CI-1030 | C-52-PR-839-CI-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | Earth Works for Access Platforms & Misc. Structural Foundations | Earth Works for Impact Wall | C-52-PR-839-CI-1040 | C-52-PR-839-CI-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | Earth Works for Thrust Anchor Block | Earth Works for Equipment Foundations | C-52-PR-839-CI-1050 | C-52-PR-839-CI-1010 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 Compaction & TestingCCOSWCS301 | Earth Works for Equipment Foundations | Compaction & Testing for Equipment Foundations | C-52-PR-839-CI-1010 | C-52-PR-839-CI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 Compaction & TestingCCOSWCS301 | Earth Works for Pipe Support Foundations | Compaction & Testing for Pipe Support Foundations | C-52-PR-839-CI-1020 | C-52-PR-839-CI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 Compaction & TestingCCOSWCS301 | Earth Works for Field Instrument, JBs & Light Pole Foundations | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | C-52-PR-839-CI-1030 | C-52-PR-839-CI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 Compaction & TestingCCOSWCS301 | Earth Works for Access Platforms & Misc. Structural Foundations | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-52-PR-839-CI-1040 | C-52-PR-839-CI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 Compaction & TestingCCOSWCS301 | Earth Works for Impact Wall | Compaction & Testing for Impact Wall | C-52-PR-839-CI-1060 | C-52-PR-839-CI-1250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 Compaction & TestingCCOSWCS301 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Compaction & Testing for Equipment Foundations | Concrete Works for Equipment Foundations | C-52-PR-839-CI-1200 | C-52-PR-839-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 Compaction & TestingCCOSWCS301 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.5 Concrete Works (Foundations for Pipe Supports)CCOSWCS302.2 | Compaction & Testing for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-52-PR-839-CI-1210 | C-52-PR-839-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 Compaction & TestingCCOSWCS301 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-52-PR-839-CI-1220 | C-52-PR-839-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 Compaction & TestingCCOSWCS301 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | Concrete Works for Access Platforms & Misc. Structural Foundations | C-52-PR-839-CI-1230 | C-52-PR-839-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.2 Compaction & TestingCCOSWCS301 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.4 Concrete Works (Impact wall)CCOSWCS302.3 | Compaction & Testing for Impact Wall | Concrete Works for Impact Wall | C-52-PR-839-CI-1250 | C-52-PR-839-CI-1500 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.5 Concrete Works (Foundations for Pipe Supports)CCOSWCS302.2 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Concrete Works for Pipe Support Foundations | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-52-PR-839-CI-1600 | C-52-PR-839-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Concrete Works for Access Platforms & Misc. Structural Foundations | C-52-PR-839-CI-1410 | C-52-PR-839-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.9 Thrust Anchor BlocklCCOSWCS317 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.4 Concrete Works (Impact wall)CCOSWCS302.3 | Concrete Works for Thrust Anchor Block | Concrete Works for Impact Wall | C-52-PR-839-CI-1510 | C-52-PR-839-CI-1500 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.6 Trenching for CablesCCOSWCS311 | Earth Works for Pipe Support Foundations | Electrical & Earthing Cable Trenching | C-52-PR-839-CI-1020 | C-52-PR-839-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.6 Trenching for CablesCCOSWCS311 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.6 Trenching for CablesCCOSWCS311 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-52-PR-839-CI-1800 | C-52-PR-839-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | P2543-R01-Oct24..4.3.1.3.4.1.22.3.2 Installation of Pig Receiver (839-V-101)CCOSWME508 | Concrete Works for Equipment Foundations | Installation of Pig Receiver (839-V-101) 52" | C-52-PR-839-CI-1400 | C-52-PR-839-ME-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.2 Installation of Pig Receiver (839-V-101)CCOSWME508 | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | Installation of Pig Receiver (839-V-101) 52" | Piping Erection | C-52-PR-839-ME-1100 | C-52-PR-839-PI-1200 | FS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.4.1.22.5.1 Pig Receiver 839-V-101 52'' Pipeline/ Piping Hook-upCCOSWPI514 | P2543-R01-Oct24..4.3.1.3.4.1.22.5.1 Pig Receiver 839-V-101 52'' Pipeline/ Piping Hook-upCCOSWPI514 | Installation of Isolation Joint | Field Joint Welding (Piping/Pipeline Section including IJ) | C-52-PR-839-PL-1000 | C-52-PR-839-PL-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.5.1 Pig Receiver 839-V-101 52'' Pipeline/ Piping Hook-upCCOSWPI514 | P2543-R01-Oct24..4.3.1.3.4.1.22.5.1 Pig Receiver 839-V-101 52'' Pipeline/ Piping Hook-upCCOSWPI514 | Field Joint Welding (Piping/Pipeline Section including IJ) | NDT for Weld Joint | C-52-PR-839-PL-1010 | C-52-PR-839-PL-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.5.1 Pig Receiver 839-V-101 52'' Pipeline/ Piping Hook-upCCOSWPI514 | P2543-R01-Oct24..4.3.1.3.4.1.22.5.1 Pig Receiver 839-V-101 52'' Pipeline/ Piping Hook-upCCOSWPI514 | NDT for Weld Joint | Ext. Coating for Weld Joint | C-52-PR-839-PL-1020 | C-52-PR-839-PL-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.6 Trenching for CablesCCOSWCS311 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Laying | C-52-PR-839-CI-1800 | C-52-PR-839-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Electrical & Earthing Cable Laying | Deep Earth Well Drilling | C-52-PR-839-EI-2000 | C-52-PR-839-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Electrical & Earthing Cable Laying | Instrument Cable Laying | C-52-PR-839-EI-2000 | C-52-PR-839-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Electrical & Earthing Cable Laying | Installation of Cable Trays | C-52-PR-839-EI-2000 | C-52-PR-839-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Installation of Cable Trays | Instrument Tubing Works | C-52-PR-839-EI-2020 | C-52-PR-839-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Instrument Cable Laying | Instrument Tubing Works | C-52-PR-839-EI-2010 | C-52-PR-839-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.4 Field InstrumentsCCOSW52E10.32 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Light Pole, Lighting & Fixtures | C-52-PR-839-EI-2210 | C-52-PR-839-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Electrical & Earthing Cable Laying | Installation of Light Pole, Lighting & Fixtures | C-52-PR-839-EI-2000 | C-52-PR-839-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Installation of Light Pole, Lighting & Fixtures | Installation of JB's | C-52-PR-839-EI-1800 | C-52-PR-839-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.4 Field InstrumentsCCOSW52E10.32 | Final Bolt Torquing/ Re-Instatement | Installation of Field Instruments (Including Pig Signaller) | C-52-PR-839-PI-2000 | C-52-PR-839-EI-2200 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.4.1.22.6.4 Field InstrumentsCCOSW52E10.32 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.5 F&G DevicesCCOSW52E10.42 | Installation of Field Instruments (Including Pig Signaller) | Installation of F&G Device | C-52-PR-839-EI-2200 | C-52-PR-839-EI-2410 | FS | Not Started | Not Started | 30
P2543-R01-Oct24..4.3.1.3.4.1.22.6.5 F&G DevicesCCOSW52E10.42 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Installation of F&G Device | Loop Checking for Instruments | C-52-PR-839-EI-2410 | C-52-PR-839-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Electrical & Earthing Cable Laying | Glanding & Termination | C-52-PR-839-EI-2000 | C-52-PR-839-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Deep Earth Well Drilling | Glanding & Termination | C-52-PR-839-EI-1400 | C-52-PR-839-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Installation of Light Pole, Lighting & Fixtures | Glanding & Termination | C-52-PR-839-EI-1800 | C-52-PR-839-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Installation of JB's | Glanding & Termination | C-52-PR-839-EI-1810 | C-52-PR-839-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Loop Checking for Instruments | Glanding & Termination | C-52-PR-839-EI-2040 | C-52-PR-839-EI-2050 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | CP Cable Laying | Installation of CP Test Post | C-52-PR-839-CA-1000 | C-52-PR-839-CA-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Installation of CP Test Post | Installation of CP JB's | C-52-PR-839-CA-1010 | C-52-PR-839-CA-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Installation of CP JB's | Glanding & Termination for CP S/m | C-52-PR-839-CA-1020 | C-52-PR-839-CA-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Electrical & Earthing Cable Laying | CP Cable Laying | C-52-PR-839-EI-2000 | C-52-PR-839-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.2 Installation of Pig Receiver (839-V-101)CCOSWME508 | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Installation of Pig Receiver (839-V-101) 52" | Glanding & Termination for CP S/m | C-52-PR-839-ME-1100 | C-52-PR-839-CA-1030 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Instrument Cable Laying | FOC Laying | C-52-PR-839-EI-2010 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | FOC Laying | Installation of CCTV System | C-52-PR-839-TE-1410 | C-52-PR-839-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Installation of CCTV System | FO Cable OTDR Testing & Splicing | C-52-PR-839-TE-1600 | C-52-PR-839-TE-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.11 Backfilling for CablesCCOSWCS320 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.11 Backfilling for CablesCCOSWCS320 | Back Filling for Electrical & Earthing Cable | Back Filling for Instrument & Telecom Cable | C-52-PR-839-CI-2800 | C-52-PR-839-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.11 Backfilling for CablesCCOSWCS320 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.13 Paving interlock & barrier installationCCOSWCS315.2 | Back Filling for Instrument & Telecom Cable | Paving of Interlock tiles & Kerb Stone Embankment | C-52-PR-839-CI-2810 | C-52-PR-839-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.11 Backfilling for CablesCCOSWCS320 | Electrical & Earthing Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-PR-839-EI-2000 | C-52-PR-839-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.11 Backfilling for CablesCCOSWCS320 | CP Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-PR-839-CA-1000 | C-52-PR-839-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.11 Backfilling for CablesCCOSWCS320 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-52-PR-839-EI-2010 | C-52-PR-839-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.11 Backfilling for CablesCCOSWCS320 | FOC Laying | Back Filling for Instrument & Telecom Cable | C-52-PR-839-TE-1410 | C-52-PR-839-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.4 Concrete Works (Impact wall)CCOSWCS302.3 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.13 Paving interlock & barrier installationCCOSWCS315.2 | Concrete Works for Impact Wall | Paving of Interlock tiles & Kerb Stone Embankment | C-52-PR-839-CI-1500 | C-52-PR-839-CI-2600 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 Excavation (incl Bedding)CCOSWCS303 | P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 Excavation (incl Bedding)CCOSWCS303 | Site Survey, Preparation & Grading Works | Earth Works for Ground Level | C-52-EB1-CI-1000 | C-52-EB1-CI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 Excavation (incl Bedding)CCOSWCS303 | P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 Excavation (incl Bedding)CCOSWCS303 | Earth Works for Ground Level | Compaction & Testing for Ground Level | C-52-EB1-CI-1010 | C-52-EB1-CI-1020 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 Excavation (incl Bedding)CCOSWCS303 | P2543-R01-Oct24..4.3.1.3.4.2.22.1.2 Foundation Works (for Substructure)CCOSWCS304 | Compaction & Testing for Ground Level | Building Foundation Works (for Substructure) | C-52-EB1-CI-1020 | C-52-EB1-CI-1200 | SS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.4.2.22.1.2 Foundation Works (for Substructure)CCOSWCS304 | P2543-R01-Oct24..4.3.1.3.4.2.22.1.3 Concrete Superstructure WorksCCOSWCS305 | Building Foundation Works (for Substructure) | Concrete Superstructure Works | C-52-EB1-CI-1200 | C-52-EB1-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.3 Concrete Superstructure WorksCCOSWCS305 | P2543-R01-Oct24..4.3.1.3.4.2.22.1.4 Masonry WorksCCOSWCS309 | Concrete Superstructure Works | Masonry Works - Internal | C-52-EB1-CI-1400 | C-52-EB1-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.4 Masonry WorksCCOSWCS309 | P2543-R01-Oct24..4.3.1.3.4.2.22.1.4 Masonry WorksCCOSWCS309 | Masonry Works - Internal | Masonry Works - External | C-52-EB1-CI-1600 | C-52-EB1-CI-1610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.4 Masonry WorksCCOSWCS309 | P2543-R01-Oct24..4.3.1.3.4.2.22.1.5 Finishing WorksCCOSWCS313 | Masonry Works - Internal | Internal Finishing Works | C-52-EB1-CI-1600 | C-52-EB1-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.4 Masonry WorksCCOSWCS309 | P2543-R01-Oct24..4.3.1.3.4.2.22.1.5 Finishing WorksCCOSWCS313 | Masonry Works - External | External Finishing Works | C-52-EB1-CI-1610 | C-52-EB1-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.5 Finishing WorksCCOSWCS313 | P2543-R01-Oct24..4.3.1.3.4.2.22.1.6 Metal WorksCCOSWCS318 | Internal Finishing Works | Steel Structural Works | C-52-EB1-CI-1810 | C-52-EB1-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.5 Finishing WorksCCOSWCS313 | P2543-R01-Oct24..4.3.1.3.4.2.22.1.6 Metal WorksCCOSWCS318 | External Finishing Works | Steel Structural Works | C-52-EB1-CI-1800 | C-52-EB1-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.6 Metal WorksCCOSWCS318 | P2543-R01-Oct24..4.3.1.3.4.2.22.1.7 Paving WorksCCOSWCS319 | Steel Structural Works | Paving Works | C-52-EB1-CI-2000 | C-52-EB1-CI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.4 Masonry WorksCCOSWCS309 | P2543-R01-Oct24..4.3.1.3.4.2.22.2.1 HVAC System & Plumbing WorksCCOSWME511 | Masonry Works - Internal | Plumbing Works | C-52-EB1-CI-1600 | C-52-EB1-ME-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.2.1 HVAC System & Plumbing WorksCCOSWME511 | P2543-R01-Oct24..4.3.1.3.4.2.22.2.1 HVAC System & Plumbing WorksCCOSWME511 | Plumbing Works | HVAC Works | C-52-EB1-ME-1000 | C-52-EB1-ME-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.2.1 HVAC System & Plumbing WorksCCOSWME511 | P2543-R01-Oct24..4.3.1.3.4.2.22.1.5 Finishing WorksCCOSWCS313 | HVAC Works | Internal Finishing Works | C-52-EB1-ME-1010 | C-52-EB1-CI-1810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | P2543-R01-Oct24..4.3.1.3.4.2.22.3.5 Lighting SystemCCOSW52E32 | Installation of Power Distribution System | Lighting & Fixtures | C-52-EB1-EI-1000 | C-52-EB1-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.5 Lighting SystemCCOSW52E32 | P2543-R01-Oct24..4.3.1.3.4.2.22.3.2 HSSD SystemCCOSW52E62 | Lighting & Fixtures | Installation of HSSD System | C-52-EB1-EI-1400 | C-52-EB1-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.2 HSSD SystemCCOSW52E62 | P2543-R01-Oct24..4.3.1.3.4.2.22.3.3 RTU SystemCCOSW52E82 | Installation of HSSD System | Installation of RTU System | C-52-EB1-EI-2000 | C-52-EB1-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.3 RTU SystemCCOSW52E82 | P2543-R01-Oct24..4.3.1.3.4.2.22.3.4 Custody Metering PanelCCOSW52E102 | Installation of RTU System | Custody Metering Panel Installation | C-52-EB1-EI-2200 | C-52-EB1-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.4 Custody Metering PanelCCOSW52E102 | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Custody Metering Panel Installation | E&I Cable Laying | C-52-EB1-EI-1200 | C-52-EB1-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | P2543-R01-Oct24..4.3.1.3.4.2.22.3.7 Earthing & Lightning Protection systemCCOSW52E42 | E&I Cable Laying | Earthing & Lightning Protection system | C-52-EB1-EI-1210 | C-52-EB1-EI-1600 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.7 Earthing & Lightning Protection systemCCOSW52E42 | P2543-R01-Oct24..4.3.1.3.4.2.22.3.8 UPS (10KVA)CCOSW52E72 | Earthing & Lightning Protection system | UPS (10KVA) Installation | C-52-EB1-EI-1600 | C-52-EB1-EI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.8 UPS (10KVA)CCOSW52E72 | P2543-R01-Oct24..4.3.1.3.4.2.22.3.9 F&G SystemCCOSW52E52 | UPS (10KVA) Installation | Installation F&G System | C-52-EB1-EI-2400 | C-52-EB1-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.9 F&G SystemCCOSW52E52 | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Installation F&G System | MCT Installation | C-52-EB1-EI-1800 | C-52-EB1-EI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | MCT Installation | Glanding & Termination | C-52-EB1-EI-1220 | C-52-EB1-EI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.5 Finishing WorksCCOSWCS313 | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Internal Finishing Works | Installation of Power Distribution System | C-52-EB1-CI-1810 | C-52-EB1-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.2 HSSD SystemCCOSW52E62 | P2543-R01-Oct24..4.3.1.3.4.2.22.4.1 SDH CabinetCCOSWIC309 | Installation of HSSD System | SDH Cabinet Installation | C-52-EB1-EI-2000 | C-52-EB1-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.4.1 SDH CabinetCCOSWIC309 | P2543-R01-Oct24..4.3.1.3.4.2.22.4.3 Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOSWIC332 | SDH Cabinet Installation | CCTV Installation | C-52-EB1-TE-1000 | C-52-EB1-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.4.3 Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOSWIC332 | P2543-R01-Oct24..4.3.1.3.4.2.22.4.2 Telecom System (Including subcontract for FOC Splicing / Termination / Testing)CCOSWIC322 | CCTV Installation | Telecom System (Including subcontract for FOC Splicing / Termination / Testing) | C-52-EB1-TE-1600 | C-52-EB1-TE-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.4.2 Telecom System (Including subcontract for FOC Splicing / Termination / Testing)CCOSWIC322 | P2543-R01-Oct24..4.3.1.3.4.2.22.4.3 Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOSWIC332 | Telecom System (Including subcontract for FOC Splicing / Termination / Testing) | Security System (Including subcontract for FOC Splicing / Termination / Testing ) | C-52-EB1-TE-1400 | C-52-EB1-TE-1610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 Excavation (incl Bedding)CCOSWCS303 | P2543-R01-Oct24..4.3.1.3.4.4.22.1.1 Concrete Works (Foundations for Equipment & Pipe Supports)CCOSWCS321 | Site Survey, Preparation & Grading Works | Concrete Works (Foundations for Equipment & Pipe Supports) | C-52-EB1-CI-1000 | C-52-OHPL-CI-1000 | FS | Not Started | Not Started | 24
P2543-R01-Oct24..4.3.1.3.4.4.22.1.1 Concrete Works (Foundations for Equipment & Pipe Supports)CCOSWCS321 | P2543-R01-Oct24..4.3.1.3.4.4.22.1.2 Trenching for CablesCCOSWCS322 | Concrete Works (Foundations for Equipment & Pipe Supports) | Trenching for Cables | C-52-OHPL-CI-1000 | C-52-OHPL-CI-1200 | FS | Not Started | Not Started | 10
P2543-R01-Oct24..4.3.1.3.4.4.22.1.2 Trenching for CablesCCOSWCS322 | P2543-R01-Oct24..4.3.1.3.4.4.22.2.1 OHPL Installation Works-Tower/Post installation (Subcontract)CCOSW52E20.1 | Trenching for Cables | OHPL Installation Works-Tower/Post installation (Subcontract) | C-52-OHPL-CI-1200 | C-52-OHPL-EL-1000 | FS | Not Started | Not Started | 30
P2543-R01-Oct24..4.3.1.3.4.4.22.2.3 Transformer / Directly Buried MV Cables (including testing)CCOSW52E22 | P2543-R01-Oct24..4.3.1.3.4.4.22.3.1 Shutdown Connection of OHL & Cable TestingCCOSW52S10 | Transformer / Directly Buried MV Cables (including testing) | Shutdown Connection of OHL & Cable Testing | C-52-OHPL-EL-1400 | C-52-OHPL-EL-2000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | P2543-R01-Oct24..4.3.1.3.4.4.22.2.3 Transformer / Directly Buried MV Cables (including testing)CCOSW52E22 | E&I Cable Laying | Transformer / Directly Buried MV Cables (including testing) | C-52-EB1-EI-1210 | C-52-OHPL-EL-1400 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.4.4.22.3.1 Shutdown Connection of OHL & Cable TestingCCOSW52S10 | P2543-R01-Oct24..4.3.1.3.4.4.22.1.3 Backfilling for CablesCCOSWCS323 | Shutdown Connection of OHL & Cable Testing | Backfilling for Cables | C-52-OHPL-EL-2000 | C-52-OHPL-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 Excavation (incl Bedding)CCOSWCS303 | P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | Site Survey, Preparation & Grading Works | Site Survey, Preparation & Grading Works | C-52-EB1-CI-1000 | C-36-KM-HT-CI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | Site Survey, Preparation & Grading Works | Earth Works for Pipe Support Foundations | C-36-KM-HT-CI-1000 | C-36-KM-HT-CI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | Earth Works for Pipe Support Foundations | Earth Works for Hot Tap Tie in Pit | C-36-KM-HT-CI-1020 | C-36-KM-HT-CI-1080 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | Earth Works for Pipe Support Foundations | Earth Works for Field Instrument, JBs | C-36-KM-HT-CI-1020 | C-36-KM-HT-CI-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | Earth Works for Field Instrument, JBs | Earth Works for Access Platforms & Misc. Structural Foundations | C-36-KM-HT-CI-1030 | C-36-KM-HT-CI-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | P2543-R01-Oct24..4.3.1.4.12.1.2 Compaction & TestingCCOJ42CS22 | Earth Works for Pipe Support Foundations | Compaction & Testing for Pipe Support Foundations | C-36-KM-HT-CI-1020 | C-36-KM-HT-CI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | P2543-R01-Oct24..4.3.1.4.12.1.2 Compaction & TestingCCOJ42CS22 | Earth Works for Field Instrument, JBs | Compaction & Testing for Field Instrument, JBs | C-36-KM-HT-CI-1030 | C-36-KM-HT-CI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | P2543-R01-Oct24..4.3.1.4.12.1.2 Compaction & TestingCCOJ42CS22 | Earth Works for Access Platforms & Misc. Structural Foundations | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-36-KM-HT-CI-1040 | C-36-KM-HT-CI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | P2543-R01-Oct24..4.3.1.4.12.1.2 Compaction & TestingCCOJ42CS22 | Earth Works for Hot Tap Tie in Pit | Compaction & Testing for Hot Tap Tie in Pit | C-36-KM-HT-CI-1080 | C-36-KM-HT-CI-1280 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.2 Compaction & TestingCCOJ42CS22 | P2543-R01-Oct24..4.3.1.4.12.1.5 Concrete Works (Foundations for Pipe Supports)CCOJ42CS28 | Compaction & Testing for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-36-KM-HT-CI-1210 | C-36-KM-HT-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.2 Compaction & TestingCCOJ42CS22 | P2543-R01-Oct24..4.3.1.4.12.1.4 Concrete Works (Foundations for Equipment)CCOJ42CS44 | Compaction & Testing for Field Instrument, JBs | Concrete Works for Field Instrument, JBs | C-36-KM-HT-CI-1220 | C-36-KM-HT-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.2 Compaction & TestingCCOJ42CS22 | P2543-R01-Oct24..4.3.1.4.12.1.4 Concrete Works (Foundations for Equipment)CCOJ42CS44 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | Concrete Works for Access Platforms & Misc. Structural Foundations | C-36-KM-HT-CI-1230 | C-36-KM-HT-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.2 Compaction & TestingCCOJ42CS22 | P2543-R01-Oct24..4.3.1.4.12.1.3 Concrete Pit (For Hot Tapping)CCOJ42CS24 | Compaction & Testing for Hot Tap Tie in Pit | Concrete Works for Hot Tap Tie in Pit | C-36-KM-HT-CI-1280 | CCV-52-KM-1120 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.5 Concrete Works (Foundations for Pipe Supports)CCOJ42CS28 | P2543-R01-Oct24..4.3.1.4.12.1.3 Concrete Pit (For Hot Tapping)CCOJ42CS24 | Concrete Works for Pipe Support Foundations | Concrete Works for Hot Tap Tie in Pit | C-36-KM-HT-CI-1600 | CCV-52-KM-1120 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.5 Concrete Works (Foundations for Pipe Supports)CCOJ42CS28 | P2543-R01-Oct24..4.3.1.4.12.1.4 Concrete Works (Foundations for Equipment)CCOJ42CS44 | Concrete Works for Pipe Support Foundations | Concrete Works for Field Instrument, JBs | C-36-KM-HT-CI-1600 | C-36-KM-HT-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.4 Concrete Works (Foundations for Equipment)CCOJ42CS44 | P2543-R01-Oct24..4.3.1.4.12.1.4 Concrete Works (Foundations for Equipment)CCOJ42CS44 | Concrete Works for Field Instrument, JBs | Concrete Works for Access Platforms & Misc. Structural Foundations | C-36-KM-HT-CI-1410 | C-36-KM-HT-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | P2543-R01-Oct24..4.3.1.4.12.1.6 Trenching for CablesCCOJ42CS30 | Earth Works for Hot Tap Tie in Pit | Electrical & Earthing Cable Trenching | C-36-KM-HT-CI-1080 | C-36-KM-HT-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.6 Trenching for CablesCCOJ42CS30 | P2543-R01-Oct24..4.3.1.4.12.1.6 Trenching for CablesCCOJ42CS30 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-36-KM-HT-CI-1800 | C-36-KM-HT-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.10 Backfilling for CablesCCOJ42CS34 | P2543-R01-Oct24..4.3.1.4.12.1.10 Backfilling for CablesCCOJ42CS34 | Back Filling for Electrical & Earthing Cable | Back Filling for Instrument & Telecom Cable | C-36-KM-HT-CI-2800 | C-36-KM-HT-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.10 Backfilling for CablesCCOJ42CS34 | P2543-R01-Oct24..4.3.1.4.12.1.11 Paving WorksCCOJ42CS32 | Back Filling for Instrument & Telecom Cable | Paving of Interlock tiles & Kerb Stone Embankment | C-36-KM-HT-CI-2810 | C-36-KM-HT-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | P2543-R01-Oct24..4.3.1.4.12.2.1 Piping Pre-FabricationCCOJ42PI070 | Piping Pre-Fabrication | Piping Pre-Fabrication | C-52-PR-839-PI-1000 | C-36-KM-HT-PI-1000 | FS | Not Started | Not Started | 30
P2543-R01-Oct24..4.3.1.4.12.1.6 Trenching for CablesCCOJ42CS30 | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Laying | C-36-KM-HT-CI-1800 | C-36-KM-HT-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Electrical & Earthing Cable Laying | Instrument Cable Laying | C-36-KM-HT-EI-2000 | C-36-KM-HT-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Instrument Cable Laying | Instrument Tubing Works | C-36-KM-HT-EI-2010 | C-36-KM-HT-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Instrument Tubing Works | Installation of Field Instruments & JB's | C-36-KM-HT-EI-2030 | C-36-KM-HT-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Installation of Field Instruments & JB's | Loop Checking for Instruments | C-36-KM-HT-EI-2200 | C-36-KM-HT-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Loop Checking for Instruments | Glanding & Termination | C-36-KM-HT-EI-2040 | C-36-KM-HT-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | P2543-R01-Oct24..4.3.1.4.12.1.10 Backfilling for CablesCCOJ42CS34 | Electrical & Earthing Cable Laying | Back Filling for Electrical & Earthing Cable | C-36-KM-HT-EI-2000 | C-36-KM-HT-CI-2800 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | P2543-R01-Oct24..4.3.1.4.12.1.10 Backfilling for CablesCCOJ42CS34 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-36-KM-HT-EI-2010 | C-36-KM-HT-CI-2810 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.4.12.4.6 Isolation of Hot Tap JointCCOJ42HT80 | P2543-R01-Oct24..4.3.1.4.12.5.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT090 | Isolation of Hot Tap Joint | Preparation, Marking & UT for Existing Line 36" Line | C-36-KM-HT03-ME-1050 | C-36-KM-HT04-ME-1000 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.4.12.2.6 Final Bolt Torquing/ Re-InstatementCCOJ42PI122 | P2543-R01-Oct24..4.3.1.4.12.6.1 Tie -in WorksCCOJ42PI72 | Final Bolt Torquing/ Re-Instatement | Tie-In with 36" Pipeline | C-36-KM-HT-PI-2000 | C-36-KM-HT-ME-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | Earth Works for Hot Tap Tie in Pit | Site Survey, Preparation (Include Existing Dismantling Fence) & Grading Works | C-36-KM-HT-CI-1080 | C-52-D-HT-CI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | Site Survey, Preparation (Include Existing Dismantling Fence) & Grading Works | Earth Works for Pipe Support Foundations | C-52-D-HT-CI-1000 | C-52-D-HT-CI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | Earth Works for Pipe Support Foundations | Earth Works for Hot Tap Tie in Pit | C-52-D-HT-CI-1020 | C-52-D-HT-CI-1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | Earth Works for Hot Tap Tie in Pit | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-D-HT-CI-1080 | C-52-D-HT-CI-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | Earth Works for Pipe Support Foundations | Compaction & Testing for Pipe Support Foundations | C-52-D-HT-CI-1020 | C-52-D-HT-CI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | Earth Works for Access Platforms & Misc. Structural Foundations | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-52-D-HT-CI-1040 | C-52-D-HT-CI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | Earth Works for Hot Tap Tie in Pit | Compaction & Testing for Hot Tap Tie in Pit | C-52-D-HT-CI-1080 | C-52-D-HT-CI-1280 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | Compaction & Testing for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-52-D-HT-CI-1210 | C-52-D-HT-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | Concrete Works for Access Platforms & Misc. Structural Foundations | C-52-D-HT-CI-1230 | C-52-D-HT-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | Compaction & Testing for Hot Tap Tie in Pit | Concrete Works for Hot Tap Tie in Pit | C-52-D-HT-CI-1280 | C-52-D-HT-CI-1480 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | Concrete Works for Pipe Support Foundations | Concrete Works for Hot Tap Tie in Pit | C-52-D-HT-CI-1600 | C-52-D-HT-CI-1480 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | Concrete Works for Hot Tap Tie in Pit | Concrete Works for Access Platforms & Misc. Structural Foundations | C-52-D-HT-CI-1480 | C-52-D-HT-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.2.1 Piping Pre-FabricationCCOJ42PI070 | P2543-R01-Oct24..4.3.1.3.3.21.2.1 Piping Pre-FabricationCCOSWPI509 | Piping Pre-Fabrication | Piping Pre-Fabrication | C-36-KM-HT-PI-1000 | C-52-D-HT-PI-1000 | SS | Not Started | Not Started | 6
P2543-R01-Oct24..4.3.1.4.12.5.6 Isolation of Hot Tap JointCCOJ42HT140 | P2543-R01-Oct24..4.3.1.3.3.21.3.1 Preparation, Marking & UT for Existing Line 48" LineCCOSWHT461 | Isolation of Hot Tap Joint | Preparation, Marking & UT for Existing Line 48" Line | C-36-KM-HT04-ME-1050 | C-52-D-HT002-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.3.6 Isolation of Hot Tap JointCCOSWHT511 | P2543-R01-Oct24..4.3.1.3.3.21.4.1 Tie in works to 52'' and 20'' PipelineCCOSWPI512 | Isolation of Hot Tap Joint | Tie-In with 30" Pipeline | C-52-D-HT002-ME-1050 | C-52-D-HT-ME-2000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | P2543-R01-Oct24..4.3.1.3.3.21.1.7 Paving WorksCCOSWCS316 | Concrete Works for Hot Tap Tie in Pit | Paving of Interlock tiles & Kerb Stone Embankment (Including Fence Re-Instatement) | C-52-D-HT-CI-1480 | C-52-D-HT-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.2.6 Final Bolt Torquing/ Re-InstatementCCOSWPI564 | P2543-R01-Oct24..4.3.1.3.3.21.1.7 Paving WorksCCOSWCS316 | Final Bolt Torquing/ Re-Instatement | Paving of Interlock tiles & Kerb Stone Embankment (Including Fence Re-Instatement) | C-52-D-HT-PI-2000 | C-52-D-HT-CI-2600 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.3.21.4.1 Tie in works to 52'' and 20'' PipelineCCOSWPI512 | P2543-R01-Oct24..4.3.1.3.3.21.1.7 Paving WorksCCOSWCS316 | Tie-In with 30" Pipeline | Paving of Interlock tiles & Kerb Stone Embankment (Including Fence Re-Instatement) | C-52-D-HT-ME-2000 | C-52-D-HT-CI-2600 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | Site Survey, Preparation & Grading Works | Earth Works for Equipment Foundations | C-52-PL-838-CI-1000 | C-52-PL-838-CI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | Earth Works for Equipment Foundations | Earth Works for Pipe Support Foundations | C-52-PL-838-CI-1010 | C-52-PL-838-CI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | Site Survey, Preparation & Grading Works | Earth Works for Thrust Anchor Block | C-52-PL-838-CI-1000 | C-52-PL-838-CI-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | Earth Works for Field Instrument, JBs & Light Pole Foundations | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-PL-838-CI-1030 | C-52-PL-838-CI-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | Earth Works for Thrust Anchor Block | Earth Works for Field Instrument, JBs & Light Pole Foundations | C-52-PL-838-CI-1050 | C-52-PL-838-CI-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | P2543-R01-Oct24..4.3.1.3.1.21.1.2 Compaction & TestingCCOH52CS32 | Earth Works for Equipment Foundations | Compaction & Testing for Equipment Foundations | C-52-PL-838-CI-1010 | C-52-PL-838-CI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | P2543-R01-Oct24..4.3.1.3.1.21.1.2 Compaction & TestingCCOH52CS32 | Earth Works for Pipe Support Foundations | Compaction & Testing for Pipe Support Foundations | C-52-PL-838-CI-1020 | C-52-PL-838-CI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | P2543-R01-Oct24..4.3.1.3.1.21.1.2 Compaction & TestingCCOH52CS32 | Earth Works for Field Instrument, JBs & Light Pole Foundations | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | C-52-PL-838-CI-1030 | C-52-PL-838-CI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | P2543-R01-Oct24..4.3.1.3.1.21.1.2 Compaction & TestingCCOH52CS32 | Earth Works for Access Platforms & Misc. Structural Foundations | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-52-PL-838-CI-1040 | C-52-PL-838-CI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | P2543-R01-Oct24..4.3.1.3.1.21.1.2 Compaction & TestingCCOH52CS32 | Earth Works for Thrust Anchor Block | Compaction & Testing for Thrust Anchor Block | C-52-PL-838-CI-1050 | C-52-PL-838-CI-1240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.2 Compaction & TestingCCOH52CS32 | P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | Compaction & Testing for Equipment Foundations | Concrete Works for Equipment Foundations | C-52-PL-838-CI-1200 | C-52-PL-838-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.2 Compaction & TestingCCOH52CS32 | P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | Compaction & Testing for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-52-PL-838-CI-1210 | C-52-PL-838-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.2 Compaction & TestingCCOH52CS32 | P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-52-PL-838-CI-1220 | C-52-PL-838-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.2 Compaction & TestingCCOH52CS32 | P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | Concrete Works for Access Platforms & Misc. Structural Foundations | C-52-PL-838-CI-1230 | C-52-PL-838-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.2 Compaction & TestingCCOH52CS32 | P2543-R01-Oct24..4.3.1.3.1.21.1.5 Thrust Anchor BlockCCOH52SS32 | Compaction & Testing for Thrust Anchor Block | Concrete Works for Thrust Anchor Block | C-52-PL-838-CI-1240 | C-52-PL-838-CI-1510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | Concrete Works for Equipment Foundations | Concrete Works for Pipe Support Foundations | C-52-PL-838-CI-1400 | C-52-PL-838-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | Concrete Works for Pipe Support Foundations | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-52-PL-838-CI-1600 | C-52-PL-838-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Concrete Works for Access Platforms & Misc. Structural Foundations | C-52-PL-838-CI-1410 | C-52-PL-838-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | P2543-R01-Oct24..4.3.1.3.1.21.1.7 Trenching for Electrical cablesCCOH52CS35.1 | Earth Works for Thrust Anchor Block | Electrical & Earthing Cable Trenching | C-52-PL-838-CI-1050 | C-52-PL-838-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.7 Trenching for Electrical cablesCCOH52CS35.1 | P2543-R01-Oct24..4.3.1.3.1.21.1.9 Trenching for Instrument cablesCCOH52CS35.2 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-52-PL-838-CI-1800 | C-52-PL-838-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.11 Backfilling for CablesCCOH52CS37 | P2543-R01-Oct24..4.3.1.3.1.21.1.11 Backfilling for CablesCCOH52CS37 | Back Filling for Electrical & Earthing Cable | Back Filling for Instrument & Telecom Cable | C-52-PL-838-CI-2800 | C-52-PL-838-CI-2810 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.1.21.1.11 Backfilling for CablesCCOH52CS37 | P2543-R01-Oct24..4.3.1.3.1.21.1.10 Paving WorksCCOH52CS36 | Back Filling for Instrument & Telecom Cable | Paving of Interlock tiles & Kerb Stone Embankment | C-52-PL-838-CI-2810 | C-52-PL-838-CI-2600 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | P2543-R01-Oct24..4.3.1.3.1.21.1.6 Pipe Supports Fabrication & InstallationCCOH52SS60 | Concrete Works for Pipe Support Foundations | Pre-Fabrication & Installation of Pipe Supports | C-52-PL-838-CI-1600 | C-52-PL-838-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | P2543-R01-Oct24..4.3.1.3.1.21.6.2 Field InstrumentsCCOH52EL72 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-PL-838-CI-1410 | C-52-PL-838-EI-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | P2543-R01-Oct24..4.3.1.3.1.21.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOH52SS61 | Concrete Works for Access Platforms & Misc. Structural Foundations | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-PL-838-CI-1420 | C-52-PL-838-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOH52SS61 | P2543-R01-Oct24..4.3.1.3.1.21.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOH52SS61 | Pre-Fabrication & Installation of Platforms & Crossovers | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-PL-838-CI-3000 | C-52-PL-838-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | P2543-R01-Oct24..4.3.1.3.1.21.3.1 Installation of Pig Launcher (838-V-602)CCOH52ME60 | Concrete Works for Equipment Foundations | Installation of Pig Launcher (838-V-602) 52" | C-52-PL-838-CI-1400 | C-52-PL-838-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.2 Installation of Pig Receiver (839-V-101)CCOSWME508 | P2543-R01-Oct24..4.3.1.3.1.21.3.1 Installation of Pig Launcher (838-V-602)CCOH52ME60 | Installation of Pig Receiver (839-V-101) 52" | Installation of Pig Launcher (838-V-602) 52" | C-52-PR-839-ME-1100 | C-52-PL-838-ME-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.21.12.4.22 Piping Pre-Fabrication CCOH56PI101 | P2543-R01-Oct24..4.3.1.3.1.21.4.1 Piping Works -FabricationCCOH52PI60.1 | Piping Pre-Fabrication | Piping Pre-Fabrication | C-56-PR-838-PI-1000 | C-52-PL-838-PI-1000 | SS | Not Started | Not Started | 21
P2543-R01-Oct24..4.3.1.3.1.21.5.1 Pig Launcher 838-V-602 52'' Pipeline/Piping Hook-upCCOH52PI70 | P2543-R01-Oct24..4.3.1.3.1.21.5.1 Pig Launcher 838-V-602 52'' Pipeline/Piping Hook-upCCOH52PI70 | Installation of Isolation Joint | Field Joint Welding (Piping/Pipeline Section including IJ) | C-52-PL-838-PL-1000 | C-52-PL-838-PL-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.5.1 Pig Launcher 838-V-602 52'' Pipeline/Piping Hook-upCCOH52PI70 | P2543-R01-Oct24..4.3.1.3.1.21.5.1 Pig Launcher 838-V-602 52'' Pipeline/Piping Hook-upCCOH52PI70 | Field Joint Welding (Piping/Pipeline Section including IJ) | NDT for Weld Joint | C-52-PL-838-PL-1010 | C-52-PL-838-PL-1020 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.1.21.5.1 Pig Launcher 838-V-602 52'' Pipeline/Piping Hook-upCCOH52PI70 | P2543-R01-Oct24..4.3.1.3.1.21.5.1 Pig Launcher 838-V-602 52'' Pipeline/Piping Hook-upCCOH52PI70 | NDT for Weld Joint | Ext. Coating for Weld Joint | C-52-PL-838-PL-1020 | C-52-PL-838-PL-1030 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Electrical & Earthing Cable Laying | Electrical & Earthing Cable Laying | C-56-PR-838-EI-2000 | C-52-PL-838-EI-2000 | FS | Not Started | Not Started | 30
P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Electrical & Earthing Cable Laying | Deep Earth Well Drilling | C-52-PL-838-EI-2000 | C-52-PL-838-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Electrical & Earthing Cable Laying | Instrument Cable Laying | C-52-PL-838-EI-2000 | C-52-PL-838-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Instrument Cable Laying | Installation of Cable Trays | C-52-PL-838-EI-2010 | C-52-PL-838-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Installation of Cable Trays | Instrument Tubing Works | C-52-PL-838-EI-2020 | C-52-PL-838-EI-2030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Electrical & Earthing Cable Laying | Installation of Light Pole, Lighting & Fixtures | C-52-PL-838-EI-2000 | C-52-PL-838-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Installation of Cable Trays | Installation of Light Pole, Lighting & Fixtures | C-52-PL-838-EI-2020 | C-52-PL-838-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.2 Field InstrumentsCCOH52EL72 | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Light Pole, Lighting & Fixtures | C-52-PL-838-EI-2210 | C-52-PL-838-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Installation of Cable Trays | Installation of JB's | C-52-PL-838-EI-2020 | C-52-PL-838-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Electrical & Earthing Cable Laying | Installation of JB's | C-52-PL-838-EI-2000 | C-52-PL-838-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.2 Field InstrumentsCCOH52EL72 | P2543-R01-Oct24..4.3.1.3.1.21.6.2 Field InstrumentsCCOH52EL72 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of Field Instruments (Including Pig Signaller) | C-52-PL-838-EI-2210 | C-52-PL-838-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | P2543-R01-Oct24..4.3.1.3.1.21.6.2 Field InstrumentsCCOH52EL72 | Instrument Cable Laying | Installation of Field Instruments (Including Pig Signaller) | C-52-PL-838-EI-2010 | C-52-PL-838-EI-2200 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | P2543-R01-Oct24..4.3.1.3.1.21.6.2 Field InstrumentsCCOH52EL72 | Installation of Cable Trays | Installation of Field Instruments (Including Pig Signaller) | C-52-PL-838-EI-2020 | C-52-PL-838-EI-2200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | P2543-R01-Oct24..4.3.1.3.1.21.6.2 Field InstrumentsCCOH52EL72 | Instrument Tubing Works | Installation of Field Instruments (Including Pig Signaller) | C-52-PL-838-EI-2030 | C-52-PL-838-EI-2200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.1.21.6.2 Field InstrumentsCCOH52EL72 | P2543-R01-Oct24..4.3.1.3.1.21.6.2 Field InstrumentsCCOH52EL72 | Installation of Field Instruments (Including Pig Signaller) | Installation of F&G Device | C-52-PL-838-EI-2200 | C-52-PL-838-EI-2410 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Instrument Cable Laying | Loop Checking for Instruments | C-52-PL-838-EI-2010 | C-52-PL-838-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Instrument Tubing Works | Loop Checking for Instruments | C-52-PL-838-EI-2030 | C-52-PL-838-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.2 Field InstrumentsCCOH52EL72 | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Installation of Field Instruments (Including Pig Signaller) | Loop Checking for Instruments | C-52-PL-838-EI-2200 | C-52-PL-838-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.2 Field InstrumentsCCOH52EL72 | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Installation of F&G Device | Loop Checking for Instruments | C-52-PL-838-EI-2410 | C-52-PL-838-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Electrical & Earthing Cable Laying | Glanding & Termination | C-52-PL-838-EI-2000 | C-52-PL-838-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Installation of Light Pole, Lighting & Fixtures | Glanding & Termination | C-52-PL-838-EI-1800 | C-52-PL-838-EI-2050 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Installation of JB's | Glanding & Termination | C-52-PL-838-EI-1810 | C-52-PL-838-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Deep Earth Well Drilling | Glanding & Termination | C-52-PL-838-EI-1400 | C-52-PL-838-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Loop Checking for Instruments | Glanding & Termination | C-52-PL-838-EI-2040 | C-52-PL-838-EI-2050 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.1.21.7.1 CP Anode Bed Installation (subcontract)CCOH52EL52 | P2543-R01-Oct24..4.3.1.3.1.21.7.1 CP Anode Bed Installation (subcontract)CCOH52EL52 | CP Cable Laying | Installation of CP Test Post | C-52-PL-838-CA-1000 | C-52-PL-838-CA-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.7.1 CP Anode Bed Installation (subcontract)CCOH52EL52 | P2543-R01-Oct24..4.3.1.3.1.21.7.1 CP Anode Bed Installation (subcontract)CCOH52EL52 | Installation of CP Test Post | Installation of CP JB's | C-52-PL-838-CA-1010 | C-52-PL-838-CA-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.7.1 CP Anode Bed Installation (subcontract)CCOH52EL52 | P2543-R01-Oct24..4.3.1.3.1.21.7.1 CP Anode Bed Installation (subcontract)CCOH52EL52 | Installation of CP JB's | Glanding & Termination for CP S/m | C-52-PL-838-CA-1020 | C-52-PL-838-CA-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | P2543-R01-Oct24..4.3.1.3.1.21.8.2 CCTV System (Including subcontract for FOC Splicing / Termination / Testing )CCOH52IC73 | Instrument Cable Laying | FOC Laying | C-52-PL-838-EI-2010 | C-52-PL-838-TE-1410 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.1.21.8.2 CCTV System (Including subcontract for FOC Splicing / Termination / Testing )CCOH52IC73 | P2543-R01-Oct24..4.3.1.3.1.21.8.2 CCTV System (Including subcontract for FOC Splicing / Termination / Testing )CCOH52IC73 | FOC Laying | FO Cable OTDR Testing & Splicing | C-52-PL-838-TE-1410 | C-52-PL-838-TE-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | P2543-R01-Oct24..4.3.1.3.1.21.7.1 CP Anode Bed Installation (subcontract)CCOH52EL52 | Electrical & Earthing Cable Laying | CP Cable Laying | C-52-PL-838-EI-2000 | C-52-PL-838-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | P2543-R01-Oct24..4.3.1.3.1.21.1.11 Backfilling for CablesCCOH52CS37 | Electrical & Earthing Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-PL-838-EI-2000 | C-52-PL-838-CI-2800 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.1.21.7.1 CP Anode Bed Installation (subcontract)CCOH52EL52 | P2543-R01-Oct24..4.3.1.3.1.21.1.11 Backfilling for CablesCCOH52CS37 | CP Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-PL-838-CA-1000 | C-52-PL-838-CI-2800 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | P2543-R01-Oct24..4.3.1.3.1.21.1.11 Backfilling for CablesCCOH52CS37 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-52-PL-838-EI-2010 | C-52-PL-838-CI-2810 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.1.21.8.2 CCTV System (Including subcontract for FOC Splicing / Termination / Testing )CCOH52IC73 | P2543-R01-Oct24..4.3.1.3.1.21.1.11 Backfilling for CablesCCOH52CS37 | FOC Laying | Back Filling for Instrument & Telecom Cable | C-52-PL-838-TE-1410 | C-52-PL-838-CI-2810 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.1.3.10.40.7 Paving WorksCCOHBCS305 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | Paving of Interlock tiles & Kerb Stone Embankment | Site Survey, Preparation & Grading Works | C-56-G-HT-CI-2600 | C-52-IDS1-CI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | Site Survey, Preparation & Grading Works | Earth Works for Solar S/m Foundation | C-52-IDS1-CI-1000 | C-52-IDS1-CI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | Earth Works for Solar S/m Foundation | Earth Works for Field Instruments & JBs | C-52-IDS1-CI-1010 | C-52-IDS1-CI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | Earth Works for Field Instruments & JBs | Earth Works for CCTV Pole, Fence & Gates Foundation | C-52-IDS1-CI-1020 | C-52-IDS1-CI-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.2 Compaction & TestingCCOH52CS39 | Earth Works for Solar S/m Foundation | Compaction & Testing for Solar S/m Foundation | C-52-IDS1-CI-1010 | C-52-IDS1-CI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.2 Compaction & TestingCCOH52CS39 | Earth Works for Field Instruments & JBs | Compaction & Testing for Field Instruments & JBs | C-52-IDS1-CI-1020 | C-52-IDS1-CI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.2 Compaction & TestingCCOH52CS39 | Earth Works for CCTV Pole, Fence & Gates Foundation | Compaction & Testing for CCTV Pole, Fence & Gates Foundation | C-52-IDS1-CI-1030 | C-52-IDS1-CI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.2 Compaction & TestingCCOH52CS39 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | Compaction & Testing for Solar S/m Foundation | Concrete Works for Solar S/m Foundation | C-52-IDS1-CI-1200 | C-52-IDS1-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.2 Compaction & TestingCCOH52CS39 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | Compaction & Testing for Field Instruments & JBs | Concrete Works for Field Instruments & JBs Foundation | C-52-IDS1-CI-1210 | C-52-IDS1-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.2 Compaction & TestingCCOH52CS39 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | Compaction & Testing for CCTV Pole, Fence & Gates Foundation | Concrete Works for CCTV Pole, Fence & Gates Foundation | C-52-IDS1-CI-1220 | C-52-IDS1-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | Concrete Works for Solar S/m Foundation | Concrete Works for Field Instruments & JBs Foundation | C-52-IDS1-CI-1400 | C-52-IDS1-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.6 Trenching for CablesCCOH52CS43 | Earth Works for CCTV Pole, Fence & Gates Foundation | Electrical & Earthing Cable Trenching | C-52-IDS1-CI-1030 | C-52-IDS1-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.6 Trenching for CablesCCOH52CS43 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.6 Trenching for CablesCCOH52CS43 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-52-IDS1-CI-1800 | C-52-IDS1-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.5 Fences & Gates ConstructionCCOH52CS42 | Concrete Works for CCTV Pole, Fence & Gates Foundation | Installation of Fence Post & Mesh Works (Type-3) | C-52-IDS1-CI-1420 | C-52-IDS1-CI-2220 | SS | Not Started | Not Started | 21
P2543-R01-Oct24..4.3.1.3.7.4.21.1.5 Fences & Gates ConstructionCCOH52CS42 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.5 Fences & Gates ConstructionCCOH52CS42 | Installation of Fence Post & Mesh Works (Type-3) | Installation of Access Gate | C-52-IDS1-CI-2220 | C-52-IDS1-CI-2230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | Concrete Works for CCTV Pole, Fence & Gates Foundation | Installation of CCTV Poles | C-52-IDS1-CI-1420 | C-52-IDS1-TE-1590 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | Concrete Works for Solar S/m Foundation | Installation of Solar S/m Structurals | C-52-IDS1-CI-1400 | C-52-IDS1-EI-1190 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.7 Paving WorksCCOH52CS44 | Installation of Solar S/m Structurals | Paving of Interlock tiles & Kerb Stone Embankment | C-52-IDS1-EI-1190 | C-52-IDS1-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.6 Trenching for CablesCCOH52CS43 | P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Laying | C-52-IDS1-CI-1800 | C-52-IDS1-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.6 Trenching for CablesCCOH52CS43 | P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-52-IDS1-CI-1810 | C-52-IDS1-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | Installation of Solar S/m Structurals | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-IDS1-EI-1190 | C-52-IDS1-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | Installation of Solar S/m (Including Panels, UPS & Battery) | Installation of Lighting & Instrument JB's | C-52-IDS1-EI-1200 | C-52-IDS1-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | Installation of Lighting & Instrument JB's | Glanding & Termination | C-52-IDS1-EI-1810 | C-52-IDS1-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | Installation of CCTV Poles | CCTV Installation | C-52-IDS1-TE-1590 | C-52-IDS1-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | Site Survey, Preparation & Grading Works | Earth Works for Solar S/m Foundation | C-52-IDS2-CI-1000 | C-52-IDS2-CI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | Earth Works for Solar S/m Foundation | Earth Works for Field Instruments & JBs | C-52-IDS2-CI-1010 | C-52-IDS2-CI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | Earth Works for Field Instruments & JBs | Earth Works for CCTV Pole, Fence & Gates Foundation | C-52-IDS2-CI-1020 | C-52-IDS2-CI-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.2 Compaction & TestingCCOH52CS47 | Earth Works for Solar S/m Foundation | Compaction & Testing for Solar S/m Foundation | C-52-IDS2-CI-1010 | C-52-IDS2-CI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.2 Compaction & TestingCCOH52CS47 | Earth Works for Field Instruments & JBs | Compaction & Testing for Field Instruments & JBs | C-52-IDS2-CI-1020 | C-52-IDS2-CI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.2 Compaction & TestingCCOH52CS47 | Earth Works for CCTV Pole, Fence & Gates Foundation | Compaction & Testing for CCTV Pole, Fence & Gates Foundation | C-52-IDS2-CI-1030 | C-52-IDS2-CI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.2 Compaction & TestingCCOH52CS47 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | Compaction & Testing for Solar S/m Foundation | Concrete Works for Solar S/m Foundation | C-52-IDS2-CI-1200 | C-52-IDS2-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.2 Compaction & TestingCCOH52CS47 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | Compaction & Testing for Field Instruments & JBs | Concrete Works for Field Instruments & JBs Foundation | C-52-IDS2-CI-1210 | C-52-IDS2-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.2 Compaction & TestingCCOH52CS47 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | Compaction & Testing for CCTV Pole, Fence & Gates Foundation | Concrete Works for CCTV Pole, Fence & Gates Foundation | C-52-IDS2-CI-1220 | C-52-IDS2-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | Concrete Works for Solar S/m Foundation | Concrete Works for Field Instruments & JBs Foundation | C-52-IDS2-CI-1400 | C-52-IDS2-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.6 Trenching for CablesCCOH52CS51 | Earth Works for CCTV Pole, Fence & Gates Foundation | Electrical & Earthing Cable Trenching | C-52-IDS2-CI-1030 | C-52-IDS2-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.6 Trenching for CablesCCOH52CS51 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.6 Trenching for CablesCCOH52CS51 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-52-IDS2-CI-1800 | C-52-IDS2-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.5 Fences & Gates ConstructionCCOH52CS50 | Concrete Works for CCTV Pole, Fence & Gates Foundation | Installation of Fence Post & Mesh Works (Type-3) | C-52-IDS2-CI-1420 | C-52-IDS2-CI-2220 | SS | Not Started | Not Started | 21
P2543-R01-Oct24..4.3.1.3.7.6.21.1.5 Fences & Gates ConstructionCCOH52CS50 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.5 Fences & Gates ConstructionCCOH52CS50 | Installation of Fence Post & Mesh Works (Type-3) | Installation of Access Gate | C-52-IDS2-CI-2220 | C-52-IDS2-CI-2230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | Concrete Works for CCTV Pole, Fence & Gates Foundation | Installation of CCTV Poles | C-52-IDS2-CI-1420 | C-52-IDS2-TE-1590 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | Concrete Works for Solar S/m Foundation | Installation of Solar S/m Structurals | C-52-IDS2-CI-1400 | C-52-IDS2-EI-1190 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.7 Paving WorksCCOH52CS52 | Installation of Solar S/m Structurals | Paving of Interlock tiles & Kerb Stone Embankment | C-52-IDS2-EI-1190 | C-52-IDS2-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.6 Trenching for CablesCCOH52CS51 | P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Laying | C-52-IDS2-CI-1800 | C-52-IDS2-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.6 Trenching for CablesCCOH52CS51 | P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-52-IDS2-CI-1810 | C-52-IDS2-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | Installation of Solar S/m Structurals | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-IDS2-EI-1190 | C-52-IDS2-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | Installation of Solar S/m (Including Panels, UPS & Battery) | Installation of Lighting & Instrument JB's | C-52-IDS2-EI-1200 | C-52-IDS2-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | Installation of Lighting & Instrument JB's | Glanding & Termination | C-52-IDS2-EI-1810 | C-52-IDS2-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | Installation of CCTV Poles | CCTV Installation | C-52-IDS2-TE-1590 | C-52-IDS2-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | Site Survey, Preparation & Grading Works | Earth Works for Solar S/m Foundation | C-52-IDS3-CI-1000 | C-52-IDS3-CI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | Earth Works for Solar S/m Foundation | Earth Works for Field Instruments & JBs | C-52-IDS3-CI-1010 | C-52-IDS3-CI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | Earth Works for Field Instruments & JBs | Earth Works for CCTV Pole, Fence & Gates Foundation | C-52-IDS3-CI-1020 | C-52-IDS3-CI-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.2 Compaction & TestingCCOH52CS55 | Earth Works for Solar S/m Foundation | Compaction & Testing for Solar S/m Foundation | C-52-IDS3-CI-1010 | C-52-IDS3-CI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.2 Compaction & TestingCCOH52CS55 | Earth Works for Field Instruments & JBs | Compaction & Testing for Field Instruments & JBs | C-52-IDS3-CI-1020 | C-52-IDS3-CI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.2 Compaction & TestingCCOH52CS55 | Earth Works for CCTV Pole, Fence & Gates Foundation | Compaction & Testing for CCTV Pole, Fence & Gates Foundation | C-52-IDS3-CI-1030 | C-52-IDS3-CI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.2 Compaction & TestingCCOH52CS55 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | Compaction & Testing for Solar S/m Foundation | Concrete Works for Solar S/m Foundation | C-52-IDS3-CI-1200 | C-52-IDS3-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.2 Compaction & TestingCCOH52CS55 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | Compaction & Testing for Field Instruments & JBs | Concrete Works for Field Instruments & JBs Foundation | C-52-IDS3-CI-1210 | C-52-IDS3-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.2 Compaction & TestingCCOH52CS55 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | Compaction & Testing for CCTV Pole, Fence & Gates Foundation | Concrete Works for CCTV Pole, Fence & Gates Foundation | C-52-IDS3-CI-1220 | C-52-IDS3-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | Concrete Works for Solar S/m Foundation | Concrete Works for Field Instruments & JBs Foundation | C-52-IDS3-CI-1400 | C-52-IDS3-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.6 Trenching for CablesCCOH52CS59 | Earth Works for CCTV Pole, Fence & Gates Foundation | Electrical & Earthing Cable Trenching | C-52-IDS3-CI-1030 | C-52-IDS3-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.6 Trenching for CablesCCOH52CS59 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.6 Trenching for CablesCCOH52CS59 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-52-IDS3-CI-1800 | C-52-IDS3-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.5 Fences & Gates ConstructionCCOH52CS58 | Concrete Works for CCTV Pole, Fence & Gates Foundation | Installation of Fence Post & Mesh Works (Type-3) | C-52-IDS3-CI-1420 | C-52-IDS3-CI-2220 | SS | Not Started | Not Started | 21
P2543-R01-Oct24..4.3.1.3.7.5.21.1.5 Fences & Gates ConstructionCCOH52CS58 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.5 Fences & Gates ConstructionCCOH52CS58 | Installation of Fence Post & Mesh Works (Type-3) | Installation of Access Gate | C-52-IDS3-CI-2220 | C-52-IDS3-CI-2230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | Concrete Works for CCTV Pole, Fence & Gates Foundation | Installation of CCTV Poles | C-52-IDS3-CI-1420 | C-52-IDS3-TE-1590 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | Concrete Works for Solar S/m Foundation | Installation of Solar S/m Structurals | C-52-IDS3-CI-1400 | C-52-IDS3-EI-1190 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.7 Paving WorksCCOH52CS60 | Installation of Solar S/m Structurals | Paving of Interlock tiles & Kerb Stone Embankment | C-52-IDS3-EI-1190 | C-52-IDS3-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.6 Trenching for CablesCCOH52CS59 | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Laying | C-52-IDS3-CI-1800 | C-52-IDS3-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.6 Trenching for CablesCCOH52CS59 | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-52-IDS3-CI-1810 | C-52-IDS3-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | Installation of Solar S/m Structurals | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-IDS3-EI-1190 | C-52-IDS3-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | Installation of Solar S/m (Including Panels, UPS & Battery) | Installation of Lighting & Instrument JB's | C-52-IDS3-EI-1200 | C-52-IDS3-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | Installation of Lighting & Instrument JB's | Glanding & Termination | C-52-IDS3-EI-1810 | C-52-IDS3-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | Installation of CCTV Poles | CCTV Installation | C-52-IDS3-TE-1590 | C-52-IDS3-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.8 Backfilling for CablesCCOH52CS45 | Electrical & Earthing Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-IDS1-EI-2000 | C-52-IDS1-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.8 Backfilling for CablesCCOH52CS45 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-52-IDS1-EI-2010 | C-52-IDS1-CI-2810 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | Site Survey, Preparation & Grading Works | Site Survey, Preparation & Grading Works | C-52-IDS1-CI-1000 | C-52-IDS2-CI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | Electrical & Earthing Cable Laying | Electrical & Earthing Cable Laying | C-52-IDS1-EI-2000 | C-52-IDS2-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | Instrument Cable Laying | Instrument Cable Laying | C-52-IDS1-EI-2010 | C-52-IDS2-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | CCTV Installation | CCTV Installation | C-52-IDS1-TE-1600 | C-52-IDS2-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.8 Backfilling for CablesCCOH52CS53 | Electrical & Earthing Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-IDS2-EI-2000 | C-52-IDS2-CI-2800 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.8 Backfilling for CablesCCOH52CS53 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-52-IDS2-EI-2010 | C-52-IDS2-CI-2810 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | Installation of Solar S/m (Including Panels, UPS & Battery) | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-IDS1-EI-1200 | C-52-IDS2-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | Site Survey, Preparation & Grading Works | Site Survey, Preparation & Grading Works | C-52-IDS2-CI-1000 | C-52-IDS3-CI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.6 Trenching for CablesCCOH52CS51 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.6 Trenching for CablesCCOH52CS59 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Trenching | C-52-IDS2-CI-1800 | C-52-IDS3-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.6 Trenching for CablesCCOH52CS51 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.6 Trenching for CablesCCOH52CS59 | Instrument & Telecom Cable Trenching | Instrument & Telecom Cable Trenching | C-52-IDS2-CI-1810 | C-52-IDS3-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.5 Fences & Gates ConstructionCCOH52CS50 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.5 Fences & Gates ConstructionCCOH52CS58 | Installation of Fence Post & Mesh Works (Type-3) | Installation of Fence Post & Mesh Works (Type-3) | C-52-IDS2-CI-2220 | C-52-IDS3-CI-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | Installation of CCTV Poles | Installation of CCTV Poles | C-52-IDS2-TE-1590 | C-52-IDS3-TE-1590 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | Installation of Solar S/m Structurals | Installation of Solar S/m Structurals | C-52-IDS2-EI-1190 | C-52-IDS3-EI-1190 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | Electrical & Earthing Cable Laying | Electrical & Earthing Cable Laying | C-52-IDS2-EI-2000 | C-52-IDS3-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | Instrument Cable Laying | Instrument Cable Laying | C-52-IDS2-EI-2010 | C-52-IDS3-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | Installation of Solar S/m (Including Panels, UPS & Battery) | Installation of Solar S/m (Including Panels, UPS & Battery) | C-52-IDS2-EI-1200 | C-52-IDS3-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | CCTV Installation | CCTV Installation | C-52-IDS2-TE-1600 | C-52-IDS3-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.8 Backfilling for CablesCCOH52CS61 | Electrical & Earthing Cable Laying | Back Filling for Electrical & Earthing Cable | C-52-IDS3-EI-2000 | C-52-IDS3-CI-2800 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.8 Backfilling for CablesCCOH52CS61 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-52-IDS3-EI-2010 | C-52-IDS3-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.9 Pipe StringingCCOPL4"104 | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | Stringing (HB-5 to HGCP) | Lowering | C-4N-H5HG-PIPEL-2800 | C-4N-H5HG-CMA13-1020 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | Lowering | Lowering | C-4N-H5HG-CMA13-1020 | C-4N-H5HG-CMA01-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | Lowering | Lowering | C-4N-H5HG-CMA01-1020 | C-4N-H5HG-CMA02-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | Lowering | Lowering | C-4N-H5HG-CMA02-1020 | C-4N-H5HG-CMA03-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | Lowering | Lowering | C-4N-H5HG-CMA03-1020 | C-4N-H5HG-CMA04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | Lowering | Lowering | C-4N-H5HG-CMA04-1020 | C-4N-H5HG-CMA05-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | Lowering | Lowering | C-4N-H5HG-CMA05-1020 | C-4N-H5HG-CMA06-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | Lowering | Lowering | C-4N-H5HG-CMA06-1020 | C-4N-H5HG-CMA07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | Lowering | Lowering | C-4N-H5HG-CMA07-1020 | C-4N-H5HG-CMA08-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | Lowering | Lowering | C-4N-H5HG-CMA08-1020 | C-4N-H5HG-CMA09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | Lowering | Lowering | C-4N-H5HG-CMA09-1020 | C-4N-H5HG-CMA10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | Lowering | Lowering | C-4N-H5HG-CMA10-1020 | C-4N-H5HG-CMA11-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | Lowering | Lowering | C-4N-H5HG-CMA12-1020 | C-4N-H5HG-CMA14-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | Lowering | Lowering | C-4N-H5HG-CMA14-1020 | C-4N-H5HG-CMA15-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | Lowering | Lowering | C-4N-H5HG-CMA15-1020 | C-4N-H5HG-CMA16-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | Lowering | Lowering | C-4N-H5HG-CMA16-1020 | C-4N-H5HG-CMA17-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | Lowering | Lowering | C-4N-H5HG-CMA17-1020 | C-4N-H5HG-CMA18-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | Lowering | Lowering | C-4N-H5HG-CMA18-1020 | C-4N-H5HG-CMA27-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | Lowering | Lowering | C-4N-H5HG-CMA27-1020 | C-4N-H5HG-CMA19-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | Lowering | Lowering | C-4N-H5HG-CMA19-1020 | C-4N-H5HG-CMA20-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | Lowering | Lowering | C-4N-H5HG-CMA20-1020 | C-4N-H5HG-CMA21-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | Lowering | Lowering | C-4N-H5HG-CMA21-1020 | C-4N-H5HG-CMA22-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | Lowering | Lowering | C-4N-H5HG-CMA23-1020 | C-4N-H5HG-CMA28-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | Lowering | Lowering | C-4N-H5HG-CMA28-1020 | C-4N-H5HG-CMA24-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | Lowering | Lowering | C-4N-H5HG-CMA24-1020 | C-4N-H5HG-CMA25-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | Lowering | Lowering | C-4N-H5HG-CMA25-1020 | C-4N-H5HG-CMA26-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | Lowering | Lowering | C-4N-H5HG-CMA26-1020 | C-4N-H5HG-CMA29-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA13-1000 | C-4N-H5HG-CMA01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA01-1000 | C-4N-H5HG-CMA02-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA02-1000 | C-4N-H5HG-CMA03-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA03-1000 | C-4N-H5HG-CMA04-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA04-1000 | C-4N-H5HG-CMA05-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA05-1000 | C-4N-H5HG-CMA06-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA06-1000 | C-4N-H5HG-CMA07-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA07-1000 | C-4N-H5HG-CMA08-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA08-1000 | C-4N-H5HG-CMA09-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA09-1000 | C-4N-H5HG-CMA10-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA10-1000 | C-4N-H5HG-CMA11-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA12-1000 | C-4N-H5HG-CMA14-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA14-1000 | C-4N-H5HG-CMA15-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA15-1000 | C-4N-H5HG-CMA16-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA16-1000 | C-4N-H5HG-CMA17-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA17-1000 | C-4N-H5HG-CMA18-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA18-1000 | C-4N-H5HG-CMA27-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA27-1000 | C-4N-H5HG-CMA19-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA19-1000 | C-4N-H5HG-CMA20-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA20-1000 | C-4N-H5HG-CMA21-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA21-1000 | C-4N-H5HG-CMA22-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA23-1000 | C-4N-H5HG-CMA28-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA28-1000 | C-4N-H5HG-CMA24-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA24-1000 | C-4N-H5HG-CMA25-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA25-1000 | C-4N-H5HG-CMA26-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA26-1000 | C-4N-H5HG-CMA29-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA13-1000 | C-4N-H5HG-CMA12-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | Lowering | Lowering | C-4N-H5HG-CMA13-1020 | C-4N-H5HG-CMA12-1020 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | Trench Excavation | Trench Excavation | C-4N-H5HG-CMA12-1000 | C-4N-H5HG-CMA23-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | Lowering | Lowering | C-4N-H5HG-CMA12-1020 | C-4N-H5HG-CMA23-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-PIPEL-6000 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA13-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA01-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA02-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA03-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA04-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA05-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA06-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA07-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA08-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA09-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA10-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA11-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA12-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA14-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA15-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA16-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA17-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA18-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA27-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA19-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA20-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA21-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA22-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA23-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA28-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA24-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA25-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA26-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Padding | Cleaning & Gauging | C-4N-H5HG-CMA29-1070 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 HDD @ CH 0+517 - 0+556 (HDD-01) | Trench Excavation | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CMA13-1000 | C-4N-H5HG-CNH01-1000 | FS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 HDD @ CH 0+517 - 0+556 (HDD-01) | P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 HDD @ CH 1+006 - 1+056 (HDD-02) | Excavation for Entry & Exit Pit Preparation | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CNH01-1000 | C-4N-H5HG-CNH02-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 HDD @ CH 1+006 - 1+056 (HDD-02) | P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 HDD @ CH 2+845 - 3+029 (HDD-03) | Excavation for Entry & Exit Pit Preparation | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CNH02-1000 | C-4N-H5HG-CNH03-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 HDD @ CH 2+845 - 3+029 (HDD-03) | P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 HDD @ CH 4+392 - 4+477 (HDD-04) | Excavation for Entry & Exit Pit Preparation | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CNH03-1000 | C-4N-H5HG-CNH04-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 HDD @ CH 4+392 - 4+477 (HDD-04) | P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 HDD @ CH 9+139 - 9+322 (HDD-05) | Excavation for Entry & Exit Pit Preparation | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CNH04-1000 | C-4N-H5HG-CNH05-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 HDD @ CH 9+139 - 9+322 (HDD-05) | P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 HDD @ CH 10+556 - 10+647 (HDD-06) | Excavation for Entry & Exit Pit Preparation | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CNH05-1000 | C-4N-H5HG-CNH06-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 HDD @ CH 10+556 - 10+647 (HDD-06) | P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 HDD @ CH 12+216 - 12+275 (HDD-07) | Excavation for Entry & Exit Pit Preparation | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CNH06-1000 | C-4N-H5HG-CNH07-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 HDD @ CH 12+216 - 12+275 (HDD-07) | P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 HDD @ CH 16+746 - 16+764 (HDD-08) | Excavation for Entry & Exit Pit Preparation | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CNH07-1000 | C-4N-H5HG-CNH08-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 HDD @ CH 0+517 - 0+556 (HDD-01) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Re-Instatement of Entry & Exit Pit | Cleaning & Gauging | C-4N-H5HG-CNH01-1030 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 HDD @ CH 1+006 - 1+056 (HDD-02) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Re-Instatement of Entry & Exit Pit | Cleaning & Gauging | C-4N-H5HG-CNH02-1030 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 HDD @ CH 2+845 - 3+029 (HDD-03) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Re-Instatement of Entry & Exit Pit | Cleaning & Gauging | C-4N-H5HG-CNH03-1030 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 HDD @ CH 4+392 - 4+477 (HDD-04) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Re-Instatement of Entry & Exit Pit | Cleaning & Gauging | C-4N-H5HG-CNH04-1030 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 HDD @ CH 9+139 - 9+322 (HDD-05) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Re-Instatement of Entry & Exit Pit | Cleaning & Gauging | C-4N-H5HG-CNH05-1030 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 HDD @ CH 10+556 - 10+647 (HDD-06) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Re-Instatement of Entry & Exit Pit | Cleaning & Gauging | C-4N-H5HG-CNH06-1030 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 HDD @ CH 12+216 - 12+275 (HDD-07) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Re-Instatement of Entry & Exit Pit | Cleaning & Gauging | C-4N-H5HG-CNH07-1030 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 HDD @ CH 16+746 - 16+764 (HDD-08) | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Re-Instatement of Entry & Exit Pit | Cleaning & Gauging | C-4N-H5HG-CNH08-1030 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.19 Test Stations & Anode BedsCCOP4"EL12 | Holiday Testing | Installation of Temp. Anode | C-4N-H5HG-PIPEL-4830 | C-4N-H5HG-PIPEL-5600 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Holiday Testing | Installation of Test Post for Crossing | C-4N-H5HG-CMA13-1060 | C-4N-H5HG-PIPEL-5220 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA01-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA02-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA03-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA04-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA05-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA06-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA07-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA08-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA09-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA10-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA11-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA12-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA14-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA15-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA16-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA17-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA18-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA27-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA19-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA20-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA21-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA22-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA23-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA28-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA24-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA25-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA26-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Padding | Installation of Test Post for Crossing | C-4N-H5HG-CMA29-1070 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 HDD @ CH 0+517 - 0+556 (HDD-01) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Re-Instatement of Entry & Exit Pit | Installation of Test Post for Crossing | C-4N-H5HG-CNH01-1030 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 HDD @ CH 1+006 - 1+056 (HDD-02) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Re-Instatement of Entry & Exit Pit | Installation of Test Post for Crossing | C-4N-H5HG-CNH02-1030 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 HDD @ CH 2+845 - 3+029 (HDD-03) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Re-Instatement of Entry & Exit Pit | Installation of Test Post for Crossing | C-4N-H5HG-CNH03-1030 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 HDD @ CH 4+392 - 4+477 (HDD-04) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Re-Instatement of Entry & Exit Pit | Installation of Test Post for Crossing | C-4N-H5HG-CNH04-1030 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 HDD @ CH 9+139 - 9+322 (HDD-05) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Re-Instatement of Entry & Exit Pit | Installation of Test Post for Crossing | C-4N-H5HG-CNH05-1030 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 HDD @ CH 10+556 - 10+647 (HDD-06) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Re-Instatement of Entry & Exit Pit | Installation of Test Post for Crossing | C-4N-H5HG-CNH06-1030 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 HDD @ CH 12+216 - 12+275 (HDD-07) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Re-Instatement of Entry & Exit Pit | Installation of Test Post for Crossing | C-4N-H5HG-CNH07-1030 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 HDD @ CH 16+746 - 16+764 (HDD-08) | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Re-Instatement of Entry & Exit Pit | Installation of Test Post for Crossing | C-4N-H5HG-CNH08-1030 | C-4N-H5HG-PIPEL-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.27 CP Works(Temporary)CCOP4"EL11.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Glanding & Termination of Temp. CP S/m | CIP/DCVG Survey | C-4N-H5HG-PIPEL-5210 | C-4N-H5HG-PIPEL-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA13-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA01-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA02-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA03-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA04-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA05-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA06-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA07-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA08-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA09-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA10-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA11-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA12-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA14-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA15-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA16-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA17-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA18-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA27-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA19-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA20-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA21-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA22-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA23-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA28-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA24-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA25-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA26-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Padding | Gatch Laying & Levelling | C-4N-H5HG-CMA29-1070 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 HDD @ CH 0+517 - 0+556 (HDD-01) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Re-Instatement of Entry & Exit Pit | Gatch Laying & Levelling | C-4N-H5HG-CNH01-1030 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 HDD @ CH 1+006 - 1+056 (HDD-02) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Re-Instatement of Entry & Exit Pit | Gatch Laying & Levelling | C-4N-H5HG-CNH02-1030 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 HDD @ CH 2+845 - 3+029 (HDD-03) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Re-Instatement of Entry & Exit Pit | Gatch Laying & Levelling | C-4N-H5HG-CNH03-1030 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 HDD @ CH 4+392 - 4+477 (HDD-04) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Re-Instatement of Entry & Exit Pit | Gatch Laying & Levelling | C-4N-H5HG-CNH04-1030 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 HDD @ CH 9+139 - 9+322 (HDD-05) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Re-Instatement of Entry & Exit Pit | Gatch Laying & Levelling | C-4N-H5HG-CNH05-1030 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 HDD @ CH 10+556 - 10+647 (HDD-06) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Re-Instatement of Entry & Exit Pit | Gatch Laying & Levelling | C-4N-H5HG-CNH06-1030 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 HDD @ CH 12+216 - 12+275 (HDD-07) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Re-Instatement of Entry & Exit Pit | Gatch Laying & Levelling | C-4N-H5HG-CNH07-1030 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 HDD @ CH 16+746 - 16+764 (HDD-08) | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Re-Instatement of Entry & Exit Pit | Gatch Laying & Levelling | C-4N-H5HG-CNH08-1030 | C-4N-H5HG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | P2543-R01-Oct24..4.3.1.5.4.12.1.33 ROW Restoration/ Marker Post/ Crash BarrierCCOPL4"126 | Gatch Laying & Levelling | ROW Restoration/ Installation of Marker Post/Sign Board | C-4N-H5HG-PIPEL-6800 | C-4N-H5HG-PIPEL-7800 | SS | Not Started | Not Started | 21
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Holiday Testing | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-PIPEL-4830 | C-4N-H5HG-PIPEL-8200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA13-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA01-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA02-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA03-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA04-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA05-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA06-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA07-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA08-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA09-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA10-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA11-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA12-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA14-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA15-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA16-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA17-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA18-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA27-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA19-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA20-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA21-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA22-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA23-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA28-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA24-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA25-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA26-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA29-1070 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 HDD @ CH 0+517 - 0+556 (HDD-01) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Re-Instatement of Entry & Exit Pit | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CNH01-1030 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 HDD @ CH 1+006 - 1+056 (HDD-02) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Re-Instatement of Entry & Exit Pit | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CNH02-1030 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 HDD @ CH 2+845 - 3+029 (HDD-03) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Re-Instatement of Entry & Exit Pit | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CNH03-1030 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 HDD @ CH 4+392 - 4+477 (HDD-04) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Re-Instatement of Entry & Exit Pit | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CNH04-1030 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 HDD @ CH 9+139 - 9+322 (HDD-05) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Re-Instatement of Entry & Exit Pit | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CNH05-1030 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 HDD @ CH 10+556 - 10+647 (HDD-06) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Re-Instatement of Entry & Exit Pit | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CNH06-1030 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 HDD @ CH 12+216 - 12+275 (HDD-07) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Re-Instatement of Entry & Exit Pit | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CNH07-1030 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 HDD @ CH 16+746 - 16+764 (HDD-08) | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Re-Instatement of Entry & Exit Pit | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CNH08-1030 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | Stringing (SV-03 to HGCP) | Lowering | C-4W-SVHG-PIPEL-2800 | CPL-4-CRMN-3340 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | Lowering | Lowering | CPL-4-CRMN-3340 | CPL-4-CRMN-3420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | Lowering | Lowering | CPL-4-CRMN-3420 | CPL-4-CRMN-3480 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | Lowering | Lowering | CPL-4-CRMN-3480 | CPL-4-CRMN-3540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 Crossing Mechanical @ KP 1+772 (RX-02) | Lowering | Lowering | CPL-4-CRMN-3540 | CPL-4-CRMN-3600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | Trench Excavation | Trench Excavation | C-4W-SVHG-PIPEL-2400 | CPL-4-CRMN-3320 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | Trench Excavation | Trench Excavation | CPL-4-CRMN-3320 | CPL-4-CRMN-3400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | Trench Excavation | Trench Excavation | CPL-4-CRMN-3400 | CPL-4-CRMN-3460 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | Trench Excavation | Trench Excavation | CPL-4-CRMN-3460 | CPL-4-CRMN-3520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 Crossing Mechanical @ KP 1+772 (RX-02) | Trench Excavation | Trench Excavation | CPL-4-CRMN-3520 | CPL-4-CRMN-3580 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 HDD @ CH 0+236 - 0+389 (HDD-01) | Trench Excavation | Excavation for Entry & Exit Pit Preparation | C-4W-SVHG-PIPEL-2400 | C-4N-H5HG-CNH1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 HDD @ CH 0+236 - 0+389 (HDD-01) | P2543-R01-Oct24..4.3.1.5.4.12.3.9.1 HDD @ CH 1+401 - 1+551 (HDD-02) | Excavation for Entry & Exit Pit Preparation | Excavation for Entry & Exit Pit Preparation | C-4N-H5HG-CNH1-1000 | C-4N-H5HG-CNH2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | Padding | Cleaning & Gauging | C-4W-SVHG-PIPEL-6000 | C-4W-SVHG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | Padding | Cleaning & Gauging | CPL-4-CRMN-3390 | C-4W-SVHG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | Padding | Cleaning & Gauging | CPL-4-CRMN-3450 | C-4W-SVHG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | Padding | Cleaning & Gauging | CPL-4-CRMN-3510 | C-4W-SVHG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | Padding | Cleaning & Gauging | CPL-4-CRMN-3570 | C-4W-SVHG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 Crossing Mechanical @ KP 1+772 (RX-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | Padding | Cleaning & Gauging | CPL-4-CRMN-3630 | C-4W-SVHG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 HDD @ CH 0+236 - 0+389 (HDD-01) | P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | Re-Instatement of Entry & Exit Pit | Cleaning & Gauging | C-4N-H5HG-CNH1-1030 | C-4W-SVHG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.9.1 HDD @ CH 1+401 - 1+551 (HDD-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | Re-Instatement of Entry & Exit Pit | Cleaning & Gauging | C-4N-H5HG-CNH2-1030 | C-4W-SVHG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.1.6.4.12.6.4 Berm Construction | Padding | Gatch Laying & Levelling | C-4W-SVHG-PIPEL-6000 | C-4W-SVHG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.4 Berm Construction | Padding | Gatch Laying & Levelling | CPL-4-CRMN-3390 | C-4W-SVHG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | P2543-R01-Oct24..4.3.1.6.4.12.6.4 Berm Construction | Padding | Gatch Laying & Levelling | CPL-4-CRMN-3450 | C-4W-SVHG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | P2543-R01-Oct24..4.3.1.6.4.12.6.4 Berm Construction | Padding | Gatch Laying & Levelling | CPL-4-CRMN-3510 | C-4W-SVHG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | P2543-R01-Oct24..4.3.1.6.4.12.6.4 Berm Construction | Padding | Gatch Laying & Levelling | CPL-4-CRMN-3570 | C-4W-SVHG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 Crossing Mechanical @ KP 1+772 (RX-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.4 Berm Construction | Padding | Gatch Laying & Levelling | CPL-4-CRMN-3630 | C-4W-SVHG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 HDD @ CH 0+236 - 0+389 (HDD-01) | P2543-R01-Oct24..4.3.1.6.4.12.6.4 Berm Construction | Re-Instatement of Entry & Exit Pit | Gatch Laying & Levelling | C-4N-H5HG-CNH1-1030 | C-4W-SVHG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.9.1 HDD @ CH 1+401 - 1+551 (HDD-02) | P2543-R01-Oct24..4.3.1.6.4.12.6.4 Berm Construction | Re-Instatement of Entry & Exit Pit | Gatch Laying & Levelling | C-4N-H5HG-CNH2-1030 | C-4W-SVHG-PIPEL-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.4 Berm Construction | P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | Gatch Compaction | Cleaning & Gauging | C-4W-SVHG-PIPEL-6810 | C-4W-SVHG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.4 Berm Construction | P2543-R01-Oct24..4.3.1.6.4.12.6.5 Marker Post & Crash Barrier | Gatch Compaction | Installation of Marker Post/Sign Board | C-4W-SVHG-PIPEL-6810 | C-4W-SVHG-PIPEL-7800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | Site Survey, Preparation & Grading Works | Earth Works for Equipment Foundations | C-4N-H5-TPL-CI-1000 | C-4N-H5-TPL-CI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | Earth Works for Equipment Foundations | Earth Works for Pipe Support Foundations | C-4N-H5-TPL-CI-1010 | C-4N-H5-TPL-CI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | Earth Works for Pipe Support Foundations | Earth Works for Field Instrument, JBs & Light Pole Foundations | C-4N-H5-TPL-CI-1020 | C-4N-H5-TPL-CI-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | Earth Works for Field Instrument, JBs & Light Pole Foundations | Earth Works for Access Platforms & Misc. Structural Foundations | C-4N-H5-TPL-CI-1030 | C-4N-H5-TPL-CI-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | Earth Works for Access Platforms & Misc. Structural Foundations | Compaction & Testing for Equipment Foundations | C-4N-H5-TPL-CI-1040 | C-4N-H5-TPL-CI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | Compaction & Testing for Equipment Foundations | Compaction & Testing for Pipe Support Foundations | C-4N-H5-TPL-CI-1200 | C-4N-H5-TPL-CI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | Compaction & Testing for Pipe Support Foundations | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | C-4N-H5-TPL-CI-1210 | C-4N-H5-TPL-CI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-4N-H5-TPL-CI-1220 | C-4N-H5-TPL-CI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | Concrete Works for Equipment Foundations | C-4N-H5-TPL-CI-1230 | C-4N-H5-TPL-CI-1400 | FS | Not Started | Not Started | 15
P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | Concrete Works for Equipment Foundations | Concrete Works for Pipe Support Foundations | C-4N-H5-TPL-CI-1400 | C-4N-H5-TPL-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | Concrete Works for Pipe Support Foundations | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-4N-H5-TPL-CI-1600 | C-4N-H5-TPL-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Concrete Works for Access Platforms & Misc. Structural Foundations | C-4N-H5-TPL-CI-1410 | C-4N-H5-TPL-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.8 Trenching for CablesCCOH5CS105 | Concrete Works for Access Platforms & Misc. Structural Foundations | Electrical & Earthing Cable Trenching | C-4N-H5-TPL-CI-1420 | C-4N-H5-TPL-CI-1800 | FS | Not Started | Not Started | 30
P2543-R01-Oct24..4.3.1.5.2.3.12.1.8 Trenching for CablesCCOH5CS105 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.8 Trenching for CablesCCOH5CS105 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-4N-H5-TPL-CI-1800 | C-4N-H5-TPL-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | Concrete Works for Pipe Support Foundations | Pre-Fabrication & Installation of Pipe Supports | C-4N-H5-TPL-CI-1600 | C-4N-H5-TPL-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-4N-H5-TPL-CI-1410 | C-4N-H5-TPL-EI-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | Concrete Works for Access Platforms & Misc. Structural Foundations | Pre-Fabrication & Installation of Platforms & Crossovers | C-4N-H5-TPL-CI-1420 | C-4N-H5-TPL-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | Pre-Fabrication & Installation of Platforms & Crossovers | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-4N-H5-TPL-CI-3000 | C-4N-H5-TPL-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | P2543-R01-Oct24..4.3.1.5.2.3.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH5ME502 | Concrete Works for Equipment Foundations | Installation of Pig Launcher 4" | C-4N-H5-TPL-CI-1400 | C-4N-H5-TPL-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-4N-H5-TPL-CI-2000 | C-4N-H5-TPL-EI-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Pre-Fabrication & Installation of Platforms & Crossovers | C-4N-H5-TPL-EI-2210 | C-4N-H5-TPL-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | Pre-Fabrication & Installation of Platforms & Crossovers | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-4N-H5-TPL-CI-3000 | C-4N-H5-TPL-CI-3010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.3.19 Installation of Pig Receiver (838-V-601) CCOH56ME50 | P2543-R01-Oct24..4.3.1.5.2.3.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH5ME502 | Installation of Pig Receiver (838-V-601) 56" | Installation of Pig Launcher 4" | C-56-PR-838-ME-1100 | C-4N-H5-TPL-ME-1000 | FS | Not Started | Not Started | 35
P2543-R01-Oct24..4.3.1.5.2.3.12.4.1 Piping Pre-FabricationCCOH5PI501 | P2543-R01-Oct24..4.3.1.5.2.3.12.4.2 ErectionCCOH5PI515 | Piping Pre-Fabrication | Piping Erection | C-4N-H5-TPL-PI-1000 | C-4N-H5-TPL-PI-1200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.4.2 ErectionCCOH5PI515 | P2543-R01-Oct24..4.3.1.5.2.3.12.4.3 Field Joint Welding, NDT & CoatingCCOH5PI525 | Piping Erection | Field Joint Welding | C-4N-H5-TPL-PI-1200 | C-4N-H5-TPL-PI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.4.3 Field Joint Welding, NDT & CoatingCCOH5PI525 | P2543-R01-Oct24..4.3.1.5.2.3.12.4.3 Field Joint Welding, NDT & CoatingCCOH5PI525 | Field Joint Welding | NDT & Coating for Field Joint Weld | C-4N-H5-TPL-PI-1400 | C-4N-H5-TPL-PI-1410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.4.5 Installation of ValvesCCOH5PI545 | P2543-R01-Oct24..4.3.1.5.2.3.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH5PI555 | Installation of Valves/MOV/ROV | Final Bolt Torquing/ Re-Instatement | C-4N-H5-TPL-PI-1800 | C-4N-H5-TPL-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | P2543-R01-Oct24..4.3.1.5.2.3.12.4.1 Piping Pre-FabricationCCOH5PI501 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Piping Pre-Fabrication | C-4N-H5-TPL-CI-3010 | C-4N-H5-TPL-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH5ME502 | P2543-R01-Oct24..4.3.1.5.2.3.12.4.2 ErectionCCOH5PI515 | Installation of Pig Launcher 4" | Piping Erection | C-4N-H5-TPL-ME-1000 | C-4N-H5-TPL-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.2.3.12.5.10 Tie In to existing SkidCCOH5PI504 | Section Tie-in Welding | Installation of Isolation Joint | C-4N-H5HG-PIPEL-4810 | C-4N-H5-TPL-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.5.10 Tie In to existing SkidCCOH5PI504 | P2543-R01-Oct24..4.3.1.5.2.3.12.5.11 Temporary Pig Launcher (4'' Nitrogen Pipeline) Piping Hook-upCCOH5PI505 | Installation of Isolation Joint | Field Joint Welding (Piping/Pipeline Section including IJ) | C-4N-H5-TPL-PL-1000 | C-4N-H5-TPL-PL-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.5.11 Temporary Pig Launcher (4'' Nitrogen Pipeline) Piping Hook-upCCOH5PI505 | P2543-R01-Oct24..4.3.1.5.2.3.12.5.11 Temporary Pig Launcher (4'' Nitrogen Pipeline) Piping Hook-upCCOH5PI505 | Field Joint Welding (Piping/Pipeline Section including IJ) | NDT for Weld Joint | C-4N-H5-TPL-PL-1010 | C-4N-H5-TPL-PL-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.5.11 Temporary Pig Launcher (4'' Nitrogen Pipeline) Piping Hook-upCCOH5PI505 | P2543-R01-Oct24..4.3.1.5.2.3.12.5.11 Temporary Pig Launcher (4'' Nitrogen Pipeline) Piping Hook-upCCOH5PI505 | NDT for Weld Joint | Ext. Coating for Weld Joint | C-4N-H5-TPL-PL-1020 | C-4N-H5-TPL-PL-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.8 Trenching for CablesCCOH5CS105 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Laying | C-4N-H5-TPL-CI-1800 | C-4N-H5-TPL-EI-2000 | FS | Not Started | Not Started | 30
P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Electrical & Earthing Cable Laying | Installation of Cable Trays | C-4N-H5-TPL-EI-2000 | C-4N-H5-TPL-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Installation of Cable Trays | Instrument Cable Laying | C-4N-H5-TPL-EI-2020 | C-4N-H5-TPL-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Instrument Cable Laying | Instrument Tubing Works | C-4N-H5-TPL-EI-2010 | C-4N-H5-TPL-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Instrument Tubing Works | Installation of Light Pole, Lighting & Fixtures | C-4N-H5-TPL-EI-2030 | C-4N-H5-TPL-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Installation of Light Pole, Lighting & Fixtures | Installation of JB's | C-4N-H5-TPL-EI-1800 | C-4N-H5-TPL-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Installation of JB's | Installation of Field Instruments (Including Pig Signaller) | C-4N-H5-TPL-EI-1810 | C-4N-H5-TPL-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Installation of Field Instruments (Including Pig Signaller) | Installation of F&G Device | C-4N-H5-TPL-EI-2200 | C-4N-H5-TPL-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Installation of F&G Device | Loop Checking for Instruments | C-4N-H5-TPL-EI-2410 | C-4N-H5-TPL-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Loop Checking for Instruments | Glanding & Termination | C-4N-H5-TPL-EI-2040 | C-4N-H5-TPL-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | CP Cable Laying | Installation of CP Test Post | C-4N-H5-TPL-CA-1000 | C-4N-H5-TPL-CA-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Installation of CP Test Post | Installation of CP JB's | C-4N-H5-TPL-CA-1010 | C-4N-H5-TPL-CA-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Installation of CP JB's | Glanding & Termination for CP S/m | C-4N-H5-TPL-CA-1020 | C-4N-H5-TPL-CA-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Electrical & Earthing Cable Laying | CP Cable Laying | C-4N-H5-TPL-EI-2000 | C-4N-H5-TPL-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | P2543-R01-Oct24..4.3.1.5.2.3.12.8.1 Telecommunication Works CCOH5IC528 | Instrument Cable Laying | FOC Laying | C-4N-H5-TPL-EI-2010 | C-4N-H5-TPL-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.8.1 Telecommunication Works CCOH5IC528 | P2543-R01-Oct24..4.3.1.5.2.3.12.8.1 Telecommunication Works CCOH5IC528 | FOC Laying | FO Cable OTDR Testing & Splicing | C-4N-H5-TPL-TE-1410 | C-4N-H5-TPL-TE-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH5ME502 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.10 Backfilling for CablesCCOH5CS108 | Installation of Pig Launcher 4" | Back Filling for Electrical & Earthing Cable | C-4N-H5-TPL-ME-1000 | C-4N-H5-TPL-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.10 Backfilling for CablesCCOH5CS108 | Glanding & Termination | Back Filling for Electrical & Earthing Cable | C-4N-H5-TPL-EI-2050 | C-4N-H5-TPL-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.10 Backfilling for CablesCCOH5CS108 | Glanding & Termination for CP S/m | Back Filling for Electrical & Earthing Cable | C-4N-H5-TPL-CA-1030 | C-4N-H5-TPL-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.10 Backfilling for CablesCCOH5CS108 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.10 Backfilling for CablesCCOH5CS108 | Back Filling for Electrical & Earthing Cable | Back Filling for Instrument & Telecom Cable | C-4N-H5-TPL-CI-2800 | C-4N-H5-TPL-CI-2810 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.5.2.3.12.1.10 Backfilling for CablesCCOH5CS108 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.9 Paving WorksCCOH5CS107 | Back Filling for Instrument & Telecom Cable | Paving of Interlock tiles & Kerb Stone Embankment | C-4N-H5-TPL-CI-2810 | C-4N-H5-TPL-CI-2600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Site Survey, Preparation & Grading Works | Site Survey, Preparation & Grading Works | C-56-PR-838-CI-1000 | C-4N-HG-TPR-CI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Site Survey, Preparation & Grading Works | Earth Works for Equipment Foundations | C-4N-HG-TPR-CI-1000 | C-4N-HG-TPR-CI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Earth Works for Equipment Foundations | Earth Works for Pipe Support Foundations | C-4N-HG-TPR-CI-1010 | C-4N-HG-TPR-CI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Earth Works for Pipe Support Foundations | Earth Works for Field Instrument, JBs & Light Pole Foundations | C-4N-HG-TPR-CI-1020 | C-4N-HG-TPR-CI-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Earth Works for Field Instrument, JBs & Light Pole Foundations | Earth Works for Access Platforms & Misc. Structural Foundations | C-4N-HG-TPR-CI-1030 | C-4N-HG-TPR-CI-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Earth Works for Access Platforms & Misc. Structural Foundations | Earth Works for Impact Wall | C-4N-HG-TPR-CI-1040 | C-4N-HG-TPR-CI-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Earth Works for Equipment Foundations | Compaction & Testing for Equipment Foundations | C-4N-HG-TPR-CI-1010 | C-4N-HG-TPR-CI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Earth Works for Pipe Support Foundations | Compaction & Testing for Pipe Support Foundations | C-4N-HG-TPR-CI-1020 | C-4N-HG-TPR-CI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Earth Works for Field Instrument, JBs & Light Pole Foundations | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | C-4N-HG-TPR-CI-1030 | C-4N-HG-TPR-CI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Earth Works for Access Platforms & Misc. Structural Foundations | Compaction & Testing for Access Platforms & Misc. Structural Foundations | C-4N-HG-TPR-CI-1040 | C-4N-HG-TPR-CI-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Earth Works for Impact Wall | Compaction & Testing for Impact Wall | C-4N-HG-TPR-CI-1060 | C-4N-HG-TPR-CI-1250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Compaction & Testing for Equipment Foundations | Concrete Works for Equipment Foundations | C-4N-HG-TPR-CI-1200 | C-4N-HG-TPR-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Compaction & Testing for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-4N-HG-TPR-CI-1210 | C-4N-HG-TPR-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Compaction & Testing for Field Instrument, JBs & Light Pole Foundations | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-4N-HG-TPR-CI-1220 | C-4N-HG-TPR-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Compaction & Testing for Access Platforms & Misc. Structural Foundations | Concrete Works for Access Platforms & Misc. Structural Foundations | C-4N-HG-TPR-CI-1230 | C-4N-HG-TPR-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Compaction & Testing for Impact Wall | Concrete Works for Impact Wall | C-4N-HG-TPR-CI-1250 | C-4N-HG-TPR-CI-1500 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Concrete Works for Equipment Foundations | Concrete Works for Impact Wall | C-4N-HG-TPR-CI-1400 | C-4N-HG-TPR-CI-1500 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Concrete Works for Pipe Support Foundations | Concrete Works for Field Instrument, JBs & Light Pole Foundations | C-4N-HG-TPR-CI-1600 | C-4N-HG-TPR-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Concrete Works for Access Platforms & Misc. Structural Foundations | C-4N-HG-TPR-CI-1410 | C-4N-HG-TPR-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Concrete Works for Impact Wall | Concrete Works for Pipe Support Foundations | C-4N-HG-TPR-CI-1500 | C-4N-HG-TPR-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-4N-HG-TPR-CI-1800 | C-4N-HG-TPR-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.14 Trenching for Cables CCOH56CS35 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Trenching | C-56-PR-838-CI-1800 | C-4N-HG-TPR-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-4N-HG-TPR-CI-2000 | C-4N-HG-TPR-EI-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Pre-Fabrication & Installation of Platforms & Crossovers | C-4N-HG-TPR-EI-2210 | C-4N-HG-TPR-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Pre-Fabrication & Installation of Platforms & Crossovers | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-4N-HG-TPR-CI-3000 | C-4N-HG-TPR-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.4.2 ErectionCCOH4NPI060 | P2543-R01-Oct24..4.3.1.5.1.12.4.3 Field Joint Welding, NDT & CoatingCCOH4NPI070 | Piping Erection | Field Joint Welding | C-4N-HG-TPR-PI-1200 | C-4N-HG-TPR-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.4.3 Field Joint Welding, NDT & CoatingCCOH4NPI070 | P2543-R01-Oct24..4.3.1.5.1.12.4.3 Field Joint Welding, NDT & CoatingCCOH4NPI070 | Field Joint Welding | NDT & Coating for Field Joint Weld | C-4N-HG-TPR-PI-1400 | C-4N-HG-TPR-PI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.4.3 Field Joint Welding, NDT & CoatingCCOH4NPI070 | P2543-R01-Oct24..4.3.1.5.1.12.4.4 HydrotestingCCOH4NPI080 | NDT & Coating for Field Joint Weld | Hydrotesting | C-4N-HG-TPR-PI-1410 | C-4N-HG-TPR-PI-1600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.4.4 HydrotestingCCOH4NPI080 | P2543-R01-Oct24..4.3.1.5.1.12.4.5 Installation of ValvesCCOH4NPI090 | Hydrotesting | Installation of Valves/MOV/ROV | C-4N-HG-TPR-PI-1600 | C-4N-HG-TPR-PI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.4.5 Installation of ValvesCCOH4NPI090 | P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | Installation of Valves/MOV/ROV | Final Bolt Torquing/ Re-Instatement | C-4N-HG-TPR-PI-1800 | C-4N-HG-TPR-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.5.9 Temporary Pig Receiver (4'' Nitrogen Pipeline) Piping Hook-upCCOH4NPI51 | P2543-R01-Oct24..4.3.1.5.1.12.5.9 Temporary Pig Receiver (4'' Nitrogen Pipeline) Piping Hook-upCCOH4NPI51 | Installation of Isolation Joint | Field Joint Welding (Piping/Pipeline Section including IJ) | C-4N-HG-TPR-PL-1000 | C-4N-HG-TPR-PL-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.5.9 Temporary Pig Receiver (4'' Nitrogen Pipeline) Piping Hook-upCCOH4NPI51 | P2543-R01-Oct24..4.3.1.5.1.12.5.9 Temporary Pig Receiver (4'' Nitrogen Pipeline) Piping Hook-upCCOH4NPI51 | Field Joint Welding (Piping/Pipeline Section including IJ) | NDT for Weld Joint | C-4N-HG-TPR-PL-1010 | C-4N-HG-TPR-PL-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.5.9 Temporary Pig Receiver (4'' Nitrogen Pipeline) Piping Hook-upCCOH4NPI51 | P2543-R01-Oct24..4.3.1.5.1.12.5.9 Temporary Pig Receiver (4'' Nitrogen Pipeline) Piping Hook-upCCOH4NPI51 | NDT for Weld Joint | Ext. Coating for Weld Joint | C-4N-HG-TPR-PL-1020 | C-4N-HG-TPR-PL-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Electrical & Earthing Cable Laying | Installation of Cable Trays | C-4N-HG-TPR-EI-2000 | C-4N-HG-TPR-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Installation of Cable Trays | Instrument Cable Laying | C-4N-HG-TPR-EI-2020 | C-4N-HG-TPR-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Instrument Cable Laying | Instrument Tubing Works | C-4N-HG-TPR-EI-2010 | C-4N-HG-TPR-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Instrument Tubing Works | Installation of Light Pole, Lighting & Fixtures | C-4N-HG-TPR-EI-2030 | C-4N-HG-TPR-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Installation of Light Pole, Lighting & Fixtures | Installation of JB's | C-4N-HG-TPR-EI-1800 | C-4N-HG-TPR-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Installation of JB's | Installation of Field Instruments (Including Pig Signaller) | C-4N-HG-TPR-EI-1810 | C-4N-HG-TPR-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Installation of Field Instruments (Including Pig Signaller) | Installation of F&G Device | C-4N-HG-TPR-EI-2200 | C-4N-HG-TPR-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Installation of F&G Device | Loop Checking for Instruments | C-4N-HG-TPR-EI-2410 | C-4N-HG-TPR-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Loop Checking for Instruments | Glanding & Termination | C-4N-HG-TPR-EI-2040 | C-4N-HG-TPR-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | CP Cable Laying | Installation of CP Test Post | C-4N-HG-TPR-CA-1000 | C-4N-HG-TPR-CA-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Installation of CP Test Post | Installation of CP JB's | C-4N-HG-TPR-CA-1010 | C-4N-HG-TPR-CA-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Installation of CP JB's | Glanding & Termination for CP S/m | C-4N-HG-TPR-CA-1020 | C-4N-HG-TPR-CA-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.8.1 Telecommunication Works CCOH4NIC52 | P2543-R01-Oct24..4.3.1.5.1.12.8.1 Telecommunication Works CCOH4NIC52 | FOC Laying | FO Cable OTDR Testing & Splicing | C-4N-HG-TPR-TE-1410 | C-4N-HG-TPR-TE-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.3.19 Installation of Pig Receiver (838-V-601) CCOH56ME50 | P2543-R01-Oct24..4.3.1.5.1.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH4NME50 | Installation of Pig Receiver (838-V-601) 56" | Installation of Pig Receiver 4" | C-56-PR-838-ME-1100 | C-4N-HG-TPR-ME-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.4.22 Piping Pre-Fabrication CCOH56PI101 | P2543-R01-Oct24..4.3.1.5.1.12.4.1 Piping Pre-FabricationCCOH4NPI050 | Piping Pre-Fabrication | Piping Pre-Fabrication | C-56-PR-838-PI-1000 | C-4N-HG-TPR-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.5.34 Pig Receiver 838-V-601 56'' Pipeline/ Piping Hook-up CCOH56PI51 | P2543-R01-Oct24..4.3.1.5.1.12.5.9 Temporary Pig Receiver (4'' Nitrogen Pipeline) Piping Hook-upCCOH4NPI51 | Installation of Isolation Joint | Installation of Isolation Joint | C-56-PR-838-PL-1000 | C-4N-HG-TPR-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Electrical & Earthing Cable Laying | Electrical & Earthing Cable Laying | C-56-PR-838-EI-2000 | C-4N-HG-TPR-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | CP Cable Laying | CP Cable Laying | C-56-PR-838-CA-1000 | C-4N-HG-TPR-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.8.33 CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) CCOH56IC30 | P2543-R01-Oct24..4.3.1.5.1.12.8.1 Telecommunication Works CCOH4NIC52 | FOC Laying | FOC Laying | C-56-PR-838-TE-1410 | C-4N-HG-TPR-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | P2543-R01-Oct24..4.3.1.5.1.12.4.2 ErectionCCOH4NPI060 | Piping Erection | Piping Erection | C-56-PR-838-PI-1200 | C-4N-HG-TPR-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.4.24 Field Joint Welding, NDT & Coating CCOH56PI121 | P2543-R01-Oct24..4.3.1.5.1.12.4.3 Field Joint Welding, NDT & CoatingCCOH4NPI070 | Field Joint Welding | Field Joint Welding | C-56-PR-838-PI-1400 | C-4N-HG-TPR-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Instrument Cable Laying | Instrument Cable Laying | C-56-PR-838-EI-2010 | C-4N-HG-TPR-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Glanding & Termination for CP S/m | Glanding & Termination for CP S/m | C-56-PR-838-CA-1030 | C-4N-HG-TPR-CA-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.8.33 CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) CCOH56IC30 | P2543-R01-Oct24..4.3.1.5.1.12.8.1 Telecommunication Works CCOH4NIC52 | FO Cable OTDR Testing & Splicing | FO Cable OTDR Testing & Splicing | C-56-PR-838-TE-1420 | C-4N-HG-TPR-TE-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Installation of F&G Device | Back Filling for Electrical & Earthing Cable | C-4N-HG-TPR-EI-2410 | C-4N-HG-TPR-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Installation of CP JB's | Back Filling for Electrical & Earthing Cable | C-4N-HG-TPR-CA-1020 | C-4N-HG-TPR-CI-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.8.1 Telecommunication Works CCOH4NIC52 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | FOC Laying | Back Filling for Instrument & Telecom Cable | C-4N-HG-TPR-TE-1410 | C-4N-HG-TPR-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Back Filling for Electrical & Earthing Cable | Back Filling for Instrument & Telecom Cable | C-4N-HG-TPR-CI-2800 | C-4N-HG-TPR-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.5 Paving WorksCCOH4NCS69 | Back Filling for Instrument & Telecom Cable | Paving of Interlock tiles & Kerb Stone Embankment | C-4N-HG-TPR-CI-2810 | C-4N-HG-TPR-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 Crossing Mechanical @ KP 1+772 (RX-02) | P2543-R01-Oct24..4.3.1.6.1.12.1.1 Demolition Works (Paving)CCOSV3CS10 | Padding | Demolition Works (Paving) | CPL-4-CRMN-3630 | C-4W-081-03-CI-0100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.1.12.1.1 Demolition Works (Paving)CCOSV3CS10 | P2543-R01-Oct24..4.3.1.6.1.12.1.2 Concrete Works (Foundations for Equipment & Pipe Supports)CCOSV3CS11 | Demolition Works (Paving) | Concrete Works (Foundations for Equipment & Pipe Supports) | C-4W-081-03-CI-0100 | C-4W-081-03-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.1.12.1.2 Concrete Works (Foundations for Equipment & Pipe Supports)CCOSV3CS11 | P2543-R01-Oct24..4.3.1.6.1.12.1.3 Concrete ProtectionCCOSV3CS12 | Concrete Works (Foundations for Equipment & Pipe Supports) | Concrete Protection | C-4W-081-03-CI-1400 | C-4W-081-03-CI-1700 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.1.12.1.3 Concrete ProtectionCCOSV3CS12 | P2543-R01-Oct24..4.3.1.6.1.12.1.4 Paving WorksCCOSV3CS14 | Concrete Protection | Paving Works | C-4W-081-03-CI-1700 | C-4W-081-03-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.1.12.1.3 Concrete ProtectionCCOSV3CS12 | P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | Concrete Protection | Piping Works (RTP) | C-4W-081-03-CI-1700 | C-4W-081-03-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | P2543-R01-Oct24..4.3.1.6.1.12.3.1 Tie - in (4'' Tie-in Connection Water Line)CCOSV3PI51 | Piping Works (RTP) | Tie - in (4'' Tie-in Connection Water Line) | C-4W-081-03-PI-1000 | C-4W-081-03-PI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.1.12.1.1 Demolition Works (Paving)CCOSV3CS10 | P2543-R01-Oct24..4.3.1.6.2.12.1.1 Demolition Works (Paving & Fence)CCOH4WCS20 | Demolition Works (Paving) | Demolition Works (Paving & Fence) | C-4W-081-03-CI-0100 | C-4W-TI-CI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.1.12.1.2 Concrete Works (Foundations for Equipment & Pipe Supports)CCOSV3CS11 | P2543-R01-Oct24..4.3.1.6.2.12.1.2 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH4WCS21 | Concrete Works (Foundations for Equipment & Pipe Supports) | Concrete Works (Foundations for Equipment & Pipe Supports) | C-4W-081-03-CI-1400 | C-4W-TI-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.1.12.1.3 Concrete ProtectionCCOSV3CS12 | P2543-R01-Oct24..4.3.1.6.2.12.1.4 Concrete ProtectionCCOH4WCS23 | Concrete Protection | Concrete Protection | C-4W-081-03-CI-1700 | C-4W-TI-CI-1700 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.1.12.1.4 Paving WorksCCOSV3CS14 | P2543-R01-Oct24..4.3.1.6.2.12.1.3 Fences & Gates ConstructionCCOH4WCS24 | Paving Works | Fences & Gates Construction | C-4W-081-03-CI-2600 | C-4W-TI-CI-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.1.3 Fences & Gates ConstructionCCOH4WCS24 | P2543-R01-Oct24..4.3.1.6.2.12.1.5 Paving WorksCCOH4WCS25 | Fences & Gates Construction | Paving Works | C-4W-TI-CI-2220 | C-4W-TI-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | P2543-R01-Oct24..4.3.1.6.2.12.2.3 ErectionCCOH4WPI060 | Piping Works (RTP) | Piping Installation | C-4W-081-03-PI-1000 | C-4W-TI-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.2.3 ErectionCCOH4WPI060 | P2543-R01-Oct24..4.3.1.6.2.12.2.4 Field Joint Welding, NDT & CoatingCCOH4WPI070 | Piping Installation | Field Joining | C-4W-TI-PI-1200 | C-4W-TI-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.2.4 Field Joint Welding, NDT & CoatingCCOH4WPI070 | P2543-R01-Oct24..4.3.1.6.2.12.2.5 HydrotestingCCOH4WPI080 | Field Joining | Hydrotesting | C-4W-TI-PI-1400 | C-4W-TI-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.2.5 HydrotestingCCOH4WPI080 | P2543-R01-Oct24..4.3.1.6.2.12.2.6 Installation of ValvesCCOH4WPI090 | Hydrotesting | Installation of Valves | C-4W-TI-PI-1600 | C-4W-TI-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.2.6 Installation of ValvesCCOH4WPI090 | P2543-R01-Oct24..4.3.1.6.2.12.3.1 Tie - in (4'' Tie-in Connection Water Line)CCOH4WTI50 | Installation of Valves | Tie - in (4'' Tie-in Connection Water Line) | C-4W-TI-PI-1800 | C-4W-TI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.1.12.3.1 Tie - in (4'' Tie-in Connection Water Line)CCOSV3PI51 | P2543-R01-Oct24..4.3.1.6.2.12.3.1 Tie - in (4'' Tie-in Connection Water Line)CCOH4WTI50 | Tie - in (4'' Tie-in Connection Water Line) | Tie - in (4'' Tie-in Connection Water Line) | C-4W-081-03-PI-3000 | C-4W-TI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.7.12.1.1 Trenching for CablesCCOB6C32 | P2543-R01-Oct24..4.3.1.7.12.1.1 Trenching for CablesCCOB6C32 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-DBV6-CI-1800 | C-DBV6-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.7.12.1.1 Trenching for CablesCCOB6C32 | P2543-R01-Oct24..4.3.1.7.12.2.1 Electrical & Instrumentation WorksCCOB6E10 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Laying | C-DBV6-CI-1800 | C-DBV6-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.7.12.1.1 Trenching for CablesCCOB6C32 | P2543-R01-Oct24..4.3.1.7.12.2.1 Electrical & Instrumentation WorksCCOB6E10 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-DBV6-CI-1810 | C-DBV6-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.7.12.2.1 Electrical & Instrumentation WorksCCOB6E10 | P2543-R01-Oct24..4.3.1.7.12.2.1 Electrical & Instrumentation WorksCCOB6E10 | Instrument Cable Laying | Installation of H2S Analyser | C-DBV6-EI-2010 | C-DBV6-EI-2500 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.7.12.2.1 Electrical & Instrumentation WorksCCOB6E10 | P2543-R01-Oct24..4.3.1.7.12.2.1 Electrical & Instrumentation WorksCCOB6E10 | Electrical & Earthing Cable Laying | Installation of H2S Analyser | C-DBV6-EI-2000 | C-DBV6-EI-2500 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.7.12.2.1 Electrical & Instrumentation WorksCCOB6E10 | P2543-R01-Oct24..4.3.1.7.12.1.2 Backfilling for CablesCCOB6C33 | Electrical & Earthing Cable Laying | Back Filling for Electrical & Earthing Cable | C-DBV6-EI-2000 | C-DBV6-CI-2800 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.7.12.2.1 Electrical & Instrumentation WorksCCOB6E10 | P2543-R01-Oct24..4.3.1.7.12.1.2 Backfilling for CablesCCOB6C33 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-DBV6-EI-2010 | C-DBV6-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.1.2 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH4WCS21 | P2543-R01-Oct24..4.3.1.7.12.1.1 Trenching for CablesCCOB6C32 | Concrete Works (Foundations for Equipment & Pipe Supports) | Electrical & Earthing Cable Trenching | C-4W-TI-CI-1400 | C-DBV6-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | LV Cable Trenching | Instrument Trenching | C-MAQTA-CI-1800 | C-MAQTA-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | LV Cable Trenching | LV Cable Laying | C-MAQTA-CI-1800 | C-MAQTA-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Instrument Trenching | Instrument Cable Laying | C-MAQTA-CI-1810 | C-MAQTA-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Instrument Cable Laying | Glanding & Termination | C-MAQTA-EI-2010 | C-MAQTA-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | LV Cable Laying | Glanding & Termination | C-MAQTA-EI-2000 | C-MAQTA-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Glanding & Termination | Installation PIDS S/m | C-MAQTA-EI-2050 | C-MAQTA-TE-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Installation PIDS S/m | SCADA S/m Modification | C-MAQTA-TE-1020 | C-MAQTA-TE-1000 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Installation PIDS S/m | Telecom S/m Modification | C-MAQTA-TE-1020 | C-MAQTA-TE-1010 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Telecom S/m Modification | SCADA S/m Modification | C-MAQTA-TE-1010 | C-MAQTA-TE-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | LV Cable Laying | Back Filling for LV Cable | C-MAQTA-EI-2000 | C-MAQTA-CI-2800 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Instrument Cable Laying | Back Filling for Instrument Cable | C-MAQTA-EI-2010 | C-MAQTA-CI-2810 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.7.12.2.1 Electrical & Instrumentation WorksCCOB6E10 | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Installation of H2S Analyser | LV Cable Trenching | C-DBV6-EI-2500 | C-MAQTA-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | LV Cable Trenching | LV Cable Laying | C-541CR-CI-1000 | C-541CR-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | LV Cable Laying | Installation of RTU | C-541CR-EI-1000 | C-541CR-EI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | Installation of RTU | Electrical & Instrumentation Works (UPS Feeder Installation) | C-541CR-EI-1020 | C-541CR-EI-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | Electrical & Instrumentation Works (UPS Feeder Installation) | Glanding & Termination | C-541CR-EI-1030 | C-541CR-EI-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | Instrument Trenching | Instrument Cable Laying | C-541CR-CI-1010 | C-541CR-EI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | Instrument Cable Laying | Installation of RTU | C-541CR-EI-1010 | C-541CR-EI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | LV Cable Trenching | Instrument Trenching | C-541CR-CI-1000 | C-541CR-CI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | LV Cable Laying | Back Filling for LV Cable | C-541CR-EI-1000 | C-541CR-CI-1020 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | Instrument Cable Laying | Back Filling for Instrument Cable | C-541CR-EI-1010 | C-541CR-CI-1030 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.3.1.9.12.3.1 Control System Modifications and Telecommunication WorksCCOC541IC2 | Glanding & Termination | Telecommunication Works (Modification of Existing Telecom Cabinet) | C-541CR-EI-1040 | C-541CR-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | LV Cable Trenching | LV Cable Trenching | C-MAQTA-CI-1800 | C-541CR-CI-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.10.12.1.1 Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB BuildingCCOU577CS5 | P2543-R01-Oct24..4.3.1.10.12.2.1 Telecommunication Works (new telecom cabinet and cable laying and terminations)CCOU577IC1 | Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB Building | Telecommunication Works (new telecom cabinet and cable laying and terminations) | C-577-CI-1000 | C-577-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.10.12.2.1 Telecommunication Works (new telecom cabinet and cable laying and terminations)CCOU577IC1 | P2543-R01-Oct24..4.3.1.10.12.1.2 Backfilling - 577-SV-02 Passive cooling Shelter to HGCP - MCB BuildingCCOU57CS10 | Telecommunication Works (new telecom cabinet and cable laying and terminations) | Backfilling - 577-SV-02 Passive cooling Shelter to HGCP - MCB Building | C-577-TE-1000 | C-577-CI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.11.12.1.1 Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS1 | P2543-R01-Oct24..4.3.1.11.12.2.1 Telecommunication Works (modifications of existing telecom cabinet)CCOU601IC1 | Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603) | Telecommunication Works (modifications of existing telecom cabinet) | C-601-CI-1000 | C-601-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.11.12.2.1 Telecommunication Works (modifications of existing telecom cabinet)CCOU601IC1 | P2543-R01-Oct24..4.3.1.11.12.1.2 Backfilling - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS2 | Telecommunication Works (modifications of existing telecom cabinet) | Backfilling - Tahammama-C E&I Building to Launcher Station (607-V-603) | C-601-TE-1000 | C-601-CI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.3.1.10.12.1.1 Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB BuildingCCOU577CS5 | Instrument Trenching | Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB Building | C-541CR-CI-1010 | C-577-CI-1000 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.10.12.1.1 Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB BuildingCCOU577CS5 | P2543-R01-Oct24..4.3.1.11.12.1.1 Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS1 | Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB Building | Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603) | C-577-CI-1000 | C-601-CI-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.9 Thrust Anchor BlockCCOHBCS210 | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Concrete Works for Thrust Anchor Block | Precommissioning | C-56-PL-607-CI-1510 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.13 Backfilling for CablesCCOHBCS212 | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Back Filling for Electrical & Earthing Cable | Precommissioning | C-56-PL-607-CI-2800 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.13 Backfilling for CablesCCOHBCS212 | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Back Filling for Instrument & Telecom Cable | Precommissioning | C-56-PL-607-CI-2810 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.14 Paving WorksCCOHBCS208 | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Paving of Interlock tiles & Kerb Stone Embankment | Precommissioning | C-56-PL-607-CI-2600 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS304 | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Pre-Fabrication & Installation of Platforms & Crossovers | Precommissioning | C-56-PL-607-CI-3000 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS304 | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Precommissioning | C-56-PL-607-CI-3010 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.3.1 Installation of Pig Launcher (607-V-603)CCOHBME303 | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Installation of Pig Launcher (607-V-603) 56" | Precommissioning | C-56-PL-607-ME-1000 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Final Bolt Torquing/ Re-Instatement | Precommissioning | C-56-PL-607-PI-2000 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.5.1 Pig Launcher 607-V-603 56'' Pipeline/Piping Hook-upCCOHBPI312 | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Ext. Coating for Weld Joint | Precommissioning | C-56-PL-607-PL-1030 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Glanding & Termination | Precommissioning | C-56-PL-607-EI-2050 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Loop Checking for Instruments | Precommissioning | C-56-PL-607-EI-2040 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Glanding & Termination for CP S/m | Precommissioning | C-56-PL-607-CA-1030 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | FO Cable OTDR Testing & Splicing | Precommissioning | C-56-PL-607-TE-1420 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.5 Finishing WorksCCOHBCS116 | P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | External Finishing Works | Precommissioning | C-56-EB2-CI-1800 | PRECOM-56-EB2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.5 Finishing WorksCCOHBCS116 | P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | Internal Finishing Works | Precommissioning | C-56-EB2-CI-1810 | PRECOM-56-EB2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.6 Metal WorksCCOHBCS117 | P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | Steel Structural Works | Precommissioning | C-56-EB2-CI-2000 | PRECOM-56-EB2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.1.7 Paving WorksCCOHBCS118 | P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | Paving Works | Precommissioning | C-56-EB2-CI-2010 | PRECOM-56-EB2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | HVAC Works | Precommissioning | C-56-EB2-ME-1010 | PRECOM-56-EB2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | Plumbing Works | Precommissioning | C-56-EB2-ME-1000 | PRECOM-56-EB2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | Glanding & Termination | Precommissioning | C-56-EB2-EI-1230 | PRECOM-56-EB2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.4.2 Telecom System (Including subcontract for FOC Splicing / Termination / Testing)CCOHBIC241 | P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | Telecom System (Including subcontract for FOC Splicing / Termination / Testing) | Precommissioning | C-56-EB2-TE-1400 | PRECOM-56-EB2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.4.3 Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOHBIC251 | P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | Security System (Including subcontract for FOC Splicing / Termination / Testing ) | Precommissioning | C-56-EB2-TE-1610 | PRECOM-56-EB2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.5.1 Shutdown Connection to Existing Substation Unit 607CCOHBST204 | P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | Termination & Connection with Existing Power Distribution Network | Precommissioning | C-56-EB2-EL-1600 | PRECOM-56-EB2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.40.7 Paving WorksCCOHBCS305 | P2543-R01-Oct24..4.3.2.1.8.3.1 PrecommissioningCPC-HBS502 | Paving of Interlock tiles & Kerb Stone Embankment | Precommissioning | C-56-G-HT-CI-2600 | PRECOM-56-G-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | P2543-R01-Oct24..4.3.2.1.8.3.1 PrecommissioningCPC-HBS502 | Final Bolt Torquing/ Re-Instatement | Precommissioning | C-56-G-HT-PI-2000 | PRECOM-56-G-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.3.6 Isolation of Hot Tap JointCCOHBHT315 | P2543-R01-Oct24..4.3.2.1.8.3.1 PrecommissioningCPC-HBS502 | Isolation of Hot Tap Joint | Precommissioning | C-56-G-HT101-ME-1050 | PRECOM-56-G-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.4.6 Isolation of Hot Tap JointCCOHBHT375 | P2543-R01-Oct24..4.3.2.1.8.3.1 PrecommissioningCPC-HBS502 | Isolation of Hot Tap Joint | Precommissioning | C-56-G-HT102-ME-1050 | PRECOM-56-G-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.5.6 Isolation of Hot Tap JointCCOHBHT435 | P2543-R01-Oct24..4.3.2.1.8.3.1 PrecommissioningCPC-HBS502 | Isolation of Hot Tap Joint | Precommissioning | C-56-G-HT103-ME-1050 | PRECOM-56-G-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.6.1 Tie-insCCOHBPI311 | P2543-R01-Oct24..4.3.2.1.8.3.1 PrecommissioningCPC-HBS502 | Tie-In with 30" Pipeline | Precommissioning | C-56-G-HT-ME-2000 | PRECOM-56-G-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Padding | Precommissioning | C-56-01HG-PL-CI-6000 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.1 Evaporation PondCCOPL56239 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Evaporation Pond | Precommissioning | C-56-01HG-PL-CI-7200 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.3 Dewatering, Swabbing, & DryingCCOPL56235 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Swabing & Drying (Upto Dew Point Temp.) | Precommissioning | C-56-01HG-PL-ME-7620 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | CIP/DCVG Survey (Pre-Com) | Precommissioning | C-56-01HG-PL-CA-5250 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Gatch Compaction | Precommissioning | C-56-01HG-PL-CI-6810 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.4 ROW Restoration/Marker Post/Crash BarrierCCOPL56229 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Installation of Crash Barriers (If any) | Precommissioning | C-56-01HG-PL-CI-7810 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Termination/Splicing @ BVS | Precommissioning | C-56-01HG-PL-TE-8210 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.20 Padding from Habshan complex to KP 6CCOPL56211.1 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Padding | Precommissioning | C-56-HC01-PL-CI-6000 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.5 Evaporation PondCCOPL56225 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Evaporation Pond | Precommissioning | C-56-HC01-PL-CI-7200 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.7 Dewatering, Swabbing, & DryingCCOPL56227 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Swabing & Drying (Upto Dew Point Temp.) | Precommissioning | C-56-HC01-PL-ME-7620 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | CIP/DCVG Survey | Precommissioning | C-56-HC01-PL-CA-5250 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Gatch Compaction | Precommissioning | C-56-HC01-PL-CI-6810 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Installation of Crash Barriers (If any) | Precommissioning | C-56-HC01-PL-CI-7810 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Termination/Splicing @ BVS | Precommissioning | C-56-HC01-PL-TE-8210 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.12 Thrust Anchor Block/ Impact WallCCOH56CS33 | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Concrete Works for Thrust Anchor Block | Precommissioning | C-56-PR-838-CI-1510 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.12 Thrust Anchor Block/ Impact WallCCOH56CS33 | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Concrete Works for Impact Wall | Precommissioning | C-56-PR-838-CI-1500 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.15 Backfilling for Cables CCOH56CS36 | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Back Filling for Electrical & Earthing Cable | Precommissioning | C-56-PR-838-CI-2800 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.15 Backfilling for Cables CCOH56CS36 | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Back Filling for Instrument & Telecom Cable | Precommissioning | C-56-PR-838-CI-2810 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.16 Paving Works CCOH56CS37 | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Paving of Interlock tiles & Kerb Stone Embankment | Precommissioning | C-56-PR-838-CI-2600 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.18 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOH56SS51 | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Pre-Fabrication & Installation of Platforms & Crossovers | Precommissioning | C-56-PR-838-CI-3000 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.18 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOH56SS51 | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Precommissioning | C-56-PR-838-CI-3010 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.3.19 Installation of Pig Receiver (838-V-601) CCOH56ME50 | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Installation of Pig Receiver (838-V-601) 56" | Precommissioning | C-56-PR-838-ME-1100 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Final Bolt Torquing/ Re-Instatement | Precommissioning | C-56-PR-838-PI-2000 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.5.34 Pig Receiver 838-V-601 56'' Pipeline/ Piping Hook-up CCOH56PI51 | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Ext. Coating for Weld Joint | Precommissioning | C-56-PR-838-PL-1030 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Glanding & Termination | Precommissioning | C-56-PR-838-EI-2050 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Loop Checking for Instruments | Precommissioning | C-56-PR-838-EI-2040 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0