P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Glanding & Termination for CP S/m | Precommissioning | C-56-PR-838-CA-1030 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.8.33 CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) CCOH56IC30 | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | FO Cable OTDR Testing & Splicing | Precommissioning | C-56-PR-838-TE-1420 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.16 Backfilling for Cables CCOB156C37 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Back Filling for Electrical & Earthing Cable | Precommissioning | C-56-591-01-CI-2800 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.16 Backfilling for Cables CCOB156C37 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Back Filling for Instrument & Telecom Cable | Precommissioning | C-56-591-01-CI-2810 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.12 Fences & Gates Construction CCOB156C31 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Installation of Fence Post & Mesh Works (Type-4 & 3) | Precommissioning | C-56-591-01-CI-2220 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.12 Fences & Gates Construction CCOB156C31 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | Precommissioning | C-56-591-01-CI-2230 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.15 Paving Works CCOB156C35 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Paving of Interlock tiles & Kerb Stone Embankment | Precommissioning | C-56-591-01-CI-2600 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.15 Paving Works CCOB156C35 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Rip-Rap Protection Laying | Precommissioning | C-56-591-01-CI-2610 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.19 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOB156S54 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Precommissioning | C-56-591-01-CI-3010 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.3.9 Mechanical Works and Equipment Installation (Fire Fighting Equipment) CCOB156M50 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | Precommissioning | C-56-591-01-ME-1000 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Final Bolt Torquing/ Re-Instatement | Precommissioning | C-56-591-01-PI-2000 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Installation of Pig Signaller | Precommissioning | C-56-591-01-PL-1080 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Padding & Backfilling | Precommissioning | C-56-591-01-PL-1090 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Loop Checking for Instruments | Precommissioning | C-56-591-01-EI-2040 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Glanding & Termination | Precommissioning | C-56-591-01-EI-2050 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Installation of CP S/m | Precommissioning | C-56-591-01-CA-1020 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.7 Fences & Gates ConstructionCCOB652C39 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Installation of Fence Post & Mesh Works (Type-4 & 3) | Precommissioning BVS-1 | C-52-598-01-CI-2220 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.10 Backfilling for CablesCCOB652C41 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Back Filling for Electrical & Earthing Cable | Precommissioning BVS-1 | C-52-598-01-CI-2800 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.10 Backfilling for CablesCCOB652C41 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Back Filling for Instrument & Telecom Cable | Precommissioning BVS-1 | C-52-598-01-CI-2810 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.7 Fences & Gates ConstructionCCOB652C39 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | Precommissioning BVS-1 | C-52-598-01-CI-2230 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.9 Paving WorksCCOB652C42 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Paving of Interlock tiles & Kerb Stone Embankment | Precommissioning BVS-1 | C-52-598-01-CI-2600 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.9 Paving WorksCCOB652C42 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Rip-Rap Protection Laying | Precommissioning BVS-1 | C-52-598-01-CI-2610 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB652S56 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Precommissioning BVS-1 | C-52-598-01-CI-3010 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB652S56 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Pre-Fabrication & Installation of Platforms & Crossovers | Precommissioning BVS-1 | C-52-598-01-CI-3000 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB652M52 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | Precommissioning BVS-1 | C-52-598-01-ME-1000 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Final Bolt Torquing/ Re-Instatement | Precommissioning BVS-1 | C-52-598-01-PI-2000 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Installation of ROV | Precommissioning BVS-1 | C-52-598-01-PL-1060 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Padding & Backfilling | Precommissioning BVS-1 | C-52-598-01-PL-1090 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Installation of Pig Signaller | Precommissioning BVS-1 | C-52-598-01-PL-1080 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Loop Checking for Instruments | Precommissioning BVS-1 | C-52-598-01-EI-2040 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Glanding & Termination | Precommissioning BVS-1 | C-52-598-01-EI-2050 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.5 Light Pole, Lighting & FixturesCCOB652E85 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Installation of Light Pole, Lighting & Fixtures | Precommissioning BVS-1 | C-52-598-01-EI-1800 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.5 Light Pole, Lighting & FixturesCCOB652E85 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Installation of Lighting & Instrument JB's | Precommissioning BVS-1 | C-52-598-01-EI-1810 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.7.1 CP Anode Bed Installation (subcontract)CCOB652E30 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Installation of CP S/m | Precommissioning BVS-1 | C-52-598-01-CA-1020 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.22 PaddingCCOPL52330 | P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | Padding | Pre-commissioning from BVS-02 to BVS-01 | C-52-0102-PL-CI-6000 | PRECOM-52-0201-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.1.1 Evaporation PondCCOPL52347 | P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | Evaporation Pond | Pre-commissioning from BVS-02 to BVS-01 | C-52-0102-PL-CI-7200 | PRECOM-52-0201-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.1.3 Dewatering, Swabbing, & DryingCCOPL52342 | P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | Swabing & Drying (Upto Dew Point Temp.) | Pre-commissioning from BVS-02 to BVS-01 | C-52-0102-PL-ME-7620 | PRECOM-52-0201-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | Gatch Compaction | Pre-commissioning from BVS-02 to BVS-01 | C-52-0102-PL-CI-6810 | PRECOM-52-0201-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | Installation of Crash Barriers (If any) | Pre-commissioning from BVS-02 to BVS-01 | C-52-0102-PL-CI-7810 | PRECOM-52-0201-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.3 Re-Instatement of Entry & Exit PitCCOPL58212 | P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from BVS-02 to BVS-01 | C-52-0102-CNH10-1800 | PRECOM-52-0201-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.2.3 Re-Instatement of Entry & Exit PitCCOPL58272 | P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from BVS-02 to BVS-01 | C-52-0102-CNH09-1800 | PRECOM-52-0201-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.3.3 Re-Instatement of Entry & Exit PitCCOPL58332 | P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from BVS-02 to BVS-01 | C-52-0102-CNH08-1800 | PRECOM-52-0201-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.4.5 Re-Instatement of Entry & Exit PitCCOPL57322 | P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from BVS-02 to BVS-01 | C-52-0102-CNM07-1800 | PRECOM-52-0201-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.6.5 Re-Instatement of Entry & Exit PitCCOPL58032 | P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from BVS-02 to BVS-01 | C-52-0102-CNM05-1800 | PRECOM-52-0201-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | CIP/DCVG Survey | Pre-commissioning from BVS-02 to BVS-01 | C-52-0102-PL-CA-5250 | PRECOM-52-0201-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.5.1 Telecom Works along PipelineCCOP52IC52 | P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | Termination/Splicing @ BVS | Pre-commissioning from BVS-02 to BVS-01 | C-52-0102-PL-TE-8210 | PRECOM-52-0201-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.11 Backfilling for CablesCCOH52CS37 | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | Back Filling for Electrical & Earthing Cable | Precommissioning Pig Launcher 838-V-602 | C-52-PL-838-CI-2800 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.10 Paving WorksCCOH52CS36 | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | Paving of Interlock tiles & Kerb Stone Embankment | Precommissioning Pig Launcher 838-V-602 | C-52-PL-838-CI-2600 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.11 Backfilling for CablesCCOH52CS37 | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | Back Filling for Instrument & Telecom Cable | Precommissioning Pig Launcher 838-V-602 | C-52-PL-838-CI-2810 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.5 Thrust Anchor BlockCCOH52SS32 | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | Concrete Works for Thrust Anchor Block | Precommissioning Pig Launcher 838-V-602 | C-52-PL-838-CI-1510 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOH52SS61 | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | Pre-Fabrication & Installation of Platforms & Crossovers | Precommissioning Pig Launcher 838-V-602 | C-52-PL-838-CI-3000 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOH52SS61 | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Precommissioning Pig Launcher 838-V-602 | C-52-PL-838-CI-3010 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.3.1 Installation of Pig Launcher (838-V-602)CCOH52ME60 | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | Installation of Pig Launcher (838-V-602) 52" | Precommissioning Pig Launcher 838-V-602 | C-52-PL-838-ME-1000 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | Final Bolt Torquing/ Re-Instatement | Precommissioning Pig Launcher 838-V-602 | C-52-PL-838-PI-2000 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.5.1 Pig Launcher 838-V-602 52'' Pipeline/Piping Hook-upCCOH52PI70 | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | Ext. Coating for Weld Joint | Precommissioning Pig Launcher 838-V-602 | C-52-PL-838-PL-1030 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | Loop Checking for Instruments | Precommissioning Pig Launcher 838-V-602 | C-52-PL-838-EI-2040 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | Glanding & Termination | Precommissioning Pig Launcher 838-V-602 | C-52-PL-838-EI-2050 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.7.1 CP Anode Bed Installation (subcontract)CCOH52EL52 | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | Glanding & Termination for CP S/m | Precommissioning Pig Launcher 838-V-602 | C-52-PL-838-CA-1030 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.8.2 CCTV System (Including subcontract for FOC Splicing / Termination / Testing )CCOH52IC73 | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | FO Cable OTDR Testing & Splicing | Precommissioning Pig Launcher 838-V-602 | C-52-PL-838-TE-1420 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | Padding -Lot1 | Pre-commissioning from HGCP to BVS-01 | C-52-HG01-PL-CI-6000 | PRECOM-52-HG01-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2.1 Evaporation PondCCOPL52319 | P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | Evaporation Pond | Pre-commissioning from HGCP to BVS-01 | C-52-HG01-PL-CI-7200 | PRECOM-52-HG01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2.3 Dewatering, Swabbing, & DryingCCOPL52326 | P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | Swabing & Drying (Upto Dew Point Temp.) | Pre-commissioning from HGCP to BVS-01 | C-52-HG01-PL-ME-7620 | PRECOM-52-HG01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.27 BermingCCOPL52316 | P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | Gatch Compaction | Pre-commissioning from HGCP to BVS-01 | C-52-HG01-PL-CI-6810 | PRECOM-52-HG01-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2.5 ROW Restoration from BVS-01 to HGCP/Crash BarrierCCOPL52324.2 | P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | Installation of Crash Barriers (If any) | Pre-commissioning from HGCP to BVS-01 | C-52-HG01-PL-CI-7810 | PRECOM-52-HG01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57712 | P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from HGCP to BVS-01 | C-52-HG01-CNM03-1800 | PRECOM-52-HG01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.3.5 Re-Instatement of Entry & Exit PitCCOPL58072 | P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from HGCP to BVS-01 | C-52-HG01-CNM02-1800 | PRECOM-52-HG01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.4.5 Re-Instatement of Entry & Exit PitCCOPL58112 | P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from HGCP to BVS-01 | C-52-HG01-CNM01-1800 | PRECOM-52-HG01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | CIP/DCVG Survey (Pre-Com) | Pre-commissioning from HGCP to BVS-01 | C-52-HG01-PL-CA-5250 | PRECOM-52-HG01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.4.1 Telecom Works along Pipeline CCOP52IC57 | P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | Termination/Splicing @ BVS | Pre-commissioning from HGCP to BVS-01 | C-52-HG01-PL-TE-8210 | PRECOM-52-HG01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.7 Fences & Gates ConstructionCCOB552C38 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Installation of Fence Post & Mesh Works (Type-4 & 3) | Precommissioning BVS-2 | C-52-598-02-CI-2220 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.10 Backfilling for CablesCCOB552C56 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Back Filling for Electrical & Earthing Cable | Precommissioning BVS-2 | C-52-598-02-CI-2800 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.7 Fences & Gates ConstructionCCOB552C38 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | Precommissioning BVS-2 | C-52-598-02-CI-2230 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.10 Backfilling for CablesCCOB552C56 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Back Filling for Instrument & Telecom Cable | Precommissioning BVS-2 | C-52-598-02-CI-2810 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.9 Paving WorksCCOB552C39 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Paving of Interlock tiles & Kerb Stone Embankment | Precommissioning BVS-2 | C-52-598-02-CI-2600 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.9 Paving WorksCCOB552C39 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Rip-Rap Protection Laying | Precommissioning BVS-2 | C-52-598-02-CI-2610 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Precommissioning BVS-2 | C-52-598-02-CI-3010 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Pre-Fabrication & Installation of Platforms & Crossovers | Precommissioning BVS-2 | C-52-598-02-CI-3000 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB552M52 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | Precommissioning BVS-2 | C-52-598-02-ME-1000 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB552P101 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Final Bolt Torquing/ Re-Instatement | Precommissioning BVS-2 | C-52-598-02-PI-2000 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Installation of Pig Signaller | Precommissioning BVS-2 | C-52-598-02-PL-1080 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Ext. Coating for Tie-in Joint | Precommissioning BVS-2 | C-52-598-02-PL-1040 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Loop Checking for Instruments | Precommissioning BVS-2 | C-52-598-02-EI-2040 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Glanding & Termination | Precommissioning BVS-2 | C-52-598-02-EI-2050 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Installation of CP S/m | Precommissioning BVS-2 | C-52-598-02-CA-1020 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | P2543-R01-Oct24..4.3.2.3.5.8.2 Pre-commissioning from BVS-02 to BVS-03CPCPL52327.5 | Padding | Pre-commissioning from BVS-02 to BVS-03 | C-52-0203-PL-CI-6000 | PRECOM-52-0203-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2.1 Evaporation PondCCOPL52375 | P2543-R01-Oct24..4.3.2.3.5.8.2 Pre-commissioning from BVS-02 to BVS-03CPCPL52327.5 | Evaporation Pond | Pre-commissioning from BVS-02 to BVS-03 | C-52-0203-PL-CI-7200 | PRECOM-52-0203-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2.3 Dewatering, Swabbing, & DryingCCOPL52370 | P2543-R01-Oct24..4.3.2.3.5.8.2 Pre-commissioning from BVS-02 to BVS-03CPCPL52327.5 | Swabing & Drying (Upto Dew Point Temp.) | Pre-commissioning from BVS-02 to BVS-03 | C-52-0203-PL-ME-7620 | PRECOM-52-0203-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | P2543-R01-Oct24..4.3.2.3.5.8.2 Pre-commissioning from BVS-02 to BVS-03CPCPL52327.5 | Gatch Compaction | Pre-commissioning from BVS-02 to BVS-03 | C-52-0203-PL-CI-6810 | PRECOM-52-0203-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.5 Marker Post & Crash Barrier | P2543-R01-Oct24..4.3.2.3.5.8.2 Pre-commissioning from BVS-02 to BVS-03CPCPL52327.5 | Installation of Crash Barriers (If any) | Pre-commissioning from BVS-02 to BVS-03 | C-52-0203-PL-CI-7810 | PRECOM-52-0203-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | P2543-R01-Oct24..4.3.2.3.5.8.2 Pre-commissioning from BVS-02 to BVS-03CPCPL52327.5 | CIP/DCVG Survey | Pre-commissioning from BVS-02 to BVS-03 | C-52-0203-PL-CA-5250 | PRECOM-52-0203-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | P2543-R01-Oct24..4.3.2.3.5.8.2 Pre-commissioning from BVS-02 to BVS-03CPCPL52327.5 | Termination/Splicing @ BVS | Pre-commissioning from BVS-02 to BVS-03 | C-52-0203-PL-TE-8210 | PRECOM-52-0203-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.7 Paving WorksCCOB452C38 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Paving of Interlock tiles & Kerb Stone Embankment | Precommissioning BVS-3 | C-52-598-03-CI-2600 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.7 Paving WorksCCOB452C38 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Rip-Rap Protection Laying | Precommissioning BVS-3 | C-52-598-03-CI-2610 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.10 Backfilling for CablesCCOB452C40 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Back Filling for Electrical & Earthing Cable | Precommissioning BVS-3 | C-52-598-03-CI-2800 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.10 Backfilling for CablesCCOB452C40 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Back Filling for Instrument & Telecom Cable | Precommissioning BVS-3 | C-52-598-03-CI-2810 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.8 Fences & Gates ConstructionCCOB452C37 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Installation of Fence Post & Mesh Works (Type-4 & 3) | Precommissioning BVS-3 | C-52-598-03-CI-2220 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.8 Fences & Gates ConstructionCCOB452C37 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | Precommissioning BVS-3 | C-52-598-03-CI-2230 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB452S52 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Precommissioning BVS-3 | C-52-598-03-CI-3010 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB452S52 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Pre-Fabrication & Installation of Platforms & Crossovers | Precommissioning BVS-3 | C-52-598-03-CI-3000 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB452M51 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | Precommissioning BVS-3 | C-52-598-03-ME-1000 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB452P101 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Final Bolt Torquing/ Re-Instatement | Precommissioning BVS-3 | C-52-598-03-PI-2000 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Installation of Pig Signaller | Precommissioning BVS-3 | C-52-598-03-PL-1080 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Padding & Backfilling | Precommissioning BVS-3 | C-52-598-03-PL-1090 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Loop Checking for Instruments | Precommissioning BVS-3 | C-52-598-03-EI-2040 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Glanding & Termination | Precommissioning BVS-3 | C-52-598-03-EI-2050 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Deep Earth Well Drilling | Precommissioning BVS-3 | C-52-598-03-EI-1400 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.7.1 CP Anode Bed Installation (subcontract)CCOB452E30 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Installation of CP S/m | Precommissioning BVS-3 | C-52-598-03-CA-1020 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.5 Fences & Gates ConstructionCCOH52CS42 | P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | Installation of Fence Post & Mesh Works (Type-3) | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | C-52-IDS1-CI-2220 | PRECOM-52-IDS1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.5 Fences & Gates ConstructionCCOH52CS42 | P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | Installation of Access Gate | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | C-52-IDS1-CI-2230 | PRECOM-52-IDS1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.7 Paving WorksCCOH52CS44 | P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | Paving of Interlock tiles & Kerb Stone Embankment | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | C-52-IDS1-CI-2600 | PRECOM-52-IDS1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.8 Backfilling for CablesCCOH52CS45 | P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | Back Filling for Electrical & Earthing Cable | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | C-52-IDS1-CI-2800 | PRECOM-52-IDS1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.8 Backfilling for CablesCCOH52CS45 | P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | Back Filling for Instrument & Telecom Cable | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | C-52-IDS1-CI-2810 | PRECOM-52-IDS1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | Glanding & Termination | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | C-52-IDS1-EI-2050 | PRECOM-52-IDS1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | Padding | Pre-commissioning from BVS-03 to BVS-04 | C-52-0304-PL-CI-6000 | PRECOM-52-0304-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.3.1 Evaporation PondCCOPL52403 | P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | Evaporation Pond | Pre-commissioning from BVS-03 to BVS-04 | C-52-0304-PL-CI-7200 | PRECOM-52-0304-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.3.3 Dewatering, Swabbing, & DryingCCOPL52398 | P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | Swabing & Drying (Upto Dew Point Temp.) | Pre-commissioning from BVS-03 to BVS-04 | C-52-0304-PL-ME-7620 | PRECOM-52-0304-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | Gatch Compaction | Pre-commissioning from BVS-03 to BVS-04 | C-52-0304-PL-CI-6810 | PRECOM-52-0304-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | Installation of Crash Barriers (If any) | Pre-commissioning from BVS-03 to BVS-04 | C-52-0304-PL-CI-7810 | PRECOM-52-0304-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | CIP/DCVG Survey | Pre-commissioning from BVS-03 to BVS-04 | C-52-0304-PL-CA-5250 | PRECOM-52-0304-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | Termination/Splicing @ BVS | Pre-commissioning from BVS-03 to BVS-04 | C-52-0304-PL-TE-8210 | PRECOM-52-0304-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Installation of Fence Post & Mesh Works (Type-4 & 3) | Precommissioning BVS-4 | C-52-598-04-CI-2220 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | Precommissioning BVS-4 | C-52-598-04-CI-2230 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Paving of Interlock tiles & Kerb Stone Embankment | Precommissioning BVS-4 | C-52-598-04-CI-2600 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.9 Backfilling for CablesCCOB352C39 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Back Filling for Electrical & Earthing Cable | Precommissioning BVS-4 | C-52-598-04-CI-2800 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Rip-Rap Protection Laying | Precommissioning BVS-4 | C-52-598-04-CI-2610 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.9 Backfilling for CablesCCOB352C39 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Back Filling for Instrument & Telecom Cable | Precommissioning BVS-4 | C-52-598-04-CI-2810 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.10 Platforms & BollardsCCOB352S52 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Pre-Fabrication & Installation of Platforms & Crossovers | Precommissioning BVS-4 | C-52-598-04-CI-3000 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.10 Platforms & BollardsCCOB352S52 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Precommissioning BVS-4 | C-52-598-04-CI-3010 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB352M51 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | Precommissioning BVS-4 | C-52-598-04-ME-1000 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB352P101 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Final Bolt Torquing/ Re-Instatement | Precommissioning BVS-4 | C-52-598-04-PI-2000 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Installation of Pig Signaller | Precommissioning BVS-4 | C-52-598-04-PL-1080 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Ext. Coating for Tie-in Joint | Precommissioning BVS-4 | C-52-598-04-PL-1040 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Loop Checking for Instruments | Precommissioning BVS-4 | C-52-598-04-EI-2040 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Glanding & Termination | Precommissioning BVS-4 | C-52-598-04-EI-2050 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Deep Earth Well Drilling | Precommissioning BVS-4 | C-52-598-04-EI-1400 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Installation of CP S/m | Precommissioning BVS-4 | C-52-598-04-CA-1020 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.5 Fences & Gates ConstructionCCOH52CS50 | P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | Installation of Fence Post & Mesh Works (Type-3) | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | C-52-IDS2-CI-2220 | PRECOM-52-IDS2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.7 Paving WorksCCOH52CS52 | P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | Paving of Interlock tiles & Kerb Stone Embankment | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | C-52-IDS2-CI-2600 | PRECOM-52-IDS2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | Installation of CCTV Poles | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | C-52-IDS2-TE-1590 | PRECOM-52-IDS2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.5 Fences & Gates ConstructionCCOH52CS50 | P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | Installation of Access Gate | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | C-52-IDS2-CI-2230 | PRECOM-52-IDS2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.8 Backfilling for CablesCCOH52CS53 | P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | Back Filling for Electrical & Earthing Cable | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | C-52-IDS2-CI-2800 | PRECOM-52-IDS2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.8 Backfilling for CablesCCOH52CS53 | P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | Back Filling for Instrument & Telecom Cable | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | C-52-IDS2-CI-2810 | PRECOM-52-IDS2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | Glanding & Termination | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | C-52-IDS2-EI-2050 | PRECOM-52-IDS2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | Padding | Pre-commissioning from BVS-04 to BVS-05 | C-52-0405-PL-CI-6000 | PRECOM-52-0405-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.3.1 Evaporation PondCCOPL52431 | P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | Evaporation Pond | Pre-commissioning from BVS-04 to BVS-05 | C-52-0405-PL-CI-7200 | PRECOM-52-0405-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.3.3 Dewatering, Swabbing, & DryingCCOPL52426 | P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | Swabing & Drying (Upto Dew Point Temp.) | Pre-commissioning from BVS-04 to BVS-05 | C-52-0405-PL-ME-7620 | PRECOM-52-0405-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | Gatch Compaction | Pre-commissioning from BVS-04 to BVS-05 | C-52-0405-PL-CI-6810 | PRECOM-52-0405-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | Installation of Crash Barriers (If any) | Pre-commissioning from BVS-04 to BVS-05 | C-52-0405-PL-CI-7810 | PRECOM-52-0405-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57132 | P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from BVS-04 to BVS-05 | C-52-0405-CNM17-1800 | PRECOM-52-0405-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.3.5 Re-Instatement of Entry & Exit PitCCOPL57792 | P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from BVS-04 to BVS-05 | C-52-0405-CNM18-1800 | PRECOM-52-0405-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.3 Re-Instatement of Entry & Exit PitCCOPL58152 | P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from BVS-04 to BVS-05 | C-52-0405-CNH19-1800 | PRECOM-52-0405-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.3 Re-Instatement of Entry & Exit PitCCOPL58312 | P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from BVS-04 to BVS-05 | C-52-0405-CNH20-1800 | PRECOM-52-0405-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.6.5 Re-Instatement of Entry & Exit PitCCOPL57752 | P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from BVS-04 to BVS-05 | C-52-0405-CNM23-1800 | PRECOM-52-0405-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.7.3 Re-Instatement of Entry & Exit PitCCOPL58252 | P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from BVS-04 to BVS-05 | C-52-0405-CNH24-1800 | PRECOM-52-0405-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | CIP/DCVG Survey | Pre-commissioning from BVS-04 to BVS-05 | C-52-0405-PL-CA-5250 | PRECOM-52-0405-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | Termination/Splicing @ BVS | Pre-commissioning from BVS-04 to BVS-05 | C-52-0405-PL-TE-8210 | PRECOM-52-0405-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.10 Backfilling for CablesCCOB252C40 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Back Filling for Electrical & Earthing Cable | Precommissioning BVS-5 | C-52-598-05-CI-2800 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.10 Backfilling for CablesCCOB252C40 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Back Filling for Instrument & Telecom Cable | Precommissioning BVS-5 | C-52-598-05-CI-2810 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.9 Paving WorksCCOB252C35 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Rip-Rap Protection Laying | Precommissioning BVS-5 | C-52-598-05-CI-2610 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.9 Paving WorksCCOB252C35 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Paving of Interlock tiles & Kerb Stone Embankment | Precommissioning BVS-5 | C-52-598-05-CI-2600 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.7 Fences & Gates ConstructionCCOB252C36 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | Precommissioning BVS-5 | C-52-598-05-CI-2230 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.7 Fences & Gates ConstructionCCOB252C36 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Installation of Fence Post & Mesh Works (Type-4 & 3) | Precommissioning BVS-5 | C-52-598-05-CI-2220 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB252S51 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Pre-Fabrication & Installation of Platforms & Crossovers | Precommissioning BVS-5 | C-52-598-05-CI-3000 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB252S51 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Precommissioning BVS-5 | C-52-598-05-CI-3010 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB252M50 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | Precommissioning BVS-5 | C-52-598-05-ME-1000 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Final Bolt Torquing/ Re-Instatement | Precommissioning BVS-5 | C-52-598-05-PI-2000 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Installation of Pig Signaller | Precommissioning BVS-5 | C-52-598-05-PL-1080 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Ext. Coating for Tie-in Joint | Precommissioning BVS-5 | C-52-598-05-PL-1040 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Loop Checking for Instruments | Precommissioning BVS-5 | C-52-598-05-EI-2040 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Glanding & Termination | Precommissioning BVS-5 | C-52-598-05-EI-2050 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Deep Earth Well Drilling | Precommissioning BVS-5 | C-52-598-05-EI-1400 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.7.1 CP Anode Bed Installation (subcontract)CCOB252E30 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Installation of CP S/m | Precommissioning BVS-5 | C-52-598-05-CA-1020 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | P2543-R01-Oct24..4.3.2.3.2.8.4 Precommissioning DEL/TFP PipelineCPCHGCP522 | Concrete Works for Hot Tap Tie in Pit | Precommissioning DEL/TFP Pipeline | C-52-D-HT-CI-1480 | PRECOM-52-D-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | P2543-R01-Oct24..4.3.2.3.2.8.4 Precommissioning DEL/TFP PipelineCPCHGCP522 | Concrete Works for Access Platforms & Misc. Structural Foundations | Precommissioning DEL/TFP Pipeline | C-52-D-HT-CI-1420 | PRECOM-52-D-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.7 Paving WorksCCOSWCS316 | P2543-R01-Oct24..4.3.2.3.2.8.4 Precommissioning DEL/TFP PipelineCPCHGCP522 | Paving of Interlock tiles & Kerb Stone Embankment (Including Fence Re-Instatement) | Precommissioning DEL/TFP Pipeline | C-52-D-HT-CI-2600 | PRECOM-52-D-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.2.6 Final Bolt Torquing/ Re-InstatementCCOSWPI564 | P2543-R01-Oct24..4.3.2.3.2.8.4 Precommissioning DEL/TFP PipelineCPCHGCP522 | Final Bolt Torquing/ Re-Instatement | Precommissioning DEL/TFP Pipeline | C-52-D-HT-PI-2000 | PRECOM-52-D-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.3.6 Isolation of Hot Tap JointCCOSWHT511 | P2543-R01-Oct24..4.3.2.3.2.8.4 Precommissioning DEL/TFP PipelineCPCHGCP522 | Isolation of Hot Tap Joint | Precommissioning DEL/TFP Pipeline | C-52-D-HT002-ME-1050 | PRECOM-52-D-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.4.1 Tie in works to 52'' and 20'' PipelineCCOSWPI512 | P2543-R01-Oct24..4.3.2.3.2.8.4 Precommissioning DEL/TFP PipelineCPCHGCP522 | Tie-In with 30" Pipeline | Precommissioning DEL/TFP Pipeline | C-52-D-HT-ME-2000 | PRECOM-52-D-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.5 Fences & Gates ConstructionCCOH52CS58 | P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | Installation of Fence Post & Mesh Works (Type-3) | Pre-Commissioning Intrusion Detection KP122 to KP123 | C-52-IDS3-CI-2220 | PRECOM-52-IDS3-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.7 Paving WorksCCOH52CS60 | P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | Paving of Interlock tiles & Kerb Stone Embankment | Pre-Commissioning Intrusion Detection KP122 to KP123 | C-52-IDS3-CI-2600 | PRECOM-52-IDS3-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.5 Fences & Gates ConstructionCCOH52CS58 | P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | Installation of Access Gate | Pre-Commissioning Intrusion Detection KP122 to KP123 | C-52-IDS3-CI-2230 | PRECOM-52-IDS3-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.8 Backfilling for CablesCCOH52CS61 | P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | Back Filling for Electrical & Earthing Cable | Pre-Commissioning Intrusion Detection KP122 to KP123 | C-52-IDS3-CI-2800 | PRECOM-52-IDS3-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.8 Backfilling for CablesCCOH52CS61 | P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | Back Filling for Instrument & Telecom Cable | Pre-Commissioning Intrusion Detection KP122 to KP123 | C-52-IDS3-CI-2810 | PRECOM-52-IDS3-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | Glanding & Termination | Pre-Commissioning Intrusion Detection KP122 to KP123 | C-52-IDS3-EI-2050 | PRECOM-52-IDS3-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | Padding | Pre-commissioning from BVS-05 to BVS-06 | C-52-0506-PL-CI-6000 | PRECOM-52-0506-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.3.1 Evaporation PondCCOPL52459 | P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | Evaporation Pond | Pre-commissioning from BVS-05 to BVS-06 | C-52-0506-PL-CI-7200 | PRECOM-52-0506-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.3.3 Dewatering, Swabbing, & DryingCCOPL52454 | P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | Swabing & Drying (Upto Dew Point Temp.) | Pre-commissioning from BVS-05 to BVS-06 | C-52-0506-PL-ME-7620 | PRECOM-52-0506-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | Gatch Compaction | Pre-commissioning from BVS-05 to BVS-06 | C-52-0506-PL-CI-6810 | PRECOM-52-0506-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | Installation of Crash Barriers (If any) | Pre-commissioning from BVS-05 to BVS-06 | C-52-0506-PL-CI-7810 | PRECOM-52-0506-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.3 Re-Instatement of Entry & Exit PitCCOPL58192 | P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from BVS-05 to BVS-06 | C-52-0506-CNH27-1800 | PRECOM-52-0506-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | CIP/DCVG Survey | Pre-commissioning from BVS-05 to BVS-06 | C-52-0506-PL-CA-5250 | PRECOM-52-0506-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | Termination/Splicing @ BVS | Pre-commissioning from BVS-05 to BVS-06 | C-52-0506-PL-TE-8210 | PRECOM-52-0506-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.8 Fences & Gates ConstructionCCOB152C36 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Installation of Fence Post & Mesh Works (Type-4 & 3) | Precommissioning BVS-6 | C-52-598-06-CI-2220 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.8 Fences & Gates ConstructionCCOB152C36 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Installation of Fence Gates (Main & Emergency Exit) (Type-4 & 3) | Precommissioning BVS-6 | C-52-598-06-CI-2230 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.9 Paving WorksCCOB152C40 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Paving of Interlock tiles & Kerb Stone Embankment | Precommissioning BVS-6 | C-52-598-06-CI-2600 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.9 Paving WorksCCOB152C40 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Rip-Rap Protection Laying | Precommissioning BVS-6 | C-52-598-06-CI-2610 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.11 Backfilling for CablesCCOB152C37 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Back Filling for Electrical & Earthing Cable | Precommissioning BVS-6 | C-52-598-06-CI-2800 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.11 Backfilling for CablesCCOB152C37 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Back Filling for Instrument & Telecom Cable | Precommissioning BVS-6 | C-52-598-06-CI-2810 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.10 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB152S54 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Pre-Fabrication & Installation of Platforms & Crossovers | Precommissioning BVS-6 | C-52-598-06-CI-3000 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.10 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB152S54 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Precommissioning BVS-6 | C-52-598-06-CI-3010 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.7 Fire Point SheltersCCOB152S50 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Installation of Fire Point Shelters | Precommissioning BVS-6 | C-52-598-06-CI-2400 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB152M50 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | Precommissioning BVS-6 | C-52-598-06-ME-1000 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Final Bolt Torquing/ Re-Instatement | Precommissioning BVS-6 | C-52-598-06-PI-2000 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Installation of Pig Signaller | Precommissioning BVS-6 | C-52-598-06-PL-1080 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Ext. Coating for Tie-in Joint | Precommissioning BVS-6 | C-52-598-06-PL-1040 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Loop Checking for Instruments | Precommissioning BVS-6 | C-52-598-06-EI-2040 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Glanding & Termination | Precommissioning BVS-6 | C-52-598-06-EI-2050 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.7.1 CP Anode Bed Installation (subcontract)CCOB152E56 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Installation of CP S/m | Precommissioning BVS-6 | C-52-598-06-CA-1020 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | Padding | Pre-commissioning from BVS-06 to CRS Sweihan | C-52-06CR-PL-CI-6000 | PRECOM-52-06CR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.2.1 Evaporation PondCCOPL52487 | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | Evaporation Pond | Pre-commissioning from BVS-06 to CRS Sweihan | C-52-06CR-PL-CI-7200 | PRECOM-52-06CR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.2.3 Dewatering & DryingCCOPL52482 | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | Swabing & Drying (Upto Dew Point Temp.) | Pre-commissioning from BVS-06 to CRS Sweihan | C-52-06CR-PL-ME-7620 | PRECOM-52-06CR-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | Gatch Compaction | Pre-commissioning from BVS-06 to CRS Sweihan | C-52-06CR-PL-CI-6810 | PRECOM-52-06CR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | Installation of Crash Barriers (If any) | Pre-commissioning from BVS-06 to CRS Sweihan | C-52-06CR-PL-CI-7810 | PRECOM-52-06CR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.5.2.3 Re-Instatement of Entry & Exit PitCCOPL58132 | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from BVS-06 to CRS Sweihan | C-52-06CR-CNH30-1800 | PRECOM-52-06CR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.5 Re-Instatement of Entry & Exit PitCCOPL56962 | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Pre-commissioning from BVS-06 to CRS Sweihan | C-52-06CR-CNM31-1800 | PRECOM-52-06CR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.21 CP Works TemporaryCCOP52EL49 | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | Glanding & Termination of Temp. CP S/m | Pre-commissioning from BVS-06 to CRS Sweihan | C-52-06CR-PL-CA-5210 | PRECOM-52-06CR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | CIP/DCVG Survey | Pre-commissioning from BVS-06 to CRS Sweihan | C-52-06CR-PL-CA-5250 | PRECOM-52-06CR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | Termination/Splicing @ BVS | Pre-commissioning from BVS-06 to CRS Sweihan | C-52-06CR-PL-TE-8210 | PRECOM-52-06CR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.7 Paving WorksCCOSWCS319 | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Paving Works | Precommissioning Electrical Building Type-I | C-52-EB1-CI-2010 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.5 Finishing WorksCCOSWCS313 | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Internal Finishing Works | Precommissioning Electrical Building Type-I | C-52-EB1-CI-1810 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.5 Finishing WorksCCOSWCS313 | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | External Finishing Works | Precommissioning Electrical Building Type-I | C-52-EB1-CI-1800 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.6 Metal WorksCCOSWCS318 | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Steel Structural Works | Precommissioning Electrical Building Type-I | C-52-EB1-CI-2000 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.2.1 HVAC System & Plumbing WorksCCOSWME511 | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | HVAC Works | Precommissioning Electrical Building Type-I | C-52-EB1-ME-1010 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.2.1 HVAC System & Plumbing WorksCCOSWME511 | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Plumbing Works | Precommissioning Electrical Building Type-I | C-52-EB1-ME-1000 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Glanding & Termination | Precommissioning Electrical Building Type-I | C-52-EB1-EI-1230 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.4.2 Telecom System (Including subcontract for FOC Splicing / Termination / Testing)CCOSWIC322 | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Telecom System (Including subcontract for FOC Splicing / Termination / Testing) | Precommissioning Electrical Building Type-I | C-52-EB1-TE-1400 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.4.3 Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOSWIC332 | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Security System (Including subcontract for FOC Splicing / Termination / Testing ) | Precommissioning Electrical Building Type-I | C-52-EB1-TE-1610 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.4.22.1.3 Backfilling for CablesCCOSWCS323 | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Backfilling for Cables | Precommissioning Electrical Building Type-I | C-52-OHPL-CI-1400 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.4.22.2.3 Transformer / Directly Buried MV Cables (including testing)CCOSW52E22 | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Transformer / Directly Buried MV Cables (including testing) | Precommissioning Electrical Building Type-I | C-52-OHPL-EL-1400 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.4.22.3.1 Shutdown Connection of OHL & Cable TestingCCOSW52S10 | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Shutdown Connection of OHL & Cable Testing | Precommissioning Electrical Building Type-I | C-52-OHPL-EL-2000 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.5.22.6 Cable Laying, Glanding, Termination & Hook-UpCCOSW52E162 | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Cable Laying, Glanding, Termination & Hook-Up | Precommissioning Electrical Building Type-I | C-52-ADDC-EL-1200 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.5.22.4 Finishing WorksCCOSW52E142 | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Finishing Works for Shelter | Precommissioning Electrical Building Type-I | C-52-ADDC-CI-1600 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.5.22.5 Transformer/ Switch Gear InstallationCCOSW52E152 | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Transformer/ Switch Gear Installation | Precommissioning Electrical Building Type-I | C-52-ADDC-EL-1000 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.9 Thrust Anchor BlocklCCOSWCS317 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Concrete Works for Thrust Anchor Block | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-CI-1510 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.10 Earth Works for Paving CCOSWCS315.1 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Earth Works for Paving of Interlock tiles & Kerb Stone Embankment | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-CI-1070 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.1 Sales Gas FilterCCOSWME506 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Installation of Sales Gas Filter (839-F-104A) | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-ME-1800 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.1 Sales Gas FilterCCOSWME506 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Installation of Sales Gas Filter (839-F-104B) | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-ME-1810 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Installation of Sales Gas Custody Transfer Metering Skid Including Control Valve (839-ME-105) | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-ME-2010 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Installation of Pressure Reducing Skid (839-ME-106) | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-ME-2000 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.11 Backfilling for CablesCCOSWCS320 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Back Filling for Electrical & Earthing Cable | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-CI-2800 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.11 Backfilling for CablesCCOSWCS320 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Back Filling for Instrument & Telecom Cable | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-CI-2810 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.4 Concrete Works (Impact wall)CCOSWCS302.3 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Concrete Works for Impact Wall | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-CI-1500 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.13 Paving interlock & barrier installationCCOSWCS315.2 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Paving of Interlock tiles & Kerb Stone Embankment | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-CI-2600 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS505 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-CI-3010 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS505 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Pre-Fabrication & Installation of Platforms & Crossovers | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-CI-3000 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.2 Installation of Pig Receiver (839-V-101)CCOSWME508 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Installation of Pig Receiver (839-V-101) 52" | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-ME-1100 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Bolt Torquing/ Re-Instatement | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-PI-2000 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.5.1 Pig Receiver 839-V-101 52'' Pipeline/ Piping Hook-upCCOSWPI514 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Ext. Coating for Weld Joint | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-PL-1030 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Glanding & Termination | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-EI-2050 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Loop Checking for Instruments | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-EI-2040 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Deep Earth Well Drilling | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-EI-1400 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Glanding & Termination for CP S/m | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-CA-1030 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | FO Cable OTDR Testing & Splicing | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-TE-1420 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.10 Backfilling for CablesCCOJ42CS34 | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Back Filling for Electrical & Earthing Cable | Precommissioning | C-36-KM-HT-CI-2800 | PRECOM-36-KM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.10 Backfilling for CablesCCOJ42CS34 | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Back Filling for Instrument & Telecom Cable | Precommissioning | C-36-KM-HT-CI-2810 | PRECOM-36-KM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.11 Paving WorksCCOJ42CS32 | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Paving of Interlock tiles & Kerb Stone Embankment | Precommissioning | C-36-KM-HT-CI-2600 | PRECOM-36-KM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.3 Concrete Pit (For Hot Tapping)CCOJ42CS24 | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Concrete Works for Hot Tap Tie in Pit | Precommissioning | CCV-52-KM-1120 | PRECOM-36-KM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.2.6 Final Bolt Torquing/ Re-InstatementCCOJ42PI122 | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Final Bolt Torquing/ Re-Instatement | Precommissioning | C-36-KM-HT-PI-2000 | PRECOM-36-KM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Loop Checking for Instruments | Precommissioning | C-36-KM-HT-EI-2040 | PRECOM-36-KM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Glanding & Termination | Precommissioning | C-36-KM-HT-EI-2050 | PRECOM-36-KM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.4.6 Isolation of Hot Tap JointCCOJ42HT80 | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Isolation of Hot Tap Joint | Precommissioning | C-36-KM-HT03-ME-1050 | PRECOM-36-KM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.5.6 Isolation of Hot Tap JointCCOJ42HT140 | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Isolation of Hot Tap Joint | Precommissioning | C-36-KM-HT04-ME-1050 | PRECOM-36-KM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.6.1 Tie -in WorksCCOJ42PI72 | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Tie-In with 36" Pipeline | Precommissioning | C-36-KM-HT-ME-2000 | PRECOM-36-KM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.10 Backfilling for CablesCCOH5CS108 | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | Back Filling for Electrical & Earthing Cable | Precommissioning | C-4N-H5-TPL-CI-2800 | PRECOM-4NH5-TPL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.10 Backfilling for CablesCCOH5CS108 | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | Back Filling for Instrument & Telecom Cable | Precommissioning | C-4N-H5-TPL-CI-2810 | PRECOM-4NH5-TPL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.9 Paving WorksCCOH5CS107 | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | Paving of Interlock tiles & Kerb Stone Embankment | Precommissioning | C-4N-H5-TPL-CI-2600 | PRECOM-4NH5-TPL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Precommissioning | C-4N-H5-TPL-CI-3010 | PRECOM-4NH5-TPL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | Pre-Fabrication & Installation of Platforms & Crossovers | Precommissioning | C-4N-H5-TPL-CI-3000 | PRECOM-4NH5-TPL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH5ME502 | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | Installation of Pig Launcher 4" | Precommissioning | C-4N-H5-TPL-ME-1000 | PRECOM-4NH5-TPL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH5PI555 | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | Final Bolt Torquing/ Re-Instatement | Precommissioning | C-4N-H5-TPL-PI-2000 | PRECOM-4NH5-TPL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.5.11 Temporary Pig Launcher (4'' Nitrogen Pipeline) Piping Hook-upCCOH5PI505 | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | Ext. Coating for Weld Joint | Precommissioning | C-4N-H5-TPL-PL-1030 | PRECOM-4NH5-TPL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | Loop Checking for Instruments | Precommissioning | C-4N-H5-TPL-EI-2040 | PRECOM-4NH5-TPL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | Glanding & Termination | Precommissioning | C-4N-H5-TPL-EI-2050 | PRECOM-4NH5-TPL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | Glanding & Termination for CP S/m | Precommissioning | C-4N-H5-TPL-CA-1030 | PRECOM-4NH5-TPL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.8.1 Telecommunication Works CCOH5IC528 | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | FO Cable OTDR Testing & Splicing | Precommissioning | C-4N-H5-TPL-TE-1420 | PRECOM-4NH5-TPL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | Back Filling for Electrical & Earthing Cable | Precommissioning | C-4N-HG-TPR-CI-2800 | PRECOM-4NHG-TPR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | Back Filling for Instrument & Telecom Cable | Precommissioning | C-4N-HG-TPR-CI-2810 | PRECOM-4NHG-TPR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.5 Paving WorksCCOH4NCS69 | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | Paving of Interlock tiles & Kerb Stone Embankment | Precommissioning | C-4N-HG-TPR-CI-2600 | PRECOM-4NHG-TPR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | Concrete Works for Impact Wall | Precommissioning | C-4N-HG-TPR-CI-1500 | PRECOM-4NHG-TPR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Precommissioning | C-4N-HG-TPR-CI-3010 | PRECOM-4NHG-TPR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | Pre-Fabrication & Installation of Platforms & Crossovers | Precommissioning | C-4N-HG-TPR-CI-3000 | PRECOM-4NHG-TPR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH4NME50 | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | Installation of Pig Receiver 4" | Precommissioning | C-4N-HG-TPR-ME-1100 | PRECOM-4NHG-TPR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | Final Bolt Torquing/ Re-Instatement | Precommissioning | C-4N-HG-TPR-PI-2000 | PRECOM-4NHG-TPR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.5.9 Temporary Pig Receiver (4'' Nitrogen Pipeline) Piping Hook-upCCOH4NPI51 | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | Ext. Coating for Weld Joint | Precommissioning | C-4N-HG-TPR-PL-1030 | PRECOM-4NHG-TPR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | Loop Checking for Instruments | Precommissioning | C-4N-HG-TPR-EI-2040 | PRECOM-4NHG-TPR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | Glanding & Termination | Precommissioning | C-4N-HG-TPR-EI-2050 | PRECOM-4NHG-TPR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | Glanding & Termination for CP S/m | Precommissioning | C-4N-HG-TPR-CA-1030 | PRECOM-4NHG-TPR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.8.1 Telecommunication Works CCOH4NIC52 | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | FO Cable OTDR Testing & Splicing | Precommissioning | C-4N-HG-TPR-TE-1420 | PRECOM-4NHG-TPR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Padding | Precommissioning | C-4N-H5HG-PIPEL-6000 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.32 Dewatering, Swabbing, & DryingCCOPL4"124 | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Swabing & Drying (Upto Dew Point Temp.) | Precommissioning | C-4N-H5HG-PIPEL-7620 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.27 CP Works(Temporary)CCOP4"EL11.1 | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Glanding & Termination of Temp. CP S/m | Precommissioning | C-4N-H5HG-PIPEL-5210 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | CIP/DCVG Survey | Precommissioning | C-4N-H5HG-PIPEL-5250 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Gatch Compaction | Precommissioning | C-4N-H5HG-PIPEL-6810 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.33 ROW Restoration/ Marker Post/ Crash BarrierCCOPL4"126 | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Installation of Crash Barriers (If any) | Precommissioning | C-4N-H5HG-PIPEL-7810 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Termination/Splicing @ HGCP | Precommissioning | C-4N-H5HG-PIPEL-8210 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 HDD @ CH 0+517 - 0+556 (HDD-01) | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Re-Instatement of Entry & Exit Pit | Precommissioning | C-4N-H5HG-CNH01-1030 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 HDD @ CH 1+006 - 1+056 (HDD-02) | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Re-Instatement of Entry & Exit Pit | Precommissioning | C-4N-H5HG-CNH02-1030 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 HDD @ CH 2+845 - 3+029 (HDD-03) | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Re-Instatement of Entry & Exit Pit | Precommissioning | C-4N-H5HG-CNH03-1030 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 HDD @ CH 4+392 - 4+477 (HDD-04) | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Re-Instatement of Entry & Exit Pit | Precommissioning | C-4N-H5HG-CNH04-1030 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 HDD @ CH 9+139 - 9+322 (HDD-05) | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Re-Instatement of Entry & Exit Pit | Precommissioning | C-4N-H5HG-CNH05-1030 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 HDD @ CH 10+556 - 10+647 (HDD-06) | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Re-Instatement of Entry & Exit Pit | Precommissioning | C-4N-H5HG-CNH06-1030 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 HDD @ CH 12+216 - 12+275 (HDD-07) | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Re-Instatement of Entry & Exit Pit | Precommissioning | C-4N-H5HG-CNH07-1030 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 HDD @ CH 16+746 - 16+764 (HDD-08) | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Re-Instatement of Entry & Exit Pit | Precommissioning | C-4N-H5HG-CNH08-1030 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.1.12.1.4 Paving WorksCCOSV3CS14 | P2543-R01-Oct24..4.3.2.6.1.8.1 PrecommissioningCPC-SV3100 | Paving Works | Precommissioning | C-4W-081-03-CI-2600 | PRECOM-4W-08103-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | P2543-R01-Oct24..4.3.2.6.1.8.1 PrecommissioningCPC-SV3100 | Piping Works (RTP) | Precommissioning | C-4W-081-03-PI-1000 | PRECOM-4W-08103-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.1.12.3.1 Tie - in (4'' Tie-in Connection Water Line)CCOSV3PI51 | P2543-R01-Oct24..4.3.2.6.1.8.1 PrecommissioningCPC-SV3100 | Tie - in (4'' Tie-in Connection Water Line) | Precommissioning | C-4W-081-03-PI-3000 | PRECOM-4W-08103-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.1.3 Fences & Gates ConstructionCCOH4WCS24 | P2543-R01-Oct24..4.3.2.6.2.8.1 PrecommissioningCPC-SV3101 | Fences & Gates Construction | Precommissioning | C-4W-TI-CI-2220 | PRE-COM1310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.1.5 Paving WorksCCOH4WCS25 | P2543-R01-Oct24..4.3.2.6.2.8.1 PrecommissioningCPC-SV3101 | Paving Works | Precommissioning | C-4W-TI-CI-2600 | PRE-COM1310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.2.6 Installation of ValvesCCOH4WPI090 | P2543-R01-Oct24..4.3.2.6.2.8.1 PrecommissioningCPC-SV3101 | Installation of Valves | Precommissioning | C-4W-TI-PI-1800 | PRE-COM1310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.3.1 Tie - in (4'' Tie-in Connection Water Line)CCOH4WTI50 | P2543-R01-Oct24..4.3.2.6.2.8.1 PrecommissioningCPC-SV3101 | Tie - in (4'' Tie-in Connection Water Line) | Precommissioning | C-4W-TI-3000 | PRE-COM1310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..4.3.2.6.8.3 4'' Water Line from SV-03 (KP 96) to HGCP (1.8 km) | Padding | Precommissioning | C-4W-SVHG-PIPEL-6000 | PRECOM-4W-SVHG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 HDD @ CH 0+236 - 0+389 (HDD-01) | P2543-R01-Oct24..4.3.2.6.8.3 4'' Water Line from SV-03 (KP 96) to HGCP (1.8 km) | Re-Instatement of Entry & Exit Pit | Precommissioning | C-4N-H5HG-CNH1-1030 | PRECOM-4W-SVHG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.9.1 HDD @ CH 1+401 - 1+551 (HDD-02) | P2543-R01-Oct24..4.3.2.6.8.3 4'' Water Line from SV-03 (KP 96) to HGCP (1.8 km) | Re-Instatement of Entry & Exit Pit | Precommissioning | C-4N-H5HG-CNH2-1030 | PRECOM-4W-SVHG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | P2543-R01-Oct24..4.3.2.6.8.3 4'' Water Line from SV-03 (KP 96) to HGCP (1.8 km) | De-watering | Precommissioning | C-4W-SVHG-PIPEL-7610 | PRECOM-4W-SVHG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.4 Berm Construction | P2543-R01-Oct24..4.3.2.6.8.3 4'' Water Line from SV-03 (KP 96) to HGCP (1.8 km) | Gatch Compaction | Precommissioning | C-4W-SVHG-PIPEL-6810 | PRECOM-4W-SVHG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.5 Marker Post & Crash Barrier | P2543-R01-Oct24..4.3.2.6.8.3 4'' Water Line from SV-03 (KP 96) to HGCP (1.8 km) | Installation of Crash Barriers (If any) | Precommissioning | C-4W-SVHG-PIPEL-7810 | PRECOM-4W-SVHG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.7.12.1.2 Backfilling for CablesCCOB6C33 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Back Filling for Instrument & Telecom Cable | Precommissioning | C-DBV6-CI-2810 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.7.12.1.2 Backfilling for CablesCCOB6C33 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Back Filling for Electrical & Earthing Cable | Precommissioning | C-DBV6-CI-2800 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.7.12.2.1 Electrical & Instrumentation WorksCCOB6E10 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Installation of H2S Analyser | Precommissioning | C-DBV6-EI-2500 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Back Filling for LV Cable | Precommissioning | C-MAQTA-CI-2800 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Back Filling for Instrument Cable | Precommissioning | C-MAQTA-CI-2810 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Glanding & Termination | Precommissioning | C-MAQTA-EI-2050 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Installation PIDS S/m | Precommissioning | C-MAQTA-TE-1020 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Back Filling for LV Cable | Precommissioning | C-541CR-CI-1020 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Back Filling for Instrument Cable | Precommissioning | C-541CR-CI-1030 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Glanding & Termination | Precommissioning | C-541CR-EI-1040 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.3.1 Control System Modifications and Telecommunication WorksCCOC541IC2 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Telecommunication Works (Modification of Existing Telecom Cabinet) | Precommissioning | C-541CR-TE-1000 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.10.12.1.2 Backfilling - 577-SV-02 Passive cooling Shelter to HGCP - MCB BuildingCCOU57CS10 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Backfilling - 577-SV-02 Passive cooling Shelter to HGCP - MCB Building | Precommissioning | C-577-CI-1010 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.10.12.2.1 Telecommunication Works (new telecom cabinet and cable laying and terminations)CCOU577IC1 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Telecommunication Works (new telecom cabinet and cable laying and terminations) | Precommissioning | C-577-TE-1000 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.11.12.1.2 Backfilling - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS2 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Backfilling - Tahammama-C E&I Building to Launcher Station (607-V-603) | Precommissioning | C-601-CI-1010 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.11.12.2.1 Telecommunication Works (modifications of existing telecom cabinet)CCOU601IC1 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Telecommunication Works (modifications of existing telecom cabinet) | Precommissioning | C-601-TE-1000 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning | Ready for Commissioning & As-Built Submission | PRECOM-56-PL-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning | Ready for Commissioning & As-Built Submission | PRECOM-56-EB2-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.1.8.3.1 PrecommissioningCPC-HBS502 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning | Ready for Commissioning & As-Built Submission | PRECOM-56-G-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning | Ready for Commissioning & As-Built Submission | PRECOM-56-HGHC-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning | Ready for Commissioning & As-Built Submission | PRECOM-56-PR-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning | Ready for Commissioning & As-Built Submission | PRECOM-56-59101-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Pre-commissioning from BVS-02 to BVS-01 | Ready for Commissioning & As-Built Submission | PRECOM-52-0201-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning BVS-1 | Ready for Commissioning & As-Built Submission | PRECOM-56-59801-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Pre-commissioning from HGCP to BVS-01 | Ready for Commissioning & As-Built Submission | PRECOM-52-HG01-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning Pig Launcher 838-V-602 | Ready for Commissioning & As-Built Submission | PRECOM-52-PL-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2 Pre-commissioning from BVS-02 to BVS-03CPCPL52327.5 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Pre-commissioning from BVS-02 to BVS-03 | Ready for Commissioning & As-Built Submission | PRECOM-52-0203-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning BVS-2 | Ready for Commissioning & As-Built Submission | PRECOM-56-59802-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Pre-commissioning from BVS-03 to BVS-04 | Ready for Commissioning & As-Built Submission | PRECOM-52-0304-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning BVS-3 | Ready for Commissioning & As-Built Submission | PRECOM-56-59803-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | Ready for Commissioning & As-Built Submission | PRECOM-52-IDS1-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning BVS-4 | Ready for Commissioning & As-Built Submission | PRECOM-56-59804-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Pre-commissioning from BVS-04 to BVS-05 | Ready for Commissioning & As-Built Submission | PRECOM-52-0405-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | Ready for Commissioning & As-Built Submission | PRECOM-52-IDS2-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning BVS-5 | Ready for Commissioning & As-Built Submission | PRECOM-56-59805-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Pre-commissioning from BVS-05 to BVS-06 | Ready for Commissioning & As-Built Submission | PRECOM-52-0506-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Pre-Commissioning Intrusion Detection KP122 to KP123 | Ready for Commissioning & As-Built Submission | PRECOM-52-IDS3-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.4 Precommissioning DEL/TFP PipelineCPCHGCP522 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning DEL/TFP Pipeline | Ready for Commissioning & As-Built Submission | PRECOM-52-D-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning BVS-6 | Ready for Commissioning & As-Built Submission | PRECOM-52-59806-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning Pig Receiver 839-V-101 | Ready for Commissioning & As-Built Submission | PRECOM-52-PR-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Pre-commissioning from BVS-06 to CRS Sweihan | Ready for Commissioning & As-Built Submission | PRECOM-52-06CR-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning Electrical Building Type-I | Ready for Commissioning & As-Built Submission | PRECOM-52-EB1-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning | Ready for Commissioning & As-Built Submission | PRECOM-36-KM-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning | Ready for Commissioning & As-Built Submission | PRECOM-4NH5-TPL-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning | Ready for Commissioning & As-Built Submission | PRECOM-4NHG-TPR-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning | Ready for Commissioning & As-Built Submission | PRECOM-4N-H5HG-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.6.1.8.1 PrecommissioningCPC-SV3100 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning | Ready for Commissioning & As-Built Submission | PRECOM-4W-08103-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.6.2.8.1 PrecommissioningCPC-SV3101 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning | Ready for Commissioning & As-Built Submission | PRE-COM1310 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.6.8.3 4'' Water Line from SV-03 (KP 96) to HGCP (1.8 km) | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning | Ready for Commissioning & As-Built Submission | PRECOM-4W-SVHG-1000 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | Precommissioning | Ready for Commissioning & As-Built Submission | PRE-COM1330 | COM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.8 Trenching for CablesCCOH5CS105 | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-4N-H5-TPL-CI-1810 | C-4N-H5-TPL-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Concrete Works for Access Platforms & Misc. Structural Foundations | Pre-Fabrication & Installation of Platforms & Crossovers | C-4N-HG-TPR-CI-1420 | C-4N-HG-TPR-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-4N-HG-TPR-CI-1810 | C-4N-HG-TPR-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.1.1 Demolition Works (Paving & Fence)CCOH4WCS20 | P2543-R01-Oct24..4.3.1.6.2.12.1.2 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH4WCS21 | Demolition Works (Paving & Fence) | Concrete Works (Foundations for Equipment & Pipe Supports) | C-4W-TI-CI-1000 | C-4W-TI-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.1.2 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH4WCS21 | P2543-R01-Oct24..4.3.1.6.2.12.1.4 Concrete ProtectionCCOH4WCS23 | Concrete Works (Foundations for Equipment & Pipe Supports) | Concrete Protection | C-4W-TI-CI-1400 | C-4W-TI-CI-1700 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.1.4 Concrete ProtectionCCOH4WCS23 | P2543-R01-Oct24..4.3.1.6.2.12.2.3 ErectionCCOH4WPI060 | Concrete Protection | Piping Installation | C-4W-TI-CI-1700 | C-4W-TI-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.40.2 Excavation WorksCCOHBCS301 | P2543-R01-Oct24..4.3.1.1.3.10.40.3 Concrete WorksCCOHBCS302 | Compaction & Testing for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-56-G-HT-CI-1210 | C-56-G-HT-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | Concrete Works for Field Instruments & JBs Foundation | Installation of Solar S/m Structurals | C-52-IDS1-CI-1410 | C-52-IDS1-EI-1190 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | Concrete Works for Field Instruments & JBs Foundation | Installation of Solar S/m Structurals | C-52-IDS2-CI-1410 | C-52-IDS2-EI-1190 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | Concrete Works for Field Instruments & JBs Foundation | Installation of Solar S/m Structurals | C-52-IDS3-CI-1410 | C-52-IDS3-EI-1190 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.4 Concrete Works (Foundations for Equipment)CCOJ42CS44 | P2543-R01-Oct24..4.3.1.4.12.2.5 Installation of ValvesCCOJ42PI112 | Concrete Works for Access Platforms & Misc. Structural Foundations | Installation of Valves/GOV/ROV | C-36-KM-HT-CI-1420 | C-36-KM-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.6 Trenching for CablesCCOJ42CS30 | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-36-KM-HT-CI-1810 | C-36-KM-HT-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.9 Trenching for Instrument cablesCCOH52CS35.2 | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-52-PL-838-CI-1810 | C-52-PL-838-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.6 Pipe Supports Fabrication & InstallationCCOH52SS60 | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Pre-Fabrication & Installation of Pipe Supports | Piping Erection | C-52-PL-838-CI-2000 | C-52-PL-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS505 | Concrete Works for Access Platforms & Misc. Structural Foundations | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-PR-839-CI-1420 | C-52-PR-839-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.7 Pipe Supports Fabrication & InstallationCCOSWSS500 | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | Pre-Fabrication & Installation of Pipe Supports | Piping Erection | C-52-PR-839-CI-2000 | C-52-PR-839-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.6 Trenching for CablesCCOSWCS311 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-52-PR-839-CI-1810 | C-52-PR-839-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.4 Field InstrumentsCCOSW52E10.32 | Instrument Tubing Works | Installation of Field Instruments (Including Pig Signaller) | C-52-PR-839-EI-2030 | C-52-PR-839-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | P2543-R01-Oct24..4.3.1.3.9.21.1.10 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB152S54 | Concrete Works for Access Platform & Misc. Structural Foundations | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-06-CI-1420 | C-52-598-06-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | P2543-R01-Oct24..4.3.1.3.10.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB252S51 | Concrete Works for Access Platform & Misc. Structural Foundations | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-05-CI-1420 | C-52-598-05-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | P2543-R01-Oct24..4.3.1.3.11.21.6.8 Field InstrumentsCCOB352E102 | Concrete Works for Field Instrument, JB Foundations | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-04-CI-1410 | C-52-598-04-EI-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | P2543-R01-Oct24..4.3.1.3.12.21.6.6 Field InstrumentsCCOB452E93 | Concrete Works for Field Instrument, JB Foundations | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-03-CI-1410 | C-52-598-03-EI-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | P2543-R01-Oct24..4.3.1.3.12.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB452S52 | Concrete Works for Access Platform & Misc. Structural Foundations | Pre-Fabrication & Installation of Platforms & Crossovers | C-52-598-03-CI-1420 | C-52-598-03-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Deep Earth Well Drilling | Glanding & Termination | C-52-598-06-EI-1400 | C-52-598-06-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Electrical & Earthing Cable Laying | Precommissioning BVS-6 | C-52-598-06-EI-2000 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Deep Earth Well Drilling | Glanding & Termination | C-52-598-01-EI-1400 | C-52-598-01-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Deep Earth Well Drilling | Precommissioning BVS-1 | C-52-598-01-EI-1400 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Deep Earth Well Drilling | Glanding & Termination | C-56-PL-607-EI-1400 | C-56-PL-607-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.17 CP Works TemporaryCCOP52EL38 | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | Glanding & Termination of Temp. CP S/m | CIP/DCVG Survey | C-52-0203-PL-CA-5210 | C-52-0203-PL-CA-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.19 CP Works TemporaryCCOP52EL41 | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Glanding & Termination of Temp. CP S/m | CIP/DCVG Survey | C-52-0304-PL-CA-5210 | C-52-0304-PL-CA-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.21 CP Works TemporaryCCOP52EL43 | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Glanding & Termination of Temp. CP S/m | CIP/DCVG Survey | C-52-0405-PL-CA-5210 | C-52-0405-PL-CA-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.43 Fence Installation (Type3) from BVS-01 to BVS-02CCOP52CS57.6 | P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | Installation of Fence Mesh (BVS-02 to BVS-01) | Pre-commissioning from BVS-02 to BVS-01 | C-52-0102-FENCE-1070 | PRECOM-52-0201-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.48 Fence Installation (Type3) from HGCP to BVS-01CCOP52CS57.7 | P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | Installation of Fence Mesh (BVS-01 to HGCP) | Pre-commissioning from HGCP to BVS-01 | C-52-HG01-FENCE-1070 | PRECOM-52-HG01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.38 Fence Installation (Type3) from BVS-02 to BVS-03CCOP52CS57.5 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Installation of Fence Mesh (BVS-02 to BVS-03) | Precommissioning BVS-2 | C-52-0203-FENCE-1070 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.33 Fence Installation (Type3) from BVS-03 to BVS-04CCOP52CS57.4 | P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | Installation of Fence Mesh (BVS-03 to BVS-04) | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | C-52-0304-FENCE-1070 | PRECOM-52-IDS1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.28 Fence Installation (Type3) from BVS-04 to BVS-05CCOP52CS57.3 | P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | Installation of Fence Mesh (BVS-04 to BVS-05) | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | C-52-0405-FENCE-1070 | PRECOM-52-IDS2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.22 Fence Installation (Type3) from BVS-05 to BVS-06CCOP52CS57.2 | P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | Installation of Fence Mesh (BVS-05 to BVS-06) | Pre-Commissioning Intrusion Detection KP122 to KP123 | C-52-0506-FENCE-1070 | PRECOM-52-IDS3-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.14 Fence Installation (Type3) from BVS-06 to CRS SweihanCCOP52CS57.1 | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | Installation of Fence Mesh (BVS-06 to Sweihan-CRS) | Pre-commissioning from BVS-06 to CRS Sweihan | C-52-06CR-FENCE-1070 | PRECOM-52-06CR-1000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Padding & Backfilling | Precommissioning BVS-6 | C-52-598-06-PL-1090 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Padding & Backfilling | Precommissioning BVS-5 | C-52-598-05-PL-1090 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Padding & Backfilling | Precommissioning BVS-4 | C-52-598-04-PL-1090 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Padding & Backfilling | Precommissioning BVS-2 | C-52-598-02-PL-1090 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.26 Test Stations & Anode Beds from BVS-01 to KP 21.3CCOP56EL24.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Glanding & Termination of Temp. CP S/m | CIP/DCVG Survey (Pre-Com) | C-56-01HG-PL-CA-5620 | C-56-01HG-PL-CA-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Glanding & Termination of Temp. CP S/m | CIP/DCVG Survey | C-56-HC01-PL-CA-5210 | C-56-HC01-PL-CA-5250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.19 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOB156S54 | P2543-R01-Oct24..4.3.1.2.1.12.1.19 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOB156S54 | Pre-Fabrication & Installation of Platforms & Crossovers | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-56-591-01-CI-3000 | C-56-591-01-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | SCADA S/m Modification | Precommissioning | C-MAQTA-TE-1000 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.16 NDT TestCCOPL52309 | P2543-R01-Oct24..4.3.1.3.2.21.1.16 NDT TestCCOPL52309 | NDT-Lot1 | NDT-Lot2 | C-52-HG01-PL-ME-4000 | C-52-HG01-PL-ME-4200 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | Ext. Joint Coating-Lot1 | Ext. Joint Coating-Lot2 | C-52-HG01-PL-ME-4400 | C-52-HG01-PL-ME-4600 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | Bedding-Lot1 | Bedding-Lot2 | C-52-HG01-PL-CI-2410 | C-52-HG01-PL-CI-2610 | FF | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Lowering-Lot1 | Lowering-Lot2 | C-52-HG01-PL-ME-4800 | C-52-HG01-PL-ME-5000 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Section Tie-in Welding -Lot1 | Section Tie-in Welding-Lot2 | C-52-HG01-PL-ME-4810 | C-52-HG01-PL-ME-5010 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | NDT (Tie-in Joint)-Lot1 | NDT (Tie-in Joint)-Lot2 | C-52-HG01-PL-ME-4820 | C-52-HG01-PL-ME-5020 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | Ext. Joint Coating (Tie-in Joint)-Lot1 | Ext. Joint Coating (Tie-in Joint)-Lot2 | C-52-HG01-PL-ME-4410 | C-52-HG01-PL-ME-4610 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Holiday Testing-Lot1 | Holiday Testing-Lot2 | C-52-HG01-PL-ME-4830 | C-52-HG01-PL-ME-5030 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | Padding -Lot1 | Padding -Lot2 | C-52-HG01-PL-CI-6000 | C-52-HG01-PL-CI-6200 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.13 Cold BendsCCOPL52307 | P2543-R01-Oct24..4.3.1.3.2.21.1.13 Cold BendsCCOPL52307 | Cold Bends-Lot1 | Cold Bends-Lot2 | C-52-HG01-PL-ME-3200 | C-52-HG01-PL-ME-3400 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.12 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 3&4)CCOPL52303.4 | P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | Sabka Gatch Compaction - Layer 4 | Trench Excavation-Lot2 | C-52-HG01-PL-CI-2230 | C-52-HG01-PL-CI-2600 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.4 Concrete Works (Impact Wall ) CCOHBCS202.3 | P2543-R01-Oct24..4.3.1.1.1.12.1.5 Concrete Works (Foundations for Pipe Supports) CCOHBCS202.2 | Concrete Works (Impact Wall ) (Deleted) | Concrete Works for Pipe Support Foundations | C-56-PL-607-CI-1500 | C-56-PL-607-CI-1600 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.6 Trenching for Electrical cables CCOHBCS205.1 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Electrical & Earthing Cable Trenching | Instrument Cable Laying | C-56-PL-607-CI-1800 | C-56-PL-607-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.6 Trenching for Electrical cables CCOHBCS205.1 | P2543-R01-Oct24..4.3.1.1.1.12.1.10 Trenching for Instrument cablesCCOHBCS205.2 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-56-PL-607-CI-1800 | C-56-PL-607-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.10 Trenching for Instrument cablesCCOHBCS205.2 | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Instrument & Telecom Cable Trenching | Instrument Cable Laying | C-56-PL-607-CI-1810 | C-56-PL-607-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.40.3 Concrete WorksCCOHBCS302 | P2543-R01-Oct24..4.3.1.1.3.10.40.5 Pipe Supports Fabrication & InstallationCCOHBSS307 | Concrete Works for Pipe Support Foundations | Pipe Supports Fabrication & Installation | C-56-G-HT-CI-1600 | C-56-G-HT-CI-2000 | FS | Not Started | Not Started | 45
P2543-R01-Oct24..4.3.1.1.3.10.40.5 Pipe Supports Fabrication & InstallationCCOHBSS307 | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | Pipe Supports Fabrication & Installation | Piping Erection | C-56-G-HT-CI-2000 | C-56-G-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.8 Surveying from KP 21.3 to HGCPCCOPL56247.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.10 ROW Access RoadCCOPL56249 | Survey Marking | Non-Sabka ROW/Grading | C-56-01HG-PL-CI-1200 | C-56-01HG-PL-CI-1800 | FS | Completed | Completed | 14
P2543-R01-Oct24..4.3.1.2.3.12.1.7 Surveying from BVS-01 to KP 21.3CCOPL56247.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.8 Surveying from KP 21.3 to HGCPCCOPL56247.2 | Survey Marking | Survey Marking | C-56-01HG-PL-CI-1000 | C-56-01HG-PL-CI-1200 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.12 Cut & Fill from KP 21.3 to HGCPCCOPL56248.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.15 Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-56-01HG-PL-CI-1600 | C-56-01HG-PL-CI-2400 | SS | Completed | Not Started | 5
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Instrument Cable Laying | FO Cable OTDR Testing & Splicing | C-56-PL-607-EI-2010 | C-56-PL-607-TE-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Instrument Cable Laying | Installation of Out Door FOC Splicing Box | C-56-PL-607-EI-2010 | C-56-PL-607-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.6 Trenching for Electrical cables CCOHBCS205.1 | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Electrical & Earthing Cable Trenching | FO Cable OTDR Testing & Splicing | C-56-PL-607-CI-1800 | C-56-PL-607-TE-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.6 Trenching for Electrical cables CCOHBCS205.1 | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Electrical & Earthing Cable Trenching | Installation of Out Door FOC Splicing Box | C-56-PL-607-CI-1800 | C-56-PL-607-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.10 Trenching for Instrument cablesCCOHBCS205.2 | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Instrument & Telecom Cable Trenching | FO Cable OTDR Testing & Splicing | C-56-PL-607-CI-1810 | C-56-PL-607-TE-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.10 Trenching for Instrument cablesCCOHBCS205.2 | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Instrument & Telecom Cable Trenching | Installation of Out Door FOC Splicing Box | C-56-PL-607-CI-1810 | C-56-PL-607-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | Instrument Cable Laying | Installation of SDH Cabinet | C-56-591-01-EI-2010 | C-56-591-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.8.3 Telephone System CCOB156I40 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Installation of Telephone System | Precommissioning | C-56-591-01-TE-1400 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | Instrument Cable Laying | Installation of SDH Cabinet | C-52-598-02-EI-2010 | C-52-598-02-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.8.3 Telephone SystemCCOB552I51 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Installation of Telephone System | Precommissioning BVS-2 | C-52-598-02-TE-1400 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | Instrument Cable Laying | Installation of SDH Cabinet | C-52-598-01-EI-2010 | C-52-598-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.8.3 Telephone SystemCCOB652I51 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Installation of Telephone System | Precommissioning BVS-1 | C-52-598-01-TE-1400 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | Instrument Cable Laying | Installation of SDH Cabinet | C-52-598-03-EI-2010 | C-52-598-03-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.8.3 Telephone SystemCCOB452I50 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Installation of Telephone System | Precommissioning BVS-3 | C-52-598-03-TE-1400 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Instrument Cable Laying | Installation of SDH Cabinet | C-52-598-04-EI-2010 | C-52-598-04-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.8.3 Telephone SystemCCOB352I50 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Installation of Telephone System | Precommissioning BVS-4 | C-52-598-04-TE-1400 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | Instrument Cable Laying | Installation of SDH Cabinet | C-52-598-05-EI-2010 | C-52-598-05-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | P2543-R01-Oct24..4.3.1.3.10.21.1.10 Backfilling for CablesCCOB252C40 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-52-598-05-EI-2010 | C-52-598-05-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.8.3 Telephone SystemCCOB252I50 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Installation of Telephone System | Precommissioning BVS-5 | C-52-598-05-TE-1400 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Instrument Cable Laying | Installation of SDH Cabinet | C-52-598-06-EI-2010 | C-52-598-06-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Installation of Cable Trays | Installation of SDH Cabinet | C-52-598-06-EI-2020 | C-52-598-06-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | P2543-R01-Oct24..4.3.1.3.9.21.1.11 Backfilling for CablesCCOB152C37 | Installation of Cable Trays | Back Filling for Instrument & Telecom Cable | C-52-598-06-EI-2020 | C-52-598-06-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.8.2 Telephone SystemCCOB152I50 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Installation of Telephone System | Precommissioning BVS-6 | C-52-598-06-TE-1400 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.8 Backfilling for CablesCCOH52CS45 | CCTV Installation | Back Filling for Instrument & Telecom Cable | C-52-IDS1-TE-1600 | C-52-IDS1-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | Instrument Cable Laying | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | C-52-IDS1-EI-2010 | PRECOM-52-IDS1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | CCTV Installation | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | C-52-IDS1-TE-1600 | PRECOM-52-IDS1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.8 Backfilling for CablesCCOH52CS53 | CCTV Installation | Back Filling for Instrument & Telecom Cable | C-52-IDS2-TE-1600 | C-52-IDS2-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.8 Backfilling for CablesCCOH52CS53 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-52-IDS1-EI-2010 | C-52-IDS2-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.8 Backfilling for CablesCCOH52CS53 | CCTV Installation | Back Filling for Instrument & Telecom Cable | C-52-IDS1-TE-1600 | C-52-IDS2-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | Instrument Cable Laying | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | C-52-IDS2-EI-2010 | PRECOM-52-IDS2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | CCTV Installation | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | C-52-IDS2-TE-1600 | PRECOM-52-IDS2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | Instrument Cable Laying | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | C-52-IDS1-EI-2010 | PRECOM-52-IDS2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | CCTV Installation | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | C-52-IDS1-TE-1600 | PRECOM-52-IDS2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.8 Backfilling for CablesCCOH52CS61 | CCTV Installation | Back Filling for Instrument & Telecom Cable | C-52-IDS3-TE-1600 | C-52-IDS3-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.8 Backfilling for CablesCCOH52CS61 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-52-IDS2-EI-2010 | C-52-IDS3-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.8 Backfilling for CablesCCOH52CS61 | CCTV Installation | Back Filling for Instrument & Telecom Cable | C-52-IDS2-TE-1600 | C-52-IDS3-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.8 Backfilling for CablesCCOH52CS61 | Instrument Cable Laying | Back Filling for Instrument & Telecom Cable | C-52-IDS1-EI-2010 | C-52-IDS3-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.8 Backfilling for CablesCCOH52CS61 | CCTV Installation | Back Filling for Instrument & Telecom Cable | C-52-IDS1-TE-1600 | C-52-IDS3-CI-2810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL62 | P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | Instrument Cable Laying | Pre-Commissioning Intrusion Detection KP122 to KP123 | C-52-IDS3-EI-2010 | PRECOM-52-IDS3-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | CCTV Installation | Pre-Commissioning Intrusion Detection KP122 to KP123 | C-52-IDS3-TE-1600 | PRECOM-52-IDS3-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL21 | P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | Instrument Cable Laying | Pre-Commissioning Intrusion Detection KP122 to KP123 | C-52-IDS2-EI-2010 | PRECOM-52-IDS3-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | CCTV Installation | Pre-Commissioning Intrusion Detection KP122 to KP123 | C-52-IDS2-TE-1600 | PRECOM-52-IDS3-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | Instrument Cable Laying | Pre-Commissioning Intrusion Detection KP122 to KP123 | C-52-IDS1-EI-2010 | PRECOM-52-IDS3-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | CCTV Installation | Pre-Commissioning Intrusion Detection KP122 to KP123 | C-52-IDS1-TE-1600 | PRECOM-52-IDS3-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.10 ROW Access RoadCCOPL56249 | P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | Non-Sabka ROW/Grading | Sabka Gatch Laying (Including ROW) - Layer 1 | C-56-01HG-PL-CI-1800 | C-56-01HG-PL-CI-2000 | FF | Completed | In Progress | 30
P2543-R01-Oct24..4.3.1.2.3.12.1.10 ROW Access RoadCCOPL56249 | P2543-R01-Oct24..4.3.1.2.3.12.1.15 Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 | Non-Sabka ROW/Grading | Trench Excavation | C-56-01HG-PL-CI-1800 | C-56-01HG-PL-CI-2400 | FF | Completed | Not Started | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.24 Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.24 Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 | Trench Excavation | Bedding | C-56-01HG-PL-CI-2600 | C-56-01HG-PL-CI-2610 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.24 Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Bedding | Lowering | C-56-01HG-PL-CI-2610 | C-56-01HG-PL-ME-4800 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | P2543-R01-Oct24..4.3.1.2.3.12.1.24 Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 | Sabka Gatch Compaction - Layer 4 | Trench Excavation | C-56-01HG-PL-CI-2230 | C-56-01HG-PL-CI-2600 | SS | In Progress | Not Started | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.10 ROW Access RoadCCOPL56249 | P2543-R01-Oct24..4.3.1.2.3.12.1.24 Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 | Non-Sabka ROW/Grading | Trench Excavation | C-56-01HG-PL-CI-1800 | C-56-01HG-PL-CI-2600 | SS | Completed | Not Started | 5
P2543-R01-Oct24..4.3.1.2.3.12.1.12 Cut & Fill from KP 21.3 to HGCPCCOPL56248.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.24 Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-56-01HG-PL-CI-1600 | C-56-01HG-PL-CI-2600 | FF | Completed | Not Started | 5
P2543-R01-Oct24..4.3.1.2.3.12.1.10 ROW Access RoadCCOPL56249 | P2543-R01-Oct24..4.3.1.2.3.12.1.24 Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 | Non-Sabka ROW/Grading | Trench Excavation | C-56-01HG-PL-CI-1800 | C-56-01HG-PL-CI-2600 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | P2543-R01-Oct24..4.3.1.2.3.12.1.24 Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 | Sabka Gatch Compaction - Layer 4 | Trench Excavation | C-56-01HG-PL-CI-2230 | C-56-01HG-PL-CI-2600 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | P2543-R01-Oct24..4.3.1.2.3.12.1.27 Pipe Stringing from KP 21.3 to HGCPCCOPL56250.2 | Sabka Gatch Compaction - Layer 4 | Stringing (KP 21.3 to HGCP) | C-56-01HG-PL-CI-2230 | C-56-01HG-PL-ME-3000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.27 Pipe Stringing from KP 21.3 to HGCPCCOPL56250.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | Stringing (KP 21.3 to HGCP) | Lowering | C-56-01HG-PL-ME-3000 | C-56-01HG-CME01-1020 | SS | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.34 Cold Bends from KP 21.3 to HGCPCCOPL56255.2 | Lowering | Cold Bends | C-56-01HG-PL-ME-4800 | C-56-01HG-PL-ME-3400 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.17 Cold Bends from BVS-01 to KP 21.3CCOPL56255.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.34 Cold Bends from KP 21.3 to HGCPCCOPL56255.2 | Cold Bends | Cold Bends | C-56-01HG-PL-ME-3200 | C-56-01HG-PL-ME-3400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.27 Pipe Stringing from KP 21.3 to HGCPCCOPL56250.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.31 Automatic Welding from KP 21.3 to HGCPCCOPL56256.2 | Stringing (KP 21.3 to HGCP) | Automatic Welding | C-56-01HG-PL-ME-3000 | C-56-01HG-PL-ME-3800 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.16 Pipe Stringing from BVS-01 to KP 21.3CCOPL56250.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.20 Automatic Welding from BVS-01 to KP 21.3CCOPL56256.1 | Stringing (BVS-01 to KP 21.3) | Automatic Welding | C-56-01HG-PL-ME-2800 | C-56-01HG-PL-ME-3600 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.27 Pipe Stringing from KP 21.3 to HGCPCCOPL56250.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.31 Automatic Welding from KP 21.3 to HGCPCCOPL56256.2 | Stringing (KP 21.3 to HGCP) | Automatic Welding | C-56-01HG-PL-ME-3000 | C-56-01HG-PL-ME-3800 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.20 Automatic Welding from BVS-01 to KP 21.3CCOPL56256.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.32 NDT Test from KP 21.3 to HGCPCCOPL56245.2 | Automatic Welding | NDT | C-56-01HG-PL-ME-3600 | C-56-01HG-PL-ME-4200 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.31 Automatic Welding from KP 21.3 to HGCPCCOPL56256.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.32 NDT Test from KP 21.3 to HGCPCCOPL56245.2 | Automatic Welding | NDT | C-56-01HG-PL-ME-3800 | C-56-01HG-PL-ME-4200 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.20 Automatic Welding from BVS-01 to KP 21.3CCOPL56256.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.13 NDT Test from BVS-01 to KP 21.3CCOPL56245.1 | Automatic Welding | NDT | C-56-01HG-PL-ME-3600 | C-56-01HG-PL-ME-4000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.20 Automatic Welding from BVS-01 to KP 21.3CCOPL56256.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.32 NDT Test from KP 21.3 to HGCPCCOPL56245.2 | Automatic Welding | NDT | C-56-01HG-PL-ME-3600 | C-56-01HG-PL-ME-4200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.31 Automatic Welding from KP 21.3 to HGCPCCOPL56256.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.32 NDT Test from KP 21.3 to HGCPCCOPL56245.2 | Automatic Welding | NDT | C-56-01HG-PL-ME-3800 | C-56-01HG-PL-ME-4200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.13 NDT Test from BVS-01 to KP 21.3CCOPL56245.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.32 NDT Test from KP 21.3 to HGCPCCOPL56245.2 | NDT | NDT | C-56-01HG-PL-ME-4000 | C-56-01HG-PL-ME-4200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.13 NDT Test from BVS-01 to KP 21.3CCOPL56245.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.39 Ext. Joint Coating from KP 21.3 to HGCPCCOPL56258.2 | NDT | Ext. Joint Coating | C-56-01HG-PL-ME-4000 | C-56-01HG-PL-ME-4600 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.39 Ext. Joint Coating from KP 21.3 to HGCPCCOPL56258.2 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-PL-ME-4820 | C-56-01HG-PL-ME-4610 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.32 NDT Test from KP 21.3 to HGCPCCOPL56245.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.39 Ext. Joint Coating from KP 21.3 to HGCPCCOPL56258.2 | NDT | Ext. Joint Coating | C-56-01HG-PL-ME-4200 | C-56-01HG-PL-ME-4600 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.25 Ext. Joint Coating from BVS-01 to KP 21.3CCOPL56258.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.39 Ext. Joint Coating from KP 21.3 to HGCPCCOPL56258.2 | Ext. Joint Coating | Ext. Joint Coating | C-56-01HG-PL-ME-4400 | C-56-01HG-PL-ME-4600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.25 Ext. Joint Coating from BVS-01 to KP 21.3CCOPL56258.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.39 Ext. Joint Coating from KP 21.3 to HGCPCCOPL56258.2 | Ext. Joint Coating (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-PL-ME-4410 | C-56-01HG-PL-ME-4610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.13 NDT Test from BVS-01 to KP 21.3CCOPL56245.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.25 Ext. Joint Coating from BVS-01 to KP 21.3CCOPL56258.1 | NDT | Ext. Joint Coating | C-56-01HG-PL-ME-4000 | C-56-01HG-PL-ME-4400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.25 Ext. Joint Coating from BVS-01 to KP 21.3CCOPL56258.1 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-PL-ME-4820 | C-56-01HG-PL-ME-4410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.39 Ext. Joint Coating from KP 21.3 to HGCPCCOPL56258.2 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-PL-ME-4820 | C-56-01HG-PL-ME-4610 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.13 NDT Test from BVS-01 to KP 21.3CCOPL56245.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.39 Ext. Joint Coating from KP 21.3 to HGCPCCOPL56258.2 | NDT | Ext. Joint Coating | C-56-01HG-PL-ME-4000 | C-56-01HG-PL-ME-4600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.32 NDT Test from KP 21.3 to HGCPCCOPL56245.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.39 Ext. Joint Coating from KP 21.3 to HGCPCCOPL56258.2 | NDT | Ext. Joint Coating | C-56-01HG-PL-ME-4200 | C-56-01HG-PL-ME-4600 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.25 Ext. Joint Coating from BVS-01 to KP 21.3CCOPL56258.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Ext. Joint Coating | Lowering | C-56-01HG-PL-ME-4400 | C-56-01HG-PL-ME-4800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-PL-ME-4810 | C-56-01HG-PL-ME-4820 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.25 Ext. Joint Coating from BVS-01 to KP 21.3CCOPL56258.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-PL-ME-4410 | C-56-01HG-PL-ME-4830 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.15 Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Bedding | Lowering | C-56-01HG-PL-CI-2410 | C-56-01HG-PL-ME-5000 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Lowering | Section Tie-in Welding | C-56-01HG-PL-ME-5000 | C-56-01HG-PL-ME-5010 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-PL-ME-5010 | C-56-01HG-PL-ME-5020 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.25 Ext. Joint Coating from BVS-01 to KP 21.3CCOPL56258.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-PL-ME-4410 | C-56-01HG-PL-ME-5030 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.25 Ext. Joint Coating from BVS-01 to KP 21.3CCOPL56258.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Ext. Joint Coating | Lowering | C-56-01HG-PL-ME-4400 | C-56-01HG-PL-ME-5000 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA01-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA02-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA03-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA04-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA05-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA06-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA07-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA08-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA09-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA10-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA11-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA12-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA13-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA14-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA15-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA23-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA24-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA25-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA26-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA27-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA21-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA22-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA19-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA17-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA20-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA16-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CMA18-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME01-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME02-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME03-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME04-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME05-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME06-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME07-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME08-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME09-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-CME10-1030 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.17 Cold Bends from BVS-01 to KP 21.3CCOPL56255.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Cold Bends | Section Tie-in Welding | C-56-01HG-PL-ME-3200 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | P2543-R01-Oct24..4.3.2.2.2.3.1.1 Evaporation PondCCOPL56239 | Section Tie-in Welding | Evaporation Pond | C-56-01HG-PL-ME-5010 | C-56-01HG-PL-CI-7200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.24 Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Bedding | Lowering | C-56-01HG-PL-CI-2610 | C-56-01HG-PL-ME-5000 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.34 Cold Bends from KP 21.3 to HGCPCCOPL56255.2 | Lowering | Cold Bends | C-56-01HG-PL-ME-5000 | C-56-01HG-PL-ME-3400 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.34 Cold Bends from KP 21.3 to HGCPCCOPL56255.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Cold Bends | Section Tie-in Welding | C-56-01HG-PL-ME-3400 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.39 Ext. Joint Coating from KP 21.3 to HGCPCCOPL56258.2 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-PL-ME-5020 | C-56-01HG-PL-ME-4610 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.39 Ext. Joint Coating from KP 21.3 to HGCPCCOPL56258.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-PL-ME-4610 | C-56-01HG-PL-ME-5030 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.39 Ext. Joint Coating from KP 21.3 to HGCPCCOPL56258.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Ext. Joint Coating | Lowering | C-56-01HG-PL-ME-4600 | C-56-01HG-PL-ME-5000 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.39 Ext. Joint Coating from KP 21.3 to HGCPCCOPL56258.2 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-PL-ME-5020 | C-56-01HG-PL-ME-4610 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.25 Ext. Joint Coating from BVS-01 to KP 21.3CCOPL56258.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Ext. Joint Coating | Lowering | C-56-01HG-PL-ME-4400 | C-56-01HG-PL-ME-5000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.39 Ext. Joint Coating from KP 21.3 to HGCPCCOPL56258.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Ext. Joint Coating | Lowering | C-56-01HG-PL-ME-4600 | C-56-01HG-PL-ME-5000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-PL-ME-5010 | C-56-01HG-PL-ME-5020 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.25 Ext. Joint Coating from BVS-01 to KP 21.3CCOPL56258.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-PL-ME-4410 | C-56-01HG-PL-ME-5030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.39 Ext. Joint Coating from KP 21.3 to HGCPCCOPL56258.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-PL-ME-4610 | C-56-01HG-PL-ME-5030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Lowering | Lowering | C-56-01HG-PL-ME-4800 | C-56-01HG-PL-ME-5000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-01HG-PL-ME-4810 | C-56-01HG-PL-ME-5010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | NDT (Tie-in Joint) | NDT (Tie-in Joint) | C-56-01HG-PL-ME-4820 | C-56-01HG-PL-ME-5020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Holiday Testing | Holiday Testing | C-56-01HG-PL-ME-4830 | C-56-01HG-PL-ME-5030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.17 Cold Bends from BVS-01 to KP 21.3CCOPL56255.1 | Lowering | Cold Bends | C-56-01HG-PL-ME-4800 | C-56-01HG-PL-ME-3200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | Holiday Testing | Padding | C-56-01HG-PL-ME-4830 | C-56-01HG-PL-CI-6000 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.41 Padding from KP 21.3 to HGCPCCOPL56251.2 | Holiday Testing | Padding | C-56-01HG-PL-ME-4830 | C-56-01HG-PL-CI-6200 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.41 Padding from KP 21.3 to HGCPCCOPL56251.2 | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Padding | Cleaning & Gauging | C-56-01HG-PL-CI-6200 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.41 Padding from KP 21.3 to HGCPCCOPL56251.2 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Padding | Precommissioning | C-56-01HG-PL-CI-6200 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.41 Padding from KP 21.3 to HGCPCCOPL56251.2 | Holiday Testing | Padding | C-56-01HG-PL-ME-5030 | C-56-01HG-PL-CI-6200 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.41 Padding from KP 21.3 to HGCPCCOPL56251.2 | Holiday Testing | Padding | C-56-01HG-PL-ME-4830 | C-56-01HG-PL-CI-6200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.41 Padding from KP 21.3 to HGCPCCOPL56251.2 | Holiday Testing | Padding | C-56-01HG-PL-ME-5030 | C-56-01HG-PL-CI-6200 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.41 Padding from KP 21.3 to HGCPCCOPL56251.2 | Padding | Padding | C-56-01HG-PL-CI-6000 | C-56-01HG-PL-CI-6200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.7 Fire Point Shelters CCOHBSS301 | P2543-R01-Oct24..4.3.1.1.1.12.1.8 Pipe Supports Fabrication & Installation CCOHBSS300 | Fire Point SheltersCCOHBSS301 (Deleted) | Pre-Fabrication & Installation of Pipe Supports | C-56-PL-607-CI-2400 | C-56-PL-607-CI-2000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS304 | P2543-R01-Oct24..4.3.1.1.1.12.1.12 Installation of Fence Type-4CCOHBCS206.1 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Installation of Fence Type-4 (Deleted) | C-56-PL-607-CI-3010 | C-56-PL-607-CI-2220 | FF | Not Started | Not Started | 21
P2543-R01-Oct24..4.3.1.1.1.12.1.12 Installation of Fence Type-4CCOHBCS206.1 | P2543-R01-Oct24..4.3.1.1.1.12.1.14 Paving WorksCCOHBCS208 | Installation of Fence Type-4 (Deleted) | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PL-607-CI-2220 | C-56-PL-607-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.12 Installation of Fence Type-4CCOHBCS206.1 | P2543-R01-Oct24..4.3.1.1.1.12.1.15 Installation of 6m wide double leaf vehicular access gatesCCOHBCS206.2 | Installation of Fence Type-4 (Deleted) | Installation of 6m wide double leaf vehicular access gates (Deleted) | C-56-PL-607-CI-2220 | C-56-PL-607-CI-2230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.15 Installation of 6m wide double leaf vehicular access gatesCCOHBCS206.2 | P2543-R01-Oct24..4.3.1.1.1.12.1.16 Installation of 1m wide single leaf vehicular access gatesCCOHBCS206.3 | Installation of 6m wide double leaf vehicular access gates (Deleted) | Installation of 1m wide single leaf vehicular access gates (Deleted) | C-56-PL-607-CI-2230 | C-56-PL-607-CI-2240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.16 Installation of 1m wide single leaf vehicular access gatesCCOHBCS206.3 | P2543-R01-Oct24..4.3.1.1.1.12.1.14 Paving WorksCCOHBCS208 | Installation of 1m wide single leaf vehicular access gates (Deleted) | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PL-607-CI-2240 | C-56-PL-607-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.3.1 Installation of Pig Launcher (607-V-603)CCOHBME303 | P2543-R01-Oct24..4.3.1.1.1.12.3.2 Installation of Pig Signaler (607-V-603)CCOHBME318 | Installation of Pig Launcher (607-V-603) 56" | Installation of Pig Signaler (607-V-603)CCOHBME318 (Deleted) | C-56-PL-607-ME-1000 | C-56-PL-607-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.3.2 Installation of Pig Signaler (607-V-603)CCOHBME318 | P2543-R01-Oct24..4.3.1.1.1.12.3.3 Installation of Filter PackageCCOHBME328 | Installation of Pig Signaler (607-V-603)CCOHBME318 (Deleted) | Installation of Filter PackageCCOHBME328 (Deleted) | C-56-PL-607-ME-1200 | C-56-PL-607-ME-1400 | FS | Not Started | Not Started | 10
P2543-R01-Oct24..4.3.1.1.1.12.3.3 Installation of Filter PackageCCOHBME328 | P2543-R01-Oct24..4.3.1.1.1.12.3.4 Installation of Fire Fighting & Safety EquipmentCCOHBME338 | Installation of Filter PackageCCOHBME328 (Deleted) | Installation of Fire Fighting & Safety EquipmentCCOHBME338 (Deleted) | C-56-PL-607-ME-1400 | C-56-PL-607-ME-1600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.3.4 Installation of Fire Fighting & Safety EquipmentCCOHBME338 | P2543-R01-Oct24..4.3.1.1.1.12.4.3 Field Joint Welding & NDTCCOHBPI332 | Installation of Fire Fighting & Safety EquipmentCCOHBME338 (Deleted) | NDT & Coating for Field Joint Weld | C-56-PL-607-ME-1600 | C-56-PL-607-PI-1410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Installation RTU | Telephone SystemCCOHBIC221 (Deleted) | C-56-PL-607-EI-1600 | C-56-PL-607-TE-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Telephone SystemCCOHBIC221 (Deleted) | FO Cable OTDR Testing & Splicing | C-56-PL-607-TE-1400 | C-56-PL-607-TE-1420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | P2543-R01-Oct24..4.3.1.1.2.12.2.2 Inergen SystemCCOHBME348 | HVAC Works | Inergen SystemCCOHBME348 (Deleted) | C-56-EB2-ME-1010 | C-56-EB2-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.2.2 Inergen SystemCCOHBME348 | P2543-R01-Oct24..4.3.1.1.2.12.3.6 HSSD SystemCCOHBEL283 | Inergen SystemCCOHBME348 (Deleted) | Installation of HSSD System | C-56-EB2-ME-1200 | C-56-EB2-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.40.3 Concrete WorksCCOHBCS302 | P2543-R01-Oct24..4.3.1.1.3.10.40.4 Concrete ProtectionCCOHBCS304 | Concrete Works for Pipe Support Foundations | Concrete ProtectionCCOHBCS304 (Deleted) | C-56-G-HT-CI-1600 | C-56-G-HT-CI-1700 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..4.3.1.1.3.10.40.6 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS310 | P2543-R01-Oct24..4.3.1.1.3.10.40.4 Concrete ProtectionCCOHBCS304 | Concrete Works for Access Platforms & Misc. Structural Foundations | Concrete ProtectionCCOHBCS304 (Deleted) | C-56-G-HT-CI-1420 | C-56-G-HT-CI-1700 | FF | Not Started | In Progress | 1
P2543-R01-Oct24..4.3.1.1.3.10.40.4 Concrete ProtectionCCOHBCS304 | P2543-R01-Oct24..4.3.1.1.3.10.40.7 Paving WorksCCOHBCS305 | Concrete ProtectionCCOHBCS304 (Deleted) | Paving of Interlock tiles & Kerb Stone Embankment | C-56-G-HT-CI-1700 | C-56-G-HT-CI-2600 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Installation of Test Post for Crossing | Installation of CP JB's | C-56-01HG-PL-CA-5420 | C-56-01HG-PL-CA-5430 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Installation of CP JB's | Installation of CP TR | C-56-01HG-PL-CA-5430 | C-56-01HG-PL-CA-5440 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Installation of CP TR | CIP/DCVG Survey (Pre-Com) | C-56-01HG-PL-CA-5440 | C-56-01HG-PL-CA-5450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA01-1070 | C-56-01HG-PL-CA-5420 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA02-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA03-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA04-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA05-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA06-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA07-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA08-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA09-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA10-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA11-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA12-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA13-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA14-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA15-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA23-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA24-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA25-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA26-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA27-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA21-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA22-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA19-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA17-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA20-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA16-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding | Installation of Test Post for Crossing | C-56-01HG-CMA18-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME01-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME02-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME03-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME04-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME05-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME06-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME07-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME08-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME09-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-01HG-CME10-1070 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.2 Tunneling & Jack UpCCOPL57962 | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-56-01HG-CNM13-1220 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.2 Tunneling & Jack UpCCOPL57602 | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-56-01HG-CNM12-1220 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.3.2 Tunneling & Jack UpCCOPL57262 | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-56-01HG-CNM11-1220 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.6.4.2 Tunneling & Jack UpCCOPL58342 | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-56-01HG-CNH10-1220 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | CIP/DCVG Survey (Pre-Com) | Precommissioning | C-56-01HG-PL-CA-5450 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.26 Test Stations & Anode Beds from BVS-01 to KP 21.3CCOP56EL24.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Glanding & Termination of Temp. CP S/m | CIP/DCVG Survey (Pre-Com) | C-56-01HG-PL-CA-5620 | C-56-01HG-PL-CA-5450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Installation of Test Post for Crossing | Installation of Test Post for Crossing | C-56-01HG-PL-CA-5220 | C-56-01HG-PL-CA-5420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Installation of CP JB's | Installation of CP JB's | C-56-01HG-PL-CA-5230 | C-56-01HG-PL-CA-5430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Installation of CP TR | Installation of CP TR | C-56-01HG-PL-CA-5240 | C-56-01HG-PL-CA-5440 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | CIP/DCVG Survey (Pre-Com) | CIP/DCVG Survey (Pre-Com) | C-56-01HG-PL-CA-5250 | C-56-01HG-PL-CA-5450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.26 Test Stations & Anode Beds from BVS-01 to KP 21.3CCOP56EL24.1 | Holiday Testing | Installation of Temp. Anode | C-56-01HG-PL-ME-4830 | C-56-01HG-PL-CA-5600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.26 Test Stations & Anode Beds from BVS-01 to KP 21.3CCOP56EL24.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.26 Test Stations & Anode Beds from BVS-01 to KP 21.3CCOP56EL24.1 | Installation of Temp. Anode | Installation of CP Test Post | C-56-01HG-PL-CA-5600 | C-56-01HG-PL-CA-5610 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.46 Test Stations & Anode Beds from KP 21.3 to HGCPCCOP56EL24.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.46 Test Stations & Anode Beds from KP 21.3 to HGCPCCOP56EL24.2 | Installation of Temp. Anode | Installation of CP Test Post | C-56-01HG-PL-CA-5800 | C-56-01HG-PL-CA-5810 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.46 Test Stations & Anode Beds from KP 21.3 to HGCPCCOP56EL24.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.46 Test Stations & Anode Beds from KP 21.3 to HGCPCCOP56EL24.2 | Installation of CP Test Post | Glanding & Termination of Temp. CP S/m | C-56-01HG-PL-CA-5810 | C-56-01HG-PL-CA-5820 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.46 Test Stations & Anode Beds from KP 21.3 to HGCPCCOP56EL24.2 | Holiday Testing | Installation of Temp. Anode | C-56-01HG-PL-ME-5030 | C-56-01HG-PL-CA-5800 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.46 Test Stations & Anode Beds from KP 21.3 to HGCPCCOP56EL24.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Glanding & Termination of Temp. CP S/m | CIP/DCVG Survey (Pre-Com) | C-56-01HG-PL-CA-5820 | C-56-01HG-PL-CA-5450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.46 Test Stations & Anode Beds from KP 21.3 to HGCPCCOP56EL24.2 | Holiday Testing | Installation of Temp. Anode | C-56-01HG-PL-ME-5030 | C-56-01HG-PL-CA-5800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.46 Test Stations & Anode Beds from KP 21.3 to HGCPCCOP56EL24.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.46 Test Stations & Anode Beds from KP 21.3 to HGCPCCOP56EL24.2 | Installation of Temp. Anode | Installation of CP Test Post | C-56-01HG-PL-CA-5800 | C-56-01HG-PL-CA-5810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.26 Test Stations & Anode Beds from BVS-01 to KP 21.3CCOP56EL24.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.46 Test Stations & Anode Beds from KP 21.3 to HGCPCCOP56EL24.2 | Installation of CP Test Post | Installation of CP Test Post | C-56-01HG-PL-CA-5610 | C-56-01HG-PL-CA-5810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.26 Test Stations & Anode Beds from BVS-01 to KP 21.3CCOP56EL24.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.46 Test Stations & Anode Beds from KP 21.3 to HGCPCCOP56EL24.2 | Glanding & Termination of Temp. CP S/m | Glanding & Termination of Temp. CP S/m | C-56-01HG-PL-CA-5620 | C-56-01HG-PL-CA-5820 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2.4 ROW Restoration from BVS-01 to HGCP/Marker PostCCOPL52324.1 | P2543-R01-Oct24..4.3.2.3.10.8.2.6 ROW Restoration from HGCP to KP 16.7 (Deleted SOW)CCOPL52324.3 | Installation of Marker Post/Sign Board | Installation of Crash Barriers (If any) (Deleted SOW) | C-52-HG01-PL-CI-7800 | C-52-HG01-PL-CI-7820 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.2.3.10.8.2.6 ROW Restoration from HGCP to KP 16.7 (Deleted SOW)CCOPL52324.3 | P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | Installation of Crash Barriers (If any) (Deleted SOW) | Pre-commissioning from HGCP to BVS-01 | C-52-HG01-PL-CI-7820 | PRECOM-52-HG01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.33 Backfilling from BVS-01 to KP 21.3CCOPL56231.1 | Padding | Backfilling from BVS-01 to KP 21.3 | C-56-01HG-PL-CI-6000 | C-56-01HG-PL-CI-6400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.41 Padding from KP 21.3 to HGCPCCOPL56251.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.43 Backfilling from KP 21.3 to HGCPCCOPL56231.2 | Padding | Backfilling from KP 21.3 to HGCP | C-56-01HG-PL-CI-6200 | C-56-01HG-PL-CI-6600 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Padding | Gatch Laying & Levelling | C-56-01HG-PL-CI-6000 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Gatch Laying & Levelling | Gatch Compaction | C-56-01HG-PL-CI-7000 | C-56-01HG-PL-CI-7010 | SS | Not Started | Not Started | 10
P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-PL-CI-6000 | C-56-01HG-PL-CI-7000 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA01-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA02-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA03-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA04-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA05-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA06-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA07-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA08-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA09-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA10-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA11-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA12-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA13-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA14-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA15-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA23-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA24-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA25-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA26-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA27-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA21-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA22-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA19-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA17-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA20-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA16-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-CMA18-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME01-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME02-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME03-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME04-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME05-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME06-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME07-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME08-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME09-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-01HG-CME10-1070 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57992 | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-56-01HG-CNM13-1800 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | P2543-R01-Oct24..4.3.2.2.2.3.1.4 ROW Restoration/Marker Post/Crash BarrierCCOPL56229 | Gatch Compaction | ROW Restoration/ Installation of Marker Post/Sign Board | C-56-01HG-PL-CI-7010 | C-56-01HG-PL-CI-7800 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Gatch Compaction | Precommissioning | C-56-01HG-PL-CI-7010 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.41 Padding from KP 21.3 to HGCPCCOPL56251.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-PL-CI-6200 | C-56-01HG-PL-CI-7000 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-PL-CI-6000 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.41 Padding from KP 21.3 to HGCPCCOPL56251.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Padding | Gatch Laying & Levelling | C-56-01HG-PL-CI-6200 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Gatch Compaction | Gatch Compaction | C-56-01HG-PL-CI-6810 | C-56-01HG-PL-CI-7010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.18.21.1.10 ROW Access Road from BVS-05 to KP 126.2CCOPL52440.2 | Survey Marking BVS-05 to BVS-06 | Sabka ROW/Grading | C-52-0506-PL-CI-1000 | C-52-0506-PL-CI-1900 | SS | Completed | Not Started | 3
P2543-R01-Oct24..4.3.1.3.18.21.1.10 ROW Access Road from BVS-05 to KP 126.2CCOPL52440.2 | P2543-R01-Oct24..4.3.1.3.18.21.1.11 Pipe StringingCCOPL52441 | Sabka ROW/Grading | Stringing (BVS-05 to BVS-06) | C-52-0506-PL-CI-1900 | C-52-0506-PL-ME-2800 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.18.21.1.8 Cut & Fill in Sandy Area from KP 126.2 to BVS-06CCOPL52466.2 | P2543-R01-Oct24..4.3.1.3.18.21.1.9 Excavation (incl Bedding)CCOPL52455 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-52-0506-PL-CI-1600 | C-52-0506-PL-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.8 Cut & Fill in Sandy Area from KP 126.2 to BVS-06CCOPL52466.2 | P2543-R01-Oct24..4.3.1.3.18.21.1.11 Pipe StringingCCOPL52441 | Cut & Fill (@ Non-Sabkha) | Stringing (BVS-05 to BVS-06) | C-52-0506-PL-CI-1600 | C-52-0506-PL-ME-2800 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.18.21.1.10 ROW Access Road from BVS-05 to KP 126.2CCOPL52440.2 | P2543-R01-Oct24..4.3.1.3.18.21.1.8 Cut & Fill in Sandy Area from KP 126.2 to BVS-06CCOPL52466.2 | Sabka ROW/Grading | Cut & Fill (@ Non-Sabkha) | C-52-0506-PL-CI-1900 | C-52-0506-PL-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.33 Backfilling from BVS-01 to KP 21.3CCOPL56231.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Backfilling from BVS-01 to KP 21.3 | Gatch Laying & Levelling | C-56-01HG-PL-CI-6400 | C-56-01HG-PL-CI-6800 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.41 Padding from KP 21.3 to HGCPCCOPL56251.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.43 Backfilling from KP 21.3 to HGCPCCOPL56231.2 | Padding | Backfilling from KP 21.3 to HGCP | C-56-01HG-PL-CI-6200 | C-56-01HG-PL-CI-6600 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.43 Backfilling from KP 21.3 to HGCPCCOPL56231.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Backfilling from KP 21.3 to HGCP | Gatch Laying & Levelling | C-56-01HG-PL-CI-6600 | C-56-01HG-PL-CI-7000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-PL-CI-6000 | C-56-01HG-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | FO - Cable Pulling/ Laying | Termination/Splicing @ BVS | C-56-01HG-PL-TE-8400 | C-56-01HG-PL-TE-8410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-PL-CI-6000 | C-56-01HG-PL-TE-8400 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA01-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA02-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA03-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA04-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA05-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA06-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA07-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA08-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA09-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA10-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA11-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA12-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA13-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA14-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA15-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA23-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA24-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA25-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA26-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA27-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA21-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA22-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA19-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA17-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA20-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA16-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-CMA18-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME01-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME02-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME03-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME04-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME05-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME06-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME07-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME08-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME09-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-01HG-CME10-1070 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.2 Tunneling & Jack UpCCOPL57962 | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Inner Grout b/w Main & RC Pipe | FO - Cable Pulling/ Laying | C-56-01HG-CNM13-1220 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.2 Tunneling & Jack UpCCOPL57602 | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Inner Grout b/w Main & RC Pipe | FO - Cable Pulling/ Laying | C-56-01HG-CNM12-1220 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.3.2 Tunneling & Jack UpCCOPL57262 | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Inner Grout b/w Main & RC Pipe | FO - Cable Pulling/ Laying | C-56-01HG-CNM11-1220 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Termination/Splicing @ BVS | Precommissioning | C-56-01HG-PL-TE-8410 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.41 Padding from KP 21.3 to HGCPCCOPL56251.2 | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-PL-CI-6200 | C-56-01HG-PL-TE-8400 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-PL-CI-6000 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.41 Padding from KP 21.3 to HGCPCCOPL56251.2 | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Padding | FO - Cable Pulling/ Laying | C-56-01HG-PL-CI-6200 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | FO - Cable Pulling/ Laying | FO - Cable Pulling/ Laying | C-56-01HG-PL-TE-8200 | C-56-01HG-PL-TE-8400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Termination/Splicing @ BVS | Termination/Splicing @ BVS | C-56-01HG-PL-TE-8210 | C-56-01HG-PL-TE-8410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Termination/Splicing @ BVS | Gatch Compaction | C-56-01HG-PL-TE-8410 | C-56-01HG-PL-CI-7010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.7 SurveyingCCOPL56200 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.9 ROW Access RoadCCOPL56203 | Survey Marking | Non-Sabka ROW/Grading | C-56-HC01-PL-CI-1000 | C-56-HC01-PL-CI-1800 | FF | Completed | In Progress | 7
P2543-R01-Oct24..4.3.1.2.2.12.4.1.14 Excavation (incl Bedding) from KP 6 to KP 12.6CCOPL56206.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.14 Excavation (incl Bedding) from KP 6 to KP 12.6CCOPL56206.2 | Trench Excavation | Bedding | C-56-HC01-PL-CI-2600 | C-56-HC01-PL-CI-2610 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.2.2.12.4.1.8 Cut & FillCCOPL56201 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.14 Excavation (incl Bedding) from KP 6 to KP 12.6CCOPL56206.2 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-56-HC01-PL-CI-1400 | C-56-HC01-PL-CI-2600 | FF | In Progress | Not Started | 3
P2543-R01-Oct24..4.3.1.2.2.12.4.1.9 ROW Access RoadCCOPL56203 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.14 Excavation (incl Bedding) from KP 6 to KP 12.6CCOPL56206.2 | Non-Sabka ROW/Grading | Trench Excavation | C-56-HC01-PL-CI-1800 | C-56-HC01-PL-CI-2600 | SS | In Progress | Not Started | 7
P2543-R01-Oct24..4.3.1.2.2.12.4.1.9 ROW Access RoadCCOPL56203 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.14 Excavation (incl Bedding) from KP 6 to KP 12.6CCOPL56206.2 | Non-Sabka ROW/Grading | Trench Excavation | C-56-HC01-PL-CI-1800 | C-56-HC01-PL-CI-2600 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.10 Excavation (incl Bedding) from Habshan complex to KP 6CCOPL56206.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.14 Excavation (incl Bedding) from KP 6 to KP 12.6CCOPL56206.2 | Bedding | Bedding | C-56-HC01-PL-CI-2410 | C-56-HC01-PL-CI-2610 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.10 Excavation (incl Bedding) from Habshan complex to KP 6CCOPL56206.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.10 Excavation (incl Bedding) from Habshan complex to KP 6CCOPL56206.1 | Trench Excavation | Bedding | C-56-HC01-PL-CI-2400 | C-56-HC01-PL-CI-2410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.14 Excavation (incl Bedding) from KP 6 to KP 12.6CCOPL56206.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.14 Excavation (incl Bedding) from KP 6 to KP 12.6CCOPL56206.2 | Trench Excavation | Bedding | C-56-HC01-PL-CI-2600 | C-56-HC01-PL-CI-2610 | FF | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.16 Automatic WeldingCCOPL56207 | Stringing (BVS-01 to HBCMPLX) | Automatic Welding | C-56-HC01-PL-ME-2800 | C-56-HC01-PL-ME-3600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.18 Ext. Joint Coating from Habshan complex to KP 6CCOPL56210.1 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-PL-ME-4820 | C-56-HC01-PL-ME-4410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.17 NDT TestCCOPL56208 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.24 Ext. Joint Coating from KP 6 to KP 12.6CCOPL56210.2 | NDT | Ext. Joint Coating | C-56-HC01-PL-ME-4000 | C-56-HC01-PL-ME-4600 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.24 Ext. Joint Coating from KP 6 to KP 12.6CCOPL56210.2 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-PL-ME-4820 | C-56-HC01-PL-ME-4610 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.24 Ext. Joint Coating from KP 6 to KP 12.6CCOPL56210.2 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-PL-ME-4820 | C-56-HC01-PL-ME-4610 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.17 NDT TestCCOPL56208 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.18 Ext. Joint Coating from Habshan complex to KP 6CCOPL56210.1 | NDT | Ext. Joint Coating | C-56-HC01-PL-ME-4000 | C-56-HC01-PL-ME-4400 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.2.12.4.1.17 NDT TestCCOPL56208 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.24 Ext. Joint Coating from KP 6 to KP 12.6CCOPL56210.2 | NDT | Ext. Joint Coating | C-56-HC01-PL-ME-4000 | C-56-HC01-PL-ME-4600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.18 Ext. Joint Coating from Habshan complex to KP 6CCOPL56210.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.24 Ext. Joint Coating from KP 6 to KP 12.6CCOPL56210.2 | Ext. Joint Coating | Ext. Joint Coating | C-56-HC01-PL-ME-4400 | C-56-HC01-PL-ME-4600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.18 Ext. Joint Coating from Habshan complex to KP 6CCOPL56210.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.24 Ext. Joint Coating from KP 6 to KP 12.6CCOPL56210.2 | Ext. Joint Coating (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-PL-ME-4410 | C-56-HC01-PL-ME-4610 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.12 Cold BendsCCOPL56209 | Lowering | Cold Bends | C-56-HC01-PL-ME-4800 | C-56-HC01-PL-ME-3200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.18 Ext. Joint Coating from Habshan complex to KP 6CCOPL56210.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | Ext. Joint Coating | Lowering | C-56-HC01-PL-ME-4400 | C-56-HC01-PL-ME-4800 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | Lowering | Section Tie-in Welding | C-56-HC01-PL-ME-4800 | C-56-HC01-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-PL-ME-4810 | C-56-HC01-PL-ME-4820 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.18 Ext. Joint Coating from Habshan complex to KP 6CCOPL56210.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-PL-ME-4410 | C-56-HC01-PL-ME-4830 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.2.12.4.1.10 Excavation (incl Bedding) from Habshan complex to KP 6CCOPL56206.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Bedding | Lowering | C-56-HC01-PL-CI-2410 | C-56-HC01-PL-ME-5000 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Lowering | Section Tie-in Welding | C-56-HC01-PL-ME-5000 | C-56-HC01-PL-ME-5010 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-PL-ME-5010 | C-56-HC01-PL-ME-5020 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.2.2.12.4.1.18 Ext. Joint Coating from Habshan complex to KP 6CCOPL56210.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-PL-ME-4410 | C-56-HC01-PL-ME-5030 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.18 Ext. Joint Coating from Habshan complex to KP 6CCOPL56210.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Ext. Joint Coating | Lowering | C-56-HC01-PL-ME-4400 | C-56-HC01-PL-ME-5000 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA02-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA03-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA13-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA09-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA11-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA14-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA15-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA22-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA04-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA16-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA18-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA20-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA23-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA28-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA29-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA27-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA24-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA25-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA26-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA17-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA19-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA21-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA30-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA08-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA10-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA31-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA05-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA12-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA06-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA01-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CMA07-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CME01-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CME02-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CME03-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CME04-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CME05-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CME06-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CME07-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CME08-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CME09-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CME10-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CME11-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CME12-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CME13-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CME14-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CME15-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-CME16-1030 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Lowering & Welding of Carrier Pipe | Section Tie-in Welding | C-56-HC01-CNH05-1070 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Lowering & Welding of Carrier Pipe | Section Tie-in Welding | C-56-HC01-CNH02-1070 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Lowering & Welding of Carrier Pipe | Section Tie-in Welding | C-56-HC01-CNH01-1070 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.12 Cold BendsCCOPL56209 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Cold Bends | Section Tie-in Welding | C-56-HC01-PL-ME-3200 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | P2543-R01-Oct24..4.3.2.2.2.3.1.5 Evaporation PondCCOPL56225 | Section Tie-in Welding | Evaporation Pond | C-56-HC01-PL-ME-5010 | C-56-HC01-PL-CI-7200 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | P2543-R01-Oct24..4.3.1.1.1.12.5.1 Pig Launcher 607-V-603 56'' Pipeline/Piping Hook-upCCOHBPI312 | Section Tie-in Welding | Installation of Isolation Joint | C-56-HC01-PL-ME-5010 | C-56-PL-607-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | P2543-R01-Oct24..4.3.1.2.21.12.5.34 Pig Receiver 838-V-601 56'' Pipeline/ Piping Hook-up CCOH56PI51 | Section Tie-in Welding | Installation of Isolation Joint | C-56-HC01-PL-ME-5010 | C-56-PR-838-PL-1000 | FS | Not Started | Not Started | 13
P2543-R01-Oct24..4.3.1.2.2.12.4.1.14 Excavation (incl Bedding) from KP 6 to KP 12.6CCOPL56206.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Bedding | Lowering | C-56-HC01-PL-CI-2610 | C-56-HC01-PL-ME-5000 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.24 Ext. Joint Coating from KP 6 to KP 12.6CCOPL56210.2 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-PL-ME-5020 | C-56-HC01-PL-ME-4610 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.2.2.12.4.1.24 Ext. Joint Coating from KP 6 to KP 12.6CCOPL56210.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-PL-ME-4610 | C-56-HC01-PL-ME-5030 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.2.2.12.4.1.24 Ext. Joint Coating from KP 6 to KP 12.6CCOPL56210.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Ext. Joint Coating | Lowering | C-56-HC01-PL-ME-4600 | C-56-HC01-PL-ME-5000 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.24 Ext. Joint Coating from KP 6 to KP 12.6CCOPL56210.2 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-PL-ME-5020 | C-56-HC01-PL-ME-4610 | FF | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.12 Cold BendsCCOPL56209 | Lowering | Cold Bends | C-56-HC01-PL-ME-5000 | C-56-HC01-PL-ME-3200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.18 Ext. Joint Coating from Habshan complex to KP 6CCOPL56210.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Ext. Joint Coating | Lowering | C-56-HC01-PL-ME-4400 | C-56-HC01-PL-ME-5000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.24 Ext. Joint Coating from KP 6 to KP 12.6CCOPL56210.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Ext. Joint Coating | Lowering | C-56-HC01-PL-ME-4600 | C-56-HC01-PL-ME-5000 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Lowering | Section Tie-in Welding | C-56-HC01-PL-ME-5000 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-PL-ME-5010 | C-56-HC01-PL-ME-5020 | FF | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.2.2.12.4.1.18 Ext. Joint Coating from Habshan complex to KP 6CCOPL56210.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-PL-ME-4410 | C-56-HC01-PL-ME-5030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.24 Ext. Joint Coating from KP 6 to KP 12.6CCOPL56210.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-PL-ME-4610 | C-56-HC01-PL-ME-5030 | FF | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Lowering | Lowering | C-56-HC01-PL-ME-4800 | C-56-HC01-PL-ME-5000 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Section Tie-in Welding | Section Tie-in Welding | C-56-HC01-PL-ME-4810 | C-56-HC01-PL-ME-5010 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | NDT (Tie-in Joint) | NDT (Tie-in Joint) | C-56-HC01-PL-ME-4820 | C-56-HC01-PL-ME-5020 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Holiday Testing | Holiday Testing | C-56-HC01-PL-ME-4830 | C-56-HC01-PL-ME-5030 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.20 Padding from Habshan complex to KP 6CCOPL56211.1 | Holiday Testing | Padding | C-56-HC01-PL-ME-4830 | C-56-HC01-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 Padding from KP 6 to KP 12.6CCOPL56211.2 | Holiday Testing | Padding | C-56-HC01-PL-ME-4830 | C-56-HC01-PL-CI-6200 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 Padding from KP 6 to KP 12.6CCOPL56211.2 | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Padding | Cleaning & Gauging | C-56-HC01-PL-CI-6200 | C-56-HC01-PL-ME-7400 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 Padding from KP 6 to KP 12.6CCOPL56211.2 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Padding | Precommissioning | C-56-HC01-PL-CI-6200 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 Padding from KP 6 to KP 12.6CCOPL56211.2 | Holiday Testing | Padding | C-56-HC01-PL-ME-5030 | C-56-HC01-PL-CI-6200 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 Padding from KP 6 to KP 12.6CCOPL56211.2 | Holiday Testing | Padding | C-56-HC01-PL-ME-4830 | C-56-HC01-PL-CI-6200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 Padding from KP 6 to KP 12.6CCOPL56211.2 | Holiday Testing | Padding | C-56-HC01-PL-ME-5030 | C-56-HC01-PL-CI-6200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.20 Padding from Habshan complex to KP 6CCOPL56211.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 Padding from KP 6 to KP 12.6CCOPL56211.2 | Padding | Padding | C-56-HC01-PL-CI-6000 | C-56-HC01-PL-CI-6200 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.5.4.12.1.9 Pipe StringingCCOPL4"104 | P2543-R01-Oct24..4.3.1.5.4.12.1.20 Manual Welding from KP-12 to HGCP Compressor StationCCOPL4"105.2 | Stringing (HB-5 to HGCP) | Welding | C-4N-H5HG-PIPEL-2800 | C-4N-H5HG-PIPEL-3800 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.5.4.12.1.11 Manual Welding from Habshan 5 to KP-12CCOPL4"105.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.22 NDT Test from KP-12 to HGCP Compressor StationCCOPL4"107.2 | Welding | NDT | C-4N-H5HG-PIPEL-3600 | C-4N-H5HG-PIPEL-4200 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.20 Manual Welding from KP-12 to HGCP Compressor StationCCOPL4"105.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.22 NDT Test from KP-12 to HGCP Compressor StationCCOPL4"107.2 | Welding | NDT | C-4N-H5HG-PIPEL-3800 | C-4N-H5HG-PIPEL-4200 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.12 NDT Test Habshan 5 to KP-12CCOPL4"107.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.26 Ext. Joint Coating from KP-12 to HGCP Compressor StationCCOPL4"111.2 | NDT | Ext. Joint Coating | C-4N-H5HG-PIPEL-4000 | C-4N-H5HG-PIPEL-4600 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.5.4.12.1.22 NDT Test from KP-12 to HGCP Compressor StationCCOPL4"107.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.26 Ext. Joint Coating from KP-12 to HGCP Compressor StationCCOPL4"111.2 | NDT | Ext. Joint Coating | C-4N-H5HG-PIPEL-4200 | C-4N-H5HG-PIPEL-4600 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.26 Ext. Joint Coating from KP-12 to HGCP Compressor StationCCOPL4"111.2 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-PIPEL-4820 | C-4N-H5HG-PIPEL-4610 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.10 Excavation (incl Bedding)CCOPL4"106 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Bedding | Lowering | C-4N-H5HG-PIPEL-2410 | C-4N-H5HG-PIPEL-5000 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.4.12.1.21 Ext. Joint Coating from Habshan 5 to KP-12CCOPL4"111.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Ext. Joint Coating | Lowering | C-4N-H5HG-PIPEL-4400 | C-4N-H5HG-PIPEL-5000 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.5.4.12.1.26 Ext. Joint Coating from KP-12 to HGCP Compressor StationCCOPL4"111.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Ext. Joint Coating | Lowering | C-4N-H5HG-PIPEL-4600 | C-4N-H5HG-PIPEL-5000 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Lowering | Section Tie-in Welding | C-4N-H5HG-PIPEL-4800 | C-4N-H5HG-PIPEL-5010 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | P2543-R01-Oct24..4.3.1.5.2.3.12.5.10 Tie In to existing SkidCCOH5PI504 | Section Tie-in Welding | Installation of Isolation Joint | C-4N-H5HG-PIPEL-5010 | C-4N-H5-TPL-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Lowering | Section Tie-in Welding | C-4N-H5HG-PIPEL-5000 | C-4N-H5HG-PIPEL-5010 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-PIPEL-4810 | C-4N-H5HG-PIPEL-5020 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.26 Ext. Joint Coating from KP-12 to HGCP Compressor StationCCOPL4"111.2 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-PIPEL-5020 | C-4N-H5HG-PIPEL-4610 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-PIPEL-5010 | C-4N-H5HG-PIPEL-5020 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.21 Ext. Joint Coating from Habshan 5 to KP-12CCOPL4"111.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-PIPEL-4410 | C-4N-H5HG-PIPEL-5030 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | Holiday Testing | Padding | C-4N-H5HG-PIPEL-5030 | C-4N-H5HG-PIPEL-6000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.19 Test Stations & Anode BedsCCOP4"EL12 | Holiday Testing | Installation of Temp. Anode | C-4N-H5HG-PIPEL-5030 | C-4N-H5HG-PIPEL-5600 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Holiday Testing | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-PIPEL-5030 | C-4N-H5HG-PIPEL-8200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.26 Ext. Joint Coating from KP-12 to HGCP Compressor StationCCOPL4"111.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-PIPEL-4610 | C-4N-H5HG-PIPEL-5030 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | Termination/Splicing @ HGCP | C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-8210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Holiday Testing | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-PIPEL-4830 | C-4N-H5HG-PIPEL-8400 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA13-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA01-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA02-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA03-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA04-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA05-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA06-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA07-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA08-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA09-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA10-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA11-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA12-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA14-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA15-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA16-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA17-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA18-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA27-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA19-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA20-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA21-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA22-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA23-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA28-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA24-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA25-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA26-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CMA29-1070 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 HDD @ CH 0+517 - 0+556 (HDD-01) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Re-Instatement of Entry & Exit Pit | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CNH01-1030 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 HDD @ CH 1+006 - 1+056 (HDD-02) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Re-Instatement of Entry & Exit Pit | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CNH02-1030 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 HDD @ CH 2+845 - 3+029 (HDD-03) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Re-Instatement of Entry & Exit Pit | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CNH03-1030 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 HDD @ CH 4+392 - 4+477 (HDD-04) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Re-Instatement of Entry & Exit Pit | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CNH04-1030 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 HDD @ CH 9+139 - 9+322 (HDD-05) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Re-Instatement of Entry & Exit Pit | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CNH05-1030 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 HDD @ CH 10+556 - 10+647 (HDD-06) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Re-Instatement of Entry & Exit Pit | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CNH06-1030 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 HDD @ CH 12+216 - 12+275 (HDD-07) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Re-Instatement of Entry & Exit Pit | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CNH07-1030 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 HDD @ CH 16+746 - 16+764 (HDD-08) | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Re-Instatement of Entry & Exit Pit | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-CNH08-1030 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Holiday Testing | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-PIPEL-5030 | C-4N-H5HG-PIPEL-8400 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | Termination/Splicing @ HGCP | C-4N-H5HG-PIPEL-8200 | C-4N-H5HG-PIPEL-8410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Termination/Splicing @ HGCP | Precommissioning | C-4N-H5HG-PIPEL-8410 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | Termination/Splicing @ HGCP | C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-8410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Installation of Test Post for Crossing | Installation of CP JB's | C-56-HC01-PL-CA-5220 | C-56-HC01-PL-CA-5230 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Installation of CP JB's | Installation of CP TR | C-56-HC01-PL-CA-5230 | C-56-HC01-PL-CA-5240 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.33 Test Stations & Anode Beds from Habshan complex to KP 6CCOP56EL22.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Installation of Temp. Anode | Installation of CP Test Post | C-56-HC01-PL-CA-5600 | C-56-HC01-PL-CA-5430 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Installation of CP Test Post | Glanding & Termination of Temp. CP S/m | C-56-HC01-PL-CA-5430 | C-56-HC01-PL-CA-5440 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Installation of Test Post for Crossing | Installation of CP JB's | C-56-HC01-PL-CA-5400 | C-56-HC01-PL-CA-5410 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Installation of CP JB's | Installation of CP TR | C-56-HC01-PL-CA-5410 | C-56-HC01-PL-CA-5420 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Installation of CP TR | CIP/DCVG Survey | C-56-HC01-PL-CA-5420 | C-56-HC01-PL-CA-5450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Holiday Testing | Installation of Test Post for Crossing | C-56-HC01-CMA02-1060 | C-56-HC01-PL-CA-5400 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA02-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA03-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA13-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA09-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA11-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA14-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA15-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA22-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA04-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA16-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA18-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA20-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA23-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA28-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA29-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA27-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA24-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA25-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA26-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA17-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA19-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA21-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA30-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA08-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA10-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA31-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA05-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA12-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA06-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA01-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding | Installation of Test Post for Crossing | C-56-HC01-CMA07-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME01-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME02-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME03-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME04-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME05-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME06-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME07-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME08-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME09-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME10-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME11-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME12-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME13-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME14-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME15-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Padding & Back Filling | Installation of Test Post for Crossing | C-56-HC01-CME16-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.1.2 Tunneling & Jack UpCCOPL57562 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-56-HC01-CNM08-1220 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.2 Tunneling & Jack UpCCOPL58282 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-56-HC01-CNH05-1220 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.2 Tunneling & Jack UpCCOPL57522 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-56-HC01-CNM03-1220 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.2 Tunneling & Jack UpCCOPL58222 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-56-HC01-CNH02-1220 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.2 Tunneling & Jack UpCCOPL58162 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-56-HC01-CNH01-1220 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | CIP/DCVG Survey | Precommissioning | C-56-HC01-PL-CA-5450 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Glanding & Termination of Temp. CP S/m | CIP/DCVG Survey | C-56-HC01-PL-CA-5440 | C-56-HC01-PL-CA-5450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Installation of Test Post for Crossing | Installation of CP JB's | C-56-HC01-PL-CA-5400 | C-56-HC01-PL-CA-5410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Installation of CP JB's | Installation of CP TR | C-56-HC01-PL-CA-5410 | C-56-HC01-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Installation of Test Post for Crossing | Installation of Test Post for Crossing | C-56-HC01-PL-CA-5220 | C-56-HC01-PL-CA-5400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Installation of CP JB's | Installation of CP JB's | C-56-HC01-PL-CA-5230 | C-56-HC01-PL-CA-5410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Installation of CP TR | Installation of CP TR | C-56-HC01-PL-CA-5240 | C-56-HC01-PL-CA-5420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Installation of CP Test Post | Installation of CP Test Post | C-56-HC01-PL-CA-5200 | C-56-HC01-PL-CA-5430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Glanding & Termination of Temp. CP S/m | Glanding & Termination of Temp. CP S/m | C-56-HC01-PL-CA-5210 | C-56-HC01-PL-CA-5440 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | CIP/DCVG Survey | CIP/DCVG Survey | C-56-HC01-PL-CA-5250 | C-56-HC01-PL-CA-5450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.38 Test Stations & Anode Beds from KP 6 to KP 12.6CCOP56EL22.2 | Holiday Testing | Installation of Temp. Anode | C-56-HC01-PL-ME-4830 | C-56-HC01-PL-CA-5800 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.38 Test Stations & Anode Beds from KP 6 to KP 12.6CCOP56EL22.2 | Holiday Testing | Installation of Temp. Anode | C-56-HC01-PL-ME-5030 | C-56-HC01-PL-CA-5800 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.2.12.4.1.38 Test Stations & Anode Beds from KP 6 to KP 12.6CCOP56EL22.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Installation of Temp. Anode | Installation of CP Test Post | C-56-HC01-PL-CA-5800 | C-56-HC01-PL-CA-5430 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.33 Test Stations & Anode Beds from Habshan complex to KP 6CCOP56EL22.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.38 Test Stations & Anode Beds from KP 6 to KP 12.6CCOP56EL22.2 | Installation of Temp. Anode | Installation of Temp. Anode | C-56-HC01-PL-CA-5600 | C-56-HC01-PL-CA-5800 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.33 Test Stations & Anode Beds from Habshan complex to KP 6CCOP56EL22.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Installation of Temp. Anode | Installation of CP Test Post | C-56-HC01-PL-CA-5600 | C-56-HC01-PL-CA-5200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.20 Padding from Habshan complex to KP 6CCOPL56211.1 | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-PL-CI-6000 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | FO - Cable Pulling/ Laying | Termination/Splicing @ BVS | C-56-HC01-PL-TE-8400 | C-56-HC01-PL-TE-8410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.20 Padding from Habshan complex to KP 6CCOPL56211.1 | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-PL-CI-6000 | C-56-HC01-PL-TE-8400 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA02-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA03-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA13-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA09-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA11-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA14-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA15-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA22-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA04-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA16-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA18-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA20-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA23-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA28-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA29-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA27-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA24-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA25-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA26-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA17-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA19-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA21-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA30-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA08-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA10-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA31-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA05-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA12-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA06-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA01-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-CMA07-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME01-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME02-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME03-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME04-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME05-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME06-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME07-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME08-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME09-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME10-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME11-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME12-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME13-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME14-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME15-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-56-HC01-CME16-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.2 Tunneling & Jack UpCCOPL58282 | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Inner Grout b/w Main & RC Pipe | FO - Cable Pulling/ Laying | C-56-HC01-CNH05-1220 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.2 Tunneling & Jack UpCCOPL57522 | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Inner Grout b/w Main & RC Pipe | FO - Cable Pulling/ Laying | C-56-HC01-CNM03-1220 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.2 Tunneling & Jack UpCCOPL58222 | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Inner Grout b/w Main & RC Pipe | FO - Cable Pulling/ Laying | C-56-HC01-CNH02-1220 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.2 Tunneling & Jack UpCCOPL58162 | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Inner Grout b/w Main & RC Pipe | FO - Cable Pulling/ Laying | C-56-HC01-CNH01-1220 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Termination/Splicing @ BVS | Precommissioning | C-56-HC01-PL-TE-8410 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 Padding from KP 6 to KP 12.6CCOPL56211.2 | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-PL-CI-6200 | C-56-HC01-PL-TE-8400 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.2.2.12.4.1.20 Padding from Habshan complex to KP 6CCOPL56211.1 | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-PL-CI-6000 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 Padding from KP 6 to KP 12.6CCOPL56211.2 | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Padding | FO - Cable Pulling/ Laying | C-56-HC01-PL-CI-6200 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | FO - Cable Pulling/ Laying | FO - Cable Pulling/ Laying | C-56-HC01-PL-TE-8200 | C-56-HC01-PL-TE-8400 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Termination/Splicing @ BVS | Termination/Splicing @ BVS | C-56-HC01-PL-TE-8210 | C-56-HC01-PL-TE-8410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | Lowering | Section Tie-in Welding | C-56-HC01-CMA20-1020 | C-56-HC01-CMA20-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | Trench Excavation | Trench Excavation | C-56-01HG-CMA01-1000 | C-56-01HG-CMA06-1000 | SS | Not Started | Not Started | 8
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | Trench Excavation | Trench Excavation | C-56-01HG-CMA01-1000 | C-56-01HG-CMA07-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | Trench Excavation | Trench Excavation | C-56-01HG-CMA02-1000 | C-56-01HG-CMA08-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | Trench Excavation | Trench Excavation | C-56-01HG-CMA03-1000 | C-56-01HG-CMA09-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | Trench Excavation | Trench Excavation | C-56-01HG-CMA04-1000 | C-56-01HG-CMA10-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | Trench Excavation | Trench Excavation | C-56-01HG-CMA05-1000 | C-56-01HG-CMA11-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | Trench Excavation | Trench Excavation | C-56-01HG-CMA06-1000 | C-56-01HG-CMA12-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | Trench Excavation | Trench Excavation | C-56-01HG-CMA07-1000 | C-56-01HG-CMA13-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | Trench Excavation | Trench Excavation | C-56-01HG-CMA08-1000 | C-56-01HG-CMA14-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | Trench Excavation | Trench Excavation | C-56-01HG-CMA09-1000 | C-56-01HG-CMA15-1000 | SS | Not Started | Not Started | 6
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | Trench Excavation | Trench Excavation | C-56-01HG-CMA10-1000 | C-56-01HG-CMA16-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | Trench Excavation | Trench Excavation | C-56-01HG-CMA11-1000 | C-56-01HG-CMA17-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | Trench Excavation | Trench Excavation | C-56-01HG-CMA12-1000 | C-56-01HG-CMA18-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | Trench Excavation | Trench Excavation | C-56-01HG-CMA13-1000 | C-56-01HG-CMA19-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | Trench Excavation | Trench Excavation | C-56-01HG-CMA14-1000 | C-56-01HG-CMA20-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | Trench Excavation | Trench Excavation | C-56-01HG-CMA15-1000 | C-56-01HG-CMA21-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | Trench Excavation | Trench Excavation | C-56-01HG-CMA16-1000 | C-56-01HG-CMA22-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | Trench Excavation | Trench Excavation | C-56-01HG-CMA17-1000 | C-56-01HG-CMA23-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | Trench Excavation | Trench Excavation | C-56-01HG-CMA18-1000 | C-56-01HG-CMA24-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | Trench Excavation | Trench Excavation | C-56-01HG-CMA19-1000 | C-56-01HG-CMA25-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | Trench Excavation | Trench Excavation | C-56-01HG-CMA20-1000 | C-56-01HG-CMA26-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | Trench Excavation | Trench Excavation | C-56-01HG-CMA21-1000 | C-56-01HG-CMA27-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Gatch Laying & Levelling | Gatch Compaction | C-56-HC01-PL-CI-7000 | C-56-HC01-PL-CI-7010 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Installation of Marker Post/Sign Board | Installation of Crash Barriers (If any) | C-56-HC01-PL-CI-8000 | C-56-HC01-PL-CI-8010 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.2.12.4.1.20 Padding from Habshan complex to KP 6CCOPL56211.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-PL-CI-6000 | C-56-HC01-PL-CI-7000 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA02-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA03-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA13-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA09-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA11-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA14-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA15-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA22-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA04-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA16-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA18-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA20-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA23-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA28-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA29-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA27-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA24-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA25-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA26-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA17-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA19-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA21-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA30-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA08-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA10-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA31-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA05-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA12-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA06-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA01-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-CMA07-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME01-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME02-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME03-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME04-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME05-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME06-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME07-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME08-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME09-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME10-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME11-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME12-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME13-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME14-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME15-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding & Back Filling | Gatch Laying & Levelling | C-56-HC01-CME16-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.3 Re-Instatement of Entry & Exit PitCCOPL58292 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-56-HC01-CNH05-1800 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.5 Re-Instatement of Entry & Exit PitCCOPL57552 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-56-HC01-CNM03-1800 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.3 Re-Instatement of Entry & Exit PitCCOPL58232 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-56-HC01-CNH02-1800 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.3 Re-Instatement of Entry & Exit PitCCOPL58172 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Gatch Laying & Levelling | C-56-HC01-CNH01-1800 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Gatch Compaction | Installation of Marker Post/Sign Board | C-56-HC01-PL-CI-7010 | C-56-HC01-PL-CI-8000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Gatch Compaction | Precommissioning | C-56-HC01-PL-CI-7010 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Installation of Crash Barriers (If any) | Precommissioning | C-56-HC01-PL-CI-8010 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 Padding from KP 6 to KP 12.6CCOPL56211.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Padding | Gatch Laying & Levelling | C-56-HC01-PL-CI-6200 | C-56-HC01-PL-CI-7000 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.2.12.4.1.20 Padding from Habshan complex to KP 6CCOPL56211.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.21 Backfilling from Habshan complex to KP 6CCOPL56217.1 | Padding | Backfilling from Habshan complex to KP 6 | C-56-HC01-PL-CI-6000 | C-56-HC01-PL-CI-6400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 Padding from KP 6 to KP 12.6CCOPL56211.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.35 Backfilling from KP 6 to KP 12.6CCOPL56217.2 | Padding | Backfilling from KP 6 to KP 12.6 | C-56-HC01-PL-CI-6200 | C-56-HC01-PL-CI-6600 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.2.12.4.1.21 Backfilling from Habshan complex to KP 6CCOPL56217.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.35 Backfilling from KP 6 to KP 12.6CCOPL56217.2 | Backfilling from Habshan complex to KP 6 | Backfilling from KP 6 to KP 12.6 | C-56-HC01-PL-CI-6400 | C-56-HC01-PL-CI-6600 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.2.12.4.1.21 Backfilling from Habshan complex to KP 6CCOPL56217.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Backfilling from Habshan complex to KP 6 | Gatch Laying & Levelling | C-56-HC01-PL-CI-6400 | C-56-HC01-PL-CI-6800 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.2.12.4.1.35 Backfilling from KP 6 to KP 12.6CCOPL56217.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Backfilling from KP 6 to KP 12.6 | Gatch Laying & Levelling | C-56-HC01-PL-CI-6600 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.2.21.12.3.19 Installation of Pig Receiver (838-V-601) CCOH56ME50 | P2543-R01-Oct24..4.3.1.2.21.12.3.20 Installation of Pig Signaler (838-V-601) CCOH56ME60 | Installation of Pig Receiver (838-V-601) 56" | Installation of Pig Signaler (838-V-601) | C-56-PR-838-ME-1100 | C-56-PR-838-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.5.34 Pig Receiver 838-V-601 56'' Pipeline/ Piping Hook-up CCOH56PI51 | P2543-R01-Oct24..4.3.1.2.21.12.3.21 Installation/ Welding of Isolation Joints, Barred Tee & Anchor Flanges CCOH56ME70 | Field Joint Welding (Piping/Pipeline Section including IJ) | Installation/ Welding of Isolation Joints, Barred Tee & Anchor FlangesCCOH56ME70 (Deleted) | C-56-PR-838-PL-1010 | C-56-PR-838-ME-1400 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.3.21 Installation/ Welding of Isolation Joints, Barred Tee & Anchor Flanges CCOH56ME70 | P2543-R01-Oct24..4.3.1.2.21.12.5.34 Pig Receiver 838-V-601 56'' Pipeline/ Piping Hook-up CCOH56PI51 | Installation/ Welding of Isolation Joints, Barred Tee & Anchor FlangesCCOH56ME70 (Deleted) | NDT for Weld Joint | C-56-PR-838-ME-1400 | C-56-PR-838-PL-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.3.20 Installation of Pig Signaler (838-V-601) CCOH56ME60 | P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | Installation of Pig Signaler (838-V-601) | Final Bolt Torquing/ Re-Instatement | C-56-PR-838-ME-1200 | C-56-PR-838-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | P2543-R01-Oct24..4.3.1.2.21.12.6.30 RTU CCOH56EL41 | Installation of F&G Device | Installation of RTUCCOH56EL41 (Deleted) | C-56-PR-838-EI-2410 | C-56-PR-838-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.30 RTU CCOH56EL41 | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Installation of RTUCCOH56EL41 (Deleted) | Loop Checking for Instruments | C-56-PR-838-EI-1600 | C-56-PR-838-EI-2040 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Earth Works for Field Instrument Foundations | Concrete Works for Field Instrument, JB Foundations | C-56-591-01-CI-1030 | C-56-591-01-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Earth Works for Light Pole, Fence & Gates Foundation | Concrete Works for Light Pole, Fence & Gates Foundation | C-56-591-01-CI-1050 | C-56-591-01-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | P2543-R01-Oct24..4.3.1.3.2.21.1.16 NDT TestCCOPL52309 | Automatic Welding-Lot1 | NDT-Lot1 | C-52-HG01-PL-ME-3600 | C-52-HG01-PL-ME-4000 | FF | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Padding | Installation of Test Post for Crossing | C-52-HG01-CMA01-1070 | C-52-HG01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Padding | Installation of Test Post for Crossing | C-52-HG01-CMA02-1070 | C-52-HG01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Padding | Installation of Test Post for Crossing | C-52-HG01-CMA03-1070 | C-52-HG01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Padding | Installation of Test Post for Crossing | C-52-HG01-CMA04-1070 | C-52-HG01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.21.2 Crossing Manual @ KP 1+281 to 1+302 (FX-01,02,PX-01) | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Padding | Installation of Test Post for Crossing | C-52-HG01-CMA05-1070 | C-52-HG01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-HG01-CME01-1070 | C-52-HG01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-HG01-CME02-1070 | C-52-HG01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-HG01-CME03-1070 | C-52-HG01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Padding | Installation of Test Post for Crossing | C-52-HG01-CMA06-1070 | C-52-HG01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.4 Crossing Manual @ KP 2+273 to 2+289 (CX-03,PX-03) | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Padding | Installation of Test Post for Crossing | C-52-HG01-CMA07-1070 | C-52-HG01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Padding -Lot1 | Installation of Test Post for Crossing | C-52-HG01-PL-CI-6000 | C-52-HG01-PL-CA-5220 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.1.2 Tunneling & Jack UpCCOPL57332 | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-52-HG01-CNM04-1220 | C-52-HG01-PL-CA-5220 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.2.2 Tunneling & Jack UpCCOPL57682 | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-52-HG01-CNM03-1220 | C-52-HG01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.3.2 Tunneling & Jack UpCCOPL58042 | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-52-HG01-CNM02-1220 | C-52-HG01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.4.2 Tunneling & Jack UpCCOPL58082 | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Inner Grout b/w Main & RC Pipe | Installation of Test Post for Crossing | C-52-HG01-CNM01-1220 | C-52-HG01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | P2543-R01-Oct24..4.3.1.3.2.21.3.2.1 Backfilling & Reinstatement for CP (for Crossings)CCOP52CS47 | Installation of CP TR | Backfilling & Reinstatement for CP (for Crossings) | C-52-HG01-PL-CA-5240 | C-52-HG01-PIPEL-5260 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.27 BermingCCOPL52316 | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Gatch Compaction | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-PL-CI-6810 | C-52-HG01-PL-ME-7400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | P2543-R01-Oct24..4.3.1.3.15.21.3.1.5 Backfilling for CP (for Crossings)CCOP52CS40 | Installation of Test Post for Crossing | Backfilling for CP (for Crossings) | C-52-0203-PL-CA-5220 | C-52-0203-PIPEL-5260 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.15.21.3.1.5 Backfilling for CP (for Crossings)CCOP52CS40 | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | Backfilling for CP (for Crossings) | Installation of CP TR | C-52-0203-PIPEL-5260 | C-52-0203-PL-CA-5240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | P2543-R01-Oct24..4.3.1.3.16.21.3.2.5 Backfilling & Reinstatement for CP (for Crossings)CCOP52CS39 | Installation of Test Post for Crossing | Backfilling & Reinstatement for CP (for Crossings) | C-52-0304-PL-CA-5220 | C-52-0304-PIPEL-5260 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.16.21.3.2.5 Backfilling & Reinstatement for CP (for Crossings)CCOP52CS39 | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Backfilling & Reinstatement for CP (for Crossings) | Installation of CP TR | C-52-0304-PIPEL-5260 | C-52-0304-PL-CA-5240 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | P2543-R01-Oct24..4.3.1.3.8.21.4.3.1 Backfilling & Reinstatement for CP (for Crossings)CCOP52CS45 | Installation of Test Post for Crossing | Backfilling & Reinstatement for CP (for Crossings) | C-52-0102-PL-CA-5220 | C-52-0102-PIPEL-5260 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.4.3.1 Backfilling & Reinstatement for CP (for Crossings)CCOP52CS45 | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Backfilling & Reinstatement for CP (for Crossings) | Installation of CP TR | C-52-0102-PIPEL-5260 | C-52-0102-PL-CA-5240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | P2543-R01-Oct24..4.3.1.3.17.21.1.23 BackfillingCCOPL52422 | Padding | Backfilling | C-52-0405-PL-CI-6000 | C-52-0405-PL-CI-6400 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.17.21.1.23 BackfillingCCOPL52422 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Backfilling | Gatch Compaction | C-52-0405-PL-CI-6400 | C-52-0405-PL-CI-6810 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.17.21.2.7.1 Entry & Exit Pit ConstructionCCOPL52918 | P2543-R01-Oct24..4.3.1.3.17.21.2.7.2 Tunneling & Jack UpCCOPL57372 | Trench Excavation | Bedding | C-52-0405-CME11-1000 | C-52-0405-CME11-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.7.2 Tunneling & Jack UpCCOPL57372 | P2543-R01-Oct24..4.3.1.3.17.21.2.7.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57382 | Bedding | Lowering | C-52-0405-CME11-1010 | C-52-0405-CME11-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.7.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57382 | P2543-R01-Oct24..4.3.1.3.17.21.2.7.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57382 | Lowering | Section Tie-in Welding | C-52-0405-CME11-1020 | C-52-0405-CME11-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.7.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57382 | P2543-R01-Oct24..4.3.1.3.17.21.2.7.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57382 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CME11-1030 | C-52-0405-CME11-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.7.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57382 | P2543-R01-Oct24..4.3.1.3.17.21.2.7.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57382 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME11-1040 | C-52-0405-CME11-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.7.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57382 | P2543-R01-Oct24..4.3.1.3.17.21.2.7.4 HydrotestingCCOPL57392 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CME11-1050 | C-52-0405-CME11-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.7.4 HydrotestingCCOPL57392 | P2543-R01-Oct24..4.3.1.3.17.21.2.7.5 Re-Instatement of Entry & Exit PitCCOPL57402 | Holiday Testing | Padding & Back Filling | C-52-0405-CME11-1060 | C-52-0405-CME11-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.7.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57382 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CME11-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.7.5 Re-Instatement of Entry & Exit PitCCOPL57402 | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0405-CME11-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.7.5 Re-Instatement of Entry & Exit PitCCOPL57402 | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0405-CME11-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.7.5 Re-Instatement of Entry & Exit PitCCOPL57402 | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding & Back Filling | Cleaning & Gauging | C-52-0405-CME11-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.7.5 Re-Instatement of Entry & Exit PitCCOPL57402 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0405-CME11-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.5.1 Entry & Exit Pit ConstructionCCOPL52912 | P2543-R01-Oct24..4.3.1.3.17.21.2.5.2 Tunneling & Jack UpCCOPL57062 | Trench Excavation | Bedding | C-52-0405-CME10-1000 | C-52-0405-CME10-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.5.2 Tunneling & Jack UpCCOPL57062 | P2543-R01-Oct24..4.3.1.3.17.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57072 | Bedding | Lowering | C-52-0405-CME10-1010 | C-52-0405-CME10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57072 | P2543-R01-Oct24..4.3.1.3.17.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57072 | Lowering | Section Tie-in Welding | C-52-0405-CME10-1020 | C-52-0405-CME10-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57072 | P2543-R01-Oct24..4.3.1.3.17.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57072 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CME10-1030 | C-52-0405-CME10-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57072 | P2543-R01-Oct24..4.3.1.3.17.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57072 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME10-1040 | C-52-0405-CME10-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57072 | P2543-R01-Oct24..4.3.1.3.17.21.2.5.4 HydrotestingCCOPL57082 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CME10-1050 | C-52-0405-CME10-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.5.4 HydrotestingCCOPL57082 | P2543-R01-Oct24..4.3.1.3.17.21.2.5.5 Re-Instatement of Entry & Exit PitCCOPL57092 | Holiday Testing | Padding & Back Filling | C-52-0405-CME10-1060 | C-52-0405-CME10-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57072 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CME10-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.5.5 Re-Instatement of Entry & Exit PitCCOPL57092 | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0405-CME10-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.5.5 Re-Instatement of Entry & Exit PitCCOPL57092 | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0405-CME10-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.5.5 Re-Instatement of Entry & Exit PitCCOPL57092 | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding & Back Filling | Cleaning & Gauging | C-52-0405-CME10-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.5.5 Re-Instatement of Entry & Exit PitCCOPL57092 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0405-CME10-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52910 | P2543-R01-Oct24..4.3.1.3.17.21.2.4.2 Tunneling & Jack UpCCOPL57412 | Trench Excavation | Bedding | C-52-0405-CME09-1000 | C-52-0405-CME09-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.4.2 Tunneling & Jack UpCCOPL57412 | P2543-R01-Oct24..4.3.1.3.17.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57422 | Bedding | Lowering | C-52-0405-CME09-1010 | C-52-0405-CME09-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57422 | P2543-R01-Oct24..4.3.1.3.17.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57422 | Lowering | Section Tie-in Welding | C-52-0405-CME09-1020 | C-52-0405-CME09-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57422 | P2543-R01-Oct24..4.3.1.3.17.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57422 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CME09-1030 | C-52-0405-CME09-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57422 | P2543-R01-Oct24..4.3.1.3.17.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57422 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME09-1040 | C-52-0405-CME09-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57422 | P2543-R01-Oct24..4.3.1.3.17.21.2.4.4 HydrotestingCCOPL57432 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CME09-1050 | C-52-0405-CME09-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.4.4 HydrotestingCCOPL57432 | P2543-R01-Oct24..4.3.1.3.17.21.2.4.5 Re-Instatement of Entry & Exit PitCCOPL57442 | Holiday Testing | Padding & Back Filling | C-52-0405-CME09-1060 | C-52-0405-CME09-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.4.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57422 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | Section Tie-in Welding | C-52-0405-CME09-1030 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.4.5 Re-Instatement of Entry & Exit PitCCOPL57442 | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0405-CME09-1070 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.4.5 Re-Instatement of Entry & Exit PitCCOPL57442 | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0405-CME09-1070 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.4.5 Re-Instatement of Entry & Exit PitCCOPL57442 | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Padding & Back Filling | Cleaning & Gauging | C-52-0405-CME09-1070 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.4.5 Re-Instatement of Entry & Exit PitCCOPL57442 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0405-CME09-1070 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.2.12.1 Entry & Exit Pit ConstructionCCOPL52948 | P2543-R01-Oct24..4.3.1.3.15.21.2.12.2 Tunneling & Jack UpCCOPL57182 | Trench Excavation | Bedding | C-52-0203-CME04-1000 | C-52-0203-CME04-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.12.2 Tunneling & Jack UpCCOPL57182 | P2543-R01-Oct24..4.3.1.3.15.21.2.12.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57192 | Bedding | Lowering | C-52-0203-CME04-1010 | C-52-0203-CME04-1020 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.12.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57192 | P2543-R01-Oct24..4.3.1.3.15.21.2.12.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57192 | Lowering | Section Tie-in Welding | C-52-0203-CME04-1020 | C-52-0203-CME04-1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.12.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57192 | P2543-R01-Oct24..4.3.1.3.15.21.2.12.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57192 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0203-CME04-1030 | C-52-0203-CME04-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.12.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57192 | P2543-R01-Oct24..4.3.1.3.15.21.2.12.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57192 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0203-CME04-1040 | C-52-0203-CME04-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.12.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57192 | P2543-R01-Oct24..4.3.1.3.15.21.2.12.4 HydrotestingCCOPL57202 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0203-CME04-1050 | C-52-0203-CME04-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.12.4 HydrotestingCCOPL57202 | P2543-R01-Oct24..4.3.1.3.15.21.2.12.5 Re-Instatement of Entry & Exit PitCCOPL57212 | Holiday Testing | Padding & Back Filling | C-52-0203-CME04-1060 | C-52-0203-CME04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.12.5 Re-Instatement of Entry & Exit PitCCOPL57212 | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | Padding & Back Filling | Installation of Test Post for Crossing | C-52-0203-CME04-1070 | C-52-0203-PL-CA-5220 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.2.12.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57192 | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Section Tie-in Welding | Section Tie-in Welding | C-52-0203-CME04-1030 | C-52-0203-PL-ME-4810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.2.12.5 Re-Instatement of Entry & Exit PitCCOPL57212 | P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | Padding & Back Filling | FO - Cable Pulling/ Laying | C-52-0203-CME04-1070 | C-52-0203-PL-TE-8200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.2.12.5 Re-Instatement of Entry & Exit PitCCOPL57212 | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Padding & Back Filling | Cleaning & Gauging | C-52-0203-CME04-1070 | C-52-0203-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.12.5 Re-Instatement of Entry & Exit PitCCOPL57212 | P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | Padding & Back Filling | Gatch Laying & Levelling | C-52-0203-CME04-1070 | C-52-0203-PL-CI-6800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | P2543-R01-Oct24..4.3.1.2.21.12.8.32 SDH Cabinet CCOH56IC20 | Installation of F&G Device | SDH Cabinet (Deleted) | C-56-PR-838-EI-2410 | C-56-PR-838-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.8.32 SDH Cabinet CCOH56IC20 | P2543-R01-Oct24..4.3.1.2.21.12.8.33 CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) CCOH56IC30 | SDH Cabinet (Deleted) | CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) (Deleted) | C-56-PR-838-TE-1000 | C-56-PR-838-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.8.33 CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) CCOH56IC30 | P2543-R01-Oct24..4.3.1.2.21.12.8.33 CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) CCOH56IC30 | CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) (Deleted) | FO Cable OTDR Testing & Splicing | C-56-PR-838-TE-1600 | C-56-PR-838-TE-1420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | P2543-R01-Oct24..4.3.1.3.18.21.4.3.1 Backfilling & Reinstatement for CP (for Crossings)CCOP52CS35 | Installation of Test Post for Crossing | Backfilling & Reinstatement for CP (for Crossings) | C-52-0506-PL-CA-5220 | C-52-0506-PIPEL-5260 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.4.3.1 Backfilling & Reinstatement for CP (for Crossings)CCOP52CS35 | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Backfilling & Reinstatement for CP (for Crossings) | Installation of CP TR | C-52-0506-PIPEL-5260 | C-52-0506-PL-CA-5240 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | P2543-R01-Oct24..4.3.1.3.17.21.3.3.1 Backfilling & Reinstatement for CP (for Crossings)CCOP52CS37 | Installation of Test Post for Crossing | Backfilling & Reinstatement for CP (for Crossings) | C-52-0405-PL-CA-5220 | C-52-0405-PIPEL-5260 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.3.3.1 Backfilling & Reinstatement for CP (for Crossings)CCOP52CS37 | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Backfilling & Reinstatement for CP (for Crossings) | Installation of CP TR | C-52-0405-PIPEL-5260 | C-52-0405-PL-CA-5240 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | P2543-R01-Oct24..4.3.1.3.19.8.1.24 BackfillingCCOPL52478 | Padding | Backfilling | C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CI-6400 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.24 BackfillingCCOPL52478 | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Backfilling | Gatch Laying & Levelling | C-52-06CR-PL-CI-6400 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 22
P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | P2543-R01-Oct24..4.3.1.3.19.8.3.1.1 Backfilling & Reinstatement for CP (for Crossings)CCOP52CS33 | Installation of Test Post for Crossing | Backfilling & Reinstatement for CP (for Crossings) | C-52-06CR-PL-CA-5220 | C-52-06CR-PIPEL-5260 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.3.1.1 Backfilling & Reinstatement for CP (for Crossings)CCOP52CS33 | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Backfilling & Reinstatement for CP (for Crossings) | Installation of CP TR | C-52-06CR-PIPEL-5260 | C-52-06CR-PL-CA-5240 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.4.1.22.3.2 Installation of Pig Receiver (839-V-101)CCOSWME508 | P2543-R01-Oct24..4.3.1.3.4.1.22.3.3 Installation of Pig Signaler (839-V-101)CCOSWME509 | Installation of Pig Receiver (839-V-101) 52" | Installation of Pig Signaler (839-V-101) | C-52-PR-839-ME-1100 | C-52-PR-839-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.3 Installation of Pig Signaler (839-V-101)CCOSWME509 | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | Installation of Pig Signaler (839-V-101) | Final Bolt Torquing/ Re-Instatement | C-52-PR-839-ME-1200 | C-52-PR-839-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.5 F&G DevicesCCOSW52E10.42 | P2543-R01-Oct24..4.3.1.3.4.1.22.3.4 Installation of Fire Fighting & Safety EquipmentCCOSWME510 | Installation of F&G Device | Installation of Fire Fighting & Safety Equipment | C-52-PR-839-EI-2410 | C-52-PR-839-ME-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.4 Installation of Fire Fighting & Safety EquipmentCCOSWME510 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Installation of Fire Fighting & Safety Equipment | Glanding & Termination | C-52-PR-839-ME-1600 | C-52-PR-839-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.10 Earth Works for Paving CCOSWCS315.1 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.12 Fences & Gates ConstructionCCOSWCS310 | Earth Works for Paving of Interlock tiles & Kerb Stone Embankment | Fences & Gates Construction | C-52-PR-839-CI-1070 | C-52-PR-839-CI-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.12 Fences & Gates ConstructionCCOSWCS310 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.13 Paving interlock & barrier installationCCOSWCS315.2 | Fences & Gates Construction | Paving of Interlock tiles & Kerb Stone Embankment | C-52-PR-839-CI-2220 | C-52-PR-839-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.7 Pipe Supports Fabrication & InstallationCCOSWSS500 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.14 Fire Point SheltersCCOSWSS504 | Pre-Fabrication & Installation of Pipe Supports | Fire Point Shelters | C-52-PR-839-CI-2000 | C-52-PR-839-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.14 Fire Point SheltersCCOSWSS504 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.15 FinishingCCOSWMC513 | Fire Point Shelters | Finishing | C-52-PR-839-CI-2400 | C-52-PR-839-CI-3200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.13 Paving interlock & barrier installationCCOSWCS315.2 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.15 FinishingCCOSWMC513 | Paving of Interlock tiles & Kerb Stone Embankment | Finishing | C-52-PR-839-CI-2600 | C-52-PR-839-CI-3200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.12 Fences & Gates ConstructionCCOSWCS310 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.15 FinishingCCOSWMC513 | Fences & Gates Construction | Finishing | C-52-PR-839-CI-2220 | C-52-PR-839-CI-3200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.15 FinishingCCOSWMC513 | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Finishing | Precommissioning Pig Receiver 839-V-101 | C-52-PR-839-CI-3200 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.2.1 HVAC System & Plumbing WorksCCOSWME511 | P2543-R01-Oct24..4.3.1.3.4.2.22.2.2 Inergen SystemCCOSWME521 | HVAC Works | Inergen System | C-52-EB1-ME-1010 | C-52-EB1-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.2.2 Inergen SystemCCOSWME521 | P2543-R01-Oct24..4.3.1.3.4.2.22.3.2 HSSD SystemCCOSW52E62 | Inergen System | Installation of HSSD System | C-52-EB1-ME-1200 | C-52-EB1-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | P2543-R01-Oct24..4.3.1.3.3.21.1.3 Pipe Supports Fabrication & InstallationCCOSWSS502 | Concrete Works for Pipe Support Foundations | Pipe Supports Fabrication & Installation | C-52-D-HT-CI-1600 | C-52-D-HT-CI-2000 | SS | Not Started | Not Started | 6
P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | P2543-R01-Oct24..4.3.1.3.3.21.1.3 Pipe Supports Fabrication & InstallationCCOSWSS502 | Concrete Works for Pipe Support Foundations | Pipe Supports Fabrication & Installation | C-52-D-HT-CI-1600 | C-52-D-HT-CI-2000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | P2543-R01-Oct24..4.3.1.3.3.21.1.4 Concrete ProtectionCCOSWCS312 | Concrete Works for Pipe Support Foundations | Concrete Protection | C-52-D-HT-CI-1600 | C-52-D-HT-CI-1700 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | P2543-R01-Oct24..4.3.1.3.3.21.1.4 Concrete ProtectionCCOSWCS312 | Concrete Works for Hot Tap Tie in Pit | Concrete Protection | C-52-D-HT-CI-1480 | C-52-D-HT-CI-1700 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.3.21.1.3 Pipe Supports Fabrication & InstallationCCOSWSS502 | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | Pipe Supports Fabrication & Installation | Piping Erection | C-52-D-HT-CI-2000 | C-52-D-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.4 Concrete ProtectionCCOSWCS312 | P2543-R01-Oct24..4.3.1.3.3.21.1.5 Fences & Gates ConstructionCCOSWCS314 | Concrete Protection | Fences & Gates Construction | C-52-D-HT-CI-1700 | C-52-D-HT-CI-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.5 Fences & Gates ConstructionCCOSWCS314 | P2543-R01-Oct24..4.3.1.3.3.21.1.6 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS510 | Fences & Gates Construction | Platforms/Crossovers/ Guardrails and Bollards/ Windsock | C-52-D-HT-CI-2220 | C-52-D-HT-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.1.6 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS510 | P2543-R01-Oct24..4.3.1.3.3.21.1.7 Paving WorksCCOSWCS316 | Platforms/Crossovers/ Guardrails and Bollards/ Windsock | Paving of Interlock tiles & Kerb Stone Embankment (Including Fence Re-Instatement) | C-52-D-HT-CI-3000 | C-52-D-HT-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | P2543-R01-Oct24..4.3.1.3.1.21.1.4 Concrete ProtectionCCOH52CS34 | Concrete Works for Equipment Foundations | Concrete Protection | C-52-PL-838-CI-1400 | C-52-PL-838-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | P2543-R01-Oct24..4.3.1.3.1.21.1.4 Concrete ProtectionCCOH52CS34 | Concrete Works for Pipe Support Foundations | Concrete Protection | C-52-PL-838-CI-1600 | C-52-PL-838-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | P2543-R01-Oct24..4.3.1.3.1.21.1.4 Concrete ProtectionCCOH52CS34 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Concrete Protection | C-52-PL-838-CI-1410 | C-52-PL-838-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | P2543-R01-Oct24..4.3.1.3.1.21.1.4 Concrete ProtectionCCOH52CS34 | Concrete Works for Access Platforms & Misc. Structural Foundations | Concrete Protection | C-52-PL-838-CI-1420 | C-52-PL-838-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.1.21.1.4 Concrete ProtectionCCOH52CS34 | P2543-R01-Oct24..4.3.1.3.1.21.1.10 Paving WorksCCOH52CS36 | Concrete Protection | Paving of Interlock tiles & Kerb Stone Embankment | C-52-PL-838-CI-1700 | C-52-PL-838-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.3.1 Installation of Pig Launcher (838-V-602)CCOH52ME60 | P2543-R01-Oct24..4.3.1.3.1.21.3.2 Installation of Pig Signaler (838-V-602)CCOH52ME70 | Installation of Pig Launcher (838-V-602) 52" | Installation of Pig Signaler (838-V-602) | C-52-PL-838-ME-1000 | C-52-PL-838-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.3.2 Installation of Pig Signaler (838-V-602)CCOH52ME70 | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Installation of Pig Signaler (838-V-602) | Final Bolt Torquing/ Re-Instatement | C-52-PL-838-ME-1200 | C-52-PL-838-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.4 RTUCCOH52EL82 | P2543-R01-Oct24..4.3.1.3.1.21.8.1 SDH CabinetCCOH52IC60 | Installation of RTU (Deleted) | SDH Cabinet (Deleted) | C-52-PL-838-EI-1600 | C-52-PL-838-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.8.1 SDH CabinetCCOH52IC60 | P2543-R01-Oct24..4.3.1.3.1.21.8.2 CCTV System (Including subcontract for FOC Splicing / Termination / Testing )CCOH52IC73 | SDH Cabinet (Deleted) | CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) (Deleted) | C-52-PL-838-TE-1000 | C-52-PL-838-TE-1600 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.2 Field InstrumentsCCOH52EL72 | P2543-R01-Oct24..4.3.1.3.1.21.6.4 RTUCCOH52EL82 | Pre-Fabrication & Installation of Field Instrument, JB Supports | Installation of RTU (Deleted) | C-52-PL-838-EI-2210 | C-52-PL-838-EI-1600 | FS | Not Started | Not Started | 25
P2543-R01-Oct24..4.3.1.3.1.21.8.2 CCTV System (Including subcontract for FOC Splicing / Termination / Testing )CCOH52IC73 | P2543-R01-Oct24..4.3.1.3.1.21.8.2 CCTV System (Including subcontract for FOC Splicing / Termination / Testing )CCOH52IC73 | CCTV System (Including subcontract for FOC Splicing / Termination / Testing ) (Deleted) | FO Cable OTDR Testing & Splicing | C-52-PL-838-TE-1600 | C-52-PL-838-TE-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.4.21.1.2 Compaction & TestingCCOH52CS39 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.4 Concrete ProtectionCCOH52CS41 | Compaction & Testing for Solar S/m Foundation | Concrete Protection | C-52-IDS1-CI-1200 | C-52-IDS1-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.7.4.21.1.2 Compaction & TestingCCOH52CS39 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.4 Concrete ProtectionCCOH52CS41 | Compaction & Testing for Field Instruments & JBs | Concrete Protection | C-52-IDS1-CI-1210 | C-52-IDS1-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.7.4.21.1.2 Compaction & TestingCCOH52CS39 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.4 Concrete ProtectionCCOH52CS41 | Compaction & Testing for CCTV Pole, Fence & Gates Foundation | Concrete Protection | C-52-IDS1-CI-1220 | C-52-IDS1-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.7.4.21.1.4 Concrete ProtectionCCOH52CS41 | P2543-R01-Oct24..4.3.1.3.7.4.21.1.5 Fences & Gates ConstructionCCOH52CS42 | Concrete Protection | Installation of Fence Post & Mesh Works (Type-3) | C-52-IDS1-CI-1700 | C-52-IDS1-CI-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.4 Concrete ProtectionCCOH52CS49 | Concrete Works for Solar S/m Foundation | Concrete Protection | C-52-IDS2-CI-1400 | C-52-IDS2-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.4 Concrete ProtectionCCOH52CS49 | Concrete Works for Field Instruments & JBs Foundation | Concrete Protection | C-52-IDS2-CI-1410 | C-52-IDS2-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.4 Concrete ProtectionCCOH52CS49 | Concrete Works for CCTV Pole, Fence & Gates Foundation | Concrete Protection | C-52-IDS2-CI-1420 | C-52-IDS2-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.7.6.21.1.4 Concrete ProtectionCCOH52CS49 | P2543-R01-Oct24..4.3.1.3.7.6.21.1.5 Fences & Gates ConstructionCCOH52CS50 | Concrete Protection | Installation of Fence Post & Mesh Works (Type-3) | C-52-IDS2-CI-1700 | C-52-IDS2-CI-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.4 Concrete ProtectionCCOH52CS57 | Concrete Works for Solar S/m Foundation | Concrete Protection | C-52-IDS3-CI-1400 | C-52-IDS3-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.4 Concrete ProtectionCCOH52CS57 | Concrete Works for Field Instruments & JBs Foundation | Concrete Protection | C-52-IDS3-CI-1410 | C-52-IDS3-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.4 Concrete ProtectionCCOH52CS57 | Concrete Works for CCTV Pole, Fence & Gates Foundation | Concrete Protection | C-52-IDS3-CI-1420 | C-52-IDS3-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.7.5.21.1.4 Concrete ProtectionCCOH52CS57 | P2543-R01-Oct24..4.3.1.3.7.5.21.1.5 Fences & Gates ConstructionCCOH52CS58 | Concrete Protection | Installation of Fence Post & Mesh Works (Type-3) | C-52-IDS3-CI-1700 | C-52-IDS3-CI-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.5 Concrete Works (Foundations for Pipe Supports)CCOJ42CS28 | P2543-R01-Oct24..4.3.1.4.12.1.7 Pipe Supports Fabrication & InstallationCCOJ42SS70 | Concrete Works for Pipe Support Foundations | Pipe Supports Fabrication & Installation | C-36-KM-HT-CI-1600 | C-36-KM-HT-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.5 Concrete Works (Foundations for Pipe Supports)CCOJ42CS28 | P2543-R01-Oct24..4.3.1.4.12.1.7 Pipe Supports Fabrication & InstallationCCOJ42SS70 | Concrete Works for Pipe Support Foundations | Pipe Supports Fabrication & Installation | C-36-KM-HT-CI-1600 | C-36-KM-HT-CI-2000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.7 Pipe Supports Fabrication & InstallationCCOJ42SS70 | P2543-R01-Oct24..4.3.1.4.12.2.1 Piping Pre-FabricationCCOJ42PI070 | Pipe Supports Fabrication & Installation | Piping Pre-Fabrication | C-36-KM-HT-CI-2000 | C-36-KM-HT-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.4 Concrete Works (Foundations for Equipment)CCOJ42CS44 | P2543-R01-Oct24..4.3.1.4.12.1.8 Fences & Gates ConstructionCCOJ42CS26 | Concrete Works for Access Platforms & Misc. Structural Foundations | Fences & Gates Construction | C-36-KM-HT-CI-1420 | C-36-KM-HT-CI-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.8 Fences & Gates ConstructionCCOJ42CS26 | P2543-R01-Oct24..4.3.1.4.12.1.9 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOJ42SS72 | Fences & Gates Construction | Platforms/Crossovers/ Guardrails and Bollards/ Windsock | C-36-KM-HT-CI-2220 | C-36-KM-HT-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.1.9 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOJ42SS72 | P2543-R01-Oct24..4.3.1.4.12.1.11 Paving WorksCCOJ42CS32 | Platforms/Crossovers/ Guardrails and Bollards/ Windsock | Paving of Interlock tiles & Kerb Stone Embankment | C-36-KM-HT-CI-3000 | C-36-KM-HT-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.6 SurveyingCCOPL4"100 | P2543-R01-Oct24..4.3.1.5.4.12.1.7 Cut & FillCCOPL4"101 | Survey Marking | Cut & Fill (@ Non-Sabkha) | C-4N-H5HG-PIPEL-1000 | C-4N-H5HG-PIPEL-1400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.8 ROW Access RoadCCOPL4"102 | P2543-R01-Oct24..4.3.1.5.4.12.1.10 Excavation (incl Bedding)CCOPL4"106 | Sabka ROW/Grading | Trench Excavation | C-4N-H5HG-PIPEL-1800 | C-4N-H5HG-PIPEL-2400 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.1.10 Excavation (incl Bedding)CCOPL4"106 | Sabka Gatch Compaction - Layer 4 | Trench Excavation | C-4N-H5HG-PIPEL-2230 | C-4N-H5HG-PIPEL-2400 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.1.9 Pipe StringingCCOPL4"104 | Sabka Gatch Compaction - Layer 4 | Stringing (HB-5 to HGCP) | C-4N-H5HG-PIPEL-2230 | C-4N-H5HG-PIPEL-2800 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.11 Manual Welding from Habshan 5 to KP-12CCOPL4"105.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.20 Manual Welding from KP-12 to HGCP Compressor StationCCOPL4"105.2 | Welding | Welding | C-4N-H5HG-PIPEL-3600 | C-4N-H5HG-PIPEL-3800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.11 Manual Welding from Habshan 5 to KP-12CCOPL4"105.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.12 NDT Test Habshan 5 to KP-12CCOPL4"107.1 | Welding | NDT | C-4N-H5HG-PIPEL-3600 | C-4N-H5HG-PIPEL-4000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.11 Manual Welding from Habshan 5 to KP-12CCOPL4"105.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.22 NDT Test from KP-12 to HGCP Compressor StationCCOPL4"107.2 | Welding | NDT | C-4N-H5HG-PIPEL-3600 | C-4N-H5HG-PIPEL-4200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.20 Manual Welding from KP-12 to HGCP Compressor StationCCOPL4"105.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.22 NDT Test from KP-12 to HGCP Compressor StationCCOPL4"107.2 | Welding | NDT | C-4N-H5HG-PIPEL-3800 | C-4N-H5HG-PIPEL-4200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.12 NDT Test Habshan 5 to KP-12CCOPL4"107.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.22 NDT Test from KP-12 to HGCP Compressor StationCCOPL4"107.2 | NDT | NDT | C-4N-H5HG-PIPEL-4000 | C-4N-H5HG-PIPEL-4200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.12 NDT Test Habshan 5 to KP-12CCOPL4"107.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.21 Ext. Joint Coating from Habshan 5 to KP-12CCOPL4"111.1 | NDT | Ext. Joint Coating | C-4N-H5HG-PIPEL-4000 | C-4N-H5HG-PIPEL-4400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.21 Ext. Joint Coating from Habshan 5 to KP-12CCOPL4"111.1 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-PIPEL-4820 | C-4N-H5HG-PIPEL-4410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.12 NDT Test Habshan 5 to KP-12CCOPL4"107.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.26 Ext. Joint Coating from KP-12 to HGCP Compressor StationCCOPL4"111.2 | NDT | Ext. Joint Coating | C-4N-H5HG-PIPEL-4000 | C-4N-H5HG-PIPEL-4600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.22 NDT Test from KP-12 to HGCP Compressor StationCCOPL4"107.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.26 Ext. Joint Coating from KP-12 to HGCP Compressor StationCCOPL4"111.2 | NDT | Ext. Joint Coating | C-4N-H5HG-PIPEL-4200 | C-4N-H5HG-PIPEL-4600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.26 Ext. Joint Coating from KP-12 to HGCP Compressor StationCCOPL4"111.2 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-PIPEL-4820 | C-4N-H5HG-PIPEL-4610 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.26 Ext. Joint Coating from KP-12 to HGCP Compressor StationCCOPL4"111.2 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-PIPEL-5020 | C-4N-H5HG-PIPEL-4610 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.21 Ext. Joint Coating from Habshan 5 to KP-12CCOPL4"111.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.26 Ext. Joint Coating from KP-12 to HGCP Compressor StationCCOPL4"111.2 | Ext. Joint Coating | Ext. Joint Coating | C-4N-H5HG-PIPEL-4400 | C-4N-H5HG-PIPEL-4600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.21 Ext. Joint Coating from Habshan 5 to KP-12CCOPL4"111.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.26 Ext. Joint Coating from KP-12 to HGCP Compressor StationCCOPL4"111.2 | Ext. Joint Coating (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-4N-H5HG-PIPEL-4410 | C-4N-H5HG-PIPEL-4610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.21 Ext. Joint Coating from Habshan 5 to KP-12CCOPL4"111.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | Ext. Joint Coating | Lowering | C-4N-H5HG-PIPEL-4400 | C-4N-H5HG-PIPEL-4800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | Lowering | Section Tie-in Welding | C-4N-H5HG-PIPEL-4800 | C-4N-H5HG-PIPEL-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-PIPEL-4810 | C-4N-H5HG-PIPEL-4820 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.21 Ext. Joint Coating from Habshan 5 to KP-12CCOPL4"111.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-PIPEL-4410 | C-4N-H5HG-PIPEL-4830 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.21 Ext. Joint Coating from Habshan 5 to KP-12CCOPL4"111.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Ext. Joint Coating | Lowering | C-4N-H5HG-PIPEL-4400 | C-4N-H5HG-PIPEL-5000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.26 Ext. Joint Coating from KP-12 to HGCP Compressor StationCCOPL4"111.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Ext. Joint Coating | Lowering | C-4N-H5HG-PIPEL-4600 | C-4N-H5HG-PIPEL-5000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Lowering | Section Tie-in Welding | C-4N-H5HG-PIPEL-4800 | C-4N-H5HG-PIPEL-5010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Lowering | Section Tie-in Welding | C-4N-H5HG-PIPEL-5000 | C-4N-H5HG-PIPEL-5010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-PIPEL-4810 | C-4N-H5HG-PIPEL-5020 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Section Tie-in Welding | NDT (Tie-in Joint) | C-4N-H5HG-PIPEL-5010 | C-4N-H5HG-PIPEL-5020 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.21 Ext. Joint Coating from Habshan 5 to KP-12CCOPL4"111.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-PIPEL-4410 | C-4N-H5HG-PIPEL-5030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.26 Ext. Joint Coating from KP-12 to HGCP Compressor StationCCOPL4"111.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-4N-H5HG-PIPEL-4610 | C-4N-H5HG-PIPEL-5030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Lowering | Lowering | C-4N-H5HG-PIPEL-4800 | C-4N-H5HG-PIPEL-5000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Section Tie-in Welding | Section Tie-in Welding | C-4N-H5HG-PIPEL-4810 | C-4N-H5HG-PIPEL-5010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | NDT (Tie-in Joint) | NDT (Tie-in Joint) | C-4N-H5HG-PIPEL-4820 | C-4N-H5HG-PIPEL-5020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Holiday Testing | Holiday Testing | C-4N-H5HG-PIPEL-4830 | C-4N-H5HG-PIPEL-5030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.1.17 BackfillingCCOPL4"115 | Padding | Backfilling | C-4N-H5HG-PIPEL-6000 | C-4N-H5HG-PIPEL-6400 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.4.12.1.17 BackfillingCCOPL4"115 | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Backfilling | Gatch Laying & Levelling | C-4N-H5HG-PIPEL-6400 | C-4N-H5HG-PIPEL-6800 | SS | Not Started | Not Started | 10
P2543-R01-Oct24..4.3.1.5.2.3.12.1.1 Demolition Works (Paving)CCOH5CS100 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | Demolition Works (Paving) | Site Survey, Preparation & Grading Works | C-4N-H5-TPL-CI-0100 | C-4N-H5-TPL-CI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.3 Piperack - Reinforced in-situ concrete for Strengthening of existing foundationsCCOH5CS102.1 | Compaction & Testing for Pipe Support Foundations | Piperack - Reinforced in-situ concrete for Strengthening of existing foundations | C-4N-H5-TPL-CI-1210 | C-4N-H5-TPL-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.3 Piperack - Reinforced in-situ concrete for Strengthening of existing foundationsCCOH5CS102.1 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.4 Piperack - Reinforced in-situ concrete for Strengthening of existing foundationsCCOH5CS102.2 | Piperack - Reinforced in-situ concrete for Strengthening of existing foundations | Piperack - Reinforced in-situ concrete for Strengthening of existing foundations | C-4N-H5-TPL-PR-1000 | C-4N-H5-TPL-PR-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.4 Piperack - Reinforced in-situ concrete for Strengthening of existing foundationsCCOH5CS102.2 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | Piperack - Reinforced in-situ concrete for Strengthening of existing foundations | Pre-Fabrication & Installation of Pipe Supports | C-4N-H5-TPL-PR-1200 | C-4N-H5-TPL-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.6 Concrete ProtectionCCOH5CS104 | Concrete Works for Equipment Foundations | Concrete Protection | C-4N-H5-TPL-CI-1400 | C-4N-H5-TPL-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.6 Concrete ProtectionCCOH5CS104 | Concrete Works for Pipe Support Foundations | Concrete Protection | C-4N-H5-TPL-CI-1600 | C-4N-H5-TPL-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.6 Concrete ProtectionCCOH5CS104 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Concrete Protection | C-4N-H5-TPL-CI-1410 | C-4N-H5-TPL-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.6 Concrete ProtectionCCOH5CS104 | Concrete Works for Access Platforms & Misc. Structural Foundations | Concrete Protection | C-4N-H5-TPL-CI-1420 | C-4N-H5-TPL-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.2.3.12.1.4 Piperack - Reinforced in-situ concrete for Strengthening of existing foundationsCCOH5CS102.2 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.6 Concrete ProtectionCCOH5CS104 | Piperack - Reinforced in-situ concrete for Strengthening of existing foundations | Concrete Protection | C-4N-H5-TPL-PR-1200 | C-4N-H5-TPL-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.2.3.12.1.6 Concrete ProtectionCCOH5CS104 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | Concrete Protection | Pre-Fabrication & Installation of Pipe Supports | C-4N-H5-TPL-CI-1700 | C-4N-H5-TPL-CI-2000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | P2543-R01-Oct24..4.3.1.5.2.3.12.9.1 Electrical Shutdown (PDBs)CCOH5ST529 | Glanding & Termination for CP S/m | Electrical Shutdown (PDBs) | C-4N-H5-TPL-CA-1030 | C-4N-H5-TPL-EL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.9.1 Electrical Shutdown (PDBs)CCOH5ST529 | P2543-R01-Oct24..4.3.1.5.2.3.12.8.1 Telecommunication Works CCOH5IC528 | Electrical Shutdown (PDBs) | FO Cable OTDR Testing & Splicing | C-4N-H5-TPL-EL-1000 | C-4N-H5-TPL-TE-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.3 Concrete ProtectionCCOH4NCS66 | Concrete Works for Equipment Foundations | Concrete Protection | C-4N-HG-TPR-CI-1400 | C-4N-HG-TPR-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.3 Concrete ProtectionCCOH4NCS66 | Concrete Works for Pipe Support Foundations | Concrete Protection | C-4N-HG-TPR-CI-1600 | C-4N-HG-TPR-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.3 Concrete ProtectionCCOH4NCS66 | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Concrete Protection | C-4N-HG-TPR-CI-1410 | C-4N-HG-TPR-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.3 Concrete ProtectionCCOH4NCS66 | Concrete Works for Access Platforms & Misc. Structural Foundations | Concrete Protection | C-4N-HG-TPR-CI-1420 | C-4N-HG-TPR-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.3 Concrete ProtectionCCOH4NCS66 | Concrete Works for Impact Wall | Concrete Protection | C-4N-HG-TPR-CI-1500 | C-4N-HG-TPR-CI-1700 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.4 Fences & Gates ConstructionCCOH4NCS67 | Pre-Fabrication & Installation of Platforms & Crossovers | Fences & Gates Construction | C-4N-HG-TPR-CI-3000 | C-4N-HG-TPR-CI-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.4 Fences & Gates ConstructionCCOH4NCS67 | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Fences & Gates Construction | C-4N-HG-TPR-CI-3010 | C-4N-HG-TPR-CI-2220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.3 Concrete ProtectionCCOH4NCS66 | P2543-R01-Oct24..4.3.1.5.1.12.1.5 Paving WorksCCOH4NCS69 | Concrete Protection | Paving of Interlock tiles & Kerb Stone Embankment | C-4N-HG-TPR-CI-1700 | C-4N-HG-TPR-CI-2600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.4 Fences & Gates ConstructionCCOH4NCS67 | P2543-R01-Oct24..4.3.1.5.1.12.1.5 Paving WorksCCOH4NCS69 | Fences & Gates Construction | Paving of Interlock tiles & Kerb Stone Embankment | C-4N-HG-TPR-CI-2220 | C-4N-HG-TPR-CI-2600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | P2543-R01-Oct24..4.3.1.6.2.12.2.2 Piping Pre-FabricationCCOH4WPI050 | Piping Works (RTP) | Piping Pre-Fabrication | C-4W-081-03-PI-1000 | C-4W-TI-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.2.2 Piping Pre-FabricationCCOH4WPI050 | P2543-R01-Oct24..4.3.1.6.2.12.2.3 ErectionCCOH4WPI060 | Piping Pre-Fabrication | Piping Installation | C-4W-TI-PI-1000 | C-4W-TI-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.2.6 Installation of ValvesCCOH4WPI090 | P2543-R01-Oct24..4.3.1.6.2.12.2.1 Final Bolt Torquing/ Re-InstatementCCOH4WPI100 | Installation of Valves | Final Bolt Torquing/ Re-Instatement | C-4W-TI-PI-1800 | C-4W-TI-PI-2000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.2.1 Final Bolt Torquing/ Re-InstatementCCOH4WPI100 | P2543-R01-Oct24..4.3.1.6.2.12.3.1 Tie - in (4'' Tie-in Connection Water Line)CCOH4WTI50 | Final Bolt Torquing/ Re-Instatement | Tie - in (4'' Tie-in Connection Water Line) | C-4W-TI-PI-2000 | C-4W-TI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.2.3 ErectionCCOH4WPI060 | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | Piping Installation | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | C-4W-TI-PI-1200 | C-DBV6-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | P2543-R01-Oct24..4.3.1.7.12.4 Shelter InstallationCCOB6S10 | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | Shelter Installation | C-DBV6-PI-1000 | C-DBV6-CI-5000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.7.12.4 Shelter InstallationCCOB6S10 | P2543-R01-Oct24..4.3.1.7.12.2.1 Electrical & Instrumentation WorksCCOB6E10 | Shelter Installation | Installation of H2S Analyser | C-DBV6-CI-5000 | C-DBV6-EI-2500 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.7.12.2.1 Electrical & Instrumentation WorksCCOB6E10 | P2543-R01-Oct24..4.3.1.8.12.2.1 Electrical & Instrumentation Works (ICSS, Feeder, FO Board...)CCOU800EL1 | Installation of H2S Analyser | Electrical & Instrumentation Works (ICSS, Feeder, FO Board...) | C-DBV6-EI-2500 | C-MAQTA-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.2.1 Electrical & Instrumentation Works (ICSS, Feeder, FO Board...)CCOU800EL1 | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Electrical & Instrumentation Works (ICSS, Feeder, FO Board...) | LV Cable Trenching | C-MAQTA-EI-1000 | C-MAQTA-CI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | P2543-R01-Oct24..4.3.1.8.12.4 ShutdownCCOU800ST4 | Installation PIDS S/m | Shutdown | C-MAQTA-TE-1020 | C-MAQTA-EL-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | P2543-R01-Oct24..4.3.1.8.12.4 ShutdownCCOU800ST4 | Telecom S/m Modification | Shutdown | C-MAQTA-TE-1010 | C-MAQTA-EL-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | P2543-R01-Oct24..4.3.1.8.12.4 ShutdownCCOU800ST4 | SCADA S/m Modification | Shutdown | C-MAQTA-TE-1000 | C-MAQTA-EL-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | P2543-R01-Oct24..4.3.1.8.12.4 ShutdownCCOU800ST4 | Glanding & Termination | Shutdown | C-MAQTA-EI-2050 | C-MAQTA-EL-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.4 ShutdownCCOU800ST4 | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Shutdown | Precommissioning | C-MAQTA-EL-2000 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.11 Pipe Stringing from HGCP to KP 16.7CCOPL52305.1 | P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | Stringing-Lot1 | Trench Excavation-Lot1 | C-52-HG01-PL-ME-2800 | C-52-HG01-PL-CI-2400 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | P2543-R01-Oct24..4.3.1.3.15.21.1.7 Excavation (incl Bedding)CCOPL52371 | Stringing (BVS-02 to BVS-03) | Trench Excavation | C-52-0203-PL-ME-2800 | C-52-0203-PL-CI-2400 | SS | Completed | Not Started | 3
P2543-R01-Oct24..4.3.1.3.8.21.1.11 Pipe StringingCCOPL52329 | P2543-R01-Oct24..4.3.1.3.8.21.1.8 Excavation (incl Bedding)CCOPL52343 | Stringing (BVS-01 to BVS-02) | Trench Excavation | C-52-0102-PL-ME-2800 | C-52-0102-PL-CI-2400 | SS | In Progress | In Progress | 7
P2543-R01-Oct24..4.3.1.3.18.21.1.11 Pipe StringingCCOPL52441 | P2543-R01-Oct24..4.3.1.3.18.21.1.9 Excavation (incl Bedding)CCOPL52455 | Stringing (BVS-05 to BVS-06) | Trench Excavation | C-52-0506-PL-ME-2800 | C-52-0506-PL-CI-2400 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.17.21.1.10 Pipe StringingCCOPL52413 | P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | Stringing (BVS-04 to BVS-05) | Trench Excavation | C-52-0405-PL-ME-2800 | C-52-0405-PL-CI-2400 | SS | In Progress | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | P2543-R01-Oct24..4.3.1.3.19.8.1.9 Excavation (incl Bedding)CCOPL52483 | Stringing (BVS-06 to SW CRS) | Trench Excavation | C-52-06CR-PL-ME-2800 | C-52-06CR-PL-CI-2400 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | P2543-R01-Oct24..4.3.1.3.18.21.1.24 BackfillingCCOPL52450 | Padding | Backfilling | C-52-0506-PL-CI-6000 | C-52-0506-PL-CI-6400 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.18.21.1.24 BackfillingCCOPL52450 | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Backfilling | Gatch Laying & Levelling | C-52-0506-PL-CI-6400 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 8
P2543-R01-Oct24..4.3.1.5.1.12.1.1 Demolition Works (Paving)CCOH4NCS64 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Demolition Works (Paving) | Site Survey, Preparation & Grading Works | C-4N-HG-TPR-CI-0100 | C-4N-HG-TPR-CI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | Site Survey, Preparation & Grading Works | Earth Works for Equipment Foundations & Hard Stand Area | C-52-598-02-CI-1000 | C-52-598-02-CI-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | Site Survey, Preparation & Grading Works | Earth Works for Equipment Foundations & Hard Stand Area | C-52-598-06-CI-1000 | C-52-598-06-CI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Earth Works for Equipment Foundations & Hard Stand Area | Concrete Works for Equipment Foundations & Hard Stand Area | C-56-591-01-CI-1010 | C-56-591-01-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.13 Concrete Works (Foundations for Pipe Supports) CCOB156C32 | Earth Works for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-56-591-01-CI-1020 | C-56-591-01-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Earth Works for Access Platforms & Misc. Structural Foundations | Concrete Works for Access Platform & Misc. Structural Foundations | C-56-591-01-CI-1040 | C-56-591-01-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Earth Works for Light Pole, Fence & Gates Foundation | Concrete Works for Light Pole, Fence & Gates Foundation | C-56-591-01-CI-1050 | C-56-591-01-CI-1430 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Sabka Gatch Laying - Layer 2 | C-56-01HG-PL-CI-2200 | C-56-01HG-PL-CI-2010 | SS | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | Sabka Gatch Compaction - Layer 2 | Sabka Gatch Laying - Layer 3 | C-56-01HG-PL-CI-2210 | C-56-01HG-PL-CI-2020 | SS | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | Sabka Gatch Compaction - Layer 3 | Sabka Gatch Laying - Layer 4 | C-56-01HG-PL-CI-2220 | C-56-01HG-PL-CI-2030 | SS | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Sabka Gatch Laying - Layer 2 | C-56-01HG-PL-CI-2200 | C-56-01HG-PL-CI-2010 | FF | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | Sabka Gatch Compaction - Layer 2 | Sabka Gatch Laying - Layer 3 | C-56-01HG-PL-CI-2210 | C-56-01HG-PL-CI-2020 | FF | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | Sabka Gatch Compaction - Layer 3 | Sabka Gatch Laying - Layer 4 | C-56-01HG-PL-CI-2220 | C-56-01HG-PL-CI-2030 | FF | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.5.4.12.1.8 ROW Access RoadCCOPL4"102 | P2543-R01-Oct24..4.3.1.5.4.12.1.7 Cut & FillCCOPL4"101 | Sabka ROW/Grading | Cut & Fill (@ Non-Sabkha) | C-4N-H5HG-PIPEL-1800 | C-4N-H5HG-PIPEL-1400 | SS | In Progress | Not Started | 5
P2543-R01-Oct24..4.3.1.3.2.21.1.7 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 1&2) CCOPL52303.2 | P2543-R01-Oct24..4.3.1.3.2.21.1.6 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 1&2)CCOPL52303.1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Sabka Gatch Laying - Layer 2 | C-52-HG01-PL-CI-2200 | C-52-HG01-PL-CI-2010 | SS | Completed | Completed | 10
P2543-R01-Oct24..4.3.1.3.2.21.1.7 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 1&2) CCOPL52303.2 | P2543-R01-Oct24..4.3.1.3.2.21.1.6 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 1&2)CCOPL52303.1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Sabka Gatch Laying - Layer 2 | C-52-HG01-PL-CI-2200 | C-52-HG01-PL-CI-2010 | FF | Completed | Completed | 10
P2543-R01-Oct24..4.3.1.3.2.21.1.7 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 1&2) CCOPL52303.2 | P2543-R01-Oct24..4.3.1.3.2.21.1.9 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 3&4)CCOPL52303.3 | Sabka Gatch Compaction - Layer 2 | Sabka Gatch Laying - Layer 3 | C-52-HG01-PL-CI-2210 | C-52-HG01-PL-CI-2020 | SS | Completed | Completed | 21
P2543-R01-Oct24..4.3.1.3.2.21.1.7 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 1&2) CCOPL52303.2 | P2543-R01-Oct24..4.3.1.3.2.21.1.9 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 3&4)CCOPL52303.3 | Sabka Gatch Compaction - Layer 2 | Sabka Gatch Laying - Layer 3 | C-52-HG01-PL-CI-2210 | C-52-HG01-PL-CI-2020 | FF | Completed | Completed | 21
P2543-R01-Oct24..4.3.1.3.2.21.1.12 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 3&4)CCOPL52303.4 | P2543-R01-Oct24..4.3.1.3.2.21.1.9 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 3&4)CCOPL52303.3 | Sabka Gatch Compaction - Layer 3 | Sabka Gatch Laying - Layer 4 | C-52-HG01-PL-CI-2220 | C-52-HG01-PL-CI-2030 | SS | Completed | Completed | 10
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Sabka Gatch Laying - Layer 2 | C-52-0203-PL-CI-2200 | C-52-0203-PL-CI-2010 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Sabka Gatch Laying - Layer 2 | C-52-0203-PL-CI-2200 | C-52-0203-PL-CI-2010 | FF | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Compaction - Layer 2 | C-52-0203-PL-CI-2010 | C-52-0203-PL-CI-2210 | FF | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Sabka Gatch Compaction - Layer 2 | Sabka Gatch Laying - Layer 3 | C-52-0203-PL-CI-2210 | C-52-0203-PL-CI-2020 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Sabka Gatch Compaction - Layer 2 | Sabka Gatch Laying - Layer 3 | C-52-0203-PL-CI-2210 | C-52-0203-PL-CI-2020 | FF | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Compaction - Layer 3 | C-52-0203-PL-CI-2020 | C-52-0203-PL-CI-2220 | FF | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Sabka Gatch Compaction - Layer 3 | Sabka Gatch Laying - Layer 4 | C-52-0203-PL-CI-2220 | C-52-0203-PL-CI-2030 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Sabka Gatch Compaction - Layer 3 | Sabka Gatch Laying - Layer 4 | C-52-0203-PL-CI-2220 | C-52-0203-PL-CI-2030 | FF | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Sabka Gatch Laying - Layer 2 | C-52-0304-PL-CI-2200 | C-52-0304-PL-CI-2010 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | Sabka Gatch Compaction - Layer 2 | Sabka Gatch Laying - Layer 3 | C-52-0304-PL-CI-2210 | C-52-0304-PL-CI-2020 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | Sabka Gatch Compaction - Layer 3 | Sabka Gatch Laying - Layer 4 | C-52-0304-PL-CI-2220 | C-52-0304-PL-CI-2030 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Sabka Gatch Laying - Layer 2 | C-52-0304-PL-CI-2200 | C-52-0304-PL-CI-2010 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | Sabka Gatch Compaction - Layer 2 | Sabka Gatch Laying - Layer 3 | C-52-0304-PL-CI-2210 | C-52-0304-PL-CI-2020 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | Sabka Gatch Compaction - Layer 3 | Sabka Gatch Laying - Layer 4 | C-52-0304-PL-CI-2220 | C-52-0304-PL-CI-2030 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.8.21.1.7 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.2 | P2543-R01-Oct24..4.3.1.3.8.21.1.6 Sabkha Pad Gatch laying from BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Sabka Gatch Laying - Layer 2 | C-52-0102-PL-CI-2200 | C-52-0102-PL-CI-2010 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.8.21.1.7 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.2 | P2543-R01-Oct24..4.3.1.3.8.21.1.6 Sabkha Pad Gatch laying from BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Sabka Gatch Laying - Layer 2 | C-52-0102-PL-CI-2200 | C-52-0102-PL-CI-2010 | FF | Completed | Completed | 3
P2543-R01-Oct24..4.3.1.3.8.21.1.7 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.2 | P2543-R01-Oct24..4.3.1.3.8.21.1.9 Sabkha Pad Gatch layingfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.3 | Sabka Gatch Compaction - Layer 2 | Sabka Gatch Laying - Layer 3 | C-52-0102-PL-CI-2210 | C-52-0102-PL-CI-2030 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.8.21.1.7 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.2 | P2543-R01-Oct24..4.3.1.3.8.21.1.9 Sabkha Pad Gatch layingfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.3 | Sabka Gatch Compaction - Layer 2 | Sabka Gatch Laying - Layer 3 | C-52-0102-PL-CI-2210 | C-52-0102-PL-CI-2030 | FF | Completed | Completed | 3
P2543-R01-Oct24..4.3.1.3.8.21.1.10 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.4 | P2543-R01-Oct24..4.3.1.3.8.21.1.9 Sabkha Pad Gatch layingfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.3 | Sabka Gatch Compaction - Layer 3 | Sabka Gatch Laying - Layer 4 | C-52-0102-PL-CI-2220 | C-52-0102-PL-CI-2040 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.8.21.1.10 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.4 | P2543-R01-Oct24..4.3.1.3.8.21.1.9 Sabkha Pad Gatch layingfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.3 | Sabka Gatch Compaction - Layer 3 | Sabka Gatch Laying - Layer 4 | C-52-0102-PL-CI-2220 | C-52-0102-PL-CI-2040 | FF | Completed | Completed | 3
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Sabka Gatch Laying - Layer 2 | C-52-0405-PL-CI-2200 | C-52-0405-PL-CI-2010 | SS | In Progress | In Progress | 5
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | Sabka Gatch Compaction - Layer 2 | Sabka Gatch Laying - Layer 3 | C-52-0405-PL-CI-2210 | C-52-0405-PL-CI-2020 | SS | In Progress | In Progress | 5
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | Sabka Gatch Compaction - Layer 3 | Sabka Gatch Laying - Layer 4 | C-52-0405-PL-CI-2220 | C-52-0405-PL-CI-2030 | SS | In Progress | In Progress | 5
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Sabka Gatch Laying - Layer 2 | C-52-0405-PL-CI-2200 | C-52-0405-PL-CI-2010 | FF | In Progress | In Progress | 5
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | Sabka Gatch Compaction - Layer 2 | Sabka Gatch Laying - Layer 3 | C-52-0405-PL-CI-2210 | C-52-0405-PL-CI-2020 | FF | In Progress | In Progress | 5
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | Sabka Gatch Compaction - Layer 3 | Sabka Gatch Laying - Layer 4 | C-52-0405-PL-CI-2220 | C-52-0405-PL-CI-2030 | FF | In Progress | In Progress | 5
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Sabka Gatch Laying - Layer 2 | C-52-06CR-PL-CI-2200 | C-52-06CR-PL-CI-2010 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | Sabka Gatch Compaction - Layer 2 | Sabka Gatch Laying - Layer 3 | C-52-06CR-PL-CI-2210 | C-52-06CR-PL-CI-2020 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | Sabka Gatch Compaction - Layer 3 | Sabka Gatch Laying - Layer 4 | C-52-06CR-PL-CI-2220 | C-52-06CR-PL-CI-2030 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Sabka Gatch Laying - Layer 2 | C-52-06CR-PL-CI-2200 | C-52-06CR-PL-CI-2010 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | Sabka Gatch Compaction - Layer 2 | Sabka Gatch Laying - Layer 3 | C-52-06CR-PL-CI-2210 | C-52-06CR-PL-CI-2020 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | Sabka Gatch Compaction - Layer 3 | Sabka Gatch Laying - Layer 4 | C-52-06CR-PL-CI-2220 | C-52-06CR-PL-CI-2030 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.5.4.12.1.17 BackfillingCCOPL4"115 | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Backfilling | Cleaning & Gauging | C-4N-H5HG-PIPEL-6400 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH4NME50 | Concrete Works for Equipment Foundations | Installation of Pig Receiver 4" | C-4N-HG-TPR-CI-1400 | C-4N-HG-TPR-ME-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.4.2 ErectionCCOH4NPI060 | Pre-Fabrication & Installation of Pipe Supports | Piping Erection | C-4N-HG-TPR-CI-2000 | C-4N-HG-TPR-PI-1200 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | P2543-R01-Oct24..4.3.1.2.21.12.1.14 Trenching for Cables CCOH56CS35 | Earth Works for Impact Wall | Electrical & Earthing Cable Trenching | C-56-PR-838-CI-1060 | C-56-PR-838-CI-1800 | FS | Not Started | Not Started | 9
P2543-R01-Oct24..4.3.1.1.1.12.4.1 Piping Pre-FabricationCCOHBPI302 | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Piping Pre-Fabrication | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-56-PL-607-PI-1000 | C-56-PL-607-EI-2210 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | P2543-R01-Oct24..4.3.1.3.4.1.22.6.4 Field InstrumentsCCOSW52E10.32 | Piping Erection | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-PR-839-PI-1200 | C-52-PR-839-EI-2210 | FF | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | P2543-R01-Oct24..4.3.1.3.1.21.6.2 Field InstrumentsCCOH52EL72 | Installation of Valves/MOV/ROV | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-PL-838-PI-1800 | C-52-PL-838-EI-2210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | P2543-R01-Oct24..4.3.1.3.14.21.6.7 Field InstrumentsCCOB652E95 | Piping Erection | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-01-PI-1200 | C-52-598-01-EI-2210 | FF | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | P2543-R01-Oct24..4.3.1.3.13.21.6.6 Field InstrumentsCCOB552E95 | Piping Erection | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-02-PI-1200 | C-52-598-02-EI-2210 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | P2543-R01-Oct24..4.3.1.3.12.21.6.6 Field InstrumentsCCOB452E93 | Piping Erection | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-03-PI-1200 | C-52-598-03-EI-2210 | FF | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | P2543-R01-Oct24..4.3.1.3.11.21.6.8 Field InstrumentsCCOB352E102 | Piping Erection | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-04-PI-1200 | C-52-598-04-EI-2210 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | P2543-R01-Oct24..4.3.1.3.10.21.6.8 Field InstrumentsCCOB252E92 | Piping Erection | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-05-PI-1200 | C-52-598-05-EI-2210 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | P2543-R01-Oct24..4.3.1.3.9.21.6.6 Field InstrumentsCCOB152E96 | Piping Erection | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-52-598-06-PI-1200 | C-52-598-06-EI-2210 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.19.1 Crossing Manual @ KP 0+63 to 0+104 (RX-01A,02A,03A,03,CX-01A,02A,03A,04A,FX-01A,02A) | Lowering-Lot1 | Lowering | C-52-HG01-PL-ME-4800 | C-52-HG01-CMA01-1020 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | Padding & Back Filling | Padding | C-52-0203-CME01-1070 | C-52-0203-PL-CI-6000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | Padding & Back Filling | Padding | C-52-0203-CME02-1070 | C-52-0203-PL-CI-6000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | Padding & Back Filling | Padding | C-52-0203-CME03-1070 | C-52-0203-PL-CI-6000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.16.1 Crossing Manual @ KP 74+821 (CX-17) | P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | Padding | Padding | C-52-0203-CMA01-1070 | C-52-0203-PL-CI-6000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.16.2 Crossing Manual @ KP 84+089 (FX-13) | P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | Padding & Back Filling | Padding | C-52-0203-CMA02-1070 | C-52-0203-PL-CI-6000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.16.21.1.15.3 Crossing Manual @ KP 88+996 (OX-04) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding | Padding | C-52-0304-CMA01-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.15.5 Crossing Manual @ KP 90+235 (OX-05) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding | Padding | C-52-0304-CMA02-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.15.12 Crossing Manual @ KP 95+763 to 95+768 (OX-06,CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding | Padding | C-52-0304-CMA03-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.1 Crossing Manual @ KP 85+318 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding | Padding | C-52-0304-CMA04-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.2 Crossing Manual @ KP 85+958 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding | Padding | C-52-0304-CMA05-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.8 Crossing Manual @ KP 93+714 (FX-16) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding | Padding | C-52-0304-CMA06-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.4 Crossing Manual @ KP 89+994 (CX-14B) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding | Padding | C-52-0304-CMA07-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.13 Crossing Manual @ KP 96+523 (FX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding | Padding | C-52-0304-CMA08-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.7 Crossing Manual @ KP 91+938 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding | Padding | C-52-0304-CMA09-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.14 Crossing Manual @ KP 97+341 (FX-18) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding | Padding | C-52-0304-CMA10-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.9 Crossing Manual @ KP 95+277 (CX-17) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding | Padding | C-52-0304-CMA11-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.10 Crossing Manual @ KP 95+304 (PX-27) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding | Padding | C-52-0304-CMA12-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.11 Crossing Manual @ KP 95+542 (CX-X1) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding | Padding | C-52-0304-CMA13-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.16.6 Crossing Manual @ KP 91+674 (FX-15) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding | Padding | C-52-0304-CMA14-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding & Back Filling | Padding | C-52-0304-CME01-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding & Back Filling | Padding | C-52-0304-CME02-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding & Back Filling | Padding | C-52-0304-CME03-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding & Back Filling | Padding | C-52-0304-CME04-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding & Back Filling | Padding | C-52-0304-CME05-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding & Back Filling | Padding | C-52-0304-CME06-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding & Back Filling | Padding | C-52-0304-CME07-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding & Back Filling | Padding | C-52-0304-CME08-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding & Back Filling | Padding | C-52-0304-CME09-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding & Back Filling | Padding | C-52-0304-CME10-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding & Back Filling | Padding | C-52-0304-CME11-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding & Back Filling | Padding | C-52-0304-CME12-1070 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.17.8 Crossing Manual @ KP 138+250 (OX-13) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding | Padding | C-52-0506-CMA01-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.4 Crossing Manual @ KP 136+961 to 136+983 (FX-40/41 & PX-36) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding | Padding | C-52-0506-CMA02-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.18.7 Crossing Manual @ KP 137+864 to 137+885 (FX-48/49 & PX-38) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding | Padding | C-52-0506-CMA03-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.3 Crossing Manual @ KP 136+575 (FX-39) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding | Padding | C-52-0506-CMA04-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.19.9 Crossing Manual @ KP 138+261 (FX-50) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding | Padding | C-52-0506-CMA05-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding & Back Filling | Padding | C-52-0506-CME01-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding & Back Filling | Padding | C-52-0506-CME02-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding & Back Filling | Padding | C-52-0506-CME03-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding & Back Filling | Padding | C-52-0506-CME04-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding & Back Filling | Padding | C-52-0506-CME05-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding & Back Filling | Padding | C-52-0506-CME06-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding & Back Filling | Padding | C-52-0506-CME07-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding & Back Filling | Padding | C-52-0506-CME08-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding & Back Filling | Padding | C-52-0506-CME09-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding & Back Filling | Padding | C-52-0506-CME10-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding | Padding | C-52-0506-CMA06-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.2 Crossing Manual @ KP 131+250, (CX-X2) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding | Padding | C-52-0506-CMA07-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.5 Crossing Manual @ KP 137+184 to 137+222 (CX-X3,X4) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding | Padding | C-52-0506-CMA08-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.21.6 Crossing Manual @ KP 137+503 to 137+660 (CX-X5,X6) | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding | Padding | C-52-0506-CMA09-1070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA01-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA02-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA03-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.15 Crossing Manual @ KP 107+124 to 107+133 (CX-40,40A,41,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA04-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.16 Crossing Manual @ KP 107+159 to 107+162 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA05-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.17 Crossing Manual @ KP 107+254 to 107+255 (CX-42,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA06-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.18 Crossing Manual @ KP 107+585 (CX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA07-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA08-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.20 Crossing Manual @ KP 108+074 to 108+074 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA09-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.21 Crossing Manual @ KP 108+723 to 108+745 (CX-44,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA10-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.22 Crossing Manual @ KP 109+580 to 109+625 (CX-X1,X2,X3,X4) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA11-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.23 Crossing Manual @ KP 109+679 (CX-45) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA12-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA13-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.25 Crossing Manual @ KP 110+339 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA14-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA15-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.28 Crossing Manual @ KP 111+032 to 111+039 (CX-48,X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA16-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.29 Crossing Manual @ KP 111+357 to 111+358 (CX-X1,X2) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA17-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.30 Crossing Manual @ KP 111+445 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA18-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.31 Crossing Manual @ KP 111+489 (CX-X1) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA19-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.3 Crossing Manual @ KP 100+684 (OX-08) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA20-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA21-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA22-1100 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA23-1100 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.16.27 Crossing Manual @ KP 110+988 (PX-35) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA24-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.2 Crossing Manual @ KP 99+898 to 99+908 (FX-19,20) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA25-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.4 Crossing Manual @ KP 100+796 (FX-21) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA26-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA27-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.10 Crossing Manual @ KP 104+230 (FX-30) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA28-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.11 Crossing Manual @ KP 104+371 (FX-31) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA29-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA30-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA31-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding | Padding | C-52-0405-CMA32-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding & Back Filling | Padding | C-52-0405-CME01-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding & Back Filling | Padding | C-52-0405-CME02-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding & Back Filling | Padding | C-52-0405-CME03-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding & Back Filling | Padding | C-52-0405-CME04-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding & Back Filling | Padding | C-52-0405-CME05-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding & Back Filling | Padding | C-52-0405-CME06-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding & Back Filling | Padding | C-52-0405-CME07-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding & Back Filling | Padding | C-52-0405-CME08-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding | Padding | C-52-06CR-CMA01-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding | Padding | C-52-06CR-CMA02-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding | Padding | C-52-06CR-CMA03-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.8 Crossing Manual @ KP 159+862 (PX-40) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding | Padding | C-52-06CR-CMA04-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.9 Crossing Manual @ KP 160+009 (FX-55) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding | Padding | C-52-06CR-CMA05-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.10 Crossing Manual @ KP 160+073 (FX-56) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding | Padding | C-52-06CR-CMA06-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.12 Crossing Manual @ KP 160+851 (FX-60) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding | Padding | C-52-06CR-CMA07-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding & Back Filling | Padding | C-52-06CR-CME01-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding & Back Filling | Padding | C-52-06CR-CME02-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding & Back Filling | Padding | C-52-06CR-CME03-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding & Back Filling | Padding | C-52-06CR-CME04-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding & Back Filling | Padding | C-52-06CR-CME05-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding & Back Filling | Padding | C-52-06CR-CME06-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding & Back Filling | Padding | C-52-06CR-CME07-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding & Back Filling | Padding | C-52-06CR-CME08-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding & Back Filling | Padding | C-52-06CR-CME09-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding & Back Filling | Padding | C-52-06CR-CME10-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding & Back Filling | Padding | C-52-06CR-CME11-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding & Back Filling | Padding | C-52-06CR-CME12-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding & Back Filling | Padding | C-52-06CR-CME13-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding & Back Filling | Padding | C-52-06CR-CME14-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.3 Crossing Manual @ KP 146+018 to 146+059 (CX-54,FX-52) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding | Padding | C-52-06CR-CMA08-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.7 Crossing Manual @ KP 158+464 to 158+595 (CX-X1,X2,X3 & X4) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding | Padding | C-52-06CR-CMA09-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding | Padding | C-52-06CR-CMA10-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding | Padding | C-52-06CR-CMA11-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding | Padding | C-52-06CR-CMA12-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding | Padding | C-52-06CR-CMA13-1070 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Concrete Works for Equipment Foundations & Hard Stand Area | Concrete Works for Field Instrument, JB Foundations | C-52-598-01-CI-1400 | C-52-598-01-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Concrete Works for Field Instrument, JB Foundations | Concrete Works for Access Platform & Misc. Structural Foundations | C-52-598-01-CI-1410 | C-52-598-01-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Concrete Works for Access Platform & Misc. Structural Foundations | Concrete Works for Light Pole, Fence & Gates Foundation | C-52-598-01-CI-1420 | C-52-598-01-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | P2543-R01-Oct24..4.3.1.3.14.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB652C37 | Concrete Works for Equipment Foundations & Hard Stand Area | Concrete Works for Pipe Support Foundations | C-52-598-01-CI-1400 | C-52-598-01-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.6 Trenching for CablesCCOSWCS311 | P2543-R01-Oct24..4.3.1.3.1.21.1.7 Trenching for Electrical cablesCCOH52CS35.1 | Electrical & Earthing Cable Trenching | Electrical & Earthing Cable Trenching | C-52-PR-839-CI-1800 | C-52-PL-838-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | P2543-R01-Oct24..4.3.1.3.14.21.1.5 Trenching for CablesCCOB652C40 | Earth Works for Light Pole, Fence & Gates Foundation | Electrical & Earthing Cable Trenching | C-52-598-01-CI-1050 | C-52-598-01-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | P2543-R01-Oct24..4.3.1.3.13.21.1.5 Trenching for CablesCCOB552C40 | Earth Works for Light Pole, Fence & Gates Foundation | Electrical & Earthing Cable Trenching | C-52-598-02-CI-1050 | C-52-598-02-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | Earth Works for Pipe Support Foundations | Earth Works for Field Instrument Foundations | C-52-598-02-CI-1020 | C-52-598-02-CI-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | Earth Works for Field Instrument Foundations | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-598-02-CI-1030 | C-52-598-02-CI-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | Earth Works for Access Platforms & Misc. Structural Foundations | Earth Works for Light Pole, Fence & Gates Foundation | C-52-598-02-CI-1040 | C-52-598-02-CI-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | Earth Works for Pipe Support Foundations | Earth Works for Field Instrument Foundations | C-52-598-03-CI-1020 | C-52-598-03-CI-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | Earth Works for Field Instrument Foundations | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-598-03-CI-1030 | C-52-598-03-CI-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | Earth Works for Access Platforms & Misc. Structural Foundations | Earth Works for Light Pole, Fence & Gates Foundation | C-52-598-03-CI-1040 | C-52-598-03-CI-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | P2543-R01-Oct24..4.3.1.3.12.21.1.6 Trenching for CablesCCOB452C39 | Earth Works for Light Pole, Fence & Gates Foundation | Electrical & Earthing Cable Trenching | C-52-598-03-CI-1050 | C-52-598-03-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | Earth Works for Pipe Support Foundations | Earth Works for Field Instrument Foundations | C-52-598-04-CI-1020 | C-52-598-04-CI-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | Earth Works for Field Instrument Foundations | Earth Works for Access Platforms & Misc. Structural Foundations | C-52-598-04-CI-1030 | C-52-598-04-CI-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | Earth Works for Access Platforms & Misc. Structural Foundations | Earth Works for Light Pole, Fence & Gates Foundation | C-52-598-04-CI-1040 | C-52-598-04-CI-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | Holiday Testing-Lot1 | Padding -Lot1 | C-52-HG01-PL-ME-4830 | C-52-HG01-PL-CI-6000 | FF | Completed | In Progress | 7
P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Holiday Testing | Padding | C-52-0304-PL-ME-4830 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | P2543-R01-Oct24..4.3.1.3.8.21.1.22 PaddingCCOPL52330 | Holiday Testing | Padding | C-52-0102-PL-ME-4830 | C-52-0102-PL-CI-6000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Holiday Testing | Padding | C-52-0506-PL-ME-4830 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.18.21.3.1.3 Re-Instatement of Entry & Exit PitCCOPL58192 | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Padding | C-52-0506-CNH27-1800 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Holiday Testing | Padding | C-52-0405-PL-ME-4830 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.4.5 Re-Instatement of Entry & Exit PitCCOPL57442 | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding & Back Filling | Padding | C-52-0405-CME09-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.5.5 Re-Instatement of Entry & Exit PitCCOPL57092 | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding & Back Filling | Padding | C-52-0405-CME10-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.7.5 Re-Instatement of Entry & Exit PitCCOPL57402 | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding & Back Filling | Padding | C-52-0405-CME11-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.10 Excavation (incl Bedding)CCOPL4"106 | P2543-R01-Oct24..4.3.1.5.4.12.1.10 Excavation (incl Bedding)CCOPL4"106 | Trench Excavation | Bedding | C-4N-H5HG-PIPEL-2400 | C-4N-H5HG-PIPEL-2410 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.8.21.1.6 Sabkha Pad Gatch laying from BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.1 | P2543-R01-Oct24..4.3.1.3.8.21.1.7 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.2 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Compaction - Layer 2 | C-52-0102-PL-CI-2010 | C-52-0102-PL-CI-2210 | FF | Completed | Completed | 3
P2543-R01-Oct24..4.3.1.3.8.21.1.6 Sabkha Pad Gatch laying from BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.1 | P2543-R01-Oct24..4.3.1.3.8.21.1.7 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.2 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-0102-PL-CI-2000 | C-52-0102-PL-CI-2200 | FF | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.8.21.1.6 Sabkha Pad Gatch laying from BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.1 | P2543-R01-Oct24..4.3.1.3.8.21.1.6 Sabkha Pad Gatch laying from BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.1 | Sabka ROW/Grading | Sabka Gatch Laying (Including ROW) - Layer 1 | C-52-0102-PL-CI-1800 | C-52-0102-PL-CI-2000 | FF | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | Sabka Gatch Compaction - Layer 4 | Stringing (BVS-02 to BVS-03) | C-52-0203-PL-CI-2230 | C-52-0203-PL-ME-2800 | FF | Completed | Completed | 3
P2543-R01-Oct24..4.3.1.3.8.21.1.17 Ext. Joint CoatingCCOPL52334 | P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0102-PL-ME-4410 | C-52-0102-PL-ME-4830 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.1.5 Trenching for CablesCCOB652C40 | P2543-R01-Oct24..4.3.1.3.14.21.1.5 Trenching for CablesCCOB652C40 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-52-598-01-CI-1800 | C-52-598-01-CI-1810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.19 Ext. Joint CoatingCCOPL52418 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-PL-ME-4410 | C-52-0405-PL-ME-4830 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | P2543-R01-Oct24..4.3.1.3.17.21.1.19 Ext. Joint CoatingCCOPL52418 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-PL-ME-4820 | C-52-0405-PL-ME-4410 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-PL-ME-4810 | C-52-0405-PL-ME-4820 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.13 NDT TestCCOPL52435 | P2543-R01-Oct24..4.3.1.3.17.21.1.19 Ext. Joint CoatingCCOPL52418 | NDT | Ext. Joint Coating | C-52-0405-PL-ME-4000 | C-52-0405-PL-ME-4400 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.17.21.1.12 Automatic WeldingCCOPL52420 | P2543-R01-Oct24..4.3.1.3.17.21.1.13 NDT TestCCOPL52435 | Automatic Welding | NDT | C-52-0405-PL-ME-3600 | C-52-0405-PL-ME-4000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.11 Pipe StringingCCOPL52441 | P2543-R01-Oct24..4.3.1.3.18.21.1.9 Excavation (incl Bedding)CCOPL52455 | Stringing (BVS-05 to BVS-06) | Trench Excavation | C-52-0506-PL-ME-2800 | C-52-0506-PL-CI-2400 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.17.21.1.19 Ext. Joint CoatingCCOPL52418 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Ext. Joint Coating | Lowering | C-52-0405-PL-ME-4400 | C-52-0405-PL-ME-4800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Lowering | Section Tie-in Welding | C-52-0405-PL-ME-4800 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | Trench Excavation | Bedding | C-52-0405-PL-CI-2400 | C-52-0405-PL-CI-2410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.10 Pipe StringingCCOPL52413 | P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | Stringing (BVS-04 to BVS-05) | Trench Excavation | C-52-0405-PL-ME-2800 | C-52-0405-PL-CI-2400 | FF | In Progress | Not Started | 3
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | Sabka Gatch Compaction - Layer 4 | Trench Excavation | C-52-0405-PL-CI-2230 | C-52-0405-PL-CI-2400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.33 Test Stations & Anode Beds from Habshan complex to KP 6CCOP56EL22.1 | Holiday Testing | Installation of Temp. Anode | C-56-HC01-PL-ME-4830 | C-56-HC01-PL-CA-5600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Gatch Compaction | Installation of Marker Post/Sign Board | C-52-0405-PL-CI-6810 | C-52-0405-PL-CI-7800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Gatch Laying & Levelling | Gatch Compaction | C-52-0405-PL-CI-6800 | C-52-0405-PL-CI-6810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.7 Surveying from BVS-01 to KP 21.3CCOPL56247.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.10 ROW Access RoadCCOPL56249 | Survey Marking | Non-Sabka ROW/Grading | C-56-01HG-PL-CI-1000 | C-56-01HG-PL-CI-1800 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.34 Cold Bends from KP 21.3 to HGCPCCOPL56255.2 | Lowering | Cold Bends | C-56-01HG-PL-ME-5000 | C-56-01HG-PL-ME-3400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.34 Cold Bends from KP 21.3 to HGCPCCOPL56255.2 | Lowering | Cold Bends | C-56-01HG-PL-ME-4800 | C-56-01HG-PL-ME-3400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.18 Ext. Joint Coating from Habshan complex to KP 6CCOPL56210.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | Ext. Joint Coating | Lowering | C-56-HC01-PL-ME-4400 | C-56-HC01-PL-ME-4800 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.1 Compaction & Testing CCOB156C11 | Earth Works for Equipment Foundations & Hard Stand Area | Compaction & Testing for Equipment Foundations & Hard Stand Area | C-56-591-01-CI-1010 | C-56-591-01-CI-3020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.1 Compaction & Testing CCOB156C11 | Earth Works for Pipe Support Foundations | Compaction & Testing for Pipe Support Foundations | C-56-591-01-CI-1020 | C-56-591-01-CI-3030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.1 Compaction & Testing CCOB156C11 | Earth Works for Field Instrument Foundations | Compaction & Testing for Field Instrument Foundations | C-56-591-01-CI-1030 | C-56-591-01-CI-3040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.1 Compaction & Testing CCOB156C11 | Earth Works for Access Platforms & Misc. Structural Foundations | Compaction & Testing for Access Platform & Misc. Structural Foundations | C-56-591-01-CI-1040 | C-56-591-01-CI-3050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | P2543-R01-Oct24..4.3.1.2.1.12.1.1 Compaction & Testing CCOB156C11 | Earth Works for Light Pole, Fence & Gates Foundation | Compaction & Testing for Light Pole, Fence & Gates Foundation | C-56-591-01-CI-1050 | C-56-591-01-CI-3060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.1 Compaction & Testing CCOB156C11 | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Compaction & Testing for Equipment Foundations & Hard Stand Area | Concrete Works for Equipment Foundations & Hard Stand Area | C-56-591-01-CI-3020 | C-56-591-01-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.1 Compaction & Testing CCOB156C11 | P2543-R01-Oct24..4.3.1.2.1.12.1.13 Concrete Works (Foundations for Pipe Supports) CCOB156C32 | Compaction & Testing for Pipe Support Foundations | Concrete Works for Pipe Support Foundations | C-56-591-01-CI-3030 | C-56-591-01-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.1 Compaction & Testing CCOB156C11 | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Compaction & Testing for Field Instrument Foundations | Concrete Works for Field Instrument, JB Foundations | C-56-591-01-CI-3040 | C-56-591-01-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.1 Compaction & Testing CCOB156C11 | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Compaction & Testing for Access Platform & Misc. Structural Foundations | Concrete Works for Access Platform & Misc. Structural Foundations | C-56-591-01-CI-3050 | C-56-591-01-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.1 Compaction & Testing CCOB156C11 | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Compaction & Testing for Light Pole, Fence & Gates Foundation | Concrete Works for Light Pole, Fence & Gates Foundation | C-56-591-01-CI-3060 | C-56-591-01-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | P2543-R01-Oct24..4.3.1.3.18.21.1.24 BackfillingCCOPL52450 | Padding | Backfilling | C-52-0506-PL-CI-6000 | C-52-0506-PL-CI-6400 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | P2543-R01-Oct24..4.3.1.3.2.21.1.27 BermingCCOPL52316 | Padding -Lot1 | Gatch Laying & Levelling | C-52-HG01-PL-CI-6000 | C-52-HG01-PL-CI-6800 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Gatch Laying & Levelling | Gatch Compaction | C-52-0506-PL-CI-6800 | C-52-0506-PL-CI-6810 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.15 Ext. Joint CoatingCCOPL52446 | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Ext. Joint Coating | Lowering | C-52-0506-PL-ME-4400 | C-52-0506-PL-ME-4800 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.18.21.1.14 NDT TestCCOPL52463 | P2543-R01-Oct24..4.3.1.3.18.21.1.15 Ext. Joint CoatingCCOPL52446 | NDT | Ext. Joint Coating | C-52-0506-PL-ME-4000 | C-52-0506-PL-ME-4400 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.19.8.1.18 NDT TestCCOPL52491 | P2543-R01-Oct24..4.3.1.3.19.8.1.19 Ext. Joint CoatingCCOPL52474 | NDT | Ext. Joint Coating | C-52-06CR-PL-ME-4000 | C-52-06CR-PL-ME-4400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Holiday Testing | Padding | C-52-06CR-PL-ME-4830 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.9.21.1.6 Pipe Supports Fabrication & InstallationCCOB152S52 | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Pre-Fabrication & Installation of Pipe Supports | Piping Erection | C-52-598-06-CI-2000 | C-52-598-06-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | Trench Excavation | Trench Excavation | C-56-01HG-CMA01-1000 | C-56-01HG-CMA06-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | P2543-R01-Oct24..4.3.1.3.19.8.1.24 BackfillingCCOPL52478 | Padding | Backfilling | C-52-06CR-PL-CI-6000 | C-52-06CR-PL-CI-6400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Lowering | Section Tie-in Welding | C-52-06CR-PL-ME-4800 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Gatch Laying & Levelling | Gatch Compaction | C-56-01HG-PL-CI-7000 | C-56-01HG-PL-CI-7010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Gatch Compaction | Cleaning & Gauging | C-56-01HG-PL-CI-7010 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.21 Backfilling from Habshan complex to KP 6CCOPL56217.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Backfilling from Habshan complex to KP 6 | Gatch Laying & Levelling | C-56-HC01-PL-CI-6400 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | P2543-R01-Oct24..4.3.1.3.19.8.1.16 Cold BendsCCOPL52475 | Lowering | Cold Bends | C-52-06CR-PL-ME-4800 | C-52-06CR-PL-ME-3200 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.5.21.1.8 Precasting for fence posts from BVS-06 to CRS SweihanCCOP52CS52.1 | P2543-R01-Oct24..4.3.1.3.5.21.1.11 Excavation Works for Fence from BVS-06 to CRS SweihanCCOP52CS53.1 | Pre-Casting of Fence Foundation (BVS-06 to Sweihan-CRS) | Earth Works for Fence Foundation (BVS-06 to Sweihan-CRS) | C-52-06CR-FENCE-1000 | C-52-06CR-FENCE-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Padding | Gatch Laying & Levelling | C-52-0405-PL-CI-6000 | C-52-0405-PL-CI-6800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.17 Automatic WeldingCCOPL52476 | P2543-R01-Oct24..4.3.1.3.19.8.1.18 NDT TestCCOPL52491 | Automatic Welding | NDT | C-52-06CR-PL-ME-3600 | C-52-06CR-PL-ME-4000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.1.1.12.4.3 Field Joint Welding & NDTCCOHBPI332 | P2543-R01-Oct24..4.3.1.1.1.12.4.3 Field Joint Welding & NDTCCOHBPI332 | Field Joint Welding | NDT & Coating for Field Joint Weld | C-56-PL-607-PI-1400 | C-56-PL-607-PI-1410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.4.2 ErectionCCOHBPI322 | P2543-R01-Oct24..4.3.1.1.1.12.4.3 Field Joint Welding & NDTCCOHBPI332 | Piping Erection | Field Joint Welding | C-56-PL-607-PI-1200 | C-56-PL-607-PI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Laboratory Facilities | Satellite Office-2 | CTF-SO1070 | CTF-SO1030 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Ware House & Storage Facilities | Laboratory Facilities | CTF-SO1060 | CTF-SO1070 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Construction Plant & Equipment Facilities | Fabrication Facilities | CTF-SO1040 | CTF-SO1050 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.7 Plumbing & Drainage Layout for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.8 Instrument & Control Layouts | Final Issue for Design-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | Final Issue for Design-Instrument & Control Layouts | HE-BL-1310 | HE-BL-1360 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.12.7 Plumbing & Drainage Layout for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.8 Instrument & Control Layouts | Final Issue for Design-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | Final Issue for Design-Instrument & Control Layouts | HE-BL-1310 | HE-BL-1360 | SS | In Progress | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Camp Facilities | Satellite Office-1 | CTF-SO1010 | CTF-SO1020 | FF | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Ready for Dispatch of Line Pipes (Coated) - Lot 9 | Receipt at site and inspection of Line Pipes - Lot 9 (Coated) | HM-PL-1250 | HM-PL-960 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.2.3 Delivery & Receipt at site | P2543-R01-Oct24..PR.BK.2.3 Delivery & Receipt at site | 1st Piping Special Items MTO | Final Piping Special Items MTO | HM-PI-80 | HM-PI-70 | FF | Not Started | Not Started | 8
P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | P2543-R01-Oct24..PR.1.16.2.2 Lot 2 | Ready for Dispatch of Line Pipes (Coated) - Lot 1 | Ready for Dispatch of Line Pipes (Coated) - Lot 2 | HM-PL-0050 | HM-PL-1010 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Main Office | Camp Facilities | CTF-SO1000 | CTF-SO1010 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.18.1 Ordering | P2543-R01-Oct24..1.EN.6.2.10 TBE for Fire & Gas Detectors | RFQ, Receipt of Bid for Gas Detectors | Issue ICR- TBE for Gas Detectors | HP-ME-0710 | HE-IC-2350 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | Ready for Dispatch of Isolating Joints | Transportation/ Custom Clearance/ Delivery at site of Isolating Joints (Lot 1) | HM-PL-0710 | HM-PL-0730 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | Ready for Dispatch of Power & Control Cables | Transportation/ Custom Clearance/ Delivery at site of Power & Control Cables (Lot 1) | HM-EL-0050 | HM-EL-0070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.4.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.4.3 Delivery & receipt at Site | Ready for Dispatch of Anchor Flanges | Transportation/ Custom Clearance/ Delivery at site of Anchor Flanges (Lot 1) | HM-PL-920 | HM-PL-950 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.19.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | Ready for Dispatch of Pig Signaler | Transportation/ Custom Clearance/ Delivery at site of Pig Signaler (Lot 1) | HM-PL-0500 | HM-PL-0520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Transportation/ Custom Clearance/ Delivery at site of Pig Launchers & Receivers (56" Line) | Vendor Documents Package | HM-ME-2380 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Issue ICR- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Issue ICR- Overall Telecom Block Diagram | HE-TL-0250 | HE-TL-0310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Final Issue for Design/ Construction-I/O list | Final Issue for Design/ Construction-Loop Diagrams | HE-IC-2720 | HE-IC-0770 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A9111 Addendum to INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | Final Issue for Design/ Construction-Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | Issue ICR- Instrument Cable Block Diagram | HE-IC-3380 | HE-IC-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | Issue ICR-Material Requisition for Electrical Bulks | Issue ICR-Material Requisition for Glanding & Termination | HE-EL-2110 | HE-EL-2010 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | Issue ICR-Material Requisition for MOV Isolator | Issue ICR-Material Requisition for Electrical Bulks | HE-EL-2060 | HE-EL-2110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | Issue ICR-Material Requisition for LV Switchgear | Issue ICR-Material Requisition for MOV Isolator | HE-EL-1960 | HE-EL-2060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | Issue ICR-Material Requisition for Solar Panels | Issue ICR-Material Requisition for LV Switchgear | HE-EL-1090 | HE-EL-1960 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | Issue ICR-Material Requisition for Solar Panels | Issue ICR-Material Requisition for Power & Control Cables | HE-EL-1090 | HE-EL-1150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | Issue ICR-Material Requisition for Distribution Boards | Issue ICR-Material Requisition for Solar Panels | HE-EL-0970 | HE-EL-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | Re-Issue for Approval-Update /New Load List | Issue ICR-Material Requisition for Distribution Boards | HE-EL-0090 | HE-EL-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | Issue ICR- Datasheet for Solar panel system | Issue ICR- Datasheet for AC UPS | HE-EL-0730 | HE-EL-1870 | FF | Completed | Completed | 3
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | Final Issue for Design/ Construction-Data sheet for LV Distribution board | Issue ICR- Datasheet for Solar panel system | HE-EL-0650 | HE-EL-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..1.EN.9.13 Lighting Layout | Issue ICR-Cable Routing Layout | Issue ICR-Lighting Layout | HE-EL-1570 | HE-EL-1690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..1.EN.9.3 Hazardous Area Register | Final Issue for Design/ Construction-Earthing Layout | Issue ICR-Hazardous Area Register | HE-EL-1670 | HE-EL-5530 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | Issue ICR-Cable Routing Layout | Receive Company Comments-Cable Routing Layout | HE-EL-1570 | HE-EL-1580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | Issue ICR-Cable Schedule | Issue ICR-Cable Routing Layout | HE-EL-0550 | HE-EL-1570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | P2543-R01-Oct24..1.EN.9.3 Hazardous Area Register | Final Issue for Design/ Construction-Single Line Diagrams for LV Distribution Board | Issue ICR-Hazardous Area Register | HE-EL-0230 | HE-EL-5530 | FF | Completed | Not Started | 5
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | Plot Plan Layout Review Workshop | Issue ICR- Electrical Equipment Layout | HE-WS-0090 | HE-EL-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..1.EN.9.4 Solar Panel Sizing | Final Issue for Design/ Construction-Solar Panel System SLDs | Final Issue for Design/ Construction-Solar Panel Sizing | HE-EL-0350 | HE-EL-0410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | P2543-R01-Oct24..1.EN.9.22 UPS SLDs | Issue ICR-Single Line Diagrams for LV Switchgear | Issue ICR - UPS SLD | HE-EL-0190 | HE-EL-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | Final Issue for Design/ Construction-Electrical Adequacy Check Report | Final Issue for Design/ Construction-Cable Routing Layout | HE-EL-0170 | HE-EL-1610 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | P2543-R01-Oct24..1.EN.8.7 Design Calculation for Typical Shelter | Issued for Review - Gas metering skid foundation drawings | Issued for Review - Calculations for Shelter | HE-CS-0790 | HE-CS-1840 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | P2543-R01-Oct24..1.EN.12.3 Structural Design Calculation | Issued for Review - Addendum to DGs | Issue ICR-Structural Design Calculation | HE-CS-0010 | HE-BL-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | Issued for Review - Addendum to DGs | Final Issue for Design/ Construction-Standard drawings for Anchor bolt | HE-CS-0010 | HE-CS-0110 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.15.3 TBE | P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | Final Issue for Design/ Construction-TBE for RBI Study | Final Issue for Design/ Construction-Cable Routing Layout | HE-CP-190 | HE-EL-1610 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.15.2 Scope of Work | P2543-R01-Oct24..1.EN.15.6 Material Coating & Painting Specification | Issue ICR - Scope of Work for RBI Study | Issue ICR - Material Coating & Painting Specification | HE-CP-100 | HE-CP-250 | SS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.15.5 Material Selection Report | P2543-R01-Oct24..1.EN.15.2 Scope of Work | Issue ICR - Material Selection Report | Issue ICR - Scope of Work for RBI Study | HE-CP-200 | HE-CP-100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | 90% Model Review Report | Issue ICR-Piping Isometrics | HE-PI-0180 | HE-PI-1200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | Issue ICR - Piping GA Drawings for 591-BVS-01 | Issue ICR-Piping GA for 591-BVS-01 to 06 | HE-PI-0780 | HE-PI-0840 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | Issue ICR-Piping GA for 52" Pipeline SWEIHAN CRS | Issue ICR- Piping GA for 4" N2 Source Pipeline | HE-PI-0660 | HE-PI-0720 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | 90% Model Review Report | Issue ICR-Piping GA-56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0180 | HE-PI-0600 | FS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | P2543-R01-Oct24..1.EN.1.17 PIPELINE CROSSING CALCULATION REPORT | Final Issue for Design/ Construction - Pipeline Wall Thickness Calculation Report | Issue ICR - Specification - PIPELINE CROSSING CALCULATION REPORT | HE-PL-0050 | HE-PL-3860 | FS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.1.17 PIPELINE CROSSING CALCULATION REPORT | P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | Final Issue for Design/ Construction - PIPELINE CROSSING CALCULATION REPORT | Final Issue for Design/ Construction-Pipeline Specifications - Addendum to DGS | HE-PL-3850 | HE-PL-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | P2543-R01-Oct24..1.EN.1.17 PIPELINE CROSSING CALCULATION REPORT | Final Issue for Design/ Construction - Pipeline Wall Thickness Calculation Report | Final Issue for Design/ Construction - PIPELINE CROSSING CALCULATION REPORT | HE-PL-0050 | HE-PL-3850 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | P2543-R01-Oct24..1.EN.1.17 PIPELINE CROSSING CALCULATION REPORT | Issue ICR - Specification - Pipeline Wall Thickness Calculation Report | Issue ICR - Specification - PIPELINE CROSSING CALCULATION REPORT | HE-PL-0010 | HE-PL-3860 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.1.60.9 Data Sheet - Linepipes | Project Kick off Meeting | Issue ICR - Data Sheet - Line pipes | ML1002 | HE-PL-1150 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.56 Pipeline Design Basis | P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | Issue ICR- Pipeline Design Basis | Issue ICR - Specification - Pipeline Wall Thickness Calculation Report | HE-DB-80 | HE-PL-0010 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | P2543-R01-Oct24..1.2.12.10 Earthworks | Review Company Comments - Civil / Structural Design Basis | Earthworks RFQ & Quotation Receipt | HE-CS-1570 | HS-CN-0460 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Issue Project Execution Plan (PEP), Coordination, Engineering, Procurement, HSE and Quality Procedures-Final Issue | Receipt at site and inspection of Line Pipes - Lot 1 (Coated) | ML1001-A01 | HM-PL-0080 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Project Kick off Meeting | Receipt at site and inspection of Line Pipes - Lot 1 (Coated) | ML1002 | HM-PL-0080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..1.2.12.4 NDT / PWHT | Topographical Survey | NDT / PWHT RFQ & Quotation Receipt | HE-SS-0030 | HS-CN-0160 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Testing & Precommissioning Subcontract Award | Intelligent Pigging Baseline Survey | HS-CN-0140 | CCM-PM4540 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.10.24 TBE for Pigging Tees | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Final Issue for Design/ Construction-TBE for Pigging Tees | Intelligent Pigging Baseline Survey | HE-PL-2190 | CCM-PM4540 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3411 HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | Final Issue for Design/ Construction-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | Final Issue for Design/ Construction-Datasheets for PSV & Orifice (incl. RO) | HE-IC-3430 | HE-IC-1370 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.6.A9111 Addendum to INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | P2543-R01-Oct24..1.EN.6.A2 Instrument Index | Final Issue for Design/ Construction-Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | Issue ICR-Instrument index -Update | HE-IC-3380 | HE-IC-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A51 Datasheets for PASSIVE COOLED SHELTER | P2543-R01-Oct24..1.EN.6.4.51 Data Sheet - Mainline Ball Valve | Final Issue for Design/ Construction-Datasheets for PASSIVE COOLED SHELTER | Final Issue for Design/ Construction-Data Sheet - Mainline Ball Valve | HE-IC-3290 | HE-PL-1250 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A202 Specification for HSSD | P2543-R01-Oct24..1.EN.6.A2 Instrument Index | Final Issue for Design/ Construction-Specification for HSSD | Final Issue for Design/ Construction-Instrument Index | HE-IC-3230 | HE-IC-0530 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2021 Specification for HYBRID PASSIVE COOLED SHELTER | P2543-R01-Oct24..1.EN.6.A2 Instrument Index | Final Issue for Design/ Construction-Specification for HYBRID PASSIVE COOLED SHELTER | Issue ICR-Instrument index -Update | HE-IC-3280 | HE-IC-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A202 Specification for HSSD | P2543-R01-Oct24..1.EN.6.A2 Instrument Index | Final Issue for Design/ Construction-Specification for HSSD | Final Issue for Design/ Construction-Instrument Index | HE-IC-3230 | HE-IC-0530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.6 Layout, Elevation & Finishing for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.8 Instrument & Control Layouts | Final Issue for Design-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | Final Issue for Design-Instrument & Control Layouts | HE-BL-1260 | HE-BL-1360 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.12.5 Layout, Elevation & Finishing for E&I Building at Habshan complex | P2543-R01-Oct24..1.EN.12.7 Plumbing & Drainage Layout for E&I Building at Sweihan CRS | Final Issue for Design-Layout, Elevation & Finishing for E&I Building at Habshan complex | Final Issue for Design-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | HE-BL-1210 | HE-BL-1310 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.12.4 Plumbing Design, Calculation & Details | P2543-R01-Oct24..1.EN.12.7 Plumbing & Drainage Layout for E&I Building at Sweihan CRS | Final Issue for Design-Plumbing Design, Calculation & Details | Final Issue for Design-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | HE-BL-1160 | HE-BL-1310 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.12.2 Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.7 Plumbing & Drainage Layout for E&I Building at Sweihan CRS | Final Issue for Design-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | Final Issue for Design-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | HE-BL-1110 | HE-BL-1310 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.12.8 Instrument & Control Layouts | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design-Instrument & Control Layouts | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-BL-1360 | C-COM-790 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.12.1 Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | P2543-R01-Oct24..1.EN.12.8 Instrument & Control Layouts | Final Issue for Design-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | Final Issue for Design-Instrument & Control Layouts | HE-BL-1060 | HE-BL-1360 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.2.13.11 Cathodic Protection Work | P2543-R01-Oct24..1.2.13.11 Cathodic Protection Work | Receive Bids - Cathodic Protection Work | Complete Evaluation (Internal) - Cathodic Protection Work | HS-GN-0500 | HS-GN-0520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.4 Topographical survey & Geotechnical Investigation | P2543-R01-Oct24..1.2.13.4 Topographical survey & Geotechnical Investigation | Receive Bids - Topographical survey & Geotechnical Investigation | Complete Evaluation (Internal) - Topographical survey & Geotechnical Investigation | HS-GN-0140 | HS-GN-0160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.9 HSE Studies | P2543-R01-Oct24..1.2.13.9 HSE Studies | Receive Bids - HSE Studies | Complete Evaluation (Internal) - HSE Studies | HS-GN-0080 | HS-GN-0100 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.2.5 Engineeirng Office | Project Kick off Meeting | Engineering Office at NPCC | ML1002 | CTF-SO1080 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.2.5 Engineeirng Office | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Engineering Office at NPCC | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | CTF-SO1080 | CTF-1000 | SS | Completed | Completed | 0
P2543-R01-Oct24..4.2.5 Engineeirng Office | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Engineering Office at NPCC | Camp Facilities | CTF-SO1080 | CTF-SO1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | Final Issue for Design/ Construction-Operating , control and safeguarding philosophy | Issue ICR - Pre-commissioning and commissioning philosophy | HE-PR-0770 | HE-PR-0910 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Telecom cable schedule | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-TL-0830 | ML1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..ML Milestones | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | ML1033-B22 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..ML Milestones | FOC Splicing / Termination Subcontract Award | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HS-CN-0290 | ML1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-TL-0470 | ML1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Telecom Equipment Layout | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-TL-0770 | ML1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..ML Milestones | 1st Telecom Bulk material MTO | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-TL-0040 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-TL-0710 | ML1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | Procedure Qualification Material (56", 52", 42", 30", Test Rings etc) Receipt at Site | Procedure Qualification (PQT/WQT for Hot Tapping - 48", 42",36 & 30") | C-COM-1000 | C-COM-1020 | FS | Completed | Not Started | 205
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..ML Milestones | 1st Structural Bulk material MTO | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-CS-0110 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Electrical Equipment Layout | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-EL-0530 | ML1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Electrical Equipment Layout | Complete E&I Installation Works - Sweihan CRS | HE-EL-0530 | ML1859-E31 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Electrical Equipment Layout | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-EL-0530 | ML1749-E20 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.8.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of AC UPS | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-ME-0790 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.8.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of AC UPS | Complete E&I Installation Works - Sweihan CRS | HM-ME-0790 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.8.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of AC UPS | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-ME-0790 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Loop Diagrams | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-IC-0770 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Loop Diagrams | Complete E&I Installation Works - Sweihan CRS | HE-IC-0770 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Loop Diagrams | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-IC-0770 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..ML Milestones | 1st Instrumentation Bulk material MTO | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-IC-0040 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | 1st Instrumentation Bulk material MTO | Complete E&I Installation Works - Sweihan CRS | HM-IC-0040 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | 1st Instrumentation Bulk material MTO | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-IC-0040 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-EL-0710 | ML1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | Complete E&I Installation Works - Sweihan CRS | HE-EL-0710 | ML1859-E31 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-EL-0710 | ML1749-E20 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-UPS SLD | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-EL-0290 | ML1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-UPS SLD | Complete E&I Installation Works - Sweihan CRS | HE-EL-0290 | ML1859-E31 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-UPS SLD | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-EL-0290 | ML1749-E20 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-IC-1550 | ML1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Complete E&I Installation Works - Sweihan CRS | HE-IC-1550 | ML1859-E31 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-IC-1550 | ML1749-E20 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Data sheet for LV Distribution board | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-EL-0650 | ML1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Data sheet for LV Distribution board | Complete E&I Installation Works - Sweihan CRS | HE-EL-0650 | ML1859-E31 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Data sheet for LV Distribution board | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-EL-0650 | ML1749-E20 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..ML Milestones | 1st Electrical Bulk material MTO | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-EL-0520 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | 1st Electrical Bulk material MTO | Complete E&I Installation Works - Sweihan CRS | HM-EL-0520 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | 1st Electrical Bulk material MTO | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-EL-0520 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-ME-1590 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Complete E&I Installation Works - Sweihan CRS | HM-ME-1590 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-ME-1590 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..ML Milestones | Obtain Company Approval-Data sheet for LV Distribution board | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-EL-0640 | ML1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Obtain Company Approval-Data sheet for LV Distribution board | Complete E&I Installation Works - Sweihan CRS | HE-EL-0640 | ML1859-E31 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Obtain Company Approval-Data sheet for LV Distribution board | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-EL-0640 | ML1749-E20 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Instrument Index | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-IC-0530 | ML1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Instrument Index | Complete E&I Installation Works - Sweihan CRS | HE-IC-0530 | ML1859-E31 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Instrument Index | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-IC-0530 | ML1749-E20 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Earthing Layout | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-EL-1670 | ML1030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Earthing Layout | Complete E&I Installation Works - Sweihan CRS | HE-EL-1670 | ML1859-E31 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Earthing Layout | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-EL-1670 | ML1749-E20 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Earthing Material (Lot 1) | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-EL-0380 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Earthing Material (Lot 1) | Complete E&I Installation Works - Sweihan CRS | HM-EL-0380 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Earthing Material (Lot 1) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-EL-0380 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Isolator (Lot 1) | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-ME-0690 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Isolator (Lot 1) | Complete E&I Installation Works - Sweihan CRS | HM-ME-0690 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Isolator (Lot 1) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-ME-0690 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Power & Control Cables (Lot 1) | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-EL-0080 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Power & Control Cables (Lot 1) | Complete E&I Installation Works - Sweihan CRS | HM-EL-0080 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Power & Control Cables (Lot 1) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-EL-0080 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-IC-1430 | ML1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Complete E&I Installation Works - Sweihan CRS | HE-IC-1430 | ML1859-E31 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-IC-1430 | ML1749-E20 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-ME-1690 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Complete E&I Installation Works - Sweihan CRS | HM-ME-1690 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-ME-1690 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-I/O list | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-IC-0590 | ML1030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-I/O list | Complete E&I Installation Works - Sweihan CRS | HE-IC-0590 | ML1859-E31 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-I/O list | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-IC-0590 | ML1749-E20 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..ML Milestones | Issue ICR- Addendum to DGs | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-IC-0010 | ML1030 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Issue ICR- Addendum to DGs | Complete E&I Installation Works - Sweihan CRS | HE-IC-0010 | ML1859-E31 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Issue ICR- Addendum to DGs | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-IC-0010 | ML1749-E20 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Electrical Installation Drawings | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-EL-1790 | ML1030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Electrical Installation Drawings | Complete E&I Installation Works - Sweihan CRS | HE-EL-1790 | ML1859-E31 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Electrical Installation Drawings | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-EL-1790 | ML1749-E20 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-EL-1010 | ML1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Complete E&I Installation Works - Sweihan CRS | HE-EL-1010 | ML1859-E31 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-EL-1010 | ML1749-E20 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-IC-2570 | ML1030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Complete E&I Installation Works - Sweihan CRS | HE-IC-2570 | ML1859-E31 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-IC-2570 | ML1749-E20 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Cable Trays (Lot 2) | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-EL-0280 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Cable Trays (Lot 2) | Complete E&I Installation Works - Sweihan CRS | HM-EL-0280 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Cable Trays (Lot 2) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-EL-0280 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Hook-Up Diagram | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-IC-0650 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Hook-Up Diagram | Complete E&I Installation Works - Sweihan CRS | HE-IC-0650 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Hook-Up Diagram | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-IC-0650 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-F&G Cause and effect | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-HS-0350 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-F&G Cause and effect | Complete E&I Installation Works - Sweihan CRS | HE-HS-0350 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-F&G Cause and effect | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-HS-0350 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Lighting Layout | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-EL-1730 | ML1030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Lighting Layout | Complete E&I Installation Works - Sweihan CRS | HE-EL-1730 | ML1859-E31 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Lighting Layout | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-EL-1730 | ML1749-E20 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..ML Milestones | Issue ICR-Instrument index -Update | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-IC-0490 | ML1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Issue ICR-Instrument index -Update | Complete E&I Installation Works - Sweihan CRS | HE-IC-0490 | ML1859-E31 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Issue ICR-Instrument index -Update | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-IC-0490 | ML1749-E20 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..ML Milestones | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | ML1032-B21 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Complete E&I Installation Works - Sweihan CRS | ML1032-B21 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | ML1032-B21 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-Typical Installation Drawings | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-IC-0710 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Typical Installation Drawings | Complete E&I Installation Works - Sweihan CRS | HE-IC-0710 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Typical Installation Drawings | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-IC-0710 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Gas Detectors (Lot 1) | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-ME-1490 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Gas Detectors (Lot 1) | Complete E&I Installation Works - Sweihan CRS | HM-ME-1490 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Gas Detectors (Lot 1) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-ME-1490 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..ML Milestones | Issue ICR- P&ID's | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HE-PR-0110 | ML1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Issue ICR- P&ID's | Complete E&I Installation Works - Sweihan CRS | HE-PR-0110 | ML1859-E31 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Issue ICR- P&ID's | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HE-PR-0110 | ML1749-E20 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Isolator (Lot 2) | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-ME-2250 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Isolator (Lot 2) | Complete E&I Installation Works - Sweihan CRS | HM-ME-2250 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Isolator (Lot 2) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-ME-2250 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Gas Detectors (Lot 2) | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-ME-2310 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Gas Detectors (Lot 2) | Complete E&I Installation Works - Sweihan CRS | HM-ME-2310 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Gas Detectors (Lot 2) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-ME-2310 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-ME-2330 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Complete E&I Installation Works - Sweihan CRS | HM-ME-2330 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-ME-2330 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-ME-2350 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Complete E&I Installation Works - Sweihan CRS | HM-ME-2350 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-ME-2350 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Power & Control Cables (Lot 2) | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-EL-630 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Power & Control Cables (Lot 2) | Complete E&I Installation Works - Sweihan CRS | HM-EL-630 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Power & Control Cables (Lot 2) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-EL-630 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Cable Trays (Lot 2) | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-EL-650 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Cable Trays (Lot 2) | Complete E&I Installation Works - Sweihan CRS | HM-EL-650 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Cable Trays (Lot 2) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-EL-650 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Earthing Material (Lot 2) | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HM-EL-690 | ML1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Earthing Material (Lot 2) | Complete E&I Installation Works - Sweihan CRS | HM-EL-690 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receipt at site and inspection of Earthing Material (Lot 2) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | HM-EL-690 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..ML Milestones | 1st Structural Bulk material MTO | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | HM-CS-0110 | ML1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.5 Anchor Block Calculation | P2543-R01-Oct24..1.EN.8.6 Anchor Block Detailed Drawings | Issued for Review - Anchor Block Calculation | Issued for Review - Anchor Block Detail Drawings | HE-CS-1710 | HE-CS-1760 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.5 Anchor Block Calculation | P2543-R01-Oct24..1.EN.8.6 Anchor Block Detailed Drawings | Final Issue for Design/ Construction-Anchor Block Calculation | Final Issue for Design/ Construction - Anchor Block Detail Drawings | HE-CS-1750 | HE-CS-1800 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Laboratory Facilities | Satellite Office-2 | CTF-SO1070 | CTF-SO1030 | SS | Completed | Completed | 2
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Satellite Office-1 | Construction Plant & Equipment Facilities | CTF-SO1020 | CTF-SO1040 | SS | Completed | Completed | 14
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Construction Plant & Equipment Facilities | Fabrication Facilities | CTF-SO1040 | CTF-SO1050 | SS | Completed | Completed | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Fabrication Facilities | Ware House & Storage Facilities | CTF-SO1050 | CTF-SO1060 | SS | Completed | Completed | 7
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Ware House & Storage Facilities | Laboratory Facilities | CTF-SO1060 | CTF-SO1070 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A202 Specification for HSSD | P2543-R01-Oct24..1.EN.6.A3411 HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | Issue ICR- Specification for HSSD | Issue ICR-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | HE-IC-3190 | HE-IC-3390 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2021 Specification for HYBRID PASSIVE COOLED SHELTER | P2543-R01-Oct24..1.EN.6.A3411 HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | Issue ICR- Specification for HYBRID PASSIVE COOLED SHELTER | Issue ICR-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | HE-IC-3240 | HE-IC-3390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | P2543-R01-Oct24..1.EN.6.A202 Specification for HSSD | Issue ICR- I/O list -Update | Issue ICR- Specification for HSSD | HE-IC-2730 | HE-IC-3190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A9111 Addendum to INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | P2543-R01-Oct24..1.EN.6.4.A51 Datasheets for PASSIVE COOLED SHELTER | Issue ICR- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | Issue ICR- Datasheets for PASSIVE COOLED SHELTER | HE-IC-3340 | HE-IC-3300 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2021 Specification for HYBRID PASSIVE COOLED SHELTER | P2543-R01-Oct24..1.EN.6.A9111 Addendum to INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | Issue ICR- Specification for HYBRID PASSIVE COOLED SHELTER | Issue ICR- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | HE-IC-3240 | HE-IC-3340 | FS | Completed | Completed | 7
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A2021 Specification for HYBRID PASSIVE COOLED SHELTER | Issue ICR- Specification for RTU | Issue ICR- Specification for HYBRID PASSIVE COOLED SHELTER | HE-IC-0190 | HE-IC-3240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.5 Layout, Elevation & Finishing for E&I Building at Habshan complex | P2543-R01-Oct24..1.EN.12.6 Layout, Elevation & Finishing for E&I Building at Sweihan CRS | Issue ICR-Layout, Elevation & Finishing for E&I Building at Habshan complex | Issue ICR-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | HE-BL-1230 | HE-BL-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.3 Structural Design Calculation | P2543-R01-Oct24..1.EN.12.5 Layout, Elevation & Finishing for E&I Building at Habshan complex | Issue ICR-Structural Design Calculation | Issue ICR-Layout, Elevation & Finishing for E&I Building at Habshan complex | HE-BL-1000 | HE-BL-1230 | FF | Completed | Completed | 10
P2543-R01-Oct24..1.EN.12.3 Structural Design Calculation | P2543-R01-Oct24..1.EN.12.4 Plumbing Design, Calculation & Details | Issue ICR-Structural Design Calculation | Issue ICR-Plumbing Design, Calculation & Details | HE-BL-1000 | HE-BL-1180 | FF | Completed | Completed | 2
P2543-R01-Oct24..1.EN.12.1 Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | P2543-R01-Oct24..1.EN.12.8 Instrument & Control Layouts | Issue ICR-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | Issue ICR-Instrument & Control Layouts | HE-BL-1080 | HE-BL-1380 | FF | Completed | Completed | 1
P2543-R01-Oct24..1.EN.12.2 Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.1 Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | Issue ICR-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | Issue ICR-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | HE-BL-1130 | HE-BL-1080 | FS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.12.3 Structural Design Calculation | P2543-R01-Oct24..1.EN.12.2 Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | Issue ICR-Structural Design Calculation | Issue ICR-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | HE-BL-1000 | HE-BL-1130 | FS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | Final Issue for Design/ Construction - Pipeline Wall Thickness Calculation Report | Issue ICR - Detailed crossing drawings - 56" | HE-PL-0050 | HE-PL-2870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.56 Pipeline Design Basis | P2543-R01-Oct24..1.EN.1.17 PIPELINE CROSSING CALCULATION REPORT | Issue ICR- Pipeline Design Basis | Issue ICR - Specification - PIPELINE CROSSING CALCULATION REPORT | HE-DB-80 | HE-PL-3860 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.17 PIPELINE CROSSING CALCULATION REPORT | P2543-R01-Oct24..1.EN.1.17 PIPELINE CROSSING CALCULATION REPORT | Receive Company Comments - PIPELINE CROSSING CALCULATION REPORT | Re-Issue for Approval - Specification -PIPELINE CROSSING CALCULATION REPORT | HE-PL-3870 | HE-PL-3830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.17 PIPELINE CROSSING CALCULATION REPORT | P2543-R01-Oct24..1.EN.1.17 PIPELINE CROSSING CALCULATION REPORT | Issue ICR - Specification - PIPELINE CROSSING CALCULATION REPORT | Receive Company Comments - PIPELINE CROSSING CALCULATION REPORT | HE-PL-3860 | HE-PL-3870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.17 PIPELINE CROSSING CALCULATION REPORT | P2543-R01-Oct24..1.EN.1.17 PIPELINE CROSSING CALCULATION REPORT | Re-Issue for Approval - Specification -PIPELINE CROSSING CALCULATION REPORT | Obtain Company Approval - PIPELINE CROSSING CALCULATION REPORT | HE-PL-3830 | HE-PL-3840 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.17 PIPELINE CROSSING CALCULATION REPORT | P2543-R01-Oct24..1.EN.1.17 PIPELINE CROSSING CALCULATION REPORT | Obtain Company Approval - PIPELINE CROSSING CALCULATION REPORT | Final Issue for Design/ Construction - PIPELINE CROSSING CALCULATION REPORT | HE-PL-3840 | HE-PL-3850 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A3411 HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | P2543-R01-Oct24..1.EN.6.A3411 HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | Receive Company Comments-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | Re-Issue for Approval-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | HE-IC-3400 | HE-IC-3410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A3411 HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | P2543-R01-Oct24..1.EN.6.A3411 HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | Obtain Company Approval-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | Final Issue for Design/ Construction-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | HE-IC-3420 | HE-IC-3430 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A3411 HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | P2543-R01-Oct24..1.EN.6.A3411 HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | Re-Issue for Approval-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | Obtain Company Approval-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | HE-IC-3410 | HE-IC-3420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A3411 HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | P2543-R01-Oct24..1.EN.6.A3411 HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | Issue ICR-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | Receive Company Comments-HYBRID PASSIVE COOLING SHELTER EQUIPMENT LAYOUT | HE-IC-3390 | HE-IC-3400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A9111 Addendum to INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | P2543-R01-Oct24..1.EN.6.A9111 Addendum to INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | Obtain Company Approval- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | Final Issue for Design/ Construction-Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | HE-IC-3370 | HE-IC-3380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A9111 Addendum to INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | P2543-R01-Oct24..1.EN.6.A9111 Addendum to INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | Issue ICR- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | Receive Company Comments- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | HE-IC-3340 | HE-IC-3350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A9111 Addendum to INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | P2543-R01-Oct24..1.EN.6.A9111 Addendum to INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | Re-Issue for Approval- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | Obtain Company Approval- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | HE-IC-3360 | HE-IC-3370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A9111 Addendum to INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | P2543-R01-Oct24..1.EN.6.A9111 Addendum to INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | Receive Company Comments- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | Re-Issue for Approval- Addendum to DGs - INSTRUMENT & THERMOCOUPLE CABLES (DGS 1511-036) | HE-IC-3350 | HE-IC-3360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A51 Datasheets for PASSIVE COOLED SHELTER | P2543-R01-Oct24..1.EN.6.4.A51 Datasheets for PASSIVE COOLED SHELTER | Issue ICR- Datasheets for PASSIVE COOLED SHELTER | Receive Company Comments- Datasheets for PASSIVE COOLED SHELTER | HE-IC-3300 | HE-IC-3310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A51 Datasheets for PASSIVE COOLED SHELTER | P2543-R01-Oct24..1.EN.6.4.A51 Datasheets for PASSIVE COOLED SHELTER | Obtain Company Approval- Datasheets for PASSIVE COOLED SHELTER | Final Issue for Design/ Construction-Datasheets for PASSIVE COOLED SHELTER | HE-IC-3330 | HE-IC-3290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A51 Datasheets for PASSIVE COOLED SHELTER | P2543-R01-Oct24..1.EN.6.4.A51 Datasheets for PASSIVE COOLED SHELTER | Receive Company Comments- Datasheets for PASSIVE COOLED SHELTER | Re-Issue for Approval- Datasheets for PASSIVE COOLED SHELTER | HE-IC-3310 | HE-IC-3320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A51 Datasheets for PASSIVE COOLED SHELTER | P2543-R01-Oct24..1.EN.6.4.A51 Datasheets for PASSIVE COOLED SHELTER | Re-Issue for Approval- Datasheets for PASSIVE COOLED SHELTER | Obtain Company Approval- Datasheets for PASSIVE COOLED SHELTER | HE-IC-3320 | HE-IC-3330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2021 Specification for HYBRID PASSIVE COOLED SHELTER | P2543-R01-Oct24..1.EN.6.A2021 Specification for HYBRID PASSIVE COOLED SHELTER | Receive Company Comments- Specification for HYBRID PASSIVE COOLED SHELTER | Re-Issue for Approval- Specification for HYBRID PASSIVE COOLED SHELTER | HE-IC-3250 | HE-IC-3260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2021 Specification for HYBRID PASSIVE COOLED SHELTER | P2543-R01-Oct24..1.EN.6.A2021 Specification for HYBRID PASSIVE COOLED SHELTER | Issue ICR- Specification for HYBRID PASSIVE COOLED SHELTER | Receive Company Comments- Specification for HYBRID PASSIVE COOLED SHELTER | HE-IC-3240 | HE-IC-3250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2021 Specification for HYBRID PASSIVE COOLED SHELTER | P2543-R01-Oct24..1.EN.6.A2021 Specification for HYBRID PASSIVE COOLED SHELTER | Obtain Company Approval- Specification for HYBRID PASSIVE COOLED SHELTER | Final Issue for Design/ Construction-Specification for HYBRID PASSIVE COOLED SHELTER | HE-IC-3270 | HE-IC-3280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2021 Specification for HYBRID PASSIVE COOLED SHELTER | P2543-R01-Oct24..1.EN.6.A2021 Specification for HYBRID PASSIVE COOLED SHELTER | Re-Issue for Approval- Specification for HYBRID PASSIVE COOLED SHELTER | Obtain Company Approval- Specification for HYBRID PASSIVE COOLED SHELTER | HE-IC-3260 | HE-IC-3270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A202 Specification for HSSD | P2543-R01-Oct24..1.EN.6.A202 Specification for HSSD | Receive Company Comments- Specification for HSSD | Re-Issue for Approval- Specification for HSSD | HE-IC-3200 | HE-IC-3210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A202 Specification for HSSD | P2543-R01-Oct24..1.EN.6.A202 Specification for HSSD | Issue ICR- Specification for HSSD | Receive Company Comments- Specification for HSSD | HE-IC-3190 | HE-IC-3200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A202 Specification for HSSD | P2543-R01-Oct24..1.EN.6.A202 Specification for HSSD | Obtain Company Approval- Specification for HSSD | Final Issue for Design/ Construction-Specification for HSSD | HE-IC-3220 | HE-IC-3230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A202 Specification for HSSD | P2543-R01-Oct24..1.EN.6.A202 Specification for HSSD | Re-Issue for Approval- Specification for HSSD | Obtain Company Approval- Specification for HSSD | HE-IC-3210 | HE-IC-3220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.8 Instrument & Control Layouts | P2543-R01-Oct24..1.EN.12.8 Instrument & Control Layouts | Re-Issue for Approval-Instrument & Control Layouts | Obtain Company Approval-Instrument & Control Layouts | HE-BL-1350 | HE-BL-1370 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.12.8 Instrument & Control Layouts | P2543-R01-Oct24..1.EN.12.8 Instrument & Control Layouts | Receive Company Comments-Instrument & Control Layouts | Re-Issue for Approval-Instrument & Control Layouts | HE-BL-1390 | HE-BL-1350 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.12.8 Instrument & Control Layouts | P2543-R01-Oct24..1.EN.12.8 Instrument & Control Layouts | Issue ICR-Instrument & Control Layouts | Receive Company Comments-Instrument & Control Layouts | HE-BL-1380 | HE-BL-1390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.8 Instrument & Control Layouts | P2543-R01-Oct24..1.EN.12.8 Instrument & Control Layouts | Obtain Company Approval-Instrument & Control Layouts | Final Issue for Design-Instrument & Control Layouts | HE-BL-1370 | HE-BL-1360 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.12.7 Plumbing & Drainage Layout for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.7 Plumbing & Drainage Layout for E&I Building at Sweihan CRS | Re-Issue for Approval-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | Obtain Company Approval-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | HE-BL-1300 | HE-BL-1320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.7 Plumbing & Drainage Layout for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.7 Plumbing & Drainage Layout for E&I Building at Sweihan CRS | Receive Company Comments-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | Re-Issue for Approval-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | HE-BL-1340 | HE-BL-1300 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.7 Plumbing & Drainage Layout for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.7 Plumbing & Drainage Layout for E&I Building at Sweihan CRS | Issue ICR-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | Receive Company Comments-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | HE-BL-1330 | HE-BL-1340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.7 Plumbing & Drainage Layout for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.7 Plumbing & Drainage Layout for E&I Building at Sweihan CRS | Obtain Company Approval-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | Final Issue for Design-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | HE-BL-1320 | HE-BL-1310 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.12.6 Layout, Elevation & Finishing for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.6 Layout, Elevation & Finishing for E&I Building at Sweihan CRS | Re-Issue for Approval-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | Obtain Company Approval-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | HE-BL-1250 | HE-BL-1270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.6 Layout, Elevation & Finishing for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.6 Layout, Elevation & Finishing for E&I Building at Sweihan CRS | Receive Company Comments-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | Re-Issue for Approval-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | HE-BL-1290 | HE-BL-1250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.6 Layout, Elevation & Finishing for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.6 Layout, Elevation & Finishing for E&I Building at Sweihan CRS | Issue ICR-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | Receive Company Comments-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | HE-BL-1280 | HE-BL-1290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.6 Layout, Elevation & Finishing for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.6 Layout, Elevation & Finishing for E&I Building at Sweihan CRS | Obtain Company Approval-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | Final Issue for Design-Layout, Elevation & Finishing for E&I Building at Sweihan CRS | HE-BL-1270 | HE-BL-1260 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.12.5 Layout, Elevation & Finishing for E&I Building at Habshan complex | P2543-R01-Oct24..1.EN.12.5 Layout, Elevation & Finishing for E&I Building at Habshan complex | Re-Issue for Approval-Layout, Elevation & Finishing for E&I Building at Habshan complex | Obtain Company Approval-Layout, Elevation & Finishing for E&I Building at Habshan complex | HE-BL-1200 | HE-BL-1220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.5 Layout, Elevation & Finishing for E&I Building at Habshan complex | P2543-R01-Oct24..1.EN.12.5 Layout, Elevation & Finishing for E&I Building at Habshan complex | Receive Company Comments-Layout, Elevation & Finishing for E&I Building at Habshan complex | Re-Issue for Approval-Layout, Elevation & Finishing for E&I Building at Habshan complex | HE-BL-1240 | HE-BL-1200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.5 Layout, Elevation & Finishing for E&I Building at Habshan complex | P2543-R01-Oct24..1.EN.12.5 Layout, Elevation & Finishing for E&I Building at Habshan complex | Issue ICR-Layout, Elevation & Finishing for E&I Building at Habshan complex | Receive Company Comments-Layout, Elevation & Finishing for E&I Building at Habshan complex | HE-BL-1230 | HE-BL-1240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.5 Layout, Elevation & Finishing for E&I Building at Habshan complex | P2543-R01-Oct24..1.EN.12.5 Layout, Elevation & Finishing for E&I Building at Habshan complex | Obtain Company Approval-Layout, Elevation & Finishing for E&I Building at Habshan complex | Final Issue for Design-Layout, Elevation & Finishing for E&I Building at Habshan complex | HE-BL-1220 | HE-BL-1210 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.12.4 Plumbing Design, Calculation & Details | P2543-R01-Oct24..1.EN.12.4 Plumbing Design, Calculation & Details | Re-Issue for Approval-Plumbing Design, Calculation & Details | Obtain Company Approval-Plumbing Design, Calculation & Details | HE-BL-1150 | HE-BL-1170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.4 Plumbing Design, Calculation & Details | P2543-R01-Oct24..1.EN.12.4 Plumbing Design, Calculation & Details | Receive Company Comments-Plumbing Design, Calculation & Details | Re-Issue for Approval-Plumbing Design, Calculation & Details | HE-BL-1190 | HE-BL-1150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.4 Plumbing Design, Calculation & Details | P2543-R01-Oct24..1.EN.12.4 Plumbing Design, Calculation & Details | Issue ICR-Plumbing Design, Calculation & Details | Receive Company Comments-Plumbing Design, Calculation & Details | HE-BL-1180 | HE-BL-1190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.4 Plumbing Design, Calculation & Details | P2543-R01-Oct24..1.EN.12.4 Plumbing Design, Calculation & Details | Obtain Company Approval-Plumbing Design, Calculation & Details | Final Issue for Design-Plumbing Design, Calculation & Details | HE-BL-1170 | HE-BL-1160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.2 Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.2 Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | Re-Issue for Approval-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | Obtain Company Approval-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | HE-BL-1100 | HE-BL-1120 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.2 Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.2 Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | Receive Company Comments-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | Re-Issue for Approval-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | HE-BL-1140 | HE-BL-1100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.2 Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.2 Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | Issue ICR-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | Receive Company Comments-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | HE-BL-1130 | HE-BL-1140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.2 Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | P2543-R01-Oct24..1.EN.12.2 Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | Obtain Company Approval-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | Final Issue for Design-Foundation, GA & Reinforcement Details for E&I Building at Sweihan CRS | HE-BL-1120 | HE-BL-1110 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.12.1 Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | P2543-R01-Oct24..1.EN.12.1 Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | Re-Issue for Approval-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | Obtain Company Approval-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | HE-BL-1050 | HE-BL-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.1 Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | P2543-R01-Oct24..1.EN.12.1 Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | Receive Company Comments-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | Re-Issue for Approval-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | HE-BL-1090 | HE-BL-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.1 Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | P2543-R01-Oct24..1.EN.12.1 Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | Issue ICR-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | Receive Company Comments-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | HE-BL-1080 | HE-BL-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.1 Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | P2543-R01-Oct24..1.EN.12.1 Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | Obtain Company Approval-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | Final Issue for Design-Foundation, GA & Reinforcement Details for E&I Building at Habshan complex | HE-BL-1070 | HE-BL-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.3 Structural Design Calculation | P2543-R01-Oct24..1.EN.12.3 Structural Design Calculation | Re-Issue for Approval-Structural Design Calculation | Obtain Company Approval-Structural Design Calculation | HE-BL-1020 | HE-BL-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.3 Structural Design Calculation | P2543-R01-Oct24..1.EN.12.3 Structural Design Calculation | Receive Company Comments-Structural Design Calculation | Re-Issue for Approval-Structural Design Calculation | HE-BL-1010 | HE-BL-1020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.3 Structural Design Calculation | P2543-R01-Oct24..1.EN.12.3 Structural Design Calculation | Issue ICR-Structural Design Calculation | Receive Company Comments-Structural Design Calculation | HE-BL-1000 | HE-BL-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.3 Structural Design Calculation | P2543-R01-Oct24..1.EN.12.3 Structural Design Calculation | Obtain Company Approval-Structural Design Calculation | Final Issue for Design-Structural Design Calculation | HE-BL-1030 | HE-BL-1040 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | Complete Line Pipe Production - Lot 1 | Procedure Qualification Material (56", 52", 42", 30", Test Rings etc) Receipt at Site | HM-PL-0030 | C-COM-1000 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | Procedure Qualification Material (56", 52", 42", 30", Test Rings etc) Receipt at Site | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | C-COM-1000 | C-COM-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | P2543-R01-Oct24..PR.26.1.2.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-TBE for fire fighting and safety equipment | Vendor Document Review of Fire Suppression System | HE-HS-1190 | HM-ME-1850 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.1.2.25.2.1 Ordering | Obtain Company Approval-TBE for Fire Fighting & Safety Eqpt | Prepare TBE and Company approval for Fire Suppression System | HE-HS-1180 | HP-ME-0920 | FF | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.2.13.4 Topographical survey & Geotechnical Investigation | Project Effective Date | Prepare/Issue Scope of Work - Topographical survey & Geotechnical Investigation | ML1001 | HS-GN-0130 | SS | Completed | Completed | 3
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Line Pipes - Lot 7 (Coated) | Project Finish | HM-PL-0120 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Issue ICR-Data sheet for Ball Valves | Issue ICR- Data sheet for PRS (Pressure Reduction System) | HE-PI-0900 | HE-IC-1210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | Issue ICR-Data sheet for Ball Valves | Issue ICR- Datasheet for GOV & ROV | HE-PI-0900 | HE-IC-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | Issue ICR-Data sheet for Ball Valves | Issue ICR- Datasheet for MOV | HE-PI-0900 | HE-IC-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Issue ICR- P&ID's | Issue ICR- Data sheet for PRS (Pressure Reduction System) | HE-PR-0110 | HE-IC-1210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | Issue ICR- P&ID's | Issue ICR- Datasheet for GOV & ROV | HE-PR-0110 | HE-IC-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | Issue ICR- P&ID's | Issue ICR- Datasheet for MOV | HE-PR-0110 | HE-IC-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..1.EN.1.15 Pipeline Station approach drawing - 4" Nitrogen | Issue ICR - Pipeline Alignment Sheets-4" | Issue ICR - Pipeline Station Approach drawing -4" | HE-PL-2510 | HE-PL-2690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | Issue ICR - Pipeline Alignment Sheets -56" | Issue ICR - Pipeline Station Approach drawing -56" | HE-PL-2390 | HE-PL-2570 | FF | Completed | Completed | 10
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | Issue ICR - Pipeline Alignment Sheets-52" | Issue ICR - Pipeline Station Approach drawing -52" | HE-PL-2450 | HE-PL-2630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.12 Pipeline Station approach drawing - 4" Waterline | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline Station approach drawing-4" | Pipeline | HE-PL-3620 | CAB-4480 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.12 Pipeline Station approach drawing - 4" Waterline | P2543-R01-Oct24..1.EN.1.12 Pipeline Station approach drawing - 4" Waterline | Receive Company Comments - Pipeline Station Approach drawing -4" | Re-Issue for Approval - Pipeline Station Approach drawing -4" | HE-PL-3590 | HE-PL-3600 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.1.12 Pipeline Station approach drawing - 4" Waterline | Issue ICR- Overall Plot Plan - 4" N2 Source Pipeline | Issue ICR - Pipeline Station Approach drawing -4" | HE-PI-0460 | HE-PL-3580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.12 Pipeline Station approach drawing - 4" Waterline | P2543-R01-Oct24..1.EN.1.12 Pipeline Station approach drawing - 4" Waterline | Obtain Company Approval - Pipeline Station Approach drawing -4" | Final Issue for Design/ Construction-Pipeline Station approach drawing-4" | HE-PL-3610 | HE-PL-3620 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.12 Pipeline Station approach drawing - 4" Waterline | P2543-R01-Oct24..1.EN.1.12 Pipeline Station approach drawing - 4" Waterline | Re-Issue for Approval - Pipeline Station Approach drawing -4" | Obtain Company Approval - Pipeline Station Approach drawing -4" | HE-PL-3600 | HE-PL-3610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.12 Pipeline Station approach drawing - 4" Waterline | P2543-R01-Oct24..1.EN.1.12 Pipeline Station approach drawing - 4" Waterline | Issue ICR - Pipeline Station Approach drawing -4" | Receive Company Comments - Pipeline Station Approach drawing -4" | HE-PL-3580 | HE-PL-3590 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.12 Pipeline Station approach drawing - 4" Waterline | Issue ICR-Topographical Survey Report (Overall) | Issue ICR - Pipeline Station Approach drawing -4" | HE-TS-0010 | HE-PL-3580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.12 Pipeline Station approach drawing - 4" Waterline | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Pipeline Station approach drawing-4" | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | HE-PL-3620 | ML1059-B28 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | HE-PL-3570 | ML1219-B59 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | P2543-R01-Oct24..1.EN.1.44 Detailed crossing drawings-4" | Issue ICR - Pipeline Alignment Sheets-4" | Issue ICR - Detailed crossing drawings-4" | HE-PL-3530 | HE-PL-3110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | Obtain Company Approval - Pipeline Alignment Sheets-4" | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | HE-PL-3560 | HE-PL-3570 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | Issue ICR - Pipeline Alignment Sheets-4" | Receive Company Comments - Pipeline Alignment Sheets-4" | HE-PL-3530 | HE-PL-3540 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | Receive Company Comments - Pipeline Alignment Sheets-4" | Re-Issue for Approval - Pipeline Alignment Sheets-4" | HE-PL-3540 | HE-PL-3550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | Issue ICR-Topographical Survey Report (Overall) | Issue ICR - Pipeline Alignment Sheets-4" | HE-TS-0010 | HE-PL-3530 | FS | Completed | Completed | 60
P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | P2543-R01-Oct24..1.EN.1.55 Crossing Schedule-4" | Issue ICR - Pipeline Alignment Sheets-4" | Issue ICR - Crossing Schedule-4" | HE-PL-3530 | HE-PL-3170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | Re-Issue for Approval - Pipeline Alignment Sheets-4" | Obtain Company Approval - Pipeline Alignment Sheets-4" | HE-PL-3550 | HE-PL-3560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Pipeline | HE-PL-3570 | CAB-4480 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.PM.12 Workshops | Project Kick off Meeting | Lesson Learned Workshop | ML1002 | HE-WS-0070 | SS | Completed | Completed | 45
P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | P2543-R01-Oct24..PR.1.16.2.9 Lot 8 | Vendor Document Review of Line Pipes - Lot 7 | Vendor Document Review of Line Pipes - Lot 8 | HM-PL-1150 | HM-PL-1390 | SS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.3 Lot 3 | P2543-R01-Oct24..PR.1.16.2.7 Lot 4 | Vendor Document Review of Line Pipes - Lot 3 | Vendor Document Review of Line Pipes - Lot 4 | HM-PL-1030 | HM-PL-1330 | SS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.7 Lot 4 | P2543-R01-Oct24..PR.1.16.2.8 Lot 5 | Vendor Document Review of Line Pipes - Lot 4 | Vendor Document Review of Line Pipes - Lot 5 | HM-PL-1330 | HM-PL-1270 | SS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.9 Lot 8 | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Ready for Dispatch of Line Pipes (Coated) - Lot 8 | Receipt at site and inspection of Line Pipes - Lot 8 (Coated) | HM-PL-1430 | HM-PL-1470 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.8 Lot 5 | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Ready for Dispatch of Line Pipes (Coated) - Lot 5 | Receipt at site and inspection of Line Pipes - Lot 5 (Coated) | HM-PL-1310 | HM-PL-1460 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.7 Lot 4 | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Ready for Dispatch of Line Pipes (Coated) - Lot 4 | Receipt at site and inspection of Line Pipes - Lot 4 (Coated) | HM-PL-1370 | HM-PL-1450 | FF | Completed | Completed | 15
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Receipt at site and inspection of Line Pipes - Lot 7 (Coated) | Receipt at site and inspection of Line Pipes - Lot 8 (Coated) | HM-PL-0120 | HM-PL-1470 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.9 Lot 8 | P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | Manufacturing & Receive Plates at Fabrication Shop - Lot 8 | Manufacturing & Receive Plates at Fabrication Shop - Lot 9 | HM-PL-1400 | HM-PL-1220 | FF | Completed | Completed | 21
P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | P2543-R01-Oct24..PR.1.16.2.9 Lot 8 | Manufacturing & Receive Plates at Fabrication Shop - Lot 7 | Manufacturing & Receive Plates at Fabrication Shop - Lot 8 | HM-PL-1160 | HM-PL-1400 | FF | Completed | Completed | 14
P2543-R01-Oct24..PR.1.16.2.8 Lot 5 | P2543-R01-Oct24..PR.1.16.2.4 Lot 6 | Manufacturing & Receive Plates at Fabrication Shop - Lot 5 | Manufacturing & Receive Plates at Fabrication Shop - Lot 6 | HM-PL-1280 | HM-PL-1100 | FF | Completed | Completed | 20
P2543-R01-Oct24..PR.1.16.2.7 Lot 4 | P2543-R01-Oct24..PR.1.16.2.8 Lot 5 | Manufacturing & Receive Plates at Fabrication Shop - Lot 4 | Manufacturing & Receive Plates at Fabrication Shop - Lot 5 | HM-PL-1340 | HM-PL-1280 | FF | Completed | Completed | 13
P2543-R01-Oct24..PR.1.16.2.3 Lot 3 | P2543-R01-Oct24..PR.1.16.2.7 Lot 4 | Manufacturing & Receive Plates at Fabrication Shop - Lot 3 | Manufacturing & Receive Plates at Fabrication Shop - Lot 4 | HM-PL-1040 | HM-PL-1340 | FF | Completed | Completed | 12
P2543-R01-Oct24..PR.1.16.2.9 Lot 8 | P2543-R01-Oct24..PR.1.16.2.9 Lot 8 | Complete External / Internal Coating - Lot 8 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 8 | HM-PL-1440 | HM-PL-1420 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.9 Lot 8 | P2543-R01-Oct24..PR.1.16.2.9 Lot 8 | Complete Line Pipe Production - Lot 8 | Complete External / Internal Coating - Lot 8 | HM-PL-1410 | HM-PL-1440 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.9 Lot 8 | P2543-R01-Oct24..PR.1.16.2.9 Lot 8 | Vendor Document Review of Line Pipes - Lot 8 | Manufacturing & Receive Plates at Fabrication Shop - Lot 8 | HM-PL-1390 | HM-PL-1400 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.9 Lot 8 | P2543-R01-Oct24..PR.1.16.2.9 Lot 8 | Manufacturing & Receive Plates at Fabrication Shop - Lot 8 | Complete Line Pipe Production - Lot 8 | HM-PL-1400 | HM-PL-1410 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.9 Lot 8 | P2543-R01-Oct24..PR.1.16.2.9 Lot 8 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 8 | Ready for Dispatch of Line Pipes (Coated) - Lot 8 | HM-PL-1420 | HM-PL-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.7 Lot 4 | P2543-R01-Oct24..PR.1.16.2.7 Lot 4 | Complete External / Internal Coating - Lot 4 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 4 | HM-PL-1380 | HM-PL-1360 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.7 Lot 4 | P2543-R01-Oct24..PR.1.16.2.7 Lot 4 | Complete Line Pipe Production - Lot 4 | Complete External / Internal Coating - Lot 4 | HM-PL-1350 | HM-PL-1380 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.7 Lot 4 | P2543-R01-Oct24..PR.1.16.2.7 Lot 4 | Vendor Document Review of Line Pipes - Lot 4 | Manufacturing & Receive Plates at Fabrication Shop - Lot 4 | HM-PL-1330 | HM-PL-1340 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.7 Lot 4 | P2543-R01-Oct24..PR.1.16.2.7 Lot 4 | Manufacturing & Receive Plates at Fabrication Shop - Lot 4 | Complete Line Pipe Production - Lot 4 | HM-PL-1340 | HM-PL-1350 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.7 Lot 4 | P2543-R01-Oct24..PR.1.16.2.7 Lot 4 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 4 | Ready for Dispatch of Line Pipes (Coated) - Lot 4 | HM-PL-1360 | HM-PL-1370 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.8 Lot 5 | P2543-R01-Oct24..PR.1.16.2.8 Lot 5 | Complete External / Internal Coating - Lot 5 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 5 | HM-PL-1320 | HM-PL-1300 | FF | In Progress | Not Started | 7
P2543-R01-Oct24..PR.1.16.2.8 Lot 5 | P2543-R01-Oct24..PR.1.16.2.8 Lot 5 | Complete Line Pipe Production - Lot 5 | Complete External / Internal Coating - Lot 5 | HM-PL-1290 | HM-PL-1320 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.1.16.2.8 Lot 5 | P2543-R01-Oct24..PR.1.16.2.8 Lot 5 | Vendor Document Review of Line Pipes - Lot 5 | Manufacturing & Receive Plates at Fabrication Shop - Lot 5 | HM-PL-1270 | HM-PL-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.8 Lot 5 | P2543-R01-Oct24..PR.1.16.2.8 Lot 5 | Manufacturing & Receive Plates at Fabrication Shop - Lot 5 | Complete Line Pipe Production - Lot 5 | HM-PL-1280 | HM-PL-1290 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.8 Lot 5 | P2543-R01-Oct24..PR.1.16.2.8 Lot 5 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 5 | Ready for Dispatch of Line Pipes (Coated) - Lot 5 | HM-PL-1300 | HM-PL-1310 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | Issue ICR- Plot plan - BVS | Issue ICR-Update /New Load List | HE-PI-0530 | HE-EL-0070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Issue ICR - Typical Installation Drawings | Issue ICR - Loop Diagrams | HE-IC-0670 | HE-IC-0730 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | Issue ICR - Hook-Up Diagram | Issue ICR - Typical Installation Drawings | HE-IC-0610 | HE-IC-0670 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | Issue ICR- I/O list -Update | Issue ICR - Hook-Up Diagram | HE-IC-2730 | HE-IC-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A181 Instrument and F&G interconnection Wiring Diagram | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Final Issue for Design/ Construction-interconnection Wiring Diagram | Final Issue for Design/ Construction-Loop Diagrams | HE-IC-2830 | HE-IC-0770 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..1.EN.6.A181 Instrument and F&G interconnection Wiring Diagram | Issue ICR - Hook-Up Diagram | Issue ICR - interconnection Wiring Diagram | HE-IC-0610 | HE-IC-2790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A181 Instrument and F&G interconnection Wiring Diagram | P2543-R01-Oct24..1.EN.6.A181 Instrument and F&G interconnection Wiring Diagram | Issue ICR - interconnection Wiring Diagram | Receive Company Comments - interconnection Wiring Diagram | HE-IC-2790 | HE-IC-2800 | FF | Completed | In Progress | 10
P2543-R01-Oct24..1.EN.6.A181 Instrument and F&G interconnection Wiring Diagram | P2543-R01-Oct24..1.EN.6.A181 Instrument and F&G interconnection Wiring Diagram | Obtain Company Approval - interconnection Wiring Diagram | Final Issue for Design/ Construction-interconnection Wiring Diagram | HE-IC-2820 | HE-IC-2830 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A181 Instrument and F&G interconnection Wiring Diagram | P2543-R01-Oct24..1.EN.6.A181 Instrument and F&G interconnection Wiring Diagram | Re-Issue for Approval - interconnection Wiring Diagram | Obtain Company Approval - interconnection Wiring Diagram | HE-IC-2810 | HE-IC-2820 | FF | In Progress | In Progress | 10
P2543-R01-Oct24..1.EN.6.A181 Instrument and F&G interconnection Wiring Diagram | P2543-R01-Oct24..1.EN.6.A181 Instrument and F&G interconnection Wiring Diagram | Receive Company Comments - interconnection Wiring Diagram | Re-Issue for Approval - interconnection Wiring Diagram | HE-IC-2800 | HE-IC-2810 | FF | In Progress | In Progress | 5
P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Issue ICR- I/O list -Update | Issue ICR-Instrument and F&G Cable Schedule | HE-IC-2730 | HE-IC-0910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A23 F&G Index | P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | Final Issue for Design/ Construction-F&G Index | Final Issue for Design/ Construction-I/O list | HE-IC-2740 | HE-IC-2720 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.6.A23 F&G Index | P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | Issue ICR-F&G index -Update | Issue ICR- I/O list -Update | HE-IC-2750 | HE-IC-2730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.5 F&G layout | P2543-R01-Oct24..1.EN.6.A23 F&G Index | Re-Issue for Approval-F&G Layout | Issue ICR-F&G index -Update | HE-HS-0270 | HE-IC-2750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A23 F&G Index | P2543-R01-Oct24..1.EN.6.A23 F&G Index | Issue ICR-F&G index -Update | Receive Company Comments-F&G index -Update | HE-IC-2750 | HE-IC-2760 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A23 F&G Index | P2543-R01-Oct24..1.EN.6.A23 F&G Index | Obtain Company Approval-F&G index -Update | Final Issue for Design/ Construction-F&G Index | HE-IC-2780 | HE-IC-2740 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A23 F&G Index | P2543-R01-Oct24..1.EN.6.A23 F&G Index | Re-Issue for Approval-F&G index -Update | Obtain Company Approval-F&G index -Update | HE-IC-2770 | HE-IC-2780 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | Receive Company Comments- I/O list -Update | Re-Issue for Approval- I/O list -Update | HE-IC-2690 | HE-IC-2700 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A23 F&G Index | P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | Re-Issue for Approval-F&G index -Update | Re-Issue for Approval- I/O list -Update | HE-IC-2770 | HE-IC-2700 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | Issue ICR- I/O list -Update | Receive Company Comments- I/O list -Update | HE-IC-2730 | HE-IC-2690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A23 F&G Index | P2543-R01-Oct24..1.EN.6.A23 F&G Index | Receive Company Comments-F&G index -Update | Re-Issue for Approval-F&G index -Update | HE-IC-2760 | HE-IC-2770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | Obtain Company Approval- I/O list -Update | Final Issue for Design/ Construction-I/O list | HE-IC-2710 | HE-IC-2720 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | Re-Issue for Approval- I/O list -Update | Obtain Company Approval- I/O list -Update | HE-IC-2700 | HE-IC-2710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- I&C Design Basis | Instrumentation & Control | HE-IC-620 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | Issue ICR- I&C Design Basis | Final Issue for Design/ Construction-Datasheets for Custody Flow Metering Skid | HE-IC-620 | HE-IC-1190 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | Issue ICR- I&C Design Basis | Issue ICR- Datasheets for Metering Skid | HE-IC-620 | HE-IC-1150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | Issue ICR - Geo Technical Survey Report (Overall) | Final Issue for Design/ Construction-Pipeline MTO - 56" and 52" | HE-GS-0010 | HE-PL-3270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Issue ICR-Piping Material Specifications | Issue ICR- P&ID's | HE-PI-0010 | HE-PR-0110 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | Issue ICR- P&ID's | Issue ICR- Specifications for PRS (Pressure Reduction System) | HE-PR-0110 | HE-IC-0070 | FF | Completed | Completed | 2
P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | Issue ICR- Addendum to DGS | Issue ICR-Datasheet for Sales Gas CRS Filters | HE-ME-0010 | HE-ME-0070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | Re-Issue for Approval - Pipeline Alignment Sheets-52" | Issue ICR - Detailed crossing drawings-52" | HE-PL-2470 | HE-PL-2990 | FS | Completed | Completed | 2
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | Obtain Company Approval - Pipeline Alignment Sheets -56" | Issue ICR - Detailed crossing drawings - 56" | HE-PL-2420 | HE-PL-2870 | FS | Completed | Completed | 30
P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | Issue ICR - Overall Pipeline Route Map - 56" | Issue ICR - Overall Pipeline Route Map - 4" | HE-PL-0130 | HE-PL-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | Issue ICR - Overall Pipeline Route Map - 52" | Issue ICR - Overall Pipeline Route Map - 56" | HE-PL-0190 | HE-PL-0130 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.1.2.LL.6.1 Ordering | P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | Commercial Clarifications & Placement of PO for Solar PV system | Issued for Review - Solar panel foundation details | HP-ME-0530 | HE-CS-0850 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | Issue ICR - Pipeline Alignment Sheets-52" | Issue ICR - Pipeline Alignment Sheets -56" | HE-PL-2450 | HE-PL-2390 | FF | Completed | Completed | 14
P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | P2543-R01-Oct24..1.EN.8.5 Anchor Block Calculation | Issue ICR - Pipeline Stress Analysis Report | Issued for Review - Anchor Block Calculation | HE-PL-2810 | HE-CS-1710 | FF | Completed | Completed | 10
P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | P2543-R01-Oct24..1.1.2.LL.12.1 Ordering | Issue ICR-Material Requisitions for Pig Launcher/Receiver | RFQ, Receipt of Bid for Pig Launchers & Receivers | HE-ME-480 | HP-ME-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.25 TBE for Isolating Joints | P2543-R01-Oct24..1.EN.6.2.26 TBE for Mainline Ball Valve | Final Issue for Design/ Construction-TBE for Isolating Joints | Final Issue for Design/ Construction-TBE for Mainline Ball Valve | HE-PL-2250 | HE-PL-2310 | FF | In Progress | In Progress | 5
P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | P2543-R01-Oct24..1.EN.1.60.12 Data Sheet - Pipeline Pigging Tees | Issue ICR - Data Sheet - Split Tee | Issue ICR - Data Sheet - Pigging Tees | HE-PL-1330 | HE-PL-1450 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | ALARP Workshop | Study & Issue ICR- HSEIA Study Report | HE-WS-0200 | HE-HS-0490 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | Bow Tie Workshop | Study & Issue ICR- HSEIA Study Report | HE-WS-0190 | HE-HS-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..1.EN.1.44 Detailed crossing drawings-4" | Obtain Company Approval - Pipeline Alignment Sheets-4" | Issue ICR - Detailed crossing drawings-4" | HE-PL-2540 | HE-PL-3110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.12.9 HVAC Design Basis | Final Issue for Design-Design Basis | Issue ICR-Design Basis | HE-DB-0050 | HE-HV-180 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | Complete External / Internal Coating - Lot 9 | Ready for Dispatch of Line Pipes (Coated) - Lot 9 | HM-PL-1260 | HM-PL-1250 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Complete External / Internal Coating - Lot 9 | Receipt at site and inspection of Line Pipes - Lot 9 (Coated) | HM-PL-1260 | HM-PL-960 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | Vendor Document Review of Line Pipes - Lot 7 | Vendor Document Review of Line Pipes - Lot 9 | HM-PL-1150 | HM-PL-1210 | SS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Ready for Dispatch of Line Pipes (Coated) - Lot 7 | Receipt at site and inspection of Line Pipes - Lot 7 (Coated) | HM-PL-1190 | HM-PL-0120 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.4 Lot 6 | P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | Manufacturing & Receive Plates at Fabrication Shop - Lot 6 | Manufacturing & Receive Plates at Fabrication Shop - Lot 7 | HM-PL-1100 | HM-PL-1160 | FF | Completed | Completed | 25
P2543-R01-Oct24..PR.1.16.2.4 Lot 6 | P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | Vendor Document Review of Line Pipes - Lot 6 | Vendor Document Review of Line Pipes - Lot 7 | HM-PL-1090 | HM-PL-1150 | SS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.4 Lot 6 | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Ready for Dispatch of Line Pipes (Coated) - Lot 6 | Receipt at site and inspection of Line Pipes - Lot 6 (Coated) | HM-PL-1130 | HM-PL-0110 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.3 Lot 3 | P2543-R01-Oct24..PR.1.16.2.4 Lot 6 | Vendor Document Review of Line Pipes - Lot 3 | Vendor Document Review of Line Pipes - Lot 6 | HM-PL-1030 | HM-PL-1090 | SS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.3 Lot 3 | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Ready for Dispatch of Line Pipes (Coated) - Lot 3 | Receipt at site and inspection of Line Pipes - Lot 3 (Coated) | HM-PL-1070 | HM-PL-0100 | FF | Completed | Completed | 5
P2543-R01-Oct24..PR.1.16.2.2 Lot 2 | P2543-R01-Oct24..PR.1.16.2.3 Lot 3 | Manufacturing & Receive Plates at Fabrication Shop - Lot 2 | Manufacturing & Receive Plates at Fabrication Shop - Lot 3 | HM-PL-980 | HM-PL-1040 | FF | Completed | Completed | 20
P2543-R01-Oct24..PR.1.16.2.2 Lot 2 | P2543-R01-Oct24..PR.1.16.2.3 Lot 3 | Vendor Document Review of Line Pipes - Lot 2 | Vendor Document Review of Line Pipes - Lot 3 | HM-PL-970 | HM-PL-1030 | SS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.2 Lot 2 | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Ready for Dispatch of Line Pipes (Coated) - Lot 2 | Receipt at site and inspection of Line Pipes - Lot 2 (Coated) | HM-PL-1010 | HM-PL-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | P2543-R01-Oct24..PR.1.16.2.2 Lot 2 | Manufacturing & Receive Plates at Fabrication Shop - Lot 1 | Manufacturing & Receive Plates at Fabrication Shop - Lot 2 | HM-PL-0020 | HM-PL-980 | FF | Completed | Completed | 10
P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | P2543-R01-Oct24..PR.1.16.2.2 Lot 2 | Vendor Document Review of Line Pipes - Lot 1 | Vendor Document Review of Line Pipes - Lot 2 | HM-PL-0010 | HM-PL-970 | SS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | Complete External / Internal Coating - Lot 9 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 9 | HM-PL-1260 | HM-PL-1240 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | Complete Line Pipe Production - Lot 9 | Complete External / Internal Coating - Lot 9 | HM-PL-1230 | HM-PL-1260 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | Vendor Document Review of Line Pipes - Lot 9 | Manufacturing & Receive Plates at Fabrication Shop - Lot 9 | HM-PL-1210 | HM-PL-1220 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | Manufacturing & Receive Plates at Fabrication Shop - Lot 9 | Complete Line Pipe Production - Lot 9 | HM-PL-1220 | HM-PL-1230 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 9 | Ready for Dispatch of Line Pipes (Coated) - Lot 9 | HM-PL-1240 | HM-PL-1250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | Complete External / Internal Coating - Lot 7 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 7 | HM-PL-1200 | HM-PL-1180 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | Complete Line Pipe Production - Lot 7 | Complete External / Internal Coating - Lot 7 | HM-PL-1170 | HM-PL-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | Vendor Document Review of Line Pipes - Lot 7 | Manufacturing & Receive Plates at Fabrication Shop - Lot 7 | HM-PL-1150 | HM-PL-1160 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | Manufacturing & Receive Plates at Fabrication Shop - Lot 7 | Complete Line Pipe Production - Lot 7 | HM-PL-1160 | HM-PL-1170 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 7 | Ready for Dispatch of Line Pipes (Coated) - Lot 7 | HM-PL-1180 | HM-PL-1190 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.4 Lot 6 | P2543-R01-Oct24..PR.1.16.2.4 Lot 6 | Complete External / Internal Coating - Lot 6 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 6 | HM-PL-1140 | HM-PL-1120 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.4 Lot 6 | P2543-R01-Oct24..PR.1.16.2.4 Lot 6 | Complete Line Pipe Production - Lot 6 | Complete External / Internal Coating - Lot 6 | HM-PL-1110 | HM-PL-1140 | FF | Completed | Completed | 28
P2543-R01-Oct24..PR.1.16.2.4 Lot 6 | P2543-R01-Oct24..PR.1.16.2.4 Lot 6 | Vendor Document Review of Line Pipes - Lot 6 | Manufacturing & Receive Plates at Fabrication Shop - Lot 6 | HM-PL-1090 | HM-PL-1100 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.4 Lot 6 | P2543-R01-Oct24..PR.1.16.2.4 Lot 6 | Manufacturing & Receive Plates at Fabrication Shop - Lot 6 | Complete Line Pipe Production - Lot 6 | HM-PL-1100 | HM-PL-1110 | FS | Completed | Completed | 10
P2543-R01-Oct24..PR.1.16.2.4 Lot 6 | P2543-R01-Oct24..PR.1.16.2.4 Lot 6 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 6 | Ready for Dispatch of Line Pipes (Coated) - Lot 6 | HM-PL-1120 | HM-PL-1130 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.3 Lot 3 | P2543-R01-Oct24..PR.1.16.2.3 Lot 3 | Complete External / Internal Coating - Lot 3 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 3 | HM-PL-1080 | HM-PL-1060 | FF | Completed | Completed | 2
P2543-R01-Oct24..PR.1.16.2.3 Lot 3 | P2543-R01-Oct24..PR.1.16.2.3 Lot 3 | Complete Line Pipe Production - Lot 3 | Complete External / Internal Coating - Lot 3 | HM-PL-1050 | HM-PL-1080 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.3 Lot 3 | P2543-R01-Oct24..PR.1.16.2.3 Lot 3 | Vendor Document Review of Line Pipes - Lot 3 | Manufacturing & Receive Plates at Fabrication Shop - Lot 3 | HM-PL-1030 | HM-PL-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.3 Lot 3 | P2543-R01-Oct24..PR.1.16.2.3 Lot 3 | Manufacturing & Receive Plates at Fabrication Shop - Lot 3 | Complete Line Pipe Production - Lot 3 | HM-PL-1040 | HM-PL-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.3 Lot 3 | P2543-R01-Oct24..PR.1.16.2.3 Lot 3 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 3 | Ready for Dispatch of Line Pipes (Coated) - Lot 3 | HM-PL-1060 | HM-PL-1070 | FF | Completed | Completed | 2
P2543-R01-Oct24..PR.1.16.2.2 Lot 2 | P2543-R01-Oct24..PR.1.16.2.2 Lot 2 | Complete External / Internal Coating - Lot 2 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 2 | HM-PL-1020 | HM-PL-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.2 Lot 2 | P2543-R01-Oct24..PR.1.16.2.2 Lot 2 | Complete Line Pipe Production - Lot 2 | Complete External / Internal Coating - Lot 2 | HM-PL-990 | HM-PL-1020 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.2 Lot 2 | P2543-R01-Oct24..PR.1.16.2.2 Lot 2 | Vendor Document Review of Line Pipes - Lot 2 | Manufacturing & Receive Plates at Fabrication Shop - Lot 2 | HM-PL-970 | HM-PL-980 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.2 Lot 2 | P2543-R01-Oct24..PR.1.16.2.2 Lot 2 | Manufacturing & Receive Plates at Fabrication Shop - Lot 2 | Complete Line Pipe Production - Lot 2 | HM-PL-980 | HM-PL-990 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.2 Lot 2 | P2543-R01-Oct24..PR.1.16.2.2 Lot 2 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 2 | Ready for Dispatch of Line Pipes (Coated) - Lot 2 | HM-PL-1000 | HM-PL-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | Complete External / Internal Coating - Lot 1 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 1 | HM-PL-0035 | HM-PL-0040 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | Complete Line Pipe Production - Lot 1 | Complete External / Internal Coating - Lot 1 | HM-PL-0030 | HM-PL-0035 | FF | Completed | Completed | 19
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.PM.1 Smart Plant | Project Kick off Meeting | Issue ICR-Smart Plant | ML1002 | HC-GN-300 | SS | Completed | Completed | 30
P2543-R01-Oct24..1.PM.1 Smart Plant | P2543-R01-Oct24..1.PM.1 Smart Plant | Re-Issue for Approval-Smart Plant | Obtain Company Approval-Smart Plant | HC-GN-320 | HC-GN-330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.1 Smart Plant | P2543-R01-Oct24..1.PM.1 Smart Plant | Issue ICR-Smart Plant | Receive Company Comments-Smart Plant | HC-GN-300 | HC-GN-310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.1 Smart Plant | P2543-R01-Oct24..1.PM.1 Smart Plant | Receive Company Comments-Smart Plant | Re-Issue for Approval-Smart Plant | HC-GN-310 | HC-GN-320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.1 Smart Plant | P2543-R01-Oct24..1.PM.1 Smart Plant | Obtain Company Approval-Smart Plant | Final Issue for Design/ Construction-Smart Plant | HC-GN-330 | HC-GN-290 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | Achieve PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | ML1030 | ML1040 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | ML1020 | ML1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Receive at Site - Coated / Painted Line pipes- 4" (Nitrogen & Water line) | Receive at Site - Coated / Painted Line pipes- 52" (100% to total Qty) | ML1389-D2 | ML1399-D5 | FF | Not Started | Not Started | 21
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Receive at Site - Coated / Painted Line pipes- 56" | Receive at Site - Coated / Painted Line pipes- 4" (Nitrogen & Water line) | ML1052-D1 | ML1389-D2 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Receive at Site - Coated / Painted Line pipes- 52" (50% to total Qty) | Receive at Site - Coated / Painted Line pipes- 56" | ML1509-D3 | ML1052-D1 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Complete Delivery to Site | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | ML1549-D32 | ML1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.6 TBE for MOV | P2543-R01-Oct24..1.1.2.LL.9.1 Ordering | Receive Company Comments- TBE for MOV | Prepare TBE and Company approval for MOV | HE-IC-2060 | HP-ME-0320 | FF | Completed | Completed | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receive at Site - UPS System | Receive at Site - Sales Gas Metering Skids | ML1499-D18 | ML1419-D08 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receive at Site - Leak Detection System | Receive at Site - UPS System | ML1053-D23 | ML1499-D18 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..ML.EN Detail Engineering | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Completion of all Detailed Engineering | ML1032-B21 | ML1219-B29 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.7.10 3D Model | Issue MRs for All E&I Equipment & Packages (Final Issue) | 90% Model Review | ML1027-B17 | HE-PI-0170 | FF | Completed | Completed | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..ML.GE General | Obtain Final Route Approval from Authorities | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | ML1011-A05 | ML1149-A07 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Final Issue for Design/ Construction-Commissioning Manuals | Issue ICR-Pre-commissioning and Commissioning Plan | HE-CO-150 | C-COM-800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.15.5 Material Selection Report | P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | Obtain Company Approval - Material Selection Report | CP Drilling & Earthing Drilling RFQ & Quotation Receipt | HE-CP-230 | HS-CN-0210 | FS | Completed | Completed | 10
P2543-R01-Oct24..1.1.2.25.23.1 Ordering | P2543-R01-Oct24..1.1.2.25.23.1 Ordering | RFQ, Receipt of Bid for LV Switch Gear | Commercial Clarifications & Placement of PO for LV Switch Gear | HP-ME-1330 | HP-ME-1340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.5 TBE for ROV/ GOV | P2543-R01-Oct24..PR.26.LL.10.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-TBE for ROV/ GOV | Vendor Document Review of ROV/ GOV | HE-IC-2330 | HM-ME-0510 | SS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.15.5 Material Selection Report | P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | Final Issue for Design/ Construction-Material Selection Report | Final Issue for Design/ Construction-Piping Material Specification | HE-CP-240 | HE-PI-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | P2543-R01-Oct24..1.EN.15.5 Material Selection Report | Final Issue for Design/ Construction-Material Selection Diagram | Final Issue for Design/ Construction-Material Selection Report | HE-CP-0050 | HE-CP-240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | P2543-R01-Oct24..1.EN.15.5 Material Selection Report | Obtain Company Approval - Material Selection Diagram | Obtain Company Approval - Material Selection Report | HE-CP-0040 | HE-CP-230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.6 Project Risk Review Register | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Project Risk Review Register | Issue ICR-Construction Procedures / Method Statements / ITPs | HE-RR-0050 | C-COM-750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..ML Milestones | Wrap up works for PAC-1 | Achieve PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | CCM-PM4550 | ML1040 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..4.4.2 Commissioning | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | Wrap up works for PAC-1 | CCM-PM4510 | CCM-PM4550 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.12.A111111 TBE for Material Handling Equipment | P2543-R01-Oct24..PR.26.LL.24.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction- TBE for Material Handling | Vendor Document Review of Filter Package | HE-HV-2930 | HM-ME-2070 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..PR.26.LL.24.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.24.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Filter Package | Testing and Inspection of Filter Package | HM-ME-2080 | HM-ME-2090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.24.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.24.3 Delivery & receipt at Site | Ready for Dispatch of Filter Package | Transportation/ Custom Clearance/ Delivery at site of Filter Package | HM-ME-2110 | HM-ME-2130 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.24.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.24.2 Manufacturing & Ready for Dispatch | Testing and Inspection of Filter Package | Packaging & Final Inspection-Filter Package | HM-ME-2090 | HM-ME-2100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.24.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.24.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Filter Package | Ready for Dispatch of Filter Package | HM-ME-2100 | HM-ME-2110 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.24.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.24.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Filter Package | Receipt at site and inspection of Filter Package | HM-ME-2130 | HM-ME-2120 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.24.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.24.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Filter Package | Manufacturing & Assembly of Filter Package | HM-ME-2070 | HM-ME-2080 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.12.A111111 TBE for Material Handling Equipment | P2543-R01-Oct24..1.1.2.25.24.1 Ordering | Issue ICR- TBE for Material Handling | Prepare TBE and Company approval for Lifting Equipment | HE-HV-2890 | HP-ME-1380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A11111 MR for Material Handling Equipment | P2543-R01-Oct24..1.1.2.25.24.1 Ordering | Issue ICR- Material Requisition for Material Handling | RFQ, Receipt of Bid for Lifting Equipment | HE-HV-2840 | HP-ME-1360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.24.1 Ordering | P2543-R01-Oct24..1.1.2.25.24.1 Ordering | Prepare TBE and Company approval for Lifting Equipment | Commercial Clarifications & Placement of PO for Lifting Equipment | HP-ME-1380 | HP-ME-1370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.24.1 Ordering | P2543-R01-Oct24..1.1.2.25.24.1 Ordering | RFQ, Receipt of Bid for Lifting Equipment | Prepare TBE and Company approval for Lifting Equipment | HP-ME-1360 | HP-ME-1380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.24.1 Ordering | P2543-R01-Oct24..1.1.2.25.24.1 Ordering | RFQ, Receipt of Bid for Lifting Equipment | Prepare TBE and Company approval for Lifting Equipment | HP-ME-1360 | HP-ME-1380 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.24.1 Ordering | P2543-R01-Oct24..1.1.2.25.24.1 Ordering | RFQ, Receipt of Bid for Lifting Equipment | Commercial Clarifications & Placement of PO for Lifting Equipment | HP-ME-1360 | HP-ME-1370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.23.1 Ordering | P2543-R01-Oct24..PR.26.1.23.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for LV Switch Gear | Vendor Document Review of LV Switch Gear | HP-ME-1340 | HM-ME-2040 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.1 TBE for LV Switchgear | P2543-R01-Oct24..1.1.2.25.23.1 Ordering | Issue ICR-TBE for LV Switchgear | Prepare TBE and Company approval for LV Switch Gear | HE-EL-2210 | HP-ME-1350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | P2543-R01-Oct24..1.1.2.25.23.1 Ordering | Issue ICR-Material Requisition for LV Switchgear | RFQ, Receipt of Bid for LV Switch Gear | HE-EL-1960 | HP-ME-1330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.23.1 Ordering | P2543-R01-Oct24..1.1.2.25.23.1 Ordering | RFQ, Receipt of Bid for LV Switch Gear | Prepare TBE and Company approval for LV Switch Gear | HP-ME-1330 | HP-ME-1350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.23.1 Ordering | P2543-R01-Oct24..1.1.2.25.23.1 Ordering | Prepare TBE and Company approval for LV Switch Gear | Commercial Clarifications & Placement of PO for LV Switch Gear | HP-ME-1350 | HP-ME-1340 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.1.23.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.23.3 Delivery & receipt at Site | Ready for Dispatch of LV Switch Gear | Transportation/ Custom Clearance/ Delivery at site of LV Switch Gear | HM-ME-2030 | HM-ME-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.23.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.23.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of LV Switch Gear | Packaging & Final Inspection-LV Switch Gear | HM-ME-2010 | HM-ME-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.23.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.23.2 Manufacturing & Ready for Dispatch | Vendor Document Review of LV Switch Gear | Manufacturing & Assembly of LV Switch Gear | HM-ME-2040 | HM-ME-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.23.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.1.23.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of LV Switch Gear | Receipt at site and inspection of LV Switch Gear | HM-ME-2050 | HM-ME-2060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.23.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.23.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-LV Switch Gear | Ready for Dispatch of LV Switch Gear | HM-ME-2020 | HM-ME-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.23.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.23.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of LV Switch Gear | Factory Acceptance Test of LV Switch Gear | HM-ME-2000 | HM-ME-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.7.2 Manufacturing & Ready for Dispatch | 1st Electrical Bulk material MTO | Final Electrical Bulk material MTO | HM-EL-0490 | HM-EL-0500 | FF | Not Started | Not Started | 65
P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | P2543-R01-Oct24..PR.1.1.2 Manufacturing & Ready for Dispatch | Manufacturing & Receive Plates at Fabrication Shop - Lot 1 | Manufacturing & Assembly of Hot Incution Bend | HM-PL-0020 | HM-PL-0570 | SS | Completed | In Progress | 150
P2543-R01-Oct24..1.EN.8.6 Anchor Block Detailed Drawings | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction - Anchor Block Detail Drawings | Completion of all Detailed Engineering | HE-CS-1800 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.6 Anchor Block Detailed Drawings | P2543-R01-Oct24..1.EN.8.6 Anchor Block Detailed Drawings | Review Company Comments - Anchor Block Detail Drawings | Re-Issue for Approval - Anchor Block Detail Drawings | HE-CS-1770 | HE-CS-1780 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.6 Anchor Block Detailed Drawings | P2543-R01-Oct24..1.EN.8.6 Anchor Block Detailed Drawings | Issued for Review - Anchor Block Detail Drawings | Review Company Comments - Anchor Block Detail Drawings | HE-CS-1760 | HE-CS-1770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.6 Anchor Block Detailed Drawings | P2543-R01-Oct24..1.EN.8.6 Anchor Block Detailed Drawings | Obtain Company Approval - Anchor Block Detail Drawings | Final Issue for Design/ Construction - Anchor Block Detail Drawings | HE-CS-1790 | HE-CS-1800 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.6 Anchor Block Detailed Drawings | P2543-R01-Oct24..1.EN.8.6 Anchor Block Detailed Drawings | Re-Issue for Approval - Anchor Block Detail Drawings | Obtain Company Approval - Anchor Block Detail Drawings | HE-CS-1780 | HE-CS-1790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.5 Anchor Block Calculation | P2543-R01-Oct24..1.EN.8.5 Anchor Block Calculation | Review Company Comments - Anchor Block Calculation | Re-Issue for Approval - Anchor Block Calculation | HE-CS-1720 | HE-CS-1730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.5 Anchor Block Calculation | P2543-R01-Oct24..1.EN.8.5 Anchor Block Calculation | Issued for Review - Anchor Block Calculation | Review Company Comments - Anchor Block Calculation | HE-CS-1710 | HE-CS-1720 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.5 Anchor Block Calculation | P2543-R01-Oct24..1.EN.8.5 Anchor Block Calculation | Obtain Company Approval - Anchor Block Calculation | Final Issue for Design/ Construction-Anchor Block Calculation | HE-CS-1740 | HE-CS-1750 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.5 Anchor Block Calculation | P2543-R01-Oct24..1.EN.8.5 Anchor Block Calculation | Re-Issue for Approval - Anchor Block Calculation | Obtain Company Approval - Anchor Block Calculation | HE-CS-1730 | HE-CS-1740 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | HE-PL-2550 | ML1219-B59 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | HE-PL-2490 | ML1219-B49 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | HE-PL-2430 | ML1219-B39 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..4.4.AB.3 As-built Survey | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | Intelligent Pigging Baseline Survey | CCM-PM4520 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.3 As-built Survey | P2543-R01-Oct24..ML Milestones | Intelligent Pigging Baseline Survey | Achieve PAC-2 for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | CCM-PM4540 | ML1050 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Approval of Commissioning Dossiers | Intelligent Pigging Baseline Survey | CCM-PM4500 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.3 As-built Survey | P2543-R01-Oct24..ML.4 Commissioning and PAC | Intelligent Pigging Baseline Survey | Achieve (PAC-2) for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | CCM-PM4540 | ML2049-F06 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.3 As-built Survey | P2543-R01-Oct24..4.4.AB As-Built & Final Documentation | Intelligent Pigging Baseline Survey | Demolitionbilization | CCM-PM4540 | A3980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Ready for Dispatch of Line Pipes (Coated) - Lot 1 | Receipt at site and inspection of Line Pipes - Lot 1 (Coated) | HM-PL-0050 | HM-PL-0080 | SS | Completed | Completed | 4
P2543-R01-Oct24..1.1.1.16.1 Ordering | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Commercial Clarifications & Placement of PO for Line Pipes (Coated) | Main Office | HP-ME-1040 | CTF-SO1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..1.2.13.11 Cathodic Protection Work | Obtain Company Approval - Pipeline Alignment Sheets -56" | Prepare/Issue Scope of Work - Cathodic Protection Work | HE-PL-2420 | HS-GN-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.9.12 Earthing Layout | Re-Issue after incorporating HAZOP / Review Comments- Plot plan - BVS | Issue ICR-Earthing Layout | HE-PI-0560 | HE-EL-1630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..1.EN.9.12 Earthing Layout | Issue ICR- Electrical Equipment Layout | Issue ICR-Earthing Layout | HE-EL-0490 | HE-EL-1630 | FS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | Re-Issue after incorporating HAZOP / Review Comments- Plot plan - BVS | Issue ICR-Cable Routing Layout | HE-PI-0560 | HE-EL-1570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | Issue ICR-Cable Sizing Calculation | Issue ICR-Material Requisition for Glanding & Termination | HE-EL-0430 | HE-EL-2010 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.10 Equipment List | P2543-R01-Oct24..1.EN.7.10 3D Model | Issue ICR - Equipment List | 30% Model Review | HE-PR-1030 | HE-PI-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | Issue ICR-Design Basis | Issue ICR- Isolation & Tie-In philosophy | HE-DB-0010 | HE-PR-0850 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Issue ICR- Isolation & Tie-In philosophy | Issue ICR- P&ID's | HE-PR-0850 | HE-PR-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- Process Simulations Report | Process | HE-PR-0610 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Issue ICR- Process Simulations Report | Final Issue for Design / Construction-P&ID's | HE-PR-0610 | HE-PR-0160 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.1.3 Pipeline Upheavl Calculation | Issue ICR- Process Simulations Report | Final Issue for Design/ Construction-Pipeline Upheaval Calculation | HE-PR-0610 | HE-PL-0650 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Process Simulations Report | Process | HE-PR-0650 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.1.3 Pipeline Upheavl Calculation | Final Issue for Design/ Construction-Process Simulations Report | Final Issue for Design/ Construction-Pipeline Upheaval Calculation | HE-PR-0650 | HE-PL-0650 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..ML.EN Detail Engineering | Issue ICR- Process Flow Diagrams ( New + Existing) | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-PR-0040 | ML1219-B19 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.17 Line List | Issue ICR- Process Flow Diagrams ( New + Existing) | Final Issue for Design/ Construction-Line List | HE-PR-0040 | HE-PR-1130 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.10 3D Model | Issue ICR- Process Flow Diagrams ( New + Existing) | 90% Model Review | HE-PR-0040 | HE-PI-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..ML.EN Detail Engineering | Issue ICR- H&MB Report | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-PR-1240 | ML1219-B19 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.17 Line List | Issue ICR- H&MB Report | Final Issue for Design/ Construction-Line List | HE-PR-1240 | HE-PR-1130 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.10 3D Model | Issue ICR- H&MB Report | 90% Model Review | HE-PR-1240 | HE-PI-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..ML.EN Detail Engineering | Receive Company Comments- H&MB Report | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-PR-1250 | ML1219-B19 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.17 Line List | Receive Company Comments- H&MB Report | Final Issue for Design/ Construction-Line List | HE-PR-1250 | HE-PR-1130 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.10 3D Model | Receive Company Comments- H&MB Report | 90% Model Review | HE-PR-1250 | HE-PI-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-PR-0060 | ML1219-B19 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.17 Line List | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Final Issue for Design/ Construction-Line List | HE-PR-0060 | HE-PR-1130 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.10 3D Model | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | 90% Model Review | HE-PR-0060 | HE-PI-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..ML.EN Detail Engineering | Design Review Workshop | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-WS-0030 | ML1219-B19 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.3.17 Line List | Design Review Workshop | Final Issue for Design/ Construction-Line List | HE-WS-0030 | HE-PR-1130 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.7.10 3D Model | Design Review Workshop | 90% Model Review | HE-WS-0030 | HE-PI-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..ML.EN Detail Engineering | Issue ICR- HAZOP reviews Report for all areas | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-HS-0670 | ML1219-B19 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.3.17 Line List | Issue ICR- HAZOP reviews Report for all areas | Final Issue for Design/ Construction-Line List | HE-HS-0670 | HE-PR-1130 | SS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.7.10 3D Model | Issue ICR- HAZOP reviews Report for all areas | 90% Model Review | HE-HS-0670 | HE-PI-0170 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-PR-0070 | ML1219-B19 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.17 Line List | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Final Issue for Design/ Construction-Line List | HE-PR-0070 | HE-PR-1130 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.10 3D Model | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | 90% Model Review | HE-PR-0070 | HE-PI-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue after incorporating Review Comments- H&MB Report | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-PR-1200 | ML1219-B19 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.17 Line List | Re-Issue after incorporating Review Comments- H&MB Report | Final Issue for Design/ Construction-Line List | HE-PR-1200 | HE-PR-1130 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.10 3D Model | Re-Issue after incorporating Review Comments- H&MB Report | 90% Model Review | HE-PR-1200 | HE-PI-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Process Flow Diagrams ( New + Existing) | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-PR-0090 | ML1219-B19 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Process Simulations Report | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-PR-0650 | ML1219-B19 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.7.10 3D Model | Final Issue for Design/ Construction-Process Simulations Report | 90% Model Review | HE-PR-0650 | HE-PI-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction- H&MB Report | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-PR-1220 | ML1219-B19 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | Issue ICR- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval-Isolation & Tie-In philosophy | HE-PR-0040 | HE-PR-0870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Issue ICR- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets - Filters (At Sweihan CRS) | HE-PR-0040 | HE-PR-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | Issue ICR- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0040 | HE-PR-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | Issue ICR- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0040 | HE-PR-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | Issue ICR- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0040 | HE-PR-1330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | Issue ICR- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0040 | HE-PR-1380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | Issue ICR- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0040 | HE-PR-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | Issue ICR- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0040 | HE-PR-1480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | Issue ICR- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0040 | HE-PR-1530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | Issue ICR- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0040 | HE-PR-1580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | Issue ICR- H&MB Report | Re-Issue for Approval-Isolation & Tie-In philosophy | HE-PR-1240 | HE-PR-0870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Issue ICR- H&MB Report | Re-Issue for Approval- Process Datasheets - Filters (At Sweihan CRS) | HE-PR-1240 | HE-PR-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | Issue ICR- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1240 | HE-PR-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | Issue ICR- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1240 | HE-PR-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | Issue ICR- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1240 | HE-PR-1330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | Issue ICR- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1240 | HE-PR-1380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | Issue ICR- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1240 | HE-PR-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | Issue ICR- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1240 | HE-PR-1480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | Issue ICR- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1240 | HE-PR-1530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | Issue ICR- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1240 | HE-PR-1580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | Receive Company Comments- H&MB Report | Re-Issue for Approval-Isolation & Tie-In philosophy | HE-PR-1250 | HE-PR-0870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Receive Company Comments- H&MB Report | Re-Issue for Approval- Process Datasheets - Filters (At Sweihan CRS) | HE-PR-1250 | HE-PR-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | Receive Company Comments- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1250 | HE-PR-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | Receive Company Comments- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1250 | HE-PR-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | Receive Company Comments- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1250 | HE-PR-1330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | Receive Company Comments- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1250 | HE-PR-1380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | Receive Company Comments- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1250 | HE-PR-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | Receive Company Comments- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1250 | HE-PR-1480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | Receive Company Comments- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1250 | HE-PR-1530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | Receive Company Comments- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1250 | HE-PR-1580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval-Isolation & Tie-In philosophy | HE-PR-0060 | HE-PR-0870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets - Filters (At Sweihan CRS) | HE-PR-0060 | HE-PR-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0060 | HE-PR-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0060 | HE-PR-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0060 | HE-PR-1330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0060 | HE-PR-1380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0060 | HE-PR-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0060 | HE-PR-1480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0060 | HE-PR-1530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0060 | HE-PR-1580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | Design Review Workshop | Re-Issue for Approval-Isolation & Tie-In philosophy | HE-WS-0030 | HE-PR-0870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Design Review Workshop | Re-Issue for Approval- Process Datasheets - Filters (At Sweihan CRS) | HE-WS-0030 | HE-PR-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | Design Review Workshop | Re-Issue for Approval- Process Datasheets | HE-WS-0030 | HE-PR-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | Design Review Workshop | Re-Issue for Approval- Process Datasheets | HE-WS-0030 | HE-PR-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | Design Review Workshop | Re-Issue for Approval- Process Datasheets | HE-WS-0030 | HE-PR-1330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | Design Review Workshop | Re-Issue for Approval- Process Datasheets | HE-WS-0030 | HE-PR-1380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | Design Review Workshop | Re-Issue for Approval- Process Datasheets | HE-WS-0030 | HE-PR-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | Design Review Workshop | Re-Issue for Approval- Process Datasheets | HE-WS-0030 | HE-PR-1480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | Design Review Workshop | Re-Issue for Approval- Process Datasheets | HE-WS-0030 | HE-PR-1530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | Design Review Workshop | Re-Issue for Approval- Process Datasheets | HE-WS-0030 | HE-PR-1580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | Issue ICR- HAZOP reviews Report for all areas | Re-Issue for Approval-Isolation & Tie-In philosophy | HE-HS-0670 | HE-PR-0870 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Issue ICR- HAZOP reviews Report for all areas | Re-Issue for Approval- Process Datasheets - Filters (At Sweihan CRS) | HE-HS-0670 | HE-PR-0450 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | Issue ICR- HAZOP reviews Report for all areas | Re-Issue for Approval- Process Datasheets | HE-HS-0670 | HE-PR-0570 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | Issue ICR- HAZOP reviews Report for all areas | Re-Issue for Approval- Process Datasheets | HE-HS-0670 | HE-PR-1280 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | Issue ICR- HAZOP reviews Report for all areas | Re-Issue for Approval- Process Datasheets | HE-HS-0670 | HE-PR-1330 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | Issue ICR- HAZOP reviews Report for all areas | Re-Issue for Approval- Process Datasheets | HE-HS-0670 | HE-PR-1380 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | Issue ICR- HAZOP reviews Report for all areas | Re-Issue for Approval- Process Datasheets | HE-HS-0670 | HE-PR-1430 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | Issue ICR- HAZOP reviews Report for all areas | Re-Issue for Approval- Process Datasheets | HE-HS-0670 | HE-PR-1480 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | Issue ICR- HAZOP reviews Report for all areas | Re-Issue for Approval- Process Datasheets | HE-HS-0670 | HE-PR-1530 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | Issue ICR- HAZOP reviews Report for all areas | Re-Issue for Approval- Process Datasheets | HE-HS-0670 | HE-PR-1580 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval-Isolation & Tie-In philosophy | HE-PR-0070 | HE-PR-0870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets - Filters (At Sweihan CRS) | HE-PR-0070 | HE-PR-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0070 | HE-PR-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0070 | HE-PR-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0070 | HE-PR-1330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0070 | HE-PR-1380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0070 | HE-PR-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0070 | HE-PR-1480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0070 | HE-PR-1530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval- Process Datasheets | HE-PR-0070 | HE-PR-1580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue for Approval-Isolation & Tie-In philosophy | HE-PR-1200 | HE-PR-0870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue for Approval- Process Datasheets - Filters (At Sweihan CRS) | HE-PR-1200 | HE-PR-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1200 | HE-PR-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1200 | HE-PR-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1200 | HE-PR-1330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1200 | HE-PR-1380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1200 | HE-PR-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1200 | HE-PR-1480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1200 | HE-PR-1530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue for Approval- Process Datasheets | HE-PR-1200 | HE-PR-1580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Issue ICR- Process Flow Diagrams ( New + Existing) | Issue ICR-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-PR-0040 | HE-HS-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.10 3D Model | Issue ICR- Process Flow Diagrams ( New + Existing) | 60% Model Review | HE-PR-0040 | HE-PI-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | Issue ICR- Process Flow Diagrams ( New + Existing) | Issue ICR- HAZOP reviews Report for all areas | HE-PR-0040 | HE-HS-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- Process Flow Diagrams ( New + Existing) | Constructability Review Workshop | HE-PR-0040 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | Issue ICR- Process Flow Diagrams ( New + Existing) | Study & Issue ICR- HSEIA Study Report | HE-PR-0040 | HE-HS-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.10 3D Model | Issue ICR- Process Flow Diagrams ( New + Existing) | 30% Model Review | HE-PR-0040 | HE-PI-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Issue ICR- Process Flow Diagrams ( New + Existing) | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-PR-0040 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Issue ICR- Process Flow Diagrams ( New + Existing) | General | HE-PR-0040 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..ML.EN Detail Engineering | Issue ICR- Process Flow Diagrams ( New + Existing) | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | HE-PR-0040 | ML1012-B06 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | Issue ICR- Process Flow Diagrams ( New + Existing) | Issue ICR-Tie-In Schedule | HE-PR-0040 | HE-PR-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- Process Flow Diagrams ( New + Existing) | HAZOP Workshop | HE-PR-0040 | HE-WS-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Issue ICR- H&MB Report | Issue ICR-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-PR-1240 | HE-HS-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.10 3D Model | Issue ICR- H&MB Report | 60% Model Review | HE-PR-1240 | HE-PI-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | Issue ICR- H&MB Report | Issue ICR- HAZOP reviews Report for all areas | HE-PR-1240 | HE-HS-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- H&MB Report | Constructability Review Workshop | HE-PR-1240 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | Issue ICR- H&MB Report | Study & Issue ICR- HSEIA Study Report | HE-PR-1240 | HE-HS-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.10 3D Model | Issue ICR- H&MB Report | 30% Model Review | HE-PR-1240 | HE-PI-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Issue ICR- H&MB Report | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-PR-1240 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Issue ICR- H&MB Report | General | HE-PR-1240 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..ML.EN Detail Engineering | Issue ICR- H&MB Report | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | HE-PR-1240 | ML1012-B06 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | Issue ICR- H&MB Report | Issue ICR-Tie-In Schedule | HE-PR-1240 | HE-PR-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- H&MB Report | HAZOP Workshop | HE-PR-1240 | HE-WS-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Receive Company Comments- H&MB Report | Issue ICR-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-PR-1250 | HE-HS-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.10 3D Model | Receive Company Comments- H&MB Report | 60% Model Review | HE-PR-1250 | HE-PI-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | Receive Company Comments- H&MB Report | Issue ICR- HAZOP reviews Report for all areas | HE-PR-1250 | HE-HS-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.PM.12 Workshops | Receive Company Comments- H&MB Report | Constructability Review Workshop | HE-PR-1250 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | Receive Company Comments- H&MB Report | Study & Issue ICR- HSEIA Study Report | HE-PR-1250 | HE-HS-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.10 3D Model | Receive Company Comments- H&MB Report | 30% Model Review | HE-PR-1250 | HE-PI-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Receive Company Comments- H&MB Report | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-PR-1250 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receive Company Comments- H&MB Report | General | HE-PR-1250 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | Receive Company Comments- H&MB Report | Issue ICR-Tie-In Schedule | HE-PR-1250 | HE-PR-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.PM.12 Workshops | Receive Company Comments- H&MB Report | HAZOP Workshop | HE-PR-1250 | HE-WS-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Issue ICR-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-PR-0060 | HE-HS-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.10 3D Model | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | 60% Model Review | HE-PR-0060 | HE-PI-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Issue ICR- HAZOP reviews Report for all areas | HE-PR-0060 | HE-HS-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.PM.12 Workshops | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Constructability Review Workshop | HE-PR-0060 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Study & Issue ICR- HSEIA Study Report | HE-PR-0060 | HE-HS-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.10 3D Model | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | 30% Model Review | HE-PR-0060 | HE-PI-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-PR-0060 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | General | HE-PR-0060 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Issue ICR-Tie-In Schedule | HE-PR-0060 | HE-PR-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.PM.12 Workshops | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | HAZOP Workshop | HE-PR-0060 | HE-WS-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..ML.EN Detail Engineering | Design Review Workshop | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | HE-WS-0030 | ML1012-B06 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | Design Review Workshop | Issue ICR-Tie-In Schedule | HE-WS-0030 | HE-PR-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.PM.12 Workshops | Design Review Workshop | HAZOP Workshop | HE-WS-0030 | HE-WS-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.17 Line List | Issue ICR- Process Flow Diagrams ( New + Existing) | Issue ICR- Line List | HE-PR-0040 | HE-PR-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.17 Line List | Issue ICR- H&MB Report | Issue ICR- Line List | HE-PR-1240 | HE-PR-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Receive Company Comments- H&MB Report | Re-Issue for HAZOP Studies- Overall Plot Plan - 52" Pipeline SWEIHAN CRS | HE-PR-1250 | HE-PI-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Receive Company Comments- H&MB Report | Re-Issue for HAZOP Studies- P&ID's review | HE-PR-1250 | HE-PR-0130 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Receive Company Comments- H&MB Report | Re-Issue for HAZOP Studies- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-1250 | HE-PI-0340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..ML.EN Detail Engineering | Receive Company Comments- H&MB Report | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | HE-PR-1250 | ML1012-B06 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Receive Company Comments- H&MB Report | Re-Issue for HAZOP Studies- Plot plan - BVS | HE-PR-1250 | HE-PI-0550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Receive Company Comments- H&MB Report | Re-Issue for HAZOP Studies- Overall Plot Plan - 4" N2 Source Pipeline | HE-PR-1250 | HE-PI-0480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | Receive Company Comments- H&MB Report | Re-Issue after incorporating Review Comments- H&MB Report | HE-PR-1250 | HE-PR-1200 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | Vendor Document Review of Pig Launchers & Receivers | Issue ICR-Piping Stress Analysis & Report | HM-ME-0410 | HE-PI-1140 | SS | Completed | Completed | 15
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..ML.EN Detail Engineering | Issue SLD, Hazardous Area Classification Details for All Areas - IFC | Completion of all Detailed Engineering | ML1031-B20 | ML1219-B29 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..ML.EN Detail Engineering | HAZOP Workshop | 30% Model Review | HE-WS-0210 | ML2059-B05 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Re-Issue for HAZOP Studies- P&ID's review | Issue ICR-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-PR-0130 | HE-HS-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.7.10 3D Model | Re-Issue for HAZOP Studies- P&ID's review | 60% Model Review | HE-PR-0130 | HE-PI-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | Re-Issue for HAZOP Studies- P&ID's review | Issue ICR- HAZOP reviews Report for all areas | HE-PR-0130 | HE-HS-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.PM.12 Workshops | Re-Issue for HAZOP Studies- P&ID's review | Constructability Review Workshop | HE-PR-0130 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | Re-Issue for HAZOP Studies- P&ID's review | Study & Issue ICR- HSEIA Study Report | HE-PR-0130 | HE-HS-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Re-Issue for HAZOP Studies- P&ID's review | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-PR-0130 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Re-Issue for HAZOP Studies- P&ID's review | General | HE-PR-0130 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.13.9 HSE Studies | P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Place LOA/FOA - HSE Studies | Issue ICR-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HS-GN-0110 | HE-HS-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.9 HSE Studies | P2543-R01-Oct24..1.EN.7.10 3D Model | Place LOA/FOA - HSE Studies | 60% Model Review | HS-GN-0110 | HE-PI-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.9 HSE Studies | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | Place LOA/FOA - HSE Studies | Issue ICR- HAZOP reviews Report for all areas | HS-GN-0110 | HE-HS-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.9 HSE Studies | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | Place LOA/FOA - HSE Studies | Study & Issue ICR- HSEIA Study Report | HS-GN-0110 | HE-HS-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.9 HSE Studies | P2543-R01-Oct24..1.EN.7.10 3D Model | Place LOA/FOA - HSE Studies | 30% Model Review | HS-GN-0110 | HE-PI-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.9 HSE Studies | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Place LOA/FOA - HSE Studies | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HS-GN-0110 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.13.9 HSE Studies | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Place LOA/FOA - HSE Studies | General | HS-GN-0110 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Issue ICR-HAZOP Procedure | Issue ICR-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-HS-0190 | HE-HS-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | P2543-R01-Oct24..1.EN.7.10 3D Model | Issue ICR-HAZOP Procedure | 60% Model Review | HE-HS-0190 | HE-PI-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR-HAZOP Procedure | Constructability Review Workshop | HE-HS-0190 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | Issue ICR-HAZOP Procedure | Study & Issue ICR- HSEIA Study Report | HE-HS-0190 | HE-HS-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | P2543-R01-Oct24..1.EN.7.10 3D Model | Issue ICR-HAZOP Procedure | 30% Model Review | HE-HS-0190 | HE-PI-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Issue ICR-HAZOP Procedure | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-HS-0190 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Issue ICR-HAZOP Procedure | General | HE-HS-0190 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HAZID /ENVID/OHID/ PHSER Workshop | Issue ICR-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-WS-0020 | HE-HS-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | HAZID /ENVID/OHID/ PHSER Workshop | Issue ICR- HAZOP reviews Report for all areas | HE-WS-0020 | HE-HS-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.PM.12 Workshops | HAZID /ENVID/OHID/ PHSER Workshop | Constructability Review Workshop | HE-WS-0020 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | HAZID /ENVID/OHID/ PHSER Workshop | Study & Issue ICR- HSEIA Study Report | HE-WS-0020 | HE-HS-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.7.10 3D Model | HAZID /ENVID/OHID/ PHSER Workshop | 30% Model Review | HE-WS-0020 | HE-PI-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | HAZID /ENVID/OHID/ PHSER Workshop | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-WS-0020 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..4.4.AB.2 Final Documentation | HAZID /ENVID/OHID/ PHSER Workshop | General | HE-WS-0020 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Design Review Workshop | Issue ICR-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-WS-0030 | HE-HS-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.7.10 3D Model | Design Review Workshop | 60% Model Review | HE-WS-0030 | HE-PI-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | Design Review Workshop | Issue ICR- HAZOP reviews Report for all areas | HE-WS-0030 | HE-HS-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.PM.12 Workshops | Design Review Workshop | Constructability Review Workshop | HE-WS-0030 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | Design Review Workshop | Study & Issue ICR- HSEIA Study Report | HE-WS-0030 | HE-HS-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.7.10 3D Model | Design Review Workshop | 30% Model Review | HE-WS-0030 | HE-PI-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Design Review Workshop | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-WS-0030 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Design Review Workshop | General | HE-WS-0030 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.PM.12 Workshops | HAZOP Workshop | CRAS Workshop | HE-WS-0210 | HE-WS-0310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | P2543-R01-Oct24..1.EN.4.11 QRA Report | Study & Issue ICR- HSEIA Study Report | Issue ICR-QRA Report | HE-HS-0490 | HE-HS-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..4.4.2 Commissioning | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | Wrap up works for PAC-2 | CCM-PM4520 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..ML Milestones | Wrap up works for PAC-2 | Achieve PAC-2 for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | CCM-PM4530 | ML1050 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..4.4.2 Commissioning | Approval of Commissioning Dossiers | Wrap up works for PAC-2 | CCM-PM4500 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..ML.4 Commissioning and PAC | Wrap up works for PAC-2 | Achieve (PAC-2) for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | CCM-PM4530 | ML2049-F06 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..4.4.AB As-Built & Final Documentation | Wrap up works for PAC-2 | Demolitionbilization | CCM-PM4530 | A3980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | Issue ICR - Geo Technical Survey Report (Overall) | Issue ICR - Overall Pipeline Route Map - 4" | HE-GS-0010 | HE-PL-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | Issue ICR-Topographical Survey Report (Overall) | Issue ICR - Overall Pipeline Route Map - 4" | HE-TS-0010 | HE-PL-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | Issue ICR - Geo Technical Survey Report (Overall) | Issue ICR - Overall Pipeline Route Map - 52" | HE-GS-0010 | HE-PL-0190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | Issue ICR-Topographical Survey Report (Overall) | Issue ICR - Overall Pipeline Route Map - 52" | HE-TS-0010 | HE-PL-0190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | Issue ICR - Geo Technical Survey Report (Overall) | Issue ICR - Overall Pipeline Route Map - 56" | HE-GS-0010 | HE-PL-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | Issue ICR-Topographical Survey Report (Overall) | Issue ICR - Overall Pipeline Route Map - 56" | HE-TS-0010 | HE-PL-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.9.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Prepare TBE and Company approval for MOV | Completion of Procurement Services | HP-ME-0320 | ML1038-C20 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..1.2.12.16 Pipe Internal Coating | NDT / PWHT RFQ & Quotation Receipt | Pipe Internal Coating RFQ & Quotation Receipt | HS-CN-0160 | HS-CN-750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.16 Pipe Internal Coating | P2543-R01-Oct24..1.2.12.16 Pipe Internal Coating | Pipe Internal Coating RFQ & Quotation Receipt | Pipe Internal Coating Complete Evaluation (Internal) | HS-CN-750 | HS-CN-760 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.16 Pipe Internal Coating | P2543-R01-Oct24..1.2.12.16 Pipe Internal Coating | Pipe Internal Coating Complete Evaluation (Internal) | Pipe Internal Coating Subcontract Award | HS-CN-760 | HS-CN-730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..1.2.12.15 Automatic Welding | NDT / PWHT RFQ & Quotation Receipt | Automatic Welding RFQ & Quotation Receipt | HS-CN-0160 | HS-CN-710 | FS | Completed | Completed | 15
P2543-R01-Oct24..1.2.12.15 Automatic Welding | P2543-R01-Oct24..1.2.12.15 Automatic Welding | Automatic Welding RFQ & Quotation Receipt | Automatic Welding Complete Evaluation (Internal) | HS-CN-710 | HS-CN-720 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.15 Automatic Welding | P2543-R01-Oct24..1.2.12.15 Automatic Welding | Automatic Welding Complete Evaluation (Internal) | Automatic Welding Subcontract Award | HS-CN-720 | HS-CN-690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.2.1 Ordering | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | RFQ, Receipt of Bid for Fire Suppression System | Complete Delivery to Site | HP-ME-0910 | ML1549-D32 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.12 Modification of Existing Telecom System | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Commercial Clarifications & Placement of PO - Modification of Existing Telecom System | Complete Delivery to Site | HS-GN-0350 | ML1549-D32 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.10 Modification of Existing CTMM | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Commercial Clarifications & Placement of PO - Modification of Exiting CTMM | Complete Delivery to Site | HS-GN-0290 | ML1549-D32 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.16.1 Ordering | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | RFQ, Receipt of Bid for MCT | Complete Delivery to Site | HP-BK-0210 | ML1549-D32 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.15.1 Ordering | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | RFQ, Receipt of Bid for Earthing Material | Complete Delivery to Site | HP-BK-0160 | ML1549-D32 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.13.1 Ordering | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | RFQ, Receipt of Bid for Cable Trays | Complete Delivery to Site | HP-BK-0110 | ML1549-D32 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.1.1.4.1 Ordering | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | RFQ, Receipt of Bid for Anchor Flanges | Complete Delivery to Site | HP-ME-1310 | ML1549-D32 | FF | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Power & Control Cables (Lot 1) | Complete Delivery to Site | HM-EL-0080 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Cable Trays (Lot 2) | Complete Delivery to Site | HM-EL-0280 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.3.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Cable Gland and Termination (Lot 1) | Complete Delivery to Site | HM-EL-580 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Earthing Material (Lot 1) | Complete Delivery to Site | HM-EL-0380 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.16.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of MCT (Lot 1) | Complete Delivery to Site | HM-EL-0480 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Final Piping Bulk material MTO | Complete Delivery to Site | HM-PI-0050 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.2.3 Delivery & Receipt at site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Final Piping Special Items MTO | Complete Delivery to Site | HM-PI-70 | ML1549-D32 | FF | Not Started | Not Started | 199
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Final Electrical Bulk material MTO | Complete Delivery to Site | HM-EL-0530 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | 1st Electrical Bulk material MTO | Final Electrical Bulk material MTO | HM-EL-0520 | HM-EL-0530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Final Instrumentation Bulk material MTO | Complete Delivery to Site | HM-IC-0050 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Final Telecom Bulk material MTO | Complete Delivery to Site | HM-TL-0050 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Pigging & Split Tee (Lot 1) | Complete Delivery to Site | HM-PL-0840 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Isolating Joints (Lot 1) | Complete Delivery to Site | HM-PL-0740 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Pig Signaler (Lot 1) | Complete Delivery to Site | HM-PL-0530 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.24.2 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Hot Tapping Material | Complete Delivery to Site | HM-PL-0320 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.4.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Anchor Flanges (Lot 1) | Complete Delivery to Site | HM-PL-940 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.25.13.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Fire Fighting & Safety Equipment | Completion of Procurement Services | HP-ME-0980 | ML1038-C20 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.1.2.25.2.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Fire Suppression System | Completion of Procurement Services | HP-ME-0930 | ML1038-C20 | FF | Completed | Not Started | 80
P2543-R01-Oct24..1.1.2.25.3.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for HVAC Equipment | Completion of Procurement Services | HP-ME-0880 | ML1038-C20 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Completion of all Detailed Engineering | HE-IC-1430 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Completion of all Detailed Engineering | HE-TL-0530 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | Completion of all Detailed Engineering | HE-EL-0710 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.16 Datasheets for fire fighting and safety equipment | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Datasheets for fire fighting and safety equipment | Completion of all Detailed Engineering | HE-HS-0470 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-HSE Action Tracking Register (Hazards and Effects Register) | Completion of all Detailed Engineering | HE-HS-1070 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Telecom Typical Hookup | Completion of all Detailed Engineering | HE-TL-930 | ML1219-B29 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.2 Telecom MTO | P2543-R01-Oct24..ML.EN Detail Engineering | Telecom 3rd MTO | Completion of all Detailed Engineering | HE-TL-0890 | ML1219-B29 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc. | Completion of all Detailed Engineering | HE-TL-0590 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Completion of all Detailed Engineering | HE-IC-1550 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Data sheet for LV Distribution board | Completion of all Detailed Engineering | HE-EL-0650 | ML1219-B29 | FF | Completed | Not Started | 20
P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | P2543-R01-Oct24..ML.EN Detail Engineering | Instrument 3rd MTO | Completion of all Detailed Engineering | HE-IC-2630 | ML1219-B29 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.3 TBE for Field Instruments / H2S Analyzers | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-TBE for Field Instruments / H2S Analyzers | Completion of all Detailed Engineering | HE-IC-2450 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.5 TBE for ROV/ GOV | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-TBE for ROV/ GOV | Completion of all Detailed Engineering | HE-IC-2330 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Loop Diagrams | Completion of all Detailed Engineering | HE-IC-0770 | ML1219-B29 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.6 TBE for MOV | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-TBE for MOV | Completion of all Detailed Engineering | HE-IC-2090 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.16 Electrical MTO | P2543-R01-Oct24..ML.EN Detail Engineering | Electrical 3rd MTO | Completion of all Detailed Engineering | HE-EL-1850 | ML1219-B29 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Electrical Installation Drawings | Completion of all Detailed Engineering | HE-EL-1790 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Lighting Layout | Completion of all Detailed Engineering | HE-EL-1730 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Earthing Layout | Completion of all Detailed Engineering | HE-EL-1670 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Material Requisition for Distribution Transformer | Completion of all Detailed Engineering | HE-EL-1070 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Material Requisition for Active/ Passive Shelters | Completion of all Detailed Engineering | HE-EL-0890 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Completion of all Detailed Engineering | HE-EL-1010 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-UPS SLD | Completion of all Detailed Engineering | HE-EL-0290 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Electrical Adequacy Check Report | Completion of all Detailed Engineering | HE-EL-0170 | ML1219-B29 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Piping Isometrics | Completion of all Detailed Engineering | HE-PI-1240 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.2.17 TBE for Piping Bulks (Pipe, Flange, etc) | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-TBE for Piping Bulks (Pipe, Flange, etc) | Completion of all Detailed Engineering | HE-PI-1400 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.2.20 TBE for Piping Special Items | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-TBE for Piping Special Items | Completion of all Detailed Engineering | HE-PI-1450 | ML1219-B29 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Piping GA- 52" Pipeline SWEIHAN CRS | Completion of all Detailed Engineering | HE-PI-0700 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Piping GA- 56" Pipeline Launcher and metering Station (Habshan Complex) | Completion of all Detailed Engineering | HE-PI-0640 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | Completion of all Detailed Engineering | HE-PI-0880 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..ML.EN Detail Engineering | 90% Model Review Report | Completion of all Detailed Engineering | HE-PI-0180 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Piping Tie In Schedule | Completion of all Detailed Engineering | HE-PI-3520 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Completion of all Detailed Engineering | HE-PL-2910 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Completion of all Detailed Engineering | Receive at Site - Hot Bends for 52" Pipeline (100% to total Qty) | ML1219-B29 | ML1459-D12 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.5.3.3 TBE for Pig Launcher/Receiver | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-TBEs for Pig Launcher/Receiver | Completion of all Detailed Engineering | HE-ME-570 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.5.4 Addendum to DGS (Launche/Receiver) | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction- Addendum to DGS | Completion of all Detailed Engineering | HE-ME-610 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.44 Detailed crossing drawings-4" | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Detailed crossing drawings-4" | Completion of all Detailed Engineering | HE-PL-3150 | ML1219-B29 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.10.1 TBE for Anchor Flanges | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-TBE for Anchor Flanges | Completion of all Detailed Engineering | HE-PL-3520 | ML1219-B29 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.9.1 MR for Anchor Flanges | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-MR for Anchor Flanges | Completion of all Detailed Engineering | HE-PL-3450 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.60.14 Data Sheet - Anchor Flange | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Data Sheet - Anchor Flange | Completion of all Detailed Engineering | HE-PL-1550 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Data Sheet - Split Tee | Completion of all Detailed Engineering | HE-PL-1370 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.6 Pipeline Location Class selection Report | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | Completion of all Detailed Engineering | HE-PL-0830 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.17 Line List | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Line List | Completion of all Detailed Engineering | HE-PR-1130 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.10 Equipment List | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Equipment List | Completion of all Detailed Engineering | HE-PR-1070 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Relief, Vent and Blowdown philosophy | Completion of all Detailed Engineering | HE-PR-0830 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Tie-In Schedule | Completion of all Detailed Engineering | HE-PR-0290 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2.6 Project Risk Review Register | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Project Risk Review Register | Completion of all Detailed Engineering | HE-RR-0050 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2.1 Site Visit Report | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Site Visit Report | Completion of all Detailed Engineering | HE-SV-0050 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.1.BK.12 Modification of Existing Telecom System | P2543-R01-Oct24..1.1.BK.12 Modification of Existing Telecom System | RFQ, Receipt of Bid - Modification of Existing Telecom System | Prepare TBE and Company approval - Modification of Existing Telecom System | HS-GN-0310 | HS-GN-0340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | RFQ, Receipt of Bid - Modification of Exiting SMC / SCADA | Prepare TBE and Company approval - Modification of Exiting SMC / SCADA | HS-GN-0370 | HS-GN-0400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | RFQ, Receipt of Bid - Modification of Existing DCS | Prepare TBE and Company approval - Modification of Existing DCS | HS-GN-0430 | HS-GN-0460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.10 Modification of Existing CTMM | P2543-R01-Oct24..1.1.BK.10 Modification of Existing CTMM | RFQ, Receipt of Bid - Modification of Exiting CTMM | Prepare TBE and Company approval - Modification of Exiting CTMM | HS-GN-0250 | HS-GN-0280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.5 Hot Tapping | P2543-R01-Oct24..1.1.1.5 Hot Tapping | RFQ, Receipt of Bid for - Hot Tapping | + | HS-GN-0190 | HS-GN-0220 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Project Effective Date | Project Kick off Meeting | ML1001 | ML1002 | SS | Completed | Completed | 9
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Award / Project Start | Project Effective Date | ML1000 | ML1001 | SS | Completed | Completed | 7
P2543-R01-Oct24..1.1.BK.15.1 Ordering | P2543-R01-Oct24..1.1.BK.15.1 Ordering | Prepare TBE and Company approval for Earthing Material | Commercial Clarifications & Placement of PO for Earthing Material | HP-BK-0170 | HP-BK-0180 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.9.19 MR for Pipeline Pigging Tees | P2543-R01-Oct24..1.1.1.2.1 Ordering | Issue ICR - MR for Pigging Tees | RFQ, Receipt of Bid for Pigging & Split Tee | HE-PL-1810 | HP-ME-1270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.3.1 Ordering | P2543-R01-Oct24..1.1.1.3.1 Ordering | Prepare TBE and Company approval for Isolating Joints | Commercial Clarifications & Placement of PO for Isolating Joints | HP-ME-1230 | HP-ME-1240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.1.1 Ordering | P2543-R01-Oct24..1.1.BK.1.1 Ordering | RFQ, Receipt of Bid for Manual/Ball/ Globe/ Check/ Plug Valves | Prepare TBE and Company approval for Manual/ Ball/ Globe/ Check/ Plug Valves | HP-ME-1070 | HP-ME-1080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | P2543-R01-Oct24..1.1.2.25.1.1 Ordering | Issue ICR-Material Requisition for Distribution Transformer | RFQ, Receipt of Bid for Distribution Transformer | HE-EL-1030 | HP-ME-0460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.17.1 Ordering | P2543-R01-Oct24..1.1.2.LL.17.1 Ordering | Prepare TBE and Company approval for Leak Detection System | Commercial Clarifications & Placement of PO for Leak Detection System | HP-ME-0120 | HP-ME-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.22.1 Ordering | P2543-R01-Oct24..1.1.2.LL.22.1 Ordering | Prepare TBE and Company approval for Custody Metering Skid | Commercial Clarifications & Placement of PO for Custody Metering Skid | HP-ME-0020 | HP-ME-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.13.1 Ordering | P2543-R01-Oct24..1.1.2.25.13.1 Ordering | RFQ, Receipt of Bid for Fire Fighting & Safety Equipment | Prepare TBE and Company approval for Fire Fighting & Safety Equipment | HP-ME-0960 | HP-ME-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.16.1 Ordering | P2543-R01-Oct24..1.1.2.25.16.1 Ordering | Prepare TBE and Company approval for Junction Boxes | Commercial Clarifications & Placement of PO for Junction Boxes | HP-ME-0820 | HP-ME-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.18.1 Ordering | P2543-R01-Oct24..1.1.2.LL.18.1 Ordering | RFQ, Receipt of Bid for Gas Detectors | Prepare TBE and Company approval for Gas Detectors | HP-ME-0710 | HP-ME-0720 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.5.1 Ordering | P2543-R01-Oct24..1.1.2.LL.5.1 Ordering | RFQ, Receipt of Bid for Active/ Passive Cooled Shelter | Prepare TBE and Company approval for Active/ Passive Cooled Shelter | HP-ME-0560 | HP-ME-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.5.1 Ordering | P2543-R01-Oct24..1.1.2.LL.5.1 Ordering | Prepare TBE and Company approval for Active/ Passive Cooled Shelter | Commercial Clarifications & Placement of PO for Active/ Passive Cooled Shelter | HP-ME-0570 | HP-ME-0580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..1.2.12.14 Fence Works | Fence Works RFQ & Quotation Receipt | Fence Works Complete Evaluation (Internal) | HS-CN-0660 | HS-CN-0680 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | FOC Splicing / Termination RFQ & Quotation Receipt | FOC Splicing / Termination Complete Evaluation (Internal) | HS-CN-0260 | HS-CN-0280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | CP Drilling & Earthing Drilling Complete Evaluation (Internal) | CP Drilling & Earthing Drilling Subcontract Award | HS-CN-0230 | HS-CN-0240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | Testing & Precommissioning Complete Evaluation (Internal) | Testing & Precommissioning Subcontract Award | HS-CN-0130 | HS-CN-0140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | Issue ICR- Specification for RTU | RFQ, Receipt of Bid - Modification of Existing DCS | HE-IC-0190 | HS-GN-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | Obtain Company Approval - Passive cooled shelter foundation GA and details | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | HE-CS-1300 | HE-CS-1310 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | Re-Issue after incorporating HAZOP /Review Comments - 52" Pipeline SWEIHAN CRS | Issued for Review - Passive cooled shelter foundation GA and details | HE-PI-0420 | HE-CS-1270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | Re-Issue for Approval - Valve pit foundation GA and RC (type) details | Obtain Company Approval - Valve pit foundation GA and RC (type) details | HE-CS-1170 | HE-CS-1180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | Issue ICR - Geo Technical Survey Report (Overall) | Issued for Review - Gas metering skid foundation drawings | HE-GS-0010 | HE-CS-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | Final Issue for Design/ Construction-Design Calculation for Typical Skid Foundations | Final Issue for Design/ Construction - Pressure Reduction Skid and Leak Detection Drawings | HE-CS-0710 | HE-CS-0770 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | Issued for Review - Pressure Reduction Skid and Leak Detection Drawings | Review Company Comments - Pressure Reduction Skid and Leak Detection Drawings | HE-CS-0730 | HE-CS-0740 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | Issued for Review - Design Cal. for Typical Skid Foundations | Review Company Comments - Design Cal. for Typical Skid Foundations | HE-CS-0670 | HE-CS-0680 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | Issued for Review - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | Review Company Comments - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | HE-CS-0610 | HE-CS-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.8.28 Calculation for Pig launcher and receiver foundations | Issue ICR - Geo Technical Survey Report (Overall) | Issued for Review - Calculation for Pig launcher and receiver foundations | HE-GS-0010 | HE-CS-0550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.8.28 Calculation for Pig launcher and receiver foundations | Final Issue for Design/ Construction-Geotechnical Survey Report (Overall) | Final Issue for Design/ Construction-Calculation for Pig launcher and receiver foundations | HE-GS-0050 | HE-CS-0590 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..1.EN.8.11 Civil UG layout | Review Company Comments - Civil UG layout | Re-Issue for Approval - Civil UG layout | HE-CS-0500 | HE-CS-0510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | Issue ICR-Topographical Survey Report (Overall) | Issued for Review - Site grading, road, drainage and fence layout | HE-TS-0010 | HE-CS-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.17 Typical details of protection slab to protect existing UG pipe at road crossing | P2543-R01-Oct24..1.EN.8.17 Typical details of protection slab to protect existing UG pipe at road crossing | Issued for Review - Typical details of protection slab to protect existing UG pipe at road crossing | Review Company Comments - Typical details of protection slab to protect existing UG pipe at road crossing | HE-CS-0370 | HE-CS-0380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | Re-Issue for Approval - Typical Fence and gate detail drawing | Obtain Company Approval - Typical Fence and gate detail drawing | HE-CS-0330 | HE-CS-0340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | Review Company Comments - Typical Road and paving detail drawing | Re-Issue for Approval - Typical Road and paving detail drawing | HE-CS-0260 | HE-CS-0270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | Re-Issue for Approval - Typical duct bank detail drawing | Obtain Company Approval - Typical duct bank detail drawing | HE-CS-0210 | HE-CS-0220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | Review Company Comments - Typical duct bank detail drawing | Re-Issue for Approval - Typical duct bank detail drawing | HE-CS-0200 | HE-CS-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | Issued for Review - Typical trench detail drawing | Issued for Review - Typical duct bank detail drawing | HE-CS-0130 | HE-CS-0190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | Issued for Review - Typical trench detail drawing | Review Company Comments - Typical trench detail drawing | HE-CS-0130 | HE-CS-0140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction-Gas metering skid foundation drawings | Issued - Civil MTO 2 | HE-CS-0830 | HE-CS-1550 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Issued - Civil MTO 2 | HE-CS-0470 | HE-CS-1550 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction-Typical duct bank detail drawing | Issued - Civil MTO 2 | HE-CS-0230 | HE-CS-1550 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction-Typical trench detail drawing | Issued - Civil MTO 2 | HE-CS-0170 | HE-CS-1550 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..1.EN.8.41 Misc. supports | Obtain Company Approval - Misc. supports and civil/ structural details | Final Issue for Design/ Construction-Misc. supports | HE-CS-1480 | HE-CS-1490 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | Issued for Review - Pipe Sleeper layout and details. | Review Company Comments - Pipe Sleeper layout and details. | HE-CS-1390 | HE-CS-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | Final Issue for Design/ Construction-Piping Stress Analysis & Report | Final Issue for Design/ Construction-Pipe Sleeper layout and details | HE-PI-1180 | HE-CS-1430 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | Obtain Company Approval - Typical Structural Steel and Foundation details for pipe support | Final Issue for Design/ Construction-Typical Structural Steel and Foundation details for pipe support | HE-CS-1360 | HE-CS-1370 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | Review Company Comments - Typical Structural Steel and Foundation details for pipe support | Re-Issue for Approval - Typical Structural Steel and Foundation details for pipe support | HE-CS-1340 | HE-CS-1350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | Final Issue for Design/ Construction- Addendum to DGS | Final Issue for Design/ Construction-Datasheet for Sales Gas CRS Filters | HE-ME-0050 | HE-ME-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | Receive Company Comments-Datasheet for Sales Gas CRS Filters | Re-Issue for Approval-Datasheet for Sales Gas CRS Filters | HE-ME-0080 | HE-ME-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Re-Issue after incorporating HAZOP / Review Comments- Plot plan - BVS | Obtain Company Approval- Plot plan - BVS | HE-PI-0560 | HE-PI-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Re-Issue for HAZOP Studies- Plot plan - BVS | Re-Issue after incorporating HAZOP / Review Comments- Plot plan - BVS | HE-PI-0550 | HE-PI-0560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Re-Issue after incorporating HAZOP /Review Comments - 4" N2 Source Pipeline | Obtain Company Approval- Overall Plot Plan - 4" N2 Source Pipeline | HE-PI-0490 | HE-PI-0500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | Issue ICR- Overall Plot Plan - 4" N2 Source Pipeline | HE-PI-0390 | HE-PI-0460 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Re-Issue after incorporating HAZOP /Review Comments - 52" Pipeline SWEIHAN CRS | Obtain Company Approval- Overall Plot Plan - 52" Pipeline SWEIHAN CRS | HE-PI-0420 | HE-PI-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Final Issue for Design/ Construction-Vent and Depressurization Report (for new facilities) | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | HE-PR-1010 | HE-PI-0440 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Obtain Company Approval- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction-Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0360 | HE-PI-0370 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR-Topographical Survey Report (Overall) | Re-Issue after HAZOP /Review Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-TS-0010 | HE-PI-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.16 Critical line List | P2543-R01-Oct24..1.EN.7.16 Critical line List | Issue ICR-Critical line List | Receive Company Comments-Critical line List | HE-PI-0262 | HE-PI-0272 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | Issue ICR-Design Basis | Issue ICR-Piping Material Specifications | HE-DB-0010 | HE-PI-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | Obtain Company Approval-Piping Isometrics | Final Issue for Design/ Construction-Piping Isometrics | HE-PI-1230 | HE-PI-1240 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.2.6 TBE for Ball valves/ Plug Valves | P2543-R01-Oct24..1.EN.7.2.6 TBE for Ball valves/ Plug Valves | Obtain Company Approval- TBE for Ball valves/ Plug Valves | Final Issue for Design/ Construction-TBE for Ball valves/ Plug Valves | HE-PI-1110 | HE-PI-1120 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | Final Issue for Design/ Construction-Datasheet for Ball valves | Final Issue for Design/ Construction-Material Requisition for Ball/ Plug Valves | HE-PI-0940 | HE-PI-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | Re-Issue for Approval-MR for Ball valves/ Plug Valves | Obtain Company Approval-MR for Ball valves/ Plug Valves | HE-PI-1040 | HE-PI-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | Obtain Company Approval-Data sheet for Ball Valves | Final Issue for Design/ Construction-Datasheet for Ball valves | HE-PI-0930 | HE-PI-0940 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | Re-Issue for Approval-Data sheet for Ball Valves | Obtain Company Approval-Data sheet for Ball Valves | HE-PI-0920 | HE-PI-0930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | Issue ICR-Data sheet for Ball Valves | Receive Company Comments-Data sheet for Ball Valves | HE-PI-0900 | HE-PI-0910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | Issue ICR- Process Simulations Report | Issue ICR-Piping GA for 591-BVS-01 to 06 | HE-PR-0610 | HE-PI-0840 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | Re-Issue for HAZOP Studies- Plot plan - BVS | Issue ICR-Piping GA for 591-BVS-01 to 06 | HE-PI-0550 | HE-PI-0840 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | Final Issue for Design/ Construction-Piping Stress Analysis & Report | Final Issue for Design/ Construction-Piping GA for 4" N2 Source Pipeline | HE-PI-1180 | HE-PI-0760 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | Re-Issue after incorporating HAZOP /Review Comments - 52" Pipeline SWEIHAN CRS | Issue ICR-Piping GA for 52" Pipeline SWEIHAN CRS | HE-PI-0420 | HE-PI-0660 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | Receive Company Comments-Piping GA for 52" Pipeline SWEIHAN CRS | Re-Issue for Approval-Piping GA for 52" Pipeline SWEIHAN CRS | HE-PI-0670 | HE-PI-0680 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR-Piping GA-56" Pipeline Launcher and metering Station (Habshan Complex) | Receive Company Comments-56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0600 | HE-PI-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | Issue ICR-HAZID/ ENVID/ OHID Report | Issue ICR- HAZOP reviews Report for all areas | HE-HS-0550 | HE-HS-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | Final Issue for Design/ Construction-HAZID/ ENVID/ OHID Report | Final Issue for Design/ Construction-HAZOP Review Report | HE-HS-0590 | HE-HS-0710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | P2543-R01-Oct24..1.EN.4.19 HAZID/ ENVID/ OHID Close out Report | Final Issue for Design/ Construction-HAZID/ ENVID/ OHID Report | Issue ICR-HAZID/ ENVID/ OHID Close out Report | HE-HS-0590 | HE-HS-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.16 Datasheets for fire fighting and safety equipment | P2543-R01-Oct24..1.EN.4.16 Datasheets for fire fighting and safety equipment | Obtain Company Approval-Data Sheets for Fire Fighting & Safety Eqpt | Final Issue for Design/ Construction-Datasheets for fire fighting and safety equipment | HE-HS-0460 | HE-HS-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.16 Datasheets for fire fighting and safety equipment | P2543-R01-Oct24..1.EN.4.16 Datasheets for fire fighting and safety equipment | Issue ICR-Data Sheets for Fire Fighting & Safety Eqpt | Receive Company Comments-Data Sheets for Fire Fighting & Safety Eqpt | HE-HS-0430 | HE-HS-0440 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | Obtain Company Approval-Fire Fighting & Safety Eqpt. Layout | Final Issue for Design/ Construction-Fire fighting & Safety equipment layout | HE-HS-0400 | HE-HS-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.5 F&G layout | P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | Issue ICR-F&G Layout | Issue ICR-F&G Cause and Effect | HE-HS-0250 | HE-HS-0310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.5 F&G layout | P2543-R01-Oct24..1.EN.4.5 F&G layout | Obtain Company Approval-F&G Layout | Final Issue for Design/ Construction-F&G layout | HE-HS-0280 | HE-HS-0290 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.4.5 F&G layout | Final Issue for Design/ Construction-Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction-F&G layout | HE-PI-0370 | HE-HS-0290 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.4.5 F&G layout | Re-Issue after HAZOP /Review Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR-F&G Layout | HE-PI-0350 | HE-HS-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | Issue ICR-HAZOP Procedure | Receive Company Comments-HAZOP Procedure | HE-HS-0190 | HE-HS-0200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.4 Project HSE Plan | P2543-R01-Oct24..1.EN.4.4 Project HSE Plan | Issue ICR-HSE Plan | Receive Company Comments-HSE Plan | HE-HS-0010 | HE-HS-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.13.1 Ordering | P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | RFQ, Receipt of Bid for Fire Fighting & Safety Equipment | Issue ICR-TBE for Fire Fighting & Safety Eqpt | HP-ME-0960 | HE-HS-1150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.17 PHSER Close Out Report | P2543-R01-Oct24..1.EN.4.17 PHSER Close Out Report | Re-Issue for Approval- PHSER Close Out Report | Obtain Company Approval- PHSER Close Out Report | HE-HS-0930 | HE-HS-0940 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.17 PHSER Close Out Report | P2543-R01-Oct24..1.EN.4.17 PHSER Close Out Report | Receive Company Comments- PHSER Close Out Report | Re-Issue for Approval- PHSER Close Out Report | HE-HS-0920 | HE-HS-0930 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.12 PHSER Report | P2543-R01-Oct24..1.EN.4.12 PHSER Report | Obtain Company Approval-PHSER Report | Final Issue for Design/ Construction-PHSER Report | HE-HS-0880 | HE-HS-0890 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | Issue ICR-Telecom Equipment Layout | Receive Company Comments-Telecom Equipment Layout | HE-TL-0730 | HE-TL-0740 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | Issue ICR- FOC Block diagram (Telecom) | Issue ICR-Telecom Equipment Layout | HE-TL-0430 | HE-TL-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Receive Company Comments- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Re-Issue for Approval- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0500 | HE-TL-0510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Re-Issue for Approval- Overall Telecom Block Diagram | Obtain Company Approval- Overall Telecom Block Diagram | HE-TL-0330 | HE-TL-0340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..1.EN.10.2 Telecom MTO | Final Issue for Design/ Construction-Telecom cable schedule | Telecom 3rd MTO | HE-TL-0830 | HE-TL-0890 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..1.EN.10.2 Telecom MTO | Re-Issue for Approval- Telecom Cable Schedule | Telecom 2nd MTO | HE-TL-0810 | HE-TL-0870 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Final Issue for Design/ Construction-Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Final Issue for Design/ Construction-Telecom cable schedule | HE-TL-0110 | HE-TL-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Re-Issue for Approval- Telecom Cable Schedule | Obtain Company Approval- Telecom Cable Schedule | HE-TL-0810 | HE-TL-0820 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Re-Issue for Approval- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Re-Issue for Approval- Telecom Cable Schedule | HE-TL-0270 | HE-TL-0810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Issue ICR- Telecom Tie-in Block Diagram | Issue ICR- Telecom Cable Schedule | HE-TL-0370 | HE-TL-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.14.1 Ordering | P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | RFQ, Receipt of Bid for Access Switch, Fiber Optic Patch Panel and Media Converter | Issue ICR-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HP-ME-0660 | HE-TL-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Issue ICR- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0070 | HE-TL-0550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | HE-TL-0350 | HE-TL-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Re-Issue for Approval- FOC Block diagram (Telecom) | Obtain Company Approval- FOC Block diagram (Telecom) | HE-TL-0450 | HE-TL-0460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Receive Company Comments- FOC Block diagram (Telecom) | Re-Issue for Approval- FOC Block diagram (Telecom) | HE-TL-0440 | HE-TL-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Receive Company Comments- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Re-Issue for Approval- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-TL-0260 | HE-TL-0270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.43 Material Requisition for Pig Signaler | P2543-R01-Oct24..1.EN.6.11.43 Material Requisition for Pig Signaler | Issue ICR- Material Requisition for Pig Signaler | Receive Company Comments- Material Requisition for Pig Signaler | HE-PL-1930 | HE-PL-1940 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..1.EN.6.11.43 Material Requisition for Pig Signaler | Obtain Company Approval - Pipeline Alignment Sheets -56" | Issue ICR- Material Requisition for Pig Signaler | HE-PL-2420 | HE-PL-1930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.11 Data Sheet - Pipeline Isolating Joints | P2543-R01-Oct24..1.EN.1.9.20 MR for Isolating Joints | Re-Issue for Approval - Data Sheet - Isolating joints | Re-Issue for Approval - MR for Isolating Joints | HE-PL-1410 | HE-PL-1890 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.12 Data Sheet - Pipeline Pigging Tees | P2543-R01-Oct24..1.EN.1.9.19 MR for Pipeline Pigging Tees | Issue ICR - Data Sheet - Pigging Tees | Issue ICR - MR for Pigging Tees | HE-PL-1450 | HE-PL-1810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.19 MR for Pipeline Pigging Tees | P2543-R01-Oct24..1.EN.1.9.19 MR for Pipeline Pigging Tees | Re-Issue for Approval - MR for Pigging Tees | Obtain Company Approval - MR for Pigging Tees | HE-PL-1830 | HE-PL-1840 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.18 MR for Hot Induction Bends | P2543-R01-Oct24..1.EN.1.9.18 MR for Hot Induction Bends | Obtain Company Approval - MR for Hot Induction Bends | Final Issue for Design/ Construction-MR for Hot Induction Bends | HE-PL-1780 | HE-PL-1790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.21 Material Requisition for Manual Ball Valves | P2543-R01-Oct24..1.EN.6.11.21 Material Requisition for Manual Ball Valves | Obtain Company Approval - MR for Mainline Ball Valve | Final Issue for Design/ Construction-Material Requisition for Manual Ball Valves | HE-PL-1720 | HE-PL-1730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.51 Data Sheet - Mainline Ball Valve | P2543-R01-Oct24..1.EN.6.11.21 Material Requisition for Manual Ball Valves | Final Issue for Design/ Construction-Data Sheet - Mainline Ball Valve | Final Issue for Design/ Construction-Material Requisition for Manual Ball Valves | HE-PL-1250 | HE-PL-1730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | P2543-R01-Oct24..1.EN.1.60.14 Data Sheet - Anchor Flange | Final Issue for Design/ Construction-Pipeline Stress Analysis Report | Final Issue for Design/ Construction-Data Sheet - Anchor Flange | HE-PL-2850 | HE-PL-1550 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.60.14 Data Sheet - Anchor Flange | P2543-R01-Oct24..1.EN.1.60.14 Data Sheet - Anchor Flange | Receive Company Comments - Data Sheet - Anchor Flange (If Required) | Re-Issue for Approval - Data Sheet - Anchor Flange (If Required) | HE-PL-1520 | HE-PL-1530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.12 Data Sheet - Pipeline Pigging Tees | P2543-R01-Oct24..1.EN.1.60.12 Data Sheet - Pipeline Pigging Tees | Re-Issue for Approval - Data Sheet - Pigging Tees | Obtain Company Approval - Data Sheet - Pigging Tees | HE-PL-1470 | HE-PL-1480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | Issue ICR - Data Sheet - Split Tee | Receive Company Comments - Data Sheet - Split Tee | HE-PL-1330 | HE-PL-1340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.10 Data Sheet - Hot Induction Bends | P2543-R01-Oct24..1.EN.1.60.10 Data Sheet - Hot Induction Bends | Obtain Company Approval - Data Sheet - Hot Induction Bends | Final Issue for Design/ Construction-Data Sheet - Hot Induction Bends | HE-PL-1300 | HE-PL-1310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.10 Data Sheet - Hot Induction Bends | P2543-R01-Oct24..1.EN.1.60.10 Data Sheet - Hot Induction Bends | Receive Company Comments - Data Sheet - Hot Induction Bends | Re-Issue for Approval - Data Sheet - Hot Induction Bends | HE-PL-1280 | HE-PL-1290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.9 Data Sheet - Linepipes | P2543-R01-Oct24..1.EN.1.60.9 Data Sheet - Linepipes | Receive Company Comments - Data Sheet - Line pipes | Re-Issue for Approval - Data Sheet - Line pipes | HE-PL-1160 | HE-PL-1170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | P2543-R01-Oct24..1.EN.1.6 Pipeline Location Class selection Report | Final Issue for Design/ Construction-Overall Pipeline Route Map - 4" | Final Issue for Design/ Construction-Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | HE-PL-0290 | HE-PL-0830 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.6 Pipeline Location Class selection Report | P2543-R01-Oct24..1.EN.1.6 Pipeline Location Class selection Report | Obtain Company Approval - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | Final Issue for Design/ Construction-Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | HE-PL-0820 | HE-PL-0830 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.4 Pipeline Road and Railway Crossing Calculation Report | P2543-R01-Oct24..1.EN.1.4 Pipeline Road and Railway Crossing Calculation Report | Receive Company Comments - Pipeline Road Crossing Calculation Report | Re-Issue for Approval - Pipeline Road Crossing Calculation Report | HE-PL-0680 | HE-PL-0690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.4 Pipeline Road and Railway Crossing Calculation Report | P2543-R01-Oct24..1.EN.1.4 Pipeline Road and Railway Crossing Calculation Report | Issue ICR - Pipeline Road Crossing Calculation Report | Receive Company Comments - Pipeline Road Crossing Calculation Report | HE-PL-0670 | HE-PL-0680 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.40 Specification - Split Tee | P2543-R01-Oct24..1.EN.1.40 Specification - Split Tee | Issue ICR - Specification - Split Tee | Receive Company Comments - Specification - Split Tee | HE-PL-0430 | HE-PL-0440 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | Site Visit | Issue ICR - Overall Pipeline Route Map - 56" | HE-SS-0020 | HE-PL-0130 | FS | Completed | Completed | 20
P2543-R01-Oct24..1.EN.1.55 Crossing Schedule-4" | P2543-R01-Oct24..1.EN.1.55 Crossing Schedule-4" | Re-Issue for Approval - Crossing Schedule-4" | Obtain Company Approval - Crossing Schedule-4" | HE-PL-3190 | HE-PL-3200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.55 Crossing Schedule-4" | P2543-R01-Oct24..1.EN.1.55 Crossing Schedule-4" | Issue ICR - Crossing Schedule-4" | Receive Company Comments - Crossing Schedule-4" | HE-PL-3170 | HE-PL-3180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.44 Detailed crossing drawings-4" | P2543-R01-Oct24..1.EN.1.44 Detailed crossing drawings-4" | Issue ICR - Detailed crossing drawings-4" | Receive Company Comments - Detailed crossing drawings-4" | HE-PL-3110 | HE-PL-3120 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | Issue ICR - Pipeline Alignment Sheets-52" | Issue ICR - Detailed crossing drawings-52" | HE-PL-2450 | HE-PL-2990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | Obtain Company Approval - Detailed crossing drawings-52" | Final Issue for Design/ Construction-Detailed crossing drawings-52" | HE-PL-3020 | HE-PL-3030 | FF | In Progress | In Progress | 20
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | Re-Issue for Approval - Detailed crossing drawings-52" | Obtain Company Approval - Detailed crossing drawings-52" | HE-PL-3010 | HE-PL-3020 | FF | Completed | In Progress | 10
P2543-R01-Oct24..1.EN.1.4 Pipeline Road and Railway Crossing Calculation Report | P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | Final Issue for Design/ Construction-Pipeline Road and Railway Crossing Calculation Report | Final Issue for Design/ Construction-Pipeline Stress Analysis Report | HE-PL-0710 | HE-PL-2850 | FF | In Progress | In Progress | 5
P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | Receive Company Comments - Pipeline Stress Analysis Report | Re-Issue for Approval - Pipeline Stress Analysis Report | HE-PL-2820 | HE-PL-2830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.1 Pipeline Route Verification and Selection Report | Final Issue for Design/ Construction-Topographical Survey Report (Overall) | Final Issue for Design/ Construction-Pipeline Route Verification and Selection Report | HE-TS-0050 | HE-PL-2790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | Final Issue for Design/ Construction-Topographical Survey Report (Overall) | Final Issue for Design/ Construction-Pipeline Station approach drawing-52" | HE-TS-0050 | HE-PL-2670 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | Obtain Company Approval - Pipeline Station Approach drawing -56" | Final Issue for Design/ Construction-Pipeline Station approach drawing - 56" | HE-PL-2600 | HE-PL-2610 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | Receive Company Comments - Pipeline Station Approach drawing -56" | Re-Issue for Approval - Pipeline Station Approach drawing -56" | HE-PL-2580 | HE-PL-2590 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | Issue ICR - Pipeline Station Approach drawing -56" | HE-PI-0390 | HE-PL-2570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | Obtain Company Approval - Pipeline Alignment Sheets -56" | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | HE-PL-2420 | HE-PL-2430 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | Receive Company Comments - Pipeline Alignment Sheets -56" | Re-Issue for Approval - Pipeline Alignment Sheets -56" | HE-PL-2400 | HE-PL-2410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.54 TBE for Pig Signaler | P2543-R01-Oct24..1.EN.6.2.54 TBE for Pig Signaler | Obtain Company Approval- TBE for Pig Signaler | Final Issue for Design/ Construction-TBE for Pig Signaler | HE-PL-2360 | HE-PL-2370 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.10.24 TBE for Pigging Tees | P2543-R01-Oct24..1.EN.1.10.24 TBE for Pigging Tees | Obtain Company Approval - TBE for Pigging Tees | Final Issue for Design/ Construction-TBE for Pigging Tees | HE-PL-2180 | HE-PL-2190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.24 TBE for Pigging Tees | P2543-R01-Oct24..1.EN.1.10.24 TBE for Pigging Tees | Receive Company Comments - TBE for Pigging Tees | Re-Issue for Approval - TBE for Pigging Tees | HE-PL-2160 | HE-PL-2170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.24 TBE for Pigging Tees | P2543-R01-Oct24..1.EN.1.10.24 TBE for Pigging Tees | Re-Issue for Approval - TBE for Pigging Tees | Obtain Company Approval - TBE for Pigging Tees | HE-PL-2170 | HE-PL-2180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.23 TBE for Hot Induction Bends | P2543-R01-Oct24..1.EN.1.10.23 TBE for Hot Induction Bends | Obtain Company Approval - TBE for Hot Induction Bends | Final Issue for Design/ Construction-TBE for Hot Induction Bends | HE-PL-2120 | HE-PL-2130 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.2.8 TBE for Junction Boxes | P2543-R01-Oct24..1.EN.6.2.8 TBE for Junction Boxes | Obtain Company Approval- TBE for Junction Boxes | Final Issue for Design/ Construction-TBE for Junction Boxes | HE-IC-2500 | HE-IC-2510 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.3 TBE for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.EN.6.2.3 TBE for Field Instruments / H2S Analyzers | Receive Company Comments- TBE for Field Instruments / H2S Analyzers | Re-Issue for Approval- TBE for Field Instruments / H2S Analyzers | HE-IC-2420 | HE-IC-2430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.3 TBE for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.EN.6.2.3 TBE for Field Instruments / H2S Analyzers | Issue ICR- TBE for Field Instruments / H2S Analyzers | Receive Company Comments- TBE for Field Instruments / H2S Analyzers | HE-IC-2410 | HE-IC-2420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A2 Instrument Index | Issue ICR-Instrument index -Update | Receive Company Comments-Instrument index -Update | HE-IC-0490 | HE-IC-0500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | Re-Issue for Approval- Specification for RTU | Issue ICR- Power Consumption Calculation (Instrumentation) | HE-IC-0210 | HE-EL-5440 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | Obtain Company Approval- Material Requisitions for Field Instruments / H2S Analyzers | Final Issue for Design/ Construction-Material Requisitions for Field Instruments / H2S Analyzers | HE-IC-1960 | HE-IC-1970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | Obtain Company Approval- Addendum to DGs | Final Issue for Design/ Construction-Addendum to DGs | HE-IC-0040 | HE-IC-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.5 TBE for ROV/ GOV | P2543-R01-Oct24..1.EN.6.2.5 TBE for ROV/ GOV | Re-Issue for Approval- TBE for ROV/ GOV | Obtain Company Approval- TBE for ROV/ GOV | HE-IC-2310 | HE-IC-2320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.6 TBE for MOV | P2543-R01-Oct24..1.EN.6.2.6 TBE for MOV | Re-Issue for Approval- TBE for MOV | Obtain Company Approval- TBE for MOV | HE-IC-2070 | HE-IC-2080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | P2543-R01-Oct24..1.EN.6.11.A17 Material Requisitions for Metering Skid | Issue ICR- Datasheets for Metering Skid | Issue ICR- Material Requisitions for Metering Skid | HE-IC-1150 | HE-IC-1810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A131 Material Requisitions for ROV/ GOV | P2543-R01-Oct24..1.EN.6.11.A131 Material Requisitions for ROV/ GOV | Re-Issue for Approval- Material Requisitions for ROV/ GOV | Obtain Company Approval- Material Requisitions for ROV/ GOV | HE-IC-1650 | HE-IC-1660 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A1311 Material Requisitions for MOV | P2543-R01-Oct24..1.EN.6.11.A1311 Material Requisitions for MOV | Re-Issue for Approval- Material Requisitions for MOV | Obtain Company Approval- Material Requisitions for MOV | HE-IC-1590 | HE-IC-1600 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | P2543-R01-Oct24..1.EN.6.11.A1311 Material Requisitions for MOV | Re-Issue for Approval- Datasheet for MOV | Re-Issue for Approval- Material Requisitions for MOV | HE-IC-1050 | HE-IC-1590 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | P2543-R01-Oct24..1.EN.6.11.A1311 Material Requisitions for MOV | Issue ICR- Datasheet for MOV | Issue ICR- Material Requisitions for MOV | HE-IC-1030 | HE-IC-1570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | Issue ICR- Addendum to DGs | Issue ICR-Datasheets for Field Instruments / H2S Analyzers | HE-IC-0010 | HE-IC-1450 | SS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | Issue ICR- P&ID's | Issue ICR- Datasheets for PSV & Orifice (incl. RO) | HE-PR-0110 | HE-IC-1330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Issue ICR- Specifications for PRS (Pressure Reduction System) | Issue ICR- Data sheet for PRS (Pressure Reduction System) | HE-IC-0070 | HE-IC-1210 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | Issue ICR- Specification for RTU | Issue ICR- Instrument Cable Block Diagram | HE-IC-0190 | HE-IC-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | Final Issue for Design/ Construction-Datasheets for Field Instruments / H2S Analyzers | Final Issue for Design/ Construction-Hook-Up Diagram | HE-IC-1490 | HE-IC-0650 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | Re-Issue for Approval-Tie-In Schedule | Obtain Company Approval-Tie-In Schedule | HE-PR-0270 | HE-PR-0280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.17 Line List | P2543-R01-Oct24..1.EN.3.17 Line List | Issue ICR- Line List | Receive Company Comments- Line List | HE-PR-1090 | HE-PR-1100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | P2543-R01-Oct24..1.EN.3.10 Equipment List | Final Issue for Design/ Construction-Process Datasheets | Final Issue for Design/ Construction-Equipment List | HE-PR-0590 | HE-PR-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.3.10 Equipment List | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | Obtain Company Approval - Equipment List | ML1012-B06 | HE-PR-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | Issue ICR- Operating and control philosophy, Safeguarding philosophy | Issue ICR - Pre-commissioning and commissioning philosophy | HE-PR-0730 | HE-PR-0910 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | Receive Company Comments-Isolation & Tie-In philosophy | Re-Issue for Approval-Isolation & Tie-In philosophy | HE-PR-0860 | HE-PR-0870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | Issue ICR - Relief, Vent and Blowdown Philosophy | Receive Company Comments - Relief, Vent and Blowdown Philosophy | HE-PR-0790 | HE-PR-0800 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | Obtain Company Approval- Process Datasheets - PRS Skid (at Sweihan CRS) | Final Issue for Design/ Construction-Process Datasheets - PRS Skid (at Sweihan CRS) | HE-PR-0400 | HE-PR-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | Re-Issue for Approval- Process Datasheets - PRS Skid (at Sweihan CRS) | Obtain Company Approval- Process Datasheets - PRS Skid (at Sweihan CRS) | HE-PR-0390 | HE-PR-0400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | Receive Company Comments- Process Datasheets - PRS Skid (at Sweihan CRS) | Re-Issue for Approval- Process Datasheets - PRS Skid (at Sweihan CRS) | HE-PR-0380 | HE-PR-0390 | FS | Completed | Completed | 20
P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | Receive Company Comments- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | Re-Issue for Approval- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | HE-PR-0320 | HE-PR-0330 | FS | Completed | Completed | 20
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Receive Company Comments-P&ID's | Re-Issue for HAZOP Studies- P&ID's review | HE-PR-0120 | HE-PR-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Final Issue for Design/ Construction-Process Flow Diagrams ( New + Existing) | Final Issue for Design / Construction-P&ID's | HE-PR-0090 | HE-PR-0160 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | Re-Issue for Approval- Process Simulations Report | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | HE-PR-0630 | HE-PR-0070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.4 Constructability Review/ SIMOPS Report | P2543-R01-Oct24..1.EN.2.4 Constructability Review/ SIMOPS Report | Re-Issue for Approval-Constructability Review / SIMOPS Report | Obtain Company Approval-Constructability Review / SIMOPS Report | HE-ST-0030 | HE-ST-0040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | Re-Issue for Approval - Geo Technical Survey Report (Overall) | Obtain Company Approval - Geo Technical Survey Report (Overall) | HE-GS-0030 | HE-GS-0040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.3 Project Procedure (PEP, Numbering Procedure) | P2543-R01-Oct24..1.PM.12 Workshops | Final Issue for Design/ Construction-Project Procedure (PEP, Numbering Procedure) | Design Review Workshop | HC-GN-0110 | HE-WS-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.9 HSE Studies | P2543-R01-Oct24..1.PM.12 Workshops | Place LOA/FOA - HSE Studies | Constructability Review Workshop | HS-GN-0110 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.30 TBE for Distibution Transformers | P2543-R01-Oct24..1.EN.9.6.30 TBE for Distibution Transformers | Re-Issue for Approval-TBE for Distribution Transformer | Obtain Company Approval-TBE for Distribution Transformer | HE-EL-1470 | HE-EL-1480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..1.EN.9.4 Solar Panel Sizing | Issue ICR-Solar Panel System SLDs | Issue ICR-Solar Panel Sizing calculation | HE-EL-0310 | HE-EL-0370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | Issue ICR-Solar Panel System SLDs | Receive Company Comments-Solar Panel System SLDs | HE-EL-0310 | HE-EL-0320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | Issue ICR-Single Line Diagrams for LV Switchgear | Receive Company Comments-Single Line Diagrams for LV Switchgear | HE-EL-0190 | HE-EL-0200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | Final Issue for Design/ Construction-Load List | Final Issue for Design/ Construction-Single Line Diagrams for LV Distribution Board | HE-EL-0110 | HE-EL-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | Obtain Company Approval-Update /New Load List | Final Issue for Design/ Construction-Load List | HE-EL-0100 | HE-EL-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | Issue ICR-Update /New Load List | Receive Company Comments-Update /New Load List | HE-EL-0070 | HE-EL-0080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..1.EN.9.16 Electrical MTO | Final Issue for Design/ Construction-Cable Routing Layout | Electrical 3rd MTO | HE-EL-1610 | HE-EL-1850 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..1.EN.9.16 Electrical MTO | Final Issue for Design/ Construction-Cable Schedule | Electrical 3rd MTO | HE-EL-0590 | HE-EL-1850 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | Issue ICR- Electrical Installation Drawings | Receive Company Comments- Electrical Installation Drawings | HE-EL-1750 | HE-EL-1760 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..1.EN.9.13 Lighting Layout | Issue ICR- Electrical Equipment Layout | Issue ICR-Lighting Layout | HE-EL-0490 | HE-EL-1690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.28 TBE for Distribution Boards | P2543-R01-Oct24..1.EN.9.6.28 TBE for Distribution Boards | Receive Company Comments-TBE for Distribution Boards | Re-Issue for Approval-TBE for Distribution Boards | HE-EL-1400 | HE-EL-1410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.29 TBE for Active/ Passive Shelters | P2543-R01-Oct24..1.EN.6.2.29 TBE for Active/ Passive Shelters | Receive Company Comments - TBE for Active / Passive Shelters | Re-Issue for Approval - TBE for Active / Passive Shelters | HE-EL-1220 | HE-EL-1230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | Receive Company Comments-Material Requisition for Power & Control Cables | Re-Issue for Approval-Material Requisition for Power & Control Cables | HE-EL-1160 | HE-EL-1170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | Issue ICR-Material Requisition for Solar Panels | Receive Company Comments-Material Requisition for Solar Panels | HE-EL-1090 | HE-EL-1100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | Re-Issue for Approval-Data sheet for LV Distribution board | Re-Issue for Approval-Material Requisition for Distribution Boards | HE-EL-0630 | HE-EL-0990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..1.EN.9.10 Cable Schedule | Issue ICR-Cable Schedule | Receive Company Comments-Cable Schedule | HE-EL-0550 | HE-EL-0560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | Re-Issue for Approval- Electrical Equipment Layout | Obtain Company Approval- Electrical Equipment Layout | HE-EL-0510 | HE-EL-0520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | Issue ICR-Design Basis | Issue ICR - Material Selection Diagram | HE-DB-0010 | HE-CP-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.4 NOC Register | P2543-R01-Oct24..1.PM.4 NOC Register | Obtain Company Approval-NOC Register | Final Issue for Design/ Construction-NOC Register | HC-GN-0280 | HC-GN-0290 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.PM.4 NOC Register | P2543-R01-Oct24..1.PM.4 NOC Register | Issue ICR-NOC Register | Receive Company Comments-NOC Register | HC-GN-0250 | HC-GN-0260 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.PM.4 NOC Register | Issue ICR- Plot plan - BVS | Issue ICR-NOC Register | HE-PI-0530 | HC-GN-0250 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.6 Quality documents | P2543-R01-Oct24..1.PM.6 Quality documents | Issue ICR-QAQC procedure | Receive Company Comments-QAQC procedure | HC-GN-0190 | HC-GN-0200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.6 Quality documents | P2543-R01-Oct24..1.PM.6 Quality documents | Obtain Company Approval-QAQC procedure | Final Issue for Design/ Construction-Quality documents | HC-GN-0220 | HC-GN-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.2 Planning Package | P2543-R01-Oct24..1.PM.6 Quality documents | Issue ICR-Planning Package | Issue ICR-QAQC procedure | HC-GN-0010 | HC-GN-0190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.3 Project Procedure (PEP, Numbering Procedure) | P2543-R01-Oct24..1.PM.3 Project Procedure (PEP, Numbering Procedure) | Obtain Company Approval-Project Procedure (PEP, Numbering Procedure etc.) | Final Issue for Design/ Construction-Project Procedure (PEP, Numbering Procedure) | HC-GN-0100 | HC-GN-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.3 Project Procedure (PEP, Numbering Procedure) | P2543-R01-Oct24..1.PM.3 Project Procedure (PEP, Numbering Procedure) | Receive Company Comments-Project Procedure (PEP, Numbering Procedure etc.) | Re-Issue for Approval-Project Procedure (PEP, Numbering Procedure etc.) | HC-GN-0080 | HC-GN-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.17.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.17.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Leak Detection System | Receipt at site and inspection of Leak Detection System | HM-ME-0270 | HM-ME-0280 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.16.2 Manufacturing & Ready for Dispatch | Testing and Inspection of Junction Boxes | Packaging & Final Inspection-Junction Boxes | HM-ME-1640 | HM-ME-1650 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.13.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Fire Fighting & Safety Equipment | Manufacturing & Assembly of Fire Fighting & Safety Equipment | HM-ME-1920 | HM-ME-1930 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.19.1 Ordering | P2543-R01-Oct24..PR.26.LL.19.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for FOC Cables | Vendor Document Review of FOC Cables | HP-BK-0080 | HM-EL-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..PR.26.1.14.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc. | Manufacturing & Assembly of Access Switch, Fiber Optic Patch Panel and Media Converter | HE-TL-0590 | HM-ME-1330 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..PR.26.1.14.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.14.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Access Switch, Fiber Optic Patch Panel and Media Converter | Manufacturing & Assembly of Access Switch, Fiber Optic Patch Panel and Media Converter | HM-ME-1320 | HM-ME-1330 | FF | Completed | In Progress | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.1.14.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - Fiber Optic Cable | Vendor Document Review of Access Switch, Fiber Optic Patch Panel and Media Converter | ML1329-C17 | HM-ME-1320 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.4.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.4.2 Manufacturing & Ready for Dispatch | Testing and Inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Packaging & Final Inspection-Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | HM-ME-1240 | HM-ME-1250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.5.1 Ordering | P2543-R01-Oct24..PR.26.LL.5.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Active/ Passive Cooled Shelter | Vendor Document Review of Active/ Passive Cooled Shelter | HP-ME-0580 | HM-ME-1120 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.6.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.6.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Solar PV system | Receipt at site and inspection of Solar PV system | HM-ME-1080 | HM-ME-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.6.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.6.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Solar PV system | Factory Acceptance Test of Solar PV system | HM-ME-1030 | HM-ME-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.6.1 Ordering | P2543-R01-Oct24..PR.26.LL.6.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Solar PV system | Vendor Document Review of Solar PV system | HP-ME-0530 | HM-ME-1020 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.1.7.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | Ready for Dispatch of Power Distribution Boards | Transportation/ Custom Clearance/ Delivery at site of Power Distribution Boards | HM-ME-0860 | HM-ME-0880 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Power Distribution Boards | Receipt at site and inspection of Power Distribution Boards | HM-ME-0880 | HM-ME-0890 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.7.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection for Power Distribution Boards | Ready for Dispatch of Power Distribution Boards | HM-ME-0850 | HM-ME-0860 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.8.1 Ordering | P2543-R01-Oct24..PR.26.LL.8.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for AC UPS | Ready for Dispatch of AC UPS | HP-ME-0380 | HM-ME-0760 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | Ready for Dispatch of Pig Launchers & Receivers | Transportation/ Custom Clearance/ Delivery at site of Pig Launchers & Receivers (52" Line) | HM-ME-0450 | HM-ME-0470 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Pig Launchers & Receivers | Testing and Inspection of Pig Launchers & Receivers | HM-ME-0420 | HM-ME-0430 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.1.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.3.2 Manufacturing & Ready for Dispatch | Vendor Document Review of HVAC Equipment | Manufacturing & Assembly of HVAC Equipment | HM-ME-1720 | HM-ME-1730 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.1.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.3.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-HVAC Equipment | Ready for Dispatch of HVAC Equipment | HM-ME-1750 | HM-ME-1760 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.3.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of HVAC Equipment | Factory Acceptance Test of HVAC Equipment | HM-ME-1730 | HM-ME-1740 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.1.2.25.2.1 Ordering | P2543-R01-Oct24..PR.26.1.2.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Fire Suppression System | Ready for Dispatch of Fire Suppression System | HP-ME-0930 | HM-ME-1890 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.2.25.2.1 Ordering | P2543-R01-Oct24..PR.26.1.2.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Fire Suppression System | Vendor Document Review of Fire Suppression System | HP-ME-0930 | HM-ME-1850 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.1.2.LL.21.1 Ordering | P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Pressure Reduction Skid | Ready for Dispatch of Pressure Reduction Skid | HP-ME-0080 | HM-ME-0150 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Pressure Reduction Skid | Manufacturing & Assembly of Pressure Reduction Skid | HM-ME-0110 | HM-ME-0120 | SS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Pressure Reduction Skid | HE-PR-0590 | HM-ME-0120 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Filter Package | Testing and Inspection of Filter Package | HM-ME-0320 | HM-ME-0330 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.15.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.15.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of Earthing Material | Packaging & Final Inspection-Earthing Material | HM-EL-0330 | HM-EL-0340 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | 1st Instrumentation Bulk material MTO | 1st Instrumentation Bulk material MTO | HM-IC-0010 | HM-IC-0040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | Final Instrumentation Bulk material MTO | Final Instrumentation Bulk material MTO | HM-IC-0020 | HM-IC-0050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.6.1 Ordering | P2543-R01-Oct24..PR.BK.6.2 Manufacturing & Ready for Dispatch | Final Pipeline Bulk material MTO | Final Pipeline Bulk material MTO | HP-BK-0390 | HM-PL-0860 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.13.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.13.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of Cable Trays | Packaging & Final Inspection-Cable Trays | HM-EL-0230 | HM-EL-0240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Power & Control Cables (Lot 1) | Receipt at site and inspection of Power & Control Cables (Lot 1) | HM-EL-0070 | HM-EL-0080 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..PR.BK.16.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.16.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-MCT | Ready for Dispatch of MCT | HM-EL-0440 | HM-EL-0450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.16.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.16.2 Manufacturing & Ready for Dispatch | Vendor Document Review of MCT | Manufacturing & Assembly of MCT | HM-EL-0410 | HM-EL-0420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.1.16.1 Ordering | P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | Commercial Clarifications & Placement of PO for Line Pipes (Coated) | Ready for Dispatch of Line Pipes (Coated) - Lot 1 | HP-ME-1040 | HM-PL-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | Vendor Document Review of Line Pipes - Lot 1 | Manufacturing & Receive Plates at Fabrication Shop - Lot 1 | HM-PL-0010 | HM-PL-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.2.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.2.2 Manufacturing & Ready for Dispatch | Testing and Inspection of Pigging & Split Tee | Packaging & Final Inspection-Pigging & Split Tee | HM-PL-0790 | HM-PL-0800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.1.2 Manufacturing & Ready for Dispatch | Testing and Inspection of Hot Incution Bend | Packaging & Final Inspection-Hot Incution Bend | HM-PL-0580 | HM-PL-0590 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..PR.1.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.1.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Hot Incution Bend | Manufacturing & Assembly of Hot Incution Bend | HM-PL-0560 | HM-PL-0570 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.1.1.1.1 Ordering | P2543-R01-Oct24..PR.1.1.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Hot Induction Bend | Vendor Document Review of Hot Incution Bend | HP-ME-1190 | HM-PL-0560 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.1.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Hot Incution Bend | Ready for Dispatch of Hot Incution Bend | HM-PL-0590 | HM-PL-0600 | FF | Not Started | Not Started | 14
P2543-R01-Oct24..PR.1.19.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.19.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Pig Signaler | Manufacturing & Assembly of Pig Signaler | HM-PL-0460 | HM-PL-0470 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.1.19.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.19.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Pig Singler | Ready for Dispatch of Pig Signaler | HM-PL-0490 | HM-PL-0500 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | Ready for Dispatch of CP System | Transportation/ Custom Clearance/ Delivery at site of CP System | HM-PL-0390 | HM-PL-0420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.24.2 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.24.2 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Hot Tapping Material | Receipt at site and inspection of Hot Tapping Material | HM-PL-0310 | HM-PL-0320 | FS | Not Started | Not Started | 60
P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Ball/ Globe/ Check/ Plug Valves | Testing and Inspection of Ball/ Globe/ Check/ Plug Valves | HM-PL-0160 | HM-PL-0170 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - Anchor Flanges | Vendor Document Review of Ball/ Globe/ Check/ Plug Valves | ML1249-C06 | HM-PL-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.1.1 Ordering | P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Manual/ Ball/ Globe/ Check/ Plug Valves | Ready for Dispatch of Ball/ Globe/ Check/ Plug Valves | HP-ME-1090 | HM-PL-0190 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.8.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of AC UPS | Receive at Site - UPS System | HM-ME-0790 | ML1499-D18 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | Receive at Site - E&I Equipment's (IDS & PIDS System) | HM-ME-1390 | ML1479-D15 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Receive at Site - Hot Bends for 52" Pipeline (50% to total Qty) | HM-PL-0630 | ML1449-D11 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.19.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for FOC Cables | Issue Purchase Order (Final) - Fiber Optic Cable | HP-BK-0080 | ML1329-C17 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.5.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Active/ Passive Cooled Shelter | Issue Purchase Order (Final) - Passive Cooling Shelters | HP-ME-0580 | ML1309-C15 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.15.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Field Instruments | Issue Purchase Order (Final) - F & G System | HP-ME-0780 | ML1269-C12 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-0350 | ML1035-B26 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-TYPICAL GA AND RC DETAILS OF IMPACT WALL | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-1250 | ML1035-B26 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical trench detail drawing | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-0170 | ML1034-B25 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Standard drawings for Anchor bolt | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-0110 | ML1034-B25 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-0470 | ML1034-B25 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | HE-TL-0110 | ML1033-B22 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | HE-TL-0710 | ML1032-B21 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.11.A131 Material Requisitions for ROV/ GOV | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Material Requisitions for ROV/ GOV | Issue MRs for All E&I Equipment & Packages (Final Issue) | HE-IC-1670 | ML1027-B17 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Material Requisition for Distribution Transformer | Issue MRs for All E&I Equipment & Packages (Final Issue) | HE-EL-1070 | ML1027-B17 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Process Flow Diagrams ( New + Existing) | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | HE-PR-0090 | ML1014-B10 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.12 PHSER Report | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue for Approval-PHSER Report | Complete HAZOP/ SIL/ LOPA Review as applicable and Submit final Report after incorporating Company comments (IFA) | HE-HS-0870 | ML1013-B07 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue for HAZOP Studies- P&ID's review | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | HE-PR-0130 | ML1012-B06 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Piping GA for 4" N2 Source Pipeline | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-PI-0760 | ML1219-B19 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical trench detail drawing | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-0170 | ML1209-B27 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-TYPICAL LIGHTING POLE FOUNDATION DETAILS | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-1010 | ML1209-B27 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | HE-PI-0440 | ML1179-B11 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..ML.EN Detail Engineering | 60% Model Review | 60% Model Review | HE-PI-0150 | ML2069-B09 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | P2543-R01-Oct24..ML.GE General | Final Issue for Design/ Construction-Overall Pipeline Route Map - 4" | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (4" Water line) | HE-PL-0290 | ML1169-A09 | FF | Completed | Completed | 40
P2543-R01-Oct24..1.PM.3 Project Procedure (PEP, Numbering Procedure) | P2543-R01-Oct24..ML.GE General | Final Issue for Design/ Construction-Project Procedure (PEP, Numbering Procedure) | Issue Project Execution Plan (PEP), Coordination, Engineering, Procurement, HSE and Quality Procedures-Final Issue | HC-GN-0110 | ML1001-A01 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.4 Commissioning and PAC | P2543-R01-Oct24..ML Milestones | Commission New pipelines system - 4" Nitrogen Pipeline | Achieve PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | ML2019-F03 | ML1040 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..ML Milestones | Civil & Structural | Project Finish | CAB-4420 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.2 Final Documentation | P2543-R01-Oct24..ML Milestones | General | Project Finish | CAB-5290 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..ML Milestones | Instrumentation & Control | Project Finish | CAB-4460 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..ML Milestones | Mechanical | Project Finish | CAB-4430 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..ML Milestones | Piping | Project Finish | CAB-4440 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 04 to BVS-05 | Project Finish | ML1799-E25 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Receive at Site - E&I Equipment's (CCTV System) | Project Finish | ML1056-D14 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..ML Milestones | Telecom | Project Finish | CAB-4470 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Receive at Site - Hot Bends for 52" Pipeline (100% to total Qty) | Project Finish | ML1459-D12 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Receive at Site - Passive Cooling Shelter | Project Finish | ML1054-D09 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..ML Milestones | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | Achieve PAC-2 for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | CCM-PM4520 | ML1050 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Piping | Close-out report | CAB-4440 | CAB-5320 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | HSE | General | CAB-4410 | CAB-5290 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Piping | General | CAB-4440 | CAB-5290 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | General | C-COM-840 | CAB-5290 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Civil & Structural | General | CAB-4420 | CAB-5290 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..PR.26.LL.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of Leak Detection System | Vendor Documents Package | HM-ME-0280 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Vendor Documents Package | HM-PL-0220 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Mechanical | Vendor Documents Package | CAB-4430 | CAB-5310 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Process | Vendor Documents Package | CAB-4400 | CAB-5310 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Mechanical | Quality Dossier | CAB-4430 | CAB-5300 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline Station approach drawing-52" | Pipeline | HE-PL-2670 | CAB-4480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.15 Pipeline Station approach drawing - 4" Nitrogen | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline Station approach drawing-4" | Pipeline | HE-PL-2730 | CAB-4480 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.1 Pipeline Route Verification and Selection Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline Route Verification and Selection Report | Pipeline | HE-PL-2790 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Overall Pipeline Route Map - 4" | Pipeline | HE-PL-0290 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.2 Telecom MTO | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Telecom 3rd MTO | Telecom | HE-TL-0890 | CAB-4470 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Telecom | HE-TL-0410 | CAB-4470 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Instrumentation & Control | ML1014-B10 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.A30 TBE for Metering Skid | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Metering Skid | Instrumentation & Control | HE-IC-2150 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Instrumentation & Control | HE-IC-0830 | CAB-4460 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.11.9 Material Requisitions for Fire & Gas Detectors | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisitions for Gas Detectors | Instrumentation & Control | HE-IC-1910 | CAB-4460 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.A331 TBE for Leak Detection System | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Leak Detection System | Instrumentation & Control | HE-IC-2270 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-I/O list | Instrumentation & Control | HE-IC-0590 | CAB-4460 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Instrument Index | Instrumentation & Control | HE-IC-0530 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.11.A17 Material Requisitions for Metering Skid | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisitions for Metering Skid | Instrumentation & Control | HE-IC-1850 | CAB-4460 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Instrumentation & Control | ML1032-B21 | CAB-4460 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Data Sheet for LV cables | Electrical | HE-EL-0830 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Load List | Electrical | HE-EL-0110 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.27 TBE for UPS System | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for UPS System | Electrical | HE-EL-1370 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | Electrical | HE-EL-0710 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Piping MTO - Final | Piping | HE-PI-1300 | CAB-4440 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Piping GA- 52" Pipeline SWEIHAN CRS | Piping | HE-PI-0700 | CAB-4440 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Mechanical | ML1179-B11 | CAB-4430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Datasheet for Sales Gas CRS Filters | Mechanical | HE-ME-0110 | CAB-4430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisitions for Sales Gas CRS Filters | Mechanical | HE-ME-0170 | CAB-4430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TYPICAL LIGHTING POLE FOUNDATION DETAILS | Civil & Structural | HE-CS-1010 | CAB-4420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Civil UG layout | Civil & Structural | HE-CS-0530 | CAB-4420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue SLD, Hazardous Area Classification Details for All Areas - IFC | HSE | ML1031-B20 | CAB-4410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Issue MRs for All E&I Equipment & Packages (Final Issue) | Issue ICR-Pre-commissioning and Commissioning Plan | ML1027-B17 | C-COM-800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | Receive Company Comments-Shutdown Requirements & Plan | Re-Issue for Approval-Shutdown Requirements & Plan | C-COM-860 | C-COM-870 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Issue ICR-Shutdown Requirements & Plan | CTF-1000 | C-COM-850 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Issue MRs for All Mechanical Equipment & Packages (Final Issue) | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | ML1017-B18 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Issue ICR- Addendum to DGs | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-IC-0010 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Commercial Clarifications & Placement of PO - Modification of Exiting SMC / SCADA | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HS-GN-0410 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Issue ICR- Addendum to DGs | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-IC-0010 | C-COM-790 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Civil UG layout | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-CS-0530 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Issue ICR-Construction Procedures / Method Statements / ITPs | HE-CS-0350 | C-COM-750 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Issue ICR-Construction Procedures / Method Statements / ITPs | CTF-1000 | C-COM-750 | SS | Completed | Not Started | 6
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Issue MR (Final) - Line pipes | Issue ICR-Construction Procedures / Method Statements / ITPs | ML1021-B15 | C-COM-750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Project Kick off Meeting | Main Office | ML1002 | CTF-SO1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | P2543-R01-Oct24..1.1.BK.6.1 Ordering | Final Issue for Design/ Construction-Pipeline MTO - 56" and 52" | Final Pipeline Bulk material MTO | HE-PL-3270 | HP-BK-0390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.42 Civil MTO | P2543-R01-Oct24..1.1.BK.5.1 Ordering | Issued - Civil MTO 1 | 1st Structural Bulk material MTO | HE-CS-1510 | HP-BK-0300 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.9.20 MR for Isolating Joints | P2543-R01-Oct24..1.1.1.3.1 Ordering | Issue ICR - MR for Isolating Joints | RFQ, Receipt of Bid for Isolating Joints | HE-PL-1870 | HP-ME-1220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.18 MR for Hot Induction Bends | P2543-R01-Oct24..1.1.1.1.1 Ordering | Issue ICR - MR for Hot Induction Bends | RFQ, Receipt of Bid for Hot Incution Bend | HE-PL-1750 | HP-ME-1170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.1.1 Ordering | P2543-R01-Oct24..1.1.1.1.1 Ordering | RFQ, Receipt of Bid for Hot Incution Bend | Prepare TBE and Company approval for Hot Incution Bend | HP-ME-1170 | HP-ME-1180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.17 MR for Linepipes | P2543-R01-Oct24..1.1.1.16.1 Ordering | Final Issue for Design/ Construction-MR for Line pipes | Commercial Clarifications & Placement of PO for Line Pipes (Coated) | HE-PL-1670 | HP-ME-1040 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.22 TBE for Linepipes | P2543-R01-Oct24..1.1.1.16.1 Ordering | Final Issue for Design/ Construction-TBE for Line pipes | Commercial Clarifications & Placement of PO for Line Pipes (Coated) | HE-PL-2070 | HP-ME-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.1.1 Ordering | P2543-R01-Oct24..1.1.2.25.1.1 Ordering | RFQ, Receipt of Bid for Distribution Transformer | Prepare TBE and Company approval for Distribution Transformer | HP-ME-0460 | HP-ME-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.8.1 Ordering | P2543-R01-Oct24..1.1.2.LL.8.1 Ordering | RFQ, Receipt of Bid for AC UPS | Prepare TBE and Company approval for AC UPS | HP-ME-0360 | HP-ME-0370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | P2543-R01-Oct24..1.1.2.LL.17.1 Ordering | Issue ICR-Material Requisitions for Leak Detection System | RFQ, Receipt of Bid for Leak Detection System | HE-IC-1750 | HP-ME-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A17 Material Requisitions for Metering Skid | P2543-R01-Oct24..1.1.2.LL.22.1 Ordering | Issue ICR- Material Requisitions for Metering Skid | RFQ, Receipt of Bid for Custody Metering Skid | HE-IC-1810 | HP-ME-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.20 Material Requisition for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.1.2.25.13.1 Ordering | Final Issue for Design/ Construction-Material Requisition for fire fighting and safety equipment | Commercial Clarifications & Placement of PO for Fire Fighting & Safety Equipment | HE-HS-1130 | HP-ME-0980 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.2.1 Ordering | P2543-R01-Oct24..1.1.2.25.2.1 Ordering | RFQ, Receipt of Bid for Fire Suppression System | Prepare TBE and Company approval for Fire Suppression System | HP-ME-0910 | HP-ME-0920 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.7 Material Requisitions for Junction Boxes | P2543-R01-Oct24..1.1.2.25.16.1 Ordering | Final Issue for Design/ Construction-Material Requisitions for Junction Boxes | Commercial Clarifications & Placement of PO for Junction Boxes | HE-IC-2030 | HP-ME-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.1.2.LL.18.1 Ordering | Issue ICR- Material Requisitions for Field Instruments / H2S Analyzers | RFQ, Receipt of Bid for Gas Detectors | HE-IC-1930 | HP-ME-0710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.14.1 Ordering | P2543-R01-Oct24..1.1.2.25.14.1 Ordering | Prepare TBE and Company approval for Access Switch, Fiber Optic Patch Panel and Media Converter | Commercial Clarifications & Placement of PO for Access Switch, Fiber Optic Patch Panel and Media Converter | HP-ME-0670 | HP-ME-0680 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.1.2.25.14.1 Ordering | Issue ICR- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | RFQ, Receipt of Bid for Access Switch, Fiber Optic Patch Panel and Media Converter | HE-TL-0550 | HP-ME-0660 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.1.2.25.14.1 Ordering | Issue ICR- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | RFQ, Receipt of Bid for Access Switch, Fiber Optic Patch Panel and Media Converter | HE-TL-0490 | HP-ME-0660 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.1.2.LL.4.1 Ordering | Issue ICR- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | RFQ, Receipt of Bid for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0490 | HP-ME-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.13 E&I Works | P2543-R01-Oct24..1.2.12.13 E&I Works | E&I Works RFQ & Quotation Receipt | E&I Works Complete Evaluation (Internal) | HS-CN-0610 | HS-CN-0630 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.2.12.7 OHPL | Project Kick off Meeting | OHPL RFQ & Quotation Receipt | ML1002 | HS-CN-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | FOC Splicing / Termination Complete Evaluation (Internal) | FOC Splicing / Termination Subcontract Award | HS-CN-0280 | HS-CN-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | CP Drilling & Earthing Drilling RFQ & Quotation Receipt | CP Drilling & Earthing Drilling Complete Evaluation (Internal) | HS-CN-0210 | HS-CN-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..1.2.12.4 NDT / PWHT | NDT / PWHT RFQ & Quotation Receipt | NDT / PWHT Complete Evaluation (Internal) | HS-CN-0160 | HS-CN-0180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | Prepare TBE and Company approval - Modification of Exiting SMC / SCADA | Commercial Clarifications & Placement of PO - Modification of Exiting SMC / SCADA | HS-GN-0400 | HS-GN-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.10 Modification of Existing CTMM | P2543-R01-Oct24..1.1.BK.10 Modification of Existing CTMM | Prepare TBE and Company approval - Modification of Exiting CTMM | Commercial Clarifications & Placement of PO - Modification of Exiting CTMM | HS-GN-0280 | HS-GN-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | P2543-R01-Oct24..1.1.1.5 Hot Tapping | Issue ICR - Data Sheet - Split Tee | RFQ, Receipt of Bid for - Hot Tapping | HE-PL-1330 | HS-GN-0190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | Obtain Company Approval - Typical Detailed Drawing - Jib Crane Foundation | Final Issue for Design/ Construction-Typical Detailed Drawing - Jib Crane Foundation | HE-CS-1060 | HE-CS-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | Review Company Comments - Typical Detailed Drawing - Jib Crane Foundation | Re-Issue for Approval - Typical Detailed Drawing - Jib Crane Foundation | HE-CS-1040 | HE-CS-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | Issued for Review - Lighting pole foundation details | Review Company Comments - Lighting pole foundation details | HE-CS-0970 | HE-CS-0980 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.8.33 Filter Foundation GA and Details | Re-Issue after incorporating HAZOP / Review Comments- Plot plan - BVS | Issued for Review - Typical Spill Pit General Arrangement And RC (type) Details | HE-PI-0560 | HE-CS-0910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | Obtain Company Approval - Solar panel foundation details | Final Issue for Design/ Construction-Solar panel foundation details | HE-CS-0880 | HE-CS-0890 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | Obtain Company Approval - Gas metering skid foundation drawings | Final Issue for Design/ Construction-Gas metering skid foundation drawings | HE-CS-0820 | HE-CS-0830 | FF | Completed | Not Started | 10
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Final Issue for Design/ Construction - Pressure Reduction Skid and Leak Detection Drawings | HE-PI-0440 | HE-CS-0770 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | Issued for Review - Design Cal. for Typical Skid Foundations | Issued for Review - Pressure Reduction Skid and Leak Detection Drawings | HE-CS-0670 | HE-CS-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | Final Issue for Design/ Construction-Geotechnical Survey Report (Overall) | Final Issue for Design/ Construction-Design Calculation for Typical Skid Foundations | HE-GS-0050 | HE-CS-0710 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | Review Company Comments - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | Re-Issue for Approval - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | HE-CS-0620 | HE-CS-0630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..1.EN.8.11 Civil UG layout | Re-Issue for Approval - Civil UG layout | Obtain Company Approval - Civil UG layout | HE-CS-0510 | HE-CS-0520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.17 Typical details of protection slab to protect existing UG pipe at road crossing | P2543-R01-Oct24..1.EN.8.17 Typical details of protection slab to protect existing UG pipe at road crossing | Re-Issue for Approval - Typical details of protection slab to protect existing UG pipe at road crossing | Obtain Company Approval - Typical details of protection slab to protect existing UG pipe at road crossing | HE-CS-0390 | HE-CS-0400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | Issued for Review - Typical Road and paving detail drawing | Issued for Review - Typical Fence and gate detail drawing | HE-CS-0250 | HE-CS-0310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | Re-Issue for Approval - Typical Road and paving detail drawing | Obtain Company Approval - Typical Road and paving detail drawing | HE-CS-0270 | HE-CS-0280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | Re-Issue for Approval - Typical trench detail drawing | Obtain Company Approval - Typical trench detail drawing | HE-CS-0150 | HE-CS-0160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | Final Issue for Design/ Construction-Addendum to DGs | Final Issue for Design/ Construction-Standard drawings for Anchor bolt | HE-CS-0050 | HE-CS-0110 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction-Civil UG layout | Issued - Civil MTO 2 | HE-CS-0530 | HE-CS-1550 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | Final Issue for Design/ Construction- Addendum to DGS | Final Issue for Design/ Construction-Material Requisitions for Sales Gas CRS Filters | HE-ME-0050 | HE-ME-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | Issue ICR-Datasheet for Sales Gas CRS Filters | Receive Company Comments-Datasheet for Sales Gas CRS Filters | HE-ME-0070 | HE-ME-0080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | Final Issue for Design/ Construction-Process Datasheets - Filters (At Sweihan CRS) | Final Issue for Design/ Construction-Datasheet for Sales Gas CRS Filters | HE-PR-0470 | HE-ME-0110 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | Obtain Company Approval- Addendum to DGS | Final Issue for Design/ Construction- Addendum to DGS | HE-ME-0040 | HE-ME-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | Re-Issue for Approval- Addendum to DGS | Obtain Company Approval- Addendum to DGS | HE-ME-0030 | HE-ME-0040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Issue ICR- Overall Plot Plan - 4" N2 Source Pipeline | Issue ICR- Plot plan - BVS | HE-PI-0460 | HE-PI-0530 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Final Issue for Design/ Construction-Process Flow Diagrams ( New + Existing) | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | HE-PR-0090 | HE-PI-0580 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Issue ICR-Topographical Survey Report (Overall) | Re-Issue after incorporating HAZOP / Review Comments- Plot plan - BVS | HE-TS-0010 | HE-PI-0560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Receive Company Comments- Overall Plot Plan - 4" N2 Source Pipeline | Re-Issue for HAZOP Studies- Overall Plot Plan - 4" N2 Source Pipeline | HE-PI-0470 | HE-PI-0480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Issue ICR- Overall Plot Plan - 4" N2 Source Pipeline | Receive Company Comments- Overall Plot Plan - 4" N2 Source Pipeline | HE-PI-0460 | HE-PI-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Re-Issue for HAZOP Studies- Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Re-Issue after incorporating HAZOP /Review Comments - 52" Pipeline SWEIHAN CRS | HE-PI-0410 | HE-PI-0420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Issue ICR- Process Flow Diagrams ( New + Existing) | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | HE-PR-0040 | HE-PI-0390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue for HAZOP Studies- Overall Plot Plan - 52" Pipeline SWEIHAN CRS | HE-PR-0060 | HE-PI-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.16 Critical line List | P2543-R01-Oct24..1.EN.7.16 Critical line List | Receive Company Comments-Critical line List | Re-Issue for Approval-Critical line List | HE-PI-0272 | HE-PI-0282 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.17 Line List | P2543-R01-Oct24..1.EN.7.16 Critical line List | Issue ICR- Line List | Issue ICR-Critical line List | HE-PR-1090 | HE-PI-0262 | FS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | Issue ICR-Pipe Wall Thickness Calculation | Issue ICR-Piping Stress Analysis & Report | HE-PI-0200 | HE-PI-1140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | Final Issue for Design/ Construction-Pipe Wall Thickness Calculation | Final Issue for Design/ Construction-Piping Stress Analysis & Report | HE-PI-0240 | HE-PI-1180 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.2.6 TBE for Ball valves/ Plug Valves | P2543-R01-Oct24..1.EN.7.2.6 TBE for Ball valves/ Plug Valves | Issue ICR- TBE for Ball valves/ Plug Valves | Receive Company Comments- TBE for Ball valves/ Plug Valves | HE-PI-1080 | HE-PI-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | Issue ICR-MR for Ball valves/ Plug Valves | Receive Company Comments-MR for Ball valves/ Plug Valves | HE-PI-1020 | HE-PI-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | Receive Company Comments- Datasheet for Plug Valves | Re-Issue for Approval- Datasheet for Plug Valves | HE-PI-0970 | HE-PI-0980 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | Obtain Company Approval- Datasheet for Plug Valves | Final Issue for Design/ Construction-Datasheet for Plug valves | HE-PI-0990 | HE-PI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.17 Line List | P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | Issue ICR- Line List | Issue ICR-Data sheet for Ball Valves | HE-PR-1090 | HE-PI-0900 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | Issue ICR - Piping GA Drawings for 591-BVS-01 | Receive Company Comments-Piping GA Drawings for 591-BVS-01 | HE-PI-0780 | HE-PI-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | Final Issue for Design/ Construction-Piping Stress Analysis & Report | Final Issue for Design/ Construction-Piping GA- 52" Pipeline SWEIHAN CRS | HE-PI-1180 | HE-PI-0700 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Final Issue for Design/ Construction-Piping GA- 52" Pipeline SWEIHAN CRS | HE-PI-0440 | HE-PI-0700 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR- Process Simulations Report | Issue ICR-Piping GA-56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0610 | HE-PI-0600 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.7.10 3D Model | 90% Model Review | 90% Model Review Report | HE-PI-0170 | HE-PI-0180 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.7.10 3D Model | 30% Model Review | 60% Model Review | ML2059-B05 | HE-PI-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.7.10 3D Model | Issue ICR- P&ID's | 30% Model Review | HE-PR-0110 | HE-PI-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.19 HAZID/ ENVID/ OHID Close out Report | P2543-R01-Oct24..1.EN.4.19 HAZID/ ENVID/ OHID Close out Report | Re-Issue for Approval-HAZID/ ENVID/ OHID Close out Report | Obtain Company Approval-HAZID/ ENVID/ OHID Close out Report | HE-HS-0630 | HE-HS-0640 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | Issue ICR-F&G Cause and Effect | Issue ICR- Fire Fighting & Safety Eqpt. Layout | HE-HS-0310 | HE-HS-0370 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | Receive Company Comments-Fire Fighting & Safety Eqpt. Layout | Re-Issue for Approval-Fire Fighting & Safety Eqpt. Layout | HE-HS-0380 | HE-HS-0390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | Issue ICR- Fire Fighting & Safety Eqpt. Layout | Receive Company Comments-Fire Fighting & Safety Eqpt. Layout | HE-HS-0370 | HE-HS-0380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | Obtain Company Approval-F&G Cause and Effect | Final Issue for Design/ Construction-F&G Cause and effect | HE-HS-0340 | HE-HS-0350 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.5 F&G layout | P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | Obtain Company Approval-F&G Layout | Re-Issue for Approval-F&G Cause and Effect | HE-HS-0280 | HE-HS-0330 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.4.5 F&G layout | Re-Issue after incorporating HAZOP / Review Comments- Plot plan - BVS | Issue ICR-F&G Layout | HE-PI-0560 | HE-HS-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | Final Issue for Design/ Construction-Project HSE Philosophy | Final Issue for Design/ Construction-HAZID / ENVID / OHID Procedure | HE-HS-0110 | HE-HS-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | Receive Company Comments - HAZID / ENVID / OHID Procedure | Re-Issue for Approval - HAZID / ENVID / OHID Procedure | HE-HS-0140 | HE-HS-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | Issue ICR - HAZID / ENVID / OHID Procedure | Receive Company Comments - HAZID / ENVID / OHID Procedure | HE-HS-0130 | HE-HS-0140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | Issue ICR-HSE Philosophy | Issue ICR - HAZID / ENVID / OHID Procedure | HE-HS-0070 | HE-HS-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | Issue ICR-TBE for Fire Fighting & Safety Eqpt | Receive Company Comments-TBE for Fire Fighting & Safety Eqpt | HE-HS-1150 | HE-HS-1160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | Obtain Company Approval-TBE for Fire Fighting & Safety Eqpt | Final Issue for Design/ Construction-TBE for fire fighting and safety equipment | HE-HS-1180 | HE-HS-1190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.21 HAZOP close out report | P2543-R01-Oct24..1.EN.4.21 HAZOP close out report | Obtain Company Approval- HAZOP Close Out Report | Final Issue for Design/ Construction-HAZOP close out report | HE-HS-0760 | HE-HS-0770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | Final Issue for Design/ Construction-Specification for RTU | Final Issue for Design/ Construction-Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | HE-IC-0230 | HE-TL-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | Receive Company Comments-Telecom Equipment Layout | Re-Issue for Approval-Telecom Equipment Layout | HE-TL-0740 | HE-TL-0750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Re-Issue for Approval- FOC Block diagram (Telecom) | Re-Issue for Approval- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0450 | HE-TL-0510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | Re-Issue for Approval- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Obtain Company Approval- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0210 | HE-TL-0220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Re-Issue for Approval - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Re-Issue for Approval- Telecom Tie-in Block Diagram | HE-TL-0090 | HE-TL-0390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Final Issue for Design/ Construction-Telecom cable schedule | HE-TL-0710 | HE-TL-0830 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Final Issue for Design/ Construction-Telecom cable schedule | HE-TL-0350 | HE-TL-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Issue ICR- Telecom Cable Schedule | Receive Company Comments- Telecom Cable Schedule | HE-TL-0790 | HE-TL-0800 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | Issue ICR- FOC Block diagram (Telecom) | Issue ICR-Telecom Location and Cable Routing layout | HE-TL-0430 | HE-TL-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- FOC Block diagram (Telecom) | Issue ICR- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0430 | HE-TL-0550 | FS | Completed | Completed | 9
P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Receive Company Comments- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Re-Issue for Approval- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0560 | HE-TL-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Obtain Company Approval- FOC Block diagram (Telecom) | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | HE-TL-0460 | HE-TL-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | HE-TL-0410 | HE-TL-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Issue ICR- Overall Telecom Block Diagram | Issue ICR- FOC Block diagram (Telecom) | HE-TL-0310 | HE-TL-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Issue ICR- Telecom Tie-in Block Diagram | Issue ICR- FOC Block diagram (Telecom) | HE-TL-0370 | HE-TL-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Issue ICR- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-TL-0070 | HE-TL-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.11 Data Sheet - Pipeline Isolating Joints | P2543-R01-Oct24..1.EN.1.9.20 MR for Isolating Joints | Issue ICR - Data Sheet - Isolating joints | Issue ICR - MR for Isolating Joints | HE-PL-1390 | HE-PL-1870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.9 Data Sheet - Linepipes | P2543-R01-Oct24..1.EN.1.9.17 MR for Linepipes | Re-Issue for Approval - Data Sheet - Line pipes | Re-Issue for Approval - MR for Line pipes | HE-PL-1170 | HE-PL-1650 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.6 Pipeline Location Class selection Report | P2543-R01-Oct24..1.EN.1.6 Pipeline Location Class selection Report | Receive Company Comments - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | Re-Issue for Approval - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | HE-PL-0800 | HE-PL-0810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.3 Pipeline Upheavl Calculation | P2543-R01-Oct24..1.EN.1.3 Pipeline Upheavl Calculation | Re-Issue for Approval - Pipeline Upheaval Calculation | Obtain Company Approval - Pipeline Upheaval Calculation | HE-PL-0630 | HE-PL-0640 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.3 Pipeline Upheavl Calculation | P2543-R01-Oct24..1.EN.1.3 Pipeline Upheavl Calculation | Issue ICR - Pipeline Upheaval Calculation | Receive Company Comments - Pipeline Upheaval Calculation | HE-PL-0610 | HE-PL-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | P2543-R01-Oct24..1.EN.1.27 Pipeline Typical Drawings | Issue ICR - Pipeline Specifications - Addendum to DGS | Issue ICR - Pipeline Typical Drawings | HE-PL-0070 | HE-PL-0370 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | Re-Issue for Approval - Overall Pipeline Route Map - 4" | Obtain Company Approval - Overall Pipeline Route Map - 4" | HE-PL-0270 | HE-PL-0280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | Receive Company Comments - Pipeline Wall Thickness Calculation Report | Re-Issue for Approval - Specification -Pipeline Wall Thickness Calculation Report | HE-PL-0020 | HE-PL-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | Issue ICR - Detailed crossing drawings-52" | Receive Company Comments - Detailed crossing drawings-52" | HE-PL-2990 | HE-PL-3000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | Receive Company Comments - Detailed crossing drawings - 56" | Re-Issue for Approval - Detailed crossing drawings - 56" | HE-PL-2880 | HE-PL-2890 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | Obtain Company Approval - Pipeline Stress Analysis Report | Final Issue for Design/ Construction-Pipeline Stress Analysis Report | HE-PL-2840 | HE-PL-2850 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.3 Pipeline Upheavl Calculation | P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | Issue ICR - Pipeline Upheaval Calculation | Issue ICR - Pipeline Stress Analysis Report | HE-PL-0610 | HE-PL-2810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.1 Pipeline Route Verification and Selection Report | Issue ICR-Topographical Survey Report (Overall) | Issue ICR - Pipeline Route Verification and Selection Report | HE-TS-0010 | HE-PL-2750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.15 Pipeline Station approach drawing - 4" Nitrogen | P2543-R01-Oct24..1.EN.1.15 Pipeline Station approach drawing - 4" Nitrogen | Receive Company Comments - Pipeline Station Approach drawing -4" | Re-Issue for Approval - Pipeline Station Approach drawing -4" | HE-PL-2700 | HE-PL-2710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | Obtain Company Approval - Pipeline Alignment Sheets-52" | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | HE-PL-2480 | HE-PL-2490 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.1.1.2.1 Ordering | P2543-R01-Oct24..1.EN.1.10.24 TBE for Pigging Tees | RFQ, Receipt of Bid for Pigging & Split Tee | Issue ICR - TBE for Pigging Tees | HP-ME-1270 | HE-PL-2150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A331 TBE for Leak Detection System | P2543-R01-Oct24..1.EN.6.2.A331 TBE for Leak Detection System | Issue ICR-TBE for Leak Detection System | Receive Company Comments-TBE for Leak Detection System | HE-IC-2230 | HE-IC-2240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Obtain Company Approval-Material Requisitions for Leak Detection System | Final Issue for Design/ Construction-Material Requisitions for Leak Detection System | HE-IC-1780 | HE-IC-1790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Receive Company Comments-Instrument Trench Layout | Re-Issue for Approval-Instrument Trench Layout | HE-IC-0980 | HE-IC-0990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | Re-Issue for Approval- Specification for Leak Detection System | Obtain Company Approval- Specification for Leak Detection System | HE-IC-0270 | HE-IC-0280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.8 TBE for Junction Boxes | P2543-R01-Oct24..1.EN.6.2.8 TBE for Junction Boxes | Re-Issue for Approval- TBE for Junction Boxes | Obtain Company Approval- TBE for Junction Boxes | HE-IC-2490 | HE-IC-2500 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A2 Instrument Index | Obtain Company Approval-Instrument index -Update | Final Issue for Design/ Construction-Instrument Index | HE-IC-0520 | HE-IC-0530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | Final Issue for Design/ Construction-Specification for Leak Detection System | Final Issue for Design/ Construction-Power Consumption Calculation (Instrumentation) | HE-IC-0290 | HE-EL-5480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | Re-Issue for Approval- Specification for Leak Detection System | Issue ICR- Power Consumption Calculation (Instrumentation) | HE-IC-0270 | HE-EL-5440 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | Issue ICR- Material Requisitions for Field Instruments / H2S Analyzers | Receive Company Comments- Material Requisitions for Field Instruments / H2S Analyzers | HE-IC-1930 | HE-IC-1940 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | Receive Company Comments- Specification for RTU | Re-Issue for Approval- Specification for RTU | HE-IC-0200 | HE-IC-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | Obtain Company Approval- Specifications for PRS (Pressure Reduction System) | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | HE-IC-0100 | HE-IC-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Re-Issue for Approval - Hook-Up Diagram | Instrument 2nd MTO | HE-IC-0630 | HE-IC-2610 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Re-Issue for Approval-Instrument Trench Layout | Instrument 2nd MTO | HE-IC-0990 | HE-IC-2610 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Re-Issue for Approval- Instrument location and Cable Routing Drawings | Obtain Company Approval- Instrument location and Cable Routing Drawings | HE-IC-2550 | HE-IC-2560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.10 TBE for Fire & Gas Detectors | P2543-R01-Oct24..1.EN.6.2.10 TBE for Fire & Gas Detectors | Re-Issue for Approval- TBE for Gas Detectors | Obtain Company Approval- TBE for Gas Detectors | HE-IC-2370 | HE-IC-2380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A30 TBE for Metering Skid | P2543-R01-Oct24..1.EN.6.2.A30 TBE for Metering Skid | Receive Company Comments-TBE for Metering Skid | Re-Issue for Approval-TBE for Metering Skid | HE-IC-2120 | HE-IC-2130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.6 TBE for MOV | P2543-R01-Oct24..1.EN.6.2.6 TBE for MOV | Issue ICR- TBE for MOV | Receive Company Comments- TBE for MOV | HE-IC-2050 | HE-IC-2060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.9.1 Ordering | P2543-R01-Oct24..1.EN.6.2.6 TBE for MOV | RFQ, Receipt of Bid for MOV | Issue ICR- TBE for MOV | HP-ME-0310 | HE-IC-2050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A17 Material Requisitions for Metering Skid | P2543-R01-Oct24..1.EN.6.11.A17 Material Requisitions for Metering Skid | Re-Issue for Approval- Material Requisitions for Metering Skid | Obtain Company Approval- Material Requisitions for Metering Skid | HE-IC-1830 | HE-IC-1840 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | Re-Issue for Approval- Datasheets for F&G Devices | Obtain Company Approval- Datasheets for F&G Devices | HE-IC-1530 | HE-IC-1540 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | Issue ICR- P&ID's | Issue ICR-Datasheets for Field Instruments / H2S Analyzers | HE-PR-0110 | HE-IC-1450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | Final Issue for Design/ Construction-Addendum to DGs | Final Issue for Design/ Construction-Datasheets for Field Instruments / H2S Analyzers | HE-IC-0050 | HE-IC-1490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | Receive Company Comments-Datasheets for Field Instruments / H2S Analyzers | Re-Issue for Approval-Datasheets for Field Instruments / H2S Analyzers | HE-IC-1460 | HE-IC-1470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | Issue ICR- Datasheets for PSV & Orifice (incl. RO) | Receive Company Comments- Datasheets for PSV & Orifice (incl. RO) | HE-IC-1330 | HE-IC-1340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | Final Issue for Design/ Construction-Addendum to DGs | Final Issue for Design/ Construction-Datasheets for PSV & Orifice (incl. RO) | HE-IC-0050 | HE-IC-1370 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | Obtain Company Approval- Datasheets for PSV & Orifice (incl. RO) | Final Issue for Design/ Construction-Datasheets for PSV & Orifice (incl. RO) | HE-IC-1360 | HE-IC-1370 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | Receive Company Comments- Instrument Cable Block Diagram | Re-Issue for Approval- Instrument Cable Block Diagram | HE-IC-0800 | HE-IC-0810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | Issue ICR- Instrument Cable Block Diagram | Receive Company Comments- Instrument Cable Block Diagram | HE-IC-0790 | HE-IC-0800 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | Final Issue for Design/ Construction-Specification for Leak Detection System | Final Issue for Design/ Construction-Instrument Cable Block Diagram | HE-IC-0290 | HE-IC-0830 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Final Issue for Design/ Construction-I/O list | Final Issue for Design/ Construction-Loop Diagrams | HE-IC-0590 | HE-IC-0770 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | Re-Issue for Approval - Typical Installation Drawings | Obtain Company Approval - Typical Installation Drawings | HE-IC-0690 | HE-IC-0700 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | Re-Issue for Approval-Instrument index -Update | Re-Issue for Approval - Typical Installation Drawings | HE-IC-0510 | HE-IC-0690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | Receive Company Comments - Typical Installation Drawings | Re-Issue for Approval - Typical Installation Drawings | HE-IC-0680 | HE-IC-0690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A3 I/O list | Issue ICR- P&ID's | Issue ICR- I/O list -Update | HE-PR-0110 | HE-IC-0550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.17 Line List | P2543-R01-Oct24..1.EN.3.17 Line List | Receive Company Comments- Line List | Re-Issue for Approval- Line List | HE-PR-1100 | HE-PR-1110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.10 Equipment List | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval - Equipment List | HE-PR-0070 | HE-PR-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | Issue ICR- Process Simulations Report | Issue ICR- Vent and Depressurization Report (for new facilities) | HE-PR-0610 | HE-PR-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | Issue ICR- Vent and Depressurization Report (for new facilities) | HE-PI-0390 | HE-PR-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | Re-Issue for Approval- Operating and control philosophy , Safeguarding philosophy | Re-Issue for Approval - Pre-commissioning and commissioning philosophy | HE-PR-0750 | HE-PR-0930 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Re-Issue for Approval - Relief, Vent and Blowdown Philosophy | HE-PR-0140 | HE-PR-0810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | Re-Issue for Approval- Process Simulations Report | Re-Issue for Approval- Operating and control philosophy , Safeguarding philosophy | HE-PR-0630 | HE-PR-0750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | Receive Company Comments- Process Simulations Report | Re-Issue for Approval- Process Simulations Report | HE-PR-0620 | HE-PR-0630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | Issue ICR- Process Datasheets - Pig Launcher / Receiver | Receive Company Comments- Process Datasheets - Pig Launcher / Receiver | HE-PR-0490 | HE-PR-0500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Obtain Company Approval- Process Datasheets - Filters (At Sweihan CRS) | Final Issue for Design/ Construction-Process Datasheets - Filters (At Sweihan CRS) | HE-PR-0460 | HE-PR-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Re-Issue for Approval- Process Datasheets - Filters (At Sweihan CRS) | HE-PR-0140 | HE-PR-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | Design Review Workshop | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | HE-WS-0030 | HE-PR-0060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | Obtain Company Approval- Process Flow Diagrams ( New + Existing) | Final Issue for Design/ Construction-Process Flow Diagrams ( New + Existing) | HE-PR-0080 | HE-PR-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.3.3 Process Design Basis | Re-Issue for Approval-Design Basis | Obtain Company Approval-Design Basis | HE-DB-0030 | HE-DB-0040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.3.3 Process Design Basis | Receive Company Comments-Design Basis | Re-Issue for Approval-Design Basis | HE-DB-0020 | HE-DB-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.1 Site Visit Report | P2543-R01-Oct24..1.EN.2.1 Site Visit Report | Obtain Company Approval - Site Visit /Survey Report | Final Issue for Design/ Construction-Site Visit Report | HE-SV-0040 | HE-SV-0050 | FF | Completed | In Progress | 10
P2543-R01-Oct24..1.EN.2.1 Site Visit Report | P2543-R01-Oct24..1.EN.2.1 Site Visit Report | Receive Company Comments- - Site Visit /Survey Report | Re-Issue for Approval - Site Visit /Survey Report | HE-SV-0020 | HE-SV-0030 | FF | Completed | Completed | 10
P2543-R01-Oct24..1.EN.2.4 Constructability Review/ SIMOPS Report | P2543-R01-Oct24..1.EN.2.4 Constructability Review/ SIMOPS Report | Receive Company Comments-Constructability Review / SIMOPS Report | Re-Issue for Approval-Constructability Review / SIMOPS Report | HE-ST-0020 | HE-ST-0030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.2.4 Constructability Review/ SIMOPS Report | P2543-R01-Oct24..1.EN.2.4 Constructability Review/ SIMOPS Report | Issue ICR-Constructability Review / SIMOPS Report | Receive Company Comments-Constructability Review / SIMOPS Report | HE-ST-0010 | HE-ST-0020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | Obtain Company Approval - Geo Technical Survey Report (Overall) | Final Issue for Design/ Construction-Geotechnical Survey Report (Overall) | HE-GS-0040 | HE-GS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..1.PM.12 Workshops | Issue Project Control, PMS and Planning Dossier covering Baseline Schedule, Histograms, S-Curves, etc. - Final Issue | Design Review Workshop | ML1002-A02 | HE-WS-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- Isolation & Tie-In philosophy | Constructability Review Workshop | HE-PR-0850 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.9 HSE Studies | P2543-R01-Oct24..1.PM.12 Workshops | Place LOA/FOA - HSE Studies | HAZID /ENVID/OHID/ PHSER Workshop | HS-GN-0110 | HE-WS-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.2 Survey & Studies | Project Kick off Meeting | Site Visit | ML1002 | HE-SS-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.30 TBE for Distibution Transformers | P2543-R01-Oct24..1.EN.9.6.30 TBE for Distibution Transformers | Receive Company Comments-TBE for Distribution Transformer | Re-Issue for Approval-TBE for Distribution Transformer | HE-EL-1460 | HE-EL-1470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | Issue ICR-Single Line Diagrams for LV Switchgear | Issue ICR-Cable Sizing Calculation | HE-EL-0190 | HE-EL-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | Re-Issue for Approval-Solar Panel System SLDs | Obtain Company Approval-Solar Panel System SLDs | HE-EL-0330 | HE-EL-0340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | Re-Issue for Approval-Single Line Diagrams for LV Switchgear | Obtain Company Approval-Single Line Diagrams for LV Switchgear | HE-EL-0210 | HE-EL-0220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | Receive Company Comments- Adequacy report of the Power supply requirements | Re-Issue for Approval- Adequacy report of the Power supply requirements | HE-EL-0140 | HE-EL-0150 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | Re-Issue for Approval-Update /New Load List | Re-Issue for Approval- Adequacy report of the Power supply requirements | HE-EL-0090 | HE-EL-0150 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | Re-Issue for Approval-Update /New Load List | Obtain Company Approval-Update /New Load List | HE-EL-0090 | HE-EL-0100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..1.EN.9.12 Earthing Layout | Re-Issue for Approval-Earthing Layout | Obtain Company Approval-Earthing Layout | HE-EL-1650 | HE-EL-1660 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | Obtain Company Approval-Cable Routing Layout | Final Issue for Design/ Construction-Cable Routing Layout | HE-EL-1600 | HE-EL-1610 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.26 TBE for Power & Control Cables | P2543-R01-Oct24..1.EN.9.6.26 TBE for Power & Control Cables | Receive Company Comments-TBE for Power & Control Cables | Re-Issue for Approval-TBE for Power & Control Cables | HE-EL-1520 | HE-EL-1530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.7.1 Ordering | P2543-R01-Oct24..1.EN.9.6.28 TBE for Distribution Boards | RFQ, Receipt of Bid for Power Distribution Boards | Issue ICR-TBE for Distribution Boards | HP-ME-0410 | HE-EL-1390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.8 TBE for Solar Panels | P2543-R01-Oct24..1.EN.9.6.8 TBE for Solar Panels | Obtain Company Approval-TBE for Solar Panels | Final Issue for Design/ Construction-TBE for Solar Panels | HE-EL-1300 | HE-EL-1310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.8 TBE for Solar Panels | P2543-R01-Oct24..1.EN.9.6.8 TBE for Solar Panels | Re-Issue for Approval-TBE for Solar Panels | Obtain Company Approval-TBE for Solar Panels | HE-EL-1290 | HE-EL-1300 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.29 TBE for Active/ Passive Shelters | P2543-R01-Oct24..1.EN.6.2.29 TBE for Active/ Passive Shelters | Obtain Company Approval - TBE for Active / Passive Shelters | Final Issue for Design/ Construction-TBE for Active/ Passive Shelters | HE-EL-1240 | HE-EL-1250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | Re-Issue for Approval-Material Requisition for Solar Panels | Obtain Company Approval-Material Requisition for Solar Panels | HE-EL-1110 | HE-EL-1120 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | Issue ICR- Data sheet for LV Distribution board | Issue ICR-Material Requisition for Distribution Boards | HE-EL-0610 | HE-EL-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.18 Material Requisition for UPS System | P2543-R01-Oct24..1.EN.9.1.18 Material Requisition for UPS System | Obtain Company Approval-Material Requisition for UPS System | Final Issue for Design/ Construction-Material Requisition for UPS System | HE-EL-0940 | HE-EL-0950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..1.EN.9.1.18 Material Requisition for UPS System | Issue ICR - UPS SLD | Issue ICR-Material Requisition for UPS System | HE-EL-0250 | HE-EL-0910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | Obtain Company Approval - Material Requisition for Active / Passive Shelters | Final Issue for Design/ Construction-Material Requisition for Active/ Passive Shelters | HE-EL-0880 | HE-EL-0890 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | Re-Issue for Approval - Material Requisition for Active / Passive Shelters | Obtain Company Approval - Material Requisition for Active / Passive Shelters | HE-EL-0870 | HE-EL-0880 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | Re-Issue for Approval-Data Sheet for LV cables | Obtain Company Approval-Data Sheet for LV cables | HE-EL-0810 | HE-EL-0820 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | Issue ICR- Datasheet for Solar panel system | Receive Company Comments- Datasheet for Solar panel system | HE-EL-0730 | HE-EL-0740 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | Issue ICR- Data sheet for LV Distribution board | Receive Company Comments-Data sheet for LV Distribution board | HE-EL-0610 | HE-EL-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.PM.4 NOC Register | Final Issue for Design/ Construction-Overall Plot Plan- 4" N2 Source Pipeline | Final Issue for Design/ Construction-NOC Register | HE-PI-0510 | HC-GN-0290 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.PM.6 Quality documents | P2543-R01-Oct24..1.PM.6 Quality documents | Receive Company Comments-QAQC procedure | Re-Issue for Approval-QAQC procedure | HC-GN-0200 | HC-GN-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.2 Planning Package | P2543-R01-Oct24..1.PM.3 Project Procedure (PEP, Numbering Procedure) | Issue ICR-Planning Package | Issue ICR-Project Procedure (PEP, Numbering Procedure etc.) | HC-GN-0010 | HC-GN-0070 | SS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.17.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.17.3 Delivery & receipt at Site | Ready for Dispatch of Leak Detection System | Transportation/ Custom Clearance/ Delivery at site of Leak Detection System | HM-ME-0250 | HM-ME-0270 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.17.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.17.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Leak Detection System | Factory Acceptance Test of Leak Detection System | HM-ME-0220 | HM-ME-0230 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.1.2.25.1.1 Ordering | P2543-R01-Oct24..PR.26.1.1.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Distribution Transformer | Vendor Document Review of Distribution Transformer | HP-ME-0480 | HM-ME-0920 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.1.15.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - F & G System | Vendor Document Review of Field Instruments | ML1269-C12 | HM-ME-1520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..PR.26.1.14.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Manufacturing & Assembly of Access Switch, Fiber Optic Patch Panel and Media Converter | HE-TL-0530 | HM-ME-1330 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..PR.26.LL.4.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.4.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Testing and Inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | HM-ME-1230 | HM-ME-1240 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.LL.5.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.5.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Active/ Passive Cooled Shelter | Manufacturing & Assembly of Active/ Passive Cooled Shelter | HM-ME-1120 | HM-ME-1130 | FF | Completed | In Progress | 20
P2543-R01-Oct24..1.1.2.25.7.1 Ordering | P2543-R01-Oct24..PR.26.1.7.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Power Distribution Boards | Ready for Dispatch of Power Distribution Boards | HP-ME-0430 | HM-ME-0860 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.8.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.8.3 Delivery & receipt at Site | Ready for Dispatch of AC UPS | Transportation/ Custom Clearance/ Delivery at site of AC UPS | HM-ME-0760 | HM-ME-0780 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.LL.9.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - MOV/ROV/GOV Valves | Vendor Document Review of MOV | ML1022-C07 | HM-ME-0610 | FF | Completed | In Progress | 0
P2543-R01-Oct24..1.1.2.LL.10.1 Ordering | P2543-R01-Oct24..PR.26.LL.10.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for ROV/ GOV | Vendor Document Review of ROV/ GOV | HP-ME-0280 | HM-ME-0510 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Pig Launchers & Receivers (52" Line) | Receipt at site and inspection of Pig Launchers & Receivers (52" Line) | HM-ME-0470 | HM-ME-0480 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.25.3.1 Ordering | P2543-R01-Oct24..PR.26.1.3.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for HVAC Equipment | Vendor Document Review of HVAC Equipment | HP-ME-0880 | HM-ME-1720 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.1.2.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.2.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of Fire Suppression System | Packaging & Final Inspection-Fire Suppression System | HM-ME-1870 | HM-ME-1880 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | Issue MRs for All Mechanical Equipment & Packages (Final Issue) | Manufacturing & Assembly of Pressure Reduction Skid | ML1017-B18 | HM-ME-0120 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.LL.22.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.22.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Custody Metering Skid | Receipt at site and inspection of Custody Metering Skid | HM-ME-0070 | HM-ME-0080 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.15.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Earthing Material | Manufacturing & Assembly of Earthing Material | HM-EL-0310 | HM-EL-0320 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.4.1 Ordering | P2543-R01-Oct24..PR.BK.4.2 Manufacturing & Ready for Dispatch | Final Piping Bulk material MTO | Final Piping Bulk material MTO | HP-BK-0350 | HM-PI-0020 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.13.1 Ordering | P2543-R01-Oct24..PR.BK.13.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Cable Trays | Ready for Dispatch of Cable Trays | HP-BK-0130 | HM-EL-0250 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.13.1 Ordering | P2543-R01-Oct24..PR.BK.13.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Cable Trays | Vendor Document Review of Cable Trays | HP-BK-0130 | HM-EL-0210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Power & Control Cables | Ready for Dispatch of Power & Control Cables | HM-EL-0040 | HM-EL-0050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.16.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.16.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of MCT (Lot 1) | Receipt at site and inspection of MCT (Lot 1) | HM-EL-0470 | HM-EL-0480 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.16.1 Ordering | P2543-R01-Oct24..PR.BK.16.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for MCT | Vendor Document Review of MCT | HP-BK-0230 | HM-EL-0410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Receipt at site and inspection of Line Pipes - Lot 6 (Coated) | Receipt at site and inspection of Line Pipes - Lot 7 (Coated) | HM-PL-0110 | HM-PL-0120 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.9.17 MR for Linepipes | P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | Final Issue for Design/ Construction-MR for Line pipes | Vendor Document Review of Line Pipes - Lot 1 | HE-PL-1670 | HM-PL-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Isolating Joints (Lot 1) | Receipt at site and inspection of Isolating Joints (Lot 1) | HM-PL-0730 | HM-PL-0740 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.3.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Isolating Joints | Ready for Dispatch of Isolating Joints | HM-PL-0700 | HM-PL-0710 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Receipt at site and inspection of Hot Incution Bend (100% Qty) | HM-PL-0630 | HM-PL-0640 | FF | Not Started | Not Started | 30
P2543-R01-Oct24..PR.1.19.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.19.2 Manufacturing & Ready for Dispatch | Testing and Inspection of Pig Signaler | Packaging & Final Inspection-Pig Singler | HM-PL-0480 | HM-PL-0490 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.20.2 Manufacturing & Ready for Dispatch | Vendor Document Review of CP System | Manufacturing & Assembly of CP System | HM-PL-0350 | HM-PL-0360 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.LL.20.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - Isolation Joints | Vendor Document Review of CP System | ML1041-C03 | HM-PL-0350 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | HM-PL-0210 | HM-PL-0220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.1.1 Ordering | P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Manual/ Ball/ Globe/ Check/ Plug Valves | Vendor Document Review of Ball/ Globe/ Check/ Plug Valves | HP-ME-1090 | HM-PL-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - Valves – Globe/Check/Plug | Vendor Document Review of Ball/ Globe/ Check/ Plug Valves | ML1369-C21 | HM-PL-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.4.AB.2 Final Documentation | P2543-R01-Oct24..ML.4 Commissioning and PAC | Vendor Documents Package | Achieve (PAC-2) for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | CAB-5310 | ML2049-F06 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pipeline | Complete As-Built drawings including Project close out report and submit to COMPANY | CAB-4480 | ML1989-E44 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of FOC Cables (Lot 1) | Receive at Site - Fiber Optic Cable | HM-EL-0180 | ML1057-D19 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.16.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Line Pipes (Coated) | Issue Purchase Order (Final) - Line pipes | HP-ME-1040 | ML1040-C01 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.4.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Issue Purchase Order (Final) - IDS & PIDS System | HP-ME-0630 | ML1339-C18 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-0350 | ML1034-B25 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-0650 | ML1034-B25 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-0290 | ML1034-B25 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical duct bank detail drawing | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-0230 | ML1034-B25 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Cable Schedule | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | HE-EL-0590 | ML1032-B21 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Material Requisitions for Field Instruments / H2S Analyzers | Issue MRs for All E&I Equipment & Packages (Final Issue) | HE-IC-1970 | ML1027-B17 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.17 MR for Linepipes | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-MR for Line pipes | Issue MR (Final) - Line pipes | HE-PL-1670 | ML1021-B15 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Civil UG layout | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | HE-CS-0530 | ML1015-B08 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Datasheet for Sales Gas CRS Filters | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | HE-ME-0110 | ML1015-B08 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue for HAZOP Studies- Overall Plot Plan - 4" N2 Source Pipeline | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | HE-PI-0480 | ML1012-B06 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Geotechnical Survey Report (Overall) | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 52" Pipeline(IFC) | HE-GS-0050 | ML1009-B04 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.4 Topographical survey & Geotechnical Investigation | P2543-R01-Oct24..ML.EN Detail Engineering | Place LOA/FOA - Topographical survey & Geotechnical Investigation | Award Subcontracts for Topographical Survey/ Geotechnical Investigation Studies | HS-GN-0170 | ML1007-B02 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Piping GA- 52" Pipeline SWEIHAN CRS | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-PI-0700 | ML1219-B19 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical Detailed Drawing - Jib Crane Foundation | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-1070 | ML1209-B27 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-0350 | ML1209-B27 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Standard drawings for Anchor bolt | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-0110 | ML1209-B27 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.PM.6 Quality documents | P2543-R01-Oct24..ML.GE General | Final Issue for Design/ Construction-Quality documents | Issue Project Execution Plan (PEP), Coordination, Engineering, Procurement, HSE and Quality Procedures-Final Issue | HC-GN-0230 | ML1001-A01 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Pipeline Welding - 36"Jump-over line | Project Finish | ML1899-E35 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Receive at Site - Solar Power System | Project Finish | ML1429-D17 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.2 Final Documentation | P2543-R01-Oct24..ML Milestones | Close-out report | Project Finish | CAB-5320 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Receive at Site - E&I Equipment's (RTUs) | Project Finish | ML1469-D13 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Pipeline welding - 52" Sales Gas Pipeline - 25% Welding | Project Finish | ML1689-E14 | ML1060 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | Project Finish | ML1629-E08 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Construction of Anchor Blocks - 52" Sales Gas Pipeline | Project Finish | ML1729-E18 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | Project Finish | ML1959-E41 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 06 to Sweihan Receiver | Project Finish | ML1819-E27 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..ML Milestones | Pipeline | Project Finish | CAB-4480 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | Project Finish | ML1030 | ML1060 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 03 to BVS-04 | Project Finish | ML1789-E24 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | Project Finish | ML1679-E13 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Construction of Anchor Blocks - 56" Sales Gas Pipeline | Project Finish | ML1609-E06 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | Project Finish | ML1949-E40 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.4 Commissioning and PAC | P2543-R01-Oct24..ML Milestones | Achieve (PAC-2) for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | Achieve PAC-2 for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | ML2049-F06 | ML1050 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Mechanical | Close-out report | CAB-4430 | CAB-5320 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Civil & Structural | Close-out report | CAB-4420 | CAB-5320 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Pipeline | Close-out report | CAB-4480 | CAB-5320 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Process | Close-out report | CAB-4400 | CAB-5320 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..1.EN.2.4 Constructability Review/ SIMOPS Report | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Final Issue for Design/ Construction-Constructability Review/ SIMOPS Report | General | HE-ST-0050 | CAB-5290 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Obtain Final Route Approval from Authorities | General | ML1011-A05 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Electrical | Vendor Documents Package | CAB-4450 | CAB-5310 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of ROV/ GOV (1st Lot) | Vendor Documents Package | HM-ME-0580 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Civil & Structural | Vendor Documents Package | CAB-4420 | CAB-5310 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..PR.26.LL.22.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of Custody Metering Skid | Vendor Documents Package | HM-ME-0080 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.11.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of Filter Package | Vendor Documents Package | HM-ME-0380 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Piping | Quality Dossier | CAB-4440 | CAB-5300 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..1.PM.6 Quality documents | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Final Issue for Design/ Construction-Quality documents | Quality Dossier | HC-GN-0230 | CAB-5300 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Pipeline | HE-PL-2490 | CAB-4480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.4 Pipeline Road and Railway Crossing Calculation Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline Road and Railway Crossing Calculation Report | Pipeline | HE-PL-0710 | CAB-4480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.3 Pipeline Upheavl Calculation | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline Upheaval Calculation | Pipeline | HE-PL-0650 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction - Pipeline Wall Thickness Calculation Report | Pipeline | HE-PL-0050 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | Pipeline | HE-PL-2430 | CAB-4480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Overall Pipeline Route Map - 52" | Pipeline | HE-PL-0230 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.10.22 TBE for Linepipes | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Line pipes | Pipeline | HE-PL-2070 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline MTO - 56" and 52" | Pipeline | HE-PL-3270 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Crossing Schedule - 56" | Pipeline | HE-PL-2970 | CAB-4480 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.60.11 Data Sheet - Pipeline Isolating Joints | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Data Sheet - Pipeline Isolating Joints | Pipeline | HE-PL-1430 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.26 TBE for Mainline Ball Valve | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Mainline Ball Valve | Pipeline | HE-PL-2310 | CAB-4480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Telecom | HE-TL-0230 | CAB-4470 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Telecom | HE-TL-0110 | CAB-4470 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Instrumentation & Control | ML1219-B19 | CAB-4460 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Datasheets for Custody Flow Metering Skid | Instrumentation & Control | HE-IC-1190 | CAB-4460 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | Instrumentation & Control | HE-IC-0110 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.6 TBE for MOV | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for MOV | Instrumentation & Control | HE-IC-2090 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Data sheet for LV Distribution board | Electrical | HE-EL-0650 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | Electrical | ML1030 | CAB-4450 | FF | Not Started | Not Started | 15
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue SLD, Hazardous Area Classification Details for All Areas - IFC | Electrical | ML1031-B20 | CAB-4450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisition for Solar Panels | Electrical | HE-EL-1130 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.18 Material Requisition for UPS System | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisition for UPS System | Electrical | HE-EL-0950 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Solar Panel System SLDs | Electrical | HE-EL-0350 | CAB-4450 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Lighting Layout | Electrical | HE-EL-1730 | CAB-4450 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-UPS SLD | Electrical | HE-EL-0290 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Piping Stress Analysis & Report | Piping | HE-PI-1180 | CAB-4440 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Piping GA for 4" N2 Source Pipeline | Piping | HE-PI-0760 | CAB-4440 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisition for Ball/ Plug Valves | Piping | HE-PI-1060 | CAB-4440 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Mechanical | ML1014-B10 | CAB-4430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Geotechnical Survey Report (Overall) | Civil & Structural | HE-GS-0050 | CAB-4420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Civil & Structural | HE-CS-1310 | CAB-4420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Civil & Structural | ML1034-B25 | CAB-4420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.42 Civil MTO | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issued - Civil MTO 2 | Civil & Structural | HE-CS-1550 | CAB-4420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisition for Active/ Passive Shelters | Civil & Structural | HE-EL-0890 | CAB-4420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Civil & Structural | ML1032-B21 | CAB-4420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.11 QRA Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-QRA Report | HSE | HE-HS-0830 | CAB-4410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | HSE | ML1030 | CAB-4410 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Fire fighting & Safety equipment layout | HSE | HE-HS-0410 | CAB-4410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Complete HAZOP/ SIL/ LOPA Review as applicable and Submit final Report after incorporating Company comments (IFA) | HSE | ML1013-B07 | CAB-4410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Final Issue for Design/ Construction-Project HSE Philosophy | Issue ICR-Pre-commissioning and Commissioning Plan | HE-HS-0110 | C-COM-800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Hook-Up Diagram | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-IC-0650 | C-COM-790 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Issue ICR-Instrument index -Update | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-IC-0490 | C-COM-790 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | Issue ICR-Construction Procedures / Method Statements / ITPs | ML1012-B06 | C-COM-750 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.42 Civil MTO | P2543-R01-Oct24..1.1.BK.11.1 Ordering | Issued - Civil MTO 2 | Final Civil Bulk material MTO | HE-CS-1550 | HP-BK-0270 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.16.1 Ordering | P2543-R01-Oct24..1.1.BK.16.1 Ordering | Prepare TBE and Company approval for MCT | Commercial Clarifications & Placement of PO for MCT | HP-BK-0220 | HP-BK-0230 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..1.1.BK.13.1 Ordering | Issue ICR-Earthing Layout | RFQ, Receipt of Bid for Cable Trays | HE-EL-1630 | HP-BK-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.2.1 Ordering | P2543-R01-Oct24..1.1.1.2.1 Ordering | Prepare TBE and Company approval for Pigging & Split Tee | Commercial Clarifications & Placement of PO for Pigging & Split Tee | HP-ME-1280 | HP-ME-1290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.17 MR for Linepipes | P2543-R01-Oct24..1.1.1.16.1 Ordering | Issue ICR - MR for Line pipes | RFQ, Receipt of Bid for Line Pipes (Coated) | HE-PL-1630 | HP-ME-1020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.6.1 Ordering | P2543-R01-Oct24..1.1.2.LL.6.1 Ordering | Prepare TBE and Company approval for Solar PV system | Commercial Clarifications & Placement of PO for Solar PV system | HP-ME-0520 | HP-ME-0530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.1.1 Ordering | P2543-R01-Oct24..1.1.2.25.1.1 Ordering | Prepare TBE and Company approval for Distribution Transformer | Commercial Clarifications & Placement of PO for Distribution Transformer | HP-ME-0470 | HP-ME-0480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.7.1 Ordering | P2543-R01-Oct24..1.1.2.25.7.1 Ordering | RFQ, Receipt of Bid for Power Distribution Boards | Prepare TBE and Company approval for Power Distribution Boards | HP-ME-0410 | HP-ME-0420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.5 TBE for ROV/ GOV | P2543-R01-Oct24..1.1.2.LL.10.1 Ordering | Obtain Company Approval- TBE for ROV/ GOV | Commercial Clarifications & Placement of PO for ROV/ GOV | HE-IC-2320 | HP-ME-0280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A131 Material Requisitions for ROV/ GOV | P2543-R01-Oct24..1.1.2.LL.10.1 Ordering | Issue ICR- Material Requisitions for ROV/ GOV | RFQ, Receipt of Bid for ROV/ GOV | HE-IC-1630 | HP-ME-0260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.10.1 Ordering | P2543-R01-Oct24..1.1.2.LL.10.1 Ordering | RFQ, Receipt of Bid for ROV/ GOV | Prepare TBE and Company approval for ROV/ GOV | HP-ME-0260 | HP-ME-0270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.3.9 TBE for Sals Gas CRS Filters | P2543-R01-Oct24..1.1.2.LL.11.1 Ordering | Obtain Company Approval-TBEs for Sales Gas CRS Filters | Commercial Clarifications & Placement of PO for Filter Package | HE-ME-0220 | HP-ME-0180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A33 TBE for PRS (Pressure Reduction Skid) | P2543-R01-Oct24..1.1.2.LL.21.1 Ordering | Obtain Company Approval-TBE for PRS | Prepare TBE and Company approval for Pressure Reduction Skid | HE-IC-2200 | HP-ME-0070 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A16 Material Requisitions for PRS (Pressure Reduction Skid) | P2543-R01-Oct24..1.1.2.LL.21.1 Ordering | Issue ICR-Material Requisitions for PRS | RFQ, Receipt of Bid for Pressure Reduction Skid | HE-IC-1690 | HP-ME-0060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A30 TBE for Metering Skid | P2543-R01-Oct24..1.1.2.LL.22.1 Ordering | Final Issue for Design/ Construction-TBE for Metering Skid | Commercial Clarifications & Placement of PO for Custody Metering Skid | HE-IC-2150 | HP-ME-0030 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.3.1 Ordering | P2543-R01-Oct24..1.1.2.25.3.1 Ordering | RFQ, Receipt of Bid for HVAC Equipment | Prepare TBE and Company approval for HVAC Equipment | HP-ME-0860 | HP-ME-0870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.15.1 Ordering | P2543-R01-Oct24..1.1.2.25.15.1 Ordering | RFQ, Receipt of Bid for Field Instruments | Prepare TBE and Company approval for Field Instruments | HP-ME-0760 | HP-ME-0770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.15.1 Ordering | P2543-R01-Oct24..1.1.2.25.15.1 Ordering | Prepare TBE and Company approval for Field Instruments | Commercial Clarifications & Placement of PO for Field Instruments | HP-ME-0770 | HP-ME-0780 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.1.2.LL.18.1 Ordering | Final Issue for Design/ Construction-Material Requisitions for Field Instruments / H2S Analyzers | Commercial Clarifications & Placement of PO for Gas Detectors | HE-IC-1970 | HP-ME-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.4.1 Ordering | P2543-R01-Oct24..1.1.2.LL.4.1 Ordering | RFQ, Receipt of Bid for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Prepare TBE and Company approval for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HP-ME-0610 | HP-ME-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.11 Hot Tapping | P2543-R01-Oct24..1.2.12.11 Hot Tapping | Hot Tapping RFQ & Quotation Receipt | Hot Tapping Complete Evaluation (Internal) | HS-CN-0510 | HS-CN-0530 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.2.12.10 Earthworks | Project Kick off Meeting | Earthworks RFQ & Quotation Receipt | ML1002 | HS-CN-0460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..1.2.12.4 NDT / PWHT | NDT / PWHT Complete Evaluation (Internal) | NDT / PWHT Subcontract Award | HS-CN-0180 | HS-CN-0190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.4 Topographical survey & Geotechnical Investigation | P2543-R01-Oct24..1.2.13.4 Topographical survey & Geotechnical Investigation | Complete Evaluation (Internal) - Topographical survey & Geotechnical Investigation | Place LOA/FOA - Topographical survey & Geotechnical Investigation | HS-GN-0160 | HS-GN-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | Re-Issue after HAZOP /Review Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Issued for Review - Passive cooled shelter foundation GA and details | HE-PI-0350 | HE-CS-1270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | Review Company Comments - Impact Wall GA and RC (type) details | Re-Issue for Approval - Impact Wall GA and RC (type) details | HE-CS-1220 | HE-CS-1230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | Issue ICR - Geo Technical Survey Report (Overall) | Issued for Review - Calculations for Pipe supports | HE-GS-0010 | HE-CS-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | Re-Issue for Approval - Calculations for Pipe supports | Obtain Company Approval - Calculations for Pipe supports | HE-CS-1110 | HE-CS-1120 | FF | Completed | In Progress | 5
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | Re-Issue after incorporating HAZOP /Review Comments - 4" N2 Source Pipeline | Issued for Review - Typical Detailed Drawing - Jib Crane Foundation | HE-PI-0490 | HE-CS-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.33 Filter Foundation GA and Details | P2543-R01-Oct24..1.EN.8.33 Filter Foundation GA and Details | Re-Issue for Approval - Typical Spill Pit General Arrangement And RC (type) Details | Obtain Company Approval - Typical Spill Pit General Arrangement And RC (type) Details | HE-CS-0930 | HE-CS-0940 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | P2543-R01-Oct24..1.EN.8.33 Filter Foundation GA and Details | Issued for Review - Design Cal. for Typical Skid Foundations | Issued for Review - Typical Spill Pit General Arrangement And RC (type) Details | HE-CS-0670 | HE-CS-0910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.4 Solar Panel Sizing | P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | Final Issue for Design/ Construction-Solar Panel Sizing | Final Issue for Design/ Construction-Solar panel foundation details | HE-EL-0410 | HE-CS-0890 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.4 Solar Panel Sizing | P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | Issue ICR-Solar Panel Sizing calculation | Issued for Review - Solar panel foundation details | HE-EL-0370 | HE-CS-0850 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | Final Issue for Design/ Construction-Geotechnical Survey Report (Overall) | Final Issue for Design/ Construction-Gas metering skid foundation drawings | HE-GS-0050 | HE-CS-0830 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | Obtain Company Approval - Pressure Reduction Skid and Leak Detection Drawings | Final Issue for Design/ Construction - Pressure Reduction Skid and Leak Detection Drawings | HE-CS-0760 | HE-CS-0770 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | Re-Issue for Approval - Pressure Reduction Skid and Leak Detection Drawings | Obtain Company Approval - Pressure Reduction Skid and Leak Detection Drawings | HE-CS-0750 | HE-CS-0760 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | Issue ICR - Geo Technical Survey Report (Overall) | Issued for Review - Design Cal. for Typical Skid Foundations | HE-GS-0010 | HE-CS-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | Obtain Company Approval - Design Cal. for Typical Skid Foundations | Final Issue for Design/ Construction-Design Calculation for Typical Skid Foundations | HE-CS-0700 | HE-CS-0710 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | Vendor Document Review of Pig Launchers & Receivers | Re-Issue for Approval - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | HM-ME-0410 | HE-CS-0630 | SS | Completed | Completed | 20
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | Obtain Company Approval - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | HE-CS-0640 | HE-CS-0650 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.28 Calculation for Pig launcher and receiver foundations | P2543-R01-Oct24..1.EN.8.28 Calculation for Pig launcher and receiver foundations | Issued for Review - Calculation for Pig launcher and receiver foundations | Review Company Comments - Calculation for Pig launcher and receiver foundations | HE-CS-0550 | HE-CS-0560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..1.EN.8.11 Civil UG layout | Obtain Company Approval - Civil UG layout | Final Issue for Design/ Construction-Civil UG layout | HE-CS-0520 | HE-CS-0530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | Review Company Comments - Typical trench detail drawing | Re-Issue for Approval - Typical trench detail drawing | HE-CS-0140 | HE-CS-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | Issue ICR - Pipeline Specifications - Addendum to DGS | Issued for Review - Typical trench detail drawing | HE-PL-0070 | HE-CS-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | Review Company Comments - Standard drawings for Anchor bolt | Re-Issue for Approval - Standard drawings for Anchor bolt | HE-CS-0080 | HE-CS-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | Issued for Review - Addendum to DGs | Issued for Review - Standard drawings for Anchor bolt | HE-CS-0010 | HE-CS-0070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction-TYPICAL LIGHTING POLE FOUNDATION DETAILS | Issued - Civil MTO 2 | HE-CS-1010 | HE-CS-1550 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Issued - Civil MTO 2 | HE-CS-0650 | HE-CS-1550 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | Review Company Comments - Pipe Sleeper layout and details. | Re-Issue for Approval - Pipe Sleeper layout and details. | HE-CS-1400 | HE-CS-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | Re-Issue for Approval-Piping Stress Analysis & Report | Issued for Review - Typical Structural Steel and Foundation details for pipe support | HE-PI-1160 | HE-CS-1330 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | Re-Issue for Approval-Material Requisitions for Sales Gas CRS Filters | Obtain Company Approval-Material Requisitions for Sales Gas CRS Filters | HE-ME-0150 | HE-ME-0160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | Issue ICR- HAZOP reviews Report for all areas | Re-Issue for Approval-Datasheet for Sales Gas CRS Filters | HE-HS-0670 | HE-ME-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Final Issue for Design/ Construction-Process Flow Diagrams ( New + Existing) | Final Issue for Design/ Construction-Overall Plot Plan- 4" N2 Source Pipeline | HE-PR-0090 | HE-PI-0510 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue after incorporating HAZOP /Review Comments - 52" Pipeline SWEIHAN CRS | HE-PR-0070 | HE-PI-0420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Issue ICR-Topographical Survey Report (Overall) | Re-Issue after incorporating HAZOP /Review Comments - 52" Pipeline SWEIHAN CRS | HE-TS-0010 | HE-PI-0420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Re-Issue after HAZOP /Review Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Obtain Company Approval- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0350 | HE-PI-0360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Re-Issue for HAZOP Studies- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Re-Issue after HAZOP /Review Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0340 | HE-PI-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Receive Company Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0320 | HE-PI-0330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | Re-Issue for Approval-Piping Material Specifications | Obtain Company Approval-Piping Material Specifications | HE-PI-0030 | HE-PI-0040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.16 Critical line List | P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | Issue ICR-Critical line List | Issue ICR-Piping Stress Analysis & Report | HE-PI-0262 | HE-PI-1140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | Issue ICR - Pipeline Stress Analysis Report | Issue ICR-Piping Stress Analysis & Report | HE-PL-2810 | HE-PI-1140 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | Re-Issue for Approval-Piping Stress Analysis & Report | Obtain Company Approval-Piping Stress Analysis & Report | HE-PI-1160 | HE-PI-1170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.2.6 TBE for Ball valves/ Plug Valves | P2543-R01-Oct24..1.EN.7.2.6 TBE for Ball valves/ Plug Valves | Re-Issue for Approval- TBE for Ball valves/ Plug Valves | Obtain Company Approval- TBE for Ball valves/ Plug Valves | HE-PI-1100 | HE-PI-1110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | Obtain Company Approval-MR for Ball valves/ Plug Valves | Final Issue for Design/ Construction-Material Requisition for Ball/ Plug Valves | HE-PI-1050 | HE-PI-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | Issue ICR- Datasheet for Plug Valves | Receive Company Comments- Datasheet for Plug Valves | HE-PI-0960 | HE-PI-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | HE-PI-0580 | HE-PI-0880 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | Re-Issue for Approval-Piping GA for 591-BVS-01 to 06 | Obtain Company Approval-Piping GA for 591-BVS-01 to 06 | HE-PI-0860 | HE-PI-0870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | Receive Company Comments-Piping GA Drawings for 591-BVS-01 | Re-Issue for Approval-Piping GA Drawings for 591-BVS-01 | HE-PI-0790 | HE-PI-0800 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | Re-Issue for Approval-Piping GA for 4" N2 Source Pipeline | Obtain Company Approval-Piping GA for 4" N2 Source Pipeline | HE-PI-0740 | HE-PI-0750 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | Issue ICR- Piping GA for 4" N2 Source Pipeline | Receive Company Comments-Piping GA for 4" N2 Source Pipeline | HE-PI-0720 | HE-PI-0730 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | Issue ICR- Process Simulations Report | Issue ICR- Piping GA for 4" N2 Source Pipeline | HE-PR-0610 | HE-PI-0720 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | Obtain Company Approval-Piping GA for 52" Pipeline SWEIHAN CRS | Final Issue for Design/ Construction-Piping GA- 52" Pipeline SWEIHAN CRS | HE-PI-0690 | HE-PI-0700 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Vendor Document Review of Pig Launchers & Receivers | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HM-ME-0410 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.7.10 3D Model | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | 30% Model Review | HE-PI-0320 | HE-PI-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | Issue ICR-HAZOP Procedure | Issue ICR- HAZOP reviews Report for all areas | HE-HS-0190 | HE-HS-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.19 HAZID/ ENVID/ OHID Close out Report | P2543-R01-Oct24..1.EN.4.19 HAZID/ ENVID/ OHID Close out Report | Receive Company Comments-HAZID/ ENVID/ OHID Close out Report | Re-Issue for Approval-HAZID/ ENVID/ OHID Close out Report | HE-HS-0620 | HE-HS-0630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | Issue ICR - HAZID / ENVID / OHID Procedure | Issue ICR-HAZID/ ENVID/ OHID Report | HE-HS-0130 | HE-HS-0550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | P2543-R01-Oct24..1.EN.4.16 Datasheets for fire fighting and safety equipment | Final Issue for Design/ Construction-Fire fighting & Safety equipment layout | Final Issue for Design/ Construction-Datasheets for fire fighting and safety equipment | HE-HS-0410 | HE-HS-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.5 F&G layout | P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | Final Issue for Design/ Construction-F&G layout | Final Issue for Design/ Construction-F&G Cause and effect | HE-HS-0290 | HE-HS-0350 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | Issue ICR-F&G Cause and Effect | Receive Company Comments-F&G Cause and Effect | HE-HS-0310 | HE-HS-0320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.4.5 F&G layout | Re-Issue after incorporating HAZOP /Review Comments - 52" Pipeline SWEIHAN CRS | Issue ICR-F&G Layout | HE-PI-0420 | HE-HS-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | Re-Issue for Approval - HAZID / ENVID / OHID Procedure | Obtain Company Approval - HAZID / ENVID / OHID Procedure | HE-HS-0150 | HE-HS-0160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | Receive Company Comments-HSE Philosophy | Re-Issue for Approval-HSE Philosophy | HE-HS-0080 | HE-HS-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.4.4 Project HSE Plan | Issue ICR-Design Basis | Issue ICR-HSE Plan | HE-DB-0010 | HE-HS-0010 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.16 Datasheets for fire fighting and safety equipment | P2543-R01-Oct24..1.EN.4.20 Material Requisition for Fire Fighting and Safety Equipment | Issue ICR-Data Sheets for Fire Fighting & Safety Eqpt | Issue ICR-Material Requisition for Fire Fighting & Safety Eqpt | HE-HS-0430 | HE-HS-1092 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.20 Material Requisition for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.EN.4.20 Material Requisition for Fire Fighting and Safety Equipment | Receive Company Comments-Material Requisition for Fire Fighting & Safety Eqpt | Re-Issue for Approval-Material Requisition for Fire Fighting & Safety Eqpt | HE-HS-1100 | HE-HS-1110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | Receive Company Comments-HSE Action Tracking Register (Hazards and Effects Register) | Re-Issue for Approval-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-1040 | HE-HS-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.11 QRA Report | P2543-R01-Oct24..1.EN.4.11 QRA Report | Obtain Company Approval-QRA Report | Final Issue for Design/ Construction-QRA Report | HE-HS-0820 | HE-HS-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | Final Issue for Design/ Construction-Specification for Leak Detection System | Final Issue for Design/ Construction-Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | HE-IC-0290 | HE-TL-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | Obtain Company Approval- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Final Issue for Design/ Construction-Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0220 | HE-TL-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Final Issue for Design/ Construction-Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | HE-TL-0110 | HE-TL-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Receive Company Comments- Overall Telecom Block Diagram | Re-Issue for Approval- Overall Telecom Block Diagram | HE-TL-0320 | HE-TL-0330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Final Issue for Design/ Construction-Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Final Issue for Design/ Construction-Overall Telecom Block Diagram | HE-TL-0110 | HE-TL-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..1.EN.10.2 Telecom MTO | Final Issue for Design/ Construction-Telecom Equipment Layout | Telecom 3rd MTO | HE-TL-0770 | HE-TL-0890 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Final Issue for Design/ Construction-Telecom cable schedule | HE-TL-0290 | HE-TL-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | Re-Issue for Approval- FOC Block diagram (Telecom) | Re-Issue for Approval-Telecom Location and Cable Routing layout | HE-TL-0450 | HE-TL-0690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Final Issue for Design/ Construction-Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc. | HE-TL-0470 | HE-TL-0590 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | HE-TL-0290 | HE-TL-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Re-Issue for Approval-Instrument index -Update | Re-Issue for Approval- FOC Block diagram (Telecom) | HE-IC-0510 | HE-TL-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Final Issue for Design/ Construction-Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-TL-0110 | HE-TL-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.20 MR for Isolating Joints | P2543-R01-Oct24..1.EN.1.9.20 MR for Isolating Joints | Obtain Company Approval - MR for Isolating Joints | Final Issue for Design/ Construction-MR for Isolating Joints | HE-PL-1900 | HE-PL-1910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.20 MR for Isolating Joints | P2543-R01-Oct24..1.EN.1.9.20 MR for Isolating Joints | Receive Company Comments - MR for Isolating Joints | Re-Issue for Approval - MR for Isolating Joints | HE-PL-1880 | HE-PL-1890 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.19 MR for Pipeline Pigging Tees | P2543-R01-Oct24..1.EN.1.9.19 MR for Pipeline Pigging Tees | Issue ICR - MR for Pigging Tees | Receive Company Comments - MR for Pigging Tees | HE-PL-1810 | HE-PL-1820 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.12 Data Sheet - Pipeline Pigging Tees | P2543-R01-Oct24..1.EN.1.9.19 MR for Pipeline Pigging Tees | Final Issue for Design/ Construction-Data Sheet - Pipeline Pigging Tees | Final Issue for Design/ Construction-MR for Pipeline Pigging Tees | HE-PL-1490 | HE-PL-1850 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.19 MR for Pipeline Pigging Tees | P2543-R01-Oct24..1.EN.1.9.19 MR for Pipeline Pigging Tees | Obtain Company Approval - MR for Pigging Tees | Final Issue for Design/ Construction-MR for Pipeline Pigging Tees | HE-PL-1840 | HE-PL-1850 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.18 MR for Hot Induction Bends | P2543-R01-Oct24..1.EN.1.9.18 MR for Hot Induction Bends | Re-Issue for Approval - MR for Hot Induction Bends | Obtain Company Approval - MR for Hot Induction Bends | HE-PL-1770 | HE-PL-1780 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.10 Data Sheet - Hot Induction Bends | P2543-R01-Oct24..1.EN.1.9.18 MR for Hot Induction Bends | Issue ICR - Data Sheet - Hot Induction Bends | Issue ICR - MR for Hot Induction Bends | HE-PL-1270 | HE-PL-1750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.51 Data Sheet - Mainline Ball Valve | P2543-R01-Oct24..1.EN.6.11.21 Material Requisition for Manual Ball Valves | Issue ICR - Data Sheet - Mainline Ball Valve | Issue ICR - MR for Mainline Ball Valve | HE-PL-1210 | HE-PL-1690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.14 Data Sheet - Anchor Flange | P2543-R01-Oct24..1.EN.1.60.14 Data Sheet - Anchor Flange | Re-Issue for Approval - Data Sheet - Anchor Flange (If Required) | Obtain Company Approval - Data Sheet - Anchor Flange (If Required) | HE-PL-1530 | HE-PL-1540 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.12 Data Sheet - Pipeline Pigging Tees | P2543-R01-Oct24..1.EN.1.60.12 Data Sheet - Pipeline Pigging Tees | Issue ICR - Data Sheet - Pigging Tees | Receive Company Comments - Data Sheet - Pigging Tees | HE-PL-1450 | HE-PL-1460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.11 Data Sheet - Pipeline Isolating Joints | P2543-R01-Oct24..1.EN.1.60.11 Data Sheet - Pipeline Isolating Joints | Obtain Company Approval - Data Sheet - Isolating joints | Final Issue for Design/ Construction-Data Sheet - Pipeline Isolating Joints | HE-PL-1420 | HE-PL-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.40 Specification - Split Tee | P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | Issue ICR - Specification - Split Tee | Issue ICR - Data Sheet - Split Tee | HE-PL-0430 | HE-PL-1330 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | P2543-R01-Oct24..1.EN.6.4.51 Data Sheet - Mainline Ball Valve | Issue ICR - Pipeline Specifications - Addendum to DGS | Issue ICR - Data Sheet - Mainline Ball Valve | HE-PL-0070 | HE-PL-1210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.51 Data Sheet - Mainline Ball Valve | P2543-R01-Oct24..1.EN.6.4.51 Data Sheet - Mainline Ball Valve | Re-Issue for Approval - Data Sheet - Mainline Ball Valve | Obtain Company Approval - Data Sheet - Mainline Ball Valve | HE-PL-1230 | HE-PL-1240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.1.3 Pipeline Upheavl Calculation | Issue ICR-Design Basis | Issue ICR - Pipeline Upheaval Calculation | HE-DB-0010 | HE-PL-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | Obtain Company Approval - Overall Pipeline Route Map - 4" | Final Issue for Design/ Construction-Overall Pipeline Route Map - 4" | HE-PL-0280 | HE-PL-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | Receive Company Comments - Overall Pipeline Route Map - 52" | Re-Issue for Approval - Overall Pipeline Route Map - 52" | HE-PL-0200 | HE-PL-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | Site Visit | Issue ICR - Overall Pipeline Route Map - 52" | HE-SS-0020 | HE-PL-0190 | FS | Completed | Completed | 20
P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | Re-Issue for Approval - Pipeline MTO - 56" | Obtain Company Approval - Pipeline MTO - 56" | HE-PL-3250 | HE-PL-3260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..1.EN.1.44 Detailed crossing drawings-4" | Issue ICR - Pipeline Alignment Sheets-4" | Issue ICR - Detailed crossing drawings-4" | HE-PL-2510 | HE-PL-3110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.44 Detailed crossing drawings-4" | P2543-R01-Oct24..1.EN.1.44 Detailed crossing drawings-4" | Re-Issue for Approval - Detailed crossing drawings-4" | Obtain Company Approval - Detailed crossing drawings-4" | HE-PL-3130 | HE-PL-3140 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.38 Crossing Schedule-52" | P2543-R01-Oct24..1.EN.1.38 Crossing Schedule-52" | Obtain Company Approval - Crossing Schedule-52" | Final Issue for Design/ Construction-Crossing Schedule-52" | HE-PL-3080 | HE-PL-3090 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.38 Crossing Schedule-52" | P2543-R01-Oct24..1.EN.1.38 Crossing Schedule-52" | Re-Issue for Approval - Crossing Schedule-52" | Obtain Company Approval - Crossing Schedule-52" | HE-PL-3070 | HE-PL-3080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | Issue ICR - Detailed crossing drawings - 56" | Receive Company Comments - Detailed crossing drawings - 56" | HE-PL-2870 | HE-PL-2880 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.1.15 Pipeline Station approach drawing - 4" Nitrogen | Issue ICR- Overall Plot Plan - 4" N2 Source Pipeline | Issue ICR - Pipeline Station Approach drawing -4" | HE-PI-0460 | HE-PL-2690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | Issue ICR - Pipeline Station Approach drawing -52" | HE-PI-0390 | HE-PL-2630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | Receive Company Comments - Pipeline Alignment Sheets-52" | Re-Issue for Approval - Pipeline Alignment Sheets-52" | HE-PL-2460 | HE-PL-2470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | Issue ICR - Pipeline Alignment Sheets -56" | Receive Company Comments - Pipeline Alignment Sheets -56" | HE-PL-2390 | HE-PL-2400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.54 TBE for Pig Signaler | P2543-R01-Oct24..1.EN.6.2.54 TBE for Pig Signaler | Receive Company Comments- TBE for Pig Signaler | Re-Issue for Approval- TBE for Pig Signaler | HE-PL-2340 | HE-PL-2350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.25 TBE for Isolating Joints | P2543-R01-Oct24..1.EN.1.10.25 TBE for Isolating Joints | Issue ICR - TBE for Isolating Joints | Receive Company Comments - TBE for Isolating Joints | HE-PL-2210 | HE-PL-2220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.23 TBE for Hot Induction Bends | P2543-R01-Oct24..1.EN.1.10.23 TBE for Hot Induction Bends | Receive Company Comments - TBE for Hot Induction Bends | Re-Issue for Approval - TBE for Hot Induction Bends | HE-PL-2100 | HE-PL-2110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Issue ICR-Material Requisitions for Leak Detection System | Receive Company Comments-Material Requisitions for Leak Detection System | HE-IC-1750 | HE-IC-1760 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Receive Company Comments-Material Requisitions for Leak Detection System | Re-Issue for Approval-Material Requisitions for Leak Detection System | HE-IC-1760 | HE-IC-1770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Obtain Company Approval- Instrument Cable Block Diagram | Re-Issue for Approval-Instrument Trench Layout | HE-IC-0820 | HE-IC-0990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.7 Material Requisitions for Junction Boxes | P2543-R01-Oct24..1.EN.6.11.7 Material Requisitions for Junction Boxes | Re-Issue for Approval- Material Requisitions for Junction Boxes | Obtain Company Approval- Material Requisitions for Junction Boxes | HE-IC-2010 | HE-IC-2020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.15.1 Ordering | P2543-R01-Oct24..1.EN.6.2.3 TBE for Field Instruments / H2S Analyzers | RFQ, Receipt of Bid for Field Instruments | Issue ICR- TBE for Field Instruments / H2S Analyzers | HP-ME-0760 | HE-IC-2410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | Issue ICR-Datasheets for Field Instruments / H2S Analyzers | Issue ICR- Material Requisitions for Field Instruments / H2S Analyzers | HE-IC-1450 | HE-IC-1930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | Issue ICR- Specification for RTU | Receive Company Comments- Specification for RTU | HE-IC-0190 | HE-IC-0200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | Receive Company Comments- Specifications for PRS (Pressure Reduction System) | Re-Issue for Approval- Specifications for PRS (Pressure Reduction System) | HE-IC-0080 | HE-IC-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | Issue ICR- Addendum to DGs | Receive Company Comments- Addendum to DGs | HE-IC-0010 | HE-IC-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Re-Issue for Approval-Instrument and F&G Cable Schedule | Instrument 2nd MTO | HE-IC-0930 | HE-IC-2610 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Re-Issue for Approval- Instrument location and Cable Routing Drawings | Instrument 2nd MTO | HE-IC-2550 | HE-IC-2610 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Re-Issue for Approval-Instrument index -Update | Instrument 2nd MTO | HE-IC-0510 | HE-IC-2610 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.10 TBE for Fire & Gas Detectors | P2543-R01-Oct24..1.EN.6.2.10 TBE for Fire & Gas Detectors | Receive Company Comments- TBE for Gas Detectors | Re-Issue for Approval- TBE for Gas Detectors | HE-IC-2360 | HE-IC-2370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.10 TBE for Fire & Gas Detectors | P2543-R01-Oct24..1.EN.6.2.10 TBE for Fire & Gas Detectors | Obtain Company Approval- TBE for Gas Detectors | Final Issue for Design/ Construction-TBE for Gas Detectors | HE-IC-2380 | HE-IC-2390 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.2.A33 TBE for PRS (Pressure Reduction Skid) | P2543-R01-Oct24..1.EN.6.2.A33 TBE for PRS (Pressure Reduction Skid) | Obtain Company Approval-TBE for PRS | Final Issue for Design/ Construction-TBE for PRS | HE-IC-2200 | HE-IC-2210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A33 TBE for PRS (Pressure Reduction Skid) | P2543-R01-Oct24..1.EN.6.2.A33 TBE for PRS (Pressure Reduction Skid) | Receive Company Comments-TBE for PRS | Re-Issue for Approval-TBE for PRS | HE-IC-2180 | HE-IC-2190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.9 Material Requisitions for Fire & Gas Detectors | P2543-R01-Oct24..1.EN.6.11.9 Material Requisitions for Fire & Gas Detectors | Obtain Company Approval- Material Requisitions for Gas Detectors | Final Issue for Design/ Construction-Material Requisitions for Gas Detectors | HE-IC-1900 | HE-IC-1910 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.11.A16 Material Requisitions for PRS (Pressure Reduction Skid) | P2543-R01-Oct24..1.EN.6.11.A16 Material Requisitions for PRS (Pressure Reduction Skid) | Re-Issue for Approval-Material Requisitions for PRS | Obtain Company Approval-Material Requisitions for PRS | HE-IC-1710 | HE-IC-1720 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | P2543-R01-Oct24..1.EN.6.11.A16 Material Requisitions for PRS (Pressure Reduction Skid) | Issue ICR- Data sheet for PRS (Pressure Reduction System) | Issue ICR-Material Requisitions for PRS | HE-IC-1210 | HE-IC-1690 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | Issue ICR- Addendum to DGs | Issue ICR- Datasheets for F&G Devices | HE-IC-0010 | HE-IC-1510 | SS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | Final Issue for Design/ Construction-Addendum to DGs | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | HE-IC-0050 | HE-IC-1550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | Obtain Company Approval- Datasheets for F&G Devices | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | HE-IC-1540 | HE-IC-1550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | Issue ICR-Datasheets for Field Instruments / H2S Analyzers | Receive Company Comments-Datasheets for Field Instruments / H2S Analyzers | HE-IC-1450 | HE-IC-1460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | Re-Issue for Approval-Datasheets for Field Instruments / H2S Analyzers | Obtain Company Approval-Datasheets for Field Instruments / H2S Analyzers | HE-IC-1470 | HE-IC-1480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Final Issue for Design/ Construction-Process Datasheets - PRS Skid (at Sweihan CRS) | Final Issue for Design/ Construction-Data sheet for PRS (Pressure Reduction System) | HE-PR-0410 | HE-IC-1250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | Issue ICR- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | Issue ICR- Datasheets for Metering Skid | HE-PR-0310 | HE-IC-1150 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | Final Issue for Design/ Construction-Addendum to DGs | Final Issue for Design/ Construction-Datasheets for Custody Flow Metering Skid | HE-IC-0050 | HE-IC-1190 | FF | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | Receive Company Comments- Datasheet for MOV | Re-Issue for Approval- Datasheet for MOV | HE-IC-1040 | HE-IC-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | Obtain Company Approval- Datasheet for MOV | Final Issue for Design/ Construction-Actuator Datasheet for MOVs | HE-IC-1060 | HE-IC-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Re-Issue for Approval- FOC Block diagram (Telecom) | Re-Issue for Approval-Instrument and F&G Cable Schedule | HE-TL-0450 | HE-IC-0930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Receive Company Comments- Instrument Cable Block Diagram | Issue ICR-Instrument and F&G Cable Schedule | HE-IC-0800 | HE-IC-0910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Issue ICR- Instrument location and Cable Routing Drawings | Issue ICR-Instrument and F&G Cable Schedule | HE-IC-2530 | HE-IC-0910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Obtain Company Approval - Loop Diagrams | Final Issue for Design/ Construction-Loop Diagrams | HE-IC-0760 | HE-IC-0770 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Re-Issue for Approval - Loop Diagrams | Obtain Company Approval - Loop Diagrams | HE-IC-0750 | HE-IC-0760 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Re-Issue for Approval- Instrument Cable Block Diagram | Re-Issue for Approval - Loop Diagrams | HE-IC-0810 | HE-IC-0750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | Obtain Company Approval - Typical Installation Drawings | Final Issue for Design/ Construction-Typical Installation Drawings | HE-IC-0700 | HE-IC-0710 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | Issue ICR-Instrument index -Update | Issue ICR - Hook-Up Diagram | HE-IC-0490 | HE-IC-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.17 Line List | Final Issue for Design/ Construction-Process Simulations Report | Final Issue for Design/ Construction-Line List | HE-PR-0650 | HE-PR-1130 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.17 Line List | P2543-R01-Oct24..1.EN.3.17 Line List | Re-Issue for Approval- Line List | Obtain Company Approval- Line List | HE-PR-1110 | HE-PR-1120 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.10 Equipment List | P2543-R01-Oct24..1.EN.3.10 Equipment List | Obtain Company Approval - Equipment List | Final Issue for Design/ Construction-Equipment List | HE-PR-1060 | HE-PR-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.10 Equipment List | Final Issue for Design/ Construction-Process Datasheets - Filters (At Sweihan CRS) | Final Issue for Design/ Construction-Equipment List | HE-PR-0470 | HE-PR-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..1.EN.3.10 Equipment List | Issue ICR- Process Datasheets - Pig Launcher / Receiver | Issue ICR - Equipment List | HE-PR-0490 | HE-PR-1030 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | Re-Issue for Approval- Vent and Depressurization Report (for new facilities) | Obtain Company Approval- Vent and Depressurization Report (for new facilities) | HE-PR-0990 | HE-PR-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | Obtain Company Approval - Pre-commissioning and commissioning philosophy | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | HE-PR-0940 | HE-PR-0950 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | Receive Company Comments - Pre-commissioning and commissioning philosophy | Re-Issue for Approval - Pre-commissioning and commissioning philosophy | HE-PR-0920 | HE-PR-0930 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | Issue ICR - Pre-commissioning and commissioning philosophy | Receive Company Comments - Pre-commissioning and commissioning philosophy | HE-PR-0910 | HE-PR-0920 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | Re-Issue for Approval - Relief, Vent and Blowdown Philosophy | Obtain Company Approval - Relief, Vent and Blowdown Philosophy | HE-PR-0810 | HE-PR-0820 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | Issue ICR- Operating and control philosophy, Safeguarding philosophy | Receive Company Comments- Operating and control philosophy , Safeguarding philosophy | HE-PR-0730 | HE-PR-0740 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | Receive Company Comments- Process Datasheets | Re-Issue for Approval- Process Datasheets | HE-PR-0560 | HE-PR-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Re-Issue for Approval- Process Datasheets - Filters (At Sweihan CRS) | Obtain Company Approval- Process Datasheets - Filters (At Sweihan CRS) | HE-PR-0450 | HE-PR-0460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Receive Company Comments- Process Datasheets - Filters (At Sweihan CRS) | Re-Issue for Approval- Process Datasheets - Filters (At Sweihan CRS) | HE-PR-0440 | HE-PR-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Issue ICR- Process Datasheets - Filters (At Sweihan CRS) | Receive Company Comments- Process Datasheets - Filters (At Sweihan CRS) | HE-PR-0430 | HE-PR-0440 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | Obtain Company Approval- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | Final Issue for Design/ Construction-Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | HE-PR-0340 | HE-PR-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | Re-Issue for Approval- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | Obtain Company Approval- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | HE-PR-0330 | HE-PR-0340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Re-Issue for HAZOP Studies- P&ID's review | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | HE-PR-0130 | HE-PR-0140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | Issue ICR- HAZOP reviews Report for all areas | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | HE-HS-0670 | HE-PR-0070 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.6 Project Risk Review Register | P2543-R01-Oct24..1.EN.2.6 Project Risk Review Register | Re-Issue for Approval-Project Risk review register | Obtain Company Approval-Project Risk review register | HE-RR-0030 | HE-RR-0040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.1 Site Visit Report | P2543-R01-Oct24..1.EN.2.1 Site Visit Report | Issue ICR - Site Visit /Survey Report | Receive Company Comments- - Site Visit /Survey Report | HE-SV-0010 | HE-SV-0020 | FF | Completed | Completed | 10
P2543-R01-Oct24..1.EN.2.4 Constructability Review/ SIMOPS Report | P2543-R01-Oct24..1.EN.2.4 Constructability Review/ SIMOPS Report | Obtain Company Approval-Constructability Review / SIMOPS Report | Final Issue for Design/ Construction-Constructability Review/ SIMOPS Report | HE-ST-0040 | HE-ST-0050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Design Review Workshop | HE-PI-0320 | HE-WS-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | Design Review Workshop | HE-PI-0390 | HE-WS-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- Overall Plot Plan - 4" N2 Source Pipeline | Design Review Workshop | HE-PI-0460 | HE-WS-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Constructability Review Workshop | HE-PI-0320 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.PM.12 Workshops | Project Risk Review Workshop | Constructability Review Workshop | HE-WS-0010 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.PM.12 Workshops | Receive Company Comments- Overall Plot Plan - 4" N2 Source Pipeline | HAZID /ENVID/OHID/ PHSER Workshop | HE-PI-0470 | HE-WS-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.PM.12 Workshops | Receive Company Comments-Design Basis | HAZID /ENVID/OHID/ PHSER Workshop | HE-DB-0020 | HE-WS-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.PM.12 Workshops | Receive Company Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HAZID /ENVID/OHID/ PHSER Workshop | HE-PI-0330 | HE-WS-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | Obtain Company Approval-Data sheet for Distribution Transformer | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | HE-EL-0700 | HE-EL-0710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | Re-Issue for Approval-Data sheet for Distribution Transformer | Obtain Company Approval-Data sheet for Distribution Transformer | HE-EL-0690 | HE-EL-0700 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | Obtain Company Approval-Solar Panel System SLDs | Final Issue for Design/ Construction-Solar Panel System SLDs | HE-EL-0340 | HE-EL-0350 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..1.EN.9.22 UPS SLDs | Receive Company Comments - UPS SLD | Re-Issue for Approval - UPS SLD | HE-EL-0260 | HE-EL-0270 | FS | Completed | Completed | 30
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..1.EN.9.22 UPS SLDs | Issue ICR - UPS SLD | Receive Company Comments - UPS SLD | HE-EL-0250 | HE-EL-0260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | Obtain Company Approval-Single Line Diagrams for LV Switchgear | Final Issue for Design/ Construction-Single Line Diagrams for LV Distribution Board | HE-EL-0220 | HE-EL-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | Receive Company Comments-Update /New Load List | Re-Issue for Approval-Update /New Load List | HE-EL-0080 | HE-EL-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..1.EN.9.16 Electrical MTO | Final Issue for Design/ Construction-Earthing Layout | Electrical 3rd MTO | HE-EL-1670 | HE-EL-1850 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | Re-Issue for Approval- Electrical Equipment Layout | Re-Issue for Approval-Cable Routing Layout | HE-EL-0510 | HE-EL-1590 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | Receive Company Comments-Cable Routing Layout | Re-Issue for Approval-Cable Routing Layout | HE-EL-1580 | HE-EL-1590 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.27 TBE for UPS System | P2543-R01-Oct24..1.EN.9.6.27 TBE for UPS System | Obtain Company Approval-TBE for UPS System | Final Issue for Design/ Construction-TBE for UPS System | HE-EL-1360 | HE-EL-1370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.8.1 Ordering | P2543-R01-Oct24..1.EN.9.6.27 TBE for UPS System | RFQ, Receipt of Bid for AC UPS | Issue ICR-TBE for UPS System | HP-ME-0360 | HE-EL-1330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.8 TBE for Solar Panels | P2543-R01-Oct24..1.EN.9.6.8 TBE for Solar Panels | Issue ICR-TBE for Solar Panels | Receive Company Comments-TBE for Solar Panels | HE-EL-1270 | HE-EL-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | Receive Company Comments-Material Requisition for Distribution Boards | Re-Issue for Approval-Material Requisition for Distribution Boards | HE-EL-0980 | HE-EL-0990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | Obtain Company Approval-Material Requisition for Distribution Boards | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | HE-EL-1000 | HE-EL-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.18 Material Requisition for UPS System | P2543-R01-Oct24..1.EN.9.1.18 Material Requisition for UPS System | Re-Issue for Approval-Material Requisition for UPS System | Obtain Company Approval-Material Requisition for UPS System | HE-EL-0930 | HE-EL-0940 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | Final Issue for Design/ Construction-Addendum to DGs | Final Issue for Design/ Construction-Material Requisition for Active/ Passive Shelters | HE-CS-0050 | HE-EL-0890 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | Receive Company Comments- Datasheet for Solar panel system | Re-Issue for Approval- Datasheet for Solar panel system | HE-EL-0740 | HE-EL-0750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | Issue ICR- Electrical Equipment Layout | Receive Company Comments- Electrical Equipment Layout | HE-EL-0490 | HE-EL-0500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | P2543-R01-Oct24..1.PM.4 NOC Register | Final Issue for Design/ Construction-Overall Pipeline Route Map - 4" | Final Issue for Design/ Construction-NOC Register | HE-PL-0290 | HC-GN-0290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.2 Planning Package | P2543-R01-Oct24..1.PM.2 Planning Package | Obtain Company Approval-Planning Package | Final Issue for Design/ Construction-Planning Package | HC-GN-0040 | HC-GN-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.17.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.17.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Leak Detection System | Manufacturing & Assembly of Leak Detection System | HM-ME-0210 | HM-ME-0220 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.1.16.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.16.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Junction Boxes | Ready for Dispatch of Junction Boxes | HM-ME-1650 | HM-ME-1660 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.25.16.1 Ordering | P2543-R01-Oct24..PR.26.1.16.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Junction Boxes | Vendor Document Review of Junction Boxes | HP-ME-0830 | HM-ME-1620 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.1.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Distribution Transformer | Manufacturing & Assembly of Distribution Transformer | HM-ME-0920 | HM-ME-0930 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.1.14.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.14.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Access Switch, Fiber Optic Patch Panel and Media Converter | Factory Acceptance Test of Access Switch, Fiber Optic Patch Panel and Media Converter | HM-ME-1330 | HM-ME-1340 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.LL.5.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.5.3 Delivery & receipt at Site | Ready for Dispatch of Active/ Passive Cooled Shelter | Transportation/ Custom Clearance/ Delivery at site of Active/ Passive Cooled Shelter | HM-ME-1160 | HM-ME-1180 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.5.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.5.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of Active/ Passive Cooled Shelter | Packaging & Final Inspection-Active/ Passive Cooled Shelter | HM-ME-1140 | HM-ME-1150 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.5.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.5.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Active/ Passive Cooled Shelter | Factory Acceptance Test of Active/ Passive Cooled Shelter | HM-ME-1130 | HM-ME-1140 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.1.2.25.7.1 Ordering | P2543-R01-Oct24..PR.26.1.7.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Power Distribution Boards | Vendor Document Review of Power Distribution Boards | HP-ME-0430 | HM-ME-0820 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.1.7.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.7.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of Power Distribution Boards | Packaging & Final Inspection for Power Distribution Boards | HM-ME-0840 | HM-ME-0850 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.8.1 Ordering | P2543-R01-Oct24..PR.26.LL.8.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for AC UPS | Vendor Document Review of AC UPS | HP-ME-0380 | HM-ME-0720 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.9.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | Ready for Dispatch of MOV | Transportation/ Custom Clearance/ Delivery at site of MOV (Lot 2) | HM-ME-0650 | HM-ME-0670 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.10.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-ROV/ GOV | Ready for Dispatch of ROV/ GOV | HM-ME-0540 | HM-ME-0550 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Pig Launchers & Receivers | Manufacturing & Assembly of Pig Launchers & Receivers | HM-ME-0410 | HM-ME-0420 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Pig Launchers & Receivers | Ready for Dispatch of Pig Launchers & Receivers | HM-ME-0440 | HM-ME-0450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Pressure Reduction Skid | Factory Acceptance Test of Pressure Reduction Skid | HM-ME-0120 | HM-ME-0130 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.LL.21.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.21.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Pressure Reduction Skid | Receipt at site and inspection of Pressure Reduction Skid | HM-ME-0170 | HM-ME-0180 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.18.2 Manufacturing & Ready for Dispatch | Testing and Inspection of Gas Detectors | Packaging & Final Inspection-Gas Detectors | HM-ME-1440 | HM-ME-1450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.LL.18.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - CCTV Systems | Vendor Document Review of Gas Detectors | ML1028-C20 | HM-ME-1420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.18.1 Ordering | P2543-R01-Oct24..PR.26.LL.18.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Gas Detectors | Vendor Document Review of Gas Detectors | HP-ME-0730 | HM-ME-1420 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.11.3 Delivery & receipt at Site | Ready for Dispatch of Filter Package | Transportation/ Custom Clearance/ Delivery at site of Filter Package | HM-ME-0350 | HM-ME-0370 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.8.1 Ordering | P2543-R01-Oct24..PR.BK.8.2 Manufacturing & Ready for Dispatch | 1st Instrumentation Bulk material MTO | 1st Instrumentation Bulk material MTO | HP-BK-0460 | HM-IC-0010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.7.1 Ordering | P2543-R01-Oct24..PR.BK.7.2 Manufacturing & Ready for Dispatch | 1st Electrical Bulk material MTO | 1st Electrical Bulk material MTO | HP-BK-0420 | HM-EL-0490 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.7.1 Ordering | P2543-R01-Oct24..PR.BK.7.2 Manufacturing & Ready for Dispatch | Final Electrical Bulk material MTO | Final Electrical Bulk material MTO | HP-BK-0430 | HM-EL-0500 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.6.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.6.3 Delivery & Receipt at site | Final Pipeline Bulk material MTO | Final Pipeline Bulk material MTO | HM-PL-0860 | HM-PL-0890 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.6.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.6.3 Delivery & Receipt at site | 1st Pipeline Bulk material MTO | 1st Pipeline Bulk material MTO | HM-PL-0850 | HM-PL-0880 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | 1st Piping Bulk material MTO | 1st Piping Bulk material MTO | HM-PI-0010 | HM-PI-0040 | FF | Not Started | Not Started | 21
P2543-R01-Oct24..1.1.BK.4.1 Ordering | P2543-R01-Oct24..PR.BK.4.2 Manufacturing & Ready for Dispatch | 1st Piping Bulk material MTO | 1st Piping Bulk material MTO | HP-BK-0340 | HM-PI-0010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | Final Structural Bulk material MTO | Final Structural Bulk material MTO | HM-CS-0090 | HM-CS-0120 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..PR.BK.11.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | 1st Civil Bulk material MTO | 1st Civil Bulk material MTO | HM-CS-0010 | HM-CS-0040 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.BK.13.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.13.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Cable Trays | Factory Acceptance Test of Cable Trays | HM-EL-0220 | HM-EL-0230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.2.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Pigging & Split Tee | Manufacturing & Assembly of Pigging & Split Tee | HM-PL-0770 | HM-PL-0780 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.1.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.3.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Isolating Joints | Manufacturing & Assembly of Isolating Joints | HM-PL-0670 | HM-PL-0680 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Pig Signaler (Lot 1) | Receipt at site and inspection of Pig Signaler (Lot 1) | HM-PL-0520 | HM-PL-0530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.1.19.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - Isolation Joints | Vendor Document Review of Pig Signaler | ML1041-C03 | HM-PL-0460 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.20.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.20.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of CP System | Factory Acceptance Test of CP System | HM-PL-0360 | HM-PL-0370 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.LL.20.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - CP System | Manufacturing & Assembly of CP System | ML1038-C10 | HM-PL-0360 | FF | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.24.1 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.24.2 Delivery & receipt at Site | Ready for Dispatch of Hot Tapping Material | Transportation/ Custom Clearance/ Delivery at site of Hot Tapping Material | HM-PL-0290 | HM-PL-0310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Ball/ Globe/ Check/ Plug Valves | Manufacturing & Assembly of Ball/ Globe/ Check/ Plug Valves | HM-PL-0150 | HM-PL-0160 | FS | Completed | In Progress | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - Manual Ball Valves | Vendor Document Review of Ball/ Globe/ Check/ Plug Valves | ML1043-C14 | HM-PL-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.4.AB.2 Final Documentation | P2543-R01-Oct24..ML.4 Commissioning and PAC | Quality Dossier | Achieve (PAC-2) for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | CAB-5300 | ML2049-F06 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Complete Pipeline welding - 52" Sales Gas Pipeline - 75% Welding | Complete Pipeline welding - 52" Sales Gas Pipeline - 100% Welding | ML1709-E16 | ML1719-E17 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Receive at Site - Manual Valves | HM-PL-0220 | ML1539-D21 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Gas Detectors (Lot 1) | Receive at Site - F & G System | HM-ME-1490 | ML2089-D16 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.4.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Issue Purchase Order (Final) - CCTV Systems | HP-ME-0630 | ML1028-C20 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.9.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for MOV | Issue Purchase Order (Final) - RTUs | HP-ME-0330 | ML1349-C19 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.22.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Custody Metering Skid | Issue Purchase Order (Final) - Sales Gas Metering Skids | HP-ME-0030 | ML1259-C09 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.3.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Isolating Joints | Issue Purchase Order (Final) - Anchor Flanges | HP-ME-1240 | ML1249-C06 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.2.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Pigging & Split Tee | Issue Purchase Order (Final) - Barred Tee | HP-ME-1290 | ML1239-C04 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-1310 | ML1034-B25 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | HE-TL-0230 | ML1033-B22 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | HE-TL-0290 | ML1033-B22 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Issue MRs for All E&I Equipment & Packages (Final Issue) | HE-EL-1010 | ML1027-B17 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A1311 Material Requisitions for MOV | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Material Requisitions for MOV | Issue MRs for All E&I Equipment & Packages (Final Issue) | HE-IC-1610 | ML1027-B17 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue for HAZOP Studies- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | HE-PI-0340 | ML1012-B06 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Topographical Survey Report (Overall) | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 52" Pipeline(IFC) | HE-TS-0050 | ML1009-B04 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Geotechnical Survey Report (Overall) | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 56" Pipeline(IFC) | HE-GS-0050 | ML1008-B03 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Topographical Survey Report (Overall) | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 56" Pipeline(IFC) | HE-TS-0050 | ML1008-B03 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Piping GA Drawings for 591-BVS-01 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-PI-0820 | ML1219-B19 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..ML.EN Detail Engineering | 90% Model Review | 90% Model Review | HE-PI-0170 | ML2079-B13 | FF | Completed | Completed | 0
P2543-R01-Oct24..ML.4 Commissioning and PAC | P2543-R01-Oct24..ML Milestones | Commission New pipeline system - 56" Sales Gas Pipeline | Achieve PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | ML1999-F01 | ML1040 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | Achieve PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | ML1020 | ML1040 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Drying & Purging of all facilities including Pipeline & Block Valve Stations- 56" Sales Gas Pipeline | Project Finish | ML1649-E10 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Pipeline welding - 4" Nitrogen Pipeline | Project Finish | ML1909-E36 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | Project Finish | ML1749-E20 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Mobilization of Automatic Welding Machines at site | Project Finish | ML1559-E01 | ML1060 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Pipeline welding - 52" Sales Gas Pipeline - 75% Welding | Project Finish | ML1709-E16 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB As-Built & Final Documentation | P2543-R01-Oct24..ML Milestones | Demolitionbilization | Project Finish | A3980 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 01 to BVS-02 | Project Finish | ML1769-E22 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Hydrotesting - 52" Sales Gas Pipeline -Launcher to BVS-01 | Project Finish | ML1759-E21 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Site Grading & ROW along the Pipeline - 4" Water line | Project Finish | ML1869-E32 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete foundations for Launchers and Receiver- 52" Sales Gas Pipeline | Project Finish | ML1739-E19 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Receive at Site - Leak Detection System | Project Finish | ML1053-D23 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.2.6 Project Risk Review Register | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Final Issue for Design/ Construction-Project Risk Review Register | General | HE-RR-0050 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of Pig Launchers & Receivers (52" Line) | Vendor Documents Package | HM-ME-0480 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Instrumentation & Control | Vendor Documents Package | CAB-4460 | CAB-5310 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..1.EN.1.9.20 MR for Isolating Joints | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-MR for Isolating Joints | Pipeline | HE-PL-1910 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.10.24 TBE for Pigging Tees | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Pigging Tees | Pipeline | HE-PL-2190 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline Stress Analysis Report | Pipeline | HE-PL-2850 | CAB-4480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Instrumentation & Control | HE-IC-2570 | CAB-4460 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | Instrumentation & Control | ML1030 | CAB-4460 | FF | Not Started | Not Started | 18
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Instrumentation & Control | HE-IC-0950 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- Addendum to DGs | Instrumentation & Control | HE-IC-0010 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.16 Electrical MTO | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Electrical 3rd MTO | Electrical | HE-EL-1850 | CAB-4450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | Electrical | ML1012-B06 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.26 TBE for Power & Control Cables | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Power & Control Cables | Electrical | HE-EL-1550 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Electrical | ML1179-B11 | CAB-4450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue MRs for All E&I Equipment & Packages (Final Issue) | Electrical | ML1027-B17 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Earthing Layout | Electrical | HE-EL-1670 | CAB-4450 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.28 TBE for Distribution Boards | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Distribution Boards | Electrical | HE-EL-1430 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.8 TBE for Solar Panels | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Solar Panels | Electrical | HE-EL-1310 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Electrical | HE-EL-1010 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | Electrical | HE-EL-0770 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Tie-In Schedule | Piping | HE-PR-0290 | CAB-4440 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Piping | ML1015-B08 | CAB-4440 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Datasheet for Ball valves | Piping | HE-PI-0940 | CAB-4440 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Mechanical | ML1219-B19 | CAB-4430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction- Addendum to DGS | Mechanical | HE-ME-0050 | CAB-4430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Solar panel foundation details | Civil & Structural | HE-CS-0890 | CAB-4420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Misc. supports | Civil & Structural | HE-CS-1490 | CAB-4420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Design Calculation for Typical Skid Foundations | Civil & Structural | HE-CS-0710 | CAB-4420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Typical trench detail drawing | Civil & Structural | HE-CS-0170 | CAB-4420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Civil & Structural | HE-CS-0350 | CAB-4420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TYPICAL GA AND RC DETAILS OF IMPACT WALL | Civil & Structural | HE-CS-1250 | CAB-4420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Civil & Structural | HE-CS-1430 | CAB-4420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-HAZID / ENVID / OHID Procedure | HSE | HE-HS-0170 | CAB-4410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Project HSE Philosophy | HSE | HE-HS-0110 | CAB-4410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-HSEIA Study Report | HSE | HE-HS-0530 | CAB-4410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-HAZID/ ENVID/ OHID Report | HSE | HE-HS-0590 | CAB-4410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.17 PHSER Close Out Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-PHSER Close Out Report | HSE | HE-HS-0950 | CAB-4410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..4.4.2 Commissioning | Approval of Commissioning Dossiers | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | CCM-PM4500 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Re-Issue for Approval-Pre-commissioning and Commissioning Plan | Obtain Company Approval-Pre-commissioning and Commissioning Plan | C-COM-820 | C-COM-830 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Final Issue for Design/ Construction-Relief, Vent and Blowdown philosophy | Issue ICR-Pre-commissioning and Commissioning Plan | HE-PR-0830 | C-COM-800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Commercial Clarifications & Placement of PO - Modification of Existing DCS | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HS-GN-0470 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Re-Issue for Approval-Construction Procedures / Method Statements / ITPs | HE-PR-0890 | C-COM-770 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Actuator Datasheet for GOV & ROV | Issue ICR-Construction Procedures / Method Statements / ITPs | HE-IC-1130 | C-COM-750 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | P2543-R01-Oct24..1.1.BK.8.1 Ordering | Instrument 1st MTO | 1st Instrumentation Bulk material MTO | HE-IC-2590 | HP-BK-0460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | P2543-R01-Oct24..1.1.BK.6.1 Ordering | Issue ICR - Pipeline MTO - 56" | 1st Pipeline Bulk material MTO | HE-PL-3230 | HP-BK-0380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..1.1.BK.4.1 Ordering | Piping MTO - Final | Final Piping Bulk material MTO | HE-PI-1300 | HP-BK-0350 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.42 Civil MTO | P2543-R01-Oct24..1.1.BK.11.1 Ordering | Issued - Civil MTO 1 | 1st Civil Bulk material MTO | HE-CS-1510 | HP-BK-0260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.19 MR for Pipeline Pigging Tees | P2543-R01-Oct24..1.1.1.2.1 Ordering | Final Issue for Design/ Construction-MR for Pipeline Pigging Tees | Commercial Clarifications & Placement of PO for Pigging & Split Tee | HE-PL-1850 | HP-ME-1290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.19.1 Ordering | P2543-R01-Oct24..1.1.1.19.1 Ordering | Prepare TBE and Company approval for Pig Signaler | Commercial Clarifications & Placement of PO for Pig Signaler | HP-ME-1130 | HP-ME-1140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.18 Material Requisition for UPS System | P2543-R01-Oct24..1.1.2.LL.8.1 Ordering | Receive Company Comments-Material Requisition for UPS System | RFQ, Receipt of Bid for AC UPS | HE-EL-0920 | HP-ME-0360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.18 Material Requisition for UPS System | P2543-R01-Oct24..1.1.2.LL.8.1 Ordering | Issue ICR-Material Requisition for UPS System | RFQ, Receipt of Bid for AC UPS | HE-EL-0910 | HP-ME-0360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.9.1 Ordering | P2543-R01-Oct24..1.1.2.LL.9.1 Ordering | RFQ, Receipt of Bid for MOV | Prepare TBE and Company approval for MOV | HP-ME-0310 | HP-ME-0320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A1311 Material Requisitions for MOV | P2543-R01-Oct24..1.1.2.LL.9.1 Ordering | Issue ICR- Material Requisitions for MOV | RFQ, Receipt of Bid for MOV | HE-IC-1570 | HP-ME-0310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.10.1 Ordering | P2543-R01-Oct24..1.1.2.LL.10.1 Ordering | Prepare TBE and Company approval for ROV/ GOV | Commercial Clarifications & Placement of PO for ROV/ GOV | HP-ME-0270 | HP-ME-0280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.21.1 Ordering | P2543-R01-Oct24..1.1.2.LL.21.1 Ordering | RFQ, Receipt of Bid for Pressure Reduction Skid | Prepare TBE and Company approval for Pressure Reduction Skid | HP-ME-0060 | HP-ME-0070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.2.1 Ordering | P2543-R01-Oct24..1.1.2.25.2.1 Ordering | Prepare TBE and Company approval for Fire Suppression System | Commercial Clarifications & Placement of PO for Fire Suppression System | HP-ME-0920 | HP-ME-0930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.16.1 Ordering | P2543-R01-Oct24..1.1.2.25.16.1 Ordering | RFQ, Receipt of Bid for Junction Boxes | Prepare TBE and Company approval for Junction Boxes | HP-ME-0810 | HP-ME-0820 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.7 Material Requisitions for Junction Boxes | P2543-R01-Oct24..1.1.2.25.16.1 Ordering | Issue ICR- Material Requisitions for Junction Boxes | RFQ, Receipt of Bid for Junction Boxes | HE-IC-1990 | HP-ME-0810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.3.1 Ordering | P2543-R01-Oct24..1.2.12.13 E&I Works | RFQ, Receipt of Bid for HVAC Equipment | E&I Works RFQ & Quotation Receipt | HP-ME-0860 | HS-CN-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.10 Earthworks | P2543-R01-Oct24..1.2.12.10 Earthworks | Earthworks RFQ & Quotation Receipt | Earthworks Complete Evaluation (Internal) | HS-CN-0460 | HS-CN-0480 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | Project Kick off Meeting | FOC Splicing / Termination RFQ & Quotation Receipt | ML1002 | HS-CN-0260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | Testing & Precommissioning RFQ & Quotation Receipt | Testing & Precommissioning Complete Evaluation (Internal) | HS-CN-0110 | HS-CN-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | P2543-R01-Oct24..1.2.13.9 HSE Studies | Issue ICR-HSE Philosophy | Prepare/Issue Scope of Work - HSE Studies | HE-HS-0070 | HS-GN-0070 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.11 Cathodic Protection Work | P2543-R01-Oct24..1.2.13.11 Cathodic Protection Work | Prepare/Issue Scope of Work - Cathodic Protection Work | Receive Bids - Cathodic Protection Work | HS-GN-0490 | HS-GN-0500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | Review Company Comments - Passive cooled shelter foundation GA and details | Re-Issue for Approval - Passive cooled shelter foundation GA and details | HE-CS-1280 | HE-CS-1290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | Obtain Company Approval - Impact Wall GA and RC (type) details | Final Issue for Design/ Construction-TYPICAL GA AND RC DETAILS OF IMPACT WALL | HE-CS-1240 | HE-CS-1250 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | Obtain Company Approval - Calculations for Pipe supports | Final Issue for Design/ Construction-Design Calculation for Typical Pipe supports | HE-CS-1120 | HE-CS-1130 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | Re-Issue after incorporating HAZOP /Review Comments - 52" Pipeline SWEIHAN CRS | Issued for Review - Typical Detailed Drawing - Jib Crane Foundation | HE-PI-0420 | HE-CS-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | Review Company Comments - Lighting pole foundation details | Re-Issue for Approval - Lighting pole foundation details | HE-CS-0980 | HE-CS-0990 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.33 Filter Foundation GA and Details | P2543-R01-Oct24..1.EN.8.33 Filter Foundation GA and Details | Review Company Comments - Typical Spill Pit General Arrangement And RC (type) Details | Re-Issue for Approval - Typical Spill Pit General Arrangement And RC (type) Details | HE-CS-0920 | HE-CS-0930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | Re-Issue for Approval - Design Cal. for Typical Skid Foundations | Obtain Company Approval - Design Cal. for Typical Skid Foundations | HE-CS-0690 | HE-CS-0700 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.28 Calculation for Pig launcher and receiver foundations | P2543-R01-Oct24..1.EN.8.28 Calculation for Pig launcher and receiver foundations | Re-Issue for Approval - Calculation for Pig launcher and receiver foundations | Obtain Company Approval - Calculation for Pig launcher and receiver foundations | HE-CS-0570 | HE-CS-0580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.8.11 Civil UG layout | Issue ICR-Topographical Survey Report (Overall) | Issued for Review - Civil UG layout | HE-TS-0010 | HE-CS-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | Issued for Review - Typical duct bank detail drawing | Issued for Review - Typical Road and paving detail drawing | HE-CS-0190 | HE-CS-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | Re-Issue for Approval - Addendum to DGs | Obtain Company Approval - Addendum to DGs | HE-CS-0030 | HE-CS-0040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction-Typical Structural Steel and Foundation details for pipe support | Issued - Civil MTO 2 | HE-CS-1370 | HE-CS-1550 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction - Pressure Reduction Skid and Leak Detection Drawings | Issued - Civil MTO 2 | HE-CS-0770 | HE-CS-1550 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | P2543-R01-Oct24..1.EN.8.41 Misc. supports | Issued for Review - Typical Structural Steel and Foundation details for pipe support | Issued for Review - Misc. supports and civil/ structural details | HE-CS-1330 | HE-CS-1450 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.11.1 Ordering | P2543-R01-Oct24..1.EN.5.3.9 TBE for Sals Gas CRS Filters | RFQ, Receipt of Bid for Filter Package | Issue ICR-TBEs for Sales Gas CRS Filters | HP-ME-0160 | HE-ME-0190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | Re-Issue for Approval-Datasheet for Sales Gas CRS Filters | Re-Issue for Approval-Material Requisitions for Sales Gas CRS Filters | HE-ME-0090 | HE-ME-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | Re-Issue for Approval-Datasheet for Sales Gas CRS Filters | Obtain Company Approval-Datasheet for Sales Gas CRS Filters | HE-ME-0090 | HE-ME-0100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Issue ICR- Plot plan - BVS | Receive Company Comments- Plot plan - BVS | HE-PI-0530 | HE-PI-0540 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Final Issue for Design/ Construction-Vent and Depressurization Report (for new facilities) | Final Issue for Design/ Construction-Overall Plot Plan- 4" N2 Source Pipeline | HE-PR-1010 | HE-PI-0510 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Final Issue for Design/ Construction-Topographical Survey Report (Overall) | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | HE-TS-0050 | HE-PI-0440 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction-Vent and Depressurization Report (for new facilities) | Final Issue for Design/ Construction-Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-1010 | HE-PI-0370 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | Receive Company Comments-Pipe Wall Thickness Calculation | Re-Issue for Approval-Pipe Wall Thickness Calculation | HE-PI-0210 | HE-PI-0220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | Receive Company Comments-Piping Isometrics | Re-Issue for Approval-Piping Isometrics | HE-PI-1210 | HE-PI-1220 | FF | Completed | Completed | 5
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | 30% Model Review | Issue ICR-Piping Stress Analysis & Report | ML2059-B05 | HE-PI-1140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | 30% Model Review | Issue ICR-Piping Stress Analysis & Report | HE-PI-0130 | HE-PI-1140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.16 Critical line List | P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | Re-Issue for Approval-Critical line List | Re-Issue for Approval-Piping Stress Analysis & Report | HE-PI-0282 | HE-PI-1160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | Issue ICR- Datasheet for Plug Valves | Issue ICR-MR for Ball valves/ Plug Valves | HE-PI-0960 | HE-PI-1020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | Issue ICR- P&ID's | Issue ICR- Datasheet for Plug Valves | HE-PR-0110 | HE-PI-0960 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | Issue ICR- P&ID's | Issue ICR-Data sheet for Ball Valves | HE-PR-0110 | HE-PI-0900 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | Re-Issue after incorporating HAZOP / Review Comments- Plot plan - BVS | Issue ICR-Piping GA for 591-BVS-01 to 06 | HE-PI-0560 | HE-PI-0840 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | Final Issue for Design/ Construction-Piping Stress Analysis & Report | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | HE-PI-1180 | HE-PI-0880 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | Obtain Company Approval-Piping GA Drawings for 591-BVS-01 | Final Issue for Design/ Construction-Piping GA Drawings for 591-BVS-01 | HE-PI-0810 | HE-PI-0820 | FS | Completed | In Progress | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.7.10 3D Model | 90% Model Review | 90% Model Review Report | ML2079-B13 | HE-PI-0180 | FF | Completed | Completed | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.7.10 3D Model | 60% Model Review | 90% Model Review | ML2069-B09 | HE-PI-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | Receive Company Comments- HAZOP reviews Report for all areas | Re-Issue for Approval- HAZOP reviews Report for all areas | HE-HS-0680 | HE-HS-0690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | Obtain Company Approval- HAZOP reviews Report for all areas | Final Issue for Design/ Construction-HAZOP Review Report | HE-HS-0700 | HE-HS-0710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | HAZID /ENVID/OHID/ PHSER Workshop | Issue ICR-HAZID/ ENVID/ OHID Report | HE-WS-0020 | HE-HS-0550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.16 Datasheets for fire fighting and safety equipment | P2543-R01-Oct24..1.EN.4.16 Datasheets for fire fighting and safety equipment | Re-Issue for Approval-Data Sheets for Fire Fighting & Safety Eqpt | Obtain Company Approval-Data Sheets for Fire Fighting & Safety Eqpt | HE-HS-0450 | HE-HS-0460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | P2543-R01-Oct24..1.EN.4.16 Datasheets for fire fighting and safety equipment | Issue ICR- Fire Fighting & Safety Eqpt. Layout | Issue ICR-Data Sheets for Fire Fighting & Safety Eqpt | HE-HS-0370 | HE-HS-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.9 HSE Studies | P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | Place LOA/FOA - HSE Studies | Issue ICR-HAZOP Procedure | HS-GN-0110 | HE-HS-0190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | Obtain Company Approval-HAZOP Procedure | Final Issue for Design/ Construction-HAZOP Procedure | HE-HS-0220 | HE-HS-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | Issue ICR-HSE Philosophy | Receive Company Comments-HSE Philosophy | HE-HS-0070 | HE-HS-0080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.20 Material Requisition for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | Final Issue for Design/ Construction-Material Requisition for fire fighting and safety equipment | Final Issue for Design/ Construction-TBE for fire fighting and safety equipment | HE-HS-1130 | HE-HS-1190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.20 Material Requisition for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.EN.4.20 Material Requisition for Fire Fighting and Safety Equipment | Obtain Company Approval-Material Requisition for Fire Fighting & Safety Eqpt | Final Issue for Design/ Construction-Material Requisition for fire fighting and safety equipment | HE-HS-1120 | HE-HS-1130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | Final Issue for Design/ Construction-HAZID/ ENVID/ OHID Report | Final Issue for Design/ Construction-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-0590 | HE-HS-1070 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.4.12 PHSER Report | P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | Issue ICR-PHSER Report | Issue ICR-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-0850 | HE-HS-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Issue ICR-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Receive Company Comments-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-HS-0970 | HE-HS-0980 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.12 PHSER Report | P2543-R01-Oct24..1.EN.4.17 PHSER Close Out Report | Issue ICR-PHSER Report | Issue ICR- PHSER Close Out Report | HE-HS-0850 | HE-HS-0910 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.4.11 QRA Report | P2543-R01-Oct24..1.EN.4.11 QRA Report | Re-Issue for Approval-QRA Report | Obtain Company Approval-QRA Report | HE-HS-0810 | HE-HS-0820 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.11 QRA Report | P2543-R01-Oct24..1.EN.4.11 QRA Report | Receive Company Comments-QRA Report | Re-Issue for Approval-QRA Report | HE-HS-0800 | HE-HS-0810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.11 QRA Report | P2543-R01-Oct24..1.EN.4.11 QRA Report | Issue ICR-QRA Report | Receive Company Comments-QRA Report | HE-HS-0790 | HE-HS-0800 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.21 HAZOP close out report | P2543-R01-Oct24..1.EN.4.21 HAZOP close out report | Issue ICR- HAZOP Close Out Report | Receive Company Comments- HAZOP Close Out Report | HE-HS-0730 | HE-HS-0740 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | Receive Company Comments - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Re-Issue for Approval - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | HE-TL-0080 | HE-TL-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | Issue ICR - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Receive Company Comments - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | HE-TL-0070 | HE-TL-0080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Receive Company Comments- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0490 | HE-TL-0500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Issue ICR- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0190 | HE-TL-0490 | FS | Completed | Completed | 20
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Re-Issue for Approval - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Re-Issue for Approval- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0090 | HE-TL-0510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | Receive Company Comments- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Re-Issue for Approval- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0200 | HE-TL-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Issue ICR- Overall Telecom Block Diagram | Receive Company Comments- Overall Telecom Block Diagram | HE-TL-0310 | HE-TL-0320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..1.EN.10.2 Telecom MTO | Re-Issue for Approval-Telecom Equipment Layout | Telecom 2nd MTO | HE-TL-0750 | HE-TL-0870 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Issue ICR- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Issue ICR- Telecom Cable Schedule | HE-TL-0250 | HE-TL-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Issue ICR- Overall Telecom Block Diagram | Issue ICR- Telecom Cable Schedule | HE-TL-0310 | HE-TL-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | Receive Company Comments-Telecom Location and Cable Routing layout | Re-Issue for Approval-Telecom Location and Cable Routing layout | HE-TL-0680 | HE-TL-0690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Re-Issue for Approval- FOC Block diagram (Telecom) | Re-Issue for Approval- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0450 | HE-TL-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.43 Material Requisition for Pig Signaler | P2543-R01-Oct24..1.EN.6.11.43 Material Requisition for Pig Signaler | Receive Company Comments- Material Requisition for Pig Signaler | Re-Issue for Approval- Material Requisition for Pig Signaler | HE-PL-1940 | HE-PL-1950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.5 Hot Tapping | P2543-R01-Oct24..1.EN.1.60.14 Data Sheet - Anchor Flange | Commercial Clarifications & Placement of PO- Hot Tapping | Re-Issue for Approval - Data Sheet - Anchor Flange (If Required) | HS-GN-0230 | HE-PL-1530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.12 Data Sheet - Pipeline Pigging Tees | P2543-R01-Oct24..1.EN.1.60.12 Data Sheet - Pipeline Pigging Tees | Obtain Company Approval - Data Sheet - Pigging Tees | Final Issue for Design/ Construction-Data Sheet - Pipeline Pigging Tees | HE-PL-1480 | HE-PL-1490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.10 Data Sheet - Hot Induction Bends | P2543-R01-Oct24..1.EN.1.60.11 Data Sheet - Pipeline Isolating Joints | Issue ICR - Data Sheet - Hot Induction Bends | Issue ICR - Data Sheet - Isolating joints | HE-PL-1270 | HE-PL-1390 | FS | Completed | Completed | 15
P2543-R01-Oct24..1.EN.1.60.9 Data Sheet - Linepipes | P2543-R01-Oct24..1.EN.1.60.10 Data Sheet - Hot Induction Bends | Issue ICR - Data Sheet - Line pipes | Issue ICR - Data Sheet - Hot Induction Bends | HE-PL-1150 | HE-PL-1270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.9 Data Sheet - Linepipes | P2543-R01-Oct24..1.EN.1.60.9 Data Sheet - Linepipes | Issue ICR - Data Sheet - Line pipes | Receive Company Comments - Data Sheet - Line pipes | HE-PL-1150 | HE-PL-1160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.4 Pipeline Road and Railway Crossing Calculation Report | P2543-R01-Oct24..1.EN.1.4 Pipeline Road and Railway Crossing Calculation Report | Obtain Company Approval - Pipeline Road Crossing Calculation Report | Final Issue for Design/ Construction-Pipeline Road and Railway Crossing Calculation Report | HE-PL-0700 | HE-PL-0710 | FF | Completed | In Progress | 10
P2543-R01-Oct24..1.EN.1.4 Pipeline Road and Railway Crossing Calculation Report | P2543-R01-Oct24..1.EN.1.4 Pipeline Road and Railway Crossing Calculation Report | Re-Issue for Approval - Pipeline Road Crossing Calculation Report | Obtain Company Approval - Pipeline Road Crossing Calculation Report | HE-PL-0690 | HE-PL-0700 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.3 Pipeline Upheavl Calculation | P2543-R01-Oct24..1.EN.1.3 Pipeline Upheavl Calculation | Receive Company Comments - Pipeline Upheaval Calculation | Re-Issue for Approval - Pipeline Upheaval Calculation | HE-PL-0620 | HE-PL-0630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.40 Specification - Split Tee | P2543-R01-Oct24..1.EN.1.40 Specification - Split Tee | Obtain Company Approval - Specification - Split Tee | Final Issue for Design/ Construction-Specification - Split Tee | HE-PL-0460 | HE-PL-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.27 Pipeline Typical Drawings | P2543-R01-Oct24..1.EN.1.27 Pipeline Typical Drawings | Receive Company Comments - Pipeline Typical Drawings | Re-Issue for Approval - Pipeline Typical Drawings | HE-PL-0380 | HE-PL-0390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | Re-Issue for Approval - Overall Pipeline Route Map - 56" | Obtain Company Approval - Overall Pipeline Route Map - 56" | HE-PL-0150 | HE-PL-0160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.44 Detailed crossing drawings-4" | P2543-R01-Oct24..1.EN.1.44 Detailed crossing drawings-4" | Receive Company Comments - Detailed crossing drawings-4" | Re-Issue for Approval - Detailed crossing drawings-4" | HE-PL-3120 | HE-PL-3130 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.38 Crossing Schedule-52" | P2543-R01-Oct24..1.EN.1.38 Crossing Schedule-52" | Issue ICR - Crossing Schedule-52" | Receive Company Comments - Crossing Schedule-52" | HE-PL-3050 | HE-PL-3060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..1.EN.1.38 Crossing Schedule-52" | Issue ICR - Pipeline Alignment Sheets-52" | Issue ICR - Crossing Schedule-52" | HE-PL-2450 | HE-PL-3050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | Receive Company Comments - Detailed crossing drawings-52" | Re-Issue for Approval - Detailed crossing drawings-52" | HE-PL-3000 | HE-PL-3010 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | Re-Issue for Approval - Crossing Schedule - 56" | Obtain Company Approval - Crossing Schedule - 56" | HE-PL-2950 | HE-PL-2960 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | Issue ICR - Crossing Schedule - 56" | Receive Company Comments - Crossing Schedule - 56" | HE-PL-2930 | HE-PL-2940 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | Issue ICR - Pipeline Alignment Sheets -56" | Issue ICR - Detailed crossing drawings - 56" | HE-PL-2390 | HE-PL-2870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..1.EN.1.1 Pipeline Route Verification and Selection Report | Issue ICR - Pipeline Alignment Sheets -56" | Issue ICR - Pipeline Route Verification and Selection Report | HE-PL-2390 | HE-PL-2750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..1.EN.1.1 Pipeline Route Verification and Selection Report | Issue ICR - Pipeline Alignment Sheets-52" | Issue ICR - Pipeline Route Verification and Selection Report | HE-PL-2450 | HE-PL-2750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | Obtain Company Approval - Pipeline Station Approach drawing -52" | Final Issue for Design/ Construction-Pipeline Station approach drawing-52" | HE-PL-2660 | HE-PL-2670 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | Re-Issue for Approval - Pipeline Station Approach drawing -52" | Obtain Company Approval - Pipeline Station Approach drawing -52" | HE-PL-2650 | HE-PL-2660 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Final Issue for Design/ Construction-Pipeline Station approach drawing - 56" | HE-PI-0440 | HE-PL-2610 | FF | In Progress | In Progress | 10
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | Final Issue for Design/ Construction-Topographical Survey Report (Overall) | Final Issue for Design/ Construction-Pipeline Station approach drawing - 56" | HE-TS-0050 | HE-PL-2610 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | Issue ICR-Topographical Survey Report (Overall) | Issue ICR - Pipeline Station Approach drawing -56" | HE-TS-0010 | HE-PL-2570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR - Pipeline Station Approach drawing -56" | HE-PI-0320 | HE-PL-2570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | Obtain Company Approval - Pipeline Alignment Sheets-4" | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | HE-PL-2540 | HE-PL-2550 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.10.23 TBE for Hot Induction Bends | P2543-R01-Oct24..1.EN.1.10.23 TBE for Hot Induction Bends | Re-Issue for Approval - TBE for Hot Induction Bends | Obtain Company Approval - TBE for Hot Induction Bends | HE-PL-2110 | HE-PL-2120 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.23 TBE for Hot Induction Bends | P2543-R01-Oct24..1.EN.1.10.23 TBE for Hot Induction Bends | Issue ICR - TBE for Hot Induction Bends | Receive Company Comments - TBE for Hot Induction Bends | HE-PL-2090 | HE-PL-2100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A331 TBE for Leak Detection System | P2543-R01-Oct24..1.EN.6.2.A331 TBE for Leak Detection System | Obtain Company Approval-TBE for Leak Detection System | Final Issue for Design/ Construction-TBE for Leak Detection System | HE-IC-2260 | HE-IC-2270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Obtain Company Approval-Instrument Trench Layout | Final Issue for Design/ Construction-Instrument Trench Layout | HE-IC-1000 | HE-IC-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Receive Company Comments- Instrument Cable Block Diagram | Issue ICR-Instrument Trench Layout | HE-IC-0800 | HE-IC-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.7 Material Requisitions for Junction Boxes | P2543-R01-Oct24..1.EN.6.11.7 Material Requisitions for Junction Boxes | Receive Company Comments- Material Requisitions for Junction Boxes | Re-Issue for Approval- Material Requisitions for Junction Boxes | HE-IC-2000 | HE-IC-2010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A2 Instrument Index | Re-Issue for Approval-Instrument index -Update | Obtain Company Approval-Instrument index -Update | HE-IC-0510 | HE-IC-0520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | Re-Issue for Approval- Specifications for PRS (Pressure Reduction System) | Obtain Company Approval- Specifications for PRS (Pressure Reduction System) | HE-IC-0090 | HE-IC-0100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | Re-Issue for Approval- Addendum to DGs | Obtain Company Approval- Addendum to DGs | HE-IC-0030 | HE-IC-0040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Final Issue for Design/ Construction-Typical Installation Drawings | Instrument 3rd MTO | HE-IC-0710 | HE-IC-2630 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Issue ICR- Instrument Cable Block Diagram | Issue ICR- Instrument location and Cable Routing Drawings | HE-IC-0790 | HE-IC-2530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.5 TBE for ROV/ GOV | P2543-R01-Oct24..1.EN.6.2.5 TBE for ROV/ GOV | Obtain Company Approval- TBE for ROV/ GOV | Final Issue for Design/ Construction-TBE for ROV/ GOV | HE-IC-2320 | HE-IC-2330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..1.EN.6.11.9 Material Requisitions for Fire & Gas Detectors | Issue ICR- Datasheets for F&G Devices | Issue ICR- Material Requisitions for Gas Detectors | HE-IC-1510 | HE-IC-1870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.9 Material Requisitions for Fire & Gas Detectors | P2543-R01-Oct24..1.EN.6.11.9 Material Requisitions for Fire & Gas Detectors | Receive Company Comments- Material Requisitions for Gas Detectors | Re-Issue for Approval- Material Requisitions for Gas Detectors | HE-IC-1880 | HE-IC-1890 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A17 Material Requisitions for Metering Skid | P2543-R01-Oct24..1.EN.6.11.A17 Material Requisitions for Metering Skid | Receive Company Comments- Material Requisitions for Metering Skid | Re-Issue for Approval- Material Requisitions for Metering Skid | HE-IC-1820 | HE-IC-1830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A16 Material Requisitions for PRS (Pressure Reduction Skid) | P2543-R01-Oct24..1.EN.6.11.A16 Material Requisitions for PRS (Pressure Reduction Skid) | Issue ICR-Material Requisitions for PRS | Receive Company Comments-Material Requisitions for PRS | HE-IC-1690 | HE-IC-1700 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | P2543-R01-Oct24..1.EN.6.11.A131 Material Requisitions for ROV/ GOV | Issue ICR- Datasheet for GOV & ROV | Issue ICR- Material Requisitions for ROV/ GOV | HE-IC-1090 | HE-IC-1630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | Obtain Company Approval-Datasheets for Field Instruments / H2S Analyzers | Final Issue for Design/ Construction-Datasheets for Field Instruments / H2S Analyzers | HE-IC-1480 | HE-IC-1490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Issue ICR- Data sheet for PRS (Pressure Reduction System) | Receive Company Comments- Data sheet for PRS (Pressure Reduction System) | HE-IC-1210 | HE-IC-1220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | Issue ICR- Datasheet for GOV & ROV | Receive Company Comments- Datasheet for GOV & ROV | HE-IC-1090 | HE-IC-1100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Final Issue for Design/ Construction-Loop Diagrams | HE-IC-0830 | HE-IC-0770 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Re-Issue for Approval-Instrument and F&G Cable Schedule | Re-Issue for Approval - Loop Diagrams | HE-IC-0930 | HE-IC-0750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | Issue ICR - Typical Installation Drawings | Receive Company Comments - Typical Installation Drawings | HE-IC-0670 | HE-IC-0680 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | Issue ICR - Hook-Up Diagram | Receive Company Comments - Hook-Up Diagram | HE-IC-0610 | HE-IC-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | Obtain Company Approval - Hook-Up Diagram | Final Issue for Design/ Construction-Hook-Up Diagram | HE-IC-0640 | HE-IC-0650 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A3 I/O list | Final Issue for Design/ Construction-Instrument Index | Final Issue for Design/ Construction-I/O list | HE-IC-0530 | HE-IC-0590 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | Obtain Company Approval-Tie-In Schedule | Final Issue for Design/ Construction-Tie-In Schedule | HE-PR-0280 | HE-PR-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.10 Equipment List | P2543-R01-Oct24..1.EN.3.10 Equipment List | Re-Issue for Approval - Equipment List | Obtain Company Approval - Equipment List | HE-PR-1050 | HE-PR-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | Obtain Company Approval - Relief, Vent and Blowdown Philosophy | Final Issue for Design/ Construction-Relief, Vent and Blowdown philosophy | HE-PR-0820 | HE-PR-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | Obtain Company Approval- Operating and control philosophy , Safeguarding philosophy | Final Issue for Design/ Construction-Operating , control and safeguarding philosophy | HE-PR-0760 | HE-PR-0770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | Issue ICR- Process Simulations Report | Receive Company Comments- Process Simulations Report | HE-PR-0610 | HE-PR-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Final Issue for Design/ Construction- Addendum to DGS | Final Issue for Design/ Construction-Process Datasheets - Filters (At Sweihan CRS) | HE-ME-0050 | HE-PR-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | Final Issue for Design/ Construction-Process Datasheets - PRS Skid (at Sweihan CRS) | HE-IC-0110 | HE-PR-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | Issue ICR- Process Datasheets - PRS Skid (at Sweihan CRS) | Receive Company Comments- Process Datasheets - PRS Skid (at Sweihan CRS) | HE-PR-0370 | HE-PR-0380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Design Review Workshop | Re-Issue for HAZOP Studies- P&ID's review | HE-WS-0030 | HE-PR-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Issue ICR- HAZOP reviews Report for all areas | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | HE-HS-0670 | HE-PR-0140 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Issue ICR-Design Basis | Issue ICR- P&ID's | HE-DB-0010 | HE-PR-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.3.3 Process Design Basis | Issue ICR-Design Basis | Receive Company Comments-Design Basis | HE-DB-0010 | HE-DB-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.6 Project Risk Review Register | P2543-R01-Oct24..1.EN.2.6 Project Risk Review Register | Receive Company Comments-Project Risk review register | Re-Issue for Approval-Project Risk review register | HE-RR-0020 | HE-RR-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | Re-Issue for Approval-Topographical Survey Report (Overall) | Obtain Company Approval-Topographical Survey Report (Overall) | HE-TS-0030 | HE-TS-0040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- P&ID's | Design Review Workshop | HE-PR-0110 | HE-WS-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.PM.12 Workshops | Prepare Design Basis for all Engineering Disciplines and Issue to COMPANY - Final Issue | Design Review Workshop | ML1005-B01 | HE-WS-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR-HSE Philosophy | Constructability Review Workshop | HE-HS-0070 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | P2543-R01-Oct24..1.PM.12 Workshops | Receive Company Comments - HAZID / ENVID / OHID Procedure | HAZID /ENVID/OHID/ PHSER Workshop | HE-HS-0140 | HE-WS-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.4 Topographical survey & Geotechnical Investigation | P2543-R01-Oct24..1.EN.2 Survey & Studies | Place LOA/FOA - Topographical survey & Geotechnical Investigation | Topographical Survey | HS-GN-0170 | HE-SS-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.2 Survey & Studies | Award Subcontracts for Topographical Survey/ Geotechnical Investigation Studies | Topographical Survey | ML1007-B02 | HE-SS-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.30 TBE for Distibution Transformers | P2543-R01-Oct24..1.EN.9.6.30 TBE for Distibution Transformers | Obtain Company Approval-TBE for Distribution Transformer | Final Issue for Design/ Construction-TBE for Distribution Transformer | HE-EL-1480 | HE-EL-1490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | Issue ICR-Material Requisition for Distribution Transformer | Receive Company Comments-Material Requisition for Distribution Transformer | HE-EL-1030 | HE-EL-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.4 Solar Panel Sizing | P2543-R01-Oct24..1.EN.9.4 Solar Panel Sizing | Issue ICR-Solar Panel Sizing calculation | Receive Company Comments-Solar Panel Sizing calculation | HE-EL-0370 | HE-EL-0380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.4 Solar Panel Sizing | P2543-R01-Oct24..1.EN.9.4 Solar Panel Sizing | Obtain Company Approval-Solar Panel Sizing calculation | Final Issue for Design/ Construction-Solar Panel Sizing | HE-EL-0400 | HE-EL-0410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.4 Solar Panel Sizing | P2543-R01-Oct24..1.EN.9.4 Solar Panel Sizing | Re-Issue for Approval-Solar Panel Sizing calculation | Obtain Company Approval-Solar Panel Sizing calculation | HE-EL-0390 | HE-EL-0400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.4 Solar Panel Sizing | P2543-R01-Oct24..1.EN.9.4 Solar Panel Sizing | Receive Company Comments-Solar Panel Sizing calculation | Re-Issue for Approval-Solar Panel Sizing calculation | HE-EL-0380 | HE-EL-0390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..1.EN.9.16 Electrical MTO | Final Issue for Design/ Construction-Lighting Layout | Electrical 3rd MTO | HE-EL-1730 | HE-EL-1850 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..1.EN.9.13 Lighting Layout | Issue ICR-Lighting Layout | Receive Company Comments-Lighting Layout | HE-EL-1690 | HE-EL-1700 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..1.EN.9.12 Earthing Layout | Issue ICR-Earthing Layout | Receive Company Comments-Earthing Layout | HE-EL-1630 | HE-EL-1640 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..1.EN.9.12 Earthing Layout | Receive Company Comments-Earthing Layout | Re-Issue for Approval-Earthing Layout | HE-EL-1640 | HE-EL-1650 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | Issue ICR- Electrical Equipment Layout | Issue ICR-Cable Routing Layout | HE-EL-0490 | HE-EL-1570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.26 TBE for Power & Control Cables | P2543-R01-Oct24..1.EN.9.6.26 TBE for Power & Control Cables | Re-Issue for Approval-TBE for Power & Control Cables | Obtain Company Approval-TBE for Power & Control Cables | HE-EL-1530 | HE-EL-1540 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.27 TBE for UPS System | P2543-R01-Oct24..1.EN.9.6.27 TBE for UPS System | Receive Company Comments-TBE for UPS System | Re-Issue for Approval-TBE for UPS System | HE-EL-1340 | HE-EL-1350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.27 TBE for UPS System | P2543-R01-Oct24..1.EN.9.6.27 TBE for UPS System | Issue ICR-TBE for UPS System | Receive Company Comments-TBE for UPS System | HE-EL-1330 | HE-EL-1340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | Re-Issue for Approval-Cable Sizing Calculation | Re-Issue for Approval-Material Requisition for Power & Control Cables | HE-EL-0450 | HE-EL-1170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | Issue ICR-Data Sheet for LV cables | Issue ICR-Material Requisition for Power & Control Cables | HE-EL-0790 | HE-EL-1150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | Issue ICR- Datasheet for Solar panel system | Issue ICR-Material Requisition for Solar Panels | HE-EL-0730 | HE-EL-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | Re-Issue for Approval- Datasheet for Solar panel system | Issue ICR-Material Requisition for Solar Panels | HE-EL-0750 | HE-EL-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | Obtain Company Approval- Datasheet for Solar panel system | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | HE-EL-0760 | HE-EL-0770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..1.EN.9.10 Cable Schedule | Obtain Company Approval-Cable Schedule | Final Issue for Design/ Construction-Cable Schedule | HE-EL-0580 | HE-EL-0590 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | Re-Issue for Approval-Single Line Diagrams for LV Switchgear | Re-Issue for Approval- Electrical Equipment Layout | HE-EL-0210 | HE-EL-0510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | Obtain Company Approval- Electrical Equipment Layout | Final Issue for Design/ Construction-Electrical Equipment Layout | HE-EL-0520 | HE-EL-0530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | P2543-R01-Oct24..1.PM.4 NOC Register | Final Issue for Design/ Construction-Overall Pipeline Route Map - 56" | Final Issue for Design/ Construction-NOC Register | HE-PL-0170 | HC-GN-0290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.4 NOC Register | P2543-R01-Oct24..1.PM.4 NOC Register | Receive Company Comments-NOC Register | Re-Issue for Approval-NOC Register | HC-GN-0260 | HC-GN-0270 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.17.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.17.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection - Leak Detection System | Ready for Dispatch of Leak Detection System | HM-ME-0240 | HM-ME-0250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | P2543-R01-Oct24..PR.26.LL.17.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Material Requisitions for Leak Detection System | Manufacturing & Assembly of Leak Detection System | HE-IC-1790 | HM-ME-0220 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.1.2.LL.17.1 Ordering | P2543-R01-Oct24..PR.26.LL.17.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Leak Detection System | Vendor Document Review of Leak Detection System | HP-ME-0130 | HM-ME-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.LL.17.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - Leak Detection System | Vendor Document Review of Leak Detection System | ML1289-C11 | HM-ME-0210 | FF | Completed | Completed | 0
P2543-R01-Oct24..PR.26.1.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.1.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Distribution Transformer | Ready for Dispatch of Distribution Transformer | HM-ME-0950 | HM-ME-0960 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.1.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of Distribution Transformer | Packaging & Final Inspection-Distribution Transformer | HM-ME-0940 | HM-ME-0950 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.15.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Field Instruments | Ready for Dispatch of Field Instruments | HM-ME-1550 | HM-ME-1560 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.13.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Fire Fighting & Safety Equipment | Ready for Dispatch of Fire Fighting & Safety Equipment | HM-ME-1950 | HM-ME-1960 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.14.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Access Switch, Fiber Optic Patch Panel and Media Converter | Ready for Dispatch of Access Switch, Fiber Optic Patch Panel and Media Converter | HM-ME-1350 | HM-ME-1360 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.25.14.1 Ordering | P2543-R01-Oct24..PR.26.1.14.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Access Switch, Fiber Optic Patch Panel and Media Converter | Vendor Document Review of Access Switch, Fiber Optic Patch Panel and Media Converter | HP-ME-0680 | HM-ME-1320 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | HM-ME-1380 | HM-ME-1390 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | HM-ME-1280 | HM-ME-1290 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.5.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.5.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Active/ Passive Cooled Shelter | Receipt at site and inspection of Active/ Passive Cooled Shelter | HM-ME-1180 | HM-ME-1190 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.LL.5.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - Passive Cooling Shelters | Vendor Document Review of Active/ Passive Cooled Shelter | ML1309-C15 | HM-ME-1120 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.6.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.6.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Solar PV system | Ready for Dispatch of Solar PV system | HM-ME-1050 | HM-ME-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.LL.6.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - Solar Power System | Vendor Document Review of Solar PV system | ML1026-C13 | HM-ME-1020 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.LL.8.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.8.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of AC UPS | Packaging & Final Inspection-AC UPS | HM-ME-0740 | HM-ME-0750 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.9.1 Ordering | P2543-R01-Oct24..PR.26.LL.9.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for MOV | Ready for Dispatch of MOV | HP-ME-0330 | HM-ME-0650 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.LL.10.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - RTUs | Vendor Document Review of ROV/ GOV | ML1349-C19 | HM-ME-0510 | FF | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Testing and Inspection of Pig Launchers & Receivers | Packaging & Final Inspection-Pig Launchers & Receivers | HM-ME-0430 | HM-ME-0440 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.12.1 Ordering | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Pig Launchers & Receivers | Vendor Document Review of Pig Launchers & Receivers | HP-ME-0230 | HM-ME-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.12.1 Ordering | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Pig Launchers & Receivers | Ready for Dispatch of Pig Launchers & Receivers | HP-ME-0230 | HM-ME-0450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.2.25.3.1 Ordering | P2543-R01-Oct24..PR.26.1.3.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for HVAC Equipment | Ready for Dispatch of HVAC Equipment | HP-ME-0880 | HM-ME-1760 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.1.3.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of HVAC Equipment | Receipt at site and inspection of HVAC Equipment | HM-ME-1780 | HM-ME-1790 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - Pressure Reduction Skids | Vendor Document Review of Pressure Reduction Skid | ML1039-C08 | HM-ME-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.22.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.22.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Custody Metering Skid | Ready for Dispatch of Custody Metering Skid | HM-ME-0040 | HM-ME-0050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.18.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Gas Detectors | Testing and Inspection of Gas Detectors | HM-ME-1430 | HM-ME-1440 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.18.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Gas Detectors | Manufacturing & Assembly of Gas Detectors | HM-ME-1420 | HM-ME-1430 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | Testing and Inspection of Filter Package | Packaging & Final Inspection-Filter Package | HM-ME-0330 | HM-ME-0340 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.11.1 Ordering | P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Filter Package | Vendor Document Review of Filter Package | HP-ME-0180 | HM-ME-0310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.15.1 Ordering | P2543-R01-Oct24..PR.BK.15.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Earthing Material | Ready for Dispatch of Earthing Material | HP-BK-0180 | HM-EL-0350 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.9.1 Ordering | P2543-R01-Oct24..PR.BK.9.2 Manufacturing & Ready for Dispatch | Final Telecom Bulk material MTO | Final Telecom Bulk material MTO | HP-BK-0510 | HM-TL-0020 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | Final Electrical Bulk material MTO | Final Electrical Bulk material MTO | HM-EL-0500 | HM-EL-0530 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Power & Control Cables | Testing and Inspection of Power & Control Cables | HM-EL-0020 | HM-EL-0030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.1.BK.16.1 Ordering | P2543-R01-Oct24..PR.BK.16.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for MCT | Ready for Dispatch of MCT | HP-BK-0230 | HM-EL-0450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.16.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.16.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of MCT | Packaging & Final Inspection-MCT | HM-EL-0430 | HM-EL-0440 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.1.16.1 Ordering | P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | Commercial Clarifications & Placement of PO for Line Pipes (Coated) | Vendor Document Review of Line Pipes - Lot 1 | HP-ME-1040 | HM-PL-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.2.1 Ordering | P2543-R01-Oct24..PR.1.2.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Pigging & Split Tee | Vendor Document Review of Pigging & Split Tee | HP-ME-1290 | HM-PL-0770 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.3.2 Manufacturing & Ready for Dispatch | Testing and Inspection of Isolating Joints | Packaging & Final Inspection-Isolating Joints | HM-PL-0690 | HM-PL-0700 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.1.3.1 Ordering | P2543-R01-Oct24..PR.1.3.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Isolating Joints | Vendor Document Review of Isolating Joints | HP-ME-1240 | HM-PL-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.3.1 Ordering | P2543-R01-Oct24..PR.1.3.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Isolating Joints | Ready for Dispatch of Isolating Joints | HP-ME-1240 | HM-PL-0710 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Hot Incution Bend | Receipt at site and inspection of Hot Incution Bend (100% Qty) | HM-PL-0620 | HM-PL-0640 | FF | Not Started | Not Started | 30
P2543-R01-Oct24..PR.1.19.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.19.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Pig Signaler | Testing and Inspection of Pig Signaler | HM-PL-0470 | HM-PL-0480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.20.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-CP System | Ready for Dispatch of CP System | HM-PL-0380 | HM-PL-0390 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Ball/ Globe/ Check/ Plug Valves | Ready for Dispatch of Ball/ Globe/ Check/ Plug Valves | HM-PL-0180 | HM-PL-0190 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..ML.4 Commissioning and PAC | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | Commission New pipeline system -52" Sales Gas Pipeline | CCM-PM4520 | ML2009-F02 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Complete Pipeline welding - 52" Sales Gas Pipeline - 100% Welding | Complete Drying & Purging of all facilities including Pipeline & Block Valve Stations - 52" Sales Gas Pipeline | ML1719-E17 | ML1829-E28 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Receive at Site - E&I Equipment's (IDS & PIDS System) | HM-ME-1290 | ML1479-D15 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Pig Signaler (Lot 1) | Receive at Site - Isolation Joints, Barred Tee, and Anchor Flanges | HM-PL-0530 | ML1409-D24 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Receive at Site - Valves – Globe/Check/Plug | HM-PL-0220 | ML1529-D20 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.6.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Solar PV system | Issue Purchase Order (Final) - Solar Power System | HP-ME-0530 | ML1026-C13 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-0290 | ML1035-B26 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.17 Typical details of protection slab to protect existing UG pipe at road crossing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical details of protection slab to protect existing UG pipe at road crossing | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-0410 | ML1035-B26 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Standard drawings for Anchor bolt | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-0110 | ML1035-B26 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical duct bank detail drawing | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-0230 | ML1035-B26 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-1310 | ML1035-B26 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | HE-IC-2570 | ML1032-B21 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical trench detail drawing | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | HE-CS-0170 | ML1032-B21 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Telecom cable schedule | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | HE-TL-0830 | ML1032-B21 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.11 QRA Report | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-QRA Report | Complete HSEIA, QRA, and Gas Dispersion Studies after review / approval by Company and Submit Final Reports | HE-HS-0830 | ML1016-B12 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.10 Equipment List | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue for Approval - Equipment List | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | HE-PR-1050 | ML1012-B06 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-PI-0880 | ML1219-B19 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design / Construction-P&ID's | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-PR-0160 | ML1219-B19 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-0290 | ML1209-B27 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-0650 | ML1209-B27 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | HE-PI-0580 | ML1179-B11 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..ML.EN Detail Engineering | 30% Model Review | 30% Model Review | HE-PI-0130 | ML2059-B05 | FF | Completed | Completed | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Receive at Site - Sales Gas Metering Skids | Project Finish | ML1419-D08 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..ML Milestones | Electrical | Project Finish | CAB-4450 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Civil works for CRS Building & equipment's foundations at Sweihan CRS | Project Finish | ML1839-E29 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete As-Built drawings including Project close out report and submit to COMPANY | Project Finish | ML1989-E44 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Piping works at Sweihan CRS | Project Finish | ML1849-E30 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Telecom | Close-out report | CAB-4470 | CAB-5320 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Prepare Design Basis for all Engineering Disciplines and Issue to COMPANY - Final Issue | General | ML1005-B01 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2.1 Site Visit Report | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Final Issue for Design/ Construction-Site Visit Report | General | HE-SV-0050 | CAB-5290 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Final Issue for Design/ Construction-Shutdown Requirements & Plan | General | C-COM-890 | CAB-5290 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.2 Final Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Quality Dossier | Vendor Documents Package | CAB-5300 | CAB-5310 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Pipeline | Vendor Documents Package | CAB-4480 | CAB-5310 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Vendor Documents Package | HM-ME-1290 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.38 Crossing Schedule-52" | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Crossing Schedule-52" | Pipeline | HE-PL-3090 | CAB-4480 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.54 TBE for Pig Signaler | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Pig Signaler | Pipeline | HE-PL-2370 | CAB-4480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.60.12 Data Sheet - Pipeline Pigging Tees | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Data Sheet - Pipeline Pigging Tees | Pipeline | HE-PL-1490 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.13 Pipeline Schematic Arrangement- 56", 52" and 4" Pipline | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | Pipeline | HE-PL-0350 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Obtain Final Route Approval from Authorities | Pipeline | ML1011-A05 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.11.43 Material Requisition for Pig Signaler | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisition for Pig Signaler | Pipeline | HE-PL-1970 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.11.21 Material Requisition for Manual Ball Valves | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisition for Manual Ball Valves | Pipeline | HE-PL-1730 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.60.10 Data Sheet - Hot Induction Bends | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Data Sheet - Hot Induction Bends | Pipeline | HE-PL-1310 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Telecom Equipment Layout | Telecom | HE-TL-0770 | CAB-4470 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Telecom | HE-TL-0350 | CAB-4470 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.11.A131 Material Requisitions for ROV/ GOV | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisitions for ROV/ GOV | Instrumentation & Control | HE-IC-1670 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Power Consumption Calculation (Instrumentation) | Instrumentation & Control | HE-EL-5480 | CAB-4460 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.10 TBE for Fire & Gas Detectors | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Gas Detectors | Instrumentation & Control | HE-IC-2390 | CAB-4460 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- Specification for Leak Detection System | Instrumentation & Control | HE-IC-0250 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Specification for RTU | Instrumentation & Control | HE-IC-0230 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Actuator Datasheet for GOV & ROV | Instrumentation & Control | HE-IC-1130 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.11.A16 Material Requisitions for PRS (Pressure Reduction Skid) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisitions for PRS | Instrumentation & Control | HE-IC-1730 | CAB-4460 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.30 TBE for Distibution Transformers | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Distribution Transformer | Electrical | HE-EL-1490 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Electrical | ML1032-B21 | CAB-4450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | Piping | HE-PI-0580 | CAB-4440 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | Piping | ML1012-B06 | CAB-4440 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.2.6 TBE for Ball valves/ Plug Valves | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Ball valves/ Plug Valves | Piping | HE-PI-1120 | CAB-4440 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.16 Critical line List | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Critical line List | Piping | HE-PI-0302 | CAB-4440 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue MRs for All Mechanical Equipment & Packages (Final Issue) | Piping | ML1017-B18 | CAB-4440 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue MRs for All Mechanical Equipment & Packages (Final Issue) | Mechanical | ML1017-B18 | CAB-4430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Typical duct bank detail drawing | Civil & Structural | HE-CS-0230 | CAB-4420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.29 TBE for Active/ Passive Shelters | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Active/ Passive Shelters | Civil & Structural | HE-EL-1250 | CAB-4420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Typical Structural Steel and Foundation details for pipe support | Civil & Structural | HE-CS-1370 | CAB-4420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Topographical Survey Report (Overall) | Civil & Structural | HE-TS-0050 | CAB-4420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Design Calculation for Typical Pipe supports | Civil & Structural | HE-CS-1130 | CAB-4420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | Civil & Structural | ML1209-B27 | CAB-4420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-HAZOP Procedure | HSE | HE-HS-0230 | CAB-4410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-HAZOP Review Report | HSE | HE-HS-0710 | CAB-4410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HSE | HE-HS-1010 | CAB-4410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.4 Project HSE Plan | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Project HSE Plan | HSE | HE-HS-0050 | CAB-4410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.17 Line List | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Line List | Process | HE-PR-1130 | CAB-4400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | Process | ML1012-B06 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Process Datasheets - PRS Skid (at Sweihan CRS) | Process | HE-PR-0410 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Process Datasheets | Process | HE-PR-0590 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Complete HSEIA, QRA, and Gas Dispersion Studies after review / approval by Company and Submit Final Reports | Issue ICR-Pre-commissioning and Commissioning Plan | ML1016-B12 | C-COM-800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-HS-1010 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Re-Issue for Approval-Construction Procedures / Method Statements / ITPs | Obtain Company Approval-Construction Procedures / Method Statements / ITPs | C-COM-770 | C-COM-780 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Actuator Datasheet for MOVs | Re-Issue for Approval-Construction Procedures / Method Statements / ITPs | HE-IC-1070 | C-COM-770 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Typical duct bank detail drawing | Issue ICR-Construction Procedures / Method Statements / ITPs | HE-CS-0230 | C-COM-750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | P2543-R01-Oct24..1.1.BK.8.1 Ordering | Instrument 3rd MTO | Final Instrumentation Bulk material MTO | HE-IC-2630 | HP-BK-0470 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..1.EN.8.42 Civil MTO | P2543-R01-Oct24..1.1.BK.5.1 Ordering | Issued - Civil MTO 2 | Final Structural Bulk material MTO | HE-CS-1550 | HP-BK-0310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.16.1 Ordering | P2543-R01-Oct24..1.1.BK.16.1 Ordering | RFQ, Receipt of Bid for MCT | Prepare TBE and Company approval for MCT | HP-BK-0210 | HP-BK-0220 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..1.1.BK.15.1 Ordering | Issue ICR-Earthing Layout | RFQ, Receipt of Bid for Earthing Material | HE-EL-1630 | HP-BK-0160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | P2543-R01-Oct24..1.1.BK.17.1 Ordering | Issue ICR-Material Requisition for Power & Control Cables | RFQ, Receipt of Bid for Power & Control Cables | HE-EL-1150 | HP-BK-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.18 MR for Hot Induction Bends | P2543-R01-Oct24..1.1.1.1.1 Ordering | Final Issue for Design/ Construction-MR for Hot Induction Bends | Commercial Clarifications & Placement of PO for Hot Induction Bend | HE-PL-1790 | HP-ME-1190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.6.1 Ordering | P2543-R01-Oct24..1.1.2.LL.6.1 Ordering | RFQ, Receipt of Bid for Solar PV system | Prepare TBE and Company approval for Solar PV system | HP-ME-0510 | HP-ME-0520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.8.1 Ordering | P2543-R01-Oct24..1.1.2.LL.8.1 Ordering | Prepare TBE and Company approval for AC UPS | Commercial Clarifications & Placement of PO for AC UPS | HP-ME-0370 | HP-ME-0380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.12.1 Ordering | P2543-R01-Oct24..1.1.2.LL.12.1 Ordering | Prepare TBE and Company approval for Pig Launchers & Receivers | Commercial Clarifications & Placement of PO for Pig Launchers & Receivers | HP-ME-0220 | HP-ME-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.11.1 Ordering | P2543-R01-Oct24..1.1.2.LL.11.1 Ordering | Prepare TBE and Company approval for Filter Package | Commercial Clarifications & Placement of PO for Filter Package | HP-ME-0170 | HP-ME-0180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A33 TBE for PRS (Pressure Reduction Skid) | P2543-R01-Oct24..1.1.2.LL.21.1 Ordering | Obtain Company Approval-TBE for PRS | Commercial Clarifications & Placement of PO for Pressure Reduction Skid | HE-IC-2200 | HP-ME-0080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.22.1 Ordering | P2543-R01-Oct24..1.1.2.LL.22.1 Ordering | RFQ, Receipt of Bid for Custody Metering Skid | Prepare TBE and Company approval for Custody Metering Skid | HP-ME-0010 | HP-ME-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | P2543-R01-Oct24..1.1.2.25.2.1 Ordering | Issue ICR- Fire Fighting & Safety Eqpt. Layout | RFQ, Receipt of Bid for Fire Suppression System | HE-HS-0370 | HP-ME-0910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.18.1 Ordering | P2543-R01-Oct24..1.1.2.LL.18.1 Ordering | Prepare TBE and Company approval for Gas Detectors | Commercial Clarifications & Placement of PO for Gas Detectors | HP-ME-0720 | HP-ME-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.2.12.14 Fence Works | Project Kick off Meeting | Fence Works RFQ & Quotation Receipt | ML1002 | HS-CN-0660 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.13 E&I Works | P2543-R01-Oct24..1.2.12.13 E&I Works | E&I Works Complete Evaluation (Internal) | E&I Works Subcontract Award | HS-CN-0630 | HS-CN-0640 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.12 Building | P2543-R01-Oct24..1.2.12.12 Building | Building RFQ & Quotation Receipt | Building Complete Evaluation (Internal) | HS-CN-0560 | HS-CN-0580 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.2.12.11 Hot Tapping | Project Kick off Meeting | Hot Tapping RFQ & Quotation Receipt | ML1002 | HS-CN-0510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..1.2.12.7 OHPL | Final Issue for Design/ Construction-Instrument Trench Layout | OHPL RFQ & Quotation Receipt | HE-IC-1010 | HS-CN-0410 | FS | Completed | Completed | 76
P2543-R01-Oct24..1.1.2.LL.19.1 Ordering | P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | RFQ, Receipt of Bid for FOC Cables | FOC Splicing / Termination RFQ & Quotation Receipt | HP-BK-0060 | HS-CN-0260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.9 HSE Studies | P2543-R01-Oct24..1.2.13.9 HSE Studies | Complete Evaluation (Internal) - HSE Studies | Place LOA/FOA - HSE Studies | HS-GN-0100 | HS-GN-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | Issue ICR- I/O list -Update | RFQ, Receipt of Bid - Modification of Existing DCS | HE-IC-0550 | HS-GN-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | Final Issue for Design/ Construction-Specification for RTU | RFQ, Receipt of Bid - Modification of Existing DCS | HE-IC-0230 | HS-GN-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | Re-Issue for Approval - Passive cooled shelter foundation GA and details | Obtain Company Approval - Passive cooled shelter foundation GA and details | HE-CS-1290 | HE-CS-1300 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | Re-Issue after incorporating HAZOP /Review Comments - 4" N2 Source Pipeline | Issued for Review - Passive cooled shelter foundation GA and details | HE-PI-0490 | HE-CS-1270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | Review Company Comments - Valve pit foundation GA and RC (type) details | Re-Issue for Approval - Valve pit foundation GA and RC (type) details | HE-CS-1160 | HE-CS-1170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | Issue ICR - Pipeline Alignment Sheets-52" | Issued for Review - Valve pit foundation GA and RC (type) details | HE-PL-2450 | HE-CS-1150 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | Final Issue for Design/ Construction-Geotechnical Survey Report (Overall) | Final Issue for Design/ Construction-Design Calculation for Typical Pipe supports | HE-GS-0050 | HE-CS-1130 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | Issued for Review - Typical Detailed Drawing - Jib Crane Foundation | Review Company Comments - Typical Detailed Drawing - Jib Crane Foundation | HE-CS-1030 | HE-CS-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | Final Issue for Design/ Construction-Design Calculation for Typical Skid Foundations | Final Issue for Design/ Construction-Gas metering skid foundation drawings | HE-CS-0710 | HE-CS-0830 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | Re-Issue for Approval - Gas metering skid foundation drawings | Obtain Company Approval - Gas metering skid foundation drawings | HE-CS-0810 | HE-CS-0820 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | Review Company Comments - Design Cal. for Typical Skid Foundations | Re-Issue for Approval - Design Cal. for Typical Skid Foundations | HE-CS-0680 | HE-CS-0690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.28 Calculation for Pig launcher and receiver foundations | P2543-R01-Oct24..1.EN.8.28 Calculation for Pig launcher and receiver foundations | Review Company Comments - Calculation for Pig launcher and receiver foundations | Re-Issue for Approval - Calculation for Pig launcher and receiver foundations | HE-CS-0560 | HE-CS-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.8.11 Civil UG layout | Final Issue for Design/ Construction-Topographical Survey Report (Overall) | Final Issue for Design/ Construction-Civil UG layout | HE-TS-0050 | HE-CS-0530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.17 Typical details of protection slab to protect existing UG pipe at road crossing | P2543-R01-Oct24..1.EN.8.17 Typical details of protection slab to protect existing UG pipe at road crossing | Obtain Company Approval - Typical details of protection slab to protect existing UG pipe at road crossing | Final Issue for Design/ Construction-Typical details of protection slab to protect existing UG pipe at road crossing | HE-CS-0400 | HE-CS-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | Obtain Company Approval - Typical Fence and gate detail drawing | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | HE-CS-0340 | HE-CS-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | Review Company Comments - Typical Fence and gate detail drawing | Re-Issue for Approval - Typical Fence and gate detail drawing | HE-CS-0320 | HE-CS-0330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | Issued for Review - Typical Road and paving detail drawing | Review Company Comments - Typical Road and paving detail drawing | HE-CS-0250 | HE-CS-0260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | Obtain Company Approval - Typical duct bank detail drawing | Final Issue for Design/ Construction-Typical duct bank detail drawing | HE-CS-0220 | HE-CS-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | Issued for Review - Standard drawings for Anchor bolt | Review Company Comments - Standard drawings for Anchor bolt | HE-CS-0070 | HE-CS-0080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | Obtain Company Approval - Addendum to DGs | Final Issue for Design/ Construction-Addendum to DGs | HE-CS-0040 | HE-CS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction-Typical Detailed Drawing - Jib Crane Foundation | Issued - Civil MTO 2 | HE-CS-1070 | HE-CS-1550 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Issued - Civil MTO 2 | HE-CS-1310 | HE-CS-1550 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | P2543-R01-Oct24..1.EN.8.41 Misc. supports | Re-Issue for Approval-Piping Stress Analysis & Report | Issued for Review - Misc. supports and civil/ structural details | HE-PI-1160 | HE-CS-1450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.3.9 TBE for Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.3.9 TBE for Sals Gas CRS Filters | Issue ICR-TBEs for Sales Gas CRS Filters | Receive Company Comments-TBEs for Sales Gas CRS Filters | HE-ME-0190 | HE-ME-0200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | Issue ICR-Datasheet for Sales Gas CRS Filters | Issue ICR-Material Requisitions for Sales Gas CRS Filters | HE-ME-0070 | HE-ME-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Obtain Company Approval- Plot plan - BVS | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | HE-PI-0570 | HE-PI-0580 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Final Issue for Design/ Construction-Topographical Survey Report (Overall) | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | HE-TS-0050 | HE-PI-0580 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Receive Company Comments- Plot plan - BVS | Re-Issue for HAZOP Studies- Plot plan - BVS | HE-PI-0540 | HE-PI-0550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue after incorporating HAZOP /Review Comments - 4" N2 Source Pipeline | HE-PR-0070 | HE-PI-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Issue ICR- Process Flow Diagrams ( New + Existing) | Issue ICR- Overall Plot Plan - 4" N2 Source Pipeline | HE-PR-0040 | HE-PI-0460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue after HAZOP /Review Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0070 | HE-PI-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR- Process Flow Diagrams ( New + Existing) | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0040 | HE-PI-0320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.16 Critical line List | P2543-R01-Oct24..1.EN.7.16 Critical line List | Obtain Company Approval-Critical line List | Final Issue for Design/ Construction-Critical line List | HE-PI-0292 | HE-PI-0302 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | Receive Company Comments-Piping Material Specifications | Re-Issue for Approval-Piping Material Specifications | HE-PI-0020 | HE-PI-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | Re-Issue for Approval-Piping GA for 52" Pipeline SWEIHAN CRS | Re-Issue for Approval-Piping Isometrics | HE-PI-0680 | HE-PI-1220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.16 Critical line List | P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | Final Issue for Design/ Construction-Critical line List | Final Issue for Design/ Construction-Piping Stress Analysis & Report | HE-PI-0302 | HE-PI-1180 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | Obtain Company Approval-Piping Stress Analysis & Report | Final Issue for Design/ Construction-Piping Stress Analysis & Report | HE-PI-1170 | HE-PI-1180 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | Receive Company Comments-Piping Stress Analysis & Report | Re-Issue for Approval-Piping Stress Analysis & Report | HE-PI-1150 | HE-PI-1160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | Obtain Company Approval-Piping GA for 591-BVS-01 to 06 | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | HE-PI-0870 | HE-PI-0880 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | Receive Company Comments-Piping GA for 591-BVS-01 to 06 | Re-Issue for Approval-Piping GA for 591-BVS-01 to 06 | HE-PI-0850 | HE-PI-0860 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | Issue ICR-Piping GA for 591-BVS-01 to 06 | Receive Company Comments-Piping GA for 591-BVS-01 to 06 | HE-PI-0840 | HE-PI-0850 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | Final Issue for Design/ Construction-Piping GA Drawings for 591-BVS-01 | HE-PI-0580 | HE-PI-0820 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | Re-Issue after incorporating HAZOP / Review Comments- Plot plan - BVS | Issue ICR - Piping GA Drawings for 591-BVS-01 | HE-PI-0560 | HE-PI-0780 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | Final Issue for Design/ Construction-Overall Plot Plan- 4" N2 Source Pipeline | Final Issue for Design/ Construction-Piping GA for 4" N2 Source Pipeline | HE-PI-0510 | HE-PI-0760 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Receive Company Comments-56" Pipeline Launcher and metering Station (Habshan Complex) | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0610 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.7.10 3D Model | Issue ICR- Overall Plot Plan - 4" N2 Source Pipeline | 30% Model Review | HE-PI-0460 | HE-PI-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.7.10 3D Model | 60% Model Review | 60% Model Review Report | HE-PI-0150 | HE-PI-0160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | Obtain Company Approval-HAZID/ ENVID/ OHID Report | Final Issue for Design/ Construction-HAZID/ ENVID/ OHID Report | HE-HS-0580 | HE-HS-0590 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | Obtain Company Approval- HSEIA Study Report | Final Issue for Design/ Construction-HSEIA Study Report | HE-HS-0520 | HE-HS-0530 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | Constructability Review Workshop | Re-Issue for Approval- HSEIA Study Report | HE-WS-0050 | HE-HS-0510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | Re-Issue for Approval-Fire Fighting & Safety Eqpt. Layout | Obtain Company Approval-Fire Fighting & Safety Eqpt. Layout | HE-HS-0390 | HE-HS-0400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | Final Issue for Design/ Construction-I/O list | Final Issue for Design/ Construction-F&G Cause and effect | HE-IC-0590 | HE-HS-0350 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | Issue ICR-HSE Philosophy | Issue ICR-F&G Cause and Effect | HE-HS-0070 | HE-HS-0310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.4.5 F&G layout | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Final Issue for Design/ Construction-F&G layout | HE-PI-0440 | HE-HS-0290 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | Obtain Company Approval-HSE Philosophy | Final Issue for Design/ Construction-Project HSE Philosophy | HE-HS-0100 | HE-HS-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.4 Project HSE Plan | P2543-R01-Oct24..1.EN.4.4 Project HSE Plan | Obtain Company Approval-HSE Plan | Final Issue for Design/ Construction-Project HSE Plan | HE-HS-0040 | HE-HS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Receive Company Comments-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Re-Issue for Approval-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-HS-0980 | HE-HS-0990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Study & Issue ICR- HSEIA Study Report | Issue ICR-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-HS-0490 | HE-HS-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.17 PHSER Close Out Report | P2543-R01-Oct24..1.EN.4.17 PHSER Close Out Report | Obtain Company Approval- PHSER Close Out Report | Final Issue for Design/ Construction-PHSER Close Out Report | HE-HS-0940 | HE-HS-0950 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.12 PHSER Report | P2543-R01-Oct24..1.EN.4.17 PHSER Close Out Report | Final Issue for Design/ Construction-PHSER Report | Issue ICR- PHSER Close Out Report | HE-HS-0890 | HE-HS-0910 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.4.12 PHSER Report | P2543-R01-Oct24..1.EN.4.12 PHSER Report | Re-Issue for Approval-PHSER Report | Obtain Company Approval-PHSER Report | HE-HS-0870 | HE-HS-0880 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.21 HAZOP close out report | P2543-R01-Oct24..1.EN.4.21 HAZOP close out report | Receive Company Comments- HAZOP Close Out Report | Re-Issue for Approval- HAZOP Close Out Report | HE-HS-0740 | HE-HS-0750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | Obtain Company Approval - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Final Issue for Design/ Construction-Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | HE-TL-0100 | HE-TL-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | Re-Issue for Approval - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Obtain Company Approval - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | HE-TL-0090 | HE-TL-0100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | Re-Issue for Approval-Telecom Equipment Layout | Obtain Company Approval-Telecom Equipment Layout | HE-TL-0750 | HE-TL-0760 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Final Issue for Design/ Construction-Telecom Equipment Layout | HE-TL-0470 | HE-TL-0770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Obtain Company Approval- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Final Issue for Design/ Construction-Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0520 | HE-TL-0530 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Re-Issue for Approval- Telecom Tie-in Block Diagram | Obtain Company Approval- Telecom Tie-in Block Diagram | HE-TL-0390 | HE-TL-0400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Receive Company Comments- Telecom Tie-in Block Diagram | Re-Issue for Approval- Telecom Tie-in Block Diagram | HE-TL-0380 | HE-TL-0390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Re-Issue for Approval-Instrument index -Update | Re-Issue for Approval- Telecom Tie-in Block Diagram | HE-IC-0510 | HE-TL-0390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Issue ICR - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Issue ICR- Telecom Tie-in Block Diagram | HE-TL-0070 | HE-TL-0370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Re-Issue for Approval - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Re-Issue for Approval- Overall Telecom Block Diagram | HE-TL-0090 | HE-TL-0330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Obtain Company Approval- Overall Telecom Block Diagram | Final Issue for Design/ Construction-Overall Telecom Block Diagram | HE-TL-0340 | HE-TL-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Re-Issue for Approval-Telecom Location and Cable Routing layout | Re-Issue for Approval- Telecom Cable Schedule | HE-TL-0690 | HE-TL-0810 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Re-Issue for Approval- Overall Telecom Block Diagram | Re-Issue for Approval- Telecom Cable Schedule | HE-TL-0330 | HE-TL-0810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.4.1 Ordering | P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | RFQ, Receipt of Bid for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Issue ICR-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HP-ME-0610 | HE-TL-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | Obtain Company Approval-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Final Issue for Design/ Construction-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0640 | HE-TL-0650 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Receive Company Comments- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-TL-0250 | HE-TL-0260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.43 Material Requisition for Pig Signaler | P2543-R01-Oct24..1.EN.6.11.43 Material Requisition for Pig Signaler | Re-Issue for Approval- Material Requisition for Pig Signaler | Obtain Company Approval- Material Requisition for Pig Signaler | HE-PL-1950 | HE-PL-1960 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.11 Data Sheet - Pipeline Isolating Joints | P2543-R01-Oct24..1.EN.1.9.20 MR for Isolating Joints | Final Issue for Design/ Construction-Data Sheet - Pipeline Isolating Joints | Final Issue for Design/ Construction-MR for Isolating Joints | HE-PL-1430 | HE-PL-1910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.12 Data Sheet - Pipeline Pigging Tees | P2543-R01-Oct24..1.EN.1.9.19 MR for Pipeline Pigging Tees | Re-Issue for Approval - Data Sheet - Pigging Tees | Re-Issue for Approval - MR for Pigging Tees | HE-PL-1470 | HE-PL-1830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.10 Data Sheet - Hot Induction Bends | P2543-R01-Oct24..1.EN.1.9.18 MR for Hot Induction Bends | Final Issue for Design/ Construction-Data Sheet - Hot Induction Bends | Final Issue for Design/ Construction-MR for Hot Induction Bends | HE-PL-1310 | HE-PL-1790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.21 Material Requisition for Manual Ball Valves | P2543-R01-Oct24..1.EN.6.11.21 Material Requisition for Manual Ball Valves | Re-Issue for Approval - MR for Mainline Ball Valve | Obtain Company Approval - MR for Mainline Ball Valve | HE-PL-1710 | HE-PL-1720 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.17 MR for Linepipes | P2543-R01-Oct24..1.EN.1.9.17 MR for Linepipes | Re-Issue for Approval - MR for Line pipes | Obtain Company Approval - MR for Line pipes | HE-PL-1650 | HE-PL-1660 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.17 MR for Linepipes | P2543-R01-Oct24..1.EN.1.9.17 MR for Linepipes | Issue ICR - MR for Line pipes | Receive Company Comments - MR for Line pipes | HE-PL-1630 | HE-PL-1640 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | Re-Issue for Approval - Data Sheet - Split Tee | Obtain Company Approval - Data Sheet - Split Tee | HE-PL-1350 | HE-PL-1360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | Receive Company Comments - Data Sheet - Split Tee | Re-Issue for Approval - Data Sheet - Split Tee | HE-PL-1340 | HE-PL-1350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.9 Data Sheet - Linepipes | P2543-R01-Oct24..1.EN.1.60.9 Data Sheet - Linepipes | Obtain Company Approval - Data Sheet - Line pipes | Final Issue for Design/ Construction-Data Sheet - Line pipes | HE-PL-1180 | HE-PL-1190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.6 Pipeline Location Class selection Report | P2543-R01-Oct24..1.EN.1.6 Pipeline Location Class selection Report | Re-Issue for Approval - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | Obtain Company Approval - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | HE-PL-0810 | HE-PL-0820 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.3 Pipeline Upheavl Calculation | P2543-R01-Oct24..1.EN.1.3 Pipeline Upheavl Calculation | Obtain Company Approval - Pipeline Upheaval Calculation | Final Issue for Design/ Construction-Pipeline Upheaval Calculation | HE-PL-0640 | HE-PL-0650 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | Receive Company Comments - Overall Pipeline Route Map - 4" | Re-Issue for Approval - Overall Pipeline Route Map - 4" | HE-PL-0260 | HE-PL-0270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | Re-Issue for Approval - Overall Pipeline Route Map - 52" | Obtain Company Approval - Overall Pipeline Route Map - 52" | HE-PL-0210 | HE-PL-0220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | Issue ICR-Topographical Survey Report (Overall) | Re-Issue for Approval - Overall Pipeline Route Map - 52" | HE-TS-0010 | HE-PL-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | Issue ICR - Specification - Pipeline Wall Thickness Calculation Report | Receive Company Comments - Pipeline Wall Thickness Calculation Report | HE-PL-0010 | HE-PL-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | Re-Issue for Approval - Specification -Pipeline Wall Thickness Calculation Report | Obtain Company Approval - Pipeline Wall Thickness Calculation Report | HE-PL-0030 | HE-PL-0040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.38 Crossing Schedule-52" | P2543-R01-Oct24..1.EN.1.38 Crossing Schedule-52" | Receive Company Comments - Crossing Schedule-52" | Re-Issue for Approval - Crossing Schedule-52" | HE-PL-3060 | HE-PL-3070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | Obtain Company Approval - Detailed crossing drawings - 56" | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | HE-PL-2900 | HE-PL-2910 | FF | Completed | In Progress | 5
P2543-R01-Oct24..1.EN.1.1 Pipeline Route Verification and Selection Report | P2543-R01-Oct24..1.EN.1.1 Pipeline Route Verification and Selection Report | Receive Company Comments - Pipeline Route Verification and Selection Report | Re-Issue for Approval - Pipeline Route Verification and Selection Report | HE-PL-2760 | HE-PL-2770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.15 Pipeline Station approach drawing - 4" Nitrogen | P2543-R01-Oct24..1.EN.1.15 Pipeline Station approach drawing - 4" Nitrogen | Obtain Company Approval - Pipeline Station Approach drawing -4" | Final Issue for Design/ Construction-Pipeline Station approach drawing-4" | HE-PL-2720 | HE-PL-2730 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.15 Pipeline Station approach drawing - 4" Nitrogen | P2543-R01-Oct24..1.EN.1.15 Pipeline Station approach drawing - 4" Nitrogen | Re-Issue for Approval - Pipeline Station Approach drawing -4" | Obtain Company Approval - Pipeline Station Approach drawing -4" | HE-PL-2710 | HE-PL-2720 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.15 Pipeline Station approach drawing - 4" Nitrogen | P2543-R01-Oct24..1.EN.1.15 Pipeline Station approach drawing - 4" Nitrogen | Issue ICR - Pipeline Station Approach drawing -4" | Receive Company Comments - Pipeline Station Approach drawing -4" | HE-PL-2690 | HE-PL-2700 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.15 Pipeline Station approach drawing - 4" Nitrogen | Issue ICR-Topographical Survey Report (Overall) | Issue ICR - Pipeline Station Approach drawing -4" | HE-TS-0010 | HE-PL-2690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | Issue ICR - Pipeline Alignment Sheets-4" | Receive Company Comments - Pipeline Alignment Sheets-4" | HE-PL-2510 | HE-PL-2520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | Issue ICR-Topographical Survey Report (Overall) | Issue ICR - Pipeline Alignment Sheets-52" | HE-TS-0010 | HE-PL-2450 | FS | Completed | Completed | 15
P2543-R01-Oct24..1.EN.6.2.54 TBE for Pig Signaler | P2543-R01-Oct24..1.EN.6.2.54 TBE for Pig Signaler | Re-Issue for Approval- TBE for Pig Signaler | Obtain Company Approval- TBE for Pig Signaler | HE-PL-2350 | HE-PL-2360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.26 TBE for Mainline Ball Valve | P2543-R01-Oct24..1.EN.6.2.26 TBE for Mainline Ball Valve | Issue ICR - TBE for Mainline Ball Valve | Receive Company Comments - TBE for Mainline Ball Valve | HE-PL-2270 | HE-PL-2280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.26 TBE for Mainline Ball Valve | P2543-R01-Oct24..1.EN.6.2.26 TBE for Mainline Ball Valve | Receive Company Comments - TBE for Mainline Ball Valve | Re-Issue for Approval - TBE for Mainline Ball Valve | HE-PL-2280 | HE-PL-2290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.3.1 Ordering | P2543-R01-Oct24..1.EN.1.10.25 TBE for Isolating Joints | RFQ, Receipt of Bid for Isolating Joints | Issue ICR - TBE for Isolating Joints | HP-ME-1220 | HE-PL-2210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.1.1 Ordering | P2543-R01-Oct24..1.EN.1.10.23 TBE for Hot Induction Bends | RFQ, Receipt of Bid for Hot Incution Bend | Issue ICR - TBE for Hot Induction Bends | HP-ME-1170 | HE-PL-2090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.7 Material Requisitions for Junction Boxes | P2543-R01-Oct24..1.EN.6.11.7 Material Requisitions for Junction Boxes | Issue ICR- Material Requisitions for Junction Boxes | Receive Company Comments- Material Requisitions for Junction Boxes | HE-IC-1990 | HE-IC-2000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.3 TBE for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.EN.6.2.3 TBE for Field Instruments / H2S Analyzers | Obtain Company Approval- TBE for Field Instruments / H2S Analyzers | Final Issue for Design/ Construction-TBE for Field Instruments / H2S Analyzers | HE-IC-2440 | HE-IC-2450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | Final Issue for Design/ Construction-Specification for RTU | Final Issue for Design/ Construction-Power Consumption Calculation (Instrumentation) | HE-IC-0230 | HE-EL-5480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | Receive Company Comments- Power Consumption Calculation (Instrumentation) | Re-Issue for Approval- Power Consumption Calculation (Instrumentation) | HE-EL-5450 | HE-EL-5460 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Final Issue for Design/ Construction-Hook-Up Diagram | Instrument 3rd MTO | HE-IC-0650 | HE-IC-2630 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Final Issue for Design/ Construction-Instrument Index | Instrument 3rd MTO | HE-IC-0530 | HE-IC-2630 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Final Issue for Design/ Construction-Actuator Datasheet for MOVs | Instrument 3rd MTO | HE-IC-1070 | HE-IC-2630 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Re-Issue for Approval - Typical Installation Drawings | Instrument 2nd MTO | HE-IC-0690 | HE-IC-2610 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.5 TBE for ROV/ GOV | P2543-R01-Oct24..1.EN.6.2.5 TBE for ROV/ GOV | Receive Company Comments- TBE for ROV/ GOV | Re-Issue for Approval- TBE for ROV/ GOV | HE-IC-2300 | HE-IC-2310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A33 TBE for PRS (Pressure Reduction Skid) | P2543-R01-Oct24..1.EN.6.2.A33 TBE for PRS (Pressure Reduction Skid) | Re-Issue for Approval-TBE for PRS | Obtain Company Approval-TBE for PRS | HE-IC-2190 | HE-IC-2200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.6 TBE for MOV | P2543-R01-Oct24..1.EN.6.2.6 TBE for MOV | Obtain Company Approval- TBE for MOV | Final Issue for Design/ Construction-TBE for MOV | HE-IC-2080 | HE-IC-2090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A17 Material Requisitions for Metering Skid | P2543-R01-Oct24..1.EN.6.11.A17 Material Requisitions for Metering Skid | Obtain Company Approval- Material Requisitions for Metering Skid | Final Issue for Design/ Construction-Material Requisitions for Metering Skid | HE-IC-1840 | HE-IC-1850 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.11.A16 Material Requisitions for PRS (Pressure Reduction Skid) | P2543-R01-Oct24..1.EN.6.11.A16 Material Requisitions for PRS (Pressure Reduction Skid) | Obtain Company Approval-Material Requisitions for PRS | Final Issue for Design/ Construction-Material Requisitions for PRS | HE-IC-1720 | HE-IC-1730 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.11.A16 Material Requisitions for PRS (Pressure Reduction Skid) | P2543-R01-Oct24..1.EN.6.11.A16 Material Requisitions for PRS (Pressure Reduction Skid) | Receive Company Comments-Material Requisitions for PRS | Re-Issue for Approval-Material Requisitions for PRS | HE-IC-1700 | HE-IC-1710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A131 Material Requisitions for ROV/ GOV | P2543-R01-Oct24..1.EN.6.11.A131 Material Requisitions for ROV/ GOV | Receive Company Comments- Material Requisitions for ROV/ GOV | Re-Issue for Approval- Material Requisitions for ROV/ GOV | HE-IC-1640 | HE-IC-1650 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A1311 Material Requisitions for MOV | P2543-R01-Oct24..1.EN.6.11.A1311 Material Requisitions for MOV | Receive Company Comments- Material Requisitions for MOV | Re-Issue for Approval- Material Requisitions for MOV | HE-IC-1580 | HE-IC-1590 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A1311 Material Requisitions for MOV | P2543-R01-Oct24..1.EN.6.11.A1311 Material Requisitions for MOV | Issue ICR- Material Requisitions for MOV | Receive Company Comments- Material Requisitions for MOV | HE-IC-1570 | HE-IC-1580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.5 F&G layout | P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | Issue ICR-F&G Layout | Issue ICR- Datasheets for F&G Devices | HE-HS-0250 | HE-IC-1510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | Final Issue for Design/ Construction-Instrument Index | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | HE-IC-0530 | HE-IC-1550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | Receive Company Comments- Datasheets for F&G Devices | Re-Issue for Approval- Datasheets for F&G Devices | HE-IC-1520 | HE-IC-1530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | Re-Issue for Approval-Datasheets for Pig Signalers | Obtain Company Approval-Datasheets for Pig Signalers | HE-IC-1410 | HE-IC-1420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | Re-Issue for Approval- Addendum to DGs | Issue ICR-Datasheets for Pig Signalers | HE-IC-0030 | HE-IC-1390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | Issue ICR- Addendum to DGs | Issue ICR- Datasheets for PSV & Orifice (incl. RO) | HE-IC-0010 | HE-IC-1330 | SS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | Obtain Company Approval- Datasheets for Metering Skid | Final Issue for Design/ Construction-Datasheets for Custody Flow Metering Skid | HE-IC-1180 | HE-IC-1190 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | Final Issue for Design/ Construction-Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | Final Issue for Design/ Construction-Datasheets for Custody Flow Metering Skid | HE-PR-0350 | HE-IC-1190 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | Obtain Company Approval- Datasheet for GOV & ROV | Final Issue for Design/ Construction-Actuator Datasheet for GOV & ROV | HE-IC-1120 | HE-IC-1130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | Re-Issue for Approval- Datasheet for MOV | Obtain Company Approval- Datasheet for MOV | HE-IC-1050 | HE-IC-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Obtain Company Approval- Instrument Cable Block Diagram | Re-Issue for Approval-Instrument and F&G Cable Schedule | HE-IC-0820 | HE-IC-0930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | Re-Issue for Approval- Instrument Cable Block Diagram | Obtain Company Approval- Instrument Cable Block Diagram | HE-IC-0810 | HE-IC-0820 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | Re-Issue for Approval- Specification for Leak Detection System | Re-Issue for Approval- Instrument Cable Block Diagram | HE-IC-0270 | HE-IC-0810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | Issue ICR- Specification for Leak Detection System | Issue ICR- Instrument Cable Block Diagram | HE-IC-0250 | HE-IC-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | Obtain Company Approval- Instrument Cable Block Diagram | Final Issue for Design/ Construction-Instrument Cable Block Diagram | HE-IC-0820 | HE-IC-0830 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | Final Issue for Design/ Construction-Specification for RTU | Final Issue for Design/ Construction-Instrument Cable Block Diagram | HE-IC-0230 | HE-IC-0830 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Final Issue for Design/ Construction-Instrument Trench Layout | Final Issue for Design/ Construction-Loop Diagrams | HE-IC-1010 | HE-IC-0770 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Issue ICR- Instrument Cable Block Diagram | Issue ICR - Loop Diagrams | HE-IC-0790 | HE-IC-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | Re-Issue for Approval-Datasheets for Field Instruments / H2S Analyzers | Re-Issue for Approval - Hook-Up Diagram | HE-IC-1470 | HE-IC-0630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.A3 I/O list | Receive Company Comments- I/O list -Update | Re-Issue for Approval- I/O list -Update | HE-IC-0560 | HE-IC-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A3 I/O list | Re-Issue for Approval-Instrument index -Update | Re-Issue for Approval- I/O list -Update | HE-IC-0510 | HE-IC-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.A3 I/O list | Issue ICR- I/O list -Update | Receive Company Comments- I/O list -Update | HE-IC-0550 | HE-IC-0560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..1.EN.3.10 Equipment List | Final Issue for Design/ Construction-Process Datasheets - Pig Launcher / Receiver | Final Issue for Design/ Construction-Equipment List | HE-PR-0530 | HE-PR-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.10 Equipment List | P2543-R01-Oct24..1.EN.3.10 Equipment List | Issue ICR - Equipment List | Receive Company Comments - Equipment List | HE-PR-1030 | HE-PR-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR- Vent and Depressurization Report (for new facilities) | HE-PI-0320 | HE-PR-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | Obtain Company Approval- Vent and Depressurization Report (for new facilities) | Final Issue for Design/ Construction-Vent and Depressurization Report (for new facilities) | HE-PR-1000 | HE-PR-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | Re-Issue for Approval - Pre-commissioning and commissioning philosophy | Obtain Company Approval - Pre-commissioning and commissioning philosophy | HE-PR-0930 | HE-PR-0940 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | Issue ICR- Isolation & Tie-In philosophy | Receive Company Comments-Isolation & Tie-In philosophy | HE-PR-0850 | HE-PR-0860 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | Re-Issue for Approval- Operating and control philosophy , Safeguarding philosophy | Obtain Company Approval- Operating and control philosophy , Safeguarding philosophy | HE-PR-0750 | HE-PR-0760 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Re-Issue for Approval- Operating and control philosophy , Safeguarding philosophy | HE-PR-0140 | HE-PR-0750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | Re-Issue for Approval- Process Datasheets | Obtain Company Approval- Process Datasheets | HE-PR-0570 | HE-PR-0580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue for HAZOP Studies- P&ID's review | HE-PR-0060 | HE-PR-0130 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Obtain Company Approval-P&ID's | HE-PR-0140 | HE-PR-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | Receive Company Comments- Process Flow Diagrams ( New + Existing) | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | HE-PR-0050 | HE-PR-0060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..1.EN.2.1 Site Visit Report | Data Acquisition | Issue ICR - Site Visit /Survey Report | HE-SS-0010 | HE-SV-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.2.4 Constructability Review/ SIMOPS Report | Constructability Review Workshop | Issue ICR-Constructability Review / SIMOPS Report | HE-WS-0050 | HE-ST-0010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | Obtain Company Approval-Topographical Survey Report (Overall) | Final Issue for Design/ Construction-Topographical Survey Report (Overall) | HE-TS-0040 | HE-TS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.PM.12 Workshops | Receive Company Comments- Process Flow Diagrams ( New + Existing) | HAZID /ENVID/OHID/ PHSER Workshop | HE-PR-0050 | HE-WS-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.2 Survey & Studies | Project Kick off Meeting | Data Acquisition | ML1002 | HE-SS-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.30 TBE for Distibution Transformers | P2543-R01-Oct24..1.EN.9.6.30 TBE for Distibution Transformers | Issue ICR-TBE for Distribution Transformer | Receive Company Comments-TBE for Distribution Transformer | HE-EL-1450 | HE-EL-1460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | Receive Company Comments-Data sheet for Distribution Transformer | Re-Issue for Approval-Data sheet for Distribution Transformer | HE-EL-0680 | HE-EL-0690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | Obtain Company Approval-Cable Sizing Calculation | Final Issue for Design/ Construction-Cable Sizing Calculation | HE-EL-0460 | HE-EL-0470 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | Issue ICR-Update /New Load List | Issue ICR-Solar Panel System SLDs | HE-EL-0070 | HE-EL-0310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | Issue ICR-Update /New Load List | Issue ICR-Single Line Diagrams for LV Switchgear | HE-EL-0070 | HE-EL-0190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | Final Issue for Design/ Construction-Load List | Final Issue for Design/ Construction-Electrical Adequacy Check Report | HE-EL-0110 | HE-EL-0170 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | Issue ICR- Adequacy report of the Power supply requirements | Receive Company Comments- Adequacy report of the Power supply requirements | HE-EL-0130 | HE-EL-0140 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..1.EN.9.16 Electrical MTO | Issue ICR- Electrical Equipment Layout | Electrical 1st MTO | HE-EL-0490 | HE-EL-1810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..1.EN.9.16 Electrical MTO | Re-Issue for Approval- Electrical Equipment Layout | Electrical 2nd MTO | HE-EL-0510 | HE-EL-1830 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | Re-Issue for Approval- Electrical Installation Drawings | Obtain Company Approval- Electrical Installation Drawings | HE-EL-1770 | HE-EL-1780 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | Receive Company Comments- Electrical Installation Drawings | Re-Issue for Approval- Electrical Installation Drawings | HE-EL-1760 | HE-EL-1770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.26 TBE for Power & Control Cables | P2543-R01-Oct24..1.EN.9.6.26 TBE for Power & Control Cables | Obtain Company Approval-TBE for Power & Control Cables | Final Issue for Design/ Construction-TBE for Power & Control Cables | HE-EL-1540 | HE-EL-1550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.17.1 Ordering | P2543-R01-Oct24..1.EN.9.6.26 TBE for Power & Control Cables | RFQ, Receipt of Bid for Power & Control Cables | Issue ICR-TBE for Power & Control Cables | HP-BK-0010 | HE-EL-1510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.28 TBE for Distribution Boards | P2543-R01-Oct24..1.EN.9.6.28 TBE for Distribution Boards | Obtain Company Approval-TBE for Distribution Boards | Final Issue for Design/ Construction-TBE for Distribution Boards | HE-EL-1420 | HE-EL-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.28 TBE for Distribution Boards | P2543-R01-Oct24..1.EN.9.6.28 TBE for Distribution Boards | Re-Issue for Approval-TBE for Distribution Boards | Obtain Company Approval-TBE for Distribution Boards | HE-EL-1410 | HE-EL-1420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.27 TBE for UPS System | P2543-R01-Oct24..1.EN.9.6.27 TBE for UPS System | Re-Issue for Approval-TBE for UPS System | Obtain Company Approval-TBE for UPS System | HE-EL-1350 | HE-EL-1360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | Obtain Company Approval-Material Requisition for Power & Control Cables | Final Issue for Design/ Construction-Material Requisition for Power & Control Cables | HE-EL-1180 | HE-EL-1190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | Issue ICR-Cable Sizing Calculation | Issue ICR-Material Requisition for Power & Control Cables | HE-EL-0430 | HE-EL-1150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.18 Material Requisition for UPS System | P2543-R01-Oct24..1.EN.9.1.18 Material Requisition for UPS System | Issue ICR-Material Requisition for UPS System | Receive Company Comments-Material Requisition for UPS System | HE-EL-0910 | HE-EL-0920 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | Obtain Company Approval - Addendum to DGs | Issue ICR - Material Requisition for Active / Passive Shelters | HE-CS-0040 | HE-EL-0850 | FS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | Obtain Company Approval-Data Sheet for LV cables | Final Issue for Design/ Construction-Data Sheet for LV cables | HE-EL-0820 | HE-EL-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | Issue ICR-Data Sheet for LV cables | Receive Company Comments-Data Sheet for LV cables | HE-EL-0790 | HE-EL-0800 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | Re-Issue for Approval- Datasheet for Solar panel system | Obtain Company Approval- Datasheet for Solar panel system | HE-EL-0750 | HE-EL-0760 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | Obtain Company Approval - Material Selection Diagram | Final Issue for Design/ Construction-Material Selection Diagram | HE-CP-0040 | HE-CP-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | Re-Issue for Approval - Material Selection Diagram | Obtain Company Approval - Material Selection Diagram | HE-CP-0030 | HE-CP-0040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | Issue ICR - Material Selection Diagram | Receive Company Comments - Material Selection Diagram | HE-CP-0010 | HE-CP-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.PM.4 NOC Register | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | Final Issue for Design/ Construction-NOC Register | HE-PI-0580 | HC-GN-0290 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.PM.3 Project Procedure (PEP, Numbering Procedure) | P2543-R01-Oct24..1.PM.3 Project Procedure (PEP, Numbering Procedure) | Issue ICR-Project Procedure (PEP, Numbering Procedure etc.) | Receive Company Comments-Project Procedure (PEP, Numbering Procedure etc.) | HC-GN-0070 | HC-GN-0080 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | Project Kick off Meeting | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | ML1002 | HM-ME-1690 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.1.1.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Distribution Transformer | Receipt at site and inspection of Distribution Transformer | HM-ME-0980 | HM-ME-0990 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.1.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Distribution Transformer | Factory Acceptance Test of Distribution Transformer | HM-ME-0930 | HM-ME-0940 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | Project Kick off Meeting | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | ML1002 | HM-ME-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Field Instruments (Lot 1) | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | HM-ME-1580 | HM-ME-1590 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.15.2 Manufacturing & Ready for Dispatch | Testing and Inspection of Field Instruments | Packaging & Final Inspection-Field Instruments | HM-ME-1540 | HM-ME-1550 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.15.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Field Instruments | Manufacturing & Assembly of Field Instruments | HM-ME-1520 | HM-ME-1530 | FF | Completed | In Progress | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.1.15.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - CCTV Systems | Vendor Document Review of Field Instruments | ML1028-C20 | HM-ME-1520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.13.1 Ordering | P2543-R01-Oct24..PR.26.1.13.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Fire Fighting & Safety Equipment | Vendor Document Review of Fire Fighting & Safety Equipment | HP-ME-0980 | HM-ME-1920 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.1.2.LL.4.1 Ordering | P2543-R01-Oct24..PR.26.LL.4.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Ready for Dispatch of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | HP-ME-0630 | HM-ME-1260 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.4.1 Ordering | P2543-R01-Oct24..PR.26.LL.4.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Vendor Document Review of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | HP-ME-0630 | HM-ME-1220 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.6.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.6.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of Solar PV system | Packaging & Final Inspection-Solar PV system | HM-ME-1040 | HM-ME-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | P2543-R01-Oct24..PR.26.LL.6.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Material Requisition for Solar Panels | Manufacturing & Assembly of Solar PV system | HE-EL-1130 | HM-ME-1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.7.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Power Distribution Boards | Factory Acceptance Test of Power Distribution Boards | HM-ME-0830 | HM-ME-0840 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.LL.8.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - AC UPS System | Vendor Document Review of AC UPS | ML1319-C16 | HM-ME-0720 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.9.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.9.2 Manufacturing & Ready for Dispatch | Testing and Inspection of MOV | Packaging & Final Inspection-MOV | HM-ME-0630 | HM-ME-0640 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.9.1 Ordering | P2543-R01-Oct24..PR.26.LL.9.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for MOV | Vendor Document Review of MOV | HP-ME-0330 | HM-ME-0610 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.1.2.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Fire Suppression System | Receipt at site and inspection of Fire Suppression System | HM-ME-1820 | HM-ME-1830 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.2.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.2.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Fire Suppression System | Factory Acceptance Test of Fire Suppression System | HM-ME-1860 | HM-ME-1870 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.2.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.2.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Fire Suppression System | Manufacturing & Assembly of Fire Suppression System | HM-ME-1850 | HM-ME-1860 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.LL.22.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.22.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Custody Metering Skid | Factory Acceptance Test of Custody Metering Skid | HM-ME-0020 | HM-ME-0030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.LL.22.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.22.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Custody Metering Skid | Manufacturing & Assembly of Custody Metering Skid | HM-ME-0010 | HM-ME-0020 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.LL.18.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.18.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Gas Detectors | Ready for Dispatch of Gas Detectors | HM-ME-1450 | HM-ME-1460 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Earthing Material (Lot 1) | Receipt at site and inspection of Earthing Material (Lot 1) | HM-EL-0370 | HM-EL-0380 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.15.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Earthing Material | Ready for Dispatch of Earthing Material | HM-EL-0340 | HM-EL-0350 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.15.1 Ordering | P2543-R01-Oct24..PR.BK.15.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Earthing Material | Vendor Document Review of Earthing Material | HP-BK-0180 | HM-EL-0310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | 1st Telecom Bulk material MTO | 1st Telecom Bulk material MTO | HM-TL-0010 | HM-TL-0040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | Final Telecom Bulk material MTO | Final Telecom Bulk material MTO | HM-TL-0020 | HM-TL-0050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.9.1 Ordering | P2543-R01-Oct24..PR.BK.9.2 Manufacturing & Ready for Dispatch | 1st Telecom Bulk material MTO | 1st Telecom Bulk material MTO | HP-BK-0500 | HM-TL-0010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.8.1 Ordering | P2543-R01-Oct24..PR.BK.8.2 Manufacturing & Ready for Dispatch | Final Instrumentation Bulk material MTO | Final Instrumentation Bulk material MTO | HP-BK-0470 | HM-IC-0020 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | 1st Electrical Bulk material MTO | 1st Electrical Bulk material MTO | HM-EL-0490 | HM-EL-0520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.6.1 Ordering | P2543-R01-Oct24..PR.BK.6.2 Manufacturing & Ready for Dispatch | 1st Pipeline Bulk material MTO | 1st Pipeline Bulk material MTO | HP-BK-0380 | HM-PL-0850 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | 1st Structural Bulk material MTO | 1st Structural Bulk material MTO | HM-CS-0080 | HM-CS-0110 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Cable Trays (Lot 1) | Receipt at site and inspection of Cable Trays (Lot 2) | HM-EL-0270 | HM-EL-0280 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.13.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Cable Trays | Manufacturing & Assembly of Cable Trays | HM-EL-0210 | HM-EL-0220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Material Requisition for Power & Control Cables | Manufacturing & Assembly of Power & Control Cables | HE-EL-1190 | HM-EL-0020 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.BK.16.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.16.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of MCT | Factory Acceptance Test of MCT | HM-EL-0420 | HM-EL-0430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Receipt at site and inspection of Line Pipes - Lot 1 (Coated) | Receipt at site and inspection of Line Pipes - Lot 2 (Coated) | HM-PL-0080 | HM-PL-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | Manufacturing & Receive Plates at Fabrication Shop - Lot 1 | Complete Line Pipe Production - Lot 1 | HM-PL-0020 | HM-PL-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.2.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.2.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Pigging & Split Tee | Testing and Inspection of Pigging & Split Tee | HM-PL-0780 | HM-PL-0790 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.24.1 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.24.1 Manufacturing & Ready for Dispatch | Testing and Inspection of Hot Tapping Material | Packaging & Final Inspection-Hot Tapping Material | HM-PL-0270 | HM-PL-0280 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.24.1 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.24.1 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Hot Tapping Material | Ready for Dispatch of Hot Tapping Material | HM-PL-0280 | HM-PL-0290 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..ML.4 Commissioning and PAC | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | Commission New pipelines system - 4" Nitrogen Pipeline | CCM-PM4510 | ML2019-F03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Project Kick off Meeting | Mobilization of Automatic Welding Machines at site | ML1002 | ML1559-E01 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.6.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Solar PV system | Receive at Site - Solar Power System | HM-ME-1090 | ML1429-D17 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of CP System - Permanent Material | Receive at Site - Cathodic Protection (CP) System | HM-PL-0430 | ML1549-D22 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Pig Launchers & Receivers (52" Line) | Receive at Site - Pig Launcher & Receiver | HM-ME-0480 | ML1519-D04 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.17.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Leak Detection System | Receive at Site - Leak Detection System | HM-ME-0280 | ML1053-D23 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of ROV/ GOV (1st Lot) | Receive at Site - MOV/ROV/GOV Valves | HM-ME-0580 | ML1024-D06 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.13.11 Cathodic Protection Work | P2543-R01-Oct24..ML.PR Procurement | Place LOA/FOA - Cathodic Protection Work | Issue Purchase Order (Final) - CP System | HS-GN-0530 | ML1038-C10 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.10.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for ROV/ GOV | Issue Purchase Order (Final) - MOV/ROV/GOV Valves | HP-ME-0280 | ML1022-C07 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.12.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Pig Launchers & Receivers | Issue Purchase Order (Final) - Pig Launcher & Receiver | HP-ME-0230 | ML1279-C05 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.1.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Hot Induction Bend | Issue Purchase Order (Final) - Hot Bends | HP-ME-1190 | ML1229-C02 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.1.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Manual/ Ball/ Globe/ Check/ Plug Valves | Issue Purchase Order (Final) - Manual Ball Valves | HP-ME-1090 | ML1043-C14 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Civil UG layout | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-0530 | ML1035-B26 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-TYPICAL LIGHTING POLE FOUNDATION DETAILS | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-1010 | ML1035-B26 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Gas metering skid foundation drawings | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-0830 | ML1035-B26 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-0350 | ML1034-B25 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical Detailed Drawing - Jib Crane Foundation | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-1070 | ML1034-B25 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-1430 | ML1034-B25 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | HE-TL-0350 | ML1033-B22 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Instrument Trench Layout | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | HE-IC-1010 | ML1032-B21 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Earthing Layout | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | HE-EL-1670 | ML1032-B21 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue for HAZOP Studies- Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | HE-PI-0410 | ML1012-B06 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-TYPICAL GA AND RC DETAILS OF IMPACT WALL | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-1250 | ML1209-B27 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical duct bank detail drawing | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-0230 | ML1209-B27 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.9.18 MR for Hot Induction Bends | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-MR for Hot Induction Bends | Issue MR (Final) - Hot Bends | HE-PL-1790 | ML1189-B16 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Electrical Equipment Layout | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | HE-EL-0530 | ML1179-B11 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.15 Pipeline Station approach drawing - 4" Nitrogen | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Pipeline Station approach drawing-4" | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | HE-PL-2730 | ML1059-B28 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | P2543-R01-Oct24..ML.GE General | Final Issue for Design/ Construction-Overall Pipeline Route Map - 56" | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (56" Pipeline) | HE-PL-0170 | ML1139-A06 | FF | Completed | Completed | 50
P2543-R01-Oct24..1.EN.4.4 Project HSE Plan | P2543-R01-Oct24..ML.GE General | Final Issue for Design/ Construction-Project HSE Plan | Issue Project Execution Plan (PEP), Coordination, Engineering, Procurement, HSE and Quality Procedures-Final Issue | HE-HS-0050 | ML1001-A01 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.4 Commissioning and PAC | P2543-R01-Oct24..ML Milestones | Commission New pipelines system - 4" Water line | Achieve PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | ML2029-F04 | ML1040 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Pipeline welding - 56" Sales Gas Pipeline (50% Welding) | Project Finish | ML1589-E04 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 02 to BVS-03 | Project Finish | ML1779-E23 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Pipeline welding - 52" Sales Gas Pipeline - 50% Welding | Project Finish | ML1699-E15 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..ML Milestones | HSE | Project Finish | CAB-4410 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Site Grading & ROW along the Pipeline - 56" Sales Gas Pipeline | Project Finish | ML1569-E02 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete foundations for Launchers and Receiver- 56" Sales Gas Pipeline | Project Finish | ML1619-E07 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..ML Milestones | Process | Project Finish | CAB-4400 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | Project Finish | ML1979-E43 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Process | General | CAB-4400 | CAB-5290 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Electrical | Quality Dossier | CAB-4450 | CAB-5300 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Telecom | Quality Dossier | CAB-4470 | CAB-5300 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..1.PM.3 Project Procedure (PEP, Numbering Procedure) | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Final Issue for Design/ Construction-Project Procedure (PEP, Numbering Procedure) | Quality Dossier | HC-GN-0110 | CAB-5300 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Pipeline | Quality Dossier | CAB-4480 | CAB-5300 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Detailed crossing drawings-52" | Pipeline | HE-PL-3030 | CAB-4480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline Specifications - Addendum to DGS | Pipeline | HE-PL-0110 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline Station approach drawing - 56" | Pipeline | HE-PL-2610 | CAB-4480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Pipeline | ML1059-B28 | CAB-4480 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.10.23 TBE for Hot Induction Bends | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Hot Induction Bends | Pipeline | HE-PL-2130 | CAB-4480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Telecom | HE-TL-0290 | CAB-4470 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Telecom | HE-TL-0650 | CAB-4470 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Telecom | HE-TL-0530 | CAB-4470 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Telecom | HE-TL-0470 | CAB-4470 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Actuator Datasheet for MOVs | Instrumentation & Control | HE-IC-1070 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- Specification for RTU | Instrumentation & Control | HE-IC-0190 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisitions for Leak Detection System | Instrumentation & Control | HE-IC-1790 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Typical Installation Drawings | Instrumentation & Control | HE-IC-0710 | CAB-4460 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.A33 TBE for PRS (Pressure Reduction Skid) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for PRS | Instrumentation & Control | HE-IC-2210 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Instrumentation & Control | HE-IC-1430 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Datasheets for Field Instruments / H2S Analyzers | Instrumentation & Control | HE-IC-1490 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Instrument Trench Layout | Instrumentation & Control | HE-IC-1010 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Cable Routing Layout | Electrical | HE-EL-1610 | CAB-4450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Electrical | ML1219-B19 | CAB-4450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Electrical Equipment Layout | Electrical | HE-EL-0530 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Piping Material Specification | Piping | HE-PI-0050 | CAB-4440 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipe Wall Thickness Calculation | Piping | HE-PI-0240 | CAB-4440 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Overall Plot Plan- 4" N2 Source Pipeline | Piping | HE-PI-0510 | CAB-4440 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping | ML1179-B11 | CAB-4440 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | Mechanical | ML1030 | CAB-4430 | FF | Not Started | Not Started | 9
P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Addendum to DGs | Civil & Structural | HE-CS-0050 | CAB-4420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Gas metering skid foundation drawings | Civil & Structural | HE-CS-0830 | CAB-4420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.33 Filter Foundation GA and Details | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-FILTER FOUNDATION GA AND DETAILS | Civil & Structural | HE-CS-0950 | CAB-4420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Civil / Structural Drawings for Launcher/ Receiver facilities | Civil & Structural | ML1199-B24 | CAB-4420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.5 F&G layout | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-F&G layout | HSE | HE-HS-0290 | CAB-4410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Relief, Vent and Blowdown philosophy | Process | HE-PR-0830 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Process | ML1014-B10 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..4.4.AB As-Built & Final Documentation | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | Demolitionbilization | CCM-PM4510 | A3980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Obtain Company Approval-Pre-commissioning and Commissioning Plan | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | C-COM-830 | C-COM-840 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Receive Company Comments-Pre-commissioning and Commissioning Plan | Re-Issue for Approval-Pre-commissioning and Commissioning Plan | C-COM-810 | C-COM-820 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Issue ICR-Pre-commissioning and Commissioning Plan | HE-PR-0950 | C-COM-800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Typical trench detail drawing | Issue ICR-Construction Procedures / Method Statements / ITPs | HE-CS-0170 | C-COM-750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.2 Telecom MTO | P2543-R01-Oct24..1.1.BK.9.1 Ordering | Telecom 1st MTO | 1st Telecom Bulk material MTO | HE-TL-0850 | HP-BK-0500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.16 Electrical MTO | P2543-R01-Oct24..1.1.BK.7.1 Ordering | Electrical 1st MTO | 1st Electrical Bulk material MTO | HE-EL-1810 | HP-BK-0420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..1.1.BK.4.1 Ordering | Piping MTO - 1st | 1st Piping Bulk material MTO | HE-PI-1260 | HP-BK-0340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.13.1 Ordering | P2543-R01-Oct24..1.1.BK.13.1 Ordering | RFQ, Receipt of Bid for Cable Trays | Prepare TBE and Company approval for Cable Trays | HP-BK-0110 | HP-BK-0120 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.1.1 Ordering | P2543-R01-Oct24..1.1.1.1.1 Ordering | Prepare TBE and Company approval for Hot Incution Bend | Commercial Clarifications & Placement of PO for Hot Induction Bend | HP-ME-1180 | HP-ME-1190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.43 Material Requisition for Pig Signaler | P2543-R01-Oct24..1.1.1.19.1 Ordering | Issue ICR- Material Requisition for Pig Signaler | RFQ, Receipt of Bid for Pig Signaler | HE-PL-1930 | HP-ME-1120 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | P2543-R01-Oct24..1.1.BK.1.1 Ordering | Issue ICR-MR for Ball valves/ Plug Valves | RFQ, Receipt of Bid for Manual/Ball/ Globe/ Check/ Plug Valves | HE-PI-1020 | HP-ME-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.16.1 Ordering | P2543-R01-Oct24..1.1.1.16.1 Ordering | RFQ, Receipt of Bid for Line Pipes (Coated) | Prepare TBE and Company approval for Line Pipes (Coated) | HP-ME-1020 | HP-ME-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.16.1 Ordering | P2543-R01-Oct24..1.1.1.16.1 Ordering | Prepare TBE and Company approval for Line Pipes (Coated) | Commercial Clarifications & Placement of PO for Line Pipes (Coated) | HP-ME-1030 | HP-ME-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | P2543-R01-Oct24..1.1.2.LL.6.1 Ordering | Issue ICR-Material Requisition for Solar Panels | RFQ, Receipt of Bid for Solar PV system | HE-EL-1090 | HP-ME-0510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.12.1 Ordering | P2543-R01-Oct24..1.1.2.LL.12.1 Ordering | RFQ, Receipt of Bid for Pig Launchers & Receivers | Prepare TBE and Company approval for Pig Launchers & Receivers | HP-ME-0210 | HP-ME-0220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.17.1 Ordering | P2543-R01-Oct24..1.1.2.LL.17.1 Ordering | RFQ, Receipt of Bid for Leak Detection System | Prepare TBE and Company approval for Leak Detection System | HP-ME-0110 | HP-ME-0120 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.19.1 Ordering | P2543-R01-Oct24..1.1.2.LL.19.1 Ordering | RFQ, Receipt of Bid for FOC Cables | Prepare TBE and Company approval for FOC Cables | HP-BK-0060 | HP-BK-0070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.20 Material Requisition for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.1.2.25.13.1 Ordering | Issue ICR-Material Requisition for Fire Fighting & Safety Eqpt | RFQ, Receipt of Bid for Fire Fighting & Safety Equipment | HE-HS-1092 | HP-ME-0960 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.13.1 Ordering | P2543-R01-Oct24..1.1.2.25.13.1 Ordering | Prepare TBE and Company approval for Fire Fighting & Safety Equipment | Commercial Clarifications & Placement of PO for Fire Fighting & Safety Equipment | HP-ME-0970 | HP-ME-0980 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.3.1 Ordering | P2543-R01-Oct24..1.1.2.25.3.1 Ordering | Prepare TBE and Company approval for HVAC Equipment | Commercial Clarifications & Placement of PO for HVAC Equipment | HP-ME-0870 | HP-ME-0880 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | P2543-R01-Oct24..1.1.2.25.3.1 Ordering | Issue ICR- Addendum to DGS | RFQ, Receipt of Bid for HVAC Equipment | HE-ME-0010 | HP-ME-0860 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.9 Material Requisitions for Fire & Gas Detectors | P2543-R01-Oct24..1.1.2.LL.18.1 Ordering | Issue ICR- Material Requisitions for Gas Detectors | RFQ, Receipt of Bid for Gas Detectors | HE-IC-1870 | HP-ME-0710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.14.1 Ordering | P2543-R01-Oct24..1.1.2.25.14.1 Ordering | RFQ, Receipt of Bid for Access Switch, Fiber Optic Patch Panel and Media Converter | Prepare TBE and Company approval for Access Switch, Fiber Optic Patch Panel and Media Converter | HP-ME-0660 | HP-ME-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.2.12.12 Building | Project Kick off Meeting | Building RFQ & Quotation Receipt | ML1002 | HS-CN-0560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.11 Hot Tapping | P2543-R01-Oct24..1.2.12.11 Hot Tapping | Hot Tapping Complete Evaluation (Internal) | Hot Tapping Subcontract Award | HS-CN-0530 | HS-CN-0540 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | P2543-R01-Oct24..1.2.12.2 NDRC | Final Issue for Design/ Construction-Overall Pipeline Route Map - 56" | NDRC RFQ & Quotation Receipt | HE-PL-0170 | HS-CN-0060 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.9 HSE Studies | P2543-R01-Oct24..1.2.13.9 HSE Studies | Prepare/Issue Scope of Work - HSE Studies | Receive Bids - HSE Studies | HS-GN-0070 | HS-GN-0080 | FS | Completed | Completed | 2
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | Final Issue for Design/ Construction-Specification for Leak Detection System | RFQ, Receipt of Bid - Modification of Existing DCS | HE-IC-0290 | HS-GN-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.4 Topographical survey & Geotechnical Investigation | P2543-R01-Oct24..1.2.13.4 Topographical survey & Geotechnical Investigation | Prepare/Issue Scope of Work - Topographical survey & Geotechnical Investigation | Receive Bids - Topographical survey & Geotechnical Investigation | HS-GN-0130 | HS-GN-0140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | Issued for Review - Passive cooled shelter foundation GA and details | Review Company Comments - Passive cooled shelter foundation GA and details | HE-CS-1270 | HE-CS-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | Re-Issue for Approval - Impact Wall GA and RC (type) details | Obtain Company Approval - Impact Wall GA and RC (type) details | HE-CS-1230 | HE-CS-1240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | Issued for Review - Valve pit foundation GA and RC (type) details | Review Company Comments - Valve pit foundation GA and RC (type) details | HE-CS-1150 | HE-CS-1160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | Obtain Company Approval - Valve pit foundation GA and RC (type) details | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | HE-CS-1180 | HE-CS-1190 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | Issued for Review - Calculations for Pipe supports | Review Company Comments - Calculations for Pipe supports | HE-CS-1090 | HE-CS-1100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | Re-Issue after HAZOP /Review Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Issued for Review - Typical Detailed Drawing - Jib Crane Foundation | HE-PI-0350 | HE-CS-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | Issued for Review - Design Cal. for Typical Skid Foundations | Issued for Review - Solar panel foundation details | HE-CS-0670 | HE-CS-0850 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | Issued for Review - Design Cal. for Typical Skid Foundations | Issued for Review - Gas metering skid foundation drawings | HE-CS-0670 | HE-CS-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | Review Company Comments - Gas metering skid foundation drawings | Re-Issue for Approval - Gas metering skid foundation drawings | HE-CS-0800 | HE-CS-0810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | Review Company Comments - Pressure Reduction Skid and Leak Detection Drawings | Re-Issue for Approval - Pressure Reduction Skid and Leak Detection Drawings | HE-CS-0740 | HE-CS-0750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | Re-Issue for Approval - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | Obtain Company Approval - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | HE-CS-0630 | HE-CS-0640 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.28 Calculation for Pig launcher and receiver foundations | P2543-R01-Oct24..1.EN.8.28 Calculation for Pig launcher and receiver foundations | Obtain Company Approval - Calculation for Pig launcher and receiver foundations | Final Issue for Design/ Construction-Calculation for Pig launcher and receiver foundations | HE-CS-0580 | HE-CS-0590 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | Issued for Review - Site grading, road, drainage and fence layout | Review Company Comments - Site grading, road, drainage and fence layout | HE-CS-0430 | HE-CS-0440 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.17 Typical details of protection slab to protect existing UG pipe at road crossing | P2543-R01-Oct24..1.EN.8.17 Typical details of protection slab to protect existing UG pipe at road crossing | Review Company Comments - Typical details of protection slab to protect existing UG pipe at road crossing | Re-Issue for Approval - Typical details of protection slab to protect existing UG pipe at road crossing | HE-CS-0380 | HE-CS-0390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | Obtain Company Approval - Typical trench detail drawing | Final Issue for Design/ Construction-Typical trench detail drawing | HE-CS-0160 | HE-CS-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction-Standard drawings for Anchor bolt | Issued - Civil MTO 2 | HE-CS-0110 | HE-CS-1550 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Issued - Civil MTO 2 | HE-CS-0290 | HE-CS-1550 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction-TYPICAL GA AND RC DETAILS OF IMPACT WALL | Issued - Civil MTO 2 | HE-CS-1250 | HE-CS-1550 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.17 Typical details of protection slab to protect existing UG pipe at road crossing | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction-Typical details of protection slab to protect existing UG pipe at road crossing | Issued - Civil MTO 2 | HE-CS-0410 | HE-CS-1550 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..1.EN.8.41 Misc. supports | Review Company Comments - Misc. supports and civil/ structural details | Re-Issue for Approval - Misc. supports and civil/ structural details | HE-CS-1460 | HE-CS-1470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..1.EN.8.41 Misc. supports | Issued for Review - Misc. supports and civil/ structural details | Review Company Comments - Misc. supports and civil/ structural details | HE-CS-1450 | HE-CS-1460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | Re-Issue for Approval-Piping Stress Analysis & Report | Issued for Review - Pipe Sleeper layout and details. | HE-PI-1160 | HE-CS-1390 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | Issued for Review - Calculations for Pipe supports | Issued for Review - Typical Structural Steel and Foundation details for pipe support | HE-CS-1090 | HE-CS-1330 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | Obtain Company Approval-Material Requisitions for Sales Gas CRS Filters | Final Issue for Design/ Construction-Material Requisitions for Sales Gas CRS Filters | HE-ME-0160 | HE-ME-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | Final Issue for Design/ Construction-Datasheet for Sales Gas CRS Filters | Final Issue for Design/ Construction-Material Requisitions for Sales Gas CRS Filters | HE-ME-0110 | HE-ME-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | Issue ICR- Process Datasheets - Filters (At Sweihan CRS) | Issue ICR-Datasheet for Sales Gas CRS Filters | HE-PR-0430 | HE-ME-0070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | Obtain Company Approval-Datasheet for Sales Gas CRS Filters | Final Issue for Design/ Construction-Datasheet for Sales Gas CRS Filters | HE-ME-0100 | HE-ME-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Issue ICR- Process Flow Diagrams ( New + Existing) | Issue ICR- Plot plan - BVS | HE-PR-0040 | HE-PI-0530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Final Issue for Design/ Construction-Vent and Depressurization Report (for new facilities) | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | HE-PR-1010 | HE-PI-0580 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Issue ICR-Topographical Survey Report (Overall) | Re-Issue after incorporating HAZOP /Review Comments - 4" N2 Source Pipeline | HE-TS-0010 | HE-PI-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | Receive Company Comments- Overall Plot Plan - 52" Pipeline SWEIHAN CRS | HE-PI-0390 | HE-PI-0400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue for HAZOP Studies- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0060 | HE-PI-0340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction-Topographical Survey Report (Overall) | Final Issue for Design/ Construction-Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-TS-0050 | HE-PI-0370 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | Re-Issue for Approval-Pipe Wall Thickness Calculation | Obtain Company Approval-Pipe Wall Thickness Calculation | HE-PI-0220 | HE-PI-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | Issue ICR-Piping Material Specifications | Receive Company Comments-Piping Material Specifications | HE-PI-0010 | HE-PI-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | Re-Issue for Approval-Piping GA Drawings for 591-BVS-01 | Re-Issue for Approval-Piping Isometrics | HE-PI-0800 | HE-PI-1220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | Re-Issue for Approval - Pipeline Stress Analysis Report | Re-Issue for Approval-Piping Stress Analysis & Report | HE-PL-2830 | HE-PI-1160 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | Final Issue for Design/ Construction-Datasheet for Plug valves | Final Issue for Design/ Construction-Material Requisition for Ball/ Plug Valves | HE-PI-1000 | HE-PI-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.17 Line List | P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | Issue ICR- Line List | Issue ICR- Datasheet for Plug Valves | HE-PR-1090 | HE-PI-0960 | FF | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | Vendor Document Review of Pig Launchers & Receivers | Re-Issue for Approval-Piping GA for 4" N2 Source Pipeline | HM-ME-0410 | HE-PI-0740 | SS | Completed | Not Started | 8
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | Issue ICR- Process Simulations Report | Issue ICR-Piping GA for 52" Pipeline SWEIHAN CRS | HE-PR-0610 | HE-PI-0660 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | Obtain Company Approval-Piping GA-56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0620 | HE-PI-0630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Re-Issue after HAZOP /Review Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR-Piping GA-56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0350 | HE-PI-0600 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.7.10 3D Model | 60% Model Review Report | 90% Model Review Report | HE-PI-0160 | HE-PI-0180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.7.10 3D Model | 30% Model Review Report | 60% Model Review | HE-PI-0140 | HE-PI-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.7.10 3D Model | 60% Model Review Report | 90% Model Review | HE-PI-0160 | HE-PI-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | Re-Issue for Approval- HAZOP reviews Report for all areas | Obtain Company Approval- HAZOP reviews Report for all areas | HE-HS-0690 | HE-HS-0700 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.19 HAZID/ ENVID/ OHID Close out Report | P2543-R01-Oct24..1.EN.4.19 HAZID/ ENVID/ OHID Close out Report | Obtain Company Approval-HAZID/ ENVID/ OHID Close out Report | Final Issue for Design/ Construction-HAZID/ ENVID/ OHID Close out Report | HE-HS-0640 | HE-HS-0650 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | Re-Issue for Approval-HAZID/ ENVID/ OHID Report | Obtain Company Approval-HAZID/ ENVID/ OHID Report | HE-HS-0570 | HE-HS-0580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | Study & Issue ICR- HSEIA Study Report | Receive Company Comments- HSEIA Study Report | HE-HS-0490 | HE-HS-0500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | Re-Issue for Approval- HSEIA Study Report | Obtain Company Approval- HSEIA Study Report | HE-HS-0510 | HE-HS-0520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.16 Datasheets for fire fighting and safety equipment | P2543-R01-Oct24..1.EN.4.16 Datasheets for fire fighting and safety equipment | Receive Company Comments-Data Sheets for Fire Fighting & Safety Eqpt | Re-Issue for Approval-Data Sheets for Fire Fighting & Safety Eqpt | HE-HS-0440 | HE-HS-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | Receive Company Comments-F&G Cause and Effect | Re-Issue for Approval-F&G Cause and Effect | HE-HS-0320 | HE-HS-0330 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.4.5 F&G layout | Final Issue for Design/ Construction-Overall Plot Plan- 4" N2 Source Pipeline | Final Issue for Design/ Construction-F&G layout | HE-PI-0510 | HE-HS-0290 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.4.5 F&G layout | P2543-R01-Oct24..1.EN.4.5 F&G layout | Issue ICR-F&G Layout | Receive Company Comments-F&G Layout | HE-HS-0250 | HE-HS-0260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | Final Issue for Design/ Construction-HAZID / ENVID / OHID Procedure | Final Issue for Design/ Construction-HAZOP Procedure | HE-HS-0170 | HE-HS-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | Re-Issue for Approval-HSE Philosophy | Obtain Company Approval-HSE Philosophy | HE-HS-0090 | HE-HS-0100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | Re-Issue for Approval-TBE for Fire Fighting & Safety Eqpt | Obtain Company Approval-TBE for Fire Fighting & Safety Eqpt | HE-HS-1170 | HE-HS-1180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.20 Material Requisition for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.EN.4.20 Material Requisition for Fire Fighting and Safety Equipment | Issue ICR-Material Requisition for Fire Fighting & Safety Eqpt | Receive Company Comments-Material Requisition for Fire Fighting & Safety Eqpt | HE-HS-1092 | HE-HS-1100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | Re-Issue for Approval-HSE Action Tracking Register (Hazards and Effects Register) | Obtain Company Approval-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-1050 | HE-HS-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | Obtain Company Approval-HSE Action Tracking Register (Hazards and Effects Register) | Final Issue for Design/ Construction-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-1060 | HE-HS-1070 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.4.21 HAZOP close out report | P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | Issue ICR- HAZOP Close Out Report | Re-Issue for Approval-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-0730 | HE-HS-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.19 HAZID/ ENVID/ OHID Close out Report | P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | Issue ICR-HAZID/ ENVID/ OHID Close out Report | Re-Issue for Approval-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-0610 | HE-HS-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.11 QRA Report | P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | Final Issue for Design/ Construction-QRA Report | Issue ICR-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-0830 | HE-HS-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Obtain Company Approval-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Final Issue for Design/ Construction-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-HS-1000 | HE-HS-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.11 QRA Report | P2543-R01-Oct24..1.EN.4.12 PHSER Report | Issue ICR-QRA Report | Issue ICR-PHSER Report | HE-HS-0790 | HE-HS-0850 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | Issue ICR- Specification for Leak Detection System | Issue ICR - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | HE-IC-0250 | HE-TL-0070 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Re-Issue for Approval- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Re-Issue for Approval- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0210 | HE-TL-0510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Re-Issue for Approval-Telecom Equipment Layout | Re-Issue for Approval- Telecom Cable Schedule | HE-TL-0750 | HE-TL-0810 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Issue ICR - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Issue ICR- Telecom Cable Schedule | HE-TL-0070 | HE-TL-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | HE-TL-0470 | HE-TL-0710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.19.1 Ordering | P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | RFQ, Receipt of Bid for FOC Cables | Issue ICR-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HP-BK-0060 | HE-TL-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | Issue ICR-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Receive Company Comments-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0610 | HE-TL-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Final Issue for Design/ Construction-Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | HE-TL-0110 | HE-TL-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Re-Issue for Approval- Specification for Leak Detection System | Re-Issue for Approval- FOC Block diagram (Telecom) | HE-IC-0270 | HE-TL-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Re-Issue for Approval- Specification for RTU | Re-Issue for Approval- FOC Block diagram (Telecom) | HE-IC-0210 | HE-TL-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Issue ICR- FOC Block diagram (Telecom) | Receive Company Comments- FOC Block diagram (Telecom) | HE-TL-0430 | HE-TL-0440 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Re-Issue for Approval - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Re-Issue for Approval- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-TL-0090 | HE-TL-0270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.22 TBE for Linepipes | P2543-R01-Oct24..1.EN.1.10.22 TBE for Linepipes | Receive Company Comments - TBE for Line pipes | Final Issue for Design/ Construction-TBE for Line pipes | HE-PL-2060 | HE-PL-2070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..1.EN.6.11.43 Material Requisition for Pig Signaler | Obtain Company Approval - Overall Pipeline Route Map - 52" | Issue ICR- Material Requisition for Pig Signaler | HE-PL-0220 | HE-PL-1930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.20 MR for Isolating Joints | P2543-R01-Oct24..1.EN.1.9.20 MR for Isolating Joints | Issue ICR - MR for Isolating Joints | Receive Company Comments - MR for Isolating Joints | HE-PL-1870 | HE-PL-1880 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.20 MR for Isolating Joints | P2543-R01-Oct24..1.EN.1.9.20 MR for Isolating Joints | Re-Issue for Approval - MR for Isolating Joints | Obtain Company Approval - MR for Isolating Joints | HE-PL-1890 | HE-PL-1900 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.12 Data Sheet - Pipeline Pigging Tees | P2543-R01-Oct24..1.EN.1.60.14 Data Sheet - Anchor Flange | Issue ICR - Data Sheet - Pigging Tees | Issue ICR - Data Sheet - Anchor Flange (If Required) | HE-PL-1450 | HE-PL-1510 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.11 Data Sheet - Pipeline Isolating Joints | P2543-R01-Oct24..1.EN.1.60.11 Data Sheet - Pipeline Isolating Joints | Re-Issue for Approval - Data Sheet - Isolating joints | Obtain Company Approval - Data Sheet - Isolating joints | HE-PL-1410 | HE-PL-1420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.11 Data Sheet - Pipeline Isolating Joints | P2543-R01-Oct24..1.EN.1.60.11 Data Sheet - Pipeline Isolating Joints | Receive Company Comments - Data Sheet - Isolating joints | Re-Issue for Approval - Data Sheet - Isolating joints | HE-PL-1400 | HE-PL-1410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.11 Data Sheet - Pipeline Isolating Joints | P2543-R01-Oct24..1.EN.1.60.11 Data Sheet - Pipeline Isolating Joints | Issue ICR - Data Sheet - Isolating joints | Receive Company Comments - Data Sheet - Isolating joints | HE-PL-1390 | HE-PL-1400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.6 Pipeline Location Class selection Report | P2543-R01-Oct24..1.EN.1.6 Pipeline Location Class selection Report | Issue ICR - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | Receive Company Comments - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | HE-PL-0790 | HE-PL-0800 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | P2543-R01-Oct24..1.EN.1.6 Pipeline Location Class selection Report | Final Issue for Design/ Construction-Overall Pipeline Route Map - 56" | Final Issue for Design/ Construction-Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | HE-PL-0170 | HE-PL-0830 | FF | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.3 Pipeline Upheavl Calculation | P2543-R01-Oct24..1.EN.1.4 Pipeline Road and Railway Crossing Calculation Report | Issue ICR - Pipeline Upheaval Calculation | Issue ICR - Pipeline Road Crossing Calculation Report | HE-PL-0610 | HE-PL-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | P2543-R01-Oct24..1.EN.1.40 Specification - Split Tee | Issue ICR - Pipeline Specifications - Addendum to DGS | Issue ICR - Specification - Split Tee | HE-PL-0070 | HE-PL-0430 | FS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.1.27 Pipeline Typical Drawings | P2543-R01-Oct24..1.EN.1.27 Pipeline Typical Drawings | Issue ICR - Pipeline Typical Drawings | Receive Company Comments - Pipeline Typical Drawings | HE-PL-0370 | HE-PL-0380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.27 Pipeline Typical Drawings | P2543-R01-Oct24..1.EN.1.27 Pipeline Typical Drawings | Re-Issue for Approval - Pipeline Typical Drawings | Obtain Company Approval - Pipeline Typical Drawings | HE-PL-0390 | HE-PL-0400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.1.13 Pipeline Schematic Arrangement- 56", 52" and 4" Pipline | Issue ICR- P&ID's | Issue ICR - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | HE-PR-0110 | HE-PL-0310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.13 Pipeline Schematic Arrangement- 56", 52" and 4" Pipline | P2543-R01-Oct24..1.EN.1.13 Pipeline Schematic Arrangement- 56", 52" and 4" Pipline | Obtain Company Approval - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | Final Issue for Design/ Construction-Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | HE-PL-0340 | HE-PL-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | Issue ICR-Topographical Survey Report (Overall) | Re-Issue for Approval - Overall Pipeline Route Map - 4" | HE-TS-0010 | HE-PL-0270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | Issue ICR - Overall Pipeline Route Map - 4" | Receive Company Comments - Overall Pipeline Route Map - 4" | HE-PL-0250 | HE-PL-0260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | Issue ICR - Overall Pipeline Route Map - 56" | Receive Company Comments - Overall Pipeline Route Map - 56" | HE-PL-0130 | HE-PL-0140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.55 Crossing Schedule-4" | P2543-R01-Oct24..1.EN.1.55 Crossing Schedule-4" | Receive Company Comments - Crossing Schedule-4" | Re-Issue for Approval - Crossing Schedule-4" | HE-PL-3180 | HE-PL-3190 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.44 Detailed crossing drawings-4" | P2543-R01-Oct24..1.EN.1.44 Detailed crossing drawings-4" | Obtain Company Approval - Detailed crossing drawings-4" | Final Issue for Design/ Construction-Detailed crossing drawings-4" | HE-PL-3140 | HE-PL-3150 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | Re-Issue for Approval - Detailed crossing drawings - 56" | Obtain Company Approval - Detailed crossing drawings - 56" | HE-PL-2890 | HE-PL-2900 | FF | Completed | Completed | 10
P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | Final Issue for Design/ Construction-Pipeline Station approach drawing - 56" | Final Issue for Design/ Construction-Pipeline Stress Analysis Report | HE-PL-2610 | HE-PL-2850 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | Issue ICR - Pipeline Stress Analysis Report | Receive Company Comments - Pipeline Stress Analysis Report | HE-PL-2810 | HE-PL-2820 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.4 Pipeline Road and Railway Crossing Calculation Report | P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | Issue ICR - Pipeline Road Crossing Calculation Report | Issue ICR - Pipeline Stress Analysis Report | HE-PL-0670 | HE-PL-2810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.1 Pipeline Route Verification and Selection Report | P2543-R01-Oct24..1.EN.1.1 Pipeline Route Verification and Selection Report | Issue ICR - Pipeline Route Verification and Selection Report | Receive Company Comments - Pipeline Route Verification and Selection Report | HE-PL-2750 | HE-PL-2760 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | Issue ICR-Topographical Survey Report (Overall) | Issue ICR - Pipeline Station Approach drawing -52" | HE-TS-0010 | HE-PL-2630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | Re-Issue for Approval - Pipeline Station Approach drawing -56" | Obtain Company Approval - Pipeline Station Approach drawing -56" | HE-PL-2590 | HE-PL-2600 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | Issue ICR - Pipeline Station Approach drawing -56" | Receive Company Comments - Pipeline Station Approach drawing -56" | HE-PL-2570 | HE-PL-2580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | Receive Company Comments - Pipeline Alignment Sheets-4" | Re-Issue for Approval - Pipeline Alignment Sheets-4" | HE-PL-2520 | HE-PL-2530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | Issue ICR-Topographical Survey Report (Overall) | Issue ICR - Pipeline Alignment Sheets-4" | HE-TS-0010 | HE-PL-2510 | FS | Completed | Completed | 30
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | Final Issue for Design/ Construction-Overall Pipeline Route Map - 52" | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | HE-PL-0230 | HE-PL-2490 | FF | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.2.26 TBE for Mainline Ball Valve | P2543-R01-Oct24..1.EN.6.2.26 TBE for Mainline Ball Valve | Obtain Company Approval - TBE for Mainline Ball Valve | Final Issue for Design/ Construction-TBE for Mainline Ball Valve | HE-PL-2300 | HE-PL-2310 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.10.25 TBE for Isolating Joints | P2543-R01-Oct24..1.EN.1.10.25 TBE for Isolating Joints | Receive Company Comments - TBE for Isolating Joints | Re-Issue for Approval - TBE for Isolating Joints | HE-PL-2220 | HE-PL-2230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A331 TBE for Leak Detection System | P2543-R01-Oct24..1.EN.6.2.A331 TBE for Leak Detection System | Receive Company Comments-TBE for Leak Detection System | Re-Issue for Approval-TBE for Leak Detection System | HE-IC-2240 | HE-IC-2250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Re-Issue for Approval-Instrument Trench Layout | Obtain Company Approval-Instrument Trench Layout | HE-IC-0990 | HE-IC-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | Obtain Company Approval- Specification for Leak Detection System | Final Issue for Design/ Construction-Specification for Leak Detection System | HE-IC-0280 | HE-IC-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | Issue ICR- Specification for Leak Detection System | Receive Company Comments- Specification for Leak Detection System | HE-IC-0250 | HE-IC-0260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | Issue ICR- P&ID's | Issue ICR- Specification for Leak Detection System | HE-PR-0110 | HE-IC-0250 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.8 TBE for Junction Boxes | P2543-R01-Oct24..1.EN.6.2.8 TBE for Junction Boxes | Receive Company Comments- TBE for Junction Boxes | Re-Issue for Approval- TBE for Junction Boxes | HE-IC-2480 | HE-IC-2490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.16.1 Ordering | P2543-R01-Oct24..1.EN.6.2.8 TBE for Junction Boxes | RFQ, Receipt of Bid for Junction Boxes | Issue ICR- TBE for Junction Boxes | HP-ME-0810 | HE-IC-2470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.7 Material Requisitions for Junction Boxes | P2543-R01-Oct24..1.EN.6.11.7 Material Requisitions for Junction Boxes | Obtain Company Approval- Material Requisitions for Junction Boxes | Final Issue for Design/ Construction-Material Requisitions for Junction Boxes | HE-IC-2020 | HE-IC-2030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A2 Instrument Index | Receive Company Comments-Instrument index -Update | Re-Issue for Approval-Instrument index -Update | HE-IC-0500 | HE-IC-0510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | Re-Issue for Approval- Power Consumption Calculation (Instrumentation) | Obtain Company Approval- Power Consumption Calculation (Instrumentation) | HE-EL-5460 | HE-EL-5470 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | Issue ICR- Power Consumption Calculation (Instrumentation) | Receive Company Comments- Power Consumption Calculation (Instrumentation) | HE-EL-5440 | HE-EL-5450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | Issue ICR- Specifications for PRS (Pressure Reduction System) | Receive Company Comments- Specifications for PRS (Pressure Reduction System) | HE-IC-0070 | HE-IC-0080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Final Issue for Design/ Construction-Typical Installation Drawings | Instrument 3rd MTO | HE-IC-0710 | HE-IC-2630 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Issue ICR- I/O list -Update | Issue ICR- Instrument location and Cable Routing Drawings | HE-IC-0550 | HE-IC-2530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.10 TBE for Fire & Gas Detectors | P2543-R01-Oct24..1.EN.6.2.10 TBE for Fire & Gas Detectors | Issue ICR- TBE for Gas Detectors | Receive Company Comments- TBE for Gas Detectors | HE-IC-2350 | HE-IC-2360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A33 TBE for PRS (Pressure Reduction Skid) | P2543-R01-Oct24..1.EN.6.2.A33 TBE for PRS (Pressure Reduction Skid) | Issue ICR-TBE for PRS | Receive Company Comments-TBE for PRS | HE-IC-2170 | HE-IC-2180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A30 TBE for Metering Skid | P2543-R01-Oct24..1.EN.6.2.A30 TBE for Metering Skid | Issue ICR-TBE for Metering Skid | Receive Company Comments-TBE for Metering Skid | HE-IC-2110 | HE-IC-2120 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A30 TBE for Metering Skid | P2543-R01-Oct24..1.EN.6.2.A30 TBE for Metering Skid | Re-Issue for Approval-TBE for Metering Skid | Obtain Company Approval-TBE for Metering Skid | HE-IC-2130 | HE-IC-2140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.6 TBE for MOV | P2543-R01-Oct24..1.EN.6.2.6 TBE for MOV | Receive Company Comments- TBE for MOV | Re-Issue for Approval- TBE for MOV | HE-IC-2060 | HE-IC-2070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A17 Material Requisitions for Metering Skid | P2543-R01-Oct24..1.EN.6.11.A17 Material Requisitions for Metering Skid | Issue ICR- Material Requisitions for Metering Skid | Receive Company Comments- Material Requisitions for Metering Skid | HE-IC-1810 | HE-IC-1820 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | Final Issue for Design/ Construction-Addendum to DGs | Final Issue for Design/ Construction-Datasheets for Pig Signalers | HE-IC-0050 | HE-IC-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | Obtain Company Approval-Datasheets for Pig Signalers | Final Issue for Design/ Construction-Datasheets for Pig Signalers | HE-IC-1420 | HE-IC-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | Receive Company Comments- Datasheets for PSV & Orifice (incl. RO) | Re-Issue for Approval- Datasheets for PSV & Orifice (incl. RO) | HE-IC-1340 | HE-IC-1350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Re-Issue for Approval- Data sheet for PRS (Pressure Reduction System) | Obtain Company Approval- Data sheet for PRS (Pressure Reduction System) | HE-IC-1230 | HE-IC-1240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | Re-Issue for Approval- Datasheets for Metering Skid | Obtain Company Approval- Datasheets for Metering Skid | HE-IC-1170 | HE-IC-1180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | Final Issue for Design/ Construction-Addendum to DGs | Final Issue for Design/ Construction-Actuator Datasheet for GOV & ROV | HE-IC-0050 | HE-IC-1130 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | Receive Company Comments- Datasheet for GOV & ROV | Re-Issue for Approval- Datasheet for GOV & ROV | HE-IC-1100 | HE-IC-1110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Obtain Company Approval-Instrument and F&G Cable Schedule | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | HE-IC-0940 | HE-IC-0950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Re-Issue for Approval-Instrument Trench Layout | Re-Issue for Approval - Loop Diagrams | HE-IC-0990 | HE-IC-0750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Issue ICR - Loop Diagrams | Receive Company Comments - Loop Diagrams | HE-IC-0730 | HE-IC-0740 | FF | Completed | In Progress | 10
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | Re-Issue for Approval - Hook-Up Diagram | Obtain Company Approval - Hook-Up Diagram | HE-IC-0630 | HE-IC-0640 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.17 Line List | Issue ICR- Process Simulations Report | Issue ICR- Line List | HE-PR-0610 | HE-PR-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.10 Equipment List | Final Issue for Design/ Construction-Process Simulations Report | Final Issue for Design/ Construction-Equipment List | HE-PR-0650 | HE-PR-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.10 Equipment List | Issue ICR- Process Datasheets - PRS Skid (at Sweihan CRS) | Issue ICR - Equipment List | HE-PR-0370 | HE-PR-1030 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.10 Equipment List | Issue ICR- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | Issue ICR - Equipment List | HE-PR-0310 | HE-PR-1030 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | Receive Company Comments- Vent and Depressurization Report (for new facilities) | Re-Issue for Approval- Vent and Depressurization Report (for new facilities) | HE-PR-0980 | HE-PR-0990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | Re-Issue for Approval-Isolation & Tie-In philosophy | Obtain Company Approval-Isolation & Tie-In philosophy | HE-PR-0870 | HE-PR-0880 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | Receive Company Comments - Relief, Vent and Blowdown Philosophy | Re-Issue for Approval - Relief, Vent and Blowdown Philosophy | HE-PR-0800 | HE-PR-0810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | Issue ICR- Process Simulations Report | Issue ICR- Operating and control philosophy, Safeguarding philosophy | HE-PR-0610 | HE-PR-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | Re-Issue for Approval- Process Simulations Report | Obtain Company Approval- Process Simulations Report | HE-PR-0630 | HE-PR-0640 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Re-Issue for Approval- Process Datasheets | HE-PR-0140 | HE-PR-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | Re-Issue for Approval- Process Datasheets - Pig Launcher / Receiver | Obtain Company Approval- Process Datasheets - Pig Launcher / Receiver | HE-PR-0510 | HE-PR-0520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | Issue ICR-Design Basis | Issue ICR- Process Flow Diagrams ( New + Existing) | HE-DB-0010 | HE-PR-0040 | FF | Completed | Completed | 4
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | Final Issue for Design/ Construction-Process Simulations Report | Final Issue for Design/ Construction-Process Flow Diagrams ( New + Existing) | HE-PR-0650 | HE-PR-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.3.3 Process Design Basis | Obtain Company Approval-Design Basis | Final Issue for Design-Design Basis | HE-DB-0040 | HE-DB-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.2.6 Project Risk Review Register | Project Risk Review Workshop | Issue ICR- Project Risk review register | HE-WS-0010 | HE-RR-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.6 Project Risk Review Register | P2543-R01-Oct24..1.EN.2.6 Project Risk Review Register | Issue ICR- Project Risk review register | Receive Company Comments-Project Risk review register | HE-RR-0010 | HE-RR-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..1.EN.2.1 Site Visit Report | Site Visit | Issue ICR - Site Visit /Survey Report | HE-SS-0020 | HE-SV-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | Receive Company Comments - Geo Technical Survey Report (Overall) | Re-Issue for Approval - Geo Technical Survey Report (Overall) | HE-GS-0020 | HE-GS-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..1.PM.12 Workshops | Site Visit | Project Risk Review Workshop | HE-SS-0020 | HE-WS-0010 | FS | Completed | Completed | 15
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | Constructability Review Workshop | HE-PI-0390 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- Plot plan - BVS | Constructability Review Workshop | HE-PI-0530 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR - HAZID / ENVID / OHID Procedure | HAZID /ENVID/OHID/ PHSER Workshop | HE-HS-0130 | HE-WS-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.2 Survey & Studies | Award Subcontracts for Topographical Survey/ Geotechnical Investigation Studies | Geo Technical Survey | ML1007-B02 | HE-SS-0040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.1.1 Ordering | P2543-R01-Oct24..1.EN.9.6.30 TBE for Distibution Transformers | RFQ, Receipt of Bid for Distribution Transformer | Issue ICR-TBE for Distribution Transformer | HP-ME-0460 | HE-EL-1450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | Receive Company Comments-Material Requisition for Distribution Transformer | Re-Issue for Approval-Material Requisition for Distribution Transformer | HE-EL-1040 | HE-EL-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | Issue ICR- Data sheet for Distribution Transformer | Issue ICR-Material Requisition for Distribution Transformer | HE-EL-0670 | HE-EL-1030 | FS | Completed | Completed | 15
P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | Obtain Company Approval-Material Requisition for Distribution Transformer | Final Issue for Design/ Construction-Material Requisition for Distribution Transformer | HE-EL-1060 | HE-EL-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | Re-Issue for Approval-Cable Sizing Calculation | Obtain Company Approval-Cable Sizing Calculation | HE-EL-0450 | HE-EL-0460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | Issue ICR-Solar Panel System SLDs | Issue ICR-Cable Sizing Calculation | HE-EL-0310 | HE-EL-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | Issue ICR-Update /New Load List | Issue ICR- Adequacy report of the Power supply requirements | HE-EL-0070 | HE-EL-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..1.EN.9.16 Electrical MTO | Final Issue for Design/ Construction-Electrical Installation Drawings | Electrical 3rd MTO | HE-EL-1790 | HE-EL-1850 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | Obtain Company Approval- Electrical Installation Drawings | Final Issue for Design/ Construction-Electrical Installation Drawings | HE-EL-1780 | HE-EL-1790 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | Issue ICR- Electrical Equipment Layout | Issue ICR- Electrical Installation Drawings | HE-EL-0490 | HE-EL-1750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..1.EN.9.12 Earthing Layout | Obtain Company Approval-Earthing Layout | Final Issue for Design/ Construction-Earthing Layout | HE-EL-1660 | HE-EL-1670 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | Final Issue for Design/ Construction-Electrical Equipment Layout | Final Issue for Design/ Construction-Cable Routing Layout | HE-EL-0530 | HE-EL-1610 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.28 TBE for Distribution Boards | P2543-R01-Oct24..1.EN.9.6.28 TBE for Distribution Boards | Issue ICR-TBE for Distribution Boards | Receive Company Comments-TBE for Distribution Boards | HE-EL-1390 | HE-EL-1400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | Issue ICR-Material Requisition for Distribution Boards | Receive Company Comments-Material Requisition for Distribution Boards | HE-EL-0970 | HE-EL-0980 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | Receive Company Comments - Material Requisition for Active / Passive Shelters | Re-Issue for Approval - Material Requisition for Active / Passive Shelters | HE-EL-0860 | HE-EL-0870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | Receive Company Comments-Data Sheet for LV cables | Re-Issue for Approval-Data Sheet for LV cables | HE-EL-0800 | HE-EL-0810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | Obtain Company Approval-Data sheet for LV Distribution board | Final Issue for Design/ Construction-Data sheet for LV Distribution board | HE-EL-0640 | HE-EL-0650 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | Receive Company Comments-Data sheet for LV Distribution board | Re-Issue for Approval-Data sheet for LV Distribution board | HE-EL-0620 | HE-EL-0630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..1.EN.9.10 Cable Schedule | Re-Issue for Approval-Cable Schedule | Obtain Company Approval-Cable Schedule | HE-EL-0570 | HE-EL-0580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..1.EN.9.10 Cable Schedule | Receive Company Comments-Cable Schedule | Re-Issue for Approval-Cable Schedule | HE-EL-0560 | HE-EL-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | Issue ICR-Single Line Diagrams for LV Switchgear | Issue ICR- Electrical Equipment Layout | HE-EL-0190 | HE-EL-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | Issue ICR-Solar Panel System SLDs | Issue ICR- Electrical Equipment Layout | HE-EL-0310 | HE-EL-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.3 Project Procedure (PEP, Numbering Procedure) | P2543-R01-Oct24..1.PM.3 Project Procedure (PEP, Numbering Procedure) | Re-Issue for Approval-Project Procedure (PEP, Numbering Procedure etc.) | Obtain Company Approval-Project Procedure (PEP, Numbering Procedure etc.) | HC-GN-0090 | HC-GN-0100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.2 Planning Package | P2543-R01-Oct24..1.PM.2 Planning Package | Issue ICR-Planning Package | Receive Company Comments-Planning Package | HC-GN-0010 | HC-GN-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.PM.2 Planning Package | Project Kick off Meeting | Issue ICR-Planning Package | ML1002 | HC-GN-0010 | FS | Completed | Completed | 4
P2543-R01-Oct24..PR.26.1.16.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.16.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Junction Boxes | Manufacturing & Assembly of Junction Boxes | HM-ME-1620 | HM-ME-1630 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.15.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Field Instruments | Testing and Inspection of Field Instruments | HM-ME-1530 | HM-ME-1540 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.13.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Fire Fighting & Safety Equipment | Factory Acceptance Test of Fire Fighting & Safety Equipment | HM-ME-1930 | HM-ME-1940 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of FOC Cables (Lot 1) | Receipt at site and inspection of FOC Cables (Lot 1) | HM-EL-0170 | HM-EL-0180 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.19.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.19.2 Manufacturing & Ready for Dispatch | Testing and Inspection of FOC Cables | Packaging & Final Inspection-FOC Cables | HM-EL-0130 | HM-EL-0140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.14.1 Ordering | P2543-R01-Oct24..PR.26.1.14.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Access Switch, Fiber Optic Patch Panel and Media Converter | Ready for Dispatch of Access Switch, Fiber Optic Patch Panel and Media Converter | HP-ME-0680 | HM-ME-1360 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.4.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Ready for Dispatch of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | HM-ME-1250 | HM-ME-1260 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.5.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.5.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Active/ Passive Cooled Shelter | Ready for Dispatch of Active/ Passive Cooled Shelter | HM-ME-1150 | HM-ME-1160 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.6.1 Ordering | P2543-R01-Oct24..PR.26.LL.6.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Solar PV system | Ready for Dispatch of Solar PV system | HP-ME-0530 | HM-ME-1060 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.7.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Power Distribution Boards | Manufacturing & Assembly of Power Distribution Boards | HM-ME-0820 | HM-ME-0830 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.LL.8.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.8.2 Manufacturing & Ready for Dispatch | Vendor Document Review of AC UPS | Manufacturing & Assembly of AC UPS | HM-ME-0720 | HM-ME-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.9.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.9.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-MOV | Ready for Dispatch of MOV | HM-ME-0640 | HM-ME-0650 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.9.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of MOV | Testing and Inspection of MOV | HM-ME-0620 | HM-ME-0630 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.11.A1311 Material Requisitions for MOV | P2543-R01-Oct24..PR.26.LL.9.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Material Requisitions for MOV | Manufacturing & Assembly of MOV | HE-IC-1610 | HM-ME-0620 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.1.2.LL.10.1 Ordering | P2543-R01-Oct24..PR.26.LL.10.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for ROV/ GOV | Ready for Dispatch of ROV/ GOV | HP-ME-0280 | HM-ME-0550 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.10.2 Manufacturing & Ready for Dispatch | Vendor Document Review of ROV/ GOV | Manufacturing & Assembly of ROV/ GOV | HM-ME-0510 | HM-ME-0520 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.LL.10.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - MOV/ROV/GOV Valves | Vendor Document Review of ROV/ GOV | ML1022-C07 | HM-ME-0510 | FF | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Pig Launchers & Receivers | HE-PR-0590 | HM-ME-0420 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.1.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.3.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of HVAC Equipment | Packaging & Final Inspection-HVAC Equipment | HM-ME-1740 | HM-ME-1750 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.3.3 Delivery & receipt at Site | Ready for Dispatch of HVAC Equipment | Transportation/ Custom Clearance/ Delivery at site of HVAC Equipment | HM-ME-1760 | HM-ME-1780 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.1.2.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Fire Suppression System | Receipt at site and inspection of Fire Suppression System | HM-ME-1820 | HM-ME-1830 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection - Pressure Reduction Skid | Ready for Dispatch of Pressure Reduction Skid | HM-ME-0140 | HM-ME-0150 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.22.1 Ordering | P2543-R01-Oct24..PR.26.LL.22.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Custody Metering Skid | Ready for Dispatch of Custody Metering Skid | HP-ME-0030 | HM-ME-0050 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Gas Detectors (Lot 1) | Receipt at site and inspection of Gas Detectors (Lot 1) | HM-ME-1480 | HM-ME-1490 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Filter Package | Ready for Dispatch of Filter Package | HM-ME-0340 | HM-ME-0350 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.11.1 Ordering | P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Filter Package | Ready for Dispatch of Filter Package | HP-ME-0180 | HM-ME-0350 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Filter Package | HE-PR-0590 | HM-ME-0320 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.BK.15.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.15.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Earthing Material | Factory Acceptance Test of Earthing Material | HM-EL-0320 | HM-EL-0330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | Final Civil Bulk material MTO | Final Civil Bulk material MTO | HM-CS-0020 | HM-CS-0050 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..PR.BK.13.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.13.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Cable Trays | Ready for Dispatch of Cable Trays | HM-EL-0240 | HM-EL-0250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 1 | Ready for Dispatch of Line Pipes (Coated) - Lot 1 | HM-PL-0040 | HM-PL-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | Issue MR (Final) - Line pipes | Vendor Document Review of Line Pipes - Lot 1 | ML1021-B15 | HM-PL-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of CP System | Receipt at site and inspection of CP System - Permanent Material | HM-PL-0420 | HM-PL-0430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - Barred Tee | Vendor Document Review of Ball/ Globe/ Check/ Plug Valves | ML1239-C04 | HM-PL-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..ML.4 Commissioning and PAC | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | Commission New pipeline system - 56" Sales Gas Pipeline | CCM-PM4510 | ML1999-F01 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of MOV (Lot 1) | Receive at Site - E&I Equipment's (RTUs) | HM-ME-0680 | ML1469-D13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Receive at Site - Hot Bends for 56" Pipeline | HM-PL-0630 | ML1439-D10 | FF | Not Started | Not Started | 9
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of CP System - Permanent Material | Receive at Site - Isolation Joints, Barred Tee, and Anchor Flanges | HM-PL-0430 | ML1409-D24 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Pigging & Split Tee (Lot 1) | Receive at Site - Isolation Joints, Barred Tee, and Anchor Flanges | HM-PL-0840 | ML1409-D24 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Isolating Joints (Lot 1) | Receive at Site - Isolation Joints, Barred Tee, and Anchor Flanges | HM-PL-0740 | ML1409-D24 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.5.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Active/ Passive Cooled Shelter | Receive at Site - Passive Cooling Shelter | HM-ME-1190 | ML1054-D09 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Receive at Site - F & G System | HM-ME-1590 | ML2089-D16 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.21.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Pressure Reduction Skid | Issue Purchase Order (Final) - Pressure Reduction Skids | HP-ME-0080 | ML1039-C08 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.8.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for AC UPS | Issue Purchase Order (Final) - AC UPS System | HP-ME-0380 | ML1319-C16 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.17.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Leak Detection System | Issue Purchase Order (Final) - Leak Detection System | HP-ME-0130 | ML1289-C11 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Gas metering skid foundation drawings | Issue Civil / Structural Drawings for Gas Filters, Pressure Reducing Skids and Metering Skids facilities - IFC. | HE-CS-0830 | ML1036-B23 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.33 Filter Foundation GA and Details | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-FILTER FOUNDATION GA AND DETAILS | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-0950 | ML1035-B26 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-0650 | ML1035-B26 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical trench detail drawing | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-0170 | ML1035-B26 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-TYPICAL LIGHTING POLE FOUNDATION DETAILS | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-1010 | ML1034-B25 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | HE-IC-0950 | ML1032-B21 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Telecom Equipment Layout | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | HE-TL-0770 | ML1032-B21 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Solar Panel System SLDs | Issue SLD, Hazardous Area Classification Details for All Areas - IFC | HE-EL-0350 | ML1031-B20 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Single Line Diagrams for LV Distribution Board | Issue SLD, Hazardous Area Classification Details for All Areas - IFC | HE-EL-0230 | ML1031-B20 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Material Requisitions for Sales Gas CRS Filters | Issue MRs for All Mechanical Equipment & Packages (Final Issue) | HE-ME-0170 | ML1017-B18 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.10 Equipment List | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Equipment List | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | HE-PR-1070 | ML1014-B10 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.11 QRA Report | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue for Approval-QRA Report | Complete HAZOP/ SIL/ LOPA Review as applicable and Submit final Report after incorporating Company comments (IFA) | HE-HS-0810 | ML1013-B07 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue for HAZOP Studies- Plot plan - BVS | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | HE-PI-0550 | ML1012-B06 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design-Design Basis | Prepare Design Basis for all Engineering Disciplines and Issue to COMPANY - Final Issue | HE-DB-0050 | ML1005-B01 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Piping GA- 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | HE-PI-0640 | ML1219-B19 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-1430 | ML1209-B27 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.17 Typical details of protection slab to protect existing UG pipe at road crossing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical details of protection slab to protect existing UG pipe at road crossing | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-0410 | ML1209-B27 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-0350 | ML1209-B27 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction - Pressure Reduction Skid and Leak Detection Drawings | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-0770 | ML1209-B27 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Civil UG layout | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-0530 | ML1209-B27 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.10 Equipment List | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Equipment List | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | HE-PR-1070 | ML1179-B11 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Receive at Site - Pig Launcher & Receiver | Project Finish | ML1519-D04 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.2 Final Documentation | P2543-R01-Oct24..ML Milestones | Quality Dossier | Project Finish | CAB-5300 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Receive at Site - MOV/ROV/GOV Valves | Project Finish | ML1024-D06 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Receive at Site - E&I Equipment's (IDS & PIDS System) | Project Finish | ML1479-D15 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Drying & Purging of all facilities including Pipeline - 4" Nitrogen Pipeline | Project Finish | ML1929-E38 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | HSE | Close-out report | CAB-4410 | CAB-5320 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Issue Project Execution Plan (PEP), Coordination, Engineering, Procurement, HSE and Quality Procedures-Final Issue | General | ML1001-A01 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.4 NOC Register | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Final Issue for Design/ Construction-NOC Register | General | HC-GN-0290 | CAB-5290 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Telecom | General | CAB-4470 | CAB-5290 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Mechanical | General | CAB-4430 | CAB-5290 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Instrumentation & Control | General | CAB-4460 | CAB-5290 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of Power Distribution Boards | Vendor Documents Package | HM-ME-0890 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.6.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of Solar PV system | Vendor Documents Package | HM-ME-1090 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.8.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of AC UPS | Vendor Documents Package | HM-ME-0790 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Telecom | Vendor Documents Package | CAB-4470 | CAB-5310 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Instrumentation & Control | Quality Dossier | CAB-4460 | CAB-5300 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..1.EN.1.9.18 MR for Hot Induction Bends | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-MR for Hot Induction Bends | Pipeline | HE-PL-1790 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.51 Data Sheet - Mainline Ball Valve | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Data Sheet - Mainline Ball Valve | Pipeline | HE-PL-1250 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.6 Pipeline Location Class selection Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | Pipeline | HE-PL-0830 | CAB-4480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.60.14 Data Sheet - Anchor Flange | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Data Sheet - Anchor Flange | Pipeline | HE-PL-1550 | CAB-4480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | Pipeline | ML1030 | CAB-4480 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.55 Crossing Schedule-4" | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Crossing Schedule-4" | Pipeline | HE-PL-3210 | CAB-4480 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.9.19 MR for Pipeline Pigging Tees | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-MR for Pipeline Pigging Tees | Pipeline | HE-PL-1850 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Telecom | HE-TL-0710 | CAB-4470 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc. | Telecom | HE-TL-0590 | CAB-4470 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Telecom | ML1032-B21 | CAB-4470 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Telecom | ML1033-B22 | CAB-4470 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Loop Diagrams | Instrumentation & Control | HE-IC-0770 | CAB-4460 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisitions for Field Instruments / H2S Analyzers | Instrumentation & Control | HE-IC-1970 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Instrumentation & Control | HE-IC-1550 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Hook-Up Diagram | Instrumentation & Control | HE-IC-0650 | CAB-4460 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Selection Diagram | Electrical | HE-CP-0050 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.4 Solar Panel Sizing | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Solar Panel Sizing | Electrical | HE-EL-0410 | CAB-4450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Cable Schedule | Electrical | HE-EL-0590 | CAB-4450 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Single Line Diagrams for LV Distribution Board | Electrical | HE-EL-0230 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Piping GA Drawings for 591-BVS-01 | Piping | HE-PI-0820 | CAB-4440 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | Piping | HE-PI-0880 | CAB-4440 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Datasheet for Plug valves | Piping | HE-PI-1000 | CAB-4440 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Piping | HE-PI-0440 | CAB-4440 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Typical Detailed Drawing - Jib Crane Foundation | Civil & Structural | HE-CS-1070 | CAB-4420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Civil & Structural | HE-CS-0470 | CAB-4420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Civil / Structural Drawings for Gas Filters, Pressure Reducing Skids and Metering Skids facilities - IFC. | Civil & Structural | ML1036-B23 | CAB-4420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Civil & Structural | HE-CS-0290 | CAB-4420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.12 PHSER Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-PHSER Report | HSE | HE-HS-0890 | CAB-4410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Complete HSEIA, QRA, and Gas Dispersion Studies after review / approval by Company and Submit Final Reports | HSE | ML1016-B12 | CAB-4410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.19 HAZID/ ENVID/ OHID Close out Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-HAZID/ ENVID/ OHID Close out Report | HSE | HE-HS-0650 | CAB-4410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Process | ML1179-B11 | CAB-4400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | Process | ML1030 | CAB-4400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.10 Equipment List | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Equipment List | Process | HE-PR-1070 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Issue ICR-Pre-commissioning and Commissioning Plan | Receive Company Comments-Pre-commissioning and Commissioning Plan | C-COM-800 | C-COM-810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.11 QRA Report | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Final Issue for Design/ Construction-QRA Report | Issue ICR-Pre-commissioning and Commissioning Plan | HE-HS-0830 | C-COM-800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.12 PHSER Report | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Final Issue for Design/ Construction-PHSER Report | Issue ICR-Pre-commissioning and Commissioning Plan | HE-HS-0890 | C-COM-800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Typical Installation Drawings | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-IC-0710 | C-COM-790 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | ML1033-B22 | C-COM-790 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Typical Installation Drawings | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-IC-0710 | C-COM-790 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Complete HSEIA, QRA, and Gas Dispersion Studies after review / approval by Company and Submit Final Reports | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | ML1016-B12 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Receive Company Comments-Construction Procedures / Method Statements / ITPs | Re-Issue for Approval-Construction Procedures / Method Statements / ITPs | C-COM-760 | C-COM-770 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..1.EN.10.2 Telecom MTO | P2543-R01-Oct24..1.1.BK.9.1 Ordering | Telecom 3rd MTO | Final Telecom Bulk material MTO | HE-TL-0890 | HP-BK-0510 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..1.1.BK.11.1 Ordering | Final Issue for Design/ Construction-Typical duct bank detail drawing | 1st Civil Bulk material MTO | HE-CS-0230 | HP-BK-0260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.15.1 Ordering | P2543-R01-Oct24..1.1.BK.15.1 Ordering | RFQ, Receipt of Bid for Earthing Material | Prepare TBE and Company approval for Earthing Material | HP-BK-0160 | HP-BK-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.13.1 Ordering | P2543-R01-Oct24..1.1.BK.13.1 Ordering | Prepare TBE and Company approval for Cable Trays | Commercial Clarifications & Placement of PO for Cable Trays | HP-BK-0120 | HP-BK-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.17.1 Ordering | P2543-R01-Oct24..1.1.BK.17.1 Ordering | Prepare TBE and Company approval for Power & Control Cables | Commercial Clarifications & Placement of PO for Power & Control Cables | HP-BK-0020 | HP-BK-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.17.1 Ordering | P2543-R01-Oct24..1.1.BK.17.1 Ordering | RFQ, Receipt of Bid for Power & Control Cables | Prepare TBE and Company approval for Power & Control Cables | HP-BK-0010 | HP-BK-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.20 MR for Isolating Joints | P2543-R01-Oct24..1.1.1.3.1 Ordering | Final Issue for Design/ Construction-MR for Isolating Joints | Commercial Clarifications & Placement of PO for Isolating Joints | HE-PL-1910 | HP-ME-1240 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.1.1.1.1 Ordering | Issue MR (Final) - Hot Bends | Commercial Clarifications & Placement of PO for Hot Induction Bend | ML1189-B16 | HP-ME-1190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.1.1 Ordering | P2543-R01-Oct24..1.1.BK.1.1 Ordering | Prepare TBE and Company approval for Manual/ Ball/ Globe/ Check/ Plug Valves | Commercial Clarifications & Placement of PO for Manual/ Ball/ Globe/ Check/ Plug Valves | HP-ME-1080 | HP-ME-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | P2543-R01-Oct24..1.1.BK.1.1 Ordering | Final Issue for Design/ Construction-Material Requisition for Ball/ Plug Valves | Commercial Clarifications & Placement of PO for Manual/ Ball/ Globe/ Check/ Plug Valves | HE-PI-1060 | HP-ME-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.2.6 TBE for Ball valves/ Plug Valves | P2543-R01-Oct24..1.1.BK.1.1 Ordering | Obtain Company Approval- TBE for Ball valves/ Plug Valves | Commercial Clarifications & Placement of PO for Manual/ Ball/ Globe/ Check/ Plug Valves | HE-PI-1110 | HP-ME-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | P2543-R01-Oct24..1.1.2.LL.6.1 Ordering | Obtain Company Approval-Material Requisition for Solar Panels | Prepare TBE and Company approval for Solar PV system | HE-EL-1120 | HP-ME-0520 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.11.1 Ordering | P2543-R01-Oct24..1.1.2.LL.11.1 Ordering | RFQ, Receipt of Bid for Filter Package | Prepare TBE and Company approval for Filter Package | HP-ME-0160 | HP-ME-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.3.9 TBE for Sals Gas CRS Filters | P2543-R01-Oct24..1.1.2.LL.11.1 Ordering | Final Issue for Design/ Construction-TBEs for Sales Gas CRS Filters | Commercial Clarifications & Placement of PO for Filter Package | HE-ME-0230 | HP-ME-0180 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.21.1 Ordering | P2543-R01-Oct24..1.1.2.LL.21.1 Ordering | Prepare TBE and Company approval for Pressure Reduction Skid | Commercial Clarifications & Placement of PO for Pressure Reduction Skid | HP-ME-0070 | HP-ME-0080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.19.1 Ordering | P2543-R01-Oct24..1.1.2.LL.19.1 Ordering | Prepare TBE and Company approval for FOC Cables | Commercial Clarifications & Placement of PO for FOC Cables | HP-BK-0070 | HP-BK-0080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.1.2.LL.4.1 Ordering | Issue ICR- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | RFQ, Receipt of Bid for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0550 | HP-ME-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..1.2.12.14 Fence Works | Fence Works Complete Evaluation (Internal) | Fence Works Subcontract Award | HS-CN-0680 | HS-CN-0690 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.2.12.13 E&I Works | Project Kick off Meeting | E&I Works RFQ & Quotation Receipt | ML1002 | HS-CN-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.10 Earthworks | P2543-R01-Oct24..1.2.12.10 Earthworks | Earthworks Complete Evaluation (Internal) | Earthworks Subcontract Award | HS-CN-0480 | HS-CN-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.7 OHPL | P2543-R01-Oct24..1.2.12.7 OHPL | OHPL Complete Evaluation (Internal) | OHPL Subcontract Award | HS-CN-0430 | HS-CN-0440 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | Project Kick off Meeting | CP Drilling & Earthing Drilling RFQ & Quotation Receipt | ML1002 | HS-CN-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..1.2.12.2 NDRC | NDRC RFQ & Quotation Receipt | NDRC Complete Evaluation (Internal) | HS-CN-0060 | HS-CN-0080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.11 Cathodic Protection Work | P2543-R01-Oct24..1.2.13.11 Cathodic Protection Work | Complete Evaluation (Internal) - Cathodic Protection Work | Place LOA/FOA - Cathodic Protection Work | HS-GN-0520 | HS-GN-0530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | Prepare TBE and Company approval - Modification of Existing DCS | Commercial Clarifications & Placement of PO - Modification of Existing DCS | HS-GN-0460 | HS-GN-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.12 Modification of Existing Telecom System | P2543-R01-Oct24..1.1.BK.12 Modification of Existing Telecom System | Prepare TBE and Company approval - Modification of Existing Telecom System | Commercial Clarifications & Placement of PO - Modification of Existing Telecom System | HS-GN-0340 | HS-GN-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | Review Company Comments - Calculations for Pipe supports | Re-Issue for Approval - Calculations for Pipe supports | HE-CS-1100 | HE-CS-1110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | Obtain Company Approval - Lighting pole foundation details | Final Issue for Design/ Construction-TYPICAL LIGHTING POLE FOUNDATION DETAILS | HE-CS-1000 | HE-CS-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | Final Issue for Design/ Construction-Design Calculation for Typical Skid Foundations | Final Issue for Design/ Construction-Solar panel foundation details | HE-CS-0710 | HE-CS-0890 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | Review Company Comments - Solar panel foundation details | Re-Issue for Approval - Solar panel foundation details | HE-CS-0860 | HE-CS-0870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..1.EN.8.11 Civil UG layout | Issued for Review - Site grading, road, drainage and fence layout | Issued for Review - Civil UG layout | HE-CS-0430 | HE-CS-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | Obtain Company Approval - Site grading, road, drainage and fence layout | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | HE-CS-0460 | HE-CS-0470 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | Re-Issue for Approval - Site grading, road, drainage and fence layout | Obtain Company Approval - Site grading, road, drainage and fence layout | HE-CS-0450 | HE-CS-0460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | Review Company Comments - Site grading, road, drainage and fence layout | Re-Issue for Approval - Site grading, road, drainage and fence layout | HE-CS-0440 | HE-CS-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..1.EN.8.17 Typical details of protection slab to protect existing UG pipe at road crossing | Issued for Review - Typical duct bank detail drawing | Issued for Review - Typical details of protection slab to protect existing UG pipe at road crossing | HE-CS-0190 | HE-CS-0370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | Issued for Review - Typical Fence and gate detail drawing | Review Company Comments - Typical Fence and gate detail drawing | HE-CS-0310 | HE-CS-0320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | Issued for Review - Typical duct bank detail drawing | Review Company Comments - Typical duct bank detail drawing | HE-CS-0190 | HE-CS-0200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | Obtain Company Approval - Standard drawings for Anchor bolt | Final Issue for Design/ Construction-Standard drawings for Anchor bolt | HE-CS-0100 | HE-CS-0110 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | Final Issue for Design/ Construction-Addendum to DGs | Final Issue for Design/ Construction-Standard drawings for Anchor bolt | HE-CS-0050 | HE-CS-0110 | FF | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Issued - Civil MTO 2 | HE-CS-1190 | HE-CS-1550 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..1.EN.8.41 Misc. supports | Re-Issue for Approval - Misc. supports and civil/ structural details | Obtain Company Approval - Misc. supports and civil/ structural details | HE-CS-1470 | HE-CS-1480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | Obtain Company Approval - Pipe Sleeper layout and details. | Final Issue for Design/ Construction-Pipe Sleeper layout and details | HE-CS-1420 | HE-CS-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | Re-Issue for Approval - Pipe Sleeper layout and details. | Obtain Company Approval - Pipe Sleeper layout and details. | HE-CS-1410 | HE-CS-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | Re-Issue for Approval - Typical Structural Steel and Foundation details for pipe support | Obtain Company Approval - Typical Structural Steel and Foundation details for pipe support | HE-CS-1350 | HE-CS-1360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | Issued for Review - Typical Structural Steel and Foundation details for pipe support | Review Company Comments - Typical Structural Steel and Foundation details for pipe support | HE-CS-1330 | HE-CS-1340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.3.9 TBE for Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.3.9 TBE for Sals Gas CRS Filters | Re-Issue for Approval-TBEs for Sales Gas CRS Filters | Obtain Company Approval-TBEs for Sales Gas CRS Filters | HE-ME-0210 | HE-ME-0220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.3.9 TBE for Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.3.9 TBE for Sals Gas CRS Filters | Receive Company Comments-TBEs for Sales Gas CRS Filters | Re-Issue for Approval-TBEs for Sales Gas CRS Filters | HE-ME-0200 | HE-ME-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | Receive Company Comments-Material Requisitions for Sales Gas CRS Filters | Re-Issue for Approval-Material Requisitions for Sales Gas CRS Filters | HE-ME-0140 | HE-ME-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | Issue ICR- Addendum to DGS | Receive Company Comments- Addendum to DGS | HE-ME-0010 | HE-ME-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Re-Issue for HAZOP Studies- Overall Plot Plan - 4" N2 Source Pipeline | Re-Issue after incorporating HAZOP /Review Comments - 4" N2 Source Pipeline | HE-PI-0480 | HE-PI-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Re-Issue after incorporating HAZOP /Review Comments - 52" Pipeline SWEIHAN CRS | Re-Issue after incorporating HAZOP /Review Comments - 4" N2 Source Pipeline | HE-PI-0420 | HE-PI-0490 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Obtain Company Approval- Overall Plot Plan - 4" N2 Source Pipeline | Final Issue for Design/ Construction-Overall Plot Plan- 4" N2 Source Pipeline | HE-PI-0500 | HE-PI-0510 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Receive Company Comments- Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Re-Issue for HAZOP Studies- Overall Plot Plan - 52" Pipeline SWEIHAN CRS | HE-PI-0400 | HE-PI-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction-Process Flow Diagrams ( New + Existing) | Final Issue for Design/ Construction-Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0090 | HE-PI-0370 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | Obtain Company Approval-Pipe Wall Thickness Calculation | Final Issue for Design/ Construction-Pipe Wall Thickness Calculation | HE-PI-0230 | HE-PI-0240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | Re-Issue for Approval-Piping Isometrics | Obtain Company Approval-Piping Isometrics | HE-PI-1220 | HE-PI-1230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | Issue ICR-Piping Stress Analysis & Report | Receive Company Comments-Piping Stress Analysis & Report | HE-PI-1140 | HE-PI-1150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.2.6 TBE for Ball valves/ Plug Valves | P2543-R01-Oct24..1.EN.7.2.6 TBE for Ball valves/ Plug Valves | Receive Company Comments- TBE for Ball valves/ Plug Valves | Re-Issue for Approval- TBE for Ball valves/ Plug Valves | HE-PI-1090 | HE-PI-1100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.1.1 Ordering | P2543-R01-Oct24..1.EN.7.2.6 TBE for Ball valves/ Plug Valves | RFQ, Receipt of Bid for Manual/Ball/ Globe/ Check/ Plug Valves | Issue ICR- TBE for Ball valves/ Plug Valves | HP-ME-1070 | HE-PI-1080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | Receive Company Comments-MR for Ball valves/ Plug Valves | Re-Issue for Approval-MR for Ball valves/ Plug Valves | HE-PI-1030 | HE-PI-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | Re-Issue for Approval- Datasheet for Plug Valves | Re-Issue for Approval-MR for Ball valves/ Plug Valves | HE-PI-0980 | HE-PI-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | Receive Company Comments-Data sheet for Ball Valves | Re-Issue for Approval-Data sheet for Ball Valves | HE-PI-0910 | HE-PI-0920 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | Final Issue for Design/ Construction-Piping Stress Analysis & Report | Final Issue for Design/ Construction-Piping GA Drawings for 591-BVS-01 | HE-PI-1180 | HE-PI-0820 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | Receive Company Comments-Piping GA for 4" N2 Source Pipeline | Re-Issue for Approval-Piping GA for 4" N2 Source Pipeline | HE-PI-0730 | HE-PI-0740 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | Re-Issue after incorporating HAZOP /Review Comments - 4" N2 Source Pipeline | Issue ICR- Piping GA for 4" N2 Source Pipeline | HE-PI-0490 | HE-PI-0720 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | Issue ICR-Piping GA for 52" Pipeline SWEIHAN CRS | Receive Company Comments-Piping GA for 52" Pipeline SWEIHAN CRS | HE-PI-0660 | HE-PI-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | Vendor Document Review of Pig Launchers & Receivers | Re-Issue for Approval-Piping GA for 52" Pipeline SWEIHAN CRS | HM-ME-0410 | HE-PI-0680 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR-Piping GA-56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0320 | HE-PI-0600 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.7.10 3D Model | HAZID /ENVID/OHID/ PHSER Workshop | 60% Model Review | HE-WS-0020 | HE-PI-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.7.10 3D Model | 30% Model Review | 30% Model Review Report | HE-PI-0130 | HE-PI-0140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.10 3D Model | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | 30% Model Review | HE-PI-0390 | HE-PI-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | Final Issue for Design/ Construction-HAZID / ENVID / OHID Procedure | Final Issue for Design/ Construction-HAZID/ ENVID/ OHID Report | HE-HS-0170 | HE-HS-0590 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | Final Issue for Design/ Construction-Project HSE Philosophy | Final Issue for Design/ Construction-F&G Cause and effect | HE-HS-0110 | HE-HS-0350 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | Re-Issue for Approval-F&G Cause and Effect | Obtain Company Approval-F&G Cause and Effect | HE-HS-0330 | HE-HS-0340 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.5 F&G layout | P2543-R01-Oct24..1.EN.4.5 F&G layout | Receive Company Comments-F&G Layout | Re-Issue for Approval-F&G Layout | HE-HS-0260 | HE-HS-0270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.4.5 F&G layout | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | Final Issue for Design/ Construction-F&G layout | HE-PI-0580 | HE-HS-0290 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.4.5 F&G layout | P2543-R01-Oct24..1.EN.4.5 F&G layout | Re-Issue for Approval-F&G Layout | Obtain Company Approval-F&G Layout | HE-HS-0270 | HE-HS-0280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | Re-Issue for Approval-HAZOP Procedure | Obtain Company Approval-HAZOP Procedure | HE-HS-0210 | HE-HS-0220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.4 Project HSE Plan | P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | Issue ICR-HSE Plan | Issue ICR-HSE Philosophy | HE-HS-0010 | HE-HS-0070 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.4 Project HSE Plan | P2543-R01-Oct24..1.EN.4.4 Project HSE Plan | Receive Company Comments-HSE Plan | Re-Issue for Approval-HSE Plan | HE-HS-0020 | HE-HS-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.4 Project HSE Plan | P2543-R01-Oct24..1.EN.4.4 Project HSE Plan | Re-Issue for Approval-HSE Plan | Obtain Company Approval-HSE Plan | HE-HS-0030 | HE-HS-0040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.20 Material Requisition for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | Issue ICR-Material Requisition for Fire Fighting & Safety Eqpt | Issue ICR-TBE for Fire Fighting & Safety Eqpt | HE-HS-1092 | HE-HS-1150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | Receive Company Comments-TBE for Fire Fighting & Safety Eqpt | Re-Issue for Approval-TBE for Fire Fighting & Safety Eqpt | HE-HS-1160 | HE-HS-1170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.20 Material Requisition for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.EN.4.20 Material Requisition for Fire Fighting and Safety Equipment | Re-Issue for Approval-Material Requisition for Fire Fighting & Safety Eqpt | Obtain Company Approval-Material Requisition for Fire Fighting & Safety Eqpt | HE-HS-1110 | HE-HS-1120 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | Issue ICR-HSE Action Tracking Register (Hazards and Effects Register) | Receive Company Comments-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-1030 | HE-HS-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | P2543-R01-Oct24..1.EN.4.8 Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Re-Issue for Approval-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | Obtain Company Approval-Waste Management Plan (WMP) / Construction Environmental Management Plan (CEMP) | HE-HS-0990 | HE-HS-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.17 PHSER Close Out Report | P2543-R01-Oct24..1.EN.4.17 PHSER Close Out Report | Issue ICR- PHSER Close Out Report | Receive Company Comments- PHSER Close Out Report | HE-HS-0910 | HE-HS-0920 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.12 PHSER Report | P2543-R01-Oct24..1.EN.4.12 PHSER Report | Issue ICR-PHSER Report | Receive Company Comments-PHSER Report | HE-HS-0850 | HE-HS-0860 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.4.12 PHSER Report | Issue ICR- HAZOP reviews Report for all areas | Issue ICR-PHSER Report | HE-HS-0670 | HE-HS-0850 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.21 HAZOP close out report | P2543-R01-Oct24..1.EN.4.21 HAZOP close out report | Re-Issue for Approval- HAZOP Close Out Report | Obtain Company Approval- HAZOP Close Out Report | HE-HS-0750 | HE-HS-0760 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | Issue ICR- Specification for RTU | Issue ICR - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | HE-IC-0190 | HE-TL-0070 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Final Issue for Design/ Construction-Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0470 | HE-TL-0530 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Obtain Company Approval- Telecom Tie-in Block Diagram | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | HE-TL-0400 | HE-TL-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Issue ICR - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Issue ICR- Overall Telecom Block Diagram | HE-TL-0070 | HE-TL-0310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..1.EN.10.2 Telecom MTO | Re-Issue for Approval-Telecom Location and Cable Routing layout | Telecom 2nd MTO | HE-TL-0690 | HE-TL-0870 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Receive Company Comments- Telecom Cable Schedule | Re-Issue for Approval- Telecom Cable Schedule | HE-TL-0800 | HE-TL-0810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | Issue ICR-Telecom Location and Cable Routing layout | Receive Company Comments-Telecom Location and Cable Routing layout | HE-TL-0670 | HE-TL-0680 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | Re-Issue for Approval-Telecom Location and Cable Routing layout | Obtain Company Approval-Telecom Location and Cable Routing layout | HE-TL-0690 | HE-TL-0700 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | Re-Issue for Approval-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Obtain Company Approval-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0630 | HE-TL-0640 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | Receive Company Comments-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Re-Issue for Approval-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0620 | HE-TL-0630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Obtain Company Approval- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Final Issue for Design/ Construction-Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc. | HE-TL-0580 | HE-TL-0590 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Final Issue for Design/ Construction-Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Final Issue for Design/ Construction-Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc. | HE-TL-0110 | HE-TL-0590 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Re-Issue for Approval- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Re-Issue for Approval- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0210 | HE-TL-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Re-Issue for Approval - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Re-Issue for Approval- FOC Block diagram (Telecom) | HE-TL-0090 | HE-TL-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Issue ICR- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Issue ICR- FOC Block diagram (Telecom) | HE-TL-0250 | HE-TL-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Issue ICR - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Issue ICR- FOC Block diagram (Telecom) | HE-TL-0070 | HE-TL-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Obtain Company Approval- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-TL-0280 | HE-TL-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.22 TBE for Linepipes | P2543-R01-Oct24..1.EN.1.10.22 TBE for Linepipes | Issue ICR - TBE for Line pipes | Receive Company Comments - TBE for Line pipes | HE-PL-2050 | HE-PL-2060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.16.1 Ordering | P2543-R01-Oct24..1.EN.1.10.22 TBE for Linepipes | RFQ, Receipt of Bid for Line Pipes (Coated) | Issue ICR - TBE for Line pipes | HP-ME-1020 | HE-PL-2050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.19 MR for Pipeline Pigging Tees | P2543-R01-Oct24..1.EN.1.9.19 MR for Pipeline Pigging Tees | Receive Company Comments - MR for Pigging Tees | Re-Issue for Approval - MR for Pigging Tees | HE-PL-1820 | HE-PL-1830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.18 MR for Hot Induction Bends | P2543-R01-Oct24..1.EN.1.9.18 MR for Hot Induction Bends | Receive Company Comments - MR for Hot Induction Bends | Re-Issue for Approval - MR for Hot Induction Bends | HE-PL-1760 | HE-PL-1770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.21 Material Requisition for Manual Ball Valves | P2543-R01-Oct24..1.EN.6.11.21 Material Requisition for Manual Ball Valves | Receive Company Comments - MR for Mainline Ball Valve | Re-Issue for Approval - MR for Mainline Ball Valve | HE-PL-1700 | HE-PL-1710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.9 Data Sheet - Linepipes | P2543-R01-Oct24..1.EN.1.9.17 MR for Linepipes | Final Issue for Design/ Construction-Data Sheet - Line pipes | Final Issue for Design/ Construction-MR for Line pipes | HE-PL-1190 | HE-PL-1670 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.14 Data Sheet - Anchor Flange | P2543-R01-Oct24..1.EN.1.60.14 Data Sheet - Anchor Flange | Issue ICR - Data Sheet - Anchor Flange (If Required) | Receive Company Comments - Data Sheet - Anchor Flange (If Required) | HE-PL-1510 | HE-PL-1520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | Obtain Company Approval - Data Sheet - Split Tee | Final Issue for Design/ Construction-Data Sheet - Split Tee | HE-PL-1360 | HE-PL-1370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.40 Specification - Split Tee | P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | Final Issue for Design/ Construction-Specification - Split Tee | Final Issue for Design/ Construction-Data Sheet - Split Tee | HE-PL-0470 | HE-PL-1370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.10 Data Sheet - Hot Induction Bends | P2543-R01-Oct24..1.EN.1.60.10 Data Sheet - Hot Induction Bends | Re-Issue for Approval - Data Sheet - Hot Induction Bends | Obtain Company Approval - Data Sheet - Hot Induction Bends | HE-PL-1290 | HE-PL-1300 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.10 Data Sheet - Hot Induction Bends | P2543-R01-Oct24..1.EN.1.60.10 Data Sheet - Hot Induction Bends | Issue ICR - Data Sheet - Hot Induction Bends | Receive Company Comments - Data Sheet - Hot Induction Bends | HE-PL-1270 | HE-PL-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.51 Data Sheet - Mainline Ball Valve | P2543-R01-Oct24..1.EN.6.4.51 Data Sheet - Mainline Ball Valve | Receive Company Comments - Data Sheet - Mainline Ball Valve | Re-Issue for Approval - Data Sheet - Mainline Ball Valve | HE-PL-1220 | HE-PL-1230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.51 Data Sheet - Mainline Ball Valve | P2543-R01-Oct24..1.EN.6.4.51 Data Sheet - Mainline Ball Valve | Obtain Company Approval - Data Sheet - Mainline Ball Valve | Final Issue for Design/ Construction-Data Sheet - Mainline Ball Valve | HE-PL-1240 | HE-PL-1250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | P2543-R01-Oct24..1.EN.6.4.51 Data Sheet - Mainline Ball Valve | Final Issue for Design/ Construction-Pipeline Specifications - Addendum to DGS | Final Issue for Design/ Construction-Data Sheet - Mainline Ball Valve | HE-PL-0110 | HE-PL-1250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.40 Specification - Split Tee | P2543-R01-Oct24..1.EN.1.40 Specification - Split Tee | Receive Company Comments - Specification - Split Tee | Re-Issue for Approval - Specification - Split Tee | HE-PL-0440 | HE-PL-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.13 Pipeline Schematic Arrangement- 56", 52" and 4" Pipline | P2543-R01-Oct24..1.EN.1.13 Pipeline Schematic Arrangement- 56", 52" and 4" Pipline | Re-Issue for Approval - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | Obtain Company Approval - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | HE-PL-0330 | HE-PL-0340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | Obtain Company Approval - Overall Pipeline Route Map - 52" | Final Issue for Design/ Construction-Overall Pipeline Route Map - 52" | HE-PL-0220 | HE-PL-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | Issue ICR - Overall Pipeline Route Map - 52" | Receive Company Comments - Overall Pipeline Route Map - 52" | HE-PL-0190 | HE-PL-0200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | Receive Company Comments - Overall Pipeline Route Map - 56" | Re-Issue for Approval - Overall Pipeline Route Map - 56" | HE-PL-0140 | HE-PL-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | Issue ICR-Topographical Survey Report (Overall) | Re-Issue for Approval - Overall Pipeline Route Map - 56" | HE-TS-0010 | HE-PL-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | Obtain Company Approval - Overall Pipeline Route Map - 56" | Final Issue for Design/ Construction-Overall Pipeline Route Map - 56" | HE-PL-0160 | HE-PL-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | Issue ICR - Pipeline Specifications - Addendum to DGS | Receive Company Comments - Pipeline Specifications - Addendum to DGS | HE-PL-0070 | HE-PL-0080 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | Project Kick off Meeting | Issue ICR - Pipeline Specifications - Addendum to DGS | ML1002 | HE-PL-0070 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | Project Kick off Meeting | Issue ICR - Specification - Pipeline Wall Thickness Calculation Report | ML1002 | HE-PL-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | Receive Company Comments - Pipeline MTO - 56" | Re-Issue for Approval - Pipeline MTO - 56" | HE-PL-3240 | HE-PL-3250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | Receive Company Comments - Crossing Schedule - 56" | Re-Issue for Approval - Crossing Schedule - 56" | HE-PL-2940 | HE-PL-2950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | Issue ICR - Pipeline Station Approach drawing -56" | Issue ICR - Pipeline Stress Analysis Report | HE-PL-2570 | HE-PL-2810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.1 Pipeline Route Verification and Selection Report | P2543-R01-Oct24..1.EN.1.1 Pipeline Route Verification and Selection Report | Re-Issue for Approval - Pipeline Route Verification and Selection Report | Obtain Company Approval - Pipeline Route Verification and Selection Report | HE-PL-2770 | HE-PL-2780 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | Issue ICR - Pipeline Station Approach drawing -52" | Receive Company Comments - Pipeline Station Approach drawing -52" | HE-PL-2630 | HE-PL-2640 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | Issue ICR - Pipeline Alignment Sheets-52" | Receive Company Comments - Pipeline Alignment Sheets-52" | HE-PL-2450 | HE-PL-2460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | Re-Issue for Approval - Overall Pipeline Route Map - 52" | Re-Issue for Approval - Pipeline Alignment Sheets-52" | HE-PL-0210 | HE-PL-2470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | Issue ICR-Topographical Survey Report (Overall) | Issue ICR - Pipeline Alignment Sheets -56" | HE-TS-0010 | HE-PL-2390 | FS | Completed | Completed | 10
P2543-R01-Oct24..1.1.1.19.1 Ordering | P2543-R01-Oct24..1.EN.6.2.54 TBE for Pig Signaler | RFQ, Receipt of Bid for Pig Signaler | Issue ICR- TBE for Pig Signaler | HP-ME-1120 | HE-PL-2330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.1.1 Ordering | P2543-R01-Oct24..1.EN.6.2.26 TBE for Mainline Ball Valve | RFQ, Receipt of Bid for Manual/Ball/ Globe/ Check/ Plug Valves | Issue ICR - TBE for Mainline Ball Valve | HP-ME-1070 | HE-PL-2270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.26 TBE for Mainline Ball Valve | P2543-R01-Oct24..1.EN.6.2.26 TBE for Mainline Ball Valve | Re-Issue for Approval - TBE for Mainline Ball Valve | Obtain Company Approval - TBE for Mainline Ball Valve | HE-PL-2290 | HE-PL-2300 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.25 TBE for Isolating Joints | P2543-R01-Oct24..1.EN.1.10.25 TBE for Isolating Joints | Obtain Company Approval - TBE for Isolating Joints | Final Issue for Design/ Construction-TBE for Isolating Joints | HE-PL-2240 | HE-PL-2250 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.10.24 TBE for Pigging Tees | P2543-R01-Oct24..1.EN.1.10.24 TBE for Pigging Tees | Issue ICR - TBE for Pigging Tees | Receive Company Comments - TBE for Pigging Tees | HE-PL-2150 | HE-PL-2160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.17.1 Ordering | P2543-R01-Oct24..1.EN.6.2.A331 TBE for Leak Detection System | RFQ, Receipt of Bid for Leak Detection System | Issue ICR-TBE for Leak Detection System | HP-ME-0110 | HE-IC-2230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A331 TBE for Leak Detection System | P2543-R01-Oct24..1.EN.6.2.A331 TBE for Leak Detection System | Re-Issue for Approval-TBE for Leak Detection System | Obtain Company Approval-TBE for Leak Detection System | HE-IC-2250 | HE-IC-2260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Re-Issue for Approval-Material Requisitions for Leak Detection System | Obtain Company Approval-Material Requisitions for Leak Detection System | HE-IC-1770 | HE-IC-1780 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Re-Issue for Approval- FOC Block diagram (Telecom) | Re-Issue for Approval-Instrument Trench Layout | HE-TL-0450 | HE-IC-0990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | Receive Company Comments- Specification for Leak Detection System | Re-Issue for Approval- Specification for Leak Detection System | HE-IC-0260 | HE-IC-0270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | Obtain Company Approval- Power Consumption Calculation (Instrumentation) | Final Issue for Design/ Construction-Power Consumption Calculation (Instrumentation) | HE-EL-5470 | HE-EL-5480 | FS | Not Started | Not Started | 10
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | Re-Issue for Approval - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Issue ICR- Power Consumption Calculation (Instrumentation) | HE-TL-0090 | HE-EL-5440 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | Receive Company Comments- Material Requisitions for Field Instruments / H2S Analyzers | Re-Issue for Approval- Material Requisitions for Field Instruments / H2S Analyzers | HE-IC-1940 | HE-IC-1950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | Re-Issue for Approval- Material Requisitions for Field Instruments / H2S Analyzers | Obtain Company Approval- Material Requisitions for Field Instruments / H2S Analyzers | HE-IC-1950 | HE-IC-1960 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | Issue ICR-Design Basis | Issue ICR- Addendum to DGs | HE-DB-0010 | HE-IC-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Re-Issue for Approval- Instrument Cable Block Diagram | Re-Issue for Approval- Instrument location and Cable Routing Drawings | HE-IC-0810 | HE-IC-2550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Issue ICR-Instrument index -Update | Issue ICR- Instrument location and Cable Routing Drawings | HE-IC-0490 | HE-IC-2530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.15.1 Ordering | P2543-R01-Oct24..1.EN.6.2.10 TBE for Fire & Gas Detectors | RFQ, Receipt of Bid for Field Instruments | Issue ICR- TBE for Gas Detectors | HP-ME-0760 | HE-IC-2350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.5 TBE for ROV/ GOV | P2543-R01-Oct24..1.EN.6.2.5 TBE for ROV/ GOV | Issue ICR- TBE for ROV/ GOV | Receive Company Comments- TBE for ROV/ GOV | HE-IC-2290 | HE-IC-2300 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.21.1 Ordering | P2543-R01-Oct24..1.EN.6.2.A33 TBE for PRS (Pressure Reduction Skid) | RFQ, Receipt of Bid for Pressure Reduction Skid | Issue ICR-TBE for PRS | HP-ME-0060 | HE-IC-2170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A30 TBE for Metering Skid | P2543-R01-Oct24..1.EN.6.2.A30 TBE for Metering Skid | Obtain Company Approval-TBE for Metering Skid | Final Issue for Design/ Construction-TBE for Metering Skid | HE-IC-2140 | HE-IC-2150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.9 Material Requisitions for Fire & Gas Detectors | P2543-R01-Oct24..1.EN.6.11.9 Material Requisitions for Fire & Gas Detectors | Re-Issue for Approval- Material Requisitions for Gas Detectors | Obtain Company Approval- Material Requisitions for Gas Detectors | HE-IC-1890 | HE-IC-1900 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.9 Material Requisitions for Fire & Gas Detectors | P2543-R01-Oct24..1.EN.6.11.9 Material Requisitions for Fire & Gas Detectors | Issue ICR- Material Requisitions for Gas Detectors | Receive Company Comments- Material Requisitions for Gas Detectors | HE-IC-1870 | HE-IC-1880 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A131 Material Requisitions for ROV/ GOV | P2543-R01-Oct24..1.EN.6.11.A131 Material Requisitions for ROV/ GOV | Obtain Company Approval- Material Requisitions for ROV/ GOV | Final Issue for Design/ Construction-Material Requisitions for ROV/ GOV | HE-IC-1660 | HE-IC-1670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | Re-Issue for Approval- Datasheets for PSV & Orifice (incl. RO) | Obtain Company Approval- Datasheets for PSV & Orifice (incl. RO) | HE-IC-1350 | HE-IC-1360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Final Issue for Design/ Construction-Addendum to DGs | Final Issue for Design/ Construction-Data sheet for PRS (Pressure Reduction System) | HE-IC-0050 | HE-IC-1250 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Obtain Company Approval- Data sheet for PRS (Pressure Reduction System) | Final Issue for Design/ Construction-Data sheet for PRS (Pressure Reduction System) | HE-IC-1240 | HE-IC-1250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Receive Company Comments- Data sheet for PRS (Pressure Reduction System) | Re-Issue for Approval- Data sheet for PRS (Pressure Reduction System) | HE-IC-1220 | HE-IC-1230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | Receive Company Comments- Datasheets for Metering Skid | Re-Issue for Approval- Datasheets for Metering Skid | HE-IC-1160 | HE-IC-1170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | Issue ICR- Datasheets for Metering Skid | Receive Company Comments- Datasheets for Metering Skid | HE-IC-1150 | HE-IC-1160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | Re-Issue for Approval- Datasheet for GOV & ROV | Obtain Company Approval- Datasheet for GOV & ROV | HE-IC-1110 | HE-IC-1120 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | Final Issue for Design/ Construction-Addendum to DGs | Final Issue for Design/ Construction-Actuator Datasheet for MOVs | HE-IC-0050 | HE-IC-1070 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Issue ICR-Instrument and F&G Cable Schedule | Receive Company Comments-Instrument and F&G Cable Schedule | HE-IC-0910 | HE-IC-0920 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | Re-Issue for Approval- Specification for RTU | Re-Issue for Approval- Instrument Cable Block Diagram | HE-IC-0210 | HE-IC-0810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | Issue ICR-Instrument index -Update | Issue ICR - Typical Installation Drawings | HE-IC-0490 | HE-IC-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.A3 I/O list | Obtain Company Approval- I/O list -Update | Final Issue for Design/ Construction-I/O list | HE-IC-0580 | HE-IC-0590 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | Issue ICR- P&ID's | Issue ICR-Tie-In Schedule | HE-PR-0110 | HE-PR-0250 | FS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | P2543-R01-Oct24..1.EN.3.17 Line List | Final Issue for Design/ Construction-Vent and Depressurization Report (for new facilities) | Final Issue for Design/ Construction-Line List | HE-PR-1010 | HE-PR-1130 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.10 Equipment List | Final Issue for Design/ Construction-Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | Final Issue for Design/ Construction-Equipment List | HE-PR-0350 | HE-PR-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | Issue ICR - Specification - Pipeline Wall Thickness Calculation Report | Issue ICR- Vent and Depressurization Report (for new facilities) | HE-PL-0010 | HE-PR-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | Final Issue for Design/ Construction - Pipeline Wall Thickness Calculation Report | Final Issue for Design/ Construction-Vent and Depressurization Report (for new facilities) | HE-PL-0050 | HE-PR-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | Obtain Company Approval-Isolation & Tie-In philosophy | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | HE-PR-0880 | HE-PR-0890 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | Obtain Company Approval- Process Simulations Report | Final Issue for Design/ Construction-Process Simulations Report | HE-PR-0640 | HE-PR-0650 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | Obtain Company Approval- Process Datasheets | Final Issue for Design/ Construction-Process Datasheets | HE-PR-0580 | HE-PR-0590 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | Receive Company Comments- Process Datasheets - Pig Launcher / Receiver | Re-Issue for Approval- Process Datasheets - Pig Launcher / Receiver | HE-PR-0500 | HE-PR-0510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | Issue ICR- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | Receive Company Comments- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | HE-PR-0310 | HE-PR-0320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Final Issue for Design/ Construction-Process Simulations Report | Final Issue for Design / Construction-P&ID's | HE-PR-0650 | HE-PR-0160 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Issue ICR- P&ID's | Receive Company Comments-P&ID's | HE-PR-0110 | HE-PR-0120 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Issue ICR- Process Flow Diagrams ( New + Existing) | Issue ICR- P&ID's | HE-PR-0040 | HE-PR-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | Issue ICR- Process Flow Diagrams ( New + Existing) | Receive Company Comments- Process Flow Diagrams ( New + Existing) | HE-PR-0040 | HE-PR-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.1 Site Visit Report | P2543-R01-Oct24..1.EN.2.1 Site Visit Report | Re-Issue for Approval - Site Visit /Survey Report | Obtain Company Approval - Site Visit /Survey Report | HE-SV-0030 | HE-SV-0040 | FF | Completed | Completed | 10
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | Geo Technical Survey | Issue ICR - Geo Technical Survey Report (Overall) | HE-SS-0040 | HE-GS-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | Topographical Survey | Issue ICR-Topographical Survey Report (Overall) | HE-SS-0030 | HE-TS-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- Plot plan - BVS | Design Review Workshop | HE-PI-0530 | HE-WS-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.2 Planning Package | P2543-R01-Oct24..1.PM.12 Workshops | Final Issue for Design/ Construction-Planning Package | Design Review Workshop | HC-GN-0050 | HE-WS-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.PM.12 Workshops | Receive Company Comments- Plot plan - BVS | HAZID /ENVID/OHID/ PHSER Workshop | HE-PI-0540 | HE-WS-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..1.EN.2 Survey & Studies | Data Acquisition | Site Visit | HE-SS-0010 | HE-SS-0020 | SS | Completed | Completed | 10
P2543-R01-Oct24..1.2.13.4 Topographical survey & Geotechnical Investigation | P2543-R01-Oct24..1.EN.2 Survey & Studies | Place LOA/FOA - Topographical survey & Geotechnical Investigation | Geo Technical Survey | HS-GN-0170 | HE-SS-0040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | Issue ICR- Data sheet for Distribution Transformer | Receive Company Comments-Data sheet for Distribution Transformer | HE-EL-0670 | HE-EL-0680 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | Receive Company Comments-Cable Sizing Calculation | Re-Issue for Approval-Cable Sizing Calculation | HE-EL-0440 | HE-EL-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | Issue ICR-Cable Sizing Calculation | Receive Company Comments-Cable Sizing Calculation | HE-EL-0430 | HE-EL-0440 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..1.EN.9.22 UPS SLDs | Re-Issue for Approval - UPS SLD | Obtain Company Approval - UPS SLD | HE-EL-0270 | HE-EL-0280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | Obtain Company Approval- Adequacy report of the Power supply requirements | Final Issue for Design/ Construction-Electrical Adequacy Check Report | HE-EL-0160 | HE-EL-0170 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | Re-Issue for Approval- Adequacy report of the Power supply requirements | Obtain Company Approval- Adequacy report of the Power supply requirements | HE-EL-0150 | HE-EL-0160 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..1.EN.9.13 Lighting Layout | Receive Company Comments-Lighting Layout | Re-Issue for Approval-Lighting Layout | HE-EL-1700 | HE-EL-1710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..1.EN.9.13 Lighting Layout | Obtain Company Approval-Lighting Layout | Final Issue for Design/ Construction-Lighting Layout | HE-EL-1720 | HE-EL-1730 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..1.EN.9.13 Lighting Layout | Re-Issue for Approval-Lighting Layout | Obtain Company Approval-Lighting Layout | HE-EL-1710 | HE-EL-1720 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.8 TBE for Solar Panels | P2543-R01-Oct24..1.EN.9.6.8 TBE for Solar Panels | Receive Company Comments-TBE for Solar Panels | Re-Issue for Approval-TBE for Solar Panels | HE-EL-1280 | HE-EL-1290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.29 TBE for Active/ Passive Shelters | P2543-R01-Oct24..1.EN.6.2.29 TBE for Active/ Passive Shelters | Issue ICR - TBE for Active / Passive Shelters | Receive Company Comments - TBE for Active / Passive Shelters | HE-EL-1210 | HE-EL-1220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | Re-Issue for Approval-Material Requisition for Power & Control Cables | Obtain Company Approval-Material Requisition for Power & Control Cables | HE-EL-1170 | HE-EL-1180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | Issue ICR-Material Requisition for Power & Control Cables | Receive Company Comments-Material Requisition for Power & Control Cables | HE-EL-1150 | HE-EL-1160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | Re-Issue for Approval- Datasheet for Solar panel system | Re-Issue for Approval-Material Requisition for Solar Panels | HE-EL-0750 | HE-EL-1110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | Receive Company Comments-Material Requisition for Solar Panels | Re-Issue for Approval-Material Requisition for Solar Panels | HE-EL-1100 | HE-EL-1110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | Obtain Company Approval-Material Requisition for Solar Panels | Final Issue for Design/ Construction-Material Requisition for Solar Panels | HE-EL-1120 | HE-EL-1130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | Re-Issue for Approval-Material Requisition for Distribution Boards | Obtain Company Approval-Material Requisition for Distribution Boards | HE-EL-0990 | HE-EL-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | Issue ICR - Material Requisition for Active / Passive Shelters | Receive Company Comments - Material Requisition for Active / Passive Shelters | HE-EL-0850 | HE-EL-0860 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | Re-Issue for Approval-Data sheet for LV Distribution board | Obtain Company Approval-Data sheet for LV Distribution board | HE-EL-0630 | HE-EL-0640 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.10 Cable Schedule | Issue ICR-Cable Sizing Calculation | Issue ICR-Cable Schedule | HE-EL-0430 | HE-EL-0550 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..1.PM.4 NOC Register | Final Issue for Design/ Construction-Overall Pipeline Route Map - 52" | Final Issue for Design/ Construction-NOC Register | HE-PL-0230 | HC-GN-0290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.4 NOC Register | P2543-R01-Oct24..1.PM.4 NOC Register | Re-Issue for Approval-NOC Register | Obtain Company Approval-NOC Register | HC-GN-0270 | HC-GN-0280 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.PM.6 Quality documents | P2543-R01-Oct24..1.PM.6 Quality documents | Re-Issue for Approval-QAQC procedure | Obtain Company Approval-QAQC procedure | HC-GN-0210 | HC-GN-0220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.2 Planning Package | P2543-R01-Oct24..1.PM.2 Planning Package | Receive Company Comments-Planning Package | Re-Issue for Approval-Planning Package | HC-GN-0020 | HC-GN-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.1.1 Ordering | P2543-R01-Oct24..PR.26.1.1.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Distribution Transformer | Ready for Dispatch of Distribution Transformer | HP-ME-0480 | HM-ME-0960 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.2.25.15.1 Ordering | P2543-R01-Oct24..PR.26.1.15.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Field Instruments | Vendor Document Review of Field Instruments | HP-ME-0780 | HM-ME-1520 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.1.14.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.14.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of Access Switch, Fiber Optic Patch Panel and Media Converter | Packaging & Final Inspection-Access Switch, Fiber Optic Patch Panel and Media Converter | HM-ME-1340 | HM-ME-1350 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.4.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Manufacturing & Assembly of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | HM-ME-1220 | HM-ME-1230 | FF | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.LL.6.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.6.3 Delivery & receipt at Site | Ready for Dispatch of Solar PV system | Transportation/ Custom Clearance/ Delivery at site of Solar PV system | HM-ME-1060 | HM-ME-1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.8.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.8.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of AC UPS | Receipt at site and inspection of AC UPS | HM-ME-0780 | HM-ME-0790 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.8.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.8.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-AC UPS | Ready for Dispatch of AC UPS | HM-ME-0750 | HM-ME-0760 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.10.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of ROV/ GOV | Testing and Inspection of ROV/ GOV | HM-ME-0520 | HM-ME-0530 | FS | In Progress | Not Started | 12
P2543-R01-Oct24..PR.26.1.2.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.2.3 Delivery & receipt at Site | Ready for Dispatch of Fire Suppression System | Transportation/ Custom Clearance/ Delivery at site of Fire Suppression System | HM-ME-1890 | HM-ME-1820 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.2.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.2.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Fire Suppression System | Ready for Dispatch of Fire Suppression System | HM-ME-1880 | HM-ME-1890 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.21.1 Ordering | P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Pressure Reduction Skid | Vendor Document Review of Pressure Reduction Skid | HP-ME-0080 | HM-ME-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.22.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.22.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of Custody Metering Skid | Packaging & Final Inspection-Custody Metering Skid | HM-ME-0030 | HM-ME-0040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.LL.22.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - Sales Gas Metering Skids | Vendor Document Review of Custody Metering Skid | ML1259-C09 | HM-ME-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Earthing Material (Lot 1) | Receipt at site and inspection of Earthing Material (Lot 1) | HM-EL-0370 | HM-EL-0380 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | Final Piping Bulk material MTO | Final Piping Bulk material MTO | HM-PI-0020 | HM-PI-0050 | FF | Not Started | Not Started | 14
P2543-R01-Oct24..1.EN.4.16 Datasheets for fire fighting and safety equipment | P2543-R01-Oct24..PR.BK.4.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Datasheets for fire fighting and safety equipment | Final Piping Bulk material MTO | HE-HS-0470 | HM-PI-0020 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.5.1 Ordering | P2543-R01-Oct24..PR.BK.5.2 Manufacturing & Ready for Dispatch | 1st Structural Bulk material MTO | 1st Structural Bulk material MTO | HP-BK-0300 | HM-CS-0080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.11.1 Ordering | P2543-R01-Oct24..PR.BK.11.2 Manufacturing & Ready for Dispatch | 1st Civil Bulk material MTO | 1st Civil Bulk material MTO | HP-BK-0260 | HM-CS-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Cable Trays (Lot 1) | Receipt at site and inspection of Cable Trays (Lot 2) | HM-EL-0270 | HM-EL-0280 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Power & Control Cables | Manufacturing & Assembly of Power & Control Cables | HM-EL-0010 | HM-EL-0020 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.BK.16.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.16.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of MCT (Lot 1) | Receipt at site and inspection of MCT (Lot 1) | HM-EL-0470 | HM-EL-0480 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Receipt at site and inspection of Line Pipes - Lot 2 (Coated) | Receipt at site and inspection of Line Pipes - Lot 3 (Coated) | HM-PL-0090 | HM-PL-0100 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Pigging & Split Tee (Lot 1) | Receipt at site and inspection of Pigging & Split Tee (Lot 1) | HM-PL-0830 | HM-PL-0840 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.1.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Hot Incution Bend | Testing and Inspection of Hot Incution Bend | HM-PL-0570 | HM-PL-0580 | FF | In Progress | Not Started | 14
P2543-R01-Oct24..PR.26.LL.20.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.20.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of CP System | Packaging & Final Inspection-CP System | HM-PL-0370 | HM-PL-0380 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | Vendor Document Review of CP System | Receipt at site and inspection of CP System - Temporary Material | HM-PL-0350 | HM-PL-0410 | FF | In Progress | Not Started | 5
P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | Testing and Inspection of Ball/ Globe/ Check/ Plug Valves | Packaging & Final Inspection-Ball/ Globe/ Check/ Plug Valves | HM-PL-0170 | HM-PL-0180 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - Line pipes | Vendor Document Review of Ball/ Globe/ Check/ Plug Valves | ML1040-C01 | HM-PL-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..ML.4 Commissioning and PAC | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | Achieve (PAC-2) for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | CCM-PM4520 | ML2049-F06 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Complete Pipeline welding - 52" Sales Gas Pipeline - 50% Welding | Complete Pipeline welding - 52" Sales Gas Pipeline - 75% Welding | ML1699-E15 | ML1709-E16 | FS | Not Started | Not Started | 49
P2543-R01-Oct24..4.4.AB.2 Final Documentation | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Close-out report | Complete As-Built drawings including Project close out report and submit to COMPANY | CAB-5320 | ML1989-E44 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.22.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Custody Metering Skid | Receive at Site - Sales Gas Metering Skids | HM-ME-0080 | ML1419-D08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.24.2 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Hot Tapping Material | Receive at Site - Isolation Joints, Barred Tee, and Anchor Flanges | HM-PL-0320 | ML1409-D24 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.21.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Pressure Reduction Skid | Receive at Site - Pressure Reduction Skids | HM-ME-0180 | ML1051-D07 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of MOV (Lot 1) | Receive at Site - MOV/ROV/GOV Valves | HM-ME-0680 | ML1024-D06 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Receive at Site - E&I Equipment's (CCTV System) | HM-ME-1290 | ML1056-D14 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.1.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Manual/ Ball/ Globe/ Check/ Plug Valves | Issue Purchase Order (Final) - Valves – Globe/Check/Plug | HP-ME-1090 | ML1369-C21 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.10.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for ROV/ GOV | Issue Purchase Order (Final) - RTUs | HP-ME-0280 | ML1349-C19 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.18.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Gas Detectors | Issue Purchase Order (Final) - F & G System | HP-ME-0730 | ML1269-C12 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.3.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for Isolating Joints | Issue Purchase Order (Final) - Isolation Joints | HP-ME-1240 | ML1041-C03 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction - Pressure Reduction Skid and Leak Detection Drawings | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-0770 | ML1035-B26 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical Detailed Drawing - Jib Crane Foundation | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-1070 | ML1035-B26 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Gas metering skid foundation drawings | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-0830 | ML1034-B25 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.17 Typical details of protection slab to protect existing UG pipe at road crossing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical details of protection slab to protect existing UG pipe at road crossing | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-0410 | ML1034-B25 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-1190 | ML1034-B25 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-TYPICAL GA AND RC DETAILS OF IMPACT WALL | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-1250 | ML1034-B25 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | HE-TL-0410 | ML1033-B22 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Earthing Layout | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | HE-EL-1670 | ML1032-B21 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-UPS SLD | Issue SLD, Hazardous Area Classification Details for All Areas - IFC | HE-EL-0290 | ML1031-B20 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Issue PFDs, P&IDs, Plot Plans, Equipment Layouts and Equipment List, for all Facilities for HAZOP | HE-PR-0060 | ML1012-B06 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Overall Pipeline Route Map - 52" | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 52" Pipeline(IFC) | HE-PL-0230 | ML1009-B04 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-1310 | ML1209-B27 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Pipeline Station approach drawing-52" | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | HE-PL-2670 | ML1059-B28 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Receive at Site - Pressure Reduction Skids | Project Finish | ML1051-D07 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Hydrotesting - 56" Sales Gas Pipeline | Project Finish | ML1639-E09 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Hydrotesting - 4" Nitrogen Pipeline | Project Finish | ML1919-E37 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | Project Finish | ML1579-E03 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 05 to BVS-06 | Project Finish | ML1809-E26 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Receive at Site - Isolation Joints, Barred Tee, and Anchor Flanges | Project Finish | ML1409-D24 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Pipeline welding - 56" Sales Gas Pipeline (100% Welding) | Project Finish | ML1599-E05 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Pipeline Jointing - 4" Waterline | Project Finish | ML1879-E33 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Receive at Site - Valves – Globe/Check/Plug | Project Finish | ML1529-D20 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Achieve Mechanical Completion of PL & facilities- ( 36"Jump over Line) | Project Finish | ML1969-E42 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.4 Commissioning and PAC | P2543-R01-Oct24..ML Milestones | Commission New pipeline system -52" Sales Gas Pipeline | Project Finish | ML2009-F02 | ML1060 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Electrical | General | CAB-4450 | CAB-5290 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Pipeline | General | CAB-4480 | CAB-5290 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Issue Project Control, PMS and Planning Dossier covering Baseline Schedule, Histograms, S-Curves, etc. - Final Issue | General | ML1002-A02 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | HSE | Vendor Documents Package | CAB-4410 | CAB-5310 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..PR.26.LL.21.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of Pressure Reduction Skid | Vendor Documents Package | HM-ME-0180 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of MOV (Lot 1) | Vendor Documents Package | HM-ME-0680 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Piping | Vendor Documents Package | CAB-4440 | CAB-5310 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | HSE | Quality Dossier | CAB-4410 | CAB-5300 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Overall Pipeline Route Map - 56" | Pipeline | HE-PL-0170 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.27 Pipeline Typical Drawings | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline Typical Drawings | Pipeline | HE-PL-0410 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.44 Detailed crossing drawings-4" | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Detailed crossing drawings-4" | Pipeline | HE-PL-3150 | CAB-4480 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | Telecom | ML1030 | CAB-4470 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Telecom | ML1015-B08 | CAB-4470 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Telecom cable schedule | Telecom | HE-TL-0830 | CAB-4470 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Specification for Leak Detection System | Instrumentation & Control | HE-IC-0290 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR-Instrument index -Update | Instrumentation & Control | HE-IC-0490 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.11.A1311 Material Requisitions for MOV | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisitions for MOV | Instrumentation & Control | HE-IC-1610 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisition for Power & Control Cables | Electrical | HE-EL-1190 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisition for Distribution Transformer | Electrical | HE-EL-1070 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Electrical | ML1014-B10 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Electrical | ML1015-B08 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Piping | HE-PI-0370 | CAB-4440 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Piping Isometrics | Piping | HE-PI-1240 | CAB-4440 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.5.3.9 TBE for Sals Gas CRS Filters | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBEs for Sales Gas CRS Filters | Mechanical | HE-ME-0230 | CAB-4430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.28 Calculation for Pig launcher and receiver foundations | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Calculation for Pig launcher and receiver foundations | Civil & Structural | HE-CS-0590 | CAB-4420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Civil & Structural | ML1015-B08 | CAB-4420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Civil & Structural | HE-CS-0650 | CAB-4420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-HSE Action Tracking Register (Hazards and Effects Register) | HSE | HE-HS-1070 | CAB-4410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Process Datasheets - Filters (At Sweihan CRS) | Process | HE-PR-0470 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Tie-in Philosophy for all new facilities - IFC | Process | ML1010-B14 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Process Datasheets - Pig Launcher / Receiver | Process | HE-PR-0530 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | Process | HE-PR-0350 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Vent and Depressurization Report (for new facilities) | Process | HE-PR-1010 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Final Issue for Design/ Construction-Operating , control and safeguarding philosophy | Issue ICR-Pre-commissioning and Commissioning Plan | HE-PR-0770 | C-COM-800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.21 HAZOP close out report | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Final Issue for Design/ Construction-HAZOP close out report | Issue ICR-Pre-commissioning and Commissioning Plan | HE-HS-0770 | C-COM-800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | Re-Issue for Approval-Shutdown Requirements & Plan | Obtain Company Approval-Shutdown Requirements & Plan | C-COM-870 | C-COM-880 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Power Consumption Calculation (Instrumentation) | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-EL-5480 | C-COM-790 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.28 Calculation for Pig launcher and receiver foundations | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Calculation for Pig launcher and receiver foundations | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-CS-0590 | C-COM-790 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Re-Issue for Approval-Construction Procedures / Method Statements / ITPs | HE-PR-0890 | C-COM-770 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Issue MR (Final) - Hot Bends | Issue ICR-Construction Procedures / Method Statements / ITPs | ML1189-B16 | C-COM-750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Pipe Wall Thickness Calculation | Issue ICR-Construction Procedures / Method Statements / ITPs | HE-PI-0240 | C-COM-750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Project Kick off Meeting | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | ML1002 | CTF-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.16 Electrical MTO | P2543-R01-Oct24..1.1.BK.7.1 Ordering | Electrical 3rd MTO | Final Electrical Bulk material MTO | HE-EL-1850 | HP-BK-0430 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..1.1.1.2.1 Ordering | P2543-R01-Oct24..1.1.1.2.1 Ordering | RFQ, Receipt of Bid for Pigging & Split Tee | Prepare TBE and Company approval for Pigging & Split Tee | HP-ME-1270 | HP-ME-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.3.1 Ordering | P2543-R01-Oct24..1.1.1.3.1 Ordering | RFQ, Receipt of Bid for Isolating Joints | Prepare TBE and Company approval for Isolating Joints | HP-ME-1220 | HP-ME-1230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.19.1 Ordering | P2543-R01-Oct24..1.1.1.19.1 Ordering | RFQ, Receipt of Bid for Pig Signaler | Prepare TBE and Company approval for Pig Signaler | HP-ME-1120 | HP-ME-1130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.21 Material Requisition for Manual Ball Valves | P2543-R01-Oct24..1.1.BK.1.1 Ordering | Issue ICR - MR for Mainline Ball Valve | RFQ, Receipt of Bid for Manual/Ball/ Globe/ Check/ Plug Valves | HE-PL-1690 | HP-ME-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.7.1 Ordering | P2543-R01-Oct24..1.1.2.25.7.1 Ordering | Prepare TBE and Company approval for Power Distribution Boards | Commercial Clarifications & Placement of PO for Power Distribution Boards | HP-ME-0420 | HP-ME-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A131 Material Requisitions for ROV/ GOV | P2543-R01-Oct24..1.1.2.LL.10.1 Ordering | Final Issue for Design/ Construction-Material Requisitions for ROV/ GOV | Commercial Clarifications & Placement of PO for ROV/ GOV | HE-IC-1670 | HP-ME-0280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | P2543-R01-Oct24..1.1.2.LL.11.1 Ordering | Issue ICR-Material Requisitions for Sales Gas CRS Filters | RFQ, Receipt of Bid for Filter Package | HE-ME-0130 | HP-ME-0160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A33 TBE for PRS (Pressure Reduction Skid) | P2543-R01-Oct24..1.1.2.LL.21.1 Ordering | Final Issue for Design/ Construction-TBE for PRS | Commercial Clarifications & Placement of PO for Pressure Reduction Skid | HE-IC-2210 | HP-ME-0080 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.1.2.25.15.1 Ordering | Issue ICR- Material Requisitions for Field Instruments / H2S Analyzers | RFQ, Receipt of Bid for Field Instruments | HE-IC-1930 | HP-ME-0760 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.4.1 Ordering | P2543-R01-Oct24..1.1.2.LL.4.1 Ordering | Prepare TBE and Company approval for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Commercial Clarifications & Placement of PO for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HP-ME-0620 | HP-ME-0630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | P2543-R01-Oct24..1.1.2.LL.5.1 Ordering | Issue ICR - Material Requisition for Active / Passive Shelters | RFQ, Receipt of Bid for Active/ Passive Cooled Shelter | HE-EL-0850 | HP-ME-0560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.12 Building | P2543-R01-Oct24..1.2.12.12 Building | Building Complete Evaluation (Internal) | Building Subcontract Award | HS-CN-0580 | HS-CN-0590 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.7 OHPL | P2543-R01-Oct24..1.2.12.7 OHPL | OHPL RFQ & Quotation Receipt | OHPL Complete Evaluation (Internal) | HS-CN-0410 | HS-CN-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.2.12.4 NDT / PWHT | Project Kick off Meeting | NDT / PWHT RFQ & Quotation Receipt | ML1002 | HS-CN-0160 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | Project Kick off Meeting | Testing & Precommissioning RFQ & Quotation Receipt | ML1002 | HS-CN-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..1.2.12.2 NDRC | NDRC Complete Evaluation (Internal) | NDRC Subcontract Award | HS-CN-0080 | HS-CN-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.2.12.2 NDRC | Project Kick off Meeting | NDRC RFQ & Quotation Receipt | ML1002 | HS-CN-0060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.4 Project HSE Plan | P2543-R01-Oct24..1.2.13.9 HSE Studies | Issue ICR-HSE Plan | Prepare/Issue Scope of Work - HSE Studies | HE-HS-0010 | HS-GN-0070 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | Issue ICR- Specification for Leak Detection System | RFQ, Receipt of Bid - Modification of Existing DCS | HE-IC-0250 | HS-GN-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.5 Hot Tapping | P2543-R01-Oct24..1.1.1.5 Hot Tapping | + | Commercial Clarifications & Placement of PO- Hot Tapping | HS-GN-0220 | HS-GN-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | Issued for Review - Impact Wall GA and RC (type) details | Review Company Comments - Impact Wall GA and RC (type) details | HE-CS-1210 | HE-CS-1220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | Issue ICR- Plot plan - BVS | Issued for Review - Valve pit foundation GA and RC (type) details | HE-PI-0530 | HE-CS-1150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | Re-Issue for Approval - Typical Detailed Drawing - Jib Crane Foundation | Obtain Company Approval - Typical Detailed Drawing - Jib Crane Foundation | HE-CS-1050 | HE-CS-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | Re-Issue for Approval - Lighting pole foundation details | Obtain Company Approval - Lighting pole foundation details | HE-CS-0990 | HE-CS-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.33 Filter Foundation GA and Details | P2543-R01-Oct24..1.EN.8.33 Filter Foundation GA and Details | Obtain Company Approval - Typical Spill Pit General Arrangement And RC (type) Details | Final Issue for Design/ Construction-FILTER FOUNDATION GA AND DETAILS | HE-CS-0940 | HE-CS-0950 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.33 Filter Foundation GA and Details | P2543-R01-Oct24..1.EN.8.33 Filter Foundation GA and Details | Issued for Review - Typical Spill Pit General Arrangement And RC (type) Details | Review Company Comments - Typical Spill Pit General Arrangement And RC (type) Details | HE-CS-0910 | HE-CS-0920 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | Re-Issue for Approval - Solar panel foundation details | Obtain Company Approval - Solar panel foundation details | HE-CS-0870 | HE-CS-0880 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | Issued for Review - Solar panel foundation details | Review Company Comments - Solar panel foundation details | HE-CS-0850 | HE-CS-0860 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | Issued for Review - Gas metering skid foundation drawings | Review Company Comments - Gas metering skid foundation drawings | HE-CS-0790 | HE-CS-0800 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | Issued for Review - Pressure Reduction Skid and Leak Detection Drawings | HE-PI-0390 | HE-CS-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.28 Calculation for Pig launcher and receiver foundations | P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | Final Issue for Design/ Construction-Calculation for Pig launcher and receiver foundations | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | HE-CS-0590 | HE-CS-0650 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..1.EN.8.11 Civil UG layout | Issued for Review - Civil UG layout | Review Company Comments - Civil UG layout | HE-CS-0490 | HE-CS-0500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | Obtain Company Approval - Typical Road and paving detail drawing | Final Issue for Design/ Construction-Typical Road and paving detail drawing | HE-CS-0280 | HE-CS-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | Re-Issue for Approval - Standard drawings for Anchor bolt | Obtain Company Approval - Standard drawings for Anchor bolt | HE-CS-0090 | HE-CS-0100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | Review Company Comments - Addendum to DGs | Re-Issue for Approval - Addendum to DGs | HE-CS-0020 | HE-CS-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | Issued for Review - Addendum to DGs | Review Company Comments - Addendum to DGs | HE-CS-0010 | HE-CS-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | Issue ICR-Design Basis | Issued for Review - Addendum to DGs | HE-DB-0010 | HE-CS-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Issued - Civil MTO 2 | HE-CS-0350 | HE-CS-1550 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | P2543-R01-Oct24..1.EN.8.41 Misc. supports | Final Issue for Design/ Construction-Piping Stress Analysis & Report | Final Issue for Design/ Construction-Misc. supports | HE-PI-1180 | HE-CS-1490 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.5.3.9 TBE for Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.3.9 TBE for Sals Gas CRS Filters | Obtain Company Approval-TBEs for Sales Gas CRS Filters | Final Issue for Design/ Construction-TBEs for Sales Gas CRS Filters | HE-ME-0220 | HE-ME-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | Issue ICR-Material Requisitions for Sales Gas CRS Filters | Receive Company Comments-Material Requisitions for Sales Gas CRS Filters | HE-ME-0130 | HE-ME-0140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | Issue ICR- Addendum to DGS | Issue ICR-Material Requisitions for Sales Gas CRS Filters | HE-ME-0010 | HE-ME-0130 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | Receive Company Comments- Addendum to DGS | Re-Issue for Approval- Addendum to DGS | HE-ME-0020 | HE-ME-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue for HAZOP Studies- Plot plan - BVS | HE-PR-0060 | HE-PI-0550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue after incorporating HAZOP / Review Comments- Plot plan - BVS | HE-PR-0070 | HE-PI-0560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue for HAZOP Studies- Overall Plot Plan - 4" N2 Source Pipeline | HE-PR-0060 | HE-PI-0480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Final Issue for Design/ Construction-Topographical Survey Report (Overall) | Final Issue for Design/ Construction-Overall Plot Plan- 4" N2 Source Pipeline | HE-TS-0050 | HE-PI-0510 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Obtain Company Approval- Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | HE-PI-0430 | HE-PI-0440 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Final Issue for Design/ Construction-Process Flow Diagrams ( New + Existing) | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | HE-PR-0090 | HE-PI-0440 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Receive Company Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Re-Issue for HAZOP Studies- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0330 | HE-PI-0340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.16 Critical line List | P2543-R01-Oct24..1.EN.7.16 Critical line List | Re-Issue for Approval-Critical line List | Obtain Company Approval-Critical line List | HE-PI-0282 | HE-PI-0292 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | Issue ICR-Pipe Wall Thickness Calculation | Receive Company Comments-Pipe Wall Thickness Calculation | HE-PI-0200 | HE-PI-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | Obtain Company Approval-Piping Material Specifications | Final Issue for Design/ Construction-Piping Material Specification | HE-PI-0040 | HE-PI-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | Issue ICR-Piping Isometrics | Receive Company Comments-Piping Isometrics | HE-PI-1200 | HE-PI-1210 | FF | Completed | Completed | 10
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | Re-Issue for Approval-Data sheet for Ball Valves | Re-Issue for Approval-MR for Ball valves/ Plug Valves | HE-PI-0920 | HE-PI-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | Issue ICR-Data sheet for Ball Valves | Issue ICR-MR for Ball valves/ Plug Valves | HE-PI-0900 | HE-PI-1020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | Re-Issue for Approval- Datasheet for Plug Valves | Obtain Company Approval- Datasheet for Plug Valves | HE-PI-0980 | HE-PI-0990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | Re-Issue for Approval-Piping GA Drawings for 591-BVS-01 | Obtain Company Approval-Piping GA Drawings for 591-BVS-01 | HE-PI-0800 | HE-PI-0810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | Issue ICR- Process Simulations Report | Issue ICR - Piping GA Drawings for 591-BVS-01 | HE-PR-0610 | HE-PI-0780 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | Obtain Company Approval-Piping GA for 4" N2 Source Pipeline | Final Issue for Design/ Construction-Piping GA for 4" N2 Source Pipeline | HE-PI-0750 | HE-PI-0760 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | Re-Issue for Approval-Piping GA for 52" Pipeline SWEIHAN CRS | Obtain Company Approval-Piping GA for 52" Pipeline SWEIHAN CRS | HE-PI-0680 | HE-PI-0690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Obtain Company Approval-Piping GA-56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction-Piping GA- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0630 | HE-PI-0640 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction-Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction-Piping GA- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0370 | HE-PI-0640 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction-Piping Stress Analysis & Report | Final Issue for Design/ Construction-Piping GA- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-1180 | HE-PI-0640 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.7.10 3D Model | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | 60% Model Review | HE-PR-0140 | HE-PI-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | Issue ICR- HAZOP reviews Report for all areas | Receive Company Comments- HAZOP reviews Report for all areas | HE-HS-0670 | HE-HS-0680 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | Final Issue for Design/ Construction-HAZOP Procedure | Final Issue for Design/ Construction-HAZOP Review Report | HE-HS-0230 | HE-HS-0710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.19 HAZID/ ENVID/ OHID Close out Report | P2543-R01-Oct24..1.EN.4.19 HAZID/ ENVID/ OHID Close out Report | Issue ICR-HAZID/ ENVID/ OHID Close out Report | Receive Company Comments-HAZID/ ENVID/ OHID Close out Report | HE-HS-0610 | HE-HS-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | Receive Company Comments-HAZID/ ENVID/ OHID Report | Re-Issue for Approval-HAZID/ ENVID/ OHID Report | HE-HS-0560 | HE-HS-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | Issue ICR-HAZID/ ENVID/ OHID Report | Receive Company Comments-HAZID/ ENVID/ OHID Report | HE-HS-0550 | HE-HS-0560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | Receive Company Comments- HSEIA Study Report | Re-Issue for Approval- HSEIA Study Report | HE-HS-0500 | HE-HS-0510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.4.5 F&G layout | Re-Issue after incorporating HAZOP /Review Comments - 4" N2 Source Pipeline | Issue ICR-F&G Layout | HE-PI-0490 | HE-HS-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | Receive Company Comments-HAZOP Procedure | Re-Issue for Approval-HAZOP Procedure | HE-HS-0200 | HE-HS-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | Obtain Company Approval - HAZID / ENVID / OHID Procedure | Final Issue for Design/ Construction-HAZID / ENVID / OHID Procedure | HE-HS-0160 | HE-HS-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.9 HSE Studies | P2543-R01-Oct24..1.EN.4.1 HAZID / ENVID / OHID Procedure | Place LOA/FOA - HSE Studies | Issue ICR - HAZID / ENVID / OHID Procedure | HS-GN-0110 | HE-HS-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | Issue ICR- HAZOP reviews Report for all areas | Issue ICR-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-0670 | HE-HS-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.11 QRA Report | P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | Issue ICR-QRA Report | Issue ICR-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-0790 | HE-HS-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | Issue ICR-HAZID/ ENVID/ OHID Report | Issue ICR-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-0550 | HE-HS-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.12 PHSER Report | P2543-R01-Oct24..1.EN.4.12 PHSER Report | Receive Company Comments-PHSER Report | Re-Issue for Approval-PHSER Report | HE-HS-0860 | HE-HS-0870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | Obtain Company Approval-Telecom Equipment Layout | Final Issue for Design/ Construction-Telecom Equipment Layout | HE-TL-0760 | HE-TL-0770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | Re-Issue for Approval- FOC Block diagram (Telecom) | Re-Issue for Approval-Telecom Equipment Layout | HE-TL-0450 | HE-TL-0750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Final Issue for Design/ Construction-Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Final Issue for Design/ Construction-Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0110 | HE-TL-0530 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Final Issue for Design/ Construction-Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Final Issue for Design/ Construction-Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0230 | HE-TL-0530 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Re-Issue for Approval- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Obtain Company Approval- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0510 | HE-TL-0520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | Issue ICR- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Receive Company Comments- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0190 | HE-TL-0200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Issue ICR- Telecom Tie-in Block Diagram | Receive Company Comments- Telecom Tie-in Block Diagram | HE-TL-0370 | HE-TL-0380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..1.EN.10.2 Telecom MTO | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Telecom 3rd MTO | HE-TL-0710 | HE-TL-0890 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Final Issue for Design/ Construction-Telecom cable schedule | HE-TL-0410 | HE-TL-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Final Issue for Design/ Construction-Telecom Equipment Layout | Final Issue for Design/ Construction-Telecom cable schedule | HE-TL-0770 | HE-TL-0830 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Final Issue for Design/ Construction-Telecom cable schedule | HE-TL-0470 | HE-TL-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Obtain Company Approval- Telecom Cable Schedule | Final Issue for Design/ Construction-Telecom cable schedule | HE-TL-0820 | HE-TL-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Re-Issue for Approval- Telecom Tie-in Block Diagram | Re-Issue for Approval- Telecom Cable Schedule | HE-TL-0390 | HE-TL-0810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Issue ICR- FOC Block diagram (Telecom) | Issue ICR- Telecom Cable Schedule | HE-TL-0430 | HE-TL-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | Obtain Company Approval-Telecom Location and Cable Routing layout | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | HE-TL-0700 | HE-TL-0710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Receive Company Comments- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0550 | HE-TL-0560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Issue ICR- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0190 | HE-TL-0550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Issue ICR- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0490 | HE-TL-0550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Re-Issue for Approval- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Obtain Company Approval- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0570 | HE-TL-0580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Re-Issue for Approval - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Re-Issue for Approval- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0090 | HE-TL-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Re-Issue for Approval- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Obtain Company Approval- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-TL-0270 | HE-TL-0280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.43 Material Requisition for Pig Signaler | P2543-R01-Oct24..1.EN.6.11.43 Material Requisition for Pig Signaler | Obtain Company Approval- Material Requisition for Pig Signaler | Final Issue for Design/ Construction-Material Requisition for Pig Signaler | HE-PL-1960 | HE-PL-1970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..1.EN.6.11.43 Material Requisition for Pig Signaler | Obtain Company Approval - Pipeline Alignment Sheets-52" | Issue ICR- Material Requisition for Pig Signaler | HE-PL-2480 | HE-PL-1930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.10 Data Sheet - Hot Induction Bends | P2543-R01-Oct24..1.EN.1.9.18 MR for Hot Induction Bends | Re-Issue for Approval - Data Sheet - Hot Induction Bends | Re-Issue for Approval - MR for Hot Induction Bends | HE-PL-1290 | HE-PL-1770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.18 MR for Hot Induction Bends | P2543-R01-Oct24..1.EN.1.9.18 MR for Hot Induction Bends | Issue ICR - MR for Hot Induction Bends | Receive Company Comments - MR for Hot Induction Bends | HE-PL-1750 | HE-PL-1760 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.21 Material Requisition for Manual Ball Valves | P2543-R01-Oct24..1.EN.6.11.21 Material Requisition for Manual Ball Valves | Issue ICR - MR for Mainline Ball Valve | Receive Company Comments - MR for Mainline Ball Valve | HE-PL-1690 | HE-PL-1700 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.17 MR for Linepipes | P2543-R01-Oct24..1.EN.1.9.17 MR for Linepipes | Obtain Company Approval - MR for Line pipes | Final Issue for Design/ Construction-MR for Line pipes | HE-PL-1660 | HE-PL-1670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.17 MR for Linepipes | P2543-R01-Oct24..1.EN.1.9.17 MR for Linepipes | Receive Company Comments - MR for Line pipes | Re-Issue for Approval - MR for Line pipes | HE-PL-1640 | HE-PL-1650 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.14 Data Sheet - Anchor Flange | P2543-R01-Oct24..1.EN.1.60.14 Data Sheet - Anchor Flange | Obtain Company Approval - Data Sheet - Anchor Flange (If Required) | Final Issue for Design/ Construction-Data Sheet - Anchor Flange | HE-PL-1540 | HE-PL-1550 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | P2543-R01-Oct24..1.EN.1.60.14 Data Sheet - Anchor Flange | Issue ICR - Pipeline Stress Analysis Report | Issue ICR - Data Sheet - Anchor Flange (If Required) | HE-PL-2810 | HE-PL-1510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.12 Data Sheet - Pipeline Pigging Tees | P2543-R01-Oct24..1.EN.1.60.12 Data Sheet - Pipeline Pigging Tees | Receive Company Comments - Data Sheet - Pigging Tees | Re-Issue for Approval - Data Sheet - Pigging Tees | HE-PL-1460 | HE-PL-1470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.51 Data Sheet - Mainline Ball Valve | P2543-R01-Oct24..1.EN.6.4.51 Data Sheet - Mainline Ball Valve | Issue ICR - Data Sheet - Mainline Ball Valve | Receive Company Comments - Data Sheet - Mainline Ball Valve | HE-PL-1210 | HE-PL-1220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.9 Data Sheet - Linepipes | P2543-R01-Oct24..1.EN.1.60.9 Data Sheet - Linepipes | Re-Issue for Approval - Data Sheet - Line pipes | Obtain Company Approval - Data Sheet - Line pipes | HE-PL-1170 | HE-PL-1180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.1.6 Pipeline Location Class selection Report | Issue ICR-Design Basis | Issue ICR - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | HE-DB-0010 | HE-PL-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | P2543-R01-Oct24..1.EN.1.6 Pipeline Location Class selection Report | Issue ICR - Pipeline Specifications - Addendum to DGS | Issue ICR - Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | HE-PL-0070 | HE-PL-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..1.EN.1.6 Pipeline Location Class selection Report | Final Issue for Design/ Construction-Overall Pipeline Route Map - 52" | Final Issue for Design/ Construction-Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | HE-PL-0230 | HE-PL-0830 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.1.3 Pipeline Upheavl Calculation | Issue ICR- Process Simulations Report | Issue ICR - Pipeline Upheaval Calculation | HE-PR-0610 | HE-PL-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.40 Specification - Split Tee | P2543-R01-Oct24..1.EN.1.40 Specification - Split Tee | Re-Issue for Approval - Specification - Split Tee | Obtain Company Approval - Specification - Split Tee | HE-PL-0450 | HE-PL-0460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.27 Pipeline Typical Drawings | P2543-R01-Oct24..1.EN.1.27 Pipeline Typical Drawings | Obtain Company Approval - Pipeline Typical Drawings | Final Issue for Design/ Construction-Pipeline Typical Drawings | HE-PL-0400 | HE-PL-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.13 Pipeline Schematic Arrangement- 56", 52" and 4" Pipline | P2543-R01-Oct24..1.EN.1.13 Pipeline Schematic Arrangement- 56", 52" and 4" Pipline | Receive Company Comments - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | Re-Issue for Approval - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | HE-PL-0320 | HE-PL-0330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.13 Pipeline Schematic Arrangement- 56", 52" and 4" Pipline | P2543-R01-Oct24..1.EN.1.13 Pipeline Schematic Arrangement- 56", 52" and 4" Pipline | Issue ICR - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | Receive Company Comments - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | HE-PL-0310 | HE-PL-0320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | Re-Issue for Approval - Pipeline Specifications - Addendum to DGS | Obtain Company Approval - Pipeline Specifications - Addendum to DGS | HE-PL-0090 | HE-PL-0100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | Receive Company Comments - Pipeline Specifications - Addendum to DGS | Re-Issue for Approval - Pipeline Specifications - Addendum to DGS | HE-PL-0080 | HE-PL-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | Obtain Company Approval - Pipeline Specifications - Addendum to DGS | Final Issue for Design/ Construction-Pipeline Specifications - Addendum to DGS | HE-PL-0100 | HE-PL-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | P2543-R01-Oct24..1.EN.1.41 Pipeline Wall Thickness Calculation Report | Obtain Company Approval - Pipeline Wall Thickness Calculation Report | Final Issue for Design/ Construction - Pipeline Wall Thickness Calculation Report | HE-PL-0040 | HE-PL-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | Obtain Company Approval - Pipeline MTO - 56" | Final Issue for Design/ Construction-Pipeline MTO - 56" and 52" | HE-PL-3260 | HE-PL-3270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | Issue ICR - Pipeline MTO - 56" | Receive Company Comments - Pipeline MTO - 56" | HE-PL-3230 | HE-PL-3240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.55 Crossing Schedule-4" | P2543-R01-Oct24..1.EN.1.55 Crossing Schedule-4" | Obtain Company Approval - Crossing Schedule-4" | Final Issue for Design/ Construction-Crossing Schedule-4" | HE-PL-3200 | HE-PL-3210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..1.EN.1.55 Crossing Schedule-4" | Issue ICR - Pipeline Alignment Sheets-4" | Issue ICR - Crossing Schedule-4" | HE-PL-2510 | HE-PL-3170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | Obtain Company Approval - Crossing Schedule - 56" | Final Issue for Design/ Construction-Crossing Schedule - 56" | HE-PL-2960 | HE-PL-2970 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | Issue ICR - Pipeline Alignment Sheets -56" | Issue ICR - Crossing Schedule - 56" | HE-PL-2390 | HE-PL-2930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | Re-Issue for Approval - Pipeline Stress Analysis Report | Obtain Company Approval - Pipeline Stress Analysis Report | HE-PL-2830 | HE-PL-2840 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | P2543-R01-Oct24..1.EN.1.5 Pipeline Stress Analysis Report | Issue ICR - Pipeline Station Approach drawing -52" | Issue ICR - Pipeline Stress Analysis Report | HE-PL-2630 | HE-PL-2810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.1 Pipeline Route Verification and Selection Report | P2543-R01-Oct24..1.EN.1.1 Pipeline Route Verification and Selection Report | Obtain Company Approval - Pipeline Route Verification and Selection Report | Final Issue for Design/ Construction-Pipeline Route Verification and Selection Report | HE-PL-2780 | HE-PL-2790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | Receive Company Comments - Pipeline Station Approach drawing -52" | Re-Issue for Approval - Pipeline Station Approach drawing -52" | HE-PL-2640 | HE-PL-2650 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | Re-Issue for Approval - Pipeline Alignment Sheets-4" | Obtain Company Approval - Pipeline Alignment Sheets-4" | HE-PL-2530 | HE-PL-2540 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | Final Issue for Design/ Construction-Overall Pipeline Route Map - 4" | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | HE-PL-0290 | HE-PL-2490 | FF | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | Re-Issue for Approval - Pipeline Alignment Sheets-52" | Obtain Company Approval - Pipeline Alignment Sheets-52" | HE-PL-2470 | HE-PL-2480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | Re-Issue for Approval - Pipeline Alignment Sheets -56" | Obtain Company Approval - Pipeline Alignment Sheets -56" | HE-PL-2410 | HE-PL-2420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.54 TBE for Pig Signaler | P2543-R01-Oct24..1.EN.6.2.54 TBE for Pig Signaler | Issue ICR- TBE for Pig Signaler | Receive Company Comments- TBE for Pig Signaler | HE-PL-2330 | HE-PL-2340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.25 TBE for Isolating Joints | P2543-R01-Oct24..1.EN.1.10.25 TBE for Isolating Joints | Re-Issue for Approval - TBE for Isolating Joints | Obtain Company Approval - TBE for Isolating Joints | HE-PL-2230 | HE-PL-2240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Issue ICR-Instrument Trench Layout | Receive Company Comments-Instrument Trench Layout | HE-IC-0970 | HE-IC-0980 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Issue ICR- Instrument location and Cable Routing Drawings | Issue ICR-Instrument Trench Layout | HE-IC-2530 | HE-IC-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.8 TBE for Junction Boxes | P2543-R01-Oct24..1.EN.6.2.8 TBE for Junction Boxes | Issue ICR- TBE for Junction Boxes | Receive Company Comments- TBE for Junction Boxes | HE-IC-2470 | HE-IC-2480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.3 TBE for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.EN.6.2.3 TBE for Field Instruments / H2S Analyzers | Re-Issue for Approval- TBE for Field Instruments / H2S Analyzers | Obtain Company Approval- TBE for Field Instruments / H2S Analyzers | HE-IC-2430 | HE-IC-2440 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A2 Instrument Index | Issue ICR- P&ID's | Issue ICR-Instrument index -Update | HE-PR-0110 | HE-IC-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | Obtain Company Approval- Specification for RTU | Final Issue for Design/ Construction-Specification for RTU | HE-IC-0220 | HE-IC-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | Re-Issue for Approval- Specification for RTU | Obtain Company Approval- Specification for RTU | HE-IC-0210 | HE-IC-0220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | Issue ICR- P&ID's | Issue ICR- Specification for RTU | HE-PR-0110 | HE-IC-0190 | FS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | Receive Company Comments- Addendum to DGs | Re-Issue for Approval- Addendum to DGs | HE-IC-0020 | HE-IC-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Issue ICR- Instrument location and Cable Routing Drawings | Receive Company Comments- Instrument location and Cable Routing Drawings | HE-IC-2530 | HE-IC-2540 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Obtain Company Approval- Instrument location and Cable Routing Drawings | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | HE-IC-2560 | HE-IC-2570 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Receive Company Comments- Instrument location and Cable Routing Drawings | Re-Issue for Approval- Instrument location and Cable Routing Drawings | HE-IC-2540 | HE-IC-2550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.10.1 Ordering | P2543-R01-Oct24..1.EN.6.2.5 TBE for ROV/ GOV | RFQ, Receipt of Bid for ROV/ GOV | Issue ICR- TBE for ROV/ GOV | HP-ME-0260 | HE-IC-2290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.22.1 Ordering | P2543-R01-Oct24..1.EN.6.2.A30 TBE for Metering Skid | RFQ, Receipt of Bid for Custody Metering Skid | Issue ICR-TBE for Metering Skid | HP-ME-0010 | HE-IC-2110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A131 Material Requisitions for ROV/ GOV | P2543-R01-Oct24..1.EN.6.11.A131 Material Requisitions for ROV/ GOV | Issue ICR- Material Requisitions for ROV/ GOV | Receive Company Comments- Material Requisitions for ROV/ GOV | HE-IC-1630 | HE-IC-1640 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.A1311 Material Requisitions for MOV | P2543-R01-Oct24..1.EN.6.11.A1311 Material Requisitions for MOV | Obtain Company Approval- Material Requisitions for MOV | Final Issue for Design/ Construction-Material Requisitions for MOV | HE-IC-1600 | HE-IC-1610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | Issue ICR- Datasheets for F&G Devices | Receive Company Comments- Datasheets for F&G Devices | HE-IC-1510 | HE-IC-1520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | Receive Company Comments-Datasheets for Pig Signalers | Re-Issue for Approval-Datasheets for Pig Signalers | HE-IC-1400 | HE-IC-1410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | Issue ICR-Datasheets for Pig Signalers | Receive Company Comments-Datasheets for Pig Signalers | HE-IC-1390 | HE-IC-1400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Issue ICR- Process Datasheets - PRS Skid (at Sweihan CRS) | Issue ICR- Data sheet for PRS (Pressure Reduction System) | HE-PR-0370 | HE-IC-1210 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | Issue ICR- Datasheet for MOV | Receive Company Comments- Datasheet for MOV | HE-IC-1030 | HE-IC-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Re-Issue for Approval-Instrument and F&G Cable Schedule | Obtain Company Approval-Instrument and F&G Cable Schedule | HE-IC-0930 | HE-IC-0940 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Receive Company Comments-Instrument and F&G Cable Schedule | Re-Issue for Approval-Instrument and F&G Cable Schedule | HE-IC-0920 | HE-IC-0930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Final Issue for Design/ Construction-Loop Diagrams | HE-IC-0950 | HE-IC-0770 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Receive Company Comments - Loop Diagrams | Re-Issue for Approval - Loop Diagrams | HE-IC-0740 | HE-IC-0750 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Issue ICR- I/O list -Update | Issue ICR - Loop Diagrams | HE-IC-0550 | HE-IC-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | Receive Company Comments - Hook-Up Diagram | Re-Issue for Approval - Hook-Up Diagram | HE-IC-0620 | HE-IC-0630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | Re-Issue for Approval-Instrument index -Update | Re-Issue for Approval - Hook-Up Diagram | HE-IC-0510 | HE-IC-0630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.A3 I/O list | Re-Issue for Approval- I/O list -Update | Obtain Company Approval- I/O list -Update | HE-IC-0570 | HE-IC-0580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | Receive Company Comments-Tie-In Schedule | Re-Issue for Approval-Tie-In Schedule | HE-PR-0260 | HE-PR-0270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | Issue ICR-Tie-In Schedule | Receive Company Comments-Tie-In Schedule | HE-PR-0250 | HE-PR-0260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.17 Line List | P2543-R01-Oct24..1.EN.3.17 Line List | Obtain Company Approval- Line List | Final Issue for Design/ Construction-Line List | HE-PR-1120 | HE-PR-1130 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.17 Line List | Issue ICR- P&ID's | Issue ICR- Line List | HE-PR-0110 | HE-PR-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.10 Equipment List | Final Issue for Design/ Construction-Process Datasheets - PRS Skid (at Sweihan CRS) | Final Issue for Design/ Construction-Equipment List | HE-PR-0410 | HE-PR-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.10 Equipment List | P2543-R01-Oct24..1.EN.3.10 Equipment List | Receive Company Comments - Equipment List | Re-Issue for Approval - Equipment List | HE-PR-1040 | HE-PR-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.10 Equipment List | Issue ICR- Process Datasheets - Filters (At Sweihan CRS) | Issue ICR - Equipment List | HE-PR-0430 | HE-PR-1030 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | Issue ICR- Vent and Depressurization Report (for new facilities) | Receive Company Comments- Vent and Depressurization Report (for new facilities) | HE-PR-0970 | HE-PR-0980 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | Final Issue for Design/ Construction-Operating , control and safeguarding philosophy | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | HE-PR-0770 | HE-PR-0950 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | Receive Company Comments- Operating and control philosophy , Safeguarding philosophy | Re-Issue for Approval- Operating and control philosophy , Safeguarding philosophy | HE-PR-0740 | HE-PR-0750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | Issue ICR- Process Datasheets | Receive Company Comments- Process Datasheets | HE-PR-0550 | HE-PR-0560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | Obtain Company Approval- Process Datasheets - Pig Launcher / Receiver | Final Issue for Design/ Construction-Process Datasheets - Pig Launcher / Receiver | HE-PR-0520 | HE-PR-0530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Obtain Company Approval-P&ID's | Final Issue for Design / Construction-P&ID's | HE-PR-0150 | HE-PR-0160 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | HE-PR-0070 | HE-PR-0140 | FS | Completed | Completed | 20
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Obtain Company Approval- Process Flow Diagrams ( New + Existing) | HE-PR-0070 | HE-PR-0080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | HE-PR-0060 | HE-PR-0070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.6 Project Risk Review Register | P2543-R01-Oct24..1.EN.2.6 Project Risk Review Register | Obtain Company Approval-Project Risk review register | Final Issue for Design/ Construction-Project Risk Review Register | HE-RR-0040 | HE-RR-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | Issue ICR - Geo Technical Survey Report (Overall) | Receive Company Comments - Geo Technical Survey Report (Overall) | HE-GS-0010 | HE-GS-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | Issue ICR-Topographical Survey Report (Overall) | Receive Company Comments-Topographical Survey Report (Overall) | HE-TS-0010 | HE-TS-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | Receive Company Comments-Topographical Survey Report (Overall) | Re-Issue for Approval-Topographical Survey Report (Overall) | HE-TS-0020 | HE-TS-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.4 Project HSE Plan | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR-HSE Plan | Constructability Review Workshop | HE-HS-0010 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- Overall Plot Plan - 4" N2 Source Pipeline | Constructability Review Workshop | HE-PI-0460 | HE-WS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.PM.12 Workshops | Receive Company Comments- Overall Plot Plan - 52" Pipeline SWEIHAN CRS | HAZID /ENVID/OHID/ PHSER Workshop | HE-PI-0400 | HE-WS-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | P2543-R01-Oct24..1.PM.12 Workshops | Receive Company Comments-HSE Philosophy | HAZID /ENVID/OHID/ PHSER Workshop | HE-HS-0080 | HE-WS-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | Re-Issue for Approval-Material Requisition for Distribution Transformer | Obtain Company Approval-Material Requisition for Distribution Transformer | HE-EL-1050 | HE-EL-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | Re-Issue for Approval-Data sheet for Distribution Transformer | Re-Issue for Approval-Material Requisition for Distribution Transformer | HE-EL-0690 | HE-EL-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | Receive Company Comments-Solar Panel System SLDs | Re-Issue for Approval-Solar Panel System SLDs | HE-EL-0320 | HE-EL-0330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..1.EN.9.22 UPS SLDs | Obtain Company Approval - UPS SLD | Final Issue for Design/ Construction-UPS SLD | HE-EL-0280 | HE-EL-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | P2543-R01-Oct24..1.EN.9.22 UPS SLDs | Issue ICR-Update /New Load List | Issue ICR - UPS SLD | HE-EL-0070 | HE-EL-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | Receive Company Comments-Single Line Diagrams for LV Switchgear | Re-Issue for Approval-Single Line Diagrams for LV Switchgear | HE-EL-0200 | HE-EL-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Re-Issue for Approval-Update /New Load List | HE-PR-0140 | HE-EL-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | Re-Issue for Approval-Cable Routing Layout | Obtain Company Approval-Cable Routing Layout | HE-EL-1590 | HE-EL-1600 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.26 TBE for Power & Control Cables | P2543-R01-Oct24..1.EN.9.6.26 TBE for Power & Control Cables | Issue ICR-TBE for Power & Control Cables | Receive Company Comments-TBE for Power & Control Cables | HE-EL-1510 | HE-EL-1520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.6.1 Ordering | P2543-R01-Oct24..1.EN.9.6.8 TBE for Solar Panels | RFQ, Receipt of Bid for Solar PV system | Issue ICR-TBE for Solar Panels | HP-ME-0510 | HE-EL-1270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.29 TBE for Active/ Passive Shelters | P2543-R01-Oct24..1.EN.6.2.29 TBE for Active/ Passive Shelters | Re-Issue for Approval - TBE for Active / Passive Shelters | Obtain Company Approval - TBE for Active / Passive Shelters | HE-EL-1230 | HE-EL-1240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.5.1 Ordering | P2543-R01-Oct24..1.EN.6.2.29 TBE for Active/ Passive Shelters | RFQ, Receipt of Bid for Active/ Passive Cooled Shelter | Issue ICR - TBE for Active / Passive Shelters | HP-ME-0560 | HE-EL-1210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.18 Material Requisition for UPS System | P2543-R01-Oct24..1.EN.9.1.18 Material Requisition for UPS System | Receive Company Comments-Material Requisition for UPS System | Re-Issue for Approval-Material Requisition for UPS System | HE-EL-0920 | HE-EL-0930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.10 Cable Schedule | Re-Issue for Approval-Cable Sizing Calculation | Re-Issue for Approval-Cable Schedule | HE-EL-0450 | HE-EL-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | Receive Company Comments- Electrical Equipment Layout | Re-Issue for Approval- Electrical Equipment Layout | HE-EL-0500 | HE-EL-0510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | Receive Company Comments - Material Selection Diagram | Re-Issue for Approval - Material Selection Diagram | HE-CP-0020 | HE-CP-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.PM.4 NOC Register | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR-NOC Register | HE-PI-0320 | HC-GN-0250 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.PM.4 NOC Register | Issue ICR- Overall Plot Plan - 4" N2 Source Pipeline | Issue ICR-NOC Register | HE-PI-0460 | HC-GN-0250 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.PM.4 NOC Register | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | Issue ICR-NOC Register | HE-PI-0390 | HC-GN-0250 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.2 Planning Package | P2543-R01-Oct24..1.PM.2 Planning Package | Re-Issue for Approval-Planning Package | Obtain Company Approval-Planning Package | HC-GN-0030 | HC-GN-0040 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.17.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.17.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of Leak Detection System | Packaging & Final Inspection - Leak Detection System | HM-ME-0230 | HM-ME-0240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Junction Boxes (Lot 1) | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | HM-ME-1680 | HM-ME-1690 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.16.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Junction Boxes | Testing and Inspection of Junction Boxes | HM-ME-1630 | HM-ME-1640 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.1.3 Delivery & receipt at Site | Ready for Dispatch of Distribution Transformer | Transportation/ Custom Clearance/ Delivery at site of Distribution Transformer | HM-ME-0960 | HM-ME-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | P2543-R01-Oct24..PR.26.1.1.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Material Requisition for Distribution Transformer | Manufacturing & Assembly of Distribution Transformer | HE-EL-1070 | HM-ME-0930 | FF | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Fire Fighting & Safety Equipment (Lot 1) | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 1) | HM-ME-1980 | HM-ME-1990 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.13.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of Fire Fighting & Safety Equipment | Packaging & Final Inspection-Fire Fighting & Safety Equipment | HM-ME-1940 | HM-ME-1950 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.19.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of FOC Cables | Testing and Inspection of FOC Cables | HM-EL-0120 | HM-EL-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.19.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.19.2 Manufacturing & Ready for Dispatch | Vendor Document Review of FOC Cables | Manufacturing & Assembly of FOC Cables | HM-EL-0110 | HM-EL-0120 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.19.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.19.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-FOC Cables | Ready for Dispatch of FOC Cables | HM-EL-0140 | HM-EL-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.1.14.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - IDS & PIDS System | Vendor Document Review of Access Switch, Fiber Optic Patch Panel and Media Converter | ML1339-C18 | HM-ME-1320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | P2543-R01-Oct24..PR.26.LL.5.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Material Requisition for Active/ Passive Shelters | Manufacturing & Assembly of Active/ Passive Cooled Shelter | HE-EL-0890 | HM-ME-1130 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.LL.6.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.6.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Solar PV system | Manufacturing & Assembly of Solar PV system | HM-ME-1020 | HM-ME-1030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.LL.8.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.8.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of AC UPS | Factory Acceptance Test of AC UPS | HM-ME-0730 | HM-ME-0740 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.9.1.18 Material Requisition for UPS System | P2543-R01-Oct24..PR.26.LL.8.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Material Requisition for UPS System | Manufacturing & Assembly of AC UPS | HE-EL-0950 | HM-ME-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.10.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.10.2 Manufacturing & Ready for Dispatch | Testing and Inspection of ROV/ GOV | Packaging & Final Inspection-ROV/ GOV | HM-ME-0530 | HM-ME-0540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - Pig Launcher & Receiver | Vendor Document Review of Pig Launchers & Receivers | ML1279-C05 | HM-ME-0410 | FF | Completed | Completed | 0
P2543-R01-Oct24..PR.26.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.1.3.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of HVAC Equipment | Receipt at site and inspection of HVAC Equipment | HM-ME-1780 | HM-ME-1790 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of Pressure Reduction Skid | Packaging & Final Inspection - Pressure Reduction Skid | HM-ME-0130 | HM-ME-0140 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.21.3 Delivery & receipt at Site | Ready for Dispatch of Pressure Reduction Skid | Transportation/ Custom Clearance/ Delivery at site of Pressure Reduction Skid | HM-ME-0150 | HM-ME-0170 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.22.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.22.3 Delivery & receipt at Site | Ready for Dispatch of Custody Metering Skid | Transportation/ Custom Clearance/ Delivery at site of Custody Metering Skid | HM-ME-0050 | HM-ME-0070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.22.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.22.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Custody Metering Skid | Receipt at site and inspection of Custody Metering Skid | HM-ME-0070 | HM-ME-0080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.22.1 Ordering | P2543-R01-Oct24..PR.26.LL.22.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Custody Metering Skid | Vendor Document Review of Custody Metering Skid | HP-ME-0030 | HM-ME-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.26.LL.18.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - F & G System | Vendor Document Review of Gas Detectors | ML1269-C12 | HM-ME-1420 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.11.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.11.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Filter Package | Receipt at site and inspection of Filter Package | HM-ME-0370 | HM-ME-0380 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Filter Package | Manufacturing & Assembly of Filter Package | HM-ME-0310 | HM-ME-0320 | SS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Material Requisitions for Sales Gas CRS Filters | Manufacturing & Assembly of Filter Package | HE-ME-0170 | HM-ME-0320 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.1.BK.5.1 Ordering | P2543-R01-Oct24..PR.BK.5.2 Manufacturing & Ready for Dispatch | Final Structural Bulk material MTO | Final Structural Bulk material MTO | HP-BK-0310 | HM-CS-0090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.11.1 Ordering | P2543-R01-Oct24..PR.BK.11.2 Manufacturing & Ready for Dispatch | Final Civil Bulk material MTO | Final Civil Bulk material MTO | HP-BK-0270 | HM-CS-0020 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | Testing and Inspection of Power & Control Cables | Packaging & Final Inspection-Power & Control Cables | HM-EL-0030 | HM-EL-0040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.17.1 Ordering | P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Power & Control Cables | Vendor Document Review of Power & Control Cables | HP-BK-0030 | HM-EL-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.2.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.2.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Pigging & Split Tee | Ready for Dispatch of Pigging & Split Tee | HM-PL-0800 | HM-PL-0810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.1.2.1 Ordering | P2543-R01-Oct24..PR.1.2.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Pigging & Split Tee | Ready for Dispatch of Pigging & Split Tee | HP-ME-1290 | HM-PL-0810 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.3.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Isolating Joints | Testing and Inspection of Isolating Joints | HM-PL-0680 | HM-PL-0690 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | Ready for Dispatch of Hot Incution Bend | Transportation/ Custom Clearance/ Delivery at site of Hot Incution Bend | HM-PL-0600 | HM-PL-0620 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..1.1.1.1.1 Ordering | P2543-R01-Oct24..PR.1.1.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Hot Induction Bend | Ready for Dispatch of Hot Incution Bend | HP-ME-1190 | HM-PL-0600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.1.19.1 Ordering | P2543-R01-Oct24..PR.1.19.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Pig Signaler | Vendor Document Review of Pig Signaler | HP-ME-1140 | HM-PL-0460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.13.11 Cathodic Protection Work | P2543-R01-Oct24..PR.26.LL.20.2 Manufacturing & Ready for Dispatch | Place LOA/FOA - Cathodic Protection Work | Vendor Document Review of CP System | HS-GN-0530 | HM-PL-0350 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.1.24.1 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.24.1 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Hot Tapping Material | Testing and Inspection of Hot Tapping Material | HM-PL-0260 | HM-PL-0270 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.24.1 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.24.1 Manufacturing & Ready for Dispatch | Vendor Document Review of Hot Tapping Material | Manufacturing & Assembly of Hot Tapping Material | HM-PL-0250 | HM-PL-0260 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.1.1.5 Hot Tapping | P2543-R01-Oct24..PR.1.24.1 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO- Hot Tapping | Vendor Document Review of Hot Tapping Material | HS-GN-0230 | HM-PL-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | Issue Purchase Order (Final) - Hot Bends | Vendor Document Review of Ball/ Globe/ Check/ Plug Valves | ML1229-C02 | HM-PL-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..ML.4 Commissioning and PAC | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | Achieve (PAC-1) for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | CCM-PM4510 | ML2039-F05 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..ML.4 Commissioning and PAC | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | Commission New pipelines system - 4" Water line | CCM-PM4510 | ML2029-F04 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of ROV/ GOV (1st Lot) | Receive at Site - E&I Equipment's (RTUs) | HM-ME-0580 | ML1469-D13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Receive at Site - Hot Bends for 52" Pipeline (100% to total Qty) | HM-PL-0640 | ML1459-D12 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.LL.9.1 Ordering | P2543-R01-Oct24..ML.PR Procurement | Commercial Clarifications & Placement of PO for MOV | Issue Purchase Order (Final) - MOV/ROV/GOV Valves | HP-ME-0330 | ML1022-C07 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-0350 | ML1035-B26 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | HE-CS-0470 | ML1035-B26 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Civil UG layout | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | HE-CS-0530 | ML1034-B25 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | HE-TL-0470 | ML1033-B22 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Electrical Equipment Layout | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | HE-EL-0530 | ML1014-B10 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue for Approval- HAZOP reviews Report for all areas | Complete HAZOP/ SIL/ LOPA Review as applicable and Submit final Report after incorporating Company comments (IFA) | HE-HS-0690 | ML1013-B07 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue for Approval-HAZID/ ENVID/ OHID Report | Complete HAZOP/ SIL/ LOPA Review as applicable and Submit final Report after incorporating Company comments (IFA) | HE-HS-0570 | ML1013-B07 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.33 Filter Foundation GA and Details | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-FILTER FOUNDATION GA AND DETAILS | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-0950 | ML1209-B27 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Gas metering skid foundation drawings | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-0830 | ML1209-B27 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | HE-CS-0470 | ML1209-B27 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Pipeline Station approach drawing - 56" | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | HE-PL-2610 | ML1059-B28 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..ML.GE General | Final Issue for Design/ Construction-Overall Pipeline Route Map - 52" | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | HE-PL-0230 | ML1149-A07 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | P2543-R01-Oct24..ML.GE General | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | Issue cleaning & gauging, hydrotesting , Drying, Purging, Pre-commissioning and commissioning Procedure (Final Issue) | C-COM-790 | ML1004-A04 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.PM.2 Planning Package | P2543-R01-Oct24..ML.GE General | Final Issue for Design/ Construction-Planning Package | Issue Project Control, PMS and Planning Dossier covering Baseline Schedule, Histograms, S-Curves, etc. - Final Issue | HC-GN-0050 | ML1002-A02 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..ML Milestones | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | Achieve PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | CCM-PM4510 | ML1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.2 Final Documentation | P2543-R01-Oct24..ML Milestones | Vendor Documents Package | Project Finish | CAB-5310 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Hydrotesting - 4" Water line | Project Finish | ML1889-E34 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete E&I Installation Works - Sweihan CRS | Project Finish | ML1859-E31 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Pipeline welding - 52" Sales Gas Pipeline - 100% Welding | Project Finish | ML1719-E17 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Receive at Site - Manual Valves | Project Finish | ML1539-D21 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Drying & Purging of all facilities including Pipeline & Block Valve Stations - 52" Sales Gas Pipeline | Project Finish | ML1829-E28 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Receive at Site - Cathodic Protection (CP) System | Project Finish | ML1549-D22 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -HGCP to BVS-3 | Project Finish | ML1659-E11 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Achieve PAC-2 for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | Project Finish | ML1050 | ML1060 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Achieve Mechanical Completion of PL & facilities- ( 4" Water line) | Project Finish | ML1939-E39 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML Milestones | Receive at Site - UPS System | Project Finish | ML1499-D18 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Instrumentation & Control | Close-out report | CAB-4460 | CAB-5320 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Electrical | Close-out report | CAB-4450 | CAB-5320 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Issue cleaning & gauging, hydrotesting , Drying, Purging, Pre-commissioning and commissioning Procedure (Final Issue) | General | ML1004-A04 | CAB-5290 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | Vendor Documents Package | HM-ME-1390 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Civil & Structural | Quality Dossier | CAB-4420 | CAB-5300 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..1.PM.2 Planning Package | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Final Issue for Design/ Construction-Planning Package | Quality Dossier | HC-GN-0050 | CAB-5300 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Process | Quality Dossier | CAB-4400 | CAB-5300 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 52" Pipeline(IFC) | Pipeline | ML1009-B04 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.10.25 TBE for Isolating Joints | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Isolating Joints | Pipeline | HE-PL-2250 | CAB-4480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Pipeline | HE-PL-2910 | CAB-4480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Pipeline | HE-PL-2550 | CAB-4480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 56" Pipeline(IFC) | Pipeline | ML1008-B03 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue MR (Final) - Hot Bends | Pipeline | ML1189-B16 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Addendum to DGs | Instrumentation & Control | HE-IC-0050 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Data sheet for PRS (Pressure Reduction System) | Instrumentation & Control | HE-IC-1250 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.5 TBE for ROV/ GOV | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for ROV/ GOV | Instrumentation & Control | HE-IC-2330 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Instrument 3rd MTO | Instrumentation & Control | HE-IC-2630 | CAB-4460 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Instrumentation & Control | ML1015-B08 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.3 TBE for Field Instruments / H2S Analyzers | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Field Instruments / H2S Analyzers | Instrumentation & Control | HE-IC-2450 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- I/O list -Update | Instrumentation & Control | HE-IC-0550 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Datasheets for PSV & Orifice (incl. RO) | Instrumentation & Control | HE-IC-1370 | CAB-4460 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue MRs for All E&I Equipment & Packages (Final Issue) | Instrumentation & Control | ML1027-B17 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Instrumentation & Control | ML1179-B11 | CAB-4460 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Cable Sizing Calculation | Electrical | HE-EL-0470 | CAB-4450 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Electrical Adequacy Check Report | Electrical | HE-EL-0170 | CAB-4450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Electrical Installation Drawings | Electrical | HE-EL-1790 | CAB-4450 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | Piping | ML1030 | CAB-4440 | FF | Not Started | Not Started | 12
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Piping | ML1014-B10 | CAB-4440 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping | ML1219-B19 | CAB-4440 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.17 Typical details of protection slab to protect existing UG pipe at road crossing | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Typical details of protection slab to protect existing UG pipe at road crossing | Civil & Structural | HE-CS-0410 | CAB-4420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | Civil & Structural | ML1035-B26 | CAB-4420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Civil & Structural | HE-CS-1190 | CAB-4420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Standard drawings for Anchor bolt | Civil & Structural | HE-CS-0110 | CAB-4420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | Civil & Structural | ML1030 | CAB-4420 | FF | Not Started | Not Started | 6
P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction - Pressure Reduction Skid and Leak Detection Drawings | Civil & Structural | HE-CS-0770 | CAB-4420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.21 HAZOP close out report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-HAZOP close out report | HSE | HE-HS-0770 | CAB-4410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.16 Datasheets for fire fighting and safety equipment | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Datasheets for fire fighting and safety equipment | HSE | HE-HS-0470 | CAB-4410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-F&G Cause and effect | HSE | HE-HS-0350 | CAB-4410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Process | ML1219-B19 | CAB-4400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..4.4.AB As-Built & Final Documentation | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | Demolitionbilization | CCM-PM4520 | A3980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Complete HSEIA, QRA, and Gas Dispersion Studies after review / approval by Company and Submit Final Reports | Issue ICR-Pre-commissioning and Commissioning Plan | ML1016-B12 | C-COM-800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Issue ICR-Pre-commissioning and Commissioning Plan | HE-PR-0890 | C-COM-800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | Obtain Company Approval-Shutdown Requirements & Plan | Final Issue for Design/ Construction-Shutdown Requirements & Plan | C-COM-880 | C-COM-890 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | Issue ICR-Shutdown Requirements & Plan | Receive Company Comments-Shutdown Requirements & Plan | C-COM-850 | C-COM-860 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Issue ICR-Instrument index -Update | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-IC-0490 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Obtain Company Approval-Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | C-COM-780 | C-COM-790 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Issue Tie-in Philosophy for all new facilities - IFC | Re-Issue for Approval-Construction Procedures / Method Statements / ITPs | ML1010-B14 | C-COM-770 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Issue ICR-Construction Procedures / Method Statements / ITPs | Receive Company Comments-Construction Procedures / Method Statements / ITPs | C-COM-750 | C-COM-760 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.7.10 3D Model | Re-Issue for HAZOP Studies- P&ID's review | 30% Model Review | HE-PR-0130 | HE-PI-0130 | FS | Completed | Completed | 10
P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..1.EN.7.10 3D Model | Vendor Document Review of Pig Launchers & Receivers | 90% Model Review | HM-ME-0410 | HE-PI-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Final Issue for Design/ Construction- H&MB Report | Final Issue for Design / Construction-P&ID's | HE-PR-1220 | HE-PR-0160 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | Re-Issue for Approval- Process Simulations Report | Re-Issue after incorporating Review Comments- H&MB Report | HE-PR-0630 | HE-PR-1200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction- H&MB Report | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | HE-PR-1220 | ML1014-B10 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Final Issue for Design/ Construction- H&MB Report | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | HE-PR-1220 | HE-PI-0580 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Issue ICR- H&MB Report | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | HE-PR-1240 | HE-PI-0390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.10 Equipment List | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue for Approval - Equipment List | HE-PR-1200 | HE-PR-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | Obtain Company Approval- H&MB Report | Final Issue for Design/ Construction- H&MB Report | HE-PR-1210 | HE-PR-1220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Final Issue for Design/ Construction- H&MB Report | Final Issue for Design/ Construction-Overall Plot Plan- 4" N2 Source Pipeline | HE-PR-1220 | HE-PI-0510 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue after incorporating HAZOP /Review Comments - 52" Pipeline SWEIHAN CRS | HE-PR-1200 | HE-PI-0420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | Issue ICR- HAZOP reviews Report for all areas | Re-Issue after incorporating Review Comments- H&MB Report | HE-HS-0670 | HE-PR-1200 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue after incorporating HAZOP /Review Comments - 4" N2 Source Pipeline | HE-PR-1200 | HE-PI-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Issue ICR- H&MB Report | Issue ICR- Overall Plot Plan - 4" N2 Source Pipeline | HE-PR-1240 | HE-PI-0460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue after HAZOP /Review Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-1200 | HE-PI-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR- H&MB Report | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-1240 | HE-PI-0320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.PM.12 Workshops | Receive Company Comments- H&MB Report | HAZID /ENVID/OHID/ PHSER Workshop | HE-PR-1250 | HE-WS-0020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Issue ICR- H&MB Report | Issue ICR- Plot plan - BVS | HE-PR-1240 | HE-PI-0530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | Issue ICR-Design Basis | Issue ICR- H&MB Report | HE-DB-0010 | HE-PR-1240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | Final Issue for Design/ Construction-Process Simulations Report | Final Issue for Design/ Construction- H&MB Report | HE-PR-0650 | HE-PR-1220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction- H&MB Report | Final Issue for Design/ Construction-Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-1220 | HE-PI-0370 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Issue ICR- H&MB Report | Issue ICR- P&ID's | HE-PR-1240 | HE-PR-0110 | FS | Completed | Completed | 8
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | Issue ICR- H&MB Report | Receive Company Comments- H&MB Report | HE-PR-1240 | HE-PR-1250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue after incorporating HAZOP / Review Comments- Plot plan - BVS | HE-PR-1200 | HE-PI-0560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Final Issue for Design/ Construction- H&MB Report | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | HE-PR-1220 | HE-PI-0440 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | HE-PR-1200 | HE-PR-0140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | Re-Issue after incorporating Review Comments- H&MB Report | Obtain Company Approval- H&MB Report | HE-PR-1200 | HE-PR-1210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.1 Design Basis | P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | Final Issue for Design/ Construction- Mechanical Design Basis | Final Issue for Design/ Construction-Datasheet for Sales Gas CRS Filters | HE-ME-260 | HE-ME-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.1 Design Basis | P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | Final Issue for Design/ Construction- Mechanical Design Basis | Final Issue for Design/ Construction-Material Requisitions for Sales Gas CRS Filters | HE-ME-260 | HE-ME-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.1 Design Basis | P2543-R01-Oct24..1.EN.5.1 Design Basis | Obtain Company Approval- Mechanical Design Basis | Final Issue for Design/ Construction- Mechanical Design Basis | HE-ME-250 | HE-ME-260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.1 Design Basis | P2543-R01-Oct24..1.EN.5.1 Design Basis | Re-Issue for Approval- Mechanical Design Basis | Obtain Company Approval- Mechanical Design Basis | HE-ME-240 | HE-ME-250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.1 Design Basis | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction- Mechanical Design Basis | Mechanical | HE-ME-260 | CAB-4430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.5.1 Design Basis | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Final Issue for Design/ Construction- Mechanical Design Basis | Final Issue for Design/ Construction-Process Datasheets - Filters (At Sweihan CRS) | HE-ME-260 | HE-PR-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.1 Design Basis | P2543-R01-Oct24..1.1.2.25.3.1 Ordering | Issue ICR- Mechanical Design Basis | RFQ, Receipt of Bid for HVAC Equipment | HE-ME-270 | HP-ME-0860 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.1 Design Basis | P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | Issue ICR- Mechanical Design Basis | Issue ICR-Datasheet for Sales Gas CRS Filters | HE-ME-270 | HE-ME-0070 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.1 Design Basis | P2543-R01-Oct24..1.EN.5.1 Design Basis | Issue ICR- Mechanical Design Basis | Receive Company Comments- Mechanical Design Basis | HE-ME-270 | HE-ME-230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.1 Design Basis | P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | Issue ICR- Mechanical Design Basis | Issue ICR-Material Requisitions for Sales Gas CRS Filters | HE-ME-270 | HE-ME-0130 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.1 Design Basis | P2543-R01-Oct24..1.EN.5.1 Design Basis | Receive Company Comments- Mechanical Design Basis | Re-Issue for Approval- Mechanical Design Basis | HE-ME-230 | HE-ME-240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | P2543-R01-Oct24..1.EN.3.10 Equipment List | Final Issue for Design/ Construction-Process Datasheets | Final Issue for Design/ Construction-Equipment List | HE-PR-1300 | HE-PR-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Pressure Reduction Skid | HE-PR-1300 | HM-ME-0120 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | Receive Company Comments- Process Datasheets | Re-Issue for Approval- Process Datasheets | HE-PR-1270 | HE-PR-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Process Datasheets | Process | HE-PR-1300 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | Re-Issue for Approval- Process Datasheets | Obtain Company Approval- Process Datasheets | HE-PR-1280 | HE-PR-1290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Re-Issue for Approval- Process Datasheets | HE-PR-0140 | HE-PR-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Pig Launchers & Receivers | HE-PR-1300 | HM-ME-0420 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Filter Package | HE-PR-1300 | HM-ME-0320 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | Obtain Company Approval- Process Datasheets | Final Issue for Design/ Construction-Process Datasheets | HE-PR-1290 | HE-PR-1300 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | Issue ICR- Process Datasheets | Receive Company Comments- Process Datasheets | HE-PR-1260 | HE-PR-1270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | P2543-R01-Oct24..1.EN.3.10 Equipment List | Final Issue for Design/ Construction-Process Datasheets | Final Issue for Design/ Construction-Equipment List | HE-PR-1350 | HE-PR-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Pressure Reduction Skid | HE-PR-1350 | HM-ME-0120 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | Receive Company Comments- Process Datasheets | Re-Issue for Approval- Process Datasheets | HE-PR-1320 | HE-PR-1330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Process Datasheets | Process | HE-PR-1350 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | Re-Issue for Approval- Process Datasheets | Obtain Company Approval- Process Datasheets | HE-PR-1330 | HE-PR-1340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Re-Issue for Approval- Process Datasheets | HE-PR-0140 | HE-PR-1330 | FS | Completed | Completed | 20
P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Pig Launchers & Receivers | HE-PR-1350 | HM-ME-0420 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Filter Package | HE-PR-1350 | HM-ME-0320 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | Obtain Company Approval- Process Datasheets | Final Issue for Design/ Construction-Process Datasheets | HE-PR-1340 | HE-PR-1350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | Issue ICR- Process Datasheets | Receive Company Comments- Process Datasheets | HE-PR-1310 | HE-PR-1320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | P2543-R01-Oct24..1.EN.3.10 Equipment List | Final Issue for Design/ Construction-Process Datasheets | Final Issue for Design/ Construction-Equipment List | HE-PR-1400 | HE-PR-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Pressure Reduction Skid | HE-PR-1400 | HM-ME-0120 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | Receive Company Comments- Process Datasheets | Re-Issue for Approval- Process Datasheets | HE-PR-1370 | HE-PR-1380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Process Datasheets | Process | HE-PR-1400 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | Re-Issue for Approval- Process Datasheets | Obtain Company Approval- Process Datasheets | HE-PR-1380 | HE-PR-1390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Re-Issue for Approval- Process Datasheets | HE-PR-0140 | HE-PR-1380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Pig Launchers & Receivers | HE-PR-1400 | HM-ME-0420 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Filter Package | HE-PR-1400 | HM-ME-0320 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | Obtain Company Approval- Process Datasheets | Final Issue for Design/ Construction-Process Datasheets | HE-PR-1390 | HE-PR-1400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | Issue ICR- Process Datasheets | Receive Company Comments- Process Datasheets | HE-PR-1360 | HE-PR-1370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | P2543-R01-Oct24..1.EN.3.10 Equipment List | Final Issue for Design/ Construction-Process Datasheets | Final Issue for Design/ Construction-Equipment List | HE-PR-1450 | HE-PR-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Pressure Reduction Skid | HE-PR-1450 | HM-ME-0120 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | Receive Company Comments- Process Datasheets | Re-Issue for Approval- Process Datasheets | HE-PR-1420 | HE-PR-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Process Datasheets | Process | HE-PR-1450 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | Re-Issue for Approval- Process Datasheets | Obtain Company Approval- Process Datasheets | HE-PR-1430 | HE-PR-1440 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Re-Issue for Approval- Process Datasheets | HE-PR-0140 | HE-PR-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Pig Launchers & Receivers | HE-PR-1450 | HM-ME-0420 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Filter Package | HE-PR-1450 | HM-ME-0320 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | Obtain Company Approval- Process Datasheets | Final Issue for Design/ Construction-Process Datasheets | HE-PR-1440 | HE-PR-1450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | Issue ICR- Process Datasheets | Receive Company Comments- Process Datasheets | HE-PR-1410 | HE-PR-1420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | P2543-R01-Oct24..1.EN.3.10 Equipment List | Final Issue for Design/ Construction-Process Datasheets | Final Issue for Design/ Construction-Equipment List | HE-PR-1500 | HE-PR-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Pressure Reduction Skid | HE-PR-1500 | HM-ME-0120 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | Receive Company Comments- Process Datasheets | Re-Issue for Approval- Process Datasheets | HE-PR-1470 | HE-PR-1480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Process Datasheets | Process | HE-PR-1500 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | Re-Issue for Approval- Process Datasheets | Obtain Company Approval- Process Datasheets | HE-PR-1480 | HE-PR-1490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Re-Issue for Approval- Process Datasheets | HE-PR-0140 | HE-PR-1480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Pig Launchers & Receivers | HE-PR-1500 | HM-ME-0420 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Filter Package | HE-PR-1500 | HM-ME-0320 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | Obtain Company Approval- Process Datasheets | Final Issue for Design/ Construction-Process Datasheets | HE-PR-1490 | HE-PR-1500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | Issue ICR- Process Datasheets | Receive Company Comments- Process Datasheets | HE-PR-1460 | HE-PR-1470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | P2543-R01-Oct24..1.EN.3.10 Equipment List | Final Issue for Design/ Construction-Process Datasheets | Final Issue for Design/ Construction-Equipment List | HE-PR-1550 | HE-PR-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Pressure Reduction Skid | HE-PR-1550 | HM-ME-0120 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | Receive Company Comments- Process Datasheets | Re-Issue for Approval- Process Datasheets | HE-PR-1520 | HE-PR-1530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Process Datasheets | Process | HE-PR-1550 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | Re-Issue for Approval- Process Datasheets | Obtain Company Approval- Process Datasheets | HE-PR-1530 | HE-PR-1540 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Re-Issue for Approval- Process Datasheets | HE-PR-0140 | HE-PR-1530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Pig Launchers & Receivers | HE-PR-1550 | HM-ME-0420 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Filter Package | HE-PR-1550 | HM-ME-0320 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | Obtain Company Approval- Process Datasheets | Final Issue for Design/ Construction-Process Datasheets | HE-PR-1540 | HE-PR-1550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | Issue ICR- Process Datasheets | Receive Company Comments- Process Datasheets | HE-PR-1510 | HE-PR-1520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | P2543-R01-Oct24..1.EN.3.10 Equipment List | Final Issue for Design/ Construction-Process Datasheets | Final Issue for Design/ Construction-Equipment List | HE-PR-1600 | HE-PR-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | P2543-R01-Oct24..PR.26.LL.21.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Pressure Reduction Skid | HE-PR-1600 | HM-ME-0120 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | Receive Company Comments- Process Datasheets | Re-Issue for Approval- Process Datasheets | HE-PR-1570 | HE-PR-1580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Process Datasheets | Process | HE-PR-1600 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | Re-Issue for Approval- Process Datasheets | Obtain Company Approval- Process Datasheets | HE-PR-1580 | HE-PR-1590 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Re-Issue for Approval- Process Datasheets | HE-PR-0140 | HE-PR-1580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Pig Launchers & Receivers | HE-PR-1600 | HM-ME-0420 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets | Manufacturing & Assembly of Filter Package | HE-PR-1600 | HM-ME-0320 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | Obtain Company Approval- Process Datasheets | Final Issue for Design/ Construction-Process Datasheets | HE-PR-1590 | HE-PR-1600 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | Issue ICR- Process Datasheets | Receive Company Comments- Process Datasheets | HE-PR-1560 | HE-PR-1570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.56 Pipeline Design Basis | P2543-R01-Oct24..1.EN.1.56 Pipeline Design Basis | Re-Issue for Approval-Design Basis | Obtain Company Approval-Design Basis | HE-DB-50 | HE-DB-70 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.56 Pipeline Design Basis | P2543-R01-Oct24..1.EN.1.56 Pipeline Design Basis | Receive Company Comments-Design Basis | Re-Issue for Approval-Design Basis | HE-DB-90 | HE-DB-50 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.56 Pipeline Design Basis | P2543-R01-Oct24..1.EN.1.56 Pipeline Design Basis | Issue ICR- Pipeline Design Basis | Receive Company Comments-Design Basis | HE-DB-80 | HE-DB-90 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.56 Pipeline Design Basis | P2543-R01-Oct24..1.EN.1.56 Pipeline Design Basis | Obtain Company Approval-Design Basis | Final Issue for Design/ Construction-Design Basis | HE-DB-70 | HE-DB-60 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.58 Pipeline Tie In List | P2543-R01-Oct24..1.EN.1.58 Pipeline Tie In List | Re-Issue for Approval - Pipeline Tie In List | Obtain Company Approval - Pipeline Tie In List | HE-PL-3350 | HE-PL-3360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.58 Pipeline Tie In List | P2543-R01-Oct24..1.EN.1.58 Pipeline Tie In List | Receive Company Comments - Pipeline Tie In List | Re-Issue for Approval - Pipeline Tie In List | HE-PL-3340 | HE-PL-3350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.58 Pipeline Tie In List | P2543-R01-Oct24..1.EN.1.58 Pipeline Tie In List | Obtain Company Approval - Pipeline Tie In List | Final Issue for Design/ Construction-Pipeline Tie In List | HE-PL-3360 | HE-PL-3370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.58 Pipeline Tie In List | P2543-R01-Oct24..1.EN.1.58 Pipeline Tie In List | Issue ICR - Pipeline Tie In List | Receive Company Comments - Pipeline Tie In List | HE-PL-3330 | HE-PL-3340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.56 Piping Design Basis | P2543-R01-Oct24..1.EN.7.56 Piping Design Basis | Re-Issue for Approval-Design Basis | Obtain Company Approval-Design Basis | HE-DB-100 | HE-DB-120 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.56 Piping Design Basis | P2543-R01-Oct24..1.EN.7.56 Piping Design Basis | Receive Company Comments-Design Basis | Re-Issue for Approval-Design Basis | HE-DB-140 | HE-DB-100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.56 Piping Design Basis | P2543-R01-Oct24..1.EN.7.56 Piping Design Basis | Issue ICR-Design Basis | Receive Company Comments-Design Basis | HE-DB-130 | HE-DB-140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.56 Piping Design Basis | P2543-R01-Oct24..1.EN.7.56 Piping Design Basis | Obtain Company Approval-Design Basis | Final Issue for Design/ Construction-Design Basis | HE-DB-120 | HE-DB-110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.15 Datasheet for Piping Special Items | P2543-R01-Oct24..1.EN.7.4.15 Datasheet for Piping Special Items | Receive Company Comments- Datasheet for Piping Special Items | Re-Issue for Approval- Datasheet for Piping Special Items | HE-PI-1330 | HE-PI-1340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.15 Datasheet for Piping Special Items | P2543-R01-Oct24..1.EN.7.4.15 Datasheet for Piping Special Items | Obtain Company Approval- Datasheet for Piping Special Items | Final Issue for Design/ Construction-Datasheet for Piping Special Items | HE-PI-1350 | HE-PI-1310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.15 Datasheet for Piping Special Items | P2543-R01-Oct24..1.EN.7.4.15 Datasheet for Piping Special Items | Issue ICR- Datasheet for Piping Special Items | Receive Company Comments- Datasheet for Piping Special Items | HE-PI-1320 | HE-PI-1330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.15 Datasheet for Piping Special Items | P2543-R01-Oct24..1.EN.7.4.15 Datasheet for Piping Special Items | Re-Issue for Approval- Datasheet for Piping Special Items | Obtain Company Approval- Datasheet for Piping Special Items | HE-PI-1340 | HE-PI-1350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.2.17 TBE for Piping Bulks (Pipe, Flange, etc) | P2543-R01-Oct24..1.EN.7.2.17 TBE for Piping Bulks (Pipe, Flange, etc) | Obtain Company Approval- TBE for Piping Bulks (Pipe, Flange, etc) | Final Issue for Design/ Construction-TBE for Piping Bulks (Pipe, Flange, etc) | HE-PI-1390 | HE-PI-1400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.2.17 TBE for Piping Bulks (Pipe, Flange, etc) | P2543-R01-Oct24..1.EN.7.2.17 TBE for Piping Bulks (Pipe, Flange, etc) | Issue ICR- TBE for Piping Bulks (Pipe, Flange, etc) | Receive Company Comments- TBE for Piping Bulks (Pipe, Flange, etc) | HE-PI-1360 | HE-PI-1370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.2.17 TBE for Piping Bulks (Pipe, Flange, etc) | P2543-R01-Oct24..1.EN.7.2.17 TBE for Piping Bulks (Pipe, Flange, etc) | Re-Issue for Approval- TBE for Piping Bulks (Pipe, Flange, etc) | Obtain Company Approval- TBE for Piping Bulks (Pipe, Flange, etc) | HE-PI-1380 | HE-PI-1390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.2.17 TBE for Piping Bulks (Pipe, Flange, etc) | P2543-R01-Oct24..1.EN.7.2.17 TBE for Piping Bulks (Pipe, Flange, etc) | Receive Company Comments- TBE for Piping Bulks (Pipe, Flange, etc) | Re-Issue for Approval- TBE for Piping Bulks (Pipe, Flange, etc) | HE-PI-1370 | HE-PI-1380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.2.20 TBE for Piping Special Items | P2543-R01-Oct24..1.EN.7.2.20 TBE for Piping Special Items | Obtain Company Approval- TBE for Piping Special Items | Final Issue for Design/ Construction-TBE for Piping Special Items | HE-PI-1440 | HE-PI-1450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.2.20 TBE for Piping Special Items | P2543-R01-Oct24..1.EN.7.2.20 TBE for Piping Special Items | Issue ICR- TBE for Piping Special Items | Receive Company Comments- TBE for Piping Special Items | HE-PI-1410 | HE-PI-1420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.2.20 TBE for Piping Special Items | P2543-R01-Oct24..1.EN.7.2.20 TBE for Piping Special Items | Re-Issue for Approval- TBE for Piping Special Items | Obtain Company Approval- TBE for Piping Special Items | HE-PI-1430 | HE-PI-1440 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.2.20 TBE for Piping Special Items | P2543-R01-Oct24..1.EN.7.2.20 TBE for Piping Special Items | Receive Company Comments- TBE for Piping Special Items | Re-Issue for Approval- TBE for Piping Special Items | HE-PI-1420 | HE-PI-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.21 Piping Specifications - Addendum to DGS | P2543-R01-Oct24..1.EN.7.21 Piping Specifications - Addendum to DGS | Issue ICR - Piping Specifications - Addendum to DGS | Receive Company Comments - Piping Specifications - Addendum to DGS | HE-PI-3440 | HE-PI-3450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.21 Piping Specifications - Addendum to DGS | P2543-R01-Oct24..1.EN.7.21 Piping Specifications - Addendum to DGS | Re-Issue for Approval - Piping Specifications - Addendum to DGS | Obtain Company Approval - Piping Specifications - Addendum to DGS | HE-PI-3460 | HE-PI-3470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.21 Piping Specifications - Addendum to DGS | P2543-R01-Oct24..1.EN.7.21 Piping Specifications - Addendum to DGS | Receive Company Comments - Piping Specifications - Addendum to DGS | Re-Issue for Approval - Piping Specifications - Addendum to DGS | HE-PI-3450 | HE-PI-3460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.21 Piping Specifications - Addendum to DGS | P2543-R01-Oct24..1.EN.7.21 Piping Specifications - Addendum to DGS | Obtain Company Approval - Piping Specifications - Addendum to DGS | Final Issue for Design/ Construction-Piping Specifications - Addendum to DGS | HE-PI-3470 | HE-PI-3430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | Re-Issue for Approval-Piping Tie In Schedule | Obtain Company Approval-Piping Tie In Schedule | HE-PI-3500 | HE-PI-3510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | Receive Company Comments-Piping Tie In Schedule | Re-Issue for Approval-Piping Tie In Schedule | HE-PI-3490 | HE-PI-3500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | Issue ICR-Piping Tie In Schedule | Receive Company Comments-Piping Tie In Schedule | HE-PI-3480 | HE-PI-3490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | Obtain Company Approval-Piping Tie In Schedule | Final Issue for Design/ Construction-Piping Tie In Schedule | HE-PI-3510 | HE-PI-3520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.1 Datasheet for PIG RECEIVER (839-V-101) 52" | P2543-R01-Oct24..1.EN.5.2.1 Datasheet for PIG RECEIVER (839-V-101) 52" | Receive Company Comments-Datasheet for PIG RECEIVER (839-V-101) | Re-Issue for Approval-Datasheet for PIG RECEIVER (839-V-101) | HE-ME-320 | HE-ME-280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.1 Datasheet for PIG RECEIVER (839-V-101) 52" | P2543-R01-Oct24..1.EN.5.2.1 Datasheet for PIG RECEIVER (839-V-101) 52" | Issue ICR-Datasheet for PIG RECEIVER (839-V-101) | Receive Company Comments-Datasheet for PIG RECEIVER (839-V-101) | HE-ME-310 | HE-ME-320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.1 Datasheet for PIG RECEIVER (839-V-101) 52" | P2543-R01-Oct24..1.EN.5.2.1 Datasheet for PIG RECEIVER (839-V-101) 52" | Re-Issue for Approval-Datasheet for PIG RECEIVER (839-V-101) | Obtain Company Approval-Datasheet for PIG RECEIVER (839-V-101) | HE-ME-280 | HE-ME-290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.1 Datasheet for PIG RECEIVER (839-V-101) 52" | P2543-R01-Oct24..1.EN.5.2.1 Datasheet for PIG RECEIVER (839-V-101) 52" | Obtain Company Approval-Datasheet for PIG RECEIVER (839-V-101) | Final Issue for Design/ Construction-Datasheet for PIG RECEIVER (839-V-101) | HE-ME-290 | HE-ME-300 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.2 Datasheet for PIG LAUNCHER (838-V-602) 52" | P2543-R01-Oct24..1.EN.5.2.2 Datasheet for PIG LAUNCHER (838-V-602) 52" | Receive Company Comments-Datasheet for PIG LAUNCHER (838-V-602) | Re-Issue for Approval-Datasheet for PIG LAUNCHER (838-V-602) | HE-ME-370 | HE-ME-330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.2 Datasheet for PIG LAUNCHER (838-V-602) 52" | P2543-R01-Oct24..1.EN.5.2.2 Datasheet for PIG LAUNCHER (838-V-602) 52" | Issue ICR-Datasheet for PIG LAUNCHER (838-V-602) | Receive Company Comments-Datasheet for PIG LAUNCHER (838-V-602) | HE-ME-360 | HE-ME-370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.2 Datasheet for PIG LAUNCHER (838-V-602) 52" | P2543-R01-Oct24..1.EN.5.2.2 Datasheet for PIG LAUNCHER (838-V-602) 52" | Re-Issue for Approval-Datasheet for PIG LAUNCHER (838-V-602) | Obtain Company Approval-Datasheet for PIG LAUNCHER (838-V-602) | HE-ME-330 | HE-ME-340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.2 Datasheet for PIG LAUNCHER (838-V-602) 52" | P2543-R01-Oct24..1.EN.5.2.2 Datasheet for PIG LAUNCHER (838-V-602) 52" | Obtain Company Approval-Datasheet for PIG LAUNCHER (838-V-602) | Final Issue for Design/ Construction-Datasheet for PIG LAUNCHER (838-V-602) | HE-ME-340 | HE-ME-350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.3 Datasheet for PIG RECEIVER (838-V-601) 56" | P2543-R01-Oct24..1.EN.5.2.3 Datasheet for PIG RECEIVER (838-V-601) 56" | Receive Company Comments-Datasheet for PIG RECEIVER (838-V-601) | Re-Issue for Approval-Datasheet for PIG RECEIVER (838-V-601) | HE-ME-420 | HE-ME-380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.3 Datasheet for PIG RECEIVER (838-V-601) 56" | P2543-R01-Oct24..1.EN.5.2.3 Datasheet for PIG RECEIVER (838-V-601) 56" | Issue ICR-Datasheet for PIG RECEIVER (838-V-601) | Receive Company Comments-Datasheet for PIG RECEIVER (838-V-601) | HE-ME-410 | HE-ME-420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.3 Datasheet for PIG RECEIVER (838-V-601) 56" | P2543-R01-Oct24..1.EN.5.2.3 Datasheet for PIG RECEIVER (838-V-601) 56" | Re-Issue for Approval-Datasheet for PIG RECEIVER (838-V-601) | Obtain Company Approval-Datasheet for PIG RECEIVER (838-V-601) | HE-ME-380 | HE-ME-390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.3 Datasheet for PIG RECEIVER (838-V-601) 56" | P2543-R01-Oct24..1.EN.5.2.3 Datasheet for PIG RECEIVER (838-V-601) 56" | Obtain Company Approval-Datasheet for PIG RECEIVER (838-V-601) | Final Issue for Design/ Construction-Datasheet for PIG RECEIVER (838-V-601) | HE-ME-390 | HE-ME-400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.4 Datasheet for PIG LAUNCHER (607-V-603) 56" | P2543-R01-Oct24..1.EN.5.2.4 Datasheet for PIG LAUNCHER (607-V-603) 56" | Receive Company Comments-Datasheet for PIG LAUNCHER (607-V-603) | Re-Issue for Approval-Datasheet for PIG LAUNCHER (607-V-603) | HE-ME-470 | HE-ME-430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.4 Datasheet for PIG LAUNCHER (607-V-603) 56" | P2543-R01-Oct24..1.EN.5.2.4 Datasheet for PIG LAUNCHER (607-V-603) 56" | Issue ICR-Datasheet for PIG LAUNCHER (607-V-603) | Receive Company Comments-Datasheet for PIG LAUNCHER (607-V-603) | HE-ME-460 | HE-ME-470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.4 Datasheet for PIG LAUNCHER (607-V-603) 56" | P2543-R01-Oct24..1.EN.5.2.4 Datasheet for PIG LAUNCHER (607-V-603) 56" | Re-Issue for Approval-Datasheet for PIG LAUNCHER (607-V-603) | Obtain Company Approval-Datasheet for PIG LAUNCHER (607-V-603) | HE-ME-430 | HE-ME-440 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.4 Datasheet for PIG LAUNCHER (607-V-603) 56" | P2543-R01-Oct24..1.EN.5.2.4 Datasheet for PIG LAUNCHER (607-V-603) 56" | Obtain Company Approval-Datasheet for PIG LAUNCHER (607-V-603) | Final Issue for Design/ Construction-Datasheet for PIG LAUNCHER (607-V-603) | HE-ME-440 | HE-ME-450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisitions for Pig Launcher/Receiver | Mechanical | HE-ME-520 | CAB-4430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | Final Issue for Design/ Construction- Addendum to DGS | Final Issue for Design/ Construction-Material Requisitions for Pig Launcher/Receiver | HE-ME-0050 | HE-ME-520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | Re-Issue for Approval-Material Requisitions for Pig Launcher/Receiver | Obtain Company Approval-Material Requisitions for Pig Launcher/Receiver | HE-ME-500 | HE-ME-510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | Re-Issue for Approval-Datasheet for Sales Gas CRS Filters | Re-Issue for Approval-Material Requisitions for Pig Launcher/Receiver | HE-ME-0090 | HE-ME-500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | Issue ICR-Datasheet for Sales Gas CRS Filters | Issue ICR-Material Requisitions for Pig Launcher/Receiver | HE-ME-0070 | HE-ME-480 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | Obtain Company Approval-Material Requisitions for Pig Launcher/Receiver | Final Issue for Design/ Construction-Material Requisitions for Pig Launcher/Receiver | HE-ME-510 | HE-ME-520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Material Requisitions for Pig Launcher/Receiver | Issue MRs for All Mechanical Equipment & Packages (Final Issue) | HE-ME-520 | ML1017-B18 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | Receive Company Comments-Material Requisitions for Pig Launcher/Receiver | Re-Issue for Approval-Material Requisitions for Pig Launcher/Receiver | HE-ME-490 | HE-ME-500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | Issue ICR-Material Requisitions for Pig Launcher/Receiver | Receive Company Comments-Material Requisitions for Pig Launcher/Receiver | HE-ME-480 | HE-ME-490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | Issue ICR- Addendum to DGS | Issue ICR-Material Requisitions for Pig Launcher/Receiver | HE-ME-0010 | HE-ME-480 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | P2543-R01-Oct24..PR.26.LL.11.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Material Requisitions for Pig Launcher/Receiver | Manufacturing & Assembly of Filter Package | HE-ME-520 | HM-ME-0320 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.5.1 Design Basis | P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | Final Issue for Design/ Construction- Mechanical Design Basis | Final Issue for Design/ Construction-Material Requisitions for Pig Launcher/Receiver | HE-ME-260 | HE-ME-520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.1 Design Basis | P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | Issue ICR- Mechanical Design Basis | Issue ICR-Material Requisitions for Pig Launcher/Receiver | HE-ME-270 | HE-ME-480 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.11.1 Ordering | P2543-R01-Oct24..1.EN.5.3.3 TBE for Pig Launcher/Receiver | RFQ, Receipt of Bid for Filter Package | Issue ICR-TBEs for Pig Launcher/Receiver | HP-ME-0160 | HE-ME-530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.3.3 TBE for Pig Launcher/Receiver | P2543-R01-Oct24..1.EN.5.3.3 TBE for Pig Launcher/Receiver | Issue ICR-TBEs for Pig Launcher/Receiver | Receive Company Comments-TBEs for Pig Launcher/Receiver | HE-ME-530 | HE-ME-540 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.3.3 TBE for Pig Launcher/Receiver | P2543-R01-Oct24..1.EN.5.3.3 TBE for Pig Launcher/Receiver | Re-Issue for Approval-TBEs for Pig Launcher/Receiver | Obtain Company Approval-TBEs for Pig Launcher/Receiver | HE-ME-550 | HE-ME-560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.3.3 TBE for Pig Launcher/Receiver | P2543-R01-Oct24..1.EN.5.3.3 TBE for Pig Launcher/Receiver | Receive Company Comments-TBEs for Pig Launcher/Receiver | Re-Issue for Approval-TBEs for Pig Launcher/Receiver | HE-ME-540 | HE-ME-550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.3.3 TBE for Pig Launcher/Receiver | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBEs for Pig Launcher/Receiver | Mechanical | HE-ME-570 | CAB-4430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.5.3.3 TBE for Pig Launcher/Receiver | P2543-R01-Oct24..1.EN.5.3.3 TBE for Pig Launcher/Receiver | Obtain Company Approval-TBEs for Pig Launcher/Receiver | Final Issue for Design/ Construction-TBEs for Pig Launcher/Receiver | HE-ME-560 | HE-ME-570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | Re-Issue for Approval-Design Basis | Obtain Company Approval-Design Basis | HE-EL-150 | HE-EL-170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | Receive Company Comments-Design Basis | Re-Issue for Approval-Design Basis | HE-EL-190 | HE-EL-150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | Issue ICR-Design Basis | Receive Company Comments-Design Basis | HE-EL-180 | HE-EL-190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | Obtain Company Approval-Design Basis | Final Issue for Design/ Construction-Design Basis | HE-EL-170 | HE-EL-160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Data Sheet for HV cables | Electrical | HE-EL-1950 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | Re-Issue for Approval-Data Sheet for HV cables | Obtain Company Approval-Data Sheet for HV cables | HE-EL-1930 | HE-EL-1940 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | Issue ICR- Datasheet for AC UPS | Receive Company Comments- Datasheet for AC UPS | HE-EL-1870 | HE-EL-1880 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | Receive Company Comments- Datasheet for AC UPS | Re-Issue for Approval- Datasheet for AC UPS | HE-EL-1880 | HE-EL-1890 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Data Sheet for AC UPS | Electrical | HE-EL-1860 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | Issue ICR-Data Sheet for HV cables | Issue ICR-Material Requisition for Power & Control Cables | HE-EL-1910 | HE-EL-1150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | Issue ICR- Datasheet for AC UPS | Issue ICR-Material Requisition for Solar Panels | HE-EL-1870 | HE-EL-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | Re-Issue for Approval- Datasheet for AC UPS | Issue ICR-Material Requisition for Solar Panels | HE-EL-1890 | HE-EL-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | Obtain Company Approval- Datasheet for AC UPS | Final Issue for Design/ Construction-Data Sheet for AC UPS | HE-EL-1900 | HE-EL-1860 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | Obtain Company Approval-Data Sheet for HV cables | Final Issue for Design/ Construction-Data Sheet for HV cables | HE-EL-1940 | HE-EL-1950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | Issue ICR-Data Sheet for HV cables | Receive Company Comments-Data Sheet for HV cables | HE-EL-1910 | HE-EL-1920 | FS | Completed | Completed | 15
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | Re-Issue for Approval- Datasheet for AC UPS | Obtain Company Approval- Datasheet for AC UPS | HE-EL-1890 | HE-EL-1900 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | Receive Company Comments-Data Sheet for HV cables | Re-Issue for Approval-Data Sheet for HV cables | HE-EL-1920 | HE-EL-1930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | Re-Issue for Approval- Datasheet for AC UPS | Re-Issue for Approval-Material Requisition for Solar Panels | HE-EL-1890 | HE-EL-1110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | Receive Company Comments-Material Requisition for LV Switchgear | Re-Issue for Approval-Material Requisition for LV Switchgear | HE-EL-1970 | HE-EL-1980 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | Re-Issue for Approval-Cable Sizing Calculation | Re-Issue for Approval-Material Requisition for LV Switchgear | HE-EL-0450 | HE-EL-1980 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | Issue ICR-Data Sheet for LV cables | Issue ICR-Material Requisition for LV Switchgear | HE-EL-0790 | HE-EL-1960 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | Final Issue for Design/ Construction-Cable Sizing Calculation | Final Issue for Design/ Construction-Material Requisition for LV Switchgear | HE-EL-0470 | HE-EL-2000 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | Obtain Company Approval-Material Requisition for LV Switchgear | Final Issue for Design/ Construction-Material Requisition for LV Switchgear | HE-EL-1990 | HE-EL-2000 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | Issue ICR-Cable Sizing Calculation | Issue ICR-Material Requisition for LV Switchgear | HE-EL-0430 | HE-EL-1960 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Material Requisition for LV Switchgear | Manufacturing & Assembly of Power & Control Cables | HE-EL-2000 | HM-EL-0020 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | Re-Issue for Approval-Material Requisition for LV Switchgear | Obtain Company Approval-Material Requisition for LV Switchgear | HE-EL-1980 | HE-EL-1990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | Issue ICR-Material Requisition for LV Switchgear | Receive Company Comments-Material Requisition for LV Switchgear | HE-EL-1960 | HE-EL-1970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisition for LV Switchgear | Electrical | HE-EL-2000 | CAB-4450 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | Issue ICR-Data Sheet for HV cables | Issue ICR-Material Requisition for LV Switchgear | HE-EL-1910 | HE-EL-1960 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | Receive Company Comments-Material Requisition for Glanding & Termination | Re-Issue for Approval-Material Requisition for Glanding & Termination | HE-EL-2020 | HE-EL-2030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | Re-Issue for Approval-Cable Sizing Calculation | Re-Issue for Approval-Material Requisition for Glanding & Termination | HE-EL-0450 | HE-EL-2030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | Issue ICR-Data Sheet for LV cables | Issue ICR-Material Requisition for Glanding & Termination | HE-EL-0790 | HE-EL-2010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | Obtain Company Approval-Material Requisition for Glanding & Termination | Final Issue for Design/ Construction-Material Requisition for Glanding & Termination | HE-EL-2040 | HE-EL-2050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | Issue ICR-Cable Sizing Calculation | Issue ICR-Material Requisition for Glanding & Termination | HE-EL-0430 | HE-EL-2010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Material Requisition for Glanding & Termination | Manufacturing & Assembly of Power & Control Cables | HE-EL-2050 | HM-EL-0020 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | Re-Issue for Approval-Material Requisition for Glanding & Termination | Obtain Company Approval-Material Requisition for Glanding & Termination | HE-EL-2030 | HE-EL-2040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | Issue ICR-Material Requisition for Glanding & Termination | Receive Company Comments-Material Requisition for Glanding & Termination | HE-EL-2010 | HE-EL-2020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisition for Glanding & Termination | Electrical | HE-EL-2050 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | Issue ICR-Data Sheet for HV cables | Issue ICR-Material Requisition for Glanding & Termination | HE-EL-1910 | HE-EL-2010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | Final Issue for Design/ Construction-Data Sheet for HV cables | Final Issue for Design/ Construction-Material Requisition for Glanding & Termination | HE-EL-1950 | HE-EL-2050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | Receive Company Comments-Material Requisition for MOV Isolator | Re-Issue for Approval-Material Requisition for MOV Isolator | HE-EL-2070 | HE-EL-2080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | Re-Issue for Approval-Cable Sizing Calculation | Re-Issue for Approval-Material Requisition for MOV Isolator | HE-EL-0450 | HE-EL-2080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | Issue ICR-Data Sheet for LV cables | Issue ICR-Material Requisition for MOV Isolator | HE-EL-0790 | HE-EL-2060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | Obtain Company Approval-Material Requisition for MOV Isolator | Final Issue for Design/ Construction-Material Requisition for MOV Isolator | HE-EL-2090 | HE-EL-2100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | Issue ICR-Cable Sizing Calculation | Issue ICR-Material Requisition for MOV Isolator | HE-EL-0430 | HE-EL-2060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Material Requisition for MOV Isolator | Manufacturing & Assembly of Power & Control Cables | HE-EL-2100 | HM-EL-0020 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | Re-Issue for Approval-Material Requisition for MOV Isolator | Obtain Company Approval-Material Requisition for MOV Isolator | HE-EL-2080 | HE-EL-2090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | Issue ICR-Material Requisition for MOV Isolator | Receive Company Comments-Material Requisition for MOV Isolator | HE-EL-2060 | HE-EL-2070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisition for MOV Isolator | Electrical | HE-EL-2100 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | Issue ICR-Data Sheet for HV cables | Issue ICR-Material Requisition for MOV Isolator | HE-EL-1910 | HE-EL-2060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | Final Issue for Design/ Construction-Data Sheet for HV cables | Final Issue for Design/ Construction-Material Requisition for MOV Isolator | HE-EL-1950 | HE-EL-2100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | Receive Company Comments-Material Requisition for Electrical Bulks | Re-Issue for Approval-Material Requisition for Electrical Bulks | HE-EL-2120 | HE-EL-2130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | Re-Issue for Approval-Cable Sizing Calculation | Re-Issue for Approval-Material Requisition for Electrical Bulks | HE-EL-0450 | HE-EL-2130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | Issue ICR-Data Sheet for LV cables | Issue ICR-Material Requisition for Electrical Bulks | HE-EL-0790 | HE-EL-2110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | Obtain Company Approval-Material Requisition for Electrical Bulks | Final Issue for Design/ Construction-Material Requisition for Electrical Bulks | HE-EL-2140 | HE-EL-2150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | Issue ICR-Cable Sizing Calculation | Issue ICR-Material Requisition for Electrical Bulks | HE-EL-0430 | HE-EL-2110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Material Requisition for Electrical Bulks | Manufacturing & Assembly of Power & Control Cables | HE-EL-2150 | HM-EL-0020 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | Re-Issue for Approval-Material Requisition for Electrical Bulks | Obtain Company Approval-Material Requisition for Electrical Bulks | HE-EL-2130 | HE-EL-2140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | Issue ICR-Material Requisition for Electrical Bulks | Receive Company Comments-Material Requisition for Electrical Bulks | HE-EL-2110 | HE-EL-2120 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisition for Electrical Bulks | Electrical | HE-EL-2150 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | Issue ICR-Data Sheet for HV cables | Issue ICR-Material Requisition for Electrical Bulks | HE-EL-1910 | HE-EL-2110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | Final Issue for Design/ Construction-Data Sheet for HV cables | Final Issue for Design/ Construction-Material Requisition for Electrical Bulks | HE-EL-1950 | HE-EL-2150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.5 Material Requisition for Modification Works | P2543-R01-Oct24..1.EN.9.1.5 Material Requisition for Modification Works | Receive Company Comments-Material Requisition for Modification Works | Re-Issue for Approval-Material Requisition for Modification Works | HE-EL-2170 | HE-EL-2180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.1.5 Material Requisition for Modification Works | Re-Issue for Approval-Cable Sizing Calculation | Re-Issue for Approval-Material Requisition for Modification Works | HE-EL-0450 | HE-EL-2180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..1.EN.9.1.5 Material Requisition for Modification Works | Issue ICR-Data Sheet for LV cables | Issue ICR-Material Requisition for Modification Works | HE-EL-0790 | HE-EL-2160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.5 Material Requisition for Modification Works | P2543-R01-Oct24..1.EN.9.1.5 Material Requisition for Modification Works | Obtain Company Approval-Material Requisition for Modification Works | Final Issue for Design/ Construction-Material Requisition for Modification Works | HE-EL-2190 | HE-EL-2200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..1.EN.9.1.5 Material Requisition for Modification Works | Issue ICR-Cable Sizing Calculation | Issue ICR-Material Requisition for Modification Works | HE-EL-0430 | HE-EL-2160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.5 Material Requisition for Modification Works | P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Material Requisition for Modification Works | Manufacturing & Assembly of Power & Control Cables | HE-EL-2200 | HM-EL-0020 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.9.1.5 Material Requisition for Modification Works | P2543-R01-Oct24..1.EN.9.1.5 Material Requisition for Modification Works | Re-Issue for Approval-Material Requisition for Modification Works | Obtain Company Approval-Material Requisition for Modification Works | HE-EL-2180 | HE-EL-2190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.5 Material Requisition for Modification Works | P2543-R01-Oct24..1.EN.9.1.5 Material Requisition for Modification Works | Issue ICR-Material Requisition for Modification Works | Receive Company Comments-Material Requisition for Modification Works | HE-EL-2160 | HE-EL-2170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.5 Material Requisition for Modification Works | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Material Requisition for Modification Works | Electrical | HE-EL-2200 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..1.EN.9.1.5 Material Requisition for Modification Works | Issue ICR-Data Sheet for HV cables | Issue ICR-Material Requisition for Modification Works | HE-EL-1910 | HE-EL-2160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..1.EN.9.1.5 Material Requisition for Modification Works | Final Issue for Design/ Construction-Data Sheet for HV cables | Final Issue for Design/ Construction-Material Requisition for Modification Works | HE-EL-1950 | HE-EL-2200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.1 TBE for LV Switchgear | P2543-R01-Oct24..1.EN.9.6.1 TBE for LV Switchgear | Receive Company Comments-TBE for LV Switchgear | Re-Issue for Approval-TBE for LV Switchgear | HE-EL-2220 | HE-EL-2230 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.1 TBE for LV Switchgear | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for LV Switchgear | Electrical | HE-EL-2250 | CAB-4450 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.1 TBE for LV Switchgear | P2543-R01-Oct24..1.EN.9.6.1 TBE for LV Switchgear | Re-Issue for Approval-TBE for LV Switchgear | Obtain Company Approval-TBE for LV Switchgear | HE-EL-2230 | HE-EL-2240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.1 TBE for LV Switchgear | P2543-R01-Oct24..1.EN.9.6.1 TBE for LV Switchgear | Obtain Company Approval-TBE for LV Switchgear | Final Issue for Design/ Construction-TBE for LV Switchgear | HE-EL-2240 | HE-EL-2250 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.1 TBE for LV Switchgear | P2543-R01-Oct24..1.EN.9.6.1 TBE for LV Switchgear | Issue ICR-TBE for LV Switchgear | Receive Company Comments-TBE for LV Switchgear | HE-EL-2210 | HE-EL-2220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.2 TBE for MOV Isolator | P2543-R01-Oct24..1.EN.9.6.2 TBE for MOV Isolator | Receive Company Comments-TBE for MOV Isolator | Re-Issue for Approval-TBE for MOV Isolator | HE-EL-2270 | HE-EL-2280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.2 TBE for MOV Isolator | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for MOV Isolator | Electrical | HE-EL-2300 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.2 TBE for MOV Isolator | P2543-R01-Oct24..1.EN.9.6.2 TBE for MOV Isolator | Re-Issue for Approval-TBE for MOV Isolator | Obtain Company Approval-TBE for MOV Isolator | HE-EL-2280 | HE-EL-2290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.2 TBE for MOV Isolator | P2543-R01-Oct24..1.EN.9.6.2 TBE for MOV Isolator | Obtain Company Approval-TBE for MOV Isolator | Final Issue for Design/ Construction-TBE for MOV Isolator | HE-EL-2290 | HE-EL-2300 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.17.1 Ordering | P2543-R01-Oct24..1.EN.9.6.2 TBE for MOV Isolator | RFQ, Receipt of Bid for Power & Control Cables | Issue ICR-TBE for MOV Isolator | HP-BK-0010 | HE-EL-2260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.2 TBE for MOV Isolator | P2543-R01-Oct24..1.EN.9.6.2 TBE for MOV Isolator | Issue ICR-TBE for MOV Isolator | Receive Company Comments-TBE for MOV Isolator | HE-EL-2260 | HE-EL-2270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.3 TBE for Modification Works | P2543-R01-Oct24..1.EN.9.6.3 TBE for Modification Works | Receive Company Comments-TBE for Modification Works | Re-Issue for Approval-TBE for Modification Works | HE-EL-2320 | HE-EL-2330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.3 TBE for Modification Works | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Modification Works | Electrical | HE-EL-2350 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.3 TBE for Modification Works | P2543-R01-Oct24..1.EN.9.6.3 TBE for Modification Works | Re-Issue for Approval-TBE for Modification Works | Obtain Company Approval-TBE for Modification Works | HE-EL-2330 | HE-EL-2340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.3 TBE for Modification Works | P2543-R01-Oct24..1.EN.9.6.3 TBE for Modification Works | Obtain Company Approval-TBE for Modification Works | Final Issue for Design/ Construction-TBE for Modification Works | HE-EL-2340 | HE-EL-2350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.17.1 Ordering | P2543-R01-Oct24..1.EN.9.6.3 TBE for Modification Works | RFQ, Receipt of Bid for Power & Control Cables | Issue ICR-TBE for Modification Works | HP-BK-0010 | HE-EL-2310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.3 TBE for Modification Works | P2543-R01-Oct24..1.EN.9.6.3 TBE for Modification Works | Issue ICR-TBE for Modification Works | Receive Company Comments-TBE for Modification Works | HE-EL-2310 | HE-EL-2320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.5 TBE for Cable Glanding & Termination | P2543-R01-Oct24..1.EN.9.6.5 TBE for Cable Glanding & Termination | Receive Company Comments-TBE for Glanding & Termination | Re-Issue for Approval-TBE for Glanding & Termination | HE-EL-2370 | HE-EL-2380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.5 TBE for Cable Glanding & Termination | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Glanding & Termination | Electrical | HE-EL-2400 | CAB-4450 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.5 TBE for Cable Glanding & Termination | P2543-R01-Oct24..1.EN.9.6.5 TBE for Cable Glanding & Termination | Re-Issue for Approval-TBE for Glanding & Termination | Obtain Company Approval-TBE for Glanding & Termination | HE-EL-2380 | HE-EL-2390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.5 TBE for Cable Glanding & Termination | P2543-R01-Oct24..1.EN.9.6.5 TBE for Cable Glanding & Termination | Obtain Company Approval-TBE for Glanding & Termination | Final Issue for Design/ Construction-TBE for Glanding & Termination | HE-EL-2390 | HE-EL-2400 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.1.BK.17.1 Ordering | P2543-R01-Oct24..1.EN.9.6.5 TBE for Cable Glanding & Termination | RFQ, Receipt of Bid for Power & Control Cables | Issue ICR-TBE for Glanding & Termination | HP-BK-0010 | HE-EL-2360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.5 TBE for Cable Glanding & Termination | P2543-R01-Oct24..1.EN.9.6.5 TBE for Cable Glanding & Termination | Issue ICR-TBE for Glanding & Termination | Receive Company Comments-TBE for Glanding & Termination | HE-EL-2360 | HE-EL-2370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.4 TBE for Electrical Bulks (JBs, Fixtures, Sockets etc) | P2543-R01-Oct24..1.EN.9.6.4 TBE for Electrical Bulks (JBs, Fixtures, Sockets etc) | Receive Company Comments-TBE for Electrical Bulks | Re-Issue for Approval-TBE for Electrical Bulks | HE-EL-2420 | HE-EL-2430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.4 TBE for Electrical Bulks (JBs, Fixtures, Sockets etc) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-TBE for Electrical Bulks | Electrical | HE-EL-2450 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.4 TBE for Electrical Bulks (JBs, Fixtures, Sockets etc) | P2543-R01-Oct24..1.EN.9.6.4 TBE for Electrical Bulks (JBs, Fixtures, Sockets etc) | Re-Issue for Approval-TBE for Electrical Bulks | Obtain Company Approval-TBE for Electrical Bulks | HE-EL-2430 | HE-EL-2440 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.4 TBE for Electrical Bulks (JBs, Fixtures, Sockets etc) | P2543-R01-Oct24..1.EN.9.6.4 TBE for Electrical Bulks (JBs, Fixtures, Sockets etc) | Obtain Company Approval-TBE for Electrical Bulks | Final Issue for Design/ Construction-TBE for Electrical Bulks | HE-EL-2440 | HE-EL-2450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.17.1 Ordering | P2543-R01-Oct24..1.EN.9.6.4 TBE for Electrical Bulks (JBs, Fixtures, Sockets etc) | RFQ, Receipt of Bid for Power & Control Cables | Issue ICR-TBE for Electrical Bulks | HP-BK-0010 | HE-EL-2410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.4 TBE for Electrical Bulks (JBs, Fixtures, Sockets etc) | P2543-R01-Oct24..1.EN.9.6.4 TBE for Electrical Bulks (JBs, Fixtures, Sockets etc) | Issue ICR-TBE for Electrical Bulks | Receive Company Comments-TBE for Electrical Bulks | HE-EL-2410 | HE-EL-2420 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | Final Issue for Design/ Construction- I&C Design Basis | Final Issue for Design/ Construction-Datasheet for Sales Gas CRS Filters | HE-IC-610 | HE-ME-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | Final Issue for Design/ Construction- I&C Design Basis | Final Issue for Design/ Construction-Material Requisitions for Sales Gas CRS Filters | HE-IC-610 | HE-ME-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | Obtain Company Approval- I&C Design Basis | Final Issue for Design/ Construction- I&C Design Basis | HE-IC-600 | HE-IC-610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | Re-Issue for Approval- I&C Design Basis | Obtain Company Approval- I&C Design Basis | HE-IC-590 | HE-IC-600 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction- I&C Design Basis | Mechanical | HE-IC-610 | CAB-4430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Final Issue for Design/ Construction- I&C Design Basis | Final Issue for Design/ Construction-Process Datasheets - Filters (At Sweihan CRS) | HE-IC-610 | HE-PR-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.1.2.25.3.1 Ordering | Issue ICR- I&C Design Basis | RFQ, Receipt of Bid for HVAC Equipment | HE-IC-620 | HP-ME-0860 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | Issue ICR- I&C Design Basis | Issue ICR-Datasheet for Sales Gas CRS Filters | HE-IC-620 | HE-ME-0070 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | Issue ICR- I&C Design Basis | Receive Company Comments- I&C Design Basis | HE-IC-620 | HE-IC-580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.5.6.7 Material Requisitions Sals Gas CRS Filters | Issue ICR- I&C Design Basis | Issue ICR-Material Requisitions for Sales Gas CRS Filters | HE-IC-620 | HE-ME-0130 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | Receive Company Comments- I&C Design Basis | Re-Issue for Approval- I&C Design Basis | HE-IC-580 | HE-IC-590 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | Final Issue for Design/ Construction- I&C Design Basis | Final Issue for Design/ Construction-Material Requisitions for Pig Launcher/Receiver | HE-IC-610 | HE-ME-520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | Issue ICR- I&C Design Basis | Issue ICR-Material Requisitions for Pig Launcher/Receiver | HE-IC-620 | HE-ME-480 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | Re-Issue for Approval-Design Basis | Obtain Company Approval-Design Basis | HE-TL-2460 | HE-TL-2480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | Receive Company Comments-Design Basis | Re-Issue for Approval-Design Basis | HE-TL-2500 | HE-TL-2460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | Issue ICR-Design Basis | Receive Company Comments-Design Basis | HE-TL-2490 | HE-TL-2500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | Obtain Company Approval-Design Basis | Final Issue for Design/ Construction-Design Basis | HE-TL-2480 | HE-TL-2470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | Final Issue for Design/ Construction-Telecom cable schedule | Final Issue for Design/ Construction-Telecom Typical Hookup | HE-TL-0830 | HE-TL-930 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | Re-Issue for Approval- Telecom Cable Schedule | Re-Issue for Approval-Telecom Typical Hookup | HE-TL-0810 | HE-TL-910 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Telecom Typical Hookup | Telecom | HE-TL-930 | CAB-4470 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | Final Issue for Design/ Construction-Telecom Equipment Layout | Final Issue for Design/ Construction-Telecom Typical Hookup | HE-TL-0770 | HE-TL-930 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | Re-Issue for Approval-Telecom Equipment Layout | Re-Issue for Approval-Telecom Typical Hookup | HE-TL-0750 | HE-TL-910 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | Obtain Company Approval-Telecom Typical Hookup | Final Issue for Design/ Construction-Telecom Typical Hookup | HE-TL-920 | HE-TL-930 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | Issue ICR-Telecom Typical Hookup | Receive Company Comments-Telecom Typical Hookup | HE-TL-890 | HE-TL-900 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | P2543-R01-Oct24..1.1.BK.9.1 Ordering | Final Issue for Design/ Construction-Telecom Typical Hookup | Final Telecom Bulk material MTO | HE-TL-930 | HP-BK-0510 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | Receive Company Comments-Telecom Typical Hookup | Re-Issue for Approval-Telecom Typical Hookup | HE-TL-900 | HE-TL-910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | Re-Issue for Approval-Telecom Location and Cable Routing layout | Re-Issue for Approval-Telecom Typical Hookup | HE-TL-0690 | HE-TL-910 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Final Issue for Design/ Construction-Telecom Typical Hookup | HE-TL-0710 | HE-TL-930 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | Re-Issue for Approval-Telecom Typical Hookup | Obtain Company Approval-Telecom Typical Hookup | HE-TL-910 | HE-TL-920 | FS | Completed | In Progress | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.3.3 Process Design Basis | Project Kick off Meeting | Issue ICR-Design Basis | ML1002 | HE-DB-0010 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.1.56 Pipeline Design Basis | Issue ICR-Design Basis | Issue ICR- Pipeline Design Basis | HE-DB-0010 | HE-DB-80 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | P2543-R01-Oct24..1.EN.1.58 Pipeline Tie In List | Issue ICR - Pipeline Station Approach drawing -56" | Issue ICR - Pipeline Tie In List | HE-PL-2570 | HE-PL-3330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.17 MR for Linepipes | P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | Issue ICR - MR for Line pipes | Issue ICR - Pipeline MTO - 56" | HE-PL-1630 | HE-PL-3230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.9 Data Sheet - Linepipes | P2543-R01-Oct24..1.EN.1.9.17 MR for Linepipes | Issue ICR - Data Sheet - Line pipes | Issue ICR - MR for Line pipes | HE-PL-1150 | HE-PL-1630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.1 MR for Anchor Flanges | P2543-R01-Oct24..1.EN.1.9.1 MR for Anchor Flanges | Obtain Company Approval - MR for Anchor Flanges | Final Issue for Design/ Construction-MR for Anchor Flanges | HE-PL-3440 | HE-PL-3450 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.9.1 MR for Anchor Flanges | P2543-R01-Oct24..1.EN.1.9.1 MR for Anchor Flanges | Receive Company Comments - MR for Anchor Flanges | Re-Issue for Approval - MR for Anchor Flanges | HE-PL-3470 | HE-PL-3430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.1 MR for Anchor Flanges | P2543-R01-Oct24..1.EN.1.9.1 MR for Anchor Flanges | Issue ICR - MR for Anchor Flanges | Receive Company Comments - MR for Anchor Flanges | HE-PL-3460 | HE-PL-3470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.1 MR for Anchor Flanges | P2543-R01-Oct24..1.EN.1.9.1 MR for Anchor Flanges | Re-Issue for Approval - MR for Anchor Flanges | Obtain Company Approval - MR for Anchor Flanges | HE-PL-3430 | HE-PL-3440 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.1 TBE for Anchor Flanges | P2543-R01-Oct24..1.EN.1.10.1 TBE for Anchor Flanges | Issue ICR - TBE for Anchor Flanges | Receive Company Comments - TBE for Anchor Flanges | HE-PL-3480 | HE-PL-3490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.1 TBE for Anchor Flanges | P2543-R01-Oct24..1.EN.1.10.1 TBE for Anchor Flanges | Receive Company Comments - TBE for Anchor Flanges | Re-Issue for Approval - TBE for Anchor Flanges | HE-PL-3490 | HE-PL-3500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.1 TBE for Anchor Flanges | P2543-R01-Oct24..1.EN.1.10.1 TBE for Anchor Flanges | Obtain Company Approval - TBE for Anchor Flanges | Final Issue for Design/ Construction-TBE for Anchor Flanges | HE-PL-3510 | HE-PL-3520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.10.1 TBE for Anchor Flanges | P2543-R01-Oct24..1.EN.1.10.1 TBE for Anchor Flanges | Re-Issue for Approval - TBE for Anchor Flanges | Obtain Company Approval - TBE for Anchor Flanges | HE-PL-3500 | HE-PL-3510 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.1.4.1 Ordering | P2543-R01-Oct24..1.1.1.4.1 Ordering | Prepare TBE and Company approval for Anchor Flanges | Commercial Clarifications & Placement of PO for Anchor Flanges | HP-ME-1320 | HP-ME-1300 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.4.1 Ordering | P2543-R01-Oct24..1.1.1.4.1 Ordering | RFQ, Receipt of Bid for Anchor Flanges | Prepare TBE and Company approval for Anchor Flanges | HP-ME-1310 | HP-ME-1320 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.4.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.4.2 Manufacturing & Ready for Dispatch | Testing and Inspection of Anchor Flanges | Packaging & Final Inspection-Anchor Flanges | HM-PL-930 | HM-PL-910 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.4.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.4.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Anchor Flanges | Manufacturing & Assembly of Anchor Flanges | HM-PL-890 | HM-PL-900 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.1.4.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.4.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Anchor Flanges | Testing and Inspection of Anchor Flanges | HM-PL-900 | HM-PL-930 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.4.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.4.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Anchor Flanges (Lot 1) | Receipt at site and inspection of Anchor Flanges (Lot 1) | HM-PL-950 | HM-PL-940 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.4.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.4.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Anchor Flanges | Ready for Dispatch of Anchor Flanges | HM-PL-910 | HM-PL-920 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.2.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.2.3 Delivery & Receipt at site | 1st Piping Special Items MTO | 1st Piping Special Items MTO | HM-PI-60 | HM-PI-80 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..PR.BK.2.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.2.3 Delivery & Receipt at site | Final Piping Special Items MTO | Final Piping Special Items MTO | HM-PI-50 | HM-PI-70 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.3.1 Ordering | P2543-R01-Oct24..1.1.BK.3.1 Ordering | RFQ, Receipt of Bid for Cable Gland & Termination | Prepare TBE and Company approval for Cable Gland & Termination | HP-BK-550 | HP-BK-540 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.3.1 Ordering | P2543-R01-Oct24..1.1.BK.3.1 Ordering | Prepare TBE and Company approval for Cable Gland & Termination | Commercial Clarifications & Placement of PO for Cable Gland & Termination | HP-BK-540 | HP-BK-530 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.BK.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.3.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of Cable Gland and Termination | Packaging & Final Inspection-Cable Gland and Termination | HM-EL-550 | HM-EL-560 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.3.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of Cable Gland and Termination | Factory Acceptance Test of Cable Gland and Termination | HM-EL-540 | HM-EL-550 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.3.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.3.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Cable Gland and Termination (Lot 1) | Receipt at site and inspection of Cable Gland and Termination (Lot 1) | HM-EL-590 | HM-EL-580 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.3.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Cable Gland and Termination | Manufacturing & Assembly of Cable Gland and Termination | HM-EL-530 | HM-EL-540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.3.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-Cable Gland and Termination | Ready for Dispatch of Cable Gland and Termination | HM-EL-560 | HM-EL-570 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.3.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.3.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Cable Gland and Termination (Lot 1) | Receipt at site and inspection of Cable Gland and Termination (Lot 1) | HM-EL-590 | HM-EL-580 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.7.56 Piping Design Basis | Issue ICR-Design Basis | Issue ICR-Design Basis | HE-DB-0010 | HE-DB-130 | FS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.7.56 Piping Design Basis | P2543-R01-Oct24..1.EN.7.21 Piping Specifications - Addendum to DGS | Issue ICR-Design Basis | Issue ICR - Piping Specifications - Addendum to DGS | HE-DB-130 | HE-PI-3440 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.21 Piping Specifications - Addendum to DGS | P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | Final Issue for Design/ Construction-Piping Specifications - Addendum to DGS | Issue ICR-Piping Tie In Schedule | HE-PI-3430 | HE-PI-3480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | Issue ICR-Design Basis | Issue ICR-Design Basis | HE-DB-0010 | HE-EL-180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | Issue ICR-Design Basis | Issue ICR- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | HE-DB-0010 | HE-PR-0310 | FS | Completed | Completed | 4
P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | Issue ICR- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | Issue ICR- Process Datasheets - PRS Skid (at Sweihan CRS) | HE-PR-0310 | HE-PR-0370 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Issue ICR-Design Basis | Issue ICR- Process Datasheets - Filters (At Sweihan CRS) | HE-DB-0010 | HE-PR-0430 | FS | Completed | Completed | 3
P2543-R01-Oct24..1.EN.1.9.1 MR for Anchor Flanges | P2543-R01-Oct24..1.EN.1.10.1 TBE for Anchor Flanges | Issue ICR - MR for Anchor Flanges | Issue ICR - TBE for Anchor Flanges | HE-PL-3460 | HE-PL-3480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.1 MR for Anchor Flanges | P2543-R01-Oct24..1.EN.1.10.1 TBE for Anchor Flanges | Final Issue for Design/ Construction-MR for Anchor Flanges | Final Issue for Design/ Construction-TBE for Anchor Flanges | HE-PL-3450 | HE-PL-3520 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.60.14 Data Sheet - Anchor Flange | P2543-R01-Oct24..1.EN.1.9.1 MR for Anchor Flanges | Issue ICR - Data Sheet - Anchor Flange (If Required) | Issue ICR - MR for Anchor Flanges | HE-PL-1510 | HE-PL-3460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.14 Data Sheet - Anchor Flange | P2543-R01-Oct24..1.EN.1.9.1 MR for Anchor Flanges | Final Issue for Design/ Construction-Data Sheet - Anchor Flange | Final Issue for Design/ Construction-MR for Anchor Flanges | HE-PL-1550 | HE-PL-3450 | FF | In Progress | In Progress | 10
P2543-R01-Oct24..1.EN.1.9.1 MR for Anchor Flanges | P2543-R01-Oct24..1.1.1.4.1 Ordering | Issue ICR - MR for Anchor Flanges | RFQ, Receipt of Bid for Anchor Flanges | HE-PL-3460 | HP-ME-1310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.1 TBE for Anchor Flanges | P2543-R01-Oct24..1.1.1.4.1 Ordering | Issue ICR - TBE for Anchor Flanges | Prepare TBE and Company approval for Anchor Flanges | HE-PL-3480 | HP-ME-1320 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | P2543-R01-Oct24..1.1.BK.3.1 Ordering | Issue ICR-Material Requisition for Glanding & Termination | RFQ, Receipt of Bid for Cable Gland & Termination | HE-EL-2010 | HP-BK-550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.3.1 Ordering | P2543-R01-Oct24..1.EN.9.6.5 TBE for Cable Glanding & Termination | RFQ, Receipt of Bid for Cable Gland & Termination | Issue ICR-TBE for Glanding & Termination | HP-BK-550 | HE-EL-2360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.6 Material Requisition for Piping Bulk | P2543-R01-Oct24..1.EN.7.8.6 Material Requisition for Piping Bulk | Re-Issue for Approval-MR for Piping Bulks | Obtain Company Approval-MR for Piping Bulks | HE-PI-3550 | HE-PI-3560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.6 Material Requisition for Piping Bulk | P2543-R01-Oct24..1.EN.7.8.6 Material Requisition for Piping Bulk | Issue ICR-MR for Piping Bulks | Receive Company Comments-MR for Piping Bulks | HE-PI-3530 | HE-PI-3540 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.6 Material Requisition for Piping Bulk | P2543-R01-Oct24..1.EN.7.8.6 Material Requisition for Piping Bulk | Obtain Company Approval-MR for Piping Bulks | Final Issue for Design/ Construction-Material Requisition for Piping Bulks & Special Items | HE-PI-3560 | HE-PI-3570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.6 Material Requisition for Piping Bulk | P2543-R01-Oct24..1.EN.7.8.6 Material Requisition for Piping Bulk | Receive Company Comments-MR for Piping Bulks | Re-Issue for Approval-MR for Piping Bulks | HE-PI-3540 | HE-PI-3550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.6 Material Requisition for Piping Bulk | P2543-R01-Oct24..1.EN.7.2.17 TBE for Piping Bulks (Pipe, Flange, etc) | Issue ICR-MR for Piping Bulks | Issue ICR- TBE for Piping Bulks (Pipe, Flange, etc) | HE-PI-3530 | HE-PI-1360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.6 Material Requisition for Piping Bulk | P2543-R01-Oct24..1.EN.7.2.17 TBE for Piping Bulks (Pipe, Flange, etc) | Final Issue for Design/ Construction-Material Requisition for Piping Bulks & Special Items | Final Issue for Design/ Construction-TBE for Piping Bulks (Pipe, Flange, etc) | HE-PI-3570 | HE-PI-1400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.6 Material Requisition for Piping Bulk | P2543-R01-Oct24..1.EN.7.2.20 TBE for Piping Special Items | Final Issue for Design/ Construction-Material Requisition for Piping Bulks & Special Items | Final Issue for Design/ Construction-TBE for Piping Special Items | HE-PI-3570 | HE-PI-1450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.3.1 Ordering | P2543-R01-Oct24..PR.BK.3.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Cable Gland & Termination | Vendor Document Review of Cable Gland and Termination | HP-BK-530 | HM-EL-530 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.2.1 Ordering | P2543-R01-Oct24..PR.BK.2.2 Manufacturing & Ready for Dispatch | 1st Piping Special Items MTO | 1st Piping Special Items MTO | HP-BK-520 | HM-PI-60 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.2.1 Ordering | P2543-R01-Oct24..PR.BK.2.2 Manufacturing & Ready for Dispatch | Final Piping Special Items MTO | Final Piping Special Items MTO | HP-BK-510 | HM-PI-50 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.2.1 Ordering | P2543-R01-Oct24..1.1.BK.2.1 Ordering | 1st Piping Special Items MTO | Final Piping Special Items MTO | HP-BK-520 | HP-BK-510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..1.1.BK.2.1 Ordering | Piping MTO - 1st | 1st Piping Special Items MTO | HE-PI-1260 | HP-BK-520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.4.1 Ordering | P2543-R01-Oct24..PR.1.4.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Anchor Flanges | Vendor Document Review of Anchor Flanges | HP-ME-1300 | HM-PL-890 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.15 Datasheet for Piping Special Items | P2543-R01-Oct24..1.EN.7.8.6 Material Requisition for Piping Bulk | Issue ICR- Datasheet for Piping Special Items | Issue ICR-MR for Piping Bulks | HE-PI-1320 | HE-PI-3530 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.BK.2.3 Delivery & Receipt at site | P2543-R01-Oct24..PR.BK.2.3 Delivery & Receipt at site | 1st Piping Special Items MTO | Final Piping Special Items MTO | HM-PI-80 | HM-PI-70 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..1.EN.1.56 Pipeline Design Basis | P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | Final Issue for Design/ Construction-Design Basis | Issue ICR - Pipeline Specifications - Addendum to DGS | HE-DB-60 | HE-PL-0070 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.56 Piping Design Basis | P2543-R01-Oct24..1.EN.7.21 Piping Specifications - Addendum to DGS | Final Issue for Design/ Construction-Design Basis | Issue ICR - Piping Specifications - Addendum to DGS | HE-DB-110 | HE-PI-3440 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.2.17 TBE for Piping Bulks (Pipe, Flange, etc) | P2543-R01-Oct24..1.1.BK.4.1 Ordering | Final Issue for Design/ Construction-TBE for Piping Bulks (Pipe, Flange, etc) | Final Piping Bulk material MTO | HE-PI-1400 | HP-BK-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | Final Issue for Design/ Construction-Piping Tie In Schedule | Final Issue for Design/ Construction-Piping Isometrics | HE-PI-3520 | HE-PI-1240 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.58 Pipeline Tie In List | P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | Final Issue for Design/ Construction-Pipeline Tie In List | Final Issue for Design/ Construction-Pipeline MTO - 56" and 52" | HE-PL-3370 | HE-PL-3270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | Issue ICR-Design Basis | Issue ICR- Process Datasheets - Pig Launcher / Receiver | HE-DB-0010 | HE-PR-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | Issue ICR- Process Datasheets | Issue ICR- Process Datasheets | HE-PR-1360 | HE-PR-1410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | Issue ICR- Process Datasheets | Issue ICR- Process Datasheets | HE-PR-1410 | HE-PR-1460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | Issue ICR- Process Datasheets | Issue ICR- Process Datasheets | HE-PR-1460 | HE-PR-1510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | Issue ICR-Design Basis | Issue ICR- Process Datasheets | HE-DB-0010 | HE-PR-0550 | FS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | Issue ICR-Design Basis | Issue ICR- Process Datasheets | HE-DB-0010 | HE-PR-1260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | Issue ICR- Process Datasheets | Issue ICR- Process Datasheets | HE-PR-1260 | HE-PR-1310 | FS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | Issue ICR- Operating and control philosophy, Safeguarding philosophy | Issue ICR - Relief, Vent and Blowdown Philosophy | HE-PR-0730 | HE-PR-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Receive Company Comments-P&ID's | Issues for Design Review | HE-PR-0120 | HE-PR-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Issues for Design Review | Receive comments from Design Review | HE-PR-0170 | HE-PR-0240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Receive comments from Design Review | Re-Issue for HAZOP Studies- P&ID's review | HE-PR-0240 | HE-PR-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.1.4 Pipeline Road and Railway Crossing Calculation Report | Issue ICR - Geo Technical Survey Report (Overall) | Issue ICR - Pipeline Road Crossing Calculation Report | HE-GS-0010 | HE-PL-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.4 Pipeline Road and Railway Crossing Calculation Report | Issue ICR-Topographical Survey Report (Overall) | Issue ICR - Pipeline Road Crossing Calculation Report | HE-TS-0010 | HE-PL-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.1.3 Pipeline Upheavl Calculation | Issue ICR-Topographical Survey Report (Overall) | Issue ICR - Pipeline Upheaval Calculation | HE-TS-0010 | HE-PL-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3 Geotechnical Survey Report | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR - Geo Technical Survey Report (Overall) | Re-Issue for HAZOP Studies- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-GS-0010 | HE-PI-0340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2 Topographical Survey Report | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR-Topographical Survey Report (Overall) | Re-Issue for HAZOP Studies- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-TS-0010 | HE-PI-0340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | P2543-R01-Oct24..1.EN.7.4.15 Datasheet for Piping Special Items | Issue ICR- Datasheet for Plug Valves | Issue ICR- Datasheet for Piping Special Items | HE-PI-0960 | HE-PI-1320 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.7.19 Piping MTO | 30% Model Review | Piping MTO - 1st | ML2059-B05 | HE-PI-1260 | FS | Completed | Completed | 10
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.7.19 Piping MTO | 60% Model Review | Piping MTO - 2nd | ML2069-B09 | HE-PI-1280 | FS | Completed | Completed | 10
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.7.19 Piping MTO | 90% Model Review | Piping MTO - Final | ML2079-B13 | HE-PI-1300 | FS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..1.EN.7.19 Piping MTO | Piping MTO - 1st | Piping MTO - 2nd | HE-PI-1260 | HE-PI-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..1.EN.7.19 Piping MTO | Piping MTO - 2nd | Piping MTO - Final | HE-PI-1280 | HE-PI-1300 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.5.1 Design Basis | Issue ICR-Design Basis | Issue ICR- Mechanical Design Basis | HE-DB-0010 | HE-ME-270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.1 Design Basis | P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | Issue ICR- Mechanical Design Basis | Issue ICR- Addendum to DGS | HE-ME-270 | HE-ME-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..1.EN.5.2.1 Datasheet for PIG RECEIVER (839-V-101) 52" | Issue ICR- Process Datasheets - Pig Launcher / Receiver | Issue ICR-Datasheet for PIG RECEIVER (839-V-101) | HE-PR-0490 | HE-ME-310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..1.EN.5.2.2 Datasheet for PIG LAUNCHER (838-V-602) 52" | Issue ICR- Process Datasheets - Pig Launcher / Receiver | Issue ICR-Datasheet for PIG LAUNCHER (838-V-602) | HE-PR-0490 | HE-ME-360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..1.EN.5.2.3 Datasheet for PIG RECEIVER (838-V-601) 56" | Issue ICR- Process Datasheets - Pig Launcher / Receiver | Issue ICR-Datasheet for PIG RECEIVER (838-V-601) | HE-PR-0490 | HE-ME-410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..1.EN.5.2.4 Datasheet for PIG LAUNCHER (607-V-603) 56" | Issue ICR- Process Datasheets - Pig Launcher / Receiver | Issue ICR-Datasheet for PIG LAUNCHER (607-V-603) | HE-PR-0490 | HE-ME-460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | Final Issue for Design/ Construction-Civil / Structural Design Basis | Final Issue for Design/ Construction-Standard drawings for Anchor bolt | HE-CS-1600 | HE-CS-0110 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | Issued for Review - Civil / Structural Design Basis | Issued for Review - Standard drawings for Anchor bolt | HE-CS-1560 | HE-CS-0070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | Final Issue for Design/ Construction-Civil / Structural Design Basis | Final Issue for Design/ Construction-Material Requisition for Active/ Passive Shelters | HE-CS-1600 | HE-EL-0890 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | Re-Issue for Approval - Civil / Structural Design Basis | Obtain Company Approval - Civil / Structural Design Basis | HE-CS-1580 | HE-CS-1590 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | Obtain Company Approval - Civil / Structural Design Basis | Final Issue for Design/ Construction-Civil / Structural Design Basis | HE-CS-1590 | HE-CS-1600 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | Obtain Company Approval - Civil / Structural Design Basis | Issue ICR - Material Requisition for Active / Passive Shelters | HE-CS-1590 | HE-EL-0850 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Civil / Structural Design Basis | Civil & Structural | HE-CS-1600 | CAB-4420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | Final Issue for Design/ Construction-Civil / Structural Design Basis | Final Issue for Design/ Construction-Standard drawings for Anchor bolt | HE-CS-1600 | HE-CS-0110 | FF | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | Review Company Comments - Civil / Structural Design Basis | Re-Issue for Approval - Civil / Structural Design Basis | HE-CS-1570 | HE-CS-1580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | Issued for Review - Civil / Structural Design Basis | Review Company Comments - Civil / Structural Design Basis | HE-CS-1560 | HE-CS-1570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | Issue ICR-Design Basis | Issued for Review - Civil / Structural Design Basis | HE-DB-0010 | HE-CS-1560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.8.42 Civil MTO | 30% Model Review | Issued - Civil MTO 1 | HE-PI-0130 | HE-CS-1510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.1 Material Selection & Corrosion Control Philosophy | P2543-R01-Oct24..1.EN.15.1 Material Selection & Corrosion Control Philosophy | Obtain Company Approval - Material Selection & Corrosion Control Philosophy | Final Issue for Design/ Construction-Material Selection & Corrosion Control Philosophy | HE-CP-80 | HE-CP-90 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.1 Material Selection & Corrosion Control Philosophy | P2543-R01-Oct24..1.EN.15.1 Material Selection & Corrosion Control Philosophy | Re-Issue for Approval - Material Selection & Corrosion Control Philosophy | Obtain Company Approval - Material Selection & Corrosion Control Philosophy | HE-CP-70 | HE-CP-80 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.1 Material Selection & Corrosion Control Philosophy | P2543-R01-Oct24..1.EN.15.1 Material Selection & Corrosion Control Philosophy | Issue ICR - Material Selection & Corrosion Control Philosophy | Receive Company Comments - Material Selection & Corrosion Control Philosophy | HE-CP-50 | HE-CP-60 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.1 Material Selection & Corrosion Control Philosophy | P2543-R01-Oct24..1.EN.15.1 Material Selection & Corrosion Control Philosophy | Receive Company Comments - Material Selection & Corrosion Control Philosophy | Re-Issue for Approval - Material Selection & Corrosion Control Philosophy | HE-CP-60 | HE-CP-70 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.2 Scope of Work | P2543-R01-Oct24..1.EN.15.2 Scope of Work | Obtain Company Approval - Scope of Work for RBI Study | Final Issue for Design/ Construction-Scope of Work for RBI Study | HE-CP-130 | HE-CP-140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.2 Scope of Work | P2543-R01-Oct24..1.EN.15.2 Scope of Work | Re-Issue for Approval - Scope of Work for RBI Study | Obtain Company Approval - Scope of Work for RBI Study | HE-CP-120 | HE-CP-130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.2 Scope of Work | P2543-R01-Oct24..1.EN.15.2 Scope of Work | Issue ICR - Scope of Work for RBI Study | Receive Company Comments - Scope of Work for RBI Study | HE-CP-100 | HE-CP-110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.2 Scope of Work | P2543-R01-Oct24..1.EN.15.2 Scope of Work | Receive Company Comments - Scope of Work for RBI Study | Re-Issue for Approval - Scope of Work for RBI Study | HE-CP-110 | HE-CP-120 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.3 TBE | P2543-R01-Oct24..1.EN.15.3 TBE | Obtain Company Approval - TBE for RBI Study | Final Issue for Design/ Construction-TBE for RBI Study | HE-CP-180 | HE-CP-190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.3 TBE | P2543-R01-Oct24..1.EN.15.3 TBE | Re-Issue for Approval - TBE for RBI Study | Obtain Company Approval - TBE for RBI Study | HE-CP-170 | HE-CP-180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.3 TBE | P2543-R01-Oct24..1.EN.15.3 TBE | Issue ICR - TBE for RBI Study | Receive Company Comments - TBE for RBI Study | HE-CP-150 | HE-CP-160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.3 TBE | P2543-R01-Oct24..1.EN.15.3 TBE | Receive Company Comments - TBE for RBI Study | Re-Issue for Approval - TBE for RBI Study | HE-CP-160 | HE-CP-170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.5 Material Selection Report | P2543-R01-Oct24..1.EN.15.5 Material Selection Report | Obtain Company Approval - Material Selection Report | Final Issue for Design/ Construction-Material Selection Report | HE-CP-230 | HE-CP-240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.5 Material Selection Report | P2543-R01-Oct24..1.EN.15.5 Material Selection Report | Re-Issue for Approval - Material Selection Report | Obtain Company Approval - Material Selection Report | HE-CP-220 | HE-CP-230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.5 Material Selection Report | P2543-R01-Oct24..1.EN.15.5 Material Selection Report | Issue ICR - Material Selection Report | Receive Company Comments - Material Selection Report | HE-CP-200 | HE-CP-210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.5 Material Selection Report | P2543-R01-Oct24..1.EN.15.5 Material Selection Report | Receive Company Comments - Material Selection Report | Re-Issue for Approval - Material Selection Report | HE-CP-210 | HE-CP-220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | Issue ICR-Design Basis | Issue ICR- Data sheet for Distribution Transformer | HE-EL-180 | HE-EL-0670 | FS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | Issue ICR- Data sheet for Distribution Transformer | Issue ICR- Data sheet for LV Distribution board | HE-EL-0670 | HE-EL-0610 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.6 Material Coating & Painting Specification | P2543-R01-Oct24..1.EN.15.6 Material Coating & Painting Specification | Obtain Company Approval - Material Coating & Painting Specification | Final Issue for Design/ Construction-Material Coating & Painting Specification | HE-CP-280 | HE-CP-290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.6 Material Coating & Painting Specification | P2543-R01-Oct24..1.EN.15.6 Material Coating & Painting Specification | Re-Issue for Approval - Material Coating & Painting Specification | Obtain Company Approval - Material Coating & Painting Specification | HE-CP-270 | HE-CP-280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.6 Material Coating & Painting Specification | P2543-R01-Oct24..1.EN.15.6 Material Coating & Painting Specification | Issue ICR - Material Coating & Painting Specification | Receive Company Comments - Material Coating & Painting Specification | HE-CP-250 | HE-CP-260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.6 Material Coating & Painting Specification | P2543-R01-Oct24..1.EN.15.6 Material Coating & Painting Specification | Receive Company Comments - Material Coating & Painting Specification | Re-Issue for Approval - Material Coating & Painting Specification | HE-CP-260 | HE-CP-270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.7 RBI Study Report | P2543-R01-Oct24..1.EN.15.7 RBI Study Report | Obtain Company Approval - RBI Study Report | Final Issue for Design/ Construction-RBI Study Report | HE-CP-330 | HE-CP-340 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.15.7 RBI Study Report | P2543-R01-Oct24..1.EN.15.7 RBI Study Report | Re-Issue for Approval - RBI Study Report | Obtain Company Approval - RBI Study Report | HE-CP-320 | HE-CP-330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.15.7 RBI Study Report | P2543-R01-Oct24..1.EN.15.7 RBI Study Report | Issue ICR - RBI Study Report | Receive Company Comments - RBI Study Report | HE-CP-300 | HE-CP-310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.15.7 RBI Study Report | P2543-R01-Oct24..1.EN.15.7 RBI Study Report | Receive Company Comments - RBI Study Report | Re-Issue for Approval - RBI Study Report | HE-CP-310 | HE-CP-320 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.16 Electrical MTO | P2543-R01-Oct24..1.EN.9.16 Electrical MTO | Electrical 1st MTO | Electrical 2nd MTO | HE-EL-1810 | HE-EL-1830 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.16 Electrical MTO | P2543-R01-Oct24..1.EN.9.16 Electrical MTO | Electrical 2nd MTO | Electrical 3rd MTO | HE-EL-1830 | HE-EL-1850 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | Issue ICR-Design Basis | Issue ICR- I&C Design Basis | HE-DB-0010 | HE-IC-620 | FS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | Issue ICR- I&C Design Basis | Issue ICR- Addendum to DGs | HE-IC-620 | HE-IC-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | Issue ICR- I&C Design Basis | Issue ICR- Specifications for PRS (Pressure Reduction System) | HE-IC-620 | HE-IC-0070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | Issue ICR- I&C Design Basis | Issue ICR- Specification for Leak Detection System | HE-IC-620 | HE-IC-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | Issue ICR- Process Datasheets | Issue ICR- Datasheet for MOV | HE-PR-0550 | HE-IC-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | Issue ICR- Process Datasheets | Issue ICR- Datasheet for GOV & ROV | HE-PR-1260 | HE-IC-1090 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | Issue ICR- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | Issue ICR- Datasheets for Metering Skid | HE-PR-0310 | HE-IC-1150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Issue ICR- Process Datasheets - PRS Skid (at Sweihan CRS) | Issue ICR- Data sheet for PRS (Pressure Reduction System) | HE-PR-0370 | HE-IC-1210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Instrument 1st MTO | Instrument 2nd MTO | HE-IC-2590 | HE-IC-2610 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Instrument 2nd MTO | Instrument 3rd MTO | HE-IC-2610 | HE-IC-2630 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | 90% Model Review | Instrument 3rd MTO | ML2079-B13 | HE-IC-2630 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | Re-Issue for Approval-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Re-Issue for Approval-Telecom Typical Hookup | HE-TL-0630 | HE-TL-910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.2 Telecom MTO | P2543-R01-Oct24..1.EN.10.2 Telecom MTO | Telecom 1st MTO | Telecom 2nd MTO | HE-TL-0850 | HE-TL-0870 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.2 Telecom MTO | P2543-R01-Oct24..1.EN.10.2 Telecom MTO | Telecom 2nd MTO | Telecom 3rd MTO | HE-TL-0870 | HE-TL-0890 | FS | Not Started | Not Started | 30
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.10.2 Telecom MTO | 30% Model Review | Telecom 1st MTO | ML2059-B05 | HE-TL-0850 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.10.2 Telecom MTO | 60% Model Review | Telecom 2nd MTO | ML2069-B09 | HE-TL-0870 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.10.2 Telecom MTO | 90% Model Review | Telecom 3rd MTO | ML2079-B13 | HE-TL-0890 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Lighting Layout | Issue ICR-Operation and Maintenance Manual | HE-EL-1730 | HE-CO-200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Obtain Company Approval-Operation and Maintenance Manual | Final Issue for Design/ Construction-Operation and Maintenance Manuals | HE-CO-180 | HE-CO-190 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Vendor Document Review of Pig Launchers & Receivers | Re-Issue for Approval-Operation and Maintenance Manual | HM-ME-0410 | HE-CO-170 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Piping GA- 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR-Operation and Maintenance Manual | HE-PI-0640 | HE-CO-200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Receive Company Comments-Operation and Maintenance Manual | Re-Issue for Approval-Operation and Maintenance Manual | HE-CO-160 | HE-CO-170 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Issue ICR-Operation and Maintenance Manual | Receive Company Comments-Operation and Maintenance Manual | HE-CO-200 | HE-CO-160 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Final Issue for Design/ Construction-Commissioning Manuals | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | HE-CO-150 | C-COM-840 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Issue ICR-Operation and Maintenance Manual | HE-TL-0710 | HE-CO-200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | Issue ICR-Operation and Maintenance Manual | HE-PI-0580 | HE-CO-200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Telecom Equipment Layout | Issue ICR-Operation and Maintenance Manual | HE-TL-0770 | HE-CO-200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Piping GA for 4" N2 Source Pipeline | Issue ICR-Operation and Maintenance Manual | HE-PI-0760 | HE-CO-200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | Obtain Company Approval-Commissioning Manual | Final Issue for Design/ Construction-Commissioning Manuals | HE-CO-140 | HE-CO-150 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Issue ICR-Commissioning Manual | Issue ICR-Pre-commissioning and Commissioning Plan | HE-CO-110 | C-COM-800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Piping GA Drawings for 591-BVS-01 | Issue ICR-Operation and Maintenance Manual | HE-PI-0820 | HE-CO-200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Piping GA- 52" Pipeline SWEIHAN CRS | Issue ICR-Operation and Maintenance Manual | HE-PI-0700 | HE-CO-200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Issue ICR-Commissioning Manual | Issue ICR-Operation and Maintenance Manual | HE-CO-110 | HE-CO-200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Issue ICR-Operation and Maintenance Manual | HE-PI-0440 | HE-CO-200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | Issue ICR-Commissioning Manual | Receive Company Comments-Commissioning Manual | HE-CO-110 | HE-CO-120 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | Issue ICR-Operation and Maintenance Manual | HE-PI-0880 | HE-CO-200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Overall Plot Plan- 4" N2 Source Pipeline | Issue ICR-Operation and Maintenance Manual | HE-PI-0510 | HE-CO-200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | Issue Tie-in Philosophy for all new facilities - IFC | Issue ICR-Commissioning Manual | ML1010-B14 | HE-CO-110 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | Issue Tie-in Philosophy for all new facilities - IFC | Issue ICR-Commissioning Manual | ML1010-B14 | HE-CO-110 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | Re-Issue for Approval-Commissioning Manual | Re-Issue for Approval-Shutdown Requirements & Plan | HE-CO-130 | C-COM-870 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Electrical Equipment Layout | Issue ICR-Operation and Maintenance Manual | HE-EL-0530 | HE-CO-200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Commissioning Manuals | Final Issue for Design/ Construction-Operation and Maintenance Manuals | HE-CO-150 | HE-CO-190 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Re-Issue for Approval-Operation and Maintenance Manual | Obtain Company Approval-Operation and Maintenance Manual | HE-CO-170 | HE-CO-180 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | Re-Issue for Approval-Commissioning Manual | Obtain Company Approval-Commissioning Manual | HE-CO-130 | HE-CO-140 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | Receive Company Comments-Commissioning Manual | Re-Issue for Approval-Commissioning Manual | HE-CO-120 | HE-CO-130 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Earthing Layout | Issue ICR-Operation and Maintenance Manual | HE-EL-1670 | HE-CO-200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Issue ICR-Operation and Maintenance Manual | HE-IC-2570 | HE-CO-200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR-Operation and Maintenance Manual | HE-PI-0370 | HE-CO-200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | P2543-R01-Oct24..4.4.2 Commissioning | Final Issue for Design/ Construction-Operation and Maintenance Manuals | Approval of Commissioning Dossiers | HE-CO-190 | CCM-PM4500 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | P2543-R01-Oct24..4.4.2 Commissioning | Final Issue for Design/ Construction-Commissioning Manuals | Approval of Commissioning Dossiers | HE-CO-150 | CCM-PM4500 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | Final Issue for Design/ Construction-Commissioning Manuals | Final Issue for Design/ Construction-Shutdown Requirements & Plan | HE-CO-150 | C-COM-890 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.1.1 Commissioning Manuals | P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | Issue ICR-Commissioning Manual | Issue ICR-Shutdown Requirements & Plan | HE-CO-110 | C-COM-850 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.PM.12 Workshops | Lesson Learned Workshop | Project Risk Review Workshop | HE-WS-0070 | HE-WS-0010 | FS | Completed | Completed | 15
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.PM.12 Workshops | Re-Issue for HAZOP Studies- P&ID's review | HAZOP Workshop | HE-PR-0130 | HE-WS-0210 | FS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Plot Plan Layout Review Workshop | HE-PI-0320 | HE-WS-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | Plot Plan Layout Review Workshop | HE-PI-0390 | HE-WS-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- Overall Plot Plan - 4" N2 Source Pipeline | Plot Plan Layout Review Workshop | HE-PI-0460 | HE-WS-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.PM.12 Workshops | Issue ICR- Plot plan - BVS | Plot Plan Layout Review Workshop | HE-PI-0530 | HE-WS-0090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.PM.12 Workshops | ALARP Workshop | SIMOPS Workshop | HE-WS-0200 | HE-WS-0170 | FS | Completed | Not Started | 30
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.PM.12 Workshops | Bow Tie Workshop | ALARP Workshop | HE-WS-0190 | HE-WS-0200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | P2543-R01-Oct24..1.PM.12 Workshops | Re-Issue for Approval - Material Selection Diagram | CRAS Workshop | HE-CP-0030 | HE-WS-0310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.5 Material Selection Report | P2543-R01-Oct24..1.PM.12 Workshops | Re-Issue for Approval - Material Selection Report | CRAS Workshop | HE-CP-220 | HE-WS-0310 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.PM.12 Workshops | 60% Model Review | PHSER III Workshop | ML2069-B09 | HE-WS-0270 | FS | Completed | Not Started | 30
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..1.PM.12 Workshops | Approval of Commissioning Dossiers | PHSER V Workshop | CCM-PM4500 | HE-WS-0290 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.15.1 Material Selection & Corrosion Control Philosophy | Issue ICR- Process Flow Diagrams ( New + Existing) | Issue ICR - Material Selection & Corrosion Control Philosophy | HE-PR-0040 | HE-CP-50 | FF | Completed | Completed | 6
P2543-R01-Oct24..1.EN.15.1 Material Selection & Corrosion Control Philosophy | P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | Issue ICR - Material Selection & Corrosion Control Philosophy | Issue ICR - Material Selection Diagram | HE-CP-50 | HE-CP-0010 | FF | Completed | Completed | 3
P2543-R01-Oct24..1.EN.15.1 Material Selection & Corrosion Control Philosophy | P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | Final Issue for Design/ Construction-Material Selection & Corrosion Control Philosophy | Obtain Company Approval - Material Selection Diagram | HE-CP-90 | HE-CP-0040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | P2543-R01-Oct24..1.EN.15.5 Material Selection Report | Issue ICR - Material Selection Diagram | Issue ICR - Material Selection Report | HE-CP-0010 | HE-CP-200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.1 Material Selection & Corrosion Control Philosophy | P2543-R01-Oct24..1.EN.15.2 Scope of Work | Issue ICR - Material Selection & Corrosion Control Philosophy | Issue ICR - Scope of Work for RBI Study | HE-CP-50 | HE-CP-100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.6 Material Coating & Painting Specification | P2543-R01-Oct24..1.EN.15.7 RBI Study Report | Final Issue for Design/ Construction-Material Coating & Painting Specification | Final Issue for Design/ Construction-RBI Study Report | HE-CP-290 | HE-CP-340 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.15.2 Scope of Work | P2543-R01-Oct24..1.EN.15.7 RBI Study Report | Final Issue for Design/ Construction-Scope of Work for RBI Study | Issue ICR - RBI Study Report | HE-CP-140 | HE-CP-300 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.15.3 TBE | P2543-R01-Oct24..1.EN.15.7 RBI Study Report | Final Issue for Design/ Construction-TBE for RBI Study | Issue ICR - RBI Study Report | HE-CP-190 | HE-CP-300 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.15.2 Scope of Work | P2543-R01-Oct24..1.EN.15.3 TBE | Final Issue for Design/ Construction-Scope of Work for RBI Study | Issue ICR - TBE for RBI Study | HE-CP-140 | HE-CP-150 | FS | Completed | Completed | 20
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.PM.12 Workshops | Plot Plan Layout Review Workshop | Design Review Workshop | HE-WS-0090 | HE-WS-0030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Constructability Review Workshop | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-WS-0050 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Constructability Review Workshop | General | HE-WS-0050 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Project Risk Review Workshop | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-WS-0010 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Project Risk Review Workshop | General | HE-WS-0010 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.PM.12 Workshops | CRAS Workshop | Bow Tie Workshop | HE-WS-0310 | HE-WS-0190 | FS | Completed | Completed | 2
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.PM.12 Workshops | SIMOPS Workshop | PHSER III Workshop | HE-WS-0170 | HE-WS-0270 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.PM.12 Workshops | PHSER III Workshop | PHSER IV Workshop | HE-WS-0270 | HE-WS-0280 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.PM.12 Workshops | PHSER IV Workshop | PHSER V Workshop | HE-WS-0280 | HE-WS-0290 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..ML Milestones | PHSER V Workshop | Project Finish | HE-WS-0290 | ML1060 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.12.9 HVAC Design Basis | P2543-R01-Oct24..1.EN.12.9 HVAC Design Basis | Re-Issue for Approval-Design Basis | Obtain Company Approval-Design Basis | HE-HV-150 | HE-HV-170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.9 HVAC Design Basis | P2543-R01-Oct24..1.EN.12.9 HVAC Design Basis | Receive Company Comments-Design Basis | Re-Issue for Approval-Design Basis | HE-HV-190 | HE-HV-150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.9 HVAC Design Basis | P2543-R01-Oct24..1.EN.12.9 HVAC Design Basis | Issue ICR-Design Basis | Receive Company Comments-Design Basis | HE-HV-180 | HE-HV-190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.9 HVAC Design Basis | P2543-R01-Oct24..1.EN.12.9 HVAC Design Basis | Obtain Company Approval-Design Basis | Final Issue for Design-Design Basis | HE-HV-170 | HE-HV-160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A11 Specification for HVAC | P2543-R01-Oct24..1.EN.12.A11 Specification for HVAC | Receive Company Comments- Specification for HVAC | Re-Issue for Approval- Specification for HVAC | HE-HV-2700 | HE-HV-2710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A11 Specification for HVAC | P2543-R01-Oct24..1.EN.12.A11 Specification for HVAC | Obtain Company Approval- Specification for HVAC | Final Issue for Design/ Construction-Specification for HVAC | HE-HV-2720 | HE-HV-2730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A11 Specification for HVAC | P2543-R01-Oct24..1.EN.12.A11 Specification for HVAC | Re-Issue for Approval- Specification for HVAC | Obtain Company Approval- Specification for HVAC | HE-HV-2710 | HE-HV-2720 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A11 Specification for HVAC | P2543-R01-Oct24..1.EN.12.A11 Specification for HVAC | Issue ICR- Specification for HVAC | Receive Company Comments- Specification for HVAC | HE-HV-2690 | HE-HV-2700 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.12.9 HVAC Design Basis | Receive Company Comments-Design Basis | Issue ICR-Design Basis | HE-DB-0020 | HE-HV-180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.9 HVAC Design Basis | P2543-R01-Oct24..1.EN.12.A11 Specification for HVAC | Issue ICR-Design Basis | Issue ICR- Specification for HVAC | HE-HV-180 | HE-HV-2690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A111 Specification for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A111 Specification for Material Handling Equipment | Receive Company Comments- Specification for Material Handling | Re-Issue for Approval- Specification for Material Handling | HE-HV-2750 | HE-HV-2760 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A111 Specification for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A111 Specification for Material Handling Equipment | Obtain Company Approval- Specification for Material Handling | Final Issue for Design/ Construction-Specification for Material Handling | HE-HV-2770 | HE-HV-2780 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A111 Specification for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A111 Specification for Material Handling Equipment | Re-Issue for Approval- Specification for Material Handling | Obtain Company Approval- Specification for Material Handling | HE-HV-2760 | HE-HV-2770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A111 Specification for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A111 Specification for Material Handling Equipment | Issue ICR- Specification for Material Handling | Receive Company Comments- Specification for Material Handling | HE-HV-2740 | HE-HV-2750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | P2543-R01-Oct24..1.EN.12.A111 Specification for Material Handling Equipment | Receive Company Comments-Piping Material Specifications | Issue ICR- Specification for Material Handling | HE-PI-0020 | HE-HV-2740 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A1111 Datasheet for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A1111 Datasheet for Material Handling Equipment | Receive Company Comments- Datasheet for Material Handling | Re-Issue for Approval- Datasheet for Material Handling | HE-HV-2800 | HE-HV-2810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A1111 Datasheet for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A1111 Datasheet for Material Handling Equipment | Obtain Company Approval- Datasheet for Material Handling | Final Issue for Design/ Construction-Datasheet for Material Handling | HE-HV-2820 | HE-HV-2830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A1111 Datasheet for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A1111 Datasheet for Material Handling Equipment | Re-Issue for Approval- Datasheet for Material Handling | Obtain Company Approval- Datasheet for Material Handling | HE-HV-2810 | HE-HV-2820 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A1111 Datasheet for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A1111 Datasheet for Material Handling Equipment | Issue ICR- Datasheet for Material Handling | Receive Company Comments- Datasheet for Material Handling | HE-HV-2790 | HE-HV-2800 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A111 Specification for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A1111 Datasheet for Material Handling Equipment | Issue ICR- Specification for Material Handling | Issue ICR- Datasheet for Material Handling | HE-HV-2740 | HE-HV-2790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A11111 MR for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A11111 MR for Material Handling Equipment | Receive Company Comments- Material Requisition for Material Handling | Re-Issue for Approval- Material Requisition for Material Handling | HE-HV-2850 | HE-HV-2860 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A11111 MR for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A11111 MR for Material Handling Equipment | Obtain Company Approval- Material Requisition for Material Handling | Final Issue for Design/ Construction-Material Requisition for Material Handling | HE-HV-2870 | HE-HV-2880 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A11111 MR for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A11111 MR for Material Handling Equipment | Re-Issue for Approval- Material Requisition for Material Handling | Obtain Company Approval- Material Requisition for Material Handling | HE-HV-2860 | HE-HV-2870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A11111 MR for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A11111 MR for Material Handling Equipment | Issue ICR- Material Requisition for Material Handling | Receive Company Comments- Material Requisition for Material Handling | HE-HV-2840 | HE-HV-2850 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A111111 TBE for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A111111 TBE for Material Handling Equipment | Receive Company Comments- TBE for Material Handling | Re-Issue for Approval- TBE for Material Handling | HE-HV-2900 | HE-HV-2910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A111111 TBE for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A111111 TBE for Material Handling Equipment | Obtain Company Approval- TBE for Material Handling | Final Issue for Design/ Construction- TBE for Material Handling | HE-HV-2920 | HE-HV-2930 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.12.A111111 TBE for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A111111 TBE for Material Handling Equipment | Re-Issue for Approval- TBE for Material Handling | Obtain Company Approval- TBE for Material Handling | HE-HV-2910 | HE-HV-2920 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.12.A111111 TBE for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A111111 TBE for Material Handling Equipment | Issue ICR- TBE for Material Handling | Receive Company Comments- TBE for Material Handling | HE-HV-2890 | HE-HV-2900 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A1111 Datasheet for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A11111 MR for Material Handling Equipment | Issue ICR- Datasheet for Material Handling | Issue ICR- Material Requisition for Material Handling | HE-HV-2790 | HE-HV-2840 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A11111 MR for Material Handling Equipment | P2543-R01-Oct24..1.1.2.25.16.1 Ordering | Issue ICR- Material Requisition for Material Handling | RFQ, Receipt of Bid for Junction Boxes | HE-HV-2840 | HP-ME-0810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.16.1 Ordering | P2543-R01-Oct24..1.EN.12.A111111 TBE for Material Handling Equipment | RFQ, Receipt of Bid for Junction Boxes | Issue ICR- TBE for Material Handling | HP-ME-0810 | HE-HV-2890 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.9 HVAC Design Basis | P2543-R01-Oct24..1.EN.12.A111 Specification for Material Handling Equipment | Final Issue for Design-Design Basis | Final Issue for Design/ Construction-Specification for Material Handling | HE-HV-160 | HE-HV-2780 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A11 Specification for HVAC | P2543-R01-Oct24..1.EN.12.A111 Specification for Material Handling Equipment | Final Issue for Design/ Construction-Specification for HVAC | Final Issue for Design/ Construction-Specification for Material Handling | HE-HV-2730 | HE-HV-2780 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A1111 Datasheet for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A11111 MR for Material Handling Equipment | Final Issue for Design/ Construction-Datasheet for Material Handling | Final Issue for Design/ Construction-Material Requisition for Material Handling | HE-HV-2830 | HE-HV-2880 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A111 Specification for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A1111 Datasheet for Material Handling Equipment | Final Issue for Design/ Construction-Specification for Material Handling | Final Issue for Design/ Construction-Datasheet for Material Handling | HE-HV-2780 | HE-HV-2830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A30 TBE for Metering Skid | P2543-R01-Oct24..1.1.2.LL.22.1 Ordering | Issue ICR-TBE for Metering Skid | Prepare TBE and Company approval for Custody Metering Skid | HE-IC-2110 | HP-ME-0020 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A30 TBE for Metering Skid | P2543-R01-Oct24..1.1.2.LL.22.1 Ordering | Obtain Company Approval-TBE for Metering Skid | Prepare TBE and Company approval for Custody Metering Skid | HE-IC-2140 | HP-ME-0020 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A33 TBE for PRS (Pressure Reduction Skid) | P2543-R01-Oct24..1.1.2.LL.21.1 Ordering | Issue ICR-TBE for PRS | Prepare TBE and Company approval for Pressure Reduction Skid | HE-IC-2170 | HP-ME-0070 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.A331 TBE for Leak Detection System | P2543-R01-Oct24..1.1.2.LL.17.1 Ordering | Issue ICR-TBE for Leak Detection System | Prepare TBE and Company approval for Leak Detection System | HE-IC-2230 | HP-ME-0120 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.3.9 TBE for Sals Gas CRS Filters | P2543-R01-Oct24..1.1.2.LL.11.1 Ordering | Issue ICR-TBEs for Sales Gas CRS Filters | Prepare TBE and Company approval for Filter Package | HE-ME-0190 | HP-ME-0170 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.3.9 TBE for Sals Gas CRS Filters | P2543-R01-Oct24..1.1.2.LL.11.1 Ordering | Obtain Company Approval-TBEs for Sales Gas CRS Filters | Prepare TBE and Company approval for Filter Package | HE-ME-0220 | HP-ME-0170 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.5 TBE for ROV/ GOV | P2543-R01-Oct24..1.1.2.LL.10.1 Ordering | Issue ICR- TBE for ROV/ GOV | Prepare TBE and Company approval for ROV/ GOV | HE-IC-2290 | HP-ME-0270 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.5 TBE for ROV/ GOV | P2543-R01-Oct24..1.1.2.LL.10.1 Ordering | Obtain Company Approval- TBE for ROV/ GOV | Prepare TBE and Company approval for ROV/ GOV | HE-IC-2320 | HP-ME-0270 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.6 TBE for MOV | P2543-R01-Oct24..1.1.2.LL.9.1 Ordering | Issue ICR- TBE for MOV | Prepare TBE and Company approval for MOV | HE-IC-2050 | HP-ME-0320 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.9.1 Ordering | P2543-R01-Oct24..1.1.2.LL.9.1 Ordering | Prepare TBE and Company approval for MOV | Commercial Clarifications & Placement of PO for MOV | HP-ME-0320 | HP-ME-0330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.9.1 Ordering | P2543-R01-Oct24..1.1.2.LL.9.1 Ordering | RFQ, Receipt of Bid for MOV | Commercial Clarifications & Placement of PO for MOV | HP-ME-0310 | HP-ME-0330 | FS | Completed | Completed | 30
P2543-R01-Oct24..1.EN.9.6.27 TBE for UPS System | P2543-R01-Oct24..1.1.2.LL.8.1 Ordering | Issue ICR-TBE for UPS System | Prepare TBE and Company approval for AC UPS | HE-EL-1330 | HP-ME-0370 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.27 TBE for UPS System | P2543-R01-Oct24..1.1.2.LL.8.1 Ordering | Obtain Company Approval-TBE for UPS System | Prepare TBE and Company approval for AC UPS | HE-EL-1360 | HP-ME-0370 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.28 TBE for Distribution Boards | P2543-R01-Oct24..1.1.2.25.7.1 Ordering | Issue ICR-TBE for Distribution Boards | Prepare TBE and Company approval for Power Distribution Boards | HE-EL-1390 | HP-ME-0420 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.28 TBE for Distribution Boards | P2543-R01-Oct24..1.1.2.25.7.1 Ordering | Obtain Company Approval-TBE for Distribution Boards | Prepare TBE and Company approval for Power Distribution Boards | HE-EL-1420 | HP-ME-0420 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.30 TBE for Distibution Transformers | P2543-R01-Oct24..1.1.2.25.1.1 Ordering | Issue ICR-TBE for Distribution Transformer | Prepare TBE and Company approval for Distribution Transformer | HE-EL-1450 | HP-ME-0470 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.8 TBE for Solar Panels | P2543-R01-Oct24..1.1.2.LL.6.1 Ordering | Issue ICR-TBE for Solar Panels | Prepare TBE and Company approval for Solar PV system | HE-EL-1270 | HP-ME-0520 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.29 TBE for Active/ Passive Shelters | P2543-R01-Oct24..1.1.2.LL.5.1 Ordering | Issue ICR - TBE for Active / Passive Shelters | Prepare TBE and Company approval for Active/ Passive Cooled Shelter | HE-EL-1210 | HP-ME-0570 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.29 TBE for Active/ Passive Shelters | P2543-R01-Oct24..1.1.2.LL.5.1 Ordering | Obtain Company Approval - TBE for Active / Passive Shelters | Prepare TBE and Company approval for Active/ Passive Cooled Shelter | HE-EL-1240 | HP-ME-0570 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | P2543-R01-Oct24..1.1.2.LL.4.1 Ordering | Issue ICR-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Prepare TBE and Company approval for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0610 | HP-ME-0620 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | P2543-R01-Oct24..1.1.2.25.14.1 Ordering | Issue ICR-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Prepare TBE and Company approval for Access Switch, Fiber Optic Patch Panel and Media Converter | HE-TL-0610 | HP-ME-0670 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.10 TBE for Fire & Gas Detectors | P2543-R01-Oct24..1.1.2.LL.18.1 Ordering | Issue ICR- TBE for Gas Detectors | Prepare TBE and Company approval for Gas Detectors | HE-IC-2350 | HP-ME-0720 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.3 TBE for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.1.2.25.15.1 Ordering | Issue ICR- TBE for Field Instruments / H2S Analyzers | Prepare TBE and Company approval for Field Instruments | HE-IC-2410 | HP-ME-0770 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.3 TBE for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.1.2.25.15.1 Ordering | Obtain Company Approval- TBE for Field Instruments / H2S Analyzers | Prepare TBE and Company approval for Field Instruments | HE-IC-2440 | HP-ME-0770 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A111111 TBE for Material Handling Equipment | P2543-R01-Oct24..1.1.2.25.3.1 Ordering | Issue ICR- TBE for Material Handling | Prepare TBE and Company approval for HVAC Equipment | HE-HV-2890 | HP-ME-0870 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.1.2.25.2.1 Ordering | Issue ICR-TBE for Fire Fighting & Safety Eqpt | Prepare TBE and Company approval for Fire Suppression System | HE-HS-1150 | HP-ME-0920 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.1.2.25.13.1 Ordering | Issue ICR-TBE for Fire Fighting & Safety Eqpt | Prepare TBE and Company approval for Fire Fighting & Safety Equipment | HE-HS-1150 | HP-ME-0970 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.1.2.25.13.1 Ordering | Obtain Company Approval-TBE for Fire Fighting & Safety Eqpt | Prepare TBE and Company approval for Fire Fighting & Safety Equipment | HE-HS-1180 | HP-ME-0970 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.22 TBE for Linepipes | P2543-R01-Oct24..1.1.1.16.1 Ordering | Receive Company Comments - TBE for Line pipes | Prepare TBE and Company approval for Line Pipes (Coated) | HE-PL-2060 | HP-ME-1030 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.22 TBE for Linepipes | P2543-R01-Oct24..1.1.1.16.1 Ordering | Issue ICR - TBE for Line pipes | Prepare TBE and Company approval for Line Pipes (Coated) | HE-PL-2050 | HP-ME-1030 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.54 TBE for Pig Signaler | P2543-R01-Oct24..1.1.1.19.1 Ordering | Issue ICR- TBE for Pig Signaler | Prepare TBE and Company approval for Pig Signaler | HE-PL-2330 | HP-ME-1130 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.54 TBE for Pig Signaler | P2543-R01-Oct24..1.1.1.19.1 Ordering | Obtain Company Approval- TBE for Pig Signaler | Prepare TBE and Company approval for Pig Signaler | HE-PL-2360 | HP-ME-1130 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.23 TBE for Hot Induction Bends | P2543-R01-Oct24..1.1.1.1.1 Ordering | Issue ICR - TBE for Hot Induction Bends | Prepare TBE and Company approval for Hot Incution Bend | HE-PL-2090 | HP-ME-1180 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.23 TBE for Hot Induction Bends | P2543-R01-Oct24..1.1.1.1.1 Ordering | Obtain Company Approval - TBE for Hot Induction Bends | Prepare TBE and Company approval for Hot Incution Bend | HE-PL-2120 | HP-ME-1180 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.25 TBE for Isolating Joints | P2543-R01-Oct24..1.1.1.3.1 Ordering | Issue ICR - TBE for Isolating Joints | Prepare TBE and Company approval for Isolating Joints | HE-PL-2210 | HP-ME-1230 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.25 TBE for Isolating Joints | P2543-R01-Oct24..1.1.1.3.1 Ordering | Obtain Company Approval - TBE for Isolating Joints | Prepare TBE and Company approval for Isolating Joints | HE-PL-2240 | HP-ME-1230 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.24 TBE for Pigging Tees | P2543-R01-Oct24..1.1.1.2.1 Ordering | Issue ICR - TBE for Pigging Tees | Prepare TBE and Company approval for Pigging & Split Tee | HE-PL-2150 | HP-ME-1280 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.24 TBE for Pigging Tees | P2543-R01-Oct24..1.1.1.2.1 Ordering | Obtain Company Approval - TBE for Pigging Tees | Prepare TBE and Company approval for Pigging & Split Tee | HE-PL-2180 | HP-ME-1280 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.2.6 TBE for Ball valves/ Plug Valves | P2543-R01-Oct24..1.1.BK.1.1 Ordering | Issue ICR- TBE for Ball valves/ Plug Valves | Prepare TBE and Company approval for Manual/ Ball/ Globe/ Check/ Plug Valves | HE-PI-1080 | HP-ME-1080 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.2.6 TBE for Ball valves/ Plug Valves | P2543-R01-Oct24..1.1.BK.1.1 Ordering | Obtain Company Approval- TBE for Ball valves/ Plug Valves | Prepare TBE and Company approval for Manual/ Ball/ Globe/ Check/ Plug Valves | HE-PI-1110 | HP-ME-1080 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.26 TBE for Mainline Ball Valve | P2543-R01-Oct24..1.1.BK.1.1 Ordering | Issue ICR - TBE for Mainline Ball Valve | Prepare TBE and Company approval for Manual/ Ball/ Globe/ Check/ Plug Valves | HE-PL-2270 | HP-ME-1080 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.26 TBE for Mainline Ball Valve | P2543-R01-Oct24..1.1.BK.1.1 Ordering | Obtain Company Approval - TBE for Mainline Ball Valve | Prepare TBE and Company approval for Manual/ Ball/ Globe/ Check/ Plug Valves | HE-PL-2300 | HP-ME-1080 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.26 TBE for Power & Control Cables | P2543-R01-Oct24..1.1.BK.13.1 Ordering | Issue ICR-TBE for Power & Control Cables | Prepare TBE and Company approval for Cable Trays | HE-EL-1510 | HP-BK-0120 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.4 TBE for Electrical Bulks (JBs, Fixtures, Sockets etc) | P2543-R01-Oct24..1.1.BK.15.1 Ordering | Issue ICR-TBE for Electrical Bulks | Prepare TBE and Company approval for Earthing Material | HE-EL-2410 | HP-BK-0170 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.4 TBE for Electrical Bulks (JBs, Fixtures, Sockets etc) | P2543-R01-Oct24..1.1.BK.15.1 Ordering | Obtain Company Approval-TBE for Electrical Bulks | Prepare TBE and Company approval for Earthing Material | HE-EL-2440 | HP-BK-0170 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.4 TBE for Electrical Bulks (JBs, Fixtures, Sockets etc) | P2543-R01-Oct24..1.1.BK.15.1 Ordering | Final Issue for Design/ Construction-TBE for Electrical Bulks | Commercial Clarifications & Placement of PO for Earthing Material | HE-EL-2450 | HP-BK-0180 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.6.5 TBE for Cable Glanding & Termination | P2543-R01-Oct24..1.1.BK.3.1 Ordering | Issue ICR-TBE for Glanding & Termination | Prepare TBE and Company approval for Cable Gland & Termination | HE-EL-2360 | HP-BK-540 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.1 TBE for LV Switchgear | P2543-R01-Oct24..1.1.BK.16.1 Ordering | Issue ICR-TBE for LV Switchgear | Prepare TBE and Company approval for MCT | HE-EL-2210 | HP-BK-0220 | SS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.9.6.1 TBE for LV Switchgear | P2543-R01-Oct24..1.1.BK.16.1 Ordering | Final Issue for Design/ Construction-TBE for LV Switchgear | Commercial Clarifications & Placement of PO for MCT | HE-EL-2250 | HP-BK-0230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | P2543-R01-Oct24..1.1.BK.16.1 Ordering | Issue ICR-Material Requisition for LV Switchgear | RFQ, Receipt of Bid for MCT | HE-EL-1960 | HP-BK-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.3 Civil GA Darawings | P2543-R01-Oct24..1.EN.8.3 Civil GA Darawings | Review Company Comments - Civil GA Drawings | Re-Issue for Approval - Civil GA Drawings | HE-CS-1650 | HE-CS-1610 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.3 Civil GA Darawings | P2543-R01-Oct24..1.EN.8.3 Civil GA Darawings | Re-Issue for Approval - Civil GA Drawings | Obtain Company Approval - Civil GA Drawings | HE-CS-1610 | HE-CS-1620 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.3 Civil GA Darawings | P2543-R01-Oct24..1.EN.8.3 Civil GA Darawings | Obtain Company Approval - Civil GA Drawings | Final Issue for Design/ Construction-Civil GA Drawings | HE-CS-1620 | HE-CS-1630 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.3 Civil GA Darawings | P2543-R01-Oct24..1.EN.8.3 Civil GA Darawings | Issued for Review - Civil GA Drawings | Review Company Comments - Civil GA Drawings | HE-CS-1640 | HE-CS-1650 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..1.EN.8.3 Civil GA Darawings | Issued for Review - Civil UG layout | Issued for Review - Civil GA Drawings | HE-CS-0490 | HE-CS-1640 | SS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | Obtain Company Approval- Plot plan - BVS | Issued for Review - Site grading, road, drainage and fence layout | HE-PI-0570 | HE-CS-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.22.1 Ordering | P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | RFQ, Receipt of Bid for Custody Metering Skid | Issued for Review - Gas metering skid foundation drawings | HP-ME-0010 | HE-CS-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | Issue ICR- Plot plan - BVS | Issued for Review - Calculations for Pipe supports | HE-PI-0530 | HE-CS-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | Issue ICR- Process Datasheets - Pig Launcher / Receiver | Issue ICR- Vent and Depressurization Report (for new facilities) | HE-PR-0490 | HE-PR-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Process Datasheets - Pig Launcher / Receiver | Pipeline | HE-PR-0530 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- Process Datasheets - Pig Launcher / Receiver | Pipeline | HE-PR-0490 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Process Datasheets - Pig Launcher / Receiver | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | HE-PR-0530 | ML1015-B08 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Pipeline Specifications - Addendum to DGS | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | HE-PL-0110 | ML1015-B08 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..ML.EN Detail Engineering | Issue ICR- Process Datasheets - Pig Launcher / Receiver | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | HE-PR-0490 | ML1015-B08 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..1.1.2.LL.12.1 Ordering | Issue ICR- Process Datasheets - Pig Launcher / Receiver | RFQ, Receipt of Bid for Pig Launchers & Receivers | HE-PR-0490 | HP-ME-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Pipeline Specifications - Addendum to DGS | Manufacturing & Assembly of Pig Launchers & Receivers | HE-PL-0110 | HM-ME-0420 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.8 Pipeline Specifications - Addendum to DGS | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Pipeline Specifications - Addendum to DGS | Issue MRs for All Mechanical Equipment & Packages (Final Issue) | HE-PL-0110 | ML1017-B18 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-Process Datasheets - Pig Launcher / Receiver | Manufacturing & Assembly of Pig Launchers & Receivers | HE-PR-0530 | HM-ME-0420 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Process Datasheets - Pig Launcher / Receiver | Issue MRs for All Mechanical Equipment & Packages (Final Issue) | HE-PR-0530 | ML1017-B18 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | Issue ICR- Process Datasheets - Pig Launcher / Receiver | Manufacturing & Assembly of Pig Launchers & Receivers | HE-PR-0490 | HM-ME-0420 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..ML.EN Detail Engineering | Issue ICR- Process Datasheets - Pig Launcher / Receiver | Issue MRs for All Mechanical Equipment & Packages (Final Issue) | HE-PR-0490 | ML1017-B18 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.12.1 Ordering | P2543-R01-Oct24..1.1.2.LL.12.1 Ordering | RFQ, Receipt of Bid for Pig Launchers & Receivers | Prepare TBE and Company approval for Pig Launchers & Receivers | HP-ME-0210 | HP-ME-0220 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.12.1 Ordering | P2543-R01-Oct24..1.1.2.LL.12.1 Ordering | RFQ, Receipt of Bid for Pig Launchers & Receivers | Commercial Clarifications & Placement of PO for Pig Launchers & Receivers | HP-ME-0210 | HP-ME-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.12.1 Ordering | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | RFQ, Receipt of Bid for Pig Launchers & Receivers | Pipeline | HP-ME-0210 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.5.4 Addendum to DGS (Launche/Receiver) | P2543-R01-Oct24..1.EN.5.4 Addendum to DGS (Launche/Receiver) | Obtain Company Approval- Addendum to DGS | Final Issue for Design/ Construction- Addendum to DGS | HE-ME-600 | HE-ME-610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.4 Addendum to DGS (Launche/Receiver) | P2543-R01-Oct24..1.EN.5.4 Addendum to DGS (Launche/Receiver) | Re-Issue for Approval- Addendum to DGS | Obtain Company Approval- Addendum to DGS | HE-ME-590 | HE-ME-600 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.4 Addendum to DGS (Launche/Receiver) | P2543-R01-Oct24..1.EN.5.4 Addendum to DGS (Launche/Receiver) | Issue ICR- Addendum to DGS | Receive Company Comments- Addendum to DGS | HE-ME-620 | HE-ME-580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.4 Addendum to DGS (Launche/Receiver) | P2543-R01-Oct24..1.EN.5.4 Addendum to DGS (Launche/Receiver) | Receive Company Comments- Addendum to DGS | Re-Issue for Approval- Addendum to DGS | HE-ME-580 | HE-ME-590 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | P2543-R01-Oct24..1.EN.5.4 Addendum to DGS (Launche/Receiver) | Issue ICR- Addendum to DGS | Issue ICR- Addendum to DGS | HE-ME-0010 | HE-ME-620 | SS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | P2543-R01-Oct24..1.EN.5.4 Addendum to DGS (Launche/Receiver) | Final Issue for Design/ Construction- Addendum to DGS | Final Issue for Design/ Construction- Addendum to DGS | HE-ME-0050 | HE-ME-610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.4 Addendum to DGS (Launche/Receiver) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction- Addendum to DGS | Mechanical | HE-ME-610 | CAB-4430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.5.5 Pig Launcher/Receiver Length Report | P2543-R01-Oct24..1.EN.5.5 Pig Launcher/Receiver Length Report | Obtain Company Approval- Pig Launcher/Receiver Length Report | Final Issue for Design/ Construction- Pig Launcher/Receiver Length Report | HE-ME-650 | HE-ME-660 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.5 Pig Launcher/Receiver Length Report | P2543-R01-Oct24..1.EN.5.5 Pig Launcher/Receiver Length Report | Re-Issue for Approval- Pig Launcher/Receiver Length Report | Obtain Company Approval- Pig Launcher/Receiver Length Report | HE-ME-640 | HE-ME-650 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.5 Pig Launcher/Receiver Length Report | P2543-R01-Oct24..1.EN.5.5 Pig Launcher/Receiver Length Report | Issue ICR- Pig Launcher/Receiver Length Report | Receive Company Comments- Pig Launcher/Receiver Length Report | HE-ME-670 | HE-ME-630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.5 Pig Launcher/Receiver Length Report | P2543-R01-Oct24..1.EN.5.5 Pig Launcher/Receiver Length Report | Receive Company Comments- Pig Launcher/Receiver Length Report | Re-Issue for Approval- Pig Launcher/Receiver Length Report | HE-ME-630 | HE-ME-640 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.4 Addendum to DGS (Launche/Receiver) | P2543-R01-Oct24..1.EN.5.5 Pig Launcher/Receiver Length Report | Issue ICR- Addendum to DGS | Issue ICR- Pig Launcher/Receiver Length Report | HE-ME-620 | HE-ME-670 | SS | Completed | Completed | 15
P2543-R01-Oct24..1.EN.5.5 Pig Launcher/Receiver Length Report | P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | Final Issue for Design/ Construction- Pig Launcher/Receiver Length Report | Final Issue for Design/ Construction-Material Requisitions for Pig Launcher/Receiver | HE-ME-660 | HE-ME-520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.1 Datasheet for PIG RECEIVER (839-V-101) 52" | P2543-R01-Oct24..1.EN.5.2.2 Datasheet for PIG LAUNCHER (838-V-602) 52" | Issue ICR-Datasheet for PIG RECEIVER (839-V-101) | Issue ICR-Datasheet for PIG LAUNCHER (838-V-602) | HE-ME-310 | HE-ME-360 | SS | Completed | Completed | 3
P2543-R01-Oct24..1.EN.5.2.2 Datasheet for PIG LAUNCHER (838-V-602) 52" | P2543-R01-Oct24..1.EN.5.2.3 Datasheet for PIG RECEIVER (838-V-601) 56" | Issue ICR-Datasheet for PIG LAUNCHER (838-V-602) | Issue ICR-Datasheet for PIG RECEIVER (838-V-601) | HE-ME-360 | HE-ME-410 | SS | Completed | Completed | 3
P2543-R01-Oct24..1.EN.5.2.3 Datasheet for PIG RECEIVER (838-V-601) 56" | P2543-R01-Oct24..1.EN.5.2.4 Datasheet for PIG LAUNCHER (607-V-603) 56" | Issue ICR-Datasheet for PIG RECEIVER (838-V-601) | Issue ICR-Datasheet for PIG LAUNCHER (607-V-603) | HE-ME-410 | HE-ME-460 | SS | Completed | Completed | 3
P2543-R01-Oct24..1.EN.5.5 Pig Launcher/Receiver Length Report | P2543-R01-Oct24..1.EN.5.2.1 Datasheet for PIG RECEIVER (839-V-101) 52" | Issue ICR- Pig Launcher/Receiver Length Report | Issue ICR-Datasheet for PIG RECEIVER (839-V-101) | HE-ME-670 | HE-ME-310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.4 Datasheet for PIG LAUNCHER (607-V-603) 56" | P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | Issue ICR-Datasheet for PIG LAUNCHER (607-V-603) | Issue ICR-Material Requisitions for Pig Launcher/Receiver | HE-ME-460 | HE-ME-480 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.7.10 3D Model | Obtain Company Approval-P&ID's | 90% Model Review | HE-PR-0150 | HE-PI-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | Issue ICR-Design Basis | Issue ICR-MR for Ball valves/ Plug Valves | HE-DB-0010 | HE-PI-1020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | Issue ICR-Piping Material Specifications | Issue ICR-MR for Ball valves/ Plug Valves | HE-PI-0010 | HE-PI-1020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.5 Material Selection Report | P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | Issue ICR - Material Selection Report | Issue ICR-Piping Material Specifications | HE-CP-200 | HE-PI-0010 | FF | Completed | Completed | 5
P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | Issue ICR - Material Selection Diagram | Issue ICR-Piping Material Specifications | HE-CP-0010 | HE-PI-0010 | FF | Completed | Completed | 5
P2543-R01-Oct24..1.EN.3.10 Equipment List | P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | Issue ICR - Equipment List | Issue ICR-Piping Material Specifications | HE-PR-1030 | HE-PI-0010 | FF | Completed | Completed | 5
P2543-R01-Oct24..1.EN.3.17 Line List | P2543-R01-Oct24..1.EN.7.16 Critical line List | Re-Issue for Approval- Line List | Issue ICR-Critical line List | HE-PR-1110 | HE-PI-0262 | FS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.7.4.1 Datasheet for Check Valve | P2543-R01-Oct24..1.EN.7.4.1 Datasheet for Check Valve | Obtain Company Approval-Data sheet for Check Valves | Final Issue for Design/ Construction-Datasheet for Check valves | HE-PI-3610 | HE-PI-3620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.1 Datasheet for Check Valve | P2543-R01-Oct24..1.EN.7.4.1 Datasheet for Check Valve | Re-Issue for Approval-Data sheet for Check Valves | Obtain Company Approval-Data sheet for Check Valves | HE-PI-3600 | HE-PI-3610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.1 Datasheet for Check Valve | P2543-R01-Oct24..1.EN.7.4.1 Datasheet for Check Valve | Issue ICR-Data sheet for Check Valves | Receive Company Comments-Data sheet for Check Valves | HE-PI-3580 | HE-PI-3590 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.1 Datasheet for Check Valve | P2543-R01-Oct24..1.EN.7.4.1 Datasheet for Check Valve | Receive Company Comments-Data sheet for Check Valves | Re-Issue for Approval-Data sheet for Check Valves | HE-PI-3590 | HE-PI-3600 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..1.EN.7.4.1 Datasheet for Check Valve | Issue ICR-Data sheet for Ball Valves | Issue ICR-Data sheet for Check Valves | HE-PI-0900 | HE-PI-3580 | FS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.7.8.1 Material Requisition for Check Valves | P2543-R01-Oct24..1.EN.7.8.1 Material Requisition for Check Valves | Re-Issue for Approval-MR for Check Valves | Obtain Company Approval-MR for Check Valves | HE-PI-3650 | HE-PI-3660 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.1 Material Requisition for Check Valves | P2543-R01-Oct24..1.EN.7.8.1 Material Requisition for Check Valves | Issue ICR-MR for Check Valves | Receive Company Comments-MR for Check Valves | HE-PI-3630 | HE-PI-3640 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.1 Material Requisition for Check Valves | P2543-R01-Oct24..1.EN.7.8.1 Material Requisition for Check Valves | Obtain Company Approval-MR for Check Valves | Final Issue for Design/ Construction-Material Requisition for Check Valves | HE-PI-3660 | HE-PI-3670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.1 Material Requisition for Check Valves | P2543-R01-Oct24..1.EN.7.8.1 Material Requisition for Check Valves | Receive Company Comments-MR for Check Valves | Re-Issue for Approval-MR for Check Valves | HE-PI-3640 | HE-PI-3650 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.1 Datasheet for Check Valve | P2543-R01-Oct24..1.EN.7.8.1 Material Requisition for Check Valves | Final Issue for Design/ Construction-Datasheet for Check valves | Final Issue for Design/ Construction-Material Requisition for Check Valves | HE-PI-3620 | HE-PI-3670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.1 Datasheet for Check Valve | P2543-R01-Oct24..1.EN.7.8.1 Material Requisition for Check Valves | Issue ICR-Data sheet for Check Valves | Issue ICR-MR for Check Valves | HE-PI-3580 | HE-PI-3630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.2 Material Requisition for Piping Special Items | P2543-R01-Oct24..1.EN.7.8.2 Material Requisition for Piping Special Items | Re-Issue for Approval-MR for Piping Special Items | Obtain Company Approval-MR for Piping Special Items | HE-PI-3700 | HE-PI-3710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.2 Material Requisition for Piping Special Items | P2543-R01-Oct24..1.EN.7.8.2 Material Requisition for Piping Special Items | Issue ICR-MR for Piping Special Items | Receive Company Comments-MR for Piping Special Items | HE-PI-3680 | HE-PI-3690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.2 Material Requisition for Piping Special Items | P2543-R01-Oct24..1.EN.7.8.2 Material Requisition for Piping Special Items | Obtain Company Approval-MR for Piping Special Items | Final Issue for Design/ Construction-Material Requisition for Piping Special Items | HE-PI-3710 | HE-PI-3720 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.8.2 Material Requisition for Piping Special Items | P2543-R01-Oct24..1.EN.7.8.2 Material Requisition for Piping Special Items | Receive Company Comments-MR for Piping Special Items | Re-Issue for Approval-MR for Piping Special Items | HE-PI-3690 | HE-PI-3700 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.2.1 TBE for Check Valves | P2543-R01-Oct24..1.EN.7.2.1 TBE for Check Valves | Obtain Company Approval- TBE for Check Valves | Final Issue for Design/ Construction-TBE for Check Valves | HE-PI-3760 | HE-PI-3770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.2.1 TBE for Check Valves | P2543-R01-Oct24..1.EN.7.2.1 TBE for Check Valves | Issue ICR- TBE for Check Valves | Receive Company Comments- TBE for Check Valves | HE-PI-3730 | HE-PI-3740 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.2.1 TBE for Check Valves | P2543-R01-Oct24..1.EN.7.2.1 TBE for Check Valves | Re-Issue for Approval- TBE for Check Valves | Obtain Company Approval- TBE for Check Valves | HE-PI-3750 | HE-PI-3760 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.2.1 TBE for Check Valves | P2543-R01-Oct24..1.EN.7.2.1 TBE for Check Valves | Receive Company Comments- TBE for Check Valves | Re-Issue for Approval- TBE for Check Valves | HE-PI-3740 | HE-PI-3750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.1 Material Requisition for Check Valves | P2543-R01-Oct24..1.EN.7.2.1 TBE for Check Valves | Issue ICR-MR for Check Valves | Issue ICR- TBE for Check Valves | HE-PI-3630 | HE-PI-3730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.2 Material Requisition for Piping Special Items | P2543-R01-Oct24..1.EN.7.2.20 TBE for Piping Special Items | Issue ICR-MR for Piping Special Items | Issue ICR- TBE for Piping Special Items | HE-PI-3680 | HE-PI-1410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.6 Material Requisition for Piping Bulk | P2543-R01-Oct24..1.EN.7.2.20 TBE for Piping Special Items | Final Issue for Design/ Construction-Material Requisition for Piping Bulks & Special Items | Final Issue for Design/ Construction-TBE for Piping Special Items | HE-PI-3570 | HE-PI-1450 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.17 Line List | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Final Issue for Design/ Construction-Line List | HE-PR-0140 | HE-PR-1130 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.8.6 Material Requisition for Piping Bulk | P2543-R01-Oct24..1.EN.7.8.2 Material Requisition for Piping Special Items | Issue ICR-MR for Piping Bulks | Issue ICR-MR for Piping Special Items | HE-PI-3530 | HE-PI-3680 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.7.8.1 Material Requisition for Check Valves | P2543-R01-Oct24..1.EN.7.2.1 TBE for Check Valves | Final Issue for Design/ Construction-Material Requisition for Check Valves | Final Issue for Design/ Construction-TBE for Check Valves | HE-PI-3670 | HE-PI-3770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.2 Material Requisition for Piping Special Items | P2543-R01-Oct24..1.EN.7.2.20 TBE for Piping Special Items | Final Issue for Design/ Construction-Material Requisition for Piping Special Items | Final Issue for Design/ Construction-TBE for Piping Special Items | HE-PI-3720 | HE-PI-1450 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..ML.GE General | Issue Project Execution Plan (PEP), Coordination, Engineering, Procurement, HSE and Quality Procedures-Final Issue | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | ML1001-A01 | ML1149-A07 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Crossing Schedule - 56" | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | HE-PL-2970 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | ML1149-A07 | ML1579-E03 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (56" Pipeline) | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | ML1139-A06 | ML1579-E03 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | NDRC Subcontract Award | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | HS-CN-0090 | ML1579-E03 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | HE-PL-2910 | ML1579-E03 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | NDRC Subcontract Award | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | HS-CN-0090 | ML1679-E13 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Detailed crossing drawings-52" | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | HE-PL-3030 | ML1679-E13 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | ML1149-A07 | ML1679-E13 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.38 Crossing Schedule-52" | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Issue for Design/ Construction-Crossing Schedule-52" | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | HE-PL-3090 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Process | HSE | CAB-4400 | CAB-4410 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | HSE | Civil & Structural | CAB-4410 | CAB-4420 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Civil & Structural | Mechanical | CAB-4420 | CAB-4430 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Mechanical | Piping | CAB-4430 | CAB-4440 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Piping | Electrical | CAB-4440 | CAB-4450 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Electrical | Instrumentation & Control | CAB-4450 | CAB-4460 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Instrumentation & Control | Telecom | CAB-4460 | CAB-4470 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Telecom | Pipeline | CAB-4470 | CAB-4480 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | 90% Model Review Report | Receive Company Comments-Piping Isometrics | HE-PI-0180 | HE-PI-1210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | NDT / PWHT Subcontract Award | Mobilization of Automatic Welding Machines at site | HS-CN-0190 | ML1559-E01 | FS | Completed | Completed | 30
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Line Pipes - Lot 7 (Coated) | Receive at Site - Coated / Painted Line pipes- 52" (100% to total Qty) | HM-PL-0120 | ML1399-D5 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Receive at Site - Coated / Painted Line pipes- 4" (Nitrogen & Water line) | Project Finish | ML1389-D2 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Line Pipes - Lot 9 (Coated) | Receive at Site - Coated / Painted Line pipes- 52" (100% to total Qty) | HM-PL-960 | ML1399-D5 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Receipt at site and inspection of Line Pipes - Lot 7 (Coated) | Receipt at site and inspection of Line Pipes - Lot 9 (Coated) | HM-PL-0120 | HM-PL-960 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Complete 75% Construction & Pre-commissioning | Complete 100% Construction & Pre-commissioning | ML1090 | ML1100 | FF | Not Started | Not Started | 90
P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.1.2.LL.19.1 Ordering | Issue ICR- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | RFQ, Receipt of Bid for FOC Cables | HE-TL-0550 | HP-BK-0060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A3 I/O list | Issue ICR-Instrument index -Update | Issue ICR- I/O list -Update | HE-IC-0490 | HE-IC-0550 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.1.25.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.25.3 Delivery & receipt at Site | Ready for Dispatch of LV Lifting Equipment | Transportation/ Custom Clearance/ Delivery at site of Lifting Equipment | HM-ME-2170 | HM-ME-2190 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.25.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.25.2 Manufacturing & Ready for Dispatch | Factory Acceptance Test of LV Lifting Equipment | Packaging & Final Inspection-LV Lifting Equipment | HM-ME-2150 | HM-ME-2160 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.25.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.25.2 Manufacturing & Ready for Dispatch | Vendor Document Review of Lifting Equipment | Manufacturing & Assembly of LV Lifting Equipment | HM-ME-2180 | HM-ME-2140 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.1.25.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.1.25.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Lifting Equipment | Receipt at site and inspection of Lifting Equipment | HM-ME-2190 | HM-ME-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.25.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.25.2 Manufacturing & Ready for Dispatch | Packaging & Final Inspection-LV Lifting Equipment | Ready for Dispatch of LV Lifting Equipment | HM-ME-2160 | HM-ME-2170 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.25.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.25.2 Manufacturing & Ready for Dispatch | Manufacturing & Assembly of LV Lifting Equipment | Factory Acceptance Test of LV Lifting Equipment | HM-ME-2140 | HM-ME-2150 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.25.24.1 Ordering | P2543-R01-Oct24..PR.26.1.25.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Lifting Equipment | Vendor Document Review of Lifting Equipment | HP-ME-1370 | HM-ME-2180 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.1.BK.10 Modification of Existing CTMM | Issue ICR- Material Requisitions for Field Instruments / H2S Analyzers | RFQ, Receipt of Bid - Modification of Exiting CTMM | HE-IC-1930 | HS-GN-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | Issue ICR- Material Requisitions for Field Instruments / H2S Analyzers | RFQ, Receipt of Bid - Modification of Exiting SMC / SCADA | HE-IC-1930 | HS-GN-0370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.3 TBE for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.1.BK.10 Modification of Existing CTMM | Obtain Company Approval- TBE for Field Instruments / H2S Analyzers | Prepare TBE and Company approval - Modification of Exiting CTMM | HE-IC-2440 | HS-GN-0280 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.3 TBE for Field Instruments / H2S Analyzers | P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | Obtain Company Approval- TBE for Field Instruments / H2S Analyzers | Prepare TBE and Company approval - Modification of Exiting SMC / SCADA | HE-IC-2440 | HS-GN-0400 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..1.EN.8.28 Calculation for Pig launcher and receiver foundations | Issued for Review - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | Issued for Review - Calculation for Pig launcher and receiver foundations | HE-CS-0610 | HE-CS-0550 | SS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | Vendor Document Review of Pig Launchers & Receivers | Issued for Review - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | HM-ME-0410 | HE-CS-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.7 Design Calculation for Typical Shelter | P2543-R01-Oct24..1.EN.8.7 Design Calculation for Typical Shelter | Re-Issue for Approval - Calculations for Shelter | Obtain Company Approval - Calculations for Shelter | HE-CS-1810 | HE-CS-1820 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.7 Design Calculation for Typical Shelter | P2543-R01-Oct24..1.EN.8.7 Design Calculation for Typical Shelter | Obtain Company Approval - Calculations for Shelter | Final Issue for Design/ Construction-Design Calculation for Shelter | HE-CS-1820 | HE-CS-1830 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.7 Design Calculation for Typical Shelter | P2543-R01-Oct24..1.EN.8.7 Design Calculation for Typical Shelter | Issued for Review - Calculations for Shelter | Review Company Comments - Calculations for Shelter | HE-CS-1840 | HE-CS-1850 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.7 Design Calculation for Typical Shelter | P2543-R01-Oct24..1.EN.8.7 Design Calculation for Typical Shelter | Review Company Comments - Calculations for Shelter | Re-Issue for Approval - Calculations for Shelter | HE-CS-1850 | HE-CS-1810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.8 Design Calculation for Typical Valve Pit | P2543-R01-Oct24..1.EN.8.8 Design Calculation for Typical Valve Pit | Re-Issue for Approval - Calculations for Valve Pit | Obtain Company Approval - Calculations for Valve Pit | HE-CS-1860 | HE-CS-1870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.8 Design Calculation for Typical Valve Pit | P2543-R01-Oct24..1.EN.8.8 Design Calculation for Typical Valve Pit | Obtain Company Approval - Calculations for Valve Pit | Final Issue for Design/ Construction-Design Calculation for Valve Pit | HE-CS-1870 | HE-CS-1880 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.8 Design Calculation for Typical Valve Pit | P2543-R01-Oct24..1.EN.8.8 Design Calculation for Typical Valve Pit | Issued for Review - Calculations for Valve Pit | Review Company Comments - Calculations for Valve Pit | HE-CS-1890 | HE-CS-1900 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.8 Design Calculation for Typical Valve Pit | P2543-R01-Oct24..1.EN.8.8 Design Calculation for Typical Valve Pit | Review Company Comments - Calculations for Valve Pit | Re-Issue for Approval - Calculations for Valve Pit | HE-CS-1900 | HE-CS-1860 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.10 Design Calculation for Impact Wall | P2543-R01-Oct24..1.EN.8.10 Design Calculation for Impact Wall | Re-Issue for Approval - Calculations for Impact Wall | Obtain Company Approval - Calculations for Impact Wall | HE-CS-1910 | HE-CS-1920 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.10 Design Calculation for Impact Wall | P2543-R01-Oct24..1.EN.8.10 Design Calculation for Impact Wall | Obtain Company Approval - Calculations for Impact Wall | Final Issue for Design/ Construction-Design Calculation for Impact Wall | HE-CS-1920 | HE-CS-1930 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.10 Design Calculation for Impact Wall | P2543-R01-Oct24..1.EN.8.10 Design Calculation for Impact Wall | Issued for Review - Calculations for Impact Wall | Review Company Comments - Calculations for Impact Wall | HE-CS-1940 | HE-CS-1950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.10 Design Calculation for Impact Wall | P2543-R01-Oct24..1.EN.8.10 Design Calculation for Impact Wall | Review Company Comments - Calculations for Impact Wall | Re-Issue for Approval - Calculations for Impact Wall | HE-CS-1950 | HE-CS-1910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.7 Design Calculation for Typical Shelter | P2543-R01-Oct24..1.EN.8.8 Design Calculation for Typical Valve Pit | Issued for Review - Calculations for Shelter | Issued for Review - Calculations for Valve Pit | HE-CS-1840 | HE-CS-1890 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.8.8 Design Calculation for Typical Valve Pit | P2543-R01-Oct24..1.EN.8.10 Design Calculation for Impact Wall | Issued for Review - Calculations for Valve Pit | Issued for Review - Calculations for Impact Wall | HE-CS-1890 | HE-CS-1940 | FS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.8.10 Design Calculation for Impact Wall | P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | Final Issue for Design/ Construction-Design Calculation for Impact Wall | Final Issue for Design/ Construction-TYPICAL GA AND RC DETAILS OF IMPACT WALL | HE-CS-1930 | HE-CS-1250 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.8.8 Design Calculation for Typical Valve Pit | P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | Final Issue for Design/ Construction-Design Calculation for Valve Pit | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | HE-CS-1880 | HE-CS-1190 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.8.7 Design Calculation for Typical Shelter | P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | Final Issue for Design/ Construction-Design Calculation for Shelter | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | HE-CS-1830 | HE-CS-1310 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.7 Design Calculation for Typical Shelter | P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | Issued for Review - Calculations for Shelter | Issued for Review - Passive cooled shelter foundation GA and details | HE-CS-1840 | HE-CS-1270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.10 Design Calculation for Impact Wall | P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | Issued for Review - Calculations for Impact Wall | Issued for Review - Impact Wall GA and RC (type) details | HE-CS-1940 | HE-CS-1210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.18 Design Calculation for Jib crane Foundation | P2543-R01-Oct24..1.EN.8.18 Design Calculation for Jib crane Foundation | Issued for Review - Design Cal. for Jib Crane Foundations | Review Company Comments - Design Cal. for Jib Crane Foundations | HE-CS-1990 | HE-CS-2000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.18 Design Calculation for Jib crane Foundation | P2543-R01-Oct24..1.EN.8.18 Design Calculation for Jib crane Foundation | Obtain Company Approval - Design Cal. for Jib Crane Foundations | Final Issue for Design/ Construction-Design Calculation for Jib Crane Foundations | HE-CS-1970 | HE-CS-1980 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.18 Design Calculation for Jib crane Foundation | P2543-R01-Oct24..1.EN.8.18 Design Calculation for Jib crane Foundation | Re-Issue for Approval - Design Cal. for Jib Crane Foundations | Obtain Company Approval - Design Cal. for Jib Crane Foundations | HE-CS-1960 | HE-CS-1970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.18 Design Calculation for Jib crane Foundation | P2543-R01-Oct24..1.EN.8.18 Design Calculation for Jib crane Foundation | Review Company Comments - Design Cal. for Jib Crane Foundations | Re-Issue for Approval - Design Cal. for Jib Crane Foundations | HE-CS-2000 | HE-CS-1960 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.19 Design Calculation for Filter Package Foundation | P2543-R01-Oct24..1.EN.8.19 Design Calculation for Filter Package Foundation | Issued for Review - Design Cal. for Filter Package | Review Company Comments - Design Cal. for Filter Package | HE-CS-2040 | HE-CS-2050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.19 Design Calculation for Filter Package Foundation | P2543-R01-Oct24..1.EN.8.19 Design Calculation for Filter Package Foundation | Obtain Company Approval - Design Cal. for Filter Package | Final Issue for Design/ Construction-Design Calculation for Filter Package | HE-CS-2020 | HE-CS-2030 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.19 Design Calculation for Filter Package Foundation | P2543-R01-Oct24..1.EN.8.19 Design Calculation for Filter Package Foundation | Re-Issue for Approval - Design Cal. for Filter Package | Obtain Company Approval - Design Cal. for Filter Package | HE-CS-2010 | HE-CS-2020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.19 Design Calculation for Filter Package Foundation | P2543-R01-Oct24..1.EN.8.19 Design Calculation for Filter Package Foundation | Review Company Comments - Design Cal. for Filter Package | Re-Issue for Approval - Design Cal. for Filter Package | HE-CS-2050 | HE-CS-2010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.26 Design Calculation for Typical Lighting Pole Foundations | P2543-R01-Oct24..1.EN.8.26 Design Calculation for Typical Lighting Pole Foundations | Issued for Review - Design Cal. for Typical Lighting Pole Foundations | Review Company Comments - Design Cal. for Typical Lighting Pole Foundations | HE-CS-2090 | HE-CS-2100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.26 Design Calculation for Typical Lighting Pole Foundations | P2543-R01-Oct24..1.EN.8.26 Design Calculation for Typical Lighting Pole Foundations | Obtain Company Approval - Design Cal. for Typical Lighting Pole Foundations | Final Issue for Design/ Construction-Design Calculation for Typical Lighting Pole Foundations | HE-CS-2070 | HE-CS-2080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.26 Design Calculation for Typical Lighting Pole Foundations | P2543-R01-Oct24..1.EN.8.26 Design Calculation for Typical Lighting Pole Foundations | Re-Issue for Approval - Design Cal. for Typical Lighting Pole Foundations | Obtain Company Approval - Design Cal. for Typical Lighting Pole Foundations | HE-CS-2060 | HE-CS-2070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.26 Design Calculation for Typical Lighting Pole Foundations | P2543-R01-Oct24..1.EN.8.26 Design Calculation for Typical Lighting Pole Foundations | Review Company Comments - Design Cal. for Typical Lighting Pole Foundations | Re-Issue for Approval - Design Cal. for Typical Lighting Pole Foundations | HE-CS-2100 | HE-CS-2060 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.24 Design Calculation for Typical Skid Foundations | P2543-R01-Oct24..1.EN.8.26 Design Calculation for Typical Lighting Pole Foundations | Issued for Review - Design Cal. for Typical Skid Foundations | Issued for Review - Design Cal. for Typical Lighting Pole Foundations | HE-CS-0670 | HE-CS-2090 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.8.26 Design Calculation for Typical Lighting Pole Foundations | P2543-R01-Oct24..1.EN.8.18 Design Calculation for Jib crane Foundation | Issued for Review - Design Cal. for Typical Lighting Pole Foundations | Issued for Review - Design Cal. for Jib Crane Foundations | HE-CS-2090 | HE-CS-1990 | FS | Completed | Completed | 30
P2543-R01-Oct24..1.EN.8.18 Design Calculation for Jib crane Foundation | P2543-R01-Oct24..1.EN.8.19 Design Calculation for Filter Package Foundation | Issued for Review - Design Cal. for Jib Crane Foundations | Issued for Review - Design Cal. for Filter Package | HE-CS-1990 | HE-CS-2040 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.8.26 Design Calculation for Typical Lighting Pole Foundations | P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | Issued for Review - Design Cal. for Typical Lighting Pole Foundations | Issued for Review - Lighting pole foundation details | HE-CS-2090 | HE-CS-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.26 Design Calculation for Typical Lighting Pole Foundations | P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | Final Issue for Design/ Construction-Design Calculation for Typical Lighting Pole Foundations | Final Issue for Design/ Construction-TYPICAL LIGHTING POLE FOUNDATION DETAILS | HE-CS-2080 | HE-CS-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.18 Design Calculation for Jib crane Foundation | P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | Issued for Review - Design Cal. for Jib Crane Foundations | Issued for Review - Typical Detailed Drawing - Jib Crane Foundation | HE-CS-1990 | HE-CS-1030 | FF | Completed | Completed | 20
P2543-R01-Oct24..1.EN.8.19 Design Calculation for Filter Package Foundation | P2543-R01-Oct24..1.EN.8.33 Filter Foundation GA and Details | Issued for Review - Design Cal. for Filter Package | Issued for Review - Typical Spill Pit General Arrangement And RC (type) Details | HE-CS-2040 | HE-CS-0910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.19 Design Calculation for Filter Package Foundation | P2543-R01-Oct24..1.EN.8.33 Filter Foundation GA and Details | Final Issue for Design/ Construction-Design Calculation for Filter Package | Final Issue for Design/ Construction-FILTER FOUNDATION GA AND DETAILS | HE-CS-2030 | HE-CS-0950 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A23 F&G Index | Final Issue for Design/ Construction-Instrument Index | Final Issue for Design/ Construction-F&G Index | HE-IC-0530 | HE-IC-2740 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.4.5 F&G layout | P2543-R01-Oct24..1.EN.6.A2 Instrument Index | Issue ICR-F&G Layout | Issue ICR-Instrument index -Update | HE-HS-0250 | HE-IC-0490 | FS | Completed | Completed | 15
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A23 F&G Index | Issue ICR-Instrument index -Update | Issue ICR-F&G index -Update | HE-IC-0490 | HE-IC-2750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | P2543-R01-Oct24..1.EN.6.A181 Instrument and F&G interconnection Wiring Diagram | Commercial Clarifications & Placement of PO - Modification of Exiting SMC / SCADA | Issue ICR - interconnection Wiring Diagram | HS-GN-0410 | HE-IC-2790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.LL.18.1 Ordering | P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | Commercial Clarifications & Placement of PO for Gas Detectors | Issue ICR - Typical Installation Drawings | HP-ME-0730 | HE-IC-0670 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.15.1 Ordering | P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | Commercial Clarifications & Placement of PO for Field Instruments | Issue ICR - Typical Installation Drawings | HP-ME-0780 | HE-IC-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Issue ICR- Specification for Leak Detection System | Issue ICR- Instrument location and Cable Routing Drawings | HE-IC-0250 | HE-IC-2530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.11.7 Material Requisitions for Junction Boxes | Issue ICR- Specification for Leak Detection System | Issue ICR- Material Requisitions for Junction Boxes | HE-IC-0250 | HE-IC-1990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Issue ICR- Specification for RTU | Issue ICR- Instrument location and Cable Routing Drawings | HE-IC-0190 | HE-IC-2530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.11.7 Material Requisitions for Junction Boxes | Issue ICR- Specification for RTU | Issue ICR- Material Requisitions for Junction Boxes | HE-IC-0190 | HE-IC-1990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Issue ICR- Instrument Cable Block Diagram | Issue ICR-Instrument Trench Layout | HE-IC-0790 | HE-IC-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Issue ICR- Instrument Cable Block Diagram | Issue ICR-Instrument and F&G Cable Schedule | HE-IC-0790 | HE-IC-0910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Issue ICR- Specification for Leak Detection System | Issue ICR-Instrument Trench Layout | HE-IC-0250 | HE-IC-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Issue ICR- Specification for Leak Detection System | Issue ICR-Instrument and F&G Cable Schedule | HE-IC-0250 | HE-IC-0910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Issue ICR- Specification for RTU | Issue ICR-Instrument Trench Layout | HE-IC-0190 | HE-IC-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Issue ICR- Specification for RTU | Issue ICR-Instrument and F&G Cable Schedule | HE-IC-0190 | HE-IC-0910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Re-Issue for Approval- I/O list -Update | Re-Issue for Approval- Instrument location and Cable Routing Drawings | HE-IC-0570 | HE-IC-2550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Re-Issue for Approval- I/O list -Update | Re-Issue for Approval - Loop Diagrams | HE-IC-0570 | HE-IC-0750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Re-Issue for Approval- Specification for RTU | Re-Issue for Approval- Instrument location and Cable Routing Drawings | HE-IC-0210 | HE-IC-2550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Re-Issue for Approval- Specification for RTU | Re-Issue for Approval - Loop Diagrams | HE-IC-0210 | HE-IC-0750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Re-Issue for Approval- Specification for Leak Detection System | Re-Issue for Approval- Instrument location and Cable Routing Drawings | HE-IC-0270 | HE-IC-2550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Re-Issue for Approval- Specification for Leak Detection System | Re-Issue for Approval - Loop Diagrams | HE-IC-0270 | HE-IC-0750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Issue ICR- Instrument Cable Block Diagram | Re-Issue for Approval- Instrument location and Cable Routing Drawings | HE-IC-0790 | HE-IC-2550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Issue ICR- Instrument Cable Block Diagram | Re-Issue for Approval - Loop Diagrams | HE-IC-0790 | HE-IC-0750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Issue ICR- Specification for Leak Detection System | Re-Issue for Approval- Instrument location and Cable Routing Drawings | HE-IC-0250 | HE-IC-2550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Issue ICR- Specification for Leak Detection System | Re-Issue for Approval - Loop Diagrams | HE-IC-0250 | HE-IC-0750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Issue ICR- Specification for RTU | Re-Issue for Approval- Instrument location and Cable Routing Drawings | HE-IC-0190 | HE-IC-2550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Issue ICR- Specification for RTU | Re-Issue for Approval - Loop Diagrams | HE-IC-0190 | HE-IC-0750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Re-Issue for Approval- I/O list -Update | Re-Issue for Approval-Instrument and F&G Cable Schedule | HE-IC-0570 | HE-IC-0930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Re-Issue for Approval- I/O list -Update | Re-Issue for Approval-Instrument Trench Layout | HE-IC-0570 | HE-IC-0990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Re-Issue for Approval- Specification for RTU | Re-Issue for Approval-Instrument and F&G Cable Schedule | HE-IC-0210 | HE-IC-0930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Re-Issue for Approval- Specification for RTU | Re-Issue for Approval-Instrument Trench Layout | HE-IC-0210 | HE-IC-0990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Re-Issue for Approval- Specification for Leak Detection System | Re-Issue for Approval-Instrument and F&G Cable Schedule | HE-IC-0270 | HE-IC-0930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Re-Issue for Approval- Specification for Leak Detection System | Re-Issue for Approval-Instrument Trench Layout | HE-IC-0270 | HE-IC-0990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Issue ICR- Instrument Cable Block Diagram | Re-Issue for Approval-Instrument and F&G Cable Schedule | HE-IC-0790 | HE-IC-0930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Issue ICR- Instrument Cable Block Diagram | Re-Issue for Approval-Instrument Trench Layout | HE-IC-0790 | HE-IC-0990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Issue ICR- Specification for Leak Detection System | Re-Issue for Approval-Instrument and F&G Cable Schedule | HE-IC-0250 | HE-IC-0930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Issue ICR- Specification for Leak Detection System | Re-Issue for Approval-Instrument Trench Layout | HE-IC-0250 | HE-IC-0990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Issue ICR- Specification for RTU | Re-Issue for Approval-Instrument and F&G Cable Schedule | HE-IC-0190 | HE-IC-0930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Issue ICR- Specification for RTU | Re-Issue for Approval-Instrument Trench Layout | HE-IC-0190 | HE-IC-0990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Final Issue for Design/ Construction-Specification for RTU | Final Issue for Design/ Construction-Instrument Trench Layout | HE-IC-0230 | HE-IC-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Final Issue for Design/ Construction-Specification for RTU | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | HE-IC-0230 | HE-IC-0950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Final Issue for Design/ Construction-Specification for RTU | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | HE-IC-0230 | HE-IC-2570 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Final Issue for Design/ Construction-Specification for RTU | Final Issue for Design/ Construction-Loop Diagrams | HE-IC-0230 | HE-IC-0770 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Final Issue for Design/ Construction-Specification for Leak Detection System | Final Issue for Design/ Construction-Instrument Trench Layout | HE-IC-0290 | HE-IC-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Final Issue for Design/ Construction-Specification for Leak Detection System | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | HE-IC-0290 | HE-IC-0950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Final Issue for Design/ Construction-Specification for Leak Detection System | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | HE-IC-0290 | HE-IC-2570 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Final Issue for Design/ Construction-Specification for Leak Detection System | Final Issue for Design/ Construction-Loop Diagrams | HE-IC-0290 | HE-IC-0770 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Re-Issue for Approval- I/O list -Update | Final Issue for Design/ Construction-Instrument Trench Layout | HE-IC-0570 | HE-IC-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Re-Issue for Approval- I/O list -Update | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | HE-IC-0570 | HE-IC-0950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Re-Issue for Approval- I/O list -Update | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | HE-IC-0570 | HE-IC-2570 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Re-Issue for Approval- I/O list -Update | Final Issue for Design/ Construction-Loop Diagrams | HE-IC-0570 | HE-IC-0770 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Re-Issue for Approval- I/O list -Update | Instrumentation & Control | HE-IC-0570 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Re-Issue for Approval- Specification for RTU | Final Issue for Design/ Construction-Instrument Trench Layout | HE-IC-0210 | HE-IC-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Re-Issue for Approval- Specification for RTU | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | HE-IC-0210 | HE-IC-0950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Re-Issue for Approval- Specification for RTU | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | HE-IC-0210 | HE-IC-2570 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Re-Issue for Approval- Specification for RTU | Final Issue for Design/ Construction-Loop Diagrams | HE-IC-0210 | HE-IC-0770 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Re-Issue for Approval- Specification for RTU | Instrumentation & Control | HE-IC-0210 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Re-Issue for Approval- Specification for Leak Detection System | Final Issue for Design/ Construction-Instrument Trench Layout | HE-IC-0270 | HE-IC-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Re-Issue for Approval- Specification for Leak Detection System | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | HE-IC-0270 | HE-IC-0950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Re-Issue for Approval- Specification for Leak Detection System | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | HE-IC-0270 | HE-IC-2570 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Re-Issue for Approval- Specification for Leak Detection System | Final Issue for Design/ Construction-Loop Diagrams | HE-IC-0270 | HE-IC-0770 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Re-Issue for Approval- Specification for Leak Detection System | Instrumentation & Control | HE-IC-0270 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Issue ICR- Instrument Cable Block Diagram | Final Issue for Design/ Construction-Instrument Trench Layout | HE-IC-0790 | HE-IC-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Issue ICR- Instrument Cable Block Diagram | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | HE-IC-0790 | HE-IC-0950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Issue ICR- Instrument Cable Block Diagram | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | HE-IC-0790 | HE-IC-2570 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Issue ICR- Instrument Cable Block Diagram | Final Issue for Design/ Construction-Loop Diagrams | HE-IC-0790 | HE-IC-0770 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- Instrument Cable Block Diagram | Instrumentation & Control | HE-IC-0790 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Issue ICR- Specification for Leak Detection System | Final Issue for Design/ Construction-Instrument Trench Layout | HE-IC-0250 | HE-IC-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Issue ICR- Specification for Leak Detection System | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | HE-IC-0250 | HE-IC-0950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Issue ICR- Specification for Leak Detection System | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | HE-IC-0250 | HE-IC-2570 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Issue ICR- Specification for Leak Detection System | Final Issue for Design/ Construction-Loop Diagrams | HE-IC-0250 | HE-IC-0770 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Issue ICR- Specification for RTU | Final Issue for Design/ Construction-Instrument Trench Layout | HE-IC-0190 | HE-IC-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Issue ICR- Specification for RTU | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | HE-IC-0190 | HE-IC-0950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Issue ICR- Specification for RTU | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | HE-IC-0190 | HE-IC-2570 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | Issue ICR- Specification for RTU | Final Issue for Design/ Construction-Loop Diagrams | HE-IC-0190 | HE-IC-0770 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Issue ICR- Instrument Cable Block Diagram | Issue ICR-Instrument and F&G Cable Schedule | HE-IC-0790 | HE-IC-0910 | FF | Completed | Completed | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | 60% Model Review | Issue ICR-Instrument and F&G Cable Schedule | ML2069-B09 | HE-IC-0910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | Issue ICR-Instrument and F&G Cable Schedule | Issue ICR-Instrument Trench Layout | HE-IC-0910 | HE-IC-0970 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Issue ICR- P&ID's | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-PR-0110 | C-COM-790 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | Issue ICR- P&ID's | Issue ICR - Hook-Up Diagram | HE-PR-0110 | HE-IC-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | Issue ICR- P&ID's | Issue ICR- Datasheets for F&G Devices | HE-PR-0110 | HE-IC-1510 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Issue ICR- P&ID's | Issue ICR- Instrument location and Cable Routing Drawings | HE-PR-0110 | HE-IC-2530 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | Issue ICR- P&ID's | Issue ICR - Typical Installation Drawings | HE-PR-0110 | HE-IC-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- P&ID's | Instrumentation & Control | HE-PR-0110 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Issue ICR- P&ID's | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-PR-0110 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | Issue ICR- P&ID's | Re-Issue for Approval - Typical Installation Drawings | HE-PR-0110 | HE-IC-0690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Issue ICR- P&ID's | Re-Issue for Approval- FOC Block diagram (Telecom) | HE-PR-0110 | HE-TL-0450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Issue ICR- P&ID's | Instrument 2nd MTO | HE-PR-0110 | HE-IC-2610 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Issue ICR- P&ID's | Re-Issue for Approval- Telecom Tie-in Block Diagram | HE-PR-0110 | HE-TL-0390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A3 I/O list | Issue ICR- P&ID's | Re-Issue for Approval- I/O list -Update | HE-PR-0110 | HE-IC-0570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- P&ID's | Re-Issue for Approval- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-PR-0110 | HE-TL-0270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Issue ICR- P&ID's | Re-Issue for Approval- Overall Telecom Block Diagram | HE-PR-0110 | HE-TL-0330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | Issue ICR- P&ID's | Re-Issue for Approval - Hook-Up Diagram | HE-PR-0110 | HE-IC-0630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | Issue ICR- P&ID's | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | HE-PR-0110 | HE-IC-2570 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | Issue ICR- P&ID's | Final Issue for Design/ Construction-Datasheets for Field Instruments / H2S Analyzers | HE-PR-0110 | HE-IC-1490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Issue ICR- P&ID's | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | HE-PR-0110 | HE-TL-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Issue ICR- P&ID's | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | HE-PR-0110 | HE-TL-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- P&ID's | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-PR-0110 | HE-TL-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Issue ICR- P&ID's | Final Issue for Design/ Construction-Overall Telecom Block Diagram | HE-PR-0110 | HE-TL-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A3 I/O list | Issue ICR- P&ID's | Final Issue for Design/ Construction-I/O list | HE-PR-0110 | HE-IC-0590 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Issue ICR- P&ID's | Instrument 3rd MTO | HE-PR-0110 | HE-IC-2630 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | Issue ICR- P&ID's | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | HE-PR-0110 | HE-IC-1550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | Issue ICR- P&ID's | Final Issue for Design/ Construction-Hook-Up Diagram | HE-PR-0110 | HE-IC-0650 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | Issue ICR- P&ID's | Final Issue for Design/ Construction-Typical Installation Drawings | HE-PR-0110 | HE-IC-0710 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | Issue ICR- Datasheet for Plug Valves | Issue ICR- Datasheet for GOV & ROV | HE-PI-0960 | HE-IC-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | Final Issue for Design/ Construction-Piping Material Specification | Final Issue for Design/ Construction-Actuator Datasheet for GOV & ROV | HE-PI-0050 | HE-IC-1130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.2 Datasheet for Plug valves | P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | Issue ICR- Datasheet for Plug Valves | Issue ICR- Datasheets for Metering Skid | HE-PI-0960 | HE-IC-1150 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Datasheets for Custody Flow Metering Skid | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-IC-1190 | C-COM-790 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Data sheet for PRS (Pressure Reduction System) | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-IC-1250 | C-COM-790 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Issue ICR-Data sheet for Ball Valves | Issue ICR-Material Requisitions for Leak Detection System | HE-PI-0900 | HE-IC-1750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Issue ICR- P&ID's | Issue ICR-Material Requisitions for Leak Detection System | HE-PR-0110 | HE-IC-1750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Issue ICR- Specification for Leak Detection System | Issue ICR-Material Requisitions for Leak Detection System | HE-IC-0250 | HE-IC-1750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Issue ICR- HAZOP reviews Report for all areas | Re-Issue for Approval-Material Requisitions for Leak Detection System | HE-HS-0670 | HE-IC-1770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Issue ICR-Data sheet for Ball Valves | Re-Issue for Approval-Material Requisitions for Leak Detection System | HE-PI-0900 | HE-IC-1770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Issue ICR- P&ID's | Re-Issue for Approval-Material Requisitions for Leak Detection System | HE-PR-0110 | HE-IC-1770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Issue ICR- Specification for Leak Detection System | Re-Issue for Approval-Material Requisitions for Leak Detection System | HE-IC-0250 | HE-IC-1770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Issue ICR- HAZOP reviews Report for all areas | Final Issue for Design/ Construction-Data sheet for PRS (Pressure Reduction System) | HE-HS-0670 | HE-IC-1250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Issue ICR-Data sheet for Ball Valves | Final Issue for Design/ Construction-Data sheet for PRS (Pressure Reduction System) | HE-PI-0900 | HE-IC-1250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Issue ICR- P&ID's | Final Issue for Design/ Construction-Data sheet for PRS (Pressure Reduction System) | HE-PR-0110 | HE-IC-1250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Issue ICR- Specification for Leak Detection System | Final Issue for Design/ Construction-Data sheet for PRS (Pressure Reduction System) | HE-IC-0250 | HE-IC-1250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Final Issue for Design/ Construction-Process Datasheets - PRS Skid (at Sweihan CRS) | Final Issue for Design/ Construction-Material Requisitions for Leak Detection System | HE-PR-0410 | HE-IC-1790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Process Datasheets - PRS Skid (at Sweihan CRS) | Instrumentation & Control | HE-PR-0410 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Final Issue for Design/ Construction-Specification for Leak Detection System | Final Issue for Design/ Construction-Material Requisitions for Leak Detection System | HE-IC-0290 | HE-IC-1790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Final Issue for Design/ Construction-Addendum to DGs | Final Issue for Design/ Construction-Material Requisitions for Leak Detection System | HE-IC-0050 | HE-IC-1790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Issue ICR- HAZOP reviews Report for all areas | Final Issue for Design/ Construction-Material Requisitions for Leak Detection System | HE-HS-0670 | HE-IC-1790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- HAZOP reviews Report for all areas | Instrumentation & Control | HE-HS-0670 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Issue ICR-Data sheet for Ball Valves | Final Issue for Design/ Construction-Material Requisitions for Leak Detection System | HE-PI-0900 | HE-IC-1790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR-Data sheet for Ball Valves | Instrumentation & Control | HE-PI-0900 | CAB-4460 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Issue ICR- P&ID's | Final Issue for Design/ Construction-Material Requisitions for Leak Detection System | HE-PR-0110 | HE-IC-1790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Issue ICR- Specification for Leak Detection System | Final Issue for Design/ Construction-Material Requisitions for Leak Detection System | HE-IC-0250 | HE-IC-1790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | Issue ICR- Datasheets for PSV & Orifice (incl. RO) | Issue ICR- Material Requisitions for Field Instruments / H2S Analyzers | HE-IC-1330 | HE-IC-1930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Datasheets for PSV & Orifice (incl. RO) | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-IC-1370 | C-COM-790 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..1.EN.6.11.43 Material Requisition for Pig Signaler | Issue ICR-Datasheets for Pig Signalers | Issue ICR- Material Requisition for Pig Signaler | HE-IC-1390 | HE-PL-1930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.1 Material Requisitions for RTU & SCADA Modification | P2543-R01-Oct24..1.EN.6.11.1 Material Requisitions for RTU & SCADA Modification | Re-Issue for Approval- Material Requisitions for RTU & SCADA Modification | Obtain Company Approval- Material Requisitions for RTU & SCADA Modification | HE-IC-2850 | HE-IC-2870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.1 Material Requisitions for RTU & SCADA Modification | P2543-R01-Oct24..1.EN.6.11.1 Material Requisitions for RTU & SCADA Modification | Receive Company Comments- Material Requisitions for RTU & SCADA Modification | Re-Issue for Approval- Material Requisitions for RTU & SCADA Modification | HE-IC-2840 | HE-IC-2850 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.1 Material Requisitions for RTU & SCADA Modification | P2543-R01-Oct24..1.EN.6.11.1 Material Requisitions for RTU & SCADA Modification | Issue ICR- Material Requisitions for RTU & SCADA Modification | Receive Company Comments- Material Requisitions for RTU & SCADA Modification | HE-IC-2880 | HE-IC-2840 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.1 Material Requisitions for RTU & SCADA Modification | P2543-R01-Oct24..1.EN.6.11.1 Material Requisitions for RTU & SCADA Modification | Obtain Company Approval- Material Requisitions for RTU & SCADA Modification | Final Issue for Design/ Construction-Material Requisitions for RTU & SCADA Modification | HE-IC-2870 | HE-IC-2860 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.1 TBE for RTU & SCADA Modification | P2543-R01-Oct24..1.EN.6.2.1 TBE for RTU & SCADA Modification | Obtain Company Approval- TBE for RTU & SCADA Modification | Final Issue for Design/ Construction-TBE for RTU & SCADA Modification | HE-IC-2930 | HE-IC-2890 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.2.1 TBE for RTU & SCADA Modification | P2543-R01-Oct24..1.EN.6.2.1 TBE for RTU & SCADA Modification | Re-Issue for Approval- TBE for RTU & SCADA Modification | Obtain Company Approval- TBE for RTU & SCADA Modification | HE-IC-2920 | HE-IC-2930 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.1 TBE for RTU & SCADA Modification | P2543-R01-Oct24..1.EN.6.2.1 TBE for RTU & SCADA Modification | Receive Company Comments- TBE for RTU & SCADA Modification | Re-Issue for Approval- TBE for RTU & SCADA Modification | HE-IC-2910 | HE-IC-2920 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.1 TBE for RTU & SCADA Modification | P2543-R01-Oct24..1.EN.6.2.1 TBE for RTU & SCADA Modification | Issue ICR- TBE for RTU & SCADA Modification | Receive Company Comments- TBE for RTU & SCADA Modification | HE-IC-2900 | HE-IC-2910 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.1 TBE for RTU & SCADA Modification | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-TBE for RTU & SCADA Modification | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | HE-IC-2890 | C-COM-790 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | P2543-R01-Oct24..1.EN.6.2.1 TBE for RTU & SCADA Modification | RFQ, Receipt of Bid - Modification of Exiting SMC / SCADA | Issue ICR- TBE for RTU & SCADA Modification | HS-GN-0370 | HE-IC-2900 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.1 Material Requisitions for RTU & SCADA Modification | P2543-R01-Oct24..1.EN.6.2.1 TBE for RTU & SCADA Modification | Final Issue for Design/ Construction-Material Requisitions for RTU & SCADA Modification | Final Issue for Design/ Construction-TBE for RTU & SCADA Modification | HE-IC-2860 | HE-IC-2890 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.11.1 Material Requisitions for RTU & SCADA Modification | P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | Issue ICR- Material Requisitions for RTU & SCADA Modification | RFQ, Receipt of Bid - Modification of Exiting SMC / SCADA | HE-IC-2880 | HS-GN-0370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.11.1 Material Requisitions for RTU & SCADA Modification | Issue ICR- I/O list -Update | Issue ICR- Material Requisitions for RTU & SCADA Modification | HE-IC-0550 | HE-IC-2880 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.6.11.1 Material Requisitions for RTU & SCADA Modification | Issue ICR- Specification for RTU | Issue ICR- Material Requisitions for RTU & SCADA Modification | HE-IC-0190 | HE-IC-2880 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | Re-Issue for Approval-Design Basis | Issue ICR-Design Basis | HE-DB-0030 | HE-TL-2490 | FS | Completed | Completed | 2
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Issue ICR- Specification for RTU | Issue ICR- Telecom Tie-in Block Diagram | HE-IC-0190 | HE-TL-0370 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Issue ICR- Specification for RTU | Issue ICR- Telecom Cable Schedule | HE-IC-0190 | HE-TL-0790 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for RTU | Issue ICR- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-0190 | HE-TL-0550 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Issue ICR- Specification for RTU | Issue ICR- Overall Telecom Block Diagram | HE-IC-0190 | HE-TL-0310 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Issue ICR- Specification for RTU | Issue ICR- FOC Block diagram (Telecom) | HE-IC-0190 | HE-TL-0430 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for RTU | Issue ICR- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-IC-0190 | HE-TL-0250 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Issue ICR- Specification for Leak Detection System | Issue ICR- Telecom Tie-in Block Diagram | HE-IC-0250 | HE-TL-0370 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Issue ICR- Specification for Leak Detection System | Issue ICR- Telecom Cable Schedule | HE-IC-0250 | HE-TL-0790 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for Leak Detection System | Issue ICR- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-0250 | HE-TL-0550 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Issue ICR- Specification for Leak Detection System | Issue ICR- Overall Telecom Block Diagram | HE-IC-0250 | HE-TL-0310 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Issue ICR- Specification for Leak Detection System | Issue ICR- FOC Block diagram (Telecom) | HE-IC-0250 | HE-TL-0430 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for Leak Detection System | Issue ICR- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-IC-0250 | HE-TL-0250 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Issue ICR- Specification for RTU | Re-Issue for Approval- FOC Block diagram (Telecom) | HE-IC-0190 | HE-TL-0450 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for RTU | Re-Issue for Approval- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-0190 | HE-TL-0510 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | Issue ICR- Specification for RTU | Issue ICR- Power Consumption Calculation (Instrumentation) | HE-IC-0190 | HE-EL-5440 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Issue ICR- Specification for RTU | Re-Issue for Approval- Telecom Tie-in Block Diagram | HE-IC-0190 | HE-TL-0390 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for RTU | Re-Issue for Approval- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-0190 | HE-TL-0570 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Issue ICR- Specification for RTU | Re-Issue for Approval- Overall Telecom Block Diagram | HE-IC-0190 | HE-TL-0330 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for RTU | Re-Issue for Approval- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-IC-0190 | HE-TL-0270 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Issue ICR- Specification for Leak Detection System | Re-Issue for Approval- FOC Block diagram (Telecom) | HE-IC-0250 | HE-TL-0450 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for Leak Detection System | Re-Issue for Approval- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-0250 | HE-TL-0510 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.9.A37 Power Consumption Calculation (Instrumentation) | Issue ICR- Specification for Leak Detection System | Issue ICR- Power Consumption Calculation (Instrumentation) | HE-IC-0250 | HE-EL-5440 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Issue ICR- Specification for Leak Detection System | Re-Issue for Approval- Telecom Tie-in Block Diagram | HE-IC-0250 | HE-TL-0390 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for Leak Detection System | Re-Issue for Approval- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-0250 | HE-TL-0570 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Issue ICR- Specification for Leak Detection System | Re-Issue for Approval- Overall Telecom Block Diagram | HE-IC-0250 | HE-TL-0330 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for Leak Detection System | Re-Issue for Approval- Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-IC-0250 | HE-TL-0270 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Final Issue for Design/ Construction-Specification for Leak Detection System | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | HE-IC-0290 | HE-TL-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Final Issue for Design/ Construction-Specification for Leak Detection System | Final Issue for Design/ Construction-Overall Telecom Block Diagram | HE-IC-0290 | HE-TL-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Final Issue for Design/ Construction-Specification for Leak Detection System | Final Issue for Design/ Construction-Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc. | HE-IC-0290 | HE-TL-0590 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Specification for Leak Detection System | Telecom | HE-IC-0290 | CAB-4470 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Final Issue for Design/ Construction-Specification for Leak Detection System | Final Issue for Design/ Construction-Telecom cable schedule | HE-IC-0290 | HE-TL-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Final Issue for Design/ Construction-Specification for Leak Detection System | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | HE-IC-0290 | HE-TL-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Final Issue for Design/ Construction-Specification for Leak Detection System | Final Issue for Design/ Construction-Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-0290 | HE-TL-0530 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Specification for Leak Detection System | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | HE-IC-0290 | ML1033-B22 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Final Issue for Design/ Construction-Specification for Leak Detection System | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-IC-0290 | HE-TL-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Final Issue for Design/ Construction-Specification for RTU | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | HE-IC-0230 | HE-TL-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Final Issue for Design/ Construction-Specification for RTU | Final Issue for Design/ Construction-Overall Telecom Block Diagram | HE-IC-0230 | HE-TL-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Final Issue for Design/ Construction-Specification for RTU | Final Issue for Design/ Construction-Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc. | HE-IC-0230 | HE-TL-0590 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Specification for RTU | Telecom | HE-IC-0230 | CAB-4470 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Final Issue for Design/ Construction-Specification for RTU | Final Issue for Design/ Construction-Telecom cable schedule | HE-IC-0230 | HE-TL-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Final Issue for Design/ Construction-Specification for RTU | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | HE-IC-0230 | HE-TL-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Final Issue for Design/ Construction-Specification for RTU | Final Issue for Design/ Construction-Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-0230 | HE-TL-0530 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Specification for RTU | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | HE-IC-0230 | ML1033-B22 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Final Issue for Design/ Construction-Specification for RTU | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-IC-0230 | HE-TL-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | HE-TL-2470 | HE-TL-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-Overall Telecom Block Diagram | HE-TL-2470 | HE-TL-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc. | HE-TL-2470 | HE-TL-0590 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Design Basis | Telecom | HE-TL-2470 | CAB-4470 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-Telecom cable schedule | HE-TL-2470 | HE-TL-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | HE-TL-2470 | HE-TL-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-2470 | HE-TL-0530 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Design Basis | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | HE-TL-2470 | ML1033-B22 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-TL-2470 | HE-TL-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Issue ICR- Specification for RTU | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | HE-IC-0190 | HE-TL-0410 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Issue ICR- Specification for RTU | Final Issue for Design/ Construction-Overall Telecom Block Diagram | HE-IC-0190 | HE-TL-0350 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for RTU | Final Issue for Design/ Construction-Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc. | HE-IC-0190 | HE-TL-0590 | SS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- Specification for RTU | Telecom | HE-IC-0190 | CAB-4470 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Issue ICR- Specification for RTU | Final Issue for Design/ Construction-Telecom cable schedule | HE-IC-0190 | HE-TL-0830 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Issue ICR- Specification for RTU | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | HE-IC-0190 | HE-TL-0470 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for RTU | Final Issue for Design/ Construction-Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-0190 | HE-TL-0530 | SS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..ML.EN Detail Engineering | Issue ICR- Specification for RTU | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | HE-IC-0190 | ML1033-B22 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for RTU | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-IC-0190 | HE-TL-0290 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | Issue ICR- Specification for Leak Detection System | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | HE-IC-0250 | HE-TL-0410 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | Issue ICR- Specification for Leak Detection System | Final Issue for Design/ Construction-Overall Telecom Block Diagram | HE-IC-0250 | HE-TL-0350 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for Leak Detection System | Final Issue for Design/ Construction-Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc. | HE-IC-0250 | HE-TL-0590 | SS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- Specification for Leak Detection System | Telecom | HE-IC-0250 | CAB-4470 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Issue ICR- Specification for Leak Detection System | Final Issue for Design/ Construction-Telecom cable schedule | HE-IC-0250 | HE-TL-0830 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Issue ICR- Specification for Leak Detection System | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | HE-IC-0250 | HE-TL-0470 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for Leak Detection System | Final Issue for Design/ Construction-Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-0250 | HE-TL-0530 | SS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..ML.EN Detail Engineering | Issue ICR- Specification for Leak Detection System | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | HE-IC-0250 | ML1033-B22 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- Specification for Leak Detection System | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | HE-IC-0250 | HE-TL-0290 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.1.BK.12 Modification of Existing Telecom System | Issue ICR- I&C Design Basis | RFQ, Receipt of Bid - Modification of Existing Telecom System | HE-IC-620 | HS-GN-0310 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- I&C Design Basis | Issue ICR- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-620 | HE-TL-0550 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | Issue ICR- I&C Design Basis | Issue ICR- Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-620 | HE-TL-0190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- I&C Design Basis | Re-Issue for Approval- Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-620 | HE-TL-0510 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Issue ICR- I&C Design Basis | Re-Issue for Approval- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-620 | HE-TL-0570 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | Final Issue for Design/ Construction-Specification for RTU | Final Issue for Design/ Construction-Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-0230 | HE-TL-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | Final Issue for Design/ Construction-Specification for Leak Detection System | Final Issue for Design/ Construction-Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-0290 | HE-TL-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | Issue ICR- I&C Design Basis | Final Issue for Design/ Construction-Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-IC-620 | HE-TL-0230 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- I&C Design Basis | Telecom | HE-IC-620 | CAB-4470 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..ML.EN Detail Engineering | Issue ICR- I&C Design Basis | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | HE-IC-620 | ML1033-B22 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Issue ICR- Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Issue ICR- Telecom Cable Schedule | HE-TL-0550 | HE-TL-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | 60% Model Review | Issue ICR-Telecom Location and Cable Routing layout | ML2069-B09 | HE-TL-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | Issue ICR-Telecom Equipment Layout | Issue ICR- Telecom Cable Schedule | HE-TL-0730 | HE-TL-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | Issue ICR-Telecom Location and Cable Routing layout | Issue ICR-Telecom Equipment Layout | HE-TL-0670 | HE-TL-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A321 Telecom Equipment List | P2543-R01-Oct24..1.EN.10.A321 Telecom Equipment List | Re-Issue for Approval-Telecom Equipment List | Obtain Company Approval- Telecom Equipment List | HE-TL-960 | HE-TL-970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A321 Telecom Equipment List | P2543-R01-Oct24..1.EN.10.A321 Telecom Equipment List | Issue ICR- Telecom Equipment List | Receive Company Comments- Telecom Equipment List | HE-TL-940 | HE-TL-950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A321 Telecom Equipment List | P2543-R01-Oct24..1.EN.10.A321 Telecom Equipment List | Receive Company Comments- Telecom Equipment List | Re-Issue for Approval-Telecom Equipment List | HE-TL-950 | HE-TL-960 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A321 Telecom Equipment List | P2543-R01-Oct24..1.EN.10.A321 Telecom Equipment List | Obtain Company Approval- Telecom Equipment List | Final Issue for Design/ Construction-Telecom Equipment List | HE-TL-970 | HE-TL-980 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..1.EN.10.A321 Telecom Equipment List | Issue ICR- Overall Telecom Block Diagram | Issue ICR- Telecom Equipment List | HE-TL-0310 | HE-TL-940 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A321 Telecom Equipment List | P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | Final Issue for Design/ Construction-Telecom Equipment List | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | HE-TL-980 | HE-TL-0470 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A2112 Telecom Inter Connection Diagram | P2543-R01-Oct24..1.EN.10.A2112 Telecom Inter Connection Diagram | Re-Issue for Approval- Telecom Inter Connection Diagram | Obtain Company Approval- Telecom Inter Connection Diagram | HE-TL-1020 | HE-TL-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A2112 Telecom Inter Connection Diagram | P2543-R01-Oct24..1.EN.10.A2112 Telecom Inter Connection Diagram | Receive Company Comments- Telecom Inter Connection Diagram | Re-Issue for Approval- Telecom Inter Connection Diagram | HE-TL-1010 | HE-TL-1020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A2112 Telecom Inter Connection Diagram | P2543-R01-Oct24..1.EN.10.A2112 Telecom Inter Connection Diagram | Issue ICR- Telecom Inter Connection Diagram | Receive Company Comments- Telecom Inter Connection Diagram | HE-TL-1000 | HE-TL-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A2112 Telecom Inter Connection Diagram | P2543-R01-Oct24..1.EN.10.A2112 Telecom Inter Connection Diagram | Obtain Company Approval- Telecom Inter Connection Diagram | Final Issue for Design/ Construction-Telecom Inter Connection Diagram | HE-TL-1030 | HE-TL-990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A21121 Typical Inter Connection Diagram for Pig Launcher/Receiver | P2543-R01-Oct24..1.EN.10.A21121 Typical Inter Connection Diagram for Pig Launcher/Receiver | Re-Issue for Approval- Typical Inter Connection Diagram for Pig Launcher/Receiver | Obtain Company Approval- Typical Inter Connection Diagram for Pig Launcher/Receiver | HE-TL-1070 | HE-TL-1080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A21121 Typical Inter Connection Diagram for Pig Launcher/Receiver | P2543-R01-Oct24..1.EN.10.A21121 Typical Inter Connection Diagram for Pig Launcher/Receiver | Receive Company Comments- Typical Inter Connection Diagram for Pig Launcher/Receiver | Re-Issue for Approval- Typical Inter Connection Diagram for Pig Launcher/Receiver | HE-TL-1060 | HE-TL-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A21121 Typical Inter Connection Diagram for Pig Launcher/Receiver | P2543-R01-Oct24..1.EN.10.A21121 Typical Inter Connection Diagram for Pig Launcher/Receiver | Issue ICR- Typical Inter Connection Diagram for Pig Launcher/Receiver | Receive Company Comments- Typical Inter Connection Diagram for Pig Launcher/Receiver | HE-TL-1050 | HE-TL-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A21121 Typical Inter Connection Diagram for Pig Launcher/Receiver | P2543-R01-Oct24..1.EN.10.A21121 Typical Inter Connection Diagram for Pig Launcher/Receiver | Obtain Company Approval- Typical Inter Connection Diagram for Pig Launcher/Receiver | Final Issue for Design/ Construction-Typical Inter Connection Diagram for Pig Launcher/Receiver | HE-TL-1080 | HE-TL-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211211 Fibre Core Allocation Diagram | P2543-R01-Oct24..1.EN.10.A211211 Fibre Core Allocation Diagram | Re-Issue for Approval- Fiber Core Allocation Diagram | Obtain Company Approval- Fiber Core Allocation Diagram | HE-TL-1120 | HE-TL-1130 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211211 Fibre Core Allocation Diagram | P2543-R01-Oct24..1.EN.10.A211211 Fibre Core Allocation Diagram | Receive Company Comments- Fiber Core Allocation Diagram | Re-Issue for Approval- Fiber Core Allocation Diagram | HE-TL-1110 | HE-TL-1120 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211211 Fibre Core Allocation Diagram | P2543-R01-Oct24..1.EN.10.A211211 Fibre Core Allocation Diagram | Issue ICR- Fiber Core Allocation Diagram | Receive Company Comments- Fiber Core Allocation Diagram | HE-TL-1100 | HE-TL-1110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211211 Fibre Core Allocation Diagram | P2543-R01-Oct24..1.EN.10.A211211 Fibre Core Allocation Diagram | Obtain Company Approval- Fiber Core Allocation Diagram | Final Issue for Design/ Construction- Fiber Core Allocation Diagram | HE-TL-1130 | HE-TL-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2112111 Optical Power Link Loss Calculation For SDH / FOC System | P2543-R01-Oct24..1.EN.10.A2112111 Optical Power Link Loss Calculation For SDH / FOC System | Re-Issue for Approval- Optical Power Link Loss Calculation For SDH / FOC System | Obtain Company Approval- Optical Power Link Loss Calculation For SDH / FOC System | HE-TL-1170 | HE-TL-1180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A2112111 Optical Power Link Loss Calculation For SDH / FOC System | P2543-R01-Oct24..1.EN.10.A2112111 Optical Power Link Loss Calculation For SDH / FOC System | Receive Company Comments- Optical Power Link Loss Calculation For SDH / FOC System | Re-Issue for Approval- Optical Power Link Loss Calculation For SDH / FOC System | HE-TL-1160 | HE-TL-1170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A2112111 Optical Power Link Loss Calculation For SDH / FOC System | P2543-R01-Oct24..1.EN.10.A2112111 Optical Power Link Loss Calculation For SDH / FOC System | Issue ICR- Optical Power Link Loss Calculation For SDH / FOC System | Receive Company Comments- Optical Power Link Loss Calculation For SDH / FOC System | HE-TL-1150 | HE-TL-1160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A2112111 Optical Power Link Loss Calculation For SDH / FOC System | P2543-R01-Oct24..1.EN.10.A2112111 Optical Power Link Loss Calculation For SDH / FOC System | Obtain Company Approval- Optical Power Link Loss Calculation For SDH / FOC System | Final Issue for Design/ Construction-Optical Power Link Loss Calculation For SDH / FOC System | HE-TL-1180 | HE-TL-1140 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.10.A21121111 Narrative For Intrusion Detection System | P2543-R01-Oct24..1.EN.10.A21121111 Narrative For Intrusion Detection System | Re-Issue for Approval- Overall Telecom Block Diagram | Obtain Company Approval- Overall Telecom Block Diagram | HE-TL-1220 | HE-TL-1230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A21121111 Narrative For Intrusion Detection System | P2543-R01-Oct24..1.EN.10.A21121111 Narrative For Intrusion Detection System | Receive Company Comments- Overall Telecom Block Diagram | Re-Issue for Approval- Overall Telecom Block Diagram | HE-TL-1210 | HE-TL-1220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A21121111 Narrative For Intrusion Detection System | P2543-R01-Oct24..1.EN.10.A21121111 Narrative For Intrusion Detection System | Issue ICR- Overall Telecom Block Diagram | Receive Company Comments- Overall Telecom Block Diagram | HE-TL-1200 | HE-TL-1210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A21121111 Narrative For Intrusion Detection System | P2543-R01-Oct24..1.EN.10.A21121111 Narrative For Intrusion Detection System | Obtain Company Approval- Overall Telecom Block Diagram | Final Issue for Design/ Construction-Overall Telecom Block Diagram | HE-TL-1230 | HE-TL-1190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211211111 Telecom Tie In Schedule | P2543-R01-Oct24..1.EN.10.A211211111 Telecom Tie In Schedule | Re-Issue for Approval- Overall Telecom Block Diagram | Obtain Company Approval- Overall Telecom Block Diagram | HE-TL-1270 | HE-TL-1280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211211111 Telecom Tie In Schedule | P2543-R01-Oct24..1.EN.10.A211211111 Telecom Tie In Schedule | Receive Company Comments- Overall Telecom Block Diagram | Re-Issue for Approval- Overall Telecom Block Diagram | HE-TL-1260 | HE-TL-1270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211211111 Telecom Tie In Schedule | P2543-R01-Oct24..1.EN.10.A211211111 Telecom Tie In Schedule | Issue ICR- Overall Telecom Block Diagram | Receive Company Comments- Overall Telecom Block Diagram | HE-TL-1250 | HE-TL-1260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211211111 Telecom Tie In Schedule | P2543-R01-Oct24..1.EN.10.A211211111 Telecom Tie In Schedule | Obtain Company Approval- Overall Telecom Block Diagram | Final Issue for Design/ Construction-Overall Telecom Block Diagram | HE-TL-1280 | HE-TL-1240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..1.EN.10.A2112 Telecom Inter Connection Diagram | Issue ICR- Overall Telecom Block Diagram | Issue ICR- Telecom Inter Connection Diagram | HE-TL-0310 | HE-TL-1000 | SS | Completed | Completed | 3
P2543-R01-Oct24..1.EN.10.A2112 Telecom Inter Connection Diagram | P2543-R01-Oct24..1.EN.10.A21121 Typical Inter Connection Diagram for Pig Launcher/Receiver | Final Issue for Design/ Construction-Telecom Inter Connection Diagram | Final Issue for Design/ Construction-Typical Inter Connection Diagram for Pig Launcher/Receiver | HE-TL-990 | HE-TL-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A2112 Telecom Inter Connection Diagram | P2543-R01-Oct24..1.EN.10.A21121 Typical Inter Connection Diagram for Pig Launcher/Receiver | Issue ICR- Telecom Inter Connection Diagram | Issue ICR- Typical Inter Connection Diagram for Pig Launcher/Receiver | HE-TL-1000 | HE-TL-1050 | SS | Completed | Completed | 3
P2543-R01-Oct24..1.EN.10.A21121 Typical Inter Connection Diagram for Pig Launcher/Receiver | P2543-R01-Oct24..1.EN.10.A211211 Fibre Core Allocation Diagram | Issue ICR- Typical Inter Connection Diagram for Pig Launcher/Receiver | Issue ICR- Fiber Core Allocation Diagram | HE-TL-1050 | HE-TL-1100 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.10.A21121 Typical Inter Connection Diagram for Pig Launcher/Receiver | P2543-R01-Oct24..1.EN.10.A211211 Fibre Core Allocation Diagram | Final Issue for Design/ Construction-Typical Inter Connection Diagram for Pig Launcher/Receiver | Final Issue for Design/ Construction- Fiber Core Allocation Diagram | HE-TL-1040 | HE-TL-1090 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..1.EN.10.A21121111 Narrative For Intrusion Detection System | Issue ICR- Overall Telecom Block Diagram | Issue ICR- Overall Telecom Block Diagram | HE-TL-0310 | HE-TL-1200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A21121111 Narrative For Intrusion Detection System | P2543-R01-Oct24..1.EN.10.A2112111 Optical Power Link Loss Calculation For SDH / FOC System | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Final Issue for Design/ Construction-Optical Power Link Loss Calculation For SDH / FOC System | HE-TL-1190 | HE-TL-1140 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.10.A211211111 Telecom Tie In Schedule | P2543-R01-Oct24..1.EN.10.A2112111 Optical Power Link Loss Calculation For SDH / FOC System | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Final Issue for Design/ Construction-Optical Power Link Loss Calculation For SDH / FOC System | HE-TL-1240 | HE-TL-1140 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A211211111 Telecom Tie In Schedule | Issue ICR - Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Issue ICR- Overall Telecom Block Diagram | HE-TL-0070 | HE-TL-1250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A2112111 Optical Power Link Loss Calculation For SDH / FOC System | P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | Final Issue for Design/ Construction-Optical Power Link Loss Calculation For SDH / FOC System | Final Issue for Design/ Construction-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-1140 | HE-TL-0650 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211211 Fibre Core Allocation Diagram | P2543-R01-Oct24..1.EN.10.A2112111 Optical Power Link Loss Calculation For SDH / FOC System | Final Issue for Design/ Construction- Fiber Core Allocation Diagram | Final Issue for Design/ Construction-Optical Power Link Loss Calculation For SDH / FOC System | HE-TL-1090 | HE-TL-1140 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..1.EN.5.4 Addendum to DGS (Launche/Receiver) | P2543-R01-Oct24..1.EN.5.2.1 Datasheet for PIG RECEIVER (839-V-101) 52" | Issue ICR- Addendum to DGS | Final Issue for Design/ Construction-Datasheet for PIG RECEIVER (839-V-101) | HE-ME-620 | HE-ME-300 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0040 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..ML.EN Detail Engineering | Issue ICR- Process Flow Diagrams ( New + Existing) | Completion of all Detailed Engineering | HE-PR-0040 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- Process Flow Diagrams ( New + Existing) | Process | HE-PR-0040 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR- H&MB Report | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-1240 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..ML.EN Detail Engineering | Issue ICR- H&MB Report | Completion of all Detailed Engineering | HE-PR-1240 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- H&MB Report | Process | HE-PR-1240 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Receive Company Comments- H&MB Report | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-1250 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..ML.EN Detail Engineering | Receive Company Comments- H&MB Report | Completion of all Detailed Engineering | HE-PR-1250 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Receive Company Comments- H&MB Report | Process | HE-PR-1250 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0060 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Completion of all Detailed Engineering | HE-PR-0060 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Re-Issue for HAZOP Studies- Process Flow Diagrams ( New + Existing) | Process | HE-PR-0060 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Design Review Workshop | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-WS-0030 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..ML.EN Detail Engineering | Design Review Workshop | Completion of all Detailed Engineering | HE-WS-0030 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Design Review Workshop | Process | HE-WS-0030 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR- HAZOP reviews Report for all areas | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-HS-0670 | HE-PI-0620 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..ML.EN Detail Engineering | Issue ICR- HAZOP reviews Report for all areas | Completion of all Detailed Engineering | HE-HS-0670 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- HAZOP reviews Report for all areas | Process | HE-HS-0670 | CAB-4400 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0070 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Completion of all Detailed Engineering | HE-PR-0070 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Re-Issue after incorporating HAZOP /Review Comments- Process Flow Diagrams ( New + Existing) | Process | HE-PR-0070 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Re-Issue after incorporating Review Comments- H&MB Report | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-1200 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue after incorporating Review Comments- H&MB Report | Completion of all Detailed Engineering | HE-PR-1200 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Re-Issue after incorporating Review Comments- H&MB Report | Process | HE-PR-1200 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction-Process Flow Diagrams ( New + Existing) | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0090 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Process Flow Diagrams ( New + Existing) | Completion of all Detailed Engineering | HE-PR-0090 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Process Flow Diagrams ( New + Existing) | Process | HE-PR-0090 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction-Process Simulations Report | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0650 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Process Simulations Report | Completion of all Detailed Engineering | HE-PR-0650 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction- H&MB Report | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-1220 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction- H&MB Report | Completion of all Detailed Engineering | HE-PR-1220 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction- H&MB Report | Process | HE-PR-1220 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction-Relief, Vent and Blowdown philosophy | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0830 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design / Construction-P&ID's | Completion of all Detailed Engineering | HE-PR-0160 | ML1219-B29 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design / Construction-P&ID's | Process | HE-PR-0160 | CAB-4400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction-Operating , control and safeguarding philosophy | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0770 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Operating , control and safeguarding philosophy | Completion of all Detailed Engineering | HE-PR-0770 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Operating , control and safeguarding philosophy | Process | HE-PR-0770 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0140 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..ML.EN Detail Engineering | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Completion of all Detailed Engineering | HE-PR-0140 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | Process | HE-PR-0140 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR- P&ID's | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0110 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..ML.EN Detail Engineering | Issue ICR- P&ID's | Completion of all Detailed Engineering | HE-PR-0110 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- P&ID's | Process | HE-PR-0110 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR- Operating and control philosophy, Safeguarding philosophy | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0730 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..ML.EN Detail Engineering | Issue ICR- Operating and control philosophy, Safeguarding philosophy | Completion of all Detailed Engineering | HE-PR-0730 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR- Operating and control philosophy, Safeguarding philosophy | Process | HE-PR-0730 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR - Relief, Vent and Blowdown Philosophy | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0790 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | P2543-R01-Oct24..ML.EN Detail Engineering | Issue ICR - Relief, Vent and Blowdown Philosophy | Completion of all Detailed Engineering | HE-PR-0790 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR - Relief, Vent and Blowdown Philosophy | Process | HE-PR-0790 | CAB-4400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.4.9 Datasheet for Ball valves | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Final Issue for Design/ Construction-Datasheet for Ball valves | Issue ICR-Material Requisitions for Leak Detection System | HE-PI-0940 | HE-IC-1750 | FS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | Issue ICR- P&ID's | Issue ICR- Operating and control philosophy, Safeguarding philosophy | HE-PR-0110 | HE-PR-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | Issue ICR - Relief, Vent and Blowdown Philosophy | Issue ICR- Process Datasheets | HE-PR-0790 | HE-PR-1310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | P2543-R01-Oct24..1.EN.3.18 Vent and Depressurization Report (for new facilities) | Issue ICR- Process Datasheets | Issue ICR- Vent and Depressurization Report (for new facilities) | HE-PR-1310 | HE-PR-0970 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | Issue ICR- Process Datasheets - Pig Launcher / Receiver | Issue ICR- Process Datasheets | HE-PR-0490 | HE-PR-0550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | Issue ICR- Process Datasheets | Issue ICR- Process Datasheets | HE-PR-0550 | HE-PR-1260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | Issue ICR- Process Datasheets | Issue ICR- Process Datasheets | HE-PR-1260 | HE-PR-1360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | Issue ICR- Process Datasheets | Issue ICR- Process Datasheets | HE-PR-1260 | HE-PR-1560 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | Issue ICR- Process Datasheets | Issue ICR- Process Datasheets | HE-PR-1560 | HE-PR-1360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.19 Heat & Material Balance | P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | Issue ICR- H&MB Report | Issue ICR- Process Simulations Report | HE-PR-1240 | HE-PR-0610 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | Issue ICR- Process Datasheets | Issue ICR-Datasheets for Field Instruments / H2S Analyzers | HE-PR-1460 | HE-IC-1450 | FS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.15.7 RBI Study Report | P2543-R01-Oct24..ML Milestones | Final Issue for Design/ Construction-RBI Study Report | Achieve PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | HE-CP-340 | ML1040 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.15.3 TBE | P2543-R01-Oct24..1.2.13.11 Cathodic Protection Work | Issue ICR - TBE for RBI Study | Prepare/Issue Scope of Work - Cathodic Protection Work | HE-CP-150 | HS-GN-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | Issue ICR - Pipeline Alignment Sheets -56" | Issue ICR - Pipeline MTO - 56" | HE-PL-2390 | HE-PL-3230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.7 Hot Tap Scope of Work | P2543-R01-Oct24..1.PM.7 Hot Tap Scope of Work | Obtain Company Approval-Hot Tap SOW | Final Issue for Design/ Construction-Hot Tap SOW | HC-GN-370 | HC-GN-380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.7 Hot Tap Scope of Work | P2543-R01-Oct24..1.PM.7 Hot Tap Scope of Work | Issue ICR-Hot Tap SOW | Receive Company Comments-Hot Tap SOW | HC-GN-340 | HC-GN-350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.7 Hot Tap Scope of Work | P2543-R01-Oct24..1.PM.7 Hot Tap Scope of Work | Receive Company Comments-Hot Tap SOW | Re-Issue for Approval-Hot Tap SOW | HC-GN-350 | HC-GN-360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.7 Hot Tap Scope of Work | P2543-R01-Oct24..1.PM.7 Hot Tap Scope of Work | Re-Issue for Approval-Hot Tap SOW | Obtain Company Approval-Hot Tap SOW | HC-GN-360 | HC-GN-370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.40 Specification - Split Tee | P2543-R01-Oct24..1.PM.7 Hot Tap Scope of Work | Issue ICR - Specification - Split Tee | Issue ICR-Hot Tap SOW | HE-PL-0430 | HC-GN-340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.7 Hot Tap Scope of Work | P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | Final Issue for Design/ Construction-Hot Tap SOW | Final Issue for Design/ Construction-Data Sheet - Split Tee | HC-GN-380 | HE-PL-1370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | P2543-R01-Oct24..1.EN.7.10 3D Model | Final Issue for Design/ Construction-Data Sheet - Split Tee | 90% Model Review Report | HE-PL-1370 | HE-PI-0180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | P2543-R01-Oct24..1.EN.7.10 3D Model | Final Issue for Design/ Construction-Piping Tie In Schedule | 90% Model Review Report | HE-PI-3520 | HE-PI-0180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Piping Tie In Schedule | Pipeline | HE-PI-3520 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.1.5 Hot Tapping | P2543-R01-Oct24..1.EN.7.10 3D Model | Commercial Clarifications & Placement of PO- Hot Tapping | 90% Model Review Report | HS-GN-0230 | HE-PI-0180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.1.5 Hot Tapping | P2543-R01-Oct24..ML.EN Detail Engineering | Commercial Clarifications & Placement of PO- Hot Tapping | Completion of all Detailed Engineering | HS-GN-0230 | ML1219-B29 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.1.1.5 Hot Tapping | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Commercial Clarifications & Placement of PO- Hot Tapping | Pipeline | HS-GN-0230 | CAB-4480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.9.2 MR for Split Tee | P2543-R01-Oct24..1.EN.1.9.2 MR for Split Tee | Re-Issue for Approval - MR for Split Tee | Obtain Company Approval - MR for Split Tee | HE-PL-3670 | HE-PL-3630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.2 MR for Split Tee | P2543-R01-Oct24..1.EN.1.9.2 MR for Split Tee | Issue ICR - MR for Split Tee | Receive Company Comments - MR for Split Tee | HE-PL-3650 | HE-PL-3660 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.2 MR for Split Tee | P2543-R01-Oct24..1.EN.1.9.2 MR for Split Tee | Obtain Company Approval - MR for Split Tee | Final Issue for Design/ Construction-MR for Split Tee | HE-PL-3630 | HE-PL-3640 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.2 MR for Split Tee | P2543-R01-Oct24..1.EN.1.9.2 MR for Split Tee | Receive Company Comments - MR for Split Tee | Re-Issue for Approval - MR for Split Tee | HE-PL-3660 | HE-PL-3670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.2 TBE for Split Tee | P2543-R01-Oct24..1.EN.1.10.2 TBE for Split Tee | Obtain Company Approval - TBE for Split Tee | Final Issue for Design/ Construction-TBE for Split Tee | HE-PL-3680 | HE-PL-3720 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.2 TBE for Split Tee | P2543-R01-Oct24..1.EN.1.10.2 TBE for Split Tee | Receive Company Comments - TBE for Split Tee | Re-Issue for Approval - TBE for Split Tee | HE-PL-3700 | HE-PL-3710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.2 TBE for Split Tee | P2543-R01-Oct24..1.EN.1.10.2 TBE for Split Tee | Re-Issue for Approval - TBE for Split Tee | Obtain Company Approval - TBE for Split Tee | HE-PL-3710 | HE-PL-3680 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.2 TBE for Split Tee | P2543-R01-Oct24..1.EN.1.10.2 TBE for Split Tee | Issue ICR - TBE for Split Tee | Receive Company Comments - TBE for Split Tee | HE-PL-3690 | HE-PL-3700 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.2 MR for Split Tee | P2543-R01-Oct24..1.EN.1.10.2 TBE for Split Tee | Issue ICR - MR for Split Tee | Issue ICR - TBE for Split Tee | HE-PL-3650 | HE-PL-3690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.2 MR for Split Tee | P2543-R01-Oct24..1.EN.1.10.2 TBE for Split Tee | Final Issue for Design/ Construction-MR for Split Tee | Final Issue for Design/ Construction-TBE for Split Tee | HE-PL-3640 | HE-PL-3720 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.9.2 MR for Split Tee | P2543-R01-Oct24..1.1.1.2.1 Ordering | Issue ICR - MR for Split Tee | RFQ, Receipt of Bid for Pigging & Split Tee | HE-PL-3650 | HP-ME-1270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.2 TBE for Split Tee | P2543-R01-Oct24..1.1.1.2.1 Ordering | Obtain Company Approval - TBE for Split Tee | Prepare TBE and Company approval for Pigging & Split Tee | HE-PL-3680 | HP-ME-1280 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.56 Piping Design Basis | P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | Issue ICR-Design Basis | Issue ICR-Pipe Wall Thickness Calculation | HE-DB-130 | HE-PI-0200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | Issue ICR-Pipe Wall Thickness Calculation | Issue ICR-Piping Material Specifications | HE-PI-0200 | HE-PI-0010 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Receive Company Comments- Process Flow Diagrams ( New + Existing) | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-0050 | HE-PI-0320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.10 Equipment List | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR - Equipment List | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PR-1030 | HE-PI-0320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.7 Process Flow Diagrams | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Receive Company Comments- Process Flow Diagrams ( New + Existing) | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | HE-PR-0050 | HE-PI-0390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0390 | HE-PI-0320 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Issue ICR- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR- Overall Plot Plan - 4" N2 Source Pipeline | HE-PI-0320 | HE-PI-0460 | SS | Completed | Completed | 5
P2543-R01-Oct24..1.EN.3.10 Equipment List | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Receive Company Comments - Equipment List | Issue ICR- Overall Plot Plan-52" Pipeline SWEIHAN CRS | HE-PR-1040 | HE-PI-0390 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.18 Material Requisition for Ball/ Plug Valves | P2543-R01-Oct24..1.EN.7.2.6 TBE for Ball valves/ Plug Valves | Receive Company Comments-MR for Ball valves/ Plug Valves | Issue ICR- TBE for Ball valves/ Plug Valves | HE-PI-1030 | HE-PI-1080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.2 Material Requisition for Piping Special Items | P2543-R01-Oct24..1.EN.7.2.20 TBE for Piping Special Items | Receive Company Comments-MR for Piping Special Items | Issue ICR- TBE for Piping Special Items | HE-PI-3690 | HE-PI-1410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.6 Material Requisition for Piping Bulk | P2543-R01-Oct24..1.EN.7.2.17 TBE for Piping Bulks (Pipe, Flange, etc) | Receive Company Comments-MR for Piping Bulks | Issue ICR- TBE for Piping Bulks (Pipe, Flange, etc) | HE-PI-3540 | HE-PI-1360 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.1 Material Requisition for Check Valves | P2543-R01-Oct24..1.EN.7.2.1 TBE for Check Valves | Receive Company Comments-MR for Check Valves | Issue ICR- TBE for Check Valves | HE-PI-3640 | HE-PI-3730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.8.6 Material Requisition for Piping Bulk | P2543-R01-Oct24..1.EN.7.19 Piping MTO | Final Issue for Design/ Construction-Material Requisition for Piping Bulks & Special Items | Piping MTO - 1st | HE-PI-3570 | HE-PI-1260 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | P2543-R01-Oct24..1.EN.1.9.2 MR for Split Tee | Issue ICR - Data Sheet - Split Tee | Issue ICR - MR for Split Tee | HE-PL-1330 | HE-PL-3650 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.10.2 TBE for Split Tee | P2543-R01-Oct24..PR.1.2.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-TBE for Split Tee | Vendor Document Review of Pigging & Split Tee | HE-PL-3720 | HM-PL-0770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.7.1 Ordering | P2543-R01-Oct24..1.EN.9.6.28 TBE for Distribution Boards | RFQ, Receipt of Bid for Power Distribution Boards | Issue ICR-TBE for Distribution Boards | HP-ME-0410 | HE-EL-1390 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..1.1.2.25.7.1 Ordering | Issue ICR-Material Requisition for Distribution Boards | RFQ, Receipt of Bid for Power Distribution Boards | HE-EL-0970 | HP-ME-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.5 Material Selection Report | P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | Issue ICR - Material Selection Report | Issue ICR-Piping Material Specifications | HE-CP-200 | HE-PI-0010 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.4 Material Selection Diagram | P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | Issue ICR - Material Selection Diagram | Issue ICR-Pipe Wall Thickness Calculation | HE-CP-0010 | HE-PI-0200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | 90% Model Review | Re-Issue for Approval-Piping Isometrics | HE-PI-0170 | HE-PI-1220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | 60% Model Review | Issue ICR-Piping Isometrics | HE-PI-0150 | HE-PI-1200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | 90% Model Review | Issue ICR-Piping Isometrics | HE-PI-0170 | HE-PI-1200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.17 Line List | P2543-R01-Oct24..1.EN.7.16 Critical line List | Final Issue for Design/ Construction-Line List | Final Issue for Design/ Construction-Critical line List | HE-PR-1130 | HE-PI-0302 | SS | In Progress | Completed | 10
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | 60% Model Review Report | Re-Issue for Approval-Piping GA -56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0160 | HE-PI-0620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.7 Hot Tap Scope of Work | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Hot Tap SOW | Issue ICR-Construction Procedures / Method Statements / ITPs | HC-GN-380 | C-COM-750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | Receive Company Comments-Isolation & Tie-In philosophy | Obtain Company Approval-Tie-In Schedule | HE-PR-0860 | HE-PR-0280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Relief, Vent and Blowdown philosophy | Issue ICR-Construction Procedures / Method Statements / ITPs | HE-PR-0830 | C-COM-750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Data Sheet - Split Tee | Issue ICR-Construction Procedures / Method Statements / ITPs | HE-PL-1370 | C-COM-750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.21 Piping Specifications - Addendum to DGS | P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | Final Issue for Design/ Construction-Piping Specifications - Addendum to DGS | Final Issue for Design/ Construction-Piping Tie In Schedule | HE-PI-3430 | HE-PI-3520 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Piping Tie In Schedule | Issue ICR-Construction Procedures / Method Statements / ITPs | HE-PI-3520 | C-COM-750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2.6 Project Risk Review Register | P2543-R01-Oct24..1.PM.12 Workshops | Final Issue for Design/ Construction-Project Risk Review Register | ALARP Workshop | HE-RR-0050 | HE-WS-0200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | Final Issue for Design/ Construction-Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | Final Issue for Design/ Construction-Process Datasheets - PRS Skid (at Sweihan CRS) | HE-PR-0350 | HE-PR-0410 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | Final Issue for Design/ Construction-Process Datasheets - Pig Launcher / Receiver | Final Issue for Design/ Construction-Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | HE-PR-0530 | HE-PR-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.14 Process Datasheets - Pig Launcher / Receiver | P2543-R01-Oct24..1.EN.5.2.1 Datasheet for PIG RECEIVER (839-V-101) 52" | Final Issue for Design/ Construction-Process Datasheets - Pig Launcher / Receiver | Issue ICR-Datasheet for PIG RECEIVER (839-V-101) | HE-PR-0530 | HE-ME-310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | Final Issue for Design/ Construction-Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | Re-Issue for Approval- Datasheets for Metering Skid | HE-PR-0350 | HE-IC-1170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Final Issue for Design/ Construction-Process Datasheets - PRS Skid (at Sweihan CRS) | Obtain Company Approval- Data sheet for PRS (Pressure Reduction System) | HE-PR-0410 | HE-IC-1240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | P2543-R01-Oct24..1.EN.5.2.5 Datasheet for Sals Gas CRS Filters | Receive Company Comments- Process Datasheets - Filters (At Sweihan CRS) | Issue ICR-Datasheet for Sales Gas CRS Filters | HE-PR-0440 | HE-ME-0070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | Receive Company Comments- Process Datasheets | Issue ICR- Datasheet for MOV | HE-PR-0560 | HE-IC-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | Receive Company Comments- Process Datasheets | Issue ICR- Datasheet for GOV & ROV | HE-PR-1270 | HE-IC-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | Receive Company Comments- Process Datasheets | Receive Company Comments- Datasheets for PSV & Orifice (incl. RO) | HE-PR-1570 | HE-IC-1340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | Receive Company Comments- Process Datasheets | Issue ICR-Datasheets for Field Instruments / H2S Analyzers | HE-PR-1370 | HE-IC-1450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | Receive Company Comments- Process Datasheets | Issue ICR-Datasheets for Field Instruments / H2S Analyzers | HE-PR-1420 | HE-IC-1450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | Receive Company Comments- Process Datasheets | Receive Company Comments-Datasheets for Field Instruments / H2S Analyzers | HE-PR-1470 | HE-IC-1460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | Issue ICR- Process Datasheets | Issue ICR-Datasheets for Field Instruments / H2S Analyzers | HE-PR-1510 | HE-IC-1450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | Issue ICR- Process Datasheets | Issue ICR- Datasheets for PSV & Orifice (incl. RO) | HE-PR-1310 | HE-IC-1330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | Receive Company Comments- Process Datasheets | Receive Company Comments- Datasheets for PSV & Orifice (incl. RO) | HE-PR-1320 | HE-IC-1340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | P2543-R01-Oct24..1.EN.6.4.A4 Datasheets for Field Instruments | Receive Company Comments- Process Datasheets | Receive Company Comments-Datasheets for Field Instruments / H2S Analyzers | HE-PR-1520 | HE-IC-1460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | P2543-R01-Oct24..1.EN.3.9 Relief, Vent and Blowdown philosophy | Receive Company Comments- Operating and control philosophy , Safeguarding philosophy | Receive Company Comments - Relief, Vent and Blowdown Philosophy | HE-PR-0740 | HE-PR-0800 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.1 Process Simulations Report | P2543-R01-Oct24..1.EN.3.4 Operating , control and safeguarding philosophy | Final Issue for Design/ Construction-Process Simulations Report | Issue ICR- Operating and control philosophy, Safeguarding philosophy | HE-PR-0650 | HE-PR-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.17 Line List | P2543-R01-Oct24..1.EN.3.10 Equipment List | Obtain Company Approval- Line List | Obtain Company Approval - Equipment List | HE-PR-1120 | HE-PR-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.10 Equipment List | P2543-R01-Oct24..1.EN.1.27 Pipeline Typical Drawings | Obtain Company Approval - Equipment List | Final Issue for Design/ Construction-Pipeline Typical Drawings | HE-PR-1060 | HE-PL-0410 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..1.EN.1.13 Pipeline Schematic Arrangement- 56", 52" and 4" Pipline | Issue ICR - Overall Pipeline Route Map - 52" | Issue ICR - Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | HE-PL-0190 | HE-PL-0310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.4 Pipeline Road and Railway Crossing Calculation Report | P2543-R01-Oct24..1.EN.1.6 Pipeline Location Class selection Report | Final Issue for Design/ Construction-Pipeline Road and Railway Crossing Calculation Report | Final Issue for Design/ Construction-Pipeline Location Class Selection Report (Incl Valve Sectionalizing) | HE-PL-0710 | HE-PL-0830 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.60.10 Data Sheet - Hot Induction Bends | P2543-R01-Oct24..1.EN.1.60.11 Data Sheet - Pipeline Isolating Joints | Final Issue for Design/ Construction-Data Sheet - Hot Induction Bends | Final Issue for Design/ Construction-Data Sheet - Pipeline Isolating Joints | HE-PL-1310 | HE-PL-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.60.11 Data Sheet - Pipeline Isolating Joints | P2543-R01-Oct24..1.EN.1.9.20 MR for Isolating Joints | Final Issue for Design/ Construction-Data Sheet - Pipeline Isolating Joints | Final Issue for Design/ Construction-MR for Isolating Joints | HE-PL-1430 | HE-PL-1910 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..1.EN.1.12 Pipeline Station approach drawing - 4" Waterline | Issue ICR - Pipeline Alignment Sheets-4" | Issue ICR - Pipeline Station Approach drawing -4" | HE-PL-2510 | HE-PL-3580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | P2543-R01-Oct24..1.EN.1.1 Pipeline Route Verification and Selection Report | Issue ICR - Pipeline Alignment Sheets-4" | Issue ICR - Pipeline Route Verification and Selection Report | HE-PL-3530 | HE-PL-2750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.44 Detailed crossing drawings-4" | P2543-R01-Oct24..1.EN.1.55 Crossing Schedule-4" | Issue ICR - Detailed crossing drawings-4" | Issue ICR - Crossing Schedule-4" | HE-PL-3110 | HE-PL-3170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.44 Detailed crossing drawings-4" | P2543-R01-Oct24..1.EN.1.55 Crossing Schedule-4" | Final Issue for Design/ Construction-Detailed crossing drawings-4" | Final Issue for Design/ Construction-Crossing Schedule-4" | HE-PL-3150 | HE-PL-3210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | P2543-R01-Oct24..1.EN.1.44 Detailed crossing drawings-4" | Re-Issue for Approval - Pipeline Alignment Sheets-4" | Issue ICR - Detailed crossing drawings-4" | HE-PL-3550 | HE-PL-3110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | P2543-R01-Oct24..1.1.BK.6.1 Ordering | Obtain Company Approval - Pipeline MTO - 56" | 1st Pipeline Bulk material MTO | HE-PL-3260 | HP-BK-0380 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | Final Issue for Design/ Construction-Piping Material Specification | Re-Issue after incorporating HAZOP /Review Comments- P&ID's | HE-PI-0050 | HE-PR-0140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | 30% Model Review Report | Final Issue for Design/ Construction-Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0140 | HE-PI-0370 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | P2543-R01-Oct24..1.EN.7.16 Critical line List | Final Issue for Design/ Construction-Pipe Wall Thickness Calculation | Issue ICR-Critical line List | HE-PI-0240 | HE-PI-0262 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.1 Piping Material Specification | P2543-R01-Oct24..1.EN.7.16 Critical line List | Final Issue for Design/ Construction-Piping Material Specification | Issue ICR-Critical line List | HE-PI-0050 | HE-PI-0262 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.3 Pipe Wall Thickness Calculation | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction-Pipe Wall Thickness Calculation | Re-Issue for HAZOP Studies- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-PI-0240 | HE-PI-0340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | Receive Company Comments-Piping GA for 52" Pipeline SWEIHAN CRS | Obtain Company Approval-Piping GA for 4" N2 Source Pipeline | HE-PI-0670 | HE-PI-0750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | Receive Company Comments-Piping GA Drawings for 591-BVS-01 | Receive Company Comments-Piping GA for 591-BVS-01 to 06 | HE-PI-0790 | HE-PI-0850 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | Receive Company Comments-Piping GA for 52" Pipeline SWEIHAN CRS | Receive Company Comments-Piping GA for 4" N2 Source Pipeline | HE-PI-0670 | HE-PI-0730 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.10 3D Model | P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | 60% Model Review | Re-Issue for Approval-Piping GA for 4" N2 Source Pipeline | HE-PI-0150 | HE-PI-0740 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | Final Issue for Design/ Construction-Piping GA for 4" N2 Source Pipeline | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | HE-PI-0760 | HE-PI-0880 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..1.EN.5.1 Design Basis | P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | Final Issue for Design/ Construction- Mechanical Design Basis | Final Issue for Design/ Construction- Addendum to DGS | HE-ME-260 | HE-ME-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.4 Addendum to DGS (Launche/Receiver) | P2543-R01-Oct24..1.EN.5.2.3 Datasheet for PIG RECEIVER (838-V-601) 56" | Final Issue for Design/ Construction- Addendum to DGS | Final Issue for Design/ Construction-Datasheet for PIG RECEIVER (838-V-601) | HE-ME-610 | HE-ME-400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.1 Datasheet for PIG RECEIVER (839-V-101) 52" | P2543-R01-Oct24..1.EN.5.2.2 Datasheet for PIG LAUNCHER (838-V-602) 52" | Final Issue for Design/ Construction-Datasheet for PIG RECEIVER (839-V-101) | Final Issue for Design/ Construction-Datasheet for PIG LAUNCHER (838-V-602) | HE-ME-300 | HE-ME-350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.2 Datasheet for PIG LAUNCHER (838-V-602) 52" | P2543-R01-Oct24..1.EN.5.2.3 Datasheet for PIG RECEIVER (838-V-601) 56" | Final Issue for Design/ Construction-Datasheet for PIG LAUNCHER (838-V-602) | Final Issue for Design/ Construction-Datasheet for PIG RECEIVER (838-V-601) | HE-ME-350 | HE-ME-400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.2.3 Datasheet for PIG RECEIVER (838-V-601) 56" | P2543-R01-Oct24..1.EN.5.2.4 Datasheet for PIG LAUNCHER (607-V-603) 56" | Final Issue for Design/ Construction-Datasheet for PIG RECEIVER (838-V-601) | Final Issue for Design/ Construction-Datasheet for PIG LAUNCHER (607-V-603) | HE-ME-400 | HE-ME-450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.6.3 Material Requisitions Pig Launcher/Receiver | P2543-R01-Oct24..1.EN.5.3.3 TBE for Pig Launcher/Receiver | Final Issue for Design/ Construction-Material Requisitions for Pig Launcher/Receiver | Final Issue for Design/ Construction-TBEs for Pig Launcher/Receiver | HE-ME-520 | HE-ME-570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.5.5 Pig Launcher/Receiver Length Report | P2543-R01-Oct24..1.EN.5.3.3 TBE for Pig Launcher/Receiver | Final Issue for Design/ Construction- Pig Launcher/Receiver Length Report | Issue ICR-TBEs for Pig Launcher/Receiver | HE-ME-660 | HE-ME-530 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.2 Civil / Structural Design Basis | P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | Final Issue for Design/ Construction-Civil / Structural Design Basis | Final Issue for Design/ Construction-Addendum to DGs | HE-CS-1600 | HE-CS-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.1 Addendum to DGs | P2543-R01-Oct24..1.EN.8.9 Standard drawings for Anchor bolt | Review Company Comments - Addendum to DGs | Issued for Review - Standard drawings for Anchor bolt | HE-CS-0020 | HE-CS-0070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | Final Issue for Design/ Construction-Typical trench detail drawing | Final Issue for Design/ Construction-Typical duct bank detail drawing | HE-CS-0170 | HE-CS-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | Final Issue for Design/ Construction-Typical duct bank detail drawing | Final Issue for Design/ Construction-Typical Road and paving detail drawing | HE-CS-0230 | HE-CS-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Issue ICR-Construction Procedures / Method Statements / ITPs | HE-CS-0290 | C-COM-750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | Issued for Review - Lighting pole foundation details | Issued for Review - Calculations for Pipe supports | HE-CS-0970 | HE-CS-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.15.6 Material Coating & Painting Specification | P2543-R01-Oct24..1.EN.15.3 TBE | Final Issue for Design/ Construction-Material Coating & Painting Specification | Issue ICR - TBE for RBI Study | HE-CP-290 | HE-CP-150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | Issue ICR-Design Basis | Issue ICR- Adequacy report of the Power supply requirements | HE-DB-0010 | HE-EL-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.22 UPS SLDs | Issue ICR-Design Basis | Issue ICR - UPS SLD | HE-DB-0010 | HE-EL-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | Issue ICR-Design Basis | Issue ICR-Solar Panel System SLDs | HE-DB-0010 | HE-EL-0310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | Issue ICR-Design Basis | Issue ICR-Single Line Diagrams for LV Switchgear | HE-DB-0010 | HE-EL-0190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | Final Issue for Design/ Construction-Design Basis | Issue ICR- Adequacy report of the Power supply requirements | HE-EL-160 | HE-EL-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.22 UPS SLDs | Final Issue for Design/ Construction-Design Basis | Issue ICR - UPS SLD | HE-EL-160 | HE-EL-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | Final Issue for Design/ Construction-Design Basis | Issue ICR-Solar Panel System SLDs | HE-EL-160 | HE-EL-0310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | Final Issue for Design/ Construction-Design Basis | Issue ICR-Single Line Diagrams for LV Switchgear | HE-EL-160 | HE-EL-0190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | Issue ICR-Design Basis | Issue ICR- Datasheet for Solar panel system | HE-DB-0010 | HE-EL-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | Issue ICR-Design Basis | Issue ICR- Datasheet for AC UPS | HE-DB-0010 | HE-EL-1870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | Final Issue for Design/ Construction-Design Basis | Issue ICR- Datasheet for Solar panel system | HE-EL-160 | HE-EL-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | Final Issue for Design/ Construction-Design Basis | Issue ICR- Datasheet for AC UPS | HE-EL-160 | HE-EL-1870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | Issue ICR-Design Basis | Final Issue for Design/ Construction-Electrical Adequacy Check Report | HE-DB-0010 | HE-EL-0170 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Issue ICR-Design Basis | Electrical | HE-DB-0010 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.22 UPS SLDs | Issue ICR-Design Basis | Final Issue for Design/ Construction-UPS SLD | HE-DB-0010 | HE-EL-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | Issue ICR-Design Basis | Final Issue for Design/ Construction-Data Sheet for LV cables | HE-DB-0010 | HE-EL-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | Issue ICR-Design Basis | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | HE-DB-0010 | HE-EL-0770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | Issue ICR-Design Basis | Final Issue for Design/ Construction-Data sheet for LV Distribution board | HE-DB-0010 | HE-EL-0650 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | Issue ICR-Design Basis | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | HE-DB-0010 | HE-EL-0710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | Issue ICR-Design Basis | Final Issue for Design/ Construction-Solar Panel System SLDs | HE-DB-0010 | HE-EL-0350 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | Issue ICR-Design Basis | Final Issue for Design/ Construction-Single Line Diagrams for LV Distribution Board | HE-DB-0010 | HE-EL-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | Issue ICR-Design Basis | Final Issue for Design/ Construction-Data Sheet for HV cables | HE-DB-0010 | HE-EL-1950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.3 Process Design Basis | P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | Issue ICR-Design Basis | Final Issue for Design/ Construction-Data Sheet for AC UPS | HE-DB-0010 | HE-EL-1860 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-Electrical Adequacy Check Report | HE-EL-160 | HE-EL-0170 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Design Basis | Electrical | HE-EL-160 | CAB-4450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.22 UPS SLDs | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-UPS SLD | HE-EL-160 | HE-EL-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-Data Sheet for LV cables | HE-EL-160 | HE-EL-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | HE-EL-160 | HE-EL-0770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-Data sheet for LV Distribution board | HE-EL-160 | HE-EL-0650 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | HE-EL-160 | HE-EL-0710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-Solar Panel System SLDs | HE-EL-160 | HE-EL-0350 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.2 Single Line Diagrams for LV Distribution Board | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-Single Line Diagrams for LV Distribution Board | HE-EL-160 | HE-EL-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-Data Sheet for HV cables | HE-EL-160 | HE-EL-1950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.56 Electrical Design Basis | P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-Data Sheet for AC UPS | HE-EL-160 | HE-EL-1860 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.7 Load List (Updates + New) | P2543-R01-Oct24..1.EN.9.A101 Electrical Adequacy Check Report | Receive Company Comments-Update /New Load List | Receive Company Comments- Adequacy report of the Power supply requirements | HE-EL-0080 | HE-EL-0140 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | Final Issue for Design/ Construction-UPS SLD | Final Issue for Design/ Construction-Cable Routing Layout | HE-EL-0290 | HE-EL-1610 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | Final Issue for Design/ Construction-Material Requisition for Distribution Transformer | HE-EL-0710 | HE-EL-1070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.25 Material Requisition for Distibution Transformers | P2543-R01-Oct24..1.EN.9.6.30 TBE for Distibution Transformers | Final Issue for Design/ Construction-Material Requisition for Distribution Transformer | Final Issue for Design/ Construction-TBE for Distribution Transformer | HE-EL-1070 | HE-EL-1490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | Final Issue for Design/ Construction-Data sheet for LV Distribution board | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | HE-EL-0650 | HE-EL-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..1.EN.9.6.28 TBE for Distribution Boards | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Final Issue for Design/ Construction-TBE for Distribution Boards | HE-EL-1010 | HE-EL-1430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.24 Material Requisition for Solar Panels | P2543-R01-Oct24..1.EN.9.6.8 TBE for Solar Panels | Final Issue for Design/ Construction-Material Requisition for Solar Panels | Final Issue for Design/ Construction-TBE for Solar Panels | HE-EL-1130 | HE-EL-1310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | Issue ICR-Data Sheet for HV cables | Issue ICR-Data Sheet for LV cables | HE-EL-1910 | HE-EL-0790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | Issue ICR-Data Sheet for LV cables | Issue ICR- Datasheet for AC UPS | HE-EL-0790 | HE-EL-1870 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | Issue ICR- Data sheet for LV Distribution board | Issue ICR-Data Sheet for HV cables | HE-EL-0610 | HE-EL-1910 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | Final Issue for Design/ Construction-Data Sheet for HV cables | Final Issue for Design/ Construction-Data Sheet for LV cables | HE-EL-1950 | HE-EL-0830 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.20 Material Requisition for Power & Control Cables | P2543-R01-Oct24..1.EN.9.6.26 TBE for Power & Control Cables | Final Issue for Design/ Construction-Material Requisition for Power & Control Cables | Final Issue for Design/ Construction-TBE for Power & Control Cables | HE-EL-1190 | HE-EL-1550 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..1.EN.9.1.18 Material Requisition for UPS System | Final Issue for Design/ Construction-Data Sheet for AC UPS | Final Issue for Design/ Construction-Material Requisition for UPS System | HE-EL-1860 | HE-EL-0950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.4 Material Requisition for Active/ Passive Shelters | P2543-R01-Oct24..1.EN.6.2.29 TBE for Active/ Passive Shelters | Final Issue for Design/ Construction-Material Requisition for Active/ Passive Shelters | Final Issue for Design/ Construction-TBE for Active/ Passive Shelters | HE-EL-0890 | HE-EL-1250 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.18 Material Requisition for UPS System | P2543-R01-Oct24..1.EN.9.6.27 TBE for UPS System | Final Issue for Design/ Construction-Material Requisition for UPS System | Final Issue for Design/ Construction-TBE for UPS System | HE-EL-0950 | HE-EL-1370 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.1 Material Requisition for LV Switchgear | P2543-R01-Oct24..1.EN.9.6.1 TBE for LV Switchgear | Final Issue for Design/ Construction-Material Requisition for LV Switchgear | Final Issue for Design/ Construction-TBE for LV Switchgear | HE-EL-2000 | HE-EL-2250 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.3 Material Requisition for MOV Isolator | P2543-R01-Oct24..1.EN.9.6.2 TBE for MOV Isolator | Final Issue for Design/ Construction-Material Requisition for MOV Isolator | Final Issue for Design/ Construction-TBE for MOV Isolator | HE-EL-2100 | HE-EL-2300 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.4 Material Requisition for Electrical Bulks (JBs, Fixtures, Sockets etc) | P2543-R01-Oct24..1.EN.9.6.4 TBE for Electrical Bulks (JBs, Fixtures, Sockets etc) | Final Issue for Design/ Construction-Material Requisition for Electrical Bulks | Final Issue for Design/ Construction-TBE for Electrical Bulks | HE-EL-2150 | HE-EL-2450 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.1.2 Material Requisition for Cable Glanding & Termination | P2543-R01-Oct24..1.EN.9.6.5 TBE for Cable Glanding & Termination | Final Issue for Design/ Construction-Material Requisition for Glanding & Termination | Final Issue for Design/ Construction-TBE for Glanding & Termination | HE-EL-2050 | HE-EL-2400 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.9.1.5 Material Requisition for Modification Works | P2543-R01-Oct24..1.EN.9.6.3 TBE for Modification Works | Final Issue for Design/ Construction-Material Requisition for Modification Works | Final Issue for Design/ Construction-TBE for Modification Works | HE-EL-2200 | HE-EL-2350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | Final Issue for Design/ Construction-Addendum to DGs | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | HE-IC-0050 | HE-IC-0110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | Final Issue for Design/ Construction-Addendum to DGs | Final Issue for Design/ Construction-Specification for RTU | HE-IC-0050 | HE-IC-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | Final Issue for Design/ Construction-Addendum to DGs | Final Issue for Design/ Construction-Specification for Leak Detection System | HE-IC-0050 | HE-IC-0290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | Final Issue for Design/ Construction- I&C Design Basis | Final Issue for Design/ Construction-Addendum to DGs | HE-IC-610 | HE-IC-0050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | Final Issue for Design/ Construction-Addendum to DGs | Re-Issue for Approval- Datasheets for Metering Skid | HE-IC-0050 | HE-IC-1170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | Obtain Company Approval- Data sheet for PRS (Pressure Reduction System) | HE-IC-0110 | HE-IC-1240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..1.EN.6.11.A161 Material Requisitions for Leak Detection System | Final Issue for Design/ Construction-Specification for Leak Detection System | Issue ICR-Material Requisitions for Leak Detection System | HE-IC-0290 | HE-IC-1750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A3 I/O list | Obtain Company Approval-Instrument index -Update | Obtain Company Approval- I/O list -Update | HE-IC-0520 | HE-IC-0580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..1.EN.6.A23 F&G Index | Obtain Company Approval- I/O list -Update | Obtain Company Approval-F&G index -Update | HE-IC-0580 | HE-IC-2780 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A23 F&G Index | P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | Obtain Company Approval-F&G index -Update | Obtain Company Approval- I/O list -Update | HE-IC-2780 | HE-IC-2710 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | Obtain Company Approval- I/O list -Update | Re-Issue for Approval - Typical Installation Drawings | HE-IC-2710 | HE-IC-0690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | Obtain Company Approval-Instrument Trench Layout | Obtain Company Approval-Instrument and F&G Cable Schedule | HE-IC-1000 | HE-IC-0940 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | P2543-R01-Oct24..1.EN.6.11.A131 Material Requisitions for ROV/ GOV | Obtain Company Approval- Datasheet for GOV & ROV | Obtain Company Approval- Material Requisitions for ROV/ GOV | HE-IC-1120 | HE-IC-1660 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | P2543-R01-Oct24..1.EN.6.11.A17 Material Requisitions for Metering Skid | Obtain Company Approval- Datasheets for Metering Skid | Obtain Company Approval- Material Requisitions for Metering Skid | HE-IC-1180 | HE-IC-1840 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A7 Data sheet for Pressure Reduction System | P2543-R01-Oct24..1.EN.6.11.A16 Material Requisitions for PRS (Pressure Reduction Skid) | Obtain Company Approval- Data sheet for PRS (Pressure Reduction System) | Obtain Company Approval-Material Requisitions for PRS | HE-IC-1240 | HE-IC-1720 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A5 Datasheets for PSV & Orifics (incl. RO) | P2543-R01-Oct24..1.EN.6.11.2 Material Requisitions for Field Instruments / H2S Analyzers | Obtain Company Approval- Datasheets for PSV & Orifice (incl. RO) | Obtain Company Approval- Material Requisitions for Field Instruments / H2S Analyzers | HE-IC-1360 | HE-IC-1960 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..1.EN.6.11.43 Material Requisition for Pig Signaler | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Final Issue for Design/ Construction-Material Requisition for Pig Signaler | HE-IC-1430 | HE-PL-1970 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.43 Material Requisition for Pig Signaler | P2543-R01-Oct24..1.EN.6.2.54 TBE for Pig Signaler | Final Issue for Design/ Construction-Material Requisition for Pig Signaler | Final Issue for Design/ Construction-TBE for Pig Signaler | HE-PL-1970 | HE-PL-2370 | FF | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..1.EN.6.11.9 Material Requisitions for Fire & Gas Detectors | Obtain Company Approval- Datasheets for F&G Devices | Obtain Company Approval- Material Requisitions for Gas Detectors | HE-IC-1540 | HE-IC-1900 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.7 Material Requisitions for Junction Boxes | P2543-R01-Oct24..1.EN.6.2.8 TBE for Junction Boxes | Final Issue for Design/ Construction-Material Requisitions for Junction Boxes | Final Issue for Design/ Construction-TBE for Junction Boxes | HE-IC-2030 | HE-IC-2510 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.6 TBE for MOV | P2543-R01-Oct24..PR.26.LL.9.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-TBE for MOV | Manufacturing & Assembly of MOV | HE-IC-2090 | HM-ME-0620 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.2.6 TBE for MOV | P2543-R01-Oct24..1.1.2.LL.9.1 Ordering | Obtain Company Approval- TBE for MOV | Prepare TBE and Company approval for MOV | HE-IC-2080 | HP-ME-0320 | FF | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.9.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.9.2 Manufacturing & Ready for Dispatch | Vendor Document Review of MOV | Manufacturing & Assembly of MOV | HM-ME-0610 | HM-ME-0620 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.6.11.A1311 Material Requisitions for MOV | P2543-R01-Oct24..1.EN.6.2.6 TBE for MOV | Final Issue for Design/ Construction-Material Requisitions for MOV | Final Issue for Design/ Construction-TBE for MOV | HE-IC-1610 | HE-IC-2090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.3 TBE for Field Instruments / H2S Analyzers | P2543-R01-Oct24..PR.26.1.15.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-TBE for Field Instruments / H2S Analyzers | Vendor Document Review of Field Instruments | HE-IC-2450 | HM-ME-1520 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Final Issue for Design/ Construction-Instrument Index | Instrument 1st MTO | HE-IC-0530 | HE-IC-2590 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | P2543-R01-Oct24..1.EN.10.A21121 Typical Inter Connection Diagram for Pig Launcher/Receiver | Final Issue for Design/ Construction-Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Final Issue for Design/ Construction-Typical Inter Connection Diagram for Pig Launcher/Receiver | HE-TL-0230 | HE-TL-1040 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | P2543-R01-Oct24..1.EN.10.A21121 Typical Inter Connection Diagram for Pig Launcher/Receiver | Final Issue for Design/ Construction-Design Basis | Issue ICR- Typical Inter Connection Diagram for Pig Launcher/Receiver | HE-TL-2470 | HE-TL-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A321 Telecom Equipment List | P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | Final Issue for Design/ Construction-Telecom Equipment List | Issue ICR-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-980 | HE-TL-0610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..1.EN.10.2 Telecom MTO | Final Issue for Design/ Construction-Telecom cable schedule | Telecom 2nd MTO | HE-TL-0830 | HE-TL-0870 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | P2543-R01-Oct24..1.EN.10.2 Telecom MTO | Obtain Company Approval-Telecom Typical Hookup | Telecom 3rd MTO | HE-TL-920 | HE-TL-0890 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.10.1 Datasheet for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Final Issue for Design/ Construction-Datasheets for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Final Issue for Design/ Construction-Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc. | HE-TL-0530 | HE-TL-0590 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.10.8 Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..1.EN.10.11 TBE for Telecom System | Final Issue for Design/ Construction-Material Requisitions for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc. | Final Issue for Design/ Construction-TBE for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0590 | HE-TL-0650 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.10.56 Telecom Design Basis | P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | Final Issue for Design/ Construction-Design Basis | Final Issue for Design/ Construction-Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-2470 | HE-TL-0230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | P2543-R01-Oct24..1.EN.10.A321 Telecom Equipment List | Final Issue for Design/ Construction-Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | Final Issue for Design/ Construction-Telecom Equipment List | HE-TL-0230 | HE-TL-980 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A191 Telecom Design Philosphy for LAN, SDH, CCTV, PIDS, IDS | P2543-R01-Oct24..1.EN.10.A281 Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc)-1 | Final Issue for Design/ Construction-Telecom Design Philosophy for LAN, SDH, CCTV, PIDS, IDS | Final Issue for Design/ Construction-Specification for Telecom systems (CCTV, Telephone, LAN, SDH, PIDS, IDS etc.) | HE-TL-0110 | HE-TL-0230 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A2112 Telecom Inter Connection Diagram | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Telecom Inter Connection Diagram | Issue ICR-Construction Procedures / Method Statements / ITPs | HE-TL-990 | C-COM-750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21121 Typical Inter Connection Diagram for Pig Launcher/Receiver | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Typical Inter Connection Diagram for Pig Launcher/Receiver | Issue ICR-Construction Procedures / Method Statements / ITPs | HE-TL-1040 | C-COM-750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21121111 Narrative For Intrusion Detection System | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Issue ICR-Construction Procedures / Method Statements / ITPs | HE-TL-1190 | C-COM-750 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.4 Project HSE Plan | P2543-R01-Oct24..1.EN.4.3 Project HSE Philosophy | Final Issue for Design/ Construction-Project HSE Plan | Final Issue for Design/ Construction-Project HSE Philosophy | HE-HS-0050 | HE-HS-0110 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.2 HAZOP Procedure | P2543-R01-Oct24..1.PM.12 Workshops | Final Issue for Design/ Construction-HAZOP Procedure | HAZOP Workshop | HE-HS-0230 | HE-WS-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.5 F&G layout | P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | Final Issue for Design/ Construction-F&G layout | Obtain Company Approval-F&G Cause and Effect | HE-HS-0290 | HE-HS-0340 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | P2543-R01-Oct24..1.EN.4.16 Datasheets for fire fighting and safety equipment | Obtain Company Approval-Fire Fighting & Safety Eqpt. Layout | Obtain Company Approval-Data Sheets for Fire Fighting & Safety Eqpt | HE-HS-0400 | HE-HS-0460 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.16 Datasheets for fire fighting and safety equipment | P2543-R01-Oct24..1.EN.4.9 HSE Action Tracking Register (Hazards and Effects Register) | Obtain Company Approval-Data Sheets for Fire Fighting & Safety Eqpt | Obtain Company Approval-HSE Action Tracking Register (Hazards and Effects Register) | HE-HS-0460 | HE-HS-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.10 HAZID/ ENVID/ OHID Report | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | Final Issue for Design/ Construction-HAZID/ ENVID/ OHID Report | Final Issue for Design/ Construction-HAZOP Review Report | HE-HS-0590 | HE-HS-0710 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.4.19 HAZID/ ENVID/ OHID Close out Report | Final Issue for Design/ Construction-HAZOP Review Report | Final Issue for Design/ Construction-HAZID/ ENVID/ OHID Close out Report | HE-HS-0710 | HE-HS-0650 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.11 QRA Report | P2543-R01-Oct24..1.EN.4.21 HAZOP close out report | Final Issue for Design/ Construction-QRA Report | Final Issue for Design/ Construction-HAZOP close out report | HE-HS-0830 | HE-HS-0770 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.12.A11111 MR for Material Handling Equipment | P2543-R01-Oct24..1.EN.12.A111111 TBE for Material Handling Equipment | Final Issue for Design/ Construction-Material Requisition for Material Handling | Final Issue for Design/ Construction- TBE for Material Handling | HE-HV-2880 | HE-HV-2930 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.12.A11111 MR for Material Handling Equipment | P2543-R01-Oct24..1.1.2.25.3.1 Ordering | Issue ICR- Material Requisition for Material Handling | RFQ, Receipt of Bid for HVAC Equipment | HE-HV-2840 | HP-ME-0860 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | Final Issue for Design/ Construction-Shutdown Requirements & Plan | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | C-COM-890 | C-COM-840 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | ML1219-B49 | ML1219-B39 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | ML1219-B39 | ML1059-B28 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | Issue Purchase Order (Final) - Line pipes | Vendor Document Review of Line Pipes - Lot 1 | ML1040-C01 | HM-PL-0010 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Project Kick off Meeting | Instrumentation & Control | ML1002 | CAB-4460 | SS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | Project Kick off Meeting | Final Issue for Design/ Construction-Datasheets for Custody Flow Metering Skid | ML1002 | HE-IC-1190 | SS | Completed | In Progress | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.6.4.A6 Datasheets for Custody Flow Metering Skid | Project Kick off Meeting | Issue ICR- Datasheets for Metering Skid | ML1002 | HE-IC-1150 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.6.4.A8 Datasheet for GOV & ROV | Project Kick off Meeting | Issue ICR- Datasheet for GOV & ROV | ML1002 | HE-IC-1090 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.6.4.A9 Datasheet for MOVs | Project Kick off Meeting | Issue ICR- Datasheet for MOV | ML1002 | HE-IC-1030 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | Project Kick off Meeting | Issue ICR - Overall Pipeline Route Map - 52" | ML1002 | HE-PL-0190 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | Project Kick off Meeting | Issue ICR - Overall Pipeline Route Map - 56" | ML1002 | HE-PL-0130 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.3.20.13 Process Datasheets - MOV | Project Kick off Meeting | Issue ICR- Process Datasheets | ML1002 | HE-PR-0550 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.3.20.16 Process Datasheets - Custody Transfer Metering Skid - (At Sweihan CRS) | Project Kick off Meeting | Issue ICR- Process Datasheets - Custody Metering Skid - (at Sweihan CRS) | ML1002 | HE-PR-0310 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.5.12 Addendum to DGS (Pressure Vessels) | Project Kick off Meeting | Issue ICR- Addendum to DGS | ML1002 | HE-ME-0010 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.3.20.21 Process Datasheets - Filters (At Sweihan CRS) | Project Kick off Meeting | Issue ICR- Process Datasheets - Filters (At Sweihan CRS) | ML1002 | HE-PR-0430 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.3.20.12 Process Datasheets - Pressure Reduction System (At Sweihan CRS) | Project Kick off Meeting | Issue ICR- Process Datasheets - PRS Skid (at Sweihan CRS) | ML1002 | HE-PR-0370 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | Project Kick off Meeting | Issue ICR - Overall Pipeline Route Map - 4" | ML1002 | HE-PL-0250 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | Project Kick off Meeting | Issue ICR- Specifications for PRS (Pressure Reduction System) | ML1002 | HE-IC-0070 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.5.1 Design Basis | Project Kick off Meeting | Issue ICR- Mechanical Design Basis | ML1002 | HE-ME-270 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.3.20.1 Process Datasheets - ROV | Project Kick off Meeting | Issue ICR- Process Datasheets | ML1002 | HE-PR-1260 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.3.20.2 Process Datasheets - PRV | Project Kick off Meeting | Issue ICR- Process Datasheets | ML1002 | HE-PR-1310 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.3.20.3 Process Datasheets - Temprature Transmitters | Project Kick off Meeting | Issue ICR- Process Datasheets | ML1002 | HE-PR-1360 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.3.20.4 Process Datasheets - Temprature Guage | Project Kick off Meeting | Issue ICR- Process Datasheets | ML1002 | HE-PR-1410 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.3.20.5 Process Datasheets - Pressure Transmitters | Project Kick off Meeting | Issue ICR- Process Datasheets | ML1002 | HE-PR-1460 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.3.20.6 Process Datasheets - Pressure Guage | Project Kick off Meeting | Issue ICR- Process Datasheets | ML1002 | HE-PR-1510 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.3.20.7 Process Datasheets - Restriction Orifice Pipeline | Project Kick off Meeting | Issue ICR- Process Datasheets | ML1002 | HE-PR-1560 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.EN.6.3 I&C Design Basis | Project Kick off Meeting | Issue ICR- I&C Design Basis | ML1002 | HE-IC-620 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Project Kick off Meeting | General | ML1002 | CAB-5290 | SS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..1.PM.12 Workshops | Project Kick off Meeting | Design Review Workshop | ML1002 | HE-WS-0030 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | HAZOP Workshop | Study & Issue ICR- HSEIA Study Report | HE-WS-0210 | HE-HS-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | HAZOP Workshop | Issue ICR- HAZOP reviews Report for all areas | HE-WS-0210 | HE-HS-0670 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.14 Pipeline Coating MTO | P2543-R01-Oct24..1.EN.1.14 Pipeline Coating MTO | Re-Issue for Approval - Pipeline Coating MTO | Obtain Company Approval - Pipeline Coating MTO | HE-PL-3750 | HE-PL-3760 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.14 Pipeline Coating MTO | P2543-R01-Oct24..1.EN.1.14 Pipeline Coating MTO | Receive Company Comments - Pipeline Coating MTO | Re-Issue for Approval - Pipeline Coating MTO | HE-PL-3740 | HE-PL-3750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.14 Pipeline Coating MTO | P2543-R01-Oct24..1.EN.1.14 Pipeline Coating MTO | Obtain Company Approval - Pipeline Coating MTO | Final Issue for Design/ Construction-Pipeline Coating MTO | HE-PL-3760 | HE-PL-3770 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.14 Pipeline Coating MTO | P2543-R01-Oct24..1.EN.1.14 Pipeline Coating MTO | Issue ICR - Pipeline Coating MTO | Receive Company Comments - Pipeline Coating MTO | HE-PL-3730 | HE-PL-3740 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.33 Pipeline MTO - 56", 52" and 4" | P2543-R01-Oct24..1.EN.1.14 Pipeline Coating MTO | Issue ICR - Pipeline MTO - 56" | Issue ICR - Pipeline Coating MTO | HE-PL-3230 | HE-PL-3730 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.14 Pipeline Coating MTO | P2543-R01-Oct24..PR.1.16.2.1 Lot 1 | Final Issue for Design/ Construction-Pipeline Coating MTO | Complete External / Internal Coating - Lot 1 | HE-PL-3770 | HM-PL-0035 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.16 Pipeline Support Schdule | P2543-R01-Oct24..1.EN.1.16 Pipeline Support Schdule | Re-Issue for Approval - Pipeline Support Schedule | Obtain Company Approval - Pipeline Support Schedule | HE-PL-3800 | HE-PL-3810 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.16 Pipeline Support Schdule | P2543-R01-Oct24..1.EN.1.16 Pipeline Support Schdule | Receive Company Comments - Pipeline Support Schedule | Re-Issue for Approval - Pipeline Support Schedule | HE-PL-3790 | HE-PL-3800 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.16 Pipeline Support Schdule | P2543-R01-Oct24..1.EN.1.16 Pipeline Support Schdule | Obtain Company Approval - Pipeline Support Schedule | Final Issue for Design/ Construction- Pipeline Support Schedule | HE-PL-3810 | HE-PL-3820 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.16 Pipeline Support Schdule | P2543-R01-Oct24..1.EN.1.16 Pipeline Support Schdule | Issue ICR - Pipeline Support Schedule | Receive Company Comments - Pipeline Support Schedule | HE-PL-3780 | HE-PL-3790 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.58 Pipeline Tie In List | P2543-R01-Oct24..1.EN.1.16 Pipeline Support Schdule | Issue ICR - Pipeline Tie In List | Issue ICR - Pipeline Support Schedule | HE-PL-3330 | HE-PL-3780 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.3 Hazardous Area Register | P2543-R01-Oct24..1.EN.9.3 Hazardous Area Register | Issue ICR-Hazardous Area Register | Receive Company Comments-Hazardous Area Register | HE-EL-5530 | HE-EL-5490 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.3 Hazardous Area Register | P2543-R01-Oct24..1.EN.9.3 Hazardous Area Register | Obtain Company Approval-Hazardous Area Register | Final Issue for Design/ Construction-Hazardous Area Register | HE-EL-5510 | HE-EL-5520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.3 Hazardous Area Register | P2543-R01-Oct24..1.EN.9.3 Hazardous Area Register | Re-Issue for Approval-Hazardous Area Register | Obtain Company Approval-Hazardous Area Register | HE-EL-5500 | HE-EL-5510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.3 Hazardous Area Register | P2543-R01-Oct24..1.EN.9.3 Hazardous Area Register | Receive Company Comments-Hazardous Area Register | Re-Issue for Approval-Hazardous Area Register | HE-EL-5490 | HE-EL-5500 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.14 HAZOP Review Report (Vendor) | P2543-R01-Oct24..1.EN.4.14 HAZOP Review Report (Vendor) | Receive Company Comments- HAZOP Review Report (Vendor) | Re-Issue for Approval- HAZOP Review Report (Vendor) | HE-HS-1230 | HE-HS-1240 | FF | Completed | Completed | 5
P2543-R01-Oct24..1.EN.4.14 HAZOP Review Report (Vendor) | P2543-R01-Oct24..1.EN.4.14 HAZOP Review Report (Vendor) | Obtain Company Approval- HAZOP Review Report (Vendor) | Final Issue for Design/ Construction-HAZOP Review Report (Vendor) | HE-HS-1200 | HE-HS-1210 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.4.14 HAZOP Review Report (Vendor) | P2543-R01-Oct24..1.EN.4.14 HAZOP Review Report (Vendor) | Re-Issue for Approval- HAZOP Review Report (Vendor) | Obtain Company Approval- HAZOP Review Report (Vendor) | HE-HS-1240 | HE-HS-1200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.14 HAZOP Review Report (Vendor) | P2543-R01-Oct24..1.EN.4.14 HAZOP Review Report (Vendor) | Issue ICR- HAZOP Review Report (Vendor) | Receive Company Comments- HAZOP Review Report (Vendor) | HE-HS-1220 | HE-HS-1230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.22 HAZOP close out report (Vendor) | P2543-R01-Oct24..1.EN.4.22 HAZOP close out report (Vendor) | Receive Company Comments- HAZOP Closeout Report (Vendor) | Re-Issue for Approval- HAZOP Closeout Report (Vendor) | HE-HS-1280 | HE-HS-1290 | FF | Completed | Completed | 5
P2543-R01-Oct24..1.EN.4.22 HAZOP close out report (Vendor) | P2543-R01-Oct24..1.EN.4.22 HAZOP close out report (Vendor) | Obtain Company Approval- HAZOP Closeout Report (Vendor) | Final Issue for Design/ Construction-HAZOP Closeout Report (Vendor) | HE-HS-1250 | HE-HS-1260 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.4.22 HAZOP close out report (Vendor) | P2543-R01-Oct24..1.EN.4.22 HAZOP close out report (Vendor) | Re-Issue for Approval- HAZOP Closeout Report (Vendor) | Obtain Company Approval- HAZOP Closeout Report (Vendor) | HE-HS-1290 | HE-HS-1250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.22 HAZOP close out report (Vendor) | P2543-R01-Oct24..1.EN.4.22 HAZOP close out report (Vendor) | Issue ICR- HAZOP Closeout Report (Vendor) | Receive Company Comments- HAZOP Closeout Report (Vendor) | HE-HS-1270 | HE-HS-1280 | FF | Completed | Completed | 10
P2543-R01-Oct24..1.EN.4.14 HAZOP Review Report (Vendor) | P2543-R01-Oct24..1.EN.4.22 HAZOP close out report (Vendor) | Issue ICR- HAZOP Review Report (Vendor) | Issue ICR- HAZOP Closeout Report (Vendor) | HE-HS-1220 | HE-HS-1270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.14 HAZOP Review Report (Vendor) | P2543-R01-Oct24..1.EN.4.22 HAZOP close out report (Vendor) | Final Issue for Design/ Construction-HAZOP Review Report (Vendor) | Final Issue for Design/ Construction-HAZOP Closeout Report (Vendor) | HE-HS-1210 | HE-HS-1260 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.4.22 HAZOP close out report (Vendor) | P2543-R01-Oct24..PR.26.1.13.2 Manufacturing & Ready for Dispatch | Final Issue for Design/ Construction-HAZOP Closeout Report (Vendor) | Manufacturing & Assembly of Fire Fighting & Safety Equipment | HE-HS-1260 | HM-ME-1930 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A911 Addendum to F&G System | P2543-R01-Oct24..1.EN.6.A911 Addendum to F&G System | Obtain Company Approval- Addendum to DGs | Final Issue for Design/ Construction-Addendum to DGs | HE-IC-2970 | HE-IC-2980 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A911 Addendum to F&G System | P2543-R01-Oct24..1.EN.6.A911 Addendum to F&G System | Issue ICR- Addendum to DGs | Receive Company Comments- Addendum to DGs | HE-IC-2940 | HE-IC-2950 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A911 Addendum to F&G System | P2543-R01-Oct24..1.EN.6.A911 Addendum to F&G System | Re-Issue for Approval- Addendum to DGs | Obtain Company Approval- Addendum to DGs | HE-IC-2960 | HE-IC-2970 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A911 Addendum to F&G System | P2543-R01-Oct24..1.EN.6.A911 Addendum to F&G System | Receive Company Comments- Addendum to DGs | Re-Issue for Approval- Addendum to DGs | HE-IC-2950 | HE-IC-2960 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..1.EN.6.A911 Addendum to F&G System | Issue ICR- Addendum to DGs | Issue ICR- Addendum to DGs | HE-IC-0010 | HE-IC-2940 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A911 Addendum to F&G System | P2543-R01-Oct24..1.EN.6.A23 F&G Index | Final Issue for Design/ Construction-Addendum to DGs | Issue ICR-F&G index -Update | HE-IC-2980 | HE-IC-2750 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.3 Material Requisitions for Instrument Cables | P2543-R01-Oct24..1.EN.6.11.3 Material Requisitions for Instrument Cables | Re-Issue for Approval- Material Requisitions for Instrument Cables | Obtain Company Approval- Material Requisitions for Instrument Cables | HE-IC-3000 | HE-IC-3020 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.3 Material Requisitions for Instrument Cables | P2543-R01-Oct24..1.EN.6.11.3 Material Requisitions for Instrument Cables | Receive Company Comments- Material Requisitions for Instrument Cables | Re-Issue for Approval- Material Requisitions for Instrument Cables | HE-IC-2990 | HE-IC-3000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.3 Material Requisitions for Instrument Cables | P2543-R01-Oct24..1.EN.6.11.3 Material Requisitions for Instrument Cables | Issue ICR- Material Requisitions for Instrument Cables | Receive Company Comments- Material Requisitions for Instrument Cables | HE-IC-3030 | HE-IC-2990 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.3 Material Requisitions for Instrument Cables | P2543-R01-Oct24..1.EN.6.11.3 Material Requisitions for Instrument Cables | Obtain Company Approval- Material Requisitions for Instrument Cables | Final Issue for Design/ Construction-Material Requisitions for Instrument Cables | HE-IC-3020 | HE-IC-3010 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.2 TBE for Instrument Cables | P2543-R01-Oct24..1.EN.6.2.2 TBE for Instrument Cables | Obtain Company Approval- TBE for Instrument Cables | Final Issue for Design/ Construction-TBE for Instrument Cables | HE-IC-3080 | HE-IC-3040 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.2.2 TBE for Instrument Cables | P2543-R01-Oct24..1.EN.6.2.2 TBE for Instrument Cables | Re-Issue for Approval- TBE for Instrument Cables | Obtain Company Approval- TBE for Instrument Cables | HE-IC-3070 | HE-IC-3080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.2 TBE for Instrument Cables | P2543-R01-Oct24..1.EN.6.2.2 TBE for Instrument Cables | Receive Company Comments- TBE for Instrument Cables | Re-Issue for Approval- TBE for Instrument Cables | HE-IC-3060 | HE-IC-3070 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.2 TBE for Instrument Cables | P2543-R01-Oct24..1.EN.6.2.2 TBE for Instrument Cables | Issue ICR- TBE for Instrument Cables | Receive Company Comments- TBE for Instrument Cables | HE-IC-3050 | HE-IC-3060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.11.3 Material Requisitions for Instrument Cables | P2543-R01-Oct24..1.EN.6.2.2 TBE for Instrument Cables | Issue ICR- Material Requisitions for Instrument Cables | Issue ICR- TBE for Instrument Cables | HE-IC-3030 | HE-IC-3050 | FS | Completed | Completed | 20
P2543-R01-Oct24..1.EN.6.11.3 Material Requisitions for Instrument Cables | P2543-R01-Oct24..1.EN.6.2.2 TBE for Instrument Cables | Final Issue for Design/ Construction-Material Requisitions for Instrument Cables | Final Issue for Design/ Construction-TBE for Instrument Cables | HE-IC-3010 | HE-IC-3040 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..1.EN.6.11.3 Material Requisitions for Instrument Cables | Issue ICR-Instrument and F&G Cable Schedule | Issue ICR- Material Requisitions for Instrument Cables | HE-IC-0910 | HE-IC-3030 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.2.2 TBE for Instrument Cables | P2543-R01-Oct24..1.EN.6.A39 Instrument MTO | Final Issue for Design/ Construction-TBE for Instrument Cables | Instrument 2nd MTO | HE-IC-3040 | HE-IC-2610 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A271 Instrument Termination Drawings | P2543-R01-Oct24..1.EN.6.A271 Instrument Termination Drawings | Re-Issue for Approval- Instrument Termination Drawings | Obtain Company Approval-Instrument Termination Drawings | HE-IC-3100 | HE-IC-3110 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A271 Instrument Termination Drawings | P2543-R01-Oct24..1.EN.6.A271 Instrument Termination Drawings | Issue ICR- Instrument Termination Drawings | Receive Company Comments- Instrument Termination Drawings | HE-IC-3090 | HE-IC-3130 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A271 Instrument Termination Drawings | P2543-R01-Oct24..1.EN.6.A271 Instrument Termination Drawings | Obtain Company Approval-Instrument Termination Drawings | Final Issue for Design/ Construction-Instrument Termination Drawings | HE-IC-3110 | HE-IC-3120 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A271 Instrument Termination Drawings | P2543-R01-Oct24..1.EN.6.A271 Instrument Termination Drawings | Receive Company Comments- Instrument Termination Drawings | Re-Issue for Approval- Instrument Termination Drawings | HE-IC-3130 | HE-IC-3100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2711 F&G Termination Drawings | P2543-R01-Oct24..1.EN.6.A2711 F&G Termination Drawings | Re-Issue for Approval- F&G Termination Drawings | Obtain Company Approval- F&G Termination Drawings | HE-IC-3150 | HE-IC-3160 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2711 F&G Termination Drawings | P2543-R01-Oct24..1.EN.6.A2711 F&G Termination Drawings | Issue ICR- F&G Termination Drawings | Receive Company Comments- F&G Termination Drawings | HE-IC-3140 | HE-IC-3180 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2711 F&G Termination Drawings | P2543-R01-Oct24..1.EN.6.A2711 F&G Termination Drawings | Obtain Company Approval- F&G Termination Drawings | Final Issue for Design/ Construction- F&G Termination Drawings | HE-IC-3160 | HE-IC-3170 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2711 F&G Termination Drawings | P2543-R01-Oct24..1.EN.6.A2711 F&G Termination Drawings | Receive Company Comments- F&G Termination Drawings | Re-Issue for Approval- F&G Termination Drawings | HE-IC-3180 | HE-IC-3150 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A271 Instrument Termination Drawings | P2543-R01-Oct24..1.EN.6.A2711 F&G Termination Drawings | Issue ICR- Instrument Termination Drawings | Issue ICR- F&G Termination Drawings | HE-IC-3090 | HE-IC-3140 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A271 Instrument Termination Drawings | P2543-R01-Oct24..1.EN.6.A2711 F&G Termination Drawings | Final Issue for Design/ Construction-Instrument Termination Drawings | Final Issue for Design/ Construction- F&G Termination Drawings | HE-IC-3120 | HE-IC-3170 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..1.EN.6.A271 Instrument Termination Drawings | Issue ICR- Instrument location and Cable Routing Drawings | Issue ICR- Instrument Termination Drawings | HE-IC-2530 | HE-IC-3090 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.23 ISD Closeout Report | P2543-R01-Oct24..1.EN.4.23 ISD Closeout Report | Obtain Company Approval- ISD Closeout Report | Final Issue for Design/ Construction- ISD Closeout Report | HE-HS-1330 | HE-HS-1340 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.4.23 ISD Closeout Report | P2543-R01-Oct24..1.EN.4.23 ISD Closeout Report | Re-Issue for Approval- ISD Closeout Report | Obtain Company Approval- ISD Closeout Report | HE-HS-1320 | HE-HS-1330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.23 ISD Closeout Report | P2543-R01-Oct24..1.EN.4.23 ISD Closeout Report | Receive Company Comments- ISD Closeout Report | Re-Issue for Approval- ISD Closeout Report | HE-HS-1310 | HE-HS-1320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.23 ISD Closeout Report | P2543-R01-Oct24..1.EN.4.23 ISD Closeout Report | Issue ICR- ISD Closeout Report | Receive Company Comments- ISD Closeout Report | HE-HS-1300 | HE-HS-1310 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.11 QRA Report | P2543-R01-Oct24..1.EN.4.23 ISD Closeout Report | Issue ICR-QRA Report | Issue ICR- ISD Closeout Report | HE-HS-0790 | HE-HS-1300 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..1.2.12.11 Hot Tapping | Receive Company Comments-Isolation & Tie-In philosophy | Hot Tapping RFQ & Quotation Receipt | HE-PR-0860 | HS-CN-0510 | FS | Completed | Completed | 14
P2543-R01-Oct24..1.2.12.11 Hot Tapping | P2543-R01-Oct24..1.EN.1.40 Specification - Split Tee | Hot Tapping Subcontract Award | Issue ICR - Specification - Split Tee | HS-CN-0540 | HE-PL-0430 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.1.2.25.23.1 Ordering | P2543-R01-Oct24..1.EN.9.6.1 TBE for LV Switchgear | RFQ, Receipt of Bid for LV Switch Gear | Issue ICR-TBE for LV Switchgear | HP-ME-1330 | HE-EL-2210 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Vendor Documents Package | HM-ME-2210 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Receive at Site - MOV/ROV/GOV Valves | HM-ME-2210 | ML1024-D06 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Receive at Site - E&I Equipment's (RTUs) | HM-ME-2210 | ML1469-D13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | Ready for Dispatch of ROV/ GOV | Transportation/ Custom Clearance/ Delivery at site of ROV/ GOV (2nd Lot) | HM-ME-0550 | HM-ME-2220 | FS | Not Started | Not Started | 15
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of ROV/ GOV (2nd Lot) | Receipt at site and inspection of ROV/ GOV (2nd Lot) | HM-ME-2220 | HM-ME-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | Manufacturing & Assembly of ROV/ GOV | Transportation/ Custom Clearance/ Delivery at site of ROV/ GOV (1st Lot) | HM-ME-0520 | HM-ME-0570 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of ROV/ GOV (1st Lot) | Receipt at site and inspection of ROV/ GOV (1st Lot) | HM-ME-0570 | HM-ME-0580 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of MOV (Lot 1) | Receipt at site and inspection of Isolator (Lot 1) | HM-ME-2230 | HM-ME-0690 | FS | Not Started | Not Started | 8
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of MOV (Lot 1) | Receipt at site and inspection of MOV (Lot 1) | HM-ME-2230 | HM-ME-0680 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | Manufacturing & Assembly of MOV | Transportation/ Custom Clearance/ Delivery at site of MOV (Lot 1) | HM-ME-0620 | HM-ME-2230 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of MOV (Lot 2) | Receipt at site and inspection of MOV (Lot 2) | HM-ME-0670 | HM-ME-2240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of MOV (Lot 2) | Receive at Site - E&I Equipment's (RTUs) | HM-ME-2240 | ML1469-D13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of MOV (Lot 2) | Receive at Site - MOV/ROV/GOV Valves | HM-ME-2240 | ML1024-D06 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of MOV (Lot 2) | Vendor Documents Package | HM-ME-2240 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | HM-ME-2260 | HM-ME-2270 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Receive at Site - E&I Equipment's (IDS & PIDS System) | HM-ME-2270 | ML1479-D15 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Vendor Documents Package | HM-ME-2270 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Receive at Site - E&I Equipment's (CCTV System) | HM-ME-2270 | ML1056-D14 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | Ready for Dispatch of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Transportation/ Custom Clearance/ Delivery at site of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | HM-ME-1260 | HM-ME-2260 | FS | Not Started | Not Started | 20
P2543-R01-Oct24..PR.26.LL.4.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | Manufacturing & Assembly of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | Transportation/ Custom Clearance/ Delivery at site of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | HM-ME-1230 | HM-ME-1280 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | Ready for Dispatch of Access Switch, Fiber Optic Patch Panel and Media Converter | Transportation/ Custom Clearance/ Delivery at site of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | HM-ME-1360 | HM-ME-2280 | FS | Not Started | Not Started | 21
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | Receive at Site - E&I Equipment's (IDS & PIDS System) | HM-ME-2290 | ML1479-D15 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | HM-ME-2280 | HM-ME-2290 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | Vendor Documents Package | HM-ME-2290 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | Manufacturing & Assembly of Access Switch, Fiber Optic Patch Panel and Media Converter | Transportation/ Custom Clearance/ Delivery at site of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | HM-ME-1330 | HM-ME-1380 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | Ready for Dispatch of Gas Detectors | Transportation/ Custom Clearance/ Delivery at site of Gas Detectors (Lot 2) | HM-ME-1460 | HM-ME-2300 | FS | Not Started | Not Started | 20
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Gas Detectors (Lot 2) | Receive at Site - F & G System | HM-ME-2310 | ML2089-D16 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Gas Detectors (Lot 2) | Receipt at site and inspection of Gas Detectors (Lot 2) | HM-ME-2300 | HM-ME-2310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | Manufacturing & Assembly of Gas Detectors | Transportation/ Custom Clearance/ Delivery at site of Gas Detectors (Lot 1) | HM-ME-1430 | HM-ME-1480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | Project Kick off Meeting | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | ML1002 | HM-ME-2330 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Field Instruments (Lot 2) | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | HM-ME-2320 | HM-ME-2330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | Ready for Dispatch of Field Instruments | Transportation/ Custom Clearance/ Delivery at site of Field Instruments (Lot 2) | HM-ME-1560 | HM-ME-2320 | FS | Not Started | Not Started | 21
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Receive at Site - F & G System | HM-ME-2330 | ML2089-D16 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | Manufacturing & Assembly of Field Instruments | Transportation/ Custom Clearance/ Delivery at site of Field Instruments (Lot 1) | HM-ME-1530 | HM-ME-1580 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | Project Kick off Meeting | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | ML1002 | HM-ME-2350 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | Ready for Dispatch of Junction Boxes | Transportation/ Custom Clearance/ Delivery at site of Junction Boxes (Lot 2) | HM-ME-1660 | HM-ME-2340 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Junction Boxes (Lot 2) | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | HM-ME-2340 | HM-ME-2350 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | Manufacturing & Assembly of Junction Boxes | Transportation/ Custom Clearance/ Delivery at site of Junction Boxes (Lot 1) | HM-ME-1630 | HM-ME-1680 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | Ready for Dispatch of Fire Fighting & Safety Equipment | Transportation/ Custom Clearance/ Delivery at site of Fire Fighting & Safety Equipment (Lot 2) | HM-ME-1960 | HM-ME-2360 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Fire Fighting & Safety Equipment (Lot 2) | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 2) | HM-ME-2360 | HM-ME-2370 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | Manufacturing & Assembly of Fire Fighting & Safety Equipment | Transportation/ Custom Clearance/ Delivery at site of Fire Fighting & Safety Equipment (Lot 1) | HM-ME-1930 | HM-ME-1980 | SS | Not Started | Not Started | 150
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of FOC Cables (Lot 2) | Receive at Site - Fiber Optic Cable | HM-EL-610 | ML1057-D19 | FF | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.19.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | Ready for Dispatch of FOC Cables | Transportation/ Custom Clearance/ Delivery at site of FOC Cables (Lot 2) | HM-EL-0150 | HM-EL-600 | FS | Completed | Completed | 21
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of FOC Cables (Lot 2) | Receipt at site and inspection of FOC Cables (Lot 2) | HM-EL-600 | HM-EL-610 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.19.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | Manufacturing & Assembly of FOC Cables | Transportation/ Custom Clearance/ Delivery at site of FOC Cables (Lot 1) | HM-EL-0120 | HM-EL-0170 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Pig Signaler (Lot 2) | Complete Delivery to Site | HM-PL-1490 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Pig Signaler (Lot 2) | Receipt at site and inspection of Pig Signaler (Lot 2) | HM-PL-1480 | HM-PL-1490 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Pig Signaler (Lot 2) | Receive at Site - Isolation Joints, Barred Tee, and Anchor Flanges | HM-PL-1490 | ML1409-D24 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.19.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | Ready for Dispatch of Pig Signaler | Transportation/ Custom Clearance/ Delivery at site of Pig Signaler (Lot 2) | HM-PL-0500 | HM-PL-1480 | FS | Not Started | Not Started | 21
P2543-R01-Oct24..PR.1.19.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | Manufacturing & Assembly of Pig Signaler | Transportation/ Custom Clearance/ Delivery at site of Pig Signaler (Lot 1) | HM-PL-0470 | HM-PL-0520 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Isolating Joints (Lot 2) | Complete Delivery to Site | HM-PL-1510 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Isolating Joints (Lot 2) | Receipt at site and inspection of Isolating Joints (Lot 2) | HM-PL-1500 | HM-PL-1510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | Ready for Dispatch of Isolating Joints | Transportation/ Custom Clearance/ Delivery at site of Isolating Joints (Lot 2) | HM-PL-0710 | HM-PL-1500 | FS | Not Started | Not Started | 21
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Isolating Joints (Lot 2) | Receive at Site - Isolation Joints, Barred Tee, and Anchor Flanges | HM-PL-1510 | ML1409-D24 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | Manufacturing & Assembly of Isolating Joints | Transportation/ Custom Clearance/ Delivery at site of Isolating Joints (Lot 1) | HM-PL-0680 | HM-PL-0730 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Pigging & Split Tee (Lot 2) | Complete Delivery to Site | HM-PL-1530 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Pigging & Split Tee (Lot 2) | Receive at Site - Isolation Joints, Barred Tee, and Anchor Flanges | HM-PL-1530 | ML1409-D24 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Pigging & Split Tee (Lot 2) | Receipt at site and inspection of Pigging & Split Tee (Lot 2) | HM-PL-1520 | HM-PL-1530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | Ready for Dispatch of Pigging & Split Tee | Transportation/ Custom Clearance/ Delivery at site of Pigging & Split Tee (Lot 2) | HM-PL-0810 | HM-PL-1520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | Manufacturing & Assembly of Pigging & Split Tee | Transportation/ Custom Clearance/ Delivery at site of Pigging & Split Tee (Lot 1) | HM-PL-0780 | HM-PL-0830 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.4.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Anchor Flanges (Lot 2) | Complete Delivery to Site | HM-PL-1550 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.4.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.4.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Anchor Flanges (Lot 2) | Receipt at site and inspection of Anchor Flanges (Lot 2) | HM-PL-1540 | HM-PL-1550 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.4.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.4.3 Delivery & receipt at Site | Ready for Dispatch of Anchor Flanges | Transportation/ Custom Clearance/ Delivery at site of Anchor Flanges (Lot 2) | HM-PL-920 | HM-PL-1540 | FS | Not Started | Not Started | 21
P2543-R01-Oct24..PR.1.4.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.4.3 Delivery & receipt at Site | Manufacturing & Assembly of Anchor Flanges | Transportation/ Custom Clearance/ Delivery at site of Anchor Flanges (Lot 1) | HM-PL-900 | HM-PL-950 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Power & Control Cables (Lot 2) | Complete Delivery to Site | HM-EL-630 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Power & Control Cables (Lot 2) | Receipt at site and inspection of Power & Control Cables (Lot 2) | HM-EL-620 | HM-EL-630 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | Ready for Dispatch of Power & Control Cables | Transportation/ Custom Clearance/ Delivery at site of Power & Control Cables (Lot 2) | HM-EL-0050 | HM-EL-620 | FS | Not Started | Not Started | 21
P2543-R01-Oct24..PR.BK.17.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | Manufacturing & Assembly of Power & Control Cables | Transportation/ Custom Clearance/ Delivery at site of Power & Control Cables (Lot 1) | HM-EL-0020 | HM-EL-0070 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Cable Trays (Lot 2) | Complete Delivery to Site | HM-EL-650 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Cable Trays (Lot 1) | Receipt at site and inspection of Cable Trays (Lot 2) | HM-EL-640 | HM-EL-650 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | Ready for Dispatch of Cable Trays | Transportation/ Custom Clearance/ Delivery at site of Cable Trays (Lot 1) | HM-EL-0250 | HM-EL-640 | FS | Not Started | Not Started | 21
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Cable Trays (Lot 1) | Receipt at site and inspection of Cable Trays (Lot 2) | HM-EL-640 | HM-EL-650 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | Manufacturing & Assembly of Cable Trays | Transportation/ Custom Clearance/ Delivery at site of Cable Trays (Lot 1) | HM-EL-0220 | HM-EL-0270 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Vendor Documents Package | HM-PL-1570 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | HM-PL-1560 | HM-PL-1570 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Receive at Site - Manual Valves | HM-PL-1570 | ML1539-D21 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Receive at Site - Valves – Globe/Check/Plug | HM-PL-1570 | ML1529-D20 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | Ready for Dispatch of Ball/ Globe/ Check/ Plug Valves | Transportation/ Custom Clearance/ Delivery at site of Ball/ Globe/ Check/ Plug Valves (Lot 2) | HM-PL-0190 | HM-PL-1560 | FS | Not Started | Not Started | 21
P2543-R01-Oct24..PR.BK.1.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | Manufacturing & Assembly of Ball/ Globe/ Check/ Plug Valves | Transportation/ Custom Clearance/ Delivery at site of Ball/ Globe/ Check/ Plug Valves (Lot 1) | HM-PL-0160 | HM-PL-0210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.3.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Cable Gland and Termination (Lot 2) | Complete Delivery to Site | HM-EL-670 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.3.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.3.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Cable Gland and Termination (Lot 2) | Receipt at site and inspection of Cable Gland and Termination (Lot 2) | HM-EL-660 | HM-EL-670 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.3.3 Delivery & receipt at Site | Ready for Dispatch of Cable Gland and Termination | Transportation/ Custom Clearance/ Delivery at site of Cable Gland and Termination (Lot 2) | HM-EL-570 | HM-EL-660 | FS | Not Started | Not Started | 21
P2543-R01-Oct24..PR.BK.3.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.3.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Cable Gland and Termination (Lot 2) | Receipt at site and inspection of Cable Gland and Termination (Lot 2) | HM-EL-660 | HM-EL-670 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.3.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.3.3 Delivery & receipt at Site | Manufacturing & Assembly of Cable Gland and Termination | Transportation/ Custom Clearance/ Delivery at site of Cable Gland and Termination (Lot 1) | HM-EL-540 | HM-EL-590 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Earthing Material (Lot 2) | Complete Delivery to Site | HM-EL-690 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | Ready for Dispatch of Earthing Material | Transportation/ Custom Clearance/ Delivery at site of Earthing Material (Lot 2) | HM-EL-0350 | HM-EL-680 | FS | Not Started | Not Started | 21
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Earthing Material (Lot 2) | Receipt at site and inspection of Earthing Material (Lot 2) | HM-EL-680 | HM-EL-690 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Earthing Material (Lot 2) | Receipt at site and inspection of Earthing Material (Lot 2) | HM-EL-680 | HM-EL-690 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | Manufacturing & Assembly of Earthing Material | Transportation/ Custom Clearance/ Delivery at site of Earthing Material (Lot 1) | HM-EL-0320 | HM-EL-0370 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.16.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of MCT (Lot 2) | Complete Delivery to Site | HM-EL-710 | ML1549-D32 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.16.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.16.3 Delivery & receipt at Site | Ready for Dispatch of MCT | Transportation/ Custom Clearance/ Delivery at site of MCT (Lot 2) | HM-EL-0450 | HM-EL-700 | FS | Not Started | Not Started | 21
P2543-R01-Oct24..PR.BK.16.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.16.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of MCT (Lot 2) | Receipt at site and inspection of MCT (Lot 2) | HM-EL-700 | HM-EL-710 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.16.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.BK.16.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of MCT (Lot 2) | Receipt at site and inspection of MCT (Lot 2) | HM-EL-700 | HM-EL-710 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.16.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.16.3 Delivery & receipt at Site | Manufacturing & Assembly of MCT | Transportation/ Custom Clearance/ Delivery at site of MCT (Lot 1) | HM-EL-0420 | HM-EL-0470 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | Ready for Dispatch of Pig Launchers & Receivers | Transportation/ Custom Clearance/ Delivery at site of Pig Launchers & Receivers (56" Line) | HM-ME-0450 | HM-ME-2380 | FS | Not Started | Not Started | 21
P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of Pig Launchers & Receivers (56" Line) | Receipt at site and inspection of Pig Launchers & Receivers (56" Line) | HM-ME-2380 | HM-ME-2390 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Receipt at site and inspection of Pig Launchers & Receivers (56" Line) | Vendor Documents Package | HM-ME-2390 | CAB-5310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | P2543-R01-Oct24..ML.2 Manufacturing & Delivery | Receipt at site and inspection of Pig Launchers & Receivers (56" Line) | Receive at Site - Pig Launcher & Receiver | HM-ME-2390 | ML1519-D04 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Main Office | Camp Facilities | CTF-SO1000 | CTF-SO1010 | SS | Completed | Completed | 15
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Camp Facilities | Satellite Office-1 | CTF-SO1010 | CTF-SO1020 | SS | Completed | Completed | 45
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..4.1.1 Construction NOC's | Issue ICR - Overall Pipeline Route Map - 52" | Construction NOC from AAM | HE-PL-0190 | C-GOV-1000 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | P2543-R01-Oct24..4.1.1 Construction NOC's | Issue ICR - Overall Pipeline Route Map - 56" | Construction NOC from AAM | HE-PL-0130 | C-GOV-1000 | FF | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | P2543-R01-Oct24..4.1.1 Construction NOC's | Issue ICR - Overall Pipeline Route Map - 4" | Construction NOC from AAM | HE-PL-0250 | C-GOV-1000 | FF | Completed | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from AAM | Construction NOC from ADM | C-GOV-1000 | C-GOV-1010 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from ADM | Construction NOC from DMT | C-GOV-1010 | C-GOV-1020 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from DMT | Construction NOC from DRM | C-GOV-1020 | C-GOV-1030 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from DRM | Construction NOC from ADDC | C-GOV-1030 | C-GOV-1040 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from ADDC | Construction NOC from AADC | C-GOV-1040 | C-GOV-1050 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from AADC | Construction NOC from ADM Al Wathba | C-GOV-1050 | C-GOV-1060 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from ADM Al Wathba | Construction NOC from ADM Musaffah | C-GOV-1060 | C-GOV-1070 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from ADM Musaffah | Construction NOC from ADM City Centre | C-GOV-1070 | C-GOV-1080 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from ADM City Centre | Construction NOC from ADM Al Shahama | C-GOV-1080 | C-GOV-1090 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from ADM Al Shahama | Construction NOC from ADNOC | C-GOV-1090 | C-GOV-1100 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from ADNOC | Construction NOC from ADSSC | C-GOV-1100 | C-GOV-1110 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from ADSSC | Construction NOC from DCT | C-GOV-1110 | C-GOV-1120 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from DCT | Construction NOC from AAM Parks | C-GOV-1120 | C-GOV-1130 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from AAM Parks | Construction NOC from DRM Parks | C-GOV-1130 | C-GOV-1140 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from DRM Parks | Construction NOC from AAM Roads | C-GOV-1140 | C-GOV-1150 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from AAM Roads | Construction NOC from DRM Roads | C-GOV-1150 | C-GOV-1160 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from DRM Roads | Construction NOC from DEL | C-GOV-1160 | C-GOV-1170 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from DEL | Construction NOC from DU | C-GOV-1170 | C-GOV-1180 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from DU | Construction NOC from EAD | C-GOV-1180 | C-GOV-1190 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from EAD | Construction NOC from Ethiad Rail | C-GOV-1190 | C-GOV-1200 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from Ethiad Rail | Construction NOC from Etisalat | C-GOV-1200 | C-GOV-1210 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from Etisalat | Construction NOC from GRQ Military | C-GOV-1210 | C-GOV-1220 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from GRQ Military | Construction NOC from ITC ROW | C-GOV-1220 | C-GOV-1230 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from ITC ROW | Construction NOC from MCC | C-GOV-1230 | C-GOV-1240 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from MCC | Construction NOC from TADWEER | C-GOV-1240 | C-GOV-1250 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from TADWEER | Construction NOC from TRANSCO | C-GOV-1250 | C-GOV-1260 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from TRANSCO | Construction NOC from Zone Cops | C-GOV-1260 | C-GOV-1270 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from Zone Cops | Construction NOC from CICPA | C-GOV-1270 | C-GOV-1280 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from CICPA | Construction NOC from BARARI | C-GOV-1280 | C-GOV-1290 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.1.1 Construction NOC's | Construction NOC from BARARI | Construction NOC from Musanada | C-GOV-1290 | C-GOV-1300 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.2.3.3 Geotechnical Survey Report 52" Line | P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | Issue ICR - Geo Technical Survey Report 52" Line | Issue ICR - Overall Pipeline Route Map - 52" | HE-GS-90 | HE-PL-0190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.3 Geotechnical Survey Report 52" Line | P2543-R01-Oct24..1.EN.2.3.3 Geotechnical Survey Report 52" Line | Re-Issue for Approval - Geo Technical Survey Report 52" Line | Obtain Company Approval - Geo Technical Survey Report 52" Line | HE-GS-60 | HE-GS-70 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.3 Geotechnical Survey Report 52" Line | P2543-R01-Oct24..1.EN.2.3.3 Geotechnical Survey Report 52" Line | Obtain Company Approval - Geo Technical Survey Report 52" Line | Final Issue for Design/ Construction-Geotechnical Survey Report 52" Line | HE-GS-70 | HE-GS-80 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.3 Geotechnical Survey Report 52" Line | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Geotechnical Survey Report 52" Line | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 52" Pipeline(IFC) | HE-GS-80 | ML1009-B04 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.3 Geotechnical Survey Report 52" Line | P2543-R01-Oct24..1.EN.2.3.3 Geotechnical Survey Report 52" Line | Receive Company Comments - Geo Technical Survey Report 52" Line | Re-Issue for Approval - Geo Technical Survey Report 52" Line | HE-GS-50 | HE-GS-60 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..1.EN.2.3.3 Geotechnical Survey Report 52" Line | Geo Technical Survey | Issue ICR - Geo Technical Survey Report 52" Line | HE-SS-0040 | HE-GS-90 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.3 Geotechnical Survey Report 52" Line | P2543-R01-Oct24..1.EN.2.3.3 Geotechnical Survey Report 52" Line | Issue ICR - Geo Technical Survey Report 52" Line | Receive Company Comments - Geo Technical Survey Report 52" Line | HE-GS-90 | HE-GS-50 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | Issue ICR-Topographical Survey Report 56" Line | Issue ICR - Overall Pipeline Route Map - 56" | HE-TS-230 | HE-PL-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR-Topographical Survey Report 56" Line | Re-Issue after HAZOP /Review Comments- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-TS-230 | HE-PI-0350 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Topographical Survey Report 56" Line | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 56" Pipeline(IFC) | HE-TS-220 | ML1008-B03 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | Final Issue for Design/ Construction-Topographical Survey Report 56" Line | Final Issue for Design/ Construction-Pipeline Station approach drawing - 56" | HE-TS-220 | HE-PL-2610 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | P2543-R01-Oct24..1.EN.1.31 Pipeline Station approach drawing - 56" | Issue ICR-Topographical Survey Report 56" Line | Issue ICR - Pipeline Station Approach drawing -56" | HE-TS-230 | HE-PL-2570 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | Re-Issue for Approval-Topographical Survey Report 56" Line | Obtain Company Approval-Topographical Survey Report 56" Line | HE-TS-200 | HE-TS-210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | Obtain Company Approval-Topographical Survey Report 56" Line | Final Issue for Design/ Construction-Topographical Survey Report 56" Line | HE-TS-210 | HE-TS-220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Final Issue for Design/ Construction-Topographical Survey Report 56" Line | Final Issue for Design/ Construction-Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-TS-220 | HE-PI-0370 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | Issue ICR-Topographical Survey Report 56" Line | Re-Issue for Approval - Overall Pipeline Route Map - 56" | HE-TS-230 | HE-PL-0150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | Issue ICR-Topographical Survey Report 56" Line | Issue ICR - Pipeline Alignment Sheets -56" | HE-TS-230 | HE-PL-2390 | FS | Completed | Completed | 10
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | Topographical Survey | Issue ICR-Topographical Survey Report 56" Line | HE-SS-0030 | HE-TS-230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | Issue ICR-Topographical Survey Report 56" Line | Receive Company Comments-Topographical Survey Report 56" Line | HE-TS-230 | HE-TS-240 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | Receive Company Comments-Topographical Survey Report 56" Line | Re-Issue for Approval-Topographical Survey Report 56" Line | HE-TS-240 | HE-TS-200 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR-Topographical Survey Report 56" Line | Re-Issue for HAZOP Studies- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-TS-230 | HE-PI-0340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | Issue ICR-Topographical Survey Report 52" Line | Issue ICR - Overall Pipeline Route Map - 52" | HE-TS-280 | HE-PL-0190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | Final Issue for Design/ Construction-Topographical Survey Report 52" Line | Final Issue for Design/ Construction-Pipeline Station approach drawing-52" | HE-TS-270 | HE-PL-2670 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Topographical Survey Report 52" Line | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 52" Pipeline(IFC) | HE-TS-270 | ML1009-B04 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Final Issue for Design/ Construction-Topographical Survey Report 52" Line | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | HE-TS-270 | HE-PI-0440 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | Re-Issue for Approval-Topographical Survey Report 52" Line | Obtain Company Approval-Topographical Survey Report 52" Line | HE-TS-250 | HE-TS-260 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | Issue ICR-Topographical Survey Report 52" Line | Re-Issue for Approval - Overall Pipeline Route Map - 52" | HE-TS-280 | HE-PL-0210 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | Issue ICR-Topographical Survey Report 52" Line | Issue ICR - Pipeline Alignment Sheets-52" | HE-TS-280 | HE-PL-2450 | FS | Completed | Completed | 15
P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | Obtain Company Approval-Topographical Survey Report 52" Line | Final Issue for Design/ Construction-Topographical Survey Report 52" Line | HE-TS-260 | HE-TS-270 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | Issue ICR-Topographical Survey Report 52" Line | Issue ICR - Pipeline Station Approach drawing -52" | HE-TS-280 | HE-PL-2630 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | Topographical Survey | Issue ICR-Topographical Survey Report 52" Line | HE-SS-0030 | HE-TS-280 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | Issue ICR-Topographical Survey Report 52" Line | Receive Company Comments-Topographical Survey Report 52" Line | HE-TS-280 | HE-TS-290 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | Receive Company Comments-Topographical Survey Report 52" Line | Re-Issue for Approval-Topographical Survey Report 52" Line | HE-TS-290 | HE-TS-250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.1 Geotechnical Survey Report 56" Line | P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | Issue ICR - Geo Technical Survey Report 56" Line | Issue ICR - Overall Pipeline Route Map - 56" | HE-GS-140 | HE-PL-0130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.1 Geotechnical Survey Report 56" Line | P2543-R01-Oct24..1.EN.2.3.1 Geotechnical Survey Report 56" Line | Re-Issue for Approval - Geo Technical Survey Report 56" Line | Obtain Company Approval - Geo Technical Survey Report 56" Line | HE-GS-110 | HE-GS-120 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.1 Geotechnical Survey Report 56" Line | P2543-R01-Oct24..1.EN.2.3.1 Geotechnical Survey Report 56" Line | Obtain Company Approval - Geo Technical Survey Report 56" Line | Final Issue for Design/ Construction-Geotechnical Survey Report 56" Line | HE-GS-120 | HE-GS-130 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.1 Geotechnical Survey Report 56" Line | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Geotechnical Survey Report 56" Line | Comp Topographic/ Soil Investigation Surveys Reports, Pipeline Route Alignment Sheets & Route Maps for 56" Pipeline(IFC) | HE-GS-130 | ML1008-B03 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.1 Geotechnical Survey Report 56" Line | P2543-R01-Oct24..1.EN.2.3.1 Geotechnical Survey Report 56" Line | Receive Company Comments - Geo Technical Survey Report 56" Line | Re-Issue for Approval - Geo Technical Survey Report 56" Line | HE-GS-100 | HE-GS-110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..1.EN.2.3.1 Geotechnical Survey Report 56" Line | Geo Technical Survey | Issue ICR - Geo Technical Survey Report 56" Line | HE-SS-0040 | HE-GS-140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.1 Geotechnical Survey Report 56" Line | P2543-R01-Oct24..1.EN.2.3.1 Geotechnical Survey Report 56" Line | Issue ICR - Geo Technical Survey Report 56" Line | Receive Company Comments - Geo Technical Survey Report 56" Line | HE-GS-140 | HE-GS-100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.1 Geotechnical Survey Report 56" Line | P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | Issue ICR - Geo Technical Survey Report 56" Line | Re-Issue for HAZOP Studies- Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | HE-GS-140 | HE-PI-0340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.2 Geotechnical Survey Report 4" Line | P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | Issue ICR - Geo Technical Survey Report 4" Line | Issue ICR - Overall Pipeline Route Map - 4" | HE-GS-190 | HE-PL-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.2 Geotechnical Survey Report 4" Line | P2543-R01-Oct24..1.EN.2.3.2 Geotechnical Survey Report 4" Line | Re-Issue for Approval - Geo Technical Survey Report 4" Line | Obtain Company Approval - Geo Technical Survey Report 4" Line | HE-GS-160 | HE-GS-170 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.2 Geotechnical Survey Report 4" Line | P2543-R01-Oct24..1.EN.2.3.2 Geotechnical Survey Report 4" Line | Obtain Company Approval - Geo Technical Survey Report 4" Line | Final Issue for Design/ Construction-Geotechnical Survey Report 4" Line | HE-GS-170 | HE-GS-180 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.2 Geotechnical Survey Report 4" Line | P2543-R01-Oct24..1.EN.2.3.2 Geotechnical Survey Report 4" Line | Receive Company Comments - Geo Technical Survey Report 4" Line | Re-Issue for Approval - Geo Technical Survey Report 4" Line | HE-GS-150 | HE-GS-160 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..1.EN.2.3.2 Geotechnical Survey Report 4" Line | Geo Technical Survey | Issue ICR - Geo Technical Survey Report 4" Line | HE-SS-0040 | HE-GS-190 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | P2543-R01-Oct24..1.EN.1.12 Pipeline Station approach drawing - 4" Waterline | Issue ICR-Topographical Survey Report 4" Line | Issue ICR - Pipeline Station Approach drawing -4" | HE-TS-330 | HE-PL-3580 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | Issue ICR-Topographical Survey Report 4" Line | Issue ICR - Pipeline Alignment Sheets-4" | HE-TS-330 | HE-PL-3530 | FS | Completed | Completed | 60
P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | Issue ICR-Topographical Survey Report 4" Line | Issue ICR - Overall Pipeline Route Map - 4" | HE-TS-330 | HE-PL-0250 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | Re-Issue for Approval-Topographical Survey Report 4" Line | Obtain Company Approval-Topographical Survey Report 4" Line | HE-TS-300 | HE-TS-310 | SS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | P2543-R01-Oct24..1.EN.1.15 Pipeline Station approach drawing - 4" Nitrogen | Issue ICR-Topographical Survey Report 4" Line | Issue ICR - Pipeline Station Approach drawing -4" | HE-TS-330 | HE-PL-2690 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | Obtain Company Approval-Topographical Survey Report 4" Line | Final Issue for Design/ Construction-Topographical Survey Report 4" Line | HE-TS-310 | HE-TS-320 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Issue ICR-Topographical Survey Report 4" Line | Re-Issue after incorporating HAZOP /Review Comments - 4" N2 Source Pipeline | HE-TS-330 | HE-PI-0490 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | Issue ICR-Topographical Survey Report 4" Line | Re-Issue for Approval - Overall Pipeline Route Map - 4" | HE-TS-330 | HE-PL-0270 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | Issue ICR-Topographical Survey Report 4" Line | Issue ICR - Pipeline Alignment Sheets-4" | HE-TS-330 | HE-PL-2510 | FS | Completed | Completed | 30
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | Topographical Survey | Issue ICR-Topographical Survey Report 4" Line | HE-SS-0030 | HE-TS-330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | Final Issue for Design/ Construction-Topographical Survey Report 4" Line | Final Issue for Design/ Construction-Overall Plot Plan- 4" N2 Source Pipeline | HE-TS-320 | HE-PI-0510 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | Issue ICR-Topographical Survey Report 4" Line | Receive Company Comments-Topographical Survey Report 4" Line | HE-TS-330 | HE-TS-340 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | Receive Company Comments-Topographical Survey Report 4" Line | Re-Issue for Approval-Topographical Survey Report 4" Line | HE-TS-340 | HE-TS-300 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | Final Issue for Design/ Construction-Topographical Survey Report 4" Line | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | HE-TS-320 | HE-PL-2550 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | Final Issue for Design/ Construction-Topographical Survey Report 4" Line | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | HE-TS-320 | HE-PL-3570 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2.3.2 Geotechnical Survey Report 4" Line | P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | Final Issue for Design/ Construction-Geotechnical Survey Report 4" Line | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | HE-GS-180 | HE-PL-2550 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.2.3.2 Geotechnical Survey Report 4" Line | P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | Final Issue for Design/ Construction-Geotechnical Survey Report 4" Line | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | HE-GS-180 | HE-PL-3570 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2.3.2 Geotechnical Survey Report 4" Line | P2543-R01-Oct24..1.EN.2.3.2 Geotechnical Survey Report 4" Line | Issue ICR - Geo Technical Survey Report 4" Line | Receive Company Comments - Geo Technical Survey Report 4" Line | HE-GS-190 | HE-GS-150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.1 Topographical Survey Report 52" Line | P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | Issue ICR-Topographical Survey Report 52" Line | Issue ICR-Topographical Survey Report 56" Line | HE-TS-280 | HE-TS-230 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.2.5 Topographical Survey Report 56" Line | P2543-R01-Oct24..1.EN.2.2.3 Topographical Survey Report 4" Line | Issue ICR-Topographical Survey Report 56" Line | Issue ICR-Topographical Survey Report 4" Line | HE-TS-230 | HE-TS-330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.3 Geotechnical Survey Report 52" Line | P2543-R01-Oct24..1.EN.2.3.1 Geotechnical Survey Report 56" Line | Issue ICR - Geo Technical Survey Report 52" Line | Issue ICR - Geo Technical Survey Report 56" Line | HE-GS-90 | HE-GS-140 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2.3.1 Geotechnical Survey Report 56" Line | P2543-R01-Oct24..1.EN.2.3.2 Geotechnical Survey Report 4" Line | Issue ICR - Geo Technical Survey Report 56" Line | Issue ICR - Geo Technical Survey Report 4" Line | HE-GS-140 | HE-GS-190 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.4.2.2 System Commissioninng - 56” P/L Facility to HGCP 56” P/R (56”) | P2543-R01-Oct24..4.4.2 Commissioning | Commissioning | Wrap up works for PAC-1 | CCM-PM4570 | CCM-PM4550 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2.1 System Commissioninng - Habshan Complex to 56” P/L Fac. (56”) | P2543-R01-Oct24..4.4.2 Commissioning | Commissioning | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | CCM-PM4560 | CCM-PM4510 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2.3 System Commissioninng - HGCP 52” P/L to Sweihan CRS 52” P/R (52”) | P2543-R01-Oct24..4.4.2 Commissioning | Commissioning | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | CCM-PM4580 | CCM-PM4520 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2.4 System Commissioninng - 36'' Jump-over connection at KM-42 | P2543-R01-Oct24..4.4.2 Commissioning | Commissioning | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | CCM-PM4590 | CCM-PM4520 | FF | Not Started | Not Started | 27
P2543-R01-Oct24..4.4.2.5 System Commissioninng - Habshan-5 4” P/L to HGCP 4” P/R (4”) | P2543-R01-Oct24..4.4.2 Commissioning | Commissioning | Wrap up works for PAC-1 | CCM-PM4600 | CCM-PM4550 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2.6 System Commissioninng - SV-03 (KP 96) to HGCP (4'') | P2543-R01-Oct24..4.4.2 Commissioning | Commissioning | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | CCM-PM4610 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2.7 System Commissioninng - Dolphin Existing BVS -06 | P2543-R01-Oct24..4.4.2 Commissioning | Commissioning | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | CCM-PM4620 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | ML1959-E41 | ML1020 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | ML1979-E43 | ML1030 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..ML.4 Commissioning and PAC | Wrap up works for PAC-1 | Achieve (PAC-1) for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | CCM-PM4550 | ML2039-F05 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.5.3.3 TBE for Pig Launcher/Receiver | P2543-R01-Oct24..1.1.2.LL.12.1 Ordering | Obtain Company Approval-TBEs for Pig Launcher/Receiver | Prepare TBE and Company approval for Pig Launchers & Receivers | HE-ME-560 | HP-ME-0220 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.6.A31 F&G I/O list | P2543-R01-Oct24..1.1.BK.12 Modification of Existing Telecom System | Issue ICR- I/O list -Update | RFQ, Receipt of Bid - Modification of Existing Telecom System | HE-IC-2730 | HS-GN-0310 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.2.5 Engineeirng Office | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Engineering Office at NPCC | NOC's / Approval /Survey | CTF-SO1080 | CTF-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | NOC's / Approval /Survey | Issue ICR-Shutdown Requirements & Plan | CTF-1010 | C-COM-850 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | NOC's / Approval /Survey | Issue ICR-Construction Procedures / Method Statements / ITPs | CTF-1010 | C-COM-750 | SS | Completed | Not Started | 6
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Project Kick off Meeting | NOC's / Approval /Survey | ML1002 | CTF-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.2.1 Mobilization & TSF | Main Office | NOC's / Approval /Survey | CTF-SO1000 | CTF-1010 | SS | Completed | Completed | 9
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-56-PL-607-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-56-PL-607-CI-1000 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-56-PL-607-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | Satellite Office-2 | Concrete Works for Equipment Foundations | CTF-SO1030 | C-56-PL-607-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Equipment Foundations | HE-CS-0230 | C-56-PL-607-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Concrete Works for Equipment Foundations | HE-CS-0650 | C-56-PL-607-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | Final Issue for Design/ Construction-Typical Detailed Drawing - Jib Crane Foundation | Concrete Works for Equipment Foundations | HE-CS-1070 | C-56-PL-607-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Concrete Works for Equipment Foundations | HE-CS-1190 | C-56-PL-607-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Concrete Works for Equipment Foundations | HE-CS-1310 | C-56-PL-607-CI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | 1st Civil Bulk material MTO | Concrete Works for Equipment Foundations | HM-CS-0040 | C-56-PL-607-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.1.1.12.1.4 Concrete Works (Impact Wall ) CCOHBCS202.3 | Satellite Office-2 | Concrete Works (Impact Wall ) (Deleted) | CTF-SO1030 | C-56-PL-607-CI-1500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.1.1.12.1.4 Concrete Works (Impact Wall ) CCOHBCS202.3 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works (Impact Wall ) (Deleted) | HE-CS-0230 | C-56-PL-607-CI-1500 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.3.1.1.1.12.1.8 Pipe Supports Fabrication & Installation CCOHBSS300 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1430 | C-56-PL-607-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.3.1.1.1.12.1.8 Pipe Supports Fabrication & Installation CCOHBSS300 | Final Issue for Design/ Construction-Misc. supports | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1490 | C-56-PL-607-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.1.8 Pipe Supports Fabrication & Installation CCOHBSS300 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0110 | C-56-PL-607-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.1.1.12.1.8 Pipe Supports Fabrication & Installation CCOHBSS300 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Pipe Supports | HS-CN-0690 | C-56-PL-607-CI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.1.9 Thrust Anchor BlockCCOHBCS210 | Receipt at site and inspection of Anchor Flanges (Lot 1) | Concrete Works for Thrust Anchor Block | HM-PL-940 | C-56-PL-607-CI-1510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS304 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0110 | C-56-PL-607-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.1.1.12.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS304 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Platforms & Crossovers | HS-CN-0690 | C-56-PL-607-CI-3000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.1.1.12.1.12 Installation of Fence Type-4CCOHBCS206.1 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Installation of Fence Type-4 (Deleted) | HE-CS-0350 | C-56-PL-607-CI-2220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.1.1.12.1.12 Installation of Fence Type-4CCOHBCS206.1 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Installation of Fence Type-4 (Deleted) | HE-CS-0470 | C-56-PL-607-CI-2220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.1.1.12.1.14 Paving WorksCCOHBCS208 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-56-PL-607-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.1.14 Paving WorksCCOHBCS208 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-56-PL-607-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | P2543-R01-Oct24..4.3.1.1.1.12.3.1 Installation of Pig Launcher (607-V-603)CCOHBME303 | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | Installation of Pig Launcher (607-V-603) 56" | C-COM-790 | C-56-PL-607-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.3.1 Installation of Pig Launcher (607-V-603)CCOHBME303 | Receipt at site and inspection of Pig Launchers & Receivers (56" Line) | Installation of Pig Launcher (607-V-603) 56" | HM-ME-2390 | C-56-PL-607-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.3.1 Installation of Pig Launcher (607-V-603)CCOHBME303 | Receipt at site and inspection of Pigging & Split Tee (Lot 1) | Installation of Pig Launcher (607-V-603) 56" | HM-PL-0840 | C-56-PL-607-ME-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.3.1 Installation of Pig Launcher (607-V-603)CCOHBME303 | Receipt at site and inspection of Pigging & Split Tee (Lot 2) | Installation of Pig Launcher (607-V-603) 56" | HM-PL-1530 | C-56-PL-607-ME-1000 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.3.1 Installation of Pig Launcher (607-V-603)CCOHBME303 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Installation of Pig Launcher (607-V-603) 56" | ML1015-B08 | C-56-PL-607-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.1.1.12.3.1 Installation of Pig Launcher (607-V-603)CCOHBME303 | Receive at Site - Pig Launcher & Receiver | Installation of Pig Launcher (607-V-603) 56" | ML1519-D04 | C-56-PL-607-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | P2543-R01-Oct24..4.3.1.1.1.12.3.2 Installation of Pig Signaler (607-V-603)CCOHBME318 | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | Installation of Pig Signaler (607-V-603)CCOHBME318 (Deleted) | C-COM-790 | C-56-PL-607-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.3.2 Installation of Pig Signaler (607-V-603)CCOHBME318 | Receipt at site and inspection of Pig Signaler (Lot 1) | Installation of Pig Signaler (607-V-603)CCOHBME318 (Deleted) | HM-PL-0530 | C-56-PL-607-ME-1200 | FF | Not Started | Not Started | 6
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.3.2 Installation of Pig Signaler (607-V-603)CCOHBME318 | Receipt at site and inspection of Pigging & Split Tee (Lot 1) | Installation of Pig Signaler (607-V-603)CCOHBME318 (Deleted) | HM-PL-0840 | C-56-PL-607-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.3.2 Installation of Pig Signaler (607-V-603)CCOHBME318 | Receipt at site and inspection of Pig Signaler (Lot 2) | Installation of Pig Signaler (607-V-603)CCOHBME318 (Deleted) | HM-PL-1490 | C-56-PL-607-ME-1200 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.3.2 Installation of Pig Signaler (607-V-603)CCOHBME318 | Receipt at site and inspection of Pigging & Split Tee (Lot 2) | Installation of Pig Signaler (607-V-603)CCOHBME318 (Deleted) | HM-PL-1530 | C-56-PL-607-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.3.2 Installation of Pig Signaler (607-V-603)CCOHBME318 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Installation of Pig Signaler (607-V-603)CCOHBME318 (Deleted) | ML1015-B08 | C-56-PL-607-ME-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | P2543-R01-Oct24..4.3.1.1.1.12.3.3 Installation of Filter PackageCCOHBME328 | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | Installation of Filter PackageCCOHBME328 (Deleted) | C-COM-790 | C-56-PL-607-ME-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.24.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.3.3 Installation of Filter PackageCCOHBME328 | Receipt at site and inspection of Filter Package | Installation of Filter PackageCCOHBME328 (Deleted) | HM-ME-2120 | C-56-PL-607-ME-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.3.3 Installation of Filter PackageCCOHBME328 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Installation of Filter PackageCCOHBME328 (Deleted) | ML1015-B08 | C-56-PL-607-ME-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.3 Construction Procedures / Method Statements / ITPs | P2543-R01-Oct24..4.3.1.1.1.12.3.4 Installation of Fire Fighting & Safety EquipmentCCOHBME338 | Final Issue for Design/ Construction-Construction Procedures / Method Statements / ITPs | Installation of Fire Fighting & Safety EquipmentCCOHBME338 (Deleted) | C-COM-790 | C-56-PL-607-ME-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.3.4 Installation of Fire Fighting & Safety EquipmentCCOHBME338 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 1) | Installation of Fire Fighting & Safety EquipmentCCOHBME338 (Deleted) | HM-ME-1990 | C-56-PL-607-ME-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.3.4 Installation of Fire Fighting & Safety EquipmentCCOHBME338 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 2) | Installation of Fire Fighting & Safety EquipmentCCOHBME338 (Deleted) | HM-ME-2370 | C-56-PL-607-ME-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.3.4 Installation of Fire Fighting & Safety EquipmentCCOHBME338 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Installation of Fire Fighting & Safety EquipmentCCOHBME338 (Deleted) | ML1015-B08 | C-56-PL-607-ME-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.3.1.1.1.12.4.1 Piping Pre-FabricationCCOHBPI302 | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | Piping Pre-Fabrication | C-COM-1010 | C-56-PL-607-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.1.1.12.4.1 Piping Pre-FabricationCCOHBPI302 | Fabrication Facilities | Piping Pre-Fabrication | CTF-SO1050 | C-56-PL-607-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..4.3.1.1.1.12.4.1 Piping Pre-FabricationCCOHBPI302 | Final Issue for Design/ Construction-Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Piping Pre-Fabrication | HE-PI-0370 | C-56-PL-607-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..4.3.1.1.1.12.4.1 Piping Pre-FabricationCCOHBPI302 | Final Issue for Design/ Construction-Piping GA- 56" Pipeline Launcher and metering Station (Habshan Complex) | Piping Pre-Fabrication | HE-PI-0640 | C-56-PL-607-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.1.1.12.4.1 Piping Pre-FabricationCCOHBPI302 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-56-PL-607-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.1.1.12.4.1 Piping Pre-FabricationCCOHBPI302 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-56-PL-607-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.1.1.12.4.1 Piping Pre-FabricationCCOHBPI302 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Pre-Fabrication | HE-PR-0290 | C-56-PL-607-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.1.1.12.4.1 Piping Pre-FabricationCCOHBPI302 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Pre-Fabrication | HE-PR-0890 | C-56-PL-607-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.4.1 Piping Pre-FabricationCCOHBPI302 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-56-PL-607-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.1.1.12.4.1 Piping Pre-FabricationCCOHBPI302 | NDT / PWHT Subcontract Award | Piping Pre-Fabrication | HS-CN-0190 | C-56-PL-607-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.1.1.12.4.1 Piping Pre-FabricationCCOHBPI302 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-56-PL-607-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.4.1 Piping Pre-FabricationCCOHBPI302 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Piping Pre-Fabrication | ML1014-B10 | C-56-PL-607-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.4.1 Piping Pre-FabricationCCOHBPI302 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-56-PL-607-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.1.1.12.4.2 ErectionCCOHBPI322 | Final Issue for Design/ Construction-Piping Isometrics | Piping Erection | HE-PI-1240 | C-56-PL-607-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.1.1.12.4.2 ErectionCCOHBPI322 | Piping MTO - Final | Piping Erection | HE-PI-1300 | C-56-PL-607-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.1.1.12.4.2 ErectionCCOHBPI322 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Erection | HE-PR-0290 | C-56-PL-607-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.1.1.12.4.2 ErectionCCOHBPI322 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Erection | HE-PR-0890 | C-56-PL-607-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.4.2 ErectionCCOHBPI322 | 1st Piping Bulk material MTO | Piping Erection | HM-PI-0040 | C-56-PL-607-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.4.2 ErectionCCOHBPI322 | Final Piping Bulk material MTO | Piping Erection | HM-PI-0050 | C-56-PL-607-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.2 ErectionCCOHBPI322 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Erection | HM-PL-0220 | C-56-PL-607-PI-1200 | FF | Not Started | Not Started | 12
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.2 ErectionCCOHBPI322 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Erection | HM-PL-0630 | C-56-PL-607-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.2 ErectionCCOHBPI322 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Erection | HM-PL-0740 | C-56-PL-607-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.2 ErectionCCOHBPI322 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Erection | HM-PL-1510 | C-56-PL-607-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.2 ErectionCCOHBPI322 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Erection | HM-PL-1570 | C-56-PL-607-PI-1200 | FF | Not Started | Not Started | 12
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.4.2 ErectionCCOHBPI322 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Piping Erection | ML1014-B10 | C-56-PL-607-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.4.2 ErectionCCOHBPI322 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Erection | ML1219-B19 | C-56-PL-607-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.1.1.12.4.3 Field Joint Welding & NDTCCOHBPI332 | Piping MTO - Final | Field Joint Welding | HE-PI-1300 | C-56-PL-607-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.1.1.12.4.3 Field Joint Welding & NDTCCOHBPI332 | NDT / PWHT Subcontract Award | Field Joint Welding | HS-CN-0190 | C-56-PL-607-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.1.1.12.4.3 Field Joint Welding & NDTCCOHBPI332 | Project Kick off Meeting | Field Joint Welding | ML1002 | C-56-PL-607-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.4.3 Field Joint Welding & NDTCCOHBPI332 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Field Joint Welding | ML1014-B10 | C-56-PL-607-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.4.3 Field Joint Welding & NDTCCOHBPI332 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Field Joint Welding | ML1219-B19 | C-56-PL-607-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.4.4 HydrotestingCCOHBPI342 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Hydrotesting | ML1014-B10 | C-56-PL-607-PI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.4.4 HydrotestingCCOHBPI342 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Hydrotesting | ML1219-B19 | C-56-PL-607-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.1.1.12.4.5 Installation of ValvesCCOHBPI352 | Final Issue for Design/ Construction-Piping Isometrics | Installation of Valves/MOV/ROV | HE-PI-1240 | C-56-PL-607-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.1.1.12.4.5 Installation of ValvesCCOHBPI352 | Final Issue for Design/ Construction-Tie-In Schedule | Installation of Valves/MOV/ROV | HE-PR-0290 | C-56-PL-607-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.1.1.12.4.5 Installation of ValvesCCOHBPI352 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Installation of Valves/MOV/ROV | HE-PR-0890 | C-56-PL-607-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.5 Installation of ValvesCCOHBPI352 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Installation of Valves/MOV/ROV | HM-PL-0220 | C-56-PL-607-PI-1800 | FF | Not Started | Not Started | 12
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.5 Installation of ValvesCCOHBPI352 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Installation of Valves/MOV/ROV | HM-PL-0630 | C-56-PL-607-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.5 Installation of ValvesCCOHBPI352 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Installation of Valves/MOV/ROV | HM-PL-0640 | C-56-PL-607-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.5 Installation of ValvesCCOHBPI352 | Receipt at site and inspection of Isolating Joints (Lot 1) | Installation of Valves/MOV/ROV | HM-PL-0740 | C-56-PL-607-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.5 Installation of ValvesCCOHBPI352 | Receipt at site and inspection of Isolating Joints (Lot 2) | Installation of Valves/MOV/ROV | HM-PL-1510 | C-56-PL-607-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.5 Installation of ValvesCCOHBPI352 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Installation of Valves/MOV/ROV | HM-PL-1570 | C-56-PL-607-PI-1800 | FF | Not Started | Not Started | 12
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.4.5 Installation of ValvesCCOHBPI352 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Installation of Valves/MOV/ROV | ML1014-B10 | C-56-PL-607-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.4.5 Installation of ValvesCCOHBPI352 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Installation of Valves/MOV/ROV | ML1219-B19 | C-56-PL-607-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | Final Issue for Design/ Construction-Piping Isometrics | Final Bolt Torquing/ Re-Instatement | HE-PI-1240 | C-56-PL-607-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | Piping MTO - Final | Final Bolt Torquing/ Re-Instatement | HE-PI-1300 | C-56-PL-607-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | Final Issue for Design/ Construction-Tie-In Schedule | Final Bolt Torquing/ Re-Instatement | HE-PR-0290 | C-56-PL-607-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Final Bolt Torquing/ Re-Instatement | HE-PR-0890 | C-56-PL-607-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0220 | C-56-PL-607-PI-2000 | FF | Not Started | Not Started | 12
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0630 | C-56-PL-607-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0640 | C-56-PL-607-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | Receipt at site and inspection of Isolating Joints (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0740 | C-56-PL-607-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | Receipt at site and inspection of Isolating Joints (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1510 | C-56-PL-607-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1570 | C-56-PL-607-PI-2000 | FF | Not Started | Not Started | 12
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | NDT / PWHT Subcontract Award | Final Bolt Torquing/ Re-Instatement | HS-CN-0190 | C-56-PL-607-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | Project Kick off Meeting | Final Bolt Torquing/ Re-Instatement | ML1002 | C-56-PL-607-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Final Bolt Torquing/ Re-Instatement | ML1014-B10 | C-56-PL-607-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Final Bolt Torquing/ Re-Instatement | ML1219-B19 | C-56-PL-607-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.5.1 Pig Launcher 607-V-603 56'' Pipeline/Piping Hook-upCCOHBPI312 | Receipt at site and inspection of Pig Launchers & Receivers (56" Line) | Installation of Isolation Joint | HM-ME-2390 | C-56-PL-607-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.1.1.12.5.1 Pig Launcher 607-V-603 56'' Pipeline/Piping Hook-upCCOHBPI312 | Receive at Site - Pig Launcher & Receiver | Installation of Isolation Joint | ML1519-D04 | C-56-PL-607-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Final Issue for Design/ Construction-Cable Sizing Calculation | Electrical & Earthing Cable Laying | HE-EL-0470 | C-56-PL-607-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Final Issue for Design/ Construction-Cable Schedule | Electrical & Earthing Cable Laying | HE-EL-0590 | C-56-PL-607-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Final Issue for Design/ Construction-Data Sheet for LV cables | Electrical & Earthing Cable Laying | HE-EL-0830 | C-56-PL-607-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Final Issue for Design/ Construction-Cable Routing Layout | Electrical & Earthing Cable Laying | HE-EL-1610 | C-56-PL-607-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Final Issue for Design/ Construction-Data Sheet for HV cables | Electrical & Earthing Cable Laying | HE-EL-1950 | C-56-PL-607-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Issue ICR- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0190 | C-56-PL-607-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Re-Issue for Approval- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0210 | C-56-PL-607-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Final Issue for Design/ Construction-Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0230 | C-56-PL-607-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Issue ICR- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0250 | C-56-PL-607-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Re-Issue for Approval- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0270 | C-56-PL-607-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Final Issue for Design/ Construction-Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0290 | C-56-PL-607-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Re-Issue for Approval- I/O list -Update | Electrical & Earthing Cable Laying | HE-IC-0570 | C-56-PL-607-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Final Issue for Design/ Construction-I/O list | Electrical & Earthing Cable Laying | HE-IC-0590 | C-56-PL-607-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Issue ICR- Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0790 | C-56-PL-607-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0830 | C-56-PL-607-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Electrical & Earthing Cable Laying | HE-IC-0950 | C-56-PL-607-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Final Issue for Design/ Construction-Instrument Trench Layout | Electrical & Earthing Cable Laying | HE-IC-1010 | C-56-PL-607-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Electrical & Earthing Cable Laying | HM-EL-0080 | C-56-PL-607-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | 1st Electrical Bulk material MTO | Electrical & Earthing Cable Laying | HM-EL-0520 | C-56-PL-607-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-630 | C-56-PL-607-EI-2000 | FS | Not Started | Not Started | 30
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-UPS SLD | Deep Earth Well Drilling | HE-EL-0290 | C-56-PL-607-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-Electrical Equipment Layout | Deep Earth Well Drilling | HE-EL-0530 | C-56-PL-607-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Obtain Company Approval-Data sheet for LV Distribution board | Deep Earth Well Drilling | HE-EL-0640 | C-56-PL-607-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-Data sheet for LV Distribution board | Deep Earth Well Drilling | HE-EL-0650 | C-56-PL-607-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | Deep Earth Well Drilling | HE-EL-0710 | C-56-PL-607-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Deep Earth Well Drilling | HE-EL-1010 | C-56-PL-607-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-Earthing Layout | Deep Earth Well Drilling | HE-EL-1670 | C-56-PL-607-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-Lighting Layout | Deep Earth Well Drilling | HE-EL-1730 | C-56-PL-607-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-Electrical Installation Drawings | Deep Earth Well Drilling | HE-EL-1790 | C-56-PL-607-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-F&G Cause and effect | Deep Earth Well Drilling | HE-HS-0350 | C-56-PL-607-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Issue ICR- Addendum to DGs | Deep Earth Well Drilling | HE-IC-0010 | C-56-PL-607-EI-1400 | SS | Completed | Not Started | 10
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Issue ICR-Instrument index -Update | Deep Earth Well Drilling | HE-IC-0490 | C-56-PL-607-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-Instrument Index | Deep Earth Well Drilling | HE-IC-0530 | C-56-PL-607-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-I/O list | Deep Earth Well Drilling | HE-IC-0590 | C-56-PL-607-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-Hook-Up Diagram | Deep Earth Well Drilling | HE-IC-0650 | C-56-PL-607-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-Typical Installation Drawings | Deep Earth Well Drilling | HE-IC-0710 | C-56-PL-607-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-Loop Diagrams | Deep Earth Well Drilling | HE-IC-0770 | C-56-PL-607-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Deep Earth Well Drilling | HE-IC-1430 | C-56-PL-607-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Deep Earth Well Drilling | HE-IC-1550 | C-56-PL-607-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Deep Earth Well Drilling | HE-IC-1550 | C-56-PL-607-EI-1400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Deep Earth Well Drilling | HE-IC-2570 | C-56-PL-607-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Issue ICR- P&ID's | Deep Earth Well Drilling | HE-PR-0110 | C-56-PL-607-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Deep Earth Well Drilling | HM-EL-0080 | C-56-PL-607-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-0280 | C-56-PL-607-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Receipt at site and inspection of Earthing Material (Lot 1) | Deep Earth Well Drilling | HM-EL-0380 | C-56-PL-607-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | 1st Electrical Bulk material MTO | Deep Earth Well Drilling | HM-EL-0520 | C-56-PL-607-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Deep Earth Well Drilling | HM-EL-630 | C-56-PL-607-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-650 | C-56-PL-607-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Receipt at site and inspection of Earthing Material (Lot 2) | Deep Earth Well Drilling | HM-EL-690 | C-56-PL-607-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | 1st Instrumentation Bulk material MTO | Deep Earth Well Drilling | HM-IC-0040 | C-56-PL-607-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Receipt at site and inspection of Isolator (Lot 1) | Deep Earth Well Drilling | HM-ME-0690 | C-56-PL-607-EI-1400 | FF | Not Started | Not Started | 26
P2543-R01-Oct24..PR.26.LL.8.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Receipt at site and inspection of AC UPS | Deep Earth Well Drilling | HM-ME-0790 | C-56-PL-607-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1590 | C-56-PL-607-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1690 | C-56-PL-607-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Deep Earth Well Drilling | HM-ME-2330 | C-56-PL-607-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Final Telecom Bulk material MTO | Deep Earth Well Drilling | HM-TL-0050 | C-56-PL-607-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Deep Earth Well Drilling | ML1032-B21 | C-56-PL-607-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-UPS SLD | Installation of Field Instruments (Including Pig Signaller) | HE-EL-0290 | C-56-PL-607-EI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of Field Instruments (Including Pig Signaller) | HE-EL-0530 | C-56-PL-607-EI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Obtain Company Approval-Data sheet for LV Distribution board | Installation of Field Instruments (Including Pig Signaller) | HE-EL-0640 | C-56-PL-607-EI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-Data sheet for LV Distribution board | Installation of Field Instruments (Including Pig Signaller) | HE-EL-0650 | C-56-PL-607-EI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | Installation of Field Instruments (Including Pig Signaller) | HE-EL-0710 | C-56-PL-607-EI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Installation of Field Instruments (Including Pig Signaller) | HE-EL-1010 | C-56-PL-607-EI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-Earthing Layout | Installation of Field Instruments (Including Pig Signaller) | HE-EL-1670 | C-56-PL-607-EI-2200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-Lighting Layout | Installation of Field Instruments (Including Pig Signaller) | HE-EL-1730 | C-56-PL-607-EI-2200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of Field Instruments (Including Pig Signaller) | HE-EL-1790 | C-56-PL-607-EI-2200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-F&G Cause and effect | Installation of Field Instruments (Including Pig Signaller) | HE-HS-0350 | C-56-PL-607-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Issue ICR- Addendum to DGs | Installation of Field Instruments (Including Pig Signaller) | HE-IC-0010 | C-56-PL-607-EI-2200 | SS | Completed | Not Started | 10
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Issue ICR-Instrument index -Update | Installation of Field Instruments (Including Pig Signaller) | HE-IC-0490 | C-56-PL-607-EI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-Instrument Index | Installation of Field Instruments (Including Pig Signaller) | HE-IC-0530 | C-56-PL-607-EI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-I/O list | Installation of Field Instruments (Including Pig Signaller) | HE-IC-0590 | C-56-PL-607-EI-2200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of Field Instruments (Including Pig Signaller) | HE-IC-0650 | C-56-PL-607-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of Field Instruments (Including Pig Signaller) | HE-IC-0710 | C-56-PL-607-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-Loop Diagrams | Installation of Field Instruments (Including Pig Signaller) | HE-IC-0770 | C-56-PL-607-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Installation of Field Instruments (Including Pig Signaller) | HE-IC-1430 | C-56-PL-607-EI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of Field Instruments (Including Pig Signaller) | HE-IC-1550 | C-56-PL-607-EI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of Field Instruments (Including Pig Signaller) | HE-IC-1550 | C-56-PL-607-EI-2200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Installation of Field Instruments (Including Pig Signaller) | HE-IC-2570 | C-56-PL-607-EI-2200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Issue ICR- P&ID's | Installation of Field Instruments (Including Pig Signaller) | HE-PR-0110 | C-56-PL-607-EI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of Field Instruments (Including Pig Signaller) | HM-EL-0080 | C-56-PL-607-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Field Instruments (Including Pig Signaller) | HM-EL-0280 | C-56-PL-607-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of Field Instruments (Including Pig Signaller) | HM-EL-0380 | C-56-PL-607-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | 1st Electrical Bulk material MTO | Installation of Field Instruments (Including Pig Signaller) | HM-EL-0520 | C-56-PL-607-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of Field Instruments (Including Pig Signaller) | HM-EL-630 | C-56-PL-607-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Field Instruments (Including Pig Signaller) | HM-EL-650 | C-56-PL-607-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of Field Instruments (Including Pig Signaller) | HM-EL-690 | C-56-PL-607-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | 1st Instrumentation Bulk material MTO | Installation of Field Instruments (Including Pig Signaller) | HM-IC-0040 | C-56-PL-607-EI-2200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Receipt at site and inspection of Isolator (Lot 1) | Installation of Field Instruments (Including Pig Signaller) | HM-ME-0690 | C-56-PL-607-EI-2200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.8.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Receipt at site and inspection of AC UPS | Installation of Field Instruments (Including Pig Signaller) | HM-ME-0790 | C-56-PL-607-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Installation of Field Instruments (Including Pig Signaller) | HM-ME-1590 | C-56-PL-607-EI-2200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Installation of Field Instruments (Including Pig Signaller) | HM-ME-1690 | C-56-PL-607-EI-2200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Receipt at site and inspection of Isolator (Lot 2) | Installation of Field Instruments (Including Pig Signaller) | HM-ME-2250 | C-56-PL-607-EI-2200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Installation of Field Instruments (Including Pig Signaller) | HM-ME-2330 | C-56-PL-607-EI-2200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Installation of Field Instruments (Including Pig Signaller) | HM-ME-2350 | C-56-PL-607-EI-2200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Final Telecom Bulk material MTO | Installation of Field Instruments (Including Pig Signaller) | HM-TL-0050 | C-56-PL-607-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Installation of Field Instruments (Including Pig Signaller) | ML1032-B21 | C-56-PL-607-EI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-Earthing Layout | Installation of Light Pole, Lighting & Fixtures | HE-EL-1670 | C-56-PL-607-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of Light Pole, Lighting & Fixtures | HE-IC-0710 | C-56-PL-607-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Obtain Company Approval-Data sheet for LV Distribution board | Installation of Light Pole, Lighting & Fixtures | HE-EL-0640 | C-56-PL-607-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of Light Pole, Lighting & Fixtures | HE-IC-1550 | C-56-PL-607-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-ME-1590 | C-56-PL-607-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | 1st Instrumentation Bulk material MTO | Installation of Light Pole, Lighting & Fixtures | HM-IC-0040 | C-56-PL-607-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-Loop Diagrams | Installation of Light Pole, Lighting & Fixtures | HE-IC-0770 | C-56-PL-607-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | 1st Electrical Bulk material MTO | Installation of Light Pole, Lighting & Fixtures | HM-EL-0520 | C-56-PL-607-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Issue ICR-Instrument index -Update | Installation of Light Pole, Lighting & Fixtures | HE-IC-0490 | C-56-PL-607-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Installation of Light Pole, Lighting & Fixtures | HE-IC-2570 | C-56-PL-607-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of Light Pole, Lighting & Fixtures | HE-IC-0650 | C-56-PL-607-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-EL-0080 | C-56-PL-607-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Installation of Light Pole, Lighting & Fixtures | ML1032-B21 | C-56-PL-607-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-Lighting Layout | Installation of Light Pole, Lighting & Fixtures | HE-EL-1730 | C-56-PL-607-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-UPS SLD | Installation of Light Pole, Lighting & Fixtures | HE-EL-0290 | C-56-PL-607-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Installation of Light Pole, Lighting & Fixtures | HE-IC-1430 | C-56-PL-607-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-F&G Cause and effect | Installation of Light Pole, Lighting & Fixtures | HE-HS-0350 | C-56-PL-607-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-EL-0280 | C-56-PL-607-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | Installation of Light Pole, Lighting & Fixtures | HE-EL-0710 | C-56-PL-607-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-Instrument Index | Installation of Light Pole, Lighting & Fixtures | HE-IC-0530 | C-56-PL-607-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Issue ICR- Addendum to DGs | Installation of Light Pole, Lighting & Fixtures | HE-IC-0010 | C-56-PL-607-EI-1800 | SS | Completed | Not Started | 10
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-Data sheet for LV Distribution board | Installation of Light Pole, Lighting & Fixtures | HE-EL-0650 | C-56-PL-607-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of Light Pole, Lighting & Fixtures | HE-EL-0530 | C-56-PL-607-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-I/O list | Installation of Light Pole, Lighting & Fixtures | HE-IC-0590 | C-56-PL-607-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of Light Pole, Lighting & Fixtures | HE-EL-1790 | C-56-PL-607-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Installation of Light Pole, Lighting & Fixtures | HE-EL-1010 | C-56-PL-607-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-ME-1690 | C-56-PL-607-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-EL-0380 | C-56-PL-607-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Receipt at site and inspection of Isolator (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-ME-0690 | C-56-PL-607-EI-1800 | FF | Not Started | Not Started | 26
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Issue ICR- P&ID's | Installation of Light Pole, Lighting & Fixtures | HE-PR-0110 | C-56-PL-607-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Telecom Bulk material MTO | Installation of Light Pole, Lighting & Fixtures | HM-TL-0050 | C-56-PL-607-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Receipt at site and inspection of Isolator (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-ME-2250 | C-56-PL-607-EI-1800 | FF | Not Started | Not Started | 26
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-ME-2330 | C-56-PL-607-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-ME-2350 | C-56-PL-607-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-EL-630 | C-56-PL-607-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-EL-650 | C-56-PL-607-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-EL-690 | C-56-PL-607-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of Light Pole, Lighting & Fixtures | HE-IC-1550 | C-56-PL-607-EI-1800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.1.1.12.8.1 PIDS SystemCCOHBIC211 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Installation of PIDS/ PLDS System | HE-TL-0710 | C-56-PL-607-TE-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.1.1.12.8.1 PIDS SystemCCOHBIC211 | Final Issue for Design/ Construction-Telecom Equipment Layout | Installation of PIDS/ PLDS System | HE-TL-0770 | C-56-PL-607-TE-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.8.1 PIDS SystemCCOHBIC211 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Installation of PIDS/ PLDS System | HM-ME-1290 | C-56-PL-607-TE-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.3.1.1.1.12.8.1 PIDS SystemCCOHBIC211 | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Installation of PIDS/ PLDS System | HE-TL-0290 | C-56-PL-607-TE-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.1.1.12.8.1 PIDS SystemCCOHBIC211 | Final Issue for Design/ Construction-Telecom cable schedule | Installation of PIDS/ PLDS System | HE-TL-0830 | C-56-PL-607-TE-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.1.1.12.8.1 PIDS SystemCCOHBIC211 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Installation of PIDS/ PLDS System | HE-TL-0470 | C-56-PL-607-TE-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..4.3.1.1.1.12.8.1 PIDS SystemCCOHBIC211 | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Installation of PIDS/ PLDS System | HE-TL-0410 | C-56-PL-607-TE-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..4.3.1.1.1.12.8.1 PIDS SystemCCOHBIC211 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Installation of PIDS/ PLDS System | HE-TL-0350 | C-56-PL-607-TE-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.8.1 PIDS SystemCCOHBIC211 | 1st Telecom Bulk material MTO | Installation of PIDS/ PLDS System | HM-TL-0040 | C-56-PL-607-TE-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.8.1 PIDS SystemCCOHBIC211 | Receipt at site and inspection of FOC Cables (Lot 1) | Installation of PIDS/ PLDS System | HM-EL-0180 | C-56-PL-607-TE-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.8.1 PIDS SystemCCOHBIC211 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Installation of PIDS/ PLDS System | ML1033-B22 | C-56-PL-607-TE-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.1.1.12.8.1 PIDS SystemCCOHBIC211 | FOC Splicing / Termination Subcontract Award | Installation of PIDS/ PLDS System | HS-CN-0290 | C-56-PL-607-TE-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.8.1 PIDS SystemCCOHBIC211 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Installation of PIDS/ PLDS System | HM-ME-2270 | C-56-PL-607-TE-1200 | FS | Not Started | Not Started | 34
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.8.1 PIDS SystemCCOHBIC211 | Receipt at site and inspection of FOC Cables (Lot 2) | Installation of PIDS/ PLDS System | HM-EL-610 | C-56-PL-607-TE-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Telephone SystemCCOHBIC221 (Deleted) | HE-TL-0290 | C-56-PL-607-TE-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Telephone SystemCCOHBIC221 (Deleted) | HE-TL-0350 | C-56-PL-607-TE-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Telephone SystemCCOHBIC221 (Deleted) | HE-TL-0410 | C-56-PL-607-TE-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Telephone SystemCCOHBIC221 (Deleted) | HE-TL-0470 | C-56-PL-607-TE-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Telephone SystemCCOHBIC221 (Deleted) | HE-TL-0710 | C-56-PL-607-TE-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Final Issue for Design/ Construction-Telecom Equipment Layout | Telephone SystemCCOHBIC221 (Deleted) | HE-TL-0770 | C-56-PL-607-TE-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Final Issue for Design/ Construction-Telecom cable schedule | Telephone SystemCCOHBIC221 (Deleted) | HE-TL-0830 | C-56-PL-607-TE-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Receipt at site and inspection of FOC Cables (Lot 1) | Telephone SystemCCOHBIC221 (Deleted) | HM-EL-0180 | C-56-PL-607-TE-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Receipt at site and inspection of FOC Cables (Lot 2) | Telephone SystemCCOHBIC221 (Deleted) | HM-EL-610 | C-56-PL-607-TE-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Telephone SystemCCOHBIC221 (Deleted) | HM-ME-1290 | C-56-PL-607-TE-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Telephone SystemCCOHBIC221 (Deleted) | HM-ME-2270 | C-56-PL-607-TE-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | 1st Telecom Bulk material MTO | Telephone SystemCCOHBIC221 (Deleted) | HM-TL-0040 | C-56-PL-607-TE-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | FOC Splicing / Termination Subcontract Award | Telephone SystemCCOHBIC221 (Deleted) | HS-CN-0290 | C-56-PL-607-TE-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.8.2 Telephone SystemCCOHBIC221 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Telephone SystemCCOHBIC221 (Deleted) | ML1033-B22 | C-56-PL-607-TE-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.3.1.1.1.12.8.3 CCTV SystemCCOHBIC231 | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Installation of CCTV System | HE-TL-0290 | C-56-PL-607-TE-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..4.3.1.1.1.12.8.3 CCTV SystemCCOHBIC231 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Installation of CCTV System | HE-TL-0350 | C-56-PL-607-TE-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..4.3.1.1.1.12.8.3 CCTV SystemCCOHBIC231 | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Installation of CCTV System | HE-TL-0410 | C-56-PL-607-TE-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.1.1.12.8.3 CCTV SystemCCOHBIC231 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Installation of CCTV System | HE-TL-0470 | C-56-PL-607-TE-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.1.1.12.8.3 CCTV SystemCCOHBIC231 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Installation of CCTV System | HE-TL-0710 | C-56-PL-607-TE-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.1.1.12.8.3 CCTV SystemCCOHBIC231 | Final Issue for Design/ Construction-Telecom Equipment Layout | Installation of CCTV System | HE-TL-0770 | C-56-PL-607-TE-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.1.1.12.8.3 CCTV SystemCCOHBIC231 | Final Issue for Design/ Construction-Telecom cable schedule | Installation of CCTV System | HE-TL-0830 | C-56-PL-607-TE-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.8.3 CCTV SystemCCOHBIC231 | Receipt at site and inspection of FOC Cables (Lot 1) | Installation of CCTV System | HM-EL-0180 | C-56-PL-607-TE-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.8.3 CCTV SystemCCOHBIC231 | Receipt at site and inspection of FOC Cables (Lot 2) | Installation of CCTV System | HM-EL-610 | C-56-PL-607-TE-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.8.3 CCTV SystemCCOHBIC231 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Installation of CCTV System | HM-ME-1290 | C-56-PL-607-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.8.3 CCTV SystemCCOHBIC231 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Installation of CCTV System | HM-ME-2270 | C-56-PL-607-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.8.3 CCTV SystemCCOHBIC231 | 1st Telecom Bulk material MTO | Installation of CCTV System | HM-TL-0040 | C-56-PL-607-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.1.1.12.8.3 CCTV SystemCCOHBIC231 | FOC Splicing / Termination Subcontract Award | Installation of CCTV System | HS-CN-0290 | C-56-PL-607-TE-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.8.3 CCTV SystemCCOHBIC231 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Installation of CCTV System | ML1033-B22 | C-56-PL-607-TE-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.3.1.3.19.8.1.8 ROW Access RoadCCOPL52468 | Construction NOC from Musanada | Sabka ROW/Grading | C-GOV-1300 | C-52-06CR-PL-CI-1800 | SS | In Progress | Not Started | 60
P2543-R01-Oct24..1.EN.4.18 HSEIA Study Report | P2543-R01-Oct24..4.3.1.3.19.8.1.6 Cut & Fill in Sandy AreaCCOPL52494 | Receive Company Comments- HSEIA Study Report | Cut & Fill (@ Non-Sabkha) | HE-HS-0500 | C-52-06CR-PL-CI-1400 | FF | Completed | Not Started | 21
P2543-R01-Oct24..1.2.12.10 Earthworks | P2543-R01-Oct24..4.3.1.3.19.8.1.6 Cut & Fill in Sandy AreaCCOPL52494 | Earthworks Subcontract Award | Cut & Fill (@ Non-Sabkha) | HS-CN-0490 | C-52-06CR-PL-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.1.2.12.1.1 Excavation WorksCCOHBCS104 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-56-EB2-CI-1000 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.1.2.12.1.1 Excavation WorksCCOHBCS104 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-56-EB2-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.1.2.12.1.1 Excavation WorksCCOHBCS104 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-56-EB2-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.2.12.1.1 Excavation WorksCCOHBCS104 | Issue Civil / Structural Drawings for Launcher/ Receiver facilities | Site Survey, Preparation & Grading Works | ML1199-B24 | C-56-EB2-CI-1000 | FS | Completed | Completed | 7
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.2.12.1.3 Concrete Superstructure WorksCCOHBCS109 | Final Civil Bulk material MTO | Concrete Superstructure Works | HM-CS-0050 | C-56-EB2-CI-1400 | FF | Not Started | In Progress | 2
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.2.12.1.3 Concrete Superstructure WorksCCOHBCS109 | 1st Civil Bulk material MTO | Concrete Superstructure Works | HM-CS-0040 | C-56-EB2-CI-1400 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.1.2.12.1.3 Concrete Superstructure WorksCCOHBCS109 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Superstructure Works | HE-CS-0230 | C-56-EB2-CI-1400 | FF | Completed | In Progress | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.2.12.1.6 Metal WorksCCOHBCS117 | 1st Structural Bulk material MTO | Steel Structural Works | HM-CS-0110 | C-56-EB2-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.1.2.12.1.7 Paving WorksCCOHBCS118 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving Works | HE-CS-0290 | C-56-EB2-CI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.2.12.1.7 Paving WorksCCOHBCS118 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving Works | ML1059-B28 | C-56-EB2-CI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.13 E&I Works | P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | E&I Works Subcontract Award | Plumbing Works | HS-CN-0640 | C-56-EB2-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | Receipt at site and inspection of HVAC Equipment | Plumbing Works | HM-ME-1790 | C-56-EB2-ME-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.12 Building | P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | Building Subcontract Award | Plumbing Works | HS-CN-0590 | C-56-EB2-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Plumbing Works | ML1015-B08 | C-56-EB2-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.13 E&I Works | P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | E&I Works Subcontract Award | HVAC Works | HS-CN-0640 | C-56-EB2-ME-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | Receipt at site and inspection of HVAC Equipment | HVAC Works | HM-ME-1790 | C-56-EB2-ME-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.12 Building | P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | Building Subcontract Award | HVAC Works | HS-CN-0590 | C-56-EB2-ME-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | HVAC Works | ML1015-B08 | C-56-EB2-ME-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | Receipt at site and inspection of HVAC Equipment | Plumbing Works | HM-ME-1790 | C-56-EB2-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.2.1 HVAC System & Plumbing WorksCCOHBME308 | Receipt at site and inspection of HVAC Equipment | HVAC Works | HM-ME-1790 | C-56-EB2-ME-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.12 Building | P2543-R01-Oct24..4.3.1.1.2.12.2.2 Inergen SystemCCOHBME348 | Building Subcontract Award | Inergen SystemCCOHBME348 (Deleted) | HS-CN-0590 | C-56-EB2-ME-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.2.12.2.2 Inergen SystemCCOHBME348 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Inergen SystemCCOHBME348 (Deleted) | ML1015-B08 | C-56-EB2-ME-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Data Sheet for LV cables | Custody Metering Panel Installation | HE-EL-0830 | C-56-EB2-EI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Custody Metering Panel Installation | HM-EL-0080 | C-56-EB2-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Custody Metering Panel Installation | HE-IC-0950 | C-56-EB2-EI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | 1st Electrical Bulk material MTO | Custody Metering Panel Installation | HM-EL-0520 | C-56-EB2-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Cable Sizing Calculation | Custody Metering Panel Installation | HE-EL-0470 | C-56-EB2-EI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Custody Metering Panel Installation | HE-IC-0830 | C-56-EB2-EI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Cable Routing Layout | Custody Metering Panel Installation | HE-EL-1610 | C-56-EB2-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Cable Schedule | Custody Metering Panel Installation | HE-EL-0590 | C-56-EB2-EI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Instrument Trench Layout | Custody Metering Panel Installation | HE-IC-1010 | C-56-EB2-EI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Data Sheet for HV cables | Custody Metering Panel Installation | HE-EL-1950 | C-56-EB2-EI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Specification for RTU | Custody Metering Panel Installation | HE-IC-0230 | C-56-EB2-EI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Specification for Leak Detection System | Custody Metering Panel Installation | HE-IC-0290 | C-56-EB2-EI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-I/O list | Custody Metering Panel Installation | HE-IC-0590 | C-56-EB2-EI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Re-Issue for Approval- I/O list -Update | Custody Metering Panel Installation | HE-IC-0570 | C-56-EB2-EI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Re-Issue for Approval- Specification for RTU | Custody Metering Panel Installation | HE-IC-0210 | C-56-EB2-EI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Re-Issue for Approval- Specification for Leak Detection System | Custody Metering Panel Installation | HE-IC-0270 | C-56-EB2-EI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Issue ICR- Instrument Cable Block Diagram | Custody Metering Panel Installation | HE-IC-0790 | C-56-EB2-EI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Issue ICR- Specification for Leak Detection System | Custody Metering Panel Installation | HE-IC-0250 | C-56-EB2-EI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Issue ICR- Specification for RTU | Custody Metering Panel Installation | HE-IC-0190 | C-56-EB2-EI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Custody Metering Panel Installation | HM-EL-630 | C-56-EB2-EI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Receipt at site and inspection of MCT (Lot 1) | Installation of Power Distribution System | HM-EL-0480 | C-56-EB2-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of Power Distribution System | HE-IC-0650 | C-56-EB2-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Final Issue for Design/ Construction-I/O list | Installation of Power Distribution System | HE-IC-0590 | C-56-EB2-EI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of Power Distribution System | HE-EL-0530 | C-56-EB2-EI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of Power Distribution System | HE-IC-0710 | C-56-EB2-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Receipt at site and inspection of Power Distribution Boards | Installation of Power Distribution System | HM-ME-0890 | C-56-EB2-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Final Issue for Design/ Construction-Earthing Layout | Installation of Power Distribution System | HE-EL-1670 | C-56-EB2-EI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Final Issue for Design/ Construction-Lighting Layout | Installation of Power Distribution System | HE-EL-1730 | C-56-EB2-EI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Installation of Power Distribution System | HM-ME-1590 | C-56-EB2-EI-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of Power Distribution System | HM-EL-0080 | C-56-EB2-EI-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Issue ICR-Instrument index -Update | Installation of Power Distribution System | HE-IC-0490 | C-56-EB2-EI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of Power Distribution System | HM-EL-0380 | C-56-EB2-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | Installation of Power Distribution System | HM-ME-1390 | C-56-EB2-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of Power Distribution System | HE-EL-1790 | C-56-EB2-EI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Final Issue for Design/ Construction-Instrument Index | Installation of Power Distribution System | HE-IC-0530 | C-56-EB2-EI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Issue ICR- Addendum to DGs | Installation of Power Distribution System | HE-IC-0010 | C-56-EB2-EI-1000 | SS | Completed | Not Started | 10
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Power Distribution System | HM-EL-0280 | C-56-EB2-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Final Issue for Design/ Construction-Loop Diagrams | Installation of Power Distribution System | HE-IC-0770 | C-56-EB2-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | 1st Electrical Bulk material MTO | Installation of Power Distribution System | HM-EL-0520 | C-56-EB2-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Issue ICR- P&ID's | Installation of Power Distribution System | HE-PR-0110 | C-56-EB2-EI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | Installation of Power Distribution System | HM-ME-2290 | C-56-EB2-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Installation of Power Distribution System | HM-ME-2330 | C-56-EB2-EI-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of Power Distribution System | HM-EL-630 | C-56-EB2-EI-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Power Distribution System | HM-EL-650 | C-56-EB2-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of Power Distribution System | HM-EL-690 | C-56-EB2-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Receipt at site and inspection of MCT (Lot 2) | Installation of Power Distribution System | HM-EL-710 | C-56-EB2-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Data Sheet for LV cables | E&I Cable Laying | HE-EL-0830 | C-56-EB2-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Receipt at site and inspection of Power & Control Cables (Lot 1) | E&I Cable Laying | HM-EL-0080 | C-56-EB2-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | E&I Cable Laying | HE-IC-0950 | C-56-EB2-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | 1st Electrical Bulk material MTO | E&I Cable Laying | HM-EL-0520 | C-56-EB2-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Cable Sizing Calculation | E&I Cable Laying | HE-EL-0470 | C-56-EB2-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | E&I Cable Laying | HE-IC-0830 | C-56-EB2-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Cable Routing Layout | E&I Cable Laying | HE-EL-1610 | C-56-EB2-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Cable Schedule | E&I Cable Laying | HE-EL-0590 | C-56-EB2-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Instrument Trench Layout | E&I Cable Laying | HE-IC-1010 | C-56-EB2-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Data Sheet for HV cables | E&I Cable Laying | HE-EL-1950 | C-56-EB2-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Specification for RTU | E&I Cable Laying | HE-IC-0230 | C-56-EB2-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Specification for Leak Detection System | E&I Cable Laying | HE-IC-0290 | C-56-EB2-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-I/O list | E&I Cable Laying | HE-IC-0590 | C-56-EB2-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Re-Issue for Approval- I/O list -Update | E&I Cable Laying | HE-IC-0570 | C-56-EB2-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Re-Issue for Approval- Specification for RTU | E&I Cable Laying | HE-IC-0210 | C-56-EB2-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Re-Issue for Approval- Specification for Leak Detection System | E&I Cable Laying | HE-IC-0270 | C-56-EB2-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Issue ICR- Instrument Cable Block Diagram | E&I Cable Laying | HE-IC-0790 | C-56-EB2-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Issue ICR- Specification for Leak Detection System | E&I Cable Laying | HE-IC-0250 | C-56-EB2-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Issue ICR- Specification for RTU | E&I Cable Laying | HE-IC-0190 | C-56-EB2-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Receipt at site and inspection of Power & Control Cables (Lot 2) | E&I Cable Laying | HM-EL-630 | C-56-EB2-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Data Sheet for LV cables | MCT Installation | HE-EL-0830 | C-56-EB2-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Receipt at site and inspection of Power & Control Cables (Lot 1) | MCT Installation | HM-EL-0080 | C-56-EB2-EI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | MCT Installation | HE-IC-0950 | C-56-EB2-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | 1st Electrical Bulk material MTO | MCT Installation | HM-EL-0520 | C-56-EB2-EI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Cable Sizing Calculation | MCT Installation | HE-EL-0470 | C-56-EB2-EI-1220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | MCT Installation | HE-IC-0830 | C-56-EB2-EI-1220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Cable Routing Layout | MCT Installation | HE-EL-1610 | C-56-EB2-EI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Cable Schedule | MCT Installation | HE-EL-0590 | C-56-EB2-EI-1220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Instrument Trench Layout | MCT Installation | HE-IC-1010 | C-56-EB2-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Data Sheet for HV cables | MCT Installation | HE-EL-1950 | C-56-EB2-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Specification for RTU | MCT Installation | HE-IC-0230 | C-56-EB2-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-Specification for Leak Detection System | MCT Installation | HE-IC-0290 | C-56-EB2-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Final Issue for Design/ Construction-I/O list | MCT Installation | HE-IC-0590 | C-56-EB2-EI-1220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Re-Issue for Approval- I/O list -Update | MCT Installation | HE-IC-0570 | C-56-EB2-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Re-Issue for Approval- Specification for RTU | MCT Installation | HE-IC-0210 | C-56-EB2-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Re-Issue for Approval- Specification for Leak Detection System | MCT Installation | HE-IC-0270 | C-56-EB2-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Issue ICR- Instrument Cable Block Diagram | MCT Installation | HE-IC-0790 | C-56-EB2-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Issue ICR- Specification for Leak Detection System | MCT Installation | HE-IC-0250 | C-56-EB2-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Issue ICR- Specification for RTU | MCT Installation | HE-IC-0190 | C-56-EB2-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.2 E&I Cable Laying, Glanding & TerminationCCOHBEL203 | Receipt at site and inspection of Power & Control Cables (Lot 2) | MCT Installation | HM-EL-630 | C-56-EB2-EI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.1.2.12.4.1 SDH CabinetCCOHBIC201 | Final Issue for Design/ Construction-Telecom cable schedule | SDH Cabinet Installation | HE-TL-0830 | C-56-EB2-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.2.12.4.1 SDH CabinetCCOHBIC201 | 1st Telecom Bulk material MTO | SDH Cabinet Installation | HM-TL-0040 | C-56-EB2-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.4.1 SDH CabinetCCOHBIC201 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | SDH Cabinet Installation | HM-ME-1390 | C-56-EB2-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.4.1 SDH CabinetCCOHBIC201 | Receipt at site and inspection of FOC Cables (Lot 1) | SDH Cabinet Installation | HM-EL-0180 | C-56-EB2-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.2.12.4.1 SDH CabinetCCOHBIC201 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | SDH Cabinet Installation | ML1033-B22 | C-56-EB2-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.1.2.12.4.1 SDH CabinetCCOHBIC201 | Final Issue for Design/ Construction-Telecom Equipment Layout | SDH Cabinet Installation | HE-TL-0770 | C-56-EB2-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.1.2.12.4.1 SDH CabinetCCOHBIC201 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | SDH Cabinet Installation | HE-TL-0470 | C-56-EB2-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.1.2.12.4.1 SDH CabinetCCOHBIC201 | FOC Splicing / Termination Subcontract Award | SDH Cabinet Installation | HS-CN-0290 | C-56-EB2-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.1.2.12.4.1 SDH CabinetCCOHBIC201 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | SDH Cabinet Installation | HE-TL-0710 | C-56-EB2-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.4.1 SDH CabinetCCOHBIC201 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | SDH Cabinet Installation | HM-ME-2290 | C-56-EB2-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.4.1 SDH CabinetCCOHBIC201 | Receipt at site and inspection of FOC Cables (Lot 2) | SDH Cabinet Installation | HM-EL-610 | C-56-EB2-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | P2543-R01-Oct24..4.3.1.1.2.12.5.1 Shutdown Connection to Existing Substation Unit 607CCOHBST204 | Final Issue for Design/ Construction-Shutdown Requirements & Plan | Termination & Connection with Existing Power Distribution Network | C-COM-890 | C-56-EB2-EL-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.3.10.40.1 Demolition Works (Paving)CCOHBCS300 | Issue Civil / Structural Drawings for Launcher/ Receiver facilities | Demolition of Existing Paving | ML1199-B24 | C-56-G-HT-CI-0100 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.1.3.10.40.2 Excavation WorksCCOHBCS301 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-56-G-HT-CI-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.1.3.10.40.2 Excavation WorksCCOHBCS301 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-56-G-HT-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.1.3.10.40.2 Excavation WorksCCOHBCS301 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-56-G-HT-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.1.3.10.40.2 Excavation WorksCCOHBCS301 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Site Survey, Preparation & Grading Works | HE-CS-0470 | C-56-G-HT-CI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.1.3.10.40.3 Concrete WorksCCOHBCS302 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Pipe Support Foundations | HE-CS-0230 | C-56-G-HT-CI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | P2543-R01-Oct24..4.3.1.1.3.10.40.3 Concrete WorksCCOHBCS302 | Final Issue for Design/ Construction-Design Calculation for Typical Pipe supports | Concrete Works for Pipe Support Foundations | HE-CS-1130 | C-56-G-HT-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.3.10.40.3 Concrete WorksCCOHBCS302 | 1st Civil Bulk material MTO | Concrete Works for Pipe Support Foundations | HM-CS-0040 | C-56-G-HT-CI-1600 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.3.10.40.3 Concrete WorksCCOHBCS302 | Final Civil Bulk material MTO | Concrete Works for Pipe Support Foundations | HM-CS-0050 | C-56-G-HT-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.1.3.10.40.5 Pipe Supports Fabrication & InstallationCCOHBSS307 | Fabrication Facilities | Pipe Supports Fabrication & Installation | CTF-SO1050 | C-56-G-HT-CI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.1.3.10.40.5 Pipe Supports Fabrication & InstallationCCOHBSS307 | Fence Works Subcontract Award | Pipe Supports Fabrication & Installation | HS-CN-0690 | C-56-G-HT-CI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.3.10.40.5 Pipe Supports Fabrication & InstallationCCOHBSS307 | Final Structural Bulk material MTO | Pipe Supports Fabrication & Installation | HM-CS-0120 | C-56-G-HT-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.3.1.1.3.10.40.5 Pipe Supports Fabrication & InstallationCCOHBSS307 | Final Issue for Design/ Construction-Misc. supports | Pipe Supports Fabrication & Installation | HE-CS-1490 | C-56-G-HT-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.3.10.40.5 Pipe Supports Fabrication & InstallationCCOHBSS307 | 1st Structural Bulk material MTO | Pipe Supports Fabrication & Installation | HM-CS-0110 | C-56-G-HT-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.3.1.1.3.10.40.5 Pipe Supports Fabrication & InstallationCCOHBSS307 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Pipe Supports Fabrication & Installation | HE-CS-1430 | C-56-G-HT-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.3.10.40.6 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS310 | 1st Structural Bulk material MTO | Concrete Works for Access Platforms & Misc. Structural Foundations | HM-CS-0110 | C-56-G-HT-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.1.3.10.40.6 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOHBSS310 | Fence Works Subcontract Award | Concrete Works for Access Platforms & Misc. Structural Foundations | HS-CN-0690 | C-56-G-HT-CI-1420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.3.10.40.7 Paving WorksCCOHBCS305 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-56-G-HT-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.1.3.10.40.7 Paving WorksCCOHBCS305 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-56-G-HT-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.1.3.10.2.1 Piping Pre-FabricationCCOHBPI309 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-56-G-HT-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.1.3.10.2.1 Piping Pre-FabricationCCOHBPI309 | Fabrication Facilities | Piping Pre-Fabrication | CTF-SO1050 | C-56-G-HT-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.1.3.10.2.1 Piping Pre-FabricationCCOHBPI309 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Pre-Fabrication | HE-PR-0890 | C-56-G-HT-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.1.3.10.2.1 Piping Pre-FabricationCCOHBPI309 | NDT / PWHT Subcontract Award | Piping Pre-Fabrication | HS-CN-0190 | C-56-G-HT-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.1.3.10.2.1 Piping Pre-FabricationCCOHBPI309 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-56-G-HT-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.3.10.2.1 Piping Pre-FabricationCCOHBPI309 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Piping Pre-Fabrication | ML1014-B10 | C-56-G-HT-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.3.10.2.1 Piping Pre-FabricationCCOHBPI309 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-56-G-HT-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.11 Overall Plot Plan - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..4.3.1.1.3.10.2.1 Piping Pre-FabricationCCOHBPI309 | Final Issue for Design/ Construction-Overall Plot Plan- 56" Pipeline Launcher and metering Station (Habshan Complex) | Piping Pre-Fabrication | HE-PI-0370 | C-56-G-HT-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.8 Piping GA - 56" Pipeline Launcher and metering Station (Habshan Complex) | P2543-R01-Oct24..4.3.1.1.3.10.2.1 Piping Pre-FabricationCCOHBPI309 | Final Issue for Design/ Construction-Piping GA- 56" Pipeline Launcher and metering Station (Habshan Complex) | Piping Pre-Fabrication | HE-PI-0640 | C-56-G-HT-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.1.3.10.2.1 Piping Pre-FabricationCCOHBPI309 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-56-G-HT-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.3.10.2.1 Piping Pre-FabricationCCOHBPI309 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-56-G-HT-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.1.3.10.2.1 Piping Pre-FabricationCCOHBPI309 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Pre-Fabrication | HE-PR-0290 | C-56-G-HT-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | Project Kick off Meeting | Piping Erection | ML1002 | C-56-G-HT-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Erection | HE-PR-0890 | C-56-G-HT-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | NDT / PWHT Subcontract Award | Piping Erection | HS-CN-0190 | C-56-G-HT-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Erection | HM-PL-0630 | C-56-G-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | Final Issue for Design/ Construction-Piping Isometrics | Piping Erection | HE-PI-1240 | C-56-G-HT-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Piping Erection | ML1014-B10 | C-56-G-HT-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Erection | ML1219-B19 | C-56-G-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Erection | HM-PL-0220 | C-56-G-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Erection | HM-PL-0640 | C-56-G-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | Piping MTO - Final | Piping Erection | HE-PI-1300 | C-56-G-HT-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Erection | HM-PL-0740 | C-56-G-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | 1st Piping Bulk material MTO | Piping Erection | HM-PI-0040 | C-56-G-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Erection | HE-PR-0290 | C-56-G-HT-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Erection | HM-PL-1510 | C-56-G-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.2 ErectionCCOHBPI372 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Erection | HM-PL-1570 | C-56-G-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.1.3.10.2.3 Field Joint Welding & NDTCCOHBPI382 | Piping MTO - Final | Field Joint Welding | HE-PI-1300 | C-56-G-HT-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.1.3.10.2.3 Field Joint Welding & NDTCCOHBPI382 | Project Kick off Meeting | Field Joint Welding | ML1002 | C-56-G-HT-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.1.3.10.2.3 Field Joint Welding & NDTCCOHBPI382 | NDT / PWHT Subcontract Award | Field Joint Welding | HS-CN-0190 | C-56-G-HT-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.3.10.2.3 Field Joint Welding & NDTCCOHBPI382 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Field Joint Welding | ML1014-B10 | C-56-G-HT-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.3.10.2.3 Field Joint Welding & NDTCCOHBPI382 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Field Joint Welding | ML1219-B19 | C-56-G-HT-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.3.10.2.4 HydrotestingCCOHBPI392 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Hydrotesting | ML1014-B10 | C-56-G-HT-PI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.3.10.2.4 HydrotestingCCOHBPI392 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Hydrotesting | ML1219-B19 | C-56-G-HT-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.1.3.10.2.5 Installation of ValvesCCOHBPI402 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Installation of Valves/GOV/ROV | HE-PR-0890 | C-56-G-HT-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.5 Installation of ValvesCCOHBPI402 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Installation of Valves/GOV/ROV | HM-PL-0630 | C-56-G-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.1.3.10.2.5 Installation of ValvesCCOHBPI402 | Final Issue for Design/ Construction-Piping Isometrics | Installation of Valves/GOV/ROV | HE-PI-1240 | C-56-G-HT-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.3.10.2.5 Installation of ValvesCCOHBPI402 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Installation of Valves/GOV/ROV | ML1014-B10 | C-56-G-HT-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.3.10.2.5 Installation of ValvesCCOHBPI402 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Installation of Valves/GOV/ROV | ML1219-B19 | C-56-G-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.5 Installation of ValvesCCOHBPI402 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Installation of Valves/GOV/ROV | HM-PL-0220 | C-56-G-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.5 Installation of ValvesCCOHBPI402 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Installation of Valves/GOV/ROV | HM-PL-0640 | C-56-G-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.5 Installation of ValvesCCOHBPI402 | Receipt at site and inspection of Isolating Joints (Lot 1) | Installation of Valves/GOV/ROV | HM-PL-0740 | C-56-G-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.1.3.10.2.5 Installation of ValvesCCOHBPI402 | Final Issue for Design/ Construction-Tie-In Schedule | Installation of Valves/GOV/ROV | HE-PR-0290 | C-56-G-HT-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.5 Installation of ValvesCCOHBPI402 | Receipt at site and inspection of Isolating Joints (Lot 2) | Installation of Valves/GOV/ROV | HM-PL-1510 | C-56-G-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.5 Installation of ValvesCCOHBPI402 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Installation of Valves/GOV/ROV | HM-PL-1570 | C-56-G-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | Piping MTO - Final | Final Bolt Torquing/ Re-Instatement | HE-PI-1300 | C-56-G-HT-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | Project Kick off Meeting | Final Bolt Torquing/ Re-Instatement | ML1002 | C-56-G-HT-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Final Bolt Torquing/ Re-Instatement | HE-PR-0890 | C-56-G-HT-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | NDT / PWHT Subcontract Award | Final Bolt Torquing/ Re-Instatement | HS-CN-0190 | C-56-G-HT-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0630 | C-56-G-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | Final Issue for Design/ Construction-Piping Isometrics | Final Bolt Torquing/ Re-Instatement | HE-PI-1240 | C-56-G-HT-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Final Bolt Torquing/ Re-Instatement | ML1014-B10 | C-56-G-HT-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Final Bolt Torquing/ Re-Instatement | ML1219-B19 | C-56-G-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0220 | C-56-G-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0640 | C-56-G-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | Receipt at site and inspection of Isolating Joints (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0740 | C-56-G-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | Final Issue for Design/ Construction-Tie-In Schedule | Final Bolt Torquing/ Re-Instatement | HE-PR-0290 | C-56-G-HT-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | Receipt at site and inspection of Isolating Joints (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1510 | C-56-G-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1570 | C-56-G-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.3.1 Preparation, Marking & UT for Existing Line 42" LineCCOHBHT265 | Receipt at site and inspection of Pigging & Split Tee (Lot 1) | Preparation, Marking & UT for Existing Line 42" Line | HM-PL-0840 | C-56-G-HT101-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.3.1.1.3.10.3.1 Preparation, Marking & UT for Existing Line 42" LineCCOHBHT265 | Procedure Qualification (PQT/WQT for Hot Tapping - 48", 42",36 & 30") | Preparation, Marking & UT for Existing Line 42" Line | C-COM-1020 | C-56-G-HT101-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | P2543-R01-Oct24..4.3.1.1.3.10.3.1 Preparation, Marking & UT for Existing Line 42" LineCCOHBHT265 | Final Issue for Design/ Construction-Piping Tie In Schedule | Preparation, Marking & UT for Existing Line 42" Line | HE-PI-3520 | C-56-G-HT101-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | P2543-R01-Oct24..4.3.1.1.3.10.3.1 Preparation, Marking & UT for Existing Line 42" LineCCOHBHT265 | Final Issue for Design/ Construction-Data Sheet - Split Tee | Preparation, Marking & UT for Existing Line 42" Line | HE-PL-1370 | C-56-G-HT101-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.3.10.3.1 Preparation, Marking & UT for Existing Line 42" LineCCOHBHT265 | 1st Piping Bulk material MTO | Preparation, Marking & UT for Existing Line 42" Line | HM-PI-0040 | C-56-G-HT101-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.3.1 Preparation, Marking & UT for Existing Line 42" LineCCOHBHT265 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Preparation, Marking & UT for Existing Line 42" Line | HM-PL-0220 | C-56-G-HT101-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.24.2 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.3.1 Preparation, Marking & UT for Existing Line 42" LineCCOHBHT265 | Receipt at site and inspection of Hot Tapping Material | Preparation, Marking & UT for Existing Line 42" Line | HM-PL-0320 | C-56-G-HT101-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.3.1 Preparation, Marking & UT for Existing Line 42" LineCCOHBHT265 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Preparation, Marking & UT for Existing Line 42" Line | HM-PL-1570 | C-56-G-HT101-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.11 Hot Tapping | P2543-R01-Oct24..4.3.1.1.3.10.3.1 Preparation, Marking & UT for Existing Line 42" LineCCOHBHT265 | Hot Tapping Subcontract Award | Preparation, Marking & UT for Existing Line 42" Line | HS-CN-0540 | C-56-G-HT101-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.1.5 Hot Tapping | P2543-R01-Oct24..4.3.1.1.3.10.3.1 Preparation, Marking & UT for Existing Line 42" LineCCOHBHT265 | Commercial Clarifications & Placement of PO- Hot Tapping | Preparation, Marking & UT for Existing Line 42" Line | HS-GN-0230 | C-56-G-HT101-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.24.2 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.3.10.3.1 Preparation, Marking & UT for Existing Line 42" LineCCOHBHT265 | Receipt at site and inspection of Hot Tapping Material | Preparation, Marking & UT for Existing Line 42" Line | HM-PL-0320 | C-56-G-HT101-ME-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.3.1.1.3.10.3.2 Split Tee Welding (42" X 42")CCOHBHT275 | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | Split Tee Welding (42" X 42") | C-COM-1010 | C-56-G-HT101-ME-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.2.2.12.4.1.7 SurveyingCCOPL56200 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Survey Marking | CTF-1000 | C-56-HC01-PL-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.2.2.12.4.1.7 SurveyingCCOPL56200 | NOC's / Approval /Survey | Survey Marking | CTF-1010 | C-56-HC01-PL-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.2.2.12.4.1.7 SurveyingCCOPL56200 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Survey Marking | CTF-1000 | C-56-HC01-PL-CI-1000 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.2.2.12.4.1.7 SurveyingCCOPL56200 | NOC's / Approval /Survey | Survey Marking | CTF-1010 | C-56-HC01-PL-CI-1000 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.2.2.12.4.1.8 Cut & FillCCOPL56201 | Satellite Office-1 | Cut & Fill (@ Non-Sabkha) | CTF-SO1020 | C-56-HC01-PL-CI-1400 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.2.2.12.4.1.9 ROW Access RoadCCOPL56203 | Satellite Office-1 | Non-Sabka ROW/Grading | CTF-SO1020 | C-56-HC01-PL-CI-1800 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.2.2.12.4.1.10 Excavation (incl Bedding) from Habshan complex to KP 6CCOPL56206.1 | Topographical Survey | Trench Excavation | HE-SS-0030 | C-56-HC01-PL-CI-2400 | SS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.2.2.12.4.1.10 Excavation (incl Bedding) from Habshan complex to KP 6CCOPL56206.1 | Project Kick off Meeting | Trench Excavation | ML1002 | C-56-HC01-PL-CI-2400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | Receive at Site - Hot Bends for 56" Pipeline | Stringing (BVS-01 to HBCMPLX) | ML1439-D10 | C-56-HC01-PL-ME-2800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.13 Pipeline Schematic Arrangement- 56", 52" and 4" Pipline | P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | Final Issue for Design/ Construction-Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | Stringing (BVS-01 to HBCMPLX) | HE-PL-0350 | C-56-HC01-PL-ME-2800 | FF | Completed | Not Started | 21
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | Issue Construction Execution Plan/ Procedures/ Method Statements along with Procedures & Philosophies-Final Issue | Stringing (BVS-01 to HBCMPLX) | ML1003-A03 | C-56-HC01-PL-ME-2800 | FF | Completed | Not Started | 21
P2543-R01-Oct24..PR.BK.6.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | 1st Pipeline Bulk material MTO | Stringing (BVS-01 to HBCMPLX) | HM-PL-0880 | C-56-HC01-PL-ME-2800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.3.1.2.2.12.4.1.16 Automatic WeldingCCOPL56207 | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | Automatic Welding | C-COM-1010 | C-56-HC01-PL-ME-3600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.6.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.2.12.4.1.16 Automatic WeldingCCOPL56207 | 1st Pipeline Bulk material MTO | Automatic Welding | HM-PL-0880 | C-56-HC01-PL-ME-3600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.2.2.12.4.1.17 NDT TestCCOPL56208 | NDT / PWHT Subcontract Award | NDT | HS-CN-0190 | C-56-HC01-PL-ME-4000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Lowering | ML1149-A07 | C-56-HC01-PL-ME-4800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (56" Pipeline) | Lowering | ML1139-A06 | C-56-HC01-PL-ME-4800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.1.2.2.12.4.1.19 Pipe Lowering & Tie-in / NDT from Habshan complex to KP 6CCOPL56212.1 | NDRC Subcontract Award | Lowering | HS-CN-0090 | C-56-HC01-PL-ME-4800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Final Issue for Design/ Construction-Telecom Equipment Layout | FO - Cable Pulling/ Laying | HE-TL-0770 | C-56-HC01-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | FO - Cable Pulling/ Laying | HE-TL-0470 | C-56-HC01-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Final Issue for Design/ Construction-Telecom cable schedule | FO - Cable Pulling/ Laying | HE-TL-0830 | C-56-HC01-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | 1st Telecom Bulk material MTO | FO - Cable Pulling/ Laying | HM-TL-0040 | C-56-HC01-PL-TE-8200 | FS | Not Started | Not Started | 32
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Receipt at site and inspection of FOC Cables (Lot 1) | FO - Cable Pulling/ Laying | HM-EL-0180 | C-56-HC01-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | FO - Cable Pulling/ Laying | ML1033-B22 | C-56-HC01-PL-TE-8200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | FO - Cable Pulling/ Laying | HE-TL-0710 | C-56-HC01-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | FOC Splicing / Termination Subcontract Award | FO - Cable Pulling/ Laying | HS-CN-0290 | C-56-HC01-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | FO - Cable Pulling/ Laying | HE-IC-0110 | C-56-HC01-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Receipt at site and inspection of FOC Cables (Lot 2) | FO - Cable Pulling/ Laying | HM-EL-610 | C-56-HC01-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Final Issue for Design/ Construction-Telecom Equipment Layout | FO - Cable Pulling/ Laying | HE-TL-0770 | C-56-HC01-PL-TE-8400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | FO - Cable Pulling/ Laying | HE-TL-0470 | C-56-HC01-PL-TE-8400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Final Issue for Design/ Construction-Telecom cable schedule | FO - Cable Pulling/ Laying | HE-TL-0830 | C-56-HC01-PL-TE-8400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | 1st Telecom Bulk material MTO | FO - Cable Pulling/ Laying | HM-TL-0040 | C-56-HC01-PL-TE-8400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Receipt at site and inspection of FOC Cables (Lot 1) | FO - Cable Pulling/ Laying | HM-EL-0180 | C-56-HC01-PL-TE-8400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | FO - Cable Pulling/ Laying | ML1033-B22 | C-56-HC01-PL-TE-8400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | FO - Cable Pulling/ Laying | HE-TL-0710 | C-56-HC01-PL-TE-8400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | FOC Splicing / Termination Subcontract Award | FO - Cable Pulling/ Laying | HS-CN-0290 | C-56-HC01-PL-TE-8400 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | FO - Cable Pulling/ Laying | HE-IC-0110 | C-56-HC01-PL-TE-8400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Receipt at site and inspection of FOC Cables (Lot 2) | FO - Cable Pulling/ Laying | HM-EL-610 | C-56-HC01-PL-TE-8400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.13.11 Cathodic Protection Work | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Place LOA/FOA - Cathodic Protection Work | Installation of Test Post for Crossing | HS-GN-0530 | C-56-HC01-PL-CA-5220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Receive at Site - Cathodic Protection (CP) System | Installation of Test Post for Crossing | ML1549-D22 | C-56-HC01-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Receipt at site and inspection of CP System - Temporary Material | Installation of Test Post for Crossing | HM-PL-0410 | C-56-HC01-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.13.11 Cathodic Protection Work | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Place LOA/FOA - Cathodic Protection Work | Installation of CP Test Post | HS-GN-0530 | C-56-HC01-PL-CA-5200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Receive at Site - Cathodic Protection (CP) System | Installation of CP Test Post | ML1549-D22 | C-56-HC01-PL-CA-5200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Receipt at site and inspection of CP System - Temporary Material | Installation of CP Test Post | HM-PL-0410 | C-56-HC01-PL-CA-5200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.13.11 Cathodic Protection Work | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Place LOA/FOA - Cathodic Protection Work | Installation of Test Post for Crossing | HS-GN-0530 | C-56-HC01-PL-CA-5400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Receive at Site - Cathodic Protection (CP) System | Installation of Test Post for Crossing | ML1549-D22 | C-56-HC01-PL-CA-5400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Receipt at site and inspection of CP System - Temporary Material | Installation of Test Post for Crossing | HM-PL-0410 | C-56-HC01-PL-CA-5400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.13.11 Cathodic Protection Work | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Place LOA/FOA - Cathodic Protection Work | Installation of CP Test Post | HS-GN-0530 | C-56-HC01-PL-CA-5430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Receive at Site - Cathodic Protection (CP) System | Installation of CP Test Post | ML1549-D22 | C-56-HC01-PL-CA-5430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Receipt at site and inspection of CP System - Temporary Material | Installation of CP Test Post | HM-PL-0410 | C-56-HC01-PL-CA-5430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.2.2.2.3.1.5 Evaporation PondCCOPL56225 | Project Kick off Meeting | Evaporation Pond | ML1002 | C-56-HC01-PL-CI-7200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (56" Pipeline) | Installation of Test Post for Crossing | ML1139-A06 | C-56-01HG-PL-CA-5220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Installation of Test Post for Crossing | ML1149-A07 | C-56-01HG-PL-CA-5220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.1.2.3.12.1.21 CP Works from BVS-01 to KP 21.3CCOP56EL23.1 | NDRC Subcontract Award | Installation of Test Post for Crossing | HS-CN-0090 | C-56-01HG-PL-CA-5220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (56" Pipeline) | Installation of Test Post for Crossing | ML1139-A06 | C-56-01HG-PL-CA-5420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Installation of Test Post for Crossing | ML1149-A07 | C-56-01HG-PL-CA-5420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | NDRC Subcontract Award | Installation of Test Post for Crossing | HS-CN-0090 | C-56-01HG-PL-CA-5420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Lowering | ML1149-A07 | C-56-01HG-PL-ME-4800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (56" Pipeline) | Lowering | ML1139-A06 | C-56-01HG-PL-ME-4800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | NDRC Subcontract Award | Lowering | HS-CN-0090 | C-56-01HG-PL-ME-4800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Complete Site Grading & ROW along the Pipeline - 56" Sales Gas Pipeline | Lowering | ML1569-E02 | C-56-01HG-PL-ME-5000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Lowering | ML1149-A07 | C-56-01HG-PL-ME-5000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (56" Pipeline) | Lowering | ML1139-A06 | C-56-01HG-PL-ME-5000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | NDRC Subcontract Award | Lowering | HS-CN-0090 | C-56-01HG-PL-ME-5000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.3.12.1.27 Pipe Stringing from KP 21.3 to HGCPCCOPL56250.2 | Receipt at site and inspection of Line Pipes - Lot 6 (Coated) | Stringing (KP 21.3 to HGCP) | HM-PL-0110 | C-56-01HG-PL-ME-3000 | SS | Not Started | Not Started | 16
P2543-R01-Oct24..1.2.12.15 Automatic Welding | P2543-R01-Oct24..4.3.1.2.3.12.1.20 Automatic Welding from BVS-01 to KP 21.3CCOPL56256.1 | Automatic Welding Complete Evaluation (Internal) | Automatic Welding | HS-CN-720 | C-56-01HG-PL-ME-3600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.6.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.3.12.1.20 Automatic Welding from BVS-01 to KP 21.3CCOPL56256.1 | 1st Pipeline Bulk material MTO | Automatic Welding | HM-PL-0880 | C-56-01HG-PL-ME-3600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.6.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.3.12.1.31 Automatic Welding from KP 21.3 to HGCPCCOPL56256.2 | 1st Pipeline Bulk material MTO | Automatic Welding | HM-PL-0880 | C-56-01HG-PL-ME-3800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Receipt at site and inspection of FOC Cables (Lot 1) | FO - Cable Pulling/ Laying | HM-EL-0180 | C-56-01HG-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | FOC Splicing / Termination Subcontract Award | FO - Cable Pulling/ Laying | HS-CN-0290 | C-56-01HG-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | Receipt at site and inspection of FOC Cables (Lot 2) | FO - Cable Pulling/ Laying | HM-EL-610 | C-56-01HG-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Receipt at site and inspection of FOC Cables (Lot 1) | FO - Cable Pulling/ Laying | HM-EL-0180 | C-56-01HG-PL-TE-8400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | FOC Splicing / Termination Subcontract Award | FO - Cable Pulling/ Laying | HS-CN-0290 | C-56-01HG-PL-TE-8400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Receipt at site and inspection of FOC Cables (Lot 2) | FO - Cable Pulling/ Laying | HM-EL-610 | C-56-01HG-PL-TE-8400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Complete Pipeline welding - 56" Sales Gas Pipeline (100% Welding) | Cleaning & Gauging | ML1599-E05 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-56-PR-838-CI-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-56-PR-838-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Site Survey, Preparation & Grading Works | CTF-1000 | C-56-PR-838-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-56-PR-838-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | NOC's / Approval /Survey | Site Survey, Preparation & Grading Works | CTF-1010 | C-56-PR-838-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Equipment Foundations | HE-CS-0230 | C-56-PR-838-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Final Civil Bulk material MTO | Concrete Works for Equipment Foundations | HM-CS-0050 | C-56-PR-838-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Concrete Works for Equipment Foundations | HE-CS-1190 | C-56-PR-838-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Final Issue for Design/ Construction-Typical Detailed Drawing - Jib Crane Foundation | Concrete Works for Equipment Foundations | HE-CS-1070 | C-56-PR-838-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Concrete Works for Equipment Foundations | HE-CS-0650 | C-56-PR-838-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Concrete Works for Equipment Foundations | HE-CS-1310 | C-56-PR-838-CI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | 1st Civil Bulk material MTO | Concrete Works for Equipment Foundations | HM-CS-0040 | C-56-PR-838-CI-1400 | SS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Field Instrument, JBs & Light Pole Foundations | HE-CS-0230 | C-56-PR-838-CI-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Final Civil Bulk material MTO | Concrete Works for Field Instrument, JBs & Light Pole Foundations | HM-CS-0050 | C-56-PR-838-CI-1410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Concrete Works for Field Instrument, JBs & Light Pole Foundations | HE-CS-0650 | C-56-PR-838-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | 1st Civil Bulk material MTO | Concrete Works for Field Instrument, JBs & Light Pole Foundations | HM-CS-0040 | C-56-PR-838-CI-1410 | SS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Access Platforms & Misc. Structural Foundations | HE-CS-0230 | C-56-PR-838-CI-1420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Final Civil Bulk material MTO | Concrete Works for Access Platforms & Misc. Structural Foundations | HM-CS-0050 | C-56-PR-838-CI-1420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Concrete Works for Access Platforms & Misc. Structural Foundations | HE-CS-0650 | C-56-PR-838-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | 1st Civil Bulk material MTO | Concrete Works for Access Platforms & Misc. Structural Foundations | HM-CS-0040 | C-56-PR-838-CI-1420 | SS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.1.12 Thrust Anchor Block/ Impact WallCCOH56CS33 | Receipt at site and inspection of Anchor Flanges (Lot 1) | Concrete Works for Thrust Anchor Block | HM-PL-940 | C-56-PR-838-CI-1510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.6 Anchor Block Detailed Drawings | P2543-R01-Oct24..4.3.1.2.21.12.1.12 Thrust Anchor Block/ Impact WallCCOH56CS33 | Final Issue for Design/ Construction - Anchor Block Detail Drawings | Concrete Works for Thrust Anchor Block | HE-CS-1800 | C-56-PR-838-CI-1510 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.1.13 Concrete Works (Foundations for Pipe Supports) CCOH56CS34 | Final Civil Bulk material MTO | Concrete Works for Pipe Support Foundations | HM-CS-0050 | C-56-PR-838-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.2.21.12.1.14 Trenching for Cables CCOH56CS35 | Final Issue for Design/ Construction-Civil UG layout | Electrical & Earthing Cable Trenching | HE-CS-0530 | C-56-PR-838-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.1.16 Paving Works CCOH56CS37 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-56-PR-838-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.2.21.12.1.16 Paving Works CCOH56CS37 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-56-PR-838-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.2.21.12.1.17 Pipe Supports Fabrication & Installation CCOH56SS50 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Pipe Supports | HS-CN-0690 | C-56-PR-838-CI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.3.1.2.21.12.1.17 Pipe Supports Fabrication & Installation CCOH56SS50 | Final Issue for Design/ Construction-Misc. supports | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1490 | C-56-PR-838-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.1.17 Pipe Supports Fabrication & Installation CCOH56SS50 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0110 | C-56-PR-838-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.3.1.2.21.12.1.17 Pipe Supports Fabrication & Installation CCOH56SS50 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1430 | C-56-PR-838-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.1.17 Pipe Supports Fabrication & Installation CCOH56SS50 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0120 | C-56-PR-838-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.2.21.12.1.18 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOH56SS51 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Platforms & Crossovers | HS-CN-0690 | C-56-PR-838-CI-3000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.1.18 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOH56SS51 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0110 | C-56-PR-838-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.2.21.12.3.19 Installation of Pig Receiver (838-V-601) CCOH56ME50 | Receive at Site - Pig Launcher & Receiver | Installation of Pig Receiver (838-V-601) 56" | ML1519-D04 | C-56-PR-838-ME-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.3.19 Installation of Pig Receiver (838-V-601) CCOH56ME50 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Installation of Pig Receiver (838-V-601) 56" | ML1015-B08 | C-56-PR-838-ME-1100 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.3.19 Installation of Pig Receiver (838-V-601) CCOH56ME50 | Receipt at site and inspection of Pig Launchers & Receivers (56" Line) | Installation of Pig Receiver (838-V-601) 56" | HM-ME-2390 | C-56-PR-838-ME-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.3.20 Installation of Pig Signaler (838-V-601) CCOH56ME60 | Receipt at site and inspection of Pigging & Split Tee (Lot 1) | Installation of Pig Signaler (838-V-601) | HM-PL-0840 | C-56-PR-838-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.3.20 Installation of Pig Signaler (838-V-601) CCOH56ME60 | Receipt at site and inspection of Pig Signaler (Lot 1) | Installation of Pig Signaler (838-V-601) | HM-PL-0530 | C-56-PR-838-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.3.20 Installation of Pig Signaler (838-V-601) CCOH56ME60 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Installation of Pig Signaler (838-V-601) | ML1015-B08 | C-56-PR-838-ME-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.3.20 Installation of Pig Signaler (838-V-601) CCOH56ME60 | Receipt at site and inspection of Pig Signaler (Lot 2) | Installation of Pig Signaler (838-V-601) | HM-PL-1490 | C-56-PR-838-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.3.20 Installation of Pig Signaler (838-V-601) CCOH56ME60 | Receipt at site and inspection of Pigging & Split Tee (Lot 2) | Installation of Pig Signaler (838-V-601) | HM-PL-1530 | C-56-PR-838-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.2.21.12.3.21 Installation/ Welding of Isolation Joints, Barred Tee & Anchor Flanges CCOH56ME70 | Receive at Site - Isolation Joints, Barred Tee, and Anchor Flanges | Installation/ Welding of Isolation Joints, Barred Tee & Anchor FlangesCCOH56ME70 (Deleted) | ML1409-D24 | C-56-PR-838-ME-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.3.21 Installation/ Welding of Isolation Joints, Barred Tee & Anchor Flanges CCOH56ME70 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Installation/ Welding of Isolation Joints, Barred Tee & Anchor FlangesCCOH56ME70 (Deleted) | ML1015-B08 | C-56-PR-838-ME-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.2.21.12.4.22 Piping Pre-Fabrication CCOH56PI101 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-56-PR-838-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.2.21.12.4.22 Piping Pre-Fabrication CCOH56PI101 | Fabrication Facilities | Piping Pre-Fabrication | CTF-SO1050 | C-56-PR-838-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.2.21.12.4.22 Piping Pre-Fabrication CCOH56PI101 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Pre-Fabrication | HE-PR-0890 | C-56-PR-838-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.2.21.12.4.22 Piping Pre-Fabrication CCOH56PI101 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Pre-Fabrication | HE-PR-0290 | C-56-PR-838-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.4.22 Piping Pre-Fabrication CCOH56PI101 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-56-PR-838-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.2.21.12.4.22 Piping Pre-Fabrication CCOH56PI101 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-56-PR-838-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.2.21.12.4.22 Piping Pre-Fabrication CCOH56PI101 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-56-PR-838-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.4.22 Piping Pre-Fabrication CCOH56PI101 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Piping Pre-Fabrication | ML1014-B10 | C-56-PR-838-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.2.21.12.4.22 Piping Pre-Fabrication CCOH56PI101 | NDT / PWHT Subcontract Award | Piping Pre-Fabrication | HS-CN-0190 | C-56-PR-838-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.4.22 Piping Pre-Fabrication CCOH56PI101 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-56-PR-838-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | Project Kick off Meeting | Piping Erection | ML1002 | C-56-PR-838-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Erection | HM-PL-0740 | C-56-PR-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Erection | HM-PL-0640 | C-56-PR-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Erection | HE-PR-0890 | C-56-PR-838-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Erection | HM-PL-0220 | C-56-PR-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Erection | HE-PR-0290 | C-56-PR-838-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Erection | ML1219-B19 | C-56-PR-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | Piping MTO - Final | Piping Erection | HE-PI-1300 | C-56-PR-838-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | Final Issue for Design/ Construction-Piping Isometrics | Piping Erection | HE-PI-1240 | C-56-PR-838-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Erection | HM-PL-0630 | C-56-PR-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Piping Erection | ML1014-B10 | C-56-PR-838-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | NDT / PWHT Subcontract Award | Piping Erection | HS-CN-0190 | C-56-PR-838-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | 1st Piping Bulk material MTO | Piping Erection | HM-PI-0040 | C-56-PR-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Erection | HM-PL-1510 | C-56-PR-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.23 Erection CCOH56PI111 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Erection | HM-PL-1570 | C-56-PR-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.2.21.12.4.24 Field Joint Welding, NDT & Coating CCOH56PI121 | Piping MTO - Final | Field Joint Welding | HE-PI-1300 | C-56-PR-838-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.2.21.12.4.24 Field Joint Welding, NDT & Coating CCOH56PI121 | Project Kick off Meeting | Field Joint Welding | ML1002 | C-56-PR-838-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.4.24 Field Joint Welding, NDT & Coating CCOH56PI121 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Field Joint Welding | ML1219-B19 | C-56-PR-838-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.4.24 Field Joint Welding, NDT & Coating CCOH56PI121 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Field Joint Welding | ML1014-B10 | C-56-PR-838-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.2.21.12.4.24 Field Joint Welding, NDT & Coating CCOH56PI121 | NDT / PWHT Subcontract Award | Field Joint Welding | HS-CN-0190 | C-56-PR-838-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.4.25 Hydrotesting CCOH56PI131 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Hydrotesting | ML1219-B19 | C-56-PR-838-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.4.25 Hydrotesting CCOH56PI131 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Hydrotesting | ML1014-B10 | C-56-PR-838-PI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.26 Installation of Valves CCOH56PI141 | Receipt at site and inspection of Isolating Joints (Lot 1) | Installation of Valves/MOV/ROV | HM-PL-0740 | C-56-PR-838-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.26 Installation of Valves CCOH56PI141 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Installation of Valves/MOV/ROV | HM-PL-0640 | C-56-PR-838-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.2.21.12.4.26 Installation of Valves CCOH56PI141 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Installation of Valves/MOV/ROV | HE-PR-0890 | C-56-PR-838-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.26 Installation of Valves CCOH56PI141 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Installation of Valves/MOV/ROV | HM-PL-0220 | C-56-PR-838-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.2.21.12.4.26 Installation of Valves CCOH56PI141 | Final Issue for Design/ Construction-Tie-In Schedule | Installation of Valves/MOV/ROV | HE-PR-0290 | C-56-PR-838-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.4.26 Installation of Valves CCOH56PI141 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Installation of Valves/MOV/ROV | ML1219-B19 | C-56-PR-838-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.2.21.12.4.26 Installation of Valves CCOH56PI141 | Final Issue for Design/ Construction-Piping Isometrics | Installation of Valves/MOV/ROV | HE-PI-1240 | C-56-PR-838-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.26 Installation of Valves CCOH56PI141 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Installation of Valves/MOV/ROV | HM-PL-0630 | C-56-PR-838-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.4.26 Installation of Valves CCOH56PI141 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Installation of Valves/MOV/ROV | ML1014-B10 | C-56-PR-838-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.26 Installation of Valves CCOH56PI141 | Receipt at site and inspection of Isolating Joints (Lot 2) | Installation of Valves/MOV/ROV | HM-PL-1510 | C-56-PR-838-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.26 Installation of Valves CCOH56PI141 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Installation of Valves/MOV/ROV | HM-PL-1570 | C-56-PR-838-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | Piping MTO - Final | Final Bolt Torquing/ Re-Instatement | HE-PI-1300 | C-56-PR-838-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | Project Kick off Meeting | Final Bolt Torquing/ Re-Instatement | ML1002 | C-56-PR-838-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | Receipt at site and inspection of Isolating Joints (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0740 | C-56-PR-838-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0640 | C-56-PR-838-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Final Bolt Torquing/ Re-Instatement | HE-PR-0890 | C-56-PR-838-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0220 | C-56-PR-838-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | Final Issue for Design/ Construction-Tie-In Schedule | Final Bolt Torquing/ Re-Instatement | HE-PR-0290 | C-56-PR-838-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Final Bolt Torquing/ Re-Instatement | ML1219-B19 | C-56-PR-838-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | Final Issue for Design/ Construction-Piping Isometrics | Final Bolt Torquing/ Re-Instatement | HE-PI-1240 | C-56-PR-838-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0630 | C-56-PR-838-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Final Bolt Torquing/ Re-Instatement | ML1014-B10 | C-56-PR-838-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | NDT / PWHT Subcontract Award | Final Bolt Torquing/ Re-Instatement | HS-CN-0190 | C-56-PR-838-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | Receipt at site and inspection of Isolating Joints (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1510 | C-56-PR-838-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.27 Final Bolt Torquing/ Re-Instatement CCOH56PI151 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1570 | C-56-PR-838-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of CP Test Post | HM-EL-0080 | C-56-PR-838-EI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of CP Test Post | HE-EL-1790 | C-56-PR-838-EI-1010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Obtain Company Approval-Data sheet for LV Distribution board | Installation of CP Test Post | HE-EL-0640 | C-56-PR-838-EI-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of CP Test Post | HE-IC-0650 | C-56-PR-838-EI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of CP Test Post | HE-IC-0710 | C-56-PR-838-EI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Installation of CP Test Post | ML1032-B21 | C-56-PR-838-EI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Installation of CP Test Post | HE-IC-2570 | C-56-PR-838-EI-1010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Installation of CP Test Post | HE-IC-1430 | C-56-PR-838-EI-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Installation of CP Test Post | HE-EL-1010 | C-56-PR-838-EI-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of CP Test Post | HM-EL-0380 | C-56-PR-838-EI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | 1st Electrical Bulk material MTO | Installation of CP Test Post | HM-EL-0520 | C-56-PR-838-EI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of CP Test Post | HE-IC-1550 | C-56-PR-838-EI-1010 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Earthing Layout | Installation of CP Test Post | HE-EL-1670 | C-56-PR-838-EI-1010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of CP Test Post | HE-EL-0530 | C-56-PR-838-EI-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue ICR- Addendum to DGs | Installation of CP Test Post | HE-IC-0010 | C-56-PR-838-EI-1010 | SS | Completed | Not Started | 10
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-F&G Cause and effect | Installation of CP Test Post | HE-HS-0350 | C-56-PR-838-EI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | 1st Instrumentation Bulk material MTO | Installation of CP Test Post | HM-IC-0040 | C-56-PR-838-EI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Installation of CP Test Post | HM-ME-1690 | C-56-PR-838-EI-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue ICR-Instrument index -Update | Installation of CP Test Post | HE-IC-0490 | C-56-PR-838-EI-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Loop Diagrams | Installation of CP Test Post | HE-IC-0770 | C-56-PR-838-EI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of CP Test Post | HM-EL-0280 | C-56-PR-838-EI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Instrument Index | Installation of CP Test Post | HE-IC-0530 | C-56-PR-838-EI-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Lighting Layout | Installation of CP Test Post | HE-EL-1730 | C-56-PR-838-EI-1010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-I/O list | Installation of CP Test Post | HE-IC-0590 | C-56-PR-838-EI-1010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue ICR- P&ID's | Installation of CP Test Post | HE-PR-0110 | C-56-PR-838-EI-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Installation of CP Test Post | HM-ME-2350 | C-56-PR-838-EI-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of CP Test Post | HM-EL-630 | C-56-PR-838-EI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of CP Test Post | HM-EL-650 | C-56-PR-838-EI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of CP Test Post | HM-EL-690 | C-56-PR-838-EI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Deep Earth Well Drilling | HM-EL-0080 | C-56-PR-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Electrical Installation Drawings | Deep Earth Well Drilling | HE-EL-1790 | C-56-PR-838-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Obtain Company Approval-Data sheet for LV Distribution board | Deep Earth Well Drilling | HE-EL-0640 | C-56-PR-838-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Hook-Up Diagram | Deep Earth Well Drilling | HE-IC-0650 | C-56-PR-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1590 | C-56-PR-838-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Typical Installation Drawings | Deep Earth Well Drilling | HE-IC-0710 | C-56-PR-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Deep Earth Well Drilling | ML1032-B21 | C-56-PR-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Deep Earth Well Drilling | HE-IC-2570 | C-56-PR-838-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Deep Earth Well Drilling | HE-IC-1430 | C-56-PR-838-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Deep Earth Well Drilling | HE-EL-1010 | C-56-PR-838-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Earthing Material (Lot 1) | Deep Earth Well Drilling | HM-EL-0380 | C-56-PR-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | 1st Electrical Bulk material MTO | Deep Earth Well Drilling | HM-EL-0520 | C-56-PR-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Deep Earth Well Drilling | HE-IC-1550 | C-56-PR-838-EI-1400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Earthing Layout | Deep Earth Well Drilling | HE-EL-1670 | C-56-PR-838-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Electrical Equipment Layout | Deep Earth Well Drilling | HE-EL-0530 | C-56-PR-838-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue ICR- Addendum to DGs | Deep Earth Well Drilling | HE-IC-0010 | C-56-PR-838-EI-1400 | SS | Completed | Not Started | 10
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-F&G Cause and effect | Deep Earth Well Drilling | HE-HS-0350 | C-56-PR-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | 1st Instrumentation Bulk material MTO | Deep Earth Well Drilling | HM-IC-0040 | C-56-PR-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1690 | C-56-PR-838-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue ICR-Instrument index -Update | Deep Earth Well Drilling | HE-IC-0490 | C-56-PR-838-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Loop Diagrams | Deep Earth Well Drilling | HE-IC-0770 | C-56-PR-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-0280 | C-56-PR-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Instrument Index | Deep Earth Well Drilling | HE-IC-0530 | C-56-PR-838-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Lighting Layout | Deep Earth Well Drilling | HE-EL-1730 | C-56-PR-838-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-I/O list | Deep Earth Well Drilling | HE-IC-0590 | C-56-PR-838-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue ICR- P&ID's | Deep Earth Well Drilling | HE-PR-0110 | C-56-PR-838-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Deep Earth Well Drilling | HM-ME-2330 | C-56-PR-838-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Deep Earth Well Drilling | HM-ME-2350 | C-56-PR-838-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Deep Earth Well Drilling | HM-EL-630 | C-56-PR-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-650 | C-56-PR-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Earthing Material (Lot 2) | Deep Earth Well Drilling | HM-EL-690 | C-56-PR-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of JB's | HM-EL-0080 | C-56-PR-838-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of JB's | HE-EL-1790 | C-56-PR-838-EI-1810 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Obtain Company Approval-Data sheet for LV Distribution board | Installation of JB's | HE-EL-0640 | C-56-PR-838-EI-1810 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of JB's | HE-IC-0650 | C-56-PR-838-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of JB's | HE-IC-0710 | C-56-PR-838-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Installation of JB's | ML1032-B21 | C-56-PR-838-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Installation of JB's | HE-IC-2570 | C-56-PR-838-EI-1810 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Installation of JB's | HE-IC-1430 | C-56-PR-838-EI-1810 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Installation of JB's | HE-EL-1010 | C-56-PR-838-EI-1810 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of JB's | HM-EL-0380 | C-56-PR-838-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | 1st Electrical Bulk material MTO | Installation of JB's | HM-EL-0520 | C-56-PR-838-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of JB's | HE-IC-1550 | C-56-PR-838-EI-1810 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Earthing Layout | Installation of JB's | HE-EL-1670 | C-56-PR-838-EI-1810 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of JB's | HE-EL-0530 | C-56-PR-838-EI-1810 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue ICR- Addendum to DGs | Installation of JB's | HE-IC-0010 | C-56-PR-838-EI-1810 | SS | Completed | Not Started | 10
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-F&G Cause and effect | Installation of JB's | HE-HS-0350 | C-56-PR-838-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | 1st Instrumentation Bulk material MTO | Installation of JB's | HM-IC-0040 | C-56-PR-838-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Installation of JB's | HM-ME-1690 | C-56-PR-838-EI-1810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue ICR-Instrument index -Update | Installation of JB's | HE-IC-0490 | C-56-PR-838-EI-1810 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Loop Diagrams | Installation of JB's | HE-IC-0770 | C-56-PR-838-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of JB's | HM-EL-0280 | C-56-PR-838-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Instrument Index | Installation of JB's | HE-IC-0530 | C-56-PR-838-EI-1810 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Lighting Layout | Installation of JB's | HE-EL-1730 | C-56-PR-838-EI-1810 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-I/O list | Installation of JB's | HE-IC-0590 | C-56-PR-838-EI-1810 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue ICR- P&ID's | Installation of JB's | HE-PR-0110 | C-56-PR-838-EI-1810 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Installation of JB's | HM-ME-2350 | C-56-PR-838-EI-1810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of JB's | HM-EL-630 | C-56-PR-838-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of JB's | HM-EL-650 | C-56-PR-838-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of JB's | HM-EL-690 | C-56-PR-838-EI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of Cable Trays | HM-EL-0080 | C-56-PR-838-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of Cable Trays | HE-EL-1790 | C-56-PR-838-EI-2020 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Obtain Company Approval-Data sheet for LV Distribution board | Installation of Cable Trays | HE-EL-0640 | C-56-PR-838-EI-2020 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of Cable Trays | HE-IC-0650 | C-56-PR-838-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of Cable Trays | HE-IC-0710 | C-56-PR-838-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Installation of Cable Trays | ML1032-B21 | C-56-PR-838-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Installation of Cable Trays | HE-IC-2570 | C-56-PR-838-EI-2020 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Installation of Cable Trays | HE-IC-1430 | C-56-PR-838-EI-2020 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Installation of Cable Trays | HE-EL-1010 | C-56-PR-838-EI-2020 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of Cable Trays | HM-EL-0380 | C-56-PR-838-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | 1st Electrical Bulk material MTO | Installation of Cable Trays | HM-EL-0520 | C-56-PR-838-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of Cable Trays | HE-IC-1550 | C-56-PR-838-EI-2020 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Earthing Layout | Installation of Cable Trays | HE-EL-1670 | C-56-PR-838-EI-2020 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of Cable Trays | HE-EL-0530 | C-56-PR-838-EI-2020 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue ICR- Addendum to DGs | Installation of Cable Trays | HE-IC-0010 | C-56-PR-838-EI-2020 | SS | Completed | Not Started | 10
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-F&G Cause and effect | Installation of Cable Trays | HE-HS-0350 | C-56-PR-838-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | 1st Instrumentation Bulk material MTO | Installation of Cable Trays | HM-IC-0040 | C-56-PR-838-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue ICR-Instrument index -Update | Installation of Cable Trays | HE-IC-0490 | C-56-PR-838-EI-2020 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Loop Diagrams | Installation of Cable Trays | HE-IC-0770 | C-56-PR-838-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Cable Trays | HM-EL-0280 | C-56-PR-838-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Instrument Index | Installation of Cable Trays | HE-IC-0530 | C-56-PR-838-EI-2020 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Lighting Layout | Installation of Cable Trays | HE-EL-1730 | C-56-PR-838-EI-2020 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-I/O list | Installation of Cable Trays | HE-IC-0590 | C-56-PR-838-EI-2020 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue ICR- P&ID's | Installation of Cable Trays | HE-PR-0110 | C-56-PR-838-EI-2020 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of Cable Trays | HM-EL-630 | C-56-PR-838-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Cable Trays | HM-EL-650 | C-56-PR-838-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of Cable Trays | HM-EL-690 | C-56-PR-838-EI-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Instrument Tubing Works | HM-EL-0080 | C-56-PR-838-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Electrical Installation Drawings | Instrument Tubing Works | HE-EL-1790 | C-56-PR-838-EI-2030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Obtain Company Approval-Data sheet for LV Distribution board | Instrument Tubing Works | HE-EL-0640 | C-56-PR-838-EI-2030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Hook-Up Diagram | Instrument Tubing Works | HE-IC-0650 | C-56-PR-838-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Typical Installation Drawings | Instrument Tubing Works | HE-IC-0710 | C-56-PR-838-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Instrument Tubing Works | ML1032-B21 | C-56-PR-838-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Instrument Tubing Works | HE-IC-2570 | C-56-PR-838-EI-2030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Instrument Tubing Works | HE-IC-1430 | C-56-PR-838-EI-2030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Instrument Tubing Works | HE-EL-1010 | C-56-PR-838-EI-2030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Earthing Material (Lot 1) | Instrument Tubing Works | HM-EL-0380 | C-56-PR-838-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | 1st Electrical Bulk material MTO | Instrument Tubing Works | HM-EL-0520 | C-56-PR-838-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Instrument Tubing Works | HE-IC-1550 | C-56-PR-838-EI-2030 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Earthing Layout | Instrument Tubing Works | HE-EL-1670 | C-56-PR-838-EI-2030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Electrical Equipment Layout | Instrument Tubing Works | HE-EL-0530 | C-56-PR-838-EI-2030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue ICR- Addendum to DGs | Instrument Tubing Works | HE-IC-0010 | C-56-PR-838-EI-2030 | SS | Completed | Not Started | 10
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-F&G Cause and effect | Instrument Tubing Works | HE-HS-0350 | C-56-PR-838-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | 1st Instrumentation Bulk material MTO | Instrument Tubing Works | HM-IC-0040 | C-56-PR-838-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue ICR-Instrument index -Update | Instrument Tubing Works | HE-IC-0490 | C-56-PR-838-EI-2030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Loop Diagrams | Instrument Tubing Works | HE-IC-0770 | C-56-PR-838-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Cable Trays (Lot 2) | Instrument Tubing Works | HM-EL-0280 | C-56-PR-838-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Instrument Index | Instrument Tubing Works | HE-IC-0530 | C-56-PR-838-EI-2030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-Lighting Layout | Instrument Tubing Works | HE-EL-1730 | C-56-PR-838-EI-2030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Final Issue for Design/ Construction-I/O list | Instrument Tubing Works | HE-IC-0590 | C-56-PR-838-EI-2030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Issue ICR- P&ID's | Instrument Tubing Works | HE-PR-0110 | C-56-PR-838-EI-2030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Instrument Tubing Works | HM-EL-630 | C-56-PR-838-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Cable Trays (Lot 2) | Instrument Tubing Works | HM-EL-650 | C-56-PR-838-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Receipt at site and inspection of Earthing Material (Lot 2) | Instrument Tubing Works | HM-EL-690 | C-56-PR-838-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.13 E&I Works | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | E&I Works Subcontract Award | CP Cable Laying | HS-CN-0640 | C-56-PR-838-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Data Sheet for LV cables | CP Cable Laying | HE-EL-0830 | C-56-PR-838-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | CP Cable Laying | HE-IC-0950 | C-56-PR-838-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | CP Cable Laying | HE-IC-0830 | C-56-PR-838-CA-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Receipt at site and inspection of Power & Control Cables (Lot 1) | CP Cable Laying | HM-EL-0080 | C-56-PR-838-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Cable Schedule | CP Cable Laying | HE-EL-0590 | C-56-PR-838-CA-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Cable Routing Layout | CP Cable Laying | HE-EL-1610 | C-56-PR-838-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Instrument Trench Layout | CP Cable Laying | HE-IC-1010 | C-56-PR-838-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Cable Sizing Calculation | CP Cable Laying | HE-EL-0470 | C-56-PR-838-CA-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | 1st Electrical Bulk material MTO | CP Cable Laying | HM-EL-0520 | C-56-PR-838-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Data Sheet for HV cables | CP Cable Laying | HE-EL-1950 | C-56-PR-838-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Specification for RTU | CP Cable Laying | HE-IC-0230 | C-56-PR-838-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Specification for Leak Detection System | CP Cable Laying | HE-IC-0290 | C-56-PR-838-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-I/O list | CP Cable Laying | HE-IC-0590 | C-56-PR-838-CA-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Re-Issue for Approval- I/O list -Update | CP Cable Laying | HE-IC-0570 | C-56-PR-838-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Re-Issue for Approval- Specification for RTU | CP Cable Laying | HE-IC-0210 | C-56-PR-838-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Re-Issue for Approval- Specification for Leak Detection System | CP Cable Laying | HE-IC-0270 | C-56-PR-838-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Issue ICR- Instrument Cable Block Diagram | CP Cable Laying | HE-IC-0790 | C-56-PR-838-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Issue ICR- Specification for Leak Detection System | CP Cable Laying | HE-IC-0250 | C-56-PR-838-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Issue ICR- Specification for RTU | CP Cable Laying | HE-IC-0190 | C-56-PR-838-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Receipt at site and inspection of Power & Control Cables (Lot 2) | CP Cable Laying | HM-EL-630 | C-56-PR-838-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.13 E&I Works | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | E&I Works Subcontract Award | Glanding & Termination for CP S/m | HS-CN-0640 | C-56-PR-838-CA-1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Data Sheet for LV cables | Glanding & Termination for CP S/m | HE-EL-0830 | C-56-PR-838-CA-1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Glanding & Termination for CP S/m | HE-IC-0950 | C-56-PR-838-CA-1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Glanding & Termination for CP S/m | HE-IC-0830 | C-56-PR-838-CA-1030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Glanding & Termination for CP S/m | HM-EL-0080 | C-56-PR-838-CA-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Cable Schedule | Glanding & Termination for CP S/m | HE-EL-0590 | C-56-PR-838-CA-1030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Cable Routing Layout | Glanding & Termination for CP S/m | HE-EL-1610 | C-56-PR-838-CA-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Instrument Trench Layout | Glanding & Termination for CP S/m | HE-IC-1010 | C-56-PR-838-CA-1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Cable Sizing Calculation | Glanding & Termination for CP S/m | HE-EL-0470 | C-56-PR-838-CA-1030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | 1st Electrical Bulk material MTO | Glanding & Termination for CP S/m | HM-EL-0520 | C-56-PR-838-CA-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Data Sheet for HV cables | Glanding & Termination for CP S/m | HE-EL-1950 | C-56-PR-838-CA-1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Specification for RTU | Glanding & Termination for CP S/m | HE-IC-0230 | C-56-PR-838-CA-1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Specification for Leak Detection System | Glanding & Termination for CP S/m | HE-IC-0290 | C-56-PR-838-CA-1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-I/O list | Glanding & Termination for CP S/m | HE-IC-0590 | C-56-PR-838-CA-1030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Re-Issue for Approval- I/O list -Update | Glanding & Termination for CP S/m | HE-IC-0570 | C-56-PR-838-CA-1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Re-Issue for Approval- Specification for RTU | Glanding & Termination for CP S/m | HE-IC-0210 | C-56-PR-838-CA-1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Re-Issue for Approval- Specification for Leak Detection System | Glanding & Termination for CP S/m | HE-IC-0270 | C-56-PR-838-CA-1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Issue ICR- Instrument Cable Block Diagram | Glanding & Termination for CP S/m | HE-IC-0790 | C-56-PR-838-CA-1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Issue ICR- Specification for Leak Detection System | Glanding & Termination for CP S/m | HE-IC-0250 | C-56-PR-838-CA-1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Issue ICR- Specification for RTU | Glanding & Termination for CP S/m | HE-IC-0190 | C-56-PR-838-CA-1030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Glanding & Termination for CP S/m | HM-EL-630 | C-56-PR-838-CA-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.13 E&I Works | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | E&I Works Subcontract Award | Electrical & Earthing Cable Laying | HS-CN-0640 | C-56-PR-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Data Sheet for LV cables | Electrical & Earthing Cable Laying | HE-EL-0830 | C-56-PR-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Electrical & Earthing Cable Laying | HE-IC-0950 | C-56-PR-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0830 | C-56-PR-838-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Electrical & Earthing Cable Laying | HM-EL-0080 | C-56-PR-838-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Cable Schedule | Electrical & Earthing Cable Laying | HE-EL-0590 | C-56-PR-838-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Cable Routing Layout | Electrical & Earthing Cable Laying | HE-EL-1610 | C-56-PR-838-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Instrument Trench Layout | Electrical & Earthing Cable Laying | HE-IC-1010 | C-56-PR-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Cable Sizing Calculation | Electrical & Earthing Cable Laying | HE-EL-0470 | C-56-PR-838-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | 1st Electrical Bulk material MTO | Electrical & Earthing Cable Laying | HM-EL-0520 | C-56-PR-838-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Data Sheet for HV cables | Electrical & Earthing Cable Laying | HE-EL-1950 | C-56-PR-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0230 | C-56-PR-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0290 | C-56-PR-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-I/O list | Electrical & Earthing Cable Laying | HE-IC-0590 | C-56-PR-838-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Re-Issue for Approval- I/O list -Update | Electrical & Earthing Cable Laying | HE-IC-0570 | C-56-PR-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Re-Issue for Approval- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0210 | C-56-PR-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Re-Issue for Approval- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0270 | C-56-PR-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Issue ICR- Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0790 | C-56-PR-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Issue ICR- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0250 | C-56-PR-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Issue ICR- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0190 | C-56-PR-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-630 | C-56-PR-838-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.13 E&I Works | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | E&I Works Subcontract Award | Instrument Cable Laying | HS-CN-0640 | C-56-PR-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Data Sheet for LV cables | Instrument Cable Laying | HE-EL-0830 | C-56-PR-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Instrument Cable Laying | HE-IC-0950 | C-56-PR-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Instrument Cable Laying | HE-IC-0830 | C-56-PR-838-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Instrument Cable Laying | HM-EL-0080 | C-56-PR-838-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Cable Schedule | Instrument Cable Laying | HE-EL-0590 | C-56-PR-838-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Cable Routing Layout | Instrument Cable Laying | HE-EL-1610 | C-56-PR-838-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Instrument Trench Layout | Instrument Cable Laying | HE-IC-1010 | C-56-PR-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Cable Sizing Calculation | Instrument Cable Laying | HE-EL-0470 | C-56-PR-838-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | 1st Electrical Bulk material MTO | Instrument Cable Laying | HM-EL-0520 | C-56-PR-838-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Data Sheet for HV cables | Instrument Cable Laying | HE-EL-1950 | C-56-PR-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Specification for RTU | Instrument Cable Laying | HE-IC-0230 | C-56-PR-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Specification for Leak Detection System | Instrument Cable Laying | HE-IC-0290 | C-56-PR-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-I/O list | Instrument Cable Laying | HE-IC-0590 | C-56-PR-838-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Re-Issue for Approval- I/O list -Update | Instrument Cable Laying | HE-IC-0570 | C-56-PR-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Re-Issue for Approval- Specification for RTU | Instrument Cable Laying | HE-IC-0210 | C-56-PR-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Re-Issue for Approval- Specification for Leak Detection System | Instrument Cable Laying | HE-IC-0270 | C-56-PR-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Issue ICR- Instrument Cable Block Diagram | Instrument Cable Laying | HE-IC-0790 | C-56-PR-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Issue ICR- Specification for Leak Detection System | Instrument Cable Laying | HE-IC-0250 | C-56-PR-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Issue ICR- Specification for RTU | Instrument Cable Laying | HE-IC-0190 | C-56-PR-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Instrument Cable Laying | HM-EL-630 | C-56-PR-838-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.13 E&I Works | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | E&I Works Subcontract Award | Loop Checking for Instruments | HS-CN-0640 | C-56-PR-838-EI-2040 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Data Sheet for LV cables | Loop Checking for Instruments | HE-EL-0830 | C-56-PR-838-EI-2040 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Loop Checking for Instruments | HE-IC-0950 | C-56-PR-838-EI-2040 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Loop Checking for Instruments | HE-IC-0830 | C-56-PR-838-EI-2040 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Loop Checking for Instruments | HM-EL-0080 | C-56-PR-838-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Cable Schedule | Loop Checking for Instruments | HE-EL-0590 | C-56-PR-838-EI-2040 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Cable Routing Layout | Loop Checking for Instruments | HE-EL-1610 | C-56-PR-838-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Instrument Trench Layout | Loop Checking for Instruments | HE-IC-1010 | C-56-PR-838-EI-2040 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Cable Sizing Calculation | Loop Checking for Instruments | HE-EL-0470 | C-56-PR-838-EI-2040 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | 1st Electrical Bulk material MTO | Loop Checking for Instruments | HM-EL-0520 | C-56-PR-838-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Data Sheet for HV cables | Loop Checking for Instruments | HE-EL-1950 | C-56-PR-838-EI-2040 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Specification for RTU | Loop Checking for Instruments | HE-IC-0230 | C-56-PR-838-EI-2040 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-Specification for Leak Detection System | Loop Checking for Instruments | HE-IC-0290 | C-56-PR-838-EI-2040 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Final Issue for Design/ Construction-I/O list | Loop Checking for Instruments | HE-IC-0590 | C-56-PR-838-EI-2040 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Re-Issue for Approval- I/O list -Update | Loop Checking for Instruments | HE-IC-0570 | C-56-PR-838-EI-2040 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Re-Issue for Approval- Specification for RTU | Loop Checking for Instruments | HE-IC-0210 | C-56-PR-838-EI-2040 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Re-Issue for Approval- Specification for Leak Detection System | Loop Checking for Instruments | HE-IC-0270 | C-56-PR-838-EI-2040 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Issue ICR- Instrument Cable Block Diagram | Loop Checking for Instruments | HE-IC-0790 | C-56-PR-838-EI-2040 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Issue ICR- Specification for Leak Detection System | Loop Checking for Instruments | HE-IC-0250 | C-56-PR-838-EI-2040 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Issue ICR- Specification for RTU | Loop Checking for Instruments | HE-IC-0190 | C-56-PR-838-EI-2040 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Loop Checking for Instruments | HM-EL-630 | C-56-PR-838-EI-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.2.21.12.8.32 SDH Cabinet CCOH56IC20 | Final Issue for Design/ Construction-Telecom Equipment Layout | SDH Cabinet (Deleted) | HE-TL-0770 | C-56-PR-838-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.2.21.12.8.32 SDH Cabinet CCOH56IC20 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | SDH Cabinet (Deleted) | HE-TL-0710 | C-56-PR-838-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.2.21.12.8.32 SDH Cabinet CCOH56IC20 | FOC Splicing / Termination Subcontract Award | SDH Cabinet (Deleted) | HS-CN-0290 | C-56-PR-838-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.21.12.8.32 SDH Cabinet CCOH56IC20 | 1st Telecom Bulk material MTO | SDH Cabinet (Deleted) | HM-TL-0040 | C-56-PR-838-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.8.32 SDH Cabinet CCOH56IC20 | Receipt at site and inspection of FOC Cables (Lot 1) | SDH Cabinet (Deleted) | HM-EL-0180 | C-56-PR-838-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.2.21.12.8.32 SDH Cabinet CCOH56IC20 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | SDH Cabinet (Deleted) | HE-TL-0470 | C-56-PR-838-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.2.21.12.8.32 SDH Cabinet CCOH56IC20 | Receive at Site - Leak Detection System | SDH Cabinet (Deleted) | ML1053-D23 | C-56-PR-838-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.21.12.8.32 SDH Cabinet CCOH56IC20 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | SDH Cabinet (Deleted) | ML1033-B22 | C-56-PR-838-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..4.3.1.2.21.12.8.32 SDH Cabinet CCOH56IC20 | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | SDH Cabinet (Deleted) | HE-IC-0110 | C-56-PR-838-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.2.21.12.8.32 SDH Cabinet CCOH56IC20 | Final Issue for Design/ Construction-Telecom cable schedule | SDH Cabinet (Deleted) | HE-TL-0830 | C-56-PR-838-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.2.21.12.8.32 SDH Cabinet CCOH56IC20 | Receive at Site - Pressure Reduction Skids | SDH Cabinet (Deleted) | ML1051-D07 | C-56-PR-838-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.8.32 SDH Cabinet CCOH56IC20 | Receipt at site and inspection of FOC Cables (Lot 2) | SDH Cabinet (Deleted) | HM-EL-610 | C-56-PR-838-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-56-591-01-CI-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-56-591-01-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Site Survey, Preparation & Grading Works | HE-CS-0470 | C-56-591-01-CI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Site Survey, Preparation & Grading Works | CTF-1000 | C-56-591-01-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-56-591-01-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | Site Survey, Preparation & Grading Works | ML1035-B26 | C-56-591-01-CI-1000 | FF | Not Started | Not Started | 32
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | NOC's / Approval /Survey | Site Survey, Preparation & Grading Works | CTF-1010 | C-56-591-01-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-1190 | C-56-591-01-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-1310 | C-56-591-01-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Final Issue for Design/ Construction-Fire fighting & Safety equipment layout | Concrete Works for Equipment Foundations & Hard Stand Area | HE-HS-0410 | C-56-591-01-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-0230 | C-56-591-01-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | Concrete Works for Equipment Foundations & Hard Stand Area | ML1035-B26 | C-56-591-01-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | 1st Civil Bulk material MTO | Concrete Works for Equipment Foundations & Hard Stand Area | HM-CS-0040 | C-56-591-01-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Final Issue for Design/ Construction-Solar panel foundation details | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-0890 | C-56-591-01-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Final Issue for Design/ Construction-Fire fighting & Safety equipment layout | Concrete Works for Field Instrument, JB Foundations | HE-HS-0410 | C-56-591-01-CI-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Field Instrument, JB Foundations | HE-CS-0230 | C-56-591-01-CI-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (56" Pipeline) - IFC | Concrete Works for Field Instrument, JB Foundations | ML1035-B26 | C-56-591-01-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | 1st Civil Bulk material MTO | Concrete Works for Field Instrument, JB Foundations | HM-CS-0040 | C-56-591-01-CI-1410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.2.1.12.1.13 Concrete Works (Foundations for Pipe Supports) CCOB156C32 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Pipe Support Foundations | HE-CS-0230 | C-56-591-01-CI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.2.1.12.1.14 Trenching for Cables CCOB156C33 | Final Issue for Design/ Construction-Civil UG layout | Electrical & Earthing Cable Trenching | HE-CS-0530 | C-56-591-01-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.1.17 Pipe Supports Fabrication & Installation CCOB156S50 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0120 | C-56-591-01-CI-2000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.2.1.12.1.17 Pipe Supports Fabrication & Installation CCOB156S50 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Pipe Supports | HS-CN-0690 | C-56-591-01-CI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.3.1.2.1.12.1.17 Pipe Supports Fabrication & Installation CCOB156S50 | Final Issue for Design/ Construction-Misc. supports | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1490 | C-56-591-01-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.3.1.2.1.12.1.17 Pipe Supports Fabrication & Installation CCOB156S50 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1430 | C-56-591-01-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.1.17 Pipe Supports Fabrication & Installation CCOB156S50 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0110 | C-56-591-01-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.2.1.12.1.12 Fences & Gates Construction CCOB156C31 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Installation of Concrete Pillers for Boundary Wall | HE-CS-0350 | C-56-591-01-CI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.2.1.12.1.12 Fences & Gates Construction CCOB156C31 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Installation of Concrete Pillers for Boundary Wall | HE-CS-0470 | C-56-591-01-CI-2200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.1.18 Fire Point Shelters CCOB156S52 | 1st Structural Bulk material MTO | Installation of Fire Point Shelters | HM-CS-0110 | C-56-591-01-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.1.15 Paving Works CCOB156C35 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-56-591-01-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.2.1.12.1.15 Paving Works CCOB156C35 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-56-591-01-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.1.19 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOB156S54 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0110 | C-56-591-01-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.2.1.12.1.19 Platforms/Crossovers/ Guardrails and Bollards/ Windsock CCOB156S54 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Platforms & Crossovers | HS-CN-0690 | C-56-591-01-CI-3000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.3.9 Mechanical Works and Equipment Installation (Fire Fighting Equipment) CCOB156M50 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 1) | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | HM-ME-1990 | C-56-591-01-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.3.9 Mechanical Works and Equipment Installation (Fire Fighting Equipment) CCOB156M50 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | ML1015-B08 | C-56-591-01-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.3.9 Mechanical Works and Equipment Installation (Fire Fighting Equipment) CCOB156M50 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 2) | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | HM-ME-2370 | C-56-591-01-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.2.1.12.4.1 Piping Pre-Fabrication CCOB156P100 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-56-591-01-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.2.1.12.4.1 Piping Pre-Fabrication CCOB156P100 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Pre-Fabrication | HE-PR-0890 | C-56-591-01-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.2.1.12.4.1 Piping Pre-Fabrication CCOB156P100 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Pre-Fabrication | HE-PR-0290 | C-56-591-01-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.4 Piping GA - Block valve Station (591-BVS-01) at KP-12.6 on 56" Pipeline | P2543-R01-Oct24..4.3.1.2.1.12.4.1 Piping Pre-Fabrication CCOB156P100 | Final Issue for Design/ Construction-Piping GA Drawings for 591-BVS-01 | Piping Pre-Fabrication | HE-PI-0820 | C-56-591-01-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.2.1.12.4.1 Piping Pre-Fabrication CCOB156P100 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-56-591-01-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.4.1 Piping Pre-Fabrication CCOB156P100 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-56-591-01-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.2.1.12.4.1 Piping Pre-Fabrication CCOB156P100 | NDT / PWHT Subcontract Award | Piping Pre-Fabrication | HS-CN-0190 | C-56-591-01-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.2.1.12.4.1 Piping Pre-Fabrication CCOB156P100 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-56-591-01-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.4.1 Piping Pre-Fabrication CCOB156P100 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Piping Pre-Fabrication | ML1014-B10 | C-56-591-01-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.4.1 Piping Pre-Fabrication CCOB156P100 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-56-591-01-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..4.3.1.2.1.12.4.1 Piping Pre-Fabrication CCOB156P100 | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | Piping Pre-Fabrication | HE-PI-0580 | C-56-591-01-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | Project Kick off Meeting | Piping Erection | ML1002 | C-56-591-01-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Erection | HM-PL-0740 | C-56-591-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Erection | HE-PR-0890 | C-56-591-01-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Erection | HE-PR-0290 | C-56-591-01-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Erection | HM-PL-0630 | C-56-591-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | Piping MTO - Final | Piping Erection | HE-PI-1300 | C-56-591-01-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | 1st Piping Bulk material MTO | Piping Erection | HM-PI-0040 | C-56-591-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | Final Piping Bulk material MTO | Piping Erection | HM-PI-0050 | C-56-591-01-PI-1200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Erection | HM-PL-0640 | C-56-591-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | NDT / PWHT Subcontract Award | Piping Erection | HS-CN-0190 | C-56-591-01-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Erection | HM-PL-0220 | C-56-591-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | Final Issue for Design/ Construction-Piping Isometrics | Piping Erection | HE-PI-1240 | C-56-591-01-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Piping Erection | ML1014-B10 | C-56-591-01-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Erection | ML1219-B19 | C-56-591-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Erection | HM-PL-1510 | C-56-591-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.2 Erection CCOB156P110 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Erection | HM-PL-1570 | C-56-591-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.2.1.12.4.3 Field Joint Welding & NDT CCOB156P120 | Piping MTO - Final | Field Joint Welding (Including Isolation Joint) | HE-PI-1300 | C-56-591-01-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.2.1.12.4.3 Field Joint Welding & NDT CCOB156P120 | Project Kick off Meeting | Field Joint Welding (Including Isolation Joint) | ML1002 | C-56-591-01-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.2.1.12.4.3 Field Joint Welding & NDT CCOB156P120 | NDT / PWHT Subcontract Award | Field Joint Welding (Including Isolation Joint) | HS-CN-0190 | C-56-591-01-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.4.3 Field Joint Welding & NDT CCOB156P120 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Field Joint Welding (Including Isolation Joint) | ML1014-B10 | C-56-591-01-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.4.3 Field Joint Welding & NDT CCOB156P120 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Field Joint Welding (Including Isolation Joint) | ML1219-B19 | C-56-591-01-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.4.4 Hydrotesting CCOB156P130 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Hydrotesting | ML1014-B10 | C-56-591-01-PI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.4.4 Hydrotesting CCOB156P130 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Hydrotesting | ML1219-B19 | C-56-591-01-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | Receipt at site and inspection of Isolating Joints (Lot 1) | Installation of Valves & GOV | HM-PL-0740 | C-56-591-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Installation of Valves & GOV | HE-PR-0890 | C-56-591-01-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | Final Issue for Design/ Construction-Tie-In Schedule | Installation of Valves & GOV | HE-PR-0290 | C-56-591-01-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Installation of Valves & GOV | HM-PL-0630 | C-56-591-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Installation of Valves & GOV | HM-PL-0640 | C-56-591-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Installation of Valves & GOV | HM-PL-0220 | C-56-591-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | Final Issue for Design/ Construction-Piping Isometrics | Installation of Valves & GOV | HE-PI-1240 | C-56-591-01-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Installation of Valves & GOV | ML1014-B10 | C-56-591-01-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Installation of Valves & GOV | ML1219-B19 | C-56-591-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.25.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | Receipt at site and inspection of Lifting Equipment | Installation of Valves & GOV | HM-ME-2200 | C-56-591-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | Receipt at site and inspection of Isolating Joints (Lot 2) | Installation of Valves & GOV | HM-PL-1510 | C-56-591-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Installation of Valves & GOV | HM-PL-1570 | C-56-591-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | Piping MTO - Final | Final Bolt Torquing/ Re-Instatement | HE-PI-1300 | C-56-591-01-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | Project Kick off Meeting | Final Bolt Torquing/ Re-Instatement | ML1002 | C-56-591-01-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | Receipt at site and inspection of Isolating Joints (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0740 | C-56-591-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Final Bolt Torquing/ Re-Instatement | HE-PR-0890 | C-56-591-01-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | Final Issue for Design/ Construction-Tie-In Schedule | Final Bolt Torquing/ Re-Instatement | HE-PR-0290 | C-56-591-01-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0630 | C-56-591-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0640 | C-56-591-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | NDT / PWHT Subcontract Award | Final Bolt Torquing/ Re-Instatement | HS-CN-0190 | C-56-591-01-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0220 | C-56-591-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | Final Issue for Design/ Construction-Piping Isometrics | Final Bolt Torquing/ Re-Instatement | HE-PI-1240 | C-56-591-01-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (56" Sales Gas pipeline) - IFC | Final Bolt Torquing/ Re-Instatement | ML1014-B10 | C-56-591-01-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Final Bolt Torquing/ Re-Instatement | ML1219-B19 | C-56-591-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.25.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | Receipt at site and inspection of Lifting Equipment | Final Bolt Torquing/ Re-Instatement | HM-ME-2200 | C-56-591-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | Receipt at site and inspection of Isolating Joints (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1510 | C-56-591-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.6 Final Bolt Torquing/ Re-Instatement CCOB156P150 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1570 | C-56-591-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.2.1.12.6.9 Hybrid Passive Cooling Shelter Installation CCOB156E30 | Receive at Site - Passive Cooling Shelter | Installation of Passive Cooling Shelter | ML1054-D09 | C-56-591-01-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.5.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.9 Hybrid Passive Cooling Shelter Installation CCOB156E30 | Receipt at site and inspection of Active/ Passive Cooled Shelter | Installation of Passive Cooling Shelter | HM-ME-1190 | C-56-591-01-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of RTU | HM-EL-0080 | C-56-591-01-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Installation of RTU | HE-EL-1010 | C-56-591-01-EI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Installation of RTU | HM-ME-1590 | C-56-591-01-EI-1600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-Instrument Index | Installation of RTU | HE-IC-0530 | C-56-591-01-EI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Receipt at site and inspection of Power Distribution Boards | Installation of RTU | HM-ME-0890 | C-56-591-01-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of RTU | HE-EL-1790 | C-56-591-01-EI-1600 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of RTU | HE-EL-0530 | C-56-591-01-EI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | 1st Electrical Bulk material MTO | Installation of RTU | HM-EL-0520 | C-56-591-01-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Issue ICR-Instrument index -Update | Installation of RTU | HE-IC-0490 | C-56-591-01-EI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Installation of RTU | ML1032-B21 | C-56-591-01-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Instrumentation Bulk material MTO | Installation of RTU | HM-IC-0050 | C-56-591-01-EI-1600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of RTU | HM-EL-0280 | C-56-591-01-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-Earthing Layout | Installation of RTU | HE-EL-1670 | C-56-591-01-EI-1600 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-F&G Cause and effect | Installation of RTU | HE-HS-0350 | C-56-591-01-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of RTU | HE-IC-1550 | C-56-591-01-EI-1600 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | Installation of RTU | HE-EL-0770 | C-56-591-01-EI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Electrical Bulk material MTO | Installation of RTU | HM-EL-0530 | C-56-591-01-EI-1600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of RTU | HM-EL-0380 | C-56-591-01-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Installation of RTU | HE-IC-2570 | C-56-591-01-EI-1600 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | 1st Instrumentation Bulk material MTO | Installation of RTU | HM-IC-0040 | C-56-591-01-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Obtain Company Approval-Data sheet for LV Distribution board | Installation of RTU | HE-EL-0640 | C-56-591-01-EI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Installation of RTU | HE-IC-1430 | C-56-591-01-EI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Issue ICR- Addendum to DGs | Installation of RTU | HE-IC-0010 | C-56-591-01-EI-1600 | SS | Completed | Not Started | 10
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of RTU | HE-IC-0710 | C-56-591-01-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Installation of RTU | HM-ME-1690 | C-56-591-01-EI-1600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-Loop Diagrams | Installation of RTU | HE-IC-0770 | C-56-591-01-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | CP Drilling & Earthing Drilling Subcontract Award | Installation of RTU | HS-CN-0240 | C-56-591-01-EI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-I/O list | Installation of RTU | HE-IC-0590 | C-56-591-01-EI-1600 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-Solar Panel System SLDs | Installation of RTU | HE-EL-0350 | C-56-591-01-EI-1600 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of RTU | HE-IC-0650 | C-56-591-01-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-Lighting Layout | Installation of RTU | HE-EL-1730 | C-56-591-01-EI-1600 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Final Issue for Design/ Construction-Data Sheet for AC UPS | Installation of RTU | HE-EL-1860 | C-56-591-01-EI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Issue ICR- P&ID's | Installation of RTU | HE-PR-0110 | C-56-591-01-EI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Installation of RTU | HM-ME-2330 | C-56-591-01-EI-1600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Installation of RTU | HM-ME-2350 | C-56-591-01-EI-1600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of RTU | HM-EL-630 | C-56-591-01-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of RTU | HM-EL-650 | C-56-591-01-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.7 RTU CCOB156E84 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of RTU | HM-EL-690 | C-56-591-01-EI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Electrical & Earthing Cable Laying | HM-EL-0080 | C-56-591-01-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Instrument Trench Layout | Electrical & Earthing Cable Laying | HE-IC-1010 | C-56-591-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Data Sheet for LV cables | Electrical & Earthing Cable Laying | HE-EL-0830 | C-56-591-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Cable Sizing Calculation | Electrical & Earthing Cable Laying | HE-EL-0470 | C-56-591-01-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0830 | C-56-591-01-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Electrical & Earthing Cable Laying | HE-IC-0950 | C-56-591-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | 1st Electrical Bulk material MTO | Electrical & Earthing Cable Laying | HM-EL-0520 | C-56-591-01-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Cable Schedule | Electrical & Earthing Cable Laying | HE-EL-0590 | C-56-591-01-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Cable Routing Layout | Electrical & Earthing Cable Laying | HE-EL-1610 | C-56-591-01-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Data Sheet for HV cables | Electrical & Earthing Cable Laying | HE-EL-1950 | C-56-591-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0230 | C-56-591-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0290 | C-56-591-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-I/O list | Electrical & Earthing Cable Laying | HE-IC-0590 | C-56-591-01-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Re-Issue for Approval- I/O list -Update | Electrical & Earthing Cable Laying | HE-IC-0570 | C-56-591-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Re-Issue for Approval- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0210 | C-56-591-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Re-Issue for Approval- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0270 | C-56-591-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Issue ICR- Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0790 | C-56-591-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Issue ICR- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0250 | C-56-591-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Issue ICR- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0190 | C-56-591-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-630 | C-56-591-01-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Instrument Cable Laying | HM-EL-0080 | C-56-591-01-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Instrument Trench Layout | Instrument Cable Laying | HE-IC-1010 | C-56-591-01-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Data Sheet for LV cables | Instrument Cable Laying | HE-EL-0830 | C-56-591-01-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Cable Sizing Calculation | Instrument Cable Laying | HE-EL-0470 | C-56-591-01-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Instrument Cable Laying | HE-IC-0830 | C-56-591-01-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Instrument Cable Laying | HE-IC-0950 | C-56-591-01-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | 1st Electrical Bulk material MTO | Instrument Cable Laying | HM-EL-0520 | C-56-591-01-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Cable Schedule | Instrument Cable Laying | HE-EL-0590 | C-56-591-01-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Cable Routing Layout | Instrument Cable Laying | HE-EL-1610 | C-56-591-01-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Data Sheet for HV cables | Instrument Cable Laying | HE-EL-1950 | C-56-591-01-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Specification for RTU | Instrument Cable Laying | HE-IC-0230 | C-56-591-01-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-Specification for Leak Detection System | Instrument Cable Laying | HE-IC-0290 | C-56-591-01-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Final Issue for Design/ Construction-I/O list | Instrument Cable Laying | HE-IC-0590 | C-56-591-01-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Re-Issue for Approval- I/O list -Update | Instrument Cable Laying | HE-IC-0570 | C-56-591-01-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Re-Issue for Approval- Specification for RTU | Instrument Cable Laying | HE-IC-0210 | C-56-591-01-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Re-Issue for Approval- Specification for Leak Detection System | Instrument Cable Laying | HE-IC-0270 | C-56-591-01-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Issue ICR- Instrument Cable Block Diagram | Instrument Cable Laying | HE-IC-0790 | C-56-591-01-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Issue ICR- Specification for Leak Detection System | Instrument Cable Laying | HE-IC-0250 | C-56-591-01-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Issue ICR- Specification for RTU | Instrument Cable Laying | HE-IC-0190 | C-56-591-01-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Instrument Cable Laying | HM-EL-630 | C-56-591-01-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | Final Telecom Bulk material MTO | Installation of SDH Cabinet | HM-TL-0050 | C-56-591-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Installation of SDH Cabinet | ML1033-B22 | C-56-591-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | Final Issue for Design/ Construction-Telecom cable schedule | Installation of SDH Cabinet | HE-TL-0830 | C-56-591-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Installation of SDH Cabinet | HE-TL-0410 | C-56-591-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Installation of SDH Cabinet | HE-TL-0350 | C-56-591-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | 1st Telecom Bulk material MTO | Installation of SDH Cabinet | HM-TL-0040 | C-56-591-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Installation of SDH Cabinet | HM-ME-1290 | C-56-591-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | Final Issue for Design/ Construction-Telecom Equipment Layout | Installation of SDH Cabinet | HE-TL-0770 | C-56-591-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | FOC Splicing / Termination Subcontract Award | Installation of SDH Cabinet | HS-CN-0290 | C-56-591-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | Receipt at site and inspection of FOC Cables (Lot 1) | Installation of SDH Cabinet | HM-EL-0180 | C-56-591-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Installation of SDH Cabinet | HE-TL-0710 | C-56-591-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | Installation of SDH Cabinet | HM-ME-1390 | C-56-591-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Installation of SDH Cabinet | HE-TL-0290 | C-56-591-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Installation of SDH Cabinet | HE-TL-0470 | C-56-591-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Installation of SDH Cabinet | HM-ME-2270 | C-56-591-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | Installation of SDH Cabinet | HM-ME-2290 | C-56-591-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.8.1 SDH Cabinet CCOB156I20 | Receipt at site and inspection of FOC Cables (Lot 2) | Installation of SDH Cabinet | HM-EL-610 | C-56-591-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | Receipt at site and inspection of Line Pipes - Lot 1 (Coated) | Stringing (BVS-06 to SW CRS) | HM-PL-0080 | C-52-06CR-PL-ME-2800 | FS | Completed | Not Started | 4
P2543-R01-Oct24..1.2.12.16 Pipe Internal Coating | P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | Pipe Internal Coating Subcontract Award | Stringing (BVS-06 to SW CRS) | HS-CN-730 | C-52-06CR-PL-ME-2800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.13 Pipeline Schematic Arrangement- 56", 52" and 4" Pipline | P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | Final Issue for Design/ Construction-Pipeline Schematic Arrangement - 56", 52" and 4" Pipelines | Stringing (BVS-06 to SW CRS) | HE-PL-0350 | C-52-06CR-PL-ME-2800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.6.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | 1st Pipeline Bulk material MTO | Stringing (BVS-06 to SW CRS) | HM-PL-0880 | C-52-06CR-PL-ME-2800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.19.8.1.21 CP Works TemporaryCCOP52EL49 | Receipt at site and inspection of CP System - Temporary Material | Installation of CP Test Post | HM-PL-0410 | C-52-06CR-PL-CA-5200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.1.3.19.8.1.21 CP Works TemporaryCCOP52EL49 | NDRC Subcontract Award | Installation of CP Test Post | HS-CN-0090 | C-52-06CR-PL-CA-5200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.3.19.8.1.21 CP Works TemporaryCCOP52EL49 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Installation of CP Test Post | ML1149-A07 | C-52-06CR-PL-CA-5200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.2.3.1.8.2.1 Evaporation PondCCOPL52487 | Project Kick off Meeting | Evaporation Pond | ML1002 | C-52-06CR-PL-CI-7200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Issue cleaning & gauging, hydrotesting , Drying, Purging, Pre-commissioning and commissioning Procedure (Final Issue) | Cleaning & Gauging | ML1004-A04 | C-52-06CR-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | NDRC Subcontract Award | Cleaning & Gauging | HS-CN-0090 | C-52-06CR-PL-ME-7400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Cleaning & Gauging | ML1149-A07 | C-52-06CR-PL-ME-7400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.13 E&I Works | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | E&I Works Subcontract Award | FO - Cable Pulling/ Laying | HS-CN-0640 | C-52-06CR-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Receipt at site and inspection of FOC Cables (Lot 1) | FO - Cable Pulling/ Laying | HM-EL-0180 | C-52-06CR-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | FOC Splicing / Termination Subcontract Award | FO - Cable Pulling/ Laying | HS-CN-0290 | C-52-06CR-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Receive at Site - Fiber Optic Cable | FO - Cable Pulling/ Laying | ML1057-D19 | C-52-06CR-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Receipt at site and inspection of FOC Cables (Lot 2) | FO - Cable Pulling/ Laying | HM-EL-610 | C-52-06CR-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Receipt at site and inspection of CP System - Temporary Material | Installation of Test Post for Crossing | HM-PL-0410 | C-52-06CR-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.3.1.3.18.21.1.7 ROW Access Road from BVS-05 to KP 126.2CCOPL52440.1 | Construction NOC from Musanada | Sabka ROW/Grading | C-GOV-1300 | C-52-0506-PL-CI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.18.21.1.11 Pipe StringingCCOPL52441 | Receipt at site and inspection of Line Pipes - Lot 2 (Coated) | Stringing (BVS-05 to BVS-06) | HM-PL-0090 | C-52-0506-PL-ME-2800 | FS | Completed | Not Started | 4
P2543-R01-Oct24..PR.BK.6.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.18.21.1.13 Automatic WeldingCCOPL52448 | 1st Pipeline Bulk material MTO | Automatic Welding | HM-PL-0880 | C-52-0506-PL-ME-3600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.18.21.1.14 NDT TestCCOPL52463 | NDT / PWHT Subcontract Award | NDT | HS-CN-0190 | C-52-0506-PL-ME-4000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.18.21.1.23 CP Works TemporaryCCOP52EL46 | Receipt at site and inspection of CP System - Temporary Material | Installation of CP Test Post | HM-PL-0410 | C-52-0506-PL-CA-5200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.1.3.18.21.1.23 CP Works TemporaryCCOP52EL46 | NDRC Subcontract Award | Installation of CP Test Post | HS-CN-0090 | C-52-0506-PL-CA-5200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.3.18.21.1.23 CP Works TemporaryCCOP52EL46 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Installation of CP Test Post | ML1149-A07 | C-52-0506-PL-CA-5200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Cleaning & Gauging | ML1149-A07 | C-52-0506-PL-ME-7400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | NDRC Subcontract Award | Cleaning & Gauging | HS-CN-0090 | C-52-0506-PL-ME-7400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Receipt at site and inspection of CP System - Temporary Material | Installation of Test Post for Crossing | HM-PL-0410 | C-52-0506-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Receipt at site and inspection of FOC Cables (Lot 1) | FO - Cable Pulling/ Laying | HM-EL-0180 | C-52-0506-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | FOC Splicing / Termination Subcontract Award | FO - Cable Pulling/ Laying | HS-CN-0290 | C-52-0506-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Receipt at site and inspection of FOC Cables (Lot 2) | FO - Cable Pulling/ Laying | HM-EL-610 | C-52-0506-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.3.1.3.17.21.1.8 ROW Access RoadCCOPL52412 | Construction NOC from Musanada | Non-Sabka ROW/Grading | C-GOV-1300 | C-52-0405-PL-CI-1800 | FF | In Progress | In Progress | 16
P2543-R01-Oct24..PR.BK.6.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.17.21.1.12 Automatic WeldingCCOPL52420 | 1st Pipeline Bulk material MTO | Automatic Welding | HM-PL-0880 | C-52-0405-PL-ME-3600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.17.21.1.13 NDT TestCCOPL52435 | NDT / PWHT Subcontract Award | NDT | HS-CN-0190 | C-52-0405-PL-ME-4000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.17.21.1.21 CP Works TemporaryCCOP52EL43 | Receipt at site and inspection of CP System - Temporary Material | Installation of CP Test Post | HM-PL-0410 | C-52-0405-PL-CA-5200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.1.3.17.21.1.21 CP Works TemporaryCCOP52EL43 | NDRC Subcontract Award | Installation of CP Test Post | HS-CN-0090 | C-52-0405-PL-CA-5200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.3.17.21.1.21 CP Works TemporaryCCOP52EL43 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Installation of CP Test Post | ML1149-A07 | C-52-0405-PL-CA-5200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | NDRC Subcontract Award | Cleaning & Gauging | HS-CN-0090 | C-52-0405-PL-ME-7400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Cleaning & Gauging | ML1149-A07 | C-52-0405-PL-ME-7400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Receipt at site and inspection of CP System - Temporary Material | Installation of Test Post for Crossing | HM-PL-0410 | C-52-0405-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | FOC Splicing / Termination Subcontract Award | FO - Cable Pulling/ Laying | HS-CN-0290 | C-52-0405-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Receipt at site and inspection of FOC Cables (Lot 1) | FO - Cable Pulling/ Laying | HM-EL-0180 | C-52-0405-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Receipt at site and inspection of FOC Cables (Lot 2) | FO - Cable Pulling/ Laying | HM-EL-610 | C-52-0405-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.3.1.3.16.21.1.8 ROW Access RoadCCOPL52384 | Construction NOC from Musanada | Non-Sabka ROW/Grading | C-GOV-1300 | C-52-0304-PL-CI-1800 | SS | In Progress | Completed | 0
P2543-R01-Oct24..PR.BK.6.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.16.21.1.12 Automatic WeldingCCOPL52392 | 1st Pipeline Bulk material MTO | Automatic Welding | HM-PL-0880 | C-52-0304-PL-ME-3600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.16.21.1.13 NDT TestCCOPL52407 | NDT / PWHT Subcontract Award | NDT | HS-CN-0190 | C-52-0304-PL-ME-4000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.16.21.1.19 CP Works TemporaryCCOP52EL41 | Receipt at site and inspection of CP System - Temporary Material | Installation of CP Test Post | HM-PL-0410 | C-52-0304-PL-CA-5200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.1.3.16.21.1.19 CP Works TemporaryCCOP52EL41 | NDRC Subcontract Award | Installation of CP Test Post | HS-CN-0090 | C-52-0304-PL-CA-5200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.3.16.21.1.19 CP Works TemporaryCCOP52EL41 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Installation of CP Test Post | ML1149-A07 | C-52-0304-PL-CA-5200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | NDRC Subcontract Award | Cleaning & Gauging | HS-CN-0090 | C-52-0304-PL-ME-7400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Cleaning & Gauging | ML1149-A07 | C-52-0304-PL-ME-7400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Receipt at site and inspection of CP System - Temporary Material | Installation of Test Post for Crossing | HM-PL-0410 | C-52-0304-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | FOC Splicing / Termination Subcontract Award | FO - Cable Pulling/ Laying | HS-CN-0290 | C-52-0304-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Receipt at site and inspection of FOC Cables (Lot 1) | FO - Cable Pulling/ Laying | HM-EL-0180 | C-52-0304-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Receipt at site and inspection of FOC Cables (Lot 2) | FO - Cable Pulling/ Laying | HM-EL-610 | C-52-0304-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.15.21.1.11 NDT TestCCOPL52379 | NDT / PWHT Subcontract Award | NDT | HS-CN-0190 | C-52-0203-PL-ME-4000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.1.3.15.21.1.17 CP Works TemporaryCCOP52EL38 | NDRC Subcontract Award | Installation of CP Test Post | HS-CN-0090 | C-52-0203-PL-CA-5200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.3.15.21.1.17 CP Works TemporaryCCOP52EL38 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Installation of CP Test Post | ML1149-A07 | C-52-0203-PL-CA-5200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | NDRC Subcontract Award | Cleaning & Gauging | HS-CN-0090 | C-52-0203-PL-ME-7400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Cleaning & Gauging | ML1149-A07 | C-52-0203-PL-ME-7400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | FOC Splicing / Termination Subcontract Award | FO - Cable Pulling/ Laying | HS-CN-0290 | C-52-0203-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | Receipt at site and inspection of FOC Cables (Lot 1) | FO - Cable Pulling/ Laying | HM-EL-0180 | C-52-0203-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2711 F&G Termination Drawings | P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | Final Issue for Design/ Construction- F&G Termination Drawings | FO - Cable Pulling/ Laying | HE-IC-3170 | C-52-0203-PL-TE-8200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | Receipt at site and inspection of FOC Cables (Lot 2) | FO - Cable Pulling/ Laying | HM-EL-610 | C-52-0203-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.8.21.1.18 NDT TestCCOPL52351 | NDT / PWHT Subcontract Award | NDT | HS-CN-0190 | C-52-0102-PL-ME-4000 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.1.3.8.21.1.21 CP Works TemporaryCCOP52EL35 | NDRC Subcontract Award | Installation of CP Test Post | HS-CN-0090 | C-52-0102-PL-CA-5200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.3.8.21.1.21 CP Works TemporaryCCOP52EL35 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Installation of CP Test Post | ML1149-A07 | C-52-0102-PL-CA-5200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Cleaning & Gauging | ML1149-A07 | C-52-0102-PL-ME-7400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | NDRC Subcontract Award | Cleaning & Gauging | HS-CN-0090 | C-52-0102-PL-ME-7400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.3.8.21.5.1 Telecom Works along PipelineCCOP52IC52 | FOC Splicing / Termination Subcontract Award | FO - Cable Pulling/ Laying | HS-CN-0290 | C-52-0102-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.8.21.5.1 Telecom Works along PipelineCCOP52IC52 | Receipt at site and inspection of FOC Cables (Lot 1) | FO - Cable Pulling/ Laying | HM-EL-0180 | C-52-0102-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.8.21.5.1 Telecom Works along PipelineCCOP52IC52 | Receipt at site and inspection of FOC Cables (Lot 2) | FO - Cable Pulling/ Laying | HM-EL-610 | C-52-0102-PL-TE-8200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | Topographical Survey | Trench Excavation-Lot1 | HE-SS-0030 | C-52-HG01-PL-CI-2400 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | Project Kick off Meeting | Trench Excavation-Lot1 | ML1002 | C-52-HG01-PL-CI-2400 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.2.21.1.16 NDT TestCCOPL52309 | NDT / PWHT Subcontract Award | NDT-Lot1 | HS-CN-0190 | C-52-HG01-PL-ME-4000 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.26.LL.20.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..4.3.1.3.2.21.1.26 CP Works TemporaryCCOP52EL56 | Manufacturing & Assembly of CP System | Installation of CP Test Post | HM-PL-0360 | C-52-HG01-PL-CA-5200 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..1.2.13.11 Cathodic Protection Work | P2543-R01-Oct24..4.3.1.3.2.21.1.26 CP Works TemporaryCCOP52EL56 | Place LOA/FOA - Cathodic Protection Work | Installation of CP Test Post | HS-GN-0530 | C-52-HG01-PL-CA-5200 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.1.3.2.21.1.26 CP Works TemporaryCCOP52EL56 | NDRC Subcontract Award | Installation of CP Test Post | HS-CN-0090 | C-52-HG01-PL-CA-5200 | FF | Completed | In Progress | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.3.2.21.1.26 CP Works TemporaryCCOP52EL56 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Installation of CP Test Post | ML1149-A07 | C-52-HG01-PL-CA-5200 | FF | Completed | In Progress | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.2.3.10.8.2.1 Evaporation PondCCOPL52319 | Project Kick off Meeting | Evaporation Pond | ML1002 | C-52-HG01-PL-CI-7200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | ML1149-A07 | C-52-HG01-PL-ME-7400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | NDRC Subcontract Award | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | HS-CN-0090 | C-52-HG01-PL-ME-7400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Final Issue for Design/ Construction-Civil UG layout | Installation of Test Post for Crossing | HE-CS-0530 | C-52-HG01-PL-CA-5220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.13.11 Cathodic Protection Work | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Place LOA/FOA - Cathodic Protection Work | Installation of Test Post for Crossing | HS-GN-0530 | C-52-HG01-PL-CA-5220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Manufacturing & Assembly of CP System | Installation of Test Post for Crossing | HM-PL-0360 | C-52-HG01-PL-CA-5220 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.2 NDRC | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | NDRC Subcontract Award | Installation of Test Post for Crossing | HS-CN-0090 | C-52-HG01-PL-CA-5220 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (52" Pipeline) | Installation of Test Post for Crossing | ML1149-A07 | C-52-HG01-PL-CA-5220 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.3.2.21.4.1 Telecom Works along Pipeline CCOP52IC57 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | FO - Cable Pulling/ Laying | HE-TL-0470 | C-52-HG01-PL-TE-8200 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.3.2.21.4.1 Telecom Works along Pipeline CCOP52IC57 | Final Issue for Design/ Construction-Telecom cable schedule | FO - Cable Pulling/ Laying | HE-TL-0830 | C-52-HG01-PL-TE-8200 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.3.2.21.4.1 Telecom Works along Pipeline CCOP52IC57 | Final Issue for Design/ Construction-Telecom Equipment Layout | FO - Cable Pulling/ Laying | HE-TL-0770 | C-52-HG01-PL-TE-8200 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.2.21.4.1 Telecom Works along Pipeline CCOP52IC57 | Receipt at site and inspection of FOC Cables (Lot 1) | FO - Cable Pulling/ Laying | HM-EL-0180 | C-52-HG01-PL-TE-8200 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.2.21.4.1 Telecom Works along Pipeline CCOP52IC57 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | FO - Cable Pulling/ Laying | HE-TL-0710 | C-52-HG01-PL-TE-8200 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.3.2.21.4.1 Telecom Works along Pipeline CCOP52IC57 | FOC Splicing / Termination Subcontract Award | FO - Cable Pulling/ Laying | HS-CN-0290 | C-52-HG01-PL-TE-8200 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..4.3.1.3.2.21.4.1 Telecom Works along Pipeline CCOP52IC57 | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | FO - Cable Pulling/ Laying | HE-IC-0110 | C-52-HG01-PL-TE-8200 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.3.5.21.1.27 Precasting for fence posts from HGCP to BVS-01CCOP52CS52.7 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Pre-Casting of Fence Foundation (BVS-01 to HGCP) | HE-CS-0350 | C-52-HG01-FENCE-1000 | FS | Completed | In Progress | 90
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.5.21.1.46 Concrete Works for fence posts from HGCP to BVS-01CCOP52CS54.7 | 1st Civil Bulk material MTO | Concrete Works (Blinding) for Fence Foundation (BVS-01 to HGCP) | HM-CS-0040 | C-52-HG01-FENCE-1030 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.5.21.1.8 Precasting for fence posts from BVS-06 to CRS SweihanCCOP52CS52.1 | Fabrication Facilities | Pre-Casting of Fence Foundation (BVS-06 to Sweihan-CRS) | CTF-SO1050 | C-52-06CR-FENCE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.3.5.21.1.8 Precasting for fence posts from BVS-06 to CRS SweihanCCOP52CS52.1 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Pre-Casting of Fence Foundation (BVS-06 to Sweihan-CRS) | HE-CS-0350 | C-52-06CR-FENCE-1000 | FS | Completed | Not Started | 28
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.5.21.1.12 Concrete Works for Fence from BVS-06 to CRS SweihanCCOP52CS54.1 | 1st Civil Bulk material MTO | Concrete Works (Blinding) for Fence Foundation (BVS-06 to Sweihan-CRS) | HM-CS-0040 | C-52-06CR-FENCE-1030 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.5.21.1.14 Fence Installation (Type3) from BVS-06 to CRS SweihanCCOP52CS57.1 | Fence Works Subcontract Award | Installation of Fence Post (Including Foundation) (BVS-06 to Sweihan-CRS) | HS-CN-0690 | C-52-06CR-FENCE-1050 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-52-598-06-CI-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-52-598-06-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-52-598-06-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Site Survey, Preparation & Grading Works | HE-CS-0470 | C-52-598-06-CI-1000 | FS | In Progress | Not Started | 3
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Site Survey, Preparation & Grading Works | CTF-1000 | C-52-598-06-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | NOC's / Approval /Survey | Site Survey, Preparation & Grading Works | CTF-1010 | C-52-598-06-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-Fire fighting & Safety equipment layout | Concrete Works for Equipment Foundations & Hard Stand Area | HE-HS-0410 | C-52-598-06-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-1190 | C-52-598-06-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.5 F&G layout | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-F&G layout | Concrete Works for Equipment Foundations & Hard Stand Area | HE-HS-0290 | C-52-598-06-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-0230 | C-52-598-06-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-Solar panel foundation details | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-0890 | C-52-598-06-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-1310 | C-52-598-06-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Equipment Foundations & Hard Stand Area | ML1034-B25 | C-52-598-06-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | 1st Civil Bulk material MTO | Concrete Works for Equipment Foundations & Hard Stand Area | HM-CS-0040 | C-52-598-06-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-Fire fighting & Safety equipment layout | Concrete Works for Field Instrument, JB Foundations | HE-HS-0410 | C-52-598-06-CI-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.5 F&G layout | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-F&G layout | Concrete Works for Field Instrument, JB Foundations | HE-HS-0290 | C-52-598-06-CI-1410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Field Instrument, JB Foundations | HE-CS-0230 | C-52-598-06-CI-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Field Instrument, JB Foundations | ML1034-B25 | C-52-598-06-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | 1st Civil Bulk material MTO | Concrete Works for Field Instrument, JB Foundations | HM-CS-0040 | C-52-598-06-CI-1410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-Fire fighting & Safety equipment layout | Concrete Works for Access Platform & Misc. Structural Foundations | HE-HS-0410 | C-52-598-06-CI-1420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.5 F&G layout | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-F&G layout | Concrete Works for Access Platform & Misc. Structural Foundations | HE-HS-0290 | C-52-598-06-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Access Platform & Misc. Structural Foundations | HE-CS-0230 | C-52-598-06-CI-1420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Access Platform & Misc. Structural Foundations | ML1034-B25 | C-52-598-06-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-Typical Structural Steel and Foundation details for pipe support | Concrete Works for Access Platform & Misc. Structural Foundations | HE-CS-1370 | C-52-598-06-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | 1st Civil Bulk material MTO | Concrete Works for Access Platform & Misc. Structural Foundations | HM-CS-0040 | C-52-598-06-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.7 Fire fighting & Safety equipment layout | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-Fire fighting & Safety equipment layout | Concrete Works for Light Pole, Fence & Gates Foundation | HE-HS-0410 | C-52-598-06-CI-1430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.5 F&G layout | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-F&G layout | Concrete Works for Light Pole, Fence & Gates Foundation | HE-HS-0290 | C-52-598-06-CI-1430 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Light Pole, Fence & Gates Foundation | HE-CS-0230 | C-52-598-06-CI-1430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Light Pole, Fence & Gates Foundation | ML1034-B25 | C-52-598-06-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Final Issue for Design/ Construction-TYPICAL LIGHTING POLE FOUNDATION DETAILS | Concrete Works for Light Pole, Fence & Gates Foundation | HE-CS-1010 | C-52-598-06-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | 1st Civil Bulk material MTO | Concrete Works for Light Pole, Fence & Gates Foundation | HM-CS-0040 | C-52-598-06-CI-1430 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.9.21.1.5 Trenching for CablesCCOB152C38 | Final Issue for Design/ Construction-Civil UG layout | Electrical & Earthing Cable Trenching | HE-CS-0530 | C-52-598-06-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.9.21.1.5 Trenching for CablesCCOB152C38 | Final Issue for Design/ Construction-Civil UG layout | Instrument & Telecom Cable Trenching | HE-CS-0530 | C-52-598-06-CI-1810 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.1.6 Pipe Supports Fabrication & InstallationCCOB152S52 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0110 | C-52-598-06-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.3.1.3.9.21.1.6 Pipe Supports Fabrication & InstallationCCOB152S52 | Final Issue for Design/ Construction-Misc. supports | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1490 | C-52-598-06-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.9.21.1.6 Pipe Supports Fabrication & InstallationCCOB152S52 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Pipe Supports | HS-CN-0690 | C-52-598-06-CI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.1.6 Pipe Supports Fabrication & InstallationCCOB152S52 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0120 | C-52-598-06-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.3.1.3.9.21.1.6 Pipe Supports Fabrication & InstallationCCOB152S52 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1430 | C-52-598-06-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.3.9.21.1.8 Fences & Gates ConstructionCCOB152C36 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Installation of Concrete Pillers for Boundary Wall | HE-CS-0350 | C-52-598-06-CI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.9.21.1.8 Fences & Gates ConstructionCCOB152C36 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Installation of Concrete Pillers for Boundary Wall | HE-CS-0470 | C-52-598-06-CI-2200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.1.7 Fire Point SheltersCCOB152S50 | 1st Structural Bulk material MTO | Installation of Fire Point Shelters | HM-CS-0110 | C-52-598-06-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.3.9.21.1.9 Paving WorksCCOB152C40 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-52-598-06-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.1.9 Paving WorksCCOB152C40 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-52-598-06-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.1.10 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB152S54 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0120 | C-52-598-06-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.9.21.1.10 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB152S54 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Platforms & Crossovers | HS-CN-0690 | C-52-598-06-CI-3000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.1.10 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB152S54 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0110 | C-52-598-06-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.1.10 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB152S54 | Final Structural Bulk material MTO | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HM-CS-0120 | C-52-598-06-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.9.21.1.10 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB152S54 | Fence Works Subcontract Award | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HS-CN-0690 | C-52-598-06-CI-3010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.1.10 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB152S54 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HM-CS-0110 | C-52-598-06-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB152M50 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 1) | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | HM-ME-1990 | C-52-598-06-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB152M50 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | ML1015-B08 | C-52-598-06-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB152M50 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 2) | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | HM-ME-2370 | C-52-598-06-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-52-598-06-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | Fabrication Facilities | Piping Pre-Fabrication | CTF-SO1050 | C-52-598-06-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | Piping Pre-Fabrication | HE-PI-0580 | C-52-598-06-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-52-598-06-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | Final Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0050 | C-52-598-06-PI-1000 | FS | Not Started | Not Started | 14
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-52-598-06-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Pre-Fabrication | HE-PR-0890 | C-52-598-06-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | NDT / PWHT Subcontract Award | Piping Pre-Fabrication | HS-CN-0190 | C-52-598-06-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | Piping Pre-Fabrication | HE-PI-0880 | C-52-598-06-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Pre-Fabrication | HE-PR-0290 | C-52-598-06-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Pre-Fabrication | ML1179-B11 | C-52-598-06-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-52-598-06-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-52-598-06-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.2.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | Final Piping Special Items MTO | Piping Pre-Fabrication | HM-PI-70 | C-52-598-06-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Project Kick off Meeting | Piping Erection | ML1002 | C-52-598-06-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Erection | HM-PL-0630 | C-52-598-06-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Erection | ML1219-B19 | C-52-598-06-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Final Piping Bulk material MTO | Piping Erection | HM-PI-0050 | C-52-598-06-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | 1st Piping Bulk material MTO | Piping Erection | HM-PI-0040 | C-52-598-06-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Erection | HE-PR-0890 | C-52-598-06-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | NDT / PWHT Subcontract Award | Piping Erection | HS-CN-0190 | C-52-598-06-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | Piping Erection | HE-PI-0880 | C-52-598-06-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Erection | HE-PR-0290 | C-52-598-06-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Erection | ML1179-B11 | C-52-598-06-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Final Issue for Design/ Construction-Piping Isometrics | Piping Erection | HE-PI-1240 | C-52-598-06-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Piping MTO - Final | Piping Erection | HE-PI-1300 | C-52-598-06-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Erection | HM-PL-0640 | C-52-598-06-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Erection | HM-PL-0220 | C-52-598-06-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Erection | HM-PL-0740 | C-52-598-06-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.2.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Final Piping Special Items MTO | Piping Erection | HM-PI-70 | C-52-598-06-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Erection | HM-PL-1510 | C-52-598-06-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.2 ErectionCCOB152P060 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Erection | HM-PL-1570 | C-52-598-06-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.9.21.4.3 Field Joint Welding & NDTCCOB152P070 | Piping MTO - Final | Field Joint Welding (Including Isolation Joint) | HE-PI-1300 | C-52-598-06-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.9.21.4.3 Field Joint Welding & NDTCCOB152P070 | Project Kick off Meeting | Field Joint Welding (Including Isolation Joint) | ML1002 | C-52-598-06-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.4.3 Field Joint Welding & NDTCCOB152P070 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Field Joint Welding (Including Isolation Joint) | ML1219-B19 | C-52-598-06-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.9.21.4.3 Field Joint Welding & NDTCCOB152P070 | NDT / PWHT Subcontract Award | Field Joint Welding (Including Isolation Joint) | HS-CN-0190 | C-52-598-06-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.4.3 Field Joint Welding & NDTCCOB152P070 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Field Joint Welding (Including Isolation Joint) | ML1179-B11 | C-52-598-06-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.4.4 HydrotestingCCOB152P080 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Hydrotesting | ML1219-B19 | C-52-598-06-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.4.4 HydrotestingCCOB152P080 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Hydrotesting | ML1179-B11 | C-52-598-06-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Installation of Valves & GOV | HM-PL-0630 | C-52-598-06-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Installation of Valves & GOV | ML1219-B19 | C-52-598-06-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Installation of Valves & GOV | HE-PR-0890 | C-52-598-06-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | Installation of Valves & GOV | HE-PI-0880 | C-52-598-06-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | Final Issue for Design/ Construction-Tie-In Schedule | Installation of Valves & GOV | HE-PR-0290 | C-52-598-06-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Installation of Valves & GOV | ML1179-B11 | C-52-598-06-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | Final Issue for Design/ Construction-Piping Isometrics | Installation of Valves & GOV | HE-PI-1240 | C-52-598-06-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Installation of Valves & GOV | HM-PL-0640 | C-52-598-06-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Installation of Valves & GOV | HM-PL-0220 | C-52-598-06-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | Receipt at site and inspection of Isolating Joints (Lot 1) | Installation of Valves & GOV | HM-PL-0740 | C-52-598-06-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | Receipt at site and inspection of Isolating Joints (Lot 2) | Installation of Valves & GOV | HM-PL-1510 | C-52-598-06-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Installation of Valves & GOV | HM-PL-1570 | C-52-598-06-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | Piping MTO - Final | Final Bolt Torquing/ Re-Instatement | HE-PI-1300 | C-52-598-06-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | Project Kick off Meeting | Final Bolt Torquing/ Re-Instatement | ML1002 | C-52-598-06-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0630 | C-52-598-06-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Final Bolt Torquing/ Re-Instatement | ML1219-B19 | C-52-598-06-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Final Bolt Torquing/ Re-Instatement | HE-PR-0890 | C-52-598-06-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | NDT / PWHT Subcontract Award | Final Bolt Torquing/ Re-Instatement | HS-CN-0190 | C-52-598-06-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | Final Bolt Torquing/ Re-Instatement | HE-PI-0880 | C-52-598-06-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | Final Issue for Design/ Construction-Tie-In Schedule | Final Bolt Torquing/ Re-Instatement | HE-PR-0290 | C-52-598-06-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Final Bolt Torquing/ Re-Instatement | ML1179-B11 | C-52-598-06-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | Final Issue for Design/ Construction-Piping Isometrics | Final Bolt Torquing/ Re-Instatement | HE-PI-1240 | C-52-598-06-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0640 | C-52-598-06-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0220 | C-52-598-06-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | Receipt at site and inspection of Isolating Joints (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0740 | C-52-598-06-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | Receipt at site and inspection of Isolating Joints (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1510 | C-52-598-06-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB152P100 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1570 | C-52-598-06-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.5.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB152E50 | Receipt at site and inspection of Active/ Passive Cooled Shelter | Installation of Passive Cooling Shelter | HM-ME-1190 | C-52-598-06-EI-1000 | FS | Not Started | Not Started | 30
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.9.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB152E50 | Receive at Site - Passive Cooling Shelter | Installation of Passive Cooling Shelter | ML1054-D09 | C-52-598-06-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Electrical Bulk material MTO | Installation of Solar Panel Structural Supports | HM-EL-0530 | C-52-598-06-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Installation of Solar Panel Structural Supports | HM-ME-1590 | C-52-598-06-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of Solar Panel Structural Supports | HE-IC-1550 | C-52-598-06-EI-1210 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Issue ICR- Addendum to DGs | Installation of Solar Panel Structural Supports | HE-IC-0010 | C-52-598-06-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Receipt at site and inspection of Power Distribution Boards | Installation of Solar Panel Structural Supports | HM-ME-0890 | C-52-598-06-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Installation of Solar Panel Structural Supports | HE-IC-1430 | C-52-598-06-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of Solar Panel Structural Supports | HM-EL-0080 | C-52-598-06-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Installation of Solar Panel Structural Supports | HE-IC-2570 | C-52-598-06-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-Instrument Index | Installation of Solar Panel Structural Supports | HE-IC-0530 | C-52-598-06-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-Lighting Layout | Installation of Solar Panel Structural Supports | HE-EL-1730 | C-52-598-06-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | 1st Electrical Bulk material MTO | Installation of Solar Panel Structural Supports | HM-EL-0520 | C-52-598-06-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of Solar Panel Structural Supports | HE-IC-0650 | C-52-598-06-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | CP Drilling & Earthing Drilling Subcontract Award | Installation of Solar Panel Structural Supports | HS-CN-0240 | C-52-598-06-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Instrumentation Bulk material MTO | Installation of Solar Panel Structural Supports | HM-IC-0050 | C-52-598-06-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Installation of Solar Panel Structural Supports | HM-ME-1690 | C-52-598-06-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of Solar Panel Structural Supports | HE-EL-0530 | C-52-598-06-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-Solar Panel System SLDs | Installation of Solar Panel Structural Supports | HE-EL-0350 | C-52-598-06-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Installation of Solar Panel Structural Supports | HE-EL-1010 | C-52-598-06-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-Loop Diagrams | Installation of Solar Panel Structural Supports | HE-IC-0770 | C-52-598-06-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of Solar Panel Structural Supports | HE-EL-1790 | C-52-598-06-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Obtain Company Approval-Data sheet for LV Distribution board | Installation of Solar Panel Structural Supports | HE-EL-0640 | C-52-598-06-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Issue ICR-Instrument index -Update | Installation of Solar Panel Structural Supports | HE-IC-0490 | C-52-598-06-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of Solar Panel Structural Supports | HM-EL-0380 | C-52-598-06-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.6.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Receipt at site and inspection of Solar PV system | Installation of Solar Panel Structural Supports | HM-ME-1090 | C-52-598-06-EI-1210 | FF | Not Started | Not Started | 12
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-F&G Cause and effect | Installation of Solar Panel Structural Supports | HE-HS-0350 | C-52-598-06-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-0280 | C-52-598-06-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of Solar Panel Structural Supports | HE-IC-0710 | C-52-598-06-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Installation of Solar Panel Structural Supports | ML1032-B21 | C-52-598-06-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | 1st Instrumentation Bulk material MTO | Installation of Solar Panel Structural Supports | HM-IC-0040 | C-52-598-06-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-Earthing Layout | Installation of Solar Panel Structural Supports | HE-EL-1670 | C-52-598-06-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-I/O list | Installation of Solar Panel Structural Supports | HE-IC-0590 | C-52-598-06-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | Installation of Solar Panel Structural Supports | HE-EL-0770 | C-52-598-06-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Final Issue for Design/ Construction-Data Sheet for AC UPS | Installation of Solar Panel Structural Supports | HE-EL-1860 | C-52-598-06-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Issue ICR- P&ID's | Installation of Solar Panel Structural Supports | HE-PR-0110 | C-52-598-06-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Installation of Solar Panel Structural Supports | HM-ME-2330 | C-52-598-06-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-630 | C-52-598-06-EI-1210 | FS | Not Started | Not Started | 3
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-650 | C-52-598-06-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.2 Solar Power SystemCCOB152E66 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-690 | C-52-598-06-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Electrical Bulk material MTO | Deep Earth Well Drilling | HM-EL-0530 | C-52-598-06-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1590 | C-52-598-06-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Deep Earth Well Drilling | HE-IC-1550 | C-52-598-06-EI-1400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Issue ICR- Addendum to DGs | Deep Earth Well Drilling | HE-IC-0010 | C-52-598-06-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Receipt at site and inspection of Power Distribution Boards | Deep Earth Well Drilling | HM-ME-0890 | C-52-598-06-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Deep Earth Well Drilling | HE-IC-1430 | C-52-598-06-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Deep Earth Well Drilling | HM-EL-0080 | C-52-598-06-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Deep Earth Well Drilling | HE-IC-2570 | C-52-598-06-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-Instrument Index | Deep Earth Well Drilling | HE-IC-0530 | C-52-598-06-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-Lighting Layout | Deep Earth Well Drilling | HE-EL-1730 | C-52-598-06-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | 1st Electrical Bulk material MTO | Deep Earth Well Drilling | HM-EL-0520 | C-52-598-06-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-Hook-Up Diagram | Deep Earth Well Drilling | HE-IC-0650 | C-52-598-06-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | CP Drilling & Earthing Drilling Subcontract Award | Deep Earth Well Drilling | HS-CN-0240 | C-52-598-06-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Instrumentation Bulk material MTO | Deep Earth Well Drilling | HM-IC-0050 | C-52-598-06-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1690 | C-52-598-06-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-Electrical Equipment Layout | Deep Earth Well Drilling | HE-EL-0530 | C-52-598-06-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-Solar Panel System SLDs | Deep Earth Well Drilling | HE-EL-0350 | C-52-598-06-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Deep Earth Well Drilling | HE-EL-1010 | C-52-598-06-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-Loop Diagrams | Deep Earth Well Drilling | HE-IC-0770 | C-52-598-06-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-Electrical Installation Drawings | Deep Earth Well Drilling | HE-EL-1790 | C-52-598-06-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Obtain Company Approval-Data sheet for LV Distribution board | Deep Earth Well Drilling | HE-EL-0640 | C-52-598-06-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Issue ICR-Instrument index -Update | Deep Earth Well Drilling | HE-IC-0490 | C-52-598-06-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Receipt at site and inspection of Earthing Material (Lot 1) | Deep Earth Well Drilling | HM-EL-0380 | C-52-598-06-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-F&G Cause and effect | Deep Earth Well Drilling | HE-HS-0350 | C-52-598-06-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-0280 | C-52-598-06-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-Typical Installation Drawings | Deep Earth Well Drilling | HE-IC-0710 | C-52-598-06-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Deep Earth Well Drilling | ML1032-B21 | C-52-598-06-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | 1st Instrumentation Bulk material MTO | Deep Earth Well Drilling | HM-IC-0040 | C-52-598-06-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-Earthing Layout | Deep Earth Well Drilling | HE-EL-1670 | C-52-598-06-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-I/O list | Deep Earth Well Drilling | HE-IC-0590 | C-52-598-06-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | Deep Earth Well Drilling | HE-EL-0770 | C-52-598-06-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Final Issue for Design/ Construction-Data Sheet for AC UPS | Deep Earth Well Drilling | HE-EL-1860 | C-52-598-06-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Issue ICR- P&ID's | Deep Earth Well Drilling | HE-PR-0110 | C-52-598-06-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Deep Earth Well Drilling | HM-ME-2330 | C-52-598-06-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-650 | C-52-598-06-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.3 Deep Earth WellCCOB152E52 | Receipt at site and inspection of Earthing Material (Lot 2) | Deep Earth Well Drilling | HM-EL-690 | C-52-598-06-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Electrical & Earthing Cable Laying | HM-EL-0080 | C-52-598-06-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Instrument Trench Layout | Electrical & Earthing Cable Laying | HE-IC-1010 | C-52-598-06-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Data Sheet for LV cables | Electrical & Earthing Cable Laying | HE-EL-0830 | C-52-598-06-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Cable Routing Layout | Electrical & Earthing Cable Laying | HE-EL-1610 | C-52-598-06-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Cable Schedule | Electrical & Earthing Cable Laying | HE-EL-0590 | C-52-598-06-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Electrical & Earthing Cable Laying | HE-IC-0950 | C-52-598-06-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0830 | C-52-598-06-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | 1st Electrical Bulk material MTO | Electrical & Earthing Cable Laying | HM-EL-0520 | C-52-598-06-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Cable Sizing Calculation | Electrical & Earthing Cable Laying | HE-EL-0470 | C-52-598-06-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Data Sheet for HV cables | Electrical & Earthing Cable Laying | HE-EL-1950 | C-52-598-06-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Receipt at site and inspection of Cable Gland and Termination (Lot 1) | Electrical & Earthing Cable Laying | HM-EL-580 | C-52-598-06-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0230 | C-52-598-06-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0290 | C-52-598-06-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-I/O list | Electrical & Earthing Cable Laying | HE-IC-0590 | C-52-598-06-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Re-Issue for Approval- I/O list -Update | Electrical & Earthing Cable Laying | HE-IC-0570 | C-52-598-06-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Re-Issue for Approval- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0210 | C-52-598-06-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Re-Issue for Approval- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0270 | C-52-598-06-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Issue ICR- Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0790 | C-52-598-06-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Issue ICR- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0250 | C-52-598-06-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Issue ICR- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0190 | C-52-598-06-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-630 | C-52-598-06-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Receipt at site and inspection of Cable Gland and Termination (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-670 | C-52-598-06-EI-2000 | FS | Not Started | Not Started | 3
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Instrument Cable Laying | HM-EL-0080 | C-52-598-06-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Instrument Trench Layout | Instrument Cable Laying | HE-IC-1010 | C-52-598-06-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Data Sheet for LV cables | Instrument Cable Laying | HE-EL-0830 | C-52-598-06-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Cable Routing Layout | Instrument Cable Laying | HE-EL-1610 | C-52-598-06-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Cable Schedule | Instrument Cable Laying | HE-EL-0590 | C-52-598-06-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Instrument Cable Laying | HE-IC-0950 | C-52-598-06-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Instrument Cable Laying | HE-IC-0830 | C-52-598-06-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | 1st Electrical Bulk material MTO | Instrument Cable Laying | HM-EL-0520 | C-52-598-06-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Cable Sizing Calculation | Instrument Cable Laying | HE-EL-0470 | C-52-598-06-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Data Sheet for HV cables | Instrument Cable Laying | HE-EL-1950 | C-52-598-06-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Receipt at site and inspection of Cable Gland and Termination (Lot 1) | Instrument Cable Laying | HM-EL-580 | C-52-598-06-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Specification for RTU | Instrument Cable Laying | HE-IC-0230 | C-52-598-06-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-Specification for Leak Detection System | Instrument Cable Laying | HE-IC-0290 | C-52-598-06-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Final Issue for Design/ Construction-I/O list | Instrument Cable Laying | HE-IC-0590 | C-52-598-06-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Re-Issue for Approval- I/O list -Update | Instrument Cable Laying | HE-IC-0570 | C-52-598-06-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Re-Issue for Approval- Specification for RTU | Instrument Cable Laying | HE-IC-0210 | C-52-598-06-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Re-Issue for Approval- Specification for Leak Detection System | Instrument Cable Laying | HE-IC-0270 | C-52-598-06-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Issue ICR- Instrument Cable Block Diagram | Instrument Cable Laying | HE-IC-0790 | C-52-598-06-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Issue ICR- Specification for Leak Detection System | Instrument Cable Laying | HE-IC-0250 | C-52-598-06-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Issue ICR- Specification for RTU | Instrument Cable Laying | HE-IC-0190 | C-52-598-06-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Instrument Cable Laying | HM-EL-630 | C-52-598-06-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB152E54 | Receipt at site and inspection of Cable Gland and Termination (Lot 2) | Instrument Cable Laying | HM-EL-670 | C-52-598-06-EI-2010 | FS | Not Started | Not Started | 3
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.7.1 CP Anode Bed Installation (subcontract)CCOB152E56 | Receipt at site and inspection of CP System - Permanent Material | CP Cable Laying | HM-PL-0430 | C-52-598-06-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.9.21.7.1 CP Anode Bed Installation (subcontract)CCOB152E56 | CP Drilling & Earthing Drilling Subcontract Award | CP Cable Laying | HS-CN-0240 | C-52-598-06-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | Installation of SDH Cabinet | HM-ME-1390 | C-52-598-06-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | FOC Splicing / Termination Subcontract Award | Installation of SDH Cabinet | HS-CN-0290 | C-52-598-06-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Installation of SDH Cabinet | HE-TL-0350 | C-52-598-06-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Final Telecom Bulk material MTO | Installation of SDH Cabinet | HM-TL-0050 | C-52-598-06-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Installation of SDH Cabinet | ML1033-B22 | C-52-598-06-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | 1st Telecom Bulk material MTO | Installation of SDH Cabinet | HM-TL-0040 | C-52-598-06-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Final Issue for Design/ Construction-Telecom cable schedule | Installation of SDH Cabinet | HE-TL-0830 | C-52-598-06-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Receipt at site and inspection of FOC Cables (Lot 1) | Installation of SDH Cabinet | HM-EL-0180 | C-52-598-06-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Installation of SDH Cabinet | HM-ME-1290 | C-52-598-06-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Installation of SDH Cabinet | HE-TL-0290 | C-52-598-06-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Installation of SDH Cabinet | HE-TL-0710 | C-52-598-06-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Installation of SDH Cabinet | HE-TL-0410 | C-52-598-06-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Final Issue for Design/ Construction-Telecom Equipment Layout | Installation of SDH Cabinet | HE-TL-0770 | C-52-598-06-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Installation of SDH Cabinet | HE-TL-0470 | C-52-598-06-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Installation of SDH Cabinet | HM-ME-2270 | C-52-598-06-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | Installation of SDH Cabinet | HM-ME-2290 | C-52-598-06-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.8.9 SDH CabinetCCOB152I30 | Receipt at site and inspection of FOC Cables (Lot 2) | Installation of SDH Cabinet | HM-EL-610 | C-52-598-06-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-52-598-05-CI-1000 | SS | Completed | In Progress | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-52-598-05-CI-1000 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-52-598-05-CI-1000 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Site Survey, Preparation & Grading Works | HE-CS-0470 | C-52-598-05-CI-1000 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Equipment Foundations & Hard Stand Area | ML1034-B25 | C-52-598-05-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Final Issue for Design/ Construction-Solar panel foundation details | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-0890 | C-52-598-05-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Final Civil Bulk material MTO | Concrete Works for Equipment Foundations & Hard Stand Area | HM-CS-0050 | C-52-598-05-CI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-1310 | C-52-598-05-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-1190 | C-52-598-05-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-0230 | C-52-598-05-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | 1st Civil Bulk material MTO | Concrete Works for Equipment Foundations & Hard Stand Area | HM-CS-0040 | C-52-598-05-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Field Instrument, JB Foundations | ML1034-B25 | C-52-598-05-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Final Civil Bulk material MTO | Concrete Works for Field Instrument, JB Foundations | HM-CS-0050 | C-52-598-05-CI-1410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Field Instrument, JB Foundations | HE-CS-0230 | C-52-598-05-CI-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | 1st Civil Bulk material MTO | Concrete Works for Field Instrument, JB Foundations | HM-CS-0040 | C-52-598-05-CI-1410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Access Platform & Misc. Structural Foundations | ML1034-B25 | C-52-598-05-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Final Civil Bulk material MTO | Concrete Works for Access Platform & Misc. Structural Foundations | HM-CS-0050 | C-52-598-05-CI-1420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Access Platform & Misc. Structural Foundations | HE-CS-0230 | C-52-598-05-CI-1420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Final Issue for Design/ Construction-Typical Structural Steel and Foundation details for pipe support | Concrete Works for Access Platform & Misc. Structural Foundations | HE-CS-1370 | C-52-598-05-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | 1st Civil Bulk material MTO | Concrete Works for Access Platform & Misc. Structural Foundations | HM-CS-0040 | C-52-598-05-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Light Pole, Fence & Gates Foundation | ML1034-B25 | C-52-598-05-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Final Civil Bulk material MTO | Concrete Works for Light Pole, Fence & Gates Foundation | HM-CS-0050 | C-52-598-05-CI-1430 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Final Issue for Design/ Construction-TYPICAL LIGHTING POLE FOUNDATION DETAILS | Concrete Works for Light Pole, Fence & Gates Foundation | HE-CS-1010 | C-52-598-05-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Light Pole, Fence & Gates Foundation | HE-CS-0230 | C-52-598-05-CI-1430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | 1st Civil Bulk material MTO | Concrete Works for Light Pole, Fence & Gates Foundation | HM-CS-0040 | C-52-598-05-CI-1430 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.10.21.1.5 Trenching for CablesCCOB252C38 | Final Issue for Design/ Construction-Civil UG layout | Electrical & Earthing Cable Trenching | HE-CS-0530 | C-52-598-05-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.10.21.1.5 Trenching for CablesCCOB252C38 | Final Issue for Design/ Construction-Civil UG layout | Instrument & Telecom Cable Trenching | HE-CS-0530 | C-52-598-05-CI-1810 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.10.21.1.6 Pipe Supports Fabrication & InstallationCCOB252S50 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Pipe Supports | HS-CN-0690 | C-52-598-05-CI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.1.6 Pipe Supports Fabrication & InstallationCCOB252S50 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0110 | C-52-598-05-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.3.1.3.10.21.1.6 Pipe Supports Fabrication & InstallationCCOB252S50 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1430 | C-52-598-05-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.1.6 Pipe Supports Fabrication & InstallationCCOB252S50 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0120 | C-52-598-05-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.3.1.3.10.21.1.6 Pipe Supports Fabrication & InstallationCCOB252S50 | Final Issue for Design/ Construction-Misc. supports | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1490 | C-52-598-05-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.3.10.21.1.7 Fences & Gates ConstructionCCOB252C36 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Installation of Concrete Pillers for Boundary Wall | HE-CS-0350 | C-52-598-05-CI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.10.21.1.7 Fences & Gates ConstructionCCOB252C36 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Installation of Concrete Pillers for Boundary Wall | HE-CS-0470 | C-52-598-05-CI-2200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.1.8 Fire Point ShelterCCOB252S52 | 1st Structural Bulk material MTO | Installation of Fire Point Shelters | HM-CS-0110 | C-52-598-05-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.1.9 Paving WorksCCOB252C35 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-52-598-05-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.3.10.21.1.9 Paving WorksCCOB252C35 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-52-598-05-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB252S51 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0110 | C-52-598-05-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.10.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB252S51 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Platforms & Crossovers | HS-CN-0690 | C-52-598-05-CI-3000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB252S51 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0120 | C-52-598-05-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB252S51 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HM-CS-0110 | C-52-598-05-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.10.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB252S51 | Fence Works Subcontract Award | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HS-CN-0690 | C-52-598-05-CI-3010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB252S51 | Final Structural Bulk material MTO | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HM-CS-0120 | C-52-598-05-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB252M50 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | ML1015-B08 | C-52-598-05-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB252M50 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 1) | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | HM-ME-1990 | C-52-598-05-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB252M50 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 2) | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | HM-ME-2370 | C-52-598-05-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.10.21.4.1 Piping Pre-FabricationCCOB252P050 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-52-598-05-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.4.1 Piping Pre-FabricationCCOB252P050 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-52-598-05-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..4.3.1.3.10.21.4.1 Piping Pre-FabricationCCOB252P050 | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | Piping Pre-Fabrication | HE-PI-0580 | C-52-598-05-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.4.1 Piping Pre-FabricationCCOB252P050 | Final Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0050 | C-52-598-05-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.4.1 Piping Pre-FabricationCCOB252P050 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-52-598-05-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.10.21.4.1 Piping Pre-FabricationCCOB252P050 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-52-598-05-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.10.21.4.1 Piping Pre-FabricationCCOB252P050 | NDT / PWHT Subcontract Award | Piping Pre-Fabrication | HS-CN-0190 | C-52-598-05-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.10.21.4.1 Piping Pre-FabricationCCOB252P050 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Pre-Fabrication | HE-PR-0290 | C-52-598-05-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.10.21.4.1 Piping Pre-FabricationCCOB252P050 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Pre-Fabrication | HE-PR-0890 | C-52-598-05-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..4.3.1.3.10.21.4.1 Piping Pre-FabricationCCOB252P050 | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | Piping Pre-Fabrication | HE-PI-0880 | C-52-598-05-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.4.1 Piping Pre-FabricationCCOB252P050 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Pre-Fabrication | ML1179-B11 | C-52-598-05-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.10.21.4.1 Piping Pre-FabricationCCOB252P050 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-52-598-05-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Project Kick off Meeting | Piping Erection | ML1002 | C-52-598-05-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | 1st Piping Bulk material MTO | Piping Erection | HM-PI-0040 | C-52-598-05-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Final Piping Bulk material MTO | Piping Erection | HM-PI-0050 | C-52-598-05-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Erection | HM-PL-0630 | C-52-598-05-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Erection | ML1219-B19 | C-52-598-05-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Piping MTO - Final | Piping Erection | HE-PI-1300 | C-52-598-05-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Erection | HM-PL-0740 | C-52-598-05-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | NDT / PWHT Subcontract Award | Piping Erection | HS-CN-0190 | C-52-598-05-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Erection | HM-PL-0220 | C-52-598-05-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Erection | HE-PR-0290 | C-52-598-05-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Erection | HE-PR-0890 | C-52-598-05-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | Piping Erection | HE-PI-0880 | C-52-598-05-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Erection | ML1179-B11 | C-52-598-05-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Erection | HM-PL-0640 | C-52-598-05-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Final Issue for Design/ Construction-Piping Isometrics | Piping Erection | HE-PI-1240 | C-52-598-05-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Erection | HM-PL-1510 | C-52-598-05-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.2 ErectionCCOB252P060 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Erection | HM-PL-1570 | C-52-598-05-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.10.21.4.3 Field Joint Welding & NDTCCOB252P070 | Piping MTO - Final | Field Joint Welding (Including Isolation Joint) | HE-PI-1300 | C-52-598-05-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.10.21.4.3 Field Joint Welding & NDTCCOB252P070 | Project Kick off Meeting | Field Joint Welding (Including Isolation Joint) | ML1002 | C-52-598-05-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.4.3 Field Joint Welding & NDTCCOB252P070 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Field Joint Welding (Including Isolation Joint) | ML1219-B19 | C-52-598-05-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.10.21.4.3 Field Joint Welding & NDTCCOB252P070 | NDT / PWHT Subcontract Award | Field Joint Welding (Including Isolation Joint) | HS-CN-0190 | C-52-598-05-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.4.3 Field Joint Welding & NDTCCOB252P070 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Field Joint Welding (Including Isolation Joint) | ML1179-B11 | C-52-598-05-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.4.4 HydrotestingCCOB252P080 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Hydrotesting | ML1219-B19 | C-52-598-05-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.4.4 HydrotestingCCOB252P080 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Hydrotesting | ML1179-B11 | C-52-598-05-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Installation of Valves & GOV | HM-PL-0630 | C-52-598-05-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Installation of Valves & GOV | ML1219-B19 | C-52-598-05-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | Receipt at site and inspection of Isolating Joints (Lot 1) | Installation of Valves & GOV | HM-PL-0740 | C-52-598-05-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Installation of Valves & GOV | HM-PL-0220 | C-52-598-05-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | Final Issue for Design/ Construction-Tie-In Schedule | Installation of Valves & GOV | HE-PR-0290 | C-52-598-05-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Installation of Valves & GOV | HE-PR-0890 | C-52-598-05-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | Installation of Valves & GOV | HE-PI-0880 | C-52-598-05-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Installation of Valves & GOV | ML1179-B11 | C-52-598-05-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Installation of Valves & GOV | HM-PL-0640 | C-52-598-05-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | Final Issue for Design/ Construction-Piping Isometrics | Installation of Valves & GOV | HE-PI-1240 | C-52-598-05-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | Receipt at site and inspection of Isolating Joints (Lot 2) | Installation of Valves & GOV | HM-PL-1510 | C-52-598-05-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Installation of Valves & GOV | HM-PL-1570 | C-52-598-05-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | Piping MTO - Final | Final Bolt Torquing/ Re-Instatement | HE-PI-1300 | C-52-598-05-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | Project Kick off Meeting | Final Bolt Torquing/ Re-Instatement | ML1002 | C-52-598-05-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0630 | C-52-598-05-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Final Bolt Torquing/ Re-Instatement | ML1219-B19 | C-52-598-05-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | Receipt at site and inspection of Isolating Joints (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0740 | C-52-598-05-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | NDT / PWHT Subcontract Award | Final Bolt Torquing/ Re-Instatement | HS-CN-0190 | C-52-598-05-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0220 | C-52-598-05-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | Final Issue for Design/ Construction-Tie-In Schedule | Final Bolt Torquing/ Re-Instatement | HE-PR-0290 | C-52-598-05-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Final Bolt Torquing/ Re-Instatement | HE-PR-0890 | C-52-598-05-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | Final Bolt Torquing/ Re-Instatement | HE-PI-0880 | C-52-598-05-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Final Bolt Torquing/ Re-Instatement | ML1179-B11 | C-52-598-05-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0640 | C-52-598-05-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | Final Issue for Design/ Construction-Piping Isometrics | Final Bolt Torquing/ Re-Instatement | HE-PI-1240 | C-52-598-05-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | Receipt at site and inspection of Isolating Joints (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1510 | C-52-598-05-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB252P100 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1570 | C-52-598-05-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.5.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB252E50 | Receipt at site and inspection of Active/ Passive Cooled Shelter | Installation of Passive Cooling Shelter | HM-ME-1190 | C-52-598-05-EI-1000 | FS | Not Started | Not Started | 35
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.10.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB252E50 | Receive at Site - Passive Cooling Shelter | Installation of Passive Cooling Shelter | ML1054-D09 | C-52-598-05-EI-1000 | FS | Not Started | Not Started | 45
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | 1st Electrical Bulk material MTO | Installation of Solar Panel Structural Supports | HM-EL-0520 | C-52-598-05-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Installation of Solar Panel Structural Supports | HE-IC-2570 | C-52-598-05-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of Solar Panel Structural Supports | HE-IC-0650 | C-52-598-05-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-Instrument Index | Installation of Solar Panel Structural Supports | HE-IC-0530 | C-52-598-05-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of Solar Panel Structural Supports | HM-EL-0080 | C-52-598-05-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Issue ICR-Instrument index -Update | Installation of Solar Panel Structural Supports | HE-IC-0490 | C-52-598-05-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of Solar Panel Structural Supports | HE-EL-1790 | C-52-598-05-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.LL.6.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Receipt at site and inspection of Solar PV system | Installation of Solar Panel Structural Supports | HM-ME-1090 | C-52-598-05-EI-1210 | FF | Not Started | Not Started | 12
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of Solar Panel Structural Supports | HM-EL-0380 | C-52-598-05-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of Solar Panel Structural Supports | HE-IC-1550 | C-52-598-05-EI-1210 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Obtain Company Approval-Data sheet for LV Distribution board | Installation of Solar Panel Structural Supports | HE-EL-0640 | C-52-598-05-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of Solar Panel Structural Supports | HE-EL-0530 | C-52-598-05-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | CP Drilling & Earthing Drilling Subcontract Award | Installation of Solar Panel Structural Supports | HS-CN-0240 | C-52-598-05-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Installation of Solar Panel Structural Supports | HE-IC-1430 | C-52-598-05-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Receipt at site and inspection of Power Distribution Boards | Installation of Solar Panel Structural Supports | HM-ME-0890 | C-52-598-05-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-Earthing Layout | Installation of Solar Panel Structural Supports | HE-EL-1670 | C-52-598-05-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Installation of Solar Panel Structural Supports | HM-ME-1590 | C-52-598-05-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-Lighting Layout | Installation of Solar Panel Structural Supports | HE-EL-1730 | C-52-598-05-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-Loop Diagrams | Installation of Solar Panel Structural Supports | HE-IC-0770 | C-52-598-05-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | 1st Instrumentation Bulk material MTO | Installation of Solar Panel Structural Supports | HM-IC-0040 | C-52-598-05-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Issue ICR- Addendum to DGs | Installation of Solar Panel Structural Supports | HE-IC-0010 | C-52-598-05-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Instrumentation Bulk material MTO | Installation of Solar Panel Structural Supports | HM-IC-0050 | C-52-598-05-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-Solar Panel System SLDs | Installation of Solar Panel Structural Supports | HE-EL-0350 | C-52-598-05-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Installation of Solar Panel Structural Supports | HM-ME-1690 | C-52-598-05-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Electrical Bulk material MTO | Installation of Solar Panel Structural Supports | HM-EL-0530 | C-52-598-05-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of Solar Panel Structural Supports | HE-IC-0710 | C-52-598-05-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-F&G Cause and effect | Installation of Solar Panel Structural Supports | HE-HS-0350 | C-52-598-05-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Installation of Solar Panel Structural Supports | HE-EL-1010 | C-52-598-05-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-I/O list | Installation of Solar Panel Structural Supports | HE-IC-0590 | C-52-598-05-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-0280 | C-52-598-05-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Installation of Solar Panel Structural Supports | ML1032-B21 | C-52-598-05-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | Installation of Solar Panel Structural Supports | HE-EL-0770 | C-52-598-05-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Final Issue for Design/ Construction-Data Sheet for AC UPS | Installation of Solar Panel Structural Supports | HE-EL-1860 | C-52-598-05-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Issue ICR- P&ID's | Installation of Solar Panel Structural Supports | HE-PR-0110 | C-52-598-05-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Installation of Solar Panel Structural Supports | HM-ME-2330 | C-52-598-05-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Installation of Solar Panel Structural Supports | HM-ME-2350 | C-52-598-05-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-630 | C-52-598-05-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-650 | C-52-598-05-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.2 Solar Power SystemCCOB252E62 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-690 | C-52-598-05-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | 1st Electrical Bulk material MTO | Deep Earth Well Drilling | HM-EL-0520 | C-52-598-05-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Deep Earth Well Drilling | HE-IC-2570 | C-52-598-05-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-Hook-Up Diagram | Deep Earth Well Drilling | HE-IC-0650 | C-52-598-05-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-Instrument Index | Deep Earth Well Drilling | HE-IC-0530 | C-52-598-05-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Deep Earth Well Drilling | HM-EL-0080 | C-52-598-05-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Issue ICR-Instrument index -Update | Deep Earth Well Drilling | HE-IC-0490 | C-52-598-05-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-Electrical Installation Drawings | Deep Earth Well Drilling | HE-EL-1790 | C-52-598-05-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Receipt at site and inspection of Earthing Material (Lot 1) | Deep Earth Well Drilling | HM-EL-0380 | C-52-598-05-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Deep Earth Well Drilling | HE-IC-1550 | C-52-598-05-EI-1400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Obtain Company Approval-Data sheet for LV Distribution board | Deep Earth Well Drilling | HE-EL-0640 | C-52-598-05-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-Electrical Equipment Layout | Deep Earth Well Drilling | HE-EL-0530 | C-52-598-05-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | CP Drilling & Earthing Drilling Subcontract Award | Deep Earth Well Drilling | HS-CN-0240 | C-52-598-05-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Deep Earth Well Drilling | HE-IC-1430 | C-52-598-05-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Receipt at site and inspection of Power Distribution Boards | Deep Earth Well Drilling | HM-ME-0890 | C-52-598-05-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-Earthing Layout | Deep Earth Well Drilling | HE-EL-1670 | C-52-598-05-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1590 | C-52-598-05-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-Lighting Layout | Deep Earth Well Drilling | HE-EL-1730 | C-52-598-05-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-Loop Diagrams | Deep Earth Well Drilling | HE-IC-0770 | C-52-598-05-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | 1st Instrumentation Bulk material MTO | Deep Earth Well Drilling | HM-IC-0040 | C-52-598-05-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Issue ICR- Addendum to DGs | Deep Earth Well Drilling | HE-IC-0010 | C-52-598-05-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Instrumentation Bulk material MTO | Deep Earth Well Drilling | HM-IC-0050 | C-52-598-05-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-Solar Panel System SLDs | Deep Earth Well Drilling | HE-EL-0350 | C-52-598-05-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1690 | C-52-598-05-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Electrical Bulk material MTO | Deep Earth Well Drilling | HM-EL-0530 | C-52-598-05-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-Typical Installation Drawings | Deep Earth Well Drilling | HE-IC-0710 | C-52-598-05-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-F&G Cause and effect | Deep Earth Well Drilling | HE-HS-0350 | C-52-598-05-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Deep Earth Well Drilling | HE-EL-1010 | C-52-598-05-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-I/O list | Deep Earth Well Drilling | HE-IC-0590 | C-52-598-05-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-0280 | C-52-598-05-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Deep Earth Well Drilling | ML1032-B21 | C-52-598-05-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | Deep Earth Well Drilling | HE-EL-0770 | C-52-598-05-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Final Issue for Design/ Construction-Data Sheet for AC UPS | Deep Earth Well Drilling | HE-EL-1860 | C-52-598-05-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Issue ICR- P&ID's | Deep Earth Well Drilling | HE-PR-0110 | C-52-598-05-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Deep Earth Well Drilling | HM-ME-2330 | C-52-598-05-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-650 | C-52-598-05-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.3 Deep Earth WellCCOB252E52 | Receipt at site and inspection of Earthing Material (Lot 2) | Deep Earth Well Drilling | HM-EL-690 | C-52-598-05-EI-1400 | FS | Not Started | Not Started | 7
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Cable Sizing Calculation | Electrical & Earthing Cable Laying | HE-EL-0470 | C-52-598-05-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Electrical & Earthing Cable Laying | HE-IC-0950 | C-52-598-05-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Data Sheet for LV cables | Electrical & Earthing Cable Laying | HE-EL-0830 | C-52-598-05-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0830 | C-52-598-05-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Instrument Trench Layout | Electrical & Earthing Cable Laying | HE-IC-1010 | C-52-598-05-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Cable Routing Layout | Electrical & Earthing Cable Laying | HE-EL-1610 | C-52-598-05-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | 1st Electrical Bulk material MTO | Electrical & Earthing Cable Laying | HM-EL-0520 | C-52-598-05-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Electrical & Earthing Cable Laying | HM-EL-0080 | C-52-598-05-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Cable Schedule | Electrical & Earthing Cable Laying | HE-EL-0590 | C-52-598-05-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Data Sheet for HV cables | Electrical & Earthing Cable Laying | HE-EL-1950 | C-52-598-05-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0230 | C-52-598-05-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0290 | C-52-598-05-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-I/O list | Electrical & Earthing Cable Laying | HE-IC-0590 | C-52-598-05-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Re-Issue for Approval- I/O list -Update | Electrical & Earthing Cable Laying | HE-IC-0570 | C-52-598-05-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Re-Issue for Approval- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0210 | C-52-598-05-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Re-Issue for Approval- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0270 | C-52-598-05-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Issue ICR- Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0790 | C-52-598-05-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Issue ICR- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0250 | C-52-598-05-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Issue ICR- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0190 | C-52-598-05-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-630 | C-52-598-05-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Cable Sizing Calculation | Instrument Cable Laying | HE-EL-0470 | C-52-598-05-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Instrument Cable Laying | HE-IC-0950 | C-52-598-05-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Data Sheet for LV cables | Instrument Cable Laying | HE-EL-0830 | C-52-598-05-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Instrument Cable Laying | HE-IC-0830 | C-52-598-05-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Instrument Trench Layout | Instrument Cable Laying | HE-IC-1010 | C-52-598-05-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Cable Routing Layout | Instrument Cable Laying | HE-EL-1610 | C-52-598-05-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | 1st Electrical Bulk material MTO | Instrument Cable Laying | HM-EL-0520 | C-52-598-05-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Instrument Cable Laying | HM-EL-0080 | C-52-598-05-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Cable Schedule | Instrument Cable Laying | HE-EL-0590 | C-52-598-05-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Data Sheet for HV cables | Instrument Cable Laying | HE-EL-1950 | C-52-598-05-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Specification for RTU | Instrument Cable Laying | HE-IC-0230 | C-52-598-05-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-Specification for Leak Detection System | Instrument Cable Laying | HE-IC-0290 | C-52-598-05-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Final Issue for Design/ Construction-I/O list | Instrument Cable Laying | HE-IC-0590 | C-52-598-05-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Re-Issue for Approval- I/O list -Update | Instrument Cable Laying | HE-IC-0570 | C-52-598-05-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Re-Issue for Approval- Specification for RTU | Instrument Cable Laying | HE-IC-0210 | C-52-598-05-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Re-Issue for Approval- Specification for Leak Detection System | Instrument Cable Laying | HE-IC-0270 | C-52-598-05-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Issue ICR- Instrument Cable Block Diagram | Instrument Cable Laying | HE-IC-0790 | C-52-598-05-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Issue ICR- Specification for Leak Detection System | Instrument Cable Laying | HE-IC-0250 | C-52-598-05-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Issue ICR- Specification for RTU | Instrument Cable Laying | HE-IC-0190 | C-52-598-05-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB252E51 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Instrument Cable Laying | HM-EL-630 | C-52-598-05-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.7.1 CP Anode Bed Installation (subcontract)CCOB252E30 | Receipt at site and inspection of CP System - Permanent Material | CP Cable Laying | HM-PL-0430 | C-52-598-05-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.10.21.7.1 CP Anode Bed Installation (subcontract)CCOB252E30 | CP Drilling & Earthing Drilling Subcontract Award | CP Cable Laying | HS-CN-0240 | C-52-598-05-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Installation of SDH Cabinet | HE-TL-0350 | C-52-598-05-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Installation of SDH Cabinet | HE-TL-0290 | C-52-598-05-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | Final Issue for Design/ Construction-Telecom cable schedule | Installation of SDH Cabinet | HE-TL-0830 | C-52-598-05-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Installation of SDH Cabinet | ML1033-B22 | C-52-598-05-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | Installation of SDH Cabinet | HM-ME-1390 | C-52-598-05-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | Final Telecom Bulk material MTO | Installation of SDH Cabinet | HM-TL-0050 | C-52-598-05-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | Final Issue for Design/ Construction-Telecom Equipment Layout | Installation of SDH Cabinet | HE-TL-0770 | C-52-598-05-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Installation of SDH Cabinet | HE-TL-0410 | C-52-598-05-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Installation of SDH Cabinet | HE-TL-0470 | C-52-598-05-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | Receipt at site and inspection of FOC Cables (Lot 1) | Installation of SDH Cabinet | HM-EL-0180 | C-52-598-05-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Installation of SDH Cabinet | HE-TL-0710 | C-52-598-05-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | FOC Splicing / Termination Subcontract Award | Installation of SDH Cabinet | HS-CN-0290 | C-52-598-05-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | 1st Telecom Bulk material MTO | Installation of SDH Cabinet | HM-TL-0040 | C-52-598-05-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Installation of SDH Cabinet | HM-ME-1290 | C-52-598-05-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Installation of SDH Cabinet | HM-ME-2270 | C-52-598-05-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | Installation of SDH Cabinet | HM-ME-2290 | C-52-598-05-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.8.1 SDH CabinetCCOB252I30 | Receipt at site and inspection of FOC Cables (Lot 2) | Installation of SDH Cabinet | HM-EL-610 | C-52-598-05-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-52-598-04-CI-1000 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-52-598-04-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-52-598-04-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-0230 | C-52-598-04-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | 1st Civil Bulk material MTO | Concrete Works for Equipment Foundations & Hard Stand Area | HM-CS-0040 | C-52-598-04-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Equipment Foundations & Hard Stand Area | ML1034-B25 | C-52-598-04-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-1190 | C-52-598-04-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Final Issue for Design/ Construction-Solar panel foundation details | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-0890 | C-52-598-04-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-1310 | C-52-598-04-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Final Civil Bulk material MTO | Concrete Works for Equipment Foundations & Hard Stand Area | HM-CS-0050 | C-52-598-04-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Field Instrument, JB Foundations | HE-CS-0230 | C-52-598-04-CI-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | 1st Civil Bulk material MTO | Concrete Works for Field Instrument, JB Foundations | HM-CS-0040 | C-52-598-04-CI-1410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Field Instrument, JB Foundations | ML1034-B25 | C-52-598-04-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Final Civil Bulk material MTO | Concrete Works for Field Instrument, JB Foundations | HM-CS-0050 | C-52-598-04-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Final Issue for Design/ Construction-Typical Structural Steel and Foundation details for pipe support | Concrete Works for Access Platform & Misc. Structural Foundations | HE-CS-1370 | C-52-598-04-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Access Platform & Misc. Structural Foundations | HE-CS-0230 | C-52-598-04-CI-1420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | 1st Civil Bulk material MTO | Concrete Works for Access Platform & Misc. Structural Foundations | HM-CS-0040 | C-52-598-04-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Access Platform & Misc. Structural Foundations | ML1034-B25 | C-52-598-04-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Final Civil Bulk material MTO | Concrete Works for Access Platform & Misc. Structural Foundations | HM-CS-0050 | C-52-598-04-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Light Pole, Fence & Gates Foundation | HE-CS-0230 | C-52-598-04-CI-1430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | 1st Civil Bulk material MTO | Concrete Works for Light Pole, Fence & Gates Foundation | HM-CS-0040 | C-52-598-04-CI-1430 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Light Pole, Fence & Gates Foundation | ML1034-B25 | C-52-598-04-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Final Issue for Design/ Construction-TYPICAL LIGHTING POLE FOUNDATION DETAILS | Concrete Works for Light Pole, Fence & Gates Foundation | HE-CS-1010 | C-52-598-04-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | Final Civil Bulk material MTO | Concrete Works for Light Pole, Fence & Gates Foundation | HM-CS-0050 | C-52-598-04-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.11.21.1.5 Trenching for CablesCCOB352C38 | Final Issue for Design/ Construction-Civil UG layout | Electrical & Earthing Cable Trenching | HE-CS-0530 | C-52-598-04-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.11.21.1.5 Trenching for CablesCCOB352C38 | Final Issue for Design/ Construction-Civil UG layout | Instrument & Telecom Cable Trenching | HE-CS-0530 | C-52-598-04-CI-1810 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.11.21.1.7 Pipe Supports Fabrication & InstallationCCOB352S50 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Pipe Supports | HS-CN-0690 | C-52-598-04-CI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.3.1.3.11.21.1.7 Pipe Supports Fabrication & InstallationCCOB352S50 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1430 | C-52-598-04-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.1.7 Pipe Supports Fabrication & InstallationCCOB352S50 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0110 | C-52-598-04-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.3.1.3.11.21.1.7 Pipe Supports Fabrication & InstallationCCOB352S50 | Final Issue for Design/ Construction-Misc. supports | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1490 | C-52-598-04-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.1.7 Pipe Supports Fabrication & InstallationCCOB352S50 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0120 | C-52-598-04-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Installation of Concrete Pillers for Boundary Wall | HE-CS-0470 | C-52-598-04-CI-2200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Installation of Concrete Pillers for Boundary Wall | HE-CS-0350 | C-52-598-04-CI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.1.6 Fire Point SheltersCCOB352S51 | 1st Structural Bulk material MTO | Installation of Fire Point Shelters | HM-CS-0110 | C-52-598-04-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.1.10 Platforms & BollardsCCOB352S52 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0120 | C-52-598-04-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.11.21.1.10 Platforms & BollardsCCOB352S52 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Platforms & Crossovers | HS-CN-0690 | C-52-598-04-CI-3000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.1.10 Platforms & BollardsCCOB352S52 | Final Structural Bulk material MTO | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HM-CS-0120 | C-52-598-04-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.11.21.1.10 Platforms & BollardsCCOB352S52 | Fence Works Subcontract Award | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HS-CN-0690 | C-52-598-04-CI-3010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB352M51 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | ML1015-B08 | C-52-598-04-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB352M51 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 1) | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | HM-ME-1990 | C-52-598-04-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB352M51 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 2) | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | HM-ME-2370 | C-52-598-04-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.11.21.4.1 Piping Pre-FabricationCCOB352P051 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-52-598-04-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.4.1 Piping Pre-FabricationCCOB352P051 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Pre-Fabrication | ML1179-B11 | C-52-598-04-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.11.21.4.1 Piping Pre-FabricationCCOB352P051 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Pre-Fabrication | HE-PR-0890 | C-52-598-04-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..4.3.1.3.11.21.4.1 Piping Pre-FabricationCCOB352P051 | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | Piping Pre-Fabrication | HE-PI-0580 | C-52-598-04-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.4.1 Piping Pre-FabricationCCOB352P051 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-52-598-04-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.11.21.4.1 Piping Pre-FabricationCCOB352P051 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-52-598-04-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..4.3.1.3.11.21.4.1 Piping Pre-FabricationCCOB352P051 | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | Piping Pre-Fabrication | HE-PI-0880 | C-52-598-04-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.11.21.4.1 Piping Pre-FabricationCCOB352P051 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-52-598-04-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.4.1 Piping Pre-FabricationCCOB352P051 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-52-598-04-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.11.21.4.1 Piping Pre-FabricationCCOB352P051 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Pre-Fabrication | HE-PR-0290 | C-52-598-04-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.11.21.4.1 Piping Pre-FabricationCCOB352P051 | NDT / PWHT Subcontract Award | Piping Pre-Fabrication | HS-CN-0190 | C-52-598-04-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | Project Kick off Meeting | Piping Erection | ML1002 | C-52-598-04-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Erection | ML1179-B11 | C-52-598-04-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Erection | HE-PR-0890 | C-52-598-04-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | 1st Piping Bulk material MTO | Piping Erection | HM-PI-0040 | C-52-598-04-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | Final Issue for Design/ Construction-Piping Isometrics | Piping Erection | HE-PI-1240 | C-52-598-04-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | Piping MTO - Final | Piping Erection | HE-PI-1300 | C-52-598-04-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Erection | ML1219-B19 | C-52-598-04-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Erection | HM-PL-0220 | C-52-598-04-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Erection | HM-PL-0740 | C-52-598-04-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Erection | HM-PL-0630 | C-52-598-04-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Erection | HE-PR-0290 | C-52-598-04-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Erection | HM-PL-0640 | C-52-598-04-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | NDT / PWHT Subcontract Award | Piping Erection | HS-CN-0190 | C-52-598-04-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | Final Piping Bulk material MTO | Piping Erection | HM-PI-0050 | C-52-598-04-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Erection | HM-PL-1510 | C-52-598-04-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.2 ErectionCCOB352P061 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Erection | HM-PL-1570 | C-52-598-04-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.11.21.4.3 Field Joint Welding & NDTCCOB352P071 | Piping MTO - Final | Field Joint Welding (Including Isolation Joint) | HE-PI-1300 | C-52-598-04-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.11.21.4.3 Field Joint Welding & NDTCCOB352P071 | Project Kick off Meeting | Field Joint Welding (Including Isolation Joint) | ML1002 | C-52-598-04-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.4.3 Field Joint Welding & NDTCCOB352P071 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Field Joint Welding (Including Isolation Joint) | ML1179-B11 | C-52-598-04-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.4.3 Field Joint Welding & NDTCCOB352P071 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Field Joint Welding (Including Isolation Joint) | ML1219-B19 | C-52-598-04-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.11.21.4.3 Field Joint Welding & NDTCCOB352P071 | NDT / PWHT Subcontract Award | Field Joint Welding (Including Isolation Joint) | HS-CN-0190 | C-52-598-04-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.4.4 HydrotestingCCOB352P081 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Hydrotesting | ML1179-B11 | C-52-598-04-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.4.4 HydrotestingCCOB352P081 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Hydrotesting | ML1219-B19 | C-52-598-04-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | Piping MTO - Final | Installation of Valves & GOV | HE-PI-1300 | C-52-598-04-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | Project Kick off Meeting | Installation of Valves & GOV | ML1002 | C-52-598-04-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Installation of Valves & GOV | ML1179-B11 | C-52-598-04-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Installation of Valves & GOV | HE-PR-0890 | C-52-598-04-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | Final Issue for Design/ Construction-Piping Isometrics | Installation of Valves & GOV | HE-PI-1240 | C-52-598-04-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Installation of Valves & GOV | ML1219-B19 | C-52-598-04-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Installation of Valves & GOV | HM-PL-0220 | C-52-598-04-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | Receipt at site and inspection of Isolating Joints (Lot 1) | Installation of Valves & GOV | HM-PL-0740 | C-52-598-04-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Installation of Valves & GOV | HM-PL-0630 | C-52-598-04-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | Final Issue for Design/ Construction-Tie-In Schedule | Installation of Valves & GOV | HE-PR-0290 | C-52-598-04-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Installation of Valves & GOV | HM-PL-0640 | C-52-598-04-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | NDT / PWHT Subcontract Award | Installation of Valves & GOV | HS-CN-0190 | C-52-598-04-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | Receipt at site and inspection of Isolating Joints (Lot 2) | Installation of Valves & GOV | HM-PL-1510 | C-52-598-04-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Installation of Valves & GOV | HM-PL-1570 | C-52-598-04-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.11.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB352P101 | Piping MTO - Final | Final Bolt Torquing/ Re-Instatement | HE-PI-1300 | C-52-598-04-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.11.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB352P101 | Project Kick off Meeting | Final Bolt Torquing/ Re-Instatement | ML1002 | C-52-598-04-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB352P101 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Final Bolt Torquing/ Re-Instatement | ML1179-B11 | C-52-598-04-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.11.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB352P101 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Final Bolt Torquing/ Re-Instatement | HE-PR-0890 | C-52-598-04-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.11.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB352P101 | Final Issue for Design/ Construction-Piping Isometrics | Final Bolt Torquing/ Re-Instatement | HE-PI-1240 | C-52-598-04-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB352P101 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Final Bolt Torquing/ Re-Instatement | ML1219-B19 | C-52-598-04-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB352P101 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0220 | C-52-598-04-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB352P101 | Receipt at site and inspection of Isolating Joints (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0740 | C-52-598-04-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB352P101 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0630 | C-52-598-04-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.11.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB352P101 | Final Issue for Design/ Construction-Tie-In Schedule | Final Bolt Torquing/ Re-Instatement | HE-PR-0290 | C-52-598-04-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB352P101 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0640 | C-52-598-04-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.11.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB352P101 | NDT / PWHT Subcontract Award | Final Bolt Torquing/ Re-Instatement | HS-CN-0190 | C-52-598-04-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB352P101 | Receipt at site and inspection of Isolating Joints (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1510 | C-52-598-04-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB352P101 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1570 | C-52-598-04-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.5.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB352E50 | Receipt at site and inspection of Active/ Passive Cooled Shelter | Installation of Passive Cooling Shelter | HM-ME-1190 | C-52-598-04-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.11.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB352E50 | Receive at Site - Passive Cooling Shelter | Installation of Passive Cooling Shelter | ML1054-D09 | C-52-598-04-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of Solar Panel Structural Supports | HM-EL-0080 | C-52-598-04-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-0280 | C-52-598-04-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Receipt at site and inspection of Power Distribution Boards | Installation of Solar Panel Structural Supports | HM-ME-0890 | C-52-598-04-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | 1st Electrical Bulk material MTO | Installation of Solar Panel Structural Supports | HM-EL-0520 | C-52-598-04-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Installation of Solar Panel Structural Supports | ML1032-B21 | C-52-598-04-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | Installation of Solar Panel Structural Supports | HE-EL-0770 | C-52-598-04-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of Solar Panel Structural Supports | HM-EL-0380 | C-52-598-04-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of Solar Panel Structural Supports | HE-EL-1790 | C-52-598-04-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Installation of Solar Panel Structural Supports | HE-IC-1430 | C-52-598-04-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Obtain Company Approval-Data sheet for LV Distribution board | Installation of Solar Panel Structural Supports | HE-EL-0640 | C-52-598-04-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Issue ICR-Instrument index -Update | Installation of Solar Panel Structural Supports | HE-IC-0490 | C-52-598-04-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-Loop Diagrams | Installation of Solar Panel Structural Supports | HE-IC-0770 | C-52-598-04-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | 1st Instrumentation Bulk material MTO | Installation of Solar Panel Structural Supports | HM-IC-0040 | C-52-598-04-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.6.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Receipt at site and inspection of Solar PV system | Installation of Solar Panel Structural Supports | HM-ME-1090 | C-52-598-04-EI-1210 | FF | Not Started | Not Started | 12
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of Solar Panel Structural Supports | HE-IC-0650 | C-52-598-04-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-I/O list | Installation of Solar Panel Structural Supports | HE-IC-0590 | C-52-598-04-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of Solar Panel Structural Supports | HE-EL-0530 | C-52-598-04-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-Solar Panel System SLDs | Installation of Solar Panel Structural Supports | HE-EL-0350 | C-52-598-04-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Installation of Solar Panel Structural Supports | HM-ME-1590 | C-52-598-04-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-F&G Cause and effect | Installation of Solar Panel Structural Supports | HE-HS-0350 | C-52-598-04-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of Solar Panel Structural Supports | HE-IC-1550 | C-52-598-04-EI-1210 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Installation of Solar Panel Structural Supports | HE-EL-1010 | C-52-598-04-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-Instrument Index | Installation of Solar Panel Structural Supports | HE-IC-0530 | C-52-598-04-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-Lighting Layout | Installation of Solar Panel Structural Supports | HE-EL-1730 | C-52-598-04-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Electrical Bulk material MTO | Installation of Solar Panel Structural Supports | HM-EL-0530 | C-52-598-04-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | CP Drilling & Earthing Drilling Subcontract Award | Installation of Solar Panel Structural Supports | HS-CN-0240 | C-52-598-04-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-Earthing Layout | Installation of Solar Panel Structural Supports | HE-EL-1670 | C-52-598-04-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of Solar Panel Structural Supports | HE-IC-0710 | C-52-598-04-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Instrumentation Bulk material MTO | Installation of Solar Panel Structural Supports | HM-IC-0050 | C-52-598-04-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Installation of Solar Panel Structural Supports | HE-IC-2570 | C-52-598-04-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Installation of Solar Panel Structural Supports | HM-ME-1690 | C-52-598-04-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Issue ICR- Addendum to DGs | Installation of Solar Panel Structural Supports | HE-IC-0010 | C-52-598-04-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Final Issue for Design/ Construction-Data Sheet for AC UPS | Installation of Solar Panel Structural Supports | HE-EL-1860 | C-52-598-04-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Issue ICR- P&ID's | Installation of Solar Panel Structural Supports | HE-PR-0110 | C-52-598-04-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Installation of Solar Panel Structural Supports | HM-ME-2330 | C-52-598-04-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Installation of Solar Panel Structural Supports | HM-ME-2350 | C-52-598-04-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-630 | C-52-598-04-EI-1210 | FS | Not Started | Not Started | 3
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-650 | C-52-598-04-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.2 Solar Power SystemCCOB352E62 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-690 | C-52-598-04-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Deep Earth Well Drilling | HM-EL-0080 | C-52-598-04-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-0280 | C-52-598-04-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Receipt at site and inspection of Power Distribution Boards | Deep Earth Well Drilling | HM-ME-0890 | C-52-598-04-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | 1st Electrical Bulk material MTO | Deep Earth Well Drilling | HM-EL-0520 | C-52-598-04-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Deep Earth Well Drilling | ML1032-B21 | C-52-598-04-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | Deep Earth Well Drilling | HE-EL-0770 | C-52-598-04-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Receipt at site and inspection of Earthing Material (Lot 1) | Deep Earth Well Drilling | HM-EL-0380 | C-52-598-04-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-Electrical Installation Drawings | Deep Earth Well Drilling | HE-EL-1790 | C-52-598-04-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Deep Earth Well Drilling | HE-IC-1430 | C-52-598-04-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Obtain Company Approval-Data sheet for LV Distribution board | Deep Earth Well Drilling | HE-EL-0640 | C-52-598-04-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Issue ICR-Instrument index -Update | Deep Earth Well Drilling | HE-IC-0490 | C-52-598-04-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-Loop Diagrams | Deep Earth Well Drilling | HE-IC-0770 | C-52-598-04-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | 1st Instrumentation Bulk material MTO | Deep Earth Well Drilling | HM-IC-0040 | C-52-598-04-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-Hook-Up Diagram | Deep Earth Well Drilling | HE-IC-0650 | C-52-598-04-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-I/O list | Deep Earth Well Drilling | HE-IC-0590 | C-52-598-04-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-Electrical Equipment Layout | Deep Earth Well Drilling | HE-EL-0530 | C-52-598-04-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-Solar Panel System SLDs | Deep Earth Well Drilling | HE-EL-0350 | C-52-598-04-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1590 | C-52-598-04-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-F&G Cause and effect | Deep Earth Well Drilling | HE-HS-0350 | C-52-598-04-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Deep Earth Well Drilling | HE-IC-1550 | C-52-598-04-EI-1400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Deep Earth Well Drilling | HE-EL-1010 | C-52-598-04-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-Instrument Index | Deep Earth Well Drilling | HE-IC-0530 | C-52-598-04-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-Lighting Layout | Deep Earth Well Drilling | HE-EL-1730 | C-52-598-04-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Electrical Bulk material MTO | Deep Earth Well Drilling | HM-EL-0530 | C-52-598-04-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | CP Drilling & Earthing Drilling Subcontract Award | Deep Earth Well Drilling | HS-CN-0240 | C-52-598-04-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-Earthing Layout | Deep Earth Well Drilling | HE-EL-1670 | C-52-598-04-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-Typical Installation Drawings | Deep Earth Well Drilling | HE-IC-0710 | C-52-598-04-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Instrumentation Bulk material MTO | Deep Earth Well Drilling | HM-IC-0050 | C-52-598-04-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Deep Earth Well Drilling | HE-IC-2570 | C-52-598-04-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1690 | C-52-598-04-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Issue ICR- Addendum to DGs | Deep Earth Well Drilling | HE-IC-0010 | C-52-598-04-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Final Issue for Design/ Construction-Data Sheet for AC UPS | Deep Earth Well Drilling | HE-EL-1860 | C-52-598-04-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Issue ICR- P&ID's | Deep Earth Well Drilling | HE-PR-0110 | C-52-598-04-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Deep Earth Well Drilling | HM-ME-2330 | C-52-598-04-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-650 | C-52-598-04-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.3 Deep Earth WellCCOB352E52 | Receipt at site and inspection of Earthing Material (Lot 2) | Deep Earth Well Drilling | HM-EL-690 | C-52-598-04-EI-1400 | FS | Not Started | Not Started | 14
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | CP Cable Laying | HE-IC-0830 | C-52-598-04-CA-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | 1st Electrical Bulk material MTO | CP Cable Laying | HM-EL-0520 | C-52-598-04-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Cable Routing Layout | CP Cable Laying | HE-EL-1610 | C-52-598-04-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Cable Schedule | CP Cable Laying | HE-EL-0590 | C-52-598-04-CA-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Data Sheet for LV cables | CP Cable Laying | HE-EL-0830 | C-52-598-04-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Receipt at site and inspection of Power & Control Cables (Lot 1) | CP Cable Laying | HM-EL-0080 | C-52-598-04-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Cable Sizing Calculation | CP Cable Laying | HE-EL-0470 | C-52-598-04-CA-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | CP Cable Laying | HE-IC-0950 | C-52-598-04-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Instrument Trench Layout | CP Cable Laying | HE-IC-1010 | C-52-598-04-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Data Sheet for HV cables | CP Cable Laying | HE-EL-1950 | C-52-598-04-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Specification for RTU | CP Cable Laying | HE-IC-0230 | C-52-598-04-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Specification for Leak Detection System | CP Cable Laying | HE-IC-0290 | C-52-598-04-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-I/O list | CP Cable Laying | HE-IC-0590 | C-52-598-04-CA-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Re-Issue for Approval- I/O list -Update | CP Cable Laying | HE-IC-0570 | C-52-598-04-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Re-Issue for Approval- Specification for RTU | CP Cable Laying | HE-IC-0210 | C-52-598-04-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Re-Issue for Approval- Specification for Leak Detection System | CP Cable Laying | HE-IC-0270 | C-52-598-04-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Issue ICR- Instrument Cable Block Diagram | CP Cable Laying | HE-IC-0790 | C-52-598-04-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Issue ICR- Specification for Leak Detection System | CP Cable Laying | HE-IC-0250 | C-52-598-04-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Issue ICR- Specification for RTU | CP Cable Laying | HE-IC-0190 | C-52-598-04-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Receipt at site and inspection of Power & Control Cables (Lot 2) | CP Cable Laying | HM-EL-630 | C-52-598-04-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0830 | C-52-598-04-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | 1st Electrical Bulk material MTO | Electrical & Earthing Cable Laying | HM-EL-0520 | C-52-598-04-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Cable Routing Layout | Electrical & Earthing Cable Laying | HE-EL-1610 | C-52-598-04-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Cable Schedule | Electrical & Earthing Cable Laying | HE-EL-0590 | C-52-598-04-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Data Sheet for LV cables | Electrical & Earthing Cable Laying | HE-EL-0830 | C-52-598-04-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Electrical & Earthing Cable Laying | HM-EL-0080 | C-52-598-04-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Cable Sizing Calculation | Electrical & Earthing Cable Laying | HE-EL-0470 | C-52-598-04-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Electrical & Earthing Cable Laying | HE-IC-0950 | C-52-598-04-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Instrument Trench Layout | Electrical & Earthing Cable Laying | HE-IC-1010 | C-52-598-04-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Data Sheet for HV cables | Electrical & Earthing Cable Laying | HE-EL-1950 | C-52-598-04-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0230 | C-52-598-04-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0290 | C-52-598-04-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Final Issue for Design/ Construction-I/O list | Electrical & Earthing Cable Laying | HE-IC-0590 | C-52-598-04-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Re-Issue for Approval- I/O list -Update | Electrical & Earthing Cable Laying | HE-IC-0570 | C-52-598-04-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Re-Issue for Approval- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0210 | C-52-598-04-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Re-Issue for Approval- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0270 | C-52-598-04-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Issue ICR- Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0790 | C-52-598-04-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Issue ICR- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0250 | C-52-598-04-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Issue ICR- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0190 | C-52-598-04-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-630 | C-52-598-04-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Final Telecom Bulk material MTO | Installation of SDH Cabinet | HM-TL-0050 | C-52-598-04-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Final Issue for Design/ Construction-Telecom cable schedule | Installation of SDH Cabinet | HE-TL-0830 | C-52-598-04-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Installation of SDH Cabinet | HE-TL-0410 | C-52-598-04-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | 1st Telecom Bulk material MTO | Installation of SDH Cabinet | HM-TL-0040 | C-52-598-04-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Installation of SDH Cabinet | ML1033-B22 | C-52-598-04-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Installation of SDH Cabinet | HE-TL-0350 | C-52-598-04-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | Installation of SDH Cabinet | HM-ME-1390 | C-52-598-04-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | FOC Splicing / Termination Subcontract Award | Installation of SDH Cabinet | HS-CN-0290 | C-52-598-04-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Installation of SDH Cabinet | HM-ME-1290 | C-52-598-04-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Receipt at site and inspection of FOC Cables (Lot 1) | Installation of SDH Cabinet | HM-EL-0180 | C-52-598-04-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Installation of SDH Cabinet | HE-TL-0290 | C-52-598-04-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | Installation of SDH Cabinet | HE-IC-0110 | C-52-598-04-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Final Issue for Design/ Construction-Telecom Equipment Layout | Installation of SDH Cabinet | HE-TL-0770 | C-52-598-04-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Installation of SDH Cabinet | HE-TL-0710 | C-52-598-04-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Installation of SDH Cabinet | HE-TL-0470 | C-52-598-04-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Installation of SDH Cabinet | HM-ME-2270 | C-52-598-04-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | Installation of SDH Cabinet | HM-ME-2290 | C-52-598-04-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.8.1 SDH CabinetCCOB352I30 | Receipt at site and inspection of FOC Cables (Lot 2) | Installation of SDH Cabinet | HM-EL-610 | C-52-598-04-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-52-598-03-CI-1000 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-52-598-03-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-52-598-03-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-1310 | C-52-598-03-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-0230 | C-52-598-03-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Equipment Foundations & Hard Stand Area | ML1034-B25 | C-52-598-03-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Final Issue for Design/ Construction-Solar panel foundation details | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-0890 | C-52-598-03-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | 1st Civil Bulk material MTO | Concrete Works for Equipment Foundations & Hard Stand Area | HM-CS-0040 | C-52-598-03-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-1190 | C-52-598-03-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Final Civil Bulk material MTO | Concrete Works for Equipment Foundations & Hard Stand Area | HM-CS-0050 | C-52-598-03-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Field Instrument, JB Foundations | HE-CS-0230 | C-52-598-03-CI-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Field Instrument, JB Foundations | ML1034-B25 | C-52-598-03-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | 1st Civil Bulk material MTO | Concrete Works for Field Instrument, JB Foundations | HM-CS-0040 | C-52-598-03-CI-1410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Final Civil Bulk material MTO | Concrete Works for Field Instrument, JB Foundations | HM-CS-0050 | C-52-598-03-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Final Issue for Design/ Construction-Typical Structural Steel and Foundation details for pipe support | Concrete Works for Access Platform & Misc. Structural Foundations | HE-CS-1370 | C-52-598-03-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Access Platform & Misc. Structural Foundations | HE-CS-0230 | C-52-598-03-CI-1420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Access Platform & Misc. Structural Foundations | ML1034-B25 | C-52-598-03-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | 1st Civil Bulk material MTO | Concrete Works for Access Platform & Misc. Structural Foundations | HM-CS-0040 | C-52-598-03-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Final Civil Bulk material MTO | Concrete Works for Access Platform & Misc. Structural Foundations | HM-CS-0050 | C-52-598-03-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Light Pole, Fence & Gates Foundation | HE-CS-0230 | C-52-598-03-CI-1430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Final Issue for Design/ Construction-TYPICAL LIGHTING POLE FOUNDATION DETAILS | Concrete Works for Light Pole, Fence & Gates Foundation | HE-CS-1010 | C-52-598-03-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Light Pole, Fence & Gates Foundation | ML1034-B25 | C-52-598-03-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | 1st Civil Bulk material MTO | Concrete Works for Light Pole, Fence & Gates Foundation | HM-CS-0040 | C-52-598-03-CI-1430 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.1.3 Concrete Works (Foundations for Equipment )CCOB452C34.1 | Final Civil Bulk material MTO | Concrete Works for Light Pole, Fence & Gates Foundation | HM-CS-0050 | C-52-598-03-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.12.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB452C34.2 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Pipe Support Foundations | HE-CS-0230 | C-52-598-03-CI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB452C34.2 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Pipe Support Foundations | ML1034-B25 | C-52-598-03-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB452C34.2 | 1st Civil Bulk material MTO | Concrete Works for Pipe Support Foundations | HM-CS-0040 | C-52-598-03-CI-1600 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.1.4 Concrete Works (Foundations for Pipe Supports)CCOB452C34.2 | Final Civil Bulk material MTO | Concrete Works for Pipe Support Foundations | HM-CS-0050 | C-52-598-03-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.12.21.1.6 Trenching for CablesCCOB452C39 | Final Issue for Design/ Construction-Civil UG layout | Electrical & Earthing Cable Trenching | HE-CS-0530 | C-52-598-03-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.12.21.1.6 Trenching for CablesCCOB452C39 | Final Issue for Design/ Construction-Civil UG layout | Instrument & Telecom Cable Trenching | HE-CS-0530 | C-52-598-03-CI-1810 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.3.1.3.12.21.1.5 Pipe Supports Fabrication & InstallationCCOB452S51 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1430 | C-52-598-03-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.3.1.3.12.21.1.5 Pipe Supports Fabrication & InstallationCCOB452S51 | Final Issue for Design/ Construction-Misc. supports | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1490 | C-52-598-03-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.12.21.1.5 Pipe Supports Fabrication & InstallationCCOB452S51 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Pipe Supports | HS-CN-0690 | C-52-598-03-CI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.1.5 Pipe Supports Fabrication & InstallationCCOB452S51 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0120 | C-52-598-03-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.1.5 Pipe Supports Fabrication & InstallationCCOB452S51 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0110 | C-52-598-03-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.3.12.21.1.8 Fences & Gates ConstructionCCOB452C37 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Installation of Concrete Pillers for Boundary Wall | HE-CS-0350 | C-52-598-03-CI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.12.21.1.8 Fences & Gates ConstructionCCOB452C37 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Installation of Concrete Pillers for Boundary Wall | HE-CS-0470 | C-52-598-03-CI-2200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.1.9 Fire Point SheltersCCOB452S53 | 1st Structural Bulk material MTO | Installation of Fire Point Shelters | HM-CS-0110 | C-52-598-03-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.3.12.21.1.7 Paving WorksCCOB452C38 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-52-598-03-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.1.7 Paving WorksCCOB452C38 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-52-598-03-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.12.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB452S52 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Platforms & Crossovers | HS-CN-0690 | C-52-598-03-CI-3000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB452S52 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0120 | C-52-598-03-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB452S52 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0110 | C-52-598-03-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB452M51 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 1) | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | HM-ME-1990 | C-52-598-03-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB452M51 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | ML1015-B08 | C-52-598-03-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB452M51 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 2) | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | HM-ME-2370 | C-52-598-03-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.12.21.4.1 Piping Pre-FabricationCCOB452P051 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-52-598-03-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.12.21.4.1 Piping Pre-FabricationCCOB452P051 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Pre-Fabrication | HE-PR-0890 | C-52-598-03-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.12.21.4.1 Piping Pre-FabricationCCOB452P051 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Pre-Fabrication | HE-PR-0290 | C-52-598-03-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..4.3.1.3.12.21.4.1 Piping Pre-FabricationCCOB452P051 | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | Piping Pre-Fabrication | HE-PI-0580 | C-52-598-03-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..4.3.1.3.12.21.4.1 Piping Pre-FabricationCCOB452P051 | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | Piping Pre-Fabrication | HE-PI-0880 | C-52-598-03-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.12.21.4.1 Piping Pre-FabricationCCOB452P051 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-52-598-03-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.4.1 Piping Pre-FabricationCCOB452P051 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-52-598-03-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.12.21.4.1 Piping Pre-FabricationCCOB452P051 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-52-598-03-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.12.21.4.1 Piping Pre-FabricationCCOB452P051 | NDT / PWHT Subcontract Award | Piping Pre-Fabrication | HS-CN-0190 | C-52-598-03-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.4.1 Piping Pre-FabricationCCOB452P051 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Pre-Fabrication | ML1179-B11 | C-52-598-03-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.4.1 Piping Pre-FabricationCCOB452P051 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-52-598-03-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | Project Kick off Meeting | Piping Erection | ML1002 | C-52-598-03-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Erection | HE-PR-0890 | C-52-598-03-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Erection | HM-PL-0740 | C-52-598-03-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Erection | HE-PR-0290 | C-52-598-03-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Erection | HM-PL-0640 | C-52-598-03-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | Final Issue for Design/ Construction-Piping Isometrics | Piping Erection | HE-PI-1240 | C-52-598-03-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | 1st Piping Bulk material MTO | Piping Erection | HM-PI-0040 | C-52-598-03-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Erection | HM-PL-0630 | C-52-598-03-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | Piping MTO - Final | Piping Erection | HE-PI-1300 | C-52-598-03-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | Final Piping Bulk material MTO | Piping Erection | HM-PI-0050 | C-52-598-03-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | NDT / PWHT Subcontract Award | Piping Erection | HS-CN-0190 | C-52-598-03-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Erection | HM-PL-0220 | C-52-598-03-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Erection | ML1179-B11 | C-52-598-03-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Erection | ML1219-B19 | C-52-598-03-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Erection | HM-PL-1510 | C-52-598-03-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.2 ErectionCCOB452P061 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Erection | HM-PL-1570 | C-52-598-03-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.12.21.4.3 Field Joint Welding & NDTCCOB452P071 | Piping MTO - Final | Field Joint Welding (Including Isolation Joint) | HE-PI-1300 | C-52-598-03-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.12.21.4.3 Field Joint Welding & NDTCCOB452P071 | Project Kick off Meeting | Field Joint Welding (Including Isolation Joint) | ML1002 | C-52-598-03-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.12.21.4.3 Field Joint Welding & NDTCCOB452P071 | NDT / PWHT Subcontract Award | Field Joint Welding (Including Isolation Joint) | HS-CN-0190 | C-52-598-03-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.4.3 Field Joint Welding & NDTCCOB452P071 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Field Joint Welding (Including Isolation Joint) | ML1179-B11 | C-52-598-03-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.4.3 Field Joint Welding & NDTCCOB452P071 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Field Joint Welding (Including Isolation Joint) | ML1219-B19 | C-52-598-03-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.4.4 HydrotestingCCOB452P081 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Hydrotesting | ML1179-B11 | C-52-598-03-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.4.4 HydrotestingCCOB452P081 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Hydrotesting | ML1219-B19 | C-52-598-03-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | Piping MTO - Final | Installation of Valves & GOV | HE-PI-1300 | C-52-598-03-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | Project Kick off Meeting | Installation of Valves & GOV | ML1002 | C-52-598-03-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Installation of Valves & GOV | HE-PR-0890 | C-52-598-03-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | Receipt at site and inspection of Isolating Joints (Lot 1) | Installation of Valves & GOV | HM-PL-0740 | C-52-598-03-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | Final Issue for Design/ Construction-Tie-In Schedule | Installation of Valves & GOV | HE-PR-0290 | C-52-598-03-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Installation of Valves & GOV | HM-PL-0640 | C-52-598-03-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | Final Issue for Design/ Construction-Piping Isometrics | Installation of Valves & GOV | HE-PI-1240 | C-52-598-03-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Installation of Valves & GOV | HM-PL-0630 | C-52-598-03-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | NDT / PWHT Subcontract Award | Installation of Valves & GOV | HS-CN-0190 | C-52-598-03-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Installation of Valves & GOV | HM-PL-0220 | C-52-598-03-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Installation of Valves & GOV | ML1179-B11 | C-52-598-03-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Installation of Valves & GOV | ML1219-B19 | C-52-598-03-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | Receipt at site and inspection of Isolating Joints (Lot 2) | Installation of Valves & GOV | HM-PL-1510 | C-52-598-03-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Installation of Valves & GOV | HM-PL-1570 | C-52-598-03-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.12.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB452P101 | Piping MTO - Final | Final Bolt Torquing/ Re-Instatement | HE-PI-1300 | C-52-598-03-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.12.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB452P101 | Project Kick off Meeting | Final Bolt Torquing/ Re-Instatement | ML1002 | C-52-598-03-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.12.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB452P101 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Final Bolt Torquing/ Re-Instatement | HE-PR-0890 | C-52-598-03-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB452P101 | Receipt at site and inspection of Isolating Joints (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0740 | C-52-598-03-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.12.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB452P101 | Final Issue for Design/ Construction-Tie-In Schedule | Final Bolt Torquing/ Re-Instatement | HE-PR-0290 | C-52-598-03-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB452P101 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0640 | C-52-598-03-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.12.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB452P101 | Final Issue for Design/ Construction-Piping Isometrics | Final Bolt Torquing/ Re-Instatement | HE-PI-1240 | C-52-598-03-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB452P101 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0630 | C-52-598-03-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.12.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB452P101 | NDT / PWHT Subcontract Award | Final Bolt Torquing/ Re-Instatement | HS-CN-0190 | C-52-598-03-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB452P101 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0220 | C-52-598-03-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB452P101 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Final Bolt Torquing/ Re-Instatement | ML1179-B11 | C-52-598-03-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB452P101 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Final Bolt Torquing/ Re-Instatement | ML1219-B19 | C-52-598-03-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB452P101 | Receipt at site and inspection of Isolating Joints (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1510 | C-52-598-03-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB452P101 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1570 | C-52-598-03-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.12.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB452E50 | Receive at Site - Passive Cooling Shelter | Installation of Passive Cooling Shelter | ML1054-D09 | C-52-598-03-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.5.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB452E50 | Receipt at site and inspection of Active/ Passive Cooled Shelter | Installation of Passive Cooling Shelter | HM-ME-1190 | C-52-598-03-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-F&G Cause and effect | Installation of Solar Panel Structural Supports | HE-HS-0350 | C-52-598-03-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Obtain Company Approval-Data sheet for LV Distribution board | Installation of Solar Panel Structural Supports | HE-EL-0640 | C-52-598-03-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-Loop Diagrams | Installation of Solar Panel Structural Supports | HE-IC-0770 | C-52-598-03-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Instrumentation Bulk material MTO | Installation of Solar Panel Structural Supports | HM-IC-0050 | C-52-598-03-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Receipt at site and inspection of Power Distribution Boards | Installation of Solar Panel Structural Supports | HM-ME-0890 | C-52-598-03-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of Solar Panel Structural Supports | HE-IC-1550 | C-52-598-03-EI-1210 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Issue ICR- Addendum to DGs | Installation of Solar Panel Structural Supports | HE-IC-0010 | C-52-598-03-EI-1210 | SS | Completed | Not Started | 10
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of Solar Panel Structural Supports | HM-EL-0380 | C-52-598-03-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | 1st Electrical Bulk material MTO | Installation of Solar Panel Structural Supports | HM-EL-0520 | C-52-598-03-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-0280 | C-52-598-03-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Installation of Solar Panel Structural Supports | HE-IC-1430 | C-52-598-03-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | 1st Instrumentation Bulk material MTO | Installation of Solar Panel Structural Supports | HM-IC-0040 | C-52-598-03-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Installation of Solar Panel Structural Supports | HE-EL-1010 | C-52-598-03-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | Installation of Solar Panel Structural Supports | HE-EL-0770 | C-52-598-03-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of Solar Panel Structural Supports | HE-IC-0650 | C-52-598-03-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-Solar Panel System SLDs | Installation of Solar Panel Structural Supports | HE-EL-0350 | C-52-598-03-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-Instrument Index | Installation of Solar Panel Structural Supports | HE-IC-0530 | C-52-598-03-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Installation of Solar Panel Structural Supports | HE-IC-2570 | C-52-598-03-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of Solar Panel Structural Supports | HE-EL-0530 | C-52-598-03-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of Solar Panel Structural Supports | HE-EL-1790 | C-52-598-03-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Installation of Solar Panel Structural Supports | ML1032-B21 | C-52-598-03-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Installation of Solar Panel Structural Supports | HM-ME-1590 | C-52-598-03-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.6.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Receipt at site and inspection of Solar PV system | Installation of Solar Panel Structural Supports | HM-ME-1090 | C-52-598-03-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of Solar Panel Structural Supports | HE-IC-0710 | C-52-598-03-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | CP Drilling & Earthing Drilling Subcontract Award | Installation of Solar Panel Structural Supports | HS-CN-0240 | C-52-598-03-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-Earthing Layout | Installation of Solar Panel Structural Supports | HE-EL-1670 | C-52-598-03-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Electrical Bulk material MTO | Installation of Solar Panel Structural Supports | HM-EL-0530 | C-52-598-03-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Installation of Solar Panel Structural Supports | HM-ME-1690 | C-52-598-03-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-I/O list | Installation of Solar Panel Structural Supports | HE-IC-0590 | C-52-598-03-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of Solar Panel Structural Supports | HM-EL-0080 | C-52-598-03-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-Lighting Layout | Installation of Solar Panel Structural Supports | HE-EL-1730 | C-52-598-03-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Issue ICR-Instrument index -Update | Installation of Solar Panel Structural Supports | HE-IC-0490 | C-52-598-03-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Final Issue for Design/ Construction-Data Sheet for AC UPS | Installation of Solar Panel Structural Supports | HE-EL-1860 | C-52-598-03-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Issue ICR- P&ID's | Installation of Solar Panel Structural Supports | HE-PR-0110 | C-52-598-03-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Installation of Solar Panel Structural Supports | HM-ME-2330 | C-52-598-03-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Installation of Solar Panel Structural Supports | HM-ME-2350 | C-52-598-03-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-630 | C-52-598-03-EI-1210 | FS | Not Started | Not Started | 12
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-650 | C-52-598-03-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.3 Solar Power SystemCCOB452E63 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-690 | C-52-598-03-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-F&G Cause and effect | Deep Earth Well Drilling | HE-HS-0350 | C-52-598-03-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Obtain Company Approval-Data sheet for LV Distribution board | Deep Earth Well Drilling | HE-EL-0640 | C-52-598-03-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-Loop Diagrams | Deep Earth Well Drilling | HE-IC-0770 | C-52-598-03-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Instrumentation Bulk material MTO | Deep Earth Well Drilling | HM-IC-0050 | C-52-598-03-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Receipt at site and inspection of Power Distribution Boards | Deep Earth Well Drilling | HM-ME-0890 | C-52-598-03-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Deep Earth Well Drilling | HE-IC-1550 | C-52-598-03-EI-1400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Issue ICR- Addendum to DGs | Deep Earth Well Drilling | HE-IC-0010 | C-52-598-03-EI-1400 | SS | Completed | Not Started | 10
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Receipt at site and inspection of Earthing Material (Lot 1) | Deep Earth Well Drilling | HM-EL-0380 | C-52-598-03-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | 1st Electrical Bulk material MTO | Deep Earth Well Drilling | HM-EL-0520 | C-52-598-03-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-0280 | C-52-598-03-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Deep Earth Well Drilling | HE-IC-1430 | C-52-598-03-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | 1st Instrumentation Bulk material MTO | Deep Earth Well Drilling | HM-IC-0040 | C-52-598-03-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Deep Earth Well Drilling | HE-EL-1010 | C-52-598-03-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | Deep Earth Well Drilling | HE-EL-0770 | C-52-598-03-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-Hook-Up Diagram | Deep Earth Well Drilling | HE-IC-0650 | C-52-598-03-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-Solar Panel System SLDs | Deep Earth Well Drilling | HE-EL-0350 | C-52-598-03-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-Instrument Index | Deep Earth Well Drilling | HE-IC-0530 | C-52-598-03-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Deep Earth Well Drilling | HE-IC-2570 | C-52-598-03-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-Electrical Equipment Layout | Deep Earth Well Drilling | HE-EL-0530 | C-52-598-03-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-Electrical Installation Drawings | Deep Earth Well Drilling | HE-EL-1790 | C-52-598-03-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Deep Earth Well Drilling | ML1032-B21 | C-52-598-03-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1590 | C-52-598-03-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-Typical Installation Drawings | Deep Earth Well Drilling | HE-IC-0710 | C-52-598-03-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | CP Drilling & Earthing Drilling Subcontract Award | Deep Earth Well Drilling | HS-CN-0240 | C-52-598-03-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-Earthing Layout | Deep Earth Well Drilling | HE-EL-1670 | C-52-598-03-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Electrical Bulk material MTO | Deep Earth Well Drilling | HM-EL-0530 | C-52-598-03-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1690 | C-52-598-03-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-I/O list | Deep Earth Well Drilling | HE-IC-0590 | C-52-598-03-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Deep Earth Well Drilling | HM-EL-0080 | C-52-598-03-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-Lighting Layout | Deep Earth Well Drilling | HE-EL-1730 | C-52-598-03-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Issue ICR-Instrument index -Update | Deep Earth Well Drilling | HE-IC-0490 | C-52-598-03-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Final Issue for Design/ Construction-Data Sheet for AC UPS | Deep Earth Well Drilling | HE-EL-1860 | C-52-598-03-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Issue ICR- P&ID's | Deep Earth Well Drilling | HE-PR-0110 | C-52-598-03-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Deep Earth Well Drilling | HM-ME-2330 | C-52-598-03-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-650 | C-52-598-03-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.2 Deep Earth WellCCOB452E51 | Receipt at site and inspection of Earthing Material (Lot 2) | Deep Earth Well Drilling | HM-EL-690 | C-52-598-03-EI-1400 | FS | Not Started | Not Started | 21
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Electrical & Earthing Cable Laying | HE-IC-0950 | C-52-598-03-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Final Issue for Design/ Construction-Cable Routing Layout | Electrical & Earthing Cable Laying | HE-EL-1610 | C-52-598-03-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Final Issue for Design/ Construction-Data Sheet for LV cables | Electrical & Earthing Cable Laying | HE-EL-0830 | C-52-598-03-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0830 | C-52-598-03-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Final Issue for Design/ Construction-Instrument Trench Layout | Electrical & Earthing Cable Laying | HE-IC-1010 | C-52-598-03-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Final Issue for Design/ Construction-Cable Schedule | Electrical & Earthing Cable Laying | HE-EL-0590 | C-52-598-03-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Final Issue for Design/ Construction-Cable Sizing Calculation | Electrical & Earthing Cable Laying | HE-EL-0470 | C-52-598-03-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Electrical & Earthing Cable Laying | HM-EL-0080 | C-52-598-03-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | 1st Electrical Bulk material MTO | Electrical & Earthing Cable Laying | HM-EL-0520 | C-52-598-03-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Final Issue for Design/ Construction-Data Sheet for HV cables | Electrical & Earthing Cable Laying | HE-EL-1950 | C-52-598-03-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Final Issue for Design/ Construction-Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0230 | C-52-598-03-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Final Issue for Design/ Construction-Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0290 | C-52-598-03-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Final Issue for Design/ Construction-I/O list | Electrical & Earthing Cable Laying | HE-IC-0590 | C-52-598-03-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Re-Issue for Approval- I/O list -Update | Electrical & Earthing Cable Laying | HE-IC-0570 | C-52-598-03-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Re-Issue for Approval- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0210 | C-52-598-03-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Re-Issue for Approval- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0270 | C-52-598-03-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Issue ICR- Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0790 | C-52-598-03-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Issue ICR- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0250 | C-52-598-03-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Issue ICR- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0190 | C-52-598-03-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB452E53 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-630 | C-52-598-03-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.7.1 CP Anode Bed Installation (subcontract)CCOB452E30 | Receipt at site and inspection of CP System - Permanent Material | CP Cable Laying | HM-PL-0430 | C-52-598-03-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.12.21.7.1 CP Anode Bed Installation (subcontract)CCOB452E30 | CP Drilling & Earthing Drilling Subcontract Award | CP Cable Laying | HS-CN-0240 | C-52-598-03-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Installation of SDH Cabinet | HE-TL-0350 | C-52-598-03-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | FOC Splicing / Termination Subcontract Award | Installation of SDH Cabinet | HS-CN-0290 | C-52-598-03-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Installation of SDH Cabinet | HE-TL-0470 | C-52-598-03-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Installation of SDH Cabinet | HM-ME-1290 | C-52-598-03-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | Final Telecom Bulk material MTO | Installation of SDH Cabinet | HM-TL-0050 | C-52-598-03-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | Receipt at site and inspection of FOC Cables (Lot 1) | Installation of SDH Cabinet | HM-EL-0180 | C-52-598-03-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Installation of SDH Cabinet | HE-TL-0290 | C-52-598-03-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Installation of SDH Cabinet | HE-TL-0710 | C-52-598-03-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Installation of SDH Cabinet | ML1033-B22 | C-52-598-03-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | Final Issue for Design/ Construction-Telecom cable schedule | Installation of SDH Cabinet | HE-TL-0830 | C-52-598-03-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | Final Issue for Design/ Construction-Telecom Equipment Layout | Installation of SDH Cabinet | HE-TL-0770 | C-52-598-03-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | Installation of SDH Cabinet | HM-ME-1390 | C-52-598-03-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | 1st Telecom Bulk material MTO | Installation of SDH Cabinet | HM-TL-0040 | C-52-598-03-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Installation of SDH Cabinet | HE-TL-0410 | C-52-598-03-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Installation of SDH Cabinet | HM-ME-2270 | C-52-598-03-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | Installation of SDH Cabinet | HM-ME-2290 | C-52-598-03-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.8.1 SDH CabinetCCOB452I30 | Receipt at site and inspection of FOC Cables (Lot 2) | Installation of SDH Cabinet | HM-EL-610 | C-52-598-03-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-52-598-02-CI-1000 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-52-598-02-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-52-598-02-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | 1st Civil Bulk material MTO | Concrete Works for Equipment Foundations & Hard Stand Area | HM-CS-0040 | C-52-598-02-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Final Civil Bulk material MTO | Concrete Works for Equipment Foundations & Hard Stand Area | HM-CS-0050 | C-52-598-02-CI-1400 | FS | Not Started | Not Started | 7
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Equipment Foundations & Hard Stand Area | ML1034-B25 | C-52-598-02-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-1310 | C-52-598-02-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-0230 | C-52-598-02-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Final Issue for Design/ Construction-Solar panel foundation details | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-0890 | C-52-598-02-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-1190 | C-52-598-02-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | 1st Civil Bulk material MTO | Concrete Works for Field Instrument, JB Foundations | HM-CS-0040 | C-52-598-02-CI-1410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Final Civil Bulk material MTO | Concrete Works for Field Instrument, JB Foundations | HM-CS-0050 | C-52-598-02-CI-1410 | FS | Not Started | Not Started | 14
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Field Instrument, JB Foundations | ML1034-B25 | C-52-598-02-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Field Instrument, JB Foundations | HE-CS-0230 | C-52-598-02-CI-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | 1st Civil Bulk material MTO | Concrete Works for Access Platform & Misc. Structural Foundations | HM-CS-0040 | C-52-598-02-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Final Civil Bulk material MTO | Concrete Works for Access Platform & Misc. Structural Foundations | HM-CS-0050 | C-52-598-02-CI-1420 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Access Platform & Misc. Structural Foundations | ML1034-B25 | C-52-598-02-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Access Platform & Misc. Structural Foundations | HE-CS-0230 | C-52-598-02-CI-1420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Final Issue for Design/ Construction-Typical Structural Steel and Foundation details for pipe support | Concrete Works for Access Platform & Misc. Structural Foundations | HE-CS-1370 | C-52-598-02-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | 1st Civil Bulk material MTO | Concrete Works for Light Pole, Fence & Gates Foundation | HM-CS-0040 | C-52-598-02-CI-1430 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Final Civil Bulk material MTO | Concrete Works for Light Pole, Fence & Gates Foundation | HM-CS-0050 | C-52-598-02-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Light Pole, Fence & Gates Foundation | ML1034-B25 | C-52-598-02-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Light Pole, Fence & Gates Foundation | HE-CS-0230 | C-52-598-02-CI-1430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..4.3.1.3.13.21.1.3 Concrete Works (Foundations for Equipment)CCOB552C35 | Final Issue for Design/ Construction-TYPICAL LIGHTING POLE FOUNDATION DETAILS | Concrete Works for Light Pole, Fence & Gates Foundation | HE-CS-1010 | C-52-598-02-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.13.21.1.5 Trenching for CablesCCOB552C40 | Final Issue for Design/ Construction-Civil UG layout | Electrical & Earthing Cable Trenching | HE-CS-0530 | C-52-598-02-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.13.21.1.5 Trenching for CablesCCOB552C40 | Final Issue for Design/ Construction-Civil UG layout | Instrument & Telecom Cable Trenching | HE-CS-0530 | C-52-598-02-CI-1810 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.3.1.3.13.21.1.6 Pipe Supports Fabrication & InstallationCCOB552S51 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1430 | C-52-598-02-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.13.21.1.6 Pipe Supports Fabrication & InstallationCCOB552S51 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Pipe Supports | HS-CN-0690 | C-52-598-02-CI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.1.6 Pipe Supports Fabrication & InstallationCCOB552S51 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0120 | C-52-598-02-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.3.1.3.13.21.1.6 Pipe Supports Fabrication & InstallationCCOB552S51 | Final Issue for Design/ Construction-Misc. supports | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1490 | C-52-598-02-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.1.6 Pipe Supports Fabrication & InstallationCCOB552S51 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0110 | C-52-598-02-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.13.21.1.7 Fences & Gates ConstructionCCOB552C38 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Installation of Concrete Pillers for Boundary Wall | HE-CS-0470 | C-52-598-02-CI-2200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.3.13.21.1.7 Fences & Gates ConstructionCCOB552C38 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Installation of Concrete Pillers for Boundary Wall | HE-CS-0350 | C-52-598-02-CI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.1.8 Fire Point SheltersCCOB552S52 | 1st Structural Bulk material MTO | Installation of Fire Point Shelters | HM-CS-0110 | C-52-598-02-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.3.13.21.1.9 Paving WorksCCOB552C39 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-52-598-02-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.1.9 Paving WorksCCOB552C39 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-52-598-02-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0110 | C-52-598-02-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0120 | C-52-598-02-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.13.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Platforms & Crossovers | HS-CN-0690 | C-52-598-02-CI-3000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HM-CS-0110 | C-52-598-02-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 | Final Structural Bulk material MTO | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HM-CS-0120 | C-52-598-02-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.13.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB552S54 | Fence Works Subcontract Award | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HS-CN-0690 | C-52-598-02-CI-3010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB552M52 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 1) | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | HM-ME-1990 | C-52-598-02-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB552M52 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | ML1015-B08 | C-52-598-02-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB552M52 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 2) | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | HM-ME-2370 | C-52-598-02-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.13.21.4.1 Piping Pre-FabricationCCOB552P051 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-52-598-02-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.13.21.4.1 Piping Pre-FabricationCCOB552P051 | NDT / PWHT Subcontract Award | Piping Pre-Fabrication | HS-CN-0190 | C-52-598-02-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.4.1 Piping Pre-FabricationCCOB552P051 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Pre-Fabrication | ML1179-B11 | C-52-598-02-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..4.3.1.3.13.21.4.1 Piping Pre-FabricationCCOB552P051 | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | Piping Pre-Fabrication | HE-PI-0580 | C-52-598-02-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.13.21.4.1 Piping Pre-FabricationCCOB552P051 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Pre-Fabrication | HE-PR-0290 | C-52-598-02-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.4.1 Piping Pre-FabricationCCOB552P051 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-52-598-02-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..4.3.1.3.13.21.4.1 Piping Pre-FabricationCCOB552P051 | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | Piping Pre-Fabrication | HE-PI-0880 | C-52-598-02-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.4.1 Piping Pre-FabricationCCOB552P051 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-52-598-02-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.13.21.4.1 Piping Pre-FabricationCCOB552P051 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-52-598-02-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.13.21.4.1 Piping Pre-FabricationCCOB552P051 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-52-598-02-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.13.21.4.1 Piping Pre-FabricationCCOB552P051 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Pre-Fabrication | HE-PR-0890 | C-52-598-02-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Project Kick off Meeting | Piping Erection | ML1002 | C-52-598-02-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | NDT / PWHT Subcontract Award | Piping Erection | HS-CN-0190 | C-52-598-02-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Erection | ML1179-B11 | C-52-598-02-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Erection | HM-PL-0630 | C-52-598-02-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Erection | HM-PL-0640 | C-52-598-02-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Erection | HE-PR-0290 | C-52-598-02-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Erection | HM-PL-0220 | C-52-598-02-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Erection | HM-PL-0740 | C-52-598-02-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Final Piping Bulk material MTO | Piping Erection | HM-PI-0050 | C-52-598-02-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Erection | ML1219-B19 | C-52-598-02-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | 1st Piping Bulk material MTO | Piping Erection | HM-PI-0040 | C-52-598-02-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Piping MTO - Final | Piping Erection | HE-PI-1300 | C-52-598-02-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Final Issue for Design/ Construction-Piping Isometrics | Piping Erection | HE-PI-1240 | C-52-598-02-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Erection | HE-PR-0890 | C-52-598-02-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Erection | HM-PL-1510 | C-52-598-02-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Erection | HM-PL-1570 | C-52-598-02-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.13.21.4.3 Field Joint Welding & NDTCCOB552P071 | Piping MTO - Final | Field Joint Welding (Including Isolation Joint) | HE-PI-1300 | C-52-598-02-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.13.21.4.3 Field Joint Welding & NDTCCOB552P071 | Project Kick off Meeting | Field Joint Welding (Including Isolation Joint) | ML1002 | C-52-598-02-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.13.21.4.3 Field Joint Welding & NDTCCOB552P071 | NDT / PWHT Subcontract Award | Field Joint Welding (Including Isolation Joint) | HS-CN-0190 | C-52-598-02-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.4.3 Field Joint Welding & NDTCCOB552P071 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Field Joint Welding (Including Isolation Joint) | ML1179-B11 | C-52-598-02-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.4.3 Field Joint Welding & NDTCCOB552P071 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Field Joint Welding (Including Isolation Joint) | ML1219-B19 | C-52-598-02-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.4.4 HydrotestingCCOB552P081 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Hydrotesting | ML1179-B11 | C-52-598-02-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.4.4 HydrotestingCCOB552P081 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Hydrotesting | ML1219-B19 | C-52-598-02-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | Piping MTO - Final | Installation of Valves & GOV | HE-PI-1300 | C-52-598-02-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | Project Kick off Meeting | Installation of Valves & GOV | ML1002 | C-52-598-02-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | NDT / PWHT Subcontract Award | Installation of Valves & GOV | HS-CN-0190 | C-52-598-02-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Installation of Valves & GOV | ML1179-B11 | C-52-598-02-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Installation of Valves & GOV | HM-PL-0630 | C-52-598-02-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Installation of Valves & GOV | HM-PL-0640 | C-52-598-02-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | Final Issue for Design/ Construction-Tie-In Schedule | Installation of Valves & GOV | HE-PR-0290 | C-52-598-02-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Installation of Valves & GOV | HM-PL-0220 | C-52-598-02-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | Receipt at site and inspection of Isolating Joints (Lot 1) | Installation of Valves & GOV | HM-PL-0740 | C-52-598-02-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Installation of Valves & GOV | ML1219-B19 | C-52-598-02-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | Final Issue for Design/ Construction-Piping Isometrics | Installation of Valves & GOV | HE-PI-1240 | C-52-598-02-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Installation of Valves & GOV | HE-PR-0890 | C-52-598-02-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | Receipt at site and inspection of Isolating Joints (Lot 2) | Installation of Valves & GOV | HM-PL-1510 | C-52-598-02-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Installation of Valves & GOV | HM-PL-1570 | C-52-598-02-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.13.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB552P101 | Piping MTO - Final | Final Bolt Torquing/ Re-Instatement | HE-PI-1300 | C-52-598-02-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.13.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB552P101 | Project Kick off Meeting | Final Bolt Torquing/ Re-Instatement | ML1002 | C-52-598-02-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.13.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB552P101 | NDT / PWHT Subcontract Award | Final Bolt Torquing/ Re-Instatement | HS-CN-0190 | C-52-598-02-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB552P101 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Final Bolt Torquing/ Re-Instatement | ML1179-B11 | C-52-598-02-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB552P101 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0630 | C-52-598-02-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB552P101 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0640 | C-52-598-02-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.13.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB552P101 | Final Issue for Design/ Construction-Tie-In Schedule | Final Bolt Torquing/ Re-Instatement | HE-PR-0290 | C-52-598-02-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB552P101 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0220 | C-52-598-02-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB552P101 | Receipt at site and inspection of Isolating Joints (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0740 | C-52-598-02-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB552P101 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Final Bolt Torquing/ Re-Instatement | ML1219-B19 | C-52-598-02-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.13.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB552P101 | Final Issue for Design/ Construction-Piping Isometrics | Final Bolt Torquing/ Re-Instatement | HE-PI-1240 | C-52-598-02-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.13.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB552P101 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Final Bolt Torquing/ Re-Instatement | HE-PR-0890 | C-52-598-02-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB552P101 | Receipt at site and inspection of Isolating Joints (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1510 | C-52-598-02-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB552P101 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1570 | C-52-598-02-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.5.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB552E51 | Receipt at site and inspection of Active/ Passive Cooled Shelter | Installation of Passive Cooling Shelter | HM-ME-1190 | C-52-598-02-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.13.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB552E51 | Receive at Site - Passive Cooling Shelter | Installation of Passive Cooling Shelter | ML1054-D09 | C-52-598-02-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of Solar Panel Structural Supports | HE-IC-1550 | C-52-598-02-EI-1210 | FF | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | 1st Electrical Bulk material MTO | Installation of Solar Panel Structural Supports | HM-EL-0520 | C-52-598-02-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Installation of Solar Panel Structural Supports | HE-EL-1010 | C-52-598-02-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-Lighting Layout | Installation of Solar Panel Structural Supports | HE-EL-1730 | C-52-598-02-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of Solar Panel Structural Supports | HE-IC-0710 | C-52-598-02-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Installation of Solar Panel Structural Supports | HE-IC-1430 | C-52-598-02-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Installation of Solar Panel Structural Supports | ML1032-B21 | C-52-598-02-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-F&G Cause and effect | Installation of Solar Panel Structural Supports | HE-HS-0350 | C-52-598-02-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Electrical Bulk material MTO | Installation of Solar Panel Structural Supports | HM-EL-0530 | C-52-598-02-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-Loop Diagrams | Installation of Solar Panel Structural Supports | HE-IC-0770 | C-52-598-02-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | CP Drilling & Earthing Drilling Subcontract Award | Installation of Solar Panel Structural Supports | HS-CN-0240 | C-52-598-02-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Installation of Solar Panel Structural Supports | HM-ME-1690 | C-52-598-02-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of Solar Panel Structural Supports | HE-IC-0650 | C-52-598-02-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Issue ICR-Instrument index -Update | Installation of Solar Panel Structural Supports | HE-IC-0490 | C-52-598-02-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-Earthing Layout | Installation of Solar Panel Structural Supports | HE-EL-1670 | C-52-598-02-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of Solar Panel Structural Supports | HM-EL-0380 | C-52-598-02-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-Instrument Index | Installation of Solar Panel Structural Supports | HE-IC-0530 | C-52-598-02-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.6.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Receipt at site and inspection of Solar PV system | Installation of Solar Panel Structural Supports | HM-ME-1090 | C-52-598-02-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of Solar Panel Structural Supports | HE-EL-1790 | C-52-598-02-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Issue ICR- Addendum to DGs | Installation of Solar Panel Structural Supports | HE-IC-0010 | C-52-598-02-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Obtain Company Approval-Data sheet for LV Distribution board | Installation of Solar Panel Structural Supports | HE-EL-0640 | C-52-598-02-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-Solar Panel System SLDs | Installation of Solar Panel Structural Supports | HE-EL-0350 | C-52-598-02-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-0280 | C-52-598-02-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Installation of Solar Panel Structural Supports | HM-ME-1590 | C-52-598-02-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | Installation of Solar Panel Structural Supports | HE-EL-0770 | C-52-598-02-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | 1st Instrumentation Bulk material MTO | Installation of Solar Panel Structural Supports | HM-IC-0040 | C-52-598-02-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of Solar Panel Structural Supports | HE-EL-0530 | C-52-598-02-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Installation of Solar Panel Structural Supports | HE-IC-2570 | C-52-598-02-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of Solar Panel Structural Supports | HM-EL-0080 | C-52-598-02-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Instrumentation Bulk material MTO | Installation of Solar Panel Structural Supports | HM-IC-0050 | C-52-598-02-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Receipt at site and inspection of Power Distribution Boards | Installation of Solar Panel Structural Supports | HM-ME-0890 | C-52-598-02-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-I/O list | Installation of Solar Panel Structural Supports | HE-IC-0590 | C-52-598-02-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Final Issue for Design/ Construction-Data Sheet for AC UPS | Installation of Solar Panel Structural Supports | HE-EL-1860 | C-52-598-02-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Issue ICR- P&ID's | Installation of Solar Panel Structural Supports | HE-PR-0110 | C-52-598-02-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Installation of Solar Panel Structural Supports | HM-ME-2330 | C-52-598-02-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Installation of Solar Panel Structural Supports | HM-ME-2350 | C-52-598-02-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-630 | C-52-598-02-EI-1210 | FS | Not Started | Not Started | 12
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-650 | C-52-598-02-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.3 Solar Power SystemCCOB552E65 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-690 | C-52-598-02-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Deep Earth Well Drilling | HE-IC-1550 | C-52-598-02-EI-1400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | 1st Electrical Bulk material MTO | Deep Earth Well Drilling | HM-EL-0520 | C-52-598-02-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Deep Earth Well Drilling | HE-EL-1010 | C-52-598-02-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-Lighting Layout | Deep Earth Well Drilling | HE-EL-1730 | C-52-598-02-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-Typical Installation Drawings | Deep Earth Well Drilling | HE-IC-0710 | C-52-598-02-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Deep Earth Well Drilling | HE-IC-1430 | C-52-598-02-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Deep Earth Well Drilling | ML1032-B21 | C-52-598-02-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-F&G Cause and effect | Deep Earth Well Drilling | HE-HS-0350 | C-52-598-02-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Electrical Bulk material MTO | Deep Earth Well Drilling | HM-EL-0530 | C-52-598-02-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-Loop Diagrams | Deep Earth Well Drilling | HE-IC-0770 | C-52-598-02-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | CP Drilling & Earthing Drilling Subcontract Award | Deep Earth Well Drilling | HS-CN-0240 | C-52-598-02-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1690 | C-52-598-02-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-Hook-Up Diagram | Deep Earth Well Drilling | HE-IC-0650 | C-52-598-02-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Issue ICR-Instrument index -Update | Deep Earth Well Drilling | HE-IC-0490 | C-52-598-02-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-Earthing Layout | Deep Earth Well Drilling | HE-EL-1670 | C-52-598-02-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Receipt at site and inspection of Earthing Material (Lot 1) | Deep Earth Well Drilling | HM-EL-0380 | C-52-598-02-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-Instrument Index | Deep Earth Well Drilling | HE-IC-0530 | C-52-598-02-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-Electrical Installation Drawings | Deep Earth Well Drilling | HE-EL-1790 | C-52-598-02-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Issue ICR- Addendum to DGs | Deep Earth Well Drilling | HE-IC-0010 | C-52-598-02-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Obtain Company Approval-Data sheet for LV Distribution board | Deep Earth Well Drilling | HE-EL-0640 | C-52-598-02-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-Solar Panel System SLDs | Deep Earth Well Drilling | HE-EL-0350 | C-52-598-02-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-0280 | C-52-598-02-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1590 | C-52-598-02-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | Deep Earth Well Drilling | HE-EL-0770 | C-52-598-02-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | 1st Instrumentation Bulk material MTO | Deep Earth Well Drilling | HM-IC-0040 | C-52-598-02-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-Electrical Equipment Layout | Deep Earth Well Drilling | HE-EL-0530 | C-52-598-02-EI-1400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Deep Earth Well Drilling | HE-IC-2570 | C-52-598-02-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Deep Earth Well Drilling | HM-EL-0080 | C-52-598-02-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Instrumentation Bulk material MTO | Deep Earth Well Drilling | HM-IC-0050 | C-52-598-02-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Receipt at site and inspection of Power Distribution Boards | Deep Earth Well Drilling | HM-ME-0890 | C-52-598-02-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-I/O list | Deep Earth Well Drilling | HE-IC-0590 | C-52-598-02-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Final Issue for Design/ Construction-Data Sheet for AC UPS | Deep Earth Well Drilling | HE-EL-1860 | C-52-598-02-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Issue ICR- P&ID's | Deep Earth Well Drilling | HE-PR-0110 | C-52-598-02-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Deep Earth Well Drilling | HM-ME-2330 | C-52-598-02-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-650 | C-52-598-02-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.2 Deep Earth WellCCOB552E53 | Receipt at site and inspection of Earthing Material (Lot 2) | Deep Earth Well Drilling | HM-EL-690 | C-52-598-02-EI-1400 | FS | Not Started | Not Started | 23
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | 1st Electrical Bulk material MTO | CP Cable Laying | HM-EL-0520 | C-52-598-02-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Instrument Trench Layout | CP Cable Laying | HE-IC-1010 | C-52-598-02-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Receipt at site and inspection of Power & Control Cables (Lot 1) | CP Cable Laying | HM-EL-0080 | C-52-598-02-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Cable Routing Layout | CP Cable Laying | HE-EL-1610 | C-52-598-02-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | CP Cable Laying | HE-IC-0950 | C-52-598-02-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Cable Sizing Calculation | CP Cable Laying | HE-EL-0470 | C-52-598-02-CA-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Data Sheet for LV cables | CP Cable Laying | HE-EL-0830 | C-52-598-02-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Cable Schedule | CP Cable Laying | HE-EL-0590 | C-52-598-02-CA-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | CP Cable Laying | HE-IC-0830 | C-52-598-02-CA-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Data Sheet for HV cables | CP Cable Laying | HE-EL-1950 | C-52-598-02-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Specification for RTU | CP Cable Laying | HE-IC-0230 | C-52-598-02-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Specification for Leak Detection System | CP Cable Laying | HE-IC-0290 | C-52-598-02-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-I/O list | CP Cable Laying | HE-IC-0590 | C-52-598-02-CA-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Re-Issue for Approval- I/O list -Update | CP Cable Laying | HE-IC-0570 | C-52-598-02-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Re-Issue for Approval- Specification for RTU | CP Cable Laying | HE-IC-0210 | C-52-598-02-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Re-Issue for Approval- Specification for Leak Detection System | CP Cable Laying | HE-IC-0270 | C-52-598-02-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Issue ICR- Instrument Cable Block Diagram | CP Cable Laying | HE-IC-0790 | C-52-598-02-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Issue ICR- Specification for Leak Detection System | CP Cable Laying | HE-IC-0250 | C-52-598-02-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Issue ICR- Specification for RTU | CP Cable Laying | HE-IC-0190 | C-52-598-02-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Receipt at site and inspection of Power & Control Cables (Lot 2) | CP Cable Laying | HM-EL-630 | C-52-598-02-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | 1st Electrical Bulk material MTO | Electrical & Earthing Cable Laying | HM-EL-0520 | C-52-598-02-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Instrument Trench Layout | Electrical & Earthing Cable Laying | HE-IC-1010 | C-52-598-02-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Electrical & Earthing Cable Laying | HM-EL-0080 | C-52-598-02-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Cable Routing Layout | Electrical & Earthing Cable Laying | HE-EL-1610 | C-52-598-02-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Electrical & Earthing Cable Laying | HE-IC-0950 | C-52-598-02-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Cable Sizing Calculation | Electrical & Earthing Cable Laying | HE-EL-0470 | C-52-598-02-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Data Sheet for LV cables | Electrical & Earthing Cable Laying | HE-EL-0830 | C-52-598-02-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Cable Schedule | Electrical & Earthing Cable Laying | HE-EL-0590 | C-52-598-02-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0830 | C-52-598-02-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Data Sheet for HV cables | Electrical & Earthing Cable Laying | HE-EL-1950 | C-52-598-02-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0230 | C-52-598-02-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0290 | C-52-598-02-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Final Issue for Design/ Construction-I/O list | Electrical & Earthing Cable Laying | HE-IC-0590 | C-52-598-02-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Re-Issue for Approval- I/O list -Update | Electrical & Earthing Cable Laying | HE-IC-0570 | C-52-598-02-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Re-Issue for Approval- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0210 | C-52-598-02-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Re-Issue for Approval- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0270 | C-52-598-02-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Issue ICR- Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0790 | C-52-598-02-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Issue ICR- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0250 | C-52-598-02-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Issue ICR- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0190 | C-52-598-02-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-630 | C-52-598-02-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | Installation of SDH Cabinet | HM-ME-1390 | C-52-598-02-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Installation of SDH Cabinet | HE-TL-0470 | C-52-598-02-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Installation of SDH Cabinet | HM-ME-1290 | C-52-598-02-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | FOC Splicing / Termination Subcontract Award | Installation of SDH Cabinet | HS-CN-0290 | C-52-598-02-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | Final Issue for Design/ Construction-Telecom Equipment Layout | Installation of SDH Cabinet | HE-TL-0770 | C-52-598-02-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | Final Issue for Design/ Construction-Telecom cable schedule | Installation of SDH Cabinet | HE-TL-0830 | C-52-598-02-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | 1st Telecom Bulk material MTO | Installation of SDH Cabinet | HM-TL-0040 | C-52-598-02-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Installation of SDH Cabinet | HE-TL-0710 | C-52-598-02-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Installation of SDH Cabinet | ML1033-B22 | C-52-598-02-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Installation of SDH Cabinet | HE-TL-0410 | C-52-598-02-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Installation of SDH Cabinet | HE-TL-0290 | C-52-598-02-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | Final Telecom Bulk material MTO | Installation of SDH Cabinet | HM-TL-0050 | C-52-598-02-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | Receipt at site and inspection of FOC Cables (Lot 1) | Installation of SDH Cabinet | HM-EL-0180 | C-52-598-02-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Installation of SDH Cabinet | HE-TL-0350 | C-52-598-02-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Installation of SDH Cabinet | HM-ME-2270 | C-52-598-02-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | Installation of SDH Cabinet | HM-ME-2290 | C-52-598-02-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.8.1 SDH CabinetCCOB552I31 | Receipt at site and inspection of FOC Cables (Lot 2) | Installation of SDH Cabinet | HM-EL-610 | C-52-598-02-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-52-598-01-CI-1000 | SS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-52-598-01-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-52-598-01-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Final Civil Bulk material MTO | Concrete Works for Equipment Foundations & Hard Stand Area | HM-CS-0050 | C-52-598-01-CI-1400 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-1310 | C-52-598-01-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.20 Solar panel Calculation & foundation details | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Final Issue for Design/ Construction-Solar panel foundation details | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-0890 | C-52-598-01-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Equipment Foundations & Hard Stand Area | ML1034-B25 | C-52-598-01-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | 1st Civil Bulk material MTO | Concrete Works for Equipment Foundations & Hard Stand Area | HM-CS-0040 | C-52-598-01-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-1190 | C-52-598-01-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Equipment Foundations & Hard Stand Area | HE-CS-0230 | C-52-598-01-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Final Civil Bulk material MTO | Concrete Works for Access Platform & Misc. Structural Foundations | HM-CS-0050 | C-52-598-01-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Access Platform & Misc. Structural Foundations | ML1034-B25 | C-52-598-01-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | 1st Civil Bulk material MTO | Concrete Works for Access Platform & Misc. Structural Foundations | HM-CS-0040 | C-52-598-01-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Access Platform & Misc. Structural Foundations | HE-CS-0230 | C-52-598-01-CI-1420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Final Issue for Design/ Construction-Typical Structural Steel and Foundation details for pipe support | Concrete Works for Access Platform & Misc. Structural Foundations | HE-CS-1370 | C-52-598-01-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.14.21.1.5 Trenching for CablesCCOB652C40 | Final Issue for Design/ Construction-Civil UG layout | Electrical & Earthing Cable Trenching | HE-CS-0530 | C-52-598-01-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.14.21.1.5 Trenching for CablesCCOB652C40 | Final Issue for Design/ Construction-Civil UG layout | Instrument & Telecom Cable Trenching | HE-CS-0530 | C-52-598-01-CI-1810 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.3.1.3.14.21.1.6 Pipe Supports Fabrication & InstallationCCOB652S52 | Final Issue for Design/ Construction-Misc. supports | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1490 | C-52-598-01-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.14.21.1.6 Pipe Supports Fabrication & InstallationCCOB652S52 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Pipe Supports | HS-CN-0690 | C-52-598-01-CI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.3.1.3.14.21.1.6 Pipe Supports Fabrication & InstallationCCOB652S52 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1430 | C-52-598-01-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.1.6 Pipe Supports Fabrication & InstallationCCOB652S52 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0120 | C-52-598-01-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.1.6 Pipe Supports Fabrication & InstallationCCOB652S52 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0110 | C-52-598-01-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.3.14.21.1.7 Fences & Gates ConstructionCCOB652C39 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Installation of Concrete Pillers for Boundary Wall | HE-CS-0350 | C-52-598-01-CI-2200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.14.21.1.7 Fences & Gates ConstructionCCOB652C39 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Installation of Concrete Pillers for Boundary Wall | HE-CS-0470 | C-52-598-01-CI-2200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.1.8 Fire Point SheltersCCOB652S54 | 1st Structural Bulk material MTO | Installation of Fire Point Shelters | HM-CS-0110 | C-52-598-01-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.1.9 Paving WorksCCOB652C42 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-52-598-01-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.3.14.21.1.9 Paving WorksCCOB652C42 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-52-598-01-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB652S56 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0110 | C-52-598-01-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.14.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB652S56 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Platforms & Crossovers | HS-CN-0690 | C-52-598-01-CI-3000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB652S56 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0120 | C-52-598-01-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB652S56 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HM-CS-0110 | C-52-598-01-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.14.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB652S56 | Fence Works Subcontract Award | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HS-CN-0690 | C-52-598-01-CI-3010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.1.11 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOB652S56 | Final Structural Bulk material MTO | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HM-CS-0120 | C-52-598-01-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB652M52 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | ML1015-B08 | C-52-598-01-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB652M52 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 1) | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | HM-ME-1990 | C-52-598-01-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.3.1 Mechanical Works and Equipment Installation (Fire Fighting Equipment)CCOB652M52 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 2) | Mechanical Works and Equipment Installation (Fire Fighting Equipment) | HM-ME-2370 | C-52-598-01-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.14.21.4.1 Piping Pre-FabricationCCOB652P052 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-52-598-01-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.4.1 Piping Pre-FabricationCCOB652P052 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-52-598-01-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.22 Plot Plan - Block Valve Station (7 nos) | P2543-R01-Oct24..4.3.1.3.14.21.4.1 Piping Pre-FabricationCCOB652P052 | Final Issue for Design/ Construction-Plot Plan - Block Valve Station | Piping Pre-Fabrication | HE-PI-0580 | C-52-598-01-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.28 Piping GA - Block valve Station (591-BVS-01 to 06) on 52" Pipeline | P2543-R01-Oct24..4.3.1.3.14.21.4.1 Piping Pre-FabricationCCOB652P052 | Final Issue for Design/ Construction-Piping GA for 591-BVS-01 to 06 | Piping Pre-Fabrication | HE-PI-0880 | C-52-598-01-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.4.1 Piping Pre-FabricationCCOB652P052 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Pre-Fabrication | ML1179-B11 | C-52-598-01-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.14.21.4.1 Piping Pre-FabricationCCOB652P052 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-52-598-01-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.14.21.4.1 Piping Pre-FabricationCCOB652P052 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Pre-Fabrication | HE-PR-0290 | C-52-598-01-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.4.1 Piping Pre-FabricationCCOB652P052 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-52-598-01-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.14.21.4.1 Piping Pre-FabricationCCOB652P052 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Pre-Fabrication | HE-PR-0890 | C-52-598-01-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.14.21.4.1 Piping Pre-FabricationCCOB652P052 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-52-598-01-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Project Kick off Meeting | Piping Erection | ML1002 | C-52-598-01-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Erection | ML1219-B19 | C-52-598-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Erection | HM-PL-0220 | C-52-598-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Erection | HM-PL-0740 | C-52-598-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Erection | ML1179-B11 | C-52-598-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Erection | HM-PL-0630 | C-52-598-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Piping MTO - Final | Piping Erection | HE-PI-1300 | C-52-598-01-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Erection | HE-PR-0290 | C-52-598-01-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | 1st Piping Bulk material MTO | Piping Erection | HM-PI-0040 | C-52-598-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Final Piping Bulk material MTO | Piping Erection | HM-PI-0050 | C-52-598-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Receive at Site - Manual Valves | Piping Erection | ML1539-D21 | C-52-598-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Erection | HE-PR-0890 | C-52-598-01-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Erection | HM-PL-0640 | C-52-598-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Final Issue for Design/ Construction-Piping Isometrics | Piping Erection | HE-PI-1240 | C-52-598-01-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Erection | HM-PL-1510 | C-52-598-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.2 ErectionCCOB652P062 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Erection | HM-PL-1570 | C-52-598-01-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.14.21.4.3 Field Joint Welding & NDTCCOB652P072 | Piping MTO - Final | Field Joint Welding (Including Isolation Joint) | HE-PI-1300 | C-52-598-01-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.14.21.4.3 Field Joint Welding & NDTCCOB652P072 | Project Kick off Meeting | Field Joint Welding (Including Isolation Joint) | ML1002 | C-52-598-01-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.4.4 HydrotestingCCOB652P082 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Hydrotesting | ML1219-B19 | C-52-598-01-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.4 HydrotestingCCOB652P082 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Hydrotesting | HM-PL-0220 | C-52-598-01-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.4.4 HydrotestingCCOB652P082 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Hydrotesting | ML1179-B11 | C-52-598-01-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.14.21.4.4 HydrotestingCCOB652P082 | Piping MTO - Final | Hydrotesting | HE-PI-1300 | C-52-598-01-PI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.14.21.4.4 HydrotestingCCOB652P082 | Final Issue for Design/ Construction-Tie-In Schedule | Hydrotesting | HE-PR-0290 | C-52-598-01-PI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.4.4 HydrotestingCCOB652P082 | 1st Piping Bulk material MTO | Hydrotesting | HM-PI-0040 | C-52-598-01-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.4.4 HydrotestingCCOB652P082 | Final Piping Bulk material MTO | Hydrotesting | HM-PI-0050 | C-52-598-01-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.14.21.4.4 HydrotestingCCOB652P082 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Hydrotesting | HE-PR-0890 | C-52-598-01-PI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.14.21.4.4 HydrotestingCCOB652P082 | Final Issue for Design/ Construction-Piping Isometrics | Hydrotesting | HE-PI-1240 | C-52-598-01-PI-1600 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Piping MTO - Final | Installation of Valves & GOV | HE-PI-1300 | C-52-598-01-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Project Kick off Meeting | Installation of Valves & GOV | ML1002 | C-52-598-01-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Installation of Valves & GOV | ML1219-B19 | C-52-598-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Installation of Valves & GOV | HM-PL-0220 | C-52-598-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Receipt at site and inspection of Isolating Joints (Lot 1) | Installation of Valves & GOV | HM-PL-0740 | C-52-598-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Installation of Valves & GOV | ML1179-B11 | C-52-598-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Installation of Valves & GOV | HM-PL-0630 | C-52-598-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Final Issue for Design/ Construction-Tie-In Schedule | Installation of Valves & GOV | HE-PR-0290 | C-52-598-01-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Receive at Site - Valves – Globe/Check/Plug | Installation of Valves & GOV | ML1529-D20 | C-52-598-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Receive at Site - Manual Valves | Installation of Valves & GOV | ML1539-D21 | C-52-598-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Installation of Valves & GOV | HE-PR-0890 | C-52-598-01-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Installation of Valves & GOV | HM-PL-0640 | C-52-598-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Final Issue for Design/ Construction-Piping Isometrics | Installation of Valves & GOV | HE-PI-1240 | C-52-598-01-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Receipt at site and inspection of Isolating Joints (Lot 2) | Installation of Valves & GOV | HM-PL-1510 | C-52-598-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Installation of Valves & GOV | HM-PL-1570 | C-52-598-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Project Kick off Meeting | Final Bolt Torquing/ Re-Instatement | ML1002 | C-52-598-01-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Final Bolt Torquing/ Re-Instatement | ML1219-B19 | C-52-598-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0220 | C-52-598-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Receipt at site and inspection of Isolating Joints (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0740 | C-52-598-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Final Bolt Torquing/ Re-Instatement | ML1179-B11 | C-52-598-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0630 | C-52-598-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Piping MTO - Final | Final Bolt Torquing/ Re-Instatement | HE-PI-1300 | C-52-598-01-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Final Issue for Design/ Construction-Tie-In Schedule | Final Bolt Torquing/ Re-Instatement | HE-PR-0290 | C-52-598-01-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | 1st Piping Bulk material MTO | Final Bolt Torquing/ Re-Instatement | HM-PI-0040 | C-52-598-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Final Piping Bulk material MTO | Final Bolt Torquing/ Re-Instatement | HM-PI-0050 | C-52-598-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Receive at Site - Valves – Globe/Check/Plug | Final Bolt Torquing/ Re-Instatement | ML1529-D20 | C-52-598-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Receive at Site - Manual Valves | Final Bolt Torquing/ Re-Instatement | ML1539-D21 | C-52-598-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Final Bolt Torquing/ Re-Instatement | HE-PR-0890 | C-52-598-01-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0640 | C-52-598-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Final Issue for Design/ Construction-Piping Isometrics | Final Bolt Torquing/ Re-Instatement | HE-PI-1240 | C-52-598-01-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Receipt at site and inspection of Isolating Joints (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1510 | C-52-598-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.6 Final Bolt Torquing/ Re-InstatementCCOB652P102 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1570 | C-52-598-01-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.14.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB652E51 | Receive at Site - Passive Cooling Shelter | Installation of Passive Cooling Shelter | ML1054-D09 | C-52-598-01-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.5.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB652E51 | Receipt at site and inspection of Active/ Passive Cooled Shelter | Installation of Passive Cooling Shelter | HM-ME-1190 | C-52-598-01-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.14.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB652E51 | Receive at Site - Passive Cooling Shelter | Installation of Passive Cooling Shelter | ML1054-D09 | C-52-598-01-EI-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Installation of Solar Panel Structural Supports | HM-ME-1590 | C-52-598-01-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of Solar Panel Structural Supports | HE-IC-1550 | C-52-598-01-EI-1210 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Receive at Site - Solar Power System | Installation of Solar Panel Structural Supports | ML1429-D17 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-Loop Diagrams | Installation of Solar Panel Structural Supports | HE-IC-0770 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Instrumentation Bulk material MTO | Installation of Solar Panel Structural Supports | HM-IC-0050 | C-52-598-01-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of Solar Panel Structural Supports | HM-EL-0380 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Obtain Company Approval-Data sheet for LV Distribution board | Installation of Solar Panel Structural Supports | HE-EL-0640 | C-52-598-01-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | Installation of Solar Panel Structural Supports | HE-EL-0770 | C-52-598-01-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Installation of Solar Panel Structural Supports | ML1032-B21 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Installation of Solar Panel Structural Supports | HM-ME-1690 | C-52-598-01-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Electrical Bulk material MTO | Installation of Solar Panel Structural Supports | HM-EL-0530 | C-52-598-01-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.6.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Receipt at site and inspection of Solar PV system | Installation of Solar Panel Structural Supports | HM-ME-1090 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Installation of Solar Panel Structural Supports | HE-IC-1430 | C-52-598-01-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-Instrument Index | Installation of Solar Panel Structural Supports | HE-IC-0530 | C-52-598-01-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | 1st Instrumentation Bulk material MTO | Installation of Solar Panel Structural Supports | HM-IC-0040 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of Solar Panel Structural Supports | HM-EL-0080 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Installation of Solar Panel Structural Supports | HE-EL-1010 | C-52-598-01-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-Lighting Layout | Installation of Solar Panel Structural Supports | HE-EL-1730 | C-52-598-01-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of Solar Panel Structural Supports | HE-IC-0710 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-Solar Panel System SLDs | Installation of Solar Panel Structural Supports | HE-EL-0350 | C-52-598-01-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of Solar Panel Structural Supports | HE-EL-0530 | C-52-598-01-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Issue ICR-Instrument index -Update | Installation of Solar Panel Structural Supports | HE-IC-0490 | C-52-598-01-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of Solar Panel Structural Supports | HE-EL-1790 | C-52-598-01-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-F&G Cause and effect | Installation of Solar Panel Structural Supports | HE-HS-0350 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Receipt at site and inspection of Power Distribution Boards | Installation of Solar Panel Structural Supports | HM-ME-0890 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of Solar Panel Structural Supports | HE-IC-0650 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-I/O list | Installation of Solar Panel Structural Supports | HE-IC-0590 | C-52-598-01-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | CP Drilling & Earthing Drilling Subcontract Award | Installation of Solar Panel Structural Supports | HS-CN-0240 | C-52-598-01-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-0280 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Issue ICR- Addendum to DGs | Installation of Solar Panel Structural Supports | HE-IC-0010 | C-52-598-01-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-Earthing Layout | Installation of Solar Panel Structural Supports | HE-EL-1670 | C-52-598-01-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Installation of Solar Panel Structural Supports | HE-IC-2570 | C-52-598-01-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Receive at Site - F & G System | Installation of Solar Panel Structural Supports | ML2089-D16 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | 1st Electrical Bulk material MTO | Installation of Solar Panel Structural Supports | HM-EL-0520 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Final Issue for Design/ Construction-Data Sheet for AC UPS | Installation of Solar Panel Structural Supports | HE-EL-1860 | C-52-598-01-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Issue ICR- P&ID's | Installation of Solar Panel Structural Supports | HE-PR-0110 | C-52-598-01-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Installation of Solar Panel Structural Supports | HM-ME-2330 | C-52-598-01-EI-1210 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-630 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-650 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.2 Solar Power SystemCCOB652E65 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of Solar Panel Structural Supports | HM-EL-690 | C-52-598-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1590 | C-52-598-01-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Deep Earth Well Drilling | HE-IC-1550 | C-52-598-01-EI-1400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-Loop Diagrams | Deep Earth Well Drilling | HE-IC-0770 | C-52-598-01-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Instrumentation Bulk material MTO | Deep Earth Well Drilling | HM-IC-0050 | C-52-598-01-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Receipt at site and inspection of Earthing Material (Lot 1) | Deep Earth Well Drilling | HM-EL-0380 | C-52-598-01-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Obtain Company Approval-Data sheet for LV Distribution board | Deep Earth Well Drilling | HE-EL-0640 | C-52-598-01-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.1 Data Sheet for Solar Power System | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-Data Sheet for Solar Panel System | Deep Earth Well Drilling | HE-EL-0770 | C-52-598-01-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Deep Earth Well Drilling | ML1032-B21 | C-52-598-01-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1690 | C-52-598-01-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Electrical Bulk material MTO | Deep Earth Well Drilling | HM-EL-0530 | C-52-598-01-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Deep Earth Well Drilling | HE-IC-1430 | C-52-598-01-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-Instrument Index | Deep Earth Well Drilling | HE-IC-0530 | C-52-598-01-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | 1st Instrumentation Bulk material MTO | Deep Earth Well Drilling | HM-IC-0040 | C-52-598-01-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Deep Earth Well Drilling | HM-EL-0080 | C-52-598-01-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Deep Earth Well Drilling | HE-EL-1010 | C-52-598-01-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-Lighting Layout | Deep Earth Well Drilling | HE-EL-1730 | C-52-598-01-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-Typical Installation Drawings | Deep Earth Well Drilling | HE-IC-0710 | C-52-598-01-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.14 Solar Panel System SLDs | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-Solar Panel System SLDs | Deep Earth Well Drilling | HE-EL-0350 | C-52-598-01-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-Electrical Equipment Layout | Deep Earth Well Drilling | HE-EL-0530 | C-52-598-01-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Issue ICR-Instrument index -Update | Deep Earth Well Drilling | HE-IC-0490 | C-52-598-01-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-Electrical Installation Drawings | Deep Earth Well Drilling | HE-EL-1790 | C-52-598-01-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-F&G Cause and effect | Deep Earth Well Drilling | HE-HS-0350 | C-52-598-01-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Receipt at site and inspection of Power Distribution Boards | Deep Earth Well Drilling | HM-ME-0890 | C-52-598-01-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-Hook-Up Diagram | Deep Earth Well Drilling | HE-IC-0650 | C-52-598-01-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-I/O list | Deep Earth Well Drilling | HE-IC-0590 | C-52-598-01-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | CP Drilling & Earthing Drilling Subcontract Award | Deep Earth Well Drilling | HS-CN-0240 | C-52-598-01-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-0280 | C-52-598-01-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Issue ICR- Addendum to DGs | Deep Earth Well Drilling | HE-IC-0010 | C-52-598-01-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-Earthing Layout | Deep Earth Well Drilling | HE-EL-1670 | C-52-598-01-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Deep Earth Well Drilling | HE-IC-2570 | C-52-598-01-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Receive at Site - F & G System | Deep Earth Well Drilling | ML2089-D16 | C-52-598-01-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | 1st Electrical Bulk material MTO | Deep Earth Well Drilling | HM-EL-0520 | C-52-598-01-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.2 Data Sheet for AC UPS | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Final Issue for Design/ Construction-Data Sheet for AC UPS | Deep Earth Well Drilling | HE-EL-1860 | C-52-598-01-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Issue ICR- P&ID's | Deep Earth Well Drilling | HE-PR-0110 | C-52-598-01-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Deep Earth Well Drilling | HM-ME-2330 | C-52-598-01-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-650 | C-52-598-01-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.3 Deep Earth WellCCOB652E53 | Receipt at site and inspection of Earthing Material (Lot 2) | Deep Earth Well Drilling | HM-EL-690 | C-52-598-01-EI-1400 | FS | Not Started | Not Started | 46
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | 1st Electrical Bulk material MTO | Electrical & Earthing Cable Laying | HM-EL-0520 | C-52-598-01-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Electrical & Earthing Cable Laying | HE-IC-0950 | C-52-598-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Final Issue for Design/ Construction-Cable Schedule | Electrical & Earthing Cable Laying | HE-EL-0590 | C-52-598-01-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Electrical & Earthing Cable Laying | HM-EL-0080 | C-52-598-01-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Final Issue for Design/ Construction-Instrument Trench Layout | Electrical & Earthing Cable Laying | HE-IC-1010 | C-52-598-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0830 | C-52-598-01-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Final Issue for Design/ Construction-Cable Routing Layout | Electrical & Earthing Cable Laying | HE-EL-1610 | C-52-598-01-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Final Issue for Design/ Construction-Data Sheet for LV cables | Electrical & Earthing Cable Laying | HE-EL-0830 | C-52-598-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Final Issue for Design/ Construction-Cable Sizing Calculation | Electrical & Earthing Cable Laying | HE-EL-0470 | C-52-598-01-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Final Issue for Design/ Construction-Data Sheet for HV cables | Electrical & Earthing Cable Laying | HE-EL-1950 | C-52-598-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Final Issue for Design/ Construction-Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0230 | C-52-598-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Final Issue for Design/ Construction-Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0290 | C-52-598-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Final Issue for Design/ Construction-I/O list | Electrical & Earthing Cable Laying | HE-IC-0590 | C-52-598-01-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Re-Issue for Approval- I/O list -Update | Electrical & Earthing Cable Laying | HE-IC-0570 | C-52-598-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Re-Issue for Approval- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0210 | C-52-598-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Re-Issue for Approval- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0270 | C-52-598-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Issue ICR- Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0790 | C-52-598-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Issue ICR- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0250 | C-52-598-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Issue ICR- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0190 | C-52-598-01-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.6 E&I Cable Laying, Glanding & TerminationCCOB652E55 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-630 | C-52-598-01-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.14.21.7.1 CP Anode Bed Installation (subcontract)CCOB652E30 | CP Drilling & Earthing Drilling Subcontract Award | CP Cable Laying | HS-CN-0240 | C-52-598-01-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.7.1 CP Anode Bed Installation (subcontract)CCOB652E30 | Receipt at site and inspection of CP System - Permanent Material | CP Cable Laying | HM-PL-0430 | C-52-598-01-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | Final Issue for Design/ Construction-Telecom Equipment Layout | Installation of SDH Cabinet | HE-TL-0770 | C-52-598-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Installation of SDH Cabinet | HE-TL-0410 | C-52-598-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | Receive at Site - E&I Equipment's (IDS & PIDS System) | Installation of SDH Cabinet | ML1479-D15 | C-52-598-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Installation of SDH Cabinet | HE-TL-0470 | C-52-598-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | FOC Splicing / Termination Subcontract Award | Installation of SDH Cabinet | HS-CN-0290 | C-52-598-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Installation of SDH Cabinet | HE-TL-0350 | C-52-598-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | Final Issue for Design/ Construction-Telecom cable schedule | Installation of SDH Cabinet | HE-TL-0830 | C-52-598-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | Installation of SDH Cabinet | HM-ME-1390 | C-52-598-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Installation of SDH Cabinet | HE-TL-0710 | C-52-598-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | Final Telecom Bulk material MTO | Installation of SDH Cabinet | HM-TL-0050 | C-52-598-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | 1st Telecom Bulk material MTO | Installation of SDH Cabinet | HM-TL-0040 | C-52-598-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | Receive at Site - E&I Equipment's (CCTV System) | Installation of SDH Cabinet | ML1056-D14 | C-52-598-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Installation of SDH Cabinet | ML1033-B22 | C-52-598-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Installation of SDH Cabinet | HM-ME-1290 | C-52-598-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Installation of SDH Cabinet | HE-TL-0290 | C-52-598-01-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Installation of SDH Cabinet | HM-ME-2270 | C-52-598-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.8.1 SDH CabinetCCOB652I31 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | Installation of SDH Cabinet | HM-ME-2290 | C-52-598-01-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-52-PR-839-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-52-PR-839-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Site Survey, Preparation & Grading Works | HE-CS-0470 | C-52-PR-839-CI-1000 | FF | In Progress | Not Started | 10
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-52-PR-839-CI-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | Issue Civil / Structural Drawings for Launcher/ Receiver facilities | Site Survey, Preparation & Grading Works | ML1199-B24 | C-52-PR-839-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Site Survey, Preparation & Grading Works | CTF-1000 | C-52-PR-839-CI-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | NOC's / Approval /Survey | Site Survey, Preparation & Grading Works | CTF-1010 | C-52-PR-839-CI-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Concrete Works for Equipment Foundations | HE-CS-1310 | C-52-PR-839-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | 1st Civil Bulk material MTO | Concrete Works for Equipment Foundations | HM-CS-0040 | C-52-PR-839-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Final Issue for Design/ Construction-Typical Detailed Drawing - Jib Crane Foundation | Concrete Works for Equipment Foundations | HE-CS-1070 | C-52-PR-839-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Concrete Works for Equipment Foundations | HE-CS-1190 | C-52-PR-839-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Equipment Foundations | HE-CS-0230 | C-52-PR-839-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Final Civil Bulk material MTO | Concrete Works for Equipment Foundations | HM-CS-0050 | C-52-PR-839-CI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Concrete Works for Equipment Foundations | HE-CS-0650 | C-52-PR-839-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | Concrete Works for Equipment Foundations | ML1209-B27 | C-52-PR-839-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | 1st Civil Bulk material MTO | Concrete Works for Field Instrument, JBs & Light Pole Foundations | HM-CS-0040 | C-52-PR-839-CI-1410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Field Instrument, JBs & Light Pole Foundations | HE-CS-0230 | C-52-PR-839-CI-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Final Civil Bulk material MTO | Concrete Works for Field Instrument, JBs & Light Pole Foundations | HM-CS-0050 | C-52-PR-839-CI-1410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Concrete Works for Field Instrument, JBs & Light Pole Foundations | HE-CS-0650 | C-52-PR-839-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | Concrete Works for Field Instrument, JBs & Light Pole Foundations | ML1209-B27 | C-52-PR-839-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | 1st Civil Bulk material MTO | Concrete Works for Access Platforms & Misc. Structural Foundations | HM-CS-0040 | C-52-PR-839-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.40 Typical Structural Steel and Foundation details for pipe support | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Final Issue for Design/ Construction-Typical Structural Steel and Foundation details for pipe support | Concrete Works for Access Platforms & Misc. Structural Foundations | HE-CS-1370 | C-52-PR-839-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Access Platforms & Misc. Structural Foundations | HE-CS-0230 | C-52-PR-839-CI-1420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Final Civil Bulk material MTO | Concrete Works for Access Platforms & Misc. Structural Foundations | HM-CS-0050 | C-52-PR-839-CI-1420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Concrete Works for Access Platforms & Misc. Structural Foundations | HE-CS-0650 | C-52-PR-839-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | Concrete Works for Access Platforms & Misc. Structural Foundations | ML1209-B27 | C-52-PR-839-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.4 Concrete Works (Impact wall)CCOSWCS302.3 | 1st Civil Bulk material MTO | Concrete Works for Impact Wall | HM-CS-0040 | C-52-PR-839-CI-1500 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.4.1.22.1.4 Concrete Works (Impact wall)CCOSWCS302.3 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Impact Wall | HE-CS-0230 | C-52-PR-839-CI-1500 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.4 Concrete Works (Impact wall)CCOSWCS302.3 | Final Civil Bulk material MTO | Concrete Works for Impact Wall | HM-CS-0050 | C-52-PR-839-CI-1500 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..4.3.1.3.4.1.22.1.4 Concrete Works (Impact wall)CCOSWCS302.3 | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Concrete Works for Impact Wall | HE-CS-0650 | C-52-PR-839-CI-1500 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.1.4 Concrete Works (Impact wall)CCOSWCS302.3 | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | Concrete Works for Impact Wall | ML1209-B27 | C-52-PR-839-CI-1500 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.5 Concrete Works (Foundations for Pipe Supports)CCOSWCS302.2 | 1st Civil Bulk material MTO | Concrete Works for Pipe Support Foundations | HM-CS-0040 | C-52-PR-839-CI-1600 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | P2543-R01-Oct24..4.3.1.3.4.1.22.1.5 Concrete Works (Foundations for Pipe Supports)CCOSWCS302.2 | Final Issue for Design/ Construction-Design Calculation for Typical Pipe supports | Concrete Works for Pipe Support Foundations | HE-CS-1130 | C-52-PR-839-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.4.1.22.1.5 Concrete Works (Foundations for Pipe Supports)CCOSWCS302.2 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Pipe Support Foundations | HE-CS-0230 | C-52-PR-839-CI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.5 Concrete Works (Foundations for Pipe Supports)CCOSWCS302.2 | Final Civil Bulk material MTO | Concrete Works for Pipe Support Foundations | HM-CS-0050 | C-52-PR-839-CI-1600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..4.3.1.3.4.1.22.1.5 Concrete Works (Foundations for Pipe Supports)CCOSWCS302.2 | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Concrete Works for Pipe Support Foundations | HE-CS-0650 | C-52-PR-839-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.1.5 Concrete Works (Foundations for Pipe Supports)CCOSWCS302.2 | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | Concrete Works for Pipe Support Foundations | ML1209-B27 | C-52-PR-839-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.4.1.22.1.6 Trenching for CablesCCOSWCS311 | Final Issue for Design/ Construction-Civil UG layout | Electrical & Earthing Cable Trenching | HE-CS-0530 | C-52-PR-839-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.4.1.22.1.6 Trenching for CablesCCOSWCS311 | Final Issue for Design/ Construction-Civil UG layout | Instrument & Telecom Cable Trenching | HE-CS-0530 | C-52-PR-839-CI-1810 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.7 Pipe Supports Fabrication & InstallationCCOSWSS500 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0120 | C-52-PR-839-CI-2000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.3.1.3.4.1.22.1.7 Pipe Supports Fabrication & InstallationCCOSWSS500 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1430 | C-52-PR-839-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.3.1.3.4.1.22.1.7 Pipe Supports Fabrication & InstallationCCOSWSS500 | Final Issue for Design/ Construction-Misc. supports | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1490 | C-52-PR-839-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.4.1.22.1.7 Pipe Supports Fabrication & InstallationCCOSWSS500 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Pipe Supports | HS-CN-0690 | C-52-PR-839-CI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.7 Pipe Supports Fabrication & InstallationCCOSWSS500 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0110 | C-52-PR-839-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS505 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0110 | C-52-PR-839-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.4.1.22.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS505 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Platforms & Crossovers | HS-CN-0690 | C-52-PR-839-CI-3000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS505 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HM-CS-0110 | C-52-PR-839-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.4.1.22.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS505 | Fence Works Subcontract Award | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | HS-CN-0690 | C-52-PR-839-CI-3010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.9 Thrust Anchor BlocklCCOSWCS317 | Receipt at site and inspection of Anchor Flanges (Lot 2) | Concrete Works for Thrust Anchor Block | HM-PL-1550 | C-52-PR-839-CI-1510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.1.10 Earth Works for Paving CCOSWCS315.1 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Earth Works for Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-52-PR-839-CI-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.3.4.1.22.1.12 Fences & Gates ConstructionCCOSWCS310 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Fences & Gates Construction | HE-CS-0350 | C-52-PR-839-CI-2220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.4.1.22.1.12 Fences & Gates ConstructionCCOSWCS310 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Fences & Gates Construction | HE-CS-0470 | C-52-PR-839-CI-2220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.3.4.1.22.1.13 Paving interlock & barrier installationCCOSWCS315.2 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-52-PR-839-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.1.13 Paving interlock & barrier installationCCOSWCS315.2 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-52-PR-839-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.14 Fire Point SheltersCCOSWSS504 | 1st Structural Bulk material MTO | Fire Point Shelters | HM-CS-0110 | C-52-PR-839-CI-2400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.1.15 FinishingCCOSWMC513 | 1st Structural Bulk material MTO | Finishing | HM-CS-0110 | C-52-PR-839-CI-3200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.11.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.3.1 Sales Gas FilterCCOSWME506 | Receipt at site and inspection of Filter Package | Installation of Sales Gas Filter (839-F-104A) | HM-ME-0380 | C-52-PR-839-ME-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.33 Filter Foundation GA and Details | P2543-R01-Oct24..4.3.1.3.4.1.22.3.1 Sales Gas FilterCCOSWME506 | Final Issue for Design/ Construction-FILTER FOUNDATION GA AND DETAILS | Installation of Sales Gas Filter (839-F-104A) | HE-CS-0950 | C-52-PR-839-ME-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.3.1 Sales Gas FilterCCOSWME506 | Issue Civil / Structural Drawings for Gas Filters, Pressure Reducing Skids and Metering Skids facilities - IFC. | Installation of Sales Gas Filter (839-F-104A) | ML1036-B23 | C-52-PR-839-ME-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.11.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.3.1 Sales Gas FilterCCOSWME506 | Receipt at site and inspection of Filter Package | Installation of Sales Gas Filter (839-F-104A) | HM-ME-0380 | C-52-PR-839-ME-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.3.2 Installation of Pig Receiver (839-V-101)CCOSWME508 | Receipt at site and inspection of Pig Launchers & Receivers (52" Line) | Installation of Pig Receiver (839-V-101) 52" | HM-ME-0480 | C-52-PR-839-ME-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.3.2 Installation of Pig Receiver (839-V-101)CCOSWME508 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Installation of Pig Receiver (839-V-101) 52" | ML1015-B08 | C-52-PR-839-ME-1100 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.4.1.22.3.2 Installation of Pig Receiver (839-V-101)CCOSWME508 | Receive at Site - Pig Launcher & Receiver | Installation of Pig Receiver (839-V-101) 52" | ML1519-D04 | C-52-PR-839-ME-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.3.3 Installation of Pig Signaler (839-V-101)CCOSWME509 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Installation of Pig Signaler (839-V-101) | ML1015-B08 | C-52-PR-839-ME-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.3.3 Installation of Pig Signaler (839-V-101)CCOSWME509 | Receipt at site and inspection of Pigging & Split Tee (Lot 1) | Installation of Pig Signaler (839-V-101) | HM-PL-0840 | C-52-PR-839-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.3.3 Installation of Pig Signaler (839-V-101)CCOSWME509 | Receipt at site and inspection of Pig Signaler (Lot 1) | Installation of Pig Signaler (839-V-101) | HM-PL-0530 | C-52-PR-839-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.3.3 Installation of Pig Signaler (839-V-101)CCOSWME509 | Receipt at site and inspection of Pig Signaler (Lot 2) | Installation of Pig Signaler (839-V-101) | HM-PL-1490 | C-52-PR-839-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.3.3 Installation of Pig Signaler (839-V-101)CCOSWME509 | Receipt at site and inspection of Pigging & Split Tee (Lot 2) | Installation of Pig Signaler (839-V-101) | HM-PL-1530 | C-52-PR-839-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.3.4 Installation of Fire Fighting & Safety EquipmentCCOSWME510 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 1) | Installation of Fire Fighting & Safety Equipment | HM-ME-1990 | C-52-PR-839-ME-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.3.4 Installation of Fire Fighting & Safety EquipmentCCOSWME510 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Installation of Fire Fighting & Safety Equipment | ML1015-B08 | C-52-PR-839-ME-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.3.4 Installation of Fire Fighting & Safety EquipmentCCOSWME510 | Receipt at site and inspection of Fire Fighting & Safety Equipment (Lot 2) | Installation of Fire Fighting & Safety Equipment | HM-ME-2370 | C-52-PR-839-ME-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | Final Issue for Design/ Construction - Pressure Reduction Skid and Leak Detection Drawings | Installation of Pressure Reducing Skid (839-ME-106) | HE-CS-0770 | C-52-PR-839-ME-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | Installation of Pressure Reducing Skid (839-ME-106) | HE-IC-0110 | C-52-PR-839-ME-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.22.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | Receipt at site and inspection of Custody Metering Skid | Installation of Pressure Reducing Skid (839-ME-106) | HM-ME-0080 | C-52-PR-839-ME-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.21.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | Receipt at site and inspection of Pressure Reduction Skid | Installation of Pressure Reducing Skid (839-ME-106) | HM-ME-0180 | C-52-PR-839-ME-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | Receive at Site - Sales Gas Metering Skids | Installation of Pressure Reducing Skid (839-ME-106) | ML1419-D08 | C-52-PR-839-ME-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | Issue Civil / Structural Drawings for Gas Filters, Pressure Reducing Skids and Metering Skids facilities - IFC. | Installation of Pressure Reducing Skid (839-ME-106) | ML1036-B23 | C-52-PR-839-ME-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.23 Pressure Reduction Skid & Leak Detection System Foundation | P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | Final Issue for Design/ Construction - Pressure Reduction Skid and Leak Detection Drawings | Installation of Sales Gas Custody Transfer Metering Skid Including Control Valve (839-ME-105) | HE-CS-0770 | C-52-PR-839-ME-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | Installation of Sales Gas Custody Transfer Metering Skid Including Control Valve (839-ME-105) | HE-IC-0110 | C-52-PR-839-ME-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.22.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | Receipt at site and inspection of Custody Metering Skid | Installation of Sales Gas Custody Transfer Metering Skid Including Control Valve (839-ME-105) | HM-ME-0080 | C-52-PR-839-ME-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.21.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | Receipt at site and inspection of Pressure Reduction Skid | Installation of Sales Gas Custody Transfer Metering Skid Including Control Valve (839-ME-105) | HM-ME-0180 | C-52-PR-839-ME-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | Receive at Site - Sales Gas Metering Skids | Installation of Sales Gas Custody Transfer Metering Skid Including Control Valve (839-ME-105) | ML1419-D08 | C-52-PR-839-ME-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | Issue Civil / Structural Drawings for Gas Filters, Pressure Reducing Skids and Metering Skids facilities - IFC. | Installation of Sales Gas Custody Transfer Metering Skid Including Control Valve (839-ME-105) | ML1036-B23 | C-52-PR-839-ME-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.25 Gas Metering Skid Foundation Drawings | P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | Final Issue for Design/ Construction-Gas metering skid foundation drawings | Installation of Sales Gas Custody Transfer Metering Skid Including Control Valve (839-ME-105) | HE-CS-0830 | C-52-PR-839-ME-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-52-PR-839-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Pre-Fabrication | HM-PL-0640 | C-52-PR-839-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-52-PR-839-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | NDT / PWHT Subcontract Award | Piping Pre-Fabrication | HS-CN-0190 | C-52-PR-839-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Pre-Fabrication | HM-PL-0630 | C-52-PR-839-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-52-PR-839-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-52-PR-839-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Pre-Fabrication | ML1179-B11 | C-52-PR-839-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Pre-Fabrication | HM-PL-0220 | C-52-PR-839-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Piping Pre-Fabrication | HE-PI-0440 | C-52-PR-839-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Pre-Fabrication | HM-PL-0740 | C-52-PR-839-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Pre-Fabrication | HE-PR-0890 | C-52-PR-839-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-52-PR-839-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | Final Issue for Design/ Construction-Piping GA- 52" Pipeline SWEIHAN CRS | Piping Pre-Fabrication | HE-PI-0700 | C-52-PR-839-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Pre-Fabrication | HE-PR-0290 | C-52-PR-839-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Pre-Fabrication | HM-PL-1510 | C-52-PR-839-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.1 Piping Works -FabricationCCOSWPI503.1 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Pre-Fabrication | HM-PL-1570 | C-52-PR-839-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | Project Kick off Meeting | NDT & Coating for Field Joint Weld | ML1002 | C-52-PR-839-PI-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | NDT & Coating for Field Joint Weld | HM-PL-0640 | C-52-PR-839-PI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | Final Issue for Design/ Construction-Piping Isometrics | NDT & Coating for Field Joint Weld | HE-PI-1240 | C-52-PR-839-PI-1410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | NDT / PWHT Subcontract Award | NDT & Coating for Field Joint Weld | HS-CN-0190 | C-52-PR-839-PI-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | 1st Piping Bulk material MTO | NDT & Coating for Field Joint Weld | HM-PI-0040 | C-52-PR-839-PI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | NDT & Coating for Field Joint Weld | ML1219-B19 | C-52-PR-839-PI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | NDT & Coating for Field Joint Weld | ML1179-B11 | C-52-PR-839-PI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | NDT & Coating for Field Joint Weld | HM-PL-0220 | C-52-PR-839-PI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | Receipt at site and inspection of Isolating Joints (Lot 1) | NDT & Coating for Field Joint Weld | HM-PL-0740 | C-52-PR-839-PI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | NDT & Coating for Field Joint Weld | HE-PR-0890 | C-52-PR-839-PI-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | Piping MTO - Final | NDT & Coating for Field Joint Weld | HE-PI-1300 | C-52-PR-839-PI-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | Final Issue for Design/ Construction-Tie-In Schedule | NDT & Coating for Field Joint Weld | HE-PR-0290 | C-52-PR-839-PI-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | Receipt at site and inspection of Isolating Joints (Lot 2) | NDT & Coating for Field Joint Weld | HM-PL-1510 | C-52-PR-839-PI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | NDT & Coating for Field Joint Weld | HM-PL-1570 | C-52-PR-839-PI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-Electrical Equipment Layout | Deep Earth Well Drilling | HE-EL-0530 | C-52-PR-839-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.8.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Receipt at site and inspection of AC UPS | Deep Earth Well Drilling | HM-ME-0790 | C-52-PR-839-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-Loop Diagrams | Deep Earth Well Drilling | HE-IC-0770 | C-52-PR-839-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | 1st Instrumentation Bulk material MTO | Deep Earth Well Drilling | HM-IC-0040 | C-52-PR-839-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | Deep Earth Well Drilling | HE-EL-0710 | C-52-PR-839-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-UPS SLD | Deep Earth Well Drilling | HE-EL-0290 | C-52-PR-839-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Deep Earth Well Drilling | HE-IC-1550 | C-52-PR-839-EI-1400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-Data sheet for LV Distribution board | Deep Earth Well Drilling | HE-EL-0650 | C-52-PR-839-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | 1st Electrical Bulk material MTO | Deep Earth Well Drilling | HM-EL-0520 | C-52-PR-839-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1590 | C-52-PR-839-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Obtain Company Approval-Data sheet for LV Distribution board | Deep Earth Well Drilling | HE-EL-0640 | C-52-PR-839-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-Instrument Index | Deep Earth Well Drilling | HE-IC-0530 | C-52-PR-839-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-Earthing Layout | Deep Earth Well Drilling | HE-EL-1670 | C-52-PR-839-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Receipt at site and inspection of Earthing Material (Lot 1) | Deep Earth Well Drilling | HM-EL-0380 | C-52-PR-839-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Receipt at site and inspection of Isolator (Lot 1) | Deep Earth Well Drilling | HM-ME-0690 | C-52-PR-839-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Deep Earth Well Drilling | HM-EL-0080 | C-52-PR-839-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Deep Earth Well Drilling | HE-IC-1430 | C-52-PR-839-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1690 | C-52-PR-839-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-I/O list | Deep Earth Well Drilling | HE-IC-0590 | C-52-PR-839-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Issue ICR- Addendum to DGs | Deep Earth Well Drilling | HE-IC-0010 | C-52-PR-839-EI-1400 | SS | Completed | Not Started | 10
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-Electrical Installation Drawings | Deep Earth Well Drilling | HE-EL-1790 | C-52-PR-839-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Deep Earth Well Drilling | HE-EL-1010 | C-52-PR-839-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Deep Earth Well Drilling | HE-IC-2570 | C-52-PR-839-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-0280 | C-52-PR-839-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-Hook-Up Diagram | Deep Earth Well Drilling | HE-IC-0650 | C-52-PR-839-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-F&G Cause and effect | Deep Earth Well Drilling | HE-HS-0350 | C-52-PR-839-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-Lighting Layout | Deep Earth Well Drilling | HE-EL-1730 | C-52-PR-839-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Issue ICR-Instrument index -Update | Deep Earth Well Drilling | HE-IC-0490 | C-52-PR-839-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Deep Earth Well Drilling | ML1032-B21 | C-52-PR-839-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Final Issue for Design/ Construction-Typical Installation Drawings | Deep Earth Well Drilling | HE-IC-0710 | C-52-PR-839-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Issue ICR- P&ID's | Deep Earth Well Drilling | HE-PR-0110 | C-52-PR-839-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Receipt at site and inspection of Isolator (Lot 2) | Deep Earth Well Drilling | HM-ME-2250 | C-52-PR-839-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Deep Earth Well Drilling | HM-ME-2330 | C-52-PR-839-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Deep Earth Well Drilling | HM-ME-2350 | C-52-PR-839-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-650 | C-52-PR-839-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | Receipt at site and inspection of Earthing Material (Lot 2) | Deep Earth Well Drilling | HM-EL-690 | C-52-PR-839-EI-1400 | FS | Not Started | Not Started | 42
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Electrical & Earthing Cable Laying | HM-EL-0080 | C-52-PR-839-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | 1st Electrical Bulk material MTO | Electrical & Earthing Cable Laying | HM-EL-0520 | C-52-PR-839-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Final Issue for Design/ Construction-Data Sheet for LV cables | Electrical & Earthing Cable Laying | HE-EL-0830 | C-52-PR-839-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Electrical & Earthing Cable Laying | HE-IC-0950 | C-52-PR-839-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0830 | C-52-PR-839-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Final Issue for Design/ Construction-Cable Sizing Calculation | Electrical & Earthing Cable Laying | HE-EL-0470 | C-52-PR-839-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Final Issue for Design/ Construction-Cable Schedule | Electrical & Earthing Cable Laying | HE-EL-0590 | C-52-PR-839-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Final Issue for Design/ Construction-Cable Routing Layout | Electrical & Earthing Cable Laying | HE-EL-1610 | C-52-PR-839-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Final Issue for Design/ Construction-Instrument Trench Layout | Electrical & Earthing Cable Laying | HE-IC-1010 | C-52-PR-839-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Final Issue for Design/ Construction-Data Sheet for HV cables | Electrical & Earthing Cable Laying | HE-EL-1950 | C-52-PR-839-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Final Issue for Design/ Construction-Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0230 | C-52-PR-839-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Final Issue for Design/ Construction-Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0290 | C-52-PR-839-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Final Issue for Design/ Construction-I/O list | Electrical & Earthing Cable Laying | HE-IC-0590 | C-52-PR-839-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Re-Issue for Approval- I/O list -Update | Electrical & Earthing Cable Laying | HE-IC-0570 | C-52-PR-839-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Re-Issue for Approval- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0210 | C-52-PR-839-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Re-Issue for Approval- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0270 | C-52-PR-839-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Issue ICR- Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0790 | C-52-PR-839-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Issue ICR- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0250 | C-52-PR-839-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Issue ICR- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0190 | C-52-PR-839-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-630 | C-52-PR-839-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of Light Pole, Lighting & Fixtures | HE-EL-0530 | C-52-PR-839-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.8.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Receipt at site and inspection of AC UPS | Installation of Light Pole, Lighting & Fixtures | HM-ME-0790 | C-52-PR-839-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-Loop Diagrams | Installation of Light Pole, Lighting & Fixtures | HE-IC-0770 | C-52-PR-839-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | 1st Instrumentation Bulk material MTO | Installation of Light Pole, Lighting & Fixtures | HM-IC-0040 | C-52-PR-839-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | Installation of Light Pole, Lighting & Fixtures | HE-EL-0710 | C-52-PR-839-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-UPS SLD | Installation of Light Pole, Lighting & Fixtures | HE-EL-0290 | C-52-PR-839-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of Light Pole, Lighting & Fixtures | HE-IC-1550 | C-52-PR-839-EI-1800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-Data sheet for LV Distribution board | Installation of Light Pole, Lighting & Fixtures | HE-EL-0650 | C-52-PR-839-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | 1st Electrical Bulk material MTO | Installation of Light Pole, Lighting & Fixtures | HM-EL-0520 | C-52-PR-839-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-ME-1590 | C-52-PR-839-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Obtain Company Approval-Data sheet for LV Distribution board | Installation of Light Pole, Lighting & Fixtures | HE-EL-0640 | C-52-PR-839-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-Instrument Index | Installation of Light Pole, Lighting & Fixtures | HE-IC-0530 | C-52-PR-839-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-Earthing Layout | Installation of Light Pole, Lighting & Fixtures | HE-EL-1670 | C-52-PR-839-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-EL-0380 | C-52-PR-839-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Receipt at site and inspection of Isolator (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-ME-0690 | C-52-PR-839-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-EL-0080 | C-52-PR-839-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Installation of Light Pole, Lighting & Fixtures | HE-IC-1430 | C-52-PR-839-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-ME-1690 | C-52-PR-839-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-I/O list | Installation of Light Pole, Lighting & Fixtures | HE-IC-0590 | C-52-PR-839-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Issue ICR- Addendum to DGs | Installation of Light Pole, Lighting & Fixtures | HE-IC-0010 | C-52-PR-839-EI-1800 | SS | Completed | Not Started | 10
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of Light Pole, Lighting & Fixtures | HE-EL-1790 | C-52-PR-839-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Installation of Light Pole, Lighting & Fixtures | HE-EL-1010 | C-52-PR-839-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Installation of Light Pole, Lighting & Fixtures | HE-IC-2570 | C-52-PR-839-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-EL-0280 | C-52-PR-839-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of Light Pole, Lighting & Fixtures | HE-IC-0650 | C-52-PR-839-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-F&G Cause and effect | Installation of Light Pole, Lighting & Fixtures | HE-HS-0350 | C-52-PR-839-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-Lighting Layout | Installation of Light Pole, Lighting & Fixtures | HE-EL-1730 | C-52-PR-839-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Issue ICR-Instrument index -Update | Installation of Light Pole, Lighting & Fixtures | HE-IC-0490 | C-52-PR-839-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Installation of Light Pole, Lighting & Fixtures | ML1032-B21 | C-52-PR-839-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of Light Pole, Lighting & Fixtures | HE-IC-0710 | C-52-PR-839-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Issue ICR- P&ID's | Installation of Light Pole, Lighting & Fixtures | HE-PR-0110 | C-52-PR-839-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Receipt at site and inspection of Isolator (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-ME-2250 | C-52-PR-839-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-ME-2330 | C-52-PR-839-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-ME-2350 | C-52-PR-839-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-EL-630 | C-52-PR-839-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-EL-650 | C-52-PR-839-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-EL-690 | C-52-PR-839-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.4.1.22.6.3 Light Pole, Lighting & FixturesCCOSW52E10.1 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of Light Pole, Lighting & Fixtures | HE-IC-1550 | C-52-PR-839-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-Electrical Equipment Layout | CP Cable Laying | HE-EL-0530 | C-52-PR-839-CA-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.8.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Receipt at site and inspection of AC UPS | CP Cable Laying | HM-ME-0790 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-Loop Diagrams | CP Cable Laying | HE-IC-0770 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | 1st Instrumentation Bulk material MTO | CP Cable Laying | HM-IC-0040 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | CP Cable Laying | HE-EL-0710 | C-52-PR-839-CA-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-UPS SLD | CP Cable Laying | HE-EL-0290 | C-52-PR-839-CA-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | CP Cable Laying | HE-IC-1550 | C-52-PR-839-CA-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-Data sheet for LV Distribution board | CP Cable Laying | HE-EL-0650 | C-52-PR-839-CA-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | 1st Electrical Bulk material MTO | CP Cable Laying | HM-EL-0520 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Obtain Company Approval-Data sheet for LV Distribution board | CP Cable Laying | HE-EL-0640 | C-52-PR-839-CA-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-Instrument Index | CP Cable Laying | HE-IC-0530 | C-52-PR-839-CA-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-Earthing Layout | CP Cable Laying | HE-EL-1670 | C-52-PR-839-CA-1000 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Receipt at site and inspection of Earthing Material (Lot 1) | CP Cable Laying | HM-EL-0380 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Receipt at site and inspection of Isolator (Lot 1) | CP Cable Laying | HM-ME-0690 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Receipt at site and inspection of Power & Control Cables (Lot 1) | CP Cable Laying | HM-EL-0080 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | CP Cable Laying | HE-IC-1430 | C-52-PR-839-CA-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | CP Cable Laying | HM-ME-1690 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-I/O list | CP Cable Laying | HE-IC-0590 | C-52-PR-839-CA-1000 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Issue ICR- Addendum to DGs | CP Cable Laying | HE-IC-0010 | C-52-PR-839-CA-1000 | SF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-Electrical Installation Drawings | CP Cable Laying | HE-EL-1790 | C-52-PR-839-CA-1000 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | CP Cable Laying | HE-EL-1010 | C-52-PR-839-CA-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | CP Cable Laying | HE-IC-2570 | C-52-PR-839-CA-1000 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Receipt at site and inspection of Cable Trays (Lot 2) | CP Cable Laying | HM-EL-0280 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-Hook-Up Diagram | CP Cable Laying | HE-IC-0650 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-F&G Cause and effect | CP Cable Laying | HE-HS-0350 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-Lighting Layout | CP Cable Laying | HE-EL-1730 | C-52-PR-839-CA-1000 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Issue ICR-Instrument index -Update | CP Cable Laying | HE-IC-0490 | C-52-PR-839-CA-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | CP Cable Laying | ML1032-B21 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Final Issue for Design/ Construction-Typical Installation Drawings | CP Cable Laying | HE-IC-0710 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Issue ICR- P&ID's | CP Cable Laying | HE-PR-0110 | C-52-PR-839-CA-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Receipt at site and inspection of Isolator (Lot 2) | CP Cable Laying | HM-ME-2250 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | CP Cable Laying | HM-ME-2330 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | CP Cable Laying | HM-ME-2350 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Receipt at site and inspection of Power & Control Cables (Lot 2) | CP Cable Laying | HM-EL-630 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Receipt at site and inspection of Cable Trays (Lot 2) | CP Cable Laying | HM-EL-650 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Receipt at site and inspection of Earthing Material (Lot 2) | CP Cable Laying | HM-EL-690 | C-52-PR-839-CA-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | Receipt at site and inspection of CP System - Permanent Material | CP Cable Laying | HM-PL-0430 | C-52-PR-839-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.4.1.22.7.1 CPRT/ CP Anode Bed Installation (subcontract)CCOSW52E14 | CP Drilling & Earthing Drilling Subcontract Award | CP Cable Laying | HS-CN-0240 | C-52-PR-839-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Electrical Equipment Layout | FOC Laying | HE-EL-0530 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.8.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Receipt at site and inspection of AC UPS | FOC Laying | HM-ME-0790 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Loop Diagrams | FOC Laying | HE-IC-0770 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | 1st Instrumentation Bulk material MTO | FOC Laying | HM-IC-0040 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | FOC Laying | HE-EL-0710 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-UPS SLD | FOC Laying | HE-EL-0290 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | FOC Laying | HE-IC-1550 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Data sheet for LV Distribution board | FOC Laying | HE-EL-0650 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | 1st Electrical Bulk material MTO | FOC Laying | HM-EL-0520 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | FOC Laying | HM-ME-1590 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Obtain Company Approval-Data sheet for LV Distribution board | FOC Laying | HE-EL-0640 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Instrument Index | FOC Laying | HE-IC-0530 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Earthing Layout | FOC Laying | HE-EL-1670 | C-52-PR-839-TE-1410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Receipt at site and inspection of Earthing Material (Lot 1) | FOC Laying | HM-EL-0380 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Receipt at site and inspection of Isolator (Lot 1) | FOC Laying | HM-ME-0690 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Receipt at site and inspection of Power & Control Cables (Lot 1) | FOC Laying | HM-EL-0080 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | FOC Laying | HE-IC-1430 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | FOC Laying | HM-ME-1690 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-I/O list | FOC Laying | HE-IC-0590 | C-52-PR-839-TE-1410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Issue ICR- Addendum to DGs | FOC Laying | HE-IC-0010 | C-52-PR-839-TE-1410 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Electrical Installation Drawings | FOC Laying | HE-EL-1790 | C-52-PR-839-TE-1410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | FOC Laying | HE-EL-1010 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | FOC Laying | HE-IC-2570 | C-52-PR-839-TE-1410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Receipt at site and inspection of Cable Trays (Lot 2) | FOC Laying | HM-EL-0280 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Hook-Up Diagram | FOC Laying | HE-IC-0650 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-F&G Cause and effect | FOC Laying | HE-HS-0350 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Lighting Layout | FOC Laying | HE-EL-1730 | C-52-PR-839-TE-1410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Issue ICR-Instrument index -Update | FOC Laying | HE-IC-0490 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | FOC Laying | ML1032-B21 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Typical Installation Drawings | FOC Laying | HE-IC-0710 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Issue ICR- P&ID's | FOC Laying | HE-PR-0110 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Receipt at site and inspection of Isolator (Lot 2) | FOC Laying | HM-ME-2250 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | FOC Laying | HM-ME-2330 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | FOC Laying | HM-ME-2350 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Receipt at site and inspection of Power & Control Cables (Lot 2) | FOC Laying | HM-EL-630 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Receipt at site and inspection of Cable Trays (Lot 2) | FOC Laying | HM-EL-650 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Receipt at site and inspection of Earthing Material (Lot 2) | FOC Laying | HM-EL-690 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | 1st Telecom Bulk material MTO | FOC Laying | HM-TL-0040 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Receipt at site and inspection of Leak Detection System | FOC Laying | HM-ME-0280 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | FOC Laying | HE-TL-0410 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | FOC Splicing / Termination Subcontract Award | FOC Laying | HS-CN-0290 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | FOC Laying | ML1033-B22 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | FOC Laying | HE-IC-0110 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | FOC Laying | HM-ME-1290 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Telecom Equipment Layout | FOC Laying | HE-TL-0770 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | FOC Laying | HE-TL-0290 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | FOC Laying | HE-TL-0470 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | FOC Laying | HE-TL-0710 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Telecom cable schedule | FOC Laying | HE-TL-0830 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | FOC Laying | HE-TL-0350 | C-52-PR-839-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.8.1 PIDS System/FOC/CCTVCCOSWIC342 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | FOC Laying | HM-ME-2270 | C-52-PR-839-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 Excavation (incl Bedding)CCOSWCS303 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-52-EB1-CI-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 Excavation (incl Bedding)CCOSWCS303 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-52-EB1-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 Excavation (incl Bedding)CCOSWCS303 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Site Survey, Preparation & Grading Works | HE-CS-0470 | C-52-EB1-CI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 Excavation (incl Bedding)CCOSWCS303 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Site Survey, Preparation & Grading Works | CTF-1000 | C-52-EB1-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 Excavation (incl Bedding)CCOSWCS303 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-52-EB1-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 Excavation (incl Bedding)CCOSWCS303 | Issue Civil / Structural Drawings for Launcher/ Receiver facilities | Site Survey, Preparation & Grading Works | ML1199-B24 | C-52-EB1-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 Excavation (incl Bedding)CCOSWCS303 | NOC's / Approval /Survey | Site Survey, Preparation & Grading Works | CTF-1010 | C-52-EB1-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.2.22.1.2 Foundation Works (for Substructure)CCOSWCS304 | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | Building Foundation Works (for Substructure) | ML1209-B27 | C-52-EB1-CI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.4.2.22.1.3 Concrete Superstructure WorksCCOSWCS305 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Superstructure Works | HE-CS-0230 | C-52-EB1-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.2.22.1.3 Concrete Superstructure WorksCCOSWCS305 | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | Concrete Superstructure Works | ML1209-B27 | C-52-EB1-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.2.22.1.3 Concrete Superstructure WorksCCOSWCS305 | 1st Civil Bulk material MTO | Concrete Superstructure Works | HM-CS-0040 | C-52-EB1-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.2.22.1.6 Metal WorksCCOSWCS318 | 1st Structural Bulk material MTO | Steel Structural Works | HM-CS-0110 | C-52-EB1-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.3.4.2.22.1.7 Paving WorksCCOSWCS319 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving Works | HE-CS-0290 | C-52-EB1-CI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.2.22.1.7 Paving WorksCCOSWCS319 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving Works | ML1059-B28 | C-52-EB1-CI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.13 E&I Works | P2543-R01-Oct24..4.3.1.3.4.2.22.2.1 HVAC System & Plumbing WorksCCOSWME511 | E&I Works Subcontract Award | Plumbing Works | HS-CN-0640 | C-52-EB1-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.12 Building | P2543-R01-Oct24..4.3.1.3.4.2.22.2.1 HVAC System & Plumbing WorksCCOSWME511 | Building Subcontract Award | Plumbing Works | HS-CN-0590 | C-52-EB1-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.2.1 HVAC System & Plumbing WorksCCOSWME511 | Receipt at site and inspection of HVAC Equipment | Plumbing Works | HM-ME-1790 | C-52-EB1-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.2.22.2.1 HVAC System & Plumbing WorksCCOSWME511 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Plumbing Works | ML1015-B08 | C-52-EB1-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.2.1 HVAC System & Plumbing WorksCCOSWME511 | Receipt at site and inspection of Fire Suppression System | Plumbing Works | HM-ME-1830 | C-52-EB1-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Issue ICR-Instrument index -Update | Installation of Power Distribution System | HE-IC-0490 | C-52-EB1-EI-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Final Issue for Design/ Construction-Loop Diagrams | Installation of Power Distribution System | HE-IC-0770 | C-52-EB1-EI-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Final Issue for Design/ Construction-Lighting Layout | Installation of Power Distribution System | HE-EL-1730 | C-52-EB1-EI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of Power Distribution System | HE-IC-0710 | C-52-EB1-EI-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of Power Distribution System | HE-IC-0650 | C-52-EB1-EI-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.7.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Receipt at site and inspection of Power Distribution Boards | Installation of Power Distribution System | HM-ME-0890 | C-52-EB1-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Final Issue for Design/ Construction-Instrument Index | Installation of Power Distribution System | HE-IC-0530 | C-52-EB1-EI-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Issue ICR- Addendum to DGs | Installation of Power Distribution System | HE-IC-0010 | C-52-EB1-EI-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of Power Distribution System | HM-EL-0080 | C-52-EB1-EI-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Receipt at site and inspection of MCT (Lot 1) | Installation of Power Distribution System | HM-EL-0480 | C-52-EB1-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Final Issue for Design/ Construction-I/O list | Installation of Power Distribution System | HE-IC-0590 | C-52-EB1-EI-1000 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of Power Distribution System | HM-EL-0380 | C-52-EB1-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of Power Distribution System | HE-EL-1790 | C-52-EB1-EI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Final Issue for Design/ Construction-Earthing Layout | Installation of Power Distribution System | HE-EL-1670 | C-52-EB1-EI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of Power Distribution System | HE-EL-0530 | C-52-EB1-EI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | 1st Electrical Bulk material MTO | Installation of Power Distribution System | HM-EL-0520 | C-52-EB1-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Installation of Power Distribution System | HM-ME-1590 | C-52-EB1-EI-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Power Distribution System | HM-EL-0280 | C-52-EB1-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Issue ICR- P&ID's | Installation of Power Distribution System | HE-PR-0110 | C-52-EB1-EI-1000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Installation of Power Distribution System | HM-ME-2330 | C-52-EB1-EI-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of Power Distribution System | HM-EL-630 | C-52-EB1-EI-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Power Distribution System | HM-EL-650 | C-52-EB1-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of Power Distribution System | HM-EL-690 | C-52-EB1-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.1 Power Distribution SystemCCOSW52E16 | Receipt at site and inspection of MCT (Lot 2) | Installation of Power Distribution System | HM-EL-710 | C-52-EB1-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | 1st Electrical Bulk material MTO | E&I Cable Laying | HM-EL-0520 | C-52-EB1-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Cable Schedule | E&I Cable Laying | HE-EL-0590 | C-52-EB1-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Receipt at site and inspection of Power & Control Cables (Lot 1) | E&I Cable Laying | HM-EL-0080 | C-52-EB1-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | E&I Cable Laying | HE-IC-0830 | C-52-EB1-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Instrument Trench Layout | E&I Cable Laying | HE-IC-1010 | C-52-EB1-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Cable Routing Layout | E&I Cable Laying | HE-EL-1610 | C-52-EB1-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | E&I Cable Laying | HE-IC-0950 | C-52-EB1-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Data Sheet for LV cables | E&I Cable Laying | HE-EL-0830 | C-52-EB1-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Cable Sizing Calculation | E&I Cable Laying | HE-EL-0470 | C-52-EB1-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Data Sheet for HV cables | E&I Cable Laying | HE-EL-1950 | C-52-EB1-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Specification for RTU | E&I Cable Laying | HE-IC-0230 | C-52-EB1-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Specification for Leak Detection System | E&I Cable Laying | HE-IC-0290 | C-52-EB1-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-I/O list | E&I Cable Laying | HE-IC-0590 | C-52-EB1-EI-1210 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Re-Issue for Approval- I/O list -Update | E&I Cable Laying | HE-IC-0570 | C-52-EB1-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Re-Issue for Approval- Specification for RTU | E&I Cable Laying | HE-IC-0210 | C-52-EB1-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Re-Issue for Approval- Specification for Leak Detection System | E&I Cable Laying | HE-IC-0270 | C-52-EB1-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Issue ICR- Instrument Cable Block Diagram | E&I Cable Laying | HE-IC-0790 | C-52-EB1-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Issue ICR- Specification for Leak Detection System | E&I Cable Laying | HE-IC-0250 | C-52-EB1-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Issue ICR- Specification for RTU | E&I Cable Laying | HE-IC-0190 | C-52-EB1-EI-1210 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Receipt at site and inspection of Power & Control Cables (Lot 2) | E&I Cable Laying | HM-EL-630 | C-52-EB1-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | 1st Electrical Bulk material MTO | MCT Installation | HM-EL-0520 | C-52-EB1-EI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Cable Schedule | MCT Installation | HE-EL-0590 | C-52-EB1-EI-1220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Receipt at site and inspection of Power & Control Cables (Lot 1) | MCT Installation | HM-EL-0080 | C-52-EB1-EI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | MCT Installation | HE-IC-0830 | C-52-EB1-EI-1220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Instrument Trench Layout | MCT Installation | HE-IC-1010 | C-52-EB1-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Cable Routing Layout | MCT Installation | HE-EL-1610 | C-52-EB1-EI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | MCT Installation | HE-IC-0950 | C-52-EB1-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Data Sheet for LV cables | MCT Installation | HE-EL-0830 | C-52-EB1-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Cable Sizing Calculation | MCT Installation | HE-EL-0470 | C-52-EB1-EI-1220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Data Sheet for HV cables | MCT Installation | HE-EL-1950 | C-52-EB1-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Specification for RTU | MCT Installation | HE-IC-0230 | C-52-EB1-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-Specification for Leak Detection System | MCT Installation | HE-IC-0290 | C-52-EB1-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Final Issue for Design/ Construction-I/O list | MCT Installation | HE-IC-0590 | C-52-EB1-EI-1220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Re-Issue for Approval- I/O list -Update | MCT Installation | HE-IC-0570 | C-52-EB1-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Re-Issue for Approval- Specification for RTU | MCT Installation | HE-IC-0210 | C-52-EB1-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Re-Issue for Approval- Specification for Leak Detection System | MCT Installation | HE-IC-0270 | C-52-EB1-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Issue ICR- Instrument Cable Block Diagram | MCT Installation | HE-IC-0790 | C-52-EB1-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Issue ICR- Specification for Leak Detection System | MCT Installation | HE-IC-0250 | C-52-EB1-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Issue ICR- Specification for RTU | MCT Installation | HE-IC-0190 | C-52-EB1-EI-1220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | Receipt at site and inspection of Power & Control Cables (Lot 2) | MCT Installation | HM-EL-630 | C-52-EB1-EI-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.4.2.22.4.1 SDH CabinetCCOSWIC309 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | SDH Cabinet Installation | ML1033-B22 | C-52-EB1-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.4.2.22.4.1 SDH CabinetCCOSWIC309 | 1st Telecom Bulk material MTO | SDH Cabinet Installation | HM-TL-0040 | C-52-EB1-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.3.4.2.22.4.1 SDH CabinetCCOSWIC309 | Final Issue for Design/ Construction-Telecom cable schedule | SDH Cabinet Installation | HE-TL-0830 | C-52-EB1-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.4.1 SDH CabinetCCOSWIC309 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 1) | SDH Cabinet Installation | HM-ME-1390 | C-52-EB1-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.3.4.2.22.4.1 SDH CabinetCCOSWIC309 | FOC Splicing / Termination Subcontract Award | SDH Cabinet Installation | HS-CN-0290 | C-52-EB1-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.3.4.2.22.4.1 SDH CabinetCCOSWIC309 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | SDH Cabinet Installation | HE-TL-0470 | C-52-EB1-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.3.4.2.22.4.1 SDH CabinetCCOSWIC309 | Final Issue for Design/ Construction-Telecom Equipment Layout | SDH Cabinet Installation | HE-TL-0770 | C-52-EB1-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.4.2.22.4.1 SDH CabinetCCOSWIC309 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | SDH Cabinet Installation | HE-TL-0710 | C-52-EB1-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.14.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.4.1 SDH CabinetCCOSWIC309 | Receipt at site and inspection of Access Switch, Fiber Optic Patch Panel and Media Converter (Lot 2) | SDH Cabinet Installation | HM-ME-2290 | C-52-EB1-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.13 E&I Works | P2543-R01-Oct24..4.3.1.3.4.4.22.2.1 OHPL Installation Works-Tower/Post installation (Subcontract)CCOSW52E20.1 | E&I Works Subcontract Award | OHPL Installation Works-Tower/Post installation (Subcontract) | HS-CN-0640 | C-52-OHPL-EL-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.7 OHPL | P2543-R01-Oct24..4.3.1.3.4.4.22.2.3 Transformer / Directly Buried MV Cables (including testing)CCOSW52E22 | OHPL Subcontract Award | Transformer / Directly Buried MV Cables (including testing) | HS-CN-0440 | C-52-OHPL-EL-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.4.22.2.3 Transformer / Directly Buried MV Cables (including testing)CCOSW52E22 | Receipt at site and inspection of Distribution Transformer | Transformer / Directly Buried MV Cables (including testing) | HM-ME-0990 | C-52-OHPL-EL-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.4.22.3.1 Shutdown Connection of OHL & Cable TestingCCOSW52S10 | Receipt at site and inspection of Distribution Transformer | Shutdown Connection of OHL & Cable Testing | HM-ME-0990 | C-52-OHPL-EL-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | P2543-R01-Oct24..4.3.1.3.4.4.22.3.1 Shutdown Connection of OHL & Cable TestingCCOSW52S10 | Final Issue for Design/ Construction-Shutdown Requirements & Plan | Shutdown Connection of OHL & Cable Testing | C-COM-890 | C-52-OHPL-EL-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.7 OHPL | P2543-R01-Oct24..4.3.1.3.4.4.22.3.1 Shutdown Connection of OHL & Cable TestingCCOSW52S10 | OHPL Subcontract Award | Shutdown Connection of OHL & Cable Testing | HS-CN-0440 | C-52-OHPL-EL-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | Topographical Survey | Site Survey, Preparation (Include Existing Dismantling Fence) & Grading Works | HE-SS-0030 | C-52-D-HT-CI-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | Project Kick off Meeting | Site Survey, Preparation (Include Existing Dismantling Fence) & Grading Works | ML1002 | C-52-D-HT-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation (Include Existing Dismantling Fence) & Grading Works | HE-CS-0170 | C-52-D-HT-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | Site Survey, Preparation (Include Existing Dismantling Fence) & Grading Works | ML1209-B27 | C-52-D-HT-CI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | Issue Civil / Structural Drawings for Launcher/ Receiver facilities | Site Survey, Preparation (Include Existing Dismantling Fence) & Grading Works | ML1199-B24 | C-52-D-HT-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Site Survey, Preparation (Include Existing Dismantling Fence) & Grading Works | CTF-1000 | C-52-D-HT-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Site Survey, Preparation (Include Existing Dismantling Fence) & Grading Works | HE-CS-0470 | C-52-D-HT-CI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.3.21.1.1 Excavation (incl Bedding)CCOSWCS306 | NOC's / Approval /Survey | Site Survey, Preparation (Include Existing Dismantling Fence) & Grading Works | CTF-1010 | C-52-D-HT-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | 1st Civil Bulk material MTO | Concrete Works for Hot Tap Tie in Pit | HM-CS-0040 | C-52-D-HT-CI-1480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Hot Tap Tie in Pit | HE-CS-0230 | C-52-D-HT-CI-1480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | Final Civil Bulk material MTO | Concrete Works for Hot Tap Tie in Pit | HM-CS-0050 | C-52-D-HT-CI-1480 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | Concrete Works for Hot Tap Tie in Pit | ML1209-B27 | C-52-D-HT-CI-1480 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | 1st Civil Bulk material MTO | Concrete Works for Pipe Support Foundations | HM-CS-0040 | C-52-D-HT-CI-1600 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Pipe Support Foundations | HE-CS-0230 | C-52-D-HT-CI-1600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.30 Design Calculation for Typical Pipe supports | P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | Final Issue for Design/ Construction-Design Calculation for Typical Pipe supports | Concrete Works for Pipe Support Foundations | HE-CS-1130 | C-52-D-HT-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | Final Civil Bulk material MTO | Concrete Works for Pipe Support Foundations | HM-CS-0050 | C-52-D-HT-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.1.2 Concrete WorksCCOSWCS308 | Issue Civil / Structural Drawings for all facilities at Sweihan CRS - IFC | Concrete Works for Pipe Support Foundations | ML1209-B27 | C-52-D-HT-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.3.1.3.3.21.1.3 Pipe Supports Fabrication & InstallationCCOSWSS502 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Pipe Supports Fabrication & Installation | HE-CS-1430 | C-52-D-HT-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.3.21.1.3 Pipe Supports Fabrication & InstallationCCOSWSS502 | Fence Works Subcontract Award | Pipe Supports Fabrication & Installation | HS-CN-0690 | C-52-D-HT-CI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.3.21.1.3 Pipe Supports Fabrication & InstallationCCOSWSS502 | 1st Structural Bulk material MTO | Pipe Supports Fabrication & Installation | HM-CS-0110 | C-52-D-HT-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.3.21.1.3 Pipe Supports Fabrication & InstallationCCOSWSS502 | Final Structural Bulk material MTO | Pipe Supports Fabrication & Installation | HM-CS-0120 | C-52-D-HT-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.3.1.3.3.21.1.3 Pipe Supports Fabrication & InstallationCCOSWSS502 | Final Issue for Design/ Construction-Misc. supports | Pipe Supports Fabrication & Installation | HE-CS-1490 | C-52-D-HT-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.3.21.1.4 Concrete ProtectionCCOSWCS312 | Final Civil Bulk material MTO | Concrete Protection | HM-CS-0050 | C-52-D-HT-CI-1700 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.3.21.1.5 Fences & Gates ConstructionCCOSWCS314 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Fences & Gates Construction | HE-CS-0470 | C-52-D-HT-CI-2220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.3.3.21.1.5 Fences & Gates ConstructionCCOSWCS314 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Fences & Gates Construction | HE-CS-0350 | C-52-D-HT-CI-2220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.3.21.1.6 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS510 | 1st Structural Bulk material MTO | Platforms/Crossovers/ Guardrails and Bollards/ Windsock | HM-CS-0110 | C-52-D-HT-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.3.21.1.6 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS510 | Fence Works Subcontract Award | Platforms/Crossovers/ Guardrails and Bollards/ Windsock | HS-CN-0690 | C-52-D-HT-CI-3000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.3.3.21.1.7 Paving WorksCCOSWCS316 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment (Including Fence Re-Instatement) | HE-CS-0290 | C-52-D-HT-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.1.7 Paving WorksCCOSWCS316 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment (Including Fence Re-Instatement) | ML1059-B28 | C-52-D-HT-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.3.21.2.1 Piping Pre-FabricationCCOSWPI509 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-52-D-HT-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.2.1 Piping Pre-FabricationCCOSWPI509 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-52-D-HT-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.3.21.2.1 Piping Pre-FabricationCCOSWPI509 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Pre-Fabrication | HE-PR-0290 | C-52-D-HT-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.3.21.2.1 Piping Pre-FabricationCCOSWPI509 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-52-D-HT-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.3.21.2.1 Piping Pre-FabricationCCOSWPI509 | NDT / PWHT Subcontract Award | Piping Pre-Fabrication | HS-CN-0190 | C-52-D-HT-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.3.21.2.1 Piping Pre-FabricationCCOSWPI509 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Pre-Fabrication | HE-PR-0890 | C-52-D-HT-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.3.21.2.1 Piping Pre-FabricationCCOSWPI509 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-52-D-HT-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.3.21.2.1 Piping Pre-FabricationCCOSWPI509 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-52-D-HT-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.13 Overall Plot Plan - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..4.3.1.3.3.21.2.1 Piping Pre-FabricationCCOSWPI509 | Final Issue for Design/ Construction-Overall Plot Plan - 52" Pipeline SWEIHAN CRS | Piping Pre-Fabrication | HE-PI-0440 | C-52-D-HT-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.2.1 Piping Pre-FabricationCCOSWPI509 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Pre-Fabrication | ML1179-B11 | C-52-D-HT-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.25 Piping GA - 52" Pipeline SWEIHAN CRS | P2543-R01-Oct24..4.3.1.3.3.21.2.1 Piping Pre-FabricationCCOSWPI509 | Final Issue for Design/ Construction-Piping GA- 52" Pipeline SWEIHAN CRS | Piping Pre-Fabrication | HE-PI-0700 | C-52-D-HT-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | Project Kick off Meeting | Piping Erection | ML1002 | C-52-D-HT-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Erection | ML1219-B19 | C-52-D-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Erection | HE-PR-0290 | C-52-D-HT-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Erection | HM-PL-0220 | C-52-D-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | Piping MTO - Final | Piping Erection | HE-PI-1300 | C-52-D-HT-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | NDT / PWHT Subcontract Award | Piping Erection | HS-CN-0190 | C-52-D-HT-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Piping Erection | HE-PR-0890 | C-52-D-HT-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | Final Issue for Design/ Construction-Piping Isometrics | Piping Erection | HE-PI-1240 | C-52-D-HT-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | 1st Piping Bulk material MTO | Piping Erection | HM-PI-0040 | C-52-D-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Erection | HM-PL-0630 | C-52-D-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Erection | HM-PL-0740 | C-52-D-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Erection | ML1179-B11 | C-52-D-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Erection | HM-PL-0640 | C-52-D-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Erection | HM-PL-1510 | C-52-D-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.3.21.2.2 ErectionCCOSWPI524 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Erection | HM-PL-1570 | C-52-D-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.3.21.2.3 Field Joint Welding, NDT & CoatingCCOSWPI534 | Piping MTO - Final | Field Joint Welding | HE-PI-1300 | C-52-D-HT-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.3.21.2.3 Field Joint Welding, NDT & CoatingCCOSWPI534 | Project Kick off Meeting | Field Joint Welding | ML1002 | C-52-D-HT-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.2.3 Field Joint Welding, NDT & CoatingCCOSWPI534 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Field Joint Welding | ML1219-B19 | C-52-D-HT-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.3.21.2.3 Field Joint Welding, NDT & CoatingCCOSWPI534 | NDT / PWHT Subcontract Award | Field Joint Welding | HS-CN-0190 | C-52-D-HT-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.2.3 Field Joint Welding, NDT & CoatingCCOSWPI534 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Field Joint Welding | ML1179-B11 | C-52-D-HT-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.2.4 HydrotestingCCOSWPI544 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Hydrotesting | ML1219-B19 | C-52-D-HT-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.2.4 HydrotestingCCOSWPI544 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Hydrotesting | ML1179-B11 | C-52-D-HT-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.2.5 Installation of ValvesCCOSWPI554 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Installation of Valves/GOV/ROV | ML1219-B19 | C-52-D-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.3.21.2.5 Installation of ValvesCCOSWPI554 | Final Issue for Design/ Construction-Tie-In Schedule | Installation of Valves/GOV/ROV | HE-PR-0290 | C-52-D-HT-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.3.21.2.5 Installation of ValvesCCOSWPI554 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Installation of Valves/GOV/ROV | HM-PL-0220 | C-52-D-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.3.21.2.5 Installation of ValvesCCOSWPI554 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Installation of Valves/GOV/ROV | HE-PR-0890 | C-52-D-HT-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.3.21.2.5 Installation of ValvesCCOSWPI554 | Final Issue for Design/ Construction-Piping Isometrics | Installation of Valves/GOV/ROV | HE-PI-1240 | C-52-D-HT-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.3.21.2.5 Installation of ValvesCCOSWPI554 | 1st Piping Bulk material MTO | Installation of Valves/GOV/ROV | HM-PI-0040 | C-52-D-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.2.5 Installation of ValvesCCOSWPI554 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Installation of Valves/GOV/ROV | ML1179-B11 | C-52-D-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.3.21.2.5 Installation of ValvesCCOSWPI554 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Installation of Valves/GOV/ROV | HM-PL-1570 | C-52-D-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.3.21.2.6 Final Bolt Torquing/ Re-InstatementCCOSWPI564 | Project Kick off Meeting | Final Bolt Torquing/ Re-Instatement | ML1002 | C-52-D-HT-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.2.6 Final Bolt Torquing/ Re-InstatementCCOSWPI564 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Final Bolt Torquing/ Re-Instatement | ML1219-B19 | C-52-D-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.3.21.2.6 Final Bolt Torquing/ Re-InstatementCCOSWPI564 | Final Issue for Design/ Construction-Tie-In Schedule | Final Bolt Torquing/ Re-Instatement | HE-PR-0290 | C-52-D-HT-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.3.21.2.6 Final Bolt Torquing/ Re-InstatementCCOSWPI564 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0220 | C-52-D-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.3.21.2.6 Final Bolt Torquing/ Re-InstatementCCOSWPI564 | Piping MTO - Final | Final Bolt Torquing/ Re-Instatement | HE-PI-1300 | C-52-D-HT-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.3.21.2.6 Final Bolt Torquing/ Re-InstatementCCOSWPI564 | NDT / PWHT Subcontract Award | Final Bolt Torquing/ Re-Instatement | HS-CN-0190 | C-52-D-HT-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.5 Isolation & Tie-In philosophy | P2543-R01-Oct24..4.3.1.3.3.21.2.6 Final Bolt Torquing/ Re-InstatementCCOSWPI564 | Final Issue for Design/ Construction-Isolation & Tie-In philosophy | Final Bolt Torquing/ Re-Instatement | HE-PR-0890 | C-52-D-HT-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.3.21.2.6 Final Bolt Torquing/ Re-InstatementCCOSWPI564 | Final Issue for Design/ Construction-Piping Isometrics | Final Bolt Torquing/ Re-Instatement | HE-PI-1240 | C-52-D-HT-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.3.21.2.6 Final Bolt Torquing/ Re-InstatementCCOSWPI564 | 1st Piping Bulk material MTO | Final Bolt Torquing/ Re-Instatement | HM-PI-0040 | C-52-D-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.3.21.2.6 Final Bolt Torquing/ Re-InstatementCCOSWPI564 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Final Bolt Torquing/ Re-Instatement | ML1179-B11 | C-52-D-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.3.21.2.6 Final Bolt Torquing/ Re-InstatementCCOSWPI564 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1570 | C-52-D-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.3.21.3.1 Preparation, Marking & UT for Existing Line 48" LineCCOSWHT461 | Receipt at site and inspection of Pigging & Split Tee (Lot 2) | Preparation, Marking & UT for Existing Line 48" Line | HM-PL-1530 | C-52-D-HT002-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.3.1.3.3.21.3.1 Preparation, Marking & UT for Existing Line 48" LineCCOSWHT461 | Procedure Qualification (PQT/WQT for Hot Tapping - 48", 42",36 & 30") | Preparation, Marking & UT for Existing Line 48" Line | C-COM-1020 | C-52-D-HT002-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | P2543-R01-Oct24..4.3.1.3.3.21.3.1 Preparation, Marking & UT for Existing Line 48" LineCCOSWHT461 | Final Issue for Design/ Construction-Piping Tie In Schedule | Preparation, Marking & UT for Existing Line 48" Line | HE-PI-3520 | C-52-D-HT002-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | P2543-R01-Oct24..4.3.1.3.3.21.3.1 Preparation, Marking & UT for Existing Line 48" LineCCOSWHT461 | Final Issue for Design/ Construction-Data Sheet - Split Tee | Preparation, Marking & UT for Existing Line 48" Line | HE-PL-1370 | C-52-D-HT002-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.3.21.3.1 Preparation, Marking & UT for Existing Line 48" LineCCOSWHT461 | 1st Piping Bulk material MTO | Preparation, Marking & UT for Existing Line 48" Line | HM-PI-0040 | C-52-D-HT002-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.3.21.3.1 Preparation, Marking & UT for Existing Line 48" LineCCOSWHT461 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Preparation, Marking & UT for Existing Line 48" Line | HM-PL-0220 | C-52-D-HT002-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.24.2 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.3.21.3.1 Preparation, Marking & UT for Existing Line 48" LineCCOSWHT461 | Receipt at site and inspection of Hot Tapping Material | Preparation, Marking & UT for Existing Line 48" Line | HM-PL-0320 | C-52-D-HT002-ME-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.3.21.3.1 Preparation, Marking & UT for Existing Line 48" LineCCOSWHT461 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Preparation, Marking & UT for Existing Line 48" Line | HM-PL-1570 | C-52-D-HT002-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.11 Hot Tapping | P2543-R01-Oct24..4.3.1.3.3.21.3.1 Preparation, Marking & UT for Existing Line 48" LineCCOSWHT461 | Hot Tapping Subcontract Award | Preparation, Marking & UT for Existing Line 48" Line | HS-CN-0540 | C-52-D-HT002-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.1.5 Hot Tapping | P2543-R01-Oct24..4.3.1.3.3.21.3.1 Preparation, Marking & UT for Existing Line 48" LineCCOSWHT461 | Commercial Clarifications & Placement of PO- Hot Tapping | Preparation, Marking & UT for Existing Line 48" Line | HS-GN-0230 | C-52-D-HT002-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.3.21.4.1 Tie in works to 52'' and 20'' PipelineCCOSWPI512 | Final Issue for Design/ Construction-Tie-In Schedule | Tie-In with 30" Pipeline | HE-PR-0290 | C-52-D-HT-ME-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-52-PL-838-CI-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-52-PL-838-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-52-PL-838-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Site Survey, Preparation & Grading Works | HE-CS-0470 | C-52-PL-838-CI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Site Survey, Preparation & Grading Works | CTF-1000 | C-52-PL-838-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | NOC's / Approval /Survey | Site Survey, Preparation & Grading Works | CTF-1010 | C-52-PL-838-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Equipment Foundations | HE-CS-0230 | C-52-PL-838-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Concrete Works for Equipment Foundations | HE-CS-0650 | C-52-PL-838-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.36 Typical Detailed Drawing - Jib Crane Foundation | P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | Final Issue for Design/ Construction-Typical Detailed Drawing - Jib Crane Foundation | Concrete Works for Equipment Foundations | HE-CS-1070 | C-52-PL-838-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Concrete Works for Equipment Foundations | HE-CS-1190 | C-52-PL-838-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | 1st Civil Bulk material MTO | Concrete Works for Equipment Foundations | HM-CS-0040 | C-52-PL-838-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Concrete Works for Equipment Foundations | HE-CS-1310 | C-52-PL-838-CI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.1.5 Thrust Anchor BlockCCOH52SS32 | Receipt at site and inspection of Anchor Flanges (Lot 2) | Concrete Works for Thrust Anchor Block | HM-PL-1550 | C-52-PL-838-CI-1510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.1.21.1.5 Thrust Anchor BlockCCOH52SS32 | 1st Structural Bulk material MTO | Concrete Works for Thrust Anchor Block | HM-CS-0110 | C-52-PL-838-CI-1510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.1.21.1.6 Pipe Supports Fabrication & InstallationCCOH52SS60 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Pipe Supports | HS-CN-0690 | C-52-PL-838-CI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.3.1.3.1.21.1.6 Pipe Supports Fabrication & InstallationCCOH52SS60 | Final Issue for Design/ Construction-Misc. supports | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1490 | C-52-PL-838-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.1.21.1.6 Pipe Supports Fabrication & InstallationCCOH52SS60 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0110 | C-52-PL-838-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.3.1.3.1.21.1.6 Pipe Supports Fabrication & InstallationCCOH52SS60 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1430 | C-52-PL-838-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.1.21.1.7 Trenching for Electrical cablesCCOH52CS35.1 | Final Issue for Design/ Construction-Civil UG layout | Electrical & Earthing Cable Trenching | HE-CS-0530 | C-52-PL-838-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.3.1.21.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOH52SS61 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Platforms & Crossovers | HS-CN-0690 | C-52-PL-838-CI-3000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.1.21.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOH52SS61 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0110 | C-52-PL-838-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.1.21.1.9 Trenching for Instrument cablesCCOH52CS35.2 | Final Issue for Design/ Construction-Civil UG layout | Instrument & Telecom Cable Trenching | HE-CS-0530 | C-52-PL-838-CI-1810 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.1.21.1.10 Paving WorksCCOH52CS36 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-52-PL-838-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.3.1.21.1.10 Paving WorksCCOH52CS36 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-52-PL-838-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.3.1 Installation of Pig Launcher (838-V-602)CCOH52ME60 | Receipt at site and inspection of Pig Launchers & Receivers (52" Line) | Installation of Pig Launcher (838-V-602) 52" | HM-ME-0480 | C-52-PL-838-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.1.21.3.1 Installation of Pig Launcher (838-V-602)CCOH52ME60 | Receive at Site - Pig Launcher & Receiver | Installation of Pig Launcher (838-V-602) 52" | ML1519-D04 | C-52-PL-838-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.1.21.3.1 Installation of Pig Launcher (838-V-602)CCOH52ME60 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Installation of Pig Launcher (838-V-602) 52" | ML1015-B08 | C-52-PL-838-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.3.2 Installation of Pig Signaler (838-V-602)CCOH52ME70 | Receipt at site and inspection of Pig Signaler (Lot 1) | Installation of Pig Signaler (838-V-602) | HM-PL-0530 | C-52-PL-838-ME-1200 | FF | Not Started | Not Started | 12
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.1.21.3.2 Installation of Pig Signaler (838-V-602)CCOH52ME70 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Installation of Pig Signaler (838-V-602) | ML1015-B08 | C-52-PL-838-ME-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.3.2 Installation of Pig Signaler (838-V-602)CCOH52ME70 | Receipt at site and inspection of Pigging & Split Tee (Lot 1) | Installation of Pig Signaler (838-V-602) | HM-PL-0840 | C-52-PL-838-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.3.2 Installation of Pig Signaler (838-V-602)CCOH52ME70 | Receipt at site and inspection of Pig Signaler (Lot 2) | Installation of Pig Signaler (838-V-602) | HM-PL-1490 | C-52-PL-838-ME-1200 | FF | Not Started | Not Started | 12
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.3.2 Installation of Pig Signaler (838-V-602)CCOH52ME70 | Receipt at site and inspection of Pigging & Split Tee (Lot 2) | Installation of Pig Signaler (838-V-602) | HM-PL-1530 | C-52-PL-838-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.1.21.4.1 Piping Works -FabricationCCOH52PI60.1 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-52-PL-838-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.4.1 Piping Works -FabricationCCOH52PI60.1 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Pre-Fabrication | HM-PL-0740 | C-52-PL-838-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.1.21.4.1 Piping Works -FabricationCCOH52PI60.1 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-52-PL-838-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.1.21.4.1 Piping Works -FabricationCCOH52PI60.1 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-52-PL-838-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.1.21.4.1 Piping Works -FabricationCCOH52PI60.1 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-52-PL-838-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.1.21.4.1 Piping Works -FabricationCCOH52PI60.1 | NDT / PWHT Subcontract Award | Piping Pre-Fabrication | HS-CN-0190 | C-52-PL-838-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.1.21.4.1 Piping Works -FabricationCCOH52PI60.1 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Pre-Fabrication | HE-PR-0290 | C-52-PL-838-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.4.1 Piping Works -FabricationCCOH52PI60.1 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Pre-Fabrication | HM-PL-0640 | C-52-PL-838-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.4.1 Piping Works -FabricationCCOH52PI60.1 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Pre-Fabrication | HM-PL-0220 | C-52-PL-838-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.4.1 Piping Works -FabricationCCOH52PI60.1 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Pre-Fabrication | HM-PL-0630 | C-52-PL-838-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.1.21.4.1 Piping Works -FabricationCCOH52PI60.1 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-52-PL-838-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.1.21.4.1 Piping Works -FabricationCCOH52PI60.1 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Pre-Fabrication | ML1179-B11 | C-52-PL-838-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.4.1 Piping Works -FabricationCCOH52PI60.1 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Pre-Fabrication | HM-PL-1510 | C-52-PL-838-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.4.1 Piping Works -FabricationCCOH52PI60.1 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Pre-Fabrication | HM-PL-1570 | C-52-PL-838-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Project Kick off Meeting | Piping Erection | ML1002 | C-52-PL-838-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Erection | HM-PL-0740 | C-52-PL-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Erection | ML1219-B19 | C-52-PL-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Piping MTO - Final | Piping Erection | HE-PI-1300 | C-52-PL-838-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Final Issue for Design/ Construction-Piping Isometrics | Piping Erection | HE-PI-1240 | C-52-PL-838-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | NDT / PWHT Subcontract Award | Piping Erection | HS-CN-0190 | C-52-PL-838-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Final Issue for Design/ Construction-Tie-In Schedule | Piping Erection | HE-PR-0290 | C-52-PL-838-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Erection | HM-PL-0640 | C-52-PL-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Erection | HM-PL-0220 | C-52-PL-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Erection | HM-PL-0630 | C-52-PL-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | 1st Piping Bulk material MTO | Piping Erection | HM-PI-0040 | C-52-PL-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Issue Plot Plans, Equipment Layouts and Piping Layouts for all Stations (52" Sales Gas pipeline) - IFC | Piping Erection | ML1179-B11 | C-52-PL-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Erection | HM-PL-1510 | C-52-PL-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Erection | HM-PL-1570 | C-52-PL-838-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Deep Earth Well Drilling | HE-EL-1010 | C-52-PL-838-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-I/O list | Deep Earth Well Drilling | HE-IC-0590 | C-52-PL-838-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Deep Earth Well Drilling | HE-IC-1550 | C-52-PL-838-EI-1400 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Issue ICR-Instrument index -Update | Deep Earth Well Drilling | HE-IC-0490 | C-52-PL-838-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Instrument Index | Deep Earth Well Drilling | HE-IC-0530 | C-52-PL-838-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | 1st Instrumentation Bulk material MTO | Deep Earth Well Drilling | HM-IC-0040 | C-52-PL-838-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Earthing Layout | Deep Earth Well Drilling | HE-EL-1670 | C-52-PL-838-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Typical Installation Drawings | Deep Earth Well Drilling | HE-IC-0710 | C-52-PL-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Loop Diagrams | Deep Earth Well Drilling | HE-IC-0770 | C-52-PL-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Earthing Material (Lot 1) | Deep Earth Well Drilling | HM-EL-0380 | C-52-PL-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Obtain Company Approval-Data sheet for LV Distribution board | Deep Earth Well Drilling | HE-EL-0640 | C-52-PL-838-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-0280 | C-52-PL-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Deep Earth Well Drilling | HE-IC-1430 | C-52-PL-838-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1590 | C-52-PL-838-EI-1400 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | 1st Electrical Bulk material MTO | Deep Earth Well Drilling | HM-EL-0520 | C-52-PL-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Lighting Layout | Deep Earth Well Drilling | HE-EL-1730 | C-52-PL-838-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Electrical Installation Drawings | Deep Earth Well Drilling | HE-EL-1790 | C-52-PL-838-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Deep Earth Well Drilling | HM-ME-1690 | C-52-PL-838-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Deep Earth Well Drilling | ML1032-B21 | C-52-PL-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Deep Earth Well Drilling | HM-EL-0080 | C-52-PL-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Deep Earth Well Drilling | HE-IC-2570 | C-52-PL-838-EI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Issue ICR- Addendum to DGs | Deep Earth Well Drilling | HE-IC-0010 | C-52-PL-838-EI-1400 | SS | Completed | Not Started | 10
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Hook-Up Diagram | Deep Earth Well Drilling | HE-IC-0650 | C-52-PL-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Electrical Equipment Layout | Deep Earth Well Drilling | HE-EL-0530 | C-52-PL-838-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Issue ICR- P&ID's | Deep Earth Well Drilling | HE-PR-0110 | C-52-PL-838-EI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Deep Earth Well Drilling | HM-ME-2330 | C-52-PL-838-EI-1400 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Deep Earth Well Drilling | HM-ME-2350 | C-52-PL-838-EI-1400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Deep Earth Well Drilling | HM-EL-630 | C-52-PL-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Cable Trays (Lot 2) | Deep Earth Well Drilling | HM-EL-650 | C-52-PL-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Earthing Material (Lot 2) | Deep Earth Well Drilling | HM-EL-690 | C-52-PL-838-EI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Electrical & Earthing Cable Laying | HE-EL-1010 | C-52-PL-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-I/O list | Electrical & Earthing Cable Laying | HE-IC-0590 | C-52-PL-838-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Electrical & Earthing Cable Laying | HE-IC-1550 | C-52-PL-838-EI-2000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Issue ICR-Instrument index -Update | Electrical & Earthing Cable Laying | HE-IC-0490 | C-52-PL-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Instrument Index | Electrical & Earthing Cable Laying | HE-IC-0530 | C-52-PL-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | 1st Instrumentation Bulk material MTO | Electrical & Earthing Cable Laying | HM-IC-0040 | C-52-PL-838-EI-2000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Earthing Layout | Electrical & Earthing Cable Laying | HE-EL-1670 | C-52-PL-838-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Typical Installation Drawings | Electrical & Earthing Cable Laying | HE-IC-0710 | C-52-PL-838-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Loop Diagrams | Electrical & Earthing Cable Laying | HE-IC-0770 | C-52-PL-838-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Earthing Material (Lot 1) | Electrical & Earthing Cable Laying | HM-EL-0380 | C-52-PL-838-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Obtain Company Approval-Data sheet for LV Distribution board | Electrical & Earthing Cable Laying | HE-EL-0640 | C-52-PL-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Cable Trays (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-0280 | C-52-PL-838-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Electrical & Earthing Cable Laying | HE-IC-1430 | C-52-PL-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | 1st Electrical Bulk material MTO | Electrical & Earthing Cable Laying | HM-EL-0520 | C-52-PL-838-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Lighting Layout | Electrical & Earthing Cable Laying | HE-EL-1730 | C-52-PL-838-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Electrical Installation Drawings | Electrical & Earthing Cable Laying | HE-EL-1790 | C-52-PL-838-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Electrical & Earthing Cable Laying | HM-ME-1690 | C-52-PL-838-EI-2000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Electrical & Earthing Cable Laying | ML1032-B21 | C-52-PL-838-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Electrical & Earthing Cable Laying | HM-EL-0080 | C-52-PL-838-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Electrical & Earthing Cable Laying | HE-IC-2570 | C-52-PL-838-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Issue ICR- Addendum to DGs | Electrical & Earthing Cable Laying | HE-IC-0010 | C-52-PL-838-EI-2000 | SS | Completed | Not Started | 10
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Hook-Up Diagram | Electrical & Earthing Cable Laying | HE-IC-0650 | C-52-PL-838-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Final Issue for Design/ Construction-Electrical Equipment Layout | Electrical & Earthing Cable Laying | HE-EL-0530 | C-52-PL-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Issue ICR- P&ID's | Electrical & Earthing Cable Laying | HE-PR-0110 | C-52-PL-838-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Electrical & Earthing Cable Laying | HM-ME-2330 | C-52-PL-838-EI-2000 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Electrical & Earthing Cable Laying | HM-ME-2350 | C-52-PL-838-EI-2000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-630 | C-52-PL-838-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Cable Trays (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-650 | C-52-PL-838-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.1 DB & Electrical WorksCCOH52EL50 | Receipt at site and inspection of Earthing Material (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-690 | C-52-PL-838-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Instrument Cable Laying | HE-IC-0950 | C-52-PL-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Instrument Cable Laying | HM-EL-0080 | C-52-PL-838-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Final Issue for Design/ Construction-Instrument Trench Layout | Instrument Cable Laying | HE-IC-1010 | C-52-PL-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Final Issue for Design/ Construction-Cable Schedule | Instrument Cable Laying | HE-EL-0590 | C-52-PL-838-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Final Issue for Design/ Construction-Cable Routing Layout | Instrument Cable Laying | HE-EL-1610 | C-52-PL-838-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Final Issue for Design/ Construction-Cable Sizing Calculation | Instrument Cable Laying | HE-EL-0470 | C-52-PL-838-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Final Issue for Design/ Construction-Data Sheet for LV cables | Instrument Cable Laying | HE-EL-0830 | C-52-PL-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | 1st Electrical Bulk material MTO | Instrument Cable Laying | HM-EL-0520 | C-52-PL-838-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Instrument Cable Laying | HE-IC-0830 | C-52-PL-838-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Final Issue for Design/ Construction-Data Sheet for HV cables | Instrument Cable Laying | HE-EL-1950 | C-52-PL-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Final Issue for Design/ Construction-Specification for RTU | Instrument Cable Laying | HE-IC-0230 | C-52-PL-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Final Issue for Design/ Construction-Specification for Leak Detection System | Instrument Cable Laying | HE-IC-0290 | C-52-PL-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Final Issue for Design/ Construction-I/O list | Instrument Cable Laying | HE-IC-0590 | C-52-PL-838-EI-2010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Re-Issue for Approval- I/O list -Update | Instrument Cable Laying | HE-IC-0570 | C-52-PL-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Re-Issue for Approval- Specification for RTU | Instrument Cable Laying | HE-IC-0210 | C-52-PL-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Re-Issue for Approval- Specification for Leak Detection System | Instrument Cable Laying | HE-IC-0270 | C-52-PL-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Issue ICR- Instrument Cable Block Diagram | Instrument Cable Laying | HE-IC-0790 | C-52-PL-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Issue ICR- Specification for Leak Detection System | Instrument Cable Laying | HE-IC-0250 | C-52-PL-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Issue ICR- Specification for RTU | Instrument Cable Laying | HE-IC-0190 | C-52-PL-838-EI-2010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Instrument Cable Laying | HM-EL-630 | C-52-PL-838-EI-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.7.1 CP Anode Bed Installation (subcontract)CCOH52EL52 | Receipt at site and inspection of CP System - Permanent Material | CP Cable Laying | HM-PL-0430 | C-52-PL-838-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.1.21.7.1 CP Anode Bed Installation (subcontract)CCOH52EL52 | CP Drilling & Earthing Drilling Subcontract Award | CP Cable Laying | HS-CN-0240 | C-52-PL-838-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.8.1 SDH CabinetCCOH52IC60 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | SDH Cabinet (Deleted) | HM-ME-1290 | C-52-PL-838-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..4.3.1.3.1.21.8.1 SDH CabinetCCOH52IC60 | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | SDH Cabinet (Deleted) | HE-IC-0110 | C-52-PL-838-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.3.1.21.8.1 SDH CabinetCCOH52IC60 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | SDH Cabinet (Deleted) | HE-TL-0470 | C-52-PL-838-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.1.21.8.1 SDH CabinetCCOH52IC60 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | SDH Cabinet (Deleted) | ML1033-B22 | C-52-PL-838-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.3.1.21.8.1 SDH CabinetCCOH52IC60 | Final Issue for Design/ Construction-Telecom Equipment Layout | SDH Cabinet (Deleted) | HE-TL-0770 | C-52-PL-838-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.1.21.8.1 SDH CabinetCCOH52IC60 | 1st Telecom Bulk material MTO | SDH Cabinet (Deleted) | HM-TL-0040 | C-52-PL-838-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.1.21.8.1 SDH CabinetCCOH52IC60 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | SDH Cabinet (Deleted) | HE-TL-0710 | C-52-PL-838-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.3.1.21.8.1 SDH CabinetCCOH52IC60 | Final Issue for Design/ Construction-Telecom cable schedule | SDH Cabinet (Deleted) | HE-TL-0830 | C-52-PL-838-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.3.1.21.8.1 SDH CabinetCCOH52IC60 | FOC Splicing / Termination Subcontract Award | SDH Cabinet (Deleted) | HS-CN-0290 | C-52-PL-838-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.8.1 SDH CabinetCCOH52IC60 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | SDH Cabinet (Deleted) | HM-ME-2270 | C-52-PL-838-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-52-IDS1-CI-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-52-IDS1-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Site Survey, Preparation & Grading Works | CTF-1000 | C-52-IDS1-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Site Survey, Preparation & Grading Works | ML1034-B25 | C-52-IDS1-CI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-52-IDS1-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Site Survey, Preparation & Grading Works | HE-CS-0470 | C-52-IDS1-CI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.7.4.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS38 | NOC's / Approval /Survey | Site Survey, Preparation & Grading Works | CTF-1010 | C-52-IDS1-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Solar S/m Foundation | ML1034-B25 | C-52-IDS1-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | Final Civil Bulk material MTO | Concrete Works for Solar S/m Foundation | HM-CS-0050 | C-52-IDS1-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | 1st Civil Bulk material MTO | Concrete Works for Solar S/m Foundation | HM-CS-0040 | C-52-IDS1-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Solar S/m Foundation | HE-CS-0230 | C-52-IDS1-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for CCTV Pole, Fence & Gates Foundation | ML1034-B25 | C-52-IDS1-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | Final Civil Bulk material MTO | Concrete Works for CCTV Pole, Fence & Gates Foundation | HM-CS-0050 | C-52-IDS1-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | 1st Civil Bulk material MTO | Concrete Works for CCTV Pole, Fence & Gates Foundation | HM-CS-0040 | C-52-IDS1-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.7.4.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS40 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for CCTV Pole, Fence & Gates Foundation | HE-CS-0230 | C-52-IDS1-CI-1420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.3.7.4.21.1.5 Fences & Gates ConstructionCCOH52CS42 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Installation of Fence Post & Mesh Works (Type-3) | HE-CS-0350 | C-52-IDS1-CI-2220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.7.4.21.1.5 Fences & Gates ConstructionCCOH52CS42 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Installation of Fence Post & Mesh Works (Type-3) | HE-CS-0470 | C-52-IDS1-CI-2220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.7.4.21.1.6 Trenching for CablesCCOH52CS43 | Final Issue for Design/ Construction-Civil UG layout | Electrical & Earthing Cable Trenching | HE-CS-0530 | C-52-IDS1-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.3.7.4.21.1.7 Paving WorksCCOH52CS44 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-52-IDS1-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.7.4.21.1.7 Paving WorksCCOH52CS44 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-52-IDS1-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.5 CP Drilling & Earthing Drilling | P2543-R01-Oct24..4.3.1.3.7.4.21.2.1 Electrical Works for Drilling for Earth Rod / Deep Well SubcontractCCOH52EL20 | CP Drilling & Earthing Drilling Subcontract Award | Electrical & Earthing Cable Laying | HS-CN-0240 | C-52-IDS1-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | Final Issue for Design/ Construction-Telecom cable schedule | Installation of CCTV Poles | HE-TL-0830 | C-52-IDS1-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Installation of CCTV Poles | HE-TL-0290 | C-52-IDS1-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Installation of CCTV Poles | HE-TL-0710 | C-52-IDS1-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Installation of CCTV Poles | HE-TL-0470 | C-52-IDS1-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Installation of CCTV Poles | HE-TL-0350 | C-52-IDS1-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Installation of CCTV Poles | HM-ME-1290 | C-52-IDS1-TE-1590 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | Final Issue for Design/ Construction-Telecom Equipment Layout | Installation of CCTV Poles | HE-TL-0770 | C-52-IDS1-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Installation of CCTV Poles | HE-TL-0410 | C-52-IDS1-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | 1st Telecom Bulk material MTO | Installation of CCTV Poles | HM-TL-0040 | C-52-IDS1-TE-1590 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.7.4.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC30 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Installation of CCTV Poles | HM-ME-2270 | C-52-IDS1-TE-1590 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-52-IDS2-CI-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-52-IDS2-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-52-IDS2-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Site Survey, Preparation & Grading Works | CTF-1000 | C-52-IDS2-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Site Survey, Preparation & Grading Works | ML1034-B25 | C-52-IDS2-CI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Site Survey, Preparation & Grading Works | HE-CS-0470 | C-52-IDS2-CI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.7.6.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS46 | NOC's / Approval /Survey | Site Survey, Preparation & Grading Works | CTF-1010 | C-52-IDS2-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Solar S/m Foundation | HE-CS-0230 | C-52-IDS2-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Solar S/m Foundation | ML1034-B25 | C-52-IDS2-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | 1st Civil Bulk material MTO | Concrete Works for Solar S/m Foundation | HM-CS-0040 | C-52-IDS2-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | Final Civil Bulk material MTO | Concrete Works for Solar S/m Foundation | HM-CS-0050 | C-52-IDS2-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for CCTV Pole, Fence & Gates Foundation | HE-CS-0230 | C-52-IDS2-CI-1420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for CCTV Pole, Fence & Gates Foundation | ML1034-B25 | C-52-IDS2-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | 1st Civil Bulk material MTO | Concrete Works for CCTV Pole, Fence & Gates Foundation | HM-CS-0040 | C-52-IDS2-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.7.6.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS48 | Final Civil Bulk material MTO | Concrete Works for CCTV Pole, Fence & Gates Foundation | HM-CS-0050 | C-52-IDS2-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.3.7.6.21.1.5 Fences & Gates ConstructionCCOH52CS50 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Installation of Fence Post & Mesh Works (Type-3) | HE-CS-0350 | C-52-IDS2-CI-2220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.7.6.21.1.5 Fences & Gates ConstructionCCOH52CS50 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Installation of Fence Post & Mesh Works (Type-3) | HE-CS-0470 | C-52-IDS2-CI-2220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.7.6.21.1.6 Trenching for CablesCCOH52CS51 | Final Issue for Design/ Construction-Civil UG layout | Electrical & Earthing Cable Trenching | HE-CS-0530 | C-52-IDS2-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.7.6.21.1.7 Paving WorksCCOH52CS52 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-52-IDS2-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.3.7.6.21.1.7 Paving WorksCCOH52CS52 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-52-IDS2-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Installation of CCTV Poles | HE-TL-0470 | C-52-IDS2-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Installation of CCTV Poles | HE-TL-0350 | C-52-IDS2-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | 1st Telecom Bulk material MTO | Installation of CCTV Poles | HM-TL-0040 | C-52-IDS2-TE-1590 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Installation of CCTV Poles | HE-TL-0710 | C-52-IDS2-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Installation of CCTV Poles | HM-ME-1290 | C-52-IDS2-TE-1590 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | Final Issue for Design/ Construction-Telecom Equipment Layout | Installation of CCTV Poles | HE-TL-0770 | C-52-IDS2-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | Final Issue for Design/ Construction-Telecom cable schedule | Installation of CCTV Poles | HE-TL-0830 | C-52-IDS2-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Installation of CCTV Poles | HE-TL-0290 | C-52-IDS2-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Installation of CCTV Poles | HE-TL-0410 | C-52-IDS2-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.7.6.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC32 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Installation of CCTV Poles | HM-ME-2270 | C-52-IDS2-TE-1590 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-52-IDS3-CI-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-52-IDS3-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Site Survey, Preparation & Grading Works | ML1034-B25 | C-52-IDS3-CI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Site Survey, Preparation & Grading Works | HE-CS-0470 | C-52-IDS3-CI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Site Survey, Preparation & Grading Works | CTF-1000 | C-52-IDS3-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-52-IDS3-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.7.5.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS54 | NOC's / Approval /Survey | Site Survey, Preparation & Grading Works | CTF-1010 | C-52-IDS3-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | Final Civil Bulk material MTO | Concrete Works for Solar S/m Foundation | HM-CS-0050 | C-52-IDS3-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for Solar S/m Foundation | ML1034-B25 | C-52-IDS3-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Solar S/m Foundation | HE-CS-0230 | C-52-IDS3-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | 1st Civil Bulk material MTO | Concrete Works for Solar S/m Foundation | HM-CS-0040 | C-52-IDS3-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | Final Civil Bulk material MTO | Concrete Works for CCTV Pole, Fence & Gates Foundation | HM-CS-0050 | C-52-IDS3-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | Issue Civil / Structural Drawings for all facilities at Block Valve Stations (52" Pipeline) - IFC | Concrete Works for CCTV Pole, Fence & Gates Foundation | ML1034-B25 | C-52-IDS3-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for CCTV Pole, Fence & Gates Foundation | HE-CS-0230 | C-52-IDS3-CI-1420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.7.5.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS56 | 1st Civil Bulk material MTO | Concrete Works for CCTV Pole, Fence & Gates Foundation | HM-CS-0040 | C-52-IDS3-CI-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.3.7.5.21.1.5 Fences & Gates ConstructionCCOH52CS58 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Installation of Fence Post & Mesh Works (Type-3) | HE-CS-0350 | C-52-IDS3-CI-2220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.7.5.21.1.5 Fences & Gates ConstructionCCOH52CS58 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Installation of Fence Post & Mesh Works (Type-3) | HE-CS-0470 | C-52-IDS3-CI-2220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.3.7.5.21.1.6 Trenching for CablesCCOH52CS59 | Final Issue for Design/ Construction-Civil UG layout | Electrical & Earthing Cable Trenching | HE-CS-0530 | C-52-IDS3-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.3.7.5.21.1.7 Paving WorksCCOH52CS60 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-52-IDS3-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.3.7.5.21.1.7 Paving WorksCCOH52CS60 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-52-IDS3-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21 Block Diagram for Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) | P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | Final Issue for Design/ Construction-Telecom System (CCTC, Telephone, LAC, SDH, PIDS, IDS, etc.) | Installation of CCTV Poles | HE-TL-0290 | C-52-IDS3-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | Final Issue for Design/ Construction-Telecom Equipment Layout | Installation of CCTV Poles | HE-TL-0770 | C-52-IDS3-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | 1st Telecom Bulk material MTO | Installation of CCTV Poles | HM-TL-0040 | C-52-IDS3-TE-1590 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Installation of CCTV Poles | HE-TL-0710 | C-52-IDS3-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A211 Overall Telecom Block Diagram | P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | Final Issue for Design/ Construction-Overall Telecom Block Diagram | Installation of CCTV Poles | HE-TL-0350 | C-52-IDS3-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 1) | Installation of CCTV Poles | HM-ME-1290 | C-52-IDS3-TE-1590 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | Final Issue for Design/ Construction-Telecom cable schedule | Installation of CCTV Poles | HE-TL-0830 | C-52-IDS3-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Installation of CCTV Poles | HE-TL-0470 | C-52-IDS3-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A2111 Telecom Tie-in Block Diagram | P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | Final Issue for Design/ Construction-Telecom Tie-in Block Diagram | Installation of CCTV Poles | HE-TL-0410 | C-52-IDS3-TE-1590 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.4.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.7.5.21.3.1 IDS and CCTV (including subcontract for FOC Splicing / Termination / Testing )CCOH52IC63 | Receipt at site and inspection of Telecom System (CCTV, Telephone, LAN, SDH, PIDS, IDS etc) (Lot 2) | Installation of CCTV Poles | HM-ME-2270 | C-52-IDS3-TE-1590 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.2 Survey & Studies | P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | Topographical Survey | Site Survey, Preparation & Grading Works | HE-SS-0030 | C-36-KM-HT-CI-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | Project Kick off Meeting | Site Survey, Preparation & Grading Works | ML1002 | C-36-KM-HT-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Site Survey, Preparation & Grading Works | HE-CS-0470 | C-36-KM-HT-CI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Site Survey, Preparation & Grading Works | CTF-1000 | C-36-KM-HT-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | Final Issue for Design/ Construction-Typical trench detail drawing | Site Survey, Preparation & Grading Works | HE-CS-0170 | C-36-KM-HT-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.4.12.1.1 Excavation (incl Bedding)CCOJ42CS20 | NOC's / Approval /Survey | Site Survey, Preparation & Grading Works | CTF-1010 | C-36-KM-HT-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.4.12.1.3 Concrete Pit (For Hot Tapping)CCOJ42CS24 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Hot Tap Tie in Pit | HE-CS-0230 | CCV-52-KM-1120 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.4.12.1.3 Concrete Pit (For Hot Tapping)CCOJ42CS24 | Final Civil Bulk material MTO | Concrete Works for Hot Tap Tie in Pit | HM-CS-0050 | CCV-52-KM-1120 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.4.12.1.3 Concrete Pit (For Hot Tapping)CCOJ42CS24 | 1st Civil Bulk material MTO | Concrete Works for Hot Tap Tie in Pit | HM-CS-0040 | CCV-52-KM-1120 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.3.1.4.12.1.3 Concrete Pit (For Hot Tapping)CCOJ42CS24 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Concrete Works for Hot Tap Tie in Pit | HE-CS-1190 | CCV-52-KM-1120 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.17 Typical details of protection slab to protect existing UG pipe at road crossing | P2543-R01-Oct24..4.3.1.4.12.1.3 Concrete Pit (For Hot Tapping)CCOJ42CS24 | Final Issue for Design/ Construction-Typical details of protection slab to protect existing UG pipe at road crossing | Concrete Works for Hot Tap Tie in Pit | HE-CS-0410 | CCV-52-KM-1120 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.4.12.1.4 Concrete Works (Foundations for Equipment)CCOJ42CS44 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Field Instrument, JBs | HE-CS-0230 | C-36-KM-HT-CI-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.4.12.1.4 Concrete Works (Foundations for Equipment)CCOJ42CS44 | Final Civil Bulk material MTO | Concrete Works for Field Instrument, JBs | HM-CS-0050 | C-36-KM-HT-CI-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.4.12.1.4 Concrete Works (Foundations for Equipment)CCOJ42CS44 | 1st Civil Bulk material MTO | Concrete Works for Field Instrument, JBs | HM-CS-0040 | C-36-KM-HT-CI-1410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.4.12.1.6 Trenching for CablesCCOJ42CS30 | Final Issue for Design/ Construction-Civil UG layout | Electrical & Earthing Cable Trenching | HE-CS-0530 | C-36-KM-HT-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.4.12.1.7 Pipe Supports Fabrication & InstallationCCOJ42SS70 | Final Structural Bulk material MTO | Pipe Supports Fabrication & Installation | HM-CS-0120 | C-36-KM-HT-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.3.1.4.12.1.7 Pipe Supports Fabrication & InstallationCCOJ42SS70 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Pipe Supports Fabrication & Installation | HE-CS-1430 | C-36-KM-HT-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.4.12.1.7 Pipe Supports Fabrication & InstallationCCOJ42SS70 | Fence Works Subcontract Award | Pipe Supports Fabrication & Installation | HS-CN-0690 | C-36-KM-HT-CI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.4.12.1.7 Pipe Supports Fabrication & InstallationCCOJ42SS70 | 1st Structural Bulk material MTO | Pipe Supports Fabrication & Installation | HM-CS-0110 | C-36-KM-HT-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.3.1.4.12.1.7 Pipe Supports Fabrication & InstallationCCOJ42SS70 | Final Issue for Design/ Construction-Misc. supports | Pipe Supports Fabrication & Installation | HE-CS-1490 | C-36-KM-HT-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.4.12.1.8 Fences & Gates ConstructionCCOJ42CS26 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Fences & Gates Construction | HE-CS-0470 | C-36-KM-HT-CI-2220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.4.12.1.8 Fences & Gates ConstructionCCOJ42CS26 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Fences & Gates Construction | HE-CS-0350 | C-36-KM-HT-CI-2220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.4.12.1.9 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOJ42SS72 | 1st Structural Bulk material MTO | Platforms/Crossovers/ Guardrails and Bollards/ Windsock | HM-CS-0110 | C-36-KM-HT-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.4.12.1.9 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOJ42SS72 | Fence Works Subcontract Award | Platforms/Crossovers/ Guardrails and Bollards/ Windsock | HS-CN-0690 | C-36-KM-HT-CI-3000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.4.12.1.11 Paving WorksCCOJ42CS32 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-36-KM-HT-CI-2600 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.4.12.1.11 Paving WorksCCOJ42CS32 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-36-KM-HT-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.4.12.2.1 Piping Pre-FabricationCCOJ42PI070 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-36-KM-HT-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.4.12.2.1 Piping Pre-FabricationCCOJ42PI070 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-36-KM-HT-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.4.12.2.1 Piping Pre-FabricationCCOJ42PI070 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-36-KM-HT-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.4.12.2.1 Piping Pre-FabricationCCOJ42PI070 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-36-KM-HT-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.4.12.2.1 Piping Pre-FabricationCCOJ42PI070 | NDT / PWHT Subcontract Award | Piping Pre-Fabrication | HS-CN-0190 | C-36-KM-HT-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.4.12.2.1 Piping Pre-FabricationCCOJ42PI070 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-36-KM-HT-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.2.2 ErectionCCOJ42PI082 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Erection | HM-PL-0630 | C-36-KM-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.4.12.2.2 ErectionCCOJ42PI082 | Final Issue for Design/ Construction-Piping Isometrics | Piping Erection | HE-PI-1240 | C-36-KM-HT-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.4.12.2.2 ErectionCCOJ42PI082 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Erection | ML1219-B19 | C-36-KM-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.4.12.2.2 ErectionCCOJ42PI082 | Piping MTO - Final | Piping Erection | HE-PI-1300 | C-36-KM-HT-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.2.2 ErectionCCOJ42PI082 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Erection | HM-PL-0640 | C-36-KM-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.2.2 ErectionCCOJ42PI082 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Erection | HM-PL-0740 | C-36-KM-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.2.2 ErectionCCOJ42PI082 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Erection | HM-PL-0220 | C-36-KM-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.4.12.2.2 ErectionCCOJ42PI082 | 1st Piping Bulk material MTO | Piping Erection | HM-PI-0040 | C-36-KM-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.2.2 ErectionCCOJ42PI082 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Erection | HM-PL-1510 | C-36-KM-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.2.2 ErectionCCOJ42PI082 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Erection | HM-PL-1570 | C-36-KM-HT-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.4.12.2.3 Field Joint Welding, NDT & CoatingCCOJ42PI092 | Project Kick off Meeting | Field Joint Welding | ML1002 | C-36-KM-HT-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.2.3 Field Joint Welding, NDT & CoatingCCOJ42PI092 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Field Joint Welding | HM-PL-0630 | C-36-KM-HT-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.4.12.2.3 Field Joint Welding, NDT & CoatingCCOJ42PI092 | Final Issue for Design/ Construction-Piping Isometrics | Field Joint Welding | HE-PI-1240 | C-36-KM-HT-PI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.4.12.2.3 Field Joint Welding, NDT & CoatingCCOJ42PI092 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Field Joint Welding | ML1219-B19 | C-36-KM-HT-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.4.12.2.3 Field Joint Welding, NDT & CoatingCCOJ42PI092 | Piping MTO - Final | Field Joint Welding | HE-PI-1300 | C-36-KM-HT-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.2.3 Field Joint Welding, NDT & CoatingCCOJ42PI092 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Field Joint Welding | HM-PL-0640 | C-36-KM-HT-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.4.12.2.3 Field Joint Welding, NDT & CoatingCCOJ42PI092 | NDT / PWHT Subcontract Award | Field Joint Welding | HS-CN-0190 | C-36-KM-HT-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.2.3 Field Joint Welding, NDT & CoatingCCOJ42PI092 | Receipt at site and inspection of Isolating Joints (Lot 1) | Field Joint Welding | HM-PL-0740 | C-36-KM-HT-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.4.12.2.3 Field Joint Welding, NDT & CoatingCCOJ42PI092 | 1st Piping Bulk material MTO | Field Joint Welding | HM-PI-0040 | C-36-KM-HT-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.2.3 Field Joint Welding, NDT & CoatingCCOJ42PI092 | Receipt at site and inspection of Isolating Joints (Lot 2) | Field Joint Welding | HM-PL-1510 | C-36-KM-HT-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.4.12.2.4 HydrotestingCCOJ42PI102 | Final Issue for Design/ Construction-Piping Isometrics | Hydrotesting | HE-PI-1240 | C-36-KM-HT-PI-1600 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.4.12.2.4 HydrotestingCCOJ42PI102 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Hydrotesting | ML1219-B19 | C-36-KM-HT-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.4.12.2.5 Installation of ValvesCCOJ42PI112 | Final Issue for Design/ Construction-Piping Isometrics | Installation of Valves/GOV/ROV | HE-PI-1240 | C-36-KM-HT-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.4.12.2.5 Installation of ValvesCCOJ42PI112 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Installation of Valves/GOV/ROV | ML1219-B19 | C-36-KM-HT-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.4.12.2.6 Final Bolt Torquing/ Re-InstatementCCOJ42PI122 | Project Kick off Meeting | Final Bolt Torquing/ Re-Instatement | ML1002 | C-36-KM-HT-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.2.6 Final Bolt Torquing/ Re-InstatementCCOJ42PI122 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0630 | C-36-KM-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.4.12.2.6 Final Bolt Torquing/ Re-InstatementCCOJ42PI122 | Final Issue for Design/ Construction-Piping Isometrics | Final Bolt Torquing/ Re-Instatement | HE-PI-1240 | C-36-KM-HT-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.4.12.2.6 Final Bolt Torquing/ Re-InstatementCCOJ42PI122 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Final Bolt Torquing/ Re-Instatement | ML1219-B19 | C-36-KM-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.4.12.2.6 Final Bolt Torquing/ Re-InstatementCCOJ42PI122 | Piping MTO - Final | Final Bolt Torquing/ Re-Instatement | HE-PI-1300 | C-36-KM-HT-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.2.6 Final Bolt Torquing/ Re-InstatementCCOJ42PI122 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0640 | C-36-KM-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.2.6 Final Bolt Torquing/ Re-InstatementCCOJ42PI122 | Receipt at site and inspection of Isolating Joints (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0740 | C-36-KM-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.2.6 Final Bolt Torquing/ Re-InstatementCCOJ42PI122 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0220 | C-36-KM-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.4.12.2.6 Final Bolt Torquing/ Re-InstatementCCOJ42PI122 | 1st Piping Bulk material MTO | Final Bolt Torquing/ Re-Instatement | HM-PI-0040 | C-36-KM-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.2.6 Final Bolt Torquing/ Re-InstatementCCOJ42PI122 | Receipt at site and inspection of Isolating Joints (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1510 | C-36-KM-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.2.6 Final Bolt Torquing/ Re-InstatementCCOJ42PI122 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1570 | C-36-KM-HT-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Final Issue for Design/ Construction-Cable Schedule | Electrical & Earthing Cable Laying | HE-EL-0590 | C-36-KM-HT-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Final Issue for Design/ Construction-Instrument Trench Layout | Electrical & Earthing Cable Laying | HE-IC-1010 | C-36-KM-HT-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Electrical & Earthing Cable Laying | HM-EL-0080 | C-36-KM-HT-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Electrical & Earthing Cable Laying | HE-IC-0950 | C-36-KM-HT-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Final Issue for Design/ Construction-Data Sheet for LV cables | Electrical & Earthing Cable Laying | HE-EL-0830 | C-36-KM-HT-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Final Issue for Design/ Construction-Cable Sizing Calculation | Electrical & Earthing Cable Laying | HE-EL-0470 | C-36-KM-HT-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0830 | C-36-KM-HT-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | 1st Electrical Bulk material MTO | Electrical & Earthing Cable Laying | HM-EL-0520 | C-36-KM-HT-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Final Issue for Design/ Construction-Cable Routing Layout | Electrical & Earthing Cable Laying | HE-EL-1610 | C-36-KM-HT-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Final Issue for Design/ Construction-Data Sheet for HV cables | Electrical & Earthing Cable Laying | HE-EL-1950 | C-36-KM-HT-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Final Issue for Design/ Construction-Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0230 | C-36-KM-HT-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Final Issue for Design/ Construction-Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0290 | C-36-KM-HT-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Final Issue for Design/ Construction-I/O list | Electrical & Earthing Cable Laying | HE-IC-0590 | C-36-KM-HT-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Re-Issue for Approval- I/O list -Update | Electrical & Earthing Cable Laying | HE-IC-0570 | C-36-KM-HT-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Re-Issue for Approval- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0210 | C-36-KM-HT-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Re-Issue for Approval- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0270 | C-36-KM-HT-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Issue ICR- Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0790 | C-36-KM-HT-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Issue ICR- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0250 | C-36-KM-HT-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Issue ICR- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0190 | C-36-KM-HT-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.3.1 Cable Laying & TerminationCCOJ42EL53 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-630 | C-36-KM-HT-EI-2000 | FS | Not Started | Not Started | 48
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | 1st Electrical Bulk material MTO | Instrument Tubing Works | HM-EL-0520 | C-36-KM-HT-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Final Issue for Design/ Construction-Loop Diagrams | Instrument Tubing Works | HE-IC-0770 | C-36-KM-HT-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Instrument Tubing Works | HE-IC-1550 | C-36-KM-HT-EI-2030 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Issue ICR-Instrument index -Update | Instrument Tubing Works | HE-IC-0490 | C-36-KM-HT-EI-2030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Final Issue for Design/ Construction-Earthing Layout | Instrument Tubing Works | HE-EL-1670 | C-36-KM-HT-EI-2030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Instrument Tubing Works | HM-ME-1690 | C-36-KM-HT-EI-2030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Instrument Tubing Works | HM-EL-0080 | C-36-KM-HT-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Instrument Tubing Works | ML1032-B21 | C-36-KM-HT-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Final Issue for Design/ Construction-I/O list | Instrument Tubing Works | HE-IC-0590 | C-36-KM-HT-EI-2030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Final Issue for Design/ Construction-Electrical Equipment Layout | Instrument Tubing Works | HE-EL-0530 | C-36-KM-HT-EI-2030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Instrument Tubing Works | HE-EL-1010 | C-36-KM-HT-EI-2030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Final Issue for Design/ Construction-Electrical Installation Drawings | Instrument Tubing Works | HE-EL-1790 | C-36-KM-HT-EI-2030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Final Issue for Design/ Construction-Instrument Index | Instrument Tubing Works | HE-IC-0530 | C-36-KM-HT-EI-2030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Receipt at site and inspection of Cable Trays (Lot 2) | Instrument Tubing Works | HM-EL-0280 | C-36-KM-HT-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Final Issue for Design/ Construction-Hook-Up Diagram | Instrument Tubing Works | HE-IC-0650 | C-36-KM-HT-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | 1st Instrumentation Bulk material MTO | Instrument Tubing Works | HM-IC-0040 | C-36-KM-HT-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Receipt at site and inspection of Earthing Material (Lot 1) | Instrument Tubing Works | HM-EL-0380 | C-36-KM-HT-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Instrument Tubing Works | HE-IC-1430 | C-36-KM-HT-EI-2030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Final Issue for Design/ Construction-Lighting Layout | Instrument Tubing Works | HE-EL-1730 | C-36-KM-HT-EI-2030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Instrument Tubing Works | HE-IC-2570 | C-36-KM-HT-EI-2030 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Final Issue for Design/ Construction-Typical Installation Drawings | Instrument Tubing Works | HE-IC-0710 | C-36-KM-HT-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Issue ICR- Addendum to DGs | Instrument Tubing Works | HE-IC-0010 | C-36-KM-HT-EI-2030 | SS | Completed | Not Started | 10
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Instrument Tubing Works | HM-ME-1590 | C-36-KM-HT-EI-2030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Issue ICR- P&ID's | Instrument Tubing Works | HE-PR-0110 | C-36-KM-HT-EI-2030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Instrument Tubing Works | HM-ME-2330 | C-36-KM-HT-EI-2030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Instrument Tubing Works | HM-ME-2350 | C-36-KM-HT-EI-2030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Instrument Tubing Works | HM-EL-630 | C-36-KM-HT-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Receipt at site and inspection of Cable Trays (Lot 2) | Instrument Tubing Works | HM-EL-650 | C-36-KM-HT-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Receipt at site and inspection of Earthing Material (Lot 2) | Instrument Tubing Works | HM-EL-690 | C-36-KM-HT-EI-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Instrument Tubing Works | HE-IC-1550 | C-36-KM-HT-EI-2030 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.4.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT30 | Receipt at site and inspection of Pigging & Split Tee (Lot 2) | Preparation, Marking & UT for Existing Line 36" Line | HM-PL-1530 | C-36-KM-HT03-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.3.1.4.12.4.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT30 | Procedure Qualification (PQT/WQT for Hot Tapping - 48", 42",36 & 30") | Preparation, Marking & UT for Existing Line 36" Line | C-COM-1020 | C-36-KM-HT03-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | P2543-R01-Oct24..4.3.1.4.12.4.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT30 | Final Issue for Design/ Construction-Piping Tie In Schedule | Preparation, Marking & UT for Existing Line 36" Line | HE-PI-3520 | C-36-KM-HT03-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | P2543-R01-Oct24..4.3.1.4.12.4.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT30 | Final Issue for Design/ Construction-Data Sheet - Split Tee | Preparation, Marking & UT for Existing Line 36" Line | HE-PL-1370 | C-36-KM-HT03-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.4.12.4.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT30 | 1st Piping Bulk material MTO | Preparation, Marking & UT for Existing Line 36" Line | HM-PI-0040 | C-36-KM-HT03-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.4.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT30 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Preparation, Marking & UT for Existing Line 36" Line | HM-PL-0220 | C-36-KM-HT03-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.24.2 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.4.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT30 | Receipt at site and inspection of Hot Tapping Material | Preparation, Marking & UT for Existing Line 36" Line | HM-PL-0320 | C-36-KM-HT03-ME-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.4.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT30 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Preparation, Marking & UT for Existing Line 36" Line | HM-PL-1570 | C-36-KM-HT03-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.11 Hot Tapping | P2543-R01-Oct24..4.3.1.4.12.4.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT30 | Hot Tapping Subcontract Award | Preparation, Marking & UT for Existing Line 36" Line | HS-CN-0540 | C-36-KM-HT03-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.1.5 Hot Tapping | P2543-R01-Oct24..4.3.1.4.12.4.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT30 | Commercial Clarifications & Placement of PO- Hot Tapping | Preparation, Marking & UT for Existing Line 36" Line | HS-GN-0230 | C-36-KM-HT03-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.24.2 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.4.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT30 | Receipt at site and inspection of Hot Tapping Material | Preparation, Marking & UT for Existing Line 36" Line | HM-PL-0320 | C-36-KM-HT03-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | P2543-R01-Oct24..4.3.1.4.12.5.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT090 | Final Issue for Design/ Construction-Piping Tie In Schedule | Preparation, Marking & UT for Existing Line 36" Line | HE-PI-3520 | C-36-KM-HT04-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.60.16 Data Sheet - Split Tee | P2543-R01-Oct24..4.3.1.4.12.5.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT090 | Final Issue for Design/ Construction-Data Sheet - Split Tee | Preparation, Marking & UT for Existing Line 36" Line | HE-PL-1370 | C-36-KM-HT04-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.4.12.5.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT090 | 1st Piping Bulk material MTO | Preparation, Marking & UT for Existing Line 36" Line | HM-PI-0040 | C-36-KM-HT04-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.5.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT090 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Preparation, Marking & UT for Existing Line 36" Line | HM-PL-0220 | C-36-KM-HT04-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.24.2 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.5.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT090 | Receipt at site and inspection of Hot Tapping Material | Preparation, Marking & UT for Existing Line 36" Line | HM-PL-0320 | C-36-KM-HT04-ME-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.4.12.5.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT090 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Preparation, Marking & UT for Existing Line 36" Line | HM-PL-1570 | C-36-KM-HT04-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.11 Hot Tapping | P2543-R01-Oct24..4.3.1.4.12.5.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT090 | Hot Tapping Subcontract Award | Preparation, Marking & UT for Existing Line 36" Line | HS-CN-0540 | C-36-KM-HT04-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.1.5 Hot Tapping | P2543-R01-Oct24..4.3.1.4.12.5.1 Preparation, Marking & UT for Existing Line 36" LineCCOJ42HT090 | Commercial Clarifications & Placement of PO- Hot Tapping | Preparation, Marking & UT for Existing Line 36" Line | HS-GN-0230 | C-36-KM-HT04-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | P2543-R01-Oct24..4.3.1.5.4.12.1.6 SurveyingCCOPL4"100 | Final Issue for Design/ Construction-Overall Pipeline Route Map - 4" | Survey Marking | HE-PL-0290 | C-4N-H5HG-PIPEL-1000 | FF | Completed | Completed | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.5.4.12.1.6 SurveyingCCOPL4"100 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (4" Nitrogen Pipeline) | Survey Marking | ML1159-A08 | C-4N-H5HG-PIPEL-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | P2543-R01-Oct24..4.3.1.5.4.12.1.6 SurveyingCCOPL4"100 | Final Issue for Design/ Construction-Overall Pipeline Route Map - 4" | Survey Marking | HE-PL-0290 | C-4N-H5HG-PIPEL-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.3.1.5.4.12.1.8 ROW Access RoadCCOPL4"102 | Construction NOC from Musanada | Sabka ROW/Grading | C-GOV-1300 | C-4N-H5HG-PIPEL-1800 | FF | In Progress | In Progress | 14
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.4.12.1.9 Pipe StringingCCOPL4"104 | Receipt at site and inspection of Line Pipes - Lot 7 (Coated) | Stringing (HB-5 to HGCP) | HM-PL-0120 | C-4N-H5HG-PIPEL-2800 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (4" Nitrogen Pipeline) | Lowering | ML1159-A08 | C-4N-H5HG-PIPEL-4800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (4" Nitrogen Pipeline) | Lowering | ML1159-A08 | C-4N-H5HG-PIPEL-5000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.5.4.12.1.27 CP Works(Temporary)CCOP4"EL11.1 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (4" Nitrogen Pipeline) | Installation of CP Test Post | ML1159-A08 | C-4N-H5HG-PIPEL-5200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.5.4.12.1.30 CP Works (Permanent)CCOP4"EL11.2 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (4" Nitrogen Pipeline) | Installation of Test Post for Crossing | ML1159-A08 | C-4N-H5HG-PIPEL-5220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.5.2.3.12.1.1 Demolition Works (Paving)CCOH5CS100 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (4" Nitrogen Pipeline) | Demolition Works (Paving) | ML1159-A08 | C-4N-H5-TPL-CI-0100 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..4.3.1.5.2.3.12.1.1 Demolition Works (Paving)CCOH5CS100 | Issued for Review - Pig launcher and Receiver Foundation Details Drg. at Habshan, HGCP & Sweihan | Demolition Works (Paving) | HE-CS-0610 | C-4N-H5-TPL-CI-0100 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.5.2.3.12.1.1 Demolition Works (Paving)CCOH5CS100 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Demolition Works (Paving) | CTF-1000 | C-4N-H5-TPL-CI-0100 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.5.2.3.12.1.1 Demolition Works (Paving)CCOH5CS100 | NOC's / Approval /Survey | Demolition Works (Paving) | CTF-1010 | C-4N-H5-TPL-CI-0100 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Concrete Works for Equipment Foundations | HE-CS-0650 | C-4N-H5-TPL-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Concrete Works for Equipment Foundations | HE-CS-1310 | C-4N-H5-TPL-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Equipment Foundations | HE-CS-0230 | C-4N-H5-TPL-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Concrete Works for Equipment Foundations | HE-CS-1190 | C-4N-H5-TPL-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.2.3.12.1.5 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH5CS103 | 1st Civil Bulk material MTO | Concrete Works for Equipment Foundations | HM-CS-0040 | C-4N-H5-TPL-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Pipe Supports | HS-CN-0690 | C-4N-H5-TPL-CI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0110 | C-4N-H5-TPL-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | Final Issue for Design/ Construction-Misc. supports | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1490 | C-4N-H5-TPL-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Pre-Fabrication & Installation of Pipe Supports | HE-CS-1430 | C-4N-H5-TPL-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Pipe Supports | HM-CS-0120 | C-4N-H5-TPL-CI-2000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.14 Fence Works | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | Fence Works Subcontract Award | Pre-Fabrication & Installation of Platforms & Crossovers | HS-CN-0690 | C-4N-H5-TPL-CI-3000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | 1st Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0110 | C-4N-H5-TPL-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.41 Misc. supports | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | Final Issue for Design/ Construction-Misc. supports | Pre-Fabrication & Installation of Platforms & Crossovers | HE-CS-1490 | C-4N-H5-TPL-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | Final Issue for Design/ Construction-Pipe Sleeper layout and details | Pre-Fabrication & Installation of Platforms & Crossovers | HE-CS-1430 | C-4N-H5-TPL-CI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.2.3.12.1.7 Pipe Supports/Platforms, Cross over/Guard rails/Bollards/WS/Mis Fabrication & InstallationCCOH5SS500 | Final Structural Bulk material MTO | Pre-Fabrication & Installation of Platforms & Crossovers | HM-CS-0120 | C-4N-H5-TPL-CI-3000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.5.2.3.12.1.8 Trenching for CablesCCOH5CS105 | Final Issue for Design/ Construction-Civil UG layout | Electrical & Earthing Cable Trenching | HE-CS-0530 | C-4N-H5-TPL-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.2.3.12.1.9 Paving WorksCCOH5CS107 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-4N-H5-TPL-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.5.2.3.12.1.9 Paving WorksCCOH5CS107 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-4N-H5-TPL-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH5ME502 | Receipt at site and inspection of Pigging & Split Tee (Lot 1) | Installation of Pig Launcher 4" | HM-PL-0840 | C-4N-H5-TPL-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH5ME502 | Receipt at site and inspection of Pig Signaler (Lot 1) | Installation of Pig Launcher 4" | HM-PL-0530 | C-4N-H5-TPL-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.2.3.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH5ME502 | Issue PFD, P&ID, Plot Plan, Eqpt Layout, DS, Eqpt List, for all facilities after Incorporating HAZOP Comments - IFC | Installation of Pig Launcher 4" | ML1015-B08 | C-4N-H5-TPL-ME-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH5ME502 | Receipt at site and inspection of Pig Signaler (Lot 2) | Installation of Pig Launcher 4" | HM-PL-1490 | C-4N-H5-TPL-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH5ME502 | Receipt at site and inspection of Pigging & Split Tee (Lot 2) | Installation of Pig Launcher 4" | HM-PL-1530 | C-4N-H5-TPL-ME-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.5.2.3.12.4.1 Piping Pre-FabricationCCOH5PI501 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-4N-H5-TPL-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.5.2.3.12.4.1 Piping Pre-FabricationCCOH5PI501 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-4N-H5-TPL-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.2.3.12.4.1 Piping Pre-FabricationCCOH5PI501 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-4N-H5-TPL-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | P2543-R01-Oct24..4.3.1.5.2.3.12.4.1 Piping Pre-FabricationCCOH5PI501 | Final Issue for Design/ Construction-Piping GA for 4" N2 Source Pipeline | Piping Pre-Fabrication | HE-PI-0760 | C-4N-H5-TPL-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.2.3.12.4.1 Piping Pre-FabricationCCOH5PI501 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-4N-H5-TPL-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.5.2.3.12.4.1 Piping Pre-FabricationCCOH5PI501 | NDT / PWHT Subcontract Award | Piping Pre-Fabrication | HS-CN-0190 | C-4N-H5-TPL-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.5.2.3.12.4.1 Piping Pre-FabricationCCOH5PI501 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-4N-H5-TPL-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..4.3.1.5.2.3.12.4.1 Piping Pre-FabricationCCOH5PI501 | Final Issue for Design/ Construction-Overall Plot Plan- 4" N2 Source Pipeline | Piping Pre-Fabrication | HE-PI-0510 | C-4N-H5-TPL-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.4.2 ErectionCCOH5PI515 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Erection | HM-PL-0220 | C-4N-H5-TPL-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.4.2 ErectionCCOH5PI515 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Erection | HM-PL-0630 | C-4N-H5-TPL-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.5.2.3.12.4.2 ErectionCCOH5PI515 | Piping MTO - Final | Piping Erection | HE-PI-1300 | C-4N-H5-TPL-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.2.3.12.4.2 ErectionCCOH5PI515 | 1st Piping Bulk material MTO | Piping Erection | HM-PI-0040 | C-4N-H5-TPL-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.2.3.12.4.2 ErectionCCOH5PI515 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Erection | ML1219-B19 | C-4N-H5-TPL-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.4.2 ErectionCCOH5PI515 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Erection | HM-PL-0740 | C-4N-H5-TPL-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.4.2 ErectionCCOH5PI515 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Erection | HM-PL-0640 | C-4N-H5-TPL-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.5.2.3.12.4.2 ErectionCCOH5PI515 | Final Issue for Design/ Construction-Piping Isometrics | Piping Erection | HE-PI-1240 | C-4N-H5-TPL-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.4.2 ErectionCCOH5PI515 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Erection | HM-PL-1510 | C-4N-H5-TPL-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.4.2 ErectionCCOH5PI515 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Erection | HM-PL-1570 | C-4N-H5-TPL-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.5.2.3.12.4.3 Field Joint Welding, NDT & CoatingCCOH5PI525 | Piping MTO - Final | Field Joint Welding | HE-PI-1300 | C-4N-H5-TPL-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.5.2.3.12.4.3 Field Joint Welding, NDT & CoatingCCOH5PI525 | Project Kick off Meeting | Field Joint Welding | ML1002 | C-4N-H5-TPL-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.2.3.12.4.3 Field Joint Welding, NDT & CoatingCCOH5PI525 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Field Joint Welding | ML1219-B19 | C-4N-H5-TPL-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.5.2.3.12.4.3 Field Joint Welding, NDT & CoatingCCOH5PI525 | NDT / PWHT Subcontract Award | Field Joint Welding | HS-CN-0190 | C-4N-H5-TPL-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.2.3.12.4.4 HydrotestingCCOH5PI535 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Hydrotesting | ML1219-B19 | C-4N-H5-TPL-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.4.5 Installation of ValvesCCOH5PI545 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Installation of Valves/MOV/ROV | HM-PL-0220 | C-4N-H5-TPL-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.2.3.12.4.5 Installation of ValvesCCOH5PI545 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Installation of Valves/MOV/ROV | ML1219-B19 | C-4N-H5-TPL-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.5.2.3.12.4.5 Installation of ValvesCCOH5PI545 | Final Issue for Design/ Construction-Piping Isometrics | Installation of Valves/MOV/ROV | HE-PI-1240 | C-4N-H5-TPL-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.4.5 Installation of ValvesCCOH5PI545 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Installation of Valves/MOV/ROV | HM-PL-1570 | C-4N-H5-TPL-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.5.2.3.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH5PI555 | Piping MTO - Final | Final Bolt Torquing/ Re-Instatement | HE-PI-1300 | C-4N-H5-TPL-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.5.2.3.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH5PI555 | Project Kick off Meeting | Final Bolt Torquing/ Re-Instatement | ML1002 | C-4N-H5-TPL-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH5PI555 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0220 | C-4N-H5-TPL-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.2.3.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH5PI555 | 1st Piping Bulk material MTO | Final Bolt Torquing/ Re-Instatement | HM-PI-0040 | C-4N-H5-TPL-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.2.3.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH5PI555 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Final Bolt Torquing/ Re-Instatement | ML1219-B19 | C-4N-H5-TPL-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.5.2.3.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH5PI555 | NDT / PWHT Subcontract Award | Final Bolt Torquing/ Re-Instatement | HS-CN-0190 | C-4N-H5-TPL-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.5.2.3.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH5PI555 | Final Issue for Design/ Construction-Piping Isometrics | Final Bolt Torquing/ Re-Instatement | HE-PI-1240 | C-4N-H5-TPL-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH5PI555 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1570 | C-4N-H5-TPL-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Issue ICR-Instrument index -Update | Installation of Light Pole, Lighting & Fixtures | HE-IC-0490 | C-4N-H5-TPL-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Installation of Light Pole, Lighting & Fixtures | HE-EL-1010 | C-4N-H5-TPL-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-EL-0280 | C-4N-H5-TPL-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Final Issue for Design/ Construction-I/O list | Installation of Light Pole, Lighting & Fixtures | HE-IC-0590 | C-4N-H5-TPL-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of Light Pole, Lighting & Fixtures | HE-IC-0710 | C-4N-H5-TPL-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of Light Pole, Lighting & Fixtures | HE-EL-1790 | C-4N-H5-TPL-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of Light Pole, Lighting & Fixtures | HE-IC-1550 | C-4N-H5-TPL-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Final Issue for Design/ Construction-Loop Diagrams | Installation of Light Pole, Lighting & Fixtures | HE-IC-0770 | C-4N-H5-TPL-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-EL-0380 | C-4N-H5-TPL-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Final Issue for Design/ Construction-Earthing Layout | Installation of Light Pole, Lighting & Fixtures | HE-EL-1670 | C-4N-H5-TPL-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Issue ICR- Addendum to DGs | Installation of Light Pole, Lighting & Fixtures | HE-IC-0010 | C-4N-H5-TPL-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | 1st Instrumentation Bulk material MTO | Installation of Light Pole, Lighting & Fixtures | HM-IC-0040 | C-4N-H5-TPL-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Installation of Light Pole, Lighting & Fixtures | HE-IC-1430 | C-4N-H5-TPL-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Installation of Light Pole, Lighting & Fixtures | ML1032-B21 | C-4N-H5-TPL-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-ME-1590 | C-4N-H5-TPL-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | 1st Electrical Bulk material MTO | Installation of Light Pole, Lighting & Fixtures | HM-EL-0520 | C-4N-H5-TPL-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Final Issue for Design/ Construction-Instrument Index | Installation of Light Pole, Lighting & Fixtures | HE-IC-0530 | C-4N-H5-TPL-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-EL-0080 | C-4N-H5-TPL-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-ME-1690 | C-4N-H5-TPL-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Installation of Light Pole, Lighting & Fixtures | HE-IC-2570 | C-4N-H5-TPL-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of Light Pole, Lighting & Fixtures | HE-IC-0650 | C-4N-H5-TPL-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Final Issue for Design/ Construction-Lighting Layout | Installation of Light Pole, Lighting & Fixtures | HE-EL-1730 | C-4N-H5-TPL-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of Light Pole, Lighting & Fixtures | HE-EL-0530 | C-4N-H5-TPL-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Issue ICR- P&ID's | Installation of Light Pole, Lighting & Fixtures | HE-PR-0110 | C-4N-H5-TPL-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-ME-2330 | C-4N-H5-TPL-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-ME-2350 | C-4N-H5-TPL-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-EL-630 | C-4N-H5-TPL-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-EL-650 | C-4N-H5-TPL-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-EL-690 | C-4N-H5-TPL-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Final Issue for Design/ Construction-Cable Schedule | Electrical & Earthing Cable Laying | HE-EL-0590 | C-4N-H5-TPL-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Final Issue for Design/ Construction-Cable Routing Layout | Electrical & Earthing Cable Laying | HE-EL-1610 | C-4N-H5-TPL-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Final Issue for Design/ Construction-Data Sheet for LV cables | Electrical & Earthing Cable Laying | HE-EL-0830 | C-4N-H5-TPL-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Final Issue for Design/ Construction-Cable Sizing Calculation | Electrical & Earthing Cable Laying | HE-EL-0470 | C-4N-H5-TPL-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Electrical & Earthing Cable Laying | HM-EL-0080 | C-4N-H5-TPL-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | 1st Electrical Bulk material MTO | Electrical & Earthing Cable Laying | HM-EL-0520 | C-4N-H5-TPL-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Final Issue for Design/ Construction-Instrument Trench Layout | Electrical & Earthing Cable Laying | HE-IC-1010 | C-4N-H5-TPL-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Electrical & Earthing Cable Laying | HE-IC-0950 | C-4N-H5-TPL-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0830 | C-4N-H5-TPL-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Final Issue for Design/ Construction-Data Sheet for HV cables | Electrical & Earthing Cable Laying | HE-EL-1950 | C-4N-H5-TPL-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Final Issue for Design/ Construction-Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0230 | C-4N-H5-TPL-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Final Issue for Design/ Construction-Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0290 | C-4N-H5-TPL-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Final Issue for Design/ Construction-I/O list | Electrical & Earthing Cable Laying | HE-IC-0590 | C-4N-H5-TPL-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Re-Issue for Approval- I/O list -Update | Electrical & Earthing Cable Laying | HE-IC-0570 | C-4N-H5-TPL-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Re-Issue for Approval- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0210 | C-4N-H5-TPL-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Re-Issue for Approval- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0270 | C-4N-H5-TPL-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Issue ICR- Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0790 | C-4N-H5-TPL-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Issue ICR- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0250 | C-4N-H5-TPL-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Issue ICR- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0190 | C-4N-H5-TPL-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-630 | C-4N-H5-TPL-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.2.3.12.8.1 Telecommunication Works CCOH5IC528 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | FOC Laying | ML1033-B22 | C-4N-H5-TPL-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.5.2.3.12.8.1 Telecommunication Works CCOH5IC528 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | FOC Laying | HE-TL-0470 | C-4N-H5-TPL-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.5.2.3.12.8.1 Telecommunication Works CCOH5IC528 | Final Issue for Design/ Construction-Telecom cable schedule | FOC Laying | HE-TL-0830 | C-4N-H5-TPL-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.5.2.3.12.8.1 Telecommunication Works CCOH5IC528 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | FOC Laying | HE-TL-0710 | C-4N-H5-TPL-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.5.2.3.12.8.1 Telecommunication Works CCOH5IC528 | FOC Splicing / Termination Subcontract Award | FOC Laying | HS-CN-0290 | C-4N-H5-TPL-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.5.2.3.12.8.1 Telecommunication Works CCOH5IC528 | Final Issue for Design/ Construction-Telecom Equipment Layout | FOC Laying | HE-TL-0770 | C-4N-H5-TPL-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.2.3.12.8.1 Telecommunication Works CCOH5IC528 | 1st Telecom Bulk material MTO | FOC Laying | HM-TL-0040 | C-4N-H5-TPL-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.9.1 Electrical Shutdown (PDBs)CCOH5ST529 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Electrical Shutdown (PDBs) | HM-ME-1590 | C-4N-H5-TPL-EL-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.2.3.12.9.1 Electrical Shutdown (PDBs)CCOH5ST529 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Electrical Shutdown (PDBs) | HM-ME-2330 | C-4N-H5-TPL-EL-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.15 Tie-In Schedule | P2543-R01-Oct24..4.3.1.5.2.3.12.5.10 Tie In to existing SkidCCOH5PI504 | Final Issue for Design/ Construction-Tie-In Schedule | Installation of Isolation Joint | HE-PR-0290 | C-4N-H5-TPL-PL-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.1.12.1.1 Demolition Works (Paving)CCOH4NCS64 | Issue Civil / Structural Drawings for Launcher/ Receiver facilities | Demolition Works (Paving) | ML1199-B24 | C-4N-HG-TPR-CI-0100 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.5.1.12.1.1 Demolition Works (Paving)CCOH4NCS64 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Demolition Works (Paving) | CTF-1000 | C-4N-HG-TPR-CI-0100 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.5.1.12.1.1 Demolition Works (Paving)CCOH4NCS64 | NOC's / Approval /Survey | Demolition Works (Paving) | CTF-1010 | C-4N-HG-TPR-CI-0100 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Concrete Works for Equipment Foundations | HE-CS-0650 | C-4N-HG-TPR-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Concrete Works for Equipment Foundations | HE-CS-1190 | C-4N-HG-TPR-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Concrete Works for Equipment Foundations | HE-CS-0470 | C-4N-HG-TPR-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | 1st Civil Bulk material MTO | Concrete Works for Equipment Foundations | HM-CS-0040 | C-4N-HG-TPR-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Concrete Works for Equipment Foundations | HE-CS-1310 | C-4N-HG-TPR-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works for Equipment Foundations | HE-CS-0230 | C-4N-HG-TPR-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.5.1.12.1.4 Fences & Gates ConstructionCCOH4NCS67 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Fences & Gates Construction | HE-CS-0470 | C-4N-HG-TPR-CI-2220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.5.1.12.1.4 Fences & Gates ConstructionCCOH4NCS67 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Fences & Gates Construction | HE-CS-0350 | C-4N-HG-TPR-CI-2220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.1.12.1.5 Paving WorksCCOH4NCS69 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving of Interlock tiles & Kerb Stone Embankment | ML1059-B28 | C-4N-HG-TPR-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.5.1.12.1.5 Paving WorksCCOH4NCS69 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving of Interlock tiles & Kerb Stone Embankment | HE-CS-0290 | C-4N-HG-TPR-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.12.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH4NME50 | Transportation/ Custom Clearance/ Delivery at site of Pig Launchers & Receivers (56" Line) | Installation of Pig Receiver 4" | HM-ME-2380 | C-4N-HG-TPR-ME-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH4NME50 | Receipt at site and inspection of Pig Signaler (Lot 1) | Installation of Pig Receiver 4" | HM-PL-0530 | C-4N-HG-TPR-ME-1100 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH4NME50 | Receipt at site and inspection of Pigging & Split Tee (Lot 1) | Installation of Pig Receiver 4" | HM-PL-0840 | C-4N-HG-TPR-ME-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.19.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH4NME50 | Receipt at site and inspection of Pig Signaler (Lot 2) | Installation of Pig Receiver 4" | HM-PL-1490 | C-4N-HG-TPR-ME-1100 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH4NME50 | Receipt at site and inspection of Pigging & Split Tee (Lot 2) | Installation of Pig Receiver 4" | HM-PL-1530 | C-4N-HG-TPR-ME-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.5.1.12.4.1 Piping Pre-FabricationCCOH4NPI050 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-4N-HG-TPR-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.24.14 Overall Plot Plan - 4" N2 Source Pipeline | P2543-R01-Oct24..4.3.1.5.1.12.4.1 Piping Pre-FabricationCCOH4NPI050 | Final Issue for Design/ Construction-Overall Plot Plan- 4" N2 Source Pipeline | Piping Pre-Fabrication | HE-PI-0510 | C-4N-HG-TPR-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.5.1.12.4.1 Piping Pre-FabricationCCOH4NPI050 | NDT / PWHT Subcontract Award | Piping Pre-Fabrication | HS-CN-0190 | C-4N-HG-TPR-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.1.12.4.1 Piping Pre-FabricationCCOH4NPI050 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-4N-HG-TPR-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.1.12.4.1 Piping Pre-FabricationCCOH4NPI050 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-4N-HG-TPR-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.5.1.12.4.1 Piping Pre-FabricationCCOH4NPI050 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-4N-HG-TPR-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.5.1.12.4.1 Piping Pre-FabricationCCOH4NPI050 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-4N-HG-TPR-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.11.27 Piping GA - 4" N2 Source Pipeline | P2543-R01-Oct24..4.3.1.5.1.12.4.1 Piping Pre-FabricationCCOH4NPI050 | Final Issue for Design/ Construction-Piping GA for 4" N2 Source Pipeline | Piping Pre-Fabrication | HE-PI-0760 | C-4N-HG-TPR-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.4.2 ErectionCCOH4NPI060 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Erection | HM-PL-0740 | C-4N-HG-TPR-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.4.2 ErectionCCOH4NPI060 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Erection | HM-PL-0220 | C-4N-HG-TPR-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.1.12.4.2 ErectionCCOH4NPI060 | 1st Piping Bulk material MTO | Piping Erection | HM-PI-0040 | C-4N-HG-TPR-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.1.12.4.2 ErectionCCOH4NPI060 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Erection | ML1219-B19 | C-4N-HG-TPR-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.5.1.12.4.2 ErectionCCOH4NPI060 | Final Issue for Design/ Construction-Piping Isometrics | Piping Erection | HE-PI-1240 | C-4N-HG-TPR-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.5.1.12.4.2 ErectionCCOH4NPI060 | Complete Site Grading & ROW along the Pipeline - 4" Water line | Piping Erection | ML1869-E32 | C-4N-HG-TPR-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.5.1.12.4.2 ErectionCCOH4NPI060 | Piping MTO - Final | Piping Erection | HE-PI-1300 | C-4N-HG-TPR-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.4.2 ErectionCCOH4NPI060 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Erection | HM-PL-0640 | C-4N-HG-TPR-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.4.2 ErectionCCOH4NPI060 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Erection | HM-PL-0630 | C-4N-HG-TPR-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.4.2 ErectionCCOH4NPI060 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Erection | HM-PL-1510 | C-4N-HG-TPR-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.4.2 ErectionCCOH4NPI060 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Erection | HM-PL-1570 | C-4N-HG-TPR-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.5.1.12.4.3 Field Joint Welding, NDT & CoatingCCOH4NPI070 | Piping MTO - Final | Field Joint Welding | HE-PI-1300 | C-4N-HG-TPR-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.5.1.12.4.3 Field Joint Welding, NDT & CoatingCCOH4NPI070 | Project Kick off Meeting | Field Joint Welding | ML1002 | C-4N-HG-TPR-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.5.1.12.4.3 Field Joint Welding, NDT & CoatingCCOH4NPI070 | NDT / PWHT Subcontract Award | Field Joint Welding | HS-CN-0190 | C-4N-HG-TPR-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.1.12.4.3 Field Joint Welding, NDT & CoatingCCOH4NPI070 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Field Joint Welding | ML1219-B19 | C-4N-HG-TPR-PI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.1.12.4.4 HydrotestingCCOH4NPI080 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Hydrotesting | ML1219-B19 | C-4N-HG-TPR-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.5.1.12.4.5 Installation of ValvesCCOH4NPI090 | Piping MTO - Final | Installation of Valves/MOV/ROV | HE-PI-1300 | C-4N-HG-TPR-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.5.1.12.4.5 Installation of ValvesCCOH4NPI090 | Project Kick off Meeting | Installation of Valves/MOV/ROV | ML1002 | C-4N-HG-TPR-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.4.5 Installation of ValvesCCOH4NPI090 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Installation of Valves/MOV/ROV | HM-PL-0220 | C-4N-HG-TPR-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.5.1.12.4.5 Installation of ValvesCCOH4NPI090 | NDT / PWHT Subcontract Award | Installation of Valves/MOV/ROV | HS-CN-0190 | C-4N-HG-TPR-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.1.12.4.5 Installation of ValvesCCOH4NPI090 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Installation of Valves/MOV/ROV | ML1219-B19 | C-4N-HG-TPR-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.5.1.12.4.5 Installation of ValvesCCOH4NPI090 | Final Issue for Design/ Construction-Piping Isometrics | Installation of Valves/MOV/ROV | HE-PI-1240 | C-4N-HG-TPR-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.5.1.12.4.5 Installation of ValvesCCOH4NPI090 | Complete Site Grading & ROW along the Pipeline - 4" Water line | Installation of Valves/MOV/ROV | ML1869-E32 | C-4N-HG-TPR-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.4.5 Installation of ValvesCCOH4NPI090 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Installation of Valves/MOV/ROV | HM-PL-1570 | C-4N-HG-TPR-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | Project Kick off Meeting | Final Bolt Torquing/ Re-Instatement | ML1002 | C-4N-HG-TPR-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | Receipt at site and inspection of Isolating Joints (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0740 | C-4N-HG-TPR-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0220 | C-4N-HG-TPR-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | NDT / PWHT Subcontract Award | Final Bolt Torquing/ Re-Instatement | HS-CN-0190 | C-4N-HG-TPR-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | 1st Piping Bulk material MTO | Final Bolt Torquing/ Re-Instatement | HM-PI-0040 | C-4N-HG-TPR-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Final Bolt Torquing/ Re-Instatement | ML1219-B19 | C-4N-HG-TPR-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | Final Issue for Design/ Construction-Piping Isometrics | Final Bolt Torquing/ Re-Instatement | HE-PI-1240 | C-4N-HG-TPR-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | Complete Site Grading & ROW along the Pipeline - 4" Water line | Final Bolt Torquing/ Re-Instatement | ML1869-E32 | C-4N-HG-TPR-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | Piping MTO - Final | Final Bolt Torquing/ Re-Instatement | HE-PI-1300 | C-4N-HG-TPR-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0640 | C-4N-HG-TPR-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0630 | C-4N-HG-TPR-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | Receipt at site and inspection of Isolating Joints (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1510 | C-4N-HG-TPR-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1570 | C-4N-HG-TPR-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of Light Pole, Lighting & Fixtures | HE-IC-1550 | C-4N-HG-TPR-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of Light Pole, Lighting & Fixtures | HE-IC-0650 | C-4N-HG-TPR-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Installation of Light Pole, Lighting & Fixtures | HE-IC-1430 | C-4N-HG-TPR-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-EL-0280 | C-4N-HG-TPR-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Final Issue for Design/ Construction-I/O list | Installation of Light Pole, Lighting & Fixtures | HE-IC-0590 | C-4N-HG-TPR-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-EL-0380 | C-4N-HG-TPR-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Installation of Light Pole, Lighting & Fixtures | HE-IC-2570 | C-4N-HG-TPR-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Final Issue for Design/ Construction-Earthing Layout | Installation of Light Pole, Lighting & Fixtures | HE-EL-1670 | C-4N-HG-TPR-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of Light Pole, Lighting & Fixtures | HE-IC-0710 | C-4N-HG-TPR-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Final Issue for Design/ Construction-Loop Diagrams | Installation of Light Pole, Lighting & Fixtures | HE-IC-0770 | C-4N-HG-TPR-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | 1st Instrumentation Bulk material MTO | Installation of Light Pole, Lighting & Fixtures | HM-IC-0040 | C-4N-HG-TPR-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Installation of Light Pole, Lighting & Fixtures | HE-EL-1010 | C-4N-HG-TPR-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Final Issue for Design/ Construction-Lighting Layout | Installation of Light Pole, Lighting & Fixtures | HE-EL-1730 | C-4N-HG-TPR-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of Light Pole, Lighting & Fixtures | HE-EL-1790 | C-4N-HG-TPR-EI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of Light Pole, Lighting & Fixtures | HE-EL-0530 | C-4N-HG-TPR-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Installation of Light Pole, Lighting & Fixtures | ML1032-B21 | C-4N-HG-TPR-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Issue ICR- Addendum to DGs | Installation of Light Pole, Lighting & Fixtures | HE-IC-0010 | C-4N-HG-TPR-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-EL-0080 | C-4N-HG-TPR-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | 1st Electrical Bulk material MTO | Installation of Light Pole, Lighting & Fixtures | HM-EL-0520 | C-4N-HG-TPR-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-ME-1590 | C-4N-HG-TPR-EI-1800 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Issue ICR-Instrument index -Update | Installation of Light Pole, Lighting & Fixtures | HE-IC-0490 | C-4N-HG-TPR-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Final Issue for Design/ Construction-Instrument Index | Installation of Light Pole, Lighting & Fixtures | HE-IC-0530 | C-4N-HG-TPR-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Installation of Light Pole, Lighting & Fixtures | HM-ME-1690 | C-4N-HG-TPR-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Issue ICR- P&ID's | Installation of Light Pole, Lighting & Fixtures | HE-PR-0110 | C-4N-HG-TPR-EI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-ME-2330 | C-4N-HG-TPR-EI-1800 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-ME-2350 | C-4N-HG-TPR-EI-1800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-EL-630 | C-4N-HG-TPR-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-EL-650 | C-4N-HG-TPR-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of Light Pole, Lighting & Fixtures | HM-EL-690 | C-4N-HG-TPR-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Data Sheet for LV cables | CP Cable Laying | HE-EL-0830 | C-4N-HG-TPR-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Cable Sizing Calculation | CP Cable Laying | HE-EL-0470 | C-4N-HG-TPR-CA-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Cable Schedule | CP Cable Laying | HE-EL-0590 | C-4N-HG-TPR-CA-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Receipt at site and inspection of Power & Control Cables (Lot 1) | CP Cable Laying | HM-EL-0080 | C-4N-HG-TPR-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Cable Routing Layout | CP Cable Laying | HE-EL-1610 | C-4N-HG-TPR-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | CP Cable Laying | HE-IC-0830 | C-4N-HG-TPR-CA-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | 1st Electrical Bulk material MTO | CP Cable Laying | HM-EL-0520 | C-4N-HG-TPR-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Instrument Trench Layout | CP Cable Laying | HE-IC-1010 | C-4N-HG-TPR-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | CP Cable Laying | HE-IC-0950 | C-4N-HG-TPR-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Data Sheet for HV cables | CP Cable Laying | HE-EL-1950 | C-4N-HG-TPR-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Specification for RTU | CP Cable Laying | HE-IC-0230 | C-4N-HG-TPR-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Specification for Leak Detection System | CP Cable Laying | HE-IC-0290 | C-4N-HG-TPR-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-I/O list | CP Cable Laying | HE-IC-0590 | C-4N-HG-TPR-CA-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Re-Issue for Approval- I/O list -Update | CP Cable Laying | HE-IC-0570 | C-4N-HG-TPR-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Re-Issue for Approval- Specification for RTU | CP Cable Laying | HE-IC-0210 | C-4N-HG-TPR-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Re-Issue for Approval- Specification for Leak Detection System | CP Cable Laying | HE-IC-0270 | C-4N-HG-TPR-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Issue ICR- Instrument Cable Block Diagram | CP Cable Laying | HE-IC-0790 | C-4N-HG-TPR-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Issue ICR- Specification for Leak Detection System | CP Cable Laying | HE-IC-0250 | C-4N-HG-TPR-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Issue ICR- Specification for RTU | CP Cable Laying | HE-IC-0190 | C-4N-HG-TPR-CA-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Receipt at site and inspection of Power & Control Cables (Lot 2) | CP Cable Laying | HM-EL-630 | C-4N-HG-TPR-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Data Sheet for LV cables | Electrical & Earthing Cable Laying | HE-EL-0830 | C-4N-HG-TPR-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Cable Sizing Calculation | Electrical & Earthing Cable Laying | HE-EL-0470 | C-4N-HG-TPR-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Cable Schedule | Electrical & Earthing Cable Laying | HE-EL-0590 | C-4N-HG-TPR-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Electrical & Earthing Cable Laying | HM-EL-0080 | C-4N-HG-TPR-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Cable Routing Layout | Electrical & Earthing Cable Laying | HE-EL-1610 | C-4N-HG-TPR-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0830 | C-4N-HG-TPR-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | 1st Electrical Bulk material MTO | Electrical & Earthing Cable Laying | HM-EL-0520 | C-4N-HG-TPR-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Instrument Trench Layout | Electrical & Earthing Cable Laying | HE-IC-1010 | C-4N-HG-TPR-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | Electrical & Earthing Cable Laying | HE-IC-0950 | C-4N-HG-TPR-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Data Sheet for HV cables | Electrical & Earthing Cable Laying | HE-EL-1950 | C-4N-HG-TPR-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0230 | C-4N-HG-TPR-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0290 | C-4N-HG-TPR-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Final Issue for Design/ Construction-I/O list | Electrical & Earthing Cable Laying | HE-IC-0590 | C-4N-HG-TPR-EI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Re-Issue for Approval- I/O list -Update | Electrical & Earthing Cable Laying | HE-IC-0570 | C-4N-HG-TPR-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Re-Issue for Approval- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0210 | C-4N-HG-TPR-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Re-Issue for Approval- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0270 | C-4N-HG-TPR-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Issue ICR- Instrument Cable Block Diagram | Electrical & Earthing Cable Laying | HE-IC-0790 | C-4N-HG-TPR-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Issue ICR- Specification for Leak Detection System | Electrical & Earthing Cable Laying | HE-IC-0250 | C-4N-HG-TPR-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Issue ICR- Specification for RTU | Electrical & Earthing Cable Laying | HE-IC-0190 | C-4N-HG-TPR-EI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.5.1.12.6.2 Cable Laying & TerminationCCOH4NEL52 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Electrical & Earthing Cable Laying | HM-EL-630 | C-4N-HG-TPR-EI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.5.1.12.8.1 Telecommunication Works CCOH4NIC52 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | FOC Laying | ML1033-B22 | C-4N-HG-TPR-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.1.5.1.12.8.1 Telecommunication Works CCOH4NIC52 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | FOC Laying | HE-TL-0710 | C-4N-HG-TPR-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.1.5.1.12.8.1 Telecommunication Works CCOH4NIC52 | Final Issue for Design/ Construction-Telecom Equipment Layout | FOC Laying | HE-TL-0770 | C-4N-HG-TPR-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.5.1.12.8.1 Telecommunication Works CCOH4NIC52 | 1st Telecom Bulk material MTO | FOC Laying | HM-TL-0040 | C-4N-HG-TPR-TE-1410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.5.1.12.8.1 Telecommunication Works CCOH4NIC52 | FOC Splicing / Termination Subcontract Award | FOC Laying | HS-CN-0290 | C-4N-HG-TPR-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.1.5.1.12.8.1 Telecommunication Works CCOH4NIC52 | Final Issue for Design/ Construction-Telecom cable schedule | FOC Laying | HE-TL-0830 | C-4N-HG-TPR-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..4.3.1.5.1.12.8.1 Telecommunication Works CCOH4NIC52 | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | FOC Laying | HE-IC-0110 | C-4N-HG-TPR-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.1.5.1.12.8.1 Telecommunication Works CCOH4NIC52 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | FOC Laying | HE-TL-0470 | C-4N-HG-TPR-TE-1410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Receipt at site and inspection of Line Pipes - Lot 3 (Coated) | Survey Marking | HM-PL-0100 | C-4W-SVHG-PIPEL-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Receipt at site and inspection of Line Pipes - Lot 6 (Coated) | Survey Marking | HM-PL-0110 | C-4W-SVHG-PIPEL-1000 | SS | Not Started | Not Started | 21
P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Final Issue for Design/ Construction-Overall Pipeline Route Map - 4" | Survey Marking | HE-PL-0290 | C-4W-SVHG-PIPEL-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Obtain NOCs for all facilities from all external agencies / third parties for Construction works (4" Water line) | Survey Marking | ML1169-A09 | C-4W-SVHG-PIPEL-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.6.1.12.1.1 Demolition Works (Paving)CCOSV3CS10 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Demolition Works (Paving) | HE-CS-0470 | C-4W-081-03-CI-0100 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.6.1.12.1.1 Demolition Works (Paving)CCOSV3CS10 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Demolition Works (Paving) | CTF-1000 | C-4W-081-03-CI-0100 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.6.1.12.1.1 Demolition Works (Paving)CCOSV3CS10 | NOC's / Approval /Survey | Demolition Works (Paving) | CTF-1010 | C-4W-081-03-CI-0100 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.6.1.12.1.2 Concrete Works (Foundations for Equipment & Pipe Supports)CCOSV3CS11 | 1st Civil Bulk material MTO | Concrete Works (Foundations for Equipment & Pipe Supports) | HM-CS-0040 | C-4W-081-03-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.3.1.6.1.12.1.2 Concrete Works (Foundations for Equipment & Pipe Supports)CCOSV3CS11 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Concrete Works (Foundations for Equipment & Pipe Supports) | HE-CS-1190 | C-4W-081-03-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.6.1.12.1.2 Concrete Works (Foundations for Equipment & Pipe Supports)CCOSV3CS11 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works (Foundations for Equipment & Pipe Supports) | HE-CS-0230 | C-4W-081-03-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.6.1.12.1.4 Paving WorksCCOSV3CS14 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving Works | HE-CS-0290 | C-4W-081-03-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.6.1.12.1.4 Paving WorksCCOSV3CS14 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving Works | ML1059-B28 | C-4W-081-03-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | Project Kick off Meeting | Piping Works (RTP) | ML1002 | C-4W-081-03-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Works (RTP) | ML1219-B19 | C-4W-081-03-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | Complete Hydrotesting - 4" Water line | Piping Works (RTP) | ML1889-E34 | C-4W-081-03-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | Complete Site Grading & ROW along the Pipeline - 4" Water line | Piping Works (RTP) | ML1869-E32 | C-4W-081-03-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | NDT / PWHT Subcontract Award | Piping Works (RTP) | HS-CN-0190 | C-4W-081-03-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | Final Issue for Design/ Construction-Piping Isometrics | Piping Works (RTP) | HE-PI-1240 | C-4W-081-03-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Works (RTP) | HM-PL-0220 | C-4W-081-03-PI-1000 | FF | Not Started | Not Started | 6
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Works (RTP) | HM-PL-0640 | C-4W-081-03-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Works (RTP) | HM-PL-0630 | C-4W-081-03-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | Piping MTO - Final | Piping Works (RTP) | HE-PI-1300 | C-4W-081-03-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | 1st Piping Bulk material MTO | Piping Works (RTP) | HM-PI-0040 | C-4W-081-03-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | Complete Pipeline Jointing - 4" Waterline | Piping Works (RTP) | ML1879-E33 | C-4W-081-03-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Works (RTP) | HM-PL-0740 | C-4W-081-03-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Works (RTP) | HM-PL-1510 | C-4W-081-03-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Works (RTP) | HM-PL-1570 | C-4W-081-03-PI-1000 | FF | Not Started | Not Started | 6
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.6.1.12.3.1 Tie - in (4'' Tie-in Connection Water Line)CCOSV3PI51 | 1st Structural Bulk material MTO | Tie - in (4'' Tie-in Connection Water Line) | HM-CS-0110 | C-4W-081-03-PI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.6.1.12.3.1 Tie - in (4'' Tie-in Connection Water Line)CCOSV3PI51 | Complete Site Grading & ROW along the Pipeline - 4" Water line | Tie - in (4'' Tie-in Connection Water Line) | ML1869-E32 | C-4W-081-03-PI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.6.2.12.1.1 Demolition Works (Paving & Fence)CCOH4WCS20 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Demolition Works (Paving & Fence) | CTF-1000 | C-4W-TI-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.6.2.12.1.1 Demolition Works (Paving & Fence)CCOH4WCS20 | NOC's / Approval /Survey | Demolition Works (Paving & Fence) | CTF-1010 | C-4W-TI-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.11.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.6.2.12.1.2 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH4WCS21 | 1st Civil Bulk material MTO | Concrete Works (Foundations for Equipment & Pipe Supports) | HM-CS-0040 | C-4W-TI-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.37 Typical Foundation Details for Shelters | P2543-R01-Oct24..4.3.1.6.2.12.1.2 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH4WCS21 | Final Issue for Design/ Construction-TYPICAL FOUNDATION DETAILS FOR SHELTERS | Concrete Works (Foundations for Equipment & Pipe Supports) | HE-CS-1310 | C-4W-TI-CI-1400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.22 Valve pit foundation GA and RC (typ) details | P2543-R01-Oct24..4.3.1.6.2.12.1.2 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH4WCS21 | Final Issue for Design/ Construction-Valve pit foundation GA and RC (type) details | Concrete Works (Foundations for Equipment & Pipe Supports) | HE-CS-1190 | C-4W-TI-CI-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.13 Typical duct bank detail drawing | P2543-R01-Oct24..4.3.1.6.2.12.1.2 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH4WCS21 | Final Issue for Design/ Construction-Typical duct bank detail drawing | Concrete Works (Foundations for Equipment & Pipe Supports) | HE-CS-0230 | C-4W-TI-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.6.2.12.1.2 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH4WCS21 | Issue Civil / Structural Drawings for Launcher/ Receiver facilities | Concrete Works (Foundations for Equipment & Pipe Supports) | ML1199-B24 | C-4W-TI-CI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.16 Typical Fence and gate detail drawing | P2543-R01-Oct24..4.3.1.6.2.12.1.3 Fences & Gates ConstructionCCOH4WCS24 | Final Issue for Design/ Construction-Typical Fence and gate detail drawing | Fences & Gates Construction | HE-CS-0350 | C-4W-TI-CI-2220 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.6.2.12.1.3 Fences & Gates ConstructionCCOH4WCS24 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Fences & Gates Construction | HE-CS-0470 | C-4W-TI-CI-2220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.6.2.12.1.4 Concrete ProtectionCCOH4WCS23 | Issue Civil / Structural Drawings for Launcher/ Receiver facilities | Concrete Protection | ML1199-B24 | C-4W-TI-CI-1700 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.6.2.12.1.5 Paving WorksCCOH4WCS25 | Issue Drawings for All Approach Roads and Other Finishing Works for All Areas - IFC | Paving Works | ML1059-B28 | C-4W-TI-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.15 Typical Road and paving detail drawing | P2543-R01-Oct24..4.3.1.6.2.12.1.5 Paving WorksCCOH4WCS25 | Final Issue for Design/ Construction-Typical Road and paving detail drawing | Paving Works | HE-CS-0290 | C-4W-TI-CI-2600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.6.2.12.2.2 Piping Pre-FabricationCCOH4WPI050 | Project Kick off Meeting | Piping Pre-Fabrication | ML1002 | C-4W-TI-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.6.2.12.2.2 Piping Pre-FabricationCCOH4WPI050 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Pre-Fabrication | ML1219-B19 | C-4W-TI-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.6.2.12.2.2 Piping Pre-FabricationCCOH4WPI050 | Final Issue for Design/ Construction-Piping Isometrics | Piping Pre-Fabrication | HE-PI-1240 | C-4W-TI-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.6.2.12.2.2 Piping Pre-FabricationCCOH4WPI050 | Piping MTO - Final | Piping Pre-Fabrication | HE-PI-1300 | C-4W-TI-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.6.2.12.2.2 Piping Pre-FabricationCCOH4WPI050 | 1st Piping Bulk material MTO | Piping Pre-Fabrication | HM-PI-0040 | C-4W-TI-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.6.2.12.2.2 Piping Pre-FabricationCCOH4WPI050 | NDT / PWHT Subcontract Award | Piping Pre-Fabrication | HS-CN-0190 | C-4W-TI-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.6.2.12.2.3 ErectionCCOH4WPI060 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Installation | ML1219-B19 | C-4W-TI-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.6.2.12.2.3 ErectionCCOH4WPI060 | Final Issue for Design/ Construction-Piping Isometrics | Piping Installation | HE-PI-1240 | C-4W-TI-PI-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.6.2.12.2.3 ErectionCCOH4WPI060 | Piping MTO - Final | Piping Installation | HE-PI-1300 | C-4W-TI-PI-1200 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.2.12.2.3 ErectionCCOH4WPI060 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Installation | HM-PL-0630 | C-4W-TI-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.2.12.2.3 ErectionCCOH4WPI060 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Installation | HM-PL-0640 | C-4W-TI-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.2.12.2.3 ErectionCCOH4WPI060 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Installation | HM-PL-0740 | C-4W-TI-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.2.12.2.3 ErectionCCOH4WPI060 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Installation | HM-PL-0220 | C-4W-TI-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.6.2.12.2.3 ErectionCCOH4WPI060 | 1st Piping Bulk material MTO | Piping Installation | HM-PI-0040 | C-4W-TI-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.2.12.2.3 ErectionCCOH4WPI060 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Installation | HM-PL-1510 | C-4W-TI-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.2.12.2.3 ErectionCCOH4WPI060 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Installation | HM-PL-1570 | C-4W-TI-PI-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.6.2.12.2.4 Field Joint Welding, NDT & CoatingCCOH4WPI070 | Piping MTO - Final | Field Joining | HE-PI-1300 | C-4W-TI-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.6.2.12.2.4 Field Joint Welding, NDT & CoatingCCOH4WPI070 | Project Kick off Meeting | Field Joining | ML1002 | C-4W-TI-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.6.2.12.2.4 Field Joint Welding, NDT & CoatingCCOH4WPI070 | NDT / PWHT Subcontract Award | Field Joining | HS-CN-0190 | C-4W-TI-PI-1400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.6.2.12.2.5 HydrotestingCCOH4WPI080 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Hydrotesting | ML1219-B19 | C-4W-TI-PI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.6.2.12.2.6 Installation of ValvesCCOH4WPI090 | Project Kick off Meeting | Installation of Valves | ML1002 | C-4W-TI-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.6.2.12.2.6 Installation of ValvesCCOH4WPI090 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Installation of Valves | ML1219-B19 | C-4W-TI-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.6.2.12.2.6 Installation of ValvesCCOH4WPI090 | Complete Hydrotesting - 4" Water line | Installation of Valves | ML1889-E34 | C-4W-TI-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.6.2.12.2.6 Installation of ValvesCCOH4WPI090 | Complete Pipeline Jointing - 4" Waterline | Installation of Valves | ML1879-E33 | C-4W-TI-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.6.2.12.2.6 Installation of ValvesCCOH4WPI090 | Final Issue for Design/ Construction-Piping Isometrics | Installation of Valves | HE-PI-1240 | C-4W-TI-PI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.6.2.12.2.6 Installation of ValvesCCOH4WPI090 | Piping MTO - Final | Installation of Valves | HE-PI-1300 | C-4W-TI-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.2.12.2.6 Installation of ValvesCCOH4WPI090 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Installation of Valves | HM-PL-0220 | C-4W-TI-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.6.2.12.2.6 Installation of ValvesCCOH4WPI090 | 1st Piping Bulk material MTO | Installation of Valves | HM-PI-0040 | C-4W-TI-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.6.2.12.2.6 Installation of ValvesCCOH4WPI090 | NDT / PWHT Subcontract Award | Installation of Valves | HS-CN-0190 | C-4W-TI-PI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.2.12.2.6 Installation of ValvesCCOH4WPI090 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Installation of Valves | HM-PL-1570 | C-4W-TI-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.6.2.12.2.1 Final Bolt Torquing/ Re-InstatementCCOH4WPI100 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Final Bolt Torquing/ Re-Instatement | ML1219-B19 | C-4W-TI-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.6.2.12.2.1 Final Bolt Torquing/ Re-InstatementCCOH4WPI100 | Complete Hydrotesting - 4" Water line | Final Bolt Torquing/ Re-Instatement | ML1889-E34 | C-4W-TI-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.6.2.12.2.1 Final Bolt Torquing/ Re-InstatementCCOH4WPI100 | Complete Pipeline Jointing - 4" Waterline | Final Bolt Torquing/ Re-Instatement | ML1879-E33 | C-4W-TI-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.6.2.12.2.1 Final Bolt Torquing/ Re-InstatementCCOH4WPI100 | Final Issue for Design/ Construction-Piping Isometrics | Final Bolt Torquing/ Re-Instatement | HE-PI-1240 | C-4W-TI-PI-2000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.6.2.12.2.1 Final Bolt Torquing/ Re-InstatementCCOH4WPI100 | Piping MTO - Final | Final Bolt Torquing/ Re-Instatement | HE-PI-1300 | C-4W-TI-PI-2000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.2.12.2.1 Final Bolt Torquing/ Re-InstatementCCOH4WPI100 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0630 | C-4W-TI-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.2.12.2.1 Final Bolt Torquing/ Re-InstatementCCOH4WPI100 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Final Bolt Torquing/ Re-Instatement | HM-PL-0640 | C-4W-TI-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.6.2.12.2.1 Final Bolt Torquing/ Re-InstatementCCOH4WPI100 | Achieve Mechanical Completion of PL & facilities- ( 4" Water line) | Final Bolt Torquing/ Re-Instatement | ML1939-E39 | C-4W-TI-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.2.12.2.1 Final Bolt Torquing/ Re-InstatementCCOH4WPI100 | Receipt at site and inspection of Isolating Joints (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0740 | C-4W-TI-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.2.12.2.1 Final Bolt Torquing/ Re-InstatementCCOH4WPI100 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Final Bolt Torquing/ Re-Instatement | HM-PL-0220 | C-4W-TI-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.6.2.12.2.1 Final Bolt Torquing/ Re-InstatementCCOH4WPI100 | 1st Piping Bulk material MTO | Final Bolt Torquing/ Re-Instatement | HM-PI-0040 | C-4W-TI-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.2.12.2.1 Final Bolt Torquing/ Re-InstatementCCOH4WPI100 | Receipt at site and inspection of Isolating Joints (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1510 | C-4W-TI-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.2.12.2.1 Final Bolt Torquing/ Re-InstatementCCOH4WPI100 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Final Bolt Torquing/ Re-Instatement | HM-PL-1570 | C-4W-TI-PI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.6.2.12.3.1 Tie - in (4'' Tie-in Connection Water Line)CCOH4WTI50 | 1st Structural Bulk material MTO | Tie - in (4'' Tie-in Connection Water Line) | HM-CS-0110 | C-4W-TI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.6.2.12.3.1 Tie - in (4'' Tie-in Connection Water Line)CCOH4WTI50 | Complete Site Grading & ROW along the Pipeline - 4" Water line | Tie - in (4'' Tie-in Connection Water Line) | ML1869-E32 | C-4W-TI-3000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | Project Kick off Meeting | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | ML1002 | C-DBV6-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.19 Piping MTO | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | Piping MTO - Final | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | HE-PI-1300 | C-DBV6-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | Issue Piping General Arrangement Drawings, Isometrics and Tie-in details - IFC | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | ML1219-B19 | C-DBV6-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | Final Issue for Design/ Construction-Piping Isometrics | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | HE-PI-1240 | C-DBV6-PI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.4.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | 1st Piping Bulk material MTO | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | HM-PI-0040 | C-DBV6-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | Receipt at site and inspection of Hot Incution Bend (50% Qty) | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | HM-PL-0630 | C-DBV6-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | CTF-1000 | C-DBV6-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | Receipt at site and inspection of Isolating Joints (Lot 1) | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | HM-PL-0740 | C-DBV6-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | NDT / PWHT Subcontract Award | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | HS-CN-0190 | C-DBV6-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.1.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | Receipt at site and inspection of Hot Incution Bend (100% Qty) | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | HM-PL-0640 | C-DBV6-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 1) | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | HM-PL-0220 | C-DBV6-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | HM-ME-1590 | C-DBV6-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.25.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | Receipt at site and inspection of Lifting Equipment | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | HM-ME-2200 | C-DBV6-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | HM-ME-2330 | C-DBV6-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.3.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | Receipt at site and inspection of Isolating Joints (Lot 2) | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | HM-PL-1510 | C-DBV6-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.1.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | Receipt at site and inspection of Ball/ Globe/ Check/ Plug Valves (Lot 2) | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | HM-PL-1570 | C-DBV6-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | NOC's / Approval /Survey | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | CTF-1010 | C-DBV6-PI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.5.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.7.12.4 Shelter InstallationCCOB6S10 | Receipt at site and inspection of Active/ Passive Cooled Shelter | Shelter Installation | HM-ME-1190 | C-DBV6-CI-5000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.7.12.4 Shelter InstallationCCOB6S10 | 1st Structural Bulk material MTO | Shelter Installation | HM-CS-0110 | C-DBV6-CI-5000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.7.12.4 Shelter InstallationCCOB6S10 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Shelter Installation | HM-ME-1590 | C-DBV6-CI-5000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.7.12.4 Shelter InstallationCCOB6S10 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Shelter Installation | HM-ME-2330 | C-DBV6-CI-5000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.8.12.2.1 Electrical & Instrumentation Works (ICSS, Feeder, FO Board...)CCOU800EL1 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Electrical & Instrumentation Works (ICSS, Feeder, FO Board...) | HM-ME-1590 | C-MAQTA-EI-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.8.12.2.1 Electrical & Instrumentation Works (ICSS, Feeder, FO Board...)CCOU800EL1 | 1st Telecom Bulk material MTO | Electrical & Instrumentation Works (ICSS, Feeder, FO Board...) | HM-TL-0040 | C-MAQTA-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | P2543-R01-Oct24..4.3.1.8.12.2.1 Electrical & Instrumentation Works (ICSS, Feeder, FO Board...)CCOU800EL1 | Commercial Clarifications & Placement of PO - Modification of Exiting SMC / SCADA | Electrical & Instrumentation Works (ICSS, Feeder, FO Board...) | HS-GN-0410 | C-MAQTA-EI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.8.12.2.1 Electrical & Instrumentation Works (ICSS, Feeder, FO Board...)CCOU800EL1 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Electrical & Instrumentation Works (ICSS, Feeder, FO Board...) | CTF-1000 | C-MAQTA-EI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.8.12.2.1 Electrical & Instrumentation Works (ICSS, Feeder, FO Board...)CCOU800EL1 | 1st Electrical Bulk material MTO | Electrical & Instrumentation Works (ICSS, Feeder, FO Board...) | HM-EL-0520 | C-MAQTA-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.8.12.2.1 Electrical & Instrumentation Works (ICSS, Feeder, FO Board...)CCOU800EL1 | 1st Instrumentation Bulk material MTO | Electrical & Instrumentation Works (ICSS, Feeder, FO Board...) | HM-IC-0040 | C-MAQTA-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.10 Modification of Existing CTMM | P2543-R01-Oct24..4.3.1.8.12.2.1 Electrical & Instrumentation Works (ICSS, Feeder, FO Board...)CCOU800EL1 | Commercial Clarifications & Placement of PO - Modification of Exiting CTMM | Electrical & Instrumentation Works (ICSS, Feeder, FO Board...) | HS-GN-0290 | C-MAQTA-EI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.12 Modification of Existing Telecom System | P2543-R01-Oct24..4.3.1.8.12.2.1 Electrical & Instrumentation Works (ICSS, Feeder, FO Board...)CCOU800EL1 | Commercial Clarifications & Placement of PO - Modification of Existing Telecom System | Electrical & Instrumentation Works (ICSS, Feeder, FO Board...) | HS-GN-0350 | C-MAQTA-EI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | P2543-R01-Oct24..4.3.1.8.12.2.1 Electrical & Instrumentation Works (ICSS, Feeder, FO Board...)CCOU800EL1 | Commercial Clarifications & Placement of PO - Modification of Existing DCS | Electrical & Instrumentation Works (ICSS, Feeder, FO Board...) | HS-GN-0470 | C-MAQTA-EI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.8.12.2.1 Electrical & Instrumentation Works (ICSS, Feeder, FO Board...)CCOU800EL1 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Electrical & Instrumentation Works (ICSS, Feeder, FO Board...) | HM-ME-2330 | C-MAQTA-EI-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.8.12.2.1 Electrical & Instrumentation Works (ICSS, Feeder, FO Board...)CCOU800EL1 | NOC's / Approval /Survey | Electrical & Instrumentation Works (ICSS, Feeder, FO Board...) | CTF-1010 | C-MAQTA-EI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Final Issue for Design/ Construction-Instrument Cable Block Diagram | LV Cable Trenching | HE-IC-0830 | C-MAQTA-CI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.11 Cable Routing Layout | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Final Issue for Design/ Construction-Cable Routing Layout | LV Cable Trenching | HE-EL-1610 | C-MAQTA-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.10 Cable Schedule | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Final Issue for Design/ Construction-Cable Schedule | LV Cable Trenching | HE-EL-0590 | C-MAQTA-CI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A341 Instrument Trench Layout | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Final Issue for Design/ Construction-Instrument Trench Layout | LV Cable Trenching | HE-IC-1010 | C-MAQTA-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.9 Cable Sizing Calculation | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Final Issue for Design/ Construction-Cable Sizing Calculation | LV Cable Trenching | HE-EL-0470 | C-MAQTA-CI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | LV Cable Trenching | CTF-1000 | C-MAQTA-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Receipt at site and inspection of Power & Control Cables (Lot 1) | LV Cable Trenching | HM-EL-0080 | C-MAQTA-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A34 Instrument and F&G Cable Schedule | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Final Issue for Design/ Construction-Instrument and F&G Cable Schedule | LV Cable Trenching | HE-IC-0950 | C-MAQTA-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | 1st Electrical Bulk material MTO | LV Cable Trenching | HM-EL-0520 | C-MAQTA-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.6 Data Sheet for LV cables | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Final Issue for Design/ Construction-Data Sheet for LV cables | LV Cable Trenching | HE-EL-0830 | C-MAQTA-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.3 Data Sheet for HV cables | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Final Issue for Design/ Construction-Data Sheet for HV cables | LV Cable Trenching | HE-EL-1950 | C-MAQTA-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Final Issue for Design/ Construction-Specification for RTU | LV Cable Trenching | HE-IC-0230 | C-MAQTA-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Final Issue for Design/ Construction-Specification for Leak Detection System | LV Cable Trenching | HE-IC-0290 | C-MAQTA-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Final Issue for Design/ Construction-I/O list | LV Cable Trenching | HE-IC-0590 | C-MAQTA-CI-1800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Re-Issue for Approval- I/O list -Update | LV Cable Trenching | HE-IC-0570 | C-MAQTA-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Re-Issue for Approval- Specification for RTU | LV Cable Trenching | HE-IC-0210 | C-MAQTA-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Re-Issue for Approval- Specification for Leak Detection System | LV Cable Trenching | HE-IC-0270 | C-MAQTA-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A22 Instrument and F&G Cable Block Diagram | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Issue ICR- Instrument Cable Block Diagram | LV Cable Trenching | HE-IC-0790 | C-MAQTA-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A201 Specification for Leak Detection System | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Issue ICR- Specification for Leak Detection System | LV Cable Trenching | HE-IC-0250 | C-MAQTA-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A20 Specification for RTU | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Issue ICR- Specification for RTU | LV Cable Trenching | HE-IC-0190 | C-MAQTA-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | Receipt at site and inspection of Power & Control Cables (Lot 2) | LV Cable Trenching | HM-EL-630 | C-MAQTA-CI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.8.12.2.2 Cable Laying and TerminationCCOU800EL2 | NOC's / Approval /Survey | LV Cable Trenching | CTF-1010 | C-MAQTA-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Commercial Clarifications & Placement of PO - Modification of Existing DCS | SCADA S/m Modification | HS-GN-0470 | C-MAQTA-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.10 Modification of Existing CTMM | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Commercial Clarifications & Placement of PO - Modification of Exiting CTMM | SCADA S/m Modification | HS-GN-0290 | C-MAQTA-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.12 Modification of Existing Telecom System | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Commercial Clarifications & Placement of PO - Modification of Existing Telecom System | SCADA S/m Modification | HS-GN-0350 | C-MAQTA-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | SCADA S/m Modification | ML1033-B22 | C-MAQTA-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | SCADA S/m Modification | CTF-1000 | C-MAQTA-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | SCADA S/m Modification | HE-IC-0110 | C-MAQTA-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Commercial Clarifications & Placement of PO - Modification of Exiting SMC / SCADA | SCADA S/m Modification | HS-GN-0410 | C-MAQTA-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | 1st Telecom Bulk material MTO | SCADA S/m Modification | HM-TL-0040 | C-MAQTA-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | FOC Splicing / Termination Subcontract Award | SCADA S/m Modification | HS-CN-0290 | C-MAQTA-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | NOC's / Approval /Survey | SCADA S/m Modification | CTF-1010 | C-MAQTA-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Commercial Clarifications & Placement of PO - Modification of Existing DCS | Telecom S/m Modification | HS-GN-0470 | C-MAQTA-TE-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.10 Modification of Existing CTMM | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Commercial Clarifications & Placement of PO - Modification of Exiting CTMM | Telecom S/m Modification | HS-GN-0290 | C-MAQTA-TE-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.12 Modification of Existing Telecom System | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Commercial Clarifications & Placement of PO - Modification of Existing Telecom System | Telecom S/m Modification | HS-GN-0350 | C-MAQTA-TE-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Telecom S/m Modification | ML1033-B22 | C-MAQTA-TE-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Telecom S/m Modification | CTF-1000 | C-MAQTA-TE-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A111 Specifications for PRS (Pressure Reduction System) | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Final Issue for Design/ Construction-Specifications for PRS (Pressure Reduction System) | Telecom S/m Modification | HE-IC-0110 | C-MAQTA-TE-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | Commercial Clarifications & Placement of PO - Modification of Exiting SMC / SCADA | Telecom S/m Modification | HS-GN-0410 | C-MAQTA-TE-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | 1st Telecom Bulk material MTO | Telecom S/m Modification | HM-TL-0040 | C-MAQTA-TE-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | FOC Splicing / Termination Subcontract Award | Telecom S/m Modification | HS-CN-0290 | C-MAQTA-TE-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.8.12.3.1 Telecommunication Works (Modification of Existing Telecom Cabinet)CCOU800IC3 | NOC's / Approval /Survey | Telecom S/m Modification | CTF-1010 | C-MAQTA-TE-1010 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.4 Shutdown Requirements & Plan | P2543-R01-Oct24..4.3.1.8.12.4 ShutdownCCOU800ST4 | Final Issue for Design/ Construction-Shutdown Requirements & Plan | Shutdown | C-COM-890 | C-MAQTA-EL-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.8.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | Receipt at site and inspection of AC UPS | Installation of RTU | HM-ME-0790 | C-541CR-EI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.12 Modification of Existing Telecom System | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | Commercial Clarifications & Placement of PO - Modification of Existing Telecom System | Installation of RTU | HS-GN-0350 | C-541CR-EI-1020 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.10 Modification of Existing CTMM | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | Commercial Clarifications & Placement of PO - Modification of Exiting CTMM | Installation of RTU | HS-GN-0290 | C-541CR-EI-1020 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | Receive at Site - UPS System | Installation of RTU | ML1499-D18 | C-541CR-EI-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | Commercial Clarifications & Placement of PO - Modification of Exiting SMC / SCADA | Installation of RTU | HS-GN-0410 | C-541CR-EI-1020 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | Commercial Clarifications & Placement of PO - Modification of Existing DCS | Installation of RTU | HS-GN-0470 | C-541CR-EI-1020 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Installation of RTU | HM-ME-1590 | C-541CR-EI-1020 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Installation of RTU | CTF-1000 | C-541CR-EI-1020 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Installation of RTU | HM-ME-2330 | C-541CR-EI-1020 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | NOC's / Approval /Survey | Installation of RTU | CTF-1010 | C-541CR-EI-1020 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | P2543-R01-Oct24..4.3.1.9.12.3.1 Control System Modifications and Telecommunication WorksCCOC541IC2 | Commercial Clarifications & Placement of PO - Modification of Exiting SMC / SCADA | Telecommunication Works (Modification of Existing Telecom Cabinet) | HS-GN-0410 | C-541CR-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | P2543-R01-Oct24..4.3.1.9.12.3.1 Control System Modifications and Telecommunication WorksCCOC541IC2 | Commercial Clarifications & Placement of PO - Modification of Existing DCS | Telecommunication Works (Modification of Existing Telecom Cabinet) | HS-GN-0470 | C-541CR-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.10 Modification of Existing CTMM | P2543-R01-Oct24..4.3.1.9.12.3.1 Control System Modifications and Telecommunication WorksCCOC541IC2 | Commercial Clarifications & Placement of PO - Modification of Exiting CTMM | Telecommunication Works (Modification of Existing Telecom Cabinet) | HS-GN-0290 | C-541CR-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.9.12.3.1 Control System Modifications and Telecommunication WorksCCOC541IC2 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Telecommunication Works (Modification of Existing Telecom Cabinet) | CTF-1000 | C-541CR-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.12 Modification of Existing Telecom System | P2543-R01-Oct24..4.3.1.9.12.3.1 Control System Modifications and Telecommunication WorksCCOC541IC2 | Commercial Clarifications & Placement of PO - Modification of Existing Telecom System | Telecommunication Works (Modification of Existing Telecom Cabinet) | HS-GN-0350 | C-541CR-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.9.12.3.1 Control System Modifications and Telecommunication WorksCCOC541IC2 | NOC's / Approval /Survey | Telecommunication Works (Modification of Existing Telecom Cabinet) | CTF-1010 | C-541CR-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.10.12.1.1 Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB BuildingCCOU577CS5 | Final Issue for Design/ Construction-Civil UG layout | Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB Building | HE-CS-0530 | C-577-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.10.12.1.1 Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB BuildingCCOU577CS5 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB Building | CTF-1000 | C-577-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.10.12.1.1 Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB BuildingCCOU577CS5 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB Building | HE-CS-0470 | C-577-CI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.10.12.1.1 Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB BuildingCCOU577CS5 | Final Issue for Design/ Construction-Typical trench detail drawing | Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB Building | HE-CS-0170 | C-577-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.10.12.1.1 Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB BuildingCCOU577CS5 | NOC's / Approval /Survey | Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB Building | CTF-1010 | C-577-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | P2543-R01-Oct24..4.3.1.10.12.2.1 Telecommunication Works (new telecom cabinet and cable laying and terminations)CCOU577IC1 | Commercial Clarifications & Placement of PO - Modification of Exiting SMC / SCADA | Telecommunication Works (new telecom cabinet and cable laying and terminations) | HS-GN-0410 | C-577-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.10.12.2.1 Telecommunication Works (new telecom cabinet and cable laying and terminations)CCOU577IC1 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Telecommunication Works (new telecom cabinet and cable laying and terminations) | CTF-1000 | C-577-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.12 Modification of Existing Telecom System | P2543-R01-Oct24..4.3.1.10.12.2.1 Telecommunication Works (new telecom cabinet and cable laying and terminations)CCOU577IC1 | Commercial Clarifications & Placement of PO - Modification of Existing Telecom System | Telecommunication Works (new telecom cabinet and cable laying and terminations) | HS-GN-0350 | C-577-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.10.12.2.1 Telecommunication Works (new telecom cabinet and cable laying and terminations)CCOU577IC1 | 1st Telecom Bulk material MTO | Telecommunication Works (new telecom cabinet and cable laying and terminations) | HM-TL-0040 | C-577-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | P2543-R01-Oct24..4.3.1.10.12.2.1 Telecommunication Works (new telecom cabinet and cable laying and terminations)CCOU577IC1 | Commercial Clarifications & Placement of PO - Modification of Existing DCS | Telecommunication Works (new telecom cabinet and cable laying and terminations) | HS-GN-0470 | C-577-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.10.12.2.1 Telecommunication Works (new telecom cabinet and cable laying and terminations)CCOU577IC1 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Telecommunication Works (new telecom cabinet and cable laying and terminations) | ML1033-B22 | C-577-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.10.12.2.1 Telecommunication Works (new telecom cabinet and cable laying and terminations)CCOU577IC1 | FOC Splicing / Termination Subcontract Award | Telecommunication Works (new telecom cabinet and cable laying and terminations) | HS-CN-0290 | C-577-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.10 Modification of Existing CTMM | P2543-R01-Oct24..4.3.1.10.12.2.1 Telecommunication Works (new telecom cabinet and cable laying and terminations)CCOU577IC1 | Commercial Clarifications & Placement of PO - Modification of Exiting CTMM | Telecommunication Works (new telecom cabinet and cable laying and terminations) | HS-GN-0290 | C-577-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.10.12.2.1 Telecommunication Works (new telecom cabinet and cable laying and terminations)CCOU577IC1 | NOC's / Approval /Survey | Telecommunication Works (new telecom cabinet and cable laying and terminations) | CTF-1010 | C-577-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.11.12.1.1 Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS1 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603) | HE-CS-0470 | C-601-CI-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.14 Typical trench detail drawing | P2543-R01-Oct24..4.3.1.11.12.1.1 Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS1 | Final Issue for Design/ Construction-Typical trench detail drawing | Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603) | HE-CS-0170 | C-601-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.11.12.1.1 Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS1 | Final Issue for Design/ Construction-Civil UG layout | Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603) | HE-CS-0530 | C-601-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.11.12.1.1 Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS1 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603) | CTF-1000 | C-601-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.11.12.1.1 Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS1 | NOC's / Approval /Survey | Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603) | CTF-1010 | C-601-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.11.12.2.1 Telecommunication Works (modifications of existing telecom cabinet)CCOU601IC1 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Telecommunication Works (modifications of existing telecom cabinet) | CTF-1000 | C-601-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.10 Modification of Existing CTMM | P2543-R01-Oct24..4.3.1.11.12.2.1 Telecommunication Works (modifications of existing telecom cabinet)CCOU601IC1 | Commercial Clarifications & Placement of PO - Modification of Exiting CTMM | Telecommunication Works (modifications of existing telecom cabinet) | HS-GN-0290 | C-601-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.12 Modification of Existing Telecom System | P2543-R01-Oct24..4.3.1.11.12.2.1 Telecommunication Works (modifications of existing telecom cabinet)CCOU601IC1 | Commercial Clarifications & Placement of PO - Modification of Existing Telecom System | Telecommunication Works (modifications of existing telecom cabinet) | HS-GN-0350 | C-601-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.1.11.12.2.1 Telecommunication Works (modifications of existing telecom cabinet)CCOU601IC1 | FOC Splicing / Termination Subcontract Award | Telecommunication Works (modifications of existing telecom cabinet) | HS-CN-0290 | C-601-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.1.BK.14 Modification of Existing SMC/RTU | P2543-R01-Oct24..4.3.1.11.12.2.1 Telecommunication Works (modifications of existing telecom cabinet)CCOU601IC1 | Commercial Clarifications & Placement of PO - Modification of Exiting SMC / SCADA | Telecommunication Works (modifications of existing telecom cabinet) | HS-GN-0410 | C-601-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.11.12.2.1 Telecommunication Works (modifications of existing telecom cabinet)CCOU601IC1 | 1st Telecom Bulk material MTO | Telecommunication Works (modifications of existing telecom cabinet) | HM-TL-0040 | C-601-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.BK.18 Modification of Existing DCS | P2543-R01-Oct24..4.3.1.11.12.2.1 Telecommunication Works (modifications of existing telecom cabinet)CCOU601IC1 | Commercial Clarifications & Placement of PO - Modification of Existing DCS | Telecommunication Works (modifications of existing telecom cabinet) | HS-GN-0470 | C-601-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.11.12.2.1 Telecommunication Works (modifications of existing telecom cabinet)CCOU601IC1 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Telecommunication Works (modifications of existing telecom cabinet) | ML1033-B22 | C-601-TE-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.11.12.2.1 Telecommunication Works (modifications of existing telecom cabinet)CCOU601IC1 | NOC's / Approval /Survey | Telecommunication Works (modifications of existing telecom cabinet) | CTF-1010 | C-601-TE-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Testing & Precommissioning Subcontract Award | Precommissioning | HS-CN-0140 | PRECOM-56-PL-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning | HE-PR-0950 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Complete foundations for Launchers and Receiver- 52" Sales Gas Pipeline | Precommissioning | ML1739-E19 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Testing & Precommissioning Subcontract Award | Precommissioning | HS-CN-0140 | PRECOM-56-PL-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning | C-COM-840 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | Testing & Precommissioning Subcontract Award | Precommissioning | HS-CN-0140 | PRECOM-56-EB2-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | Complete foundations for Launchers and Receiver- 56" Sales Gas Pipeline | Precommissioning | ML1619-E07 | PRECOM-56-EB2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | Testing & Precommissioning Subcontract Award | Precommissioning | HS-CN-0140 | PRECOM-56-EB2-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning | C-COM-840 | PRECOM-56-EB2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning | HE-PR-0950 | PRECOM-56-EB2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.1.8.3.1 PrecommissioningCPC-HBS502 | Testing & Precommissioning Subcontract Award | Precommissioning | HS-CN-0140 | PRECOM-56-G-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.1.8.3.1 PrecommissioningCPC-HBS502 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning | HE-PR-0950 | PRECOM-56-G-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.1.8.3.1 PrecommissioningCPC-HBS502 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning | C-COM-840 | PRECOM-56-G-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Testing & Precommissioning Subcontract Award | Precommissioning | HS-CN-0140 | PRECOM-56-59101-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning | HE-PR-0950 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning | C-COM-840 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Testing & Precommissioning Subcontract Award | Precommissioning | HS-CN-0140 | PRECOM-56-59101-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | 1st Structural Bulk material MTO | Precommissioning | HM-CS-0110 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Complete foundations for Launchers and Receiver- 56" Sales Gas Pipeline | Precommissioning | ML1619-E07 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Testing & Precommissioning Subcontract Award | Precommissioning | HS-CN-0140 | PRECOM-56-PR-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning | HE-PR-0950 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning | C-COM-840 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | Complete foundations for Launchers and Receiver- 52" Sales Gas Pipeline | Precommissioning | ML1739-E19 | PRECOM-56-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Complete Hydrotesting - 56" Sales Gas Pipeline | Precommissioning | ML1639-E09 | PRECOM-56-HGHC-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Complete Construction of Anchor Blocks - 56" Sales Gas Pipeline | Precommissioning | ML1609-E06 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Testing & Precommissioning Subcontract Award | Precommissioning | HS-CN-0140 | PRECOM-56-HGHC-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | Precommissioning | ML1579-E03 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning | HE-PR-0950 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning BVS-6 | HE-PR-0950 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning BVS-6 | C-COM-840 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Testing & Precommissioning Subcontract Award | Precommissioning BVS-6 | HS-CN-0140 | PRECOM-52-59806-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Pre-commissioning from BVS-06 to CRS Sweihan | HE-PR-0950 | PRECOM-52-06CR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | Testing & Precommissioning Subcontract Award | Pre-commissioning from BVS-06 to CRS Sweihan | HS-CN-0140 | PRECOM-52-06CR-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Testing & Precommissioning Subcontract Award | Precommissioning Electrical Building Type-I | HS-CN-0140 | PRECOM-52-EB1-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Complete Civil works for CRS Building & equipment's foundations at Sweihan CRS | Precommissioning Electrical Building Type-I | ML1839-E29 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning Electrical Building Type-I | C-COM-840 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning Electrical Building Type-I | HE-PR-0950 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-Electrical Equipment Layout | Precommissioning Pig Receiver 839-V-101 | HE-EL-0530 | PRECOM-52-PR-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-Loop Diagrams | Precommissioning Pig Receiver 839-V-101 | HE-IC-0770 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | 1st Instrumentation Bulk material MTO | Precommissioning Pig Receiver 839-V-101 | HM-IC-0040 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | Precommissioning Pig Receiver 839-V-101 | HE-EL-0710 | PRECOM-52-PR-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-UPS SLD | Precommissioning Pig Receiver 839-V-101 | HE-EL-0290 | PRECOM-52-PR-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Precommissioning Pig Receiver 839-V-101 | HE-IC-1550 | PRECOM-52-PR-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-Data sheet for LV Distribution board | Precommissioning Pig Receiver 839-V-101 | HE-EL-0650 | PRECOM-52-PR-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | 1st Electrical Bulk material MTO | Precommissioning Pig Receiver 839-V-101 | HM-EL-0520 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Precommissioning Pig Receiver 839-V-101 | HM-ME-1590 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Obtain Company Approval-Data sheet for LV Distribution board | Precommissioning Pig Receiver 839-V-101 | HE-EL-0640 | PRECOM-52-PR-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-Instrument Index | Precommissioning Pig Receiver 839-V-101 | HE-IC-0530 | PRECOM-52-PR-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-Earthing Layout | Precommissioning Pig Receiver 839-V-101 | HE-EL-1670 | PRECOM-52-PR-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Receipt at site and inspection of Earthing Material (Lot 1) | Precommissioning Pig Receiver 839-V-101 | HM-EL-0380 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Receipt at site and inspection of Isolator (Lot 1) | Precommissioning Pig Receiver 839-V-101 | HM-ME-0690 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Precommissioning Pig Receiver 839-V-101 | HM-EL-0080 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Precommissioning Pig Receiver 839-V-101 | HE-IC-1430 | PRECOM-52-PR-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 1) | Precommissioning Pig Receiver 839-V-101 | HM-ME-1690 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-I/O list | Precommissioning Pig Receiver 839-V-101 | HE-IC-0590 | PRECOM-52-PR-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Issue ICR- Addendum to DGs | Precommissioning Pig Receiver 839-V-101 | HE-IC-0010 | PRECOM-52-PR-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-Electrical Installation Drawings | Precommissioning Pig Receiver 839-V-101 | HE-EL-1790 | PRECOM-52-PR-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Precommissioning Pig Receiver 839-V-101 | HE-EL-1010 | PRECOM-52-PR-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Precommissioning Pig Receiver 839-V-101 | HE-IC-2570 | PRECOM-52-PR-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Receipt at site and inspection of Cable Trays (Lot 2) | Precommissioning Pig Receiver 839-V-101 | HM-EL-0280 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-Hook-Up Diagram | Precommissioning Pig Receiver 839-V-101 | HE-IC-0650 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-F&G Cause and effect | Precommissioning Pig Receiver 839-V-101 | HE-HS-0350 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-Lighting Layout | Precommissioning Pig Receiver 839-V-101 | HE-EL-1730 | PRECOM-52-PR-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Issue ICR-Instrument index -Update | Precommissioning Pig Receiver 839-V-101 | HE-IC-0490 | PRECOM-52-PR-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Precommissioning Pig Receiver 839-V-101 | ML1032-B21 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-Typical Installation Drawings | Precommissioning Pig Receiver 839-V-101 | HE-IC-0710 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Receipt at site and inspection of Gas Detectors (Lot 1) | Precommissioning Pig Receiver 839-V-101 | HM-ME-1490 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Issue ICR- P&ID's | Precommissioning Pig Receiver 839-V-101 | HE-PR-0110 | PRECOM-52-PR-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Receipt at site and inspection of Isolator (Lot 2) | Precommissioning Pig Receiver 839-V-101 | HM-ME-2250 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Receipt at site and inspection of Gas Detectors (Lot 2) | Precommissioning Pig Receiver 839-V-101 | HM-ME-2310 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Precommissioning Pig Receiver 839-V-101 | HM-ME-2330 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Receipt at site and inspection of Junction Boxes incl H2S Analyzers (Lot 2) | Precommissioning Pig Receiver 839-V-101 | HM-ME-2350 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Precommissioning Pig Receiver 839-V-101 | HM-EL-630 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Receipt at site and inspection of Cable Trays (Lot 2) | Precommissioning Pig Receiver 839-V-101 | HM-EL-650 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Receipt at site and inspection of Earthing Material (Lot 2) | Precommissioning Pig Receiver 839-V-101 | HM-EL-690 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Testing & Precommissioning Subcontract Award | Precommissioning Pig Receiver 839-V-101 | HS-CN-0140 | PRECOM-52-PR-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Complete foundations for Launchers and Receiver- 52" Sales Gas Pipeline | Precommissioning Pig Receiver 839-V-101 | ML1739-E19 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning Pig Receiver 839-V-101 | HE-PR-0950 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Complete Civil works for CRS Building & equipment's foundations at Sweihan CRS | Precommissioning Pig Receiver 839-V-101 | ML1839-E29 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning Pig Receiver 839-V-101 | C-COM-840 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning BVS-5 | C-COM-840 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Testing & Precommissioning Subcontract Award | Precommissioning BVS-5 | HS-CN-0140 | PRECOM-56-59805-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning BVS-5 | HE-PR-0950 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Pre-Commissioning Intrusion Detection KP122 to KP123 | HE-PR-0950 | PRECOM-52-IDS3-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | Testing & Precommissioning Subcontract Award | Pre-Commissioning Intrusion Detection KP122 to KP123 | HS-CN-0140 | PRECOM-52-IDS3-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.3.2.8.4 Precommissioning DEL/TFP PipelineCPCHGCP522 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning DEL/TFP Pipeline | C-COM-840 | PRECOM-52-D-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.3.2.8.4 Precommissioning DEL/TFP PipelineCPCHGCP522 | Testing & Precommissioning Subcontract Award | Precommissioning DEL/TFP Pipeline | HS-CN-0140 | PRECOM-52-D-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.3.2.8.4 Precommissioning DEL/TFP PipelineCPCHGCP522 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning DEL/TFP Pipeline | HE-PR-0950 | PRECOM-52-D-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Testing & Precommissioning Subcontract Award | Precommissioning BVS-4 | HS-CN-0140 | PRECOM-56-59804-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning BVS-4 | HE-PR-0950 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning BVS-4 | C-COM-840 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | HE-PR-0950 | PRECOM-52-IDS2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | Testing & Precommissioning Subcontract Award | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | HS-CN-0140 | PRECOM-52-IDS2-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | HE-PR-0950 | PRECOM-52-IDS1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | Testing & Precommissioning Subcontract Award | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | HS-CN-0140 | PRECOM-52-IDS1-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning BVS-3 | C-COM-840 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Testing & Precommissioning Subcontract Award | Precommissioning BVS-3 | HS-CN-0140 | PRECOM-56-59803-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning BVS-3 | HE-PR-0950 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning BVS-2 | C-COM-840 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Testing & Precommissioning Subcontract Award | Precommissioning BVS-2 | HS-CN-0140 | PRECOM-56-59802-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning BVS-2 | HE-PR-0950 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Testing & Precommissioning Subcontract Award | Precommissioning BVS-1 | HS-CN-0140 | PRECOM-56-59801-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning BVS-1 | HE-PR-0950 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning BVS-1 | C-COM-840 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | 1st Structural Bulk material MTO | Precommissioning Pig Launcher 838-V-602 | HM-CS-0110 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning Pig Launcher 838-V-602 | HE-PR-0950 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | Complete foundations for Launchers and Receiver- 52" Sales Gas Pipeline | Precommissioning Pig Launcher 838-V-602 | ML1739-E19 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | Testing & Precommissioning Subcontract Award | Precommissioning Pig Launcher 838-V-602 | HS-CN-0140 | PRECOM-52-PL-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning Pig Launcher 838-V-602 | C-COM-840 | PRECOM-52-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Pre-commissioning from HGCP to BVS-01 | HE-PR-0950 | PRECOM-52-HG01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | Testing & Precommissioning Subcontract Award | Pre-commissioning from HGCP to BVS-01 | HS-CN-0140 | PRECOM-52-HG01-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Final Issue for Design/ Construction-Telecom cable schedule | Precommissioning | HE-TL-0830 | PRECOM-36-KM-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Complete SMC/ Telecom System Design and Issue Drawings for all facilities - IFC | Precommissioning | ML1033-B22 | PRECOM-36-KM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.6 FOC Splicing / Termination | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | FOC Splicing / Termination Subcontract Award | Precommissioning | HS-CN-0290 | PRECOM-36-KM-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A25 FOC Block diagram (Telecom) | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Final Issue for Design/ Construction-FOC Block diagram (Telecom) | Precommissioning | HE-TL-0470 | PRECOM-36-KM-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A291 Telecom Equipment Layout | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Final Issue for Design/ Construction-Telecom Equipment Layout | Precommissioning | HE-TL-0770 | PRECOM-36-KM-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | 1st Telecom Bulk material MTO | Precommissioning | HM-TL-0040 | PRECOM-36-KM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.10.A29 Telecom Cable Routing Layout | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Final Issue for Design/ Construction-Telecom Location and Cable Routing layout | Precommissioning | HE-TL-0710 | PRECOM-36-KM-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Complete Pipeline Welding - 36"Jump-over line | Precommissioning | ML1899-E35 | PRECOM-36-KM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning | HE-PR-0950 | PRECOM-36-KM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Testing & Precommissioning Subcontract Award | Precommissioning | HS-CN-0140 | PRECOM-36-KM-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning | C-COM-840 | PRECOM-36-KM-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | Testing & Precommissioning Subcontract Award | Precommissioning | HS-CN-0140 | PRECOM-4NH5-TPL-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | 1st Structural Bulk material MTO | Precommissioning | HM-CS-0110 | PRECOM-4NH5-TPL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | Testing & Precommissioning Subcontract Award | Precommissioning | HS-CN-0140 | PRECOM-4NH5-TPL-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning | C-COM-840 | PRECOM-4NH5-TPL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning | HE-PR-0950 | PRECOM-4NH5-TPL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | 1st Structural Bulk material MTO | Precommissioning | HM-CS-0110 | PRECOM-4NHG-TPR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning | C-COM-840 | PRECOM-4NHG-TPR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | Testing & Precommissioning Subcontract Award | Precommissioning | HS-CN-0140 | PRECOM-4NHG-TPR-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning | HE-PR-0950 | PRECOM-4NHG-TPR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Complete Pipeline welding - 4" Nitrogen Pipeline | Precommissioning | ML1909-E36 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning | HE-PR-0950 | PRECOM-4N-H5HG-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | Complete Hydrotesting - 4" Nitrogen Pipeline | Precommissioning | ML1919-E37 | PRECOM-4N-H5HG-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.2.6.1.8.1 PrecommissioningCPC-SV3100 | 1st Structural Bulk material MTO | Precommissioning | HM-CS-0110 | PRECOM-4W-08103-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.6.1.8.1 PrecommissioningCPC-SV3100 | Testing & Precommissioning Subcontract Award | Precommissioning | HS-CN-0140 | PRECOM-4W-08103-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.6.1.8.1 PrecommissioningCPC-SV3100 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning | HE-PR-0950 | PRECOM-4W-08103-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.5.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.2.6.2.8.1 PrecommissioningCPC-SV3101 | 1st Structural Bulk material MTO | Precommissioning | HM-CS-0110 | PRE-COM1310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.6.2.8.1 PrecommissioningCPC-SV3101 | Testing & Precommissioning Subcontract Award | Precommissioning | HS-CN-0140 | PRE-COM1310 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.6.2.8.1 PrecommissioningCPC-SV3101 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning | C-COM-840 | PRE-COM1310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.6.2.8.1 PrecommissioningCPC-SV3101 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning | HE-PR-0950 | PRE-COM1310 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.5 Pre-commissioning and commissioning philosophy | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Final Issue for Design/ Construction-Pre-commissioning and commissioning philosophy | Precommissioning | HE-PR-0950 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.6 Pre-commissioning and Commissioning Plan | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Final Issue for Design/ Construction-Pre-commissioning and Commissioning Plan | Precommissioning | C-COM-840 | PRE-COM1330 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.3 Testing & Precommissioning | P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | Testing & Precommissioning Subcontract Award | Precommissioning | HS-CN-0140 | PRE-COM1330 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.12 Earthing Layout | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-Earthing Layout | Installation of F&G Device | HE-EL-1670 | C-56-PL-607-EI-2410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A35 Typical Installation Drawings | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-Typical Installation Drawings | Installation of F&G Device | HE-IC-0710 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Obtain Company Approval-Data sheet for LV Distribution board | Installation of F&G Device | HE-EL-0640 | C-56-PL-607-EI-2410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of F&G Device | HE-IC-1550 | C-56-PL-607-EI-2410 | FF | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 1) | Installation of F&G Device | HM-ME-1590 | C-56-PL-607-EI-2410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.8.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | 1st Instrumentation Bulk material MTO | Installation of F&G Device | HM-IC-0040 | C-56-PL-607-EI-2410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A36 Loop Diagrams | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-Loop Diagrams | Installation of F&G Device | HE-IC-0770 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.7.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | 1st Electrical Bulk material MTO | Installation of F&G Device | HM-EL-0520 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Issue ICR-Instrument index -Update | Installation of F&G Device | HE-IC-0490 | C-56-PL-607-EI-2410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A27 Instrument location and Cable Routing Drawings | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-Instrument location and Cable Routing Drawings | Installation of F&G Device | HE-IC-2570 | C-56-PL-607-EI-2410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.6.A18 Hook-Up Diagram | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-Hook-Up Diagram | Installation of F&G Device | HE-IC-0650 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of F&G Device | HM-EL-0080 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.EN Detail Engineering | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Issue Electrical & Instrument Cable Schedules, Cable Layouts, Earthing Layouts, Trench Details for All Areas - IFC | Installation of F&G Device | ML1032-B21 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.13 Lighting Layout | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-Lighting Layout | Installation of F&G Device | HE-EL-1730 | C-56-PL-607-EI-2410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.22 UPS SLDs | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-UPS SLD | Installation of F&G Device | HE-EL-0290 | C-56-PL-607-EI-2410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Receipt at site and inspection of Gas Detectors (Lot 1) | Installation of F&G Device | HM-ME-1490 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A41 Datasheets for Pig Signallers | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-Datasheets for Pig Signalers | Installation of F&G Device | HE-IC-1430 | C-56-PL-607-EI-2410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.4.6 F&G Cause and effect | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-F&G Cause and effect | Installation of F&G Device | HE-HS-0350 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of F&G Device | HM-EL-0280 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.31.23 Data sheet for Distibution Transformers | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-Data sheet for Distribution Transformer | Installation of F&G Device | HE-EL-0710 | C-56-PL-607-EI-2410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A2 Instrument Index | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-Instrument Index | Installation of F&G Device | HE-IC-0530 | C-56-PL-607-EI-2410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A91 Addendum to DGS Sales Gas Metering Station | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Issue ICR- Addendum to DGs | Installation of F&G Device | HE-IC-0010 | C-56-PL-607-EI-2410 | SS | Completed | Not Started | 10
P2543-R01-Oct24..1.EN.9.31.5 Data sheet for Distribution board | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-Data sheet for LV Distribution board | Installation of F&G Device | HE-EL-0650 | C-56-PL-607-EI-2410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-Electrical Equipment Layout | Installation of F&G Device | HE-EL-0530 | C-56-PL-607-EI-2410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.6.A3 I/O list | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-I/O list | Installation of F&G Device | HE-IC-0590 | C-56-PL-607-EI-2410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.19 Electrical Installation Drawings | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-Electrical Installation Drawings | Installation of F&G Device | HE-EL-1790 | C-56-PL-607-EI-2410 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.9.1.15 Material Requisition for Distribution Boards | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-Material Requisition for Distribution Boards | Installation of F&G Device | HE-EL-1010 | C-56-PL-607-EI-2410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.26.LL.8.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Receipt at site and inspection of AC UPS | Installation of F&G Device | HM-ME-0790 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Receipt at site and inspection of Earthing Material (Lot 1) | Installation of F&G Device | HM-EL-0380 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Receipt at site and inspection of Isolator (Lot 1) | Installation of F&G Device | HM-ME-0690 | C-56-PL-607-EI-2410 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..1.EN.3.11 P&ID's (New) | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Issue ICR- P&ID's | Installation of F&G Device | HE-PR-0110 | C-56-PL-607-EI-2410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.9.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Telecom Bulk material MTO | Installation of F&G Device | HM-TL-0050 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Receipt at site and inspection of Gas Detectors (Lot 2) | Installation of F&G Device | HM-ME-2310 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Receipt at site and inspection of Field Instruments incl H2S Analyzers (Lot 2) | Installation of F&G Device | HM-ME-2330 | C-56-PL-607-EI-2410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of F&G Device | HM-EL-630 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.13.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Receipt at site and inspection of Cable Trays (Lot 2) | Installation of F&G Device | HM-EL-650 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.15.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Receipt at site and inspection of Earthing Material (Lot 2) | Installation of F&G Device | HM-EL-690 | C-56-PL-607-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.4.A72 Datasheets for Fire and Gas Devices | P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | Final Issue for Design/ Construction-Datasheets for Fire and Gas Devices | Installation of F&G Device | HE-IC-1550 | C-56-PL-607-EI-2410 | FS | Completed | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Receipt at site and inspection of Power & Control Cables (Lot 1) | Installation of Power Distribution System | HM-EL-0080 | C-56-EB2-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.2.12.3.1 Power Distribution SystemCCOHBEL202 | Receipt at site and inspection of Power & Control Cables (Lot 2) | Installation of Power Distribution System | HM-EL-630 | C-56-EB2-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA01-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA02-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA03-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA04-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA05-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA06-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA07-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA08-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA09-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA10-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA11-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA12-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA13-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA14-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA15-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA16-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA17-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA18-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA19-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA20-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA21-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA22-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA23-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CME01-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CME02-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CME03-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CME04-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CME05-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CME06-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CME07-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CME08-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CME09-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CME10-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CME11-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CME12-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CME13-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CME14-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CME15-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CME16-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA24-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA25-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA26-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA27-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA28-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA29-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA30-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-HC01-CMA31-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA01-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA02-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA03-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA04-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA05-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA06-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA07-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA08-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA09-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA10-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA11-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA12-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA13-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA14-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA15-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CME01-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CME02-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CME03-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CME04-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CME05-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CME06-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CME07-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CME08-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CME09-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CME10-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA16-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA17-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA18-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA19-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA20-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA21-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA22-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA23-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA24-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA25-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA26-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Trench Excavation | HE-PL-2910 | C-56-01HG-CMA27-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA02-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA03-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA04-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA05-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA06-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA07-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA08-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA09-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA10-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA11-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA12-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA13-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA14-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA15-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA16-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA17-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA18-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA19-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA20-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA21-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA22-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA23-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CME01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CME02-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CME03-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CME04-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CME05-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CME06-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CME07-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CME08-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CME09-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CME10-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CME11-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CME12-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CME13-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CME14-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CME15-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CME16-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA24-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA25-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA26-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA27-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA28-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA29-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA30-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-HC01-CMA31-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA02-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA03-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA04-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA05-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA06-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA07-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA08-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA09-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA10-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA11-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA12-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA13-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA14-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA15-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CME01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CME02-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CME03-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CME04-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CME05-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CME06-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CME07-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CME08-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CME09-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CME10-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA16-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA17-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA18-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA19-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA20-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA21-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA22-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA23-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA24-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA25-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA26-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | Final Issue for Design/ Construction-Crossing Schedule - 56" | Trench Excavation | HE-PL-2970 | C-56-01HG-CMA27-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2910 | C-56-HC01-CNM03-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2910 | C-56-HC01-CNH05-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2910 | C-56-HC01-CNH02-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2910 | C-56-HC01-CNH01-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2910 | C-56-01HG-CNM12-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2910 | C-56-01HG-CNM11-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2910 | C-56-01HG-CNH10-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | Final Issue for Design/ Construction-Crossing Schedule - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2970 | C-56-HC01-CNM08-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | Final Issue for Design/ Construction-Crossing Schedule - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2970 | C-56-HC01-CNM03-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | Final Issue for Design/ Construction-Crossing Schedule - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2970 | C-56-HC01-CNH05-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | Final Issue for Design/ Construction-Crossing Schedule - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2970 | C-56-HC01-CNH02-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | Final Issue for Design/ Construction-Crossing Schedule - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2970 | C-56-HC01-CNH01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | Final Issue for Design/ Construction-Crossing Schedule - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2970 | C-56-01HG-CNM13-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | Final Issue for Design/ Construction-Crossing Schedule - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2970 | C-56-01HG-CNM12-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | Final Issue for Design/ Construction-Crossing Schedule - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2970 | C-56-01HG-CNM11-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | Final Issue for Design/ Construction-Crossing Schedule - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2970 | C-56-01HG-CNH10-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.2.12.4 NDT / PWHT | P2543-R01-Oct24..4.3.1.3.19.8.1.18 NDT TestCCOPL52491 | NDT / PWHT Subcontract Award | NDT | HS-CN-0190 | C-52-06CR-PL-ME-4000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.3.1.3.19.8.1.17 Automatic WeldingCCOPL52476 | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | Automatic Welding | C-COM-1010 | C-52-06CR-PL-ME-3600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.2.12.15 Automatic Welding | P2543-R01-Oct24..4.3.1.3.19.8.1.17 Automatic WeldingCCOPL52476 | Automatic Welding Subcontract Award | Automatic Welding | HS-CN-690 | C-52-06CR-PL-ME-3600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.9 ROW Access RoadCCOPL56203 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Non-Sabka ROW/Grading | Complete Site Grading & ROW along the Pipeline - 56" Sales Gas Pipeline | C-56-HC01-PL-CI-1800 | ML1569-E02 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.10 ROW Access RoadCCOPL56249 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Non-Sabka ROW/Grading | Complete Site Grading & ROW along the Pipeline - 56" Sales Gas Pipeline | C-56-01HG-PL-CI-1800 | ML1569-E02 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.8 Cut & FillCCOPL56201 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Cut & Fill (@ Non-Sabkha) | Complete Site Grading & ROW along the Pipeline - 56" Sales Gas Pipeline | C-56-HC01-PL-CI-1400 | ML1569-E02 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.12 Cut & Fill from KP 21.3 to HGCPCCOPL56248.2 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Cut & Fill (@ Non-Sabkha) | Complete Site Grading & ROW along the Pipeline - 56" Sales Gas Pipeline | C-56-01HG-PL-CI-1600 | ML1569-E02 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Sabka Gatch Compaction - Layer 4 | Complete Site Grading & ROW along the Pipeline - 56" Sales Gas Pipeline | C-56-01HG-PL-CI-2230 | ML1569-E02 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57592 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CNM08-1800 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.5 Re-Instatement of Entry & Exit PitCCOPL57552 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CNM03-1800 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.3 Re-Instatement of Entry & Exit PitCCOPL58292 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CNH05-1800 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.3 Re-Instatement of Entry & Exit PitCCOPL58232 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CNH02-1800 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.3 Re-Instatement of Entry & Exit PitCCOPL58172 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CNH01-1800 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57992 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CNM13-1800 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57632 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CNM12-1800 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.3.5 Re-Instatement of Entry & Exit PitCCOPL57292 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CNM11-1800 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.6.4.3 Re-Instatement of Entry & Exit PitCCOPL58352 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CNH10-1800 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA02-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA03-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA04-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA05-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA06-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA01-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA07-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA13-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA09-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA11-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA14-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA15-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA22-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA16-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA18-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA20-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA23-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA17-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA19-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA21-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA08-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA10-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA12-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CME01-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CME02-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CME03-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CME04-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CME05-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CME06-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CME07-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CME08-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CME09-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CME10-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CME11-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CME12-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CME13-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CME14-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CME15-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CME16-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA28-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA29-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA27-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA24-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA25-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA26-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA30-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CMA31-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA01-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA02-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA03-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA04-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA05-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.6 Crossing Manual @ KP 20+737 (CX-19) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA06-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.7 Crossing Manual @ KP 20+900 (CX-20) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA07-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.8 Crossing Manual @ KP 24+826 (CX-21) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA08-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.9 Crossing Manual @ KP 26+556 (CX-22) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA09-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.19.10 Crossing Manual @ KP 21+136 (PX-186) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA10-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.11 Crossing Manual @ KP 20+727 (PX-131) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA11-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.12 Crossing Manual @ KP 20+725 (OX-08) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA12-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.13 Crossing Manual @ KP 20+662 (PX-130) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA13-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.14 Crossing Manual @ KP 20+562 (PX-129) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA14-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.22.15 Crossing Manual @ KP 20+488 (PX-128) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA15-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.16 Crossing Manual @ KP 26+558 (FX-03) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA23-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.17 Crossing Manual @ KP 20+229 (PX-162) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA24-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.18 Crossing Manual @ KP 19+811 (PX-159) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA25-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.19 Crossing Manual @ KP 19+202 (PX-157) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA26-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.35.20 Crossing Manual @ KP 18+829 (PX-140) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA27-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.21 Crossing Manual @ KP 18+134 to 25+070 (OX-07,08) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA21-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.37.22 Crossing Manual @ KP 27+219 (OX-09) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA22-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.23 Crossing Manual @ KP 22+058 to 24+892 (PX-211 to PX-218) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA19-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.24 Crossing Manual @ KP 22+019 to 22+036 (PX-195 to PX-202) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA17-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.25 Crossing Manual @ KP 25+335 to 26+403 (PX-219 to PX-222) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA20-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.26 Crossing Manual @ KP 21+440 to 22+016 (PX-188 to PX-194) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA16-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.29.27 Crossing Manual @ KP 22+038 to PX-210 (PX-203 to PX-210) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CMA18-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CME01-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CME02-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CME03-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CME04-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CME05-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CME06-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CME07-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CME08-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CME09-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Padding & Back Filling | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-01HG-CME10-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.16 Automatic WeldingCCOPL56207 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding | Complete Pipeline welding - 56" Sales Gas Pipeline (100% Welding) | C-56-HC01-PL-ME-3600 | ML1599-E05 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Equipment Foundations | Complete foundations for Launchers and Receiver- 56" Sales Gas Pipeline | C-56-PR-838-CI-1400 | ML1619-E07 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Complete foundations for Launchers and Receiver- 56" Sales Gas Pipeline | C-56-PR-838-CI-1410 | ML1619-E07 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.11 Concrete Works (Foundations for Equipment)CCOH56CS32 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Access Platforms & Misc. Structural Foundations | Complete foundations for Launchers and Receiver- 56" Sales Gas Pipeline | C-56-PR-838-CI-1420 | ML1619-E07 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.1.13 Concrete Works (Foundations for Pipe Supports) CCOH56CS34 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Pipe Support Foundations | Complete foundations for Launchers and Receiver- 56" Sales Gas Pipeline | C-56-PR-838-CI-1600 | ML1619-E07 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.5 Concrete Works (Foundations for Pipe Supports) CCOHBCS202.2 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Pipe Support Foundations | Complete foundations for Launchers and Receiver- 56" Sales Gas Pipeline | C-56-PL-607-CI-1600 | ML1619-E07 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Access Platforms & Misc. Structural Foundations | Complete foundations for Launchers and Receiver- 56" Sales Gas Pipeline | C-56-PL-607-CI-1420 | ML1619-E07 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Complete foundations for Launchers and Receiver- 56" Sales Gas Pipeline | C-56-PL-607-CI-1410 | ML1619-E07 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.3 Concrete Works (Foundations for Equipment ) CCOHBCS202.1 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Equipment Foundations | Complete foundations for Launchers and Receiver- 56" Sales Gas Pipeline | C-56-PL-607-CI-1400 | ML1619-E07 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.9 Hybrid Passive Cooling Shelter Installation CCOB156E30 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Passive Cooling Shelter | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-591-01-EI-1000 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Glanding & Termination | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-591-01-EI-2050 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.4 Light Pole, Lighting & Fixtures CCOB156E54 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Light Pole, Lighting & Fixtures | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-591-01-EI-1800 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.4 Light Pole, Lighting & Fixtures CCOB156E54 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Lighting & Instrument JB's | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-591-01-EI-1810 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.6 F&G Devices CCOB156E74 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of F&G Devices | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-591-01-EI-2410 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.6.6 F&G Devices CCOB156E74 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of F&G Panel | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-591-01-EI-2400 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Glanding & Termination | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-PR-838-EI-2050 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Field Instruments (Including Pig Signaller) | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-PR-838-EI-2200 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.2 Deep Earth WellCCOHBEL200 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Deep Earth Well Drilling | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-PL-607-EI-1400 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Glanding & Termination | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-PL-607-EI-2050 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.1 E&I Cable Laying, Glanding & TerminationCCOHBEL201 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Glanding & Termination for CP S/m | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-PL-607-CA-1030 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.5 Light Pole, Lighting & FixturesCCOHBEL213 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Light Pole, Lighting & Fixtures | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-PL-607-EI-1800 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Field Instruments (Including Pig Signaller) | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-PL-607-EI-2200 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.3 Field InstrumentsCCOHBEL223 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-Fabrication & Installation of Field Instrument, JB Supports | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-PL-607-EI-2210 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.6.4 F&G DevicesCCOHBEL233 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of F&G Device | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-PL-607-EI-2410 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.3.8 UPS (6KVA)CCOHBEL293 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | UPS (10KVA) Installation | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-EB2-EI-2400 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOHBPI362 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Bolt Torquing/ Re-Instatement | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-PL-607-PI-2000 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.2.6 Final Bolt Torquing/ Re-InstatementCCOHBPI412 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Bolt Torquing/ Re-Instatement | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | C-56-G-HT-PI-2000 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | PRECOM-56-PL-1000 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | PRECOM-56-EB2-1000 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.1.8.3.1 PrecommissioningCPC-HBS502 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | PRECOM-56-G-1000 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | PRECOM-56-59101-1000 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning | Complete Piping and E&I Installation Works - 56" Sales Gas Pipeline | PRECOM-56-PR-1000 | ML1629-E08 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.7 Dewatering, Swabbing, & DryingCCOPL56227 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Swabing & Drying (Upto Dew Point Temp.) | Complete Hydrotesting - 56" Sales Gas Pipeline | C-56-HC01-PL-ME-7620 | ML1639-E09 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.3 Dewatering, Swabbing, & DryingCCOPL56235 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Swabing & Drying (Upto Dew Point Temp.) | Complete Hydrotesting - 56" Sales Gas Pipeline | C-56-01HG-PL-ME-7620 | ML1639-E09 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning | Complete Drying & Purging of all facilities including Pipeline & Block Valve Stations- 56" Sales Gas Pipeline | PRECOM-56-HGHC-1000 | ML1649-E10 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.7 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 1&2) CCOPL52303.2 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Sabka Gatch Compaction - Layer 2 | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -HGCP to BVS-3 | C-52-HG01-PL-CI-2210 | ML1659-E11 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.12 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 3&4)CCOPL52303.4 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Sabka Gatch Compaction - Layer 4 | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -HGCP to BVS-3 | C-52-HG01-PL-CI-2230 | ML1659-E11 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.6 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 1&2)CCOPL52303.1 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Sabka Gatch Laying - Layer 2 | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -HGCP to BVS-3 | C-52-HG01-PL-CI-2010 | ML1659-E11 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.10 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.4 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Sabka Gatch Compaction - Layer 4 | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -HGCP to BVS-3 | C-52-0102-PL-CI-2230 | ML1659-E11 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Sabka Gatch Compaction - Layer 4 | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -HGCP to BVS-3 | C-52-0203-PL-CI-2230 | ML1659-E11 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Sabka Gatch Compaction - Layer 4 | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -BVS-3 to Sweihan CRS | C-52-06CR-PL-CI-2230 | ML1669-E12 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.6 Cut & Fill in Sandy AreaCCOPL52494 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Cut & Fill (@ Non-Sabkha) | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -BVS-3 to Sweihan CRS | C-52-06CR-PL-CI-1400 | ML1669-E12 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Sabka Gatch Compaction - Layer 4 | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -BVS-3 to Sweihan CRS | C-52-0304-PL-CI-2230 | ML1669-E12 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.7 Cut & Fill in Sandy AreaCCOPL52410 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Cut & Fill (@ Non-Sabkha) | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -BVS-3 to Sweihan CRS | C-52-0304-PL-CI-1400 | ML1669-E12 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Sabka Gatch Compaction - Layer 4 | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -BVS-3 to Sweihan CRS | C-52-0405-PL-CI-2230 | ML1669-E12 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.6 Cut & Fill in Sandy Area from BVS-05 to KP 126.2CCOPL52466.1 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Cut & Fill (@ Non-Sabkha) | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -BVS-3 to Sweihan CRS | C-52-0506-PL-CI-1400 | ML1669-E12 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.8 Cut & Fill in Sandy Area from KP 126.2 to BVS-06CCOPL52466.2 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Cut & Fill (@ Non-Sabkha) | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -BVS-3 to Sweihan CRS | C-52-0506-PL-CI-1600 | ML1669-E12 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.7 Cut & Fill in Sandy AreaCCOPL52438 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Cut & Fill (@ Non-Sabkha) | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -BVS-3 to Sweihan CRS | C-52-0405-PL-CI-1400 | ML1669-E12 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.3.5 Re-Instatement of Entry & Exit PitCCOPL56962 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-06CR-CNM31-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.5.2.3 Re-Instatement of Entry & Exit PitCCOPL58132 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-06CR-CNH30-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.3.1.3 Re-Instatement of Entry & Exit PitCCOPL58192 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-0506-CNH27-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57132 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-0405-CNM17-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.3.5 Re-Instatement of Entry & Exit PitCCOPL57792 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-0405-CNM18-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.6.5 Re-Instatement of Entry & Exit PitCCOPL57752 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-0405-CNM23-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.3 Re-Instatement of Entry & Exit PitCCOPL58152 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-0405-CNH19-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.3 Re-Instatement of Entry & Exit PitCCOPL58312 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-0405-CNH20-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.7.3 Re-Instatement of Entry & Exit PitCCOPL58252 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-0405-CNH24-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.4.5 Re-Instatement of Entry & Exit PitCCOPL57322 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-0102-CNM07-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.6.5 Re-Instatement of Entry & Exit PitCCOPL58032 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-0102-CNM05-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.3 Re-Instatement of Entry & Exit PitCCOPL58212 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-0102-CNH10-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.2.3 Re-Instatement of Entry & Exit PitCCOPL58272 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-0102-CNH09-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.3.3 Re-Instatement of Entry & Exit PitCCOPL58332 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-0102-CNH08-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57362 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-HG01-CNM04-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57712 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-HG01-CNM03-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.3.5 Re-Instatement of Entry & Exit PitCCOPL58072 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-HG01-CNM02-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.4.5 Re-Instatement of Entry & Exit PitCCOPL58112 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-HG01-CNM01-1800 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding-Lot1 | Complete Pipeline welding - 52" Sales Gas Pipeline - 25% Welding | C-52-HG01-PL-ME-3600 | ML1689-E14 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.10 Automatic WeldingCCOPL52364 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding | Complete Pipeline welding - 52" Sales Gas Pipeline - 50% Welding | C-52-0203-PL-ME-3600 | ML1699-E15 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.13 Automatic WeldingCCOPL52336 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding | Complete Pipeline welding - 52" Sales Gas Pipeline - 50% Welding | C-52-0102-PL-ME-3600 | ML1699-E15 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding-Lot1 | Complete Pipeline welding - 52" Sales Gas Pipeline - 50% Welding | C-52-HG01-PL-ME-3600 | ML1699-E15 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding-Lot1 | Complete Pipeline welding - 52" Sales Gas Pipeline - 75% Welding | C-52-HG01-PL-ME-3600 | ML1709-E16 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.10 Automatic WeldingCCOPL52364 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding | Complete Pipeline welding - 52" Sales Gas Pipeline - 75% Welding | C-52-0203-PL-ME-3600 | ML1709-E16 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.13 Automatic WeldingCCOPL52336 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding | Complete Pipeline welding - 52" Sales Gas Pipeline - 75% Welding | C-52-0102-PL-ME-3600 | ML1709-E16 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.12 Automatic WeldingCCOPL52392 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding | Complete Pipeline welding - 52" Sales Gas Pipeline - 75% Welding | C-52-0304-PL-ME-3600 | ML1709-E16 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.12 Automatic WeldingCCOPL52420 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding | Complete Pipeline welding - 52" Sales Gas Pipeline - 75% Welding | C-52-0405-PL-ME-3600 | ML1709-E16 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding-Lot1 | Complete Pipeline welding - 52" Sales Gas Pipeline - 100% Welding | C-52-HG01-PL-ME-3600 | ML1719-E17 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.13 Automatic WeldingCCOPL52336 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding | Complete Pipeline welding - 52" Sales Gas Pipeline - 100% Welding | C-52-0102-PL-ME-3600 | ML1719-E17 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.10 Automatic WeldingCCOPL52364 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding | Complete Pipeline welding - 52" Sales Gas Pipeline - 100% Welding | C-52-0203-PL-ME-3600 | ML1719-E17 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.12 Automatic WeldingCCOPL52392 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding | Complete Pipeline welding - 52" Sales Gas Pipeline - 100% Welding | C-52-0304-PL-ME-3600 | ML1719-E17 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.12 Automatic WeldingCCOPL52420 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding | Complete Pipeline welding - 52" Sales Gas Pipeline - 100% Welding | C-52-0405-PL-ME-3600 | ML1719-E17 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.13 Automatic WeldingCCOPL52448 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding | Complete Pipeline welding - 52" Sales Gas Pipeline - 100% Welding | C-52-0506-PL-ME-3600 | ML1719-E17 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.17 Automatic WeldingCCOPL52476 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding | Complete Pipeline welding - 52" Sales Gas Pipeline - 100% Welding | C-52-06CR-PL-ME-3600 | ML1719-E17 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Lowering-Lot1 | Complete Construction of Anchor Blocks - 52" Sales Gas Pipeline | C-52-HG01-PL-ME-4800 | ML1729-E18 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Lowering | Complete Construction of Anchor Blocks - 52" Sales Gas Pipeline | C-52-0102-PL-ME-4800 | ML1729-E18 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Lowering | Complete Construction of Anchor Blocks - 52" Sales Gas Pipeline | C-52-0203-PL-ME-4800 | ML1729-E18 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Lowering | Complete Construction of Anchor Blocks - 52" Sales Gas Pipeline | C-52-0304-PL-ME-4800 | ML1729-E18 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Lowering | Complete Construction of Anchor Blocks - 52" Sales Gas Pipeline | C-52-0405-PL-ME-4800 | ML1729-E18 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Lowering | Complete Construction of Anchor Blocks - 52" Sales Gas Pipeline | C-52-0506-PL-ME-4800 | ML1729-E18 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Lowering | Complete Construction of Anchor Blocks - 52" Sales Gas Pipeline | C-52-06CR-PL-ME-4800 | ML1729-E18 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Equipment Foundations | Complete foundations for Launchers and Receiver- 52" Sales Gas Pipeline | C-52-PL-838-CI-1400 | ML1739-E19 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Complete foundations for Launchers and Receiver- 52" Sales Gas Pipeline | C-52-PL-838-CI-1410 | ML1739-E19 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Access Platforms & Misc. Structural Foundations | Complete foundations for Launchers and Receiver- 52" Sales Gas Pipeline | C-52-PL-838-CI-1420 | ML1739-E19 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.3 Concrete Works (Foundations for Equipment & Pipe Supports)CCOH52CS33 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Pipe Support Foundations | Complete foundations for Launchers and Receiver- 52" Sales Gas Pipeline | C-52-PL-838-CI-1600 | ML1739-E19 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.5 Concrete Works (Foundations for Pipe Supports)CCOSWCS302.2 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Pipe Support Foundations | Complete foundations for Launchers and Receiver- 52" Sales Gas Pipeline | C-52-PR-839-CI-1600 | ML1739-E19 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Equipment Foundations | Complete foundations for Launchers and Receiver- 52" Sales Gas Pipeline | C-52-PR-839-CI-1400 | ML1739-E19 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Field Instrument, JBs & Light Pole Foundations | Complete foundations for Launchers and Receiver- 52" Sales Gas Pipeline | C-52-PR-839-CI-1410 | ML1739-E19 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.3 Concrete Works (Foundations for Equipment)CCOSWCS302.1 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Access Platforms & Misc. Structural Foundations | Complete foundations for Launchers and Receiver- 52" Sales Gas Pipeline | C-52-PR-839-CI-1420 | ML1739-E19 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.1.4 Concrete ProtectionCCOH52CS34 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Protection | Complete foundations for Launchers and Receiver- 52" Sales Gas Pipeline | C-52-PL-838-CI-1700 | ML1739-E19 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.28 Pipe Lowering & Tie-in / NDT from BVS-01 to KP 21.3CCOPL56237.1 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Lowering | Complete Construction of Anchor Blocks - 56" Sales Gas Pipeline | C-56-01HG-PL-ME-4800 | ML1609-E06 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Lowering | Complete Construction of Anchor Blocks - 56" Sales Gas Pipeline | C-56-01HG-PL-ME-5000 | ML1609-E06 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Lowering | Complete Construction of Anchor Blocks - 56" Sales Gas Pipeline | C-56-HC01-PL-ME-5000 | ML1609-E06 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.3 E&I Cable Laying, Glanding & TerminationCCOH52EL51 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Glanding & Termination | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PL-838-EI-2050 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Piping Erection | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PL-838-PI-1200 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Deep Earth Well Drilling | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PR-839-EI-1400 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Glanding & Termination | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PR-839-EI-2050 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Glanding & Termination | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-EB1-EI-1230 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.1 Sales Gas FilterCCOSWME506 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Sales Gas Filter (839-F-104A) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PR-839-ME-1800 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.1 Sales Gas FilterCCOSWME506 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Sales Gas Filter (839-F-104B) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PR-839-ME-1810 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Pressure Reducing Skid (839-ME-106) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PR-839-ME-2000 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Sales Gas Custody Transfer Metering Skid Including Control Valve (839-ME-105) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PR-839-ME-2010 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.2 Installation of Pig Receiver (839-V-101)CCOSWME508 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Pig Receiver (839-V-101) 52" | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PR-839-ME-1100 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.3 Installation of Pig Signaler (839-V-101)CCOSWME509 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Pig Signaler (839-V-101) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PR-839-ME-1200 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.4 Installation of Fire Fighting & Safety EquipmentCCOSWME510 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Fire Fighting & Safety Equipment | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PR-839-ME-1600 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | NDT & Coating for Field Joint Weld | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PR-839-PI-1410 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | NDT & Coating for Field Joint Weld | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PR-839-PI-1410 | ML1749-E20 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.2.6 Final Bolt Torquing/ Re-InstatementCCOSWPI564 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Bolt Torquing/ Re-Instatement | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-D-HT-PI-2000 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.7 Pipe Supports Fabrication & InstallationCCOSWSS500 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-Fabrication & Installation of Pipe Supports | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PR-839-CI-2000 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS505 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-Fabrication & Installation of Platforms & Crossovers | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PR-839-CI-3000 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS505 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PR-839-CI-3010 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.6.4 RTUCCOH52EL82 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of RTU (Deleted) | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-PL-838-EI-1600 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.8 UPS (10KVA)CCOSW52E72 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | UPS (10KVA) Installation | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | C-52-EB1-EI-2400 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning BVS-6 | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | PRECOM-52-59806-1000 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning BVS-5 | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | PRECOM-56-59805-1000 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning BVS-4 | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | PRECOM-56-59804-1000 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning BVS-3 | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | PRECOM-56-59803-1000 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning Pig Launcher 838-V-602 | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | PRECOM-52-PL-1000 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.4 Precommissioning DEL/TFP PipelineCPCHGCP522 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning DEL/TFP Pipeline | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | PRECOM-52-D-1000 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | PRECOM-52-IDS2-1000 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-Commissioning Intrusion Detection KP122 to KP123 | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | PRECOM-52-IDS3-1000 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | PRECOM-52-IDS1-1000 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning Electrical Building Type-I | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | PRECOM-52-EB1-1000 | ML1749-E20 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning Pig Receiver 839-V-101 | Complete Piping and E&I Installation Works - 52" Sales Gas Pipeline | PRECOM-52-PR-1000 | ML1749-E20 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Holding of Test Pressure | Complete Hydrotesting - 52" Sales Gas Pipeline -Launcher to BVS-01 | C-52-HG01-PL-ME-7430 | ML1759-E21 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2.3 Dewatering, Swabbing, & DryingCCOPL52326 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Swabing & Drying (Upto Dew Point Temp.) | Complete Hydrotesting - 52" Sales Gas Pipeline -Launcher to BVS-01 | C-52-HG01-PL-ME-7620 | ML1759-E21 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Holding of Test Pressure | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 01 to BVS-02 | C-52-0102-PL-ME-7430 | ML1769-E22 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.1.3 Dewatering, Swabbing, & DryingCCOPL52342 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Swabing & Drying (Upto Dew Point Temp.) | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 01 to BVS-02 | C-52-0102-PL-ME-7620 | ML1769-E22 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Holding of Test Pressure | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 02 to BVS-03 | C-52-0203-PL-ME-7430 | ML1779-E23 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2.3 Dewatering, Swabbing, & DryingCCOPL52370 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Swabing & Drying (Upto Dew Point Temp.) | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 02 to BVS-03 | C-52-0203-PL-ME-7620 | ML1779-E23 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Holding of Test Pressure | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 03 to BVS-04 | C-52-0304-PL-ME-7430 | ML1789-E24 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.3.3 Dewatering, Swabbing, & DryingCCOPL52398 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Swabing & Drying (Upto Dew Point Temp.) | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 03 to BVS-04 | C-52-0304-PL-ME-7620 | ML1789-E24 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Holding of Test Pressure | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 04 to BVS-05 | C-52-0405-PL-ME-7430 | ML1799-E25 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.3.3 Dewatering, Swabbing, & DryingCCOPL52426 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Swabing & Drying (Upto Dew Point Temp.) | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 04 to BVS-05 | C-52-0405-PL-ME-7620 | ML1799-E25 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Holding of Test Pressure | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 05 to BVS-06 | C-52-0506-PL-ME-7430 | ML1809-E26 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.3.3 Dewatering, Swabbing, & DryingCCOPL52454 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Swabing & Drying (Upto Dew Point Temp.) | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 05 to BVS-06 | C-52-0506-PL-ME-7620 | ML1809-E26 | FS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Holding of Test Pressure | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 06 to Sweihan Receiver | C-52-06CR-PL-ME-7430 | ML1819-E27 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.2.3 Dewatering & DryingCCOPL52482 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Swabing & Drying (Upto Dew Point Temp.) | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 06 to Sweihan Receiver | C-52-06CR-PL-ME-7620 | ML1819-E27 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-commissioning from HGCP to BVS-01 | Complete Drying & Purging of all facilities including Pipeline & Block Valve Stations - 52" Sales Gas Pipeline | PRECOM-52-HG01-1000 | ML1829-E28 | FS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.4.1.22.1.5 Concrete Works (Foundations for Pipe Supports)CCOSWCS302.2 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Works for Pipe Support Foundations | Complete Civil works for CRS Building & equipment's foundations at Sweihan CRS | C-52-PR-839-CI-1600 | ML1839-E29 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 Excavation (incl Bedding)CCOSWCS303 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Compaction & Testing for Ground Level | Complete Civil works for CRS Building & equipment's foundations at Sweihan CRS | C-52-EB1-CI-1020 | ML1839-E29 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.2 Foundation Works (for Substructure)CCOSWCS304 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Building Foundation Works (for Substructure) | Complete Civil works for CRS Building & equipment's foundations at Sweihan CRS | C-52-EB1-CI-1200 | ML1839-E29 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.1.3 Concrete Superstructure WorksCCOSWCS305 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Concrete Superstructure Works | Complete Civil works for CRS Building & equipment's foundations at Sweihan CRS | C-52-EB1-CI-1400 | ML1839-E29 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | NDT & Coating for Field Joint Weld | Complete Piping works at Sweihan CRS | C-52-PR-839-PI-1410 | ML1849-E30 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.2.6 Final Bolt Torquing/ Re-InstatementCCOSWPI564 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Bolt Torquing/ Re-Instatement | Complete Piping works at Sweihan CRS | C-52-D-HT-PI-2000 | ML1849-E30 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.1 Deep Earth WellCCOSW52E10.12 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Deep Earth Well Drilling | Complete E&I Installation Works - Sweihan CRS | C-52-PR-839-EI-1400 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.6.2 E&I Cable Laying, Glanding & TerminationCCOSW52E12 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Glanding & Termination | Complete E&I Installation Works - Sweihan CRS | C-52-PR-839-EI-2050 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.6 E&I Cable Laying, Glanding & TerminationCCOSW52E18 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Glanding & Termination | Complete E&I Installation Works - Sweihan CRS | C-52-EB1-EI-1230 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.1 Sales Gas FilterCCOSWME506 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Sales Gas Filter (839-F-104B) | Complete E&I Installation Works - Sweihan CRS | C-52-PR-839-ME-1810 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Pressure Reducing Skid (839-ME-106) | Complete E&I Installation Works - Sweihan CRS | C-52-PR-839-ME-2000 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.5 Skids (Pressure Metering skid, Pressure Reducing Skid)CCOSWME507 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Sales Gas Custody Transfer Metering Skid Including Control Valve (839-ME-105) | Complete E&I Installation Works - Sweihan CRS | C-52-PR-839-ME-2010 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.2 Installation of Pig Receiver (839-V-101)CCOSWME508 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Pig Receiver (839-V-101) 52" | Complete E&I Installation Works - Sweihan CRS | C-52-PR-839-ME-1100 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.3 Installation of Pig Signaler (839-V-101)CCOSWME509 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Pig Signaler (839-V-101) | Complete E&I Installation Works - Sweihan CRS | C-52-PR-839-ME-1200 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.4 Installation of Fire Fighting & Safety EquipmentCCOSWME510 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Fire Fighting & Safety Equipment | Complete E&I Installation Works - Sweihan CRS | C-52-PR-839-ME-1600 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | NDT & Coating for Field Joint Weld | Complete E&I Installation Works - Sweihan CRS | C-52-PR-839-PI-1410 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.7 Pipe Supports Fabrication & InstallationCCOSWSS500 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-Fabrication & Installation of Pipe Supports | Complete E&I Installation Works - Sweihan CRS | C-52-PR-839-CI-2000 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.4.3 Piping Works -NDT & PaintingCCOSWPI503.3 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | NDT & Coating for Field Joint Weld | Complete E&I Installation Works - Sweihan CRS | C-52-PR-839-PI-1410 | ML1859-E31 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.7 Pipe Supports Fabrication & InstallationCCOSWSS500 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-Fabrication & Installation of Pipe Supports | Complete E&I Installation Works - Sweihan CRS | C-52-PR-839-CI-2000 | ML1859-E31 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS505 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-Fabrication & Installation of Platforms & Crossovers | Complete E&I Installation Works - Sweihan CRS | C-52-PR-839-CI-3000 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS505 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | Complete E&I Installation Works - Sweihan CRS | C-52-PR-839-CI-3010 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.3.8 UPS (10KVA)CCOSW52E72 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | UPS (10KVA) Installation | Complete E&I Installation Works - Sweihan CRS | C-52-EB1-EI-2400 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning Electrical Building Type-I | Complete E&I Installation Works - Sweihan CRS | PRECOM-52-EB1-1000 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning Electrical Building Type-I | Complete E&I Installation Works - Sweihan CRS | PRECOM-52-EB1-1000 | ML1859-E31 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning Pig Receiver 839-V-101 | Complete E&I Installation Works - Sweihan CRS | PRECOM-52-PR-1000 | ML1859-E31 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Sabka Gatch Compaction - Layer 4 | Complete Site Grading & ROW along the Pipeline - 4" Water line | C-4W-SVHG-PIPEL-2230 | ML1869-E32 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Joint | Complete Pipeline Jointing - 4" Waterline | C-4W-SVHG-PIPEL-4810 | ML1879-E33 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | De-watering | Complete Hydrotesting - 4" Water line | C-4W-SVHG-PIPEL-7610 | ML1889-E34 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.5.5 Hot Tapping of Existing 36" LineCCOJ42HT130 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Hot Tapping of Existing 36" Line | Complete Pipeline Welding - 36"Jump-over line | C-36-KM-HT04-ME-1040 | ML1899-E35 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.4.5 Hot Tapping of Existing 36" LineCCOJ42HT70 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Hot Tapping of Existing 36" Line | Complete Pipeline Welding - 36"Jump-over line | C-36-KM-HT03-ME-1040 | ML1899-E35 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.2.6 Final Bolt Torquing/ Re-InstatementCCOJ42PI122 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Bolt Torquing/ Re-Instatement | Complete Pipeline Welding - 36"Jump-over line | C-36-KM-HT-PI-2000 | ML1899-E35 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.20 Manual Welding from KP-12 to HGCP Compressor StationCCOPL4"105.2 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-PIPEL-3800 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Holding of Test Pressure | Complete Hydrotesting - 4" Nitrogen Pipeline | C-4N-H5HG-PIPEL-7430 | ML1919-E37 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.32 Dewatering, Swabbing, & DryingCCOPL4"124 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Swabing & Drying (Upto Dew Point Temp.) | Complete Hydrotesting - 4" Nitrogen Pipeline | C-4N-H5HG-PIPEL-7620 | ML1919-E37 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.5.9 Temporary Pig Receiver (4'' Nitrogen Pipeline) Piping Hook-upCCOH4NPI51 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Ext. Coating for Weld Joint | Complete Drying & Purging of all facilities including Pipeline - 4" Nitrogen Pipeline | C-4N-HG-TPR-PL-1030 | ML1929-E38 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.5.11 Temporary Pig Launcher (4'' Nitrogen Pipeline) Piping Hook-upCCOH5PI505 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Ext. Coating for Weld Joint | Complete Drying & Purging of all facilities including Pipeline - 4" Nitrogen Pipeline | C-4N-H5-TPL-PL-1030 | ML1929-E38 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning | Complete Drying & Purging of all facilities including Pipeline - 4" Nitrogen Pipeline | PRECOM-4N-H5HG-1000 | ML1929-E38 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.4 Berm Construction | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Gatch Compaction | Achieve Mechanical Completion of PL & facilities- ( 4" Water line) | C-4W-SVHG-PIPEL-6810 | ML1939-E39 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.1 Crossing Manual @ KP 0+151 (FX-02) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Joint | Complete Pipeline Jointing - 4" Waterline | CPL-4-CRMN-3350 | ML1879-E33 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.2 Crossing Manual @ KP 0+561 to 0+585 (FX-04,05) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Joint | Complete Pipeline Jointing - 4" Waterline | CPL-4-CRMN-3430 | ML1879-E33 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.3 Crossing Manual @ KP 1+268 (CX-05) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Joint | Complete Pipeline Jointing - 4" Waterline | CPL-4-CRMN-3490 | ML1879-E33 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.4 Crossing Manual @ KP 1+780 to 1+799 (FX-06,07 & RX-03) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Joint | Complete Pipeline Jointing - 4" Waterline | CPL-4-CRMN-3550 | ML1879-E33 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.1.5 Crossing Mechanical @ KP 1+772 (RX-02) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Joint | Complete Pipeline Jointing - 4" Waterline | CPL-4-CRMN-3610 | ML1879-E33 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-PIPEL-4810 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-PIPEL-5010 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.2 Crossing Manual @ KP 0+753 to 0+755 (PX-02,03) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA01-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.3 Crossing Manual @ KP 1+390 (PX-04) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA02-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.4 Crossing Manual @ KP 1+936 to 1+953 (PX-05,06) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA03-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.5 Crossing Manual @ KP 2+519 (PX-07) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA04-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.6 Crossing Manual @ KP 3+526 (PX-19) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA05-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.7 Crossing Manual @ KP 5+768 (PX-30) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA06-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.8 Crossing Manual @ KP 7+135 to 7+153 (PX-31,32) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA07-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.9 Crossing Manual @ KP 7+704 (PX-33) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA08-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.10 Crossing Manual @ KP 9+013 to 9+058 (PX-34,35) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA09-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.11 Crossing Manual @ KP 9+389 (PX-47) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA10-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.12 Crossing Manual @ KP 9+447 (PX-48) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA11-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.15.13 Crossing Manual @ KP 10+022 (PX-49) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA12-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA13-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.16.29 Crossing Manual @ KP 20+610 to 20+649(RX-03,CX-06,07,08,09) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA29-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.14 Crossing Manual @ KP 10+458 to 10+460 (PX-50,51,52) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA14-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.15 Crossing Manual @ KP 10+523 (PX-53) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA15-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.16 Crossing Manual @ KP 10+703 (PX-67) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA16-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.17 Crossing Manual @ KP 10+788 (PX-68) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA17-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.18 Crossing Manual @ KP 10+882 (PX-69) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA18-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.20 Crossing Manual @ KP 11+343 to 11+349 (PX-71,PX-72) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA19-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.21 Crossing Manual @ KP 11+646 to 11+668 (PX-73,PX-74) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA20-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.22 Crossing Manual @ KP 12+129 to 12+135 (PX-75,PX-76) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA21-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.25.23 Crossing Manual @ KP 13+692 to 13+785 (PX-102,103,104) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA22-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.24 Crossing Manual @ KP 15+082 (PX-105) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA23-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.26 Crossing Manual @ KP 15+542 (PX-106) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA24-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.27 Crossing Manual @ KP 16+486 (PX-107) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA25-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.28.28 Crossing Manual @ KP 16+594 to 16+609(PX-108,109) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA26-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.19 Crossing Manual @ KP 10+945 to 10+954 (OX-02,PX-70) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA27-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.29.25 Crossing Manual @ KP 15+276 (OX-03) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Section Tie-in Welding | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CMA28-1030 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 HDD @ CH 0+517 - 0+556 (HDD-01) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CNH01-1020 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 HDD @ CH 1+006 - 1+056 (HDD-02) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CNH02-1020 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 HDD @ CH 2+845 - 3+029 (HDD-03) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CNH03-1020 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 HDD @ CH 4+392 - 4+477 (HDD-04) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CNH04-1020 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 HDD @ CH 9+139 - 9+322 (HDD-05) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CNH05-1020 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 HDD @ CH 10+556 - 10+647 (HDD-06) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CNH06-1020 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 HDD @ CH 12+216 - 12+275 (HDD-07) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CNH07-1020 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 HDD @ CH 16+746 - 16+764 (HDD-08) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CNH08-1020 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.9.1 HDD @ CH 1+401 - 1+551 (HDD-02) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CNH2-1020 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 HDD @ CH 0+236 - 0+389 (HDD-01) | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | HDD Drilling & Pulling (Pilot, Reaming & Pulling) | Complete Pipeline welding - 4" Nitrogen Pipeline | C-4N-H5HG-CNH1-1020 | ML1909-E36 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.3 Hydrotesting | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | De-watering | Achieve Mechanical Completion of PL & facilities- ( 4" Water line) | C-4W-SVHG-PIPEL-7610 | ML1939-E39 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.5.9 Temporary Pig Receiver (4'' Nitrogen Pipeline) Piping Hook-upCCOH4NPI51 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Ext. Coating for Weld Joint | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | C-4N-HG-TPR-PL-1030 | ML1949-E40 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.8.1 Telecommunication Works CCOH4NIC52 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | FO Cable OTDR Testing & Splicing | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | C-4N-HG-TPR-TE-1420 | ML1949-E40 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Bolt Torquing/ Re-Instatement | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | C-4N-HG-TPR-PI-2000 | ML1949-E40 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH4NME50 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Pig Receiver 4" | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | C-4N-HG-TPR-ME-1100 | ML1949-E40 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.5.11 Temporary Pig Launcher (4'' Nitrogen Pipeline) Piping Hook-upCCOH5PI505 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Ext. Coating for Weld Joint | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | C-4N-H5-TPL-PL-1030 | ML1949-E40 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.8.1 Telecommunication Works CCOH5IC528 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | FO Cable OTDR Testing & Splicing | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | C-4N-H5-TPL-TE-1420 | ML1949-E40 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.9.1 Electrical Shutdown (PDBs)CCOH5ST529 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Electrical Shutdown (PDBs) | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | C-4N-H5-TPL-EL-1000 | ML1949-E40 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.5.10 Tie In to existing SkidCCOH5PI504 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Isolation Joint | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | C-4N-H5-TPL-PL-1000 | ML1949-E40 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.2 Cable Laying & TerminationCCOH5EL526 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Glanding & Termination for CP S/m | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | C-4N-H5-TPL-CA-1030 | ML1949-E40 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.6.1 E&I WorksCCOH5EL524 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Glanding & Termination | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | C-4N-H5-TPL-EI-2050 | ML1949-E40 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH5PI555 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Bolt Torquing/ Re-Instatement | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | C-4N-H5-TPL-PI-2000 | ML1949-E40 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.3.1 Mechanical Works and Equipment Installation (Temporary Scraper Trap )CCOH5ME502 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Pig Launcher 4" | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | C-4N-H5-TPL-ME-1000 | ML1949-E40 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.33 ROW Restoration/ Marker Post/ Crash BarrierCCOPL4"126 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | ROW Restoration/ Installation of Marker Post/Sign Board | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | C-4N-H5HG-PIPEL-7800 | ML1949-E40 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.33 ROW Restoration/ Marker Post/ Crash BarrierCCOPL4"126 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Crash Barriers (If any) | Achieve Mechanical Completion of PL & facilities- ( 4" Nitrogen PL) | C-4N-H5HG-PIPEL-7810 | ML1949-E40 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.4 ROW Restoration/Marker Post/Crash BarrierCCOPL56229 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | ROW Restoration/ Installation of Marker Post/Sign Board | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | C-56-01HG-PL-CI-7800 | ML1959-E41 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.4 ROW Restoration/Marker Post/Crash BarrierCCOPL56229 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Crash Barriers (If any) | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | C-56-01HG-PL-CI-7810 | ML1959-E41 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.7 Dewatering, Swabbing, & DryingCCOPL56227 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Swabing & Drying (Upto Dew Point Temp.) | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | C-56-HC01-PL-ME-7620 | ML1959-E41 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Crash Barriers (If any) | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | C-56-HC01-PL-CI-8010 | ML1959-E41 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Installation of Marker Post/Sign Board | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | C-56-HC01-PL-CI-8000 | ML1959-E41 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | PRECOM-56-HGHC-1000 | ML1959-E41 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.6.1 Tie -in WorksCCOJ42PI72 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Tie-In with 36" Pipeline | Achieve Mechanical Completion of PL & facilities- ( 36"Jump over Line) | C-36-KM-HT-ME-2000 | ML1969-E42 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.5.6 Isolation of Hot Tap JointCCOJ42HT140 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Isolation of Hot Tap Joint | Achieve Mechanical Completion of PL & facilities- ( 36"Jump over Line) | C-36-KM-HT04-ME-1050 | ML1969-E42 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.4.6 Isolation of Hot Tap JointCCOJ42HT80 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Isolation of Hot Tap Joint | Achieve Mechanical Completion of PL & facilities- ( 36"Jump over Line) | C-36-KM-HT03-ME-1050 | ML1969-E42 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.3.2 E&I WorksCCOJ42EL51 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Glanding & Termination | Achieve Mechanical Completion of PL & facilities- ( 36"Jump over Line) | C-36-KM-HT-EI-2050 | ML1969-E42 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.2.6 Final Bolt Torquing/ Re-InstatementCCOJ42PI122 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Final Bolt Torquing/ Re-Instatement | Achieve Mechanical Completion of PL & facilities- ( 36"Jump over Line) | C-36-KM-HT-PI-2000 | ML1969-E42 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-commissioning from HGCP to BVS-01 | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-HG01-1000 | ML1979-E43 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-commissioning from BVS-02 to BVS-01 | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-0201-1000 | ML1979-E43 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2 Pre-commissioning from BVS-02 to BVS-03CPCPL52327.5 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-commissioning from BVS-02 to BVS-03 | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-0203-1000 | ML1979-E43 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-commissioning from BVS-03 to BVS-04 | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-0304-1000 | ML1979-E43 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-commissioning from BVS-05 to BVS-06 | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-0506-1000 | ML1979-E43 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-commissioning from BVS-06 to CRS Sweihan | Achieve Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-06CR-1000 | ML1979-E43 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.7.12.3 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)CCOB6PI10 | P2543-R01-Oct24..4.4.2 Commissioning | Piping Works (Pre-Fab/Erection/Welding/NDT/Coating) | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | C-DBV6-PI-1000 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.2.12.2.1 Final Bolt Torquing/ Re-InstatementCCOH4WPI100 | P2543-R01-Oct24..4.4.2 Commissioning | Final Bolt Torquing/ Re-Instatement | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | C-4W-TI-PI-2000 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.5.34 Pig Receiver 838-V-601 56'' Pipeline/ Piping Hook-up CCOH56PI51 | P2543-R01-Oct24..4.4.2 Commissioning | Ext. Coating for Weld Joint | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | C-56-PR-838-PL-1030 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.5.10 Tie In to existing SkidCCOH5PI504 | P2543-R01-Oct24..4.4.2 Commissioning | Installation of Isolation Joint | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | C-4N-H5-TPL-PL-1000 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.3.5 Hot Tapping of Existing 42" LineCCOHBHT305 | P2543-R01-Oct24..4.4.2 Commissioning | Hot Tapping of Existing 42" Line | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | C-56-G-HT101-ME-1040 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.4.5 Hot Tapping of Existing 30" LineCCOHBHT365 | P2543-R01-Oct24..4.4.2 Commissioning | Hot Tapping of Existing 30" Line | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | C-56-G-HT102-ME-1040 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.5.5 Hot Tapping of Existing 42" LineCCOHBHT425 | P2543-R01-Oct24..4.4.2 Commissioning | Hot Tapping of Existing 42" Line | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | C-56-G-HT103-ME-1040 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.3.10.6.1 Tie-insCCOHBPI311 | P2543-R01-Oct24..4.4.2 Commissioning | Tie-In with 30" Pipeline | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | C-56-G-HT-ME-2000 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.5.1 Pig Launcher 607-V-603 56'' Pipeline/Piping Hook-upCCOHBPI312 | P2543-R01-Oct24..4.4.2 Commissioning | Ext. Coating for Weld Joint | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | C-56-PL-607-PL-1030 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.2.12.5.1 Shutdown Connection to Existing Substation Unit 607CCOHBST204 | P2543-R01-Oct24..4.4.2 Commissioning | Termination & Connection with Existing Power Distribution Network | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | C-56-EB2-EL-1600 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.4 ROW Restoration/Marker Post/Crash BarrierCCOPL56229 | P2543-R01-Oct24..4.4.2 Commissioning | ROW Restoration/ Installation of Marker Post/Sign Board | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | C-56-01HG-PL-CI-7800 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.1.12.2.1 Piping Works (Pre-Fab/Erection/Welding/NDT/Coating)(including painting subcontract)CCOSV3PI50 | P2543-R01-Oct24..4.4.2 Commissioning | Piping Works (RTP) | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | C-4W-081-03-PI-1000 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.5.9 Temporary Pig Receiver (4'' Nitrogen Pipeline) Piping Hook-upCCOH4NPI51 | P2543-R01-Oct24..4.4.2 Commissioning | Ext. Coating for Weld Joint | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | C-4N-HG-TPR-PL-1030 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.5.11 Temporary Pig Launcher (4'' Nitrogen Pipeline) Piping Hook-upCCOH5PI505 | P2543-R01-Oct24..4.4.2 Commissioning | Ext. Coating for Weld Joint | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | C-4N-H5-TPL-PL-1030 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.5.2.8.1 PrecommissioningCPC-H51000 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | PRECOM-4NHG-TPR-1000 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.5.1.8.1 PrecommissioningCPC-H51010 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | PRECOM-4NH5-TPL-1000 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | PRECOM-56-PL-1000 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | PRECOM-56-EB2-1000 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.1.8.3.1 PrecommissioningCPC-HBS502 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | PRECOM-56-G-1000 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.6.1.8.1 PrecommissioningCPC-SV3100 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | PRECOM-4W-08103-1000 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.6.2.8.1 PrecommissioningCPC-SV3101 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | PRE-COM1310 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | PRECOM-56-59101-1000 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | PRE-COM1330 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | PRECOM-56-PR-1000 | CCM-PM4510 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.4.2 Commissioning | Glanding & Termination | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-541CR-EI-1040 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.3.1 Control System Modifications and Telecommunication WorksCCOC541IC2 | P2543-R01-Oct24..4.4.2 Commissioning | Telecommunication Works (Modification of Existing Telecom Cabinet) | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-541CR-TE-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.5.1 Pig Launcher 838-V-602 52'' Pipeline/Piping Hook-upCCOH52PI70 | P2543-R01-Oct24..4.4.2 Commissioning | Ext. Coating for Weld Joint | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-52-PL-838-PL-1030 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.5.5 Hot Tapping of Existing 36" LineCCOJ42HT130 | P2543-R01-Oct24..4.4.2 Commissioning | Hot Tapping of Existing 36" Line | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-36-KM-HT04-ME-1040 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.4.5 Hot Tapping of Existing 36" LineCCOJ42HT70 | P2543-R01-Oct24..4.4.2 Commissioning | Hot Tapping of Existing 36" Line | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-36-KM-HT03-ME-1040 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.6.1 Tie -in WorksCCOJ42PI72 | P2543-R01-Oct24..4.4.2 Commissioning | Tie-In with 36" Pipeline | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-36-KM-HT-ME-2000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.4.22.2.3 Transformer / Directly Buried MV Cables (including testing)CCOSW52E22 | P2543-R01-Oct24..4.4.2 Commissioning | Transformer / Directly Buried MV Cables (including testing) | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-52-OHPL-EL-1400 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.4.22.3.1 Shutdown Connection of OHL & Cable TestingCCOSW52S10 | P2543-R01-Oct24..4.4.2 Commissioning | Shutdown Connection of OHL & Cable Testing | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-52-OHPL-EL-2000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.3.5 Hot Tapping of Existing 48" LineCCOSWHT501 | P2543-R01-Oct24..4.4.2 Commissioning | Hot Tapping of Existing 48" Line | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-52-D-HT002-ME-1040 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.4.1 Tie in works to 52'' and 20'' PipelineCCOSWPI512 | P2543-R01-Oct24..4.4.2 Commissioning | Tie-In with 30" Pipeline | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-52-D-HT-ME-2000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.5.1 Pig Receiver 839-V-101 52'' Pipeline/ Piping Hook-upCCOSWPI514 | P2543-R01-Oct24..4.4.2 Commissioning | Ext. Coating for Weld Joint | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-52-PR-839-PL-1030 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.10.12.1.1 Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB BuildingCCOU577CS5 | P2543-R01-Oct24..4.4.2 Commissioning | Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB Building | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-577-CI-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.10.12.2.1 Telecommunication Works (new telecom cabinet and cable laying and terminations)CCOU577IC1 | P2543-R01-Oct24..4.4.2 Commissioning | Telecommunication Works (new telecom cabinet and cable laying and terminations) | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-577-TE-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.11.12.1.1 Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS1 | P2543-R01-Oct24..4.4.2 Commissioning | Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603) | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-601-CI-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.11.12.2.1 Telecommunication Works (modifications of existing telecom cabinet)CCOU601IC1 | P2543-R01-Oct24..4.4.2 Commissioning | Telecommunication Works (modifications of existing telecom cabinet) | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-601-TE-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.4 ShutdownCCOU800ST4 | P2543-R01-Oct24..4.4.2 Commissioning | Shutdown | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-MAQTA-EL-2000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2.6 ROW Restoration from HGCP to KP 16.7 (Deleted SOW)CCOPL52324.3 | P2543-R01-Oct24..4.4.2 Commissioning | Installation of Crash Barriers (If any) (Deleted SOW) | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-52-HG01-PL-CI-7820 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.4.22.1.3 Backfilling for CablesCCOSWCS323 | P2543-R01-Oct24..4.4.2 Commissioning | Backfilling for Cables | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-52-OHPL-CI-1400 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.4.3 Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOSWIC332 | P2543-R01-Oct24..4.4.2 Commissioning | CCTV Installation | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-52-EB1-TE-1600 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.4.3 Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOSWIC332 | P2543-R01-Oct24..4.4.2 Commissioning | Security System (Including subcontract for FOC Splicing / Termination / Testing ) | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-52-EB1-TE-1610 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.10.12.1.2 Backfilling - 577-SV-02 Passive cooling Shelter to HGCP - MCB BuildingCCOU57CS10 | P2543-R01-Oct24..4.4.2 Commissioning | Backfilling - 577-SV-02 Passive cooling Shelter to HGCP - MCB Building | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-577-CI-1010 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.11.12.1.2 Backfilling - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS2 | P2543-R01-Oct24..4.4.2 Commissioning | Backfilling - Tahammama-C E&I Building to Launcher Station (607-V-603) | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | C-601-CI-1010 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning BVS-6 | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | PRECOM-52-59806-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning BVS-5 | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | PRECOM-56-59805-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning BVS-4 | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | PRECOM-56-59804-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning BVS-3 | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | PRECOM-56-59803-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning BVS-2 | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | PRECOM-56-59802-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning BVS-1 | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | PRECOM-56-59801-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning Pig Launcher 838-V-602 | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | PRECOM-52-PL-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.4 Precommissioning DEL/TFP PipelineCPCHGCP522 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning DEL/TFP Pipeline | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | PRECOM-52-D-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | P2543-R01-Oct24..4.4.2 Commissioning | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | PRECOM-52-IDS2-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | P2543-R01-Oct24..4.4.2 Commissioning | Pre-Commissioning Intrusion Detection KP122 to KP123 | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | PRECOM-52-IDS3-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | P2543-R01-Oct24..4.4.2 Commissioning | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | PRECOM-52-IDS1-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | PRECOM-36-KM-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | P2543-R01-Oct24..4.4.2 Commissioning | Pre-commissioning from HGCP to BVS-01 | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | PRECOM-52-HG01-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning Electrical Building Type-I | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | PRECOM-52-EB1-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning Pig Receiver 839-V-101 | PAC-2 for for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | PRECOM-52-PR-1000 | CCM-PM4520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.4.2 Commissioning | Glanding & Termination | Wrap up works for PAC-2 | C-541CR-EI-1040 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.3.1 Control System Modifications and Telecommunication WorksCCOC541IC2 | P2543-R01-Oct24..4.4.2 Commissioning | Telecommunication Works (Modification of Existing Telecom Cabinet) | Wrap up works for PAC-2 | C-541CR-TE-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.5.1 Pig Launcher 838-V-602 52'' Pipeline/Piping Hook-upCCOH52PI70 | P2543-R01-Oct24..4.4.2 Commissioning | Ext. Coating for Weld Joint | Wrap up works for PAC-2 | C-52-PL-838-PL-1030 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.5.5 Hot Tapping of Existing 36" LineCCOJ42HT130 | P2543-R01-Oct24..4.4.2 Commissioning | Hot Tapping of Existing 36" Line | Wrap up works for PAC-2 | C-36-KM-HT04-ME-1040 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.4.5 Hot Tapping of Existing 36" LineCCOJ42HT70 | P2543-R01-Oct24..4.4.2 Commissioning | Hot Tapping of Existing 36" Line | Wrap up works for PAC-2 | C-36-KM-HT03-ME-1040 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.6.1 Tie -in WorksCCOJ42PI72 | P2543-R01-Oct24..4.4.2 Commissioning | Tie-In with 36" Pipeline | Wrap up works for PAC-2 | C-36-KM-HT-ME-2000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.4.22.2.3 Transformer / Directly Buried MV Cables (including testing)CCOSW52E22 | P2543-R01-Oct24..4.4.2 Commissioning | Transformer / Directly Buried MV Cables (including testing) | Wrap up works for PAC-2 | C-52-OHPL-EL-1400 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.4.22.3.1 Shutdown Connection of OHL & Cable TestingCCOSW52S10 | P2543-R01-Oct24..4.4.2 Commissioning | Shutdown Connection of OHL & Cable Testing | Wrap up works for PAC-2 | C-52-OHPL-EL-2000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.3.5 Hot Tapping of Existing 48" LineCCOSWHT501 | P2543-R01-Oct24..4.4.2 Commissioning | Hot Tapping of Existing 48" Line | Wrap up works for PAC-2 | C-52-D-HT002-ME-1040 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.4.1 Tie in works to 52'' and 20'' PipelineCCOSWPI512 | P2543-R01-Oct24..4.4.2 Commissioning | Tie-In with 30" Pipeline | Wrap up works for PAC-2 | C-52-D-HT-ME-2000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.5.1 Pig Receiver 839-V-101 52'' Pipeline/ Piping Hook-upCCOSWPI514 | P2543-R01-Oct24..4.4.2 Commissioning | Ext. Coating for Weld Joint | Wrap up works for PAC-2 | C-52-PR-839-PL-1030 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.10.12.1.1 Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB BuildingCCOU577CS5 | P2543-R01-Oct24..4.4.2 Commissioning | Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB Building | Wrap up works for PAC-2 | C-577-CI-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.10.12.2.1 Telecommunication Works (new telecom cabinet and cable laying and terminations)CCOU577IC1 | P2543-R01-Oct24..4.4.2 Commissioning | Telecommunication Works (new telecom cabinet and cable laying and terminations) | Wrap up works for PAC-2 | C-577-TE-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.11.12.1.1 Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS1 | P2543-R01-Oct24..4.4.2 Commissioning | Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603) | Wrap up works for PAC-2 | C-601-CI-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.11.12.2.1 Telecommunication Works (modifications of existing telecom cabinet)CCOU601IC1 | P2543-R01-Oct24..4.4.2 Commissioning | Telecommunication Works (modifications of existing telecom cabinet) | Wrap up works for PAC-2 | C-601-TE-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.4 ShutdownCCOU800ST4 | P2543-R01-Oct24..4.4.2 Commissioning | Shutdown | Wrap up works for PAC-2 | C-MAQTA-EL-2000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2.6 ROW Restoration from HGCP to KP 16.7 (Deleted SOW)CCOPL52324.3 | P2543-R01-Oct24..4.4.2 Commissioning | Installation of Crash Barriers (If any) (Deleted SOW) | Wrap up works for PAC-2 | C-52-HG01-PL-CI-7820 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.4.22.1.3 Backfilling for CablesCCOSWCS323 | P2543-R01-Oct24..4.4.2 Commissioning | Backfilling for Cables | Wrap up works for PAC-2 | C-52-OHPL-CI-1400 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.4.3 Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOSWIC332 | P2543-R01-Oct24..4.4.2 Commissioning | CCTV Installation | Wrap up works for PAC-2 | C-52-EB1-TE-1600 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.4.3 Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOSWIC332 | P2543-R01-Oct24..4.4.2 Commissioning | Security System (Including subcontract for FOC Splicing / Termination / Testing ) | Wrap up works for PAC-2 | C-52-EB1-TE-1610 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.10.12.1.2 Backfilling - 577-SV-02 Passive cooling Shelter to HGCP - MCB BuildingCCOU57CS10 | P2543-R01-Oct24..4.4.2 Commissioning | Backfilling - 577-SV-02 Passive cooling Shelter to HGCP - MCB Building | Wrap up works for PAC-2 | C-577-CI-1010 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.11.12.1.2 Backfilling - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS2 | P2543-R01-Oct24..4.4.2 Commissioning | Backfilling - Tahammama-C E&I Building to Launcher Station (607-V-603) | Wrap up works for PAC-2 | C-601-CI-1010 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning BVS-6 | Wrap up works for PAC-2 | PRECOM-52-59806-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning BVS-5 | Wrap up works for PAC-2 | PRECOM-56-59805-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning BVS-4 | Wrap up works for PAC-2 | PRECOM-56-59804-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning BVS-3 | Wrap up works for PAC-2 | PRECOM-56-59803-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning BVS-2 | Wrap up works for PAC-2 | PRECOM-56-59802-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning BVS-1 | Wrap up works for PAC-2 | PRECOM-56-59801-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning Pig Launcher 838-V-602 | Wrap up works for PAC-2 | PRECOM-52-PL-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.4 Precommissioning DEL/TFP PipelineCPCHGCP522 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning DEL/TFP Pipeline | Wrap up works for PAC-2 | PRECOM-52-D-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | P2543-R01-Oct24..4.4.2 Commissioning | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | Wrap up works for PAC-2 | PRECOM-52-IDS2-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | P2543-R01-Oct24..4.4.2 Commissioning | Pre-Commissioning Intrusion Detection KP122 to KP123 | Wrap up works for PAC-2 | PRECOM-52-IDS3-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | P2543-R01-Oct24..4.4.2 Commissioning | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | Wrap up works for PAC-2 | PRECOM-52-IDS1-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning | Wrap up works for PAC-2 | PRECOM-36-KM-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | P2543-R01-Oct24..4.4.2 Commissioning | Pre-commissioning from HGCP to BVS-01 | Wrap up works for PAC-2 | PRECOM-52-HG01-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning Electrical Building Type-I | Wrap up works for PAC-2 | PRECOM-52-EB1-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning Pig Receiver 839-V-101 | Wrap up works for PAC-2 | PRECOM-52-PR-1000 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | P2543-R01-Oct24..4.4.2.1 System Commissioninng - Habshan Complex to 56” P/L Fac. (56”) | Precommissioning | Commissioning | PRECOM-56-PL-1000 | CCM-PM4560 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | P2543-R01-Oct24..4.4.2.2 System Commissioninng - 56” P/L Facility to HGCP 56” P/R (56”) | Precommissioning | Commissioning | PRECOM-56-HGHC-1000 | CCM-PM4570 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | P2543-R01-Oct24..4.4.2.3 System Commissioninng - HGCP 52” P/L to Sweihan CRS 52” P/R (52”) | Pre-commissioning from HGCP to BVS-01 | Commissioning | PRECOM-52-HG01-1000 | CCM-PM4580 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | P2543-R01-Oct24..4.4.2.4 System Commissioninng - 36'' Jump-over connection at KM-42 | Precommissioning | Commissioning | PRECOM-36-KM-1000 | CCM-PM4590 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.5.3.8.1 Pre-commissioningCCOPL4"125 | P2543-R01-Oct24..4.4.2.5 System Commissioninng - Habshan-5 4” P/L to HGCP 4” P/R (4”) | Precommissioning | Commissioning | PRECOM-4N-H5HG-1000 | CCM-PM4600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.6.2.8.1 PrecommissioningCPC-SV3101 | P2543-R01-Oct24..4.4.2.6 System Commissioninng - SV-03 (KP 96) to HGCP (4'') | Precommissioning | Commissioning | PRE-COM1310 | CCM-PM4610 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.7.8.1 PrecommissioningCPCB611 | P2543-R01-Oct24..4.4.2.7 System Commissioninng - Dolphin Existing BVS -06 | Precommissioning | Commissioning | PRE-COM1330 | CCM-PM4620 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.5.1 Pig Launcher 838-V-602 52'' Pipeline/Piping Hook-upCCOH52PI70 | P2543-R01-Oct24..4.4.AB As-Built & Final Documentation | Ext. Coating for Weld Joint | Demolitionbilization | C-52-PL-838-PL-1030 | A3980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.5.34 Pig Receiver 838-V-601 56'' Pipeline/ Piping Hook-up CCOH56PI51 | P2543-R01-Oct24..4.4.AB As-Built & Final Documentation | Ext. Coating for Weld Joint | Demolitionbilization | C-56-PR-838-PL-1030 | A3980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.5.1 Pig Launcher 607-V-603 56'' Pipeline/Piping Hook-upCCOHBPI312 | P2543-R01-Oct24..4.4.AB As-Built & Final Documentation | Ext. Coating for Weld Joint | Demolitionbilization | C-56-PL-607-PL-1030 | A3980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.5.1 Pig Receiver 839-V-101 52'' Pipeline/ Piping Hook-upCCOSWPI514 | P2543-R01-Oct24..4.4.AB As-Built & Final Documentation | Ext. Coating for Weld Joint | Demolitionbilization | C-52-PR-839-PL-1030 | A3980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.5.11 Temporary Pig Launcher (4'' Nitrogen Pipeline) Piping Hook-upCCOH5PI505 | P2543-R01-Oct24..4.4.AB As-Built & Final Documentation | Ext. Coating for Weld Joint | Demolitionbilization | C-4N-H5-TPL-PL-1030 | A3980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | P2543-R01-Oct24..4.4.AB As-Built & Final Documentation | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | Demolitionbilization | PRECOM-52-IDS2-1000 | A3980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | P2543-R01-Oct24..4.4.AB As-Built & Final Documentation | Pre-Commissioning Intrusion Detection KP122 to KP123 | Demolitionbilization | PRECOM-52-IDS3-1000 | A3980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.2.1 Electrical & Instrumentation Works (RTU, UPS Feeder Installation)CCOC541EL1 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Glanding & Termination | Intelligent Pigging Baseline Survey | C-541CR-EI-1040 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.9.12.3.1 Control System Modifications and Telecommunication WorksCCOC541IC2 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Telecommunication Works (Modification of Existing Telecom Cabinet) | Intelligent Pigging Baseline Survey | C-541CR-TE-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.5.1 Pig Launcher 838-V-602 52'' Pipeline/Piping Hook-upCCOH52PI70 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Ext. Coating for Weld Joint | Intelligent Pigging Baseline Survey | C-52-PL-838-PL-1030 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.5.5 Hot Tapping of Existing 36" LineCCOJ42HT130 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Hot Tapping of Existing 36" Line | Intelligent Pigging Baseline Survey | C-36-KM-HT04-ME-1040 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.4.5 Hot Tapping of Existing 36" LineCCOJ42HT70 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Hot Tapping of Existing 36" Line | Intelligent Pigging Baseline Survey | C-36-KM-HT03-ME-1040 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.4.12.6.1 Tie -in WorksCCOJ42PI72 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Tie-In with 36" Pipeline | Intelligent Pigging Baseline Survey | C-36-KM-HT-ME-2000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.4.22.2.3 Transformer / Directly Buried MV Cables (including testing)CCOSW52E22 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Transformer / Directly Buried MV Cables (including testing) | Intelligent Pigging Baseline Survey | C-52-OHPL-EL-1400 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.4.22.3.1 Shutdown Connection of OHL & Cable TestingCCOSW52S10 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Shutdown Connection of OHL & Cable Testing | Intelligent Pigging Baseline Survey | C-52-OHPL-EL-2000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.3.5 Hot Tapping of Existing 48" LineCCOSWHT501 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Hot Tapping of Existing 48" Line | Intelligent Pigging Baseline Survey | C-52-D-HT002-ME-1040 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.3.21.4.1 Tie in works to 52'' and 20'' PipelineCCOSWPI512 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Tie-In with 30" Pipeline | Intelligent Pigging Baseline Survey | C-52-D-HT-ME-2000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.5.1 Pig Receiver 839-V-101 52'' Pipeline/ Piping Hook-upCCOSWPI514 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Ext. Coating for Weld Joint | Intelligent Pigging Baseline Survey | C-52-PR-839-PL-1030 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.10.12.1.1 Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB BuildingCCOU577CS5 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Trenching - 577-SV-02 Passive cooling Shelter to PL - MCB Building | Intelligent Pigging Baseline Survey | C-577-CI-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.10.12.2.1 Telecommunication Works (new telecom cabinet and cable laying and terminations)CCOU577IC1 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Telecommunication Works (new telecom cabinet and cable laying and terminations) | Intelligent Pigging Baseline Survey | C-577-TE-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.11.12.1.1 Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS1 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Trenching - Tahammama-C E&I Building to Launcher Station (607-V-603) | Intelligent Pigging Baseline Survey | C-601-CI-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.11.12.2.1 Telecommunication Works (modifications of existing telecom cabinet)CCOU601IC1 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Telecommunication Works (modifications of existing telecom cabinet) | Intelligent Pigging Baseline Survey | C-601-TE-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.8.12.4 ShutdownCCOU800ST4 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Shutdown | Intelligent Pigging Baseline Survey | C-MAQTA-EL-2000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2.6 ROW Restoration from HGCP to KP 16.7 (Deleted SOW)CCOPL52324.3 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Installation of Crash Barriers (If any) (Deleted SOW) | Intelligent Pigging Baseline Survey | C-52-HG01-PL-CI-7820 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.4.22.1.3 Backfilling for CablesCCOSWCS323 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Backfilling for Cables | Intelligent Pigging Baseline Survey | C-52-OHPL-CI-1400 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.4.3 Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOSWIC332 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | CCTV Installation | Intelligent Pigging Baseline Survey | C-52-EB1-TE-1600 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.2.22.4.3 Security System (Including subcontract for FOC Splicing / Termination / Testing )CCOSWIC332 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Security System (Including subcontract for FOC Splicing / Termination / Testing ) | Intelligent Pigging Baseline Survey | C-52-EB1-TE-1610 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.10.12.1.2 Backfilling - 577-SV-02 Passive cooling Shelter to HGCP - MCB BuildingCCOU57CS10 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Backfilling - 577-SV-02 Passive cooling Shelter to HGCP - MCB Building | Intelligent Pigging Baseline Survey | C-577-CI-1010 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.11.12.1.2 Backfilling - Tahammama-C E&I Building to Launcher Station (607-V-603)CCOU601CS2 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Backfilling - Tahammama-C E&I Building to Launcher Station (607-V-603) | Intelligent Pigging Baseline Survey | C-601-CI-1010 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Precommissioning BVS-6 | Intelligent Pigging Baseline Survey | PRECOM-52-59806-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Precommissioning BVS-5 | Intelligent Pigging Baseline Survey | PRECOM-56-59805-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Precommissioning BVS-4 | Intelligent Pigging Baseline Survey | PRECOM-56-59804-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Precommissioning BVS-3 | Intelligent Pigging Baseline Survey | PRECOM-56-59803-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Precommissioning BVS-2 | Intelligent Pigging Baseline Survey | PRECOM-56-59802-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Precommissioning BVS-1 | Intelligent Pigging Baseline Survey | PRECOM-56-59801-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Precommissioning Pig Launcher 838-V-602 | Intelligent Pigging Baseline Survey | PRECOM-52-PL-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.4 Precommissioning DEL/TFP PipelineCPCHGCP522 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Precommissioning DEL/TFP Pipeline | Intelligent Pigging Baseline Survey | PRECOM-52-D-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | Intelligent Pigging Baseline Survey | PRECOM-52-IDS2-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Pre-Commissioning Intrusion Detection KP122 to KP123 | Intelligent Pigging Baseline Survey | PRECOM-52-IDS3-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | Intelligent Pigging Baseline Survey | PRECOM-52-IDS1-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.4.8.1 PrecommissioningCPCJ421 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Precommissioning | Intelligent Pigging Baseline Survey | PRECOM-36-KM-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Pre-commissioning from HGCP to BVS-01 | Intelligent Pigging Baseline Survey | PRECOM-52-HG01-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Precommissioning Electrical Building Type-I | Intelligent Pigging Baseline Survey | PRECOM-52-EB1-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | P2543-R01-Oct24..4.4.AB.3 As-built Survey | Precommissioning Pig Receiver 839-V-101 | Intelligent Pigging Baseline Survey | PRECOM-52-PR-1000 | CCM-PM4540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.4 ROW Restoration/Marker Post/Crash BarrierCCOPL56229 | P2543-R01-Oct24..4.4.2 Commissioning | Installation of Crash Barriers (If any) | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | C-56-01HG-PL-CI-7810 | CCM-PM4510 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | P2543-R01-Oct24..4.4.2 Commissioning | Precommissioning | PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | PRECOM-56-HGHC-1000 | CCM-PM4510 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Electrical & Earthing Cable Laying | Installation of Light Pole, Lighting & Fixtures | C-56-PR-838-EI-2000 | C-56-PR-838-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | Installation of Cable Trays | Installation of Light Pole, Lighting & Fixtures | C-56-PR-838-EI-2020 | C-56-PR-838-EI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | P2543-R01-Oct24..4.3.1.2.21.12.1.16 Paving Works CCOH56CS37 | Installation of Light Pole, Lighting & Fixtures | Paving of Interlock tiles & Kerb Stone Embankment | C-56-PR-838-EI-1800 | C-56-PR-838-CI-2600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.21.12.6.28 Electrical Works CCOH56EL30 | P2543-R01-Oct24..4.3.1.2.21.12.6.29 E&I Cable Laying, Glanding & Termination CCOH56EL31 | Installation of Light Pole, Lighting & Fixtures | Glanding & Termination | C-56-PR-838-EI-1800 | C-56-PR-838-EI-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 2 | HE-PL-2490 | C-PER-1030 | FF | In Progress | Not Started | 14
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 6 | HE-PL-2490 | C-PER-1070 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 12 | HE-PL-2490 | C-PER-1130 | SS | In Progress | Completed | 14
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13 | HE-PL-2490 | C-PER-1140 | SS | In Progress | Completed | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13A | HE-PL-2490 | C-PER-1150 | SS | In Progress | Completed | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 14 | HE-PL-2490 | C-PER-1160 | SS | In Progress | Completed | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | HE-PL-2490 | C-PER-1180 | SS | In Progress | Completed | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 17 | HE-PL-2490 | C-PER-1190 | SS | In Progress | Completed | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 18 | HE-PL-2490 | C-PER-1200 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 19 | HE-PL-2490 | C-PER-1210 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 20 | HE-PL-2490 | C-PER-1220 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 23 | HE-PL-2490 | C-PER-1250 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 24 | HE-PL-2490 | C-PER-1260 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 25A | HE-PL-2490 | C-PER-1280 | SS | In Progress | Completed | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 27 | HE-PL-2490 | C-PER-1300 | SS | In Progress | In Progress | 14
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 28 | HE-PL-2490 | C-PER-1310 | FF | In Progress | In Progress | 14
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 29 | HE-PL-2490 | C-PER-1320 | FF | In Progress | In Progress | 14
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 30 | HE-PL-2490 | C-PER-1330 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 31 | HE-PL-2490 | C-PER-1340 | FF | In Progress | In Progress | 14
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 1 | HE-PL-2430 | C-PER-1350 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 3 | HE-PL-2430 | C-PER-1370 | FF | In Progress | Not Started | 14
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 4 | HE-PL-2430 | C-PER-1380 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 5 | HE-PL-2430 | C-PER-1390 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 6 | HE-PL-2430 | C-PER-1400 | FF | In Progress | In Progress | 14
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 9 | HE-PL-2430 | C-PER-1430 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 10 | HE-PL-2430 | C-PER-1440 | SS | In Progress | In Progress | 14
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 11 | HE-PL-2430 | C-PER-1450 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 12 | HE-PL-2430 | C-PER-1460 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 13 | HE-PL-2430 | C-PER-1470 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 2 | HE-PL-2550 | C-PER-1490 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 3 | HE-PL-2550 | C-PER-1500 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 4 | HE-PL-2550 | C-PER-1510 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 5 | HE-PL-2550 | C-PER-1520 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 6 | HE-PL-2550 | C-PER-1530 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 7 | HE-PL-2550 | C-PER-1540 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 8 | HE-PL-2550 | C-PER-1550 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Trial pit, Crossing Methodology, NOC & Permits-4" Water Pipeline-NDRC 1 | HE-PL-3570 | C-PER-1560 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.11 Pipeline Alignment Sheets - 4" Waterline | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Trial pit, Crossing Methodology, NOC & Permits-4" Water Pipeline-NDRC 2 | HE-PL-3570 | C-PER-1570 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Station approach drawing-52" | NOC & Permits-BVS02-52" | HE-PL-2670 | C-PER-1590 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Station approach drawing-52" | NOC & Permits-BVS03-52" | HE-PL-2670 | C-PER-1600 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Station approach drawing-52" | NOC & Permits-BVS04-52" | HE-PL-2670 | C-PER-1610 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Station approach drawing-52" | NOC & Permits-BVS05-52" | HE-PL-2670 | C-PER-1620 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Station approach drawing-52" | NOC & Permits-BVS06-52" | HE-PL-2670 | C-PER-1630 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Mobilization of Job Performers-56" Pipelines & Stations,4" Pipeline | Receiving Permits-56" Pipelines & Stations,4" Pipeline | C-PER-0915 | C-PER-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.2.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52900 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 1 | Sheet Piling for Driving & Receiving Pit | C-PER-1020 | C-52-HG01-CNM01-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52902 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 2 | Sheet Piling for Driving & Receiving Pit | C-PER-1030 | C-52-HG01-CNM02-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.2.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52930 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 3 | Sheet Piling for Driving & Receiving Pit | C-PER-1040 | C-52-HG01-CNM03-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.2.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52936 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 4 | Sheet Piling for Driving & Receiving Pit | C-PER-1050 | C-52-HG01-CNM04-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 5 | Sheet Piling for Driving & Receiving Pit | C-PER-1060 | C-52-0102-CNM05-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 7 | Sheet Piling for Driving & Receiving Pit | C-PER-1080 | C-52-0102-CNM07-1000 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.8.21.3.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52942 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 8 | Sheet Piling for Driving & Receiving Pit | C-PER-1090 | C-52-0102-CNH08-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.8.21.3.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52944 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 9 | Sheet Piling for Driving & Receiving Pit | C-PER-1100 | C-52-0102-CNH09-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 10 | Sheet Piling for Driving & Receiving Pit | C-PER-1110 | C-52-0102-CNH10-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.17.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52904 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 17 | Sheet Piling for Driving & Receiving Pit | C-PER-1190 | C-52-0405-CNM17-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.17.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52906 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 18 | Sheet Piling for Driving & Receiving Pit | C-PER-1200 | C-52-0405-CNM18-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.17.21.8.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52962 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 19 | Sheet Piling for Driving & Receiving Pit | C-PER-1210 | C-52-0405-CNH19-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.17.21.8.5.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52908 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 20 | Sheet Piling for Driving & Receiving Pit | C-PER-1220 | C-52-0405-CNH20-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.17.21.8.7.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52916 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 24 | Sheet Piling for Driving & Receiving Pit | C-PER-1260 | C-52-0405-CNH24-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.18.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52922 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 27 | Sheet Piling for Driving & Receiving Pit | C-PER-1300 | C-52-0506-CNH27-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.19.8.5.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52926 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 30 | Sheet Piling for Driving & Receiving Pit | C-PER-1330 | C-52-06CR-CNH30-1000 | FS | In Progress | Not Started | 15
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 31 | Sheet Piling for Driving & Receiving Pit | C-PER-1340 | C-52-06CR-CNM31-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 8 | Sheet Piling for Driving & Receiving Pit | C-PER-1420 | C-56-HC01-CNM08-1000 | FS | Not Started | Not Started | 15
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 3 | Sheet Piling for Driving & Receiving Pit | C-PER-1370 | C-56-HC01-CNM03-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 5 | Sheet Piling for Driving & Receiving Pit | C-PER-1390 | C-56-HC01-CNH05-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 2 | Sheet Piling for Driving & Receiving Pit | C-PER-1360 | C-56-HC01-CNH02-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 1 | Sheet Piling for Driving & Receiving Pit | C-PER-1350 | C-56-HC01-CNH01-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.3.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56916 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 13 | Sheet Piling for Driving & Receiving Pit | C-PER-1470 | C-56-01HG-CNM13-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.3.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56914 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 12 | Sheet Piling for Driving & Receiving Pit | C-PER-1460 | C-56-01HG-CNM12-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.3.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56912 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 11 | Sheet Piling for Driving & Receiving Pit | C-PER-1450 | C-56-01HG-CNM11-1000 | FS | Not Started | Not Started | 10
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.3.12.6.4.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56908 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 10 | Sheet Piling for Driving & Receiving Pit | C-PER-1440 | C-56-01HG-CNH10-1000 | FS | In Progress | Not Started | 25
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 6 | C-PER-1080 | C-PER-1070 | SS | Completed | In Progress | 7
P2543-R01-Oct24..1.EN.1.38 Crossing Schedule-52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Crossing Schedule-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 18 | HE-PL-3090 | C-PER-1200 | FF | Not Started | In Progress | 14
P2543-R01-Oct24..1.EN.1.38 Crossing Schedule-52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Crossing Schedule-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 19 | HE-PL-3090 | C-PER-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.38 Crossing Schedule-52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Crossing Schedule-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 20 | HE-PL-3090 | C-PER-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 2 | C-PER-1000 | C-PER-1360 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 3 | C-PER-1000 | C-PER-1370 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 4 | C-PER-1000 | C-PER-1380 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 5 | C-PER-1000 | C-PER-1390 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 6 | C-PER-1000 | C-PER-1400 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 8 | C-PER-1000 | C-PER-1420 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 9 | C-PER-1000 | C-PER-1430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 11 | C-PER-1000 | C-PER-1450 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 13 | C-PER-1000 | C-PER-1470 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 1 | C-PER-1000 | C-PER-1480 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 2 | C-PER-1000 | C-PER-1490 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 3 | C-PER-1000 | C-PER-1500 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 4 | C-PER-1000 | C-PER-1510 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 5 | C-PER-1000 | C-PER-1520 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 6 | C-PER-1000 | C-PER-1530 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 7 | C-PER-1000 | C-PER-1540 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 8 | C-PER-1000 | C-PER-1550 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-4" Water Pipeline-NDRC 1 | C-PER-1000 | C-PER-1560 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Trial pit, Crossing Methodology, NOC & Permits-4" Water Pipeline-NDRC 2 | C-PER-1000 | C-PER-1570 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.5.4.12.3.1.1 HDD @ CH 0+517 - 0+556 (HDD-01) | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 1 | Excavation for Entry & Exit Pit Preparation | C-PER-1480 | C-4N-H5HG-CNH01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.5.4.12.3.2.1 HDD @ CH 1+006 - 1+056 (HDD-02) | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 2 | Excavation for Entry & Exit Pit Preparation | C-PER-1490 | C-4N-H5HG-CNH02-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.5.4.12.3.3.1 HDD @ CH 2+845 - 3+029 (HDD-03) | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 3 | Excavation for Entry & Exit Pit Preparation | C-PER-1500 | C-4N-H5HG-CNH03-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.5.4.12.3.4.1 HDD @ CH 4+392 - 4+477 (HDD-04) | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 4 | Excavation for Entry & Exit Pit Preparation | C-PER-1510 | C-4N-H5HG-CNH04-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.5.4.12.3.5.1 HDD @ CH 9+139 - 9+322 (HDD-05) | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 5 | Excavation for Entry & Exit Pit Preparation | C-PER-1520 | C-4N-H5HG-CNH05-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.5.4.12.3.6.1 HDD @ CH 10+556 - 10+647 (HDD-06) | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 6 | Excavation for Entry & Exit Pit Preparation | C-PER-1530 | C-4N-H5HG-CNH06-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.5.4.12.3.7.1 HDD @ CH 12+216 - 12+275 (HDD-07) | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 7 | Excavation for Entry & Exit Pit Preparation | C-PER-1540 | C-4N-H5HG-CNH07-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.5.4.12.3.8.1 HDD @ CH 16+746 - 16+764 (HDD-08) | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 8 | Excavation for Entry & Exit Pit Preparation | C-PER-1550 | C-4N-H5HG-CNH08-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.5.4.12.3.10.1 HDD @ CH 0+236 - 0+389 (HDD-01) | Trial pit, Crossing Methodology, NOC & Permits-4" Water Pipeline-NDRC 1 | Excavation for Entry & Exit Pit Preparation | C-PER-1560 | C-4N-H5HG-CNH1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.5.4.12.3.9.1 HDD @ CH 1+401 - 1+551 (HDD-02) | Trial pit, Crossing Methodology, NOC & Permits-4" Water Pipeline-NDRC 2 | Excavation for Entry & Exit Pit Preparation | C-PER-1570 | C-4N-H5HG-CNH2-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.9.21.1.1 Earthworks, Site Preparation, Site GradingCCOB152C31 | NOC & Permits-BVS06-52" | Site Survey, Preparation & Grading Works | C-PER-1630 | C-52-598-06-CI-1000 | FS | In Progress | Not Started | 27
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | NOC & Permits-BVS05-52" | Site Survey, Preparation & Grading Works | C-PER-1620 | C-52-598-05-CI-1000 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.37 Pipeline Station approach drawing - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Station approach drawing-52" | NOC & Permits-Sweihan CRS | HE-PL-2670 | C-PER-1650 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.1.21.1.1 Earthworks, Site Preparation, Site GradingCCOH52CS30 | NOC & Permits-Sweihan CRS | Site Survey, Preparation & Grading Works | C-PER-1650 | C-52-PL-838-CI-1000 | FS | Not Started | Not Started | 30
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.3.1.2.3.12.1.20 Automatic Welding from BVS-01 to KP 21.3CCOPL56256.1 | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | Automatic Welding | C-COM-1010 | C-56-01HG-PL-ME-3600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.3.1.2.3.12.1.31 Automatic Welding from KP 21.3 to HGCPCCOPL56256.2 | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | Automatic Welding | C-COM-1010 | C-56-01HG-PL-ME-3800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.3.1.3.18.21.1.13 Automatic WeldingCCOPL52448 | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | Automatic Welding | C-COM-1010 | C-52-0506-PL-ME-3600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.3.1.3.17.21.1.12 Automatic WeldingCCOPL52420 | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | Automatic Welding | C-COM-1010 | C-52-0405-PL-ME-3600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.3.1.3.16.21.1.12 Automatic WeldingCCOPL52392 | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | Automatic Welding | C-COM-1010 | C-52-0304-PL-ME-3600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.3.1.3.15.21.1.10 Automatic WeldingCCOPL52364 | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | Automatic Welding | C-COM-1010 | C-52-0203-PL-ME-3600 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.3.1.3.8.21.1.13 Automatic WeldingCCOPL52336 | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | Automatic Welding | C-COM-1010 | C-52-0102-PL-ME-3600 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | Automatic Welding-Lot1 | C-COM-1010 | C-52-HG01-PL-ME-3600 | SS | Completed | Completed | 0
P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | Automatic Welding-Lot2 | C-COM-1010 | C-52-HG01-PL-ME-3800 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.7.23 Piping Tie In Schedule | P2543-R01-Oct24..4.3.1.1.3.10.40.1 Demolition Works (Paving)CCOHBCS300 | Final Issue for Design/ Construction-Piping Tie In Schedule | Demolition of Existing Paving | HE-PI-3520 | C-56-G-HT-CI-0100 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | Receive Company Comments - Overall Pipeline Route Map - 52" | Survey Marking HGCP to BVS-01 | HE-PL-0200 | C-52-HG01-PL-CI-1000 | FS | Completed | Completed | 5
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | Site Mobilization for Construction works( including mobilization Plan for Key Personnel & Construction Equipment) | Survey Marking HGCP to BVS-01 | CTF-1000 | C-52-HG01-PL-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.2.1 Mobilization & TSF | P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | NOC's / Approval /Survey | Survey Marking HGCP to BVS-01 | CTF-1010 | C-52-HG01-PL-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.6 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 1&2)CCOPL52303.1 | P2543-R01-Oct24..4.3.1.3.2.21.1.7 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 1&2) CCOPL52303.2 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-HG01-PL-CI-2000 | C-52-HG01-PL-CI-2200 | FF | Completed | Completed | 20
P2543-R01-Oct24..4.3.1.3.2.21.1.6 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 1&2)CCOPL52303.1 | P2543-R01-Oct24..4.3.1.3.2.21.1.7 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 1&2) CCOPL52303.2 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Compaction - Layer 2 | C-52-HG01-PL-CI-2010 | C-52-HG01-PL-CI-2210 | FF | Completed | Completed | 10
P2543-R01-Oct24..4.3.1.3.2.21.1.9 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 3&4)CCOPL52303.3 | P2543-R01-Oct24..4.3.1.3.2.21.1.12 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 3&4)CCOPL52303.4 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Compaction - Layer 3 | C-52-HG01-PL-CI-2020 | C-52-HG01-PL-CI-2220 | FF | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.2.21.1.12 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 3&4)CCOPL52303.4 | P2543-R01-Oct24..4.3.1.3.2.21.1.9 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 3&4)CCOPL52303.3 | Sabka Gatch Compaction - Layer 3 | Sabka Gatch Laying - Layer 4 | C-52-HG01-PL-CI-2220 | C-52-HG01-PL-CI-2030 | FF | Completed | Completed | 10
P2543-R01-Oct24..4.3.1.3.2.21.1.9 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 3&4)CCOPL52303.3 | P2543-R01-Oct24..4.3.1.3.2.21.1.12 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 3&4)CCOPL52303.4 | Sabka Gatch Laying - Layer 4 | Sabka Gatch Compaction - Layer 4 | C-52-HG01-PL-CI-2030 | C-52-HG01-PL-CI-2230 | FF | Completed | Completed | 10
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.2.21.1.11 Pipe Stringing from HGCP to KP 16.7CCOPL52305.1 | Receipt at site and inspection of Line Pipes - Lot 1 (Coated) | Stringing-Lot1 | HM-PL-0080 | C-52-HG01-PL-ME-2800 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.2.21.1.11 Pipe Stringing from HGCP to KP 16.7CCOPL52305.1 | Receipt at site and inspection of Line Pipes - Lot 2 (Coated) | Stringing-Lot1 | HM-PL-0090 | C-52-HG01-PL-ME-2800 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Lowering-Lot1 | Complete Construction of Anchor Blocks - 52" Sales Gas Pipeline | C-52-HG01-PL-ME-4800 | ML1729-E18 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | Ext. Joint Coating (Tie-in Joint)-Lot1 | Padding -Lot1 | C-52-HG01-PL-ME-4410 | C-52-HG01-PL-CI-6000 | FF | Completed | In Progress | 7
P2543-R01-Oct24..4.3.1.3.2.21.1.11 Pipe Stringing from HGCP to KP 16.7CCOPL52305.1 | P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | Stringing-Lot1 | Automatic Welding-Lot1 | C-52-HG01-PL-ME-2800 | C-52-HG01-PL-ME-3600 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | Automatic Welding-Lot1 | Trench Excavation-Lot1 | C-52-HG01-PL-ME-3600 | C-52-HG01-PL-CI-2400 | FS | Completed | Completed | 15
P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | Trench Excavation-Lot1 | Bedding-Lot1 | C-52-HG01-PL-CI-2400 | C-52-HG01-PL-CI-2410 | FF | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Bedding-Lot1 | Lowering-Lot1 | C-52-HG01-PL-CI-2410 | C-52-HG01-PL-ME-4800 | SS | Completed | Completed | 5
P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Ext. Joint Coating-Lot1 | Lowering-Lot1 | C-52-HG01-PL-ME-4400 | C-52-HG01-PL-ME-4800 | FF | Completed | Completed | 3
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Section Tie-in Welding -Lot1 | NDT (Tie-in Joint)-Lot1 | C-52-HG01-PL-ME-4810 | C-52-HG01-PL-ME-4820 | FF | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Ext. Joint Coating (Tie-in Joint)-Lot1 | Holiday Testing-Lot1 | C-52-HG01-PL-ME-4410 | C-52-HG01-PL-ME-4830 | FF | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | Survey Marking BVS-05 to BVS-06 | Survey Marking BVS-06 to Sweihan CRS | C-52-0506-PL-CI-1000 | C-52-06CR-PL-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | Survey Marking BVS-03 to BVS-04 | Survey Marking BVS-04 to BVS-05 | C-52-0304-PL-CI-1000 | C-52-0405-PL-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.9 Sabkha Pad Gatch layingfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.3 | P2543-R01-Oct24..4.3.1.3.8.21.1.10 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.4 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Compaction - Layer 3 | C-52-0102-PL-CI-2030 | C-52-0102-PL-CI-2220 | FF | Completed | Completed | 3
P2543-R01-Oct24..4.3.1.3.8.21.1.9 Sabkha Pad Gatch layingfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.3 | P2543-R01-Oct24..4.3.1.3.8.21.1.10 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.4 | Sabka Gatch Laying - Layer 4 | Sabka Gatch Compaction - Layer 4 | C-52-0102-PL-CI-2040 | C-52-0102-PL-CI-2230 | FF | Completed | Completed | 3
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.8.21.1.11 Pipe StringingCCOPL52329 | Receipt at site and inspection of Line Pipes - Lot 3 (Coated) | Stringing (BVS-01 to BVS-02) | HM-PL-0100 | C-52-0102-PL-ME-2800 | FF | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.13 Automatic WeldingCCOPL52336 | P2543-R01-Oct24..4.3.1.3.8.21.1.8 Excavation (incl Bedding)CCOPL52343 | Automatic Welding | Trench Excavation | C-52-0102-PL-ME-3600 | C-52-0102-PL-CI-2400 | SS | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Gatch Compaction | Cleaning & Gauging | C-52-0102-PL-CI-6810 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.27 BermingCCOPL52316 | P2543-R01-Oct24..4.3.2.3.10.8.2.1 Evaporation PondCCOPL52319 | Gatch Compaction | Evaporation Pond | C-52-HG01-PL-CI-6810 | C-52-HG01-PL-CI-7200 | FF | In Progress | Not Started | 3
P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | P2543-R01-Oct24..4.3.2.3.6.8.1.1 Evaporation PondCCOPL52347 | Gatch Compaction | Evaporation Pond | C-52-0102-PL-CI-6810 | C-52-0102-PL-CI-7200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.1 Crossing Manual @ KP 56+666 (OX-03) | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Holiday Testing | Installation of Test Post for Crossing | C-52-0102-CMA01-1060 | C-52-0102-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.2 Crossing Manual @ KP 62+000 (OX-04) | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Holiday Testing | Installation of Test Post for Crossing | C-52-0102-CMA02-1060 | C-52-0102-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.14.3 Crossing Manual @ KP 62+194 (OX-05) | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Holiday Testing | Installation of Test Post for Crossing | C-52-0102-CMA03-1060 | C-52-0102-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.1 Crossing Manual @ KP 45+143 to 45+153 (PX-06,PX-07) | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Holiday Testing | Installation of Test Post for Crossing | C-52-0102-CMA04-1060 | C-52-0102-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.15.2 Crossing Manual @ KP 45+201 (PX-08) | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Holiday Testing | Installation of Test Post for Crossing | C-52-0102-CMA05-1060 | C-52-0102-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Holiday Testing | Installation of Test Post for Crossing | C-52-0102-CME01-1060 | C-52-0102-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Holiday Testing | Installation of Test Post for Crossing | C-52-0102-CME02-1060 | C-52-0102-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Holiday Testing | Installation of Test Post for Crossing | C-52-0102-CME03-1060 | C-52-0102-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Holiday Testing | Installation of Test Post for Crossing | C-52-0102-CME04-1060 | C-52-0102-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Holiday Testing | Installation of Test Post for Crossing | C-52-0102-CME05-1060 | C-52-0102-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-0203-PL-CI-2000 | C-52-0203-PL-CI-2200 | FF | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Sabka Gatch Laying - Layer 4 | Sabka Gatch Compaction - Layer 4 | C-52-0203-PL-CI-2030 | C-52-0203-PL-CI-2230 | FF | Completed | Completed | 7
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | Receipt at site and inspection of Line Pipes - Lot 3 (Coated) | Stringing (BVS-02 to BVS-03) | HM-PL-0100 | C-52-0203-PL-ME-2800 | FF | Completed | Completed | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.10 Automatic WeldingCCOPL52364 | P2543-R01-Oct24..4.3.1.3.15.21.1.7 Excavation (incl Bedding)CCOPL52371 | Automatic Welding | Trench Excavation | C-52-0203-PL-ME-3600 | C-52-0203-PL-CI-2400 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.15.21.2.12.5 Re-Instatement of Entry & Exit PitCCOPL57212 | P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | Padding & Back Filling | Padding | C-52-0203-CME04-1070 | C-52-0203-PL-CI-6000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | P2543-R01-Oct24..4.3.2.3.5.8.2.1 Evaporation PondCCOPL52375 | Gatch Compaction | Evaporation Pond | C-52-0203-PL-CI-6810 | C-52-0203-PL-CI-7200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Gatch Compaction | Cleaning & Gauging | C-52-0203-PL-CI-6810 | C-52-0203-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-0304-PL-CI-2000 | C-52-0304-PL-CI-2200 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Compaction - Layer 2 | C-52-0304-PL-CI-2010 | C-52-0304-PL-CI-2210 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Compaction - Layer 3 | C-52-0304-PL-CI-2020 | C-52-0304-PL-CI-2220 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | Sabka Gatch Laying - Layer 4 | Sabka Gatch Compaction - Layer 4 | C-52-0304-PL-CI-2030 | C-52-0304-PL-CI-2230 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.12 Automatic WeldingCCOPL52392 | P2543-R01-Oct24..4.3.1.3.16.21.1.9 Excavation (incl Bedding)CCOPL52399 | Automatic Welding | Trench Excavation | C-52-0304-PL-ME-3600 | C-52-0304-PL-CI-2400 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.16.21.1.9 Excavation (incl Bedding)CCOPL52399 | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Bedding | Lowering | C-52-0304-PL-CI-2410 | C-52-0304-PL-ME-4800 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | Receipt at site and inspection of Line Pipes - Lot 3 (Coated) | Stringing (BVS-03 to BVS-04) | HM-PL-0100 | C-52-0304-PL-ME-2800 | SS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.12 Automatic WeldingCCOPL52392 | P2543-R01-Oct24..4.3.1.3.16.21.1.13 NDT TestCCOPL52407 | Automatic Welding | NDT | C-52-0304-PL-ME-3600 | C-52-0304-PL-ME-4000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.13 NDT TestCCOPL52407 | P2543-R01-Oct24..4.3.1.3.16.21.1.14 Ext. Joint CoatingCCOPL52390 | NDT | Ext. Joint Coating | C-52-0304-PL-ME-4000 | C-52-0304-PL-ME-4400 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.16.21.1.14 Ext. Joint CoatingCCOPL52390 | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Ext. Joint Coating | Lowering | C-52-0304-PL-ME-4400 | C-52-0304-PL-ME-4800 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.16.21.1.9 Excavation (incl Bedding)CCOPL52399 | P2543-R01-Oct24..4.3.1.3.16.21.1.9 Excavation (incl Bedding)CCOPL52399 | Trench Excavation | Bedding | C-52-0304-PL-CI-2400 | C-52-0304-PL-CI-2410 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-PL-ME-4810 | C-52-0304-PL-ME-4820 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | P2543-R01-Oct24..4.3.1.3.16.21.1.14 Ext. Joint CoatingCCOPL52390 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-PL-ME-4820 | C-52-0304-PL-ME-4410 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.14 Ext. Joint CoatingCCOPL52390 | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-PL-ME-4410 | C-52-0304-PL-ME-4830 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Padding | Gatch Laying & Levelling | C-52-0304-PL-CI-6000 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Gatch Laying & Levelling | Gatch Compaction | C-52-0304-PL-CI-6800 | C-52-0304-PL-CI-6810 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Gatch Compaction | Installation of Marker Post/Sign Board | C-52-0304-PL-CI-6810 | C-52-0304-PL-CI-7800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | P2543-R01-Oct24..4.3.2.3.4.8.3.1 Evaporation PondCCOPL52403 | Gatch Compaction | Evaporation Pond | C-52-0304-PL-CI-6810 | C-52-0304-PL-CI-7200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.3.1 Evaporation PondCCOPL52403 | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Evaporation Pond | Cleaning & Gauging | C-52-0304-PL-CI-7200 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Gatch Compaction | Cleaning & Gauging | C-52-0304-PL-CI-6810 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 3 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 14 | C-PER-1040 | C-PER-1160 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 3 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | C-PER-1040 | C-PER-1180 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 4 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13 | C-PER-1050 | C-PER-1140 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 4 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13A | C-PER-1050 | C-PER-1150 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 14 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 28 | C-PER-1160 | C-PER-1310 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 14 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 29 | C-PER-1160 | C-PER-1320 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 14 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 31 | C-PER-1160 | C-PER-1340 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Overall Pipeline Route Map - 56" | Receiving Permits-56" Pipelines & Stations,4" Pipeline | HE-PL-0170 | C-PER-1000 | SS | Completed | Completed | 14
P2543-R01-Oct24..1.EN.1.2 Overall Pipeline Route Map - 4" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Overall Pipeline Route Map - 4" | Receiving Permits-56" Pipelines & Stations,4" Pipeline | HE-PL-0290 | C-PER-1000 | SS | Completed | Completed | 14
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 11 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 9 | C-PER-1450 | C-PER-1430 | SS | Not Started | Not Started | 14
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 5 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 4 | C-PER-1390 | C-PER-1380 | SS | Not Started | Not Started | 14
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 4 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 5 | C-PER-1510 | C-PER-1520 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 4 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 6 | C-PER-1510 | C-PER-1530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 4 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 7 | C-PER-1510 | C-PER-1540 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 4 | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 8 | C-PER-1510 | C-PER-1550 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-4" Water Pipeline-NDRC 1 | Trial pit, Crossing Methodology, NOC & Permits-4" Water Pipeline-NDRC 2 | C-PER-1560 | C-PER-1570 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-0405-PL-CI-2000 | C-52-0405-PL-CI-2200 | FF | In Progress | In Progress | 5
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Compaction - Layer 2 | C-52-0405-PL-CI-2010 | C-52-0405-PL-CI-2210 | FF | In Progress | In Progress | 5
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Compaction - Layer 3 | C-52-0405-PL-CI-2020 | C-52-0405-PL-CI-2220 | FF | In Progress | In Progress | 5
P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | Sabka Gatch Laying - Layer 4 | Sabka Gatch Compaction - Layer 4 | C-52-0405-PL-CI-2030 | C-52-0405-PL-CI-2230 | FF | In Progress | In Progress | 5
P2543-R01-Oct24..4.3.1.3.17.21.1.8 ROW Access RoadCCOPL52412 | P2543-R01-Oct24..4.3.1.3.17.21.1.7 Cut & Fill in Sandy AreaCCOPL52438 | Non-Sabka ROW/Grading | Cut & Fill (@ Non-Sabkha) | C-52-0405-PL-CI-1800 | C-52-0405-PL-CI-1400 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.12 Automatic WeldingCCOPL52420 | P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | Automatic Welding | Trench Excavation | C-52-0405-PL-ME-3600 | C-52-0405-PL-CI-2400 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.17.21.1.12 Automatic WeldingCCOPL52420 | P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | Automatic Welding | Trench Excavation | C-52-0405-PL-ME-3600 | C-52-0405-PL-CI-2400 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.17.21.1.10 Pipe StringingCCOPL52413 | Receipt at site and inspection of Line Pipes - Lot 5 (Coated) | Stringing (BVS-04 to BVS-05) | HM-PL-1460 | C-52-0405-PL-ME-2800 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | P2543-R01-Oct24..4.3.2.3.3.8.3.1 Evaporation PondCCOPL52431 | Gatch Compaction | Evaporation Pond | C-52-0405-PL-CI-6810 | C-52-0405-PL-CI-7200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Gatch Compaction | Cleaning & Gauging | C-52-0405-PL-CI-6810 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.3.1 Evaporation PondCCOPL52431 | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Evaporation Pond | Cleaning & Gauging | C-52-0405-PL-CI-7200 | C-52-0405-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.14 Crossing Manual @ KP 107+081 (FX-37) | Trench Excavation | Trench Excavation | C-52-0405-CME06-1000 | C-52-0405-CMA31-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.13 Automatic WeldingCCOPL52448 | P2543-R01-Oct24..4.3.1.3.18.21.1.9 Excavation (incl Bedding)CCOPL52455 | Automatic Welding | Trench Excavation | C-52-0506-PL-ME-3600 | C-52-0506-PL-CI-2400 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.18.21.1.9 Excavation (incl Bedding)CCOPL52455 | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Bedding | Lowering | C-52-0506-PL-CI-2410 | C-52-0506-PL-ME-4800 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | P2543-R01-Oct24..4.3.2.3.2.8.3.1 Evaporation PondCCOPL52459 | Gatch Compaction | Evaporation Pond | C-52-0506-PL-CI-6810 | C-52-0506-PL-CI-7200 | FF | Not Started | Not Started | 6
P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Gatch Compaction | Cleaning & Gauging | C-52-0506-PL-CI-6810 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Padding | Gatch Laying & Levelling | C-52-0506-PL-CI-6000 | C-52-0506-PL-CI-6800 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.18.21.1.24 BackfillingCCOPL52450 | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Backfilling | Gatch Laying & Levelling | C-52-0506-PL-CI-6400 | C-52-0506-PL-CI-6800 | SS | Not Started | Not Started | 8
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-52-06CR-PL-CI-2000 | C-52-06CR-PL-CI-2200 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Compaction - Layer 2 | C-52-06CR-PL-CI-2010 | C-52-06CR-PL-CI-2210 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Compaction - Layer 3 | C-52-06CR-PL-CI-2020 | C-52-06CR-PL-CI-2220 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | Sabka Gatch Laying - Layer 4 | Sabka Gatch Compaction - Layer 4 | C-52-06CR-PL-CI-2030 | C-52-06CR-PL-CI-2230 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.17 Automatic WeldingCCOPL52476 | P2543-R01-Oct24..4.3.1.3.19.8.1.9 Excavation (incl Bedding)CCOPL52483 | Automatic Welding | Trench Excavation | C-52-06CR-PL-ME-3600 | C-52-06CR-PL-CI-2400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.19.8.1.17 Automatic WeldingCCOPL52476 | P2543-R01-Oct24..4.3.1.3.19.8.1.9 Excavation (incl Bedding)CCOPL52483 | Automatic Welding | Trench Excavation | C-52-06CR-PL-ME-3600 | C-52-06CR-PL-CI-2400 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | P2543-R01-Oct24..4.3.1.3.19.8.1.9 Excavation (incl Bedding)CCOPL52483 | Stringing (BVS-06 to SW CRS) | Trench Excavation | C-52-06CR-PL-ME-2800 | C-52-06CR-PL-CI-2400 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | Lowering | Lowering | C-52-06CR-CMA11-1020 | C-52-06CR-CME04-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.1.13.11 Crossing Manual @ KP 160637.776 to 160642.361 (CX-59,FX-59) | Lowering | Lowering | C-52-06CR-CMA11-1020 | C-52-06CR-CMA10-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | Lowering | Lowering | C-52-06CR-CMA11-1020 | C-52-06CR-CME07-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.9 Excavation (incl Bedding)CCOPL52483 | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Bedding | Lowering | C-52-06CR-PL-CI-2410 | C-52-06CR-PL-ME-4800 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | P2543-R01-Oct24..4.3.2.3.1.8.2.1 Evaporation PondCCOPL52487 | Gatch Compaction | Evaporation Pond | C-52-06CR-PL-CI-6810 | C-52-06CR-PL-CI-7200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Gatch Compaction | Cleaning & Gauging | C-52-06CR-PL-CI-6810 | C-52-06CR-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Padding | FO - Cable Pulling/ Laying | C-52-06CR-PL-CI-6000 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.13 Automatic WeldingCCOPL52336 | P2543-R01-Oct24..4.3.1.3.8.21.1.8 Excavation (incl Bedding)CCOPL52343 | Automatic Welding | Trench Excavation | C-52-0102-PL-ME-3600 | C-52-0102-PL-CI-2400 | FF | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.3.8.21.1.13 Automatic WeldingCCOPL52336 | P2543-R01-Oct24..4.3.1.3.8.21.1.18 NDT TestCCOPL52351 | Automatic Welding | NDT | C-52-0102-PL-ME-3600 | C-52-0102-PL-ME-4000 | FF | In Progress | In Progress | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | P2543-R01-Oct24..4.3.1.3.15.21.1.10 Automatic WeldingCCOPL52364 | Stringing (BVS-02 to BVS-03) | Automatic Welding | C-52-0203-PL-ME-2800 | C-52-0203-PL-ME-3600 | FF | Completed | Not Started | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.10 Automatic WeldingCCOPL52364 | P2543-R01-Oct24..4.3.1.3.15.21.1.7 Excavation (incl Bedding)CCOPL52371 | Automatic Welding | Trench Excavation | C-52-0203-PL-ME-3600 | C-52-0203-PL-CI-2400 | FF | Not Started | Not Started | 17
P2543-R01-Oct24..4.3.1.3.15.21.1.10 Automatic WeldingCCOPL52364 | P2543-R01-Oct24..4.3.1.3.15.21.1.11 NDT TestCCOPL52379 | Automatic Welding | NDT | C-52-0203-PL-ME-3600 | C-52-0203-PL-ME-4000 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.12 Automatic WeldingCCOPL52392 | P2543-R01-Oct24..4.3.1.3.16.21.1.9 Excavation (incl Bedding)CCOPL52399 | Automatic Welding | Trench Excavation | C-52-0304-PL-ME-3600 | C-52-0304-PL-CI-2400 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.18.21.1.13 Automatic WeldingCCOPL52448 | P2543-R01-Oct24..4.3.1.3.18.21.1.9 Excavation (incl Bedding)CCOPL52455 | Automatic Welding | Trench Excavation | C-52-0506-PL-ME-3600 | C-52-0506-PL-CI-2400 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.18.21.1.13 Automatic WeldingCCOPL52448 | P2543-R01-Oct24..4.3.1.3.18.21.1.14 NDT TestCCOPL52463 | Automatic Welding | NDT | C-52-0506-PL-ME-3600 | C-52-0506-PL-ME-4000 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.2.21.1.12 Sabkha Pad Compaction from HGCP to BVS-01 (Layer 3&4)CCOPL52303.4 | P2543-R01-Oct24..4.3.1.3.2.21.1.11 Pipe Stringing from HGCP to KP 16.7CCOPL52305.1 | Sabka Gatch Compaction - Layer 4 | Stringing-Lot1 | C-52-HG01-PL-CI-2230 | C-52-HG01-PL-ME-2800 | FF | Completed | Completed | 3
P2543-R01-Oct24..4.3.1.3.8.21.1.10 Sabkha Pad Compactionfrom BVS-01 to BVS-02 (Layer-3 &4)CCOPL52349.4 | P2543-R01-Oct24..4.3.1.3.8.21.1.11 Pipe StringingCCOPL52329 | Sabka Gatch Compaction - Layer 4 | Stringing (BVS-01 to BVS-02) | C-52-0102-PL-CI-2230 | C-52-0102-PL-ME-2800 | FF | Completed | In Progress | 3
P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | Sabka Gatch Compaction - Layer 4 | Stringing (BVS-03 to BVS-04) | C-52-0304-PL-CI-2230 | C-52-0304-PL-ME-2800 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.18.21.1.6 Cut & Fill in Sandy Area from BVS-05 to KP 126.2CCOPL52466.1 | P2543-R01-Oct24..4.3.1.3.18.21.1.11 Pipe StringingCCOPL52441 | Cut & Fill (@ Non-Sabkha) | Stringing (BVS-05 to BVS-06) | C-52-0506-PL-CI-1400 | C-52-0506-PL-ME-2800 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.18.21.1.8 Cut & Fill in Sandy Area from KP 126.2 to BVS-06CCOPL52466.2 | P2543-R01-Oct24..4.3.1.3.18.21.1.11 Pipe StringingCCOPL52441 | Cut & Fill (@ Non-Sabkha) | Stringing (BVS-05 to BVS-06) | C-52-0506-PL-CI-1600 | C-52-0506-PL-ME-2800 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | Sabka Gatch Compaction - Layer 4 | Stringing (BVS-06 to SW CRS) | C-52-06CR-PL-CI-2230 | C-52-06CR-PL-ME-2800 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | P2543-R01-Oct24..4.3.1.3.15.21.1.7 Excavation (incl Bedding)CCOPL52371 | Stringing (BVS-02 to BVS-03) | Trench Excavation | C-52-0203-PL-ME-2800 | C-52-0203-PL-CI-2400 | FF | Completed | Not Started | 3
P2543-R01-Oct24..4.3.1.3.8.21.1.11 Pipe StringingCCOPL52329 | P2543-R01-Oct24..4.3.1.3.8.21.1.8 Excavation (incl Bedding)CCOPL52343 | Stringing (BVS-01 to BVS-02) | Trench Excavation | C-52-0102-PL-ME-2800 | C-52-0102-PL-CI-2400 | FF | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.3.2.21.1.11 Pipe Stringing from HGCP to KP 16.7CCOPL52305.1 | P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | Stringing-Lot1 | Trench Excavation-Lot1 | C-52-HG01-PL-ME-2800 | C-52-HG01-PL-CI-2400 | FF | Completed | Completed | 3
P2543-R01-Oct24..4.3.1.3.8.21.1.8 Excavation (incl Bedding)CCOPL52343 | P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | Bedding | Lowering | C-52-0102-PL-CI-2410 | C-52-0102-PL-ME-4800 | SS | In Progress | Not Started | 2
P2543-R01-Oct24..4.3.1.3.8.21.1.17 Ext. Joint CoatingCCOPL52334 | P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | Ext. Joint Coating | Lowering | C-52-0102-PL-ME-4400 | C-52-0102-PL-ME-4800 | FF | In Progress | Not Started | 3
P2543-R01-Oct24..4.3.1.3.15.21.1.7 Excavation (incl Bedding)CCOPL52371 | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Bedding | Lowering | C-52-0203-PL-CI-2410 | C-52-0203-PL-ME-4800 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.15.21.1.12 Ext. Joint CoatingCCOPL52362 | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Ext. Joint Coating | Lowering | C-52-0203-PL-ME-4400 | C-52-0203-PL-ME-4800 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Bedding | Lowering | C-52-0405-PL-CI-2410 | C-52-0405-PL-ME-4800 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.19 Ext. Joint CoatingCCOPL52474 | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Ext. Joint Coating | Lowering | C-52-06CR-PL-ME-4400 | C-52-06CR-PL-ME-4800 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | P2543-R01-Oct24..4.3.1.3.18.21.1.12 Cold BendsCCOPL52447 | Lowering | Cold Bends | C-52-0506-PL-ME-4800 | C-52-0506-PL-ME-3200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Lowering | Section Tie-in Welding | C-52-0506-PL-ME-4800 | C-52-0506-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | P2543-R01-Oct24..4.3.1.3.17.21.1.11 Cold BendsCCOPL52419 | Lowering | Cold Bends | C-52-0405-PL-ME-4800 | C-52-0405-PL-ME-3200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | P2543-R01-Oct24..4.3.1.3.16.21.1.11 Cold BendsCCOPL52391 | Lowering | Cold Bends | C-52-0304-PL-ME-4800 | C-52-0304-PL-ME-3200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Lowering | Section Tie-in Welding | C-52-0304-PL-ME-4800 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | P2543-R01-Oct24..4.3.1.3.15.21.1.9 Cold BendsCCOPL52363 | Lowering | Cold Bends | C-52-0203-PL-ME-4800 | C-52-0203-PL-ME-3200 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Lowering | Section Tie-in Welding | C-52-0203-PL-ME-4800 | C-52-0203-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | Lowering | Section Tie-in Welding | C-52-0102-PL-ME-4800 | C-52-0102-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.29 Test Stations & Anode BedsCCOP52EL31 | Lowering-Lot1 | Installation of Temp. Anode | C-52-HG01-PL-ME-4800 | C-52-HG01-PL-CA-5600 | FF | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Lowering-Lot1 | Section Tie-in Welding -Lot1 | C-52-HG01-PL-ME-4800 | C-52-HG01-PL-ME-4810 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | P2543-R01-Oct24..4.3.1.3.8.21.1.24 Test Stations & Anode BedsCCOP52EL34 | Lowering | Installation of Temp. Anode | C-52-0102-PL-ME-4800 | C-52-0102-PL-CA-5600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.16 NDT TestCCOPL52309 | P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | NDT-Lot1 | Ext. Joint Coating-Lot1 | C-52-HG01-PL-ME-4000 | C-52-HG01-PL-ME-4400 | FF | Completed | Completed | 2
P2543-R01-Oct24..4.3.1.3.8.21.1.18 NDT TestCCOPL52351 | P2543-R01-Oct24..4.3.1.3.8.21.1.17 Ext. Joint CoatingCCOPL52334 | NDT | Ext. Joint Coating | C-52-0102-PL-ME-4000 | C-52-0102-PL-ME-4400 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.11 NDT TestCCOPL52379 | P2543-R01-Oct24..4.3.1.3.15.21.1.12 Ext. Joint CoatingCCOPL52362 | NDT | Ext. Joint Coating | C-52-0203-PL-ME-4000 | C-52-0203-PL-ME-4400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Automatic Welding-Lot1 | Section Tie-in Welding -Lot1 | C-52-HG01-PL-ME-3600 | C-52-HG01-PL-ME-4810 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Automatic Welding-Lot1 | Section Tie-in Welding -Lot1 | C-52-HG01-PL-ME-3600 | C-52-HG01-PL-ME-4810 | SS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0102-PL-ME-4810 | C-52-0102-PL-ME-4820 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0203-PL-ME-4810 | C-52-0203-PL-ME-4820 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-PL-ME-4810 | C-52-0506-PL-ME-4820 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-PL-ME-4810 | C-52-06CR-PL-ME-4820 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | P2543-R01-Oct24..4.3.1.3.8.21.1.17 Ext. Joint CoatingCCOPL52334 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0102-PL-ME-4820 | C-52-0102-PL-ME-4410 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | P2543-R01-Oct24..4.3.1.3.15.21.1.12 Ext. Joint CoatingCCOPL52362 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0203-PL-ME-4820 | C-52-0203-PL-ME-4410 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | P2543-R01-Oct24..4.3.1.3.18.21.1.15 Ext. Joint CoatingCCOPL52446 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-PL-ME-4820 | C-52-0506-PL-ME-4410 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | P2543-R01-Oct24..4.3.1.3.19.8.1.19 Ext. Joint CoatingCCOPL52474 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-PL-ME-4820 | C-52-06CR-PL-ME-4410 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.15.5 Crossing Manual @ KP 100+858 (OX-09) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.8 Crossing Manual @ KP 103+960 to 103+972 (CX-30A,31,32,X1,X2) | Trench Excavation | Excavation (Manual-Trial Pit) | C-52-0405-CMA21-1000 | C-52-0405-CMA02-0970 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.12 Crossing Manual @ KP 104+570 (FX-32) | Trench Excavation | Sabkha Gatch Laying | C-52-0405-CMA27-1000 | C-52-0405-CMA30-0980 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.6 Crossing Manual @ KP 155+502 (OX-15) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.1 Crossing Manual @ KP 140+403 (OX-14) | Trench Excavation | Trench Excavation | C-52-06CR-CMA12-1000 | C-52-06CR-CMA11-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.26 Test Stations & Anode BedsCCOP52EL45 | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Installation of Temp. Anode | Padding | C-52-0506-PL-CA-5600 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.26 Test Stations & Anode BedsCCOP52EL45 | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Installation of Temp. Anode | Padding | C-52-0506-PL-CA-5600 | C-52-0506-PL-CI-6000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.26 Test Stations & Anode BedsCCOP52EL48 | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Installation of Temp. Anode | Padding | C-52-06CR-PL-CA-5600 | C-52-06CR-PL-CI-6000 | SS | Not Started | Not Started | 11
P2543-R01-Oct24..4.3.1.3.19.8.1.26 Test Stations & Anode BedsCCOP52EL48 | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Installation of Temp. Anode | Padding | C-52-06CR-PL-CA-5600 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 11
P2543-R01-Oct24..4.3.1.3.17.21.1.26 Test Stations & Anode BedsCCOP52EL42 | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Installation of Temp. Anode | Padding | C-52-0405-PL-CA-5600 | C-52-0405-PL-CI-6000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.26 Test Stations & Anode BedsCCOP52EL42 | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Installation of Temp. Anode | Padding | C-52-0405-PL-CA-5600 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.23 Test Stations & Anode BedsCCOP52EL39 | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Installation of Temp. Anode | Padding | C-52-0304-PL-CA-5600 | C-52-0304-PL-CI-6000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.23 Test Stations & Anode BedsCCOP52EL39 | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Installation of Temp. Anode | Padding | C-52-0304-PL-CA-5600 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.20 Test Stations & Anode BedsCCOP52EL36 | P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | Installation of Temp. Anode | Padding | C-52-0203-PL-CA-5600 | C-52-0203-PL-CI-6000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.20 Test Stations & Anode BedsCCOP52EL36 | P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | Installation of Temp. Anode | Padding | C-52-0203-PL-CA-5600 | C-52-0203-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.24 Test Stations & Anode BedsCCOP52EL34 | P2543-R01-Oct24..4.3.1.3.8.21.1.22 PaddingCCOPL52330 | Installation of Temp. Anode | Padding | C-52-0102-PL-CA-5600 | C-52-0102-PL-CI-6000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.24 Test Stations & Anode BedsCCOP52EL34 | P2543-R01-Oct24..4.3.1.3.8.21.1.22 PaddingCCOPL52330 | Installation of Temp. Anode | Padding | C-52-0102-PL-CA-5600 | C-52-0102-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.24 BackfillingCCOPL52478 | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Backfilling | Gatch Laying & Levelling | C-52-06CR-PL-CI-6400 | C-52-06CR-PL-CI-6800 | SS | Not Started | Not Started | 22
P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Gatch Laying & Levelling | Gatch Compaction | C-52-06CR-PL-CI-6800 | C-52-06CR-PL-CI-6810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.23 BackfillingCCOPL52422 | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Backfilling | Gatch Laying & Levelling | C-52-0405-PL-CI-6400 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | Padding | Gatch Laying & Levelling | C-52-0203-PL-CI-6000 | C-52-0203-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | Gatch Laying & Levelling | Gatch Compaction | C-52-0203-PL-CI-6800 | C-52-0203-PL-CI-6810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.22 PaddingCCOPL52330 | P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | Padding | Gatch Laying & Levelling | C-52-0102-PL-CI-6000 | C-52-0102-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | Gatch Laying & Levelling | Gatch Compaction | C-52-0102-PL-CI-6800 | C-52-0102-PL-CI-6810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.27 BermingCCOPL52316 | P2543-R01-Oct24..4.3.1.3.2.21.1.27 BermingCCOPL52316 | Gatch Laying & Levelling | Gatch Compaction | C-52-HG01-PL-CI-6800 | C-52-HG01-PL-CI-6810 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.9 Excavation (incl Bedding)CCOPL52483 | P2543-R01-Oct24..4.3.1.3.19.8.1.9 Excavation (incl Bedding)CCOPL52483 | Trench Excavation | Bedding | C-52-06CR-PL-CI-2400 | C-52-06CR-PL-CI-2410 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | P2543-R01-Oct24..4.3.1.2.3.12.1.7 Surveying from BVS-01 to KP 21.3CCOPL56247.1 | Final Issue for Design/ Construction-Overall Pipeline Route Map - 56" | Survey Marking | HE-PL-0170 | C-56-01HG-PL-CI-1000 | SS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | Sabka Gatch Laying (Including ROW) - Layer 1 | Sabka Gatch Compaction (Including ROW) - Layer 1 | C-56-01HG-PL-CI-2000 | C-56-01HG-PL-CI-2200 | FF | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | Sabka Gatch Laying - Layer 2 | Sabka Gatch Compaction - Layer 2 | C-56-01HG-PL-CI-2010 | C-56-01HG-PL-CI-2210 | FF | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | Sabka Gatch Laying - Layer 3 | Sabka Gatch Compaction - Layer 3 | C-56-01HG-PL-CI-2020 | C-56-01HG-PL-CI-2220 | FF | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.14 Sabkha Pad- Gatch CompactionCCOPL56241.3 | Sabka Gatch Laying - Layer 4 | Sabka Gatch Compaction - Layer 4 | C-56-01HG-PL-CI-2030 | C-56-01HG-PL-CI-2230 | FF | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.15 Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.15 Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 | Trench Excavation | Bedding | C-56-01HG-PL-CI-2400 | C-56-01HG-PL-CI-2410 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.24 Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.24 Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 | Trench Excavation | Bedding | C-56-01HG-PL-CI-2600 | C-56-01HG-PL-CI-2610 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.26 Test Stations & Anode Beds from BVS-01 to KP 21.3CCOP56EL24.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | Installation of Temp. Anode | Padding | C-56-01HG-PL-CA-5600 | C-56-01HG-PL-CI-6000 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.3.12.1.26 Test Stations & Anode Beds from BVS-01 to KP 21.3CCOP56EL24.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | Installation of Temp. Anode | Padding | C-56-01HG-PL-CA-5600 | C-56-01HG-PL-CI-6000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.3.12.1.46 Test Stations & Anode Beds from KP 21.3 to HGCPCCOP56EL24.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.41 Padding from KP 21.3 to HGCPCCOPL56251.2 | Installation of Temp. Anode | Padding | C-56-01HG-PL-CA-5800 | C-56-01HG-PL-CI-6200 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.46 Test Stations & Anode Beds from KP 21.3 to HGCPCCOP56EL24.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.41 Padding from KP 21.3 to HGCPCCOPL56251.2 | Installation of Temp. Anode | Padding | C-56-01HG-PL-CA-5800 | C-56-01HG-PL-CI-6200 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.30 Padding from BVS-01 to KP 21.3CCOPL56251.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.33 Backfilling from BVS-01 to KP 21.3CCOPL56231.1 | Padding | Backfilling from BVS-01 to KP 21.3 | C-56-01HG-PL-CI-6000 | C-56-01HG-PL-CI-6400 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.33 Backfilling from BVS-01 to KP 21.3CCOPL56231.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Backfilling from BVS-01 to KP 21.3 | Gatch Laying & Levelling | C-56-01HG-PL-CI-6400 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.43 Backfilling from KP 21.3 to HGCPCCOPL56231.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Backfilling from KP 21.3 to HGCP | Gatch Laying & Levelling | C-56-01HG-PL-CI-6600 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | P2543-R01-Oct24..4.3.2.2.2.3.1.1 Evaporation PondCCOPL56239 | Gatch Compaction | Evaporation Pond | C-56-01HG-PL-CI-7010 | C-56-01HG-PL-CI-7200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Gatch Compaction | Cleaning & Gauging | C-56-01HG-PL-CI-6810 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.8 Cut & FillCCOPL56201 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.14 Excavation (incl Bedding) from KP 6 to KP 12.6CCOPL56206.2 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-56-HC01-PL-CI-1400 | C-56-HC01-PL-CI-2600 | SS | In Progress | Not Started | 3
P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | P2543-R01-Oct24..4.3.2.2.2.3.1.5 Evaporation PondCCOPL56225 | Gatch Compaction | Evaporation Pond | C-56-HC01-PL-CI-7010 | C-56-HC01-PL-CI-7200 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Gatch Compaction | Cleaning & Gauging | C-56-HC01-PL-CI-7010 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.5 Evaporation PondCCOPL56225 | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Evaporation Pond | Cleaning & Gauging | C-56-HC01-PL-CI-7200 | C-56-HC01-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.33 Test Stations & Anode Beds from Habshan complex to KP 6CCOP56EL22.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.20 Padding from Habshan complex to KP 6CCOPL56211.1 | Installation of Temp. Anode | Padding | C-56-HC01-PL-CA-5600 | C-56-HC01-PL-CI-6000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.33 Test Stations & Anode Beds from Habshan complex to KP 6CCOP56EL22.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.20 Padding from Habshan complex to KP 6CCOPL56211.1 | Installation of Temp. Anode | Padding | C-56-HC01-PL-CA-5600 | C-56-HC01-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.38 Test Stations & Anode Beds from KP 6 to KP 12.6CCOP56EL22.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 Padding from KP 6 to KP 12.6CCOPL56211.2 | Installation of Temp. Anode | Padding | C-56-HC01-PL-CA-5800 | C-56-HC01-PL-CI-6200 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.38 Test Stations & Anode Beds from KP 6 to KP 12.6CCOP56EL22.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 Padding from KP 6 to KP 12.6CCOPL56211.2 | Installation of Temp. Anode | Padding | C-56-HC01-PL-CA-5800 | C-56-HC01-PL-CI-6200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 Padding from KP 6 to KP 12.6CCOPL56211.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.35 Backfilling from KP 6 to KP 12.6CCOPL56217.2 | Padding | Backfilling from KP 6 to KP 12.6 | C-56-HC01-PL-CI-6200 | C-56-HC01-PL-CI-6600 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.9 Cut & Fill from BVS-01 to KP 21.3CCOPL56248.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.15 Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-56-01HG-PL-CI-1400 | C-56-01HG-PL-CI-2400 | SS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.9 Cut & Fill from BVS-01 to KP 21.3CCOPL56248.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.24 Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-56-01HG-PL-CI-1400 | C-56-01HG-PL-CI-2600 | SS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.9 Cut & Fill from BVS-01 to KP 21.3CCOPL56248.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.24 Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-56-01HG-PL-CI-1400 | C-56-01HG-PL-CI-2600 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.9 Cut & Fill from BVS-01 to KP 21.3CCOPL56248.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.15 Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-56-01HG-PL-CI-1400 | C-56-01HG-PL-CI-2400 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.12 Cut & Fill from KP 21.3 to HGCPCCOPL56248.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.15 Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-56-01HG-PL-CI-1600 | C-56-01HG-PL-CI-2400 | FF | Completed | Not Started | 5
P2543-R01-Oct24..4.3.1.2.3.12.1.12 Cut & Fill from KP 21.3 to HGCPCCOPL56248.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.24 Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 | Cut & Fill (@ Non-Sabkha) | Trench Excavation | C-56-01HG-PL-CI-1600 | C-56-01HG-PL-CI-2600 | SS | Completed | Not Started | 5
P2543-R01-Oct24..4.3.1.2.3.12.1.16 Pipe Stringing from BVS-01 to KP 21.3CCOPL56250.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.18.1 Crossing Manual @ KP 13+317 to 14+198 (PX-119 to PX-130) | Stringing (BVS-01 to KP 21.3) | Trench Excavation | C-56-01HG-PL-ME-2800 | C-56-01HG-CMA01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | Trench Excavation | Trench Excavation | C-56-HC01-CMA01-1000 | C-56-HC01-CMA06-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.29 Crossing Manual @ KP 0+734 to KP 1+156 (CX-08,09) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | Trench Excavation | Trench Excavation | C-56-HC01-CMA06-1000 | C-56-HC01-CMA05-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.27 Crossing Manual @ KP 2+913 (CX-10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | Trench Excavation | Trench Excavation | C-56-HC01-CMA05-1000 | C-56-HC01-CMA07-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | Trench Excavation | Trench Excavation | C-56-HC01-CMA07-1000 | C-56-HC01-CMA04-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.9 Crossing Manual @ KP 8+810 to 8+908 (CX-12,13,14,15,16) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | Trench Excavation | Trench Excavation | C-56-HC01-CMA04-1000 | C-56-HC01-CMA02-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.1 Crossing Manual @ KP 10+050 (CX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.2 Crossing Manual @ KP 11+183 (CX-18) | Trench Excavation | Trench Excavation | C-56-HC01-CMA02-1000 | C-56-HC01-CMA03-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | Trench Excavation | Trench Excavation | C-56-HC01-CMA08-1000 | C-56-HC01-CMA12-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | Trench Excavation | Trench Excavation | C-56-HC01-CMA12-1000 | C-56-HC01-CMA10-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.7 Crossing Manual @ KP 1+104 to 1+226 (PX-19 to PX-24) | Trench Excavation | Trench Excavation | C-56-HC01-CMA10-1000 | C-56-HC01-CMA15-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | Trench Excavation | Trench Excavation | C-56-HC01-CMA14-1000 | C-56-HC01-CMA11-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.5 Crossing Manual @ KP 1+796 to 2+973 (PX-31 to PX-36) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | Trench Excavation | Trench Excavation | C-56-HC01-CMA11-1000 | C-56-HC01-CMA09-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.4 Crossing Manual @ KP 2+989 to 3+468 (PX-37 to PX-42) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.3 Crossing Manual @ KP 3+470 to 5+930 (PX-43 to PX-49) | Trench Excavation | Trench Excavation | C-56-HC01-CMA09-1000 | C-56-HC01-CMA13-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | Trench Excavation | Trench Excavation | C-56-HC01-CMA16-1000 | C-56-HC01-CMA17-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.20 Crossing Manual @ KP 6+989 to 8+754 (PX-60 to PX-70) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | Trench Excavation | Trench Excavation | C-56-HC01-CMA17-1000 | C-56-HC01-CMA18-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.11 Crossing Manual @ KP 8+769 to 9+565 (PX-71 to PX-77) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.21 Crossing Manual @ KP 9+913 to 11+199 (PX-78 to PX-86) | Trench Excavation | Trench Excavation | C-56-HC01-CMA18-1000 | C-56-HC01-CMA19-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | Trench Excavation | Trench Excavation | C-56-HC01-CMA20-1000 | C-56-HC01-CMA21-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.22 Crossing Manual @ KP 11+491 to 11+504 (PX-96 to PX-104) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | Trench Excavation | Trench Excavation | C-56-HC01-CMA21-1000 | C-56-HC01-CMA22-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.8 Crossing Manual @ KP 11+506 to 11+533 (PX-105 to PX-113) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.13 Crossing Manual @ KP 11+534 to 12+079 (PX-114 to PX-118) | Trench Excavation | Trench Excavation | C-56-HC01-CMA22-1000 | C-56-HC01-CMA23-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | Trench Excavation | Trench Excavation | C-56-HC01-CMA24-1000 | C-56-HC01-CMA25-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.18 Crossing Manual @ KP 7+488 (PX-68) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.19 Crossing Manual @ KP 6+992 (PX-62) | Trench Excavation | Trench Excavation | C-56-HC01-CMA25-1000 | C-56-HC01-CMA26-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | Trench Excavation | Trench Excavation | C-56-HC01-CMA27-1000 | C-56-HC01-CMA28-1000 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.14 Crossing Manual @ KP 8+917 (FX-02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.15 Crossing Manual @ KP 8+829, KP8+888 (Culvert) | Trench Excavation | Trench Excavation | C-56-HC01-CMA28-1000 | C-56-HC01-CMA29-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.26 Crossing Manual @ KP 1+789 to 8+968 (OX-04 to OX-06) | Trench Excavation | Trench Excavation | C-56-HC01-CMA30-1000 | C-56-HC01-CMA31-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.30 Crossing Manual @ KP 0+246 to 0+664 (CX-01,02,03,04,05,06,07) | Stringing (BVS-01 to HBCMPLX) | Trench Excavation | C-56-HC01-PL-ME-2800 | C-56-HC01-CMA01-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | Stringing (BVS-01 to HBCMPLX) | Trench Excavation | C-56-HC01-PL-ME-2800 | C-56-HC01-CMA08-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.10 Crossing Manual @ KP 6+768 to 6+985 (PX-50 to PX-59) | Stringing (BVS-01 to HBCMPLX) | Trench Excavation | C-56-HC01-PL-ME-2800 | C-56-HC01-CMA16-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | Stringing (BVS-01 to HBCMPLX) | Trench Excavation | C-56-HC01-PL-ME-2800 | C-56-HC01-CME01-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.29.17 Crossing Manual @ KP 7+860 (PX-69) | Stringing (BVS-01 to HBCMPLX) | Trench Excavation | C-56-HC01-PL-ME-2800 | C-56-HC01-CMA24-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.30.16 Crossing Manual @ KP 8+800 (FX-01) | Stringing (BVS-01 to HBCMPLX) | Trench Excavation | C-56-HC01-PL-ME-2800 | C-56-HC01-CMA27-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.31.23 Crossing Manual @ KP 0+220 to 1+749 (OX-01 to OX-03) | Stringing (BVS-01 to HBCMPLX) | Trench Excavation | C-56-HC01-PL-ME-2800 | C-56-HC01-CMA30-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.15.31 Crossing Manual @ KP 6+074 (CX-11) | Lowering | Section Tie-in Welding | C-56-HC01-CMA07-1020 | C-56-HC01-CMA07-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | Lowering | Section Tie-in Welding | C-56-HC01-CMA10-1020 | C-56-HC01-CMA10-1030 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.10 ROW Access RoadCCOPL56249 | P2543-R01-Oct24..4.3.1.2.3.12.1.9 Cut & Fill from BVS-01 to KP 21.3CCOPL56248.1 | Non-Sabka ROW/Grading | Cut & Fill (@ Non-Sabkha) | C-56-01HG-PL-CI-1800 | C-56-01HG-PL-CI-1400 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.20 Automatic Welding from BVS-01 to KP 21.3CCOPL56256.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.15 Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 | Automatic Welding | Trench Excavation | C-56-01HG-PL-ME-3600 | C-56-01HG-PL-CI-2400 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.18.2 Crossing Manual @ KP 14+204 to 18+923 (PX-131 to PX-145) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | Trench Excavation | Trench Excavation | C-56-01HG-CMA02-1000 | C-56-01HG-CMA03-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.3 Crossing Manual @ KP 20+228 to 20+351 (PX-161 to PX-175) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | Trench Excavation | Trench Excavation | C-56-01HG-CMA03-1000 | C-56-01HG-CMA04-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.18.4 Crossing Manual @ KP 20+355 to 21+142 (PX-176 to PX-187) | P2543-R01-Oct24..4.3.1.2.3.12.1.18.5 Crossing Manual @ KP 18+928 to 20+227 (PX-146 to PX-160) | Trench Excavation | Trench Excavation | C-56-01HG-CMA04-1000 | C-56-01HG-CMA05-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.20 Automatic Welding from BVS-01 to KP 21.3CCOPL56256.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.15 Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 | Automatic Welding | Trench Excavation | C-56-01HG-PL-ME-3600 | C-56-01HG-PL-CI-2400 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.31 Automatic Welding from KP 21.3 to HGCPCCOPL56256.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.24 Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 | Automatic Welding | Trench Excavation | C-56-01HG-PL-ME-3800 | C-56-01HG-PL-CI-2600 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.3.12.1.31 Automatic Welding from KP 21.3 to HGCPCCOPL56256.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.24 Excavation (incl Bedding) from KP 21.3 to HGCPCCOPL56236.2 | Automatic Welding | Trench Excavation | C-56-01HG-PL-ME-3800 | C-56-01HG-PL-CI-2600 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.3.12.3.1 Telecommunication Works from BVS-01 to CCOP56IC21.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Termination/Splicing @ BVS | Gatch Compaction | C-56-01HG-PL-TE-8210 | C-56-01HG-PL-CI-7010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.17.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52914 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 23 | Sheet Piling for Driving & Receiving Pit | C-PER-1250 | C-52-0405-CNM23-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1.1 Evaporation PondCCOPL56239 | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Evaporation Pond | Cleaning & Gauging | C-56-01HG-PL-CI-7200 | C-56-01HG-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Issue ICR - Pipeline Alignment Sheets -56" | Mobilization of Job Performers-56" Pipelines & Stations,4" Pipeline | HE-PL-2390 | C-PER-0915 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.10 ROW Access RoadCCOPL56249 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.9 ROW Access RoadCCOPL56203 | Non-Sabka ROW/Grading | Non-Sabka ROW/Grading | C-56-01HG-PL-CI-1800 | C-56-HC01-PL-CI-1800 | FS | Completed | In Progress | 14
P2543-R01-Oct24..4.3.1.2.3.12.1.12 Cut & Fill from KP 21.3 to HGCPCCOPL56248.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.8 Cut & FillCCOPL56201 | Cut & Fill (@ Non-Sabkha) | Cut & Fill (@ Non-Sabkha) | C-56-01HG-PL-CI-1600 | C-56-HC01-PL-CI-1400 | FF | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.9 ROW Access RoadCCOPL56203 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.10 Excavation (incl Bedding) from Habshan complex to KP 6CCOPL56206.1 | Non-Sabka ROW/Grading | Trench Excavation | C-56-HC01-PL-CI-1800 | C-56-HC01-PL-CI-2400 | SS | In Progress | Not Started | 7
P2543-R01-Oct24..4.3.1.2.2.12.4.1.16 Automatic WeldingCCOPL56207 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.10 Excavation (incl Bedding) from Habshan complex to KP 6CCOPL56206.1 | Automatic Welding | Trench Excavation | C-56-HC01-PL-ME-3600 | C-56-HC01-PL-CI-2400 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | Receipt at site and inspection of Line Pipes - Lot 5 (Coated) | Stringing (BVS-01 to HBCMPLX) | HM-PL-1460 | C-56-HC01-PL-ME-2800 | FF | Not Started | Not Started | 21
P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.21 Backfilling from Habshan complex to KP 6CCOPL56217.1 | FO - Cable Pulling/ Laying | Backfilling from Habshan complex to KP 6 | C-56-HC01-PL-TE-8200 | C-56-HC01-PL-CI-6400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.35 Backfilling from KP 6 to KP 12.6CCOPL56217.2 | FO - Cable Pulling/ Laying | Backfilling from KP 6 to KP 12.6 | C-56-HC01-PL-TE-8400 | C-56-HC01-PL-CI-6600 | FF | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.2.2.12.4.1.35 Backfilling from KP 6 to KP 12.6CCOPL56217.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Backfilling from KP 6 to KP 12.6 | Gatch Laying & Levelling | C-56-HC01-PL-CI-6600 | C-56-HC01-PL-CI-7000 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Gatch Compaction | Cleaning & Gauging | C-56-HC01-PL-CI-6810 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | P2543-R01-Oct24..ML Milestones | Installation of Crash Barriers (If any) | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | C-56-HC01-PL-CI-7810 | ML1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | P2543-R01-Oct24..ML Milestones | Installation of Crash Barriers (If any) | Achieve Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | C-56-HC01-PL-CI-8010 | ML1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | P2543-R01-Oct24..4.3.1.2.1.12.6.3 Solar Power System CCOB156E44 | Concrete Works for Access Platform & Misc. Structural Foundations | Installation of Solar Panel Structural Supports | C-56-591-01-CI-1420 | C-56-591-01-EI-1210 | FS | Not Started | Not Started | 88
P2543-R01-Oct24..1.EN.8.11 Civil UG layout | P2543-R01-Oct24..4.3.1.2.1.12.1.9 Earthworks, Site Preparation, Site Grading CCOB156C10 | Final Issue for Design/ Construction-Civil UG layout | Site Survey, Preparation & Grading Works | HE-CS-0530 | C-56-591-01-CI-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.17 Precasting for fence posts from BVS-02 to BVS-03CCOP52CS52.5 | P2543-R01-Oct24..4.3.1.3.5.21.1.21 Precasting for fence posts from BVS-01 to BVS-02CCOP52CS52.6 | Pre-Casting of Fence Foundation (BVS-02 to BVS-03) | Pre-Casting of Fence Foundation (BVS-02 to BVS-01) | C-52-0203-FENCE-1000 | C-52-0102-FENCE-1000 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.21 Precasting for fence posts from BVS-01 to BVS-02CCOP52CS52.6 | P2543-R01-Oct24..4.3.1.3.5.21.1.16 Precasting for fence posts from BVS-03 to BVS-04CCOP52CS52.4 | Pre-Casting of Fence Foundation (BVS-02 to BVS-01) | Pre-Casting of Fence Foundation (BVS-03 to BVS-04) | C-52-0102-FENCE-1000 | C-52-0304-FENCE-1000 | SS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.4.1 Piping Pre-FabricationCCOB652P052 | P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | Piping Pre-Fabrication | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | C-52-598-01-PI-1000 | C-52-598-01-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.4.1 Piping Pre-FabricationCCOB552P051 | P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | Piping Pre-Fabrication | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | C-52-598-02-PI-1000 | C-52-598-02-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.4.1 Piping Pre-FabricationCCOB452P051 | P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | Piping Pre-Fabrication | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | C-52-598-03-PI-1000 | C-52-598-03-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.4.1 Piping Pre-FabricationCCOB252P050 | P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | Piping Pre-Fabrication | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | C-52-598-05-PI-1000 | C-52-598-05-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | Site Survey, Preparation & Grading Works | Earth Works for Thrust Anchor Block | C-52-PR-839-CI-1000 | C-52-PR-839-CI-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.5 Trenching for CablesCCOB152C38 | P2543-R01-Oct24..4.3.1.3.9.21.1.5 Trenching for CablesCCOB152C38 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-52-598-06-CI-1800 | C-52-598-06-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.4.1 Piping Pre-FabricationCCOB552P051 | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Piping Pre-Fabrication | Piping Erection | C-52-598-02-PI-1000 | C-52-598-02-PI-1200 | SS | Not Started | Not Started | 10
P2543-R01-Oct24..4.3.1.3.13.21.4.1 Piping Pre-FabricationCCOB552P051 | P2543-R01-Oct24..4.3.1.3.13.21.4.2 ErectionCCOB552P061 | Piping Pre-Fabrication | Piping Erection | C-52-598-02-PI-1000 | C-52-598-02-PI-1200 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.12.21.1.5 Pipe Supports Fabrication & InstallationCCOB452S51 | P2543-R01-Oct24..4.3.1.3.12.21.4.1 Piping Pre-FabricationCCOB452P051 | Pre-Fabrication & Installation of Pipe Supports | Piping Pre-Fabrication | C-52-598-03-CI-2000 | C-52-598-03-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.1.6 Pipe Supports Fabrication & InstallationCCOB152S52 | P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | Pre-Fabrication & Installation of Pipe Supports | Piping Pre-Fabrication | C-52-598-06-CI-2000 | C-52-598-06-PI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.4.1 Piping Pre-FabricationCCOB152P050 | P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | Piping Pre-Fabrication | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | C-52-598-06-PI-1000 | C-52-598-06-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | P2543-R01-Oct24..4.3.1.3.4.5.22.1 Earth WorksCCOSW52E112 | Site Survey, Preparation & Grading Works | Site Survey, Preparation & Grading Works | C-52-PR-839-CI-1000 | C-52-ADDC-CI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.5.4.12.1.6 SurveyingCCOPL4"100 | Receiving Permits-56" Pipelines & Stations,4" Pipeline | Survey Marking | C-PER-1000 | C-4N-H5HG-PIPEL-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.8 ROW Access RoadCCOPL4"102 | P2543-R01-Oct24..4.3.1.5.4.12.1.7 Cut & FillCCOPL4"101 | Sabka ROW/Grading | Cut & Fill (@ Non-Sabkha) | C-4N-H5HG-PIPEL-1800 | C-4N-H5HG-PIPEL-1400 | FS | In Progress | Not Started | 5
P2543-R01-Oct24..4.3.1.5.4.12.1.9 Pipe StringingCCOPL4"104 | P2543-R01-Oct24..4.3.1.5.4.12.1.24.1 Crossing Manual @ KP 0+114 to 0+141 (CX-01,02) | Stringing (HB-5 to HGCP) | Trench Excavation | C-4N-H5HG-PIPEL-2800 | C-4N-H5HG-CMA13-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.19 Test Stations & Anode BedsCCOP4"EL12 | P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | Installation of Temp. Anode | Padding | C-4N-H5HG-PIPEL-5600 | C-4N-H5HG-PIPEL-6000 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.5.4.12.1.19 Test Stations & Anode BedsCCOP4"EL12 | P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | Installation of Temp. Anode | Padding | C-4N-H5HG-PIPEL-5600 | C-4N-H5HG-PIPEL-6000 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.1.17 BackfillingCCOPL4"115 | Padding | Backfilling | C-4N-H5HG-PIPEL-6000 | C-4N-H5HG-PIPEL-6400 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | P2543-R01-Oct24..4.3.1.5.4.12.1.31 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL4"123 | Gatch Compaction | Cleaning & Gauging | C-4N-H5HG-PIPEL-6810 | C-4N-H5HG-PIPEL-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-PIPEL-6000 | C-4N-H5HG-PIPEL-8200 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.2.1 Telecommunication Works along Pipeline from Habshan 5 CCOPL4"114.1 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-PIPEL-6000 | C-4N-H5HG-PIPEL-8200 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-PIPEL-6000 | C-4N-H5HG-PIPEL-8400 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | Padding | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | C-4N-H5HG-PIPEL-6000 | C-4N-H5HG-PIPEL-8400 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.17 BackfillingCCOPL4"115 | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | Backfilling | C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-6400 | SS | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.5.4.12.2.2 Telecommunication Works along Pipeline from KP-12 to HCCOPL4"114.2 | P2543-R01-Oct24..4.3.1.5.4.12.1.17 BackfillingCCOPL4"115 | FO - Cable Pulling/ Laying from Habshan 5 to HGCP | Backfilling | C-4N-H5HG-PIPEL-8400 | C-4N-H5HG-PIPEL-6400 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | Sabka Gatch Compaction - Layer 2 | Sabka Gatch Laying - Layer 3 | C-4N-H5HG-PIPEL-2210 | C-4N-H5HG-PIPEL-2020 | SS | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | Sabka Gatch Compaction (Including ROW) - Layer 1 | Sabka Gatch Laying - Layer 2 | C-4N-H5HG-PIPEL-2200 | C-4N-H5HG-PIPEL-2010 | SS | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | P2543-R01-Oct24..4.3.1.5.4.12.1.14 PaddingCCOPL4"112 | Sabka Gatch Compaction - Layer 3 | Sabka Gatch Laying - Layer 4 | C-4N-H5HG-PIPEL-2220 | C-4N-H5HG-PIPEL-2030 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.10 Excavation (incl Bedding)CCOPL4"106 | P2543-R01-Oct24..4.3.1.5.4.12.1.13 Pipe Lowering & Tie-in / NDT from Habshan 5 to KP-12CCOPL4"108.1 | Bedding | Lowering | C-4N-H5HG-PIPEL-2410 | C-4N-H5HG-PIPEL-4800 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.5.4.12.1.10 Excavation (incl Bedding)CCOPL4"106 | P2543-R01-Oct24..4.3.1.5.4.12.1.23 Pipe Lowering & Tie-in / NDT from KP-12 to HGCP Compressor StationCCOPL4"108.2 | Bedding | Lowering | C-4N-H5HG-PIPEL-2410 | C-4N-H5HG-PIPEL-5000 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.2.3.12.1.15 Excavation (incl Bedding) from BVS-01 to KP 21.3CCOPL56236.1 | P2543-R01-Oct24..4.3.1.5.4.12.1.10 Excavation (incl Bedding)CCOPL4"106 | Trench Excavation | Trench Excavation | C-56-01HG-PL-CI-2400 | C-4N-H5HG-PIPEL-2400 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.4.12.1.17 BackfillingCCOPL4"115 | P2543-R01-Oct24..4.3.1.5.4.12.1.18 BermingCCOPL4"116 | Backfilling | Gatch Laying & Levelling | C-4N-H5HG-PIPEL-6400 | C-4N-H5HG-PIPEL-6800 | FF | Not Started | Not Started | 10
P2543-R01-Oct24..4.3.1.3.15.21.1.7 Excavation (incl Bedding)CCOPL52371 | P2543-R01-Oct24..4.3.1.3.15.21.1.7 Excavation (incl Bedding)CCOPL52371 | Trench Excavation | Bedding | C-52-0203-PL-CI-2400 | C-52-0203-PL-CI-2410 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.16.21.1.9 Excavation (incl Bedding)CCOPL52399 | P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | Bedding | Bedding | C-52-0304-PL-CI-2410 | C-52-0405-PL-CI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.7 ROW Access Road from BVS-05 to KP 126.2CCOPL52440.1 | P2543-R01-Oct24..4.3.1.3.18.21.1.10 ROW Access Road from BVS-05 to KP 126.2CCOPL52440.2 | Sabka ROW/Grading | Sabka ROW/Grading | C-52-0506-PL-CI-1800 | C-52-0506-PL-CI-1900 | FS | Not Started | Not Started | 30
P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | P2543-R01-Oct24..4.3.1.3.18.21.1.9 Excavation (incl Bedding)CCOPL52455 | Bedding | Bedding | C-52-0405-PL-CI-2410 | C-52-0506-PL-CI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.4.1 Telecom Works along Pipeline CCOP52IC57 | P2543-R01-Oct24..4.3.1.3.2.21.1.27 BermingCCOPL52316 | FO - Cable Pulling/ Laying | Gatch Laying & Levelling | C-52-HG01-PL-TE-8200 | C-52-HG01-PL-CI-6800 | FF | In Progress | In Progress | 1
P2543-R01-Oct24..4.3.2.3.10.8.2.1 Evaporation PondCCOPL52319 | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Evaporation Pond | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-PL-CI-7200 | C-52-HG01-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2.1 Evaporation PondCCOPL52375 | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Evaporation Pond | Cleaning & Gauging | C-52-0203-PL-CI-7200 | C-52-0203-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.1.1 Evaporation PondCCOPL52347 | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Evaporation Pond | Cleaning & Gauging | C-52-0102-PL-CI-7200 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.3.1 Evaporation PondCCOPL52459 | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Evaporation Pond | Cleaning & Gauging | C-52-0506-PL-CI-7200 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.2.1 Evaporation PondCCOPL52487 | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Evaporation Pond | Cleaning & Gauging | C-52-06CR-PL-CI-7200 | C-52-06CR-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.4.1 Piping Pre-Fabrication CCOB156P100 | P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | Piping Pre-Fabrication | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | C-56-591-01-PI-1000 | C-56-591-01-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | P2543-R01-Oct24..4.4.2.3 System Commissioninng - HGCP 52” P/L to Sweihan CRS 52” P/R (52”) | Pre-commissioning from BVS-06 to CRS Sweihan | Commissioning | PRECOM-52-06CR-1000 | CCM-PM4580 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.7.5 Piping Isometrics | P2543-R01-Oct24..4.3.1.1.3.10.40.1 Demolition Works (Paving)CCOHBCS300 | Final Issue for Design/ Construction-Piping Isometrics | Demolition of Existing Paving | HE-PI-1240 | C-56-G-HT-CI-0100 | SS | In Progress | Not Started | 60
P2543-R01-Oct24..4.3.1.3.2.21.1.11 Pipe Stringing from HGCP to KP 16.7CCOPL52305.1 | P2543-R01-Oct24..4.3.1.3.2.21.1.14 Pipe Stringing from KP 16.7 to BVS-01CCOPL52305.2 | Stringing-Lot1 | Stringing-Lot2 | C-52-HG01-PL-ME-2800 | C-52-HG01-PL-ME-3000 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.14 Pipe Stringing from KP 16.7 to BVS-01CCOPL52305.2 | P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | Stringing-Lot2 | Automatic Welding-Lot2 | C-52-HG01-PL-ME-3000 | C-52-HG01-PL-ME-3800 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | Automatic Welding-Lot1 | Automatic Welding-Lot2 | C-52-HG01-PL-ME-3600 | C-52-HG01-PL-ME-3800 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Ext. Joint Coating (Tie-in Joint)-Lot2 | Holiday Testing-Lot2 | C-52-HG01-PL-ME-4610 | C-52-HG01-PL-ME-5030 | SS | In Progress | In Progress | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Ext. Joint Coating (Tie-in Joint)-Lot2 | Holiday Testing-Lot2 | C-52-HG01-PL-ME-4610 | C-52-HG01-PL-ME-5030 | FF | In Progress | In Progress | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | Holiday Testing-Lot2 | Padding -Lot2 | C-52-HG01-PL-ME-5030 | C-52-HG01-PL-CI-6200 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | Holiday Testing-Lot2 | Padding -Lot2 | C-52-HG01-PL-ME-5030 | C-52-HG01-PL-CI-6200 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.2.21.1.29 Test Stations & Anode BedsCCOP52EL31 | P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | Installation of Temp. Anode | Padding -Lot2 | C-52-HG01-PL-CA-5600 | C-52-HG01-PL-CI-6200 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.2.21.1.29 Test Stations & Anode BedsCCOP52EL31 | P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | Installation of Temp. Anode | Padding -Lot2 | C-52-HG01-PL-CA-5600 | C-52-HG01-PL-CI-6200 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.2.21.1.16 NDT TestCCOPL52309 | P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | NDT-Lot2 | Ext. Joint Coating-Lot2 | C-52-HG01-PL-ME-4200 | C-52-HG01-PL-ME-4600 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.16 NDT TestCCOPL52309 | P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | NDT-Lot2 | Ext. Joint Coating-Lot2 | C-52-HG01-PL-ME-4200 | C-52-HG01-PL-ME-4600 | FF | In Progress | In Progress | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.13 Cold BendsCCOPL52307 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Cold Bends-Lot2 | Section Tie-in Welding-Lot2 | C-52-HG01-PL-ME-3400 | C-52-HG01-PL-ME-5010 | FF | Completed | In Progress | 2
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Lowering-Lot2 | Section Tie-in Welding-Lot2 | C-52-HG01-PL-ME-5000 | C-52-HG01-PL-ME-5010 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Lowering-Lot2 | Section Tie-in Welding-Lot2 | C-52-HG01-PL-ME-5000 | C-52-HG01-PL-ME-5010 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Section Tie-in Welding-Lot2 | NDT (Tie-in Joint)-Lot2 | C-52-HG01-PL-ME-5010 | C-52-HG01-PL-ME-5020 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Section Tie-in Welding-Lot2 | NDT (Tie-in Joint)-Lot2 | C-52-HG01-PL-ME-5010 | C-52-HG01-PL-ME-5020 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | NDT (Tie-in Joint)-Lot2 | Ext. Joint Coating (Tie-in Joint)-Lot2 | C-52-HG01-PL-ME-5020 | C-52-HG01-PL-ME-4610 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | NDT (Tie-in Joint)-Lot2 | Ext. Joint Coating (Tie-in Joint)-Lot2 | C-52-HG01-PL-ME-5020 | C-52-HG01-PL-ME-4610 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | P2543-R01-Oct24..4.3.1.3.2.21.1.16 NDT TestCCOPL52309 | Automatic Welding-Lot2 | NDT-Lot2 | C-52-HG01-PL-ME-3800 | C-52-HG01-PL-ME-4200 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | P2543-R01-Oct24..4.3.1.3.2.21.1.16 NDT TestCCOPL52309 | Automatic Welding-Lot2 | NDT-Lot2 | C-52-HG01-PL-ME-3800 | C-52-HG01-PL-ME-4200 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.6 Crossing Manual @ KP 1+255 to 1+474 (PX-25 to PX-30) | Stringing (BVS-01 to HBCMPLX) | Trench Excavation | C-56-HC01-PL-ME-2800 | C-56-HC01-CMA14-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.22.12 Crossing Manual @ KP 11+213 to 11+490 (PX-87 to PX-95) | Stringing (BVS-01 to HBCMPLX) | Trench Excavation | C-56-HC01-PL-ME-2800 | C-56-HC01-CMA20-1000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.2.3.5.8.2 Pre-commissioning from BVS-02 to BVS-03CPCPL52327.5 | P2543-R01-Oct24..4.4.2.3 System Commissioninng - HGCP 52” P/L to Sweihan CRS 52” P/R (52”) | Pre-commissioning from BVS-02 to BVS-03 | Commissioning | PRECOM-52-0203-1000 | CCM-PM4580 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | P2543-R01-Oct24..4.4.2.3 System Commissioninng - HGCP 52” P/L to Sweihan CRS 52” P/R (52”) | Pre-commissioning from BVS-02 to BVS-01 | Commissioning | PRECOM-52-0201-1000 | CCM-PM4580 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | P2543-R01-Oct24..4.4.2.3 System Commissioninng - HGCP 52” P/L to Sweihan CRS 52” P/R (52”) | Pre-commissioning from BVS-03 to BVS-04 | Commissioning | PRECOM-52-0304-1000 | CCM-PM4580 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | P2543-R01-Oct24..4.4.2.3 System Commissioninng - HGCP 52” P/L to Sweihan CRS 52” P/R (52”) | Pre-commissioning from BVS-04 to BVS-05 | Commissioning | PRECOM-52-0405-1000 | CCM-PM4580 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | P2543-R01-Oct24..4.4.2.3 System Commissioninng - HGCP 52” P/L to Sweihan CRS 52” P/R (52”) | Pre-commissioning from BVS-05 to BVS-06 | Commissioning | PRECOM-52-0506-1000 | CCM-PM4580 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | Trench Excavation | Excavation (Manual-Trial Pit) | C-52-0405-PL-CI-2400 | C-52-0405-CMA23-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | P2543-R01-Oct24..4.3.1.3.17.21.1.23 BackfillingCCOPL52422 | FO - Cable Pulling/ Laying | Backfilling | C-52-0405-PL-TE-8200 | C-52-0405-PL-CI-6400 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Concrete Works for Pipe Support Foundations | Pre-Fabrication & Installation of Pipe Supports | C-4N-HG-TPR-CI-1600 | C-4N-HG-TPR-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.2.3.12.1.2 Piperack - Excavation (including backfilling, compaction and disposal of surplus earth)CCOH5CS101 | P2543-R01-Oct24..4.3.1.5.1.12.1.1 Demolition Works (Paving)CCOH4NCS64 | Earth Works for Access Platforms & Misc. Structural Foundations | Demolition Works (Paving) | C-4N-H5-TPL-CI-1040 | C-4N-HG-TPR-CI-0100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2.3 System Commissioninng - HGCP 52” P/L to Sweihan CRS 52” P/R (52”) | P2543-R01-Oct24..4.4.2 Commissioning | Commissioning | Wrap up works for PAC-2 | CCM-PM4580 | CCM-PM4530 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | P2543-R01-Oct24..4.3.1.3.19.8.1.24 BackfillingCCOPL52478 | FO - Cable Pulling/ Laying | Backfilling | C-52-06CR-PL-TE-8200 | C-52-06CR-PL-CI-6400 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | P2543-R01-Oct24..4.3.1.3.4.1.22.5.1 Pig Receiver 839-V-101 52'' Pipeline/ Piping Hook-upCCOSWPI514 | Piping Erection | Installation of Isolation Joint | C-52-PR-839-PI-1200 | C-52-PR-839-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | P2543-R01-Oct24..4.3.1.3.1.21.5.1 Pig Launcher 838-V-602 52'' Pipeline/Piping Hook-upCCOH52PI70 | Piping Erection | Installation of Isolation Joint | C-52-PL-838-PI-1200 | C-52-PL-838-PL-1000 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Complete 50% Construction & Pre-commissioning | Complete 75% Construction & Pre-commissioning | ML1080 | ML1090 | FF | Not Started | Not Started | 126
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 8 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 2 | C-PER-1420 | C-PER-1360 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 1 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 6 | C-PER-1350 | C-PER-1400 | FF | In Progress | In Progress | 14
P2543-R01-Oct24..4.3.1.2.3.12.1.20 Automatic Welding from BVS-01 to KP 21.3CCOPL56256.1 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding | Complete Pipeline welding - 56" Sales Gas Pipeline (50% Welding) | C-56-01HG-PL-ME-3600 | ML1589-E04 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.31 Automatic Welding from KP 21.3 to HGCPCCOPL56256.2 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding | Complete Pipeline welding - 56" Sales Gas Pipeline (50% Welding) | C-56-01HG-PL-ME-3800 | ML1589-E04 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | Trench Excavation-Lot2 | Bedding-Lot2 | C-52-HG01-PL-CI-2600 | C-52-HG01-PL-CI-2610 | SS | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Bedding-Lot2 | Lowering-Lot2 | C-52-HG01-PL-CI-2610 | C-52-HG01-PL-ME-5000 | SS | In Progress | In Progress | 4
P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Ext. Joint Coating-Lot2 | Lowering-Lot2 | C-52-HG01-PL-ME-4600 | C-52-HG01-PL-ME-5000 | SS | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning | Complete Drying & Purging of all facilities including Pipeline & Block Valve Stations- 56" Sales Gas Pipeline | PRECOM-56-59101-1000 | ML1649-E10 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Project Commencement Date (Effective) | Project Kick off Meeting | PRJ-MI-1000 | ML1002 | FS | Completed | Completed | 8
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Award / Project Start | Project Commencement Date (Effective) | ML1000 | PRJ-MI-1000 | FS | Completed | Completed | 8
P2543-R01-Oct24..4.4.AB.4 Commissioning & As-Built | P2543-R01-Oct24..4.4.2.3 System Commissioninng - HGCP 52” P/L to Sweihan CRS 52” P/R (52”) | Ready for Commissioning & As-Built Submission | Commissioning | COM-1000 | CCM-PM4580 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.BK.6.3 Delivery & Receipt at site | P2543-R01-Oct24..4.3.1.2.3.12.1.20 Automatic Welding from BVS-01 to KP 21.3CCOPL56256.1 | Final Pipeline Bulk material MTO | Automatic Welding | HM-PL-0890 | C-56-01HG-PL-ME-3600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..ML Milestones | Completion of Procurement Services | Project Finish | ML1038-C20 | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | Receive at Site - Coated / Painted Line pipes- 52" (100% to total Qty) | Stringing (BVS-06 to SW CRS) | ML1399-D5 | C-52-06CR-PL-ME-2800 | FS | Not Started | Not Started | 5
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.17.21.1.10 Pipe StringingCCOPL52413 | Receive at Site - Coated / Painted Line pipes- 52" (50% to total Qty) | Stringing (BVS-04 to BVS-05) | ML1509-D3 | C-52-0405-PL-ME-2800 | FS | Completed | In Progress | 5
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.24 Crossing Manual @ KP 0+126 to KP 0+250 (PX-01 to PX-06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | Padding | Trench Excavation | C-56-HC01-CMA08-1070 | C-56-HC01-CMA12-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.28 Crossing Manual @ KP 0+252 to 0+365 (PX-07 to PX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.13.25 Crossing Manual @ KP 0+974 to 1+070 (PX-13 to PX-18) | Padding | Trench Excavation | C-56-HC01-CMA12-1070 | C-56-HC01-CMA10-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Achieve PAC-1 for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | Project Finish | ML1040 | ML1060 | FF | Not Started | Not Started | 14
P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.10 Earth Works for Paving CCOSWCS315.1 | Earth Works for Impact Wall | Earth Works for Paving of Interlock tiles & Kerb Stone Embankment | C-52-PR-839-CI-1060 | C-52-PR-839-CI-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.8 ROW Access RoadCCOPL52384 | P2543-R01-Oct24..4.3.1.3.16.21.1.7 Cut & Fill in Sandy AreaCCOPL52410 | Non-Sabka ROW/Grading | Cut & Fill (@ Non-Sabkha) | C-52-0304-PL-CI-1800 | C-52-0304-PL-CI-1400 | FS | Completed | In Progress | 45
P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | P2543-R01-Oct24..4.3.1.3.18.21.1.21.1 Crossing Manual @ KP 117+727, 117+824 (CX-50,X-1) | Trench Excavation | Trench Excavation | C-52-0405-CME08-1000 | C-52-0506-CMA06-1000 | FS | Not Started | Not Started | 4
P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | P2543-R01-Oct24..4.3.1.3.18.21.1.24 BackfillingCCOPL52450 | FO - Cable Pulling/ Laying | Backfilling | C-52-0506-PL-TE-8200 | C-52-0506-PL-CI-6400 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | P2543-R01-Oct24..4.3.1.3.18.21.1.24 BackfillingCCOPL52450 | FO - Cable Pulling/ Laying | Backfilling | C-52-0506-PL-TE-8200 | C-52-0506-PL-CI-6400 | SS | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.18.21.1.9 Excavation (incl Bedding)CCOPL52455 | P2543-R01-Oct24..4.3.1.3.18.21.1.9 Excavation (incl Bedding)CCOPL52455 | Trench Excavation | Bedding | C-52-0506-PL-CI-2400 | C-52-0506-PL-CI-2410 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..4.3.1.3.18.21.1.15 Ext. Joint CoatingCCOPL52446 | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-PL-ME-4410 | C-52-0506-PL-ME-4830 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.3.19.8.1.19 Ext. Joint CoatingCCOPL52474 | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-PL-ME-4410 | C-52-06CR-PL-ME-4830 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.35 Backfilling from KP 6 to KP 12.6CCOPL56217.2 | FO - Cable Pulling/ Laying | Backfilling from KP 6 to KP 12.6 | C-56-HC01-PL-TE-8400 | C-56-HC01-PL-CI-6600 | SS | Not Started | Not Started | 4
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.1.2 Construction Procedure Qualification | Mobilization of Automatic Welding Machines at site | Procedure Qualification (PQT/WQT for Pipeline & Piping etc) | ML1559-E01 | C-COM-1010 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -HGCP to BVS-3 | Complete 25% Construction & Pre-commissioning | ML1659-E11 | ML1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Complete Site Grading & ROW along the Pipeline - 56" Sales Gas Pipeline | Lowering | ML1569-E02 | C-56-HC01-PL-ME-5000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | P2543-R01-Oct24..ML Milestones | Precommissioning Pig Launcher 838-V-602 | Complete 100% Construction & Pre-commissioning | PRECOM-52-PL-1000 | ML1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML Milestones | Complete 25% Construction & Pre-commissioning | Complete 50% Construction & Pre-commissioning | ML1070 | ML1080 | FF | Not Started | Not Started | 102
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Complete Pipeline welding - 56" Sales Gas Pipeline (50% Welding) | Complete Hydrotesting - 56" Sales Gas Pipeline | ML1589-E04 | ML1639-E09 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Complete Pipeline welding - 56" Sales Gas Pipeline (100% Welding) | Complete Hydrotesting - 56" Sales Gas Pipeline | ML1599-E05 | ML1639-E09 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | Project Finish | ML1020 (Internal) | ML1060 | FF | Not Started | Not Started | 65
P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning | Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | PRECOM-56-PL-1000 | ML1020 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.1.2.3.1 PrecommissioningCPC-HBS501 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning | Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | PRECOM-56-EB2-1000 | ML1020 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.1.8.3.1 PrecommissioningCPC-HBS502 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning | Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | PRECOM-56-G-1000 | ML1020 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning | Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | PRECOM-56-HGHC-1000 | ML1020 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.1.3.1 PrecommissioningCPCHGCP561 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning | Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | PRECOM-56-PR-1000 | ML1020 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning | Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | PRECOM-56-59101-1000 | ML1020 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning BVS-1 | Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | PRECOM-56-59801-1000 | ML1020 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning BVS-2 | Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | PRECOM-56-59802-1000 | ML1020 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning BVS-4 | Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | PRECOM-56-59804-1000 | ML1020 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning BVS-5 | Mechanical Completion of PL & facilities- 56" Sales Gas Pipeline | PRECOM-56-59805-1000 | ML1020 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-commissioning from BVS-02 to BVS-01 | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-0201-1000 | ML1030 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.1 Precommissioning Pig Launcher 838-V-602CPCHGCP521 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning Pig Launcher 838-V-602 | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-PL-1000 | ML1030 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-commissioning from HGCP to BVS-01 | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-HG01-1000 | ML1030 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2 Pre-commissioning from BVS-02 to BVS-03CPCPL52327.5 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-commissioning from BVS-02 to BVS-03 | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-0203-1000 | ML1030 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.1 Pre-Commissioning Intrusion Detection KP96.2 to KP98.3CPCHGCP525 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-Commissioning Intrusion Detection KP96.2 to KP98.3 | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-IDS1-1000 | ML1030 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-commissioning from BVS-03 to BVS-04 | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-0304-1000 | ML1030 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.2 Pre-Commissioning Intrusion Detection KP102 to KP108.9CPCHGCP523 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-Commissioning Intrusion Detection KP102 to KP108.9 | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-IDS2-1000 | ML1030 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-commissioning from BVS-04 to BVS-05 | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-0405-1000 | ML1030 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.4 Precommissioning DEL/TFP PipelineCPCHGCP522 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning DEL/TFP Pipeline | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-D-1000 | ML1030 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.2 Pre-Commissioning Intrusion Detection KP122 to KP123CPCHGCP524 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-Commissioning Intrusion Detection KP122 to KP123 | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-IDS3-1000 | ML1030 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-commissioning from BVS-05 to BVS-06 | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-0506-1000 | ML1030 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning BVS-6 | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-59806-1000 | ML1030 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Pre-commissioning from BVS-06 to CRS Sweihan | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-06CR-1000 | ML1030 (Internal) | FS | Not Started | Not Started | 6
P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning Electrical Building Type-I | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-EB1-1000 | ML1030 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Precommissioning Pig Receiver 839-V-101 | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | PRECOM-52-PR-1000 | ML1030 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..ML.4 Commissioning and PAC | Wrap up works for PAC-1 | PAC 1 - 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | CCM-PM4550 | ML-PAC1 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2 Commissioning | P2543-R01-Oct24..ML.4 Commissioning and PAC | Wrap up works for PAC-2 | PAC 2 - 52" Sales Gas Pipeline & 36"Jump-over Line | CCM-PM4530 | ML-PAC2 (Internal) | FS | Not Started | Not Started | 11
P2543-R01-Oct24..4.4.2.2 System Commissioninng - 56” P/L Facility to HGCP 56” P/R (56”) | P2543-R01-Oct24..ML.4 Commissioning and PAC | Commissioning | PAC 1 - 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | CCM-PM4570 | ML-PAC1 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.4.2.3 System Commissioninng - HGCP 52” P/L to Sweihan CRS 52” P/R (52”) | P2543-R01-Oct24..ML.4 Commissioning and PAC | Commissioning | PAC 2 - 52" Sales Gas Pipeline & 36"Jump-over Line | CCM-PM4580 | ML-PAC2 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML Milestones | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | Project Finish | ML1030 (Internal) | ML1060 | FS | Not Started | Not Started | 39
P2543-R01-Oct24..ML.4 Commissioning and PAC | P2543-R01-Oct24..ML Milestones | PAC 1 - 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | Project Finish | ML-PAC1 (Internal) | ML1060 | FS | Not Started | Not Started | 12
P2543-R01-Oct24..ML.4 Commissioning and PAC | P2543-R01-Oct24..ML Milestones | PAC 2 - 52" Sales Gas Pipeline & 36"Jump-over Line | Project Finish | ML-PAC2 (Internal) | ML1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Complete 100% Construction & Pre-commissioning | Mechanical Completion of PL & facilities- 52" Sales Gas Pipeline | ML1100 | ML1030 (Internal) | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.2.2.12.4.1.16 Automatic WeldingCCOPL56207 | Complete Pipeline welding - 56" Sales Gas Pipeline (50% Welding) | Automatic Welding | ML1589-E04 | C-56-HC01-PL-ME-3600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.2.2.12.4.1.17 NDT TestCCOPL56208 | Complete Pipeline welding - 56" Sales Gas Pipeline (100% Welding) | NDT | ML1599-E05 | C-56-HC01-PL-ME-4000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | Complete Site Grading & ROW along the Pipeline - 52" Sales Gas Pipeline -BVS-3 to Sweihan CRS | Stringing (BVS-06 to SW CRS) | ML1669-E12 | C-52-06CR-PL-ME-2800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | Pre-commissioning from BVS-06 to CRS Sweihan | ML1679-E13 | PRECOM-52-06CR-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Complete Pipeline welding - 52" Sales Gas Pipeline - 25% Welding | Complete Pipeline welding - 52" Sales Gas Pipeline - 50% Welding | ML1689-E14 | ML1699-E15 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.1.3.19.8.1.9 Excavation (incl Bedding)CCOPL52483 | Complete Pipeline welding - 52" Sales Gas Pipeline - 100% Welding | Trench Excavation | ML1719-E17 | C-52-06CR-PL-CI-2400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | Complete Hydrotesting - 52" Sales Gas Pipeline -Launcher to BVS-01 | Pre-commissioning from HGCP to BVS-01 | ML1759-E21 | PRECOM-52-HG01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 01 to BVS-02 | Pre-commissioning from BVS-02 to BVS-01 | ML1769-E22 | PRECOM-52-0201-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.3.5.8.2 Pre-commissioning from BVS-02 to BVS-03CPCPL52327.5 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 02 to BVS-03 | Pre-commissioning from BVS-02 to BVS-03 | ML1779-E23 | PRECOM-52-0203-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 03 to BVS-04 | Pre-commissioning from BVS-03 to BVS-04 | ML1789-E24 | PRECOM-52-0304-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 04 to BVS-05 | Pre-commissioning from BVS-04 to BVS-05 | ML1799-E25 | PRECOM-52-0405-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 05 to BVS-06 | Pre-commissioning from BVS-05 to BVS-06 | ML1809-E26 | PRECOM-52-0506-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | Complete Hydrotesting - 52" Sales Gas Pipeline - BVS 06 to Sweihan Receiver | Pre-commissioning from BVS-06 to CRS Sweihan | ML1819-E27 | PRECOM-52-06CR-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.4.2.3 System Commissioninng - HGCP 52” P/L to Sweihan CRS 52” P/R (52”) | Complete Drying & Purging of all facilities including Pipeline & Block Valve Stations - 52" Sales Gas Pipeline | Commissioning | ML1829-E28 | CCM-PM4580 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | Complete Piping works at Sweihan CRS | Precommissioning Electrical Building Type-I | ML1849-E30 | PRECOM-52-EB1-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | P2543-R01-Oct24..4.3.2.3.1.8.4 Precommissioning Pig Receiver 839-V-101CPCSW112 | Complete Piping works at Sweihan CRS | Precommissioning Pig Receiver 839-V-101 | ML1849-E30 | PRECOM-52-PR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.4 Commissioning and PAC | P2543-R01-Oct24..ML.4 Commissioning and PAC | PAC 1 - 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | Achieve (PAC-1) for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | ML-PAC1 (Internal) | ML2039-F05 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.4 Commissioning and PAC | P2543-R01-Oct24..ML Milestones | Achieve (PAC-1) for pipeline & facilities- 56" Sales Gas Pipeline, 4" Water line & 4" Nitrogen pipeline | Project Finish | ML2039-F05 | ML1060 | FF | Not Started | Not Started | 14
P2543-R01-Oct24..ML.4 Commissioning and PAC | P2543-R01-Oct24..ML.4 Commissioning and PAC | PAC 2 - 52" Sales Gas Pipeline & 36"Jump-over Line | Achieve (PAC-2) for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | ML-PAC2 (Internal) | ML2049-F06 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.4 Commissioning and PAC | P2543-R01-Oct24..ML Milestones | Achieve (PAC-2) for pipeline & facilities- 52" Sales Gas Pipeline & 36"Jump-over Line | Project Finish | ML2049-F06 | ML1060 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 7 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 6 | C-PER-1080 | C-PER-1070 | FF | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.16 Automatic WeldingCCOPL56207 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.17 NDT TestCCOPL56208 | Automatic Welding | NDT | C-56-HC01-PL-ME-3600 | C-56-HC01-PL-ME-4000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.11 Pipe StringingCCOPL52329 | P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | Stringing (BVS-01 to BVS-02) | Stringing (BVS-03 to BVS-04) | C-52-0102-PL-ME-2800 | C-52-0304-PL-ME-2800 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | P2543-R01-Oct24..4.3.1.3.17.21.1.10 Pipe StringingCCOPL52413 | Stringing (BVS-03 to BVS-04) | Stringing (BVS-04 to BVS-05) | C-52-0304-PL-ME-2800 | C-52-0405-PL-ME-2800 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.14 Pipe Stringing from KP 16.7 to BVS-01CCOPL52305.2 | P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | Stringing-Lot2 | Stringing (BVS-02 to BVS-03) | C-52-HG01-PL-ME-3000 | C-52-0203-PL-ME-2800 | SS | In Progress | Completed | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.15.21.1.20 Test Stations & Anode BedsCCOP52EL36 | Lowering | Installation of Temp. Anode | C-52-0203-CME01-1020 | C-52-0203-PL-CA-5600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.40 Excavation Works for fence posts from BVS-01 to BVS-02CCOP52CS53.6 | P2543-R01-Oct24..4.3.1.3.5.21.1.41 Concrete Works for fence posts from BVS-01 to BVS-02CCOP52CS54.6 | Compaction & Testing for Fence Foundation (BVS-02 to BVS-01) | Concrete Works (Blinding) for Fence Foundation (BVS-02 to BVS-01) | C-52-0102-FENCE-1020 | C-52-0102-FENCE-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Gatch Laying & Levelling | Gatch Laying & Levelling | C-56-01HG-PL-CI-6800 | C-56-01HG-PL-CI-7000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.5 Crossing Manual @ KP 150+322 (FX-54) | Lowering | Section Tie-in Welding | C-52-06CR-CMA03-1020 | C-52-06CR-CMA03-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.1.7 Pipe Supports Fabrication & InstallationCCOSWSS500 | P2543-R01-Oct24..4.3.1.3.4.1.22.1.8 Platforms/Crossovers/ Guardrails and Bollards/ WindsockCCOSWSS505 | Pre-Fabrication & Installation of Pipe Supports | Pre-Fabrication & Installation Guardrails, Bollards, Windsock & Misc. Supports | C-52-PR-839-CI-2000 | C-52-PR-839-CI-3010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.4.1 Piping Pre-FabricationCCOH4NPI050 | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Piping Pre-Fabrication | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-4N-HG-TPR-PI-1000 | C-4N-HG-TPR-EI-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.5.1.12.4.6 Final Bolt Torquing/ Re-InstatementCCOH4NPI100 | P2543-R01-Oct24..4.3.1.5.1.12.6.1 E&I WorksCCOH4NEL51 | Final Bolt Torquing/ Re-Instatement | Pre-Fabrication & Installation of Field Instrument, JB Supports | C-4N-HG-TPR-PI-2000 | C-4N-HG-TPR-EI-2210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | P2543-R01-Oct24..4.3.1.3.19.8.1.11.4 Crossing Manual @ KP 150+043 (FX-53) | Excavation (Manual-Trial Pit) | Trench Excavation | C-52-06CR-CMA01-0970 | C-52-06CR-CMA02-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | P2543-R01-Oct24..4.3.1.3.19.8.1.14.13 Crossing Manual @ KP 160+979 (OX-16) | Lowering | Section Tie-in Welding | C-52-06CR-CMA13-1020 | C-52-06CR-CMA13-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | Stringing (BVS-06 to SW CRS) | Excavation (Manual-Trial Pit) | C-52-06CR-PL-ME-2800 | C-52-06CR-CMA01-0970 | SS | Not Started | Not Started | 21
P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | P2543-R01-Oct24..4.3.1.3.19.8.1.10.2 Crossing Manual @ KP 145+909 to 145+995 (PX-39,FX-51) | Stringing (BVS-06 to SW CRS) | Excavation (Manual-Trial Pit) | C-52-06CR-PL-ME-2800 | C-52-06CR-CMA01-0970 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | P2543-R01-Oct24..4.3.1.3.19.8.1.26 Test Stations & Anode BedsCCOP52EL48 | Holiday Testing | Installation of Temp. Anode | C-52-06CR-PL-ME-4830 | C-52-06CR-PL-CA-5600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | P2543-R01-Oct24..ML Milestones | Pre-commissioning from BVS-06 to CRS Sweihan | Complete 100% Construction & Pre-commissioning | PRECOM-52-06CR-1000 | ML1100 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | P2543-R01-Oct24..4.3.1.3.15.21.1.6 Sabkha PadCCOPL52377 | Sabka ROW/Grading | Sabka Gatch Laying (Including ROW) - Layer 1 | C-52-0203-PL-CI-1800 | C-52-0203-PL-CI-2000 | FF | Completed | Completed | 21
P2543-R01-Oct24..4.3.1.3.16.21.1.8 ROW Access RoadCCOPL52384 | P2543-R01-Oct24..4.3.1.3.16.21.1.6 Sabkha PadCCOPL52405 | Non-Sabka ROW/Grading | Sabka Gatch Laying (Including ROW) - Layer 1 | C-52-0304-PL-CI-1800 | C-52-0304-PL-CI-2000 | FF | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.8 ROW Access RoadCCOPL52412 | P2543-R01-Oct24..4.3.1.3.17.21.1.6 Sabkha PadCCOPL52433 | Non-Sabka ROW/Grading | Sabka Gatch Laying (Including ROW) - Layer 1 | C-52-0405-PL-CI-1800 | C-52-0405-PL-CI-2000 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.10 Pipe StringingCCOPL52413 | P2543-R01-Oct24..4.3.1.3.18.21.1.11 Pipe StringingCCOPL52441 | Stringing (BVS-04 to BVS-05) | Stringing (BVS-05 to BVS-06) | C-52-0405-PL-ME-2800 | C-52-0506-PL-ME-2800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | P2543-R01-Oct24..4.3.1.3.19.8.1.17 Automatic WeldingCCOPL52476 | Stringing (BVS-06 to SW CRS) | Automatic Welding | C-52-06CR-PL-ME-2800 | C-52-06CR-PL-ME-3600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.3.12.1.16 Pipe Stringing from BVS-01 to KP 21.3CCOPL56250.1 | Receipt at site and inspection of Line Pipes - Lot 6 (Coated) | Stringing (BVS-01 to KP 21.3) | HM-PL-0110 | C-56-01HG-PL-ME-2800 | FF | Not Started | Not Started | 20
P2543-R01-Oct24..4.3.1.3.17.21.1.12 Automatic WeldingCCOPL52420 | P2543-R01-Oct24..4.3.1.3.18.21.1.13 Automatic WeldingCCOPL52448 | Automatic Welding | Automatic Welding | C-52-0405-PL-ME-3600 | C-52-0506-PL-ME-3600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.11 Pipe StringingCCOPL52441 | P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | Stringing (BVS-05 to BVS-06) | Stringing (BVS-06 to SW CRS) | C-52-0506-PL-ME-2800 | C-52-06CR-PL-ME-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.1.13 Automatic WeldingCCOPL52448 | P2543-R01-Oct24..4.3.1.3.19.8.1.17 Automatic WeldingCCOPL52476 | Automatic Welding | Automatic Welding | C-52-0506-PL-ME-3600 | C-52-06CR-PL-ME-3600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.18 Ext. Joint CoatingCCOPL52311 | NDT (Tie-in Joint)-Lot1 | Ext. Joint Coating (Tie-in Joint)-Lot1 | C-52-HG01-PL-ME-4820 | C-52-HG01-PL-ME-4410 | FF | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.15.21.1.12 Ext. Joint CoatingCCOPL52362 | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0203-PL-ME-4410 | C-52-0203-PL-ME-4830 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | P2543-R01-Oct24..4.3.1.3.8.21.1.13 Automatic WeldingCCOPL52336 | Automatic Welding-Lot2 | Automatic Welding | C-52-HG01-PL-ME-3800 | C-52-0102-PL-ME-3600 | FF | In Progress | In Progress | 6
P2543-R01-Oct24..4.3.1.3.8.21.1.13 Automatic WeldingCCOPL52336 | P2543-R01-Oct24..4.3.1.3.15.21.1.10 Automatic WeldingCCOPL52364 | Automatic Welding | Automatic Welding | C-52-0102-PL-ME-3600 | C-52-0203-PL-ME-3600 | FS | In Progress | Not Started | -32
P2543-R01-Oct24..4.3.1.3.15.21.1.10 Automatic WeldingCCOPL52364 | P2543-R01-Oct24..4.3.1.3.16.21.1.12 Automatic WeldingCCOPL52392 | Automatic Welding | Automatic Welding | C-52-0203-PL-ME-3600 | C-52-0304-PL-ME-3600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.12 Automatic WeldingCCOPL52392 | P2543-R01-Oct24..4.3.1.3.17.21.1.12 Automatic WeldingCCOPL52420 | Automatic Welding | Automatic Welding | C-52-0304-PL-ME-3600 | C-52-0405-PL-ME-3600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | Survey Marking BVS-04 to BVS-05 | Survey Marking BVS-05 to BVS-06 | C-52-0405-PL-CI-1000 | C-52-0506-PL-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | Survey Marking HGCP to BVS-01 | Survey Marking BVS-01 to BVS-02 | C-52-HG01-PL-CI-1000 | C-52-0102-PL-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | Survey Marking BVS-01 to BVS-02 | Survey Marking BVS-02 to BVS-03 | C-52-0102-PL-CI-1000 | C-52-0203-PL-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | Survey Marking BVS-02 to BVS-03 | Survey Marking BVS-03 to BVS-04 | C-52-0203-PL-CI-1000 | C-52-0304-PL-CI-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.2.21.1.6 Sabkha Pad Gatch laying from HGCP to BVS-01 (Layer 1&2)CCOPL52303.1 | Survey Marking HGCP to BVS-01 | Sabka ROW/Grading | C-52-HG01-PL-CI-1000 | C-52-HG01-PL-CI-1800 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | Automatic Welding-Lot2 | Trench Excavation-Lot2 | C-52-HG01-PL-ME-3800 | C-52-HG01-PL-CI-2600 | SS | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.3.2.21.1.15 Automatic WeldingCCOPL52308 | P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | Automatic Welding-Lot2 | Trench Excavation-Lot2 | C-52-HG01-PL-ME-3800 | C-52-HG01-PL-CI-2600 | FF | In Progress | In Progress | 3
P2543-R01-Oct24..4.3.1.3.20 Surveying of Pipeline Route (HGCP to Sweihan 161.7Km)CCOPL52300 | P2543-R01-Oct24..4.3.1.3.8.21.1.6 Sabkha Pad Gatch laying from BVS-01 to BVS-02 (Layer-1 &2)CCOPL52349.1 | Survey Marking BVS-01 to BVS-02 | Sabka ROW/Grading | C-52-0102-PL-CI-1000 | C-52-0102-PL-CI-1800 | FF | Completed | Completed | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.8 Excavation (incl Bedding)CCOPL52343 | P2543-R01-Oct24..4.3.1.3.8.21.1.8 Excavation (incl Bedding)CCOPL52343 | Trench Excavation | Bedding | C-52-0102-PL-CI-2400 | C-52-0102-PL-CI-2410 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.2.21.1.14 Pipe Stringing from KP 16.7 to BVS-01CCOPL52305.2 | P2543-R01-Oct24..4.3.1.3.8.21.1.11 Pipe StringingCCOPL52329 | Stringing-Lot2 | Stringing (BVS-01 to BVS-02) | C-52-HG01-PL-ME-3000 | C-52-0102-PL-ME-2800 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.8 ROW Access RoadCCOPL52468 | P2543-R01-Oct24..4.3.1.3.19.8.1.7 Sabkha PadCCOPL52489 | Sabka ROW/Grading | Sabka Gatch Laying (Including ROW) - Layer 1 | C-52-06CR-PL-CI-1800 | C-52-06CR-PL-CI-2000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.29 Backfilling for Fence from BVS-04 to BVS-05CCOP52CS56.3 | P2543-R01-Oct24..4.3.1.3.5.21.1.28 Fence Installation (Type3) from BVS-04 to BVS-05CCOP52CS57.3 | Back Filliing of Fence Post Foundation (BVS-04 to BVS-05) | Installation of Fence Mesh (BVS-04 to BVS-05) | C-52-0405-FENCE-1060 | C-52-0405-FENCE-1070 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.28 Fence Installation (Type3) from BVS-04 to BVS-05CCOP52CS57.3 | P2543-R01-Oct24..4.3.1.3.5.21.1.29 Backfilling for Fence from BVS-04 to BVS-05CCOP52CS56.3 | Installation of Fence Post (Including Foundation) (BVS-04 to BVS-05) | Back Filliing of Fence Post Foundation (BVS-04 to BVS-05) | C-52-0405-FENCE-1050 | C-52-0405-FENCE-1060 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.25 Concrete Works for fence posts from BVS-04 to BVS-05CCOP52CS54.3 | P2543-R01-Oct24..4.3.1.3.5.21.1.26 Concrete Protection for fence from BVS-04 to BVS-05CCOP52CS55.3 | Concrete Works (Blinding) for Fence Foundation (BVS-04 to BVS-05) | Concrete Protection (Blinding) for Fence Foundation (BVS-04 to BVS-05) | C-52-0405-FENCE-1030 | C-52-0405-FENCE-1040 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.24 Excavation Works for fence posts from BVS-04 to BVS-05CCOP52CS53.3 | P2543-R01-Oct24..4.3.1.3.5.21.1.25 Concrete Works for fence posts from BVS-04 to BVS-05CCOP52CS54.3 | Compaction & Testing for Fence Foundation (BVS-04 to BVS-05) | Concrete Works (Blinding) for Fence Foundation (BVS-04 to BVS-05) | C-52-0405-FENCE-1020 | C-52-0405-FENCE-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.24 Excavation Works for fence posts from BVS-04 to BVS-05CCOP52CS53.3 | P2543-R01-Oct24..4.3.1.3.5.21.1.24 Excavation Works for fence posts from BVS-04 to BVS-05CCOP52CS53.3 | Earth Works for Fence Foundation (BVS-04 to BVS-05) | Compaction & Testing for Fence Foundation (BVS-04 to BVS-05) | C-52-0405-FENCE-1010 | C-52-0405-FENCE-1020 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | P2543-R01-Oct24..4.3.1.3.17.21.1.26 Test Stations & Anode BedsCCOP52EL42 | Holiday Testing | Installation of Temp. Anode | C-52-0405-PL-ME-4830 | C-52-0405-PL-CA-5600 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.14.24 Crossing Manual @ KP 110+118 to 110+225 (CX-46,X1,X2,X3) | P2543-R01-Oct24..4.3.1.3.17.21.1.14.26 Crossing Manual @ KP 110+873 to 110+874 (CX-48,X1) | Trench Excavation | Trench Excavation | C-52-0405-CMA13-1000 | C-52-0405-CMA15-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | P2543-R01-Oct24..4.3.1.3.17.21.1.17.32 Crossing Manual @ KP 111+732 (FX-38) | Lowering | Section Tie-in Welding | C-52-0405-CMA32-1020 | C-52-0405-CMA32-1030 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.16 Automatic WeldingCCOPL56207 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.14 Excavation (incl Bedding) from KP 6 to KP 12.6CCOPL56206.2 | Automatic Welding | Trench Excavation | C-56-HC01-PL-ME-3600 | C-56-HC01-PL-CI-2600 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.3.12.2.5.1 Entry & Exit Pit ConstructionCCOPL56906 | P2543-R01-Oct24..4.3.1.2.3.12.2.5.2 Tunneling & Jack UpCCOPL57922 | Trench Excavation | Bedding | C-56-01HG-CME09-1080 | C-56-01HG-CME09-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.5.2 Tunneling & Jack UpCCOPL57922 | P2543-R01-Oct24..4.3.1.2.3.12.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57932 | Bedding | Lowering | C-56-01HG-CME09-1090 | C-56-01HG-CME09-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57932 | P2543-R01-Oct24..4.3.1.2.3.12.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57932 | Lowering | Section Tie-in Welding | C-56-01HG-CME09-1100 | C-56-01HG-CME09-1110 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57932 | P2543-R01-Oct24..4.3.1.2.3.12.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57932 | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-01HG-CME09-1110 | C-56-01HG-CME09-1120 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57932 | P2543-R01-Oct24..4.3.1.2.3.12.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57932 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-01HG-CME09-1120 | C-56-01HG-CME09-1130 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57932 | P2543-R01-Oct24..4.3.1.2.3.12.2.5.4 HydrotestingCCOPL57942 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-01HG-CME09-1130 | C-56-01HG-CME09-1140 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.5.4 HydrotestingCCOPL57942 | P2543-R01-Oct24..4.3.1.2.3.12.2.5.5 Re-Instatement of Entry & Exit PitCCOPL57952 | Holiday Testing | Padding & Back Filling | C-56-01HG-CME09-1140 | C-56-01HG-CME09-1150 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.3.12.1.38 Pipe Lowering & Tie-in / NDT from KP 21.3 to HGCPCCOPL56237.2 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 9 | Section Tie-in Welding | C-PER-1430 | C-56-01HG-PL-ME-5010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 9 | Cleaning & Gauging | C-PER-1430 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.3.12.1.40 CP Works from KP 21.3 to HGCPCCOP56EL23.2 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 9 | Installation of Test Post for Crossing | C-PER-1430 | C-56-01HG-PL-CA-5420 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.3.12.3.2 Telecommunication Works from KP 21.3 t CCOP56IC21.2 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 9 | FO - Cable Pulling/ Laying | C-PER-1430 | C-56-01HG-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.3.12.1.36 Berming from BVS-01 to KP 21.3CCOPL56232.1 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 9 | Gatch Laying & Levelling | C-PER-1430 | C-56-01HG-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 9 | Precommissioning | C-PER-1430 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.3.12.1.44 Berming from KP 21.3 to HGCPCCOPL56232.2 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 9 | Gatch Laying & Levelling | C-PER-1430 | C-56-01HG-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 9 | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-PER-1430 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56922 | P2543-R01-Oct24..4.3.1.2.2.12.2.2.2 Tunneling & Jack UpCCOPL57222 | Trench Excavation | Bedding | C-56-HC01-CME10-1090 | C-56-HC01-CME10-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.2.2 Tunneling & Jack UpCCOPL57222 | P2543-R01-Oct24..4.3.1.2.2.12.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57232 | Bedding | Lowering | C-56-HC01-CME10-1100 | C-56-HC01-CME10-1110 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57232 | P2543-R01-Oct24..4.3.1.2.2.12.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57232 | Lowering | Section Tie-in Welding | C-56-HC01-CME10-1110 | C-56-HC01-CME10-1120 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57232 | P2543-R01-Oct24..4.3.1.2.2.12.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57232 | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME10-1120 | C-56-HC01-CME10-1130 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57232 | P2543-R01-Oct24..4.3.1.2.2.12.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57232 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME10-1130 | C-56-HC01-CME10-1140 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57232 | P2543-R01-Oct24..4.3.1.2.2.12.2.2.4 HydrotestingCCOPL57242 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME10-1140 | C-56-HC01-CME10-1150 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.2.4 HydrotestingCCOPL57242 | P2543-R01-Oct24..4.3.1.2.2.12.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57252 | Holiday Testing | Padding & Back Filling | C-56-HC01-CME10-1150 | C-56-HC01-CME10-1160 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Lowering & Welding of Carrier Pipe | Installation of Test Post for Crossing | C-56-HC01-CNH02-1070 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Lowering & Welding of Carrier Pipe | FO - Cable Pulling/ Laying | C-56-HC01-CNH02-1070 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Lowering & Welding of Carrier Pipe | Cleaning & Gauging | C-56-HC01-CNH02-1070 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Lowering & Welding of Carrier Pipe | Installation of Test Post for Crossing | C-56-HC01-CNH02-1070 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Lowering & Welding of Carrier Pipe | FO - Cable Pulling/ Laying | C-56-HC01-CNH02-1070 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Lowering & Welding of Carrier Pipe | Gatch Laying & Levelling | C-56-HC01-CNH02-1070 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Lowering & Welding of Carrier Pipe | Precommissioning | C-56-HC01-CNH02-1070 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Lowering & Welding of Carrier Pipe | Gatch Laying & Levelling | C-56-HC01-CNH02-1070 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56902 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Lowering & Welding of Carrier Pipe | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CNH02-1070 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 6 | Section Tie-in Welding | C-PER-1400 | C-56-HC01-PL-ME-5010 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 6 | Installation of Test Post for Crossing | C-PER-1400 | C-56-HC01-PL-CA-5220 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 6 | FO - Cable Pulling/ Laying | C-PER-1400 | C-56-HC01-PL-TE-8200 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 6 | Cleaning & Gauging | C-PER-1400 | C-56-HC01-PL-ME-7400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 6 | Installation of Test Post for Crossing | C-PER-1400 | C-56-HC01-PL-CA-5400 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 6 | FO - Cable Pulling/ Laying | C-PER-1400 | C-56-HC01-PL-TE-8400 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 6 | Gatch Laying & Levelling | C-PER-1400 | C-56-HC01-PL-CI-6800 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 6 | Precommissioning | C-PER-1400 | PRECOM-56-HGHC-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 6 | Gatch Laying & Levelling | C-PER-1400 | C-56-HC01-PL-CI-7000 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 6 | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-PER-1400 | ML1579-E03 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Sheet Piling for Driving & Receiving Pit | Section Tie-in Welding | C-56-HC01-CNH01-1000 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Sheet Piling for Driving & Receiving Pit | Installation of Test Post for Crossing | C-56-HC01-CNH01-1000 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Sheet Piling for Driving & Receiving Pit | FO - Cable Pulling/ Laying | C-56-HC01-CNH01-1000 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Sheet Piling for Driving & Receiving Pit | Cleaning & Gauging | C-56-HC01-CNH01-1000 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Sheet Piling for Driving & Receiving Pit | Installation of Test Post for Crossing | C-56-HC01-CNH01-1000 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Sheet Piling for Driving & Receiving Pit | FO - Cable Pulling/ Laying | C-56-HC01-CNH01-1000 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Sheet Piling for Driving & Receiving Pit | Gatch Laying & Levelling | C-56-HC01-CNH01-1000 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Sheet Piling for Driving & Receiving Pit | Precommissioning | C-56-HC01-CNH01-1000 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Sheet Piling for Driving & Receiving Pit | Gatch Laying & Levelling | C-56-HC01-CNH01-1000 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56900 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Sheet Piling for Driving & Receiving Pit | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-56-HC01-CNH01-1000 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56918 | P2543-R01-Oct24..4.3.1.2.2.12.2.3.2 Tunneling & Jack UpCCOPL57882 | Trench Excavation | Bedding | C-56-HC01-CME10-1170 | C-56-HC01-CME10-1180 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.3.2 Tunneling & Jack UpCCOPL57882 | P2543-R01-Oct24..4.3.1.2.2.12.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57892 | Bedding | Lowering | C-56-HC01-CME10-1180 | C-56-HC01-CME10-1190 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57892 | P2543-R01-Oct24..4.3.1.2.2.12.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57892 | Lowering | Section Tie-in Welding | C-56-HC01-CME10-1190 | C-56-HC01-CME10-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57892 | P2543-R01-Oct24..4.3.1.2.2.12.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57892 | Section Tie-in Welding | NDT (Tie-in Joint) | C-56-HC01-CME10-1200 | C-56-HC01-CME10-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57892 | P2543-R01-Oct24..4.3.1.2.2.12.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57892 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-56-HC01-CME10-1210 | C-56-HC01-CME10-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57892 | P2543-R01-Oct24..4.3.1.2.2.12.2.3.4 HydrotestingCCOPL57902 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-56-HC01-CME10-1220 | C-56-HC01-CME10-1230 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.3.4 HydrotestingCCOPL57902 | P2543-R01-Oct24..4.3.1.2.2.12.2.3.5 Re-Instatement of Entry & Exit PitCCOPL57912 | Holiday Testing | Padding & Back Filling | C-56-HC01-CME10-1230 | C-56-HC01-CME10-1240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.4.1.25 Pipe Lowering & Tie-in / NDT from KP 6 to KP 12.6CCOPL56212.2 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 4 | Section Tie-in Welding | C-PER-1380 | C-56-HC01-PL-ME-5010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 4 | Installation of Test Post for Crossing | C-PER-1380 | C-56-HC01-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.3.1 Telecommunication Works from Habshan CCOP56IC20.1 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 4 | FO - Cable Pulling/ Laying | C-PER-1380 | C-56-HC01-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 4 | Cleaning & Gauging | C-PER-1380 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.4.1.34 CP Works from KP 6 to KP 12.6CCOP56EL21.2 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 4 | Installation of Test Post for Crossing | C-PER-1380 | C-56-HC01-PL-CA-5400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.3.2 Telecommunication Works from KP 6 to KCCOP56IC20.2 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 4 | FO - Cable Pulling/ Laying | C-PER-1380 | C-56-HC01-PL-TE-8400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.4.1.23 Berming from Habshan complex to KP 6CCOPL56218.1 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 4 | Gatch Laying & Levelling | C-PER-1380 | C-56-HC01-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.2.2.3.1 Pre-commissioningCPCPL56228 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 4 | Precommissioning | C-PER-1380 | PRECOM-56-HGHC-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.2.2.12.4.1.36 Berming from KP 6 to KP 12.6CCOPL56218.2 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 4 | Gatch Laying & Levelling | C-PER-1380 | C-56-HC01-PL-CI-7000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 4 | Complete construction of NDRC Road and assets crossings - 56" Sales Gas Pipeline | C-PER-1380 | ML1579-E03 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.5.1 Entry & Exit Pit ConstructionCCOPL52934 | P2543-R01-Oct24..4.3.1.3.8.21.2.5.2 Tunneling & Jack UpCCOPL57642 | Trench Excavation | Bedding | C-52-0102-CME06-1090 | C-52-0102-CME06-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.5.2 Tunneling & Jack UpCCOPL57642 | P2543-R01-Oct24..4.3.1.3.8.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57652 | Bedding | Lowering | C-52-0102-CME06-1100 | C-52-0102-CME06-1110 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57652 | P2543-R01-Oct24..4.3.1.3.8.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57652 | Lowering | Section Tie-in Welding | C-52-0102-CME06-1110 | C-52-0102-CME06-1120 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57652 | P2543-R01-Oct24..4.3.1.3.8.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57652 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0102-CME06-1120 | C-52-0102-CME06-1130 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57652 | P2543-R01-Oct24..4.3.1.3.8.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57652 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0102-CME06-1130 | C-52-0102-CME06-1140 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.5.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57652 | P2543-R01-Oct24..4.3.1.3.8.21.2.5.4 HydrotestingCCOPL57662 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0102-CME06-1140 | C-52-0102-CME06-1150 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.5.4 HydrotestingCCOPL57662 | P2543-R01-Oct24..4.3.1.3.8.21.2.5.5 Re-Instatement of Entry & Exit PitCCOPL57672 | Holiday Testing | Padding & Back Filling | C-52-0102-CME06-1150 | C-52-0102-CME06-1160 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 6 | Cleaning & Gauging | C-PER-1070 | C-52-0102-PL-ME-7400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 6 | Gatch Laying & Levelling | C-PER-1070 | C-52-0102-PL-CI-6800 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.6.8.1 Pre-commissioning from BVS-01 to BVS-02CPCPL52327.6 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 6 | Pre-commissioning from BVS-02 to BVS-01 | C-PER-1070 | PRECOM-52-0201-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 6 | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-PER-1070 | ML1679-E13 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52950 | P2543-R01-Oct24..4.3.1.3.15.21.2.1.2 Tunneling & Jack UpCCOPL57842 | Trench Excavation | Bedding | C-52-0203-CME04-1080 | C-52-0203-CME04-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.1.2 Tunneling & Jack UpCCOPL57842 | P2543-R01-Oct24..4.3.1.3.15.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57852 | Bedding | Lowering | C-52-0203-CME04-1090 | C-52-0203-CME04-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57852 | P2543-R01-Oct24..4.3.1.3.15.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57852 | Lowering | Section Tie-in Welding | C-52-0203-CME04-1100 | C-52-0203-CME04-1110 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57852 | P2543-R01-Oct24..4.3.1.3.15.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57852 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0203-CME04-1110 | C-52-0203-CME04-1120 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57852 | P2543-R01-Oct24..4.3.1.3.15.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57852 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0203-CME04-1120 | C-52-0203-CME04-1130 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57852 | P2543-R01-Oct24..4.3.1.3.15.21.2.1.4 HydrotestingCCOPL57862 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0203-CME04-1130 | C-52-0203-CME04-1140 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.1.4 HydrotestingCCOPL57862 | P2543-R01-Oct24..4.3.1.3.15.21.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57872 | Holiday Testing | Padding & Back Filling | C-52-0203-CME04-1140 | C-52-0203-CME04-1150 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Stringing (BVS-02 to BVS-03) | Section Tie-in Welding | C-52-0203-PL-ME-2800 | C-52-0203-PL-ME-4810 | SF | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | Stringing (BVS-02 to BVS-03) | Installation of Test Post for Crossing | C-52-0203-PL-ME-2800 | C-52-0203-PL-CA-5220 | SF | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | Stringing (BVS-02 to BVS-03) | FO - Cable Pulling/ Laying | C-52-0203-PL-ME-2800 | C-52-0203-PL-TE-8200 | SF | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Stringing (BVS-02 to BVS-03) | Cleaning & Gauging | C-52-0203-PL-ME-2800 | C-52-0203-PL-ME-7400 | SS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | Stringing (BVS-02 to BVS-03) | Gatch Laying & Levelling | C-52-0203-PL-ME-2800 | C-52-0203-PL-CI-6800 | SF | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | P2543-R01-Oct24..4.3.2.3.5.8.2 Pre-commissioning from BVS-02 to BVS-03CPCPL52327.5 | Stringing (BVS-02 to BVS-03) | Pre-commissioning from BVS-02 to BVS-03 | C-52-0203-PL-ME-2800 | PRECOM-52-0203-1000 | SS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | Stringing (BVS-02 to BVS-03) | Padding | C-52-0203-PL-ME-2800 | C-52-0203-PL-CI-6000 | SF | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Stringing (BVS-02 to BVS-03) | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-0203-PL-ME-2800 | ML1679-E13 | SS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.15.21.1.13 Pipe Lowering & Tie-in / NDTCCOPL52372 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 12 | Section Tie-in Welding | C-PER-1130 | C-52-0203-PL-ME-4810 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 12 | Installation of Test Post for Crossing | C-PER-1130 | C-52-0203-PL-CA-5220 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 12 | FO - Cable Pulling/ Laying | C-PER-1130 | C-52-0203-PL-TE-8200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 12 | Cleaning & Gauging | C-PER-1130 | C-52-0203-PL-ME-7400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.15.21.1.19 BermingCCOPL52367 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 12 | Gatch Laying & Levelling | C-PER-1130 | C-52-0203-PL-CI-6800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.5.8.2 Pre-commissioning from BVS-02 to BVS-03CPCPL52327.5 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 12 | Pre-commissioning from BVS-02 to BVS-03 | C-PER-1130 | PRECOM-52-0203-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 12 | Padding | C-PER-1130 | C-52-0203-PL-CI-6000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 12 | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-PER-1130 | ML1679-E13 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52952 | P2543-R01-Oct24..4.3.1.3.16.21.2.1.2 Tunneling & Jack UpCCOPL57482 | Trench Excavation | Bedding | C-52-0304-CME06-1090 | C-52-0304-CME06-1100 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.1.2 Tunneling & Jack UpCCOPL57482 | P2543-R01-Oct24..4.3.1.3.16.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57492 | Bedding | Lowering | C-52-0304-CME06-1100 | C-52-0304-CME06-1110 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57492 | P2543-R01-Oct24..4.3.1.3.16.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57492 | Lowering | Section Tie-in Welding | C-52-0304-CME06-1110 | C-52-0304-CME06-1120 | FS | Completed | In Progress | 35
P2543-R01-Oct24..4.3.1.3.16.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57492 | P2543-R01-Oct24..4.3.1.3.16.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57492 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CME06-1120 | C-52-0304-CME06-1130 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57492 | P2543-R01-Oct24..4.3.1.3.16.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57492 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME06-1130 | C-52-0304-CME06-1140 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57492 | P2543-R01-Oct24..4.3.1.3.16.21.2.1.4 HydrotestingCCOPL57502 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CME06-1140 | C-52-0304-CME06-1150 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.1.4 HydrotestingCCOPL57502 | P2543-R01-Oct24..4.3.1.3.16.21.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57512 | Holiday Testing | Padding & Back Filling | C-52-0304-CME06-1150 | C-52-0304-CME06-1160 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52954 | P2543-R01-Oct24..4.3.1.3.16.21.2.2.2 Tunneling & Jack UpCCOPL57142 | Trench Excavation | Bedding | C-52-0304-CME06-1170 | C-52-0304-CME06-1180 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.2.2 Tunneling & Jack UpCCOPL57142 | P2543-R01-Oct24..4.3.1.3.16.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL5715 | Bedding | Lowering | C-52-0304-CME06-1180 | C-52-0304-CME06-1190 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL5715 | P2543-R01-Oct24..4.3.1.3.16.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL5715 | Lowering | Section Tie-in Welding | C-52-0304-CME06-1190 | C-52-0304-CME06-1200 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL5715 | P2543-R01-Oct24..4.3.1.3.16.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL5715 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CME06-1200 | C-52-0304-CME06-1210 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL5715 | P2543-R01-Oct24..4.3.1.3.16.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL5715 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME06-1210 | C-52-0304-CME06-1220 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL5715 | P2543-R01-Oct24..4.3.1.3.16.21.2.2.4 HydrotestingCCOPL57162 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CME06-1220 | C-52-0304-CME06-1230 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.2.4 HydrotestingCCOPL57162 | P2543-R01-Oct24..4.3.1.3.16.21.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57172 | Holiday Testing | Padding & Back Filling | C-52-0304-CME06-1230 | C-52-0304-CME06-1240 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52956 | P2543-R01-Oct24..4.3.1.3.16.21.2.3.2 Tunneling & Jack UpCCOPL57802 | Trench Excavation | Bedding | C-52-0304-CME06-1250 | C-52-0304-CME06-1260 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.3.2 Tunneling & Jack UpCCOPL57802 | P2543-R01-Oct24..4.3.1.3.16.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57812 | Bedding | Lowering | C-52-0304-CME06-1260 | C-52-0304-CME06-1270 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57812 | P2543-R01-Oct24..4.3.1.3.16.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57812 | Lowering | Section Tie-in Welding | C-52-0304-CME06-1270 | C-52-0304-CME06-1280 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57812 | P2543-R01-Oct24..4.3.1.3.16.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57812 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0304-CME06-1280 | C-52-0304-CME06-1290 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57812 | P2543-R01-Oct24..4.3.1.3.16.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57812 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0304-CME06-1290 | C-52-0304-CME06-1300 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.3.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57812 | P2543-R01-Oct24..4.3.1.3.16.21.2.3.4 HydrotestingCCOPL57822 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0304-CME06-1300 | C-52-0304-CME06-1310 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.3.4 HydrotestingCCOPL57822 | P2543-R01-Oct24..4.3.1.3.16.21.2.3.5 Re-Instatement of Entry & Exit PitCCOPL57832 | Holiday Testing | Padding & Back Filling | C-52-0304-CME06-1310 | C-52-0304-CME06-1320 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Stringing (BVS-03 to BVS-04) | Section Tie-in Welding | C-52-0304-PL-ME-2800 | C-52-0304-PL-ME-4810 | SF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Stringing (BVS-03 to BVS-04) | Installation of Test Post for Crossing | C-52-0304-PL-ME-2800 | C-52-0304-PL-CA-5220 | SF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Stringing (BVS-03 to BVS-04) | FO - Cable Pulling/ Laying | C-52-0304-PL-ME-2800 | C-52-0304-PL-TE-8200 | SF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Stringing (BVS-03 to BVS-04) | Cleaning & Gauging | C-52-0304-PL-ME-2800 | C-52-0304-PL-ME-7400 | SS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Stringing (BVS-03 to BVS-04) | Gatch Laying & Levelling | C-52-0304-PL-ME-2800 | C-52-0304-PL-CI-6800 | SF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | Stringing (BVS-03 to BVS-04) | Pre-commissioning from BVS-03 to BVS-04 | C-52-0304-PL-ME-2800 | PRECOM-52-0304-1000 | SS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Stringing (BVS-03 to BVS-04) | Padding | C-52-0304-PL-ME-2800 | C-52-0304-PL-CI-6000 | SF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Stringing (BVS-03 to BVS-04) | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-0304-PL-ME-2800 | ML1679-E13 | SS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13 | Section Tie-in Welding | C-PER-1140 | C-52-0304-PL-ME-4810 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13 | Installation of Test Post for Crossing | C-PER-1140 | C-52-0304-PL-CA-5220 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13 | FO - Cable Pulling/ Laying | C-PER-1140 | C-52-0304-PL-TE-8200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13 | Cleaning & Gauging | C-PER-1140 | C-52-0304-PL-ME-7400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13 | Gatch Laying & Levelling | C-PER-1140 | C-52-0304-PL-CI-6800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13 | Pre-commissioning from BVS-03 to BVS-04 | C-PER-1140 | PRECOM-52-0304-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13 | Padding | C-PER-1140 | C-52-0304-PL-CI-6000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13 | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-PER-1140 | ML1679-E13 | FS | Completed | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Receive at Site - Hot Bends for 52" Pipeline (100% to total Qty) | Section Tie-in Welding | ML1459-D12 | C-52-0304-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Receive at Site - Hot Bends for 52" Pipeline (100% to total Qty) | Installation of Test Post for Crossing | ML1459-D12 | C-52-0304-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Receive at Site - Hot Bends for 52" Pipeline (100% to total Qty) | FO - Cable Pulling/ Laying | ML1459-D12 | C-52-0304-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Receive at Site - Hot Bends for 52" Pipeline (100% to total Qty) | Cleaning & Gauging | ML1459-D12 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Receive at Site - Hot Bends for 52" Pipeline (100% to total Qty) | Gatch Laying & Levelling | ML1459-D12 | C-52-0304-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | Receive at Site - Hot Bends for 52" Pipeline (100% to total Qty) | Pre-commissioning from BVS-03 to BVS-04 | ML1459-D12 | PRECOM-52-0304-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Receive at Site - Hot Bends for 52" Pipeline (100% to total Qty) | Padding | ML1459-D12 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receive at Site - Hot Bends for 52" Pipeline (100% to total Qty) | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | ML1459-D12 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13A | Section Tie-in Welding | C-PER-1150 | C-52-0304-PL-ME-4810 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13A | Installation of Test Post for Crossing | C-PER-1150 | C-52-0304-PL-CA-5220 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13A | FO - Cable Pulling/ Laying | C-PER-1150 | C-52-0304-PL-TE-8200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13A | Cleaning & Gauging | C-PER-1150 | C-52-0304-PL-ME-7400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13A | Gatch Laying & Levelling | C-PER-1150 | C-52-0304-PL-CI-6800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13A | Pre-commissioning from BVS-03 to BVS-04 | C-PER-1150 | PRECOM-52-0304-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13A | Padding | C-PER-1150 | C-52-0304-PL-CI-6000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 13A | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-PER-1150 | ML1679-E13 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.16.21.1.18 Pipe Lowering & Tie-in / NDTCCOPL52400 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 14 | Section Tie-in Welding | C-PER-1160 | C-52-0304-PL-ME-4810 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 14 | Installation of Test Post for Crossing | C-PER-1160 | C-52-0304-PL-CA-5220 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 14 | FO - Cable Pulling/ Laying | C-PER-1160 | C-52-0304-PL-TE-8200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 14 | Cleaning & Gauging | C-PER-1160 | C-52-0304-PL-ME-7400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 14 | Gatch Laying & Levelling | C-PER-1160 | C-52-0304-PL-CI-6800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.4.8.3 Pre-commissioning from BVS-03 to BVS-04CPCPL52327.4 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 14 | Pre-commissioning from BVS-03 to BVS-04 | C-PER-1160 | PRECOM-52-0304-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 14 | Padding | C-PER-1160 | C-52-0304-PL-CI-6000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 14 | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-PER-1160 | ML1679-E13 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52920 | P2543-R01-Oct24..4.3.1.3.18.21.2.1.2 Tunneling & Jack UpCCOPL57022 | Trench Excavation | Bedding | C-52-0506-CME25-2000 | C-52-0506-CME25-2010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.2.1.2 Tunneling & Jack UpCCOPL57022 | P2543-R01-Oct24..4.3.1.3.18.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57032 | Bedding | Lowering | C-52-0506-CME25-2010 | C-52-0506-CME25-2020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57032 | P2543-R01-Oct24..4.3.1.3.18.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57032 | Lowering | Section Tie-in Welding | C-52-0506-CME25-2020 | C-52-0506-CME25-2030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57032 | P2543-R01-Oct24..4.3.1.3.18.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57032 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CME25-2030 | C-52-0506-CME25-2040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57032 | P2543-R01-Oct24..4.3.1.3.18.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57032 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME25-2040 | C-52-0506-CME25-2050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57032 | P2543-R01-Oct24..4.3.1.3.18.21.2.1.4 HydrotestingCCOPL57042 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CME25-2050 | C-52-0506-CME25-2060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.2.1.4 HydrotestingCCOPL57042 | P2543-R01-Oct24..4.3.1.3.18.21.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57052 | Holiday Testing | Padding & Back Filling | C-52-0506-CME25-2060 | C-52-0506-CME25-2070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.2.2.1 Entry & Exit Pit ConstructionCCOPL56972 | P2543-R01-Oct24..4.3.1.3.18.21.2.2.2 Tunneling & Jack UpCCOPL56982 | Trench Excavation | Bedding | C-52-0506-CME28-1080 | C-52-0506-CME28-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.2.2.2 Tunneling & Jack UpCCOPL56982 | P2543-R01-Oct24..4.3.1.3.18.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL56992 | Bedding | Lowering | C-52-0506-CME28-1090 | C-52-0506-CME28-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL56992 | P2543-R01-Oct24..4.3.1.3.18.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL56992 | Lowering | Section Tie-in Welding | C-52-0506-CME28-1100 | C-52-0506-CME28-1110 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL56992 | P2543-R01-Oct24..4.3.1.3.18.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL56992 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0506-CME28-1110 | C-52-0506-CME28-1120 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL56992 | P2543-R01-Oct24..4.3.1.3.18.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL56992 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0506-CME28-1120 | C-52-0506-CME28-1130 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL56992 | P2543-R01-Oct24..4.3.1.3.18.21.2.2.4 HydrotestingCCOPL57002 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0506-CME28-1130 | C-52-0506-CME28-1140 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.18.21.2.2.4 HydrotestingCCOPL57002 | P2543-R01-Oct24..4.3.1.3.18.21.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57012 | Holiday Testing | Padding & Back Filling | C-52-0506-CME28-1140 | C-52-0506-CME28-1150 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.1.1 Entry & Exit Pit ConstructionCCOPL52964 | P2543-R01-Oct24..4.3.1.3.19.8.2.1.2 Tunneling & Jack UpCCOPL52924 | Trench Excavation | Bedding | C-52-06CR-CME29-1080 | C-52-06CR-CME29-1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.1.2 Tunneling & Jack UpCCOPL52924 | P2543-R01-Oct24..4.3.1.3.19.8.2.1.3 Pipe Lowering, Welding & NDTCCOPL52974 | Bedding | Lowering | C-52-06CR-CME29-1090 | C-52-06CR-CME29-1100 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.1.3 Pipe Lowering, Welding & NDTCCOPL52974 | P2543-R01-Oct24..4.3.1.3.19.8.2.1.3 Pipe Lowering, Welding & NDTCCOPL52974 | Lowering | Section Tie-in Welding | C-52-06CR-CME29-1100 | C-52-06CR-CME29-1110 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.1.3 Pipe Lowering, Welding & NDTCCOPL52974 | P2543-R01-Oct24..4.3.1.3.19.8.2.1.3 Pipe Lowering, Welding & NDTCCOPL52974 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-06CR-CME29-1110 | C-52-06CR-CME29-1120 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.1.3 Pipe Lowering, Welding & NDTCCOPL52974 | P2543-R01-Oct24..4.3.1.3.19.8.2.1.3 Pipe Lowering, Welding & NDTCCOPL52974 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-06CR-CME29-1120 | C-52-06CR-CME29-1130 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.1.3 Pipe Lowering, Welding & NDTCCOPL52974 | P2543-R01-Oct24..4.3.1.3.19.8.2.1.4 HydrotestingCCOPL52984 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-06CR-CME29-1130 | C-52-06CR-CME29-1140 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.1.4 HydrotestingCCOPL52984 | P2543-R01-Oct24..4.3.1.3.19.8.2.1.5 Re-Instatement of Entry & Exit PitCCOPL52994 | Holiday Testing | Padding & Back Filling | C-52-06CR-CME29-1140 | C-52-06CR-CME29-1150 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 Tunneling & Jack UpCCOPL58202 | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Jacking of MTBM & RC Sleeves | Section Tie-in Welding | C-52-0102-CNH10-1200 | C-52-0506-PL-ME-4810 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 Tunneling & Jack UpCCOPL58202 | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Jacking of MTBM & RC Sleeves | Installation of Test Post for Crossing | C-52-0102-CNH10-1200 | C-52-0506-PL-CA-5220 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 Tunneling & Jack UpCCOPL58202 | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Jacking of MTBM & RC Sleeves | FO - Cable Pulling/ Laying | C-52-0102-CNH10-1200 | C-52-0506-PL-TE-8200 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 Tunneling & Jack UpCCOPL58202 | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Jacking of MTBM & RC Sleeves | Cleaning & Gauging | C-52-0102-CNH10-1200 | C-52-0506-PL-ME-7400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 Tunneling & Jack UpCCOPL58202 | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Jacking of MTBM & RC Sleeves | Gatch Laying & Levelling | C-52-0102-CNH10-1200 | C-52-0506-PL-CI-6800 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 Tunneling & Jack UpCCOPL58202 | P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | Jacking of MTBM & RC Sleeves | Pre-commissioning from BVS-05 to BVS-06 | C-52-0102-CNH10-1200 | PRECOM-52-0506-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 Tunneling & Jack UpCCOPL58202 | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Jacking of MTBM & RC Sleeves | Padding | C-52-0102-CNH10-1200 | C-52-0506-PL-CI-6000 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 Tunneling & Jack UpCCOPL58202 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Jacking of MTBM & RC Sleeves | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-0102-CNH10-1200 | ML1679-E13 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 25A | Section Tie-in Welding | C-PER-1280 | C-52-0506-PL-ME-4810 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 25A | Installation of Test Post for Crossing | C-PER-1280 | C-52-0506-PL-CA-5220 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 25A | FO - Cable Pulling/ Laying | C-PER-1280 | C-52-0506-PL-TE-8200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 25A | Cleaning & Gauging | C-PER-1280 | C-52-0506-PL-ME-7400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 25A | Gatch Laying & Levelling | C-PER-1280 | C-52-0506-PL-CI-6800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 25A | Pre-commissioning from BVS-05 to BVS-06 | C-PER-1280 | PRECOM-52-0506-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 25A | Padding | C-PER-1280 | C-52-0506-PL-CI-6000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 25A | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-PER-1280 | ML1679-E13 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 28 | Section Tie-in Welding | C-PER-1310 | C-52-0506-PL-ME-4810 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 28 | Installation of Test Post for Crossing | C-PER-1310 | C-52-0506-PL-CA-5220 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 28 | FO - Cable Pulling/ Laying | C-PER-1310 | C-52-0506-PL-TE-8200 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 28 | Cleaning & Gauging | C-PER-1310 | C-52-0506-PL-ME-7400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 28 | Gatch Laying & Levelling | C-PER-1310 | C-52-0506-PL-CI-6800 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 28 | Pre-commissioning from BVS-05 to BVS-06 | C-PER-1310 | PRECOM-52-0506-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 28 | Padding | C-PER-1310 | C-52-0506-PL-CI-6000 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 28 | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-PER-1310 | ML1679-E13 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 Tunneling & Jack UpCCOPL58302 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.2 Tunneling & Jack UpCCOPL56932 | Jacking of MTBM & RC Sleeves | Jacking of MTBM & RC Sleeves | C-52-0405-CNH20-1200 | C-52-06CR-CNM31-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 Tunneling & Jack UpCCOPL58302 | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Jacking of MTBM & RC Sleeves | Section Tie-in Welding | C-52-0405-CNH20-1200 | C-52-06CR-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 Tunneling & Jack UpCCOPL58302 | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Jacking of MTBM & RC Sleeves | Installation of Test Post for Crossing | C-52-0405-CNH20-1200 | C-52-06CR-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 Tunneling & Jack UpCCOPL58302 | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Jacking of MTBM & RC Sleeves | FO - Cable Pulling/ Laying | C-52-0405-CNH20-1200 | C-52-06CR-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 Tunneling & Jack UpCCOPL58302 | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Jacking of MTBM & RC Sleeves | Cleaning & Gauging | C-52-0405-CNH20-1200 | C-52-06CR-PL-ME-7400 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 Tunneling & Jack UpCCOPL58302 | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Jacking of MTBM & RC Sleeves | Gatch Laying & Levelling | C-52-0405-CNH20-1200 | C-52-06CR-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 Tunneling & Jack UpCCOPL58302 | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | Jacking of MTBM & RC Sleeves | Pre-commissioning from BVS-06 to CRS Sweihan | C-52-0405-CNH20-1200 | PRECOM-52-06CR-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 Tunneling & Jack UpCCOPL58302 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Jacking of MTBM & RC Sleeves | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-52-0405-CNH20-1200 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.19.8.2.3.2 Tunneling & Jack UpCCOPL56932 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 29 | Jacking of MTBM & RC Sleeves | C-PER-1320 | C-52-06CR-CNM31-1200 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.19.8.1.20 Pipe Lowering & Tie-in / NDTCCOPL52484 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 29 | Section Tie-in Welding | C-PER-1320 | C-52-06CR-PL-ME-4810 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.19.8.3.2.1 CP Works (for Crossings)CCOP52EL50 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 29 | Installation of Test Post for Crossing | C-PER-1320 | C-52-06CR-PL-CA-5220 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.19.8.4.1 Telecom Works along Pipeline CCOP52IC30 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 29 | FO - Cable Pulling/ Laying | C-PER-1320 | C-52-06CR-PL-TE-8200 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.1.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52481 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 29 | Cleaning & Gauging | C-PER-1320 | C-52-06CR-PL-ME-7400 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.19.8.1.25 BermingCCOPL52479 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 29 | Gatch Laying & Levelling | C-PER-1320 | C-52-06CR-PL-CI-6800 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.1.8.2 Pre-commissioning from BVS-06 to CRS SweihanCPCPL52327.1 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 29 | Pre-commissioning from BVS-06 to CRS Sweihan | C-PER-1320 | PRECOM-52-06CR-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 29 | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-PER-1320 | ML1679-E13 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57872 | P2543-R01-Oct24..4.3.1.3.15.21.1.18 PaddingCCOPL52358 | Padding & Back Filling | Padding | C-52-0203-CME04-1150 | C-52-0203-PL-CI-6000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.2.21.1.22.8 Crossing Mechanical (TX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | Trench Excavation | Trench Excavation | C-52-HG01-CME01-1000 | C-52-HG01-CME02-1000 | FS | Completed | Not Started | 30
P2543-R01-Oct24..4.3.1.3.2.21.1.22.9 Crossing Mechanical (TX-03) | P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | Trench Excavation | Trench Excavation | C-52-HG01-CME02-1000 | C-52-HG01-CME03-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.11 Pipe StringingCCOPL52329 | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | Stringing (BVS-01 to BVS-02) | Trench Excavation | C-52-0102-PL-ME-2800 | C-52-0102-CME01-1000 | FS | In Progress | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | Trench Excavation | Trench Excavation | C-52-0102-CME01-1000 | C-52-0102-CME02-1000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.16.2 Crossing Mechanical (TX-15) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | Trench Excavation | Trench Excavation | C-52-0102-CME02-1000 | C-52-0102-CME03-1000 | SS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.16.3 Crossing Mechanical (TX-16) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | Trench Excavation | Trench Excavation | C-52-0102-CME03-1000 | C-52-0102-CME04-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.16.4 Crossing Mechanical (TX-17) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | Trench Excavation | Trench Excavation | C-52-0102-CME04-1000 | C-52-0102-CME05-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.8 Pipe StringingCCOPL52357 | P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | Stringing (BVS-02 to BVS-03) | Trench Excavation | C-52-0203-PL-ME-2800 | C-52-0203-CME01-1000 | SS | Completed | Not Started | 3
P2543-R01-Oct24..4.3.1.3.15.21.1.15.3 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.15.21.1.15.4 Crossing Mechanical (TX-31A) | Trench Excavation | Trench Excavation | C-52-0203-CME01-1000 | C-52-0203-CME02-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.10 Pipe StringingCCOPL52385 | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | Stringing (BVS-03 to BVS-04) | Trench Excavation | C-52-0304-PL-ME-2800 | C-52-0304-CME01-1000 | FF | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | Trench Excavation | Trench Excavation | C-52-0304-CME01-1000 | C-52-0304-CME02-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.16 Crossing Mechanical (TX-32) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | Trench Excavation | Trench Excavation | C-52-0304-CME02-1000 | C-52-0304-CME03-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.17 Crossing Mechanical (TX-33) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.18 Crossing Mechanical (TX-34) | Trench Excavation | Trench Excavation | C-52-0304-CME03-1000 | C-52-0304-CME04-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.19 Crossing Mechanical (TX-35) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | Trench Excavation | Trench Excavation | C-52-0304-CME05-1000 | C-52-0304-CME06-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.20 Crossing Mechanical (TX-36) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | Trench Excavation | Trench Excavation | C-52-0304-CME06-1000 | C-52-0304-CME07-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.21 Crossing Mechanical (TX-37) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | Trench Excavation | Trench Excavation | C-52-0304-CME07-1000 | C-52-0304-CME08-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.22 Crossing Mechanical (TX-38,39) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | Trench Excavation | Trench Excavation | C-52-0304-CME08-1000 | C-52-0304-CME09-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.23 Crossing Mechanical (TX-40) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | Trench Excavation | Road Diversion & Trench Excavation | C-52-0304-CME09-1000 | C-52-0304-CME10-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.24 Crossing Mechanical (RX-14) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | Road Diversion & Trench Excavation | Trench Excavation | C-52-0304-CME10-1000 | C-52-0304-CME11-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.1.17.25 Crossing Mechanical (TX-41) | P2543-R01-Oct24..4.3.1.3.16.21.1.17.26 Crossing Mechanical (TX-42) | Trench Excavation | Trench Excavation | C-52-0304-CME11-1000 | C-52-0304-CME12-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.10 Pipe StringingCCOPL52413 | P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | Stringing (BVS-04 to BVS-05) | Trench Excavation | C-52-0405-PL-ME-2800 | C-52-0405-CME01-1000 | SS | In Progress | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.33 Crossing Mechanical (TX-43) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | Trench Excavation | Trench Excavation | C-52-0405-CME01-1000 | C-52-0405-CME02-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.34 Crossing Mechanical (TX-46) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | Trench Excavation | Trench Excavation | C-52-0405-CME02-1000 | C-52-0405-CME03-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.35 Crossing Mechanical (TX-47) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | Trench Excavation | Trench Excavation | C-52-0405-CME03-1000 | C-52-0405-CME04-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.36 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | Trench Excavation | Trench Excavation | C-52-0405-CME04-1000 | C-52-0405-CME05-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.37 Crossing Mechanical (TX-50) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | Trench Excavation | Trench Excavation | C-52-0405-CME05-1000 | C-52-0405-CME06-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.38 Crossing Mechanical (TX-52) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | Trench Excavation | Trench Excavation | C-52-0405-CME06-1000 | C-52-0405-CME07-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.1.18.39 Crossing Mechanical (TX-53) | P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | Trench Excavation | Trench Excavation | C-52-0405-CME07-1000 | C-52-0405-CME08-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.11 Pipe StringingCCOPL52441 | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | Stringing (BVS-05 to BVS-06) | Trench Excavation | C-52-0506-PL-ME-2800 | C-52-0506-CME01-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | Trench Excavation | Trench Excavation | C-52-0506-CME01-1000 | C-52-0506-CME02-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.11 Crossing Mechanical (TX-58) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | Trench Excavation | Trench Excavation | C-52-0506-CME02-1000 | C-52-0506-CME03-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.12 Crossing Mechanical (TX-59) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | Trench Excavation | Trench Excavation | C-52-0506-CME03-1000 | C-52-0506-CME04-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.13 Crossing Mechanical (TX-60) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | Trench Excavation | Trench Excavation | C-52-0506-CME04-1000 | C-52-0506-CME05-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.14 Crossing Mechanical (TX-61) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | Trench Excavation | Trench Excavation | C-52-0506-CME05-1000 | C-52-0506-CME06-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.15 Crossing Mechanical (TX-62) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | Trench Excavation | Trench Excavation | C-52-0506-CME06-1000 | C-52-0506-CME07-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.16 Crossing Mechanical (TX-63) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | Trench Excavation | Trench Excavation | C-52-0506-CME07-1000 | C-52-0506-CME08-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.17 Crossing Mechanical (TX-64) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | Trench Excavation | Trench Excavation | C-52-0506-CME08-1000 | C-52-0506-CME09-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.18 Crossing Mechanical (TX-65) | P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | Trench Excavation | Trench Excavation | C-52-0506-CME09-1000 | C-52-0506-CME10-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.15 Pipe StringingCCOPL52469 | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | Stringing (BVS-06 to SW CRS) | Trench Excavation | C-52-06CR-PL-ME-2800 | C-52-06CR-CME01-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | Trench Excavation | Trench Excavation | C-52-06CR-CME01-1000 | C-52-06CR-CME02-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.15 Crossing Mechanical (TX-74) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | Trench Excavation | Trench Excavation | C-52-06CR-CME02-1000 | C-52-06CR-CME03-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.16 Crossing Mechanical (TX-75) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | Trench Excavation | Trench Excavation | C-52-06CR-CME03-1000 | C-52-06CR-CME04-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.17 Crossing Mechanical (TX-76) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | Trench Excavation | Trench Excavation | C-52-06CR-CME04-1000 | C-52-06CR-CME05-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.18 Crossing Mechanical (TX-77) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | Trench Excavation | Trench Excavation | C-52-06CR-CME05-1000 | C-52-06CR-CME06-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.19 Crossing Mechanical (TX-78) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | Trench Excavation | Trench Excavation | C-52-06CR-CME06-1000 | C-52-06CR-CME07-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.20 Crossing Mechanical (TX-79) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | Trench Excavation | Trench Excavation | C-52-06CR-CME07-1000 | C-52-06CR-CME08-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.21 Crossing Mechanical (TX-80) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | Trench Excavation | Trench Excavation | C-52-06CR-CME08-1000 | C-52-06CR-CME09-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | Trench Excavation | Trench Excavation | C-52-06CR-CME09-1000 | C-52-06CR-CME10-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | Trench Excavation | Trench Excavation | C-52-06CR-CME10-1000 | C-52-06CR-CME11-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.24 Crossing Mechanical (TX-83) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | Trench Excavation | Trench Excavation | C-52-06CR-CME11-1000 | C-52-06CR-CME12-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | Trench Excavation | Trench Excavation | C-52-06CR-CME12-1000 | C-52-06CR-CME13-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | Trench Excavation | Trench Excavation | C-52-06CR-CME13-1000 | C-52-06CR-CME14-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.16 Pipe Stringing from BVS-01 to KP 21.3CCOPL56250.1 | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | Stringing (BVS-01 to KP 21.3) | Trench Excavation | C-56-01HG-PL-ME-2800 | C-56-01HG-CME01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | Trench Excavation | Trench Excavation | C-56-01HG-CME01-1000 | C-56-01HG-CME02-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.29 Crossing Mechanical (TX-25 to TX-27) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | Trench Excavation | Trench Excavation | C-56-01HG-CME02-1000 | C-56-01HG-CME03-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.30 Crossing Mechanical (TX-28 to TX-30) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | Trench Excavation | Trench Excavation | C-56-01HG-CME03-1000 | C-56-01HG-CME04-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.31 Crossing Mechanical (TX-31 to TX-33) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | Trench Excavation | Trench Excavation | C-56-01HG-CME04-1000 | C-56-01HG-CME05-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.32 Crossing Mechanical (TX-34 to TX-36) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | Trench Excavation | Trench Excavation | C-56-01HG-CME05-1000 | C-56-01HG-CME06-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.33 Crossing Mechanical (TX-37 to TX-39) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | Trench Excavation | Trench Excavation | C-56-01HG-CME06-1000 | C-56-01HG-CME07-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.34 Crossing Mechanical (TX-40 to TX-42) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | Trench Excavation | Trench Excavation | C-56-01HG-CME07-1000 | C-56-01HG-CME08-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.35 Crossing Mechanical (TX-43 to TX-45) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | Trench Excavation | Trench Excavation | C-56-01HG-CME08-1000 | C-56-01HG-CME09-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.1.23.36 Crossing Mechanical (TX-46,47) | P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | Trench Excavation | Trench Excavation | C-56-01HG-CME09-1000 | C-56-01HG-CME10-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.16.5 Crossing Mechanical (TX-23) | P2543-R01-Oct24..4.3.1.3.8.21.2.5.1 Entry & Exit Pit ConstructionCCOPL52934 | Trench Excavation | Trench Excavation | C-52-0102-CME05-1000 | C-52-0102-CME06-1090 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.12.1 Entry & Exit Pit ConstructionCCOPL52948 | P2543-R01-Oct24..4.3.1.3.15.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52950 | Trench Excavation | Trench Excavation | C-52-0203-CME04-1000 | C-52-0203-CME04-1080 | FS | Completed | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52952 | P2543-R01-Oct24..4.3.1.3.16.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52954 | Trench Excavation | Trench Excavation | C-52-0304-CME06-1090 | C-52-0304-CME06-1170 | FS | Completed | In Progress | 1
P2543-R01-Oct24..4.3.1.3.16.21.2.2.1 Entry & Exit Pit ConstructionCCOPL52954 | P2543-R01-Oct24..4.3.1.3.16.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52956 | Trench Excavation | Trench Excavation | C-52-0304-CME06-1170 | C-52-0304-CME06-1250 | FS | In Progress | Not Started | 1
P2543-R01-Oct24..4.3.1.3.16.21.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57512 | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding & Back Filling | Padding | C-52-0304-CME06-1160 | C-52-0304-PL-CI-6000 | FF | In Progress | Not Started | 7
P2543-R01-Oct24..4.3.1.3.16.21.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57172 | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding & Back Filling | Padding | C-52-0304-CME06-1240 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.16.21.2.3.5 Re-Instatement of Entry & Exit PitCCOPL57832 | P2543-R01-Oct24..4.3.1.3.16.21.1.21 PaddingCCOPL52386 | Padding & Back Filling | Padding | C-52-0304-CME06-1320 | C-52-0304-PL-CI-6000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.17.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52958 | P2543-R01-Oct24..4.3.1.3.17.21.2.1.2 Tunneling & Jack UpCCOPL52960 | Trench Excavation | Bedding | C-52-0405-CME16-1000 | C-52-0405-CME16-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.1.2 Tunneling & Jack UpCCOPL52960 | P2543-R01-Oct24..4.3.1.3.17.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57452 | Bedding | Lowering | C-52-0405-CME16-1010 | C-52-0405-CME16-1020 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57452 | P2543-R01-Oct24..4.3.1.3.17.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57452 | Lowering | Section Tie-in Welding | C-52-0405-CME16-1020 | C-52-0405-CME16-1030 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57452 | P2543-R01-Oct24..4.3.1.3.17.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57452 | Section Tie-in Welding | NDT (Tie-in Joint) | C-52-0405-CME16-1030 | C-52-0405-CME16-1040 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57452 | P2543-R01-Oct24..4.3.1.3.17.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57452 | NDT (Tie-in Joint) | Ext. Joint Coating (Tie-in Joint) | C-52-0405-CME16-1040 | C-52-0405-CME16-1050 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57452 | P2543-R01-Oct24..4.3.1.3.17.21.2.1.4 HydrotestingCCOPL57462 | Ext. Joint Coating (Tie-in Joint) | Holiday Testing | C-52-0405-CME16-1050 | C-52-0405-CME16-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.2.1.4 HydrotestingCCOPL57462 | P2543-R01-Oct24..4.3.1.3.17.21.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57472 | Holiday Testing | Padding & Back Filling | C-52-0405-CME16-1060 | C-52-0405-CME16-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Receive at Site - Hot Bends for 52" Pipeline (50% to total Qty) | Section Tie-in Welding | ML1449-D11 | C-52-0405-PL-ME-4810 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Receive at Site - Hot Bends for 52" Pipeline (50% to total Qty) | Installation of Test Post for Crossing | ML1449-D11 | C-52-0405-PL-CA-5220 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Receive at Site - Hot Bends for 52" Pipeline (50% to total Qty) | FO - Cable Pulling/ Laying | ML1449-D11 | C-52-0405-PL-TE-8200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Receive at Site - Hot Bends for 52" Pipeline (50% to total Qty) | Cleaning & Gauging | ML1449-D11 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Receive at Site - Hot Bends for 52" Pipeline (50% to total Qty) | Gatch Laying & Levelling | ML1449-D11 | C-52-0405-PL-CI-6800 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | Receive at Site - Hot Bends for 52" Pipeline (50% to total Qty) | Pre-commissioning from BVS-04 to BVS-05 | ML1449-D11 | PRECOM-52-0405-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.2 Manufacturing & Delivery | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Receive at Site - Hot Bends for 52" Pipeline (50% to total Qty) | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | ML1449-D11 | ML1679-E13 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.18.21.1.16 Pipe Lowering & Tie-in / NDTCCOPL52456 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | Section Tie-in Welding | C-PER-1180 | C-52-0506-PL-ME-4810 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.18.21.4.4.1 CP Works (for Crossings)CCOP52EL51 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | Installation of Test Post for Crossing | C-PER-1180 | C-52-0506-PL-CA-5220 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.18.21.5.1 Telecom Works along PipelineCCOP52IC35 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | FO - Cable Pulling/ Laying | C-PER-1180 | C-52-0506-PL-TE-8200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | Cleaning & Gauging | C-PER-1180 | C-52-0506-PL-ME-7400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.18.21.1.25 BermingCCOPL52451 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | Gatch Laying & Levelling | C-PER-1180 | C-52-0506-PL-CI-6800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.2.8.3 Pre-commissioning from BVS-05 to BVS-06CPCPL52327.2 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | Pre-commissioning from BVS-05 to BVS-06 | C-PER-1180 | PRECOM-52-0506-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | Padding | C-PER-1180 | C-52-0506-PL-CI-6000 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | Complete construction of NDRC Road crossings - 52" Sales Gas Pipeline | C-PER-1180 | ML1679-E13 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.17.21.1.20 Pipe Lowering & Tie-in / NDTCCOPL52428 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | Section Tie-in Welding | C-PER-1180 | C-52-0405-PL-ME-4810 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.17.21.3.4.2 CP Works (for Crossings)CCOP52EL52 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | Installation of Test Post for Crossing | C-PER-1180 | C-52-0405-PL-CA-5220 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.17.21.4.1 Telecom Works along PipelineCCOP52IC36 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | FO - Cable Pulling/ Laying | C-PER-1180 | C-52-0405-PL-TE-8200 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | Cleaning & Gauging | C-PER-1180 | C-52-0405-PL-ME-7400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.17.21.1.25 BermingCCOPL52423 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | Gatch Laying & Levelling | C-PER-1180 | C-52-0405-PL-CI-6800 | FF | Completed | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.2.3.3.8.3 Pre-commissioning from BVS-04 to BVS-05CPCPL52327.3 | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 16 | Pre-commissioning from BVS-04 to BVS-05 | C-PER-1180 | PRECOM-52-0405-1000 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.18.40 Crossing Mechanical (TX-56) | P2543-R01-Oct24..4.3.1.3.17.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52958 | Trench Excavation | Trench Excavation | C-52-0405-CME08-1000 | C-52-0405-CME16-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57472 | P2543-R01-Oct24..4.3.1.3.17.21.1.22 PaddingCCOPL52414 | Padding & Back Filling | Padding | C-52-0405-CME16-1070 | C-52-0405-PL-CI-6000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.2.3.12.2.5.1 Entry & Exit Pit ConstructionCCOPL56906 | Trench Excavation | Trench Excavation | C-56-01HG-CME10-1000 | C-56-01HG-CME09-1080 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.2.5.5 Re-Instatement of Entry & Exit PitCCOPL57952 | P2543-R01-Oct24..4.3.1.2.3.12.1.41 Padding from KP 21.3 to HGCPCCOPL56251.2 | Padding & Back Filling | Padding | C-56-01HG-CME09-1150 | C-56-01HG-PL-CI-6200 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | Trench Excavation | Trench Excavation | C-56-HC01-CME01-1000 | C-56-HC01-CME02-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | Trench Excavation | Trench Excavation | C-56-HC01-CME02-1000 | C-56-HC01-CME03-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.34 Crossing Mechanical @ KP 0+281 to 0+905 (TX-05,06) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | Trench Excavation | Trench Excavation | C-56-HC01-CME03-1000 | C-56-HC01-CME04-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.35 Crossing Mechanical @ KP 1+093 to 1+152 (TX-07,08) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | Trench Excavation | Trench Excavation | C-56-HC01-CME04-1000 | C-56-HC01-CME05-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.36 Crossing Mechanical @ KP 1+907 to 3+782 (TX-09,10) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | Trench Excavation | Trench Excavation | C-56-HC01-CME05-1000 | C-56-HC01-CME06-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | Trench Excavation | Trench Excavation | C-56-HC01-CME06-1000 | C-56-HC01-CME07-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.38 Crossing Mechanical @ KP 6+288 (TX-12) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | Trench Excavation | Trench Excavation | C-56-HC01-CME07-1000 | C-56-HC01-CME08-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.39 Crossing Mechanical @ KP 6+869 (TX-13) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | Trench Excavation | Trench Excavation | C-56-HC01-CME08-1000 | C-56-HC01-CME09-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.40 Crossing Mechanical @ KP 9+004 (TX-14) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | Trench Excavation | Trench Excavation | C-56-HC01-CME09-1000 | C-56-HC01-CME10-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.41 Crossing Mechanical @ KP 10+019 (TX-15) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.42 Crossing Mechanical @ KP 10+466 (TX-16) | Trench Excavation | Trench Excavation | C-56-HC01-CME10-1000 | C-56-HC01-CME11-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | Trench Excavation | Trench Excavation | C-56-HC01-CME12-1000 | C-56-HC01-CME13-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.44 Crossing Mechanical @ KP 11+193 (TX-18) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | Trench Excavation | Trench Excavation | C-56-HC01-CME13-1000 | C-56-HC01-CME14-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.45 Crossing Mechanical @ KP 11+615 (TX-19) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | Trench Excavation | Trench Excavation | C-56-HC01-CME14-1000 | C-56-HC01-CME15-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.46 Crossing Mechanical @ KP 11+803 (TX-20) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | Trench Excavation | Trench Excavation | C-56-HC01-CME15-1000 | C-56-HC01-CME16-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.47 Crossing Mechanical @ KP 12+058 (TX-21) | P2543-R01-Oct24..4.3.1.2.2.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56922 | Trench Excavation | Trench Excavation | C-56-HC01-CME16-1000 | C-56-HC01-CME10-1090 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.2.2.1 Entry & Exit Pit ConstructionCCOPL56922 | P2543-R01-Oct24..4.3.1.2.2.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56918 | Trench Excavation | Trench Excavation | C-56-HC01-CME10-1090 | C-56-HC01-CME10-1170 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57252 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 Padding from KP 6 to KP 12.6CCOPL56211.2 | Padding & Back Filling | Padding | C-56-HC01-CME10-1160 | C-56-HC01-PL-CI-6200 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.2.2.12.2.3.5 Re-Instatement of Entry & Exit PitCCOPL57912 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.32 Padding from KP 6 to KP 12.6CCOPL56211.2 | Padding & Back Filling | Padding | C-56-HC01-CME10-1240 | C-56-HC01-PL-CI-6200 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.17.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52958 | P2543-R01-Oct24..4.3.1.3.17.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52910 | Trench Excavation | Trench Excavation | C-52-0405-CME16-1000 | C-52-0405-CME09-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52910 | P2543-R01-Oct24..4.3.1.3.17.21.2.5.1 Entry & Exit Pit ConstructionCCOPL52912 | Trench Excavation | Trench Excavation | C-52-0405-CME09-1000 | C-52-0405-CME10-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.5.1 Entry & Exit Pit ConstructionCCOPL52912 | P2543-R01-Oct24..4.3.1.3.17.21.2.7.1 Entry & Exit Pit ConstructionCCOPL52918 | Trench Excavation | Trench Excavation | C-52-0405-CME10-1000 | C-52-0405-CME11-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.1.20.19 Crossing Mechanical (TX-66) | P2543-R01-Oct24..4.3.1.3.18.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52920 | Trench Excavation | Trench Excavation | C-52-0506-CME10-1000 | C-52-0506-CME25-2000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52920 | P2543-R01-Oct24..4.3.1.3.18.21.2.2.1 Entry & Exit Pit ConstructionCCOPL56972 | Trench Excavation | Trench Excavation | C-52-0506-CME25-2000 | C-52-0506-CME28-1080 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57052 | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding & Back Filling | Padding | C-52-0506-CME25-2070 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.18.21.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57012 | P2543-R01-Oct24..4.3.1.3.18.21.1.22 PaddingCCOPL52442 | Padding & Back Filling | Padding | C-52-0506-CME28-1150 | C-52-0506-PL-CI-6000 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | P2543-R01-Oct24..4.3.1.3.19.8.2.1.1 Entry & Exit Pit ConstructionCCOPL52964 | Trench Excavation | Trench Excavation | C-52-06CR-CME14-1000 | C-52-06CR-CME29-1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.2.1.5 Re-Instatement of Entry & Exit PitCCOPL52994 | P2543-R01-Oct24..4.3.1.3.19.8.1.23 PaddingCCOPL52470 | Padding & Back Filling | Padding | C-52-06CR-CME29-1150 | C-52-06CR-PL-CI-6000 | FF | Not Started | Not Started | 2
P2543-R01-Oct24..4.3.1.2.3.12.1.23.37 Crossing Mechanical (TX-48) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | Trench Excavation | Trench Excavation | C-56-01HG-CME10-1000 | C-56-HC01-CME01-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.17.21.2.7.1 Entry & Exit Pit ConstructionCCOPL52918 | P2543-R01-Oct24..4.3.1.3.18.21.1.20.10 Crossing Mechanical (TX-57) | Trench Excavation | Trench Excavation | C-52-0405-CME11-1000 | C-52-0506-CME01-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.18.21.2.2.1 Entry & Exit Pit ConstructionCCOPL56972 | P2543-R01-Oct24..4.3.1.3.19.8.1.12.14 Crossing Mechanical (TX-73) | Trench Excavation | Trench Excavation | C-52-0506-CME28-1080 | C-52-06CR-CME01-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.22 Crossing Mechanical (TX-81) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | Trench Excavation | Trench Excavation | C-52-06CR-CME09-1000 | C-52-06CR-CME13-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.12.26 Crossing Mechanical (TX-85) | P2543-R01-Oct24..4.3.1.3.19.8.2.1.1 Entry & Exit Pit ConstructionCCOPL52964 | Trench Excavation | Trench Excavation | C-52-06CR-CME13-1000 | C-52-06CR-CME29-1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.22.10 Crossing Mechanical (TX-04) | P2543-R01-Oct24..4.3.1.3.8.21.1.16.1 Crossing Mechanical (TX-08) | Trench Excavation | Trench Excavation | C-52-HG01-CME03-1000 | C-52-0102-CME01-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.2.5.1 Entry & Exit Pit ConstructionCCOPL52934 | P2543-R01-Oct24..4.3.1.3.16.21.1.17.15 Crossing Mechanical (TX-31B) | Trench Excavation | Trench Excavation | C-52-0102-CME06-1090 | C-52-0304-CME01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52956 | P2543-R01-Oct24..4.3.1.2.3.12.1.23.28 Crossing Mechanical (TX-22 to TX-24) | Trench Excavation | Trench Excavation | C-52-0304-CME06-1250 | C-56-01HG-CME01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.32 Crossing Mechanical @ KP 0+151 to 0+172 (TX-01,02) | P2543-R01-Oct24..4.3.1.2.3.12.2.5.1 Entry & Exit Pit ConstructionCCOPL56906 | Trench Excavation | Trench Excavation | C-56-HC01-CME01-1000 | C-56-01HG-CME09-1080 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.3.12.2.5.1 Entry & Exit Pit ConstructionCCOPL56906 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.33 Crossing Mechanical @ KP 0+198 to 0+233 (TX-03,04) | Trench Excavation | Trench Excavation | C-56-01HG-CME09-1080 | C-56-HC01-CME02-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.2.2.12.2.3.1 Entry & Exit Pit ConstructionCCOPL56918 | P2543-R01-Oct24..4.3.1.3.19.8.1.12.23 Crossing Mechanical (TX-82) | Trench Excavation | Trench Excavation | C-56-HC01-CME10-1170 | C-52-06CR-CME10-1000 | FS | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.19.8.1.12.25 Crossing Mechanical (TX-84) | P2543-R01-Oct24..4.3.1.3.19.8.1.12.27 Crossing Mechanical (TX-89) | Trench Excavation | Trench Excavation | C-52-06CR-CME12-1000 | C-52-06CR-CME14-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | P2543-R01-Oct24..4.3.1.3.2.21.1.20.5 Crossing Manual @ KP 6+258 to 6+308 (PX-04,CX-08) | Trench Excavation-Lot1 | Excavation (Manual-Trial Pit) | C-52-HG01-PL-CI-2400 | C-52-HG01-CMA02-0970 | FS | Completed | Not Started | 50
P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | Excavation (Manual-Trial Pit) | Excavation (Manual-Trial Pit) | C-52-HG01-CMA04-0970 | C-52-HG01-CMA06-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.16 Automatic WeldingCCOPL56207 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.10 Excavation (incl Bedding) from Habshan complex to KP 6CCOPL56206.1 | Automatic Welding | Trench Excavation | C-56-HC01-PL-ME-3600 | C-56-HC01-PL-CI-2400 | FF | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.2.2.12.4.1.16 Automatic WeldingCCOPL56207 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.14 Excavation (incl Bedding) from KP 6 to KP 12.6CCOPL56206.2 | Automatic Welding | Trench Excavation | C-56-HC01-PL-ME-3600 | C-56-HC01-PL-CI-2600 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.17.21.1.23 BackfillingCCOPL52422 | P2543-R01-Oct24..4.3.1.3.5.21.1.24 Excavation Works for fence posts from BVS-04 to BVS-05CCOP52CS53.3 | Backfilling | Earth Works for Fence Foundation (BVS-04 to BVS-05) | C-52-0405-PL-CI-6400 | C-52-0405-FENCE-1010 | SS | Not Started | Not Started | 21
P2543-R01-Oct24..4.3.1.3.17.21.1.23 BackfillingCCOPL52422 | P2543-R01-Oct24..4.3.1.3.5.21.1.24 Excavation Works for fence posts from BVS-04 to BVS-05CCOP52CS53.3 | Backfilling | Earth Works for Fence Foundation (BVS-04 to BVS-05) | C-52-0405-PL-CI-6400 | C-52-0405-FENCE-1010 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | P2543-R01-Oct24..4.3.1.3.17.21.1.16.13 Crossing Manual @ KP 104+784 to 104+819 (FX-33,34,PX-32,CX-33) | Trench Excavation | Excavation (Manual-Trial Pit) | C-52-0405-PL-CI-2400 | C-52-0405-CMA23-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | P2543-R01-Oct24..4.3.1.3.17.21.1.14.19 Crossing Manual @ KP 107+927 (CX-43A) | Trench Excavation | Trench Excavation | C-52-0405-PL-CI-2400 | C-52-0405-CMA08-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | P2543-R01-Oct24..4.3.1.3.17.21.1.17.6 Crossing Manual @ KP 100+906 (FX-22) | Trench Excavation | Trench Excavation | C-52-0405-PL-CI-2400 | C-52-0405-CMA27-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | P2543-R01-Oct24..4.3.1.3.17.21.1.14.9 Crossing Manual @ KP 104+057 to 104+084 (CX-X1,X2, FX-27,28,29) | Trench Excavation | Excavation (Manual-Trial Pit) | C-52-0405-PL-CI-2400 | C-52-0405-CMA03-0970 | SS | Not Started | Not Started | 3
P2543-R01-Oct24..4.3.1.3.19.8.1.26 Test Stations & Anode BedsCCOP52EL48 | P2543-R01-Oct24..4.3.1.3.19.8.1.21 CP Works TemporaryCCOP52EL49 | Installation of Temp. Anode | Installation of CP Test Post | C-52-06CR-PL-CA-5600 | C-52-06CR-PL-CA-5200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 12 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 5 | C-PER-1460 | C-PER-1390 | SS | In Progress | Not Started | 7
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 3 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 11 | C-PER-1370 | C-PER-1450 | SS | Not Started | Not Started | 7
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 2 | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 3 | C-PER-1360 | C-PER-1370 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Re-Issue for Approval - Detailed crossing drawings - 56" | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 13 | HE-PL-2890 | C-PER-1470 | SS | Completed | Not Started | 7
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Re-Issue for Approval - Detailed crossing drawings - 56" | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 8 | HE-PL-2890 | C-PER-1420 | FF | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.12.5 Layout, Elevation & Finishing for E&I Building at Habshan complex | P2543-R01-Oct24..1.EN.12.7 Plumbing & Drainage Layout for E&I Building at Sweihan CRS | Issue ICR-Layout, Elevation & Finishing for E&I Building at Habshan complex | Issue ICR-Plumbing & Drainage Layout for E&I Building at Sweihan CRS | HE-BL-1230 | HE-BL-1330 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.3 Hazardous Area Register | P2543-R01-Oct24..ML.EN Detail Engineering | Final Issue for Design/ Construction-Hazardous Area Register | Completion of all Detailed Engineering | HE-EL-5520 | ML1219-B29 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.4.21 HAZOP close out report | Issue ICR- HAZOP reviews Report for all areas | Issue ICR- HAZOP Close Out Report | HE-HS-0670 | HE-HS-0730 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.13 HAZOP Review Report | P2543-R01-Oct24..1.EN.4.21 HAZOP close out report | Final Issue for Design/ Construction-HAZOP Review Report | Final Issue for Design/ Construction-HAZOP close out report | HE-HS-0710 | HE-HS-0770 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.4.23 ISD Closeout Report | P2543-R01-Oct24..1.EN.4.12 PHSER Report | Final Issue for Design/ Construction- ISD Closeout Report | Final Issue for Design/ Construction-PHSER Report | HE-HS-1340 | HE-HS-0890 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.PM.1 Smart Plant | P2543-R01-Oct24..4.4.AB.2 Final Documentation | Final Issue for Design/ Construction-Smart Plant | General | HC-GN-290 | CAB-5290 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.5.2.4 Datasheet for PIG LAUNCHER (607-V-603) 56" | P2543-R01-Oct24..4.4.AB.1 Discipline wise As-Built Documentation | Final Issue for Design/ Construction-Datasheet for PIG LAUNCHER (607-V-603) | Mechanical | HE-ME-450 | CAB-4430 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.4.15 Datasheet for Piping Special Items | P2543-R01-Oct24..1.EN.7.8.2 Material Requisition for Piping Special Items | Final Issue for Design/ Construction-Datasheet for Piping Special Items | Final Issue for Design/ Construction-Material Requisition for Piping Special Items | HE-PI-1310 | HE-PI-3720 | FF | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.16 Pipeline Support Schdule | P2543-R01-Oct24..1.EN.1.32 Crossing Schedule - 56" | Final Issue for Design/ Construction- Pipeline Support Schedule | Final Issue for Design/ Construction-Crossing Schedule - 56" | HE-PL-3820 | HE-PL-2970 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.10.A21121 Typical Inter Connection Diagram for Pig Launcher/Receiver | P2543-R01-Oct24..1.EN.10.A2112111 Optical Power Link Loss Calculation For SDH / FOC System | Issue ICR- Typical Inter Connection Diagram for Pig Launcher/Receiver | Issue ICR- Optical Power Link Loss Calculation For SDH / FOC System | HE-TL-1050 | HE-TL-1150 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.42 Civil MTO | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Issued - Civil MTO 1 | Issued - Civil MTO 2 | HE-CS-1510 | HE-CS-1550 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.7.2.1 TBE for Check Valves | P2543-R01-Oct24..1.EN.7.12 Piping Stress Analysis & Report | Final Issue for Design/ Construction-TBE for Check Valves | Final Issue for Design/ Construction-Piping Stress Analysis & Report | HE-PI-3770 | HE-PI-1180 | FF | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.8.28 Calculation for Pig launcher and receiver foundations | P2543-R01-Oct24..ML.EN Detail Engineering | Issued for Review - Calculation for Pig launcher and receiver foundations | Issue Civil / Structural Drawings for Launcher/ Receiver facilities | HE-CS-0550 | ML1199-B24 | FF | Completed | Completed | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | NOC & Permits-BVS01-52" | Earth Works for Equipment Foundations & Hard Stand Area | C-PER-1580 | C-52-598-01-CI-1010 | FS | Completed | Not Started | 20
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | NOC & Permits-BVS02-52" | Earth Works for Equipment Foundations & Hard Stand Area | C-PER-1590 | C-52-598-02-CI-1010 | FS | In Progress | Not Started | 25
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.13.21.1.1 Earthworks, Site Preparation, Site GradingCCOB552C33 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Earth Works for Equipment Foundations & Hard Stand Area | HE-CS-0470 | C-52-598-02-CI-1010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Earth Works for Equipment Foundations & Hard Stand Area | HE-CS-0470 | C-52-598-03-CI-1010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.12.21.1.1 Earthworks, Site Preparation, Site GradingCCOB452C32 | NOC & Permits-BVS03-52" | Earth Works for Equipment Foundations & Hard Stand Area | C-PER-1600 | C-52-598-03-CI-1010 | FS | In Progress | Not Started | 30
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.11.21.1.1 Earthworks, Site Preparation, Site GradingCCOB352C31 | NOC & Permits-BVS04-52" | Earth Works for Equipment Foundations & Hard Stand Area | C-PER-1610 | C-52-598-04-CI-1010 | FS | In Progress | Not Started | 35
P2543-R01-Oct24..4.3.1.2.3.12.1.8 Surveying from KP 21.3 to HGCPCCOPL56247.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.12 Cut & Fill from KP 21.3 to HGCPCCOPL56248.2 | Survey Marking | Cut & Fill (@ Non-Sabkha) | C-56-01HG-PL-CI-1200 | C-56-01HG-PL-CI-1600 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.1 Construction NOC's | P2543-R01-Oct24..4.3.1.2.3.12.1.11 Sabkha Pad- Gatch LayingCCOPL56241.1 | Construction NOC from Musanada | Sabka Gatch Laying (Including ROW) - Layer 1 | C-GOV-1300 | C-56-01HG-PL-CI-2000 | FF | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.28 Overall Pipeline Route Map - 56" | P2543-R01-Oct24..4.3.1.2.2.12.4.1.10 Excavation (incl Bedding) from Habshan complex to KP 6CCOPL56206.1 | Final Issue for Design/ Construction-Overall Pipeline Route Map - 56" | Trench Excavation | HE-PL-0170 | C-56-HC01-PL-CI-2400 | FS | Completed | Not Started | 0
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Issue ICR - Detailed crossing drawings-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 1 | HE-PL-2990 | C-PER-1020 | FS | Completed | In Progress | 0
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Issue ICR - Detailed crossing drawings-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 3 | HE-PL-2990 | C-PER-1040 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Issue ICR - Detailed crossing drawings-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 4 | HE-PL-2990 | C-PER-1050 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Issue ICR - Detailed crossing drawings-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 5 | HE-PL-2990 | C-PER-1060 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Issue ICR - Detailed crossing drawings-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 7 | HE-PL-2990 | C-PER-1080 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Issue ICR - Detailed crossing drawings-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 8 | HE-PL-2990 | C-PER-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Issue ICR - Detailed crossing drawings-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 9 | HE-PL-2990 | C-PER-1100 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Issue ICR - Detailed crossing drawings-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 10 | HE-PL-2990 | C-PER-1110 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.3.14.21.1.1 Earthworks, Site Preparation, Site GradingCCOB652C33 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Earth Works for Equipment Foundations & Hard Stand Area | HE-CS-0470 | C-52-598-01-CI-1010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.4.15 TBE for Fire Fighting and Safety Equipment | P2543-R01-Oct24..1.EN.4.14 HAZOP Review Report (Vendor) | Issue ICR-TBE for Fire Fighting & Safety Eqpt | Issue ICR- HAZOP Review Report (Vendor) | HE-HS-1150 | HE-HS-1220 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.10.A32 Telecom cable schedule | P2543-R01-Oct24..1.EN.10.3 Telecom Typical Hookup | Issue ICR- Telecom Cable Schedule | Issue ICR-Telecom Typical Hookup | HE-TL-0790 | HE-TL-890 | FS | Completed | Completed | 0
P2543-R01-Oct24..PR.1.2.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | Ready for Dispatch of Pigging & Split Tee | Transportation/ Custom Clearance/ Delivery at site of Pigging & Split Tee (Lot 1) | HM-PL-0810 | HM-PL-0830 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.2.3 Delivery & receipt at Site | Receipt at site and inspection of Pigging & Split Tee (Lot 1) | Receipt at site and inspection of Pigging & Split Tee (Lot 2) | HM-PL-0840 | HM-PL-1530 | FF | Not Started | Not Started | 6
P2543-R01-Oct24..PR.BK.4.2 Manufacturing & Ready for Dispatch | P2543-R01-Oct24..PR.BK.4.2 Manufacturing & Ready for Dispatch | 1st Piping Bulk material MTO | Final Piping Bulk material MTO | HM-PI-0010 | HM-PI-0020 | FF | Not Started | Not Started | 45
P2543-R01-Oct24..1.EN.8.27 Foundation for Launcher & Receivers | P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | Final Issue for Design/ Construction - Foundation Details Drg. at Habshan, HGCP & Sweihan | Earth Works for Equipment Foundations | HE-CS-0650 | C-56-PL-607-CI-1010 | FS | Not Started | Not Started | 25
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Earth Works for Equipment Foundations | HE-CS-0470 | C-56-PL-607-CI-1010 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.3 Civil GA Darawings | P2543-R01-Oct24..4.3.1.1.1.12.1.1 Earthworks, Site Preparation, Site Grading CCOHBCS200 | Final Issue for Design/ Construction-Civil GA Drawings | Earth Works for Equipment Foundations | HE-CS-1630 | C-56-PL-607-CI-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.9.17 Electrical Equipment Layout | P2543-R01-Oct24..4.3.1.1.1.12.1.6 Trenching for Electrical cables CCOHBCS205.1 | Final Issue for Design/ Construction-Electrical Equipment Layout | Electrical & Earthing Cable Trenching | HE-EL-0530 | C-56-PL-607-CI-1800 | FS | Completed | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.3 Concrete Works (Foundations for Equipments)CCOB252C34 | P2543-R01-Oct24..4.3.1.3.9.21.1.3 Concrete Works (Foundations for Equipment )CCOB152C32 | Concrete Works for Access Platform & Misc. Structural Foundations | Concrete Works for Access Platform & Misc. Structural Foundations | C-52-598-05-CI-1420 | C-52-598-06-CI-1420 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Receipt at site and inspection of Line Pipes - Lot 6 (Coated) | Survey Marking | HM-PL-0110 | C-4W-SVHG-PIPEL-1000 | FS | Not Started | Not Started | 15
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.6.4.12.6 Construction 4'' RTP Water LineCCOPL4"150 | Receipt at site and inspection of Line Pipes - Lot 6 (Coated) | Survey Marking | HM-PL-0110 | C-4W-SVHG-PIPEL-1000 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | Trench Excavation-Lot1 | Trench Excavation-Lot2 | C-52-HG01-PL-CI-2400 | C-52-HG01-PL-CI-2600 | FS | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.8 Excavation (incl Bedding)CCOPL52306 | P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | Bedding-Lot2 | Lowering-Lot2 | C-52-HG01-PL-CI-2610 | C-52-HG01-PL-ME-5000 | FF | In Progress | In Progress | 2
P2543-R01-Oct24..4.3.1.3.18.21.1.6 Cut & Fill in Sandy Area from BVS-05 to KP 126.2CCOPL52466.1 | P2543-R01-Oct24..4.3.1.3.18.21.1.8 Cut & Fill in Sandy Area from KP 126.2 to BVS-06CCOPL52466.2 | Cut & Fill (@ Non-Sabkha) | Cut & Fill (@ Non-Sabkha) | C-52-0506-PL-CI-1400 | C-52-0506-PL-CI-1600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Cleaning & Gauging | Cleaning & Gauging | C-52-0203-PL-ME-7400 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.1.8.3 Precommissioning Electrical Building Type-ICPCSW108 | P2543-R01-Oct24..ML Milestones | Precommissioning Electrical Building Type-I | Complete 100% Construction & Pre-commissioning | PRECOM-52-EB1-1000 | ML1100 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.2.2 Tunneling & Jack UpCCOPL58262 | P2543-R01-Oct24..4.3.1.3.8.21.2.4.2 Tunneling & Jack UpCCOPL52940 | Jacking of MTBM & RC Sleeves | Jacking of MTBM & RC Sleeves | C-52-0102-CNH09-1200 | C-52-0102-CNM07-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.4.2 Tunneling & Jack UpCCOPL52940 | P2543-R01-Oct24..4.3.1.3.2.21.2.3.2 Tunneling & Jack UpCCOPL58042 | Jacking of MTBM & RC Sleeves | Jacking of MTBM & RC Sleeves | C-52-0102-CNM07-1200 | C-52-HG01-CNM02-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.6.2 Tunneling & Jack UpCCOPL58002 | P2543-R01-Oct24..4.3.1.3.19.8.5.2.2 Tunneling & Jack UpCCOPL58122 | Jacking of MTBM & RC Sleeves | Jacking of MTBM & RC Sleeves | C-52-0102-CNM05-1200 | C-52-06CR-CNH30-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.5.2 Tunneling & Jack UpCCOPL58302 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.2 Tunneling & Jack UpCCOPL56932 | Jacking of MTBM & RC Sleeves | Jacking of MTBM & RC Sleeves | C-52-0405-CNH20-1200 | C-52-06CR-CNM31-1200 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.8.4.2 Tunneling & Jack UpCCOPL58142 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.2 Tunneling & Jack UpCCOPL56932 | Jacking of MTBM & RC Sleeves | Jacking of MTBM & RC Sleeves | C-52-0405-CNH19-1200 | C-52-06CR-CNM31-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.1 Entry & Exit Pit ConstructionCCOPL56910 | P2543-R01-Oct24..4.3.1.2.2.12.8.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL56920 | Sheet Piling for Driving & Receiving Pit | Sheet Piling for Driving & Receiving Pit | C-56-HC01-CNM03-1000 | C-56-HC01-CNH05-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | Transportation/ Custom Clearance/ Delivery at site of ROV/ GOV (1st Lot) | Transportation/ Custom Clearance/ Delivery at site of ROV/ GOV (2nd Lot) | HM-ME-0570 | HM-ME-2220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.34 Overall Pipeline Route Map - 52" | P2543-R01-Oct24..4.3.1.3.17.21.1.8 ROW Access RoadCCOPL52412 | Final Issue for Design/ Construction-Overall Pipeline Route Map - 52" | Non-Sabka ROW/Grading | HE-PL-0230 | C-52-0405-PL-CI-1800 | FF | Completed | In Progress | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52902 | P2543-R01-Oct24..4.3.1.3.2.21.2.3.1 Entry & Exit Pit ConstructionCCOPL52902 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-HG01-CNM02-1000 | C-52-HG01-CNM02-1010 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.12 Automatic WeldingCCOPL52392 | P2543-R01-Oct24..ML.CO1 Construction & Pre-Commissioning | Automatic Welding | Complete Pipeline welding - 52" Sales Gas Pipeline - 50% Welding | C-52-0304-PL-ME-3600 | ML1699-E15 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..PR.1.16.2.5 Lot 7 | P2543-R01-Oct24..PR.1.16.2.6 Lot 9 | Ready for Dispatch of Line Pipes (Coated) - Lot 7 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 9 | HM-PL-1190 | HM-PL-1240 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.1.1.12.4.5 Installation of ValvesCCOHBPI352 | P2543-R01-Oct24..4.3.2.1.1.3.1 PrecommissioningCPC-HBS500 | Installation of Valves/MOV/ROV | Precommissioning | C-56-PL-607-PI-1800 | PRECOM-56-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.3 Civil GA Darawings | P2543-R01-Oct24..1.EN.8.3 Civil GA Darawings | Review Company Comments - Civil GA Drawings | Re-Issue for Approval - Civil GA Drawings | HE-CS-1650 | HE-CS-1610 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.3 Civil GA Darawings | P2543-R01-Oct24..1.EN.8.3 Civil GA Darawings | Re-Issue for Approval - Civil GA Drawings | Obtain Company Approval - Civil GA Drawings | HE-CS-1610 | HE-CS-1620 | FS | Completed | Completed | 0
P2543-R01-Oct24..1.EN.9.6.1 TBE for LV Switchgear | P2543-R01-Oct24..1.1.2.25.23.1 Ordering | Receive Company Comments-TBE for LV Switchgear | Prepare TBE and Company approval for LV Switch Gear | HE-EL-2220 | HP-ME-1350 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.8.38 Pipe Sleeper layout and details | P2543-R01-Oct24..1.EN.8.42 Civil MTO | Re-Issue for Approval - Pipe Sleeper layout and details. | Issued - Civil MTO 2 | HE-CS-1410 | HE-CS-1550 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.1.2.25.24.1 Ordering | P2543-R01-Oct24..PR.26.LL.24.2 Manufacturing & Ready for Dispatch | Commercial Clarifications & Placement of PO for Lifting Equipment | Vendor Document Review of Filter Package | HP-ME-1370 | HM-ME-2070 | FS | Completed | In Progress | 0
P2543-R01-Oct24..PR.1.16.2.8 Lot 5 | P2543-R01-Oct24..PR.1.16.2.4 Lot 6 | Ready for Dispatch of Line Pipes (Coated) - Lot 5 | Packaging & Final Inspection-Line Pipes (Coated) - Lot 6 | HM-PL-1310 | HM-PL-1120 | FF | Not Started | Not Started | 5
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Line Pipes - Lot 4 (Coated) | Receive at Site - Coated / Painted Line pipes- 52" (50% to total Qty) | HM-PL-1450 | ML1509-D3 | FF | Completed | Completed | 0
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Line Pipes - Lot 6 (Coated) | Receive at Site - Coated / Painted Line pipes- 56" | HM-PL-0110 | ML1052-D1 | FF | Not Started | Not Started | 17
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..ML Milestones | Receipt at site and inspection of Line Pipes - Lot 7 (Coated) | Receive at Site - Coated / Painted Line pipes- 4" (Nitrogen & Water line) | HM-PL-0120 | ML1389-D2 | FF | Not Started | Not Started | 14
P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | P2543-R01-Oct24..PR.1.16.3 Delivery & receipt at Site | Receipt at site and inspection of Line Pipes - Lot 8 (Coated) | Receipt at site and inspection of Line Pipes - Lot 9 (Coated) | HM-PL-1470 | HM-PL-960 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.6.2.8 TBE for Junction Boxes | P2543-R01-Oct24..1.EN.6.A271 Instrument Termination Drawings | Final Issue for Design/ Construction-TBE for Junction Boxes | Final Issue for Design/ Construction-Instrument Termination Drawings | HE-IC-2510 | HE-IC-3120 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..1.PM.12 Workshops | P2543-R01-Oct24..ML Milestones | PHSER V Workshop | Complete 75% Construction & Pre-commissioning | HE-WS-0290 | ML1090 | FF | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.4.1 Piping Pre-FabricationCCOB352P051 | P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | Piping Pre-Fabrication | Pipeline Trench Preparation (Including Excavation & Sand Bedding) | C-52-598-04-PI-1000 | C-52-598-04-PL-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Receipt at site and inspection of ROV/ GOV (1st Lot) | Installation of Valves & GOV | HM-ME-0580 | C-52-598-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | Receipt at site and inspection of ROV/ GOV (1st Lot) | Installation of ROV | HM-ME-0580 | C-52-598-01-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | Receipt at site and inspection of ROV/ GOV (1st Lot) | Installation of Valves & GOV | HM-ME-0580 | C-52-598-02-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | Receipt at site and inspection of ROV/ GOV (1st Lot) | Installation of ROV | HM-ME-0580 | C-52-598-02-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | Receipt at site and inspection of ROV/ GOV (1st Lot) | Installation of Valves & GOV | HM-ME-0580 | C-52-598-03-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | Receipt at site and inspection of ROV/ GOV (1st Lot) | Installation of ROV | HM-ME-0580 | C-52-598-03-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | Receipt at site and inspection of ROV/ GOV (1st Lot) | Installation of Valves & GOV | HM-ME-0580 | C-52-598-04-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | Receipt at site and inspection of ROV/ GOV (1st Lot) | Installation of ROV | HM-ME-0580 | C-52-598-04-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | Receipt at site and inspection of ROV/ GOV (1st Lot) | Installation of Valves & GOV | HM-ME-0580 | C-52-598-05-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | Receipt at site and inspection of ROV/ GOV (1st Lot) | Installation of ROV | HM-ME-0580 | C-52-598-05-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | Receipt at site and inspection of ROV/ GOV (1st Lot) | Installation of Valves & GOV | HM-ME-0580 | C-52-598-06-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | Receipt at site and inspection of ROV/ GOV (1st Lot) | Installation of ROV | HM-ME-0580 | C-52-598-06-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | Receipt at site and inspection of ROV/ GOV (1st Lot) | Installation of Valves/MOV/ROV | HM-ME-0580 | C-52-PR-839-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | Receipt at site and inspection of ROV/ GOV (1st Lot) | Installation of Valves & GOV | HM-ME-0580 | C-56-591-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | Receipt at site and inspection of ROV/ GOV (1st Lot) | Installation of ROV | HM-ME-0580 | C-56-591-01-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Installation of Valves & GOV | HM-ME-2210 | C-56-591-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Installation of ROV | HM-ME-2210 | C-56-591-01-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Installation of Valves/MOV/ROV | HM-ME-2210 | C-52-PR-839-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Installation of Valves & GOV | HM-ME-2210 | C-52-598-06-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Installation of ROV | HM-ME-2210 | C-52-598-06-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Installation of Valves & GOV | HM-ME-2210 | C-52-598-05-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Installation of ROV | HM-ME-2210 | C-52-598-05-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Installation of Valves & GOV | HM-ME-2210 | C-52-598-04-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Installation of ROV | HM-ME-2210 | C-52-598-04-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Installation of Valves & GOV | HM-ME-2210 | C-52-598-03-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Installation of ROV | HM-ME-2210 | C-52-598-03-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Installation of Valves & GOV | HM-ME-2210 | C-52-598-02-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Installation of ROV | HM-ME-2210 | C-52-598-02-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Installation of Valves & GOV | HM-ME-2210 | C-52-598-01-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.10.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.5.1 Pipeline Works @ BVS-1 (Entry & Exit)CCOPL52552 | Receipt at site and inspection of ROV/ GOV (2nd Lot) | Installation of ROV | HM-ME-2210 | C-52-598-01-PL-1060 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.4.5 Installation of ValvesCCOB152P090 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Installation of Valves & GOV | Precommissioning BVS-6 | C-52-598-06-PI-1800 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.9.21.5.1 Pipeline Works @ BVS-6 (Entry & Exit)CCOPL52502 | P2543-R01-Oct24..4.3.2.3.1.8.1 Precommissioning BVS-6CPCB15210 | Installation of ROV | Precommissioning BVS-6 | C-52-598-06-PL-1060 | PRECOM-52-59806-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.4.5 Installation of ValvesCCOB252P090 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Installation of Valves & GOV | Precommissioning BVS-5 | C-52-598-05-PI-1800 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.5.1 Pipeline Works @ BVS-5 (Entry & Exit)CCOPL52512 | P2543-R01-Oct24..4.3.2.3.2.8.1 Precommissioning BVS-5CPCB25210 | Installation of ROV | Precommissioning BVS-5 | C-52-598-05-PL-1060 | PRECOM-56-59805-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.4.5 Installation of ValvesCCOB352P091 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Installation of Valves & GOV | Precommissioning BVS-4 | C-52-598-04-PI-1800 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.5.1 Pipeline Works @ BVS-4 (Entry & Exit)CCOPL52522 | P2543-R01-Oct24..4.3.2.3.3.8.1 Precommissioning BVS-4CPCB35210 | Installation of ROV | Precommissioning BVS-4 | C-52-598-04-PL-1060 | PRECOM-56-59804-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.4.5 Installation of ValvesCCOB452P091 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Installation of Valves & GOV | Precommissioning BVS-3 | C-52-598-03-PI-1800 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.12.21.5.1 Pipeline Works @ BVS-3 (Entry & Exit)CCOPL52532 | P2543-R01-Oct24..4.3.2.3.4.8.2 Precommissioning BVS-3CPCB45210 | Installation of ROV | Precommissioning BVS-3 | C-52-598-03-PL-1060 | PRECOM-56-59803-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.4.5 Installation of ValvesCCOB552P091 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Installation of Valves & GOV | Precommissioning BVS-2 | C-52-598-02-PI-1800 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.13.21.5.1 Pipeline Works @ BVS-2 (Entry & Exit)CCOPL52542 | P2543-R01-Oct24..4.3.2.3.5.8.1 Precommissioning BVS-2CPCB55210 | Installation of ROV | Precommissioning BVS-2 | C-52-598-02-PL-1060 | PRECOM-56-59802-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.14.21.4.5 Installation of ValvesCCOB652P092 | P2543-R01-Oct24..4.3.2.3.6.8.2 Precommissioning BVS-1CPCB65211 | Installation of Valves & GOV | Precommissioning BVS-1 | C-52-598-01-PI-1800 | PRECOM-56-59801-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.5.1 Pipeline Works @ BVS-1 (Entry & Exit) CCOPL56362 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Installation of ROV | Precommissioning | C-56-591-01-PL-1060 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.1.12.4.5 Installation of Valves CCOB156P140 | P2543-R01-Oct24..4.3.2.2.8.3.1 PrecommissioningCPCB15610 | Installation of Valves & GOV | Precommissioning | C-56-591-01-PI-1800 | PRECOM-56-59101-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | Receipt at site and inspection of MOV (Lot 1) | Installation of Valves/MOV/ROV | HM-ME-0680 | C-52-PR-839-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Receipt at site and inspection of MOV (Lot 1) | Installation of Valves/MOV/ROV | HM-ME-0680 | C-52-PL-838-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.26 Installation of Valves CCOH56PI141 | Receipt at site and inspection of MOV (Lot 1) | Installation of Valves/MOV/ROV | HM-ME-0680 | C-56-PR-838-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.5 Installation of ValvesCCOHBPI352 | Receipt at site and inspection of MOV (Lot 1) | Installation of Valves/MOV/ROV | HM-ME-0680 | C-56-PL-607-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.1.1.12.4.5 Installation of ValvesCCOHBPI352 | Receipt at site and inspection of MOV (Lot 2) | Installation of Valves/MOV/ROV | HM-ME-2240 | C-56-PL-607-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.4.26 Installation of Valves CCOH56PI141 | Receipt at site and inspection of MOV (Lot 2) | Installation of Valves/MOV/ROV | HM-ME-2240 | C-56-PR-838-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.4.2 Piping Works -ErectionCCOSWPI503.2 | Receipt at site and inspection of MOV (Lot 2) | Installation of Valves/MOV/ROV | HM-ME-2240 | C-52-PR-839-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.9.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.4.3 Piping Works -ErectionCCOH52PI60.3 | Receipt at site and inspection of MOV (Lot 2) | Installation of Valves/MOV/ROV | HM-ME-2240 | C-52-PL-838-PI-1800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.17.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.8.2 PIDS SystemCCOB452I40 | Receipt at site and inspection of Leak Detection System | Installation of PIDS/ PLDS System | HM-ME-0280 | C-52-598-03-TE-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.2.21.1.26 CP Works TemporaryCCOP52EL56 | Receipt at site and inspection of CP System - Temporary Material | Installation of CP Test Post | HM-PL-0410 | C-52-HG01-PL-CA-5200 | FF | Not Started | In Progress | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.2.21.3.3.25 CP Works (for Crossings)CCOP52EL32 | Receipt at site and inspection of CP System - Temporary Material | Installation of Test Post for Crossing | HM-PL-0410 | C-52-HG01-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.8.21.1.21 CP Works TemporaryCCOP52EL35 | Receipt at site and inspection of CP System - Temporary Material | Installation of CP Test Post | HM-PL-0410 | C-52-0102-PL-CA-5200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | Receipt at site and inspection of CP System - Temporary Material | Installation of Test Post for Crossing | HM-PL-0410 | C-52-0102-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | Receipt at site and inspection of CP System - Temporary Material | Installation of Test Post for Crossing | HM-PL-0410 | C-52-0203-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.15.21.1.17 CP Works TemporaryCCOP52EL38 | Receipt at site and inspection of CP System - Temporary Material | Installation of CP Test Post | HM-PL-0410 | C-52-0203-PL-CA-5200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.6.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.3 Solar Power System CCOB156E44 | Receipt at site and inspection of Solar PV system | Installation of Solar Panel Structural Supports | HM-ME-1090 | C-56-591-01-EI-1210 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB552E55 | Receipt at site and inspection of CP System - Permanent Material | CP Cable Laying | HM-PL-0430 | C-52-598-02-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.7 E&I Cable Laying, Glanding & TerminationCCOB352E51 | Receipt at site and inspection of CP System - Permanent Material | CP Cable Laying | HM-PL-0430 | C-52-598-04-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.20.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.2 E&I Cable Laying, Glanding & Termination CCOB156E34 | Receipt at site and inspection of CP System - Permanent Material | CP Cable Laying | HM-PL-0430 | C-56-591-01-CA-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.8 F&G DevicesCCOB652E105 | Receipt at site and inspection of Gas Detectors (Lot 1) | Installation of F&G Devices | HM-ME-1490 | C-52-598-01-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.8 F&G DevicesCCOB552E105 | Receipt at site and inspection of Gas Detectors (Lot 1) | Installation of F&G Devices | HM-ME-1490 | C-52-598-02-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.8 F&G DevicesCCOB452E103 | Receipt at site and inspection of Gas Detectors (Lot 1) | Installation of F&G Devices | HM-ME-1490 | C-52-598-03-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.6 F&G DevicesCCOB352E92 | Receipt at site and inspection of Gas Detectors (Lot 1) | Installation of F&G Devices | HM-ME-1490 | C-52-598-04-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.6 F&G DevicesCCOB252E102 | Receipt at site and inspection of Gas Detectors (Lot 1) | Installation of F&G Devices | HM-ME-1490 | C-52-598-05-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.8 F&G DevicesCCOB152E106 | Receipt at site and inspection of Gas Detectors (Lot 1) | Installation of F&G Devices | HM-ME-1490 | C-52-598-06-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.6 F&G Devices CCOB156E74 | Receipt at site and inspection of Gas Detectors (Lot 1) | Installation of F&G Devices | HM-ME-1490 | C-56-591-01-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.14.21.6.8 F&G DevicesCCOB652E105 | Receipt at site and inspection of Gas Detectors (Lot 2) | Installation of F&G Devices | HM-ME-2310 | C-52-598-01-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.13.21.6.8 F&G DevicesCCOB552E105 | Receipt at site and inspection of Gas Detectors (Lot 2) | Installation of F&G Devices | HM-ME-2310 | C-52-598-02-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.12.21.6.8 F&G DevicesCCOB452E103 | Receipt at site and inspection of Gas Detectors (Lot 2) | Installation of F&G Devices | HM-ME-2310 | C-52-598-03-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.11.21.6.6 F&G DevicesCCOB352E92 | Receipt at site and inspection of Gas Detectors (Lot 2) | Installation of F&G Devices | HM-ME-2310 | C-52-598-04-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.10.21.6.6 F&G DevicesCCOB252E102 | Receipt at site and inspection of Gas Detectors (Lot 2) | Installation of F&G Devices | HM-ME-2310 | C-52-598-05-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.9.21.6.8 F&G DevicesCCOB152E106 | Receipt at site and inspection of Gas Detectors (Lot 2) | Installation of F&G Devices | HM-ME-2310 | C-52-598-06-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.1.12.6.6 F&G Devices CCOB156E74 | Receipt at site and inspection of Gas Detectors (Lot 2) | Installation of F&G Devices | HM-ME-2310 | C-56-591-01-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | Receipt at site and inspection of Gas Detectors (Lot 2) | Installation of F&G Device | HM-ME-2310 | C-56-PR-838-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.2 Field InstrumentsCCOH52EL72 | Receipt at site and inspection of Gas Detectors (Lot 2) | Installation of F&G Device | HM-ME-2310 | C-52-PL-838-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.5 F&G DevicesCCOSW52E10.42 | Receipt at site and inspection of Gas Detectors (Lot 2) | Installation of F&G Device | HM-ME-2310 | C-52-PR-839-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.1.21.6.2 Field InstrumentsCCOH52EL72 | Receipt at site and inspection of Gas Detectors (Lot 1) | Installation of F&G Device | HM-ME-1490 | C-52-PL-838-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.1.22.6.5 F&G DevicesCCOSW52E10.42 | Receipt at site and inspection of Gas Detectors (Lot 1) | Installation of F&G Device | HM-ME-1490 | C-52-PR-839-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.LL.18.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.2.21.12.6.31 Field Instruments CCOH56EL51 | Receipt at site and inspection of Gas Detectors (Lot 1) | Installation of F&G Device | HM-ME-1490 | C-56-PR-838-EI-2410 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..PR.26.1.2.3 Delivery & receipt at Site | P2543-R01-Oct24..4.3.1.3.4.2.22.2.2 Inergen SystemCCOSWME521 | Receipt at site and inspection of Fire Suppression System | Inergen System | HM-ME-1830 | C-52-EB1-ME-1200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 2 | HE-PL-2430 | C-PER-1360 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.29 Pipeline Alignment Sheets - 56" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets -56" | Trial pit, Crossing Methodology, NOC & Permits-56" Pipeline-NDRC 8 | HE-PL-2430 | C-PER-1420 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.35 Pipeline Alignment Sheets - 52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 1 | HE-PL-2490 | C-PER-1020 | SS | In Progress | In Progress | 0
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Issue ICR - Detailed crossing drawings-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 3 | HE-PL-2990 | C-PER-1040 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Issue ICR - Detailed crossing drawings-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 4 | HE-PL-2990 | C-PER-1050 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.36 Detailed crossing drawings-52" | P2543-R01-Oct24..4.1.7 Permits/Approvals | Issue ICR - Detailed crossing drawings-52" | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 8 | HE-PL-2990 | C-PER-1090 | FF | Completed | Completed | 0
P2543-R01-Oct24..1.EN.1.7 Pipeline Alignment Sheets - 4" Nitrogen | P2543-R01-Oct24..4.1.7 Permits/Approvals | Final Issue for Design/ Construction-Pipeline Alignment Sheets-4" | Trial pit, Crossing Methodology, NOC & Permits-4" Nitrogen Pipeline-NDRC 1 | HE-PL-2550 | C-PER-1480 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.1.30 Detailed crossing drawings - 56" | P2543-R01-Oct24..4.3.1.2.2.12.2.1.1 Entry & Exit Pit ConstructionCCOPL56904 | Final Issue for Design/ Construction-Detailed crossing drawings - 56" | Sheet Piling for Driving & Receiving Pit | HE-PL-2910 | C-56-HC01-CNM08-1000 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..4.3.1.3.14.21.1.3 Concrete Works (Foundations for Equipment)CCOB652C36 | Final Issue for Design/ Construction-TYPICAL LIGHTING POLE FOUNDATION DETAILS | Concrete Works for Light Pole, Fence & Gates Foundation | HE-CS-1010 | C-52-598-01-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.21 Typical Lighting Pole Foundation Details | P2543-R01-Oct24..4.3.1.2.1.12.1.11 Concrete Works (Foundations for Equipment) CCOB156C30 | Final Issue for Design/ Construction-TYPICAL LIGHTING POLE FOUNDATION DETAILS | Concrete Works for Light Pole, Fence & Gates Foundation | HE-CS-1010 | C-56-591-01-CI-1430 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | P2543-R01-Oct24..4.3.1.1.1.12.1.4 Concrete Works (Impact Wall ) CCOHBCS202.3 | Final Issue for Design/ Construction-TYPICAL GA AND RC DETAILS OF IMPACT WALL | Concrete Works (Impact Wall ) (Deleted) | HE-CS-1250 | C-56-PL-607-CI-1500 | SS | In Progress | Completed | 0
P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | P2543-R01-Oct24..4.3.1.2.21.12.1.12 Thrust Anchor Block/ Impact WallCCOH56CS33 | Final Issue for Design/ Construction-TYPICAL GA AND RC DETAILS OF IMPACT WALL | Concrete Works for Impact Wall | HE-CS-1250 | C-56-PR-838-CI-1500 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | P2543-R01-Oct24..4.3.1.3.4.1.22.1.4 Concrete Works (Impact wall)CCOSWCS302.3 | Final Issue for Design/ Construction-TYPICAL GA AND RC DETAILS OF IMPACT WALL | Concrete Works for Impact Wall | HE-CS-1250 | C-52-PR-839-CI-1500 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..1.EN.8.29 Typical GA and RC Details of Impact Wall | P2543-R01-Oct24..4.3.1.5.1.12.1.2 Concrete Works & Structural (Foundations for Equipment & Pipe Supports)CCOH4NCS65 | Final Issue for Design/ Construction-TYPICAL GA AND RC DETAILS OF IMPACT WALL | Concrete Works for Impact Wall | HE-CS-1250 | C-4N-HG-TPR-CI-1500 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.27 Pipe Stringing from KP 21.3 to HGCPCCOPL56250.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.16 Pipe Stringing from BVS-01 to KP 21.3CCOPL56250.1 | Stringing (KP 21.3 to HGCP) | Stringing (BVS-01 to KP 21.3) | C-56-01HG-PL-ME-3000 | C-56-01HG-PL-ME-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.16 Pipe Stringing from BVS-01 to KP 21.3CCOPL56250.1 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | Stringing (BVS-01 to KP 21.3) | Stringing (BVS-01 to HBCMPLX) | C-56-01HG-PL-ME-2800 | C-56-HC01-PL-ME-2800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.1.31 Automatic Welding from KP 21.3 to HGCPCCOPL56256.2 | P2543-R01-Oct24..4.3.1.2.3.12.1.20 Automatic Welding from BVS-01 to KP 21.3CCOPL56256.1 | Automatic Welding | Automatic Welding | C-56-01HG-PL-ME-3800 | C-56-01HG-PL-ME-3600 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.12 Automatic WeldingCCOPL52392 | P2543-R01-Oct24..4.3.1.2.3.12.1.31 Automatic Welding from KP 21.3 to HGCPCCOPL56256.2 | Automatic Welding | Automatic Welding | C-52-0304-PL-ME-3600 | C-56-01HG-PL-ME-3800 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | P2543-R01-Oct24..4.3.1.3.8.21.2.4.1 Entry & Exit Pit ConstructionCCOPL52938 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-0102-CNM07-1000 | C-52-0102-CNM07-1010 | FF | In Progress | Not Started | 18
P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | P2543-R01-Oct24..4.3.1.3.8.21.2.6.1 Entry & Exit Pit ConstructionCCOPL52932 | Sheet Piling for Driving & Receiving Pit | Driving & Receiving Pit Excavation | C-52-0102-CNM05-1000 | C-52-0102-CNM05-1010 | FF | Completed | In Progress | 7
P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | Lowering & Welding of Carrier Pipe | NDT, Coating & Holiday Inspection of Carrier Pipe | C-52-0102-CNH10-1070 | C-52-0102-CNH10-1080 | FF | Not Started | Not Started | 1
P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 Tunneling & Jack UpCCOPL58202 | NDT, Coating & Holiday Inspection of Carrier Pipe | Inner Grout b/w Main & RC Pipe | C-52-0102-CNH10-1080 | C-52-0102-CNH10-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.10 Automatic WeldingCCOPL52364 | P2543-R01-Oct24..ML Milestones | Automatic Welding | Complete 25% Construction & Pre-commissioning | C-52-0203-PL-ME-3600 | ML1070 | FF | Not Started | Not Started | 9
P2543-R01-Oct24..4.3.1.3.2.21.2.1.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57342 | P2543-R01-Oct24..4.3.1.3.2.21.2.2.3 Pipe Lowering, Welding, NDT & CoatingCCOPL57692 | Lowering & Welding of Carrier Pipe | Lowering & Welding of Carrier Pipe | C-52-HG01-CNM04-1400 | C-52-HG01-CNM03-1400 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.19.8.1.9 Excavation (incl Bedding)CCOPL52483 | P2543-R01-Oct24..4.3.1.3.19.8.2.3.1 Entry & Exit Pit ConstructionCCOPL52928 | Trench Excavation | Sheet Piling for Driving & Receiving Pit | C-52-06CR-PL-CI-2400 | C-52-06CR-CNM31-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.37 Crossing Mechanical @ KP 6+063 (TX-11) | P2543-R01-Oct24..4.3.1.2.2.12.4.1.28.43 Crossing Mechanical @ KP 10+930 (TX-17) | Trench Excavation | Trench Excavation | C-56-HC01-CME06-1000 | C-56-HC01-CME12-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.7 Cut & Fill in Sandy AreaCCOPL52438 | P2543-R01-Oct24..4.3.1.3.17.21.1.10 Pipe StringingCCOPL52413 | Cut & Fill (@ Non-Sabkha) | Stringing (BVS-04 to BVS-05) | C-52-0405-PL-CI-1400 | C-52-0405-PL-ME-2800 | SS | In Progress | In Progress | 7
P2543-R01-Oct24..4.3.1.5.4.12.1.8 ROW Access RoadCCOPL4"102 | P2543-R01-Oct24..4.3.1.5.2.3.12.1.1 Demolition Works (Paving)CCOH5CS100 | Sabka ROW/Grading | Demolition Works (Paving) | C-4N-H5HG-PIPEL-1800 | C-4N-H5-TPL-CI-0100 | FS | In Progress | Not Started | 28
P2543-R01-Oct24..4.3.1.3.13.21.1.5 Trenching for CablesCCOB552C40 | P2543-R01-Oct24..4.3.1.3.13.21.1.5 Trenching for CablesCCOB552C40 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-52-598-02-CI-1800 | C-52-598-02-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.10.21.1.1 Earthworks, Site Preparation, Site GradingCCOB252C31 | NOC & Permits-BVS05-52" | Earth Works for Equipment Foundations & Hard Stand Area | C-PER-1620 | C-52-598-05-CI-1010 | FS | In Progress | Not Started | 25
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.4.1.22.1.1 Earthworks, Site Preparation, Site GradingCCOSWCS300 | NOC & Permits-Sweihan CRS | Site Survey, Preparation & Grading Works | C-PER-1650 | C-52-PR-839-CI-1000 | FS | Not Started | Not Started | 25
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.3.1.3.4.2.22.1.1 Excavation (incl Bedding)CCOSWCS303 | NOC & Permits-Sweihan CRS | Site Survey, Preparation & Grading Works | C-PER-1650 | C-52-EB1-CI-1000 | FS | Not Started | Not Started | 25
P2543-R01-Oct24..4.3.1.3.12.21.1.6 Trenching for CablesCCOB452C39 | P2543-R01-Oct24..4.3.1.3.12.21.1.6 Trenching for CablesCCOB452C39 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-52-598-03-CI-1800 | C-52-598-03-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.5 Trenching for CablesCCOB352C38 | P2543-R01-Oct24..4.3.1.3.11.21.1.5 Trenching for CablesCCOB352C38 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-52-598-04-CI-1800 | C-52-598-04-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.10.21.1.5 Trenching for CablesCCOB252C38 | P2543-R01-Oct24..4.3.1.3.10.21.1.5 Trenching for CablesCCOB252C38 | Electrical & Earthing Cable Trenching | Instrument & Telecom Cable Trenching | C-52-598-05-CI-1800 | C-52-598-05-CI-1810 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.4.1.8 Cut & FillCCOPL56201 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.11 Pipe StringingCCOPL56205 | Cut & Fill (@ Non-Sabkha) | Stringing (BVS-01 to HBCMPLX) | C-56-HC01-PL-CI-1400 | C-56-HC01-PL-ME-2800 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.3.2.1 Backfilling & Reinstatement for CP (for Crossings)CCOP52CS47 | P2543-R01-Oct24..4.3.2.3.10.8.2 Pre-commissioning from HGCP to BVS-01CPCPL52327.7 | Backfilling & Reinstatement for CP (for Crossings) | Pre-commissioning from HGCP to BVS-01 | C-52-HG01-PIPEL-5260 | PRECOM-52-HG01-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.25 Pipe Lowering & Tie-in / NDTCCOPL52313 | P2543-R01-Oct24..4.3.1.3.2.21.1.29 Test Stations & Anode BedsCCOP52EL31 | Lowering-Lot2 | Installation of Temp. Anode | C-52-HG01-PL-ME-5000 | C-52-HG01-PL-CA-5600 | FF | In Progress | In Progress | 7
P2543-R01-Oct24..4.3.1.3.2.21.1.24 PaddingCCOPL52310 | P2543-R01-Oct24..4.3.1.3.2.21.4.1 Telecom Works along Pipeline CCOP52IC57 | Padding -Lot2 | FO - Cable Pulling/ Laying | C-52-HG01-PL-CI-6200 | C-52-HG01-PL-TE-8200 | FF | In Progress | In Progress | 1
P2543-R01-Oct24..4.3.1.3.8.21.1.19 Pipe Lowering & Tie-in / NDTCCOPL52344 | P2543-R01-Oct24..4.3.1.3.8.21.1.12 Cold BendsCCOPL52335 | Lowering | Cold Bends | C-52-0102-PL-ME-4800 | C-52-0102-PL-ME-3200 | FF | Not Started | In Progress | 1
P2543-R01-Oct24..4.3.1.3.2.21.2.4.5 Re-Instatement of Entry & Exit PitCCOPL58112 | P2543-R01-Oct24..4.3.2.3.10.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52320 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging ( Incl. 2+300 to 33+400, 0 to 2+300 ) | C-52-HG01-CNM01-1800 | C-52-HG01-PL-ME-7400 | FF | Not Started | Not Started | 7
P2543-R01-Oct24..4.3.1.3.8.21.2.5.5 Re-Instatement of Entry & Exit PitCCOPL57672 | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Padding & Back Filling | Cleaning & Gauging | C-52-0102-CME06-1160 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | P2543-R01-Oct24..4.3.1.3.11.21.6.1 Hybrid Passive Cooling Shelter InstallationCCOB352E50 | Concrete Works for Equipment Foundations & Hard Stand Area | Installation of Passive Cooling Shelter | C-52-598-04-CI-1400 | C-52-598-04-EI-1000 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.1 Entry & Exit Pit Preparation, Section ReadinessCCOPL52946 | P2543-R01-Oct24..4.3.1.3.8.21.3.1.2 Tunneling & Jack UpCCOPL58202 | Post Hydrotest/Gauging /Cleaning for NDRC Section | Inner Grout b/w Main & RC Pipe | C-52-0102-CNH10-1090 | C-52-0102-CNH10-1220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.11.21.1.3 Concrete Works (Foundations for Equipment )CCOB352C33 | P2543-R01-Oct24..4.3.1.3.11.21.1.8 Fences & Gates ConstructionCCOB352C36 | Concrete Works for Light Pole, Fence & Gates Foundation | Installation of Concrete Pillers for Boundary Wall | C-52-598-04-CI-1430 | C-52-598-04-CI-2200 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.15.21.1.15.5 Crossing Mechanical (RX-08) | Project Kick off Meeting | Road Diversion & Trench Excavation | ML1002 | C-52-0203-CME03-1000 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.16.21.2.1.1 Entry & Exit Pit ConstructionCCOPL52952 | Project Kick off Meeting | Trench Excavation | ML1002 | C-52-0304-CME06-1090 | FS | Completed | Completed | 0
P2543-R01-Oct24..ML Milestones | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | Project Kick off Meeting | Excavation (Manual-Trial Pit) | ML1002 | C-52-HG01-CMA03-0970 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | Bedding | Section Tie-in Welding | C-52-HG01-CMA03-1010 | C-52-HG01-CMA03-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | Bedding | Section Tie-in Welding | C-52-HG01-CMA04-1010 | C-52-HG01-CMA04-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | Bedding | Section Tie-in Welding | C-52-HG01-CMA06-1010 | C-52-HG01-CMA06-1030 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.1.1.12.1.4 Concrete Works (Impact Wall ) CCOHBCS202.3 | P2543-R01-Oct24..4.3.1.1.1.12.1.7 Fire Point Shelters CCOHBSS301 | Concrete Works (Impact Wall ) (Deleted) | Fire Point SheltersCCOHBSS301 (Deleted) | C-56-PL-607-CI-1500 | C-56-PL-607-CI-2400 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.1.7 Permits/Approvals | P2543-R01-Oct24..4.1.7 Permits/Approvals | Trial pit, Crossing Methodology, NOC & Permits-52" Pipeline-NDRC 12 | NOC & Permits-BVS01-52" | C-PER-1130 | C-PER-1580 | FS | Completed | Completed | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.6 Crossing Manual @ KP 25+127 (PX-05) | Lowering | Padding | C-52-HG01-CMA03-1020 | C-52-HG01-CMA03-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | P2543-R01-Oct24..4.3.1.3.2.21.1.20.7 Crossing Manual @ KP 28+089 (PX-06) | Lowering | Padding | C-52-HG01-CMA04-1020 | C-52-HG01-CMA04-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | P2543-R01-Oct24..4.3.1.3.2.21.1.23.3 Crossing Manual @ KP 1+477 (CX-01) | Lowering | Padding | C-52-HG01-CMA06-1020 | C-52-HG01-CMA06-1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | P2543-R01-Oct24..4.3.1.3.17.21.1.14.1 Crossing Manual @ KP 99+506 to 99+546 (CX-X1,X2) | Trench Excavation | Trench Excavation | C-52-0405-PL-CI-2400 | C-52-0405-CMA01-1000 | SS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.17.21.1.9 Excavation (incl Bedding)CCOPL52427 | P2543-R01-Oct24..4.3.1.3.17.21.1.16.7 Crossing Manual @ KP 103+615 to 103+631 (FX-23,24,PX-31) | Trench Excavation | Excavation (Manual-Trial Pit) | C-52-0405-PL-CI-2400 | C-52-0405-CMA22-1000 | SS | Not Started | Not Started | 30
P2543-R01-Oct24..4.3.1.2.3.12.2.3.5 Re-Instatement of Entry & Exit PitCCOPL57292 | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-56-01HG-CNM11-1800 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57632 | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-56-01HG-CNM12-1800 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.8.12 Site grading, road, drainage and fence layout | P2543-R01-Oct24..4.3.1.2.21.12.1.9 Earthworks, Site Preparation, Site GradingCCOH56CS30 | Final Issue for Design/ Construction-Site grading, road, drainage and fence layout | Site Survey, Preparation & Grading Works | HE-CS-0470 | C-56-PR-838-CI-1000 | FS | In Progress | Not Started | 20
P2543-R01-Oct24..4.3.1.2.2.12.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57592 | P2543-R01-Oct24..4.3.1.2.2.12.4.1.27 CP Works from Habshan complex to KP 6CCOP56EL21.1 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Installation of Test Post for Crossing | C-56-HC01-CNM08-1800 | C-56-HC01-PL-CA-5220 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57992 | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-56-01HG-CNM13-1800 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.3.12.6.4.3 Re-Instatement of Entry & Exit PitCCOPL58352 | P2543-R01-Oct24..4.3.2.2.2.3.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56234 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-56-01HG-CNH10-1800 | C-56-01HG-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57592 | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-56-HC01-CNM08-1800 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.2.4.5 Re-Instatement of Entry & Exit PitCCOPL57552 | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-56-HC01-CNM03-1800 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.1.3 Re-Instatement of Entry & Exit PitCCOPL58292 | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-56-HC01-CNH05-1800 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.2.3 Re-Instatement of Entry & Exit PitCCOPL58232 | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-56-HC01-CNH02-1800 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.2.2.12.8.3.3 Re-Instatement of Entry & Exit PitCCOPL58172 | P2543-R01-Oct24..4.3.2.2.2.3.1.6 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL56226 | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Cleaning & Gauging | C-56-HC01-CNH01-1800 | C-56-HC01-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57362 | P2543-R01-Oct24..ML Milestones | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete 50% Construction & Pre-commissioning | C-52-HG01-CNM04-1800 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.4.1 Telecom Works along Pipeline CCOP52IC57 | P2543-R01-Oct24..ML Milestones | Termination/Splicing @ BVS | Complete 50% Construction & Pre-commissioning | C-52-HG01-PL-TE-8210 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.2.5.5 Re-Instatement of Entry & Exit PitCCOPL57672 | P2543-R01-Oct24..ML Milestones | Padding & Back Filling | Complete 50% Construction & Pre-commissioning | C-52-0102-CME06-1160 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.4.4.2 CP Works (for Crossings)CCOP52EL55 | P2543-R01-Oct24..ML Milestones | Installation of CP JB's | Complete 75% Construction & Pre-commissioning | C-52-0102-PL-CA-5230 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.5.1 Telecom Works along PipelineCCOP52IC52 | P2543-R01-Oct24..ML Milestones | Termination/Splicing @ BVS | Complete 50% Construction & Pre-commissioning | C-52-0102-PL-TE-8210 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.17 CP Works TemporaryCCOP52EL38 | P2543-R01-Oct24..ML Milestones | Installation of CP Test Post | Complete 50% Construction & Pre-commissioning | C-52-0203-PL-CA-5200 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.12.5 Re-Instatement of Entry & Exit PitCCOPL57212 | P2543-R01-Oct24..ML Milestones | Padding & Back Filling | Complete 25% Construction & Pre-commissioning | C-52-0203-CME04-1070 | ML1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.2.1.5 Re-Instatement of Entry & Exit PitCCOPL57872 | P2543-R01-Oct24..ML Milestones | Padding & Back Filling | Complete 25% Construction & Pre-commissioning | C-52-0203-CME04-1150 | ML1070 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.3.1.5 Backfilling for CP (for Crossings)CCOP52CS40 | P2543-R01-Oct24..ML Milestones | Backfilling for CP (for Crossings) | Complete 50% Construction & Pre-commissioning | C-52-0203-PIPEL-5260 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | P2543-R01-Oct24..ML Milestones | Installation of CP JB's | Complete 50% Construction & Pre-commissioning | C-52-0304-PL-CA-5230 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.49 Backfilling for Fence from HGCP to BVS-01CCOP52CS56.7 | P2543-R01-Oct24..ML Milestones | Back Filliing of Fence Post Foundation (BVS-01 to HGCP) | Complete 50% Construction & Pre-commissioning | C-52-HG01-FENCE-1060 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.48 Fence Installation (Type3) from HGCP to BVS-01CCOP52CS57.7 | P2543-R01-Oct24..ML Milestones | Installation of Fence Mesh (BVS-01 to HGCP) | Complete 50% Construction & Pre-commissioning | C-52-HG01-FENCE-1070 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.6.4.12.6.5 Marker Post & Crash Barrier | P2543-R01-Oct24..ML Milestones | Installation of Crash Barriers (If any) | Complete 75% Construction & Pre-commissioning | C-4W-SVHG-PIPEL-7810 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2.1 Evaporation PondCCOPL52319 | P2543-R01-Oct24..ML Milestones | Evaporation Pond | Complete 50% Construction & Pre-commissioning | C-52-HG01-PL-CI-7200 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2.3 Dewatering, Swabbing, & DryingCCOPL52370 | P2543-R01-Oct24..ML Milestones | Swabing & Drying (Upto Dew Point Temp.) | Complete 75% Construction & Pre-commissioning | C-52-0203-PL-ME-7620 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.6.8.3 4'' Water Line from SV-03 (KP 96) to HGCP (1.8 km) | P2543-R01-Oct24..ML Milestones | Precommissioning | Complete 75% Construction & Pre-commissioning | PRECOM-4W-SVHG-1000 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.5.8.2 Pre-commissioning from BVS-02 to BVS-03CPCPL52327.5 | P2543-R01-Oct24..ML Milestones | Pre-commissioning from BVS-02 to BVS-03 | Complete 75% Construction & Pre-commissioning | PRECOM-52-0203-1000 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.6.8.1.1 Evaporation PondCCOPL52347 | P2543-R01-Oct24..ML Milestones | Evaporation Pond | Complete 50% Construction & Pre-commissioning | C-52-0102-PL-CI-7200 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2.4 ROW Restoration from BVS-01 to HGCP/Marker PostCCOPL52324.1 | P2543-R01-Oct24..ML Milestones | Installation of Marker Post/Sign Board | Complete 75% Construction & Pre-commissioning | C-52-HG01-PL-CI-7800 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2.5 ROW Restoration from BVS-01 to HGCP/Crash BarrierCCOPL52324.2 | P2543-R01-Oct24..ML Milestones | Installation of Crash Barriers (If any) | Complete 75% Construction & Pre-commissioning | C-52-HG01-PL-CI-7810 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.2.3.10.8.2.6 ROW Restoration from HGCP to KP 16.7 (Deleted SOW)CCOPL52324.3 | P2543-R01-Oct24..ML Milestones | Installation of Crash Barriers (If any) (Deleted SOW) | Complete 75% Construction & Pre-commissioning | C-52-HG01-PL-CI-7820 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.1 Sales Gas FilterCCOSWME506 | P2543-R01-Oct24..ML Milestones | Installation of Sales Gas Filter (839-F-104A) | Complete 75% Construction & Pre-commissioning | C-52-PR-839-ME-1800 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.4.1.22.3.1 Sales Gas FilterCCOSWME506 | P2543-R01-Oct24..ML Milestones | Installation of Sales Gas Filter (839-F-104B) | Complete 75% Construction & Pre-commissioning | C-52-PR-839-ME-1810 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.43 Fence Installation (Type3) from BVS-01 to BVS-02CCOP52CS57.6 | P2543-R01-Oct24..ML Milestones | Installation of Fence Mesh (BVS-02 to BVS-01) | Complete 75% Construction & Pre-commissioning | C-52-0102-FENCE-1070 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.5.21.1.44 Backfilling for Fence from BVS-01 to BVS-02CCOP52CS56.6 | P2543-R01-Oct24..ML Milestones | Back Filliing of Fence Post Foundation (BVS-02 to BVS-01) | Complete 75% Construction & Pre-commissioning | C-52-0102-FENCE-1060 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | P2543-R01-Oct24..ML Milestones | Termination/Splicing @ BVS | Complete 50% Construction & Pre-commissioning | C-52-0304-PL-TE-8210 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.4.1 Telecom Works along Pipeline CCOP52IC37 | P2543-R01-Oct24..ML Milestones | FO - Cable Pulling/ Laying | Complete 50% Construction & Pre-commissioning | C-52-0304-PL-TE-8200 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | P2543-R01-Oct24..ML Milestones | CIP/DCVG Survey | Complete 50% Construction & Pre-commissioning | C-52-0304-PL-CA-5250 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.3.3.1 CP Works (for Crossings)CCOP52EL53 | P2543-R01-Oct24..ML Milestones | Installation of CP TR | Complete 50% Construction & Pre-commissioning | C-52-0304-PL-CA-5240 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.3.2.5 Backfilling & Reinstatement for CP (for Crossings)CCOP52CS39 | P2543-R01-Oct24..ML Milestones | Backfilling & Reinstatement for CP (for Crossings) | Complete 50% Construction & Pre-commissioning | C-52-0304-PIPEL-5260 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | P2543-R01-Oct24..ML Milestones | Installation of Crash Barriers (If any) | Complete 75% Construction & Pre-commissioning | C-52-0304-PL-CI-7810 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.22 BermingCCOPL52395 | P2543-R01-Oct24..ML Milestones | Installation of Marker Post/Sign Board | Complete 75% Construction & Pre-commissioning | C-52-0304-PL-CI-7800 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.16.21.1.19 CP Works TemporaryCCOP52EL41 | P2543-R01-Oct24..ML Milestones | Glanding & Termination of Temp. CP S/m | Complete 75% Construction & Pre-commissioning | C-52-0304-PL-CA-5210 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.4.1 Telecom Works along PipelineCCOP52IC39 | P2543-R01-Oct24..ML Milestones | Termination/Splicing @ BVS | Complete 50% Construction & Pre-commissioning | C-52-0203-PL-TE-8210 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.3.2.6 CP Works (for Crossings)CCOP52EL54 | P2543-R01-Oct24..ML Milestones | CIP/DCVG Survey | Complete 50% Construction & Pre-commissioning | C-52-0203-PL-CA-5250 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.5 Marker Post & Crash Barrier | P2543-R01-Oct24..ML Milestones | Installation of Crash Barriers (If any) | Complete 50% Construction & Pre-commissioning | C-52-0203-PL-CI-7810 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.15.21.1.5 Marker Post & Crash Barrier | P2543-R01-Oct24..ML Milestones | Installation of Marker Post/Sign Board | Complete 50% Construction & Pre-commissioning | C-52-0203-PL-CI-7800 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.3.3 Re-Instatement of Entry & Exit PitCCOPL58332 | P2543-R01-Oct24..ML Milestones | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete 75% Construction & Pre-commissioning | C-52-0102-CNH08-1800 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.2.3 Re-Instatement of Entry & Exit PitCCOPL58272 | P2543-R01-Oct24..ML Milestones | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete 75% Construction & Pre-commissioning | C-52-0102-CNH09-1800 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.3.1.3 Re-Instatement of Entry & Exit PitCCOPL58212 | P2543-R01-Oct24..ML Milestones | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete 50% Construction & Pre-commissioning | C-52-0102-CNH10-1800 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.8.21.1.23 BermingCCOPL52339 | P2543-R01-Oct24..ML Milestones | Installation of Crash Barriers (If any) | Complete 75% Construction & Pre-commissioning | C-52-0102-PL-CI-7810 | ML1090 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.2.2.5 Re-Instatement of Entry & Exit PitCCOPL57712 | P2543-R01-Oct24..ML Milestones | Backfilling, Removal of Bracing Structure & Removal of Sheet Piles | Complete 50% Construction & Pre-commissioning | C-52-HG01-CNM03-1800 | ML1080 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..4.3.1.3.2.21.1.26 CP Works TemporaryCCOP52EL56 | P2543-R01-Oct24..ML Milestones | Glanding & Termination of Temp. CP S/m | Complete 50% Construction & Pre-commissioning | C-52-HG01-PL-CA-5210 | ML1080 | FS | In Progress | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.2.3.2.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52453 | Issue cleaning & gauging, hydrotesting , Drying, Purging, Pre-commissioning and commissioning Procedure (Final Issue) | Cleaning & Gauging | ML1004-A04 | C-52-0506-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.2.3.3.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52425 | Issue cleaning & gauging, hydrotesting , Drying, Purging, Pre-commissioning and commissioning Procedure (Final Issue) | Cleaning & Gauging | ML1004-A04 | C-52-0405-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.2.3.4.8.3.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52397 | Issue cleaning & gauging, hydrotesting , Drying, Purging, Pre-commissioning and commissioning Procedure (Final Issue) | Cleaning & Gauging | ML1004-A04 | C-52-0304-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.2.3.5.8.2.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52369 | Issue cleaning & gauging, hydrotesting , Drying, Purging, Pre-commissioning and commissioning Procedure (Final Issue) | Cleaning & Gauging | ML1004-A04 | C-52-0203-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.GE General | P2543-R01-Oct24..4.3.2.3.6.8.1.2 Final Cleaning & Gauging, Line Filling , & HydrotestingCCOPL52341 | Issue cleaning & gauging, hydrotesting , Drying, Purging, Pre-commissioning and commissioning Procedure (Final Issue) | Cleaning & Gauging | ML1004-A04 | C-52-0102-PL-ME-7400 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..1.EN.2.4 Constructability Review/ SIMOPS Report | P2543-R01-Oct24..4.4.1.2 Operation and Maintenance Manuals | Final Issue for Design/ Construction-Constructability Review/ SIMOPS Report | Re-Issue for Approval-Operation and Maintenance Manual | HE-ST-0050 | HE-CO-170 | FS | Not Started | Not Started | 0
P2543-R01-Oct24..ML.PR Procurement | P2543-R01-Oct24..ML.EN Detail Engineering | Completion of Procurement Services | Completion of all Detailed Engineering | ML1038-C20 | ML1219-B29 | FF | Not Started | Not Started | 0

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Day ShowAsPercentage=0 SmallScaleQtyType=QT_Hour DateFormat=dd/MM/yyyy CurrencyFormat=US Dollar